## Foundation Gap Monthly
Foundation Gap Monthly
Project | Source Type | Snapshot Limited | Month | Foundations Cumulative | Erections Cumulative | Gap Cumulative
TA 413 | detail | No | 2024-06 | 14 | 0 | 14
TA 413 | detail | No | 2024-07 | 34 | 0 | 34
TA 413 | detail | No | 2024-08 | 57 | 0 | 57
TA 413 | detail | No | 2024-09 | 97 | 2 | 95
TA 413 | detail | No | 2024-10 | 133 | 7 | 126
TA 413 | detail | No | 2024-11 | 157 | 9 | 148
TA 413 | detail | No | 2024-12 | 189 | 22 | 167
TA 413 | detail | No | 2025-01 | 224 | 47 | 177
TA 413 | detail | No | 2025-02 | 255 | 68 | 187
TA 413 | detail | No | 2025-03 | 274 | 93 | 181
TA 413 | detail | No | 2025-04 | 297 | 104 | 193
TA 413 | detail | No | 2025-05 | 307 | 104 | 203
TA 413 | detail | No | 2025-06 | 311 | 104 | 207
TA 413 | detail | No | 2025-07 | 313 | 112 | 201
TA 413 | detail | No | 2025-08 | 313 | 156 | 157
TA 413 | detail | No | 2025-09 | 313 | 221 | 92
TA 413 | detail | No | 2025-10 | 313 | 257 | 56
TA 413 | detail | No | 2025-11 | 313 | 281 | 32
TA 413 | detail | No | 2025-12 | 313 | 294 | 19
TA 413 | detail | No | 2026-01 | 314 | 300 | 14
TA 413 | detail | No | 2026-02 | 315 | 303 | 12
TA 413 | detail | No | 2026-03 | 316 | 303 | 13
TA 414 | detail | No | 2024-05 | 3 | 0 | 3
TA 414 | detail | No | 2024-08 | 4 | 0 | 4
TA 414 | detail | No | 2024-09 | 5 | 0 | 5
TA 414 | detail | No | 2024-11 | 10 | 0 | 10
TA 414 | detail | No | 2024-12 | 26 | 0 | 26
TA 414 | detail | No | 2025-01 | 45 | 0 | 45
TA 414 | detail | No | 2025-02 | 55 | 0 | 55
TA 414 | detail | No | 2025-03 | 72 | 0 | 72
TA 414 | detail | No | 2025-04 | 83 | 1 | 82
TA 414 | detail | No | 2025-05 | 90 | 1 | 89
TA 414 | detail | No | 2025-06 | 90 | 5 | 85
TA 414 | detail | No | 2025-08 | 95 | 9 | 86
TA 414 | detail | No | 2025-09 | 96 | 11 | 85
TA 414 | detail | No | 2025-10 | 109 | 12 | 97
TA 414 | detail | No | 2025-11 | 144 | 12 | 132
TA 414 | detail | No | 2025-12 | 213 | 28 | 185
TA 414 | detail | No | 2026-01 | 255 | 73 | 182
TA 414 | detail | No | 2026-02 | 281 | 123 | 158
TA 414 | detail | No | 2026-03 | 301 | 173 | 128
TA 414 | detail | No | 2026-04 | 319 | 207 | 112
TA 414 | detail | No | 2026-05 | 327 | 225 | 102
TA 416 | detail | No | 2024-04 | 1 | 0 | 1
TA 416 | detail | No | 2024-05 | 9 | 0 | 9
TA 416 | detail | No | 2024-06 | 23 | 0 | 23
TA 416 | detail | No | 2024-07 | 36 | 0 | 36
TA 416 | detail | No | 2024-08 | 55 | 0 | 55
TA 416 | detail | No | 2024-09 | 84 | 2 | 82
TA 416 | detail | No | 2024-10 | 143 | 11 | 132
TA 416 | detail | No | 2024-11 | 209 | 22 | 187
TA 416 | detail | No | 2024-12 | 267 | 47 | 220
TA 416 | detail | No | 2025-01 | 320 | 73 | 247
TA 416 | detail | No | 2025-02 | 374 | 102 | 272
TA 416 | detail | No | 2025-03 | 422 | 132 | 290
TA 416 | detail | No | 2025-04 | 471 | 167 | 304
TA 416 | detail | No | 2025-05 | 514 | 205 | 309
TA 416 | detail | No | 2025-06 | 533 | 229 | 304
TA 416 | detail | No | 2025-07 | 541 | 235 | 306
TA 416 | detail | No | 2025-08 | 556 | 243 | 313
TA 416 | detail | No | 2025-09 | 574 | 260 | 314
TA 416 | detail | No | 2025-10 | 582 | 273 | 309
TA 416 | detail | No | 2025-11 | 593 | 285 | 308
TA 416 | detail | No | 2025-12 | 601 | 292 | 309
TA 416 | detail | No | 2026-01 | 603 | 299 | 304
TA 416 | detail | No | 2026-02 | 605 | 300 | 305
TA 416 | detail | No | 2026-03 | 605 | 302 | 303
TA 418 | detail | No | 2024-01 | 2 | 0 | 2
TA 418 | detail | No | 2024-06 | 6 | 0 | 6
TA 418 | detail | No | 2024-07 | 18 | 0 | 18
TA 418 | detail | No | 2024-08 | 23 | 0 | 23
TA 418 | detail | No | 2024-09 | 34 | 0 | 34
TA 418 | detail | No | 2024-10 | 40 | 1 | 39
TA 418 | detail | No | 2024-11 | 50 | 5 | 45
TA 418 | detail | No | 2024-12 | 64 | 13 | 51
TA 418 | detail | No | 2025-01 | 80 | 21 | 59
TA 418 | detail | No | 2025-02 | 91 | 28 | 63
TA 418 | detail | No | 2025-03 | 104 | 34 | 70
TA 418 | detail | No | 2025-04 | 119 | 41 | 78
TA 418 | detail | No | 2025-05 | 133 | 48 | 85
TA 418 | detail | No | 2025-06 | 160 | 54 | 106
TA 418 | detail | No | 2025-07 | 175 | 62 | 113
TA 418 | detail | No | 2025-08 | 188 | 72 | 116
TA 418 | detail | No | 2025-09 | 200 | 82 | 118
TA 418 | detail | No | 2025-10 | 205 | 89 | 116
TA 418 | detail | No | 2025-11 | 217 | 97 | 120
TA 418 | detail | No | 2025-12 | 234 | 108 | 126
TA 418 | detail | No | 2026-01 | 243 | 118 | 125
TA 418 | detail | No | 2026-02 | 249 | 124 | 125
TA 418 | detail | No | 2026-04 | 249 | 125 | 124
TA 419 | detail | No | 2024-05 | 5 | 0 | 5
TA 419 | detail | No | 2024-06 | 13 | 0 | 13
TA 419 | detail | No | 2024-07 | 33 | 0 | 33
TA 419 | detail | No | 2024-08 | 40 | 0 | 40
TA 419 | detail | No | 2024-09 | 58 | 0 | 58
TA 419 | detail | No | 2024-10 | 76 | 0 | 76
TA 419 | detail | No | 2024-11 | 85 | 2 | 83
TA 419 | detail | No | 2024-12 | 98 | 16 | 82
TA 419 | detail | No | 2025-01 | 107 | 29 | 78
TA 419 | detail | No | 2025-02 | 113 | 46 | 67
TA 419 | detail | No | 2025-03 | 121 | 54 | 67
TA 419 | detail | No | 2025-04 | 136 | 70 | 66
TA 419 | detail | No | 2025-05 | 145 | 75 | 70
TA 419 | detail | No | 2025-06 | 153 | 79 | 74
TA 419 | detail | No | 2025-07 | 156 | 84 | 72
TA 419 | detail | No | 2025-08 | 158 | 92 | 66
TA 419 | detail | No | 2025-09 | 165 | 98 | 67
TA 419 | detail | No | 2025-10 | 170 | 106 | 64
TA 419 | detail | No | 2025-11 | 190 | 120 | 70
TA 419 | detail | No | 2025-12 | 216 | 157 | 59
TA 419 | detail | No | 2026-01 | 228 | 181 | 47
TA 419 | detail | No | 2026-02 | 232 | 183 | 49
TA 419 | detail | No | 2026-03 | 238 | 185 | 53
TA 419 | detail | No | 2026-04 | 256 | 195 | 61
TA 419 | detail | No | 2026-05 | 269 | 202 | 67
TA 421 | detail | No | 2024-01 | 1 | 0 | 1
TA 421 | detail | No | 2024-02 | 2 | 0 | 2
TA 421 | detail | No | 2024-03 | 4 | 0 | 4
TA 421 | detail | No | 2024-05 | 12 | 0 | 12
TA 421 | detail | No | 2024-06 | 34 | 0 | 34
TA 421 | detail | No | 2024-07 | 80 | 2 | 78
TA 421 | detail | No | 2024-08 | 115 | 8 | 107
TA 421 | detail | No | 2024-09 | 144 | 17 | 127
TA 421 | detail | No | 2024-10 | 184 | 31 | 153
TA 421 | detail | No | 2024-11 | 228 | 50 | 178
TA 421 | detail | No | 2024-12 | 308 | 65 | 243
TA 421 | detail | No | 2025-01 | 394 | 79 | 315
TA 421 | detail | No | 2025-02 | 473 | 94 | 379
TA 421 | detail | No | 2025-03 | 547 | 118 | 429
TA 421 | detail | No | 2025-04 | 607 | 142 | 465
TA 421 | detail | No | 2025-05 | 678 | 159 | 519
TA 421 | detail | No | 2025-06 | 735 | 169 | 566
TA 421 | detail | No | 2025-07 | 785 | 193 | 592
TA 421 | detail | No | 2025-08 | 809 | 216 | 593
TA 421 | detail | No | 2025-09 | 831 | 238 | 593
TA 421 | detail | No | 2025-10 | 852 | 256 | 596
TA 421 | detail | No | 2025-11 | 882 | 278 | 604
TA 421 | detail | No | 2025-12 | 911 | 299 | 612
TA 421 | detail | No | 2026-01 | 914 | 305 | 609
TA 505 | detail | No | 2015-11 | 1 | 0 | 1
TA 505 | detail | No | 2024-03 | 2 | 0 | 2
TA 505 | detail | No | 2024-04 | 4 | 0 | 4
TA 505 | detail | No | 2024-10 | 13 | 0 | 13
TA 505 | detail | No | 2024-11 | 39 | 0 | 39
TA 505 | detail | No | 2024-12 | 75 | 0 | 75
TA 505 | detail | No | 2025-01 | 105 | 4 | 101
TA 505 | detail | No | 2025-02 | 137 | 11 | 126
TA 505 | detail | No | 2025-03 | 158 | 22 | 136
TA 505 | detail | No | 2025-04 | 206 | 41 | 165
TA 505 | detail | No | 2025-05 | 253 | 65 | 188
TA 505 | detail | No | 2025-06 | 268 | 81 | 187
TA 505 | detail | No | 2025-07 | 270 | 90 | 180
TA 505 | detail | No | 2025-08 | 271 | 97 | 174
TA 505 | detail | No | 2025-09 | 281 | 127 | 154
TA 505 | detail | No | 2025-10 | 293 | 153 | 140
TA 505 | detail | No | 2025-11 | 309 | 187 | 122
TA 505 | detail | No | 2025-12 | 327 | 236 | 91
TA 505 | detail | No | 2026-01 | 344 | 276 | 68
TA 505 | detail | No | 2026-02 | 354 | 300 | 54
TA 505 | detail | No | 2026-03 | 362 | 321 | 41
TA 505 | detail | No | 2026-04 | 370 | 347 | 23
TA 505 | detail | No | 2026-05 | 373 | 354 | 19
TA 509 | detail | No | 2025-01 | 6 | 0 | 6
TA 509 | detail | No | 2025-02 | 20 | 0 | 20
TA 509 | detail | No | 2025-03 | 55 | 0 | 55
TA 509 | detail | No | 2025-04 | 104 | 0 | 104
TA 509 | detail | No | 2025-05 | 144 | 0 | 144
TA 509 | detail | No | 2025-06 | 159 | 0 | 159
TA 509 | detail | No | 2025-07 | 165 | 0 | 165
TA 509 | detail | No | 2025-08 | 171 | 0 | 171
TA 509 | detail | No | 2025-09 | 177 | 19 | 158
TA 509 | detail | No | 2025-10 | 188 | 30 | 158
TA 509 | detail | No | 2025-11 | 211 | 39 | 172
TA 509 | detail | No | 2025-12 | 229 | 59 | 170
TA 509 | detail | No | 2026-01 | 234 | 80 | 154
TA 509 | detail | No | 2026-02 | 240 | 111 | 129
TA 509 | detail | No | 2026-03 | 245 | 135 | 110
TA 509 | detail | No | 2026-04 | 258 | 181 | 77
TA 509 | detail | No | 2026-05 | 264 | 198 | 66
TA 510 | detail | No | 2025-02 | 4 | 0 | 4
TA 510 | detail | No | 2025-03 | 10 | 0 | 10
TA 510 | detail | No | 2025-04 | 16 | 0 | 16
TA 510 | detail | No | 2025-05 | 24 | 0 | 24
TA 510 | detail | No | 2025-06 | 25 | 0 | 25
TA 510 | detail | No | 2025-07 | 26 | 0 | 26
TA 510 | detail | No | 2025-08 | 27 | 0 | 27
TA 510 | detail | No | 2025-09 | 32 | 0 | 32
TA 510 | detail | No | 2025-10 | 33 | 0 | 33
TA 510 | detail | No | 2025-11 | 41 | 0 | 41
TA 510 | detail | No | 2025-12 | 49 | 0 | 49
TA 510 | detail | No | 2026-01 | 56 | 8 | 48
TA 510 | detail | No | 2026-02 | 63 | 17 | 46
TA 510 | detail | No | 2026-03 | 64 | 25 | 39
TA 510 | detail | No | 2026-04 | 78 | 29 | 49
TA 510 | detail | No | 2026-05 | 85 | 34 | 51
TA 512 | detail | No | 2025-02 | 3 | 0 | 3
TA 512 | detail | No | 2025-03 | 29 | 0 | 29
TA 512 | detail | No | 2025-04 | 53 | 0 | 53
TA 512 | detail | No | 2025-05 | 76 | 0 | 76
TA 512 | detail | No | 2025-06 | 103 | 0 | 103
TA 512 | detail | No | 2025-07 | 142 | 0 | 142
TA 512 | detail | No | 2025-08 | 168 | 6 | 162
TA 512 | detail | No | 2025-09 | 187 | 23 | 164
TA 512 | detail | No | 2025-10 | 211 | 36 | 175
TA 512 | detail | No | 2025-11 | 240 | 52 | 188
TA 512 | detail | No | 2025-12 | 276 | 82 | 194
TA 512 | detail | No | 2026-01 | 287 | 126 | 161
TA 512 | detail | No | 2026-02 | 291 | 170 | 121
TA 512 | detail | No | 2026-03 | 294 | 202 | 92
TA 512 | detail | No | 2026-04 | 301 | 217 | 84
TA 512 | detail | No | 2026-05 | 302 | 221 | 81
TA 513 | detail | No | 2025-03 | 3 | 0 | 3
TA 513 | detail | No | 2025-04 | 16 | 0 | 16
TA 513 | detail | No | 2025-05 | 36 | 0 | 36
TA 513 | detail | No | 2025-06 | 44 | 0 | 44
TA 513 | detail | No | 2025-07 | 54 | 0 | 54
TA 513 | detail | No | 2025-08 | 58 | 0 | 58
TA 513 | detail | No | 2025-09 | 65 | 2 | 63
TA 513 | detail | No | 2025-10 | 67 | 8 | 59
TA 513 | detail | No | 2025-11 | 70 | 14 | 56
TA 513 | detail | No | 2025-12 | 73 | 18 | 55
TA 513 | detail | No | 2026-01 | 74 | 20 | 54
TA 513 | detail | No | 2026-02 | 76 | 21 | 55
TA 513 | detail | No | 2026-03 | 77 | 27 | 50
TA 513 | detail | No | 2026-04 | 80 | 28 | 52
TA 513 | detail | No | 2026-05 | 84 | 29 | 55
TA 515 | missing | No | 2026-03 |  | 2
TA 601 | detail | No | 2025-03 | 0 | 1 | -1
TA 601 | detail | No | 2025-05 | 1 | 1 | 0
TA 601 | detail | No | 2025-08 | 3 | 1 | 2
TA 601 | detail | No | 2025-09 | 5 | 1 | 4
TA 601 | detail | No | 2025-10 | 13 | 1 | 12
TA 601 | detail | No | 2025-11 | 23 | 1 | 22
TA 601 | detail | No | 2025-12 | 46 | 4 | 42
TA 601 | detail | No | 2026-01 | 94 | 25 | 69
TA 601 | detail | No | 2026-02 | 140 | 54 | 86
TA 601 | detail | No | 2026-03 | 168 | 67 | 101
TA 601 | detail | No | 2026-04 | 184 | 70 | 114
TA 601 | detail | No | 2026-05 | 191 | 71 | 120
TA 602 | detail | No | 2025-09 | 1 | 0 | 1
TA 602 | detail | No | 2025-10 | 10 | 0 | 10
TA 602 | detail | No | 2025-11 | 40 | 0 | 40
TA 602 | detail | No | 2025-12 | 77 | 0 | 77
TA 602 | detail | No | 2026-01 | 97 | 0 | 97
TA 602 | detail | No | 2026-02 | 109 | 3 | 106
TA 602 | detail | No | 2026-03 | 114 | 14 | 100
TA 602 | detail | No | 2026-04 | 136 | 22 | 114
TA 602 | detail | No | 2026-05 | 143 | 40 | 103
TB 408 | missing | No | 2024-02 |  | 22
TB 408 | missing | No | 2024-03 |  | 42
TB 408 | missing | No | 2024-04 |  | 61
TB 408 | missing | No | 2024-05 |  | 75
TB 408 | missing | No | 2024-06 |  | 78
TB 408 | missing | No | 2024-07 |  | 80
TB 408 | missing | No | 2024-08 |  | 83
TB 408 | missing | No | 2024-09 |  | 99
TB 408 | missing | No | 2024-10 |  | 129
TB 408 | missing | No | 2024-11 |  | 159
TB 408 | missing | No | 2024-12 |  | 170
TB 408 | missing | No | 2025-01 |  | 186
TB 408 | missing | No | 2025-02 |  | 200
TB 408 | missing | No | 2025-03 |  | 213
TB 408 | missing | No | 2025-04 |  | 220
TB 408 | missing | No | 2025-05 |  | 222
TB 408 | missing | No | 2025-06 |  | 228
TB 408 | missing | No | 2025-07 |  | 251
TB 408 | missing | No | 2025-08 |  | 303
TB 408 | missing | No | 2025-09 |  | 350
TB 408 | missing | No | 2025-10 |  | 375
TB 408 | missing | No | 2025-11 |  | 408
TB 408 | missing | No | 2025-12 |  | 448
TB 408 | missing | No | 2026-01 |  | 459
TB 408 | missing | No | 2026-02 |  | 465
TB 408 | missing | No | 2026-03 |  | 475
TB 408 | missing | No | 2026-04 |  | 478
TB 408 | missing | No | 2026-05 |  | 479
TB 501 | detail | No | 2024-08 | 3 | 0 | 3
TB 501 | detail | No | 2024-09 | 10 | 0 | 10
TB 501 | detail | No | 2024-10 | 35 | 0 | 35
TB 501 | detail | No | 2024-11 | 61 | 0 | 61
TB 501 | detail | No | 2024-12 | 88 | 5 | 83
TB 501 | detail | No | 2025-01 | 109 | 21 | 88
TB 501 | detail | No | 2025-02 | 130 | 60 | 70
TB 501 | detail | No | 2025-03 | 139 | 100 | 39
TB 501 | detail | No | 2025-04 | 150 | 120 | 30
TB 501 | detail | No | 2025-05 | 168 | 138 | 30
TB 501 | detail | No | 2025-06 | 174 | 156 | 18
TB 501 | detail | No | 2025-07 | 175 | 169 | 6
TB 501 | detail | No | 2025-08 | 178 | 173 | 5
TB 501 | detail | No | 2025-09 | 186 | 173 | 13
TB 501 | detail | No | 2025-10 | 192 | 178 | 14
TB 501 | detail | No | 2025-11 | 199 | 193 | 6
TB 501 | detail | No | 2025-12 | 209 | 203 | 6
TB 501 | detail | No | 2026-01 | 218 | 212 | 6
TB 501 | detail | No | 2026-02 | 222 | 219 | 3
TB 501 | detail | No | 2026-03 | 226 | 226 | 0
TB 501 | detail | No | 2026-04 | 231 | 228 | 3
TB 501 | detail | No | 2026-05 | 231 | 230 | 1
TB 507 | detail | No | 2025-01 | 2 | 0 | 2
TB 507 | detail | No | 2025-02 | 22 | 0 | 22
TB 507 | detail | No | 2025-03 | 38 | 0 | 38
TB 507 | detail | No | 2025-04 | 51 | 0 | 51
TB 507 | detail | No | 2025-05 | 60 | 1 | 59
TB 507 | detail | No | 2025-06 | 85 | 2 | 83
TB 507 | detail | No | 2025-07 | 135 | 13 | 122
TB 507 | detail | No | 2025-08 | 187 | 24 | 163
TB 507 | detail | No | 2025-09 | 207 | 62 | 145
TB 507 | detail | No | 2025-10 | 215 | 105 | 110
TB 507 | detail | No | 2025-11 | 234 | 138 | 96
TB 507 | detail | No | 2025-12 | 247 | 163 | 84
TB 507 | detail | No | 2026-01 | 262 | 177 | 85
TB 507 | detail | No | 2026-02 | 274 | 184 | 90
TB 507 | detail | No | 2026-03 | 291 | 189 | 102
TB 507 | detail | No | 2026-04 | 311 | 198 | 113
TB 507 | detail | No | 2026-05 | 334 | 213 | 121
TB 605 | detail | No | 2025-08 | 1 | 0 | 1
TB 605 | detail | No | 2025-09 | 4 | 0 | 4
TB 605 | detail | No | 2025-10 | 19 | 0 | 19
TB 605 | detail | No | 2025-11 | 61 | 1 | 60
TB 605 | detail | No | 2025-12 | 118 | 4 | 114
TB 605 | detail | No | 2026-01 | 160 | 10 | 150
TB 605 | detail | No | 2026-02 | 202 | 55 | 147
TB 605 | detail | No | 2026-03 | 230 | 105 | 125
TB 605 | detail | No | 2026-04 | 256 | 157 | 99
TB 605 | detail | No | 2026-05 | 288 | 189 | 99
TB 608 | detail | No | 2025-10 | 2 | 0 | 2
TB 608 | detail | No | 2025-11 | 22 | 0 | 22
TB 608 | detail | No | 2025-12 | 56 | 0 | 56
TB 608 | detail | No | 2026-01 | 86 | 3 | 83
TB 608 | detail | No | 2026-02 | 116 | 7 | 109
TB 608 | detail | No | 2026-03 | 131 | 12 | 119
TB 608 | detail | No | 2026-04 | 133 | 21 | 112
TB 608 | detail | No | 2026-05 | 133 | 22 | 111

## Foundation Gap Weekly
Foundation Gap Weekly
Project | Source Type | Snapshot Limited | Week Start | Week End | Week | Foundations Cumulative | Erections Cumulative | Gap Cumulative
TA 413 | detail | No | 2024-06-02 | 2024-06-08 | 2024-06-02 to 2024-06-08 | 2 | 0 | 2
TA 413 | detail | No | 2024-06-09 | 2024-06-15 | 2024-06-09 to 2024-06-15 | 4 | 0 | 4
TA 413 | detail | No | 2024-06-16 | 2024-06-22 | 2024-06-16 to 2024-06-22 | 8 | 0 | 8
TA 413 | detail | No | 2024-06-23 | 2024-06-29 | 2024-06-23 to 2024-06-29 | 14 | 0 | 14
TA 413 | detail | No | 2024-06-30 | 2024-07-06 | 2024-06-30 to 2024-07-06 | 18 | 0 | 18
TA 413 | detail | No | 2024-07-07 | 2024-07-13 | 2024-07-07 to 2024-07-13 | 23 | 0 | 23
TA 413 | detail | No | 2024-07-14 | 2024-07-20 | 2024-07-14 to 2024-07-20 | 27 | 0 | 27
TA 413 | detail | No | 2024-07-21 | 2024-07-27 | 2024-07-21 to 2024-07-27 | 31 | 0 | 31
TA 413 | detail | No | 2024-07-28 | 2024-08-03 | 2024-07-28 to 2024-08-03 | 37 | 0 | 37
TA 413 | detail | No | 2024-08-04 | 2024-08-10 | 2024-08-04 to 2024-08-10 | 40 | 0 | 40
TA 413 | detail | No | 2024-08-11 | 2024-08-17 | 2024-08-11 to 2024-08-17 | 44 | 0 | 44
TA 413 | detail | No | 2024-08-18 | 2024-08-24 | 2024-08-18 to 2024-08-24 | 49 | 0 | 49
TA 413 | detail | No | 2024-08-25 | 2024-08-31 | 2024-08-25 to 2024-08-31 | 57 | 0 | 57
TA 413 | detail | No | 2024-09-01 | 2024-09-07 | 2024-09-01 to 2024-09-07 | 65 | 0 | 65
TA 413 | detail | No | 2024-09-08 | 2024-09-14 | 2024-09-08 to 2024-09-14 | 74 | 0 | 74
TA 413 | detail | No | 2024-09-15 | 2024-09-21 | 2024-09-15 to 2024-09-21 | 85 | 1 | 84
TA 413 | detail | No | 2024-09-22 | 2024-09-28 | 2024-09-22 to 2024-09-28 | 94 | 2 | 92
TA 413 | detail | No | 2024-09-29 | 2024-10-05 | 2024-09-29 to 2024-10-05 | 104 | 3 | 101
TA 413 | detail | No | 2024-10-06 | 2024-10-12 | 2024-10-06 to 2024-10-12 | 113 | 4 | 109
TA 413 | detail | No | 2024-10-13 | 2024-10-19 | 2024-10-13 to 2024-10-19 | 122 | 6 | 116
TA 413 | detail | No | 2024-10-20 | 2024-10-26 | 2024-10-20 to 2024-10-26 | 129 | 7 | 122
TA 413 | detail | No | 2024-10-27 | 2024-11-02 | 2024-10-27 to 2024-11-02 | 133 | 7 | 126
TA 413 | detail | No | 2024-11-03 | 2024-11-09 | 2024-11-03 to 2024-11-09 | 137 | 7 | 130
TA 413 | detail | No | 2024-11-10 | 2024-11-16 | 2024-11-10 to 2024-11-16 | 141 | 7 | 134
TA 413 | detail | No | 2024-11-17 | 2024-11-23 | 2024-11-17 to 2024-11-23 | 150 | 7 | 143
TA 413 | detail | No | 2024-11-24 | 2024-11-30 | 2024-11-24 to 2024-11-30 | 157 | 9 | 148
TA 413 | detail | No | 2024-12-01 | 2024-12-07 | 2024-12-01 to 2024-12-07 | 163 | 10 | 153
TA 413 | detail | No | 2024-12-08 | 2024-12-14 | 2024-12-08 to 2024-12-14 | 170 | 11 | 159
TA 413 | detail | No | 2024-12-15 | 2024-12-21 | 2024-12-15 to 2024-12-21 | 178 | 14 | 164
TA 413 | detail | No | 2024-12-22 | 2024-12-28 | 2024-12-22 to 2024-12-28 | 183 | 19 | 164
TA 413 | detail | No | 2024-12-29 | 2025-01-04 | 2024-12-29 to 2025-01-04 | 191 | 24 | 167
TA 413 | detail | No | 2025-01-05 | 2025-01-11 | 2025-01-05 to 2025-01-11 | 199 | 30 | 169
TA 413 | detail | No | 2025-01-12 | 2025-01-18 | 2025-01-12 to 2025-01-18 | 206 | 33 | 173
TA 413 | detail | No | 2025-01-19 | 2025-01-25 | 2025-01-19 to 2025-01-25 | 217 | 41 | 176
TA 413 | detail | No | 2025-01-26 | 2025-02-01 | 2025-01-26 to 2025-02-01 | 225 | 47 | 178
TA 413 | detail | No | 2025-02-02 | 2025-02-08 | 2025-02-02 to 2025-02-08 | 232 | 52 | 180
TA 413 | detail | No | 2025-02-09 | 2025-02-15 | 2025-02-09 to 2025-02-15 | 239 | 56 | 183
TA 413 | detail | No | 2025-02-16 | 2025-02-22 | 2025-02-16 to 2025-02-22 | 248 | 61 | 187
TA 413 | detail | No | 2025-02-23 | 2025-03-01 | 2025-02-23 to 2025-03-01 | 256 | 68 | 188
TA 413 | detail | No | 2025-03-02 | 2025-03-08 | 2025-03-02 to 2025-03-08 | 262 | 73 | 189
TA 413 | detail | No | 2025-03-09 | 2025-03-15 | 2025-03-09 to 2025-03-15 | 264 | 78 | 186
TA 413 | detail | No | 2025-03-16 | 2025-03-22 | 2025-03-16 to 2025-03-22 | 266 | 84 | 182
TA 413 | detail | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 | 271 | 89 | 182
TA 413 | detail | No | 2025-03-30 | 2025-04-05 | 2025-03-30 to 2025-04-05 | 277 | 94 | 183
TA 413 | detail | No | 2025-04-06 | 2025-04-12 | 2025-04-06 to 2025-04-12 | 284 | 98 | 186
TA 413 | detail | No | 2025-04-13 | 2025-04-19 | 2025-04-13 to 2025-04-19 | 291 | 101 | 190
TA 413 | detail | No | 2025-04-20 | 2025-04-26 | 2025-04-20 to 2025-04-26 | 296 | 102 | 194
TA 413 | detail | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 | 299 | 104 | 195
TA 413 | detail | No | 2025-05-04 | 2025-05-10 | 2025-05-04 to 2025-05-10 | 302 | 104 | 198
TA 413 | detail | No | 2025-05-11 | 2025-05-17 | 2025-05-11 to 2025-05-17 | 304 | 104 | 200
TA 413 | detail | No | 2025-05-18 | 2025-05-24 | 2025-05-18 to 2025-05-24 | 306 | 104 | 202
TA 413 | detail | No | 2025-05-25 | 2025-05-31 | 2025-05-25 to 2025-05-31 | 307 | 104 | 203
TA 413 | detail | No | 2025-06-01 | 2025-06-07 | 2025-06-01 to 2025-06-07 | 308 | 104 | 204
TA 413 | detail | No | 2025-06-08 | 2025-06-14 | 2025-06-08 to 2025-06-14 | 310 | 104 | 206
TA 413 | detail | No | 2025-06-22 | 2025-06-28 | 2025-06-22 to 2025-06-28 | 311 | 104 | 207
TA 413 | detail | No | 2025-06-29 | 2025-07-05 | 2025-06-29 to 2025-07-05 | 312 | 104 | 208
TA 413 | detail | No | 2025-07-13 | 2025-07-19 | 2025-07-13 to 2025-07-19 | 313 | 106 | 207
TA 413 | detail | No | 2025-07-20 | 2025-07-26 | 2025-07-20 to 2025-07-26 | 313 | 110 | 203
TA 413 | detail | No | 2025-07-27 | 2025-08-02 | 2025-07-27 to 2025-08-02 | 313 | 114 | 199
TA 413 | detail | No | 2025-08-03 | 2025-08-09 | 2025-08-03 to 2025-08-09 | 313 | 123 | 190
TA 413 | detail | No | 2025-08-10 | 2025-08-16 | 2025-08-10 to 2025-08-16 | 313 | 131 | 182
TA 413 | detail | No | 2025-08-17 | 2025-08-23 | 2025-08-17 to 2025-08-23 | 313 | 144 | 169
TA 413 | detail | No | 2025-08-24 | 2025-08-30 | 2025-08-24 to 2025-08-30 | 313 | 155 | 158
TA 413 | detail | No | 2025-08-31 | 2025-09-06 | 2025-08-31 to 2025-09-06 | 313 | 169 | 144
TA 413 | detail | No | 2025-09-07 | 2025-09-13 | 2025-09-07 to 2025-09-13 | 313 | 182 | 131
TA 413 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 313 | 199 | 114
TA 413 | detail | No | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 | 313 | 212 | 101
TA 413 | detail | No | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 | 313 | 225 | 88
TA 413 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 313 | 232 | 81
TA 413 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 313 | 240 | 73
TA 413 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 313 | 247 | 66
TA 413 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 313 | 257 | 56
TA 413 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 313 | 262 | 51
TA 413 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 313 | 270 | 43
TA 413 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 313 | 273 | 40
TA 413 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 313 | 281 | 32
TA 413 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 313 | 284 | 29
TA 413 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 313 | 285 | 28
TA 413 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 313 | 288 | 25
TA 413 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 313 | 292 | 21
TA 413 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 313 | 294 | 19
TA 413 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 313 | 295 | 18
TA 413 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 313 | 296 | 17
TA 413 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 314 | 298 | 16
TA 413 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 314 | 300 | 14
TA 413 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 314 | 301 | 13
TA 413 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 315 | 302 | 13
TA 413 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 315 | 303 | 12
TA 413 | detail | No | 2026-03-01 | 2026-03-07 | 2026-03-01 to 2026-03-07 | 316 | 303 | 13
TA 414 | detail | No | 2024-05-12 | 2024-05-18 | 2024-05-12 to 2024-05-18 | 1 | 0 | 1
TA 414 | detail | No | 2024-05-19 | 2024-05-25 | 2024-05-19 to 2024-05-25 | 2 | 0 | 2
TA 414 | detail | No | 2024-05-26 | 2024-06-01 | 2024-05-26 to 2024-06-01 | 3 | 0 | 3
TA 414 | detail | No | 2024-08-25 | 2024-08-31 | 2024-08-25 to 2024-08-31 | 4 | 0 | 4
TA 414 | detail | No | 2024-09-15 | 2024-09-21 | 2024-09-15 to 2024-09-21 | 5 | 0 | 5
TA 414 | detail | No | 2024-10-27 | 2024-11-02 | 2024-10-27 to 2024-11-02 | 6 | 0 | 6
TA 414 | detail | No | 2024-11-03 | 2024-11-09 | 2024-11-03 to 2024-11-09 | 8 | 0 | 8
TA 414 | detail | No | 2024-11-17 | 2024-11-23 | 2024-11-17 to 2024-11-23 | 9 | 0 | 9
TA 414 | detail | No | 2024-11-24 | 2024-11-30 | 2024-11-24 to 2024-11-30 | 10 | 0 | 10
TA 414 | detail | No | 2024-12-01 | 2024-12-07 | 2024-12-01 to 2024-12-07 | 13 | 0 | 13
TA 414 | detail | No | 2024-12-08 | 2024-12-14 | 2024-12-08 to 2024-12-14 | 18 | 0 | 18
TA 414 | detail | No | 2024-12-15 | 2024-12-21 | 2024-12-15 to 2024-12-21 | 21 | 0 | 21
TA 414 | detail | No | 2024-12-22 | 2024-12-28 | 2024-12-22 to 2024-12-28 | 25 | 0 | 25
TA 414 | detail | No | 2024-12-29 | 2025-01-04 | 2024-12-29 to 2025-01-04 | 27 | 0 | 27
TA 414 | detail | No | 2025-01-05 | 2025-01-11 | 2025-01-05 to 2025-01-11 | 31 | 0 | 31
TA 414 | detail | No | 2025-01-12 | 2025-01-18 | 2025-01-12 to 2025-01-18 | 34 | 0 | 34
TA 414 | detail | No | 2025-01-19 | 2025-01-25 | 2025-01-19 to 2025-01-25 | 38 | 0 | 38
TA 414 | detail | No | 2025-01-26 | 2025-02-01 | 2025-01-26 to 2025-02-01 | 46 | 0 | 46
TA 414 | detail | No | 2025-02-02 | 2025-02-08 | 2025-02-02 to 2025-02-08 | 52 | 0 | 52
TA 414 | detail | No | 2025-02-09 | 2025-02-15 | 2025-02-09 to 2025-02-15 | 54 | 0 | 54
TA 414 | detail | No | 2025-02-23 | 2025-03-01 | 2025-02-23 to 2025-03-01 | 56 | 0 | 56
TA 414 | detail | No | 2025-03-02 | 2025-03-08 | 2025-03-02 to 2025-03-08 | 61 | 0 | 61
TA 414 | detail | No | 2025-03-09 | 2025-03-15 | 2025-03-09 to 2025-03-15 | 68 | 0 | 68
TA 414 | detail | No | 2025-03-16 | 2025-03-22 | 2025-03-16 to 2025-03-22 | 69 | 0 | 69
TA 414 | detail | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 | 71 | 0 | 71
TA 414 | detail | No | 2025-03-30 | 2025-04-05 | 2025-03-30 to 2025-04-05 | 75 | 1 | 74
TA 414 | detail | No | 2025-04-06 | 2025-04-12 | 2025-04-06 to 2025-04-12 | 79 | 1 | 78
TA 414 | detail | No | 2025-04-13 | 2025-04-19 | 2025-04-13 to 2025-04-19 | 80 | 1 | 79
TA 414 | detail | No | 2025-04-20 | 2025-04-26 | 2025-04-20 to 2025-04-26 | 83 | 1 | 82
TA 414 | detail | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 | 85 | 1 | 84
TA 414 | detail | No | 2025-05-04 | 2025-05-10 | 2025-05-04 to 2025-05-10 | 88 | 1 | 87
TA 414 | detail | No | 2025-05-11 | 2025-05-17 | 2025-05-11 to 2025-05-17 | 89 | 1 | 88
TA 414 | detail | No | 2025-05-18 | 2025-05-24 | 2025-05-18 to 2025-05-24 | 90 | 1 | 89
TA 414 | detail | No | 2025-06-01 | 2025-06-07 | 2025-06-01 to 2025-06-07 | 90 | 2 | 88
TA 414 | detail | No | 2025-06-08 | 2025-06-14 | 2025-06-08 to 2025-06-14 | 90 | 3 | 87
TA 414 | detail | No | 2025-06-15 | 2025-06-21 | 2025-06-15 to 2025-06-21 | 90 | 4 | 86
TA 414 | detail | No | 2025-06-29 | 2025-07-05 | 2025-06-29 to 2025-07-05 | 90 | 5 | 85
TA 414 | detail | No | 2025-08-03 | 2025-08-09 | 2025-08-03 to 2025-08-09 | 92 | 6 | 86
TA 414 | detail | No | 2025-08-10 | 2025-08-16 | 2025-08-10 to 2025-08-16 | 94 | 7 | 87
TA 414 | detail | No | 2025-08-24 | 2025-08-30 | 2025-08-24 to 2025-08-30 | 95 | 9 | 86
TA 414 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 95 | 11 | 84
TA 414 | detail | No | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 | 96 | 11 | 85
TA 414 | detail | No | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 | 96 | 12 | 84
TA 414 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 102 | 12 | 90
TA 414 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 103 | 12 | 91
TA 414 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 110 | 12 | 98
TA 414 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 117 | 12 | 105
TA 414 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 123 | 12 | 111
TA 414 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 130 | 12 | 118
TA 414 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 141 | 12 | 129
TA 414 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 159 | 12 | 147
TA 414 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 177 | 14 | 163
TA 414 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 199 | 20 | 179
TA 414 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 210 | 23 | 187
TA 414 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 217 | 30 | 187
TA 414 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 227 | 39 | 188
TA 414 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 235 | 47 | 188
TA 414 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 251 | 59 | 192
TA 414 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 255 | 73 | 182
TA 414 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 263 | 83 | 180
TA 414 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 269 | 98 | 171
TA 414 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 279 | 109 | 170
TA 414 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 281 | 123 | 158
TA 414 | detail | No | 2026-03-01 | 2026-03-07 | 2026-03-01 to 2026-03-07 | 284 | 127 | 157
TA 414 | detail | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 | 289 | 142 | 147
TA 414 | detail | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 | 296 | 154 | 142
TA 414 | detail | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 | 301 | 167 | 134
TA 414 | detail | No | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 | 302 | 182 | 120
TA 414 | detail | No | 2026-04-05 | 2026-04-11 | 2026-04-05 to 2026-04-11 | 308 | 192 | 116
TA 414 | detail | No | 2026-04-12 | 2026-04-18 | 2026-04-12 to 2026-04-18 | 312 | 200 | 112
TA 414 | detail | No | 2026-04-19 | 2026-04-25 | 2026-04-19 to 2026-04-25 | 316 | 206 | 110
TA 414 | detail | No | 2026-04-26 | 2026-05-02 | 2026-04-26 to 2026-05-02 | 320 | 208 | 112
TA 414 | detail | No | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 | 324 | 216 | 108
TA 414 | detail | No | 2026-05-10 | 2026-05-16 | 2026-05-10 to 2026-05-16 | 326 | 222 | 104
TA 414 | detail | No | 2026-05-17 | 2026-05-23 | 2026-05-17 to 2026-05-23 | 327 | 225 | 102
TA 416 | detail | No | 2024-04-21 | 2024-04-27 | 2024-04-21 to 2024-04-27 | 1 | 0 | 1
TA 416 | detail | No | 2024-04-28 | 2024-05-04 | 2024-04-28 to 2024-05-04 | 2 | 0 | 2
TA 416 | detail | No | 2024-05-05 | 2024-05-11 | 2024-05-05 to 2024-05-11 | 3 | 0 | 3
TA 416 | detail | No | 2024-05-12 | 2024-05-18 | 2024-05-12 to 2024-05-18 | 5 | 0 | 5
TA 416 | detail | No | 2024-05-19 | 2024-05-25 | 2024-05-19 to 2024-05-25 | 6 | 0 | 6
TA 416 | detail | No | 2024-05-26 | 2024-06-01 | 2024-05-26 to 2024-06-01 | 9 | 0 | 9
TA 416 | detail | No | 2024-06-02 | 2024-06-08 | 2024-06-02 to 2024-06-08 | 14 | 0 | 14
TA 416 | detail | No | 2024-06-09 | 2024-06-15 | 2024-06-09 to 2024-06-15 | 20 | 0 | 20
TA 416 | detail | No | 2024-06-16 | 2024-06-22 | 2024-06-16 to 2024-06-22 | 23 | 0 | 23
TA 416 | detail | No | 2024-06-30 | 2024-07-06 | 2024-06-30 to 2024-07-06 | 24 | 0 | 24
TA 416 | detail | No | 2024-07-07 | 2024-07-13 | 2024-07-07 to 2024-07-13 | 28 | 0 | 28
TA 416 | detail | No | 2024-07-14 | 2024-07-20 | 2024-07-14 to 2024-07-20 | 32 | 0 | 32
TA 416 | detail | No | 2024-07-21 | 2024-07-27 | 2024-07-21 to 2024-07-27 | 33 | 0 | 33
TA 416 | detail | No | 2024-07-28 | 2024-08-03 | 2024-07-28 to 2024-08-03 | 36 | 0 | 36
TA 416 | detail | No | 2024-08-04 | 2024-08-10 | 2024-08-04 to 2024-08-10 | 39 | 0 | 39
TA 416 | detail | No | 2024-08-11 | 2024-08-17 | 2024-08-11 to 2024-08-17 | 42 | 0 | 42
TA 416 | detail | No | 2024-08-18 | 2024-08-24 | 2024-08-18 to 2024-08-24 | 53 | 0 | 53
TA 416 | detail | No | 2024-08-25 | 2024-08-31 | 2024-08-25 to 2024-08-31 | 55 | 0 | 55
TA 416 | detail | No | 2024-09-01 | 2024-09-07 | 2024-09-01 to 2024-09-07 | 58 | 0 | 58
TA 416 | detail | No | 2024-09-08 | 2024-09-14 | 2024-09-08 to 2024-09-14 | 66 | 0 | 66
TA 416 | detail | No | 2024-09-15 | 2024-09-21 | 2024-09-15 to 2024-09-21 | 74 | 1 | 73
TA 416 | detail | No | 2024-09-22 | 2024-09-28 | 2024-09-22 to 2024-09-28 | 84 | 1 | 83
TA 416 | detail | No | 2024-09-29 | 2024-10-05 | 2024-09-29 to 2024-10-05 | 96 | 3 | 93
TA 416 | detail | No | 2024-10-06 | 2024-10-12 | 2024-10-06 to 2024-10-12 | 107 | 4 | 103
TA 416 | detail | No | 2024-10-13 | 2024-10-19 | 2024-10-13 to 2024-10-19 | 125 | 7 | 118
TA 416 | detail | No | 2024-10-20 | 2024-10-26 | 2024-10-20 to 2024-10-26 | 143 | 9 | 134
TA 416 | detail | No | 2024-10-27 | 2024-11-02 | 2024-10-27 to 2024-11-02 | 145 | 11 | 134
TA 416 | detail | No | 2024-11-03 | 2024-11-09 | 2024-11-03 to 2024-11-09 | 162 | 12 | 150
TA 416 | detail | No | 2024-11-10 | 2024-11-16 | 2024-11-10 to 2024-11-16 | 174 | 14 | 160
TA 416 | detail | No | 2024-11-17 | 2024-11-23 | 2024-11-17 to 2024-11-23 | 196 | 16 | 180
TA 416 | detail | No | 2024-11-24 | 2024-11-30 | 2024-11-24 to 2024-11-30 | 209 | 22 | 187
TA 416 | detail | No | 2024-12-01 | 2024-12-07 | 2024-12-01 to 2024-12-07 | 223 | 27 | 196
TA 416 | detail | No | 2024-12-08 | 2024-12-14 | 2024-12-08 to 2024-12-14 | 242 | 32 | 210
TA 416 | detail | No | 2024-12-15 | 2024-12-21 | 2024-12-15 to 2024-12-21 | 253 | 38 | 215
TA 416 | detail | No | 2024-12-22 | 2024-12-28 | 2024-12-22 to 2024-12-28 | 265 | 44 | 221
TA 416 | detail | No | 2024-12-29 | 2025-01-04 | 2024-12-29 to 2025-01-04 | 278 | 50 | 228
TA 416 | detail | No | 2025-01-05 | 2025-01-11 | 2025-01-05 to 2025-01-11 | 287 | 55 | 232
TA 416 | detail | No | 2025-01-12 | 2025-01-18 | 2025-01-12 to 2025-01-18 | 300 | 60 | 240
TA 416 | detail | No | 2025-01-19 | 2025-01-25 | 2025-01-19 to 2025-01-25 | 314 | 67 | 247
TA 416 | detail | No | 2025-01-26 | 2025-02-01 | 2025-01-26 to 2025-02-01 | 325 | 74 | 251
TA 416 | detail | No | 2025-02-02 | 2025-02-08 | 2025-02-02 to 2025-02-08 | 339 | 79 | 260
TA 416 | detail | No | 2025-02-09 | 2025-02-15 | 2025-02-09 to 2025-02-15 | 352 | 87 | 265
TA 416 | detail | No | 2025-02-16 | 2025-02-22 | 2025-02-16 to 2025-02-22 | 366 | 95 | 271
TA 416 | detail | No | 2025-02-23 | 2025-03-01 | 2025-02-23 to 2025-03-01 | 385 | 102 | 283
TA 416 | detail | No | 2025-03-02 | 2025-03-08 | 2025-03-02 to 2025-03-08 | 390 | 109 | 281
TA 416 | detail | No | 2025-03-09 | 2025-03-15 | 2025-03-09 to 2025-03-15 | 395 | 114 | 281
TA 416 | detail | No | 2025-03-16 | 2025-03-22 | 2025-03-16 to 2025-03-22 | 408 | 120 | 288
TA 416 | detail | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 | 419 | 125 | 294
TA 416 | detail | No | 2025-03-30 | 2025-04-05 | 2025-03-30 to 2025-04-05 | 433 | 133 | 300
TA 416 | detail | No | 2025-04-06 | 2025-04-12 | 2025-04-06 to 2025-04-12 | 444 | 142 | 302
TA 416 | detail | No | 2025-04-13 | 2025-04-19 | 2025-04-13 to 2025-04-19 | 451 | 149 | 302
TA 416 | detail | No | 2025-04-20 | 2025-04-26 | 2025-04-20 to 2025-04-26 | 462 | 160 | 302
TA 416 | detail | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 | 471 | 168 | 303
TA 416 | detail | No | 2025-05-04 | 2025-05-10 | 2025-05-04 to 2025-05-10 | 484 | 176 | 308
TA 416 | detail | No | 2025-05-11 | 2025-05-17 | 2025-05-11 to 2025-05-17 | 498 | 185 | 313
TA 416 | detail | No | 2025-05-18 | 2025-05-24 | 2025-05-18 to 2025-05-24 | 506 | 197 | 309
TA 416 | detail | No | 2025-05-25 | 2025-05-31 | 2025-05-25 to 2025-05-31 | 514 | 205 | 309
TA 416 | detail | No | 2025-06-01 | 2025-06-07 | 2025-06-01 to 2025-06-07 | 520 | 211 | 309
TA 416 | detail | No | 2025-06-08 | 2025-06-14 | 2025-06-08 to 2025-06-14 | 526 | 216 | 310
TA 416 | detail | No | 2025-06-15 | 2025-06-21 | 2025-06-15 to 2025-06-21 | 529 | 220 | 309
TA 416 | detail | No | 2025-06-22 | 2025-06-28 | 2025-06-22 to 2025-06-28 | 533 | 223 | 310
TA 416 | detail | No | 2025-06-29 | 2025-07-05 | 2025-06-29 to 2025-07-05 | 536 | 230 | 306
TA 416 | detail | No | 2025-07-06 | 2025-07-12 | 2025-07-06 to 2025-07-12 | 538 | 232 | 306
TA 416 | detail | No | 2025-07-13 | 2025-07-19 | 2025-07-13 to 2025-07-19 | 538 | 233 | 305
TA 416 | detail | No | 2025-07-20 | 2025-07-26 | 2025-07-20 to 2025-07-26 | 540 | 234 | 306
TA 416 | detail | No | 2025-07-27 | 2025-08-02 | 2025-07-27 to 2025-08-02 | 543 | 235 | 308
TA 416 | detail | No | 2025-08-03 | 2025-08-09 | 2025-08-03 to 2025-08-09 | 546 | 236 | 310
TA 416 | detail | No | 2025-08-10 | 2025-08-16 | 2025-08-10 to 2025-08-16 | 550 | 237 | 313
TA 416 | detail | No | 2025-08-17 | 2025-08-23 | 2025-08-17 to 2025-08-23 | 552 | 238 | 314
TA 416 | detail | No | 2025-08-24 | 2025-08-30 | 2025-08-24 to 2025-08-30 | 554 | 243 | 311
TA 416 | detail | No | 2025-08-31 | 2025-09-06 | 2025-08-31 to 2025-09-06 | 558 | 246 | 312
TA 416 | detail | No | 2025-09-07 | 2025-09-13 | 2025-09-07 to 2025-09-13 | 560 | 246 | 314
TA 416 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 564 | 248 | 316
TA 416 | detail | No | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 | 574 | 258 | 316
TA 416 | detail | No | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 | 576 | 260 | 316
TA 416 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 579 | 263 | 316
TA 416 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 579 | 269 | 310
TA 416 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 580 | 270 | 310
TA 416 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 582 | 273 | 309
TA 416 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 585 | 275 | 310
TA 416 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 589 | 279 | 310
TA 416 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 591 | 280 | 311
TA 416 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 592 | 282 | 310
TA 416 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 596 | 287 | 309
TA 416 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 598 | 288 | 310
TA 416 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 600 | 290 | 310
TA 416 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 601 | 292 | 309
TA 416 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 601 | 294 | 307
TA 416 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 601 | 297 | 304
TA 416 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 603 | 298 | 305
TA 416 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 603 | 299 | 304
TA 416 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 605 | 300 | 305
TA 416 | detail | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 | 605 | 301 | 304
TA 416 | detail | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 | 605 | 302 | 303
TA 418 | detail | No | 2024-01-07 | 2024-01-13 | 2024-01-07 to 2024-01-13 | 2 | 0 | 2
TA 418 | detail | No | 2024-06-09 | 2024-06-15 | 2024-06-09 to 2024-06-15 | 4 | 0 | 4
TA 418 | detail | No | 2024-06-23 | 2024-06-29 | 2024-06-23 to 2024-06-29 | 6 | 0 | 6
TA 418 | detail | No | 2024-06-30 | 2024-07-06 | 2024-06-30 to 2024-07-06 | 9 | 0 | 9
TA 418 | detail | No | 2024-07-07 | 2024-07-13 | 2024-07-07 to 2024-07-13 | 11 | 0 | 11
TA 418 | detail | No | 2024-07-14 | 2024-07-20 | 2024-07-14 to 2024-07-20 | 15 | 0 | 15
TA 418 | detail | No | 2024-07-21 | 2024-07-27 | 2024-07-21 to 2024-07-27 | 17 | 0 | 17
TA 418 | detail | No | 2024-07-28 | 2024-08-03 | 2024-07-28 to 2024-08-03 | 19 | 0 | 19
TA 418 | detail | No | 2024-08-04 | 2024-08-10 | 2024-08-04 to 2024-08-10 | 21 | 0 | 21
TA 418 | detail | No | 2024-08-11 | 2024-08-17 | 2024-08-11 to 2024-08-17 | 22 | 0 | 22
TA 418 | detail | No | 2024-08-25 | 2024-08-31 | 2024-08-25 to 2024-08-31 | 23 | 0 | 23
TA 418 | detail | No | 2024-09-01 | 2024-09-07 | 2024-09-01 to 2024-09-07 | 27 | 0 | 27
TA 418 | detail | No | 2024-09-08 | 2024-09-14 | 2024-09-08 to 2024-09-14 | 28 | 0 | 28
TA 418 | detail | No | 2024-09-15 | 2024-09-21 | 2024-09-15 to 2024-09-21 | 29 | 0 | 29
TA 418 | detail | No | 2024-09-22 | 2024-09-28 | 2024-09-22 to 2024-09-28 | 33 | 0 | 33
TA 418 | detail | No | 2024-09-29 | 2024-10-05 | 2024-09-29 to 2024-10-05 | 34 | 0 | 34
TA 418 | detail | No | 2024-10-06 | 2024-10-12 | 2024-10-06 to 2024-10-12 | 36 | 0 | 36
TA 418 | detail | No | 2024-10-13 | 2024-10-19 | 2024-10-13 to 2024-10-19 | 37 | 0 | 37
TA 418 | detail | No | 2024-10-27 | 2024-11-02 | 2024-10-27 to 2024-11-02 | 40 | 1 | 39
TA 418 | detail | No | 2024-11-03 | 2024-11-09 | 2024-11-03 to 2024-11-09 | 42 | 2 | 40
TA 418 | detail | No | 2024-11-10 | 2024-11-16 | 2024-11-10 to 2024-11-16 | 46 | 3 | 43
TA 418 | detail | No | 2024-11-17 | 2024-11-23 | 2024-11-17 to 2024-11-23 | 48 | 4 | 44
TA 418 | detail | No | 2024-11-24 | 2024-11-30 | 2024-11-24 to 2024-11-30 | 50 | 5 | 45
TA 418 | detail | No | 2024-12-01 | 2024-12-07 | 2024-12-01 to 2024-12-07 | 54 | 7 | 47
TA 418 | detail | No | 2024-12-08 | 2024-12-14 | 2024-12-08 to 2024-12-14 | 59 | 9 | 50
TA 418 | detail | No | 2024-12-15 | 2024-12-21 | 2024-12-15 to 2024-12-21 | 61 | 11 | 50
TA 418 | detail | No | 2024-12-22 | 2024-12-28 | 2024-12-22 to 2024-12-28 | 62 | 12 | 50
TA 418 | detail | No | 2024-12-29 | 2025-01-04 | 2024-12-29 to 2025-01-04 | 66 | 13 | 53
TA 418 | detail | No | 2025-01-05 | 2025-01-11 | 2025-01-05 to 2025-01-11 | 67 | 16 | 51
TA 418 | detail | No | 2025-01-12 | 2025-01-18 | 2025-01-12 to 2025-01-18 | 72 | 18 | 54
TA 418 | detail | No | 2025-01-19 | 2025-01-25 | 2025-01-19 to 2025-01-25 | 76 | 20 | 56
TA 418 | detail | No | 2025-01-26 | 2025-02-01 | 2025-01-26 to 2025-02-01 | 80 | 21 | 59
TA 418 | detail | No | 2025-02-02 | 2025-02-08 | 2025-02-02 to 2025-02-08 | 81 | 23 | 58
TA 418 | detail | No | 2025-02-09 | 2025-02-15 | 2025-02-09 to 2025-02-15 | 86 | 25 | 61
TA 418 | detail | No | 2025-02-16 | 2025-02-22 | 2025-02-16 to 2025-02-22 | 87 | 27 | 60
TA 418 | detail | No | 2025-02-23 | 2025-03-01 | 2025-02-23 to 2025-03-01 | 93 | 28 | 65
TA 418 | detail | No | 2025-03-02 | 2025-03-08 | 2025-03-02 to 2025-03-08 | 95 | 30 | 65
TA 418 | detail | No | 2025-03-09 | 2025-03-15 | 2025-03-09 to 2025-03-15 | 99 | 31 | 68
TA 418 | detail | No | 2025-03-16 | 2025-03-22 | 2025-03-16 to 2025-03-22 | 102 | 32 | 70
TA 418 | detail | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 | 104 | 34 | 70
TA 418 | detail | No | 2025-03-30 | 2025-04-05 | 2025-03-30 to 2025-04-05 | 107 | 36 | 71
TA 418 | detail | No | 2025-04-06 | 2025-04-12 | 2025-04-06 to 2025-04-12 | 111 | 37 | 74
TA 418 | detail | No | 2025-04-13 | 2025-04-19 | 2025-04-13 to 2025-04-19 | 116 | 38 | 78
TA 418 | detail | No | 2025-04-20 | 2025-04-26 | 2025-04-20 to 2025-04-26 | 117 | 40 | 77
TA 418 | detail | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 | 120 | 42 | 78
TA 418 | detail | No | 2025-05-04 | 2025-05-10 | 2025-05-04 to 2025-05-10 | 123 | 44 | 79
TA 418 | detail | No | 2025-05-11 | 2025-05-17 | 2025-05-11 to 2025-05-17 | 128 | 45 | 83
TA 418 | detail | No | 2025-05-18 | 2025-05-24 | 2025-05-18 to 2025-05-24 | 129 | 46 | 83
TA 418 | detail | No | 2025-05-25 | 2025-05-31 | 2025-05-25 to 2025-05-31 | 133 | 48 | 85
TA 418 | detail | No | 2025-06-01 | 2025-06-07 | 2025-06-01 to 2025-06-07 | 139 | 50 | 89
TA 418 | detail | No | 2025-06-08 | 2025-06-14 | 2025-06-08 to 2025-06-14 | 146 | 52 | 94
TA 418 | detail | No | 2025-06-15 | 2025-06-21 | 2025-06-15 to 2025-06-21 | 150 | 53 | 97
TA 418 | detail | No | 2025-06-22 | 2025-06-28 | 2025-06-22 to 2025-06-28 | 157 | 54 | 103
TA 418 | detail | No | 2025-06-29 | 2025-07-05 | 2025-06-29 to 2025-07-05 | 167 | 55 | 112
TA 418 | detail | No | 2025-07-06 | 2025-07-12 | 2025-07-06 to 2025-07-12 | 168 | 56 | 112
TA 418 | detail | No | 2025-07-13 | 2025-07-19 | 2025-07-13 to 2025-07-19 | 171 | 57 | 114
TA 418 | detail | No | 2025-07-20 | 2025-07-26 | 2025-07-20 to 2025-07-26 | 175 | 60 | 115
TA 418 | detail | No | 2025-07-27 | 2025-08-02 | 2025-07-27 to 2025-08-02 | 177 | 62 | 115
TA 418 | detail | No | 2025-08-03 | 2025-08-09 | 2025-08-03 to 2025-08-09 | 181 | 65 | 116
TA 418 | detail | No | 2025-08-10 | 2025-08-16 | 2025-08-10 to 2025-08-16 | 182 | 66 | 116
TA 418 | detail | No | 2025-08-17 | 2025-08-23 | 2025-08-17 to 2025-08-23 | 186 | 69 | 117
TA 418 | detail | No | 2025-08-24 | 2025-08-30 | 2025-08-24 to 2025-08-30 | 187 | 72 | 115
TA 418 | detail | No | 2025-08-31 | 2025-09-06 | 2025-08-31 to 2025-09-06 | 191 | 73 | 118
TA 418 | detail | No | 2025-09-07 | 2025-09-13 | 2025-09-07 to 2025-09-13 | 194 | 77 | 117
TA 418 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 196 | 77 | 119
TA 418 | detail | No | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 | 198 | 80 | 118
TA 418 | detail | No | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 | 201 | 84 | 117
TA 418 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 201 | 85 | 116
TA 418 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 204 | 88 | 116
TA 418 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 205 | 89 | 116
TA 418 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 209 | 91 | 118
TA 418 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 213 | 93 | 120
TA 418 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 214 | 95 | 119
TA 418 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 216 | 97 | 119
TA 418 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 220 | 98 | 122
TA 418 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 225 | 100 | 125
TA 418 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 230 | 104 | 126
TA 418 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 233 | 107 | 126
TA 418 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 235 | 108 | 127
TA 418 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 238 | 111 | 127
TA 418 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 239 | 113 | 126
TA 418 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 241 | 115 | 126
TA 418 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 243 | 118 | 125
TA 418 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 246 | 120 | 126
TA 418 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 247 | 120 | 127
TA 418 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 248 | 122 | 126
TA 418 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 249 | 124 | 125
TA 418 | detail | No | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 | 249 | 125 | 124
TA 419 | detail | No | 2024-05-19 | 2024-05-25 | 2024-05-19 to 2024-05-25 | 2 | 0 | 2
TA 419 | detail | No | 2024-05-26 | 2024-06-01 | 2024-05-26 to 2024-06-01 | 5 | 0 | 5
TA 419 | detail | No | 2024-06-02 | 2024-06-08 | 2024-06-02 to 2024-06-08 | 6 | 0 | 6
TA 419 | detail | No | 2024-06-09 | 2024-06-15 | 2024-06-09 to 2024-06-15 | 7 | 0 | 7
TA 419 | detail | No | 2024-06-16 | 2024-06-22 | 2024-06-16 to 2024-06-22 | 9 | 0 | 9
TA 419 | detail | No | 2024-06-23 | 2024-06-29 | 2024-06-23 to 2024-06-29 | 13 | 0 | 13
TA 419 | detail | No | 2024-06-30 | 2024-07-06 | 2024-06-30 to 2024-07-06 | 16 | 0 | 16
TA 419 | detail | No | 2024-07-07 | 2024-07-13 | 2024-07-07 to 2024-07-13 | 21 | 0 | 21
TA 419 | detail | No | 2024-07-14 | 2024-07-20 | 2024-07-14 to 2024-07-20 | 24 | 0 | 24
TA 419 | detail | No | 2024-07-21 | 2024-07-27 | 2024-07-21 to 2024-07-27 | 29 | 0 | 29
TA 419 | detail | No | 2024-07-28 | 2024-08-03 | 2024-07-28 to 2024-08-03 | 33 | 0 | 33
TA 419 | detail | No | 2024-08-04 | 2024-08-10 | 2024-08-04 to 2024-08-10 | 35 | 0 | 35
TA 419 | detail | No | 2024-08-11 | 2024-08-17 | 2024-08-11 to 2024-08-17 | 37 | 0 | 37
TA 419 | detail | No | 2024-08-25 | 2024-08-31 | 2024-08-25 to 2024-08-31 | 40 | 0 | 40
TA 419 | detail | No | 2024-09-01 | 2024-09-07 | 2024-09-01 to 2024-09-07 | 43 | 0 | 43
TA 419 | detail | No | 2024-09-08 | 2024-09-14 | 2024-09-08 to 2024-09-14 | 46 | 0 | 46
TA 419 | detail | No | 2024-09-15 | 2024-09-21 | 2024-09-15 to 2024-09-21 | 51 | 0 | 51
TA 419 | detail | No | 2024-09-22 | 2024-09-28 | 2024-09-22 to 2024-09-28 | 55 | 0 | 55
TA 419 | detail | No | 2024-09-29 | 2024-10-05 | 2024-09-29 to 2024-10-05 | 58 | 0 | 58
TA 419 | detail | No | 2024-10-06 | 2024-10-12 | 2024-10-06 to 2024-10-12 | 66 | 0 | 66
TA 419 | detail | No | 2024-10-13 | 2024-10-19 | 2024-10-13 to 2024-10-19 | 73 | 0 | 73
TA 419 | detail | No | 2024-10-20 | 2024-10-26 | 2024-10-20 to 2024-10-26 | 75 | 0 | 75
TA 419 | detail | No | 2024-10-27 | 2024-11-02 | 2024-10-27 to 2024-11-02 | 76 | 0 | 76
TA 419 | detail | No | 2024-11-03 | 2024-11-09 | 2024-11-03 to 2024-11-09 | 77 | 0 | 77
TA 419 | detail | No | 2024-11-10 | 2024-11-16 | 2024-11-10 to 2024-11-16 | 81 | 0 | 81
TA 419 | detail | No | 2024-11-17 | 2024-11-23 | 2024-11-17 to 2024-11-23 | 83 | 0 | 83
TA 419 | detail | No | 2024-11-24 | 2024-11-30 | 2024-11-24 to 2024-11-30 | 85 | 2 | 83
TA 419 | detail | No | 2024-12-01 | 2024-12-07 | 2024-12-01 to 2024-12-07 | 90 | 4 | 86
TA 419 | detail | No | 2024-12-08 | 2024-12-14 | 2024-12-08 to 2024-12-14 | 95 | 8 | 87
TA 419 | detail | No | 2024-12-15 | 2024-12-21 | 2024-12-15 to 2024-12-21 | 97 | 10 | 87
TA 419 | detail | No | 2024-12-22 | 2024-12-28 | 2024-12-22 to 2024-12-28 | 98 | 13 | 85
TA 419 | detail | No | 2024-12-29 | 2025-01-04 | 2024-12-29 to 2025-01-04 | 99 | 16 | 83
TA 419 | detail | No | 2025-01-05 | 2025-01-11 | 2025-01-05 to 2025-01-11 | 100 | 18 | 82
TA 419 | detail | No | 2025-01-12 | 2025-01-18 | 2025-01-12 to 2025-01-18 | 103 | 22 | 81
TA 419 | detail | No | 2025-01-19 | 2025-01-25 | 2025-01-19 to 2025-01-25 | 104 | 25 | 79
TA 419 | detail | No | 2025-01-26 | 2025-02-01 | 2025-01-26 to 2025-02-01 | 107 | 30 | 77
TA 419 | detail | No | 2025-02-02 | 2025-02-08 | 2025-02-02 to 2025-02-08 | 109 | 32 | 77
TA 419 | detail | No | 2025-02-09 | 2025-02-15 | 2025-02-09 to 2025-02-15 | 111 | 38 | 73
TA 419 | detail | No | 2025-02-16 | 2025-02-22 | 2025-02-16 to 2025-02-22 | 113 | 40 | 73
TA 419 | detail | No | 2025-02-23 | 2025-03-01 | 2025-02-23 to 2025-03-01 | 114 | 46 | 68
TA 419 | detail | No | 2025-03-02 | 2025-03-08 | 2025-03-02 to 2025-03-08 | 114 | 49 | 65
TA 419 | detail | No | 2025-03-09 | 2025-03-15 | 2025-03-09 to 2025-03-15 | 114 | 50 | 64
TA 419 | detail | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 | 121 | 53 | 68
TA 419 | detail | No | 2025-03-30 | 2025-04-05 | 2025-03-30 to 2025-04-05 | 123 | 56 | 67
TA 419 | detail | No | 2025-04-06 | 2025-04-12 | 2025-04-06 to 2025-04-12 | 128 | 58 | 70
TA 419 | detail | No | 2025-04-13 | 2025-04-19 | 2025-04-13 to 2025-04-19 | 130 | 64 | 66
TA 419 | detail | No | 2025-04-20 | 2025-04-26 | 2025-04-20 to 2025-04-26 | 133 | 66 | 67
TA 419 | detail | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 | 137 | 70 | 67
TA 419 | detail | No | 2025-05-04 | 2025-05-10 | 2025-05-04 to 2025-05-10 | 139 | 73 | 66
TA 419 | detail | No | 2025-05-11 | 2025-05-17 | 2025-05-11 to 2025-05-17 | 142 | 74 | 68
TA 419 | detail | No | 2025-05-18 | 2025-05-24 | 2025-05-18 to 2025-05-24 | 144 | 75 | 69
TA 419 | detail | No | 2025-05-25 | 2025-05-31 | 2025-05-25 to 2025-05-31 | 145 | 75 | 70
TA 419 | detail | No | 2025-06-01 | 2025-06-07 | 2025-06-01 to 2025-06-07 | 148 | 76 | 72
TA 419 | detail | No | 2025-06-08 | 2025-06-14 | 2025-06-08 to 2025-06-14 | 151 | 77 | 74
TA 419 | detail | No | 2025-06-15 | 2025-06-21 | 2025-06-15 to 2025-06-21 | 152 | 78 | 74
TA 419 | detail | No | 2025-06-22 | 2025-06-28 | 2025-06-22 to 2025-06-28 | 153 | 79 | 74
TA 419 | detail | No | 2025-07-06 | 2025-07-12 | 2025-07-06 to 2025-07-12 | 154 | 80 | 74
TA 419 | detail | No | 2025-07-13 | 2025-07-19 | 2025-07-13 to 2025-07-19 | 155 | 82 | 73
TA 419 | detail | No | 2025-07-20 | 2025-07-26 | 2025-07-20 to 2025-07-26 | 156 | 84 | 72
TA 419 | detail | No | 2025-07-27 | 2025-08-02 | 2025-07-27 to 2025-08-02 | 157 | 85 | 72
TA 419 | detail | No | 2025-08-03 | 2025-08-09 | 2025-08-03 to 2025-08-09 | 157 | 87 | 70
TA 419 | detail | No | 2025-08-10 | 2025-08-16 | 2025-08-10 to 2025-08-16 | 157 | 88 | 69
TA 419 | detail | No | 2025-08-17 | 2025-08-23 | 2025-08-17 to 2025-08-23 | 157 | 89 | 68
TA 419 | detail | No | 2025-08-24 | 2025-08-30 | 2025-08-24 to 2025-08-30 | 158 | 91 | 67
TA 419 | detail | No | 2025-08-31 | 2025-09-06 | 2025-08-31 to 2025-09-06 | 159 | 92 | 67
TA 419 | detail | No | 2025-09-07 | 2025-09-13 | 2025-09-07 to 2025-09-13 | 160 | 95 | 65
TA 419 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 162 | 96 | 66
TA 419 | detail | No | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 | 165 | 98 | 67
TA 419 | detail | No | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 | 166 | 98 | 68
TA 419 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 167 | 100 | 67
TA 419 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 167 | 102 | 65
TA 419 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 168 | 103 | 65
TA 419 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 171 | 106 | 65
TA 419 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 179 | 108 | 71
TA 419 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 183 | 111 | 72
TA 419 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 186 | 112 | 74
TA 419 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 189 | 118 | 71
TA 419 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 195 | 124 | 71
TA 419 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 200 | 134 | 66
TA 419 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 210 | 144 | 66
TA 419 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 215 | 150 | 65
TA 419 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 218 | 158 | 60
TA 419 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 219 | 165 | 54
TA 419 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 225 | 170 | 55
TA 419 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 227 | 175 | 52
TA 419 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 228 | 181 | 47
TA 419 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 230 | 182 | 48
TA 419 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 231 | 183 | 48
TA 419 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 232 | 183 | 49
TA 419 | detail | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 | 234 | 184 | 50
TA 419 | detail | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 | 238 | 184 | 54
TA 419 | detail | No | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 | 241 | 185 | 56
TA 419 | detail | No | 2026-04-05 | 2026-04-11 | 2026-04-05 to 2026-04-11 | 245 | 185 | 60
TA 419 | detail | No | 2026-04-12 | 2026-04-18 | 2026-04-12 to 2026-04-18 | 248 | 188 | 60
TA 419 | detail | No | 2026-04-19 | 2026-04-25 | 2026-04-19 to 2026-04-25 | 251 | 192 | 59
TA 419 | detail | No | 2026-04-26 | 2026-05-02 | 2026-04-26 to 2026-05-02 | 256 | 195 | 61
TA 419 | detail | No | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 | 262 | 197 | 65
TA 419 | detail | No | 2026-05-10 | 2026-05-16 | 2026-05-10 to 2026-05-16 | 267 | 202 | 65
TA 419 | detail | No | 2026-05-17 | 2026-05-23 | 2026-05-17 to 2026-05-23 | 269 | 202 | 67
TA 421 | detail | No | 2023-12-31 | 2024-01-06 | 2023-12-31 to 2024-01-06 | 1 | 0 | 1
TA 421 | detail | No | 2024-02-04 | 2024-02-10 | 2024-02-04 to 2024-02-10 | 2 | 0 | 2
TA 421 | detail | No | 2024-03-03 | 2024-03-09 | 2024-03-03 to 2024-03-09 | 4 | 0 | 4
TA 421 | detail | No | 2024-04-28 | 2024-05-04 | 2024-04-28 to 2024-05-04 | 5 | 0 | 5
TA 421 | detail | No | 2024-05-05 | 2024-05-11 | 2024-05-05 to 2024-05-11 | 7 | 0 | 7
TA 421 | detail | No | 2024-05-19 | 2024-05-25 | 2024-05-19 to 2024-05-25 | 11 | 0 | 11
TA 421 | detail | No | 2024-05-26 | 2024-06-01 | 2024-05-26 to 2024-06-01 | 12 | 0 | 12
TA 421 | detail | No | 2024-06-02 | 2024-06-08 | 2024-06-02 to 2024-06-08 | 14 | 0 | 14
TA 421 | detail | No | 2024-06-09 | 2024-06-15 | 2024-06-09 to 2024-06-15 | 17 | 0 | 17
TA 421 | detail | No | 2024-06-16 | 2024-06-22 | 2024-06-16 to 2024-06-22 | 22 | 0 | 22
TA 421 | detail | No | 2024-06-23 | 2024-06-29 | 2024-06-23 to 2024-06-29 | 34 | 0 | 34
TA 421 | detail | No | 2024-06-30 | 2024-07-06 | 2024-06-30 to 2024-07-06 | 42 | 0 | 42
TA 421 | detail | No | 2024-07-07 | 2024-07-13 | 2024-07-07 to 2024-07-13 | 61 | 0 | 61
TA 421 | detail | No | 2024-07-14 | 2024-07-20 | 2024-07-14 to 2024-07-20 | 67 | 1 | 66
TA 421 | detail | No | 2024-07-21 | 2024-07-27 | 2024-07-21 to 2024-07-27 | 70 | 1 | 69
TA 421 | detail | No | 2024-07-28 | 2024-08-03 | 2024-07-28 to 2024-08-03 | 85 | 3 | 82
TA 421 | detail | No | 2024-08-04 | 2024-08-10 | 2024-08-04 to 2024-08-10 | 91 | 4 | 87
TA 421 | detail | No | 2024-08-11 | 2024-08-17 | 2024-08-11 to 2024-08-17 | 97 | 5 | 92
TA 421 | detail | No | 2024-08-18 | 2024-08-24 | 2024-08-18 to 2024-08-24 | 106 | 7 | 99
TA 421 | detail | No | 2024-08-25 | 2024-08-31 | 2024-08-25 to 2024-08-31 | 115 | 8 | 107
TA 421 | detail | No | 2024-09-01 | 2024-09-07 | 2024-09-01 to 2024-09-07 | 116 | 9 | 107
TA 421 | detail | No | 2024-09-08 | 2024-09-14 | 2024-09-08 to 2024-09-14 | 125 | 11 | 114
TA 421 | detail | No | 2024-09-15 | 2024-09-21 | 2024-09-15 to 2024-09-21 | 131 | 13 | 118
TA 421 | detail | No | 2024-09-22 | 2024-09-28 | 2024-09-22 to 2024-09-28 | 141 | 15 | 126
TA 421 | detail | No | 2024-09-29 | 2024-10-05 | 2024-09-29 to 2024-10-05 | 155 | 20 | 135
TA 421 | detail | No | 2024-10-06 | 2024-10-12 | 2024-10-06 to 2024-10-12 | 161 | 21 | 140
TA 421 | detail | No | 2024-10-13 | 2024-10-19 | 2024-10-13 to 2024-10-19 | 172 | 25 | 147
TA 421 | detail | No | 2024-10-20 | 2024-10-26 | 2024-10-20 to 2024-10-26 | 181 | 28 | 153
TA 421 | detail | No | 2024-10-27 | 2024-11-02 | 2024-10-27 to 2024-11-02 | 188 | 33 | 155
TA 421 | detail | No | 2024-11-03 | 2024-11-09 | 2024-11-03 to 2024-11-09 | 199 | 37 | 162
TA 421 | detail | No | 2024-11-10 | 2024-11-16 | 2024-11-10 to 2024-11-16 | 210 | 42 | 168
TA 421 | detail | No | 2024-11-17 | 2024-11-23 | 2024-11-17 to 2024-11-23 | 221 | 45 | 176
TA 421 | detail | No | 2024-11-24 | 2024-11-30 | 2024-11-24 to 2024-11-30 | 228 | 50 | 178
TA 421 | detail | No | 2024-12-01 | 2024-12-07 | 2024-12-01 to 2024-12-07 | 243 | 53 | 190
TA 421 | detail | No | 2024-12-08 | 2024-12-14 | 2024-12-08 to 2024-12-14 | 271 | 56 | 215
TA 421 | detail | No | 2024-12-15 | 2024-12-21 | 2024-12-15 to 2024-12-21 | 286 | 59 | 227
TA 421 | detail | No | 2024-12-22 | 2024-12-28 | 2024-12-22 to 2024-12-28 | 305 | 64 | 241
TA 421 | detail | No | 2024-12-29 | 2025-01-04 | 2024-12-29 to 2025-01-04 | 318 | 66 | 252
TA 421 | detail | No | 2025-01-05 | 2025-01-11 | 2025-01-05 to 2025-01-11 | 334 | 68 | 266
TA 421 | detail | No | 2025-01-12 | 2025-01-18 | 2025-01-12 to 2025-01-18 | 349 | 72 | 277
TA 421 | detail | No | 2025-01-19 | 2025-01-25 | 2025-01-19 to 2025-01-25 | 378 | 75 | 303
TA 421 | detail | No | 2025-01-26 | 2025-02-01 | 2025-01-26 to 2025-02-01 | 401 | 79 | 322
TA 421 | detail | No | 2025-02-02 | 2025-02-08 | 2025-02-02 to 2025-02-08 | 426 | 82 | 344
TA 421 | detail | No | 2025-02-09 | 2025-02-15 | 2025-02-09 to 2025-02-15 | 448 | 86 | 362
TA 421 | detail | No | 2025-02-16 | 2025-02-22 | 2025-02-16 to 2025-02-22 | 463 | 90 | 373
TA 421 | detail | No | 2025-02-23 | 2025-03-01 | 2025-02-23 to 2025-03-01 | 474 | 96 | 378
TA 421 | detail | No | 2025-03-02 | 2025-03-08 | 2025-03-02 to 2025-03-08 | 493 | 100 | 393
TA 421 | detail | No | 2025-03-09 | 2025-03-15 | 2025-03-09 to 2025-03-15 | 512 | 105 | 407
TA 421 | detail | No | 2025-03-16 | 2025-03-22 | 2025-03-16 to 2025-03-22 | 526 | 110 | 416
TA 421 | detail | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 | 541 | 117 | 424
TA 421 | detail | No | 2025-03-30 | 2025-04-05 | 2025-03-30 to 2025-04-05 | 552 | 122 | 430
TA 421 | detail | No | 2025-04-06 | 2025-04-12 | 2025-04-06 to 2025-04-12 | 569 | 125 | 444
TA 421 | detail | No | 2025-04-13 | 2025-04-19 | 2025-04-13 to 2025-04-19 | 591 | 131 | 460
TA 421 | detail | No | 2025-04-20 | 2025-04-26 | 2025-04-20 to 2025-04-26 | 603 | 137 | 466
TA 421 | detail | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 | 618 | 143 | 475
TA 421 | detail | No | 2025-05-04 | 2025-05-10 | 2025-05-04 to 2025-05-10 | 632 | 150 | 482
TA 421 | detail | No | 2025-05-11 | 2025-05-17 | 2025-05-11 to 2025-05-17 | 644 | 154 | 490
TA 421 | detail | No | 2025-05-18 | 2025-05-24 | 2025-05-18 to 2025-05-24 | 657 | 157 | 500
TA 421 | detail | No | 2025-05-25 | 2025-05-31 | 2025-05-25 to 2025-05-31 | 678 | 159 | 519
TA 421 | detail | No | 2025-06-01 | 2025-06-07 | 2025-06-01 to 2025-06-07 | 696 | 162 | 534
TA 421 | detail | No | 2025-06-08 | 2025-06-14 | 2025-06-08 to 2025-06-14 | 701 | 163 | 538
TA 421 | detail | No | 2025-06-15 | 2025-06-21 | 2025-06-15 to 2025-06-21 | 715 | 166 | 549
TA 421 | detail | No | 2025-06-22 | 2025-06-28 | 2025-06-22 to 2025-06-28 | 731 | 169 | 562
TA 421 | detail | No | 2025-06-29 | 2025-07-05 | 2025-06-29 to 2025-07-05 | 742 | 173 | 569
TA 421 | detail | No | 2025-07-06 | 2025-07-12 | 2025-07-06 to 2025-07-12 | 756 | 178 | 578
TA 421 | detail | No | 2025-07-13 | 2025-07-19 | 2025-07-13 to 2025-07-19 | 773 | 183 | 590
TA 421 | detail | No | 2025-07-20 | 2025-07-26 | 2025-07-20 to 2025-07-26 | 781 | 188 | 593
TA 421 | detail | No | 2025-07-27 | 2025-08-02 | 2025-07-27 to 2025-08-02 | 787 | 196 | 591
TA 421 | detail | No | 2025-08-03 | 2025-08-09 | 2025-08-03 to 2025-08-09 | 795 | 202 | 593
TA 421 | detail | No | 2025-08-10 | 2025-08-16 | 2025-08-10 to 2025-08-16 | 801 | 207 | 594
TA 421 | detail | No | 2025-08-17 | 2025-08-23 | 2025-08-17 to 2025-08-23 | 804 | 209 | 595
TA 421 | detail | No | 2025-08-24 | 2025-08-30 | 2025-08-24 to 2025-08-30 | 807 | 214 | 593
TA 421 | detail | No | 2025-08-31 | 2025-09-06 | 2025-08-31 to 2025-09-06 | 814 | 220 | 594
TA 421 | detail | No | 2025-09-07 | 2025-09-13 | 2025-09-07 to 2025-09-13 | 821 | 227 | 594
TA 421 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 824 | 231 | 593
TA 421 | detail | No | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 | 830 | 235 | 595
TA 421 | detail | No | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 | 832 | 239 | 593
TA 421 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 836 | 244 | 592
TA 421 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 844 | 248 | 596
TA 421 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 848 | 253 | 595
TA 421 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 852 | 256 | 596
TA 421 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 858 | 260 | 598
TA 421 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 865 | 264 | 601
TA 421 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 871 | 269 | 602
TA 421 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 881 | 277 | 604
TA 421 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 887 | 281 | 606
TA 421 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 893 | 287 | 606
TA 421 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 899 | 292 | 607
TA 421 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 909 | 297 | 612
TA 421 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 912 | 300 | 612
TA 421 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 914 | 303 | 611
TA 421 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 914 | 305 | 609
TA 505 | detail | No | 2015-11-22 | 2015-11-28 | 2015-11-22 to 2015-11-28 | 1 | 0 | 1
TA 505 | detail | No | 2024-03-24 | 2024-03-30 | 2024-03-24 to 2024-03-30 | 2 | 0 | 2
TA 505 | detail | No | 2024-03-31 | 2024-04-06 | 2024-03-31 to 2024-04-06 | 3 | 0 | 3
TA 505 | detail | No | 2024-04-28 | 2024-05-04 | 2024-04-28 to 2024-05-04 | 4 | 0 | 4
TA 505 | detail | No | 2024-10-06 | 2024-10-12 | 2024-10-06 to 2024-10-12 | 8 | 0 | 8
TA 505 | detail | No | 2024-10-20 | 2024-10-26 | 2024-10-20 to 2024-10-26 | 11 | 0 | 11
TA 505 | detail | No | 2024-10-27 | 2024-11-02 | 2024-10-27 to 2024-11-02 | 14 | 0 | 14
TA 505 | detail | No | 2024-11-03 | 2024-11-09 | 2024-11-03 to 2024-11-09 | 16 | 0 | 16
TA 505 | detail | No | 2024-11-10 | 2024-11-16 | 2024-11-10 to 2024-11-16 | 20 | 0 | 20
TA 505 | detail | No | 2024-11-17 | 2024-11-23 | 2024-11-17 to 2024-11-23 | 29 | 0 | 29
TA 505 | detail | No | 2024-11-24 | 2024-11-30 | 2024-11-24 to 2024-11-30 | 39 | 0 | 39
TA 505 | detail | No | 2024-12-01 | 2024-12-07 | 2024-12-01 to 2024-12-07 | 44 | 0 | 44
TA 505 | detail | No | 2024-12-08 | 2024-12-14 | 2024-12-08 to 2024-12-14 | 51 | 0 | 51
TA 505 | detail | No | 2024-12-15 | 2024-12-21 | 2024-12-15 to 2024-12-21 | 61 | 0 | 61
TA 505 | detail | No | 2024-12-22 | 2024-12-28 | 2024-12-22 to 2024-12-28 | 69 | 0 | 69
TA 505 | detail | No | 2024-12-29 | 2025-01-04 | 2024-12-29 to 2025-01-04 | 77 | 0 | 77
TA 505 | detail | No | 2025-01-05 | 2025-01-11 | 2025-01-05 to 2025-01-11 | 80 | 0 | 80
TA 505 | detail | No | 2025-01-12 | 2025-01-18 | 2025-01-12 to 2025-01-18 | 89 | 0 | 89
TA 505 | detail | No | 2025-01-19 | 2025-01-25 | 2025-01-19 to 2025-01-25 | 98 | 2 | 96
TA 505 | detail | No | 2025-01-26 | 2025-02-01 | 2025-01-26 to 2025-02-01 | 105 | 4 | 101
TA 505 | detail | No | 2025-02-02 | 2025-02-08 | 2025-02-02 to 2025-02-08 | 111 | 6 | 105
TA 505 | detail | No | 2025-02-09 | 2025-02-15 | 2025-02-09 to 2025-02-15 | 119 | 8 | 111
TA 505 | detail | No | 2025-02-16 | 2025-02-22 | 2025-02-16 to 2025-02-22 | 126 | 9 | 117
TA 505 | detail | No | 2025-02-23 | 2025-03-01 | 2025-02-23 to 2025-03-01 | 137 | 11 | 126
TA 505 | detail | No | 2025-03-02 | 2025-03-08 | 2025-03-02 to 2025-03-08 | 142 | 13 | 129
TA 505 | detail | No | 2025-03-09 | 2025-03-15 | 2025-03-09 to 2025-03-15 | 144 | 15 | 129
TA 505 | detail | No | 2025-03-16 | 2025-03-22 | 2025-03-16 to 2025-03-22 | 147 | 17 | 130
TA 505 | detail | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 | 151 | 20 | 131
TA 505 | detail | No | 2025-03-30 | 2025-04-05 | 2025-03-30 to 2025-04-05 | 159 | 23 | 136
TA 505 | detail | No | 2025-04-06 | 2025-04-12 | 2025-04-06 to 2025-04-12 | 173 | 28 | 145
TA 505 | detail | No | 2025-04-13 | 2025-04-19 | 2025-04-13 to 2025-04-19 | 182 | 33 | 149
TA 505 | detail | No | 2025-04-20 | 2025-04-26 | 2025-04-20 to 2025-04-26 | 198 | 38 | 160
TA 505 | detail | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 | 209 | 43 | 166
TA 505 | detail | No | 2025-05-04 | 2025-05-10 | 2025-05-04 to 2025-05-10 | 221 | 48 | 173
TA 505 | detail | No | 2025-05-11 | 2025-05-17 | 2025-05-11 to 2025-05-17 | 230 | 53 | 177
TA 505 | detail | No | 2025-05-18 | 2025-05-24 | 2025-05-18 to 2025-05-24 | 241 | 58 | 183
TA 505 | detail | No | 2025-05-25 | 2025-05-31 | 2025-05-25 to 2025-05-31 | 253 | 65 | 188
TA 505 | detail | No | 2025-06-01 | 2025-06-07 | 2025-06-01 to 2025-06-07 | 259 | 70 | 189
TA 505 | detail | No | 2025-06-08 | 2025-06-14 | 2025-06-08 to 2025-06-14 | 265 | 72 | 193
TA 505 | detail | No | 2025-06-15 | 2025-06-21 | 2025-06-15 to 2025-06-21 | 265 | 75 | 190
TA 505 | detail | No | 2025-06-22 | 2025-06-28 | 2025-06-22 to 2025-06-28 | 266 | 79 | 187
TA 505 | detail | No | 2025-06-29 | 2025-07-05 | 2025-06-29 to 2025-07-05 | 268 | 81 | 187
TA 505 | detail | No | 2025-07-06 | 2025-07-12 | 2025-07-06 to 2025-07-12 | 268 | 84 | 184
TA 505 | detail | No | 2025-07-13 | 2025-07-19 | 2025-07-13 to 2025-07-19 | 270 | 86 | 184
TA 505 | detail | No | 2025-07-20 | 2025-07-26 | 2025-07-20 to 2025-07-26 | 270 | 87 | 183
TA 505 | detail | No | 2025-07-27 | 2025-08-02 | 2025-07-27 to 2025-08-02 | 270 | 90 | 180
TA 505 | detail | No | 2025-08-03 | 2025-08-09 | 2025-08-03 to 2025-08-09 | 270 | 91 | 179
TA 505 | detail | No | 2025-08-10 | 2025-08-16 | 2025-08-10 to 2025-08-16 | 270 | 93 | 177
TA 505 | detail | No | 2025-08-17 | 2025-08-23 | 2025-08-17 to 2025-08-23 | 270 | 95 | 175
TA 505 | detail | No | 2025-08-24 | 2025-08-30 | 2025-08-24 to 2025-08-30 | 271 | 97 | 174
TA 505 | detail | No | 2025-08-31 | 2025-09-06 | 2025-08-31 to 2025-09-06 | 272 | 98 | 174
TA 505 | detail | No | 2025-09-07 | 2025-09-13 | 2025-09-07 to 2025-09-13 | 274 | 105 | 169
TA 505 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 276 | 111 | 165
TA 505 | detail | No | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 | 279 | 119 | 160
TA 505 | detail | No | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 | 281 | 130 | 151
TA 505 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 283 | 134 | 149
TA 505 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 289 | 145 | 144
TA 505 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 292 | 149 | 143
TA 505 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 294 | 153 | 141
TA 505 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 297 | 160 | 137
TA 505 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 301 | 167 | 134
TA 505 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 305 | 174 | 131
TA 505 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 309 | 185 | 124
TA 505 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 311 | 193 | 118
TA 505 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 316 | 206 | 110
TA 505 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 319 | 216 | 103
TA 505 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 322 | 227 | 95
TA 505 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 327 | 239 | 88
TA 505 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 331 | 247 | 84
TA 505 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 334 | 254 | 80
TA 505 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 339 | 265 | 74
TA 505 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 344 | 276 | 68
TA 505 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 347 | 280 | 67
TA 505 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 349 | 288 | 61
TA 505 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 352 | 293 | 59
TA 505 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 354 | 300 | 54
TA 505 | detail | No | 2026-03-01 | 2026-03-07 | 2026-03-01 to 2026-03-07 | 355 | 303 | 52
TA 505 | detail | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 | 359 | 309 | 50
TA 505 | detail | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 | 361 | 312 | 49
TA 505 | detail | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 | 361 | 317 | 44
TA 505 | detail | No | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 | 362 | 324 | 38
TA 505 | detail | No | 2026-04-05 | 2026-04-11 | 2026-04-05 to 2026-04-11 | 364 | 330 | 34
TA 505 | detail | No | 2026-04-12 | 2026-04-18 | 2026-04-12 to 2026-04-18 | 368 | 338 | 30
TA 505 | detail | No | 2026-04-19 | 2026-04-25 | 2026-04-19 to 2026-04-25 | 369 | 343 | 26
TA 505 | detail | No | 2026-04-26 | 2026-05-02 | 2026-04-26 to 2026-05-02 | 370 | 347 | 23
TA 505 | detail | No | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 | 370 | 351 | 19
TA 505 | detail | No | 2026-05-10 | 2026-05-16 | 2026-05-10 to 2026-05-16 | 372 | 354 | 18
TA 505 | detail | No | 2026-05-17 | 2026-05-23 | 2026-05-17 to 2026-05-23 | 373 | 354 | 19
TA 509 | detail | No | 2024-12-29 | 2025-01-04 | 2024-12-29 to 2025-01-04 | 5 | 0 | 5
TA 509 | detail | No | 2025-01-05 | 2025-01-11 | 2025-01-05 to 2025-01-11 | 6 | 0 | 6
TA 509 | detail | No | 2025-01-26 | 2025-02-01 | 2025-01-26 to 2025-02-01 | 20 | 0 | 20
TA 509 | detail | No | 2025-02-23 | 2025-03-01 | 2025-02-23 to 2025-03-01 | 53 | 0 | 53
TA 509 | detail | No | 2025-03-02 | 2025-03-08 | 2025-03-02 to 2025-03-08 | 55 | 0 | 55
TA 509 | detail | No | 2025-03-30 | 2025-04-05 | 2025-03-30 to 2025-04-05 | 104 | 0 | 104
TA 509 | detail | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 | 105 | 0 | 105
TA 509 | detail | No | 2025-05-04 | 2025-05-10 | 2025-05-04 to 2025-05-10 | 117 | 0 | 117
TA 509 | detail | No | 2025-05-11 | 2025-05-17 | 2025-05-11 to 2025-05-17 | 124 | 0 | 124
TA 509 | detail | No | 2025-05-18 | 2025-05-24 | 2025-05-18 to 2025-05-24 | 135 | 0 | 135
TA 509 | detail | No | 2025-05-25 | 2025-05-31 | 2025-05-25 to 2025-05-31 | 144 | 0 | 144
TA 509 | detail | No | 2025-06-01 | 2025-06-07 | 2025-06-01 to 2025-06-07 | 150 | 0 | 150
TA 509 | detail | No | 2025-06-08 | 2025-06-14 | 2025-06-08 to 2025-06-14 | 152 | 0 | 152
TA 509 | detail | No | 2025-06-15 | 2025-06-21 | 2025-06-15 to 2025-06-21 | 156 | 0 | 156
TA 509 | detail | No | 2025-06-22 | 2025-06-28 | 2025-06-22 to 2025-06-28 | 158 | 0 | 158
TA 509 | detail | No | 2025-06-29 | 2025-07-05 | 2025-06-29 to 2025-07-05 | 159 | 0 | 159
TA 509 | detail | No | 2025-07-06 | 2025-07-12 | 2025-07-06 to 2025-07-12 | 162 | 0 | 162
TA 509 | detail | No | 2025-07-13 | 2025-07-19 | 2025-07-13 to 2025-07-19 | 164 | 0 | 164
TA 509 | detail | No | 2025-07-20 | 2025-07-26 | 2025-07-20 to 2025-07-26 | 165 | 0 | 165
TA 509 | detail | No | 2025-08-03 | 2025-08-09 | 2025-08-03 to 2025-08-09 | 166 | 0 | 166
TA 509 | detail | No | 2025-08-10 | 2025-08-16 | 2025-08-10 to 2025-08-16 | 168 | 0 | 168
TA 509 | detail | No | 2025-08-17 | 2025-08-23 | 2025-08-17 to 2025-08-23 | 171 | 0 | 171
TA 509 | detail | No | 2025-08-31 | 2025-09-06 | 2025-08-31 to 2025-09-06 | 171 | 1 | 170
TA 509 | detail | No | 2025-09-07 | 2025-09-13 | 2025-09-07 to 2025-09-13 | 171 | 4 | 167
TA 509 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 174 | 11 | 163
TA 509 | detail | No | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 | 175 | 17 | 158
TA 509 | detail | No | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 | 178 | 22 | 156
TA 509 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 180 | 25 | 155
TA 509 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 183 | 28 | 155
TA 509 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 185 | 30 | 155
TA 509 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 188 | 30 | 158
TA 509 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 199 | 32 | 167
TA 509 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 202 | 33 | 169
TA 509 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 207 | 34 | 173
TA 509 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 211 | 38 | 173
TA 509 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 215 | 43 | 172
TA 509 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 220 | 46 | 174
TA 509 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 224 | 51 | 173
TA 509 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 228 | 54 | 174
TA 509 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 229 | 60 | 169
TA 509 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 231 | 66 | 165
TA 509 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 231 | 69 | 162
TA 509 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 233 | 73 | 160
TA 509 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 234 | 80 | 154
TA 509 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 236 | 88 | 148
TA 509 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 237 | 96 | 141
TA 509 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 237 | 100 | 137
TA 509 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 240 | 111 | 129
TA 509 | detail | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 | 241 | 116 | 125
TA 509 | detail | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 | 242 | 125 | 117
TA 509 | detail | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 | 243 | 129 | 114
TA 509 | detail | No | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 | 246 | 142 | 104
TA 509 | detail | No | 2026-04-05 | 2026-04-11 | 2026-04-05 to 2026-04-11 | 251 | 153 | 98
TA 509 | detail | No | 2026-04-12 | 2026-04-18 | 2026-04-12 to 2026-04-18 | 255 | 163 | 92
TA 509 | detail | No | 2026-04-19 | 2026-04-25 | 2026-04-19 to 2026-04-25 | 257 | 171 | 86
TA 509 | detail | No | 2026-04-26 | 2026-05-02 | 2026-04-26 to 2026-05-02 | 259 | 182 | 77
TA 509 | detail | No | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 | 262 | 186 | 76
TA 509 | detail | No | 2026-05-10 | 2026-05-16 | 2026-05-10 to 2026-05-16 | 264 | 196 | 68
TA 509 | detail | No | 2026-05-17 | 2026-05-23 | 2026-05-17 to 2026-05-23 | 264 | 198 | 66
TA 510 | detail | No | 2025-02-09 | 2025-02-15 | 2025-02-09 to 2025-02-15 | 1 | 0 | 1
TA 510 | detail | No | 2025-02-16 | 2025-02-22 | 2025-02-16 to 2025-02-22 | 3 | 0 | 3
TA 510 | detail | No | 2025-02-23 | 2025-03-01 | 2025-02-23 to 2025-03-01 | 4 | 0 | 4
TA 510 | detail | No | 2025-03-02 | 2025-03-08 | 2025-03-02 to 2025-03-08 | 6 | 0 | 6
TA 510 | detail | No | 2025-03-09 | 2025-03-15 | 2025-03-09 to 2025-03-15 | 7 | 0 | 7
TA 510 | detail | No | 2025-03-16 | 2025-03-22 | 2025-03-16 to 2025-03-22 | 8 | 0 | 8
TA 510 | detail | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 | 10 | 0 | 10
TA 510 | detail | No | 2025-03-30 | 2025-04-05 | 2025-03-30 to 2025-04-05 | 11 | 0 | 11
TA 510 | detail | No | 2025-04-13 | 2025-04-19 | 2025-04-13 to 2025-04-19 | 14 | 0 | 14
TA 510 | detail | No | 2025-04-20 | 2025-04-26 | 2025-04-20 to 2025-04-26 | 16 | 0 | 16
TA 510 | detail | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 | 17 | 0 | 17
TA 510 | detail | No | 2025-05-11 | 2025-05-17 | 2025-05-11 to 2025-05-17 | 21 | 0 | 21
TA 510 | detail | No | 2025-05-18 | 2025-05-24 | 2025-05-18 to 2025-05-24 | 22 | 0 | 22
TA 510 | detail | No | 2025-05-25 | 2025-05-31 | 2025-05-25 to 2025-05-31 | 24 | 0 | 24
TA 510 | detail | No | 2025-06-01 | 2025-06-07 | 2025-06-01 to 2025-06-07 | 25 | 0 | 25
TA 510 | detail | No | 2025-07-20 | 2025-07-26 | 2025-07-20 to 2025-07-26 | 26 | 0 | 26
TA 510 | detail | No | 2025-08-31 | 2025-09-06 | 2025-08-31 to 2025-09-06 | 27 | 0 | 27
TA 510 | detail | No | 2025-09-07 | 2025-09-13 | 2025-09-07 to 2025-09-13 | 28 | 0 | 28
TA 510 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 29 | 0 | 29
TA 510 | detail | No | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 | 32 | 0 | 32
TA 510 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 33 | 0 | 33
TA 510 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 37 | 0 | 37
TA 510 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 38 | 0 | 38
TA 510 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 39 | 0 | 39
TA 510 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 43 | 0 | 43
TA 510 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 45 | 0 | 45
TA 510 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 47 | 0 | 47
TA 510 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 49 | 0 | 49
TA 510 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 50 | 0 | 50
TA 510 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 54 | 1 | 53
TA 510 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 55 | 3 | 52
TA 510 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 55 | 4 | 51
TA 510 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 56 | 8 | 48
TA 510 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 60 | 10 | 50
TA 510 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 60 | 12 | 48
TA 510 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 63 | 14 | 49
TA 510 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 63 | 17 | 46
TA 510 | detail | No | 2026-03-01 | 2026-03-07 | 2026-03-01 to 2026-03-07 | 63 | 18 | 45
TA 510 | detail | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 | 64 | 19 | 45
TA 510 | detail | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 | 64 | 21 | 43
TA 510 | detail | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 | 64 | 23 | 41
TA 510 | detail | No | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 | 68 | 25 | 43
TA 510 | detail | No | 2026-04-05 | 2026-04-11 | 2026-04-05 to 2026-04-11 | 69 | 26 | 43
TA 510 | detail | No | 2026-04-12 | 2026-04-18 | 2026-04-12 to 2026-04-18 | 72 | 27 | 45
TA 510 | detail | No | 2026-04-19 | 2026-04-25 | 2026-04-19 to 2026-04-25 | 76 | 28 | 48
TA 510 | detail | No | 2026-04-26 | 2026-05-02 | 2026-04-26 to 2026-05-02 | 78 | 29 | 49
TA 510 | detail | No | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 | 80 | 31 | 49
TA 510 | detail | No | 2026-05-10 | 2026-05-16 | 2026-05-10 to 2026-05-16 | 81 | 33 | 48
TA 510 | detail | No | 2026-05-17 | 2026-05-23 | 2026-05-17 to 2026-05-23 | 85 | 34 | 51
TA 512 | detail | No | 2025-02-23 | 2025-03-01 | 2025-02-23 to 2025-03-01 | 3 | 0 | 3
TA 512 | detail | No | 2025-03-02 | 2025-03-08 | 2025-03-02 to 2025-03-08 | 6 | 0 | 6
TA 512 | detail | No | 2025-03-09 | 2025-03-15 | 2025-03-09 to 2025-03-15 | 12 | 0 | 12
TA 512 | detail | No | 2025-03-16 | 2025-03-22 | 2025-03-16 to 2025-03-22 | 18 | 0 | 18
TA 512 | detail | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 | 26 | 0 | 26
TA 512 | detail | No | 2025-03-30 | 2025-04-05 | 2025-03-30 to 2025-04-05 | 33 | 0 | 33
TA 512 | detail | No | 2025-04-06 | 2025-04-12 | 2025-04-06 to 2025-04-12 | 37 | 0 | 37
TA 512 | detail | No | 2025-04-13 | 2025-04-19 | 2025-04-13 to 2025-04-19 | 44 | 0 | 44
TA 512 | detail | No | 2025-04-20 | 2025-04-26 | 2025-04-20 to 2025-04-26 | 49 | 0 | 49
TA 512 | detail | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 | 53 | 0 | 53
TA 512 | detail | No | 2025-05-04 | 2025-05-10 | 2025-05-04 to 2025-05-10 | 59 | 0 | 59
TA 512 | detail | No | 2025-05-11 | 2025-05-17 | 2025-05-11 to 2025-05-17 | 65 | 0 | 65
TA 512 | detail | No | 2025-05-18 | 2025-05-24 | 2025-05-18 to 2025-05-24 | 72 | 0 | 72
TA 512 | detail | No | 2025-05-25 | 2025-05-31 | 2025-05-25 to 2025-05-31 | 76 | 0 | 76
TA 512 | detail | No | 2025-06-01 | 2025-06-07 | 2025-06-01 to 2025-06-07 | 82 | 0 | 82
TA 512 | detail | No | 2025-06-08 | 2025-06-14 | 2025-06-08 to 2025-06-14 | 88 | 0 | 88
TA 512 | detail | No | 2025-06-15 | 2025-06-21 | 2025-06-15 to 2025-06-21 | 95 | 0 | 95
TA 512 | detail | No | 2025-06-22 | 2025-06-28 | 2025-06-22 to 2025-06-28 | 101 | 0 | 101
TA 512 | detail | No | 2025-06-29 | 2025-07-05 | 2025-06-29 to 2025-07-05 | 110 | 0 | 110
TA 512 | detail | No | 2025-07-06 | 2025-07-12 | 2025-07-06 to 2025-07-12 | 117 | 0 | 117
TA 512 | detail | No | 2025-07-13 | 2025-07-19 | 2025-07-13 to 2025-07-19 | 127 | 0 | 127
TA 512 | detail | No | 2025-07-20 | 2025-07-26 | 2025-07-20 to 2025-07-26 | 137 | 0 | 137
TA 512 | detail | No | 2025-07-27 | 2025-08-02 | 2025-07-27 to 2025-08-02 | 146 | 0 | 146
TA 512 | detail | No | 2025-08-03 | 2025-08-09 | 2025-08-03 to 2025-08-09 | 157 | 0 | 157
TA 512 | detail | No | 2025-08-10 | 2025-08-16 | 2025-08-10 to 2025-08-16 | 161 | 1 | 160
TA 512 | detail | No | 2025-08-17 | 2025-08-23 | 2025-08-17 to 2025-08-23 | 165 | 3 | 162
TA 512 | detail | No | 2025-08-24 | 2025-08-30 | 2025-08-24 to 2025-08-30 | 168 | 6 | 162
TA 512 | detail | No | 2025-08-31 | 2025-09-06 | 2025-08-31 to 2025-09-06 | 174 | 10 | 164
TA 512 | detail | No | 2025-09-07 | 2025-09-13 | 2025-09-07 to 2025-09-13 | 177 | 15 | 162
TA 512 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 181 | 18 | 163
TA 512 | detail | No | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 | 186 | 23 | 163
TA 512 | detail | No | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 | 191 | 26 | 165
TA 512 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 192 | 28 | 164
TA 512 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 199 | 32 | 167
TA 512 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 203 | 34 | 169
TA 512 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 213 | 36 | 177
TA 512 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 219 | 39 | 180
TA 512 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 227 | 42 | 185
TA 512 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 234 | 47 | 187
TA 512 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 240 | 52 | 188
TA 512 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 249 | 56 | 193
TA 512 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 257 | 65 | 192
TA 512 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 266 | 72 | 194
TA 512 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 273 | 77 | 196
TA 512 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 277 | 86 | 191
TA 512 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 279 | 90 | 189
TA 512 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 284 | 99 | 185
TA 512 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 286 | 110 | 176
TA 512 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 287 | 126 | 161
TA 512 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 289 | 138 | 151
TA 512 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 289 | 151 | 138
TA 512 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 290 | 159 | 131
TA 512 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 291 | 170 | 121
TA 512 | detail | No | 2026-03-01 | 2026-03-07 | 2026-03-01 to 2026-03-07 | 292 | 177 | 115
TA 512 | detail | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 | 293 | 185 | 108
TA 512 | detail | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 | 294 | 192 | 102
TA 512 | detail | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 | 294 | 197 | 97
TA 512 | detail | No | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 | 295 | 205 | 90
TA 512 | detail | No | 2026-04-05 | 2026-04-11 | 2026-04-05 to 2026-04-11 | 296 | 208 | 88
TA 512 | detail | No | 2026-04-12 | 2026-04-18 | 2026-04-12 to 2026-04-18 | 298 | 214 | 84
TA 512 | detail | No | 2026-04-19 | 2026-04-25 | 2026-04-19 to 2026-04-25 | 300 | 216 | 84
TA 512 | detail | No | 2026-04-26 | 2026-05-02 | 2026-04-26 to 2026-05-02 | 301 | 217 | 84
TA 512 | detail | No | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 | 302 | 219 | 83
TA 512 | detail | No | 2026-05-10 | 2026-05-16 | 2026-05-10 to 2026-05-16 | 302 | 221 | 81
TA 513 | detail | No | 2025-03-16 | 2025-03-22 | 2025-03-16 to 2025-03-22 | 1 | 0 | 1
TA 513 | detail | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 | 2 | 0 | 2
TA 513 | detail | No | 2025-03-30 | 2025-04-05 | 2025-03-30 to 2025-04-05 | 5 | 0 | 5
TA 513 | detail | No | 2025-04-06 | 2025-04-12 | 2025-04-06 to 2025-04-12 | 7 | 0 | 7
TA 513 | detail | No | 2025-04-13 | 2025-04-19 | 2025-04-13 to 2025-04-19 | 10 | 0 | 10
TA 513 | detail | No | 2025-04-20 | 2025-04-26 | 2025-04-20 to 2025-04-26 | 15 | 0 | 15
TA 513 | detail | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 | 20 | 0 | 20
TA 513 | detail | No | 2025-05-04 | 2025-05-10 | 2025-05-04 to 2025-05-10 | 25 | 0 | 25
TA 513 | detail | No | 2025-05-11 | 2025-05-17 | 2025-05-11 to 2025-05-17 | 30 | 0 | 30
TA 513 | detail | No | 2025-05-18 | 2025-05-24 | 2025-05-18 to 2025-05-24 | 33 | 0 | 33
TA 513 | detail | No | 2025-05-25 | 2025-05-31 | 2025-05-25 to 2025-05-31 | 36 | 0 | 36
TA 513 | detail | No | 2025-06-01 | 2025-06-07 | 2025-06-01 to 2025-06-07 | 39 | 0 | 39
TA 513 | detail | No | 2025-06-08 | 2025-06-14 | 2025-06-08 to 2025-06-14 | 40 | 0 | 40
TA 513 | detail | No | 2025-06-15 | 2025-06-21 | 2025-06-15 to 2025-06-21 | 43 | 0 | 43
TA 513 | detail | No | 2025-06-22 | 2025-06-28 | 2025-06-22 to 2025-06-28 | 44 | 0 | 44
TA 513 | detail | No | 2025-06-29 | 2025-07-05 | 2025-06-29 to 2025-07-05 | 47 | 0 | 47
TA 513 | detail | No | 2025-07-06 | 2025-07-12 | 2025-07-06 to 2025-07-12 | 48 | 0 | 48
TA 513 | detail | No | 2025-07-13 | 2025-07-19 | 2025-07-13 to 2025-07-19 | 50 | 0 | 50
TA 513 | detail | No | 2025-07-20 | 2025-07-26 | 2025-07-20 to 2025-07-26 | 54 | 0 | 54
TA 513 | detail | No | 2025-08-17 | 2025-08-23 | 2025-08-17 to 2025-08-23 | 58 | 0 | 58
TA 513 | detail | No | 2025-09-07 | 2025-09-13 | 2025-09-07 to 2025-09-13 | 61 | 0 | 61
TA 513 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 63 | 0 | 63
TA 513 | detail | No | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 | 64 | 1 | 63
TA 513 | detail | No | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 | 66 | 3 | 63
TA 513 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 66 | 4 | 62
TA 513 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 66 | 5 | 61
TA 513 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 67 | 7 | 60
TA 513 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 67 | 8 | 59
TA 513 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 68 | 10 | 58
TA 513 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 69 | 12 | 57
TA 513 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 69 | 13 | 56
TA 513 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 69 | 14 | 55
TA 513 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 71 | 15 | 56
TA 513 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 71 | 16 | 55
TA 513 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 73 | 17 | 56
TA 513 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 73 | 18 | 55
TA 513 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 74 | 19 | 55
TA 513 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 74 | 20 | 54
TA 513 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 74 | 21 | 53
TA 513 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 75 | 21 | 54
TA 513 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 76 | 21 | 55
TA 513 | detail | No | 2026-03-01 | 2026-03-07 | 2026-03-01 to 2026-03-07 | 76 | 22 | 54
TA 513 | detail | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 | 76 | 23 | 53
TA 513 | detail | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 | 76 | 25 | 51
TA 513 | detail | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 | 77 | 26 | 51
TA 513 | detail | No | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 | 77 | 27 | 50
TA 513 | detail | No | 2026-04-05 | 2026-04-11 | 2026-04-05 to 2026-04-11 | 77 | 28 | 49
TA 513 | detail | No | 2026-04-19 | 2026-04-25 | 2026-04-19 to 2026-04-25 | 79 | 28 | 51
TA 513 | detail | No | 2026-04-26 | 2026-05-02 | 2026-04-26 to 2026-05-02 | 80 | 28 | 52
TA 513 | detail | No | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 | 82 | 28 | 54
TA 513 | detail | No | 2026-05-17 | 2026-05-23 | 2026-05-17 to 2026-05-23 | 84 | 29 | 55
TA 515 | missing | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 |  | 1
TA 515 | missing | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 |  | 2
TA 601 | detail | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 | 0 | 1 | -1
TA 601 | detail | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 | 1 | 1 | 0
TA 601 | detail | No | 2025-08-03 | 2025-08-09 | 2025-08-03 to 2025-08-09 | 2 | 1 | 1
TA 601 | detail | No | 2025-08-17 | 2025-08-23 | 2025-08-17 to 2025-08-23 | 3 | 1 | 2
TA 601 | detail | No | 2025-09-07 | 2025-09-13 | 2025-09-07 to 2025-09-13 | 4 | 1 | 3
TA 601 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 5 | 1 | 4
TA 601 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 6 | 1 | 5
TA 601 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 11 | 1 | 10
TA 601 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 13 | 1 | 12
TA 601 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 15 | 1 | 14
TA 601 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 18 | 1 | 17
TA 601 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 19 | 1 | 18
TA 601 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 22 | 1 | 21
TA 601 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 24 | 1 | 23
TA 601 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 26 | 1 | 25
TA 601 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 32 | 2 | 30
TA 601 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 39 | 3 | 36
TA 601 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 46 | 4 | 42
TA 601 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 54 | 7 | 47
TA 601 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 64 | 11 | 53
TA 601 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 75 | 17 | 58
TA 601 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 94 | 25 | 69
TA 601 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 102 | 31 | 71
TA 601 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 116 | 38 | 78
TA 601 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 126 | 46 | 80
TA 601 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 140 | 54 | 86
TA 601 | detail | No | 2026-03-01 | 2026-03-07 | 2026-03-01 to 2026-03-07 | 146 | 58 | 88
TA 601 | detail | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 | 153 | 61 | 92
TA 601 | detail | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 | 161 | 65 | 96
TA 601 | detail | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 | 166 | 66 | 100
TA 601 | detail | No | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 | 170 | 68 | 102
TA 601 | detail | No | 2026-04-05 | 2026-04-11 | 2026-04-05 to 2026-04-11 | 173 | 69 | 104
TA 601 | detail | No | 2026-04-12 | 2026-04-18 | 2026-04-12 to 2026-04-18 | 179 | 70 | 109
TA 601 | detail | No | 2026-04-19 | 2026-04-25 | 2026-04-19 to 2026-04-25 | 181 | 70 | 111
TA 601 | detail | No | 2026-04-26 | 2026-05-02 | 2026-04-26 to 2026-05-02 | 184 | 70 | 114
TA 601 | detail | No | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 | 185 | 70 | 115
TA 601 | detail | No | 2026-05-10 | 2026-05-16 | 2026-05-10 to 2026-05-16 | 188 | 70 | 118
TA 601 | detail | No | 2026-05-17 | 2026-05-23 | 2026-05-17 to 2026-05-23 | 191 | 71 | 120
TA 602 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 1 | 0 | 1
TA 602 | detail | No | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 | 2 | 0 | 2
TA 602 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 4 | 0 | 4
TA 602 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 6 | 0 | 6
TA 602 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 9 | 0 | 9
TA 602 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 12 | 0 | 12
TA 602 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 17 | 0 | 17
TA 602 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 23 | 0 | 23
TA 602 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 30 | 0 | 30
TA 602 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 36 | 0 | 36
TA 602 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 45 | 0 | 45
TA 602 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 55 | 0 | 55
TA 602 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 63 | 0 | 63
TA 602 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 72 | 0 | 72
TA 602 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 78 | 0 | 78
TA 602 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 82 | 0 | 82
TA 602 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 85 | 0 | 85
TA 602 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 88 | 0 | 88
TA 602 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 97 | 0 | 97
TA 602 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 100 | 0 | 100
TA 602 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 105 | 0 | 105
TA 602 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 107 | 0 | 107
TA 602 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 109 | 3 | 106
TA 602 | detail | No | 2026-03-01 | 2026-03-07 | 2026-03-01 to 2026-03-07 | 111 | 3 | 108
TA 602 | detail | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 | 112 | 6 | 106
TA 602 | detail | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 | 113 | 9 | 104
TA 602 | detail | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 | 113 | 13 | 100
TA 602 | detail | No | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 | 116 | 16 | 100
TA 602 | detail | No | 2026-04-05 | 2026-04-11 | 2026-04-05 to 2026-04-11 | 120 | 18 | 102
TA 602 | detail | No | 2026-04-12 | 2026-04-18 | 2026-04-12 to 2026-04-18 | 125 | 19 | 106
TA 602 | detail | No | 2026-04-19 | 2026-04-25 | 2026-04-19 to 2026-04-25 | 131 | 21 | 110
TA 602 | detail | No | 2026-04-26 | 2026-05-02 | 2026-04-26 to 2026-05-02 | 136 | 23 | 113
TA 602 | detail | No | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 | 141 | 30 | 111
TA 602 | detail | No | 2026-05-10 | 2026-05-16 | 2026-05-10 to 2026-05-16 | 143 | 37 | 106
TA 602 | detail | No | 2026-05-17 | 2026-05-23 | 2026-05-17 to 2026-05-23 | 143 | 40 | 103
TB 408 | missing | No | 2024-02-04 | 2024-02-10 | 2024-02-04 to 2024-02-10 |  | 3
TB 408 | missing | No | 2024-02-11 | 2024-02-17 | 2024-02-11 to 2024-02-17 |  | 7
TB 408 | missing | No | 2024-02-18 | 2024-02-24 | 2024-02-18 to 2024-02-24 |  | 15
TB 408 | missing | No | 2024-02-25 | 2024-03-02 | 2024-02-25 to 2024-03-02 |  | 22
TB 408 | missing | No | 2024-03-03 | 2024-03-09 | 2024-03-03 to 2024-03-09 |  | 26
TB 408 | missing | No | 2024-03-10 | 2024-03-16 | 2024-03-10 to 2024-03-16 |  | 31
TB 408 | missing | No | 2024-03-17 | 2024-03-23 | 2024-03-17 to 2024-03-23 |  | 36
TB 408 | missing | No | 2024-03-24 | 2024-03-30 | 2024-03-24 to 2024-03-30 |  | 40
TB 408 | missing | No | 2024-03-31 | 2024-04-06 | 2024-03-31 to 2024-04-06 |  | 44
TB 408 | missing | No | 2024-04-07 | 2024-04-13 | 2024-04-07 to 2024-04-13 |  | 50
TB 408 | missing | No | 2024-04-14 | 2024-04-20 | 2024-04-14 to 2024-04-20 |  | 53
TB 408 | missing | No | 2024-04-21 | 2024-04-27 | 2024-04-21 to 2024-04-27 |  | 60
TB 408 | missing | No | 2024-04-28 | 2024-05-04 | 2024-04-28 to 2024-05-04 |  | 63
TB 408 | missing | No | 2024-05-05 | 2024-05-11 | 2024-05-05 to 2024-05-11 |  | 66
TB 408 | missing | No | 2024-05-12 | 2024-05-18 | 2024-05-12 to 2024-05-18 |  | 69
TB 408 | missing | No | 2024-05-19 | 2024-05-25 | 2024-05-19 to 2024-05-25 |  | 72
TB 408 | missing | No | 2024-05-26 | 2024-06-01 | 2024-05-26 to 2024-06-01 |  | 75
TB 408 | missing | No | 2024-06-09 | 2024-06-15 | 2024-06-09 to 2024-06-15 |  | 76
TB 408 | missing | No | 2024-06-16 | 2024-06-22 | 2024-06-16 to 2024-06-22 |  | 77
TB 408 | missing | No | 2024-06-23 | 2024-06-29 | 2024-06-23 to 2024-06-29 |  | 78
TB 408 | missing | No | 2024-07-07 | 2024-07-13 | 2024-07-07 to 2024-07-13 |  | 79
TB 408 | missing | No | 2024-07-21 | 2024-07-27 | 2024-07-21 to 2024-07-27 |  | 80
TB 408 | missing | No | 2024-08-18 | 2024-08-24 | 2024-08-18 to 2024-08-24 |  | 81
TB 408 | missing | No | 2024-08-25 | 2024-08-31 | 2024-08-25 to 2024-08-31 |  | 83
TB 408 | missing | No | 2024-09-01 | 2024-09-07 | 2024-09-01 to 2024-09-07 |  | 84
TB 408 | missing | No | 2024-09-08 | 2024-09-14 | 2024-09-08 to 2024-09-14 |  | 88
TB 408 | missing | No | 2024-09-15 | 2024-09-21 | 2024-09-15 to 2024-09-21 |  | 91
TB 408 | missing | No | 2024-09-22 | 2024-09-28 | 2024-09-22 to 2024-09-28 |  | 97
TB 408 | missing | No | 2024-09-29 | 2024-10-05 | 2024-09-29 to 2024-10-05 |  | 103
TB 408 | missing | No | 2024-10-06 | 2024-10-12 | 2024-10-06 to 2024-10-12 |  | 111
TB 408 | missing | No | 2024-10-13 | 2024-10-19 | 2024-10-13 to 2024-10-19 |  | 118
TB 408 | missing | No | 2024-10-20 | 2024-10-26 | 2024-10-20 to 2024-10-26 |  | 125
TB 408 | missing | No | 2024-10-27 | 2024-11-02 | 2024-10-27 to 2024-11-02 |  | 132
TB 408 | missing | No | 2024-11-03 | 2024-11-09 | 2024-11-03 to 2024-11-09 |  | 138
TB 408 | missing | No | 2024-11-10 | 2024-11-16 | 2024-11-10 to 2024-11-16 |  | 143
TB 408 | missing | No | 2024-11-17 | 2024-11-23 | 2024-11-17 to 2024-11-23 |  | 151
TB 408 | missing | No | 2024-11-24 | 2024-11-30 | 2024-11-24 to 2024-11-30 |  | 159
TB 408 | missing | No | 2024-12-01 | 2024-12-07 | 2024-12-01 to 2024-12-07 |  | 164
TB 408 | missing | No | 2024-12-08 | 2024-12-14 | 2024-12-08 to 2024-12-14 |  | 167
TB 408 | missing | No | 2024-12-15 | 2024-12-21 | 2024-12-15 to 2024-12-21 |  | 169
TB 408 | missing | No | 2024-12-22 | 2024-12-28 | 2024-12-22 to 2024-12-28 |  | 170
TB 408 | missing | No | 2024-12-29 | 2025-01-04 | 2024-12-29 to 2025-01-04 |  | 172
TB 408 | missing | No | 2025-01-05 | 2025-01-11 | 2025-01-05 to 2025-01-11 |  | 175
TB 408 | missing | No | 2025-01-12 | 2025-01-18 | 2025-01-12 to 2025-01-18 |  | 180
TB 408 | missing | No | 2025-01-19 | 2025-01-25 | 2025-01-19 to 2025-01-25 |  | 182
TB 408 | missing | No | 2025-01-26 | 2025-02-01 | 2025-01-26 to 2025-02-01 |  | 186
TB 408 | missing | No | 2025-02-02 | 2025-02-08 | 2025-02-02 to 2025-02-08 |  | 190
TB 408 | missing | No | 2025-02-09 | 2025-02-15 | 2025-02-09 to 2025-02-15 |  | 195
TB 408 | missing | No | 2025-02-16 | 2025-02-22 | 2025-02-16 to 2025-02-22 |  | 198
TB 408 | missing | No | 2025-02-23 | 2025-03-01 | 2025-02-23 to 2025-03-01 |  | 201
TB 408 | missing | No | 2025-03-02 | 2025-03-08 | 2025-03-02 to 2025-03-08 |  | 203
TB 408 | missing | No | 2025-03-09 | 2025-03-15 | 2025-03-09 to 2025-03-15 |  | 205
TB 408 | missing | No | 2025-03-16 | 2025-03-22 | 2025-03-16 to 2025-03-22 |  | 208
TB 408 | missing | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 |  | 211
TB 408 | missing | No | 2025-03-30 | 2025-04-05 | 2025-03-30 to 2025-04-05 |  | 215
TB 408 | missing | No | 2025-04-06 | 2025-04-12 | 2025-04-06 to 2025-04-12 |  | 218
TB 408 | missing | No | 2025-04-13 | 2025-04-19 | 2025-04-13 to 2025-04-19 |  | 219
TB 408 | missing | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 |  | 221
TB 408 | missing | No | 2025-05-25 | 2025-05-31 | 2025-05-25 to 2025-05-31 |  | 222
TB 408 | missing | No | 2025-06-08 | 2025-06-14 | 2025-06-08 to 2025-06-14 |  | 223
TB 408 | missing | No | 2025-06-15 | 2025-06-21 | 2025-06-15 to 2025-06-21 |  | 224
TB 408 | missing | No | 2025-06-22 | 2025-06-28 | 2025-06-22 to 2025-06-28 |  | 226
TB 408 | missing | No | 2025-06-29 | 2025-07-05 | 2025-06-29 to 2025-07-05 |  | 230
TB 408 | missing | No | 2025-07-06 | 2025-07-12 | 2025-07-06 to 2025-07-12 |  | 231
TB 408 | missing | No | 2025-07-13 | 2025-07-19 | 2025-07-13 to 2025-07-19 |  | 236
TB 408 | missing | No | 2025-07-20 | 2025-07-26 | 2025-07-20 to 2025-07-26 |  | 243
TB 408 | missing | No | 2025-07-27 | 2025-08-02 | 2025-07-27 to 2025-08-02 |  | 252
TB 408 | missing | No | 2025-08-03 | 2025-08-09 | 2025-08-03 to 2025-08-09 |  | 263
TB 408 | missing | No | 2025-08-10 | 2025-08-16 | 2025-08-10 to 2025-08-16 |  | 268
TB 408 | missing | No | 2025-08-17 | 2025-08-23 | 2025-08-17 to 2025-08-23 |  | 284
TB 408 | missing | No | 2025-08-24 | 2025-08-30 | 2025-08-24 to 2025-08-30 |  | 299
TB 408 | missing | No | 2025-08-31 | 2025-09-06 | 2025-08-31 to 2025-09-06 |  | 314
TB 408 | missing | No | 2025-09-07 | 2025-09-13 | 2025-09-07 to 2025-09-13 |  | 327
TB 408 | missing | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 |  | 334
TB 408 | missing | No | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 |  | 344
TB 408 | missing | No | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 |  | 351
TB 408 | missing | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 |  | 356
TB 408 | missing | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 |  | 362
TB 408 | missing | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 |  | 367
TB 408 | missing | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 |  | 375
TB 408 | missing | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 |  | 382
TB 408 | missing | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 |  | 389
TB 408 | missing | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 |  | 398
TB 408 | missing | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 |  | 403
TB 408 | missing | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 |  | 412
TB 408 | missing | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 |  | 418
TB 408 | missing | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 |  | 429
TB 408 | missing | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 |  | 438
TB 408 | missing | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 |  | 448
TB 408 | missing | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 |  | 454
TB 408 | missing | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 |  | 457
TB 408 | missing | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 |  | 458
TB 408 | missing | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 |  | 459
TB 408 | missing | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 |  | 460
TB 408 | missing | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 |  | 461
TB 408 | missing | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 |  | 465
TB 408 | missing | No | 2026-03-01 | 2026-03-07 | 2026-03-01 to 2026-03-07 |  | 467
TB 408 | missing | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 |  | 469
TB 408 | missing | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 |  | 472
TB 408 | missing | No | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 |  | 475
TB 408 | missing | No | 2026-04-19 | 2026-04-25 | 2026-04-19 to 2026-04-25 |  | 477
TB 408 | missing | No | 2026-04-26 | 2026-05-02 | 2026-04-26 to 2026-05-02 |  | 478
TB 408 | missing | No | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 |  | 479
TB 501 | detail | No | 2024-08-11 | 2024-08-17 | 2024-08-11 to 2024-08-17 | 2 | 0 | 2
TB 501 | detail | No | 2024-08-18 | 2024-08-24 | 2024-08-18 to 2024-08-24 | 3 | 0 | 3
TB 501 | detail | No | 2024-09-08 | 2024-09-14 | 2024-09-08 to 2024-09-14 | 5 | 0 | 5
TB 501 | detail | No | 2024-09-15 | 2024-09-21 | 2024-09-15 to 2024-09-21 | 7 | 0 | 7
TB 501 | detail | No | 2024-09-22 | 2024-09-28 | 2024-09-22 to 2024-09-28 | 10 | 0 | 10
TB 501 | detail | No | 2024-09-29 | 2024-10-05 | 2024-09-29 to 2024-10-05 | 12 | 0 | 12
TB 501 | detail | No | 2024-10-06 | 2024-10-12 | 2024-10-06 to 2024-10-12 | 16 | 0 | 16
TB 501 | detail | No | 2024-10-13 | 2024-10-19 | 2024-10-13 to 2024-10-19 | 19 | 0 | 19
TB 501 | detail | No | 2024-10-20 | 2024-10-26 | 2024-10-20 to 2024-10-26 | 30 | 0 | 30
TB 501 | detail | No | 2024-10-27 | 2024-11-02 | 2024-10-27 to 2024-11-02 | 35 | 0 | 35
TB 501 | detail | No | 2024-11-03 | 2024-11-09 | 2024-11-03 to 2024-11-09 | 43 | 0 | 43
TB 501 | detail | No | 2024-11-10 | 2024-11-16 | 2024-11-10 to 2024-11-16 | 48 | 0 | 48
TB 501 | detail | No | 2024-11-17 | 2024-11-23 | 2024-11-17 to 2024-11-23 | 54 | 0 | 54
TB 501 | detail | No | 2024-11-24 | 2024-11-30 | 2024-11-24 to 2024-11-30 | 61 | 0 | 61
TB 501 | detail | No | 2024-12-01 | 2024-12-07 | 2024-12-01 to 2024-12-07 | 64 | 0 | 64
TB 501 | detail | No | 2024-12-08 | 2024-12-14 | 2024-12-08 to 2024-12-14 | 68 | 0 | 68
TB 501 | detail | No | 2024-12-15 | 2024-12-21 | 2024-12-15 to 2024-12-21 | 76 | 0 | 76
TB 501 | detail | No | 2024-12-22 | 2024-12-28 | 2024-12-22 to 2024-12-28 | 84 | 3 | 81
TB 501 | detail | No | 2024-12-29 | 2025-01-04 | 2024-12-29 to 2025-01-04 | 89 | 6 | 83
TB 501 | detail | No | 2025-01-05 | 2025-01-11 | 2025-01-05 to 2025-01-11 | 95 | 10 | 85
TB 501 | detail | No | 2025-01-12 | 2025-01-18 | 2025-01-12 to 2025-01-18 | 101 | 14 | 87
TB 501 | detail | No | 2025-01-19 | 2025-01-25 | 2025-01-19 to 2025-01-25 | 105 | 18 | 87
TB 501 | detail | No | 2025-01-26 | 2025-02-01 | 2025-01-26 to 2025-02-01 | 109 | 23 | 86
TB 501 | detail | No | 2025-02-02 | 2025-02-08 | 2025-02-02 to 2025-02-08 | 116 | 27 | 89
TB 501 | detail | No | 2025-02-09 | 2025-02-15 | 2025-02-09 to 2025-02-15 | 121 | 36 | 85
TB 501 | detail | No | 2025-02-16 | 2025-02-22 | 2025-02-16 to 2025-02-22 | 126 | 47 | 79
TB 501 | detail | No | 2025-02-23 | 2025-03-01 | 2025-02-23 to 2025-03-01 | 130 | 61 | 69
TB 501 | detail | No | 2025-03-02 | 2025-03-08 | 2025-03-02 to 2025-03-08 | 131 | 74 | 57
TB 501 | detail | No | 2025-03-09 | 2025-03-15 | 2025-03-09 to 2025-03-15 | 132 | 80 | 52
TB 501 | detail | No | 2025-03-16 | 2025-03-22 | 2025-03-16 to 2025-03-22 | 136 | 88 | 48
TB 501 | detail | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 | 139 | 96 | 43
TB 501 | detail | No | 2025-03-30 | 2025-04-05 | 2025-03-30 to 2025-04-05 | 140 | 104 | 36
TB 501 | detail | No | 2025-04-06 | 2025-04-12 | 2025-04-06 to 2025-04-12 | 141 | 109 | 32
TB 501 | detail | No | 2025-04-13 | 2025-04-19 | 2025-04-13 to 2025-04-19 | 144 | 113 | 31
TB 501 | detail | No | 2025-04-20 | 2025-04-26 | 2025-04-20 to 2025-04-26 | 147 | 118 | 29
TB 501 | detail | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 | 150 | 122 | 28
TB 501 | detail | No | 2025-05-04 | 2025-05-10 | 2025-05-04 to 2025-05-10 | 151 | 124 | 27
TB 501 | detail | No | 2025-05-11 | 2025-05-17 | 2025-05-11 to 2025-05-17 | 155 | 127 | 28
TB 501 | detail | No | 2025-05-18 | 2025-05-24 | 2025-05-18 to 2025-05-24 | 160 | 132 | 28
TB 501 | detail | No | 2025-05-25 | 2025-05-31 | 2025-05-25 to 2025-05-31 | 168 | 138 | 30
TB 501 | detail | No | 2025-06-01 | 2025-06-07 | 2025-06-01 to 2025-06-07 | 172 | 141 | 31
TB 501 | detail | No | 2025-06-08 | 2025-06-14 | 2025-06-08 to 2025-06-14 | 173 | 145 | 28
TB 501 | detail | No | 2025-06-15 | 2025-06-21 | 2025-06-15 to 2025-06-21 | 173 | 149 | 24
TB 501 | detail | No | 2025-06-22 | 2025-06-28 | 2025-06-22 to 2025-06-28 | 173 | 155 | 18
TB 501 | detail | No | 2025-06-29 | 2025-07-05 | 2025-06-29 to 2025-07-05 | 174 | 160 | 14
TB 501 | detail | No | 2025-07-06 | 2025-07-12 | 2025-07-06 to 2025-07-12 | 175 | 163 | 12
TB 501 | detail | No | 2025-07-13 | 2025-07-19 | 2025-07-13 to 2025-07-19 | 175 | 166 | 9
TB 501 | detail | No | 2025-07-20 | 2025-07-26 | 2025-07-20 to 2025-07-26 | 175 | 168 | 7
TB 501 | detail | No | 2025-07-27 | 2025-08-02 | 2025-07-27 to 2025-08-02 | 175 | 169 | 6
TB 501 | detail | No | 2025-08-10 | 2025-08-16 | 2025-08-10 to 2025-08-16 | 175 | 170 | 5
TB 501 | detail | No | 2025-08-17 | 2025-08-23 | 2025-08-17 to 2025-08-23 | 177 | 172 | 5
TB 501 | detail | No | 2025-08-24 | 2025-08-30 | 2025-08-24 to 2025-08-30 | 178 | 172 | 6
TB 501 | detail | No | 2025-08-31 | 2025-09-06 | 2025-08-31 to 2025-09-06 | 179 | 173 | 6
TB 501 | detail | No | 2025-09-07 | 2025-09-13 | 2025-09-07 to 2025-09-13 | 182 | 173 | 9
TB 501 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 183 | 173 | 10
TB 501 | detail | No | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 | 185 | 173 | 12
TB 501 | detail | No | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 | 186 | 173 | 13
TB 501 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 188 | 173 | 15
TB 501 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 190 | 173 | 17
TB 501 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 191 | 175 | 16
TB 501 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 192 | 178 | 14
TB 501 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 195 | 181 | 14
TB 501 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 196 | 184 | 12
TB 501 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 198 | 189 | 9
TB 501 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 199 | 193 | 6
TB 501 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 200 | 194 | 6
TB 501 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 202 | 197 | 5
TB 501 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 207 | 199 | 8
TB 501 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 208 | 202 | 6
TB 501 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 209 | 204 | 5
TB 501 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 211 | 207 | 4
TB 501 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 212 | 208 | 4
TB 501 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 214 | 209 | 5
TB 501 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 218 | 212 | 6
TB 501 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 219 | 214 | 5
TB 501 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 220 | 216 | 4
TB 501 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 221 | 218 | 3
TB 501 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 222 | 219 | 3
TB 501 | detail | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 | 224 | 219 | 5
TB 501 | detail | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 | 226 | 223 | 3
TB 501 | detail | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 | 226 | 226 | 0
TB 501 | detail | No | 2026-04-05 | 2026-04-11 | 2026-04-05 to 2026-04-11 | 227 | 226 | 1
TB 501 | detail | No | 2026-04-12 | 2026-04-18 | 2026-04-12 to 2026-04-18 | 229 | 226 | 3
TB 501 | detail | No | 2026-04-19 | 2026-04-25 | 2026-04-19 to 2026-04-25 | 230 | 227 | 3
TB 501 | detail | No | 2026-04-26 | 2026-05-02 | 2026-04-26 to 2026-05-02 | 231 | 228 | 3
TB 501 | detail | No | 2026-05-10 | 2026-05-16 | 2026-05-10 to 2026-05-16 | 231 | 230 | 1
TB 507 | detail | No | 2025-01-12 | 2025-01-18 | 2025-01-12 to 2025-01-18 | 1 | 0 | 1
TB 507 | detail | No | 2025-01-26 | 2025-02-01 | 2025-01-26 to 2025-02-01 | 2 | 0 | 2
TB 507 | detail | No | 2025-02-02 | 2025-02-08 | 2025-02-02 to 2025-02-08 | 5 | 0 | 5
TB 507 | detail | No | 2025-02-09 | 2025-02-15 | 2025-02-09 to 2025-02-15 | 9 | 0 | 9
TB 507 | detail | No | 2025-02-16 | 2025-02-22 | 2025-02-16 to 2025-02-22 | 15 | 0 | 15
TB 507 | detail | No | 2025-02-23 | 2025-03-01 | 2025-02-23 to 2025-03-01 | 22 | 0 | 22
TB 507 | detail | No | 2025-03-02 | 2025-03-08 | 2025-03-02 to 2025-03-08 | 27 | 0 | 27
TB 507 | detail | No | 2025-03-09 | 2025-03-15 | 2025-03-09 to 2025-03-15 | 32 | 0 | 32
TB 507 | detail | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 | 34 | 0 | 34
TB 507 | detail | No | 2025-03-30 | 2025-04-05 | 2025-03-30 to 2025-04-05 | 39 | 0 | 39
TB 507 | detail | No | 2025-04-06 | 2025-04-12 | 2025-04-06 to 2025-04-12 | 40 | 0 | 40
TB 507 | detail | No | 2025-04-13 | 2025-04-19 | 2025-04-13 to 2025-04-19 | 44 | 0 | 44
TB 507 | detail | No | 2025-04-20 | 2025-04-26 | 2025-04-20 to 2025-04-26 | 48 | 0 | 48
TB 507 | detail | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 | 51 | 0 | 51
TB 507 | detail | No | 2025-05-04 | 2025-05-10 | 2025-05-04 to 2025-05-10 | 52 | 1 | 51
TB 507 | detail | No | 2025-05-11 | 2025-05-17 | 2025-05-11 to 2025-05-17 | 53 | 1 | 52
TB 507 | detail | No | 2025-05-18 | 2025-05-24 | 2025-05-18 to 2025-05-24 | 56 | 1 | 55
TB 507 | detail | No | 2025-05-25 | 2025-05-31 | 2025-05-25 to 2025-05-31 | 60 | 1 | 59
TB 507 | detail | No | 2025-06-01 | 2025-06-07 | 2025-06-01 to 2025-06-07 | 64 | 1 | 63
TB 507 | detail | No | 2025-06-08 | 2025-06-14 | 2025-06-08 to 2025-06-14 | 68 | 1 | 67
TB 507 | detail | No | 2025-06-15 | 2025-06-21 | 2025-06-15 to 2025-06-21 | 75 | 1 | 74
TB 507 | detail | No | 2025-06-22 | 2025-06-28 | 2025-06-22 to 2025-06-28 | 81 | 2 | 79
TB 507 | detail | No | 2025-06-29 | 2025-07-05 | 2025-06-29 to 2025-07-05 | 87 | 5 | 82
TB 507 | detail | No | 2025-07-06 | 2025-07-12 | 2025-07-06 to 2025-07-12 | 96 | 6 | 90
TB 507 | detail | No | 2025-07-13 | 2025-07-19 | 2025-07-13 to 2025-07-19 | 109 | 8 | 101
TB 507 | detail | No | 2025-07-20 | 2025-07-26 | 2025-07-20 to 2025-07-26 | 119 | 10 | 109
TB 507 | detail | No | 2025-07-27 | 2025-08-02 | 2025-07-27 to 2025-08-02 | 137 | 13 | 124
TB 507 | detail | No | 2025-08-03 | 2025-08-09 | 2025-08-03 to 2025-08-09 | 149 | 16 | 133
TB 507 | detail | No | 2025-08-10 | 2025-08-16 | 2025-08-10 to 2025-08-16 | 156 | 18 | 138
TB 507 | detail | No | 2025-08-17 | 2025-08-23 | 2025-08-17 to 2025-08-23 | 168 | 20 | 148
TB 507 | detail | No | 2025-08-24 | 2025-08-30 | 2025-08-24 to 2025-08-30 | 179 | 23 | 156
TB 507 | detail | No | 2025-08-31 | 2025-09-06 | 2025-08-31 to 2025-09-06 | 190 | 27 | 163
TB 507 | detail | No | 2025-09-07 | 2025-09-13 | 2025-09-07 to 2025-09-13 | 194 | 32 | 162
TB 507 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 200 | 44 | 156
TB 507 | detail | No | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 | 203 | 56 | 147
TB 507 | detail | No | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 | 207 | 65 | 142
TB 507 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 208 | 75 | 133
TB 507 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 211 | 85 | 126
TB 507 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 212 | 95 | 117
TB 507 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 215 | 106 | 109
TB 507 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 219 | 115 | 104
TB 507 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 223 | 124 | 99
TB 507 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 230 | 130 | 100
TB 507 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 232 | 136 | 96
TB 507 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 237 | 141 | 96
TB 507 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 239 | 147 | 92
TB 507 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 242 | 152 | 90
TB 507 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 243 | 160 | 83
TB 507 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 247 | 163 | 84
TB 507 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 250 | 168 | 82
TB 507 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 253 | 173 | 80
TB 507 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 256 | 176 | 80
TB 507 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 262 | 177 | 85
TB 507 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 264 | 178 | 86
TB 507 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 267 | 181 | 86
TB 507 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 270 | 182 | 88
TB 507 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 274 | 184 | 90
TB 507 | detail | No | 2026-03-01 | 2026-03-07 | 2026-03-01 to 2026-03-07 | 275 | 185 | 90
TB 507 | detail | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 | 279 | 186 | 93
TB 507 | detail | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 | 283 | 188 | 95
TB 507 | detail | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 | 290 | 188 | 102
TB 507 | detail | No | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 | 293 | 189 | 104
TB 507 | detail | No | 2026-04-05 | 2026-04-11 | 2026-04-05 to 2026-04-11 | 299 | 190 | 109
TB 507 | detail | No | 2026-04-12 | 2026-04-18 | 2026-04-12 to 2026-04-18 | 305 | 192 | 113
TB 507 | detail | No | 2026-04-19 | 2026-04-25 | 2026-04-19 to 2026-04-25 | 309 | 196 | 113
TB 507 | detail | No | 2026-04-26 | 2026-05-02 | 2026-04-26 to 2026-05-02 | 313 | 200 | 113
TB 507 | detail | No | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 | 324 | 205 | 119
TB 507 | detail | No | 2026-05-10 | 2026-05-16 | 2026-05-10 to 2026-05-16 | 329 | 210 | 119
TB 507 | detail | No | 2026-05-17 | 2026-05-23 | 2026-05-17 to 2026-05-23 | 334 | 213 | 121
TB 605 | detail | No | 2025-08-10 | 2025-08-16 | 2025-08-10 to 2025-08-16 | 1 | 0 | 1
TB 605 | detail | No | 2025-08-31 | 2025-09-06 | 2025-08-31 to 2025-09-06 | 2 | 0 | 2
TB 605 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 3 | 0 | 3
TB 605 | detail | No | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 | 4 | 0 | 4
TB 605 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 5 | 0 | 5
TB 605 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 7 | 0 | 7
TB 605 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 9 | 0 | 9
TB 605 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 19 | 0 | 19
TB 605 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 24 | 0 | 24
TB 605 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 35 | 0 | 35
TB 605 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 44 | 1 | 43
TB 605 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 55 | 1 | 54
TB 605 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 69 | 2 | 67
TB 605 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 81 | 3 | 78
TB 605 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 93 | 3 | 90
TB 605 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 108 | 3 | 105
TB 605 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 118 | 4 | 114
TB 605 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 129 | 6 | 123
TB 605 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 138 | 7 | 131
TB 605 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 152 | 9 | 143
TB 605 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 160 | 10 | 150
TB 605 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 165 | 15 | 150
TB 605 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 176 | 26 | 150
TB 605 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 189 | 38 | 151
TB 605 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 202 | 55 | 147
TB 605 | detail | No | 2026-03-01 | 2026-03-07 | 2026-03-01 to 2026-03-07 | 206 | 61 | 145
TB 605 | detail | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 | 212 | 75 | 137
TB 605 | detail | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 | 218 | 84 | 134
TB 605 | detail | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 | 223 | 95 | 128
TB 605 | detail | No | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 | 230 | 109 | 121
TB 605 | detail | No | 2026-04-05 | 2026-04-11 | 2026-04-05 to 2026-04-11 | 235 | 119 | 116
TB 605 | detail | No | 2026-04-12 | 2026-04-18 | 2026-04-12 to 2026-04-18 | 240 | 133 | 107
TB 605 | detail | No | 2026-04-19 | 2026-04-25 | 2026-04-19 to 2026-04-25 | 245 | 145 | 100
TB 605 | detail | No | 2026-04-26 | 2026-05-02 | 2026-04-26 to 2026-05-02 | 257 | 158 | 99
TB 605 | detail | No | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 | 266 | 172 | 94
TB 605 | detail | No | 2026-05-10 | 2026-05-16 | 2026-05-10 to 2026-05-16 | 276 | 185 | 91
TB 605 | detail | No | 2026-05-17 | 2026-05-23 | 2026-05-17 to 2026-05-23 | 288 | 189 | 99
TB 608 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 2 | 0 | 2
TB 608 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 7 | 0 | 7
TB 608 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 12 | 0 | 12
TB 608 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 16 | 0 | 16
TB 608 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 24 | 0 | 24
TB 608 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 29 | 0 | 29
TB 608 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 36 | 0 | 36
TB 608 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 48 | 0 | 48
TB 608 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 58 | 0 | 58
TB 608 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 62 | 1 | 61
TB 608 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 69 | 1 | 68
TB 608 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 73 | 2 | 71
TB 608 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 86 | 3 | 83
TB 608 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 91 | 3 | 88
TB 608 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 99 | 4 | 95
TB 608 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 107 | 5 | 102
TB 608 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 116 | 7 | 109
TB 608 | detail | No | 2026-03-01 | 2026-03-07 | 2026-03-01 to 2026-03-07 | 117 | 9 | 108
TB 608 | detail | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 | 125 | 10 | 115
TB 608 | detail | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 | 127 | 11 | 116
TB 608 | detail | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 | 128 | 12 | 116
TB 608 | detail | No | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 | 131 | 12 | 119
TB 608 | detail | No | 2026-04-05 | 2026-04-11 | 2026-04-05 to 2026-04-11 | 131 | 14 | 117
TB 608 | detail | No | 2026-04-12 | 2026-04-18 | 2026-04-12 to 2026-04-18 | 132 | 16 | 116
TB 608 | detail | No | 2026-04-19 | 2026-04-25 | 2026-04-19 to 2026-04-25 | 133 | 19 | 114
TB 608 | detail | No | 2026-04-26 | 2026-05-02 | 2026-04-26 to 2026-05-02 | 133 | 21 | 112
TB 608 | detail | No | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 | 133 | 22 | 111

## Foundation Gap Coverage
Foundation Gap Coverage
Project | Foundation Source Used | Coverage Status | Coverage Reason | Snapshot Limited | First Month Available | Last Month Available | First Week Available | Last Week Available | Detail Rows | Detail Completions | Snapshot Rows | Erection First Month | Erection Last Month | Notes
TA 413 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2024-06 | 2026-03 | 2024-06-02 to 2024-06-08 | 2026-03-01 to 2026-03-07 | 316 | 316 | 1 | 2024-09 | 2026-02
TA 414 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2024-05 | 2026-05 | 2024-05-12 to 2024-05-18 | 2026-05-17 to 2026-05-23 | 327 | 327 | 1 | 2025-04 | 2026-05
TA 416 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2024-04 | 2026-03 | 2024-04-21 to 2024-04-27 | 2026-03-22 to 2026-03-28 | 700 | 606 | 1 | 2024-09 | 2026-03
TA 418 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2024-01 | 2026-04 | 2024-01-07 to 2024-01-13 | 2026-03-29 to 2026-04-04 | 281 | 249 | 1 | 2024-10 | 2026-04
TA 419 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2024-05 | 2026-05 | 2024-05-19 to 2024-05-25 | 2026-05-17 to 2026-05-23 | 330 | 269 | 1 | 2024-11 | 2026-05
TA 421 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2024-01 | 2026-01 | 2023-12-31 to 2024-01-06 | 2026-01-11 to 2026-01-17 | 996 | 915 | 1 | 2024-07 | 2026-01
TA 505 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2015-11 | 2026-05 | 2015-11-22 to 2015-11-28 | 2026-05-17 to 2026-05-23 | 374 | 373 | 1 | 2025-01 | 2026-05
TA 509 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2025-01 | 2026-05 | 2024-12-29 to 2025-01-04 | 2026-05-17 to 2026-05-23 | 272 | 264 | 1 | 2025-09 | 2026-05
TA 510 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2025-02 | 2026-05 | 2025-02-09 to 2025-02-15 | 2026-05-17 to 2026-05-23 | 87 | 85 | 1 | 2026-01 | 2026-05
TA 512 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2025-02 | 2026-05 | 2025-02-23 to 2025-03-01 | 2026-05-10 to 2026-05-16 | 308 | 302 | 0 | 2025-08 | 2026-05
TA 513 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2025-03 | 2026-05 | 2025-03-16 to 2025-03-22 | 2026-05-17 to 2026-05-23 | 85 | 84 | 1 | 2025-09 | 2026-05
TA 515 | missing | MAPPING_CONFIRMATION_REQUIRED | Detail rows are present but very few parseable completion dates were found. Foundation column mapping likely needs confirmation. | No |  |  |  |  | 14 | 0 | 0 | 2026-03 | 2026-03
TA 601 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2025-03 | 2026-05 | 2025-03-23 to 2025-03-29 | 2026-05-17 to 2026-05-23 | 309 | 191 | 1 | 2025-03 | 2026-05
TA 602 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2025-09 | 2026-05 | 2025-09-14 to 2025-09-20 | 2026-05-17 to 2026-05-23 | 143 | 143 | 1 | 2026-02 | 2026-05
TB 408 | missing | BLOCKED_NO_SOURCE | Configured foundation sheet unavailable and no usable foundation/status fallback in raw DPR. | No |  |  |  |  | 0 | 0 | 0 | 2024-02 | 2026-05
TB 501 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2024-08 | 2026-05 | 2024-08-11 to 2024-08-17 | 2026-05-10 to 2026-05-16 | 240 | 231 | 1 | 2024-12 | 2026-05
TB 507 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2025-01 | 2026-05 | 2025-01-12 to 2025-01-18 | 2026-05-17 to 2026-05-23 | 345 | 334 | 1 | 2025-05 | 2026-05
TB 605 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2025-08 | 2026-05 | 2025-08-10 to 2025-08-16 | 2026-05-17 to 2026-05-23 | 317 | 288 | 1 | 2025-11 | 2026-05
TB 608 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2025-10 | 2026-05 | 2025-10-12 to 2025-10-18 | 2026-05-03 to 2026-05-09 | 186 | 133 | 1 | 2026-01 | 2026-05

## Foundation Delay Phases
Foundation Delay Phases
Project | Phase | Foundation Bucket Start % | Foundation Bucket End % | Foundation Count | Matched Count | Match % | Median Delay Days | Average Delay Days | P90 Delay Days | Negative Excluded | Unmatched | Source Type | Parser Modes | Coverage Status
TA 413 | Phase 1 | 0 | 20 | 63 | 63 | 100 | 341 | 300.2063 | 491.6 | 0 | 0 | detail |  | OK_DETAIL
TA 413 | Phase 2 | 20 | 40 | 63 | 57 | 90.48 | 299 | 243.9474 | 402.2 | 0 | 6 | detail |  | OK_DETAIL
TA 413 | Phase 3 | 40 | 60 | 63 | 61 | 96.83 | 99 | 157.0984 | 306 | 0 | 2 | detail |  | OK_DETAIL
TA 413 | Phase 4 | 60 | 80 | 63 | 63 | 100 | 213.5 | 203.1613 | 287.8 | 1 | 0 | detail |  | OK_DETAIL
TA 413 | Phase 5 | 80 | 100 | 62 | 60 | 96.77 | 163 | 163.3559 | 220.8 | 1 | 2 | detail |  | OK_DETAIL
TA 414 | Phase 1 | 0 | 20 | 66 | 58 | 87.88 | 342 | 351.2456 | 452.8 | 1 | 8 | detail |  | OK_DETAIL
TA 414 | Phase 2 | 20 | 40 | 65 | 57 | 87.69 | 162 | 187.9649 | 347.2 | 0 | 8 | detail |  | OK_DETAIL
TA 414 | Phase 3 | 40 | 60 | 66 | 51 | 77.27 | 59 | 64.8235 | 106 | 0 | 15 | detail |  | OK_DETAIL
TA 414 | Phase 4 | 60 | 80 | 65 | 39 | 60 | 56 | 59.359 | 86 | 0 | 26 | detail |  | OK_DETAIL
TA 414 | Phase 5 | 80 | 100 | 65 | 20 | 30.77 | 30 | 32.7368 | 51.4 | 1 | 45 | detail |  | OK_DETAIL
TA 416 | Phase 1 | 0 | 20 | 61 | 61 | 100 | 172 | 185.8525 | 288 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | Phase 2 | 20 | 40 | 61 | 61 | 100 | 151 | 154.5738 | 243 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | Phase 3 | 40 | 60 | 60 | 60 | 100 | 118 | 124.1 | 191.4 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | Phase 4 | 60 | 80 | 61 | 61 | 100 | 151 | 168.7541 | 284 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | Phase 5 | 80 | 100 | 60 | 60 | 100 | 161.5 | 166.5167 | 259.2 | 0 | 0 | detail |  | OK_DETAIL
TA 418 | Phase 1 | 0 | 20 | 26 | 25 | 96.15 | 159 | 162.68 | 259.6 | 0 | 1 | detail |  | OK_DETAIL
TA 418 | Phase 2 | 20 | 40 | 26 | 25 | 96.15 | 99 | 133.32 | 225 | 0 | 1 | detail |  | OK_DETAIL
TA 418 | Phase 3 | 40 | 60 | 26 | 26 | 100 | 145 | 155.2308 | 244 | 0 | 0 | detail |  | OK_DETAIL
TA 418 | Phase 4 | 60 | 80 | 26 | 25 | 96.15 | 92 | 98.88 | 156.8 | 0 | 1 | detail |  | OK_DETAIL
TA 418 | Phase 5 | 80 | 100 | 25 | 24 | 96 | 80 | 93.625 | 176.7 | 0 | 1 | detail |  | OK_DETAIL
TA 419 | Phase 1 | 0 | 20 | 54 | 54 | 100 | 206 | 219.1887 | 347.6 | 1 | 0 | detail |  | OK_DETAIL
TA 419 | Phase 2 | 20 | 40 | 54 | 52 | 96.3 | 175 | 195.3077 | 321.4 | 0 | 2 | detail |  | OK_DETAIL
TA 419 | Phase 3 | 40 | 60 | 53 | 47 | 88.68 | 220 | 200 | 283.4 | 0 | 6 | detail |  | OK_DETAIL
TA 419 | Phase 4 | 60 | 80 | 54 | 39 | 72.22 | 36 | 53.9211 | 133.9 | 1 | 15 | detail |  | OK_DETAIL
TA 419 | Phase 5 | 80 | 100 | 53 | 9 | 16.98 | 87 | 74.3333 | 104.6 | 0 | 44 | detail |  | OK_DETAIL
TA 421 | Phase 1 | 0 | 20 | 61 | 61 | 100 | 110 | 131.3443 | 244 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | Phase 2 | 20 | 40 | 61 | 61 | 100 | 117 | 142.3115 | 301 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | Phase 3 | 40 | 60 | 60 | 60 | 100 | 107 | 132.6 | 286.1 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | Phase 4 | 60 | 80 | 61 | 60 | 98.36 | 129.5 | 128.1 | 219.1 | 0 | 1 | detail |  | OK_DETAIL
TA 421 | Phase 5 | 80 | 100 | 60 | 57 | 95 | 159 | 152.7018 | 214.2 | 0 | 3 | detail |  | OK_DETAIL
TA 505 | Phase 1 | 0 | 20 | 75 | 74 | 98.67 | 142 | 179.5 | 309.1 | 0 | 1 | detail |  | OK_DETAIL
TA 505 | Phase 2 | 20 | 40 | 75 | 75 | 100 | 218 | 221.9067 | 362.8 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | Phase 3 | 40 | 60 | 74 | 74 | 100 | 217 | 222.8514 | 349.7 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | Phase 4 | 60 | 80 | 75 | 75 | 100 | 134 | 151.7467 | 289.8 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | Phase 5 | 80 | 100 | 74 | 55 | 74.32 | 17 | 21.463 | 45.7 | 1 | 19 | detail |  | OK_DETAIL
TA 509 | Phase 1 | 0 | 20 | 53 | 51 | 96.23 | 265 | 272.2941 | 356 | 0 | 2 | detail |  | OK_DETAIL
TA 509 | Phase 2 | 20 | 40 | 53 | 40 | 75.47 | 350 | 324.825 | 393.5 | 0 | 13 | detail |  | OK_DETAIL
TA 509 | Phase 3 | 40 | 60 | 53 | 42 | 79.25 | 270 | 270.4524 | 344.8 | 0 | 11 | detail |  | OK_DETAIL
TA 509 | Phase 4 | 60 | 80 | 53 | 42 | 79.25 | 152.5 | 144.0476 | 208.6 | 0 | 11 | detail |  | OK_DETAIL
TA 509 | Phase 5 | 80 | 100 | 52 | 24 | 46.15 | 63.5 | 66.5 | 120.6 | 0 | 28 | detail |  | OK_DETAIL
TA 510 | Phase 1 | 0 | 20 | 17 | 1 | 5.88 | 365 | 365 | 365 | 0 | 16 | detail |  | OK_DETAIL
TA 510 | Phase 2 | 20 | 40 | 17 | 13 | 76.47 | 169 | 198.4615 | 341.2 | 0 | 4 | detail |  | OK_DETAIL
TA 510 | Phase 3 | 40 | 60 | 17 | 15 | 88.24 | 90 | 91.4667 | 121.2 | 0 | 2 | detail |  | OK_DETAIL
TA 510 | Phase 4 | 60 | 80 | 17 | 5 | 29.41 | 57 | 60.2 | 90.8 | 0 | 12 | detail |  | OK_DETAIL
TA 510 | Phase 5 | 80 | 100 | 17 | 0 | 0 |  |  |  | 0 | 17 | detail |  | OK_DETAIL
TA 512 | Phase 1 | 0 | 20 | 60 | 59 | 98.33 | 224 | 220.3559 | 305.2 | 0 | 1 | detail |  | OK_DETAIL
TA 512 | Phase 2 | 20 | 40 | 59 | 53 | 89.83 | 211 | 197.6792 | 250.6 | 0 | 6 | detail |  | OK_DETAIL
TA 512 | Phase 3 | 40 | 60 | 60 | 43 | 71.67 | 154 | 151.6047 | 209.4 | 0 | 17 | detail |  | OK_DETAIL
TA 512 | Phase 4 | 60 | 80 | 59 | 36 | 61.02 | 115 | 108.8333 | 166.5 | 0 | 23 | detail |  | OK_DETAIL
TA 512 | Phase 5 | 80 | 100 | 59 | 22 | 37.29 | 73.5 | 73 | 105.8 | 0 | 37 | detail |  | OK_DETAIL
TA 513 | Phase 1 | 0 | 20 | 17 | 5 | 29.41 | 185 | 189.8 | 204.4 | 0 | 12 | detail |  | OK_DETAIL
TA 513 | Phase 2 | 20 | 40 | 17 | 7 | 41.18 | 183 | 180 | 203.2 | 0 | 10 | detail |  | OK_DETAIL
TA 513 | Phase 3 | 40 | 60 | 16 | 3 | 18.75 | 205 | 205.6667 | 249 | 0 | 13 | detail |  | OK_DETAIL
TA 513 | Phase 4 | 60 | 80 | 17 | 8 | 47.06 | 110 | 110.75 | 195.3 | 0 | 9 | detail |  | OK_DETAIL
TA 513 | Phase 5 | 80 | 100 | 16 | 5 | 31.25 | 83.5 | 77.5 | 117.8 | 1 | 11 | detail |  | OK_DETAIL
TA 601 | Phase 1 | 0 | 20 | 24 | 17 | 70.83 | 86 | 79 | 128.2 | 0 | 7 | detail |  | OK_DETAIL
TA 601 | Phase 2 | 20 | 40 | 24 | 16 | 66.67 | 32 | 57.1875 | 70.5 | 0 | 8 | detail |  | OK_DETAIL
TA 601 | Phase 3 | 40 | 60 | 24 | 20 | 83.33 | 16 | 17.6842 | 23.6 | 1 | 4 | detail |  | OK_DETAIL
TA 601 | Phase 4 | 60 | 80 | 24 | 16 | 66.67 | 14 | 15.875 | 22.5 | 0 | 8 | detail |  | OK_DETAIL
TA 601 | Phase 5 | 80 | 100 | 24 | 1 | 4.17 | 29 | 29 | 29 | 0 | 23 | detail |  | OK_DETAIL
TA 602 | Phase 1 | 0 | 20 | 29 | 18 | 62.07 | 156 | 149 | 186.8 | 1 | 11 | detail |  | OK_DETAIL
TA 602 | Phase 2 | 20 | 40 | 29 | 12 | 41.38 | 133 | 136 | 150.8 | 0 | 17 | detail |  | OK_DETAIL
TA 602 | Phase 3 | 40 | 60 | 28 | 7 | 25 | 116 | 113 | 132.6 | 0 | 21 | detail |  | OK_DETAIL
TA 602 | Phase 4 | 60 | 80 | 29 | 3 | 10.34 | 39 | 48 | 77.4 | 0 | 26 | detail |  | OK_DETAIL
TA 602 | Phase 5 | 80 | 100 | 28 | 0 | 0 |  |  |  | 0 | 28 | detail |  | OK_DETAIL
TB 501 | Phase 1 | 0 | 20 | 47 | 47 | 100 | 118 | 124.8298 | 183 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | Phase 2 | 20 | 40 | 46 | 46 | 100 | 63.5 | 72 | 111 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | Phase 3 | 40 | 60 | 46 | 46 | 100 | 61.5 | 72.1739 | 129.5 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | Phase 4 | 60 | 80 | 46 | 46 | 100 | 40 | 47.3913 | 95.5 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | Phase 5 | 80 | 100 | 46 | 45 | 97.83 | 14 | 17.4884 | 37.8 | 2 | 1 | detail |  | OK_DETAIL
TB 507 | Phase 1 | 0 | 20 | 67 | 43 | 64.18 | 164 | 180.0465 | 268.8 | 0 | 24 | detail |  | OK_DETAIL
TB 507 | Phase 2 | 20 | 40 | 66 | 59 | 89.39 | 77 | 90.7627 | 144.6 | 0 | 7 | detail |  | OK_DETAIL
TB 507 | Phase 3 | 40 | 60 | 66 | 51 | 77.27 | 62 | 73.8824 | 132 | 0 | 15 | detail |  | OK_DETAIL
TB 507 | Phase 4 | 60 | 80 | 66 | 47 | 71.21 | 46 | 57.6522 | 97 | 1 | 19 | detail |  | OK_DETAIL
TB 507 | Phase 5 | 80 | 100 | 66 | 13 | 19.7 | 20 | 24.9231 | 40.2 | 0 | 53 | detail |  | OK_DETAIL
TB 605 | Phase 1 | 0 | 20 | 58 | 48 | 82.76 | 92.5 | 102.0833 | 165.6 | 0 | 10 | detail |  | OK_DETAIL
TB 605 | Phase 2 | 20 | 40 | 58 | 44 | 75.86 | 91.5 | 94.3409 | 139.2 | 0 | 14 | detail |  | OK_DETAIL
TB 605 | Phase 3 | 40 | 60 | 57 | 47 | 82.46 | 63 | 64.4681 | 96.2 | 0 | 10 | detail |  | OK_DETAIL
TB 605 | Phase 4 | 60 | 80 | 58 | 34 | 58.62 | 31.5 | 36.7647 | 64.4 | 0 | 24 | detail |  | OK_DETAIL
TB 605 | Phase 5 | 80 | 100 | 57 | 6 | 10.53 | 14.5 | 13.3333 | 18 | 0 | 51 | detail |  | OK_DETAIL
TB 608 | Phase 1 | 0 | 20 | 27 | 8 | 29.63 | 97 | 96.625 | 145.4 | 0 | 19 | detail |  | OK_DETAIL
TB 608 | Phase 2 | 20 | 40 | 26 | 6 | 23.08 | 55.5 | 55 | 69.5 | 0 | 20 | detail |  | OK_DETAIL
TB 608 | Phase 3 | 40 | 60 | 27 | 5 | 18.52 | 76 | 77.6 | 97.4 | 0 | 22 | detail |  | OK_DETAIL
TB 608 | Phase 4 | 60 | 80 | 26 | 1 | 3.85 | 45 | 45 | 45 | 0 | 25 | detail |  | OK_DETAIL
TB 608 | Phase 5 | 80 | 100 | 26 | 2 | 7.69 | 47.5 | 47.5 | 47.9 | 0 | 24 | detail |  | OK_DETAIL

## Foundation Delay Monthly
Foundation Delay Monthly
Project | Month | Foundation Count | Matched Count | Match % | Median Delay Days | Average Delay Days | P90 Delay Days | Negative Excluded | Unmatched | Source Type | Parser Modes | Coverage Status
TA 413 | 2024-06 | 14 | 14 | 100 | 275 | 339.2857 | 493.4 | 0 | 0 | detail |  | OK_DETAIL
TA 413 | 2024-07 | 20 | 20 | 100 | 380 | 316.2 | 495.3 | 0 | 0 | detail |  | OK_DETAIL
TA 413 | 2024-08 | 23 | 23 | 100 | 341 | 259.2174 | 418.2 | 0 | 0 | detail |  | OK_DETAIL
TA 413 | 2024-09 | 40 | 39 | 97.5 | 335 | 268.0256 | 399 | 0 | 1 | detail |  | OK_DETAIL
TA 413 | 2024-10 | 35 | 29 | 82.86 | 131 | 200.4483 | 356.6 | 0 | 6 | detail |  | OK_DETAIL
TA 413 | 2024-11 | 24 | 24 | 100 | 90.5 | 165.7083 | 306 | 0 | 0 | detail |  | OK_DETAIL
TA 413 | 2024-12 | 32 | 31 | 96.88 | 99 | 153.871 | 306 | 0 | 1 | detail |  | OK_DETAIL
TA 413 | 2025-01 | 34 | 34 | 100 | 218 | 201.697 | 287.6 | 1 | 0 | detail |  | OK_DETAIL
TA 413 | 2025-02 | 31 | 31 | 100 | 215 | 211.3226 | 294 | 0 | 0 | detail |  | OK_DETAIL
TA 413 | 2025-03 | 19 | 19 | 100 | 182 | 179.6842 | 225 | 0 | 0 | detail |  | OK_DETAIL
TA 413 | 2025-04 | 23 | 23 | 100 | 154 | 160.2609 | 209.6 | 0 | 0 | detail |  | OK_DETAIL
TA 413 | 2025-05 | 10 | 10 | 100 | 160.5 | 165.2 | 179.3 | 0 | 0 | detail |  | OK_DETAIL
TA 413 | 2025-06 | 4 | 4 | 100 | 105 | 102.25 | 146.9 | 0 | 0 | detail |  | OK_DETAIL
TA 413 | 2025-07 | 2 | 2 | 100 | 109 | 109 | 158.6 | 0 | 0 | detail |  | OK_DETAIL
TA 413 | 2026-01 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TA 413 | 2026-02 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TA 413 | 2026-03 | 1 | 1 | 100 |  |  |  | 1 | 0 | detail |  | OK_DETAIL
TA 414 | 2024-05 | 3 | 3 | 100 | 609 | 594 | 685 | 0 | 0 | detail |  | OK_DETAIL
TA 414 | 2024-08 | 1 | 1 | 100 | 565 | 565 | 565 | 0 | 0 | detail |  | OK_DETAIL
TA 414 | 2024-09 | 1 | 1 | 100 | 253 | 253 | 253 | 0 | 0 | detail |  | OK_DETAIL
TA 414 | 2024-11 | 5 | 5 | 100 | 295 | 312.25 | 429.7 | 1 | 0 | detail |  | OK_DETAIL
TA 414 | 2024-12 | 16 | 13 | 81.25 | 381 | 336.6154 | 420.2 | 0 | 3 | detail |  | OK_DETAIL
TA 414 | 2025-01 | 19 | 16 | 84.21 | 354 | 360.375 | 451 | 0 | 3 | detail |  | OK_DETAIL
TA 414 | 2025-02 | 10 | 9 | 90 | 326 | 334.6667 | 371.4 | 0 | 1 | detail |  | OK_DETAIL
TA 414 | 2025-03 | 17 | 16 | 94.12 | 325.5 | 328.8125 | 409 | 0 | 1 | detail |  | OK_DETAIL
TA 414 | 2025-04 | 11 | 11 | 100 | 295 | 296.6364 | 349 | 0 | 0 | detail |  | OK_DETAIL
TA 414 | 2025-05 | 7 | 5 | 71.43 | 245 | 243 | 278.6 | 0 | 2 | detail |  | OK_DETAIL
TA 414 | 2025-08 | 5 | 5 | 100 | 152 | 167 | 213.8 | 0 | 0 | detail |  | OK_DETAIL
TA 414 | 2025-09 | 1 | 1 | 100 | 175 | 175 | 175 | 0 | 0 | detail |  | OK_DETAIL
TA 414 | 2025-10 | 13 | 10 | 76.92 | 123 | 134.2 | 196 | 0 | 3 | detail |  | OK_DETAIL
TA 414 | 2025-11 | 35 | 31 | 88.57 | 83 | 82.0323 | 132 | 0 | 4 | detail |  | OK_DETAIL
TA 414 | 2025-12 | 69 | 50 | 72.46 | 57 | 60.12 | 98.2 | 0 | 19 | detail |  | OK_DETAIL
TA 414 | 2026-01 | 42 | 25 | 59.52 | 56 | 58.6 | 80 | 0 | 17 | detail |  | OK_DETAIL
TA 414 | 2026-02 | 26 | 15 | 57.69 | 38 | 47.3571 | 82.4 | 1 | 11 | detail |  | OK_DETAIL
TA 414 | 2026-03 | 20 | 8 | 40 | 28.5 | 25.875 | 35 | 0 | 12 | detail |  | OK_DETAIL
TA 414 | 2026-04 | 18 | 0 | 0 |  |  |  | 0 | 18 | detail |  | OK_DETAIL
TA 414 | 2026-05 | 8 | 0 | 0 |  |  |  | 0 | 8 | detail |  | OK_DETAIL
TA 416 | 2024-04 | 1 | 1 | 100 | 130 | 130 | 130 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2024-05 | 8 | 8 | 100 | 204 | 185.625 | 221.9 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2024-06 | 14 | 14 | 100 | 177.5 | 213 | 329.6 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2024-07 | 13 | 13 | 100 | 120 | 151 | 269.2 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2024-08 | 19 | 19 | 100 | 209 | 185 | 276.6 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2024-09 | 26 | 26 | 100 | 215 | 191.8462 | 268.5 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2024-10 | 51 | 51 | 100 | 127 | 134.7647 | 209 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2024-11 | 50 | 50 | 100 | 119 | 125.52 | 198.5 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2024-12 | 34 | 34 | 100 | 138 | 159.7941 | 281.7 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2025-01 | 26 | 26 | 100 | 159.5 | 184.2692 | 300 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2025-02 | 26 | 26 | 100 | 132 | 160.8077 | 286 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2025-03 | 18 | 18 | 100 | 214.5 | 196.5 | 258.2 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2025-04 | 10 | 10 | 100 | 134 | 144.9 | 240.7 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2025-05 | 6 | 6 | 100 | 146 | 149 | 222 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2025-12 | 1 | 1 | 100 | 0 | 0 | 0 | 0 | 0 | detail |  | OK_DETAIL
TA 418 | 2024-01 | 2 | 2 | 100 | 0 | 0 | 0 | 0 | 0 | detail |  | OK_DETAIL
TA 418 | 2024-06 | 3 | 3 | 100 | 186 | 187.6667 | 198 | 0 | 0 | detail |  | OK_DETAIL
TA 418 | 2024-07 | 12 | 12 | 100 | 191 | 200.9167 | 310 | 0 | 0 | detail |  | OK_DETAIL
TA 418 | 2024-08 | 5 | 4 | 80 | 148.5 | 154 | 178.6 | 0 | 1 | detail |  | OK_DETAIL
TA 418 | 2024-09 | 10 | 10 | 100 | 137.5 | 171.9 | 281.9 | 0 | 0 | detail |  | OK_DETAIL
TA 418 | 2024-10 | 4 | 4 | 100 | 159 | 158.5 | 208.8 | 0 | 0 | detail |  | OK_DETAIL
TA 418 | 2024-11 | 7 | 7 | 100 | 94 | 101.7143 | 191.4 | 0 | 0 | detail |  | OK_DETAIL
TA 418 | 2024-12 | 5 | 4 | 80 | 98.5 | 104 | 125.6 | 0 | 1 | detail |  | OK_DETAIL
TA 418 | 2025-01 | 9 | 9 | 100 | 114 | 125.4444 | 242.8 | 0 | 0 | detail |  | OK_DETAIL
TA 418 | 2025-02 | 6 | 6 | 100 | 125 | 114.6667 | 153 | 0 | 0 | detail |  | OK_DETAIL
TA 418 | 2025-03 | 8 | 8 | 100 | 181 | 176.375 | 271.6 | 0 | 0 | detail |  | OK_DETAIL
TA 418 | 2025-04 | 7 | 7 | 100 | 149 | 162.4286 | 213.2 | 0 | 0 | detail |  | OK_DETAIL
TA 418 | 2025-05 | 7 | 7 | 100 | 97 | 104.4286 | 170.8 | 0 | 0 | detail |  | OK_DETAIL
TA 418 | 2025-06 | 22 | 21 | 95.45 | 98 | 105.4286 | 159 | 0 | 1 | detail |  | OK_DETAIL
TA 418 | 2025-07 | 6 | 6 | 100 | 170.5 | 161.3333 | 201 | 0 | 0 | detail |  | OK_DETAIL
TA 418 | 2025-08 | 3 | 3 | 100 | 136 | 104.3333 | 139.2 | 0 | 0 | detail |  | OK_DETAIL
TA 418 | 2025-11 | 5 | 5 | 100 | 77 | 68.2 | 84.2 | 0 | 0 | detail |  | OK_DETAIL
TA 418 | 2025-12 | 6 | 5 | 83.33 | 21 | 21.2 | 45.2 | 0 | 1 | detail |  | OK_DETAIL
TA 418 | 2026-01 | 1 | 1 | 100 | 33 | 33 | 33 | 0 | 0 | detail |  | OK_DETAIL
TA 418 | 2026-02 | 1 | 1 | 100 | 13 | 13 | 13 | 0 | 0 | detail |  | OK_DETAIL
TA 419 | 2024-05 | 5 | 5 | 100 | 242 | 243.2 | 250.8 | 0 | 0 | detail |  | OK_DETAIL
TA 419 | 2024-06 | 8 | 8 | 100 | 166.5 | 195.625 | 287.2 | 0 | 0 | detail |  | OK_DETAIL
TA 419 | 2024-07 | 20 | 20 | 100 | 239 | 245.5263 | 396 | 1 | 0 | detail |  | OK_DETAIL
TA 419 | 2024-08 | 7 | 7 | 100 | 206 | 209.2857 | 275.8 | 0 | 0 | detail |  | OK_DETAIL
TA 419 | 2024-09 | 18 | 18 | 100 | 136.5 | 176.2778 | 306 | 0 | 0 | detail |  | OK_DETAIL
TA 419 | 2024-10 | 18 | 18 | 100 | 175 | 210.0556 | 357.8 | 0 | 0 | detail |  | OK_DETAIL
TA 419 | 2024-11 | 9 | 9 | 100 | 132 | 190.1111 | 338.4 | 0 | 0 | detail |  | OK_DETAIL
TA 419 | 2024-12 | 13 | 12 | 92.31 | 135 | 164.1667 | 244.7 | 0 | 1 | detail |  | OK_DETAIL
TA 419 | 2025-01 | 9 | 8 | 88.89 | 255.5 | 239.875 | 312.9 | 0 | 1 | detail |  | OK_DETAIL
TA 419 | 2025-02 | 6 | 6 | 100 | 292.5 | 289 | 303.5 | 0 | 0 | detail |  | OK_DETAIL
TA 419 | 2025-03 | 8 | 7 | 87.5 | 269 | 242.5714 | 275.4 | 0 | 1 | detail |  | OK_DETAIL
TA 419 | 2025-04 | 15 | 14 | 93.33 | 227.5 | 218.5714 | 243.2 | 0 | 1 | detail |  | OK_DETAIL
TA 419 | 2025-05 | 9 | 8 | 88.89 | 186 | 210.875 | 320.2 | 0 | 1 | detail |  | OK_DETAIL
TA 419 | 2025-06 | 8 | 7 | 87.5 | 134 | 132 | 222.2 | 0 | 1 | detail |  | OK_DETAIL
TA 419 | 2025-07 | 3 | 2 | 66.67 | 152 | 152 | 156.8 | 0 | 1 | detail |  | OK_DETAIL
TA 419 | 2025-08 | 2 | 1 | 50 | 101 | 101 | 101 | 0 | 1 | detail |  | OK_DETAIL
TA 419 | 2025-09 | 7 | 7 | 100 | 62 | 79.8571 | 130.4 | 0 | 0 | detail |  | OK_DETAIL
TA 419 | 2025-10 | 5 | 5 | 100 | 47 | 55.2 | 85 | 0 | 0 | detail |  | OK_DETAIL
TA 419 | 2025-11 | 20 | 13 | 65 | 37 | 54.75 | 129.9 | 1 | 7 | detail |  | OK_DETAIL
TA 419 | 2025-12 | 26 | 17 | 65.38 | 26 | 44.5294 | 120.4 | 0 | 9 | detail |  | OK_DETAIL
TA 419 | 2026-01 | 12 | 5 | 41.67 | 99 | 98.4 | 109.8 | 0 | 7 | detail |  | OK_DETAIL
TA 419 | 2026-02 | 4 | 2 | 50 | 56 | 56 | 72 | 0 | 2 | detail |  | OK_DETAIL
TA 419 | 2026-03 | 6 | 1 | 16.67 | 28 | 28 | 28 | 0 | 5 | detail |  | OK_DETAIL
TA 419 | 2026-04 | 17 | 1 | 5.88 | 37 | 37 | 37 | 0 | 16 | detail |  | OK_DETAIL
TA 419 | 2026-05 | 13 | 0 | 0 |  |  |  | 0 | 13 | detail |  | OK_DETAIL
TA 421 | 2024-01 | 1 | 1 | 100 | 368 | 368 | 368 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2024-02 | 1 | 1 | 100 | 441 | 441 | 441 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2024-03 | 2 | 2 | 100 | 530.5 | 530.5 | 541.3 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2024-05 | 7 | 7 | 100 | 127 | 140.8571 | 180.8 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2024-06 | 18 | 18 | 100 | 116.5 | 115 | 200 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2024-07 | 22 | 22 | 100 | 91 | 93.7727 | 128 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2024-08 | 16 | 16 | 100 | 104.5 | 116.3125 | 201 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2024-09 | 10 | 10 | 100 | 133.5 | 156 | 281.4 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2024-10 | 12 | 12 | 100 | 161 | 187.4167 | 361.9 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2024-11 | 19 | 19 | 100 | 109 | 138.0526 | 265.8 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2024-12 | 36 | 36 | 100 | 97.5 | 123.5278 | 269 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2025-01 | 39 | 39 | 100 | 104 | 127.9487 | 273 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2025-02 | 28 | 28 | 100 | 155.5 | 141.1429 | 202.7 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2025-03 | 12 | 12 | 100 | 106.5 | 101 | 157.5 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2025-04 | 29 | 27 | 93.1 | 142 | 143.7778 | 230.2 | 0 | 2 | detail |  | OK_DETAIL
TA 421 | 2025-05 | 22 | 22 | 100 | 175 | 169.0909 | 230.4 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2025-06 | 17 | 17 | 100 | 159 | 141.8235 | 189.4 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2025-07 | 9 | 8 | 88.89 | 136.5 | 133 | 165.5 | 0 | 1 | detail |  | OK_DETAIL
TA 421 | 2025-08 | 1 | 1 | 100 | 51 | 51 | 51 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2025-11 | 1 | 1 | 100 | 28 | 28 | 28 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2025-12 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TA 505 | 2015-11 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TA 505 | 2024-03 | 1 | 1 | 100 | 637 | 637 | 637 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2024-04 | 2 | 2 | 100 | 574.5 | 574.5 | 626.9 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2024-10 | 9 | 9 | 100 | 123 | 144.3333 | 192.4 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2024-11 | 26 | 26 | 100 | 129 | 135.1154 | 175.5 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2024-12 | 36 | 36 | 100 | 151.5 | 185.6944 | 308.5 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2025-01 | 30 | 30 | 100 | 231 | 226.3333 | 362.1 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2025-02 | 32 | 32 | 100 | 211 | 215.25 | 367.3 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2025-03 | 21 | 21 | 100 | 251 | 230.1429 | 359 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2025-04 | 48 | 48 | 100 | 224 | 233.5625 | 352 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2025-05 | 47 | 47 | 100 | 196 | 195.0638 | 309 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2025-06 | 15 | 15 | 100 | 200 | 216.8 | 293.8 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2025-07 | 2 | 2 | 100 | 75 | 75 | 87.8 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2025-08 | 1 | 1 | 100 | 218 | 218 | 218 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2025-09 | 10 | 10 | 100 | 87 | 80.1 | 101.3 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2025-10 | 12 | 12 | 100 | 44.5 | 74.75 | 173.3 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2025-11 | 16 | 15 | 93.75 | 39 | 41.1333 | 60 | 0 | 1 | detail |  | OK_DETAIL
TA 505 | 2025-12 | 18 | 16 | 88.89 | 19 | 21.6875 | 33 | 0 | 2 | detail |  | OK_DETAIL
TA 505 | 2026-01 | 17 | 15 | 88.24 | 12 | 18.6667 | 26 | 0 | 2 | detail |  | OK_DETAIL
TA 505 | 2026-02 | 10 | 8 | 80 | 7.5 | 9.875 | 18.6 | 0 | 2 | detail |  | OK_DETAIL
TA 505 | 2026-03 | 8 | 4 | 50 | 29.5 | 30 | 54.7 | 0 | 4 | detail |  | OK_DETAIL
TA 505 | 2026-04 | 8 | 2 | 25 | 11.5 | 11.5 | 17.5 | 0 | 6 | detail |  | OK_DETAIL
TA 505 | 2026-05 | 3 | 1 | 33.33 |  |  |  | 1 | 2 | detail |  | OK_DETAIL
TA 509 | 2025-01 | 6 | 6 | 100 | 318.5 | 309.6667 | 376 | 0 | 0 | detail |  | OK_DETAIL
TA 509 | 2025-02 | 14 | 14 | 100 | 266 | 265.7143 | 318.2 | 0 | 0 | detail |  | OK_DETAIL
TA 509 | 2025-03 | 35 | 33 | 94.29 | 257 | 271.0909 | 374.6 | 0 | 2 | detail |  | OK_DETAIL
TA 509 | 2025-04 | 49 | 36 | 73.47 | 353.5 | 326.4444 | 395.5 | 0 | 13 | detail |  | OK_DETAIL
TA 509 | 2025-05 | 40 | 36 | 90 | 277.5 | 272.7222 | 347 | 0 | 4 | detail |  | OK_DETAIL
TA 509 | 2025-06 | 15 | 8 | 53.33 | 269 | 268.125 | 314.3 | 0 | 7 | detail |  | OK_DETAIL
TA 509 | 2025-07 | 6 | 4 | 66.67 | 214 | 205.5 | 236.2 | 0 | 2 | detail |  | OK_DETAIL
TA 509 | 2025-08 | 6 | 4 | 66.67 | 170.5 | 184 | 212.9 | 0 | 2 | detail |  | OK_DETAIL
TA 509 | 2025-09 | 6 | 6 | 100 | 189 | 186 | 211.5 | 0 | 0 | detail |  | OK_DETAIL
TA 509 | 2025-10 | 11 | 10 | 90.91 | 98 | 120.7 | 194.1 | 0 | 1 | detail |  | OK_DETAIL
TA 509 | 2025-11 | 23 | 17 | 73.91 | 140 | 125.1765 | 166 | 0 | 6 | detail |  | OK_DETAIL
TA 509 | 2025-12 | 18 | 16 | 88.89 | 74 | 78.3125 | 125 | 0 | 2 | detail |  | OK_DETAIL
TA 509 | 2026-01 | 5 | 3 | 60 | 49 | 47.6667 | 63.4 | 0 | 2 | detail |  | OK_DETAIL
TA 509 | 2026-02 | 6 | 5 | 83.33 | 60 | 45.8 | 64 | 0 | 1 | detail |  | OK_DETAIL
TA 509 | 2026-03 | 5 | 0 | 0 |  |  |  | 0 | 5 | detail |  | OK_DETAIL
TA 509 | 2026-04 | 13 | 1 | 7.69 | 12 | 12 | 12 | 0 | 12 | detail |  | OK_DETAIL
TA 509 | 2026-05 | 6 | 0 | 0 |  |  |  | 0 | 6 | detail |  | OK_DETAIL
TA 510 | 2025-02 | 4 | 0 | 0 |  |  |  | 0 | 4 | detail |  | OK_DETAIL
TA 510 | 2025-03 | 6 | 0 | 0 |  |  |  | 0 | 6 | detail |  | OK_DETAIL
TA 510 | 2025-04 | 6 | 0 | 0 |  |  |  | 0 | 6 | detail |  | OK_DETAIL
TA 510 | 2025-05 | 8 | 7 | 87.5 | 290 | 306.7143 | 362.6 | 0 | 1 | detail |  | OK_DETAIL
TA 510 | 2025-06 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TA 510 | 2025-07 | 1 | 1 | 100 | 169 | 169 | 169 | 0 | 0 | detail |  | OK_DETAIL
TA 510 | 2025-08 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TA 510 | 2025-09 | 5 | 4 | 80 | 115.5 | 121 | 141.4 | 0 | 1 | detail |  | OK_DETAIL
TA 510 | 2025-10 | 1 | 1 | 100 | 82 | 82 | 82 | 0 | 0 | detail |  | OK_DETAIL
TA 510 | 2025-11 | 8 | 7 | 87.5 | 78 | 81.8571 | 101.2 | 0 | 1 | detail |  | OK_DETAIL
TA 510 | 2025-12 | 8 | 8 | 100 | 97 | 99.75 | 130.4 | 0 | 0 | detail |  | OK_DETAIL
TA 510 | 2026-01 | 7 | 2 | 28.57 | 75 | 75 | 83.8 | 0 | 5 | detail |  | OK_DETAIL
TA 510 | 2026-02 | 7 | 4 | 57.14 | 50.5 | 53.75 | 82.9 | 0 | 3 | detail |  | OK_DETAIL
TA 510 | 2026-03 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TA 510 | 2026-04 | 14 | 0 | 0 |  |  |  | 0 | 14 | detail |  | OK_DETAIL
TA 510 | 2026-05 | 7 | 0 | 0 |  |  |  | 0 | 7 | detail |  | OK_DETAIL
TA 512 | 2025-02 | 3 | 3 | 100 | 180 | 198.3333 | 248.8 | 0 | 0 | detail |  | OK_DETAIL
TA 512 | 2025-03 | 26 | 26 | 100 | 224 | 230.2308 | 324 | 0 | 0 | detail |  | OK_DETAIL
TA 512 | 2025-04 | 24 | 24 | 100 | 225 | 214 | 286.2 | 0 | 0 | detail |  | OK_DETAIL
TA 512 | 2025-05 | 23 | 21 | 91.3 | 206 | 200.0952 | 275 | 0 | 2 | detail |  | OK_DETAIL
TA 512 | 2025-06 | 27 | 23 | 85.19 | 213 | 204.8696 | 248.8 | 0 | 4 | detail |  | OK_DETAIL
TA 512 | 2025-07 | 35 | 29 | 82.86 | 162 | 177.8621 | 246.2 | 0 | 6 | detail |  | OK_DETAIL
TA 512 | 2025-08 | 26 | 20 | 76.92 | 160 | 152.15 | 213.6 | 0 | 6 | detail |  | OK_DETAIL
TA 512 | 2025-09 | 19 | 12 | 63.16 | 141.5 | 132.5833 | 153.7 | 0 | 7 | detail |  | OK_DETAIL
TA 512 | 2025-10 | 23 | 15 | 65.22 | 108 | 113.6667 | 168.2 | 0 | 8 | detail |  | OK_DETAIL
TA 512 | 2025-11 | 29 | 18 | 62.07 | 103 | 99.2778 | 138.5 | 0 | 11 | detail |  | OK_DETAIL
TA 512 | 2025-12 | 36 | 18 | 50 | 73.5 | 77.7778 | 110.8 | 0 | 18 | detail |  | OK_DETAIL
TA 512 | 2026-01 | 11 | 3 | 27.27 | 75 | 64 | 84.6 | 0 | 8 | detail |  | OK_DETAIL
TA 512 | 2026-02 | 4 | 0 | 0 |  |  |  | 0 | 4 | detail |  | OK_DETAIL
TA 512 | 2026-03 | 3 | 1 | 33.33 | 14 | 14 | 14 | 0 | 2 | detail |  | OK_DETAIL
TA 512 | 2026-04 | 7 | 0 | 0 |  |  |  | 0 | 7 | detail |  | OK_DETAIL
TA 512 | 2026-05 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TA 513 | 2025-03 | 3 | 2 | 66.67 | 180.5 | 180.5 | 184.1 | 0 | 1 | detail |  | OK_DETAIL
TA 513 | 2025-04 | 13 | 2 | 15.38 | 189 | 189 | 194.6 | 0 | 11 | detail |  | OK_DETAIL
TA 513 | 2025-05 | 20 | 8 | 40 | 184 | 183.75 | 211.2 | 0 | 12 | detail |  | OK_DETAIL
TA 513 | 2025-06 | 8 | 1 | 12.5 | 260 | 260 | 260 | 0 | 7 | detail |  | OK_DETAIL
TA 513 | 2025-07 | 10 | 4 | 40 | 184 | 181.25 | 201.1 | 0 | 6 | detail |  | OK_DETAIL
TA 513 | 2025-08 | 4 | 2 | 50 | 147.5 | 147.5 | 191.9 | 0 | 2 | detail |  | OK_DETAIL
TA 513 | 2025-09 | 7 | 3 | 42.86 | 31 | 31.6667 | 37.4 | 0 | 4 | detail |  | OK_DETAIL
TA 513 | 2025-10 | 2 | 1 | 50 | 128 | 128 | 128 | 0 | 1 | detail |  | OK_DETAIL
TA 513 | 2025-11 | 2 | 1 | 50 | 122 | 122 | 122 | 0 | 1 | detail |  | OK_DETAIL
TA 513 | 2025-12 | 3 | 2 | 66.67 | 108 | 108 | 108 | 1 | 1 | detail |  | OK_DETAIL
TA 513 | 2026-01 | 1 | 1 | 100 | 59 | 59 | 59 | 0 | 0 | detail |  | OK_DETAIL
TA 513 | 2026-02 | 2 | 1 | 50 | 21 | 21 | 21 | 0 | 1 | detail |  | OK_DETAIL
TA 513 | 2026-03 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TA 513 | 2026-04 | 3 | 0 | 0 |  |  |  | 0 | 3 | detail |  | OK_DETAIL
TA 513 | 2026-05 | 4 | 0 | 0 |  |  |  | 0 | 4 | detail |  | OK_DETAIL
TA 601 | 2025-05 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TA 601 | 2025-08 | 2 | 1 | 50 | 142 | 142 | 142 | 0 | 1 | detail |  | OK_DETAIL
TA 601 | 2025-09 | 2 | 2 | 100 | 134.5 | 134.5 | 146.9 | 0 | 0 | detail |  | OK_DETAIL
TA 601 | 2025-10 | 8 | 7 | 87.5 | 89 | 88.5714 | 97.4 | 0 | 1 | detail |  | OK_DETAIL
TA 601 | 2025-11 | 10 | 6 | 60 | 40.5 | 48.3333 | 75.5 | 0 | 4 | detail |  | OK_DETAIL
TA 601 | 2025-12 | 20 | 13 | 65 | 33 | 61 | 69.6 | 0 | 7 | detail |  | OK_DETAIL
TA 601 | 2026-01 | 27 | 23 | 85.19 | 17 | 20.7727 | 30.5 | 1 | 4 | detail |  | OK_DETAIL
TA 601 | 2026-02 | 17 | 14 | 82.35 | 14 | 15.2857 | 21.8 | 0 | 3 | detail |  | OK_DETAIL
TA 601 | 2026-03 | 15 | 3 | 20 | 20 | 21 | 24 | 0 | 12 | detail |  | OK_DETAIL
TA 601 | 2026-04 | 12 | 1 | 8.33 | 29 | 29 | 29 | 0 | 11 | detail |  | OK_DETAIL
TA 601 | 2026-05 | 6 | 0 | 0 |  |  |  | 0 | 6 | detail |  | OK_DETAIL
TA 602 | 2025-09 | 1 | 1 | 100 | 156 | 156 | 156 | 0 | 0 | detail |  | OK_DETAIL
TA 602 | 2025-10 | 9 | 5 | 55.56 | 181 | 173.25 | 202.9 | 1 | 4 | detail |  | OK_DETAIL
TA 602 | 2025-11 | 30 | 17 | 56.67 | 134 | 139.6471 | 181.4 | 0 | 13 | detail |  | OK_DETAIL
TA 602 | 2025-12 | 37 | 12 | 32.43 | 127 | 125.9167 | 148.9 | 0 | 25 | detail |  | OK_DETAIL
TA 602 | 2026-01 | 20 | 4 | 20 | 94.5 | 87 | 114.6 | 0 | 16 | detail |  | OK_DETAIL
TA 602 | 2026-02 | 12 | 1 | 8.33 | 18 | 18 | 18 | 0 | 11 | detail |  | OK_DETAIL
TA 602 | 2026-03 | 5 | 0 | 0 |  |  |  | 0 | 5 | detail |  | OK_DETAIL
TA 602 | 2026-04 | 22 | 0 | 0 |  |  |  | 0 | 22 | detail |  | OK_DETAIL
TA 602 | 2026-05 | 7 | 0 | 0 |  |  |  | 0 | 7 | detail |  | OK_DETAIL
TB 501 | 2024-08 | 3 | 3 | 100 | 185 | 171.6667 | 189.8 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2024-09 | 7 | 7 | 100 | 144 | 133.2857 | 172.8 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2024-10 | 25 | 25 | 100 | 123 | 127.2 | 170.6 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2024-11 | 26 | 26 | 100 | 93 | 87.6923 | 121.5 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2024-12 | 27 | 27 | 100 | 68 | 70.1481 | 106.4 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2025-01 | 21 | 21 | 100 | 62 | 80.5238 | 133 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2025-02 | 21 | 21 | 100 | 63 | 75.6667 | 112 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2025-03 | 9 | 9 | 100 | 29 | 46.3333 | 85.6 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2025-04 | 11 | 11 | 100 | 41 | 49.9091 | 98 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2025-05 | 18 | 18 | 100 | 31.5 | 41.0556 | 72.7 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2025-06 | 6 | 6 | 100 | 22 | 25.5 | 39 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2025-07 | 1 | 1 | 100 | 49 | 49 | 49 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2025-08 | 3 | 3 | 100 | 74 | 72 | 77.2 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2025-09 | 8 | 8 | 100 | 48 | 64.875 | 111.5 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2025-10 | 6 | 6 | 100 | 28 | 30.1667 | 43.5 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2025-11 | 7 | 7 | 100 | 10 | 13.4286 | 28.4 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2025-12 | 10 | 10 | 100 | 12 | 13.1111 | 21.2 | 1 | 0 | detail |  | OK_DETAIL
TB 501 | 2026-01 | 9 | 9 | 100 | 14 | 17.4444 | 25.6 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2026-02 | 4 | 4 | 100 | 24 | 23.6667 | 34.4 | 1 | 0 | detail |  | OK_DETAIL
TB 501 | 2026-03 | 4 | 4 | 100 | 4.5 | 5.25 | 7.1 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2026-04 | 5 | 4 | 80 | 15 | 16.25 | 26.3 | 0 | 1 | detail |  | OK_DETAIL
TB 507 | 2025-01 | 2 | 2 | 100 | 188.5 | 188.5 | 216.9 | 0 | 0 | detail |  | OK_DETAIL
TB 507 | 2025-02 | 20 | 19 | 95 | 164 | 176.3158 | 203 | 0 | 1 | detail |  | OK_DETAIL
TB 507 | 2025-03 | 16 | 6 | 37.5 | 177 | 206.3333 | 278.5 | 0 | 10 | detail |  | OK_DETAIL
TB 507 | 2025-04 | 13 | 5 | 38.46 | 235 | 218 | 288.4 | 0 | 8 | detail |  | OK_DETAIL
TB 507 | 2025-05 | 9 | 5 | 55.56 | 166 | 189.4 | 294 | 0 | 4 | detail |  | OK_DETAIL
TB 507 | 2025-06 | 25 | 22 | 88 | 118.5 | 125.0455 | 196.6 | 0 | 3 | detail |  | OK_DETAIL
TB 507 | 2025-07 | 50 | 45 | 90 | 71 | 78.7333 | 121.2 | 0 | 5 | detail |  | OK_DETAIL
TB 507 | 2025-08 | 52 | 43 | 82.69 | 61 | 71.907 | 128.8 | 0 | 9 | detail |  | OK_DETAIL
TB 507 | 2025-09 | 20 | 12 | 60 | 46 | 61.3333 | 109.7 | 0 | 8 | detail |  | OK_DETAIL
TB 507 | 2025-10 | 8 | 8 | 100 | 43 | 61.2857 | 115 | 1 | 0 | detail |  | OK_DETAIL
TB 507 | 2025-11 | 19 | 17 | 89.47 | 22 | 43.7059 | 84.6 | 0 | 2 | detail |  | OK_DETAIL
TB 507 | 2025-12 | 13 | 7 | 53.85 | 53 | 77.1429 | 134 | 0 | 6 | detail |  | OK_DETAIL
TB 507 | 2026-01 | 15 | 7 | 46.67 | 79 | 76.1429 | 95 | 0 | 8 | detail |  | OK_DETAIL
TB 507 | 2026-02 | 12 | 4 | 33.33 | 58.5 | 59.25 | 76 | 0 | 8 | detail |  | OK_DETAIL
TB 507 | 2026-03 | 16 | 4 | 25 | 35 | 34 | 36.4 | 0 | 12 | detail |  | OK_DETAIL
TB 507 | 2026-04 | 20 | 5 | 25 | 18 | 18 | 19.6 | 0 | 15 | detail |  | OK_DETAIL
TB 507 | 2026-05 | 21 | 2 | 9.52 | 4.5 | 4.5 | 4.9 | 0 | 19 | detail |  | OK_DETAIL
TB 605 | 2025-08 | 1 | 1 | 100 | 108 | 108 | 108 | 0 | 0 | detail |  | OK_DETAIL
TB 605 | 2025-09 | 3 | 3 | 100 | 90 | 131.6667 | 196.4 | 0 | 0 | detail |  | OK_DETAIL
TB 605 | 2025-10 | 15 | 11 | 73.33 | 108 | 124.7273 | 189 | 0 | 4 | detail |  | OK_DETAIL
TB 605 | 2025-11 | 42 | 34 | 80.95 | 88 | 91.5588 | 114 | 0 | 8 | detail |  | OK_DETAIL
TB 605 | 2025-12 | 57 | 45 | 78.95 | 91 | 93 | 138.6 | 0 | 12 | detail |  | OK_DETAIL
TB 605 | 2026-01 | 42 | 37 | 88.1 | 69 | 66.5135 | 98.4 | 0 | 5 | detail |  | OK_DETAIL
TB 605 | 2026-02 | 42 | 26 | 61.9 | 41.5 | 48.3846 | 82.5 | 0 | 16 | detail |  | OK_DETAIL
TB 605 | 2026-03 | 28 | 15 | 53.57 | 23 | 27.6 | 44.8 | 0 | 13 | detail |  | OK_DETAIL
TB 605 | 2026-04 | 26 | 7 | 26.92 | 16 | 15 | 21.4 | 0 | 19 | detail |  | OK_DETAIL
TB 605 | 2026-05 | 32 | 0 | 0 |  |  |  | 0 | 32 | detail |  | OK_DETAIL
TB 608 | 2025-10 | 2 | 1 | 50 | 186 | 186 | 186 | 0 | 1 | detail |  | OK_DETAIL
TB 608 | 2025-11 | 20 | 6 | 30 | 85.5 | 85 | 127 | 0 | 14 | detail |  | OK_DETAIL
TB 608 | 2025-12 | 34 | 8 | 23.53 | 67 | 60.375 | 76.3 | 0 | 26 | detail |  | OK_DETAIL
TB 608 | 2026-01 | 30 | 4 | 13.33 | 82.5 | 78 | 97.8 | 0 | 26 | detail |  | OK_DETAIL
TB 608 | 2026-02 | 30 | 3 | 10 | 47 | 46.6667 | 47.8 | 0 | 27 | detail |  | OK_DETAIL
TB 608 | 2026-03 | 14 | 0 | 0 |  |  |  | 0 | 14 | detail |  | OK_DETAIL
TB 608 | 2026-04 | 2 | 0 | 0 |  |  |  | 0 | 2 | detail |  | OK_DETAIL

## Foundation Delay Coverage
Foundation Delay Coverage
Project | Eligible | Coverage Status | Source Type | Parser Modes | Reason | Foundation Locations | Matched Locations | Negative Excluded | Unmatched Locations | Notes
TA 413 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 314 | 304 | 2 | 10 | Negative delays are excluded from trend statistics.
TA 414 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 327 | 225 | 2 | 102 | Negative delays are excluded from trend statistics.
TA 416 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 303 | 303 | 0 | 0 | Negative delays are excluded from trend statistics.
TA 418 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 129 | 125 | 0 | 4 | Negative delays are excluded from trend statistics.
TA 419 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 268 | 201 | 2 | 67 | Negative delays are excluded from trend statistics.
TA 421 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 303 | 299 | 0 | 4 | Negative delays are excluded from trend statistics.
TA 504 | No | SKIPPED_BLANK_CONFIG | missing |  | Foundation mapping intentionally blank in DPR_Config. | 0 | 0 | 0 | 0 | Negative delays are excluded from trend statistics.
TA 505 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 373 | 353 | 1 | 20 | Negative delays are excluded from trend statistics.
TA 506 | No | SKIPPED_BLANK_CONFIG | missing |  | Foundation mapping intentionally blank in DPR_Config. | 0 | 0 | 0 | 0 | Negative delays are excluded from trend statistics.
TA 509 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 264 | 199 | 0 | 65 | Negative delays are excluded from trend statistics.
TA 510 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 85 | 34 | 0 | 51 | Negative delays are excluded from trend statistics.
TA 512 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 297 | 213 | 0 | 84 | Negative delays are excluded from trend statistics.
TA 513 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 83 | 28 | 1 | 55 | Negative delays are excluded from trend statistics.
TA 515 | No | MAPPING_CONFIRMATION_REQUIRED | missing |  | Only snapshot/missing foundation source is available. | 0 | 0 | 0 | 0 | Negative delays are excluded from trend statistics.
TA 601 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 120 | 70 | 1 | 50 | Negative delays are excluded from trend statistics.
TA 602 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 143 | 40 | 1 | 103 | Negative delays are excluded from trend statistics.
TB 408 | No | BLOCKED_NO_SOURCE | missing |  | Only snapshot/missing foundation source is available. | 0 | 0 | 0 | 0 | Negative delays are excluded from trend statistics.
TB 501 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 231 | 230 | 2 | 1 | Negative delays are excluded from trend statistics.
TB 507 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 331 | 213 | 1 | 118 | Negative delays are excluded from trend statistics.
TB 605 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 288 | 179 | 0 | 109 | Negative delays are excluded from trend statistics.
TB 608 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 132 | 22 | 0 | 110 | Negative delays are excluded from trend statistics.

## Foundation Delay Anomalies
Foundation Delay Anomalies
Project | Location | Foundation Date | Erection Start | Delay Days | Issue | Foundation Line | Erection Line
TA 413 | 39/8 | 2025-01-24 | 2024-03-26 | -304 | NEGATIVE_DELAY_EXCLUDED
TA 413 | N'37A/0 | 2026-03-05 | 2025-02-28 | -370 | NEGATIVE_DELAY_EXCLUDED |  | nan
TA 413 | 37/1 | 2024-09-23 |  |  | UNMATCHED_LOCATION
TA 413 | 3/8 | 2024-10-05 |  |  | UNMATCHED_LOCATION
TA 413 | 3/9 | 2024-10-09 |  |  | UNMATCHED_LOCATION
TA 413 | 37/0 | 2024-10-14 |  |  | UNMATCHED_LOCATION
TA 413 | 3/7 | 2024-10-19 |  |  | UNMATCHED_LOCATION
TA 413 | 3/6 | 2024-10-22 |  |  | UNMATCHED_LOCATION
TA 413 | 3/4 | 2024-10-29 |  |  | UNMATCHED_LOCATION
TA 413 | 16/0 | 2024-12-28 |  |  | UNMATCHED_LOCATION
TA 413 | 36B/0 | 2026-01-23 |  |  | UNMATCHED_LOCATION
TA 413 | N'37/0 | 2026-02-08 |  |  | UNMATCHED_LOCATION
TA 414 | 121/4 | 2024-11-19 | 2024-03-27 | -237 | NEGATIVE_DELAY_EXCLUDED
TA 414 | 126/0 | 2026-02-18 | 2026-01-17 | -32 | NEGATIVE_DELAY_EXCLUDED
TA 414 | 249/1 | 2024-12-19 |  |  | UNMATCHED_LOCATION
TA 414 | 249/0 | 2024-12-26 |  |  | UNMATCHED_LOCATION
TA 414 | 249/2 | 2024-12-28 |  |  | UNMATCHED_LOCATION
TA 414 | 250/0 | 2025-01-07 |  |  | UNMATCHED_LOCATION
TA 414 | 121/8 | 2025-01-10 |  |  | UNMATCHED_LOCATION
TA 414 | 121/9 | 2025-01-20 |  |  | UNMATCHED_LOCATION
TA 414 | 243/3 | 2025-02-07 |  |  | UNMATCHED_LOCATION
TA 414 | 172/0 | 2025-03-07 |  |  | UNMATCHED_LOCATION
TA 414 | 165/2 | 2025-05-02 |  |  | UNMATCHED_LOCATION
TA 414 | 130/0 | 2025-05-10 |  |  | UNMATCHED_LOCATION
TA 414 | 221/0 | 2025-10-21 |  |  | UNMATCHED_LOCATION
TA 414 | 223/2 | 2025-10-26 |  |  | UNMATCHED_LOCATION
TA 414 | 224/0 | 2025-10-26 |  |  | UNMATCHED_LOCATION
TA 414 | 135/0 | 2025-11-04 |  |  | UNMATCHED_LOCATION
TA 414 | 219/1 | 2025-11-18 |  |  | UNMATCHED_LOCATION
TA 414 | 225/1 | 2025-11-22 |  |  | UNMATCHED_LOCATION
TA 414 | 225/4 | 2025-11-25 |  |  | UNMATCHED_LOCATION
TA 414 | 127/2 | 2025-12-01 |  |  | UNMATCHED_LOCATION
TA 414 | 194/0 | 2025-12-04 |  |  | UNMATCHED_LOCATION
TA 414 | 225/3 | 2025-12-05 |  |  | UNMATCHED_LOCATION
TA 414 | 244/0 | 2025-12-05 |  |  | UNMATCHED_LOCATION
TA 414 | 256/1 | 2025-12-09 |  |  | UNMATCHED_LOCATION
TA 414 | 225/2 | 2025-12-11 |  |  | UNMATCHED_LOCATION
TA 414 | 210/0 | 2025-12-13 |  |  | UNMATCHED_LOCATION
TA 414 | 139/3 | 2025-12-16 |  |  | UNMATCHED_LOCATION
TA 414 | 216/1 | 2025-12-16 |  |  | UNMATCHED_LOCATION
TA 414 | 257/0 | 2025-12-16 |  |  | UNMATCHED_LOCATION
TA 414 | 170/0 | 2025-12-17 |  |  | UNMATCHED_LOCATION
TA 414 | 173/0 | 2025-12-18 |  |  | UNMATCHED_LOCATION
TA 414 | 165/6 | 2025-12-20 |  |  | UNMATCHED_LOCATION
TA 414 | 193/0 | 2025-12-20 |  |  | UNMATCHED_LOCATION
TA 414 | 250/1 | 2025-12-20 |  |  | UNMATCHED_LOCATION
TA 414 | 216/2 | 2025-12-25 |  |  | UNMATCHED_LOCATION
TA 414 | 216/3 | 2025-12-25 |  |  | UNMATCHED_LOCATION
TA 414 | 244/3 | 2025-12-26 |  |  | UNMATCHED_LOCATION
TA 414 | 162/0 | 2025-12-29 |  |  | UNMATCHED_LOCATION
TA 414 | 211/0 | 2026-01-01 |  |  | UNMATCHED_LOCATION
TA 414 | 217/5 | 2026-01-12 |  |  | UNMATCHED_LOCATION
TA 414 | 211/4 | 2026-01-15 |  |  | UNMATCHED_LOCATION
TA 414 | 188/0 | 2026-01-16 |  |  | UNMATCHED_LOCATION
TA 414 | 212/0 | 2026-01-16 |  |  | UNMATCHED_LOCATION
TA 414 | 189/0 | 2026-01-18 |  |  | UNMATCHED_LOCATION
TA 414 | 213/0 | 2026-01-18 |  |  | UNMATCHED_LOCATION
TA 414 | 133/1 | 2026-01-19 |  |  | UNMATCHED_LOCATION
TA 414 | 165/4 | 2026-01-19 |  |  | UNMATCHED_LOCATION
TA 414 | 232/4 | 2026-01-19 |  |  | UNMATCHED_LOCATION
TA 414 | 233/0 | 2026-01-19 |  |  | UNMATCHED_LOCATION
TA 414 | 168/0 | 2026-01-20 |  |  | UNMATCHED_LOCATION
TA 414 | 238/0 | 2026-01-20 |  |  | UNMATCHED_LOCATION
TA 414 | 235/0 | 2026-01-21 |  |  | UNMATCHED_LOCATION
TA 414 | 236/0 | 2026-01-21 |  |  | UNMATCHED_LOCATION
TA 414 | 129/0 | 2026-01-23 |  |  | UNMATCHED_LOCATION
TA 414 | 163/0 | 2026-01-26 |  |  | UNMATCHED_LOCATION
TA 414 | 124/2 | 2026-02-01 |  |  | UNMATCHED_LOCATION
TA 414 | 214/0 | 2026-02-05 |  |  | UNMATCHED_LOCATION
TA 414 | 237/0 | 2026-02-05 |  |  | UNMATCHED_LOCATION
TA 414 | 232/0 | 2026-02-07 |  |  | UNMATCHED_LOCATION
TA 414 | 235/1 | 2026-02-07 |  |  | UNMATCHED_LOCATION
TA 414 | 217/0 | 2026-02-13 |  |  | UNMATCHED_LOCATION
TA 414 | 217/1 | 2026-02-13 |  |  | UNMATCHED_LOCATION
TA 414 | 248/0 | 2026-02-13 |  |  | UNMATCHED_LOCATION
TA 414 | 145/1 | 2026-02-14 |  |  | UNMATCHED_LOCATION
TA 414 | 219/0 | 2026-02-17 |  |  | UNMATCHED_LOCATION
TA 414 | 255/1 | 2026-02-25 |  |  | UNMATCHED_LOCATION
TA 414 | 234/0 | 2026-03-11 |  |  | UNMATCHED_LOCATION
TA 414 | 231/0 | 2026-03-12 |  |  | UNMATCHED_LOCATION
TA 414 | 131/0 | 2026-03-13 |  |  | UNMATCHED_LOCATION
TA 414 | 150/1 | 2026-03-16 |  |  | UNMATCHED_LOCATION
TA 414 | 180/0 | 2026-03-16 |  |  | UNMATCHED_LOCATION
TA 414 | 225/7 | 2026-03-16 |  |  | UNMATCHED_LOCATION
TA 414 | 232/2 | 2026-03-16 |  |  | UNMATCHED_LOCATION
TA 414 | 225/5 | 2026-03-18 |  |  | UNMATCHED_LOCATION
TA 414 | 230/1 | 2026-03-23 |  |  | UNMATCHED_LOCATION
TA 414 | 156/0 | 2026-03-25 |  |  | UNMATCHED_LOCATION
TA 414 | 150/0 | 2026-03-26 |  |  | UNMATCHED_LOCATION
TA 414 | 230A/0 | 2026-03-26 |  |  | UNMATCHED_LOCATION
TA 414 | 200/0 | 2026-04-01 |  |  | UNMATCHED_LOCATION
TA 414 | 155/0 | 2026-04-05 |  |  | UNMATCHED_LOCATION
TA 414 | 156/1 | 2026-04-05 |  |  | UNMATCHED_LOCATION
TA 414 | 159/0 | 2026-04-05 |  |  | UNMATCHED_LOCATION
TA 414 | 195/0 | 2026-04-05 |  |  | UNMATCHED_LOCATION
TA 414 | 232/3 | 2026-04-05 |  |  | UNMATCHED_LOCATION
TA 414 | 151/0 | 2026-04-09 |  |  | UNMATCHED_LOCATION
TA 414 | 164/0 | 2026-04-12 |  |  | UNMATCHED_LOCATION
TA 414 | 165/0 | 2026-04-12 |  |  | UNMATCHED_LOCATION
TA 414 | 131/1 | 2026-04-14 |  |  | UNMATCHED_LOCATION
TA 414 | 229B/0 | 2026-04-17 |  |  | UNMATCHED_LOCATION
TA 414 | 151A/0 | 2026-04-21 |  |  | UNMATCHED_LOCATION
TA 414 | 153/1 | 2026-04-21 |  |  | UNMATCHED_LOCATION
TA 414 | 229A/0 | 2026-04-21 |  |  | UNMATCHED_LOCATION
TA 414 | 235/4 | 2026-04-23 |  |  | UNMATCHED_LOCATION
TA 414 | 169/0 | 2026-04-26 |  |  | UNMATCHED_LOCATION
TA 414 | 206/0 | 2026-04-27 |  |  | UNMATCHED_LOCATION
TA 414 | 225/6 | 2026-04-27 |  |  | UNMATCHED_LOCATION
TA 414 | 206/1 | 2026-05-02 |  |  | UNMATCHED_LOCATION
TA 414 | 201/0 | 2026-05-09 |  |  | UNMATCHED_LOCATION
TA 414 | 203/0 | 2026-05-09 |  |  | UNMATCHED_LOCATION
TA 414 | 203A/0 | 2026-05-09 |  |  | UNMATCHED_LOCATION
TA 414 | 203B/0 | 2026-05-09 |  |  | UNMATCHED_LOCATION
TA 414 | 153A/0 | 2026-05-13 |  |  | UNMATCHED_LOCATION
TA 414 | 229/0 | 2026-05-14 |  |  | UNMATCHED_LOCATION
TA 414 | 153/2 | 2026-05-20 |  |  | UNMATCHED_LOCATION
TA 418 | 35/6 | 2024-08-07 |  |  | UNMATCHED_LOCATION
TA 418 | 45/02 | 2024-12-04 |  |  | UNMATCHED_LOCATION
TA 418 | 46/1 | 2025-06-25 |  |  | UNMATCHED_LOCATION
TA 418 | 59/1 | 2025-12-12 |  |  | UNMATCHED_LOCATION
TA 419 | 6/9 | 2024-07-10 | 2024-01-06 | -186 | NEGATIVE_DELAY_EXCLUDED
TA 419 | 26/1 | 2025-11-15 | 2025-03-22 | -238 | NEGATIVE_DELAY_EXCLUDED
TA 419 | 15/0 | 2024-12-12 |  |  | UNMATCHED_LOCATION
TA 419 | 36/4 | 2025-01-28 |  |  | UNMATCHED_LOCATION
TA 419 | 39/0 | 2025-03-27 |  |  | UNMATCHED_LOCATION
TA 419 | 41/0 | 2025-04-23 |  |  | UNMATCHED_LOCATION
TA 419 | 83/6 | 2025-05-03 |  |  | UNMATCHED_LOCATION
TA 419 | 78/3 | 2025-06-11 |  |  | UNMATCHED_LOCATION
TA 419 | 8/0 | 2025-07-15 |  |  | UNMATCHED_LOCATION
TA 419 | 46/0 | 2025-08-01 |  |  | UNMATCHED_LOCATION
TA 419 | 43/3 | 2025-11-01 |  |  | UNMATCHED_LOCATION
TA 419 | 63/5 | 2025-11-02 |  |  | UNMATCHED_LOCATION
TA 419 | 83/9 | 2025-11-02 |  |  | UNMATCHED_LOCATION
TA 419 | 36/9 | 2025-11-06 |  |  | UNMATCHED_LOCATION
TA 419 | 43/1 | 2025-11-07 |  |  | UNMATCHED_LOCATION
TA 419 | 43/2 | 2025-11-09 |  |  | UNMATCHED_LOCATION
TA 419 | 83/8 | 2025-11-23 |  |  | UNMATCHED_LOCATION
TA 419 | 63/6 | 2025-12-10 |  |  | UNMATCHED_LOCATION
TA 419 | 84/0 | 2025-12-15 |  |  | UNMATCHED_LOCATION
TA 419 | 52/1 | 2025-12-16 |  |  | UNMATCHED_LOCATION
TA 419 | 63B/6 | 2025-12-18 |  |  | UNMATCHED_LOCATION
TA 419 | 64A/0 | 2025-12-18 |  |  | UNMATCHED_LOCATION
TA 419 | 62/0 | 2025-12-19 |  |  | UNMATCHED_LOCATION
TA 419 | 36/3 | 2025-12-24 |  |  | UNMATCHED_LOCATION
TA 419 | 60/0 | 2025-12-25 |  |  | UNMATCHED_LOCATION
TA 419 | 64/0 | 2025-12-29 |  |  | UNMATCHED_LOCATION
TA 419 | 78A/0 | 2026-01-03 |  |  | UNMATCHED_LOCATION
TA 419 | 64/2 | 2026-01-07 |  |  | UNMATCHED_LOCATION
TA 419 | 38/1 | 2026-01-11 |  |  | UNMATCHED_LOCATION
TA 419 | 81/0 | 2026-01-16 |  |  | UNMATCHED_LOCATION
TA 419 | 82/0 | 2026-01-16 |  |  | UNMATCHED_LOCATION
TA 419 | 77/0 | 2026-01-20 |  |  | UNMATCHED_LOCATION
TA 419 | 38/3 | 2026-01-28 |  |  | UNMATCHED_LOCATION
TA 419 | 42/0 | 2026-02-04 |  |  | UNMATCHED_LOCATION
TA 419 | 40/8 | 2026-02-12 |  |  | UNMATCHED_LOCATION
TA 419 | 13/0 | 2026-03-20 |  |  | UNMATCHED_LOCATION
TA 419 | 73/0 | 2026-03-22 |  |  | UNMATCHED_LOCATION
TA 419 | 32/0 | 2026-03-25 |  |  | UNMATCHED_LOCATION
TA 419 | 76/2 | 2026-03-25 |  |  | UNMATCHED_LOCATION
TA 419 | 84/2 | 2026-03-25 |  |  | UNMATCHED_LOCATION
TA 419 | 38/4 | 2026-04-01 |  |  | UNMATCHED_LOCATION
TA 419 | 80/0 | 2026-04-01 |  |  | UNMATCHED_LOCATION
TA 419 | 64/3 | 2026-04-05 |  |  | UNMATCHED_LOCATION
TA 419 | 64/4 | 2026-04-05 |  |  | UNMATCHED_LOCATION
TA 419 | 93B/0 | 2026-04-07 |  |  | UNMATCHED_LOCATION
TA 419 | 71/0 | 2026-04-08 |  |  | UNMATCHED_LOCATION
TA 419 | 41/2 | 2026-04-13 |  |  | UNMATCHED_LOCATION
TA 419 | 69/0 | 2026-04-17 |  |  | UNMATCHED_LOCATION
TA 419 | 70/0 | 2026-04-18 |  |  | UNMATCHED_LOCATION
TA 419 | 14/1 | 2026-04-23 |  |  | UNMATCHED_LOCATION
TA 419 | 66/1 | 2026-04-25 |  |  | UNMATCHED_LOCATION
TA 419 | 67/0 | 2026-04-25 |  |  | UNMATCHED_LOCATION
TA 419 | 37/0 | 2026-04-27 |  |  | UNMATCHED_LOCATION
TA 419 | 53/0 | 2026-04-27 |  |  | UNMATCHED_LOCATION
TA 419 | 52/0 | 2026-04-30 |  |  | UNMATCHED_LOCATION
TA 419 | 54/0 | 2026-04-30 |  |  | UNMATCHED_LOCATION
TA 419 | 38/2 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TA 419 | 59/0 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TA 419 | 87/1 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TA 419 | 87/2 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TA 419 | 65/0 | 2026-05-08 |  |  | UNMATCHED_LOCATION
TA 419 | 72/0 | 2026-05-09 |  |  | UNMATCHED_LOCATION
TA 419 | 68/0 | 2026-05-11 |  |  | UNMATCHED_LOCATION
TA 419 | 95A/0 | 2026-05-12 |  |  | UNMATCHED_LOCATION
TA 419 | 76/1 | 2026-05-13 |  |  | UNMATCHED_LOCATION
TA 419 | 66/0 | 2026-05-16 |  |  | UNMATCHED_LOCATION
TA 419 | 75/0 | 2026-05-16 |  |  | UNMATCHED_LOCATION
TA 419 | 76/0 | 2026-05-17 |  |  | UNMATCHED_LOCATION
TA 419 | 96/0 | 2026-05-17 |  |  | UNMATCHED_LOCATION
TA 421 | 8/11 | 2025-04-15 |  |  | UNMATCHED_LOCATION
TA 421 | 4/16 | 2025-04-29 |  |  | UNMATCHED_LOCATION
TA 421 | 43A/0 | 2025-07-22 |  |  | UNMATCHED_LOCATION
TA 421 | 8/0 | 2025-12-06 |  |  | UNMATCHED_LOCATION
TA 505 | 177/0 | 2026-05-15 | 2025-12-04 | -162 | NEGATIVE_DELAY_EXCLUDED
TA 505 | 171/10 | 2015-11-27 |  |  | UNMATCHED_LOCATION
TA 505 | 138/0 | 2025-11-29 |  |  | UNMATCHED_LOCATION
TA 505 | 149B/0 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TA 505 | 158/0 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TA 505 | 174B/0 | 2026-01-22 |  |  | UNMATCHED_LOCATION
TA 505 | 182/0 | 2026-01-25 |  |  | UNMATCHED_LOCATION
TA 505 | 148C/0 | 2026-02-21 |  |  | UNMATCHED_LOCATION
TA 505 | 148B/0 | 2026-02-28 |  |  | UNMATCHED_LOCATION
TA 505 | 157/0 | 2026-03-10 |  |  | UNMATCHED_LOCATION
TA 505 | 144/0 | 2026-03-21 |  |  | UNMATCHED_LOCATION
TA 505 | 171/5 | 2026-03-21 |  |  | UNMATCHED_LOCATION
TA 505 | 143/0 | 2026-03-31 |  |  | UNMATCHED_LOCATION
TA 505 | 134/0 | 2026-04-09 |  |  | UNMATCHED_LOCATION
TA 505 | 129/0 | 2026-04-14 |  |  | UNMATCHED_LOCATION
TA 505 | 133/0 | 2026-04-14 |  |  | UNMATCHED_LOCATION
TA 505 | 136/4 | 2026-04-15 |  |  | UNMATCHED_LOCATION
TA 505 | 129/1 | 2026-04-23 |  |  | UNMATCHED_LOCATION
TA 505 | 117/0 | 2026-04-30 |  |  | UNMATCHED_LOCATION
TA 505 | 137/0 | 2026-05-15 |  |  | UNMATCHED_LOCATION
TA 505 | 181/2 | 2026-05-18 |  |  | UNMATCHED_LOCATION
TA 509 | 13/5 | 2025-03-01 |  |  | UNMATCHED_LOCATION
TA 509 | 24/1 | 2025-03-01 |  |  | UNMATCHED_LOCATION
TA 509 | 21/3 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 24/2 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 24/4 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 24/5 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 39/7 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 39/8 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 41/1 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 41/2 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 41/5 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 41/8 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 44/2 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 44/3 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 23/1 | 2025-04-05 |  |  | UNMATCHED_LOCATION
TA 509 | 49/3 | 2025-05-23 |  |  | UNMATCHED_LOCATION
TA 509 | 49/2 | 2025-05-26 |  |  | UNMATCHED_LOCATION
TA 509 | 51/3 | 2025-05-26 |  |  | UNMATCHED_LOCATION
TA 509 | 47/4 | 2025-05-27 |  |  | UNMATCHED_LOCATION
TA 509 | 48/6 | 2025-06-01 |  |  | UNMATCHED_LOCATION
TA 509 | 47/6 | 2025-06-04 |  |  | UNMATCHED_LOCATION
TA 509 | 49/5 | 2025-06-06 |  |  | UNMATCHED_LOCATION
TA 509 | 48/9 | 2025-06-10 |  |  | UNMATCHED_LOCATION
TA 509 | 65/1 | 2025-06-18 |  |  | UNMATCHED_LOCATION
TA 509 | 66/7 | 2025-06-27 |  |  | UNMATCHED_LOCATION
TA 509 | 65/3 | 2025-06-30 |  |  | UNMATCHED_LOCATION
TA 509 | 67/1 | 2025-07-06 |  |  | UNMATCHED_LOCATION
TA 509 | 63/2 | 2025-07-16 |  |  | UNMATCHED_LOCATION
TA 509 | 41/4 | 2025-08-06 |  |  | UNMATCHED_LOCATION
TA 509 | 21/0 | 2025-08-12 |  |  | UNMATCHED_LOCATION
TA 509 | 64/1 | 2025-10-30 |  |  | UNMATCHED_LOCATION
TA 509 | 47/2 | 2025-11-05 |  |  | UNMATCHED_LOCATION
TA 509 | 46A/2 | 2025-11-06 |  |  | UNMATCHED_LOCATION
TA 509 | 47/7 | 2025-11-06 |  |  | UNMATCHED_LOCATION
TA 509 | 47/3 | 2025-11-13 |  |  | UNMATCHED_LOCATION
TA 509 | 66/3 | 2025-11-18 |  |  | UNMATCHED_LOCATION
TA 509 | 23/0 | 2025-11-29 |  |  | UNMATCHED_LOCATION
TA 509 | 65/0 | 2025-12-02 |  |  | UNMATCHED_LOCATION
TA 509 | 56/2 | 2025-12-19 |  |  | UNMATCHED_LOCATION
TA 509 | 48/3 | 2026-01-04 |  |  | UNMATCHED_LOCATION
TA 509 | 48/1 | 2026-01-24 |  |  | UNMATCHED_LOCATION
TA 509 | 26/0 | 2026-02-06 |  |  | UNMATCHED_LOCATION
TA 509 | 53A/0 | 2026-03-14 |  |  | UNMATCHED_LOCATION
TA 509 | 39/6 | 2026-03-21 |  |  | UNMATCHED_LOCATION
TA 509 | 41/7 | 2026-03-26 |  |  | UNMATCHED_LOCATION
TA 509 | 53B/0 | 2026-03-30 |  |  | UNMATCHED_LOCATION
TA 509 | 39/10 | 2026-03-31 |  |  | UNMATCHED_LOCATION
TA 509 | 28/0 | 2026-04-04 |  |  | UNMATCHED_LOCATION
TA 509 | 48/0 | 2026-04-05 |  |  | UNMATCHED_LOCATION
TA 509 | 65/4 | 2026-04-05 |  |  | UNMATCHED_LOCATION
TA 509 | 39/11 | 2026-04-08 |  |  | UNMATCHED_LOCATION
TA 509 | 35/0 | 2026-04-09 |  |  | UNMATCHED_LOCATION
TA 509 | 41/3 | 2026-04-10 |  |  | UNMATCHED_LOCATION
TA 509 | 4/6 | 2026-04-16 |  |  | UNMATCHED_LOCATION
TA 509 | 4/4 | 2026-04-18 |  |  | UNMATCHED_LOCATION
TA 509 | 54/0 | 2026-04-18 |  |  | UNMATCHED_LOCATION
TA 509 | 4/3 | 2026-04-20 |  |  | UNMATCHED_LOCATION
TA 509 | 39/9 | 2026-04-25 |  |  | UNMATCHED_LOCATION
TA 509 | 3/1 | 2026-04-29 |  |  | UNMATCHED_LOCATION
TA 509 | 4/5 | 2026-05-02 |  |  | UNMATCHED_LOCATION
TA 509 | 45/2 | 2026-05-04 |  |  | UNMATCHED_LOCATION
TA 509 | 50/0 | 2026-05-05 |  |  | UNMATCHED_LOCATION
TA 509 | 4/0 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TA 509 | 3/0 | 2026-05-12 |  |  | UNMATCHED_LOCATION
TA 509 | 47/9 | 2026-05-14 |  |  | UNMATCHED_LOCATION
TA 510 | 155/1 | 2025-02-12 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 155/3 | 2025-02-18 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 155/4 | 2025-02-18 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 155/5 | 2025-02-23 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 156/0 | 2025-03-05 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 156/1 | 2025-03-05 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 156/3 | 2025-03-13 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 156/4 | 2025-03-21 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 139/1 | 2025-03-26 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 156/2 | 2025-03-26 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 138/0 | 2025-04-05 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 137/0 | 2025-04-14 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 138/1 | 2025-04-14 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 139/5 | 2025-04-14 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 139/4 | 2025-04-23 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 136/0 | 2025-04-25 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 143/2 | 2025-05-30 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 144/0 | 2025-06-01 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 133/2 | 2025-08-31 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 138/2 | 2025-09-19 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 138/3 | 2025-11-18 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 147/2 | 2026-01-01 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 147/1 | 2026-01-08 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 192/7 | 2026-01-09 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 192/12 | 2026-01-16 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 142/0 | 2026-01-27 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 148/0 | 2026-02-01 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 157B/0 | 2026-02-16 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 157A/0 | 2026-02-17 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 157/2 | 2026-03-14 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 139/0 | 2026-04-01 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 192/9 | 2026-04-02 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 139/3 | 2026-04-04 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 153/0 | 2026-04-04 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 193/2 | 2026-04-08 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 193/1 | 2026-04-12 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 131/1 | 2026-04-13 |  |  | UNMATCHED_LOCATION | Pile
TA 510 | 193/5 | 2026-04-14 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 193/0 | 2026-04-19 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 193/4 | 2026-04-19 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 150/2 | 2026-04-22 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 157B/1 | 2026-04-22 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 192/8 | 2026-04-29 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 194/0 | 2026-04-30 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 167/2 | 2026-05-07 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 133/0 | 2026-05-09 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 167/3 | 2026-05-11 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 167/4 | 2026-05-17 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 133/1 | 2026-05-19 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 155/2 | 2026-05-20 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 167/1 | 2026-05-20 |  |  | UNMATCHED_LOCATION | FDN
TA 512 | 7/2 | 2025-05-04 |  |  | UNMATCHED_LOCATION
TA 512 | 5/8 | 2025-05-19 |  |  | UNMATCHED_LOCATION
TA 512 | 31/11 | 2025-06-10 |  |  | UNMATCHED_LOCATION
TA 512 | 27/2 | 2025-06-17 |  |  | UNMATCHED_LOCATION
TA 512 | 27/3 | 2025-06-20 |  |  | UNMATCHED_LOCATION
TA 512 | 34/4 | 2025-06-30 |  |  | UNMATCHED_LOCATION
TA 512 | 16/2 | 2025-07-10 |  |  | UNMATCHED_LOCATION
TA 512 | 4/3 | 2025-07-17 |  |  | UNMATCHED_LOCATION
TA 512 | 1A/3 | 2025-07-20 |  |  | UNMATCHED_LOCATION
TA 512 | 40/2 | 2025-07-25 |  |  | UNMATCHED_LOCATION
TA 512 | 31/24 | 2025-07-29 |  |  | UNMATCHED_LOCATION
TA 512 | 40/3 | 2025-07-29 |  |  | UNMATCHED_LOCATION
TA 512 | 40/4 | 2025-08-03 |  |  | UNMATCHED_LOCATION
TA 512 | 31/21 | 2025-08-07 |  |  | UNMATCHED_LOCATION
TA 512 | 2/1 | 2025-08-13 |  |  | UNMATCHED_LOCATION
TA 512 | 34/5 | 2025-08-14 |  |  | UNMATCHED_LOCATION
TA 512 | 30/16 | 2025-08-22 |  |  | UNMATCHED_LOCATION
TA 512 | 31/22 | 2025-08-22 |  |  | UNMATCHED_LOCATION
TA 512 | 29/18 | 2025-09-03 |  |  | UNMATCHED_LOCATION
TA 512 | 36/9 | 2025-09-03 |  |  | UNMATCHED_LOCATION
TA 512 | 4/5 | 2025-09-03 |  |  | UNMATCHED_LOCATION
TA 512 | 37/6 | 2025-09-06 |  |  | UNMATCHED_LOCATION
TA 512 | 34/2 | 2025-09-09 |  |  | UNMATCHED_LOCATION
TA 512 | 36/5 | 2025-09-21 |  |  | UNMATCHED_LOCATION
TA 512 | 36/4 | 2025-09-26 |  |  | UNMATCHED_LOCATION
TA 512 | 29/19 | 2025-10-01 |  |  | UNMATCHED_LOCATION
TA 512 | 36/2 | 2025-10-12 |  |  | UNMATCHED_LOCATION
TA 512 | 30/0 | 2025-10-17 |  |  | UNMATCHED_LOCATION
TA 512 | 3/1 | 2025-10-23 |  |  | UNMATCHED_LOCATION
TA 512 | 12/0 | 2025-10-27 |  |  | UNMATCHED_LOCATION
TA 512 | 3/2 | 2025-10-28 |  |  | UNMATCHED_LOCATION
TA 512 | 31/0 | 2025-10-30 |  |  | UNMATCHED_LOCATION
TA 512 | 40/1 | 2025-10-30 |  |  | UNMATCHED_LOCATION
TA 512 | 37/1 | 2025-11-03 |  |  | UNMATCHED_LOCATION
TA 512 | 40/0 | 2025-11-10 |  |  | UNMATCHED_LOCATION
TA 512 | 16/1 | 2025-11-11 |  |  | UNMATCHED_LOCATION
TA 512 | 39/0 | 2025-11-14 |  |  | UNMATCHED_LOCATION
TA 512 | 38/2 | 2025-11-16 |  |  | UNMATCHED_LOCATION
TA 512 | 30/1 | 2025-11-18 |  |  | UNMATCHED_LOCATION
TA 512 | 29/16 | 2025-11-24 |  |  | UNMATCHED_LOCATION
TA 512 | 38/1 | 2025-11-24 |  |  | UNMATCHED_LOCATION
TA 512 | 32/0 | 2025-11-25 |  |  | UNMATCHED_LOCATION
TA 512 | 32/4 | 2025-11-28 |  |  | UNMATCHED_LOCATION
TA 512 | 3/0 | 2025-11-29 |  |  | UNMATCHED_LOCATION
TA 512 | 21/0 | 2025-12-01 |  |  | UNMATCHED_LOCATION
TA 512 | 32/1 | 2025-12-01 |  |  | UNMATCHED_LOCATION
TA 512 | 2A/5 | 2025-12-02 |  |  | UNMATCHED_LOCATION
TA 512 | 32/3 | 2025-12-02 |  |  | UNMATCHED_LOCATION
TA 512 | 32/5 | 2025-12-04 |  |  | UNMATCHED_LOCATION
TA 512 | 32/6 | 2025-12-06 |  |  | UNMATCHED_LOCATION
TA 512 | 2A/3 | 2025-12-09 |  |  | UNMATCHED_LOCATION
TA 512 | 2A/2 | 2025-12-12 |  |  | UNMATCHED_LOCATION
TA 512 | 4/2 | 2025-12-12 |  |  | UNMATCHED_LOCATION
TA 512 | 20A/0 | 2025-12-13 |  |  | UNMATCHED_LOCATION
TA 512 | 4/1 | 2025-12-14 |  |  | UNMATCHED_LOCATION
TA 512 | 2A/1 | 2025-12-16 |  |  | UNMATCHED_LOCATION
TA 512 | 32/7 | 2025-12-16 |  |  | UNMATCHED_LOCATION
TA 512 | 2A/0 | 2025-12-25 |  |  | UNMATCHED_LOCATION
TA 512 | 36/0 | 2025-12-26 |  |  | UNMATCHED_LOCATION
TA 512 | 22/0 | 2025-12-27 |  |  | UNMATCHED_LOCATION
TA 512 | 27/1 | 2025-12-27 |  |  | UNMATCHED_LOCATION
TA 512 | 36/1 | 2025-12-30 |  |  | UNMATCHED_LOCATION
TA 512 | 23/0 | 2026-01-04 |  |  | UNMATCHED_LOCATION
TA 512 | 33A/0 | 2026-01-05 |  |  | UNMATCHED_LOCATION
TA 512 | 42/0 | 2026-01-11 |  |  | UNMATCHED_LOCATION
TA 512 | 13/1 | 2026-01-12 |  |  | UNMATCHED_LOCATION
TA 512 | 34/0 | 2026-01-13 |  |  | UNMATCHED_LOCATION
TA 512 | 43/0 | 2026-01-16 |  |  | UNMATCHED_LOCATION
TA 512 | 2/0 | 2026-01-20 |  |  | UNMATCHED_LOCATION
TA 512 | 33/1 | 2026-01-31 |  |  | UNMATCHED_LOCATION
TA 512 | 10/0 | 2026-02-02 |  |  | UNMATCHED_LOCATION
TA 512 | 16/3 | 2026-02-07 |  |  | UNMATCHED_LOCATION
TA 512 | 32/8 | 2026-02-19 |  |  | UNMATCHED_LOCATION
TA 512 | 32/9 | 2026-02-22 |  |  | UNMATCHED_LOCATION
TA 512 | 33/0 | 2026-03-03 |  |  | UNMATCHED_LOCATION
TA 512 | 44/0 | 2026-03-09 |  |  | UNMATCHED_LOCATION
TA 512 | 17/0 | 2026-04-03 |  |  | UNMATCHED_LOCATION
TA 512 | 47/0 | 2026-04-08 |  |  | UNMATCHED_LOCATION
TA 512 | 18/0 | 2026-04-12 |  |  | UNMATCHED_LOCATION
TA 512 | 44/1 | 2026-04-15 |  |  | UNMATCHED_LOCATION
TA 512 | 45/0 | 2026-04-24 |  |  | UNMATCHED_LOCATION
TA 512 | 46/0 | 2026-04-24 |  |  | UNMATCHED_LOCATION
TA 512 | 34/1 | 2026-04-29 |  |  | UNMATCHED_LOCATION
TA 512 | 11/7 | 2026-05-09 |  |  | UNMATCHED_LOCATION
TA 513 | 51/2 | 2025-12-06 | 2025-05-10 | -210 | NEGATIVE_DELAY_EXCLUDED | S-P | nan
TA 513 | 24/2 | 2025-03-30 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 24/1 | 2025-04-02 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 30/2 | 2025-04-09 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 23/6 | 2025-04-12 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 23/5 | 2025-04-14 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 31/1 | 2025-04-14 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 37/1 | 2025-04-17 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 30/3 | 2025-04-21 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 30/1 | 2025-04-22 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 31/2 | 2025-04-23 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 30/2 | 2025-04-24 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 24/3 | 2025-04-26 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 52/5 | 2025-05-05 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 55/3 | 2025-05-06 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 55/7 | 2025-05-11 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 64/2 | 2025-05-11 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 64/5 | 2025-05-11 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 3/5 | 2025-05-16 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 3/6 | 2025-05-20 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 23/3 | 2025-05-21 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 3/10 | 2025-05-24 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 32B/1 | 2025-05-25 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 21/6 | 2025-05-30 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 21/7 | 2025-05-30 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 23/1 | 2025-06-03 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 23/3 | 2025-06-05 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 23/2 | 2025-06-07 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 23/4 | 2025-06-11 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 14/4 | 2025-06-20 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 18/4 | 2025-06-20 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 26/1 | 2025-06-28 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 14/3 | 2025-07-02 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 56/4 | 2025-07-05 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 14/2 | 2025-07-07 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 15B/4 | 2025-07-15 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 55/0 | 2025-07-20 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 36/3 | 2025-07-26 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 56/3 | 2025-08-19 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 36/4 | 2025-08-21 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 30/0 | 2025-09-10 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 24/0 | 2025-09-19 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 19/0 | 2025-09-25 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 28/0 | 2025-09-30 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 18/0 | 2025-10-04 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 51/4 | 2025-11-30 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 51/5 | 2025-12-19 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 52/3 | 2026-02-17 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 55/2 | 2026-03-28 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 52/2 | 2026-04-22 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 52/0 | 2026-04-24 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 55/4 | 2026-04-27 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 30/0 | 2026-05-04 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 52/1 | 2026-05-04 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 28/1 | 2026-05-17 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 64/3 | 2026-05-19 |  |  | UNMATCHED_LOCATION | S-P
TA 601 | 56/7 | 2026-01-16 | 2025-12-15 | -32 | NEGATIVE_DELAY_EXCLUDED
TA 601 | 66/0 | 2025-05-03 |  |  | UNMATCHED_LOCATION
TA 601 | 81/2 | 2025-08-07 |  |  | UNMATCHED_LOCATION
TA 601 | 80/4 | 2025-10-27 |  |  | UNMATCHED_LOCATION
TA 601 | 77/8 | 2025-11-13 |  |  | UNMATCHED_LOCATION
TA 601 | 60/3 | 2025-11-15 |  |  | UNMATCHED_LOCATION
TA 601 | 60/8 | 2025-11-23 |  |  | UNMATCHED_LOCATION
TA 601 | 59/1 | 2025-11-29 |  |  | UNMATCHED_LOCATION
TA 601 | 77/6 | 2025-12-12 |  |  | UNMATCHED_LOCATION
TA 601 | 73/1 | 2025-12-18 |  |  | UNMATCHED_LOCATION
TA 601 | 56/1 | 2025-12-24 |  |  | UNMATCHED_LOCATION
TA 601 | 73/2 | 2025-12-24 |  |  | UNMATCHED_LOCATION
TA 601 | 79/1 | 2025-12-25 |  |  | UNMATCHED_LOCATION
TA 601 | 84/6 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TA 601 | 94/1 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TA 601 | 99/12 | 2026-01-06 |  |  | UNMATCHED_LOCATION
TA 601 | 100/3 | 2026-01-14 |  |  | UNMATCHED_LOCATION
TA 601 | 83/0 | 2026-01-14 |  |  | UNMATCHED_LOCATION
TA 601 | 59/0 | 2026-01-26 |  |  | UNMATCHED_LOCATION
TA 601 | 78/3 | 2026-02-06 |  |  | UNMATCHED_LOCATION
TA 601 | 50/1 | 2026-02-12 |  |  | UNMATCHED_LOCATION
TA 601 | 50/2 | 2026-02-17 |  |  | UNMATCHED_LOCATION
TA 601 | 89/1 | 2026-03-03 |  |  | UNMATCHED_LOCATION
TA 601 | 49/10 | 2026-03-11 |  |  | UNMATCHED_LOCATION
TA 601 | 51/7 | 2026-03-13 |  |  | UNMATCHED_LOCATION
TA 601 | 49/11 | 2026-03-14 |  |  | UNMATCHED_LOCATION
TA 601 | 51/8 | 2026-03-14 |  |  | UNMATCHED_LOCATION
TA 601 | 51/10 | 2026-03-17 |  |  | UNMATCHED_LOCATION
TA 601 | 90/0 | 2026-03-18 |  |  | UNMATCHED_LOCATION
TA 601 | 51/6 | 2026-03-19 |  |  | UNMATCHED_LOCATION
TA 601 | 52/1 | 2026-03-22 |  |  | UNMATCHED_LOCATION
TA 601 | 50/3 | 2026-03-25 |  |  | UNMATCHED_LOCATION
TA 601 | 51/2 | 2026-03-27 |  |  | UNMATCHED_LOCATION
TA 601 | 53/3 | 2026-03-31 |  |  | UNMATCHED_LOCATION
TA 601 | 70/1 | 2026-04-11 |  |  | UNMATCHED_LOCATION
TA 601 | 53/0 | 2026-04-13 |  |  | UNMATCHED_LOCATION
TA 601 | 70/2 | 2026-04-13 |  |  | UNMATCHED_LOCATION
TA 601 | 50/0 | 2026-04-16 |  |  | UNMATCHED_LOCATION
TA 601 | 70/4 | 2026-04-16 |  |  | UNMATCHED_LOCATION
TA 601 | 70/3 | 2026-04-18 |  |  | UNMATCHED_LOCATION
TA 601 | 66/1 | 2026-04-21 |  |  | UNMATCHED_LOCATION
TA 601 | 49/9 | 2026-04-23 |  |  | UNMATCHED_LOCATION
TA 601 | 67/0 | 2026-04-26 |  |  | UNMATCHED_LOCATION
TA 601 | 65/3 | 2026-04-29 |  |  | UNMATCHED_LOCATION
TA 601 | 49/8 | 2026-04-30 |  |  | UNMATCHED_LOCATION
TA 601 | 67/1 | 2026-05-05 |  |  | UNMATCHED_LOCATION
TA 601 | 48/7 | 2026-05-10 |  |  | UNMATCHED_LOCATION
TA 601 | 69/0 | 2026-05-13 |  |  | UNMATCHED_LOCATION
TA 601 | 69/2 | 2026-05-16 |  |  | UNMATCHED_LOCATION
TA 601 | 48/3 | 2026-05-19 |  |  | UNMATCHED_LOCATION
TA 601 | 69/1 | 2026-05-20 |  |  | UNMATCHED_LOCATION
TA 602 | 126/5 | 2025-10-28 | 2025-03-01 | -241 | NEGATIVE_DELAY_EXCLUDED
TA 602 | 123/1 | 2025-10-07 |  |  | UNMATCHED_LOCATION
TA 602 | 124/1 | 2025-10-08 |  |  | UNMATCHED_LOCATION
TA 602 | 124/2 | 2025-10-15 |  |  | UNMATCHED_LOCATION
TA 602 | 123/3 | 2025-10-19 |  |  | UNMATCHED_LOCATION
TA 602 | 124/3 | 2025-11-04 |  |  | UNMATCHED_LOCATION
TA 602 | 123/4 | 2025-11-06 |  |  | UNMATCHED_LOCATION
TA 602 | 123/2 | 2025-11-13 |  |  | UNMATCHED_LOCATION
TA 602 | 126/10 | 2025-11-14 |  |  | UNMATCHED_LOCATION
TA 602 | 111/3 | 2025-11-19 |  |  | UNMATCHED_LOCATION
TA 602 | 103/2 | 2025-11-20 |  |  | UNMATCHED_LOCATION
TA 602 | 126/2 | 2025-11-21 |  |  | UNMATCHED_LOCATION
TA 602 | 111/4 | 2025-11-23 |  |  | UNMATCHED_LOCATION
TA 602 | 103/3 | 2025-11-24 |  |  | UNMATCHED_LOCATION
TA 602 | 103/1 | 2025-11-28 |  |  | UNMATCHED_LOCATION
TA 602 | 111/5 | 2025-11-28 |  |  | UNMATCHED_LOCATION
TA 602 | 110/2 | 2025-11-30 |  |  | UNMATCHED_LOCATION
TA 602 | 121/5 | 2025-11-30 |  |  | UNMATCHED_LOCATION
TA 602 | 110/1 | 2025-12-03 |  |  | UNMATCHED_LOCATION
TA 602 | 134/6 | 2025-12-06 |  |  | UNMATCHED_LOCATION
TA 602 | 99/1 | 2025-12-06 |  |  | UNMATCHED_LOCATION
TA 602 | 102/9 | 2025-12-07 |  |  | UNMATCHED_LOCATION
TA 602 | 109/10 | 2025-12-07 |  |  | UNMATCHED_LOCATION
TA 602 | 110/3 | 2025-12-11 |  |  | UNMATCHED_LOCATION
TA 602 | 109/11 | 2025-12-12 |  |  | UNMATCHED_LOCATION
TA 602 | 136/7 | 2025-12-12 |  |  | UNMATCHED_LOCATION
TA 602 | 99/2 | 2025-12-13 |  |  | UNMATCHED_LOCATION
TA 602 | 102/8 | 2025-12-15 |  |  | UNMATCHED_LOCATION
TA 602 | 108/7 | 2025-12-16 |  |  | UNMATCHED_LOCATION
TA 602 | 110/4 | 2025-12-19 |  |  | UNMATCHED_LOCATION
TA 602 | 136/9 | 2025-12-19 |  |  | UNMATCHED_LOCATION
TA 602 | 109/7 | 2025-12-20 |  |  | UNMATCHED_LOCATION
TA 602 | 108/5 | 2025-12-22 |  |  | UNMATCHED_LOCATION
TA 602 | 136/6 | 2025-12-22 |  |  | UNMATCHED_LOCATION
TA 602 | 109/9 | 2025-12-24 |  |  | UNMATCHED_LOCATION
TA 602 | 139/3 | 2025-12-24 |  |  | UNMATCHED_LOCATION
TA 602 | 89/9 | 2025-12-24 |  |  | UNMATCHED_LOCATION
TA 602 | 107/2 | 2025-12-26 |  |  | UNMATCHED_LOCATION
TA 602 | 108/6 | 2025-12-26 |  |  | UNMATCHED_LOCATION
TA 602 | 109/6 | 2025-12-27 |  |  | UNMATCHED_LOCATION
TA 602 | 89/8 | 2025-12-28 |  |  | UNMATCHED_LOCATION
TA 602 | 109/5 | 2025-12-30 |  |  | UNMATCHED_LOCATION
TA 602 | 89/7 | 2025-12-30 |  |  | UNMATCHED_LOCATION
TA 602 | 107/1 | 2026-01-03 |  |  | UNMATCHED_LOCATION
TA 602 | 89/6 | 2026-01-04 |  |  | UNMATCHED_LOCATION
TA 602 | 129A/1 | 2026-01-07 |  |  | UNMATCHED_LOCATION
TA 602 | 89/5 | 2026-01-10 |  |  | UNMATCHED_LOCATION
TA 602 | 108/4 | 2026-01-11 |  |  | UNMATCHED_LOCATION
TA 602 | 129A/5 | 2026-01-11 |  |  | UNMATCHED_LOCATION
TA 602 | 108/1 | 2026-01-17 |  |  | UNMATCHED_LOCATION
TA 602 | 76/2 | 2026-01-20 |  |  | UNMATCHED_LOCATION
TA 602 | 77/1 | 2026-01-24 |  |  | UNMATCHED_LOCATION
TA 602 | 107/4 | 2026-01-25 |  |  | UNMATCHED_LOCATION
TA 602 | 129A/7 | 2026-01-27 |  |  | UNMATCHED_LOCATION
TA 602 | 76/1 | 2026-01-27 |  |  | UNMATCHED_LOCATION
TA 602 | 139/6 | 2026-01-28 |  |  | UNMATCHED_LOCATION
TA 602 | 127/7 | 2026-01-30 |  |  | UNMATCHED_LOCATION
TA 602 | 129A/2 | 2026-01-30 |  |  | UNMATCHED_LOCATION
TA 602 | 76/6 | 2026-01-31 |  |  | UNMATCHED_LOCATION
TA 602 | 82/2 | 2026-02-02 |  |  | UNMATCHED_LOCATION
TA 602 | 127/4 | 2026-02-03 |  |  | UNMATCHED_LOCATION
TA 602 | 129A/10 | 2026-02-05 |  |  | UNMATCHED_LOCATION
TA 602 | 82/3 | 2026-02-08 |  |  | UNMATCHED_LOCATION
TA 602 | 127/1 | 2026-02-09 |  |  | UNMATCHED_LOCATION
TA 602 | 127/2 | 2026-02-13 |  |  | UNMATCHED_LOCATION
TA 602 | 70/3 | 2026-02-13 |  |  | UNMATCHED_LOCATION
TA 602 | 129A/6 | 2026-02-16 |  |  | UNMATCHED_LOCATION
TA 602 | 121/10 | 2026-02-17 |  |  | UNMATCHED_LOCATION
TA 602 | 70/1 | 2026-02-23 |  |  | UNMATCHED_LOCATION
TA 602 | 125/1 | 2026-02-28 |  |  | UNMATCHED_LOCATION
TA 602 | 126/7 | 2026-03-03 |  |  | UNMATCHED_LOCATION
TA 602 | 70/2 | 2026-03-07 |  |  | UNMATCHED_LOCATION
TA 602 | 124/5 | 2026-03-14 |  |  | UNMATCHED_LOCATION
TA 602 | 76/5 | 2026-03-21 |  |  | UNMATCHED_LOCATION
TA 602 | 88/2 | 2026-03-30 |  |  | UNMATCHED_LOCATION
TA 602 | 88/1 | 2026-04-02 |  |  | UNMATCHED_LOCATION
TA 602 | 127/3 | 2026-04-03 |  |  | UNMATCHED_LOCATION
TA 602 | 124/0 | 2026-04-08 |  |  | UNMATCHED_LOCATION
TA 602 | 87/4 | 2026-04-08 |  |  | UNMATCHED_LOCATION
TA 602 | 102/11 | 2026-04-11 |  |  | UNMATCHED_LOCATION
TA 602 | 139/4 | 2026-04-11 |  |  | UNMATCHED_LOCATION
TA 602 | 69/2 | 2026-04-13 |  |  | UNMATCHED_LOCATION
TA 602 | 87/5 | 2026-04-14 |  |  | UNMATCHED_LOCATION
TA 602 | 121/9 | 2026-04-15 |  |  | UNMATCHED_LOCATION
TA 602 | 71/1 | 2026-04-18 |  |  | UNMATCHED_LOCATION
TA 602 | 87/2 | 2026-04-18 |  |  | UNMATCHED_LOCATION
TA 602 | 69/1 | 2026-04-21 |  |  | UNMATCHED_LOCATION
TA 602 | 109/8 | 2026-04-22 |  |  | UNMATCHED_LOCATION
TA 602 | 125/0 | 2026-04-23 |  |  | UNMATCHED_LOCATION
TA 602 | 136/0 | 2026-04-24 |  |  | UNMATCHED_LOCATION
TA 602 | 71/2 | 2026-04-24 |  |  | UNMATCHED_LOCATION
TA 602 | 87/3 | 2026-04-25 |  |  | UNMATCHED_LOCATION
TA 602 | 69/3 | 2026-04-28 |  |  | UNMATCHED_LOCATION
TA 602 | 127/0 | 2026-04-30 |  |  | UNMATCHED_LOCATION
TA 602 | 139/0 | 2026-04-30 |  |  | UNMATCHED_LOCATION
TA 602 | 71/3 | 2026-04-30 |  |  | UNMATCHED_LOCATION
TA 602 | 88/3 | 2026-04-30 |  |  | UNMATCHED_LOCATION
TA 602 | 108/0 | 2026-05-04 |  |  | UNMATCHED_LOCATION
TA 602 | 139/1 | 2026-05-04 |  |  | UNMATCHED_LOCATION
TA 602 | 71/4 | 2026-05-04 |  |  | UNMATCHED_LOCATION
TA 602 | 107/0 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TA 602 | 69/4 | 2026-05-08 |  |  | UNMATCHED_LOCATION
TA 602 | 126/0 | 2026-05-12 |  |  | UNMATCHED_LOCATION
TA 602 | 88/0 | 2026-05-15 |  |  | UNMATCHED_LOCATION
TB 501 | 8D/0A | 2025-12-07 | 2025-12-04 | -3 | NEGATIVE_DELAY_EXCLUDED | 220kV | 220kV
TB 501 | 6/0 | 2026-02-19 | 2026-02-17 | -2 | NEGATIVE_DELAY_EXCLUDED | 132kV | 132kV
TB 501 | 34/0 (New) | 2026-04-30 |  |  | UNMATCHED_LOCATION | 220kV
TB 507 | 71/2 | 2025-10-30 | 2025-01-14 | -289 | NEGATIVE_DELAY_EXCLUDED | MAIN | MAIN
TB 507 | 86/2 | 2025-02-22 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 66/2 | 2025-03-06 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 64/3 | 2025-03-07 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 96/2 | 2025-03-07 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 64/4 | 2025-03-10 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 99/1 | 2025-03-10 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 66/3 | 2025-03-11 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 87/1 | 2025-03-24 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 64/6 | 2025-03-30 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 87/2 | 2025-03-30 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 64/5 | 2025-03-31 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 71/1 | 2025-04-09 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 91/2 | 2025-04-16 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 51/2 | 2025-04-17 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 95/2 | 2025-04-20 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 51/3 | 2025-04-23 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 99/2 | 2025-04-25 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 104B/1 | 2025-04-29 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 62/4 | 2025-04-29 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 100/1 | 2025-05-18 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 99C/2 | 2025-05-25 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 105/0 | 2025-05-28 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 62/5 | 2025-05-31 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 96/0 | 2025-06-06 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 119/0 | 2025-06-15 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 74/0 | 2025-06-20 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 106/0 | 2025-07-06 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 125/1 | 2025-07-14 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 125/0 | 2025-07-24 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 94/0 | 2025-07-24 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 99/3 | 2025-07-29 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 102/1 | 2025-08-14 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 99/0 | 2025-08-14 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 87/0 | 2025-08-22 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 99/4 | 2025-08-22 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 63/1 | 2025-08-24 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 56/4 | 2025-08-26 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 56/2 | 2025-08-27 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 56/5 | 2025-08-31 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 99A/0 | 2025-08-31 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 57/0 | 2025-09-10 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 59/0 | 2025-09-12 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 64/0 | 2025-09-14 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 58/0 | 2025-09-17 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 125/2 | 2025-09-18 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 72/1 | 2025-09-19 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 56/1 | 2025-09-20 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 48/0 | 2025-09-25 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 89/0 | 2025-11-12 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 71/0 | 2025-11-14 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 88/0 | 2025-12-05 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 98B/2 | 2025-12-08 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 117/0 | 2025-12-13 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 91/0 | 2025-12-24 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 104A/0 | 2025-12-30 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 124/0 | 2025-12-30 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 104B/0 | 2026-01-04 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 122/2 | 2026-01-08 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 126/3 | 2026-01-15 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 69/3 | 2026-01-15 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 108/0 | 2026-01-20 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 10/3 | 2026-01-23 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 109/0 | 2026-01-23 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 120/0 | 2026-01-25 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 7/0 | 2026-02-11 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 10/12 | 2026-02-12 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 6/2 | 2026-02-16 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 6/1 | 2026-02-20 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 1/0 | 2026-02-28 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 117/2 | 2026-02-28 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 4/0 | 2026-02-28 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 6/0 | 2026-02-28 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 157/0 | 2026-03-04 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 156/0 | 2026-03-10 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 98B/1 | 2026-03-11 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 2/0 | 2026-03-13 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 2/2 | 2026-03-15 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 2/3 | 2026-03-16 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 2/4 | 2026-03-17 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 103/0 | 2026-03-19 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 3/0B | 2026-03-26 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 2/5 | 2026-03-27 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 3/0A | 2026-03-28 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5/2 | 2026-03-31 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5/1 | 2026-04-02 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 3/1 | 2026-04-04 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 3/1 | 2026-04-07 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 2/1B | 2026-04-08 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 2/1 A | 2026-04-09 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 103/1 | 2026-04-10 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 8/0 | 2026-04-11 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5/0 | 2026-04-12 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 99C/0 | 2026-04-15 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 4/5 | 2026-04-16 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 3/3 | 2026-04-18 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 3/2 | 2026-04-21 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 100/0 | 2026-04-24 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 10/11 | 2026-04-28 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 3/4 | 2026-04-29 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 10/0 | 2026-05-02 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 2/0 | 2026-05-02 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 155/0 | 2026-05-03 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 3/5 | 2026-05-05 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 154/1B | 2026-05-06 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 10/13 | 2026-05-08 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 154/2B | 2026-05-08 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 4/2 | 2026-05-08 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 154/1A | 2026-05-09 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 154/2A | 2026-05-09 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 4/4 | 2026-05-10 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 7/6 | 2026-05-11 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 13/2 | 2026-05-14 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 4/0 | 2026-05-15 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 7/8 | 2026-05-16 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 8/3 | 2026-05-17 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 4/1 | 2026-05-18 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 4/3 | 2026-05-19 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 8/4 | 2026-05-19 |  |  | UNMATCHED_LOCATION | MAIN
TB 605 | 18/0 | 2025-10-16 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 22/1 | 2025-10-28 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 21/1 | 2025-10-31 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 22/0 | 2025-10-31 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 74/0 | 2025-11-06 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 72/0 | 2025-11-09 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 22/2 | 2025-11-13 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | AP90 | 2025-11-22 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 17/0 | 2025-11-23 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 20/0 | 2025-11-30 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | AP116 | 2025-11-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP87 | 2025-11-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 40/0 | 2025-12-03 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | AP28 | 2025-12-04 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 23/0 | 2025-12-09 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 29/0 | 2025-12-10 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 85/1 | 2025-12-16 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 106/1 | 2025-12-17 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 102/1 | 2025-12-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 135/2 | 2025-12-21 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 139/1 | 2025-12-24 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 138/1 | 2025-12-26 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 80/1 | 2025-12-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 138/2 | 2025-12-31 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 137/2 | 2026-01-10 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP131 | 2026-01-11 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 152/2 | 2026-01-16 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP154 | 2026-01-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP138 | 2026-01-20 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 153/0 | 2026-02-05 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP139 | 2026-02-06 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP15 | 2026-02-08 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | AP155 | 2026-02-09 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP130 | 2026-02-12 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP92 | 2026-02-13 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 153/2 | 2026-02-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP150 | 2026-02-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 136/4 | 2026-02-20 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP12 | 2026-02-20 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | AP132 | 2026-02-24 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 70/1 | 2026-02-26 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP137 | 2026-02-27 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP21 | 2026-02-27 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | AP91 | 2026-02-27 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP159 | 2026-02-28 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP14 | 2026-03-08 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | AP149 | 2026-03-10 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 67/2 | 2026-03-13 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP127 | 2026-03-15 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP148 | 2026-03-16 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP136 | 2026-03-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP71 | 2026-03-23 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP152 | 2026-03-26 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP108 | 2026-03-28 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP124 | 2026-03-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP67 | 2026-03-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 152/3 | 2026-03-31 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 56/3 | 2026-03-31 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP125 | 2026-04-06 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 144/3 | 2026-04-07 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 65/2 | 2026-04-07 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP109 | 2026-04-12 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP126 | 2026-04-15 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP1 | 2026-04-18 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | AP61 | 2026-04-21 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP165 | 2026-04-22 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP86 | 2026-04-23 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 56/2 | 2026-04-25 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP123 | 2026-04-26 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP59 | 2026-04-27 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 55/1 | 2026-04-28 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP142 | 2026-04-29 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP7 | 2026-04-29 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 122/1 | 2026-04-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP166 | 2026-04-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP41 | 2026-04-30 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | AP6 | 2026-04-30 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | AP64 | 2026-05-01 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 33/1 | 2026-05-07 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 64/1 | 2026-05-07 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP144 | 2026-05-07 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP56 | 2026-05-07 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 142/1 | 2026-05-08 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 61/1 | 2026-05-08 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP82 | 2026-05-08 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 57/1 | 2026-05-09 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP161 | 2026-05-09 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP163 | 2026-05-11 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 56/4 | 2026-05-13 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 62/2 | 2026-05-14 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 71/1 | 2026-05-14 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP110 | 2026-05-14 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP38 | 2026-05-14 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | AP57 | 2026-05-15 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 159/3 | 2026-05-16 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 40/3 | 2026-05-16 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 65/4 | 2026-05-16 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 50A/2 | 2026-05-17 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | AP162 | 2026-05-17 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP60 | 2026-05-17 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 62/1 | 2026-05-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP128 | 2026-05-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP143 | 2026-05-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP63 | 2026-05-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 159/2 | 2026-05-19 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 23/2 | 2026-05-19 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 57/2 | 2026-05-19 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP112 | 2026-05-19 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP70/3 | 2026-05-19 |  |  | UNMATCHED_LOCATION | Punjab
TB 608 | 65/3 | 2025-10-18 |  |  | UNMATCHED_LOCATION
TB 608 | 69/0 | 2025-11-10 |  |  | UNMATCHED_LOCATION
TB 608 | 58/0 | 2025-11-11 |  |  | UNMATCHED_LOCATION
TB 608 | 75/5 | 2025-11-15 |  |  | UNMATCHED_LOCATION
TB 608 | 34/3 | 2025-11-18 |  |  | UNMATCHED_LOCATION
TB 608 | 101/0 | 2025-11-19 |  |  | UNMATCHED_LOCATION
TB 608 | 33/2 | 2025-11-22 |  |  | UNMATCHED_LOCATION
TB 608 | 90/0 | 2025-11-22 |  |  | UNMATCHED_LOCATION
TB 608 | 29/0 | 2025-11-25 |  |  | UNMATCHED_LOCATION
TB 608 | 100/0 | 2025-11-30 |  |  | UNMATCHED_LOCATION
TB 608 | 103/0 | 2025-11-30 |  |  | UNMATCHED_LOCATION
TB 608 | 109/0 | 2025-11-30 |  |  | UNMATCHED_LOCATION
TB 608 | 71/0 | 2025-11-30 |  |  | UNMATCHED_LOCATION
TB 608 | 85/0 | 2025-11-30 |  |  | UNMATCHED_LOCATION
TB 608 | 89/0 | 2025-11-30 |  |  | UNMATCHED_LOCATION
TB 608 | 29/1 | 2025-12-02 |  |  | UNMATCHED_LOCATION
TB 608 | 69/3 | 2025-12-08 |  |  | UNMATCHED_LOCATION
TB 608 | 5/0 | 2025-12-10 |  |  | UNMATCHED_LOCATION
TB 608 | 80/0 | 2025-12-11 |  |  | UNMATCHED_LOCATION
TB 608 | 108/0 | 2025-12-12 |  |  | UNMATCHED_LOCATION
TB 608 | 111/0 | 2025-12-12 |  |  | UNMATCHED_LOCATION
TB 608 | 48/0 | 2025-12-14 |  |  | UNMATCHED_LOCATION
TB 608 | 75/4 | 2025-12-18 |  |  | UNMATCHED_LOCATION
TB 608 | 99/0 | 2025-12-18 |  |  | UNMATCHED_LOCATION
TB 608 | 102/0 | 2025-12-19 |  |  | UNMATCHED_LOCATION
TB 608 | 84/0 | 2025-12-19 |  |  | UNMATCHED_LOCATION
TB 608 | 111/1 | 2025-12-21 |  |  | UNMATCHED_LOCATION
TB 608 | 83/0 | 2025-12-21 |  |  | UNMATCHED_LOCATION
TB 608 | 91/0 | 2025-12-21 |  |  | UNMATCHED_LOCATION
TB 608 | 93/0 | 2025-12-21 |  |  | UNMATCHED_LOCATION
TB 608 | 34/1 | 2025-12-22 |  |  | UNMATCHED_LOCATION
TB 608 | 25/1 | 2025-12-23 |  |  | UNMATCHED_LOCATION
TB 608 | 4/1 | 2025-12-25 |  |  | UNMATCHED_LOCATION
TB 608 | 112/0 | 2025-12-27 |  |  | UNMATCHED_LOCATION
TB 608 | 49/0 | 2025-12-27 |  |  | UNMATCHED_LOCATION
TB 608 | 91/1 | 2025-12-27 |  |  | UNMATCHED_LOCATION
TB 608 | 79/1 | 2025-12-28 |  |  | UNMATCHED_LOCATION
TB 608 | 91/2 | 2025-12-28 |  |  | UNMATCHED_LOCATION
TB 608 | 114/0 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TB 608 | 86/0 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TB 608 | 94/0 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TB 608 | 41/2 | 2026-01-02 |  |  | UNMATCHED_LOCATION
TB 608 | 11/2 | 2026-01-03 |  |  | UNMATCHED_LOCATION
TB 608 | 70/0 | 2026-01-04 |  |  | UNMATCHED_LOCATION
TB 608 | 97/0 | 2026-01-09 |  |  | UNMATCHED_LOCATION
TB 608 | 113/0 | 2026-01-11 |  |  | UNMATCHED_LOCATION
TB 608 | 91/5 | 2026-01-12 |  |  | UNMATCHED_LOCATION
TB 608 | 110/0 | 2026-01-13 |  |  | UNMATCHED_LOCATION
TB 608 | 115/0 | 2026-01-14 |  |  | UNMATCHED_LOCATION
TB 608 | 8/0 | 2026-01-14 |  |  | UNMATCHED_LOCATION
TB 608 | 76/0 | 2026-01-15 |  |  | UNMATCHED_LOCATION
TB 608 | 69/4 | 2026-01-18 |  |  | UNMATCHED_LOCATION
TB 608 | 75/1 | 2026-01-19 |  |  | UNMATCHED_LOCATION
TB 608 | 50/0 | 2026-01-21 |  |  | UNMATCHED_LOCATION
TB 608 | 11/1 | 2026-01-24 |  |  | UNMATCHED_LOCATION
TB 608 | 123/2 | 2026-01-25 |  |  | UNMATCHED_LOCATION
TB 608 | 129/1 | 2026-01-27 |  |  | UNMATCHED_LOCATION
TB 608 | 34/2 | 2026-01-27 |  |  | UNMATCHED_LOCATION
TB 608 | 47/1 | 2026-01-28 |  |  | UNMATCHED_LOCATION
TB 608 | 79/0 | 2026-01-28 |  |  | UNMATCHED_LOCATION
TB 608 | 132/1 | 2026-01-29 |  |  | UNMATCHED_LOCATION
TB 608 | 91/7 | 2026-01-29 |  |  | UNMATCHED_LOCATION
TB 608 | 96/0 | 2026-01-30 |  |  | UNMATCHED_LOCATION
TB 608 | 128/0 | 2026-01-31 |  |  | UNMATCHED_LOCATION
TB 608 | 131/0 | 2026-01-31 |  |  | UNMATCHED_LOCATION
TB 608 | 75/2 | 2026-01-31 |  |  | UNMATCHED_LOCATION
TB 608 | 91/4 | 2026-01-31 |  |  | UNMATCHED_LOCATION
TB 608 | 59/1 | 2026-02-05 |  |  | UNMATCHED_LOCATION
TB 608 | 73/6 | 2026-02-05 |  |  | UNMATCHED_LOCATION
TB 608 | 76/1 | 2026-02-05 |  |  | UNMATCHED_LOCATION
TB 608 | 96/1 | 2026-02-05 |  |  | UNMATCHED_LOCATION
TB 608 | 104/0 | 2026-02-08 |  |  | UNMATCHED_LOCATION
TB 608 | 42/1 | 2026-02-08 |  |  | UNMATCHED_LOCATION
TB 608 | 126/0 | 2026-02-10 |  |  | UNMATCHED_LOCATION
TB 608 | 43/0 | 2026-02-10 |  |  | UNMATCHED_LOCATION
TB 608 | 72/7 | 2026-02-11 |  |  | UNMATCHED_LOCATION
TB 608 | 9/1 | 2026-02-11 |  |  | UNMATCHED_LOCATION
TB 608 | 78/2 | 2026-02-12 |  |  | UNMATCHED_LOCATION
TB 608 | 95/3 | 2026-02-14 |  |  | UNMATCHED_LOCATION
TB 608 | 95/1 | 2026-02-16 |  |  | UNMATCHED_LOCATION
TB 608 | 131/3 | 2026-02-17 |  |  | UNMATCHED_LOCATION
TB 608 | 129/2 | 2026-02-18 |  |  | UNMATCHED_LOCATION
TB 608 | 6/1 | 2026-02-18 |  |  | UNMATCHED_LOCATION
TB 608 | 95/0 | 2026-02-18 |  |  | UNMATCHED_LOCATION
TB 608 | 131/1 | 2026-02-19 |  |  | UNMATCHED_LOCATION
TB 608 | 44/0 | 2026-02-19 |  |  | UNMATCHED_LOCATION
TB 608 | 30/0 | 2026-02-20 |  |  | UNMATCHED_LOCATION
TB 608 | 10/3 | 2026-02-22 |  |  | UNMATCHED_LOCATION
TB 608 | 124/0 | 2026-02-22 |  |  | UNMATCHED_LOCATION
TB 608 | 70/1 | 2026-02-23 |  |  | UNMATCHED_LOCATION
TB 608 | 127/0 | 2026-02-25 |  |  | UNMATCHED_LOCATION
TB 608 | 132/2 | 2026-02-28 |  |  | UNMATCHED_LOCATION
TB 608 | 132/3 | 2026-02-28 |  |  | UNMATCHED_LOCATION
TB 608 | 95/2 | 2026-02-28 |  |  | UNMATCHED_LOCATION
TB 608 | 31/0 | 2026-03-06 |  |  | UNMATCHED_LOCATION
TB 608 | 35/0 | 2026-03-08 |  |  | UNMATCHED_LOCATION
TB 608 | 10/1 | 2026-03-10 |  |  | UNMATCHED_LOCATION
TB 608 | 129/0 | 2026-03-10 |  |  | UNMATCHED_LOCATION
TB 608 | 130/0 | 2026-03-10 |  |  | UNMATCHED_LOCATION
TB 608 | 82/2 | 2026-03-10 |  |  | UNMATCHED_LOCATION
TB 608 | 82/1 | 2026-03-11 |  |  | UNMATCHED_LOCATION
TB 608 | 116/0 | 2026-03-12 |  |  | UNMATCHED_LOCATION
TB 608 | 27/0 | 2026-03-14 |  |  | UNMATCHED_LOCATION
TB 608 | 125/0 | 2026-03-19 |  |  | UNMATCHED_LOCATION
TB 608 | 47/0 | 2026-03-28 |  |  | UNMATCHED_LOCATION
TB 608 | 132/0 | 2026-03-29 |  |  | UNMATCHED_LOCATION
TB 608 | 34/0 | 2026-03-31 |  |  | UNMATCHED_LOCATION
TB 608 | 7/2 | 2026-03-31 |  |  | UNMATCHED_LOCATION
TB 608 | 92/0 | 2026-04-13 |  |  | UNMATCHED_LOCATION
TB 608 | 107/1 | 2026-04-19 |  |  | UNMATCHED_LOCATION

## Delay Phase - Project
Delay Phase - Project
Project | Phase | Foundation Bucket Start % | Foundation Bucket End % | Foundation Count | Matched Count | Match % | Median Delay Days | Average Delay Days | P90 Delay Days | Negative Excluded | Unmatched | Scope Total | Phase Foundations % of Scope | Phase Start Date | Phase End Date | Phase Duration Days | Monsoon Overlap | Monsoon Overlap Days | Monsoon Foundation Count | Source Type | Parser Modes | Coverage Status | Scope Source | Scope Report Date
TA 413 | 0-20 | 0 | 20 | 126 | 120 | 95.24 | 312 | 273.4833 | 438.1 | 0 | 6 | 632 | 19.94 | 2024-06-06 | 2024-10-25 | 142 | Yes | 117 | 97 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 413 | 20-40 | 20 | 40 | 126 | 124 | 98.41 | 193 | 180.3171 | 306 | 1 | 2 | 632 | 19.94 | 2024-10-25 | 2025-02-26 | 125 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 413 | 40-60 | 40 | 60 | 62 | 60 | 96.77 | 163 | 163.3559 | 220.8 | 1 | 2 | 632 | 9.81 | 2025-02-27 | 2026-03-05 | 372 | Yes | 122 | 6 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 414 | 0-20 | 0 | 20 | 70 | 62 | 88.57 | 346 | 352.4754 | 452 | 1 | 8 | 352 | 19.89 | 2024-05-15 | 2025-03-24 | 314 | Yes | 122 | 2 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-21
TA 414 | 20-40 | 20 | 40 | 70 | 61 | 87.14 | 132 | 162.3279 | 301 | 0 | 9 | 352 | 19.89 | 2025-03-24 | 2025-11-27 | 249 | Yes | 122 | 6 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-21
TA 414 | 40-60 | 40 | 60 | 71 | 53 | 74.65 | 54 | 59.5094 | 99.6 | 0 | 18 | 352 | 20.17 | 2025-11-27 | 2025-12-28 | 32 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-21
TA 414 | 60-80 | 60 | 80 | 70 | 41 | 58.57 | 54 | 55.35 | 86 | 1 | 29 | 352 | 19.89 | 2025-12-29 | 2026-02-25 | 59 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-21
TA 414 | 80-100+ | 80 | 100 | 46 | 8 | 17.39 | 28.5 | 25.875 | 35 | 0 | 38 | 352 | 13.07 | 2026-03-01 | 2026-05-20 | 81 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-21
TA 416 | 0-20 | 0 | 20 | 60 | 60 | 100 | 171 | 184.65 | 288.1 | 0 | 0 | 302 | 19.87 | 2024-04-24 | 2024-09-08 | 138 | Yes | 100 | 51 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-17
TA 416 | 20-40 | 20 | 40 | 60 | 60 | 100 | 154 | 158.9833 | 244.6 | 0 | 0 | 302 | 19.87 | 2024-09-09 | 2024-10-22 | 44 | Yes | 22 | 21 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-17
TA 416 | 40-60 | 40 | 60 | 61 | 61 | 100 | 118 | 123.1639 | 190 | 0 | 0 | 302 | 20.2 | 2024-10-24 | 2024-11-30 | 38 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-17
TA 416 | 60-80 | 60 | 80 | 60 | 60 | 100 | 150.5 | 168.6167 | 287.2 | 0 | 0 | 302 | 19.87 | 2024-11-30 | 2025-01-26 | 58 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-17
TA 416 | 80-100+ | 80 | 100 | 62 | 62 | 100 | 161.5 | 165.3065 | 258.8 | 0 | 0 | 302 | 20.53 | 2025-01-30 | 2025-12-05 | 310 | Yes | 122 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-17
TA 418 | 0-20 | 0 | 20 | 25 | 24 | 96 | 167.5 | 168.0417 | 260.2 | 0 | 1 | 127 | 19.69 | 2024-01-07 | 2024-09-02 | 240 | Yes | 94 | 23 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-21
TA 418 | 20-40 | 20 | 40 | 25 | 24 | 96 | 106.5 | 136.5 | 226 | 0 | 1 | 127 | 19.69 | 2024-09-05 | 2025-01-03 | 121 | Yes | 26 | 7 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-21
TA 418 | 40-60 | 40 | 60 | 26 | 26 | 100 | 139.5 | 142.1538 | 244 | 0 | 0 | 127 | 20.47 | 2025-01-10 | 2025-04-15 | 96 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-21
TA 418 | 60-80 | 60 | 80 | 25 | 25 | 100 | 97 | 107.48 | 213.6 | 0 | 0 | 127 | 19.69 | 2025-04-16 | 2025-06-24 | 70 | Yes | 24 | 16 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-21
TA 418 | 80-100+ | 80 | 100 | 28 | 26 | 92.86 | 84 | 94.7308 | 176.5 | 0 | 2 | 127 | 22.05 | 2025-06-25 | 2026-02-11 | 232 | Yes | 98 | 15 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-21
TA 419 | 0-20 | 0 | 20 | 66 | 66 | 100 | 196 | 214.5231 | 370.4 | 1 | 0 | 330 | 20 | 2024-05-21 | 2024-10-11 | 144 | Yes | 122 | 53 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 419 | 20-40 | 20 | 40 | 66 | 63 | 95.45 | 235 | 214.2698 | 313.4 | 0 | 3 | 330 | 20 | 2024-10-14 | 2025-04-23 | 192 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 419 | 40-60 | 40 | 60 | 66 | 58 | 87.88 | 80 | 107.3684 | 210.8 | 1 | 8 | 330 | 20 | 2025-04-25 | 2025-12-10 | 230 | Yes | 122 | 20 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 419 | 60-80 | 60 | 80 | 66 | 29 | 43.94 | 40 | 59.5172 | 108.6 | 0 | 37 | 330 | 20 | 2025-12-10 | 2026-05-13 | 155 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 419 | 80-100+ | 80 | 100 | 4 | 0 | 0 |  |  |  | 0 | 4 | 330 | 1.21 | 2026-05-16 | 2026-05-17 | 2 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 421 | 0-20 | 0 | 20 | 61 | 61 | 100 | 110 | 131.3443 | 244 | 0 | 0 | 309 | 19.74 | 2024-01-02 | 2024-08-20 | 232 | Yes | 81 | 50 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 421 | 20-40 | 20 | 40 | 62 | 62 | 100 | 118.5 | 145.5323 | 310.9 | 0 | 0 | 309 | 20.06 | 2024-08-24 | 2024-12-09 | 108 | Yes | 38 | 16 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 421 | 40-60 | 40 | 60 | 62 | 62 | 100 | 103 | 125.629 | 283.5 | 0 | 0 | 309 | 20.06 | 2024-12-09 | 2025-02-01 | 55 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 421 | 60-80 | 60 | 80 | 62 | 61 | 98.39 | 145 | 136.4262 | 225 | 0 | 1 | 309 | 20.06 | 2025-02-01 | 2025-04-19 | 78 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 421 | 80-100+ | 80 | 100 | 56 | 55 | 98.21 | 147 | 146.5273 | 206.2 | 0 | 1 | 309 | 18.12 | 2025-04-19 | 2025-12-06 | 232 | Yes | 122 | 27 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 505 | 0-20 | 0 | 20 | 75 | 74 | 98.67 | 142 | 179.5 | 309.1 | 0 | 1 | 379 | 19.79 | 2015-11-27 | 2024-12-31 | 3323 | Yes | 1098 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 505 | 20-40 | 20 | 40 | 76 | 76 | 100 | 222 | 222.5921 | 362.5 | 0 | 0 | 379 | 20.05 | 2025-01-02 | 2025-03-29 | 87 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 505 | 40-60 | 40 | 60 | 76 | 76 | 100 | 212.5 | 220.2763 | 349.5 | 0 | 0 | 379 | 20.05 | 2025-03-30 | 2025-05-16 | 48 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 505 | 60-80 | 60 | 80 | 76 | 76 | 100 | 122.5 | 144.5132 | 289.5 | 0 | 0 | 379 | 20.05 | 2025-05-16 | 2025-11-18 | 187 | Yes | 122 | 28 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 505 | 80-100+ | 80 | 100 | 70 | 54 | 77.14 | 17 | 22.3962 | 46.6 | 1 | 16 | 379 | 18.47 | 2025-11-19 | 2026-05-18 | 181 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 509 | 0-20 | 0 | 20 | 61 | 58 | 95.08 | 266 | 276.5172 | 382.1 | 0 | 3 | 309 | 19.74 | 2025-01-01 | 2025-04-01 | 91 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 509 | 20-40 | 20 | 40 | 62 | 51 | 82.26 | 339 | 309.8431 | 386 | 0 | 11 | 309 | 20.06 | 2025-04-01 | 2025-05-16 | 46 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 509 | 40-60 | 40 | 60 | 62 | 48 | 77.42 | 228.5 | 223.25 | 313.3 | 0 | 14 | 309 | 20.06 | 2025-05-17 | 2025-10-25 | 162 | Yes | 122 | 33 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 509 | 60-80 | 60 | 80 | 62 | 46 | 74.19 | 86.5 | 95.3696 | 163 | 0 | 16 | 309 | 20.06 | 2025-10-26 | 2026-04-05 | 162 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 509 | 80-100+ | 80 | 100 | 17 | 1 | 5.88 | 12 | 12 | 12 | 0 | 16 | 309 | 5.5 | 2026-04-05 | 2026-05-14 | 40 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 510 | 0-20 | 0 | 20 | 58 | 31 | 53.45 | 102 | 143.4516 | 290 | 0 | 27 | 293 | 19.8 | 2025-02-12 | 2026-02-01 | 355 | Yes | 122 | 8 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-20
TA 510 | 20-40 | 20 | 40 | 27 | 3 | 11.11 | 57 | 57 | 86.6 | 0 | 24 | 293 | 9.22 | 2026-02-02 | 2026-05-20 | 108 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-20
TA 512 | 0-20 | 0 | 20 | 63 | 62 | 98.41 | 219 | 216.7581 | 302.6 | 0 | 1 | 315 | 20 | 2025-02-23 | 2025-05-15 | 82 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-20
TA 512 | 20-40 | 20 | 40 | 63 | 56 | 88.89 | 208 | 198.3036 | 251 | 0 | 7 | 315 | 20 | 2025-05-17 | 2025-07-20 | 65 | Yes | 50 | 50 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-20
TA 512 | 40-60 | 40 | 60 | 63 | 48 | 76.19 | 154.5 | 154.1458 | 214.8 | 0 | 15 | 315 | 20 | 2025-07-21 | 2025-10-12 | 84 | Yes | 72 | 57 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-20
TA 512 | 60-80 | 60 | 80 | 63 | 36 | 57.14 | 99 | 97.6111 | 150 | 0 | 27 | 315 | 20 | 2025-10-12 | 2025-12-13 | 63 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-20
TA 512 | 80-100+ | 80 | 100 | 45 | 15 | 33.33 | 72 | 67 | 86.2 | 0 | 30 | 315 | 14.29 | 2025-12-14 | 2026-05-09 | 147 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-20
TA 513 | 0-20 | 0 | 20 | 83 | 29 | 34.94 | 175.5 | 149.6786 | 206.5 | 1 | 54 | 619 | 13.41 | 2025-03-22 | 2026-05-19 | 424 | Yes | 122 | 29 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 601 | 0-20 | 0 | 20 | 58 | 41 | 70.69 | 36 | 58.725 | 102.8 | 1 | 17 | 292 | 19.86 | 2025-05-03 | 2026-01-23 | 266 | Yes | 122 | 4 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-20
TA 601 | 20-40 | 20 | 40 | 58 | 29 | 50 | 16 | 18.2069 | 26.6 | 0 | 29 | 292 | 19.86 | 2026-01-24 | 2026-05-10 | 107 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-20
TA 601 | 40-60 | 40 | 60 | 4 | 0 | 0 |  |  |  | 0 | 4 | 292 | 1.37 | 2026-05-13 | 2026-05-20 | 8 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-20
TA 602 | 0-20 | 0 | 20 | 95 | 38 | 40 | 130 | 135 | 181.4 | 1 | 57 | 478 | 19.87 | 2025-09-15 | 2026-01-31 | 139 | Yes | 16 | 1 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 602 | 20-40 | 20 | 40 | 48 | 2 | 4.17 | 52.5 | 52.5 | 80.1 | 0 | 46 | 478 | 10.04 | 2026-01-31 | 2026-05-15 | 105 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TB 501 | 0-20 | 0 | 20 | 47 | 47 | 100 | 118 | 124.8298 | 183 | 0 | 0 | 238 | 19.75 | 2024-08-12 | 2024-11-15 | 96 | Yes | 50 | 10 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-20
TB 501 | 20-40 | 20 | 40 | 48 | 48 | 100 | 63.5 | 71.5625 | 110.6 | 0 | 0 | 238 | 20.17 | 2024-11-15 | 2025-01-10 | 57 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-20
TB 501 | 40-60 | 40 | 60 | 47 | 47 | 100 | 61 | 72.0426 | 128.8 | 0 | 0 | 238 | 19.75 | 2025-01-12 | 2025-04-15 | 94 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-20
TB 501 | 60-80 | 60 | 80 | 48 | 48 | 100 | 40 | 45.3958 | 82.5 | 0 | 0 | 238 | 20.17 | 2025-04-17 | 2025-10-17 | 184 | Yes | 122 | 18 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-20
TB 501 | 80-100+ | 80 | 100 | 41 | 40 | 97.56 | 12.5 | 14.8421 | 26.9 | 2 | 1 | 238 | 17.23 | 2025-10-23 | 2026-04-30 | 190 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-20
TB 507 | 0-20 | 0 | 20 | 111 | 83 | 74.77 | 134 | 142.1687 | 208.8 | 0 | 28 | 556 | 19.96 | 2025-01-17 | 2025-07-21 | 186 | Yes | 51 | 51 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TB 507 | 20-40 | 20 | 40 | 111 | 91 | 81.98 | 59 | 68.6556 | 117.6 | 1 | 20 | 556 | 19.96 | 2025-07-21 | 2025-11-12 | 115 | Yes | 72 | 96 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TB 507 | 40-60 | 40 | 60 | 109 | 46 | 42.2 | 46 | 55.0435 | 120 | 0 | 63 | 556 | 19.6 | 2025-11-14 | 2026-05-19 | 187 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TB 605 | 0-20 | 0 | 20 | 104 | 84 | 80.77 | 92.5 | 101.4762 | 156.1 | 0 | 20 | 523 | 19.89 | 2025-08-11 | 2025-12-26 | 138 | Yes | 51 | 4 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-20
TB 605 | 20-40 | 20 | 40 | 105 | 82 | 78.1 | 59 | 61.0854 | 97.8 | 0 | 23 | 523 | 20.08 | 2025-12-26 | 2026-03-09 | 74 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-20
TB 605 | 40-60 | 40 | 60 | 79 | 20 | 25.32 | 19 | 22.4 | 41.5 | 0 | 59 | 523 | 15.11 | 2026-03-10 | 2026-05-19 | 71 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-20
TB 608 | 0-20 | 0 | 20 | 63 | 21 | 33.33 | 77 | 91.2381 | 143 | 0 | 42 | 318 | 19.81 | 2025-10-18 | 2026-01-11 | 86 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-04-05
TB 608 | 20-40 | 20 | 40 | 64 | 6 | 9.38 | 48 | 53.8333 | 67.5 | 0 | 58 | 318 | 20.13 | 2026-01-11 | 2026-03-28 | 77 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-04-05
TB 608 | 40-60 | 40 | 60 | 5 | 0 | 0 |  |  |  | 0 | 5 | 318 | 1.57 | 2026-03-29 | 2026-04-19 | 22 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-04-05

## Delay Phase - Series
Delay Phase - Series
Series | Phase | Foundation Bucket Start % | Foundation Bucket End % | Foundation Count | Matched Count | Match % | Median Delay Days | Average Delay Days | P90 Delay Days | Negative Excluded | Unmatched | Scope Total | Phase Foundations % of Scope | Phase Start Date | Phase End Date | Phase Duration Days | Monsoon Overlap | Monsoon Overlap Days | Monsoon Foundation Count
4xx | 0-20 | 0 | 20 | 408 | 393 | 96.32 | 217 | 233.7263 | 416 | 2 | 15 | 2052 | 19.88 | 2024-01-02 | 2025-03-24 | 448 | Yes | 122 | 276
4xx | 20-40 | 20 | 40 | 409 | 394 | 96.33 | 159 | 171.5471 | 304 | 1 | 15 | 2052 | 19.93 | 2024-08-24 | 2025-11-27 | 461 | Yes | 160 | 50
4xx | 40-60 | 40 | 60 | 348 | 320 | 91.95 | 110.5 | 119.2138 | 214.2 | 2 | 28 | 2052 | 16.96 | 2024-10-24 | 2026-03-05 | 498 | Yes | 122 | 26
4xx | 60-80 | 60 | 80 | 283 | 216 | 76.33 | 99 | 116.586 | 234.8 | 1 | 67 | 2052 | 13.79 | 2024-11-30 | 2026-05-13 | 530 | Yes | 122 | 16
4xx | 80-100+ | 80 | 100 | 196 | 151 | 77.04 | 137 | 138.9272 | 240 | 0 | 45 | 2052 | 9.55 | 2025-01-30 | 2026-05-20 | 476 | Yes | 122 | 42
5xx | 0-20 | 0 | 20 | 498 | 384 | 77.11 | 161 | 180.3264 | 312.4 | 1 | 114 | 2709 | 18.38 | 2015-11-27 | 2026-05-19 | 3827 | Yes | 1220 | 98
5xx | 20-40 | 20 | 40 | 387 | 325 | 83.98 | 133.5 | 165.4599 | 347.5 | 1 | 62 | 2709 | 14.29 | 2024-11-15 | 2026-05-20 | 552 | Yes | 122 | 146
5xx | 40-60 | 40 | 60 | 357 | 265 | 74.23 | 150 | 153.8642 | 296.4 | 0 | 92 | 2709 | 13.18 | 2025-01-12 | 2026-05-19 | 493 | Yes | 122 | 90
5xx | 60-80 | 60 | 80 | 249 | 206 | 82.73 | 78.5 | 102.2476 | 218 | 0 | 43 | 2709 | 9.19 | 2025-04-17 | 2026-04-05 | 354 | Yes | 122 | 46
5xx | 80-100+ | 80 | 100 | 173 | 110 | 63.58 | 15 | 25.8692 | 69.4 | 3 | 63 | 2709 | 6.39 | 2025-10-23 | 2026-05-18 | 208 | No | 0 | 0
6xx | 0-20 | 0 | 20 | 320 | 184 | 57.5 | 93.5 | 97.7143 | 161.5 | 2 | 136 | 1611 | 19.86 | 2025-05-03 | 2026-01-31 | 274 | Yes | 122 | 9
6xx | 20-40 | 20 | 40 | 275 | 119 | 43.27 | 45 | 50.1261 | 95 | 0 | 156 | 1611 | 17.07 | 2025-12-26 | 2026-05-15 | 141 | No | 0 | 0
6xx | 40-60 | 40 | 60 | 88 | 20 | 22.73 | 19 | 22.4 | 41.5 | 0 | 68 | 1611 | 5.46 | 2026-03-10 | 2026-05-20 | 72 | No | 0 | 0

## Delay Phase - Ownership
Delay Phase - Ownership
Ownership | Phase | Foundation Bucket Start % | Foundation Bucket End % | Foundation Count | Matched Count | Match % | Median Delay Days | Average Delay Days | P90 Delay Days | Negative Excluded | Unmatched | Scope Total | Phase Foundations % of Scope | Phase Start Date | Phase End Date | Phase Duration Days | Monsoon Overlap | Monsoon Overlap Days | Monsoon Foundation Count
Government | 0-20 | 0 | 20 | 901 | 726 | 80.58 | 180 | 208.2233 | 376 | 5 | 175 | 4737 | 19.02 | 2015-11-27 | 2026-05-19 | 3827 | Yes | 1220 | 318
Government | 20-40 | 20 | 40 | 743 | 611 | 82.23 | 178 | 183.682 | 329 | 1 | 132 | 4737 | 15.69 | 2024-08-24 | 2026-05-20 | 635 | Yes | 160 | 100
Government | 40-60 | 40 | 60 | 553 | 492 | 88.97 | 143.5 | 148.502 | 274.1 | 2 | 61 | 4737 | 11.67 | 2024-10-24 | 2026-05-20 | 574 | Yes | 122 | 116
Government | 60-80 | 60 | 80 | 484 | 374 | 77.27 | 101 | 117.8284 | 232.8 | 1 | 110 | 4737 | 10.22 | 2024-11-30 | 2026-05-13 | 530 | Yes | 122 | 44
Government | 80-100+ | 80 | 100 | 328 | 221 | 67.38 | 93.5 | 105.3727 | 221.3 | 1 | 107 | 4737 | 6.92 | 2025-01-30 | 2026-05-20 | 476 | Yes | 122 | 42
Private | 0-20 | 0 | 20 | 325 | 235 | 72.31 | 108 | 119.6043 | 183 | 0 | 90 | 1635 | 19.88 | 2024-08-12 | 2026-01-11 | 518 | Yes | 172 | 65
Private | 20-40 | 20 | 40 | 328 | 227 | 69.21 | 59 | 66.1327 | 104.5 | 1 | 101 | 1635 | 20.06 | 2024-11-15 | 2026-03-28 | 499 | Yes | 122 | 96
Private | 40-60 | 40 | 60 | 240 | 113 | 47.08 | 46 | 56.3363 | 113.6 | 0 | 127 | 1635 | 14.68 | 2025-01-12 | 2026-05-19 | 493 | Yes | 122 | 0
Private | 60-80 | 60 | 80 | 48 | 48 | 100 | 40 | 45.3958 | 82.5 | 0 | 0 | 1635 | 2.94 | 2025-04-17 | 2025-10-17 | 184 | Yes | 122 | 18
Private | 80-100+ | 80 | 100 | 41 | 40 | 97.56 | 12.5 | 14.8421 | 26.9 | 2 | 1 | 1635 | 2.51 | 2025-10-23 | 2026-04-30 | 190 | No | 0 | 0

## Delay Buckets - Project
Delay Buckets - Project
Project | Bucket | Bucket Start Days | Bucket End Days | Foundations In Bucket | % of Foundations Done Till Date | % of Scope | Foundations Done Till Date | Scope Total | Matched Non-Negative | Unmatched | Negative Excluded
TA 413 | 0-30 | 0 | 30 | 3 | 0.96 | 0.47 | 314 | 632 | 302 | 10 | 2
TA 413 | 31-60 | 31 | 60 | 23 | 7.32 | 3.64 | 314 | 632 | 302 | 10 | 2
TA 413 | 61-90 | 61 | 90 | 34 | 10.83 | 5.38 | 314 | 632 | 302 | 10 | 2
TA 413 | 91-120 | 91 | 120 | 24 | 7.64 | 3.8 | 314 | 632 | 302 | 10 | 2
TA 413 | 121-150 | 121 | 150 | 19 | 6.05 | 3.01 | 314 | 632 | 302 | 10 | 2
TA 413 | 151-180 | 151 | 180 | 33 | 10.51 | 5.22 | 314 | 632 | 302 | 10 | 2
TA 413 | 181-210 | 181 | 210 | 28 | 8.92 | 4.43 | 314 | 632 | 302 | 10 | 2
TA 413 | 211-240 | 211 | 240 | 16 | 5.1 | 2.53 | 314 | 632 | 302 | 10 | 2
TA 413 | 241-270 | 241 | 270 | 22 | 7.01 | 3.48 | 314 | 632 | 302 | 10 | 2
TA 413 | 271-300 | 271 | 300 | 21 | 6.69 | 3.32 | 314 | 632 | 302 | 10 | 2
TA 413 | 301-330 | 301 | 330 | 21 | 6.69 | 3.32 | 314 | 632 | 302 | 10 | 2
TA 413 | 331-360 | 331 | 360 | 19 | 6.05 | 3.01 | 314 | 632 | 302 | 10 | 2
TA 413 | 361-390 | 361 | 390 | 10 | 3.18 | 1.58 | 314 | 632 | 302 | 10 | 2
TA 413 | 391-420 | 391 | 420 | 9 | 2.87 | 1.42 | 314 | 632 | 302 | 10 | 2
TA 413 | 421-450 | 421 | 450 | 9 | 2.87 | 1.42 | 314 | 632 | 302 | 10 | 2
TA 413 | 451-480 | 451 | 480 | 2 | 0.64 | 0.32 | 314 | 632 | 302 | 10 | 2
TA 413 | 481-510 | 481 | 510 | 9 | 2.87 | 1.42 | 314 | 632 | 302 | 10 | 2
TA 414 | 0-30 | 0 | 30 | 26 | 7.95 | 7.39 | 327 | 352 | 223 | 102 | 2
TA 414 | 31-60 | 31 | 60 | 45 | 13.76 | 12.78 | 327 | 352 | 223 | 102 | 2
TA 414 | 61-90 | 61 | 90 | 34 | 10.4 | 9.66 | 327 | 352 | 223 | 102 | 2
TA 414 | 91-120 | 91 | 120 | 22 | 6.73 | 6.25 | 327 | 352 | 223 | 102 | 2
TA 414 | 121-150 | 121 | 150 | 7 | 2.14 | 1.99 | 327 | 352 | 223 | 102 | 2
TA 414 | 151-180 | 151 | 180 | 8 | 2.45 | 2.27 | 327 | 352 | 223 | 102 | 2
TA 414 | 181-210 | 181 | 210 | 5 | 1.53 | 1.42 | 327 | 352 | 223 | 102 | 2
TA 414 | 211-240 | 211 | 240 | 6 | 1.83 | 1.7 | 327 | 352 | 223 | 102 | 2
TA 414 | 241-270 | 241 | 270 | 8 | 2.45 | 2.27 | 327 | 352 | 223 | 102 | 2
TA 414 | 271-300 | 271 | 300 | 9 | 2.75 | 2.56 | 327 | 352 | 223 | 102 | 2
TA 414 | 301-330 | 301 | 330 | 12 | 3.67 | 3.41 | 327 | 352 | 223 | 102 | 2
TA 414 | 331-360 | 331 | 360 | 15 | 4.59 | 4.26 | 327 | 352 | 223 | 102 | 2
TA 414 | 361-390 | 361 | 390 | 7 | 2.14 | 1.99 | 327 | 352 | 223 | 102 | 2
TA 414 | 391-420 | 391 | 420 | 7 | 2.14 | 1.99 | 327 | 352 | 223 | 102 | 2
TA 414 | 421-450 | 421 | 450 | 5 | 1.53 | 1.42 | 327 | 352 | 223 | 102 | 2
TA 414 | 451-480 | 451 | 480 | 4 | 1.22 | 1.14 | 327 | 352 | 223 | 102 | 2
TA 414 | 481-510 | 481 | 510 | 0 | 0 | 0 | 327 | 352 | 223 | 102 | 2
TA 414 | 511-540 | 511 | 540 | 0 | 0 | 0 | 327 | 352 | 223 | 102 | 2
TA 414 | 541-570 | 541 | 570 | 1 | 0.31 | 0.28 | 327 | 352 | 223 | 102 | 2
TA 414 | 571-600 | 571 | 600 | 0 | 0 | 0 | 327 | 352 | 223 | 102 | 2
TA 414 | 601-630 | 601 | 630 | 1 | 0.31 | 0.28 | 327 | 352 | 223 | 102 | 2
TA 414 | 631-660 | 631 | 660 | 0 | 0 | 0 | 327 | 352 | 223 | 102 | 2
TA 414 | 661-690 | 661 | 690 | 0 | 0 | 0 | 327 | 352 | 223 | 102 | 2
TA 414 | 691-720 | 691 | 720 | 1 | 0.31 | 0.28 | 327 | 352 | 223 | 102 | 2
TA 416 | 0-30 | 0 | 30 | 7 | 2.31 | 2.32 | 303 | 302 | 303 | 0 | 0
TA 416 | 31-60 | 31 | 60 | 16 | 5.28 | 5.3 | 303 | 302 | 303 | 0 | 0
TA 416 | 61-90 | 61 | 90 | 36 | 11.88 | 11.92 | 303 | 302 | 303 | 0 | 0
TA 416 | 91-120 | 91 | 120 | 56 | 18.48 | 18.54 | 303 | 302 | 303 | 0 | 0
TA 416 | 121-150 | 121 | 150 | 48 | 15.84 | 15.89 | 303 | 302 | 303 | 0 | 0
TA 416 | 151-180 | 151 | 180 | 31 | 10.23 | 10.26 | 303 | 302 | 303 | 0 | 0
TA 416 | 181-210 | 181 | 210 | 30 | 9.9 | 9.93 | 303 | 302 | 303 | 0 | 0
TA 416 | 211-240 | 211 | 240 | 21 | 6.93 | 6.95 | 303 | 302 | 303 | 0 | 0
TA 416 | 241-270 | 241 | 270 | 24 | 7.92 | 7.95 | 303 | 302 | 303 | 0 | 0
TA 416 | 271-300 | 271 | 300 | 18 | 5.94 | 5.96 | 303 | 302 | 303 | 0 | 0
TA 416 | 301-330 | 301 | 330 | 6 | 1.98 | 1.99 | 303 | 302 | 303 | 0 | 0
TA 416 | 331-360 | 331 | 360 | 6 | 1.98 | 1.99 | 303 | 302 | 303 | 0 | 0
TA 416 | 361-390 | 361 | 390 | 2 | 0.66 | 0.66 | 303 | 302 | 303 | 0 | 0
TA 416 | 391-420 | 391 | 420 | 0 | 0 | 0 | 303 | 302 | 303 | 0 | 0
TA 416 | 421-450 | 421 | 450 | 1 | 0.33 | 0.33 | 303 | 302 | 303 | 0 | 0
TA 416 | 451-480 | 451 | 480 | 1 | 0.33 | 0.33 | 303 | 302 | 303 | 0 | 0
TA 418 | 0-30 | 0 | 30 | 12 | 9.3 | 9.45 | 129 | 127 | 125 | 4 | 0
TA 418 | 31-60 | 31 | 60 | 12 | 9.3 | 9.45 | 129 | 127 | 125 | 4 | 0
TA 418 | 61-90 | 61 | 90 | 17 | 13.18 | 13.39 | 129 | 127 | 125 | 4 | 0
TA 418 | 91-120 | 91 | 120 | 17 | 13.18 | 13.39 | 129 | 127 | 125 | 4 | 0
TA 418 | 121-150 | 121 | 150 | 23 | 17.83 | 18.11 | 129 | 127 | 125 | 4 | 0
TA 418 | 151-180 | 151 | 180 | 17 | 13.18 | 13.39 | 129 | 127 | 125 | 4 | 0
TA 418 | 181-210 | 181 | 210 | 8 | 6.2 | 6.3 | 129 | 127 | 125 | 4 | 0
TA 418 | 211-240 | 211 | 240 | 8 | 6.2 | 6.3 | 129 | 127 | 125 | 4 | 0
TA 418 | 241-270 | 241 | 270 | 7 | 5.43 | 5.51 | 129 | 127 | 125 | 4 | 0
TA 418 | 271-300 | 271 | 300 | 0 | 0 | 0 | 129 | 127 | 125 | 4 | 0
TA 418 | 301-330 | 301 | 330 | 3 | 2.33 | 2.36 | 129 | 127 | 125 | 4 | 0
TA 418 | 331-360 | 331 | 360 | 0 | 0 | 0 | 129 | 127 | 125 | 4 | 0
TA 418 | 361-390 | 361 | 390 | 0 | 0 | 0 | 129 | 127 | 125 | 4 | 0
TA 418 | 391-420 | 391 | 420 | 0 | 0 | 0 | 129 | 127 | 125 | 4 | 0
TA 418 | 421-450 | 421 | 450 | 0 | 0 | 0 | 129 | 127 | 125 | 4 | 0
TA 418 | 451-480 | 451 | 480 | 1 | 0.78 | 0.79 | 129 | 127 | 125 | 4 | 0
TA 419 | 0-30 | 0 | 30 | 22 | 8.21 | 6.67 | 268 | 330 | 214 | 52 | 2
TA 419 | 31-60 | 31 | 60 | 22 | 8.21 | 6.67 | 268 | 330 | 214 | 52 | 2
TA 419 | 61-90 | 61 | 90 | 15 | 5.6 | 4.55 | 268 | 330 | 214 | 52 | 2
TA 419 | 91-120 | 91 | 120 | 27 | 10.07 | 8.18 | 268 | 330 | 214 | 52 | 2
TA 419 | 121-150 | 121 | 150 | 20 | 7.46 | 6.06 | 268 | 330 | 214 | 52 | 2
TA 419 | 151-180 | 151 | 180 | 21 | 7.84 | 6.36 | 268 | 330 | 214 | 52 | 2
TA 419 | 181-210 | 181 | 210 | 13 | 4.85 | 3.94 | 268 | 330 | 214 | 52 | 2
TA 419 | 211-240 | 211 | 240 | 17 | 6.34 | 5.15 | 268 | 330 | 214 | 52 | 2
TA 419 | 241-270 | 241 | 270 | 22 | 8.21 | 6.67 | 268 | 330 | 214 | 52 | 2
TA 419 | 271-300 | 271 | 300 | 15 | 5.6 | 4.55 | 268 | 330 | 214 | 52 | 2
TA 419 | 301-330 | 301 | 330 | 7 | 2.61 | 2.12 | 268 | 330 | 214 | 52 | 2
TA 419 | 331-360 | 331 | 360 | 5 | 1.87 | 1.52 | 268 | 330 | 214 | 52 | 2
TA 419 | 361-390 | 361 | 390 | 3 | 1.12 | 0.91 | 268 | 330 | 214 | 52 | 2
TA 419 | 391-420 | 391 | 420 | 2 | 0.75 | 0.61 | 268 | 330 | 214 | 52 | 2
TA 419 | 421-450 | 421 | 450 | 2 | 0.75 | 0.61 | 268 | 330 | 214 | 52 | 2
TA 419 | 451-480 | 451 | 480 | 1 | 0.37 | 0.3 | 268 | 330 | 214 | 52 | 2
TA 421 | 0-30 | 0 | 30 | 17 | 5.61 | 5.5 | 303 | 309 | 301 | 2 | 0
TA 421 | 31-60 | 31 | 60 | 37 | 12.21 | 11.97 | 303 | 309 | 301 | 2 | 0
TA 421 | 61-90 | 61 | 90 | 32 | 10.56 | 10.36 | 303 | 309 | 301 | 2 | 0
TA 421 | 91-120 | 91 | 120 | 64 | 21.12 | 20.71 | 303 | 309 | 301 | 2 | 0
TA 421 | 121-150 | 121 | 150 | 43 | 14.19 | 13.92 | 303 | 309 | 301 | 2 | 0
TA 421 | 151-180 | 151 | 180 | 41 | 13.53 | 13.27 | 303 | 309 | 301 | 2 | 0
TA 421 | 181-210 | 181 | 210 | 24 | 7.92 | 7.77 | 303 | 309 | 301 | 2 | 0
TA 421 | 211-240 | 211 | 240 | 12 | 3.96 | 3.88 | 303 | 309 | 301 | 2 | 0
TA 421 | 241-270 | 241 | 270 | 10 | 3.3 | 3.24 | 303 | 309 | 301 | 2 | 0
TA 421 | 271-300 | 271 | 300 | 8 | 2.64 | 2.59 | 303 | 309 | 301 | 2 | 0
TA 421 | 301-330 | 301 | 330 | 2 | 0.66 | 0.65 | 303 | 309 | 301 | 2 | 0
TA 421 | 331-360 | 331 | 360 | 5 | 1.65 | 1.62 | 303 | 309 | 301 | 2 | 0
TA 421 | 361-390 | 361 | 390 | 2 | 0.66 | 0.65 | 303 | 309 | 301 | 2 | 0
TA 421 | 391-420 | 391 | 420 | 1 | 0.33 | 0.32 | 303 | 309 | 301 | 2 | 0
TA 421 | 421-450 | 421 | 450 | 1 | 0.33 | 0.32 | 303 | 309 | 301 | 2 | 0
TA 421 | 451-480 | 451 | 480 | 0 | 0 | 0 | 303 | 309 | 301 | 2 | 0
TA 421 | 481-510 | 481 | 510 | 0 | 0 | 0 | 303 | 309 | 301 | 2 | 0
TA 421 | 511-540 | 511 | 540 | 1 | 0.33 | 0.32 | 303 | 309 | 301 | 2 | 0
TA 421 | 541-570 | 541 | 570 | 1 | 0.33 | 0.32 | 303 | 309 | 301 | 2 | 0
TA 505 | 0-30 | 0 | 30 | 48 | 12.87 | 12.66 | 373 | 379 | 355 | 17 | 1
TA 505 | 31-60 | 31 | 60 | 28 | 7.51 | 7.39 | 373 | 379 | 355 | 17 | 1
TA 505 | 61-90 | 61 | 90 | 14 | 3.75 | 3.69 | 373 | 379 | 355 | 17 | 1
TA 505 | 91-120 | 91 | 120 | 41 | 10.99 | 10.82 | 373 | 379 | 355 | 17 | 1
TA 505 | 121-150 | 121 | 150 | 50 | 13.4 | 13.19 | 373 | 379 | 355 | 17 | 1
TA 505 | 151-180 | 151 | 180 | 29 | 7.77 | 7.65 | 373 | 379 | 355 | 17 | 1
TA 505 | 181-210 | 181 | 210 | 27 | 7.24 | 7.12 | 373 | 379 | 355 | 17 | 1
TA 505 | 211-240 | 211 | 240 | 28 | 7.51 | 7.39 | 373 | 379 | 355 | 17 | 1
TA 505 | 241-270 | 241 | 270 | 22 | 5.9 | 5.8 | 373 | 379 | 355 | 17 | 1
TA 505 | 271-300 | 271 | 300 | 22 | 5.9 | 5.8 | 373 | 379 | 355 | 17 | 1
TA 505 | 301-330 | 301 | 330 | 12 | 3.22 | 3.17 | 373 | 379 | 355 | 17 | 1
TA 505 | 331-360 | 331 | 360 | 19 | 5.09 | 5.01 | 373 | 379 | 355 | 17 | 1
TA 505 | 361-390 | 361 | 390 | 4 | 1.07 | 1.06 | 373 | 379 | 355 | 17 | 1
TA 505 | 391-420 | 391 | 420 | 3 | 0.8 | 0.79 | 373 | 379 | 355 | 17 | 1
TA 505 | 421-450 | 421 | 450 | 5 | 1.34 | 1.32 | 373 | 379 | 355 | 17 | 1
TA 505 | 451-480 | 451 | 480 | 0 | 0 | 0 | 373 | 379 | 355 | 17 | 1
TA 505 | 481-510 | 481 | 510 | 1 | 0.27 | 0.26 | 373 | 379 | 355 | 17 | 1
TA 505 | 511-540 | 511 | 540 | 0 | 0 | 0 | 373 | 379 | 355 | 17 | 1
TA 505 | 541-570 | 541 | 570 | 0 | 0 | 0 | 373 | 379 | 355 | 17 | 1
TA 505 | 571-600 | 571 | 600 | 0 | 0 | 0 | 373 | 379 | 355 | 17 | 1
TA 505 | 601-630 | 601 | 630 | 0 | 0 | 0 | 373 | 379 | 355 | 17 | 1
TA 505 | 631-660 | 631 | 660 | 2 | 0.54 | 0.53 | 373 | 379 | 355 | 17 | 1
TA 509 | 0-30 | 0 | 30 | 5 | 1.89 | 1.62 | 264 | 309 | 204 | 60 | 0
TA 509 | 31-60 | 31 | 60 | 12 | 4.55 | 3.88 | 264 | 309 | 204 | 60 | 0
TA 509 | 61-90 | 61 | 90 | 11 | 4.17 | 3.56 | 264 | 309 | 204 | 60 | 0
TA 509 | 91-120 | 91 | 120 | 7 | 2.65 | 2.27 | 264 | 309 | 204 | 60 | 0
TA 509 | 121-150 | 121 | 150 | 14 | 5.3 | 4.53 | 264 | 309 | 204 | 60 | 0
TA 509 | 151-180 | 151 | 180 | 14 | 5.3 | 4.53 | 264 | 309 | 204 | 60 | 0
TA 509 | 181-210 | 181 | 210 | 28 | 10.61 | 9.06 | 264 | 309 | 204 | 60 | 0
TA 509 | 211-240 | 211 | 240 | 17 | 6.44 | 5.5 | 264 | 309 | 204 | 60 | 0
TA 509 | 241-270 | 241 | 270 | 17 | 6.44 | 5.5 | 264 | 309 | 204 | 60 | 0
TA 509 | 271-300 | 271 | 300 | 13 | 4.92 | 4.21 | 264 | 309 | 204 | 60 | 0
TA 509 | 301-330 | 301 | 330 | 23 | 8.71 | 7.44 | 264 | 309 | 204 | 60 | 0
TA 509 | 331-360 | 331 | 360 | 21 | 7.95 | 6.8 | 264 | 309 | 204 | 60 | 0
TA 509 | 361-390 | 361 | 390 | 12 | 4.55 | 3.88 | 264 | 309 | 204 | 60 | 0
TA 509 | 391-420 | 391 | 420 | 9 | 3.41 | 2.91 | 264 | 309 | 204 | 60 | 0
TA 509 | 421-450 | 421 | 450 | 1 | 0.38 | 0.32 | 264 | 309 | 204 | 60 | 0
TA 510 | 0-30 | 0 | 30 | 1 | 1.18 | 0.34 | 85 | 293 | 34 | 51 | 0
TA 510 | 31-60 | 31 | 60 | 3 | 3.53 | 1.02 | 85 | 293 | 34 | 51 | 0
TA 510 | 61-90 | 61 | 90 | 10 | 11.76 | 3.41 | 85 | 293 | 34 | 51 | 0
TA 510 | 91-120 | 91 | 120 | 9 | 10.59 | 3.07 | 85 | 293 | 34 | 51 | 0
TA 510 | 121-150 | 121 | 150 | 2 | 2.35 | 0.68 | 85 | 293 | 34 | 51 | 0
TA 510 | 151-180 | 151 | 180 | 2 | 2.35 | 0.68 | 85 | 293 | 34 | 51 | 0
TA 510 | 181-210 | 181 | 210 | 0 | 0 | 0 | 85 | 293 | 34 | 51 | 0
TA 510 | 211-240 | 211 | 240 | 1 | 1.18 | 0.34 | 85 | 293 | 34 | 51 | 0
TA 510 | 241-270 | 241 | 270 | 1 | 1.18 | 0.34 | 85 | 293 | 34 | 51 | 0
TA 510 | 271-300 | 271 | 300 | 2 | 2.35 | 0.68 | 85 | 293 | 34 | 51 | 0
TA 510 | 301-330 | 301 | 330 | 0 | 0 | 0 | 85 | 293 | 34 | 51 | 0
TA 510 | 331-360 | 331 | 360 | 1 | 1.18 | 0.34 | 85 | 293 | 34 | 51 | 0
TA 510 | 361-390 | 361 | 390 | 2 | 2.35 | 0.68 | 85 | 293 | 34 | 51 | 0
TA 512 | 0-30 | 0 | 30 | 4 | 1.35 | 1.27 | 297 | 315 | 217 | 80 | 0
TA 512 | 31-60 | 31 | 60 | 10 | 3.37 | 3.17 | 297 | 315 | 217 | 80 | 0
TA 512 | 61-90 | 61 | 90 | 22 | 7.41 | 6.98 | 297 | 315 | 217 | 80 | 0
TA 512 | 91-120 | 91 | 120 | 21 | 7.07 | 6.67 | 297 | 315 | 217 | 80 | 0
TA 512 | 121-150 | 121 | 150 | 35 | 11.78 | 11.11 | 297 | 315 | 217 | 80 | 0
TA 512 | 151-180 | 151 | 180 | 44 | 14.81 | 13.97 | 297 | 315 | 217 | 80 | 0
TA 512 | 181-210 | 181 | 210 | 13 | 4.38 | 4.13 | 297 | 315 | 217 | 80 | 0
TA 512 | 211-240 | 211 | 240 | 26 | 8.75 | 8.25 | 297 | 315 | 217 | 80 | 0
TA 512 | 241-270 | 241 | 270 | 21 | 7.07 | 6.67 | 297 | 315 | 217 | 80 | 0
TA 512 | 271-300 | 271 | 300 | 13 | 4.38 | 4.13 | 297 | 315 | 217 | 80 | 0
TA 512 | 301-330 | 301 | 330 | 5 | 1.68 | 1.59 | 297 | 315 | 217 | 80 | 0
TA 512 | 331-360 | 331 | 360 | 2 | 0.67 | 0.63 | 297 | 315 | 217 | 80 | 0
TA 512 | 361-390 | 361 | 390 | 1 | 0.34 | 0.32 | 297 | 315 | 217 | 80 | 0
TA 513 | 0-30 | 0 | 30 | 2 | 2.41 | 0.32 | 83 | 619 | 28 | 54 | 1
TA 513 | 31-60 | 31 | 60 | 3 | 3.61 | 0.48 | 83 | 619 | 28 | 54 | 1
TA 513 | 61-90 | 61 | 90 | 0 | 0 | 0 | 83 | 619 | 28 | 54 | 1
TA 513 | 91-120 | 91 | 120 | 2 | 2.41 | 0.32 | 83 | 619 | 28 | 54 | 1
TA 513 | 121-150 | 121 | 150 | 3 | 3.61 | 0.48 | 83 | 619 | 28 | 54 | 1
TA 513 | 151-180 | 151 | 180 | 6 | 7.23 | 0.97 | 83 | 619 | 28 | 54 | 1
TA 513 | 181-210 | 181 | 210 | 10 | 12.05 | 1.62 | 83 | 619 | 28 | 54 | 1
TA 513 | 211-240 | 211 | 240 | 1 | 1.2 | 0.16 | 83 | 619 | 28 | 54 | 1
TA 513 | 241-270 | 241 | 270 | 1 | 1.2 | 0.16 | 83 | 619 | 28 | 54 | 1
TA 601 | 0-30 | 0 | 30 | 43 | 35.83 | 14.73 | 120 | 292 | 69 | 50 | 1
TA 601 | 31-60 | 31 | 60 | 10 | 8.33 | 3.42 | 120 | 292 | 69 | 50 | 1
TA 601 | 61-90 | 61 | 90 | 9 | 7.5 | 3.08 | 120 | 292 | 69 | 50 | 1
TA 601 | 91-120 | 91 | 120 | 4 | 3.33 | 1.37 | 120 | 292 | 69 | 50 | 1
TA 601 | 121-150 | 121 | 150 | 2 | 1.67 | 0.68 | 120 | 292 | 69 | 50 | 1
TA 601 | 151-180 | 151 | 180 | 0 | 0 | 0 | 120 | 292 | 69 | 50 | 1
TA 601 | 181-210 | 181 | 210 | 0 | 0 | 0 | 120 | 292 | 69 | 50 | 1
TA 601 | 211-240 | 211 | 240 | 0 | 0 | 0 | 120 | 292 | 69 | 50 | 1
TA 601 | 241-270 | 241 | 270 | 0 | 0 | 0 | 120 | 292 | 69 | 50 | 1
TA 601 | 271-300 | 271 | 300 | 0 | 0 | 0 | 120 | 292 | 69 | 50 | 1
TA 601 | 301-330 | 301 | 330 | 0 | 0 | 0 | 120 | 292 | 69 | 50 | 1
TA 601 | 331-360 | 331 | 360 | 1 | 0.83 | 0.34 | 120 | 292 | 69 | 50 | 1
TA 602 | 0-30 | 0 | 30 | 1 | 0.7 | 0.21 | 143 | 478 | 39 | 103 | 1
TA 602 | 31-60 | 31 | 60 | 1 | 0.7 | 0.21 | 143 | 478 | 39 | 103 | 1
TA 602 | 61-90 | 61 | 90 | 3 | 2.1 | 0.63 | 143 | 478 | 39 | 103 | 1
TA 602 | 91-120 | 91 | 120 | 10 | 6.99 | 2.09 | 143 | 478 | 39 | 103 | 1
TA 602 | 121-150 | 121 | 150 | 13 | 9.09 | 2.72 | 143 | 478 | 39 | 103 | 1
TA 602 | 151-180 | 151 | 180 | 6 | 4.2 | 1.26 | 143 | 478 | 39 | 103 | 1
TA 602 | 181-210 | 181 | 210 | 5 | 3.5 | 1.05 | 143 | 478 | 39 | 103 | 1
TB 501 | 0-30 | 0 | 30 | 61 | 26.41 | 25.63 | 231 | 238 | 228 | 1 | 2
TB 501 | 31-60 | 31 | 60 | 60 | 25.97 | 25.21 | 231 | 238 | 228 | 1 | 2
TB 501 | 61-90 | 61 | 90 | 38 | 16.45 | 15.97 | 231 | 238 | 228 | 1 | 2
TB 501 | 91-120 | 91 | 120 | 36 | 15.58 | 15.13 | 231 | 238 | 228 | 1 | 2
TB 501 | 121-150 | 121 | 150 | 19 | 8.23 | 7.98 | 231 | 238 | 228 | 1 | 2
TB 501 | 151-180 | 151 | 180 | 5 | 2.16 | 2.1 | 231 | 238 | 228 | 1 | 2
TB 501 | 181-210 | 181 | 210 | 8 | 3.46 | 3.36 | 231 | 238 | 228 | 1 | 2
TB 501 | 211-240 | 211 | 240 | 0 | 0 | 0 | 231 | 238 | 228 | 1 | 2
TB 501 | 241-270 | 241 | 270 | 1 | 0.43 | 0.42 | 231 | 238 | 228 | 1 | 2
TB 507 | 0-30 | 0 | 30 | 27 | 8.16 | 4.86 | 331 | 556 | 219 | 111 | 1
TB 507 | 31-60 | 31 | 60 | 62 | 18.73 | 11.15 | 331 | 556 | 219 | 111 | 1
TB 507 | 61-90 | 61 | 90 | 42 | 12.69 | 7.55 | 331 | 556 | 219 | 111 | 1
TB 507 | 91-120 | 91 | 120 | 25 | 7.55 | 4.5 | 331 | 556 | 219 | 111 | 1
TB 507 | 121-150 | 121 | 150 | 24 | 7.25 | 4.32 | 331 | 556 | 219 | 111 | 1
TB 507 | 151-180 | 151 | 180 | 22 | 6.65 | 3.96 | 331 | 556 | 219 | 111 | 1
TB 507 | 181-210 | 181 | 210 | 8 | 2.42 | 1.44 | 331 | 556 | 219 | 111 | 1
TB 507 | 211-240 | 211 | 240 | 2 | 0.6 | 0.36 | 331 | 556 | 219 | 111 | 1
TB 507 | 241-270 | 241 | 270 | 2 | 0.6 | 0.36 | 331 | 556 | 219 | 111 | 1
TB 507 | 271-300 | 271 | 300 | 1 | 0.3 | 0.18 | 331 | 556 | 219 | 111 | 1
TB 507 | 301-330 | 301 | 330 | 1 | 0.3 | 0.18 | 331 | 556 | 219 | 111 | 1
TB 507 | 331-360 | 331 | 360 | 2 | 0.6 | 0.36 | 331 | 556 | 219 | 111 | 1
TB 507 | 361-390 | 361 | 390 | 1 | 0.3 | 0.18 | 331 | 556 | 219 | 111 | 1
TB 605 | 0-30 | 0 | 30 | 28 | 9.72 | 5.35 | 288 | 523 | 186 | 102 | 0
TB 605 | 31-60 | 31 | 60 | 41 | 14.24 | 7.84 | 288 | 523 | 186 | 102 | 0
TB 605 | 61-90 | 61 | 90 | 56 | 19.44 | 10.71 | 288 | 523 | 186 | 102 | 0
TB 605 | 91-120 | 91 | 120 | 41 | 14.24 | 7.84 | 288 | 523 | 186 | 102 | 0
TB 605 | 121-150 | 121 | 150 | 10 | 3.47 | 1.91 | 288 | 523 | 186 | 102 | 0
TB 605 | 151-180 | 151 | 180 | 7 | 2.43 | 1.34 | 288 | 523 | 186 | 102 | 0
TB 605 | 181-210 | 181 | 210 | 2 | 0.69 | 0.38 | 288 | 523 | 186 | 102 | 0
TB 605 | 211-240 | 211 | 240 | 1 | 0.35 | 0.19 | 288 | 523 | 186 | 102 | 0
TB 608 | 0-30 | 0 | 30 | 0 | 0 | 0 | 132 | 318 | 27 | 105 | 0
TB 608 | 31-60 | 31 | 60 | 10 | 7.58 | 3.14 | 132 | 318 | 27 | 105 | 0
TB 608 | 61-90 | 61 | 90 | 7 | 5.3 | 2.2 | 132 | 318 | 27 | 105 | 0
TB 608 | 91-120 | 91 | 120 | 4 | 3.03 | 1.26 | 132 | 318 | 27 | 105 | 0
TB 608 | 121-150 | 121 | 150 | 4 | 3.03 | 1.26 | 132 | 318 | 27 | 105 | 0
TB 608 | 151-180 | 151 | 180 | 1 | 0.76 | 0.31 | 132 | 318 | 27 | 105 | 0
TB 608 | 181-210 | 181 | 210 | 1 | 0.76 | 0.31 | 132 | 318 | 27 | 105 | 0

## Delay Buckets - Series
Delay Buckets - Series
Series | Bucket | Bucket Start Days | Bucket End Days | Foundations In Bucket | % of Foundations Done Till Date | % of Scope | Foundations Done Till Date | Scope Total | Matched Non-Negative | Unmatched | Negative Excluded
4xx | 0-30 | 0 | 30 | 87 | 5.29 | 4.24 | 1644 | 2052 | 1468 | 170 | 6
4xx | 31-60 | 31 | 60 | 155 | 9.43 | 7.55 | 1644 | 2052 | 1468 | 170 | 6
4xx | 61-90 | 61 | 90 | 168 | 10.22 | 8.19 | 1644 | 2052 | 1468 | 170 | 6
4xx | 91-120 | 91 | 120 | 210 | 12.77 | 10.23 | 1644 | 2052 | 1468 | 170 | 6
4xx | 121-150 | 121 | 150 | 160 | 9.73 | 7.8 | 1644 | 2052 | 1468 | 170 | 6
4xx | 151-180 | 151 | 180 | 151 | 9.18 | 7.36 | 1644 | 2052 | 1468 | 170 | 6
4xx | 181-210 | 181 | 210 | 108 | 6.57 | 5.26 | 1644 | 2052 | 1468 | 170 | 6
4xx | 211-240 | 211 | 240 | 80 | 4.87 | 3.9 | 1644 | 2052 | 1468 | 170 | 6
4xx | 241-270 | 241 | 270 | 93 | 5.66 | 4.53 | 1644 | 2052 | 1468 | 170 | 6
4xx | 271-300 | 271 | 300 | 71 | 4.32 | 3.46 | 1644 | 2052 | 1468 | 170 | 6
4xx | 301-330 | 301 | 330 | 51 | 3.1 | 2.49 | 1644 | 2052 | 1468 | 170 | 6
4xx | 331-360 | 331 | 360 | 50 | 3.04 | 2.44 | 1644 | 2052 | 1468 | 170 | 6
4xx | 361-390 | 361 | 390 | 24 | 1.46 | 1.17 | 1644 | 2052 | 1468 | 170 | 6
4xx | 391-420 | 391 | 420 | 19 | 1.16 | 0.93 | 1644 | 2052 | 1468 | 170 | 6
4xx | 421-450 | 421 | 450 | 18 | 1.09 | 0.88 | 1644 | 2052 | 1468 | 170 | 6
4xx | 451-480 | 451 | 480 | 9 | 0.55 | 0.44 | 1644 | 2052 | 1468 | 170 | 6
4xx | 481-510 | 481 | 510 | 9 | 0.55 | 0.44 | 1644 | 2052 | 1468 | 170 | 6
4xx | 511-540 | 511 | 540 | 1 | 0.06 | 0.05 | 1644 | 2052 | 1468 | 170 | 6
4xx | 541-570 | 541 | 570 | 2 | 0.12 | 0.1 | 1644 | 2052 | 1468 | 170 | 6
4xx | 571-600 | 571 | 600 | 0 | 0 | 0 | 1644 | 2052 | 1468 | 170 | 6
4xx | 601-630 | 601 | 630 | 1 | 0.06 | 0.05 | 1644 | 2052 | 1468 | 170 | 6
4xx | 631-660 | 631 | 660 | 0 | 0 | 0 | 1644 | 2052 | 1468 | 170 | 6
4xx | 661-690 | 661 | 690 | 0 | 0 | 0 | 1644 | 2052 | 1468 | 170 | 6
4xx | 691-720 | 691 | 720 | 1 | 0.06 | 0.05 | 1644 | 2052 | 1468 | 170 | 6
5xx | 0-30 | 0 | 30 | 148 | 8.89 | 5.46 | 1664 | 2709 | 1285 | 374 | 5
5xx | 31-60 | 31 | 60 | 178 | 10.7 | 6.57 | 1664 | 2709 | 1285 | 374 | 5
5xx | 61-90 | 61 | 90 | 137 | 8.23 | 5.06 | 1664 | 2709 | 1285 | 374 | 5
5xx | 91-120 | 91 | 120 | 141 | 8.47 | 5.2 | 1664 | 2709 | 1285 | 374 | 5
5xx | 121-150 | 121 | 150 | 147 | 8.83 | 5.43 | 1664 | 2709 | 1285 | 374 | 5
5xx | 151-180 | 151 | 180 | 122 | 7.33 | 4.5 | 1664 | 2709 | 1285 | 374 | 5
5xx | 181-210 | 181 | 210 | 94 | 5.65 | 3.47 | 1664 | 2709 | 1285 | 374 | 5
5xx | 211-240 | 211 | 240 | 75 | 4.51 | 2.77 | 1664 | 2709 | 1285 | 374 | 5
5xx | 241-270 | 241 | 270 | 65 | 3.91 | 2.4 | 1664 | 2709 | 1285 | 374 | 5
5xx | 271-300 | 271 | 300 | 51 | 3.06 | 1.88 | 1664 | 2709 | 1285 | 374 | 5
5xx | 301-330 | 301 | 330 | 41 | 2.46 | 1.51 | 1664 | 2709 | 1285 | 374 | 5
5xx | 331-360 | 331 | 360 | 45 | 2.7 | 1.66 | 1664 | 2709 | 1285 | 374 | 5
5xx | 361-390 | 361 | 390 | 20 | 1.2 | 0.74 | 1664 | 2709 | 1285 | 374 | 5
5xx | 391-420 | 391 | 420 | 12 | 0.72 | 0.44 | 1664 | 2709 | 1285 | 374 | 5
5xx | 421-450 | 421 | 450 | 6 | 0.36 | 0.22 | 1664 | 2709 | 1285 | 374 | 5
5xx | 451-480 | 451 | 480 | 0 | 0 | 0 | 1664 | 2709 | 1285 | 374 | 5
5xx | 481-510 | 481 | 510 | 1 | 0.06 | 0.04 | 1664 | 2709 | 1285 | 374 | 5
5xx | 511-540 | 511 | 540 | 0 | 0 | 0 | 1664 | 2709 | 1285 | 374 | 5
5xx | 541-570 | 541 | 570 | 0 | 0 | 0 | 1664 | 2709 | 1285 | 374 | 5
5xx | 571-600 | 571 | 600 | 0 | 0 | 0 | 1664 | 2709 | 1285 | 374 | 5
5xx | 601-630 | 601 | 630 | 0 | 0 | 0 | 1664 | 2709 | 1285 | 374 | 5
5xx | 631-660 | 631 | 660 | 2 | 0.12 | 0.07 | 1664 | 2709 | 1285 | 374 | 5
6xx | 0-30 | 0 | 30 | 72 | 10.54 | 4.47 | 683 | 1611 | 321 | 360 | 2
6xx | 31-60 | 31 | 60 | 62 | 9.08 | 3.85 | 683 | 1611 | 321 | 360 | 2
6xx | 61-90 | 61 | 90 | 75 | 10.98 | 4.66 | 683 | 1611 | 321 | 360 | 2
6xx | 91-120 | 91 | 120 | 59 | 8.64 | 3.66 | 683 | 1611 | 321 | 360 | 2
6xx | 121-150 | 121 | 150 | 29 | 4.25 | 1.8 | 683 | 1611 | 321 | 360 | 2
6xx | 151-180 | 151 | 180 | 14 | 2.05 | 0.87 | 683 | 1611 | 321 | 360 | 2
6xx | 181-210 | 181 | 210 | 8 | 1.17 | 0.5 | 683 | 1611 | 321 | 360 | 2
6xx | 211-240 | 211 | 240 | 1 | 0.15 | 0.06 | 683 | 1611 | 321 | 360 | 2
6xx | 241-270 | 241 | 270 | 0 | 0 | 0 | 683 | 1611 | 321 | 360 | 2
6xx | 271-300 | 271 | 300 | 0 | 0 | 0 | 683 | 1611 | 321 | 360 | 2
6xx | 301-330 | 301 | 330 | 0 | 0 | 0 | 683 | 1611 | 321 | 360 | 2
6xx | 331-360 | 331 | 360 | 1 | 0.15 | 0.06 | 683 | 1611 | 321 | 360 | 2

## Delay Buckets - Ownership
Delay Buckets - Ownership
Ownership | Bucket | Bucket Start Days | Bucket End Days | Foundations In Bucket | % of Foundations Done Till Date | % of Scope | Foundations Done Till Date | Scope Total | Matched Non-Negative | Unmatched | Negative Excluded
Government | 0-30 | 0 | 30 | 191 | 6.35 | 4.03 | 3009 | 4737 | 2414 | 585 | 10
Government | 31-60 | 31 | 60 | 222 | 7.38 | 4.69 | 3009 | 4737 | 2414 | 585 | 10
Government | 61-90 | 61 | 90 | 237 | 7.88 | 5 | 3009 | 4737 | 2414 | 585 | 10
Government | 91-120 | 91 | 120 | 304 | 10.1 | 6.42 | 3009 | 4737 | 2414 | 585 | 10
Government | 121-150 | 121 | 150 | 279 | 9.27 | 5.89 | 3009 | 4737 | 2414 | 585 | 10
Government | 151-180 | 151 | 180 | 252 | 8.37 | 5.32 | 3009 | 4737 | 2414 | 585 | 10
Government | 181-210 | 181 | 210 | 191 | 6.35 | 4.03 | 3009 | 4737 | 2414 | 585 | 10
Government | 211-240 | 211 | 240 | 153 | 5.08 | 3.23 | 3009 | 4737 | 2414 | 585 | 10
Government | 241-270 | 241 | 270 | 155 | 5.15 | 3.27 | 3009 | 4737 | 2414 | 585 | 10
Government | 271-300 | 271 | 300 | 121 | 4.02 | 2.55 | 3009 | 4737 | 2414 | 585 | 10
Government | 301-330 | 301 | 330 | 91 | 3.02 | 1.92 | 3009 | 4737 | 2414 | 585 | 10
Government | 331-360 | 331 | 360 | 94 | 3.12 | 1.98 | 3009 | 4737 | 2414 | 585 | 10
Government | 361-390 | 361 | 390 | 43 | 1.43 | 0.91 | 3009 | 4737 | 2414 | 585 | 10
Government | 391-420 | 391 | 420 | 31 | 1.03 | 0.65 | 3009 | 4737 | 2414 | 585 | 10
Government | 421-450 | 421 | 450 | 24 | 0.8 | 0.51 | 3009 | 4737 | 2414 | 585 | 10
Government | 451-480 | 451 | 480 | 9 | 0.3 | 0.19 | 3009 | 4737 | 2414 | 585 | 10
Government | 481-510 | 481 | 510 | 10 | 0.33 | 0.21 | 3009 | 4737 | 2414 | 585 | 10
Government | 511-540 | 511 | 540 | 1 | 0.03 | 0.02 | 3009 | 4737 | 2414 | 585 | 10
Government | 541-570 | 541 | 570 | 2 | 0.07 | 0.04 | 3009 | 4737 | 2414 | 585 | 10
Government | 571-600 | 571 | 600 | 0 | 0 | 0 | 3009 | 4737 | 2414 | 585 | 10
Government | 601-630 | 601 | 630 | 1 | 0.03 | 0.02 | 3009 | 4737 | 2414 | 585 | 10
Government | 631-660 | 631 | 660 | 2 | 0.07 | 0.04 | 3009 | 4737 | 2414 | 585 | 10
Government | 661-690 | 661 | 690 | 0 | 0 | 0 | 3009 | 4737 | 2414 | 585 | 10
Government | 691-720 | 691 | 720 | 1 | 0.03 | 0.02 | 3009 | 4737 | 2414 | 585 | 10
Private | 0-30 | 0 | 30 | 116 | 11.81 | 7.09 | 982 | 1635 | 660 | 319 | 3
Private | 31-60 | 31 | 60 | 173 | 17.62 | 10.58 | 982 | 1635 | 660 | 319 | 3
Private | 61-90 | 61 | 90 | 143 | 14.56 | 8.75 | 982 | 1635 | 660 | 319 | 3
Private | 91-120 | 91 | 120 | 106 | 10.79 | 6.48 | 982 | 1635 | 660 | 319 | 3
Private | 121-150 | 121 | 150 | 57 | 5.8 | 3.49 | 982 | 1635 | 660 | 319 | 3
Private | 151-180 | 151 | 180 | 35 | 3.56 | 2.14 | 982 | 1635 | 660 | 319 | 3
Private | 181-210 | 181 | 210 | 19 | 1.93 | 1.16 | 982 | 1635 | 660 | 319 | 3
Private | 211-240 | 211 | 240 | 3 | 0.31 | 0.18 | 982 | 1635 | 660 | 319 | 3
Private | 241-270 | 241 | 270 | 3 | 0.31 | 0.18 | 982 | 1635 | 660 | 319 | 3
Private | 271-300 | 271 | 300 | 1 | 0.1 | 0.06 | 982 | 1635 | 660 | 319 | 3
Private | 301-330 | 301 | 330 | 1 | 0.1 | 0.06 | 982 | 1635 | 660 | 319 | 3
Private | 331-360 | 331 | 360 | 2 | 0.2 | 0.12 | 982 | 1635 | 660 | 319 | 3
Private | 361-390 | 361 | 390 | 1 | 0.1 | 0.06 | 982 | 1635 | 660 | 319 | 3

## Delay Coverage
Delay Coverage
Project | Series | Ownership | Eligible | Coverage Status | Source Type | Parser Modes | Reason | Foundation Locations | Matched Locations | RawData Start-Date Matches | Dropped-by-Daily Recovered | Alias Matches | Negative Excluded | Unmatched Locations | Scope Total | Scope Source | Scope Report Date | Status Rows Considered | Status Rows Used | Duplicate Rows Dropped | Notes
TA 413 | 4xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 314 | 304 | 304 | 1 | 1 | 2 | 10 | 632 | status_quantity_primary_latest | 2026-05-19 | 2 | 2 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 414 | 4xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 327 | 225 | 225 | 0 | 0 | 2 | 102 | 352 | status_quantity_primary_latest | 2026-05-21 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 416 | 4xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 303 | 303 | 303 | 2 | 2 | 0 | 0 | 302 | status_quantity_primary_latest | 2026-05-17 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 418 | 4xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 129 | 125 | 125 | 0 | 0 | 0 | 4 | 127 | status_quantity_primary_latest | 2026-05-21 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 419 | 4xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 268 | 216 | 216 | 15 | 0 | 2 | 52 | 330 | status_quantity_primary_latest | 2026-05-18 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 421 | 4xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 303 | 301 | 301 | 2 | 0 | 0 | 2 | 309 | status_quantity_primary_latest | 2026-05-18 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 505 | 5xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 373 | 356 | 356 | 3 | 0 | 1 | 17 | 379 | status_quantity_primary_latest | 2026-05-19 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 509 | 5xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 264 | 204 | 204 | 7 | 0 | 0 | 60 | 309 | status_quantity_primary_latest | 2026-05-18 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 510 | 5xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 85 | 34 | 34 | 0 | 0 | 0 | 51 | 293 | status_quantity_primary_latest | 2026-05-20 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 512 | 5xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 297 | 217 | 217 | 4 | 0 | 0 | 80 | 315 | status_quantity_primary_latest | 2026-05-20 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 513 | 5xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 83 | 29 | 29 | 1 | 0 | 1 | 54 | 619 | status_quantity_primary_latest | 2026-05-19 | 2 | 2 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 601 | 6xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 120 | 70 | 70 | 3 | 0 | 1 | 50 | 292 | status_quantity_primary_latest | 2026-05-20 | 2 | 2 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 602 | 6xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 143 | 40 | 40 | 0 | 0 | 1 | 103 | 478 | status_quantity_primary_latest | 2026-05-18 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TB 501 | 5xx | Private | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 231 | 230 | 230 | 0 | 0 | 2 | 1 | 238 | status_quantity_primary_latest | 2026-05-20 | 2 | 2 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TB 507 | 5xx | Private | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 331 | 220 | 220 | 8 | 0 | 1 | 111 | 556 | status_quantity_primary_latest | 2026-05-19 | 2 | 2 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TB 605 | 6xx | Private | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 288 | 186 | 186 | 8 | 0 | 0 | 102 | 523 | status_quantity_primary_latest | 2026-05-20 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TB 608 | 6xx | Private | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 132 | 27 | 27 | 5 | 0 | 0 | 105 | 318 | status_quantity_primary_latest | 2026-04-05 | 9 | 9 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.

## Delay Anomalies
Delay Anomalies
Project | Series | Ownership | Phase | Location | Foundation Date | Erection Start | Delay Days | Issue | Foundation Line | Erection Line
TA 413 | 4xx | Government | 20-40 | 39/8 | 2025-01-24 | 2024-03-26 | -304 | NEGATIVE_DELAY_EXCLUDED
TA 413 | 4xx | Government | 40-60 | N'37A/0 | 2026-03-05 | 2025-02-28 | -370 | NEGATIVE_DELAY_EXCLUDED
TA 413 | 4xx | Government | 0-20 | 37/1 | 2024-09-23 |  |  | UNMATCHED_LOCATION
TA 413 | 4xx | Government | 0-20 | 3/8 | 2024-10-05 |  |  | UNMATCHED_LOCATION
TA 413 | 4xx | Government | 0-20 | 3/9 | 2024-10-09 |  |  | UNMATCHED_LOCATION
TA 413 | 4xx | Government | 0-20 | 37/0 | 2024-10-14 |  |  | UNMATCHED_LOCATION
TA 413 | 4xx | Government | 0-20 | 3/7 | 2024-10-19 |  |  | UNMATCHED_LOCATION
TA 413 | 4xx | Government | 0-20 | 3/6 | 2024-10-22 |  |  | UNMATCHED_LOCATION
TA 413 | 4xx | Government | 20-40 | 3/4 | 2024-10-29 |  |  | UNMATCHED_LOCATION
TA 413 | 4xx | Government | 20-40 | 16/0 | 2024-12-28 |  |  | UNMATCHED_LOCATION
TA 413 | 4xx | Government | 40-60 | 36B/0 | 2026-01-23 |  |  | UNMATCHED_LOCATION
TA 413 | 4xx | Government | 40-60 | N'37/0 | 2026-02-08 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 0-20 | 121/4 | 2024-11-19 | 2024-03-27 | -237 | NEGATIVE_DELAY_EXCLUDED
TA 414 | 4xx | Government | 60-80 | 126/0 | 2026-02-18 | 2026-01-17 | -32 | NEGATIVE_DELAY_EXCLUDED
TA 414 | 4xx | Government | 0-20 | 249/1 | 2024-12-19 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 0-20 | 249/0 | 2024-12-26 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 0-20 | 249/2 | 2024-12-28 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 0-20 | 250/0 | 2025-01-07 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 0-20 | 121/8 | 2025-01-10 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 0-20 | 121/9 | 2025-01-20 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 0-20 | 243/3 | 2025-02-07 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 0-20 | 172/0 | 2025-03-07 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 20-40 | 165/2 | 2025-05-02 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 20-40 | 130/0 | 2025-05-10 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 20-40 | 221/0 | 2025-10-21 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 20-40 | 223/2 | 2025-10-26 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 20-40 | 224/0 | 2025-10-26 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 20-40 | 135/0 | 2025-11-04 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 20-40 | 219/1 | 2025-11-18 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 20-40 | 225/1 | 2025-11-22 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 20-40 | 225/4 | 2025-11-25 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 127/2 | 2025-12-01 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 194/0 | 2025-12-04 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 225/3 | 2025-12-05 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 244/0 | 2025-12-05 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 256/1 | 2025-12-09 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 225/2 | 2025-12-11 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 210/0 | 2025-12-13 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 139/3 | 2025-12-16 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 216/1 | 2025-12-16 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 257/0 | 2025-12-16 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 170/0 | 2025-12-17 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 173/0 | 2025-12-18 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 165/6 | 2025-12-20 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 193/0 | 2025-12-20 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 250/1 | 2025-12-20 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 216/2 | 2025-12-25 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 216/3 | 2025-12-25 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 244/3 | 2025-12-26 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 162/0 | 2025-12-29 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 211/0 | 2026-01-01 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 217/5 | 2026-01-12 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 211/4 | 2026-01-15 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 188/0 | 2026-01-16 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 212/0 | 2026-01-16 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 189/0 | 2026-01-18 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 213/0 | 2026-01-18 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 133/1 | 2026-01-19 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 165/4 | 2026-01-19 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 232/4 | 2026-01-19 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 233/0 | 2026-01-19 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 168/0 | 2026-01-20 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 238/0 | 2026-01-20 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 235/0 | 2026-01-21 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 236/0 | 2026-01-21 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 129/0 | 2026-01-23 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 163/0 | 2026-01-26 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 124/2 | 2026-02-01 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 214/0 | 2026-02-05 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 237/0 | 2026-02-05 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 232/0 | 2026-02-07 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 235/1 | 2026-02-07 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 217/0 | 2026-02-13 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 217/1 | 2026-02-13 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 248/0 | 2026-02-13 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 145/1 | 2026-02-14 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 219/0 | 2026-02-17 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 255/1 | 2026-02-25 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 234/0 | 2026-03-11 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 231/0 | 2026-03-12 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 131/0 | 2026-03-13 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 150/1 | 2026-03-16 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 180/0 | 2026-03-16 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 225/7 | 2026-03-16 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 232/2 | 2026-03-16 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 225/5 | 2026-03-18 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 230/1 | 2026-03-23 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 156/0 | 2026-03-25 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 150/0 | 2026-03-26 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 230A/0 | 2026-03-26 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 200/0 | 2026-04-01 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 155/0 | 2026-04-05 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 156/1 | 2026-04-05 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 159/0 | 2026-04-05 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 195/0 | 2026-04-05 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 232/3 | 2026-04-05 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 151/0 | 2026-04-09 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 164/0 | 2026-04-12 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 165/0 | 2026-04-12 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 131/1 | 2026-04-14 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 229B/0 | 2026-04-17 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 151A/0 | 2026-04-21 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 153/1 | 2026-04-21 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 229A/0 | 2026-04-21 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 235/4 | 2026-04-23 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 169/0 | 2026-04-26 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 206/0 | 2026-04-27 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 225/6 | 2026-04-27 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 206/1 | 2026-05-02 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 201/0 | 2026-05-09 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 203/0 | 2026-05-09 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 203A/0 | 2026-05-09 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 203B/0 | 2026-05-09 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 153A/0 | 2026-05-13 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 229/0 | 2026-05-14 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 153/2 | 2026-05-20 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 0-20 | 35/6 | 2024-08-07 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 20-40 | 45/02 | 2024-12-04 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 46/1 | 2025-06-25 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 59/1 | 2025-12-12 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 0-20 | 6/9 | 2024-07-10 | 2024-01-06 | -186 | NEGATIVE_DELAY_EXCLUDED
TA 419 | 4xx | Government | 40-60 | 26/1 | 2025-11-15 | 2025-03-22 | -238 | NEGATIVE_DELAY_EXCLUDED
TA 419 | 4xx | Government | 20-40 | 15/0 | 2024-12-12 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 20-40 | 39/0 | 2025-03-27 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 20-40 | 41/0 | 2025-04-23 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 40-60 | 78/3 | 2025-06-11 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 40-60 | 8/0 | 2025-07-15 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 40-60 | 46/0 | 2025-08-01 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 40-60 | 63/5 | 2025-11-02 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 40-60 | 83/9 | 2025-11-02 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 40-60 | 36/9 | 2025-11-06 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 40-60 | 43/1 | 2025-11-07 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 40-60 | 43/2 | 2025-11-09 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 52/1 | 2025-12-16 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 63B/6 | 2025-12-18 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 36/3 | 2025-12-24 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 60/0 | 2025-12-25 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 64/0 | 2025-12-29 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 78A/0 | 2026-01-03 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 38/1 | 2026-01-11 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 82/0 | 2026-01-16 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 77/0 | 2026-01-20 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 38/3 | 2026-01-28 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 73/0 | 2026-03-22 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 32/0 | 2026-03-25 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 76/2 | 2026-03-25 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 84/2 | 2026-03-25 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 38/4 | 2026-04-01 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 80/0 | 2026-04-01 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 64/4 | 2026-04-05 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 93B/0 | 2026-04-07 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 71/0 | 2026-04-08 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 41/2 | 2026-04-13 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 69/0 | 2026-04-17 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 70/0 | 2026-04-18 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 66/1 | 2026-04-25 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 67/0 | 2026-04-25 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 37/0 | 2026-04-27 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 53/0 | 2026-04-27 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 52/0 | 2026-04-30 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 54/0 | 2026-04-30 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 38/2 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 59/0 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 87/1 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 87/2 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 65/0 | 2026-05-08 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 72/0 | 2026-05-09 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 68/0 | 2026-05-11 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 95A/0 | 2026-05-12 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 76/1 | 2026-05-13 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 80-100+ | 66/0 | 2026-05-16 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 80-100+ | 75/0 | 2026-05-16 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 80-100+ | 76/0 | 2026-05-17 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 80-100+ | 96/0 | 2026-05-17 |  |  | UNMATCHED_LOCATION
TA 421 | 4xx | Government | 60-80 | 8/11 | 2025-04-15 |  |  | UNMATCHED_LOCATION
TA 421 | 4xx | Government | 80-100+ | 4/16 | 2025-04-29 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 177/0 | 2026-05-15 | 2025-12-04 | -162 | NEGATIVE_DELAY_EXCLUDED
TA 505 | 5xx | Government | 0-20 | 171/10 | 2015-11-27 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 138/0 | 2025-11-29 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 149B/0 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 158/0 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 174B/0 | 2026-01-22 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 148C/0 | 2026-02-21 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 148B/0 | 2026-02-28 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 157/0 | 2026-03-10 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 144/0 | 2026-03-21 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 171/5 | 2026-03-21 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 143/0 | 2026-03-31 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 134/0 | 2026-04-09 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 129/0 | 2026-04-14 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 133/0 | 2026-04-14 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 129/1 | 2026-04-23 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 137/0 | 2026-05-15 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 181/2 | 2026-05-18 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 0-20 | 13/5 | 2025-03-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 0-20 | 24/1 | 2025-03-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 0-20 | 21/3 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 20-40 | 24/2 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 20-40 | 24/4 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 20-40 | 24/5 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 20-40 | 39/7 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 20-40 | 39/8 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 20-40 | 41/1 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 20-40 | 41/2 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 20-40 | 41/5 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 20-40 | 41/8 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 20-40 | 44/2 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 20-40 | 44/3 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 49/3 | 2025-05-23 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 49/2 | 2025-05-26 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 51/3 | 2025-05-26 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 47/4 | 2025-05-27 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 48/6 | 2025-06-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 47/6 | 2025-06-04 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 49/5 | 2025-06-06 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 48/9 | 2025-06-10 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 65/1 | 2025-06-18 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 66/7 | 2025-06-27 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 65/3 | 2025-06-30 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 63/2 | 2025-07-16 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 41/4 | 2025-08-06 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 21/0 | 2025-08-12 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 64/1 | 2025-10-30 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 47/2 | 2025-11-05 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 47/7 | 2025-11-06 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 47/3 | 2025-11-13 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 66/3 | 2025-11-18 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 23/0 | 2025-11-29 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 65/0 | 2025-12-02 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 56/2 | 2025-12-19 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 48/3 | 2026-01-04 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 26/0 | 2026-02-06 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 53A/0 | 2026-03-14 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 39/6 | 2026-03-21 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 41/7 | 2026-03-26 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 53B/0 | 2026-03-30 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 39/10 | 2026-03-31 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 48/0 | 2026-04-05 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 65/4 | 2026-04-05 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 39/11 | 2026-04-08 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 35/0 | 2026-04-09 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 41/3 | 2026-04-10 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 4/6 | 2026-04-16 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 4/4 | 2026-04-18 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 54/0 | 2026-04-18 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 4/3 | 2026-04-20 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 39/9 | 2026-04-25 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 3/1 | 2026-04-29 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 4/5 | 2026-05-02 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 45/2 | 2026-05-04 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 50/0 | 2026-05-05 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 4/0 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 3/0 | 2026-05-12 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 47/9 | 2026-05-14 |  |  | UNMATCHED_LOCATION
TA 510 | 5xx | Government | 0-20 | 155/1 | 2025-02-12 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 155/3 | 2025-02-18 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 155/4 | 2025-02-18 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 155/5 | 2025-02-23 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 156/0 | 2025-03-05 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 156/1 | 2025-03-05 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 156/3 | 2025-03-13 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 156/4 | 2025-03-21 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 139/1 | 2025-03-26 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 156/2 | 2025-03-26 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 138/0 | 2025-04-05 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 137/0 | 2025-04-14 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 138/1 | 2025-04-14 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 139/5 | 2025-04-14 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 139/4 | 2025-04-23 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 136/0 | 2025-04-25 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 143/2 | 2025-05-30 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 144/0 | 2025-06-01 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 133/2 | 2025-08-31 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 138/2 | 2025-09-19 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 138/3 | 2025-11-18 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 147/2 | 2026-01-01 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 147/1 | 2026-01-08 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 192/7 | 2026-01-09 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 192/12 | 2026-01-16 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 142/0 | 2026-01-27 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 148/0 | 2026-02-01 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 157B/0 | 2026-02-16 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 157A/0 | 2026-02-17 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 157/2 | 2026-03-14 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 139/0 | 2026-04-01 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 192/9 | 2026-04-02 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 139/3 | 2026-04-04 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 153/0 | 2026-04-04 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 193/2 | 2026-04-08 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 193/1 | 2026-04-12 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 131/1 | 2026-04-13 |  |  | UNMATCHED_LOCATION | Pile
TA 510 | 5xx | Government | 20-40 | 193/5 | 2026-04-14 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 193/0 | 2026-04-19 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 193/4 | 2026-04-19 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 150/2 | 2026-04-22 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 157B/1 | 2026-04-22 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 192/8 | 2026-04-29 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 194/0 | 2026-04-30 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 167/2 | 2026-05-07 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 133/0 | 2026-05-09 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 167/3 | 2026-05-11 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 167/4 | 2026-05-17 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 133/1 | 2026-05-19 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 155/2 | 2026-05-20 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 167/1 | 2026-05-20 |  |  | UNMATCHED_LOCATION | FDN
TA 512 | 5xx | Government | 0-20 | 7/2 | 2025-05-04 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 20-40 | 5/8 | 2025-05-19 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 20-40 | 31/11 | 2025-06-10 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 20-40 | 27/2 | 2025-06-17 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 20-40 | 27/3 | 2025-06-20 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 20-40 | 16/2 | 2025-07-10 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 20-40 | 4/3 | 2025-07-17 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 20-40 | 1A/3 | 2025-07-20 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 40/2 | 2025-07-25 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 31/24 | 2025-07-29 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 40/4 | 2025-08-03 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 31/21 | 2025-08-07 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 2/1 | 2025-08-13 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 30/16 | 2025-08-22 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 31/22 | 2025-08-22 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 29/18 | 2025-09-03 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 36/9 | 2025-09-03 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 4/5 | 2025-09-03 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 37/6 | 2025-09-06 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 34/2 | 2025-09-09 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 36/5 | 2025-09-21 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 36/4 | 2025-09-26 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 29/19 | 2025-10-01 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 36/2 | 2025-10-12 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 30/0 | 2025-10-17 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 3/1 | 2025-10-23 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 12/0 | 2025-10-27 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 3/2 | 2025-10-28 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 31/0 | 2025-10-30 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 40/1 | 2025-10-30 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 37/1 | 2025-11-03 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 40/0 | 2025-11-10 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 16/1 | 2025-11-11 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 39/0 | 2025-11-14 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 38/2 | 2025-11-16 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 30/1 | 2025-11-18 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 29/16 | 2025-11-24 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 38/1 | 2025-11-24 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 32/0 | 2025-11-25 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 32/4 | 2025-11-28 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 3/0 | 2025-11-29 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 21/0 | 2025-12-01 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 32/1 | 2025-12-01 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 2A/5 | 2025-12-02 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 32/3 | 2025-12-02 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 32/6 | 2025-12-06 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 2A/3 | 2025-12-09 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 2A/2 | 2025-12-12 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 4/2 | 2025-12-12 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 20A/0 | 2025-12-13 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 4/1 | 2025-12-14 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 2A/1 | 2025-12-16 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 32/7 | 2025-12-16 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 2A/0 | 2025-12-25 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 36/0 | 2025-12-26 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 22/0 | 2025-12-27 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 27/1 | 2025-12-27 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 36/1 | 2025-12-30 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 23/0 | 2026-01-04 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 33A/0 | 2026-01-05 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 42/0 | 2026-01-11 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 13/1 | 2026-01-12 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 34/0 | 2026-01-13 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 43/0 | 2026-01-16 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 2/0 | 2026-01-20 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 33/1 | 2026-01-31 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 10/0 | 2026-02-02 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 16/3 | 2026-02-07 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 32/8 | 2026-02-19 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 32/9 | 2026-02-22 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 33/0 | 2026-03-03 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 44/0 | 2026-03-09 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 17/0 | 2026-04-03 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 47/0 | 2026-04-08 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 18/0 | 2026-04-12 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 44/1 | 2026-04-15 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 45/0 | 2026-04-24 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 46/0 | 2026-04-24 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 34/1 | 2026-04-29 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 11/7 | 2026-05-09 |  |  | UNMATCHED_LOCATION
TA 513 | 5xx | Government | 0-20 | 51/2 | 2025-12-06 | 2025-05-10 | -210 | NEGATIVE_DELAY_EXCLUDED | S-P
TA 513 | 5xx | Government | 0-20 | 24/2 | 2025-03-30 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 24/1 | 2025-04-02 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 30/2 | 2025-04-09 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 23/6 | 2025-04-12 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 23/5 | 2025-04-14 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 31/1 | 2025-04-14 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 37/1 | 2025-04-17 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 30/3 | 2025-04-21 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 30/1 | 2025-04-22 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 31/2 | 2025-04-23 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 30/2 | 2025-04-24 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 24/3 | 2025-04-26 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 52/5 | 2025-05-05 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 55/3 | 2025-05-06 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 55/7 | 2025-05-11 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 64/2 | 2025-05-11 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 64/5 | 2025-05-11 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 3/5 | 2025-05-16 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 3/6 | 2025-05-20 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 23/3 | 2025-05-21 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 3/10 | 2025-05-24 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 32B/1 | 2025-05-25 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 21/6 | 2025-05-30 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 21/7 | 2025-05-30 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 23/1 | 2025-06-03 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 23/3 | 2025-06-05 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 23/2 | 2025-06-07 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 23/4 | 2025-06-11 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 14/4 | 2025-06-20 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 18/4 | 2025-06-20 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 26/1 | 2025-06-28 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 14/3 | 2025-07-02 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 56/4 | 2025-07-05 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 14/2 | 2025-07-07 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 15B/4 | 2025-07-15 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 55/0 | 2025-07-20 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 36/3 | 2025-07-26 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 56/3 | 2025-08-19 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 36/4 | 2025-08-21 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 30/0 | 2025-09-10 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 24/0 | 2025-09-19 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 19/0 | 2025-09-25 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 28/0 | 2025-09-30 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 18/0 | 2025-10-04 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 51/5 | 2025-12-19 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 52/3 | 2026-02-17 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 55/2 | 2026-03-28 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 52/2 | 2026-04-22 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 52/0 | 2026-04-24 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 55/4 | 2026-04-27 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 30/0 | 2026-05-04 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 52/1 | 2026-05-04 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 28/1 | 2026-05-17 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 64/3 | 2026-05-19 |  |  | UNMATCHED_LOCATION | S-P
TA 601 | 6xx | Government | 0-20 | 56/7 | 2026-01-16 | 2025-12-15 | -32 | NEGATIVE_DELAY_EXCLUDED
TA 601 | 6xx | Government | 0-20 | 66/0 | 2025-05-03 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 81/2 | 2025-08-07 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 80/4 | 2025-10-27 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 77/8 | 2025-11-13 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 60/3 | 2025-11-15 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 60/8 | 2025-11-23 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 59/1 | 2025-11-29 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 77/6 | 2025-12-12 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 73/1 | 2025-12-18 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 56/1 | 2025-12-24 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 73/2 | 2025-12-24 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 79/1 | 2025-12-25 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 84/6 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 94/1 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 99/12 | 2026-01-06 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 100/3 | 2026-01-14 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 83/0 | 2026-01-14 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 59/0 | 2026-01-26 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 78/3 | 2026-02-06 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 50/1 | 2026-02-12 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 50/2 | 2026-02-17 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 89/1 | 2026-03-03 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 49/10 | 2026-03-11 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 51/7 | 2026-03-13 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 49/11 | 2026-03-14 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 51/8 | 2026-03-14 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 51/10 | 2026-03-17 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 90/0 | 2026-03-18 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 51/6 | 2026-03-19 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 52/1 | 2026-03-22 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 50/3 | 2026-03-25 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 51/2 | 2026-03-27 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 53/3 | 2026-03-31 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 70/1 | 2026-04-11 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 53/0 | 2026-04-13 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 70/2 | 2026-04-13 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 50/0 | 2026-04-16 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 70/4 | 2026-04-16 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 70/3 | 2026-04-18 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 66/1 | 2026-04-21 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 49/9 | 2026-04-23 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 67/0 | 2026-04-26 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 65/3 | 2026-04-29 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 49/8 | 2026-04-30 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 67/1 | 2026-05-05 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 48/7 | 2026-05-10 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 69/0 | 2026-05-13 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 69/2 | 2026-05-16 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 48/3 | 2026-05-19 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 69/1 | 2026-05-20 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 126/5 | 2025-10-28 | 2025-03-01 | -241 | NEGATIVE_DELAY_EXCLUDED
TA 602 | 6xx | Government | 0-20 | 123/1 | 2025-10-07 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 124/1 | 2025-10-08 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 124/2 | 2025-10-15 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 123/3 | 2025-10-19 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 124/3 | 2025-11-04 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 123/4 | 2025-11-06 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 123/2 | 2025-11-13 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 126/10 | 2025-11-14 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 111/3 | 2025-11-19 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 103/2 | 2025-11-20 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 126/2 | 2025-11-21 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 111/4 | 2025-11-23 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 103/3 | 2025-11-24 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 103/1 | 2025-11-28 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 111/5 | 2025-11-28 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 110/2 | 2025-11-30 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 121/5 | 2025-11-30 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 110/1 | 2025-12-03 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 134/6 | 2025-12-06 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 99/1 | 2025-12-06 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 102/9 | 2025-12-07 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 109/10 | 2025-12-07 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 110/3 | 2025-12-11 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 109/11 | 2025-12-12 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 136/7 | 2025-12-12 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 99/2 | 2025-12-13 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 102/8 | 2025-12-15 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 108/7 | 2025-12-16 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 110/4 | 2025-12-19 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 136/9 | 2025-12-19 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 109/7 | 2025-12-20 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 108/5 | 2025-12-22 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 136/6 | 2025-12-22 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 109/9 | 2025-12-24 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 139/3 | 2025-12-24 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 89/9 | 2025-12-24 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 107/2 | 2025-12-26 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 108/6 | 2025-12-26 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 109/6 | 2025-12-27 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 89/8 | 2025-12-28 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 109/5 | 2025-12-30 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 89/7 | 2025-12-30 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 107/1 | 2026-01-03 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 89/6 | 2026-01-04 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 129A/1 | 2026-01-07 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 89/5 | 2026-01-10 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 108/4 | 2026-01-11 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 129A/5 | 2026-01-11 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 108/1 | 2026-01-17 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 76/2 | 2026-01-20 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 77/1 | 2026-01-24 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 107/4 | 2026-01-25 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 129A/7 | 2026-01-27 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 76/1 | 2026-01-27 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 139/6 | 2026-01-28 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 127/7 | 2026-01-30 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 129A/2 | 2026-01-30 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 76/6 | 2026-01-31 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 82/2 | 2026-02-02 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 127/4 | 2026-02-03 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 129A/10 | 2026-02-05 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 82/3 | 2026-02-08 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 127/1 | 2026-02-09 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 127/2 | 2026-02-13 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 70/3 | 2026-02-13 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 129A/6 | 2026-02-16 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 121/10 | 2026-02-17 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 70/1 | 2026-02-23 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 125/1 | 2026-02-28 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 126/7 | 2026-03-03 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 70/2 | 2026-03-07 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 124/5 | 2026-03-14 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 76/5 | 2026-03-21 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 88/2 | 2026-03-30 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 88/1 | 2026-04-02 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 127/3 | 2026-04-03 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 124/0 | 2026-04-08 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 87/4 | 2026-04-08 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 102/11 | 2026-04-11 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 139/4 | 2026-04-11 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 69/2 | 2026-04-13 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 87/5 | 2026-04-14 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 121/9 | 2026-04-15 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 71/1 | 2026-04-18 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 87/2 | 2026-04-18 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 69/1 | 2026-04-21 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 109/8 | 2026-04-22 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 125/0 | 2026-04-23 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 136/0 | 2026-04-24 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 71/2 | 2026-04-24 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 87/3 | 2026-04-25 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 69/3 | 2026-04-28 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 127/0 | 2026-04-30 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 139/0 | 2026-04-30 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 71/3 | 2026-04-30 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 88/3 | 2026-04-30 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 108/0 | 2026-05-04 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 139/1 | 2026-05-04 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 71/4 | 2026-05-04 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 107/0 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 69/4 | 2026-05-08 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 126/0 | 2026-05-12 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 88/0 | 2026-05-15 |  |  | UNMATCHED_LOCATION
TB 501 | 5xx | Private | 80-100+ | 8D/0A | 2025-12-07 | 2025-12-04 | -3 | NEGATIVE_DELAY_EXCLUDED | 220kV | 220kV
TB 501 | 5xx | Private | 80-100+ | 6/0 | 2026-02-19 | 2026-02-17 | -2 | NEGATIVE_DELAY_EXCLUDED | 132kV | 132kV
TB 501 | 5xx | Private | 80-100+ | 34/0 (New) | 2026-04-30 |  |  | UNMATCHED_LOCATION | 220kV
TB 507 | 5xx | Private | 20-40 | 71/2 | 2025-10-30 | 2025-01-14 | -289 | NEGATIVE_DELAY_EXCLUDED | MAIN | MAIN
TB 507 | 5xx | Private | 0-20 | 86/2 | 2025-02-22 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 66/2 | 2025-03-06 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 64/3 | 2025-03-07 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 96/2 | 2025-03-07 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 64/4 | 2025-03-10 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 99/1 | 2025-03-10 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 66/3 | 2025-03-11 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 87/1 | 2025-03-24 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 64/6 | 2025-03-30 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 87/2 | 2025-03-30 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 64/5 | 2025-03-31 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 71/1 | 2025-04-09 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 91/2 | 2025-04-16 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 51/2 | 2025-04-17 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 95/2 | 2025-04-20 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 51/3 | 2025-04-23 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 99/2 | 2025-04-25 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 104B/1 | 2025-04-29 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 62/4 | 2025-04-29 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 100/1 | 2025-05-18 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 99C/2 | 2025-05-25 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 105/0 | 2025-05-28 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 62/5 | 2025-05-31 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 96/0 | 2025-06-06 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 119/0 | 2025-06-15 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 74/0 | 2025-06-20 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 106/0 | 2025-07-06 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 125/1 | 2025-07-14 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 125/0 | 2025-07-24 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 94/0 | 2025-07-24 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 99/3 | 2025-07-29 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 99/0 | 2025-08-14 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 87/0 | 2025-08-22 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 99/4 | 2025-08-22 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 63/1 | 2025-08-24 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 56/4 | 2025-08-26 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 56/2 | 2025-08-27 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 56/5 | 2025-08-31 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 99A/0 | 2025-08-31 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 57/0 | 2025-09-10 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 59/0 | 2025-09-12 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 64/0 | 2025-09-14 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 58/0 | 2025-09-17 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 125/2 | 2025-09-18 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 72/1 | 2025-09-19 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 56/1 | 2025-09-20 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 48/0 | 2025-09-25 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 89/0 | 2025-11-12 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 71/0 | 2025-11-14 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 88/0 | 2025-12-05 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 98B/2 | 2025-12-08 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 117/0 | 2025-12-13 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 104A/0 | 2025-12-30 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 124/0 | 2025-12-30 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 122/2 | 2026-01-08 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 126/3 | 2026-01-15 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 69/3 | 2026-01-15 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 108/0 | 2026-01-20 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 10/3 | 2026-01-23 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 109/0 | 2026-01-23 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 7/0 | 2026-02-11 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 10/12 | 2026-02-12 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 6/2 | 2026-02-16 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 6/1 | 2026-02-20 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 1/0 | 2026-02-28 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 117/2 | 2026-02-28 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 4/0 | 2026-02-28 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 6/0 | 2026-02-28 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 157/0 | 2026-03-04 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 156/0 | 2026-03-10 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 98B/1 | 2026-03-11 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 2/0 | 2026-03-13 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 2/2 | 2026-03-15 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 2/3 | 2026-03-16 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 2/4 | 2026-03-17 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 103/0 | 2026-03-19 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 3/0B | 2026-03-26 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 2/5 | 2026-03-27 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 3/0A | 2026-03-28 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 5/2 | 2026-03-31 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 5/1 | 2026-04-02 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 3/1 | 2026-04-04 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 3/1 | 2026-04-07 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 2/1B | 2026-04-08 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 2/1 A | 2026-04-09 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 103/1 | 2026-04-10 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 8/0 | 2026-04-11 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 5/0 | 2026-04-12 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 99C/0 | 2026-04-15 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 4/5 | 2026-04-16 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 3/3 | 2026-04-18 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 3/2 | 2026-04-21 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 100/0 | 2026-04-24 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 10/11 | 2026-04-28 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 3/4 | 2026-04-29 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 2/0 | 2026-05-02 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 155/0 | 2026-05-03 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 3/5 | 2026-05-05 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 154/1B | 2026-05-06 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 10/13 | 2026-05-08 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 154/2B | 2026-05-08 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 4/2 | 2026-05-08 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 154/1A | 2026-05-09 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 154/2A | 2026-05-09 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 4/4 | 2026-05-10 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 13/2 | 2026-05-14 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 4/0 | 2026-05-15 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 8/3 | 2026-05-17 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 4/1 | 2026-05-18 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 4/3 | 2026-05-19 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 8/4 | 2026-05-19 |  |  | UNMATCHED_LOCATION | MAIN
TB 605 | 6xx | Private | 0-20 | 18/0 | 2025-10-16 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 0-20 | 22/1 | 2025-10-28 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 0-20 | 21/1 | 2025-10-31 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 0-20 | 22/0 | 2025-10-31 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 0-20 | 74/0 | 2025-11-06 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 0-20 | 72/0 | 2025-11-09 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 0-20 | 22/2 | 2025-11-13 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 0-20 | 17/0 | 2025-11-23 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 0-20 | 20/0 | 2025-11-30 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 0-20 | AP116 | 2025-11-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 0-20 | AP87 | 2025-11-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 0-20 | 40/0 | 2025-12-03 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 0-20 | 23/0 | 2025-12-09 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 0-20 | 29/0 | 2025-12-10 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 0-20 | 85/1 | 2025-12-16 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 0-20 | 106/1 | 2025-12-17 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 0-20 | 102/1 | 2025-12-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 0-20 | 135/2 | 2025-12-21 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 0-20 | 139/1 | 2025-12-24 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 0-20 | 138/1 | 2025-12-26 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | 80/1 | 2025-12-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | 138/2 | 2025-12-31 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | 137/2 | 2026-01-10 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP131 | 2026-01-11 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | 152/2 | 2026-01-16 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP154 | 2026-01-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP138 | 2026-01-20 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | 153/0 | 2026-02-05 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP139 | 2026-02-06 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP15 | 2026-02-08 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 20-40 | AP155 | 2026-02-09 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP130 | 2026-02-12 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP92 | 2026-02-13 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP150 | 2026-02-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | 136/4 | 2026-02-20 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP12 | 2026-02-20 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 20-40 | AP132 | 2026-02-24 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | 70/1 | 2026-02-26 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP137 | 2026-02-27 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP21 | 2026-02-27 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 20-40 | AP91 | 2026-02-27 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP159 | 2026-02-28 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP14 | 2026-03-08 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 40-60 | AP149 | 2026-03-10 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 67/2 | 2026-03-13 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP127 | 2026-03-15 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP148 | 2026-03-16 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP71 | 2026-03-23 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP152 | 2026-03-26 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP108 | 2026-03-28 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP124 | 2026-03-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP67 | 2026-03-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 56/3 | 2026-03-31 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP125 | 2026-04-06 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 144/3 | 2026-04-07 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 65/2 | 2026-04-07 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP109 | 2026-04-12 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP126 | 2026-04-15 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP1 | 2026-04-18 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 40-60 | AP61 | 2026-04-21 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP165 | 2026-04-22 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP86 | 2026-04-23 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 56/2 | 2026-04-25 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP123 | 2026-04-26 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP59 | 2026-04-27 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 55/1 | 2026-04-28 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP142 | 2026-04-29 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP7 | 2026-04-29 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 40-60 | 122/1 | 2026-04-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP166 | 2026-04-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP6 | 2026-04-30 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 40-60 | AP64 | 2026-05-01 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 64/1 | 2026-05-07 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP144 | 2026-05-07 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP56 | 2026-05-07 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 142/1 | 2026-05-08 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 61/1 | 2026-05-08 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP82 | 2026-05-08 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 57/1 | 2026-05-09 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP161 | 2026-05-09 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP163 | 2026-05-11 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 56/4 | 2026-05-13 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 62/2 | 2026-05-14 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 71/1 | 2026-05-14 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP110 | 2026-05-14 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP38 | 2026-05-14 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 40-60 | AP57 | 2026-05-15 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 159/3 | 2026-05-16 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 40/3 | 2026-05-16 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 40-60 | 65/4 | 2026-05-16 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 50A/2 | 2026-05-17 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 40-60 | AP162 | 2026-05-17 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP60 | 2026-05-17 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 62/1 | 2026-05-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP128 | 2026-05-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP143 | 2026-05-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP63 | 2026-05-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 159/2 | 2026-05-19 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 23/2 | 2026-05-19 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 40-60 | 57/2 | 2026-05-19 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP112 | 2026-05-19 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP70/3 | 2026-05-19 |  |  | UNMATCHED_LOCATION | Punjab
TB 608 | 6xx | Private | 0-20 | 65/3 | 2025-10-18 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 75/5 | 2025-11-15 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 34/3 | 2025-11-18 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 101/0 | 2025-11-19 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 33/2 | 2025-11-22 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 90/0 | 2025-11-22 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 29/0 | 2025-11-25 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 100/0 | 2025-11-30 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 103/0 | 2025-11-30 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 109/0 | 2025-11-30 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 71/0 | 2025-11-30 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 85/0 | 2025-11-30 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 29/1 | 2025-12-02 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 69/3 | 2025-12-08 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 5/0 | 2025-12-10 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 80/0 | 2025-12-11 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 108/0 | 2025-12-12 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 111/0 | 2025-12-12 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 48/0 | 2025-12-14 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 75/4 | 2025-12-18 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 99/0 | 2025-12-18 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 102/0 | 2025-12-19 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 84/0 | 2025-12-19 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 111/1 | 2025-12-21 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 83/0 | 2025-12-21 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 91/0 | 2025-12-21 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 93/0 | 2025-12-21 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 34/1 | 2025-12-22 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 25/1 | 2025-12-23 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 4/1 | 2025-12-25 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 112/0 | 2025-12-27 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 49/0 | 2025-12-27 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 91/1 | 2025-12-27 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 79/1 | 2025-12-28 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 91/2 | 2025-12-28 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 114/0 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 86/0 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 94/0 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 41/2 | 2026-01-02 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 11/2 | 2026-01-03 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 97/0 | 2026-01-09 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 113/0 | 2026-01-11 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 91/5 | 2026-01-12 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 110/0 | 2026-01-13 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 115/0 | 2026-01-14 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 8/0 | 2026-01-14 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 76/0 | 2026-01-15 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 69/4 | 2026-01-18 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 75/1 | 2026-01-19 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 50/0 | 2026-01-21 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 11/1 | 2026-01-24 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 123/2 | 2026-01-25 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 129/1 | 2026-01-27 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 34/2 | 2026-01-27 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 47/1 | 2026-01-28 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 79/0 | 2026-01-28 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 132/1 | 2026-01-29 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 91/7 | 2026-01-29 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 96/0 | 2026-01-30 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 128/0 | 2026-01-31 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 131/0 | 2026-01-31 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 75/2 | 2026-01-31 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 91/4 | 2026-01-31 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 59/1 | 2026-02-05 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 73/6 | 2026-02-05 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 76/1 | 2026-02-05 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 96/1 | 2026-02-05 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 104/0 | 2026-02-08 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 42/1 | 2026-02-08 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 126/0 | 2026-02-10 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 43/0 | 2026-02-10 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 72/7 | 2026-02-11 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 9/1 | 2026-02-11 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 78/2 | 2026-02-12 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 95/3 | 2026-02-14 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 95/1 | 2026-02-16 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 129/2 | 2026-02-18 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 6/1 | 2026-02-18 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 95/0 | 2026-02-18 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 131/1 | 2026-02-19 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 44/0 | 2026-02-19 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 30/0 | 2026-02-20 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 10/3 | 2026-02-22 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 124/0 | 2026-02-22 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 70/1 | 2026-02-23 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 127/0 | 2026-02-25 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 132/2 | 2026-02-28 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 132/3 | 2026-02-28 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 95/2 | 2026-02-28 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 31/0 | 2026-03-06 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 35/0 | 2026-03-08 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 10/1 | 2026-03-10 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 129/0 | 2026-03-10 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 130/0 | 2026-03-10 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 82/2 | 2026-03-10 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 82/1 | 2026-03-11 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 116/0 | 2026-03-12 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 27/0 | 2026-03-14 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 125/0 | 2026-03-19 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 47/0 | 2026-03-28 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 40-60 | 132/0 | 2026-03-29 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 40-60 | 34/0 | 2026-03-31 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 40-60 | 7/2 | 2026-03-31 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 40-60 | 92/0 | 2026-04-13 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 40-60 | 107/1 | 2026-04-19 |  |  | UNMATCHED_LOCATION

## Scope Snapshot
Scope Snapshot
Project | Project Rollup Key | Project Base Code | Series | Ownership | Scope Total | Scope Source | Scope Report Date | Status Rows Considered | Status Rows Used | Duplicate Rows Dropped | Quantity Primary Sum | Cumulative Progress Sum | Balance Progress Sum | Fallback Foundation Done Count | Coverage Status | Coverage Reason | Note
TA 413 | ta413 | TA 413 | 4xx | Government | 632 | status_quantity_primary_latest | 2026-05-19 | 2 | 2 | 0 | 632 | 632 | 0 | 314 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 414 | ta414 | TA 414 | 4xx | Government | 352 | status_quantity_primary_latest | 2026-05-21 | 1 | 1 | 0 | 352 | 316 | 36 | 327 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 416 | ta416 | TA 416 | 4xx | Government | 302 | status_quantity_primary_latest | 2026-05-17 | 1 | 1 | 0 | 302 | 302 | 0 | 303 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 418 | ta418 | TA 418 | 4xx | Government | 127 | status_quantity_primary_latest | 2026-05-21 | 1 | 1 | 0 | 127 | 127 | 0 | 129 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 419 | ta419 | TA 419 | 4xx | Government | 330 | status_quantity_primary_latest | 2026-05-18 | 1 | 1 | 0 | 330 | 247 | 83 | 268 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 421 | ta421 | TA 421 | 4xx | Government | 309 | status_quantity_primary_latest | 2026-05-18 | 1 | 1 | 0 | 309 | 309 | 0 | 303 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 505 | ta505 | TA 505 | 5xx | Government | 379 | status_quantity_primary_latest | 2026-05-19 | 1 | 1 | 0 | 379 | 374 | 7 | 373 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 509 | ta509 | TA 509 | 5xx | Government | 309 | status_quantity_primary_latest | 2026-05-18 | 1 | 1 | 0 | 309 | 264 | 45 | 264 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 510 | ta510 | TA 510 | 5xx | Government | 293 | status_quantity_primary_latest | 2026-05-20 | 1 | 1 | 0 | 293 | 79 | 214 | 85 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 512 | ta512 | TA 512 | 5xx | Government | 315 | status_quantity_primary_latest | 2026-05-20 | 1 | 1 | 0 | 315 | 0 | 302 | 297 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 513 | ta513 | TA 513 | 5xx | Government | 619 | status_quantity_primary_latest | 2026-05-19 | 2 | 2 | 0 | 619 | 81 | 538 | 83 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 601 | ta601 | TA 601 | 6xx | Government | 292 | status_quantity_primary_latest | 2026-05-20 | 2 | 2 | 0 | 292 | 120 | 172 | 120 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 602 | ta602 | TA 602 | 6xx | Government | 478 | status_quantity_primary_latest | 2026-05-18 | 1 | 1 | 0 | 478 | 143 | 335 | 143 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TB 501 | tb501 | TB 501 | 5xx | Private | 238 | status_quantity_primary_latest | 2026-05-20 | 2 | 2 | 0 | 238 | 235 | 3 | 231 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TB 507 | tb507 | TB 507 | 5xx | Private | 556 | status_quantity_primary_latest | 2026-05-19 | 2 | 2 | 0 | 556 | 334 | 222 | 331 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TB 605 | tb605 | TB 605 | 6xx | Private | 523 | status_quantity_primary_latest | 2026-05-20 | 1 | 1 | 0 | 523 | 340 | 183 | 288 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TB 608 | tb608 | TB 608 | 6xx | Private | 318 | status_quantity_primary_latest | 2026-04-05 | 9 | 9 | 0 | 318 | 137 | 181 | 132 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).