## FDN-June25 (hidden)
Project Code |  |  | TA-416
Name of Line |  |  | NEEMRANA-II-BAREILLY (PG) 765KV D/C LINE,WZ-5 (Part-III)
Activity |  |  | Foundation | Qty
|  |  | Total | 302
|  |  | Completed (May-25) | 301
|  |  | Balance | 1
Micro Plan for month |  |  | 2025-06-01 | 1 | Nos | 4925228.89 | Rs. Cr.
Achievement for Month |  |  | Wk-1 | 1 | 100% | 4925228.89 | 100%
|  |  | Wk-2 | 0 | 0% | 0 | 0%
|  |  | Wk-3 | 0 | 0% | 0 | 0%
|  |  | Wk-4 | 0 | 0% | 0 | 0%
|  |  | Wk-5 | 0 | 0% | 0 | 0%
Actual for the Month |  |  | Total | 1 | 1 | 4925228.89 | 1
Sl | Loc No. | Tower type | Classification | Conc. Vol (CuM) | Reinf (MT) | Sub-Cont | Work Plan | [7 empty] | Revenue | Actual Completion | Physical Completion | [5 empty] | Revenue Achievement | [5 empty] | Shortfall
[7 empty] | Excavation |  | Stub-setting |  | Concreting |  | Earthing | Backfilling |  |  | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total
[7 empty] | Start | End | Start | End | Start | End |  |  | Rs. Lacs. | Date | [11 empty] | Rs. Lacs. | Rs. Lacs.
1 | 38/0 | DC2+18 | FS | 261.196 | 15.029 | AVI | 2025-05-21 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 4925228.89 | 2025-06-03 | 1 |  |  |  |  | 1 | 4925228.89 | 0 | 0 | 0 | 0 | 4925228.89 | 0
2 | [21 empty] | 0 |  |  |  |  | 0 | 0 | 0
3 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 261.196 | 15.029 | [9 empty] | 4925228.89 |  | 1 | 0 | 0 | 0 | 0 | 1 | 4925228.89 | 0 | 0 | 0 | 0 | 4925228.89 | 0
[13 empty] | STUB Setting-1 |  | 7224.33
[13 empty] | Earthing-1 |  | 7782.57
[13 empty] | Total Reve |  | 4940235.79

## Stub dispatch (hidden)
Location | Project | Tower type | Structure | B LOT | Actual PRS Date | STEEL Wt (MT) | BNA Wt | Disp Bal | May'24 Disp Plan | Wk01 | WK02 | WK03 | WK04 | Jun'24 Disp Plan MT | July'24 Disp Plan | Remark
JPR | TA416 | DA | Stub - 28 Nos | TA416-00018 | 2024-04-11 | 26.8617 | 0.46323 | 26.8617 | 0 |  |  |  | 0 | 26.8617 | 0 | As on date 160 stub reieved.
JPR | TA416 | DA | Stub - 132 Nos | TA416-00026 | 2024-04-15 | 126.634 | 2.184 | 126.634 | [5 empty] | 126.634 | 0
Total |  |  | 160 | [10 empty] | 153.4957

## Erection-Nov25
Sl | Location No. | Tower type | Tower Weight | Gang Name | Manpower | Section Incharge | Supervisor | Power Tools Issued (YES/NO) | Material Feeding | Starting Date | Completion Date | Tack-welding | Final checking | Revenue Planned | Revenue Realised
1 | 33/0 | DD45+18 | 89.029 | M/s TOFIT MIA | 28 | Ajith | Rahman |  | 2025-10-16 | 2025-10-19 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 1150500
2 | 33/4 | DA+3 | 29.122 | M/s TOFIT MIA | 28 | Ajith | Rahman |  | 2025-11-05 | 2025-11-06 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 360000
3 | 43/2 | DA+0 | 27.963 | M/s TOFIT MIA | 28 | Ajith | Rahman |  | 2025-11-10 | 2025-11-11 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 308000
4 | 43/3 | DA-3 | 26.846 | M/s TOFIT MIA | 28 | Ajith | Rahman |  | 2025-11-14 | 2025-11-15 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 295000
5 | 44/1 | DA+0 | 27.963 | M/s TOFIT MIA | 28 | Ajith | Rahman |  | 2025-11-18 | 2025-11-19 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 308000
6 | 38/0 | DD60+6 | 73.176 | M/s TOFIT MIA | 28 | Ajith | Rahman |  | 2025-11-23 | 2025-11-24 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 809000
7 | 46/10 | DA-3 | 26.846 | M/s BARKAT ALI | 25 | Ajith | Jitender Kumar |  | 2025-10-29 | 2025-10-30 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 295000
8 | 46/6 | DA+0 | 27.963 | M/s BARKAT ALI | 25 | Ajith | Jitender Kumar |  | 2025-11-05 | 2025-11-06 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 308000
9 | 46/11 | DA-1.5 | 27.601 | M/s BARKAT ALI | 25 | Ajith | Jitender Kumar |  | 2025-11-11 | 2025-11-12 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 304000
10 | 46/1 | DA-3 | 26.846 | M/s BARKAT ALI | 25 | Ajith | Jitender Kumar |  | 2025-11-16 | 2025-11-17 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 295000
11 | 48/0 | DB2+0 | 45.136 | M/s BARKAT ALI | 25 | Ajith | Jitender Kumar |  | 2025-11-22 | 2025-11-23 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 488000
12 | 39/0 | DD45+18 | 89.029 | M/s MDPL | 24 | Ajith | Prabhu Prasad |  | 2025-10-16 | 2025-10-19 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 1151000
13 | 47/0 | DC1+0 | 51.673 | M/s MDPL | 24 | Ajith | Prabhu Prasad |  | 2025-11-07 | 2025-11-08 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 562000
14 | 47/1 | DA+3 | 29.122 | M/s MDPL | 24 | Ajith | Prabhu Prasad |  | 2025-11-14 | 2025-11-15 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 360000
15 | 54/2 | DA-3 | 26.846 | M/s MDPL | 24 | Ajith | Prabhu Prasad |  | 2025-11-19 | 2025-11-20 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 295000
16 | 52/1 | DA-3 | 26.846 | M/s MDPL | 24 | Ajith | Prabhu Prasad |  | 2025-11-24 | 2025-11-25 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 295000
17 | 52/2 | DA-3 | 26.846 | Team - 04 | 25 | Ajith | Basudev Mahato |  | 2025-11-08 | 2025-11-09 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 295000
18 | 56/1 | DA+6 | 33.304 | Team - 04 | 25 | Ajith | Basudev Mahato |  | 2025-11-13 | 2025-11-14 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 374000
19 | 56/2 | DA-3 | 26.846 | Team - 04 | 25 | Ajith | Basudev Mahato |  | 2025-11-18 | 2025-11-19 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 295000
20 | 56/3 | DB1+6 | 52.141 | Team - 04 | 25 | Ajith | Basudev Mahato |  | 2025-11-23 | 2025-11-24 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 594000
Formulas:
Starting Date = [Material Feeding]+3
Tack-welding = [Completion Date]+1
Final checking = [Tack-welding]+1

## Stringing- Nov25
Name of the line : '765KV D/C KOPPAL II(PS) - RAICHUR TL (Part-1)
Powergrid Koppal - Gadag Transmission Limited (Power Grid Corporation of India)
Executing Agency:- KEC International Limited
Datewise Stringing planning for the month of November 2025
Micro Plan - Stringing
S. No. | From AP | To AP | Span (m) | Tower Erection Status | Towers in Section | Insulator Hoisting | Paying Out Start | Paying Out Completed | Final Sag Complete | Method | Gang Name | Gang Strength | Supervisor | Section Incharge
1 | 36/0 | 36/1 | 0.48 | Complete | 0 | 2025-10-30 | 2025-11-01 | 2025-11-03 | 2025-11-05 | D1 | M/s SUFIYAN |  | A | D
2 | 35/0 | 36/0 | 4.48 | Complete | 11 | 2025-11-16 | 2025-11-05 | 2025-11-13 | 2025-11-15 | D1 | M/s SUFIYAN |  | A | D
3 | 34/0 | 35/0 | 1.98 | Complete | 4 | 2025-11-23 | 2025-11-15 | 2025-11-21 | 2025-11-23 | D1 | M/s SUFIYAN |  | B | D
4 | 40/0 | 41/0 | 2.46 | Complete | 5 | 2025-11-10 | 2025-11-23 | 2025-11-30 | 2025-12-02 | D2 | M/s SUFIYAN |  | B | D

## STG-Sep25 (hidden)
Project Code
Name of Line
Activity |  |  | Stringing | Qty |  |  |  |  | Rate @Kms | 905812
|  |  | Total | 115
|  |  | Completed (Aug-25) | 32.6
|  |  | Balance | 82.4
Micro Plan for month |  |  | 2025-09-01 | 23.985 | km | 21725900.82 | Rs. Cr
Achievement for Month |  |  | Wk-1 | 0 | 0% | 0 | 0%
|  |  | Wk-2 | 0 | 0% | 0 | 0%
|  |  | Wk-3 | 0 | 0% | 0 | 0%
|  |  | Wk-4 | 0 | 0% | 0 | 0%
|  |  | Wk-5 | 0 | 0% | 0 | 0%
|  |  | Total | 0 | 0% | 0 | 0%
Sl | Section | Section Length (km) | Manual/TSE | Sub-Cont | Work Plan |  |  |  |  | Revenue | Actual Completion | Physical Completion | [5 empty] | Revenue Achievement | [5 empty] | Shortfall
[5 empty] | Matl feeding | Pay-Out |  | Final Sag |  |  |  | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total
[6 empty] | Start | End | Start | End | Rs. Cr. | Date | [11 empty] | Rs. Cr. | Rs. Cr.
1 | 14/0-15/0 | 3.611 | TSE | Anarul | 2025-08-30 | 2025-09-01 | 2025-09-08 | 2025-09-09 | 2025-09-12 | 3270887.132 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3270887.132
2 | 12/0-13/0 | 3.92 | TSE |  | 2025-09-13 | 2025-09-14 | 2025-09-19 | 2025-09-20 | 2025-09-22 | 3550783.04 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3550783.04
3 | 3/0-4/0 | 0.28 | Manual-1 |  | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-12 | 2025-09-12 | 253627.36 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253627.36
4 | 11/0-12/0 | 0.313 | Manual-1 |  | 2025-09-27 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 283519.156 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283519.156
5 | 13/0-14/0 | 0.319 | Manual-1 |  | 2025-09-15 | 2025-09-16 | 2025-09-16 | 2025-09-16 | 2025-09-16 | 288954.028 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288954.028
6 | 20/0-21/0 | 4.958 | TSE | Pankaj | 2025-09-03 | 2025-09-04 | 2025-09-09 | 2025-09-10 | 2025-09-13 | 4491015.896 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4491015.896
7 | 21/0-22/0 | 1.606 | TSE |  | 2025-09-14 | 2025-09-15 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 1454734.072 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1454734.072
8 | 18/0-19/0 | 0.323 | Manual-1 |  | 2025-09-20 | 2025-09-21 | 2025-09-26 | 2025-09-27 | 2025-09-30 | 292577.276 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292577.276
9 | 36/0-37/0 | 4.947 | TSE |  | 2025-08-30 | 2025-08-31 | 2025-09-06 | 2025-09-07 | 2025-09-10 | 4481051.964 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4481051.964
10 | 30/0-31/0 | 2.75 | TSE |  | 2025-09-11 | 2025-09-12 | 2025-09-17 | 2025-09-18 | 2025-09-21 | 2490983 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2490983
11 | 29/0-30/0 | 0.27 | TSE |  | 2025-09-20 | 2025-09-20 | 2025-09-20 | 2025-09-22 | 2025-09-22 | 244569.24 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244569.24
12 | 28/0-29/0 | 0.688 | Manual-2 |  | 2025-09-27 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 623198.656 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 623198.656
13 | [9 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 23.985 | [7 empty] | 21725900.82 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21725900.82