## FoundationRaw
project_code | project_display | project_scope_key | line_name | line_name_source | report_date | event_date | source_file | source_sheet | configured_sheet | source_type | quality_flag | location_no | status_text | cumulative_foundation | fallback_note
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-06 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-07 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-09 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-11 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/11 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-17 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-17 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 15/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-18 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 15/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-21 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 15/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-23 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-24 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 15/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-26 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-27 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 15/6 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-28 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/10 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-29 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-03 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 15/9 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-03 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/6 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-06 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 15/8 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-06 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/9 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-09 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/7 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-10 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-10 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/8 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-10 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 15/10 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-11 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 15/7 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-15 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/7 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-18 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 15/11 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-19 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/8 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-20 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-22 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/6 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-24 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-25 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/9 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-25 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-28 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/10 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-29 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-31 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-03 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-03 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-08 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-08 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29A/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-10 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-13 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/10 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-14 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29A/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-16 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 27/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-17 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7A/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-18 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/8 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-20 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29A/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-20 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-23 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7A/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-24 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29A/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-25 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-26 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-27 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29A/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-27 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-28 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 27/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-30 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-30 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/6 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-31 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29A/6 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7A/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4A/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-04 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/10 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-04 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/7 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-05 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/12 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-06 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7A/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-06 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4A/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-07 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-09 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-09 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4A/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-10 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7A/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-10 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-12 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4A/6 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-12 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/7 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-13 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/12 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-13 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-14 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/11 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-15 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/6 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-15 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36A/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-15 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-16 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4A/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-18 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-19 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36A/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-20 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/11 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-20 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-20 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 27/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-21 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4A/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-21 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-23 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/6 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-23 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-23 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-25 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-26 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-27 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-27 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-28 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/6 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-28 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 27/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-29 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/10 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-30 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/8 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-30 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4A/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/9 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-03 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-04 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/7 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-05 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36A/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-05 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/8 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-07 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/9 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-07 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/9 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-08 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-08 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 27/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-09 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/6 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-09 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/9 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-12 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/10 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-12 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-12 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/10 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-14 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 27/6 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-14 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-16 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/7 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-16 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-16 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/11 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-17 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/7 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-18 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-19 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-19 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/7 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-21 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37A/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-22 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/6 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-22 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-23 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-25 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-25 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/8 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-25 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37A/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-27 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/9 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-29 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-29 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/8 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-30 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37A/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-07 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29A/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-08 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/8 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-08 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37A/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-09 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/11 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-11 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/9 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-12 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-12 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37A/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-16 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-17 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-19 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-20 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-20 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/8 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-21 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-21 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/9 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-22 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7A/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-23 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-23 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/10 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-24 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-26 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/7 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-27 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-27 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37A/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-29 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-29 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/6 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-30 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-04 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-04 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/6 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-06 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-06 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-07 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-08 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37A/6 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-08 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-10 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-12 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-12 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-13 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-14 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-15 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 39/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-17 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-18 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-19 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/7 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-19 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 17/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-21 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/6 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-21 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 39/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-21 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 39/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-22 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-23 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 39/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-25 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/8 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-27 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 41/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-28 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 16/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-29 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-29 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 39/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-29 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-30 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/6 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-31 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-31 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 15/12 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-03 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 42/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-03 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-05 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 39/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-05 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/9 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-06 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-07 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/6 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-08 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 42/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-09 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 39/6 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-09 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/10 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-10 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/7 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-13 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-13 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 42/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-13 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/8 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-13 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/11 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-15 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 22/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-17 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/9 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-17 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 39/7 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-19 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 41/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-20 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40A/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-21 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-21 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/10 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-21 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 43/7 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-22 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 23/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-23 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 43/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-24 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 39/8 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-24 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-25 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 43/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-25 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 43/8 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-27 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 15/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-28 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 43/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-29 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-30 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 23A/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-31 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 42/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-31 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 39/9 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-31 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-02 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 43/6 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-04 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/7 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-04 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 44/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-04 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-05 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 43/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-07 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-08 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 43/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-09 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 43/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-09 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-10 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-11 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 13/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-11 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 39/10 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-12 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-13 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/11 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-16 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 21/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-16 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-17 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/7 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-18 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 13A/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-18 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32A/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-19 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/6 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-20 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-22 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 21/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-22 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32A/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-23 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-24 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 39/11 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-25 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/9 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-25 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 27/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-26 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 28/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-26 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/7 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-27 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 24/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 44/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-05 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/8 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-05 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 26/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-06 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 15/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-06 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 44/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-08 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 25/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-08 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-12 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 44/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-13 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 44/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-16 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-17 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 44/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-23 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2A/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-23 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-23 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3B/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-26 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3B/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-27 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2A/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-30 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-30 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3B/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-30 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2A/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5A/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-03 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3A/6 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-05 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2A/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-08 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3A/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-08 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3A/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-08 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-10 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3A/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-11 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/6 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-12 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3A/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-12 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-14 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-15 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-15 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3A/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-16 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 14/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-17 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-18 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3A/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-19 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3B/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-22 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 21/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-23 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2A/6 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-24 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 21/2 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-25 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8A/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-25 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-29 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 21/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-05-02 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/10 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-05-03 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-05-05 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 45/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-05-07 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 46/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-05-09 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/6 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-05-13 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 21/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-05-13 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/5 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-05-18 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/4 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-05-22 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/3 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-05-26 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 19/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-06-02 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-06-08 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 11/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-06-14 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 12/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-06-27 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 1/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-07-05 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2A/1 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-07-14 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2A/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2026-01-23 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36B/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2026-02-08 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | N'37/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2026-03-05 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | N'37A/0 | Completed |  | XML scrub fallback used for sheet 'Foundation'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-05-15 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 241/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-05-21 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 241/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-05-28 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 241/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-08-31 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 235/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-09-20 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 118/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-11-02 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 121/5 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-11-04 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 120/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-11-09 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 120/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-11-19 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 121/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-11-30 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 120/5 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 121/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-03 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 119/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-05 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 120/6 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-08 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 120/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-09 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 121/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-11 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 145/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-11 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 119/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-13 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 244/6 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-17 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 121/6 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-19 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 249/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-21 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 119/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-24 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 121/7 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-26 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 249/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-27 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 137/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-28 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 249/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-30 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 145/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-03 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 121/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-07 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 244/5 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-07 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 250/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-10 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 120/7 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-10 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 121/8 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-15 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 145/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-15 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 137/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-17 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 252/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-19 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 136/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-20 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 250A/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-20 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 121/9 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-22 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 252/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-27 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 141/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-27 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 141/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-28 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 121/10 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-28 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 145/7 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-29 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 248/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-29 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 241/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-31 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 124/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 137/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-02-03 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 248/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-02-07 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 243/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-02-07 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 126/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-02-07 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 124/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-02-07 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 148/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-02-08 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 141/5 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-02-13 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 243/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-02-14 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 250/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-02-23 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 244/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 180/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-02 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 132/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-03 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 117/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-03 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 117/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-06 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 121/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-07 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 172/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-11 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 251/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-11 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 180/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-11 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 179/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-11 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 180/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-11 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 180/5 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-13 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 171/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-15 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 132/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-19 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 174/6 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-24 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 172/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-24 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 165/7 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-31 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 165/5 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 174/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-04-02 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 179/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-04-03 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 180/7 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-04-06 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 174/5 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-04-10 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 174/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-04-11 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 176/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-04-11 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 177/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-04-13 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 175/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-04-20 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 176/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-04-23 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 148/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-04-24 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 178/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-05-02 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 165/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-05-02 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 252/5 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-05-05 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 148/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-05-08 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 180/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-05-10 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 130/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-05-15 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 243/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-05-19 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 256/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-08-04 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 246/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-08-05 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 131/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-08-11 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 120/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-08-14 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 241/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-08-27 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 250A/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-09-23 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 178/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-10-12 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 224/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-10-12 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 119/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-10-15 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 224/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-10-15 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 225/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-10-15 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 120/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-10-16 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 223/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-10-21 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 221/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-10-26 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 224/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-10-26 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 223/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-10-26 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 220/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-10-26 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 223/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-10-26 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 139/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-10-31 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 125/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 222/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-03 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 138/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-03 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 185/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-04 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 220/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-04 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 144/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-04 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 135/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-05 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 136/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-06 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 218/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-10 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 141/6 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-11 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 196/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-11 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 142/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-11 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 186/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-12 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 223/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-13 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 214/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-16 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 187/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-18 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 219/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-19 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 148/5 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-20 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 215/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-20 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 176/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-22 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 225/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-22 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 214/5 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-23 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 183/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-23 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 143/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-24 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 194/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-24 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 214/7 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-25 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 225/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-26 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 214/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-26 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 184/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-26 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 161/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-27 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 145/5 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-27 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 139/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-27 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 214/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-30 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 244/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-30 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 183/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-30 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 182/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 148/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 127/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-04 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 175/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-04 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 128/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-04 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 194/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-05 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 225/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-05 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 217/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-05 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 250/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-05 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 214/6 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-05 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 183/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-05 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 145/6 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-05 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 217/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-05 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 244/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-06 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 141/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-06 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 141/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-08 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 243/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-08 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 166/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-08 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 127/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-09 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 190/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-09 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 256/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-10 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 249/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-11 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 225/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-12 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 189/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-12 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 180/6 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-12 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 250A/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-13 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 191/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-13 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 199/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-13 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 254/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-13 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 197/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-13 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 197/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-13 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 183/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-13 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 210/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-13 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 198/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-15 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 217/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-15 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 149/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-15 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 216/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-16 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 257/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-16 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 216/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-16 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 139/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-17 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 170/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-17 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 127/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-18 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 148/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-18 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 173/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-18 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 174/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-18 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 174/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-19 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 196/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-19 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 252/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-19 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 196/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-19 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 252/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-20 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 165/6 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-20 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 167/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-20 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 139/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-20 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 255/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-20 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 193/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-20 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 250/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-21 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 141/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-22 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 140/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-23 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 179/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-23 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 178/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-25 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 216/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-25 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 216/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-26 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 192/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-26 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 191/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-26 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 244/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-27 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 199/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-27 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 244/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-28 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 199/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-29 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 162/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-31 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 126/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 211/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 211/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-03 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 245/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-03 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 245/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-04 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 230/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-04 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 227/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-04 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 227/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-06 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 132/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-06 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 160/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-06 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 125/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-06 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 133/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-06 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 133/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-08 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 211/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-09 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 178/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-12 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 217/5 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-13 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 174/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-13 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 211/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-15 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 211/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-16 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 125/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-16 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 212/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-16 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 188/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-17 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 197/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-18 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 189/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-18 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 209/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-18 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 211/5 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-18 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 213/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-19 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 165/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-19 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 133/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-19 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 233/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-19 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 235/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-19 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 232/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-20 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 168/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-20 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 238/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-20 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 240/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-21 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 236/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-21 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 235/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-22 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 226/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-23 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 129/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-26 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 252/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-26 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 163/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-29 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 147/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-30 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 134/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 124/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 124/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 228/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-05 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 237/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-05 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 242/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-05 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 214/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-07 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 235/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-07 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 232/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-10 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 228/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-11 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 133/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-13 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 248/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-13 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 217/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-13 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 217/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-14 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 145/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-15 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 214/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-16 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 240/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-16 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 126/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-17 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 209/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-17 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 209/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-17 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 219/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-18 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 126/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-19 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 239/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-19 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 207/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-21 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 226/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-23 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 133/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-25 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 255/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 239/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 226/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-03 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 145/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-11 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 234/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-11 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 227/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-12 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 231/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-13 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 251/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-13 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 131/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-16 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 232/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-16 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 225/7 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-16 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 121/11 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-16 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 150/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-16 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 180/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-18 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 225/5 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-19 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 179/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-22 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 226/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-23 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 230/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-25 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 156/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-26 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 150/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-26 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 230A/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 200/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-05 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 195/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-05 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 232/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-05 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 155/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-05 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 156/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-05 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 159/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-09 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 151/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-12 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 164/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-12 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 165/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-14 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 131/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-17 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 229B/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-21 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 153/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-21 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 229A/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-21 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 151A/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-23 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 235/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-26 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 169/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-27 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 206/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-27 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 225/6 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-05-02 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 206/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-05-09 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 203A/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-05-09 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 203B/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-05-09 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 203/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-05-09 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 201/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-05-13 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 153A/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-05-14 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 229/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-05-20 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 153/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-04-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/8 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/7 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-05-09 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/6 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-05-13 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/5 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-05-16 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/4 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-05-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/3 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-05-28 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/10 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-05-31 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/4 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-05-31 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/5 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-04 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/3 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-04 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/8 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-06 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 6/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-07 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/6 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-08 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/9 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/7 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/7 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-13 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-13 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/6 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-13 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/8 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-13 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/6 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-21 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/7 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/11 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-07-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-07-08 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/12 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-07-11 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-07-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/11 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-07-13 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/5 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-07-15 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/3 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-07-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/4 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-07-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/8 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-07-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/8 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-07-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/6 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-07-28 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/9 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-07-28 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/4 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-07-30 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/9 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/12 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-05 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/5 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-08 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/11 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/3 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 23/3 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/12 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-16 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/9 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-23 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 23/4 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-23 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/3 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/7 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/7 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/8 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/3 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/6 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 45/3 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 50/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-29 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/4 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-30 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/8 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/4 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-08 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-08 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 23/5 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-08 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/3 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-09 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 41/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-09 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/10 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-09 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 45/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-11 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 23/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-19 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/6 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-19 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-19 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 41/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-19 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/9 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/5 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 25/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/4 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-23 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/6 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-25 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-26 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 23/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-27 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/7 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-09 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 46/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-25 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 46/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-26 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/8 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-26 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/7 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-27 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/3 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 25/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/3 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-04 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 25/3 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-04 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/9 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-04 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/5 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-04 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/6 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-04 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/3 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-04 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/4 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-08 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-08 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/5 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/8 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/5 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/8 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-13 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/9 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-13 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-13 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/11 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-13 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-13 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-13 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/10 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-16 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/3 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-16 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-17 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/3 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-17 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8B/3 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-17 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 28/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-17 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/9 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-17 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/5 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-17 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/10 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-17 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-19 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/10 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-21 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/5 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/3 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/9 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/7 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/4 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/11 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/8 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/6 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/7 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/10 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/4 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-25 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/4 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-25 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/4 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-25 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/5 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8B/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/9 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/3 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/4 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8B/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/8 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/6 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-06 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/7 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-06 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-06 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/4 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-06 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/8 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-06 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/7 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-08 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 32/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-09 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 10/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/5 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/3 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-14 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8B/4 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-14 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/8 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-14 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-18 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/6 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-18 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/4 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-16 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 54/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-18 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 21/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-18 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8/3 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-18 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/11 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/6 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8/4 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/7 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8B/5 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/3 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 10/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 54/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-25 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-29 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 26/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-30 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-30 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/5 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 5/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/4 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/7 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-04 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 3/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-04 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/5 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/10 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-02 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 55/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-09 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/5 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-09 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 49/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-09 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/9 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-09 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/6 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-09 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 6/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-09 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-09 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/8 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-09 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/7 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-09 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/7 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-15 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 48/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 47/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 9/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-17 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/10 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-19 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/8 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 6/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/7 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-18 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 46/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-23 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/6 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-23 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 54/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/5 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 64/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-17 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 15/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/9 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8A/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-29 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 5/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/4 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 64/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-04 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 48/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-28 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 28/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-26 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8B/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/10 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/3 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/10 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-04 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 55/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/6 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 51/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-18 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/3 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-14 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 27/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-21 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 45/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-25 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 21/3 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-21 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/6 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-15 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 57/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-23 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 0/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 0/3 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-26 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-18 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 24/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-23 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 42/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/6 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 22/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 0/4 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-30 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 29/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/4 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-02 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/5 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-02 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 40/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-02 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 59/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-02 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 0/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-09 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 22A/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-06 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 25/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-06 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 64/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/7 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-11 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-06 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 43/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/3 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-16 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 41/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-19 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 63/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-19 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 11/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-19 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 58/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-26 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 21/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-26 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 13/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-26 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 50/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 23/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-27 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 60/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-04 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-04 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/5 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/4 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 61/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 67/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 18/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 64/3 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 66/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 62/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-25 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-25 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 57/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-25 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/6 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-31 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 21/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-25 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 66/0 A,B | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-25 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 66/0 C,D | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-04 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 16/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-04 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 68/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-17 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/1 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-04 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 44/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 1/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-11 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 65/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-17 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 70/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-27 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/2 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-25 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 45/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-05 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/5 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-05 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 0/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-06 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 69/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-11 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 37/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-14 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 69A/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/0 | Completed
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/8 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-16 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/4 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-16 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/10 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/8 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/8 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-08 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/6 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-14 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/9 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-15 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/7 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/5 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/7 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/9 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/12 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-05 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/6 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/6 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/5 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-17 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/4 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/5 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/3 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-14 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 6/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/3 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/8 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 41/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-26 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/7 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-28 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-29 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/7 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-28 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/3 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-29 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/12 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/6 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-30 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 41/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-06 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/3 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-06 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/4 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-06 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/4 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/3 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-06 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 45/3 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-13 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-17 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/8 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-18 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-18 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/10 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-21 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 45/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/5 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/7 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/9 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/4 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/3 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-28 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/5 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-28 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 46/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-31 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-28 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/6 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/4 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-04 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/4 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-08 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/8 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-07 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/3 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-07 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-09 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/7 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/3 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-11 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/3 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-15 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/7 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-17 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-15 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/5 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/6 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-21 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/4 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-16 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/9 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-16 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/5 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-21 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/6 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-25 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-21 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/10 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-25 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/5 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-25 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-30 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/7 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-28 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-02 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-02 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/9 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-29 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/5 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/7 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-29 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-02 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/11 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-06 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 21/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-07 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-08 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/9 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-09 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/4 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/3 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-11 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/9 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/7 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-14 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/6 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-16 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-16 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/7 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-14 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/9 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/4 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-21 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/7 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-19 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-21 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/6 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/4 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-19 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-26 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/3 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-27 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/5 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/10 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/8 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-27 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/11 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-28 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/3 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/4 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-08 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/4 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-08 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8/3 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 5/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/5 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/6 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-09 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 6/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-13 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8/4 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-16 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 5/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-16 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/8 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-19 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8B/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/3 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 6/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/10 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-21 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/8 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/8 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/3 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8B/5 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-28 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/6 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-28 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8B/3 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-31 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/11 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/4 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-31 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/6 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 9/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 32/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/4 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-08 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8B/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-02 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-09 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/10 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-05 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/6 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 10/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-06 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-14 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8B/4 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/5 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/7 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/6 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-16 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-15 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 25/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-17 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/5 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 0/4 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-23 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/12 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-23 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/7 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-23 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-17 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 10/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/6 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-26 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/4 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-23 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/9 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8A/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-27 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/11 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-29 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/3 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-29 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/4 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-29 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/8 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-30 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/10 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-30 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/3 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-30 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/3 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-30 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 25/3 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-06 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/8 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-04 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-04 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/9 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-05 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/5 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-07 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-07 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-07 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/4 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-07 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-05 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8B/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-11 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/8 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-13 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/9 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-14 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-14 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/11 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/11 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-14 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-16 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/10 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-15 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 23/3 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-11 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/6 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/9 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/10 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/3 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-16 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 15/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 23/5 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/8 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-23 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 23/4 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-23 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 0/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-23 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/4 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-26 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/8 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-25 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/10 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-28 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/5 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-28 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 23/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-25 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 0/3 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-30 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/5 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-27 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 51/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-04 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 23/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-02 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/5 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-04 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 0/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-08 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 50/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-02 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/5 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/5 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 22/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-25 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 3/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-21 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 21/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 45/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/3 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-15 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 48/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/7 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-27 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 21/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-04 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 40/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 28/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-07-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 21/3 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-07-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 25/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-07-05 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 44/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-28 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-07-08 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 28/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-07-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 41/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-07-09 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 13/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-07-27 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/6 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-14 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 46/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-07-26 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 24/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-02 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 65/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-04 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 18/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-09 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 1/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-12 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-18 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 54/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 43/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-16 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 16/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 11/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-31 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 64/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-05 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-07 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 47/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-06 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 29/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-18 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/8 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-15 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 48/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-15 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/6 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-31 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-15 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 26/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-11 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-28 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 25/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 64/3 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-25 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 54/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-25 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 46/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 63/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 27/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-18 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-23 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 42/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-25 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 50/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-26 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-10-08 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 54/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-10-07 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-10-03 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 0/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-23 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 37/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-10-23 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 55/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-10-09 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 45/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-10-26 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-10-31 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-25 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 61/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-24 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/6 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-11-09 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 55/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-11-15 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 69A/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-11-08 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 60/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-11-06 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 49/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-11-06 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 64/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-11-15 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-11-10 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 62/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-11-16 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 59/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-11-27 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 66/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-11-17 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 23/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-12-05 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 66/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-12-07 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 57/1 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-12-06 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/7 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-12-08 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/7 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-12-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 70/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 58/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-12-15 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 22A/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-12-22 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 57/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-11-30 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 68/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2026-01-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 64/2 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2026-01-20 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 69/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2026-02-09 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/7 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2026-02-09 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 67/0 | COMPLETED
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP7/0-AP8/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP6/0-AP7/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP35/0-AP36/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP8/0-AP8A/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP31/0-AP32/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP8A/0-AP8B/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP32/0-AP33/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP8B/0-AP9/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP33/0-AP34/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP5/0-AP6/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP9/0-AP10/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP34/0-AP35/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP4/0-AP5/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP14/0-AP15/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP3/0-AP4/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP30/0-AP31/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP20/0-AP21/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP36/0-AP37/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP12/0-AP13/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP21/0-AP22/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP39/0-AP40/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP17/0-AP18/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP38/0-AP39/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP19/0-AP20/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP13/0-AP14/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP18/0-AP19/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP15/0-AP16/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP10/0-AP11/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP37/0-AP38/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP11/0-AP12/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP1/0-AP2/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP0/0-AP1/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP24/0-AP25/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP23/0-AP24/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP40/0-AP41/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP2/0-AP3/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP16/0-AP17/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP26/0-AP27/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP42/0-AP43/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP25/0-AP26/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP41/0-AP42/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP28/0-AP29/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP27/0-AP28/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP22/0-AP22A/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP22A/0-AP23/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP46/0-AP47/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP45/0-AP46/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP53/0-AP53A/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP29/0-AP30/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP52/1-AP53/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP52/0-52/1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP53A/0-AP54/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP44/0-AP45/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP69A-AP70/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP70/0-Gantry
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP43/0-AP44/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP69/0-AP69A/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP66/0-AP67/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP65/0-AP66/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP68/0-AP69/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP67/0-AP68/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP54/0-AP55/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP62/0-AP63/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP55/0-AP56/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP61/0-AP62/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP64/0-AP65/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP56/0-AP57/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP47/0-AP48/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP57/0-AP58/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | AP60-AP61/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | 4/0-5/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | 5/0-7/6
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | 7/6-8B/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | 34/0-35/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | 35/0-36/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | 33/0-34/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | 31/0-33/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | 30/0-31/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | 12/0-14/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | 20/0-21/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | 19/0-20/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | 0/0-2/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | 2/0-3/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | 36/0-37/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | 14/0-17/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | 37/0-38/11
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | 8B/0-12/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | 38/11-40/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | 21/0-25/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | 17/0-19/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | 25/0-30/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | 40/0-47/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | 52/1-53/0
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 |  | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_unparsed | 53/0-54/0
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-06-09 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 42/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-06-10 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 42/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-06-29 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 54/4 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-06-29 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 40/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-07-02 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-07-03 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 41/3 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-07-07 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 41/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-07-10 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 40/5 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-07-14 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 40/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-07-18 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/3 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-07-18 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/4 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-07-20 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 40/3 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-07-24 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 54/3 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-07-27 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 41/4 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-07-29 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/3 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-08-03 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 41/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-08-07 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/6 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-08-09 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/7 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_marker_no_date | 52/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-08-14 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 40/4 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-08-25 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/8 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-09-02 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/11 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-09-02 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 34/3 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-09-02 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 34/4 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-09-05 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 34/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-09-12 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 52/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-09-20 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/9 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-09-22 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/12 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-09-24 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/14 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-09-24 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/11 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-09-27 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/10 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-09-29 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/9 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-10-08 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/8 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-10-19 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 34/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-10-27 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/7 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-10-30 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/7 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-11-08 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/8 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-11-13 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 34/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-11-15 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/5 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-11-15 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/4 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-11-19 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 41/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-11-24 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 43/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-04 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 45/02 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-09 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 45/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-10 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 45/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-11 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-22 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-03 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/15 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_marker_no_date | 33/6 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-10 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/5 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-17 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 42/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-23 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-28 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-30 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 40/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-31 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 32/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-02-12 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/4 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-02-15 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 37/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-02-15 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 37/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-02-23 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 48A/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-02-24 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 38/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-02-27 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 36/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-03-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 60/4 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-03-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 37/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-03-10 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 38/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-03-13 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 47/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-03-13 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 54/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-03-20 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 61/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-03-28 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 54/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-02 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/13 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-08 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 56/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-11 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 60/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-13 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 45/3 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-15 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/12 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-16 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 43/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-17 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 60/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-02 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 59/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-10 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 52/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-11 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 48/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-11 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-14 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 48/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-26 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-25 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 41/5 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-02 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/5 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-02 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-02 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/9 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-03 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/10 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-06 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-09 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 36/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-10 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/4 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-12 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/3 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-12 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 43/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-16 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 62/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-18 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 39/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-18 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 44/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-23 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 57/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-24 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/6 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-24 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/3 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-25 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-25 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 44/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-27 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/10 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-28 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/11 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-30 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 48/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-29 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 57/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-03 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 47/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-03 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 58/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-04 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 53/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-04 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 60/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-10 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 43/3 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_marker_no_date | 56/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-15 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 57/3 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-08-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 56/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-08-02 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 56/3 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-08-23 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 54/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-11-02 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/6 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-11-04 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/5 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-11-12 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 51/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-11-13 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 50/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-11-24 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 48A/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-03 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 49/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-10 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 48A/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-12 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 59/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-13 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 57/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-18 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 60/3 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-01-03 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 63/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-02-11 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 38/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-10-09 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 34/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-10-28 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/12 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-11-05 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/06 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-11-14 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 34/3 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-11-19 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/4 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-11-26 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 40/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-02 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 40/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-03 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 42/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-06 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 41/3 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-12 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 41/4 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-12 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 42/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-19 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/11 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-19 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/7 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-29 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/10 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-30 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 40/4 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-01-07 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/14 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-01-09 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 54/4 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-13 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/8 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-16 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-16 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/4 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-24 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/3 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-24 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 34/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-25 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-31 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/8 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-02-06 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 41/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-02-12 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 41/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-02-12 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 54/3 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-02-21 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 41/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-02-26 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 43/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-03-03 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-03-06 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/9 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-03-12 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/7 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-03-18 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 45/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-03-18 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 45/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-03-28 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 45/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-02 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 40/3 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-05 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 42/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-11 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/5 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-12 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/4 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-18 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-22 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 34/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-27 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/15 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-29 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 37/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-05 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-08 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-11 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/5 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-11 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/11 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-22 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 34/4 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-30 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/3 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-29 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 40/5 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-03 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/7 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-09 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/8 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-12 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/9 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-14 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/6 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-19 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 36/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-03 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 38/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-03 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 40/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-03 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 37/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-14 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 37/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-15 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 38/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-21 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/9 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-22 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/5 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-21 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-24 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 41/5 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-29 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-08-06 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 36/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-08-07 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/10 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-08-07 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 48A/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-08-09 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/13 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-08-16 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 48/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-08-18 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 43/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-08-19 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 52/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-08-22 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/3 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-08-26 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 60/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-08-31 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/3 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-09-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 62/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-09-03 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/12 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-09-05 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 56/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-09-09 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 48/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-09-09 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 45/3 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-09-12 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-09-14 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 61/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-09-16 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 53/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-09-22 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-09-25 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 44/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-09-28 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 54/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-09-29 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 54/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-10-04 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 32/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-10-16 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-10-16 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 39/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-10-18 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 60/4 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-10-29 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/10 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-11-04 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/6 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-11-06 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 43/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-11-11 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 48/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-11-12 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/4 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-11-21 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 47/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-11-23 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 44/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-11-30 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 60/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 47/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-04 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/11 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-07 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 56/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-10 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 52/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-15 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 56/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-17 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 52/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-16 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 60/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-20 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 56/3 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-23 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 48A/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-26 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 58/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-26 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 57/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_marker_no_date | 59/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-31 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 48A/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-01-07 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 59/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-01-08 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/6 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-01-08 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 57/3 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-01-16 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 60/3 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-16 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 57/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-01-20 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/5 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-01-22 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 54/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-01-28 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 49/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-01-29 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 57/2 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-02-04 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 50/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-02-05 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 63/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-02-05 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 51/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-02-20 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 43/3 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_marker_no_date | 46/1 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-02-24 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 38/0 | COMPLETED
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_unparsed | 42/0 - 43/0
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_unparsed | 41/0 - 42/0
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_unparsed | 40/0 - 41/0
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_unparsed | 35/0 - 36/0
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_unparsed | 34/0 - 35/0
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_unparsed | 36/0 - 36/1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_unparsed | 33/6 - 34/0
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_unparsed | 33/0 - 33/5
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_unparsed | 33/5 - 33/6
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_unparsed | 39/0-40/0
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_unparsed | 32/0-33/0
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_unparsed | 44/0-45/0
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_unparsed | 45/1-46/0
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_unparsed | 45/0 - 45/1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_unparsed | 43/0 - 44/0
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_unparsed | 56/0-56/3
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_unparsed | 55/0-56/0
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_unparsed | 62/0-63/0
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_unparsed | 63/0-GNTY
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_unparsed | 61/0-62/0
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_unparsed | 37/0-38/0
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_unparsed | 38/0-39/0
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_unparsed | 32/0 - 33/6
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_unparsed | 33/6 - 35/0
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_unparsed | 35/0 - 36/0
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_unparsed | 40/0 -42/0
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 |  | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_unparsed | 42/0 - 45/1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-12-02 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0A/0 (CT) | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-20 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0B/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-18 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0B/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-11 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0B/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-30 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0B/3 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-07 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0C/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-19 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0C/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-29 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0D/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-23 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0D/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-05 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0D/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-08-29 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0D/3 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-25 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0D/4 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-15 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0D/5 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-10 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0E/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-18 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0E/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-09 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0E/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-11-15 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0F/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-11-27 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0G/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-12-21 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0G/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-12-21 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0H/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-12-23 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 1/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-06-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 2/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-05-12 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 3/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-11-26 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 3/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-05 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 3/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-21 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 3/3 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-31 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 3/4 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-25 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 3/5 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-04 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 4/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-08-04 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 4/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-23 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 5/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-08-04 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 5/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-08-30 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 5/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-08-11 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 5/3 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-07 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 5/4 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-07 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 6/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-18 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 6/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-28 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 6/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-20 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 6/3 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-09 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 6/4 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-31 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 6/5 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-23 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 6/6 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-11-08 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 6/7 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-12 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 6/8 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-10 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 6/9 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-06 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 6/10 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-08-11 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 6/11 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-15 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 6/12 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-18 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 7/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-11-19 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 7/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-07-15 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 8/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-07-08 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 9/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-01-02 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 10/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-05-21 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 11/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-12-02 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 11/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-19 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 11/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-06-25 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 11/3 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-06-21 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 11/4 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-09 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 12/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 12/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-28 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 12/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-22 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 12A/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-21 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 12A/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-03-20 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 13/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-01-18 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 14/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-23 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 14/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-12-12 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 15/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-12-03 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 15A/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-12-05 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 16/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-11-20 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 17/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-05-30 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 17/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-05-30 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 17/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-25 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 18/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-19 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 19/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-05-29 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 19/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-06-04 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 19/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-05-21 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 19/3 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-05-21 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 19/4 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_marker_no_date | 19/5 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-17 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 20/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-06-14 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 20/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-06-16 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 20/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-02 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 20/3 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-06-22 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 21/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-01-15 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 22/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-12-02 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 22/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-06-24 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 22/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-06-29 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 22/3 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-30 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 23/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-06-27 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 23/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-09 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 23/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-10 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 23/3 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-17 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 24/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-23 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 24/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-27 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 24/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-11-15 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 24/3 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-05-12 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 25/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-05-15 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 26/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-15 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 26/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-31 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 26/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-13 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 26/3 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-15 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 26/4 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-08 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 26/5 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-14 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 26/6 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-14 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 27/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-02 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 27/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-08-27 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 27/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-11 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 27/3 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-06 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 28/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-12-08 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 28/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-06-09 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 29/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-06-14 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 30/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-12-12 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 30/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-12-11 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 31/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-12-11 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 31/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-09-26 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 31/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-03-25 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 32/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-02-04 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 33/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-30 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 33/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-03-25 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 34/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-06-04 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 34/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-05-29 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 35/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-05-19 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 36/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-01-18 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 36/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-01-25 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 36/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-24 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 36/3 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-01-28 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 36/4 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-19 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 36/5 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-11-13 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 36/6 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-11-13 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 36/7 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-01-10 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 36/8 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-06 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 36/9 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-04 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 36/10 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-27 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 37/0 | WIP |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-02-20 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 38/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-01-11 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 38/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-05-06 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 38/2 | WIP |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-01-28 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 38/3 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 38/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-01-29 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 38/5 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-02-14 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 38/6 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-01-29 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 38/7 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-02-06 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 38/8 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-03-23 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 38/9 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-02-08 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 38/10 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-03-23 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 38/11 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-03-27 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 39/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-03-23 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 40/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 40/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-15 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 40/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-03-27 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 40/3 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 40/4 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-12 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 40/5 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-07 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 40/6 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-09 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 40/7 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-02-12 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 40/8 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-06 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 40/9 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-23 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 41/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-19 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 41/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-13 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 41/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-05-06 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 41/3 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-05-04 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 41/4 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-25 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 41/5 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-07-24 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 41/6 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-23 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 41/7 | completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-28 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 41/8 | completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-02-04 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 42/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-10-20 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 43/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-07 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 43/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-09 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 43/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 43/3 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-14 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 43/4 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-10-28 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 43/5 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-03 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 43/6 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 44/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-09-21 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 45/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-08-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 46/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-09-05 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 46/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-09-11 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 46/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-09-15 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 46/3 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-09 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 46/4 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 47/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 48/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 48/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 49/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 50/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 50/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 51/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-30 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 52/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-16 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 52/1 | WIP |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 52/2 | WIP |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-27 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 53/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-30 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 54/0 | WIP |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-02-26 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 54/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-25 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 54/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-02 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 54/3 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-03 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 54/4 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-04 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 54/5 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-02 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 54/6 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-10 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 54/7 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-25 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 55/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-19 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 55/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-01-16 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 55/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-01-11 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 55/3 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-23 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 55/4 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-05 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 55/5 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-27 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 55/6 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 56/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 57/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-18 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 57/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 58/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-05-06 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 59/0 | WIP |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-18 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 59/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-25 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 60/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-27 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 61/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 61/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-19 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 62/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-02-11 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 62/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-01-16 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 62/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-03-24 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 62/3 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-03-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 62/4 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-02-18 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 62/5 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-18 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 63/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-24 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 63/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-04 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 63/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_marker_no_date | 63/3 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-11 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 63/4 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-02 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 63/5 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-10 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 63/6 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-10-27 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 63A/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-01-17 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 63B/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-01-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 63B/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 63B/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 63B/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 63B/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 63B/5 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-18 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 63B/6 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-29 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 64/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-06 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 64/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-01-07 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 64/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-05 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 64/3 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-05 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 64/4 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-18 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 64/5 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-18 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 64A/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-05-08 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 65/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 65/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 65/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-05-16 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 66/0 | WIP |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-25 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 66/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-25 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 67/0 | WIP |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-05-11 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 68/0 | WIP |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-17 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 69/0 | WIP |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-18 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 70/0 | WIP |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-08 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 71/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-05-09 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 72/0 | WIP |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-03-22 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 73/0 | WIP |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 74/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-05-16 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 75/0 | WIP |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-05-17 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 76/0 | WIP |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-05-13 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 76/1 | WIP |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-03-25 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 76/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-09-24 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 76/3 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-01-20 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 77/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-10-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 78/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-09-16 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 78/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-03-16 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 78/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-06-11 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 78/3 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-08 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 78/4 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-01-03 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 78A/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 79/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 80/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-01-16 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 81/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-01-16 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 82/0 | WIP |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-08-30 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 83/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-10-05 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 83/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 83/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 83/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 83/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-06-05 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 83/5 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-05-03 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 83/6 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-29 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 83/7 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-23 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 83/8 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-02 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 83/9 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-15 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 84/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-29 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 84/1 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-03-25 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 84/2 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-18 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 84/3 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-06-20 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 84/4 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-07 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 84/5 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-10 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 84A/0 | Completed |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 84A/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 85/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 85A/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 86/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 86/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 86/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 86A/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 86A/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 86A/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 86A/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 86A/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 86A/5 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 87/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-05-06 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 87/1 | WIP |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-05-06 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 87/2 | WIP |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 88/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 88/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 88/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 89/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 90/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 90A/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 90A/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 90B/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 91/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 92/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 93/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 93A/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-07 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 93B/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 93C/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 94/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 95/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-05-12 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 95A/0 | WIP |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-05-17 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 96/0 | WIP |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 96/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 96/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 97/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 98/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 99/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 100/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 |  | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_unparsed | 101/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-05-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-05-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-05-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-05-09 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/5 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-05-25 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/6 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-05-25 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/7 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-05-31 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/5 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-15 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-20 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-21 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/8 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-25 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/5 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-25 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-28 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/11 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-07 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-02 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-10 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-28 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/7 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-10 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/9 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-09 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/6 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/8 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/7 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/8 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/5 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/5 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/8 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-02 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-25 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/7 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/6 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-28 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-20 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/9 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/9 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-20 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/5 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-20 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/11 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-25 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-16 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/9 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-09 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/8 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/5 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-28 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/6 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/10 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-31 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 19/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-31 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-10 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 19/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-30 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/7 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 17/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/6 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-29 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 41/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-02 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/6 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 18/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-10 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/10 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-25 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/9 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 17/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/6 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 18/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-16 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/9 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/8 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-28 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/5 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/9 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/5 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 18/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-28 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 35/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-02 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 18/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-30 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-02 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/10 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/6 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-07 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/5 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-07 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/5 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 35/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-09 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/5 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-15 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/7 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-09 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/11 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-15 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/10 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/8 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/6 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 28/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-29 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/7 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 19/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-31 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/7 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/8 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/7 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-29 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/6 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/5 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/6 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/7 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 17/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/6 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-09 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 33/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-07 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/5 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 17/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 33/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/5 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 33/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-07 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 32/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/6 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 32/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 14/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-20 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 35/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 19/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-25 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/8 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-30 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 35/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-25 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-25 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-25 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/10 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/9 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-28 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 32/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-29 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/7 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-09 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/5 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/5 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-02 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/9 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/9 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/8 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-16 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 35/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/6 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/8 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/5 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/7 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/6 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/6 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-16 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/7 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-20 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 40/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/5 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-25 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 32/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-20 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 40/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-03-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/15 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/14 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/7 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-03-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 34/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/12 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/11 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-10 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 34/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-09 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/8 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-07 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 20/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/6 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-21 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/7 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-07 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 20A/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 34/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/8 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/7 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-07 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/7 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/20 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/8 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-10 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/9 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_marker_no_date | 41/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/9 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/5 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-15 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/10 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-20 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/6 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-15 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/9 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/6 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-07 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/12 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/21 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-16 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-16 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/19 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/5 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/18 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-15 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/11 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/5 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/23 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-15 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/17 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/14 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/15 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/13 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-29 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/16 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 3/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/5 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/13 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/11 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/10 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 3/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 28/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1B/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-31 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/5 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-10 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/8 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1B/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-31 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-31 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 3/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1B/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 3/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1A/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1B/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-02 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-20 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1C/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-25 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/2 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-02 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-31 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/4 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-29 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/5 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 5/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/3 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-07 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/1 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-09 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/22 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-16 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43B/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-16 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 44/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 7/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_marker_no_date | 8/0 | COMPLETED
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-05-25 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-07 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/5
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/6
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/5
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/5
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-28 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/9
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-28 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-28 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-30 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-30 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-31 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/7
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-31 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-31 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-31 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/5
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-09 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-10 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/8
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/11
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/6
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/5
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/7
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-25 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/8
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/8
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/9
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-10 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/7
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-15 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/9
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-15 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/7
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-20 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/5
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/10
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/6
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-28 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/8
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-09 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-09 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/8
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/6
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-07 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 19/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-07 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-16 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 17/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-02 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/6
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/10
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/9
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-09 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 18/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/11
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/8
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/5
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/9
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/10
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-15 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/6
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 41/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/5
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 18/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/7
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/6
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/7
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/6
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 17/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/7
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 33/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-20 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/10
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-20 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 17/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-21 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-21 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 18/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-21 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 19/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-21 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 17/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 19/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-25 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/8
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-25 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-25 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-28 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-29 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-29 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-29 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/5
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-31 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 14/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-31 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/6
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 32/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 32/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 19/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-02 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/5
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-15 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/8
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-02 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 35/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 35/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/5
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/6
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/8
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 35/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-02-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-07 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/5
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-10 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/9
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/10
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 33/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 33/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-15 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-15 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-10 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-09 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 18/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/9
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-02 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/6
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-02 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/7
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-02 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/7
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-02 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/9
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/5
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/8
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-09 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-10 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 32/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-10 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/5
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/6
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/7
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 40/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/5
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-01-02 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-20 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-20 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/5
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-15 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 32/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-16 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/6
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-16 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/7
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-16 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/8
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/5
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-20 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/7
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/5
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-29 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 34/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-30 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/12
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-30 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/14
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-30 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/15
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-30 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-30 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/11
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-07 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-15 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/8
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 34/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 28/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/6
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-25 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/9
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/6
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-02 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-02 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 20/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 20A/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/7
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/7
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-09 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/20
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/8
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 34/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/7
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-15 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/8
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/9
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/9
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-25 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/5
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/19
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/21
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/23
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/5
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-28 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/6
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-30 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/6
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-31 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/17
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-31 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/18
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-31 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/5
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-31 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/9
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/10
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/13
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/14
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/15
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 41/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-15 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/7
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 28/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-21 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 3/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-21 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1B/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-21 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-21 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/11
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 3/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 3/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 3/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1A/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1B/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-25 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-28 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1B/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-28 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-30 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-30 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1C/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/8
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-09 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/16
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/6
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/7
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-16 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/13
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/5
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 5/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-20 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-29 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/22
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43B/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-31 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/10
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-10 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 44/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/11
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/11
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 7/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-28 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-29 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/12
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1B/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-20 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-21 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-21 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-21 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/9
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/5
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 23/0-24/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 24/0-25/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 25/0-26/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 26/0-27/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 22/0 - 23/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 29/0 - 29/9
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 32/0-33/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 31/0-32/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 30/0-31/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 29/9-30/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 21/0-22/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 20A/0 - 21/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 20/0- 20A/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 12/0-13/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 10/0-11/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 19/0-20/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 18/0-19/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 9/10-10/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 13/0- 14/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 11/0-12/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 17/0 -18/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 14/0 - 15/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 16/0-17/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 15/0 - 16/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 8/4 - 9/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 6/0-7/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 27/0 - 27/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 27/3 - 28/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 8/3-8/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 7/0 - 8/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | Gantry - 1/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 8/2 - 8/3
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 28/0 -29/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 1/0-1A/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 1A/0 - 1B/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 4/12 - 5/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 8/1-8/2
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 8/0 - 8/1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 1C/0 - 2/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 5/0 - 6/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 4/0 - 4/12
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 38/0 - 39/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 3/0-4/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 37/0 - 38/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 2/0 - 3/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 1B/0 - 1C/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 39/0 - 40/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 36/0 - 37/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 43/0 - 43A/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 34/2-35/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 35/0 - 36/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 33/0 - 34/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 30/0-32/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 29/0 - 30/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 22/0-24/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 24/0-25/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 25/0-27/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 20/0-22/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 12/0-13/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 10/0 - 11/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 17/0-20/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 11/0-12/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 9/0-10/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 13/0 -14/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 14/0-16/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 16/0-17/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 27/0- 29/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 8/4 - 9/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 5/0-6/0-8/4
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 4/12-5/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 4/0 - 4/12
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 2/0-4/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | Gantry-2/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 38/0-39/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_unparsed | 37/0-38/0
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-10 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-02 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-09 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-16 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/5 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-29 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/5 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-29 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-09 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/9 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/5 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/7 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-29 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/6 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-21 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/7 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/5 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/8 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-16 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-21 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/8 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/9 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/7 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-16 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-29 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/5 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-02 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-02 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/10 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-07 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/6 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-09 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/6 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-15 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/7 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-16 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-21 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/8 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/6 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/8 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-09 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 19/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-16 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 19/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-15 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/8 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 18/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 18/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-20 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/11 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 18/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 18/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-02 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 17/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-28 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-02 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/10 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/6 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-16 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/6 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/8 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/10 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/5 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-16 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/6 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/9 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-28 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-30 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-30 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/5 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-09 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-10 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/5 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-10 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-15 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/6 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/11 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/5 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-21 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/6 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/9 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/7 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-28 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/5 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/7 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-02 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 32/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-10 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/8 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 33/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-16 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/9 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-15 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/5 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-20 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/10 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-20 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/6 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 32/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 32/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/7 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-28 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 32/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-29 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-29 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/5 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-30 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-02 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 33/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-28 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 19/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-10 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 35/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-15 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 35/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-16 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/5 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/5 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 17/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-25 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 28/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-28 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/11 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-29 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/9 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/7 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-02 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 17/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-07 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/9 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-10 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-10 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 20/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/6 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-15 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 19/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/6 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-21 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 35/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-29 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/5 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-10 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 17/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 33/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/9 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/5 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/6 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 34/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-25 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-29 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-25 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 35/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-20 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 20A/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/5 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_marker_no_date | 9/10 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_marker_no_date | 14/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 34/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/8 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-15 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/7 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/6 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-21 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/6 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/14 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-21 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/5 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-29 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/21 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/7 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-30 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/8 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 35/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-02 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/6 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-30 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/5 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/7 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/13 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-09 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/23 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-07 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/8 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 34/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/12 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/6 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-16 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/7 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 40/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-20 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1A/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-25 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-31 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/9 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-30 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 40/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/8 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-31 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/15 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/6 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/5 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/7 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-07 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/9 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 41/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-10 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/9 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/9 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-09 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/12 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/10 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-21 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-16 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-16 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/17 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-21 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 5/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-25 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-28 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/18 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-21 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/7 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-07 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-07 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-10 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-12 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/5 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/20 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-10 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/7 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/19 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 41/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/6 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-28 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/7 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-21 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/8 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-31 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/13 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 3/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43B/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-10 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/5 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 3/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-15 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/8 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/14 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-21 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/15 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-20 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/10 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-16 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/11 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-06 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/8 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-18 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_marker_no_date | 4/16 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 |  | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_marker_no_date | 8/11 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-20 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/11 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-23 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-28 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/5 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-30 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1B/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-04 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1B/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-05 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/5 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-07 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1B/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-11 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-09 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 7/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-09 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1B/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-14 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/7 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-13 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 3/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-10 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 44/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/9 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-17 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-20 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 3/3 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/4 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-24 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/5 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-22 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-19 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-26 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1C/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-27 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/22 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-31 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/0 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2026-01-03 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/8 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-30 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/1 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2026-01-08 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/2 | Completed
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2026-01-07 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 28/1 | Completed
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-10-06 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 101/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-10-16 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 100/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-31 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 101/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-14 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 101/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-10-11 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 101/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-10-21 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 101/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-10-25 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 101/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-02 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 101/6
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-18 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 101/7
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-08 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 101/8
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-14 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 102/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-22 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 103/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-11 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 103/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-13 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 103/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-08 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 103/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-22 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 103/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-14 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 103/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-03 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 103/5A
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-05 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 103/5A1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-18 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 103/6A
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-15 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 103/7
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-24 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 103/8
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-19 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 103/9
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-07 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 104/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-27 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 104/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-03 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 104/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-30 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 105/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-19 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 105/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-22 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 106/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-27 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 108/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-13 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 108/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-30 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 108/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-19 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 108/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-10-28 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 108/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-31 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 109/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-10-29 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 109/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-10-07 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 109/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-30 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 109/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-17 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 109/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-17 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 110/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-22 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 110/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-29 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 110/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-17 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 110/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-07 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 110/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-23 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 110/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-10-24 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 110/6
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-29 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 110/7
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-15 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 110/8
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-20 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 110A/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-10 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 110A/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-10-11 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 110A/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-04 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 111/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-04 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 111/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-18 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 111/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-08 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 111/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-16 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 111/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-27 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 112/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-28 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 113/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-22 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 113/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-14 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 113/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-29 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 113/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-09 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 113/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-05 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 113/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-12 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 113/6
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-19 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 114/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-31 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 114/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-20 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 114/10
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-14 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 114/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-07 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 114/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-09-19 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 114/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-07 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 114/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-30 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 114/6
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-28 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 114/7
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-23 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 114/8
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-27 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 114/9
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-03 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 115/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-07 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 116/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-26 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 116/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 116/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-27 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 118/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-15 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 119/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-12 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 120/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-12 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 120/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-30 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 120/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-24 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 120/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-02 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 121/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-26 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 122/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-03 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 123/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-08 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 123/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-22 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 123/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-12 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 123/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-09 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 124/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-04 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 125/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-15 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 125/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-16 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 126/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-10-05 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 126/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-18 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 126/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-20 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 126/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-17 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 126/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-29 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 127/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-20 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 127/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-15 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 127/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-10 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 127/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-31 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 128/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-23 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 129A/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-11 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 129A/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-10 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 129A/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-06 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 129A/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-14 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 130/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-31 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 130/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-09 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 130/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-17 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 131/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-22 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 132/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-05 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 135/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-17 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 135/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-21 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 135/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-22 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 135/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-04-28 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 136/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-25 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 136/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-03 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 136/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-27 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 136/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-29 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 138/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-02-10 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 138/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-02-12 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 138/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-02-04 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 139/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-02-06 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 139/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-12 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 140/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-05 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 140/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-13 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 141/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-20 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 142/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-22 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 144A/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-16 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 144A/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-28 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 144A/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-19 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 144A/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-09-14 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 145/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-25 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 146/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-31 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 147/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-05 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 147/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-10 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 147A/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-27 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 147A/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-31 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 147A/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-10 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 147A/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-19 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 147A/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-24 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 147A/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-31 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 148/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-12 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 148/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-13 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 148A/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-29 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 148B/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-02-15 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 148B/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-13 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 149/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-18 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 149/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-16 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 149/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-31 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 149A/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-31 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 149B/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-10-09 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 149B/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-10-15 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 149B/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-09-27 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 149B/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-10-17 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 149B/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-31 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 150/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-12 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 150/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-22 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 150/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-21 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 150/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-24 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 150/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-28 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 150/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-29 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 151/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-11 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-30 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-26 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-25 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-17 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152A/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-10 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152A/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-25 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152A/10
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-21 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152A/11
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-13 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152A/12
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-28 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152A/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-22 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152A/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-27 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152A/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-02 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152A/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-23 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152A/6
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-05 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152A/7
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-16 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152A/8
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-29 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152A/9
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-13 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 153/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-14 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 154/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-30 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 154/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-04 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 154/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-28 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 154/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-09-30 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 154/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-08 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 154/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-10-17 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 155/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-24 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 155/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-28 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 155/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-21 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 155/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-10 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 155/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-15 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 155/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-07-15 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 156/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-12 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 156/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-03-10 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 156/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-22 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 156/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-05 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 156/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-02-07 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 156/6
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-31 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 158/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-31 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 158/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-16 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 158/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-09 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 158/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-24 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 159/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-19 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 159/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-04 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 159/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-16 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 159/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-25 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 160/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-04 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 160/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-28 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 160/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-15 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 160/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-08 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 160/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-31 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 160/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-28 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 161/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-26 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 161/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-06 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 161/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-31 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 161/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-27 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 161/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-11 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 161/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-07 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 162/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-24 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 162/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-08 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 162/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-23 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 163/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-19 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 164/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-25 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 164/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-31 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 164/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-03-28 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 164/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-16 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 164/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-26 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 164/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-07 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 164/6
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-08 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 164/7
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-15 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 164/8
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-10-22 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 165/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-30 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 165/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-07 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 165/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-18 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 165/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-13 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 165/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-29 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 165/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-09 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 165/6
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-24 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 166/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-13 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 166/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-28 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 166/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-20 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 166/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-28 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 166/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-31 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 166/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-13 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 166/6
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 |  | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_unparsed | 166/7
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-08 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 166/8
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-20 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 166/9
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-03 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 167/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-09 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 167/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-27 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 167/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-29 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 167/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-26 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 167/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-30 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 167/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-10-25 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 168/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-20 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 169/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-24 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 169/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-14 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 169/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-07 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 169/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-04 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 169/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-11 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 169/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-25 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 169/6
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-07-17 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 169/7
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-08 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 169/9
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-16 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 170/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-11 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 170/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-12 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 170/10
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-30 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 170/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-29 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 170/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-04-04 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 170/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-22 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 170/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-28 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 170/6
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-17 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 170/7
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-31 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 170/8
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-07 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 170/9
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-08 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 171/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-22 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 171/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2015-11-27 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 171/10
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-26 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 171/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-08 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 171/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-21 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 171/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-29 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 171/6
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-03 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 171/7
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-17 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 171/8
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-04 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 171/9
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-09 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 172/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-26 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 172/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-10 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 172/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-18 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 172/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-21 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 172/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-30 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 172/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-23 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 172/6
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-05 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 173/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-26 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 173/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-20 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 173/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-12 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 173/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-16 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 173/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-13 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 174A/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-04 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 174A/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-28 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 174A/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-10 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 174A/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-23 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 174A/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-29 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 174A/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-22 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 174B/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-30 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 175/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-15 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 175/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-26 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 175/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-26 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 175/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-24 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 175/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-04 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 176/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-30 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 176/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-06 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 176/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-10 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 176/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-05-15 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 177/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-17 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 177/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-21 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 177/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-23 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 177/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-27 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 177/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-29 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 177/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-31 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 177/6
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-03 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 177/7
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-25 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 177/8
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-18 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 178/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-08 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 178/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-10-16 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 178/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-30 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 178/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-09-04 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 178/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-09-12 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 178/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-09-23 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 179/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-09-29 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 179/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-09-26 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 179/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-10 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 179/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-09-12 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 179/6
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-08-29 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 179/7
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-11 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 179/9
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-10-30 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 180/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-24 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 181/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-18 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 181/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-05-18 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 181/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-27 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 181/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-06 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 181/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-10 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 181/6
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-25 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 182/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-11 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 99/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-09 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 99/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-06 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 99/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 99/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-03 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 99/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-10-25 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 99/6
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-16 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 99/7
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-10-17 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 99/8
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-02-19 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 146/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-02-21 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 148C/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-02-24 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 142/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-02-28 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 148B/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-03-03 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 156/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-03-08 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 169/8
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-03-10 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 157/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-03-11 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 138/2
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-03-21 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 144/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-03-21 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 171/5
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-03-31 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 143/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-04-09 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 134/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-04-09 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 137A/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-04-14 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 133/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-04-15 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 136/4
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-04-18 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 136/3
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-04-14 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 129/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-04-23 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 129/1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-04-30 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 117/0
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-05-15 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 137/0
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-01-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 8/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-01-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 8/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-01-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 8/4 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-01-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 8/6 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-01-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 16/4 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 8/5 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 8/7 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 8/8 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 8/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 16/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 15/7 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 7/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 9/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 15/8 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 13/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 15/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 15/9 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 9/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 13/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 7/4 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 15/4 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 16/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 13/4 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 16/8 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 7/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 13/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 10/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 15/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 15/5 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 13/5 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 10/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 16/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 15/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 14/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 16/7 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 12/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 14/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 12/5 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 14/4 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 16/6 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 12/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 12/6 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 14/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 16/9 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 16/5 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 12/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 12/4 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 16/11 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 16/10 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 24/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 24/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 39/4 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 39/7 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 24/6 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 24/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 39/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 39/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 39/5 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 24/9 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 24/7 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 21/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 24/8 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 39/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 24/10 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 40/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 24/11 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 24/5 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 21/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 41/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 24/4 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 44/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 40/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 26/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 8/9 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 26/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 44/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 41/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 40/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 21/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 9/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 26/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 26/4 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 27/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 27/5 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 8/10 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 41/5 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 39/8 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 36/8 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 27/4 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 21/4 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 36/7 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 41/8 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 5/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 29/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 22/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 7/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 36/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 36/6 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 34/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 29/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-02 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 36/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-05 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 5/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-05 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 27/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-05 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 23/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-05 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 30/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-05 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 34/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-05 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 36/4 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-05 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 36/5 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-06 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 5/5 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-07 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 6/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-08 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 20/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-08 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 34/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-08 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 32/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-09 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 36/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-09 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 5/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-10 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 32/4 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-11 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 38/4 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-12 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 20/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-13 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 5/4 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-13 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 38/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-15 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 32/5 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-16 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 6/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-17 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 38/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-19 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 38/7 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-19 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 47/8 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-19 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 49/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-21 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 32/7 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-21 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 32/6 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-22 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 51/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-23 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 47/11 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-23 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 5/7 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-23 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 38/6 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-23 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 49/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-24 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 51/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-25 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 32/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-25 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 5/6 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-26 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 49/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-27 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 47/4 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-26 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 51/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-30 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 13/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-29 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 38/8 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-29 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 48/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-31 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 67/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 48/6 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 49/4 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-02 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 38/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-04 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 47/6 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-05 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 48/8 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-06 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 49/5 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-07-06 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 67/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-08-06 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 41/4 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-10 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 48/9 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-06 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 47/7 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-06 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 66/8 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-14 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 49/6 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-16 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 49/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-17 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 66/5 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-18 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 65/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-21 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 41/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-23 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 65/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-27 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 66/7 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-30 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 65/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-07-07 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 65/9 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-07-14 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 65/7 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-07-11 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 63/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-07-16 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 63/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-07-22 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 65/11 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-08-19 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 7/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-08-12 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 21/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-08-12 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 46/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-08-19 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 45/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-08-18 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 15/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-09-14 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 46A/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-09-16 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 45/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-09-22 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 33/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-10-13 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 10/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-09-14 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 34/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-09-30 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 45/4 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-10-13 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 46/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-10-11 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 46A/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-09-29 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 12/7 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-10-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 10/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-10-06 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 14/5 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-10-15 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 8/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-10-23 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 9/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-07 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 45A/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-06 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 46A/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-03 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 66/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-10-26 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 46A/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-08 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 47/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-05 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 47/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-05 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 66/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-13 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 47/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-10-25 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 16/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-05 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 18/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-13 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 65/8 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-20 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 66/6 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 |  | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_unparsed | 61/1 | No Progress (Water pipe line)
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-10-29 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 64/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-10-30 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 64/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-03 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 17/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-08 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 63/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-15 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 18/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-19 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 65/5 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-18 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 66/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-23 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 66/4 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-02 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 65/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-21 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 45/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-04 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 67/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-07 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 40/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-21 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 6/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-29 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 23/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-23 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 55/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-24 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 6/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-16 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 55/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 14/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-03 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 52/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-13 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 53/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-27 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 68/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-07 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 32/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-09 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 48/4 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-09 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 11/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-19 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 56/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-20 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 39/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-21 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 53B/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-01-09 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 52/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-16 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 29/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-22 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 25/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-01-07 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 38/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-26 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 27/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-30 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 30/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-01-21 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 36/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-01-04 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 48/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-01-29 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 30/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-01-24 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 48/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 48/5 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-02-06 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 26/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-02-12 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 27/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-02-25 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 37/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-02-23 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 31/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-02-28 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 32/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-03-14 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 53A/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-03-21 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 39/6 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-03-26 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 41/7 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-03-30 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 53B/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-04-05 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 48/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-04-10 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 41/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-04-05 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 65/4 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-03-31 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 39/10 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-04-08 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 39/11 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-04-04 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 28/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-04-18 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 54/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-04-09 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 35/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 |  | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_unparsed | 47/10 | Pit-A,B Steel binding & Pit-A,B,C,D prop set
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-04-14 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 5/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-05-05 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 50/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-04-25 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 39/9 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-05-04 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 45/2 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-04-16 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 4/6 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-05-14 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 47/9 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-04-20 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 4/3 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-04-18 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 4/4 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-04-29 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 3/1 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-05-06 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 4/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-05-02 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 4/5 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 |  | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_marker_no_date | 51/0 | Block level complete
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-05-12 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 3/0 | COMPLETED
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 |  | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_marker_no_date | 2/0 | Pit-A&D Frustum & Stepbox-I,II Complete
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 |  | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_marker_no_date | 63/0 | Pit-C Prop setting complete
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 |  | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_unparsed | 47/0 | Excavation u/p
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 |  | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_unparsed | 3/2 | Excavation u/p
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 |  | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_unparsed | 47/5 | Pit Marking
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-02-18 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 155/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-02-18 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 155/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-02-23 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 155/5 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-02-12 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 155/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-03-26 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 156/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-03-05 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 156/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-03-05 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 156/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-03-13 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 156/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-03-21 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 156/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-04-14 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 139/5 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-04-23 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 139/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-03-26 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 139/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-04-14 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 138/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-04-14 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 137/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-04-05 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 138/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-04-25 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 136/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-05-13 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 148/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-05-15 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 134/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-06-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 144/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-05-25 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 143/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-05-30 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 143/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-07-23 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 141/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-08-31 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 133/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-09-21 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 141/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-09-19 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 138/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-09-24 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 140/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-05-03 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 148/5 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-05-15 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 148/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-05-19 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 148/6 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-05-17 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 148/7 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-09-25 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 145/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-10-15 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 139/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-09-10 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 140/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-11-11 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 135/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-11-11 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 145/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-11-18 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 138/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-11-15 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 192/11 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-11-30 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 141/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-11-30 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 143/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-11-15 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 145/5 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-11-27 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 148/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-12-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 192/13 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-12-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 145/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-12-10 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 146/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-12-21 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 146/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-12-16 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 140/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-12-10 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 145/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-12-21 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 192/10 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-01-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 147/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-12-15 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 146A/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-01-05 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 186/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-01-09 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 192/7 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-01-16 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 192/12 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-01-08 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 147/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-01-27 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 142/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-01-06 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 146/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-02-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 194/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-02-02 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 146A/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-02-03 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 148/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-02-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 148/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-02-16 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 157B/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-02-17 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 157A/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-03-14 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 157/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-02-17 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 146/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-04-14 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 193/5 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-04-29 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 192/8 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-04-02 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 192/9 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-04-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 139/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-04-04 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 139/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-04-08 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 193/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-04-12 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 193/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-04-19 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 193/4 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-04-19 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 193/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-05-07 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 167/2 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-04-22 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 157B/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-05-11 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 167/3 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-05-09 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 133/0 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-05-17 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 167/4 | 3rd & 4th Pit Py &Chimney Casting Done |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-04-04 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 153/0 | 4th Pit Py &Chimney Casting Done |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-04-30 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 194/0 | Pit BC frustum casting Complete |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-05-19 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 133/1 | B & D Pit Frustum Casting done and A & C Pit Rebar Binding WIP |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-05-20 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 167/1 | Trail Pit Excavation Done |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-05-20 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 155/2 | Trail Pit Excavation Done |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-04-22 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 150/2 | Trail Pit Excavation Done |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 |  | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_marker_no_date | 155/0 | Already 2 Pit Casting done with Chimney. Right now ROW |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 |  | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_unparsed | 153/1 |  |  | XML scrub fallback used for sheet 'FDN'
TA 510 | TA 510 - Pile | ta510pile | Pile | config | 2026-05-20 | 2026-04-13 | TA 510 - DPR - 2026-05-20.xlsx | Pile Foundation | Pile Foundation | detail | detail_date | 131/1 | work hampered due to forest dept. approval pending |  | XML scrub fallback used for sheet 'Pile Foundation'
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-02-23 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-02-26 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-02-28 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/6
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-05 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/5
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-05 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-07 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 12/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-10 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/4
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-10 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 12/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-10 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/8
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-10 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 12/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-15 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/7
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-17 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/6
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-13 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 12/4
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-17 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/5
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-24 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/7
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-20 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/8
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-18 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/4
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-21 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-21 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/5
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-23 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 19/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-24 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 19/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-25 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 19/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-26 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/7
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-26 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/10
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-27 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 19/6
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-30 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-28 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 19/4
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-30 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 19/7
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-31 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/8
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-02 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/9
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-03 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-04 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/5
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-06 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/9
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-07 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/6
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-10 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-11 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/11
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-13 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/5
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-13 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/4
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-15 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-15 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/4
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-16 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/10
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-19 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 19/5
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-19 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/7
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-21 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/4
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-23 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/8
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-24 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 28/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-25 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/6
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-26 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/10
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-28 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-28 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 28/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-30 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 23/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-30 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/12
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-04 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-04 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 23/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-04 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/11
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-07 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/13
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-09 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/14
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-10 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-11 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/18
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-12 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 11/4
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-14 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-15 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-17 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-17 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-18 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/4
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-19 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/8
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-19 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 28/4
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-20 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/5
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-21 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 11/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-23 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/10
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-23 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/6
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-25 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-26 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 11/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-26 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/7
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-27 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 28/7
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 28/6
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-04 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 11/5
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-04 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/8
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-06 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 28/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-07 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/12
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-08 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/9
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-10 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/11
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-11 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/6
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-11 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/13
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-11 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 28/5
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-11 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/11
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-16 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/5
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-16 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/5
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-17 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/9
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-17 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 27/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-18 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/9
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-18 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/4
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-20 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 27/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-22 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-23 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-26 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 19/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-26 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-26 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/14
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-26 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-30 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-30 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/4
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 41/6
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-03 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-03 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-04 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/7
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-04 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 12/5
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-05 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/13
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-05 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 41/5
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-07 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 11/6
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-09 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-09 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 41/4
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-09 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/11
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-10 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 16/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-10 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/6
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-12 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/4
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-13 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/12
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-14 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 41/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-15 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/8
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-15 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 1A/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-16 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/10
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-17 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-17 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/26
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-18 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/9
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-18 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 41/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-19 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/5
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-20 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 41/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-20 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 1A/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-20 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/9
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-21 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/14
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-22 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 1A/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-23 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/15
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-25 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/10
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-25 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/11
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-25 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-26 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/8
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-29 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/24
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-29 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-29 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-30 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-31 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/20
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/12
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/19
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-02 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/7
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-03 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/4
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-03 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3A/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-03 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/4
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-05 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/20
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-05 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/16
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-06 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/6
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-07 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/15
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-07 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/21
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-07 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/23
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-07 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3A/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-08 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/5
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-13 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-13 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-14 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3A/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-14 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/5
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-21 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-22 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/16
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-22 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/22
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-23 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-28 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-28 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 41/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-29 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/7
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-03 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/5
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-03 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/18
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-03 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36/9
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-06 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/6
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-06 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-06 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36/8
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-09 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-11 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/14
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-11 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36/7
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-16 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/5
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-16 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-16 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/6
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-16 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36/6
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-21 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36/5
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-22 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/8
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-23 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 13/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-25 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/9
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-26 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36/4
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-29 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/19
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/10
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-04 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/9
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-04 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-09 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/7
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-12 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-12 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/10
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-12 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/4
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-16 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-17 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-17 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-18 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-19 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/17
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-23 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-25 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/13
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-25 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-26 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/18
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-26 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/4
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-27 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 12/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-28 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-30 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-30 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/4
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-30 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-30 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/21
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-02 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/4
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-03 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-04 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/17
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-05 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 11/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-06 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/5
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-07 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-09 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/17
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-09 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/6
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-10 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-11 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 16/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-12 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/25
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-12 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/7
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-13 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-14 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 39/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-16 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 11/8
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-16 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-17 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/27
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-18 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-19 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3A/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-21 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/7
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-22 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-24 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/16
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-24 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-25 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-28 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/4
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-29 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-29 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/8
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 21/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-02 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-02 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-02 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2A/5
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-03 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/5
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-04 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/5
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-05 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2A/4
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-06 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/6
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-07 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/4
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-07 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/4
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-08 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-09 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2A/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-10 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/6
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-12 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2A/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-12 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-13 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20A/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-14 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-14 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/8
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-16 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/7
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-16 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2A/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-17 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 28/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-17 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-17 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 23/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-17 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/7
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-19 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/6
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-21 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/9
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-23 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/4
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-25 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2A/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-26 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/7
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-26 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-27 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 22/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-27 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 27/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-30 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/6
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-30 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-31 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/22
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-01-04 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 23/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-01-03 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-01-05 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33A/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-01-11 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-01-11 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 42/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-01-12 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 13/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-01-13 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-01-16 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 43/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-01-20 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-01-21 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-01-31 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-02-02 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-02-07 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 16/3
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-02-19 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/8
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-02-22 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/9
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-03-03 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-03-09 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 44/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-03-15 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/2
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-04-03 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 17/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-04-08 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 47/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-04-12 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-04-15 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 44/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-04-24 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 46/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-04-24 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 45/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-04-29 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-05-09 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 11/7
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 |  | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_unparsed | 27/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 |  | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_unparsed | 11/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 |  | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_unparsed | 16/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 |  | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_unparsed | 1A/0
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 |  | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_unparsed | 31/10
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 |  | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_unparsed | 25/1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-04-21 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 30/3 | Template
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-04-22 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 30/1 | Template
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-04-24 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 30/2 | Template
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-04-29 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 29/5 | Template
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 29/2 | Template
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-02 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 29/4 | Template
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-03 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 29/1 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-03 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 29/3 | Template
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-07 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 28/4 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-07 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 28/3 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-09 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 28/2 | Template
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-16 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 3/5 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-20 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 3/6 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-24 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 3/10 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-30 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 21/7 | Template
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-30 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 21/6 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-06-03 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 23/1 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-06-05 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 23/3 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-06-07 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 23/2 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-06-11 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 23/4 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-06-21 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 56/1 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-06-20 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 14/4 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-06-28 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 26/1 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-07-02 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 56/2 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-07-02 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 14/3 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-07-05 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 56/4 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-07-07 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 14/2 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 |  | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_unparsed | 56/0 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-07-16 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 55/5 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-07-15 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 15B/4 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-07-20 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 55/0 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-07-24 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 55/6 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-07-21 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 54/6 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-07-26 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 36/3 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-08-19 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 56/3 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-08-21 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 36/4 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-09-10 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 30/0 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-08-19 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 29/0 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-10-24 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 54/3 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-11-14 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 54/7 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-11-03 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 55/3
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-11-30 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 51/4 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-12-06 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 51/2 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-08-21 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 54/5 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-12-14 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 52/4 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-12-19 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 51/5 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2026-01-24 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 54/8 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2026-02-17 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 52/3 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2026-02-27 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 55/1 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2026-03-28 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 55/2 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2026-04-22 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 52/2 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2026-04-27 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 55/4 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2026-04-24 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 52/0 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2026-05-04 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 52/1 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-05 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 52/5 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-06 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 55/3 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-11 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 64/2 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-11 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 64/5 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-11 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 55/7 | Prop
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2026-05-19 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 64/3 | Prop
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-03-22 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 25/1 | Prop
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-03-25 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 25/2 | Prop
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-03-30 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 24/2 | Prop
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-04-02 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 24/1 | Prop
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-04-04 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 26/2 | Prop
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-04-09 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 30/2 | Prop
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-04-12 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 23/6 | Prop
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-04-14 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 23/5 | Prop
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-04-14 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 31/1 | Prop
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-04-17 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 37/1 | Prop
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-04-23 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 31/2 | Prop
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-04-26 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 24/3 | Prop
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-05-16 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 24/4 | Template
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-05-21 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 23/3 | Template
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-05-25 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 32B/1 | Template
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-06-20 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 18/4 | Template
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-09-10 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 27/0 | Prop
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-09-13 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 26/0 | Prop
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-09-15 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 25/0 | Prop
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-09-19 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 24/0 | Prop
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-09-25 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 19/0 | Prop
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-09-30 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 28/0 | Prop
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-10-04 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 18/0 | Prop
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2026-05-04 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 30/0 | Prop
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2026-05-17 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 28/1
TA 515 | TA 515 | ta515 |  | filename | 2026-05-11 | 2026-05-11 | TA 515 - DPR - 2026-05-11.xlsx | DPR | DPR | detail | detail_date | 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) | 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) ¦ 2026-05-11 00:00:00
TA 515 | TA 515 | ta515 |  | filename | 2026-05-11 |  | TA 515 - DPR - 2026-05-11.xlsx | DPR | DPR | detail | detail_unparsed | L2 / Actual | Sl. ¦ Description ¦ L2 / Actual ¦ UOM ¦ Total Qty ¦ Progress upto Apr'26 ¦ Todays Progress ¦ Progress for current month (May'26)
TA 515 | TA 515 | ta515 |  | filename | 2026-05-11 |  | TA 515 - DPR - 2026-05-11.xlsx | DPR | DPR | detail | detail_unparsed | 1 | 1 ¦ Route Alignment ¦ L2 (Plan) ¦ KM ¦ 83.14 ¦ 83.14 ¦ - ¦ -
TA 515 | TA 515 | ta515 |  | filename | 2026-05-11 |  | TA 515 - DPR - 2026-05-11.xlsx | DPR | DPR | detail | detail_unparsed | 2 | 2 ¦ Detailed Survey ¦ L2 (Plan) ¦ KM ¦ 83.14 ¦ 83.14 ¦ - ¦ -
TA 515 | TA 515 | ta515 |  | filename | 2026-05-11 |  | TA 515 - DPR - 2026-05-11.xlsx | DPR | DPR | detail | detail_unparsed | 3 | 3 ¦ Check Survey ¦ L2 (Plan) ¦ KM ¦ 83.14 ¦ 83.14 ¦ - ¦ -
TA 515 | TA 515 | ta515 |  | filename | 2026-05-11 |  | TA 515 - DPR - 2026-05-11.xlsx | DPR | DPR | detail | detail_unparsed | 4 | 4 ¦ Soil Investigation ¦ L2 (Plan) ¦ Nos ¦ 17 ¦ 17 ¦ - ¦ -
TA 515 | TA 515 | ta515 |  | filename | 2026-05-11 |  | TA 515 - DPR - 2026-05-11.xlsx | DPR | DPR | detail | detail_unparsed | 12 | Actual ¦ 12 ¦ 12 ¦ - ¦ - ¦ 12
TA 515 | TA 515 | ta515 |  | filename | 2026-05-11 |  | TA 515 - DPR - 2026-05-11.xlsx | DPR | DPR | detail | detail_unparsed | 5 | 5 ¦ Foundation ¦ L2 (Plan) ¦ Nos ¦ 215 ¦ 84 ¦ - ¦ 12
TA 515 | TA 515 | ta515 |  | filename | 2026-05-11 |  | TA 515 - DPR - 2026-05-11.xlsx | DPR | DPR | detail | detail_unparsed | 217 | Actual ¦ 217 ¦ 8 ¦ - ¦ 1 ¦ 9
TA 515 | TA 515 | ta515 |  | filename | 2026-05-11 |  | TA 515 - DPR - 2026-05-11.xlsx | DPR | DPR | detail | detail_unparsed | 6 | 6 ¦ Earthing ¦ L2 (Plan) ¦ Nos ¦ 215 ¦ 84 ¦ - ¦ 12
TA 515 | TA 515 | ta515 |  | filename | 2026-05-11 |  | TA 515 - DPR - 2026-05-11.xlsx | DPR | DPR | detail | detail_unparsed | 217 | Actual ¦ 217 ¦ 8 ¦ - ¦ 1 ¦ 9
TA 515 | TA 515 | ta515 |  | filename | 2026-05-11 |  | TA 515 - DPR - 2026-05-11.xlsx | DPR | DPR | detail | detail_unparsed | 7 | 7 ¦ Erection ¦ L2 (Plan) ¦ Nos ¦ 215 ¦ 60 ¦ - ¦ 12
TA 515 | TA 515 | ta515 |  | filename | 2026-05-11 |  | TA 515 - DPR - 2026-05-11.xlsx | DPR | DPR | detail | detail_unparsed | 217 | Actual ¦ 217 ¦ 2 ¦ - ¦ - ¦ 2
TA 515 | TA 515 | ta515 |  | filename | 2026-05-11 |  | TA 515 - DPR - 2026-05-11.xlsx | DPR | DPR | detail | detail_unparsed | 8 | 8 ¦ Stringing ¦ L2 (Plan) ¦ KM ¦ 83.14 ¦ 8 ¦ - ¦ 3
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-08-07 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 81/2 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-08-22 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 82/1 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-09-13 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 81/1 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-09-18 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 80/5 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-10-10 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 80/1 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-10-19 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 59/5 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-10-19 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 84/3 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-10-21 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 59/4 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-10-24 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 84/4 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-10-25 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 60/2 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-10-27 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 80/4 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-10-31 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/4 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-11-05 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/10 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-11-08 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 59/2 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-11-09 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/7 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-11-13 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/8 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-11-15 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 60/3 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-11-19 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/3 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-11-23 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 60/8 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-11-25 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/1 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-11-29 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 59/1 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-11-30 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/2 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-03 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 58/2 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-08 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 58/1 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-12 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/6 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-14 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 58/3 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-15 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 99/7 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-18 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 73/1 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-19 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/3 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-20 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 99/6 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-23 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 99/9 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-24 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 73/2 | Foundation completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-24 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/1 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-25 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 79/1 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-26 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 99/8 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-27 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/2 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-29 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 99/10 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-30 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 79/3 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-31 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 94/1 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-31 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 55/3 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-31 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 99/11 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-31 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 84/6 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-05 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 79/2 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-06 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/4 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-06 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 99/12 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-08 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 84/5 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-10 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/9 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-12 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/2 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-12 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 84/1 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-14 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/3 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-14 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 83/0 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-16 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/7 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-17 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/6 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-21 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/8 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-22 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 85/2 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-22 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/2 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-23 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/1 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-24 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/4 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-26 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 84/0 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-26 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 59/0 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-26 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 102/4 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-27 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/5 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-28 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/1 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-28 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 55/1 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-30 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 53/2 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-31 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 102/5 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-31 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 52/0 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-31 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/3 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-31 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/0 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-05 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 51/9 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-06 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 78/3 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-08 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 53/1 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-08 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 102/3 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-10 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/9 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-11 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 102/2 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-12 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 50/1 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-14 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/5 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-14 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 102/1 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-15 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 83/1 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-17 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 50/2 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-22 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/6 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-24 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/6 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-25 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 85/1 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-26 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/8 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-28 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/7 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-28 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/7 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-03 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 89/1 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-06 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 53/4 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-08 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 53/5 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-11 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 49/10 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-13 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 51/7 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-14 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 49/11 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-14 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 51/8 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-17 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 51/10 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-18 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 90/0 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-18 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/0 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-19 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 51/6 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-22 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 52/1 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-25 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 50/3 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-27 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 51/2 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-31 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 53/3 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-06 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 60/0 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-11 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 70/1 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-13 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 70/2 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-13 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 53/0 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-16 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 50/0 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-16 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 70/4 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-18 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 70/3 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-21 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 66/1 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-23 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 49/9 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-26 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 67/0 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-29 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 65/3 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-30 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 49/8 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-05-03 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 66/0 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-05-05 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 67/1 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-05-10 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 48/7 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-05-13 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 69/0 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-05-16 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 69/2 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-05-19 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 48/3 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-05-20 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 69/1 | Foundation Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 84/2 | WIP: Excavation Hard Rock Encounted
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 60/1 | Trial Pit Excavated, Hard Rock encounted
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 101/4 | WIP: Excavated
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 85/0 | WIP: Pit Marking
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 90/1 | WIP: Pit Marking
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 102/0 | WIP: Pit Marking
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 90/3 | WIP: Blasting
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 90/2 | WIP: Blasting
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 99/5 | WIP: Excavation
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 49/7 | WIP: Pit Marking
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 56/10 | WIP: Trial Pit
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 56/5 | WIP: Excavation
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 49/1 | WIP: Trial Pit
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 48/1 | WIP: Blasting
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 48/2 | WIP: Steel Binding
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 48/4 | WIP: Blasting
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 56/0 | WIP: Excavation
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 49/0 | WIP: Excavation
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 68/2 | WIP: Blasting
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 82/1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 80/5
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 59/4
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 77/1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 77/2
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 77/6
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 56/3
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 79/1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 80/1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 99/9
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 99/8
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 99/10
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 99/11
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 99/6
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 99/7
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 73/1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 73/2
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 56/2
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 56/4
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 58/2
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 58/3
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 56/7
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 56/6
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 59/1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 58/1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 60/2
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 60/8
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 100/3
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 59/0
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 101/0
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 100/5
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 52/0
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 77/9
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 102/4
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 78/3
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 50/1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 51/9
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 53/1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 102/1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 50/2
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 56/8
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 56/9
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 53/2
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 55/1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 55/3
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 60/3
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 59/5
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 59/2
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 83/1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 101/1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 101/2
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 101/3
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 101/5
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 101/6
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 101/7
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 100/8
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 100/6
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 100/7
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 85/1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 89/1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 51/7
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 51/8
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 100/0
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 52/1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 51/6
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 50/3
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 51/2
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 53/3
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 53/4
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 53/5
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 53/0
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 70/1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 60/0
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 70/2
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 51/10
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 79/2
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 79/3
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 84/0
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 70/4
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 83/0
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 84/1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 70/3
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 84/4
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 50/0
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 49/10
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 49/11
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 66/1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 67/0
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 49/8
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 65/3
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 66/0
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 81/2
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 81/1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 77/8
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 77/7
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 77/3
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 48/7
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 69/2
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-20 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 59/1 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-27 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 59/2 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-31 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/3 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-10 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 58/2 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-08 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/2 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-10 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 58/1 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-13 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/1 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-14 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 58/3 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-16 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/4 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-16 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 82/1 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-20 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 80/5 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-21 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 59/4 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-21 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/7 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-21 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 84/3 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-21 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 99/11 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-24 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 84/4 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-25 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 80/1 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-27 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 59/5 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-27 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 99/10 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-28 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 84/1 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-29 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 99/7 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-30 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/10 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-31 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 79/2 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-31 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/2 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-02 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 60/2 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-03 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 99/8 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-03 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 85/2 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-04 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 79/3 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-05 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 84/5 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-05 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/1 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-09 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/8 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-09 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 99/6 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-10 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 84/0 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-11 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/6 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-12 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/2 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-13 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/9 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-13 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 81/1 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-16 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 99/9 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-16 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/3 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-17 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 102/4 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-17 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 55/1 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-19 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 102/5 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-20 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/7 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-20 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/1 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-21 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 52/0 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-22 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 102/2 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-24 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/5 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-24 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 102/3 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-25 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 53/1 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-26 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/2 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-27 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 102/1 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-28 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/9 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-28 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 53/2 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-02 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/5 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-03 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/0 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-05 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 51/9 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-07 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/3 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-09 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 83/1 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-11 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 85/1 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-16 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/6 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-16 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/6 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-18 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 55/3 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-20 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/7 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-23 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/7 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-25 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/4 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-29 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/4 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 53/4 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-04 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/8 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-07 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 53/5 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-12 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/0 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-05-18 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 60/0 | Erection Completed.
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 |  | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_unparsed | 59/0 | WIP: 1st Section
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-09-15 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 125/2
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-10-03 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 125/3
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-10-07 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 123/1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-10-08 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 124/1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-10-15 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 124/2
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-10-16 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 121/7
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-10-19 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 121/2
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-10-19 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 123/3
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-10-25 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 122/2
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-10-28 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 126/5
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 116/1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 126/4
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-03 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 116/2
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-04 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 124/3
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-06 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 123/4
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-06 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 126/3
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-08 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 130/1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-09 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 111/1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-11 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 126/9
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-13 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 123/2
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-14 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 111/2
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-14 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 126/10
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-15 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 121/6
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-16 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 121/1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-19 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 111/3
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-19 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 130/3
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-20 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 103/2
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-21 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 124/4
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-21 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 126/2
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-22 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 121/4
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-23 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 111/4
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-24 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 103/3
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-24 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 134/2
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-28 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 103/1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-28 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 111/5
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-28 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 134/3
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-30 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 102/7
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-30 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 110/2
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-30 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 121/5
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-30 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 134/5
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-03 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 110/1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-03 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 134/4
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-06 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 99/1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-06 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 109/1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-06 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 134/6
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-07 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 102/9
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-07 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 109/10
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-07 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 134/9
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-08 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 134/7
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-10 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 136/2
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-11 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 110/3
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-12 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 109/2
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-12 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 109/11
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-12 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 136/7
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-13 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 99/2
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-15 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 102/8
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-16 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 108/7
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-16 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 136/8
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-17 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 134/8
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-17 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 136/5
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-19 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 110/4
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-19 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 136/9
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-20 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 109/7
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-22 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 108/5
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-22 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 136/6
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-24 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 89/9
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-24 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 109/9
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-24 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 139/3
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-26 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 107/2
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-26 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 108/6
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-27 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 109/6
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-27 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 130/2
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-28 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 89/8
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-29 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 136/1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-30 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 89/7
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-30 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 109/5
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-30 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 139/2
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-03 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 107/1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-04 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 89/6
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-07 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 129A/1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-09 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 139/5
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-10 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 89/5
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-11 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 108/4
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-11 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 129A/5
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-17 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 108/1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-20 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 76/2
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-20 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 136/4
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-24 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 77/1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-25 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 107/4
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-27 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 76/1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-27 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 129A/7
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-28 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 139/6
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-30 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 127/7
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-30 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 129A/2
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-31 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 76/6
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-31 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 129A/4
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-31 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 136/3
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-02-02 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 82/2
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-02-03 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 127/4
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-02-05 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 129A/10
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-02-08 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 82/3
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-02-09 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 127/1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-02-11 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 129A/3
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-02-13 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 127/2
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-02-13 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 70/3
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-02-16 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 129A/6
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-02-17 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 121/10
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-02-23 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 70/1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-02-28 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 125/1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-03-03 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 126/7
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-03-07 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 70/2
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-03-14 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 124/5
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-03-21 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 76/5
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-03-30 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 88/2
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-02 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 88/1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-03 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 127/3
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-08 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 124/0
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-08 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 87/4
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-11 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 139/4
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-11 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 102/11
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-13 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 69/2
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-14 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 87/5
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-15 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 121/9
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-18 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 71/1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-18 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 87/2
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-21 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 69/1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-22 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 109/8
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-23 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 125/0
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-24 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 71/2
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-24 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 136/0
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-25 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 87/3
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-28 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 69/3
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-30 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 88/3
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-30 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 71/3
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-30 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 139/0
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-30 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 127/0
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-05-04 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 71/4
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-05-04 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 139/1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-05-04 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 108/0
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-05-06 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 107/0
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-05-08 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 69/4
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-05-12 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 126/0
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-05-15 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 88/0
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 |  | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_unparsed | Sc-5
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 |  | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_unparsed | SC-4
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 |  | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_unparsed | Sc-3 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 |  | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_unparsed | SC-2 | U/P
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 |  | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_unparsed | SC-1 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 |  | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_unparsed | 1/0 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 |  | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_unparsed | 2/0 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 |  | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_unparsed | 2/1 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-04-14 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 3/0 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-04-12 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 3/1 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-03-08 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 4/0 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-03-16 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 4/1 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-03-17 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 4/2 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-02-05 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 5/0 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-02-19 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 6/0 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-01-30 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 6/1 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-01-27 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 6/2 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-01-31 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 6/3 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-03-14 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 6/4 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-01-25 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 7/0 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-01-21 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 8/0 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-01-21 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 9/0 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2025-12-13 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 10/0 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2025-12-16 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 11/0 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2025-12-17 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 12/0 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-01-10 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 12/1 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2025-12-25 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 13/0 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-01-14 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 13/1 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-01-10 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 13/2 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2025-12-28 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 14/0 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-02-10 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 15/0 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2025-12-16 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 15/1 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2025-12-15 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 15/2 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2025-12-19 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 15/3 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2025-10-23 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 16/0 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2025-10-27 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 16/1 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2025-11-15 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 16/2 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2025-07-10 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 17/0 | C
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2025-11-07 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 18/0 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-20 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 0/0 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-09 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 0/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-03-27 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 1/0 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-23 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 1/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-06 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 1/2 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-17 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 1A/0 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-05 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 1A/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-02 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 1A/2 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-03-05 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 1B/0 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2026-02-24 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 1C/0 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-25 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 1C/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-31 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 1D/0 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-22 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 1D/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-03-22 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 1E/0 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-02 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 2/0 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-18 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 3/0 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-05 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/0 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-24 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-18 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/2 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-14 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/3 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-08 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/4 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-19 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/5 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-14 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/6 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-09-26 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/7 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-09-03 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/8 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-30 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/9 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-08 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/10 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-12 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/11 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-13 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/12 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-20 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/13 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-19 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/14 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-25 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/15 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-12 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/16 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-15 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/17 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-03-28 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 5/0 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-05 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 5/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-06 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 5/2 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-07 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 5/3 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-29 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 5A/0 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-10-08 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 5A/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-10-12 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 5A/2 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-10-17 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 5B/0 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-11-26 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 6/0 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-03-16 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 7/0 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-03-09 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 7/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-03-16 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 7/2 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-03-23 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 7/3 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-18 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8/0 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-04 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8A/0 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-11 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8B/0 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-19 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8B/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-27 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8B/2 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-12 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8C/0 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-16 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8D/0 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-12-07 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8D/0A | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-11-20 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8D/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-12-03 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8D/2 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-09-10 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8D/3 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-08-30 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8D/4 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-08-17 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8D/5 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-08-23 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8D/6 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-09-21 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8E/0 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-06-08 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8E/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-27 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8E/2 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-06-06 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8E/3 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-04-26 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8E/4 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-04-25 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8E/5 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-06-04 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8E/6 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-11-16 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8E/7 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-26 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8E/8 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-29 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8E/9 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-25 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8E/10 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-30 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8E/11 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-27 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8E/12 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-18 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-9 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-17 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 9/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-22 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 9/2 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-06-05 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 9/3 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-06-05 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 9/4 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-25 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 9/5 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-23 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 9/6 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-29 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 9/7 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-09-28 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 9/8 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-30 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 9/9 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-26 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-10 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-04-19 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 10/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-15 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 10/2 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-09-09 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 10/3 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-22 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 10/4 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-20 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-11 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-27 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 11/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-19 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-12 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-04-08 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-13 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-11-08 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 13/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-08 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-14 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-09-07 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 14/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-09-20 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 14/2 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-09-12 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 14/3 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-09-30 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 14/4 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-10-08 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 14/5 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-11-05 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 14/6 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-25 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 14/7 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-31 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 14/8 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-19 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 14/9 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-15 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-15 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-09-22 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 15/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-09-11 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 15/2 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-09-15 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 15/3 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-24 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 15/4 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-09 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 15/5 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-06 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 15/6 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-03 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 15/7 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-09 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 15/8 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-12 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 15/9 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-10 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-16 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 16/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-27 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 16/2 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-16 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 16/3 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-31 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-17 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-24 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 17/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-11 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 17/2 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-06 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 17/3 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-21 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-18 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-29 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 18/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-08 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 18/2 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-08-19 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 18/3 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-04 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 18/4 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-18 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 18/5 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-14 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 18/6 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-20 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 18/7 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-30 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 18/8 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-26 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 18/9 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-30 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 18/10 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-24 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 18/11 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-20 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-19 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-26 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 19/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-04 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 19/2 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-18 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 19/3 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-24 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 19/4 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-21 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 19/5 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-12 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-20 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-08 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 20/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-05 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 20/2 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-26 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 20/3 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-30 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 20/4 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-08-16 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 20/5 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-22 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 20/6 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-08-12 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 20/7 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-25 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 20/8 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-09 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-21 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-04-15 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 21/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-04-21 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 21/2 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-26 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 21/3 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-17 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 21/4 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-15 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 21/5 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-09-19 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 21/6 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-09-23 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 21/7 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-19 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 21/8 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-04 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 21/9 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-19 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 21/10 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-19 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 21/11 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-21 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 21/12 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-04-27 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 21/13 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-11 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-22 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-19 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 22/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-09 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 22/2 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-06 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-23 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-10 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 23/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-23 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 23/2 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-28 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 23/3 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-15 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 23/4 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-04-30 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 23/5 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-04-29 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-24 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-04-17 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-25 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-03-16 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-26 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-04-03 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-27 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-25 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-28 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-24 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 28/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-06-29 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 28/2 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-14 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-29 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-10 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 29A/0 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-26 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 29A/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-20 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 29A/2 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-25 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 29A/3 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-19 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 29A/4 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-28 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-30 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-28 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 30/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-06 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 30/2 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-31 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 30/3 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-05 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 30/4 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-10 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 30/5 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-30 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 30/6 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-07 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-31 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-15 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 31/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-29 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-32 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-23 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 32/1 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-15 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 32/2 | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2026-04-09 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 33/0 (New) | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2026-04-20 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 33/1 (New) | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2026-04-30 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 34/0 (New) | C
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 |  | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_unparsed | 35/0 (New) | C
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-01-17 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 83/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-01-27 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 75/7
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-02 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 75/6
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-05 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 75/4
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-05 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 75/5
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-09 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 77/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-10 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 75/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-11 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 77/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-14 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 77/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-17 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 75/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-17 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 77/4
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-18 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 75/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-19 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 77/5
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-22 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 73/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-22 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 86/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-23 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 79/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-25 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 73/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-25 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 95A/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-27 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 80/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-28 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 66/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-28 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 74/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-28 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 96/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-02 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 76/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-06 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 66/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-07 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 64/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-07 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 96/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-08 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 81/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-09 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 86/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-10 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 64/4
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-10 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 85/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-10 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 99/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-11 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 66/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-24 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 87/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-26 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 64/7
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-30 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 64/6
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-30 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 87/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-30 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 98A/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-31 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 64/5
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-04-04 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 98/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-04-09 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 71/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-04-13 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 91/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-04-16 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 91/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-04-17 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 51/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-04-18 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 119/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-04-20 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 95/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-04-22 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 119/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-04-23 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 51/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-04-25 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 99/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-04-29 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 104B/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-04-29 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 62/4
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-04-29 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 81/4
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-05-05 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 104B/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-05-15 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 105/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-05-18 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 100/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-05-21 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 81/5
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-05-23 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 97/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-05-25 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 99C/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-05-28 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 105/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-05-29 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 98A/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-05-31 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 62/5
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-04 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 81/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-05 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 120/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-06 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 96/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-07 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 75/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-08 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 147/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-10 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 82/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-12 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 147/5
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-12 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 79/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-15 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 119/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-15 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 147/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-15 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 82/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-16 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 147/4
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-16 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 78/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-20 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 74/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-21 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 147/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-22 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 147/7
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-23 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 95A/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-25 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 146/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-25 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 147/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-26 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 73/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-27 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 86/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-30 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 114/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-30 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 146/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-30 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 147/8
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-30 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 72/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-04 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 95/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-05 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 148/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-06 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 106/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-08 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 146/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-08 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 148/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-10 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 114/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-10 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 148/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-10 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 80/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-11 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 141/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-11 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 95/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-12 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 148/4
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-13 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 141/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-13 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 145/4
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-14 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 125/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-14 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 133/6
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-15 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 148/5
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-16 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 109A/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-16 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 113A/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-16 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 133/5
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-16 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 145/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-17 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 142/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-18 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 115/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-18 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 148/6
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-19 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 77/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-21 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 133/4
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-21 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 143/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-21 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 145/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-23 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 148/7
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-24 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 125/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-24 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 133/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-24 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 94/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-25 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 145/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-26 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 126/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-26 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 143/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-27 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 133/8
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-27 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 149B/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-27 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 79/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-28 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 110/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-29 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 143/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-29 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 99/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-30 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 133/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-30 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 149B/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-31 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 111/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-31 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 116/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-31 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 129/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-31 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 133/7
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-31 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 143/6
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-31 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 145/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-31 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 76/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-31 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 98B/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-02 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 126/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-02 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 143/7
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-04 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 130/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-04 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 143/5
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-05 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 97/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-06 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 143/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-07 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 102/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-07 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 133/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-07 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 144/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-07 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 98/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-08 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 112/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-08 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 129/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-09 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 143/4
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-09 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 83/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-12 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 131/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-12 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 149B/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-14 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 102/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-14 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 140/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-14 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 99/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-16 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 115/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-16 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 134A/4
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-17 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 140/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-19 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 126/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-19 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 135/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-19 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 149A/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-20 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 128/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-20 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 131/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-20 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 141/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-22 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 87/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-22 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 99/4
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-23 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 129/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-23 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 135/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-23 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 138/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-24 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 137/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-24 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 63/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-25 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 132/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-25 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 138/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-26 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 134A/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-26 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 56/4
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-27 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 56/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-28 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 138/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-28 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 149/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-29 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 134/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-29 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 134A/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-31 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 116/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-31 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 132/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-31 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 134A/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-31 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 138/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-31 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 82/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-31 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 85/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-31 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 99A/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-31 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 56/5
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-04 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 131/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-05 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 139/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-05 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 147/6
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-10 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 125/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-10 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 57/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-12 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 59/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-12 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 81/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-14 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 147/9
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-14 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 64/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-17 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 58/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-18 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 125/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-19 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 72/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-20 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 56/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-21 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 136/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-25 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 132/4
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-25 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 48/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-30 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 123/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-30 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 133/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-30 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 152/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-30 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 153A/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-10-11 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 135/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-10-13 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 149B/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-10-16 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 135/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-10-16 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 73/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-10-19 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 84/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-10-29 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 150/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-10-30 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 71/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-10-31 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 134A/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-04 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 148/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-07 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 71/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-08 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 151/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-08 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 78/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-10 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 81/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-11 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 140/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-12 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 89/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-14 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 71/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-16 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 113/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-16 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 139/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-17 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 72/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-18 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 89/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-22 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 140/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-22 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 154/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-22 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 90/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-26 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 90/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-28 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 127/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-30 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 153/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-30 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 66/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-12-05 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 118/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-12-05 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 88/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-12-06 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 130/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-12-08 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 98B/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-12-13 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 117/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-12-14 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 128/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-12-19 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 117/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-12-20 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 132/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-12-24 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 91/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-12-28 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 132/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-12-30 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 124/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-12-30 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 104A/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-12-31 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 91/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-04 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 104B/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-07 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 65/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-08 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 122/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-15 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 126/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-15 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 69/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-15 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 65/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-20 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 108/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-23 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 109/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-23 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-25 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 120/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-26 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/5
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-28 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 92/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-28 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/6
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-30 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 93/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-30 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/7
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-02-04 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/7
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-02-06 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/9
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-02-12 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/12
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-02-28 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-02-28 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 117/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-03-04 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 157/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-03-10 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 156/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-03-11 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 98B/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-03-19 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 103/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-03-22 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/8
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-03-25 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-03-26 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-03-26 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/0B
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-03-28 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/0A
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-04-06 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-04-07 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-04-08 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/1B
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-04-09 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/1 A
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-04-10 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 103/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-04-11 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-04-14 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-04-15 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 99C/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-04-15 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/4
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-04-21 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/5
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-04-23 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/14
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-04-24 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 100/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-04-28 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/11
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-02 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-02 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-03 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 155/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-03 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-03 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-06 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 154/1B
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-08 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/13
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-08 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 154/2B
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-09 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 154/1A
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-09 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 154/2A
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-11 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/6
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-14 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 13/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-16 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/8
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-17 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-19 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/4
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 |  | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_unparsed | 7/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 |  | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_unparsed | 13/3
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 |  | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_unparsed | 13/1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 |  | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_unparsed | 42/2
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 |  | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_unparsed | 9/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 |  | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_unparsed | 27/0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 |  | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_unparsed | 62/3
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-02-11 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-02-14 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 1/1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-02-16 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/2
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-02-18 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 1/2
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-02-20 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-02-28 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 1/0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-02-28 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-03-11 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-03-13 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-03-15 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/2
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-03-16 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/3
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-03-17 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/4
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-03-22 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 1/0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-03-27 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/5
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-03-31 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/2
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-04-02 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-04-04 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-04-12 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-04-16 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/5
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-04-18 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/3
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-04-21 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/2
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-04-29 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/4
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-05-05 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/5
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-05-06 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-05-08 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/2
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-05-10 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/4
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-05-15 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-05-18 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-05-19 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-05-19 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/3
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-05-20 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 |  | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_unparsed | 4/2
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 |  | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_unparsed | 4/3
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 |  | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_unparsed | 5/0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 |  | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_unparsed | 3A/1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-08-11 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 29/5 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-09-06 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 29/4 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-09-24 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 29/3 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-09-20 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 27/0 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-11-23 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 17/0 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-10-16 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 18/0 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-10-16 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 29/6 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-11-24 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 30/3 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-11-10 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 23/1 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-10-10 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 29/1 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-10-28 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 22/1 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-11-19 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 15/2 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-10-30 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 31/1 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-10-31 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 22/0 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-10-31 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 21/1 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-11-11 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 31/3 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-11-13 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 22/2 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-11-17 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 15/1 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-03 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 40/0 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-11-30 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 20/0 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-11-23 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 27/1 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-11-26 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP32 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-09 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 23/0 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-11-29 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 30/5 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-11-30 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 40/1 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-13 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 19/2 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-06 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 18/1 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-04 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP28 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-12 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 30/2 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-31 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 23/4 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-10 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 29/0 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-21 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 23/5 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-13 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 39/2 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-19 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 30/4 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-31 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP33 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-24 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP19 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-25 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP43 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-23 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP45 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-27 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 31/2 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-25 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 46/1 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-18 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP31 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-25 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP16 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-08 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 18/2 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-08 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP26 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-04 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 43/1 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-09 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 31/4 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-09 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 46/3 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-31 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP30 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-12 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 43/2 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-30 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 32/1 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-05-07 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 33/1 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-21 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 25/2 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-21 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 45/2 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-20 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 19/1 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-22 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 31/5 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-02-14 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 50A/7 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-21 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 44/3 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-02-07 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 44/2 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-02-27 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP21 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-02-05 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 45/1 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-02-08 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP15 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-02-20 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP12 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-02-13 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 25/1 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_unparsed | AP35 | WIP
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-02-20 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP46 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-02-20 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP44 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-02-25 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP25 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-03-07 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 29/2 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-02-25 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 50A/8 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-02-27 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 44/1 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-03-09 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 33/2 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-03-05 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 46/5 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-03-06 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 50A/3 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-03-08 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP14 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-03-15 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP24 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_unparsed | 30/1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-03-08 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 43/3 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-03-21 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 43/4 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-03-11 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 46/4 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-04-25 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP34 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-03-28 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 46/2 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-03-30 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 15/3 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-03-30 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 38/1 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-03-31 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 42/3 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-04-05 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 47/1 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-04-26 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP47 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-04-13 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 40/2 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-04-29 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP7 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-04-16 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 42/2 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-04-18 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP1 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-04-30 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP6 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-04-30 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP41 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-04-29 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 37/1 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-05-14 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP38 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-05-16 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 40/3 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-05-19 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 23/2 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-05-17 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 50A/2 | Completed
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_unparsed | AP42 | WIP
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_unparsed | 50A/4 | WIP
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_unparsed | 39/1 | WIP
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_unparsed | AP39 | WIP
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_unparsed | 50A/1 | WIP
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_unparsed | 23/3 | WIP
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_unparsed | 34/1 | WIP
TB 605 | TB 605 - LILO | tb605lilo | LILO | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | LILO | LILO | detail | detail_unparsed | AP7 | WIP
TB 605 | TB 605 - LILO | tb605lilo | LILO | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | LILO | LILO | detail | detail_unparsed | AP8 | WIP
TB 605 | TB 605 - LILO | tb605lilo | LILO | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | LILO | LILO | detail | detail_unparsed | AP9 | WIP
TB 605 | TB 605 - LILO | tb605lilo | LILO | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | LILO | LILO | detail | detail_unparsed | AP10 | WIP
TB 605 | TB 605 - LILO | tb605lilo | LILO | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | LILO | LILO | detail | detail_unparsed | 8/1 | WIP
TB 605 | TB 605 - LILO | tb605lilo | LILO | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | LILO | LILO | detail | detail_unparsed | AP6 | WIP
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-11 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 90/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-10-20 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 117/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-10-27 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 92/3 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-10-28 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 92/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-10-23 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 71/3 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-10-28 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 72/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-10-29 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 117/3 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-06 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 74/0 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-09 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 72/0 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-10-31 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 89/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-10-31 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 93/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-04 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 117/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-06 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 118/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-08 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 95/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-10 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 95/3 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-04 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 93/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-10 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 92/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-12 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 97/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-13 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 97/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-22 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP90 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-16 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP118 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-15 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 131/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-15 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 95/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-19 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP93 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-14 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 76/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-20 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 97/3 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-24 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP98 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-20 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 95/4 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-18 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 76/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-19 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 131/3 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-30 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP116 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-29 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP96 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-13 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP77 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-24 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 131/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-27 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP94 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-26 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 98/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-28 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 103/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-30 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 131/4 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-30 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP87 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-30 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP99 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP75 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-05 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 82/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-07 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP100 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-09 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP117 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-07 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP95 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-04 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 104/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-18 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP103 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-06 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 99/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-10 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 82/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-06 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 76/3 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-10 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 77/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-15 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP106 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-13 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP104 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-16 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP135 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-29 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 135/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-16 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 85/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-17 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 106/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-19 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 136/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-17 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 130/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-24 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP85 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-21 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 135/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-16 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 77/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-18 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 102/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-20 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 130/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-25 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP80 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-20 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 116/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-26 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 156/4 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-24 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 139/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-07 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 69/3 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-24 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 131/6 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-27 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 150/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-26 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 138/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-28 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 137/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-27 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 131/5 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-05 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP146 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-29 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP102 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-30 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 80/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-30 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 86/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-30 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 156/3 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-04 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 150/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-31 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 132/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-31 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 138/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-08 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 156/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-09 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 155/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-11 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP131 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-16 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 90/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-22 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP115 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-11 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 152/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-10 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 137/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-12 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 87/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-20 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 145/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-16 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP147 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-18 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP154 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-16 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 152/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-20 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP138 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-17 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP157 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-20 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP129 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-22 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 69/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-22 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 156/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-05 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 153/0 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-12 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP130 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-13 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP92 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-21 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 71/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-31 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 151/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-27 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 69/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-06 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP139 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-30 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 155/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-31 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 115/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-11 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 136/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-31 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 155/3 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-08 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP97 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-09 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP155 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-07 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 151/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-12 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 152/4 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-14 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP156 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-21 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 70/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-13 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 153/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-19 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP111 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-15 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 136/3 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-15 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 157/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-18 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP150 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-18 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP70 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-20 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 136/4 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-21 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP68 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-27 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP91 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-18 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 153/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-25 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP79 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-17 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 72/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-27 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP137 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-24 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP132 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-16 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP148 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-28 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP159 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-26 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 67/3 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-02 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP69 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-28 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 145/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-10 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP149 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-28 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP114 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-26 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 70/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-13 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 67/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-23 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP71 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-31 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 56/3 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-26 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP152 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-28 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP108 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-15 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP127 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-25 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP145 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-18 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP136 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-30 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP67 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-19 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 67/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-31 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 152/3 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-06 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP125 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-30 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP124 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-19 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP70/3 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-12 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP109 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-05 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 144/4 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-07 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 144/3 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-07 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 65/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-27 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP59 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-22 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP165 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-28 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 55/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-21 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP61 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-15 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP126 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-29 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP142 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-30 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP166 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-26 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP123 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-25 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 56/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-23 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP86 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-07 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP144 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP64 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-09 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP161 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-08 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP82 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-07 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP56 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-30 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 122/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-07 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 64/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-08 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 142/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-16 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 65/4 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-08 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 61/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-09 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 57/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-18 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP128 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-11 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP163 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-16 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 159/3 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_unparsed | AP158 | WIP
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-17 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP162 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-14 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP110 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-14 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 71/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-15 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP57 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-14 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 62/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-18 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP143 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-13 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 56/4 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-17 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP60 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-18 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP63 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_unparsed | 59/1 | WIP
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-18 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 62/1 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_unparsed | AP84 | WIP
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_unparsed | AP78 | WIP
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-19 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP112 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-19 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 159/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_unparsed | AP55 | WIP
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-19 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 57/2 | Completed
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_unparsed | 60/1 | WIP
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_unparsed | 65/5 | WIP
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_unparsed | AP81 | WIP
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_unparsed | 65/1 | WIP
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_unparsed | AP134 | WIP
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_unparsed | AP113 | WIP
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_unparsed | 143/1 | WIP
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_unparsed | AP168 | WIP
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 |  | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_unparsed | 159/1 | WIP
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-10-18 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 69/2
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-10-18 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 65/3
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-09 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 131/2
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-10 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 58/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-10 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 69/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-11 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 58/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-15 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 75/5
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-18 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 34/3
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-19 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 101/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-20 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 71/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-22 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 33/2
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-22 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 90/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-25 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 40/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-25 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 29/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-28 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 72/6
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-28 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 88/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-30 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 100/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-30 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 103/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-30 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 109/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-30 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 85/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-30 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 71/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-30 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 89/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-02 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 29/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-03 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 75/3
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-08 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 69/3
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-11 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 80/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-12 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 108/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-12 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 111/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-14 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 48/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-14 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 29/4
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-17 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 29/3
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-18 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 99/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-18 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 75/4
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-19 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 102/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-19 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 84/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-21 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 83/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-21 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 91/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-21 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 111/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-21 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 93/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-22 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 34/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-23 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 25/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-23 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 70/3
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-25 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 29/2
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-27 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 91/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-27 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 112/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-27 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 49/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-28 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 91/2
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-28 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 79/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-31 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 86/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-31 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 77/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-31 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 91/8
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-31 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 70/2
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-31 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 114/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-31 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 94/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-02 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 41/2
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-04 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 70/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-07 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 40/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-09 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 97/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-10 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 41/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-11 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 76/3
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-11 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 113/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-12 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 91/5
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-13 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 110/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-14 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 115/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-15 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 76/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-18 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 69/4
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-19 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 75/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-21 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 50/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-25 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 123/2
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-27 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 34/2
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-27 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 129/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-28 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 47/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-28 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 79/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-29 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 69/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-29 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 91/7
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-29 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 132/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-30 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 96/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-31 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 131/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-31 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 75/2
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-31 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 128/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-31 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 91/4
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-05 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 76/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-05 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 73/6
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-05 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 59/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-05 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 96/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-05 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 81/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-08 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 42/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-08 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 104/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-10 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 43/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-10 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 126/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-11 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 72/7
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-12 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 78/2
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-14 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 95/3
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-16 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 95/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-17 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 131/3
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-18 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 129/2
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-18 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 95/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-19 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 44/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-19 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 131/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-20 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 30/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-22 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 71/2
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-22 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 124/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-23 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 70/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-23 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 72/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-25 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 127/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-28 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 95/2
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-28 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 132/2
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-28 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 132/3
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-06 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 31/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-08 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 35/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-10 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 82/2
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-10 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 129/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-10 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 130/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-11 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 82/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-12 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 116/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-14 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 27/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-19 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 125/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-28 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 47/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-29 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 132/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-31 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 34/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-04-13 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 92/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-04-19 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 107/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 61A/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 106/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 39/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 38/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 78/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 61/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 62/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 105/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 62/3
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 91/6
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 91/9
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 31/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 132/4
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 128/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 1/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 2/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 3/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 4/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-18 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 5/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 6/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-18 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 6/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 6/2
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 7/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 8/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 9/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 10/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-10 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 10/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 10/2
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-22 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 10/3
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 11/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-24 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 11/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-03 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 11/2
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 12/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 13/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 14/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 14/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 14/2
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 15/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 16/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 17/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 18/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 1/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 2/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 2/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 3/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 4/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-25 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 4/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-10 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 5/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 6/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 7/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 7/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-31 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 7/2
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-14 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 8/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 9/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-11 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 9/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 10/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 11/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 12/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 12/1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 12/2
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 12/3
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 13/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 14/0
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_unparsed | 15/0

## FoundationCompletions
project_code | project_display | project_scope_key | line_name | line_name_source | report_date | event_date | period_week_start | period_month | source_file | source_sheet | configured_sheet | source_type | quality_flag | location_no | event_value | cumulative_foundation
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-06 | 2024-06-02 | 2024-06-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-07 | 2024-06-02 | 2024-06-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-09 | 2024-06-09 | 2024-06-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-11 | 2024-06-09 | 2024-06-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/11 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-17 | 2024-06-16 | 2024-06-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 15/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-17 | 2024-06-16 | 2024-06-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-18 | 2024-06-16 | 2024-06-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 15/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-21 | 2024-06-16 | 2024-06-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 15/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-23 | 2024-06-23 | 2024-06-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-24 | 2024-06-23 | 2024-06-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 15/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-26 | 2024-06-23 | 2024-06-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-27 | 2024-06-23 | 2024-06-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 15/6 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-28 | 2024-06-23 | 2024-06-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/10 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-06-29 | 2024-06-23 | 2024-06-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-03 | 2024-06-30 | 2024-07-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 15/9 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-03 | 2024-06-30 | 2024-07-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/6 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-06 | 2024-06-30 | 2024-07-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 15/8 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-06 | 2024-06-30 | 2024-07-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/9 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-09 | 2024-07-07 | 2024-07-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/7 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-10 | 2024-07-07 | 2024-07-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 15/10 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-10 | 2024-07-07 | 2024-07-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/8 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-10 | 2024-07-07 | 2024-07-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-11 | 2024-07-07 | 2024-07-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 15/7 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-15 | 2024-07-14 | 2024-07-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/7 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-18 | 2024-07-14 | 2024-07-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 15/11 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-19 | 2024-07-14 | 2024-07-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/8 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-20 | 2024-07-14 | 2024-07-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-22 | 2024-07-21 | 2024-07-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/6 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-24 | 2024-07-21 | 2024-07-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-25 | 2024-07-21 | 2024-07-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-25 | 2024-07-21 | 2024-07-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/9 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-28 | 2024-07-28 | 2024-07-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/10 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-29 | 2024-07-28 | 2024-07-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-07-31 | 2024-07-28 | 2024-07-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-01 | 2024-07-28 | 2024-08-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-03 | 2024-07-28 | 2024-08-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-03 | 2024-07-28 | 2024-08-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-08 | 2024-08-04 | 2024-08-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29A/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-08 | 2024-08-04 | 2024-08-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-10 | 2024-08-04 | 2024-08-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-13 | 2024-08-11 | 2024-08-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/10 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-14 | 2024-08-11 | 2024-08-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29A/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-16 | 2024-08-11 | 2024-08-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 27/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-17 | 2024-08-11 | 2024-08-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7A/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-18 | 2024-08-18 | 2024-08-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/8 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-20 | 2024-08-18 | 2024-08-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29A/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-20 | 2024-08-18 | 2024-08-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-23 | 2024-08-18 | 2024-08-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7A/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-24 | 2024-08-18 | 2024-08-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29A/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-25 | 2024-08-25 | 2024-08-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-26 | 2024-08-25 | 2024-08-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-27 | 2024-08-25 | 2024-08-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29A/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-27 | 2024-08-25 | 2024-08-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-28 | 2024-08-25 | 2024-08-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 27/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-30 | 2024-08-25 | 2024-08-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/6 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-30 | 2024-08-25 | 2024-08-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-08-31 | 2024-08-25 | 2024-08-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29A/6 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-01 | 2024-09-01 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4A/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-01 | 2024-09-01 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7A/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-04 | 2024-09-01 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/7 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-04 | 2024-09-01 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/10 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-05 | 2024-09-01 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/12 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-06 | 2024-09-01 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4A/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-06 | 2024-09-01 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7A/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-07 | 2024-09-01 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-09 | 2024-09-08 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-09 | 2024-09-08 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4A/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-10 | 2024-09-08 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-10 | 2024-09-08 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7A/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-12 | 2024-09-08 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4A/6 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-12 | 2024-09-08 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/7 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-13 | 2024-09-08 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-13 | 2024-09-08 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/12 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-14 | 2024-09-08 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/11 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-15 | 2024-09-15 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-15 | 2024-09-15 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36A/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-15 | 2024-09-15 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/6 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-16 | 2024-09-15 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4A/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-18 | 2024-09-15 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-19 | 2024-09-15 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36A/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-20 | 2024-09-15 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 27/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-20 | 2024-09-15 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/11 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-20 | 2024-09-15 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-21 | 2024-09-15 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-21 | 2024-09-15 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4A/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-23 | 2024-09-22 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-23 | 2024-09-22 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-23 | 2024-09-22 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/6 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-25 | 2024-09-22 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-26 | 2024-09-22 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-27 | 2024-09-22 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-27 | 2024-09-22 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-28 | 2024-09-22 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 27/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-28 | 2024-09-22 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/6 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-29 | 2024-09-29 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/10 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-30 | 2024-09-29 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/8 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-09-30 | 2024-09-29 | 2024-09-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-01 | 2024-09-29 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4A/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-01 | 2024-09-29 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/9 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-01 | 2024-09-29 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-03 | 2024-09-29 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-04 | 2024-09-29 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/7 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-05 | 2024-09-29 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/8 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-05 | 2024-09-29 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36A/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-07 | 2024-10-06 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/9 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-07 | 2024-10-06 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/9 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-08 | 2024-10-06 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 27/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-08 | 2024-10-06 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-09 | 2024-10-06 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/9 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-09 | 2024-10-06 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/6 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-12 | 2024-10-06 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/10 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-12 | 2024-10-06 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/10 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-12 | 2024-10-06 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-14 | 2024-10-13 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 27/6 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-14 | 2024-10-13 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-16 | 2024-10-13 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/11 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-16 | 2024-10-13 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-16 | 2024-10-13 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/7 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-17 | 2024-10-13 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/7 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-18 | 2024-10-13 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-19 | 2024-10-13 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/7 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-19 | 2024-10-13 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-21 | 2024-10-20 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37A/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-22 | 2024-10-20 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/6 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-22 | 2024-10-20 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-23 | 2024-10-20 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-25 | 2024-10-20 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-25 | 2024-10-20 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/8 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-25 | 2024-10-20 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37A/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-27 | 2024-10-27 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/9 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-29 | 2024-10-27 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-29 | 2024-10-27 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/8 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-10-30 | 2024-10-27 | 2024-10-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37A/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-07 | 2024-11-03 | 2024-11-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29A/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-08 | 2024-11-03 | 2024-11-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37A/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-08 | 2024-11-03 | 2024-11-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/8 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-09 | 2024-11-03 | 2024-11-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/11 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-11 | 2024-11-10 | 2024-11-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/9 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-12 | 2024-11-10 | 2024-11-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-12 | 2024-11-10 | 2024-11-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37A/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-16 | 2024-11-10 | 2024-11-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-17 | 2024-11-17 | 2024-11-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-19 | 2024-11-17 | 2024-11-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-20 | 2024-11-17 | 2024-11-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-20 | 2024-11-17 | 2024-11-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/8 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-21 | 2024-11-17 | 2024-11-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-21 | 2024-11-17 | 2024-11-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/9 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-22 | 2024-11-17 | 2024-11-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7A/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-23 | 2024-11-17 | 2024-11-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-23 | 2024-11-17 | 2024-11-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/10 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-24 | 2024-11-24 | 2024-11-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-26 | 2024-11-24 | 2024-11-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/7 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-27 | 2024-11-24 | 2024-11-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-27 | 2024-11-24 | 2024-11-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37A/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-29 | 2024-11-24 | 2024-11-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-29 | 2024-11-24 | 2024-11-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/6 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-11-30 | 2024-11-24 | 2024-11-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-01 | 2024-12-01 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-04 | 2024-12-01 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/6 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-04 | 2024-12-01 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-06 | 2024-12-01 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-06 | 2024-12-01 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-07 | 2024-12-01 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-08 | 2024-12-08 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37A/6 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-08 | 2024-12-08 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-10 | 2024-12-08 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-12 | 2024-12-08 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-12 | 2024-12-08 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-13 | 2024-12-08 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-14 | 2024-12-08 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-15 | 2024-12-15 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 39/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-17 | 2024-12-15 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-18 | 2024-12-15 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-19 | 2024-12-15 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 17/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-19 | 2024-12-15 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/7 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-21 | 2024-12-15 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 39/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-21 | 2024-12-15 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 39/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-21 | 2024-12-15 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/6 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-22 | 2024-12-22 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-23 | 2024-12-22 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 39/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-25 | 2024-12-22 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/8 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-27 | 2024-12-22 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 41/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-28 | 2024-12-22 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 16/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-29 | 2024-12-29 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-29 | 2024-12-29 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 39/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-29 | 2024-12-29 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-30 | 2024-12-29 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/6 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-31 | 2024-12-29 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 15/12 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2024-12-31 | 2024-12-29 | 2024-12-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-03 | 2024-12-29 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-03 | 2024-12-29 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 42/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-05 | 2025-01-05 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 39/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-05 | 2025-01-05 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/9 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-06 | 2025-01-05 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-07 | 2025-01-05 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/6 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-08 | 2025-01-05 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 42/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-09 | 2025-01-05 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 39/6 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-09 | 2025-01-05 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/10 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-10 | 2025-01-05 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/7 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-13 | 2025-01-12 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/8 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-13 | 2025-01-12 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/11 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-13 | 2025-01-12 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 42/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-13 | 2025-01-12 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-15 | 2025-01-12 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 22/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-17 | 2025-01-12 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/9 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-17 | 2025-01-12 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 39/7 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-19 | 2025-01-19 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 41/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-20 | 2025-01-19 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40A/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-21 | 2025-01-19 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-21 | 2025-01-19 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/10 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-21 | 2025-01-19 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 43/7 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-22 | 2025-01-19 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 23/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-23 | 2025-01-19 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 43/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-24 | 2025-01-19 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 39/8 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-24 | 2025-01-19 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-25 | 2025-01-19 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 43/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-25 | 2025-01-19 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 43/8 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-27 | 2025-01-26 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 15/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-28 | 2025-01-26 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 43/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-29 | 2025-01-26 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-30 | 2025-01-26 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 23A/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-31 | 2025-01-26 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-31 | 2025-01-26 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 39/9 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-01-31 | 2025-01-26 | 2025-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 42/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-02 | 2025-02-02 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 43/6 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-04 | 2025-02-02 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/7 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-04 | 2025-02-02 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-04 | 2025-02-02 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 44/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-05 | 2025-02-02 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 43/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-07 | 2025-02-02 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-08 | 2025-02-02 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 43/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-09 | 2025-02-09 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-09 | 2025-02-09 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 43/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-10 | 2025-02-09 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-11 | 2025-02-09 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 13/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-11 | 2025-02-09 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 39/10 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-12 | 2025-02-09 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-13 | 2025-02-09 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/11 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-16 | 2025-02-16 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-16 | 2025-02-16 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 21/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-17 | 2025-02-16 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/7 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-18 | 2025-02-16 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 13A/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-18 | 2025-02-16 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32A/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-19 | 2025-02-16 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/6 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-20 | 2025-02-16 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-22 | 2025-02-16 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 21/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-22 | 2025-02-16 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32A/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-23 | 2025-02-23 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-24 | 2025-02-23 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 39/11 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-25 | 2025-02-23 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 27/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-25 | 2025-02-23 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/9 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-26 | 2025-02-23 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 28/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-26 | 2025-02-23 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/7 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-02-27 | 2025-02-23 | 2025-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 24/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 44/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-05 | 2025-03-02 | 2025-03-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 26/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-05 | 2025-03-02 | 2025-03-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/8 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-06 | 2025-03-02 | 2025-03-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 15/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-06 | 2025-03-02 | 2025-03-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 44/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-08 | 2025-03-02 | 2025-03-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 25/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-08 | 2025-03-02 | 2025-03-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-12 | 2025-03-09 | 2025-03-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 44/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-13 | 2025-03-09 | 2025-03-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 44/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-16 | 2025-03-16 | 2025-03-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-17 | 2025-03-16 | 2025-03-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 44/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-23 | 2025-03-23 | 2025-03-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2A/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-23 | 2025-03-23 | 2025-03-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3B/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-23 | 2025-03-23 | 2025-03-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-26 | 2025-03-23 | 2025-03-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3B/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-27 | 2025-03-23 | 2025-03-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2A/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-30 | 2025-03-30 | 2025-03-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2A/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-30 | 2025-03-30 | 2025-03-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3B/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-03-30 | 2025-03-30 | 2025-03-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5A/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-03 | 2025-03-30 | 2025-04-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3A/6 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-05 | 2025-03-30 | 2025-04-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2A/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-08 | 2025-04-06 | 2025-04-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-08 | 2025-04-06 | 2025-04-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3A/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-08 | 2025-04-06 | 2025-04-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3A/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-10 | 2025-04-06 | 2025-04-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3A/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-11 | 2025-04-06 | 2025-04-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/6 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-12 | 2025-04-06 | 2025-04-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-12 | 2025-04-06 | 2025-04-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3A/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-14 | 2025-04-13 | 2025-04-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-15 | 2025-04-13 | 2025-04-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-15 | 2025-04-13 | 2025-04-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3A/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-16 | 2025-04-13 | 2025-04-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 14/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-17 | 2025-04-13 | 2025-04-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-18 | 2025-04-13 | 2025-04-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3A/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-19 | 2025-04-13 | 2025-04-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3B/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-22 | 2025-04-20 | 2025-04-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 21/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-23 | 2025-04-20 | 2025-04-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2A/6 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-24 | 2025-04-20 | 2025-04-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 21/2 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-25 | 2025-04-20 | 2025-04-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-25 | 2025-04-20 | 2025-04-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8A/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-04-29 | 2025-04-27 | 2025-04-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 21/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-05-02 | 2025-04-27 | 2025-05-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/10 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-05-03 | 2025-04-27 | 2025-05-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-05-05 | 2025-05-04 | 2025-05-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 45/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-05-07 | 2025-05-04 | 2025-05-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 46/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-05-09 | 2025-05-04 | 2025-05-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/6 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-05-13 | 2025-05-11 | 2025-05-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/5 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-05-13 | 2025-05-11 | 2025-05-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 21/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-05-18 | 2025-05-18 | 2025-05-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/4 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-05-22 | 2025-05-18 | 2025-05-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/3 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-05-26 | 2025-05-25 | 2025-05-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 19/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-06-02 | 2025-06-01 | 2025-06-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-06-08 | 2025-06-08 | 2025-06-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 11/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-06-14 | 2025-06-08 | 2025-06-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 12/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-06-27 | 2025-06-22 | 2025-06-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 1/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-07-05 | 2025-06-29 | 2025-07-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2A/1 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2025-07-14 | 2025-07-13 | 2025-07-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2A/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2026-01-23 | 2026-01-18 | 2026-01-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36B/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2026-02-08 | 2026-02-08 | 2026-02-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | N'37/0 | 1
TA 413 | TA 413 | ta413 |  | filename | 2026-05-20 | 2026-03-05 | 2026-03-01 | 2026-03-01 | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | N'37A/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-05-15 | 2024-05-12 | 2024-05-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 241/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-05-21 | 2024-05-19 | 2024-05-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 241/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-05-28 | 2024-05-26 | 2024-05-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 241/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-08-31 | 2024-08-25 | 2024-08-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 235/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-09-20 | 2024-09-15 | 2024-09-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 118/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-11-02 | 2024-10-27 | 2024-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 121/5 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-11-04 | 2024-11-03 | 2024-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 120/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-11-09 | 2024-11-03 | 2024-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 120/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-11-19 | 2024-11-17 | 2024-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 121/4 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-11-30 | 2024-11-24 | 2024-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 120/5 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-01 | 2024-12-01 | 2024-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 121/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-03 | 2024-12-01 | 2024-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 119/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-05 | 2024-12-01 | 2024-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 120/6 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-08 | 2024-12-08 | 2024-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 120/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-09 | 2024-12-08 | 2024-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 121/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-11 | 2024-12-08 | 2024-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 119/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-11 | 2024-12-08 | 2024-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 145/4 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-13 | 2024-12-08 | 2024-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 244/6 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-17 | 2024-12-15 | 2024-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 121/6 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-19 | 2024-12-15 | 2024-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 249/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-21 | 2024-12-15 | 2024-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 119/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-24 | 2024-12-22 | 2024-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 121/7 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-26 | 2024-12-22 | 2024-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 249/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-27 | 2024-12-22 | 2024-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 137/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-28 | 2024-12-22 | 2024-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 249/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2024-12-30 | 2024-12-29 | 2024-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 145/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-03 | 2024-12-29 | 2025-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 121/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-07 | 2025-01-05 | 2025-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 244/5 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-07 | 2025-01-05 | 2025-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 250/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-10 | 2025-01-05 | 2025-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 120/7 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-10 | 2025-01-05 | 2025-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 121/8 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-15 | 2025-01-12 | 2025-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 137/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-15 | 2025-01-12 | 2025-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 145/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-17 | 2025-01-12 | 2025-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 252/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-19 | 2025-01-19 | 2025-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 136/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-20 | 2025-01-19 | 2025-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 121/9 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-20 | 2025-01-19 | 2025-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 250A/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-22 | 2025-01-19 | 2025-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 252/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-27 | 2025-01-26 | 2025-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 141/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-27 | 2025-01-26 | 2025-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 141/4 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-28 | 2025-01-26 | 2025-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 121/10 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-28 | 2025-01-26 | 2025-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 145/7 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-29 | 2025-01-26 | 2025-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 241/4 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-29 | 2025-01-26 | 2025-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 248/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-01-31 | 2025-01-26 | 2025-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 124/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 137/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-02-03 | 2025-02-02 | 2025-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 248/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-02-07 | 2025-02-02 | 2025-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 124/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-02-07 | 2025-02-02 | 2025-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 126/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-02-07 | 2025-02-02 | 2025-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 148/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-02-07 | 2025-02-02 | 2025-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 243/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-02-08 | 2025-02-02 | 2025-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 141/5 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-02-13 | 2025-02-09 | 2025-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 243/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-02-14 | 2025-02-09 | 2025-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 250/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-02-23 | 2025-02-23 | 2025-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 244/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 180/4 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-02 | 2025-03-02 | 2025-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 132/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-03 | 2025-03-02 | 2025-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 117/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-03 | 2025-03-02 | 2025-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 117/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-06 | 2025-03-02 | 2025-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 121/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-07 | 2025-03-02 | 2025-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 172/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-11 | 2025-03-09 | 2025-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 179/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-11 | 2025-03-09 | 2025-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 180/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-11 | 2025-03-09 | 2025-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 180/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-11 | 2025-03-09 | 2025-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 180/5 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-11 | 2025-03-09 | 2025-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 251/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-13 | 2025-03-09 | 2025-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 171/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-15 | 2025-03-09 | 2025-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 132/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-19 | 2025-03-16 | 2025-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 174/6 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-24 | 2025-03-23 | 2025-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 165/7 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-24 | 2025-03-23 | 2025-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 172/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-03-31 | 2025-03-30 | 2025-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 165/5 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 174/4 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-04-02 | 2025-03-30 | 2025-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 179/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-04-03 | 2025-03-30 | 2025-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 180/7 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-04-06 | 2025-04-06 | 2025-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 174/5 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-04-10 | 2025-04-06 | 2025-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 174/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-04-11 | 2025-04-06 | 2025-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 176/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-04-11 | 2025-04-06 | 2025-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 177/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-04-13 | 2025-04-13 | 2025-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 175/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-04-20 | 2025-04-20 | 2025-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 176/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-04-23 | 2025-04-20 | 2025-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 148/4 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-04-24 | 2025-04-20 | 2025-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 178/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-05-02 | 2025-04-27 | 2025-05-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 165/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-05-02 | 2025-04-27 | 2025-05-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 252/5 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-05-05 | 2025-05-04 | 2025-05-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 148/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-05-08 | 2025-05-04 | 2025-05-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 180/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-05-10 | 2025-05-04 | 2025-05-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 130/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-05-15 | 2025-05-11 | 2025-05-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 243/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-05-19 | 2025-05-18 | 2025-05-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 256/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-08-04 | 2025-08-03 | 2025-08-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 246/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-08-05 | 2025-08-03 | 2025-08-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 131/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-08-11 | 2025-08-10 | 2025-08-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 120/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-08-14 | 2025-08-10 | 2025-08-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 241/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-08-27 | 2025-08-24 | 2025-08-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 250A/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-09-23 | 2025-09-21 | 2025-09-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 178/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-10-12 | 2025-10-12 | 2025-10-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 119/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-10-12 | 2025-10-12 | 2025-10-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 224/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-10-15 | 2025-10-12 | 2025-10-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 120/4 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-10-15 | 2025-10-12 | 2025-10-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 224/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-10-15 | 2025-10-12 | 2025-10-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 225/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-10-16 | 2025-10-12 | 2025-10-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 223/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-10-21 | 2025-10-19 | 2025-10-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 221/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-10-26 | 2025-10-26 | 2025-10-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 139/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-10-26 | 2025-10-26 | 2025-10-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 220/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-10-26 | 2025-10-26 | 2025-10-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 223/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-10-26 | 2025-10-26 | 2025-10-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 223/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-10-26 | 2025-10-26 | 2025-10-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 224/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-10-31 | 2025-10-26 | 2025-10-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 125/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-01 | 2025-10-26 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 222/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-03 | 2025-11-02 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 138/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-03 | 2025-11-02 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 185/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-04 | 2025-11-02 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 135/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-04 | 2025-11-02 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 144/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-04 | 2025-11-02 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 220/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-05 | 2025-11-02 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 136/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-06 | 2025-11-02 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 218/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-10 | 2025-11-09 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 141/6 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-11 | 2025-11-09 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 142/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-11 | 2025-11-09 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 186/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-11 | 2025-11-09 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 196/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-12 | 2025-11-09 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 223/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-13 | 2025-11-09 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 214/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-16 | 2025-11-16 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 187/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-18 | 2025-11-16 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 219/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-19 | 2025-11-16 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 148/5 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-20 | 2025-11-16 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 176/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-20 | 2025-11-16 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 215/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-22 | 2025-11-16 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 214/5 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-22 | 2025-11-16 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 225/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-23 | 2025-11-23 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 143/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-23 | 2025-11-23 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 183/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-24 | 2025-11-23 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 194/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-24 | 2025-11-23 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 214/7 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-25 | 2025-11-23 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 225/4 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-26 | 2025-11-23 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 161/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-26 | 2025-11-23 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 184/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-26 | 2025-11-23 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 214/4 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-27 | 2025-11-23 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 139/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-27 | 2025-11-23 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 145/5 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-27 | 2025-11-23 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 214/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 182/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 183/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 244/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-01 | 2025-11-30 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 127/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-01 | 2025-11-30 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 148/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-04 | 2025-11-30 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 128/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-04 | 2025-11-30 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 175/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-04 | 2025-11-30 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 194/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-05 | 2025-11-30 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 145/6 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-05 | 2025-11-30 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 183/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-05 | 2025-11-30 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 214/6 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-05 | 2025-11-30 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 217/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-05 | 2025-11-30 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 217/4 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-05 | 2025-11-30 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 225/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-05 | 2025-11-30 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 244/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-05 | 2025-11-30 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 250/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-06 | 2025-11-30 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 141/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-06 | 2025-11-30 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 141/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-08 | 2025-12-07 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 127/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-08 | 2025-12-07 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 166/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-08 | 2025-12-07 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 243/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-09 | 2025-12-07 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 190/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-09 | 2025-12-07 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 256/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-10 | 2025-12-07 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 249/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-11 | 2025-12-07 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 225/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-12 | 2025-12-07 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 180/6 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-12 | 2025-12-07 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 189/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-12 | 2025-12-07 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 250A/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-13 | 2025-12-07 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 183/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-13 | 2025-12-07 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 191/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-13 | 2025-12-07 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 197/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-13 | 2025-12-07 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 197/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-13 | 2025-12-07 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 198/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-13 | 2025-12-07 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 199/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-13 | 2025-12-07 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 210/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-13 | 2025-12-07 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 254/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-15 | 2025-12-14 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 149/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-15 | 2025-12-14 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 216/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-15 | 2025-12-14 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 217/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-16 | 2025-12-14 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 139/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-16 | 2025-12-14 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 216/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-16 | 2025-12-14 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 257/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-17 | 2025-12-14 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 127/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-17 | 2025-12-14 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 170/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-18 | 2025-12-14 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 148/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-18 | 2025-12-14 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 173/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-18 | 2025-12-14 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 174/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-18 | 2025-12-14 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 174/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-19 | 2025-12-14 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 196/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-19 | 2025-12-14 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 196/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-19 | 2025-12-14 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 252/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-19 | 2025-12-14 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 252/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-20 | 2025-12-14 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 139/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-20 | 2025-12-14 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 165/6 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-20 | 2025-12-14 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 167/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-20 | 2025-12-14 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 193/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-20 | 2025-12-14 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 250/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-20 | 2025-12-14 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 255/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-21 | 2025-12-21 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 141/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-22 | 2025-12-21 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 140/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-23 | 2025-12-21 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 178/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-23 | 2025-12-21 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 179/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-25 | 2025-12-21 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 216/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-25 | 2025-12-21 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 216/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-26 | 2025-12-21 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 191/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-26 | 2025-12-21 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 192/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-26 | 2025-12-21 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 244/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-27 | 2025-12-21 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 199/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-27 | 2025-12-21 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 244/4 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-28 | 2025-12-28 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 199/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-29 | 2025-12-28 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 162/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2025-12-31 | 2025-12-28 | 2025-12-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 126/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-01 | 2025-12-28 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 211/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-01 | 2025-12-28 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 211/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-03 | 2025-12-28 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 245/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-03 | 2025-12-28 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 245/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-04 | 2026-01-04 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 227/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-04 | 2026-01-04 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 227/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-04 | 2026-01-04 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 230/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-06 | 2026-01-04 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 125/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-06 | 2026-01-04 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 132/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-06 | 2026-01-04 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 133/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-06 | 2026-01-04 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 133/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-06 | 2026-01-04 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 160/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-08 | 2026-01-04 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 211/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-09 | 2026-01-04 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 178/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-12 | 2026-01-11 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 217/5 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-13 | 2026-01-11 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 174/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-13 | 2026-01-11 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 211/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-15 | 2026-01-11 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 211/4 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-16 | 2026-01-11 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 125/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-16 | 2026-01-11 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 188/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-16 | 2026-01-11 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 212/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-17 | 2026-01-11 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 197/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-18 | 2026-01-18 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 189/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-18 | 2026-01-18 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 209/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-18 | 2026-01-18 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 211/5 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-18 | 2026-01-18 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 213/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-19 | 2026-01-18 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 133/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-19 | 2026-01-18 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 165/4 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-19 | 2026-01-18 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 232/4 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-19 | 2026-01-18 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 233/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-19 | 2026-01-18 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 235/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-20 | 2026-01-18 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 168/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-20 | 2026-01-18 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 238/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-20 | 2026-01-18 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 240/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-21 | 2026-01-18 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 235/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-21 | 2026-01-18 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 236/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-22 | 2026-01-18 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 226/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-23 | 2026-01-18 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 129/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-26 | 2026-01-25 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 163/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-26 | 2026-01-25 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 252/4 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-29 | 2026-01-25 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 147/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-01-30 | 2026-01-25 | 2026-01-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 134/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-01 | 2026-02-01 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 124/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-01 | 2026-02-01 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 124/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-01 | 2026-02-01 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 228/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-05 | 2026-02-01 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 214/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-05 | 2026-02-01 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 237/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-05 | 2026-02-01 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 242/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-07 | 2026-02-01 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 232/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-07 | 2026-02-01 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 235/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-10 | 2026-02-08 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 228/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-11 | 2026-02-08 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 133/4 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-13 | 2026-02-08 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 217/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-13 | 2026-02-08 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 217/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-13 | 2026-02-08 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 248/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-14 | 2026-02-08 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 145/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-15 | 2026-02-15 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 214/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-16 | 2026-02-15 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 126/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-16 | 2026-02-15 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 240/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-17 | 2026-02-15 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 209/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-17 | 2026-02-15 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 209/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-17 | 2026-02-15 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 219/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-18 | 2026-02-15 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 126/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-19 | 2026-02-15 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 207/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-19 | 2026-02-15 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 239/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-21 | 2026-02-15 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 226/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-23 | 2026-02-22 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 133/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-02-25 | 2026-02-22 | 2026-02-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 255/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-01 | 2026-03-01 | 2026-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 226/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-01 | 2026-03-01 | 2026-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 239/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-03 | 2026-03-01 | 2026-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 145/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-11 | 2026-03-08 | 2026-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 227/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-11 | 2026-03-08 | 2026-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 234/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-12 | 2026-03-08 | 2026-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 231/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-13 | 2026-03-08 | 2026-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 131/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-13 | 2026-03-08 | 2026-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 251/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-16 | 2026-03-15 | 2026-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 121/11 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-16 | 2026-03-15 | 2026-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 150/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-16 | 2026-03-15 | 2026-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 180/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-16 | 2026-03-15 | 2026-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 225/7 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-16 | 2026-03-15 | 2026-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 232/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-18 | 2026-03-15 | 2026-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 225/5 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-19 | 2026-03-15 | 2026-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 179/2 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-22 | 2026-03-22 | 2026-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 226/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-23 | 2026-03-22 | 2026-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 230/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-25 | 2026-03-22 | 2026-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 156/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-26 | 2026-03-22 | 2026-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 150/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-03-26 | 2026-03-22 | 2026-03-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 230A/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-01 | 2026-03-29 | 2026-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 200/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-05 | 2026-04-05 | 2026-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 155/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-05 | 2026-04-05 | 2026-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 156/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-05 | 2026-04-05 | 2026-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 159/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-05 | 2026-04-05 | 2026-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 195/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-05 | 2026-04-05 | 2026-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 232/3 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-09 | 2026-04-05 | 2026-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 151/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-12 | 2026-04-12 | 2026-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 164/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-12 | 2026-04-12 | 2026-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 165/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-14 | 2026-04-12 | 2026-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 131/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-17 | 2026-04-12 | 2026-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 229B/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-21 | 2026-04-19 | 2026-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 151A/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-21 | 2026-04-19 | 2026-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 153/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-21 | 2026-04-19 | 2026-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 229A/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-23 | 2026-04-19 | 2026-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 235/4 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-26 | 2026-04-26 | 2026-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 169/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-27 | 2026-04-26 | 2026-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 206/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-04-27 | 2026-04-26 | 2026-04-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 225/6 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-05-02 | 2026-04-26 | 2026-05-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 206/1 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-05-09 | 2026-05-03 | 2026-05-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 201/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-05-09 | 2026-05-03 | 2026-05-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 203/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-05-09 | 2026-05-03 | 2026-05-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 203A/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-05-09 | 2026-05-03 | 2026-05-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 203B/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-05-13 | 2026-05-10 | 2026-05-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 153A/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-05-14 | 2026-05-10 | 2026-05-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 229/0 | 1
TA 414 | TA 414 | ta414 |  | filename | 2026-05-21 | 2026-05-20 | 2026-05-17 | 2026-05-01 | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | detail | detail_date | 153/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-04-24 | 2024-04-21 | 2024-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-05-01 | 2024-04-28 | 2024-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-05-09 | 2024-05-05 | 2024-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-05-13 | 2024-05-12 | 2024-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-05-16 | 2024-05-12 | 2024-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-05-22 | 2024-05-19 | 2024-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-05-28 | 2024-05-26 | 2024-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/10 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-05-31 | 2024-05-26 | 2024-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-05-31 | 2024-05-26 | 2024-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-04 | 2024-06-02 | 2024-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-04 | 2024-06-02 | 2024-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-06 | 2024-06-02 | 2024-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 6/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-07 | 2024-06-02 | 2024-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-08 | 2024-06-02 | 2024-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/9 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-10 | 2024-06-09 | 2024-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-12 | 2024-06-09 | 2024-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-13 | 2024-06-09 | 2024-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-13 | 2024-06-09 | 2024-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-13 | 2024-06-09 | 2024-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-13 | 2024-06-09 | 2024-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-20 | 2024-06-16 | 2024-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-21 | 2024-06-16 | 2024-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-06-22 | 2024-06-16 | 2024-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/11 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-07-01 | 2024-06-30 | 2024-07-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-07-08 | 2024-07-07 | 2024-07-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/12 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-07-11 | 2024-07-07 | 2024-07-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-07-12 | 2024-07-07 | 2024-07-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/11 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-07-13 | 2024-07-07 | 2024-07-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-07-15 | 2024-07-14 | 2024-07-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-07-20 | 2024-07-14 | 2024-07-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-07-20 | 2024-07-14 | 2024-07-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-07-20 | 2024-07-14 | 2024-07-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-07-22 | 2024-07-21 | 2024-07-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-07-28 | 2024-07-28 | 2024-07-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-07-28 | 2024-07-28 | 2024-07-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/9 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-07-30 | 2024-07-28 | 2024-07-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/9 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-05 | 2024-08-04 | 2024-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-08 | 2024-08-04 | 2024-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/11 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-10 | 2024-08-04 | 2024-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-12 | 2024-08-11 | 2024-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/12 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-12 | 2024-08-11 | 2024-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 23/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-16 | 2024-08-11 | 2024-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/9 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-23 | 2024-08-18 | 2024-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 23/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-23 | 2024-08-18 | 2024-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-24 | 2024-08-18 | 2024-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-24 | 2024-08-18 | 2024-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-24 | 2024-08-18 | 2024-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-24 | 2024-08-18 | 2024-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-24 | 2024-08-18 | 2024-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-24 | 2024-08-18 | 2024-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-24 | 2024-08-18 | 2024-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-24 | 2024-08-18 | 2024-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 45/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-24 | 2024-08-18 | 2024-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 50/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-29 | 2024-08-25 | 2024-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-08-30 | 2024-08-25 | 2024-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-01 | 2024-09-01 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-01 | 2024-09-01 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-01 | 2024-09-01 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-08 | 2024-09-08 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-08 | 2024-09-08 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 23/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-08 | 2024-09-08 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-09 | 2024-09-08 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/10 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-09 | 2024-09-08 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 41/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-09 | 2024-09-08 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 45/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-09 | 2024-09-08 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 46/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-11 | 2024-09-08 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 23/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-16 | 2024-09-15 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-16 | 2024-09-15 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/10 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-19 | 2024-09-15 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-19 | 2024-09-15 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-19 | 2024-09-15 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/9 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-19 | 2024-09-15 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 41/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-20 | 2024-09-15 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-20 | 2024-09-15 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-22 | 2024-09-22 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 25/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-22 | 2024-09-22 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-23 | 2024-09-22 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-25 | 2024-09-22 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-25 | 2024-09-22 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 46/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-26 | 2024-09-22 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 23/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-26 | 2024-09-22 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-26 | 2024-09-22 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-27 | 2024-09-22 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-09-27 | 2024-09-22 | 2024-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-01 | 2024-09-29 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-01 | 2024-09-29 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-01 | 2024-09-29 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 25/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-01 | 2024-09-29 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-03 | 2024-09-29 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-03 | 2024-09-29 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-04 | 2024-09-29 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 25/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-04 | 2024-09-29 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-04 | 2024-09-29 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-04 | 2024-09-29 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-04 | 2024-09-29 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/9 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-04 | 2024-09-29 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-08 | 2024-10-06 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-08 | 2024-10-06 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-08 | 2024-10-06 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-10 | 2024-10-06 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-10 | 2024-10-06 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-10 | 2024-10-06 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-10 | 2024-10-06 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-10 | 2024-10-06 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-12 | 2024-10-06 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-12 | 2024-10-06 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-12 | 2024-10-06 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-13 | 2024-10-13 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-13 | 2024-10-13 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/10 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-13 | 2024-10-13 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-13 | 2024-10-13 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/11 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-13 | 2024-10-13 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-13 | 2024-10-13 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/9 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-14 | 2024-10-13 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/9 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-15 | 2024-10-13 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-16 | 2024-10-13 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-16 | 2024-10-13 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-17 | 2024-10-13 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 28/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-17 | 2024-10-13 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/9 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-17 | 2024-10-13 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/10 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-17 | 2024-10-13 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-17 | 2024-10-13 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-17 | 2024-10-13 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-17 | 2024-10-13 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8B/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-19 | 2024-10-13 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/10 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-20 | 2024-10-20 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-21 | 2024-10-20 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-22 | 2024-10-20 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-22 | 2024-10-20 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-24 | 2024-10-20 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-24 | 2024-10-20 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-24 | 2024-10-20 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-24 | 2024-10-20 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-24 | 2024-10-20 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-24 | 2024-10-20 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/9 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-24 | 2024-10-20 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-24 | 2024-10-20 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/9 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-24 | 2024-10-20 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-24 | 2024-10-20 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/10 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-24 | 2024-10-20 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/11 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-25 | 2024-10-20 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-25 | 2024-10-20 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-10-25 | 2024-10-20 | 2024-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-01 | 2024-10-27 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/12 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-01 | 2024-10-27 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-03 | 2024-11-03 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-03 | 2024-11-03 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-03 | 2024-11-03 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-03 | 2024-11-03 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-03 | 2024-11-03 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-03 | 2024-11-03 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-03 | 2024-11-03 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/9 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-03 | 2024-11-03 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8B/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-03 | 2024-11-03 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8B/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-05 | 2024-11-03 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-06 | 2024-11-03 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-06 | 2024-11-03 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-06 | 2024-11-03 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-06 | 2024-11-03 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-06 | 2024-11-03 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-08 | 2024-11-03 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 32/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-09 | 2024-11-03 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 10/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-10 | 2024-11-10 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-10 | 2024-11-10 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-10 | 2024-11-10 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-10 | 2024-11-10 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-10 | 2024-11-10 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-10 | 2024-11-10 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 41/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-12 | 2024-11-10 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-14 | 2024-11-10 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-14 | 2024-11-10 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-14 | 2024-11-10 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 6/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-14 | 2024-11-10 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8B/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-16 | 2024-11-10 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 54/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-17 | 2024-11-17 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-18 | 2024-11-17 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-18 | 2024-11-17 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/11 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-18 | 2024-11-17 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 21/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-18 | 2024-11-17 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-18 | 2024-11-17 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-20 | 2024-11-17 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-20 | 2024-11-17 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 54/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-20 | 2024-11-17 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-20 | 2024-11-17 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8A/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-22 | 2024-11-17 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 10/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-22 | 2024-11-17 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-22 | 2024-11-17 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-22 | 2024-11-17 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-22 | 2024-11-17 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-22 | 2024-11-17 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-22 | 2024-11-17 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-22 | 2024-11-17 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-22 | 2024-11-17 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-22 | 2024-11-17 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-22 | 2024-11-17 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-22 | 2024-11-17 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8B/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-24 | 2024-11-24 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/9 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-24 | 2024-11-24 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-24 | 2024-11-24 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 64/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-25 | 2024-11-24 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-26 | 2024-11-24 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-28 | 2024-11-24 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-28 | 2024-11-24 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-29 | 2024-11-24 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-29 | 2024-11-24 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 26/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-29 | 2024-11-24 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/12 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-30 | 2024-11-24 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-30 | 2024-11-24 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 41/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-11-30 | 2024-11-24 | 2024-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-01 | 2024-12-01 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-01 | 2024-12-01 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/10 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-02 | 2024-12-01 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 55/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-03 | 2024-12-01 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-03 | 2024-12-01 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 5/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-03 | 2024-12-01 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-03 | 2024-12-01 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-03 | 2024-12-01 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-04 | 2024-12-01 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 3/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-04 | 2024-12-01 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-06 | 2024-12-01 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-06 | 2024-12-01 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-06 | 2024-12-01 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-06 | 2024-12-01 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-09 | 2024-12-08 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-09 | 2024-12-08 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-09 | 2024-12-08 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/9 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-09 | 2024-12-08 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 49/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-09 | 2024-12-08 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-09 | 2024-12-08 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-09 | 2024-12-08 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 6/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-09 | 2024-12-08 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-09 | 2024-12-08 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-10 | 2024-12-08 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-10 | 2024-12-08 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 45/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-10 | 2024-12-08 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 47/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-10 | 2024-12-08 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-10 | 2024-12-08 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-10 | 2024-12-08 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-10 | 2024-12-08 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 9/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-12 | 2024-12-08 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-12 | 2024-12-08 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-13 | 2024-12-08 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-15 | 2024-12-15 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 48/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-17 | 2024-12-15 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 15/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-17 | 2024-12-15 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/10 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-17 | 2024-12-15 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-18 | 2024-12-15 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-18 | 2024-12-15 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 46/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-18 | 2024-12-15 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/10 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-19 | 2024-12-15 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-20 | 2024-12-15 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-20 | 2024-12-15 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 6/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-21 | 2024-12-15 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 45/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-22 | 2024-12-22 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-23 | 2024-12-22 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-23 | 2024-12-22 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 54/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-24 | 2024-12-22 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-24 | 2024-12-22 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-24 | 2024-12-22 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-24 | 2024-12-22 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/9 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-26 | 2024-12-22 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8B/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-28 | 2024-12-22 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-28 | 2024-12-22 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 28/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-28 | 2024-12-22 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-28 | 2024-12-22 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 46/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-29 | 2024-12-29 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 5/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2024-12-31 | 2024-12-29 | 2024-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-01 | 2024-12-29 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-03 | 2024-12-29 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-03 | 2024-12-29 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-03 | 2024-12-29 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-03 | 2024-12-29 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-03 | 2024-12-29 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-03 | 2024-12-29 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-03 | 2024-12-29 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 64/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-04 | 2024-12-29 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-04 | 2024-12-29 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 48/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-04 | 2024-12-29 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 55/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-07 | 2025-01-05 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-07 | 2025-01-05 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-08 | 2025-01-05 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-09 | 2025-01-05 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-10 | 2025-01-05 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-10 | 2025-01-05 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/10 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-10 | 2025-01-05 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/10 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-10 | 2025-01-05 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-11 | 2025-01-05 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-12 | 2025-01-12 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-12 | 2025-01-12 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 51/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-12 | 2025-01-12 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-12 | 2025-01-12 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-14 | 2025-01-12 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 27/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-15 | 2025-01-12 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-15 | 2025-01-12 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 57/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-15 | 2025-01-12 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-16 | 2025-01-12 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/9 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-16 | 2025-01-12 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-17 | 2025-01-12 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-18 | 2025-01-12 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 24/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-18 | 2025-01-12 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-20 | 2025-01-19 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-21 | 2025-01-19 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-21 | 2025-01-19 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/10 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-21 | 2025-01-19 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 45/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-21 | 2025-01-19 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-21 | 2025-01-19 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-23 | 2025-01-19 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 0/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-23 | 2025-01-19 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 42/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-24 | 2025-01-19 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 0/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-24 | 2025-01-19 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-25 | 2025-01-19 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-25 | 2025-01-19 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 21/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-25 | 2025-01-19 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-25 | 2025-01-19 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-26 | 2025-01-26 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-28 | 2025-01-26 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-29 | 2025-01-26 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-29 | 2025-01-26 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-30 | 2025-01-26 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-01-30 | 2025-01-26 | 2025-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 29/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 0/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 22/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-02 | 2025-02-02 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 0/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-02 | 2025-02-02 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/9 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-02 | 2025-02-02 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/11 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-02 | 2025-02-02 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-02 | 2025-02-02 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 40/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-02 | 2025-02-02 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-02 | 2025-02-02 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 59/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-03 | 2025-02-02 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-06 | 2025-02-02 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 21/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-06 | 2025-02-02 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 25/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-06 | 2025-02-02 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 43/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-06 | 2025-02-02 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 64/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-07 | 2025-02-02 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-08 | 2025-02-02 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/9 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-09 | 2025-02-09 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 22A/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-09 | 2025-02-09 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-10 | 2025-02-09 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-10 | 2025-02-09 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-10 | 2025-02-09 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-10 | 2025-02-09 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-10 | 2025-02-09 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-11 | 2025-02-09 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/9 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-11 | 2025-02-09 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-12 | 2025-02-09 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-12 | 2025-02-09 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-14 | 2025-02-09 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-14 | 2025-02-09 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/9 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-16 | 2025-02-16 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-16 | 2025-02-16 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 41/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-16 | 2025-02-16 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-19 | 2025-02-16 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 11/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-19 | 2025-02-16 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-19 | 2025-02-16 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 58/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-19 | 2025-02-16 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 63/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-19 | 2025-02-16 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-20 | 2025-02-16 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-20 | 2025-02-16 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-20 | 2025-02-16 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-21 | 2025-02-16 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-21 | 2025-02-16 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-22 | 2025-02-16 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-26 | 2025-02-23 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 13/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-26 | 2025-02-23 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 21/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-26 | 2025-02-23 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-26 | 2025-02-23 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 50/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-27 | 2025-02-23 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-27 | 2025-02-23 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 60/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-27 | 2025-02-23 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-02-28 | 2025-02-23 | 2025-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 23/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/10 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 5/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 61/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 67/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/11 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-03 | 2025-03-02 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-04 | 2025-03-02 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-04 | 2025-03-02 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-08 | 2025-03-02 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-08 | 2025-03-02 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-09 | 2025-03-09 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 6/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-10 | 2025-03-09 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-10 | 2025-03-09 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-12 | 2025-03-09 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-13 | 2025-03-09 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-16 | 2025-03-16 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-16 | 2025-03-16 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 5/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-19 | 2025-03-16 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-20 | 2025-03-16 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 18/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-20 | 2025-03-16 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-20 | 2025-03-16 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 62/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-20 | 2025-03-16 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 64/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-20 | 2025-03-16 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 66/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-20 | 2025-03-16 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 7/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-21 | 2025-03-16 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-22 | 2025-03-16 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 35/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-22 | 2025-03-16 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 6/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-22 | 2025-03-16 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8B/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-24 | 2025-03-23 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/10 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-24 | 2025-03-23 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-24 | 2025-03-23 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-24 | 2025-03-23 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8B/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-25 | 2025-03-23 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-25 | 2025-03-23 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-25 | 2025-03-23 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 57/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-25 | 2025-03-23 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 66/0 A,B | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-25 | 2025-03-23 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 66/0 C,D | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-28 | 2025-03-23 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-28 | 2025-03-23 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8B/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-31 | 2025-03-30 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/11 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-31 | 2025-03-30 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 21/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-03-31 | 2025-03-30 | 2025-03-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 32/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 9/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-02 | 2025-03-30 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-03 | 2025-03-30 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-04 | 2025-03-30 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 16/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-04 | 2025-03-30 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 44/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-04 | 2025-03-30 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 68/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-05 | 2025-03-30 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-06 | 2025-04-06 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-08 | 2025-04-06 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8B/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-09 | 2025-04-06 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/10 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-11 | 2025-04-06 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 65/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-12 | 2025-04-06 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 0/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-12 | 2025-04-06 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 10/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-12 | 2025-04-06 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 31/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-12 | 2025-04-06 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-12 | 2025-04-06 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-12 | 2025-04-06 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-12 | 2025-04-06 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-14 | 2025-04-13 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8B/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-15 | 2025-04-13 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 25/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-16 | 2025-04-13 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 20/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-17 | 2025-04-13 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 10/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-17 | 2025-04-13 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-17 | 2025-04-13 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-17 | 2025-04-13 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 70/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-20 | 2025-04-20 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-22 | 2025-04-20 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 1/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-22 | 2025-04-20 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-22 | 2025-04-20 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-22 | 2025-04-20 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8A/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-23 | 2025-04-20 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/12 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-23 | 2025-04-20 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-23 | 2025-04-20 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-23 | 2025-04-20 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/9 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-25 | 2025-04-20 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 45/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-26 | 2025-04-20 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-27 | 2025-04-27 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/11 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-27 | 2025-04-27 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-29 | 2025-04-27 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-29 | 2025-04-27 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-29 | 2025-04-27 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-30 | 2025-04-27 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/10 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-30 | 2025-04-27 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 25/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-30 | 2025-04-27 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-04-30 | 2025-04-27 | 2025-04-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-04 | 2025-05-04 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-04 | 2025-05-04 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 4/9 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-05 | 2025-05-04 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 0/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-05 | 2025-05-04 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-05 | 2025-05-04 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 39/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-05 | 2025-05-04 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 8B/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-06 | 2025-05-04 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-06 | 2025-05-04 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 69/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-07 | 2025-05-04 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-07 | 2025-05-04 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-07 | 2025-05-04 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-07 | 2025-05-04 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-10 | 2025-05-04 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 23/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-11 | 2025-05-11 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-11 | 2025-05-11 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-11 | 2025-05-11 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 37/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-12 | 2025-05-11 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-12 | 2025-05-11 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/11 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-12 | 2025-05-11 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-13 | 2025-05-11 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/9 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-14 | 2025-05-11 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-14 | 2025-05-11 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/11 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-14 | 2025-05-11 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-14 | 2025-05-11 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 69A/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-15 | 2025-05-11 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 23/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-16 | 2025-05-11 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 15/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-16 | 2025-05-11 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/10 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-20 | 2025-05-18 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/9 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-20 | 2025-05-18 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-20 | 2025-05-18 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/10 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-20 | 2025-05-18 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-22 | 2025-05-18 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-23 | 2025-05-18 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 0/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-23 | 2025-05-18 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 23/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-23 | 2025-05-18 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/4 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-25 | 2025-05-25 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 0/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-25 | 2025-05-25 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 30/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-25 | 2025-05-25 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/10 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-26 | 2025-05-25 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-27 | 2025-05-25 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 51/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-28 | 2025-05-25 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 23/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-28 | 2025-05-25 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-05-30 | 2025-05-25 | 2025-05-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-01 | 2025-06-01 | 2025-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 14/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-02 | 2025-06-01 | 2025-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 33/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-02 | 2025-06-01 | 2025-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-04 | 2025-06-01 | 2025-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 0/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-04 | 2025-06-01 | 2025-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 23/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-04 | 2025-06-01 | 2025-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 40/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-08 | 2025-06-08 | 2025-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 50/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-10 | 2025-06-08 | 2025-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 45/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-10 | 2025-06-08 | 2025-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-12 | 2025-06-08 | 2025-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 22/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-12 | 2025-06-08 | 2025-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 3/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-12 | 2025-06-08 | 2025-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 34/5 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-15 | 2025-06-15 | 2025-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 48/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-20 | 2025-06-15 | 2025-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-21 | 2025-06-15 | 2025-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 21/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-24 | 2025-06-22 | 2025-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-24 | 2025-06-22 | 2025-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 28/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-27 | 2025-06-22 | 2025-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 21/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-06-28 | 2025-06-22 | 2025-06-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-07-01 | 2025-06-29 | 2025-07-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 21/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-07-01 | 2025-06-29 | 2025-07-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 25/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-07-05 | 2025-06-29 | 2025-07-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 44/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-07-08 | 2025-07-06 | 2025-07-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 28/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-07-09 | 2025-07-06 | 2025-07-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 13/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-07-20 | 2025-07-20 | 2025-07-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 41/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-07-26 | 2025-07-20 | 2025-07-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 24/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-07-27 | 2025-07-27 | 2025-07-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-01 | 2025-07-27 | 2025-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 36/12 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-02 | 2025-07-27 | 2025-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 65/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-04 | 2025-08-03 | 2025-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 18/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-06 | 2025-08-03 | 2025-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 29/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-09 | 2025-08-03 | 2025-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 1/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-10 | 2025-08-10 | 2025-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 43/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-12 | 2025-08-10 | 2025-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 12/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-14 | 2025-08-10 | 2025-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 46/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-16 | 2025-08-10 | 2025-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 16/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-18 | 2025-08-17 | 2025-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 54/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-18 | 2025-08-17 | 2025-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/8 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-24 | 2025-08-24 | 2025-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 11/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-28 | 2025-08-24 | 2025-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 25/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-31 | 2025-08-31 | 2025-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 19/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-08-31 | 2025-08-31 | 2025-08-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 64/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-03 | 2025-08-31 | 2025-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-05 | 2025-08-31 | 2025-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-07 | 2025-09-07 | 2025-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 47/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-11 | 2025-09-07 | 2025-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-15 | 2025-09-14 | 2025-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 17/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-15 | 2025-09-14 | 2025-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 26/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-15 | 2025-09-14 | 2025-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 48/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-18 | 2025-09-14 | 2025-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-22 | 2025-09-21 | 2025-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 27/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-23 | 2025-09-21 | 2025-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 37/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-23 | 2025-09-21 | 2025-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 42/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-24 | 2025-09-21 | 2025-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/6 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-24 | 2025-09-21 | 2025-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 64/3 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-25 | 2025-09-21 | 2025-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 46/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-25 | 2025-09-21 | 2025-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 50/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-25 | 2025-09-21 | 2025-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 54/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-25 | 2025-09-21 | 2025-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 61/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-09-26 | 2025-09-21 | 2025-09-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-10-01 | 2025-09-28 | 2025-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 63/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-10-03 | 2025-09-28 | 2025-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 0/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-10-07 | 2025-10-05 | 2025-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 38/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-10-08 | 2025-10-05 | 2025-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 54/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-10-09 | 2025-10-05 | 2025-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 45/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-10-23 | 2025-10-19 | 2025-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 55/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-10-26 | 2025-10-26 | 2025-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-10-31 | 2025-10-26 | 2025-10-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 2/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-11-06 | 2025-11-02 | 2025-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 49/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-11-06 | 2025-11-02 | 2025-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 64/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-11-08 | 2025-11-02 | 2025-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 60/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-11-09 | 2025-11-09 | 2025-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 55/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-11-10 | 2025-11-09 | 2025-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 62/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-11-15 | 2025-11-09 | 2025-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-11-15 | 2025-11-09 | 2025-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 69A/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-11-16 | 2025-11-16 | 2025-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 59/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-11-17 | 2025-11-16 | 2025-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 23/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-11-27 | 2025-11-23 | 2025-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 66/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 68/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-12-01 | 2025-11-30 | 2025-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 58/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-12-05 | 2025-11-30 | 2025-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 66/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-12-06 | 2025-11-30 | 2025-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 52/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-12-07 | 2025-12-07 | 2025-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 57/1 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-12-08 | 2025-12-07 | 2025-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 53A/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-12-15 | 2025-12-14 | 2025-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 22A/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-12-20 | 2025-12-14 | 2025-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 70/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2025-12-22 | 2025-12-21 | 2025-12-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 57/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2026-01-20 | 2026-01-18 | 2026-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 64/2 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2026-01-20 | 2026-01-18 | 2026-01-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 69/0 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2026-02-09 | 2026-02-08 | 2026-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 56/7 | 1
TA 416 | TA 416 | ta416 |  | filename | 2026-05-17 | 2026-02-09 | 2026-02-08 | 2026-02-01 | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | detail | detail_date | 67/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-01-07 | 2024-01-07 | 2024-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/14 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-01-09 | 2024-01-07 | 2024-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 54/4 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-06-09 | 2024-06-09 | 2024-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 42/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-06-10 | 2024-06-09 | 2024-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 42/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-06-29 | 2024-06-23 | 2024-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 54/4 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-06-29 | 2024-06-23 | 2024-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-07-01 | 2024-06-30 | 2024-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 40/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-07-02 | 2024-06-30 | 2024-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-07-03 | 2024-06-30 | 2024-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 41/3 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-07-07 | 2024-07-07 | 2024-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 41/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-07-10 | 2024-07-07 | 2024-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 40/5 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-07-14 | 2024-07-14 | 2024-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 40/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-07-18 | 2024-07-14 | 2024-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/3 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-07-18 | 2024-07-14 | 2024-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/4 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-07-20 | 2024-07-14 | 2024-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 40/3 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-07-24 | 2024-07-21 | 2024-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 54/3 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-07-27 | 2024-07-21 | 2024-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 41/4 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-07-29 | 2024-07-28 | 2024-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/3 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-08-03 | 2024-07-28 | 2024-08-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 41/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-08-07 | 2024-08-04 | 2024-08-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/6 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-08-09 | 2024-08-04 | 2024-08-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/7 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-08-14 | 2024-08-11 | 2024-08-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 40/4 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-08-25 | 2024-08-25 | 2024-08-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/8 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-09-02 | 2024-09-01 | 2024-09-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 34/3 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-09-02 | 2024-09-01 | 2024-09-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 34/4 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-09-02 | 2024-09-01 | 2024-09-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/11 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-09-05 | 2024-09-01 | 2024-09-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 34/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-09-12 | 2024-09-08 | 2024-09-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 52/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-09-20 | 2024-09-15 | 2024-09-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/9 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-09-22 | 2024-09-22 | 2024-09-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/12 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-09-24 | 2024-09-22 | 2024-09-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/11 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-09-24 | 2024-09-22 | 2024-09-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/14 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-09-27 | 2024-09-22 | 2024-09-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/10 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-09-29 | 2024-09-29 | 2024-09-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/9 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-10-08 | 2024-10-06 | 2024-10-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/8 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-10-09 | 2024-10-06 | 2024-10-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 34/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-10-19 | 2024-10-13 | 2024-10-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 34/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-10-27 | 2024-10-27 | 2024-10-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/7 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-10-28 | 2024-10-27 | 2024-10-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/12 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-10-30 | 2024-10-27 | 2024-10-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/7 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-11-05 | 2024-11-03 | 2024-11-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/06 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-11-08 | 2024-11-03 | 2024-11-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/8 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-11-13 | 2024-11-10 | 2024-11-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 34/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-11-14 | 2024-11-10 | 2024-11-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 34/3 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-11-15 | 2024-11-10 | 2024-11-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/4 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-11-15 | 2024-11-10 | 2024-11-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/5 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-11-19 | 2024-11-17 | 2024-11-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/4 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-11-19 | 2024-11-17 | 2024-11-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 41/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-11-24 | 2024-11-24 | 2024-11-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 43/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-11-26 | 2024-11-24 | 2024-11-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 40/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-02 | 2024-12-01 | 2024-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 40/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-03 | 2024-12-01 | 2024-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 42/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-04 | 2024-12-01 | 2024-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 45/02 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-06 | 2024-12-01 | 2024-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 41/3 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-09 | 2024-12-08 | 2024-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 45/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-10 | 2024-12-08 | 2024-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 45/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-11 | 2024-12-08 | 2024-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-12 | 2024-12-08 | 2024-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 41/4 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-12 | 2024-12-08 | 2024-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 42/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-19 | 2024-12-15 | 2024-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/11 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-19 | 2024-12-15 | 2024-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/7 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-22 | 2024-12-22 | 2024-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-29 | 2024-12-29 | 2024-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/10 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2024-12-30 | 2024-12-29 | 2024-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 40/4 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-01 | 2024-12-29 | 2025-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-03 | 2024-12-29 | 2025-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/15 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-10 | 2025-01-05 | 2025-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/5 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-13 | 2025-01-12 | 2025-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/8 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-16 | 2025-01-12 | 2025-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/4 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-16 | 2025-01-12 | 2025-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-16 | 2025-01-12 | 2025-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 57/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-17 | 2025-01-12 | 2025-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 42/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-23 | 2025-01-19 | 2025-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-24 | 2025-01-19 | 2025-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 34/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-24 | 2025-01-19 | 2025-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/3 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-25 | 2025-01-19 | 2025-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-28 | 2025-01-26 | 2025-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-30 | 2025-01-26 | 2025-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 40/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-31 | 2025-01-26 | 2025-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 32/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-01-31 | 2025-01-26 | 2025-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/8 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-02-06 | 2025-02-02 | 2025-02-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 41/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-02-12 | 2025-02-09 | 2025-02-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 41/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-02-12 | 2025-02-09 | 2025-02-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 54/3 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-02-12 | 2025-02-09 | 2025-02-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/4 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-02-15 | 2025-02-09 | 2025-02-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 37/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-02-15 | 2025-02-09 | 2025-02-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 37/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-02-21 | 2025-02-16 | 2025-02-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 41/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-02-23 | 2025-02-23 | 2025-02-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 48A/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-02-24 | 2025-02-23 | 2025-02-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 38/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-02-26 | 2025-02-23 | 2025-02-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 43/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-02-27 | 2025-02-23 | 2025-02-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 36/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 37/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 60/4 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-03-03 | 2025-03-02 | 2025-03-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-03-06 | 2025-03-02 | 2025-03-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/9 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-03-10 | 2025-03-09 | 2025-03-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 38/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-03-12 | 2025-03-09 | 2025-03-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/7 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-03-13 | 2025-03-09 | 2025-03-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 47/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-03-13 | 2025-03-09 | 2025-03-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 54/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-03-18 | 2025-03-16 | 2025-03-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 45/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-03-18 | 2025-03-16 | 2025-03-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 45/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-03-20 | 2025-03-16 | 2025-03-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 61/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-03-28 | 2025-03-23 | 2025-03-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 45/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-03-28 | 2025-03-23 | 2025-03-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 54/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-02 | 2025-03-30 | 2025-04-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 40/3 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-02 | 2025-03-30 | 2025-04-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/13 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-05 | 2025-03-30 | 2025-04-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 42/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-08 | 2025-04-06 | 2025-04-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 56/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-11 | 2025-04-06 | 2025-04-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/5 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-11 | 2025-04-06 | 2025-04-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 60/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-12 | 2025-04-06 | 2025-04-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/4 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-13 | 2025-04-13 | 2025-04-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 45/3 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-15 | 2025-04-13 | 2025-04-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/12 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-16 | 2025-04-13 | 2025-04-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 43/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-17 | 2025-04-13 | 2025-04-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 60/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-18 | 2025-04-13 | 2025-04-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-22 | 2025-04-20 | 2025-04-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 34/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-27 | 2025-04-27 | 2025-04-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/15 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-04-29 | 2025-04-27 | 2025-04-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 37/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-02 | 2025-04-27 | 2025-05-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 59/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-05 | 2025-05-04 | 2025-05-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-08 | 2025-05-04 | 2025-05-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-10 | 2025-05-04 | 2025-05-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 52/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-11 | 2025-05-11 | 2025-05-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/11 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-11 | 2025-05-11 | 2025-05-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-11 | 2025-05-11 | 2025-05-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/5 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-11 | 2025-05-11 | 2025-05-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 48/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-14 | 2025-05-11 | 2025-05-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 48/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-22 | 2025-05-18 | 2025-05-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 34/4 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-25 | 2025-05-25 | 2025-05-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 41/5 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-26 | 2025-05-25 | 2025-05-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-29 | 2025-05-25 | 2025-05-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 40/5 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-05-30 | 2025-05-25 | 2025-05-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/3 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-02 | 2025-06-01 | 2025-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-02 | 2025-06-01 | 2025-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/5 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-02 | 2025-06-01 | 2025-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/9 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-03 | 2025-06-01 | 2025-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/7 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-03 | 2025-06-01 | 2025-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/10 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-06 | 2025-06-01 | 2025-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-09 | 2025-06-08 | 2025-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/8 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-09 | 2025-06-08 | 2025-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 36/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-10 | 2025-06-08 | 2025-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/4 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-12 | 2025-06-08 | 2025-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/3 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-12 | 2025-06-08 | 2025-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/9 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-12 | 2025-06-08 | 2025-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 43/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-14 | 2025-06-08 | 2025-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/6 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-16 | 2025-06-15 | 2025-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 62/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-18 | 2025-06-15 | 2025-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 39/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-18 | 2025-06-15 | 2025-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 44/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-19 | 2025-06-15 | 2025-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 36/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-23 | 2025-06-22 | 2025-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 57/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-24 | 2025-06-22 | 2025-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/3 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-24 | 2025-06-22 | 2025-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/6 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-25 | 2025-06-22 | 2025-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 44/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-25 | 2025-06-22 | 2025-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-27 | 2025-06-22 | 2025-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/10 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-28 | 2025-06-22 | 2025-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/11 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-29 | 2025-06-29 | 2025-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-29 | 2025-06-29 | 2025-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 57/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-06-30 | 2025-06-29 | 2025-06-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 48/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-03 | 2025-06-29 | 2025-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 37/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-03 | 2025-06-29 | 2025-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 38/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-03 | 2025-06-29 | 2025-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 40/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-03 | 2025-06-29 | 2025-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 47/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-03 | 2025-06-29 | 2025-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 58/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-04 | 2025-06-29 | 2025-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 53/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-04 | 2025-06-29 | 2025-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 60/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-10 | 2025-07-06 | 2025-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 43/3 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-14 | 2025-07-13 | 2025-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 37/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-15 | 2025-07-13 | 2025-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 38/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-15 | 2025-07-13 | 2025-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 57/3 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-21 | 2025-07-20 | 2025-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-21 | 2025-07-20 | 2025-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/9 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-22 | 2025-07-20 | 2025-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/5 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-07-24 | 2025-07-20 | 2025-07-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 41/5 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-08-01 | 2025-07-27 | 2025-08-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 56/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-08-02 | 2025-07-27 | 2025-08-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 56/3 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-08-06 | 2025-08-03 | 2025-08-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 36/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-08-07 | 2025-08-03 | 2025-08-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 35/10 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-08-07 | 2025-08-03 | 2025-08-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 48A/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-08-09 | 2025-08-03 | 2025-08-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/13 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-08-16 | 2025-08-10 | 2025-08-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 48/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-08-18 | 2025-08-17 | 2025-08-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 43/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-08-19 | 2025-08-17 | 2025-08-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 52/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-08-22 | 2025-08-17 | 2025-08-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/3 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-08-23 | 2025-08-17 | 2025-08-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 54/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-08-26 | 2025-08-24 | 2025-08-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 60/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-08-31 | 2025-08-31 | 2025-08-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/3 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-09-01 | 2025-08-31 | 2025-09-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 62/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-09-03 | 2025-08-31 | 2025-09-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/12 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-09-05 | 2025-08-31 | 2025-09-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 56/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-09-09 | 2025-09-07 | 2025-09-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 45/3 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-09-09 | 2025-09-07 | 2025-09-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 48/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-09-12 | 2025-09-07 | 2025-09-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-09-14 | 2025-09-14 | 2025-09-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 61/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-09-16 | 2025-09-14 | 2025-09-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 53/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-09-22 | 2025-09-21 | 2025-09-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-09-25 | 2025-09-21 | 2025-09-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 44/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-09-28 | 2025-09-28 | 2025-09-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 54/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-09-29 | 2025-09-28 | 2025-09-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 54/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-10-04 | 2025-09-28 | 2025-10-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 32/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-10-16 | 2025-10-12 | 2025-10-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-10-16 | 2025-10-12 | 2025-10-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 39/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-10-18 | 2025-10-12 | 2025-10-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 60/4 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-10-29 | 2025-10-26 | 2025-10-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/10 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-11-02 | 2025-11-02 | 2025-11-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/6 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-11-04 | 2025-11-02 | 2025-11-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/6 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-11-04 | 2025-11-02 | 2025-11-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/5 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-11-06 | 2025-11-02 | 2025-11-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 43/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-11-11 | 2025-11-09 | 2025-11-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 48/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-11-12 | 2025-11-09 | 2025-11-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 33/4 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-11-12 | 2025-11-09 | 2025-11-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 51/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-11-13 | 2025-11-09 | 2025-11-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 50/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-11-21 | 2025-11-16 | 2025-11-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 47/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-11-23 | 2025-11-23 | 2025-11-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 44/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-11-24 | 2025-11-23 | 2025-11-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 48A/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 60/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-01 | 2025-11-30 | 2025-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 47/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-03 | 2025-11-30 | 2025-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 49/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-04 | 2025-11-30 | 2025-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 46/11 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-07 | 2025-12-07 | 2025-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 56/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-10 | 2025-12-07 | 2025-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 48A/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-10 | 2025-12-07 | 2025-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 52/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-12 | 2025-12-07 | 2025-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 59/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-13 | 2025-12-07 | 2025-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 57/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-15 | 2025-12-14 | 2025-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 56/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-16 | 2025-12-14 | 2025-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 60/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-17 | 2025-12-14 | 2025-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 52/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-18 | 2025-12-14 | 2025-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 60/3 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-20 | 2025-12-14 | 2025-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 56/3 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-23 | 2025-12-21 | 2025-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 48A/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-26 | 2025-12-21 | 2025-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 57/1 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-26 | 2025-12-21 | 2025-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 58/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2025-12-31 | 2025-12-28 | 2025-12-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 48A/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-01-03 | 2025-12-28 | 2026-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 63/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-01-07 | 2026-01-04 | 2026-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 59/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-01-08 | 2026-01-04 | 2026-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/6 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-01-08 | 2026-01-04 | 2026-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 57/3 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-01-16 | 2026-01-11 | 2026-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 60/3 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-01-20 | 2026-01-18 | 2026-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 55/5 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-01-22 | 2026-01-18 | 2026-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 54/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-01-28 | 2026-01-25 | 2026-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 49/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-01-29 | 2026-01-25 | 2026-01-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 57/2 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-02-04 | 2026-02-01 | 2026-02-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 50/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-02-05 | 2026-02-01 | 2026-02-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 51/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-02-05 | 2026-02-01 | 2026-02-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 63/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-02-11 | 2026-02-08 | 2026-02-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 38/0 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-02-20 | 2026-02-15 | 2026-02-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 43/3 | 1
TA 418 | TA 418 | ta418 |  | filename | 2026-05-21 | 2026-02-24 | 2026-02-22 | 2026-02-01 | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | detail | detail_date | 38/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-05-21 | 2024-05-19 | 2024-05-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 19/3 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-05-21 | 2024-05-19 | 2024-05-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 19/4 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-05-29 | 2024-05-26 | 2024-05-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 19/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-05-30 | 2024-05-26 | 2024-05-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 17/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-05-30 | 2024-05-26 | 2024-05-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 17/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-06-04 | 2024-06-02 | 2024-06-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 19/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-06-14 | 2024-06-09 | 2024-06-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 20/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-06-16 | 2024-06-16 | 2024-06-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 20/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-06-21 | 2024-06-16 | 2024-06-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 11/4 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-06-24 | 2024-06-23 | 2024-06-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 22/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-06-25 | 2024-06-23 | 2024-06-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 11/3 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-06-27 | 2024-06-23 | 2024-06-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 23/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-06-29 | 2024-06-23 | 2024-06-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 22/3 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-01 | 2024-06-30 | 2024-07-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 12/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-05 | 2024-06-30 | 2024-07-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 3/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-06 | 2024-06-30 | 2024-07-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 6/10 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-09 | 2024-07-07 | 2024-07-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 23/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-10 | 2024-07-07 | 2024-07-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 23/3 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-10 | 2024-07-07 | 2024-07-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 6/9 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-12 | 2024-07-07 | 2024-07-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 6/8 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-13 | 2024-07-07 | 2024-07-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 26/3 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-15 | 2024-07-14 | 2024-07-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 26/4 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-15 | 2024-07-14 | 2024-07-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 6/12 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-20 | 2024-07-14 | 2024-07-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 6/3 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-21 | 2024-07-21 | 2024-07-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 3/3 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-23 | 2024-07-21 | 2024-07-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 24/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-23 | 2024-07-21 | 2024-07-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 6/6 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-25 | 2024-07-21 | 2024-07-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 3/5 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-27 | 2024-07-21 | 2024-07-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 24/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-28 | 2024-07-28 | 2024-07-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 6/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-31 | 2024-07-28 | 2024-07-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 26/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-31 | 2024-07-28 | 2024-07-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 3/4 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-07-31 | 2024-07-28 | 2024-07-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 6/5 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-08-04 | 2024-08-04 | 2024-08-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 4/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-08-04 | 2024-08-04 | 2024-08-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 5/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-08-11 | 2024-08-11 | 2024-08-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 5/3 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-08-11 | 2024-08-11 | 2024-08-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 6/11 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-08-27 | 2024-08-25 | 2024-08-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 27/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-08-29 | 2024-08-25 | 2024-08-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0D/3 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-08-30 | 2024-08-25 | 2024-08-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 5/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-02 | 2024-09-01 | 2024-09-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 27/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-04 | 2024-09-01 | 2024-09-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 4/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-05 | 2024-09-01 | 2024-09-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0D/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-09 | 2024-09-08 | 2024-09-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0E/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-09 | 2024-09-08 | 2024-09-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 12/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-11 | 2024-09-08 | 2024-09-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0B/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-15 | 2024-09-15 | 2024-09-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0D/5 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-18 | 2024-09-15 | 2024-09-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0B/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-18 | 2024-09-15 | 2024-09-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0E/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-18 | 2024-09-15 | 2024-09-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 6/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-18 | 2024-09-15 | 2024-09-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 7/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-22 | 2024-09-22 | 2024-09-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 12A/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-23 | 2024-09-22 | 2024-09-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0D/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-23 | 2024-09-22 | 2024-09-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 5/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-25 | 2024-09-22 | 2024-09-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0D/4 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-29 | 2024-09-29 | 2024-09-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0D/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-30 | 2024-09-29 | 2024-09-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0B/3 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-09-30 | 2024-09-29 | 2024-09-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 23/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-06 | 2024-10-06 | 2024-10-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 28/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-07 | 2024-10-06 | 2024-10-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0C/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-07 | 2024-10-06 | 2024-10-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 5/4 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-07 | 2024-10-06 | 2024-10-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 6/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-08 | 2024-10-06 | 2024-10-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 26/5 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-09 | 2024-10-06 | 2024-10-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 6/4 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-10 | 2024-10-06 | 2024-10-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0E/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-11 | 2024-10-06 | 2024-10-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 27/3 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-14 | 2024-10-13 | 2024-10-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 26/6 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-14 | 2024-10-13 | 2024-10-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 27/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-17 | 2024-10-13 | 2024-10-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 20/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-17 | 2024-10-13 | 2024-10-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 24/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-19 | 2024-10-13 | 2024-10-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0C/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-19 | 2024-10-13 | 2024-10-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 11/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-19 | 2024-10-13 | 2024-10-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 19/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-20 | 2024-10-20 | 2024-10-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0B/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-25 | 2024-10-20 | 2024-10-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 18/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-10-28 | 2024-10-27 | 2024-10-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 12/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-11-08 | 2024-11-03 | 2024-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 6/7 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-11-13 | 2024-11-10 | 2024-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 36/6 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-11-13 | 2024-11-10 | 2024-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 36/7 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-11-15 | 2024-11-10 | 2024-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0F/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-11-15 | 2024-11-10 | 2024-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 24/3 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-11-19 | 2024-11-17 | 2024-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 7/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-11-20 | 2024-11-17 | 2024-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 17/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-11-26 | 2024-11-24 | 2024-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 3/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-11-27 | 2024-11-24 | 2024-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0G/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-12-02 | 2024-12-01 | 2024-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0A/0 (CT) | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-12-02 | 2024-12-01 | 2024-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 11/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-12-02 | 2024-12-01 | 2024-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 22/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-12-03 | 2024-12-01 | 2024-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 15A/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-12-05 | 2024-12-01 | 2024-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 16/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-12-08 | 2024-12-08 | 2024-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 28/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-12-11 | 2024-12-08 | 2024-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 31/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-12-11 | 2024-12-08 | 2024-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 31/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-12-12 | 2024-12-08 | 2024-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 15/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-12-12 | 2024-12-08 | 2024-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 30/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-12-21 | 2024-12-15 | 2024-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0G/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-12-21 | 2024-12-15 | 2024-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 0H/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2024-12-23 | 2024-12-22 | 2024-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 1/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-01-02 | 2024-12-29 | 2025-01-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 10/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-01-10 | 2025-01-05 | 2025-01-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 36/8 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-01-15 | 2025-01-12 | 2025-01-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 22/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-01-16 | 2025-01-12 | 2025-01-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 62/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-01-18 | 2025-01-12 | 2025-01-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 36/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-01-25 | 2025-01-19 | 2025-01-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 36/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-01-28 | 2025-01-26 | 2025-01-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 36/4 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-01-29 | 2025-01-26 | 2025-01-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 38/5 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-01-29 | 2025-01-26 | 2025-01-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 38/7 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-02-06 | 2025-02-02 | 2025-02-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 38/8 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-02-08 | 2025-02-02 | 2025-02-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 38/10 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-02-11 | 2025-02-09 | 2025-02-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 62/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-02-14 | 2025-02-09 | 2025-02-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 38/6 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-02-18 | 2025-02-16 | 2025-02-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 62/5 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-02-20 | 2025-02-16 | 2025-02-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 38/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 62/4 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-03-23 | 2025-03-23 | 2025-03-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 38/11 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-03-23 | 2025-03-23 | 2025-03-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 38/9 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-03-23 | 2025-03-23 | 2025-03-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 40/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-03-24 | 2025-03-23 | 2025-03-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 62/3 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-03-25 | 2025-03-23 | 2025-03-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 34/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-03-27 | 2025-03-23 | 2025-03-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 39/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-03-27 | 2025-03-23 | 2025-03-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 40/3 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 40/4 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-02 | 2025-03-30 | 2025-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 20/3 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-06 | 2025-04-06 | 2025-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 40/9 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-07 | 2025-04-06 | 2025-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 40/6 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-09 | 2025-04-06 | 2025-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 40/7 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-09 | 2025-04-06 | 2025-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 46/4 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-12 | 2025-04-06 | 2025-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 40/5 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-15 | 2025-04-13 | 2025-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 40/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-19 | 2025-04-13 | 2025-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 41/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-23 | 2025-04-20 | 2025-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 41/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-23 | 2025-04-20 | 2025-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 41/7 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-25 | 2025-04-20 | 2025-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 41/5 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-28 | 2025-04-27 | 2025-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 41/8 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-29 | 2025-04-27 | 2025-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 83/7 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-04-29 | 2025-04-27 | 2025-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 84/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-05-03 | 2025-04-27 | 2025-05-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 83/6 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-05-04 | 2025-05-04 | 2025-05-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 41/4 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-05-06 | 2025-05-04 | 2025-05-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 41/3 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-05-12 | 2025-05-11 | 2025-05-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 25/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-05-12 | 2025-05-11 | 2025-05-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 3/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-05-15 | 2025-05-11 | 2025-05-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 26/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-05-19 | 2025-05-18 | 2025-05-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 36/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-05-21 | 2025-05-18 | 2025-05-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 11/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-05-29 | 2025-05-25 | 2025-05-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 35/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-06-01 | 2025-06-01 | 2025-06-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 2/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-06-04 | 2025-06-01 | 2025-06-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 34/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-06-05 | 2025-06-01 | 2025-06-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 83/5 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-06-09 | 2025-06-08 | 2025-06-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 29/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-06-11 | 2025-06-08 | 2025-06-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 78/3 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-06-14 | 2025-06-08 | 2025-06-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 30/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-06-20 | 2025-06-15 | 2025-06-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 84/4 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-06-22 | 2025-06-22 | 2025-06-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 21/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-07-08 | 2025-07-06 | 2025-07-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 9/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-07-15 | 2025-07-13 | 2025-07-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 8/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-07-24 | 2025-07-20 | 2025-07-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 41/6 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-08-01 | 2025-07-27 | 2025-08-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 46/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-08-30 | 2025-08-24 | 2025-08-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 83/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-09-05 | 2025-08-31 | 2025-09-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 46/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-09-11 | 2025-09-07 | 2025-09-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 46/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-09-15 | 2025-09-14 | 2025-09-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 46/3 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-09-16 | 2025-09-14 | 2025-09-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 78/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-09-21 | 2025-09-21 | 2025-09-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 45/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-09-24 | 2025-09-21 | 2025-09-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 76/3 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-09-26 | 2025-09-21 | 2025-09-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 31/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-10-01 | 2025-09-28 | 2025-10-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 78/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-10-05 | 2025-10-05 | 2025-10-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 83/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-10-20 | 2025-10-19 | 2025-10-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 43/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-10-27 | 2025-10-26 | 2025-10-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 63A/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-10-28 | 2025-10-26 | 2025-10-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 43/5 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-01 | 2025-10-26 | 2025-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 43/3 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-02 | 2025-11-02 | 2025-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 54/6 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-02 | 2025-11-02 | 2025-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 63/5 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-02 | 2025-11-02 | 2025-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 83/9 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-03 | 2025-11-02 | 2025-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 43/6 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-04 | 2025-11-02 | 2025-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 36/10 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-04 | 2025-11-02 | 2025-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 54/5 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-06 | 2025-11-02 | 2025-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 36/9 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-07 | 2025-11-02 | 2025-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 43/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-09 | 2025-11-09 | 2025-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 43/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-11 | 2025-11-09 | 2025-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 63/4 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-14 | 2025-11-09 | 2025-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 43/4 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-15 | 2025-11-09 | 2025-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 26/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-18 | 2025-11-16 | 2025-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 84/3 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-19 | 2025-11-16 | 2025-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 55/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-21 | 2025-11-16 | 2025-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 12A/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-23 | 2025-11-23 | 2025-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 83/8 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-25 | 2025-11-23 | 2025-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 54/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-27 | 2025-11-23 | 2025-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 55/6 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 33/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-02 | 2025-11-30 | 2025-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 54/3 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-03 | 2025-11-30 | 2025-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 54/4 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-04 | 2025-11-30 | 2025-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 63/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-05 | 2025-11-30 | 2025-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 55/5 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-06 | 2025-11-30 | 2025-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 64/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-07 | 2025-12-07 | 2025-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 84/5 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-08 | 2025-12-07 | 2025-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 78/4 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-10 | 2025-12-07 | 2025-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 54/7 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-10 | 2025-12-07 | 2025-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 63/6 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-10 | 2025-12-07 | 2025-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 84A/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-15 | 2025-12-14 | 2025-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 84/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-16 | 2025-12-14 | 2025-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 52/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-18 | 2025-12-14 | 2025-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 57/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-18 | 2025-12-14 | 2025-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 59/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-18 | 2025-12-14 | 2025-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 63/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-18 | 2025-12-14 | 2025-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 63B/6 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-18 | 2025-12-14 | 2025-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 64/5 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-18 | 2025-12-14 | 2025-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 64A/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-19 | 2025-12-14 | 2025-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 36/5 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-19 | 2025-12-14 | 2025-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 62/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-23 | 2025-12-21 | 2025-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 55/4 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-24 | 2025-12-21 | 2025-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 36/3 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-24 | 2025-12-21 | 2025-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 63/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-25 | 2025-12-21 | 2025-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 55/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-25 | 2025-12-21 | 2025-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 60/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2025-12-29 | 2025-12-28 | 2025-12-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 64/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-01-01 | 2025-12-28 | 2026-01-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 63B/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-01-03 | 2025-12-28 | 2026-01-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 78A/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-01-07 | 2026-01-04 | 2026-01-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 64/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-01-11 | 2026-01-11 | 2026-01-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 38/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-01-11 | 2026-01-11 | 2026-01-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 55/3 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-01-16 | 2026-01-11 | 2026-01-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 55/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-01-16 | 2026-01-11 | 2026-01-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 81/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-01-16 | 2026-01-11 | 2026-01-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 82/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-01-17 | 2026-01-11 | 2026-01-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 63B/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-01-18 | 2026-01-18 | 2026-01-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 14/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-01-20 | 2026-01-18 | 2026-01-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 77/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-01-28 | 2026-01-25 | 2026-01-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 38/3 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-02-04 | 2026-02-01 | 2026-02-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 33/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-02-04 | 2026-02-01 | 2026-02-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 42/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-02-12 | 2026-02-08 | 2026-02-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 40/8 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-02-26 | 2026-02-22 | 2026-02-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 54/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-03-16 | 2026-03-15 | 2026-03-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 78/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-03-20 | 2026-03-15 | 2026-03-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 13/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-03-22 | 2026-03-22 | 2026-03-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 73/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-03-25 | 2026-03-22 | 2026-03-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 32/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-03-25 | 2026-03-22 | 2026-03-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 76/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-03-25 | 2026-03-22 | 2026-03-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 84/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-01 | 2026-03-29 | 2026-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 38/4 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-01 | 2026-03-29 | 2026-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 40/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-01 | 2026-03-29 | 2026-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 80/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-05 | 2026-04-05 | 2026-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 64/3 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-05 | 2026-04-05 | 2026-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 64/4 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-07 | 2026-04-05 | 2026-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 93B/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-08 | 2026-04-05 | 2026-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 71/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-13 | 2026-04-12 | 2026-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 41/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-17 | 2026-04-12 | 2026-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 69/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-18 | 2026-04-12 | 2026-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 70/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-23 | 2026-04-19 | 2026-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 14/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-25 | 2026-04-19 | 2026-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 66/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-25 | 2026-04-19 | 2026-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 67/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-27 | 2026-04-26 | 2026-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 37/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-27 | 2026-04-26 | 2026-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 53/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-27 | 2026-04-26 | 2026-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 61/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-30 | 2026-04-26 | 2026-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 52/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-04-30 | 2026-04-26 | 2026-04-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 54/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-05-06 | 2026-05-03 | 2026-05-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 38/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-05-06 | 2026-05-03 | 2026-05-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 59/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-05-06 | 2026-05-03 | 2026-05-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 87/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-05-06 | 2026-05-03 | 2026-05-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 87/2 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-05-08 | 2026-05-03 | 2026-05-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 65/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-05-09 | 2026-05-03 | 2026-05-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 72/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-05-11 | 2026-05-10 | 2026-05-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 68/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-05-12 | 2026-05-10 | 2026-05-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 95A/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-05-13 | 2026-05-10 | 2026-05-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 76/1 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-05-16 | 2026-05-10 | 2026-05-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 66/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-05-16 | 2026-05-10 | 2026-05-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 75/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-05-17 | 2026-05-17 | 2026-05-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 76/0 | 1
TA 419 | TA 419 | ta419 |  | filename | 2026-05-18 | 2026-05-17 | 2026-05-17 | 2026-05-01 | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 96/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-01-02 | 2023-12-31 | 2024-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-02-06 | 2024-02-04 | 2024-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-03-05 | 2024-03-03 | 2024-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 34/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-03-05 | 2024-03-03 | 2024-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/15 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-05-03 | 2024-04-28 | 2024-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-05-06 | 2024-05-05 | 2024-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-05-09 | 2024-05-05 | 2024-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-05-23 | 2024-05-19 | 2024-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-05-25 | 2024-05-19 | 2024-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-05-25 | 2024-05-19 | 2024-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-05-25 | 2024-05-19 | 2024-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-05-31 | 2024-05-26 | 2024-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-03 | 2024-06-02 | 2024-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-07 | 2024-06-02 | 2024-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-11 | 2024-06-09 | 2024-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-13 | 2024-06-09 | 2024-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-15 | 2024-06-09 | 2024-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-17 | 2024-06-16 | 2024-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-19 | 2024-06-16 | 2024-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-20 | 2024-06-16 | 2024-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-21 | 2024-06-16 | 2024-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-22 | 2024-06-16 | 2024-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-23 | 2024-06-23 | 2024-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-23 | 2024-06-23 | 2024-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-24 | 2024-06-23 | 2024-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-24 | 2024-06-23 | 2024-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-25 | 2024-06-23 | 2024-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-25 | 2024-06-23 | 2024-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-25 | 2024-06-23 | 2024-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-26 | 2024-06-23 | 2024-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-27 | 2024-06-23 | 2024-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-27 | 2024-06-23 | 2024-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-28 | 2024-06-23 | 2024-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/11 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-06-28 | 2024-06-23 | 2024-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-01 | 2024-06-30 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-02 | 2024-06-30 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-03 | 2024-06-30 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-05 | 2024-06-30 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-06 | 2024-06-30 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-06 | 2024-06-30 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-06 | 2024-06-30 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-06 | 2024-06-30 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-07 | 2024-07-07 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-08 | 2024-07-07 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-09 | 2024-07-07 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-10 | 2024-07-07 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-10 | 2024-07-07 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-10 | 2024-07-07 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-11 | 2024-07-07 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-11 | 2024-07-07 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-12 | 2024-07-07 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-12 | 2024-07-07 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-12 | 2024-07-07 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-12 | 2024-07-07 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-12 | 2024-07-07 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-12 | 2024-07-07 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-13 | 2024-07-07 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-13 | 2024-07-07 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-13 | 2024-07-07 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-13 | 2024-07-07 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-13 | 2024-07-07 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-14 | 2024-07-14 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-17 | 2024-07-14 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-18 | 2024-07-14 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-19 | 2024-07-14 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-19 | 2024-07-14 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-20 | 2024-07-14 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-22 | 2024-07-21 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-24 | 2024-07-21 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-27 | 2024-07-21 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-28 | 2024-07-28 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-28 | 2024-07-28 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-28 | 2024-07-28 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-28 | 2024-07-28 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-30 | 2024-07-28 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-30 | 2024-07-28 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-31 | 2024-07-28 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-31 | 2024-07-28 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-31 | 2024-07-28 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-07-31 | 2024-07-28 | 2024-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-01 | 2024-07-28 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-02 | 2024-07-28 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-02 | 2024-07-28 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-03 | 2024-07-28 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-03 | 2024-07-28 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-05 | 2024-08-04 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-08 | 2024-08-04 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-08 | 2024-08-04 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-09 | 2024-08-04 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-09 | 2024-08-04 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-10 | 2024-08-04 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-11 | 2024-08-11 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-13 | 2024-08-11 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-14 | 2024-08-11 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/11 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-14 | 2024-08-11 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-16 | 2024-08-11 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-16 | 2024-08-11 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-19 | 2024-08-18 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-19 | 2024-08-18 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-19 | 2024-08-18 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-20 | 2024-08-18 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/11 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-20 | 2024-08-18 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-22 | 2024-08-18 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-23 | 2024-08-18 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-24 | 2024-08-18 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/10 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-24 | 2024-08-18 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-25 | 2024-08-25 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-25 | 2024-08-25 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-27 | 2024-08-25 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-27 | 2024-08-25 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-28 | 2024-08-25 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-29 | 2024-08-25 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-29 | 2024-08-25 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-31 | 2024-08-25 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-08-31 | 2024-08-25 | 2024-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-05 | 2024-09-01 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-09 | 2024-09-08 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-09 | 2024-09-08 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-10 | 2024-09-08 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-11 | 2024-09-08 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-11 | 2024-09-08 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-12 | 2024-09-08 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-13 | 2024-09-08 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-14 | 2024-09-08 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-14 | 2024-09-08 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-15 | 2024-09-15 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-15 | 2024-09-15 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-17 | 2024-09-15 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-19 | 2024-09-15 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-20 | 2024-09-15 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-21 | 2024-09-15 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-22 | 2024-09-22 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 19/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-23 | 2024-09-22 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-23 | 2024-09-22 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-24 | 2024-09-22 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/10 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-24 | 2024-09-22 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-24 | 2024-09-22 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-24 | 2024-09-22 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-26 | 2024-09-22 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-27 | 2024-09-22 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-28 | 2024-09-22 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-29 | 2024-09-29 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-29 | 2024-09-29 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-09-30 | 2024-09-29 | 2024-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-01 | 2024-09-29 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-01 | 2024-09-29 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-01 | 2024-09-29 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-03 | 2024-09-29 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-03 | 2024-09-29 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-04 | 2024-09-29 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-05 | 2024-09-29 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-05 | 2024-09-29 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-05 | 2024-09-29 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-05 | 2024-09-29 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-05 | 2024-09-29 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-09 | 2024-10-06 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-09 | 2024-10-06 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-10 | 2024-10-06 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 19/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-10 | 2024-10-06 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-12 | 2024-10-06 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-12 | 2024-10-06 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-14 | 2024-10-13 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 17/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-14 | 2024-10-13 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-16 | 2024-10-13 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-16 | 2024-10-13 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-17 | 2024-10-13 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-18 | 2024-10-13 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-18 | 2024-10-13 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-18 | 2024-10-13 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-18 | 2024-10-13 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 17/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-18 | 2024-10-13 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-19 | 2024-10-13 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-21 | 2024-10-20 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-22 | 2024-10-20 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-22 | 2024-10-20 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-23 | 2024-10-20 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-23 | 2024-10-20 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-23 | 2024-10-20 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-23 | 2024-10-20 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 41/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-24 | 2024-10-20 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-25 | 2024-10-20 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-27 | 2024-10-27 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/10 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-27 | 2024-10-27 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-10-29 | 2024-10-27 | 2024-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-01 | 2024-10-27 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-02 | 2024-10-27 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-02 | 2024-10-27 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-02 | 2024-10-27 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-04 | 2024-11-03 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 18/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-04 | 2024-11-03 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-05 | 2024-11-03 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-06 | 2024-11-03 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/10 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-07 | 2024-11-03 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-07 | 2024-11-03 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 19/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-07 | 2024-11-03 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-08 | 2024-11-03 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 18/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-08 | 2024-11-03 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-08 | 2024-11-03 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-09 | 2024-11-03 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-10 | 2024-11-10 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-11 | 2024-11-10 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-12 | 2024-11-10 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-13 | 2024-11-10 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-13 | 2024-11-10 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-14 | 2024-11-10 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-14 | 2024-11-10 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-15 | 2024-11-10 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-16 | 2024-11-10 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-16 | 2024-11-10 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 17/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-16 | 2024-11-10 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-18 | 2024-11-17 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-18 | 2024-11-17 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-18 | 2024-11-17 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-19 | 2024-11-17 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-19 | 2024-11-17 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 26/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-21 | 2024-11-17 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 23/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-22 | 2024-11-17 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-22 | 2024-11-17 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-23 | 2024-11-17 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-23 | 2024-11-17 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/10 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-23 | 2024-11-17 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-24 | 2024-11-24 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-24 | 2024-11-24 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-26 | 2024-11-24 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-26 | 2024-11-24 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-28 | 2024-11-24 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-28 | 2024-11-24 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 35/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-11-30 | 2024-11-24 | 2024-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-01 | 2024-12-01 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/10 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-01 | 2024-12-01 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-01 | 2024-12-01 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 18/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-02 | 2024-12-01 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-02 | 2024-12-01 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-02 | 2024-12-01 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 18/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-02 | 2024-12-01 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-03 | 2024-12-01 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-03 | 2024-12-01 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-03 | 2024-12-01 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-03 | 2024-12-01 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-04 | 2024-12-01 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-04 | 2024-12-01 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-07 | 2024-12-01 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-07 | 2024-12-01 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-08 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-08 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 35/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-08 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-09 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/11 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-09 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 18/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-09 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-09 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-11 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/11 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-11 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 18/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-11 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 19/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-11 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-12 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-12 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-12 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/11 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-13 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-13 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-14 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-14 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/10 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-14 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-14 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-14 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-14 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-14 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-14 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-14 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-14 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-14 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-14 | 2024-12-08 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-15 | 2024-12-15 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-15 | 2024-12-15 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-15 | 2024-12-15 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-15 | 2024-12-15 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-16 | 2024-12-15 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 19/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-17 | 2024-12-15 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-18 | 2024-12-15 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-18 | 2024-12-15 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-18 | 2024-12-15 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 41/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-19 | 2024-12-15 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 18/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-19 | 2024-12-15 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-19 | 2024-12-15 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-20 | 2024-12-15 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-20 | 2024-12-15 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-20 | 2024-12-15 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-22 | 2024-12-22 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-22 | 2024-12-22 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-22 | 2024-12-22 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-23 | 2024-12-22 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/10 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-23 | 2024-12-22 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 18/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-23 | 2024-12-22 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-24 | 2024-12-22 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-24 | 2024-12-22 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-24 | 2024-12-22 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 28/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-24 | 2024-12-22 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-24 | 2024-12-22 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-26 | 2024-12-22 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 18/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-26 | 2024-12-22 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 18/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-26 | 2024-12-22 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-26 | 2024-12-22 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-26 | 2024-12-22 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-27 | 2024-12-22 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 18/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-27 | 2024-12-22 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 19/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-28 | 2024-12-22 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-29 | 2024-12-29 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-29 | 2024-12-29 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2024-12-31 | 2024-12-29 | 2024-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-02 | 2024-12-29 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/10 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-03 | 2024-12-29 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-03 | 2024-12-29 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 17/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-03 | 2024-12-29 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-03 | 2024-12-29 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-03 | 2024-12-29 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-03 | 2024-12-29 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-04 | 2024-12-29 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-04 | 2024-12-29 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-04 | 2024-12-29 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-05 | 2025-01-05 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-05 | 2025-01-05 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-05 | 2025-01-05 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-05 | 2025-01-05 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-06 | 2025-01-05 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-06 | 2025-01-05 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 17/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-07 | 2025-01-05 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-07 | 2025-01-05 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-08 | 2025-01-05 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-08 | 2025-01-05 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-09 | 2025-01-05 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-09 | 2025-01-05 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 33/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-11 | 2025-01-05 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-11 | 2025-01-05 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-11 | 2025-01-05 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-11 | 2025-01-05 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-12 | 2025-01-12 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-12 | 2025-01-12 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-13 | 2025-01-12 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 17/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-13 | 2025-01-12 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 33/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-14 | 2025-01-12 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-15 | 2025-01-12 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-16 | 2025-01-12 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-16 | 2025-01-12 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-17 | 2025-01-12 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 33/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-17 | 2025-01-12 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-17 | 2025-01-12 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-18 | 2025-01-12 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-18 | 2025-01-12 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 14/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-18 | 2025-01-12 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-18 | 2025-01-12 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 17/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-19 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-19 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-19 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 19/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-19 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-19 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 33/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-20 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/10 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-20 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 17/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-20 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-21 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 17/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-21 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 18/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-21 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 19/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-21 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-22 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/10 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-22 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-22 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 32/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-22 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 32/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-23 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-23 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 19/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-23 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-24 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-24 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-24 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-25 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-25 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 24/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-25 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-25 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-25 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-25 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-25 | 2025-01-19 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/10 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-26 | 2025-01-26 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-27 | 2025-01-26 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 35/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-27 | 2025-01-26 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-27 | 2025-01-26 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-28 | 2025-01-26 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-28 | 2025-01-26 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-28 | 2025-01-26 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-29 | 2025-01-26 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-29 | 2025-01-26 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-29 | 2025-01-26 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-29 | 2025-01-26 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-30 | 2025-01-26 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-30 | 2025-01-26 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-30 | 2025-01-26 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 35/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-31 | 2025-01-26 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 14/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-01-31 | 2025-01-26 | 2025-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 19/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 32/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 32/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 32/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-02 | 2025-02-02 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 35/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-02 | 2025-02-02 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-02 | 2025-02-02 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-03 | 2025-02-02 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-03 | 2025-02-02 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-03 | 2025-02-02 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 35/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-03 | 2025-02-02 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-03 | 2025-02-02 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-03 | 2025-02-02 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-03 | 2025-02-02 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-04 | 2025-02-02 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-04 | 2025-02-02 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-04 | 2025-02-02 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-04 | 2025-02-02 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-04 | 2025-02-02 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-04 | 2025-02-02 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-04 | 2025-02-02 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-04 | 2025-02-02 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-05 | 2025-02-02 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-05 | 2025-02-02 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-05 | 2025-02-02 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 35/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-05 | 2025-02-02 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-05 | 2025-02-02 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-06 | 2025-02-02 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-07 | 2025-02-02 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-09 | 2025-02-09 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-09 | 2025-02-09 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-10 | 2025-02-09 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-10 | 2025-02-09 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-10 | 2025-02-09 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-11 | 2025-02-09 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-11 | 2025-02-09 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/11 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-12 | 2025-02-09 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-12 | 2025-02-09 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-13 | 2025-02-09 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-13 | 2025-02-09 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 33/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-13 | 2025-02-09 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 33/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-13 | 2025-02-09 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-13 | 2025-02-09 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-13 | 2025-02-09 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/10 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-13 | 2025-02-09 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-14 | 2025-02-09 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-14 | 2025-02-09 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-14 | 2025-02-09 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-15 | 2025-02-09 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-15 | 2025-02-09 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-15 | 2025-02-09 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-16 | 2025-02-16 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 35/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-16 | 2025-02-16 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-17 | 2025-02-16 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-17 | 2025-02-16 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-17 | 2025-02-16 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-17 | 2025-02-16 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-18 | 2025-02-16 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-18 | 2025-02-16 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-19 | 2025-02-16 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-19 | 2025-02-16 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 25/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-19 | 2025-02-16 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-20 | 2025-02-16 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 40/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-20 | 2025-02-16 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 40/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-21 | 2025-02-16 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-22 | 2025-02-16 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-24 | 2025-02-23 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-24 | 2025-02-23 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-25 | 2025-02-23 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 32/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-26 | 2025-02-23 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-26 | 2025-02-23 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-26 | 2025-02-23 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-26 | 2025-02-23 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-27 | 2025-02-23 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-27 | 2025-02-23 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-02-28 | 2025-02-23 | 2025-02-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-02 | 2025-03-02 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-02 | 2025-03-02 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-02 | 2025-03-02 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-02 | 2025-03-02 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-02 | 2025-03-02 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-03 | 2025-03-02 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-03 | 2025-03-02 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 22/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-03 | 2025-03-02 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-04 | 2025-03-02 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-04 | 2025-03-02 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-04 | 2025-03-02 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-04 | 2025-03-02 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-05 | 2025-03-02 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-06 | 2025-03-02 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-06 | 2025-03-02 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-06 | 2025-03-02 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-08 | 2025-03-02 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-08 | 2025-03-02 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 32/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-08 | 2025-03-02 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-09 | 2025-03-09 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-10 | 2025-03-09 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 32/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-10 | 2025-03-09 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 34/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-10 | 2025-03-09 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-10 | 2025-03-09 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-11 | 2025-03-09 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-11 | 2025-03-09 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-11 | 2025-03-09 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-12 | 2025-03-09 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-12 | 2025-03-09 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 40/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-12 | 2025-03-09 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-13 | 2025-03-09 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-13 | 2025-03-09 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 33/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-13 | 2025-03-09 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 34/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-13 | 2025-03-09 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-13 | 2025-03-09 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-13 | 2025-03-09 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/14 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-15 | 2025-03-09 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 32/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-15 | 2025-03-09 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-16 | 2025-03-16 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-16 | 2025-03-16 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-16 | 2025-03-16 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-16 | 2025-03-16 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-17 | 2025-03-16 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 32/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-17 | 2025-03-16 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/12 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-18 | 2025-03-16 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-19 | 2025-03-16 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-19 | 2025-03-16 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-19 | 2025-03-16 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-20 | 2025-03-16 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-20 | 2025-03-16 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/10 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-20 | 2025-03-16 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-22 | 2025-03-16 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/11 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-23 | 2025-03-23 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-23 | 2025-03-23 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 32/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-23 | 2025-03-23 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-23 | 2025-03-23 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-23 | 2025-03-23 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-23 | 2025-03-23 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-24 | 2025-03-23 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-24 | 2025-03-23 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-27 | 2025-03-23 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-27 | 2025-03-23 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-28 | 2025-03-23 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 19/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-28 | 2025-03-23 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 32/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-29 | 2025-03-23 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-29 | 2025-03-23 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 34/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-29 | 2025-03-23 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-30 | 2025-03-30 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/11 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-30 | 2025-03-30 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-30 | 2025-03-30 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/12 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-30 | 2025-03-30 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/14 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-30 | 2025-03-30 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/15 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-03-30 | 2025-03-30 | 2025-03-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 20/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-02 | 2025-03-30 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 33/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-03 | 2025-03-30 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-03 | 2025-03-30 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-05 | 2025-03-30 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-06 | 2025-04-06 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-06 | 2025-04-06 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-06 | 2025-04-06 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-07 | 2025-04-06 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-07 | 2025-04-06 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 20A/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-07 | 2025-04-06 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-07 | 2025-04-06 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-08 | 2025-04-06 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-08 | 2025-04-06 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/13 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-09 | 2025-04-06 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-10 | 2025-04-06 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 35/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-10 | 2025-04-06 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-11 | 2025-04-06 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-11 | 2025-04-06 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/20 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-11 | 2025-04-06 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/21 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-12 | 2025-04-06 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 17/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-12 | 2025-04-06 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-14 | 2025-04-13 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-14 | 2025-04-13 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-15 | 2025-04-13 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-15 | 2025-04-13 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 35/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-15 | 2025-04-13 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-15 | 2025-04-13 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/10 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-15 | 2025-04-13 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/11 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-16 | 2025-04-13 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-16 | 2025-04-13 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-16 | 2025-04-13 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-17 | 2025-04-13 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 34/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-17 | 2025-04-13 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/19 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-17 | 2025-04-13 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/23 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-17 | 2025-04-13 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-17 | 2025-04-13 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-17 | 2025-04-13 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-17 | 2025-04-13 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-18 | 2025-04-13 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-19 | 2025-04-13 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-19 | 2025-04-13 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-19 | 2025-04-13 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/18 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-19 | 2025-04-13 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-20 | 2025-04-20 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-21 | 2025-04-20 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-22 | 2025-04-20 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-22 | 2025-04-20 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-22 | 2025-04-20 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-23 | 2025-04-20 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-23 | 2025-04-20 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-24 | 2025-04-20 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 28/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-24 | 2025-04-20 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-25 | 2025-04-20 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-25 | 2025-04-20 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-26 | 2025-04-20 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 3/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-27 | 2025-04-27 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 17/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-28 | 2025-04-27 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/11 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-29 | 2025-04-27 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-04-29 | 2025-04-27 | 2025-04-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/16 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-01 | 2025-04-27 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-01 | 2025-04-27 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-01 | 2025-04-27 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-01 | 2025-04-27 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-01 | 2025-04-27 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-02 | 2025-04-27 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 20/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-02 | 2025-04-27 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 38/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-02 | 2025-04-27 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-03 | 2025-04-27 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 20A/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-03 | 2025-04-27 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-03 | 2025-04-27 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-04 | 2025-05-04 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/15 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-05 | 2025-05-04 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-05 | 2025-05-04 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 28/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-05 | 2025-05-04 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-06 | 2025-05-04 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-06 | 2025-05-04 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-06 | 2025-05-04 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-07 | 2025-05-04 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-07 | 2025-05-04 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/12 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-08 | 2025-05-04 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 35/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-09 | 2025-05-04 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/20 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-10 | 2025-05-04 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-10 | 2025-05-04 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 17/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-10 | 2025-05-04 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 20/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-11 | 2025-05-11 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-11 | 2025-05-11 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-11 | 2025-05-11 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/13 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-11 | 2025-05-11 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/14 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-12 | 2025-05-11 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-13 | 2025-05-11 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 34/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-13 | 2025-05-11 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-14 | 2025-05-11 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-15 | 2025-05-11 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 19/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-15 | 2025-05-11 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/17 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-15 | 2025-05-11 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-17 | 2025-05-11 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/11 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-18 | 2025-05-18 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-18 | 2025-05-18 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-18 | 2025-05-18 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-18 | 2025-05-18 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-18 | 2025-05-18 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-19 | 2025-05-18 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 28/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-19 | 2025-05-18 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-19 | 2025-05-18 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-19 | 2025-05-18 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-21 | 2025-05-18 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-24 | 2025-05-18 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 3/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-24 | 2025-05-18 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 3/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-24 | 2025-05-18 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/10 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-25 | 2025-05-25 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-26 | 2025-05-25 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/19 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-26 | 2025-05-25 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/21 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-26 | 2025-05-25 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/23 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-26 | 2025-05-25 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-26 | 2025-05-25 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-26 | 2025-05-25 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-27 | 2025-05-25 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-27 | 2025-05-25 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-27 | 2025-05-25 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-28 | 2025-05-25 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-29 | 2025-05-25 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-30 | 2025-05-25 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-31 | 2025-05-25 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-31 | 2025-05-25 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-31 | 2025-05-25 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 3/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-31 | 2025-05-25 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-31 | 2025-05-25 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/17 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-31 | 2025-05-25 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/18 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-31 | 2025-05-25 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-05-31 | 2025-05-25 | 2025-05-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-01 | 2025-06-01 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1B/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-01 | 2025-06-01 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1B/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-01 | 2025-06-01 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1B/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-01 | 2025-06-01 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 31/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-01 | 2025-06-01 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/10 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-02 | 2025-06-01 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-03 | 2025-06-01 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 30/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-03 | 2025-06-01 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-04 | 2025-06-01 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-05 | 2025-06-01 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 21/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-05 | 2025-06-01 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 33/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-06 | 2025-06-01 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 29/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-06 | 2025-06-01 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/13 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-06 | 2025-06-01 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/14 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-06 | 2025-06-01 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/15 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-06 | 2025-06-01 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-06 | 2025-06-01 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-06 | 2025-06-01 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-08 | 2025-06-08 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 41/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-10 | 2025-06-08 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-13 | 2025-06-08 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1A/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-13 | 2025-06-08 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-13 | 2025-06-08 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-15 | 2025-06-15 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-17 | 2025-06-15 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1B/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-17 | 2025-06-15 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 28/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-17 | 2025-06-15 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 34/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-17 | 2025-06-15 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-18 | 2025-06-15 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-18 | 2025-06-15 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-19 | 2025-06-15 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-20 | 2025-06-15 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 20A/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-20 | 2025-06-15 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-21 | 2025-06-15 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1B/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-21 | 2025-06-15 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 3/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-21 | 2025-06-15 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-21 | 2025-06-15 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/11 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-22 | 2025-06-22 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1A/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-22 | 2025-06-22 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 3/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-22 | 2025-06-22 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 3/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-22 | 2025-06-22 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 3/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-24 | 2025-06-22 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 15/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-24 | 2025-06-22 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1B/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-24 | 2025-06-22 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1C/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-24 | 2025-06-22 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-24 | 2025-06-22 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-25 | 2025-06-22 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-25 | 2025-06-22 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 35/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-25 | 2025-06-22 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-25 | 2025-06-22 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-27 | 2025-06-22 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-28 | 2025-06-22 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1B/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-28 | 2025-06-22 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-29 | 2025-06-29 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-29 | 2025-06-29 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-30 | 2025-06-29 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-06-30 | 2025-06-29 | 2025-06-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-01 | 2025-06-29 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 5/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-02 | 2025-06-29 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-03 | 2025-06-29 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-04 | 2025-06-29 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1C/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-04 | 2025-06-29 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-04 | 2025-06-29 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-05 | 2025-06-29 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 34/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-06 | 2025-07-06 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-07 | 2025-07-06 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-08 | 2025-07-06 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-08 | 2025-07-06 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-08 | 2025-07-06 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-08 | 2025-07-06 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-09 | 2025-07-06 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/22 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-09 | 2025-07-06 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-11 | 2025-07-06 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-11 | 2025-07-06 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/16 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-11 | 2025-07-06 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-12 | 2025-07-06 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-12 | 2025-07-06 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-12 | 2025-07-06 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-13 | 2025-07-13 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-13 | 2025-07-13 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-13 | 2025-07-13 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-13 | 2025-07-13 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-14 | 2025-07-13 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-14 | 2025-07-13 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-15 | 2025-07-13 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-16 | 2025-07-13 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43B/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-16 | 2025-07-13 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 44/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-16 | 2025-07-13 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/13 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-17 | 2025-07-13 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 35/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-17 | 2025-07-13 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-17 | 2025-07-13 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-18 | 2025-07-13 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 5/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-18 | 2025-07-13 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-19 | 2025-07-13 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-19 | 2025-07-13 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-20 | 2025-07-20 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-21 | 2025-07-20 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-21 | 2025-07-20 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-22 | 2025-07-20 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-22 | 2025-07-20 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-22 | 2025-07-20 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/14 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-24 | 2025-07-20 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-26 | 2025-07-20 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-29 | 2025-07-27 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/21 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-29 | 2025-07-27 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/22 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-30 | 2025-07-27 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-07-30 | 2025-07-27 | 2025-07-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-01 | 2025-07-27 | 2025-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-02 | 2025-07-27 | 2025-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-03 | 2025-08-03 | 2025-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-04 | 2025-08-03 | 2025-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 34/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-05 | 2025-08-03 | 2025-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-05 | 2025-08-03 | 2025-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/13 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-07 | 2025-08-03 | 2025-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 10/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-08 | 2025-08-03 | 2025-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-08 | 2025-08-03 | 2025-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/12 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-09 | 2025-08-03 | 2025-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/23 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-11 | 2025-08-10 | 2025-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-12 | 2025-08-10 | 2025-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-13 | 2025-08-10 | 2025-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 40/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-13 | 2025-08-10 | 2025-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-14 | 2025-08-10 | 2025-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-16 | 2025-08-10 | 2025-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-19 | 2025-08-17 | 2025-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-20 | 2025-08-17 | 2025-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1A/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-23 | 2025-08-17 | 2025-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 12/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-25 | 2025-08-24 | 2025-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-26 | 2025-08-24 | 2025-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-30 | 2025-08-24 | 2025-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 40/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-31 | 2025-08-31 | 2025-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-08-31 | 2025-08-31 | 2025-08-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/15 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-01 | 2025-08-31 | 2025-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-01 | 2025-08-31 | 2025-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-05 | 2025-08-31 | 2025-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-05 | 2025-08-31 | 2025-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-06 | 2025-08-31 | 2025-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 41/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-07 | 2025-09-07 | 2025-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-08 | 2025-09-07 | 2025-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-08 | 2025-09-07 | 2025-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-09 | 2025-09-07 | 2025-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/12 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-10 | 2025-09-07 | 2025-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-13 | 2025-09-07 | 2025-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-13 | 2025-09-07 | 2025-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-14 | 2025-09-14 | 2025-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/10 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-16 | 2025-09-14 | 2025-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-16 | 2025-09-14 | 2025-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/17 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-21 | 2025-09-21 | 2025-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-21 | 2025-09-21 | 2025-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-21 | 2025-09-21 | 2025-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 5/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-24 | 2025-09-21 | 2025-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-25 | 2025-09-21 | 2025-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-27 | 2025-09-21 | 2025-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-09-28 | 2025-09-28 | 2025-09-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/18 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-01 | 2025-09-28 | 2025-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-07 | 2025-10-05 | 2025-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-07 | 2025-10-05 | 2025-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 9/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-10 | 2025-10-05 | 2025-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-10 | 2025-10-05 | 2025-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-12 | 2025-10-12 | 2025-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-12 | 2025-10-12 | 2025-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-13 | 2025-10-12 | 2025-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/20 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-13 | 2025-10-12 | 2025-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43B/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-14 | 2025-10-12 | 2025-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/6 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-17 | 2025-10-12 | 2025-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/19 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-17 | 2025-10-12 | 2025-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-17 | 2025-10-12 | 2025-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 42/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-21 | 2025-10-19 | 2025-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-22 | 2025-10-19 | 2025-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-22 | 2025-10-19 | 2025-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 41/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-23 | 2025-10-19 | 2025-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-26 | 2025-10-26 | 2025-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-28 | 2025-10-26 | 2025-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-31 | 2025-10-26 | 2025-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/10 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-10-31 | 2025-10-26 | 2025-10-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/13 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-04 | 2025-11-02 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43B/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-04 | 2025-11-02 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-06 | 2025-11-02 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 3/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-06 | 2025-11-02 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-06 | 2025-11-02 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-08 | 2025-11-02 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 36/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-10 | 2025-11-09 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 44/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-10 | 2025-11-09 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-11 | 2025-11-09 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 3/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-11 | 2025-11-09 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-11 | 2025-11-09 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 7/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-13 | 2025-11-09 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/11 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-15 | 2025-11-09 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 11/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-16 | 2025-11-16 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/11 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-18 | 2025-11-16 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/14 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-18 | 2025-11-16 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-20 | 2025-11-16 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-20 | 2025-11-16 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/10 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-21 | 2025-11-16 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/15 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-23 | 2025-11-23 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-24 | 2025-11-23 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/11 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-26 | 2025-11-23 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 27/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-26 | 2025-11-23 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/11 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-27 | 2025-11-23 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 39/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-27 | 2025-11-23 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-27 | 2025-11-23 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 7/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-28 | 2025-11-23 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-28 | 2025-11-23 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-29 | 2025-11-23 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/12 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1B/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-01 | 2025-11-30 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1B/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-01 | 2025-11-30 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-04 | 2025-11-30 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1B/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-05 | 2025-11-30 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-06 | 2025-11-30 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-07 | 2025-12-07 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1B/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-09 | 2025-12-07 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1B/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-09 | 2025-12-07 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 7/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-10 | 2025-12-07 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 44/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-11 | 2025-12-07 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-13 | 2025-12-07 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 37/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-14 | 2025-12-14 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 6/7 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-17 | 2025-12-14 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 3/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-17 | 2025-12-14 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-19 | 2025-12-14 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-20 | 2025-12-14 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 13/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-20 | 2025-12-14 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 3/3 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-21 | 2025-12-21 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-21 | 2025-12-21 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/2 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-21 | 2025-12-21 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 16/9 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-22 | 2025-12-21 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/4 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-22 | 2025-12-21 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-24 | 2025-12-21 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-26 | 2025-12-21 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 1C/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-26 | 2025-12-21 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/5 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-27 | 2025-12-21 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/22 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-27 | 2025-12-21 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 8/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-30 | 2025-12-28 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2025-12-31 | 2025-12-28 | 2025-12-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 2/0 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2026-01-03 | 2025-12-28 | 2026-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 4/8 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2026-01-07 | 2026-01-04 | 2026-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 28/1 | 1
TA 421 | TA 421 | ta421 |  | filename | 2026-05-18 | 2026-01-08 | 2026-01-04 | 2026-01-01 | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | detail | detail_date | 43A/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2015-11-27 | 2015-11-22 | 2015-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 171/10 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-03-28 | 2024-03-24 | 2024-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 164/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-04-04 | 2024-03-31 | 2024-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 170/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-04-28 | 2024-04-28 | 2024-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 136/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-10-06 | 2024-10-06 | 2024-10-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 101/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-10-07 | 2024-10-06 | 2024-10-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 109/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-10-11 | 2024-10-06 | 2024-10-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 101/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-10-11 | 2024-10-06 | 2024-10-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 110A/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-10-21 | 2024-10-20 | 2024-10-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 101/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-10-24 | 2024-10-20 | 2024-10-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 110/6 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-10-25 | 2024-10-20 | 2024-10-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 101/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-10-28 | 2024-10-27 | 2024-10-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 108/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-10-29 | 2024-10-27 | 2024-10-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 109/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-02 | 2024-10-27 | 2024-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 101/6 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-04 | 2024-11-03 | 2024-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 111/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-08 | 2024-11-03 | 2024-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 101/8 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-10 | 2024-11-10 | 2024-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 110A/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-14 | 2024-11-10 | 2024-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 101/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-14 | 2024-11-10 | 2024-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 113/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-15 | 2024-11-10 | 2024-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 110/8 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-17 | 2024-11-17 | 2024-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 110/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-18 | 2024-11-17 | 2024-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 101/7 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-18 | 2024-11-17 | 2024-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 111/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-19 | 2024-11-17 | 2024-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 105/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-20 | 2024-11-17 | 2024-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 114/10 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-22 | 2024-11-17 | 2024-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 110/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-22 | 2024-11-17 | 2024-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 113/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-23 | 2024-11-17 | 2024-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 110/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-23 | 2024-11-17 | 2024-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 114/8 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-27 | 2024-11-24 | 2024-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 104/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-27 | 2024-11-24 | 2024-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 114/9 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-28 | 2024-11-24 | 2024-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 114/7 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-29 | 2024-11-24 | 2024-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 110/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-29 | 2024-11-24 | 2024-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 110/7 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-29 | 2024-11-24 | 2024-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 113/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-30 | 2024-11-24 | 2024-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 105/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-30 | 2024-11-24 | 2024-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 108/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-30 | 2024-11-24 | 2024-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 109/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-11-30 | 2024-11-24 | 2024-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 114/6 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-01 | 2024-12-01 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 116/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-03 | 2024-12-01 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 104/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-05 | 2024-12-01 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 113/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-07 | 2024-12-01 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 114/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-07 | 2024-12-01 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 114/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-08 | 2024-12-08 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 111/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-09 | 2024-12-08 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 113/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-10 | 2024-12-08 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 127/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-12 | 2024-12-08 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 113/6 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-13 | 2024-12-08 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 108/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-14 | 2024-12-08 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 102/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-14 | 2024-12-08 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 114/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-15 | 2024-12-15 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 127/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-16 | 2024-12-15 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 111/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-16 | 2024-12-15 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 126/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-17 | 2024-12-15 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 110/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-17 | 2024-12-15 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 126/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-19 | 2024-12-15 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 108/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-19 | 2024-12-15 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 114/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-19 | 2024-12-15 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 147A/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-20 | 2024-12-15 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 127/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-21 | 2024-12-15 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 150/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-22 | 2024-12-22 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152A/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-24 | 2024-12-22 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 147A/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-24 | 2024-12-22 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 150/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-26 | 2024-12-22 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 116/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-26 | 2024-12-22 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-27 | 2024-12-22 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 147A/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-27 | 2024-12-22 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152A/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-28 | 2024-12-22 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 150/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-29 | 2024-12-29 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 127/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-29 | 2024-12-29 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152A/9 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-30 | 2024-12-29 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-31 | 2024-12-29 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 109/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-31 | 2024-12-29 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 114/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2024-12-31 | 2024-12-29 | 2024-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 147A/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-02 | 2024-12-29 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152A/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-04 | 2024-12-29 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 111/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-05 | 2025-01-05 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 147/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-05 | 2025-01-05 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152A/7 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-10 | 2025-01-05 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152A/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-12 | 2025-01-12 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 120/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-12 | 2025-01-12 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 150/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-15 | 2025-01-12 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 103/7 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-15 | 2025-01-12 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 155/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-16 | 2025-01-12 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 144A/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-16 | 2025-01-12 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152A/8 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-17 | 2025-01-12 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 131/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-17 | 2025-01-12 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152A/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-18 | 2025-01-12 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 126/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-19 | 2025-01-19 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 144A/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-20 | 2025-01-19 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 126/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-21 | 2025-01-19 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152A/11 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-21 | 2025-01-19 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 155/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-22 | 2025-01-19 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 150/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-23 | 2025-01-19 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152A/6 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-24 | 2025-01-19 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 120/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-25 | 2025-01-19 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-25 | 2025-01-19 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152A/10 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-27 | 2025-01-26 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 112/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-28 | 2025-01-26 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152A/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-30 | 2025-01-26 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 120/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-30 | 2025-01-26 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 154/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-31 | 2025-01-26 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 128/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-31 | 2025-01-26 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 130/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-01-31 | 2025-01-26 | 2025-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 148/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-04 | 2025-02-02 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 154/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-05 | 2025-02-02 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 140/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-05 | 2025-02-02 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 156/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-06 | 2025-02-02 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 129A/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-07 | 2025-02-02 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 104/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-08 | 2025-02-02 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 154/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-09 | 2025-02-09 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 130/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-10 | 2025-02-09 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 129A/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-10 | 2025-02-09 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 155/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-11 | 2025-02-09 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 129A/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-12 | 2025-02-09 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 156/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-13 | 2025-02-09 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 148A/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-14 | 2025-02-09 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 130/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-15 | 2025-02-09 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 160/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-16 | 2025-02-16 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 159/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-17 | 2025-02-16 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 109/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-17 | 2025-02-16 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 135/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-20 | 2025-02-16 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 110A/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-21 | 2025-02-16 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 135/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-22 | 2025-02-16 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 135/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-22 | 2025-02-16 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 156/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-24 | 2025-02-23 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 155/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-24 | 2025-02-23 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 159/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-25 | 2025-02-23 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 136/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-25 | 2025-02-23 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 160/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-26 | 2025-02-23 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 164/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-27 | 2025-02-23 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 118/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-27 | 2025-02-23 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 136/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-27 | 2025-02-23 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 161/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-28 | 2025-02-23 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 154/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-28 | 2025-02-23 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 155/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-02-28 | 2025-02-23 | 2025-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 160/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-04 | 2025-03-02 | 2025-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 160/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-05 | 2025-03-02 | 2025-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 135/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-06 | 2025-03-02 | 2025-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 161/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-07 | 2025-03-02 | 2025-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 164/6 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-08 | 2025-03-02 | 2025-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 160/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-11 | 2025-03-09 | 2025-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 161/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-12 | 2025-03-09 | 2025-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 140/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-16 | 2025-03-16 | 2025-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 164/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-19 | 2025-03-16 | 2025-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 159/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-22 | 2025-03-16 | 2025-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 144A/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-26 | 2025-03-23 | 2025-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 161/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-28 | 2025-03-23 | 2025-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 144A/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-28 | 2025-03-23 | 2025-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 166/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-29 | 2025-03-23 | 2025-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 170/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-30 | 2025-03-30 | 2025-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 170/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-31 | 2025-03-30 | 2025-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 147/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-31 | 2025-03-30 | 2025-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 160/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-31 | 2025-03-30 | 2025-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 161/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-31 | 2025-03-30 | 2025-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 164/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-31 | 2025-03-30 | 2025-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 166/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-03-31 | 2025-03-30 | 2025-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 170/8 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-03 | 2025-03-30 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 115/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-07 | 2025-04-06 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 116/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-07 | 2025-04-06 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 169/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-07 | 2025-04-06 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 170/9 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-08 | 2025-04-06 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 164/7 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-08 | 2025-04-06 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 166/8 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-09 | 2025-04-06 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 165/6 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-10 | 2025-04-06 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 147A/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-10 | 2025-04-06 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 147A/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-10 | 2025-04-06 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 172/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-11 | 2025-04-06 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 170/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-12 | 2025-04-06 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 120/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-12 | 2025-04-06 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 148/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-12 | 2025-04-06 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 170/10 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-12 | 2025-04-06 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 173/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-13 | 2025-04-13 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 165/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-13 | 2025-04-13 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 166/6 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-14 | 2025-04-13 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 169/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-15 | 2025-04-13 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 119/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-15 | 2025-04-13 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 164/8 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-16 | 2025-04-13 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 173/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-17 | 2025-04-13 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 170/7 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-18 | 2025-04-13 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 165/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-18 | 2025-04-13 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 172/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-20 | 2025-04-20 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 166/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-20 | 2025-04-20 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 166/9 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-20 | 2025-04-20 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 173/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-22 | 2025-04-20 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 103/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-22 | 2025-04-20 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 106/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-22 | 2025-04-20 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 132/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-22 | 2025-04-20 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 170/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-22 | 2025-04-20 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 171/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-24 | 2025-04-20 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 166/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-24 | 2025-04-20 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 169/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-24 | 2025-04-20 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 175/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-26 | 2025-04-20 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 167/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-26 | 2025-04-20 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 171/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-26 | 2025-04-20 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 172/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-26 | 2025-04-20 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 173/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-26 | 2025-04-20 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 175/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-27 | 2025-04-27 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 108/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-28 | 2025-04-27 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 161/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-28 | 2025-04-27 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 166/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-28 | 2025-04-27 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 170/6 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-29 | 2025-04-27 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 165/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-30 | 2025-04-27 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 165/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-30 | 2025-04-27 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 167/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-04-30 | 2025-04-27 | 2025-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 176/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-03 | 2025-04-27 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 103/5A | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-03 | 2025-04-27 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 136/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-03 | 2025-04-27 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 167/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-04 | 2025-05-04 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 159/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-04 | 2025-05-04 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 169/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-04 | 2025-05-04 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 171/9 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-04 | 2025-05-04 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 176/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-05 | 2025-05-04 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 103/5A1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-06 | 2025-05-04 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 176/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-08 | 2025-05-04 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 103/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-08 | 2025-05-04 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 178/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-09 | 2025-05-04 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 158/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-09 | 2025-05-04 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 167/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-10 | 2025-05-04 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 174A/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-10 | 2025-05-04 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 176/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-11 | 2025-05-11 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 103/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-11 | 2025-05-11 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 169/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-13 | 2025-05-11 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 103/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-13 | 2025-05-11 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 141/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-13 | 2025-05-11 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 166/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-16 | 2025-05-11 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 158/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-16 | 2025-05-11 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 170/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-17 | 2025-05-11 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 171/8 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-17 | 2025-05-11 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 177/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-18 | 2025-05-18 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 103/6A | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-18 | 2025-05-18 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 178/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-20 | 2025-05-18 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 142/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-21 | 2025-05-18 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 171/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-21 | 2025-05-18 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 172/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-21 | 2025-05-18 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 177/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-22 | 2025-05-18 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 103/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-23 | 2025-05-18 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 172/6 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-23 | 2025-05-18 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 174A/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-23 | 2025-05-18 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 177/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-24 | 2025-05-18 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 103/8 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-25 | 2025-05-25 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 169/6 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-25 | 2025-05-25 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 177/8 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-27 | 2025-05-25 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 167/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-27 | 2025-05-25 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 177/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-29 | 2025-05-25 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 167/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-29 | 2025-05-25 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 174A/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-29 | 2025-05-25 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 177/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-30 | 2025-05-25 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 172/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-30 | 2025-05-25 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 178/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-31 | 2025-05-25 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 101/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-31 | 2025-05-25 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 150/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-05-31 | 2025-05-25 | 2025-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 177/6 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-02 | 2025-06-01 | 2025-06-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 121/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-03 | 2025-06-01 | 2025-06-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 171/7 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-03 | 2025-06-01 | 2025-06-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 177/7 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-04 | 2025-06-01 | 2025-06-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 174A/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-05 | 2025-06-01 | 2025-06-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 173/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-07 | 2025-06-01 | 2025-06-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 110/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-08 | 2025-06-08 | 2025-06-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 171/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-08 | 2025-06-08 | 2025-06-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 171/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-09 | 2025-06-08 | 2025-06-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 172/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-11 | 2025-06-08 | 2025-06-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-13 | 2025-06-08 | 2025-06-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 152A/12 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-13 | 2025-06-08 | 2025-06-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 174A/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-28 | 2025-06-22 | 2025-06-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 174A/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-29 | 2025-06-29 | 2025-06-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 151/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-06-29 | 2025-06-29 | 2025-06-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 171/6 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-07-15 | 2025-07-13 | 2025-07-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 156/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-07-17 | 2025-07-13 | 2025-07-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 169/7 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-08-29 | 2025-08-24 | 2025-08-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 179/7 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-09-04 | 2025-08-31 | 2025-09-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 178/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-09-12 | 2025-09-07 | 2025-09-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 178/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-09-12 | 2025-09-07 | 2025-09-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 179/6 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-09-14 | 2025-09-14 | 2025-09-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 145/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-09-19 | 2025-09-14 | 2025-09-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 114/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-09-23 | 2025-09-21 | 2025-09-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 179/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-09-26 | 2025-09-21 | 2025-09-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 179/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-09-27 | 2025-09-21 | 2025-09-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 149B/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-09-29 | 2025-09-28 | 2025-09-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 179/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-09-30 | 2025-09-28 | 2025-09-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 154/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-10-05 | 2025-10-05 | 2025-10-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 126/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-10-09 | 2025-10-05 | 2025-10-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 149B/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-10-15 | 2025-10-12 | 2025-10-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 149B/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-10-16 | 2025-10-12 | 2025-10-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 100/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-10-16 | 2025-10-12 | 2025-10-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 178/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-10-17 | 2025-10-12 | 2025-10-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 149B/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-10-17 | 2025-10-12 | 2025-10-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 155/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-10-17 | 2025-10-12 | 2025-10-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 99/8 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-10-22 | 2025-10-19 | 2025-10-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 165/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-10-25 | 2025-10-19 | 2025-10-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 168/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-10-25 | 2025-10-19 | 2025-10-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 99/6 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-10-30 | 2025-10-26 | 2025-10-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 180/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-01 | 2025-10-26 | 2025-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 99/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-03 | 2025-11-02 | 2025-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 99/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-06 | 2025-11-02 | 2025-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 99/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-07 | 2025-11-02 | 2025-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 165/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-09 | 2025-11-09 | 2025-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 99/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-10 | 2025-11-09 | 2025-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 181/6 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-11 | 2025-11-09 | 2025-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 99/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-14 | 2025-11-09 | 2025-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 103/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-16 | 2025-11-16 | 2025-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 99/7 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-18 | 2025-11-16 | 2025-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 181/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-19 | 2025-11-16 | 2025-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 103/9 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-20 | 2025-11-16 | 2025-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 169/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-26 | 2025-11-23 | 2025-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 122/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-26 | 2025-11-23 | 2025-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 175/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-27 | 2025-11-23 | 2025-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 181/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-11-29 | 2025-11-23 | 2025-11-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 138/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-03 | 2025-11-30 | 2025-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 123/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-06 | 2025-11-30 | 2025-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 181/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-08 | 2025-12-07 | 2025-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 123/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-08 | 2025-12-07 | 2025-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 169/9 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-10 | 2025-12-07 | 2025-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 179/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-12 | 2025-12-07 | 2025-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 123/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-13 | 2025-12-07 | 2025-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 153/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-14 | 2025-12-14 | 2025-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 154/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-15 | 2025-12-14 | 2025-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 125/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-15 | 2025-12-14 | 2025-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 175/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-22 | 2025-12-21 | 2025-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 123/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-23 | 2025-12-21 | 2025-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 129A/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-24 | 2025-12-21 | 2025-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 181/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-28 | 2025-12-28 | 2025-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 113/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-30 | 2025-12-28 | 2025-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 175/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-31 | 2025-12-28 | 2025-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 149B/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-31 | 2025-12-28 | 2025-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 158/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2025-12-31 | 2025-12-28 | 2025-12-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 158/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-04 | 2026-01-04 | 2026-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 125/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-07 | 2026-01-04 | 2026-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 162/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-08 | 2026-01-04 | 2026-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 162/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-09 | 2026-01-04 | 2026-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 124/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-11 | 2026-01-11 | 2026-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 179/9 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-13 | 2026-01-11 | 2026-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 149/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-16 | 2026-01-11 | 2026-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 149/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-18 | 2026-01-18 | 2026-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 149/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-19 | 2026-01-18 | 2026-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 164/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-22 | 2026-01-18 | 2026-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 174B/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-23 | 2026-01-18 | 2026-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 163/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-24 | 2026-01-18 | 2026-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 162/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-25 | 2026-01-25 | 2026-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 146/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-25 | 2026-01-25 | 2026-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 164/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-25 | 2026-01-25 | 2026-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 182/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-29 | 2026-01-25 | 2026-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 148B/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-01-31 | 2026-01-25 | 2026-01-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 149A/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-02-04 | 2026-02-01 | 2026-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 139/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-02-06 | 2026-02-01 | 2026-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 139/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-02-07 | 2026-02-01 | 2026-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 156/6 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-02-10 | 2026-02-08 | 2026-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 138/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-02-12 | 2026-02-08 | 2026-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 138/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-02-15 | 2026-02-15 | 2026-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 148B/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-02-19 | 2026-02-15 | 2026-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 146/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-02-21 | 2026-02-15 | 2026-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 148C/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-02-24 | 2026-02-22 | 2026-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 142/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-02-28 | 2026-02-22 | 2026-02-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 148B/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-03-03 | 2026-03-01 | 2026-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 156/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-03-08 | 2026-03-08 | 2026-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 169/8 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-03-10 | 2026-03-08 | 2026-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 156/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-03-10 | 2026-03-08 | 2026-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 157/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-03-11 | 2026-03-08 | 2026-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 138/2 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-03-21 | 2026-03-15 | 2026-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 144/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-03-21 | 2026-03-15 | 2026-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 171/5 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-03-31 | 2026-03-29 | 2026-03-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 143/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-04-09 | 2026-04-05 | 2026-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 134/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-04-09 | 2026-04-05 | 2026-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 137A/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-04-14 | 2026-04-12 | 2026-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 129/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-04-14 | 2026-04-12 | 2026-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 133/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-04-15 | 2026-04-12 | 2026-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 136/4 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-04-18 | 2026-04-12 | 2026-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 136/3 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-04-23 | 2026-04-19 | 2026-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 129/1 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-04-30 | 2026-04-26 | 2026-04-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 117/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-05-15 | 2026-05-10 | 2026-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 137/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-05-15 | 2026-05-10 | 2026-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 177/0 | 1
TA 505 | TA 505 | ta505 |  | filename | 2026-05-19 | 2026-05-18 | 2026-05-17 | 2026-05-01 | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | detail | detail_date | 181/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-01-01 | 2024-12-29 | 2025-01-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 16/4 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-01-01 | 2024-12-29 | 2025-01-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 8/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-01-01 | 2024-12-29 | 2025-01-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 8/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-01-01 | 2024-12-29 | 2025-01-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 8/4 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-01-01 | 2024-12-29 | 2025-01-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 8/6 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-01-07 | 2025-01-05 | 2025-01-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 38/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 13/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 13/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 15/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 15/7 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 15/8 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 15/9 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 16/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 7/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 8/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 8/5 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 8/7 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 8/8 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 9/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-02-01 | 2025-01-26 | 2025-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 9/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 10/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 10/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 12/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 12/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 12/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 12/4 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 12/5 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 12/6 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 13/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 13/4 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 13/5 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 14/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 14/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 14/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 14/4 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 15/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 15/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 15/4 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 15/5 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 16/10 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 16/11 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 16/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 16/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 16/5 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 16/6 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 16/7 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 16/8 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 16/9 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 24/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 24/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 39/4 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 7/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-01 | 2025-02-23 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 7/4 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-05 | 2025-03-02 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 27/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-03-05 | 2025-03-02 | 2025-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 5/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 21/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 21/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 21/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 21/4 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 22/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 24/10 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 24/11 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 24/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 24/4 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 24/5 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 24/6 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 24/7 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 24/8 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 24/9 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 26/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 26/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 26/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 26/4 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 27/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 27/4 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 27/5 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 29/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 29/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 34/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 36/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 36/6 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 36/7 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 36/8 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 39/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 39/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 39/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 39/5 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 39/7 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 39/8 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 40/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 40/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 40/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 41/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 41/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 41/5 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 41/8 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 44/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 44/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 5/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 7/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 8/10 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 8/9 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 9/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-04-05 | 2025-03-30 | 2025-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 23/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-02 | 2025-04-27 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 36/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-05 | 2025-05-04 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 30/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-05 | 2025-05-04 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 34/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-05 | 2025-05-04 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 36/4 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-05 | 2025-05-04 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 36/5 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-06 | 2025-05-04 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 5/5 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-07 | 2025-05-04 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 6/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-08 | 2025-05-04 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 20/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-08 | 2025-05-04 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 32/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-08 | 2025-05-04 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 34/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-09 | 2025-05-04 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 36/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-09 | 2025-05-04 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 5/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-10 | 2025-05-04 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 32/4 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-11 | 2025-05-11 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 38/4 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-12 | 2025-05-11 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 20/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-13 | 2025-05-11 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 38/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-13 | 2025-05-11 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 5/4 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-15 | 2025-05-11 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 32/5 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-16 | 2025-05-11 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 6/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-17 | 2025-05-11 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 38/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-19 | 2025-05-18 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 38/7 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-19 | 2025-05-18 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 47/8 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-19 | 2025-05-18 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 49/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-21 | 2025-05-18 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 32/6 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-21 | 2025-05-18 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 32/7 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-22 | 2025-05-18 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 51/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-23 | 2025-05-18 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 38/6 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-23 | 2025-05-18 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 47/11 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-23 | 2025-05-18 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 49/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-23 | 2025-05-18 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 5/7 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-24 | 2025-05-18 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 51/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-25 | 2025-05-25 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 32/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-25 | 2025-05-25 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 5/6 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-26 | 2025-05-25 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 49/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-26 | 2025-05-25 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 51/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-27 | 2025-05-25 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 47/4 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-29 | 2025-05-25 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 38/8 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-29 | 2025-05-25 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 48/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-30 | 2025-05-25 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 13/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-05-31 | 2025-05-25 | 2025-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 67/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-01 | 2025-06-01 | 2025-06-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 48/6 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-01 | 2025-06-01 | 2025-06-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 49/4 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-02 | 2025-06-01 | 2025-06-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 38/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-04 | 2025-06-01 | 2025-06-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 47/6 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-05 | 2025-06-01 | 2025-06-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 48/8 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-06 | 2025-06-01 | 2025-06-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 49/5 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-10 | 2025-06-08 | 2025-06-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 48/9 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-14 | 2025-06-08 | 2025-06-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 49/6 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-16 | 2025-06-15 | 2025-06-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 49/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-17 | 2025-06-15 | 2025-06-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 66/5 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-18 | 2025-06-15 | 2025-06-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 65/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-21 | 2025-06-15 | 2025-06-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 41/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-23 | 2025-06-22 | 2025-06-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 65/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-27 | 2025-06-22 | 2025-06-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 66/7 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-06-30 | 2025-06-29 | 2025-06-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 65/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-07-06 | 2025-07-06 | 2025-07-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 67/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-07-07 | 2025-07-06 | 2025-07-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 65/9 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-07-11 | 2025-07-06 | 2025-07-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 63/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-07-14 | 2025-07-13 | 2025-07-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 65/7 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-07-16 | 2025-07-13 | 2025-07-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 63/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-07-22 | 2025-07-20 | 2025-07-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 65/11 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-08-06 | 2025-08-03 | 2025-08-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 41/4 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-08-12 | 2025-08-10 | 2025-08-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 21/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-08-12 | 2025-08-10 | 2025-08-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 46/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-08-18 | 2025-08-17 | 2025-08-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 15/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-08-19 | 2025-08-17 | 2025-08-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 45/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-08-19 | 2025-08-17 | 2025-08-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 7/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-09-14 | 2025-09-14 | 2025-09-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 34/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-09-14 | 2025-09-14 | 2025-09-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 46A/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-09-16 | 2025-09-14 | 2025-09-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 45/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-09-22 | 2025-09-21 | 2025-09-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 33/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-09-29 | 2025-09-28 | 2025-09-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 12/7 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-09-30 | 2025-09-28 | 2025-09-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 45/4 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-10-01 | 2025-09-28 | 2025-10-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 10/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-10-06 | 2025-10-05 | 2025-10-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 14/5 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-10-11 | 2025-10-05 | 2025-10-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 46A/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-10-13 | 2025-10-12 | 2025-10-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 10/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-10-13 | 2025-10-12 | 2025-10-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 46/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-10-15 | 2025-10-12 | 2025-10-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 8/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-10-23 | 2025-10-19 | 2025-10-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 9/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-10-25 | 2025-10-19 | 2025-10-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 16/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-10-26 | 2025-10-26 | 2025-10-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 46A/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-10-29 | 2025-10-26 | 2025-10-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 64/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-10-30 | 2025-10-26 | 2025-10-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 64/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-03 | 2025-11-02 | 2025-11-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 17/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-03 | 2025-11-02 | 2025-11-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 66/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-05 | 2025-11-02 | 2025-11-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 18/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-05 | 2025-11-02 | 2025-11-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 47/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-05 | 2025-11-02 | 2025-11-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 66/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-06 | 2025-11-02 | 2025-11-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 46A/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-06 | 2025-11-02 | 2025-11-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 47/7 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-06 | 2025-11-02 | 2025-11-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 66/8 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-07 | 2025-11-02 | 2025-11-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 45A/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-08 | 2025-11-02 | 2025-11-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 47/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-08 | 2025-11-02 | 2025-11-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 63/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-13 | 2025-11-09 | 2025-11-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 47/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-13 | 2025-11-09 | 2025-11-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 65/8 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-15 | 2025-11-09 | 2025-11-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 18/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-18 | 2025-11-16 | 2025-11-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 66/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-19 | 2025-11-16 | 2025-11-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 65/5 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-20 | 2025-11-16 | 2025-11-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 66/6 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-21 | 2025-11-16 | 2025-11-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 45/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-21 | 2025-11-16 | 2025-11-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 6/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-23 | 2025-11-23 | 2025-11-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 55/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-23 | 2025-11-23 | 2025-11-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 66/4 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-24 | 2025-11-23 | 2025-11-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 6/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-11-29 | 2025-11-23 | 2025-11-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 23/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-01 | 2025-11-30 | 2025-12-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 14/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-02 | 2025-11-30 | 2025-12-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 65/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-03 | 2025-11-30 | 2025-12-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 52/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-04 | 2025-11-30 | 2025-12-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 67/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-07 | 2025-12-07 | 2025-12-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 32/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-07 | 2025-12-07 | 2025-12-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 40/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-09 | 2025-12-07 | 2025-12-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 11/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-09 | 2025-12-07 | 2025-12-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 48/4 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-13 | 2025-12-07 | 2025-12-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 53/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-16 | 2025-12-14 | 2025-12-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 29/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-16 | 2025-12-14 | 2025-12-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 55/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-19 | 2025-12-14 | 2025-12-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 56/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-20 | 2025-12-14 | 2025-12-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 39/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-21 | 2025-12-21 | 2025-12-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 53B/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-22 | 2025-12-21 | 2025-12-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 25/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-26 | 2025-12-21 | 2025-12-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 27/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-27 | 2025-12-21 | 2025-12-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 68/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2025-12-30 | 2025-12-28 | 2025-12-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 30/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-01-04 | 2026-01-04 | 2026-01-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 48/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-01-09 | 2026-01-04 | 2026-01-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 52/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-01-21 | 2026-01-18 | 2026-01-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 36/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-01-24 | 2026-01-18 | 2026-01-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 48/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-01-29 | 2026-01-25 | 2026-01-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 30/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-02-01 | 2026-02-01 | 2026-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 48/5 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-02-06 | 2026-02-01 | 2026-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 26/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-02-12 | 2026-02-08 | 2026-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 27/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-02-23 | 2026-02-22 | 2026-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 31/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-02-25 | 2026-02-22 | 2026-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 37/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-02-28 | 2026-02-22 | 2026-02-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 32/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-03-14 | 2026-03-08 | 2026-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 53A/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-03-21 | 2026-03-15 | 2026-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 39/6 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-03-26 | 2026-03-22 | 2026-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 41/7 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-03-30 | 2026-03-29 | 2026-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 53B/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-03-31 | 2026-03-29 | 2026-03-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 39/10 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-04-04 | 2026-03-29 | 2026-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 28/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-04-05 | 2026-04-05 | 2026-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 48/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-04-05 | 2026-04-05 | 2026-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 65/4 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-04-08 | 2026-04-05 | 2026-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 39/11 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-04-09 | 2026-04-05 | 2026-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 35/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-04-10 | 2026-04-05 | 2026-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 41/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-04-14 | 2026-04-12 | 2026-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 5/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-04-16 | 2026-04-12 | 2026-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 4/6 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-04-18 | 2026-04-12 | 2026-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 4/4 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-04-18 | 2026-04-12 | 2026-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 54/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-04-20 | 2026-04-19 | 2026-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 4/3 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-04-25 | 2026-04-19 | 2026-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 39/9 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-04-29 | 2026-04-26 | 2026-04-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 3/1 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-05-02 | 2026-04-26 | 2026-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 4/5 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-05-04 | 2026-05-03 | 2026-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 45/2 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-05-05 | 2026-05-03 | 2026-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 50/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-05-06 | 2026-05-03 | 2026-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 4/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-05-12 | 2026-05-10 | 2026-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 3/0 | 1
TA 509 | TA 509 | ta509 |  | filename | 2026-05-18 | 2026-05-14 | 2026-05-10 | 2026-05-01 | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | detail | detail_date | 47/9 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-02-12 | 2025-02-09 | 2025-02-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 155/1 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-02-18 | 2025-02-16 | 2025-02-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 155/3 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-02-18 | 2025-02-16 | 2025-02-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 155/4 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-02-23 | 2025-02-23 | 2025-02-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 155/5 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-03-05 | 2025-03-02 | 2025-03-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 156/0 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-03-05 | 2025-03-02 | 2025-03-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 156/1 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-03-13 | 2025-03-09 | 2025-03-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 156/3 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-03-21 | 2025-03-16 | 2025-03-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 156/4 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-03-26 | 2025-03-23 | 2025-03-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 139/1 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-03-26 | 2025-03-23 | 2025-03-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 156/2 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-04-05 | 2025-03-30 | 2025-04-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 138/0 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-04-14 | 2025-04-13 | 2025-04-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 137/0 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-04-14 | 2025-04-13 | 2025-04-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 138/1 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-04-14 | 2025-04-13 | 2025-04-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 139/5 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-04-23 | 2025-04-20 | 2025-04-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 139/4 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-04-25 | 2025-04-20 | 2025-04-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 136/0 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-05-03 | 2025-04-27 | 2025-05-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 148/5 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-05-13 | 2025-05-11 | 2025-05-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 148/4 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-05-15 | 2025-05-11 | 2025-05-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 134/0 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-05-15 | 2025-05-11 | 2025-05-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 148/2 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-05-17 | 2025-05-11 | 2025-05-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 148/7 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-05-19 | 2025-05-18 | 2025-05-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 148/6 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-05-25 | 2025-05-25 | 2025-05-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 143/1 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-05-30 | 2025-05-25 | 2025-05-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 143/2 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-06-01 | 2025-06-01 | 2025-06-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 144/0 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-07-23 | 2025-07-20 | 2025-07-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 141/0 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-08-31 | 2025-08-31 | 2025-08-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 133/2 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-09-10 | 2025-09-07 | 2025-09-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 140/2 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-09-19 | 2025-09-14 | 2025-09-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 138/2 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-09-21 | 2025-09-21 | 2025-09-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 141/1 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-09-24 | 2025-09-21 | 2025-09-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 140/1 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-09-25 | 2025-09-21 | 2025-09-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 145/0 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-10-15 | 2025-10-12 | 2025-10-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 139/2 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-11-11 | 2025-11-09 | 2025-11-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 135/0 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-11-11 | 2025-11-09 | 2025-11-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 145/1 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-11-15 | 2025-11-09 | 2025-11-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 145/5 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-11-15 | 2025-11-09 | 2025-11-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 192/11 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-11-18 | 2025-11-16 | 2025-11-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 138/3 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-11-27 | 2025-11-23 | 2025-11-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 148/3 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 141/2 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 143/0 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-12-01 | 2025-11-30 | 2025-12-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 145/3 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-12-01 | 2025-11-30 | 2025-12-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 192/13 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-12-10 | 2025-12-07 | 2025-12-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 145/4 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-12-10 | 2025-12-07 | 2025-12-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 146/1 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-12-15 | 2025-12-14 | 2025-12-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 146A/0 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-12-16 | 2025-12-14 | 2025-12-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 140/0 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-12-21 | 2025-12-21 | 2025-12-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 146/3 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2025-12-21 | 2025-12-21 | 2025-12-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 192/10 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-01-01 | 2025-12-28 | 2026-01-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 147/2 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-01-05 | 2026-01-04 | 2026-01-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 186/1 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-01-06 | 2026-01-04 | 2026-01-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 146/0 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-01-08 | 2026-01-04 | 2026-01-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 147/1 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-01-09 | 2026-01-04 | 2026-01-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 192/7 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-01-16 | 2026-01-11 | 2026-01-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 192/12 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-01-27 | 2026-01-25 | 2026-01-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 142/0 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-02-01 | 2026-02-01 | 2026-02-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 148/0 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-02-01 | 2026-02-01 | 2026-02-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 194/1 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-02-02 | 2026-02-01 | 2026-02-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 146A/1 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-02-03 | 2026-02-01 | 2026-02-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 148/1 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-02-16 | 2026-02-15 | 2026-02-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 157B/0 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-02-17 | 2026-02-15 | 2026-02-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 146/2 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-02-17 | 2026-02-15 | 2026-02-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 157A/0 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-03-14 | 2026-03-08 | 2026-03-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 157/2 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-04-01 | 2026-03-29 | 2026-04-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 139/0 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-04-02 | 2026-03-29 | 2026-04-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 192/9 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-04-04 | 2026-03-29 | 2026-04-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 139/3 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-04-04 | 2026-03-29 | 2026-04-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 153/0 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-04-08 | 2026-04-05 | 2026-04-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 193/2 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-04-12 | 2026-04-12 | 2026-04-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 193/1 | 1
TA 510 | TA 510 - Pile | ta510pile | Pile | config | 2026-05-20 | 2026-04-13 | 2026-04-12 | 2026-04-01 | TA 510 - DPR - 2026-05-20.xlsx | Pile Foundation | Pile Foundation | detail | detail_date | 131/1 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-04-14 | 2026-04-12 | 2026-04-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 193/5 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-04-19 | 2026-04-19 | 2026-04-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 193/0 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-04-19 | 2026-04-19 | 2026-04-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 193/4 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-04-22 | 2026-04-19 | 2026-04-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 150/2 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-04-22 | 2026-04-19 | 2026-04-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 157B/1 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-04-29 | 2026-04-26 | 2026-04-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 192/8 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-04-30 | 2026-04-26 | 2026-04-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 194/0 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-05-07 | 2026-05-03 | 2026-05-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 167/2 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-05-09 | 2026-05-03 | 2026-05-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 133/0 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-05-11 | 2026-05-10 | 2026-05-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 167/3 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-05-17 | 2026-05-17 | 2026-05-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 167/4 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-05-19 | 2026-05-17 | 2026-05-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 133/1 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-05-20 | 2026-05-17 | 2026-05-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 155/2 | 1
TA 510 | TA 510 - FDN | ta510fdn | FDN | config | 2026-05-20 | 2026-05-20 | 2026-05-17 | 2026-05-01 | TA 510 - DPR - 2026-05-20.xlsx | FDN | FDN | detail | detail_date | 167/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-02-23 | 2025-02-23 | 2025-02-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-02-26 | 2025-02-23 | 2025-02-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-02-28 | 2025-02-23 | 2025-02-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/6 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-05 | 2025-03-02 | 2025-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-05 | 2025-03-02 | 2025-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/5 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-07 | 2025-03-02 | 2025-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 12/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-10 | 2025-03-09 | 2025-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 12/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-10 | 2025-03-09 | 2025-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 12/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-10 | 2025-03-09 | 2025-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/4 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-10 | 2025-03-09 | 2025-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/8 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-13 | 2025-03-09 | 2025-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 12/4 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-15 | 2025-03-09 | 2025-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/7 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-17 | 2025-03-16 | 2025-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/5 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-17 | 2025-03-16 | 2025-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/6 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-18 | 2025-03-16 | 2025-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/4 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-20 | 2025-03-16 | 2025-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/8 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-21 | 2025-03-16 | 2025-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-21 | 2025-03-16 | 2025-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/5 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-23 | 2025-03-23 | 2025-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 19/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-24 | 2025-03-23 | 2025-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 19/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-24 | 2025-03-23 | 2025-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/7 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-25 | 2025-03-23 | 2025-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 19/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-26 | 2025-03-23 | 2025-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/10 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-26 | 2025-03-23 | 2025-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/7 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-27 | 2025-03-23 | 2025-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 19/6 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-28 | 2025-03-23 | 2025-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 19/4 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-30 | 2025-03-30 | 2025-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 19/7 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-30 | 2025-03-30 | 2025-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-03-31 | 2025-03-30 | 2025-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-01 | 2025-03-30 | 2025-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/8 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-02 | 2025-03-30 | 2025-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/9 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-03 | 2025-03-30 | 2025-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-04 | 2025-03-30 | 2025-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/5 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-06 | 2025-04-06 | 2025-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/9 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-07 | 2025-04-06 | 2025-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/6 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-10 | 2025-04-06 | 2025-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-11 | 2025-04-06 | 2025-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/11 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-13 | 2025-04-13 | 2025-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/5 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-13 | 2025-04-13 | 2025-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/4 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-15 | 2025-04-13 | 2025-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-15 | 2025-04-13 | 2025-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/4 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-16 | 2025-04-13 | 2025-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/10 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-19 | 2025-04-13 | 2025-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 19/5 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-19 | 2025-04-13 | 2025-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/7 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-21 | 2025-04-20 | 2025-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/4 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-23 | 2025-04-20 | 2025-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/8 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-24 | 2025-04-20 | 2025-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 28/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-25 | 2025-04-20 | 2025-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/6 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-26 | 2025-04-20 | 2025-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/10 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-28 | 2025-04-27 | 2025-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 28/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-28 | 2025-04-27 | 2025-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-30 | 2025-04-27 | 2025-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 23/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-04-30 | 2025-04-27 | 2025-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/12 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-04 | 2025-05-04 | 2025-05-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 23/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-04 | 2025-05-04 | 2025-05-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/11 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-04 | 2025-05-04 | 2025-05-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-07 | 2025-05-04 | 2025-05-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/13 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-09 | 2025-05-04 | 2025-05-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/14 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-10 | 2025-05-04 | 2025-05-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-11 | 2025-05-11 | 2025-05-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/18 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-12 | 2025-05-11 | 2025-05-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 11/4 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-14 | 2025-05-11 | 2025-05-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-15 | 2025-05-11 | 2025-05-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-17 | 2025-05-11 | 2025-05-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-17 | 2025-05-11 | 2025-05-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-18 | 2025-05-18 | 2025-05-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/4 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-19 | 2025-05-18 | 2025-05-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 28/4 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-19 | 2025-05-18 | 2025-05-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/8 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-20 | 2025-05-18 | 2025-05-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/5 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-21 | 2025-05-18 | 2025-05-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 11/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-23 | 2025-05-18 | 2025-05-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/6 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-23 | 2025-05-18 | 2025-05-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/10 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-25 | 2025-05-25 | 2025-05-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-26 | 2025-05-25 | 2025-05-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 11/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-26 | 2025-05-25 | 2025-05-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/7 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-05-27 | 2025-05-25 | 2025-05-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 28/7 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-01 | 2025-06-01 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 28/6 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-01 | 2025-06-01 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-04 | 2025-06-01 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 11/5 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-04 | 2025-06-01 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/8 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-06 | 2025-06-01 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 28/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-07 | 2025-06-01 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/12 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-08 | 2025-06-08 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/9 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-10 | 2025-06-08 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/11 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-11 | 2025-06-08 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 28/5 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-11 | 2025-06-08 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/13 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-11 | 2025-06-08 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/11 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-11 | 2025-06-08 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/6 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-16 | 2025-06-15 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/5 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-16 | 2025-06-15 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/5 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-17 | 2025-06-15 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 27/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-17 | 2025-06-15 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/9 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-18 | 2025-06-15 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/9 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-18 | 2025-06-15 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/4 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-20 | 2025-06-15 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 27/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-22 | 2025-06-22 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-23 | 2025-06-22 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-26 | 2025-06-22 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 19/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-26 | 2025-06-22 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-26 | 2025-06-22 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/14 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-26 | 2025-06-22 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-30 | 2025-06-29 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-06-30 | 2025-06-29 | 2025-06-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/4 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-01 | 2025-06-29 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 41/6 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-03 | 2025-06-29 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-03 | 2025-06-29 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-04 | 2025-06-29 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 12/5 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-04 | 2025-06-29 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/7 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-05 | 2025-06-29 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/13 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-05 | 2025-06-29 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 41/5 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-07 | 2025-07-06 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 11/6 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-09 | 2025-07-06 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-09 | 2025-07-06 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/11 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-09 | 2025-07-06 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 41/4 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-10 | 2025-07-06 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 16/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-10 | 2025-07-06 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/6 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-12 | 2025-07-06 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/4 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-13 | 2025-07-13 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/12 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-14 | 2025-07-13 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 41/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-15 | 2025-07-13 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 1A/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-15 | 2025-07-13 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/8 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-16 | 2025-07-13 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/10 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-17 | 2025-07-13 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/26 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-17 | 2025-07-13 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-18 | 2025-07-13 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/9 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-18 | 2025-07-13 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 41/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-19 | 2025-07-13 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/5 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-20 | 2025-07-20 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 1A/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-20 | 2025-07-20 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/9 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-20 | 2025-07-20 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 41/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-21 | 2025-07-20 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/14 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-22 | 2025-07-20 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 1A/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-23 | 2025-07-20 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/15 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-25 | 2025-07-20 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/10 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-25 | 2025-07-20 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/11 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-25 | 2025-07-20 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-26 | 2025-07-20 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/8 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-29 | 2025-07-27 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-29 | 2025-07-27 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/24 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-29 | 2025-07-27 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-30 | 2025-07-27 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-07-31 | 2025-07-27 | 2025-07-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/20 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-01 | 2025-07-27 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-01 | 2025-07-27 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/12 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-01 | 2025-07-27 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/19 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-02 | 2025-07-27 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/7 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-03 | 2025-08-03 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/4 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-03 | 2025-08-03 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3A/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-03 | 2025-08-03 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/4 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-05 | 2025-08-03 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/20 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-05 | 2025-08-03 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/16 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-06 | 2025-08-03 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/6 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-07 | 2025-08-03 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/15 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-07 | 2025-08-03 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/21 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-07 | 2025-08-03 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/23 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-07 | 2025-08-03 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3A/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-08 | 2025-08-03 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/5 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-13 | 2025-08-10 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-13 | 2025-08-10 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-14 | 2025-08-10 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/5 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-14 | 2025-08-10 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3A/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-21 | 2025-08-17 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-22 | 2025-08-17 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/16 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-22 | 2025-08-17 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/22 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-23 | 2025-08-17 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-28 | 2025-08-24 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 41/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-28 | 2025-08-24 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-08-29 | 2025-08-24 | 2025-08-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/7 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-03 | 2025-08-31 | 2025-09-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/18 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-03 | 2025-08-31 | 2025-09-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36/9 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-03 | 2025-08-31 | 2025-09-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/5 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-06 | 2025-08-31 | 2025-09-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36/8 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-06 | 2025-08-31 | 2025-09-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/6 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-06 | 2025-08-31 | 2025-09-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-09 | 2025-09-07 | 2025-09-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-11 | 2025-09-07 | 2025-09-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/14 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-11 | 2025-09-07 | 2025-09-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36/7 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-16 | 2025-09-14 | 2025-09-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36/6 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-16 | 2025-09-14 | 2025-09-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/5 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-16 | 2025-09-14 | 2025-09-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/6 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-16 | 2025-09-14 | 2025-09-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-21 | 2025-09-21 | 2025-09-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36/5 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-22 | 2025-09-21 | 2025-09-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/8 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-23 | 2025-09-21 | 2025-09-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 13/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-25 | 2025-09-21 | 2025-09-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/9 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-26 | 2025-09-21 | 2025-09-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36/4 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-09-29 | 2025-09-28 | 2025-09-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-01 | 2025-09-28 | 2025-10-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/19 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-01 | 2025-09-28 | 2025-10-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/10 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-04 | 2025-09-28 | 2025-10-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/9 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-04 | 2025-09-28 | 2025-10-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-09 | 2025-10-05 | 2025-10-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/7 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-12 | 2025-10-12 | 2025-10-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/4 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-12 | 2025-10-12 | 2025-10-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/10 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-12 | 2025-10-12 | 2025-10-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-16 | 2025-10-12 | 2025-10-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-17 | 2025-10-12 | 2025-10-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-17 | 2025-10-12 | 2025-10-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-18 | 2025-10-12 | 2025-10-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-19 | 2025-10-19 | 2025-10-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/17 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-23 | 2025-10-19 | 2025-10-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-25 | 2025-10-19 | 2025-10-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/13 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-25 | 2025-10-19 | 2025-10-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-26 | 2025-10-26 | 2025-10-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/18 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-26 | 2025-10-26 | 2025-10-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/4 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-27 | 2025-10-26 | 2025-10-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 12/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-28 | 2025-10-26 | 2025-10-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-30 | 2025-10-26 | 2025-10-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-30 | 2025-10-26 | 2025-10-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-30 | 2025-10-26 | 2025-10-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-10-30 | 2025-10-26 | 2025-10-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/4 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-01 | 2025-10-26 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/21 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-01 | 2025-10-26 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-02 | 2025-11-02 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/4 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-03 | 2025-11-02 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 37/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-04 | 2025-11-02 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/17 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-05 | 2025-11-02 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 11/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-06 | 2025-11-02 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/5 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-07 | 2025-11-02 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-09 | 2025-11-09 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/17 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-09 | 2025-11-09 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/6 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-10 | 2025-11-09 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 40/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-11 | 2025-11-09 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 16/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-12 | 2025-11-09 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/7 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-12 | 2025-11-09 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/25 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-13 | 2025-11-09 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-14 | 2025-11-09 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 39/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-16 | 2025-11-16 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 11/8 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-16 | 2025-11-16 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-17 | 2025-11-16 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 31/27 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-18 | 2025-11-16 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-19 | 2025-11-16 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3A/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-21 | 2025-11-16 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20/7 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-22 | 2025-11-16 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-24 | 2025-11-23 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/16 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-24 | 2025-11-23 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 38/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-25 | 2025-11-23 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-28 | 2025-11-23 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/4 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-29 | 2025-11-23 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-11-29 | 2025-11-23 | 2025-11-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/8 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-01 | 2025-11-30 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 21/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-01 | 2025-11-30 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-02 | 2025-11-30 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2A/5 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-02 | 2025-11-30 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-02 | 2025-11-30 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-03 | 2025-11-30 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/5 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-04 | 2025-11-30 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/5 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-05 | 2025-11-30 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2A/4 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-06 | 2025-11-30 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/6 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-07 | 2025-12-07 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/4 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-07 | 2025-12-07 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/4 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-08 | 2025-12-07 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 30/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-09 | 2025-12-07 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2A/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-10 | 2025-12-07 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/6 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-12 | 2025-12-07 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2A/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-12 | 2025-12-07 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-13 | 2025-12-07 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 20A/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-14 | 2025-12-14 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/8 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-14 | 2025-12-14 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-16 | 2025-12-14 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2A/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-16 | 2025-12-14 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/7 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-17 | 2025-12-14 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 23/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-17 | 2025-12-14 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 28/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-17 | 2025-12-14 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-17 | 2025-12-14 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/7 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-19 | 2025-12-14 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/6 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-21 | 2025-12-21 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 35/9 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-23 | 2025-12-21 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/4 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-25 | 2025-12-21 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2A/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-26 | 2025-12-21 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-26 | 2025-12-21 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/7 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-27 | 2025-12-21 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 22/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-27 | 2025-12-21 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 27/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-30 | 2025-12-28 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/6 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-30 | 2025-12-28 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 36/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2025-12-31 | 2025-12-28 | 2025-12-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 29/22 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-01-03 | 2025-12-28 | 2026-01-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-01-04 | 2026-01-04 | 2026-01-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 23/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-01-05 | 2026-01-04 | 2026-01-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33A/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-01-11 | 2026-01-11 | 2026-01-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-01-11 | 2026-01-11 | 2026-01-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 42/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-01-12 | 2026-01-11 | 2026-01-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 13/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-01-13 | 2026-01-11 | 2026-01-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-01-16 | 2026-01-11 | 2026-01-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 43/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-01-20 | 2026-01-18 | 2026-01-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-01-21 | 2026-01-18 | 2026-01-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-01-31 | 2026-01-25 | 2026-01-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-02-02 | 2026-02-01 | 2026-02-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-02-07 | 2026-02-01 | 2026-02-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 16/3 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-02-19 | 2026-02-15 | 2026-02-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/8 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-02-22 | 2026-02-22 | 2026-02-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/9 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-03-03 | 2026-03-01 | 2026-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 33/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-03-09 | 2026-03-08 | 2026-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 44/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-03-15 | 2026-03-15 | 2026-03-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 32/2 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-04-03 | 2026-03-29 | 2026-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 17/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-04-08 | 2026-04-05 | 2026-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 47/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-04-12 | 2026-04-12 | 2026-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 18/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-04-15 | 2026-04-12 | 2026-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 44/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-04-24 | 2026-04-19 | 2026-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 45/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-04-24 | 2026-04-19 | 2026-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 46/0 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-04-29 | 2026-04-26 | 2026-04-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 34/1 | 1
TA 512 | TA 512 | ta512 |  | filename | 2026-05-20 | 2026-05-09 | 2026-05-03 | 2026-05-01 | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 11/7 | 1
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-03-22 | 2025-03-16 | 2025-03-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 25/1 | 1
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-03-25 | 2025-03-23 | 2025-03-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 25/2 | 1
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-03-30 | 2025-03-30 | 2025-03-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 24/2 | 1
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-04-02 | 2025-03-30 | 2025-04-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 24/1 | 1
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-04-04 | 2025-03-30 | 2025-04-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 26/2 | 1
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-04-09 | 2025-04-06 | 2025-04-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 30/2 | 1
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-04-12 | 2025-04-06 | 2025-04-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 23/6 | 1
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-04-14 | 2025-04-13 | 2025-04-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 23/5 | 1
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-04-14 | 2025-04-13 | 2025-04-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 31/1 | 1
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-04-17 | 2025-04-13 | 2025-04-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 37/1 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-04-21 | 2025-04-20 | 2025-04-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 30/3 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-04-22 | 2025-04-20 | 2025-04-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 30/1 | 1
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-04-23 | 2025-04-20 | 2025-04-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 31/2 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-04-24 | 2025-04-20 | 2025-04-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 30/2 | 1
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-04-26 | 2025-04-20 | 2025-04-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 24/3 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-04-29 | 2025-04-27 | 2025-04-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 29/5 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-01 | 2025-04-27 | 2025-05-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 29/2 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-02 | 2025-04-27 | 2025-05-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 29/4 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-03 | 2025-04-27 | 2025-05-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 29/1 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-03 | 2025-04-27 | 2025-05-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 29/3 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-05 | 2025-05-04 | 2025-05-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 52/5 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-06 | 2025-05-04 | 2025-05-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 55/3 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-07 | 2025-05-04 | 2025-05-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 28/3 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-07 | 2025-05-04 | 2025-05-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 28/4 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-09 | 2025-05-04 | 2025-05-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 28/2 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-11 | 2025-05-11 | 2025-05-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 55/7 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-11 | 2025-05-11 | 2025-05-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 64/2 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-11 | 2025-05-11 | 2025-05-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 64/5 | 1
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-05-16 | 2025-05-11 | 2025-05-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 24/4 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-16 | 2025-05-11 | 2025-05-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 3/5 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-20 | 2025-05-18 | 2025-05-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 3/6 | 1
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-05-21 | 2025-05-18 | 2025-05-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 23/3 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-24 | 2025-05-18 | 2025-05-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 3/10 | 1
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-05-25 | 2025-05-25 | 2025-05-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 32B/1 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-30 | 2025-05-25 | 2025-05-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 21/6 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-05-30 | 2025-05-25 | 2025-05-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 21/7 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-06-03 | 2025-06-01 | 2025-06-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 23/1 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-06-05 | 2025-06-01 | 2025-06-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 23/3 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-06-07 | 2025-06-01 | 2025-06-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 23/2 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-06-11 | 2025-06-08 | 2025-06-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 23/4 | 1
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-06-20 | 2025-06-15 | 2025-06-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 18/4 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-06-20 | 2025-06-15 | 2025-06-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 14/4 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-06-21 | 2025-06-15 | 2025-06-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 56/1 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-06-28 | 2025-06-22 | 2025-06-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 26/1 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-07-02 | 2025-06-29 | 2025-07-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 14/3 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-07-02 | 2025-06-29 | 2025-07-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 56/2 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-07-05 | 2025-06-29 | 2025-07-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 56/4 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-07-07 | 2025-07-06 | 2025-07-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 14/2 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-07-15 | 2025-07-13 | 2025-07-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 15B/4 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-07-16 | 2025-07-13 | 2025-07-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 55/5 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-07-20 | 2025-07-20 | 2025-07-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 55/0 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-07-21 | 2025-07-20 | 2025-07-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 54/6 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-07-24 | 2025-07-20 | 2025-07-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 55/6 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-07-26 | 2025-07-20 | 2025-07-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 36/3 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-08-19 | 2025-08-17 | 2025-08-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 29/0 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-08-19 | 2025-08-17 | 2025-08-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 56/3 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-08-21 | 2025-08-17 | 2025-08-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 36/4 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-08-21 | 2025-08-17 | 2025-08-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 54/5 | 1
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-09-10 | 2025-09-07 | 2025-09-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 27/0 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-09-10 | 2025-09-07 | 2025-09-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 30/0 | 1
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-09-13 | 2025-09-07 | 2025-09-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 26/0 | 1
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-09-15 | 2025-09-14 | 2025-09-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 25/0 | 1
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-09-19 | 2025-09-14 | 2025-09-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 24/0 | 1
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-09-25 | 2025-09-21 | 2025-09-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 19/0 | 1
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-09-30 | 2025-09-28 | 2025-09-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 28/0 | 1
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2025-10-04 | 2025-09-28 | 2025-10-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 18/0 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-10-24 | 2025-10-19 | 2025-10-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 54/3 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-11-03 | 2025-11-02 | 2025-11-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 55/3 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-11-14 | 2025-11-09 | 2025-11-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 54/7 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 51/4 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-12-06 | 2025-11-30 | 2025-12-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 51/2 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-12-14 | 2025-12-14 | 2025-12-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 52/4 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2025-12-19 | 2025-12-14 | 2025-12-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 51/5 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2026-01-24 | 2026-01-18 | 2026-01-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 54/8 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2026-02-17 | 2026-02-15 | 2026-02-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 52/3 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2026-02-27 | 2026-02-22 | 2026-02-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 55/1 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2026-03-28 | 2026-03-22 | 2026-03-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 55/2 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2026-04-22 | 2026-04-19 | 2026-04-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 52/2 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2026-04-24 | 2026-04-19 | 2026-04-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 52/0 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2026-04-27 | 2026-04-26 | 2026-04-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 55/4 | 1
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2026-05-04 | 2026-05-03 | 2026-05-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 30/0 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2026-05-04 | 2026-05-03 | 2026-05-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 52/1 | 1
TA 513 | TA 513 - S-F | ta513sf | S-F | config | 2026-05-19 | 2026-05-17 | 2026-05-17 | 2026-05-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-F | FDN S-F | detail | detail_date | 28/1 | 1
TA 513 | TA 513 - S-P | ta513sp | S-P | config | 2026-05-19 | 2026-05-19 | 2026-05-17 | 2026-05-01 | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P | FDN S-P | detail | detail_date | 64/3 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-05-03 | 2025-04-27 | 2025-05-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 66/0 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-08-07 | 2025-08-03 | 2025-08-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 81/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-08-22 | 2025-08-17 | 2025-08-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 82/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-09-13 | 2025-09-07 | 2025-09-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 81/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-09-18 | 2025-09-14 | 2025-09-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 80/5 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-10-10 | 2025-10-05 | 2025-10-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 80/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-10-19 | 2025-10-19 | 2025-10-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 59/5 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-10-19 | 2025-10-19 | 2025-10-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 84/3 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-10-21 | 2025-10-19 | 2025-10-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 59/4 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-10-24 | 2025-10-19 | 2025-10-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 84/4 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-10-25 | 2025-10-19 | 2025-10-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 60/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-10-27 | 2025-10-26 | 2025-10-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 80/4 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-10-31 | 2025-10-26 | 2025-10-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/4 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-11-05 | 2025-11-02 | 2025-11-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/10 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-11-08 | 2025-11-02 | 2025-11-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 59/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-11-09 | 2025-11-09 | 2025-11-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/7 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-11-13 | 2025-11-09 | 2025-11-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/8 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-11-15 | 2025-11-09 | 2025-11-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 60/3 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-11-19 | 2025-11-16 | 2025-11-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/3 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-11-23 | 2025-11-23 | 2025-11-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 60/8 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-11-25 | 2025-11-23 | 2025-11-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-11-29 | 2025-11-23 | 2025-11-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 59/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-03 | 2025-11-30 | 2025-12-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 58/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-08 | 2025-12-07 | 2025-12-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 58/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-12 | 2025-12-07 | 2025-12-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/6 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-14 | 2025-12-14 | 2025-12-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 58/3 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-15 | 2025-12-14 | 2025-12-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 99/7 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-18 | 2025-12-14 | 2025-12-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 73/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-19 | 2025-12-14 | 2025-12-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/3 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-20 | 2025-12-14 | 2025-12-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 59/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-20 | 2025-12-14 | 2025-12-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 99/6 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-23 | 2025-12-21 | 2025-12-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 99/9 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-24 | 2025-12-21 | 2025-12-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-24 | 2025-12-21 | 2025-12-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 73/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-25 | 2025-12-21 | 2025-12-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 79/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-26 | 2025-12-21 | 2025-12-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 99/8 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-27 | 2025-12-21 | 2025-12-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-27 | 2025-12-21 | 2025-12-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 59/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-29 | 2025-12-28 | 2025-12-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 99/10 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-30 | 2025-12-28 | 2025-12-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 79/3 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-31 | 2025-12-28 | 2025-12-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 55/3 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-31 | 2025-12-28 | 2025-12-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/3 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-31 | 2025-12-28 | 2025-12-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 84/6 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-31 | 2025-12-28 | 2025-12-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 94/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2025-12-31 | 2025-12-28 | 2025-12-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 99/11 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-05 | 2026-01-04 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 79/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-06 | 2026-01-04 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/4 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-06 | 2026-01-04 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 99/12 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-08 | 2026-01-04 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-08 | 2026-01-04 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 84/5 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-10 | 2026-01-04 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/9 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-10 | 2026-01-04 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 58/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-10 | 2026-01-04 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 58/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-12 | 2026-01-11 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-12 | 2026-01-11 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 84/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-13 | 2026-01-11 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-14 | 2026-01-11 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/3 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-14 | 2026-01-11 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 58/3 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-14 | 2026-01-11 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 83/0 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-16 | 2026-01-11 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/7 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-16 | 2026-01-11 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/4 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-16 | 2026-01-11 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 82/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-17 | 2026-01-11 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/6 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-20 | 2026-01-18 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 80/5 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-21 | 2026-01-18 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/8 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-21 | 2026-01-18 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 59/4 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-21 | 2026-01-18 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/7 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-21 | 2026-01-18 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 84/3 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-21 | 2026-01-18 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 99/11 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-22 | 2026-01-18 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-22 | 2026-01-18 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 85/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-23 | 2026-01-18 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-24 | 2026-01-18 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/4 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-24 | 2026-01-18 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 84/4 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-25 | 2026-01-25 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 80/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-26 | 2026-01-25 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 102/4 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-26 | 2026-01-25 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 59/0 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-26 | 2026-01-25 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 84/0 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-27 | 2026-01-25 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/5 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-27 | 2026-01-25 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 59/5 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-27 | 2026-01-25 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 99/10 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-28 | 2026-01-25 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-28 | 2026-01-25 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 55/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-28 | 2026-01-25 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 84/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-29 | 2026-01-25 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 99/7 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-30 | 2026-01-25 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 53/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-30 | 2026-01-25 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/10 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-31 | 2026-01-25 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-31 | 2026-01-25 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/0 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-31 | 2026-01-25 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/3 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-31 | 2026-01-25 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 102/5 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-31 | 2026-01-25 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 52/0 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-01-31 | 2026-01-25 | 2026-01-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 79/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-02 | 2026-02-01 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 60/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-03 | 2026-02-01 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 85/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-03 | 2026-02-01 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 99/8 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-04 | 2026-02-01 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 79/3 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-05 | 2026-02-01 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-05 | 2026-02-01 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 51/9 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-05 | 2026-02-01 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 84/5 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-06 | 2026-02-01 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 78/3 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-08 | 2026-02-08 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 102/3 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-08 | 2026-02-08 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 53/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-09 | 2026-02-08 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/8 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-09 | 2026-02-08 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 99/6 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-10 | 2026-02-08 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/9 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-10 | 2026-02-08 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 84/0 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-11 | 2026-02-08 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 102/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-11 | 2026-02-08 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/6 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-12 | 2026-02-08 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-12 | 2026-02-08 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 50/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-13 | 2026-02-08 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/9 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-13 | 2026-02-08 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 81/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-14 | 2026-02-08 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/5 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-14 | 2026-02-08 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 102/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-15 | 2026-02-15 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 83/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-16 | 2026-02-15 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/3 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-16 | 2026-02-15 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 99/9 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-17 | 2026-02-15 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 102/4 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-17 | 2026-02-15 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 50/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-17 | 2026-02-15 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 55/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-19 | 2026-02-15 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 102/5 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-20 | 2026-02-15 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-20 | 2026-02-15 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/7 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-21 | 2026-02-15 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 52/0 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-22 | 2026-02-22 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/6 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-22 | 2026-02-22 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 102/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-24 | 2026-02-22 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/5 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-24 | 2026-02-22 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/6 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-24 | 2026-02-22 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 102/3 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-25 | 2026-02-22 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 53/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-25 | 2026-02-22 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 85/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-26 | 2026-02-22 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/8 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-26 | 2026-02-22 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-27 | 2026-02-22 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 102/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-28 | 2026-02-22 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/7 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-28 | 2026-02-22 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/7 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-28 | 2026-02-22 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 53/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-02-28 | 2026-02-22 | 2026-02-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 77/9 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-02 | 2026-03-01 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/5 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-03 | 2026-03-01 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/0 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-03 | 2026-03-01 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 89/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-05 | 2026-03-01 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 51/9 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-06 | 2026-03-01 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 53/4 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-07 | 2026-03-01 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/3 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-08 | 2026-03-08 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 53/5 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-09 | 2026-03-08 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 83/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-11 | 2026-03-08 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 49/10 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-11 | 2026-03-08 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 85/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-13 | 2026-03-08 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 51/7 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-14 | 2026-03-08 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 49/11 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-14 | 2026-03-08 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 51/8 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-16 | 2026-03-15 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/6 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-16 | 2026-03-15 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/6 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-17 | 2026-03-15 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 51/10 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-18 | 2026-03-15 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/0 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-18 | 2026-03-15 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 55/3 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-18 | 2026-03-15 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 90/0 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-19 | 2026-03-15 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 51/6 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-20 | 2026-03-15 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 101/7 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-22 | 2026-03-22 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 52/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-23 | 2026-03-22 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/7 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-25 | 2026-03-22 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 50/3 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-25 | 2026-03-22 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 56/4 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-27 | 2026-03-22 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 51/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-29 | 2026-03-29 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/4 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-03-31 | 2026-03-29 | 2026-03-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 53/3 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-01 | 2026-03-29 | 2026-04-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 53/4 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-04 | 2026-03-29 | 2026-04-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/8 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-06 | 2026-04-05 | 2026-04-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 60/0 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-07 | 2026-04-05 | 2026-04-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 53/5 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-11 | 2026-04-05 | 2026-04-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 70/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-12 | 2026-04-12 | 2026-04-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 100/0 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-13 | 2026-04-12 | 2026-04-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 53/0 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-13 | 2026-04-12 | 2026-04-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 70/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-16 | 2026-04-12 | 2026-04-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 50/0 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-16 | 2026-04-12 | 2026-04-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 70/4 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-18 | 2026-04-12 | 2026-04-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 70/3 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-21 | 2026-04-19 | 2026-04-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 66/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-23 | 2026-04-19 | 2026-04-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 49/9 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-26 | 2026-04-26 | 2026-04-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 67/0 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-29 | 2026-04-26 | 2026-04-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 65/3 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-04-30 | 2026-04-26 | 2026-04-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 49/8 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-05-05 | 2026-05-03 | 2026-05-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 67/1 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-05-10 | 2026-05-10 | 2026-05-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 48/7 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-05-13 | 2026-05-10 | 2026-05-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 69/0 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-05-16 | 2026-05-10 | 2026-05-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 69/2 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-05-18 | 2026-05-17 | 2026-05-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 60/0 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-05-19 | 2026-05-17 | 2026-05-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 48/3 | 1
TA 601 | TA 601 | ta601 |  | filename | 2026-05-20 | 2026-05-20 | 2026-05-17 | 2026-05-01 | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | detail | detail_date | 69/1 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-09-15 | 2025-09-14 | 2025-09-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 125/2 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-10-03 | 2025-09-28 | 2025-10-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 125/3 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-10-07 | 2025-10-05 | 2025-10-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 123/1 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-10-08 | 2025-10-05 | 2025-10-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 124/1 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-10-15 | 2025-10-12 | 2025-10-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 124/2 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-10-16 | 2025-10-12 | 2025-10-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 121/7 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-10-19 | 2025-10-19 | 2025-10-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 121/2 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-10-19 | 2025-10-19 | 2025-10-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 123/3 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-10-25 | 2025-10-19 | 2025-10-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 122/2 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-10-28 | 2025-10-26 | 2025-10-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 126/5 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-01 | 2025-10-26 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 116/1 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-01 | 2025-10-26 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 126/4 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-03 | 2025-11-02 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 116/2 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-04 | 2025-11-02 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 124/3 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-06 | 2025-11-02 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 123/4 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-06 | 2025-11-02 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 126/3 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-08 | 2025-11-02 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 130/1 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-09 | 2025-11-09 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 111/1 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-11 | 2025-11-09 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 126/9 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-13 | 2025-11-09 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 123/2 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-14 | 2025-11-09 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 111/2 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-14 | 2025-11-09 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 126/10 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-15 | 2025-11-09 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 121/6 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-16 | 2025-11-16 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 121/1 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-19 | 2025-11-16 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 111/3 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-19 | 2025-11-16 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 130/3 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-20 | 2025-11-16 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 103/2 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-21 | 2025-11-16 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 124/4 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-21 | 2025-11-16 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 126/2 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-22 | 2025-11-16 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 121/4 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-23 | 2025-11-23 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 111/4 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-24 | 2025-11-23 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 103/3 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-24 | 2025-11-23 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 134/2 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-28 | 2025-11-23 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 103/1 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-28 | 2025-11-23 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 111/5 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-28 | 2025-11-23 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 134/3 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 102/7 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 110/2 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 121/5 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 134/5 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-03 | 2025-11-30 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 110/1 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-03 | 2025-11-30 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 134/4 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-06 | 2025-11-30 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 109/1 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-06 | 2025-11-30 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 134/6 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-06 | 2025-11-30 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 99/1 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-07 | 2025-12-07 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 102/9 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-07 | 2025-12-07 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 109/10 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-07 | 2025-12-07 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 134/9 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-08 | 2025-12-07 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 134/7 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-10 | 2025-12-07 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 136/2 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-11 | 2025-12-07 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 110/3 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-12 | 2025-12-07 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 109/11 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-12 | 2025-12-07 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 109/2 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-12 | 2025-12-07 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 136/7 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-13 | 2025-12-07 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 99/2 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-15 | 2025-12-14 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 102/8 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-16 | 2025-12-14 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 108/7 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-16 | 2025-12-14 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 136/8 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-17 | 2025-12-14 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 134/8 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-17 | 2025-12-14 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 136/5 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-19 | 2025-12-14 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 110/4 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-19 | 2025-12-14 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 136/9 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-20 | 2025-12-14 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 109/7 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-22 | 2025-12-21 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 108/5 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-22 | 2025-12-21 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 136/6 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-24 | 2025-12-21 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 109/9 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-24 | 2025-12-21 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 139/3 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-24 | 2025-12-21 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 89/9 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-26 | 2025-12-21 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 107/2 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-26 | 2025-12-21 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 108/6 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-27 | 2025-12-21 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 109/6 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-27 | 2025-12-21 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 130/2 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-28 | 2025-12-28 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 89/8 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-29 | 2025-12-28 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 136/1 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-30 | 2025-12-28 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 109/5 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-30 | 2025-12-28 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 139/2 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2025-12-30 | 2025-12-28 | 2025-12-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 89/7 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-03 | 2025-12-28 | 2026-01-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 107/1 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-04 | 2026-01-04 | 2026-01-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 89/6 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-07 | 2026-01-04 | 2026-01-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 129A/1 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-09 | 2026-01-04 | 2026-01-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 139/5 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-10 | 2026-01-04 | 2026-01-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 89/5 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-11 | 2026-01-11 | 2026-01-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 108/4 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-11 | 2026-01-11 | 2026-01-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 129A/5 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-17 | 2026-01-11 | 2026-01-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 108/1 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-20 | 2026-01-18 | 2026-01-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 136/4 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-20 | 2026-01-18 | 2026-01-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 76/2 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-24 | 2026-01-18 | 2026-01-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 77/1 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-25 | 2026-01-25 | 2026-01-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 107/4 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-27 | 2026-01-25 | 2026-01-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 129A/7 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-27 | 2026-01-25 | 2026-01-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 76/1 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-28 | 2026-01-25 | 2026-01-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 139/6 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-30 | 2026-01-25 | 2026-01-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 127/7 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-30 | 2026-01-25 | 2026-01-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 129A/2 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-31 | 2026-01-25 | 2026-01-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 129A/4 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-31 | 2026-01-25 | 2026-01-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 136/3 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-01-31 | 2026-01-25 | 2026-01-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 76/6 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-02-02 | 2026-02-01 | 2026-02-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 82/2 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-02-03 | 2026-02-01 | 2026-02-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 127/4 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-02-05 | 2026-02-01 | 2026-02-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 129A/10 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-02-08 | 2026-02-08 | 2026-02-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 82/3 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-02-09 | 2026-02-08 | 2026-02-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 127/1 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-02-11 | 2026-02-08 | 2026-02-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 129A/3 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-02-13 | 2026-02-08 | 2026-02-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 127/2 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-02-13 | 2026-02-08 | 2026-02-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 70/3 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-02-16 | 2026-02-15 | 2026-02-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 129A/6 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-02-17 | 2026-02-15 | 2026-02-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 121/10 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-02-23 | 2026-02-22 | 2026-02-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 70/1 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-02-28 | 2026-02-22 | 2026-02-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 125/1 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-03-03 | 2026-03-01 | 2026-03-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 126/7 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-03-07 | 2026-03-01 | 2026-03-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 70/2 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-03-14 | 2026-03-08 | 2026-03-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 124/5 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-03-21 | 2026-03-15 | 2026-03-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 76/5 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-03-30 | 2026-03-29 | 2026-03-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 88/2 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-02 | 2026-03-29 | 2026-04-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 88/1 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-03 | 2026-03-29 | 2026-04-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 127/3 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-08 | 2026-04-05 | 2026-04-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 124/0 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-08 | 2026-04-05 | 2026-04-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 87/4 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-11 | 2026-04-05 | 2026-04-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 102/11 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-11 | 2026-04-05 | 2026-04-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 139/4 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-13 | 2026-04-12 | 2026-04-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 69/2 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-14 | 2026-04-12 | 2026-04-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 87/5 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-15 | 2026-04-12 | 2026-04-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 121/9 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-18 | 2026-04-12 | 2026-04-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 71/1 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-18 | 2026-04-12 | 2026-04-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 87/2 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-21 | 2026-04-19 | 2026-04-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 69/1 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-22 | 2026-04-19 | 2026-04-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 109/8 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-23 | 2026-04-19 | 2026-04-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 125/0 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-24 | 2026-04-19 | 2026-04-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 136/0 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-24 | 2026-04-19 | 2026-04-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 71/2 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-25 | 2026-04-19 | 2026-04-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 87/3 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-28 | 2026-04-26 | 2026-04-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 69/3 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-30 | 2026-04-26 | 2026-04-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 127/0 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-30 | 2026-04-26 | 2026-04-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 139/0 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-30 | 2026-04-26 | 2026-04-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 71/3 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-04-30 | 2026-04-26 | 2026-04-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 88/3 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-05-04 | 2026-05-03 | 2026-05-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 108/0 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-05-04 | 2026-05-03 | 2026-05-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 139/1 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-05-04 | 2026-05-03 | 2026-05-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 71/4 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-05-06 | 2026-05-03 | 2026-05-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 107/0 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-05-08 | 2026-05-03 | 2026-05-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 69/4 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-05-12 | 2026-05-10 | 2026-05-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 126/0 | 1
TA 602 | TA 602 | ta602 |  | filename | 2026-05-18 | 2026-05-15 | 2026-05-10 | 2026-05-01 | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | detail | detail_date | 88/0 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-08-12 | 2024-08-11 | 2024-08-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 20/7 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-08-16 | 2024-08-11 | 2024-08-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 20/5 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-08-19 | 2024-08-18 | 2024-08-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 18/3 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-09-09 | 2024-09-08 | 2024-09-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 10/3 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-09-11 | 2024-09-08 | 2024-09-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 15/2 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-09-15 | 2024-09-15 | 2024-09-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 15/3 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-09-19 | 2024-09-15 | 2024-09-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 21/6 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-09-22 | 2024-09-22 | 2024-09-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 15/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-09-23 | 2024-09-22 | 2024-09-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 21/7 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-09-28 | 2024-09-22 | 2024-09-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 9/8 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-01 | 2024-09-29 | 2024-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 16/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-04 | 2024-09-29 | 2024-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 19/2 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-06 | 2024-10-06 | 2024-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 17/3 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-09 | 2024-10-06 | 2024-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 22/2 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-10 | 2024-10-06 | 2024-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-16 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-11 | 2024-10-06 | 2024-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 17/2 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-16 | 2024-10-13 | 2024-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 16/3 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-18 | 2024-10-13 | 2024-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 18/5 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-19 | 2024-10-13 | 2024-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-12 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-20 | 2024-10-20 | 2024-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-11 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-20 | 2024-10-20 | 2024-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-19 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-21 | 2024-10-20 | 2024-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 21/12 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-21 | 2024-10-20 | 2024-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-18 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-22 | 2024-10-20 | 2024-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 10/4 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-22 | 2024-10-20 | 2024-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 20/6 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-24 | 2024-10-20 | 2024-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 15/4 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-24 | 2024-10-20 | 2024-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 17/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-24 | 2024-10-20 | 2024-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 18/11 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-26 | 2024-10-20 | 2024-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 20/3 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-26 | 2024-10-20 | 2024-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 21/3 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-27 | 2024-10-27 | 2024-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 11/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-27 | 2024-10-27 | 2024-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 16/2 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-30 | 2024-10-27 | 2024-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 20/4 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-30 | 2024-10-27 | 2024-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 9/9 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-10-31 | 2024-10-27 | 2024-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-17 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-03 | 2024-11-03 | 2024-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 15/7 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-04 | 2024-11-03 | 2024-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 18/4 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-05 | 2024-11-03 | 2024-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 20/2 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-06 | 2024-11-03 | 2024-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 15/6 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-08 | 2024-11-03 | 2024-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 20/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-08 | 2024-11-03 | 2024-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-14 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-09 | 2024-11-03 | 2024-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 15/8 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-09 | 2024-11-03 | 2024-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-21 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-12 | 2024-11-10 | 2024-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 15/9 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-12 | 2024-11-10 | 2024-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-20 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-14 | 2024-11-10 | 2024-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 18/6 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-15 | 2024-11-10 | 2024-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 10/2 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-15 | 2024-11-10 | 2024-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 21/5 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-17 | 2024-11-17 | 2024-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 21/4 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-18 | 2024-11-17 | 2024-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 19/3 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-19 | 2024-11-17 | 2024-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 21/10 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-19 | 2024-11-17 | 2024-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 21/8 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-20 | 2024-11-17 | 2024-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 18/7 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-21 | 2024-11-17 | 2024-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 19/5 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-24 | 2024-11-24 | 2024-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 19/4 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-26 | 2024-11-24 | 2024-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 18/9 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-26 | 2024-11-24 | 2024-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 19/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-26 | 2024-11-24 | 2024-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-10 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-29 | 2024-11-24 | 2024-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 18/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-30 | 2024-11-24 | 2024-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 18/10 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-11-30 | 2024-11-24 | 2024-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 18/8 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-04 | 2024-12-01 | 2024-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 21/9 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-06 | 2024-12-01 | 2024-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 5/2 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-07 | 2024-12-01 | 2024-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 5/3 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-08 | 2024-12-08 | 2024-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 18/2 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-09 | 2024-12-08 | 2024-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 15/5 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-11 | 2024-12-08 | 2024-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8B/0 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-11 | 2024-12-08 | 2024-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-22 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-15 | 2024-12-15 | 2024-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 23/4 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-15 | 2024-12-15 | 2024-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-15 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-19 | 2024-12-15 | 2024-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 14/9 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-19 | 2024-12-15 | 2024-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 22/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-19 | 2024-12-15 | 2024-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/14 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-19 | 2024-12-15 | 2024-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8B/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-20 | 2024-12-15 | 2024-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 29A/2 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-20 | 2024-12-15 | 2024-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/13 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-23 | 2024-12-22 | 2024-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 23/2 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-25 | 2024-12-22 | 2024-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 14/7 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-25 | 2024-12-22 | 2024-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 29A/3 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-25 | 2024-12-22 | 2024-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/15 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-26 | 2024-12-22 | 2024-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 29A/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-27 | 2024-12-22 | 2024-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8B/2 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-28 | 2024-12-22 | 2024-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 30/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-28 | 2024-12-22 | 2024-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-30 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-29 | 2024-12-29 | 2024-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 5A/0 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-30 | 2024-12-29 | 2024-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 30/6 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-31 | 2024-12-29 | 2024-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 14/8 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2024-12-31 | 2024-12-29 | 2024-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 30/3 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-04 | 2024-12-29 | 2025-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8A/0 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-05 | 2025-01-05 | 2025-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 30/4 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-05 | 2025-01-05 | 2025-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 5/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-06 | 2025-01-05 | 2025-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 30/2 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-07 | 2025-01-05 | 2025-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-31 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-08 | 2025-01-05 | 2025-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/4 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-10 | 2025-01-05 | 2025-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 30/5 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-12 | 2025-01-12 | 2025-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/11 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-14 | 2025-01-12 | 2025-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/3 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-14 | 2025-01-12 | 2025-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/6 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-15 | 2025-01-12 | 2025-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 31/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-16 | 2025-01-12 | 2025-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8D/0 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-18 | 2025-01-12 | 2025-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/2 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-19 | 2025-01-19 | 2025-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 29A/4 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-19 | 2025-01-19 | 2025-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/5 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-23 | 2025-01-19 | 2025-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 32/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-24 | 2025-01-19 | 2025-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-27 | 2025-01-26 | 2025-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8E/2 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-29 | 2025-01-26 | 2025-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-32 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-30 | 2025-01-26 | 2025-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/9 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-01-31 | 2025-01-26 | 2025-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 1D/0 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-02 | 2025-02-02 | 2025-02-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 1A/2 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-02 | 2025-02-02 | 2025-02-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 2/0 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-05 | 2025-02-02 | 2025-02-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 1A/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-05 | 2025-02-02 | 2025-02-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/0 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-06 | 2025-02-02 | 2025-02-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 1/2 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-06 | 2025-02-02 | 2025-02-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-23 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-08 | 2025-02-02 | 2025-02-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/10 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-09 | 2025-02-09 | 2025-02-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 0/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-10 | 2025-02-09 | 2025-02-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 23/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-12 | 2025-02-09 | 2025-02-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/16 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-15 | 2025-02-09 | 2025-02-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 32/2 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-15 | 2025-02-09 | 2025-02-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/17 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-17 | 2025-02-16 | 2025-02-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 1A/0 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-18 | 2025-02-16 | 2025-02-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 3/0 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-19 | 2025-02-16 | 2025-02-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 21/11 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-20 | 2025-02-16 | 2025-02-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 0/0 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-22 | 2025-02-16 | 2025-02-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 1D/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-23 | 2025-02-23 | 2025-02-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 1/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-25 | 2025-02-23 | 2025-02-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 1C/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-25 | 2025-02-23 | 2025-02-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 20/8 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-02-28 | 2025-02-23 | 2025-02-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 23/3 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-03-05 | 2025-03-02 | 2025-03-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 1B/0 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-03-09 | 2025-03-09 | 2025-03-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 7/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-03-16 | 2025-03-16 | 2025-03-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 7/0 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-03-16 | 2025-03-16 | 2025-03-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 7/2 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-03-16 | 2025-03-16 | 2025-03-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-26 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-03-22 | 2025-03-16 | 2025-03-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 1E/0 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-03-23 | 2025-03-23 | 2025-03-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 7/3 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-03-27 | 2025-03-23 | 2025-03-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 1/0 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-03-28 | 2025-03-23 | 2025-03-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 5/0 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-04-03 | 2025-03-30 | 2025-04-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-27 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-04-08 | 2025-04-06 | 2025-04-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-13 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-04-15 | 2025-04-13 | 2025-04-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 21/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-04-17 | 2025-04-13 | 2025-04-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-25 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-04-19 | 2025-04-13 | 2025-04-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 10/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-04-21 | 2025-04-20 | 2025-04-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 21/2 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-04-25 | 2025-04-20 | 2025-04-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8E/5 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-04-26 | 2025-04-20 | 2025-04-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8E/4 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-04-27 | 2025-04-27 | 2025-04-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 21/13 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-04-29 | 2025-04-27 | 2025-04-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-24 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-04-30 | 2025-04-27 | 2025-04-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 23/5 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-10 | 2025-05-04 | 2025-05-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 29A/0 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-12 | 2025-05-11 | 2025-05-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8C/0 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-13 | 2025-05-11 | 2025-05-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/12 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-14 | 2025-05-11 | 2025-05-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-29 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-17 | 2025-05-11 | 2025-05-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 9/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-18 | 2025-05-18 | 2025-05-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8/0 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-18 | 2025-05-18 | 2025-05-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-9 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-22 | 2025-05-18 | 2025-05-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 9/2 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-23 | 2025-05-18 | 2025-05-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 9/6 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-24 | 2025-05-18 | 2025-05-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 28/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-25 | 2025-05-25 | 2025-05-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8E/10 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-25 | 2025-05-25 | 2025-05-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 9/5 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-25 | 2025-05-25 | 2025-05-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | AP-28 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-26 | 2025-05-25 | 2025-05-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8E/8 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-27 | 2025-05-25 | 2025-05-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8E/12 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-29 | 2025-05-25 | 2025-05-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8E/9 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-29 | 2025-05-25 | 2025-05-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 9/7 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-05-30 | 2025-05-25 | 2025-05-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8E/11 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-06-04 | 2025-06-01 | 2025-06-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8E/6 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-06-05 | 2025-06-01 | 2025-06-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 9/3 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-06-05 | 2025-06-01 | 2025-06-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 9/4 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-06-06 | 2025-06-01 | 2025-06-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8E/3 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-06-08 | 2025-06-08 | 2025-06-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8E/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-06-29 | 2025-06-29 | 2025-06-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 28/2 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2025-07-10 | 2025-07-06 | 2025-07-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 17/0 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-08-17 | 2025-08-17 | 2025-08-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8D/5 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-08-23 | 2025-08-17 | 2025-08-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8D/6 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-08-30 | 2025-08-24 | 2025-08-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8D/4 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-09-03 | 2025-08-31 | 2025-09-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/8 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-09-07 | 2025-09-07 | 2025-09-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 14/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-09-10 | 2025-09-07 | 2025-09-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8D/3 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-09-12 | 2025-09-07 | 2025-09-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 14/3 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-09-20 | 2025-09-14 | 2025-09-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 14/2 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-09-21 | 2025-09-21 | 2025-09-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8E/0 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-09-26 | 2025-09-21 | 2025-09-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 4/7 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-09-30 | 2025-09-28 | 2025-09-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 14/4 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-10-08 | 2025-10-05 | 2025-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 14/5 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-10-08 | 2025-10-05 | 2025-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 5A/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-10-12 | 2025-10-12 | 2025-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 5A/2 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-10-17 | 2025-10-12 | 2025-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 5B/0 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2025-10-23 | 2025-10-19 | 2025-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 16/0 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2025-10-27 | 2025-10-26 | 2025-10-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 16/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-11-05 | 2025-11-02 | 2025-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 14/6 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2025-11-07 | 2025-11-02 | 2025-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 18/0 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-11-08 | 2025-11-02 | 2025-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 13/1 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2025-11-15 | 2025-11-09 | 2025-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 16/2 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-11-16 | 2025-11-16 | 2025-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8E/7 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-11-20 | 2025-11-16 | 2025-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8D/1 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-11-26 | 2025-11-23 | 2025-11-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 6/0 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-12-03 | 2025-11-30 | 2025-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8D/2 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2025-12-07 | 2025-12-07 | 2025-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 8D/0A | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2025-12-13 | 2025-12-07 | 2025-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 10/0 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2025-12-15 | 2025-12-14 | 2025-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 15/2 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2025-12-16 | 2025-12-14 | 2025-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 11/0 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2025-12-16 | 2025-12-14 | 2025-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 15/1 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2025-12-17 | 2025-12-14 | 2025-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 12/0 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2025-12-19 | 2025-12-14 | 2025-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 15/3 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2025-12-25 | 2025-12-21 | 2025-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 13/0 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2025-12-28 | 2025-12-28 | 2025-12-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 14/0 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-01-10 | 2026-01-04 | 2026-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 12/1 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-01-10 | 2026-01-04 | 2026-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 13/2 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-01-14 | 2026-01-11 | 2026-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 13/1 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-01-21 | 2026-01-18 | 2026-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 8/0 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-01-21 | 2026-01-18 | 2026-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 9/0 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-01-25 | 2026-01-25 | 2026-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 7/0 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-01-27 | 2026-01-25 | 2026-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 6/2 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-01-30 | 2026-01-25 | 2026-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 6/1 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-01-31 | 2026-01-25 | 2026-01-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 6/3 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-02-05 | 2026-02-01 | 2026-02-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 5/0 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-02-10 | 2026-02-08 | 2026-02-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 15/0 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-02-19 | 2026-02-15 | 2026-02-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 6/0 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2026-02-24 | 2026-02-22 | 2026-02-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 1C/0 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-03-08 | 2026-03-08 | 2026-03-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 4/0 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-03-14 | 2026-03-08 | 2026-03-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 6/4 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-03-16 | 2026-03-15 | 2026-03-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 4/1 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-03-17 | 2026-03-15 | 2026-03-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 4/2 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2026-04-09 | 2026-04-05 | 2026-04-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 33/0 (New) | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-04-12 | 2026-04-12 | 2026-04-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 3/1 | 1
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | 2026-05-20 | 2026-04-14 | 2026-04-12 | 2026-04-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV | Progress-132kV | detail | detail_date | 3/0 | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2026-04-20 | 2026-04-19 | 2026-04-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 33/1 (New) | 1
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | 2026-05-20 | 2026-04-30 | 2026-04-26 | 2026-04-01 | TB 501 - DPR - 2026-05-20.xlsx | Progress-220kV | Progress-220kV | detail | detail_date | 34/0 (New) | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-01-17 | 2025-01-12 | 2025-01-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 83/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-01-27 | 2025-01-26 | 2025-01-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 75/7 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-02 | 2025-02-02 | 2025-02-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 75/6 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-05 | 2025-02-02 | 2025-02-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 75/4 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-05 | 2025-02-02 | 2025-02-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 75/5 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-09 | 2025-02-09 | 2025-02-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 77/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-10 | 2025-02-09 | 2025-02-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 75/3 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-11 | 2025-02-09 | 2025-02-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 77/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-14 | 2025-02-09 | 2025-02-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 77/3 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-17 | 2025-02-16 | 2025-02-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 75/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-17 | 2025-02-16 | 2025-02-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 77/4 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-18 | 2025-02-16 | 2025-02-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 75/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-19 | 2025-02-16 | 2025-02-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 77/5 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-22 | 2025-02-16 | 2025-02-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 73/3 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-22 | 2025-02-16 | 2025-02-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 86/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-23 | 2025-02-23 | 2025-02-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 79/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-25 | 2025-02-23 | 2025-02-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 73/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-25 | 2025-02-23 | 2025-02-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 95A/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-27 | 2025-02-23 | 2025-02-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 80/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-28 | 2025-02-23 | 2025-02-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 66/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-28 | 2025-02-23 | 2025-02-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 74/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-02-28 | 2025-02-23 | 2025-02-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 96/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-02 | 2025-03-02 | 2025-03-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 76/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-06 | 2025-03-02 | 2025-03-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 66/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-07 | 2025-03-02 | 2025-03-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 64/3 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-07 | 2025-03-02 | 2025-03-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 96/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-08 | 2025-03-02 | 2025-03-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 81/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-09 | 2025-03-09 | 2025-03-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 86/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-10 | 2025-03-09 | 2025-03-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 64/4 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-10 | 2025-03-09 | 2025-03-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 85/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-10 | 2025-03-09 | 2025-03-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 99/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-11 | 2025-03-09 | 2025-03-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 66/3 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-24 | 2025-03-23 | 2025-03-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 87/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-26 | 2025-03-23 | 2025-03-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 64/7 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-30 | 2025-03-30 | 2025-03-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 64/6 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-30 | 2025-03-30 | 2025-03-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 87/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-30 | 2025-03-30 | 2025-03-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 98A/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-03-31 | 2025-03-30 | 2025-03-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 64/5 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-04-04 | 2025-03-30 | 2025-04-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 98/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-04-09 | 2025-04-06 | 2025-04-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 71/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-04-13 | 2025-04-13 | 2025-04-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 91/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-04-16 | 2025-04-13 | 2025-04-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 91/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-04-17 | 2025-04-13 | 2025-04-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 51/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-04-18 | 2025-04-13 | 2025-04-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 119/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-04-20 | 2025-04-20 | 2025-04-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 95/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-04-22 | 2025-04-20 | 2025-04-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 119/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-04-23 | 2025-04-20 | 2025-04-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 51/3 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-04-25 | 2025-04-20 | 2025-04-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 99/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-04-29 | 2025-04-27 | 2025-04-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 104B/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-04-29 | 2025-04-27 | 2025-04-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 62/4 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-04-29 | 2025-04-27 | 2025-04-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 81/4 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-05-05 | 2025-05-04 | 2025-05-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 104B/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-05-15 | 2025-05-11 | 2025-05-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 105/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-05-18 | 2025-05-18 | 2025-05-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 100/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-05-21 | 2025-05-18 | 2025-05-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 81/5 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-05-23 | 2025-05-18 | 2025-05-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 97/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-05-25 | 2025-05-25 | 2025-05-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 99C/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-05-28 | 2025-05-25 | 2025-05-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 105/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-05-29 | 2025-05-25 | 2025-05-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 98A/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-05-31 | 2025-05-25 | 2025-05-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 62/5 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-04 | 2025-06-01 | 2025-06-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 81/3 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-05 | 2025-06-01 | 2025-06-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 120/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-06 | 2025-06-01 | 2025-06-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 96/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-07 | 2025-06-01 | 2025-06-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 75/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-08 | 2025-06-08 | 2025-06-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 147/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-10 | 2025-06-08 | 2025-06-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 82/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-12 | 2025-06-08 | 2025-06-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 147/5 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-12 | 2025-06-08 | 2025-06-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 79/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-15 | 2025-06-15 | 2025-06-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 119/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-15 | 2025-06-15 | 2025-06-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 147/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-15 | 2025-06-15 | 2025-06-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 82/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-16 | 2025-06-15 | 2025-06-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 147/4 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-16 | 2025-06-15 | 2025-06-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 78/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-20 | 2025-06-15 | 2025-06-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 74/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-21 | 2025-06-15 | 2025-06-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 147/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-22 | 2025-06-22 | 2025-06-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 147/7 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-23 | 2025-06-22 | 2025-06-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 95A/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-25 | 2025-06-22 | 2025-06-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 146/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-25 | 2025-06-22 | 2025-06-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 147/3 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-26 | 2025-06-22 | 2025-06-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 73/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-27 | 2025-06-22 | 2025-06-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 86/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-30 | 2025-06-29 | 2025-06-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 114/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-30 | 2025-06-29 | 2025-06-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 146/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-30 | 2025-06-29 | 2025-06-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 147/8 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-06-30 | 2025-06-29 | 2025-06-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 72/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-04 | 2025-06-29 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 95/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-05 | 2025-06-29 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 148/3 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-06 | 2025-07-06 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 106/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-08 | 2025-07-06 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 146/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-08 | 2025-07-06 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 148/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-10 | 2025-07-06 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 114/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-10 | 2025-07-06 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 148/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-10 | 2025-07-06 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 80/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-11 | 2025-07-06 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 141/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-11 | 2025-07-06 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 95/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-12 | 2025-07-06 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 148/4 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-13 | 2025-07-13 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 141/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-13 | 2025-07-13 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 145/4 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-14 | 2025-07-13 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 125/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-14 | 2025-07-13 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 133/6 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-15 | 2025-07-13 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 148/5 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-16 | 2025-07-13 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 109A/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-16 | 2025-07-13 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 113A/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-16 | 2025-07-13 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 133/5 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-16 | 2025-07-13 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 145/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-17 | 2025-07-13 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 142/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-18 | 2025-07-13 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 115/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-18 | 2025-07-13 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 148/6 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-19 | 2025-07-13 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 77/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-21 | 2025-07-20 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 133/4 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-21 | 2025-07-20 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 143/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-21 | 2025-07-20 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 145/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-23 | 2025-07-20 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 148/7 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-24 | 2025-07-20 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 125/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-24 | 2025-07-20 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 133/3 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-24 | 2025-07-20 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 94/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-25 | 2025-07-20 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 145/3 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-26 | 2025-07-20 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 126/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-26 | 2025-07-20 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 143/3 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-27 | 2025-07-27 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 133/8 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-27 | 2025-07-27 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 149B/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-27 | 2025-07-27 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 79/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-28 | 2025-07-27 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 110/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-29 | 2025-07-27 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 143/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-29 | 2025-07-27 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 99/3 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-30 | 2025-07-27 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 133/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-30 | 2025-07-27 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 149B/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-31 | 2025-07-27 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 111/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-31 | 2025-07-27 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 116/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-31 | 2025-07-27 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 129/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-31 | 2025-07-27 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 133/7 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-31 | 2025-07-27 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 143/6 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-31 | 2025-07-27 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 145/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-31 | 2025-07-27 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 76/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-07-31 | 2025-07-27 | 2025-07-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 98B/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-02 | 2025-07-27 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 126/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-02 | 2025-07-27 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 143/7 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-04 | 2025-08-03 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 130/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-04 | 2025-08-03 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 143/5 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-05 | 2025-08-03 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 97/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-06 | 2025-08-03 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 143/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-07 | 2025-08-03 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 102/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-07 | 2025-08-03 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 133/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-07 | 2025-08-03 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 144/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-07 | 2025-08-03 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 98/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-08 | 2025-08-03 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 112/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-08 | 2025-08-03 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 129/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-09 | 2025-08-03 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 143/4 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-09 | 2025-08-03 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 83/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-12 | 2025-08-10 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 131/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-12 | 2025-08-10 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 149B/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-14 | 2025-08-10 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 102/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-14 | 2025-08-10 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 140/3 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-14 | 2025-08-10 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 99/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-16 | 2025-08-10 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 115/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-16 | 2025-08-10 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 134A/4 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-17 | 2025-08-17 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 140/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-19 | 2025-08-17 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 126/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-19 | 2025-08-17 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 135/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-19 | 2025-08-17 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 149A/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-20 | 2025-08-17 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 128/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-20 | 2025-08-17 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 131/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-20 | 2025-08-17 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 141/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-22 | 2025-08-17 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 87/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-22 | 2025-08-17 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 99/4 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-23 | 2025-08-17 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 129/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-23 | 2025-08-17 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 135/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-23 | 2025-08-17 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 138/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-24 | 2025-08-24 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 137/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-24 | 2025-08-24 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 63/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-25 | 2025-08-24 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 132/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-25 | 2025-08-24 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 138/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-26 | 2025-08-24 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 134A/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-26 | 2025-08-24 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 56/4 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-27 | 2025-08-24 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 56/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-28 | 2025-08-24 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 138/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-28 | 2025-08-24 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 149/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-29 | 2025-08-24 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 134/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-29 | 2025-08-24 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 134A/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-31 | 2025-08-31 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 116/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-31 | 2025-08-31 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 132/3 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-31 | 2025-08-31 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 134A/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-31 | 2025-08-31 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 138/3 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-31 | 2025-08-31 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 56/5 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-31 | 2025-08-31 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 82/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-31 | 2025-08-31 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 85/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-08-31 | 2025-08-31 | 2025-08-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 99A/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-04 | 2025-08-31 | 2025-09-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 131/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-05 | 2025-08-31 | 2025-09-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 139/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-05 | 2025-08-31 | 2025-09-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 147/6 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-10 | 2025-09-07 | 2025-09-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 125/3 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-10 | 2025-09-07 | 2025-09-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 57/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-12 | 2025-09-07 | 2025-09-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 59/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-12 | 2025-09-07 | 2025-09-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 81/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-14 | 2025-09-14 | 2025-09-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 147/9 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-14 | 2025-09-14 | 2025-09-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 64/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-17 | 2025-09-14 | 2025-09-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 58/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-18 | 2025-09-14 | 2025-09-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 125/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-19 | 2025-09-14 | 2025-09-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 72/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-20 | 2025-09-14 | 2025-09-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 56/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-21 | 2025-09-21 | 2025-09-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 136/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-25 | 2025-09-21 | 2025-09-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 132/4 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-25 | 2025-09-21 | 2025-09-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 48/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-30 | 2025-09-28 | 2025-09-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 123/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-30 | 2025-09-28 | 2025-09-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 133/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-30 | 2025-09-28 | 2025-09-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 152/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-09-30 | 2025-09-28 | 2025-09-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 153A/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-10-11 | 2025-10-05 | 2025-10-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 135/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-10-13 | 2025-10-12 | 2025-10-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 149B/3 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-10-16 | 2025-10-12 | 2025-10-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 135/3 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-10-16 | 2025-10-12 | 2025-10-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 73/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-10-19 | 2025-10-19 | 2025-10-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 84/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-10-29 | 2025-10-26 | 2025-10-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 150/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-10-30 | 2025-10-26 | 2025-10-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 71/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-10-31 | 2025-10-26 | 2025-10-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 134A/3 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-04 | 2025-11-02 | 2025-11-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 148/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-07 | 2025-11-02 | 2025-11-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 71/3 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-08 | 2025-11-02 | 2025-11-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 151/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-08 | 2025-11-02 | 2025-11-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 78/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-10 | 2025-11-09 | 2025-11-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 81/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-11 | 2025-11-09 | 2025-11-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 140/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-12 | 2025-11-09 | 2025-11-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 89/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-14 | 2025-11-09 | 2025-11-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 71/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-16 | 2025-11-16 | 2025-11-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 113/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-16 | 2025-11-16 | 2025-11-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 139/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-17 | 2025-11-16 | 2025-11-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 72/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-18 | 2025-11-16 | 2025-11-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 89/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-22 | 2025-11-16 | 2025-11-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 140/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-22 | 2025-11-16 | 2025-11-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 154/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-22 | 2025-11-16 | 2025-11-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 90/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-26 | 2025-11-23 | 2025-11-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 90/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-28 | 2025-11-23 | 2025-11-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 127/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 153/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 66/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-12-05 | 2025-11-30 | 2025-12-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 118/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-12-05 | 2025-11-30 | 2025-12-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 88/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-12-06 | 2025-11-30 | 2025-12-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 130/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-12-08 | 2025-12-07 | 2025-12-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 98B/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-12-13 | 2025-12-07 | 2025-12-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 117/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-12-14 | 2025-12-14 | 2025-12-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 128/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-12-19 | 2025-12-14 | 2025-12-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 117/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-12-20 | 2025-12-14 | 2025-12-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 132/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-12-24 | 2025-12-21 | 2025-12-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 91/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-12-28 | 2025-12-28 | 2025-12-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 132/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-12-30 | 2025-12-28 | 2025-12-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 104A/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-12-30 | 2025-12-28 | 2025-12-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 124/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2025-12-31 | 2025-12-28 | 2025-12-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 91/3 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-04 | 2026-01-04 | 2026-01-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 104B/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-07 | 2026-01-04 | 2026-01-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 65/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-08 | 2026-01-04 | 2026-01-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 122/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-15 | 2026-01-11 | 2026-01-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 126/3 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-15 | 2026-01-11 | 2026-01-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 65/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-15 | 2026-01-11 | 2026-01-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 69/3 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-20 | 2026-01-18 | 2026-01-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 108/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-23 | 2026-01-18 | 2026-01-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/3 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-23 | 2026-01-18 | 2026-01-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 109/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-25 | 2026-01-25 | 2026-01-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 120/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-26 | 2026-01-25 | 2026-01-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/5 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-28 | 2026-01-25 | 2026-01-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/6 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-28 | 2026-01-25 | 2026-01-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 92/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-30 | 2026-01-25 | 2026-01-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/7 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-01-30 | 2026-01-25 | 2026-01-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 93/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-02-04 | 2026-02-01 | 2026-02-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/7 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-02-06 | 2026-02-01 | 2026-02-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/9 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-02-11 | 2026-02-08 | 2026-02-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-02-12 | 2026-02-08 | 2026-02-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/12 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-02-14 | 2026-02-08 | 2026-02-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 1/1 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-02-16 | 2026-02-15 | 2026-02-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/2 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-02-18 | 2026-02-15 | 2026-02-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 1/2 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-02-20 | 2026-02-15 | 2026-02-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/1 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-02-28 | 2026-02-22 | 2026-02-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 1/0 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-02-28 | 2026-02-22 | 2026-02-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 6/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-02-28 | 2026-02-22 | 2026-02-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 117/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-02-28 | 2026-02-22 | 2026-02-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-03-04 | 2026-03-01 | 2026-03-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 157/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-03-10 | 2026-03-08 | 2026-03-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 156/0 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-03-11 | 2026-03-08 | 2026-03-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-03-11 | 2026-03-08 | 2026-03-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 98B/1 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-03-13 | 2026-03-08 | 2026-03-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/0 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-03-15 | 2026-03-15 | 2026-03-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/2 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-03-16 | 2026-03-15 | 2026-03-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/3 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-03-17 | 2026-03-15 | 2026-03-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/4 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-03-19 | 2026-03-15 | 2026-03-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 103/0 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-03-22 | 2026-03-22 | 2026-03-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 1/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-03-22 | 2026-03-22 | 2026-03-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/8 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-03-25 | 2026-03-22 | 2026-03-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-03-26 | 2026-03-22 | 2026-03-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/0B | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-03-26 | 2026-03-22 | 2026-03-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/1 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-03-27 | 2026-03-22 | 2026-03-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/5 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-03-28 | 2026-03-22 | 2026-03-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/0A | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-03-31 | 2026-03-29 | 2026-03-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/2 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-04-02 | 2026-03-29 | 2026-04-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/1 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-04-04 | 2026-03-29 | 2026-04-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-04-06 | 2026-04-05 | 2026-04-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-04-07 | 2026-04-05 | 2026-04-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-04-08 | 2026-04-05 | 2026-04-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/1B | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-04-09 | 2026-04-05 | 2026-04-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/1 A | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-04-10 | 2026-04-05 | 2026-04-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 103/1 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-04-11 | 2026-04-05 | 2026-04-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/0 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-04-12 | 2026-04-12 | 2026-04-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 5/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-04-14 | 2026-04-12 | 2026-04-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/3 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-04-15 | 2026-04-12 | 2026-04-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/4 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-04-15 | 2026-04-12 | 2026-04-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 99C/0 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-04-16 | 2026-04-12 | 2026-04-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/5 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-04-18 | 2026-04-12 | 2026-04-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/3 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-04-21 | 2026-04-19 | 2026-04-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-04-21 | 2026-04-19 | 2026-04-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/5 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-04-23 | 2026-04-19 | 2026-04-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/14 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-04-24 | 2026-04-19 | 2026-04-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 100/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-04-28 | 2026-04-26 | 2026-04-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/11 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-04-29 | 2026-04-26 | 2026-04-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/4 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-02 | 2026-04-26 | 2026-05-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-02 | 2026-04-26 | 2026-05-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 2/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-03 | 2026-05-03 | 2026-05-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-03 | 2026-05-03 | 2026-05-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 155/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-03 | 2026-05-03 | 2026-05-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 9/2 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-05-05 | 2026-05-03 | 2026-05-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 3/5 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-05-06 | 2026-05-03 | 2026-05-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-06 | 2026-05-03 | 2026-05-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 154/1B | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-05-08 | 2026-05-03 | 2026-05-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/2 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-08 | 2026-05-03 | 2026-05-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 10/13 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-08 | 2026-05-03 | 2026-05-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 154/2B | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-09 | 2026-05-03 | 2026-05-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 154/1A | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-09 | 2026-05-03 | 2026-05-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 154/2A | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-05-10 | 2026-05-10 | 2026-05-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/4 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-11 | 2026-05-10 | 2026-05-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/6 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-14 | 2026-05-10 | 2026-05-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 13/2 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-05-15 | 2026-05-10 | 2026-05-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/0 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-16 | 2026-05-10 | 2026-05-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 7/8 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-17 | 2026-05-17 | 2026-05-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/3 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-05-18 | 2026-05-17 | 2026-05-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/1 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-05-19 | 2026-05-17 | 2026-05-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/0 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-05-19 | 2026-05-17 | 2026-05-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/3 | 1
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-05-20 | 2026-05-19 | 2026-05-17 | 2026-05-01 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 8/4 | 1
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | 2026-05-20 | 2026-05-20 | 2026-05-17 | 2026-05-01 | TB 507 - DPR - 2026-05-20.xlsx | Foundation | Foundation | detail | detail_date | 4/1 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-08-11 | 2025-08-10 | 2025-08-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 29/5 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-09-06 | 2025-08-31 | 2025-09-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 29/4 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-09-20 | 2025-09-14 | 2025-09-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 27/0 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-09-24 | 2025-09-21 | 2025-09-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 29/3 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-10-10 | 2025-10-05 | 2025-10-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 29/1 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-10-16 | 2025-10-12 | 2025-10-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 18/0 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-10-16 | 2025-10-12 | 2025-10-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 29/6 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-10-20 | 2025-10-19 | 2025-10-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 117/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-10-23 | 2025-10-19 | 2025-10-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 71/3 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-10-27 | 2025-10-26 | 2025-10-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 92/3 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-10-28 | 2025-10-26 | 2025-10-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 22/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-10-28 | 2025-10-26 | 2025-10-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 72/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-10-28 | 2025-10-26 | 2025-10-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 92/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-10-29 | 2025-10-26 | 2025-10-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 117/3 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-10-30 | 2025-10-26 | 2025-10-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 31/1 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-10-31 | 2025-10-26 | 2025-10-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 21/1 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-10-31 | 2025-10-26 | 2025-10-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 22/0 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-10-31 | 2025-10-26 | 2025-10-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 89/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-10-31 | 2025-10-26 | 2025-10-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 93/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-04 | 2025-11-02 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 117/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-04 | 2025-11-02 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 93/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-06 | 2025-11-02 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 118/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-06 | 2025-11-02 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 74/0 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-08 | 2025-11-02 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 95/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-09 | 2025-11-09 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 72/0 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-11-10 | 2025-11-09 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 23/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-10 | 2025-11-09 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 92/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-10 | 2025-11-09 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 95/3 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-11-11 | 2025-11-09 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 31/3 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-12 | 2025-11-09 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 97/2 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-11-13 | 2025-11-09 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 22/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-13 | 2025-11-09 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 97/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-14 | 2025-11-09 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 76/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-15 | 2025-11-09 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 131/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-15 | 2025-11-09 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 95/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-16 | 2025-11-16 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP118 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-11-17 | 2025-11-16 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 15/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-18 | 2025-11-16 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 76/1 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-11-19 | 2025-11-16 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 15/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-19 | 2025-11-16 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 131/3 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-19 | 2025-11-16 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP93 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-20 | 2025-11-16 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 95/4 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-20 | 2025-11-16 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 97/3 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-22 | 2025-11-16 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP90 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-11-23 | 2025-11-23 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 17/0 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-11-23 | 2025-11-23 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 27/1 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-11-24 | 2025-11-23 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 30/3 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-24 | 2025-11-23 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 131/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-24 | 2025-11-23 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP98 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-11-26 | 2025-11-23 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP32 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-26 | 2025-11-23 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 98/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-27 | 2025-11-23 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP94 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-28 | 2025-11-23 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 103/1 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-11-29 | 2025-11-23 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 30/5 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-29 | 2025-11-23 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP96 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 20/0 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 40/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 131/4 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP116 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP87 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP99 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-01 | 2025-11-30 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP75 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-03 | 2025-11-30 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 40/0 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-04 | 2025-11-30 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP28 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-04 | 2025-11-30 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 104/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-05 | 2025-11-30 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 82/2 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-06 | 2025-11-30 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 18/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-06 | 2025-11-30 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 76/3 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-06 | 2025-11-30 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 99/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-07 | 2025-12-07 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP100 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-07 | 2025-12-07 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP95 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-09 | 2025-12-07 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 23/0 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-09 | 2025-12-07 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP117 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-10 | 2025-12-07 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 29/0 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-10 | 2025-12-07 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 77/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-10 | 2025-12-07 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 82/1 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-12 | 2025-12-07 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 30/2 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-13 | 2025-12-07 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 19/2 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-13 | 2025-12-07 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 39/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-13 | 2025-12-07 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP104 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-13 | 2025-12-07 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP77 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-15 | 2025-12-14 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP106 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-16 | 2025-12-14 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 77/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-16 | 2025-12-14 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 85/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-16 | 2025-12-14 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP135 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-17 | 2025-12-14 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 106/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-17 | 2025-12-14 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 130/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-18 | 2025-12-14 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 102/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-18 | 2025-12-14 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP103 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-19 | 2025-12-14 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 30/4 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-19 | 2025-12-14 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 136/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-20 | 2025-12-14 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 116/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-20 | 2025-12-14 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 130/1 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-21 | 2025-12-21 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 23/5 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-21 | 2025-12-21 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 135/2 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-23 | 2025-12-21 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP45 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-24 | 2025-12-21 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP19 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-24 | 2025-12-21 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 131/6 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-24 | 2025-12-21 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 139/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-24 | 2025-12-21 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP85 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-25 | 2025-12-21 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 46/1 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-25 | 2025-12-21 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP43 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-25 | 2025-12-21 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP80 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-26 | 2025-12-21 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 138/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-26 | 2025-12-21 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 156/4 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-27 | 2025-12-21 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 31/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-27 | 2025-12-21 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 131/5 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-27 | 2025-12-21 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 150/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-28 | 2025-12-28 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 137/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-29 | 2025-12-28 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 135/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-29 | 2025-12-28 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP102 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-30 | 2025-12-28 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 156/3 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-30 | 2025-12-28 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 80/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-30 | 2025-12-28 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 86/1 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-31 | 2025-12-28 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 23/4 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2025-12-31 | 2025-12-28 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP33 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-31 | 2025-12-28 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 132/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2025-12-31 | 2025-12-28 | 2025-12-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 138/2 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-04 | 2026-01-04 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 43/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-04 | 2026-01-04 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 150/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-05 | 2026-01-04 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP146 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-07 | 2026-01-04 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 69/3 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-08 | 2026-01-04 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 18/2 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-08 | 2026-01-04 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP26 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-08 | 2026-01-04 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 156/2 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-09 | 2026-01-04 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 31/4 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-09 | 2026-01-04 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 46/3 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-09 | 2026-01-04 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 155/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-10 | 2026-01-04 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 137/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-11 | 2026-01-11 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 152/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-11 | 2026-01-11 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 90/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-11 | 2026-01-11 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP131 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-12 | 2026-01-11 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 43/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-12 | 2026-01-11 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 87/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-16 | 2026-01-11 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 152/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-16 | 2026-01-11 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 90/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-16 | 2026-01-11 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP147 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-17 | 2026-01-11 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP157 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-18 | 2026-01-18 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP31 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-18 | 2026-01-18 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP154 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-20 | 2026-01-18 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 19/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-20 | 2026-01-18 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 145/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-20 | 2026-01-18 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP129 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-20 | 2026-01-18 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP138 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-21 | 2026-01-18 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 25/2 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-21 | 2026-01-18 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 44/3 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-21 | 2026-01-18 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 45/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-21 | 2026-01-18 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 71/2 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-22 | 2026-01-18 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 31/5 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-22 | 2026-01-18 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 156/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-22 | 2026-01-18 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 69/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-22 | 2026-01-18 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP115 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-25 | 2026-01-25 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP16 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-27 | 2026-01-25 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 69/1 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-30 | 2026-01-25 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 32/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-30 | 2026-01-25 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 155/2 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-01-31 | 2026-01-25 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP30 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-31 | 2026-01-25 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 115/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-31 | 2026-01-25 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 151/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-01-31 | 2026-01-25 | 2026-01-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 155/3 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-02-05 | 2026-02-01 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 45/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-05 | 2026-02-01 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 153/0 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-06 | 2026-02-01 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP139 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-02-07 | 2026-02-01 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 44/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-07 | 2026-02-01 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 151/2 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-02-08 | 2026-02-08 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP15 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-08 | 2026-02-08 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP97 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-09 | 2026-02-08 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP155 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-11 | 2026-02-08 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 136/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-12 | 2026-02-08 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 152/4 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-12 | 2026-02-08 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP130 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-02-13 | 2026-02-08 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 25/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-13 | 2026-02-08 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 153/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-13 | 2026-02-08 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP92 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-02-14 | 2026-02-08 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 50A/7 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-14 | 2026-02-08 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP156 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-15 | 2026-02-15 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 136/3 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-15 | 2026-02-15 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 157/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-17 | 2026-02-15 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 72/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-18 | 2026-02-15 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 153/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-18 | 2026-02-15 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP150 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-18 | 2026-02-15 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP70 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-19 | 2026-02-15 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP111 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-02-20 | 2026-02-15 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP12 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-02-20 | 2026-02-15 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP44 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-02-20 | 2026-02-15 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP46 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-20 | 2026-02-15 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 136/4 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-21 | 2026-02-15 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 70/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-21 | 2026-02-15 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP68 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-24 | 2026-02-22 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP132 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-02-25 | 2026-02-22 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 50A/8 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-02-25 | 2026-02-22 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP25 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-25 | 2026-02-22 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP79 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-26 | 2026-02-22 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 67/3 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-26 | 2026-02-22 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 70/1 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-02-27 | 2026-02-22 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 44/1 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-02-27 | 2026-02-22 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP21 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-27 | 2026-02-22 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP137 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-27 | 2026-02-22 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP91 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-28 | 2026-02-22 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 145/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-28 | 2026-02-22 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP114 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-02-28 | 2026-02-22 | 2026-02-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP159 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-02 | 2026-03-01 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP69 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-03-05 | 2026-03-01 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 46/5 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-03-06 | 2026-03-01 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 50A/3 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-03-07 | 2026-03-01 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 29/2 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-03-08 | 2026-03-08 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 43/3 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-03-08 | 2026-03-08 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP14 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-03-09 | 2026-03-08 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 33/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-10 | 2026-03-08 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP149 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-03-11 | 2026-03-08 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 46/4 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-13 | 2026-03-08 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 67/2 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-03-15 | 2026-03-15 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP24 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-15 | 2026-03-15 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP127 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-16 | 2026-03-15 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP148 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-18 | 2026-03-15 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP136 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-19 | 2026-03-15 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 67/1 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-03-21 | 2026-03-15 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 43/4 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-23 | 2026-03-22 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP71 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-25 | 2026-03-22 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP145 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-26 | 2026-03-22 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP152 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-03-28 | 2026-03-22 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 46/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-28 | 2026-03-22 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP108 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-03-30 | 2026-03-29 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 15/3 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-03-30 | 2026-03-29 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 38/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-30 | 2026-03-29 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP124 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-30 | 2026-03-29 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP67 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-03-31 | 2026-03-29 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 42/3 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-31 | 2026-03-29 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 152/3 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-03-31 | 2026-03-29 | 2026-03-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 56/3 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-04-05 | 2026-04-05 | 2026-04-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 47/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-05 | 2026-04-05 | 2026-04-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 144/4 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-06 | 2026-04-05 | 2026-04-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP125 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-07 | 2026-04-05 | 2026-04-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 144/3 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-07 | 2026-04-05 | 2026-04-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 65/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-12 | 2026-04-12 | 2026-04-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP109 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-04-13 | 2026-04-12 | 2026-04-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 40/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-15 | 2026-04-12 | 2026-04-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP126 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-04-16 | 2026-04-12 | 2026-04-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 42/2 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-04-18 | 2026-04-12 | 2026-04-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-21 | 2026-04-19 | 2026-04-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP61 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-22 | 2026-04-19 | 2026-04-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP165 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-23 | 2026-04-19 | 2026-04-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP86 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-04-25 | 2026-04-19 | 2026-04-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP34 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-25 | 2026-04-19 | 2026-04-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 56/2 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-04-26 | 2026-04-26 | 2026-04-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP47 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-26 | 2026-04-26 | 2026-04-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP123 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-27 | 2026-04-26 | 2026-04-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP59 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-28 | 2026-04-26 | 2026-04-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 55/1 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-04-29 | 2026-04-26 | 2026-04-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 37/1 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-04-29 | 2026-04-26 | 2026-04-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP7 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-29 | 2026-04-26 | 2026-04-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP142 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-04-30 | 2026-04-26 | 2026-04-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP41 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-04-30 | 2026-04-26 | 2026-04-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP6 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-30 | 2026-04-26 | 2026-04-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 122/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-04-30 | 2026-04-26 | 2026-04-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP166 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-01 | 2026-04-26 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP64 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-05-07 | 2026-05-03 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 33/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-07 | 2026-05-03 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 64/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-07 | 2026-05-03 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP144 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-07 | 2026-05-03 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP56 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-08 | 2026-05-03 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 142/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-08 | 2026-05-03 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 61/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-08 | 2026-05-03 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP82 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-09 | 2026-05-03 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 57/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-09 | 2026-05-03 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP161 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-11 | 2026-05-10 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP163 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-13 | 2026-05-10 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 56/4 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-05-14 | 2026-05-10 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | AP38 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-14 | 2026-05-10 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 62/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-14 | 2026-05-10 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 71/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-14 | 2026-05-10 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP110 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-15 | 2026-05-10 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP57 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-05-16 | 2026-05-10 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 40/3 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-16 | 2026-05-10 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 159/3 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-16 | 2026-05-10 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 65/4 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-05-17 | 2026-05-17 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 50A/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-17 | 2026-05-17 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP162 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-17 | 2026-05-17 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP60 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-18 | 2026-05-17 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 62/1 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-18 | 2026-05-17 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP128 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-18 | 2026-05-17 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP143 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-18 | 2026-05-17 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP63 | 1
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | config | 2026-05-20 | 2026-05-19 | 2026-05-17 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | detail | detail_date | 23/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-19 | 2026-05-17 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 159/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-19 | 2026-05-17 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | 57/2 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-19 | 2026-05-17 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP112 | 1
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | config | 2026-05-20 | 2026-05-19 | 2026-05-17 | 2026-05-01 | TB 605 - DPR - 2026-05-20.xlsx | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | detail | detail_date | AP70/3 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-10-18 | 2025-10-12 | 2025-10-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 65/3 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-10-18 | 2025-10-12 | 2025-10-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 69/2 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-09 | 2025-11-09 | 2025-11-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 131/2 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-10 | 2025-11-09 | 2025-11-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 58/1 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-10 | 2025-11-09 | 2025-11-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 69/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-11 | 2025-11-09 | 2025-11-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 58/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-15 | 2025-11-09 | 2025-11-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 75/5 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-18 | 2025-11-16 | 2025-11-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 34/3 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-19 | 2025-11-16 | 2025-11-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 101/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-20 | 2025-11-16 | 2025-11-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 71/1 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-22 | 2025-11-16 | 2025-11-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 33/2 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-22 | 2025-11-16 | 2025-11-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 90/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-25 | 2025-11-23 | 2025-11-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 29/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-25 | 2025-11-23 | 2025-11-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 40/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-28 | 2025-11-23 | 2025-11-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 72/6 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-28 | 2025-11-23 | 2025-11-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 88/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 100/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 103/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 109/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 71/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 85/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-11-30 | 2025-11-30 | 2025-11-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 89/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-02 | 2025-11-30 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 29/1 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-03 | 2025-11-30 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 75/3 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-08 | 2025-12-07 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 69/3 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-10 | 2025-12-07 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 5/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-11 | 2025-12-07 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 80/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-12 | 2025-12-07 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 108/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-12 | 2025-12-07 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 111/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-14 | 2025-12-14 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 29/4 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-14 | 2025-12-14 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 48/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-17 | 2025-12-14 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 29/3 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-18 | 2025-12-14 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 75/4 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-18 | 2025-12-14 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 99/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-19 | 2025-12-14 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 102/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-19 | 2025-12-14 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 84/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-21 | 2025-12-21 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 111/1 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-21 | 2025-12-21 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 83/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-21 | 2025-12-21 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 91/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-21 | 2025-12-21 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 93/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-22 | 2025-12-21 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 34/1 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-23 | 2025-12-21 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 25/1 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-23 | 2025-12-21 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 70/3 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-25 | 2025-12-21 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 29/2 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-25 | 2025-12-21 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 4/1 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-27 | 2025-12-21 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 112/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-27 | 2025-12-21 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 49/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-27 | 2025-12-21 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 91/1 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-28 | 2025-12-28 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 79/1 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-28 | 2025-12-28 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 91/2 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-31 | 2025-12-28 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 114/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-31 | 2025-12-28 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 70/2 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-31 | 2025-12-28 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 77/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-31 | 2025-12-28 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 86/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-31 | 2025-12-28 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 91/8 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2025-12-31 | 2025-12-28 | 2025-12-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 94/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-02 | 2025-12-28 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 41/2 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-03 | 2025-12-28 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 11/2 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-04 | 2026-01-04 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 70/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-07 | 2026-01-04 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 40/1 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-09 | 2026-01-04 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 97/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-10 | 2026-01-04 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 41/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-11 | 2026-01-11 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 113/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-11 | 2026-01-11 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 76/3 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-12 | 2026-01-11 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 91/5 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-13 | 2026-01-11 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 110/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-14 | 2026-01-11 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 115/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-14 | 2026-01-11 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 8/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-15 | 2026-01-11 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 76/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-18 | 2026-01-18 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 69/4 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-19 | 2026-01-18 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 75/1 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-21 | 2026-01-18 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 50/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-24 | 2026-01-18 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 11/1 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-25 | 2026-01-25 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 123/2 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-27 | 2026-01-25 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 129/1 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-27 | 2026-01-25 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 34/2 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-28 | 2026-01-25 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 47/1 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-28 | 2026-01-25 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 79/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-29 | 2026-01-25 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 132/1 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-29 | 2026-01-25 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 69/1 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-29 | 2026-01-25 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 91/7 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-30 | 2026-01-25 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 96/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-31 | 2026-01-25 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 128/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-31 | 2026-01-25 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 131/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-31 | 2026-01-25 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 75/2 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-01-31 | 2026-01-25 | 2026-01-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 91/4 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-05 | 2026-02-01 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 59/1 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-05 | 2026-02-01 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 73/6 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-05 | 2026-02-01 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 76/1 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-05 | 2026-02-01 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 81/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-05 | 2026-02-01 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 96/1 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-08 | 2026-02-08 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 104/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-08 | 2026-02-08 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 42/1 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-10 | 2026-02-08 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 126/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-10 | 2026-02-08 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 43/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-11 | 2026-02-08 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 72/7 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-11 | 2026-02-08 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 9/1 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-12 | 2026-02-08 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 78/2 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-14 | 2026-02-08 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 95/3 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-16 | 2026-02-15 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 95/1 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-17 | 2026-02-15 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 131/3 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-18 | 2026-02-15 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 129/2 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-18 | 2026-02-15 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 6/1 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-18 | 2026-02-15 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 95/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-19 | 2026-02-15 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 131/1 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-19 | 2026-02-15 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 44/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-20 | 2026-02-15 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 30/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-22 | 2026-02-22 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 10/3 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-22 | 2026-02-22 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 124/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-22 | 2026-02-22 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 71/2 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-23 | 2026-02-22 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 70/1 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-23 | 2026-02-22 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 72/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-25 | 2026-02-22 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 127/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-28 | 2026-02-22 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 132/2 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-28 | 2026-02-22 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 132/3 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-02-28 | 2026-02-22 | 2026-02-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 95/2 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-06 | 2026-03-01 | 2026-03-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 31/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-08 | 2026-03-08 | 2026-03-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 35/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-10 | 2026-03-08 | 2026-03-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 10/1 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-10 | 2026-03-08 | 2026-03-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 129/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-10 | 2026-03-08 | 2026-03-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 130/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-10 | 2026-03-08 | 2026-03-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 82/2 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-11 | 2026-03-08 | 2026-03-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 82/1 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-12 | 2026-03-08 | 2026-03-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 116/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-14 | 2026-03-08 | 2026-03-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 27/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-18 | 2026-03-15 | 2026-03-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 5/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-19 | 2026-03-15 | 2026-03-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 125/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-28 | 2026-03-22 | 2026-03-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 47/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-29 | 2026-03-29 | 2026-03-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 132/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-31 | 2026-03-29 | 2026-03-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 34/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-03-31 | 2026-03-29 | 2026-03-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 7/2 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-04-13 | 2026-04-12 | 2026-04-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 92/0 | 1
TB 608 | TB 608 | tb608 |  | filename | 2026-04-05 | 2026-04-19 | 2026-04-19 | 2026-04-01 | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | detail | detail_date | 107/1 | 1

## Coverage
project_code | project_display | status | reason_code | reason | source_used | snapshot_limited | workbook | configured_sheet | resolved_sheet | detail_rows | detail_completions | snapshot_rows | first_event_date | last_event_date | first_report_date | last_report_date | available_sheets
TA 413 | TA 413 | OK_DETAIL | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | detail | No | TA 413 - DPR - 2026-05-20.xlsx | Foundation | Foundation | 316 | 316 | 1 | 2024-06-06 | 2026-03-05 | 2026-05-20 | 2026-05-20 | Final checking; Accessories; Area; Bird Guard ; Check Survey ; Crossing status; Detailed Survey ; Earthing; Erection; Foundation; Foundation Daily Progress; Hardware Supply; JUMPER Details; L2 Plan vs Actual; Location Summary; OPGW; ROW Tracker; S-Curve Erection; S-Curve FDN; S-Curve Stringing; Statutory Proposals; Stretch readiness ; Stretch readiness (2); Stringing; Supply Status; Survey summary; TA413_PBNTL; Tack Welding; Tower Abstarct ; Tower Abstract sheet; Tower PRS abstract ; Visual Chart
TA 414 | TA 414 | OK_DETAIL | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | detail | No | TA 414 - DPR - 2026-05-21.xlsx | FDN | FDN | 327 | 327 | 1 | 2024-05-15 | 2026-05-20 | 2026-05-21 | 2026-05-21 | 765KV TA 414 VNTL; Crossing; DPR Sheet; Erection ; Erection Compiled; Erection Completed ; FDN; FDN Completed; Pile Fdn; Project Details; Sheet1; Sheet2; Sheet3; Sheet4; Sheet5; Sheet6; Sheet7; Soil Inv.; Stringing; Stringing Compiled; Stringing Completed; Survey; Survey Anx; VNTL - KEC; Visual chart
TA 416 | TA 416 | OK_DETAIL | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | detail | No | TA 416 - DPR - 2026-05-17.xlsx | Progress. | Progress. | 700 | 606 | 1 | 2024-04-24 | 2026-02-09 | 2026-05-17 | 2026-05-17 | Crossing Details; Erection Compiled ; MASTER SHEET; PENDING ERE DETAILS; PENDING FDN DETAILS; Progress.; Project Details; Stringing compiled; TS; TS (2); TSE-MANUAL-LT-11KV-33KV Details; Visual chart.
TA 418 | TA 418 | OK_DETAIL | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | detail | No | TA 418 - DPR - 2026-05-21.xlsx | Progress | Progress | 281 | 249 | 1 | 2024-01-07 | 2026-02-24 | 2026-05-21 | 2026-05-21 | Crossing Details; Erection Compiled; MASTER SHEET; PENDING FDN DETAILS; Progress; Project Details; ROW TRACKER; Stringing Compiled; TS; TS (2); TSE-MANUAL-LT-11KV-33KV Details; Visual Chart
TA 419 | TA 419 | OK_DETAIL | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | detail | No | TA 419 - DPR - 2026-05-18.xlsx | FDN | FDN | 330 | 269 | 1 | 2024-05-21 | 2026-05-17 | 2026-05-18 | 2026-05-18 | Summary; Const Revenue; DPR_TA419; Detailed Survey; ERECTION COMPILED; ERT; Erection Daily Progress; Erection productivity; FDN; Foundation Daily Progress; Foundation Daily Progresss; Ins Hosting; L2; Latest Tower Schedule; PGCIL; Pkg 2_Erection; Pkg 2_Foundation; Pkg2_Stringing; Project details; RATE; ROW; Sheet10; Sheet7; Sheet8; Sheet9; Soil Inv; Statutory; Stock Details; Stringing; Stringing Stretch Readiness; Supply; Supply Status; TOWER ABSTRACT; TOWER SUPPLY; Tack Welding; Tower Schedule; Tower schedule_07.03.25; Visual Chart; dont change
TA 421 | TA 421 | OK_DETAIL | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | detail | No | TA 421 - DPR - 2026-05-18.xlsx | ProGress Sheet | ProGress Sheet | 996 | 915 | 1 | 2024-01-02 | 2026-01-08 | 2026-05-18 | 2026-05-18 | Erection Compiled ; Erection Productivity ; Hardwares & Tower Accessories ; Master Sheet; ProGress Sheet ; Project Details; Stringing Compiled ; Stubs and Towers ; SuPPLY ; Tack Welding ; Tower Accessories ; Tower Tightening ; Visual Chart ; X-ing Details
TA 504 | TA 504 | SKIPPED_BLANK_CONFIG | SKIPPED_BLANK_CONFIG | Foundation sheet mapping left blank in DPR_Config; project explicitly skipped. | missing | No | TA 504 - DPR - 2026-05-21.xlsx |  |  | 0 | 0 | 0 |  |  |  |  | DPR_TA-504; Erection compiled; Location Summary; Project Details; Stringing Compiled; Tightening; VC_Lilo; VC_RMTL
TA 505 | TA 505 | OK_DETAIL | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | detail | No | TA 505 - DPR - 2026-05-19.xlsx | Foundation | Foundation | 374 | 373 | 1 | 2015-11-27 | 2026-05-18 | 2026-05-19 | 2026-05-19 | Balance Erc-RAJ; DPR-Summary; ERC ROW-MP; Earthing Status; Erection Compiled; Erection Productivity; Foundation; Project Details; Sheet1; Sheet2; Sheet3; Sheet4; Sheet5; Stringing Compiled; Visual Chart
TA 506 | TA 506 | SKIPPED_BLANK_CONFIG | SKIPPED_BLANK_CONFIG | Foundation sheet mapping left blank in DPR_Config; project explicitly skipped. | missing | No | TA 506 - DPR - 2026-05-21.xlsx |  |  | 0 | 0 | 0 |  |  |  |  | DPR_TA-506; Erection compiled; Location Summary; Project Details; Stringing; Tightening; Visual Chart
TA 509 | TA 509 | OK_DETAIL | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | detail | No | TA 509 - DPR - 2026-05-18.xlsx | FOUNDATION | FOUNDATION | 272 | 264 | 1 | 2025-01-01 | 2026-05-14 | 2026-05-18 | 2026-05-18 | CST Gantry To AP 68 Common Poin; DPR; EARTHING; ERECTION; Erc pivot; Erection productivity; FDN pivot; FOUNDATION; SUMMARY; SUPPLY; SURVEY STATUS ; SURVEY SUMMARY; Sheet1; VC-765kV MKTL; XING
TA 510 | TA 510 | OK_DETAIL | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | detail | No | TA 510 - DPR - 2026-05-20.xlsx | FDN; Pile Foundation | FDN; Pile Foundation | 87 | 85 | 1 | 2025-02-12 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 765KV ASOTL; 765KV TA 414 VNTL; AOTL - KEC; Crossing; DPR Sheet; Erection ; Erection Compiled ; FDN; Pile Foundation; Project Details; Sheet1; Sheet2; Sheet3; Sheet4; Sheet5; Sheet6; Sheet7; Soil Inv.; String; Stringing Compiled; Survey; Survey Anx; Tack welding; Tree Enumeration; Visual chart 1
TA 512 | TA 512 | OK_DETAIL | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | detail | No | TA 512 - DPR - 2026-05-20.xlsx | Foundation | Foundation | 308 | 302 | 0 | 2025-02-23 | 2026-05-09 | 2026-05-20 | 2026-05-20 | Accessories; CS; DPR Sheet ; DS; Earthing; Erection Compiled; Foundation; Hardware; Hindrance Record; L3 Plan; OPGW; Power line Crossings ; Project Details; Sheet1; Shield Wire Earthing; Statuary clearance; Stringing; Summary E; Summary S; Supply DPR ; Supply Status; TS Gantry - AP47; Tack Welding; Visual Chart; WIP
TA 513 | TA 513 | OK_DETAIL | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | detail | No | TA 513 - DPR - 2026-05-19.xlsx | FDN S-P; FDN S-F | FDN S-F; FDN S-P | 85 | 84 | 1 | 2025-03-22 | 2026-05-19 | 2026-05-19 | 2026-05-19 | Concrete; Crossing status; DPR S-F & S-P (2); ERT; Earthing S-F; Earthing S-P; Ere S-F ; Ere S-P ; Erection Compiled; FDN S-F; FDN S-P; Forest; LS; Master SF; Master SP; Proposal; Proposal .; ROW S-F; ROW S-P; Sheet1; Sheet2; Sheet4; Sheet5; Summary; Summary DPR; Supply; Supply.; Survey ; T.Abstract; T.Marking; TS SF; TS SP ; VC -SF; VC -SP
TA 515 | TA 515 | MAPPING_CONFIRMATION_REQUIRED | MAPPING_CONFIRMATION_REQUIRED | Detail rows are present but very few parseable completion dates were found. Foundation column mapping likely needs confirmation. | missing | No | TA 515 - DPR - 2026-05-11.xlsx | DPR | DPR | 14 | 0 | 0 |  |  |  |  | DPR; Erection Compiled; Store Stock; Visual chart
TA 601 | TA 601 | OK_DETAIL | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | detail | No | TA 601 - DPR - 2026-05-20.xlsx | Progress Sheet | Progress Sheet | 309 | 191 | 1 | 2025-05-03 | 2026-05-20 | 2026-05-20 | 2026-05-20 | Erection Compiled; Foundation & Erection; Master Sheet; Progress Sheet ; ROW; STRG Stretch ; SUPPLY; Stringing Compiled; Visual Chart; Visual Chart ; X-ing Details
TA 602 | TA 602 | OK_DETAIL | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | detail | No | TA 602 - DPR - 2026-05-18.xlsx | FDN | FDN | 143 | 143 | 1 | 2025-09-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 | Check Survey ; Composite-Survey(05-04-2026); DPR-KEC; Detail Survey; Earthing; Erection; FDN; Supply Status; Survey details; Visual Chart ; WIP; statuary clearance; statuary clearance (2)
TB 408 | TB 408 | BLOCKED_NO_SOURCE | BLOCKED_NO_SOURCE | Configured foundation sheet unavailable and no usable foundation/status fallback in raw DPR. | missing | No | TB 408 - DPR - 2026-05-11.xlsx | Foundation |  | 0 | 0 | 0 |  |  |  |  | Erection Compiled ; Project Details; Stringing Compiled
TB 501 | TB 501 | OK_DETAIL | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | detail | No | TB 501 - DPR - 2026-05-20.xlsx | Progress-132kV; Progress-220kV | Progress-132kV; Progress-220kV | 240 | 231 | 1 | 2024-08-12 | 2026-04-30 | 2026-05-20 | 2026-05-20 | Check Survey-132kV; Check Survey-220kV; Detail Survey-132kV; Detail Survey-220kV; Mail Body; Progress-132kV; Progress-220kV; Statutory; Stringing-132KV; Stringing-220kV; Summary; Supply; VC-132kV; VC-220kV
TB 507 | TB 507 | OK_DETAIL | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | detail | No | TB 507 - DPR - 2026-05-20.xlsx; TB 507 [MAIN] - DPR - 2026-05-20.xlsx | Foundation; Foundation | Foundation | 346 | 335 | 1 | 2025-01-17 | 2026-05-20 | 2026-05-20 | 2026-05-20 | Crossing Proposal; 400kV Summery; 765kV Summery; Check Survey; Check Survey ; Check Survey Status; Check survey Loop In; Check survey Loop out; Completion date; Earthing; Erection ; Erection Compiled ; Final Check In And Tack Welding; Foundation; June; L2 Vs Actual Progress Chart; L2 Vs Actual Progress Chart (2); Project Details; ROW; Royalty; Sheet1; Sheet10; Sheet14; Sheet2; Sheet3; Sheet4; Sheet5; Sheet6; Sheet7; Sheet8; Sheet9; Soil Investigation; Statutory Clearence; Stringing Compiled ; Tower Schedule; VC; VC ; VC 51-121; VC 51-96; Visual Chart
TB 605 | TB 605 | OK_DETAIL | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | detail | No | TB 605 - DPR - 2026-05-20.xlsx | Foundation JS-Line -Jammu; LILO; Foundation -JS Line- Punjab | Foundation -JS Line- Punjab; Foundation JS-Line -Jammu; LILO | 317 | 288 | 1 | 2025-08-11 | 2026-05-19 | 2026-05-20 | 2026-05-20 | Benching Status-F; Benching Status-G; Approved CS J-S Line; Approved CS K-S Line; Approved Survey; Clear locs shared by client; Crossing; Earthing (PKG-F); Earthing (PKG-G); Earthing Pkg -G Ist section; Earthing balance; Eng.; Erection -Jammu; Erection -SK; Erection-Punjab; Eretion - PKG-F; Eretion - PKG-G; Fdn (Pkg -G Section -I); Foundation -JS Line- Punjab; Foundation -KS Line; Foundation JS-Line -Jammu; Hindrance; Insulator Hoisting - F; Insulator Hoisting - G; JMC 27.9.23; JS Supply Towers; JS-Supply Stubs; Jumpering-F; Jumpering-G; LILO; Manpower; Material Status-Jammu-Punjab; Material Status-Punjab; OPGW PKG-F; OPGW PKG-G; Painting - PKG-F; Painting - PKG-G; Planned Vs Actual -FDN; ROW; ROW Front vs Progress; Revetment Pkg-G; SK Supply Stubs; SK Supply Towers; Sheet1; Sheet10; Sheet11; Sheet12; Sheet13; Sheet13 (2); Sheet14; Sheet15; Sheet16; Sheet17; Sheet18; Sheet19; Sheet2; Sheet3; Sheet4; Sheet5; Sheet6; Sheet7; Sheet8; Sheet9; Stringing - PKG-F; Stringing - PKG-G; Sum; Supply Status; Survey-Summary; TB-605; TB401 DPR; TB401 DPR.....; Tack Welding - PKG-F; Tack Welding - PKG-G; Vertical Chart -JS Line Jammu ; Vertical Chart -JS Line Punjab
TB 608 | TB 608 | OK_DETAIL | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | detail | No | TB 608 - DPR - 2026-04-05.xlsm | WIP-FDN | WIP-FDN | 186 | 133 | 1 | 2025-10-18 | 2026-04-19 | 2026-04-05 | 2026-04-05 | DPR Sum.; Foundation Activity; Gang Movement; Line Details; Master Sheet; Master Sheet ; Sheet2; Supply; Support Required; Visual_Chart; WIP-ERC; WIP-FDN

## Diagnostics
Workbook | Project | Sheet | ConfiguredSheet | LineName | LineNameSource | Rows | DetailRows | Completions | ParserMode | FallbackNote | Status | Reason | TemplateSheet | TemplateApplied | TemplateChanges
TA 413 - DPR - 2026-05-20.xlsx | TA 413 | Foundation | Foundation |  | filename | 365 | 316 | 316 | template | XML scrub fallback used for sheet 'Foundation' | OK_TEMPLATE |  | TA 413 Foundation | TRUE | C3:2->Location No; C7:6->Foundation Completion Date; C17:16->Foundation Status
TA 414 - DPR - 2026-05-21.xlsx | TA 414 | FDN | FDN |  | filename | 329 | 327 | 327 | header | XML scrub fallback used for sheet 'FDN' | OK |  |  | FALSE
TA 416 - DPR - 2026-05-17.xlsx | TA 416 | Progress. | Progress. |  | filename | 726 | 700 | 606 | header |  | OK |  |  | FALSE
TA 418 - DPR - 2026-05-21.xlsx | TA 418 | Progress | Progress |  | filename | 302 | 281 | 249 | header |  | OK |  |  | FALSE
TA 419 - DPR - 2026-05-18.xlsx | TA 419 | FDN | FDN |  | filename | 340 | 330 | 269 | header | XML scrub fallback used for sheet 'FDN' | OK |  |  | FALSE
TA 421 - DPR - 2026-05-18.xlsx | TA 421 | ProGress Sheet | ProGress Sheet |  | filename | 1013 | 996 | 915 | header |  | OK |  |  | FALSE
TA 505 - DPR - 2026-05-19.xlsx | TA 505 | Foundation | Foundation |  | filename | 401 | 374 | 373 | template |  | OK_TEMPLATE |  | TA 505 Foundation | TRUE | C3:2->Location No; C22:21->Foundation Starting Date; C23:22->Foundation Completion Date
TA 509 - DPR - 2026-05-18.xlsx | TA 509 | FOUNDATION | FOUNDATION |  | filename | 274 | 272 | 264 | template |  | OK_TEMPLATE |  | TA 509 Foundation | TRUE | C2:1->Location No; C6:5->Foundation Status; C9:8->Foundation Completion Date
TA 510 - DPR - 2026-05-20.xlsx | TA 510 | FDN | FDN | FDN | config | 258 | 86 | 84 | header | XML scrub fallback used for sheet 'FDN' | OK |  |  | FALSE
TA 510 - DPR - 2026-05-20.xlsx | TA 510 | Pile Foundation | Pile Foundation | Pile | config | 3 | 1 | 1 | header | XML scrub fallback used for sheet 'Pile Foundation' | OK |  |  | FALSE
TA 512 - DPR - 2026-05-20.xlsx | TA 512 | Foundation | Foundation |  | filename | 357 | 308 | 302 | template |  | OK_TEMPLATE |  | TA 512 Foundation | TRUE | C4:3->Loc. No.; C7:6->Start; C8:7->Completed
TA 513 - DPR - 2026-05-19.xlsx | TA 513 | FDN S-P | FDN S-P | S-P | config | 75 | 60 | 59 | header |  | OK |  |  | FALSE
TA 513 - DPR - 2026-05-19.xlsx | TA 513 | FDN S-F | FDN S-F | S-F | config | 36 | 25 | 25 | header |  | OK |  |  | FALSE
TA 515 - DPR - 2026-05-11.xlsx | TA 515 | DPR | DPR |  | filename | 21 | 14 | 1 | rowwise |  | OK_ROWWISE |  |  | FALSE
TA 601 - DPR - 2026-05-20.xlsx | TA 601 | Progress Sheet | Progress Sheet |  | filename | 336 | 309 | 191 | template |  | OK_TEMPLATE |  | TA 601 Foundation | TRUE | C3:2->Location No; C9:8->Foundation Status; C13:12->Foundation Completion Date
TA 602 - DPR - 2026-05-18.xlsx | TA 602 | FDN | FDN |  | filename | 155 | 143 | 143 | template |  | OK_TEMPLATE |  | TA 602 Foundation | TRUE | C3:2->Loc. No.; C6:5->Start; C7:6->Complete
TB 501 - DPR - 2026-05-20.xlsx | TB 501 | Progress-132kV | Progress-132kV | 132kV | config | 93 | 39 | 31 | template |  | OK_TEMPLATE |  | TB 501 132kV Foundation | TRUE | C2:1->Location No; C32:31->Foundation Status; C36:35->Foundation Completion Date; C45:44->Foundation Completion Date Backup
TB 501 - DPR - 2026-05-20.xlsx | TB 501 | Progress-220kV | Progress-220kV | 220kV | config | 413 | 201 | 200 | template |  | OK_TEMPLATE |  | TB 501 220kV Foundation | TRUE | C2:1->Location No; C39:38->Foundation Status; C45:44->Foundation Completion Date; C58:57->Foundation Completion Date Backup
TB 507 [MAIN] - DPR - 2026-05-20.xlsx | TB 507 | Foundation | Foundation | MAIN | config | 318 | 311 | 304 | template |  | OK_TEMPLATE |  | TB 507 MAIN Foundation | TRUE | C2:1->Location Number; C12:11->Foundation Starting Date; C13:12->Foundation Completion Date
TB 507 - DPR - 2026-05-20.xlsx | TB 507 | Foundation | Foundation | 765kV | config | 42 | 35 | 31 | template |  | OK_TEMPLATE |  | TB 507 765kV Foundation | TRUE | C2:1->Location Number; C13:12->Foundation Starting Date; C14:13->Foundation Completion Date
TB 605 - DPR - 2026-05-20.xlsx | TB 605 | Foundation JS-Line -Jammu | Foundation JS-Line -Jammu | Jammu | config | 110 | 104 | 95 | template |  | OK_TEMPLATE |  | TB 605 Jammu Foundation | TRUE | C2:1->Location No; C12:11->Foundation Completion Date; C14:13->Foundation Status
TB 605 - DPR - 2026-05-20.xlsx | TB 605 | LILO | LILO | LILO | config | 12 | 6 | 0 | template |  | NO_COMPLETION_DATES_TEMPLATE | Template columns resolved but completion dates were not parseable. | TB 605 LILO Foundation | TRUE | C2:1->Location No; C12:11->Foundation Completion Date; C13:12->Foundation Status
TB 605 - DPR - 2026-05-20.xlsx | TB 605 | Foundation -JS Line- Punjab | Foundation -JS Line- Punjab | Punjab | config | 214 | 207 | 193 | template |  | OK_TEMPLATE |  | TB 605 Punjab Foundation | TRUE | C2:1->Location No; C12:11->Foundation Completion Date; C13:12->Foundation Status
TB 608 - DPR - 2026-04-05.xlsm | TB 608 | WIP-FDN | WIP-FDN |  | filename | 344 | 186 | 133 | template |  | OK_TEMPLATE |  | TB 608 Foundation | TRUE | C2:1->LOC. NO.; C7:6->Start Date; C8:7->Completion Date

## Issues
Workbook | Project | Sheet | ConfiguredSheet | LineName | LineNameSource | Issue | Reason
TA 512 - DPR - 2026-05-20.xlsx | TA 512 |  | Foundation |  |  | MAPPING_CONFIRMATION_REQUIRED | Status snapshot fallback returned non-positive cumulative foundation value. Please confirm status/foundation mapping for this project.
TA 515 - DPR - 2026-05-11.xlsx | TA 515 |  | DPR |  |  | MAPPING_CONFIRMATION_REQUIRED | Detail rows=14, parseable completion rows=1. Please confirm foundation completion-date column mapping.
TB 408 - DPR - 2026-05-11.xlsx | TB 408 |  | Foundation |  |  | NO_TARGET_SHEET | Configured foundation sheet not found in project workbooks.
TB 605 - DPR - 2026-05-20.xlsx | TB 605 | LILO | LILO | LILO | config | NO_COMPLETION_DATES_TEMPLATE | Template columns resolved but completion dates were not parseable.