## Project Details
Project Name | Client Name | LOA Start Date | LOA End Date | Planning Engineer | PCH | Regional Manager | Project Manger | Section Incharge | Supervisor/Engineer

## 765KV TA 325 ANTL
| Project Code | TA 325 | Date |  | 2025-10-05 |  | President-T&D | Mr. Ganesh Srinivasan
| Project Name | 765KV D/C HEXA AHMEDABAD - NAVSARI TL (PKG 02) |  |  | NOA Start Date | 2023-03-23 | PCH | Mr. Sivaraman Natrajan
| Client Name | PGKTL |  |  | LOA End Date | 2024-12-22 | Regional Manager | Mr. Nitin Bandale
| Revised End Date | 2025-12-30 |  |  | Planning Engineer | Mr. Bikash Ranjan Pradhan | Project Manger | Mr. Sanjeev Garg
Survey Status
Activity | Unit | Final Est. Qty | L2 till Last Month | Submitted till Last Month | Approved till Last Month | Balance to Submit | Balance to Approve | L2 Submission Plan for Current Month | Progress For Month | Approved till Current Month | Remarks
Rout Alignment | km | 177.35 | 177.35 | 177.35 | 177.35 |  |  |  |  | 177.35 | Completed
Detailed Survey | km | 177.35 | 177.35 | 177.35 | 177.35 |  |  |  |  | 177.35 | Completed
Check Survey | km | 177.35 | 177.35 | 177.35 | 177.35 |  |  |  |  | 177.35 | Completed
Progress Status
Activity | Final Estimated Quantity | Cumulative L2 till Last Month (Aug'25) | Cumulative Progress till Last Month(Aug'25) | L2 for present Month | Plan for the Month | Today's Progress | Progress till Date for the Month | L2 till Current Month | Completed till Date | Balance Work | Under Progress | Gangs at Present | Remarks | ROW | Clear | Clear but Not approachable
Soil Investigation | 29 | 29 | 29 | 0 | 0 |  |  | 29 | 29 | 0 |  |  | Completed.
Foundation | 484 | 484 | 477 | 0 | 7 |  | 1 | 484 | 478 | 6 | 1 | 1 | 165/4 Loc WIP. | 0 | 5 | 5
Earthing | 484 | 484 | 477 | 0 | 7 |  | 1 | 484 | 478 | 6
Tower Erection | 484 | 484 | 378 | 0 | 82 | 1 | 8 | 484 | 386 | 98 | 29 | 34 | 29 Locations WIP, 5 gang shifting U/P | 45 | 13 | 12
Tack welding | 484 | 484 | 310 | 0 | 106 | 1 | 8 | 484 | 318 | 166 | 3 | 3 | 3 No Location WIP.
Stringing(Km) | 177.35 | 177.35 | 98.193 | 0 | 32.41 |  | 1.25 | 177.35 | 99.443 | 77.907 | 5.214 | 7 | 4 TSE, 2 manual , 1 hotline gang | 15.237 | 22.396

## Soil Inv.
ANTL PROJECT - SOIL INVESTIGATION LOCATIONS
Sl. No. | Loc. No. | Work Portion | Status | Classification | Approval Letter Status | Drawing Status
1 | AP101 | Vadodara | Completed
2 | AP102 | Vadodara | Completed
3 | AP103 | Vadodara | Completed
4 | AP104 | Vadodara | Completed
5 | AP105 | Vadodara | Completed
6 | AP120 | Vadodara | Completed
7 | AP129 | Vadodara | Completed
8 | AP134 | Vadodara | Completed
9 | AP136 | Vadodara | Completed
10 | AP141 | Vadodara | Completed
11 | AP146 | Vadodara | Completed
12 | 154/1 | Navsari | Completed | Sandy Wet | Received
13 | AP154 | Navsari | Completed | Sandy Wet
14 | AP157 | Navsari | Completed | BC | Received | Avail.
15 | AP162 | Navsari | Completed | BC | Received | Avail.
16 | AP167 | Navsari | Completed | BC | Received | Avail.
17 | AP179 | Navsari | Completed | BC | Received | Avail.
18 | AP185 | Navsari | Completed | BC | Received | Avail.
19 | AP196 | Navsari | Completed | BC | Received | Avail.
20 | AP203 | Navsari | Completed | BC | Received
21 | AP213 | Navsari | Completed | BC | Received
22 | AP229 | Navsari | Completed | WBC | Received | Avail.
23 | AP241 | Navsari | Completed | BC | Received
24 | AP244 | Navsari | Completed | BC | Received
25 | AP249 | Navsari | Completed
26 | AP252 | Navsari | Completed
27 | AP260 | Navsari | Completed | BC | Received | Avail.
28 | AP270 | Navsari | Completed
29 | AP274 | Navsari | Completed

## Daily
CURRENT STATUS OF FOUNDATION WORK IN PROGRESS LOCATIONS
Sl. No. | Loc No. | Tower Type | Classification | Gang Name | Man power | Start Date | Pit A | Pit B | Pit C | Pit D | Today's status | Plan for tomorrow | Target / Actual Completion | Gang Leader | Gang Leader Ph no. | KEC Supervisor | Section Incharge | Safety Steward | Material Total trip / Completed Trip | PGCIL | Remarks
1 | 165/4 | DD45+9 | PS | Kashtabhanjan | 15 | 2025-06-28 |  | PCC Completed | Frustum casting completed | 0 | Pit B PCC and Pit C frustum casting completed | Pit A PCC, Pit B Steel binding and Pit D excavation |  | Ram manohar | 748980795 | Digamber rathod / 9766653262 | Milan Mal / 7063322977 |  |  | Rahul Sharma / 9001890543 |  |  | 102/0
CURRENT STATUS OF TOWER ERECTION WORK IN PROGRESS LOCATIONS
Sl. No. | Loc No. | Tower Type | Total Tonnage of Tower (MT) | Gang Name | Fitter | Man power | Start Date | Productivity Planned (MT) | Tonnage done for the day(MT) | Cumm Tonnage done(MT) | Today's status | Plan for tomorrow | Target / Actual Completion | Gang Leader | Gang Leader Ph no. | KEC Supervisor | Section Incharge | Safety Steward | Material Total trip / Completed Trip | PGCIL | Remarks
1 | 102/0 | DD45+35 | 156.901 | Dhaneshwar Mahto | 12 | 40 |  | 0 | 0 | 0 | No work due to High tide as location is fully submerged in water | No work due to high tide | 2025-11-09 | Shiva | 9546473499 | Mohit / 7070782092 | Subash S / 7988331768 | Vivek Singh / 93347 69279 | 15/9 | Rahul Sharma / 9001890543 |  |  | 102/0
2 | 157/3 | DA+0 | 37.73 | Mithun Kumar (VNTL) | 7 | 33 | 2025-07-23 | 0 | 0 | 10 | Derrick pole installation and dewatering WIP | 3rd section | 2025-10-12 | Mithun | 9113363892 | Rejaul 9933336674 | Milan Mal / 7063322977 |  |  | Gobind Sukhla / 8650502454 |  |  | 237/0
3 | 202/0 | DD60+55 | 226.737 | Nasirudin 2 | 8 | 27 |  | 0 | 0 | 0 | Gang shifting U/P | Material shifting and ground assembling
4 | 203/0 | DD60+55 | 226.737 | Prayag Mahto | 10 | 30 |  | 0 | 0 | 0 | Gang shifting U/P | Material shifting and ground assembling |  | Prayag Mahto | 9905954299 | Khemlal 9799569820 | Milan Mal / 7063322977 | Aryan Yadav 9721127668 |  | Rahul Sharma / 9001890543
5 | 206/0 | DD60+25 | 141.874 | Jwala Singh | 8 | 27 |  | 0 | 0 | 35 | No work due to ROW | 3rd section after clearing ROW | 2025-10-18 | Suraj | 6305201858 | Abhishek Kumar 9128142998 | Milan Mal / 7063322977 | Santosh Kumar 9889476631 |  | Naresh Rathwa / 9712938627 |  |  | 215/0 | 45948 | #REF!
6 | 218/0 | DD60+0 | 80.408 | Emadur | 7 | 27 |  | 0 | 0 | 0 | Gang shifting U/P | Material shifting and ground assembling
7 | 217A/2 | DA+0 | 37.73 | Manirul Haque / Rulu-2 | 7 | 23 | 2025-10-04 | 4 | 4 | 8 | 2nd section is u/p. | 2nd and 3rd section | 2025-10-10 | Rulu Sekh | 9748515261 |  | Milan Mal / 7063322977 | [5 empty] | 236/0
8 | 223/1 | DA+0 | 37.73 | Teklal Mahto | 6 | 26 | 2025-10-06 | 5 | 4 | 12 | 2nd section U/P | 3rd section | 2025-10-13 | Deglal Mahto | 7061046700 | Kalicharan / 7999828516 | Milan Mal / 7063322977 | Rohit / 9771254634 |  | Hashmukh Prajapati / 9824175156 | Material shifting plan for today |  | 245/1
9 | 225/1 | DA+6 | 44.728 | Muni Bibi | 8 | 30 | 2025-10-08 | 0 | 0 | 0 | Gang and T&P shifting completed and material shifting U/P | 1st section | 2025-10-15 | Ashraful | 9382586568 | Vikash Bishnoi / 9462802216 | Milan Mal / 7063322977 | Akhilesh Kumar / 6207417388 |  | Deepak Khadeekar / 7000938170 |  |  | 242/2
10 | 224/0 | DC+6 | 74.632 | Nasirudin | 9 | 20 | 2025-10-05 | 5 | 3 | 15 | 2nd section completed and 3rd section U/P | 3rd section | 2025-10-15 | Nijamul | 8392001517 | Govind Mahto | Milan Mal / 7063322977 | Arif Khan 8789210732 |  | Hashmukh Prajapati / 9824175156 | 3 trip material shifting completed and 4 trip material loading WIP |  | 273/0
11 | 229/3 | DA+0 | 37.73 | Modina India-3 (PGCIL) | 7 | 28 | 2025-10-05 | 5 | 0 | 12 | 2nd section U/P and work stopped due to not availibility of 11 kv line shutdown | 3rd section | 2025-10-12 | Abdul Kalam | 8250547694 | Ramlagan / 9199759709 | Milan Mal / 7063322977 | Raghunath Mandal / 9800733539 | 4/4 | Deepak Khadeekar / 7000938170 | Material Shifting Completed |  | 276/0
12 | 229/5 | DA+0 | 37.73 | Dildar Electrical-3 | 7 | 27 | 2025-10-08 | 4 | 4 | 4 | 1st section U/P | 1st section | 2025-10-13 | Manshoor/Sahim | 97733235217 | Ramlagan / 9199759709 | Milan Mal / 7063322977 | Pintu 9771254634 | 4/4 | Deepak Khadeekar / 7000938170 | Material shifting plan for today |  | 246/0
13 | 230/0 | DD60+0 | 80.408 | Javir Hossen | 6 | 16 |  | 0 | 0 | 0 | Materials shifting and ground assembling is u/p. | 1st section | 2025-10-22 | Md Javir | 9593717231 | Md Alamgir / 8116173246 | Milan Mal / 7063322977 |  |  | Deepak Khadeekar / 7000938170 | Material shifting plan for today Awaiting confirmation from Client for clearance of ROW |  | 237/5
14 | 231/0 | DD60+6 | 94.408 | Manirul Haque / Rulu-1 | 7 | 24 |  | 0 | 0 | 0 | Material sorting and ground assembling U/P | 1st section | 2025-10-25 | Lalchand |  |  | Milan Mal / 7063322977 | Vijay Pal 7318438253 | 9/2 | Deepak Khadeekar / 7000938170 | Material shifting plan for today Awaiting confirmation from Client for clearance of ROW |  | 242/0
15 | 233/0 | DD45+0 | 72.238 | Anita Devi | 15 | 45 | 2025-10-06 | 5 | 5 | 10 | Ist section is completed | 2nd section | 2025-10-15 | Hemlal Mahto | 6202654628 | Janki Mahto | Milan Mal / 7063322977 | Ashok Kumar 9887502909 |  | Deepak Khadeekar / 7000938170 | Material shifting plan for today Awaiting confirmation from Client for clearance of ROW |  | 237/3
16 | 234/0 | DD45+0 | 72.238 | MD Akhtar | 8 | 34 | 2025-09-18 | 6 | 6 | 72.238 | X-arm completed. Erection completed | Tightening and gang shifting to 235/0 | 2025-10-11 | Akhtarul Haque | 8670708587 | B K Singh 7549288822 | Gurveet Singh / 9149702860 | Rohit 6299338616 |  | Deepak Khadeekar / 7000938170 | ROW since 02-Oct-25 |  | 234/0
16 | 235/0 | DC2+3 | 66.268 | MD Akhtar |  |  |  | 0 | 0 | 0 |  | Gang shifting |  | Akhtarul Haque | 8670708587 | B K Singh 7549288822 | Gurveet Singh / 9149702860 | Rohit 6299338616
17 | 236/0 | DB+0 | 54.418 | Subhash | 8 | 28 | 2025-09-23 | 6 | 6 | 25 | 3rd Section completed and bottom section WIP | Middle section and top section | 2025-10-12 | Mahadev | 9525701017 | Harsh / 7772024400 | Gurveet Singh / 9149702860 | Triloki / 9336598740 |  | Deepak Khadeekar / 7000938170 | Material Shifting Completed |  | 229/3
18 | 237/0 | DD45+9 | 89.146 | Rupesh | 7 | 35 | 2025-10-06 | 5 | 5 | 10 | Ist section is u/p. | 2nd section | 2025-10-18 | Rupesh | 7631445752 8247816848 | Rezaul Haque 9933412695 | Gurveet Singh / 9149702860 | Harendra Mehta 7209849293 |  | Deepak Khadeekar / 7000938170 | 3 Trip Completed & 4 Trip Balance & planned to complete today ROW Since 01-Oct-25 |  | 247/3
19 | 237/1 | DA+0 | 37.73 | Muni Bibi-2 | 8 | 24 | 2025-10-07 | 4 | 4 | 9 | Ist section is completed and 2nd section u/p. | 2nd section | 2025-10-11 | Asirul | 8116042648 | Abu Alam / 8507642198 | Gurveet Singh / 9149702860 | Rupesh Kumar / 7272979782 |  | Deepak Khadeekar / 7000938170 | 2 trip Material shifting done |  | 237/4
20 | 237/2 | DA-3 | 36.045 | Modina India-1&4 (PGCIL) | 12 | 36 | 2025-10-05 | 5 | 4 | 10 | 2nd section U/P | 3rd section | 2025-10-10 | Rahul | 8709096040 | Abu Alam / 8507642198 | Gurveet Singh / 9149702860 | Nitish / 7418271962 |  | Deepak Khadeekar / 7000938170 | 1 Trip Balance & planned to complete today |  | 237/2
21 | 237/4 | DA+0 | 37.73 | Sukruddin | 8 | 34 | 2025-10-05 | 6 | 6 | 25 | Bottom section completed and middle section U/P | Top and X-arm | 2025-10-08 | Saddam | 9735945842 | Vikash Sharma / 7579979909 | Gurveet Singh / 9149702860 | Amresh Kumar Tiwari / 9631465980 |  | Deepak Khadeekar / 7000938170 |  |  | 237/6
22 | 237/6 | DA+3 | 39.4589 | Dildar Electrical-2_PGCIL | 10 | 29 | 2025-10-03 | 6 | 4 | 8 | Ist section is completed and 2nd section u/p. | 2nd and 3rd section section | 2025-10-12 | Masidur | 8617627491 |  | Gurveet Singh / 9149702860 | Sandeep Gautam / 8009922456 |  | Deepak Khadeekar / 7000938170 | Material Shifting Completed |  | 244/0
23 | 239/0 | DD60+25 | 141.874 | Laldev | 8 | 28 |  | 0 | 0 | 0 | Gang shifting U/P | Material shifting and ground assembling
24 | 241/0 | DB2+9 | 65.757 | SakiLa Khatun | 8 | 26 |  | 0 | 0 | 0 | Material shifting and ground assembling U/P | 1st section | 2025-10-06 | MD Ulhaq | 9679172400 | Baleshwar | Bibhukalyan Das / 8073102751 | Abdullah 6207450105 |  | Deepak Khadeekar / 7000938170 |  | 241/0 | 224/0
25 | 242/2 | DA-3 | 36.045 | Gokul-1 | 8 | 26 | 2025-10-03 | 5 | 4 | 25 | 3rd Section completed and bottom section WIP | Middle section and top section | 2025-10-11 | Animesh Sarkar | 9635949231 | Nunuchand 9685480040 | Bibhukalyan Das / 8073102751 | Parmatma 8009460313 |  | Deepak Khadeekar / 7000938170 | 2 trip Material shifting done (80 Mtr Shifting to be done) |  | 230/0
26 | 243/0 | DB+9 | 65.757 | Satish Kumar | 4 | 23 | 2025-10-07 | 4 | 4 | 8 | 1st section U/P | 1st snd 2nd section | 2025-10-17 | Satish | 9931126692 | Gauri Shankar 9253563632 | Bibhukalyan Das / 8073102751 | Roshan 6202450308 |  | Deepak Khadeekar / 7000938170 |  |  | 244/1
27 | 244/0 | DC+9 | 77.718 | Jaman Mahto-1 (Ratna Devi) | 8 | 38 | 2025-10-05 | 5 | 4 | 14 | 2nd section completed | 3rd section | 2025-10-18 | Chhaman Mahto | 7004691763 | Gauri Shankar 9253563632 | Bibhukalyan Das / 8073102751 | Ravindra 9691445222 |  | Deepak Khadeekar / 7000938170 | 1st trip material loading WIP |  | 233/0
28 | 244/1 | DB+9 | 65.757 | Gokul Sarkar-2 | 7 | 20 | 2025-10-06 | 5 | 3 | 8 | 2nd section U/P | 2nd and 3rd section | 2025-10-16 |  |  | Sabo | Bibhukalyan Das / 8073102751 |  |  | Deepak Khadeekar / 7000938170 | Material shifting plan for today Awaiting confirmation from Client for clearance of ROW |  | 157/3
29 | 245/1 | DA+0 | 37.73 | Senaul | 8 | 32 | 2025-09-05 | 5 | 4 | 29 | Middle section completed and top section U/P | Peak section and X-arm | 2025-10-10 | Samirul | 7671840805 | Nageshwar Mahto | Bibhukalyan Das / 8073102751 | Prince |  | Deepak Khadeekar / 7000938170 |  |  | 229/5
30 | 247/0 | DD60+0 | 80.408 | Rahul Kumar | 7 | 30 | 2025-10-08 | 3 | 3 | 3 | 1st section U/P | 1st section |  | Bipin | 8340613056 | Ravi Kumar 9431525402 | Bibhukalyan Das / 8073102751 | Mukesh 7493807619 |  | Deepak Khadeekar / 7000938170 |  | 247/0 | 231/0
31 | 247/2 | DA+3 | 39.4589 | Didar Electricals (PGCIL) | 10 | 29 |  | 0 | 0 | 0 | Gang shifting completed and material shifting U/P | Ground assembling and 1st section |  | Tarikul | 9933388787 | Bibhukalyan Das / 8073102751 | Bibhukalyan Das / 8073102751 | Abdullah |  | Deepak Khadeekar / 7000938170 |  |  | 223/1
32 | 273/0 | DB+0 | 54.418 | Modina India-2 (PGCIL) | 5 | 30 | 2025-09-20 | 6 | 3 | 25 | Bottom section is completed and middle section U/P | Middle section and top section | 2025-10-11 | Jitender Singh | 7759950858 | Anil Kumar | Mithun Samui / 7978177657 | Shubham Singh 7459830385 |  | Susheel Soni /9406535741
33 | 229/0 | DD60+18 | 129.341 | PC Construction 1 | 10 | 35 |  | 0 | 0 | 0 | Gang shifting U/P | Material shifting and ground assembling
34 |  |  |  | PC Construction 2 |  | 10 |  | 0 | 0 | 0 | Gang reached at store | Gang shifting
|  |  | 2542.7809 | Total | 268 | 970 |  | 99 | 80 | 377.238
CURRENT STATUS OF STRINGING WORK IN PROGRESS LOCATIONS
Sl. No. | Section | Length (Km) | Method | Gang Name | Fitter | Man power | P/O Start | P/O complete | F/S start | F/S complete | Today's status | Plan for tomorrow | Target / Actual Completion | Gang Leader | Gang Leader Ph no. | KEC Supervisor | Section Incharge | Safety Steward | Material Status | PGCIL | Remarks
1 | 158/0 - 158A/0 | 1.131 | TSE | Deepak Sarkar | 12 | 30 |  |  |  |  | Insulator hoisting completed at 158/1 and pilot paying out completed | Conductor paying out |  | Deepak Sarkar | 8250862021 | Sanjit Singh / 7632928609 | Milan Mal / 7063322977
2 | 158A/0-158B/0 | 0.481 | Hotline | Dharmendra | 8 | 17 | 2025-10-07 |  |  |  | Top Left phase final sag U/P | Balance final sag |  | Jagdish | 8788822587 | Sanjit Singh / 7632928609 | Milan Mal / 7063322977
3 | 191/0 - 191A/0 | 1.476 | TSE | Alam Construction |  | 13 |  |  |  |  | Gang shifting completed | Insulator hoisting |  | Aamir |  | Dularchand / | Abdul Mateen / 99323 93368
4 | 191A/0 - 192/0 | 0.611 | Manual | Enamul Haque |  | 13 |  |  |  |  | Insulator hoisting completed at 191A/1 | Back stay at 191A/0 & 192/0 and Conductor paying out |  | Safikul | 7908019141 | Laxman / 7000548302 | Abdul Mateen / 99323 93368
5 | 191A/0 - 192/0 | 0.611 | Manual | Md Anwar |  | 12 |  |  |  |  | Insulator hoisting completed at 191A/1 | Back stay at 191A/0 & 192/0 and Conductor paying out |  |  |  | Ranjeet singh / 7989943386 | Abdul Mateen / 99323 93368
6 | 195A/0 - 196/0 | 1.542 | TSE | Muslehuddin | 20 | 37 |  |  |  |  | Insulator hoisting completed at 195A/1, 195A/2, 196/0 and 195A/3 | Insulator hoisting at 195A/3, 195A/0 and pilot paying out |  | Giyash | 9732095699 | Abdul Mateen / 99323 93368 | Abdul Mateen / 99323 93368
7 | 272A/0 ~ 273/0 | 2.944 | TSE | Bhola |  | 50 | [5 empty] | Gang and T&P shifting
Formulas:
Target / Actual Completion = [Pit A]+7

## FDN-Compile
Sl. No. | Location No. | Tower Type | Classification | Revenue | Concreting Volume in M3 | Start Date | Todays Status | End Date | Remarks | Sub-Contractor Name
1 | 101/0 | DD60+35(6M RC) | FS |  | 440.345 | 2025-01-01 | Completed | 2025-02-02 |  | Rawat Construction
2 | 102/0 | DD45+35(11.84M RC) | PILE |  |  | 2025-03-06 | Completed | 2025-06-28 |  | AK Construction
3 | 104/0 | DD60+35 | PILE |  | 861.11 | 2024-11-17 | Completed | 2025-02-28 |  | Jai Mata Di
4 | 105/0 | DD60+35 | PILE |  | 861.114 | 2024-11-25 | Completed | 2025-01-17 |  | Jai Mata Di
5 | 106/0 | DD60+9 | WPS |  | 180.61 | 2024-05-21 | Completed | 2024-07-15 |  | JMD
6 | 106A/0 | DC2+0 | PS |  | 168.913 | 2024-11-18 | Completed | 2024-12-18 |  | Rawat Construction
7 | 106A/1 | DA+6 | PS | 1215596 | 83.812 | 2024-11-23 | Completed | 2024-12-10 |  | Rawat Construction
8 | 106A/2 | DA-3 | PS | 1086615 | 80.771 | 2024-11-23 | Completed | 2024-12-05 |  | Verma
9 | 106A/3 | DA+3 | WPS | 623377 | 40.634 | 2024-05-19 | Completed | 2024-06-10
10 | 106A/4 | DA+9 | WPS | 623377 | 40.634 | 2024-05-06 | Completed | 2024-05-16
11 | 106B/0 | DB2+9 | WPS | 2143792.36 | 65.135 | 2024-04-24 | Completed | 2024-06-06
12 | 106B/1 | DA+9 | WPS | 623377 | 40.634 | 2024-04-18 | Completed | 2024-04-26
13 | 106B/2 | DA+6 | WPS | 623377 | 40.634 | 2024-05-15 | Completed | 2024-05-24
14 | 107/0 | DD45+0 | WPS |  | 128.427 | 2024-03-31 | Completed | 2024-04-17
15 | 107/1 | DA-3 | WPS | 545016 | 39.126 | 2024-03-22 | Completed | 2024-04-01
16 | 108/0 | DD45+0 | WPS |  | 128.427 | 2024-08-14 | Completed | 2024-09-20 |  | Prince
17 | 109/0 | DB2+0 | WPS | 1196479 | 62.882 | 2024-07-02 | Completed | 2024-07-14 |  | Integar
18 | 110/0 | DB2+0 | WPS | 1196479 | 62.882 | 2024-07-16 | Completed | 2024-07-31 |  | Jyoti Construction (Departmental Gang)
19 | 111/0 | DC1+0 | WPS |  | 79.994 | 2024-08-03 | Completed | 2024-08-21 |  | Jyoti Construction (Departmental Gang)
20 | 112/0 | DD45+0 | WPS |  | 128.427 | 2024-01-18 | Completed | 2024-02-10
21 | 113/0 | DD60+0 | WPS |  | 178.19 | 2024-02-08 | Completed | 2024-05-09
22 | 114/0 | DD45+0 | WPS |  | 128.427 | 2024-07-31 | Completed | 2024-08-13 |  | Prince
23 | 115/0 | DC2+25 | WPS |  | 103.703 | 2024-07-08 | Completed | 2024-07-31 |  | Prince
24 | 116/0 | DD45+18 | WPS |  | 151.172 | 2024-07-17 | Completed | 2024-08-17 |  | B K Traders
25 | 116A/0 | DC1+0 | WPS |  | 79.994 | 2024-07-08 | Completed | 2024-07-17 |  | B K Traders
26 | 116A/1 | DA+0 | WPS | 545016 | 39.126 | 2024-11-21 | Completed | 2024-11-23
27 | 116B/0 | DD45+6 | WPS |  | 131.047 | 2024-08-18 | Completed | 2024-09-20 | No work due to approach road damaged badly. | B K Traders
28 | 117/0 | DD60+3 | WPS |  | 180.61 | 2024-07-16 | Completed | 2024-07-31 |  | Alamin Construction
29 | 118/0 | DD45+0 | WPS |  | 128.427 | 2024-07-09 | Completed | 2024-07-17 |  | Alamin Construction
30 | 119/0 | DD45+0 | WPS |  | 128.427 | 2024-07-10 | Completed | 2024-08-14 |  | Jeet Infra (Departmental Gang)
31 | 119/1 | DA-3 | WPS | 545016 | 39.126 | 2024-06-04 | Completed | 2024-06-08
32 | 119/2 | DA+0 | WPS | 545016 | 39.126 | 2024-06-08 | Completed | 2024-06-15
33 | 119/3 | DA+0 | WPS | 545016 | 39.126 | 2024-05-29 | Completed | 2024-06-03
34 | 120/0 | DD60+9 | WPS |  | 180.61 | 2024-08-17 | Completed | 2024-09-15 | Work hampered due to rain | Jeet Infra (Departmental Gang)
35 | 121/0 | DD60+18 | WPS |  | 201.075 | 2024-06-15 | Completed | 2024-07-18 |  | H K Construction
36 | 122/0 | DC1+6 | WPS |  | 82.223 | 2024-08-22 | Completed | 2024-09-22 |  | Haaji Saheb
37 | 123/0 | DD60+6 | WPS |  | 180.61 | 2024-08-03 | Completed | 2024-08-11 |  | Alamin Construction
38 | 123/1 | DA+3 | WPS | 623377 | 40.36 | 2024-09-20 | Completed | 2024-10-05 |  | Prince
39 | 124/0 | DC1+3 | WPS |  | 82.223 | 2024-09-20 | Completed | 2024-10-06 |  | B K Traders
40 | 124A/0 | DD60+0 | WPS |  | 178.19 | 2024-11-07 | Completed | 2024-11-14 |  | Alamin
41 | 124A/1 | DA+3 | WPS | 623377 | 40.634 | 2024-08-16 | Completed | 2024-08-18 |  | Alamin Construction
42 | 125/0 | DD60+6 | WPS |  | 180.61 | 2024-08-21 | Completed | 2024-11-07 |  | Alamin Construction
43 | 125A/0 | DB2+3 | WPS | 2143792.36 | 65.135 | 2024-09-12 | Completed | 2024-10-19 |  | Jyoti Construction (Departmental Gang)
44 | 126/0 | DC2+0 | WPS |  | 92.292 | 2023-12-23 | Completed | 2024-01-15
45 | 126/1 | DA+6 | WPS | 623377 | 40.63 | 2024-09-24 | Completed | 2024-10-11 |  | Hajji Saheb
46 | 127/0 | DD45+0 | WPS |  | 128.427 | 2023-11-11 | Completed | 2023-12-13
47 | 127/1 | DA+0 | WPS | 545016 | 39.126 | 2023-08-18 | Completed | 2023-08-29
48 | 127/2 | DA+0 | WPS | 545016 | 39.126 | 2023-08-28 | Completed | 2023-09-14
49 | 127/3 | DA+0 | WPS | 545016 | 39.126 | 2023-10-03 | Completed | 2023-11-02
50 | 127/4 | DA+3 | WPS | 623377 | 40.634 | 2023-10-16 | Completed | 2023-10-29
51 | 127/5 | DA+3 | WPS | 623377 | 40.634 | 2023-12-19 | Completed | 2024-01-04
52 | 128/0 | DD60+6 | WPS |  | 180.61 | 2024-09-24 | Completed | 2024-10-22 |  | Alamin Construction
53 | 129/0 | DD60+6 | WPS |  | 180.61 | 2024-10-07 | Completed | 2024-11-12 | No work due to approach road issues. | Prince Construction
54 | 129A/0 | DC1+0 | WPS |  | 79.994 | 2024-01-31 | Completed | 2024-02-15
55 | 129A/1 | DA+0 | WPS | 545016 | 39.126 | 2024-01-07 | Completed | 2024-02-02
56 | 129A/2 | DA+3 | WPS | 623377 | 40.634 | 2024-02-13 | Completed | 2024-02-24
57 | 130/0 | DB1+0 | WPS | 1017007 | 54.675 | 2024-01-12 | Completed | 2024-01-30
58 | 130/1 | DA+0 | WPS | 545016 | 39.126 | 2024-10-28 | Completed | 2024-11-20 |  | Haji Saheb
59 | 130/2 | DA+3 | WPS | 623377 | 40.634 | 2024-11-30 | Completed | 2024-12-07 |  | haji saheb
60 | 130/3 | DA+0 | WPS | 545016 | 39.126 | 2024-11-22 | Completed | 2024-12-02 |  | Hajji Saheb
61 | 130/4 | DA+3 | WPS | 623377 | 40.634 | 2024-11-24 | Completed | 2024-11-30
62 | 131/0 | DD45+3 | WPS |  | 131.047 | 2024-11-18 | Completed | 2024-12-06 |  | Arvind singh
63 | 132/0 | DC2+3 | WPS |  | 94.746 | 2024-10-15 | Completed | 2024-11-13 | No work due to waterlogged. | Hajji Saheb
64 | 132/1 | DA+0 | WPS | 545016 | 39.126 | 2024-11-18 | Completed | 2024-11-27
65 | 132/2 | DA+0 | WPS | 545016 | 39.126 | 2023-08-05 | Completed | 2023-08-14
66 | 132/3 | DA+0 | WPS | 545016 | 39.126 | 2023-06-12 | Completed | 2023-06-21
67 | 133/0 | DB1+0 | WPS | 1017007 | 54.675 | 2023-12-11 | Completed | 2024-01-10
68 | 133/1 | DA+0 | WPS | 545016 | 39.126 | 2023-08-28 | Completed | 2023-09-04
69 | 133/2 | DA+0 | WPS | 545016 | 39.126 | 2023-10-07 | Completed | 2023-10-29
70 | 133/3 | DA+0 | WPS | 545016 | 39.126 | 2023-10-28 | Completed | 2023-11-09
71 | 133/4 | DA+0 | WPS | 545016 | 39.126 | 2023-12-17 | Completed | 2023-12-26
72 | 133/5 | DA+0 | WPS | 545016 | 39.126 | 2023-11-19 | Completed | 2023-12-09
73 | 133A/0 | DB1+0 | WPS | 1017007 | 54.675 | 2023-12-11 | Completed | 2024-01-05
74 | 133A/1 | DA+0 | WPS | 545016 | 39.126 | 2023-11-07 | Completed | 2023-11-23
75 | 133A/2 | DA+6 | WPS | 623377 | 40.634 | 2023-11-22 | Completed | 2023-12-01
76 | 133A/3 | DA+0 | WPS | 545016 | 39.126 | 2023-12-31 | Completed | 2024-01-10
77 | 133A/4 | DA+6 | WPS | 623377 | 40.634 | 2023-08-11 | Completed | 2023-08-29
78 | 134/0 | DC2+25 | WPS |  | 103.7 | 2024-09-21 | Completed | 2024-10-26 |  | Jeet Infra (Departmental Gang)
79 | 135/0 | DC2+25 | WPS |  | 103.703 | 2024-12-02 | Completed | 2024-12-20 |  | Haaji Saheb
80 | 135/1 | DA+6 | WPS | 623377 | 40.634 | 2024-12-02 | Completed | 2024-12-24 |  | haji saheb
81 | 135/2 | DA+0 | WPS | 545016 | 39.126 | 2023-09-03 | Completed | 2023-09-24
82 | 135/3 | DA+0 | WPS | 545016 | 39.126 | 2023-10-03 | Completed | 2023-10-20
83 | 135/4 | DA+0 | WPS | 545016 | 39.126 | 2024-03-11 | Completed | 2024-03-20
84 | 135/5 | DA+0 | WPS | 545016 | 39.126 | 2024-02-27 | Completed | 2024-03-10
85 | 135/6 | DA+0 | WPS | 545016 | 39.126 | 2024-02-18 | Completed | 2024-02-26
86 | 135/7 | DA+0 | WPS | 545016 | 39.126 | 2025-03-26 | Completed | 2025-04-03
87 | 135A/0 | DC1+0 | PS |  | 138.086 | 2024-11-11 | Completed | 2024-12-08 |  | Niraj Tiwari
88 | 135A/1 | DD45+3 | WPS |  | 131.047 | 2024-05-07 | Completed | 2024-05-26
89 | 135A/2 | DB2+9 | WPS | 2143792.36 | 65.135 | 2024-05-21 | Completed | 2024-06-17
90 | 135A/3 | DA+0 | WPS | 545016 | 39.126 | 2023-08-26 | Completed | 2023-09-07
91 | 135A/4 | DA+0 | WPS | 545016 | 39.126 | 2023-08-10 | Completed | 2023-08-23
92 | 135A/5 | DA+0 | WPS | 545016 | 39.126 | 2024-12-02 | Completed | 2024-12-31 |  | Lal Hussain
93 | 135A/6 | DA+0 | WPS | 545016 | 39.126 | 2024-12-02 | Completed | 2024-12-17 |  | Neeraj Tiwari
94 | 135A/7 | DA+0 | WPS | 545016 | 39.126 | 2023-10-07 | Completed | 2023-10-29
95 | 135B/0 | DB1+0 | WPS | 1017007 | 54.675 | 2023-12-12 | Completed | 2023-12-30
96 | 135B/1 | DA+0 | WPS | 545016 | 39.126 | 2024-01-27 | Completed | 2024-02-06
97 | 135B/2 | DA+0 | WPS | 545016 | 39.126 | 2023-12-07 | Completed | 2023-12-20
98 | 135B/3 | DA+0 | WPS | 545016 | 39.126 | 2023-12-07 | Completed | 2023-12-17
99 | 135B/4 | DA+6 | WPS | 623377 | 40.634 | 2023-10-07 | Completed | 2023-10-19
100 | 135B/5 | DA+0 | WPS | 545016 | 39.126 | 2023-12-24 | Completed | 2023-12-31
101 | 135B/6 | DA+0 | WPS | 545016 | 39.126 | 2023-12-24 | Completed | 2024-01-05
102 | 135B/7 | DA+3 | WPS | 623377 | 40.634 | 2024-02-08 | Completed | 2024-02-17
103 | 136/0 | DD45+18(3M RC) | WPS |  | 161.632 | 2024-11-19 | Completed | 2024-12-28 |  | Lala rams
104 | 137/0 | DC2+9 (3M RC) | WPS |  | 112.877 | 2024-10-15 | Completed | 2024-12-23 |  | Himashi
105 | 137/1 | DA+3 | WPS | 623377 | 40.634 | 2024-02-29 | Completed | 2024-03-08
106 | 137/2 | DA+0 | WPS | 545016 | 39.126 | 2024-03-06 | Completed | 2024-03-14
107 | 137/3 | DA+0 | WPS | 545016 | 39.126 | 2024-03-09 | Completed | 2024-03-16
108 | 137/4 | DA+0 | WPS | 545016 | 39.126 | 2024-02-29 | Completed | 2024-03-10
109 | 137/5 | DA+3 | WPS | 623377 | 40.634 | 2024-11-22 | Completed | 2024-12-31 |  | Himanshi-01
110 | 137/6 | DA+0 | WPS | 545016 | 39.126 | 2024-11-24 | Completed | 2024-12-14 |  | Shree Krishna Const.
111 | 137A/0 | DB1+0 | WPS | 1017007 | 54.675 | 2024-12-15 | Completed | 2024-12-29 |  | Shree Krishna Const.
112 | 137A/1 | DA+6 | WPS | 623377 | 40.634 | 2024-12-01 | Completed | 2024-12-20 |  | Rabari Vankabhai
113 | 137A/2 | DA+0 | WPS | 545016 | 39.126 | 2024-12-21 | Completed | 2024-12-30 |  | Rabari Vankabhai
114 | 137A/3 | DA+6 | WPS | 623377 | 40.634 | 2024-03-14 | Completed | 2024-03-23
115 | 137A/4 | DA-3 | WPS | 545016 | 39.126 | 2024-04-13 | Completed | 2024-04-20
116 | 137A/5 | DA-3 | WPS | 545016 | 39.126 | 2024-04-19 | Completed | 2024-04-28
117 | 137A/6 | DA+9 | WPS | 623377 | 40.634 | 2024-10-28 | Completed | 2024-12-05 |  | Suresh Choudhary
118 | 138/0 | DB2+0 | WPS | 1196479 | 62.882 |  | Completed | 2024-12-17 |  | Nav Durga
119 | 138/1 | DA+6 | WPS | 623377 | 40.634 | 2024-12-03 | Completed | 2024-12-20 |  | Suresh Choudhary
120 | 138/2 | DA+0 | WPS | 545016 | 39.126 | 2024-12-27 | Completed | 2025-01-03 |  | SA Enterprises
121 | 139/0 | DB2+0 | WPS | 1196479 | 62.882 | 2024-12-28 | Completed | 2025-01-04 |  | Nav Durga
122 | 139/1 | DA+3 | WPS | 623377 | 40.634 | 2024-12-22 | Completed | 2024-12-28 |  | Rawat Construction
123 | 139/2 | DA+0 | WPS | 545016 | 39.126 | 2024-12-18 | Completed | 2024-12-24 |  | PR Construction
124 | 139A/0 | DB2+9 | WPS | 2143792.36 | 65.135 | 2024-12-19 | Completed | 2024-12-31 |  | Lala Ram
125 | 140/0 | DD60+0 | WPS |  | 178.19 | 2024-12-13 | Completed | 2024-12-23 |  | Nav Durga
126 | 141/0 | DD60+3 | WPS |  | 180.61 | 2024-12-16 | Completed | 2024-12-29 |  | Nav Durga
127 | 141/1 | DA+0 | WPS | 545016 | 39.126 | 2024-12-15 | Completed | 2024-12-27 |  | SA Enterprises
128 | 141/2 | DA-3 | WPS | 545016 | 39.126 | 2024-12-11 | Completed | 2024-12-27 |  | Pratibha
129 | 141/3 | DA+3 | WPS | 623377 | 40.634 | 2024-12-22 | Completed | 2024-12-31 |  | Pratibha
130 | 142/0 | DD60+0 | WPS |  | 178.19 | 2025-01-07 | Completed | 2025-01-16 |  | Nav Durga
131 | 143/0 | DD60+3 | WPS |  | 180.61 | 2025-01-18 | Completed | 2025-01-28 |  | Nav Durga
132 | 143A/0 | DD45+0 | WPS |  | 128.427 | 2025-01-15 | Completed | 2025-01-20 |  | Nav Durga
133 | 143A/1 | DA+6 | WPS | 623377 | 40.634 | 2025-01-28 | Completed | 2025-01-31 |  | Nav Durga
134 | 143A/2 | DD45+0 | WPS |  | 128.427 | 2025-01-30 | Completed | 2025-02-10 |  | Nav Durga
135 | 143A/3 | DD45+3 | WPS |  | 131.047 | 2024-11-18 | Completed | 2024-12-11 |  | Madhav Constr.
136 | 143A/4 | DA+0 | WPS | 545016 | 39.126 | 2024-11-21 | Completed | 2024-12-23 |  | Lalhusain
137 | 143A/5 | DA+3 | WPS | 623377 | 40.634 | 2024-06-19 | Completed | 2024-07-13 |  | Himanshi Agency
138 | 144/0 | DB2+3 | WPS | 2143792.36 | 65.135 | 2024-06-16 | Completed | 2024-06-26
139 | 144/1 | DA+0 | WPS | 545016 | 39.126 | 2024-06-11 | Completed | 2024-06-18
140 | 144/2 | DA+0 | WPS | 545016 | 39.126 | 2024-03-29 | Completed | 2024-04-06
141 | 144/3 | DA+0 | WPS | 545016 | 39.126 | 2024-03-22 | Completed | 2024-03-31
142 | 144/4 | DA+0 | WPS | 545016 | 39.126 | 2024-04-07 | Completed | 2024-04-15
143 | 144/5 | DA+0 | WPS | 545016 | 39.126 | 2024-03-15 | Completed | 2024-03-26
144 | 144A/0 | DB1+9 | WPS | 1108538 | 54.992 | 2024-04-03 | Completed | 2024-04-14
145 | 145/0 | DB1+18 | WPS | 1330245 | 61.574 | 2024-03-23 | Completed | 2024-04-04
146 | 145A/0 | DB1+6 | WPS | 1108538 | 54.992 | 2024-12-13 | Completed | 2024-12-21 |  | Himanshi
147 | 145A/1 | DA+3 | WPS | 623377 | 40.634 | 2024-03-09 | Completed | 2024-03-22
148 | 145A/2 | DA+3 | WPS | 623377 | 40.634 | 2025-01-19 | Completed | 2025-01-23 |  | Himanshi
149 | 145A/3 | DA+0 | WPS | 545016 | 39.126 | 2024-03-19 | Completed | 2024-03-27
150 | 146/0 | DC1+9 | WBC |  | 192.814 | 2024-12-12 | Completed | 2024-12-25 |  | Himanshi
151 | 147/0 | DC2+9 | WPS |  | 94.746 | 2024-12-07 | Completed | 2024-12-18 |  | Himanshi
152 | 147/1 | DC2+0 | WPS |  | 92.292 | 2024-05-20 | Completed | 2024-06-08
153 | 147/2 | DC1+0 | WPS |  | 79.994 | 2024-05-20 | Completed | 2024-06-03
154 | 147/3 | DA-3 | WPS | 545016 | 39.126 | 2024-05-16 | Completed | 2024-05-29
155 | 147/4 | DA+3 | WPS | 623377 | 40.634 | 2024-05-04 | Completed | 2024-05-17
156 | 147/5 | DA+6 | WPS | 623377 | 40.634 | 2024-04-20 | Completed | 2024-05-03
157 | 147/6 | DA-3 | WPS | 545016 | 39.126 | 2024-05-15 | Completed | 2024-05-25
158 | 147A/0 | DB1+18 | WPS | 1330245 | 61.574 | 2024-06-05 | Completed | 2024-06-14
159 | 147B/0 | DB1+18 | WPS | 1330245 | 61.574 | 2024-04-30 | Completed | 2024-05-10
160 | 147B/1 | DA+0 | WET | 881091 | 63.346 | 2024-11-25 | Completed | 2024-12-05 |  | Himanshi-01
161 | 148/0 | DC2+0 | WET |  | 134.785 | 2024-11-05 | Completed | 2024-11-20 |  | Himanshi Construction
162 | 148/1 | DA+3 | WET | 986514 | 65.631 | 2024-11-18 | Completed | 2024-11-27
163 | 148/2 | DA+0 | WPS | 545016 | 39.126 | 2024-11-19 | Completed | 2024-11-26
164 | 148/3 | DA+0 | WET | 881091 | 63.346 | 2024-11-24 | Completed | 2024-12-05 |  | BK Traders
165 | 148/4 | DA+0 | WPS | 545016 | 39.126 | 2024-06-13 | Completed | 2024-06-20
166 | 148/5 | DA+0 | WET | 881091 | 63.346 | 2024-11-24 | Completed | 2024-12-10 |  | Himanshi
167 | 148/6 | DA+0 | WET | 881091 | 63.346 | 2025-01-03 | Completed | 2025-01-06 |  | Himanshi
168 | 148/7 | DA+0 | WET | 881091 | 63.346 | 2025-01-04 | Completed | 2025-01-08 |  | Himanshi
169 | 149/0 | DB2+0 | WET | 1880164 | 89.905 | 2024-12-23 | Completed | 2024-12-31 |  | Himanshi
170 | 149/1 | DA+0 | WET | 881091 | 63.346 | 2024-12-24 | Completed | 2024-12-29 |  | Himanshi
171 | 150/0 | DD60+9 | WET |  | 255.731 | 2025-01-11 | Completed | 2025-01-28 |  | Himanshi
172 | 150/1 | DA+9 | WET | 986514 | 65.631 | 2025-01-07 | Completed | 2025-01-12 |  | Himanshi
173 | 150/2 | DA+3 | WET | 986514 | 65.631 | 2025-01-12 | Completed | 2025-01-16 |  | Himanshi
174 | 150/3 | DA+6 | WPS | 623377 | 40.634 | 2025-01-15 | Completed | 2025-01-18 |  | Himanshi
175 | 150A/0 | DC1+0 | WET |  | 117.033 | 2024-05-29 | Completed | 2024-06-11
176 | 150A/1 | DA+3 | WET | 986514 | 65.631 | 2024-05-08 | Completed | 2024-05-22
177 | 150A/2 | DA+0 | WET | 881091 | 63.346 | 2024-04-12 | Completed | 2024-04-26
178 | 151/0 | DB2+3 | WPS | 2143792.36 | 65.135 | 2025-01-20 | Completed | 2025-01-27 |  | Himanshi
179 | 152/0 | DC2+0 | WPS |  | 92.292 | 2024-05-19 | Completed | 2024-05-30
180 | 152/1 | DA+0 | WPS | 545016 | 39.126 | 2024-05-25 | Completed | 2024-05-31
181 | 152/2 | DA-3 | WPS | 545016 | 39.126 | 2024-04-25 | Completed | 2024-05-03
182 | 152/3 | DA-3 | WPS | 545016 | 39.126 | 2024-05-01 | Completed | 2024-05-09
183 | 152/4 | DA+0 | WPS | 545016 | 39.126 | 2024-05-05 | Completed | 2024-05-14
184 | 152A/0 | DB1+0 | WPS | 1017007 | 54.675 | 2024-12-16 | Completed | 2024-12-24 |  | BK Traders
185 | 153/0 | DD60+25(1M RC) | WET |  | 602.294 | 2024-12-18 | Completed | 2024-12-30 |  | BK Traders
186 | 154/1 | DD45+25(11.96 M RC) | PILE |  |  | 2025-01-24 | Completed | 2025-05-11 |  | Harshi
187 | 155/0 | DD60+0 | WET | 3915704.88 | 252.474 | 2024-04-16 | Completed | 2024-05-11
188 | 155/1 | DA+0 | PS | 1086615 | 80.771 | 2024-10-03 | Completed | 2024-10-24 |  | Jyoti Const.
189 | 155/2 | DA+3 | PS | 1215596 | 83.812 | 2024-10-03 | Completed | 2024-10-11 |  | Jyoti Const.
190 | 155/3 | DA+3 | WET | 986514 | 65.631 | 2024-04-08 | Completed | 2024-04-25
191 | 155/4 | DA+0 | WET | 881091 | 63.346 |  | Completed | 2025-04-12 |  | Nav Durga
192 | 155/5 | DA+0 | WET | 881091 | 63.346 | 2025-04-13 | Completed | 2025-04-16 |  | Nav Durga
193 | 155/6 | DA-3 | PS | 1086615 | 80.771 | 2024-10-15 | Completed | 2024-10-29 |  | M/s Rudra Associate
194 | 156/0 | DD60+3 | PS | 5188063.13 | 309.952 | 2024-10-30 | Completed | 2024-11-24 |  | Rudra Associate
195 | 157/0 | DD60+6 | PS |  | 309.952 | 2025-01-12 | Completed | 2025-01-29 |  | Anya Constr.
196 | 157/1 | DA+0 | PS | 1086615 | 80.771 | 2024-11-23 | Completed | 2024-12-20 |  | Anya Construction
197 | 157/2 | DA+0 | FS | 1287409 | 91.088 | 2024-12-27 | Completed | 2025-01-07 |  | Anya Construction.
198 | 157/3 | DA+0 | FS | 1287409 | 91.088 | 2024-12-18 | Completed | 2024-12-24 |  | Maa Bhawani
199 | 158/0 | DB2+0 | FS | 2986642.46 | 132.205 | 2025-01-23 | Completed | 2025-01-30 |  | NR road Contr.
200 | 158/1 | DA-3 | PS | 1086615 | 80.771 | 2025-01-23 | Completed | 2025-01-31 |  | NR road Contr.
201 | 158/2 | DA-3 | FS | 1287409 | 91.088 | 2025-01-10 | Completed | 2025-01-23 |  | Haaji Saheb
202 | 158A/0 | DD45+6 | WET | 3953330 | 192.374 | 2024-07-01 | Completed | 2024-07-30 |  | Kudiyaar
203 | 158B/0 | DD45+18 | PS | 5320583 | 257.278 | 2024-10-24 | Completed | 2024-10-31 |  | Maa Bhawani
204 | 158B/1 | DA+3 | PS | 1215596 | 83.812 | 2024-11-06 | Completed | 2024-11-09 |  | Maa Bhawani
205 | 158B/2 | DA+3 | PS | 1215596 | 83.812 | 2024-10-20 | Completed | 2024-10-26 |  | Maa Bhawani
206 | 159/0 | DB1+0 | WET | 1598139 | 79.944 | 2024-03-26 | Completed | 2024-04-04
207 | 159/1 | DA+0 | FS | 1287409 | 91.088 | 2024-11-27 | Completed | 2024-12-14 |  | Rudra Associate
208 | 159/2 | DCT+0 | FS |  | 158.016 | 2025-01-02 | Completed | 2025-01-13 | DC2+0 | NR road Contr.
209 | 159/3 | DA+0 | WET | 881091 | 63.346 | 2024-02-09 | Completed | 2024-02-16
210 | 159/4 | DA+0 | FS | 1287409 | 91.088 | 2024-11-26 | Completed | 2024-12-03 |  | Alamin
211 | 160/0 | DD60+18 | FS |  | 39.682 | 2024-12-28 | Completed | 2025-01-13 |  | Haji Saheb
212 | 161/0 | DD60+25 | PS |  | 341.95 | 2024-12-01 | Completed | 2024-12-30 |  | Tes Transco
213 | 162/0 | DD60+25 | PS |  | 341.95 | 2025-01-03 | Completed | 2025-01-24 |  | BK Traders
214 | 163/0 | DC2+0 | FS |  | 193.49 | 2024-12-14 | Completed | 2024-12-29 |  | Lala Ram
215 | 163/1 | DA+0 | WET | 881091 | 63.346 | 2024-01-29 | Completed | 2024-02-05
216 | 163/2 | DA+0 | WET | 881091 | 63.346 | 2024-01-24 | Completed | 2023-01-29
217 | 163/3 | DA+0 | WET | 881091 | 63.346 | 2024-01-17 | Completed | 2024-01-23
218 | 163/4 | DA+0 | WET | 881091 | 63.346 | 2024-02-08 | Completed | 2024-02-13
219 | 163/5 | DA+0 | FS | 1287409 | 91.088 | 2024-02-14 | Completed | 2024-02-23
220 | 163/6 | DA+0 | FS | 1287409 | 91.088 | 2024-02-22 | Completed | 2024-02-29
221 | 164/0 | DB2+0 | FS | 2986642.46 | 132.205 | 2024-10-21 | Completed | 2024-11-07 |  | Tes Transco
222 | 164/1 | DA+0 | FS | 1287409 | 91.088 | 2024-11-11 | Completed | 2024-11-28 |  | Tes Transco
223 | 164/2 | DA+0 | WET | 881091 | 63.346 | 2023-12-28 | Completed | 2024-01-17
224 | 164/3 | DA+0 | FS | 1287409 | 91.088 | 2024-12-04 | Completed | 2024-12-14 |  | Lala Ram
225 | 164/4 | DA+0 | WFR | 947845 | 60.634 | 2024-03-11 | Completed | 2024-03-22
226 | 164/5 | DA+0 | WFR | 947845 | 60.634 | 2024-02-12 | Completed | 2024-02-23
227 | 164/6 | DA+0 | PS | 1086615 | 80.771 | 2024-03-11 | Completed | 2024-03-22
228 | 164/7 | DA+0 | WET | 881091 | 63.346 | 2024-01-18 | Completed | 2024-01-29
229 | 165/0 | DB2+0 | PS | 2481749.46 | 115.247 | 2024-01-09 | Completed | 2024-01-21
230 | 165/1 | DA+0 | PS | 1086615 | 80.771 | 2024-01-30 | Completed | 2024-02-09
231 | 165/2 | DA+0 | WET | 881091 | 63.346 | 2024-02-13 | Completed | 2024-02-28
232 | 165/3 | DA+6 | WET | 986514 | 65.631 | 2024-02-28 | Completed | 2024-03-10
233 | 165/4 | DA+0 | WET | 881091 | 63.346 | 2023-10-20 | Completed | 2023-11-03
234 | 166/0 | DD60+6 | PS | 5188063.13 | 309.952 | 2024-11-28 | Completed | 2024-12-10 |  | Jyoti Constr.
235 | 167/0 | DD60+0 | WBC |  | 396.566 | 2025-01-06 | Completed | 2025-01-18 |  | Sukhriddin
236 | 167/1 | DA+9 | FS | 1442822 | 94.623 | 2024-12-21 | Completed | 2024-12-28 |  | Sukhriddin
237 | 167/2 | DA+6 | WET | 986514 | 65.631 | 2023-11-13 | Completed | 2023-11-30
238 | 167/3 | DA+6 | WPS | 623377 | 40.634 | 2023-11-23 | Completed | 2023-11-30
239 | 167/4 | DA+0 | WET | 881091 | 63.346 | 2023-12-09 | Completed | 2023-12-15
240 | 168/0 | DC1+0 | WET | 2328166.27 | 117.033 | 2025-03-13 | Completed | 2025-03-27 |  | Ammu Engg.
241 | 168/1 | DA-3 | WET | 881091 | 63.346 | 2024-11-09 | Completed | 2024-11-18 |  | M/s Rajesh Singh
242 | 168/2 | DA+0 | FS | 1287409 | 91.088 | 2024-10-07 | Completed | 2024-10-24 |  | M/s Rajesh Singh
243 | 169/0 | DD45+18 | PS | 5320583 | 257.278 | 2024-10-22 | Completed | 2024-11-06 |  | M/s Rajesh Singh
244 | 171/0 | DD60+25 (3M RC) | PS |  | 353.162 | 2024-10-26 | Completed | 2024-11-19 |  | Jyoti Const.
245 | 172/0 | DD60+25 | PS | 5611385.97 | 341.95 | 2024-12-16 | Completed | 2025-01-04 |  | Khodiyar Krupa
246 | 172/1 | DA+3 | PS | 1215596 | 83.812 | 2024-12-24 | Completed | 2024-12-28 |  | Value Constr.
247 | 172/2 | DA+6 | PS | 1215596 | 83.812 | 2024-12-29 | Completed | 2025-01-04 |  | Value Constr.
248 | 173/0 | DD60+25 | PS | 5611385.97 | 341.95 | 2024-12-10 | Completed | 2024-12-24 |  | Value Constr.
249 | 174/0 | DD60+18 | FS | 6685851 | 390.682 | 2025-02-11 | Completed | 2025-02-22 |  | Jyoti
250 | 174/1 | DB1+0 | PS | 2122856.48 | 98.821 | 2025-03-26 | Completed | 2025-03-30 |  | Jyoti
251 | 175/0 | DD45+0 | WET | 3743190.59 | 189.081 | 2025-03-22 | Completed | 2025-03-28 |  | Arvind
252 | 175/1 | DA+0 | WET | 881091 | 63.346 | 2025-03-16 | Completed | 2025-03-19 |  | Arvind
253 | 175/2 | DA+0 | WET | 881091 | 63.346 | 2025-05-18 | Completed | 2025-05-22 |  | Himanshi Construction
254 | 176/0 | DD60+0 | WET | 3915704.88 | 252.474 | 2025-05-15 | Completed | 2025-05-23 |  | Jyoti
255 | 177/0 | DD60+0 | PS | 4780790.5 | 306.052 | 2025-03-12 | Completed | 2025-03-22 |  | Jyoti
256 | 178/0 | DD60+6 | PS | 5188063.13 | 309.952 | 2024-12-23 | Completed | 2024-12-31 |  | Jyoti
257 | 179/0 | DD60+0 | WBC |  | 396.566 | 2024-12-31 | Completed | 2025-01-18 |  | Jyoti
258 | 180/0 | DD45+9 (3M RC) | WET |  | 213.318 | 2025-01-25 | Completed | 2025-01-31 |  | Jyoti
259 | 181/0 | DD45+18 | WET | 4465782 | 224.07 | 2025-02-02 | Completed | 2025-02-08 |  | Jyoti
260 | 181/1 | DA+0 | WET | 881091 | 63.346 | 2025-03-13 | Completed | 2025-03-20 |  | Himanshi
261 | 181/2 | DA+0 | WET | 881091 | 63.346 | 2025-03-03 | Completed | 2025-03-06 |  | Jyoti
262 | 181/3 | DA+0 | WET | 881091 | 63.346 | 2025-01-20 | Completed | 2025-01-23 |  | Jyoti
263 | 181/4 | DA+0 | WET | 881091 | 63.346 | 2025-02-25 | Completed | 2025-02-28 |  | Jyoti
264 | 182/0 | DD60+0 | WET | 3915704.88 | 252.474 | 2025-02-27 | Completed | 2025-03-13 |  | Arvind
265 | 182A/0 | DD45+6(2M RC) | PS |  | 239.926 | 2024-12-02 | Completed | 2024-12-22 |  | Jyoti
266 | 183/0 | DD60+25 | PS | 5611385.97 | 341.95 | 2025-04-07 | Completed | 2025-04-20 |  | Tes Transco
267 | 184/0 | DD60+25 | WET | 4801423 | 298.554 | 2024-12-28 | Completed | 2025-01-08 |  | Maa Bhawani
268 | 184/1 | DB1+6 | WET | 1741972 | 80.469 | 2025-02-20 | Completed | 2025-02-26 |  | Arvind
269 | 185/0 | DC2+0 | WET | 2530056 | 134.785 | 2025-02-27 | Completed | 2025-03-13 |  | Himanshi
270 | 185/1 | DA+9 | WET | 986514 | 65.631 | 2024-11-28 | Completed | 2024-11-30 |  | Jyoti
271 | 186/0 | DD60+35 | WET | 7665610 | 315.149 | 2024-12-28 | Completed | 2025-04-04 | Again start date is 30-03-2025 | Sukhriddin
272 | 187/0 | DD60+25 | WET | 4801423 | 298.554 | 2025-02-17 | Completed | 2025-03-03 |  | Jyoti-2
273 | 187/1 | DA+3 | WET | 986514 | 65.631 | 2025-03-04 | Completed | 2025-03-10 |  | Jyoti
274 | 187/2 | DA-3 | FS | 1287409 | 91.088 |  | Completed | 2024-04-13
275 | 187/3 | DA+0 | PS | 1086615 | 80.771 | 2024-03-09 | Completed | 2024-03-20
276 | 188/0 | DB1+6 | WET | 1741972 | 80.469 | 2024-04-01 | Completed | 2024-04-07
277 | 189/0 | DB2+6 | WET | 2143792.36 | 94.918 | 2024-03-22 | Completed | 2024-03-31
278 | 189/1 | DA+0 | WET | 881091 | 63.346 | 2025-01-06 | Completed | 2025-01-09 |  | Value Constr.
279 | 190/0 | DD45+25 | WET | 4465782 | 224.07 | 2024-11-30 | Completed | 2024-12-31 |  | Tes transco
280 | 191/0 | DD45+25 | WET | 4465782 | 224.07 | 2024-03-06 | Completed | 2024-03-17
281 | 191/1 | DA+0 | WET | 881091 | 63.346 | 2024-03-16 | Completed | 2024-03-21
282 | 191/2 | DA-3 | WET | 881091 | 63.346 | 2024-12-14 | Completed | 2024-12-21 |  | Khodiyar Krupa
283 | 191/3 | DA-3 | PS | 1086615 | 80.771 | 2024-12-17 | Completed | 2024-12-24 |  | Khodiyar Krupa
284 | 191A/0 | DB2+0 | WET | 1880164 | 89.905 | 2024-04-25 | Completed | 2024-05-13
285 | 191A/1 | DA-3 | FS | 1287409 | 91.088 | 2024-04-14 | Completed | 2024-04-21
286 | 192/0 | DC1+0 | PS | 3074652.99 | 138.086 | 2024-11-29 | Completed | 2024-12-14 |  | M/s Rajesh Singh
287 | 193/0 | DD60+6 | WET | 4251845 | 255.731 | 2024-04-21 | Completed | 2024-04-30
288 | 194/0 | DD60+6 | WET | 4251845 | 255.731 | 2025-03-19 | Completed | 2025-03-31 |  | Himanshi
289 | 195/0 | DC2+0 | PS | 3206945.94 | 168.913 | 2024-05-14 | Completed | 2024-05-24 | Again completed on 16-04-2025
290 | 195/1 | DA+6 | PS | 1215596 | 83.812 | 2024-12-30 | Completed | 2025-01-07 |  | Hari Krishna
291 | 195/2 | DA+0 | WET | 881091 | 63.346 | 2025-02-21 | Completed | 2025-02-26 |  | Himanshi
292 | 195/3 | DA+6 | PS | 1215596 | 83.812 | 2023-12-07 | Completed | 2023-12-26
293 | 195/4 | DA+0 | WET | 881091 | 63.346 | 2023-12-26 | Completed | 2024-01-12
294 | 195/5 | DA+6 | WBC | 1821043 | 113.924 | 2025-01-08 | Completed | 2025-01-16 |  | Hari Krishna
295 | 195A/0 | DB1+0 | PS | 2122856.48 | 98.821 | 2024-11-30 | Completed | 2024-12-28 |  | Hari Krishna
296 | 195A/1 | DA+6 | FS | 1442822 | 94.623 | 2025-03-25 | Completed | 2025-03-29 |  | kastabhanja
297 | 195A/2 | DA+6 | FS | 1442822 | 94.623 | 2024-12-07 | Completed | 2024-12-12 |  | Maa Bhawanis
298 | 195A/3 | DA+0 | PS | 1086615 | 80.771 | 2023-08-22 | Completed | 2023-10-01
299 | 196/0 | DD60+9 | WBC |  | 401.731 | 2024-11-16 | Completed | 2024-11-30 |  | Maa Bhawani
300 | 197/0 | DD60+9 | WET | 4251845 | 255.731 | 2024-11-12 | Completed | 2024-11-18 |  | Maa Bhawani
301 | 197/1 | DA+0 | PS | 1086615 | 80.771 | 2024-11-18 | Completed | 2024-11-22 |  | Maa Bhawani
302 | 197/2 | DA+0 | WET | 881091 | 63.346 | 2024-11-25 | Completed | 2024-11-30 |  | Maa Bhawani
303 | 197/3 | DA+0 | PS | 1086615 | 80.771 | 2023-08-18 | Completed | 2023-08-31
304 | 197/4 | DA+0 | WET | 881091 | 63.346 | 2024-11-08 | Completed | 2024-11-10 |  | Maa Bhawani
305 | 198/0 | DC1+0 | WET | 2328166.27 | 117.033 | 2024-11-13 | Completed | 2024-11-30 |  | M/s Rajesh Singh
306 | 198/1 | DA+0 | WET | 881091 | 63.346 | 2024-11-17 | Completed | 2024-12-12 |  | Kumar
307 | 198/2 | DA+0 | WET | 881091 | 63.346 | 2025-02-16 | Completed | 2025-02-23 |  | Hari Krishna
308 | 199/0 | DD45+18 | WET | 4465782 | 224.07 | 02-02-025 | Completed | 2025-02-13 |  | Hari Krishna
309 | 200/0 | DB2+18 | WET | 2472338 | 111.669 | 2025-01-19 | Completed | 2025-01-31 |  | Hari Krishna
310 | 201/0 | DC2+18 | WET | 3336290 | 149.965 | 2025-02-26 | Completed | 2025-03-06 |  | Hari Krishna
311 | 201/1 | DD60+9 (2M RC) | WET | 5379537 | 282.692 | 2025-03-30 | Completed | 2025-04-09 |  | Kastabbhanja
312 | 202/0 | DD60+55(4.5M RC) | WBC |  | 768.133 | 2025-04-05 | Completed | 2025-05-06 |  | Sukhriddin
313 | 203/0 | DD60+55(4.5M RC) | WBC |  | 768.133 | 2025-03-09 | Completed | 2025-03-31 |  | Sukhriddin
314 | 203/1 | DD60+6 | WET | 4251845 | 255.731 | 2025-02-21 | Completed | 2025-02-28 |  | Sukhriddin
315 | 204/0 | DD60+9 | WET | 4251845 | 255.731 | 2025-03-02 | Completed | 2025-03-08 |  | Sukhriddin
316 | 205/0 | DD60+3 (2M RC) | WET |  | 282.692 | 2025-02-13 | Completed | 2025-02-20 |  | Sukhridin
317 | 205/1 | DA-3 | WET | 881091 | 63.346 | 2025-01-29 | Completed | 2025-01-31 |  | Sukhridin
318 | 205/2 | DA+3 | WET | 986514 | 65.631 | 2025-02-26 | Completed | 2025-02-28 |  | Kastbahana
319 | 206/0 | DD60+25 | WET | 4801423 | 298.554 | 2025-01-21 | Completed | 2025-01-28 |  | Sukhridin
320 | 208/0 | DD60+25 | WET | 4801423 | 298.554 | 2025-01-20 | Completed | 2025-01-29 |  | Velly
321 | 209/0 | DC1+0 | WET | 2328166.27 | 117.033 | 2025-01-09 | Completed | 2025-01-17 |  | Velly Constr.
322 | 209/1 | DA+3 | WET | 986514 | 65.631 | 2025-01-13 | Completed | 2025-01-20 |  | Velly Constr.
323 | 210/0 | DB2+18 | WET | 2472338 | 111.669 | 2025-03-02 | Completed | 2025-03-20 |  | Tes Trasnsco
324 | 211/0 | DB1+9 | WET | 1741972 | 80.469 | 2025-03-02 | Completed | 2025-03-16 |  | Tower foundation
325 | 211/1 | DA+0 | WET | 881091 | 63.346 | 2025-01-13 | Completed | 2025-01-19 |  | Tower Foundation
326 | 211/2 | DA+0 | WET | 881091 | 63.346 | 2025-01-21 | Completed | 2025-01-25 |  | Tower Foundation
327 | 211A/0 | DB2+0 | WET | 1880164 | 89.905 | 2025-02-02 | Completed | 2025-02-08 |  | Tower foundation
328 | 211A/1 | DA-3 | WET | 881091 | 63.346 | 2025-01-21 | Completed | 2025-01-25 |  | Khodiyar
329 | 211A/2 | DA+0 | WET | 881091 | 63.346 | 28-01-202 | Completed | 2025-01-31 |  | Tower Foundation
330 | 212/0 | DD45+3 | WET | 3953330 | 192.374 | 2025-02-10 | Completed | 2025-02-21 |  | Tower Foundation
331 | 213/0 | DD60+3 | WBC |  | 401.731 | 2025-01-16 | Completed | 2025-02-04 |  | Tes Transco
332 | 213/1 | DA+0 | WET | 881091 | 63.346 | 2025-01-23 | Completed | 2025-01-31 |  | Tes Transco
333 | 214/0 | DD45+0 | PS | 4512711.95 | 233.46 | 2025-01-31 | Completed | 2025-02-17 |  | Tes Transco
334 | 214/1 | DA+6 | WET | 986514 | 65.631 | 2025-02-03 | Completed | 2025-02-12 |  | Tes Transco
335 | 215/0 | DB1+6 | WET | 1741972 | 80.469 | 2025-01-12 | Completed | 2025-01-18 |  | BLG Infratech
336 | 215/1 | DA+9 | WET | 986514 | 65.631 | 2025-01-17 | Completed | 2025-01-22 |  | BLG
337 | 216/0 | DB2+25(2M RC) | WET |  | 120.61 | 2025-02-27 | Completed | 2025-03-12 |  | Tes Transco
338 | 217/0 | DD45+25(2M RC) | WET |  | 231.258 | 2025-03-18 | Completed | 2025-03-31 |  | Tes Transco
339 | 217A/0 | DB1+3 | WET | 1741972 | 80.469 | 2025-03-19 | Completed | 2025-03-23 |  | Kastabhanja
340 | 217A/1 | DA+3 | PS | 1215596 | 83.812 | 2025-02-17 | Completed | 2025-02-25 |  | Tes Transco
341 | 217A/2 | DA+0 | PS | 1086615 | 80.771 | 2025-02-25 | Completed | 2025-02-28 |  | Tes Transco
342 | 218/0 | DD60+0 | WET | 3915704.88 | 252.474 | 2025-03-10 | Completed | 2025-03-31 |  | Tes Transcvo
343 | 218/1 | DA+3 | WET | 986514 | 65.631 | 2025-01-12 | Completed | 2025-01-19 |  | Tes Transco
344 | 219/0 | DC2+18 | WET | 3336290 | 149.965 | 2025-01-12 | Completed | 2025-01-25 |  | Tes Transco
345 | 220/0 | DD45+9 | WET | 3953330 | 192.374 | 2025-02-02 | Completed | 2025-02-11 |  | Tes Transco
346 | 220/1 | DA+3 | WET | 986514 | 65.631 | 2025-02-07 | Completed | 2025-02-16 |  | Tes Transco
347 | 221/0 | DD60+18 | FS | 6685851 | 390.682 | 2025-02-11 | Completed | 2025-02-25 |  | Tes Transco
348 | 222/0 | DD60+25 | FS | 6685851 | 390.682 | 2025-02-13 | Completed | 2025-02-23 |  | Kastbhanja
349 | 222/1 | DB1+3 | WET | 1741972 | 80.469 | 2025-03-14 | Completed | 2025-03-17 |  | Kastabhanja
350 | 223/0 | DC1+0 | WET | 2328166.27 | 117.033 | 2025-01-26 | Completed | 2025-01-31 |  | BLG
351 | 223/1 | DA+0 | WET | 881091 | 63.346 | 2025-02-18 | Completed | 2025-02-21 |  | Murgan
352 | 223/2 | DA+0 | WET | 881091 | 63.346 | 2025-02-14 | Completed | 2025-02-18 |  | Murgan
353 | 223/3 | DA+0 | WET | 881091 | 63.346 | 2025-01-30 | Completed | 2025-02-02 |  | Khodiyar
354 | 224/0 | DC2+6 | WET | 2772635 | 138.207 | 2025-01-23 | Completed | 2025-01-30 |  | Khodiyar
355 | 225/0 | DD60+0 | WET | 3915704.88 | 252.474 | 2025-02-04 | Completed | 2025-02-12 |  | Khodiyar
356 | 225/1 | DA+6 | WET | 986514 | 65.631 | 2025-02-03 | Completed | 2025-02-07 |  | BLG
357 | 226/0 | DC2+0 | WET | 2530056 | 134.785 | 2025-02-03 | Completed | 2025-02-10 |  | Kastabhanja
358 | 227/0 | DB1+6 | PS | 2075500 | 99.33 | 2025-01-26 | Completed | 2025-02-04 |  | Ammu Eng.
359 | 228/0 | DD60+25 | PS | 5611385.97 | 341.95 | 2025-03-01 | Completed | 2025-05-28 | Again start date is 14-05-2025 | Kastabhanja
360 | 229/0 | DD60+18 | WBC |  | 448.208 | 2025-02-02 | Completed | 2025-02-11 |  | Sukhridin
361 | 229/1 | DB1+6 | WET | 1741972 | 80.469 | 2025-03-25 | Completed | 2025-04-07 |  | Tes Transco
362 | 229/2 | DA+6 | WET | 986514 | 65.631 | 2025-02-10 | Completed | 2025-02-13 |  | Murgan
363 | 229/3 | DA+0 | WET | 881091 | 63.346 | 2025-02-01 | Completed | 2025-02-05 |  | Velly Constr.
364 | 229/4 | DA+0 | WET | 881091 | 63.346 | 2025-03-14 | Completed | 2025-03-17 |  | Tes Transco
365 | 229/5 | DA+0 | WET | 881091 | 63.346 | 2025-02-05 | Completed | 2025-02-08 |  | Velly Constr.
366 | 230/0 | DD60+0 | WET | 3915704.88 | 252.474 | 2025-02-10 | Completed | 2025-02-17 |  | Velly Constr.
367 | 231/0 | DD60+6 | WET | 4251845 | 255.731 | 2025-02-09 | Completed | 2025-02-18 |  | BLG
368 | 232/0 | DD60+3 | WET | 4251845 | 255.731 | 2025-02-19 | Completed | 2025-02-28 |  | Velly Constr
369 | 233/0 | DD45+0 | WET | 3743190.59 | 189.081 | 2025-02-07 | Completed | 2025-02-15 |  | Ammu Engg.-1
370 | 234/0 | DD45+0 | WET | 3743190.59 | 189.081 | 2025-02-13 | Completed | 2025-02-21 |  | Ammu Engg.
371 | 235/0 | DC2+3 | PS |  | 162.896 | 2025-02-17 | Completed | 2025-02-28 |  | Ammu Engg.
372 | 236/0 | DB2+0 | WET | 1880164 | 89.905 | 2025-03-02 | Completed | 2025-03-19 |  | Ammu Engg.
373 | 237/0 | DD45+9 (3M RC) | WET |  | 213.318 | 2025-02-14 | Completed | 2025-02-23 |  | Khodiyar
374 | 237/1 | DA+0 | WET | 881091 | 63.346 | 2025-02-24 | Completed | 2025-02-27 |  | Khodiyar
375 | 237/2 | DA-3 | WET | 881091 | 63.346 | 2025-02-26 | Completed | 2025-02-28 |  | Khodiyar
376 | 237/3 | DA-3 | WET | 881091 | 63.346 | 2025-03-03 | Completed | 2025-03-07 |  | Ammu
377 | 237/4 | DA+0 | PS | 1086615 | 80.771 | 2025-02-22 | Completed | 2025-02-27 |  | Tower Foundation
378 | 237/5 | DA-3 | WET | 881091 | 63.346 | 2025-02-23 | Completed | 2025-02-28 |  | Ammu Engg-1
379 | 237/6 | DA+3 | WET | 986514 | 65.631 | 2025-02-12 | Completed | 2025-02-16 |  | Jayesh Electrical
380 | 239/0 | DD60+25 | WET | 4801423 | 298.554 | 2025-04-01 | Completed | 2025-04-11 |  | Khodiyar Krupa
381 | 240/0 | DD60+25 | FS | 6685851 | 390.682 | 2025-02-18 | Completed | 2025-02-28 |  | Jayesh Electrical
382 | 241/0 | DB2+9 | WBC | 3850981 | 173.061 | 2025-03-23 | Completed | 2025-04-06 |  | Jayesh Electrical
383 | 242/0 | DB1+0 | FS |  | 113.343 | 2025-02-19 | Completed | 2025-02-27 |  | Tes Trasnsco
384 | 242/1 | DA-3 | WET | 881091 | 63.346 | 2025-03-02 | Completed | 2025-03-06 |  | Tes Transco
385 | 242/2 | DA-3 | WET | 881091 | 63.346 | 2025-02-18 | Completed | 2025-02-21 |  | BLG
386 | 242/3 | DA-3 | WET | 881091 | 63.346 | 2025-03-10 | Completed | 2025-03-13 |  | Khodiyar
387 | 243/0 | DB1+9 | FS |  | 113.896 | 2025-03-23 | Completed | 2025-03-29 |  | Khodiyar
388 | 244/0 | DC1+9 | WBC |  | 197.882 | 2025-03-01 | Completed | 2025-03-13 |  | BLG
389 | 244/1 | DB1+9 | WBC |  | 138.164 | 2025-03-27 | Completed | 2025-03-31 |  | BLG
390 | 245/0 | DD45+0 | FS | 5295995.92 | 266.818 | 2025-03-16 | Completed | 2025-03-26 |  | BLG
391 | 245/1 | DA+0 | FS | 1287409 | 91.088 | 2025-02-16 | Completed | 2025-02-22 |  | Neelkanth
392 | 246/0 | DD60+0 | PS | 4780790.5 | 306.052 | 2025-03-02 | Completed | 2025-03-21 |  | Khodiyar
393 | 247/0 | DD60+0 | FS | 5576159.92 | 346.952 | 2025-02-27 | Completed | 2025-03-12 |  | Murgan
394 | 247/1 | DA+0 | FS | 1287409 | 91.088 | 2025-02-23 | Completed | 2025-02-26 |  | Murgan
395 | 247/2 | DA+3 | WET | 986514 | 65.631 | 2025-02-24 | Completed | 2025-02-28 |  | Neel Kanth
396 | 247/3 | DA-3 | WET | 881091 | 63.346 | 2025-03-03 | Completed | 2025-03-07 |  | Khodiyar
397 | 247/4 | DA+0 | WET | 881091 | 63.346 | 2025-02-24 | Completed | 2025-02-27 |  | BLG
398 | 248/0 | DC2+9 | WET | 2772635 | 138.207 | 2025-03-09 | Completed | 2025-03-26 |  | Ketan
399 | 248/1 | DA+9 | WET | 986514 | 65.631 | 2025-02-25 | Completed | 2025-02-28 |  | Ketan
400 | 248/2 | DA+9 | WET | 986514 | 65.631 | 2025-02-18 | Completed | 2025-02-24 |  | Ketan
401 | 248/3 | DA+6 | WET | 986514 | 65.631 | 2025-03-03 | Completed | 2025-03-07 |  | Ketan
402 | 248/4 | DA+3 | WET | 986514 | 65.631 | 2025-01-25 | Completed | 2025-01-29 |  | Kastabhanja
403 | 248/5 | DA+0 | WET | 881091 | 63.346 | 2025-01-29 | Completed | 2025-01-31 |  | Kastabhanja
404 | 248/6 | DA+0 | WET | 881091 | 63.346 | 2025-01-08 | Completed | 2025-01-11 |  | Kastabhanja
405 | 249/0 | DB2+0 | WET | 1880164 | 89.905 | 2025-01-14 | Completed | 2025-01-19 |  | Khodiyar Krupa
406 | 249/1 | DA+0 | WET | 881091 | 63.346 | 2025-01-07 | Completed | 2025-01-10 |  | Khodiyar Krupa
407 | 249/2 | DA+0 | WET | 881091 | 63.346 | 2025-01-11 | Completed | 2025-01-13 |  | Khodiyar Krupa
408 | 249/3 | DA+0 | WET | 881091 | 63.346 | 2025-01-10 | Completed | 2025-01-13 |  | Jayesh Electrical
409 | 250/0 | DD60+0 | WET | 3915704.88 | 252.474 | 2025-01-14 | Completed | 2025-01-23 |  | Jayesh Electrical
410 | 250/1 | DA-3 | WET | 881091 | 63.346 | 2025-01-12 | Completed | 2025-01-16 |  | Kastabhanja
411 | 251/0 | DB1+9 | FS |  | 113.896 | 2024-09-04 | Completed | 2024-09-19 |  | Kudiyaar
412 | 252/0 | DC1+18 | WET | 3216269 | 131.849 | 2025-01-17 | Completed | 2025-01-24 |  | Kastabhanja
413 | 253/0 | DC1+0 | WET | 2328166.27 | 117.033 | 2025-01-08 | Completed | 2025-01-19 |  | Tes Transco
414 | 254/0 | DB2+0 | FS | 2986642.46 | 132.205 | 2024-08-04 | Completed | 2024-08-22
415 | 255/0 | DD60+3 | FS | 5918512 | 351.748 | 2024-09-13 | Completed | 2024-10-10 |  | Tes Transco
416 | 255/1 | DA+6 | WET | 986514 | 65.631 | 2025-01-02 | Completed | 2025-01-07 |  | Kastabhanja
417 | 255/2 | DA+0 | WET | 881091 | 63.346 | 2024-12-10 | Completed | 2024-12-15 |  | Jayesh Electrical
418 | 255/3 | DA+3 | WET | 986514 | 65.631 | 2024-11-13 | Completed | 2024-11-21 |  | Paresh mahto
419 | 255/4 | DA+0 | WPS | 545016 | 39.126 | 2024-06-14 | Completed | 2024-06-21
420 | 257/0 | DC2+0 | WET | 2530056 | 134.785 | 2024-05-29 | Completed | 2024-06-01
421 | 257/1 | DA+0 | FS | 1287409 | 91.088 | 2024-12-18 | Completed | 2024-12-31 |  | Jayesh Electrical
422 | 257/2 | DA-3 | WET | 881091 | 63.346 | 2024-04-21 | Completed | 2024-04-30
423 | 257/3 | DA+0 | WET | 881091 | 63.346 | 2024-03-18 | Completed | 2024-03-30
424 | 257/4 | DA+0 | WET | 881091 | 63.346 | 2024-05-03 | Completed | 2024-05-10
425 | 259/0 | DD60+18 | PS | 5611385.97 | 341.95 | 2024-06-14 | Completed | 2024-07-11
426 | 260/0 | DD60+18 | WBC |  | 448.208 |  | Completed | 2024-05-31
427 | 261/0 | DC2+18 | WET | 3336290 | 149.965 | 2024-05-03 | Completed | 2024-05-10
428 | 262/0 | DD45+9 | WET | 3953330 | 192.374 | 2024-05-13 | Completed | 2024-06-01
429 | 262/1 | DA+0 | WET | 881091 | 63.346 | 2024-04-13 | Completed | 2024-04-27
430 | 263/0 | DC2+0 | PS | 3206945.94 | 168.913 | 2024-10-09 | Completed | 2024-10-29 |  | Tes Transco
431 | 264/0 | DC1+6 | WET | 2633913 | 120.461 | 2024-05-01 | Completed | 2024-05-11
432 | 265/0 | DB2+3 | WET | 2143792.36 | 94.918 | 2024-04-27 | Completed | 2024-05-12
433 | 266/0 | DB1+0 | WET | 1598139 | 79.944 | 2024-12-01 | Completed | 2024-12-08 |  | Kastabhaja
434 | 266/1 | DB1+6 | WET | 1741972 | 80.469 | 2024-11-15 | Completed | 2024-11-22 |  | Tes Transco
435 | 266/2 | DA+0 | WET | 881091 | 63.346 | 2025-01-25 | Completed | 2025-01-29 |  | Jayesh Electrical
436 | 267/0 | DC1+9 (2M RC) | WET |  | 139.849 | 2024-05-10 | Completed | 2024-05-21 | RC done o 16-12-2024. | Jayesh Electrical
437 | 267A/0 | DC2+9 (2M RC) | WET |  | 151.836 | 2024-04-13 | Completed | 2024-04-28 | RC done on 17-12-2024 | Jayesh Electrical
438 | 267A/1 | DA+0 | FS | 1287409 | 91.088 | 2024-08-14 | Completed | 2024-09-23 |  | Rudra Associate
439 | 267A/2 | DA-3 | WET | 881091 | 63.346 | 2024-04-27 | Completed | 2024-05-15
440 | 267A/3 | DA+0 | WET | 881091 | 63.346 | 2024-04-30 | Completed | 2024-05-08
441 | 268/0 | DD60+6 | WET | 4251845 | 255.731 | 2024-05-12 | Completed | 2024-05-22
442 | 269/0 | DD60+0 | WET | 3915704.88 | 252.474 | 2024-06-03 | Completed | 2024-06-14
443 | 269/1 | DA+0 | WET | 881091 | 63.346 | 2024-11-23 | Completed | 2024-11-29 |  | Paresh
444 | 269/2 | DA+6 | PS | 1215596 | 83.812 | 2025-01-02 | Completed | 2025-01-08 |  | Jayesh Electrical
445 | 270/0 | DD45+0 | FS | 5295995.92 | 266.818 | 2025-01-30 | Completed | 2025-02-10 |  | Jayesh Electrical
446 | 270/1 | DA+0 | PS | 1086615 | 80.771 | 2024-05-27 | Completed | 2024-06-01
447 | 270/2 | DA+3 | WET | 986514 | 65.631 | 2024-05-20 | Completed | 2024-05-26
448 | 270/3 | DA-3 | WBC | 1686873 | 109.919 | 2025-01-07 | Completed | 2025-01-17 |  | Tes Transco
449 | 270/4 | DA+0 | WET | 881091 | 63.346 | 2024-11-28 | Completed | 2024-12-20 |  | Maa Bhawani(Jitu)
450 | 270/5 | DA+0 | WET | 881091 | 63.346 | 2025-01-20 | Completed | 2025-01-28 |  | Tes Transco
451 | 270/6 | DA-3 | WET | 881091 | 63.346 | 2025-01-18 | Completed | 2025-01-24 |  | Tes Transco
452 | 270/7 | DA-3 | WET | 881091 | 63.346 | 2024-12-01 | Completed | 2024-12-06 |  | Tes Trasnsco
453 | 270A/0 | DC2+0 | WET | 2530056 | 134.785 | 2024-12-18 | Completed | 2024-12-31 |  | Tes transco
454 | 271/0 | DC1+0 | WET | 2328166.27 | 117.033 | 2024-11-23 | Completed | 2024-11-30 |  | Tes Transco
455 | 271/1 | DA-3 | FS | 1287409 | 91.088 | 2025-03-03 | Completed | 2025-03-13 |  | Neekl Kanta
456 | 271/2 | DA+0 | WET | 881091 | 63.346 | 2025-01-14 | Completed | 2025-01-21 |  | Tes Transco
457 | 271/3 | DA-3 | WBC | 1686873 | 109.919 | 2024-12-01 | Completed | 2024-12-08 |  | Jayesh Electrical
458 | 271/4 | DA-3 | WET | 881091 | 63.346 | 2025-01-23 | Completed | 2025-01-29 |  | Tes Transco
459 | 271/5 | DA-3 | WET | 881091 | 63.346 | 2024-05-26 | Completed | 2024-06-01
460 | 272/0 | DC1+6 | WET | 2633913 | 120.461 | 2024-06-04 | Completed | 2024-06-13
461 | 272/1 | DA+9 | WET | 986514 | 65.631 | 2024-06-05 | Completed | 2024-06-12
462 | 272/2 | DA-3 | WET | 881091 | 63.346 | 2024-11-18 | Completed | 2024-11-26 |  | Tes Transco
463 | 272/3 | DA+3 | WET | 986514 | 65.631 | 2024-12-14 | Completed | 2024-12-21 |  | Tes transco
464 | 272/4 | DA+3 | WET | 986514 | 65.631 | 2024-12-08 | Completed | 2024-12-12 |  | Tes Transco
465 | 272/5 | DB1+0 | WET | 1598139 | 79.944 | 2024-11-23 | Completed | 2024-11-30 |  | Tes Transco
466 | 272/6 | DA+3 | FS | 1442822 | 94.623 | 2025-02-26 | Completed | 2025-03-04 |  | New Gang
467 | 272/7 | DA+9 (2M RC) | WET |  | 71.29 | 2024-11-20 | Completed | 2024-12-10 |  | Tes Transco
468 | 272A/0 | DB1+18 (2M RC) | PS |  | 117.99 | 2024-11-05 | Completed | 2024-11-13 |  | Tes Transco
469 | 272A/1 | DA+6 | WET | 986514 | 65.631 | 2024-11-07 | Completed | 2024-11-17 |  | Tes Transco
470 | 272A/2 | DA+0 | WET | 881091 | 63.346 | 2024-11-06 | Completed | 2024-11-13 |  | Tes Transco
471 | 272A/3 | DA+0 | WET | 881091 | 63.346 | 2024-12-28 | Completed | 2025-01-03 |  | Tes Transco
472 | 272A/4 | DA+0 | WET | 881091 | 63.346 | 2025-01-02 | Completed | 2025-01-08 |  | Tes Transco
473 | 272A/5 | DA+3 | WET | 986514 | 65.631 | 2025-01-04 | Completed | 2025-01-11 |  | Tes Transco
474 | 272A/6 | DA-3 | WET | 881091 | 63.346 | 2024-12-22 | Completed | 2024-12-29 |  | Tes Transco
475 | 272A/7 | DA-3 | WET | 881091 | 63.346 | 2025-01-05 | Completed | 2025-01-12 |  | Tes Transco
476 | 273/0 | DB2+0 | FS | 2986642.46 | 132.205 | 2025-05-01 | Completed | 2025-06-13 | Again start date is 06-06-2025 | Tes Transco
477 | 273/1 | DA+6 | WBC | 1821043 | 113.924 | 2025-02-22 | Completed | 2025-02-27 |  | Neelkanth
478 | 273/2 | DA+6 | WET | 986514 | 65.631 | 2024-12-09 | Completed | 2024-12-15 |  | Kastabhanja
479 | 274/0 | DC1+0 | WET | 2328166.27 | 117.033 | 2025-01-02 | Completed | 2025-01-11 |  | Tes Transco
480 | 275/0 | DD45+0(2M RC) | WET |  | 206.583 | 2024-12-09 | Completed | 2024-12-23 |  | Tes Transco
481 | 276/0 | DD60+0(2M RC) | WET |  | 265.697 | 2024-12-18 | Completed | 2024-12-31 |  | Kastabhanja
482 | 166/0 | DD60+6 | FS |  |  | 2025-08-17 | Completed | 2025-10-03 |  | Kastabhanja
483 | 103/0 | DD45+25 | PILE |  |  |  | WIP |  |  | Chaudhary Construction
484 | 154/0 | DD45+25(10.96 M RC) | PILE |  |  |  | WIP |  |  | KND

## FDN-VDRA
Foundation Part-I (VADODARA SECTION)
Sl. No. | Location No. | Tower Type | Classification | Revenue | Concreting Volume in M3 | Start Date | Todays Status | Cumulative Status | End Date | Remarks | Sub-Contractor name | Earthing Status | Earthing Completion Date
1 | 132/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-06-12 | Completed |  | 2023-06-21
2 | 132/2 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-08-05 | Completed |  | 2023-08-14
3 | 135A/4 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-08-10 | Completed |  | 2023-08-23
4 | 133A/4 | DA+6 | WET PADDY | 623377 | 40.634 | 2023-08-11 | Completed |  | 2023-08-29
5 | 127/1 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-08-18 | Completed |  | 2023-08-29
6 | 127/2 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-08-28 | Completed |  | 2023-09-14
7 | 135A/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-08-26 | Completed |  | 2023-09-07
8 | 133/1 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-08-28 | Completed |  | 2023-09-04
9 | 135/2 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-09-03 | Completed |  | 2023-09-24
10 | 135/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-10-03 | Completed |  | 2023-10-20
11 | 127/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-10-03 | Completed |  | 2023-11-02
12 | 133/2 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-10-07 | Completed |  | 2023-10-29
13 | 135A/7 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-10-07 | Completed |  | 2023-10-29
14 | 135B/4 | DA+6 | WET PADDY | 623377 | 40.634 | 2023-10-07 | Completed |  | 2023-10-19
15 | 127/4 | DA+3 | WET PADDY | 623377 | 40.634 | 2023-10-16 | Completed |  | 2023-10-29
16 | 133/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-10-28 | Completed |  | 2023-11-09
17 | 133A/1 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-11-07 | Completed |  | 2023-11-23
18 | 127/0 | DD45+0 | WET PADDY |  | 128.427 | 2023-11-11 | Completed |  | 2023-12-13
19 | 133/5 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-11-19 | Completed |  | 2023-12-09
20 | 133A/2 | DA+6 | WET PADDY | 623377 | 40.634 | 2023-11-22 | Completed |  | 2023-12-01
21 | 135B/2 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-12-07 | Completed |  | 2023-12-20
22 | 135B/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-12-07 | Completed |  | 2023-12-17
23 | 133A/0 | DB1+0 | WET PADDY | 1017007 | 54.675 | 2023-12-11 | Completed |  | 2024-01-05
24 | 135B/0 | DB1+0 | WET PADDY | 1017007 | 54.675 | 2023-12-12 | Completed |  | 2023-12-30
25 | 133/0 | DB1+0 | WET PADDY | 1017007 | 54.675 | 2023-12-11 | Completed |  | 2024-01-10
26 | 133/4 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-12-17 | Completed |  | 2023-12-26
27 | 127/5 | DA+3 | WET PADDY | 623377 | 40.634 | 2023-12-19 | Completed |  | 2024-01-04
28 | 135B/5 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-12-24 | Completed |  | 2023-12-31
29 | 135B/6 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-12-24 | Completed |  | 2024-01-05
30 | 126/0 | DC2+0 | WET PADDY |  | 92.292 | 2023-12-23 | Completed |  | 2024-01-15
31 | 133A/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-12-31 | Completed |  | 2024-01-10
32 | 129A/1 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-01-07 | Completed |  | 2024-02-02
33 | 130/0 | DB1+0 | WET PADDY | 1017007 | 54.675 | 2024-01-12 | Completed |  | 2024-01-30
34 | 112/0 | DD45+0 | WET PADDY |  | 128.427 | 2024-01-18 | Completed |  | 2024-02-10
35 | 135B/1 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-01-27 | Completed |  | 2024-02-06
36 | 129A/0 | DC1+0 | WET PADDY |  | 79.994 | 2024-01-31 | Completed |  | 2024-02-15
37 | 135B/7 | DA+3 | WET PADDY | 623377 | 40.634 | 2024-02-08 | Completed |  | 2024-02-17
38 | 113/0 | DD60+0 | WET PADDY |  | 178.19 | 2024-02-08 | Completed |  | 2024-05-09
39 | 129A/2 | DA+3 | WET PADDY | 623377 | 40.634 | 2024-02-13 | Completed |  | 2024-02-24
40 | 135/6 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-02-18 | Completed |  | 2024-02-26
41 | 137/4 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-02-29 | Completed |  | 2024-03-10
42 | 135/5 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-02-27 | Completed |  | 2024-03-10
43 | 137/1 | DA+3 | WET PADDY | 623377 | 40.634 | 2024-02-29 | Completed |  | 2024-03-08
44 | 144/5 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-03-15 | Completed |  | 2024-03-26
45 | 145A/1 | DA+3 | WET PADDY | 623377 | 40.634 | 2024-03-09 | Completed |  | 2024-03-22
46 | 137/2 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-03-06 | Completed |  | 2024-03-14
47 | 137/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-03-09 | Completed |  | 2024-03-16
48 | 135/4 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-03-11 | Completed |  | 2024-03-20
49 | 137A/3 | DA+6 | WET PADDY | 623377 | 40.634 | 2024-03-14 | Completed |  | 2024-03-23
50 | 145A/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-03-19 | Completed |  | 2024-03-27
51 | 107/0 | DD45+0 | WET PADDY |  | 128.427 | 2024-03-31 | Completed |  | 2024-04-17
52 | 107/1 | DA-3 | WET PADDY | 545016 | 39.126 | 2024-03-22 | Completed |  | 2024-04-01
53 | 144/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-03-22 | Completed |  | 2024-03-31
54 | 145/0 | DB1+18 | WET PADDY | 1330245 | 61.574 | 2024-03-23 | Completed |  | 2024-04-04
55 | 144/2 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-03-29 | Completed |  | 2024-04-06
56 | 144/4 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-04-07 | Completed |  | 2024-04-15
57 | 144A/0 | DB1+9 | WET PADDY | 1108538 | 54.992 | 2024-04-03 | Completed |  | 2024-04-14
58 | 137A/4 | DA-3 | WET PADDY | 545016 | 39.126 | 2024-04-13 | Completed |  | 2024-04-20
59 | 150A/2 | DA+0 | WET | 881091 | 63.346 | 2024-04-12 | Completed |  | 2024-04-26
60 | 104/0 | DD60+35 | Pile |  | 861.11 | 2024-11-17 | Completed. | Completed. | 2025-02-28 |  | Jai Mata Di
61 | 152/2 | DA-3 | WET PADDY | 545016 | 39.126 | 2024-04-25 | Completed |  | 2024-05-03
62 | 147/5 | DA+6 | WET PADDY | 623377 | 40.634 | 2024-04-20 | Completed |  | 2024-05-03
63 | 137A/5 | DA-3 | WET PADDY | 545016 | 39.126 | 2024-04-19 | Completed |  | 2024-04-28
64 | 106B/1 | DA+9 | WET PADDY | 623377 | 40.634 | 2024-04-18 | Completed |  | 2024-04-26
65 | 152/3 | DA-3 | WET PADDY | 545016 | 39.126 | 2024-05-01 | Completed |  | 2024-05-09
66 | 147B/0 | DB1+18 | WET PADDY | 1330245 | 61.574 | 2024-04-30 | Completed |  | 2024-05-10
67 | 152/4 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-05-05 | Completed |  | 2024-05-14
68 | 147/4 | DA+3 | WET PADDY | 623377 | 40.634 | 2024-05-04 | Completed |  | 2024-05-17
69 | 106A/4 | DA+9 | WET PADDY | 623377 | 40.634 | 2024-05-06 | Completed |  | 2024-05-16
70 | 135A/1 | DD45+3 | WET PADDY |  | 131.047 | 2024-05-07 | Completed |  | 2024-05-26
71 | 150A/1 | DA+3 | WET | 986514 | 65.631 | 2024-05-08 | Completed |  | 2024-05-22
72 | 147/3 | DA-3 | WET PADDY | 545016 | 39.126 | 2024-05-16 | Completed |  | 2024-05-29
73 | 147/6 | DA-3 | WET PADDY | 545016 | 39.126 | 2024-05-15 | Completed |  | 2024-05-25
74 | 106B/2 | DA+6 | WET PADDY | 623377 | 40.634 | 2024-05-15 | Completed |  | 2024-05-24
75 | 106B/0 | DB2+9 | WET PADDY | 2143792.36 | 65.135 | 2024-04-24 | Completed |  | 2024-06-06
76 | 106A/3 | DA+3 | WET PADDY | 623377 | 40.634 | 2024-05-19 | Completed |  | 2024-06-10
77 | 147/1 | DC2+0 | Wet Paddy |  | 92.292 | 2024-05-20 | Completed |  | 2024-06-08
78 | 147/2 | DC1+0 | Wet Paddy |  | 79.994 | 2024-05-20 | Completed |  | 2024-06-03
79 | 152/0 | DC2+0 | Wet Paddy |  | 92.292 | 2024-05-19 | Completed |  | 2024-05-30
80 | 135A/2 | DB2+9 | Wet Paddy | 2143792.36 | 65.135 | 2024-05-21 | Completed |  | 2024-06-17
81 | 152/1 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-05-25 | Completed |  | 2024-05-31
82 | 119/2 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-06-08 | Completed |  | 2024-06-15
83 | 119/1 | DA-3 | WET PADDY | 545016 | 39.126 | 2024-06-04 | Completed |  | 2024-06-08
84 | 105/0 | DD60+35 | Pile Foundation |  | 861.114 | 2024-11-25 | Completed. | Completed. | 2025-01-17 |  | Jai Mata Di
85 | 119/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-05-29 | Completed |  | 2024-06-03
86 | 147A/0 | DB1+18 | WET PADDY | 1330245 | 61.574 | 2024-06-05 | Completed |  | 2024-06-14
87 | 144/1 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-06-11 | Completed |  | 2024-06-18
88 | 150A/0 | DC1+0 | WET |  | 117.033 | 2024-05-29 | Completed |  | 2024-06-11
89 | 144/0 | DB2+3 | WET PADDY | 2143792.36 | 65.135 | 2024-06-16 | Completed |  | 2024-06-26
90 | 148/4 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-06-13 | Completed |  | 2024-06-20
91 | 106/0 | DD60+9 | Wet Paddy |  | 180.61 | 2024-05-21 | Completed |  | 2024-07-15 |  | JMD
92 | 109/0 | DB2+0 | Wet Paddy | 1196479 | 62.882 | 2024-07-02 | Completed |  | 2024-07-14 |  | Integar
93 | 116A/0 | DC1+0 | Wet Paddy |  | 79.994 | 2024-07-08 | Completed |  | 2024-07-17 |  | B K Traders
94 | 115/0 | DC2+25 | Wet Paddy |  | 103.703 | 2024-07-08 | Completed |  | 2024-07-31 |  | Prince
95 | 118/0 | DD45+0 | Wet Paddy |  | 128.427 | 2024-07-09 | Completed |  | 2024-07-17 |  | Alamin Construction
96 | 121/0 | DD60+18 | WET PADDY |  | 201.075 | 2024-06-15 | Completed |  | 2024-07-18 |  | H K Construction
97 | 143A/5 | DA+3 | WET PADDY | 623377 | 40.634 | 2024-06-19 | Completed |  | 2024-07-13 |  | Himanshi Agency
98 | 119/0 | DD45+0 | WET PADDY |  | 128.427 | 2024-07-10 | Completed. |  | 2024-08-14 |  | Jeet Infra (Departmental Gang)
99 | 117/0 | DD60+3 | WET PADDY |  | 180.61 | 2024-07-16 | Completed |  | 2024-07-31 |  | Alamin Construction
100 | 116/0 | DD45+18 | WET PADDY |  | 151.172 | 2024-07-17 | Completed. |  | 2024-08-17 |  | B K Traders
101 | 110/0 | DB2+0 | WET PADDY | 1196479 | 62.882 | 2024-07-16 | Completed |  | 2024-07-31 |  | Jyoti Construction (Departmental Gang)
102 | 114/0 | DD45+0 | WET PADDY |  | 128.427 | 2024-07-31 | Completed. |  | 2024-08-13 |  | Prince
103 | 111/0 | DC1+0 | WET PADDY |  | 79.994 | 2024-08-03 | Completed. |  | 2024-08-21 |  | Jyoti Construction (Departmental Gang)
104 | 123/0 | DD60+6 | WET PADDY |  | 180.61 | 2024-08-03 | Completed. |  | 2024-08-11 |  | Alamin Construction
105 | 124A/1 | DA+3 | WET PADDY | 623377 | 40.634 | 2024-08-16 | Completed. |  | 2024-08-18 |  | Alamin Construction
106 | 108/0 | DD45+0 | WET PADDY |  | 128.427 | 2024-08-14 | Completed. |  | 2024-09-20 |  | Prince
107 | 120/0 | DD60+9 | WET PADDY |  | 180.61 | 2024-08-17 | Completed |  | 2024-09-15 | Work hampered due to rain | Jeet Infra (Departmental Gang) | Completed | 2024-09-16
108 | 116B/0 | DD45+6 | WET PADDY |  | 131.047 | 2024-08-18 | Completed. |  | 2024-09-20 | No work due to approach road damaged badly. | B K Traders
109 | 125/0 | DD60+6 | WET PADDY |  | 180.61 | 2024-08-21 | Completed. | Complete. | 2024-11-07 |  | Alamin Construction
110 | 122/0 | DC1+6 | WET PADDY |  | 82.223 | 2024-08-22 | Completed. |  | 2024-09-22 |  | Haaji Saheb | Completed | 2024-09-24
111 | 125A/0 | DB2+3 | WET PADDY | 2143792.36 | 65.135 | 2024-09-12 | Completed |  | 2024-10-19 |  | Jyoti Construction (Departmental Gang)
112 | 134/0 | DC2+25 | WPS |  | 103.7 | 2024-09-21 | Completed | Complete. | 2024-10-26 |  | Jeet Infra (Departmental Gang)
113 | 123/1 | DA+3 | WPS | 623377 | 40.36 | 2024-09-20 | Completed. |  | 2024-10-05 |  | Prince
114 | 124/0 | DC1+3 | WPS |  | 82.223 | 2024-09-20 | Completed |  | 2024-10-06 |  | B K Traders
115 | 126/1 | DA+6 | WPS | 623377 | 40.63 | 2024-09-24 | Completed |  | 2024-10-11 |  | Hajji Saheb | Completed | 2024-10-14
116 | 128/0 | DD60+6 | WPS |  | 180.61 | 2024-09-24 | Completed |  | 2024-10-22 |  | Alamin Construction
117 | 106A/2 | DA-3 | PS | 1086615 | 80.771 | 2024-11-23 | Completed. | Completed. | 2024-12-05 |  | Verma
118 | 129/0 | DD60+6 | WPS |  | 180.61 | 2024-10-07 | Completed. | Completed. | 2024-11-12 | No work due to approach road issues. | Prince Construction
119 | 132/0 | DC2+3 | WPS |  | 94.746 | 2024-10-15 | Completed. | Completed. | 2024-11-13 | No work due to waterlogged. | Hajji Saheb
120 | 137/0 | DC2+9 (3M RC) | WPS |  | 112.877 | 2024-10-15 | Completed. | Completed. | 2024-12-23 |  | Himashi
121 | 130/1 | DA+0 | WPS | 545016 | 39.126 | 2024-10-28 | Completed. |  | 2024-11-20 |  | Haji Saheb
122 | 137A/6 | DA+9 | WPS | 623377 | 40.634 | 2024-10-28 | Completed. | Completed. | 2024-12-05 |  | Suresh Choudhary
123 | 148/0 | DC2+0 | Wet |  | 134.785 | 2024-11-05 | Completed. |  | 2024-11-20 |  | Himanshi Construction
124 | 124A/0 | DD60+0 | WPS |  | 178.19 | 2024-11-07 | Completed. | Completed. | 2024-11-14 |  | Alamin
125 | 135A/0 | DC1+0 | PS |  | 138.086 | 2024-11-11 | Completed. | Completed. | 2024-12-08 |  | Niraj Tiwari
126 | 146/0 | DC1+9 | WBC |  | 192.814 | 2024-12-12 | Completed. | Completed. | 2024-12-25 |  | Himanshi
127 | 143A/3 | DD45+3 | WPS |  | 131.047 | 2024-11-18 | Completed. | Completed. | 2024-12-11 |  | Madhav Constr.
128 | 132/1 | DA+0 | WPS | 545016 | 39.126 | 2024-11-18 | Completed. |  | 2024-11-27
129 | 148/1 | DA+3 | WET | 986514 | 65.631 | 2024-11-18 | Completed. |  | 2024-11-27
130 | 148/2 | DA+0 | WPS | 545016 | 39.126 | 2024-11-19 | Completed. |  | 2024-11-26
131 | 106A/0 | DC2+0 | PS |  | 168.913 | 2024-11-18 | Completed. | Completed. | 2024-12-18 |  | Rawat Construction
132 | 106A/1 | DA+6 | PS | 1215596 | 83.812 | 2024-11-23 | Completed. | Completed. | 2024-12-10 |  | Rawat Construction
133 | 116A/1 | DA+0 | WPS | 545016 | 39.126 | 2024-11-21 | Completed. | Completed. | 2024-11-23
134 | 130/3 | DA+0 | WPS | 545016 | 39.126 | 2024-11-22 | Completed. | Completed. | 2024-12-02 |  | Hajji Saheb
135 | 136/0 | DD45+18(3M RC) | WPS |  | 161.632 | 2024-11-19 | Completed. | Completed. | 2024-12-28 |  | Lala rams
136 | 143A/4 | DA+0 | WPS | 545016 | 39.126 | 2024-11-21 | Completed. | Completed. | 2024-12-23 |  | Lalhusain
137 | 130/4 | DA+3 | WPS | 623377 | 40.634 | 2024-11-24 | Completed. | Completed. | 2024-11-30
138 | 137/5 | DA+3 | WPS | 623377 | 40.634 | 2024-11-22 | Completed | Completed. | 2024-12-31 |  | Himanshi-01
139 | 147B/1 | DA+0 | WET | 881091 | 63.346 | 2024-11-25 | Completed. | Completed. | 2024-12-05 |  | Himanshi-01
140 | 148/3 | DA+0 | WET | 881091 | 63.346 | 2024-11-24 | Completed. | Completed. | 2024-12-05 |  | BK Traders
141 | 157/1 | DA+0 | PS | 1086615 | 80.771 | 2024-11-23 | Completed. | Completed. | 2024-12-20 |  | Anya Construction
142 | 159/4 | DA+0 | FS | 1287409 | 91.088 | 2024-11-26 | Completed. | Completed. | 2024-12-03 |  | Alamin
143 | 131/0 | DD45+3 | WPS |  | 131.047 | 2024-11-18 | Completed. | Completed. | 2024-12-06 |  | Arvind singh
144 | 137/6 | DA+0 | WPS | 545016 | 39.126 | 2024-11-24 | Completed. | Completed. | 2024-12-14 |  | Shree Krishna Const.
145 | 164/1 | DA+0 | FS | 1287409 | 91.088 | 2024-11-11 | Completed. | Completed. | 2024-11-28 |  | Tes Transco
146 | 159/1 | DA+0 | FS | 1287409 | 91.088 | 2024-11-27 | Completed. | Completed. | 2024-12-14 |  | Rudra Associate
147 | 148/5 | DA+0 | WET | 881091 | 63.346 | 2024-11-24 | Completed. | Completed. | 2024-12-10 |  | Himanshi
148 | 161/0 | DD60+25 | PS |  | 341.95 | 2024-12-01 | Completed | Completed. | 2024-12-30 |  | Tes Transco
149 | 130/2 | DA+3 | WPS | 623377 | 40.634 | 2024-11-30 | Completed. | Completed. | 2024-12-07 |  | haji saheb
150 | 137A/0 | DB1+0 | WPS | 1017007 | 54.675 | 2024-12-15 | Completed. | Completed. | 2024-12-29 |  | Shree Krishna Const.
151 | 137A/1 | DA+6 | WPS | 623377 | 40.634 | 2024-12-01 | Completed. | Completed. | 2024-12-20 |  | Rabari Vankabhai
152 | 135/1 | DA+6 | WPS | 623377 | 40.634 | 2024-12-02 | Completed. | Completed. | 2024-12-24 |  | haji saheb
153 | 135A/5 | DA+0 | WPS | 545016 | 39.126 | 2024-12-02 | Completed. | Completed. | 2024-12-31 |  | Lal Hussain
154 | 135A/6 | DA+0 | WPS | 545016 | 39.126 | 2024-12-02 | Completed. | Completed. | 2024-12-17 |  | Neeraj Tiwari | Completed. | 2024-12-18
155 | 163/0 | DC2+0 | FS |  | 193.49 | 2024-12-14 | Completed. | Completed. | 2024-12-29 |  | Lala Ram
156 | 135/0 | DC2+25 | WPS |  | 103.703 | 2024-12-02 | Completed. | Completed. | 2024-12-20 |  | Haaji Saheb
157 | 138/1 | DA+6 | WPS | 623377 | 40.634 | 2024-12-03 | Completed. | Completed. | 2024-12-20 |  | Suresh Choudhary
158 | 152A/0 | DB1+0 | WPS | 1017007 | 54.675 | 2024-12-16 | Completed. | Completed. | 2024-12-24 |  | BK Traders
159 | 164/3 | DA+0 | FS | 1287409 | 91.088 | 2024-12-04 | Completed. | Completed. | 2024-12-14 |  | Lala Ram
160 | 138/0 | DB2+0 | WPS | 1196479 | 62.882 |  | Completed. | Completed. | 2024-12-17 |  | Nav Durga
161 | 141/1 | DA+0 | WPS | 545016 | 39.126 | 2024-12-15 | Completed. | Completed. | 2024-12-27 |  | SA Enterprises
162 | 147/0 | DC2+9 | WPS |  | 94.746 | 2024-12-07 | Completed. | Completed. | 2024-12-18 |  | Himanshi
163 | 140/0 | DD60+0 | WPS |  | 178.19 | 2024-12-13 | Completed. | Completed. | 2024-12-23 |  | Nav Durga
164 | 141/0 | DD60+3 | WPS |  | 180.61 | 2024-12-16 | Completed. | Completed. | 2024-12-29 |  | Nav Durga
165 | 141/2 | DA-3 | WPS | 545016 | 39.126 | 2024-12-11 | Completed. | Completed. | 2024-12-27 |  | Pratibha
166 | 141/3 | DA+3 | WPS | 623377 | 40.634 | 2024-12-22 | Completed. | Completed. | 2024-12-31 |  | Pratibha
167 | 145A/0 | DB1+6 | WPS | 1108538 | 54.992 | 2024-12-13 | Completed. | Completed. | 2024-12-21 |  | Himanshi
168 | 153/0 | DD60+25(1M RC) | Wet |  | 602.294 | 2024-12-18 | Completed. | Completed. | 2024-12-30 |  | BK Traders
169 | 157/3 | DA+0 | FS | 1287409 | 91.088 | 2024-12-18 | Completed. | Completed. | 2024-12-24 |  | Maa Bhawani
170 | 159/2 | DCT+0 | FS |  | 158.016 | 2025-01-02 | Completed. | Completed. | 2025-01-13 | DC2+0 | NR road Contr.
171 | 139/2 | DA+0 | WPS | 545016 | 39.126 | 2024-12-18 | Completed. | Completed. | 2024-12-24 |  | PR Construction
172 | 139A/0 | DB2+9 | WPS | 2143792.36 | 65.135 | 2024-12-19 | Completed. | Completed. | 2024-12-31 |  | Lala Ram
173 | 149/1 | DA+0 | Wet | 881091 | 63.346 | 2024-12-24 | Completed | Completed. | 2024-12-29 |  | Himanshi
174 | 137A/2 | DA+0 | WPS | 545016 | 39.126 | 2024-12-21 | Completed. | Completed. | 2024-12-30 |  | Rabari Vankabhai
175 | 139/1 | DA+3 | WPS | 623377 | 40.634 | 2024-12-22 | Completed. | Completed. | 2024-12-28 |  | Rawat Construction
176 | 148/6 | DA+0 | Wet | 881091 | 63.346 | 2025-01-03 | Completed | Completed. | 2025-01-06 |  | Himanshi
177 | 148/7 | DA+0 | Wet | 881091 | 63.346 | 2025-01-04 | Completed. | Completed. | 2025-01-08 |  | Himanshi
178 | 149/0 | DB2+0 | Wet | 1880164 | 89.905 | 2024-12-23 | Completed | Completed. | 2024-12-31 |  | Himanshi
179 | 157/0 | DD60+6 | PS |  | 309.952 | 2025-01-12 | Completed. | Completed. | 2025-01-29 |  | Anya Constr.
180 | 157/2 | DA+0 | FS | 1287409 | 91.088 | 2024-12-27 | Completed. | Completed. | 2025-01-07 |  | Anya Construction.
181 | 138/2 | DA+0 | WPS | 545016 | 39.126 | 2024-12-27 | Completed. | Completed. | 2025-01-03 |  | SA Enterprises
182 | 139/0 | DB2+0 | WPS | 1196479 | 62.882 | 2024-12-28 | Completed. | Completed. | 2025-01-04 |  | Nav Durga
183 | 160/0 | DD60+18 | FS |  | 39.682 | 2024-12-28 | Completed. | Completed. | 2025-01-13 |  | Haji Saheb
184 | 101/0 | DD60+35(6M RC) | FS |  | 440.345 | 2025-01-01 | Completed. | Completed. | 2025-02-02 |  | Rawat Construction
185 | 162/0 | DD60+25 | PS |  | 341.95 | 2025-01-03 | Completed. | Completed. | 2025-01-24 |  | BK Traders
186 | 142/0 | DD60+0 | WPS |  | 178.19 | 2025-01-07 | Completed. | Completed. | 2025-01-16 |  | Nav Durga
187 | 150/1 | DA+9 | Wet | 986514 | 65.631 | 2025-01-07 | Completed. | Completed. | 2025-01-12 |  | Himanshi
188 | 150/2 | DA+3 | Wet | 986514 | 65.631 | 2025-01-12 | Completed. | Completed. | 2025-01-16 |  | Himanshi
189 | 150/3 | DA+6 | WPS | 623377 | 40.634 | 2025-01-15 | Completed. | Completed. | 2025-01-18 |  | Himanshi
190 | 150/0 | DD60+9 | Wet |  | 255.731 | 2025-01-11 | Completed. | Completed. | 2025-01-28 |  | Himanshi
191 | 158/2 | DA-3 | FS | 1287409 | 91.088 | 2025-01-10 | Completed. | Completed. | 2025-01-23 |  | Haaji Saheb
192 | 143A/0 | DD45+0 | WPS |  | 128.427 | 2025-01-15 | Completed | Completed. | 2025-01-20 |  | Nav Durga
193 | 151/0 | DB2+3 | WPS | 2143792.36 | 65.135 | 2025-01-20 | Completed. | Completed. | 2025-01-27 |  | Himanshi
194 | 154/1 | DD45+25(11.96 M RC) | PILE |  |  | 2025-01-24 | Completed. | Completed. | 2025-05-11 |  | Harshi
195 | 158/0 | DB2+0 | FS | 2986642.46 | 132.205 | 2025-01-23 | Completed. | Completed. | 2025-01-30 |  | NR road Contr.
196 | 158/1 | DA-3 | PS | 1086615 | 80.771 | 2025-01-23 | Completed. | Completed. | 2025-01-31 |  | NR road Contr.
197 | 143/0 | DD60+3 | WPS |  | 180.61 | 2025-01-18 | Completed. | Compeleted. | 2025-01-28 |  | Nav Durga
198 | 145A/2 | DA+3 | WPS | 623377 | 40.634 | 2025-01-19 | Completed. | Completed. | 2025-01-23 |  | Himanshi
199 | 143A/2 | DD45+0 | WPS |  | 128.427 | 2025-01-30 | Completed. | Completed. | 2025-02-10 |  | Nav Durga
200 | 143A/1 | DA+6 | WPS | 623377 | 40.634 | 2025-01-28 | Completed. | Completed. | 2025-01-31 |  | Nav Durga
201 | 155/4 | DA+0 | Wet | 881091 | 63.346 |  | Completed. | Completed. | 2025-04-12 |  | Nav Durga
202 | 102/0 | DD45+35(11.84M RC) | Pile |  |  | 2025-03-06 | Completed. | Completed. | 2025-06-28 |  | AK Construction
203 | 135/7 | DA+0 | WPS | 545016 | 39.126 | 2025-03-26 | Completed. | Completed. | 2025-04-03
204 | 154/0 | DD45+25(10.96 M RC) | Pile |  |  | 2025-04-04 | No work. | All pile completed. Pit D pile cap casting done. |  |  | KND
205 | 155/5 | DA+0 | WET | 881091 | 63.346 | 2025-04-13 | Completed. | Completed. | 2025-04-16 |  | Nav Durga
206 | 103/0 | DD45+25 | Pile |  |  | 2025-05-23 | Approach road making WIP | All pile(16) completed. Pit A pile cap shuttering worku/p. Pit D pile cap shuttering work u/p. |  |  | Choudhry Construction
17956.57

## FDN-NVSR
Foundation Part-II (NAVSARI SECTION)
Sl. No. | Location No. | Tower Type | Classification | Revenue | Concreting Volume in M3 | Trial pit start date | Start Date | Todays Status | Cumulative Status | End Date | Remarks | Sub-Contractor Name | Manpower | Earthing Status | Earthing Completed Date | Hindrance total days | Hindance details
1 | 197/3 | DA+0 | PS | 1086615 | 80.771 |  | 2023-08-18 | Completed. | Completed. | 2023-08-31 |  |  |  | Completed
2 | 195A/3 | DA+0 | PS | 1086615 | 80.771 |  | 2023-08-22 | Completed. | Completed. | 2023-10-01 |  |  |  | Completed
3 | 165/4 | DA+0 | WET | 881091 | 63.346 |  | 2023-10-20 | Completed. | Completed. | 2023-11-03 | Zealand |  |  | Completed
4 | 167/2 | DA+6 | WET | 986514 | 65.631 |  | 2023-11-13 | Completed. | Completed. | 2023-11-30 |  |  |  | Completed
5 | 167/3 | DA+6 | WET PADDY | 623377 | 40.634 |  | 2023-11-23 | Completed. | Completed. | 2023-11-30 |  |  |  | Completed
6 | 167/4 | DA+0 | WET | 881091 | 63.346 |  | 2023-12-09 | Completed. | Completed. | 2023-12-15 |  |  |  | Completed
7 | 195/3 | DA+6 | PS | 1215596 | 83.812 |  | 2023-12-07 | Completed. | Completed. | 2023-12-26 |  |  |  | Completed
8 | 195/4 | DA+0 | WET | 881091 | 63.346 |  | 2023-12-26 | Completed. | Completed. | 2024-01-12 |  |  |  | Completed
9 | 164/2 | DA+0 | WET | 881091 | 63.346 |  | 2023-12-28 | Completed. | Completed. | 2024-01-17 |  |  |  | Completed
10 | 163/3 | DA+0 | WET | 881091 | 63.346 |  | 2024-01-17 | Completed. | Completed. | 2024-01-23 |  |  |  | Completed
11 | 165/0 | DB2+0 | PS | 2481749.46 | 115.247 |  | 2024-01-09 | Completed. | Completed. | 2024-01-21 |  |  |  | Completed
12 | 163/2 | DA+0 | WET | 881091 | 63.346 |  | 2024-01-24 | Completed. | Completed. | 2023-01-29 |  |  |  | Completed
13 | 164/7 | DA+0 | WET | 881091 | 63.346 |  | 2024-01-18 | Completed. | Completed. | 2024-01-29 |  |  |  | Completed
14 | 163/1 | DA+0 | WET | 881091 | 63.346 |  | 2024-01-29 | Completed. | Completed. | 2024-02-05 |  |  |  | Completed
15 | 165/1 | DA+0 | PS | 1086615 | 80.771 |  | 2024-01-30 | Completed. | Completed. | 2024-02-09 |  |  |  | Completed
16 | 163/4 | DA+0 | WET | 881091 | 63.346 |  | 2024-02-08 | Completed. | Completed. | 2024-02-13 |  |  |  | Completed
17 | 159/3 | DA+0 | WET | 881091 | 63.346 |  | 2024-02-09 | Completed. | Completed. | 2024-02-16
18 | 163/5 | DA+0 | FS | 1287409 | 91.088 |  | 2024-02-14 | Completed. | Completed. | 2024-02-23 |  |  |  | Completed
19 | 164/5 | DA+0 | WFR | 947845 | 60.634 |  | 2024-02-12 | Completed. | Completed. | 2024-02-23
20 | 165/2 | DA+0 | WET | 881091 | 63.346 |  | 2024-02-13 | Completed. | Completed. | 2024-02-28 |  |  |  | Completed
21 | 163/6 | DA+0 | FS | 1287409 | 91.088 |  | 2024-02-22 | Completed. | Completed. | 2024-02-29 |  |  |  | Completed
22 | 164/6 | DA+0 | PS | 1086615 | 80.771 |  | 2024-03-11 | Completed. | Completed. | 2024-03-22 |  |  |  | Completed
23 | 165/3 | DA+6 | WET | 986514 | 65.631 |  | 2024-02-28 | Completed. | Completed. | 2024-03-10 |  |  |  | Completed
24 | 191/0 | DD45+25 | WET | 4465782 | 224.07 |  | 2024-03-06 | Completed. | Completed. | 2024-03-17 |  |  |  | Completed
25 | 187/3 | DA+0 | PS | 1086615 | 80.771 |  | 2024-03-09 | Completed. | Completed. | 2024-03-20 |  |  |  | Completed
26 | 191/1 | DA+0 | WET | 881091 | 63.346 |  | 2024-03-16 | Completed. | Completed. | 2024-03-21 |  |  |  | Completed
27 | 164/4 | DA+0 | WFR | 947845 | 60.634 |  | 2024-03-11 | Completed. | Completed. | 2024-03-22
28 | 257/3 | DA+0 | WET | 881091 | 63.346 |  | 2024-03-18 | Completed. | Completed. | 2024-03-30 |  |  |  | Completed
29 | 189/0 | DB2+6 | WET | 2143792.36 | 94.918 |  | 2024-03-22 | Completed. | Completed. | 2024-03-31 |  |  |  | Completed
30 | 159/0 | DB1+0 | WET | 1598139 | 79.944 |  | 2024-03-26 | Completed. | Completed. | 2024-04-04 |  |  |  | Completed
31 | 188/0 | DB1+6 | WET | 1741972 | 80.469 |  | 2024-04-01 | Completed. | Completed. | 2024-04-07 |  |  |  | Completed
32 | 187/2 | DA-3 | FS | 1287409 | 91.088 |  |  | Completed. | Completed. | 2024-04-13 |  |  |  | Completed
33 | 191A/1 | DA-3 | FS | 1287409 | 91.088 |  | 2024-04-14 | Completed. | Completed. | 2024-04-21 |  |  |  | Completed
34 | 267A/0 | DC2+9 (2M RC) | WET |  | 151.836 |  | 2024-04-13 | Completed. | Completed. | 2024-04-28 | RC done on 17-12-2024 | Jayesh Electrical |  | Completed
35 | 155/3 | DA+3 | WET | 986514 | 65.631 |  | 2024-04-08 | Completed. | Completed. | 2024-04-25 |  |  |  | Completed
36 | 262/1 | DA+0 | WET | 881091 | 63.346 |  | 2024-04-13 | Completed. | Completed. | 2024-04-27 |  |  |  | Completed
37 | 257/2 | DA-3 | WET | 881091 | 63.346 |  | 2024-04-21 | Completed. | Completed. | 2024-04-30 |  |  |  | Completed
38 | 193/0 | DD60+6 | WET | 4251845 | 255.731 |  | 2024-04-21 | Completed. | Completed. | 2024-04-30 |  |  |  | Completed
39 | 267A/3 | DA+0 | WET | 881091 | 63.346 |  | 2024-04-30 | Completed. | Completed. | 2024-05-08 |  |  |  | Completed
40 | 264/0 | DC1+6 | WET | 2633913 | 120.461 |  | 2024-05-01 | Completed. | Completed. | 2024-05-11
41 | 257/4 | DA+0 | WET | 881091 | 63.346 |  | 2024-05-03 | Completed. | Completed. | 2024-05-10 |  |  |  | Completed
42 | 155/0 | DD60+0 | WET | 3915704.88 | 252.474 |  | 2024-04-16 | Completed. | Completed. | 2024-05-11 |  |  |  | Completed
43 | 261/0 | DC2+18 | WET | 3336290 | 149.965 |  | 2024-05-03 | Completed. | Completed. | 2024-05-10 |  |  |  | Completed
44 | 191A/0 | DB2+0 | WET | 1880164 | 89.905 |  | 2024-04-25 | Completed. | Completed. | 2024-05-13 |  |  |  | Completed
45 | 265/0 | DB2+3 | WET | 2143792.36 | 94.918 |  | 2024-04-27 | Completed. | Completed. | 2024-05-12 |  |  |  | Completed
46 | 267A/2 | DA-3 | WET | 881091 | 63.346 |  | 2024-04-27 | Completed. | Completed. | 2024-05-15 |  |  |  | Completed
47 | 268/0 | DD60+6 | WET | 4251845 | 255.731 |  | 2024-05-12 | Completed. | Completed. | 2024-05-22 |  |  |  | Completed
48 | 267/0 | DC1+9 (2M RC) | WET |  | 139.849 |  | 2024-05-10 | Completed. | Completed. | 2024-05-21 | RC done o 16-12-2024. | Jayesh Electrical
49 | 195/0 | DC2+0 | PS | 3206945.94 | 168.913 |  | 2024-05-14 | Completed. | Completed. | 2024-05-24 | Again completed on 16-04-2025 |  |  | Completed
50 | 270/2 | DA+3 | WET | 986514 | 65.631 |  | 2024-05-20 | Completed. | Completed. | 2024-05-26 |  |  |  | Completed
51 | 270/1 | DA+0 | PS | 1086615 | 80.771 |  | 2024-05-27 | Completed. | Completed. | 2024-06-01 |  |  |  | Completed
52 | 271/5 | DA-3 | WET | 881091 | 63.346 |  | 2024-05-26 | Completed. | Completed. | 2024-06-01 |  |  |  | Completed
53 | 262/0 | DD45+9 | WET | 3953330 | 192.374 |  | 2024-05-13 | Completed. | Completed. | 2024-06-01 |  |  |  | Completed
54 | 257/0 | DC2+0 | WET | 2530056 | 134.785 |  | 2024-05-29 | Completed. | Completed. | 2024-06-01 |  |  |  | Completed
55 | 260/0 | DD60+18 | WBC |  | 448.208 |  |  | Completed. | Completed. | 2024-05-31 |  |  |  | Completed
56 | 272/1 | DA+9 | WET | 986514 | 65.631 |  | 2024-06-05 | Completed. | Completed. | 2024-06-12 |  |  |  | Completed
57 | 272/0 | DC1+6 | WET | 2633913 | 120.461 |  | 2024-06-04 | Completed. | Completed. | 2024-06-13 |  |  |  | Completed
58 | 269/0 | DD60+0 | WET | 3915704.88 | 252.474 |  | 2024-06-03 | Completed. | Completed. | 2024-06-14 |  |  |  | Completed
59 | 255/4 | DA+0 | WPS | 545016 | 39.126 |  | 2024-06-14 | Completed. | Completed. | 2024-06-21 |  |  |  | Completed
60 | 259/0 | DD60+18 | PS | 5611385.97 | 341.95 |  | 2024-06-14 | Completed. | Completed. | 2024-07-11
61 | 158A/0 | DD45+6 | WET | 3953330 | 192.374 |  | 2024-07-01 | Completed. | Completed. | 2024-07-30 |  | Kudiyaar |  | Completed
62 | 263/0 | DC2+0 | PS | 3206945.94 | 168.913 |  | 2024-10-09 | Completed. | Completed. | 2024-10-29 |  | Tes Transco | 23 | Completed | 2024-11-03
64 | 254/0 | DB2+0 | FS | 2986642.46 | 132.205 |  | 2024-08-04 | Completed. | Completed. | 2024-08-22 |  |  |  | Completed
65 | 267A/1 | DA+0 | FS | 1287409 | 91.088 |  | 2024-08-14 | Completed. | Completed. | 2024-09-23 |  | Rudra Associate |  | Completed
66 | 251/0 | DB1+9 | FS |  | 113.896 |  | 2024-09-04 | Completed. | Completed. | 2024-09-19 |  | Kudiyaar |  | Completed
67 | 255/0 | DD60+3 | FS | 5918512 | 351.748 |  | 2024-09-13 | Completed. | Completed. | 2024-10-10 |  | Tes Transco |  | Completed
68 | 169/0 | DD45+18 | PS | 5320583 | 257.278 |  | 2024-10-22 | Completed. | Completed. | 2024-11-06 |  | M/s Rajesh Singh | 18
69 | 168/2 | DA+0 | FS | 1287409 | 91.088 |  | 2024-10-07 | Completed. | Completed. | 2024-10-24 |  | M/s Rajesh Singh
71 | 155/1 | DA+0 | PS | 1086615 | 80.771 |  | 2024-10-03 | Completed. | Completed | 2024-10-24 |  | Jyoti Const. |  | Completed | 2024-10-23
72 | 155/2 | DA+3 | PS | 1215596 | 83.812 |  | 2024-10-03 | Completed. | Completed | 2024-10-11 |  | Jyoti Const. |  | Completed | 2024-10-13
74 | 155/6 | DA-3 | PS | 1086615 | 80.771 |  | 2024-10-15 | Completed. | Completed. | 2024-10-29 |  | M/s Rudra Associate | 14 | Completed | 2024-10-30
76 | 158B/2 | DA+3 | PS | 1215596 | 83.812 |  | 2024-10-20 | Completed. | Completed. | 2024-10-26 |  | Maa Bhawani |  | Completed
77 | 164/0 | DB2+0 | FS | 2986642.46 | 132.205 |  | 2024-10-21 | Completed. | Completed. | 2024-11-07 |  | Tes Transco | 28
78 | 158B/0 | DD45+18 | PS | 5320583 | 257.278 |  | 2024-10-24 | Completed. | Completed. | 2024-10-31 |  | Maa Bhawani | 20 | Completed
79 | 171/0 | DD60+25 (3M RC) | PS |  | 353.162 |  | 2024-10-26 | Completed. | Completed | 2024-11-19 |  | Jyoti Const. | 14
80 | 156/0 | DD60+3 | PS | 5188063.13 | 309.952 |  | 2024-10-30 | Completed. | Completed | 2024-11-24 |  | Rudra Associate | 14
83 | 158B/1 | DA+3 | PS | 1215596 | 83.812 |  | 2024-11-06 | Completed. | Completed. | 2024-11-09 |  | Maa Bhawani |  | Completed
84 | 272A/0 | DB1+18 (2M RC) | PS |  | 117.99 |  | 2024-11-05 | Completed. | Completed | 2024-11-13 |  | Tes Transco |  | Completed | 2024-11-15
85 | 272A/2 | DA+0 | WET | 881091 | 63.346 |  | 2024-11-06 | Completed. | Completed | 2024-11-13 |  | Tes Transco |  | Completed | 2024-11-14
86 | 272A/1 | DA+6 | WET | 986514 | 65.631 |  | 2024-11-07 | Completed. | Completed | 2024-11-17 |  | Tes Transco |  | Completed | 2024-11-19
87 | 168/1 | DA-3 | Wet | 881091 | 63.346 |  | 2024-11-09 | Completed. | Completed. | 2024-11-18 |  | M/s Rajesh Singh
88 | 197/4 | DA+0 | WET | 881091 | 63.346 |  | 2024-11-08 | Completed. | Completed. | 2024-11-10 |  | Maa Bhawani
90 | 197/0 | DD60+9 | Wet | 4251845 | 255.731 |  | 2024-11-12 | Completed. | Completed. | 2024-11-18 |  | Maa Bhawani
91 | 255/3 | DA+3 | Wet | 986514 | 65.631 |  | 2024-11-13 | Completed. | Completed. | 2024-11-21 |  | Paresh mahto | 15 | Completed
92 | 198/0 | DC1+0 | Wet | 2328166.27 | 117.033 |  | 2024-11-13 | Completed. | Completed. | 2024-11-30 |  | M/s Rajesh Singh
93 | 266/1 | DB1+6 | Wet | 1741972 | 80.469 |  | 2024-11-15 | Completed. | Completed. | 2024-11-22 |  | Tes Transco |  | Completed | 2024-11-22
94 | 196/0 | DD60+9 | WBC |  | 401.731 |  | 2024-11-16 | Completed. | Completed. | 2024-11-30 |  | Maa Bhawani
95 | 198/1 | DA+0 | Wet | 881091 | 63.346 |  | 2024-11-17 | Completed. | Completed. | 2024-12-12 |  | Kumar
96 | 272/7 | DA+9 (2M RC) | Wet |  | 71.29 |  | 2024-11-20 | Completed. | Completed. | 2024-12-10 |  | Tes Transco |  | Completed
97 | 272/2 | DA-3 | Wet | 881091 | 63.346 |  | 2024-11-18 | Completed. | Completed. | 2024-11-26 |  | Tes Transco |  | Completed | 2024-11-28
98 | 197/1 | DA+0 | PS | 1086615 | 80.771 |  | 2024-11-18 | Completed. | Completed. | 2024-11-22 |  | Maa Bhawani
99 | 272/5 | DB1+0 | Wet | 1598139 | 79.944 |  | 2024-11-23 | Completed. | Completed. | 2024-11-30 |  | Tes Transco |  | Completed.
100 | 269/1 | DA+0 | WeT | 881091 | 63.346 |  | 2024-11-23 | Completed. | Completed. | 2024-11-29 |  | Paresh |  | Completed.
101 | 197/2 | DA+0 | Wet | 881091 | 63.346 |  | 2024-11-25 | Completed. | Completed | 2024-11-30 |  | Maa Bhawani
102 | 271/0 | DC1+0 | Wet | 2328166.27 | 117.033 |  | 2024-11-23 | Completed. | Completed. | 2024-11-30 |  | Tes Transco |  | Completed.
103 | 271/3 | DA-3 | WBC | 1686873 | 109.919 |  | 2024-12-01 | Completed. | Completed. | 2024-12-08 |  | Jayesh Electrical |  | Completed.
| 185/1 | DA+9 | Wet | 986514 | 65.631 |  | 2024-11-28 | Completed. | Completed. | 2024-11-30 |  | Jyoti
105 | 270/4 | DA+0 | Wet | 881091 | 63.346 |  | 2024-11-28 | Completed. | Completed. | 2024-12-20 |  | Maa Bhawani(Jitu)
106 | 166/0 | DD60+6 | PS | 5188063.13 | 309.952 |  | 2024-11-28 | Completed. | Completed. | 2024-12-10 |  | Jyoti Constr.
107 | 192/0 | DC1+0 | PS | 3074652.99 | 138.086 |  | 2024-11-29 | Completed. | Completed. | 2024-12-14 |  | M/s Rajesh Singh
108 | 266/0 | DB1+0 | Wet | 1598139 | 79.944 |  | 2024-12-01 | Completed. | Completed. | 2024-12-08 |  | Kastabhaja |  | Completed.
109 | 195A/0 | DB1+0 | PS | 2122856.48 | 98.821 |  | 2024-11-30 | Completed. | Completed. | 2024-12-28 |  | Hari Krishna
110 | 190/0 | DD45+25 | Wet | 4465782 | 224.07 |  | 2024-11-30 | Completed. | Completed. | 2024-12-31 |  | Tes transco
111 | 182A/0 | DD45+6(2M RC) | PS |  | 239.926 |  | 2024-12-02 | Completed. | Completed. | 2024-12-22 |  | Jyoti
112 | 270/7 | DA-3 | Wet | 881091 | 63.346 |  | 2024-12-01 | Completed. | Completed. | 2024-12-06 |  | Tes Trasnsco |  | Completed.
113 | 178/0 | DD60+6 | PS | 5188063.13 | 309.952 |  | 2024-12-23 | Completed. | Completed. | 2024-12-31 |  | Jyoti
114 | 195A/2 | DA+6 | FS | 1442822 | 94.623 |  | 2024-12-07 | Completed. | Completed. | 2024-12-12 |  | Maa Bhawanis
115 | 275/0 | DD45+0(2M RC) | Wet |  | 206.583 |  | 2024-12-09 | Completed. | Completed. | 2024-12-23 |  | Tes Transco |  | Completed. | 2024-12-23
116 | 272/4 | DA+3 | Wet | 986514 | 65.631 |  | 2024-12-08 | Completed. | Completed. | 2024-12-12 |  | Tes Transco |  | Completed.
117 | 273/2 | DA+6 | Wet | 986514 | 65.631 |  | 2024-12-09 | Completed. | Completed. | 2024-12-15 |  | Kastabhanja |  | Completed. | 2024-12-15
118 | 255/2 | DA+0 | Wet | 881091 | 63.346 |  | 2024-12-10 | Completed. | Completed. | 2024-12-15 |  | Jayesh Electrical |  | Completed.
119 | 173/0 | DD60+25 | PS | 5611385.97 | 341.95 |  | 2024-12-10 | Completed. | Completed. | 2024-12-24 |  | Value Constr.
120 | 167/1 | DA+9 | FS | 1442822 | 94.623 |  | 2024-12-21 | Completed. | Completed. | 2024-12-28 |  | Sukhriddin
121 | 272/3 | DA+3 | Wet | 986514 | 65.631 |  | 2024-12-14 | Completed. | Completed. | 2024-12-21 |  | Tes transco |  | Completed
122 | 191/2 | DA-3 | Wet | 881091 | 63.346 |  | 2024-12-14 | Completed. | Completed. | 2024-12-21 |  | Khodiyar Krupa
123 | 172/0 | DD60+25 | PS | 5611385.97 | 341.95 |  | 2024-12-16 | Completed. | Completed. | 2025-01-04 |  | Khodiyar Krupa
124 | 172/1 | DA+3 | PS | 1215596 | 83.812 |  | 2024-12-24 | Completed. | Completed. | 2024-12-28 |  | Value Constr.
125 | 195/1 | DA+6 | PS | 1215596 | 83.812 |  | 2024-12-30 | Completed | Completed | 2025-01-07 |  | Hari Krishna
126 | 191/3 | DA-3 | PS | 1086615 | 80.771 |  | 2024-12-17 | Completed. | Completed. | 2024-12-24 |  | Khodiyar Krupa
127 | 276/0 | DD60+0(2M RC) | Wet |  | 265.697 |  | 2024-12-18 | Completed. | Completed. | 2024-12-31 |  | Kastabhanja
128 | 270A/0 | DC2+0 | Wet | 2530056 | 134.785 |  | 2024-12-18 | Completed. | Completed. | 2024-12-31 |  | Tes transco |  | Completed | 2024-12-31
129 | 257/1 | DA+0 | FS | 1287409 | 91.088 |  | 2024-12-18 | Completed. | Completed | 2024-12-31 |  | Jayesh Electrical |  | Completed | 2024-12-31
130 | 272A/6 | DA-3 | Wet | 881091 | 63.346 |  | 2024-12-22 | Completed. | Completed. | 2024-12-29 |  | Tes Transco |  | Completed | 2024-12-31
131 | 186/0 | DD60+35 | Wet | 7665610 | 315.149 |  | 2024-12-28 | Completed. | Completed. | 2025-04-04 | Again start date is 30-03-2025 | Sukhriddin
132 | 272A/3 | DA+0 | Wet | 881091 | 63.346 |  | 2024-12-28 | Completed. | Completed. | 2025-01-03 |  | Tes Transco |  | Completed. | 2025-01-04
133 | 184/0 | DD60+25 | Wet | 4801423 | 298.554 |  | 2024-12-28 | Completed. | Completed | 2025-01-08 |  | Maa Bhawani
134 | 172/2 | DA+6 | PS | 1215596 | 83.812 |  | 2024-12-29 | Completed. | Completed. | 2025-01-04 |  | Value Constr.
135 | 274/0 | DC1+0 | Wet | 2328166.27 | 117.033 |  | 2025-01-02 | Completed. | Completed. | 2025-01-11 |  | Tes Transco |  | Completed | 2025-01-13
136 | 269/2 | DA+6 | PS | 1215596 | 83.812 |  | 2025-01-02 | Completed. | Completed | 2025-01-08 |  | Jayesh Electrical |  | Completed | 2025-01-08
137 | 179/0 | DD60+0 | WBC |  | 396.566 |  | 2024-12-31 | Completed. | Completed. | 2025-01-18 |  | Jyoti
138 | 255/1 | DA+6 | Wet | 986514 | 65.631 |  | 2025-01-02 | Completed. | Completed. | 2025-01-07 |  | Kastabhanja
139 | 272A/4 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-02 | Completed. | Completed | 2025-01-08 |  | Tes Transco |  | Completed | 2025-01-08
140 | 272A/5 | DA+3 | Wet | 986514 | 65.631 |  | 2025-01-04 | Completed. | Completed. | 2025-01-11 |  | Tes Transco |  | Completed | 2025-01-13
141 | 272A/7 | DA-3 | Wet | 881091 | 63.346 |  | 2025-01-05 | Completed. | Completed. | 2025-01-12 |  | Tes Transco
142 | 270/3 | DA-3 | WBC | 1686873 | 109.919 |  | 2025-01-07 | Completed. | Completed. | 2025-01-17 |  | Tes Transco
143 | 189/1 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-06 | Completed | Completed | 2025-01-09 |  | Value Constr.
144 | 167/0 | DD60+0 | WBC |  | 396.566 |  | 2025-01-06 | Completed. | Completed. | 2025-01-18 |  | Sukhriddin
146 | 248/6 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-08 | Completed. | Completed | 2025-01-11 |  | Kastabhanja
147 | 249/0 | DB2+0 | Wet | 1880164 | 89.905 |  | 2025-01-14 | Completed. | Completed. | 2025-01-19 |  | Khodiyar Krupa
148 | 249/1 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-07 | Completed. | Completed. | 2025-01-10 |  | Khodiyar Krupa |  | Completed | 2025-01-18
149 | 249/2 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-11 | Completed. | completed. | 2025-01-13 |  | Khodiyar Krupa |  | Completed | 2025-01-18
150 | 195/5 | DA+6 | WBC | 1821043 | 113.924 |  | 2025-01-08 | Completed. | Completed. | 2025-01-16 |  | Hari Krishna
153 | 250/0 | DD60+0 | Wet | 3915704.88 | 252.474 |  | 2025-01-14 | Completed. | Completed. | 2025-01-23 |  | Jayesh Electrical |  | Completed. | 2025-01-23
154 | 249/3 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-10 | Completed. | Completed. | 2025-01-13 |  | Jayesh Electrical
155 | 253/0 | DC1+0 | Wet | 2328166.27 | 117.033 |  | 2025-01-08 | Completed | Completed. | 2025-01-19 |  | Tes Transco
156 | 250/1 | DA-3 | Wet | 881091 | 63.346 |  | 2025-01-12 | Completed. | Completed. | 2025-01-16 |  | Kastabhanja
157 | 252/0 | DC1+18 | Wet | 3216269 | 131.849 |  | 2025-01-17 | Completed. | Completed. | 2025-01-24 |  | Kastabhanja
158 | 209/0 | DC1+0 | Wet | 2328166.27 | 117.033 |  | 2025-01-09 | Completed. | Completed. | 2025-01-17 |  | Velly Constr.
159 | 209/1 | DA+3 | Wet | 986514 | 65.631 |  | 2025-01-13 | Completed. | Completed. | 2025-01-20 |  | Velly Constr.
160 | 211/1 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-13 | Completed. | Completed. | 2025-01-19 |  | Tower Foundation
161 | 211/2 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-21 | Completed | Compleed. | 2025-01-25 |  | Tower Foundation
162 | 218/1 | DA+3 | Wet | 986514 | 65.631 |  | 2025-01-12 | Completed. | Completed. | 2025-01-19 |  | Tes Transco
164 | 219/0 | DC2+18 | Wet | 3336290 | 149.965 |  | 2025-01-12 | Completed. | Completed. | 2025-01-25 |  | Tes Transco
167 | 208/0 | DD60+25 | Wet | 4801423 | 298.554 |  | 2025-01-20 | Completed. | Completed. | 2025-01-29 |  | Velly
168 | 215/0 | DB1+6 | Wet | 1741972 | 80.469 |  | 2025-01-12 | Completed. | Completed. | 2025-01-18 |  | BLG Infratech
169 | 213/0 | DD60+3 | WBC |  | 401.731 |  | 2025-01-16 | Completed. | Completed. | 2025-02-04 |  | Tes Transco
171 | 200/0 | DB2+18 | Wet | 2472338 | 111.669 | 2025-01-11 | 2025-01-19 | Completed. | Completed. | 2025-01-31 |  | Hari Krishna
173 | 271/2 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-14 | Completed | Completed. | 2025-01-21 |  | Tes Transco
174 | 270/5 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-20 | Completed. | Completed. | 2025-01-28 |  | Tes Transco
175 | 270/6 | DA-3 | Wet | 881091 | 63.346 |  | 2025-01-18 | Completed. | Completed. | 2025-01-24 |  | Tes Transco
176 | 215/1 | DA+9 | Wet | 986514 | 65.631 |  | 2025-01-17 | Completed. | Completed. | 2025-01-22 |  | BLG
181 | 213/1 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-23 | Completed. | Completed. | 2025-01-31 |  | Tes Transco
182 | 180/0 | DD45+9 (3M RC) | Wet |  | 213.318 |  | 2025-01-25 | Completed. | Completed. | 2025-01-31 |  | Jyoti
183 | 181/3 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-20 | Completed. | Completed. | 2025-01-23 |  | Jyoti
184 | 206/0 | DD60+25 | Wet | 4801423 | 298.554 |  | 2025-01-21 | Completed. | Completed. | 2025-01-28 |  | Sukhridin
185 | 211A/1 | DA-3 | Wet | 881091 | 63.346 |  | 2025-01-21 | Completed. | Completed. | 2025-01-25 |  | Khodiyar
186 | 271/4 | DA-3 | Wet | 881091 | 63.346 |  | 2025-01-23 | Completed. | Completed. | 2025-01-29 |  | Tes Transco
187 | 224/0 | DC2+6 | Wet | 2772635 | 138.207 |  | 2025-01-23 | Completed. | Completed. | 2025-01-30 |  | Khodiyar
188 | 211A/0 | DB2+0 | Wet | 1880164 | 89.905 |  | 2025-02-02 | Completed. | Completed. | 2025-02-08 |  | Tower foundation
189 | 227/0 | DB1+6 | PS | 2075500 | 99.33 |  | 2025-01-26 | Completed. | Completed. | 2025-02-04 |  | Ammu Eng.
190 | 248/4 | DA+3 | Wet | 986514 | 65.631 |  | 2025-01-25 | Completed. | Completed. | 2025-01-29 |  | Kastabhanja
191 | 266/2 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-25 | Completed. | Completed. | 2025-01-29 |  | Jayesh Electrical
192 | 223/0 | DC1+0 | Wet | 2328166.27 | 117.033 |  | 2025-01-26 | Completed. | Completed. | 2025-01-31 |  | BLG
193 | 205/1 | DA-3 | Wet | 881091 | 63.346 |  | 2025-01-29 | Completed. | Completed. | 2025-01-31 |  | Sukhridin
196 | 248/5 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-29 | Completed. | Completed. | 2025-01-31 |  | Kastabhanja
197 | 211A/2 | DA+0 | Wet | 881091 | 63.346 |  | 28-01-202 | Completed. | Completed. | 2025-01-31 |  | Tower Foundation
198 | 270/0 | DD45+0 | FS | 5295995.92 | 266.818 |  | 2025-01-30 | Completed. | Completed. | 2025-02-10 |  | Jayesh Electrical
200 | 223/3 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-30 | Completed. | Completed. | 2025-02-02 |  | Khodiyar
202 | 214/0 | DD45+0 | PS | 4512711.95 | 233.46 |  | 2025-01-31 | Completed. | Completed. | 2025-02-17 |  | Tes Transco
203 | 229/3 | DA+0 | Wet | 881091 | 63.346 |  | 2025-02-01 | Completed. | Completed. | 2025-02-05 |  | Velly Constr.
204 | 199/0 | DD45+18 | Wet | 4465782 | 224.07 |  | 02-02-025 | Completed. | Completed. | 2025-02-13 |  | Hari Krishna
205 | 181/0 | DD45+18 | Wet | 4465782 | 224.07 |  | 2025-02-02 | Completed. | Completed. | 2025-02-08 |  | Jyoti
206 | 225/1 | DA+6 | Wet | 986514 | 65.631 |  | 2025-02-03 | Completed. | Completed. | 2025-02-07 |  | BLG
207 | 225/0 | DD60+0 | Wet | 3915704.88 | 252.474 |  | 2025-02-04 | Completed. | Completed. | 2025-02-12 |  | Khodiyar
208 | 229/0 | DD60+18 | WBC |  | 448.208 |  | 2025-02-02 | Completed. | Completed. | 2025-02-11 |  | Sukhridin
209 | 226/0 | DC2+0 | Wet | 2530056 | 134.785 |  | 2025-02-03 | Completed. | Completed. | 2025-02-10 |  | Kastabhanja
210 | 214/1 | DA+6 | Wet | 986514 | 65.631 |  | 2025-02-03 | Completed. | Completed. | 2025-02-12 |  | Tes Transco
211 | 220/0 | DD45+9 | Wet | 3953330 | 192.374 |  | 2025-02-02 | Completed. | Completed. | 2025-02-11 |  | Tes Transco
212 | 229/5 | DA+0 | Wet | 881091 | 63.346 |  | 2025-02-05 | Completed. | Completed. | 2025-02-08 |  | Velly Constr.
213 | 233/0 | DD45+0 | Wet | 3743190.59 | 189.081 |  | 2025-02-07 | Completed. | Competed. | 2025-02-15 |  | Ammu Engg.-1
214 | 220/1 | DA+3 | Wet | 986514 | 65.631 |  | 2025-02-07 | Completed. | Completed. | 2025-02-16 |  | Tes Transco
215 | 231/0 | DD60+6 | Wet | 4251845 | 255.731 |  | 2025-02-09 | Completed. | Completed. | 2025-02-18 |  | BLG
217 | 212/0 | DD45+3 | Wet | 3953330 | 192.374 |  | 2025-02-10 | Completed. | Completed. | 2025-02-21 |  | Tower Foundation
218 | 230/0 | DD60+0 | Wet | 3915704.88 | 252.474 |  | 2025-02-10 | Completed. | Completed. | 2025-02-17 |  | Velly Constr.
219 | 174/0 | DD60+18 | FS | 6685851 | 390.682 |  | 2025-02-11 | Completed. | Completed. | 2025-02-22 |  | Jyoti
220 | 229/2 | DA+6 | Wet | 986514 | 65.631 |  | 2025-02-10 | Completed. | Completed. | 2025-02-13 |  | Murgan
221 | 221/0 | DD60+18 | FS | 6685851 | 390.682 |  | 2025-02-11 | Completed. | Completed. | 2025-02-25 |  | Tes Transco
222 | 222/0 | DD60+25 | FS | 6685851 | 390.682 |  | 2025-02-13 | Completed. | Completed. | 2025-02-23 |  | Kastbhanja
223 | 205/0 | DD60+3 (2M RC) | Wet |  | 282.692 |  | 2025-02-13 | Completed. | Completed. | 2025-02-20 |  | Sukhridin
224 | 237/6 | DA+3 | Wet | 986514 | 65.631 |  | 2025-02-12 | Completed. | Completed. | 2025-02-16 |  | Jayesh Electrical
225 | 237/0 | DD45+9 (3M RC) | Wet |  | 213.318 |  | 2025-02-14 | Completed. | Completed. | 2025-02-23 |  | Khodiyar
226 | 234/0 | DD45+0 | Wet | 3743190.59 | 189.081 |  | 2025-02-13 | Completed. | Completed. | 2025-02-21 |  | Ammu Engg.
227 | 223/2 | DA+0 | Wet | 881091 | 63.346 |  | 2025-02-14 | Completed. | Completed. | 2025-02-18 |  | Murgan
228 | 198/2 | DA+0 | Wet | 881091 | 63.346 |  | 2025-02-16 | Completed. | Completed. | 2025-02-23 |  | Hari Krishna
229 | 187/0 | DD60+25 | Wet | 4801423 | 298.554 |  | 2025-02-17 | Completed. | Completed. | 2025-03-03 |  | Jyoti-2
230 | 235/0 | DC2+3 | PS |  | 162.896 |  | 2025-02-17 | Completed. | Completed. | 2025-02-28 |  | Ammu Engg.
231 | 245/1 | DA+0 | FS | 1287409 | 91.088 |  | 2025-02-16 | Completed. | Completed. | 2025-02-22 |  | Neelkanth | 25
232 | 217A/1 | DA+3 | PS | 1215596 | 83.812 |  | 2025-02-17 | Completed. | Completed. | 2025-02-25 |  | Tes Transco
233 | 240/0 | DD60+25 | FS | 6685851 | 390.682 |  | 2025-02-18 | Completed. | Completed. | 2025-02-28 |  | Jayesh Electrical
235 | 248/2 | DA+9 | Wet | 986514 | 65.631 |  | 2025-02-18 | Completed. | Completed. | 2025-02-24 |  | Ketan
236 | 223/1 | DA+0 | Wet | 881091 | 63.346 |  | 2025-02-18 | Completed. | Completed. | 2025-02-21 |  | Murgan
237 | 232/0 | DD60+3 | Wet | 4251845 | 255.731 |  | 2025-02-19 | Completed. | Completed. | 2025-02-28 |  | Velly Constr
238 | 242/0 | DB1+0 | FS |  | 113.343 |  | 2025-02-19 | Completed. | Completed. | 2025-02-27 |  | Tes Trasnsco
239 | 242/2 | DA-3 | Wet | 881091 | 63.346 |  | 2025-02-18 | Completed. | Completed. | 2025-02-21 |  | BLG
241 | 184/1 | DB1+6 | Wet | 1741972 | 80.469 |  | 2025-02-20 | Completed. | Completed. | 2025-02-26 |  | Arvind
242 | 195/2 | DA+0 | Wet | 881091 | 63.346 |  | 2025-02-21 | Completed. | Completed. | 2025-02-26 |  | Himanshi
243 | 203/1 | DD60+6 | Wet | 4251845 | 255.731 |  | 2025-02-21 | Completed. | Completed. | 2025-02-28 |  | Sukhriddin
244 | 237/4 | DA+0 | PS | 1086615 | 80.771 |  | 2025-02-22 | Completed. | Completed. | 2025-02-27 |  | Tower Foundation
245 | 247/1 | DA+0 | FS | 1287409 | 91.088 |  | 2025-02-23 | Completed. | Completed. | 2025-02-26 |  | Murgan
246 | 237/5 | DA-3 | Wet | 881091 | 63.346 |  | 2025-02-23 | Completed. | Completed. | 2025-02-28 |  | Ammu Engg-1
247 | 273/1 | DA+6 | WBC | 1821043 | 113.924 |  | 2025-02-22 | Completed. | Completed. | 2025-02-27 |  | Neelkanth
248 | 247/4 | DA+0 | Wet | 881091 | 63.346 |  | 2025-02-24 | Completed. | Completed. | 2025-02-27 |  | BLG
249 | 181/4 | DA+0 | Wet | 881091 | 63.346 |  | 2025-02-25 | Completed. | Completed. | 2025-02-28 |  | Jyoti
250 | 247/2 | DA+3 | Wet | 986514 | 65.631 |  | 2025-02-24 | Completed. | Completed. | 2025-02-28 |  | Neel Kanth
251 | 272/6 | DA+3 | FS | 1442822 | 94.623 |  | 2025-02-26 | Completed. | Completed. | 2025-03-04 |  | New Gang
252 | 248/1 | DA+9 | Wet | 986514 | 65.631 |  | 2025-02-25 | Completed. | Completed. | 2025-02-28 |  | Ketan
253 | 217A/2 | DA+0 | PS | 1086615 | 80.771 |  | 2025-02-25 | Completed. | Completed. | 2025-02-28 |  | Tes Transco
254 | 216/0 | DB2+25(2M RC) | Wet |  | 120.61 |  | 2025-02-27 | Completed. | Completed. | 2025-03-12 |  | Tes Transco
255 | 205/2 | DA+3 | Wet | 986514 | 65.631 |  | 2025-02-26 | Completed. | Completed. | 2025-02-28 |  | Kastbahana
256 | 201/0 | DC2+18 | Wet | 3336290 | 149.965 |  | 2025-02-26 | Completed. | Completed. | 2025-03-06 |  | Hari Krishna
257 | 237/1 | DA+0 | Wet | 881091 | 63.346 |  | 2025-02-24 | Completed. | Completed. | 2025-02-27 |  | Khodiyar
258 | 237/2 | DA-3 | Wet | 881091 | 63.346 |  | 2025-02-26 | Completed. | Completed. | 2025-02-28 |  | Khodiyar
259 | 182/0 | DD60+0 | Wet | 3915704.88 | 252.474 |  | 2025-02-27 | Completed. | Completed. | 2025-03-13 |  | Arvind
260 | 185/0 | DC2+0 | Wet | 2530056 | 134.785 |  | 2025-02-27 | Completed. | Completed. | 2025-03-13 |  | Himanshi
261 | 247/0 | DD60+0 | FS | 5576159.92 | 346.952 |  | 2025-02-27 | Completed. | Completed. | 2025-03-12 |  | Murgan
263 | 211/0 | DB1+9 | Wet | 1741972 | 80.469 |  | 2025-03-02 | Completed. | Completed. | 2025-03-16 |  | Tower foundation
264 | 244/0 | DC1+9 | WBC |  | 197.882 |  | 2025-03-01 | Completed. | Completed. | 2025-03-13 |  | BLG
265 | 228/0 | DD60+25 | PS | 5611385.97 | 341.95 |  | 2025-03-01 | Completed. | Completed. | 2025-05-28 | Again start date is 14-05-2025 | Kastabhanja
266 | 204/0 | DD60+9 | Wet | 4251845 | 255.731 |  | 2025-03-02 | Completed. | Completed. | 2025-03-08 |  | Sukhriddin
267 | 210/0 | DB2+18 | Wet | 2472338 | 111.669 |  | 2025-03-02 | Completed. | Completed. | 2025-03-20 |  | Tes Trasnsco
268 | 241/0 | DB2+9 | WBC | 3850981 | 173.061 |  | 2025-03-23 | Completed. | Completed. | 2025-04-06 |  | Jayesh Electrical
269 | 246/0 | DD60+0 | PS | 4780790.5 | 306.052 |  | 2025-03-02 | Completed. | Completed. | 2025-03-21 |  | Khodiyar
270 | 271/1 | DA-3 | FS | 1287409 | 91.088 |  | 2025-03-03 | Completed. | Completed. | 2025-03-13 |  | Neekl Kanta
273 | 236/0 | DB2+0 | Wet | 1880164 | 89.905 |  | 2025-03-02 | Completed. | Completed. | 2025-03-19 |  | Ammu Engg.
274 | 237/3 | DA-3 | Wet | 881091 | 63.346 |  | 2025-03-03 | Completed. | Completed. | 2025-03-07 |  | Ammu
275 | 242/1 | DA-3 | Wet | 881091 | 63.346 |  | 2025-03-02 | Completed. | Completed. | 2025-03-06 |  | Tes Transco
277 | 181/2 | DA+0 | Wet | 881091 | 63.346 |  | 2025-03-03 | Completed. | Completed. | 2025-03-06 |  | Jyoti
279 | 187/1 | DA+3 | Wet | 986514 | 65.631 |  | 2025-03-04 | Completed. | Completed. | 2025-03-10 |  | Jyoti
280 | 247/3 | DA-3 | Wet | 881091 | 63.346 |  | 2025-03-03 | Completed. | Completed. | 2025-03-07 |  | Khodiyar
281 | 248/3 | DA+6 | Wet | 986514 | 65.631 |  | 2025-03-03 | Completed. | Completed. | 2025-03-07 |  | Ketan
282 | 248/0 | DC2+9 | Wet | 2772635 | 138.207 |  | 2025-03-09 | Completed. | Completed. | 2025-03-26 |  | Ketan
283 | 242/3 | DA-3 | Wet | 881091 | 63.346 |  | 2025-03-10 | Completed. | Completed. | 2025-03-13 |  | Khodiyar
284 | 181/1 | DA+0 | Wet | 881091 | 63.346 |  | 2025-03-13 | Completed. | Completed. | 2025-03-20 |  | Himanshi
285 | 218/0 | DD60+0 | Wet | 3915704.88 | 252.474 |  | 2025-03-10 | Completed. | Completed. | 2025-03-31 |  | Tes Transcvo
286 | 168/0 | DC1+0 | Wet | 2328166.27 | 117.033 |  | 2025-03-13 | Completed. | Completed. | 2025-03-27 |  | Ammu Engg.
287 | 203/0 | DD60+55(4.5M RC) | WBC |  | 768.133 |  | 2025-03-09 | Completed. | Completed. | 2025-03-31 |  | Sukhriddin
288 | 177/0 | DD60+0 | PS | 4780790.5 | 306.052 |  | 2025-03-12 | Completed. | Completed. | 2025-03-22 |  | Jyoti
289 | 175/1 | DA+0 | Wet | 881091 | 63.346 |  | 2025-03-16 | Completed. | Completed. | 2025-03-19 |  | Arvind
290 | 245/0 | DD45+0 | FS | 5295995.92 | 266.818 |  | 2025-03-16 | Completed. | Completed. | 2025-03-26 |  | BLG
293 | 229/4 | DA+0 | Wet | 881091 | 63.346 |  | 2025-03-14 | Completed. | Completed. | 2025-03-17 |  | Tes Transco
294 | 222/1 | DB1+3 | Wet | 1741972 | 80.469 |  | 2025-03-14 | Completed. | Completed. | 2025-03-17 |  | Kastabhanja
295 | 217A/0 | DB1+3 | Wet | 1741972 | 80.469 |  | 2025-03-19 | Completed. | Completed. | 2025-03-23 |  | Kastabhanja
296 | 217/0 | DD45+25(2M RC) | Wet |  | 231.258 |  | 2025-03-18 | Completed. | Completed. | 2025-03-31 |  | Tes Transco
297 | 194/0 | DD60+6 | Wet | 4251845 | 255.731 |  | 2025-03-19 | Completed. | Completed. | 2025-03-31 |  | Himanshi |  |  |  | 04 days idle due to 02 pit in row
298 | 175/0 | DD45+0 | Wet | 3743190.59 | 189.081 |  | 2025-03-22 | Completed. | Completed. | 2025-03-28 |  | Arvind
299 | 243/0 | DB1+9 | FS |  | 113.896 |  | 2025-03-23 | Completed. | Completed. | 2025-03-29 |  | Khodiyar
300 | 174/1 | DB1+0 | PS | 2122856.48 | 98.821 |  | 2025-03-26 | Completed. | Completed. | 2025-03-30 |  | Jyoti
301 | 195A/1 | DA+6 | FS | 1442822 | 94.623 |  | 2025-03-25 | Completed. | Completed. | 2025-03-29 |  | kastabhanja
302 | 229/1 | DB1+6 | Wet | 1741972 | 80.469 |  | 2025-03-25 | Completed. | Completed. | 2025-04-07 |  | Tes Transco
303 | 244/1 | DB1+9 | WBC |  | 138.164 |  | 2025-03-27 | Completed. | Completed. | 2025-03-31 |  | BLG
304 | 201/1 | DD60+9 (2M RC) | Wet | 5379537 | 282.692 |  | 2025-03-30 | Completed. | Completed. | 2025-04-09 |  | Kastabbhanja
305 | 239/0 | DD60+25 | Wet | 4801423 | 298.554 |  | 2025-04-01 | Completed. | Completed. | 2025-04-11 |  | Khodiyar Krupa
306 | 202/0 | DD60+55(4.5M RC) | WBC |  | 768.133 |  | 2025-04-05 | Completed. | Completed. | 2025-05-06 |  | Sukhriddin | 18 |  | 2025-05-09
307 | 183/0 | DD60+25 | PS | 5611385.97 | 341.95 |  | 2025-04-07 | Completed. | Completed. | 2025-04-20 |  | Tes Transco | 26
308 | 273/0 | DB2+0 | FS | 2986642.46 | 132.205 |  | 2025-05-01 | Completed. | Completed. | 2025-06-13 | Again start date is 06-06-2025 | Kastabhanja |  |  |  |  | Hindrance from 02-05-2025 to continue
309 | 176/0 | DD60+0 | Wet | 3915704.88 | 252.474 |  | 2025-05-15 | Completed. | Completed. | 2025-05-23 |  | Jyoti
310 | 175/2 | DA+0 | Wet | 881091 | 63.346 |  | 2025-05-18 | Completed. | Completed. | 2025-05-22 |  | Himanshi Construction
311 | 166/0 | DD60+6 | FS |  |  |  | 2025-08-17 | Completed. | Completed. | 2025-10-03 | Earthing & Backfilling U/P | Kashtabhanjan
312 | 165/4 | DD45+9 ( 4.5m RC) | PS |  |  |  | 2025-09-25 | Pit B PCC and Pit C frustum casting completed | Pit C Excavation Done Pit B Excavation U/P |  | Pit C Dewatering U/P & Gang Shifting U/P from 166/0. | Kashtabhanjan | 29
38482.842

## Erection Compiled
Sl. No. | Location No. | Type | Type of Tower | Starting Date | Revenue | Tower Weight | Status | Completion Date | Gang Name | Final Checking | Tack Welding
1 | 101/0 | DD60 | DD60+35 |  |  | 171.017 | Completed | 2025-09-19 | Dhaneshwar
2 | 104/0 | DD60 | DD60+35 |  |  | 172.151 | Completed | 2025-08-13 | Dhaneshwar
3 | 105/0 | DD60 | DD60+35 | 2025-05-24 |  | 172.151 | Completed | 2025-09-23 | Rupesh
4 | 106/0 | DD60 | DD60+9 | 2024-10-03 | 753337 | 98.836 | Completed | 2024-12-08 | DK Verma
5 | 106A/0 | DC | DC2+0 | 2024-12-29 | 470077 | 64.254 | Completed | 2025-01-03 | DK Verma
6 | 106A/1 | DA | DA+6 | 2024-12-22 | 342192 | 44.728 | Completed | 2024-12-28 | DK Verma
7 | 106A/2 | DA | DA-3 | 2024-12-19 | 273608.93 | 36.045 | Completed | 2024-12-28 | Barkat Ali
8 | 106A/3 | DA | DA+3 | 2024-06-25 | 297143 | 39.459 | Completed | 2024-07-02 | Gourishankar
9 | 106A/4 | DA | DA+9 | 2024-06-14 | 357181 | 46.623 | Completed | 2024-06-24 | Gourishankar
10 | 106B/0 | DB | DB2+9 | 2024-08-08 | 503365 | 65.757 | Completed | 2024-08-24 | Rahul Kumar
11 | 106B/1 | DA | DA+9 | 2024-07-28 | 357181 | 46.263 | Completed | 2024-08-08 | Ajay Kumar
12 | 106B/2 | DA | DA+6 | 2024-07-02 | 342192 | 44.728 | Completed | 2024-07-12 | Gourishankar
13 | 107/0 | DD45 | DD45+0 | 2024-07-13 | 546238 | 72.238 | Completed | 2024-07-29 | Gourishankar
14 | 107/1 | DA | DA-3 | 2024-09-16 | 273608.93 | 36.045 | Completed | 2024-09-26 | Barkat Ali
15 | 108/0 | DD45 | DD45+0 | 2024-09-28 | 546238 | 72.238 | Completed | 2024-10-13 | DK Verma
16 | 109/0 | DB | DB2+0 | 2024-08-11 | 403998 | 54.418 | Completed | 2024-08-23 | Gourishankar
17 | 110/0 | DB | DB2+0 | 2024-08-18 | 403998 | 54.418 | Completed | 2024-08-31 | Rahul Kumar
18 | 111/0 | DC | DC1+0 | 2024-09-09 | 470077 | 64.254 | Completed | 2024-09-21 | Rahul Kumar
19 | 112/0 | DD45 | DD45+0 | 2024-06-05 | 546238 | 72.238 | Completed | 2024-06-13 | Gourishankar
20 | 113/0 | DD60 | DD60+0 | 2024-07-08 | 604881 | 80.408 | Completed | 2024-07-25 | Ajay Kumar
21 | 114/0 | DD45 | DD45+0 | 2024-09-02 | 546238 | 72.238 | Completed | 2024-09-13 | Gourishankar
22 | 115/0 | DC | DC2+25 | 2024-12-04 |  | 109.608 | Completed | 2024-12-20 | Gourishankar
23 | 116/0 | DD45 | DD45+18 | 2024-09-10 | 906755 | 112.424 | Completed | 2024-09-27 | Dhaneswar Mahto
24 | 116A/0 | DC | DC1+0 | 2024-07-30 | 470077 | 64.254 | Completed | 2024-08-11 | Gourishankar
25 | 116A/1 | DA | DA+0 | 2024-12-09 | 286911 | 37.73 | Completed | 2024-12-21 | DK Verma
26 | 116B/0 | DD45 | DD45+6 | 2024-10-13 | 650023 | 85.234 | Completed | 2024-10-31 | Ajay Kumar
27 | 117/0 | DD60 | DD60+3 | 2024-11-20 | 635073 | 84.299 | Completed | 2024-12-03 | Gourishankar
28 | 118/0 | DD45 | DD45+0 | 2024-08-01 | 546238 | 72.238 | Completed | 2024-08-20 | Rahul Kumar
29 | 119/0 | DD45 | DD45+0 | 2024-09-12 | 546238 | 72.238 | Completed | 2024-09-24 | Ajay Kumar
30 | 119/1 | DA | DA-3 | 2024-09-14 | 273608.93 | 36.045 | Completed | 2024-09-23 | Gourishankar
31 | 119/2 | DA | DA+0 | 2024-07-08 | 286911 | 37.73 | Completed | 2024-07-12 | Rahul Kumar
32 | 119/3 | DA | DA+0 | 2024-07-13 | 286911 | 37.73 | Completed | 2024-07-18 | Rahul Kumar
33 | 120/0 | DD60 | DD60+9 | 2024-10-01 | 753337 | 98.836 | Completed | 2024-10-24 | Gourishankar
34 | 121/0 | DD60 | DD60+18 | 2024-09-23 | 1003256 | 129.341 | Completed | 2024-10-10 | Rahul Kumar
35 | 122/0 | DC | DC1+6 | 2024-10-04 | 559332 | 74.632 | Completed | 2024-10-15 | Gourishankar
36 | 123/0 | DD60 | DD60+6 | 2024-09-26 | 719574 | 94.408 | Completed | 2024-10-10 | Ajay Kumar
37 | 123/1 | DA | DA+3 | 2024-10-17 | 297143 | 39.459 | Completed | 2024-10-31 | Gourishankar
38 | 124/0 | DC | DC1+3 | 2024-10-28 | 493565 | 66.268 | Completed | 2024-11-11 | Ajay Kumar
39 | 124A/0 | DD60 | DD60+0 | 2024-12-21 | 604881 | 80.408 | Completed | 2025-01-05 | Gourishankar
40 | 124A/1 | DA | DA+3 | 2024-09-16 | 297143 | 39.459 | Completed | 2024-09-30 | Senahul
41 | 125/0 | DD60 | DD60+0 | 2024-12-22 | 604881 | 80.408 | Completed | 2025-01-05 | MJR
42 | 125A/0 | DB | DB2+3 | 2024-11-02 | 424198 | 56.863 | Completed | 2024-11-13 | Gourishankar
43 | 126/0 | DC | DC2+0 | 2024-07-20 | 470077 | 64.254 | Completed | 2024-07-31 | Rahul Kumar
44 | 126/1 | DA | DA+6 | 2024-12-21 | 342192 | 44.728 | Completed | 2024-12-27 | Gourishankar
45 | 127/0 | DD45 | DD45+0 | 2024-05-31 | 546238 | 72.238 | Completed | 2024-06-10 | Lalan Mahto
46 | 127/1 | DA | DA+0 | 2023-09-30 | 286911 | 37.73 | Completed | 2023-10-15 | Ghanshyam Mahto
47 | 127/2 | DA | DA+0 | 2023-10-16 | 286911 | 37.73 | Completed | 2023-10-29 | Ghanshyam Mahto
48 | 127/3 | DA | DA+0 | 2024-05-25 | 286911 | 37.73 | Completed | 2024-05-31 | Lalan Mahto
49 | 127/4 | DA | DA+3 | 2024-05-19 | 297143 | 39.459 | Completed | 2024-05-24 | Lalan Mahto
50 | 127/5 | DA | DA+3 | 2024-11-27 | 297143 | 39.459 | Completed | 2024-12-07 | Ajay Kumar
51 | 128/0 | DD60 | DD60+6 | 2024-11-13 | 719574 | 94.408 | Completed | 2024-11-26 | Ajay Kumar
52 | 129/0 | DD60 | DD60+6 | 2024-12-30 | 719574 | 94.408 | Completed | 2025-01-18 | Barkat Ali
53 | 129A/0 | DC | DC1+0 | 2024-04-25 | 470077 | 64.254 | Completed | 2024-04-30 | Lalan Mahto
54 | 129A/1 | DA | DA+0 | 2024-05-02 | 286911 | 37.73 | Completed | 2024-05-07 | Lalan Mahto
55 | 129A/2 | DA | DA+3 | 2024-05-07 | 297143 | 39.459 | Completed | 2024-05-12 | Lalan Mahto
56 | 130/0 | DB | DB1+0 | 2024-05-07 | 403998 | 54.418 | Completed | 2024-05-18 | Lalan Mahto
57 | 130/1 | DA | DA+0 | 2025-01-25 | 286911 | 37.73 | Completed | 2025-02-09 | SK Samuil
58 | 130/2 | DA | DA+3 | 2025-01-20 | 297143 | 39.459 | Completed | 2025-01-29 | MJR
59 | 130/3 | DA | DA+0 | 2025-01-09 | 286911 | 37.73 | Completed | 2025-01-18 | MJR
60 | 130/4 | DA | DA+3 | 2024-12-22 | 297143 | 39.459 | Completed | 2025-01-21 | SK Samuil
61 | 131/0 | DD45 | DD45+3 | 2025-01-21 | 573550 | 75.452 | Completed | 2025-02-05 | Barkat Ali
62 | 132/0 | DC | DC2+3 | 2024-12-08 |  | 66.268 | Completed | 2024-12-21 | SK Samuil
63 | 132/1 | DA | DA+0 | 2024-12-22 | 286911 | 37.73 | Completed | 2024-12-30 | SK Samuil
64 | 132/2 | DA | DA+0 | 2024-02-04 | 286911 | 37.73 | Completed | 2024-02-13 | Lalan Mahto
65 | 132/3 | DA | DA+0 | 2024-06-12 | 286911 | 37.73 | Completed | 2024-06-18 | Lalan Mahto
66 | 133/0 | DB | DB1+0 | 2024-02-13 | 403998 | 54.418 | Completed | 2024-02-21 | Lalan Mahto
67 | 133/1 | DA | DA+0 | 2023-12-02 | 286911 | 37.73 | Completed | 2023-12-15 | Ghanshyam Mahto
68 | 133/2 | DA | DA+0 | 2024-02-27 | 286911 | 37.73 | Completed | 2024-03-03 | Lalan Mahto
69 | 133/3 | DA | DA+0 | 2024-02-20 | 286911 | 37.73 | Completed | 2024-02-28 | Lalan Mahto
70 | 133/4 | DA | DA+0 | 2024-04-20 | 286911 | 37.73 | Completed | 2024-04-24 | Lalan Mahto
71 | 133/5 | DA | DA+0 | 2024-03-03 | 286911 | 37.73 | Completed | 2024-03-08 | Lalan Mahto
72 | 133A/0 | DB | DB1+0 | 2024-03-08 | 403998 | 54.418 | Completed | 2024-03-13 | Lalan Mahto
73 | 133A/1 | DA | DA+0 | 2024-03-13 | 286911 | 37.73 | Completed | 2024-03-13 | Lalan Mahto
74 | 133A/2 | DA | DA+6 | 2024-04-13 | 342192 | 44.728 | Completed | 2024-04-19 | Lalan Mahto
75 | 133A/3 | DA | DA+0 | 2024-02-15 | 286911 | 37.73 | Completed | 2024-02-20 | Poonam Kumari
76 | 133A/4 | DA | DA+6 | 2024-09-27 | 342192 | 44.728 | Completed | 2024-10-12 | Mithun Kumar
77 | 134/0 | DC | DC2+25 | 2024-12-04 |  | 109.608 | Completed | 2024-12-20 | Dhaneswar Mahto
78 | 135/0 | DC | DC2+25 | 2025-01-09 |  | 109.628 | Completed | 2025-01-22 | DK Verma
79 | 135/1 | DA | DA+6 | 2025-01-06 | 342192 | 44.728 | Completed | 2025-01-11 | Surender Mahto
80 | 135/2 | DA | DA+0 | 2023-11-11 | 286911 | 37.73 | Completed | 2023-11-17 | Ghanshyam Mahto
81 | 135/3 | DA | DA+0 | 2024-02-26 | 286911 | 37.73 | Completed | 2024-03-02 | Poonam Kumari
82 | 135/4 | DA | DA+0 | 2024-05-31 | 286911 | 37.73 | Completed | 2024-06-10 | Intizer Infratech
83 | 135/5 | DA | DA+0 | 2024-05-19 | 286911 | 37.73 | Completed | 2024-05-31 | Intizer Infratech
84 | 135/6 | DA | DA+0 | 2024-05-01 | 286911 | 37.73 | Completed | 2024-05-19 | Intizer Infratech
85 | 135/7 | DA | DA+0 | 2025-04-13 | 286911 | 37.73 | Completed | 2025-04-22 | SK Samuil
86 | 135A/0 | DC | DC1+0 | 2024-12-27 | 470077 | 64.254 | Completed | 2025-01-04 | Dhaneswar Mahto
87 | 135A/1 | DD45 | DD45+3 | 2024-10-08 | 573550 | 75.452 | Completed | 2024-11-03 | Dhaneswar Mahto
88 | 135A/2 | DB | DB2+9 | 2024-11-05 | 503365 | 65.757 | Completed | 2024-11-13 | Dhaneswar Mahto
89 | 135A/3 | DA | DA+0 | 2024-01-23 | 286911 | 37.73 | Completed | 2024-01-28 | Poonam Kumari
90 | 135A/4 | DA | DA+0 | 2023-11-01 | 286911 | 37.73 | Completed | 2023-11-09 | Ghanshyam Mahto
91 | 135A/5 | DA | DA+0 | 2025-01-13 | 286911 | 37.73 | Completed | 2025-01-18 | Dhaneswar Mahto
92 | 135A/6 | DA | DA+0 | 2024-12-21 | 286911 | 37.73 | Completed | 2024-12-26 | Dhaneswar Mahto
93 | 135A/7 | DA | DA+0 | 2023-11-19 | 286911 | 37.73 | Completed | 2023-12-01 | Ghanshyam Mahto
94 | 135B/0 | DB | DB1+0 | 2024-02-02 | 403998 | 54.418 | Completed | 2024-02-09 | Poonam Kumari
95 | 135B/1 | DA | DA+0 | 2024-02-20 | 286911 | 37.73 | Completed | 2024-02-26 | Poonam Kumari
96 | 135B/2 | DA | DA+0 | 2024-01-18 | 286911 | 37.73 | Completed | 2024-01-23 | Poonam Kumari
97 | 135B/3 | DA | DA+0 | 2024-01-12 | 286911 | 37.73 | Completed | 2024-01-18 | Poonam Kumari
98 | 135B/4 | DA | DA+6 | 2024-01-04 | 342192 | 44.728 | Completed | 2024-01-12 | Poonam Kumari
99 | 135B/5 | DA | DA+0 | 2024-01-28 | 286911 | 37.73 | Completed | 2024-02-02 | Poonam Kumari
100 | 135B/6 | DA | DA+0 | 2024-02-04 | 286911 | 37.73 | Completed | 2024-02-15 | Poonam Kumari
101 | 135B/7 | DA | DA+3 | 2024-03-02 | 297143 | 39.459 | Completed | 2024-04-11 | Poonam Kumari
102 | 136/0 | DD45 | DD45+18 | 2025-01-09 | 906755 | 112.424 | Completed | 2025-01-25 | Gourishankar
103 | 137/0 | DC | DC2+9 | 2025-02-01 | 585620 | 77.718 | Completed | 2025-02-15 | MJR
104 | 137/1 | DA | DA+3 | 2024-05-25 | 297143 | 39.459 | Completed | 2024-05-31 | Rahul Kumar
105 | 137/2 | DA | DA+0 | 2025-02-18 | 286911 | 37.73 | Completed | 2025-02-27 | MJR
106 | 137/3 | DA | DA+0 | 2024-05-19 | 286911 | 37.73 | Completed | 2024-05-24 | Rahul Kumar
107 | 137/4 | DA | DA+0 | 2024-05-07 | 286911 | 37.73 | Completed | 2024-05-18 | Rahul Kumar
108 | 137/5 | DA | DA+3 | 2025-02-03 | 297143 | 39.459 | Completed | 2025-02-07 | Dhaneswar Mahto
109 | 137/6 | DA | DA+0 | 2025-01-27 | 286911 | 37.73 | Completed | 2025-02-07 | SK Samuil
110 | 137A/0 | DB | DB1+0 | 2025-01-23 | 403998 | 54.418 | Completed | 2025-01-29 | DK Verma
111 | 137A/1 | DA | DA+6 | 2025-01-27 | 342192 | 44.728 | Completed | 2025-01-29 | Dhaneswar Mahto
112 | 137A/2 | DA | DA+0 | 2025-01-30 | 286911 | 37.73 | Completed | 2025-02-02 | Dhaneswar Mahto
113 | 137A/3 | DA | DA+6 | 2024-11-20 | 342192 | 44.728 | Completed | 2024-11-28 | Dhaneswar Mahto
114 | 137A/4 | DA | DA-3 | 2024-11-29 | 273608.93 | 36.045 | Completed | 2024-12-03 | Dhaneswar Mahto
115 | 137A/5 | DA | DA-3 | 2024-11-14 | 273608.93 | 36.045 | Completed | 2024-11-20 | Dhaneswar Mahto
116 | 137A/6 | DA | DA+9 | 2025-01-20 | 357181 | 46.623 | Completed | 2025-01-24 | Dhaneswar Mahto
117 | 138/0 | DB | DB2+0 | 2025-01-27 | 403998 | 54.418 | Completed | 2025-02-01 | Gourishankar
118 | 138/1 | DA | DA+6 | 2025-02-03 | 342192 | 44.728 | Completed | 2025-02-09 | Gourishankar
119 | 138/2 | DA | DA+0 | 2025-02-05 | 286911 | 37.73 | Completed | 2025-02-11 | DK Verma
120 | 139/0 | DB | DB2+0 | 2025-01-30 | 403998 | 54.418 | Completed | 2025-02-04 | DK Verma
121 | 139/1 | DA | DA+3 | 2025-02-12 | 297143 | 39.459 | Completed | 2025-02-17 | DK Verma
122 | 139/2 | DA | DA+0 | 2025-02-10 | 286911 | 37.73 | Completed | 2025-02-14 | Gourishankar
123 | 139A/0 | DB | DB2+9 | 2025-02-09 | 503365 | 65.757 | Completed | 2025-02-14 | Dhaneswar Mahto
124 | 140/0 | DD60 | DD60+0 | 2025-02-16 | 604881 | 80.408 | Completed | 2025-02-22 | Dhaneswar Mahto
125 | 141/0 | DD60 | DD60+3 | 2025-02-16 | 635073 | 84.299 | Completed | 2025-02-23 | Gourishankar
126 | 141/1 | DA | DA+0 | 2025-02-11 | 286911 | 37.73 | Completed | 2025-02-17 | SK Samuil
127 | 141/2 | DA | DA-3 | 2025-02-13 | 273608.93 | 36.045 | Completed | 2025-02-19 | SK Samuil
128 | 141/3 | DA | DA+3 | 2025-02-19 | 297143 | 39.459 | Completed | 2025-02-25 | SK Samuil
129 | 142/0 | DD60 | DD60+0 | 2025-02-18 | 604881 | 80.408 | Completed | 2025-03-03 | DK Verma
130 | 143/0 | DD60 | DD60+3 | 2025-02-25 | 635073 | 84.299 | Completed | 2025-03-04 | Gourishankar
131 | 143A/0 | DD45 | DD45+0 | 2025-02-24 | 546238 | 72.238 | Completed | 2025-03-02 | Dhaneswar Mahto
132 | 143A/1 | DA | DA+6 | 2025-03-01 | 342192 | 44.728 | Completed | 2025-03-09 | SK Samuil
133 | 143A/2 | DD45 | DD45+0 | 2025-03-04 | 546238 | 72.238 | Completed | 2025-03-17 | Dhaneswar Mahto
134 | 143A/3 | DD45 | DD45+3 | 2025-03-05 | 573550 | 75.452 | Completed | 2025-03-11 | Gourishankar
135 | 143A/4 | DA | DA+0 | 2025-03-02 | 286911 | 37.73 | Completed | 2025-03-10 | MJR
136 | 143A/5 | DA | DA+3 | 2025-03-05 | 297143 | 39.459 | Completed | 2025-03-10 | DK Verma
137 | 144/0 | DB | DB2+3 | 2024-10-15 | 424198 | 56.863 | Completed | 2024-11-16 | Mukesh
138 | 144/1 | DA | DA+0 | 2024-06-30 | 286911 | 37.73 | Completed | 2024-07-05 | Rahul Kumar
139 | 144/2 | DA | DA+0 | 2024-06-11 | 286911 | 37.73 | Completed | 2024-06-15 | Rahul Kumar
140 | 144/3 | DA | DA+0 | 2024-06-13 | 286911 | 37.73 | Completed | 2024-06-15 | Rahul Kumar
141 | 144/4 | DA | DA+0 | 2024-06-16 | 286911 | 37.73 | Completed | 2024-06-20 | Rahul Kumar
142 | 144/5 | DA | DA+0 | 2024-06-21 | 286911 | 37.73 | Completed | 2024-06-26 | Rahul Kumar
143 | 144A/0 | DB | DB1+9 | 2024-11-18 | 503365 | 65.757 | Completed | 2024-11-24 | Mukesh
144 | 145/0 | DB | DB1+18 | 2024-11-18 | 670636 | 82.239 | Completed | 2024-12-08 | Mukesh
145 | 145A/0 | DB | DB1+6 | 2025-03-15 | 480757 | 63.509 | Completed | 2025-03-28 | MJR
146 | 145A/1 | DA | DA+3 | 2025-02-22 | 297143 | 39.459 | Completed | 2025-03-07 | Sulen sarkar
147 | 145A/2 | DA | DA+3 | 2025-03-19 | 297143 | 39.459 | Completed | 2025-03-27 | Sulen sarkar
148 | 145A/3 | DA | DA+0 | 2025-03-08 | 286911 | 37.73 | Completed | 2025-03-16 | Sulen sarkar
149 | 146/0 | DC | DC1+9 | 2025-03-12 | 585620 | 77.718 | Completed | 2025-03-22 | DK Verma
150 | 147/0 | DC | DC2+9 | 2025-03-24 | 585620 | 77.718 | Completed | 2025-04-01 | DK Verma
151 | 147/1 | DC | DC2+0 | 2024-12-09 | 470077 | 64.254 | Completed | 2024-12-16 | Mukesh
152 | 147/2 | DC | DC1+0 | 2024-12-17 | 470077 | 64.254 | Completed | 2024-12-23 | Mukesh
153 | 147/3 | DA | DA-3 | 2024-11-13 | 273608.93 | 36.045 | Completed | 2024-12-02 | Modina India
154 | 147/4 | DA | DA+3 | 2024-12-10 | 297143 | 39.459 | Completed | 2024-12-25 | Modina India
155 | 147/5 | DA | DA+6 | 2024-12-03 | 342192 | 44.728 | Completed | 2024-12-22 | Modina India
156 | 147/6 | DA | DA-3 | 2025-01-27 | 273608.93 | 36.045 | Completed | 2025-02-18 | Ajay Kumar
157 | 147A/0 | DB | DB1+18 | 2024-12-24 | 670636 | 82.239 | Completed | 2025-01-03 | Mukesh
158 | 147B/0 | DB | DB1+18 | 2025-02-26 | 670636 | 82.239 | Completed | 2025-03-22 | Modina India
159 | 147B/1 | DA | DA+0 | 2025-02-13 | 286911 | 37.73 | Completed | 2025-02-21 | Modina India
160 | 148/0 | DC | DC2+0 | 2025-01-04 | 470077 | 64.254 | Completed | 2025-01-10 | Mukesh
161 | 148/1 | DA | DA+3 | 2025-02-01 | 297143 | 39.459 | Completed | 2025-02-09 | Modina India
162 | 148/2 | DA | DA+0 | 2025-01-21 | 286911 | 37.73 | Completed | 2025-01-30 | Modina India
163 | 148/3 | DA | DA+0 | 2025-01-10 | 286911 | 37.73 | Completed | 2025-01-19 | Modina India
164 | 148/4 | DA | DA+0 | 2024-12-23 | 286911 | 37.73 | Completed | 2025-01-06 | Modina India
165 | 148/5 | DA | DA+0 | 2025-02-25 | 286911 | 37.73 | Completed | 2025-02-28 | SK Samuil
166 | 148/6 | DA | DA+0 | 2025-03-03 | 286911 | 37.73 | Completed | 2025-03-09 | SK Samuil
167 | 148/7 | DA | DA+0 | 2025-03-08 | 286911 | 37.73 | Completed | 2025-03-20 | Rahim Khan
168 | 149/0 | DB | DB2+0 | 2025-03-10 | 403998 | 54.418 | Completed | 2025-04-06 | SK Samuil
169 | 149/1 | DA | DA+0 | 2025-03-17 | 286911 | 37.73 | Completed | 2025-03-27 | SK Samuil
170 | 150/0 | DD60 | DD60+9 | 2025-03-22 | 753337 | 98.836 | Completed | 2025-03-31 | Dhaneswar Mahto
171 | 150/1 | DA | DA+9 | 2025-03-20 | 357181 | 46.623 | Completed | 2025-04-06 | MJR
172 | 150/2 | DA | DA+3 | 2025-03-18 | 297143 | 39.459 | Completed | 2025-03-22 | SK Samuil
173 | 150/3 | DA | DA+6 | 2025-03-19 | 342192 | 44.728 | Completed | 2025-04-01 | Rupesh
174 | 150A/0 | DC | DC1+0 | 2025-03-25 | 470077 | 64.254 | Completed | 2025-04-11 | Rahim Khan
175 | 150A/1 | DA | DA+3 | 2024-11-10 | 297143 | 39.459 | Completed | 2024-11-22 | SK Samuil
176 | 150A/2 | DA | DA+0 | 2024-11-23 | 286911 | 37.73 | Completed | 2024-12-02 | SK Samuil
177 | 151/0 | DB | DB2+3 | 2025-03-21 | 424198 | 56.863 | Completed | 2025-03-27 | Gourishankar
178 | 152/0 | DC | DC2+0 | 2024-10-15 | 470077 | 64.254 | Completed | 2024-10-24 | Mukesh
179 | 152/1 | DA | DA+0 | 2024-09-16 | 286911 | 37.73 | Completed | 2024-10-12 | Rejaul
180 | 152/2 | DA | DA-3 | 2024-09-24 | 273608.93 | 36.045 | Completed | 2024-11-07 | SK Samuil
181 | 152/3 | DA | DA-3 | 2024-10-25 | 273608.93 | 36.045 | Completed | 2024-10-31 | Mukesh
182 | 152/4 | DA | DA+0 | 2024-11-02 | 286911 | 37.73 | Completed | 2024-11-07 | Mukesh
183 | 152A/0 | DB | DB1+0 | 2025-03-16 | 403998 | 54.418 | Completed | 2025-03-20 | Gourishankar
184 | 153/0 | DD60 | DD60+25 |  |  | 141.874 | Completed | 2025-08-08
185 | 155/0 | DD60 | DD60+0 | 2025-04-02 | 604881 | 80.408 | Completed | 2025-04-11 | Rahul Kumar
186 | 155/1 | DA | DA+0 | 2025-03-26 | 286911 | 37.73 | Completed | 2025-04-03 | Barkat Ali
187 | 155/2 | DA | DA+3 | 2024-11-16 | 297143 | 39.459 | Completed | 2024-11-30 | Rahul Kumar
188 | 155/3 | DA | DA+3 | 2024-11-16 | 297143 | 39.459 | Completed | 2024-11-22 | Rahul Kumar
189 | 155/4 | DA | DA+0 | 2025-04-28 | 286911 | 37.73 | Completed | 2025-05-11 | SK Samuil
190 | 155/5 | DA | DA+0 | 2025-04-29 | 286911 | 37.73 | Completed | 2025-05-11 | Barkat Ali
191 | 155/6 | DA | DA-3 | 2025-03-15 | 273608.93 | 36.045 | Completed | 2025-03-23 | Barkat Ali
192 | 156/0 | DD60 | DD60+3 | 2025-03-22 | 635073 | 84.299 | Completed | 2025-03-28 | Rahul Kumar
193 | 157/0 | DD60 | DD60+6 | 2025-03-12 | 719574 | 94.408 | Completed | 2025-03-27 | Rahim Khan
194 | 157/1 | DA | DA+0 | 2025-02-09 | 286911 | 37.73 | Completed | 2025-02-18 | Sukhriddin
195 | 157/2 | DA | DA+0 | 2025-02-23 | 286911 | 37.73 | Completed | 2025-03-11 | Barkat Ali
196 | 158/0 | DB | DB2+0 | 2025-04-02 | 403998 | 54.418 | Completed | 2025-04-10 | Rahim Khan
197 | 158/1 | DA | DA-3 | 2025-04-07 | 273608.93 | 36.045 | Completed | 2025-04-25 | Barkat Ali
198 | 158/2 | DA | DA-3 | 2025-03-13 | 273608.93 | 36.045 | Completed | 2025-03-18 | Rahul Kumar
199 | 158A/0 | DD45 | DD45+6 | 2024-10-23 | 650023 | 85.234 | Completed | 2024-11-12 | Rahul Kumar
200 | 158B/0 | DD45 | DD45+18 | 2024-11-13 | 906755 | 112.424 | Completed | 2024-12-30 | Rahul Kumar
201 | 158B/1 | DA | DA+3 | 2024-11-16 | 297143 | 39.459 | Completed | 2024-12-12 | Rahul Kumar
202 | 158B/2 | DA | DA+3 | 2024-12-31 | 297143 | 39.459 | Completed | 2025-01-10 | Rahul Kumar
203 | 159/0 | DB | DB+0 | 2024-08-14 | 403998 | 54.418 | Completed | 2024-09-08 | Sukhriddin
204 | 159/1 | DA | DA+0 | 2025-01-21 | 286911 | 37.73 | Completed | 2025-02-12 | Rahim Khan
205 | 159/3 | DA | DA+0 | 2024-07-08 | 286911 | 37.73 | Completed | 2024-07-23 | Sukhriddin
206 | 159/4 | DA | DA+0 | 2025-01-21 | 286911 | 37.73 | Completed | 2025-02-03 | Modina India
207 | 161/0 | DD60 | DD60+25 | 2025-01-28 | 1099828 | 141.874 | Completed | 2025-02-16 | Rahul Kumar
208 | 162/0 | DD60 | DD60+25 | 2025-02-20 | 1099828 | 141.874 | Completed | 2025-03-09 | Rahul Kumar
209 | 163/0 | DC | DC2+0 | 2025-01-16 | 470077 | 64.254 | Completed | 2025-01-23 | Rahul Kumar
210 | 163/1 | DA | DA+0 | 2024-12-30 | 286911 | 37.73 | Completed | 2025-01-08 | Rahim Khan
211 | 163/2 | DA | DA+0 | 2024-11-28 | 286911 | 37.73 | Completed | 2024-12-29 | Rahim Khan
212 | 163/3 | DA | DA+0 | 2024-11-28 | 286911 | 37.73 | Completed | 2024-12-18 | Rahim Khan
213 | 163/4 | DA | DA+0 | 2025-01-16 | 286911 | 37.73 | Completed | 2025-01-29 | Sukhriddin
214 | 163/5 | DA | DA+0 | 2025-01-12 | 286911 | 37.73 | Completed | 2025-02-20 | Barkat Ali
215 | 163/6 | DA | DA+0 | 2025-01-10 | 286911 | 37.73 | Completed | 2025-01-25 | Barkat Ali
216 | 164/0 | DB | DB2+0 | 2024-12-28 | 403998 | 54.418 | Completed | 2025-01-12 | Sukhriddin
217 | 164/1 | DA | DA+0 | 2024-12-28 | 286911 | 37.73 | Completed | 2025-01-16 | Modina India
218 | 164/2 | DA | DA+0 | 2024-07-27 | 286911 | 37.73 | Completed | 2024-08-13 | Sukhriddin
219 | 164/3 | DA | DA+0 | 2025-01-11 | 286911 | 37.73 | Completed | 2025-01-20 | Rahim Khan
220 | 164/4 | DA | DA+0 | 2024-11-16 | 286911 | 37.73 | Completed | 2024-11-27 | Sukhriddin
221 | 164/5 | DA | DA+0 | 2024-11-28 | 286911 | 37.73 | Completed | 2024-12-14 | Sukhriddin
222 | 164/6 | DA | DA+0 | 2024-12-14 | 286911 | 37.73 | Completed | 2024-12-25 | Sukhriddin
223 | 164/7 | DA | DA+0 | 2024-09-22 | 286911 | 37.73 | Completed | 2024-10-09 | Sukhriddin
224 | 165/0 | DB | DB2+0 | 2024-10-09 | 403998 | 54.418 | Completed | 2024-10-28 | Sukhriddin
225 | 165/1 | DA | DA+0 | 2025-05-16 | 286911 | 37.73 | Completed | 2025-05-25 | Barkat Ali
226 | 165/2 | DA | DA+0 | 2024-09-09 | 286911 | 37.73 | Completed | 2024-09-20 | Sukhriddin
227 | 165/3 | DA | DA+6 | 2024-10-30 | 342192 | 44.728 | Completed | 2024-11-15 | Sukhriddin
228 | 167/0 | DD60 | DD60+0 | 2025-04-18 | 604881 | 80.408 | Completed | 2025-05-05 | Rupesh
229 | 167/1 | DA | DA+9 | 2025-05-04 | 357181 | 46.623 | Completed | 2025-05-19 | Barkat Ali
230 | 167/2 | DA | DA+6 | 2025-04-08 | 342192 | 44.728 | Completed | 2025-04-18 | Barkat Ali
231 | 167/3 | DA | DA+6 | 2025-03-28 | 342192 | 44.728 | Completed | 2025-04-06 | Barkat Ali
232 | 167/4 | DA | DA+0 | 2025-04-20 | 286911 | 37.73 | Completed | 2025-04-29 | Barkat Ali
233 | 168/0 | DC | DC1+0 | 2025-04-06 | 470077 | 64.254 | Completed | 2025-04-16 | Rupesh
234 | 168/1 | DA | DA-3 | 2025-05-13 | 273608.93 | 36.045 | Completed | 2025-05-20 | Rahim Khan
235 | 168/2 | DA | DA+0 | 2025-05-02 | 286911 | 37.73 | Completed | 2025-05-11 | Sukhriddin
236 | 169/0 | DD45 | DD45+18 | 2025-05-24 | 906755 | 112.424 | Completed | 2025-06-08 | DK Verma
237 | 171/0 | DD60 | DD60+25(3M RC) | 2025-02-26 | 1099828 | 141.874 | Completed | 2025-03-29 | Sukhriddin
238 | 172/0 | DD60 | DD60+25 | 2025-04-02 | 1099828 | 141.874 | Completed | 2025-04-28 | Sukhriddin
239 | 172/2 | DA | DA+6 | 2025-05-29 | 342192 | 44.728 | Completed | 2025-06-06 | Thanu Mahto
240 | 174/1 | DB | DB1+0 | 2025-06-06 | 403998 | 54.418 | Completed | 2025-06-13 | Gourishankar
241 | 175/0 | DD45 | DD45+0 | 2025-05-28 | 546238 | 72.238 | Completed | 2025-06-05 | Gourishankar
242 | 175/2 | DA | DA+0 |  |  | 37.73 | Completed | 2025-07-20
243 | 176/0 | DD60 | DD60+0 | 2025-06-11 | 604881 | 80.408 | Completed | 2025-07-04 | DK Verma
244 | 177/0 | DD60 | DD60+0 | 2025-05-06 | 604881 | 80.408 | Completed | 2025-05-18 | Gourishankar
245 | 178/0 | DD60 | DD60+6 | 2025-04-06 | 719574 | 94.408 | Completed | 2025-04-13 | Gourishankar
246 | 179/0 | DD60 | DD60+0 | 2025-04-16 | 604881 | 80.408 | Completed | 2025-04-22 | Gourishankar
247 | 180/0 | DD45 | DD45+9 | 2025-04-24 | 680590 | 89.146 | Completed | 2025-05-03 | Gourishankar
248 | 181/0 | DD45 | DD45+18 | 2025-04-06 | 906755 | 112.424 | Completed | 2025-04-27 | DK Verma
249 | 181/1 | DA | DA+0 | 2025-04-24 | 286911 | 37.73 | Completed | 2025-04-30 | Rahim Khan
250 | 181/2 | DA | DA+0 | 2025-04-16 | 286911 | 37.73 | Completed | 2025-04-22 | Rahim Khan
251 | 181/3 | DA | DA+0 | 2025-05-19 | 286911 | 37.73 | Completed | 2025-05-24 | Gourishankar
252 | 181/4 | DA | DA+0 | 2025-05-03 | 286911 | 37.73 | Completed | 2025-05-11 | Rahim Khan
253 | 182/0 | DD60 | DD60+0 | 2025-04-28 | 604881 | 80.408 | Completed | 2025-05-06 | DK Verma
254 | 187/1 | DA | DA+3 | 2025-04-03 | 297143 | 39.459 | Completed | 2025-04-12 | Thanu mahto
255 | 187/2 | DA | DA-3 | 2024-12-26 | 273608.93 | 36.045 | Completed | 2025-01-04 | Mithun Kumar
256 | 187/3 | DA | DA+0 | 2024-11-22 | 286911 | 37.73 | Completed | 2024-11-26 | Jwala
257 | 188/0 | DB | DB1+6 | 2024-11-27 | 480757 | 63.509 | Completed | 2024-12-10 | Jwala
258 | 189/0 | DB | DB2+6 | 2024-11-22 | 480757 | 63.509 | Completed | 2024-12-14 | Barkat Ali
259 | 189/1 | DA | DA+0 | 2025-04-05 | 286911 | 37.73 | Completed | 2025-04-11 | Dhaneswar Mahto
260 | 190/0 | DD45 | DD45+25 | 2025-04-18 | 994153 | 122.808 | Completed | 2025-05-06 | Dhaneswar Mahto
261 | 191/0 | DD45 | DD45+25 |  |  | 122.808 | Completed | 2025-08-26 | Modina India
262 | 191/1 | DA | DA+0 | 2024-12-09 | 286911 | 37.73 | Completed | 2024-12-23 | Mithun Kumar
263 | 191/2 | DA | DA-3 | 2025-04-23 | 273608.93 | 36.045 | Completed | 2025-04-27 | Rahul Kumar
264 | 191/3 | DA | DA-3 | 2025-04-29 | 273608.93 | 36.045 | Completed | 2025-05-04 | Rahul Kumar
265 | 191A/0 | DB | DB2+0 | 2025-04-15 | 403998 | 54.418 | Completed | 2025-04-22 | Rahul Kumar
266 | 191A/1 | DA | DA-3 | 2024-11-22 | 273608.93 | 36.045 | Completed | 2024-11-30 | Mithun Kumar
267 | 192/0 | DC | DC1+0 | 2025-04-13 | 470077 | 64.254 | Completed | 2025-04-28 | MJR
268 | 193/0 | DD60 | DD60+6 | 2024-12-11 | 719574 | 94.408 | Completed | 2024-12-21 | Jwala
269 | 194/0 | DD60 | DD60+6 | 2025-04-22 | 719574 | 94.408 | Completed | 2025-05-15 | MJR
270 | 195/0 | DC | DC2+0 | 2025-04-28 | 470077 | 64.254 | Completed | 2025-05-11 | Mithun Kumar
271 | 195/1 | DA | DA+6 | 2025-04-16 | 342192 | 44.728 | Completed | 2025-04-25 | Mithun Kumar
272 | 195/2 | DA | DA+0 | 2025-04-01 | 286911 | 37.73 | Completed | 2025-04-08 | SK Samuil
273 | 195/3 | DA | DA+6 | 2025-04-18 | 342192 | 44.728 | Completed | 2025-04-28 | SK Samuil
274 | 195/4 | DA | DA+0 | 2025-04-09 | 286911 | 37.73 | Completed | 2025-04-15 | SK Samuil
275 | 195/5 | DA | DA+6 | 2025-05-02 | 342192 | 44.728 | Completed | 2025-05-11 | SK Samuil
276 | 195A/0 | DB | DB1+0 | 2025-04-22 | 403998 | 54.418 | Completed | 2025-05-18 | Daulat Mahto
277 | 195A/1 | DA | DA+6 | 2025-04-24 | 342192 | 44.728 | Completed | 2025-05-09 | Modina India
278 | 195A/2 | DA | DA+6 | 2025-04-11 | 342192 | 44.728 | Completed | 2025-04-22 | Modina India
279 | 195A/3 | DA | DA+0 | 2025-03-30 | 286911 | 37.73 | Completed | 2025-04-08 | Modina India
280 | 196/0 | DD60 | DD60+9 | 2024-12-31 | 753337 | 98.839 | Completed | 2025-01-10 | Jwala
281 | 197/0 | DD60 | DD60+9 | 2025-01-12 | 753337 | 98.836 | Completed | 2025-01-22 | Jwala
282 | 197/1 | DA | DA+0 | 2025-04-01 | 286911 | 37.73 | Completed | 2025-04-12 | Mithun Kumar
283 | 197/2 | DA | DA+0 | 2025-01-29 | 286911 | 37.73 | Completed | 2025-02-07 | Mithun Kumar
284 | 197/3 | DA | DA+0 | 2025-01-07 | 286911 | 37.73 | Completed | 2025-01-16 | Mithun Kumar
285 | 197/4 | DA | DA+0 | 2024-12-23 | 286911 | 37.73 | Completed | 2024-12-29 | Jwala
286 | 198/0 | DC | DC1+0 | 2025-04-01 | 470077 | 64.254 | Completed | 2025-04-15 | Mithun Kumar
287 | 198/1 | DA | DA+0 | 2025-01-17 | 286911 | 37.73 | Completed | 2025-01-27 | Mithun Kumar
288 | 198/2 | DA | DA+0 | 2025-04-04 | 286911 | 37.73 | Completed | 2025-04-12 | Daulat Mahto
289 | 199/0 | DD45 | DD45+18 | 2025-04-18 | 906755 | 112.424 | Completed | 2025-05-22 | Mithun Kumar
290 | 204/0 | DD60 | DD60+9 | 2025-05-02 | 753337 | 98.836 | Completed | 2025-05-11 | Jwala
291 | 205/0 | DD60 | DD60+3 (2M RC) | 2025-04-18 | 635073 | 84.299 | Completed | 2025-04-29 | Jwala
292 | 205/1 | DA | DA-3 | 2025-04-11 | 273608.93 | 36.045 | Completed | 2025-04-16 | Jwala
293 | 205/2 | DA | DA+3 | 2025-05-15 | 297143 | 39.459 | Completed | 2025-05-21 | Jwala
294 | 209/0 | DC | DC1+0 | 2025-05-08 | 470077 | 64.254 | Completed | 2025-05-16 | Rahul Kumar
295 | 211/1 | DA | DA+0 | 2025-05-13 | 286911 | 37.73 | Completed | 2025-05-18 | Dhaneswar Mahto
296 | 217A/1 | DA | DA+3 | 2025-05-04 | 297143 | 39.459 | Completed | 2025-05-18 | Rahim Khan
297 | 242/0 | DB1 | DB1+0 | 2025-09-24 |  | 54.418 | Completed | 2025-10-05 | Sakia Khatun
298 | 246/0 | DD | DD60+0 | 2025-09-19 |  | 80.408 | Completed | 2025-10-05 | Rahul Kumar
299 | 247/1 | DA | DA+0 | 2025-05-11 | 286911 | 37.73 | Completed | 2025-05-19 | Sulen sarkar
300 | 247/4 | DA | DA+0 | 2025-05-13 |  | 37.73 | Completed | 2025-06-26 | Senahul & Modina India-3
301 | 248/0 | DC | DC2+9 | 2025-04-14 | 585620 | 77.718 | Completed | 2025-04-30 | Anarul Haque
302 | 248/1 | DA | DA+9 | 2025-05-06 | 357181 | 46.623 | Completed | 2025-05-18 | DK Verma
303 | 248/2 | DA | DA+9 | 2025-04-17 | 357181 | 46.623 | Completed | 2025-04-30 | Sulen sarkar
304 | 248/3 | DA | DA+6 | 2025-05-09 | 342192 | 44.728 | Completed | 2025-05-20 | MJR
305 | 248/4 | DA | DA+3 | 2025-04-17 | 297143 | 39.459 | Completed | 2025-05-05 | MJR
306 | 248/5 | DA | DA+0 | 2025-04-01 | 286911 | 37.73 | Completed | 2025-04-12 | Sulen sarkar
307 | 248/6 | DA | DA+0 | 2025-04-29 | 286911 | 37.73 | Completed | 2025-05-09 | Senahul
308 | 249/0 | DB | DB2+0 | 2025-02-14 | 403998 | 54.418 | Completed | 2025-02-26 | Maa Construction
309 | 249/1 | DA | DA+0 | 2025-04-13 | 286911 | 37.73 | Completed | 2025-04-21 | Sulen sarkar
310 | 249/2 | DA | DA+0 | 2025-03-01 | 286911 | 37.73 | Completed | 2025-03-09 | Maa Construction
311 | 249/3 | DA | DA+0 | 2025-03-10 | 286911 | 37.73 | Completed | 2025-03-18 | Maa Construction
312 | 250/0 | DD60 | DD60+0 | 2025-03-21 | 604881 | 80.408 | Completed | 2025-04-12 | Maa Construction
313 | 250/1 | DA | DA-3 | 2025-02-14 | 273608.93 | 36.045 | Completed | 2025-02-24 | Ghanshyam Mahto
314 | 251/0 | DB | DB1+9 | 2024-12-03 | 503365 | 65.757 | Completed | 2024-12-28 | Senahul
315 | 252/0 | DC | DC1+18 | 2025-03-18 | 780122 | 97.934 | Completed | 2025-04-11 | Anarul Haque
316 | 253/0 | DC | DC1+0 | 2025-02-01 | 470077 | 64.254 | Completed | 2025-02-17 | Senahul
317 | 254/0 | DB | DB2+0 | 2024-11-04 | 403998 | 54.418 | Completed | 2024-11-21 | Senahul
318 | 255/0 | DD60 | DD60+3 | 2024-11-27 | 635073 | 84.299 | Completed | 2024-12-21 | Senahul
319 | 255/1 | DA | DA+6 | 2025-01-19 | 342192 | 44.728 | Completed | 2025-01-27 | Daulat Mahto
320 | 255/2 | DA | DA+0 | 2025-01-03 | 286911 | 37.73 | Completed | 2025-01-10 | Maa Construction
321 | 255/3 | DA | DA+3 | 2024-12-26 | 297143 | 39.459 | Completed | 2025-01-02 | Maa Construction
322 | 255/4 | DA | DA+0 | 2024-07-10 | 286911 | 37.73 | Completed | 2024-08-22 | Ghanshyam Mahto
323 | 257/0 | DC | DC+0 | 2024-08-30 | 470077 | 64.254 | Completed | 2024-09-23 | Ghanshyam Mahto
324 | 257/1 | DA | DA+0 | 2025-01-09 | 286911 | 37.73 | Completed | 2025-01-17 | Daulat Mahto
325 | 257/2 | DA | DA-3 | 2024-09-23 | 273608.93 | 36.044 | Completed | 2024-10-24 | Ghanshyam Mahto
326 | 257/3 | DA | DA+0 | 2024-08-29 | 286911 | 37.73 | Completed | 2024-10-06 | Chahanur Bibi
327 | 257/4 | DA | DA+0 | 2024-10-29 | 286911 | 37.73 | Completed | 2024-11-16 | Thanu mahto
328 | 259/0 | DD60 | DD60+18 | 2024-11-10 | 1003256 | 129.341 | Completed | 2024-12-23 | Maa Construction
329 | 260/0 | DD60 | DD60+18 | 2024-09-11 | 1003256 | 129.341 | Completed | 2024-10-31 | Ramjivan
330 | 261/0 | DC | DC2+18 | 2024-11-23 | 780122 | 97.934 | Completed | 2024-12-28 | Ghanshyam Mahto
331 | 262/0 | DD45 | DD45+9 | 2025-01-18 | 680590 | 89.146 | Completed | 2025-02-11 | Ghanshyam Mahto
332 | 262/1 | DA | DA+0 | 2024-10-25 | 286911 | 37.73 | Completed | 2024-11-07 | Ghanshyam Mahto
333 | 263/0 | DC | DC2+0 | 2024-12-31 | 470077 | 64.254 | Completed | 2025-01-13 | Ghanshyam Mahto
334 | 264/0 | DC | DC1+6 | 2024-11-17 | 559332 | 74.632 | Completed | 2024-12-10 | Thanu Mahto
335 | 265/0 | DB | DB2+3 | 2024-09-30 | 424198 | 56.863 | Completed | 2024-10-31 | Thanu mahto
336 | 266/0 | DB | DB1+0 | 2024-12-28 | 403998 | 54.418 | Completed | 2025-01-12 | Senahul
337 | 266/1 | DB | DB1+6 | 2025-01-13 | 480757 | 63.509 | Completed | 2025-01-29 | Senahul
338 | 266/2 | DA | DA+0 | 2025-02-04 | 286911 | 37.73 | Completed | 2025-02-12 | Maa Construction
339 | 267/0 | DC | DC1+9(2M RC) | 2025-01-21 | 585620 | 77.718 | Completed | 2025-01-31 | Maa Construction
340 | 267A/0 | DC | DC2+9(2M RC) | 2025-02-21 |  | 77.718 | Completed | 2025-03-18 | Senahul
341 | 267A/1 | DA | DA+0 | 2025-02-27 | 286911 | 37.73 | Completed | 2025-03-05 | Daulat Mahto
342 | 267A/2 | DA | DA-3 | 2025-03-07 | 273608.93 | 36.045 | Completed | 2025-03-15 | Daulat Mahto
343 | 267A/3 | DA | DA+0 | 2024-08-21 | 286911 | 37.73 | Completed | 2024-09-13 | Ramjivan
344 | 268/0 | DD60 | DD60+6 | 2024-11-10 | 719574 | 94.408 | Completed | 2024-12-07 | Daulat Mahto
345 | 269/0 | DD60 | DD60+0 | 2025-03-26 | 604881 | 80.408 | Completed | 2025-04-01 | Jwala
346 | 269/1 | DA | DA+0 | 2024-12-28 | 286911 | 37.73 | Completed | 2025-01-07 | Daulat Mahto
347 | 269/2 | DA | DA+6 | 2025-01-11 | 342192 | 44.728 | Completed | 2025-01-19 | Maa Construction
348 | 270/0 | DD45 | DD45+0 | 2025-02-22 | 546238 | 72.238 | Completed | 2025-03-16 | Anarul Haque
349 | 270/1 | DA | DA+0 | 2024-12-11 | 286911 | 37.73 | Completed | 2024-12-24 | Daulat Mahto
350 | 270/2 | DA | DA+3 | 2024-09-14 | 297143 | 39.459 | Completed | 2024-10-28 | Senahul
351 | 270/3 | DA | DA-3 | 2025-03-19 | 273608.93 | 36.045 | Completed | 2025-03-28 | Thanu mahto
352 | 270/4 | DA | DA+0 | 2025-03-09 | 286911 | 37.73 | Completed | 2025-03-28 | Mithun Kumar
353 | 270/5 | DA | DA+0 | 2025-02-20 | 286911 | 37.73 | Completed | 2025-02-28 | Mithun Kumar
354 | 270/6 | DA | DA-3 | 2025-02-11 | 273608.93 | 36.045 | Completed | 2025-02-17 | Mithun Kumar
355 | 270/7 | DA | DA-3 | 2025-02-17 | 273608.93 | 36.045 | Completed | 2025-02-23 | Daulat Mahto
356 | 270A/0 | DC | DC2+0 | 2025-02-05 | 470077 | 64.254 | Completed | 2025-02-15 | Daulat Mahto
357 | 271/0 | DC | DC1+0 | 2025-02-04 | 470077 | 64.254 | Completed | 2025-02-13 | Thanu mahto
358 | 271/1 | DA | DA-3 | 2025-03-21 | 273608.93 | 36.045 | Completed | 2025-03-25 | Jwala
359 | 271/2 | DA | DA+0 | 2025-02-14 | 286911 | 37.73 | Completed | 2025-02-21 | Thanu Mahto
360 | 271/3 | DA | DA-3 | 2035-03-04 | 273608.93 | 36.045 | Completed | 2025-03-11 | Thanu Mahto
361 | 271/4 | DA | DA-3 | 2025-02-22 | 273608.93 | 36.045 | Completed | 2025-03-03 | Thanu Mahto
362 | 271/5 | DA | DA-3 | 2025-01-01 | 273608.93 | 36.045 | Completed | 2025-01-11 | Thanu mahto
363 | 272/0 | DC | DC1+6 | 2024-12-11 | 559332 | 74.632 | Completed | 2024-12-31 | Thanu mahto
364 | 272/1 | DA | DA+9 | 2024-12-02 | 357181 | 46.623 | Completed | 2024-12-16 | MJR
365 | 272/2 | DA | DA-3 | 2025-01-30 | 273608.93 | 36.045 | Completed | 2025-02-04 | Daulat Mahto
366 | 272/3 | DA | DA+3 | 2025-01-17 | 297143 | 39.459 | Completed | 2025-02-06 | Tajirul
367 | 272/4 | DA | DA+3 | 2025-01-25 | 297143 | 39.459 | Completed | 2025-02-02 | Thanu mahto
368 | 272/5 | DB | DB1+0 | 2025-01-13 | 403998 | 54.418 | Completed | 2025-01-23 | Thanu mahto
369 | 272/6 | DA | DA+3 | 2025-03-19 | 297143 | 39.459 | Completed | 2025-03-30 | Daulat Mahto
370 | 272/7 | DA | DA+9 | 2025-02-10 | 357181 | 46.623 | Completed | 2025-03-07 | Tajirul
371 | 272A/0 | DB | DB1+18(2M RC) | 2025-04-03 | 670636 | 82.239 | Completed | 2025-04-26 | Senahul
372 | 272A/1 | DA | DA+6 | 2025-01-24 | 342192 | 44.728 | Completed | 2025-01-29 | Jwala
373 | 272A/2 | DA | DA+0 | 2025-01-30 | 286911 | 37.73 | Completed | 2025-02-04 | Jwala
374 | 272A/3 | DA | DA+0 | 2025-02-05 | 286911 | 37.73 | Completed | 2025-02-09 | Jwala
375 | 272A/4 | DA | DA+0 | 2025-03-17 | 286911 | 37.73 | Completed | 2025-03-20 | Jwala
376 | 272A/5 | DA | DA+3 | 2025-03-11 | 297143 | 39.459 | Completed | 2025-03-16 | Jwala
377 | 272A/6 | DA | DA-3 | 2025-03-02 | 273608.93 | 36.045 | Completed | 2025-03-05 | Jwala
378 | 272A/7 | DA | DA-3 | 2025-03-06 | 273608.93 | 36.045 | Completed | 2025-03-10 | Jwala
379 | 273/1 | DA | DA+6 | 2025-04-04 | 342192 | 44.728 | Completed | 2025-04-09 | Jwala
380 | 273/2 | DA | DA+6 | 2025-02-24 | 342192 | 44.728 | Completed | 2025-02-28 | Jwala
381 | 274/0 | DC | DC1+0 | 2025-02-17 | 470077 | 64.254 | Completed | 2025-02-23 | Jwala
382 | 275/0 | DD45 | DD45+0 | 2025-08-06 |  | 72.238 | Completed | 2025-09-14 | Modina india
383 | 276/0 | DD | DD60+0 | 2025-08-26 |  | 80.408 | Completed | 2025-10-04 | Kamruddin
384 | 237/3 | DA | DA-3 | 2025-09-24 |  | 36.045 | Completed | 2025-10-03 | Sukhrridin
385 | 247/3 | DA | DA-3 | 2025-03-14 |  | 36.405 | Completed | 2025-10-06 | Didar Electricals (PGCIL)
386 | 215/0 | DB | DB+6 | 2025-09-13 |  | 63.509 | Completed | 2025-10-06 | Prayag Mahto
387 | 237/5 | DA | DA-3 | 2025-09-24 |  | 36.045 | Completed | 2025-10-06 | Muni Bibi
388 | 234/0 | DD45 | DD45+0 | 2025-09-18 |  | 72.238 | Completed | 2025-10-08 | MD Akhtar
389 | 102/0 | DD45 | DD45+35 |  |  | 156.901 |  |  | Dhaneshwar Mahto
390 | 229/3 | DA | DA+0 |  |  | 37.73 |  | 2025-10-05 | Modina India-3 (PGCIL)
391 | 237/1 | DA | DA+0 |  |  | 37.73 |  | 2025-10-05 | Muni Bibi-2
392 | 237/0 | DD45 | DD45+9 |  |  | 89.146 |  | 2025-10-15 | Rupesh
393 | 237/6 | DA | DA+4 |  |  | 39.459 |  | 2025-10-08 | Dildar Electrical-2_PGCIL
21414.926
Summary
|  | DA | 237 |  | Tower Type | Supply | Completed Erection
|  | DB | 40 |  | DA-3 | 40 | 35
|  | DC | 39 |  | DA+0 | 146 | 130
|  | DD45 | 30 |  | DA+3 | 40 | 33
|  | DD60 | 40 |  | DA+6 | 30 | 28
|  | Total | 386 |  | DA+9 | 11 | 9
[5 empty] | DA Type | 267 | 235
[5 empty] | DB+0 | 25
[5 empty] | DB+3 | 6
[5 empty] | DB+6 | 8
[5 empty] | DB+9 | 9
[5 empty] | DB+18 | 6
[5 empty] | DB+25 | 1
[5 empty] | DB Type | 55
[5 empty] | DC+0 | 26
[5 empty] | DC+3 | 3
[5 empty] | DC+6 | 4
[5 empty] | DC+9 | 7
[5 empty] | DC+18 | 4
[5 empty] | DC+25 | 3
[5 empty] | DC Type | 47
[5 empty] | DD45+0 | 16
[5 empty] | DD45+3 | 4
[5 empty] | DD45+6 | 3
[5 empty] | DD45+9 | 4
[5 empty] | DD45+18 | 6
[5 empty] | DD45+25 | 5
[5 empty] | DD45+35 | 2
[5 empty] | DD45 Type | 40
[5 empty] | DD60+0 | 19
[5 empty] | DD60+3 | 8
[5 empty] | DD60+6 | 11
[5 empty] | DD60+9 | 7
[5 empty] | DD60+18 | 7
[5 empty] | DD60+25 | 15
[5 empty] | DD60+35 | 4
[5 empty] | DD60+55 | 2
[5 empty] | DD60+55 Type | 73
[5 empty] | DCT+0 | 1
[5 empty] | DCT Type | 1
[5 empty] | Total | 483

## EREC-VDRA
#REF!
Tower Erection Part-I (Vadodara Section)
Sl. No. | Loc. No. | Type of Tower | Start Date | Revenue | Tower Wgt. (MT) | Todays Status | End Date | Sub Contractor | Remarks | Tackwelding Status | Tackwelding Start date | Tackwelding Completion date | Sub Contractor
1 | 127/1 | DA+0 | 2023-09-30 | 286911 | 37.73 | Completed | 2023-10-15 | Team 01 |  | Completed | 2024-02-18 | 2024-02-19 | Bharath Const.
2 | 127/2 | DA+0 | 2023-10-16 | 286911 | 37.73 | Completed | 2023-10-29 | Team 01 |  | Completed | 2024-02-17 | 2024-02-18 | Bharath Const.
3 | 135A/4 | DA+0 | 2023-11-01 | 286911 | 37.73 | Completed | 2023-11-09 | Team 01 |  | Completed | 2024-02-08 | 2024-02-09 | Bharath Const.
4 | 135/2 | DA+0 | 2023-11-11 | 286911 | 37.73 | Completed | 2023-11-17 | Team 01 |  | Completed | 2024-02-09 | 2024-02-10 | Bharath Const.
5 | 135A/7 | DA+0 | 2023-11-19 | 286911 | 37.73 | Completed | 2023-12-01 | Team 01 |  | Completed | 2024-02-14 | 2024-02-15 | Bharath Const.
6 | 133/1 | DA+0 | 2023-12-02 | 286911 | 37.73 | Completed | 2023-12-15 | Team 01 |  | Completed | 2024-02-15 | 2024-02-17 | Bharath Const.
7 | 135B/4 | DA+6 | 2024-01-04 | 342192 | 44.728 | Completed | 2024-01-12 | Team 02 |  | Completed | 2024-02-11 | 2024-02-12 | Bharath Const.
8 | 135B/3 | DA+0 | 2024-01-12 | 286911 | 37.73 | Completed | 2024-01-18 | Team 02 |  | Completed | 2024-02-12 | 2024-02-13 | Bharath Const.
9 | 135B/2 | DA+0 | 2024-01-18 | 286911 | 37.73 | Completed | 2024-01-23 | Team 02 |  | Completed | 2024-02-21 | 2024-02-21 | Bharath Const.
10 | 135A/3 | DA+0 | 2024-01-23 | 286911 | 37.73 | Completed | 2024-01-28 | Team 02 |  | Completed | 2024-02-13 | 2024-02-14 | Bharath Const.
11 | 135B/5 | DA+0 | 2024-01-28 | 286911 | 37.73 | Completed | 2024-02-02 | Team 02 |  | Completed | 2024-02-10 | 2024-02-11 | Bharath Const.
12 | 135B/0 | DB1+0 | 2024-02-02 | 403998 | 54.418 | Completed | 2024-02-09 | Team 02 |  | Completed | 2024-05-07 | 2024-05-07 | Bharath Const.
13 | 132/2 | DA+0 | 2024-02-04 | 286911 | 37.73 | Completed | 2024-02-13 | Team 03 |  | Completed | 2024-02-25 | 2024-02-25 | Bharath Const.
14 | 135B/6 | DA+0 | 2024-02-04 | 286911 | 37.73 | Completed | 2024-02-15 | Team 02 |  | Completed | 2024-02-24 | 2024-02-24 | Bharath Const.
15 | 133/0 | DB1+0 | 2024-02-13 | 403998 | 54.418 | Completed | 2024-02-21 | Team 03
16 | 133A/3 | DA+0 | 2024-02-15 | 286911 | 37.73 | Completed | 2024-02-20 | Team 02 |  | Completed | 2024-03-02 | 2024-03-02 | Bharath Const.
17 | 135B/1 | DA+0 | 2024-02-20 | 286911 | 37.73 | Completed | 2024-02-26 | Team 02 |  | Completed | 2024-05-06 | 2024-05-06 | Bharath Const.
18 | 133/3 | DA+0 | 2024-02-20 | 286911 | 37.73 | Completed | 2024-02-28 | Team 03
19 | 135/3 | DA+0 | 2024-02-26 | 286911 | 37.73 | Completed | 2024-03-02 | Team 02 |  | Completed | 2024-03-03 | 2024-03-04 | Bharath Const.
20 | 133/2 | DA+0 | 2024-02-27 | 286911 | 37.73 | Completed | 2024-03-03 | Team 03
21 | 135B/7 | DA+3 | 2024-03-02 | 297143 | 39.459 | Completed | 2024-04-11 | Team 02 |  | Completed | 2024-05-08 | 2024-05-08 | Bharath Const.
22 | 133/5 | DA+0 | 2024-03-03 | 286911 | 37.73 | Completed | 2024-03-08 | Team 03
23 | 133A/0 | DB1+0 | 2024-03-08 | 403998 | 54.418 | Completed | 2024-03-13 | Team 03
24 | 133A/1 | DA+0 | 2024-03-13 | 286911 | 37.73 | Completed | 2024-03-13 | Team 03
25 | 133A/2 | DA+6 | 2024-04-13 | 342192 | 44.728 | Completed | 2024-04-19 | Team 03
26 | 133/4 | DA+0 | 2024-04-20 | 286911 | 37.73 | Completed | 2024-04-24 | Team 03
27 | 129A/0 | DC1+0 | 2024-04-25 | 470077 | 64.254 | Completed | 2024-04-30 | Team 03
28 | 129A/1 | DA+0 | 2024-05-02 | 286911 | 37.73 | Completed | 2024-05-07 | Team 03
29 | 135/6 | DA+0 | 2024-05-01 | 286911 | 37.73 | Completed | 2024-05-19 | Team 04
30 | 129A/2 | DA+3 | 2024-05-07 | 297143 | 39.459 | Completed | 2024-05-12 | Team 03
31 | 137/4 | DA+0 | 2024-05-07 | 286911 | 37.73 | Completed | 2024-05-18 | Team 04
32 | 130/0 | DB1+0 | 2024-05-07 | 403998 | 54.418 | Completed | 2024-05-18 | Team 03
33 | 137/3 | DA+0 | 2024-05-19 | 286911 | 37.73 | Completed | 2024-05-24 | Team 03
34 | 135/5 | DA+0 | 2024-05-19 | 286911 | 37.73 | Completed | 2024-05-31 | Team 04
35 | 127/4 | DA+3 | 2024-05-19 | 297143 | 39.459 | Completed | 2024-05-24 | Team 01
36 | 127/3 | DA+0 | 2024-05-25 | 286911 | 37.73 | Completed | 2024-05-31 | Team 02
37 | 137/1 | DA+3 | 2024-05-25 | 297143 | 39.459 | Completed | 2024-05-31 | Team 03
38 | 127/0 | DD45+0 | 2024-05-31 | 546238 | 72.238 | Completed | 2024-06-10 | Team 01
39 | 135/4 | DA+0 | 2024-05-31 | 286911 | 37.73 | Completed | 2024-06-10 | Team 03
40 | 144/2 | DA+0 | 2024-06-11 | 286911 | 37.73 | Completed | 2024-06-15 | Team 04 |  | Completed |  |  | Bharath Const.
41 | 112/0 | DD45+0 | 2024-06-05 | 546238 | 72.238 | Completed | 2024-06-13 | Team-05
42 | 132/3 | DA+0 | 2024-06-12 | 286911 | 37.73 | Completed | 2024-06-18 | Team 02
43 | 144/3 | DA+0 | 2024-06-13 | 286911 | 37.73 | Completed | 2024-06-15 | Team 04 |  | Completed | 2024-06-23 | 2024-06-23 | Bharath Const.
44 | 106A/4 | DA+9 | 2024-06-14 | 357181 | 46.623 | Completed | 2024-06-24 | Team-05
45 | 144/4 | DA+0 | 2024-06-16 | 286911 | 37.73 | Completed | 2024-06-20 | Team 04
46 | 144/5 | DA+0 | 2024-06-21 | 286911 | 37.73 | Completed | 2024-06-26 | Team 04
47 | 144/1 | DA+0 | 2024-06-30 | 286911 | 37.73 | Completed | 2024-07-05 | Team 04
48 | 106A/3 | DA+3 | 2024-06-25 | 297143 | 39.459 | Completed | 2024-07-02 | Team-05
49 | 106B/2 | DA+6 | 2024-07-02 | 342192 | 44.728 | Completed | 2024-07-12 | Gouri Shankar
50 | 119/2 | DA+0 | 2024-07-08 | 286911 | 37.73 | Completed | 2024-07-12 | Rahul Kumar
51 | 113/0 | DD60+0 | 2024-07-08 | 604881 | 80.408 | Completed | 2024-07-25 | Ajay Kumar
52 | 119/3 | DA+0 | 2024-07-13 | 286911 | 37.73 | Completed | 2024-07-18 | Rahul Kumar
53 | 107/0 | DD45+0 | 2024-07-13 | 546238 | 72.238 | Completed | 2024-07-29 | Gouri Shankar
54 | 126/0 | DC2+0 | 2024-07-20 | 470077 | 64.254 | Completed | 2024-07-31 | Rahul Kumar
55 | 106B/1 | DA+9 | 2024-07-28 | 357181 | 46.263 | Completed. | 2024-08-08 | Ajay Kumar
56 | 116A/0 | DC1+0 | 2024-07-30 | 470077 | 64.254 | Completed. | 2024-08-11 | Gouri Shankar
57 | 118/0 | DD45+0 | 2024-08-01 | 546238 | 72.238 | Completed. | 2024-08-20 | Rahul Kumar
58 | 106B/0 | DB2+9 | 2024-08-08 | 503365 | 65.757 | Completed. | 2024-08-24 | Rahul Kumar
59 | 109/0 | DB2+0 | 2024-08-11 | 403998 | 54.418 | Completed | 2024-08-23 | Gouri Shankar
60 | 110/0 | DB2+0 | 2024-08-18 | 403998 | 54.418 | Completed | 2024-08-31 | Rahul Kumar
61 | 117/0 | DD60+3 | 2024-11-20 | 635073 | 84.299 | Completed. | 2024-12-03 | Gouri Shankar
62 | 123/0 | DD60+6 | 2024-09-26 | 719574 | 94.408 | Completed. | 2024-10-10 | Ajay Kumar
63 | 114/0 | DD45+0 | 2024-09-02 | 546238 | 72.238 | Completed | 2024-09-13 | Gouri Shankar
64 | 111/0 | DC1+0 | 2024-09-09 | 470077 | 64.254 | Completed. | 2024-09-21 | Rahul Kumar
65 | 119/0 | DD45+0 | 2024-09-12 | 546238 | 72.238 | Completed. | 2024-09-24 | Ajay Kumar
66 | 116/0 | DD45+18 | 2024-09-10 | 906755 | 112.424 | Completed. | 2024-09-27 | Dhaneswar Mahto
67 | 107/1 | DA-3 | 2024-09-16 | 273608.93 | 36.045 | Completed. | 2024-09-26 | Barkad Alli
68 | 152/1 | DA+0 | 2024-09-16 | 286911 | 37.73 | Completed. | 2024-10-12 | Rejaul | No work due to holiday.
69 | 119/1 | DA-3 | 2024-09-14 | 273608.93 | 36.045 | Completed. | 2024-09-23 | Gouri Shankar
70 | 124A/1 | DA+3 | 2024-09-16 | 297143 | 39.459 | Completed. | 2024-09-30 | Senaul Haque
71 | 121/0 | DD60+18 | 2024-09-23 | 1003256 | 129.341 | Completed. | 2024-10-10 | Rahul Kumar
72 | 133A/4 | DA+6 | 2024-09-27 | 342192 | 44.728 | Completed. | 2024-10-12 | Mithun Kumar
73 | 108/0 | DD45+0 | 2024-09-28 | 546238 | 72.238 | Completed. | 2024-10-13 | Dherendra Kumar
74 | 120/0 | DD60+9 | 2024-10-01 | 753337 | 98.836 | Completed | 2024-10-24 | Gouri Shankar-01
75 | 122/0 | DC1+6 | 2024-10-04 | 559332 | 74.632 | Completed. | 2024-10-15 | Gouri Shankar-02
76 | 106/0 | DD60+9 | 2024-10-03 | 753337 | 98.836 | Completed. | 2024-12-08 | DK Verma
77 | 135A/1 | DD45+3 | 2024-10-08 | 573550 | 75.452 | Completed. | 2024-11-03 | Dhaneshwar
78 | 116B/0 | DD45+6 | 2024-10-13 | 650023 | 85.234 | Completed. | 2024-10-31 | Ajay Kumar
79 | 152/0 | DC2+0 | 2024-10-15 | 470077 | 64.254 | Completed | 2024-10-24 | Mukesh
80 | 144/0 | DB2+3 | 2024-10-15 | 424198 | 56.863 | Completed. | 2024-11-16 | Mukesh
81 | 152/2 | DA-3 | 2024-09-24 | 273608.93 | 36.045 | Completed. | 2024-11-07 | SK Samuil
82 | 123/1 | DA+3 | 2024-10-17 | 297143 | 39.459 | Completed | 2024-10-31 | Gourishankar-02
83 | 152/3 | DA-3 | 2024-10-25 | 273608.93 | 36.045 | Completed | 2024-10-31 | Mukesh
84 | 126/1 | DA+6 | 2024-12-21 | 342192 | 44.728 | Completed. | 2024-12-27 | Gouri Shankar-01
85 | 124/0 | DC1+3 | 2024-10-28 | 493565 | 66.268 | Completed. | 2024-11-11 | Ajay Kumar
86 | 125A/0 | DB2+3 | 2024-11-02 | 424198 | 56.863 | Completed. | 2024-11-13 | Gouri Shankar-02
87 | 152/4 | DA+0 | 2024-11-02 | 286911 | 37.73 | Completed. | 2024-11-07 | Mukesh
88 | 135A/2 | DB2+9 | 2024-11-05 | 503365 | 65.757 | Completed. | 2024-11-13 | Dhaneshwar
89 | 150A/1 | DA+3 | 2024-11-10 | 297143 | 39.459 | Completed. | 2024-11-22 | SK Samuil
90 | 128/0 | DD60+6 | 2024-11-13 | 719574 | 94.408 | Completed. | 2024-11-26 | Ajay
91 | 147/3 | DA-3 | 2024-11-13 | 273608.93 | 36.045 | Completed. | 2024-12-02 | Modina India
92 | 137A/5 | DA-3 | 2024-11-14 | 273608.93 | 36.045 | Completed. | 2024-11-20 | Dahneshwar
93 | 144A/0 | DB1+9 | 2024-11-18 | 503365 | 65.757 | Completed. | 2024-11-24 | Mukesh
94 | 137A/3 | DA+6 | 2024-11-20 | 342192 | 44.728 | Completed. | 2024-11-28 | Dhaneshwar Mahto
95 | 127/5 | DA+3 | 2024-11-27 | 297143 | 39.459 | Completed. | 2024-12-07 | Ajay Kumar
96 | 150A/2 | DA+0 | 2024-11-23 | 286911 | 37.73 | Completed. | 2024-12-02 | SK Samuil
97 | 155/2 | DA+3 | 2024-11-16 | 297143 | 39.459 | Completed. | 2024-11-30 | Rahul Kumar
98 | 164/4 | DA+0 | 2024-11-16 | 286911 | 37.73 | Completed. | 2024-11-27 | Sukhriddin
99 | 145/0 | DB1+18 | 2024-11-18 | 670636 | 82.239 | Completed. | 2024-12-08 | Mukesh Kumar
100 | 163/3 | DA+0 | 2024-11-28 | 286911 | 37.73 | Completed. | 2024-12-18 | Rahim
101 | 164/5 | DA+0 | 2024-11-28 | 286911 | 37.73 | Completed. | 2024-12-14 | Sukhriddin
102 | 137A/4 | DA-3 | 2024-11-29 | 273608.93 | 36.045 | Completed. | 2024-12-03 | Dhaeshwar Mahto
103 | 158B/1 | DA+3 | 2024-11-16 | 297143 | 39.459 | Completed. | 2024-12-12 | Rahul Kumar
104 | 115/0 | DC2+25 | 2024-12-04 |  | 109.608 | Completed. | 2024-12-20 | Gouri Shankar
105 | 134/0 | DC2+25 | 2024-12-04 |  | 109.608 | Completed. | 2024-12-20 | Dhaneshawar Mahto
106 | 147/5 | DA+6 | 2024-12-03 | 342192 | 44.728 | Completed. | 2024-12-22 | Modina India
107 | 148/4 | DA+0 | 2024-12-23 | 286911 | 37.73 | Completed. | 2025-01-06 | Modina India-1
108 | 147/1 | DC2+0 | 2024-12-09 | 470077 | 64.254 | Completed. | 2024-12-16 | Mukesh Kumar
109 | 116A/1 | DA+0 | 2024-12-09 | 286911 | 37.73 | Completed. | 2024-12-21 | DK Verma
110 | 132/0 | DC2+3 | 2024-12-08 |  | 66.268 | Completed. | 2024-12-21 | SK Samuil
111 | 147/4 | DA+3 | 2024-12-10 | 297143 | 39.459 | Completed. | 2024-12-25 | Modina India
112 | 158B/0 | DD45+18 | 2024-11-13 | 906755 | 112.424 | Completed. | 2024-12-30 | Rahul Kumar
113 | 164/6 | DA+0 | 2024-12-14 | 286911 | 37.73 | Completed. | 2024-12-25 | Sukhriddin
114 | 147/2 | DC1+0 | 2024-12-17 | 470077 | 64.254 | Completed. | 2024-12-23 | Mukesh Kumar
115 | 106A/2 | DA-3 | 2024-12-19 | 273608.93 | 36.045 | Completed. | 2024-12-28 | Barkat Ali
116 | 163/2 | DA+0 | 2024-11-28 | 286911 | 37.73 | Completed. | 2024-12-29 | Rahim
117 | 106A/1 | DA+6 | 2024-12-22 | 342192 | 44.728 | Completed | 2024-12-28 | DK Verma
118 | 125/0 | DD60+0 | 2024-12-22 | 604881 | 80.408 | Completed. | 2025-01-05 | MJR
119 | 132/1 | DA+0 | 2024-12-22 | 286911 | 37.73 | Completed. | 2024-12-30 | SK Samuil
120 | 135A/6 | DA+0 | 2024-12-21 | 286911 | 37.73 | Completed. | 2024-12-26 | Dhaneshwar mahto
121 | 147A/0 | DB1+18 | 2024-12-24 | 670636 | 82.239 | Completed. | 2025-01-03 | Mukesh Kumar
122 | 135A/0 | DC1+0 | 2024-12-27 | 470077 | 64.254 | Completed. | 2025-01-04 | Dhaneshwar Mahto
123 | 106A/0 | DC2+0 | 2024-12-29 | 470077 | 64.254 | Completed. | 2025-01-03 | DK Verma
124 | 124A/0 | DD60+0 | 2024-12-21 | 604881 | 80.408 | Completed. | 2025-01-05 | Gouri Shankar
125 | 129/0 | DD60+6 | 2024-12-30 | 719574 | 94.408 | Completed. | 2025-01-18 | Barkat Ali
126 | 164/0 | DB2+0 | 2024-12-28 | 403998 | 54.418 | Completed. | 2025-01-12 | Sukhriddin
127 | 164/1 | DA+0 | 2024-12-28 | 286911 | 37.73 | Completed. | 2025-01-16 | Modina India-2
128 | 130/4 | DA+3 | 2024-12-22 | 297143 | 39.459 | Completed. | 2025-01-21 | SK Samuil
129 | 158B/2 | DA+3 | 2024-12-31 | 297143 | 39.459 | Completed. | 2025-01-10 | Rahul Kumar
130 | 163/1 | DA+0 | 2024-12-30 | 286911 | 37.73 | Completed. | 2025-01-08 | Rahim
131 | 135/0 | DC2+25 | 2025-01-09 |  | 109.628 | Completed. | 2025-01-22 | DK Verma
132 | 148/0 | DC2+0 | 2025-01-04 | 470077 | 64.254 | Completed. | 2025-01-10 | Mukesh Kumar
133 | 135/1 | DA+6 | 2025-01-06 | 342192 | 44.728 | Completed. | 2025-01-11 | Surender Mahto
134 | 130/3 | DA+0 | 2025-01-09 | 286911 | 37.73 | Completed. | 2025-01-18 | MJR
135 | 136/0 | DD45+18 | 2025-01-09 | 906755 | 112.424 | Completed. | 2025-01-25 | Gouri Shankar
136 | 148/3 | DA+0 | 2025-01-10 | 286911 | 37.73 | Completed. | 2025-01-19 | Modina Inda-1
137 | 163/6 | DA+0 | 2025-01-10 | 286911 | 37.73 | Completed. | 2025-01-25 | Barkat Ali
138 | 164/3 | DA+0 | 2025-01-11 | 286911 | 37.73 | Completed. | 2025-01-20 | Rahim Khan
139 | 135A/5 | DA+0 | 2025-01-13 | 286911 | 37.73 | Completed. | 2025-01-18 | Dhaneshwar Mahto
140 | 163/4 | DA+0 | 2025-01-16 | 286911 | 37.73 | Completed. | 2025-01-29 | Sukhriddin
141 | 163/5 | DA+0 | 2025-01-12 | 286911 | 37.73 | Completed. | 2025-02-20 | Barkat Ali
142 | 130/2 | DA+3 | 2025-01-20 | 297143 | 39.459 | Completed. | 2025-01-29 | MJR
143 | 163/0 | DC2+0 | 2025-01-16 | 470077 | 64.254 | Completed. | 2025-01-23 | Rahul Kumar
144 | 159/4 | DA+0 | 2025-01-21 | 286911 | 37.73 | Completed. | 2025-02-03 | Modina India-2
145 | 137A/6 | DA+9 | 2025-01-20 | 357181 | 46.623 | Completed. | 2025-01-24 | Dhaneshwar Mahto
146 | 131/0 | DD45+3 | 2025-01-21 | 573550 | 75.452 | Completed. | 2025-02-05 | Barkat Ali
147 | 148/2 | DA+0 | 2025-01-21 | 286911 | 37.73 | Completed. | 2025-01-30 | Modina India-1
148 | 159/1 | DA+0 | 2025-01-21 | 286911 | 37.73 | Completed. | 2025-02-12 | Rahim Khan
149 | 130/1 | DA+0 | 2025-01-25 | 286911 | 37.73 | Completed. | 2025-02-09 | SK Samuil
150 | 137A/0 | DB1+0 | 2025-01-23 | 403998 | 54.418 | Completed. | 2025-01-29 | DK Verma
151 | 147/6 | DA-3 | 2025-01-27 | 273608.93 | 36.045 | Completed. | 2025-02-18 | Ajay Kumar
152 | 161/0 | DD60+25 | 2025-01-28 | 1099828 | 141.874 | Completed. | 2025-02-16 | Rahul Kumar
153 | 137/6 | DA+0 | 2025-01-27 | 286911 | 37.73 | Completed. | 2025-02-07 | SK Samuil
154 | 137A/1 | DA+6 | 2025-01-27 | 342192 | 44.728 | Completed. | 2025-01-29 | Dhaneshwar Mahto
155 | 138/0 | DB2+0 | 2025-01-27 | 403998 | 54.418 | Completed. | 2025-02-01 | Gouri Shankar
156 | 137A/2 | DA+0 | 2025-01-30 | 286911 | 37.73 | Completed. | 2025-02-02 | Dhaneshwar Mahto
157 | 139/0 | DB2+0 | 2025-01-30 | 403998 | 54.418 | Completed. | 2025-02-04 | DK Verma
158 | 148/1 | DA+3 | 2025-02-01 | 297143 | 39.459 | Completed. | 2025-02-09 | Modina India
159 | 137/0 | DC2+9 | 2025-02-01 | 585620 | 77.718 | Completed. | 2025-02-15 | MJR
160 | 137/5 | DA+3 | 2025-02-03 | 297143 | 39.459 | Completed. | 2025-02-07 | Dhaneshwar Mahto
161 | 138/1 | DA+6 | 2025-02-03 | 342192 | 44.728 | Completed. | 2025-02-09 | Gouri Shankar
162 | 157/1 | DA+0 | 2025-02-09 | 286911 | 37.73 | Completed. | 2025-02-18 | Sukhriddin
163 | 157/2 | DA+0 | 2025-02-23 | 286911 | 37.73 | Completed. | 2025-03-11 | Barkat Ali
164 | 138/2 | DA+0 | 2025-02-05 | 286911 | 37.73 | Completed. | 2025-02-11 | DK Verma
165 | 139A/0 | DB2+9 | 2025-02-09 | 503365 | 65.757 | Completed. | 2025-02-14 | Dhaneshwar Mahto
166 | 141/1 | DA+0 | 2025-02-11 | 286911 | 37.73 | Completed. | 2025-02-17 | SK Samuil
167 | 139/2 | DA+0 | 2025-02-10 | 286911 | 37.73 | Completed. | 2025-02-14 | Gouri Shankar
168 | 141/2 | DA-3 | 2025-02-13 | 273608.93 | 36.045 | Completed. | 2025-02-19 | SK Samui
169 | 147B/1 | DA+0 | 2025-02-13 | 286911 | 37.73 | Completed. | 2025-02-21 | Modina India
170 | 139/1 | DA+3 | 2025-02-12 | 297143 | 39.459 | Completed. | 2025-02-17 | DK Verma
171 | 141/3 | DA+3 | 2025-02-19 | 297143 | 39.459 | Completed. | 2025-02-25 | SK Samui-3
172 | 137/2 | DA+0 | 2025-02-18 | 286911 | 37.73 | Completed. | 2025-02-27 | MJR
173 | 140/0 | DD60+0 | 2025-02-16 | 604881 | 80.408 | Completed. | 2025-02-22 | Dhaneshwar Mahto
174 | 141/0 | DD60+3 | 2025-02-16 | 635073 | 84.299 | Completed. | 2025-02-23 | Gouri Shankar
175 | 162/0 | DD60+25 | 2025-02-20 | 1099828 | 141.874 | Completed. | 2025-03-09 | Rahul Kumar
176 | 142/0 | DD60+0 | 2025-02-18 | 604881 | 80.408 | Completed. | 2025-03-03 | DK Verma
177 | 148/5 | DA+0 | 2025-02-25 | 286911 | 37.73 | Completed. | 2025-02-28 | SK Samui | Crane erection
178 | 145A/1 | DA+3 | 2025-02-22 | 297143 | 39.459 | Completed. | 2025-03-07 | Sulen sarkar
179 | 147B/0 | DB1+18 | 2025-02-26 | 670636 | 82.239 | Completed. | 2025-03-22 | Modina India
180 | 143/0 | DD60+3 | 2025-02-25 | 635073 | 84.299 | Completed. | 2025-03-04 | Gouri Shankar
181 | 143A/0 | DD45+0 | 2025-02-24 | 546238 | 72.238 | Completed. | 2025-03-02 | Dhaneshwar Mahto
182 | 145A/3 | DA+0 | 2025-03-08 | 286911 | 37.73 | Completed. | 2025-03-16 | Sulen Sarkar
183 | 149/1 | DA+0 | 2025-03-17 | 286911 | 37.73 | Completed. | 2025-03-27 | SK Samui | Crane erection
184 | 143A/1 | DA+6 | 2025-03-01 | 342192 | 44.728 | Completed. | 2025-03-09 | SK Samui
185 | 143A/4 | DA+0 | 2025-03-02 | 286911 | 37.73 | Completed. | 2025-03-10 | MJR
186 | 148/6 | DA+0 | 2025-03-03 | 286911 | 37.73 | Completed. | 2025-03-09 | SK Samui
187 | 143A/2 | DD45+0 | 2025-03-04 | 546238 | 72.238 | Completed. | 2025-03-17 | Dhaneshwar Mahto
188 | 143A/3 | DD45+3 | 2025-03-05 | 573550 | 75.452 | Completed. | 2025-03-11 | Gouri Shankar
189 | 143A/5 | DA+3 | 2025-03-05 | 297143 | 39.459 | Completed. | 2025-03-10 | DK Verma
190 | 148/7 | DA+0 | 2025-03-08 | 286911 | 37.73 | Completed. | 2025-03-20 | Rahim Khan | Crane erection
191 | 149/0 | DB2+0 | 2025-03-10 | 403998 | 54.418 | Completed. | 2025-04-06 | SK Samui
192 | 157/0 | DD60+6 | 2025-03-12 | 719574 | 94.408 | Completed. | 2025-03-27 | Rahim Khan
193 | 145A/0 | DB1+6 | 2025-03-15 | 480757 | 63.509 | Completed. | 2025-03-28 | MJR
194 | 146/0 | DC1+9 | 2025-03-12 | 585620 | 77.718 | Completed. | 2025-03-22 | DK Verma
195 | 158/2 | DA-3 | 2025-03-13 | 273608.93 | 36.045 | Completed. | 2025-03-18 | Rahul Kumar
196 | 150/1 | DA+9 | 2025-03-20 | 357181 | 46.623 | Completed. | 2025-04-06 | MJR
197 | 150/2 | DA+3 | 2025-03-18 | 297143 | 39.459 | Completed. | 2025-03-22 | SK Samui
198 | 150/3 | DA+6 | 2025-03-19 | 342192 | 44.728 | Completed. | 2025-04-01 | Rupesh
199 | 152A/0 | DB1+0 | 2025-03-16 | 403998 | 54.418 | Completed. | 2025-03-20 | Gouri Shankar
200 | 155/6 | DA-3 | 2025-03-15 | 273608.93 | 36.045 | Completed. | 2025-03-23 | Barkat Ali
201 | 145A/2 | DA+3 | 2025-03-19 | 297143 | 39.459 | Completed. | 2025-03-27 | Sulen sarkar
202 | 156/0 | DD60+3 | 2025-03-22 | 635073 | 84.299 | Completed. | 2025-03-28 | Rahul Kumar
203 | 147/0 | DC2+9 | 2025-03-24 | 585620 | 77.718 | Completed. | 2025-04-01 | DK Verma
204 | 151/0 | DB2+3 | 2025-03-21 | 424198 | 56.863 | Completed. | 2025-03-27 | Gouri Shankar
205 | 150A/0 | DC1+0 | 2025-03-25 | 470077 | 64.254 | Completed. | 2025-04-11 | Rahim Khan
206 | 155/1 | DA+0 | 2025-03-26 | 286911 | 37.73 | Completed. | 2025-04-03 | Barkat Ali
207 | 158/0 | DB2+0 | 2025-04-02 | 403998 | 54.418 | Completed. | 2025-04-10 | Rahim Khan
208 | 155/0 | DD60+0 | 2025-04-02 | 604881 | 80.408 | Completed. | 2025-04-11 | Rahul Kumar
209 | 158/1 | DA-3 | 2025-04-07 | 273608.93 | 36.045 | Completed. | 2025-04-25 | Barkat Ali
210 | 135/7 | DA+0 | 2025-04-13 | 286911 | 37.73 | Completed. | 2025-04-22 | SK samui
211 | 155/4 | DA+0 | 2025-04-28 | 286911 | 37.73 | Completed. | 2025-05-11 | SK Samui | 02 days idle |  |  |  | 04 days ROW.
212 | 155/5 | DA+0 | 2025-04-29 | 286911 | 37.73 | Completed. | 2025-05-11 | Barkat Ali | 02 days idle
213 | 150/0 | DD60+9 | 2025-03-22 | 753337 | 98.836 | Completed. | 2025-03-31 | Dhaneshwar mahto
214 | 105/0 | DD60+35 | 2025-05-24 | 1294023 | 172.017 | Completed. | 2025-09-23 | Rupesh
215 | 165/1 | DA+0 | 2025-05-16 | 286911 | 37.73 | Completed. | 2025-05-25 | Barkat Ali
216 | 104/0 | DD60+35 | 2025-06-01 | 1294023 | 172.017 | Completed.Tightening u/p. | 2025-08-13 | Dhaneshwar
217 | 153/0 | DD60+25 | 2025-06-15 | 1099828 | 141.874 | Completed. | 2025-08-08 | Barkat Ali & Mithun Gang | Mithun gang shifted to this loc. on 12-06-2026
218 | 160/0 | DD60+18 |  | 1003256 | 129.341 | Materials shifting is u/p.Gang shifted.
219 | 101/0 | DD60+35 | 2025-06-15 | 1294023 | 171.017 | Completed. | 2025-09-19 | Sanjay Kumar & Dhaneshwar | Sanjya kumar demobilsed on 20-07-2025. Dhaneshwar mahto gang joined on 19-08-2025.
220 | 157/3 | DA+0 | 2025-06-15 | 286911 | 37.73 | Gang shifting completed and dewatering WIP |  | Barkat Ali & Sukhriddin | Sukhriddin gang moved to this loc. On 22-07-2025.ROW from 24-06-2025 to 21-07-2025.Sukhriddin gang demobilized on 25-07-2025.
221 | 102/0 | DD45+35 |  |  | 156.901 | Material shifting and plateform making U/P |  | Dhaneshwar Mahto
12340.403

## EREC-NAV
Tower Erection Part-II (Navsari Section)
Sl. No. | Loc. No. | Type of Tower | Start Date | Revenue | Tower Weight (MT) | Status | End Date | Sub Contractor | Manpower | Hindarnce Days | Remarks | Tackweldng Status | Tackwelding start date | Tackwelding Completion date | Sub Contractor name
1 | 159/3 | DA+0 | 2024-07-08 | 286911 | 37.73 | Completed | 2024-07-23 | Sukhridwin
2 | 255/4 | DA+0 | 2024-07-10 | 286911 | 37.73 | Completed | 2024-08-22 | Ghanshyam
3 | 164/2 | DA+0 | 2024-07-27 | 286911 | 37.73 | Completed | 2024-08-13 | Sukhridwin
4 | 159/0 | DB+0 | 2024-08-14 | 403998 | 54.418 | Completed. | 2024-09-08 | Sukhridwin
5 | 267A/3 | DA+0 | 2024-08-21 | 286911 | 37.73 | Completed. | 2024-09-13 | Ramjivan-01
6 | 257/3 | DA+0 | 2024-08-29 | 286911 | 37.73 | Completed | 2024-10-06 | Chahanur Bibi
7 | 257/0 | DC+0 | 2024-08-30 | 470077 | 64.254 | Completed | 2024-09-23 | Ghanshyam Mahto
8 | 165/2 | DA+0 | 2024-09-09 | 286911 | 37.73 | Completed | 2024-09-20 | Sukhridwin
9 | 260/0 | DD60+18 | 2024-09-11 | 1003256 | 129.341 | Completed. | 2024-10-31 | Ramjivan-02 | 34
10 | 270/2 | DA+3 | 2024-09-14 | 297143 | 39.459 | Completed. | 2024-10-28 | Senahul
11 | 164/7 | DA+0 | 2024-09-22 | 286911 | 37.73 | Completed | 2024-10-09 | Sukuriddne
12 | 257/2 | DA-3 | 2024-09-23 | 273608.93 | 36.044 | Completed | 2024-10-24 | Ghanshyam Mahto | 42
13 | 265/0 | DB2+3 | 2024-09-30 | 424198 | 56.863 | Completed. | 2024-10-31 | Thanu mahto
14 | 165/0 | DB2+0 | 2024-10-09 | 403998 | 54.418 | Completed. | 2024-10-28 | Sukuriddne
15 | 158A/0 | DD45+6 | 2024-10-23 | 650023 | 85.234 | Completed. | 2024-11-12 | Rahul Kumar | 23
16 | 262/1 | DA+0 | 2024-10-25 | 286911 | 37.73 | Completed. | 2024-11-07 | Ghanshyam Mahto
17 | 257/4 | DA+0 | 2024-10-29 | 286911 | 37.73 | Completed. | 2024-11-16 | Thanu mahto
18 | 165/3 | DA+6 | 2024-10-30 | 342192 | 44.728 | Completed. | 2024-11-15 | Sukhruddin | 35
19 | 254/0 | DB2+0 | 2024-11-04 | 403998 | 54.418 | Completed. | 2024-11-21 | Senahul
20 | 259/0 | DD60+18 | 2024-11-10 | 1003256 | 129.341 | Completed. | 2024-12-23 | Maa Construction | 29
21 | 268/0 | DD60+6 | 2024-11-10 | 719574 | 94.408 | Completed. | 2024-12-07 | Daulat Mahto | 29
22 | 155/3 | DA+3 | 2024-11-16 | 297143 | 39.459 | Completed. | 2024-11-22 | Rahul Kumar
23 | 189/0 | DB2+6 | 2024-11-22 | 480757 | 63.509 | Completed. | 2024-12-14 | Barkat Ali
24 | 191A/1 | DA-3 | 2024-11-22 | 273608.93 | 36.045 | Completed. | 2024-11-30 | Midhun
25 | 187/3 | DA+0 | 2024-11-22 | 286911 | 37.73 | Completed. | 2024-11-26 | Jwala
26 | 261/0 | DC2+18 | 2024-11-23 | 780122 | 97.934 | Completed. | 2024-12-28 | Ghanshyam mahto
27 | 264/0 | DC1+6 | 2024-11-17 | 559332 | 74.632 | Completed. | 2024-12-10 | Thanu Mahto
28 | 255/0 | DD60+3 | 2024-11-27 | 635073 | 84.299 | Completed. | 2024-12-21 | Senahul-01
29 | 188/0 | DB1+6 | 2024-11-27 | 480757 | 63.509 | Completed. | 2024-12-10 | Jwala
30 | 251/0 | DB1+9 | 2024-12-03 | 503365 | 65.757 | Completed. | 2024-12-28 | Senahul-02
31 | 272/1 | DA+9 | 2024-12-02 | 357181 | 46.623 | Completed. | 2024-12-16 | MJR
32 | 191/1 | DA+0 | 2024-12-09 | 286911 | 37.73 | Completed. | 2024-12-23 | Midhun
33 | 193/0 | DD60+6 | 2024-12-11 | 719574 | 94.408 | Completed. | 2024-12-21 | Jwala
34 | 270/1 | DA+0 | 2024-12-11 | 286911 | 37.73 | Completed. | 2024-12-24 | Daulat Mahto
35 | 272/0 | DC1+6 | 2024-12-11 | 559332 | 74.632 | Completed. | 2024-12-31 | Thanu mahto
36 | 197/4 | DA+0 | 2024-12-23 | 286911 | 37.73 | Completed. | 2024-12-29 | Jwala
37 | 266/0 | DB1+0 | 2024-12-28 | 403998 | 54.418 | Completed. | 2025-01-12 | Senahul-01
38 | 187/2 | DA-3 | 2024-12-26 | 273608.93 | 36.045 | Completed. | 2025-01-04 | Midhun
39 | 255/3 | DA+3 | 2024-12-26 | 297143 | 39.459 | Completed. | 2025-01-02 | Maa Construction
40 | 269/1 | DA+0 | 2024-12-28 | 286911 | 37.73 | Completed. | 2025-01-07 | Daulat Mahto
41 | 263/0 | DC2+0 | 2024-12-31 | 470077 | 64.254 | Completed. | 2025-01-13 | Ghanshyam Mahto
42 | 196/0 | DD60+9 | 2024-12-31 | 753337 | 98.839 | Completed. | 2025-01-10 | Jwala
43 | 271/5 | DA-3 | 2025-01-01 | 273608.93 | 36.045 | Completed. | 2025-01-11 | Thanu mahto
44 | 255/2 | DA+0 | 2025-01-03 | 286911 | 37.73 | Completed. | 2025-01-10 | Maa Construction
45 | 197/3 | DA+0 | 2025-01-07 | 286911 | 37.73 | Completed. | 2025-01-16 | Midhun
46 | 197/0 | DD60+9 | 2025-01-12 | 753337 | 98.836 | Completed. | 2025-01-22 | Jwala
47 | 257/1 | DA+0 | 2025-01-09 | 286911 | 37.73 | Completed. | 2025-01-17 | Daulat Mahto
48 | 269/2 | DA+6 | 2025-01-11 | 342192 | 44.728 | Completed. | 2025-01-19 | Maa Construction
49 | 272/5 | DB1+0 | 2025-01-13 | 403998 | 54.418 | Completed. | 2025-01-23 | Thanu mahto
50 | 262/0 | DD45+9 | 2025-01-18 | 680590 | 89.146 | Completed. | 2025-02-11 | Ghanshyam Mahto
51 | 272/3 | DA+3 | 2025-01-17 | 297143 | 39.459 | Completed. | 2025-02-06 | Tajirul
52 | 198/1 | DA+0 | 2025-01-17 | 286911 | 37.73 | Completed. | 2025-01-27 | Midhun
53 | 255/1 | DA+6 | 2025-01-19 | 342192 | 44.728 | Completed. | 2025-01-27 | Daulat Mahto
54 | 267/0 | DC1+9(2M RC) | 2025-01-21 | 585620 | 77.718 | Completed. | 2025-01-31 | Maa Construction
55 | 272/4 | DA+3 | 2025-01-25 | 297143 | 39.459 | Completed. | 2025-02-02 | Thanu mahto
56 | 272A/1 | DA+6 | 2025-01-24 | 342192 | 44.728 | Completed. | 2025-01-29 | Jwala
57 | 197/2 | DA+0 | 2025-01-29 | 286911 | 37.73 | Completed. | 2025-02-07 | Midhun
58 | 272/2 | DA-3 | 2025-01-30 | 273608.93 | 36.045 | Completed. | 2025-02-04 | Daulat Mahto
59 | 253/0 | DC1+0 | 2025-02-01 | 470077 | 64.254 | Completed. | 2025-02-17 | Senahul
60 | 272A/2 | DA+0 | 2025-01-30 | 286911 | 37.73 | Completed. | 2025-02-04 | Jwala
61 | 271/0 | DC1+0 | 2025-02-04 | 470077 | 64.254 | Completed. | 2025-02-13 | Thanu mahto
62 | 266/2 | DA+0 | 2025-02-04 | 286911 | 37.73 | Completed. | 2025-02-12 | Maa Construction
63 | 270A/0 | DC2+0 | 2025-02-05 | 470077 | 64.254 | Completed. | 2025-02-15 | Daulat Mahto
64 | 272A/3 | DA+0 | 2025-02-05 | 286911 | 37.73 | Completed. | 2025-02-09 | Jwala
65 | 272/7 | DA+9 | 2025-02-10 | 357181 | 46.623 | Completed. | 2025-03-07 | Tajirul |  |  | Mithun Gang join at 02-03-2025
66 | 270/6 | DA-3 | 2025-02-11 | 273608.93 | 36.045 | Completed. | 2025-02-17 | Mithun
67 | 250/1 | DA-3 | 2025-02-14 | 273608.93 | 36.045 | Completed. | 2025-02-24 | Ghanshyam Mahto
68 | 249/0 | DB2+0 | 2025-02-14 | 403998 | 54.418 | Completed. | 2025-02-26 | Maa Construction
69 | 271/2 | DA+0 | 2025-02-14 | 286911 | 37.73 | Completed. | 2025-02-21 | Thanu Mahto
70 | 270/7 | DA-3 | 2025-02-17 | 273608.93 | 36.045 | Completed. | 2025-02-23 | Daulat Mahto
71 | 274/0 | DC1+0 | 2025-02-17 | 470077 | 64.254 | Completed. | 2025-02-23 | Jwala
72 | 267A/0 | DC2+9(2M RC) | 2025-02-21 |  | 77.718 | Completed. | 2025-03-18 | Senahul
73 | 270/5 | DA+0 | 2025-02-20 | 286911 | 37.73 | Completed. | 2025-02-28 | Mithun
74 | 270/0 | DD45+0 | 2025-02-22 | 546238 | 72.238 | Completed. | 2025-03-16 | Anarul Haque
75 | 271/4 | DA-3 | 2025-02-22 | 273608.93 | 36.045 | Completed. | 2025-03-03 | Thanu Mahto
76 | 273/2 | DA+6 | 2025-02-24 | 342192 | 44.728 | Completed. | 2025-02-28 | Jwala
77 | 267A/1 | DA+0 | 2025-02-27 | 286911 | 37.73 | Completed. | 2025-03-05 | Daulat Mahto
78 | 171/0 | DD60+25(3M RC) | 2025-02-26 | 1099828 | 141.874 | Completed. | 2025-03-29 | Sukhriddin |  |  | Crane erection
79 | 249/2 | DA+0 | 2025-03-01 | 286911 | 37.73 | Completed. | 2025-03-09 | Maa Construction
80 | 270/4 | DA+0 | 2025-03-09 | 286911 | 37.73 | Completed. | 2025-03-28 | Mithun | 15
81 | 272A/6 | DA-3 | 2025-03-02 | 273608.93 | 36.045 | Completed. | 2025-03-05 | Jwala
82 | 272A/7 | DA-3 | 2025-03-06 | 273608.93 | 36.045 | Completed. | 2025-03-10 | Jwala
83 | 271/3 | DA-3 | 2035-03-04 | 273608.93 | 36.045 | Completed. | 2025-03-11 | Thanu Mahto
84 | 267A/2 | DA-3 | 2025-03-07 | 273608.93 | 36.045 | Completed. | 2025-03-15 | Daulat Mahto
85 | 249/3 | DA+0 | 2025-03-10 | 286911 | 37.73 | Completed. | 2025-03-18 | Maa Construction |  |  | After complete 02 days gang not interested to work.
86 | 272A/5 | DA+3 | 2025-03-11 | 297143 | 39.459 | Completed. | 2025-03-16 | Jwala
87 | 270/3 | DA-3 | 2025-03-19 | 273608.93 | 36.045 | Completed. | 2025-03-28 | Thanu mahto
88 | 252/0 | DC1+18 | 2025-03-18 | 780122 | 97.934 | Completed. | 2025-04-11 | Anarul Haque | 20 |  | 24
89 | 272A/4 | DA+0 | 2025-03-17 | 286911 | 37.73 | Completed. | 2025-03-20 | Jwala
90 | 272/6 | DA+3 | 2025-03-19 | 297143 | 39.459 | Completed. | 2025-03-30 | Daulat Mahto
91 | 272A/0 | DB1+18(2M RC) | 2025-04-03 | 670636 | 82.239 | Completed. | 2025-04-26 | Senahul | 34
92 | 271/1 | DA-3 | 2025-03-21 | 273608.93 | 36.045 | Completed. | 2025-03-25 | Jwala
93 | 250/0 | DD60+0 | 2025-03-21 | 604881 | 80.408 | Completed. | 2025-04-12 | Maa Construction | 16 |  | 22
94 | 269/0 | DD60+0 | 2025-03-26 | 604881 | 80.408 | Completed. | 2025-04-01 | Jwala
95 | 167/3 | DA+6 | 2025-03-28 | 342192 | 44.728 | Completed. | 2025-04-06 | Barkat Ali | 34 |  | 9
96 | 195/2 | DA+0 | 2025-04-01 | 286911 | 37.73 | Completed. | 2025-04-08 | Samirul | 24
97 | 195A/3 | DA+0 | 2025-03-30 | 286911 | 37.73 | Completed. | 2025-04-08 | Modina India | 22
98 | 198/0 | DC1+0 | 2025-04-01 | 470077 | 64.254 | Completed. | 2025-04-15 | Mithun-2 | 21
99 | 197/1 | DA+0 | 2025-04-01 | 286911 | 37.73 | Completed. | 2025-04-12 | Mithun-1 | 22
100 | 187/1 | DA+3 | 2025-04-03 | 297143 | 39.459 | Completed. | 2025-04-12 | Thanu mahto | 24
101 | 172/0 | DD60+25 | 2025-04-02 | 1099828 | 141.874 | Completed. | 2025-04-28 | Sukhriddin | 36 |  | Crane erection
102 | 198/2 | DA+0 | 2025-04-04 | 286911 | 37.73 | Completed. | 2025-04-12 | Daulat Mahto | 27 |  | 8
103 | 248/5 | DA+0 | 2025-04-01 | 286911 | 37.73 | Completed. | 2025-04-12 | SulenSarkar | 26
104 | 181/0 | DD45+18 | 2025-04-06 | 906755 | 112.424 | Completed. | 2025-04-27 | DK Verma | 26
105 | 178/0 | DD60+6 | 2025-04-06 | 719574 | 94.408 | Completed. | 2025-04-13 | Gouri Shankar | 27 |  | 7
106 | 273/1 | DA+6 | 2025-04-04 | 342192 | 44.728 | Completed. | 2025-04-09 | Jwala | 28
107 | 168/0 | DC1+0 | 2025-04-06 | 470077 | 64.254 | Completed. | 2025-04-16 | Rupesh | 22
108 | 189/1 | DA+0 | 2025-04-05 | 286911 | 37.73 | Completed. | 2025-04-11 | Dhaneshwar | 26 |  | 6
109 | 167/2 | DA+6 | 2025-04-08 | 342192 | 44.728 | Completed. | 2025-04-18 | Barkat Ali
110 | 195A/2 | DA+6 | 2025-04-11 | 342192 | 44.728 | Completed. | 2025-04-22 | Modina india
111 | 195/4 | DA+0 | 2025-04-09 | 286911 | 37.73 | Completed. | 2025-04-15 | Samirul
112 | 179/0 | DD60+0 | 2025-04-16 | 604881 | 80.408 | Completed. | 2025-04-22 | Gouri Shankar
113 | 190/0 | DD45+25 | 2025-04-18 | 994153 | 122.808 | Completed. | 2025-05-06 | Dhaneshwar |  |  | Crane erection
114 | 187/0 | DD60+25 | 2025-04-22 | 1099828 | 141.874 | Cage section is u/p. ROW |  | Thanu Mahto |  | ROW from 22-05-2025 | Crane erection
115 | 205/1 | DA-3 | 2025-04-11 | 273608.93 | 36.045 | Completed | 2025-04-16 | Jwala
116 | 182/0 | DD60+0 | 2025-04-28 | 604881 | 80.408 | Completed. | 2025-05-06 | DK Verma
117 | 192/0 | DC1+0 | 2025-04-13 | 470077 | 64.254 | Completed. | 2025-04-28 | MJR | 34
118 | 194/0 | DD60+6 | 2025-04-22 | 719574 | 94.408 | Completed. | 2025-05-15 | MJR-2
119 | 248/0 | DC2+9 | 2025-04-14 | 585620 | 77.718 | Completed. | 2025-04-30 | Anarul Haque
120 | 249/1 | DA+0 | 2025-04-13 | 286911 | 37.73 | Completed. | 2025-04-21 | SulenSarkar
121 | 167/0 | DD60+0 | 2025-04-18 | 604881 | 80.408 | Completed. | 2025-05-05 | Rupesh
122 | 195/1 | DA+6 | 2025-04-16 | 342192 | 44.728 | Completed. | 2025-04-25 | Mithun-1
123 | 248/4 | DA+3 | 2025-04-17 | 297143 | 39.459 | Completed. | 2025-05-05 | Rahim Khan-2 & MJR-1
124 | 205/0 | DD60+3 (2M RC) | 2025-04-18 | 635073 | 84.299 | Completed. | 2025-04-29 | Jwala
125 | 199/0 | DD45+18 | 2025-04-18 | 906755 | 112.424 | Completed. | 2025-05-22 | Mithun-2
126 | 191A/0 | DB2+0 | 2025-04-15 | 403998 | 54.418 | Completed. | 2025-04-22 | Rahul Kumar
127 | 181/2 | DA+0 | 2025-04-16 | 286911 | 37.73 | Completed. | 2025-04-22 | Rahim Khan-1
128 | 195/3 | DA+6 | 2025-04-18 | 342192 | 44.728 | Completed. | 2025-04-28 | Samirul
129 | 248/2 | DA+9 | 2025-04-17 | 357181 | 46.623 | Completed. | 2025-04-30 | Rahim Khan-3 & Sulen sarkar |  |  | Sulen sarkar
130 | 195A/0 | DB1+0 | 2025-04-22 | 403998 | 54.418 | Completed. | 2025-05-18 | Daulat Mahto |  | 1 | After lunch gang strike.
131 | 167/4 | DA+0 | 2025-04-20 | 286911 | 37.73 | Completed. | 2025-04-29 | Barkat Ali
132 | 248/6 | DA+0 | 2025-04-29 | 286911 | 37.73 | Completed. | 2025-05-09 | Senahul
133 | 195A/1 | DA+6 | 2025-04-24 | 342192 | 44.728 | Completed. | 2025-05-09 | Modina India
134 | 191/2 | DA-3 | 2025-04-23 | 273608.93 | 36.045 | Completed. | 2025-04-27 | Rahul Kumar
135 | 180/0 | DD45+9 | 2025-04-24 | 680590 | 89.146 | Completed. | 2025-05-03 | Gouri Shankar |  |  | Crane erection
136 | 181/1 | DA+0 | 2025-04-24 | 286911 | 37.73 | Completed. | 2025-04-30 | Rahim Khan-1
137 | 195/0 | DC2+0 | 2025-04-28 | 470077 | 64.254 | Completed. | 2025-05-11 | Mithun-1 |  |  | Crane erection
138 | 204/0 | DD60+9 | 2025-05-02 | 753337 | 98.836 | Completed. | 2025-05-11 | Jwala
139 | 191/3 | DA-3 | 2025-04-29 | 273608.93 | 36.045 | Completed. | 2025-05-04 | Rahul Kumar
140 | 195/5 | DA+6 | 2025-05-02 | 342192 | 44.728 | Completed. | 2025-05-11 | Samirul
141 | 168/2 | DA+0 | 2025-05-02 | 286911 | 37.73 | Completed. | 2025-05-11 | Sukhriddin
142 | 167/1 | DA+9 | 2025-05-04 | 357181 | 46.623 | Completed. | 2025-05-19 | Barkat Ali
143 | 217A/1 | DA+3 | 2025-05-04 | 297143 | 39.459 | Completed. | 2025-05-18 | Rahim Khan-3
144 | 181/4 | DA+0 | 2025-05-03 | 286911 | 37.73 | Completed. | 2025-05-11 | Rahim Khan-1
145 | 248/1 | DA+9 | 2025-05-06 | 357181 | 46.623 | Completed. | 2025-05-18 | Sulen Sarkar & DK Verma |  |  | 02days no work due to strike.
146 | 177/0 | DD60+0 | 2025-05-06 | 604881 | 80.408 | Completed. | 2025-05-18 | Gouri Shankar
147 | 209/0 | DC1+0 | 2025-05-08 | 470077 | 64.254 | Completed. | 2025-05-16 | Rahul Kumar
148 | 248/3 | DA+6 | 2025-05-09 | 342192 | 44.728 | Completed. | 2025-05-20 | MJR-1
149 | 172/1 | DA+3 | 2025-05-16 | 297143 | 39.459 | Ist section done.Collapse on 24-05-2025 |  | Rupesh |  | 1 | 1-S/D not avail.
150 | 247/1 | DA+0 | 2025-05-11 | 286911 | 37.73 | Completed. | 2025-05-19 | Sulen sarkar
151 | 211/1 | DA+0 | 2025-05-13 | 286911 | 37.73 | Completed. | 2025-05-18 | Dhaneshwar |  |  | Crane
152 | 247/4 | DA+0 | 2025-05-13 | 286911 | 37.73 | Completed | 2025-06-26 | Senahul & Modina India-3 |  | 4 | ROW from 19-05-2025-04-06-2025. Loc. Cleared on 23-09-2025.Modina Indian -3 engaged on 23-09-2025.
153 | 168/1 | DA-3 | 2025-05-13 | 273608.93 | 36.045 | Completed. | 2025-05-20 | Rahim Khan-1
154 | 205/2 | DA+3 | 2025-05-15 | 297143 | 39.459 | Completed. | 2025-05-21 | Jwala
155 | 210/0 | DB2+18 | 2025-05-17 | 670636 | 82.239 | 3rd section is u/p.ROW |  | Rahul Kumar |  |  | ROW from 23-05-2025
156 | 191/0 | DD45+25 | 2025-06-02 | 994153 | 122.808 | Completed. | 2025-08-26 | Daulat Mahto |  | 1 | 1-Approach road issues
157 | 181/3 | DA+0 | 2025-05-19 | 286911 | 37.73 | Completed. | 2025-05-24 | Gouri Shankar
158 | 169/0 | DD45+18 | 2025-05-24 | 906755 | 112.424 | Completed. | 2025-06-08 | DK Verma
159 | 175/0 | DD45+0 | 2025-05-28 | 546238 | 72.238 | Completed. | 2025-06-05 | Gouri Shankar
160 | 172/2 | DA+6 | 2025-05-29 | 342192 | 44.728 | Completed. | 2025-06-06 | Thanu Mahto
161 | 174/0 | DD60+18 | 2025-06-01 | 1003256 | 129.341 | Ist section is u/p.ROW |  | Mithun |  | 5 | ROW since 04-06-2025-06-06-2025 & 09-06-2025-12-06-2025. Then gang shifted to 153/0.
162 | 175/2 | DA+0 | 2025-06-08 | 286911 | 37.73 | Completed. | 2025-07-20 | Senahul,Sulen Sarkar & MJR |  |  | Sulen Sarkar join on 02-07-2025.Sulen Sarkar demobilized on 05-07-2025.And MJR join on 08-07-2025.
163 | 174/1 | DB1+0 | 2025-06-06 | 403998 | 54.418 | Completed. | 2025-06-13 | Gouri Shankar
164 | 176/0 | DD60+0 | 2025-06-11 | 604881 | 80.408 | Completed | 2025-07-04 | DK Verma
165 | 275/0 | DD45+0 | 2025-08-06 | 546238 | 72.238 | Body completed. | 2025-09-14 | Modina India
166 | 276/0 | DD60+0 | 2025-08-26 |  | 80.408 | Completed | 2025-10-04 | Kamruddin | 28
167 | 246/0 | DD60+0 | 2025-09-19 |  | 80.408 | Completed. |  | Rahul Kumar | 34
168 | 242/0 | DB1+0 | 2025-09-24 |  | 54.418 | Completed |  | Sakia Khatun | 21
169 | 237/3 | DA-3 | 2025-09-24 |  | 36.045 | Completed | 2025-10-03 | Sukhrridin | 30 |  | ROW.
170 | 215/0 | DB+6 | 2025-09-13 |  | 63.509 | Completed | 2025-10-06 | Prayag Mahto | 39
171 | 237/5 | DA-3 | 2025-09-24 |  | 36.045 | Completed | 2025-10-06 | Muni Bibi | 32
172 | 247/3 | DA-3 | 2025-03-14 |  | 36.405 | Completed | 2025-10-06 | Didar Electricals (PGCIL) | 26 |  | ROW from 19-05-2025. Loc. Cleared on 23-09-2025.Gang Dildar Electrical enganged on 23-09-2025
173 | 157/3 | DA+0 | 2025-07-23 |  | 37.73 | Derrick pole installation and dewatering WIP |  | Mithun Kumar (VNTL) | 33 |  | ROW
174 | 202/0 | DD60+55 |  |  | 226.737 | Gang shifting U/P |  | Nasirudin 2 | 27
175 | 203/0 | DD60+55 |  |  | 226.737 | Gang shifting U/P |  | Prayag Mahto | 30
176 | 206/0 | DD60+25 |  |  | 141.874 | No work due to ROW |  | Jwala Singh | 27 |  | ROW since 31-05-2025 & Row Cleared On 3-10-2025
177 | 218/0 | DD60+0 |  |  | 80.408 | Gang shifting U/P |  | Emadur | 27 | 3 | 02 days idle at 214/0 due to ROW
178 | 217A/2 | DA+0 | 2025-10-04 |  | 37.73 | 2nd section is u/p. |  | Manirul Haque / Rulu-2 | 23
179 | 223/1 | DA+0 | 2025-10-06 |  | 37.73 | 2nd section U/P |  | Teklal Mahto | 26
180 | 225/1 | DA+6 | 2025-10-08 |  | 44.728 | Gang and T&P shifting completed and material shifting U/P |  | Muni Bibi | 30 |  | ROW
181 | 224/0 | DC+6 | 2025-10-05 |  | 74.632 | 2nd section completed and 3rd section U/P |  | Nasirudin | 20 | 2 | ROW since 10-09-2025
182 | 229/3 | DA+0 | 2025-10-05 |  | 37.73 | 2nd section U/P and work stopped due to not availibility of 11 kv line shutdown |  | Modina India-3 (PGCIL) | 28 |  | ROW
183 | 229/5 | DA+0 | 2025-10-08 |  | 37.73 | 1st section U/P |  | Dildar Electrical-3 | 27 |  | ROW
184 | 230/0 | DD60+0 |  |  | 80.408 | Materials shifting and ground assembling is u/p. |  | Javir Hossen | 16 |  | ROW
185 | 231/0 | DD60+6 |  |  | 94.408 | Material sorting and ground assembling U/P |  | Manirul Haque / Rulu-1 | 24 |  | ROW
186 | 233/0 | DD45+0 | 2025-10-06 |  | 72.238 | Ist section is completed |  | Anita Devi | 45
187 | 234/0 | DD45+0 | 2025-09-18 |  | 72.238 | X-arm completed. Erection completed | 2025-10-08 | MD Akhtar | 34
188 | 235/0 | DC2+3 |  |  | 66.268 |  |  | MD Akhtar
189 | 236/0 | DB+0 | 2025-09-23 |  | 54.418 | 3rd Section completed and bottom section WIP |  | Subhash | 28
190 | 237/0 | DD45+9 | 2025-10-06 |  | 89.146 | Ist section is u/p. |  | Rupesh | 35
191 | 237/1 | DA+0 | 2025-10-07 |  | 37.73 | Ist section is completed and 2nd section u/p. |  | Muni Bibi-2 | 24
192 | 237/2 | DA-3 | 2025-10-05 |  | 36.045 | 2nd section U/P |  | Modina India-1&4 (PGCIL) | 36
193 | 237/4 | DA+0 | 2025-10-05 |  | 37.73 | Bottom section completed and middle section U/P |  | Sukruddin | 34
194 | 237/6 | DA+3 | 2025-10-03 |  | 39.4589 | Ist section is completed and 2nd section u/p. |  | Dildar Electrical-2_PGCIL | 29
195 | 239/0 | DD60+25 |  |  | 141.874 | Gang shifting U/P |  | Laldev | 28
196 | 241/0 | DB2+9 |  |  | 65.757 | Material shifting and ground assembling U/P |  | SakiLa Khatun | 26
197 | 242/2 | DA-3 | 2025-10-03 |  | 36.045 | 3rd Section completed and bottom section WIP |  | Gokul-1 | 26 |  | ROW from 21-05-2025 & ROW Resolved On 3-10-2025
198 | 243/0 | DB+9 | 2025-10-07 |  | 65.757 | 1st section U/P |  | Satish Kumar | 23
199 | 244/0 | DC+9 | 2025-10-05 |  | 77.718 | 2nd section completed |  | Jaman Mahto-1 (Ratna Devi) | 38
200 | 244/1 | DB+9 | 2025-10-06 |  | 65.757 | 2nd section U/P |  | Gokul Sarkar-2 | 20 |  | ROW since 07-09-2025-17-09-2025
201 | 245/1 | DA+0 | 2025-09-05 |  | 37.73 | Middle section completed and top section U/P |  | Senaul | 32 | 3 | ROW from 19-05-2025 to 23-05-2025.Gang moved to 169/0.
202 | 247/0 | DD60+0 | 2025-10-08 |  | 80.408 | 1st section U/P |  | Rahul Kumar | 30 | 4 | From 16-05-2025 idle due to ROW.
203 | 247/2 | DA+3 |  |  | 39.4589 | Gang shifting completed and material shifting U/P |  | Didar Electricals (PGCIL) | 29
204 | 273/0 | DB+0 | 2025-09-20 |  | 54.418 | Bottom section is completed and middle section U/P |  | Modina India-2 (PGCIL) | 30
205 | 229/0 | DD60+18 |  |  | 129.341 | Gang shifting U/P |  | PC Construction 1 | 35
206 | [5 empty] | Gang reached at store
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
| 266/1 | DB1+6 | 2025-01-13 | 480757 | 63.509 | Completed. | 2025-01-29 | Senahul
214

## Balance Erection
Erection Balance Location Status of ANTL Project | [13 empty] | Status of loaction as per KEC
Sr. No. | Loc. No. | TOT | Village | Tehsil | District | Tower Weight | Engaged Gang Date | Start Date | Status | ROW cleared Date | Comp Date | Sub-Contractor | Remarks | Approach | Water Logging
1 | 102/0 | DD45+35 | DABKA | PADRA | VADODARA | 156.901 |  |  | Clear |  |  |  | Waterlogged | Clear | Waterlogged
2 | 103/0 | DD45+35 | DABKA | PADRA | VADODARA | 156.901 |  |  | Pending |  |  |  | Foundation u/p. | Not approachable | Waterlogged
3 | 154/0 | DD45+25 | Kukurwada | Bharuch | Bharuch | 122.8082 |  |  | Pending |  |  |  | Foundation u/p. | Not approachable | Waterlogged
4 | 154/1 | DD45+25 | Kukurwada | Bharuch | Bharuch | 122.8082 |  |  | Clear |  |  |  |  | Not approachable
5 | 157/3 | DA+0 | Pungam | Ankleshwar | Bharuch | 37.73 |  |  | WIP |  |  |  | 2nd section is u/p.
6 | 159/2 | DCT+0 | Boidra | Ankleshwar | Bharuch | 64.2538 |  |  | Clear |  |  |  | Approach road issues. |  | Waterlogged
7 | 160/0 | DD60+18 | Umarwada | Ankleshwar | Bharuch | 129.341 |  |  | Clear |  |  |  | Waterlogged |  | Waterlogged
8 | 165/4 | DD45+9 | Haturan | Mangrol | Surat | 89.1461 |  |  | Pending |  |  |  |  | Foundation WIP
9 | 165/5 | DD45+9 | Haturan | Mangrol | Surat | 89.1461 |  |  | Pending |  |  |  |  | Foundation Pending
10 | 166/0 | DD60+6 | Haturan | Mangrol | Surat | 94.4077 |  |  | Clear |  |  |  |  | Not approachable
11 | 167/0 | DD60+6 | Haturan | Mangrol | Surat | 94.4077 |  |  | Pending |  |  |  |  | Foundation Pending
12 | 167/1 | DD60+0 | Haturan | Mangrol | Surat | 80.408 |  |  | Pending |  |  |  |  | Foundation Pending
13 | 172/1 | DA+3 | Mahuvej | Mangrol | Surat | 39.4589 |  |  | Pending |  |  | MJR | Dismantling completed | Recasting
14 | 173/0 | DD60+25 | Mahuvej | Mangrol | Surat | 141.874 |  |  | WIP
15 | 174/0 | DD60+18 | Mahuvej | Mangrol | Surat | 129.341 |  |  | ROW |  |  |  | Ist section is u/p. | Not approachable
16 | 175/1 | DA+0 | Kosamba | Mangrol | Surat | 37.73 |  |  | ROW |  |  |  |  | Clear
17 | 182A/0 | DD45+6 | Valecha | Mangrol | Surat | 85.2338 |  |  | ROW |  |  |  |  | 300 m headloading
18 | 183/0 | DD60+25 | Valecha | Mangrol | Surat | 141.874 |  |  | ROW |  |  |  |  | 300 m headloading
19 | 184/0 | DD60+25 | Valecha | Mangrol | Surat | 141.874 |  |  | ROW |  |  |  |  | Not approachable
20 | 184/1 | DB1+6 | Valecha | Mangrol | Surat | 63.509 |  |  | ROW |  |  |  |  | Clear
21 | 185/0 | DC2+0 | Valecha | Mangrol | Surat | 64.2538 |  |  | ROW |  |  |  |  | Not approachable
22 | 185/1 | DA+9 | Valecha | Mangrol | Surat | 46.6235 |  |  | ROW |  |  |  |  | Not approachable
23 | 186/0 | DD60+35 | Valecha | Mangrol | Surat | 172.151 |  |  | ROW |  |  |  |  | Not approachable
24 | 187/0 | DD60+25 | Panetha | Mangrol | Surat | 141.874 |  |  | ROW |  |  |  | 3rd section . | Clear
25 | 200/0 | DB2+18 | Ghala | Kamrej | Surat | 82.2388 |  |  | Clear |  |  |  |  | 600 m headloading
26 | 201/0 | DC2+18 | Ghala | Kamrej | Surat | 97.9336 |  |  | ROW |  |  |  |  | 200 m headloading
27 | 201/1 | DD60+9 | Ghala | Kamrej | Surat | 98.8356 |  |  | ROW |  |  |  |  | Clear
28 | 202/0 | DD60+55 | Ghala | Kamrej | Surat | 226.737 |  |  | WIP |  |  |  | Crane erection | Clear
29 | 203/0 | DD60+55 | Jior | Kamrej | Surat | 226.737 |  |  | WIP |  |  |  | Crane erection | Clear
30 | 203/1 | DD60+6 | Jior | Kamrej | Surat | 94.4077 |  |  | ROW |  |  |  |  | Clear
31 | 206/0 | DD60+25 | Dhatav | Kamrej | Surat | 141.874 |  |  | WIP |  |  |  | 3rd section.
32 | 208/0 | DD60+25 | Netrang | Kamrej | Surat | 141.874 |  |  | Clear |  |  |  |  | Not approachable
33 | 209/1 | DA+3 | Netrang | Kamrej | Surat | 39.459 |  |  | ROW |  |  |  |  | Clear
34 | 210/0 | DB2+18 | Netrang | Kamrej | Surat | 82.239 |  |  | Clear |  |  |  | 3rd section . | 70 m headloading
35 | 211/0 | DB1+9 | Netrang | Kamrej | Surat | 65.757 |  |  | ROW |  |  |  |  | 200 m headloading
36 | 211/2 | DA+0 | Netrang | Kamrej | Surat | 37.73 |  |  | ROW |  |  |  |  | 30 m headloading
37 | 211A/0 | DB2+0 | Dharutha | Kamrej | Surat | 54.418 |  |  | ROW |  |  |  |  | 70 m headloading
38 | 211A/1 | DA-3 | Dharutha | Kamrej | Surat | 36.045 |  |  | ROW |  |  |  |  | 400 m headloading
39 | 211A/2 | DA+0 | Jat Barthana | Kamrej | Surat | 37.73 |  |  | ROW |  |  |  |  | Clear
40 | 212/0 | DD45+3 | Asta | Kamrej | Surat | 75.452 |  |  | ROW |  |  |  |  | 50 m headloading
41 | 213/0 | DD60+3 | Asta | Kamrej | Surat | 84.2993 |  |  | ROW |  |  |  |  | Clear
42 | 213/1 | DA+0 | Asta | Kamrej | Surat | 37.73 |  |  | ROW |  |  |  |  | 10 m headloading
43 | 214/0 | DD45+0 | Asta | Kamrej | Surat | 72.238 |  |  | ROW |  |  |  |  | Clear
44 | 214/1 | DA+6 | Asta | Kamrej | Surat | 44.728 |  |  | ROW |  |  |  |  | 230 m headloading
45 | 215/1 | DA+9 | Asta | Kamrej | Surat | 46.623 |  |  | ROW |  |  |  |  | 200 m headloading
46 | 216/0 | DB2+25 | Segva | Kamrej | Surat | 91.083 |  |  | ROW |  |  |  |  | 200 m headloading
47 | 217/0 | DD45+25 | Segva | Kamrej | Surat | 122.808 |  |  | ROW |  |  |  |  | Building construction
48 | 217A/0 | DB1+3 | Segva | Kamrej | Surat | 56.863 |  |  | ROW |  |  |  |  | Clear
49 | 217A/2 | DA+0 | Segva | Kamrej | Surat | 37.73 |  |  | WIP
50 | 218/0 | DD60+0 | Segva | Kamrej | Surat | 80.408 |  |  | WIP |  |  |  |  | Clear
51 | 218/1 | DA+3 | Segva | Kamrej | Surat | 39.459 |  |  | Clear |  |  |  | Water logged |  | Water logged
52 | 219/0 | DC2+18 | Pali | Kamrej | Surat | 97.934 |  |  | ROW |  |  |  |  | Clear
53 | 220/0 | DD45+9 | Pali | Kamrej | Surat | 89.1461 |  |  | ROW |  |  |  |  | Clear | 5 days
54 | 220/1 | DA+3 | Pali | Kamrej | Surat | 39.459 |  |  | ROW |  |  |  |  | not approachable
55 | 221/0 | DD60+18 | Pali | Kamrej | Surat | 129.341 |  |  | ROW |  |  |  |  | 100 M headloading
56 | 222/0 | DD60+25 | Mota | Bardoli | Surat | 141.874 |  |  | ROW |  |  |  |  | Clear
57 | 222/1 | DB1+3 | Mota | Bardoli | Surat | 56.863 |  |  | ROW |  |  |  |  | Sugarcane cutting required
58 | 223/0 | DC1+0 | Mota | Bardoli | Surat | 64.254 |  |  | ROW |  |  |  |  | Sugarcane cutting required
59 | 223/1 | DA+0 | Mota | Bardoli | Surat | 37.73 |  |  | WIP | 2025-09-23
60 | 223/2 | DA+0 | Mota | Bardoli | Surat | 37.73 |  |  | ROW |  |  |  |  | Sugarcane cutting required
61 | 223/3 | DA+0 | Mota | Bardoli | Surat | 37.73 |  |  | ROW |  |  |  |  | Sugarcane cutting required
62 | 224/0 | DC2+6 | Mota | Bardoli | Surat | 74.632 |  |  | WIP | 2025-09-23
63 | 225/0 | DD60+0 | Mota | Bardoli | Surat | 80.408 |  |  | Clear |  |  |  |  | Clear
64 | 225/1 | DA+6 | Mota | Bardoli | Surat | 44.728 |  |  | WIP
65 | 226/0 | DC2+0 | Mota | Bardoli | Surat | 64.254 |  |  | ROW |  |  |  |  | Sugarcane cutting required
66 | 227/0 | DB1+6 | Mota | Bardoli | Surat | 63.509 |  |  | ROW |  |  |  |  | Not approachable | 5 days
67 | 228/0 | DD60+25 | Mota | Bardoli | Surat | 141.874 |  |  | ROW |  |  |  |  | Clear | Waterlogged
68 | 229/0 | DD60+18 | Mota | Bardoli | Surat | 129.341 |  |  | WIP
69 | 229/1 | DB1+6 | Umrakh | Bardoli | Surat | 63.509 |  |  | ROW |  |  |  |  | Not approachable
70 | 229/2 | DA+6 | Umrakh | Bardoli | Surat | 44.728 |  |  | ROW |  |  |  |  | Not approachable
71 | 229/3 | DA+0 | Umrakh | Bardoli | Surat | 37.73 |  |  | WIP | 2025-09-23 |  | Modina India-3
72 | 229/4 | DA+0 | Umrakh | Bardoli | Surat | 37.73 |  |  | ROW |  |  |  |  | Clear
73 | 229/5 | DA+0 | Gangpore | Palsana | Surat | 37.73 |  |  | WIP | 2025-09-23
74 | 230/0 | DD60+0 | Gangpore | Palsana | Surat | 80.408 |  |  | WIP | 2025-09-17
75 | 231/0 | DD60+6 | Gangpore | Palsana | Surat | 94.4077 |  |  | WIP | 2025-09-23
76 | 232/0 | DD60+3 | Gangpore | Palsana | Surat | 84.2993 |  |  | ROW |  |  |  |  | Clear
77 | 233/0 | DD45+0 | Jetpor | Palsana | Surat | 72.238 |  |  | WIP | 2025-09-23
78 | 235/0 | DC2+3 | Barasadi | Palsana | Surat | 66.268 |  |  | WIP | 2025-10-06
79 | 236/0 | DB2+0 | Barasadi | Palsana | Surat | 54.418 | 2025-09-17 |  | WIP | 2025-09-17 |  | Modina India
80 | 237/0 | DD45+9 | Barasadi | Palsana | Surat | 89.1461 |  |  | WIP | 2025-09-23
81 | 237/1 | DA+0 | Barasadi | Palsana | Surat | 37.73 |  |  | WIP | 2025-09-23
82 | 237/2 | DA-3 | Barasadi | Palsana | Surat | 36.045 |  |  | WIP | 2025-09-23
83 | 237/4 | DA+0 | Barasadi | Palsana | Surat | 37.73 | 2025-09-24 |  | WIP | 2025-09-23 |  | Anil Marandi
84 | 237/6 | DA+3 | Dhamdod | Palsana | Surat | 39.459 |  |  | WIP | 2025-09-23
85 | 239/0 | DD60+25 | Dhamdod | Palsana | Surat | 141.874 |  |  | WIP | 2025-09-23 |  |  | Gang shifting U/P | Not approachable
86 | 240/0 | DD60+25 | Ena | Palsana | Surat | 141.874 |  |  | Clear | 2025-09-23 |  |  | Approach road issues. | Not approachable
87 | 241/0 | DB2+9 | Ena | Palsana | Surat | 65.757 |  |  | WIP | 2025-09-23
88 | 242/1 | DA-3 | Ena | Palsana | Surat | 36.045 |  |  | Clear |  |  |  | Approach road issues. | Not approachable
89 | 242/2 | DA-3 | Ena | Palsana | Surat | 36.045 |  |  | WIP
90 | 242/3 | DA-3 | Ena | Palsana | Surat | 36.045 |  |  | Clear | 2025-09-23 |  |  | Approach road issues. | Not approachable
91 | 243/0 | DB1+9 | Ena | Palsana | Surat | 65.757 |  |  | WIP
92 | 244/0 | DC1+9 | Ena | Palsana | Surat | 77.718 |  |  | WIP | 2025-09-23
93 | 244/1 | DB1+9 | Ghaluda | Palsana | Surat | 65.757 |  |  | WIP | 2025-09-23
94 | 245/0 | DD45+0 | Bhutpor | Palsana | Surat | 72.238 |  |  | ROW |  |  |  |  | Not approachable
95 | 245/1 | DA+0 | Bhutpor | Palsana | Surat | 37.73 |  | 2025-09-05 | WIP |  |  | Arjun
96 | 247/0 | DD60+0 | Kanav | Palsana | Surat | 80.408 |  |  | WIP | 2025-09-17
97 | 247/2 | DA+3 | Kanav | Palsana | Surat | 39.459 |  |  | WIP
98 | 273/0 | DB2+0 | Nimlai | Jalalpore | Navsari | 54.418 |  |  | WIP |  |  | Modina India
[5 empty] | Total | 7893.0013
Summary
|  |  | ROW | 45
|  |  | Clear | 13
|  |  | WIP | 33
|  |  | Pending | 7
|  |  | Total | 98

## Striging-VDRA
Stringing Part-I (Vadodara Section)
Sr. No. | Section | Length (M) | PO Length | FS Length | Manual/TSE | Start Date | Status | Cumulative Status | Completion Date | Sub-Contractor name | Manpower | Remarks
1 | 112/0-113/0 | 0.376 | 0.376 | 0.376 | Manual | 2024-08-12 | Completed | Completed. | 2024-08-19 | Muslaahudin
2 | 106/0-106A/0 | 0.411 | 0.411 | 0.411 | Manual | 2025-02-02 | Completed. | Completed. | 2025-02-15 | Muslaahudin
3 | 106A/0-106B/0 | 2.016 | 2.016 | 2.016 | TSE | 2025-01-28 | Completed. | Compeleted. | 2025-02-06 | Muslaahudin
4 | 106B/0- 107/0 | 1.148 | 1.148 | 1.148 | TSE | 2024-11-15 | Completed. | Completed. | 2024-11-24 | Muslaahudin
5 | 107/0-108/0 | 0.559 | 0.559 | 0.559 | Manual | 2024-10-20 | Completed | Completed. | 2024-11-07 | Muslaahudin
6 | 108/0-109/0 | 0.277 | 0.277 | 0.277 | Manual | 2024-10-10 | Completed | Final sag done. | 2024-10-28 | Muslaahudin
7 | 109/0-110/0 | 0.342 | 0.342 | 0.342 | Manual | 2024-08-20 | Completed | Completed. | 2024-10-13 | Muslaahudin
8 | 110/0-111/0 | 0.312 | 0.312 | 0.312 | Manual | 2024-09-11 | Completed | Completed. | 2024-10-06 | Muslaahudin
9 | 111/0-112/0 | 0.342 | 0.342 | 0.342 | Manual | 2024-09-23 | Completed | Completed. | 2024-10-06 | Muslaahudin
10 | 113/0-114/0 | 0.297 | 0.297 | 0.297 | Manual | 2024-09-24 | Completed | Completed. | 2024-10-07 | Gokul Sarkar
11 | 114/0-115/0 | 0.374 | 0.374 | 0.374 | Manual | 2024-12-25 | Completed. | Completed. | 2025-01-02 | Muslaahudin
12 | 115/0-116/0 | 0.226 | 0.226 | 0.226 | Manual | 2024-12-25 | Completed. | Completed. | 2025-01-02 | Muslaahudin
13 | 116/0- 116A/0 | 0.243 | 0.243 | 0.243 | Manual | 2024-09-24 | Completed | Completed. | 2024-10-27 | Gokul Sarkar
14 | 116A/0-116B/0 | 0.675 | 0.675 | 0.675 | Manual | 2024-11-03 | Completed. | Completed. | 2025-01-13 | Muslaahudin
15 | 116B/0-117/0 | 0.436 | 0.436 | 0.436 | Manual | 2024-11-14 | Completed. | Completed. | 2024-12-24 | Zahirul+Yakub
16 | 117/0-118/0 | 0.285 | 0.285 | 0.285 | Manual | 2024-11-09 | Completed. | Completed. | 2024-12-20 | Zahirul
17 | 118/0- 119/0 | 0.294 | 0.294 | 0.294 | Manual | 2024-11-09 | Completed. | Completed. | 2024-12-03 | Zahirul
18 | 119/0-120/0 | 1.373 | 1.373 | 1.373 | TSE | 2024-11-09 | Completed. | Completed. | 2024-12-22 | Gokul Sarkar
19 | 120/0-121/0 | 0.265 | 0.265 | 0.265 | Hotline | 2024-11-02 | Completed. | Completed. | 2025-01-01 | Dharvendra+Yakub
20 | 121/0-122/0 | 0.525 | 0.525 | 0.525 | Manual | 2024-11-01 | Completed | Completed. | 2024-11-19 | Gokul Sarkar
21 | 122/0-123/0 | 0.328 | 0.328 | 0.328 | Manual | 2024-11-19 | Completed. | Completed. | 2024-11-30 | Dharvendra
22 | 123/0-124/0 | 0.843 | 0.843 | 0.843 | Manual | 2024-11-09 | Completed. | Completed. | 2025-01-06 | Zahirul
23 | 124/0-124A/0 | 0.395 | 0.395 | 0.395 | Manual | 2024-12-10 | Completed. | Completed. | 2025-02-19 | Enamul Haque
| 124A/0-124A/1 | 0.253 | 0.253 | 0.253 | Hotline | 2025-02-15 | Completed. | Completed. | 2025-02-19 | Dharvendra
| 124A/1-125/0 | 0.203 | 0.203 | 0.203 | Manual | 2025-02-15 | Completed. | Completed. | 2025-02-19 | Dharvendra
25 | 125/0-125A/0 | 0.401 | 0.401 | 0.401 | Manual |  | Completed. | Completed. | 2025-02-07 | Enamul Haque
26 | 125A/0-126/0 | 0.38 | 0.38 | 0.38 | Manual | 2025-01-16 | Completed. | Completed. | 2025-02-05 | Enamul Haque
27 | 126/0-127/0 | 0.808 | 0.808 | 0.808 | Manual | 2025-01-04 | Completed. | Completed. | 2025-01-24 | Zahirul
28 | 127/0-128/0 | 2.399 | 2.399 | 2.399 | TSE | 2024-11-08 | Completed. | Completed. | 2025-01-19 | Muslaahudin
29 | 128/0-129/0 | 0.253 | 0.253 | 0.253 | Manual | 2025-02-10 | Completed. | Completed. | 2025-02-12 | Alamin Construction
30 | 129/0-129A/0 | 0.305 | 0.305 | 0.305 | Manual | 2025-02-10 | Completed. | Completed. | 2025-02-12 | Alamin Construction
31 | 129A/0-130/0 | 1.182 | 1.182 | 1.182 | TSE | 2024-11-16 | Completed. | Completed. | 2024-11-18 | Rejaul
32 | 130/0-131/0 | 2.041 | 2.041 | 2.041 | TSE | 2025-03-03 | Completed. | Completed. | 2025-03-10 | Muslaahudin
33 | 131/0-132/0 | 0.236 | 0.236 | 0.236 | Hotline | 2025-03-06 | Completed. | Completed. | 2025-03-10 | Dharvendra
34 | 132/0-133/0 | 1.28 | 1.28 | 1.28 | TSE | 2025-01-12 | Completed. | Completed. | 2025-01-24 | Rejaul
35 | 133/0-133A/0 | 2.267 | 2.267 | 2.267 | TSE | 2024-10-17 | Completed. | Completed. | 2024-11-07 | Rejaul | 18
36 | 133A/0-134/0 | 2.037 | 2.037 | 2.037 | TSE | 2024-12-03 | Completed. | Completed. | 2025-01-04 | Rejaul
37 | 134/0-135/0 | 0.235 | 0.235 | 0.235 | Hotline |  | Completed. | Completed. | 2025-03-22
38 | 135/0-135A/0 | 2.998 | 2.998 | 2.998 | TSE | 2025-03-21 | Completed. | Completed. | 2025-05-01 | Rafikul Alam Construction
39 | 135A/0-135A/1 | 0.34 | 0.34 | 0.34 | Manual | 2025-01-20 | Completed. | Completed. | 2025-02-14 | Matirul | 26
40 | 135A/1-135A/2 | 0.452 | 0.452 | 0.452 | Manual | 2025-01-29 | Completed. | Completed. | 2025-02-16 | Matirul+Rejaul
41 | 135A/2-135B/0 | 2.234 | 2.234 | 2.234 | TSE | 2025-02-04 | Completed. | Completed. | 2025-02-14 | Matirul
42 | 135B/0-136/0 | 2.989 | 2.989 | 2.989 | TSE | 2025-01-04 | Completed. | Completed. | 2025-02-14 | Matirul
43 | 136/0-137/0 | 0.426 | 0.426 | 0.426 | Hotline | 2025-03-26 | Completed. | Completed. | 2025-04-01 | Dharvendra | 26
44 | 137/0-137A/0 | 2.827 | 2.827 | 2.827 | TSE | 2025-03-05 | Completed. | Completed. | 2025-04-01 | Rafikul Alam Construction | 18
45 | 137A/0-138/0 | 2.729 | 2.729 | 2.729 | TSE |  | Completed. | Completed. | 2025-03-04 | Alamin Construction | 15
47 | 138/0-139/0 | 1.238 | 1.238 | 1.238 | TSE |  | Completed. | Completed. | 2025-03-04 | Enamul Haque
48 | 139/0-139A/0 | 1.211 | 1.211 | 1.211 | Machine | 2025-03-02 | Completed. | Completed. | 2025-03-09 | SK Zenarul
49 | 139A/0-140/0 | 0.427 | 0.427 | 0.427 | Manual | 2025-03-02 | Completed. | Completed. | 2025-03-13 | SK Zenarul
50 | 140/0-141/0 | 0.249 | 0.249 | 0.249 | Manual | 2025-05-22 | Completed. | Completed. | 2025-05-23 | Rafikul alam & Enamul
51 | 141/0-142/0 | 1.565 | 1.565 | 1.565 | TSE | 2025-04-05 | Completed. | Completed. | 2025-04-13 | Alam Construction
52 | 142/0-143/0 | 0.223 | 0.223 | 0.223 | Manual | 2025-03-18 | Completed. | Completed. | 2025-03-18 | Enamal Haque
53 | 143/0-143A/0 | 0.393 | 0.393 | 0.393 | Manual | 2025-03-08 | Completed. | Completed. | 2025-03-21 | Alamin Construction |  | TSE-1
54 | 143A/0-143A/2 | 0.841 | 0.841 | 0.841 | Manual | 2025-03-19 | Completed. | Completed. | 2025-03-26 | Alam Construction
55 | 143A/2-143A/3 | 0.413 | 0.413 | 0.413 | Manual | 2025-03-23 | Completed. | Completed. | 2025-03-26 | Enamul Haque
57 | 143A/3-144/0 | 1.246 | 1.246 | 1.246 | TSE | 2025-03-18 | Completed. | Completed. | 2025-03-26 | Enamul Haque
58 | 144/0-144A/0 | 2.391 | 2.391 | 2.391 | TSE | 2024-12-05 | Completed. | Completed. | 2024-12-24 | Gokul Sarkar
59 | 144A/0-145/0 | 0.398 | 0.398 | 0.398 | Hotline | 2024-12-25 | Completed. | Completed. | 2025-01-13 | Gokul Sarkar
60 | 145/0-145A/0 | 0.398 | 0.398 | 0.398 | Hotline | 2025-04-19 | Completed. | Completed. | 2025-04-23 | Dharvendra
61 | 145A/0-146/0 | 1.621 | 1.621 | 1.621 | TSE | 2025-04-02 | Completed. | Completed. |  | Enamal Haque |  | TSE-2
62 | 146/0-147/0 | 0.475 | 0.475 | 0.475 | Hotline | 2025-04-12 | Completed. | Completed. | 2025-04-15 | Enamal Haque
63 | 147/0-147/1 | 0.426 | 0.426 | 0.426 | Hotline | 2025-04-11 | Completed. | Completed. | 2025-04-15 | Dharvendra
64 | 147/1-147/2 | 0.33 | 0.33 | 0.33 | Manual | 2025-01-04 | Completed. | Completed. | 2025-01-16 | Gokul Sarkar
65 | 147/2-147A/0 | 2.02 | 2.02 | 2.02 | TSE | 2025-05-16 | Completed. | Completed. | 2025-05-18 | Rafikul Alam Construction |  | Spacering work u/p.
66 | 147A/0-147B/0 | 0.263 | 0.263 | 0.263 | Manual | 2025-04-30 | Completed. | Completed. | 2025-05-01 | Enamal Haque
67 | 147B/0-148/0 | 0.828 | 0.828 | 0.828 | TSE | 2025-04-04 | Completed. | Completed. | 2025-04-15 | Muslaahudin
68 | 148/0-149/0 | 2.994 | 2.994 | 2.994 | TSE | 2025-04-17 | Completed. | Completed. | 2025-04-26 | Muslaahudin
69 | 149/0-150/0 | 0.809 | 0.809 | 0.809 | TSE | 2025-04-22 | Completed. | Completed. | 2025-04-26 | Rafikul Alam Construction
70 | 150/0-150A/0 | 1.633 | 1.633 | 1.633 | TSE | 2025-05-06 | Completed. | Completed. | 2025-05-26 | Alaam Construction
71 | 150A/0-151/0 | 1.252 | 1.252 | 1.252 | TSE | 2025-04-26 | Completed. | Completed. | 2025-05-15 | Alam Construction
72 | 151/0-152/0 | 0.403 | 0.403 | 0.403 | Manual | 2025-04-11 | Completed. | Completed. | 2025-05-15 | Dharvendra
73 | 152/0-152A/0 | 1.78 | 1.78 | 1.78 | TSE | 2025-04-03 | Completed. | Completed. | 2025-04-15 | Alangir
74 | 155/0-156/0 | 2.733 | 2.733 | 2.733 | TSE | 2025-06-06 | Completed. | Completed. | 2025-06-20 | Gokul & Enamul
75 | 156/0-157/0 | 0.24 | 0.24 | 0.24 | Manual | 2025-06-03 | Completed | Completed. | 2025-06-04 | Gokul Sarkar
76 | 167/0-168/0 | 1.95 |  |  | TSE |  | No work. | Insulator hoisting & final chceking u/p.Materials shifting. |  | Enamal Haque
77 | 161/0-162/0 | 0.279 | 0.279 | 0.279 | Hotline | 2025-04-28 | Completed. | Completed. | 2025-05-04 | Gokul Sarkar Dharvendra
78 | 162/0-163/0 | 0.402 | 0.402 | 0.402 | Manual | 2025-04-07 | Completed. | Completed. | 2025-04-26 | Gokul Sarkar
79 | 163/0-164/0 | 2.576 | 2.576 | 2.576 | TSE | 2025-02-24 | Completed. | Completed. | 2025-03-22 | Gokul Sarkar
80 | 164/0-165/0 | 2.981 | 2.981 | 2.981 | TSE | 2025-02-07 | Completed. | Completed. | 2025-02-15 | Gokul Sarkar
82 | 152A/0-153/0 | 0.37 | 0.37 | 0.37 | Manual | 2025-09-03 | Completed. | Completed. | 2025-09-10 | Alam construction

## String-Nav
Stringing Part-II (Navsari Section)
Sr. No. | Section | length | Manual/TSE | Engaged Date | Paying Out |  | Final Sag |  | P/O Completed | F/S Completed | Stringing Status As on Today | Cumulative Status | Sub Contractor name | Manpower | Hindarnce Days | Remarks
[5 empty] | Start Date | End Date | Start Date | End Date
1 | 259/0-260/0 | 0.256 | Hotline | 2025-01-18 | 2025-01-23 | 2025-01-24 | 2025-01-26 | 2025-01-28 | 0.256 | 0.256 | Completed. | Final sag done. | Dharmendra Electrical |  |  | Clipping & jumpering done.
2 | 260/0-261/0 | 0.338 | Manual | 2025-01-17 | 2025-01-23 | 2025-01-25 | 2025-01-26 | 2025-01-28 | 0.338 | 0.338 | Completed. | Final sag done. | Monera | 34 |  | Jumpering & spacering done.
3 | 263/0-264/0 | 0.243 | Hotline | 2025-03-09 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-15 | 0.243 | 0.243 | Completed. | Completed. | Dharmendra Electrical |  |  | Spacer work done.
4 | 264/0-265/0 | 0.44 | Manual |  | 2025-03-16 | 2025-03-18 | 2025-03-19 | 2025-03-22 | 0.44 | 0.44 | Completed. | Completed. | Monera |  |  | Spaer work done.
5 | 257/0-259/0 | 1.809 | TSE | 2025-02-10 | 2025-02-11 | 2025-02-13 | 2025-02-21 | 2025-02-24 | 1.809 | 1.809 | Completed. | Completed. | Monera | 45 |  | Clipping & jumpering done.
6 | 255/0-257/0 | 1.839 | TSE | 2025-02-13 | 2025-02-12 | 2025-02-25 | 2025-03-20 | 2025-03-21 | 1.839 | 1.839 | Completed. | Completed. | Kamruddin | 54 | 4
7 | 262/0-263/0 | 0.685 | Manual | 2025-02-16 | 2025-02-17 | 2025-02-19 | 2025-03-12 | 2025-03-15 | 0.685 | 0.685 | Completed. | Completed. | Monera |  |  | Clipping & spacer work done.
8 | 265/0-266/0 | 0.222 | Hotline |  | 2025-03-16 | 2025-03-18 | 2025-03-19 | 2025-03-21 | 0.222 | 0.222 | Completed. | Completed. | Dharmendra Electrical |  |  | Spcaer work done.
9 | 261/0-262/0 | 0.242 | Hotline | 2025-02-28 | 2025-03-02 | 2025-03-04 | 2025-03-06 | 2025-03-08 | 0.242 | 0.242 | Completed. | Completed. | Dharmendra Electrical | 10 |  | jumpering done.
10 | 254/0-255/0 | 0.3 | Manual |  | 2025-02-26 | 2025-02-28 | 2025-04-07 | 2025-04-08 | 0.3 | 0.3 | Completed. | Completed. | Monera
11 | 272/0-272/5 | 2.053 | TSE | 2025-03-01 | 2025-03-12 | 2025-03-15 | 2025-06-13 | 2025-06-15 | 2.053 | 2.053 | Completed. | Completed. | Kamruddin & Deepak Sarkar |  |  | Deepak sarkar enganged on 12-06-2025 to doing final sag
12 | 266/1-267/0 | 0.835 | Manual |  | 2025-03-22 | 2025-03-24 | 2025-03-25 | 2025-03-28 | 0.835 | 0.835 | Completed. | Completed. | Monera |  |  | Clipping work u/p.
13 | 266/0-266/1 | 0.34 | Hotline |  | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-03-28 | 0.34 | 0.34 | Completed. | Completed. | Dharmendra Electrical
14 | 267A/0-268/0 | 1.44 | TSE | 2025-03-25 | 2025-03-27 | 2025-03-29 | 2025-04-07 | 2025-04-10 | 1.44 | 1.44 | Completed. | Completed. | Kamruddin
15 | 253/0-254/0 | 0.246 | Hotline |  | 2025-04-04 | 2025-04-06 | 2025-04-07 | 2025-04-08 | 0.246 | 0.246 | Completed. | Completed. | Dharmendra Electrical
16 | 267/0-267A/0 | 0.511 | Manual |  | 2025-04-01 | 2025-04-03 | 2025-04-07 | 2025-04-10 | 0.511 | 0.511 | Completed. | Completed. | Kamruddin Deepak Sarkar
17 | 269/0-270/0 | 1.237 | TSE |  | 2025-04-05 | 2025-04-08 | 2025-04-18 | 2025-04-23 | 1.237 | 1.237 | Completed. | Completed. | Kamruddin & Maidul rahman
18 | 270/0-270A/0 | 2.821 | TSE |  | 2025-04-12 | 2025-04-14 | 2025-04-14 | 2025-04-15 | 2.821 | 2.821 | Completed. | Completed. | Kamruddin & Deepak |  |  | Clipping work u/p.
19 | 268/0-269/0 | 0.292 | Hotline |  | 2025-04-17 | 2025-04-19 | 2025-04-21 | 2025-04-23 | 0.292 | 0.292 | Completed. | Completed. | Dharmendra Electrical
20 | 270A/0-271/0 | 0.268 | Manual |  | 2025-04-12 | 2025-04-15 | 2025-04-21 | 2025-04-25 | 0.268 | 0.268 | Completed. | Completed. | Alamgir
21 | 271/0-272/0 | 2.108 | TSE |  | 2025-04-18 | 2025-04-20 | 2025-04-21 | 2025-04-25 | 2.108 | 2.108 | Completed. | Completed. | Kamruddin & Deepak |  |  | Clipping work u/p.
22 | 252/0-253/0 | 0.317 | Manual |  | 2025-04-17 | 2025-04-19 | 2025-05-04 | 2025-05-06 | 0.317 | 0.317 | Completed. | Completed. | Deepak Sarkar
23 | 251/-252/0 | 0.222 | Hotline |  | 2025-04-29 | 2025-05-01 | 2025-05-02 | 2025-05-04 | 0.222 | 0.222 | Completed. | Completed. | Dharmendra Electrical
24 | 250/0-251/0 | 0.737 | Manual |  | 2025-05-04 | 2025-05-05 | 2025-05-08 | 2025-05-10 | 0.737 | 0.737 | Completed. | Completed. | Deepak Sarkar
25 | 249/0-250/0 | 1.368 | TSE |  | 2025-04-29 | 2025-05-03 | 2025-05-09 | 2025-05-12 | 1.368 | 1.368 | Completed. | Completed. | Kamruddin
26 | 197/0-198/0 | 1.74 | TSE | [7 empty] | No work due to ROW. | 197/1/2/3/4 insulator hoisting done. Final checking u/p. |  |  | 3
27 | 248/0-249/0 | 2.525 | TSE | [7 empty] | No work due to ROW. | 04 towers final checking with insulator hoisting done.Cable bypass work u/p. | Kamruddin & Deepak Sarkar | 69 | 1 | ROW from 20-05-2025
28 | 272/5-272A/0 | 1.202 | TSE | [7 empty] | No work. | Insulator hoisting completed.
29 | 158B/0-159/0 | 1.484 | TSE |  | 2025-09-16 | 2025-09-27 | 2025-10-02 | 2025-10-05 | 1.484 | 1.484 | Completed. | Completed. | Deepak Sarkar |  | 1 | Spacering and Clipping U/P
30 | 158/0 - 158A/0 | 1.131 | TSE | [7 empty] | Insulator hoisting completed at 158/1 and pilot paying out completed |  | Deepak Sarkar | 30
31 | 158A/0-158B/0 | 0.481 | Hotline |  | 2025-10-07 | [5 empty] | Top Left phase final sag U/P |  | Dharmendra | 17
32 | 191/0 - 191A/0 | 1.476 | TSE | [7 empty] | Gang shifting completed |  | Alam Construction-1 | 14
33 | 191A/0 - 192/0 | 0.611 | TSE | [7 empty] | Insulator hoisting completed at 191A/1 |  | Md Anwar + Enamul | 26
34 | 195A/0 - 196/0 | 1.542 | TSE | [7 empty] | Insulator hoisting completed at 191A/1 |  | Muslehuddin | 37
35 | 272A/0 ~ 273/0 | 2.944 | TSE | [7 empty] | Insulator hoisting completed at 195A/1, 195A/2, 196/0 and 195A/3 |  | Bhola | 50

## Balance ready stringing
Balance Stringing Ready Status of ANTL project
Sr. No. | Section | Length(Km.) | Total Length | Method | Crossing | Readyness | Status
1 | 174/1-175/0 | 0.289 | 2.79(8) | Manual | NA | Ready | ROW | Approachable
2 | 177/0-178/0 | 0.405 |  | Manual | NA | Ready | ROW | Not Approachable
3 | 178/0-179/0 | 0.278 |  | Manual | NA | Ready | ROW | Not Approachable
4 | 191A/0-192/0 | 0.612 |  | Manual | NA | Ready | Clear | Approachable
5 | 192/0-193/0 | 0.376 |  | Manual | NA | Ready | ROW | Not Approachable
6 | 194/0-195/0 | 0.182 |  | Manual | NA | Ready | ROW | Approachable
7 | 196/0-197/0 | 0.246 |  | Manual | Xpressway | Ready | ROW | Not Approachable
8 | 274/0-275/0 | 0.402 |  | Manual |  | Ready | ROW | Not Approachable
9 | 169/0-171/0 | 0.433 |  | Hotline | 220kV | Ready | ROW | Approachable
10 | 171/0-172/0 | 0.274 |  | Hotline | 400kV | Ready | ROW | Approachable
11 | 176/0-177/0 | 0.232 |  | Hotline | NH | Ready | ROW | Approachable
12 | 179/0-180/0 | 0.264 |  | Hotline | 66kV | Ready | ROW | Not Approachable
13 | 180/0-181/0 | 0.263 |  | Hotline | 220kV | Ready | ROW | Not Approachable
14 | 188/0-189/0 | 0.218 |  | Hotline | 220kV | Ready | ROW | Not Approachable
15 | 190/0-191/0 | 0.329 |  | Hotline | 220kV | Ready | ROW | Approachable
16 | 193/0-194/0 | 0.241 |  | Hotline | 400kV | Ready | ROW | Approachable
17 | 204/0-205/0 | 0.198 |  | Hotline | 400kV | Ready | ROW | Approachable
18 | 168/0-169/0 | 1.044 |  | Machine | NA | Ready | ROW | Approachable
19 | 181/0-182/0 | 1.778 |  | Machine | NA | Ready | ROW | Not Approachable
20 | 189/0-190/0 | 0.829 |  | Machine | NA | Ready | ROW | Not Approachable
21 | 191/0-191A/0 | 1.477 |  | Machine | 66kV | Ready | Clear | Approachable
22 | 195/0-195A/0 | 2.481 |  | Machine | NA | Ready | Clear | Not Approachable
23 | 195A/0-196/0 | 1.542 |  | Machine | NA | Ready | ROW | Not Approachable
24 | 197/0-198/0 | 1.74 |  | Machine | NA | Ready | ROW | Not Approachable | ROW
25 | 198/0-199/0 | 1.149 |  | Machine | NA | Ready | ROW | Not Approachable | Clear
26 | 248/0-249/0 | 2.525 |  | Machine | NA | Ready | ROW | Approachable
27 | 272/5-272A/0 | 1.202 |  | Machine | 66kV | Ready | Clear | Not Approachable
Total | 28 | 21.009
Summary
|  | ROW | 23
|  | Clear | 4
|  | Total | 27

## Visual chart Vadodara
Visual Chart | [31 empty] | #REF!
Name of the Line : |  |  |  | 765 kV D/C Ahmedabad - Navsari Transmission Line | [17 empty] | Completed
Name of Project: |  |  |  | Power Grid Khavda-II C Transmission Limited | [17 empty] | DS (Aprd) | CS (Aprd) | SOIL INVSTGN | FOUNDATION |  |  | TOWER ERECTION |  |  |  | TW | TIG & PUN | STR P/O | STR F/S | OPGW STR
Name of Contractor: |  |  |  | KEC International Limited
[25 empty] | TOTAL | COMP. | BAL. | EAR | TOTAL | COMP. | BAL.
PROGRESS AT A GLANCE : | [10 empty] | CROSSING PROPOSAL STATUS :
Sl. No. | Activity |  |  | UoM | Total Qty |  | Completed Till Date |  | Balance |  | Sl. No. | Type of Crossing |  |  |  | No. of X-ing |  | Approved |  | Balance
1 | Detailed Survey |  |  | Kms | 70.4955 |  | 70.4955 |  | 0 |  | 1 | Powerline X-ing |  |  |  | 23 |  | 22 |  | 1
2 | Check Survey |  |  | Kms | 70.4955 |  | 70.4955 |  | 0 |  | TRUE | 66 kV |  |  |  | 13 |  | 12 |  | 1
3 | Soil Investigation |  |  | Nos. | 11 |  | 11 |  | 0 |  | TRUE | 132 kV |  |  |  | 0 |  | 0 |  | 0
4 | Foundation |  |  | Nos. | 186 |  | 185 |  | 1 |  | TRUE | 220 kV |  |  |  | 7 |  | 7 |  | 0
5 | Earthing |  |  | Nos. | 186 |  | 185 |  | 1 |  | TRUE | 400 kV |  |  |  | 3 |  | 3 |  | 0
6 | Erection |  |  | Nos. | 186 |  | 184 |  | 2 |  | 2 | RLY X-ING |  |  |  | 3 |  | 1 |  | 2
7 | Tack Welding |  |  | Nos. | 186 |  | 180 |  | 6 |  | 3 | NH X-ING |  |  |  | 1 |  | 0 |  | 1
8 | Stringing (P/O) |  |  | Kms | 70.4955 |  | 67.814 |  | 2.6815 |  | 4 | Bullet Train |  |  |  | 0 |  | 0 |  | 0
9 | Stringing (F/S) |  |  | Kms | 70.4955 |  | 67.813 |  | 2.6825 |  | 5 | Express-way |  |  |  | 0 |  | 0 |  | 0
10 | OPGW Stringing |  |  | Kms | 70.4955 |  | 61.106 |  | 9.3895 |  | 6 | GAS PIPELINE |  |  |  | 17 |  | 0 |  | 17
[22 empty] | 4.7514 | 4.7514 | 5 | 10 | 9 | 1 | 9 | 10 | 8 | 2 | 5 |  | 2.078 | 2.078 | 0.442
VADODARA DISTRICT FROM 101/0 - 133A/2 = 74 Locations (Length 27.031 Kms)
| 1 | MAHI | 2 | MAHI | 3 | MAHI | 4 | MAHI | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10
| 101/0 | RIVER | 102/0 | RIVER | 103/0 | RIVER | 104/0 | RIVER | 105/0 |  | 106/0 |  | 106A/0 |  | 106A/1 |  | 106A/2 |  | 106A/3
|  | 665.001 |  | 685 |  | 680.117 |  | 386.59 |  | 256.448 |  | 411.252 |  | 414 |  | 414 |  | 397 |  | 442 | 4751.408
|  |  | PILE |  | PILE |  | PILE |  | PILE |  | WPS | [7 empty] | WPS
| DD60+35 |  | DD45+35 |  | DD45+35 |  | DD60+35 |  | DD60+35 |  | DD60+9 |  | DC2+0 |  | DA+6 |  | DA-3 |  | DA+3
| 6M RC |  | 11.84M RC |  | 12.51M RC |  | 9.97M RC |  | 6M RC
[8 empty] | 400 kV GETCO |  | 220 kV GETCO | [11 empty] | 3.3301 | 3.3301 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.33 | 3.33 | 3.33
GAS PIPELINE-GAIL
| 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20
| 106A/4 |  | 106B/0 |  | 106B/1 |  | 106B/2 |  | 107/0 |  | 107/1 |  | 108/0 |  | 109/0 |  | 110/0 |  | 111/0
|  | 349.362 |  | 324 |  | 431 |  | 393.243 |  | 279 |  | 279.876 |  | 277.199 |  | 342.42 |  | 312.143 |  | 341.895 | 3330.138
| WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS
| DA+9 |  | DB2+9 |  | DA+9 |  | DA+6 |  | DD45+0 |  | DA-3 |  | DD45+0 |  | DB2+0 |  | DB2+0 |  | DC1+0
GAS PIPELINE-GAIL
[16 empty] | GAS PIPELINE-RELIANCE | [5 empty] | 3.2075 | 3.2075 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.207 | 3.207 | 3.207
| 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30
| 112/0 |  | 113/0 |  | 114/0 |  | 115/0 |  | 116/0 |  | 116A/0 |  | 116A/1 |  | 116B/0 |  | 117/0 |  | 118/0
|  | 375.843 |  | 297.046 |  | 373.958 |  | 225.6 |  | 243.413 |  | 360 |  | 315.161 |  | 436.813 |  | 285.244 |  | 294.43 | 3207.508
| WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS |  |  |  | WPS |  | WPS |  | WPS
| DD45+0 |  | DD60+0 |  | DD45+0 |  | DC2+25 |  | DD45+18 |  | DC1+0 |  | DA+0 |  | DD45+6 |  | DD60+3 |  | DD45+0
66 kV GETCO (H-FRAME)
[8 empty] | 220 kV GETCO | [9 empty] | GAS PIPELINE-GAIL |  |  |  | 3.7298 | 3.7298 | 1 | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.729 | 3.729 | 3.729
| 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40
| 119/0 |  | 119/1 |  | 119/2 |  | 119/3 |  | 120/0 |  | 121/0 |  | 122/0 |  | 123/0 |  | 123/1 |  | 124/0
|  | 347 |  | 333 |  | 328 |  | 364.873 |  | 264.71 |  | 525.488 |  | 328.315 |  | 444.001 |  | 399.102 |  | 395.28 | 3729.769
| DD45+0 |  | DA-3 |  | DA+0 |  | DA+0 |  | DD60+9 |  | DD60+18 |  | DC1+6 |  | DD60+6 |  | DA+3 |  | DC1+3
[6 empty] | 66 kV GETCO (H-FRAME) |  | 66 kV GETCO |  | 400 kV GETCO |  |  |  | 66 kV GETCO |  | GAS PIPELINE-ONGC
[22 empty] | 3.604 | 3.604 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.603 | 3.603 | 3.603
| 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49 |  | 50
| 124A/0 |  | 124A/1 |  | 125/0 |  | 125A/0 |  | 126/0 |  | 126/1 |  | 127/0 |  | 127/1 |  | 127/2 |  | 127/3
|  | 253 |  | 203.134 |  | 401.324 |  | 380.082 |  | 425 |  | 383.43 |  | 376.001 |  | 389 |  | 379 |  | 414 | 3603.971
| DD60+0 |  | DA+3 |  | DD60+0 |  | DB2+3 |  | DC2+0 |  | DA+6 |  | DD45+0 |  | DA+0 |  | DA+0 |  | DA+0
|  | 66 kV GETCO |  | GAS PIPELINE-ONGC | [15 empty] | 66 kV GETCO
[22 empty] | 3.7823 | 3.7823 | 1 | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.782 | 3.782 | 3.782
| 51 |  | 52 |  | 53 |  | 54 |  | 55 |  | 56 |  | 57 |  | 58 |  | 59 |  | 60
| 127/4 |  | 127/5 |  | 128/0 |  | 129/0 |  | 129A/0 |  | 129A/1 |  | 129A/2 |  | 130/0 |  | 130/1 |  | 130/2
|  | 428 |  | 413.379 |  | 253.252 |  | 305.53 |  | 373 |  | 400 |  | 409.118 |  | 385 |  | 404 |  | 411 | 3782.279
| DA+3 |  | DA+3 |  | DD60+6 |  | DD60+6 |  | DC1+0 |  | DA+0 |  | DA+3 |  | DB1+0 |  | DA+0 |  | DA+3
3-GAS PIPELINE
[6 empty] | RLY X-ING (NOT IN USE) | [15 empty] | 3.4877 | 3.4877 |  | 10 | 10 | 1 | 10 | 10 | 10 | 0 | 10 |  | 3.487 | 3.487 | 3.487
| 61 |  | 62 |  | 63 |  | 64 |  | 65 |  | 66 |  | 67 |  | 68 |  | 69 |  | 70
| 130/3 |  | 130/4 |  | 131/0 |  | 132/0 |  | 132/1 |  | 132/2 |  | 132/3 |  | 133/0 |  | 133/1 |  | 133/2
|  | 409 |  | 432.128 |  | 236.46 |  | 338 |  | 308 |  | 293 |  | 341.12 |  | 375 |  | 385 |  | 370 | 3487.708
| DA+0 |  | DA+3 |  | DD45+3 |  | DC2+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+0 |  | DA+0
66 kV GETCO
[11 empty] | VADODARA SECTION <<<<<<<<< | BHARUCH DISTRICT FROM 133A/3-153/0 =112 Locations (Length 43.464 Kms) | [9 empty] | 3.8361 | 3.8361 | 1 | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.836 | 3.836 | 3.836
| 71 |  | 72 |  | 73 |  | 74 |  | 75 |  | 76 |  | 77 |  | 78 |  | 79 |  | 80
| 133/3 |  | 133/4 |  | 133/5 |  | 133A/0 |  | 133A/1 |  | 133A/2 |  | 133A/3 |  | 133A/4 |  | 134/0 |  | 135/0
|  | 373 |  | 386 |  | 378.721 |  | 377 |  | 389 |  | 430 |  | 350 |  | 491.5 |  | 235.866 |  | 425 | 3836.087
| WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS
| DA+0 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+0 |  | DA+6 |  | DA+0 |  | DA+6 |  | DC2+25 |  | DC2+25
220 kV GETCO
[22 empty] | 3.7683 | 3.7683 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.768 | 3.768 | 3.768
| 81 |  | 82 |  | 83 |  | 84 |  | 85 |  | 86 |  | 87 |  | 88 |  | 89 |  | 90
| 135/1 |  | 135/2 |  | 135/3 |  | 135/4 |  | 135/5 |  | 135/6 |  | 135/7 |  | 135A/0 |  | 135A/1 |  | 135A/2
|  | 410 |  | 385 |  | 365 |  | 360 |  | 393 |  | 358 |  | 301.642 |  | 339.827 |  | 451.848 |  | 404 | 3768.317
|  |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS | [5 empty] | WPS |  | WPS
| DA+6 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC1+0 |  | DD45+3 |  | DB2+9
[16 empty] | GAS PIPELINE-IOCL |  |  |  | 66 kV GETCO (H-FRAME)
[22 empty] | 3.7404 | 3.7404 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.74 | 3.74 | 3.74
| 91 |  | 92 |  | 93 |  | 94 |  | 95 |  | 96 |  | 97 |  | 98 |  | 99 |  | 100
| 135A/3 |  | 135A/4 |  | 135A/5 |  | 135A/6 |  | 135A/7 |  | 135B/0 |  | 135B/1 |  | 135B/2 |  | 135B/3 |  | 135B/4
|  | 331 |  | 369 |  | 365 |  | 401 |  | 364.387 |  | 362 |  | 356 |  | 352 |  | 430 |  | 410 | 3740.387
| WPS |  | WPS | [5 empty] | WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS
| DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+6
[22 empty] | 3.9486 | 3.9486 | 1 | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.948 | 3.948 | 3.948
| 101 |  | 102 |  | 103 |  | 104 |  | 105 |  | 106 |  | 107 |  | 108 |  | 109 |  | 110
| 135B/5 |  | 135B/6 |  | 135B/7 |  | 136/0 |  | 137/0 |  | 137/1 |  | 137/2 |  | 137/3 |  | 137/4 |  | 137/5
|  | 352 |  | 319 |  | 404.986 |  | 425.582 |  | 447 |  | 396 |  | 369 |  | 400 |  | 420 |  | 415 | 3948.568
| WPS |  | WPS |  | WPS | [5 empty] | WPS |  | WPS |  | WPS |  | WPS
| DA+0 |  | DA+0 |  | DA+3 |  | DD45+18 |  | DC2+9 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3
[7 empty] | 3M RC | 220 kV GETCO | 3M RC
[8 empty] | GAS PIPELINE-IHB | [13 empty] | 3.953 | 3.953 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.953 | 3.952 | 3.953
| 111 |  | 112 |  | 113 |  | 114 |  | 115 |  | 116 |  | 117 |  | 118 |  | 119 |  | 120
| 137/6 |  | 137A/0 |  | 137A/1 |  | 137A/2 |  | 137A/3 |  | 137A/4 |  | 137A/5 |  | 137A/6 |  | 138/0 |  | 138/1
|  | 380.097 |  | 414 |  | 428 |  | 406 |  | 417 |  | 251.002 |  | 374 |  | 439.899 |  | 420.001 |  | 423 | 3952.999
[9 empty] | WPS |  | WPS |  | WPS
| DA+0 |  | DB1+0 |  | DA+6 |  | DA+0 |  | DA+6 |  | DA-3 |  | DA-3 |  | DA+9 |  | DB2+0 |  | DA+6
[22 empty] | 3.8482 | 3.8482 | 1 | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.848 | 3.848 | 3.848
| 121 |  | 122 |  | 123 |  | 124 |  | 125 |  | 126 |  | 127 |  | 128 |  | 129 |  | 130
| 138/2 |  | 139/0 |  | 139/1 |  | 139/2 |  | 139A/0 |  | 140/0 |  | 141/0 |  | 141/1 |  | 141/2 |  | 141/3
|  | 395.993 |  | 386.999 |  | 397 |  | 427.031 |  | 427.136 |  | 249 |  | 390 |  | 370 |  | 391 |  | 414.063 | 3848.222
| DA+0 |  | DB2+0 |  | DA+3 |  | DA+0 |  | DB2+9 |  | DD60+0 |  | DD60+3 |  | DA+0 |  | DA-3 |  | DA+3
[10 empty] | 66 kV GETCO |  | RLY X-ING |  |  |  | 66 kV GETCO |  |  |  | GAS PIPELINE-GAIL
[12 empty] | NH X-ING | [9 empty] | 3.907 | 3.907 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.906 | 3.906 | 3.906
| 131 |  | 132 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137 |  | 138 |  | 139 |  | 140
| 142/0 |  | 143/0 |  | 143A/0 |  | 143A/1 |  | 143A/2 |  | 143A/3 |  | 143A/4 |  | 143A/5 |  | 144/0 |  | 144/1
|  | 223.383 |  | 393.222 |  | 432 |  | 409.199 |  | 413.091 |  | 413 |  | 419 |  | 414.062 |  | 402 |  | 388 | 3906.957
[15 empty] | WPS |  | WPS |  | WPS
| DD60+0 |  | DD60+3 |  | DD45+0 |  | DA+6 |  | DD45+0 |  | DD45+3 |  | DA+0 |  | DA+3 |  | DB2+3 |  | DA+0
|  | RLY X-ING |  | GAS PIPELINE-GAIL | [5 empty] | GAS PIPELINE-GSPL
|  | GAS PIPELINE-GAIL | [19 empty] | 4.0175 | 4.0175 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 4.017 | 4.017 | 4.017
| 141 |  | 142 |  | 143 |  | 144 |  | 145 |  | 146 |  | 147 |  | 148 |  | 149 |  | 150
| 144/2 |  | 144/3 |  | 144/4 |  | 144/5 |  | 144A/0 |  | 145/0 |  | 145A/0 |  | 145A/1 |  | 145A/2 |  | 145A/3
|  | 394 |  | 373 |  | 389 |  | 445 |  | 397.583 |  | 398 |  | 442.999 |  | 383 |  | 417 |  | 377.887 | 4017.469
| WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS |  |  |  | WPS |  |  |  | WPS
| DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+9 |  | DB1+18 |  | DB1+6 |  | DA+3 |  | DA+3 |  | DA+0
[10 empty] | 220 kV GETCO |  | 220 kV GETCO | [9 empty] | 3.9866 | 3.9866 | 1 | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.986 | 3.986 | 3.986
| 151 |  | 152 |  | 153 |  | 154 |  | 155 |  | 156 |  | 157 |  | 158 |  | 159 |  | 160
| 146/0 |  | 147/0 |  | 147/1 |  | 147/2 |  | 147/3 |  | 147/4 |  | 147/5 |  | 147/6 |  | 147A/0 |  | 147B/0
|  | 475.024 |  | 425.519 |  | 330.117 |  | 354.995 |  | 381 |  | 443 |  | 400 |  | 441.898 |  | 263 |  | 472 | 3986.553
[5 empty] | WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS
| DC1+9 |  | DC2+9 |  | DC2+0 |  | DC1+0 |  | DA-3 |  | DA+3 |  | DA+6 |  | DA-3 |  | DB1+18 |  | DB1+18
|  | 66 kV GETCO (H-Frame) |  | 66 kV GETCO
[6 empty] | GAS PIPELINE-GAIL | [11 empty] | 220 kV GETCO |  |  |  | 3.7193 | 3.7193 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.719 | 3.719 | 3.719
| 161 |  | 162 |  | 163 |  | 164 |  | 165 |  | 166 |  | 167 |  | 168 |  | 169 |  | 170
| 147B/1 |  | 148/0 |  | 148/1 |  | 148/2 |  | 148/3 |  | 148/4 |  | 148/5 |  | 148/6 |  | 148/7 |  | 149/0
|  | 355.562 |  | 393 |  | 411 |  | 386 |  | 386 |  | 388 |  | 350 |  | 353 |  | 326.719 |  | 370 | 3719.281
WPS
| DA+0 |  | DC2+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB2+0
[22 empty] | 4.0916 | 4.0916 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 4.091 | 4.091 | 0.805
| 171 |  | 172 |  | 173 |  | 174 |  | 175 |  | 176 |  | 177 |  | 178 |  | 179 |  | 180
| 149/1 |  | 150/0 |  | 150/1 |  | 150/2 |  | 150/3 |  | 150A/0 |  | 150A/1 |  | 150A/2 |  | 151/0 |  | 152/0
|  | 438.762 |  | 367 |  | 475 |  | 362 |  | 429.025 |  | 412 |  | 421 |  | 419.42 |  | 403.348 |  | 364 | 4091.555
[11 empty] | WET |  | WET |  | WET |  |  |  | WET
| DA+0 |  | DD60+9 |  | DA+9 |  | DA+3 |  | DA+6 |  | DC1+0 |  | DA+3 |  | DA+0 |  | DB2+3 |  | DC2+0
|  |  |  | 66 kV GETCO | [7 empty] | GAS PIPELINE-GSPL
[11 empty] | BHARUCH SECTION <<<<<<<<< | [10 empty] | 1.7863 | 1.7863 |  | 6 | 6 | 0 | 6 | 6 | 6 | 0 | 5 |  | 1.786 | 1.786
| 181 |  | 182 |  | 183 |  | 184 |  | 185 |  | 186
| 152/1 |  | 152/2 |  | 152/3 |  | 152/4 |  | 152A/0 |  | 153/0
|  | 343 |  | 331 |  | 344 |  | 397.942 |  | 370.343 | [10 empty] | 1786.285
| WET |  | WET |  | WET |  | WET
| DA+0 |  | DA-3 |  | DA-3 |  | DA+0 |  | DB1+0 |  | DD60+25 | [9 empty] | 70.4955
[11 empty] | 1M RC | [8 empty] | TOTAL - >>>>> |  | 70.4955 | 70.4955 | 11 | 186 | 185 | 2 | 185 | 186 | 184 | 2 | 180 | 0 | 67.814 | 67.813 | 61.106
GAS PIPELINE

## Visual chart NAVSARI Revised
Visual Chart
Visual Chart | [30 empty] | #REF!
Name of the Line : |  |  |  | 765 kV D/C Ahmedabad - Navsari Transmission Line (Navsari Portion) | [17 empty] | Completed
Name of Project: |  |  |  | Power Grid Khavda-II C Transmission Limited | [17 empty] | DS (Aprd) | CS (Aprd) | SOIL INVSTGN | FOUNDATION |  |  | EARTH | TOWER ERECTION |  |  | TW | TIG & PUN | STR P/O | STR F/S | OPGW STR
Name of Contractor: |  |  |  | KEC International Limited
[25 empty] | TOTAL | COMP. | BAL. |  | TOTAL | COMP. | BAL.
PROGRESS AT A GLANCE : | [10 empty] | CROSSING PROPOSAL STATUS :
Sl. No. | Activity |  |  | UoM | Total Qty |  | Completed Till Date |  | Balance |  | Sl. No. | Type of Crossing |  |  |  | No. of X-ing |  | Approved |  | Balance
1 | Detailed Survey |  |  | Kms | 106.8547 |  | 106.8547 |  | 0 |  | 1 | Powerline X-ing |  |  |  | 44 |  | 42 |  | 2
2 | Check Survey |  |  | Kms | 106.8547 |  | 106.8547 |  | 0 |  | TRUE | 66 kV |  |  |  | 18 |  | 16 |  | 2
3 | Soil Investigation |  |  | Nos. | 19 |  | 19 |  | 0 |  | TRUE | 132 kV |  |  |  | 2 |  | 2 |  | 0
4 | Foundation |  |  | Nos. | 298 |  | 293 |  | 5 |  | TRUE | 220 kV |  |  |  | 13 |  | 13 |  | 0
5 | Earthing |  |  | Nos. | 298 |  | 292 |  | 6 |  | TRUE | 400 kV |  |  |  | 11 |  | 11 |  | 0
6 | Erection |  |  | Nos. | 298 |  | 200 |  | 98 |  | 2 | RLY X-ING |  |  |  | 3 |  | 3 |  | 0
7 | Tack Welding |  |  | Nos. | 298 |  | 127 |  | 171 |  | 3 | NH X-ING |  |  |  | 3 |  | 0 |  | 3
8 | Stringing (P/O) |  |  | Kms | 106.8547 |  | 32.115 |  | 74.7397 |  | 4 | Bullet Train |  |  |  | 2 |  | 0 |  | 2
9 | Stringing (F/S) |  |  | Kms | 106.8547 |  | 31.633 |  | 75.2217 |  | 5 | Express-way |  |  |  | 5 |  | 0 |  | 5
10 | OPGW Stringing |  |  | Kms | 106.8547 |  | 4.836 |  | 102.0187 |  | 6 | GAS PIPELINE |  |  |  | 6 |  | 0 |  | 6
[22 empty] | 4.3881 | 4.3881 | 2 | 9 | 8 | 1 | 8 | 9 | 7 | 2 | 7 |  | 2.733 | 2.733
BHARUCH DISTRICT FROM 154/0 - 165/3 = 48 Locations (Length 18.616 Kms)
| 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10
| 153/0 |  | 154/0 |  | 154/1 |  | 155/0 |  | 155/1 |  | 155/2 |  | 155/3 |  | 155/4 |  | 155/5 |  | 155/6
|  | 620 |  | 620 |  | 414.995 |  | 400 |  | 408 |  | 428 |  | 408 |  | 384 |  | 337 |  | 368.134 | 4388.129
|  |  | PILE |  | PILE |  | WET |  | PS |  | PS |  | WET | [5 empty] | PS
| DD60+25 |  | DD45+25 |  | DD45+25 |  | DD60+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA-3
| 1M RC |  | 10.96M RC |  | 11.96M RC
[22 empty] | 3.8435 | 3.8435 | 1 | 10 | 10 | 0 | 10 | 10 | 9 | 1 | 9 |  | 1.137 | 0.655
| 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20
| 156/0 |  | 157/0 |  | 157/1 |  | 157/2 |  | 157/3 |  | 158/0 |  | 158/1 |  | 158/2 |  | 158A/0 |  | 158B/0
|  | 240.527 |  | 418 |  | 393 |  | 389 |  | 375.803 |  | 367 |  | 343 |  | 420.567 |  | 481.567 |  | 415 | 3843.464
| WPS | [7 empty] | FS | [7 empty] | WET |  | PS
| DD60+3 |  | DD60+6 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA-3 |  | DA-3 |  | DD45+6 |  | DD45+18
|  | XPRESSWAY | [13 empty] | GAS PIPELINE |  | 66 kV GETCO
[22 empty] | 3.6216 | 3.6216 | 1 | 10 | 10 | 0 | 10 | 10 | 8 | 2 | 8 |  | 1.519 | 1.519
| 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30
| 158B/1 |  | 158B/2 |  | 159/0 |  | 159/1 |  | 159/2 |  | 159/3 |  | 159/4 |  | 160/0 |  | 161/0 |  | 162/0
|  | 421 |  | 417.829 |  | 340 |  | 380 |  | 371 |  | 354 |  | 427.196 |  | 229.824 |  | 279.052 |  | 401.678 | 3621.579
| PS |  | PS |  | WET | [5 empty] | WET
| DA+3 |  | DA+3 |  | DB1+0 |  | DA+0 |  | DCT+0 |  | DA+0 |  | DA+0 |  | DD60+18 |  | DD60+25 |  | DD60+25
[8 empty] | GAS PIPELINE | [7 empty] | 400KV EASER POWER |  | BULLET
[22 empty] | 3.703 | 3.703 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.703 | 3.703 | 3.702
| 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40
| 163/0 |  | 163/1 |  | 163/2 |  | 163/3 |  | 163/4 |  | 163/5 |  | 163/6 |  | 164/0 |  | 164/1 |  | 164/2
|  | 385 |  | 383 |  | 384 |  | 367 |  | 375 |  | 339 |  | 342.998 |  | 370 |  | 382 |  | 375 | 3702.998
|  |  | WET |  | WET |  | WET |  | WET |  | FS |  | FS |  | FS |  |  |  | WET
| DC2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA+0 |  | DA+0
66KV GETCO
[18 empty] | SURAT DISTRICT From 165/3-248/3 |  |  |  | 4.0054 | 4.0054 |  | 10 | 9 | 1 | 9 | 10 | 9 | 1 | 9 |  | 1.853 | 1.853 | 1.134
[16 empty] | BHARUCH SECTION <<<<<<<<< |  | 169 Locations (Length 59.223 Kms)
| 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49 |  | 50
| 164/3 |  | 164/4 |  | 164/5 |  | 164/6 |  | 164/7 |  | 165/0 |  | 165/1 |  | 165/2 |  | 165/3 |  | 165/4
|  | 376 |  | 372 |  | 386 |  | 379 |  | 340.776 |  | 382 |  | 390 |  | 434 |  | 407 |  | 538.65 | 4005.426
|  |  | WFR |  | WFR |  | PS |  | WET |  | PS |  | PS |  | WET |  | WET
| DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DA+6 |  | DD45+9
4.5M RC
[22 empty] | 3.4188 | 3.4188 | 1 | 10 | 7 | 3 | 6 | 10 | 6 | 4 | 6
| 51 |  | 52 |  | 53 |  | 54 |  | 55 |  | 56 |  | 57 |  | 58 |  | 59 |  | 60
| 165/5 |  | 166/0 |  | 167/0 |  | 167/1 |  | 167/2 |  | 167/3 |  | 167/4 |  | 168/0 |  | 168/1 |  | 168/2
|  | 423.12 |  | 270.31 |  | 342.5 |  | 229.11 |  | 444 |  | 339 |  | 326.332 |  | 310 |  | 328 |  | 406.389 | 3418.761
[9 empty] | WET |  | WPS |  | WET | [5 empty] | FS
| DD45+9 |  | DD60+6 |  | DD60+6 |  | DD60+0 |  | DA+6 |  | DA+6 |  | DA+0 |  | DC1+0 |  | DA-3 |  | DA+0
| 4.5M RC |  |  | RLY X-ING
[22 empty] | 3.3882 | 3.3882 |  | 10 | 10 | 0 | 10 | 10 | 6 | 4
| 61 |  | 62 |  | 63 |  | 64 |  | 65 |  | 66 |  | 67 |  | 68 |  | 69 |  | 70
| 169/0 |  | 171/0 |  | 172/0 |  | 172/1 |  | 172/2 |  | 173/0 |  | 174/0 |  | 174/1 |  | 175/0 |  | 175/1
|  | 433.217 |  | 274.117 |  | 446 |  | 272 |  | 405.018 |  | 231.552 |  | 381 |  | 289.251 |  | 329.999 |  | 326 | 3388.154
| PS |  | PS
| DD45+18 |  | DD60+25 |  | DD60+25 |  | DA+3 |  | DA+6 |  | DD60+25 |  | DD60+18 |  | DB1+0 |  | DD45+0 |  | DA+0
|  | GAS PIPELINE | 3M RC | 400KV GETCO | [7 empty] | 400KV TORRENT | [5 empty] | GAS PIPELINE
|  | 220KV PGCIL | [15 empty] | 66KV GETCO |  |  |  | 3.2591 | 3.2591 | 1 | 10 | 10 | 0 | 10 | 10 | 10 | 0
| 71 |  | 72 |  | 73 |  | 74 |  | 75 |  | 76 |  | 77 |  | 78 |  | 79 |  | 80
| 175/2 |  | 176/0 |  | 177/0 |  | 178/0 |  | 179/0 |  | 180/0 |  | 181/0 |  | 181/1 |  | 181/2 |  | 181/3
|  | 323.209 |  | 231.636 |  | 404.857 |  | 277.839 |  | 264.355 |  | 263.234 |  | 414.999 |  | 326 |  | 377 |  | 376 | 3259.129
| DA+0 |  | DD60+0 |  | DD60+0 |  | DD60+6 |  | DD60+0 |  | DD45+9 |  | DD45+18 |  | DA+0 |  | DA+0 |  | DA+0
|  |  |  | NH X-ING |  |  |  | RLY X-ING NOT IN USE |  | 66KV GETCO | 3M RC | 220KV GETCO
[22 empty] | 3.7405 | 3.7405 | 1 | 10 | 10 | 0 | 10 | 10 | 2 | 8
| 81 |  | 82 |  | 83 |  | 84 |  | 85 |  | 86 |  | 87 |  | 88 |  | 89 |  | 90
| 181/4 |  | 182/0 |  | 182A/0 |  | 183/0 |  | 184/0 |  | 184/1 |  | 185/0 |  | 185/1 |  | 186/0 |  | 187/0
|  | 284.072 |  | 246.217 |  | 430.404 |  | 234.635 |  | 468 |  | 412.076 |  | 360 |  | 460.116 |  | 398.978 |  | 446 | 3740.498
| DA+0 |  | DD60+0 |  | DD45+6 |  | DD60+25 |  | DD60+25 |  | DB1+6 |  | DC2+0 |  | DA+9 |  | DD60+35 |  | DD60+25
|  |  |  | 66KV GETCO | 2M RC |  |  | 400KV TORRENT |  |  |  | KIM RIVER | [5 empty] | 400KV TORRENT
[18 empty] | 66KV GETCO |  |  |  | 3.5631 | 3.5631 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0
| 91 |  | 92 |  | 93 |  | 94 |  | 95 |  | 96 |  | 97 |  | 98 |  | 99 |  | 100
| 187/1 |  | 187/2 |  | 187/3 |  | 188/0 |  | 189/0 |  | 189/1 |  | 190/0 |  | 191/0 |  | 191/1 |  | 191/2
|  | 317 |  | 335 |  | 411.498 |  | 218.419 |  | 370 |  | 458.939 |  | 329.237 |  | 465 |  | 355 |  | 303 | 3563.093
|  |  | FS |  | PS |  | WET |  | WET | [5 empty] | WET |  | WET
| DA+3 |  | DA-3 |  | DA+0 |  | DB1+6 |  | DB2+6 |  | DA+0 |  | DD45+25 |  | DD45+25 |  | DA+0 |  | DA-3
[8 empty] | 220KV GETCO | [5 empty] | 220KV GETCO | [5 empty] | 66KV GETCO
[22 empty] | 3.4393 | 3.4393 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0
| 101 |  | 102 |  | 103 |  | 104 |  | 105 |  | 106 |  | 107 |  | 108 |  | 109 |  | 110
| 191/3 |  | 191A/0 |  | 191A/1 |  | 192/0 |  | 193/0 |  | 194/0 |  | 195/0 |  | 195/1 |  | 195/2 |  | 195/3
|  | 353.561 |  | 290 |  | 321.994 |  | 376.036 |  | 241.118 |  | 181.604 |  | 408 |  | 433 |  | 407 |  | 427 | 3439.313
|  |  | WET |  | FS |  |  |  | WET |  |  |  | PS | [5 empty] | PS
| DA-3 |  | DB2+0 |  | DA-3 |  | DC1+0 |  | DD60+6 |  | DD60+6 |  | DC2+0 |  | DA+6 |  | DA+0 |  | DA+6
400KV TORRENT
[22 empty] | 3.6648 | 3.6648 | 1 | 10 | 10 | 0 | 10 | 10 | 10 | 0
| 111 |  | 112 |  | 113 |  | 114 |  | 115 |  | 116 |  | 117 |  | 118 |  | 119 |  | 120
| 195/4 |  | 195/5 |  | 195A/0 |  | 195A/1 |  | 195A/2 |  | 195A/3 |  | 196/0 |  | 197/0 |  | 197/1 |  | 197/2
|  | 411 |  | 395 |  | 339 |  | 443 |  | 386 |  | 374.31 |  | 246.469 |  | 385.999 |  | 353 |  | 331 | 3664.778
| WET | [9 empty] | PS |  | WBC
| DA+0 |  | DA+6 |  | DB1+0 |  | DA+6 |  | DA+6 |  | DA+0 |  | DD60+9 |  | DD60+9 |  | DA+0 |  | DA+0
XPRESSWAY
[22 empty] | 3.9332 | 3.9332 |  | 10 | 10 | 0 | 10 | 10 | 6 | 4
| 121 |  | 122 |  | 123 |  | 124 |  | 125 |  | 126 |  | 127 |  | 128 |  | 129 |  | 130
| 197/3 |  | 197/4 |  | 198/0 |  | 198/1 |  | 198/2 |  | 199/0 |  | 200/0 |  | 201/0 |  | 201/1 |  | 202/0
|  | 368 |  | 302.151 |  | 374 |  | 366 |  | 409.422 |  | 221.436 |  | 204.39 |  | 532.469 |  | 366.962 |  | 788.368 | 3933.198
| PS |  | WET |  | WET |  | WET
| DA+0 |  | DA+0 |  | DC1+0 |  | DA+0 |  | DA+0 |  | DD45+18 |  | DB2+18 |  | DC2+18 |  | DD60+9 |  | DD60+55
[12 empty] | 220KV TORRENT |  | 220KV TORRENT |  |  | 2M RC |  | 4.5M RC | TAPI RIVER
[12 empty] | 66KV TORRENT | [9 empty] | 3.6672 | 3.6672 | 1 | 10 | 10 | 0 | 10 | 10 | 5 | 5
| 131 |  | 132 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137 |  | 138 |  | 139 |  | 140
| 203/0 |  | 203/1 |  | 204/0 |  | 205/0 |  | 205/1 |  | 205/2 |  | 206/0 |  | 208/0 |  | 209/0 |  | 209/1
|  | 459.999 |  | 424.69 |  | 198.036 |  | 328 |  | 292 |  | 443.161 |  | 412.08 |  | 409.847 |  | 299.999 |  | 399.426 | 3667.238
| DD60+55 |  | DD60+6 |  | DD60+9 |  | DD60+3 |  | DA-3 |  | DA+3 |  | DD60+25 |  | DD60+25 |  | DC1+0 |  | DA+3
| 4.5M RC |  |  |  |  | 400KV TORRENT | 2M RC | [6 empty] | 220KV TORRENT
[14 empty] | 400KV GETCO | [7 empty] | 3.4246 | 3.4246 | 1 | 10 | 10 | 0 | 10 | 10 | 1 | 9
| 141 |  | 142 |  | 143 |  | 144 |  | 145 |  | 146 |  | 147 |  | 148 |  | 149 |  | 150
| 210/0 |  | 211/0 |  | 211/1 |  | 211/2 |  | 211A/0 |  | 211A/1 |  | 211A/2 |  | 212/0 |  | 213/0 |  | 213/1
|  | 223.42 |  | 386.999 |  | 378 |  | 393.196 |  | 359 |  | 354 |  | 311.323 |  | 248.056 |  | 385 |  | 385.596 | 3424.59
| DB2+18 |  | DB1+9 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA-3 |  | DA+0 |  | DD45+3 |  | DD60+3 |  | DA+0
|  | 220KV TORRENT | [13 empty] | XPRESSWAY
[22 empty] | 3.7323 | 3.7323 |  | 10 | 10 | 0 | 10 | 10 | 1 | 9
| 151 |  | 152 |  | 153 |  | 154 |  | 155 |  | 156 |  | 157 |  | 158 |  | 159 |  | 160
| 214/0 |  | 214/1 |  | 215/0 |  | 215/1 |  | 216/0 |  | 217/0 |  | 217A/0 |  | 217A/1 |  | 217A/2 |  | 218/0
|  | 250 |  | 463.098 |  | 221 |  | 410.769 |  | 456.491 |  | 347 |  | 426 |  | 400 |  | 347.899 |  | 410 | 3732.257
| DD45+0 |  | DA+6 |  | DB1+6 |  | DA+9 |  | DB2+25 |  | DD45+25 |  | DB1+3 |  | DA+3 |  | DA+0 |  | DD60+0
[6 empty] | 66KV GETCO |  |  | 2M RC | 220KV PGCIL | 2M RC | 220KV GETCO
[22 empty] | 3.2464 | 3.2464 |  | 10 | 10 | 0 | 10 | 10 |  | 10
| 161 |  | 162 |  | 163 |  | 164 |  | 165 |  | 166 |  | 167 |  | 168 |  | 169 |  | 170
| 218/1 |  | 219/0 |  | 220/0 |  | 220/1 |  | 221/0 |  | 222/0 |  | 222/1 |  | 223/0 |  | 223/1 |  | 223/2
|  | 412.193 |  | 242.397 |  | 324.003 |  | 411.037 |  | 222.183 |  | 388.109 |  | 182.523 |  | 342 |  | 338 |  | 384 | 3246.445
| DA+3 |  | DC2+18 |  | DD45+9 |  | DA+3 |  | DD60+18 |  | DD60+25 |  | DB1+3 |  | DC1+0 |  | DA+0 |  | DA+0
|  |  |  | 220KV GETCO | [5 empty] | 400KV PGCIL |  |  |  | 66KV GETCO
[22 empty] | 3.4818 | 3.4818 | 1 | 10 | 10 | 0 | 10 | 10 |  | 10
| 171 |  | 172 |  | 173 |  | 174 |  | 175 |  | 176 |  | 177 |  | 178 |  | 179 |  | 180
| 223/3 |  | 224/0 |  | 225/0 |  | 225/1 |  | 226/0 |  | 227/0 |  | 228/0 |  | 229/0 |  | 229/1 |  | 229/2
|  | 333.514 |  | 234.721 |  | 409 |  | 268.584 |  | 417.449 |  | 238.569 |  | 196.002 |  | 549 |  | 463 |  | 372 | 3481.839
| DA+0 |  | DC2+6 |  | DD60+0 |  | DA+6 |  | DC2+0 |  | DB1+6 |  | DD60+25 |  | DD60+18 |  | DB1+6 |  | DA+6
|  |  |  | 66KV GETCO | [9 empty] | 400KV PGCIL
[22 empty] | 3.1085 | 3.1085 |  | 10 | 10 | 0 | 10 | 10 | 1 | 9
| 181 |  | 182 |  | 183 |  | 184 |  | 185 |  | 186 |  | 187 |  | 188 |  | 189 |  | 190
| 229/3 |  | 229/4 |  | 229/5 |  | 230/0 |  | 231/0 |  | 232/0 |  | 233/0 |  | 234/0 |  | 235/0 |  | 236/0
|  | 365 |  | 351 |  | 333.363 |  | 226.874 |  | 419.216 |  | 194.761 |  | 305.03 |  | 328.278 |  | 305.141 |  | 279.863 | 3108.526
| DA+0 |  | DA+0 |  | DA+0 |  | DD60+0 |  | DD60+6 |  | DD60+3 |  | DD45+0 |  | DD45+0 |  | DC2+3 |  | DB2+0
[8 empty] | RLY X-ING |  |  |  | 66KV GETCO |  |  |  | 66KV GETCO |  |  |  | 66KV GETCO
[22 empty] | 3.2209 | 3.2209 | 1 | 10 | 10 | 0 | 10 | 10 | 1 | 9
| 191 |  | 192 |  | 193 |  | 194 |  | 195 |  | 196 |  | 197 |  | 198 |  | 199 |  | 200
| 237/0 |  | 237/1 |  | 237/2 |  | 237/3 |  | 237/4 |  | 237/5 |  | 237/6 |  | 239/0 |  | 240/0 |  | 241/0
|  | 446 |  | 312 |  | 308 |  | 353 |  | 347 |  | 290 |  | 463.512 |  | 247.697 |  | 207.386 |  | 246.351 | 3220.946
| DD45+9 |  | DA+0 |  | DA-3 |  | DA-3 |  | DA+0 |  | DA-3 |  | DA+3 |  | DD60+25 |  | DD60+25 |  | DB2+9
| 3M RC | [14 empty] | 400KV PGCIL |  |  |  | XPRESSWAY
[22 empty] | 3.3145 | 3.3145 | 1 | 10 | 10 | 0 | 10 | 10 | 2 | 8
| 201 |  | 202 |  | 203 |  | 204 |  | 205 |  | 206 |  | 207 |  | 208 |  | 209 |  | 210
| 242/0 |  | 242/1 |  | 242/2 |  | 242/3 |  | 243/0 |  | 244/0 |  | 244/1 |  | 245/0 |  | 245/1 |  | 246/0
|  | 320 |  | 308 |  | 312 |  | 394.895 |  | 249.614 |  | 494 |  | 426.974 |  | 233 |  | 335.543 |  | 240.465 | 3314.491
| DB1+0 |  | DA-3 |  | DA-3 |  | DA-3 |  | DB1+9 |  | DC1+9 |  | DB1+9 |  | DD45+0 |  | DA+0 |  | DD60+0
[10 empty] | XPRESSWAY | [9 empty] | NH X-ING
[16 empty] | NAVSARI DISTRICT FROM 248/3 - GANTRY | [5 empty] | 3.7896 | 3.7896 |  | 10 | 10 | 0 | 10 | 10 | 8 | 2 | 5
[14 empty] | SURAT SECTION <<<<<<<<< |  | 80 Locations (Length 28.711 Kms)
| 211 |  | 212 |  | 213 |  | 214 |  | 215 |  | 216 |  | 217 |  | 218 |  | 219 |  | 220
| 247/0 |  | 247/1 |  | 247/2 |  | 247/3 |  | 247/4 |  | 248/0 |  | 248/1 |  | 248/2 |  | 248/3 |  | 248/4
|  | 382.999 |  | 415 |  | 391 |  | 300 |  | 467.57 |  | 486 |  | 265 |  | 271 |  | 380 |  | 431 | 3789.569
| DD60+0 |  | DA+0 |  | DA+3 |  | DA-3 |  | DA+0 |  | DC2+9 |  | DA+9 |  | DA+9 |  | DA+6 |  | DA+3
[22 empty] | 3.3357 | 3.3357 | 2 | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 2.643 | 2.643
| 221 |  | 222 |  | 223 |  | 224 |  | 225 |  | 226 |  | 227 |  | 228 |  | 229 |  | 230
| 248/5 |  | 248/6 |  | 249/0 |  | 249/1 |  | 249/2 |  | 249/3 |  | 250/0 |  | 250/1 |  | 251/0 |  | 252/0
|  | 380 |  | 311.881 |  | 303 |  | 357 |  | 367 |  | 340.703 |  | 337 |  | 400.076 |  | 222.09 |  | 316.922 | 3335.672
FS
| DA+0 |  | DA+0 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DD60+0 |  | DA-3 |  | DB1+9 |  | DC1+18
220KV GETCO
[22 empty] | 3.3663 | 3.3663 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.366 | 3.366
| 231 |  | 232 |  | 233 |  | 234 |  | 235 |  | 236 |  | 237 |  | 238 |  | 239 |  | 240
| 253/0 |  | 254/0 |  | 255/0 |  | 255/1 |  | 255/2 |  | 255/3 |  | 255/4 |  | 257/0 |  | 257/1 |  | 257/2
|  | 245.523 |  | 300.466 |  | 315 |  | 428 |  | 408 |  | 412.002 |  | 276.298 |  | 374 |  | 296 |  | 311 | 3366.289
|  |  | FS |  | FS | [7 empty] | WPS |  | WET |  |  |  | WET
| DC1+0 |  | DB2+0 |  | DD60+3 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+0 |  | DC2+0 |  | DA+0 |  | DA-3
|  | NH X-ING |  |  |  | 66KV GETCO
[22 empty] | 3.256 | 3.256 | 1 | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.256 | 3.256
| 241 |  | 242 |  | 243 |  | 244 |  | 245 |  | 246 |  | 247 |  | 248 |  | 249 |  | 250
| 257/3 |  | 257/4 |  | 259/0 |  | 260/0 |  | 261/0 |  | 262/0 |  | 262/1 |  | 263/0 |  | 264/0 |  | 265/0
|  | 358 |  | 470.323 |  | 255.672 |  | 337.664 |  | 242.024 |  | 367 |  | 318.597 |  | 243.259 |  | 440.728 |  | 222.758 | 3256.025
| wet |  | WET |  | PS |  | WBC |  | WET |  | WET |  | WET |  | PS |  | WET |  | WET
| DA+0 |  | DA+0 |  | DD60+18 |  | DD60+18 |  | DC2+18 |  | DD45+9 |  | DA+0 |  | DC2+0 |  | DC1+6 |  | DB2+3
|  |  |  | GAS PIPELINE |  | BULLET |  |  |  | 220KV PGCIL | [5 empty] | 132KV GETCO |  |  |  | 66KV GETCO
[22 empty] | 3.8115 | 3.8115 | 1 | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.812 | 3.812
| 251 |  | 252 |  | 253 |  | 254 |  | 255 |  | 256 |  | 257 |  | 258 |  | 259 |  | 260
| 266/0 |  | 266/1 |  | 266/2 |  | 267/0 |  | 267A/0 |  | 267A/1 |  | 267A/2 |  | 267A/3 |  | 268/0 |  | 269/0
|  | 340 |  | 440 |  | 395.057 |  | 511.129 |  | 380 |  | 338 |  | 302 |  | 420.092 |  | 292.226 |  | 393 | 3811.504
[7 empty] | WET |  | WET |  | FS |  | WET |  | WET |  | WET |  | WET
| DB1+0 |  | DB1+6 |  | DA+0 |  | DC1+9 |  | DC2+9 |  | DA+0 |  | DA-3 |  | DA+0 |  | DD60+6 |  | DD60+0
|  | 132KV GETCO |  |  |  |  | 2M RC | GAS PIPELINE | 2M RC | [8 empty] | RLY X-ING
[22 empty] | 3.6642 | 3.6642 | 1 | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.664 | 3.664
| 261 |  | 262 |  | 263 |  | 264 |  | 265 |  | 266 |  | 267 |  | 268 |  | 269 |  | 270
| 269/1 |  | 269/2 |  | 270/0 |  | 270/1 |  | 270/2 |  | 270/3 |  | 270/4 |  | 270/5 |  | 270/6 |  | 270/7
|  | 421 |  | 422.589 |  | 330 |  | 399 |  | 379 |  | 353 |  | 378 |  | 344 |  | 307 |  | 330.606 | 3664.195
[7 empty] | PS |  | WET
| DA+0 |  | DA+6 |  | DD45+0 |  | DA+0 |  | DA+3 |  | DA-3 |  | DA+0 |  | DA+0 |  | DA-3 |  | DA-3
GAS PIPELINE
[22 empty] | 3.5903 | 3.5903 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.59 | 3.59
| 271 |  | 272 |  | 273 |  | 274 |  | 275 |  | 276 |  | 277 |  | 278 |  | 279 |  | 280
| 270A/0 |  | 271/0 |  | 271/1 |  | 271/2 |  | 271/3 |  | 271/4 |  | 271/5 |  | 272/0 |  | 272/1 |  | 272/2
|  | 268.315 |  | 354 |  | 360 |  | 362 |  | 341 |  | 331 |  | 360.025 |  | 478 |  | 359 |  | 377 | 3590.34
|  |  | WET | [9 empty] | WET |  | WET |  | WET |  | WET
| DC2+0 |  | DC1+0 |  | DA-3 |  | DA+0 |  | DA-3 |  | DA-3 |  | DA-3 |  | DC1+6 |  | DA+9 |  | DA-3
[22 empty] | 3.9316 | 3.9316 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 0.839 | 0.839
| 281 |  | 282 |  | 283 |  | 284 |  | 285 |  | 286 |  | 287 |  | 288 |  | 289 |  | 290
| 272/3 |  | 272/4 |  | 272/5 |  | 272/6 |  | 272/7 |  | 272A/0 |  | 272A/1 |  | 272A/2 |  | 272A/3 |  | 272A/4
|  | 434 |  | 405.02 |  | 390.995 |  | 312 |  | 498.56 |  | 382 |  | 346 |  | 381 |  | 366 |  | 416 | 3931.575
[5 empty] | WET |  |  |  | WET |  | PS |  | WET |  | WET
| DA+3 |  | DA+3 |  | DB1+0 |  | DA+3 |  | DA+9 |  | DB1+18 |  | DA+6 |  | DA+0 |  | DA+0 |  | DA+0
[9 empty] | 2M RC | 66KV GETCO | 2M RC
[22 empty] | 2.9447 | 2.9447 | 1 | 9 | 9 | 0 | 9 | 9 | 8 | 1 | 3
| 291 |  | 292 |  | 293 |  | 294 |  | 295 |  | 296 |  | 297 |  | 298 |  | 299 |  | NAVSARI
| 272A/5 |  | 272A/6 |  | 272A/7 |  | 273/0 |  | 273/1 |  | 273/2 |  | 274/0 |  | 275/0 |  | 276/0 |  | GANTRY
|  | 370 |  | 328 |  | 354.532 |  | 390 |  | 395 |  | 368.331 |  | 401.674 |  | 177.173 |  | 159.989 | GANTRY |  | 2944.699
| DA+3 |  | DA-3 |  | DA-3 |  | DB2+0 |  | DA+6 |  | DA+6 |  | DC1+0 |  | DD45+0 |  | DD60+0 |  |  |  | 106.8547
[15 empty] | 2M RC | 66KV GETCO | 2M RC |  |  | TOTAL - >>>>> |  | 106.8547 | 106.8547 | 19 | 298 | 293 | 5 | 292 | 298 | 200 | 98 | 127 | 0 | 32.115 | 31.633 | 4.836
R
R
R
R
R
R
R
NARMADA RIVER
NARMADA RIVER
NARMADA RIVER
GAS PIPELINE

## Crossing Vadodara
765KV D/C HEXA AHEMDABAD - NAVSARI TL (PKG 02)- CROSSING DETAILS
Sl No | AP NO | AP No | Type of Crossings | OWNER | Nos. | Work Portion | Submitted to Client for Review | Revised Submisison due to Route Div. | Confirmation received from Client | Hard Copy Submission Date | Joint Inspection Date | Proposal Currently With
1 | 104 | 105 | 400KV | GETCO | 2 | Vadodara | 2014-02-27 |  |  |  | 2024-05-03 | Approved 30.07.24
2 | 104 | 105 | Gas Pipe Line | GAIL | 1 | Vadodara | 2024-02-14 |  |  |  |  | Online proposal submitted
3 | 105 | 106 | 220KV | GETCO | 1 | Vadodara | 2024-03-22 | 2024-04-10 |  | 2024-04-23 |  | Approved
4 | 108 | 109 | Gas Pipe Line | GAIL | 1 | Vadodara | 2024-02-22 |  |  |  |  | Online proposal submitted
5 | 109 | 110 | Gas Pipe Line | RELIANCE | 1 | Vadodara | 2024-02-22 |  |  |  | 2024-04-05 | Awaiting DD
6 | 115 | 116 | 220KV | GETCO | 1 | Vadodara | 2023-09-28 | 2024-04-10 | 2023-10-16 | 2024-04-23 | 2023-11-22 | Approved
7 | 117 | 118 | Gas Pipe Line | GAIL | 1 | Vadodara | 2024-02-22 |  |  |  |  | Online proposal submitted
8 | 118 | 119 | 66KV H-Frame Mobha – Karkhadi TL | GETCO | 1 | Vadodara | 2023-09-11 | 2023-09-28 | 2023-10-16 | 2023-10-23 | 2023-11-22 | Approved
9 | 119/2 | 119/3 | 66KV H-Frame Mobha – Karkhadi TL | GETCO | 1 | Vadodara | 2023-09-11 | 2023-09-28 | 2023-10-16 | 2023-10-23 | 2023-11-22 | Approved
10 | 119/3 | 120 | 66KV D/C Gavasad to Sterling/Sarod TL | GETCO | 1 | Vadodara | 2023-09-11 | 2023-09-28 | 2023-10-16 | 2023-10-23 | 2023-11-22 | Approved
11 | 120 | 121 | 400KV S/C Kasor – Jeepek TL | GETCO | 1 | Vadodara | 2023-09-11 | 2023-09-28 | 2023-10-16 | 2023-10-23 | 2023-11-29 | Approved
12 | 122 | 123 | 66KV | GETCO | 1 | Vadodara | 2023-09-28 |  | 2023-10-16 | 2023-10-23 | 2023-11-22 | Approved
13 | 123 | 123/1 | Gas Pipe Line | ONGC | 1 | Vadodara | 2024-02-26 |  |  |  |  | Online proposal submitted
14 | 124A/0 | 124A/1 | 66KV | GETCO | 1 | Vadodara | 2023-09-28 |  | 2023-10-16 | 2023-10-23 | 2023-11-22 | Approved
15 | 124A/1 | 125 | Gas Pipe Line | ONGC | 1 | Vadodara | 2024-02-26 |  |  |  |  | Online proposal submitted
16 | 127/3 | 127/4 | 66KV | GETCO | 1 | Vadodara | 2023-09-28 |  | 2023-10-16 | 2023-10-23 | 2023-11-22 | Approved
17 | 128 | 129 | RLY Crossing (Not in Use) | RLY | 1 | Vadodara | 2023-09-01 |  |  | 2023-12-10 | 2024-05-13 | Submitted to Railway - Vadodara
18 | 129 | 129A | Gas Pipe Line | ONGC | 1 | Vadodara | 2024-02-26 |  |  |  |  | Proposal submitted.
| 129 | 129A | Gas Pipe Line | GSPL | 1 | Vadodara | [5 empty] | Proposal submitted,Demand received.
| 129 | 129A | Gas Pipe Line | GAIL | 1 | Vadodara | [5 empty] | Online Proposal Submitted.
19 | 131 | 132 | 66KV Line | GETCO | 1 | Vadodara | 2023-09-09 | 2023-09-28 | 2023-10-16 | 2023-10-23 | 2023-11-22 | Approved
20 | 134 | 135 | 220KV M/C Gavasad - Amod TL | GETCO | 1 | Vadodara | 2023-07-06 |  | 2023-07-12 | 2023-07-16 | 2023-09-12 | Approved
21 | 135A/0 | 135A/1 | Gas Pipe Line | IOCL | 1 | Vadodara | 2024-02-14 | 2024-02-20 |  |  | 2024-04-13 | Demand & aggrement awaiting
22 | 135A/2 | 135A/3 | 66KV H FRAME SARBHAN-AMOD | GETCO | 1 | Vadodara | 2024-03-31 |  |  |  | 2024-05-04 | Approved 01-08-2024
23 | 136 | 137 | 220KVD/C MBH - SUV TL | GETCO | 1 | Vadodara | 2023-07-06 |  | 2023-10-16 | 2023-10-23 | 19.04.2024 | Approved
24 | 136 | 137 | Gas Pipe Line | IHB | 1 | Vadodara | 2024-01-23 | 2024-03-27 |  |  | 2024-04-03 | Demand received, E office note 844813 initiate.
25 | 139A/0 | 140 | 66KV U/C TOWER LINE | GETCO | 1 | Vadodara | 2023-09-09 | 2024-04-10 | 2023-10-16 | 2023-10-23 | 2024-05-08 | Approved
26 | 140 | 141 | NH 228 | NH | 1 | Vadodara | 2023-09-09 |  | 2023-09-12 | 2023-12-10 |  | Submitted in Bharuch
27 | 140 | 141 | RLY Line | RLY | 1 | Vadodara | 2023-09-01 |  |  | 2023-12-10 | 2024-05-08 | Awaited for DD
28 | 141/1 | 141/2 | 66KV H Frame Kurchan-Wagra | GETCO | 1 | Vadodara | 2024-04-05 | 2024-04-10 |  |  | 2024-05-02 | Pole no. 40 of existing line has to be shift away from corridor of 67 mtr.
| 141/3 | 142/0 | Gas Pipe Line | GAIL | 1 | Vadodara | [5 empty] | Online proposal submitted.
29 | 142 | 143 | RLY Line | RLY | 1 | Vadodara | 2023-09-01 |  |  | 2023-12-10 | 2024-01-24 | Approved
30 | 142 | 143 | Gas Pipe Line | GAIL | 1 | Vadodara | 2024-01-23 | 2024-01-23 |  |  |  | Online proposal submitted
31 | 143 | 143A | Gas Pipe Line | GAIL | 1 | Vadodara | 2024-01-23 | 2024-01-23 |  |  |  | Online proposal submitted
32 | 143A/2 | 143A/3 | Gas Pipe Line | GSPL | 1 | Vadodara | [5 empty] | Reapplied in PM gatishakti portal
33 | 144A | 145 | 220KV D/C Haldarva - Wagra TL | GETCO | 1 | Vadodara | 2023-08-17 |  | 2023-08-20 | 2023-09-08 | 2023-11-02 | Approved
34 | 145 | 145A | 220KV Haldarva- IPCL (Dahej) TL | GETCO | 1 | Vadodara | 2023-08-17 |  | 2023-08-20 | 2023-09-08 | 2023-11-02 | Approved
35 | 146 | 147 | 66KV H FRAME NANDEWAR - WAGRA TL | GETCO | 1 | Vadodara | 2023-09-09 | 2024-01-03 | 2023-10-16 | 2024-01-03 |  | Approved
36 | 147 | 147/1 | 66KV TOWER TAPPING FROM NANDEWAR - WAGRA TO VILAYAT S/S | GETCO | 1 | Vadodara | 2023-09-09 | 2024-01-03 | 2023-09-12 | 2024-01-03 |  | Approved
37 | 147/1 | 147/2 | Gas Pipe Line | GAIL | 1 | Vadodara | 2024-01-23 | 2024-01-23 | 2024-03-18 |  |  | Online proposal submitted.
38 | 147A | 147B | 220KV D/C Wagra - TSS (Tham) TL | GETCO | 1 | Vadodara | 2023-08-17 |  | 2023-08-20 | 2023-09-08 |  | Approved 02-08-2024
39 | 150 | 150/1 | 66KV | GETCO | 1 | Vadodara | 2023-09-28 |  | 2023-10-16 | 2023-10-23 | 12.04.2024 | Approved 03-08-2024
40 | 150A/0 | 151A/1 | Gas Pipe Line | GSPL | 1 | Vadodara | 2024-02-14 | 2024-02-20 |  |  |  | Reapplied in PM gatishakti portal
44

## Crossing Navsari
765KV D/C HEXA AHEMDABAD - NAVSARI TL PKG 02 (NAVSARI PORTION) - CROSSING STATUS
Sl No | AP NO | Towe Type | AP No | Tower Type | Type of Crossings | LINE OWNER | Nos. | Work Portion | Status | Submitted to Client for Review | Submission to Line Owner Date | Joint Inspection Date | Proposal Currently With | Remarks
1 | 156/0 | DD60+3 | 157/0 | DD60+6 | DEL - MUM Xpressway (SAKKARPUR - ANKLESHWAR) | NHAI | 1 | Navsari | Submitted | 2024-01-30 | 2024-02-03 | 2024-02-23 | NHAI Kamrej
2 | 158/2 | DA-3 | 158A/0 | DD45+6 | Gas Pipeline |  | 1 | Navsari | Submitted |  |  | Done
3 | 158A/0 | DD45+6 | 158B/0 | DD45+18 | 66KV Hansot - Urban TL | GETCO | 1 | Navsari | Submitted |  | 2024-06-04 |  |  | Approved on 01-08-2024
4 | 159/1 | DA+0 | 159/2 | DA+0 | Gas Pipeline (Avanton) |  |  | Navsari | Proposal Not Required |  |  | Done
5 | 160/0 | DD60+18 | 161/0 | DD60+25 | 400KV HZR - GDR | EASER POWER | 1 | Navsari | Submitted | 2023-09-07 | 2023-09-15 | 2023-09-30 | Eassar | Approved on 09-09-2024
6 | 161/0 | DD60+25 | 162/0 | DD60+25 | Bullet Train |  | 1 | Navsari | Submitted | 2024-02-19 | 2024-02-22 | 2024-04-30 |  | Approved
7 | 163/5 | DA+0 | 163/6 | DA+0 | 66KV Panoli - Hansot TL | GETCO | 1 | Navsari | Submitted | 2023-10-03 | 2023-10-06 | 2023-10-14 | Vadodara GETCO | Approved on 01-03-2024
8 | 166/0 | DD60+6 | 167/0 | DD60+0 | RLY Line Haturan - Panoli | Western Railway Vadodara | 1 | Navsari | Submitted | 2023-09-08 | 2023-10-05 | 2024-01-19 | Vadodara GETCO (DRM office) | Approved
9 | 169/0 | DD45+9 | 171/0 | DD60+25 | Gas Pipeline |  | 1 | Navsari | Submitted |  | 2024-03-08 | Done
10 | 169/0 | DD45+9 | 171/0 | DD60+25 | 220KV D/C KWS - HAL | PGCIL | 1 | Navsari | Submitted | 2023-09-02 | 2023-09-04 |  | PGCIL DASTAN | Approved on 20.06.2024
11 | 171/0 | DD60+25 | 172/0 | DD60+25 | 400KV Kosamba - Chorania | GETCO | 1 | Navsari | Submitted | 2023-09-07 | 2023-09-09 | 2023-10-03 | Vadodara GETCO | Approved on 01-03-2024
12 | 173/0 | DD60+18 | 174/0 | DD60+18 | 400KV DGEN - Navsari | TORRENT POWER | 1 | Navsari | Submitted | 2023-09-07 | 2023-09-09 | 2023-10-09 | TORRENT Surat | Approved
13 | 175/0 | DD45+0 | 175/1 | DA+0 | 66KV Dinoda - Kharch | GETCO | 1 | Navsari | Submitted | 2023-09-18 | 2023-09-19 | 2023-10-03 | Vadodara GETCO | Resubmit to GETCO
14 | 175/0 | DD45+0 | 175/1 | DA+0 | Gas Pipeline |  | 1 | Navsari | Submitted |  |  | Done
15 | 176/0 | DD60+0 | 177/0 | DD60+0 | NH48 (Delhi - Mumbai) - Kosamba | NHAI | 1 | Navsari | Submitted | 2023-10-03 | 2023-10-05 | 2023-11-28 | NHAI Kamrej | Approved
16 | 178/0 | DD60+6 | 179/0 | DD60+0 | RLY Crossing (Not in Use) | Western Railway Vadodara | 1 | Navsari | Submitted | 2023-10-03 | 2023-10-17 |  | Available with PGCIL | No need approval
17 | 179/0 | DD60+0 | 180/0 | DD45+9 | 66KV D/C Palod - Kosamba TL | GETCO | 1 | Navsari | Submitted | 2023-10-03 | 2023-10-05 | 2023-10-13 | Vadodara GETCO | Approved on 22-04-2024
18 | 180/0 | DD45+9 | 181/0 | DD45+18 | 220KV Jiseg - Kosamba | GETCO | 1 | Navsari | Submitted | 2023-10-03 | 2023-10-05 | 2023-10-13 | Vadodara GETCO | Approved on 22-04-2024
19 | 182/0 | DD60+0 | 182A/0 | DD45+6 | 66KV D/C Kim - FTP TL | GETCO | 1 | Navsari | Submitted | 2023-11-03 | 2023-12-11 | 2024-01-17 | GETCO BHARUCH | Approved
20 | 183/0 | DD60+25 | 184/0 | DD60+25 | 400KV D/C DGEN - Navsari | TORRENT POWER | 1 | Navsari | Submitted | 2023-11-03 | 2023-12-11 | 2024-01-17 | TORRENT Surat | Approved
21 | 184/1 | DB1+6 | 185/0 | DC2+0 | KIM RIVER |  | 1 | Navsari | Proposal Not Required |  | 2023-12-11
22 | 186/0 | DD60+25 | 187/0 | DD60+18 | 400KV SUG - PIR | TORRENT POWER | 1 | Navsari | Submitted | 2023-11-03 | 2023-12-11 |  | TORRENT Surat | Approved
23 | 186/0 | DD60+25 | 187/0 | DD60+18 | 66KV Lilo - Simodra | GETCO | 1 | Navsari | Submitted | 2024-01-29 | 2023-12-11 | 2024-02-10 | GETCO BHARUCH | Approved on 01-08-2024
24 | 188/0 | DB1+6 | 189/0 | DB2+6 | 220KV D/C Kim - Kosamba TL | GETCO | 1 | Navsari | Submitted | 2023-11-03 | 2023-12-11 | 2024-01-17 | GETCO BHARUCH | Approved on 01.-08-2024
25 | 190/0 | DD45+25 | 191/0 | DD45+25 | 220KV D/C Kosamba - Vav TL | GETCO | 1 | Navsari | Submitted | 2023-11-03 | 2023-12-11 | 2024-01-17 | GETCO BHARUCH | Approved on 01-08-2024
26 | 191/2 | DA-3 | 191/3 | DA-3 | 66KV Kim - Masoli TL | GETCO | 1 | Navsari | Submitted | 2023-11-03 | 2023-12-11 | 2024-01-17 | GETCO BHARUCH | Awaiting NOC
27 | 193/0 | DD60+6 | 194/0 | DD60+6 | 400KV S/C GHT - TPL | TORRENT POWER | 1 | Navsari | Submitted | 2023-11-03 | 2023-12-11 | 2024-01-17 | TORRENT Surat | Approved
28 | 196/0 | DD60+9 | 197/0 | DD60+9 | DEL - MUM Xpressway - Roswad | NHAI | 1 | Navsari | Submitted | 2023-10-03 | 2023-10-06 | 2023-11-18 | NHAI Kamrej
29 | 199/0 | DD45+18 | 200/0 | DB2+18 | 66KV Karanj - Areth | GETCO | 1 | Navsari | Submitted | 2024-01-29 | 2024-01-31 | 2024-02-10 | GETCO BHARUCH | Approved
30 | 199/0 | DD45+18 | 200/0 | DB2+18 | 220KV Sugen - Bhatar | TORRENT POWER | 1 | Navsari | Submitted | 2024-01-29 | 2024-02-01 |  | TORRENT Surat | Approved on 14-05-2024
31 | 200/0 | DB2+18 | 201/0 | DC1+18 | 220KV Sugen - Puna | TORRENT POWER | 1 | Navsari | Submitted | 2024-01-29 | 2024-02-01 |  | TORRENT Surat | Approved on 14-05-2024
32 | 202/0 |  | 203/0 |  | TAPI RIVER |  | 1 | Navsari | Proposal Not Required
33 | 204/0 | DD60+6 | 205/0 | DD60+3 | 400KV TPL - VAP | TORRENT POWER | 1 | Navsari | Submitted | 2024-01-29 | 2024-02-01 |  | TORRENT surat | Approved
34 | 206/0 | DD60+25 | 208/0 | DD60+25 | 220KV Sugen - Puna | TORRENT POWER | 1 | Navsari | Submitted | 2024-01-29 | 2024-02-01 |  | TORRENT surat | Approved on 14-05-2024
35 | 206/0 | DD60+25 | 208/0 | DD60+25 | 400KV Kosamba - Vav | GETCO | 1 | Navsari | Submitted | 2024-01-29 | 2024-01-30 | 2024-02-06 | GETCO NAVSARI | Approved
36 | 210/0 | DB1+18 | 211/0 | DB2+6 | 220KV Sugen - Bhatar | TORRENT POWER | 1 | Navsari | Submitted | 2024-01-29 | 2024-02-01 |  | TORRENT surat | Approved on 14-05-2024
37 | 212/0 | DD60+0 | 213/0 | DD60+0 | DEL - MUM Xpressway (Jat Barthana Kamrej) | NHAI | 1 | Navsari | Submitted | 2024-01-30 | 2024-02-03 | Done | NHAI Kamrej
38 | 215/0 | DB1+6 | 215/1 | DA+9 | 66KV Vav - Shmpura Line | GETCO | 1 | Navsari | Submitted | 2023-10-03 | 2024-02-03 | 2023-10-11 | Vadodara GETCO | Approved on 12-02-2024
39 | 216/0 | DB2+25 | 217/0 | DD45+25 | 220KV D/C Kap - Vav | PGCIL | 1 | Navsari | Submitted | 2023-09-18 | 2024-02-03 |  | PGCIL DASTAN | Approved
40 | 217/0 | DD45+25 | 217A/0 | DB1+3 | 220KV Vav - Mota | GETCO | 1 | Navsari | Submitted | 2023-09-18 | 2023-09-19 | 2023-10-04 | Vadodara GETCO | Approved
41 | 219/0 | DC2+18 | 220/0 | DD45+9 | 220KV D/C Mota - Koshamba | GETCO | 1 | Navsari | Submitted | 2023-09-18 | 2023-09-19 | 2023-09-29 | Vadodara GETCO | Approved on 01-04-2024
42 | 221/0 | DD60+25 | 222/0 | DD60+25 | 400KV GND - NAV | PGCIL | 1 | Navsari | Submitted | 2023-09-18 | 2023-09-19 |  | PGCIL DASTAN | Approved on 20.06.2024
43 | 222/1 | DB1+3 | 223/0 | DC1+0 | 66KV Parab - Shampura | GETCO | 1 | Navsari | Submitted | 2023-09-18 | 2023-09-19 | 2023-09-29 | Vadodara GETCO | Approved on 09-02-2024
44 | 224/0 | DC2+6 | 225/0 | DD60+0 | 66KV D/C Mota - Kejriwal TL | GETCO | 1 | Navsari | Submitted | 2023-09-18 | 2023-09-19 | 2023-09-29 | Vadodara GETCO | Approved on 01-04-2024
45 | 228/0 | DD60+25 | 229/0 | DD60+18 | 400KV D/C KPP - Nav | PGCIL | 1 | Navsari | Submitted | 2023-09-08 | 2023-09-18 |  | PGCIL DASTAN | Approved on 20.06.2024
46 | 230/0 | DD60+0 | 231/0 | DD60+6 | RLY LINE | Western Railway Mumbai | 1 | Navsari | Submitted | 2023-10-13 | 2023-10-13 |  | Mumbai | Approved 05.08.2024
47 | 232/0 | DD60+3 | 233/0 | DD45+0 | 66KV Mota - Bardoli Line | GETCO | 1 | Navsari | Submitted | 2023-10-03 | 2023-10-06 | 2023-10-16 | Bharuch GETCO | Approved on 01-04-2024
48 | 234/0 | DC2+3 | 235/0 | DD45+0 | 66KV VAV -Jolwa-Palsana | GETCO | 1 | Navsari | Submitted | 2024-01-29 | 2024-01-30 | 2024-02-07 | GETCO NAVSARI | Approved
49 | 236/0 | DB2+0 | 237/0 | DD45+9 | 66KV Mota - Sharvon | GETCO | 1 | Navsari | Submitted | 2024-01-29 | 2024-01-30 | 2024-02-06 | GETCO NAVSARI | Approved on 01-08-2024
50 | 239/0 | DD60+25 | 240/0 | DD60+25 | 400KV Navsari - Magarwada | PGCIL | 1 | Navsari | Submitted | 2024-01-29 | 2024-02-02 |  | PGCIL DASTAN | Approved on 20.06.2024
51 | 241/0 | DD60+9 | 242/0 | DD60+0 | DEL - MUM Xpressway (Ena - Palsana) | NHAI | 1 | Navsari | Submitted | 2024-01-30 | 2024-02-03 | Done | NHAI Kamrej
52 | 243/0 | DD60+9 | 244/0 | DD60+9 | DEL - MUM Xpressway (Ghaluda) | NHAI | 1 | Navsari | Submitted | 2024-01-30 | 2024-02-03 | Done | NHAI Kamrej
53 | 246/0 | DD60+0 | 247/0 | DD60+0 | NH Crossing | NHAI | 1 | Navsari | Route Divertion |  |  | 2024-09-05 |  | Succeding span Not Available
54 | 251/0 | DB1+9 | 252/0 | DC1+18 | 220KV Nav - Popda | GETCO | 1 | Navsari | Submitted | 2023-10-03 | 2023-10-06 | 2023-10-11 | Vadodara GETCO | Approved on 01-04-2024
55 | 253/0 | DD60+0 | 254/0 | DD60+0 | NH48 (Delhi - Mumbai) - Vesma | NHAI | 1 | Navsari | Submitted | 2023-10-03 | 2023-10-05 | 2024-09-03 | NHAI Kamrej
56 | 255/0 | DD60+3 | 255/1 | DA+6 | 66KV Tavdi - Vesma | GETCO | 1 | Navsari | Submitted | 2023-10-03 | 2023-10-06 | 2023-10-11 | Vadodara GETCO | Approved on 12-02-2024
57 | 257/4 | DA+0 | 259/0 | DD60+18 | Gas Pipeline |  | 1 | Navsari | Submitted |  |  | Done
58 | 259/0 | DD60+18 | 260/0 | DD60+18 | Bullet Train |  | 1 | Navsari | Submitted | 2024-02-19 | 2024-02-22 | 2024-04-29 |  | Approved
59 | 261/0 | DC2+9 | 262/0 | DD45+9 | 220KV D/C Nav - Nav | PGCIL | 1 | Navsari | Submitted | 2023-09-18 | 2023-09-19 |  | PGCIL DASTAN | Approved on 20.06.2024
60 | 263/0 | DC2+0 | 264/0 | DC1+6 | 132KV S/C NAV - Popda TL | GETCO | 1 | Navsari | Submitted | 2023-09-18 | 2023-09-19 | 2023-09-27 | Vadodara GETCO | Approved on 12-02-2024
61 | 265/0 | DB2+3 | 266/0 | DB1+0 | 66KV Nav - Eklera | GETCO | 1 | Navsari | Submitted | 2023-09-18 | 2023-09-19 | 2023-09-27 | Vadodara GETCO | Approved on 12-02-2024
62 | 266/0 | DB1+0 | 266/1 | DB1+6 | 132KV Nav - Bhestan | GETCO | 1 | Navsari | Submitted | 2023-09-18 | 2023-09-19 | 2023-09-27 | Vadodara GETCO | Approved
63 | 267/0 | DB2+0 | 267A/0 | DC2+9 | Gas Pipeline |  | 1 | Navsari | Submitted |  |  | Done |  | Route Divertion not confirmed from PGCIL
64 | 268/0 | DD60+6 | 269/0 | DD60+0 | RLY LINE | Western Railway Mumbai | 1 | Navsari | Submitted | 2023-10-13 | 2023-10-13 |  | Mumbai | Approved 05.08.2024
65 | 270/0 | DD45+0 | 270/1 | DA+0 | Gas Pipeline |  | 1 | Navsari | Submitted |  | 2024-03-08 | Done
66 | 272/7 | DB1+0 | 272A/0 | DA+3 | 66KV Talangpur - Mangrol Line | GETCO | 1 | Navsari | Submitted | 2023-10-03 | 2023-10-06 | 2023-10-11 | Vadodara GETCO | Approved on 29-01-2024
67 | 275/0 | DD60+0 | 276/0 | DD60+3 | 66KV Mangrol. - Umbrath | GETCO | 1 | Navsari | Submitted | 2024-01-29 | 2024-01-30 | 2024-02-05 | GETCO NAVSARI | Approved on 01-08-2024
66

## Subcontractor
Navsari Portion Sub Contractor Details
Sr. No. | Activity | Sub-Contractor Name | Manpower | Gang Mobilization Date | Gang Demobilization date | Sr. No. | Activity | Sub-Contractor Name | Manpower | Gang Mobilization Date | Gang Demobilization date | Sr. No. | Activity | Sub-Contractor Name | Gang Mobilization Date
1 | Foundation | M/s Rudra Associate | 14 |  |  | 1 | Erection | M/s Sukhridwin | 35 |  |  | 1 | Stringing
2 | Foundation | M/s Khodiyar Krupra |  |  |  | 2 | Erection | M/s Ghanshyam | 42 |  |  | 2
3 | Foundation | M/s Tes Transco-01 | 26 | 2024-09-10 |  | 3 | Erection | M/s Ram Jivan-01 |  |  |  | 3
4 | Foundation | M/s Tes Transco-02 | 15 | 2024-09-15 |  | 4 | Erection | M/s Ram Jivan-02 |  |  |  | 4
5 | Foundation | M/s Tes Transco-03 | 15 | 2024-10-03 |  | 5 | Erection | M/s Hari Narayan |  |  |  | 5
6 | Foundation | M/s Maa Bhawani | 25 | 2024-09-30 |  | 6 | Erection | M/s Chahnur Bibi |  |  |  | 6
7 | Foundation | M/s Rajesh Singh | 16 | 2024-09-30 |  | 7 | Erection | M/s Thanu Mahto | 32 | 2024-09-28 |  | 7
8 | Foundation | M/s Jyoti Constr. | 15 | 2024-10-01 |  | 8 | Erection | M/s Senaul-01 | 22 | 2024-10-02 |  | 8
9 | Foundation | M/s Kastabhanja | 15 | 2024-11-22 |  | 9 | Erection | M/s Rahul Kumar | 23 | 2024-10-23 |  | 9
10 | Foundation | M/s Jitu Bhai | 18 |  |  | 10 | Erection | M/s Modina India | 29 | 2024-11-08 |  | 10
11 | [5 empty] | 11 | Erection | M/s Modina India | 29 | 2024-11-08 |  | 11
12 | [5 empty] | 12 | Erection | M/s Mithun | 23 | 2024-11-17 |  | 12
13 | [5 empty] | 13 | Erection | M/s Barkat Ali | 29 | 2024-11-15 |  | 13
14 | [5 empty] | 14 | Erection | M/s Jwala | 23 | 2024-11-18 |  | 14
[6 empty] | 15 | Erection | M/s Rahim | 12 | 2024-11-26
[6 empty] | 16 | Erection | M/s MJR | 30 | 2024-11-27
[6 empty] | 17 | Erection | M/s Senahul-02 | 12 | 2024-11-28
[6 empty] | 18 | [5 empty] | 15
Vadodara Portion Sub Contractor Details
Sr. No. | Activity | Sub-Contractor Name |  | Gang Mobilization Date | Gang Demobilization date | Sr. No. | Activity | Sub-Contractor Name |  | Gang Mobilization Date | Gang Demobilization date | Sr. No. | Activity | Sub-Contractor Name | Gang Mobilization Date
1 | Foundation | M/s Alamin Constr.-01 |  |  |  | 1 | Erection | M/s Ajay Kumar | 22 |  |  | 1 | Stringing | M/s Musladudin
2 | Foundation | M/s Alamin Constr.-02 |  |  |  | 2 | Erection | M/s Gouri Shankar | 30 |  |  | 2 | Stringing | M/s Gokul Sarkar
3 | Foundation | M/s hajji saheb |  |  |  | 3 | Erection | M/s Rahul Kumar |  |  |  | 3
4 | Foundation | M/s Jyoti Construction |  |  |  | 4 | Erection | M/s Dhaneshwar mahto | 28 |  |  | 4
5 | Foundation | M/s Jeet Infra |  |  |  | 5 | Erection | M/s Barkad Alli |  |  |  | 5
6 | Foundation | M/s Prince construction |  |  |  | 6 | Erection | M/s Rejaul |  |  |  | 6
7 | Foundation | M/s BK Traders | 14 | 146/0 |  | 7 | Erection | M/s Senaul Haque | 18 |  |  | 7
8 |  | Hmanshi Constr.-01 | 13 | 148/0 |  | 8 | Erection | M/s SK Samiul |  |  |  | 8
9 |  | Himanshi-02 | 12 | 148/1 |  | 9 |  | M/s Vijay Sah | 22 | 147/3 |  | 9
10 | [5 empty] | 10 |  | Mukesh Kumar | 28 |  |  | 10
11 | [5 empty] | 11 | [5 empty] | 11
12 | [5 empty] | 12 | [5 empty] | 12
13 | [5 empty] | 13 | [5 empty] | 13
14 | [5 empty] | 14 | [5 empty] | 14
15 | [5 empty] | 15 | [5 empty] | 15

## OPGW
OPGW stringing Status for TA-325 Project
Sr. No. | Drum No. | [5 empty] | Section Length | OPGW length | Completed Length | Status
1 | AHMD-NVSA-1 | 101/0 | DD60+35 | - | 106A/3 | DA+3 | 4309.408 | 4581
2 | AHMD-NVSA-2 | 106A/3 | DA+3 | - | 112/0 | DD45+0 | 3772.138 | 3995 | 3772.138 | Completed.
3 | AHMD-NVSA-3 | 112/0 | DD45+0 | - | 119/3 | DA+0 | 4215.508 | 4442 | 4215.508 | Completed.
4 | AHMD-NVSA-4 | 119/3 | DA+0 | - | 124A/1 | DA+3 | 2974.769 | 3187 | 2974.769 | Completed.
5 | AHMD-NVSA-5 | 124A/1 | DA+3 | - | 129/0 | DD60+6 | 4445.602 | 4684 | 4445.602 | Completed.
6 | AHMD-NVSA-6 | 129/0 | DD60+6 | - | 132/3 | DA+0 | 4704.236 | 4944 | 4704.236 | Completed.
7 | AHMD-NVSA-7 | 132/3 | DA+0 | - | 133A/0 | DB1+0 | 2608.841 | 2811 | 2608.841 | Completed.
8 | AHMD-NVSA-8 | 133A/0 | DB1+0 | - | 135/5 | DA+0 | 4218.366 | 4445 | 4218.366 | Completed.
9 | AHMD-NVSA-9 | 135/5 | DA+0 | - | 135B/2 | DA+0 | 4796.704 | 5033 | 4796.704 | Completed.
10 | AHMD-NVSA-10 | 135B/2 | DA+0 | - | 137/5 | DA+3 | 4725.568 | 4964 | 4725.568 | Completed.
11 | AHMD-NVSA-11 | 137/5 | DA+3 | - | 138/2 | DA+0 | 4367.999 | 4601 | 4367.999 | Completed.
12 | AHMD-NVSA-12 | 138/2 | DA+0 | - | 141/3 | DA+3 | 3434.159 | 3653 | 3434.159 | Completed.
13 | AHMD-NVSA-13 | 141/3 | DA+3 | - | 144/3 | DA+0 | 4715.02 | 4953 | 4715.02 | Completed.
14 | AHMD-NVSA-14 | 144/3 | DA+0 | - | 145A/2 | DA+3 | 2828.582 | 3038 | 2828.582 | Completed.
15 | AHMD-NVSA-15 | 145A/2 | DA+3 | - | 147A/0 | DB1+18 | 4046.44 | 4291 | 4046.44 | Completed.
16 | AHMD-NVSA-16 | 147A/0 | DB1+18 | - | 150/1 | DA+9 | 5260.043 | 5529 | 5260.043 | Completed.
17 | AHMD-NVSA-17 | 150/1 | DA+9 | - | 152A/0 | DB1+0 | 4701.735 | 4944 | 4.702 | Completed.
18 | AHMD-NVSA-18 | 152A/0 | DB1+0 | - | 155/3 | DA+3 | 3261.338 | 3476
19 | AHMD-NVSA-19 | 155/3 | DA+3 | - | 158A/0 | DD45+6 | 4444.031 | 4683
20 | AHMD-NVSA-20 | 158A/0 | DD45+6 | - | 163/0 | DC2+0 | 4518.146 | 4753
21 | AHMD-NVSA-21 | 163/0 | DC2+0 | - | 164/6 | DA+0 | 4836.998 | 5072 | 4836.998 | Completed.
22 | AHMD-NVSA-22 | 164/6 | DA+0 | - | 167/4 | DA+0 | 4614.529 | 4848
23 | AHMD-NVSA-23 | 167/4 | DA+0 | - | 175/2 | DA+0 | 4758.875 | 4995
24 | AHMD-NVSA-24 | 175/2 | DA+0 | - | 182/0 | DD60+0 | 3543.201 | 3759
25 | AHMD-NVSA-25 | 182/0 | DD60+0 | - | 187/1 | DA+3 | 3456.426 | 3674
26 | AHMD-NVSA-26 | 187/1 | DA+3 | - | 192/0 | DC1+0 | 4528.648 | 4762
27 | AHMD-NVSA-27 | 192/0 | DC1+0 | - | 195A/3 | DA+0 | 4447.758 | 4677
28 | AHMD-NVSA-28 | 195A/3 | DA+0 | - | 199/0 | DD45+18 | 3510.351 | 3744
29 | AHMD-NVSA-29 | 199/0 | DD45+18 | - | 206/0 | DD60+25 | 4259.511 | 4549
30 | AHMD-NVSA-30 | 206/0 | DD60+25 | - | 213/1 | DA+0 | 4560.346 | 4817
31 | AHMD-NVSA-31 | 213/1 | DA+0 | - | 220/0 | DD45+9 | 4772.443 | 5016
32 | AHMD-NVSA-32 | 220/0 | DD45+9 | - | 227/0 | DB1+6 | 4255.123 | 4496
33 | AHMD-NVSA-33 | 227/0 | DB1+6 | - | 237/0 | DD45+9 | 4927.097 | 5178
34 | AHMD-NVSA-34 | 237/0 | DD45+9 | - | 243/0 | DB1+9 | 4555.841 | 4804
35 | AHMD-NVSA-35 | 243/0 | DB1+9 | - | 245/0 | DD45+0 | 1170.588 | 1359
36 | AHMD-NVSA-36 | 245/0 | DD45+0 | - | 248/5 | DA+0 | 4598.577 | 4830
37 | AHMD-NVSA-37 | 248/5 | DA+0 | - | 255/2 | DA+0 | 4624.661 | 4858
38 | AHMD-NVSA-38 | 152A/0 | DB1+0 | - | 264/0 | DC1+6 | 4669.839 | 4909
39 | AHMD-NVSA-39 | 264/0 | DC1+6 | - | 269/2 | DA+6 | 4895.99 | 5144
40 | AHMD-NVSA-40 | 269/2 | DA+6 | - | 270/3 | DA-3 | 1530.589 | 1721
41 | AHMD-NVSA-41 | 270/3 | DA-3 | - | 272/1 | DA+9 | 4566.946 | 4806
42 | AHMD-NVSA-42 | 272/1 | DA+9 | - | 272A/5 | DA+3 | 4667.575 | 4914
43 | AHMD-NVSA-43 | 272A/5 | DA+3 | - | GANTRY | S/S GANTRY | 2944.699 | 3130
Total Drum Length in Meter | [6 empty] | 177045.244 | 187069 | 65955.675
Total Drum Length in Km | [6 empty] | 177.0452 | 187.069 | 65.9557