## Stub dispatch (hidden)
Location | Project | Tower type | Structure | B LOT | Actual PRS Date | STEEL Wt (MT) | BNA Wt | Disp Bal | May'24 Disp Plan | Wk01 | WK02 | WK03 | WK04 | Jun'24 Disp Plan MT | July'24 Disp Plan | Remark
JPR | TA416 | DA | Stub - 28 Nos | TA416-00018 | 2024-04-11 | 26.8617 | 0.46323 | 26.8617 | 0 |  |  |  | 0 | 26.8617 | 0 | As on date 160 stub reieved.
JPR | TA416 | DA | Stub - 132 Nos | TA416-00026 | 2024-04-15 | 126.634 | 2.184 | 126.634 | [5 empty] | 126.634 | 0
Total |  |  | 160 | [10 empty] | 153.4957

## Erection - Oct'25
Sl | Location No. | Tower type | Tower Weight | Gang Name | Manpower | Section Incharge | Supervisor | Power Tools Issued (YES/NO) | Material Feeding | Starting Date | Completion Date | Tack-welding | Final checking | Revenue Planned | Revenue Realised
1 | 1/0 | 2D60+0 | 72.63 | Subash | 33 | Mr. Manikandan | Mr. Chandrasekar | No |  | WIP | 2025-10-08 | 2025-10-18 | 2025-10-13 | 661012
2 | 4/3 | 2DA+6 | 37.7169 | Subash | 33 | Mr. Manikandan | Mr. Chandrasekar | No | 2025-10-08 | 2025-10-09 | 2025-10-12 | 2025-10-22 | 2025-10-17 | 347642
3 | 4/1 | 2DA+3 | 33.38 | Subash | 33 | Mr. Manikandan | Mr. Chandrasekar | No | 2025-10-10 | 2025-10-13 | 2025-10-16 | 2025-10-26 | 2025-10-21 | 307108
4 | 4/4 | 2DA+0 | 31.99 | Subash | 33 | Mr. Manikandan | Mr. Chandrasekar | No | 2025-10-15 | 2025-10-17 | 2025-10-20 | 2025-10-30 | 2025-10-25 | 292211
5 | 4/5 | 2DA+3 | 33.38 | Subash | 33 | Mr. Manikandan | Mr. Chandrasekar | No | 2025-10-17 | 2025-10-21 | 2025-10-24 | 2025-11-03 | 2025-10-29 | 307108
6 | 4/8 | 2DA+3 | 33.38 | Subash | 33 | Mr. Manikandan | Mr. Chandrasekar | No | 2025-10-21 | 2025-10-25 | 2025-10-27 | 2025-11-06 | 2025-11-01 | 307108
7 | 4/11 | 2DA+6 | 37.7169 | Subash | 33 | Mr. Manikandan | Mr. Chandrasekar | No | 2025-10-25 | 2025-10-28 | 2025-10-31 | 2025-11-10 | 2025-11-05 | 347642
8 | 4/18 | 2DA+0 | 31.99 | Shakila Khatun | 32 | Mr. Manikandan | Mr. Srinivasan | No |  | Completed | 2025-10-05 | 2025-10-15 | 2025-10-10 | 292211
9 | 9/3 | 2DA+9 | 39.1682 | Shakila Khatun | 32 | Mr. Manikandan | Mr. Srinivasan | No | 2025-10-05 | 2025-10-06 | 2025-10-09 | 2025-10-19 | 2025-10-14 | 362229
10 | 4/19 | 2DA+6 | 37.7169 | Shakila Khatun | 32 | Mr. Manikandan | Mr. Srinivasan | No | 2025-10-07 | 2025-10-10 | 2025-10-14 | 2025-10-24 | 2025-10-19 | 347642
11 | 4/20 | 2DA+9 | 39.1682 | Shakila Khatun | 32 | Mr. Manikandan | Mr. Srinivasan | No | 2025-10-11 | 2025-10-15 | 2025-10-19 | 2025-10-29 | 2025-10-24 | 362229
12 | 4/13 | 2DA+0 | 31.99 | Shakila Khatun | 32 | Mr. Manikandan | Mr. Srinivasan | No | 2025-10-16 | 2025-10-20 | 2025-10-25 | 2025-11-04 | 2025-10-30 | 292211
13 | 4/14 | 2DA+3 | 33.38 | Shakila Khatun | 32 | Mr. Manikandan | Mr. Srinivasan | No | 2025-10-23 | 2025-10-26 | 2025-10-31 | 2025-11-10 | 2025-11-05 | 307108
14 | 39/2 | 3DA+0 | 36.372 | Nasiruddin (Bulbul ) | 24 | Mr. Satyam Tiwari | Mr. Bhimmahto | No |  | WIP | 2025-10-05 | 2025-10-15 | 2025-10-10 | 327992
15 | 39/9 | 3DA+9 | 44.85 | Nasiruddin (Bulbul ) | 24 | Mr. Satyam Tiwari | Mr. Bhimmahto | No | 2025-09-29 | 2025-10-06 | 2025-10-10 | 2025-10-20 | 2025-10-15 | 406294
16 | 36/7 | 3DA+3 | 37.931 | Nasiruddin (Bulbul ) | 24 | Mr. Satyam Tiwari | Mr. Bhimmahto | No | 2025-10-09 | 2025-10-11 | 2025-10-15 | 2025-10-25 | 2025-10-20 | 342752
17 | 36/8 | 3DA+0 | 36.372 | Nasiruddin (Bulbul ) | 24 | Mr. Satyam Tiwari | Mr. Bhimmahto | No | 2025-10-14 | 2025-10-16 | 2025-10-22 | 2025-11-01 | 2025-10-27 | 327992
18 | 37/0 | 3DB2+0 | 54.66 | Nasiruddin (Bulbul ) | 24 | Mr. Satyam Tiwari | Mr. Bhimmahto | No | 2025-10-20 | 2025-10-23 | 2025-10-30 | 2025-11-09 | 2025-11-04 | 478941
19 | 39/7 | 3DA+6 | 43.08 | Sabhnam Praveen | 20 | Mr. Satyam Tiwari | Mr. Anand | No |  | WIP | 2025-10-07 | 2025-10-17 | 2025-10-12 | 391124
20 | 16/11 | 3DA+3 | 37.931 | Sabhnam Praveen | 20 | Mr. Manikandan | Mr. Anand | No | 2025-10-07 | 2025-10-08 | 2025-10-17 | 2025-10-27 | 2025-10-22 | 342752
21 | 11/4 | 3DA+0 | 36.372 | Sabhnam Praveen | 20 | Mr. Manikandan | Mr. Anand | No | 2025-10-15 | 2025-10-18 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 327992
22 | 11/7 | 3DA+0 | 36.372 | Rajiv Yadhav | 22 | Mr. Manikandan | Mr. Ram Asish | No | 2025-10-09 | 2025-10-11 | 2025-10-20 | 2025-10-25 | 2025-10-24 | 327992
23 | 11/8 | 3DA+0 | 36.372 | Rajiv Yadhav | 22 | Mr. Manikandan | Mr. Ram Asish | No | 2025-10-18 | 2025-10-21 | 2025-10-27 | 2025-10-30 | 2025-10-29 | 327992
24 | 43/4 | 3DA+3 | 37.931 | D K Verma | 25 | Mr. Satyam Tiwari | Mr. Sudalaimuthu | yes |  | Completed | 2025-10-07 | 2025-10-17 | 2025-10-12 | 342752
25 | 43/5 | 3DA+9 | 44.85 | D K Verma | 25 | Mr. Satyam Tiwari | Mr. Sudalaimuthu | yes | 2025-09-25 | 2025-10-08 | 2025-10-13 | 2025-10-23 | 2025-10-18 | 406294
26 | 43/3 | 3DA+0 | 36.372 | D K Verma | 25 | Mr. Satyam Tiwari | Mr. Sudalaimuthu | yes | 2025-10-03 | 2025-10-14 | 2025-10-18 | 2025-10-28 | 2025-10-23 | 327992
27 | 41/1 | 3DA+3 | 36.372 | D K Verma | 25 | Mr. Satyam Tiwari | Mr. Sudalaimuthu | yes | 2025-10-12 | 2025-10-19 | 2025-10-24 | 2025-11-03 | 2025-10-29 | 342752
28 | 42/2 | 3DA+0 | 36.372 | D K Verma | 25 | Mr. Satyam Tiwari | Mr. Sudalaimuthu | yes | 2025-10-20 | 2025-10-25 | 2025-10-31 | 2025-11-10 | 2025-11-05 | 327992
|  |  | 1085.8161 | [10 empty] | 9883066
Formulas:
Tack-welding = [Completion Date]+10
Final checking = [Completion Date]+5