## 400kV Summery
|  | TB-507 | DAILY PROGRESS REPORT | [8 empty] | 2026-04-24 11:21
CONTRACTUAL START DATE: |  | 2024-12-06 | 400kV D/C Fatehgarh IV (Section-2)PS - Bhinmal (PG) Transmission Line
CONTRACTUAL FINISH DATE: |  | 2026-06-05
REPORTING DATE |  |  | Client Name : RAJASTHAN IV A POWER TRANSMISSION LTD
TOTAL DAYS |  |  | NOA Ref No(Supply): RIVA/LOA-KEC(SUP)/AUG 24/405
COMP. DAYS |  |  | NOA Ref No(Service): RIVA/LOA-KEC(SER)/AUG 24/406
Progress Summary | [11 empty] | 2026-04-24 11:21
Sl No. | Activity | LOA Quantity | Estimated Line Quantity | Cumm. Progress till Last Month | Plan For APR'25 | Progress in APR'25 | WIP | Today's Progress | Cumulative progress till date | Balance | Gangs working Apr-26 | Remarks
A.i | Route Alignment (Kms) | 184 | 188.678 | 188.678 | 0 | 0 | 0 | 0 | 188.678 | 0 |  | In the Scope of Rajasthan IV A Power Transmission Ltd
ii | Detailed Survey (Kms) | 184 | 188.678 | 188.678 | 0 | 0 | 0 | 0 | 188.678 | 0 |  | 188.678 Kms Approved
iii | Check Survey (Kms) | 184 | 188.678 | 188.678 | 0 | 0 | 0 | 0 | 188.678 | 0 |  | 188.678 KmsApproved
B. | Soil Investigation (Nos) | 73 | 73 | 73 | 0 | 0 | 0 | 0 | 73 | 0
C. | Foundation (Nos) | 508 | 513 | 276 | 33 | 11 | 4 | 1 | 287 | 226 | 4 | Today Com -100/0 WIP-154/1A, 154/2A & 10/14, 11/0 Loc Hold due to ROW - 7/2 & 47/2, Gang Intense Wave MP-13 Idle since 24.4.26
D. | Earthing (Nos) | 508 | 513 | 260 | 33 | 3 |  | 0 | 263 | 250 |  | Today Complete -NIL
E. | Tower Erection (Nos) | 508 | 513 | 188 | 26 | 5 | 2 | 1 | 193 | 320 | 2 | Today com - 10/7 WIP - 8/1 & 7/7
F. | Tack Welding (Nos) | 508 | 513 | 61 | 40 | 19 | 1 | 1 | 80 | 433 | 1 | Today Com -134A/1 WIP - 134A/0
G. | Stringing (Kms)
i | Paying Out (Kms) | 184 | 188.678 | 8.999 | 18.981 | 8.998 | 0.29 |  | 17.997 | 170.681 | 1 | Today Com-NIL WIP- 150/0-151/0 Rly Crossing and 151/0-152/0 Under Preparetion
ii | Final Sag (Kms) | 184 | 188.678 | 7.339 | 18.981 | 8.998 |  |  | 16.337 | 172.341 |  | Today Com-NIL WIP- 150/0-151/0 Lifting Arrangement in Rly Crossing
I. | OPGW Stringing (Kms) | 184 | 188.678 | 0
i | Paying Out (Kms) | 184 | 188.678 | [5 empty] | 0 | 188.678
ii | Final Sag (Kms) | 184 | 188.678 | [5 empty] | 0 | 188.678

## Check Survey
NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE
Client : RAJASTHAN IV A POWER TRANSMISSION LTD.
CONTRACTOR : KEC INTERNATIONAL LIMITED
400 KV CHECK SURVEY
SL No | Section | Section Length | Submission Date | Approval Date | Remarks
1 | AP 51- AP 54 | 2.653 | 2025-01-27 | 2025-02-03 | Approved
2 | AP 54- AP 60 | 5.31 |  |  | Approved
3 | AP 60- AP 75 | 19.672 | 15.02.2025 , 24-02-2025 25-02-2025 | 2025-02-25 | Approved | Required Change
4 | AP 75- AP 92 | 20.273 | 2024-12-31 | 2025-02-03 | Approved
5 | AP 92- AP 96 | 3.084 | 15-02-25 & 21-02-2025 | 2025-02-24 | Approved
6 | AP 96- AP 97 | 1.063 | 2025-02-25 | 2025-02-27 | Approved
7 | AP 97- AP 98B | 2.09 | 2025-02-25 |  | Approved
8 | AP 98B- 99A/0 | 3.893 | 2025-02-25 |  | Approved
9 | AP99A/0-AP 107 | 6.971 | 2025-02-25 |  | Approved
10 | AP 107- AP 121 | 9.495 | 2025-03-05 | 2025-03-06 | Approved
11 | AP 121- AP 131 | 8.697 | 12-03-2025 & ReSubmission 4-04-2025 |  | Submitted | Resubmitted
12 | AP 131- AP 133 | 3.084 |  |  | Submitted
13 | AP 133- AP 134 | 3.963 |  |  | Submitted
14 | AP 134- AP 135 | 1.656 |  |  | Submitted
15 | AP 135- AP 136 | 1.635 |  |  | Submitted
16 | AP 136 - AP 139 | 2.221 |  |  | Submitted
17 | AP 139 - AP 147 | 10.724 | 26-03-2025 Resubmission 4-04-2025 &28-04-25 |  | Submitted | Resubmitted
18 | AP 147/0 - AP 148 | 3.666 | 26-03-2025 Resubmission 4-04-2025 & 28-04-25 |  | Submitted | Resubmitted
19 | AP148/0 - AP 149B | 4.88 |  |  | Submitted
20 | AP 150 to Bhinmal GTY | 2.474 | 2025-04-18 |  | Submitted
21 | AP 50- AP 51 | 0.275 | 2025-04-05 |  | Submitted
22 | AP 47- AP 50 | 2.008 | 2025-04-05 |  | Submitted
23 | AP 46- AP 47 | 0.223 | 2025-04-05 |  | Submitted
24 | AP 42- AP 43 | 2.731 | 2025-04-05 |  | Submitted
25 | AP 45- AP 46 | 1.717 | 2025-04-05 |  | Submitted
26 | AP 43- AP 45 | 1.068 | 2025-04-05 |  | Submitted
27 | AP 40- AP 42 | 2.873 | 2025-04-05 |  | Submitted
28 | AP 10- AP 21 | 19.57 | 16-04-2025 & 16.05.2025 |  | Re Submitted
29 | 21/0-24/0 | 2.618 | 2025-05-04 |  | Complete
30 | 24/0-40/0 | 18.193 | 2025-05-28 |  | Complete
| AS on date | 168.78
Submission of Check Survey
SL. No. | Section | Date of submission | Section Length in kms | Letter Reference Number | Date of Approval | Section Length in kms
1 | AP75 To AP92 | 2024-12-31 | 20.273 | KEC/FBTL/RPTL/TB507/008A | 2025-02-03 | 20.273 | JMC -01
2 | AP51 To AP60 | 2025-01-27 | 7.962 | KEC/FBTL/RPTL/TB507/0014 | 2025-02-03 | 7.962 | JMC -01
3 | AP92 To AP96 | 2025-02-21 | 3.084 | KEC/FBTL/RPTL/TB507/0025 & 0029 | 2025-02-24 | 3.084 | JMC -02
4 | AP60 To AP75 | 2025-02-15 | 19.672 | KEC/FBTL/RPTL/TB507/0025 , 0030 & 0033 | 2025-02-25 | 19.672 | JMC -02
5 | AP96 To AP107 | 2025-02-25 | 14.017 | KEC/FBTL/RPTL/TB507/0032 | 2025-02-27 | 14.017 | JMC -02
6 | AP107 To AP121 | 2025-03-05 | 9.495 | KEC/FBTL/RPTL/TB507/0036 | 2025-03-06 | 9.495 | JMC -03
7 | AP121 To AP131 | 2025-04-04 | 8.697 | KEC/FBTL/RPTL/TB507/0043 ,0050,0061 | 2025-04-16 | 8.697 | JMC -04
8 | AP139 To AP148 | 2025-03-26 | 14.39 | KEC/FBTL/RPTL/TB507/0049 | 2025-04-16 | 14.39 | JMC -04
9 | AP40 To AP51 | 2025-04-05 | 10.894 | KEC/FBTL/RPTL/TB507/0064
10 | AP10 To AP21 | 06-04-2025 & 16.05.2025 | 19.57 | KEC/FBTL/RPTL/TB507/79
11 | AP150 To Bhinmal GTY | 2025-04-18 | 2.474 | KEC/FBTL/RPTL/TB507/0068
12 | AP131-AP 133 | 2025-05-10 | 3.084 | KEC/FBTL/RPTL/TB507/0077
13 | AP136-AP 139 | 2025-05-10 | 2.22 | KEC/FBTL/RPTL/TB507/0077
14 | AP 133-AP 135 | 2025-05-25 | 5.619 | Resubmitted on dated 25/05/2025
15 | AP 99-AP 100 | 2025-05-17 | 3.95 | KEC/FBTL/RPTL/TB507/82 | 2025-06-02
16 | AP 135-AP 136 | 2025-05-25 | 1.635 | KEC/FBTL/RPTL/TB507/0077 on 10/05/25
17 | AP 148-AP 149B | 2025-05-25 | 4.88
Total |  |  | 151.916 |  |  | 97.59
Check Survey
Sr. no | Action by | Section AP To AP | Section length | Approved by Client | Pending by Client | Remarks | JMC
1 | KEC | S/S Gantry To AP-5/0 | 1.609 |  |  | Approved on 17.2.26
2 | KEC | AP 5 to AP 5B | 3.619 | yes | Yes | Approved
3 | KEC | AP 5B To AP 7/0 | 5.374 |  |  | Approved
4 | KEC | AP-7/0 To AP-10/0 | 8.716 |  |  | Approved on 25-07-2025
5 |  | AP-10/0 To AP-21/0 | 19.572 | YES |  | Approved on 16-06-2025 | JMC -04
6 | Apraava | AP-21/0 To AP-24/0 | 2.616 | YES |  | Approved on 23-07-2025
7 | KEC | AP-24/0 To AP-27/0 | 1.428 | YES |  | Approved on 5-09-2025
8 | KEC | AP-27/0 To AP-40/0 | 16.76 |  |  | Approved on 23-07-2025
9 |  | AP-40/0 To AP-45/0 | 6.659 | Yes |  | Approved on 18-06-2025 | JMC -04
10 | KEC | AP-45/0 To AP-48/0 | 3.187 | YES |  | Approved on 18-06-2025
11 |  | AP 48/0 to AP 51/0, | 1.051 | Yes |  | Approved on 18-06-2025 | JMC -04
12 |  | AP-51/0 To AP-60/0 | 7.962 | Yes |  | Approved | JMC -01
13 |  | AP-60/0 To AP-75/0 | 19.567 | Yes |  | Approved | JMC -04
14 |  | AP-75/0 To AP-92/0 | 20.274 | Yes |  | Approved | JMC -01
15 |  | AP-92/0 To AP-96/0 | 3.084 | Yes |  | Approved | JMC -02
16 |  | AP-96/0 To AP-107/0 | 14.119 | Yes |  | Approved | JMC -02
17 |  | AP-107/0 To AP-121/0 | 9.495 | Yes |  | Approved | JMC -03
18 |  | AP-121/0 To AP-131/0 | 8.693 | Yes |  | Approved | JMC -04
19 | KEC | AP-131/0 To AP-139/0 | 12.659 | Yes |  | Approved on 20-06-2025 | JMC -04
20 | KEC | AP-139/0 To AP-148/0 | 14.392 | Yes |  | Approved | JMC -04
21 | KEC | AP-148/0 To AP-153/0 | 6.321 | Yes |  | Approved | JMC -04
22 | Apraava | AP-153/0 To AP-154/0 | 0.732 | Yes |  | Approved on 5-09-2025
23 | KEC | AP-154/0 To AP-155/0 | 0.218 | Yes |  | Approved on 5-09-2025
24 | Apraava | AP-155/0 To S/S Gantry | 0.571 | Yes |  | Approved on 5-09-2025
|  | TOTAL | 188.678
TOTAL |  |  |  | 188.678
Check Survey Submitted |  |  |  | 188.678
Check Survey Approved |  |  |  | 188.678
Balance for Approval by Client |  |  |  | 0
Check Survey Approval Pending |  |  |  | 0 | 13.1
Sr. no | Section AP To AP | Section length | Check Survey | Details Survey | Remarks
1 | S/S Gantry To AP-7/0 | 10.369 | YES | YES | Details Survey Completed. Profile & Tower Schedule Submitted with Apraava Engg.
2 | AP-7/0 To AP-10/0 | 8.713 | YES |  | Approved
3 | AP-10/0 To AP-21/0 | 19.57 | YES |  | Approved
4 | AP-21/0 To AP-24/0 | 2.618 | YES |  | Approved
5 | AP-24/0 To AP-27/0 | 1.44 | YES |  | Check Survey Completed. Profile & Tower Schedule Submitted with Apraava Engg.
6 | AP-27/0 To AP-40/0 | 16.759 | YES |  | Approved
7 | AP-40/0 To AP-45/0 | 6.672 | YES |  | Approved
8 | AP-45/0 To AP-48/0 | 3.172 | YES | YES | Details Survey Completed. Profile & Tower Schedule Submitted with Apraava Engg.
9 | AP 48/0 to AP 51/0, | 1.05 | Yes |  | Approved
10 | AP-51/0 To AP-60/0 | 7.962 | Yes |  | Approved
11 | AP-60/0 To AP-75/0 | 19.567 | Yes |  | Approved
12 | AP-75/0 To AP-92/0 | 20.273 | Yes |  | Approved
13 | AP-92/0 To AP-96/0 | 3.084 | Yes |  | Approved
14 | AP-96/0 To AP-107/0 | 14.119 | Yes |  | Approved
15 | AP-107/0 To AP-121/0 | 9.495 | Yes |  | Approved
16 | AP-121/0 To AP-131/0 | 8.697 | Yes |  | Approved
17 | AP-131/0 To AP-139/0 | 12.65 | Yes |  | Approved
18 | AP-139/0 To AP-148/0 | 14.392 | Yes |  | Approved
19 | AP-148/0 To AP-153/0 | 6.321 | Yes |  | Approved
20 | AP-153/0 To S/S Gantry | 1.521 | Yes |  | Check Survey Completed. Profile & Tower Schedule Submitted with Apraava Engg.
| TOTAL | 188.444

## Check Survey Status (hidden)
NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE
Client : RAJASTHAN IV A POWER TRANSMISSION LTD.
CONTRACTOR : KEC INTERNATIONAL LIMITED
400 KV CHECK SURVEY
SL No | Section | Section Length | Submission Date | Approval Date | Remarks
1 | AP 51- AP 54 | 2.653 | 2025-01-27 | 2025-02-03 | Approved
2 | AP 54- AP 60 | 5.31 |  |  | Approved
3 | AP 60- AP 75 | 19.672 | 15.02.2025 , 24-02-2025 25-02-2025 | 2025-02-25 | Approved | Required Change
4 | AP 75- AP 92 | 20.273 | 2024-12-31 | 2025-02-03 | Approved
5 | AP 92- AP 96 | 3.084 | 15-02-25 & 21-02-2025 | 2025-02-24 | Approved
6 | AP 96- AP 97 | 1.063 | 2025-02-25 | 2025-02-27 | Approved
7 | AP 97- AP 98B | 2.09 | 2025-02-25 |  | Approved
8 | AP 98B- 99A/0 | 3.893 | 2025-02-25 |  | Approved
9 | AP99A/0-AP 107 | 6.971 | 2025-02-25 |  | Approved
10 | AP 107- AP 121 | 9.495 | 2025-03-05 | 2025-03-06 | Approved
11 | AP 121- AP 131 | 8.697 | 12-03-2025 & ReSubmission 4-04-2025 |  | Submitted | Resubmitted
12 | AP 131- AP 133 | 3.084 |  |  | Submitted
13 | AP 133- AP 134 | 3.963 |  |  | Submitted
14 | AP 134- AP 135 | 1.656 |  |  | Submitted
15 | AP 135- AP 136 | 1.635 |  |  | Submitted
16 | AP 136 - AP 139 | 2.221 |  |  | Submitted
17 | AP 139 - AP 147 | 10.724 | 26-03-2025 Resubmission 4-04-2025 &28-04-25 |  | Submitted | Resubmitted
18 | AP 147/0 - AP 148 | 3.666 | 26-03-2025 Resubmission 4-04-2025 & 28-04-25 |  | Submitted | Resubmitted
19 | AP148/0 - AP 149B | 4.88 |  |  | Submitted
20 | AP 150 to Bhinmal GTY | 2.474 | 2025-04-18 |  | Submitted
21 | AP 50- AP 51 | 0.275 | 2025-04-05 |  | Submitted
22 | AP 47- AP 50 | 2.008 | 2025-04-05 |  | Submitted
23 | AP 46- AP 47 | 0.223 | 2025-04-05 |  | Submitted
24 | AP 42- AP 43 | 2.731 | 2025-04-05 |  | Submitted
25 | AP 45- AP 46 | 1.717 | 2025-04-05 |  | Submitted
26 | AP 43- AP 45 | 1.068 | 2025-04-05 |  | Submitted
27 | AP 40- AP 42 | 2.873 | 2025-04-05 |  | Submitted
28 | AP 10- AP 21 | 19.57 | 16-04-2025 & 16.05.2025 |  | Re Submitted
29 | 21/0-24/0 | 2.618 | 2025-05-04 |  | Complete
30 | 24/0-40/0 | 18.193 | 2025-05-28 |  | Complete
| AS on date | 168.78
Submission of Check Survey
SL. No. | Section | Date of submission | Section Length in kms | Letter Reference Number | Date of Approval | Section Length in kms
1 | AP75 To AP92 | 2024-12-31 | 20.273 | KEC/FBTL/RPTL/TB507/008A | 2025-02-03 | 20.273
2 | AP51 To AP60 | 2025-01-27 | 7.962 | KEC/FBTL/RPTL/TB507/0014 | 2025-02-03 | 7.962
3 | AP92 To AP96 | 2025-02-21 | 3.084 | KEC/FBTL/RPTL/TB507/0025 & 0029 | 2025-02-24 | 3.084
4 | AP60 To AP75 | 2025-02-15 | 19.672 | KEC/FBTL/RPTL/TB507/0025 , 0030 & 0033 | 2025-02-25 | 19.672
5 | AP96 To AP107 | 2025-02-25 | 14.017 | KEC/FBTL/RPTL/TB507/0032 | 2025-02-27 | 14.017
6 | AP107 To AP121 | 2025-03-05 | 9.495 | KEC/FBTL/RPTL/TB507/0036 | 2025-03-06 | 9.495
7 | AP121 To AP131 | 2025-04-04 | 8.697 | KEC/FBTL/RPTL/TB507/0043 ,0050,0061 | 2025-03-16 | 8.697
8 | AP139 To AP148 | 2025-03-26 | 14.39 | KEC/FBTL/RPTL/TB507/0049 | 2025-03-16 | 14.39
9 | AP40 To AP51 | 2025-04-05 | 10.894 | KEC/FBTL/RPTL/TB507/0064
10 | AP10 To AP21 | 06-04-2025 & 16.05.2025 | 19.57 | KEC/FBTL/RPTL/TB507/79
11 | AP150 To Bhinmal GTY | 2025-04-18 | 2.474 | KEC/FBTL/RPTL/TB507/0068
12 | AP131-AP 133 | 2025-05-10 | 3.084 | KEC/FBTL/RPTL/TB507/0077
13 | AP136-AP 139 | 2025-05-10 | 2.22 | KEC/FBTL/RPTL/TB507/0077
14 | AP 133-AP 135 | 2025-05-25 | 5.619 | Resubmitted on dated 25/05/2025
15 | AP 99-AP 100 | 2025-05-17 | 3.95 | KEC/FBTL/RPTL/TB507/82 | 2025-06-02
16 | AP 135-AP 136 | 2025-05-25 | 1.635 | KEC/FBTL/RPTL/TB507/0077 on 10/05/25
17 | AP 148-AP 149B | 2025-05-25 | 4.88
Total |  |  | 151.916 |  |  | 97.59
Check Survey
Sr. no | Action by | Section AP To AP | Section length | Approved by Client | Pending by Client | Remarks
1 | KEC | S/S Gantry To AP-7/0 | 10.373 |  |  | Details Survey Completed. Profile Preperation in process with KEC Engg.
2 | KEC | AP-7/0 To AP-10/0 | 8.719 |  |  | Submitted on 3.07.2025,
3 |  | AP-10/0 To AP-21/0 | 19.57 | YES |  | Approved
4 | Apraava | AP-21/0 To AP-24/0 | 2.618 |  | YES | Hard Copy Submitted on 24-06-2025
5 | KEC | AP-24/0 To AP-40/0 | 18.193 |  |  | Submited on 30.06.2025
6 |  | AP-40/0 To AP-45/0 | 6.659 | Yes |  | Approved on 18-06-2025
7 | KEC | AP-45/0 To AP-48/0 | 3.17 |  |  | Profile Preperation in process with KEC Engg.
8 |  | AP 48/0 to AP 51/0, | 1.05 | Yes |  | Approved on 18-06-2025
9 |  | AP-51/0 To AP-60/0 | 7.962 | Yes |  | Approved
10 |  | AP-60/0 To AP-75/0 | 19.567 | Yes |  | Approved
11 |  | AP-75/0 To AP-92/0 | 20.273 | Yes |  | Approved
12 |  | AP-92/0 To AP-96/0 | 3.084 | Yes |  | Approved
13 |  | AP-96/0 To AP-107/0 | 14.119 | Yes |  | Approved
14 |  | AP-107/0 To AP-121/0 | 9.495 | Yes |  | Approved
15 |  | AP-121/0 To AP-131/0 | 8.694 | Yes |  | Approved
16 | KEC | AP-131/0 To AP-139/0 | 12.559 | Yes |  | Approved
17 | KEC | AP-139/0 To AP-148/0 | 14.391 | Yes |  | Approved
18 | KEC | AP-148/0 To AP-153/0 | 6.321 | Yes |  | Approved
19 | Apraava | AP-153/0 To AP-154/0 | 0.389 |  | Yes
20 | KEC | AP-154/0 To AP-155/0 | 0.22 |  |  | Underneath crossing proposal under process with KEC Engg.
21 | Apraava | AP-155/0 To S/S Gantry | 0.57 |  | Yes | Submitted on 16.04.2025,
|  | TOTAL | 187.996
|  |  |  | 2.618 | AP 21 to AP 24
TOTAL |  |  |  | 187.996
Check Survey Submitted |  |  |  | 156.04
Check Survey Approved |  |  |  | 152.463
Balance for Approval by Client |  |  |  | 3.577
Check Survey report to be Submitted |  |  |  | 31.956
Check Survey
| Sr.no | Section AP To AP | Section length | Approved | Resposnibility | Remarks
| 1 | AP-1/0 To AP-10/0 | 18.116 |  | M/s Kec | Rerouting confirmation given on 12.06.2025 to carry out detail survey, When will be the survey started
| 2 | AP-10/0 To AP-21/0 | 19.57 |  | M/s Apraava | Will be approved by 17.06.2025
| 3 | AP-21/0 To AP-40/0 | 20.811 |  | M/s Kec | From AP 21 to AP 24 and AP 27 to AP 40 has to be submitted. From AP 24 to AP 27 Underneath data has also to be submitted. When it will be submitted
| 4 | AP-40/0 To AP 45 and AP 48 to AP 51/0 | 10.894 |  | M/s Apraava | From AP 40 to AP 45, AP 48 to AP 51 will be approved by 17.06.2025
|  | AP 45 to AP 48 |  |  | M/s Kec | Railway crossing detail survey profile, Tower Schedule yet not provided, When will we get this.
| 5 | AP-51/0 To AP-60/0 | 7.962 | 2025-02-03
| 6 | AP-60/0 To AP-75/0 | 19.567 | 2025-02-25
| 7 | AP-75/0 To AP-92/0 | 20.273 | 2025-02-03
| 8 | AP-92/0 To AP-96/0 | 3.084 | 2025-02-24
| 9 | AP-96/0 To AP-107/0 | 14.017 | 2025-02-27
| 10 | AP-107/0 To AP-121/0 | 9.495 | 2025-03-06
| 11 | AP-121/0 To AP-131/0 | 8.694 | 2025-04-16
| 12 | AP-131/0 To AP-133/0 | 3.084 |  | M/s Kec | Yet not submitted
| 13 | AP-133/0 To AP-135/0 | 5.619 |  | M/s Kec | Yet not submitted
| 14 | AP-135/0 To AP-139/0 | 3.856 |  | M/s Kec | Yet not submitted
| 15 | AP-139/0 To AP-148/0 | 14.391 | 2025-04-16
| 16 | AP-148/0 To AP-150/0 | 5.268 |  | M/s Apraava | Will be approved by 17.06.2025
| 17 | AP-150/0 To AP-157/0 | 2.474 | 2025-04-18 | M/s Apraava & M/s Kec | Under discussion due to Underneath crossing at 154/0 to 155/0 and railway proposal crossing 150/0 to 151/0.
|  | Total | 187.175

## Check Survey (hidden)
NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE
Client : RAJASTHAN IV A POWER TRANSMISSION LTD.
CONTRACTOR : KEC INTERNATIONAL LIMITED
400 KV CHECK SURVEY
SL No | Section | Section Length | Submission Date | Approval Date | Remarks
1 | AP 51- AP 54 | 2.653 | 2025-01-27 | 2025-02-03 | Approved
2 | AP 54- AP 60 | 5.31 |  |  | Approved
3 | AP 60- AP 75 | 19.672 | 15.02.2025 , 24-02-2025 25-02-2025 | 2025-02-25 | Approved | Required Change | Approved | 97.59
4 | AP 75- AP 92 | 20.273 | 2024-12-31 | 2025-02-03 | Approved
5 | AP 92- AP 96 | 3.084 | 15-02-25 & 21-02-2025 | 2025-02-24 | Approved |  | Submitted | 151.916
6 | AP 96- AP 97 | 1.063 | 2025-02-25 | 2025-02-27 | Approved
7 | AP 97- AP 98B | 2.09 | 2025-02-25 |  | Approved
8 | AP 98B- 99A/0 | 3.893 | 2025-02-25 |  | Approved
9 | AP99A/0-AP 107 | 6.971 | 2025-02-25 |  | Approved
10 | AP 107- AP 121 | 9.495 | 2025-03-05 | 2025-03-06 | Approved
11 | AP 121- AP 131 | 8.697 | 12-03-2025 & ReSubmission 4-04-2025 |  | Submitted | Resubmitted
12 | AP 131- AP 133 | 3.084 |  |  | Submitted
13 | AP 133- AP 134 | 3.963 |  |  | Submitted
14 | AP 134- AP 135 | 1.656 |  |  | Submitted
15 | AP 135- AP 136 | 1.635 |  |  | Submitted
16 | AP 136 - AP 139 | 2.221 |  |  | Submitted
17 | AP 139 - AP 147 | 10.724 | 26-03-2025 Resubmission 4-04-2025 &28-04-25 |  | Submitted | Resubmitted
18 | AP 147/0 - AP 148 | 3.666 | 26-03-2025 Resubmission 4-04-2025 & 28-04-25 |  | Submitted | Resubmitted |  |  | Blance | 187.176
19 | AP148/0 - AP 149B | 4.88 |  |  | Submitted
20 | AP 150 to Bhinmal GTY | 2.474 | 2025-04-18 |  | Submitted
21 | AP 50- AP 51 | 0.275 | 2025-04-05 |  | Submitted
22 | AP 47- AP 50 | 2.008 | 2025-04-05 |  | Submitted
23 | AP 46- AP 47 | 0.223 | 2025-04-05 |  | Submitted
24 | AP 42- AP 43 | 2.731 | 2025-04-05 |  | Submitted
25 | AP 45- AP 46 | 1.717 | 2025-04-05 |  | Submitted
26 | AP 43- AP 45 | 1.068 | 2025-04-05 |  | Submitted
27 | AP 40- AP 42 | 2.873 | 2025-04-05 |  | Submitted
28 | AP 10- AP 21 | 19.57 | 16-04-2025 & 16.05.2025 |  | Re Submitted
29 | 21/0-24/0 | 2.618 | 2025-05-04 |  | Complete
30 | 24/0-40/0 | 18.193 | 2025-05-28 |  | Complete |  |  | 25.321
| AS on date | 168.78
Submission of Check Survey
SL. No. | Section | Date of submission | Section Length in kms | Letter Reference Number | Date of Approval | Section Length in kms | Approved By | Remarks
1 | AP75 To AP92 | 2024-12-31 | 20.273 | KEC/FBTL/RPTL/TB507/008A | 2025-02-03 | 20.273 | Gundewadi Mallappa
2 | AP51 To AP60 | 2025-01-27 | 7.962 | KEC/FBTL/RPTL/TB507/0014 | 2025-02-03 | 7.962 | Gundewadi Mallappa
3 | AP92 To AP96 | 2025-02-21 | 3.084 | KEC/FBTL/RPTL/TB507/0025 & 0029 | 2025-02-24 | 3.084 | Gundewadi Mallappa | Resubmission on dated 21/02/2025
4 | AP60 To AP75 | 2025-02-15 | 19.672 | KEC/FBTL/RPTL/TB507/0025 , 0030 & 0033 | 2025-02-25 | 19.672 | Gundewadi Mallappa | Resubmission on dated 24/02/2025 & 25/02/2025
5 | AP96 To AP107 | 2025-02-25 | 14.017 | KEC/FBTL/RPTL/TB507/0032 | 2025-02-27 | 14.017 | Gundewadi Mallappa
6 | AP107 To AP121 | 2025-03-05 | 9.495 | KEC/FBTL/RPTL/TB507/0036 | 2025-03-06 | 9.495 | Gundewadi Mallappa
7 | AP121 To AP131 | 2025-04-04 | 8.697 | KEC/FBTL/RPTL/TB507/0043 ,0050,0061 | 2025-03-16 | 8.697 | Gundewadi Mallappa | Resubmission on dated 04/04/2025
8 | AP139 To AP148 | 2025-03-26 | 14.39 | KEC/FBTL/RPTL/TB507/0049 | 2025-03-16 | 14.39 | Gundewadi Mallappa | Resubmission on dated 04/04/2025
9 | AP40 To AP51 | 2025-04-05 | 10.894 | KEC/FBTL/RPTL/TB507/0064
10 | AP10 To AP21 | 06-04-2025 & 16.05.2025 | 19.57 | KEC/FBTL/RPTL/TB507/79 |  |  |  | Resubmission on dated 16/05/2025
11 | AP150 To Bhinmal GTY | 2025-04-18 | 2.474 | KEC/FBTL/RPTL/TB507/0068
12 | AP131-AP 133 | 2025-05-10 | 3.084 | KEC/FBTL/RPTL/TB507/0077 |  |  |  | Resubmission on dated 10/05/2025
13 | AP136-AP 139 | 2025-05-10 | 2.22 | KEC/FBTL/RPTL/TB507/0077 |  |  |  | Resubmission on dated 10/05/2025
14 | AP 133-AP 135 | 2025-05-25 | 5.619 | Resubmitted on dated 25/05/2025 |  |  |  | Resubmission on dated 25/05/2025
15 | AP 99-AP 100 | 2025-05-17 | 3.95 | KEC/FBTL/RPTL/TB507/82 | 2025-06-02 |  |  | Resubmission on dated 16/05/2025
16 | AP 135-AP 136 | 2025-05-25 | 1.635 | KEC/FBTL/RPTL/TB507/0077 on 10/05/25 |  |  |  | Resubmission on dated 25/05/2025
17 | AP 148-AP 149B | 2025-05-25 | 4.88 |  |  |  |  | Resubmission on dated 25/05/2025
Resubmission on dated 25/05/2025
Total |  |  | 151.916 |  |  | 97.59
Check Survey
Action by | Sr.no | Section AP To AP | Section length | Approved by Client | Pending by Client | Remarks | Apraava Comments
Apraava | 1 | AP-1/0 To AP-7/0 | 9.4 |  |  | Details Survey Completed | Discussion and coordination with Statcraft are ongoing. Awaiting their response
| 2 | AP-7/0 To AP-10/0 | 9.096 |  |  | Check Survry Completed
KEC | 3 | AP-10/0 To AP-21/0 | 19.57 |  | YES | Approved | KEC was to submit a proposal avoiding the shifting of the 11 kV line; their response is still awaited. The rest of the profile is acceptable—awaiting a hard-signed copy along with revised tower schdule from the KEC team for official release
| 4 | AP-21/0 To AP-24/0 | 2.618 |  |  | Hard Copy Submitted on 24-06-2025
KEC | 5 | AP-24/0 To AP-40/0 | 18.193 |  | 2025-05-07 | AP 27 to AP 40(16.753Km) CS completed and Profile Under Process in KEC Engg, GTY position finalization at AP 24 to AP 27(1.440 KM) | Check Survey for two oil/gas pipeline crossings is awaited, and the re-survey for the 400kV line crossing between AP25 to AP26 (underneath crossing) is pending from KEC.
KEC | 6 | AP-40/0 To AP-45/0 | 6.659 |  |  | Approved on 18-06-2025
KEC | 7 | AP-45/0 To AP-48/0 | 3.17 |  |  | Hold due to Railway crossing angle 870 to 900 | Re-survey for the railway crossing between AP46 and AP47, due to alignment change from 86° to 90°, is pending from KEC.
KEC | 8 | AP 48/0 to AP 51/0, | 1.05 |  | 2025-04-05 | Approved on 18-06-2025
KEC | 9 | AP-51/0 To AP-60/0 | 7.962 | 2025-02-03 |  | Approved | Tower schedule has been approved; however, the profile as per the approved check survey is still awaited from KEC
| 10 | AP-60/0 To AP-75/0 | 19.567 | 2025-02-25 |  | Approved
| 11 | AP-75/0 To AP-92/0 | 20.273 | 2025-02-03 |  | Approved
| 12 | AP-92/0 To AP-96/0 | 3.084 | 2025-02-24 |  | Approved
| 13 | AP-96/0 To AP-107/0 | 14.119 | 2025-02-27 |  | Approved
| 14 | AP-107/0 To AP-121/0 | 9.495 | 2025-03-06 |  | Approved
| 15 | AP-121/0 To AP-131/0 | 8.694 | 2025-04-16 |  | Approved
KEC | 16 | AP-131/0 To AP-139/0 | 12.559 |  | YES | Approved | Location of AP132 has been changed due to the presence of a house within the corridor; revised check survey and profile are awaited from KEC."
KEC | 17 | AP-139/0 To AP-148/0 | 14.391 | 2025-04-16 |  | Approved | Tower schedule has been approved; however, the profile as per the approved check survey is still awaited from KEC
KEC | 18 | AP-148/0 To AP-150/0 | 5.268 |  | 2025-05-23 | Approved | Hard signed profile & Tower schudle copies are awaited from KEC to offical realse.
KEC | 19 | AP-150/0 To AP-157/0 | 2.474 | 2025-04-18 |  | Approval pending from Engg Team | Re-survey for the 400kV line crossing between AP154 to AP155 (underneath crossing) is pending from KEC.
187.642
|  |  | CS Submitted | 166.062
|  |  |  | 2.618 | AP 21 to AP 24
|  |  | TOTAL | 187.642
|  |  | Approved | 145.165
|  |  | Balance | 42.477
Check Survey
| Sr.no | Section AP To AP | Section length | Approved | Resposnibility | Remarks
| 1 | AP-1/0 To AP-10/0 | 18.116 |  | M/s Kec | Rerouting confirmation given on 12.06.2025 to carry out detail survey, When will be the survey started
| 2 | AP-10/0 To AP-21/0 | 19.57 |  | M/s Apraava | Will be approved by 17.06.2025
| 3 | AP-21/0 To AP-40/0 | 20.811 |  | M/s Kec | From AP 21 to AP 24 and AP 27 to AP 40 has to be submitted. From AP 24 to AP 27 Underneath data has also to be submitted. When it will be submitted
| 4 | AP-40/0 To AP 45 and AP 48 to AP 51/0 | 10.894 |  | M/s Apraava | From AP 40 to AP 45, AP 48 to AP 51 will be approved by 17.06.2025
|  | AP 45 to AP 48 |  |  | M/s Kec | Railway crossing detail survey profile, Tower Schedule yet not provided, When will we get this.
| 5 | AP-51/0 To AP-60/0 | 7.962 | 2025-02-03
| 6 | AP-60/0 To AP-75/0 | 19.567 | 2025-02-25
| 7 | AP-75/0 To AP-92/0 | 20.273 | 2025-02-03
| 8 | AP-92/0 To AP-96/0 | 3.084 | 2025-02-24
| 9 | AP-96/0 To AP-107/0 | 14.017 | 2025-02-27
| 10 | AP-107/0 To AP-121/0 | 9.495 | 2025-03-06
| 11 | AP-121/0 To AP-131/0 | 8.694 | 2025-04-16
| 12 | AP-131/0 To AP-133/0 | 3.084 |  | M/s Kec | Yet not submitted
| 13 | AP-133/0 To AP-135/0 | 5.619 |  | M/s Kec | Yet not submitted
| 14 | AP-135/0 To AP-139/0 | 3.856 |  | M/s Kec | Yet not submitted
| 15 | AP-139/0 To AP-148/0 | 14.391 | 2025-04-16
| 16 | AP-148/0 To AP-150/0 | 5.268 |  | M/s Apraava | Will be approved by 17.06.2025
| 17 | AP-150/0 To AP-157/0 | 2.474 | 2025-04-18 | M/s Apraava & M/s Kec | Under discussion due to Underneath crossing at 154/0 to 155/0 and railway proposal crossing 150/0 to 151/0.
|  | Total | 187.175

## Sheet8 (hidden)
S No. | MOM as on 11/6/25 | Timeline | Responsibility | Status as on 19/6/25
1 | 400kv Detail Survey from AP 01 to AP 10
a | Apraava will give clearance for further proceeding of Detail Survey | 2025-06-13 | M/S Apraava | Clearance provided for Detail Survey
b | Completion of Detail Survey | 2025-06-25 | M/S KEC | Detail Survey work under progress
c | Detail Survey of 765 kV is submitted by KEC, observation raised by Apraava, KEC has to re-submitted according to observation | 2025-06-16 | M/S KEC | Reobservation mail by Engg. Team on dt. 19.06.25
2 | Check Survey
a | 50 km will be approved | 2025-06-12 | M/S Apraava & KEC | 33 km Approved & 15 km submitted by KEC
b | Pending Section of 21 km will be approved | 2025-06-20 | M/S Apraava & KEC | Under Progress
c | Check Survey of 765kV is to be submitted by KEC | 2026-06-25 | M/S KEC | Detail Survey work under progress
3 | Statutory Approvals
a | 02 No NH Proposal Submission | 2025-06-30 | M/S KEC | Under Progress
b | 02 No Railway Proposal Submission | 2025-06-30 | M/S KEC | Under Progress
c | 02 Nos PLC Proposal of 400 kV Underneath has to Submit | ASAP | M/S KEC | Under Progress
d | Statutory Approvals tracker to be maintain for monitoring current status of NOC | N/A | M/S Apraava & KEC | Under Progress
e | 04 Submission of SH Proposal to SH Authority | 2025-06-20 | M/S Apraava | Under Progress
f | 03 Submission of Oil Proposal to Oil Authority | 2025-06-20 | M/s Apraava | Under Progress
4 | Deployment of surveyor, supervisors, engineers & section in charge to be expedite in Bhinmal Section | 2025-06-12 | M/S KEC | Under Progress
5 | KEC committed 43 nos. foundation for this month & accordingly Apraava will provide ROW clearance | 2025-06-30 | M/S Apraava & KEC | Till date 13 foundations completed, 10 are in WIP and 30 work fronts are available
6 | Manpower in each foundation gang need to be strengthen with at least 8-10 manpower/gang | ASAP | M/S KEC | Under Progress
7 | Apraava asked to increase 4 more foundation gangs to expedite foundation work (currently 7 gangs are available with insufficient manpower | ASAP | M/S KEC | 9 Gangs are available (insufficient manpower in 4 gangs)
8 | 40 Nos Departmental Manpower availability at site | 2025-06-30 | M/S KEC | -
9 | Quality Constraints
a | Information regarding supply of cement with prior & proper documentation | N/A | M/S KEC | -
b | Material availability at site from approved source | - | M/S KEC | -
c | Approval of use of Curing compound in foundation work need to be expedite after jointly discussion of both team | ASAP | M/S Apraava & KEC | Cubes taken after applying curing compound & further process is u/p
d | CTM Machine at store need be installed on priority for cube testing | 2025-06-13 | M/S KEC | Under Progress
10 | Erection team to be deployed and erection to be start | 2025-06-18 | M/S KEC | Erection to be start by Monday, 23/6/25
11 | July month foundation & erection plan to be shared by KEC | 2025-06-16 | M/S KEC | July month plan to be shared within 2-3 days by KEC
12 | Supply of conductor to be start in September month | 2025-09-30 | M/S Apraava | Planned for September month
13 | Total 121 nos. of DA type of tower supplied to store & 2nd lot of 74 nos. towers (approx. 1500 MT) supply, consisting of DC & DD type towers are scheduled for next month | 2025-07-10 | M/S KEC | DA type towers are supplied

## Sheet2 (hidden)
400kV D/C Fatehgarh IV (Section-2)PS - Bhinmal (PG) Transmission Line
Sl No | Section AP To AP | Section length | Remarks
1 | AP-21/0 To AP-24/0 | 2.618
2 | AP-24/0 To AP-27/0 | 1.428
3 | AP-27/0 To AP-40/0 | 16.76
4 | AP-45/0 To AP-48/0 | 3.187
5 | AP-153/0 To AP-154/0 | 0.732
6 | AP-154/0 To AP-155/0 | 0.218
7 | AP-155/0 To S/S Gantry | 0.571
| TOTAL | 25.514
765kV D/C Fatehgarh IV (Section-2)PS - Bhinmal (PG) Transmission Line
Sl No | Section AP To AP | Section length | Route Allignment,Detail Survey,Check survey
| LI | 7.584
| LO | 6.951
| TOTAL | 14.535

## Project Details
Project Code | Project Name | Client Name | LOA Start Date | LOA End Date | Planning Engineer | PCH | Regional Manager | Project Manger | Section Incharge | Supervisor/Engineer
TB 507 | 400kV D/C Fatehgarh IV (Section-2)PS - Bhinmal (PG) Transmission Line | RAJASTHAN IV A POWER TRANSMISSION LTD | 23.08.2024 | 22.02.2026 | Mr. Amartya sarkar | Mr. N K Gupta |  | Mr.ALOK SINHA | Mr.ALOK JANA Mr. VARUN TYAGI

## Statutory Clearence
Rajasthan IV A 400 KV LINE - STATUTORY APPROVAL STATUS
| KEC RESPONSIBILITY |  |  |  | APRAAVA RESPONSIBILITY
S N | Loc No. | Line Crossing | Asset Owner | Submission by KEC | Submission to Asset Owner | Date of Joint site visit | Demand letter from Asset Owner | Letter submission/ Demand fulfillment | Date of NOC/ Approval | Target date for NOC | Status as on 31-03-2026 | Remarks
Power Line Crossing for Line (12 Nos)
1 | AP 2 - 3/1 | 400KV D/C | APRAAVA | 01.02.2026 | 01.02.2026 |  |  |  | Approved |  | PL crossing Apraava's Line. Technical team approved during check survey
2 | AP4-AP5 | 220KV D/C | AMPIN | 01.04.2026 | [5 empty] | 30.04.2026
3 | AP 5D - AP 5E | 132KV S/C | RRVPNL | 21.02.2026 | 06.03.2026 |  |  |  |  | 15.04.2026 | Joint Site visit planned by 7th April
4 | AP 6D/5 - AP 7/0 | 132KV D/C | RRVPNL | 21.02.2026 | 06.03.2026 |  |  |  |  | 15.04.2026 | Joint Site visit planned by 7th April
5 | AP25 - AP 26 | 400KV D/C | RRVPNL | 25.09.2025 | DONE | DONE |  |  | 07.11.2025
6 | AP 27- AP 27A | 220KV S/C | RRVPNL | 24.05.2025 | 30.05.2025 | 31.08.2025 |  |  | 07.11.2025 |  |  | Demand letter awiated
7 | AP 50-AP 51 | 220KV S/C | RRVPNL | 24.05.2025 | 30.05.2025 | 26.08.2025 |  |  | 07.11.2025 |  |  | Demand letter awiated | Barmer
8 | AP 58-AP 59 | 132KV S/C | RRVPNL | 24.05.2025 | 30.05.2025 | 31.08.2025 |  |  | 07.11.2025 |  |  | Demand letter awiated
9 | AP 111-AP 112 | 132KV S/C | RRVPNL | 24.05.2025 | 05.06.2025 | 30.06.2025 |  |  | 28.08.2025
10 | AP 144-AP 145 | 132KV S/C | RRVPNL | 24.05.2025 | 05.06.2025 | 30.06.2025 |  |  | 28.08.2025 |  |  |  | Sirohi
11 | AP 152-AP 153 | 220KV D/C | RRVPNL | 24.05.2025 | 05.06.2025 | 30.06.2025 |  |  | 28.08.2025
12 | AP 154-AP 155 | 400KV D/C | RRVPNL | 25.09.2025 | 21.11.2025 | 28.01.2026 |  |  | 17.02.2026
NH/Expressway Crossing (02 Nos)
1 | AP 43 - AP 44 | Barmer-Jodhpur National Highway-25 | NHAI | 14.07.2025 | 14.07.2025 | 06.10.2025 |  |  |  | 15.04.2026 | Demand letter expected by 7th April
2 | AP 121 - AP 122 | Jamnagar-Amritsar Bharat Mala Expressway NH -754 | NHAI | 14.07.2025 | 14.07.2025 | 08.09.2025 | 28.10.2025 | 21.11.2025 | 06.12.2025
Railway Crossing (02 Nos)
1 | AP 46 - AP 47 | Barmer-Jodhpur Single Track Electrified | NWR | 14.07.2025 | 03.08.2025 | 27.08.2025 | 13.11.2025 | 19.11.2025 | 13.11.2025
2 | AP 150 - AP 151 | Jalore-Bhinmal Single Track Electrified | NWR | 14.07.2025 | 03.08.2025 | 18.08.2025 | 13.11.2025 | 19.11.2025 | 13.11.2025
SH Crossing (07 Nos)
1 | 5/6 - AP 5A/0 | SH- 65 Sheo - Phalsund | PWD | 01.04.2026 | [5 empty] | 30.04.2026
2 | AP 53-AP 54 | Baytu (Balotra Road) -Chava (Barmer Road) | PWD | 31.05.2025 | 25.06.2025 | 13.08.2025 |  |  | 15.10.2025
3 | AP 71 - 71/1 | Barmer-Sindhari | PWD | 31.05.2025 | 25.06.2025 | 26.08.2025 | 24.09.2025 | 2025-11-03 | 2025-11-14
4 | AP 92- AP 93 | Sindhari-Gudamalani | PWD | 31.05.2025 | 25.06.2025 |  |  |  | 21.08.2025
5 | 103/1-104/0 | Bagoda-Sindhari SH | PWD | 21.02.2026 | 06.03.2026 |  |  |  |  | 15.04.2026 | Joint Site visit planned by 7th April
6 | 130/1 - AP 131 | Bagoda-Sayla | PWD | 31.05.2025 | 25.06.2025 | 26.08.2025 | 24.09.2025 | 2025-11-03 | 2025-11-14
7 | AP 147/9 - AP 148 | Siyawat/Daspa- Bhinmal | PWD | 31.05.2025 | 25.06.2025 | 26.08.2025 | 24.09.2025 | 2025-11-03 | 2025-11-14
Oil Line Crossing (06 Nos) | [11 empty] | Required document for final approval
1 | AP 29 - AP 29/1 | OIL Line | Vedanta Cairn Oil & Pipeline | 28.05.2025 | 12.06.2025 | 20.06.2025 |  |  | 26.09.2025
2 | AP 36A - AP 37 | OIL Line | Mangla Crude Oil Pipeline | 28.05.2025 | 11.06.2025 | 10.07.2025 | 17.11.2025 | 31.12.2025 |  | 2026-03-30 | Hard copies submitted on 06.03.2026 | 1. Joint agreement to be signed 2. Special contingency insurance policy (5cr) to be taken and policy shall be valid till one month after completion of work. 3. Supervision charges (E-payment mode) : Rs. 50,000 + 18% GST (Non-Refundable) 4. Processing fee (E-payment mode) : Rs. 25,000 + 18% GST (Non-Refundable) 5. Concrete slab work on pipeline at crossing to be done by Apraava.
3 | AP 99B - AP 99C | OIL Line | GSPL | 28.05.2025 | 11.06.2025 | 14.07.2025 | 19.06.2025 | 31.12.2025 |  | 2026-03-30 | Soft copies submitted through mail and hard copies will be submitted as per confirmation of address. | 1. Joint agreement to be signed 2. Special contingency insurance policy (2.5cr) to be taken till the completion of work 3. Security deposit (DD) : Rs. 2 lakh - Refundable 4. Processing fee & Supervision charges (DD) : Rs.1.18 lakh (Non-Refundable) 5. AC mitigation Earthing work to be done by Apraava.
4 | AP 102/1 - AP 102/2 | OIL Line | HPCL Rajasthan Refinery Ltd. | 28.05.2025 | 09.06.2025 | 20.06.2025 | 22.07.2025 | 31.12.2025 |  | 2026-03-30 | Hard copies submitted on 06.03.2026 | 1. Joint agreement to be signed 2. Special contingency insurance policy (5cr) to be taken and policy shall be valid till one month after completion of work. 3. Supervision charges (E-payment mode) : Rs. 50,000 + 18% GST (Non-Refundable) 4. Processing fee (E-payment mode) : Rs. 25,000 + 18% GST (Non-Refundable) 5. AC mitigation Earthing work to be done by Apraava.
5 | AP 134 - AP 134A | OIL Line | BPPL | 28.05.2025 | 16.06.2025 | 24.07.2025 | 07.11.2025 | 31.12.2025 |  | 2026-03-30 | Hard copies submitted on 06.03.2026 | 1. Joint agreement to be signed 2. Processing fee (E-payment mode) : Rs. 25,000 + 18% GST (Non-Refundable) 3. Sepervision charges : Rs. 1.21 lakh - Non-Refundable 4. AC mitigation charges : Rs.9.36 lakh - Non-Refundable We need to conduct AC-DC interference survey to verify the effectiveness of the mitigation measures implemented, within 30 days of the completion of the crossing work and the charging of the HT Line.
6 | AP 149 - AP 149A | OIL Line | HMEL | 28.05.2025 | 16.06.2025 | 01.07.2025 | 14.07.2025 | 31.12.2025 |  | 2026-03-30 | Hard copies submitted on 06.03.2026 (Stringing work completed) | 1. Joint agreement to be signed 2. Security deposit : Rs. 5 lakh - Refundable 3. Sepervision charges : Rs. 1.475 lakh - Non-Refundable 4. AC mitigation charges : Rs.3.304 lakh - Non-Refundable
Forest Proposal (01 Nos)
1 | FP/RJ/PWR_TRANS/554020/2025 |  | MoECC |  | 2025-10-09 |  |  | 04.03.2026 | 21.01.2026 (Stage-1) | 2026-04-30 | Demand letter received on 16.02.2026 Payment done on 04.03.2026 Processing for Stage-II approval
Defence Proposal (01 Nos)
1 | For Whole Line |  | Ministry of Defence |  | 14.08.2025 |  |  |  | 2025-12-22
Aviation Proposal (01 Nos)
1 | For Whole Line |  | NOCAS |  | Applied for 497 loc. |  |  |  | 497/497
PTCC Proposal (01 Nos)
1 | For Whole Line |  |  |  | 07.02.2026 |  |  |  |  | 30.04.2026 | File submitted and NOC from Defence, Railway & Local BSNL office is awaited
765kV LILO Line
Defence Proposal (01 Nos)
1 | For Whole Line |  | Ministry of Defence | [7 empty] | Will be submitted by 1st Apr 26 | Due to ambiguity in submitting single or separate application for LI and LO circuits, process is delayed. Now got the clarity from PGCIL lines and separte application will be submitted.
Aviation Proposal (01 Nos)
1 | For Whole Line |  | NOCAS |  | 24.03.26 | [5 empty] | Will be submitted by 28th Mar 26
PTCC Proposal (01 Nos)
1 | For Whole Line | [9 empty] | Will be submitted by 7th Apr 26
Section 164
1 | For Whole Line |  |  |  | 21.08.2025 |  |  |  | 30.01.2026

## Crossing Proposal (hidden)
Sl No. | Crossing Span | Type | Description |  |  | Proposal Status | Remarks
A | Power Line Crossings
1 | AP2/1 - AP3 | 400KV D/C Fatehgarh III Fatehgarh IV T/L | Apraava Energy PVT. LTD. | 10.07.2025 | Subject to Approval of CS | Survey Report Submitted to Apraava Engg,
2 | AP4 - AP5 | 220 KV S/C PSS To FS IV Ampin CKT-1. | RRVPNL | 10.07.2025 | Subject to Approval of CS | Survey Report Submitted to Apraava Engg,
3 | AP5D - AP5E | 132 KV S/C Sheo to Undoo Line. | RRVPNL | 10.07.2025 | Subject to Approval of CS | Survey Report Submitted to Apraava Engg,
4 | AP25 - 26 | 400kV D/C Rajwest to Jodhpur TL & Rajwest to Pancpadra | RRVPNL | 07.07.2025 | Crossing Proposal Hardcopy submitted to Apraava | Proposal Submitted to Apraava
5 | A 27- A 27A | 220kV S/C BALOTARA TO GIRAL T/ Lin | RRVPNL |  | Submitted on 24.05.25 | AE will forward proposal for NOC to Chief Zonal by 10.10.2025
6 | AP50-AP51 | 220kV S/C BALOTARA TO BARMER T/ Line | RRVPNL |  | Submitted on 24.05.25
7 | AP58-AP59 | 132kV S/C BALOTARA TO BARMER T/ Line | RRVPNL |  | Submitted on 24.05.25
8 | AP111-AP112 | 132kV S/C KHOOKHA TO JIWANA T/ Line | RRVPNL |  | Submitted on 24.05.25 | NOC/Approval Given on 28.08.2025
9 | AP144-AP145 | 132kV S/C BHINMAL TO DASPUR T/ Line | RRVPNL |  | Submitted on 24.05.25
10 | AP152-AP153 | 220kV D/C SAYLA TO BHINMAL,PGCIL (RRVPNL) T/ Line | RRVPNL |  | Submitted on 24.05.25
11 | AP154-AP155 | 400kV D/C BARMER-II TO BHINMAL T/ Line | RRVPNL | 07.07.2025 | Crossing Proposal Hardcopy under submission | Proposal submited by KEC.
B | River Crossing
1 | AP 94 TO AP 95 | LUNI River | River Crossing
2 | 133/0 TO 133/4 | SUKRI River | River Crossing
3 | 137/0 TO138/0 | BANDI RIVER | River Crossing
C | Railway Crossings
1 | AP 46 TO AP 47 | Rly | Barmer-Jodhpur Single Track |  |  | Partial payment done on 25th Sep. Further proceedings of approval are under process.
2 | AP 150 AP 151 | Rly | Jalore-Bhinmal Single Track
D. | NH/Expressway Crossing (02 Nos)
1 | AP 43 - AP 44 | Barmer-Jodhpur National Highway-25 | NHAI |  | 15.12.2025 | Reply to the queries raised by PIU Jaisalmer will be submitted by 26th Nov
2 | AP 121 - AP 122 | Jamnagar-Amritsar Bharat Mala Expressway NH -754 | NHAI |  | 15.12.2025 | NOC expected by 30th Nov 25
E. | Road Crossing
1 | AP 53-AP-54 | Baytu (Balotra Road) -Chava (Barmer Road) | PWD |  | NOC pending
2 | AP 71 - 71/1 | Barmer-Sindhari | PWD
3 | AP 92- AP 93 | Sindhari-Gudamalani | PWD | NOC/Approved on21.08.2025
4 | 130/1 - AP 131 | Bagoda-Sayla | PWD
5 | AP 147/9 - AP 148 | Siyawat/Daspa- Bhinmal | PWD
6 | AP 04 - AP 05 | Re-Route |  |  | Detail survey submitted by KEC.
F. | Oil Pipe Crossing
1 | 29/0-29/1 |  | VEDANTA CAIRN OIL & GAS PIPE LINE RAJASTHAN |  |  | NOC/APPROVAL 26.09.2025
2 | 36A/0-37/0 |  | MANGALA CRUDE OIL PIPE LINE (HPCL-RAJASTHAN REFINERY LIMITED) RAJASTHAN |  |  | Demand letter expected by 15.10.2025
3 | 99B/0-99C/0 |  | HRRL CONNECTIVITY GAS PIPE LINE(GSPL INDIA GASNE LIMITED BALOTRA ) RAJASTHAN |  |  | DD submitted and other documents to be submitted as per GSPL requirement
4 | 102/1-102/2 |  | ARAB MIX CRUDE OIL PIPE LINE(HPCL RAJASTHAN REFINERY LIMITED PACHADRA,BALOTRA ) RAJASTHAN |  |  | Documents to be submitted as per HRRL requirement
5 | 134/0-134A/0 |  | BARMER- PALANPUR PRTROLEUM PIPE LINE (HINDUSTAN PERTOLEUM CORP.LTD) RAJASTHAN |  |  | Demand letter expected by 15.10.2025
6 | 149/0-149A/0 |  | MUNDRA- BATHINDA CRUDE OIL PIPE LINE (HPCL-Mittal Pipelines Limited) RAJASTHAN |  |  | Draft agreement copy submitted for HMEL review
185
5

## Sheet1 (hidden)
FOUNDATION STATUS | [7 empty] | 18
SL. No. | Location Number | Span | Tower Type | RC | Foundation type
[6 empty] | Starting date | Completion Date | Agency | Remark | Remarks
1 | 83/1 | 83/1 | DA+3 |  | Sandy | 2025-01-08 | 2025-01-17 | Mahadeep Company | 2025-01-17 | Complete
2 | 81/4 | 81/4 | DA+0 |  | Sandy | 2025-01-18 | ROW | Mahadeep Company | ROW LOC HOLD | Row Since 20-01-2025, Gang Domobilized
3 | 75/7 | 75/7 | DA+0 |  | Sandy | 2025-01-18 | 2025-01-27 | AR PATEL |  | RCC Complete
4 | 75/6 |  | DA+0 |  | Sandy | 2025-01-28 | 2025-02-02 | AR PATEL |  | RCC Complete, Backfilling Done
5 | 75/5 |  | DA+0 |  | Sandy | 2025-01-28 | 2025-02-05 | AR PATEL |  | RCC Complete.
6 | 75/4 |  | DA+0 |  | Sandy | 2025-01-29 | 2025-02-05 | Om Constraction |  | RCC Complete, Backfilling Done
7 | 75/3 |  | DA+3 |  | Sandy | 2025-02-03 | 2025-02-10 | Om Constraction |  | RCC Complete.
8 | 75/1 |  | DA+0 |  | Sandy | 2025-02-09 | 2025-02-17 | Om Constraction |  | RCC Complete.
9 | 75/2 |  | DA+0 |  | Sandy | 2025-02-12 | 2025-02-18 | Om Constraction |  | RCC Complete.
10 | 77/1 |  | DA+0 |  | Sandy | 2025-02-03 | 2025-02-11 | Anjaana Construction |  | RCC Complete.
11 | 77/2 |  | DA+3 |  | Sandy | 2025-02-03 | 2025-02-09 | AR PATEL |  | RCC Complete, Backfilling Done
12 | 77/3 |  | DA+0 |  | Sandy | 2025-02-08 | 2025-02-14 | AR PATEL |  | RCC Complete.
13 | 77/4 |  | DA+3 |  | Sandy | 2015-02-11 | 2025-02-17 | Anjaana Construction |  | RCC Complete.
14 | 77/5 |  | DA+6 |  | Sandy | 2025-02-13 |  | AR PATEL |  | Pit B,C RCC Done & Pit A,D Frustrum RCC done.
15 | 86/2 |  | DA+0 |  | Sandy | 2025-02-10 |  | Kalpana Enterprises |  | Pit A , Pit B RCC Done , Pit C -Stub setting.
16 | 66/1 |  | DA+9 |  | Sandy | 2025-02-17 |  | Siyag Construction |  | Excavation WIP, ROW,Material Shifting WIP
17 | 73/3 |  | DA+9 |  | Sandy | 2025-02-17 |  | Om Constraction |  | Excavation WIP, ROW, Material Shifting WIP
18 | 79/1 |  | DA+9 |  | Sandy | 2025-02-17 |  | Anjana Construction |  | Excavation WIP, ROW, Material Shifting WIP
19 | 95A/1 |  | DA+0 |  | Sandy |  |  | Gurukripa Enterprises |  | Pit Marking Done
20 | 80/1
21 | 85/1
22 | 73/2
23 | 66/2
24 | 66/3
25 | 86/1
26 | 76/1

## VC 51-96 (hidden)
TB-507 400 KV (Twin) D/C Fatehgarh IV - Bhinmal Transmission Line
DPR and VISUAL CHART
DPR- |  |  | District |  | No.Of Towers | Length | Foundation |  |  | Earthing | Tower Erection |  |  | Stringing
[7 empty] | Com | WIP | Bal | Com | Com | WIP | Bal | Com | WIP | Bal
[5 empty] | 163 | 50.886 | 16 | 5 | 142 | 10 |  |  | 163 |  |  | 50.886
|  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9
|  |  | 465.03 |  | 375.98 |  | 414.86 |  | 381.02 |  | 353.63 |  | 351.4 |  | 433.26 |  | 396.56 |  | 408.11 | 3579.85
|  | AP51 |  | 51/1 |  | 51/2 |  | 51/3 |  | AP52 |  | 52/1 |  | AP53 |  | AP54 |  | 54/1
|  | DD+18 |  | DA+03 |  | DA+00 |  | DA+03 |  | DB+0 |  | DA+06 |  | DD+0 |  | DC+00 |  | DA+03
[10 empty] | RC |  | RC
| 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19
|  | 425.22 |  | 420.54 |  | 340.56 |  | 336.52 |  | 375.99 |  | 303.41 |  | 448.76 |  | 393.09 |  | 407.8 |  | 206.06 | 3657.95
| 54/2 |  | 54/3 |  | AP55 |  | AP56 |  | 56/1 |  | 56/2 |  | 56/3 |  | 56/4 |  | 56/5 |  | AP57
| DA+06 |  | DA+03 |  | DD+18 |  | DB+09 |  | DB+9 |  | DA+0 |  | DB+9 |  | DA+6 |  | DA+6 |  | DB+09
| Benching &RC |  | RC |  | RC |  | Benching &RC |  |  |  | Benching Required | [5 empty] | Benching &RC |  | Benching &RC
| 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29
|  | 417.38 |  | 304.56 |  | 408.66 |  | 434.89 |  | 408.17 |  | 398.59 |  | 446.37 |  | 297.58 |  | 240.47 |  | 312.69 | 3669.36
| AP58 |  | AP59 |  | 59/1 |  | AP60 |  | 60/1 |  | 60/2 |  | 60/3 |  | AP61 |  | 61/1 |  | AP62
| DB+09 |  | DC+09 |  | DA+0 |  | DD+00 |  | DA+9 |  | DA+0 |  | DA+9 |  | DC+00 |  | DA+9 |  | DB+00
[5 empty] | Benching | [7 empty] | RC
| 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39
|  | 347.88 |  | 379.25 |  | 398.7 |  | 439.06 |  | 381.53 |  | 379.71 |  | 426.3 |  | 387.14 |  |  |  | 423.77 | #REF!
| 62/1 |  | 62/2 |  | 62/3 |  | 62/4 |  | 62/5 |  | AP63 |  | 63/1 |  | AP64 |  | 64/1 |  | 64/2
| DA+0 |  | DA+0 |  | DA+09 |  | DA+06 |  | DA+06 |  | DC+00 |  | DA+0 |  | DC+09 |  | DA+9 |  | DA+9
| RC |  |  |  | RC | [9 empty] | Benching &RC |  |  |  | RC
| 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49
|  | 407.9 |  | 426.63 |  | 392.27 |  | 431.96 |  | 426.02 |  | 405.36 |  | 411.93 |  | 423.77 |  | 407.9 |  | 426.63
| F |  | WIP | [13 empty] | F |  | F
| 64/3 |  | 64/4 |  | 64/5 |  | 64/6 |  | 64/7 |  | 65/0 |  | 65/1 |  | 66/0 |  | 66/1 |  | 66/2
| DA+9 |  | DA+9 |  | DA+9 |  | DA+3 |  | DA+3 |  | DD+0 |  | DB+09 |  | DD+0 |  | DA+9 |  | DA+0 |  | #REF!
RC
| 50 |  | 51 |  | 52 |  | 53 |  | 54 |  | 55 |  | 56 |  | 57 |  | 58 |  | 59
|  | 392.27 |  | 431.96 |  | 426.02 |  | 405.36 |  | 411.93 |  | 350.33 |  | 378.3 |  | 416.82 |  | 371.85
WIP
| 66/3 |  | 66/4 |  | 67/0 |  | 67/1 |  | 67/2 |  | AP68 |  | AP69 |  | 69/1 |  | 69/2 |  | 69/3
| DA+3 |  | DA+9 |  | DC+6 |  | DA+6 |  | DB+0 |  | DB+09 |  | DD+3 |  | DA+6 |  | DA+0 |  | DA+00
[5 empty] | RC | [11 empty] | Benching |  | RC |  | #REF!
| 60 |  | 61 |  | 62 |  | 63 |  | 64 |  | 65 |  | 66 |  | 67 |  | 68 |  | 69
|  | 392.27 |  | 431.96 |  | 426.02 |  | 405.36 |  | 411.93 |  | 350.33 |  | 378.3 |  | 416.82 |  | 371.85
F
| AP71 |  | 71/1 |  | 71/2 |  | 71/3 |  | AP72 |  | 72/1 |  | 72/2 |  | AP73 |  | 73/1 |  | 73/2
| DB+00 |  | DA+09 |  | DA+00 |  | DA+00 |  | DD+00 |  | DA+03 |  | DA+03 |  | DB+00 |  | DA+00 |  | DA+09
[7 empty] | RC |  | Benching &RC |  | RC | [5 empty] | Benching & RC |  | CLEAR |  | 3994.99
| 70 |  | 71 |  | 72 |  | 73 |  | 74 |  | 75 |  | 76 |  | 77 |  | 78 |  | 79
|  | 385.17 |  | 345.19 |  | 332.38 |  | 393.62 |  | 387.95 |  | 340.35 |  | 393.12 |  | 328.54 |  | 398.52
| F |  |  |  | F |  |  |  | F |  | F |  | F |  | F |  | F |  | F
| Er | [7 empty] | Er |  | Er |  | Er | [5 empty] | Er
| 73/3 |  | AP74 |  | 74/1 |  | AP75 |  | 75/1 |  | 75/2 |  | 75/3 |  | 75/4 |  | 75/5 |  | 75/6
| DA+09 |  | DB+09 |  | DA+0 |  | DC+0 |  | DA+00 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0
| CLEAR | [5 empty] | Benching |  | Benching |  | Benching &RC
| 80 |  | 81 |  | 82 |  | 83 |  | 84 |  | 85 |  | 86 |  | 87 |  | 88 |  | 89
[6 empty] | 388.46 |  | 380.96 |  | 374.03 |  | 351.96 |  | 395.64 |  | 414.76 |  | 401.93
| F |  |  |  | F |  |  |  | F |  | F |  | F |  | F |  | F
| Er | [7 empty] | Er | [5 empty] | Er |  | Er
| 75/7 |  | AP76 |  | 76/1 |  | 77/0 |  | 77/1 |  | 77/2 |  | 77/3 |  | 77/4 |  | 77/5 |  | AP78
| DA+0 |  | DC+00 |  | DA+06 |  | DB+00 |  | DA+00 |  | DA+03 |  | DA+00 |  | DA+03 |  | DA+06 |  | DC+00
[5 empty] | Clear | [5 empty] | Benching
| 90 |  | 91 |  | 92 |  | 93 |  | 94 |  | 95 |  | 96 |  | 97 |  | 98 |  | 99
|  | 385.54 |  |  |  | 351.18 |  | 441.06 |  | 387.5 |  | 372.63 |  | 415.3 |  | 424.58 |  | 391.7 |  | 410.47
[5 empty] | F | [5 empty] | F
Er
| 78/1 |  | AP79 |  | 79/1 |  | 79/2 |  | AP80 |  | 80/1 |  | AP81 |  | 81/1 |  | 81/2 |  | 81/3
| DA+03 |  | DD+00 |  | DA+09 |  | DA+00 |  | DB+03 |  | DA+9 |  | DB+09 |  | DA+00 |  | DA+03 |  | DA+00
[5 empty] | Clear |  | RC,Benching |  |  |  | Benching |  |  |  | Benching &RC
| 100 |  | 101 |  | 102 |  | 103 |  | 104 |  | 105 |  | 106 |  | 107 |  | 108 |  | 109
#REF!
415.03 |  | 416.87 |  |  |  | 426.47 |  | 396.98 |  | 429.38 |  | 403.83 |  | 384.63 |  | 380.68 |  | 354.53
| ROW | [11 empty] | F
U/P
| 81/4 |  | 81/5 |  | AP82 |  | 82/1 |  | 82/2 |  | AP83 |  | 83/1 |  | AP84 |  | AP85 |  | 85/1
| DA+00 |  | DA+06 |  | DB+03 |  | DA+00 |  | DA+03 |  | DC+00 |  | DA+03 |  | DC+06 |  | DC+00 |  | DA+00
[7 empty] | RC | [11 empty] | CLEAR
| 110 |  | 111 |  | 112 |  | 113 |  | 114 |  | 115 |  | 116 |  | 117 |  | 118 |  | 119
3121.94
|  | 395.01 | #REF! |  |  | 380.77 |  | 411.81 |  | 432.08 |  | 256.87 |  | 412.4 |  | 382.17 |  | 452.74
F
| AP86 |  | 86/1 |  | 86/2 |  | AP87 |  | 87/1 |  | 87/2 |  | AP88 |  | AP89 |  | 89/1 |  | AP90
| DD+00 |  | DA+06 |  | DA+00 |  | DC+00 |  | DA+03 |  | DA+09 |  | DC+00 |  | DC+00 |  | DA+09 |  | DC+00
| CLEAR |  | CLEAR |  | CLEAR
| 120 |  | 121 |  | 122 |  | 123 |  | 124 |  | 125 |  | 126 |  | 127 |  | 128 |  | 129
#REF!
|  | 430.39 |  |  |  | 378.62 |  | 350.22 |  | 357.91 |  | 237.48 |  | 440.03 |  | 504 |  | 430.57
| 90/1 |  | AP91 |  | 91/1 |  | 91/2 |  | 91/3 |  | AP92 |  | AP93 |  | AP94 |  | AP95 |  | 95/1
| DA+09 |  | DD+00 |  | DA+00 |  | DA+00 |  | DA+00 |  | DC+00 |  | DC+00 |  | DB+06 |  | DB+06 |  | DB+00
| 130 |  | 131 |  | 132 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137 |  | 138 |  | 139 |  | 130
|  | 354.92 |  |  |  | 419.38 |  | 406.18 |  | 427.47 |  |  |  | 416.77 |  | 378.13 |  | 358.57 |  | 360.52
[5 empty] | F |  |  |  | F
| 95/2 |  | 95A/0 |  | 95A/1 |  | AP96 |  | 96/1 |  | 96/2 |  | AP97 |  | 97/1 |  | AP98 |  | AP98/1 |  | 98A/0
| DA+09 |  | DB+0 |  | DA+00 |  | DC+00 |  | DA+00 |  | DA+00 |  | DC+00 |  | DA+03 |  | DC+00 |  | DA+00 |  | DC+00
RC
| 131 |  | 132 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137 |  | 138 |  | 139 |  | 140 |  | 141
| 98A/1 |  | 98B/0 |  | 98B/1 |  | 98B/2 |  | 99/0 |  | 99/1 |  | 99/2 |  | 99/3 |  | 99/4 |  | 99/5 |  | 99/6
| DA+00 |  | DD+00 |  | DA+00 |  | DCT+00 |  | DC+0 |  | DA+06 |  | DA+00 |  | DA+00 |  | DA+06 |  | DA+03 |  | DA+03
[5 empty] | RC | [9 empty] | RC
| 142 |  | 143 |  | 144 |  | 145 |  | 146 |  | 147 |  | 148 |  | 149 |  | 150 |  | 151 |  | 152
| AP99A |  | 99A/1 |  | 99A/2 |  | AP100 |  | 100/1 |  | AP101 |  | AP102 |  | 102/1 |  | 102/2 |  | AP103 |  | 103/1
| DB+00 |  | DA+00 |  | DA+00 |  | DC+00 |  | DA+6 |  | DD+06 |  | DD+3 |  | DA+00 |  | DA+00 |  | DC+0 |  | DA+6
| 153 |  | 154 |  | 155 |  | 156 |  | 157 |  | 158 |  | 159 |  | 160 |  | 161 |  | 162 |  | 163
| AP104 |  | AP104A |  | AP104B |  | 104B/1 |  | 104B/2 |  | AP105 |  | 105/1 |  | AP106 |  | AP107
| DB+9 |  | DC+9 |  | DB+9 |  | DA+0 |  | DA+0 |  | DD+0 |  | DA+3 |  | DC+6 |  | DD+3
|  |  | RC |  | RC
| 164 |  | 165 |  | 166 |  | 167 |  | 168 |  | 169 |  | 170 |  | 171 |  | 172 |  | 173 |  | 174
| AP104 |  | AP104A |  | AP104B |  | 104B/1 |  | 104B/2 |  | AP105 |  | 105/1 |  | AP106 |  | AP107 |  | 107/1 |  | 108/0
| DB+9 |  | DC+9 |  | DB+9 |  | DA+0 |  | DA+0 |  | DD+0 |  | DA+3 |  | DC+6 |  | DD+3 |  | DA+9 |  | DC+0
|  |  | RC |  | RC | [15 empty] | 1MRC
| 175 |  | 176 |  | 177 |  | 178 |  | 179 |  | 180 |  | 181 |  | 182 |  | 183 |  | 184 |  | 185
| AP109 |  | AP109A |  | AP110 |  | AP111 |  | AP112 |  | AP113 |  | AP113A |  | AP114 |  | 114/1 |  | AP115 |  | 115/1
| DC+3 |  | DB+6 |  | DC+0 |  | DB+9 |  | DC+9 |  | DD+0 |  | DC+0 |  | DC+0 |  | DA+9 |  | DC+0 |  | DB+9
[7 empty] | 3 MRC |  | 3 MRC | [9 empty] | 1MRC
| 186 |  | 187 |  | 188 |  | 189 |  | 190 |  | 191 |  | 192 |  | 193 |  | 194 |  | 195 |  | 196
| AP116 |  | 116/1 |  | AP117 |  | 117/1 |  | 117/2 |  | AP118 |  | AP119 |  | 119/1 |  | 119/2 |  | AP120 |  | 120/1
| DD+0 |  | DA+0 |  | DD+0 |  | DA+3 |  | DB+9 |  | DC+3 |  | DD+3 |  | DA+3 |  | DA+3 |  | DC+0 |  | DA+6
|  |  | Benching |  | RC
197
AP121
DD+0
TSE
Manual
Total
Paying out/ Rough sag
[11 empty] | Tack welding completed | [5 empty] | Erection ROW
Erection Completed ------>
|  | Foundation completed ----> | [8 empty] | <------Insulator hosting
|  | Earthing completed -----> |  |  |  |  | U/P | [9 empty] | Erection Cleared
Road
[7 empty] | 325 | Span
[12 empty] | HT-D/C Power Line Crossing |  |  |  |  | Cart Track
| Transformer |  |  | ROW | ROW |  |  | Water Tank
| Temple |  |  | A+0 | Tower Type |  |  | LT Power Line Crossing |  |  |  | HT-S/C Power Line Crossing |  |  |  |  | Broad Gauge Railway
[8 empty] | 11 KV Line Crossing | [8 empty] | Line Crossing
| Hut |  |  | 1/0 | Location No. |  |  | 33 KV Line Crossing
| Bore & Handpump |  |  |  | Minor River Crossing | [6 empty] | Forest Stretch |  |  |  |  | SH Crossing
| Oil Pipe Line |  |  | RC | Raised Chimney |  |  | Major River Crossing |  |  |  | NH Crossing |  |  |  |  | Wild Life Sanctuary
3
3
3
3
3

## VC (hidden)
TB-507 400 KV (Twin) D/C Fatehgarh IV - Bhinmal Transmission Line
DPR and VISUAL CHART
| DPR- |  |  | District |  | No.Of Towers | Length | Foundation |  |  | Earthing | Tower Erection |  |  | Stringing
[8 empty] | Com | WIP | Bal | Com | Com | WIP | Bal | Com | WIP | Bal
[6 empty] | 495 | 187.175 | 9 | 5 | 481 | 3 |  |  | 495 |  |  | 187.175
r
| 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10
|  | 97.4 |  | 139.42 |  | 484.04 |  | 398 |  | 443.16 |  | 399.53 |  | 402.87 |  | 437.15 |  | 381.84 |  | 416.91 | 3600.32 | FDN | TE | Earthing | Stringing |  | Tack Welding | 3600.32
1 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| GE |  | AP1 |  | AP2 |  | AP3 |  | 03/1 |  | 3/2 |  | 3/3 |  | 3/4 |  | 3/5 |  | 3/6 |  |  | 0 | 0 | 0 |  | ROW
|  |  | DD+03 |  | DD+9 |  | DC+9 |  | DA+9 |  | DA+0 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+00
| 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20
|  | 428.12 |  | 249.58 |  | 454.54 |  | 377.83 |  | 447.64 |  | 396.44 |  | 445.93 |  | 156.98 |  | 409.67 |  | 382.38 | 3749.11 | [6 empty] | 3749.11
2 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 3/7 |  | 3/8 |  | AP4 |  | 4/1 |  | AP5 |  | 5/1 |  | 5/2 |  | AP6 |  | AP7 |  | 7/1 |  |  | 0 | 0 | 0 |  | ROW
| DA+03 |  | DD+03 RC |  | DD+03 |  | DA+09 |  | DC+3 |  | DA+06 |  | DA+03 |  | DD+09 |  | DD+09 |  | DA+00
| 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30
|  | 353.89 |  | 385.21 |  | 367.67 |  | 378.32 |  | 392.49 |  | 399.24 |  | 390.93 |  | 412.07 |  | 421.95 |  | 391.87 | 3893.64 | [6 empty] | 3893.64
3 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 7/2 |  | 7/3 |  | 7/4 |  | 7/5 |  | 7/6 |  | '7/7 |  | AP8 |  | 08/01 |  | 08/2 |  | 08/3 |  |  | 0 | 0 | 0 |  | ROW
| DA+00 |  | DA+00 |  | DA+00 |  | DA+00 |  | DA+00 |  | DA+00 |  | DB+00 |  | DA+06 |  | DA+00 |  | DA+00
| 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40
|  | 406.65 |  | 383.31 |  | 402.96 |  | 433.9 |  | 328.55 |  | 331.44 |  | 358.83 |  | 358.55 |  | 429.37 |  | 354.9 | 3788.46 | [6 empty] | 3788.46
4 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 08/4 |  | 08/5 |  | 08/6 |  | 08/7 |  | AP9 |  | 09/01 |  | 09/02 |  | 09/03 |  | 09/04 |  | 09/05 |  |  | 0 | 0 | 0 |  | ROW
| DA+03 |  | DA+00 |  | DA+06 |  | DA+06 |  | DB+00 |  | DA+00 |  | DA+00 |  | DA+00 |  | DA+00 |  | DA+00
| 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49 |  | 50
|  | 340.94 |  | 405.66 |  | 409.41 |  | 378.36 |  | 322.47 |  | 386.39 |  | 386.19 |  | 406.2 |  | 351.15 |  | 380.59 | 3767.36 | [6 empty] | 3767.36
5 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 09/06 |  | AP10 |  | 10/01 |  | 10/02 |  | 10/03 |  | 10/04 |  | 10/05 |  | 10/06 |  | 10/07 |  | 10/08 |  |  | 0 | 0 | 0 |  | ROW
| DA+00 |  | DC+9 |  | DA+09 |  | DA+00 |  | DA+00 |  | DA+00 |  | DA+00 |  | DA+00 |  | DA+00 |  | DA+00
| 51 |  | 52 |  | 53 |  | 54 |  | 55 |  | 56 |  | 57 |  | 58 |  | 59 |  | 60
|  | 380.02 |  | 393.7 |  | 390.68 |  | 349.16 |  | 416.01 |  | 400.75 |  | 406.84 |  | 404.76 |  | 311.74 |  | 389.98 | 3843.64 | [6 empty] | 3843.64
6 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 10/09 |  | AP11 |  | 11/01 |  | AP12 |  | 12/01 |  | 12/02 |  | 12/03 |  | 12/04 |  | 12/05 |  | 12/06 |  |  | 0 | 0 | 0 |  | ROW
| DA+00 |  | DC+00 |  | DA+03 |  | DD+00 |  | DA+03 |  | DA+03 |  | DA+00 |  | DA+03 |  | DA+00 |  | DA+00
| 61 |  | 62 |  | 63 |  | 64 |  | 65 |  | 66 |  | 67 |  | 68 |  | 69 |  | 70
|  | 384.15 |  | 350.96 |  | 437.11 |  | 406.67 |  | 421.42 |  | 421.75 |  | 380.8 |  | 438.78 |  | 426.5 |  | 375.59 | 4066.13 | [6 empty] | 4043.73
7 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 12/07 |  | 12/08 |  | AP13 |  | 13/01 |  | 13/02 |  | 13/03 |  | 13/04 |  | AP14 |  | AP15 |  | 15/01 |  |  | 0 | 0 | 0 |  | ROW
| DA+00 |  | DA+00 |  | DC+00 |  | DA+09 |  | DA+00 |  | DA+06 |  | DA+03 |  | DB+09 |  | DC+06 |  | DA+03
Paddy
| 71 |  | 72 |  | 73 |  | 74 |  | 75 |  | 76 |  | 77 |  | 78 |  | 79 |  | 80
|  | 413.56 |  | 407.62 |  | 397.38 |  | 408.9 |  | 395.25 |  | 384.81 |  | 388.05 |  | 362.31 |  | 359.92 |  | 386.31 | #REF! | [6 empty] | 3904.11
8 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 15/02 |  | 15/03 |  | AP16 |  | 16/01 |  | 16/02 |  | 16/03 |  | 16/04 |  | 16/05 |  | 16/06 |  | 16/07 |  |  | 0 | 0 | 0 |  | ROW
| DA+03 |  | DA+06 |  | DC+00 |  | DA+03 |  | DA+09 |  | DA+00 |  | DA+00 |  | DA+00 |  | DA+00 |  | DA+00
Paddy
| 81 |  | 82 |  | 83 |  | 84 |  | 85 |  | 86 |  | 87 |  | 88 |  | 89 |  | 90
|  | 319.93 |  | 342.16 |  | 384.83 |  | 365.71 |  | 394.61 |  | 315.81 |  | 419.79 |  | 418.97 |  | 420.65 |  | 422.09 | 3804.55 | [6 empty] | 3804.55
9 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 16/08 |  | AP17 |  | 17/01 |  | 17/02 |  | 17/03 |  | AP18 |  | AP19 |  | AP20 |  | 20/01 |  | 20/02 |  |  | 0 | 0 | 0 |  | ROW
| DA+00 |  | DB+0 |  | DA+00 |  | DA+00 |  | DA+03 |  | DB+00 |  | DB+06 |  | DB+09 |  | DA+03 |  | DA+00
[11 empty] | Paddy | [5 empty] | Paddy
| 91 |  | 92 |  | 93 |  | 94 |  | 95 |  | 96 |  | 97 |  | 98 |  | 99 |  | 100
|  | 420.49 |  | 459.09 |  | 386.28 |  | 273.16 |  | 313.62 |  | 361.38 |  | 308.79 |  | 332.52 |  | 269.07 |  | 357.59 | 3481.99 | [6 empty] | 3481.99
10 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 20/03 |  | 20/04 |  | 20/05 |  | AP21 |  | 21/01 |  | 21/02 |  | 21/03 |  | AP22 |  | 22/01 |  | 22/02 |  |  | 0 | 0 | 0 |  | ROW
| DA+06 |  | DB+00 |  | DA+09 |  | DC+09 |  | DA+03 |  | DA+06 |  | DA+00 |  | DC+09 |  | DA+03 |  | DA+06
[13 empty] | Paddy | [5 empty] | Paddy
| 101 |  | 102 |  | 103 |  | 104 |  | 105 |  | 106 |  | 107 |  | 108 |  | 109 |  | 110
|  | 201.38 |  | 218.35 |  | 439.11 |  | 365.6 |  | 424.47 |  | 412.73 |  | 401.93 |  | 379.06 |  | 404.19 |  | 441.06 | 3687.88 | [6 empty] | 3687.88
11 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| AP23 |  | AP24 |  | AP25 |  | 25/01 |  | AP26 |  | 26/01 |  | 26/02 |  | 26/03 |  | 26/04 |  | 26/05 |  |  | 0 | 0 | 0 |  | ROW
| DD+18 |  | DD+25 |  | DD+06 |  | DA+09 |  | DC+09 |  | DA+09 |  | DA+06 |  | DA+03 |  | DA+06 |  | DA+03
Paddy
| 111 |  | 112 |  | 113 |  | 114 |  | 115 |  | 116 |  | 117 |  | 118 |  | 119 |  | 120
|  | 404.77 |  | 386.79 |  | 382.59 |  | 460.27 |  | 369.05 |  | 447.91 |  | 371.72 |  | 373.16 |  | 423.96 |  | 381.03 | 4001.25 | [6 empty] | 4001.25
12 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 26/06 |  | AP27 |  | 27/1 |  | 27/2 |  | AP28 |  | 28/1 |  | 28/2 |  | 28/3 |  | 28/4 |  | AP29 |  |  | 0 | 0 | 0 |  | ROW
| DA+06 |  | DC+3 |  | DA+09 |  | DA+09 |  | DB+0 |  | DA+00 |  | DA+09 |  | DA+00 |  | DB+9 |  | DC+3
Paddy
| 121 |  | 122 |  | 123 |  | 124 |  | 125 |  | 126 |  | 127 |  | 128 |  | 129 |  | 130
|  | 419.6 |  | 425.18 |  | 287.54 |  | 336.51 |  | 325.3 |  | 214.25 |  | 455.95 |  | 421.16 |  | 423.79 |  | 403.85 | 3725.44 | [6 empty] | 3713.13
13 |  |  | ROW | [5 empty] | ROW |  | ROW | [10 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 29/1 |  | 29/2 |  | AP30 |  | 30/1 |  | 30/2 |  | 30/3 |  | AP31 |  | AP32 |  | 32/1 |  | 32/2 |  |  | 3 | 0 | 0 |  | ROW
| DA+06 |  | DA+09 |  | DC+0 |  | DA+00 |  | DA+00 |  | DA+00 |  | DC+9 |  | DC+9 |  | DA+03 |  | DA+03
Paddy
| 131 |  | 132 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137 |  | 138 |  | 139 |  | 140
|  | 408.95 |  | 324.03 |  | 366.7 |  | 473.31 |  | 358.32 |  | 477.82 |  | 411.46 |  | 406.23 |  | 437.43 |  | 455.92 | #REF! | [6 empty] | 4120.17
14 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 32/3 |  | AP33 |  | AP34 |  | 34/1 |  | AP35 |  | 35/1 |  | AP36 |  | 36/1 |  | 36/2 |  | AP37 |  |  | 0 | 0 | 0 |  | ROW
| DA+09 |  | DB+0 |  | DC+6 |  | DA+09 |  | DC+9 |  | DA+09 |  | DC+9 |  | DA+09 |  | DA+09 |  | DD+3
| 141 |  | 142 |  | 143 |  | 144 |  | 145 |  | 146 |  | 147 |  | 148 |  | 149 |  | 150
|  | 368.5 |  | 419.77 |  | 418.92 |  | 386.49 |  | 376.53 |  | 404.74 |  | 366.73 |  | 274.59 |  | 341.67 |  | 425.86 | 3783.8 | [6 empty] | 3783.8
15 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 37/1 |  | AP38 |  | 38/1 |  | 38/2 |  | 38/3 |  | AP39 |  | 39/1 |  | 39/2 |  | 39/3 |  | 39/4 |  |  | 0 | 0 | 0 |  | ROW
| DA+06 |  | DB+0 |  | DA+06 |  | DA+09 |  | DA+03 |  | DB+3 |  | DA+06 |  | DA+00 |  | DA+00 |  | DA+00
| 151 |  | 152 |  | 153 |  | 154 |  | 155 |  | 156 |  | 157 |  | 158 |  | 159 |  | 160
|  | 394.31 |  | 370.45 |  | 436.75 |  | 397.61 |  | 413.4 |  | 423.65 |  | 415.97 |  | 415.35 |  | 394.88 |  | 429.62 | 4091.99 | [6 empty] | 4091.99
16 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 39/5 |  | AP40 |  | 40/1 |  | 40/2 |  | AP41 |  | 41/1 |  | 41/2 |  | 41/3 |  | AP42 |  | 42/1 |  |  | 0 | 0 | 0 |  | ROW
| DA+06 |  | DD+3 |  | DB+06 |  | DA+06 |  | DB+0 |  | DA+09 |  | DCT+0 |  | DA+09 |  | DC+3 |  | DA+09
| 161 |  | 162 |  | 163 |  | 164 |  | 165 |  | 166 |  | 167 |  | 168 |  | 169 |  | 170
|  | 381.91 |  | 405.26 |  | 338.16 |  | 288.3 |  | 297.15 |  | 195.9 |  | 249.66 |  | 374.48 |  | 443.95 |  | 404.39 | #REF! | [6 empty] | 3379.16
17 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 42/2 |  | 42/3 |  | 42/4 |  | 42/5 |  | 42/6 |  | 42/7 |  | AP43 |  | AP44 |  | 44/1 |  | AP45 |  |  | 0 | 0 | 0 |  | ROW
| DA+06 |  | DA+09 |  | DA+09 |  | DA+00 |  | DA+03 |  | DA+00 |  | DC+6 |  | DB+09 |  | DA+09 |  | DD+09
| 171 |  | 172 |  | 173 |  | 174 |  | 175 |  | 176 |  | 177 |  | 178 |  | 179 |  | 180
|  | 341.42 |  | 305.4 |  | 319.98 |  | 345.62 |  | 223.15 |  | 389.84 |  | 439.14 |  | 403.21 |  | 422.55 |  | 353.48 | 3543.79 | [6 empty] | 3543.79
18 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 45/1 |  | 45/2 |  | 45/3 |  | 45/4 |  | AP46 |  | AP47 |  | 47/1 |  | 47/2 |  | AP48 |  | AP49 |  |  | 0 | 0 | 0 |  | ROW
| DA+00 |  | DA+03 |  | DA+00 |  | DA+06 |  | DD+09 |  | DD+09 |  | DA+09 |  | DA+09 |  | DD+03 |  | DD+03
| 181 |  | 182 |  | 183 |  | 184 |  | 185 |  | 186 |  | 187 |  | 188 |  | 189 |  | 190
0
19 |  |  |  | 465.03 |  | 375.98 |  | 414.86 |  | 381.02 |  | 353.63 |  | 351.4 |  | 433.26 |  | 396.56 |  | 408.11 |  | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
[22 empty] | 0 | 0 | 0 |  | ROW
| AP51 |  | AP51 |  | 51/1 |  | 51/2 |  | 51/3 |  | AP52 |  | 52/1 |  | AP53 |  | AP54 |  | 54/1
| DD+18 |  | DD+18 |  | DA+03 |  | DA+00 |  | DA+03 |  | DB+0 |  | DA+06 |  | DD+0 |  | DC+00 |  | DA+03
| 191 |  | 192 |  | 193 |  | 194 |  | 195 |  | 196 |  | 197 |  | 198 |  | 199 |  | 200
0
20 |  | 425.22 |  | 420.54 |  | 340.56 |  | 336.52 |  | 375.99 |  | 303.41 |  | 448.76 |  | 393.09 |  | 407.8 |  | 206.06 |  | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
[22 empty] | 0 | 0 | 0 |  | ROW
| 54/2 |  | 54/3 |  | AP55 |  | AP56 |  | 56/1 |  | 56/2 |  | 56/3 |  | 56/4 |  | 56/5 |  | AP57
| DA+06 |  | DA+03 |  | DD+18 |  | DB+09 |  | DB+9 |  | DA+0 |  | DB+9 |  | DA+6 |  | DA+6 |  | DB+09
| Benching &RC | [5 empty] | Benching &RC |  |  |  | Benching &RC | [5 empty] | Benching &RC |  | Benching &RC
| 201 |  | 202 |  | 203 |  | 204 |  | 205 |  | 206 |  | 207 |  | 208 |  | 209 |  | 210
0
21 |  | 417.38 |  | 304.56 |  | 408.66 |  | 434.89 |  | 408.17 |  | 398.59 |  | 446.37 |  | 297.58 |  | 240.47 |  | 312.69 |  | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
[22 empty] | 0 | 0 | 0 |  | ROW
| AP58 |  | AP59 |  | 59/1 |  | AP60 |  | 60/1 |  | 60/2 |  | 60/3 |  | AP61 |  | 61/1 |  | AP62
| DB+09 |  | DC+09 |  | DA+0 |  | DD+00 |  | DA+9 |  | DA+0 |  | DA+9 |  | DC+00 |  | DA+9 |  | DB+00
[5 empty] | Benching &RC |  |  |  | CHECK SURVEY WIP
| 211 |  | 212 |  | 213 |  | 214 |  | 215 |  | 216 |  | 217 |  | 218 |  | 219 |  | 220
0
22 |  | 347.88 |  | 379.25 |  | 398.7 |  | 439.06 |  | 381.53 |  | 379.71 |  | 387.43 |  | 426.3 |  | 387.14 |  | 392.93 |  | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
[22 empty] | 0 | 0 | 0 |  | ROW
| 62/1 |  | 62/2 |  | 62/3 |  | 62/4 |  | 62/5 |  | AP63 |  | 63/1 |  | 63/2 |  | AP64 |  | 64/1
| DA+0 |  | DA+0 |  | DA+09 |  | DA+06 |  | DA+06 |  | DC+00 |  | DA+0 |  | DA+9 |  | DB+09 |  | DA+9
CHECK SURVEY WIP
| 221 |  | 222 |  | 223 |  | 224 |  | 225 |  | 226 |  | 227 |  | 228 |  | 229 |  | 230
0
23 |  | 423.77 |  | 407.9 |  | 426.63 |  | 392.27 |  | 431.96 |  | 426.02 |  | 405.36 |  | 411.93 |  | 350.33 |  | 378.3 |  | 0 | 0 | 0 |  | COM
[17 empty] | U/P |  |  |  |  | 1 | 0 | 0 |  | WIP
[22 empty] | 0 | 0 | 0 |  | ROW
| 64/2 |  | 64/3 |  | 64/4 |  | 64/5 |  | 64/6 |  | AP65 |  | 65/1 |  | AP66 |  | 66/1 |  | AP67
| DA+9 |  | DA+9 |  | DA+9 |  | DA+3 |  | DA+3 |  | DC+00 |  | DB+9 |  | DD+03 |  | DA+06 |  | DC+00
CHECK SURVEY WIP
Paddy
| 231 |  | 232 |  | 233 |  | 234 |  | 235 |  | 236 |  | 237 |  | 238 |  | 239 |  | 240
0
24 |  | 387.92 |  | 418.48 |  | 408.62 |  | 432.92 |  | 430.33 |  | 379.76 |  | 387.45 |  | 425.67 |  | 351.42 |  | 389.3 |  | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
[22 empty] | 0 | 0 | 0 |  | ROW
| 67/1 |  | 67/2 |  | 67/3 |  | 67/4 |  | 67/5 |  | AP68 |  | AP69 |  | 69/1 |  | 69/2 |  | 69/3
| DA+0 |  | DA+6 |  | DA+9 |  | DA+03 |  | DA+0 |  | DB+09 |  | DC+09 |  | DA+0 |  | DA+0 |  | DA+03
CHECK SURVEY WIP
| 241 |  | 242 |  | 243 |  | 244 |  | 245 |  | 246 |  | 247 |  | 248 |  | 249 |  | 250
0
25 |  | 416.82 |  | 371.85 |  | 404.03 |  | 422.11 |  | 388.48 |  | 455.28 |  | 464.05 |  | 376.87 |  | 415.71 |  | 409.51 |  | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
[22 empty] | 0 | 0 | 0 |  | ROW
| AP70 |  | AP71 |  | 71/1 |  | 71/2 |  | AP72 |  | 72/1 |  | 72/2 |  | AP73 |  | 73/1 |  | 73/2
| DD+00 |  | DB+00 |  | DA+03 |  | DA+00 |  | DD+03 |  | DA+06 |  | DA+00 |  | DB+00 |  | DA+09 |  | DA+09
CHECK SURVEY WIP
| 251 |  | 252 |  | 253 |  | 254 |  | 255 |  | 256 |  | 257 |  | 258 |  | 259 |  | 260
0
26 |  | 385.17 |  | 345.19 |  | 332.38 |  | 393.62 |  | 387.95 |  | 340.35 |  | 393.12 |  | 328.54 |  | 398.52 |  | 425.85 |  | 6 | 0 | 3 |  | COM
[7 empty] | F |  | U/P |  | F |  | F |  | F |  | F |  | F |  |  | 1 | 0 | 0 |  | WIP
[11 empty] | Er | [5 empty] | Er |  | Er |  |  | 0 | 0 | 0 |  | ROW
| AP74 |  | 74/1 |  | AP75 |  | 75/1 |  | 75/2 |  | 75/3 |  | 75/4 |  | 75/5 |  | 75/6 |  | 75/7
| DB+09 |  | DA+0 |  | DC+0 |  | DA+00 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0
| CHECK SURVEY WIP |  |  |  | Benching |  | Benching |  | Benching &RC
| 261 |  | 262 |  | 263 |  | 264 |  | 265 |  | 266 |  | 267 |  | 268 |  | 269 |  | 270
0
27 |  | 409.37 |  | 388.46 |  | 380.96 |  | 374.03 |  | 351.96 |  | 395.64 |  | 414.76 |  | 401.93 |  | 354.95 |  | 425..84 |  | 4 | 0 | 0 |  | COM
[7 empty] | F |  | F |  | F |  | F |  | U/P | [6 empty] | 1 | 0 | 0 |  | WIP
[22 empty] | 0 | 0 | 0 |  | ROW
| AP76 |  | 76/1 |  | 77/0 |  | 77/1 |  | 77/2 |  | 77/3 |  | 77/4 |  | 77/5 |  | AP78 |  | 78/1
| DC+00 |  | DA+06 |  | DB+00 |  | DA+00 |  | DA+03 |  | DA+00 |  | DA+03 |  | DA+06 |  | DC+00 |  | DA+03
[9 empty] | Benching | [5 empty] | CLEAR
| 271 |  | 272 |  | 273 |  | 274 |  | 275 |  | 276 |  | 277 |  | 278 |  | 279 |  | 280
0
28 |  | 415.03 |  | 351.18 |  | 441.06 |  | 387.5 |  | 372.63 |  | 415.3 |  | 424.58 |  | 391.7 |  | 410.47 |  | 385.54 |  | 0 | 0 | 0 |  | COM
[9 empty] | ROW |  | ROW |  | ROW |  | ROW |  | ROW |  | ROW |  |  | 0 | 0 | 0 |  | WIP
[19 empty] | U/P |  |  | 6 | 0 | 0 |  | ROW
| AP79 |  | 79/1 |  | 79/2 |  | AP80 |  | 80/1 |  | AP81 |  | 81/1 |  | 81/2 |  | 81/3 |  | 81/4
| DD+00 |  | DA+09 |  | DA+00 |  | DB+03 |  | DA+9 |  | DB+09 |  | DA+00 |  | DA+03 |  | DA+00 |  | DA+00
[5 empty] | Benching |  |  |  | Benching |  |  |  | Benching &RC
| 281 |  | 282 |  | 283 |  | 284 |  | 285 |  | 286 |  | 287 |  | 288 |  | 289 |  | 290
0
29 |  | 418.31 |  | 426.47 |  | 396.98 |  | 429.38 |  | 403.83 |  | 384.63 |  | 380.68 |  | 354.53 |  | 405.57 |  | 416.87 |  | 1 | 0 | 0 |  | COM
| ROW |  | ROW |  | ROW |  | ROW |  | ROW |  | F |  | ROW |  | ROW | [6 empty] | 0 | 0 | 0 |  | WIP
[22 empty] | 7 | 0 | 0 |  | ROW
| 81/5 |  | AP82 |  | 82/1 |  | 82/2 |  | AP83 |  | 83/1 |  | AP84 |  | AP85 |  | 85/1 |  | AP86
| DA+06 |  | DB+03 |  | DA+00 |  | DA+03 |  | DC+00 |  | DA+03 |  | DC+06 |  | DC+00 |  | DA+00 |  | DD+00
[17 empty] | CLEAR |  | CLEAR
| 291 |  | 292 |  | 293 |  | 294 |  | 295 |  | 296 |  | 297 |  | 298 |  | 299 |  | 300
0
30 |  | 380.77 |  | 411.81 |  | 432.08 |  | 256.87 |  | 412.4 |  | 382.17 |  | 452.74 |  | 420.21 |  | 395.01 |  | 386.74 |  | 0 | 0 | 0 |  | COM
| U/P | [20 empty] | 1 | 0 | 0 |  | WIP
[22 empty] | 0 | 0 | 0 |  | ROW
| 86/2 |  | AP87 |  | 87/1 |  | 87/2 |  | AP88 |  | AP89 |  | 89/1 |  | AP90 |  | 90/1 |  | AP91
| DA+00 |  | DC+00 |  | DA+03 |  | DA+09 |  | DC+00 |  | DC+00 |  | DA+09 |  | DC+00 |  | DA+09 |  | DD+00
CLEAR
| 301 |  | 302 |  | 303 |  | 304 |  | 305 |  | 306 |  | 307 |  | 308 |  | 309 |  | 310
0
31 |  | 378.62 |  | 350.22 |  | 357.91 |  | 237.48 |  | 440.03 |  | 504 |  | 430.57 |  | 415.06 |  | 430.39 |  | 414.36 |  | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
[22 empty] | 0 | 0 | 0 |  | ROW
| 91/1 |  | 91/2 |  | 91/3 |  | AP92 |  | AP93 |  | AP94 |  | AP95 |  | 95/1 |  | 95/2 |  | 95A/0
| DA+00 |  | DA+00 |  | DA+00 |  | DC+00 |  | DC+00 |  | DB+06 |  | DB+06 |  | DA+00 |  | DA+06 |  | DB+0
WIP CHECK SURVEY
| 311 |  | 312 |  | 313 |  | 314 |  | 315 |  | 316 |  | 317 |  | 318 |  | 319 |  | 320
0
32 |  | 419.38 |  | 406.18 |  | 427.47 |  | 416.77 |  | 378.13 |  | 358.57 |  | 360.52 |  | 324.53 |  | 354.92 |  | 406.11 |  | 0 | 0 | 0 |  | COM
| ROW | [20 empty] | 0 | 0 | 0 |  | WIP
[22 empty] | 0 | 0 | 0 |  | ROW
| 95A/1 |  | AP96 |  | 96/1 |  | AP97 |  | 97/1 |  | AP98 |  | AP98/1 |  | 98/2 |  | 98/3 |  | 98/4
| DA+00 |  | DC+00 |  | DA+00 |  | DC+00 |  | DA+03 |  | DC+00 |  | DA+00 |  | DA+00 |  | DA+00 |  | DA+00
| 321 |  | 322 |  | 323 |  | 324 |  | 325 |  | 326 |  | 327 |  | 328 |  | 329 |  | 330
|  | 357.82 |  | 424.78 |  | 414.36 |  | 413.59 |  | 432.24 |  | 397.06 |  | 426.06 |  | 417.12 |  | 364.36 |  | 332.45 | 3979.84 | [6 empty] | 3979.84
33 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 98/5 |  | AP99 |  | 99/1 |  | 99/2 |  | 99/3 |  | 99/4 |  | 99/5 |  | 99/6 |  | AP99A |  | 99A/1 |  |  | 0 | 0 | 0 |  | ROW
| DA+06 |  | DB+03 |  | DA+03 |  | DA+00 |  | DA+00 |  | DA+03 |  | DA+03 |  | DA+03 |  | DB+00 |  | DA+06
| 331 |  | 332 |  | 333 |  | 334 |  | 335 |  | 336 |  | 337 |  | 338 |  | 339 |  | 340
|  | 348.85 |  | 381.82 |  | 458.16 |  | 420.55 |  | 426.94 |  | 416.99 |  | 366.19 |  | 351 |  | 251.81 |  | 420 | 3842.31 | [6 empty] | 3842.31
34 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 99A/2 |  | 100/0 |  | 100/1 |  | 101/0 |  | 102/0 |  | 102/1 |  | 102/2 |  | 103/0 |  | 103/1 |  | 104/0 |  |  | 0 | 0 | 0 |  | ROW
| DA+00 |  | DC+06 |  | DD+03 |  | DD+3 |  | DD+3 |  | DA+06 |  | DA+06 |  | DC+0 |  | DA+00 |  | DD+0
| 341 |  | 342 |  | 343 |  | 344 |  | 345 |  | 346 |  | 347 |  | 348 |  | 349 |  | 350
|  | 425 |  | 420 |  | 367.44 |  | 398 |  | 370.48 |  | 437.33 |  | 447 |  | 394.62 |  | 388.49 |  | 440 | 44 | [6 empty] | 4088.36
35 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 104/1 |  | 104/2 |  | 104/3 |  | 105/0 |  | 105/1 |  | 106/0 |  | AP107 |  | 107/1 |  | AP108 |  | AP109 |  |  | 0 | 0 | 0 |  | ROW
| DA+03 |  | DA+09 |  | DA+03 |  | DD+00 |  | DA+3 |  | DC+06 |  | DD+03 |  | DA+9 |  | DC+00 |  | DC+03
| 351 |  | 352 |  | 353 |  | 354 |  | 355 |  | 356 |  | 357 |  | 358 |  | 359 |  | 360
|  | 227.51 |  | 279 |  | 365.62 |  | 217.72 |  | 378.38 |  | 295.12 |  | 390 |  | 428.04 |  | 384 |  | 398.62 | 3364.01 | [6 empty] | 3364.01
36 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 109/1 |  | 110/0 |  | 110/1 |  | AP111 |  | AP112 |  | AP113 |  | AP114 |  | 114/1 |  | AP115 |  | 115/1 |  |  | 0 | 0 | 0 |  | ROW
| DA+06 |  | DD+00 |  | DA+00 |  | DD+09 |  | DB+9 |  | DD+00 |  | DD+00 |  | DA+09 |  | DC+00 |  | DA+03
| 361 |  | 362 |  | 363 |  | 364 |  | 365 |  | 366 |  | 367 |  | 368 |  | 369 |  | 370
|  | 395 |  | 446.11 |  | 398 |  | 390 |  | 419.64 |  | 424.44 |  | 444 |  | 400 |  | 391.11 |  | 413 | 4121.3 | [6 empty] | 4121.3
37 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| AP116 |  | 116/1 |  | AP117 |  | 117/1 |  | 117/2 |  | AP118 |  | AP119 |  | 119/1 |  | 119/2 |  | AP120 |  |  | 0 | 0 | 0 |  | ROW
| DD+00 |  | DA+0 |  | DC+00 |  | DA+0 |  | DA+06 |  | DC+03 |  | DD+03 |  | DA+03 |  | DA+00 |  | DC+00
| 371 |  | 372 |  | 373 |  | 374 |  | 375 |  | 376 |  | 377 |  | 378 |  | 379 |  | 380
|  | 402.25 |  | 250.69 |  | 403 |  | 387 |  | 369.16 |  | 419.36 |  | 421.74 |  | 403 |  | 355 |  | 355 | 3766.2 | [6 empty] | 3766.2
38 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 120/1 |  | AP121 |  | AP122 |  | 122/1 |  | 122/2 |  | AP123 |  | AP124 |  | AP125 |  | 125/1 |  | 125/2 |  |  | 0 | 0 | 0 |  | ROW
| DA+06 |  | DD+00 |  | DC+03 |  | DA+03 |  | DA+03 |  | DC+00 |  | DC+03 |  | DC+03 |  | DA+00 |  | DA+00
| 381 |  | 382 |  | 383 |  | 384 |  | 385 |  | 386 |  | 387 |  | 388 |  | 389 |  | 390
|  | 373.77 |  | 364 |  | 421 |  | 334 |  | 388.22 |  | 398 |  | 442.51 |  | 415 |  | 417.97 |  | 439 | 3993.47 | [6 empty] | 3993.47
39 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 125/3 |  | AP126 |  | 126/1 |  | 126/2 |  | 126/3 |  | AP127 |  | 127/1 |  | AP128 |  | 128/1 |  | AP129 |  |  | 0 | 0 | 0 |  | ROW
| DA+00 |  | DC+00 |  | DA+06 |  | DA+03 |  | DA+06 |  | DD+06 |  | DA+09 |  | DC+03 |  | DA+06 |  | DC+00
| 391 |  | 392 |  | 393 |  | 394 |  | 395 |  | 396 |  | 397 |  | 398 |  | 399 |  | 400
|  | 406 |  | 406.21 |  | 260 |  | 267.27 |  | 395 |  | 408 |  | 352 |  | 373 |  | 367 |  | 384 | 3618.48 | [6 empty] | 3618.48
40 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 129/1 |  | 129/2 |  | AP130 |  | 130/1 |  | 131/0 |  | 131/1 |  | 131/2 |  | 132/0 |  | 132/1 |  | 132/2 |  |  | 0 | 0 | 0 |  | ROW
| DA+03 |  | DA+09 |  | DC+06 |  | DA+00 |  | DD+0 |  | DA+03 |  | DA+03 |  | DD+0 |  | DA+00 |  | DA+00
| 401 |  | 402 |  | 403 |  | 404 |  | 405 |  | 406 |  | 407 |  | 408 |  | 409 |  | 410
|  | 385 |  | 419.37 |  | 288 |  | 404 |  | 411 |  | 411 |  | 419 |  | 425 |  | 409 |  | 407 | 3978.37 | [6 empty] | 3978.37
41 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 132/3 |  | 132/4 |  | AP133 |  | 133/1 |  | 133/2 |  | 133/3 |  | 133/4 |  | 133/5 |  | 133/6 |  | 133/7 |  |  | 0 | 0 | 0 |  | ROW
| DA+00 |  | DA+00 |  | DC+00 |  | DA+00 |  | DA+00 |  | DA+03 |  | DA+03 |  | DA+03 |  | DA+03 |  | DA+00
| 411 |  | 412 |  | 413 |  | 414 |  | 415 |  | 416 |  | 417 |  | 418 |  | 419 |  | 420
|  | 389 |  | 399.98 |  | 408 |  | 405 |  | 418 |  | 425.34 |  | 392 |  | 397 |  | 420 |  | 425.56 | 4079.88 | [6 empty] | 4079.88
42 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 133/8 |  | 133/9 |  | AP134 |  | 134/1 |  | 134/2 |  | 134/3 |  | AP135 |  | 135/1 |  | 135/2 |  | 135/3 |  |  | 0 | 0 | 0 |  | ROW
| DA+03 |  | DA+03 |  | DB+00 |  | DA+03 |  | DA+00 |  | DA+06 |  | DC+00 |  | DA+00 |  | DA+03 |  | DA+06
| 421 |  | 422 |  | 423 |  | 424 |  | 425 |  | 426 |  | 427 |  | 428 |  | 429 |  | 430
|  | 356.03 |  | 426.82 |  | 381 |  | 334 |  | 347 |  | 375.55 |  | 382 |  | 417.97 |  | 390 |  | 407 | 3817.37 | [6 empty] | 3817.37
43 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| AP136 |  | AP137 |  | AP138 |  | 138/1 |  | 138/2 |  | 138/3 |  | AP139 |  | 139/1 |  | AP140 |  | 140/1 |  |  | 0 | 0 | 0 |  | ROW
| DD+00 |  | DB+03 |  | DB+03 |  | DA+00 |  | DA+00 |  | DA+00 |  | DC+03 |  | DA+09 |  | DB+00 |  | DA+03
| 431 |  | 432 |  | 433 |  | 434 |  | 435 |  | 436 |  | 437 |  | 438 |  | 439 |  | 440
|  | 433 |  | 380.33 |  | 386 |  | 391 |  | 399.83 |  | 437.01 |  | 423 |  | 395 |  | 417 |  | 399 | 4061.17 | [6 empty] | 4061.17
44 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 140/2 |  | 140/3 |  | AP141 |  | 141/1 |  | 141/2 |  | AP142 |  | AP143 |  | 143/1 |  | 143/2 |  | 143/3 |  |  | 0 | 0 | 0 |  | ROW
| DA+03 |  | DA+03 |  | DC+00 |  | DA+00 |  | DA+06 |  | DC+03 |  | DC+03 |  | DA+03 |  | DA+00 |  | DA+03
| 441 |  | 442 |  | 443 |  | 444 |  | 445 |  | 446 |  | 447 |  | 448 |  | 449 |  | 450
|  | 420 |  | 409 |  | 412 |  | 400.41 |  | 232.12 |  | 442 |  | 385 |  | 362 |  | 399 |  | 382.07 | 3843.6 | [6 empty] | 3843.6
45 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 143/4 |  | 143/5 |  | 143/6 |  | 143/7 |  | AP144 |  | AP145 |  | 145/1 |  | 145/2 |  | 145/3 |  | 145/4 |  |  | 0 | 0 | 0 |  | ROW
| DA+03 |  | DA+03 |  | DA+00 |  | DA+03 |  | DD+06 |  | DD+06 |  | DA+03 |  | DA+00 |  | DA+00 |  | DA+03
| 451 |  | 452 |  | 453 |  | 454 |  | 455 |  | 456 |  | 457 |  | 458 |  | 459 |  | 460
|  | 392 |  | 422 |  | 409.46 |  | 402 |  | 409 |  | 404 |  | 394 |  | 423 |  | 421 |  | 411 | 4087.46 | [6 empty] | 4087.46
46 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| AP146 |  | 146/1 |  | 146/2 |  | 147/0 |  | 147/1 |  | 147/2 |  | 147/3 |  | 147/4 |  | 147/5 |  | 147/6 |  |  | 0 | 0 | 0 |  | ROW
| DC+00 |  | DA+03 |  | DA+00 |  | DC+00 |  | DA+03 |  | DA+00 |  | DA+03 |  | DA+03 |  | DA+03 |  | DA+03
| 461 |  | 462 |  | 463 |  | 464 |  | 465 |  | 466 |  | 467 |  | 468 |  | 469 |  | 470
|  | 429 |  | 373.37 |  | 403 |  | 402 |  | 387 |  | 386 |  | 413 |  | 407 |  | 390 |  | 392 | 3982.37 | [6 empty] | 3982.37
47 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 147/7 |  | 147/8 |  | 148/0 |  | 148/1 |  | 148/2 |  | 148/3 |  | 148/4 |  | 148/5 |  | 148/6 |  | 148/7 |  |  | 0 | 0 | 0 |  | ROW
| DA+00 |  | DA+09 |  | DB+00 |  | DA+03 |  | DA+00 |  | DA+00 |  | DA+00 |  | DA+03 |  | DA+00 |  | DA+00
| 471 |  | 472 |  | 473 |  | 474 |  | 475 |  | 476 |  | 477 |  | 478 |  | 479 |  | 480
|  | 415 |  | 407.99 |  | 420 |  | 404 |  | 440.94 |  | 249.42 |  | 415.86 |  | 278.87 |  | 426.84 |  | 286.02 | 3744.94 | [6 empty] | 3744.94
48 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 148/8 |  | 148/9 |  | AP149 |  | 149/1 |  | 149/2 |  | AP150 |  | AP151 |  | AP152 |  | AP153 |  | 153/1 |  |  | 0 | 0 | 0 |  | ROW
| DA+00 |  | DA+03 |  | DB+00 |  | DA+03 |  | DCT+00 |  | DD+09 |  | DD+09 |  | DD+18 |  | DD+18 |  | DB+09
| 481 |  | 482 |  | 483 |  | 484 |  | 485
|  | 220.25 |  | 241.31 |  | 214.9 |  | 113.74 | [12 empty] | 790.2 | [6 empty] | 790.2
49 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| AP154 |  | AP155 |  | AP156 |  | AP157 |  | GE | [12 empty] | 0 | 0 | 0 |  | ROW
| DD+30 |  | DD+30 |  | DD+09 |  | DD+00
131357.41
[28 empty] | 131.3574 | 54.6426
[22 empty] | 11 | FDN COM |  | TE COM |  | STR COM
|  |  |  | Crossing Type | 110kV | 230kV | 400kV | 320kV | 765kV | NH-Xing | Railway Xing | Total | Remarks | [8 empty] | 4 | FDN WIP |  | TE WIP |  | STR WIP
|  |  |  | Total Nos | 4 | 3 |  |  |  | 2 | 1 | 10 | [9 empty] | 13 | FDN ROW |  | TE ROW |  | STR ROW
Completed
|  |  |  | Balance | 4 | 3 | 0 | 0 | 0 | 2 | 1 | 10 | [9 empty] | 3 | Earthing COM |  | Tackwelding COM
[5 empty] | Nos | CMP | WIP | Balance | Kms | CMP | WIP | Balance | Remarks
TSE
Manual
Total
Paying out/ Rough sag
[11 empty] | Tack welding completed | [5 empty] | Erection ROW
Erection Completed ------>
|  | Foundation completed ----> | [8 empty] | <------Insulator hosting
|  | Earthing completed -----> |  |  |  |  | U/P | [9 empty] | Erection Cleared
Road
[7 empty] | 325 | Span
[12 empty] | HT-D/C Power Line Crossing |  |  |  |  | Cart Track
| Transformer |  |  | ROW | ROW |  |  | Water Tank
| Temple |  |  | A+0 | Tower Type |  |  | LT Power Line Crossing |  |  |  | HT-S/C Power Line Crossing |  |  |  |  | Broad Gauge Railway
[8 empty] | 11 KV Line Crossing | [8 empty] | Line Crossing
| Hut |  |  | 1/0 | Location No. |  |  | 33 KV Line Crossing
| Bore & Handpump |  |  |  | Minor River Crossing | [6 empty] | Forest Stretch |  |  |  |  | SH Crossing
| Oil Pipe Line |  |  | RC | Raised Chimney |  |  | Major River Crossing |  |  |  | NH Crossing |  |  |  |  | Wild Life Sanctuary
2
2
2
2
2
2
3
2
3
2
2
2
3
3
2
2
3

## ROW (hidden)
NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE
Client : RAJASTHAN IV A POWER TRANSMISSION LTD.
CONTRACTOR : KEC INTERNATIONAL LIMITED
FOUNDATION STATUS
SL. No. | Location Number | Span | Tower Type | AS PER RAPTL ROW CLEARED ON | WORK COMMENCED KEC | STATUS
1 | 80/0
2 | 66/4 |  |  |  | ROW
3 | 89/1 |  |  |  | ROW
4 | 102/1
5 | 102/2 |  |  |  | Anjana Const |  | Previous Loc Done 99/2 on 25/4/2025
6 | 107/1
7 | 90/1 |  |  |  | ROW
8 | 81/1
9 | 51/1
10 | 99A/2
11 | 61/1
12 | 72/2
13 | 73/1
14 | 99/5
15 | 56/2
16 | 63/1
17 | 114/1
18 | 116/1
19 | 56/1
20 | 99A/2
21 | 73/1
22 | 63/1
23 | 114/1
24 | 56/1
25 | 125/2
26 | 84/0
27 | 85/0
28 | 86/0
29 | 110/0
30 | 113A/0
31 | 147/1
32 | 147/7

## June (hidden)
Sl No | Loc No | TOT | Classification | Starting Date | Completion
1 | 81/3 | DA+0 | Sandy | 2025-05-22 | 2025-06-04
2 | 120/1 | DA+6 | Sandy | 2025-05-30 | 2025-06-05
3 | 96/0 | DC+0 | DFR | 2025-05-28 | 2025-06-06
4 | 75/0 | DC+0 | Sandy | 2025-06-01 | 2025-06-07
5 | 147/2 | DA+0 | Sandy | 2025-06-02 | 2025-06-08
6 | 82/2 | DA+0 | Sandy | 2025-06-02 | 2025-06-10
7 | 79/0 | DD+0 | Sandy | 2025-08-08 | 2025-06-12
8 | 147/5 | DA+0 | Sandy | 2025-06-04 | 2025-06-12
9 | 119/0 | DD+3 | Sandy | 2025-06-05 | 2025-06-15
10 | 82/1 | DA+6 | Sandy | 2025-06-10 | 2025-06-15
11 | 147/0 | DC+0 | Sandy | 2025-06-08 | 2025-06-15
12 | 78/0 | DC+0 | Sandy | 2025-06-13 | 2025-06-16
13 | 147/4 | DA+0 | Sandy | 2025-06-13 | 2025-06-16
14 | 74/0 | DB+9 | Sandy | 2025-06-16 | 2025-06-20
15 | 147/1 | DA+0 | Sandy | 2025-06-15 | 2025-06-21
16 | 147/7 | DA+0 | Sandy | 2025-06-15 | 2025-06-22
17 | 95A/0 | DB+0 | DFR | 2025-06-16 | 2025-06-23
18 | 146/2 | DA+0 | Sandy | 2025-06-22 | 2025-06-25
19 | 147/3 | DA+0 | Sandy | 2025-06-22 | 2025-06-25
20 | 73/0 | DB+0 | Sandy | 2025-06-20 | 2025-06-26
21 | 86/0 | DD+0 | Sandy | 2025-06-17 | 2025-06-27
22 | 72/2 | DA+3 | DFR | 2025-06-25 | 2025-06-30
23 | 114/0 | DC+0 | Sandy | 2025-06-10 | 2025-06-30
24 | 146/1 | DA+3 | Sandy | 2025-06-25 | 2025-06-30
25 | 147/8 | DA+0 | Sandy | 2025-06-25 | 2025-06-30

## Foundation
NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE
Client : RAJASTHAN IV A POWER TRANSMISSION LTD.
CONTRACTOR : KEC INTERNATIONAL LIMITED
FOUNDATION STATUS
SL. No. | Location Number | Span | Tower Type | M10 | M20 | Excavation | Reinforcement | Stub | RC | Foundation type
[11 empty] | Starting date | Completion Date | Agency | Remark | Remarks
1 | 83/1 | 83/1 | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-01-08 | 2025-01-17 | Mahadeep Company | 2025-01-17 | RCC Complete, Backfilling Done
2 | 75/7 | 75/7 | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-01-18 | 2025-01-27 | AR Patel Contractor |  | RCC Complete, Backfilling Done
3 | 75/6 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-01-28 | 2025-02-02 | AR Patel Contractor |  | RCC Complete, Backfilling Done
4 | 75/4 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-01-29 | 2025-02-05 | OM Construction |  | RCC Complete, Backfilling Done
5 | 75/5 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-02-03 | 2025-02-05 | AR Patel Contractor |  | RCC Complete, Backfilling Done
6 | 77/2 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-02-03 | 2025-02-09 | AR Patel Contractor |  | RCC Complete, Backfilling Done
7 | 75/3 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 1900-01-23 | 2025-02-10 | OM Construction |  | RCC Complete, Backfilling Done
8 | 77/1 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-02-03 | 2025-02-11 | AAnjana Contractors |  | RCC Complete, Backfilling Done
9 | 77/3 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-02-08 | 2025-02-14 | AR Patel Contractor |  | RCC Complete, Backfilling Done
10 | 75/1 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-02-09 | 2025-02-17 | OM Construction |  | RCC Complete, Backfilling Done
11 | 77/4 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-02-11 | 2025-02-17 | AAnjana Contractors |  | RCC Complete, Backfilling Done
12 | 75/2 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-02-12 | 2025-02-18 | OM Construction |  | RCC Complete, Backfilling Done
13 | 77/5 |  | DA+6 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-02-13 | 2025-02-19 | AR Patel Contractor |  | RCC Complete, Backfilling Done
14 | 73/3 |  | DA+9 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-02-17 | 2025-02-22 | OM Construction |  | RCC Complete, Backfilling Done
15 | 86/2 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-02-10 | 2025-02-22 | Kalpana Enterprises |  | RCC Complete, Backfilling Done
16 | 79/1 |  | DA+9 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-02-17 | 2025-02-23 | AAnjana Contractors |  | RCC Complete, Backfilling Done
17 | 73/2 |  | DA+9 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-02-21 | 2025-02-25 | OM Construction |  | RCC Complete, Backfilling Done
18 | 95A/1 |  | DA+0 | 1.08 | 8.68 | 50.1 | 0.788 | 0.299 |  | DFR | 2025-02-20 | 2025-02-25 | Gurukripa Enterprises |  | RCC Complete, Backfilling Done
19 | 80/1 |  | DA+9 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-02-20 | 2025-02-27 | AR Patel Contractor |  | RCC Complete, Backfilling Done
20 | 66/1 |  | DA+9 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-02-17 | 2025-02-28 | Siyag Construction |  | RCC Complete, Backfilling Done
21 | 74/1 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-02-24 | 2025-02-28 | OM Construction |  | RCC Complete, Backfilling Done
22 | 96/1 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-02-25 | 2025-02-28 | Gurukripa Enterprises |  | RCC Complete, Backfilling Done
23 | 76/1 |  | DA+6 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-02-24 | 2025-03-02 | AAnjana Contractors |  | RCC Complete, Backfilling Done
24 | 66/2 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-02-28 | 2025-03-06 | Siyag Construction |  | RCC Complete, Backfilling Done
25 | 64/3 |  | DA+9 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-03-03 | 2025-03-07 | OM Construction |  | RCC Complete, Backfilling Done
26 | 96/2 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-03-02 | 2025-03-07 | Gurukripa Enterprises |  | RCC Complete, Backfilling Done
27 | 81/2 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-03-02 | 2025-03-08 | AR Patel Contractor |  | RCC Complete, Backfilling Done
28 | 86/1 |  | DA+6 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-02-23 | 2025-03-09 | Kalpana Enterprises |  | RCC Complete, Backfilling Done
29 | 64/4 |  | DA+9 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-03-06 | 2025-03-10 | OM Construction |  | RCC Complete, Backfilling Done
30 | 85/1 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-03-04 | 2025-03-10 | AAnjana Contractors |  | RCC Complete, Backfilling Done
31 | 99/1 |  | DA+6 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-02-27 | 2025-03-10 | Shreeraj Agency |  | RCC Complete, Backfilling Done
32 | 66/3 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-03-05 | 2025-03-11 | Siyag Construction |  | RCC Complete, Backfilling Done
33 | 87/1 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-03-15 | 2025-03-24 | AAnjana Contractors |  | RCC Complete, Backfilling Done
34 | 64/7 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-03-19 | 2025-03-26 | OM Construction |  | RCC Complete, Backfilling Done
35 | 64/6 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-03-25 | 2025-03-30 | OM Construction |  | RCC Complete, Backfilling Done
36 | 87/2 |  | DA+9 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-03-22 | 2025-03-30 | AAnjana Contractors |  | RCC Complete, Backfilling Done
37 | 98A/1 |  | DA+0 | 1.08 | 8.68 | 50.1 | 0.788 | 0.299 |  | DFR | 2025-03-13 | 2025-03-30 | Shreeraj Agency |  | RCC Complete, Backfilling Done
38 | 64/5 |  | DA+9 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-03-29 | 2025-03-31 | OM Construction |  | RCC Complete, Backfilling Done
39 | 98/1 |  | DA+0 | 1.08 | 8.68 | 50.1 | 0.788 | 0.299 |  | DFR | 2025-03-29 | 2025-04-04 | Shreeraj Agency |  | RCC Complete, Backfilling Done
40 | 71/1 |  | DA+9 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-04-04 | 2025-04-09 | OM Construction |  | RCC Complete, Backfilling Done
41 | 91/1 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-04-03 | 2025-04-13 | AAnjana Contractors |  | RCC Complete, Backfilling Done
42 | 91/2 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-03-30 | 2025-04-16 | AAnjana Contractors |  | RCC Complete, Backfilling Done
43 | 51/2 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-03-30 | 2025-04-17 | Ram Shenai Construction |  | RCC Complete, Backfilling Done
44 | 119/1 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-04-15 | 2025-04-18 | OM Construction |  | RCC Complete, Backfilling Done
45 | 95/2 |  | DA+9 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-04-14 | 2025-04-20 | Mundhan Trading Company |  | RCC Complete, Backfilling Done
46 | 119/2 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-04-18 | 2025-04-22 | OM Construction |  | RCC Complete, Backfilling Done
47 | 51/3 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-04-18 | 2025-04-23 | Ram Shenai Construction |  | RCC Complete, Backfilling Done
48 | 99/2 |  | DA+0 | 1.08 | 8.68 | 50.1 | 0.788 | 0.299 |  | DFR | 2025-04-19 | 2025-04-25 | AAnjana Contractors |  | RCC Complete, Backfilling Done
49 | 104B/1 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-04-22 | 2025-04-29 | Gurukripa Enterprizes |  | RCC Complete, Backfilling Done
50 | 62/4 |  | DA+6 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-04-23 | 2025-04-29 | Ram Shenai Construction |  | RCC Complete, Backfilling Done
51 | 81/4 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-04-20 | 2025-04-29 | Mundhan Trading Company |  | RCC Complete, Backfilling Done
52 | 104B/2 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-04-28 | 2025-05-05 | Gurukripa Enterprizes |  | RCC Complete, Backfilling Done
53 | 105/1 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-05-06 | 2025-05-15 | Gurukripa Enterprizes |  | RCC Complete, Backfilling Done
54 | 100/1 |  | DA+6 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-05-04 | 2025-05-18 | Mundhan Trading Company |  | RCC Complete, Backfilling Done
55 | 81/5 |  | DA+6 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-05-13 | 2025-05-21 | Ram Shenai Construction |  | RCC Complete, Backfilling Done
56 | 97/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2025-05-07 | 2025-05-23 | AAnjana Contractors |  | RCC Complete, Backfilling Done
57 | 99C/2 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-05-18 | 2025-05-25 | Mundhan Trading Company |  | RCC Complete, Backfilling Done
58 | 105/0 |  | DD+0 | 2.93 | 20.34 | 224.85 | 2.664 | 0.50145 |  | Sandy | 2025-05-16 | 2025-05-28 | Gurukripa Enterprizes |  | RCC Complete, Backfilling Done
59 | 98A/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | DFR | 2025-05-12 | 2025-05-29 | Ganga Construction Company |  | RCC Complete, Backfilling Done
60 | 62/5 |  | DA+6 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-05-02 | 2025-05-31 | Ram Shenai Construction |  | RCC Complete, Backfilling Done
61 | 81/3 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-05-22 | 2025-06-04 | Ram Shenai Construction |  | RCC Complete, Backfilling Done
62 | 120/1 |  | DA+6 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-05-30 | 2025-06-05 | Majisa Construction |  | RCC Complete, Backfilling Done
63 | 96/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | DFR | 2025-05-28 | 2025-06-06 | Mundhan Trading Company |  | RCC Complete, Backfilling Done
64 | 75/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2025-06-01 | 2025-06-07 | OM Construction |  | RCC Complete, Backfilling Done
65 | 147/2 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-06-02 | 2025-06-08 | JP Enterprises |  | RCC Complete, Backfilling Done
66 | 82/2 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-06-02 | 2025-06-10 | AAnjana Contractors |  | RCC Complete, Backfilling Done
67 | 147/5 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-06-04 | 2025-06-12 | AR Patel Contractor |  | RCC Complete, Backfilling Done
68 | 79/0 |  | DD+0 | 2.93 | 20.34 | 224.85 | 2.664 | 0.50145 |  | Sandy | 2025-08-08 | 2025-06-12 | OM Construction |  | RCC Complete, Backfilling Done
69 | 119/0 |  | DD+3 | 2.93 | 20.34 | 224.85 | 2.664 | 0.50145 |  | Sandy | 2025-06-05 | 2025-06-15 | Majisa Construction |  | RCC Complete, Backfilling Done
70 | 147/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2025-06-08 | 2025-06-15 | JP Enterprises |  | RCC Complete, Backfilling Done
71 | 82/1 |  | DA+6 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-06-10 | 2025-06-15 | AAnjana Contractors |  | RCC Complete, Backfilling Done
72 | 147/4 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-06-13 | 2025-06-16 | AR Patel Contractor1 |  | RCC Complete, Backfilling Done
73 | 78/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2025-06-13 | 2025-06-16 | OM Construction |  | RCC Complete, Backfilling Done
74 | 74/0 |  | DB+9 | 1.68 | 12.41 | 143.4 | 1.728 | 0.414 |  | Sandy | 2025-06-16 | 2025-06-20 | OM Construction |  | RCC Complete, Backfilling Done
75 | 147/1 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-06-15 | 2025-06-21 | JP Enterprises |  | RCC Complete, Backfilling Done
76 | 147/7 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-06-15 | 2025-06-22 | AR Patel Contractor 2 |  | RCC Complete, Backfilling Done
77 | 95A/0 |  | DB+0 | 1.12 | 9.63 | 61.2 | 1.865 | 0.413 |  | DFR | 2025-06-16 | 2025-06-23 | Mundhan Trading Company |  | RCC Complete, Backfilling Done
78 | 146/2 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-06-22 | 2025-06-25 | JP Enterprises |  | RCC Complete, Backfilling Done
79 | 147/3 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-06-22 | 2025-06-25 | AR Patel Contractor |  | RCC Complete, Backfilling Done
80 | 73/0 |  | DB+0 | 1.68 | 12.41 | 143.4 | 1.728 | 0.414 |  | Sandy | 2025-06-20 | 2025-06-26 | OM Construction |  | RCC Complete, Backfilling Done
81 | 86/0 |  | DD+0 | 2.93 | 20.34 | 224.85 | 2.664 | 0.50145 |  | Sandy | 2025-06-17 | 2025-06-27 | AAnjana Contractors |  | RCC Complete, Backfilling Done
82 | 114/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2025-06-10 | 2025-06-30 | Goswami and Co |  | RCC Complete, Backfilling Done
83 | 146/1 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-06-25 | 2025-06-30 | JP Enterprises |  | RCC Complete, Backfilling Done
84 | 147/8 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-06-25 | 2025-06-30 | AR Patel Contractor 2 |  | RCC Complete, Backfilling Done
85 | 72/2 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-06-25 | 2025-06-30 | OM Construction |  | RCC Complete, Backfilling Done
86 | 95/1 |  | DB+0 | 1.12 | 9.63 | 61.2 | 1.865 | 0.413 |  | DFR | 2025-06-23 | 2025-07-04 | Baba Ramdev Construction |  | RCC Complete, Backfilling Done
87 | 148/3 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-06-27 | 2025-07-05 | AR Patel Contractor |  | RCC Complete, Backfilling Done
88 | 106/0 |  | DC+6 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2025-06-25 | 2025-07-06 | Mundhan Trading Company |  | RCC Complete, Backfilling Done
89 | 146/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2025-07-03 | 2025-07-08 | JP Enterprises |  | RCC Complete, Backfilling Done
90 | 148/1 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-07-04 | 2025-07-08 | AR Patel Contractor |  | RCC Complete, Backfilling Done
91 | 114/1 |  | DA+9 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-07-04 | 2025-07-10 | Goswami & Company |  | RCC Complete, Backfilling Done
92 | 148/2 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-07-07 | 2025-07-10 | AR Patel Contractor |  | RCC Complete, Backfilling Done
93 | 80/0 |  | DB+3 | 1.46 | 15.22 | 82 | 1.723 | 0.576 | 1MRC | Sandy | 2025-06-28 | 2025-07-10 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
94 | 141/1 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-07-07 | 2025-07-11 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
95 | 95/0 |  | DB+6 | 1.68 | 12.41 | 143.4 | 1.728 | 0.414 |  | Sandy | 2025-06-27 | 2025-07-11 | Baba Ramdev Construction |  | RCC Complete, Backfilling Done
96 | 148/4 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-07-10 | 2025-07-12 | AR Patel Contractor |  | RCC Complete, Backfilling Done
97 | 141/2 |  | DA+6 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-07-09 | 2025-07-13 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
98 | 145/4 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-07-09 | 2025-07-13 | JP Enterprises |  | RCC Complete, Backfilling Done
99 | 125/1 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-07-04 | 2025-07-14 | Intense Wave Pvt Ltd |  | RCC Complete, Backfilling Done
100 | 133/6 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-07-10 | 2025-07-14 | OM Construction |  | RCC Complete, Backfilling Done
101 | 148/5 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-07-13 | 2025-07-15 | AR Patel Contractor |  | RCC Complete, Backfilling Done
102 | 109A/0 |  | DB+6 | 1.68 | 12.41 | 143.4 | 1.728 | 0.414 |  | Sandy | 2025-07-09 | 2025-07-16 | Mundhan Trading Company |  | RCC Complete, Backfilling Done
103 | 113A/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2025-07-08 | 2025-07-16 | Goswami & Company-1 |  | RCC Complete, Backfilling Done
104 | 133/5 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-07-14 | 2025-07-16 | OM Construction |  | RCC Complete, Backfilling Done
105 | 145/2 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-07-14 | 2025-07-16 | JP Enterprises |  | RCC Complete, Backfilling Done
106 | 142/0 |  | DC+3 | 2.07 | 15.35 | 162.6 | 1.589 | 0.501 |  | Sandy | 2025-07-12 | 2025-07-17 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
107 | 115/0 |  | DC+0,1MRC | [6 empty] | Sandy | 2025-07-10 | 2025-07-18 | Goswami & Company-2 |  | RCC Complete, Backfilling Done
108 | 148/6 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-07-15 | 2025-07-18 | AR Patel Contractor |  | RCC Complete, Backfilling Done
109 | 77/0 |  | DB+0 | 1.12 | 9.63 | 61.2 | 1.865 | 0.413 |  | Sandy | 2025-07-08 | 2025-07-19 | Godara Enterprises |  | RCC Complete, Backfilling Done
110 | 133/4 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-07-17 | 2025-07-21 | OM Construction |  | RCC Complete, Backfilling Done
111 | 143/0 |  | DC+3 | 2.07 | 15.35 | 162.6 | 1.589 | 0.501 |  | Sandy | 2025-07-17 | 2025-07-21 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
112 | 145/1 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-07-16 | 2025-07-21 | JP Enterprises |  | RCC Complete, Backfilling Done
113 | 148/7 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-07-19 | 2025-07-23 | AR Patel Contractor |  | RCC Complete, Backfilling Done
114 | 125/0 |  | DC+3 | 2.07 | 15.35 | 162.6 | 1.589 | 0.501 |  | Sandy | 2025-07-15 | 2025-07-24 | Intense Wave Pvt Ltd |  | RCC Complete, Backfilling Done
115 | 133/3 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-07-22 | 2025-07-24 | OM Construction |  | RCC Complete, Backfilling Done
116 | 94/0 |  | DB+6 | 1.68 | 12.41 | 143.4 | 1.728 | 0.414 |  | Sandy | 2025-07-13 | 2025-07-24 | Baba Ramdev Construction |  | RCC Complete, Backfilling Done
117 | 145/3 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-07-22 | 2025-07-25 | JP Enterprises |  | RCC Complete, Backfilling Done
118 | 126/2 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-07-15 | 2025-07-26 | MS Construction |  | RCC Complete, Backfilling Done
119 | 143/3 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-07-22 | 2025-07-26 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
120 | 133/8 |  | DA+6 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-07-24 | 2025-07-27 | OM Construction |  | RCC Complete, Backfilling Done
121 | 149B/1 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-07-24 | 2025-07-27 | AR Patel Contractor |  | RCC Complete, Backfilling Done
122 | 79/2 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-07-11 | 2025-07-27 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
123 | 110/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2025-07-21 | 2025-07-28 | Mundhan Trading Company |  | RCC Complete, Backfilling Done
124 | 143/1 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-07-25 | 2025-07-29 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
125 | 99/3 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-07-13 | 2025-07-29 | AAnjana Contractors |  | RCC Complete, Backfilling Done
126 | 133/1 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-07-27 | 2025-07-30 | OM Construction |  | RCC Complete, Backfilling Done
127 | 149B/2 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-07-27 | 2025-07-30 | AR Patel Contractor |  | RCC Complete, Backfilling Done
128 | 111/0 |  | DB+9,3MRC | [6 empty] | Sandy | 2025-07-17 | 2025-07-31 | Goswami & Company-1 |  | RCC Complete, Backfilling Done
129 | 116/0 |  | DD+0 | 2.93 | 20.34 | 224.85 | 2.664 | 0.50145 |  | Sandy | 2025-07-23 | 2025-07-31 | Goswami & Company-2 |  | RCC Complete, Backfilling Done
130 | 129/1 |  | DA+9 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-07-25 | 2025-07-31 | Intense Wave Pvt Ltd |  | RCC Complete, Backfilling Done
131 | 133/7 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-07-30 | 2025-07-31 | OM Construction |  | RCC Complete, Backfilling Done
132 | 143/6 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-07-29 | 2025-07-31 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
133 | 145/0 |  | DD+6 | [6 empty] | Sandy | 2025-07-25 | 2025-07-31 | JP Enterprises |  | RCC Complete, Backfilling Done
134 | 76/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2025-07-24 | 2025-07-31 | Baba Ramdev Construction |  | RCC Complete, Backfilling Done
135 | 98B/0 |  | DD+0 | 2.93 | 20.34 | 224.85 | 2.664 | 0.50145 |  | DFR | 2025-06-10 | 2025-07-31 | AAnjana Contractors |  | RCC Complete, Backfilling Done
136 | 126/1 |  | DA+6 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-07-27 | 2025-08-02 | MS Construction |  | RCC Complete, Backfilling Done
137 | 143/7 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-07-30 | 2025-08-02 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
138 | 130/0 |  | DC+6 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2025-07-07 | 2025-08-04 | Sparkle Telenet Service |  | RCC Complete, Backfilling Done
139 | 143/5 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-08-03 | 2025-08-04 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
140 | 97/1 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-07-31 | 2025-08-05 | AAnjana Contractors |  | RCC Complete, Backfilling Done
141 | 143/2 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-08-04 | 2025-08-06 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
142 | 102/2 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-08-01 | 2025-08-07 | Mundhan Trading Company |  | RCC Complete, Backfilling Done
143 | 133/2 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-08-01 | 2025-08-07 | OM Construction |  | RCC Complete, Backfilling Done
144 | 144/0 |  | DD+6 | [6 empty] | Sandy | 2025-08-01 | 2025-08-07 | JP Enterprises |  | RCC Complete, Backfilling Done
145 | 98/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | DFR | 2025-05-26 | 2025-08-07 | AAnjana Contractors |  | RCC Complete, Backfilling Done
146 | 112/0 |  | DC+9 | [6 empty] | Sandy | 2025-08-02 | 2025-08-08 | Goswami & Company-1 |  | RCC Complete, Backfilling Done
147 | 129/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2025-08-01 | 2025-08-08 | Intense Wave Pvt Ltd |  | RCC Complete, Backfilling Done
148 | 143/4 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-08-06 | 2025-08-09 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
149 | 83/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2025-07-29 | 2025-08-09 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
150 | 131/1 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-08-06 | 2025-08-12 | JP Enterprises |  | RCC Complete, Backfilling Done
151 | 149B/0 |  | DB+3 | 1.46 | 15.22 | 82 | 1.723 | 0.576 |  | Sandy | 2025-08-07 | 2025-08-12 | AR Patel Contractor |  | RCC Complete, Backfilling Done
152 | 102/1 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-08-11 | 2025-08-14 | Mundhan Trading Company |  | RCC Complete, Backfilling Done
153 | 140/3 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-08-10 | 2025-08-14 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
154 | 99/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2025-08-05 | 2025-08-14 | AAnjana Contractors |  | RCC Complete, Backfilling Done
155 | 115/1 |  | DB+9 | 1.68 | 12.41 | 143.4 | 1.728 | 0.414 |  | Sandy | 2025-08-05 | 2025-08-16 | Goswami & Company-2 |  | RCC Complete, Backfilling Done
156 | 134A/4 |  | DA+9 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-08-06 | 2025-08-16 | OM Construction |  | RCC Complete, Backfilling Done
157 | 140/2 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-08-11 | 2025-08-17 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
158 | 126/0 |  | DC+6 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2025-08-03 | 2025-08-19 | MS Construction |  | RCC Complete, Backfilling Done
159 | 135/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2025-08-16 | 2025-08-19 | OM Construction |  | RCC Complete, Backfilling Done
160 | 149A/0 |  | DD+0 | 2.93 | 20.34 | 224.85 | 2.664 | 0.50145 |  | Sandy | 2025-08-10 | 2025-08-19 | AR Patel Contractor |  | RCC Complete, Backfilling Done
161 | 128/0 |  | DC+3 | 2.07 | 15.35 | 162.6 | 1.589 | 0.501 |  | Sandy | 2025-08-11 | 2025-08-20 | Intense Wave Pvt Ltd |  | RCC Complete, Backfilling Done
162 | 131/2 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-08-13 | 2025-08-20 | JP Enterprises |  | RCC Complete, Backfilling Done
163 | 141/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2025-08-16 | 2025-08-20 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
164 | 87/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2025-08-12 | 2025-08-22 | Compnay Gang |  | RCC Complete, Backfilling Done
165 | 99/4 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-08-14 | 2025-08-22 | AAnjana Contractors |  | RCC Complete, Backfilling Done
166 | 129/2 |  | DA+9,3MRC | [6 empty] | Sandy | 2025-08-04 | 2025-08-23 | Sparkle Telenet Service |  | RCC Complete, Backfilling Done
167 | 135/1 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-08-20 | 2025-08-23 | OM Construction |  | RCC Complete, Backfilling Done
168 | 138/1 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-08-21 | 2025-08-23 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
169 | 137/0 |  | DB+3 | 1.46 | 15.22 | 82 | 1.723 | 0.576 |  | Sandy | 2025-08-05 | 2025-08-24 | Bajrang Construction Company |  | RCC Complete, Backfilling Done
170 | 63/1 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-08-16 | 2025-08-24 | Bhawna Construction Co |  | RCC Complete, Backfilling Done
171 | 132/1 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-08-20 | 2025-08-25 | JP Enterprises |  | RCC Complete, Backfilling Done
172 | 138/2 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-08-22 | 2025-08-25 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
173 | 134A/2 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-08-24 | 2025-08-26 | OM Construction |  | RCC Complete, Backfilling Done
174 | 56/4 |  | DA+6 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-08-20 | 2025-08-26 | SM Infrastructure |  | RCC Complete, Backfilling Done
175 | 56/2 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-08-16 | 2025-08-27 | SM Infrastructure |  | RCC Complete, Backfilling Done
176 | 138/0 |  | DB+3 | 1.46 | 15.22 | 82 | 1.723 | 0.576 |  | Sandy | 2025-08-22 | 2025-08-28 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
177 | 149/0 |  | DD+0 | 2.93 | 20.34 | 224.85 | 2.664 | 0.50145 |  | Sandy | 2025-08-18 | 2025-08-28 | AR Patel Contractor |  | RCC Complete, Backfilling Done
178 | 134/0 |  | DD+0 | 2.93 | 20.34 | 224.85 | 2.664 | 0.50145 |  | Sandy | 2025-08-24 | 2025-08-29 | Sparkle Telenet Service |  | RCC Complete, Backfilling Done
179 | 134A/1 |  | DA+9 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-08-25 | 2025-08-29 | OM Construction |  | RCC Complete, Backfilling Done
180 | 116/1 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-08-22 | 2025-08-31 | Goswami & Company |  | RCC Complete, Backfilling Done
181 | 132/3 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-08-26 | 2025-08-31 | JP Enterprises |  | RCC Complete, Backfilling Done
182 | 134A/0 |  | DD+0 | 2.93 | 20.34 | 224.85 | 2.664 | 0.50145 |  | Sandy | 2025-08-25 | 2025-08-31 | Intense Wave Pvt Ltd |  | RCC Complete, Backfilling Done
183 | 138/3 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-08-26 | 2025-08-31 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
184 | 82/0 |  | DB+3 | 1.46 | 15.22 | 82 | 1.723 | 0.576 |  | Sandy | 2024-08-23 | 2025-08-31 | Mundhan Trading Company |  | RCC Complete, Backfilling Done
185 | 85/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | DFR | 2025-08-22 | 2025-08-31 | Gurukripa(Company Gang) |  | RCC Complete, Backfilling Done
186 | 99A/0 |  | DB+6 | 1.68 | 12.41 | 143.4 | 1.728 | 0.414 |  | Sandy | 2025-08-23 | 2025-08-31 | AAnjana Contractors |  | RCC Complete, Backfilling Done
187 | 56/5 |  | DA+6 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-08-26 | 2025-08-31 | SM Infrastructure |  | RCC Complete, Backfilling Done
188 | 131/0 |  | DD+0 | 2.93 | 20.34 | 224.85 | 2.664 | 0.50145 |  | Sandy | 2025-08-31 | 2025-09-04 | Sparkle Telenet Service |  | RCC Complete, Backfilling Done
189 | 139/0 |  | DC+3 | [5 empty] | 1MRC | Sandy | 2025-08-29 | 2025-09-05 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
190 | 147/6 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-09-01 | 2025-09-05 | AR Patel Contractor |  | RCC Complete, Backfilling Done
191 | 125/3 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-09-05 | 2025-09-10 | Intense Wave Pvt Ltd |  | RCC Complete, Backfilling Done
192 | 57/0 |  | DB+9 | 1.68 | 12.41 | 143.4 | 1.728 | 0.414 |  | Sandy | 2025-09-03 | 2025-09-10 | SM Infrastructure |  | RCC Complete, Backfilling Done
193 | 59/0 |  | DC+9 | 2.07 | 15.35 |  | 1.589 | 0.501 |  | Sandy | 2025-09-05 | 2025-09-12 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
194 | 81/0 |  | DB+9 | 1.68 | 12.41 | 143.4 | 1.728 | 0.414 |  | Sandy | 2025-09-04 | 2025-09-12 | Mundhan Trading Company |  | RCC Complete, Backfilling Done
195 | 147/9 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-09-06 | 2025-09-14 | AR Patel Contractor |  | RCC Complete, Backfilling Done
196 | 64/0 |  | DC+9,1MRC | [6 empty] | Sandy | 2025-08-25 | 2025-09-14 | Bhawna Construction Co |  | RCC Complete, Backfilling Done
197 | 58/0 |  | DB+9 | 1.68 | 12.41 | 143.4 | 1.728 | 0.414 |  | Sandy | 2025-09-12 | 2025-09-17 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
198 | 125/2 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-09-13 | 2025-09-18 | Intense Wave Pvt Ltd |  | RCC Complete, Backfilling Done
199 | 72/1 | DA+3(C-1MRC,D-3MRC | DA+3(C-1MRC,D-3MRC | 2.01 | 16.69 |  | 1.399 | 0.4 |  | Sandy | 2025-08-12 | 2025-09-19 | Harish Infratech Service |  | RCC Complete, Backfilling Done
200 | 56/1 |  | DB+9 | 1.68 | 12.41 | 143.4 | 1.728 | 0.414 |  | Sandy | 2025-09-12 | 2025-09-20 | SM Infrastructure |  | RCC Complete, Backfilling Done
201 | 136/0 |  | DD+0 | 2.93 | 20.34 | 224.85 | 2.664 | 0.50145 |  | Sandy | 2025-09-03 | 2025-09-21 | OM Construction |  | RCC Complete, Backfilling Done
202 | 132/4 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-09-04 | 2025-09-25 | JP Enterprises |  | RCC Complete, Backfilling Done
203 | 48/0 |  | DD+3 | 2.93 | 20.34 | 224.85 | 2.664 | 0.50145 |  | Sandy | 2025-09-21 | 2025-09-25 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
204 | 123/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2025-09-22 | 2025-09-30 | Intense Wave Pvt Ltd |  | RCC Complete, Backfilling Done
205 | 133/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2025-09-11 | 2025-09-30 | JP Enterprises |  | RCC Complete, Backfilling Done
206 | 152/0 |  | DD+18 | [6 empty] | DFR | 2025-09-17 | 2025-09-30 | Sparkle Telenet Service |  | RCC Complete, Backfilling Done
207 | 153A/0 |  | DB+0 | 1.12 | 9.63 | 61.2 | 1.865 | 0.413 |  | DFR | 2025-09-22 | 2025-09-30 | OM Construction |  | RCC Complete, Backfilling Done
208 | 135/2 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-10-01 | 2025-10-11 | JP Enterprises |  | RCC Complete, Backfilling Done
209 | 149B/3 |  | DB+9 | 1.68 | 12.41 | 143.4 | 1.728 | 0.414 |  | Sandy | 2025-10-01 | 2025-10-13 | Intense Wave Pvt Ltd |  | RCC Complete, Backfilling Done
210 | 135/3 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-10-10 | 2025-10-16 | JP Enterprises |  | RCC Complete, Backfilling Done
211 | 73/1 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-10-04 | 2025-10-16 | Mundhan Trading Company |  | RCC Complete, Backfilling Done
212 | 84/0 |  | DC+6 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2025-10-10 | 2025-10-19 | Gurukripa |  | RCC Complete, Backfilling Done
213 | 150/0 |  | DD+9 | [6 empty] | DFR | 2025-10-14 | 2025-10-29 | Intense Wave Pvt Ltd |  | RCC Complete, Backfilling Done
214 | 71/2 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-10-16 | 2025-10-30 | Mundhan Trading Company |  | RCC Complete, Backfilling Done
215 | 134A/3 |  | DA+6 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-10-27 | 2025-10-31 | JP Enterprises |  | RCC Complete, Backfilling Done
216 | 148/0 |  | DB+0 | 1.12 | 9.63 | 61.2 | 1.865 | 0.413 |  | Sandy | 2025-10-16 | 2025-11-04 | AR Patel Contractor |  | RCC Complete, Backfilling Done
217 | 71/3 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-10-29 | 2025-11-07 | Mundhan Trading Company |  | RCC Complete, Backfilling Done
218 | 151/0 |  | DD+9 | [6 empty] | DFR | 2025-10-29 | 2025-11-08 | Intense Wave Pvt Ltd |  | RCC Complete, Backfilling Done
219 | 78/1 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-10-27 | 2025-11-08 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
220 | 81/1 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-10-29 | 2025-11-10 | Mahadev Construction Company2 |  | RCC Complete, Backfilling Done
221 | 140/1 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-11-06 | 2025-11-11 | JP Enterprises |  | RCC Complete, Backfilling Done
222 | 89/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2025-11-04 | 2025-11-12 | AAnjana Contractors |  | RCC Complete, Backfilling Done
223 | 71/0 |  | DB+0 | 1.12 | 9.63 | 61.2 | 1.865 | 0.413 |  | Sandy | 2025-11-08 | 2025-11-14 | Mundhan Trading Company |  | RCC Complete, Backfilling Done
224 | 113/0 |  | DD+0 | 2.93 | 20.34 | 224.85 | 2.664 | 0.50145 |  | Sandy | 2025-10-31 | 2025-11-16 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
225 | 139/1 |  | DA+9 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-11-11 | 2025-11-16 | JP Enterprises |  | RCC Complete, Backfilling Done
226 | 72/0 |  | DD+0 | 2.93 | 20.34 | 224.85 | 2.664 | 0.50145 |  | Sandy | 2025-09-26 | 2025-11-17 | Harish Infratech Service |  | RCC Complete, Backfilling Done
227 | 89/1 |  | DA+9 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-11-13 | 2025-11-18 | AAnjana Contractors |  | RCC Complete, Backfilling Done
228 | 140/0 |  | DB+0 | 1.12 | 9.63 | 61.2 | 1.865 | 0.413 |  | Sandy | 2025-11-14 | 2025-11-22 | JP Enterprises 1 |  | RCC Complete, Backfilling Done
229 | 154/0 |  | DD+0 | 2.93 | 20.34 | 224.85 | 2.664 | 0.50145 |  | DFR | 2025-11-03 | 2025-11-22 | Intense Wave Pvt Ltd |  | RCC Complete, Backfilling Done
230 | 90/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2025-11-12 | 2025-11-22 | Mahadev Construction Company2 |  | RCC Complete, Backfilling Done
231 | 90/1 |  | DA+9 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-11-18 | 2025-11-26 | AAnjana Contractors |  | RCC Complete, Backfilling Done
232 | 127/1 |  | DA+9 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-11-23 | 2025-11-28 | JP Enterprise 1 |  | RCC Complete, Backfilling Done
233 | 153/0 |  | DD+18 | [6 empty] | DFR | 2025-11-20 | 2025-11-30 | Intense Wave Pvt Ltd |  | RCC Complete, Backfilling Done
234 | 66/0 |  | DD+0 | 2.93 | 20.34 | 224.85 | 2.664 | 0.50145 |  | Sandy | 2025-11-15 | 2025-11-30 | Mundhan Trading Company |  | RCC Complete, Backfilling Done
235 | 118/0 |  | DC+3 | 2.07 | 15.35 | 162.6 | 1.589 | 0.501 |  | Sandy | 2025-12-01 | 2025-12-05 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
236 | 88/0 |  | DC+6 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2025-11-23 | 2025-12-05 | AAnjana Contractors |  | RCC Complete, Backfilling Done
237 | 130/1 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-11-27 | 2025-12-06 | JP Enterprise |  | RCC Complete, Backfilling Done
238 | 98B/2 |  | DCT+0 | [6 empty] | Sandy | 2025-11-29 | 2025-12-08 | Mahadev Construction Company2 |  | RCC Complete, Backfilling Done
239 | 117/0 |  | DD+0 | 2.93 | 20.34 | 224.85 | 2.664 | 0.50145 |  | Sandy | 2025-12-07 | 2025-12-13 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
240 | 128/1 |  | DA+6 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-12-06 | 2025-12-14 | JP Enterprise |  | RCC Complete, Backfilling Done
241 | 117/1 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2025-12-15 | 2025-12-19 | Mahadev Construction Company2 |  | RCC Complete, Backfilling Done
242 | 132/2 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-12-14 | 2025-12-20 | JP Enterprise |  | RCC Complete, Backfilling Done
243 | 91/0 |  | DD+0 | 2.93 | 20.34 | 224.85 | 2.664 | 0.50145 |  | Sandy | 2025-12-14 | 2025-12-24 | AAnjana Contractors |  | RCC Complete, Backfilling Done
244 | 132/0 |  | DD+0 | 2.93 | 20.34 | 224.85 | 2.664 | 0.50145 |  | Sandy | 2025-12-18 | 2025-12-28 | Intense Wave Pvt Ltd |  | RCC Complete, Backfilling Done
245 | 124/0 |  | DC+3 | 2.07 | 15.35 | 162.6 | 1.589 | 0.473 |  | Sandy | 2025-12-22 | 2025-12-30 | JP Enterprise |  | RCC Complete, Backfilling Done
246 | 104A/0 |  | DC+9 | [6 empty] | Sandy | 2025-12-21 | 2025-12-30 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
247 | 91/3 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2025-12-27 | 2025-12-31 | AAnjana Contractors |  | RCC Complete, Backfilling Done
248 | 104B/0 |  | DB+9 | 1.68 | 12.41 | 143.4 | 1.728 | 0.414 |  | Sandy | 2025-12-26 | 2026-01-04 | Mahadev Construction Company2 |  | RCC Complete, Backfilling Done
249 | 65/0 |  | DD+0 | 2.93 | 20.34 | 224.85 | 2.664 | 0.50145 |  | Sandy | 2025-12-27 | 2026-01-07 | Mundhan Construction |  | RCC Complete, Backfilling Done
250 | 122/2 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2026-01-02 | 2026-01-08 | JP Enterprise |  | RCC Complete, Backfilling Done
251 | 126/3 |  | DA+6 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2026-01-05 | 2026-01-15 | Intense Wave Pvt Ltd |  | RCC Complete, Backfilling Done
252 | 69/3 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2026-01-05 | 2026-01-15 | AAnjana Contractors |  | RCC Complete, Backfilling Done
253 | 65/1 |  | DB+9 | 1.68 | 12.41 | 143.4 | 1.728 | 0.414 |  | Sandy | 2026-01-08 | 2026-01-15 | Mundhan Construction |  | RCC Complete, Backfilling Done
254 | 108/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2026-01-15 | 2026-01-20 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
255 | 109/0 |  | DC+3 | 2.07 | 15.35 | 162.6 | 1.589 | 0.473 |  | Sandy | 18-01-02026 | 2026-01-23 | Intense Wave Pvt Ltd |  | RCC Complete, Backfilling Done
256 | 10/3 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2026-01-20 | 2026-01-23 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
257 | 120/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2026-01-21 | 2026-01-25 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
258 | 10/5 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2026-01-25 | 2026-01-26 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
259 | 92/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2026-01-24 | 2026-01-28 | Mahadev Construction Company2 |  | RCC Complete, Backfilling Done
260 | 10/6 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2026-01-27 | 2026-01-28 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
261 | 93/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2026-01-25 | 2026-01-30 | Intense Wave Pvt Ltd |  | RCC Complete, Backfilling Done
262 | 10/7 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2026-01-28 | 2026-01-30 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
263 | 7/7 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2026-02-02 | 2026-02-04 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
264 | 7/9 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2026-02-02 | 2026-02-06 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
265 | 10/12 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2026-02-08 | 2026-02-12 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
266 | 4/0 |  | DD+18 | 3.04 | 21.92 | 157.5 | 4.485 |  |  | DFR | 2026-02-18 | 2026-02-28 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
267 | 117/2 |  | DB+9 | 1.68 | 12.41 | 143.4 | 1.728 | 0.414 |  | Sandy | 2026-02-21 | 2026-02-28 | Mahadev Construction Company |  | RCC Complete, Backfilling Done | 185
268 | 157/0 |  | DD+0 | 2.93 | 20.34 | 224.85 | 2.664 | 0.50145 |  | DFR | 2026-02-16 | 2026-03-04 | Mahadev Construction Company2 |  | RCC Complete, Backfilling Done
269 | 156/0 |  | DD+0 | 2.93 | 20.34 | 224.85 | 2.664 | 0.50145 |  | DFR | 2026-02-14 | 2026-03-10 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
270 | 98B/1 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2026-02-19 | 2026-03-11 | Mahadev Construction Company |  | RCC Complete, Backfilling Done
271 | 103/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2026-03-12 | 2026-03-19 | Mundhan Construction |  | RCC Complete, Backfilling Done | 5
272 | 10/8 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2026-03-20 | 2026-03-22 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
273 | 8/2 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2026-03-20 | 2026-03-25 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
274 | 7/1 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2026-03-24 | 2026-03-26 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
275 | 3/0B |  | UCS | 2.38 | 29.26 | 140.44 | 4.531 |  |  | DFR | 2026-03-20 | 2026-03-26 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
276 | 3/0A |  | UCS | 2.38 | 29.26 | 140.44 | 4.531 |  |  | DFR | 2026-03-23 | 2026-03-28 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
277 | 8/1 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2026-04-02 | 2026-04-06 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
278 | 3/1 |  | DD+3 1M RC | [6 empty] | DFR | 2026-03-27 | 2026-04-07 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
279 | 2/1B |  | UCS | 2.38 | 29.26 | 140.44 | 4.531 |  |  | DFR | 2026-04-03 | 2026-04-08 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
280 | 2/1 A |  | UCS | 2.38 | 29.26 | 140.44 | 4.531 |  |  | DFR | 2026-03-28 | 2026-04-09 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
281 | 103/1 |  | DA+6 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2026-04-03 | 2026-04-10 | Mundhan Construction |  | RCC Complete, Backfilling Done
282 | 8/0 |  | DB+0 | 1.12 | 9.63 | 61.2 | 1.865 | 0.413 |  | Sandy | 2026-04-06 | 2026-04-11 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
283 | 9/3 |  | DA+3 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2026-04-10 | 2026-04-14 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
284 | 99C/0 |  | DD+0 | 2.93 | 20.34 | 224.85 | 2.664 | 0.50145 |  | Sandy | 2026-04-10 | 2026-04-15 | Mundhan Construction |  | RCC Complete, Backfilling Done
285 | 9/4 |  | DA+6 | 1.86 | 12.47 | 134.7 | 1.115 | 0.299 |  | Sandy | 2026-04-10 | 2026-04-15 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
286 | 9/5 |  | DB+6 | 1.68 | 12.41 | 143.4 | 1.728 | 0.414 |  | Sandy | 2026-04-17 | 2026-04-21 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
287 | 100/0 |  | DC+0 | 1.6 | 13.13 | 87.25 | 1.374 | 0.501 |  | Sandy | 2026-04-16 | 2026-04-24 | Mundhan Construction |  | RCC Complete, Backfilling Done
288 | 7/2 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2026-03-27 |  | Karni Mata Construction Company |  | Prop set Next: Work start after clear ROW
289 | 154/1A |  | UCS | 2.38 | 29.26 | 140.44 | 4.531 |  |  | DFR | 2026-04-18 |  | Sparkle Telenet |  | Steel Binding Todays’ Plan: Steel Binding/Frustum
290 | 154/2A |  | UCS | 2.38 | 29.26 | 140.44 | 4.531 |  |  | DFR | 2026-04-18 |  | Ipsa systems India Pvt. Ltd. |  | Excavation WIP Todays’ Plan: Prope Setting.
291 | 10/14 |  | DA+0 | 1.57 | 11.05 | 115.3 | 0.919 | 0.299 |  | Sandy | 2026-04-20 |  | Karni Mata Construction Company |  | 3 pit Frustrum, Pyramid, Next Plan: 4th Pit Prope Setting
292 | 11/0 |  | DB+0 | 1.12 | 9.63 | 61.2 | 1.865 | 0.413 |  | Sandy | 2026-04-24 |  | Karni Mata Construction Company |  | Excavation WIP
293 | 10/0 |  | DC+3 | 2.07 | 15.35 | 162.6 | 1.589 | 0.473 |  | Sandy |  |  | Karni Mata Construction Company |  | Pit Marking

## Royalty (hidden)
OM Construction
Loc No | TOT | M-10 | M-20
120/1 | DA+6 | 1.86 | 12.47 |  |  |  | 75/0 | DC+0 | 1.6 | 13.13
119/0 | DD+3 | 2.93 | 20.34 |  |  |  | 79/0 | DD+0 | 2.93 | 20.34
| CUM | 4.79 | 32.81 |  |  | ROYALTY ISSUED | 78/0 | DC+0 | 1.6 | 13.13
CUM | 20MM | 4.426 | 27.5604 | 31.9864 |  | 20MM | 74/0 | DB+9 | 1.68 | 12.41
CUM | SAND | 2.0448 | 11.5754 | 13.6202 |  | 18.48 | 73/0 | DB+0 | 1.68 | 12.41
MT | 20MM |  |  | 51.1782 | Required | 14.67 | 72/2 | DA+3 | 1.86 | 12.47
MT | SAND |  |  | 21.7923 | Required | 33.15 |  |  | 11.35 | 83.89
[7 empty] | CUM | 20MM | 10.4874 | 70.4676 | 80.955
[7 empty] | CUM | SAND | 4.8452 | 29.5964 | 34.4416
77/1 | DA+0 | 1.57 | 11.05 |  |  |  | MT | 20MM |  |  | 129.528
77/4 | DA+3 | 1.86 | 12.47 |  |  |  | MT | SAND |  |  | 55.1065
79/1 | DA+9 | 1.86 | 12.47
76/1 | DA+6 | 1.86 | 12.47
85/1 | DA+0 | 1.57 | 11.05 |  |  |  | JP Enterprises
87/1 | DA+3 | 1.86 | 12.47 |  |  |  |  | 147/2 | DA+0 | 1.57 | 11.05
87/2 | DA+9 | 1.86 | 12.47 |  |  |  |  | 147/0 | DC+0 | 1.6 | 13.13
91/1 | DA+0 | 1.57 | 11.05 |  |  |  |  | 147/1 | DA+0 | 1.57 | 11.05
91/2 | DA+0 | 1.57 | 11.05 |  |  |  |  | 146/2 | DA+0 | 1.57 | 11.05
99/2 | DA+0 | 1.08 | 8.68 |  |  |  |  | 146/1 | DA+3 | 1.86 | 12.47
97/0 | DC+0 | 1.6 | 13.13 | [6 empty] | 8.17 | 58.75
82/2 | DA+0 | 1.57 | 11.05 |  |  |  |  | CUM | 20MM | 7.5491 | 49.35 | 56.8991
82/1 | DA+6 | 1.86 | 12.47 |  |  |  |  | CUM | SAND | 3.4877 | 20.727 | 24.2147
86/0 | DD+0 | 2.93 | 20.34 |  |  |  |  | MT | 20MM |  |  | 91.0385
85/0 | DC+0 | 1.6 | 13.13 |  |  |  |  | MT | SAND |  |  | 38.7435
|  | 26.22 | 185.35 | [9 empty] | Balance
CUM | 20MM | 24.2273 | 155.694 | 179.9213 |  |  | Submitted | MT | 20MM |  |  | 68.58 | 22.4585
CUM | SAND | 11.193 | 65.3915 | 76.5845
MT | 20MM |  |  | 287.874
MT | SAND |  |  | 122.5352

## Sheet14 (hidden)
1 | 95/1 | DB+0 |  | DFR | 2025-06-23 | 2025-07-04 | Baba Ramdev Construction | RCC Complete, Backfilling Done
2 | 148/3 | DA+0 |  | Sandy | 2025-06-27 | 2025-07-05 | AR Patel | RCC Complete, Backfilling Done
3 | 106/0 | DC+6 |  | Sandy | 2025-06-25 | 2025-07-06 | Mundhan Trading Company | RCC Complete, Backfilling Done
4 | 148/1 | DA+0 |  | Sandy | 2025-07-04 | 2025-07-08 | AR Patel | RCC Complete, Backfilling Done
5 | 146/0 | DC+0 |  | Sandy | 2025-07-03 | 2025-07-08 | JP Enterprises | RCC Complete, Backfilling Done
6 | 80/0 | DB+3 | 1MRC | Sandy | 2025-06-28 | 2025-07-10 | Mahadev Enterprises | RCC Complete, Backfilling Done
7 | 114/1 | DA+9 |  | Sandy | 2025-07-04 | 2025-07-10 | Goswami and Company | RCC Complete, Backfilling Done
8 | 148/2 | DA+0 |  | Sandy | 2025-07-07 | 2025-07-10 | AR Patel | RCC Complete, Backfilling Done
9 | 95/0 | DB+6 |  | Sandy | 2025-06-27 | 2025-07-11 | Baba Ramdev Construction | RCC Complete, Backfilling Done
10 | 141/1 | DA+0 |  | Sandy | 2025-07-07 | 2025-07-11 | Mahadev Construction | RCC Complete, Backfilling Done
11 | 148/4 | DA+0 |  | Sandy | 2025-07-10 | 2025-07-12 | AR Patel | RCC Complete, Backfilling Done
12 | 141/2 | DA+6 |  | Sandy | 2025-07-09 | 2025-07-13 | Mahadev Construction | RCC Complete, Backfilling Done
13 | 145/4 | DA+3 |  | Sandy | 2025-07-09 | 2025-07-13 | JP Enterprises | RCC Complete, Backfilling Done
14 | 133/6 | DA+3 |  | Sandy | 2025-07-10 | 2025-07-14 | OM Construction | RCC Complete, Backfilling Done
15 | 125/1 | DA+0 |  | Sandy | 2025-07-04 | 2025-07-14 | Instance Wave Pvt Ltd | RCC Complete, Backfilling Done
16 | 148/5 | DA+0 |  | Sandy | 2025-07-13 | 2025-07-15 | AR Patel | RCC Complete, Backfilling Done
17 | 109A/0 | DB+6 |  | Sandy | 2025-07-09 | 2025-07-16 | Mundhan Construction | RCC Complete, Backfilling Done
18 | 113A/0 | DC+0 |  | Sandy | 2025-07-08 | 2025-07-16 | Goswami and Company-1 | RCC Complete, Backfilling Done
19 | 133/5 | DA+0 |  | Sandy | 2025-07-14 | 2025-07-16 | OM Construction | RCC Complete, Backfilling Done
20 | 145/2 | DA+0 |  | Sandy | 2025-07-14 | 2025-07-16 | JP Enterprises | RCC Complete, Backfilling Done
21 | 142/0 | DC+3 |  | Sandy | 2025-07-12 | 2025-07-17 | Mahadev Construction | RCC Complete, Backfilling Done
22 | 115/0 | DC+0,1MRC |  | Sandy | 2025-07-10 | 2025-07-18 | Goswami and Company-2 | RCC Complete, Backfilling Done
23 | 148/6 | DA+0 |  | Sandy | 2025-07-15 | 2025-07-18 | AR Patel | RCC Complete, Backfilling Done
24 | 77/0 | DB+0 |  | Sandy | 2025-07-08 | 2025-07-19 | Godara Enterprises | RCC Complete, Backfilling Done
25 | 133/4 | DA+0 |  | Sandy | 2025-07-17 | 2025-07-21 | OM Construction | RCC Complete, Backfilling Done
26 | 143/0 | DC+3 |  | Sandy | 2025-07-17 | 2025-07-21 | Mahadev Construction | RCC Complete, Backfilling Done
27 | 145/1 | DA+3 |  | Sandy | 2025-07-16 | 2025-07-21 | JP Enterprises | RCC Complete, Backfilling Done
28 | 148/7 | DA+0 |  | Sandy | 2025-07-19 | 2025-07-23 | AR Patel | RCC Complete, Backfilling Done
29 | 125/0 | DC+3 |  | Sandy | 2025-07-15 | 2025-07-24 | Instance Wave Pvt Ltd | RCC Complete, Backfilling Done
30 | 94/0 | DB+6 |  | Sandy | 2025-07-13 | 2025-07-24 | Baba Ramdev Construction | RCC Complete, Backfilling Done
31 | 133/3 | DA+0 |  | Sandy | 2025-07-22 | 2025-07-24 | OM Construction | RCC Complete, Backfilling Done
32 | 145/3 | DA+0 |  | Sandy | 2025-07-22 | 2025-07-25 | JP Enterprises | RCC Complete, Backfilling Done
33 | 126/2 | DA+3 |  | Sandy | 2025-07-15 | 2025-07-26 | MS Construction | RCC Complete, Backfilling Done
34 | 143/3 | DA+3 |  | Sandy | 2025-07-22 | 2025-07-26 | Mahadev Construction | RCC Complete, Backfilling Done
35 | 79/2 | DA+0 |  | Sandy | 2025-07-11 | 2025-07-27 | Mahadev Enterprises | RCC Complete, Backfilling Done
36 | 133/8 | DA+6 |  | Sandy | 2025-07-24 | 2025-07-27 | OM Construction | RCC Complete, Backfilling Done
37 | 149B/1 | DA+3 |  | Sandy | 2025-07-24 | 2025-07-27 | AR Patel | RCC Complete, Backfilling Done
38 | 110/0 | DC+0 |  | Sandy | 2025-07-21 | 2025-07-28 | Mundhan Construction | RCC Complete, Backfilling Done
39 | 99/3 | DA+3 |  | Sandy | 2025-07-13 | 2025-07-29 | Anjana Construction | RCC Complete, Backfilling Done
40 | 143/1 | DA+3 |  | Sandy | 2025-07-25 | 2025-07-29 | Mahadev Construction | RCC Complete, Backfilling Done
41 | 133/1 | DA+0 |  | Sandy | 2025-07-27 | 2025-07-30 | OM Construction | RCC Complete, Backfilling Done
42 | 149B/2 | DA+0 |  | Sandy | 2025-07-27 | 2025-07-30 | AR Patel | RCC Complete, Backfilling Done
43 | 145/0 | DD+6 |  | Sandy | 2025-07-25 | 2025-07-31 | JP Enterprises | RCC Complete, Backfilling Done
44 | 143/6 | DA+0 |  | Sandy | 2025-07-29 | 2025-07-31 | Mahadev Construction | RCC Complete, Backfilling Done
45 | 133/7 | DA+0 |  | Sandy | 2025-07-30 | 2025-07-31 | OM Construction | RCC Complete, Backfilling Done
46 | 129/1 | DA+9 |  | Sandy | 2025-07-25 | 2025-07-31 | Instance Wave Pvt Ltd | RCC Complete, Backfilling Done
47 | 111/0 | DB+9,3MRC |  | Sandy | 2025-07-17 | 2025-07-31 | Goswami and Company-1 | RCC Complete, Backfilling Done
48 | 98B/0 | DD+0 |  | DFR | 2025-06-10 | 2025-07-31 | Anajana Construction | RCC Complete, Backfilling Done
49 | 76/0 | DC+0 |  | Sandy | 2025-07-24 | 2025-07-31 | Baba Ramdev Construction | RCC Complete, Backfilling Done
50 | 116/0 | DD+0 |  | Sandy | 2025-07-23 | 2025-07-31 | Goswami and Company-2 | RCC Complete, Backfilling Done

## Sheet7 (hidden)
SL | Loc | TOT | Gang | Starting Date | Completion
1 | 148/3 | DA+0 | Gokul Sarkar | 2025-08-29 | 2025-09-04 | Completed
2 | 81/2 | DA+3 | Dipak | 2025-09-01 | 2025-09-05 | Completed
3 | 145/1 | DA+3 | Ayansh Const | 2025-08-27 | 2025-09-09 | Completed
4 | 81/4 | DA+0 | Dipak | 2025-09-05 | 2025-09-09 | Completed
5 | 148/2 | DA+0 | Gokul Sarkar | 2025-09-05 | 2025-09-10 | Completed
6 | 83/1 | DA+3 | Ahmed Construction | 2025-08-29 | 2025-09-11 | Completed
7 | 97/0 | DC+0 | Ajay Kumar1 | 2025-09-01 | 2025-09-11 | Completed
8 | 148/5 | DA+0 | Gokul Sarkar | 2025-09-11 | 2025-09-14 | Completed
9 | 145/2 | DA+0 | Ayansh Const | 2025-09-09 | 2025-09-14 | Completed
10 | 82/1 | DA+6 | Dipak | 2025-09-09 | 2025-09-14 | Completed
11 | 96/1 | DA+0 | Ajay Kumar1 | 2025-09-01 | 2025-09-15 | Completed
12 | 79/2 | DA+0 | Ahmed Construction | 2025-09-11 | 2025-09-15 | Completed
13 | 133/2 | DA+0 | Windbridge Energy | 2025-08-28 | 2025-09-16 | Completed
14 | 148/6 | DA+0 | Gokul Sarkar | 2025-09-14 | 2025-09-19 | Completed
15 | 145/3 | DA+0 | Ayansh Const | 2025-09-14 | 2025-09-19 | Completed
16 | 143/5 | DA+3 | Prayag Saw1 | 2025-09-11 | 2025-09-17 | Completed
17 | 143/4 | DA+3 | Prayag Saw2 | 2025-09-11 | 2025-09-17 | Completed
18 | 143/2 | DA+0 | Prayag Saw1 | 2025-09-18 | 2025-09-20 | Completed
19 | 143/6 | DA+0 | Prayag Saw2 | 2025-09-18 | 2025-09-20 | Completed
20 | 97/1 | DA+3 | Ajay Kumar2 | 2025-09-11 | 2025-09-21 | Completed
21 | 113A/0 | DC+0 | Dipak | 2025-09-14 | 2025-09-21 | Completed
22 | 133/3 | DA+0 | Windbridge Energy | 2025-09-17 | 2025-09-22 | Completed
23 | 143/3 | DA+3 | Prayag Saw1 | 2025-09-21 | 2025-09-23 | Completed
24 | 143/7 | DA+6 | Prayag Saw2 | 2025-09-21 | 2025-09-23 | Completed
25 | 148/7 | DA+0 | Gokul Sarkar | 2025-09-20 | 2025-09-23 | Completed
26 | 98/1 | DA+0 | Ajay Kumar1 | 2025-09-15 | 2025-09-24 | Completed
27 | 114/1 | DA+9 | Dipak | 2025-09-24 | 2025-09-26 | Completed
28 | 143/1 | DA+6 | Prayag Saw2 | 2025-09-22 | 2025-09-27 | Completed
29 | 141/2 | DA+6 | Prayag Saw1 | 2025-09-24 | 2025-09-27 | Completed
30 | 149B/1 | DA+3 | Gokul Sarkar | 2025-09-24 | 2025-09-27 | Completed

## Erection (hidden)
NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE
Client : RAJASTHAN IV A POWER TRANSMISSION LTD.
CONTRACTOR : KEC INTERNATIONAL LIMITED
SL. No. | Location No. | Tower Type | Tower Weight | Gang Name | Starting Date | Completion Date | Remarks
1 | 77/2 | DA+3 | 11.145 | Dipak | 2025-06-23 | 2025-06-28 | Completed
2 | 77/4 | DA+3 | 11.997 | Dipak | 2025-06-28 | 2025-07-02 | Completed
3 | 75/7 | DA+0 | 11.145 | Srikarni | 2025-06-29 | 2025-07-05 | Completed
4 | 77/5 | DA+6 | 13.072 | Dipak | 2025-07-03 | 2025-07-05 | Completed
5 | 77/3 | DA+0 | 11.145 | Dipak | 2025-07-07 | 2025-07-10 | Completed
6 | 77/1 | DA+0 | 11.145 | Dipak | 2025-07-11 | 2025-07-14 | Completed |  |  |  |  | 185
7 | 75/6 | DA+0 | 11.145 | Dipak | 2025-07-15 | 2025-07-18 | Completed
8 | 75/5 | DA+0 | 11.145 | Dipak | 2025-07-19 | 2025-07-22 | Completed |  |  | 90 |  | 24
9 | 75/4 | DA+0 | 11.145 | Dipak | 2025-07-22 | 2025-07-25 | Completed
10 | 75/3 | DA+3 | 11.997 | Dipak | 2025-07-25 | 2025-07-28 | Completed
11 | 75/2 | DA+0 | 11.145 | Dipak | 2025-07-29 | 2025-07-31 | Completed
12 | 74/1 | DA+0 | 11.145 | Ahmed Construction | 2025-07-24 | 2025-07-31 | Completed
13 | 75/1 | DA+0 | 11.145 | Dipak | 2025-08-01 | 2025-08-04 | Completed |  | 41
14 | 73/3 | DA+9 | 13.958 | Ahmed Construction | 2025-08-01 | 2025-08-08 | Completed
15 | 75/0 | DC+0 | 18.727 | Dipak | 2025-08-04 | 2025-08-09 | Completed
16 | 73/2 | DA+9 | 13.958 | Ahmed Construction | 2025-08-08 | 2025-08-16 | Completed
17 | 78/0 | DC+0 | 18.727 | Dipak | 2025-08-10 | 2025-08-16 | Completed
18 | 85/1 | DA+0 | 11.145 | Ahmed Construction | 2025-08-17 | 2025-08-23 | Completed
19 | 79/0 | DD+0 | 21.41 | Dipak | 2025-08-17 | 2025-08-23 | Completed
20 | 86/1 | DA+6 | 13.072 | Ahmed Construction | 2025-08-23 | 2025-08-28 | Completed
21 | 80/1 | DA+9 | 13.958 | Dipak | 2025-08-23 | 2025-08-28 | Completed
22 | 148/4 | DA+0 | 11.145 | Gokul Sarkar | 2025-08-27 | 2025-08-29 | Completed
23 | 95A/1 | DA+0 | 11.145 | Ajay Kumar | 2025-08-23 | 2025-08-31 | Completed
24 | 81/3 | DA+0 | 11.145 | Dipak | 2025-08-29 | 2025-08-31 | Completed
25 | 148/3 | DA+0 | 11.145 | Gokul Sarkar | 2025-08-29 | 2025-09-04 | Completed
26 | 81/2 | DA+3 | 11.997 | Dipak | 2025-09-01 | 2025-09-05 | Completed
27 | 145/1 | DA+3 | 11.997 | Ayansh Const | 2025-08-27 | 2025-09-09 | Completed
28 | 81/4 | DA+0 | 11.145 | Dipak | 2025-09-05 | 2025-09-09 | Completed | 148/1 | HOLD
29 | 148/2 | DA+0 | 11.145 | Gokul Sarkar | 2025-09-05 | 2025-09-10 | Completed
30 | 83/1 | DA+3 | 11.997 | Ahmed Construction | 2025-08-29 | 2025-09-11 | Completed
31 | 97/0 | DC+0 | 18.727 | Ajay Kumar1 | 2025-09-01 | 2025-09-11 | Completed
32 | 148/5 | DA+0 | 11.145 | Gokul Sarkar | 2025-09-11 | 2025-09-14 | Completed
33 | 145/2 | DA+0 | 11.145 | Ayansh Const | 2025-09-09 | 2025-09-14 | Completed
34 | 82/1 | DA+6 | 13.072 | Dipak | 2025-09-09 | 2025-09-14 | Completed |  | 113/0,DC+0
35 | 96/1 | DA+0 | 11.145 | Ajay Kumar1 | 2025-09-01 | 2025-09-15 | Completed
36 | 79/2 | DA+0 | 11.145 | Ahmed Construction | 2025-09-11 | 2025-09-15 | Completed | 133/3
37 | 133/2 | DA+0 | 11.145 | Bhoi Enterprises | 2025-08-28 | 2025-09-16 | Completed
38 | 148/6 | DA+0 | 11.145 | Gokul Sarkar | 2025-09-14 | 2025-09-19 | Completed | 148/7
39 | 145/3 | DA+0 | 11.145 | Ayansh Const | 2025-09-14 | 2025-09-19 | Completed | 145/4
40 | 143/5 | DA+3 | 11.997 | Prayag Saw1 | 2025-09-11 | 2025-09-17 | Completed
41 | 143/4 | DA+3 | 11.997 | Prayag Saw2 | 2025-09-11 | 2025-09-17 | Completed | 143/2
42 | 143/2 | DA+0 | 11.145 | Prayag Saw1 | 2025-09-18 | 2025-09-20 | Completed | 143/3 | 143/1
43 | 143/6 | DA+0 | 11.145 | Prayag Saw2 | 2025-09-18 | 2025-09-20 | Completed | 143/7
44 | 97/1 | DA+3 | 11.997 | Ajay Kumar2 | 2025-09-11 | 2025-09-21 | Completed | 98A/1
45 | 113A/0 | DC+0 | 18.727 | Dipak | 2025-09-14 | 2025-09-21 | Completed
46 | 133/3 | DA+0 | 11.145 | Bhoi Enterprises | 2025-09-17 | 2025-09-22 | Completed |  |  |  | 79/1 | 64/3
47 | 143/3 | DA+3 | 11.997 | Prayag Saw1 | 2025-09-21 | 2025-09-23 | Completed | 98/0 | ROW | 98A/1
48 | 143/7 | DA+6 | 13.072 | Prayag Saw2 | 2025-09-21 | 2025-09-23 | Completed
49 | 148/7 | DA+0 | 11.145 | Gokul Sarkar | 2025-09-20 | 2025-09-23 | Completed
50 | 98/1 | DA+0 | 11.145 | Ajay Kumar1 | 2025-09-15 | 2025-09-24 | Completed | 115/0,116/1,114/0,112/1,111/0
51 | 114/1 | DA+9 | 13.958 | Dipak | 2025-09-24 | 2025-09-26 | Completed | 96/2 | 2025-09-15 | 76/0 | 98A/0
52 | 143/1 | DA+6 | 13.072 | Prayag Saw2 | 2025-09-22 | 2025-09-27 | Completed
53 | 141/2 | DA+6 | 13.072 | Prayag Saw1 | 2025-09-24 | 2025-09-27 | Completed
54 | 149B/1 | DA+3 | 11.997 | Gokul Sarkar | 2025-09-24 | 2025-09-27 | Completed
55 | 76/1 | DA+6 | 13.072 | Ahmed Construction | 2025-09-19 | 2025-09-27 | Completed
56 | 116/1 | DA+0 | 11.145 | Dipak | 2025-09-27 | 2025-09-29 | Completed | [5 empty] | 2025-09-29
57 | 133/6 | DA+3 | 11.997 | Bhoi Enterprises | 2025-09-23 | 2025-09-29 | Completed | [5 empty] | 2025-09-30 | 133/7
58 | 149B/2 | DA+0 | 11.145 | Gokul Sarkar | 2025-09-27 | 2025-09-30 | Completed | [5 empty] | 2025-09-29 | 147/7 | 147/8 | 149/0 | 149A/0
59 | 145/4 | DA+3 | 11.997 | Pritam Enterprises | 2025-09-20 | 2025-09-30 | Completed | [5 empty] | 2025-09-29 | 146/1
60 | 141/1 | DA+0 | 11.145 | Prayag Saw1 | 2025-09-27 | 2025-09-30 | Completed
61 | 143/0 | DC+3 | 18.9798 | Prayag Saw2 | 2025-09-27 | 2025-09-30 | Completed | [5 empty] | 2025-09-29 | 142/0
62 | 98A/1 | DA+0 | 11.145 | Ajay Kumar2 | 2025-09-23 | 2025-10-01 | Completed
63 | 146/1 | DA+3 | 11.997 | Pritam Enterprises | 2025-09-30 | 2025-10-03 | Completed
64 | 147/7 | DA+0 | 11.145 | Gokul Sarkar | 2025-09-30 | 2025-10-03 | Completed
65 | 133/7 | DA+0 | 11.145 | Bhoi Enterprises | 2025-09-29 | 2025-10-05 | Completed
66 | 146/2 | DA+0 | 11.145 | Pritam Enterprises | 2025-10-03 | 2025-10-05 | Completed
67 | 116/0 | DD+0 | 21.41 | Dipak | 2025-09-30 | 2025-10-07 | Completed | [14 empty] | GST@18 | #REF!
68 | 142/0 | DC+3 | 18.9798 | Prayag Saw1 | 2025-10-01 | 2025-10-07 | Completed | [5 empty] | ROW SINCE 3-10-25 to 5-10-25 |  |  |  |  | 85/1 | DA+0 | DA+0 | 3 | 11.15 | 33.45 | 439
69 | 144/0 | DD+6 | 26.291 | Prayag Saw2 | 2025-10-01 | 2025-10-08 | Completed | [15 empty] | 9000
70 | 146/0 | DC+0 | 18.727 | Pritam Enterprises | 2025-10-05 | 2025-10-10 | Completed | [10 empty] | 73/2 | DA+9
71 | 140/2 | DA+3 | 11.997 | Prayag Saw1 | 2025-10-08 | 2025-10-10 | Completed
72 | 149/0 | DD+0 | 21.41 | Gokul Sarkar | 2025-10-03 | 2025-10-10 | Completed | [14 empty] | TOTAL | #REF!
73 | 133/8 | DA+6 | 13.072 | Bhoi Enterprises | 2025-10-05 | 2025-10-11 | Completed | [14 empty] | RETENTION | #REF!
74 | 140/3 | DA+3 | 11.997 | Prayag Saw1 | 2025-10-10 | 2025-10-11 | Completed | [14 empty] | TDS 1% | #REF!
75 | 147/0 | DC+0 | 18.727 | Pritam Enterprises | 2025-10-10 | 2025-10-12 | Completed | [14 empty] | PF 10 | #REF!
76 | 115/0 | DC+0 | 18.727 | Dipak | 2025-10-08 | 2025-10-13 | Completed | [14 empty] | GST 20 | #REF!
77 | 138/1 | DA+0 | 11.145 | Prayag Saw2 | 2025-10-08 | 2025-10-13 | Completed | [14 empty] | ADVANCE | 600000
78 | 98A/0 | DC+0 | 18.727 | Ajay Kumar | 2025-09-26 | 2025-10-15 | Completed | [14 empty] | TIGHT & PUNCH 10 | #REF!
79 | 149A/0 | DD+0 | 21.41 | Gokul Sarkar | 2025-10-10 | 2025-10-15 | Completed | [14 empty] | NET PAYABLE | #REF!
80 | 133/4 | DA+0 | 11.145 | Bhoi Enterprises | 2025-10-11 | 2025-10-15 | Completed
81 | 141/0 | DC+0 | 18.727 | Prayag Saw1 | 2025-10-11 | 2025-10-16 | Completed
82 | 147/3 | DA+0 | 11.145 | Pritam Enterprises | 2025-10-12 | 2025-10-15 | Completed
83 | 138/2 | DA+0 | 11.145 | Prayag Saw2 | 2025-10-13 | 2025-10-16 | Completed
84 | 110/0 | DC+0 | 18.727 | Dipak | 2025-10-13 | 2025-10-18 | Completed
85 | 133/1 | DA+0 | 11.145 | Bhoi Enterprises | 2025-10-15 | 2025-10-19 | Completed
86 | 138/3 | DA+0 | 11.145 | Prayag Saw2 | 2025-10-16 | 2025-10-19 | Completed
87 | 147/9 | DA+0 | 11.145 | Gokul Sarkar | 2025-10-16 | 2025-10-19 | Completed
88 | 147/2 | DA+0 | 11.145 | Pritam Enterprises | 2025-10-15 | 2025-10-19 | Completed
89 | 147/1 | DA+0 | 11.145 | Pritam Enterprises | 2025-10-19 | 2025-10-22 | Completed
90 | 147/8 | DA+0 | 11.145 | Gokul Sarkar | 2025-10-19 | 2025-10-22 | Completed
91 | 134A/0 | DD+0 | 21.41 | Prayag Saw1 | 2025-10-16 | 2025-10-23 | Completed
92 | 135/1 | DA+0 | 11.145 | Bhoi Enterprises | 2025-10-19 | 2025-10-24 | Completed
93 | 82/2 | DA+0 | 11.145 | Namechand Mahto | 2025-10-19 | 2025-10-24 | Completed
94 | 138/0 | DB+3 | 18.1115 | Prayag Saw2 | 2025-10-19 | 2025-10-24 | Completed
95 | 134A/2 | DA+3 | 11.997 | Prayag Saw1 | 2025-10-24 | 2025-10-26 | Completed
96 | 112/0 | DC+9 | 24.1826 | Dipak | 2025-10-19 | 2025-10-27 | Completed
97 | 147/6 | DA+0 |  | Pritam Enterprises | 2025-10-23 | 2025-10-26 | Completed
98 | 148/1 | DA+0 |  | Gokul Sarkar | 2025-10-23 | 2025-10-27 | Completed
99 | 147/5 | DA+0 |  | Pritam Enterprises | 2025-10-27 | 2025-10-28 | Completed
100 | 134/0 | DD+0 |  | Prayag Saw2 | 2025-10-27 | 2025-10-29 | Completed
101 | 76/0 | DC+0 | 18.727 | Namechand Mahto | 2025-10-24 | 2025-10-31 | Completed
102 | 133/0 | DC+0 | 18.727 | Bhoi Enterprises | 2025-10-24 | 2025-10-31 | Completed
103 | 147/4 | DA+0 |  | Pritam Enterprises | 2025-10-28 | 2025-10-31 | Completed
104 | 139/0 | DC+3 |  | Prayag Saw1 | 2025-10-26 | 2025-10-28 | Completed
105 | 153A/0 | DB+0 |  | Gokul Sarkar | 2025-10-27 | 2025-11-01 | Completed
106 | 115/1 | DB+9 |  | Dipak | 2025-10-27 | 2025-11-02 | Completed
107 | 135/0 | DC+0 |  | Prayag Saw1 | 2025-10-29 | 2025-11-02 | Completed
108 | 134A/1 | DA+9 |  | Prayag Saw2 | 2025-10-29 | 2025-11-03 | Completed
109 | 132/3 | DA+0 |  | Bhoi Enterprises | 2025-11-01 | 2025-11-04 | Completed
110 | 77/0 | DB+0 |  | Namechand Mahto | 2025-11-01 | 2025-11-05 | Completed
111 | 129/1 | DA+3 |  | Pritam Enterprises | 2025-11-01 | 2025-11-05 | Completed
112 | 134A/4 | DA+9 |  | Prayag Saw2 | 2025-11-04 | 2025-11-06 | Completed
113 | 132/1 | DA+0 |  | Bhoi Enterprises | 2025-11-05 | 2025-11-07 | Completed | Strong ROW. Landowner stopped work not allowing to enter at location and Tower material left without watchmen.
114 | 136/0 | DD+0 |  | Prayag Saw1 | 2025-11-03 | 2025-11-08 | Completed
115 | 131/1 | DA+3 |  | Pritam Enterprises | 2025-11-06 | 2025-11-09 | Completed
116 | 98/0 | DC+0 | 18.727 | Namechand Mahto | 2025-11-06 | 2025-11-10 | Completed
117 | 111/0 | DB+9 |  | Dipak | 2025-11-03 | 2025-11-10 | Completed
118 | 132/4 | DA+0 |  | Bhoi Enterprises | 2025-11-08 | 2025-11-11 | Completed
119 | 137/0 | DB+3 |  | Prayag Saw2 | 2025-11-06 | 2025-11-12 | Completed
120 | 152/0 | DD+18 |  | Gokul Sarkar | 2025-11-01 | 2025-11-14 | Completed | [5 empty] | 149B/3
121 | 129/0 | DC+0 |  | Pritam Enterprises | 2025-11-09 | 2025-11-14 | Completed | [5 empty] | 133/5
122 | 131/2 | DA+3 | 11.997 | Bhoi Enterprises | 11.11.2025 | 2025-11-15 | Completed
123 | 80/0 | DB+3 | 18.1115 | Namechand Mahto | 10.11.2025 | 2025-11-15 | Completed
124 | 145/0 | DD+6 |  | Prayag Saw2 | 12.11.2025 | 2025-11-17 | Completed | [5 empty] | 2025-11-17
125 | 82/0 | DB+3 |  | Namechand Mahto | 2025-11-15 | 2025-11-20 | Completed
126 | 109A/0 | DB+6 |  | Dipak | 2025-11-13 | 2025-11-20 | Completed
127 | 133/5 | DA+0 |  | Bhoi Enterprises | 2025-11-15 | 2025-11-20 | Completed | [5 empty] | 2025-11-19
128 | 148/0 | DB+0 |  | Prayag Saw2 | 2025-11-16 | 2025-11-21 | Completed
129 | 149B/3 | DB+9 |  | Gokul Sarkar | 2025-11-14 | 2025-11-22 | Completed | [5 empty] | 2025-11-19 | 2025-11-22
130 | 78/1 | DA+3 |  | Namechand Mahto | 2025-11-21 | 2025-11-25 | Completed | [5 empty] | 2025-11-24 | 79/1
131 | 134A/3 | DA+6 |  | Prayag Saw2 | 2025-11-21 | 2025-11-25 | Completed | [5 empty] | 2025-11-24 | 135/2 | Approach Road
132 | 135/2 | DA+0 |  | Prayag Saw2 | 2025-11-25 | 2025-11-27 | Completed
133 | 149B/0 | DB+3 |  | Gokul Sarkar | 2025-11-23 | 2025-11-28 | Completed | [5 empty] | 2025-11-27
134 | 128/0 | DC+3 |  | Bhoi Enterprises | 2025-11-21 | 2025-11-28 | Completed | [5 empty] | 2025-11-26 | 130/0 | 129/2
135 | 98B/0 | DD+0 |  | Dipak | 2025-11-22 | 2025-11-29 | Completed | [5 empty] | 2025-11-25 | 99/0
136 | 79/1 | DA+9 |  | Namechand Mahto | 2025-11-25 | 2025-11-30 | Completed
137 | 135/3 | DA+3 |  | Prayag Saw2 | 2025-11-28 | 2025-11-30 | Completed
138 | 140/1 | DA+3 |  | Prayag Saw2 | 2025-12-01 | 2025-12-03 | Completed
139 | 130/0 | DC+6 |  | Bhoi Enterprises | 2025-11-28 | 2025-12-05 | Completed
140 | 81/1 | DA+0 |  | Namechand Mahto | 2025-12-01 | 2025-12-05 | Completed
141 | 150/0 | DD+9 |  | Gokul Sarkar | 2025-11-28 | 2025-12-07 | Completed
142 | 95/0 | DB+9 |  | Dipak | 2025-11-29 | 2025-12-07 | Completed
143 | 139/1 | DA+9 |  | Prayag Saw2 | 2025-12-06 | 2025-12-10 | Completed
144 | 81/0 | DB+9 |  | Namechand Mahto | 2025-12-06 | 2025-12-11 | Completed
145 | 126/2 | DA+3 |  | Bhoi Enterprises | 2025-12-06 | 2025-12-12 | Completed
146 | 140/0 | DB+0 |  | Prayag Saw2 | 2025-12-09 | 2025-12-13 | Completed
147 | 151/0 | DD+9 |  | Gokul Sarkar | 2025-12-07 | 2025-12-14 | Completed
148 | 126/1 | DA+6 |  | Bhoi Enterprises | 2025-12-12 | 2025-12-16 | Completed
149 | 85/0 | DC+0 |  | Namechand Mahto | 2025-12-12 | 2025-12-16 | Completed
150 | 72/2 | DA+3 |  | Balaji Tour & Travels 2 | 2025-12-06 | 2025-12-16 | Completed
151 | 119/2 | DA+3 |  | Prayag Saw | 2025-12-13 | 2025-12-18 | Completed
152 | 104B/2 | DA+0 |  | Namechand Mahto2 | 2025-10-18 |  | WIP
153 | 95/1 | DB+0 |  | Balaji Tour & Travels | 2025-12-07 |  | WIP
154 | 90/1 | DA+9 |  | Namechand Mahto 2 | 2025-12-12 |  | WIP
155 | 154/0 | DD+0 |  | Gokul Sarkar | 2025-12-14 |  | WIP
156 | 84/0 | DC+6 |  | Namechand Mahto | 2025-12-17 |  | Material Shifting
157 | 119/1 | DA+3 |  | Prayag Saw | 2025-12-18 |  | Material Shifting
185
5

## Completion date (hidden)
Location no | Tower type | FDN TYPE | FDN CMP date | Erection CMP Date | Earthing CMP Date
GANTRY | GE | #N/A | #N/A | #N/A | #N/A
1/0 | DE+0 | #N/A | #N/A | #N/A | #N/A
1A/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
2/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
2/1 | Gantry UCS | #N/A | #N/A | #N/A | #N/A
3/0 | Gantry UCS | #N/A | #N/A | #N/A | #N/A
3/1 | DD+3 | DFR | 2026-04-07 | #N/A | #N/A
4/0 | DD+18 | DFR | 2026-02-28 | #N/A | #N/A
5/0 | DD+9 | #N/A | #N/A | #N/A | #N/A
5/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
5/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
5/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
5/4 | DA+0 | #N/A | #N/A | #N/A | #N/A
5/5 | DA+0 | #N/A | #N/A | #N/A | #N/A
5/6 | DA+6 | #N/A | #N/A | #N/A | #N/A
5A/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
5A/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
5B/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
5B/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
5C/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
5D/0 | DC+3 | #N/A | #N/A | #N/A | #N/A
5E/0 | DC+3 | #N/A | #N/A | #N/A | #N/A
6/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
6A/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
68/0 | DB+9 | #N/A | #N/A | #N/A | #N/A
6C/0 | DC+3 | #N/A | #N/A | #N/A | #N/A
6C/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
6D/0 | DD+6 | #N/A | #N/A | #N/A | #N/A
6D/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
6D/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
6D/3 | DA+3 | #N/A | #N/A | #N/A | #N/A
6D/4 | DA+3 | #N/A | #N/A | #N/A | #N/A
7/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
7/1 | DA+0 | Sandy | 2026-03-26 | #N/A | #N/A
7/2 | DA+0 | Sandy | 0 | #N/A | #N/A
7/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
7/4 | DA+0 | #N/A | #N/A | #N/A | #N/A
7/5 | DA+0 | #N/A | #N/A | #N/A | #N/A
7/6 | DA+0 | #N/A | #N/A | #N/A | #N/A
7/7 | DA+0 | Sandy | 2026-02-04 | 0 | 2026-02-05
7/8 | DA+3 | #N/A | #N/A | #N/A | #N/A
7/9 | DA+0 | Sandy | 2026-02-06 | 2026-04-20 | #N/A
7/10 | DA+3 | #N/A | #N/A | #N/A | #N/A
8/0 | DB+0 | Sandy | 2026-04-11 | #N/A | #N/A
8/1 | DA+0 | Sandy | 2026-04-06 | 0 | #N/A
8/2 | DA+0 | Sandy | 2026-03-25 | #N/A | #N/A
8/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
8/4 | DA+3 | #N/A | #N/A | #N/A | #N/A
9/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
9/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
9/2 | DA+6 | #N/A | #N/A | #N/A | #N/A
9/3 | DA+0 | Sandy | 2026-04-14 | #N/A | #N/A
9/4 | DA+3 | Sandy | 2026-04-15 | #N/A | #N/A
9/5 | DB+9 | Sandy | 2026-04-21 | #N/A | #N/A
10/0 | DC+3 | Sandy | 0 | #N/A | #N/A
10/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
10/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
10/3 | DA+3 | Sandy | 2026-01-23 | #N/A | 2026-01-25
10/4 | DA+6 | #N/A | #N/A | #N/A | #N/A
10/5 | DA+0 | Sandy | 2026-01-26 | 2026-04-17 | 2026-01-30
10/6 | DA+0 | Sandy | 2026-01-28 | 2026-04-20 | 2026-01-30
10/7 | DA+0 | Sandy | 2026-01-30 | 2026-04-23 | 2026-01-31
10/8 | DA+0 | Sandy | 2026-03-22 | 2026-04-24 | 2026-03-23
10/9 | DB+0 | #N/A | #N/A | #N/A | #N/A
10/10 | DA+0 | #N/A | #N/A | #N/A | #N/A
10/11 | DA+3 | #N/A | #N/A | #N/A | #N/A
10/12 | DA+3 | Sandy | 2026-02-12 | #N/A | #N/A
10/13 | DA+3 | #N/A | #N/A | #N/A | #N/A
10/14 | DA+0 | Sandy | 0 | #N/A | #N/A
10/15 | DA+6 | #N/A | #N/A | #N/A | #N/A
11/0 | DB+0 | Sandy | 0 | #N/A | #N/A
11/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
11/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
11/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
11/4 | DA+0 | #N/A | #N/A | #N/A | #N/A
11/5 | DA+0 | #N/A | #N/A | #N/A | #N/A
11/6 | DA+0 | #N/A | #N/A | #N/A | #N/A
12/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
12/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
12/2 | DA+3 | #N/A | #N/A | #N/A | #N/A
13/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
13/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
13/2 | DA+6 | #N/A | #N/A | #N/A | #N/A
13/3 | DA+3 | #N/A | #N/A | #N/A | #N/A
14/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
14/1 | DB+9 | #N/A | #N/A | #N/A | #N/A
15/0 | DC+9 | #N/A | #N/A | #N/A | #N/A
15/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
16/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
16/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
17/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
17/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
18/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
18/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
19/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
19/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
19/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
19/3 | DA+3 | #N/A | #N/A | #N/A | #N/A
20/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
20/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
20/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
20/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
20/4 | DA+0 | #N/A | #N/A | #N/A | #N/A
20/5 | DA+3 | #N/A | #N/A | #N/A | #N/A
20/6 | DA+9 | #N/A | #N/A | #N/A | #N/A
21/0 | DD+3 | #N/A | #N/A | #N/A | #N/A
21/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
21/2 | DA+6 | #N/A | #N/A | #N/A | #N/A
22/0 | DB+3 | #N/A | #N/A | #N/A | #N/A
23/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
23/1 | DB+3 | #N/A | #N/A | #N/A | #N/A
23/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
23/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
24/0 | DC+9 | #N/A | #N/A | #N/A | #N/A
24/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
25/0 | DD+6 | #N/A | #N/A | #N/A | #N/A
25/1 | Gantry UCS | #N/A | #N/A | #N/A | #N/A
25/2 | Gantry UCS | #N/A | #N/A | #N/A | #N/A
26/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
27/0 | DC+9 | #N/A | #N/A | #N/A | #N/A
27A/0 | DD+9 | #N/A | #N/A | #N/A | #N/A
27A/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
27A/2 | DA+6 | #N/A | #N/A | #N/A | #N/A
27B/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
27B/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
27B/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
27B/3 | DA+9 | #N/A | #N/A | #N/A | #N/A
28/0 | DB+3 | #N/A | #N/A | #N/A | #N/A
28/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
29/0 | DB+9 | #N/A | #N/A | #N/A | #N/A
29/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
29/2 | DA+9 | #N/A | #N/A | #N/A | #N/A
29/3 | DB+9 | #N/A | #N/A | #N/A | #N/A
30/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
30/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
30/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
30/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
31/0 | DC+9 | #N/A | #N/A | #N/A | #N/A
32/0 | DC+9 | #N/A | #N/A | #N/A | #N/A
32/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
32/2 | DA+3 | #N/A | #N/A | #N/A | #N/A
32/3 | DA+9 | #N/A | #N/A | #N/A | #N/A
33/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
34/0 | DC+6 | #N/A | #N/A | #N/A | #N/A
34/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
35/0 | DC+9 | #N/A | #N/A | #N/A | #N/A
35/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
36/0 | DC+6 | #N/A | #N/A | #N/A | #N/A
36/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
36/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
36A | DD+0 | #N/A | #N/A | #N/A | #N/A
37/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
38/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
38/1 | DB+6 | #N/A | #N/A | #N/A | #N/A
38/2 | DA+3 | #N/A | #N/A | #N/A | #N/A
38/3 | DA+9 | #N/A | #N/A | #N/A | #N/A
38/4 | DA+0 | #N/A | #N/A | #N/A | #N/A
38/5 | DA+9 | #N/A | #N/A | #N/A | #N/A
39/0 | DB+3 | #N/A | #N/A | #N/A | #N/A
39/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
39/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
39/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
39/4 | DA+6 | #N/A | #N/A | #N/A | #N/A
40/0 | DD+3 | #N/A | #N/A | #N/A | #N/A
40/1 | DB+6 | #N/A | #N/A | #N/A | #N/A
40/2 | DA+6 | #N/A | #N/A | #N/A | #N/A
41/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
41/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
41/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
41/3 | DA+9 | #N/A | #N/A | #N/A | #N/A
42/0 | DC+3 | #N/A | #N/A | #N/A | #N/A
42/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
42/2 | DCT+6 | #N/A | #N/A | #N/A | #N/A
42/3 | DA+9 | #N/A | #N/A | #N/A | #N/A
42/4 | DA+9 | #N/A | #N/A | #N/A | #N/A
42/5 | DA+0 | #N/A | #N/A | #N/A | #N/A
42/6 | DA+3 | #N/A | #N/A | #N/A | #N/A
42/7 | DA+0 | #N/A | #N/A | #N/A | #N/A
43/0 | DC+6 | #N/A | #N/A | #N/A | #N/A
44/0 | DB+9 | #N/A | #N/A | #N/A | #N/A
44/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
45/0 | DD+9 | #N/A | #N/A | #N/A | #N/A
45/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
45/2 | DA+6 | #N/A | #N/A | #N/A | #N/A
45/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
45/4 | DA+6 | #N/A | #N/A | #N/A | #N/A
46/0 | DD+3 | #N/A | #N/A | #N/A | #N/A
47/0 | DD+9 | #N/A | #N/A | #N/A | #N/A
47/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
47/2 | DA+9 | #N/A | #N/A | #N/A | #N/A
48/0 | DD+3 | Sandy | 2025-09-25 | #N/A | 2025-09-17
49/0 | DD+3 | #N/A | #N/A | #N/A | #N/A
50/0 | DD+9 | #N/A | #N/A | #N/A | #N/A
51/0 | DD+18 | #N/A | #N/A | #N/A | #N/A
51/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
51/2 | DA+0 | Sandy | 2025-04-17 | #N/A | 2025-04-18
51/3 | DA+3 | Sandy | 2025-04-23 | #N/A | 2025-04-24
52/0 | DB+3 | #N/A | #N/A | #N/A | #N/A
52/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
53/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
54/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
54/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
54/2 | DA+6 | #N/A | #N/A | #N/A | #N/A
54/3 | DA+3 | #N/A | #N/A | #N/A | #N/A
55/0 | DD+18 | #N/A | #N/A | #N/A | #N/A
56/0 | DB+9 | #N/A | #N/A | #N/A | #N/A
56/1 | DB+9 | Sandy | 2025-09-20 | #N/A | 2025-09-19
56/2 | DA+0 | Sandy | 2025-08-27 | #N/A | 2025-09-16
56/3 | DB+9 | #N/A | #N/A | #N/A | #N/A
56/4 | DA+6 | Sandy | 2025-08-26 | #N/A | 2025-09-16
56/5 | DA+6 | Sandy | 2025-08-31 | #N/A | 2025-09-16
57/0 | DB+9 | Sandy | 2025-09-10 | #N/A | 2025-09-13
58/0 | DB+9 | Sandy | 2025-09-17 | #N/A | 2025-09-19
59/0 | DC+9 | Sandy | 2025-09-12 | #N/A | 2025-09-19
59/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
60/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
60/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
60/2 | DA+3 | #N/A | #N/A | #N/A | #N/A
60/3 | DA+9 | #N/A | #N/A | #N/A | #N/A
61/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
61/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
62/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
62/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
62/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
62/3 | DA+9 | #N/A | #N/A | #N/A | #N/A
62/4 | DA+6 | Sandy | 2025-04-29 | #N/A | 2025-05-06
62/5 | DA+6 | Sandy | 2025-05-31 | #N/A | 2025-05-30
63/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
63/1 | DA+0 | Sandy | 2025-08-24 | #N/A | 2025-09-11
64/0 | DC+9 | #N/A | #N/A | #N/A | 2025-09-15
64/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
64/2 | DA+9 | #N/A | #N/A | #N/A | #N/A
64/3 | DA+9 | Sandy | 2025-03-07 | #N/A | 2025-03-28
64/4 | DA+9 | Sandy | 2025-03-10 | #N/A | 2025-04-08
64/5 | DA+9 | Sandy | 2025-03-31 | #N/A | 2025-04-05
64/6 | DA+3 | Sandy | 2025-03-30 | #N/A | 2025-04-08
64/7 | DA+3 | Sandy | 2025-03-26 | 2026-03-21 | 2025-04-08
65/0 | DD+0 | Sandy | 2026-01-07 | 2026-03-16 | 2026-01-17
65/1 | DB+9 | Sandy | 2026-01-15 | 2026-03-09 | 2026-01-16
66/0 | DD+0 | Sandy | 2025-11-30 | 2026-03-03 | 2025-12-02
66/1 | DA+9 | Sandy | 2025-02-28 | 2026-03-29 | #N/A
66/2 | DA+0 | Sandy | 2025-03-06 | #N/A | #N/A
66/3 | DA+3 | Sandy | 2025-03-11 | #N/A | #N/A
66/4 | DA+9 | #N/A | #N/A | #N/A | #N/A
67/0 | DC+6 | #N/A | #N/A | #N/A | #N/A
67/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
67/2 | DB+0 | #N/A | #N/A | #N/A | #N/A
68/0 | DB+9 | #N/A | #N/A | #N/A | #N/A
69/0 | DD+3 | #N/A | #N/A | #N/A | #N/A
69/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
69/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
69/3 | DA+0 | Sandy | 2026-01-15 | #N/A | 2026-01-16
70/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
71/0 | DB+0 | Sandy | 2025-11-14 | #N/A | 2025-11-15
71/1 | DA+9 | Sandy | 2025-04-09 | #N/A | 2025-04-10
71/2 | DA+0 | Sandy | 2025-10-30 | 2026-01-18 | 2025-10-31
71/3 | DA+0 | Sandy | 2025-11-07 | 2026-01-13 | 2025-11-08
72/0 | DD+0 | Sandy | 2025-11-17 | #N/A | 2025-11-18
72/1 | DA+3 | Sandy | 2025-09-19 | #N/A | 2025-09-22
72/2 | DA+3 | Sandy | 2025-06-30 | 2025-12-16 | 2025-07-01
73/0 | DB+0 | Sandy | 2025-06-26 | 2025-12-24 | 2025-06-28
73/1 | DA+0 | Sandy | 2025-10-16 | #N/A | 2025-11-05
74/0 | DB+9 | Sandy | 2025-06-20 | #N/A | 2025-06-20
81/0 | DB+9 | Sandy | 2025-09-12 | 2025-12-11 | 2025-09-15
81/1 | DA+0 | Sandy | 2025-11-10 | 2025-12-05 | 2025-11-11
81/5 | DA+6 | Sandy | 2025-05-21 | 2025-12-26 | 2025-05-21
83/0 | DC+0 | Sandy | 2025-08-09 | 2026-01-07 | 2025-08-05
84/0 | DC+6 | Sandy | 2025-10-19 | 2025-12-21 | 2025-11-05
85/0 | DC+0 | DFR | 2025-08-31 | 2025-12-16 | 2025-11-05
86/0 | DD+0 | Sandy | 2025-06-27 | 2025-12-31 | 2025-06-29
86/2 | DA+0 | Sandy | 2025-02-22 | #N/A | #N/A
87/0 | DC+0 | Sandy | 2025-08-22 | #N/A | 2025-08-02
87/1 | DA+3 | Sandy | 2025-03-24 | #N/A | 2025-04-17
87/2 | DA+9 | Sandy | 2025-03-30 | #N/A | 2025-04-17
88/0 | DC+6 | Sandy | 2025-12-05 | #N/A | 2025-12-03
89/0 | DC+0 | Sandy | 2025-11-12 | #N/A | 2025-11-28
89/1 | DA+9 | Sandy | 2025-11-18 | #N/A | 2025-11-28
90/0 | DC+0 | Sandy | 2025-11-22 | 2026-02-24 | 2025-12-04
90/1 | DA+9 | Sandy | 2025-11-26 | 2025-12-26 | 2025-11-28
91/0 | DD+0 | Sandy | 2025-12-24 | #N/A | 2025-12-26
91/1 | DA+0 | Sandy | 2025-04-13 | 2026-02-27 | #N/A
91/2 | DA+0 | Sandy | 2025-04-16 | #N/A | 2025-04-17
91/3 | DA+0 | Sandy | 2025-12-31 | #N/A | 2026-01-02
92/0 | DC+0 | Sandy | 2026-01-28 | #N/A | 2026-01-29
93/0 | DC+0 | Sandy | 2026-01-30 | #N/A | 2026-01-31
94/0 | DB+6 | Sandy | 2025-07-24 | #N/A | 2025-07-25
95/0 | DB+9 | Sandy | 2025-07-11 | 2025-12-07 | 2025-07-16
95/1 | DB+0 | DFR | 2025-07-04 | 2025-12-30 | 2025-07-06
95/2 | DA+9 | Sandy | 2025-04-20 | #N/A | 2025-04-21
95A/0 | DB+0 | DFR | 2025-06-23 | 2026-01-10 | 2025-06-24
96/0 | DC+0 | DFR | 2025-06-06 | #N/A | 2025-06-07
96/2 | DA+0 | Sandy | 2025-03-07 | #N/A | 2025-03-08
98B/1 | DA+0 | Sandy | 2026-03-11 | #N/A | 2026-03-11
98B/2 | DCT+0 | Sandy | 2025-12-08 | #N/A | 2025-12-08
99/0 | DC+0 | Sandy | 2025-08-14 | #N/A | 2025-08-12
99/1 | DA+6 | Sandy | 2025-03-10 | #N/A | 2025-11-05
99/2 | DA+0 | DFR | 2025-04-25 | #N/A | 2025-04-25
99/3 | DA+3 | Sandy | 2025-07-29 | #N/A | 2025-07-29
99/4 | DA+3 | #N/A | #N/A | #N/A | 2025-08-24
99A/0 | DB+6 | Sandy | 2025-08-31 | #N/A | 2025-09-03
99B/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
99C/0 | DD+0 | Sandy | 2026-04-15 | #N/A | 2025-04-16
99C/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
99C/2 | DA+3 | #N/A | #N/A | #N/A | 2025-05-26
100/0 | DC+0 | Sandy | 2026-04-24 | #N/A | #N/A
100/1 | DA+6 | Sandy | 2025-05-18 | #N/A | 2025-05-19
101/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
102/0 | DD+3 | #N/A | #N/A | #N/A | #N/A
102/1 | DA+0 | Sandy | 2025-08-14 | #N/A | 2025-08-16
102/2 | DA+0 | Sandy | 2025-08-07 | 2026-01-20 | 2025-08-08
103/0 | DC+0 | Sandy | 2026-03-19 | #N/A | 2026-03-20
103/1 | DA+6 | Sandy | 2026-04-10 | #N/A | 2026-04-11
104/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
104A/0 | DC+9 | Sandy | 2025-12-30 | #N/A | 2026-01-05
104B/0 | DB+9 | Sandy | 2026-01-04 | #N/A | 2026-01-04
104B/1 | DA+0 | Sandy | 2025-04-29 | #N/A | #N/A
105/0 | DD+0 | Sandy | 2025-05-28 | #N/A | 2025-05-28
105/1 | DA+3 | Sandy | 2025-05-15 | #N/A | 2025-05-15
106/0 | DC+6 | Sandy | 2025-07-06 | #N/A | 2025-07-07
107/0 | DD+3 | #N/A | #N/A | #N/A | #N/A
107/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
108/0 | DC+0 | Sandy | 2026-01-20 | #N/A | 2026-01-20
109/0 | DC+3 | Sandy | 2026-01-23 | #N/A | 2026-01-24
113/0 | DD+0 | Sandy | 2025-11-16 | 2026-01-17 | 2025-11-16
114/0 | DC+0 | Sandy | 2025-06-30 | 2026-01-24 | 2025-07-07
117/0 | DD+0 | Sandy | 2025-12-13 | #N/A | 2025-12-13
117/1 | DA+3 | Sandy | 2025-12-19 | #N/A | 2025-12-20
117/2 | DB+9 | Sandy | 2026-02-28 | #N/A | 2026-02-28
118/0 | DC+3 | Sandy | 2025-12-05 | 2026-01-30 | 2025-12-14
119/0 | DD+3 | Sandy | 2025-06-15 | #N/A | 2025-06-15
119/1 | DA+3 | Sandy | 2025-04-18 | 2025-12-21 | 2025-04-20
119/2 | DA+3 | Sandy | 2025-04-22 | 2025-12-18 | 2025-04-21
120/0 | DC+0 | Sandy | 2026-01-25 | #N/A | 2026-01-28
120/1 | DA+6 | Sandy | 2025-06-05 | 2025-12-25 | 2025-06-06
121/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
122/0 | DC+6 | #N/A | #N/A | #N/A | #N/A
122/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
122/2 | DA+3 | Sandy | 2026-01-08 | #N/A | 2026-01-09
123/0 | DC+0 | Sandy | 2025-09-30 | 2025-12-30 | 2025-09-30
124/0 | DC+3 | Sandy | 2025-12-30 | #N/A | 2025-12-30
125/0 | DC+3 | Sandy | 2025-07-24 | #N/A | 2025-08-26
125/1 | DA+0 | Sandy | 2025-07-14 | #N/A | 2025-08-26
125/2 | DA+0 | Sandy | 2025-09-18 | #N/A | 2025-09-16
125/3 | DA+0 | Sandy | 2025-09-10 | #N/A | 2025-09-10
126/0 | DC+6 | Sandy | 2025-08-19 | 2026-01-11 | 2025-08-26
126/1 | DA+6 | Sandy | 2025-08-02 | 2025-12-16 | 2025-08-26
126/2 | DA+3 | Sandy | 2025-07-26 | 2025-12-12 | 2025-08-26
126/3 | DA+6 | Sandy | 2026-01-15 | #N/A | 2026-01-15
127/0 | DD+6 | #N/A | #N/A | #N/A | #N/A
127/1 | DA+9 | Sandy | 2025-11-28 | 2026-01-16 | 2025-12-17
128/1 | DA+6 | Sandy | 2025-12-14 | 2026-02-08 | 2025-12-17
129/2 | DA+9 | Sandy | 2025-08-23 | 2026-01-15 | 2025-08-24
130/1 | DA+0 | Sandy | 2025-12-06 | 2026-02-11 | 2025-12-15
131/0 | DD+0 | Sandy | 2025-09-04 | 2026-02-05 | 2025-09-05
132/0 | DD+0 | Sandy | 2025-12-28 | 2026-02-18 | 2025-12-29
132/2 | DA+0 | Sandy | 2025-12-20 | 2026-02-13 | 2025-12-21
139/1 | DA+9 | Sandy | 2025-11-16 | 2025-12-10 | 2025-12-18
140/0 | DB+0 | Sandy | 2025-11-22 | 2025-12-13 | 2025-12-18
151/0 | DD+9 | DFR | 2025-11-08 | 2025-12-14 | 2025-11-08
153/0 | DD+18 | DFR | 2025-11-30 | 2026-01-04 | 2025-12-02
154/0 | DD+0 | DFR | 2025-11-22 | 2025-12-21 | 2025-11-23
154/1 | Gantry UCS | #N/A | #N/A | #N/A | #N/A
154/2 | Gantry UCS | #N/A | #N/A | #N/A | #N/A
155/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
156/0 | DD+0 | DFR | 2026-03-10 | #N/A | 2026-03-11
157/0 | DD+0(aux) | DFR | 2026-03-04 | #N/A | 2026-03-11
GE | GE(aux) | #N/A | #N/A | #N/A | #N/A
140/1 | DA+3 | Sandy | 2025-11-11 | 2025-12-03 | 2025-12-18
79/1 | DA+9 | Sandy | 2025-02-23 | 2025-11-30 | 2025-02-24
135/3 | DA+3 | Sandy | 2025-10-16 | 2025-11-30 | 2025-10-16
98B/0 | DD+0 | DFR | 2025-07-31 | 2025-11-29 | 2025-08-02
128/0 | DC+3 | Sandy | 2025-08-20 | 2025-11-28 | 2025-08-26
149B/0 | DB+3 | Sandy | 2025-08-12 | 2025-11-28 | 2025-08-28
135/2 | DA+0 | Sandy | 2025-10-11 | 2025-11-27 | 2025-10-16
78/1 | DA+3 | Sandy | 2025-11-08 | 2025-11-25 | 2025-11-11
134A/3 | DA+6 | Sandy | 2025-10-31 | 2025-11-25 | 2025-12-18
149B/3 | DB+9 | Sandy | 2025-10-13 | 2025-11-22 | 2025-10-13
148/0 | DB+0 | Sandy | 2025-11-04 | 2025-11-21 | 2025-11-04
82/0 | DB+3 | Sandy | 2025-08-31 | 2025-11-20 | 2025-09-01
109A/0 | DB+6 | Sandy | 2025-07-16 | 2025-11-20 | 2025-07-20
133/5 | DA+0 | Sandy | 2025-07-16 | 2025-11-20 | 2025-07-17
145/0 | DD+6 | Sandy | 2025-07-31 | 2025-11-17 | 2025-08-07
80/0 | DB+3 | Sandy | 2025-07-10 | 2025-11-15 | 2025-07-10
131/2 | DA+3 | Sandy | 2025-08-20 | 2025-11-15 | 2025-08-21
129/0 | DC+0 | Sandy | 2025-08-08 | 2025-11-14 | 2025-08-08
152/0 | DD+18 | DFR | 2025-09-30 | 2025-11-14 | 2025-12-02
137/0 | DB+3 | Sandy | 2025-08-24 | 2025-11-12 | 2025-08-28
132/4 | DA+0 | Sandy | 2025-09-25 | 2025-11-11 | 2025-09-25
98/0 | DC+0 | DFR | 2025-08-07 | 2025-11-10 | 2025-08-07
111/0 | DB+9 | Sandy | 2025-07-31 | 2025-11-10 | 2025-08-01
131/1 | DA+3 | Sandy | 2025-08-12 | 2025-11-09 | 2025-08-21
136/0 | DD+0 | Sandy | 2025-09-21 | 2025-11-08 | 2025-09-22
132/1 | DA+0 | Sandy | 2025-08-25 | 2025-11-07 | 2025-10-01
134A/4 | DA+9 | Sandy | 2025-08-16 | 2025-11-06 | 2025-08-19
77/0 | DB+0 | Sandy | 2025-07-19 | 2025-11-05 | 2025-07-21
129/1 | DA+3 | Sandy | 2025-07-31 | 2025-11-05 | 2025-08-26
132/3 | DA+0 | Sandy | 2025-08-31 | 2025-11-04 | 2025-10-01
134A/1 | DA+9 | Sandy | 2025-08-29 | 2025-11-03 | 2025-08-29
115/1 | DB+9 | Sandy | 2025-08-16 | 2025-11-02 | 2025-08-16
135/0 | DC+0 | Sandy | 2025-08-19 | 2025-11-02 | 2025-08-21
153A/0 | DB+0 | DFR | 2025-09-30 | 2025-11-01 | 2025-09-29
76/0 | DC+0 | Sandy | 2025-07-31 | 2025-10-31 | 2025-08-03
133/0 | DC+0 | Sandy | 2025-09-30 | 2025-10-31 | 2025-09-29
147/4 | DA+0 | Sandy | 2025-06-16 | 2025-10-31 | 2025-06-16
134/0 | DD+0 | Sandy | 2025-08-29 | 2025-10-29 | 2025-08-30
139/0 | DC+3 | Sandy | 2025-09-05 | 2025-10-28 | 2025-09-07
147/5 | DA+0 | Sandy | 2025-06-12 | 2025-10-28 | 2026-04-13
112/0 | DC+9 | Sandy | 2025-08-08 | 2025-10-27 | 2025-08-10
148/1 | DA+0 | Sandy | 2025-07-08 | 2025-10-27 | 2025-07-17
134A/2 | DA+3 | Sandy | 2025-08-26 | 2025-10-26 | 2025-08-27
147/6 | DA+0 | Sandy | 2025-09-05 | 2025-10-26 | 2025-09-08
82/2 | DA+0 | Sandy | 2025-06-10 | 2025-10-24 | 2025-06-10
135/1 | DA+0 | Sandy | 2025-08-23 | 2025-10-24 | 2025-08-23
138/0 | DB+3 | Sandy | 2025-08-28 | 2025-10-24 | 2025-08-29
134A/0 | DD+0 | Sandy | 2025-08-31 | 2025-10-23 | #N/A
147/1 | DA+0 | Sandy | 2025-06-21 | 2025-10-22 | 2025-06-22
147/8 | DA+0 | Sandy | 2025-06-30 | 2025-10-22 | 2025-07-01
133/1 | DA+0 | Sandy | 2025-07-30 | 2025-10-19 | 2025-08-01
138/3 | DA+0 | Sandy | 2025-08-31 | 2025-10-19 | 2025-09-19
147/2 | DA+0 | Sandy | 2025-06-08 | 2025-10-19 | #N/A
147/9 | DA+0 | Sandy | 2025-09-14 | 2025-10-19 | 2025-09-17
110/0 | DC+0 | Sandy | 2025-07-28 | 2025-10-18 | 2025-07-30
138/2 | DA+0 | Sandy | 2025-08-25 | 2025-10-16 | 2025-08-26
141/0 | DC+0 | Sandy | 2025-08-20 | 2025-10-16 | 2025-08-21
98A/0 | DC+0 | DFR | 2025-05-29 | 2025-10-15 | 2025-05-30
133/4 | DA+0 | Sandy | 2025-07-21 | 2025-10-15 | 2025-07-20
147/3 | DA+0 | Sandy | 2025-06-25 | 2025-10-15 | 2025-06-29
149A/0 | DD+0 | Sandy | 2025-08-19 | 2025-10-15 | 2025-09-26
115/0 | DC+0 | Sandy | 2025-07-18 | 2025-10-13 | 2025-07-22
138/1 | DA+0 | Sandy | 2025-08-23 | 2025-10-13 | 2025-08-24
147/0 | DC+0 | Sandy | 2025-06-15 | 2025-10-12 | 2025-06-27
133/8 | DA+6 | Sandy | 2025-07-27 | 2025-10-11 | 2025-07-26
140/3 | DA+3 | Sandy | 2025-08-14 | 2025-10-11 | 2025-08-19
140/2 | DA+3 | Sandy | 2025-08-17 | 2025-10-10 | 2025-08-19
146/0 | DC+0 | Sandy | 2025-07-08 | 2025-10-10 | 2025-07-08
149/0 | DD+0 | Sandy | 2025-08-28 | 2025-10-10 | 2025-08-28
144/0 | DD+6 | Sandy | 2025-08-07 | 2025-10-08 | 2025-08-06
116/0 | DD+0 | Sandy | 2025-07-31 | 2025-10-07 | 2025-08-03
142/0 | DC+3 | Sandy | 2025-07-17 | 2025-10-07 | 2025-08-13
133/7 | DA+0 | Sandy | 2025-07-31 | 2025-10-05 | 2025-08-01
146/2 | DA+0 | Sandy | 2025-06-25 | 2025-10-05 | 2025-06-25
146/1 | DA+3 | Sandy | 2025-06-30 | 2025-10-03 | 2025-07-08
147/7 | DA+0 | Sandy | 2025-06-22 | 2025-10-03 | 2025-06-29
98A/1 | DA+0 | DFR | 2025-03-30 | 2025-10-01 | 2025-04-06
141/1 | DA+0 | Sandy | 2025-07-11 | 2025-09-30 | 2025-08-19
143/0 | DC+3 | Sandy | 2025-07-21 | 2025-09-30 | 2025-07-24
145/4 | DA+3 | Sandy | 2025-07-13 | 2025-09-30 | 2025-07-12
149B/2 | DA+0 | Sandy | 2025-07-30 | 2025-09-30 | 2025-07-31
116/1 | DA+0 | Sandy | 2025-08-31 | 2025-09-29 | 2025-09-03
133/6 | DA+3 | Sandy | 2025-07-14 | 2025-09-29 | 2025-07-16
76/1 | DA+6 | Sandy | 2025-03-02 | 2025-09-27 | 2025-03-08
141/2 | DA+6 | Sandy | 2025-07-13 | 2025-09-27 | 2025-07-24
143/1 | DA+6 | Sandy | 2025-07-29 | 2025-09-27 | 2025-08-12
149B/1 | DA+3 | Sandy | 2025-07-27 | 2025-09-27 | #N/A
114/1 | DA+9 | Sandy | 2025-07-10 | 2025-09-26 | 2025-07-10
98/1 | DA+0 | DFR | 2025-04-04 | 2025-09-24 | 2025-04-06
143/3 | DA+3 | Sandy | 2025-07-26 | 2025-09-23 | 2025-08-13
143/7 | DA+3 | Sandy | 2025-08-02 | 2025-09-23 | 2025-08-06
148/7 | DA+0 | Sandy | 2025-07-23 | 2025-09-23 | 2025-07-27
133/3 | DA+0 | Sandy | 2025-07-24 | 2025-09-22 | 2025-07-25
97/1 | DA+3 | Sandy | 2025-08-05 | 2025-09-21 | 2025-08-06
113A/0 | DC+0 | Sandy | 2025-07-16 | 2025-09-21 | 2025-07-20
143/2 | DA+0 | Sandy | 2025-08-06 | 2025-09-20 | 2025-08-19
143/6 | DA+0 | Sandy | 2025-07-31 | 2025-09-20 | 2025-08-06
145/3 | DA+0 | Sandy | 2025-07-25 | 2025-09-19 | 2025-08-06
148/6 | DA+0 | Sandy | 2025-07-18 | 2025-09-19 | 2025-07-21
143/4 | DA+3 | Sandy | 2025-08-09 | 2025-09-17 | 2025-08-19
143/5 | DA+3 | Sandy | 2025-08-04 | 2025-09-17 | 2025-08-06
133/2 | DA+0 | Sandy | 2025-08-07 | 2025-09-16 | 2025-08-08
79/2 | DA+0 | Sandy | 2025-07-27 | 2025-09-15 | 2025-07-28
96/1 | DA+0 | Sandy | 2025-02-28 | 2025-09-15 | 2025-03-08
82/1 | DA+6 | Sandy | 2025-06-15 | 2025-09-14 | 2025-06-16
145/2 | DA+0 | Sandy | 2025-07-16 | 2025-09-14 | 2025-07-17
148/5 | DA+0 | Sandy | 2025-07-15 | 2025-09-14 | 2025-08-26
83/1 | DA+3 | Sandy | 2025-01-17 | 2025-09-11 | #N/A
97/0 | DC+0 | Sandy | 2025-05-23 | 2025-09-11 | 2025-06-10
148/2 | DA+0 | Sandy | 2025-07-10 | 2025-09-10 | 2025-07-17
81/4 | DA+0 | Sandy | 2025-04-29 | 2025-09-09 | 2025-05-02
145/1 | DA+3 | Sandy | 2025-07-21 | 2025-09-09 | 2025-07-17
81/2 | DA+3 | Sandy | 2025-03-08 | 2025-09-05 | 2025-03-08
148/3 | DA+0 | Sandy | 2025-07-05 | 2025-09-04 | 2025-07-17
81/3 | DA+0 | Sandy | 2025-06-04 | 2025-08-31 | 2025-06-05
95A/1 | DA+0 | DFR | 2025-02-25 | 2025-09-02 | 2025-02-25
148/4 | DA+0 | Sandy | 2025-07-12 | 2025-08-29 | 2025-08-26
80/1 | DA+9 | Sandy | 2025-02-27 | 2025-08-28 | 2025-02-28
86/1 | DA+6 | Sandy | 2025-03-09 | 2025-08-28 | #N/A
79/0 | DD+0 | Sandy | 2025-06-12 | 2025-08-23 | #N/A
85/1 | DA+0 | Sandy | 2025-03-10 | 2025-08-23 | 2025-03-11
73/2 | DA+9 | Sandy | 2025-02-25 | 2025-08-16 | 2025-02-25
78/0 | DC+0 | Sandy | 2025-06-16 | 2025-08-16 | 2025-06-16
75/0 | DC+0 | Sandy | 2025-06-07 | 2025-08-09 | #N/A
73/3 | DA+9 | Sandy | 2025-02-22 | 2025-08-08 | 2025-02-22
75/1 | DA+0 | Sandy | 2025-02-17 | 2025-08-04 | 2025-02-22
74/1 | DA+0 | Sandy | 2025-02-28 | 2025-07-31 | 2025-03-03
75/2 | DA+0 | Sandy | 2025-02-18 | 2025-07-31 | 2025-02-22
75/3 | DA+3 | Sandy | 2025-02-10 | 2025-07-28 | 2025-02-09
75/4 | DA+0 | Sandy | 2025-02-05 | 2025-07-25 | 2025-03-08
75/5 | DA+0 | Sandy | 2025-02-05 | 2025-07-22 | #N/A
75/6 | DA+0 | Sandy | 2025-02-02 | 2025-07-18 | 2025-02-03
77/1 | DA+0 | Sandy | 2025-02-11 | 2025-07-14 | 2025-02-24
77/3 | DA+0 | Sandy | 2025-02-14 | 2025-07-10 | 2025-03-01
75/7 | DA+0 | Sandy | 2025-01-27 | 2025-07-05 | 2025-01-28
77/5 | DA+6 | Sandy | 2025-02-19 | 2025-07-05 | 2025-02-20
77/4 | DA+3 | Sandy | 2025-02-17 | 2025-07-02 | 2025-02-24
77/2 | DA+3 | Sandy | 2025-02-09 | 2025-06-28 | 2025-03-08
104B/2 | DA+0 | Sandy | 2025-05-05 | 2025-12-21 | 2025-05-07
130/0 | DC+6 | Sandy | 2025-08-04 | 2025-12-05 | #N/A
150/0 | DD+9 | DFR | 2025-10-29 | 2025-12-07 | 2025-10-29
Formulas:
FDN CMP date = VLOOKUP([Location no],Foundation!$B8:P538,12, 0)
Erection CMP Date = VLOOKUP([Location no],'Erection Compiled '!$B2:Q516,10, 0)
Earthing CMP Date = VLOOKUP([Location no],Earthing!$B7:G560,4, 0)

## Erection Compiled
SL No. | Location No. | Tower Type | Classification | Starting Date | Tower Weight | Status | Completion Date | Gang Name | Gang Strength | Remark
1 | 77/2 | DA+3 |  | 2025-06-23 | 11.997 | COMPLETE | 2025-06-28 | Dipak
2 | 77/4 | DA+3 |  | 2025-06-28 | 11.997 | COMPLETE | 2025-07-02 | Dipak
3 | 75/7 | DA+0 |  | 2025-06-29 | 11.145 | COMPLETE | 2025-07-05 | Srikarni
4 | 77/5 | DA+6 |  | 2025-07-03 | 13.687 | COMPLETE | 2025-07-05 | Dipak
5 | 77/3 | DA+0 |  | 2025-07-07 | 11.145 | COMPLETE | 2025-07-10 | Dipak
6 | 77/1 | DA+0 |  | 2025-07-11 | 11.145 | COMPLETE | 2025-07-14 | Dipak
7 | 75/6 | DA+0 |  | 2025-07-15 | 11.145 | COMPLETE | 2025-07-18 | Dipak
8 | 75/5 | DA+0 |  | 2025-07-19 | 11.145 | COMPLETE | 2025-07-22 | Dipak
9 | 75/4 | DA+0 |  | 2025-07-22 | 11.145 | COMPLETE | 2025-07-25 | Dipak
10 | 75/3 | DA+3 |  | 2025-07-25 | 11.997 | COMPLETE | 2025-07-28 | Dipak
11 | 75/2 | DA+0 |  | 2025-07-29 | 11.145 | COMPLETE | 2025-07-31 | Dipak
12 | 74/1 | DA+0 |  | 2025-07-24 | 11.145 | COMPLETE | 2025-07-31 | Ahmed Construction
13 | 75/1 | DA+0 |  | 2025-08-01 | 11.145 | COMPLETE | 2025-08-04 | Dipak
14 | 73/3 | DA+9 |  | 2025-08-01 | 14.573 | COMPLETE | 2025-08-08 | Ahmed Construction
15 | 75/0 | DC+0 |  | 2025-08-04 | 18.727 | COMPLETE | 2025-08-09 | Dipak
16 | 73/2 | DA+9 |  | 2025-08-08 | 14.573 | COMPLETE | 2025-08-16 | Ahmed Construction
17 | 78/0 | DC+0 |  | 2025-08-10 | 18.727 | COMPLETE | 2025-08-16 | Dipak
18 | 85/1 | DA+0 |  | 2025-08-17 | 11.145 | COMPLETE | 2025-08-23 | Ahmed Construction
19 | 79/0 | DD+0 |  | 2025-08-17 | 21.410 | COMPLETE | 2025-08-23 | Dipak
20 | 86/1 | DA+6 |  | 2025-08-23 | 13.687 | COMPLETE | 2025-08-28 | Ahmed Construction
21 | 80/1 | DA+9 |  | 2025-08-23 | 14.573 | COMPLETE | 2025-08-28 | Dipak
22 | 148/4 | DA+0 |  | 2025-08-27 | 11.145 | COMPLETE | 2025-08-29 | Gokul Sarkar | 17
23 | 81/3 | DA+0 |  | 2025-08-29 | 11.145 | COMPLETE | 2025-08-31 | Dipak
24 | 95A/1 | DA+0 |  | 2025-08-23 | 11.145 | COMPLETE | 2025-09-02 | Ajay Kumar
25 | 148/3 | DA+0 |  | 2025-08-29 | 11.145 | COMPLETE | 2025-09-04 | Gokul Sarkar | 17
26 | 81/2 | DA+3 |  | 2025-09-01 | 11.997 | COMPLETE | 2025-09-05 | Dipak
27 | 145/1 | DA+3 |  | 2025-08-27 | 11.997 | COMPLETE | 2025-09-09 | Ayansh Const
28 | 81/4 | DA+0 |  | 2025-09-05 | 11.145 | COMPLETE | 2025-09-09 | Dipak
29 | 148/2 | DA+0 |  | 2025-09-05 | 11.145 | COMPLETE | 2025-09-10 | Gokul Sarkar | 17
30 | 83/1 | DA+3 |  | 2025-08-29 | 11.997 | COMPLETE | 2025-09-11 | Ahmed Construction
31 | 97/0 | DC+0 |  | 2025-09-01 | 18.727 | COMPLETE | 2025-09-11 | Ajay Kumar1
32 | 148/5 | DA+0 |  | 2025-09-11 | 11.145 | COMPLETE | 2025-09-14 | Gokul Sarkar | 17
33 | 145/2 | DA+0 |  | 2025-09-09 | 11.145 | COMPLETE | 2025-09-14 | Ayansh Const
34 | 82/1 | DA+6 |  | 2025-09-09 | 13.687 | COMPLETE | 2025-09-14 | Dipak
35 | 96/1 | DA+0 |  | 2025-09-01 | 11.145 | COMPLETE | 2025-09-15 | Ajay Kumar1
36 | 79/2 | DA+0 |  | 2025-09-11 | 11.145 | COMPLETE | 2025-09-15 | Ahmed Construction
37 | 133/2 | DA+0 |  | 2025-08-28 | 11.145 | COMPLETE | 2025-09-16 | Bhoi Enterprises | 23
38 | 148/6 | DA+0 |  | 2025-09-14 | 11.145 | COMPLETE | 2025-09-19 | Gokul Sarkar | 17
39 | 145/3 | DA+0 |  | 2025-09-14 | 11.145 | COMPLETE | 2025-09-19 | Ayansh Const
40 | 143/5 | DA+3 |  | 2025-09-11 | 11.997 | COMPLETE | 2025-09-17 | Prayag Saw | 26
41 | 143/4 | DA+3 |  | 2025-09-11 | 11.997 | COMPLETE | 2025-09-17 | Prayag Saw2 | 26
42 | 143/2 | DA+0 |  | 2025-09-18 | 11.145 | COMPLETE | 2025-09-20 | Prayag Saw | 26
43 | 143/6 | DA+0 |  | 2025-09-18 | 11.145 | COMPLETE | 2025-09-20 | Prayag Saw2 | 26
44 | 97/1 | DA+3 |  | 2025-09-11 | 11.997 | COMPLETE | 2025-09-21 | Ajay Kumar2
45 | 113A/0 | DC+0 |  | 2025-09-14 | 18.727 | COMPLETE | 2025-09-21 | Dipak
46 | 133/3 | DA+0 |  | 2025-09-17 | 11.145 | COMPLETE | 2025-09-22 | Bhoi Enterprises | 23
47 | 143/3 | DA+3 |  | 2025-09-21 | 11.997 | COMPLETE | 2025-09-23 | Prayag Saw | 26
48 | 143/7 | DA+6 |  | 2025-09-21 | 13.687 | COMPLETE | 2025-09-23 | Prayag Saw2 | 26
49 | 148/7 | DA+0 |  | 2025-09-20 | 11.145 | COMPLETE | 2025-09-23 | Gokul Sarkar | 17
50 | 98/1 | DA+0 |  | 2025-09-15 | 11.145 | COMPLETE | 2025-09-24 | Ajay Kumar1
51 | 114/1 | DA+9 |  | 2025-09-24 | 14.573 | COMPLETE | 2025-09-26 | Dipak
52 | 143/1 | DA+6 |  | 2025-09-22 | 13.687 | COMPLETE | 2025-09-27 | Prayag Saw2 | 26
53 | 141/2 | DA+6 |  | 2025-09-24 | 13.687 | COMPLETE | 2025-09-27 | Prayag Saw | 26
54 | 149B/1 | DA+3 |  | 2025-09-24 | 11.997 | COMPLETE | 2025-09-27 | Gokul Sarkar | 17
55 | 76/1 | DA+6 |  | 2025-09-19 | 13.687 | COMPLETE | 2025-09-27 | Ahmed Construction
56 | 116/1 | DA+0 |  | 2025-09-27 | 11.145 | COMPLETE | 2025-09-29 | Dipak
57 | 133/6 | DA+3 |  | 2025-09-23 | 11.997 | COMPLETE | 2025-09-29 | Bhoi Enterprises | 23
58 | 149B/2 | DA+0 |  | 2025-09-27 | 11.145 | COMPLETE | 2025-09-30 | Gokul Sarkar | 17
59 | 145/4 | DA+3 |  | 2025-09-20 | 11.997 | COMPLETE | 2025-09-30 | Pritam Enterprises
60 | 141/1 | DA+0 |  | 2025-09-27 | 11.145 | COMPLETE | 2025-09-30 | Prayag Saw | 26
61 | 143/0 | DC+3 |  | 2025-09-27 | 20.006 | COMPLETE | 2025-09-30 | Prayag Saw2 | 26
62 | 98A/1 | DA+0 |  | 2025-09-23 | 11.145 | COMPLETE | 2025-10-01 | Ajay Kumar2
63 | 146/1 | DA+3 |  | 2025-09-30 | 11.997 | COMPLETE | 2025-10-03 | Pritam Enterprises
64 | 147/7 | DA+0 |  | 2025-09-30 | 11.145 | COMPLETE | 2025-10-03 | Gokul Sarkar | 17
65 | 133/7 | DA+0 |  | 2025-09-29 | 11.145 | COMPLETE | 2025-10-05 | Bhoi Enterprises | 23
66 | 146/2 | DA+0 |  | 2025-10-03 | 11.145 | COMPLETE | 2025-10-05 | Pritam Enterprises
67 | 116/0 | DD+0 |  | 2025-09-30 | 21.410 | COMPLETE | 2025-10-07 | Dipak
68 | 142/0 | DC+3 |  | 2025-10-01 | 20.006 | COMPLETE | 2025-10-07 | Prayag Saw | 26
69 | 144/0 | DD+6 |  | 2025-10-01 | 26.291 | COMPLETE | 2025-10-08 | Prayag Saw2 | 26
70 | 146/0 | DC+0 |  | 2025-10-05 | 18.727 | COMPLETE | 2025-10-10 | Pritam Enterprises
71 | 140/2 | DA+3 |  | 2025-10-08 | 11.997 | COMPLETE | 2025-10-10 | Prayag Saw | 26
72 | 149/0 | DD+0 |  | 2025-10-03 | 21.410 | COMPLETE | 2025-10-10 | Gokul Sarkar | 17
73 | 133/8 | DA+6 |  | 2025-10-05 | 13.687 | COMPLETE | 2025-10-11 | Bhoi Enterprises | 23
74 | 140/3 | DA+3 |  | 2025-10-10 | 11.997 | COMPLETE | 2025-10-11 | Prayag Saw | 26
75 | 147/0 | DC+0 |  | 2025-10-10 | 18.727 | COMPLETE | 2025-10-12 | Pritam Enterprises
76 | 115/0 | DC+0 |  | 2025-10-08 | 18.727 | COMPLETE | 2025-10-13 | Dipak
77 | 138/1 | DA+0 |  | 2025-10-08 | 11.145 | COMPLETE | 2025-10-13 | Prayag Saw2 | 26
78 | 98A/0 | DC+0 |  | 2025-09-26 | 18.727 | COMPLETE | 2025-10-15 | Ajay Kumar
79 | 149A/0 | DD+0 |  | 2025-10-10 | 21.410 | COMPLETE | 2025-10-15 | Gokul Sarkar | 17
80 | 133/4 | DA+0 |  | 2025-10-11 | 11.145 | COMPLETE | 2025-10-15 | Bhoi Enterprises | 23
81 | 141/0 | DC+0 |  | 2025-10-11 | 18.727 | COMPLETE | 2025-10-16 | Prayag Saw | 26
82 | 147/3 | DA+0 |  | 2025-10-12 | 11.145 | COMPLETE | 2025-10-15 | Pritam Enterprises
83 | 138/2 | DA+0 |  | 2025-10-13 | 11.145 | COMPLETE | 2025-10-16 | Prayag Saw2 | 26
84 | 110/0 | DC+0 |  | 2025-10-13 | 18.727 | COMPLETE | 2025-10-18 | Dipak
85 | 133/1 | DA+0 |  | 2025-10-15 | 11.145 | COMPLETE | 2025-10-19 | Bhoi Enterprises | 23
86 | 138/3 | DA+0 |  | 2025-10-16 | 11.145 | COMPLETE | 2025-10-19 | Prayag Saw2 | 26
87 | 147/9 | DA+0 |  | 2025-10-16 | 11.145 | COMPLETE | 2025-10-19 | Gokul Sarkar | 17
88 | 147/2 | DA+0 |  | 2025-10-15 | 11.145 | COMPLETE | 2025-10-19 | Pritam Enterprises
89 | 147/1 | DA+0 |  | 2025-10-19 | 11.145 | COMPLETE | 2025-10-22 | Pritam Enterprises
90 | 147/8 | DA+0 |  | 2025-10-19 | 11.145 | COMPLETE | 2025-10-22 | Gokul Sarkar | 17
91 | 134A/0 | DD+0 |  | 2025-10-16 | 21.410 | COMPLETE | 2025-10-23 | Prayag Saw | 26
92 | 135/1 | DA+0 |  | 2025-10-19 | 11.145 | COMPLETE | 2025-10-24 | Bhoi Enterprises | 23
93 | 82/2 | DA+0 |  | 2025-10-19 | 11.145 | COMPLETE | 2025-10-24 | Namechand Mahto | 20
94 | 138/0 | DB+3 |  | 2025-10-19 | 18.111 | COMPLETE | 2025-10-24 | Prayag Saw2 | 26
95 | 134A/2 | DA+3 |  | 2025-10-24 | 11.997 | COMPLETE | 2025-10-26 | Prayag Saw | 26
96 | 112/0 | DC+9 |  | 2025-10-19 | 24.183 | COMPLETE | 2025-10-27 | Dipak
97 | 147/6 | DA+0 |  | 2025-10-23 | 11.145 | COMPLETE | 2025-10-26 | Pritam Enterprises
98 | 148/1 | DA+0 |  | 2025-10-23 | 11.145 | COMPLETE | 2025-10-27 | Gokul Sarkar | 17
99 | 147/5 | DA+0 |  | 2025-10-27 | 11.145 | COMPLETE | 2025-10-28 | Pritam Enterprises
100 | 134/0 | DD+0 |  | 2025-10-27 | 21.410 | COMPLETE | 2025-10-29 | Prayag Saw2 | 26
101 | 76/0 | DC+0 |  | 2025-10-24 | 18.727 | COMPLETE | 2025-10-31 | Namechand Mahto | 20
102 | 133/0 | DC+0 |  | 2025-10-24 | 18.727 | COMPLETE | 2025-10-31 | Bhoi Enterprises | 23
103 | 147/4 | DA+0 |  | 2025-10-28 | 11.145 | COMPLETE | 2025-10-31 | Pritam Enterprises
104 | 139/0 | DC+3 |  | 2025-10-26 | 20.006 | COMPLETE | 2025-10-28 | Prayag Saw | 26
105 | 153A/0 | DB+0 |  | 2025-10-27 | 16.817 | COMPLETE | 2025-11-01 | Gokul Sarkar | 17
106 | 115/1 | DB+9 |  | 2025-10-27 | 21.671 | COMPLETE | 2025-11-02 | Dipak
107 | 135/0 | DC+0 |  | 2025-10-29 | 18.727 | COMPLETE | 2025-11-02 | Prayag Saw | 26
108 | 134A/1 | DA+9 |  | 2025-10-29 | 14.573 | COMPLETE | 2025-11-03 | Prayag Saw2 | 26
109 | 132/3 | DA+0 |  | 2025-11-01 | 11.145 | COMPLETE | 2025-11-04 | Bhoi Enterprises | 23
110 | 77/0 | DB+0 |  | 2025-11-01 | 16.817 | COMPLETE | 2025-11-05 | Namechand Mahto | 20
111 | 129/1 | DA+3 |  | 2025-11-01 | 11.997 | COMPLETE | 2025-11-05 | Pritam Enterprises
112 | 134A/4 | DA+9 |  | 2025-11-04 | 14.573 | COMPLETE | 2025-11-06 | Prayag Saw2 | 26
113 | 132/1 | DA+0 |  | 2025-11-05 | 11.145 | COMPLETE | 2025-11-07 | Bhoi Enterprises | 23
114 | 136/0 | DD+0 |  | 2025-11-03 | 21.410 | COMPLETE | 2025-11-08 | Prayag Saw | 26
115 | 131/1 | DA+3 |  | 2025-11-06 | 11.997 | COMPLETE | 2025-11-09 | Pritam Enterprises
116 | 98/0 | DC+0 |  | 2025-11-06 | 18.727 | COMPLETE | 2025-11-10 | Namechand Mahto | 20
117 | 111/0 | DB+9 |  | 2025-11-03 | 21.671 | COMPLETE | 2025-11-10 | Dipak
118 | 132/4 | DA+0 |  | 2025-11-08 | 11.145 | COMPLETE | 2025-11-11 | Bhoi Enterprises | 23
119 | 137/0 | DB+3 |  | 2025-11-06 | 18.111 | COMPLETE | 2025-11-12 | Prayag Saw2 | 26
120 | 152/0 | DD+18 |  | 2025-11-01 | 39.401 | COMPLETE | 2025-11-14 | Gokul Sarkar | 17
121 | 129/0 | DC+0 |  | 2025-11-09 | 18.727 | COMPLETE | 2025-11-14 | Pritam Enterprises
122 | 131/2 | DA+3 |  | 11.11.2025 | 11.997 | COMPLETE | 2025-11-15 | Bhoi Enterprises | 23
123 | 80/0 | DB+3 |  | 10.11.2025 | 18.111 | COMPLETE | 2025-11-15 | Namechand Mahto | 20
124 | 145/0 | DD+6 |  | 12.11.2025 | 26.291 | COMPLETE | 2025-11-17 | Prayag Saw2 | 26
125 | 82/0 | DB+3 |  | 2025-11-15 | 18.111 | COMPLETE | 2025-11-20 | Namechand Mahto | 20
126 | 109A/0 | DB+6 |  | 2025-11-13 | 20.619 | COMPLETE | 2025-11-20 | Dipak
127 | 133/5 | DA+0 |  | 2025-11-15 | 11.145 | COMPLETE | 2025-11-20 | Bhoi Enterprises | 23
128 | 148/0 | DB+0 |  | 2025-11-16 | 16.817 | COMPLETE | 2025-11-21 | Prayag Saw2 | 26
129 | 149B/3 | DB+9 |  | 2025-11-14 | 21.671 | COMPLETE | 2025-11-22 | Gokul Sarkar | 17
130 | 78/1 | DA+3 |  | 2025-11-21 | 11.997 | COMPLETE | 2025-11-25 | Namechand Mahto | 20
131 | 134A/3 | DA+6 |  | 2025-11-21 | 13.687 | COMPLETE | 2025-11-25 | Prayag Saw2 | 26
132 | 135/2 | DA+0 |  | 2025-11-25 | 11.145 | COMPLETE | 2025-11-27 | Prayag Saw2 | 26
133 | 149B/0 | DB+3 |  | 2025-11-23 | 18.111 | COMPLETE | 2025-11-28 | Gokul Sarkar | 17
134 | 128/0 | DC+3 |  | 2025-11-21 | 20.006 | COMPLETE | 2025-11-28 | Bhoi Enterprises | 23
135 | 98B/0 | DD+0 |  | 2025-11-22 | 21.410 | COMPLETE | 2025-11-29 | Dipak
136 | 79/1 | DA+9 |  | 2025-11-25 | 14.573 | COMPLETE | 2025-11-30 | Namechand Mahto | 20
137 | 135/3 | DA+3 |  | 2025-11-28 | 11.997 | COMPLETE | 2025-11-30 | Prayag Saw2 | 26
138 | 140/1 | DA+3 |  | 2025-12-01 | 11.997 | COMPLETE | 2025-12-03 | Prayag Saw2 | 26
139 | 130/0 | DC+6 |  | 2025-11-28 | 22.946 | COMPLETE | 2025-12-05 | Bhoi Enterprises | 23
140 | 81/1 | DA+0 |  | 2025-12-01 | 11.145 | COMPLETE | 2025-12-05 | Namechand Mahto | 20
141 | 150/0 | DD+9 |  | 2025-11-28 | 27.715 | COMPLETE | 2025-12-07 | Gokul Sarkar | 17
142 | 95/0 | DB+9 |  | 2025-11-29 | 21.671 | COMPLETE | 2025-12-07 | Dipak
143 | 139/1 | DA+9 |  | 2025-12-06 | 14.573 | COMPLETE | 2025-12-10 | Prayag Saw2 | 26
144 | 81/0 | DB+9 |  | 2025-12-06 | 21.671 | COMPLETE | 2025-12-11 | Namechand Mahto | 20
145 | 126/2 | DA+3 |  | 2025-12-06 | 11.997 | COMPLETE | 2025-12-12 | Bhoi Enterprises | 23
146 | 140/0 | DB+0 |  | 2025-12-09 | 16.817 | COMPLETE | 2025-12-13 | Prayag Saw2 | 26
147 | 151/0 | DD+9 |  | 2025-12-07 | 27.715 | COMPLETE | 2025-12-14 | Gokul Sarkar | 17
148 | 126/1 | DA+6 |  | 2025-12-12 | 13.687 | COMPLETE | 2025-12-16 | Bhoi Enterprises | 23
149 | 85/0 | DC+0 |  | 2025-12-12 | 18.727 | COMPLETE | 2025-12-16 | Namechand Mahto | 20
150 | 72/2 | DA+3 |  | 2025-12-06 | 11.997 | COMPLETE | 2025-12-16 | Balaji Tour & Travels 2 | 24
151 | 119/2 | DA+3 |  | 2025-12-13 | 11.997 | COMPLETE | 2025-12-18 | Prayag Saw | 26
152 | 104B/2 | DA+0 |  | 2025-10-18 | 11.145 | COMPLETE | 2025-12-21 | Rajesh Mahto | 15
153 | 154/0 | DD+0 |  | 2025-12-14 | 21.410 | COMPLETE | 2025-12-21 | Gokul Sarkar | 17
154 | 119/1 | DA+3 |  | 2025-12-18 | 11.997 | COMPLETE | 2025-12-21 | Prayag Saw | 26
155 | 84/0 | DC+6 |  | 2025-12-17 | 22.946 | COMPLETE | 2025-12-21 | Namechand Mahto | 20
156 | 73/0 | DB+0 |  | 2025-12-19 | 16.817 | COMPLETE | 2025-12-24 | Bhoi Enterprises | 23
157 | 120/1 | DA+6 |  | 2025-12-21 | 13.687 | COMPLETE | 2025-12-25 | Prayag Saw | 26
158 | 90/1 | DA+9 |  | 2025-12-12 | 14.573 | COMPLETE | 2025-12-26 | Rajesh Mahto | 15
159 | 81/5 | DA+6 |  | 2025-12-17 | 13.687 | COMPLETE | 2025-12-26 | Namechand Mahto | 20
160 | 95/1 | DB+0 |  | 2025-12-27 | 16.817 | COMPLETE | 2025-12-30 | Rajesh Mahto | 15
161 | 123/0 | DC+0 |  | 2025-12-28 | 18.727 | COMPLETE | 2025-12-30 | Prayag Saw | 26
162 | 86/0 | DD+0 |  | 2025-12-28 | 21.410 | COMPLETE | 2025-12-31 | Namechand Mahto | 20
163 | 153/0 | DD+18 |  | 2025-12-21 | 39.401 | COMPLETE | 2026-01-04 | Gokul Sarkar | 17
164 | 125/3 | DA+0 |  | 2025-12-31 | 11.145 | COMPLETE | 2026-01-04 | Prayag Saw | 26
165 | 89/1 | DA+9 |  | 2025-12-31 | 14.573 | COMPLETE | 2026-01-05 | Rajesh Mahto | 15
166 | 83/0 | DC+0 |  | 2026-01-02 | 18.727 | COMPLETE | 2026-01-07 | Namechand Mahto | 20
167 | 95A/0 | DB+0 |  | 2026-01-07 | 16.817 | COMPLETE | 2026-01-10 | Vinay Construction
168 | 126/0 | DC+6 |  | 2026-01-05 | 22.946 | COMPLETE | 2026-01-11 | Prayag Saw | 26
169 | 71/3 | DA+0 |  | 2026-01-08 | 11.145 | COMPLETE | 2026-01-13 | Namechand Mahto | 20
170 | 129/2 | DA+9 |  | 2026-01-07 | 14.573 | COMPLETE | 2026-01-15 | Gokul Sarkar | 17
171 | 127/1 | DA+9 |  | 2026-01-13 | 14.573 | COMPLETE | 2026-01-16 | Prayag Saw | 26
172 | 113/0 | DD+0 |  | 2026-01-12 | 21.410 | COMPLETE | 2026-01-17 | Vinay Construction
173 | 71/2 | DA+0 |  | 2025-01-14 | 11.145 | COMPLETE | 2026-01-18 | Namechand Mahto | 20
174 | 102/2 | DA+0 |  | 2026-01-17 | 11.145 | COMPLETE | 2026-01-20 | Prayag Saw | 26
175 | 114/0 | DC+0 |  | 2026-01-20 | 18.727 | COMPLETE | 2026-01-24 | Prayag Saw | 26
176 | 118/0 | DC+3 |  | 2026-01-27 | 20.006 | COMPLETE | 2026-01-30 | Prayag Saw | 26
177 | 131/0 | DD+0 |  | 2026-01-31 | 21.410 | COMPLETE | 2026-02-05 | Prayag Saw | 26
178 | 128/1 | DA+6 |  | 2026-02-05 | 13.687 | COMPLETE | 2026-02-08 | Prayag Saw | 26
179 | 130/1 | DA+0 |  | 2026-02-08 | 11.145 | COMPLETE | 2026-02-11 | Prayag Saw | 26
180 | 132/2 | DA+0 |  | 2026-02-11 | 11.145 | COMPLETE | 2026-02-13 | Prayag Saw | 26
181 | 132/0 | DD+0 |  | 2026-02-12 | 11.145 | COMPLETE | 2026-02-18 | Prayag Saw | 26
182 | 91/1 | DA+0 |  | 2026-02-25 | 11.145 | COMPLETE | 2026-02-27 | Prayag Saw | 26
183 | 90/0 | DC+0 |  | 2026-02-20 | 18.727 | COMPLETE | 2026-02-24 | Prayag Saw | 26
184 | 66/0 | DD+0,1MRC |  | 2026-02-19 | 21.410 | COMPLETE | 2026-03-03 | Jitender Yadav | 16
185 | 65/1 | DB+9 |  | 2026-03-01 | 21.671 | COMPLETE | 2026-03-09 | Prayag Saw | 19
186 | 65/0 | DD+0 |  | 2026-03-10 | 21.410 | COMPLETE | 2026-03-16 | Prayag Saw | 19
187 | 64/7 | DA+3 |  | 2026-03-17 | 11.997 | COMPLETE | 2026-03-21 | Prayag Saw | 19
188 | 66/1 | DA+9 |  | 22--03-2026 | 14.573 | COMPLETE | 2026-03-29 | Rupesh Kumar | 22
189 | 10/5 | DA+0 |  | 2026-04-10 | 11.145 | COMPLETE | 2026-04-17 | KMCC (1) | 25
190 | 7/9 | DA+0 |  | 2026-04-16 | 11.145 | COMPLETE | 2026-04-20 | KMCC (2) | 20
191 | 10/6 | DA+0 |  | 2026-04-17 | 11.145 | COMPLETE | 2026-04-20 | KMCC (1) | 25
192 | 10/7 | DA+0 |  | 2026-04-20 | 11.145 | COMPLETE | 2026-04-23 | KMCC (2) | 20
193 | 10/8 | DA+0 |  | 2026-04-20 | 11.145 | COMPLETE | 2026-04-24 | KMCC (1) | 25
194 | 8/1 | DA+0 |  | 2026-04-20 | 11.145 | WIP |  | KMCC (1) | 25
195 | 7/7 | DA+0 |  | 2026-04-20 | 11.145 | WIP |  | KMCC (1) | 25

## Earthing
NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE
Client : RAJASTHAN IV A POWER TRANSMISSION LTD.
CONTRACTOR : KEC INTERNATIONAL LIMITED
SL. No. | Location Number | Tower Type | Foundation type | Completion Date | Remarks
1 | 75/7 | DA+0 | Sandy | 2025-01-28 | Complete | RA-2
2 | 75/6 | DA+0 | Sandy | 2025-02-03 | Complete | RA-2
3 | 75/3 | DA+3 | Sandy | 2025-02-09 | Complete | RA-2
4 | 77/5 | DA+6 | Sandy | 2025-02-20 | Complete | RA-2
5 | 73/3 | DA+09 | Sandy | 2025-02-22 | Complete | RA-2
6 | 75/1 | DA+0 | Sandy | 2025-02-22 | Complete | RA-2
7 | 75/2 | DA+0 | Sandy | 2025-02-22 | Complete | RA-2
8 | 77/1 | DA+0 | Sandy | 2025-02-24 | Complete | RA-2
9 | 77/4 | DA+3 | Sandy | 2025-02-24 | Complete | RA-2
10 | 79/1 | DA+9 | Sandy | 2025-02-24 | Complete | RA-2
11 | 73/2 | DA+9 | Sandy | 2025-02-25 | Complete | RA-2
12 | 95A/1 | DA+0 | DFR | 2025-02-25 | Complete | RA-2
13 | 80/1 | DA+9 | Sandy | 2025-02-28 | Complete | RA-2
14 | 77/3 | DA+0 | Sandy | 2025-03-01 | Complete | RA-3
15 | 74/1 | DA+0 | Sandy | 2025-03-03 | Complete | RA-3
16 | 75/4 | DA+0 | Sandy | 2025-03-08 | Complete | RA-3
17 | 76/1 | DA+6 | Sandy | 2025-03-08 | Complete | RA-3
18 | 77/2 | DA+3 | Sandy | 2025-03-08 | Complete | RA-3
19 | 81/2 | DA+3 | Sandy | 2025-03-08 | Complete | RA-4
20 | 96/1 | DA+0 | Sandy | 2025-03-08 | Complete | RA-3
21 | 96/2 | DA+0 | Sandy | 2025-03-08 | Complete | RA-3
22 | 85/1 | DA+0 | Sandy | 2025-03-11 | Complete | RA-3
23 | 64/3 | DA+9 | Sandy | 2025-03-28 | Complete | RA-4
24 | 64/5 | DA+9 | Sandy | 2025-04-05 | Complete | RA-4
25 | 98/1 | DA+0 | DFR | 2025-04-06 | Complete | RA-4
26 | 98A/1 | DA+0 | DFR | 2025-04-06 | Complete | RA-4
27 | 64/4 | DA+9 | Sandy | 2025-04-08 | Complete | RA-4
28 | 64/6 | DA+3 | Sandy | 2025-04-08 | Complete | RA-4
29 | 64/7 | DA+3 | Sandy | 2025-04-08 | Complete | RA-4
30 | 71/1 | DA+9 | Sandy | 2025-04-10 | Complete | RA-4
31 | 87/1 | DA+3 | Sandy | 2025-04-17 | Complete | RA-4
32 | 87/2 | DA+9 | Sandy | 2025-04-17 | Complete | RA-4
33 | 91/1 | DA+0 | Sandy | 2025-04-17 | Complete | RA-4
34 | 91/2 | DA+0 | Sandy | 2025-04-17 | Complete | RA-4
35 | 51/2 | DA+0 | Sandy | 2025-04-18 | Complete | RA-4
36 | 119/1 | DA+3 | Sandy | 2025-04-20 | Complete | RA-4
37 | 119/2 | DA+3 | Sandy | 2025-04-21 | Complete | RA-4
38 | 95/2 | DA+9 | Sandy | 2025-04-21 | Complete | RA-4
39 | 51/3 | DA+3 | Sandy | 2025-04-24 | Complete | RA-4
40 | 99/2 | DA+0 | DFR | 2025-04-25 | Complete | RA-4
41 | 81/4 | DA+0 | Sandy | 2025-05-02 | Complete | RA-5
42 | 62/4 | DA+6 | Sandy | 2025-05-06 | Complete | RA-5
43 | 104B/1 | DA+0 | Sandy | 2025-05-07 | Complete | RA-5
44 | 104B/2 | DA+0 | Sandy | 2025-05-07 | Complete | RA-5
45 | 105/1 | DA+3 | Sandy | 2025-05-15 | Complete | RA-5
46 | 100/1 | DA+6 | Sandy | 2025-05-19 | Complete | RA-5
47 | 81/5 | DA+6 | Sandy | 2025-05-21 | Complete | RA-5
48 | 99C/2 | DA+6 | Sandy | 2025-05-26 | Complete | RA-5
49 | 105/0 | DD+0 | Sandy | 2025-05-28 | Complete | RA-5
50 | 62/5 | DA+6 | Sandy | 2025-05-30 | Complete | RA-5
51 | 98A/0 | DC+0 | DFR | 2025-05-30 | Complete | RA-6
52 | 81/3 | DA+0 | Sandy | 2025-06-05 | Complete | RA-6
53 | 120/1 | DA+6 | Sandy | 2025-06-06 | Complete
54 | 96/0 | DC+0 | Sandy | 2025-06-07 | Complete | RA-6
55 | 82/2 | DA+0 | Sandy | 2025-06-10 | Complete | RA-6
56 | 97/0 | DC +0 | Sandy | 2025-06-10 | Complete | RA-6
57 | 147/2 | DA+0 | Sandy | 2025-06-13 | Complete | RA-14
58 | 79/0 | DD+0 | Sandy | 2025-06-14 | Complete | RA-15
59 | 119/0 | DD+3 | Sandy | 2025-06-15 | Complete
60 | 147/4 | DA+0 | Sandy | 2025-06-16 | Complete | RA -9
61 | 78/0 | DC+0 | Sandy | 2025-06-16 | Complete | RA-15
62 | 82/1 | DA+6 | Sandy | 2025-06-16 | Complete | RA-15
63 | 74/0 | DB+9 | Sandy | 2025-06-20 | Complete | RA-15
64 | 147/1 | DA+0 | Sandy | 2025-06-22 | Complete | RA-14
65 | 95A/0 | DB+0 | Sandy | 2025-06-24 | Complete | RA-15
66 | 146/2 | DA+0 | Sandy | 2025-06-25 | Complete | RA-14
67 | 147/0 | DC+0 | Sandy | 2025-06-27 | Complete | RA-14
68 | 73/0 | DB+0 | Sandy | 2025-06-28 | Complete | RA-15
69 | 147/3 | DA+0 | Sandy | 2025-06-29 | Complete | RA -9
70 | 147/7 | DA+0 | Sandy | 2025-06-29 | Complete | RA -9
71 | 86/0 | DD+0 | Sandy | 2025-06-29 | Complete | RA-6
72 | 147/8 | DA+0 | Sandy | 2025-07-01 | Complete | RA -9
73 | 72/2 | DA+3 | DFR | 2025-07-01 | Complete | RA-15
74 | 95/1 | DB+0 | DFR | 2025-07-06 | Complete | RA-15
75 | 106/0 | DC+6 | Sandy | 2025-07-07 | Complete
76 | 114/0 | DC+0 | Sandy | 2025-07-07 | Complete | RA-15
77 | 146/0 | DC+0 | Sandy | 2025-07-08 | Complete | RA-14
78 | 146/1 | DA+3 | Sandy | 2025-07-08 | Complete | RA-14
79 | 114/1 | DA+9 | Sandy | 2025-07-10 | Complete | RA-15
80 | 80/0 | DB+3,1MRC | Sandy | 2025-07-10 | Complete | RA-15
81 | 145/4 | DA+0 | Sandy | 2025-07-12 | Complete | RA -9
82 | 133/6 | DA+3 | Sandy | 2025-07-16 | Complete | RA -9
83 | 95/0 | DB+9 | DFR | 2025-07-16 | Complete | RA-15
84 | 133/5 | DA+0 | Sandy | 2025-07-17 | Complete | RA -9
85 | 145/1 | DA+3 | Sandy | 2025-07-17 | Complete | RA -9
86 | 145/2 | DA+0 | Sandy | 2025-07-17 | Complete | RA -9
87 | 148/1 | DA+0 | Sandy | 2025-07-17 | Complete | RA -9
88 | 148/2 | DA+0 | Sandy | 2025-07-17 | Complete | RA -9
89 | 148/3 | DA+0 | Sandy | 2025-07-17 | Complete | RA -9
90 | 109A/0 | DB+6 | Sandy | 2025-07-20 | Complete | RA-15
91 | 113A/0 | DC+0 | Sandy | 2025-07-20 | Complete | RA-15
92 | 133/4 | DA+0 | Sandy | 2025-07-20 | Complete | RA-14
93 | 148/6 | DA+0 | Sandy | 2025-07-21 | Complete | RA -9
94 | 77/0 | DB+0 | Sandy | 2025-07-21 | Complete | RA-15
95 | 115/0 | DC+0 | Sandy | 2025-07-22 | Complete
96 | 141/2 | DA+6 | Sandy | 2025-07-24 | Complete | RA -9
97 | 143/0 | DC+3 | Sandy | 2025-07-24 | Complete | RA -9
98 | 133/3 | DA+0 | Sandy | 2025-07-25 | Complete | RA -9
99 | 94/0 | DB+6 | Sandy | 2025-07-25 | Complete | RA-15
100 | 133/8 | DA+6 | Sandy | 2025-07-26 | Complete | RA -9
101 | 148/7 | DA+0 | Sandy | 2025-07-27 | Complete | RA -9
102 | 79/2 | DA+0 | Sandy | 2025-07-28 | Complete | RA-15
103 | 149B/1 | DA+3 | Sandy | 2025-07-28 | Complete | RA 12
104 | 99/3 | DA+3 | Sandy | 2025-07-29 | Complete
105 | 110/0 | DC+0 | Sandy | 2025-07-30 | Complete
106 | 149B/2 | DA+0 | Sandy | 2025-07-31 | Complete | RA 12
107 | 111/0 | DB+9,3MRC | Sandy | 2025-08-01 | Complete
108 | 133/1 | DA+0 | Sandy | 2025-08-01 | Complete | RA -9
109 | 133/7 | DA+0 | Sandy | 2025-08-01 | Complete | RA -9
110 | 98B/0 | DD+0 | DFR | 2025-08-02 | Complete | RA-15
111 | 87/0 | DC+0 | Sandy | 2025-08-02 | Complete | RA-15
112 | 116/0 | DD+0 | Sandy | 2025-08-03 | Complete
113 | 76/0 | DC+0 | Sandy | 2025-08-03 | Complete | RA-15
114 | 83/0 | DC+0 | Sandy | 2025-08-05 | Complete | RA-15
115 | 143/5 | DA+3 | Sandy | 2025-08-06 | Complete | RA-14
116 | 143/6 | DA+0 | Sandy | 2025-08-06 | Complete | RA -9
117 | 143/7 | DA+3 | Sandy | 2025-08-06 | Complete | RA-14
118 | 144/0 | DD+6 | Sandy | 2025-08-06 | Complete | RA -9
119 | 145/3 | DA+0 | Sandy | 2025-08-06 | Complete | RA -9
120 | 97/1 | DA+3 | Sandy | 2025-08-06 | Complete | RA-15
121 | 145/0 | DD+6 | Sandy | 2025-08-07 | Complete | RA -9
122 | 98/0 | DC+0,1MRC | Sandy | 2025-08-07 | Complete | RA-15
123 | 102/2 | DA+0 | Sandy | 2025-08-08 | Complete
124 | 129/0 | DC+0 | Sandy | 2025-08-08 | Complete | RA -9
125 | 133/2 | DA+0 | Sandy | 2025-08-08 | Complete | RA -9
126 | 112/0 | DC+9 | Sandy | 2025-08-10 | Complete
127 | 143/1 | DA+6 | Sandy | 2025-08-12 | Complete | RA-15
128 | 99/0 | DC +0 | Sandy | 2025-08-12 | Complete | RA-15
129 | 142/0 | DC+3 | Sandy | 2025-08-13 | Complete | RA -9
130 | 143/3 | DA+3 | Sandy | 2025-08-13 | Complete | RA-14
131 | 102/1 | DA+0 | Sandy | 2025-08-16 | Complete | RA-15
132 | 115/1 | DB+9 | Sandy | 2025-08-16 | Complete
133 | 134A/4 | DD+0 | Sandy | 2025-08-19 | Complete | RA -9
134 | 140/2 | DA+3 | Sandy | 2025-08-19 | Complete | RA -9
135 | 140/3 | DA+3 | Sandy | 2025-08-19 | Complete | RA -9
136 | 141/1 | DA+0 | Sandy | 2025-08-19 | Complete | RA -9
137 | 143/2 | DA+0 | Sandy | 2025-08-19 | Complete | RA-15
138 | 143/4 | DA+3 | Sandy | 2025-08-19 | Complete | RA -9
139 | 131/1 | DA+3 | Sandy | 2025-08-21 | Complete | RA -9
140 | 131/2 | DA+3 | Sandy | 2025-08-21 | Complete | RA -9
141 | 135/0 | DC+0 | Sandy | 2025-08-21 | Complete | RA-14
142 | 141/0 | DC+0 | Sandy | 2025-08-21 | Complete | RA -9
143 | 130/0 | DC+6 | Sandy | 2025-08-23 | Complete
144 | 135/1 | DA+0 | Sandy | 2025-08-23 | Complete | RA -9
145 | 129/2 | DA+9,3MRC | Sandy | 2025-08-24 | Complete | RA -9
146 | 138/1 | DA+0 | Sandy | 2025-08-24 | Complete | RA-14
147 | 99/4 | DA+3 | Sandy | 2025-08-24 | Complete | RA -9
148 | 125/0 | DC+3 | Sandy | 2025-08-26 | Complete | RA -9
149 | 125/1 | DA+0 | Sandy | 2025-08-26 | Complete | RA -9
150 | 126/0 | DC+6 | Sandy | 2025-08-26 | Complete | RA -9
151 | 126/1 | DA+6 | Sandy | 2025-08-26 | Complete | RA -9
152 | 126/2 | DA+3 | Sandy | 2025-08-26 | Complete | RA -9
153 | 128/0 | DC+3 | Sandy | 2025-08-26 | Complete | RA -9
154 | 129/1 | DA+3 | Sandy | 2025-08-26 | Complete | RA -9
155 | 138/2 | DA+0 | Sandy | 2025-08-26 | Complete | RA -9
156 | 148/4 | DA+0 | Sandy | 2025-08-26 | Complete | RA -9
157 | 148/5 | DA+0 | Sandy | 2025-08-26 | Complete | RA -9
158 | 134A/2 | DA+3 | Sandy | 2025-08-27 | Complete | RA -9
159 | 137/0 | DB+3 | Sandy | 2025-08-28 | Complete | RA -9
160 | 149/0 | DD+0 | Sandy | 2025-08-28 | Complete | RA 12
161 | 149B/0 | DB+3 | Sandy | 2025-08-28 | Complete | RA-14
162 | 134A/1 | DA+9 | Sandy | 2025-08-29 | Complete | RA-14
163 | 138/0 | DB+3 | Sandy | 2025-08-29 | Complete | RA-14
164 | 134/0 | DD+0 | Sandy | 2025-08-30 | Complete | RA -9
165 | 82/0 | DB+3 | Sandy | 2025-09-01 | Complete | RA-15
166 | 134A/0 | DD+0 | Sandy | 2025-09-02 | Complete | RA -9
167 | 116/1 | DA+0 | Sandy | 2025-09-03 | Complete | RA -9
168 | 99A/0 | DB+6 | Sandy | 2025-09-03 | Complete | RA -9
169 | 131/0 | DD+0 | Sandy | 2025-09-05 | Complete | RA 12
170 | 139/0 | DC+3,1MRC | Sandy | 2025-09-07 | Complete | RA -9
171 | 147/6 | DA+0 | Sandy | 2025-09-08 | Complete | RA -9
172 | 125/3 | DA+0 | Sandy | 2025-09-10 | Complete | RA -9
173 | 63/1 | DA+0 | Sandy | 2025-09-11 | Complete | RA-15
174 | 57/0 | DB+9 | Sandy | 2025-09-13 | Complete | RA -9
175 | 64/0 | DC+9 | Sandy | 2025-09-15 | Complete | RA -9
176 | 81/0 | DB+9 | Sandy | 2025-09-15 | Complete | RA-15
177 | 125/2 | DA+0 | Sandy | 2025-09-16 | Complete | RA -9
178 | 56/2 | DA+0 | Sandy | 2025-09-16 | Complete | RA -9
179 | 56/4 | DA+6 | Sandy | 2025-09-16 | Complete | RA -9
180 | 56/5 | DA+6 | Sandy | 2025-09-16 | Complete | RA -9
181 | 147/9 | DA+0 | Sandy | 2025-09-17 | Complete | RA -9
182 | 48/0 | DD+3 | Sandy | 2025-09-17 | Complete | RA-15
183 | 138/3 | DA+0 | Sandy | 2025-09-19 | Complete | RA -9
184 | 56/1 | DB+9 | Sandy | 2025-09-19 | Complete | RA-15
185 | 58/0 | DB+9 | Sandy | 2025-09-19 | Complete | RA -9
186 | 59/0 | DC+9 | Sandy | 2025-09-19 | Complete | RA -9
187 | 136/0 | DD+0 | Sandy | 2025-09-22 | Complete | RA -9
188 | 72/1 | DA+3 | Sandy | 2025-09-22 | Complete | RA -9
189 | 132/4 | DA+0 | Sandy | 2025-09-25 | Complete | RA 12
190 | 149A/0 | DD+0 | Sandy | 2025-09-26 | Complete | RA -9
191 | 153A/0 | DB+0 | DFR | 2025-09-29 | Complete | RA-15
192 | 133/0 | DC+0 | Sandy | 2025-09-29 | Complete | RA 12
193 | 123/0 | DC+0 | Sandy | 2025-09-30 | Complete | RA 12
194 | 132/1 | DA+0 | Sandy | 2025-10-01 | Complete | RA-15
195 | 132/3 | DA+0 | Sandy | 2025-10-01 | Complete | RA-15
196 | 149B/3 | DB+9 | Sandy | 2025-10-13 | Complete | RA 12
197 | 135/3 | DA+3 | Sandy | 2025-10-16 | Complete | RA-14
198 | 135/2 | DA+0 | Sandy | 2025-10-16 | Complete | RA-14
199 | 150/0 | DD+9 | DFR | 2025-10-29 | Complete | RA 12
200 | 71/2 | DA+0 | Sandy | 2025-10-31 | Complete | RA-15
201 | 148/0 | DB+0 | Sandy | 2025-11-04 | Complete | RA 12
202 | 73/1 | DA+0 | Sandy | 2025-11-05 | Complete | RA-15
203 | 84/0 | DC+6 | Sandy | 2025-11-05 | Complete | RA-15
204 | 85/0 | DC+0 | DFR | 2025-11-05 | Complete | RA-15
205 | 99/1 | DA+6 | Sandy | 2025-11-05 | Complete
206 | 71/3 | DA+0 | Sandy | 2025-11-08 | Complete | RA-15
207 | 151/0 | DD+9 | DFR | 2025-11-08 | Complete | RA-14
208 | 78/1 | DA+3 | Sandy | 2025-11-11 | Complete | RA-15
209 | 81/1 | DA+0 | Sandy | 2025-11-11 | Complete | RA-15
210 | 71/0 | DA+0 | Sandy | 2025-11-15 | Complete | RA-15
211 | 113/0 | DD+0 | Sandy | 2025-11-16 | Complete
212 | 72/0 | DD+0 | Sandy | 2025-11-18 | Complete | RA-15
213 | 154/0 | DD+0 | DFR | 2025-11-23 | Complete | RA 12
214 | 89/0 | DC+0 | Sandy | 2025-11-28 | Complete | RA-15
215 | 89/1 | DA+9 | Sandy | 2025-11-28 | Complete | RA-15
216 | 90/1 | DA+9 | Sandy | 2025-11-28 | Complete | RA-15
217 | 152/0 | DD+18 | DFR | 2025-12-02 | Complete | RA-14
218 | 153/0 | DD+18 | DFR | 2025-12-02 | Complete | RA-14
219 | 66/0 | DD+0 | Sandy | 2025-12-02 | Complete | RA-15
220 | 88/0 | DC+6 | Sandy | 2025-12-03 | Complete | RA-15
221 | 90/0 | DC+0 | Sandy | 2025-12-04 | Complete | RA-15
222 | 98B/2 | DCT+0 | Sandy | 2025-12-08 | Complete | RA-15
223 | 117/0 | DD+0 | Sandy | 2025-12-13 | Complete | RA-15
224 | 118/0 | DC+3 | Sandy | 2025-12-14 | Complete | RA-15
225 | 130/1 | DA+0 | Sandy | 2025-12-15 | Complete | RA 12
226 | 127/1 | DA+9 | Sandy | 2025-12-17 | Complete | RA 12
227 | 128/1 | DA+6 | sandy | 2025-12-17 | Complete | RA 12
228 | 139/1 | DA+9 | sandy | 2025-12-18 | Complete | RA 12
229 | 140/0 | DB+0 | sandy | 2025-12-18 | Complete | RA 12
230 | 140/1 | DA+3 | sandy | 2025-12-18 | Complete | RA 12
231 | 134A/3 | DA+6 | Sandy | 2025-12-18 | Complete | RA-14
232 | 117/1 | DA+3 | Sandy | 2025-12-20 | Complete | RA-15
233 | 132/2 | DA+0 | Sandy | 2025-12-21 | Complete | RA-14
234 | 91/0 | DD+0 | Sandy | 2025-12-26 | Complete | RA-15
235 | 132/0 | DD+0 | Sandy | 2025-12-29 | Complete | RA 12
236 | 124/0 | DC+3 | Sandy | 2025-12-30 | Complete | RA 12
237 | 91/3 | DA+0 | Sandy | 2026-01-02 | Complete | RA-15
238 | 104B/0 | DB+9 | Sandy | 2026-01-04 | Complete | RA-15
239 | 104A/0 | DC+9 | Sandy | 2026-01-05 | Complete | RA-15
240 | 122/2 | DA+3 | Sandy | 2026-01-09 | Complete | RA-14
241 | 126/3 | DA+6 | Sandy | 2026-01-15 | Complete | RA-14
242 | 65/1 | DB+9 | Sandy | 2026-01-16 | Complete | RA-15
243 | 69/3 | DA+0 | Sandy | 2026-01-16 | Complete | RA-15
244 | 65/0 | DD+0 | Sandy | 2026-01-17 | Complete | RA-15
245 | 108/0 | DC+0 | Sandy | 2026-01-20 | Complete | RA-15
246 | 109/0 | DC+3 | Sandy | 2026-01-24 | Complete
247 | 10/3 | DA+3 | Sandy | 2026-01-25 | Complete
248 | 120/0 | DC+0 | Sandy | 2026-01-28 | Complete | RA-15
249 | 92/0 | DC+0 | Sandy | 2026-01-29 | Complete | RA-15
250 | 10/6 | DA+0 | Sandy | 2026-01-30 | Complete
251 | 10/5 | DA+0 | Sandy | 2026-01-30 | Complete
252 | 93/0 | DA+3 | Sandy | 2026-01-31 | Complete | RA-15
253 | 10/7 | DC+0 | Sandy | 2026-01-31 | Complete
254 | 7/7 | DA+3 | Sandy | 2026-02-05 | Complete
255 | 117/2 | DB+9 | Sandy | 2026-02-28 | Complete | RA-14
256 | 98B/1 | DA+0 | Sandy | 2026-03-11 | Complete | RA-15
257 | 156/0 | DD+0 | DFR | 2026-03-11 | Complete | RA-15
258 | 157/0 | DD+0 | DFR | 2026-03-11 | Complete | RA-15
259 | 103/0 | DC+0 | Sandy | 2026-03-20 | Complete
260 | 10/8 | DA+0 | Sandy | 2026-03-23 | Complete
261 | 103/1 | DA+6 | Sandy | 2026-04-11 | Complete
262 | 147/5 | DA+0 | Sandy | 2026-04-13 | Complete
263 | 99C/0 | DD+0 | Sandy | 2025-04-16 | Complete

## Final Check In And Tack Welding
NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE
Client : RAJASTHAN IV A POWER TRANSMISSION LTD.
CONTRACTOR : KEC INTERNATIONAL LIMITED
SL No | Loc No | Final Checking | Tack Welding
1 | 65/0 | DONE
2 | 65/1 | DONE
3 | 66/0 | DONE
4 | 84/0 | DONE
5 | 85/0 | DONE
6 | 85/1 | DONE
7 | 86/0 | ROW
8 | 109A/0 | DONE
9 | 110/0 | DONE
10 | 111/0 | DONE
11 | 112/0 | DONE
12 | 113/0 | DONE
13 | 113A/0 | DONE
14 | 114/0 | DONE
15 | 114/1 | DONE
16 | 115/0 | DONE
17 | 115/1 | DONE
18 | 116/0 | DONE
19 | 116/1 | DONE
20 | 127/1 | DONE
21 | 128/0 | DONE
22 | 128/1 | DONE
23 | 129/0 | DONE
24 | 129/1 | DONE
25 | 129/2 | DONE
26 | 130/0 | DONE
27 | 130/1 | DONE
28 | 131/0 | DONE
29 | 131/1 | DONE
30 | 131/2 | DONE
31 | 132/0 | DONE | DONE
32 | 132/1 | DONE | DONE
33 | 132/2 | DONE | DONE
34 | 132/3 | DONE | DONE
35 | 132/4 | DONE | DONE
36 | 133/0 | DONE | DONE
37 | 133/1 | DONE | DONE
38 | 133/2 | DONE | DONE
39 | 133/3 | DONE | DONE
40 | 133/4 | DONE | DONE
41 | 133/5 | DONE | DONE
42 | 133/6 | DONE | ROW
43 | 133/7 | DONE | DONE
44 | 133/8 | DONE | DONE
45 | 134/0 | DONE | DONE
46 | 134A/0 | DONE | WIP
47 | 134A/1 | DONE | DONE
48 | 134A/2 | DONE
49 | 134A/3 | DONE
50 | 134A/4 | DONE
51 | 135/0 | DONE | DONE
52 | 135/1 | DONE
53 | 135/2 | DONE | DONE
54 | 135/3 | DONE | DONE
55 | 136/0 | DONE
56 | 137/0 | DONE | DONE
57 | 138/0 | DONE | DONE
58 | 138/1 | DONE | DONE
59 | 138/2 | DONE | DONE
60 | 138/3 | DONE | DONE
61 | 139/0 | DONE | DONE
62 | 139/1 | DONE | DONE
63 | 140/0 | DONE | DONE
64 | 140/1 | DONE | DONE
65 | 140/2 | DONE | DONE
66 | 140/3 | DONE | DONE
67 | 141/0 | DONE | DONE
68 | 141/1 | DONE | DONE
69 | 141/2 | DONE | DONE
70 | 142/0 | DONE | DONE
71 | 143/0 | DONE | DONE
72 | 143/1 | DONE | DONE
73 | 143/2 | DONE | DONE
74 | 143/3 | DONE | DONE
75 | 143/4 | DONE | DONE
76 | 143/5 | DONE | DONE
77 | 143/6 | DONE | DONE
78 | 143/7 | DONE | DONE
79 | 144/0 | DONE | DONE
80 | 145/0 | DONE | DONE
81 | 145/1 | DONE | DONE
82 | 145/2 | DONE | DONE
83 | 145/3 | DONE | DONE
84 | 145/4 | DONE | DONE
85 | 146/0 | DONE | DONE
86 | 146/1 | DONE | DONE
87 | 146/2 | DONE | DONE
88 | 147/0 | DONE | DONE
89 | 147/1 | DONE | DONE
90 | 147/2 | DONE | DONE
91 | 147/3 | DONE | DONE
92 | 147/4 | DONE | DONE
93 | 147/5 | DONE | DONE
94 | 147/6 | DONE | DONE
95 | 147/7 | DONE | DONE
96 | 147/8 | DONE | DONE
97 | 147/9 | DONE | DONE
98 | 148/0 | DONE | DONE
99 | 148/1 | DONE | DONE
100 | 148/2 | DONE | DONE
101 | 148/3 | DONE | DONE
102 | 148/4 | DONE | DONE
103 | 148/5 | DONE | DONE
104 | 148/6 | DONE | DONE
105 | 148/7 | DONE | DONE
106 | 149/0 | DONE | DONE
107 | 149A/0 | DONE | DONE
108 | 149B/0 | DONE | DONE
109 | 149B/1 | DONE | DONE
110 | 149B/2 | DONE | DONE
111 | 149B/3 | DONE | DONE
112 | 150/0 | DONE | DONE
113 | 151/0 | DONE | DONE
114 | 152/0 | DONE | DONE
115 | 153/0 | DONE | DONE
116 | 153A/0 | DONE | DONE
117 | 154/0 | DONE | DONE

## Stringing Compiled
|  |  | Number of TSE | 1
S.no | Sec | From AP | To AP | Span (M) | Method | Section Readiness | P/O Starting Date | P/O Completion Date | P/O | F/S Starting Date | F/S/ Completion Date | Length | Status | Gang Name | Hindrance | Remarks
1 | Bhinmal | 146/0 | 145/0 | 1970 | TSE | Ready | 2026-02-14 | 2026-02-16 |  | 2026-02-20 | 2026-02-22 | 1970 | complete | Mahadev Enterprises |  | Final Sag Complete
2 | Bhinmal | 149A/0 | 149/0 | 188 | Manual | Ready | 2026-03-01 | 2026-03-03 |  | 2026-03-03 | 2026-03-03 | 188 | complete | Mahadev Enterprises |  | Final Sag Complete
3 | Bhinmal | 149/0 | 148/0 | 3031 | TSE | Ready | 2026-02-01 | 2026-02-06 |  | 2026-03-16 | 2026-03-18 | 3031 | complete | Mahadev Enterprises |  | Final Sag Complete
4 | Bhinmal | 150/0 | 149B/3 | 489 | Manual | Ready | 2026-02-26 | 2026-02-27 |  | 2026-03-08 | 2026-03-08 | 489 | complete | Mahadev Enterprises |  | Final Sag Complete
5 | Bhinmal | 149B/0 | 149A/0 | 396 | Manual | Ready | 2026-03-05 | 2026-03-05 |  | 2026-03-10 | 2026-03-10 | 396 | complete | Mahadev Enterprises |  | Final Sag Complete
6 | Bhinmal | 149B/3 | 149B/0 | 1265 | TSE | Ready | 2026-03-05 | 2026-03-09 |  | 2026-03-08 | 2026-03-10 | 1265 | complete | Mahadev Enterprises |  | Final Sag Complete
7 | Bhinmal | 144/0 | 143/0 | 3275 | TSE | Ready | 2026-03-23 | 2026-04-04 |  |  | 2026-04-04 | 3275 | complete | Mahadev Enterprises |  | Final Sag Complete
8 | Bhinmal | 145/0 | 144/0 | 232 | Manual | Ready | 2026-04-09 |  |  |  | 2026-04-10 | 232 | complete | Mahadev Enterprises |  | Final Sag Complete (132 kv PLC )
9 | Sindhari | 113/0 | 112/0 | 158 | Manual | Ready | 2026-04-09 | 2026-04-10 |  |  | 2025-04-15 | 158 | complete | Mahadev Maan Construction |  | Final Sag Complete
10 | Bhinmal | 153/0 | 152/0 | 243 | Manual | Ready | 2026-04-16 |  |  |  | 2026-04-17 | 243 | complete | Mahadev Enterprises |  | Final Sag Complete (220 kv PLC )
11 | Sindhari | 113A/0 | 113/0 | 201 | Manual | Ready | 2026-04-10 | 2026-04-10 |  |  | 2026-04-18 | 201 | complete | Mahadev Maan Construction |  | Final Sag Complete
12 | Bhinmal | 147/0 | 146/0 | 1223 | TSE | Ready | 2026-02-18 | 2026-02-23 |  | 2026-03-20 | 2026-04-21 | 1223 | complete | Mahadev Enterprises |  | Final Sag Complete
13 | Bhinmal | 148/0 | 147/0 | 3666 | TSE | Ready | 2026-04-09 | 2026-04-20 |  |  | 2026-04-21 | 3666 | complete | Mahadev Enterprises |  | Final Sag Complete
14 | Bhinmal | 143/0 | 142/0 | 437 | Manual | Ready | 2026-03-23 | 2026-03-26 |  |  |  | 437 |  | Mahadev Enterprises |  | Paying out Complete
15 | Bhinmal | 134/0 | 133/0 | 3486 | TSE | Ready | [5 empty] | 3486 |  | Mahadev Enterprises |  | Insulator hosting Done
16 | Bhinmal | 150/0 | 151/0 | 290 | Manual | Ready | [5 empty] | 290 |  | Mahadev Enterprises |  | Rly Crossing Bit Cutting and Makeup
Total

## Soil Investigation
NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE
Client : RAJASTHAN IV A POWER TRANSMISSION LTD.
CONTRACTOR : KEC INTERNATIONAL LIMITED
SOIL INVESTIGATION STATUS
SL No. | LOC. No. | Tower Type | Soil Investigation date | Recommended Soil classification | Remarks
1 | 3/0 | DD+25 | 2025-02-01
2 | 4/0 | DC+0 | 2025-02-01
3 | 6/0 | DD+18 | 2025-01-31
4 | 7/0 | DB+0 | 2025-01-31
5 | 8/0 | DB+0 | 2025-01-31
6 | 9/0 | DB+0 | 2025-01-31
7 | 10/0 | DC+9 | 2025-01-30
8 | 12/0 | DD+0 | 2025-01-30
9 | 13/0 | DC+0 | 2025-01-30
10 | 15/0 | DC+6 | 2025-01-29
11 | 16/0 | DC+0 | 2025-01-29
12 | 17/0 | DB+0 | 2025-01-29
13 | 20/0 | DB+9 | 2025-01-29
14 | 21/0 | DC+9 | 2025-01-28
15 | 23/0 | DD+18 | 2025-01-28
16 | 24/0 | DD+25 | 2025-01-28
17 | 27/0 | DC+3 | 2025-01-27
18 | 29/0 | DC+3 | 2025-01-27
19 | 31/0 | DC+9 | 2025-01-27
20 | 35/0 | DC+9 | 2025-01-26
21 | 38/0 | DB+0 | 2025-01-26
22 | 40/0 | DD+3 | 2025-01-26
23 | 43/0 | DC+6 | 2025-01-25
24 | 44/0 | DB+9 | 2025-01-25
25 | 46/0 | DD+9 | 2025-01-25
26 | 47/0 | DD+9 | 2025-01-24
27 | 51/0 | DD+18 | 2025-01-24
28 | 54/0 | DB+9 | 2025-01-16
29 | 59/0 | DD+9 | 2025-01-16
30 | 62/0 | DB+0 | 2025-01-16
31 | 64/0 | DB+9 | 2025-01-15
32 | 66/0 | DD+3 | 2025-01-15
33 | 68/0 | DB+9 | 2025-01-15
34 | 71/0 | DB+0 | 2025-01-14
35 | 74/0 | DB+9 | 2025-01-14
36 | 76/0 | DC+0 | 2025-01-07
37 | 78/0 | DC+0 | 2025-01-07
38 | 81/0 | DB+9 | 2025-01-08
39 | 83/0 | DB+0 | 2025-01-09
40 | 87/0 | DC+0 | 2025-01-09
41 | 91/0 | DD+0 | 2025-01-09
42 | 92/0 | DC+0 | 2025-01-10
43 | 93/0 | DC+0 | 2025-01-10
44 | 94/0 | DB+6 | 2025-01-11
45 | 95/0 | DB+6 | 2025-01-11
46 | 98/1 | DCT+0 | 2025-01-11
47 | 99A/0 | DB+0 | 2025-01-12
48 | 103/0 | DC+0 | 2025-01-12
49 | 107/0 | DD+3 | 2025-01-12
50 | 111/0 | DD+9 | 2025-01-13
51 | 117/0 | DC+0 | 2025-01-13
52 | 121/0 | DD+0 | 2025-01-13
53 | 126/0 | DC+3 | 2025-01-17
54 | 131/0 | DC+0 | 2025-01-17
55 | 133/0 | DD+0 | 2025-01-18
56 | 133/1 | DC+0 | 2025-01-18 |  | River Crossing
57 | 133/2 | DA+0 | 2025-01-18 |  | River Crossing
58 | 133/3 | DA+0 | 2025-01-18
59 | 134/0 | DA+3 | 2025-01-19
60 | 137/0 | DB+0 | 2025-01-19
61 | 138/0 | DB+3 | 2025-01-20
62 | 141/0 | DB+3 | 2025-01-20
63 | 144/0 | DC+0 | 2025-01-20
64 | 145/0 | DD+6 | 2025-01-21
65 | 147/0 | DD+6 | 2025-01-21
66 | 148/0 | DC+0 | 2025-01-22
67 | 150/0 | DB+0 | 2025-01-21
68 | 151/0 | DD+9 | 2025-01-22
69 | 152/0 | DD+9 | 2025-01-22
70 | 153/0 | DD+18 | 2025-01-22
71 | 154/0 | DD+18 | 2025-01-23
72 | 155/0 | DD+30 | 2025-01-23
73 | 2/0 | DD+25 | 2025-03-28
Total Completed |  |  | 73

## Sheet9 (hidden)
400 KV D/C (TWIN) FATEHGARH IV - BHINMAL (PG) TRANSMISSION LINE (VISUAL CHART)
Name of Contractor:M/S KEC INTERNATIONAL LIMITED | [24 empty] | AS ON |  | 2026-04-24 11:21
PROGRESS AT A GLANCE :
[18 empty] | Stringing WIP |  |  |  | Stringing Completed
Sl. No. |  | Activity |  |  | UoM |  | Total Qty |  |  | Completed |  |  | Balance | [12 empty] | River Crossing
1 |  | Detail survey |  |  | Kms. |  | 188.444 |  |  | 188.444 |  |  | 0
2 |  | Check survey |  |  | Kms. |  | 188.444 |  |  | 178.075 |  |  | 10.369
3 |  | CS Approval |  |  | Kms. |  | 188.444 |  |  | 178.075 |  |  | 10.369
4 |  | Soil Investigation |  |  | Loc |  | 73 |  |  | 73 |  |  | 0
5 |  | Foundation |  |  | Loc |  | 512 |  |  | 208 |  |  | 304 | [12 empty] | Erection WIP
6 |  | Earthing |  |  | Nos. |  | 514 |  |  | 190 |  |  | 324 |  |  |  |  | Erection Comp |  |  | Span | [6 empty] | Rly. X-ing
7 |  | Erection |  |  | Loc |  | 512 |  |  | 75 |  |  | 437 |  |  |  |  | Earthing
8 |  | Tack Welding |  |  | Nos. |  | 512 | [5 empty] | 512
9 |  | Stringing(P/0) |  |  | Kms. |  | 188.444 | [5 empty] | 188.444 |  |  |  |  | Pipe Line |  |  |  |  | Excavation
10 |  | Stringing (F/S) |  |  | Kms. |  | 188.444 | [5 empty] | 188.444 | [11 empty] | NH | SH | 66/132/ 220/ 400
GANTRY |  |  | AP1 |  | AP 1A |  | AP2 |  | AP3 |  | 3/1 |  | 3/2 |  | 3/3 |  | AP4 |  | 4/1 |  | 4/2 |  | 4/3 |  | 4/4 |  | 4/5 | SH
[36 empty] | U/P | ROW | CLEAR
|  | 89 |  | 113 |  | 264 |  | 244 |  | 657 |  | 419.226 |  | 420.01 |  | 416.531 |  | 356.262 |  | 343.074 |  | 381.329 |  | 373.323 |  | 246.012 |  | 249.424 | [7 empty] | 0 | 0 | 0
|  |  | DD+0 |  | DD+3 |  | DD+25 |  | DD+25 |  | DB+6 |  | DA+0 |  | DA+9 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+6 |  | DA+3 |  | DB+0
REVISED DETAIL SURVEY REPORT SUBMITTED
| 4/6 |  | 4/7 |  | 4/8 |  | 4/9 |  | AP5 |  | AP6 |  | 6/1 |  | 6/2 |  | 6/3 |  | 6/4 |  | 6/5 |  | 6/6 |  | 6/7 |  | AP7
|  | 399.707 |  | 438.616 |  | 400.604 |  | 438.765 |  | 226.315 |  | 442.553 |  | 389.329 |  | 359.361 |  | 405.006 |  | 426.518 |  | 356.055 |  | 369.295 |  | 374.993 |  | 383.768 | [7 empty] | 0 | 0 | 0
| DA+0 |  | DA+6 |  | DA+6 |  | DA+3 |  | DD+18 |  | DD+18 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB+0
REVISED DETAIL SURVEY REPORT SUBMITTED
| 7/1 |  |  |  | 7/2 |  | 7/3 |  | 7/4 |  | 7/5 |  | 7/6 |  | 7/7 |  | 7/8 |  | 7/9 |  | 7/10 |  | AP8 |  | 8/1 |  | 8/2
|  |  | 396.38 |  |  | 392.534 |  | 332.162 |  | 352.112 |  | 389.393 |  | 374.477 |  | 419.977 |  | 387.899 |  | 407.654 |  | 402.357 |  | 372.259 |  | 410.949 |  | 379.075 | [7 empty] | 0 | 0 | 0
1MRC
| DA+0 |  |  |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DB+0 |  | DA+0 |  | DA+0
WORK FRONT TO BE CLEARED
| 8/3 |  | 8/4 |  | AP9 |  | 9/1 |  | 9/2 |  | 9/3 |  | 9/4 |  | 9/5 |  | AP 10 |  | 10/1 |  | 10/2 |  | 10/3 |  | 10/4 |  | 10/5
|  | 412.596 |  | 340.112 |  | 410.76 |  | 427.9 |  | 404.21 |  | 398.446 |  | 431.939 |  | 486.196 |  | 369.717 |  | 389.344 |  | 395.602 |  | 375 |  | 462 |  | 382 | [7 empty] | 0 | 0 | 0
| DA+0 |  | DA+3 |  | DB+0 |  | DA+3 |  | DA+6 |  | DA+0 |  | DA+3 |  | DB+9 |  | DC+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+6 |  | DA+0
WORK FRONT YET TO BE CLEARED
| 10/6 |  | 10/7 |  | 10/8 |  | 10/9 |  | 10/10 |  | 10/11 |  | 10/12 |  | 10/13 |  | 10/14 |  | 10/15 |  | AP11 |  | 11/1 |  | 11/2 |  | 11/3
|  | 428 |  | 411 |  | 352 |  | 405 |  | 400.126 |  | 384 |  | 406 |  | 378 |  | 373 |  | 378.362 |  | 433.995 |  | 370.685 |  | 323.972 |  | 384.462 | [7 empty] | 0 | 0 | 0
| DA+0 |  | DA+0 |  | DA+0 |  | DB+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+6 |  | DB+0 |  | DA+3 |  | DA+0 |  | DA+0
|  |  | 1 MRC-4 Leg | [5 empty] | 1 MRC-4 Leg
WORK FRONT YET TO BE CLEARED
| 11/4 |  | 11/5 |  | 11/6 |  | AP12 |  | 12/1 |  | 12/2 |  | AP13 |  | 13/1 |  | 13/2 |  | 13/3 |  | AP14 |  | 14/1 |  | AP15 |  | 15/1
|  | 381.188 |  | 336.409 |  | 438.97 |  | 395.179 |  | 388.12 |  | 364.446 |  | 404.572 |  | 432.27 |  | 404.23 |  | 416.621 |  | 468.039 |  | 432.318 |  | 464.521 |  | 369.743 | [7 empty] | 0 | 0 | 0
| DA+0 |  | DA+0 |  | DA+0 |  | DB+0 |  | DA+0 |  | DA+3 |  | DC+0 |  | DA+9 |  | DA+6 |  | DA+3 |  | DB+0 |  | DB+9 |  | DC+9 |  | DA+6
[8 empty] | Pit A,B 1MRC |  |  | B,C Bench | [9 empty] | 1 MRC -4 Leg
WORK FRONT YET TO BE CLEARED
| AP16 |  | 16/1 |  | AP17 |  | 17/1 |  | AP18 |  | 18/1 |  | AP19 |  | 19/1 |  | 19/2 |  | 19/3 |  | AP20 |  | 20/1 |  | 20/2 |  | 20/3
|  | 284.16 |  | 270.742 |  | 286.64 |  | 291.699 |  | 398.719 |  | 425.465 |  | 383.813 |  | 403.279 |  | 355.215 |  | 399.839 |  | 287.442 |  | 390.748 |  | 364.274 |  | 337.546 | [7 empty] | 0 | 0 | 0
| DD+0 |  | DA+0 |  | DB+0 |  | DA+0 |  | DC+0 |  | DA+6 |  | DD+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+0
[12 empty] | Pit D 1MRC | [10 empty] | Pit B 1MRC
WORK FRONT YET TO BE CLEARED
| 20/4 |  | 20/5 |  | 20/6 |  | AP21 |  | 21/1 |  | 21/2 |  | AP22 |  | AP23 |  | 23/1 |  | 23/2 |  | 23/3 |  | AP24 |  | 24/1 |  | AP25
|  | 348.292 |  | 418.835 |  | 408.963 |  | 365.467 |  | 437.074 |  | 363.142 |  | 159.789 |  | 300.158 |  | 293.131 |  | 357.377 |  | 341.409 |  | 362.905 |  | 421.052 |  | 216.448 | [7 empty] | 0 | 0 | 0
| DA+0 |  | DA+3 |  | DA+9 |  | DD+3 |  | DA+0 |  | DA+6 |  | DB+3 |  | DD+0 |  | DB+3 |  | DA+0 |  | DA+0 |  | DC+9 |  | DA+9 |  | DD+6
3MRC-4 LEG
WORK FRONT YET TO BE CLEARED | [22 empty] | C/S REPORT TO BE APPROVED
| 25/1 |  | 25/2 |  | AP 26 |  | AP 27 |  | 27A/0 |  | 27A/1 |  | 27A/2 |  | AP27B |  | 27B/1 |  | 27B/2 |  | 27B/3 |  | AP28 |  | 28/1 |  | AP29
|  | 439.695 |  | 243.188 |  | 333.219 |  | 333.219 |  | 363.001 |  | 363.001 |  | 356.124 |  | 376.245 |  | 381.122 |  | 364.433 |  | 263.077 |  | 356.193 |  | 352.42 |  | 381.028 | [7 empty] | 0 | 0 | 0
| GTY |  | GTY |  | DB+0 |  | DC+9 |  | DD+9 |  | DA+0 |  | DA+6 |  | DC+0 |  | DA+6 |  | DA+0 |  | DA+9 |  | DB+3 |  | DA+3 |  | DB+9
C/S REPORT YET TO BE APPROVED | [7 empty] | WORK FRONT TO BE CLEARED
| 29/1 |  | 29/2 |  | 29/3 |  | AP30 |  | 30/1 |  | 30/2 |  | 30/3 |  | AP31 |  | AP32 |  | 32/1 |  | 32/2 |  | 32/3 |  | AP33 |  | AP34 |  | 34/1
|  | 419.603 |  | 425.18 |  | 425.18 |  | 287.537 |  | 336.512 |  | 325.304 |  | 214.253 |  | 455.946 |  | 421 |  | 419 |  | 408 |  | 409.749 |  | 324.03 |  | 366.7 |  | 473.305 | [5 empty] | 0 | 0 | 0
| DA+6 |  | DA+9 |  | DB+9 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC+9 |  | DC+9 |  | DA+3 |  | DA+3 |  | DA+9 |  | DB+0 |  | DC+6 |  | DA+9
WORK FRONT TO BE CLEARED
| AP35 |  | 35/1 |  | AP36 |  | 36/1 |  | 36/2 |  | 36A |  | AP37 |  | AP38 |  | 38/1 |  | 38/2 |  | 38/3 |  | 38/4 |  | 38/5 |  | AP39 |  | 39/1 |  | 39/2
|  | 358.321 |  | 477.815 |  | 415.464 |  | 402.229 |  | 437.434 |  |  |  | 455.922 |  | 419.765 |  | 418.917 |  | 386.486 |  | 376.53 | [5 empty] | 404.739 |  | 366.729 |  | 274.587 |  |  |  | 0 | 0 | 0
| DC+9 |  | DA+9 |  | DC+6 |  | DA+9 |  | DA+0 |  | DD+0 |  | DD+0 |  | DB+0 |  | DB+6 |  | DA+3 |  | DA+9 |  | DA+0 |  | DA+9 |  | DB+3 |  | DA+6 |  | DA+0
WORK FRONT TO BE CLEARED
| 39/3 |  | 39/4 |  | AP40 |  |  | AP41 |  | 41/1 |  | 41/2 |  | 41/3 |  | AP42 |  | 42/1 |  | 42/2 |  | 42/3
|  | 341.668 |  | 425.863 |  | 370.45 | 397.61 |  | 413.4 |  | 423.65 |  | 415.97 |  | 415.35 |  | 394.875 | U/P | 429.62 |  | 381.905 |  | 405.26 | [9 empty] | 1 | 0 | 0 | 1 | 0 | 0
ROW
| DA+0 |  | DA+6 |  | DD+3 |  |  | DB+0 |  | DA+9 |  | DA+0 |  | DA+9 |  | DC+3 |  | DA+9 |  | DCT+6 |  | DA+9
[12 empty] | Pit C,B 1MRC |  |  |  |  | Benching ,Pit C,B 1MRC |  |  |  |  | 3MRC-4 LEG
WORK FRONT YET TO BE CLEARED
| 42/4 |  | 42/5 |  | 42/6 |  | 42/7 |  | AP43 | NH | AP44 |  | 44/1 |  | AP45 |  | 45/1 |  | 45/2 |  | 45/3 |  | 45/4 |  | AP46 |  | AP47
|  | 338.156 |  | 288.303 |  | 297.15 |  | 195.903 |  | 249.66 |  | 374.48 |  | 430.3 |  | 404.386 |  | 341.423 |  | 305.401 |  | 319.981 |  | 345.621 |  | 223.151 |  | 393.817 | [7 empty] | 0 | 0 | 0
| DA+9 |  | DA+0 |  | DA+3 |  | DA+0 |  | DC+6 |  | DB+9 |  | DA+9 |  | DD+9 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+6 |  | DD+3 |  | DD+9
3MRC-4 LEG |  |  | Benching |  | 1MRC-4 leg |  | Benching |  |  |  | 3MRC |  | 3MRC
WORK FRONT YET TO BE CLEARED | [15 empty] | REVISED CHECK SURVEY TO BE SUBMITTED
| 47/1 |  | 47/2 |  | AP48 |  | AP49 |  | AP50 |  | AP51 |  | 51/1 |  | 51/2 |  | 51/3 |  | AP52 |  | 52/1 |  | AP53 | SH | AP54 |  | 54/1
|  | 435.136 | U/P | 403.209 |  | 422.554 |  | 353.484 |  | 274.9 |  | 465.033 |  | 373.98 |  | 416.864 |  | 381.019 |  | 391.52 |  | 374.93 |  | 248.57 |  | 384.17 |  | 330.76 | [7 empty] | 1 | 0 | 0
ROW
| DA+9 |  | DA+9 |  | DD+3 |  | DD+3 |  | DD+9 |  | DD+18 |  | DA+3 |  | DA+0 |  | DA+3 |  | DB+0 |  | DA+6 |  | DD+0 |  | DC+0 |  | DA+3
[9 empty] | 3MRC | [9 empty] | 2MRC ?? |  | 1MRC-4LEG
REVISED C/S TO BE SUBMITTED | [5 empty] | WOK FRONT YET TO BE CLEARED | [11 empty] | WORK FRONT YET TO BE CLEARED
| 54/2 |  | 54/3 |  | AP55 |  | AP56 |  | 56/1 |  | 56/2 |  | 56/3 |  | 56/4 |  | 56/5 |  | AP57 |  | AP58 |  | AP59 |  | 59/1 |  | AP60
C
| C | 285.32 |  | 354.7 |  | 420.54 |  | 340.56 |  | 336.52 |  | 375.99 |  | 308.41 |  | 444.84 |  | 392.02 |  | 407.803 |  | 206.062 |  | 417.384 |  | 304.564 |  | 395.51 | [7 empty] | 0 | 0 | 1
| DA+6 |  | DA+3 |  | DD+18 |  | DB+9 |  | DB+9 |  | DA+0 |  | DB+9 |  | DA+6 |  | DA+6 |  | DB+9 |  | DB+9 |  | DC+9 |  | DA+0 |  | DD+0
|  |  | 1MRC-4Leg |  | 3MRC-4 Leg |  | 2MRC?? |  |  |  | Pit | [5 empty] | B & RC?? |  | B & RC?? | [5 empty] | Benching
WORK FRONT YET TO BE CLEARED | [12 empty] | ROW | [6 empty] | WORK FRONT YET TO BE CLEARED
| 60/1 |  | 60/2 |  | 60/3 |  | AP61 |  | 61/1 |  | AP62 |  | 62/1 |  | 62/2 |  | 62/3 |  | 62/4 |  | 62/5 |  | AP63 |  | 63/1 |  | AP64
ROW
|  | 431.02 |  | 403.43 |  | 420.36 |  | 446.37 |  | 297.58 |  | 280.47 |  | 272.69 |  | 347.88 |  | 379.25 |  | 398.7 |  | 439.06 | ROW | 360.21 |  | 379.58 |  | 384 | [7 empty] | 0 | 1 | 0
| DA+9 |  | DA+3 |  | DA+9 |  | DC+0 |  | DA+9 |  | DB+0 |  | DA+0 |  | DA+0 |  | DA+9 |  | DA+6 |  | DA+6 |  | DC+0 |  | DA+0 |  | DC+9
[5 empty] | RC 3M-4 Leg | [7 empty] | B Leg A&D,C Leg 1MRC |  |  |  | 3MRC-4 Leg | [11 empty] | 1MRC-4 Leg, A,D Benching,C Leg 1MRC
WORK FRONT YET TO BE CLEARED | [22 empty] | ROW
| 64/1 |  | 64/2 |  | 64/3 |  | 64/4 |  | 64/5 |  | 64/6 |  | 64/7 |  | AP65 |  | 65/1 |  | AP66 |  | 66/1 |  | 66/2 |  | 66/3 |  | 66/4
| ROW | 442 | ROW | 397 |  | 395 |  | 432 |  | 408 |  | 426 |  | 392.95 |  | 431.96 |  | 426.02 |  | 401 |  | 437 |  | 402 |  | 436 |  | 392.28 | [7 empty] | 0 | 1 | 0
| DA+9 |  | DA+9 |  | DA+9 |  | DA+9 |  | DA+9 |  | DA+3 |  | DA+3 |  | DD+0 |  | DB+9 |  | DD+0 |  | DA+9 |  | DA+0 |  | DA+3 |  | DA+9
| 3MRC-4 Leg |  | 1MRC-4 Leg | [15 empty] | 1MRC-4 Leg
| ROW | [13 empty] | ROW | [11 empty] | ROW
| AP67 |  | 67/1 |  | 67/2 |  | AP68 |  | AP69 |  | 69/1 |  | 69/2 |  | 69/3 | AP70 |  | AP71 |  | SH | 71/1 |  | 71/2 |  | 71/3 |  | AP72
|  | 402.5 |  | 411.56 |  | 438.46 |  | 410.36 |  | 379.76 |  | 396.95 |  | 414.59 |  | 352.99 |  | 389.3 |  | 237.59 |  | 290.88 |  | 345.61 |  | 318.63 | U/P | 307.02 | [7 empty] | 1 | 0 | 0
| DC+6 |  | DA+6 |  | DB+0 |  | DB+9 |  | DD+3 |  | DA+6 |  | DA+0 |  | DA+0 |  | DD+0 |  | DB+0 |  | DA+9 |  | DA+0 |  | DA+0 |  | DD+0
| 1MRC-4 Leg | [11 empty] | Bench |  | 1MRC-4 Leg | [9 empty] | 1MRC-4 Leg?? |  | Bench 4 Legs,RC A&C- 3M, B&D- 1M RC
WORK FRONT YET TO BE CLEARED | [21 empty] | WORK FRONT YET TO BE CLEARED
| 72/1 |  | 72/2 |  | AP73 |  | 73/1 |  | 73/2 |  | 73/3 |  | AP74 |  | 74/1 |  | AP75 |  | 75/1 |  | 75/2 |  | 75/3 |  | 75/4 |  | 75/5
|  | 346.85 |  | 300.19 |  | 317 | U/P | 454 |  | 385 |  | 417.69 |  | 409.51 |  | 385.17 |  | 345.19 |  | 332.38 |  | 393.62 |  | 387.95 |  | 340.35 |  | 393.12 | [7 empty] | 1 | 0 | 0
| DA+3 |  | DA+3 |  | DB+0 |  | DA+0 |  | DA+9 |  | DA+9 |  | DB+9 |  | DA+0 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0
Bench A & B, Pit C 1MRC & Pit D 3M RC | [6 empty] | C&D-3MRC | [11 empty] | Bench
| 75/6 |  | 75/7 |  | AP76 |  | 76/1 |  | AP77 |  | 77/1 |  | 77/2 |  | 77/3 |  | 77/4 |  | 77/5 |  | AP78 |  | 78/1 |  | AP79 |  | 79/1
|  | 328.54 |  | 398.52 |  | 425.85 |  | 409.37 |  | 388.46 |  | 380.96 |  | 381.39 |  | 344.6 |  | 395.64 |  | 414.76 |  | 401.93 | ROW | 354.95 |  | 425 |  | 414 | [7 empty] | 0 | 1 | 0
| DA+0 |  | DA+0 |  | DC+0 |  | DA+6 |  | DB+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+6 |  | DC+0 |  | DA+3 |  | DD+0 |  | DA+9
[13 empty] | Bench | [9 empty] | 1MRC
ROW
| 79/2 |  | AP80 |  | 80/1 |  | AP81 |  | 81/1 |  | 81/2 |  | 81/3 |  | 81/4 |  | 81/5 |  | AP82 |  | 82/1 |  | 82/2 |  | AP83 |  | 83/1
|  | 353.05 |  | 441.06 |  | 387.5 |  | 372.63 |  | 415.3 |  | 424.58 |  | 391.7 |  | 410.47 |  | 385.54 |  | 418.31 |  | 421.47 |  | 401.98 |  | 429.38 |  | 403.83 | [7 empty] | 0 | 0 | 0
| DA+0 |  | DB+3 |  | DA+9 |  | DB+9 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+6 |  | DB+3 |  | DA+6 |  | DA+3 |  | DC+0 |  | DA+3
Bench & 1MRC |  |  | 1MRC |  | Bench |  | Bench |  | Bench
[7 empty] | ROW | [17 empty] | ROW
| AP84 |  | AP85 |  | 85/1 |  | AP86 |  | 86/1 |  | 86/2 |  | AP87 |  | 87/1 |  | 87/2 |  | AP88 |  | AP89 |  | 89/1 |  | AP90 |  | 90/1
| U/P | 384.63 |  | 380.682 |  | 354.526 |  | 405.574 |  | 416.874 |  | 380.766 |  | 411.81 |  | 392.08 |  | 296.87 | ROW | 412.4 | ROW | 382.17 | ROW | 452.74 | ROW | 420.21 | ROW | 395.01 | [7 empty] | 1 | 5 | 0
| DC+6 |  | DC+0 |  | DA+0 |  | DD+0 |  | DA+6 |  | DA+0 |  | DC+0 |  | DA+3 |  | DA+9 |  | DC+6 |  | DC+0 |  | DA+9 |  | DC+0 |  | DA+9
WORK FRONT YET TO BE CLEARED
| AP91 |  | 91/1 |  | 91/2 |  | 91/3 |  | AP92 | SH | AP93 |  | AP94 |  | AP95 |  | 95/1 |  | 95/2 |  | AP95A |  | 95A/1 |  | AP96 |  | 96/1
| ROW | 386.74 |  | 378.62 |  | 350.215 | ROW | 357.91 | ROW | 237.48 | ROW | 440.03 |  | 503.74 |  | 437 |  | 430 |  | 409.27 |  | 312.45 |  | 314.25 |  | 361.96 |  | 329.49 | [7 empty] | 0 | 3 | 0
ROW
| DD+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC+0 |  | DC+0 |  | DB+6 |  | DB+9 |  | DB+0 |  | DA+9 |  | DB+0 |  | DA+0 |  | DC+0 |  | DA+0
| ROW | [5 empty] | ROW
| 96/2 |  | AP97 |  | 97/1 |  | AP98 |  | 98/1 |  | AP98A |  | 98A/1 |  | AP98B |  | 98B/1 |  | 98B/2 |  | AP99 |  | 99/1 |  | 99/2 |  | 99/3
|  | 371.33 |  | 417.92 |  | 376.99 |  | 343.8 |  | 318.7 |  | 308 |  | 324.87 |  | 365.39 | ROW | 269.53 | ROW | 360.33 |  | 414 |  | 424 |  | 405 |  | 426 | [7 empty] | 0 | 2 | 0
| DA+0 |  | DC+0 |  | DA+3 |  | DC+0 |  | DA+0 |  | DC+0 |  | DA+0 |  | DD+0 |  | DA+0 |  | DCT+0 |  | DC+0 |  | DA+6 |  | DA+0 |  | DA+3
[5 empty] | 1MRC-4 Leg | [6 empty] | ROW |  |  |  |  | 1MRC-4Leg
ROW
| 99/4 |  | 99A/0 |  | 99B/0 |  | 99C/0 |  | 99C/1 |  | 99C/2 |  | AP100 |  | 100/1 |  | AP101 |  | AP102 |  | 102/1 |  | 102/2 |  | AP103 |  | 103/1
|  | 410 |  | 421 | ROW | 407.61 | ROW | 364.36 | ROW | 332.448 |  | 348.85 | ROW | 387.35 |  | 452.64 | ROW | 386.96 | ROW | 382.14 |  | 336.47 |  | 389.14 | ROW(P) | 334.55 | ROW(P) | 396.2 | [7 empty] | 0 | 6 | 0
| DA+3 |  | DB+6 |  | DD+0 |  | DD+0 |  | DA+6 |  | DA+3 |  | DC+0 |  | DA+6 |  | DD+0 |  | DD+3 |  | DA+0 |  | DA+0 |  | DC+0 |  | DA+6
Bench A&D
[5 empty] | ROW | [7 empty] | ROW |  |  |  | ROW | [7 empty] | ROW
AP104 |  | AP 104A |  |  | AP 104B |  | 104B/1 |  | 104B/2 |  | AP105 |  | 105/1 |  | AP106 |  | AP107 |  | 107/1 |  | AP108 |  | AP 109 | AP 109A |  |  | AP110
|  | 233.29 |  | 467.19 | ROW(P) | 423.02 |  | 248.69 |  | 282.03 |  | 398 |  | 370.48 |  | 437.33 |  | 435 | ROW(P) | 406.62 |  |  | (P) | 440.63 |  | 410.34 |  | 444.33 | [7 empty] | 0 | 0 | 0
| DD+0 |  | DC+9 |  | DB+9 |  | DA+0 |  | DA+0 |  | DD+0 |  | DA+3 |  | DC+6 |  | DD+3 |  | DA+9 |  | DC+0 |  | DC+3 |  | DB+6 |  | DC+0
|  |  | 3MRC-4Leg |  | 3MRC-4Leg | [15 empty] | 1MRC-4Leg
WORK FRONT YET TO BE CLEARED | [15 empty] | WORK FRONT YET TO BE CLEARED
AP111 |  |  | AP112 |  | AP113 |  | AP 113A |  | AP114 |  | 114/1 |  | AP115 |  | 115/1 |  | AP116 |  | 116/1 |  | AP117 |  | 117/1 |  | 117/2 |  | AP118
|  | 189.81 |  | 157.88 | C(P) | 200.69 |  | 165.49 |  | 403.86 |  | 434.79 |  | 425.38 |  | 441.35 |  | 357.54 |  | 438.29 | (P) | 430 |  | 410 |  | 439.98 | (P) | 424.44 | [7 empty] | 0 | 0 | 0
| DB+9 |  | DC+9 |  | DD+0 |  | DC+0 |  | DC+0 |  | DA+9 |  | DC+0 |  | DB+9 |  | DD+0 |  | DA+0 |  | DD+0 |  | DA+3 |  | DB+9 |  | DC+3
| 3MRC | [11 empty] | 1MRC-4 Leg |  |  |  |  | Benching,LegB&C
[5 empty] | ROW | [15 empty] | ROW
AP119 |  |  | 119/1 |  | 119/2 |  | AP120 |  | 120/1 | AP121 |  | NH | AP122 |  | 122/1 |  | 122/2 |  | AP123 |  | AP124 |  | AP125 |  | 125/1 |  | 125/2
|  | 439 |  | 395 |  | 401.11 | ROW | 413 |  | 402.25 |  | 250.69 |  | 425.61 | (P) | 381.68 | (P) | 351.87 |  | 419.36 | (P) | 421.74 |  | 403 |  | 355 |  | 355 | [7 empty] | 0 | 1 | 0
| DD+3 |  | DA+3 |  | DA+3 |  | DC+0 |  | DA+6 |  | DD+0 |  | DC+6 |  | DA+3 |  | DA+3 |  | DC+0 |  | DC+3 |  | DC+3 |  | DA+0 |  | DA+0
[7 empty] | ROW | [6 empty] | WORK FRONT YET TO BE CLEARED | [5 empty] | WORK FRONT YET TO BE CLEARED
| 125/3 |  | AP126 |  | 126/1 |  | 126/2 |  | 126/3 |  | AP127 |  | 127/1 |  | AP128 |  | 128/1 |  | AP129 |  | 129/1 |  | 129/2 |  | AP130 |  | 130/1 | SH
|  | 373.771 |  | 364 |  | 421 |  | 334 | R | 388.22 | R | 398 | C(P) | 442.515 |  | 415 | (P) | 417.97 |  | 424 |  | 415 |  | 412.21 |  | 268 | (P) | 259.27 | [7 empty] | 0 | 0 | 0
| DA+0 |  | DC+6 |  | DA+6 |  | DA+3 |  | DA+6 |  | DD+6 |  | DA+9 |  | DC+3 |  | DA+6 |  | DC+0 |  | DA+3 |  | DA+9 |  | DC+6 |  | DA+0
[9 empty] | ROW | [7 empty] | ROW |  |  |  |  | 3MRC-4 Leg
| AP131 |  | 131/1 |  | 131/2 |  | AP132 |  | 132/1 |  | 132/2 |  | 132/3 |  | 132/4 |  | AP133 |  | 133/1 |  | 133/2 |  | 133/3 |  | 133/4 |  | 133/5
|  | 395 |  | 408 |  | 356 |  | 379 |  | 367 |  | 384 |  | 385 |  | 419.37 |  | 343.49 |  | 392.09 |  | 390.92 |  | 372.24 |  | 388.01 |  | 414.07 | [7 empty] | 0 | 0 | 0
| DD+0 |  | DA+3 |  | DA+3 |  | DD+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0
[17 empty] | A&D 3MRC |  |  |  | 1MRC-4 Leg
[7 empty] | ROW |  |  |  | ROW
| 133/6 |  | 133/7 |  | 133/8 |  | AP134 |  | 134A/0 |  | 134A/1 |  | 134A/2 |  | 134A/3 |  | 134A/4 |  | AP135 |  | 135/1 |  | 135/2 |  | 135/3 |  | AP136 |  | AP137
|  | 410.11 |  | 414.83 |  | 360.43 |  | 226.21 |  | 438.04 |  | 402.74 |  | 433.49 | U/P | 409.21 |  | 436.61 |  | 394.61 |  | 383.9 |  | 356.32 | U/P | 378.3 |  | 356.03 |  | 426.817 | [5 empty] | 2 | 0 | 0
| DA+3 |  | DA+0 |  | DA+6 |  | DD+0 |  | DD+0 |  | DA+9 |  | DA+3 |  | DA+6 |  | DA+9 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DD+0 |  | DB+3
ROW
| AP138 |  | 138/1 |  | 138/2 |  | 138/3 |  | AP139 |  | 139/1 |  | AP140 |  | 140/1 |  | 140/2 |  | 140/3 |  | AP141 |  | 141/1 |  | 141/2 |  | AP142
|  | 381 |  | 334 |  | 347 |  | 375.55 |  | 392 | R | 407.97 | (P) | 392 | R | 405 |  | 435 |  | 378.33 |  | 386 |  | 391 |  | 399.83 |  | 437.01 | [7 empty] | 0 | 0 | 0
| DB+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC+3 |  | DA+9 |  | DB+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DC+0 |  | DA+0 |  | DA+6 |  | DC+3
[9 empty] | 1MRC-4 Leg |  | ROW | [15 empty] | ROW
| AP143 |  | 143/1 |  | 143/2 |  | 143/3 |  | 143/4 |  | 143/5 |  | 143/6 |  | 143/7 |  | AP144 |  | AP145 |  | 145/1 |  | 145/2 |  | 145/3 |  | 145/4
|  | 401.76 |  | 416.24 |  | 417 |  | 399 |  | 420 |  | 409 |  | 412 |  | 400.41 |  | 232.12 |  | 442 |  | 385 |  | 362 |  | 399 |  | 382.07 | [7 empty] | 0 | 0 | 0
| DC+3 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DD+6 |  | DD+6 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+3
| AP146 |  | 146/1 |  | 146/2 |  | AP147 |  | 147/1 |  | 147/2 |  | 147/3 |  | 147/4 |  | 147/5 |  | 147/6 |  | 147/7 |  | 147/8 |  | 147/9 | SH | AP148
|  | 392 |  | 422 |  | 409.46 |  | 373.69 |  | 381.62 |  | 381.82 |  | 391.44 |  | 385.78 |  | 367.45 |  | 379.63 |  | 380.46 |  | 382.98 |  | 241.5 | ROW | 363.92 | [7 empty] | 0 | 1 | 0
| DC+0 |  | DA+3 |  | DA+0 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB+0
ROW
| 148/1 |  | 148/2 |  | 148/3 |  | 148/4 |  | 148/5 |  | 148/6 |  | 148/7 |  | AP149 |  | 149A/0 |  | AP149B/0 |  | 149B/1 |  | 149B/2 |  | 149B/3 |  | AP150 |  | AP151
|  | 359.14 |  | 384.88 |  | 381.91 |  | 397.15 |  | 387.13 |  | 392.12 |  | 364.62 |  | 188.37 |  | 395.54 |  | 425 |  | 407 |  | 433 | U/P | 489.23 | C | 290 |  | 419.403 | [5 empty] | 1 | 0 | 1
| DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DD+0 |  | DD+0 |  | DB+3 |  | DA+3 |  | DA+0 |  | DB+9 |  | DD+9 |  | DD+9
UNDER HOLD
| AP152 |  | AP153 |  | AP153A |  | AP154 |  | AP155 |  | AP156 |  | AP157 |  | GANTRY |  |  |  | 1 | Total Locations
[19 empty] | 2 | Completed Locations | [8 empty] | 0
[19 empty] | 3 | Work in Progress
|  | 242.63 | U/P | 342.727 |  | 389.221 |  | 220.253 |  | 241.312 |  | 214.902 |  | 113.742 |  |  |  |  | 4 | ROW Cleared Locations | [15 empty] | 1 | 0 | 0
[19 empty] | 5 | Not Cleared due to D/S & C/S Approval | [8 empty] | 0 | [6 empty] | 9 | 21 | 2
| DD+18 |  | DD+18 |  | DB+0 |  | DD+0 |  | DD+0 |  | DD+9 |  | DD+0 | [5 empty] | 6 | Hold Due to Major Crossing & Others | [15 empty] | U/P | ROW | CLEAR
|  |  | ROW | [5 empty] | UNDER HOLD | [9 empty] | 7 | ROW Not Cleared
R

## VC (hidden)
52
2026-04-24 11:21
Name of Contractor:M/S KEC INTERNATIONAL LIMITED
PROGRESS AT A GLANCE :
[18 empty] | Stringing WIP |  |  |  | Stringing Completed
Sl. No. |  | Activity |  |  | UoM |  | Total Qty |  |  | Completed Till Date |  |  | Balance | [15 empty] | River Crossing
1 |  | Detail survey |  |  | Kms. |  | 187.175 |  |  | 187.175 |  |  | 0 |  |  | Oil pipeline
2 |  | Check survey |  |  | Kms. |  | 187.175 |  |  | 169.168 |  |  | 18.007 |  |  | Gas pipeline
3 |  | Soil Investigation |  |  | Loc |  | 73 |  |  | 73 |  |  | 0
4 |  | Foundation |  |  | Loc |  | 495 |  |  | 79 |  |  | 416 | [12 empty] | Erection WIP
5 |  | Earthing |  |  | Nos. |  | 497 |  |  | 61 |  |  | 436 |  |  |  |  | Erection Comp |  |  | Span | [8 empty] | Railway Crossing
6 |  | Erection |  |  | Loc |  | 495 | [5 empty] | 495 |  |  |  |  | Earthing
7 |  | Tack Welding |  |  | Nos. |  | 405 | [5 empty] | 405
8 |  | Stringing(Paying out) |  |  | Kms. |  | 187.175 | [5 empty] | 187.175 | [9 empty] | Excavation
9 |  | Stringing (Final Sag) |  |  | Kms. |  | 187.175 | [5 empty] | 187.175 | [11 empty] | NH/SH |  | 66/132/ 220/400KV
| 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14
| GNT |  | AP1 |  | AP1A |  | AP2 |  | AP3 |  | 3/1 |  | 3/2 |  | 3/3 |  | AP4 |  | 4/1 |  | 4/2 |  | 4/3 |  | 4/4 |  | 4/5 |  |  |  | T | F | EA | ER | Length | TW
|  | 96.534 |  | 114.097 |  | 290.581 |  | 214.485 |  | 451.783 |  | 419.226 |  | 420.01 |  | 416.531 |  | 356.262 |  | 343.074 |  | 381.329 |  | 373.323 |  | 246.012 |  | 249.424 |  |  | 13
|  |  | DD+0 |  | DD+3 |  | DD+25 |  | DD+25 |  | DB+6 |  | DA+0 |  | DA+9 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+6 |  | DA+3 |  | DB+0
| 4/6 |  | 4/7 |  | 4/8 |  | 4/9 |  | AP5 |  | AP6 |  | 6/1 |  | 6/2 |  | 6/3 |  | 6/4 |  | 6/5 |  | 6/6 |  | 6/7 |  | AP7
[31 empty] | T | F | EA | ER | Length | TW
|  | 399.707 |  | 438.616 |  | 400.604 |  | 438.765 |  | 226.315 |  | 442.553 |  | 389.329 |  | 359.361 |  | 405.006 |  | 426.518 |  | 356.055 |  | 369.295 |  | 374.993 |  | 383.768 |  |  | 14
| DA+0 |  | DA+6 |  | DA+6 |  | DA+3 |  | DD+18 |  | DD+18 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB+0
| 7/1 |  | 7/1 |  | 7/2 |  | 7/3 |  | 7/4 |  | 7/5 |  | 7/6 |  | 7/7 |  | 7/8 |  | 7/9 |  | 7/10 |  | AP8 |  | 8/1 |  | 8/2
[31 empty] | T | F | EA | ER | Length | TW
|  | 383.768 |  | 396.38 |  | 392.534 |  | 332.162 |  | 352.112 |  | 389.393 |  | 374.477 |  | 419.977 |  | 387.899 |  | 407.654 |  | 402.357 |  | 372.259 |  | 410.949 |  | 379.075 |  |  | 14
| DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DB+0 |  | DA+0 |  | DA+0
| 8/3 |  | 8/4 |  | AP9 |  | 9/1 |  | 9/2 |  | 9/3 |  | 9/4 |  | 9/5 |  | AP10 |  | 10/1 |  | 10/2 |  | 10/3 |  | 10/4 |  | 10/5
[31 empty] | T | F | EA | ER | Length | TW
|  | 412.596 |  | 340.112 |  | 410.76 |  | 427.9 |  | 404.21 |  | 398.446 |  | 431.939 |  | 486.196 |  | 369.717 |  | 389.344 |  | 395.602 |  | 372.377 |  | 431.547 |  | 370.651 |  |  | 14
| DA+0 |  | DA+3 |  | DB+0 |  | DA+0 |  | DA+6 |  | DA+0 |  | DA+3 |  | DB+9 |  | DC+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+6 |  | DA+0
| 10/6 |  | 10/7 |  | 10/8 |  | 10/9 |  | 10/10 |  | 10/11 |  | 10/12 |  | 10/13 |  | 10/14 |  | 10/15 |  | AP11 |  | 11/1 |  | 11/2 |  | 11/3
[31 empty] | T | F | EA | ER | Length | TW
|  | 345.352 |  | 381.912 |  | 366.819 |  | 424.002 |  | 400.126 |  | 403.795 |  | 437.705 |  | 399.87 |  | 437.786 |  | 378.362 |  | 433.995 |  | 370.685 |  | 323.972 |  | 384.462 |  |  | 14
| DA+0 |  | DA+0 |  | DA+0 |  | DB+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+6 |  | DB+0 |  | DA+3 |  | DA+0 |  | DA+0
| 11/4 |  | 11/5 |  | 11/6 |  | AP12 |  | 12/1 |  | 12/2 |  | AP13 |  | 13/1 |  | 13/2 |  | 13/3 |  | AP14 |  | 14/1 |  | AP15 |  | 15/1
[31 empty] | T | F | EA | ER | Length | TW
|  | 381.188 |  | 336.409 |  | 438.97 |  | 395.179 |  | 388.12 |  | 364.446 |  | 404.572 |  | 432.27 |  | 404.23 |  | 416.621 |  | 468.039 |  | 432.318 |  | 464.521 |  | 369.743 |  |  | 14
| DA+0 |  | DA+0 |  | DA+0 |  | DB+0 |  | DA+0 |  | DA+3 |  | DC+0 |  | DA+9 |  | DA+6 |  | DA+3 |  | DB+0 |  | DB+9 |  | DC+9 |  | DA+6
| AP16 |  | 16/1 |  | AP17 |  | 17/1 |  | AP18 |  | 18/1 |  | AP19 |  | 19/1 |  | 19/2 |  | 19/3 |  | AP20 |  | 20/1 |  | 20/2 |  | 20/3
[31 empty] | T | F | EA | ER | Length | TW
|  | 284.16 |  | 270.742 |  | 286.64 |  | 291.699 |  | 398.719 |  | 425.465 |  | 383.813 |  | 403.279 |  | 355.215 |  | 399.839 |  | 287.442 |  | 390.748 |  | 364.274 |  | 337.546 |  |  | 14
| DD+0 |  | DA+0 |  | DB+0 |  | DA+0 |  | DC+0 |  | DA+6 |  | DD+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+0
| 20/4 |  | 20/5 |  | 20/6 |  | AP21 |  | 21/1 |  | 21/2 |  | AP22 |  | AP23 |  | 23/1 |  | 23/2 |  | 23/3 |  | AP24 |  | 24/1 |  | AP25
[31 empty] | T | F | EA | ER | Length | TW
|  | 348.292 |  | 418.835 |  | 408.963 |  | 365.467 |  | 437.074 |  | 363.142 |  | 159.789 |  | 300.158 |  | 293.131 |  | 357.377 |  | 341.409 |  | 362.905 |  | 421.052 |  | 216.448 |  |  | 14
| DA+0 |  | DA+3 |  | DA+9 |  | DD+3 |  | DA+0 |  | DA+6 |  | DB+3 |  | DD+0 |  | DB+3 |  | DA+0 |  | DA+0 |  | DC+9 |  | DA+9 |  | DD+30
| AP26 |  | AP27 |  | AP27A |  | 27A/1 |  | 27A/2 |  | 27A/3 |  | AP27B |  | 27B/1 |  | 27B/2 |  | 27B/3 |  | AP28 |  | 28/1 |  | 28/2 |  | AP29
[31 empty] | T | F | EA | ER | Length | TW
|  | 439.695 |  | 243.188 |  | 333.219 |  | 363.001 |  | 356.124 |  | 511.692 |  | 376.245 |  | 381.122 |  | 364.433 |  | 263.077 |  | 356.193 |  | 352.42 |  | 460.564 |  | 381.028 |  |  | 14
| DD+30 |  | DC+0 |  | DD+0 |  | DA+3 |  | DA+3 |  | DB+0 |  | DB+0 |  | DA+0 |  | DA+3 |  | DA+9 |  | DD+6 |  | DA+0 |  | DB+9 |  | DC+6
| 29/1 |  | 29/2 |  | AP30 |  | 30/1 |  | 30/2 |  | 30/3 |  | AP31 |  | AP32 |  | 32/1 |  | 32/2 |  | 32/3 |  | AP33 |  | AP34 |  | 34/1
[31 empty] | T | F | EA | ER | Length | TW
|  | 419.603 |  | 425.18 |  | 287.537 |  | 336.512 |  | 325.304 |  | 214.253 |  | 455.946 |  | 421 |  | 419 |  | 408 |  | 409.749 |  | 324.03 |  | 366.7 |  | 473.305 |  |  | 14
| DA+3 |  | DA+9 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC+9 |  | DC+9 |  | DA+3 |  | DA+3 |  | DA+9 |  | DB+0 |  | DC+6 |  | DA+9
| AP35 |  | 35/1 |  | AP36 |  | 36/1 |  | 36/2 |  | 36A |  | AP37 |  | 37/1 |  | AP38 |  | 38/1 |  | 38/2 |  | 38/3 |  | AP39 |  | 39/1 |  | 39/2
[31 empty] | T | F | EA | ER | Length | TW
|  | 358.321 |  | 477.815 |  | 415.464 |  | 402.229 |  | 437.434 |  |  |  | 455.922 |  | 368.5 |  | 419.765 |  | 418.917 |  | 386.486 |  | 376.53 |  | 404.739 |  | 366.729 |  | 274.587 | 14
| DC+9 |  | DA+9 |  | DC+9 |  | DA+9 |  | DA+9 |  | DD+0 |  | DD+0 |  | DA+6 |  | DB+0 |  | DA+6 |  | DA+9 |  | DA+3 |  | DB+3 |  | DA+6 |  | DA+0
| 39/3 |  | 39/4 |  | 39/5 |  | AP40 |  | 40/1 |  | 40/2 |  | AP41 |  | 41/1 |  | 41/2 |  | 41/3 |  | AP42 |  | 42/1 |  | 42/2 |  | 42/3
[31 empty] | T | F | EA | ER | Length | TW
|  | 341.668 |  | 425.863 |  | 394.307 |  | 370.45 |  | 436.754 |  | 397.605 |  | 413.401 |  | 423.645 |  | 415.968 |  | 415.349 |  | 394.875 |  | 429.62 |  | 381.905 |  | 405.26 |  |  | 14
| DA+0 |  | DA+0 |  | DA+6 |  | DD+3 |  | DB+6 |  | DA+6 |  | DB+0 |  | DA+9 |  | DA+0 |  | DA+9 |  | DC+3 |  | DA+9 |  | DCT+6 |  | DA+9
| 42/4 |  | 42/5 |  | 42/6 |  | 42/7 |  | AP43 |  | AP44 |  | 44/1 |  | AP45 |  | 45/1 |  | 45/2 |  | 45/3 |  | 45/4 |  | AP46 |  | AP47
[31 empty] | T | F | EA | ER | Length | TW
s
|  | 338.156 |  | 288.303 |  | 297.148 |  | 195.903 |  | 249.66 |  | 374.475 |  | 443.95 |  | 404.386 |  | 341.423 |  | 305.401 |  | 319.981 |  | 345.621 |  | 223.151 |  | 393.817 |  |  | 14
| DA+9 |  | DA+0 |  | DA+3 |  | DA+0 |  | DC+6 |  | DB+9 |  | DA+9 |  | DD+9 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+6 |  | DD+3 |  | DD+9
| 47/1 |  | 47/2 |  | AP48 |  | AP49 |  | AP50 |  | AP51 |  | 51/1 |  | 51/2 |  | 51/3 |  | AP52 |  | 52/1 |  | AP53 |  | AP54 |  | 54/1
[31 empty] | T | F | EA | ER | Length | TW
|  | 435.136 |  | 403.209 |  | 422.554 |  | 353.484 |  | 274.899 |  | 465.033 |  | 373.977 |  | 416.864 |  | 381.019 |  | 391.519 |  | 374.934 |  | 248.567 |  | 384.17 |  | 330.764 |  |  | 14 | 1
| DA+9 |  | DA+9 |  | DD+3 |  | DD+3 |  | DD+9 |  | DD+18 |  | DA+3 |  | DA+0 |  | DA+3 |  | DB+0 |  | DA+6 |  | DD+0 |  | DC+0 |  | DA+3
[19 empty] | RC 3M |  | RC 1M
| 54/2 |  | 54/3 |  | AP55 |  | AP56 |  | 56/1 |  | 56/2 |  | 56/3 |  | 56/4 |  | 56/5 |  | AP57 |  | AP58 |  | AP59 |  | 59/1 |  | AP60
[31 empty] | T | F | EA | ER | Length | TW
|  | 285.319 |  | 354.7 |  | 420.541 |  | 340.559 |  | 336.519 |  | 375.992 |  | 308.407 |  | 444.838 |  | 392.016 |  | 407.803 |  | 206.062 |  | 417.384 |  | 304.564 |  | 395.509 |  |  | 14
| DA+6 |  | DA+3 |  | DD+18 |  | DB+9 |  | DB+9 |  | DA+0 |  | DB+9 |  | DA+6 |  | DA+6 |  | DB+9 |  | DB+9 |  | DC+9 |  | DA+0 |  | DD+0
| RC 1M |  | RC 1M |  | RC 3M |  | RC 3M | [11 empty] | RC 1M & 3M
| 60/1 |  | 60/2 |  | 60/3 |  | AP61 |  | 61/1 |  | AP62 |  | 62/1 |  | 62/2 |  | 62/3 |  | 62/4 |  | 62/5 |  | AP63 |  | 63/1 |  | AP64
[31 empty] | T | F | EA | ER | Length | TW
|  | 431.017 |  | 403.426 |  | 420.357 |  | 446.37 |  | 297.577 |  | 240.473 |  | 312.687 |  | 347.884 |  | 379.249 |  | 398.697 |  | 439.062 |  | 360.21 |  | 399.579 |  | 364 |  |  | 14
| DA+9 |  | DA+3 |  | DA+9 |  | DC+0 |  | DA+9 |  | DB+0 |  | DA+0 |  | DA+0 |  | DA+9 |  | DA+6 |  | DA+6 |  | DC+0 |  | DA+0 |  | DC+9
[5 empty] | RC 3M | [7 empty] | RC 1M |  |  |  | RC 3M | [9 empty] | RC 1M
| 64/1 |  | 64/2 |  | 64/3 |  | 64/4 |  | 64/5 |  | 64/6 |  | 64/7 |  | AP65 |  | 65/1 |  | AP66 |  | 66/1 |  | 66/2 |  | 66/3 |  | 66/4
[31 empty] | T | F | EA | ER | Length | TW
|  | 442 |  | 397 |  | 395 |  | 432 |  | 408 |  | 426 |  | 392.954 |  | 431.957 |  | 426.02 |  | 401 |  | 437 |  | 402 |  | 436 |  | 392.283 |  |  | 14 | 8 | 2
| DA+9 |  | DA+9 |  | DA+9 |  | DA+9 |  | DA+9 |  | DA+3 |  | DA+3 |  | DD+0 |  | DB+9 |  | DD+0 |  | DA+9 |  | DA+0 |  | DA+3 |  | DA+9
| RC 3M |  | RC 1M | [15 empty] | RC 1M
| AP67 |  | 67/1 |  | 67/2 |  | AP68 |  | AP69 |  | 69/1 |  | 69/2 |  | 69/3 |  | AP70 |  | AP71 |  | 71/1 |  | 71/2 |  | 71/3 |  | AP72
[31 empty] | T | F | EA | ER | Length | TW
|  | 402.5 |  | 411.557 |  | 438.461 |  | 410.356 |  | 379.755 |  | 396.947 |  | 414.594 |  | 352.994 |  | 389.303 |  | 237.59 |  | 290.877 |  | 345.605 |  | 318.63 |  | 307.017 |  |  | 14
| DC+6 |  | DA+6 |  | DB+0 |  | DB+9 |  | DD+3 |  | DA+6 |  | DA+0 |  | DA+0 |  | DD+0 |  | DB+0 |  | DA+9 |  | DA+0 |  | DA+0 |  | DD+0
| RC 1M | [13 empty] | RC 1M | [9 empty] | RC 1M |  | RC 1M & 3M
| 72/1 |  | 72/2 |  | AP73 |  | 73/1 |  | 73/2 |  | 73/3 |  | AP74 |  | 74/1 |  | AP75 |  | 75/1 |  | 75/2 |  | 75/3 |  | 75/4 |  | 75/5
[31 empty] | T | F | EA | ER | Length | TW
|  | 346.846 | u/p | 300.193 | u/p | 317 |  | 454 |  | 385 |  | 417.688 |  | 409.505 |  | 385.169 |  | 345.191 |  | 332.383 |  | 393.622 |  | 387.948 |  | 340.348 |  | 393.121 |  |  | 14 | 8 | 7
| DA+3 |  | DA+3 |  | DB+0 |  | DA+0 |  | DA+9 |  | DA+9 |  | DB+9 |  | DA+0 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0
| RC 1M & 3M | [5 empty] | RC 3M
| 75/6 |  | 75/7 |  | AP76 |  | 76/1 |  | AP77 |  | 77/1 |  | 77/2 |  | 77/3 |  | 77/4 |  | 77/5 |  | AP78 |  | 78/1 |  | AP79 |  | 79/1
[31 empty] | T | F | EA | ER | Length | TW
|  | 328.536 |  | 398.515 |  | 425.848 |  | 409.369 |  | 388.455 |  | 380.961 |  | 381.389 |  | 344.595 |  | 395.641 |  | 414.763 |  | 401.929 |  | 354.949 |  | 425 |  | 414 |  |  | 14 | 9 | 9
| DA+0 |  | DA+0 |  | DC+0 |  | DA+6 |  | DB+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+6 |  | DC+0 |  | DA+3 |  | DD+0 |  | DA+9
RC 1M
| 79/2 |  | AP80 |  | 80/1 |  | AP81 |  | 81/1 |  | 81/2 |  | 81/3 |  | 81/4 |  | 81/5 |  | AP82 |  | 82/1 |  | 82/2 |  | AP83 |  | 83/1
[31 empty] | T | F | EA | ER | Length | TW
|  | 353.052 |  | 441.055 |  | 387.495 |  | 372.627 |  | 415.304 |  | 424.584 |  | 391.704 |  | 410.466 |  | 385.541 |  | 418.313 |  | 421.473 |  | 401.979 | ROW | 429.379 |  | 403.832 |  |  | 14 | 2 | 2
| DA+0 |  | DB+3 |  | DA+9 |  | DB+9 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+6 |  | DB+3 |  | DA+6 |  | DA+0 |  | DC+0 |  | DA+3
| RC 1M |  | RC 1M | [5 empty] | RC 3M
| AP84 |  | AP85 |  | 85/1 |  | AP86 |  | 86/1 |  | 86/2 |  | AP87 |  | 87/1 |  | 87/2 |  | AP88 |  | AP89 |  | 89/1 |  | AP90 |  | 90/1
[31 empty] | T | F | EA | ER | Length | TW
|  | 384.63 |  | 380.682 |  | 354.526 | u/p | 405.574 |  | 416.874 |  | 380.766 |  | 411.814 |  | 392.08 |  | 296.873 |  | 412.399 |  | 382.173 |  | 452.737 |  | 420.207 |  | 395.011 |  |  | 14 | 5
| ROW |  | ROW
| DC+6 |  | DC+0 |  | DA+0 |  | DD+0 |  | DA+6 |  | DA+0 |  | DC+0 |  | DA+3 |  | DA+9 |  | DC+0 |  | DC+0 |  | DA+9 |  | DC+0 |  | DA+9
| AP91 |  | 91/1 |  | 91/2 |  | 91/3 |  | AP92 |  | AP93 |  | AP94 |  | AP95 |  | 95/1 |  | 95/2 |  | AP95A |  | 95A/1 |  | AP96 |  | 96/1
[31 empty] | T | F | EA | ER | Length | TW
|  | 386.735 |  | 378.624 |  | 350.215 |  | 357.906 |  | 237.476 |  | 440.03 |  | 503.74 | u/p | 437 | U/P | 430 |  | 409.273 |  | 312.446 |  | 314.247 |  | 361.96 |  | 329.486 |  |  | 14 | 2 | 2
| DD+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC+0 |  | DC+0 |  | DB+6 |  | DB+6 |  | DB+0 |  | DA+9 |  | DB+0 |  | DA+0 |  | DC+0 |  | DA+0
| 96/2 |  | AP97 |  | 97/1 |  | AP98 |  | 98/1 |  | AP98A |  | 98A/1 |  | AP98B |  | 98B/1 |  | 98B/2 |  | AP99 |  | 99/1 |  | 99/2 |  | 99/3
[31 empty] | T | F | EA | ER | Length | TW
|  | 371.327 |  | 417.917 |  | 376.988 | U/P | 343.797 |  | 318.696 |  | 308 |  | 324.874 | U/P | 365.391 |  | 269.525 |  | 350.326 |  | 414 |  | 424 |  | 405 |  | 426 |  |  | 14 | 4 | 2
[7 empty] | ROW | [7 empty] | ROW
| DA+0 |  | DC+0 |  | DA+3 |  | DC+0 |  | DA+0 |  | DC+0 |  | DA+0 |  | DD+0 |  | DA+0 |  | DCT+0 |  | DC+0 |  | DA+6 |  | DA+0 |  | DA+3
[5 empty] | RC 1M | [11 empty] | RC 1M | [9 empty] | RC 3M
| 99/4 |  | 99A/0 |  | 99B/0 |  | AP99C/0 |  | 99C/1 |  | 99C/2 |  | AP100 |  | 100/1 |  | AP101 |  | AP102 |  | 102/1 |  | 102/2 |  | AP103 |  | 103/1
[31 empty] | T | F | EA | ER | Length | TW
|  | 410 |  | 421 |  | 407.607 |  | 364.364 |  | 332.448 |  | 348.853 |  | 387.348 |  | 452.637 |  | 386.957 |  | 382.143 |  | 336.469 |  | 389.14 |  | 334.554 |  | 396.198 |  |  | 14
| DA+3 |  | DB+6 |  | DD+0 |  | DD+0 |  | DA+6 |  | DA+3 |  | DC+0 |  | DA+6 |  | DD+0 |  | DD+3 |  | DA+0 |  | DA+0 |  | DC+0 |  | DA+6
| AP104 |  | AP104A |  | AP104B |  | 104B/1 |  | 104B/2 |  | AP105 |  | 105/1 |  | AP106 |  | AP107 |  | 107/1 |  | AP108 |  | AP109 |  | AP109A |  | AP110
[31 empty] | T | F | EA | ER | Length | TW
|  | 233.292 |  | 467.189 |  | 423.018 |  | 248.691 |  | 282.025 |  | 398 |  | 370.48 | u/p | 437.333 |  | 435 |  | 406.615 |  | 388.494 |  | 440.626 |  | 410.342 |  | 444.331 |  |  | 14
| DD+0 |  | DC+9 |  | DB+9 |  | DA+0 |  | DA+0 |  | DD+0 |  | DA+3 |  | DC+6 |  | DD+3 |  | DA+9 |  | DC+0 |  | DC+3 |  | DB+6 |  | DC+0
|  |  | RC 3M |  | RC 3M | [15 empty] | RC 1M
| AP111 |  | AP112 |  | AP113 |  | AP113A |  | AP114 |  | 114/1 |  | AP115 |  | 115/1 |  | AP116 |  | 116/1 |  | AP117 |  | 117/1 |  | 117/2 |  | AP118
[31 empty] | T | F | EA | ER | Length | TW
|  | 189.805 |  | 157.883 |  | 200.685 |  | 165.49 | U/P | 403.859 |  | 434.788 |  | 425.384 |  | 441.345 |  | 357.543 |  | 438.293 |  | 430 |  | 410 |  | 439.976 |  | 424.44 |  |  | 14
| DB+9 |  | DC+9 |  | DD+0 |  | DC+0 |  | DC+0 |  | DA+9 |  | DC+0 |  | DB+9 |  | DD+0 |  | DA+0 |  | DD+0 |  | DA+3 |  | DB+9 |  | DC+3
| RC 3M |  | RC 3M | [9 empty] | RC 1M
| AP119 |  | 119/1 |  | 119/2 |  | AP120 |  | 120/1 |  | AP121 |  | AP122 |  | 122/1 |  | 122/2 |  | AP123 |  | AP124 |  | AP125 |  | 125/1 |  | 125/2
T
|  | 439 |  | 395 |  | 401.113 |  | 413 |  | 402.253 |  | 250.694 |  | 425.612 |  | 381.675 |  | 351.869 |  | 419.361 |  | 421.739 |  | 403 |  | 355 |  | 355 |  |  | 14
| DD+3 |  | DA+3 |  | DA+3 |  | DC+0 |  | DA+6 |  | DD+0 |  | DC+6 |  | DA+3 |  | DA+3 |  | DC+0 |  | DC+3 |  | DC+3 |  | DA+0 |  | DA+0
| 125/3 |  | AP126 |  | 126/1 |  | 126/2 |  | 126/3 |  | AP127 |  | 127/1 |  | AP128 |  | 128/1 |  | AP129 |  | 129/1 |  | 129/2 |  | AP130 |  | 130/1
[31 empty] | T | F | EA | ER | Length | TW
|  | 373.771 |  | 364 |  | 421 |  | 334 |  | 388.22 |  | 398 |  | 442.515 |  | 415 |  | 417.968 |  | 424 |  | 415 |  | 412.205 |  | 278 |  | 249.272 |  |  | 14
| DA+0 |  | DC+0 |  | DA+6 |  | DA+3 |  | DA+6 |  | DD+6 |  | DA+9 |  | DC+3 |  | DA+6 |  | DC+0 |  | DA+3 |  | DA+9 |  | DC+6 |  | DA+0
| AP131 |  | 131/1 |  | 131/2 |  | AP132 |  | 132/1 |  | 132/2 |  | 132/3 |  | 132/4 |  | AP133 |  | 133/1 |  | 133/2 |  | 133/3 |  | 133/4 |  | 133/5
T
|  | 395 |  | 408 |  | 352.002 |  | 373.572 |  | 367 |  | 384 |  | 385 |  | 419.368 |  | 288 |  | 404 |  | 413 |  | 414 |  | 414 |  | 425 |  |  | 14
| DD+0 |  | DA+3 |  | DA+3 |  | DD+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0
1MRC
| 133/6 |  | 133/7 |  | 133/8 |  | AP134 |  | 134A/0 |  | 134A/1 |  | 134A/2 |  | 134A/3 |  | 134A/4 |  | AP135 |  | 135/1 |  | 135/2 |  | 135/3 |  | AP136 |  | AP137
[31 empty] | T | F | EA | ER | Length | TW
|  | 410.108 |  | 414.825 |  | 360.431 |  | 226 |  | 438.037 |  | 402.737 |  | 433.49 |  | 409.206 |  | 436.605 |  | 394.613 |  | 383.901 |  | 356.322 |  | 378.301 |  | 356.028 |  |  | 14
| DA+3 |  | DA+0 |  | DA+6 |  | DD+0 |  | DD+0 |  | DA+9 |  | DA+3 |  | DA+6 |  | DA+9 |  | DC+0 |  | DA+0 |  | DA+3 |  | DA+6 |  | DD+0 |  | DB+3
| AP138 |  | 138/1 |  | 138/2 |  | 138/3 |  | AP139 |  | 139/1 |  | AP140 |  | 140/1 |  | 140/2 |  | 140/3 |  | AP141 |  | 141/1 |  | 141/2 |  | AP142
T
|  | 381 |  | 334 |  | 347 |  | 375.546 |  | 392 |  | 407.974 |  | 392 |  | 405 |  | 435 |  | 378.328 |  | 386 |  | 391 |  | 399.827 |  | 437.008 |  |  | 14
| DB+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC+3 |  | DA+9 |  | DB+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DC+0 |  | DA+0 |  | DA+6 |  | DC+3
| AP143 |  | 143/1 |  | 143/2 |  | 143/3 |  | 143/4 |  | 143/5 |  | 143/6 |  | 143/7 |  | AP144 |  | AP145 |  | 145/1 |  | 145/2 |  | 145/3 |  | 145/4
T
|  | 401.757 |  | 416.243 |  | 417 |  | 399 |  | 420 |  | 409 |  | 412 |  | 400.406 |  | 232.123 |  | 442 |  | 385 |  | 362 |  | 399 |  | 382.072 |  |  | 14
| DC+3 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DD+6 |  | DD+6 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+3
| AP146 |  | 146/1 |  | 146/2 |  | AP147 |  | 147/1 |  | 147/2 |  | 147/3 |  | 147/4 |  | 147/5 |  | 147/6 |  | 147/7 |  | 147/8 |  | 147/9 |  | AP148
T
|  | 392 | u/p | 422 |  | 409.457 |  | 373.694 |  | 381.617 |  | 381.822 |  | 391.436 |  | 385.784 |  | 367.452 |  | 379.63 |  | 380.459 | U/P | 382.979 |  | 241.496 |  | 403 |  |  | 14
| DC+0 |  | DA+3 |  | DA+0 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB+0
| 148/1 |  | 148/2 |  | 148/3 |  | 148/4 |  | 148/5 |  | 148/6 |  | 148/7 |  | AP149 |  | 149A/0 |  | AP149B/0 |  | 149B/1 |  | 149B/2 |  | 149B/3 |  | AP150 |  | AP151
T
|  | 359.142 |  | 384.878 |  | 381.905 |  | 397.152 |  | 387.131 |  | 392.124 |  | 364.623 |  | 188.369 |  | 396 |  | 425 |  | 407 |  | 433 |  | 489.23 |  | 419.403 |  |  | 14
| DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DD+0 |  | DD+0 |  | DB+3 |  | DA+3 |  | DA+0 |  | DB+9 |  | DD+9 |  | DD+9
| AP152 |  | AP153 |  | AP153A |  | AP154 |  | AP155 |  | AP156 |  | AP157 |  | GNT
T
|  | 242.63 |  | 342.727 |  | 389.221 |  | 220.253 |  | 241.312 |  | 214.902 |  | 113.742 | [16 empty] | 7
| DD+18 |  | DD+18 |  | DB+6 |  | DD+30 |  | DD+30 |  | DD+9 |  | DD+0
T
[31 empty] | 496 | 39 | 24

## Sheet6 (hidden)
SL No | Loc No | TOT | Classificatin | M-10 | M-20
1 | 83/1 | DA+3 | Sandy | 1.86 | 12.47
2 | 75/7 | DA+0 | Sandy | 1.57 | 11.05
3 | 75/6 | DA+0 | Sandy | 1.57 | 11.05
4 | 75/5 | DA+0 | Sandy | 1.57 | 11.05
5 | 75/4 | DA+0 | Sandy | 1.57 | 11.05
6 | 75/3 | DA+3 | Sandy | 1.86 | 12.47
7 | 75/1 | DA+0 | Sandy | 1.57 | 11.05
8 | 75/2 | DA+0 | Sandy | 1.57 | 11.05
9 | 77/1 | DA+0 | Sandy | 1.57 | 11.05
10 | 77/2 | DA+3 | Sandy | 1.86 | 12.47
11 | 77/3 | DA+0 | Sandy | 1.57 | 11.05
12 | 77/4 | DA+3 | Sandy | 1.86 | 12.47
13 | 77/5 | DA+6 | Sandy | 1.86 | 12.47
14 | 73/3 | DA+9 | Sandy | 1.86 | 12.47
15 | 86/2 | DA+0 | Sandy | 1.57 | 11.05
16 | 79/1 | DA+9 | Sandy | 1.86 | 12.47
17 | 95A/1 | DA+0 | DFR | 1.08 | 8.68
18 | 73/2 | DA+9 | Sandy | 1.86 | 12.47
19 | 66/1 | DA+9 | Sandy | 1.86 | 12.47
20 | 80/1 | DA+9 | Sandy | 1.86 | 12.47
21 | 86/1 | DA+6 | Sandy | 1.86 | 12.47
22 | 76/1 | DA+6 | Sandy | 1.86 | 12.47
23 | 74/1 | DA+0 | Sandy | 1.57 | 11.05
24 | 96/1 | DA+0 | Sandy | 1.57 | 11.05
25 | 99/1 | DA+6 | Sandy | 1.86 | 12.47
26 | 66/2 | DA+0 | Sandy | 1.57 | 11.05
27 | 96/2 | DA+0 | Sandy | 1.57 | 11.05
28 | 81/2 | DA+3 | Sandy | 1.86 | 12.47
29 | 64/3 | DA+9 | Sandy | 1.86 | 12.47
30 | 66/3 | DA+9 | Sandy | 1.86 | 12.47
31 | 64/4 | DA+9 | Sandy | 1.86 | 12.47
32 | 85/1 | DA+0 | Sandy | 1.57 | 11.05
33 | 87/1 | DA+3 | Sandy | 1.86 | 12.47
34 | 64/7 | DA+3 | Sandy | 1.86 | 12.47
35 | 98A/1 | DA+0 | DFR | 1.08 | 8.68 |  | ]]
36 | 87/2 | DA+9 | Sandy | 1.86 | 12.47
37 | 64/6 | DA+3 | Sandy | 1.86 | 12.47
38 | 64/5 | DA+9 | Sandy | 1.86 | 12.47
|  |  |  | 65.06 | 446.4 | 511.46

## VC 51-121 (hidden)
TB-507 400 KV (Twin) D/C Fatehgarh IV - Bhinmal Transmission Line
DPR and VISUAL CHART
DPR- |  |  | As per Approved Check Survey |  | No.Of Towers | Length | Foundation |  |  | Earthing | Tower Erection |  |  | Stringing
[7 empty] | Com | WIP | Bal | Com | Com | WIP | Bal | Com | WIP | Bal
|  |  | AP 51- AP 121 |  | 196 | 74.398 | 39 | 4 | 153 | 25 |  |  | 196 |  |  | 74.398
|  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9
[23 empty] | DA |  |  |  |  | DB |  |  |  |  | DC |  |  |  |  | DD
|  |  | 465.03 |  | 375.98 |  | 414.86 |  | 381.02 |  | 353.63 |  | 351.4 |  | 433.26 |  | 396.56 |  | 408.11 | 3579.85 |  | +0 | +3 | +6 | +9 |  | +0 | +3 | +6 | +9 |  | +0 | +3 | +6 | +9 |  | +0 | +3 | +6 | +9
[6 empty] | U/P | [15 empty] | 1 | 3 | 1 | 0 |  | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
|  | AP51 |  | 51/1 |  | 51/2 |  | 51/3 |  | AP52 |  | 52/1 |  | AP53 |  | AP54 |  | 54/1
|  | DD+18 |  | DA+3 |  | DA+0 |  | DA+3 |  | DB+0 |  | DA+6 |  | DD+0 |  | DC+00 |  | DA+3
[10 empty] | RC |  | RC
| 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19
|  | 425.22 |  | 420.54 |  | 340.56 |  | 336.52 |  | 375.99 |  | 303.41 |  | 448.76 |  | 393.09 |  | 407.8 |  | 206.06 | 3657.95
| 54/2 |  | 54/3 |  | AP55 |  | AP56 |  | 56/1 |  | 56/2 |  | 56/3 |  | 56/4 |  | 56/5 |  | AP57 |  |  | 1 | 1 | 3 | 0 |  | 0 | 0 | 0 | 2 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| DA+6 |  | DA+3 |  | DD+18 |  | DB+09 |  | DB+9 |  | DA+0 |  | DB+9 |  | DA+6 |  | DA+6 |  | DB+09
| Benching &RC |  | RC |  | RC |  | Benching &RC | [11 empty] | Benching &RC
| 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29
|  | 417.38 |  | 304.56 |  | 408.66 |  | 434.89 |  | 408.17 |  | 398.59 |  | 446.37 |  | 297.58 |  | 240.47 |  | 312.69 | 3669.36
| AP58 |  | AP59 |  | 59/1 |  | AP60 |  | 60/1 |  | 60/2 |  | 60/3 |  | AP61 |  | 61/1 |  | AP62
| DB+09 |  | DC+09 |  | DA+0 |  | DD+00 |  | DA+9 |  | DA+0 |  | DA+9 |  | DC+00 |  | DA+9 |  | DB+00 |  |  | 2 | 0 | 0 | 3 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[5 empty] | Benching | [7 empty] | RC
| 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39
|  | 347.88 |  | 379.25 |  | 398.7 |  | 439.06 |  | 381.53 |  | 379.71 |  | 426.3 |  | 387.14 |  |  |  | 423.77 | #REF!
| 62/1 |  | 62/2 |  | 62/3 |  | 62/4 |  | 62/5 |  | AP63 |  | 63/1 |  | AP64 |  | 64/1 |  | 64/2
| DA+0 |  | DA+0 |  | DA+9 |  | DA+6 |  | DA+6 |  | DC+00 |  | DA+0 |  | DC+09 |  | DA+9 |  | DA+9 |  |  | 3 | 0 | 2 | 3 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| RC |  |  |  | RC | [9 empty] | Benching &RC |  | RC |  | RC
| 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49
|  | 407.9 |  | 426.63 |  | 392.27 |  | 431.96 |  | 426.02 |  | 405.36 |  | 411.93 |  | 423.77 |  | 407.9 |  | 426.63
| F |  | F |  | F |  | F |  | F | [7 empty] | F |  | F
| Er |  |  |  | Er
| 64/3 |  | 64/4 |  | 64/5 |  | 64/6 |  | 64/7 |  | 65/0 |  | 65/1 |  | 66/0 |  | 66/1 |  | 66/2
| DA+9 |  | DA+9 |  | DA+9 |  | DA+3 |  | DA+3 |  | DD+0 |  | DB+09 |  | DD+0 |  | DA+9 |  | DA+0 |  | #REF! | 1 | 3 | 1 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 2 | 0 | 0 | 0
RC
| 50 |  | 51 |  | 52 |  | 53 |  | 54 |  | 55 |  | 56 |  | 57 |  | 58 |  | 59 |  | 60
|  | 392.27 |  | 431.96 |  | 426.02 |  | 405.36 |  | 411.93 |  | 350.33 |  | 378.3 |  | 416.82 |  | 371.85
| F |  | ROW
| 66/3 |  | 66/4 |  | 67/0 |  | 67/1 |  | 67/2 |  | AP68 |  | AP69 |  | 69/1 |  | 69/2 |  | 69/3 |  | 70/0
| DA+3 |  | DA+9 |  | DC+6 |  | DA+6 |  | DB+0 |  | DB+09 |  | DD+3 |  | DA+6 |  | DA+0 |  | DA+0 |  | DD+00 | 2 | 1 | 2 | 1 |  | 1 | 0 | 0 | 0 |  | 0 | 0 | 1 | 0 |  | 0 | 1 | 0 | 0
[5 empty] | RC | [11 empty] | Benching |  | RC |  | #REF!
| 61 |  | 62 |  | 63 |  | 64 |  | 65 |  | 66 |  | 67 |  | 68 |  | 69 |  | 70
|  | 392.27 |  | 431.96 |  | 426.02 |  | 405.36 |  | 411.93 |  | 350.33 |  | 378.3 |  | 416.82 |  | 371.85
F
| AP71 |  | 71/1 |  | 71/2 |  | 71/3 |  | AP72 |  | 72/1 |  | 72/2 |  | AP73 |  | 73/1 |  | 73/2
| DB+00 |  | DA+9 |  | DA+0 |  | DA+0 |  | DD+00 |  | DA+3 |  | DA+3 |  | DB+00 |  | DA+0 |  | DA+9 |  |  | 3 | 2 | 0 | 2 |  | 0 | 2 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | RC |  | Benching &RC |  | RC | [5 empty] | Benching & RC |  | CLEAR |  | 3994.99
| 71 |  | 72 |  | 73 |  | 74 |  | 75 |  | 76 |  | 77 |  | 78 |  | 79 |  | 80
|  | 385.17 |  | 345.19 |  | 332.38 |  | 393.62 |  | 387.95 |  | 340.35 |  | 393.12 |  | 328.54 |  | 398.52
| F |  |  |  | F |  |  |  | F |  | F |  | F |  | F |  | F |  | F
| Er |  |  |  | Er |  |  |  | Er |  | Er |  | Er |  | Er |  |  |  | Er
| 73/3 |  | AP74 |  | 74/1 |  | AP75 |  | 75/1 |  | 75/2 |  | 75/3 |  | 75/4 |  | 75/5 |  | 75/6
| DA+9 |  | DB+09 |  | DA+0 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  |  | 6 | 1 | 0 | 1 |  | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| CLEAR | [5 empty] | Benching |  | Benching |  | Benching &RC
| 81 |  | 82 |  | 83 |  | 84 |  | 85 |  | 86 |  | 87 |  | 88 |  | 89 |  | 90
[6 empty] | 388.46 |  | 380.96 |  | 374.03 |  | 351.96 |  | 395.64 |  | 414.76 |  | 401.93
| F |  |  |  | F |  |  |  | F |  | F |  | F |  | F |  | F
| Er |  |  |  | Er |  |  |  | Er |  | Er |  | Er |  | Er |  | Er
| 75/7 |  | AP76 |  | 76/1 |  | 77/0 |  | 77/1 |  | 77/2 |  | 77/3 |  | 77/4 |  | 77/5 |  | AP78
| DA+0 |  | DC+00 |  | DA+6 |  | DB+00 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+6 |  | DC+00 |  |  | 2 | 2 | 2 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[5 empty] | Clear | [5 empty] | Benching
| 91 |  | 92 |  | 93 |  | 94 |  | 95 |  | 96 |  | 97 |  | 98 |  | 99 |  | 100
|  | 385.54 |  |  |  | 351.18 |  | 441.06 |  | 387.5 |  | 372.63 |  | 415.3 |  | 424.58 |  | 391.7 |  | 410.47
[5 empty] | F | [5 empty] | F | [5 empty] | F
[5 empty] | Er | [5 empty] | Er | [5 empty] | Er
| 78/1 |  | AP79 |  | 79/1 |  | 79/2 |  | AP80 |  | 80/1 |  | AP81 |  | 81/1 |  | 81/2 |  | 81/3
| DA+3 |  | DD+00 |  | DA+9 |  | DA+0 |  | DB+03 |  | DA+9 |  | DB+09 |  | DA+0 |  | DA+3 |  | DA+0 |  |  | 3 | 2 | 0 | 2 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[5 empty] | RC |  | RC,Benching |  |  |  | Benching |  |  |  | Benching &RC
| 101 |  | 102 |  | 103 |  | 104 |  | 105 |  | 106 |  | 107 |  | 108 |  | 109 |  | 110
#REF!
415.03 |  | 416.87 |  |  |  | 426.47 |  | 396.98 |  | 429.38 |  | 403.83 |  | 384.63 |  | 380.68 |  | 354.53
| ROW | [11 empty] | F | [5 empty] | F
U/P
| 81/4 |  | 81/5 |  | AP82 |  | 82/1 |  | 82/2 |  | AP83 |  | 83/1 |  | AP84 |  | AP85 |  | 85/1
| DA+0 |  | DA+6 |  | DB+03 |  | DA+0 |  | DA+3 |  | DC+00 |  | DA+3 |  | DC+06 |  | DC+00 |  | DA+0 |  |  | 3 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 | 0 |  | 0 | 1 | 0 | 0
[7 empty] | RC | [11 empty] | CLEAR
| 111 |  | 112 |  | 113 |  | 114 |  | 115 |  | 116 |  | 117 |  | 118 |  | 119 |  | 120
3121.94
|  | 395.01 | #REF! |  |  | 380.77 |  | 411.81 |  | 432.08 |  | 256.87 |  | 412.4 |  | 382.17 |  | 452.74
|  |  | F |  | F |  |  |  | F |  | F
| AP86 |  | 86/1 |  | 86/2 |  | AP87 |  | 87/1 |  | 87/2 |  | AP88 |  | AP89 |  | 89/1 |  | AP90
| DD+00 |  | DA+6 |  | DA+0 |  | DC+00 |  | DA+3 |  | DA+9 |  | DC+00 |  | DC+00 |  | DA+9 |  | DC+00 |  |  | 1 | 1 | 1 | 2 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| CLEAR |  | CLEAR |  | CLEAR
| 121 |  | 122 |  | 123 |  | 124 |  | 125 |  | 126 |  | 127 |  | 128 |  | 129 |  | 130
#REF!
|  | 430.39 |  |  |  | 378.62 |  | 350.22 |  | 357.91 |  | 237.48 |  | 440.03 |  | 504 |  | 430.57
U/P
| 90/1 |  | AP91 |  | 91/1 |  | 91/2 |  | 91/3 |  | AP92 |  | AP93 |  | AP94 |  | AP95 |  | 95/1
| DA+9 |  | DD+00 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC+00 |  | DC+00 |  | DB+06 |  | DB+06 |  | DB+00 |  |  | 3 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| 131 |  | 132 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137 |  | 138 |  | 139 |  | 140 |  | 141
|  | 354.92 |  |  |  | 419.38 |  | 406.18 |  | 427.47 |  |  |  | 416.77 |  | 378.13 |  | 358.57 |  | 360.52
[5 empty] | F |  |  |  | F |  | F | [7 empty] | F
[9 empty] | Er |  | Er | [7 empty] | Er
| 95/2 |  | 95A/0 |  | 95A/1 |  | AP96 |  | 96/1 |  | 96/2 |  | AP97 |  | 97/1 |  | AP98 |  | AP98/1 |  | 98A/0
| DA+9 |  | DB+0 |  | DA+0 |  | DC+00 |  | DA+0 |  | DA+0 |  | DC+00 |  | DA+3 |  | DC+00 |  | DA+0 |  | DC+00 | 4 | 1 | 0 | 1 |  | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
RC
| 142 |  | 143 |  | 144 |  | 145 |  | 146 |  | 147 |  | 148 |  | 149 |  | 150 |  | 151 |  | 152
| F | [9 empty] | F
Er
| 98A/1 |  | 98B/0 |  | 98B/1 |  | 98B/2 |  | 99/0 |  | 99/1 |  | 99/2 |  | 99/3 |  | 99/4 |  | 99/5 |  | 99/6
| DA+0 |  | DD+00 |  | DA+0 |  | DCT+00 |  | DC+0 |  | DA+6 |  | DA+0 |  | DA+0 |  | DA+6 |  | DA+3 |  | DA+3 | 4 | 2 | 2 | 0 |  | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[5 empty] | RC | [9 empty] | RC
| 153 |  | 154 |  | 155 |  | 156 |  | 157 |  | 158 |  | 159 |  | 160 |  | 161 |  | 162 |  | 163
| AP99A |  | 99A/1 |  | 99A/2 |  | AP100 |  | 100/1 |  | AP101 |  | AP102 |  | 102/1 |  | 102/2 |  | AP103 |  | 103/1
| DB+00 |  | DA+0 |  | DA+0 |  | DC+00 |  | DA+6 |  | DD+06 |  | DD+3 |  | DA+0 |  | DA+0 |  | DC+0 |  | DA+6 | 4 | 0 | 2 | 0 |  | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 0 | 1 | 0 | 0
| 164 |  | 165 |  | 166 |  | 167 |  | 168 |  | 169 |  | 170 |  | 171 |  | 172 |  | 173 |  | 174
| AP104 |  | AP104A |  | AP104B |  | 104B/1 |  | 104B/2 |  | AP105 |  | 105/1 |  | AP106 |  | AP107 |  | 107/1 |  | 108/0
| DB+9 |  | DC+9 |  | DB+9 |  | DA+0 |  | DA+0 |  | DD+0 |  | DA+3 |  | DC+6 |  | DD+3 |  | DA+9 |  | DC+0 | 2 | 1 | 0 | 1 |  | 0 | 0 | 0 | 2 |  | 1 | 0 | 1 | 1 |  | 1 | 1 | 0 | 0
|  |  | RC |  | RC | [15 empty] | 1MRC
| 175 |  | 176 |  | 177 |  | 178 |  | 179 |  | 180 |  | 181 |  | 182 |  | 183 |  | 184 |  | 185
| AP109 |  | AP109A |  | AP110 |  | AP111 |  | AP112 |  | AP113 |  | AP113A |  | AP114 |  | 114/1 |  | AP115 |  | 115/1
| DC+3 |  | DB+6 |  | DC+0 |  | DB+9 |  | DC+9 |  | DD+0 |  | DC+0 |  | DC+0 |  | DA+9 |  | DC+0 |  | DB+9 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 | 2 |  | 4 | 1 | 0 | 1 |  | 1 | 0 | 0 | 0
[7 empty] | 3 MRC |  | 3 MRC | [9 empty] | 1MRC
| 186 |  | 187 |  | 188 |  | 189 |  | 190 |  | 191 |  | 192 |  | 193 |  | 194 |  | 195 |  | 196
| AP116 |  | 116/1 |  | AP117 |  | 117/1 |  | 117/2 |  | AP118 |  | AP119 |  | 119/1 |  | 119/2 |  | AP120 |  | 120/1
| DD+0 |  | DA+0 |  | DD+0 |  | DA+3 |  | DB+9 |  | DC+3 |  | DD+3 |  | DA+3 |  | DA+3 |  | DC+0 |  | DA+6 | 1 | 3 | 1 | 0 |  | 0 | 0 | 0 | 1 |  | 1 | 1 | 0 | 0 |  | 2 | 1 | 0 | 0
|  |  | Benching |  | RC
| 197 |  | 198 |  | 199 |  | 200 |  | 201 |  | 202 |  | 203 |  | 204 |  | 205 |  | 206 |  | 207
| AP121 |  | 122/0 |  | 122/1 |  | 122/2 |  | 123/0 |  | 124/0 |  | 125/0 |  | 125/1 |  | 125/2 |  | 125/3 |  | 126/0
| DD+0 |  | DC+6 |  | DA+3 |  | DA+3 |  | DC+0 |  | DC+3 |  | DC+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC+0 | 3 | 2 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 2 | 2 | 1 | 0 |  | 1 | 0 | 0 | 0
| 208 |  | 209 |  | 210 |  | 211 |  | 212 |  | 213 |  | 214 |  | 215 |  | 216 |  | 217 |  | 218
[22 empty] | 0 | 2 | 3 | 2 |  | 0 | 0 | 0 | 0 |  | 1 | 1 | 1 | 0 |  | 0 | 0 | 1 | 0
| 126/1 |  | 126/2 |  | 126/3 |  | 127/0 |  | 127/1 |  | 128/0 |  | 128/1 |  | 129/0 |  | 129/1 |  | 129/2 |  | 130/0
| DA+6 |  | DA+3 |  | DA+6 |  | DD+6 |  | DA+9 |  | DC+3 |  | DA+6 |  | DC+0 |  | DA+3 |  | DA+9 |  | DC+6
| 219 |  | 220 |  | 221 |  | 222 |  | 223 |  | 224 |  | 225 |  | 226 |  | 227 |  | 228 |  | 229
| 130/1 |  | 131/0 | [18 empty] | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
| DA+0 |  | DD+0
| 230 |  | 231 |  | 232 |  | 233 |  | 234 |  | 235 |  | 236 |  | 237 |  | 238 |  | 239 |  | 240
[22 empty] | 50 | 28 | 21 | 20 | 119 | 3 | 2 | 1 | 7 | 13 | 12 | 6 | 4 | 2 | 24 | 9 | 5 | 1 | 0 | 15
52
TSE
Manual
Total
Paying out/ Rough sag
[11 empty] | Tack welding completed | [5 empty] | Erection ROW
Erection Completed ------>
|  | Foundation completed ----> | [8 empty] | <------Insulator hosting
|  | Earthing completed -----> |  |  |  |  | U/P | [9 empty] | Erection Cleared
Road
[7 empty] | 325 | Span
[12 empty] | HT-D/C Power Line Crossing |  |  |  |  | Cart Track
| Transformer |  |  | ROW | ROW |  |  | Water Tank
| Temple |  |  | A+0 | Tower Type |  |  | LT Power Line Crossing |  |  |  | HT-S/C Power Line Crossing |  |  |  |  | Broad Gauge Railway
[8 empty] | 11 KV Line Crossing | [8 empty] | Line Crossing
| Hut |  |  | 1/0 | Location No. |  |  | 33 KV Line Crossing
| Bore & Handpump |  |  |  | Minor River Crossing | [6 empty] | Forest Stretch |  |  |  |  | SH Crossing
| Oil Pipe Line |  |  | RC | Raised Chimney |  |  | Major River Crossing |  |  |  | NH Crossing |  |  |  |  | Wild Life Sanctuary
3
3
3
3
3

## Sheet5 (hidden)
Sl.No. | Loc.No. | Tower Type |  | Tower Leg |  |  |  | Remarks
|  |  |  | A | B | C | D
1 | AP52 | DB+0 | 2 | 3 | 3 | 3 | 3
2 | 52/1 | DA+6 | 1 | 1 | 1 | 1 | 1
3 | 54/2 | DA+6 | Benching & RC Required | - | - | 1 | -
4 | 54/3 | DA+3 | 1 | 1 | 1 | 1 | 1
5 | AP55 | DD+18 | 3 | 3 | 3 | 3 | 3
6 | AP56 | DB+9 | Benching & RC Required | 3 | 3 | 3 | 3
7 | 57/0 | DB+9 | Benching & RC Required | - | 1 | 3 | -
8 | 60/3 | DA+9 | 2 | 3 | 3 | 3 | 3
9 | 62/1 | DA+0 | 1) Benching - A&D Legs, 2) C-Leg 1MRC, | - | - | 1 | -
10 | 62/3 | DA+9 | 3 | 3 | 3 | 3 | 3
11 | 64/0 | DC+9 | 1) Benching - A&D Legs, 2) C-Leg 1MRC, | - | - | 1 | -
12 | 64/1 | DA+9 | 3 | 3 | 3 | 3 | 3
13 | 64/2 | DA+9 | 1 | 1 | 1 | 1 | 1
14 | AP66 | DD+0 | 1 | 1 | 1 | 1 | 1
15 | AP67 | DC+6 | 1 | 1 | 1 | 1 | 1
16 | 69/3 | DA+0 | 1 | 1 | 1 | 1 | 1
17 | 71/3 | DA+0 | 1 | 1 | 1 | 1 | 1
18 | 72/0 | DD+0 | 1) ABC Benching, 2) C-Leg 1MRC,D-LEG-3MRC | - | - | 1 | 3
19 | 72/1 | DA+3 | 1) A&B Leg Benching, 2) C-Leg 1MRC 3) D-Leg 3MRC | - | - | 1 | 3
20 | 73/1 | DA+0 | 1) A-Leg Benching, C-Leg 2MRC & D-Leg 1MRC | - | - | 3 | 3
21 | 78/1 | DA+3 | 1 | 1 | 1 | 1 | 1
22 | 79/2 | DA+0 | 1 | 1 | 1 | 1 | 1
23 | AP80 | DB+3 | 1 | 1 | 1 | 1 | 1
24 | 81/1 | DA+0 | Benching & RC Required | - | 3 | 3 | -
25 | 82/1 | DA+0 | 1 | 1 | 1 | 1 | 1
26 | 97/1 | DA+3 | 1 | 1 | 1 | 1 | 1
27 | 98B/1 | DA+0 | 1 | 1 | 1 | 1 | 1
28 | 99/3 | DA+0 | 1 | 1 | 1 | 1 | 1
29 | AP104A | DC+9 | 3 | 3 | 3 | 3 | 3
30 | AP104B | DB+9 | 3 | 3 | 3 | 3 | 3
31 | AP108 | DC+0 | 1 | 1 | 1 | 1 | 1
32 | AP111 | DB+9 | 3 | 3 | 3 | 3 | 3
33 | AP112 | DC+9 | 2 | 3 | 3 | 3 | 3
34 | AP115 | DC+0 | 1 | 1 | 1 | 1 | 1

## Sheet3 (hidden)
TB-507 400 KV (Twin) D/C Fatehgarh IV - Bhinmal Transmission Line
DPR and VISUAL CHART
DPR- |  |  | As per Approved Check Survey |  | No.Of Towers | Length | Foundation |  |  | Earthing | Tower Erection |  |  | Stringing
[7 empty] | Com | WIP | Bal | Com | Com | WIP | Bal | Com | WIP | Bal
|  |  | AP 51- AP 121 |  | 171 | 74 | 34 | 3 | 134 | 21 |  |  | 171 |  |  | 74
|  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9
|  |  | 465.03 |  | 375.98 |  | 414.86 |  | 381.02 |  | 353.63 |  | 351.4 |  | 433.26 |  | 396.56 |  | 408.11 | 3579.85
|  | AP51 |  | 51/1 |  | 51/2 |  | 51/3 |  | AP52 |  | 52/1 |  | AP53 |  | AP54 |  | 54/1
|  | DD+18 |  | DA+3 |  | DA+0 |  | DA+3 |  | DB+0 |  | DA+6 |  | DD+0 |  | DC+00 |  | DA+3
[10 empty] | RC |  | RC
| 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19
|  | 425.22 |  | 420.54 |  | 340.56 |  | 336.52 |  | 375.99 |  | 303.41 |  | 448.76 |  | 393.09 |  | 407.8 |  | 206.06 | 3657.95
| 54/2 |  | 54/3 |  | AP55 |  | AP56 |  | 56/1 |  | 56/2 |  | 56/3 |  | 56/4 |  | 56/5 |  | AP57
| DA+6 |  | DA+3 |  | DD+18 |  | DB+09 |  | DB+9 |  | DA+0 |  | DB+9 |  | DA+6 |  | DA+6 |  | DB+09
| Benching &RC |  | RC |  | RC |  | Benching &RC |  |  |  | Benching Required | [5 empty] | Benching &RC |  | Benching &RC
| 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29
|  | 417.38 |  | 304.56 |  | 408.66 |  | 434.89 |  | 408.17 |  | 398.59 |  | 446.37 |  | 297.58 |  | 240.47 |  | 312.69 | 3669.36
| AP58 |  | AP59 |  | 59/1 |  | AP60 |  | 60/1 |  | 60/2 |  | 60/3 |  | AP61 |  | 61/1 |  | AP62
| DB+09 |  | DC+09 |  | DA+0 |  | DD+00 |  | DA+9 |  | DA+0 |  | DA+9 |  | DC+00 |  | DA+9 |  | DB+00
[5 empty] | Benching | [7 empty] | RC
| 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39
|  | 347.88 |  | 379.25 |  | 398.7 |  | 439.06 |  | 381.53 |  | 379.71 |  | 426.3 |  | 387.14 |  |  |  | 423.77 | #REF!
| 62/1 |  | 62/2 |  | 62/3 |  | 62/4 |  | 62/5 |  | AP63 |  | 63/1 |  | AP64 |  | 64/1 |  | 64/2
| DA+0 |  | DA+0 |  | DA+9 |  | DA+6 |  | DA+6 |  | DC+00 |  | DA+0 |  | DC+09 |  | DA+9 |  | DA+9
| RC |  |  |  | RC | [9 empty] | Benching &RC |  |  |  | RC
| 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49
|  | 407.9 |  | 426.63 |  | 392.27 |  | 431.96 |  | 426.02 |  | 405.36 |  | 411.93 |  | 423.77 |  | 407.9 |  | 426.63
| F |  | F | [13 empty] | F |  | F
U/P
| 64/3 |  | 64/4 |  | 64/5 |  | 64/6 |  | 64/7 |  | 65/0 |  | 65/1 |  | 66/0 |  | 66/1 |  | 66/2
| DA+9 |  | DA+9 |  | DA+9 |  | DA+3 |  | DA+3 |  | DD+0 |  | DB+09 |  | DD+0 |  | DA+9 |  | DA+0 |  | #REF!
RC
| 50 |  | 51 |  | 52 |  | 53 |  | 54 |  | 55 |  | 56 |  | 57 |  | 58 |  | 59 |  | 60
|  | 392.27 |  | 431.96 |  | 426.02 |  | 405.36 |  | 411.93 |  | 350.33 |  | 378.3 |  | 416.82 |  | 371.85
F
| 66/3 |  | 66/4 |  | 67/0 |  | 67/1 |  | 67/2 |  | AP68 |  | AP69 |  | 69/1 |  | 69/2 |  | 69/3 |  | 70/0
| DA+3 |  | DA+9 |  | DC+6 |  | DA+6 |  | DB+0 |  | DB+09 |  | DD+3 |  | DA+6 |  | DA+0 |  | DA+0 |  | DD+00
[5 empty] | RC | [11 empty] | Benching |  | RC |  | #REF!
| 61 |  | 62 |  | 63 |  | 64 |  | 65 |  | 66 |  | 67 |  | 68 |  | 69 |  | 70
|  | 392.27 |  | 431.96 |  | 426.02 |  | 405.36 |  | 411.93 |  | 350.33 |  | 378.3 |  | 416.82 |  | 371.85
F
| AP71 |  | 71/1 |  | 71/2 |  | 71/3 |  | AP72 |  | 72/1 |  | 72/2 |  | AP73 |  | 73/1 |  | 73/2
| DB+00 |  | DA+9 |  | DA+0 |  | DA+0 |  | DD+00 |  | DA+3 |  | DA+3 |  | DB+00 |  | DA+0 |  | DA+9
[7 empty] | RC |  | Benching &RC |  | RC | [5 empty] | Benching & RC |  | CLEAR |  | 3994.99
| 71 |  | 72 |  | 73 |  | 74 |  | 75 |  | 76 |  | 77 |  | 78 |  | 79 |  | 80
|  | 385.17 |  | 345.19 |  | 332.38 |  | 393.62 |  | 387.95 |  | 340.35 |  | 393.12 |  | 328.54 |  | 398.52
| F |  |  |  | F |  |  |  | F |  | F |  | F |  | F |  | F |  | F
| Er | [7 empty] | Er |  | Er |  | Er | [5 empty] | Er
| 73/3 |  | AP74 |  | 74/1 |  | AP75 |  | 75/1 |  | 75/2 |  | 75/3 |  | 75/4 |  | 75/5 |  | 75/6
| DA+9 |  | DB+09 |  | DA+0 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0
| CLEAR | [5 empty] | Benching |  | Benching |  | Benching &RC
| 81 |  | 82 |  | 83 |  | 84 |  | 85 |  | 86 |  | 87 |  | 88 |  | 89 |  | 90
[6 empty] | 388.46 |  | 380.96 |  | 374.03 |  | 351.96 |  | 395.64 |  | 414.76 |  | 401.93
| F |  |  |  | F |  |  |  | F |  | F |  | F |  | F |  | F
| Er | [7 empty] | Er | [5 empty] | Er |  | Er
| 75/7 |  | AP76 |  | 76/1 |  | 77/0 |  | 77/1 |  | 77/2 |  | 77/3 |  | 77/4 |  | 77/5 |  | AP78
| DA+0 |  | DC+00 |  | DA+6 |  | DB+00 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+6 |  | DC+00
[5 empty] | Clear | [5 empty] | Benching
| 91 |  | 92 |  | 93 |  | 94 |  | 95 |  | 96 |  | 97 |  | 98 |  | 99 |  | 100
|  | 385.54 |  |  |  | 351.18 |  | 441.06 |  | 387.5 |  | 372.63 |  | 415.3 |  | 424.58 |  | 391.7 |  | 410.47
[5 empty] | F | [5 empty] | F | [5 empty] | F
Er
| 78/1 |  | AP79 |  | 79/1 |  | 79/2 |  | AP80 |  | 80/1 |  | AP81 |  | 81/1 |  | 81/2 |  | 81/3
| DA+3 |  | DD+00 |  | DA+9 |  | DA+0 |  | DB+03 |  | DA+9 |  | DB+09 |  | DA+0 |  | DA+3 |  | DA+0
[5 empty] | Clear |  | RC,Benching |  |  |  | Benching |  |  |  | Benching &RC
| 101 |  | 102 |  | 103 |  | 104 |  | 105 |  | 106 |  | 107 |  | 108 |  | 109 |  | 110
#REF!
415.03 |  | 416.87 |  |  |  | 426.47 |  | 396.98 |  | 429.38 |  | 403.83 |  | 384.63 |  | 380.68 |  | 354.53
| ROW | [11 empty] | F | [5 empty] | F
U/P
| 81/4 |  | 81/5 |  | AP82 |  | 82/1 |  | 82/2 |  | AP83 |  | 83/1 |  | AP84 |  | AP85 |  | 85/1
| DA+0 |  | DA+6 |  | DB+03 |  | DA+0 |  | DA+3 |  | DC+00 |  | DA+3 |  | DC+06 |  | DC+00 |  | DA+0
[7 empty] | RC | [11 empty] | CLEAR
| 111 |  | 112 |  | 113 |  | 114 |  | 115 |  | 116 |  | 117 |  | 118 |  | 119 |  | 120
3121.94
|  | 395.01 | #REF! |  |  | 380.77 |  | 411.81 |  | 432.08 |  | 256.87 |  | 412.4 |  | 382.17 |  | 452.74
|  |  | F |  | F |  |  |  | F
U/P
| AP86 |  | 86/1 |  | 86/2 |  | AP87 |  | 87/1 |  | 87/2 |  | AP88 |  | AP89 |  | 89/1 |  | AP90
| DD+00 |  | DA+6 |  | DA+0 |  | DC+00 |  | DA+3 |  | DA+9 |  | DC+00 |  | DC+00 |  | DA+9 |  | DC+00
| CLEAR |  | CLEAR |  | CLEAR
| 121 |  | 122 |  | 123 |  | 124 |  | 125 |  | 126 |  | 127 |  | 128 |  | 129 |  | 130
#REF!
|  | 430.39 |  |  |  | 378.62 |  | 350.22 |  | 357.91 |  | 237.48 |  | 440.03 |  | 504 |  | 430.57
| 90/1 |  | AP91 |  | 91/1 |  | 91/2 |  | 91/3 |  | AP92 |  | AP93 |  | AP94 |  | AP95 |  | 95/1
| DA+9 |  | DD+00 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC+00 |  | DC+00 |  | DB+06 |  | DB+06 |  | DB+00
| 131 |  | 132 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137 |  | 138 |  | 139 |  | 140 |  | 141
|  | 354.92 |  |  |  | 419.38 |  | 406.18 |  | 427.47 |  |  |  | 416.77 |  | 378.13 |  | 358.57 |  | 360.52
[5 empty] | F |  |  |  | F |  | F
| 95/2 |  | 95A/0 |  | 95A/1 |  | AP96 |  | 96/1 |  | 96/2 |  | AP97 |  | 97/1 |  | AP98 |  | AP98/1 |  | 98A/0
| DA+9 |  | DB+0 |  | DA+0 |  | DC+00 |  | DA+0 |  | DA+0 |  | DC+00 |  | DA+3 |  | DC+00 |  | DA+0 |  | DC+00
RC
| 142 |  | 143 |  | 144 |  | 145 |  | 146 |  | 147 |  | 148 |  | 149 |  | 150 |  | 151 |  | 152
F
U/P
| 98A/1 |  | 98B/0 |  | 98B/1 |  | 98B/2 |  | 99/0 |  | 99/1 |  | 99/2 |  | 99/3 |  | 99/4 |  | 99/5 |  | 99/6
| DA+0 |  | DD+00 |  | DA+0 |  | DCT+00 |  | DC+0 |  | DA+6 |  | DA+0 |  | DA+0 |  | DA+6 |  | DA+3 |  | DA+3
[5 empty] | RC | [9 empty] | RC
| 153 |  | 154 |  | 155 |  | 156 |  | 157 |  | 158 |  | 159 |  | 160 |  | 161 |  | 162 |  | 163
| AP99A |  | 99A/1 |  | 99A/2 |  | AP100 |  | 100/1 |  | AP101 |  | AP102 |  | 102/1 |  | 102/2 |  | AP103 |  | 103/1
| DB+00 |  | DA+0 |  | DA+0 |  | DC+00 |  | DA+6 |  | DD+06 |  | DD+3 |  | DA+0 |  | DA+0 |  | DC+0 |  | DA+6
| 164 |  | 165 |  | 166 |  | 167 |  | 168 |  | 169 |  | 170 |  | 171 |  | 172 |  | 173 |  | 174
| AP104 |  | AP104A |  | AP104B |  | 104B/1 |  | 104B/2 |  | AP105 |  | 105/1 |  | AP106 |  | AP107 |  | 107/1 |  | 108/0
| DB+9 |  | DC+9 |  | DB+9 |  | DA+0 |  | DA+0 |  | DD+0 |  | DA+3 |  | DC+6 |  | DD+3 |  | DA+9 |  | DC+0
|  |  | RC |  | RC | [15 empty] | 1MRC
| 175 |  | 176 |  | 177 |  | 178 |  | 179 |  | 180 |  | 181 |  | 182 |  | 183 |  | 184 |  | 185
| AP109 |  | AP109A |  | AP110 |  | AP111 |  | AP112 |  | AP113 |  | AP113A |  | AP114 |  | 114/1 |  | AP115 |  | 115/1
| DC+3 |  | DB+6 |  | DC+0 |  | DB+9 |  | DC+9 |  | DD+0 |  | DC+0 |  | DC+0 |  | DA+9 |  | DC+0 |  | DB+9
[7 empty] | 3 MRC |  | 3 MRC | [9 empty] | 1MRC
| 186 |  | 187 |  | 188 |  | 189 |  | 190 |  | 191 |  | 192 |  | 193 |  | 194 |  | 195 |  | 196
| AP116 |  | 116/1 |  | AP117 |  | 117/1 |  | 117/2 |  | AP118 |  | AP119 |  | 119/1 |  | 119/2 |  | AP120 |  | 120/1
| DD+0 |  | DA+0 |  | DD+0 |  | DA+3 |  | DB+9 |  | DC+3 |  | DD+3 |  | DA+3 |  | DA+3 |  | DC+0 |  | DA+6
|  |  | Benching |  | RC
| 197 |  | 198 |  | 199 |  | 200 |  | 201 |  | 202 |  | 203 |  | 204 |  | 205 |  | 206 |  | 207
| AP121 |  | 122/0 |  | 122/1 |  | 122/2 |  | 123/0 |  | 124/0 |  | 125/0 |  | 125/1 |  | 125/2 |  | 125/3 |  | 126/0
| DD+0 |  | DC+6 |  | DA+3 |  | DA+3 |  | DC+0 |  | DC+3 |  | DC+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC+0
| 208 |  | 209 |  | 210 |  | 211 |  | 212 |  | 213 |  | 214 |  | 215 |  | 216 |  | 217 |  | 218
| 126/1 |  | 126/2 |  | 126/3 |  | 127/0 |  | 127/1 |  | 128/0 |  | 128/1 |  | 129/0 |  | 129/1 |  | 129/2 |  | 130/0
| DA+6 |  | DA+3 |  | DA+6 |  | DD+6 |  | DA+9 |  | DC+3 |  | DA+6 |  | DC+0 |  | DA+3 |  | DA+9 |  | DC+6
| 219 |  | 220 |  | 221 |  | 222 |  | 223 |  | 224 |  | 225 |  | 226 |  | 227 |  | 228 |  | 229
| 130/1 |  | 131/0
| DA+0 |  | DD+0
| 230 |  | 231 |  | 232 |  | 233 |  | 234 |  | 235 |  | 236 |  | 237 |  | 238 |  | 239 |  | 240
DA+0
| 50 | 28 | 21 | 20 | 119 | 3 | 2 | 1 | 7 | 13 | 12 | 6 | 4 | 2 | 24 | 9 | 5 | 1 | 0 | 15
SUMMERY
| TOT | QTY | TOT | QTY | TOT | QTY | TOT | QTY
| DA+0 | 50 | DB+0 | 3 | DC+0 | 12 | DD+0 | 9
| DA+3 | 28 | DB+3 | 2 | DC+3 | 6 | DD+3 | 5
| DA+6 | 21 | DB+6 | 1 | DC+6 | 4 | DD+6 | 1
| DA+9 | 20 | DB+9 | 7 | DC+9 | 2 | DD+9 | 0
|  | 119 |  | 13 |  | 24 | DD+18
DD+25
DD+30
15
3
3
3
3
3

## Tower Schedule (hidden)
NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE
Client : RAJASTHAN IV A POWER TRANSMISSION LTD.
CONTRACTOR : KEC INTERNATIONAL LIMITED
CHECK SURVEY
Tower Schedule from AP-75/0 to AP-92/0 (Section Length = 20.273 kms)
AS PER DETAILED SURVEY | [6 empty] | AS PER CHECK SURVEY
Sl. No | Twr No. | Tower Type | Raise Chimney | Deviation Angle (DMS) | Span (m) | Section Length (M) | Sl. No | Twr No. | Tower Type | Raise Chimney | Ground Cutting Length X Height | Deviation Angle (DMS) | Span (m) | Section Length (M) | Sum of Adjacent Span |  |  | Wind Span (m) | Weight Span (Cold) |  |  | Weight Span (Hot) |  |  | Major Crossings /Remarks | UTM Coordinate (Zone 43)
[15 empty] | Left | Right | Total |  | Left | Right | Total | Left | Right | Total |  | Easting | Northing | Elevation
1 | AP75 | DC+0 |  | 17°34'26"(RT) |  |  | 1 | AP75 | DC+0 |  | Benching Required | 00°00'00"(RT) |  |  | 385.17 | 345.19 | 730.36 | 365 | 197 | 128 | 325 | 196 | 147 | 343 |  | 782527.143 | 2837712.305 | 125.81
[5 empty] | 345.19 | 2920 | [6 empty] | 345.19 | 2920 | [10 empty] | Road,11Kv Line
2 | 75/1 | DA+0 |  |  |  |  | 2 | 75/1 | DA+0 | [5 empty] | 345.19 | 332.38 | 677.57 | 339 | 218 | 116 | 334 | 200 | 137 | 337 |  | 782723.206 | 2837428.199 | 133.297
[5 empty] | 332.38 | [7 empty] | 332.38 | [11 empty] | Water Tank
3 | 75/2 | DA+0 |  |  |  |  | 3 | 75/2 | DA+0 | [5 empty] | 332.38 | 393.62 | 726.01 | 363 | 217 | 288 | 505 | 197 | 252 | 449 |  | 782911.993 | 2837154.634 | 141.17
[5 empty] | 393.62 | [7 empty] | 393.62
4 | 75/3 | DA+3 |  |  |  |  | 4 | 75/3 | DA+3 | [5 empty] | 393.62 | 387.95 | 781.57 | 391 | 107 | 260 | 367 | 144 | 234 | 378 |  | 783135.564 | 2836830.667 | 121.365
[5 empty] | 387.95 | [7 empty] | 387.95 | [11 empty] | Cart Track
5 | 75/4 | DA+0 |  |  |  |  | 5 | 75/4 | DA+0 | [5 empty] | 387.95 | 340.35 | 728.3 | 364 | 129 | 196 | 325 | 156 | 186 | 342 |  | 783355.912 | 2836511.37 | 112.432
[5 empty] | 340.35 | [7 empty] | 340.35 | [11 empty] | 11kV Line
6 | 75/5 | DA+0 |  |  |  |  | 6 | 75/5 | DA+0 | [5 empty] | 340.35 | 393.12 | 733.47 | 367 | 145 | 176 | 321 | 156 | 185 | 341 |  | 783549.223 | 2836231.25 | 108.339
[5 empty] | 393.12 | [7 empty] | 393.12
7 | 75/6 | DA+0 |  |  |  |  | 7 | 75/6 | DA+0 | [5 empty] | 393.12 | 328.54 | 721.66 | 361 | 217 | 180 | 397 | 210 | 174 | 384 |  | 783772.509 | 2835907.696 | 112.147
[5 empty] | 328.54 | [7 empty] | 328.54
8 | 75/7 | DA+0 |  |  |  |  | 8 | 75/7 | DA+0 | [5 empty] | 328.54 | 398.52 | 727.05 | 364 | 149 | 240 | 389 | 156 | 224 | 380 |  | 783959.112 | 2835637.297 | 109.802
[5 empty] | 398.52 | [7 empty] | 398.52 | [11 empty] | 11kV Line
9 | AP76 | DC+0 |  | 16°40'52"(LT) |  |  | 9 | AP76 | DC+0 |  |  | 16°40'52"(LT) |  |  | 398.52 | 425.85 | 824.36 | 412 | 159 | 190 | 349 | 176 | 199 | 375 |  | 784185.462 | 2835309.303 | 101.99
[5 empty] | 425.85 | 835 | [6 empty] | 425.85 | 835 | [10 empty] | 11kV Line
10 | 76/1 | DA+6 |  |  |  |  | 10 | 76/1 | DA+6 | [5 empty] | 425.85 | 409.37 | 835.22 | 418 | 237 | 224 | 461 | 229 | 218 | 447 |  | 784517.764 | 2835042.992 | 101.179
[5 empty] | 409.37 | [7 empty] | 409.37
11 | AP77 | DB+0 |  | 12°41'03"(RT) |  |  | 11 | AP77 | DB+0 |  |  | 12°41'03"(RT) |  |  | 409.37 | 388.46 | 797.82 | 399 | 186 | 199 | 385 | 193 | 198 | 391 |  | 784837.208 | 2834786.986 | 103.07
[5 empty] | 388.46 | 2306 | [6 empty] | 388.46 | 2306
12 | 77/1 | DA+0 |  |  |  |  | 12 | 77/1 | DA+0 | [5 empty] | 388.46 | 380.96 | 769.42 | 385 | 190 | 193 | 383 | 192 | 192 | 384 |  | 785079.593 | 2834483.429 | 102.411
[5 empty] | 380.96 | [7 empty] | 380.96 | [11 empty] | 2Nos.11kV Line,Road
13 | 77/2 | DA+3 |  |  |  |  | 13 | 77/2 | DA+3 |  | Benching Required |  |  |  | 380.96 | 381.39 | 762.35 | 381 | 189 | 212 | 401 | 190 | 204 | 394 |  | 785317.301 | 2834185.728 | 99.05
[5 empty] | 381.39 | [7 empty] | 381.39 | [11 empty] | 11kV Line
14 | 77/3 | DA+0 |  |  |  |  | 14 | 77/3 | DA+0 | [5 empty] | 381.39 | 344.6 | 725.98 | 363 | 170 | 170 | 340 | 179 | 171 | 350 |  | 785555.277 | 2833887.693 | 98.293
[5 empty] | 344.6 | [7 empty] | 344.6 | [11 empty] | 11kV Line,Road
15 | 77/4 | DA+3 |  |  |  |  | 15 | 77/4 | DA+3 | [5 empty] | 344.6 | 395.64 | 740.24 | 370 | 175 | 205 | 380 | 174 | 203 | 377 |  | 785770.295 | 2833618.41 | 95.695
[5 empty] | 395.64 | [7 empty] | 395.64
16 | 77/5 | DA+6 |  |  |  |  | 16 | 77/5 | DA+6 | [5 empty] | 395.64 | 414.76 | 810.4 | 405 | 191 | 118 | 309 | 195 | 153 | 348 |  | 786017.163 | 2833309.237 | 91.436
[5 empty] | 414.76 | [7 empty] | 414.76 | [11 empty] | 11kV Line
17 | AP78 | DC+0 |  | 24°47'00"(LT) |  |  | 17 | AP78 | DC+0 |  |  | 24°47'00"(LT) |  |  | 414.76 | 401.93 | 816.69 | 409 | 298 | 296 | 594 | 264 | 259 | 523 |  | 786275.963 | 2832985.122 | 114.99
[5 empty] | 401.93 | 757 | [6 empty] | 401.93 | 757 | [10 empty] | WaterTank
18 | 78/1 | DA+3 | 1 |  |  |  | 18 | 78/1 | DA+3 | 1 |  |  |  |  | 401.93 | 354.95 | 756.88 | 379 | 106 | 225 | 331 | 144 | 207 | 351 |  | 786635.319 | 2832805.093 | 93.103
[5 empty] | 354.95 | [7 empty] | 354.95
19 | AP79 | DD+0 |  | 38°25'04"(RT) |  |  | 19 | AP79 | DD+0 |  |  | 38°25'04"(RT) |  |  | 354.95 | 425 | 779.95 | 390 | 130 | 142 | 272 | 149 | 169 | 318 |  | 786952.67 | 2832646.107 | 88.93
[5 empty] | 425 | 1192 | [6 empty] | 425 | 1192 | [10 empty] | 3No.11kV Line,Cart Track
20 | 79/1 | DA+9 |  |  |  |  | 20 | 79/1 | DA+9 | [5 empty] | 425 | 414 | 839 | 420 | 284 | 203 | 487 | 258 | 205 | 463 |  | 787132.097 | 2832260.84 | 94.695
[5 empty] | 414 | [7 empty] | 414
21 | 79/2 | DA+0 | 1 |  |  |  | 21 | 79/2 | DA+0 | 1 | Benching Required |  |  |  | 414 | 353.05 | 767.05 | 384 | 211 | 188 | 399 | 210 | 184 | 394 |  | 787306.881 | 2831885.544 | 103.516
[5 empty] | 353.05 | [7 empty] | 353.05 | [11 empty] | 11kV Line
22 | AP80 | DB+3 | 1 | 14°24'42"(LT) |  |  | 22 | AP80 | DB+3 | 1 |  | 14°24'42"(LT) |  |  | 353.05 | 441.06 | 794.11 | 397 | 165 | 156 | 321 | 170 | 179 | 349 |  | 787455.933 | 2831565.499 | 98.39
[5 empty] | 441.06 | 829 | [6 empty] | 441.06 | 829 | [10 empty] | Road
23 | 80/1 | DA+9 |  |  |  |  | 23 | 80/1 | DA+9 |  | Benching Required |  |  |  | 441.06 | 387.5 | 828.55 | 415 | 287 | 271 | 558 | 264 | 245 | 509 |  | 787735.789 | 2831224.603 | 108.033
[5 empty] | 387.5 | [7 empty] | 387.5 | [11 empty] | Cart Track,2Nos.11kV Line
24 | AP81 | DB+9 |  | 14°07'31"(RT) |  |  | 24 | AP81 | DB+9 |  |  | 14°07'31"(RT) |  |  | 387.5 | 372.63 | 760.12 | 380 | 117 | 157 | 274 | 145 | 168 | 313 |  | 787981.661 | 2830925.105 | 92.91
[5 empty] | 372.63 | 2400 | [6 empty] | 372.63 | 2400 | [10 empty] | Cart Track
25 | 81/1 | DA+0 |  |  |  |  | 25 | 81/1 | DA+0 |  | Benching & RC Required |  |  |  | 372.63 | 415.3 | 787.93 | 394 | 216 | 255 | 471 | 206 | 238 | 444 |  | 788140.665 | 2830588.105 | 107.482
[5 empty] | 415.3 | [7 empty] | 415.3 | [11 empty] | Cart Track,2Nos.WaterTank
26 | 81/2 | DA+3 |  |  |  |  | 26 | 81/2 | DA+3 | [5 empty] | 415.3 | 424.58 | 839.89 | 420 | 161 | 132 | 293 | 179 | 162 | 341 |  | 788317.879 | 2830212.509 | 94.983
[5 empty] | 424.58 | [7 empty] | 424.58
27 | 81/3 | DA+0 |  |  |  |  | 27 | 81/3 | DA+0 | [5 empty] | 424.58 | 391.7 | 816.29 | 408 | 294 | 205 | 499 | 264 | 202 | 466 |  | 788499.053 | 2829828.52 | 114.644
[5 empty] | 391.7 | [7 empty] | 391.7
28 | 81/4 | DA+0 |  |  |  |  | 28 | 81/4 | DA+0 | [5 empty] | 391.7 | 410.47 | 802.17 | 401 | 187 | 206 | 393 | 191 | 206 | 397 |  | 788666.198 | 2829474.268 | 112.98
[5 empty] | 410.47 | [7 empty] | 410.47 | [11 empty] | WaterTank,11kV Line,Road,33kV Line
29 | 81/5 | DA+6 |  |  |  |  | 29 | 81/5 | DA+6 | [5 empty] | 410.47 | 385.54 | 796.01 | 398 | 205 | 235 | 440 | 206 | 220 | 426 |  | 788841.348 | 2829103.047 | 106.942
[5 empty] | 385.54 | [7 empty] | 385.54 | [11 empty] | 2Nos. 11kV Line
30 | AP82 | DB+3 |  | 12°00'06"(LT) |  |  | 30 | AP82 | DB+3 |  |  | 12°00'06"(LT) |  |  | 385.54 | 418.31 | 803.85 | 402 | 151 | 214 | 365 | 167 | 213 | 380 |  | 789005.862 | 2828754.368 | 101.9
[5 empty] | 418.31 | 1242 | [6 empty] | 418.31 | 1242 | [10 empty] | Cart Track
31 | 82/1 | DA+0 | 1 |  |  |  | 31 | 82/1 | DA+0 | 1 |  |  |  |  | 418.31 | 421.47 | 839.79 | 420 | 205 | 230 | 435 | 207 | 224 | 431 |  | 789259.126 | 2828421.437 | 103.093
[5 empty] | 421.47 | [7 empty] | 421.47 | [11 empty] | 11kV Line
32 | 82/2 | DA+3 |  |  |  |  | 32 | 82/2 | DA+3 | [5 empty] | 421.47 | 401.98 | 823.45 | 412 | 192 | 233 | 425 | 199 | 222 | 421 |  | 789514.304 | 2828085.991 | 97.132
[5 empty] | 401.98 | [7 empty] | 401.98 | [11 empty] | 11kV Line
33 | AP83 | DC+0 |  | 14°21'11"(RT) |  |  | 33 | AP83 | DC+0 |  |  | 14°21'11"(RT) |  |  | 401.98 | 429.38 | 831.36 | 416 | 170 | 198 | 368 | 182 | 205 | 387 |  | 789757.679 | 2827766.061 | 93.67
[5 empty] | 429.38 | 833 | [6 empty] | 429.38 | 833 | [10 empty] | 2Nos.Cart Track
34 | 83/1 | DA+3 |  |  |  |  | 34 | 83/1 | DA+3 | [5 empty] | 429.38 | 403.83 | 833.21 | 417 | 233 | 191 | 424 | 227 | 196 | 423 |  | 789924.813 | 2827370.545 | 94.494
[5 empty] | 403.83 | [7 empty] | 403.83 | [11 empty] | Road
35 | AP84 | DC+6 |  | 17°28'54"(LT) |  |  | 35 | AP84 | DC+6 |  |  | 17°28'54"(LT) |  |  | 403.83 | 384.63 | 788.46 | 394 | 214 | 272 | 486 | 210 | 241 | 451 |  | 790082.003 | 2826998.562 | 93.69
[5 empty] | 384.63 | 385 | [6 empty] | 384.63 | 385 | [10 empty] | Cart Track
36 | AP85 | DC+0 |  | 26°43'01"(RT) |  |  | 36 | AP85 | DC+0 |  |  | 26°43'01"(RT) |  |  | 384.63 | 380.68 | 765.31 | 383 | 114 | 189 | 303 | 145 | 190 | 335 |  | 790331.234 | 2826705.605 | 85.28
[5 empty] | 380.68 | 735 | [6 empty] | 380.68 | 735 | [10 empty] | 11kV Line
37 | 85/1 | DA+0 |  |  |  |  | 37 | 85/1 | DA+0 | [5 empty] | 380.68 | 354.53 | 735.21 | 368 | 193 | 176 | 369 | 193 | 177 | 370 |  | 790421.216 | 2826335.71 | 85.764
[5 empty] | 354.53 | [7 empty] | 354.53 | [11 empty] | Cart Track
38 | AP86 | DD+0 |  | 40°12'50"(LT) |  |  | 38 | AP86 | DD+0 |  |  | 40°12'50"(LT) |  |  | 354.53 | 405.57 | 760.1 | 380 | 180 | 165 | 345 | 180 | 180 | 360 |  | 790505.015 | 2825991.23 | 86.03
[5 empty] | 405.57 | 1203 | [6 empty] | 405.57 | 1203
39 | 86/1 | DA+6 |  |  |  |  | 39 | 86/1 | DA+6 | [5 empty] | 405.57 | 416.87 | 822.45 | 411 | 241 | 246 | 487 | 227 | 233 | 460 |  | 790832.658 | 2825752.189 | 87.613
[5 empty] | 416.87 | [7 empty] | 416.87 | [11 empty] | 11kV Line,2No.Cart Track
40 | 86/2 | DA+0 |  |  |  |  | 40 | 86/2 | DA+0 | [5 empty] | 416.87 | 380.77 | 797.64 | 399 | 172 | 191 | 363 | 186 | 191 | 377 |  | 791169.429 | 2825506.488 | 86.123
[5 empty] | 380.77 | [7 empty] | 380.77 | [11 empty] | Cart Track
41 | AP87 | DC+0 |  | 23°52'06"(RT) |  |  | 41 | AP87 | DC+0 |  |  | 23°52'06"(RT) |  |  | 380.77 | 411.81 | 792.58 | 396 | 191 | 203 | 394 | 191 | 205 | 396 |  | 791477.031 | 2825282.069 | 85.95
[5 empty] | 411.81 | 1101 | [6 empty] | 411.81 | 1101 | [10 empty] | Cart Track,2Nos.11kV Line
42 | 87/1 | DA+3 |  |  |  |  | 42 | 87/1 | DA+3 | [5 empty] | 411.81 | 392.08 | 803.89 | 402 | 210 | 169 | 379 | 209 | 180 | 389 |  | 791683.05 | 2824925.492 | 83.796
[5 empty] | 392.08 | [7 empty] | 392.08 | [11 empty] | Cart Track
43 | 87/2 | DA+9 |  |  |  |  | 43 | 87/2 | DA+9 | [5 empty] | 392.08 | 296.87 | 688.95 | 345 | 224 | 191 | 415 | 213 | 174 | 387 |  | 791879.197 | 2824586.003 | 82.85
[5 empty] | 296.87 | [7 empty] | 296.87 | [11 empty] | Cart Track , Benching Required 1m depth & 5m Length
44 | AP88 | DC+0 |  | 24°54'04"(RT) |  |  | 44 | AP88 | DC+0 |  |  | 24°54'04"(RT) |  |  | 296.87 | 412.4 | 709.27 | 355 | 107 | 209 | 316 | 124 | 209 | 333 |  | 792027.714 | 2824328.95 | 85.77
[5 empty] | 412.4 | 412 | [6 empty] | 412.4 | 412
45 | AP89 | DC+0 |  | 24°07'20"(LT) |  |  | 45 | AP89 | DC+0 |  |  | 24°07'20"(LT) |  |  | 412.4 | 382.17 | 794.57 | 397 | 204 | 107 | 311 | 206 | 137 | 343 |  | 792064.495 | 2823918.194 | 85.31
[5 empty] | 382.17 | 835 | [6 empty] | 382.17 | 835 | [10 empty] | Road,Cart Track
46 | 89/1 | DA+9 |  |  |  |  | 46 | 89/1 | DA+9 | [5 empty] | 382.17 | 452.74 | 834.91 | 418 | 276 | 266 | 542 | 247 | 253 | 500 |  | 792251.169 | 2823584.714 | 92.75
[5 empty] | 452.74 | [7 empty] | 452.74 | [11 empty] | 2Nos.11kV Line
47 | AP90 | DC+0 |  | 17°57'57"(RT) |  |  | 47 | AP90 | DC+0 |  |  | 17°57'57"(RT) |  |  | 452.74 | 420.21 | 872.94 | 437 | 188 | 205 | 393 | 202 | 207 | 409 |  | 792472.311 | 2823189.661 | 92.68
[5 empty] | 420.21 | 815 | [6 empty] | 420.21 | 815
48 | 90/1 | DA+9 |  |  |  |  | 48 | 90/1 | DA+9 | [5 empty] | 420.21 | 395.01 | 815.22 | 408 | 216 | 252 | 468 | 215 | 233 | 448 |  | 792554.457 | 2822777.562 | 85.094
[5 empty] | 395.01 | [7 empty] | 395.01 | [11 empty] | 2Nos. WaterTank,11kV Line,Cart Track
49 | AP91 | DD+0 |  | 38°03'06"(LT) |  |  | 49 | AP91 | DD+0 |  |  | 38°03'06"(LT) |  |  | 395.01 | 386.74 | 781.75 | 391 | 143 | 197 | 340 | 164 | 196 | 360 |  | 792631.678 | 2822390.172 | 83.39
[5 empty] | 386.74 | 1473 | [6 empty] | 386.74 | 1473
50 | 91/1 | DA+0 |  |  |  |  | 50 | 91/1 | DA+0 | [5 empty] | 386.74 | 378.62 | 765.36 | 383 | 191 | 198 | 389 | 192 | 195 | 387 |  | 792924.985 | 2822138.111 | 83.029
[5 empty] | 378.62 | [7 empty] | 378.62
51 | 91/2 | DA+0 |  |  |  |  | 51 | 91/2 | DA+0 | [5 empty] | 378.62 | 350.22 | 728.84 | 364 | 181 | 228 | 409 | 185 | 207 | 392 |  | 793212.14 | 2821891.335 | 81.543
[5 empty] | 350.22 | [7 empty] | 350.22 | [11 empty] | Cart Track,11kV Line
52 | 91/3 | DA+0 |  |  |  |  | 52 | 91/3 | DA+0 | [5 empty] | 350.22 | 357.91 | 708.12 | 354 | 122 | 184 | 306 | 144 | 182 | 326 |  | 793477.75 | 2821663.077 | 72.815
[5 empty] | 357.91 | [7 empty] | 357.91
53 | AP92 | DC+0 |  | 15°43'35"(LT) |  |  | 53 | AP92 | DC+0 |  |  | 00°00'00"(LT) |  |  | 357.91 | 237.48 | 595.38 | 298 | 174 | 165 | 339 | 177 | 140 | 317 |  | 793749.192 | 2821429.805 | 71.78
Summary of Tower Quantities
|  |  |  | As per Detail survey |  |  |  |  | As per Check Survey
|  |  |  | Twr Type |  | Qty in Nos |  |  | Twr Type |  | Qty in Nos
|  |  |  | DA+0 | = | 18 |  |  | DA+0 | = | 18
|  |  |  | DA+3 | = | 8 |  |  | DA+3 | = | 8
|  |  |  | DA+6 | = | 4 |  |  | DA+6 | = | 4
|  |  |  | DA+9 | = | 5 |  |  | DA+9 | = | 5
|  |  |  | DB+0 | = | 1 |  |  | DB+0 | = | 1
|  |  |  | DB+3 | = | 2 |  |  | DB+3 | = | 2
|  |  |  | DB+6 | = | 0 |  |  | DB+6 | = | 0
|  |  |  | DB+9 | = | 1 |  |  | DB+9 | = | 1
|  |  |  | DC+0 | = | 10 |  |  | DC+0 | = | 10
|  |  |  | DC+3 | = | 0 |  |  | DC+3 | = | 0
|  |  |  | DC+6 | = | 1 |  |  | DC+6 | = | 1
|  |  |  | DC+9 | = | 0 |  |  | DC+9 | = | 0
|  |  |  | DD+0 | = | 3 |  |  | DD+0 | = | 3
|  |  |  | DD+3 | = | 0 |  |  | DD+3 | = | 0
|  |  |  | DD+6 | = | 0 |  |  | DD+6 | = | 0
|  |  |  | DD+9 | = | 0 |  |  | DD+9 | = | 0
|  |  |  | DD+18 | = | 0 |  |  | DD+18 | = | 0
|  |  |  | DD+25 | = | 0 |  |  | DD+25 | = | 0
|  |  |  | DD+30 | = | 0 |  |  | DD+30 | = | 0
|  |  |  | Total | = | 53 |  |  | Total | = | 53
FOR KEC INTERNATIONAL LTD | [13 empty] | FOR RAJASTHAN IV A POWER TRANSMISSION LTD.
SURVEYED BY: |  |  |  |  | CHECKED BY: |  |  |  | SUBMITTED BY: |  |  |  |  | CHECKED BY: |  |  |  |  | RECOMMENDED BY: | [5 empty] | APPROVED BY:

## Visual Chart
400 KV D/C (TWIN) FATEHGARH IV - BHINMAL (PG) TRANSMISSION LINE (VISUAL CHART)
Name of Contractor:M/S KEC INTERNATIONAL LIMITED | [20 empty] | AS ON |  | 2026-04-24 11:21
PROGRESS AT A GLANCE :
[17 empty] | Stringing WIP |  |  |  | Stringing Completed
| Sl. No. | Activity |  |  | UoM |  | Total Qty |  |  | Completed |  |  | Balance
[20 empty] | SH | NH
| 1 | Detail survey |  |  | Kms. |  | 188.678 |  |  | 188.678 |  |  | 0 |  |  | Rly. X-ing
| 2 | Check survey |  |  | Kms. |  | 188.678 |  |  | 188.678 |  |  | 0 | [9 empty] | Erection WIP
| 3 | CS Approval |  |  | Kms. |  | 188.678 |  |  | 188.678 |  |  | 0
| 4 | Soil Investigation |  |  | Loc |  | 73 |  |  | 73 |  |  | 0 |  |  | River Crossing |  |  |  | Span
| 5 | Foundation |  |  | Loc |  | 513 |  |  | 287 |  |  | 226
| 6 | Earthing |  |  | Nos. |  | 513 |  |  | 263 |  |  | 250 |  |  |  | Erection Comp
| 7 | Erection |  |  | Loc |  | 513 |  |  | 193 |  |  | 320 |  |  |  |  | Earthing |  |  | Excavation | 66/132/ 220/ 400
| 8 | Tack Welding |  |  | Nos. |  | 513 |  |  | 80 |  |  | 433
| 9 | Stringing(P/0) |  |  | Kms. |  | 188.678 |  |  | 17.997 |  |  | 170.681 |  |  |  | Pipe Line |  | Tack Welding |  |  |  | Oil Line
| 10 | Stringing (F/S) |  |  | Kms. |  | 188.678 |  |  | 16.337 |  |  | 172.341
[9 empty] | 2/1A 2/1B |  |  | 3/0A 3/0B
| GANTRY |  | AP1 |  | AP1A |  | AP2 | [7 empty] | 3/1 |  | AP4 |  | AP5 |  | 5/1 |  | 5/2
|  | 98 |  | 115 |  | 264 |  | 113 |  |  | 140 |  |  | 202 |  | 455 |  | 222 |  | 400 |  | 346 |  | 386 | 2741
| GANTRY |  | DE+0 |  | DD+0 |  | DD+0 |  |  | GANTRY UCS |  |  | GANTRY UCS |  | DD+3 |  | DD+18 |  | DD+9 |  | DA+0 |  | DA+0
[15 empty] | 1 MRC |  | 1MRC |  | 3 MRC |  |  |  | 1MRC
| 5/3 |  | 5/4 |  | 5/5 |  | 5/6 |  | AP5A |  | 5A/1 |  | AP5B |  | 5BA/0 |  | AP5C |  | AP5D |  | AP5E |  | AP6
[8 empty] | SH | [11 empty] | 132 KV
|  | 388 |  | 395 |  | 446 |  | 374 |  | 412 |  | 471 |  | 265 |  | 358 |  | 268 |  | 163 |  | 250 |  | 258 | 4048
| DA+0 |  | DA+0 |  | DA+0 |  | DA+6 |  | DD+9 |  | DB+9 |  | DC+6 |  | DC+6 |  | DD+9 |  | DC+6 |  | DD+3 |  | DC+0
|  |  | 1MRC |  | 1MRC |  | 2736 | [7 empty] | 1MRC
| AP6A |  | AP6B |  | 6B/1 |  | AP6C/0 |  | AP6D |  | 6D/1 |  | 6D/2 |  | 6D/3 |  | 6D/4 |  | 6D/5 |  | AP7 |  | 7/1
|  | 337 |  | 477 |  | 472 |  | 334 |  | 338 |  | 438 |  | 397 |  | 377 |  | 450 |  | 192 |  | 384 |  | 396 | 4592
| DC+0 |  | DB+9 |  | DB+9 |  | DD+6 |  | DC+6 |  | DA+9 |  | DA+0 |  | DA+0 |  | DA+0 |  | DD+18 |  | DC+9 |  | DA+0
[13 empty] | 1MRC |  |  |  | 2000
| 7/2 |  | 7/3 |  | 7/4 |  | 7/5 |  | 7/6 |  | 7/7 |  | 7/8 |  | 7/9 |  | 7/10 |  | AP8 |  | 8/1 |  | 8/2
|  | 393 |  | 332 |  | 352 |  | 389 |  | 395 |  | 400 |  | 388 |  | 408 |  | 402 |  | 372 |  | 411 |  | 379 | 4621
WIP
| DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DB+0 |  | DA+0 |  | DA+0
[15 empty] | 1MRC |  | 4239
| 8/3 |  | 8/4 |  | AP9 |  | 9A/0 |  | 9/2 |  | 9/3 |  | 9/4 |  | 9/5 |  | AP10 |  | 10/1 |  | 10/2 |  | 10/3
|  | 413 |  | 340 |  | 446 |  | 441 |  | 402 |  | 409 |  | 436 |  | 428 |  | 387 |  | 389 |  | 396 |  | 375 | 4862
| DA+0 |  | DA+3 |  | DC+0 |  | DB+9 |  | DA+0 |  | DA+3 |  | DA+6 |  | DB+6 |  | DC+3 |  | DA+3 |  | DA+0 |  | DA+3
|  |  | 1915 | [9 empty] | 1688
| 10/4 |  | 10/5 |  | 10/6 |  | 10/7 |  | 10/8 |  | 10/9 |  | 10/10 |  | 10/11 |  | 10/12 |  | 10/13 |  | 10/14 |  | 10/15
|  | 462 |  | 382 |  | 428 |  | 411 |  | 352 |  | 405 |  | 400 |  | 384 |  | 406 |  | 378 |  | 373 |  | 378 | 4759
wip
| DA+6 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+6
[7 empty] | 1 MRC |  | 3582 |  |  |  | 1 MRC | [9 empty] | 2724
| AP11 |  | 11/1 |  | 11/2 |  | 11/3 |  | 11/4 |  | 11/5 |  | 11/6 |  | AP12 |  | 12/1 |  | 12/2 |  | AP13 |  | 13/1
|  | 434 |  | 371 |  | 324 |  | 384 |  | 381 |  | 336 |  | 439 |  | 395 |  | 388 |  | 364 |  | 405 |  | 432 | 4653
WIP
1148
| DB+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB+0 |  | DA+0 |  | DA+3 |  | DC+0 |  | DA+9
[13 empty] | 2670 |  |  | A, B 1MRC |  |  | B, C Benching
| 13/2 |  | 13/3 |  | AP14 |  | 14/1 |  | AP15 |  | 15/1 |  | AP16 |  | 16/1 |  | AP17 |  | 17/1 |  | AP18 |  | 18/1
|  | 404 |  | 417 |  | 468 |  | 432 |  | 465 |  | 370 |  | 284 |  | 271 |  | 287 |  | 292 |  | 399 |  | 425 | 4514
| DA+6 |  | DA+3 |  | DB+0 |  | DB+9 |  | DC+9 |  | DA+6 |  | DD+0 |  | DA+0 |  | DB+0 |  | DA+0 |  | DC+0 |  | DA+6
|  |  | 1658 |  | 1 MRC | [5 empty] | 834 |  |  |  | 555 |  |  |  | 578 |  |  |  | 824
| AP19 |  | 19/1 |  | 19/2 |  | 19/3 |  | AP20 |  | 20/1 |  | 20/2 |  | 20/3 |  | 20/4 |  | 20/5 |  | 20/6 |  | AP21
|  | 384 |  | 403 |  | 355 |  | 400 |  | 287 |  | 391 |  | 364 |  | 338 |  | 348 |  | 419 |  | 409 |  | 359 | 4457
| DD+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+9 |  | DD+3
| D 1MRC | [5 empty] | 1542 |  |  |  | B 1MRC | [9 empty] | 3MRC | 2556
| 21/1 |  | 21/2 |  | AP22 |  | AP23 |  | 23/1 |  | 23/2 |  | 23/3 |  | AP24 |  | 24/1 |  | AP25 | 400 KV | 25/1A 25/1B |  | 25/2A 25/2B
[20 empty] | 117 |  | 101 |  | 220
|  | 443 |  | 363 |  | 160 |  | 300 |  | 293 |  | 357 |  | 341 |  | 363 |  | 326 | [6 empty] | 3384
| DA+0 |  | DA+6 |  | DB+3 |  | DD+0 |  | DB+3 |  | DA+0 |  | DA+0 |  | DC+9 |  | DA+9 |  | DD+6 |  | GANTRY UCS
|  |  | 1166 | [9 empty] | 991 |  |  |  | 690
| AP26 |  | AP27 |  | AP27A |  | 27A/1 |  | 27A/2 |  | 27B/0 |  | 27B/1 |  | 27B/2 |  | 27B/3 |  | 28/0 |  | 28/1 |  | 29/0
|  |  |  | 220 KV | [19 empty] | OIL Line
|  | 301 |  | 243 |  | 333 |  | 358 |  | 358 |  | 419 |  | 418 |  | 408 |  | 382 |  | 400 |  | 403 |  | 428 | 4451
| DB+0 |  | DC+9 |  | DD+9 |  | DA+0 |  | DA+6 |  | DC+0 |  | DA+6 |  | DA+0 |  | DA+9 |  | DB+3 |  | DA+3 |  | DB+9
[9 empty] | 1049 | [7 empty] | 1628 |  |  |  | 803
| .29/1 |  | 29/2 |  | .29/3 |  | 30/0 |  | 30/1 |  | 30/2 |  | 30/3 |  | 31/0 |  | AP 32 |  | 32/1 |  | 32/2 |  | 32/3
|  | 411 |  | 380 |  | 485 |  | 288 |  | 337 |  | 325 |  | 214 |  | 456 |  | 421 |  | 419 |  | 408 |  | 410 | 4554
| DA+6 |  | DA+9 |  | DB+9 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC+9 |  | DC+9 |  | DA+3 |  | DA+3 |  | DA+9
|  |  | 1225 | [9 empty] | 1164 | [9 empty] | 1658
| AP 33 |  | AP 34 |  | 34/1 |  | AP 35 |  | 35/1 |  | 36/0 |  | 36/1 |  | 36/2 |  | AP36A |  | 37/0 |  | 38/0 |  | 38/1
OIL Line
|  | 324 |  | 367 |  | 473 |  | 358 |  | 478 |  | 360 |  | 383 |  | 281 |  | 396 |  | 307 |  | 449 |  | 415 | 4591
358
| DB+0 |  | DC+6 |  | DA+9 |  | DC+9 |  | DA+9 |  | DC+6 |  | DA+9 |  | DA+0 |  | DD+0 |  | DD+0 |  | DB+0 |  | DB+6
[5 empty] | 840 |  |  |  | 836 | [5 empty] | 1024
| 38/2 |  | 38/3 |  | 38/4 |  | 38/5 |  | 39/0 |  | 39/1 |  | 39/2 |  | 39/3 |  | 39/4 |  | 40/0 |  | 40/1 |  | 40/2
|  | 404 |  | 415 |  | 424 |  | 412 |  | 327 |  | 301 |  | 354 |  | 426 |  | 395 |  | 370 |  | 437 |  | 398 | 4663
| DA+3 |  | DA+9 |  | DA+0 |  | DA+9 |  | DB+3 |  | DA+6 |  | DA+0 |  | DA+0 |  | DA+6 |  | DD+3 |  | DB+6 |  | DA+6
[7 empty] | 2070 | [9 empty] | 1803 | [5 empty] | 834
| AP41 |  | 41/1 |  | 41/2 |  | 41/3 |  | AP42 |  | 42/1 |  | 42/2 |  | 42/3 |  | 42/4 |  | 42/5 |  | 42/6 |  | 42/7
|  | 413 |  | 424 |  | 416 |  | 415 |  | 395 |  | 430 |  | 382 |  | 405 |  | 338 |  | 288 |  | 297 |  | 196 | 4399
| DB+0 |  | DA+9 |  | DA+0 |  | DA+9 |  | DC+3 |  | DA+9 |  | DCT+6 |  | DA+9 |  | DA+9 |  | DA+0 |  | DA+3 |  | DA+0 | 1907
[7 empty] | 1668 |  |  |  | 824 |  |  |  | 3MRC |  | 3MRC |  | Benching |  | 1MRC |  | Benching
| AP43 |  | AP44 |  | 44/1 |  | AP45 |  | 45/1 |  | 45/2 |  | 45/3 |  | 45/4 |  | AP46 |  | AP47 |  | 47/1 |  | 47/2
|  | NH | [15 empty] | Rly Xing
|  | 250 |  | 374 |  | 430 |  | 416 |  | 341 |  | 305 |  | 319 |  | 350 |  | 223 |  | 394 |  | 435 |  | 403 | 4240
[11 empty] | R | [11 empty] | wip
| DC+6 |  | DB+9 |  | DA+9 |  | DD+9 |  | DA+0 |  | DA+6 |  | DA+0 |  | DA+6 |  | DD+3 |  | DD+9 |  | DA+9 |  | DA+9 | 1232
|  |  | 3MRC |  | 3MRC | 805 |  |  | ROW | [5 empty] | 1732 | [7 empty] | ROW
| AP48 |  | AP49 |  | AP50 |  | AP51 |  | 51/1 |  | 51/2 |  | 51/3 |  | AP52 |  | 52/1 |  | AP53 |  | AP54 |  | 54/1
[6 empty] | 220 KV | [13 empty] | SH-40
|  | 423 |  | 353 |  | 275 |  | 465 |  | 374 |  | 417 |  | 381 |  | 392 |  | 375 |  | 249 |  | 384 |  | 331 | 4419
| DD+3 |  | DD+3 |  | DD+9 |  | DD+18 |  | DA+3 |  | DA+0 |  | DA+3 |  | DB+3 |  | DA+6 |  | DD+0 |  | DC+0 |  | DA+3
[5 empty] | 3MRC | [7 empty] | 1637 |  |  |  | 1MRC | 766
| 54/2 |  | 54/3 |  | AP55 |  | AP56 |  | 56/1 |  | 56/2 |  | 56/3 |  | 56/4 |  | 56/5 |  | AP57 |  | AP58 |  | AP59
132 KV
|  | 285 |  | 355 |  | 421 |  | 341 |  | 337 |  | 376 |  | 308 |  | 445 |  | 392 |  | 408 |  | 206 |  | 417 | 4291
| DA+6 |  | DA+3 | 1355 | DD+18 |  | DB+9 |  | DB+9 |  | DA+0 |  | DB+9 |  | DA+6 |  | DA+6 | 1145 | DB+9 |  | DB+9 |  | DC+9
|  |  | 1MRC |  | 3MRC |  | Benching & 3 MRC |  |  |  | 713 |  |  |  |  | B Leg & D 1 MRC |  |  | 1MRC &3MRC
| 59/1 |  | AP60 |  | 60/1 |  | 60/2 |  | 60/3 |  | AP61 |  | 61/1 |  | AP62 |  | 62/1 |  | 62/2 |  | 62/3 |  | 62/4
|  | 305 |  | 396 |  | 431 |  | 403 |  | 420 |  | 446 |  | 298 |  | 280 |  | 273 |  | 348 |  | 379 |  | 399 | 4378
| DA+0 |  | DD+0 |  | DA+9 |  | DA+3 |  | DA+9 |  | DC+0 |  | DA+9 | 744 | DB+0 |  | DA+0 |  | DA+0 |  | DA+9 |  | DA+6
| Benching | 722 |  |  | 3MRC |  |  |  | 1650 |  |  | B Leg A&D,C 1MRC |  |  |  | B Leg A&D,C 1MRC |  |  |  | B Leg A&D,C 1MRC
| 62/5 |  | AP63 |  | 63/1 |  | AP64 |  | 64/1 |  | 64/2 |  | 64/3 |  | 64/4 |  | 64/5 |  | 64/6 |  | 64/7 |  | AP65
|  | 439 |  | 360 |  | 380 |  | 384 |  | 442 |  | 397 |  | 395 |  | 432 |  | 408 |  | 426 |  | 393 |  | 432 | 4888
| DA+6 |  | DC+0 |  | DA+0 |  | DC+9 |  | DA+9 |  | DA+9 |  | DA+9 |  | DA+9 |  | DA+9 |  | DA+3 |  | DA+3 |  | DD+0
| 2118 |  |  |  | 740 |  |  |  | 3MRC |  | 1MRC | [9 empty] | 3277
| 65/1 |  | AP66 |  | 66/1 |  | 66/2 |  | 66/3 |  | 66/4 |  | AP67 |  | 67/1 |  | 67/2 |  | AP68 |  | AP69 |  | 69/1
|  | 426 |  | 402 |  | 437 |  | 402 |  | 436 |  | 392 |  | 403 |  | 412 |  | 438 |  | 410 |  | 380 |  | 397 | 4935
| DB+9 |  | DD+0 |  | DA+9 |  | DA+0 |  | DA+3 |  | DA+9 |  | DC+6 |  | DA+6 |  | DB+0 |  | DB+9 |  | DD+3 |  | DA+6
|  |  | 1MRC | [7 empty] | 2068 |  | 1MRC |  | 814
| 69/2 |  | 69/3 |  | AP70 |  | AP71 |  | 71/1 |  | 71/2 |  | 71/3 |  | AP72 |  | 72/1 |  | 72/2 |  | AP73 |  | 73/1
SH
|  | 415 |  | 353 |  | 389 |  | 238 |  | 291 |  | 346 |  | 319 |  | 307 |  | 347 |  | 300 |  | 317 |  | 454 | 4076
| DA+0 |  | DA+0 |  | DD+0 |  | DB+0 |  | DA+9 |  | DA+0 |  | DA+0 | 1193 | DD+0 |  | DA+3 |  | DA+3 |  | DB+0 |  | DA+0
|  |  | RC 1M | 1544 | [8 empty] | RC 1M |  | RC 1M & 3M |  | RC 1M & 3M |  | 954 |  |  |  | C&D-3MRC
75/7
| 73/2 |  | 73/3 |  | AP74 |  | 74/1 |  | AP75 |  | 75/1 |  | 75/2 |  | 75/3 |  | 75/4 |  | 75/5 |  | 75/6 |  | 75/7
|  | 385 |  | 418 |  | 410 |  | 385 |  | 345 |  | 332 |  | 394 |  | 388 |  | 340 |  | 393 |  | 329 |  | 399 | 4518
| DA+9 |  | DA+9 |  | DB+9 |  | DA+0 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0
|  |  | 1574 |  |  |  | 795 | [15 empty] | 2920
| AP76 |  | 76/1 |  | AP77 |  | 77/1 |  | 77/2 |  | 77/3 |  | 77/4 |  | 77/5 |  | AP78 |  | 78/1 |  | AP79 |  | 79/1
|  | 426 |  | 409 |  | 388 |  | 381 |  | 381 |  | 345 |  | 396 |  | 415 |  | 402 |  | 355 |  | 425 |  | 414 | 4737
| DC+0 |  | DA+6 |  | DB+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+6 |  | DC+0 |  | DA+3 |  | DD+0 |  | DA+9
|  |  | 835 | [11 empty] | 2306 |  |  |  | RC 1M | 757
| 79/2 |  | AP80 |  | 80/1 |  | AP81 |  | 81/1 |  | 81/2 |  | 81/3 |  | 81/4 |  | 81/5 |  | AP82 |  | 82/1 |  | 82/2
|  | 353 |  | 441 |  | 388 |  | 373 |  | 415 |  | 425 |  | 392 |  | 410 |  | 386 |  | 453 |  | 386 |  | 421 | 4843
| DA+0 |  | DB+3 |  | DA+9 |  | DB+9 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+6 |  | DB+3 |  | DA+6 |  | DA+3
| RC 1M | 1192 |  |  | 829 |  |  |  | RC 3M | [7 empty] | 2400 | [5 empty] | 1261
| AP83 |  | 83/1 |  | AP84 |  | AP85 |  | 85/1 |  | AP86 |  | 86/1 |  | 86/2 |  | AP87 |  | 87/1 |  | 87/2 |  | AP88
|  | 409 |  | 428 |  | 361 |  | 381 |  | 355 |  | 406 |  | 417 |  | 381 |  | 412 |  | 392 |  | 297 |  | 412 | 4651
| DC+0 |  | DA+3 |  | DC+6 |  | DC+0 |  | DA+0 |  | DD+0 |  | DA+6 |  | DA+0 |  | DC+0 |  | DA+3 |  | DA+9 |  | DC+6
|  |  | 837 | [5 empty] | 736 | [5 empty] | 1204 | [5 empty] | 1101
| AP89 |  | 89/1 |  | AP90 |  | 90/1 |  | AP91 |  | 91/1 |  | 91/2 |  | 91/3 |  | AP92 |  | AP93 |  | AP94 |  | AP95
SH
|  | 382 |  | 453 |  | 420 |  | 395 |  | 387 |  | 379 |  | 350 |  | 358 |  | 237 |  | 440 |  | 504 |  | 437 | 4742
| DC+0 |  | DA+9 |  | DC+0 |  | DA+9 |  | DD+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC+0 |  | DC+0 |  | DB+6 |  | DB+9
|  |  | 835 |  |  |  | 815 | [7 empty] | 1474
| 95/1 |  | 95/2 |  | AP95A |  | 95A/1 |  | AP96 |  | 96/1 |  | 96/2 |  | AP97 |  | 97/1 |  | AP98 |  | 98/1 |  | AP98A
|  | 430 |  | 409 |  | 312 |  | 314 |  | 362 |  | 329 |  | 371 |  | 418 |  | 377 |  | 344 |  | 319 |  | 308 | 4293
| DB+0 |  | DA+9 |  | DB+0 |  | DA+0 |  | DC+0 |  | DA+0 |  | DA+0 |  | DC+0 |  | DA+3 |  | DC+0 |  | DA+0 |  | DC+0
|  |  | 839 |  |  |  | 627 | [5 empty] | 1063 |  |  |  | 795 |  |  |  | 662
| 98A/1 |  | AP98B |  | 98B/1 |  | 98B/2 |  | AP99 |  | 99/1 |  | 99/2 |  | 99/3 |  | 99/4 |  | 99A/0 |  | 99B/0 |  | 99C/0
OIL Line
|  | 325 |  | 365 |  | 260 |  | 360 |  | 414 |  | 424 |  | 404 |  | 430 |  | 406 |  | 423 |  | 286 |  | 424 | 4521
| DA+0 |  | DD+0 |  | DA+0 |  | DCT+0 |  | DC+0 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+3 |  | DB+6 |  | DD+0 |  | DD+0
| 633 |  |  |  | 1MRC | 625 | [10 empty] | 2079
| 99C/1 |  | 99C/2 |  | AP100 |  | 100/1 |  | AP101 |  | AP102 |  | 102/1 |  | 102/2 |  | AP103 |  | 103/1 |  | AP104 |  | AP104A
|  | 420 |  | 424 |  | 387 |  | 453 |  | 387 |  | 382 |  | 336 |  | 389 |  | 335 |  | 396 |  | 233 |  | 467 | 4609
| DA+6 |  | DA+3 |  | DC+0 |  | DA+6 |  | DD+0 |  | DD+3 |  | DA+0 |  | DA+0 |  | DC+0 |  | DA+6 |  | DD+0 |  | DC+9
|  |  | 1268 |  |  |  | 840 | [7 empty] | 1108 |  |  |  | 731
| AP104B |  | 104B/1 |  | 104B/2 |  | AP105 |  | 105/1 |  | AP106 |  | AP107 |  | 107/1 |  | AP108 |  | AP109 |  | AP109A |  | AP110
|  | 423 |  | 249 |  | 282 |  | 398 |  | 370 |  | 437 |  | 435 |  | 407 |  | 388 |  | 441 |  | 410 |  | 444 | 4684
P
| DB+9 |  | DA+0 |  | DA+0 |  | DD+0 |  | DA+3 |  | DC+6 |  | DD+3 |  | DA+9 |  | DC+0 |  | DC+3 |  | DB+6 |  | DC+0
[5 empty] | 3MRC | 954 |  |  | 768 | [5 empty] | 842 |  | 1MRC
| AP111 |  | AP112 |  | AP113 |  | AP113A |  | AP114 |  | 114/1 |  | AP115 |  | 115/1 |  | AP116 |  | 116/1 |  | AP117 |  | 117/1
132 KV
|  | 190 |  | 158 |  | 201 |  | 165 |  | 404 |  | 435 |  | 425 |  | 441 |  | 358 |  | 438 |  | 430 |  | 410 | 4055
| DB+9 |  | DC+9 |  | DD+0 |  | DC+0 |  | DC+0 |  | DA+9 |  | DC+0 |  | DB+9 |  | DD+0 |  | DA+0 |  | DD+0 |  | DA+3
[11 empty] | 839 | [7 empty] | 796
| 117/2 |  | AP118 |  | AP119 |  | 119/1 |  | 119/2 |  | AP120 |  | 120/1 |  | AP121 |  | AP122 |  | 122/1 |  | 122/2 |  | AP123
NH 754
|  | 440 |  | 424 |  | 439 |  | 395 |  | 401 |  | 413 |  | 402 |  | 251 |  | 426 |  | 382 |  | 352 |  | 419 | 4744
P
| DB+9 |  | DC+3 |  | DD+3 |  | DA+3 |  | DA+3 |  | DC+0 |  | DA+6 |  | DC+0 |  | DC+6 |  | DA+3 |  | DA+3 |  | DC+0
| 840 | [7 empty] | 1235 |  |  |  | 815 | [7 empty] | 1159
| AP124 |  | AP125 |  | 125/1 |  | 125/2 |  | 125/3 |  | AP126 |  | 126/1 |  | 126/2 |  | 126/3 |  | AP127 |  | 127/1 |  | AP128
|  | 422 |  | 403 |  | 355 |  | 355 |  | 344 |  | 390 |  | 421 |  | 334 |  | 388 |  | 398 |  | 443 |  | 415 | 4668
| DC+3 |  | DC+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC+6 |  | DA+6 |  | DA+3 |  | DA+6 |  | DD+6 |  | DA+9 |  | DC+3
[9 empty] | 1457 | [7 empty] | 1534 |  |  |  | 841
| 128/1 |  | AP129 |  | 129/1 |  | 129/2 |  | AP130 |  | 130/1 |  | AP131 |  | 131/1 |  | 131/2 |  | AP132 |  | 132/1 |  | 132/2
SH 16
|  | 418 |  | 424 |  | 415 |  | 412 |  | 268 |  | 259 |  | 395 |  | 408 |  | 356 |  | 379 |  | 367 |  | 384 | 4485
| DA+6 |  | DC+0 |  | DA+3 |  | DA+9 |  | DC+6 |  | DA+0 |  | DD+0 |  | DA+3 |  | DA+3 |  | DD+0 |  | DA+0 |  | DA+0
| 833 | [5 empty] | RC 3M | 1251 |  |  | 527 | [5 empty] | 1159
| 132/3 |  | 132/4 |  | AP133 |  | 133/1 |  | 133/2 |  | 133/3 |  | 133/4 |  | 133/5 |  | 133/6 |  | 133/7 |  | 133/8 |  | AP134
OIL Line
|  | 385 |  | 419 |  | 343 |  | 392 |  | 390 |  | 372 |  | 388 |  | 414 |  | 410 |  | 415 |  | 360 |  | 226 | 4514
| DA+0 |  | DA+0 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+6 |  | DD+0
|  |  | 1934 | [5 empty] | 1M RC | [11 empty] | 3486
| AP134A |  | 134A/1 |  | 134A/2 |  | 134A/3 |  | 134A/4 |  | AP135 |  | 135/1 |  | 135/2 |  | 135/3 |  | AP136 |  | AP137 |  | AP138
|  | 438 |  | 402 |  | 433 |  | 409 |  | 437 |  | 394 |  | 403 |  | 356 |  | 378 |  | 356 |  | 427 |  | 381 | 4814
| DD+0 |  | DA+9 |  | DA+3 |  | DA+6 |  | DA+9 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DD+0 |  | DB+3 |  | DB+3
[5 empty] | RC 3M |  |  |  | 2120 | [7 empty] | 1513
| 138/1 |  | 138/2 |  | 138/3 |  | AP139 |  | 139/1 |  | AP140 |  | 140/1 |  | 140/2 |  | 140/3 |  | AP141 |  | 141/1 |  | 141/2
|  | 334 |  | 347 |  | 376 |  | 392 |  | 408 |  | 392 |  | 405 |  | 435 |  | 378 |  | 386 |  | 391 |  | 400 | 4644
| DA+0 |  | DA+0 |  | DA+0 |  | DC+3 |  | DA+9 |  | DB+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DC+0 |  | DA+0 |  | DA+6
[5 empty] | 1438 |  |  |  | 800 | [7 empty] | 1610 | [5 empty] | 1177
| AP142 |  | AP143 |  | 143/1 |  | 143/2 |  | 143/3 |  | 143/4 |  | 143/5 |  | 143/6 |  | 143/7 |  | AP144 | 132 KV | AP145 |  | 145/1
|  | 437 |  | 402 |  | 416 |  | 417 |  | 399 |  | 420 |  | 409 |  | 412 |  | 400 |  | 232 |  | 442 |  | 385 | 4771
| DC+3 |  | DC+3 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DD+6 |  | DD+6 |  | DA+3
3275
| 145/2 |  | 145/3 |  | 145/4 |  | AP146 |  | 146/1 |  | 146/2 |  | AP147 |  | 147/1 |  | 147/2 |  | 147/3 |  | 147/4 |  | 147/5
|  | 362 |  | 399 |  | 382 |  | 392 |  | 422 |  | 409 |  | 374 |  | 382 |  | 382 |  | 391 |  | 386 |  | 367 | 4648
| DA+0 |  | DA+0 |  | DA+3 |  | DC+0 |  | DA+3 |  | DA+0 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0
[6 empty] | 1970 | [5 empty] | 1223
| 147/6 |  | 147/7 |  | 147/8 |  | 147/9 |  | AP148 |  | 148/1 |  | 148/2 |  | 148/3 |  | 148/4 |  | 148/5 |  | 148/6 |  | 148/7
SH 31
|  | 380 |  | 380 |  | 383 |  | 242 |  | 364 |  | 359 |  | 384 |  | 381 |  | 397 |  | 387 |  | 392 |  | 365 | 4414
| DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0
[7 empty] | 3666 | [15 empty] | 3031
| AP149 |  | AP149A |  | AP149B |  | AP149B/1 |  | 149B/2 |  | 149B/3 |  | AP150 |  | AP151 |  | AP152 |  | AP153 |  | AP153A |  | AP154
[14 empty] | RLY XING |  |  |  | 220 KV
OIL Line
|  | 188 |  | 396 |  | 425 |  | 407 |  | 433 |  | 489 |  | 290 |  | 419 |  | 243 |  | 343 |  | 389 |  | 71 | 4093
| DD+0 |  | DD+0 |  | DB+3 |  | DA+3 |  | DA+0 |  | DB+9 |  | DD+9 |  | DD+9 |  | DD+18 |  | DD+18 |  | DB+0 |  | DD+0
1265
|  |  | 400 KV |  |  |  | AP155 |  | AP156 |  | AP157 |  | GANTRY
|  |  | 92 |  |  | 55 |  | 243 |  | 215 |  | 114 | [12 empty] | 719
|  | GANTRY UCS |  |  | GANTRY UCS |  | DD+0 |  | DD+0 |  | DD+0 (Aux) |  | PGCIL GANTRY
| 154/1A 154/1B |  |  |  | 154/2A 154/2B
ṅ
z
z
z
WIP
BAYTU SINDHARI
SHEO BAYTU
SHINDHARI BHINMAL

## L2 Vs Actual Progress Chart
NAME OF LINE: 400kV Transmisison Line Fatehgarh IV to Bhinmal
As Per L2
Sl. No. | ACTIVITY | Responsibility | Sch. Start date | Sch. Finish date | Days | Unit | Quantity | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26 | Feb'26 | Mar'26 | Apr'26 | May'26 | June'26
[8 empty] | M0 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18
1 | Notice of Award | KEC & Apraava | 2024-12-06 | 2026-06-05 | 546
Services
1 | Establishment of site office | KEC | 2024-12-16 | 2025-01-15 | 30 | LS
| Check Survey Submission & Approval | KEC & Apraava | 2025-01-05 | 2025-04-15 | 100 | Kms. | 184 | M1: 20; M2: 60; M3: 60; M4: 44
5.a | ROW clearance and front avaibility for Civil foundation | Apraava | 25.12.24 | 30.12.25 | #VALUE! | Loc. | 508 | 5 | 35 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 45 | 48 | 50 | 45
5.b | Foundation Work execution | KEC | 2025-01-07 | 2026-01-26 | 384 | Loc. | 508 |  | 35 | 40 | 40 | 40 | 40 | 40 | 30 | 25 | 25 | 48 | 45 | 50 | 48
Note | ROW / Way leave clearance / Forest clearance / Tree Cutting clearance / any other Statutory clearance to be arranged suitably ahead of respective work schedule by | [6 empty] | M3: 185
Any delay due to ROW / Statutory approvals / Railway, Forest, NHAI , etc shall be on account of Apraava.
| The L2 schedule is formulated considering average rainfall / heat in these areas, any unprecedented rain / heat waves will have an impact on overall completion schedule. | [6 empty] | M3: 24; M4: 586.2478; M6: 540.792; M8: -69.2478; M9: 139.2
Actual Done
Sl. No. | ACTIVITY | Responsibility | Sch. Start date | Sch. Finish date | Days | Unit | Quantity | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26 | Feb'26 | Mar'26 | Apr'26 | May'26 | June'26
[8 empty] | M0 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18
1 | Notice of Award | KEC & Apraava | 2024-12-06 | 2026-06-05 | 546
Services
1 | Establishment of site office | KEC | 2024-12-16 | 2025-01-15 | 30 | LS |  | M1: 100%
| Check Survey Submission & Approval | KEC & Apraava | 2025-01-05 | 2025-04-15 | 100 | Kms. | 184 | M1: 28
5.a | ROW clearance and front avaibility for Civil foundation | Apraava | 25.12.24 | 30.12.25 | #VALUE! | Loc. | 508 | M1: 4
5.b | Foundation Work execution | KEC | 2025-01-07 | 2026-01-26 | 384 | Loc. | 508 | M1: 2; M2: 20; M3: 16; M4: 13; M5: 9; M6: 25; M7: 50; M8: 14
185
5
Formulas:
Sch. Finish date = [Sch. Start date]+30
Sch. Finish date = [Sch. Start date]+364+20

## L2 Vs Actual Progress Chart (2) (hidden)
NAME OF LINE: 400kV Transmisison Line Fatehgarh IV to Bhinmal
As Per L2
Sl. No. | ACTIVITY | Responsibility | Sch. Start date | Sch. Finish date | Days | Unit | Quantity | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26 | Feb'26 | Mar'26 | Apr'26 | May'26 | June'26
[8 empty] | M0 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18
1 | Notice of Award | KEC & Apraava | 2024-12-06 | 2026-06-05 | 546
Services
1 | Establishment of site office | KEC | 2024-12-16 | 2025-01-15 | 30 | LS
| Check Survey Submission & Approval | KEC & Apraava | 2025-01-05 | 2025-04-15 | 100 | Kms. | 184 | M1: 20; M2: 60; M3: 60; M4: 44
5.a | ROW clearance and front avaibility for Civil foundation | Apraava | 25.12.24 | 30.12.25 | #VALUE! | Loc. | 508 | 5 | 35 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 45 | 48 | 50 | 45
5.b | Foundation Work execution | KEC | 2025-01-07 | 2026-01-26 | 384 | Loc. | 508 |  | 35 | 40 | 40 | 40 | 40 | 40 | 30 | 25 | 25 | 48 | 45 | 50 | 48
Note | ROW / Way leave clearance / Forest clearance / Tree Cutting clearance / any other Statutory clearance to be arranged suitably ahead of respective work schedule by
Any delay due to ROW / Statutory approvals / Railway, Forest, NHAI , etc shall be on account of Apraava.
The L2 schedule is formulated considering average rainfall / heat in these areas, any unprecedented rain / heat waves will have an impact on overall completion schedule.
Actual Done
Sl. No. | ACTIVITY | Responsibility | Sch. Start date | Sch. Finish date | Days | Unit | Quantity | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26 | Feb'26 | Mar'26 | Apr'26 | May'26 | June'26
[8 empty] | M0 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18
1 | Notice of Award | KEC & Apraava | 2024-12-06 | 2026-06-05 | 546
Services
1 | Establishment of site office | KEC | 2024-12-16 | 2025-01-15 | 30 | LS |  | M1: 100%
| Check Survey Submission & Approval | KEC & Apraava | 2025-01-05 | 2025-04-15 | 100 | Kms. | 184 | M1: 28
5.a | ROW clearance and front avaibility for Civil foundation | Apraava | 25.12.24 | 30.12.25 | #VALUE! | Loc. | 508 | M1: 4
5.b | Foundation Work execution | KEC | 2025-01-07 | 2026-01-26 | 384 | Loc. | 508 | M1: 2; M2: 20; M3: 16; M4: 13; M5: 9
Formulas:
Sch. Finish date = [Sch. Start date]+30
Sch. Finish date = [Sch. Start date]+364+20

## Sheet4 (hidden)
Activity | As Per L2
| Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26 | Feb'26 | Mar'26 | Apr'26 | May'26 | June'26
Check Survey (Kms) |  | 20 | 60 | 60 | 44
Actual Progress |  | 28
Foundation (Nos) |  | 35 | 40 | 40 | 40 | 40 | 40 | 30 | 25 | 25 | 48 | 45 | 50 | 48
ROW Front Clearence | 5 | 35 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 45 | 48 | 50 | 45
Actual Foundation Completed (Nos) |  | 3
WIP |  | 2
Work Stopped
Front Availaibility |  | 8