## Definition
Point | Detail
Current FE cohort metric definition | Foundation completion date to tower erection START date.
30-day rule | A foundation is counted within 30D when erection start - foundation completion is between 0 and 30 days inclusive.
Completion-date alternative | Also computed here. It answers a stricter question: complete erection within 30 days of foundation completion.
MD recommendation | Use start-based only if the business definition is pickup/start within 30 days. If the MD expects full tower completion within 30 days, use completion-based figures.

## 30D Definition Comparison
Cohort | Definition | Horizon Days | Foundation Locations | Eligible Locations | Within Horizon | % Within Horizon | Full Cohort Exposure
Apr-Jun 2025 | Foundation complete -> erection start | 30 | 532 | 532 | 24 | 4.5 | Yes
Apr-Jun 2026 | Foundation complete -> erection start | 30 | 466 | 466 | 120 | 25.8 | Yes
Apr-Jun 2025 | Foundation complete -> erection complete | 30 | 532 | 532 | 20 | 3.8 | Yes
Apr-Jun 2026 | Foundation complete -> erection complete | 30 | 466 | 466 | 85 | 18.2 | Yes

## Apr-Jun Detail
Cohort | Definition | Horizon Days | Foundation Locations | Eligible Locations | Within Horizon | % Within Horizon | Full Cohort Exposure
2025-04 | Foundation complete -> erection start | 30 | 201 | 201 | 7 | 3.5 | Yes
2025-05 | Foundation complete -> erection start | 30 | 192 | 192 | 10 | 5.2 | Yes
2025-06 | Foundation complete -> erection start | 30 | 139 | 139 | 7 | 5 | Yes
2026-04 | Foundation complete -> erection start | 30 | 117 | 117 | 32 | 27.4 | Yes
2026-05 | Foundation complete -> erection start | 30 | 179 | 179 | 44 | 24.6 | Yes
2026-06 | Foundation complete -> erection start | 30 | 170 | 170 | 44 | 25.9 | Yes
2025-04 | Foundation complete -> erection start | 60 | 201 | 201 | 13 | 6.5 | Yes
2025-05 | Foundation complete -> erection start | 60 | 192 | 192 | 23 | 12 | Yes
2025-06 | Foundation complete -> erection start | 60 | 139 | 139 | 20 | 14.4 | Yes
2026-04 | Foundation complete -> erection start | 60 | 117 | 117 | 43 | 36.8 | Yes
2026-05 | Foundation complete -> erection start | 60 | 179 | 179 | 68 | 38 | Yes
2026-06 | Foundation complete -> erection start | 60 | 170 | 68 | 30 | 44.1 | No
2025-04 | Foundation complete -> erection complete | 30 | 201 | 201 | 6 | 3 | Yes
2025-05 | Foundation complete -> erection complete | 30 | 192 | 192 | 9 | 4.7 | Yes
2025-06 | Foundation complete -> erection complete | 30 | 139 | 139 | 5 | 3.6 | Yes
2026-04 | Foundation complete -> erection complete | 30 | 117 | 117 | 22 | 18.8 | Yes
2026-05 | Foundation complete -> erection complete | 30 | 179 | 179 | 29 | 16.2 | Yes
2026-06 | Foundation complete -> erection complete | 30 | 170 | 170 | 34 | 20 | Yes
2025-04 | Foundation complete -> erection complete | 60 | 201 | 201 | 12 | 6 | Yes
2025-05 | Foundation complete -> erection complete | 60 | 192 | 192 | 22 | 11.5 | Yes
2025-06 | Foundation complete -> erection complete | 60 | 139 | 139 | 14 | 10.1 | Yes
2026-04 | Foundation complete -> erection complete | 60 | 117 | 117 | 42 | 35.9 | Yes
2026-05 | Foundation complete -> erection complete | 60 | 179 | 179 | 58 | 32.4 | Yes
2026-06 | Foundation complete -> erection complete | 60 | 170 | 68 | 27 | 39.7 | No

## Join Checks
Check | Rows | Pass Rows | Pass %
Official matched rows with erection completion date joined | 3271 | 3218 | 98.38
Official foundation evidence rows | 3972 | 3972 | 100

## Raw Trace Summary
Trace Check | Rows | Pass Rows | Pass %
Sample foundation loc+date found directly in raw DPR | 23 | 23 | 100
Sample erection loc+start found directly in raw DPR | 16 | 16 | 100
Sample erection loc+complete found directly in raw DPR | 16 | 16 | 100

## Raw Trace Sample
Project | Location | Foundation Date | Erection Start | Erection Complete | Delay to Start | Delay to Completion | Start <=30D | Completion <=30D | Foundation Source File | Foundation Source Sheet | Raw Foundation Loc+Date Found | Raw Foundation Row | Raw Foundation Evidence | Foundation Load Note | Erection Source File | Erection Source Sheet | Raw Erection Loc+Start Found | Raw Erection Start Row | Raw Erection Start Evidence | Raw Erection Loc+Complete Found | Raw Erection Complete Row | Raw Erection Complete Evidence | Erection Load Note
TA 601 | 56/12 | 2026-06-12 | 2026-06-29 | 2026-07-05 | 17 | 23 | TRUE | TRUE | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | Yes | 143 | loc_cols=[3]; date_cols=[13] |  | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled | Yes | 93 | loc_cols=[2]; date_cols=[5] | Yes | 93 | loc_cols=[2]; date_cols=[8]
TA 601 | 99/3 | 2026-06-22 | 2026-07-07 | 2026-07-12 | 15 | 20 | TRUE | TRUE | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | Yes | 149 | loc_cols=[3]; date_cols=[13] |  | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled | Yes | 102 | loc_cols=[2]; date_cols=[5] | Yes | 102 | loc_cols=[2]; date_cols=[8]
TA 414 | 229/0 | 2026-05-31 | 2026-06-15 | 2026-06-29 | 15 | 29 | TRUE | TRUE | TA 414 - DPR - 2026-08-12.xlsx | FDN | Yes | 328 | loc_cols=[2]; date_cols=[13] | XML scrub fallback used for sheet 'FDN' | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled | Yes | 275 | loc_cols=[2]; date_cols=[4] | Yes | 275 | loc_cols=[2]; date_cols=[7] | XML scrub fallback used for sheet 'Erection Compiled'
TB 501 | 33/0 (New) | 2026-04-09 | 2026-05-08 | 2026-05-12 | 29 | 33 | TRUE | FALSE | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | Yes | 404 | loc_cols=[2]; date_cols=[45] |  | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | Yes | 404 | loc_cols=[2]; date_cols=[57] | Yes | 404 | loc_cols=[2]; date_cols=[58]
TA 419 | 48/1 | 2026-06-13 | 2026-07-01 | 2026-07-08 | 18 | 25 | TRUE | TRUE | TA 419 - DPR - 2026-08-11.xlsx | FDN | Yes | 187 | loc_cols=[2]; date_cols=[9] | XML scrub fallback used for sheet 'FDN' | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED | Yes | 186 | loc_cols=[2]; date_cols=[5] | Yes | 186 | loc_cols=[2]; date_cols=[6] | XML scrub fallback used for sheet 'ERECTION COMPILED'
TB 507 | 10/14 | 2026-04-23 | 2026-05-13 | 2026-05-16 | 20 | 23 | TRUE | TRUE | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | Yes | 294 | loc_cols=[2]; date_cols=[13] |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled | Yes | 208 | loc_cols=[2]; date_cols=[5] | Yes | 208 | loc_cols=[2]; date_cols=[11]
TB 507 | 8/3 | 2026-05-17 | 2026-05-24 | 2026-05-28 | 7 | 11 | TRUE | TRUE | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | Yes | 310 | loc_cols=[2]; date_cols=[13] |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled | Yes | 215 | loc_cols=[2]; date_cols=[5] | Yes | 215 | loc_cols=[2]; date_cols=[11]
TA 419 | 40/1 | 2026-04-29 | 2026-05-08 | 2026-05-14 | 9 | 15 | TRUE | TRUE | TA 419 - DPR - 2026-08-11.xlsx | FDN | Yes | 152 | loc_cols=[2]; date_cols=[9] | XML scrub fallback used for sheet 'FDN' | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED | Yes | 151 | loc_cols=[2]; date_cols=[5] | Yes | 151 | loc_cols=[2]; date_cols=[6] | XML scrub fallback used for sheet 'ERECTION COMPILED'
TA 601 | 60/0 | 2026-04-06 | 2026-05-05 | 2026-05-18 | 29 | 42 | TRUE | FALSE | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | Yes | 114 | loc_cols=[3]; date_cols=[13] |  | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled | Yes | 73 | loc_cols=[2]; date_cols=[5] | Yes | 73 | loc_cols=[2]; date_cols=[8]
TB 605 | 35/1 | 2026-06-03 | 2026-06-14 | 2026-06-24 | 11 | 21 | TRUE | TRUE | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | Yes | 111 | loc_cols=[2]; date_cols=[11, 12] |  | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu | Yes | 95 | loc_cols=[2]; date_cols=[6] | Yes | 95 | loc_cols=[2]; date_cols=[7]
TB 507 | 154/1A | 2026-05-09 |  |  |  |  | FALSE | FALSE | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | Yes | 305 | loc_cols=[2]; date_cols=[13] |  |  |  | Unmatched |  |  | Unmatched
TB 605 | AP166 | 2026-04-30 | 2026-06-21 | 2026-06-28 | 52 | 59 | FALSE | FALSE | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | Yes | 169 | loc_cols=[2]; date_cols=[11, 12] |  | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab | Yes | 154 | loc_cols=[2]; date_cols=[6] | Yes | 154 | loc_cols=[2]; date_cols=[7]
TA 414 | 165/0 | 2026-05-09 | 2026-06-17 | 2026-07-02 | 39 | 54 | FALSE | FALSE | TA 414 - DPR - 2026-08-12.xlsx | FDN | Yes | 312 | loc_cols=[2]; date_cols=[13] | XML scrub fallback used for sheet 'FDN' | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled | Yes | 122 | loc_cols=[2]; date_cols=[4] | Yes | 122 | loc_cols=[2]; date_cols=[7] | XML scrub fallback used for sheet 'Erection Compiled'
TB 605 | AP105 | 2026-05-30 |  |  |  |  | FALSE | FALSE | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | Yes | 216 | loc_cols=[2]; date_cols=[11, 12, 14] |  |  |  | Unmatched |  |  | Unmatched
TA 414 | 129/0 | 2026-05-11 |  |  |  |  | FALSE | FALSE | TA 414 - DPR - 2026-08-12.xlsx | FDN | Yes | 253 | loc_cols=[2]; date_cols=[13] | XML scrub fallback used for sheet 'FDN' | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled | Unmatched |  |  | Unmatched
TB 608 | 7/1 | 2026-04-21 |  |  |  |  | FALSE | FALSE | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN | Yes | 331 | loc_cols=[2]; date_cols=[8] |  |  |  | Unmatched |  |  | Unmatched
TB 605 | AP1 | 2026-04-18 |  |  |  |  | FALSE | FALSE | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | Yes | 95 | loc_cols=[2]; date_cols=[8, 9, 10, 11, 12] |  |  |  | Unmatched |  |  | Unmatched
TA 601 | 48/3 | 2026-05-19 | 2026-06-26 | 2026-07-03 | 38 | 45 | FALSE | FALSE | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | Yes | 131 | loc_cols=[3]; date_cols=[13] |  | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled | Yes | 91 | loc_cols=[2]; date_cols=[5] | Yes | 91 | loc_cols=[2]; date_cols=[8]
TA 419 | 65/1 | 2026-06-06 | 2026-07-13 | 2026-07-22 | 37 | 46 | FALSE | FALSE | TA 419 - DPR - 2026-08-11.xlsx | FDN | Yes | 249 | loc_cols=[2]; date_cols=[9] | XML scrub fallback used for sheet 'FDN' | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED | Yes | 248 | loc_cols=[2]; date_cols=[5] | Yes | 248 | loc_cols=[2]; date_cols=[6] | XML scrub fallback used for sheet 'ERECTION COMPILED'
TB 605 | 61/1 | 2026-05-08 |  |  |  |  | FALSE | FALSE | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | Yes | 182 | loc_cols=[2]; date_cols=[11, 12, 14] |  |  |  | Unmatched |  |  | Unmatched
TA 419 | 13/0 | 2026-04-15 | 2026-05-10 | 2026-05-30 | 25 | 45 | TRUE | FALSE | TA 419 - DPR - 2026-08-11.xlsx | FDN | Yes | 67 | loc_cols=[2]; date_cols=[9] | XML scrub fallback used for sheet 'FDN' | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED | Yes | 66 | loc_cols=[2]; date_cols=[5] | Yes | 66 | loc_cols=[2]; date_cols=[6] | XML scrub fallback used for sheet 'ERECTION COMPILED'
TB 507 | 5/1 | 2026-04-02 |  |  |  |  | FALSE | FALSE | TB 507 - DPR - 2026-08-12.xlsx | Foundation | Yes | 23 | loc_cols=[2]; date_cols=[14] |  |  |  | Unmatched |  |  | Unmatched
TB 608 | 92/0 | 2026-04-13 | 2026-06-28 | 2026-07-10 | 76 | 88 | FALSE | FALSE | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN | Yes | 128 | loc_cols=[2]; date_cols=[8] |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-ERC | Yes | 53 | loc_cols=[2]; date_cols=[7] | Yes | 53 | loc_cols=[2]; date_cols=[8]

## Official Fact With Complete
Project | Location | Foundation Date | Erection Start | complete | delay_to_start_days | delay_to_completion_days | foundation_month | exposure_days | start_within_30d | completion_within_30d | Matched | Negative Excluded | Match Basis | Foundation Source File | Foundation Source Sheet | Erection Source File | Erection Source Sheet
TA 413 | 9/4 | 2024-06-06 | 2025-03-05 | 2025-03-09 | 272 | 276 | 2024-06 | 797 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 10/1 | 2024-06-07 | 2025-10-12 | 2025-10-31 | 492 | 511 | 2024-06 | 796 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 10/2 | 2024-06-09 | 2025-11-01 | 2025-11-09 | 510 | 518 | 2024-06 | 794 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 9/11 | 2024-06-11 | 2025-10-18 | 2025-10-28 | 494 | 504 | 2024-06 | 792 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 15/2 | 2024-06-17 | 2025-03-14 | 2025-03-18 | 270 | 274 | 2024-06 | 786 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 9/5 | 2024-06-17 | 2025-08-15 | 2025-08-19 | 424 | 428 | 2024-06 | 786 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 15/3 | 2024-06-18 | 2025-03-19 | 2025-03-22 | 274 | 277 | 2024-06 | 785 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 15/4 | 2024-06-21 | 2025-03-23 | 2025-03-27 | 275 | 279 | 2024-06 | 782 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 9/3 | 2024-06-23 | 2025-03-01 | 2025-03-04 | 251 | 254 | 2024-06 | 780 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 15/5 | 2024-06-24 | 2025-03-26 | 2025-03-31 | 275 | 280 | 2024-06 | 779 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 8/5 | 2024-06-26 | 2025-01-04 | 2025-01-09 | 192 | 197 | 2024-06 | 777 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 15/6 | 2024-06-27 | 2025-03-31 | 2025-04-06 | 277 | 283 | 2024-06 | 776 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 9/10 | 2024-06-28 | 2025-10-31 | 2025-11-05 | 490 | 495 | 2024-06 | 775 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 9/2 | 2024-06-29 | 2025-03-10 | 2025-03-13 | 254 | 257 | 2024-06 | 774 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 15/9 | 2024-07-03 | 2025-11-22 | 2025-11-28 | 507 | 513 | 2024-07 | 770 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 8/6 | 2024-07-03 | 2025-01-10 | 2025-01-15 | 191 | 196 | 2024-07 | 770 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 15/8 | 2024-07-06 | 2025-09-27 | 2025-10-04 | 448 | 455 | 2024-07 | 767 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 31/9 | 2024-07-06 | 2025-08-23 | 2025-09-03 | 413 | 424 | 2024-07 | 767 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 8/7 | 2024-07-09 | 2025-01-16 | 2025-01-20 | 191 | 195 | 2024-07 | 764 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 15/10 | 2024-07-10 | 2025-11-16 | 2025-11-21 | 494 | 499 | 2024-07 | 763 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 31/8 | 2024-07-10 | 2025-09-15 | 2025-09-21 | 432 | 438 | 2024-07 | 763 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 9/1 | 2024-07-10 | 2025-02-24 | 2025-02-28 | 229 | 233 | 2024-07 | 763 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 15/7 | 2024-07-11 | 2025-11-10 | 2025-11-15 | 487 | 492 | 2024-07 | 762 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 31/7 | 2024-07-15 | 2025-09-10 | 2025-09-16 | 422 | 428 | 2024-07 | 758 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 15/11 | 2024-07-18 | 2025-12-07 | 2025-12-21 | 507 | 521 | 2024-07 | 755 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 8/8 | 2024-07-19 | 2025-01-20 | 2025-01-25 | 185 | 190 | 2024-07 | 754 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 8/1 | 2024-07-20 | 2024-12-07 | 2024-12-16 | 140 | 149 | 2024-07 | 753 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 31/6 | 2024-07-22 | 2025-09-04 | 2025-09-18 | 409 | 423 | 2024-07 | 751 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 29/4 | 2024-07-24 | 2024-10-03 | 2024-10-08 | 71 | 76 | 2024-07 | 749 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 8/2 | 2024-07-25 | 2025-02-03 | 2025-02-08 | 193 | 198 | 2024-07 | 748 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 8/9 | 2024-07-25 | 2025-01-25 | 2025-01-30 | 184 | 189 | 2024-07 | 748 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 31/10 | 2024-07-28 | 2025-08-15 | 2025-08-25 | 383 | 393 | 2024-07 | 745 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 29/3 | 2024-07-29 | 2024-09-28 | 2024-10-03 | 61 | 66 | 2024-07 | 744 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 31/3 | 2024-07-31 | 2025-08-12 | 2025-08-22 | 377 | 387 | 2024-07 | 742 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 30/1 | 2024-08-01 | 2024-10-09 | 2024-10-17 | 69 | 77 | 2024-08 | 741 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 29/5 | 2024-08-03 | 2024-09-21 | 2024-09-27 | 49 | 55 | 2024-08 | 739 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 31/1 | 2024-08-03 | 2025-08-02 | 2025-08-10 | 364 | 372 | 2024-08 | 739 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 29A/2 | 2024-08-08 | 2024-09-12 | 2024-09-21 | 35 | 44 | 2024-08 | 734 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 5/3 | 2024-08-08 | 2025-09-09 | 2025-09-30 | 397 | 418 | 2024-08 | 734 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 7/1 | 2024-08-10 | 2024-12-15 | 2024-12-26 | 127 | 138 | 2024-08 | 732 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 8/10 | 2024-08-13 | 2025-01-30 | 2025-02-03 | 170 | 174 | 2024-08 | 729 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 29A/1 | 2024-08-14 | 2024-10-14 | 2024-10-25 | 61 | 72 | 2024-08 | 728 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 27/4 | 2024-08-16 | 2025-10-27 | 2025-11-15 | 437 | 456 | 2024-08 | 726 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 7A/5 | 2024-08-17 | 2024-12-17 | 2024-12-24 | 122 | 129 | 2024-08 | 725 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 5/8 | 2024-08-18 | 2025-09-10 | 2025-09-15 | 388 | 393 | 2024-08 | 724 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 29A/3 | 2024-08-20 | 2025-12-27 | 2026-01-06 | 494 | 504 | 2024-08 | 722 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 32/3 | 2024-08-20 | 2025-07-27 | 2025-08-05 | 341 | 350 | 2024-08 | 722 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 7A/4 | 2024-08-23 | 2024-12-24 | 2024-12-31 | 123 | 130 | 2024-08 | 719 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 29A/4 | 2024-08-24 | 2025-10-05 | 2025-10-10 | 407 | 412 | 2024-08 | 718 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 5/4 | 2024-08-25 | 2025-08-29 | 2025-09-08 | 369 | 379 | 2024-08 | 717 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 32/4 | 2024-08-26 | 2025-08-07 | 2025-08-14 | 346 | 353 | 2024-08 | 716 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 29A/5 | 2024-08-27 | 2025-09-26 | 2025-10-04 | 395 | 403 | 2024-08 | 715 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 6/2 | 2024-08-27 | 2025-08-04 | 2025-08-08 | 342 | 346 | 2024-08 | 715 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 27/5 | 2024-08-28 | 2025-10-23 | 2025-10-30 | 421 | 428 | 2024-08 | 714 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 33/6 | 2024-08-30 | 2025-01-29 | 2025-02-08 | 152 | 162 | 2024-08 | 712 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 6/1 | 2024-08-30 | 2025-07-16 | 2025-07-26 | 320 | 330 | 2024-08 | 712 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 29A/6 | 2024-08-31 | 2024-10-03 | 2024-10-14 | 33 | 44 | 2024-08 | 711 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4A/5 | 2024-09-01 | 2025-08-25 | 2025-09-08 | 358 | 372 | 2024-09 | 710 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 7A/1 | 2024-09-01 | 2025-01-17 | 2025-01-22 | 138 | 143 | 2024-09 | 710 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 33/7 | 2024-09-04 | 2025-08-23 | 2025-08-30 | 353 | 360 | 2024-09 | 707 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 5/10 | 2024-09-04 | 2025-08-22 | 2025-08-28 | 352 | 358 | 2024-09 | 707 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 6/12 | 2024-09-05 | 2025-08-01 | 2025-08-09 | 330 | 338 | 2024-09 | 706 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4A/4 | 2024-09-06 | 2025-08-18 | 2025-08-28 | 346 | 356 | 2024-09 | 705 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 7A/2 | 2024-09-06 | 2025-01-08 | 2025-01-16 | 124 | 132 | 2024-09 | 705 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 6/3 | 2024-09-07 | 2025-08-08 | 2025-08-14 | 335 | 341 | 2024-09 | 704 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 33/4 | 2024-09-09 | 2025-09-05 | 2025-09-09 | 361 | 365 | 2024-09 | 702 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4A/3 | 2024-09-09 | 2025-08-29 | 2025-09-06 | 354 | 362 | 2024-09 | 702 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 29/1 | 2024-09-10 | 2025-10-07 | 2025-10-12 | 392 | 397 | 2024-09 | 701 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 7A/3 | 2024-09-10 | 2025-01-01 | 2025-01-08 | 113 | 120 | 2024-09 | 701 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4A/6 | 2024-09-12 | 2025-09-09 | 2025-09-18 | 362 | 371 | 2024-09 | 699 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 5/7 | 2024-09-12 | 2025-09-02 | 2025-09-09 | 355 | 362 | 2024-09 | 699 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 33/3 | 2024-09-13 | 2025-08-31 | 2025-09-04 | 352 | 356 | 2024-09 | 698 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 34/12 | 2024-09-13 | 2024-11-14 | 2024-11-25 | 62 | 73 | 2024-09 | 698 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 6/11 | 2024-09-14 | 2025-08-19 | 2025-08-25 | 339 | 345 | 2024-09 | 697 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 34/1 | 2024-09-15 | 2025-01-21 | 2025-01-29 | 128 | 136 | 2024-09 | 696 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 36A/1 | 2024-09-15 | 2024-12-13 | 2024-12-25 | 89 | 101 | 2024-09 | 696 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 5/6 | 2024-09-15 | 2025-08-08 | 2025-08-20 | 327 | 339 | 2024-09 | 696 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4A/2 | 2024-09-16 | 2025-09-07 | 2025-09-16 | 356 | 365 | 2024-09 | 695 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 34/3 | 2024-09-18 | 2024-12-05 | 2024-12-16 | 78 | 89 | 2024-09 | 693 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 36A/2 | 2024-09-19 | 2025-01-04 | 2025-01-11 | 107 | 114 | 2024-09 | 692 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 27/2 | 2024-09-20 | 2025-11-21 | 2025-11-27 | 427 | 433 | 2024-09 | 691 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 34/11 | 2024-09-20 | 2024-12-30 | 2025-01-07 | 101 | 109 | 2024-09 | 691 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 6/4 | 2024-09-20 | 2025-08-15 | 2025-08-21 | 329 | 335 | 2024-09 | 691 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 34/4 | 2024-09-21 | 2024-11-25 | 2024-12-04 | 65 | 74 | 2024-09 | 690 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4A/1 | 2024-09-21 | 2025-09-18 | 2025-09-25 | 362 | 369 | 2024-09 | 690 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 37/1 | 2024-09-23 |  |  |  |  | 2024-09 | 688 | FALSE | FALSE | No | No |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation
TA 413 | 5/2 | 2024-09-23 | 2025-09-26 | 2025-09-30 | 368 | 372 | 2024-09 | 688 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 6/6 | 2024-09-23 | 2025-08-14 | 2025-08-21 | 325 | 332 | 2024-09 | 688 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 34/5 | 2024-09-25 | 2024-12-17 | 2024-12-29 | 83 | 95 | 2024-09 | 686 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 35/1 | 2024-09-26 | 2025-01-07 | 2025-01-19 | 103 | 115 | 2024-09 | 685 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 37/2 | 2024-09-27 | 2026-01-12 | 2026-01-22 | 472 | 482 | 2024-09 | 684 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4/1 | 2024-09-27 | 2025-09-06 | 2025-09-12 | 344 | 350 | 2024-09 | 684 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 27/1 | 2024-09-28 | 2025-12-05 | 2025-12-14 | 433 | 442 | 2024-09 | 683 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 34/6 | 2024-09-28 | 2024-12-30 | 2025-01-09 | 93 | 103 | 2024-09 | 683 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 6/10 | 2024-09-29 | 2025-08-09 | 2025-08-18 | 314 | 323 | 2024-09 | 682 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 34/8 | 2024-09-30 | 2024-11-12 | 2024-11-24 | 43 | 55 | 2024-09 | 681 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 37/3 | 2024-09-30 | 2026-01-23 | 2026-01-29 | 480 | 486 | 2024-09 | 681 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4A/0 | 2024-10-01 | 2025-09-13 | 2025-09-24 | 347 | 358 | 2024-10 | 680 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 6/9 | 2024-10-01 | 2025-08-23 | 2025-09-02 | 326 | 336 | 2024-10 | 680 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 7/0 | 2024-10-01 | 2025-07-22 | 2025-07-31 | 294 | 303 | 2024-10 | 680 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 35/5 | 2024-10-03 | 2025-01-06 | 2025-01-13 | 95 | 102 | 2024-10 | 678 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 34/7 | 2024-10-04 | 2024-11-26 | 2024-12-12 | 53 | 69 | 2024-10 | 677 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 36A/0 | 2024-10-05 | 2025-04-18 | 2025-04-30 | 195 | 207 | 2024-10 | 676 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 3/8 | 2024-10-05 |  |  |  |  | 2024-10 | 676 | FALSE | FALSE | No | No |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation
TA 413 | 34/9 | 2024-10-07 | 2024-12-13 | 2024-12-21 | 67 | 75 | 2024-10 | 674 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 5/9 | 2024-10-07 | 2025-08-29 | 2025-09-05 | 326 | 333 | 2024-10 | 674 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 27/3 | 2024-10-08 | 2025-11-28 | 2025-12-05 | 416 | 423 | 2024-10 | 673 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 7/3 | 2024-10-08 | 2025-07-09 | 2025-07-21 | 274 | 286 | 2024-10 | 673 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 35/6 | 2024-10-09 | 2024-12-29 | 2025-01-05 | 81 | 88 | 2024-10 | 672 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 3/9 | 2024-10-09 |  |  |  |  | 2024-10 | 672 | FALSE | FALSE | No | No |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation
TA 413 | 3/10 | 2024-10-12 | 2025-07-16 | 2025-08-01 | 277 | 293 | 2024-10 | 669 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 34/10 | 2024-10-12 | 2024-12-22 | 2024-12-29 | 71 | 78 | 2024-10 | 669 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 7/4 | 2024-10-12 | 2025-02-20 | 2025-02-27 | 131 | 138 | 2024-10 | 669 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 27/6 | 2024-10-14 | 2025-11-13 | 2025-11-20 | 395 | 402 | 2024-10 | 667 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 37/0 | 2024-10-14 |  |  |  |  | 2024-10 | 667 | FALSE | FALSE | No | No |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation
TA 413 | 34/2 | 2024-10-16 | 2025-01-10 | 2025-01-21 | 86 | 97 | 2024-10 | 665 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 6/7 | 2024-10-16 | 2025-08-22 | 2025-08-28 | 310 | 316 | 2024-10 | 665 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 35/7 | 2024-10-17 | 2024-12-13 | 2024-12-22 | 57 | 66 | 2024-10 | 664 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 6/0 | 2024-10-18 | 2025-08-13 | 2025-08-21 | 299 | 307 | 2024-10 | 663 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 3/7 | 2024-10-19 |  |  |  |  | 2024-10 | 662 | FALSE | FALSE | No | No |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation
TA 413 | 6/5 | 2024-10-19 | 2025-08-02 | 2025-08-13 | 287 | 298 | 2024-10 | 662 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 37A/4 | 2024-10-21 | 2025-02-25 | 2025-03-06 | 127 | 136 | 2024-10 | 660 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 33/5 | 2024-10-22 | 2025-01-31 | 2025-02-18 | 101 | 119 | 2024-10 | 659 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 3/6 | 2024-10-22 |  |  |  |  | 2024-10 | 659 | FALSE | FALSE | No | No |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation
TA 413 | 5/5 | 2024-10-23 | 2025-08-20 | 2025-08-28 | 301 | 309 | 2024-10 | 658 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 29/2 | 2024-10-25 | 2025-12-12 | 2025-12-20 | 413 | 421 | 2024-10 | 656 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 33/8 | 2024-10-25 | 2025-02-18 | 2025-03-04 | 116 | 130 | 2024-10 | 656 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 37A/5 | 2024-10-25 | 2025-02-24 | 2025-02-28 | 122 | 126 | 2024-10 | 656 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 35/9 | 2024-10-27 | 2025-01-17 | 2025-01-24 | 82 | 89 | 2024-10 | 654 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 3/4 | 2024-10-29 |  |  |  |  | 2024-10 | 652 | FALSE | FALSE | No | No |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation
TA 413 | 35/8 | 2024-10-29 | 2024-12-23 | 2024-12-28 | 55 | 60 | 2024-10 | 652 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 37A/3 | 2024-10-30 | 2025-02-16 | 2025-02-25 | 109 | 118 | 2024-10 | 651 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 29A/0 | 2024-11-07 | 2025-10-06 | 2025-10-22 | 333 | 349 | 2024-11 | 643 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 37A/2 | 2024-11-08 | 2025-01-29 | 2025-02-07 | 82 | 91 | 2024-11 | 642 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 6/8 | 2024-11-08 | 2025-08-29 | 2025-09-06 | 294 | 302 | 2024-11 | 642 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 35/11 | 2024-11-09 | 2024-12-24 | 2025-01-03 | 45 | 55 | 2024-11 | 641 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 33/9 | 2024-11-11 | 2025-08-18 | 2025-08-22 | 280 | 284 | 2024-11 | 639 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 18/0 | 2024-11-12 | 2025-09-07 | 2025-09-15 | 299 | 307 | 2024-11 | 638 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 37A/1 | 2024-11-12 | 2025-02-08 | 2025-02-16 | 88 | 96 | 2024-11 | 638 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 18/1 | 2024-11-16 | 2025-09-16 | 2025-09-20 | 304 | 308 | 2024-11 | 634 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 37/4 | 2024-11-17 | 2025-01-11 | 2025-01-22 | 55 | 66 | 2024-11 | 633 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 18/2 | 2024-11-19 | 2025-09-21 | 2025-09-25 | 306 | 310 | 2024-11 | 631 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 36/0 | 2024-11-20 | 2026-01-22 | 2026-02-04 | 428 | 441 | 2024-11 | 630 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 38/8 | 2024-11-20 | 2025-03-19 | 2025-03-24 | 119 | 124 | 2024-11 | 630 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 37/5 | 2024-11-21 | 2025-01-22 | 2025-01-30 | 62 | 70 | 2024-11 | 629 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 38/9 | 2024-11-21 | 2025-02-15 | 2025-02-18 | 86 | 89 | 2024-11 | 629 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 7A/0 | 2024-11-22 | 2025-01-22 | 2025-01-31 | 61 | 70 | 2024-11 | 628 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 34/0 | 2024-11-23 | 2025-01-17 | 2025-01-31 | 55 | 69 | 2024-11 | 627 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 38/10 | 2024-11-23 | 2025-02-18 | 2025-02-24 | 87 | 93 | 2024-11 | 627 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 18/3 | 2024-11-24 | 2025-09-26 | 2025-09-30 | 306 | 310 | 2024-11 | 626 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 38/7 | 2024-11-26 | 2025-03-12 | 2025-03-18 | 106 | 112 | 2024-11 | 624 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 35/4 | 2024-11-27 | 2025-01-14 | 2025-01-19 | 48 | 53 | 2024-11 | 623 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 37A/0 | 2024-11-27 | 2025-02-28 | 2025-03-11 | 93 | 104 | 2024-11 | 623 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 18/4 | 2024-11-29 | 2025-10-01 | 2025-10-06 | 306 | 311 | 2024-11 | 621 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 38/6 | 2024-11-29 | 2025-01-29 | 2025-02-04 | 61 | 67 | 2024-11 | 621 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 38/5 | 2024-11-30 | 2025-02-11 | 2025-02-15 | 73 | 77 | 2024-11 | 620 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 7/2 | 2024-12-01 | 2024-12-27 | 2025-01-03 | 26 | 33 | 2024-12 | 619 | TRUE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 18/6 | 2024-12-04 | 2025-10-11 | 2025-10-15 | 311 | 315 | 2024-12 | 616 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 38/0 | 2024-12-04 | 2025-03-29 | 2025-04-11 | 115 | 128 | 2024-12 | 616 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 35/0 | 2024-12-06 | 2025-02-09 | 2025-02-23 | 65 | 79 | 2024-12 | 614 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 38/3 | 2024-12-06 | 2025-01-24 | 2025-01-29 | 49 | 54 | 2024-12 | 614 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 18/5 | 2024-12-07 | 2025-10-07 | 2025-10-10 | 304 | 307 | 2024-12 | 613 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 37A/6 | 2024-12-08 | 2025-02-24 | 2025-03-08 | 78 | 90 | 2024-12 | 612 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 38/4 | 2024-12-08 | 2025-02-05 | 2025-02-10 | 59 | 64 | 2024-12 | 612 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 30/3 | 2024-12-10 | 2025-10-12 | 2025-10-22 | 306 | 316 | 2024-12 | 610 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 38/2 | 2024-12-12 | 2025-03-07 | 2025-03-11 | 85 | 89 | 2024-12 | 608 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 40/2 | 2024-12-12 | 2025-03-26 | 2025-03-31 | 104 | 109 | 2024-12 | 608 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 38/1 | 2024-12-13 | 2025-03-01 | 2025-03-06 | 78 | 83 | 2024-12 | 607 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 40/3 | 2024-12-14 | 2025-03-31 | 2025-04-09 | 107 | 116 | 2024-12 | 606 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 39/1 | 2024-12-15 | 2025-03-22 | 2025-03-29 | 97 | 104 | 2024-12 | 605 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 7/5 | 2024-12-17 | 2025-02-11 | 2025-02-19 | 56 | 64 | 2024-12 | 603 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 30/0 | 2024-12-18 | 2025-09-11 | 2025-09-25 | 267 | 281 | 2024-12 | 602 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 17/0 | 2024-12-19 | 2025-11-16 | 2025-12-23 | 332 | 369 | 2024-12 | 601 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 40/7 | 2024-12-19 | 2025-08-14 | 2025-08-20 | 238 | 244 | 2024-12 | 601 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 39/0 | 2024-12-21 | 2025-03-09 | 2025-03-21 | 78 | 90 | 2024-12 | 599 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 39/2 | 2024-12-21 | 2025-03-12 | 2025-03-19 | 81 | 88 | 2024-12 | 599 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 40/6 | 2024-12-21 | 2025-04-14 | 2025-04-22 | 114 | 122 | 2024-12 | 599 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 30/2 | 2024-12-22 | 2025-09-24 | 2025-10-04 | 276 | 286 | 2024-12 | 598 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 39/4 | 2024-12-23 | 2025-03-21 | 2025-03-27 | 88 | 94 | 2024-12 | 597 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 40/8 | 2024-12-25 | 2025-10-10 | 2025-10-19 | 289 | 298 | 2024-12 | 595 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 41/1 | 2024-12-27 | 2025-09-24 | 2025-10-04 | 271 | 281 | 2024-12 | 593 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 16/0 | 2024-12-28 | 2026-06-02 | 2026-06-19 | 521 | 538 | 2024-12 | 592 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 30/4 | 2024-12-29 | 2025-09-09 | 2025-09-15 | 254 | 260 | 2024-12 | 591 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 39/3 | 2024-12-29 | 2025-03-20 | 2025-03-25 | 81 | 86 | 2024-12 | 591 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 40/5 | 2024-12-29 | 2025-04-05 | 2025-04-14 | 97 | 106 | 2024-12 | 591 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 7/6 | 2024-12-30 | 2025-01-31 | 2025-02-10 | 32 | 42 | 2024-12 | 590 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 15/12 | 2024-12-31 | 2025-11-29 | 2025-12-06 | 333 | 340 | 2024-12 | 589 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 40/4 | 2024-12-31 | 2025-04-09 | 2025-04-18 | 99 | 108 | 2024-12 | 589 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 30/5 | 2025-01-03 | 2025-12-21 | 2025-12-26 | 352 | 357 | 2025-01 | 586 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 42/0 | 2025-01-03 | 2025-07-21 | 2025-08-02 | 199 | 211 | 2025-01 | 586 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 39/5 | 2025-01-05 | 2025-03-14 | 2025-03-20 | 68 | 74 | 2025-01 | 584 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 40/9 | 2025-01-05 | 2025-08-01 | 2025-08-13 | 208 | 220 | 2025-01 | 584 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 8/3 | 2025-01-06 | 2025-02-14 | 2025-02-19 | 39 | 44 | 2025-01 | 583 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 30/6 | 2025-01-07 | 2025-08-29 | 2025-09-08 | 234 | 244 | 2025-01 | 582 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 42/1 | 2025-01-08 | 2025-08-02 | 2025-08-06 | 206 | 210 | 2025-01 | 581 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 39/6 | 2025-01-09 | 2025-04-09 | 2025-04-18 | 90 | 99 | 2025-01 | 580 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 40/10 | 2025-01-09 | 2025-09-30 | 2025-10-09 | 264 | 273 | 2025-01 | 580 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 30/7 | 2025-01-10 | 2025-09-09 | 2025-09-13 | 242 | 246 | 2025-01 | 579 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 30/8 | 2025-01-13 | 2025-09-14 | 2025-09-22 | 244 | 252 | 2025-01 | 576 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 40/11 | 2025-01-13 | 2025-09-21 | 2025-09-29 | 251 | 259 | 2025-01 | 576 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 42/2 | 2025-01-13 | 2025-08-07 | 2025-08-11 | 206 | 210 | 2025-01 | 576 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 8/0 | 2025-01-13 | 2025-02-09 | 2025-02-14 | 27 | 32 | 2025-01 | 576 | TRUE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 22/0 | 2025-01-15 | 2025-10-28 | 2025-11-13 | 286 | 302 | 2025-01 | 574 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 30/9 | 2025-01-17 | 2025-08-12 | 2025-08-21 | 207 | 216 | 2025-01 | 572 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 39/7 | 2025-01-17 | 2025-03-07 | 2025-03-13 | 49 | 55 | 2025-01 | 572 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 41/0 | 2025-01-19 | 2025-10-08 | 2025-10-22 | 262 | 276 | 2025-01 | 570 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 40A/0 | 2025-01-20 | 2025-09-04 | 2025-09-20 | 227 | 243 | 2025-01 | 569 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 10/0 | 2025-01-21 | 2025-10-02 | 2025-10-17 | 254 | 269 | 2025-01 | 568 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 30/10 | 2025-01-21 | 2025-07-18 | 2025-08-03 | 178 | 194 | 2025-01 | 568 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 43/7 | 2025-01-21 | 2025-09-24 | 2025-09-28 | 246 | 250 | 2025-01 | 568 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 23/0 | 2025-01-22 | 2025-10-12 | 2025-10-27 | 263 | 278 | 2025-01 | 567 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 43/3 | 2025-01-23 | 2025-08-23 | 2025-09-02 | 212 | 222 | 2025-01 | 566 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 39/8 | 2025-01-24 | 2024-03-26 | 2025-03-31 | -304 | 66 | 2025-01 | 565 | FALSE | FALSE | Yes | Yes | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 8/4 | 2025-01-24 | 2025-02-20 | 2025-02-24 | 27 | 31 | 2025-01 | 565 | TRUE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 43/0 | 2025-01-25 | 2026-02-01 | 2026-02-14 | 372 | 385 | 2025-01 | 564 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 43/8 | 2025-01-25 | 2025-09-14 | 2025-09-19 | 232 | 237 | 2025-01 | 564 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 15/1 | 2025-01-27 | 2025-11-27 | 2025-12-03 | 304 | 310 | 2025-01 | 562 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 43/4 | 2025-01-28 | 2025-09-03 | 2025-09-07 | 218 | 222 | 2025-01 | 561 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 23A/0 | 2025-01-30 | 2025-11-14 | 2025-11-27 | 288 | 301 | 2025-01 | 559 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 32/1 | 2025-01-31 | 2025-07-05 | 2025-07-17 | 155 | 167 | 2025-01 | 558 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 39/9 | 2025-01-31 | 2025-03-25 | 2025-03-30 | 53 | 58 | 2025-01 | 558 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 42A/0 | 2025-01-31 | 2025-08-12 | 2025-08-19 | 193 | 200 | 2025-01 | 558 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 31/2 | 2025-02-01 | 2025-08-04 | 2025-08-11 | 184 | 191 | 2025-02 | 557 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 43/6 | 2025-02-02 | 2025-09-08 | 2025-09-11 | 218 | 221 | 2025-02 | 556 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 18/7 | 2025-02-04 | 2025-10-16 | 2025-10-22 | 254 | 260 | 2025-02 | 554 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 32/2 | 2025-02-04 | 2025-07-18 | 2025-07-26 | 164 | 172 | 2025-02 | 554 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 44/0 | 2025-02-04 | 2025-09-20 | 2025-09-29 | 228 | 237 | 2025-02 | 554 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 43/1 | 2025-02-05 | 2025-12-22 | 2025-12-31 | 320 | 329 | 2025-02 | 553 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 31/4 | 2025-02-07 | 2025-08-22 | 2025-08-31 | 196 | 205 | 2025-02 | 551 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 43/2 | 2025-02-08 | 2025-08-20 | 2025-08-25 | 193 | 198 | 2025-02 | 550 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 32/0 | 2025-02-09 | 2025-09-04 | 2025-09-14 | 207 | 217 | 2025-02 | 549 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 43A/0 | 2025-02-09 | 2025-11-30 | 2025-12-21 | 294 | 315 | 2025-02 | 549 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 31/5 | 2025-02-10 | 2025-08-23 | 2025-09-03 | 194 | 205 | 2025-02 | 548 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 13/0 | 2025-02-11 | 2025-12-18 | 2025-12-31 | 310 | 323 | 2025-02 | 547 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 39/10 | 2025-02-11 | 2025-03-31 | 2025-04-05 | 48 | 53 | 2025-02 | 547 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 20/2 | 2025-02-12 | 2025-09-26 | 2025-09-30 | 226 | 230 | 2025-02 | 546 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 8/11 | 2025-02-13 | 2025-07-15 | 2025-08-03 | 152 | 171 | 2025-02 | 545 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 20/1 | 2025-02-16 | 2025-09-19 | 2025-09-25 | 215 | 221 | 2025-02 | 542 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 21/5 | 2025-02-16 | 2025-11-07 | 2025-11-12 | 264 | 269 | 2025-02 | 542 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 32/7 | 2025-02-17 | 2025-07-26 | 2025-07-31 | 159 | 164 | 2025-02 | 541 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 13A/0 | 2025-02-18 | 2026-01-01 | 2026-01-20 | 317 | 336 | 2025-02 | 540 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 32A/0 | 2025-02-18 | 2025-08-01 | 2025-08-09 | 164 | 172 | 2025-02 | 540 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 9/6 | 2025-02-19 | 2025-08-20 | 2025-08-25 | 182 | 187 | 2025-02 | 539 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 33/2 | 2025-02-20 | 2025-08-09 | 2025-08-17 | 170 | 178 | 2025-02 | 538 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 21/4 | 2025-02-22 | 2025-11-13 | 2025-11-20 | 264 | 271 | 2025-02 | 536 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 32A/1 | 2025-02-22 | 2025-08-14 | 2025-09-02 | 173 | 192 | 2025-02 | 536 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 29/0 | 2025-02-23 | 2025-10-08 | 2025-10-25 | 227 | 244 | 2025-02 | 535 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 39/11 | 2025-02-24 | 2025-03-30 | 2025-04-09 | 34 | 44 | 2025-02 | 534 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 27/0 | 2025-02-25 | 2025-11-08 | 2025-11-29 | 256 | 277 | 2025-02 | 533 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 9/9 | 2025-02-25 | 2025-11-06 | 2025-11-12 | 254 | 260 | 2025-02 | 533 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 28/0 | 2025-02-26 | 2025-10-31 | 2025-11-12 | 247 | 259 | 2025-02 | 532 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 9/7 | 2025-02-26 | 2025-08-23 | 2025-08-29 | 178 | 184 | 2025-02 | 532 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 24/0 | 2025-02-27 | 2025-11-13 | 2025-11-27 | 259 | 273 | 2025-02 | 531 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 44/1 | 2025-03-01 | 2025-08-25 | 2025-09-03 | 177 | 186 | 2025-03 | 529 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 26/0 | 2025-03-05 | 2025-10-10 | 2025-11-07 | 219 | 247 | 2025-03 | 525 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 9/8 | 2025-03-05 | 2025-12-04 | 2025-12-12 | 274 | 282 | 2025-03 | 525 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 15/0 | 2025-03-06 | 2025-10-05 | 2025-10-30 | 213 | 238 | 2025-03 | 524 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 44/2 | 2025-03-06 | 2025-09-04 | 2025-09-09 | 182 | 187 | 2025-03 | 524 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 25/0 | 2025-03-08 | 2025-11-12 | 2025-11-29 | 249 | 266 | 2025-03 | 522 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 40/0 | 2025-03-08 | 2025-04-18 | 2025-04-30 | 41 | 53 | 2025-03 | 522 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 44/4 | 2025-03-12 | 2025-09-16 | 2025-09-19 | 188 | 191 | 2025-03 | 518 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 44/3 | 2025-03-13 | 2025-09-10 | 2025-09-15 | 181 | 186 | 2025-03 | 517 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 5/0 | 2025-03-16 | 2025-09-19 | 2025-09-30 | 187 | 198 | 2025-03 | 514 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 44/5 | 2025-03-17 | 2025-09-20 | 2025-09-23 | 187 | 190 | 2025-03 | 513 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 2A/2 | 2025-03-23 | 2025-08-28 | 2025-09-02 | 158 | 163 | 2025-03 | 507 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 3B/2 | 2025-03-23 | 2025-09-26 | 2025-10-07 | 187 | 198 | 2025-03 | 507 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 5/1 | 2025-03-23 | 2025-09-13 | 2025-09-25 | 174 | 186 | 2025-03 | 507 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 3B/1 | 2025-03-26 | 2025-10-09 | 2025-10-16 | 197 | 204 | 2025-03 | 504 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 2A/3 | 2025-03-27 | 2025-09-03 | 2025-09-08 | 160 | 165 | 2025-03 | 503 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 2A/4 | 2025-03-30 | 2025-09-09 | 2025-09-15 | 163 | 169 | 2025-03 | 500 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 3B/0 | 2025-03-30 | 2025-09-25 | 2025-10-12 | 179 | 196 | 2025-03 | 500 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 40/1 | 2025-03-30 | 2025-07-06 | 2025-08-07 | 98 | 130 | 2025-03 | 500 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 5A/0 | 2025-04-01 | 2025-08-22 | 2025-09-01 | 143 | 153 | 2025-04 | 498 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 3A/6 | 2025-04-03 | 2025-09-16 | 2025-09-24 | 166 | 174 | 2025-04 | 496 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 2A/5 | 2025-04-05 | 2025-09-16 | 2025-09-23 | 164 | 171 | 2025-04 | 494 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 32/5 | 2025-04-08 | 2025-07-16 | 2025-07-25 | 99 | 108 | 2025-04 | 491 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 3A/1 | 2025-04-08 | 2025-09-03 | 2025-09-11 | 148 | 156 | 2025-04 | 491 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 3A/5 | 2025-04-08 | 2025-09-07 | 2025-09-15 | 152 | 160 | 2025-04 | 491 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 3A/4 | 2025-04-10 | 2025-10-01 | 2025-10-10 | 174 | 183 | 2025-04 | 489 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 32/6 | 2025-04-11 | 2025-07-06 | 2025-07-15 | 86 | 95 | 2025-04 | 488 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 35/3 | 2025-04-12 | 2026-01-07 | 2026-01-11 | 270 | 274 | 2025-04 | 487 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 3A/3 | 2025-04-12 | 2025-09-20 | 2025-09-27 | 161 | 168 | 2025-04 | 487 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 33/1 | 2025-04-14 | 2025-08-25 | 2025-09-10 | 133 | 149 | 2025-04 | 485 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 35/2 | 2025-04-15 | 2025-08-01 | 2025-08-09 | 108 | 116 | 2025-04 | 484 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 3A/2 | 2025-04-15 | 2025-09-12 | 2025-09-19 | 150 | 157 | 2025-04 | 484 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 14/0 | 2025-04-16 | 2025-11-30 | 2025-12-17 | 228 | 245 | 2025-04 | 483 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 33/0 | 2025-04-17 | 2025-09-03 | 2025-09-20 | 139 | 156 | 2025-04 | 482 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 3A/0 | 2025-04-18 | 2025-10-11 | 2025-10-26 | 176 | 191 | 2025-04 | 481 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 3B/3 | 2025-04-19 | 2025-10-27 | 2025-11-08 | 191 | 203 | 2025-04 | 480 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 21/3 | 2025-04-22 | 2025-11-21 | 2025-11-27 | 213 | 219 | 2025-04 | 477 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 2A/6 | 2025-04-23 | 2025-09-24 | 2025-09-30 | 154 | 160 | 2025-04 | 476 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 21/2 | 2025-04-24 | 2025-11-06 | 2025-11-13 | 196 | 203 | 2025-04 | 475 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4/0 | 2025-04-25 | 2025-09-25 | 2025-10-12 | 153 | 170 | 2025-04 | 474 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 8A/0 | 2025-04-25 | 2025-08-07 | 2025-08-14 | 104 | 111 | 2025-04 | 474 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 21/1 | 2025-04-29 | 2025-10-24 | 2025-10-29 | 178 | 183 | 2025-04 | 470 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 35/10 | 2025-05-02 | 2026-02-07 | 2026-02-16 | 281 | 290 | 2025-05 | 467 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 9/0 | 2025-05-03 | 2025-08-30 | 2025-09-06 | 119 | 126 | 2025-05 | 466 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 45/0 | 2025-05-05 | 2025-09-28 | 2025-10-09 | 146 | 157 | 2025-05 | 464 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 46/0 | 2025-05-07 | 2025-09-30 | 2025-10-12 | 146 | 158 | 2025-05 | 462 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 20/6 | 2025-05-09 | 2025-10-17 | 2025-10-23 | 161 | 167 | 2025-05 | 460 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 20/5 | 2025-05-13 | 2025-10-28 | 2025-10-31 | 168 | 171 | 2025-05 | 456 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 21/0 | 2025-05-13 | 2025-10-20 | 2025-10-29 | 160 | 169 | 2025-05 | 456 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 20/4 | 2025-05-18 | 2025-11-01 | 2025-11-06 | 167 | 172 | 2025-05 | 451 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 20/3 | 2025-05-22 | 2025-10-30 | 2025-11-05 | 161 | 167 | 2025-05 | 447 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 19/0 | 2025-05-26 | 2025-10-16 | 2025-10-28 | 143 | 155 | 2025-05 | 443 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 20/0 | 2025-06-02 | 2025-10-01 | 2025-10-15 | 121 | 135 | 2025-06 | 436 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 11/0 | 2025-06-08 | 2025-11-13 | 2025-11-26 | 158 | 171 | 2025-06 | 430 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 12/0 | 2025-06-14 | 2025-09-11 | 2025-09-26 | 89 | 104 | 2025-06 | 424 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 1/0 | 2025-06-27 | 2025-08-07 | 2025-08-21 | 41 | 55 | 2025-06 | 411 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 2A/1 | 2025-07-05 | 2025-08-21 | 2025-08-27 | 47 | 53 | 2025-07 | 403 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 2A/0 | 2025-07-14 | 2026-01-01 | 2026-01-25 | 171 | 195 | 2025-07 | 394 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 36B/0-N | 2026-01-23 | 2026-08-02 |  | 191 |  | 2026-01 | 201 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 36C/0-N | 2026-02-08 |  |  |  |  | 2026-02 | 185 | FALSE | FALSE | No | No |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation
TA 413 | 37/0-N | 2026-03-05 | 2026-07-12 | 2026-07-31 | 129 | 148 | 2026-03 | 160 | FALSE | FALSE | Yes | No | exact | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 414 | 241/2 | 2024-05-25 | 2026-01-14 | 2026-01-28 | 599 | 613 | 2024-05 | 809 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 241/0 | 2024-05-30 | 2025-09-02 | 2025-09-15 | 460 | 473 | 2024-05 | 804 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 118/0 | 2024-10-31 | 2025-05-31 | 2025-06-15 | 212 | 227 | 2024-10 | 650 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 120/3 | 2024-11-12 | 2025-06-09 | 2025-06-14 | 209 | 214 | 2024-11 | 638 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 121/5 | 2024-11-19 | 2026-01-30 | 2026-02-11 | 437 | 449 | 2024-11 | 631 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 120/2 | 2024-11-22 | 2025-06-02 | 2025-06-07 | 192 | 197 | 2024-11 | 628 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 121/4 | 2024-11-29 | 2024-03-27 | 2025-04-01 | -247 | 123 | 2024-11 | 621 | FALSE | FALSE | Yes | Yes | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 121/2 | 2024-12-07 | 2025-12-30 | 2026-01-19 | 388 | 408 | 2024-12 | 613 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 183/1 | 2024-12-09 | 2026-02-23 | 2026-03-10 | 441 | 456 | 2024-12 | 611 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 119/0 | 2024-12-16 | 2025-08-10 | 2025-08-30 | 237 | 257 | 2024-12 | 604 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 121/3 | 2024-12-21 | 2026-01-19 | 2026-01-30 | 394 | 405 | 2024-12 | 599 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 120/0 | 2024-12-22 | 2026-01-21 | 2026-01-31 | 395 | 405 | 2024-12 | 598 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 120/5 | 2024-12-22 | 2025-12-08 | 2025-12-27 | 351 | 370 | 2024-12 | 598 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 244/6 | 2024-12-23 | 2026-02-25 | 2026-03-15 | 429 | 447 | 2024-12 | 597 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 145/4 | 2024-12-27 | 2026-01-09 | 2026-01-15 | 378 | 384 | 2024-12 | 593 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 249/1 | 2024-12-27 | 2026-06-25 | 2026-08-09 | 545 | 590 | 2024-12 | 593 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 119/2 | 2024-12-28 | 2025-08-07 | 2025-08-14 | 222 | 229 | 2024-12 | 592 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 119/3 | 2024-12-30 | 2025-07-26 | 2025-08-05 | 208 | 218 | 2024-12 | 590 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 121/6 | 2024-12-31 | 2026-02-13 | 2026-02-22 | 409 | 418 | 2024-12 | 589 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 249/0 | 2025-01-02 | 2026-06-13 | 2026-06-26 | 527 | 540 | 2025-01 | 587 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 249/2 | 2025-01-03 |  |  |  |  | 2025-01 | 586 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 120/6 | 2025-01-04 | 2025-06-16 | 2025-06-29 | 163 | 176 | 2025-01 | 585 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 126/3 | 2025-01-08 | 2026-03-27 | 2026-04-03 | 443 | 450 | 2025-01 | 581 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 121/1 | 2025-01-10 | 2026-03-29 | 2026-05-07 | 443 | 482 | 2025-01 | 579 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 137/2 | 2025-01-10 | 2025-12-28 | 2026-01-04 | 352 | 359 | 2025-01 | 579 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 121/7 | 2025-01-12 | 2025-09-15 | 2025-10-01 | 246 | 262 | 2025-01 | 577 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 145/3 | 2025-01-13 | 2026-01-15 | 2026-01-19 | 367 | 371 | 2025-01 | 576 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 120/7 | 2025-01-14 | 2025-12-28 | 2026-01-09 | 348 | 360 | 2025-01 | 575 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 244/5 | 2025-01-16 | 2025-12-14 | 2025-12-23 | 332 | 341 | 2025-01 | 573 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 121/8 | 2025-01-20 | 2026-05-07 | 2026-05-27 | 472 | 492 | 2025-01 | 569 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 250/0 | 2025-01-20 | 2026-06-05 | 2026-06-17 | 501 | 513 | 2025-01 | 569 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 252/3 | 2025-01-22 | 2026-04-14 | 2026-05-10 | 447 | 473 | 2025-01 | 567 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 136/1 | 2025-01-24 | 2025-12-20 | 2025-12-28 | 330 | 338 | 2025-01 | 565 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 145/2 | 2025-01-26 | 2026-04-24 | 2026-05-03 | 453 | 462 | 2025-01 | 563 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 250A/2 | 2025-01-28 | 2026-01-04 | 2026-01-13 | 341 | 350 | 2025-01 | 561 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 252/0 | 2025-01-31 | 2026-02-05 | 2026-02-14 | 370 | 379 | 2025-01 | 558 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 248/2 | 2025-02-03 | 2025-09-11 | 2026-02-02 | 220 | 364 | 2025-02 | 555 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 121/10 | 2025-02-04 | 2025-09-08 | 2025-09-18 | 216 | 226 | 2025-02 | 554 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 141/4 | 2025-02-04 | 2026-01-29 | 2026-02-08 | 359 | 369 | 2025-02 | 554 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 241/4 | 2025-02-04 | 2025-12-06 | 2025-12-19 | 305 | 318 | 2025-02 | 554 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 124/1 | 2025-02-06 | 2026-04-24 | 2026-04-28 | 442 | 446 | 2025-02 | 552 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 137/1 | 2025-02-07 | 2026-01-22 | 2026-01-31 | 349 | 358 | 2025-02 | 551 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 141/3 | 2025-02-08 | 2026-01-04 | 2026-01-09 | 330 | 335 | 2025-02 | 550 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 145/7 | 2025-02-08 | 2026-01-19 | 2026-01-25 | 345 | 351 | 2025-02 | 550 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 121/9 | 2025-02-11 | 2026-05-16 | 2026-05-22 | 459 | 465 | 2025-02 | 547 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 126/1 | 2025-02-13 | 2025-12-30 | 2026-01-18 | 320 | 339 | 2025-02 | 545 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 141/5 | 2025-02-13 | 2026-01-09 | 2026-01-13 | 330 | 334 | 2025-02 | 545 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 243/3 | 2025-02-13 | 2026-05-29 | 2026-06-15 | 470 | 487 | 2025-02 | 545 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 248/1 | 2025-02-13 | 2025-12-26 | 2026-01-14 | 316 | 335 | 2025-02 | 545 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 137/0 | 2025-02-14 | 2026-01-04 | 2026-01-12 | 324 | 332 | 2025-02 | 544 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 124/0 | 2025-02-19 | 2026-04-08 | 2026-04-24 | 413 | 429 | 2025-02 | 539 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 243/2 | 2025-02-21 | 2025-12-19 | 2025-12-29 | 301 | 311 | 2025-02 | 537 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 250/3 | 2025-02-23 | 2025-12-23 | 2026-01-03 | 303 | 314 | 2025-02 | 535 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 126/2 | 2025-02-26 | 2026-03-14 | 2026-03-26 | 381 | 393 | 2025-02 | 532 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 148/0 | 2025-02-27 | 2026-01-31 | 2026-02-21 | 338 | 359 | 2025-02 | 531 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 126/0 | 2025-02-28 | 2026-01-17 | 2026-02-18 | 323 | 355 | 2025-02 | 530 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 244/1 | 2025-03-07 | 2025-12-04 | 2025-12-13 | 272 | 281 | 2025-03 | 523 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 132/0 | 2025-03-08 | 2025-12-08 | 2025-12-15 | 275 | 282 | 2025-03 | 522 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 117/1 | 2025-03-13 | 2026-01-15 | 2026-01-21 | 308 | 314 | 2025-03 | 517 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 117/2 | 2025-03-17 | 2025-08-19 | 2025-08-28 | 155 | 164 | 2025-03 | 513 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 251/0 | 2025-03-20 | 2026-02-07 | 2026-02-16 | 324 | 333 | 2025-03 | 510 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 171/0 | 2025-03-22 | 2026-04-26 | 2026-05-07 | 400 | 411 | 2025-03 | 508 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 121/0 | 2025-03-23 | 2026-02-24 | 2026-03-29 | 338 | 371 | 2025-03 | 507 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 180/3 | 2025-03-23 | 2025-12-29 | 2026-01-23 | 281 | 306 | 2025-03 | 507 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 172/0 | 2025-03-26 |  |  |  |  | 2025-03 | 504 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 180/4 | 2025-03-27 | 2025-12-30 | 2026-01-15 | 278 | 294 | 2025-03 | 503 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 172/1 | 2025-04-01 | 2026-05-07 | 2026-05-13 | 401 | 407 | 2025-04 | 498 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 179/3 | 2025-04-01 | 2026-03-12 | 2026-03-17 | 345 | 350 | 2025-04 | 498 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 165/7 | 2025-04-05 | 2026-05-13 | 2026-05-20 | 403 | 410 | 2025-04 | 494 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 180/2 | 2025-04-05 | 2026-01-23 | 2026-02-05 | 293 | 306 | 2025-04 | 494 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 180/5 | 2025-04-06 | 2025-12-17 | 2025-12-29 | 255 | 267 | 2025-04 | 493 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 180/7 | 2025-04-08 | 2026-01-29 | 2026-02-13 | 296 | 311 | 2025-04 | 491 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 179/1 | 2025-04-09 | 2025-12-08 | 2025-12-12 | 243 | 247 | 2025-04 | 490 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 132/1 | 2025-04-10 | 2026-02-24 | 2026-02-28 | 320 | 324 | 2025-04 | 489 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 174/4 | 2025-04-10 | 2026-03-16 | 2026-03-23 | 340 | 347 | 2025-04 | 489 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 174/6 | 2025-04-11 | 2026-01-23 | 2026-02-06 | 287 | 301 | 2025-04 | 488 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 174/5 | 2025-04-15 | 2026-03-23 | 2026-03-29 | 342 | 348 | 2025-04 | 484 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 174/1 | 2025-04-16 | 2026-02-25 | 2026-03-16 | 315 | 334 | 2025-04 | 483 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 176/1 | 2025-04-18 | 2026-02-15 | 2026-02-20 | 303 | 308 | 2025-04 | 481 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 175/0 | 2025-04-23 | 2026-01-06 | 2026-01-15 | 258 | 267 | 2025-04 | 476 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 177/0 | 2025-04-23 | 2026-01-25 | 2026-02-09 | 277 | 292 | 2025-04 | 476 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 176/2 | 2025-04-27 | 2026-02-09 | 2026-02-15 | 288 | 294 | 2025-04 | 472 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 148/4 | 2025-04-28 | 2025-12-20 | 2026-01-06 | 236 | 253 | 2025-04 | 471 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 178/3 | 2025-04-28 | 2026-02-06 | 2026-02-26 | 284 | 304 | 2025-04 | 471 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 165/5 | 2025-05-03 | 2026-03-20 | 2026-04-04 | 321 | 336 | 2025-05 | 466 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 148/2 | 2025-05-12 | 2025-12-06 | 2025-12-20 | 208 | 222 | 2025-05 | 457 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 180/1 | 2025-05-13 | 2026-02-07 | 2026-02-27 | 270 | 290 | 2025-05 | 456 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 165/2 | 2025-05-15 |  |  |  |  | 2025-05 | 454 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 252/5 | 2025-05-17 | 2026-01-02 | 2026-01-19 | 230 | 247 | 2025-05 | 452 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 243/0 | 2025-06-01 | 2025-11-30 | 2025-12-25 | 182 | 207 | 2025-06 | 437 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 256/0 | 2025-06-14 | 2026-02-24 | 2026-03-11 | 255 | 270 | 2025-06 | 424 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 246/0 | 2025-08-23 | 2026-01-03 | 2026-01-31 | 133 | 161 | 2025-08 | 354 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 250A/1 | 2025-09-09 | 2026-01-13 | 2026-01-23 | 126 | 136 | 2025-09 | 337 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 131/2 | 2025-09-15 | 2025-12-15 | 2025-12-20 | 91 | 96 | 2025-09 | 331 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 241/3 | 2025-09-20 | 2026-01-28 | 2026-02-09 | 130 | 142 | 2025-09 | 326 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 178/0 | 2025-10-14 | 2026-03-17 | 2026-04-04 | 154 | 172 | 2025-10 | 302 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 120/1 | 2025-10-16 | 2026-04-13 | 2026-04-19 | 179 | 185 | 2025-10 | 300 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 224/1 | 2025-10-19 | 2026-04-02 | 2026-04-09 | 165 | 172 | 2025-10 | 297 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 119/1 | 2025-10-20 | 2026-01-09 | 2026-01-15 | 81 | 87 | 2025-10 | 296 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 224/2 | 2025-10-20 | 2026-04-29 | 2026-05-08 | 191 | 200 | 2025-10 | 296 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 225/0 | 2025-10-22 | 2026-04-29 | 2026-05-11 | 189 | 201 | 2025-10 | 294 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 120/4 | 2025-10-26 | 2025-12-28 | 2026-01-02 | 63 | 68 | 2025-10 | 290 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 223/3 | 2025-10-27 | 2026-03-27 | 2026-04-03 | 151 | 158 | 2025-10 | 289 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 221/0 | 2025-11-05 | 2026-05-08 | 2026-05-24 | 184 | 200 | 2025-11 | 280 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 224/0 | 2025-11-08 |  |  |  |  | 2025-11 | 277 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 138/0 | 2025-11-13 | 2026-01-12 | 2026-01-22 | 60 | 70 | 2025-11 | 272 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 220/1 | 2025-11-14 | 2026-02-05 | 2026-02-20 | 83 | 98 | 2025-11 | 271 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 223/1 | 2025-11-14 | 2026-03-11 | 2026-03-19 | 117 | 125 | 2025-11 | 271 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 222/0 | 2025-11-15 | 2026-03-13 | 2026-04-02 | 118 | 138 | 2025-11 | 270 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 185/0 | 2025-11-16 | 2026-04-04 | 2026-04-20 | 139 | 155 | 2025-11 | 269 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 141/6 | 2025-11-17 | 2025-12-04 | 2025-12-19 | 17 | 32 | 2025-11 | 268 | TRUE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 220/0 | 2025-11-17 | 2026-04-10 | 2026-04-18 | 144 | 152 | 2025-11 | 268 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 223/2 | 2025-11-18 | 2026-05-18 | 2026-05-29 | 181 | 192 | 2025-11 | 267 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 219/1 | 2025-11-21 | 2026-05-18 | 2026-05-27 | 178 | 187 | 2025-11 | 264 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 223/0 | 2025-11-22 | 2026-02-20 | 2026-03-10 | 90 | 108 | 2025-11 | 263 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 218/0 | 2025-11-23 | 2026-02-16 | 2026-03-12 | 85 | 109 | 2025-11 | 262 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 144/0 | 2025-11-24 | 2026-03-16 | 2026-03-29 | 112 | 125 | 2025-11 | 261 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 196/0 | 2025-11-24 | 2026-02-06 | 2026-02-16 | 74 | 84 | 2025-11 | 261 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 142/0 | 2025-11-25 | 2025-12-19 | 2026-01-29 | 24 | 65 | 2025-11 | 260 | TRUE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 225/1 | 2025-11-25 | 2026-06-26 | 2026-07-27 | 213 | 244 | 2025-11 | 260 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 125/1 | 2025-11-26 | 2026-02-18 | 2026-03-01 | 84 | 95 | 2025-11 | 259 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 187/0 | 2025-11-26 | 2025-12-11 | 2025-12-20 | 15 | 24 | 2025-11 | 259 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 136/0 | 2025-11-27 | 2026-02-14 | 2026-02-24 | 79 | 89 | 2025-11 | 258 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 214/2 | 2025-11-27 | 2026-02-04 | 2026-02-08 | 69 | 73 | 2025-11 | 258 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 225/4 | 2025-11-29 | 2026-06-08 | 2026-06-28 | 191 | 211 | 2025-11 | 256 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 148/5 | 2025-11-30 | 2026-01-21 | 2026-01-31 | 52 | 62 | 2025-11 | 255 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 215/0 | 2025-11-30 | 2026-03-03 | 2026-03-12 | 93 | 102 | 2025-11 | 255 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 186/0 | 2025-12-01 | 2026-02-27 | 2026-03-17 | 88 | 106 | 2025-12 | 254 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 194/1 | 2025-12-02 | 2026-02-16 | 2026-02-23 | 76 | 83 | 2025-12 | 253 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 176/0 | 2025-12-03 | 2025-12-21 | 2025-12-28 | 18 | 25 | 2025-12 | 252 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 214/5 | 2025-12-03 | 2026-02-12 | 2026-02-16 | 71 | 75 | 2025-12 | 252 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 214/7 | 2025-12-04 | 2026-04-02 | 2026-04-09 | 119 | 126 | 2025-12 | 251 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 143/0 | 2025-12-05 | 2026-01-13 | 2026-01-28 | 39 | 54 | 2025-12 | 250 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 184/0 | 2025-12-05 | 2026-02-15 | 2026-03-11 | 72 | 96 | 2025-12 | 250 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 214/4 | 2025-12-05 | 2026-02-08 | 2026-02-12 | 65 | 69 | 2025-12 | 250 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 244/2 | 2025-12-06 | 2026-01-21 | 2026-02-02 | 46 | 58 | 2025-12 | 249 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 145/5 | 2025-12-07 | 2025-12-28 | 2026-01-04 | 21 | 28 | 2025-12 | 248 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 225/3 | 2025-12-10 | 2026-07-12 | 2026-08-08 | 214 | 241 | 2025-12 | 245 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 139/0 | 2025-12-11 | 2026-02-06 | 2026-02-14 | 57 | 65 | 2025-12 | 244 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 148/3 | 2025-12-11 | 2026-01-06 | 2026-01-21 | 26 | 41 | 2025-12 | 244 | TRUE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 183/0 | 2025-12-11 | 2026-01-11 | 2026-01-25 | 31 | 45 | 2025-12 | 244 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 217/4 | 2025-12-11 | 2026-03-13 | 2026-03-23 | 92 | 102 | 2025-12 | 244 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 250/2 | 2025-12-11 | 2026-02-01 | 2026-02-07 | 52 | 58 | 2025-12 | 244 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 127/2 | 2025-12-12 | 2026-06-14 | 2026-07-16 | 184 | 216 | 2025-12 | 243 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 183/2 | 2025-12-12 | 2026-02-02 | 2026-02-14 | 52 | 64 | 2025-12 | 243 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 214/3 | 2025-12-12 | 2026-03-13 | 2026-03-16 | 91 | 94 | 2025-12 | 243 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 214/6 | 2025-12-12 | 2026-02-27 | 2026-03-03 | 77 | 81 | 2025-12 | 243 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 249/3 | 2025-12-13 | 2025-12-24 | 2026-01-04 | 11 | 22 | 2025-12 | 242 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 182/0 | 2025-12-14 | 2026-01-03 | 2026-01-29 | 20 | 46 | 2025-12 | 241 | TRUE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 225/2 | 2025-12-14 | 2026-06-23 | 2026-07-12 | 191 | 210 | 2025-12 | 241 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 141/1 | 2025-12-15 | 2025-12-25 | 2025-12-31 | 10 | 16 | 2025-12 | 240 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 161/0 | 2025-12-16 | 2026-03-12 | 2026-03-16 | 86 | 90 | 2025-12 | 239 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 243/1 | 2025-12-16 | 2025-12-29 | 2026-01-21 | 13 | 36 | 2025-12 | 239 | TRUE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 189/1 | 2025-12-17 | 2026-01-30 | 2026-02-08 | 44 | 53 | 2025-12 | 238 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 145/6 | 2025-12-18 | 2026-01-04 | 2026-01-09 | 17 | 22 | 2025-12 | 237 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 141/2 | 2025-12-19 | 2026-01-02 | 2026-01-04 | 14 | 16 | 2025-12 | 236 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 175/1 | 2025-12-19 | 2025-12-28 | 2026-01-06 | 9 | 18 | 2025-12 | 236 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 217/2 | 2025-12-19 | 2026-03-23 | 2026-03-29 | 94 | 100 | 2025-12 | 236 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 217/3 | 2025-12-19 | 2026-03-19 | 2026-04-02 | 90 | 104 | 2025-12 | 236 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 166/0 | 2025-12-20 | 2026-04-06 | 2026-04-13 | 107 | 114 | 2025-12 | 235 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 165/6 | 2025-12-23 |  |  |  |  | 2025-12 | 232 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 180/6 | 2025-12-23 | 2026-01-06 | 2026-01-19 | 14 | 27 | 2025-12 | 232 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 191/1 | 2025-12-23 | 2026-02-20 | 2026-02-27 | 59 | 66 | 2025-12 | 232 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 199/1 | 2025-12-23 | 2026-02-27 | 2026-03-02 | 66 | 69 | 2025-12 | 232 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 257/0 | 2025-12-23 |  |  |  |  | 2025-12 | 232 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 216/1 | 2025-12-24 | 2026-06-15 | 2026-06-22 | 173 | 180 | 2025-12 | 231 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 254/1 | 2025-12-24 | 2026-02-02 | 2026-02-26 | 40 | 64 | 2025-12 | 231 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 127/0 | 2025-12-25 | 2026-02-22 | 2026-03-11 | 59 | 76 | 2025-12 | 230 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 148/1 | 2025-12-25 | 2026-01-25 | 2026-01-31 | 31 | 37 | 2025-12 | 230 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 190/0 | 2025-12-25 | 2026-01-17 | 2026-01-30 | 23 | 36 | 2025-12 | 230 | TRUE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 196/1 | 2025-12-25 | 2026-02-23 | 2026-03-03 | 60 | 68 | 2025-12 | 230 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 197/0 | 2025-12-26 | 2026-02-10 | 2026-02-16 | 46 | 52 | 2025-12 | 229 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 170/0 | 2025-12-27 |  |  |  |  | 2025-12 | 228 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 252/2 | 2025-12-27 | 2026-01-23 | 2026-02-01 | 27 | 36 | 2025-12 | 228 | TRUE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 197/2 | 2025-12-29 | 2026-01-15 | 2026-01-21 | 17 | 23 | 2025-12 | 226 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 196/2 | 2025-12-30 | 2026-02-16 | 2026-02-21 | 48 | 53 | 2025-12 | 225 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 252/1 | 2025-12-30 | 2026-01-19 | 2026-02-04 | 20 | 36 | 2025-12 | 225 | TRUE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 128/0 | 2025-12-31 | 2026-03-12 | 2026-03-27 | 71 | 86 | 2025-12 | 224 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 179/0 | 2025-12-31 | 2026-01-19 | 2026-02-02 | 19 | 33 | 2025-12 | 224 | TRUE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 183/3 | 2025-12-31 | 2026-03-16 | 2026-03-21 | 75 | 80 | 2025-12 | 224 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 216/2 | 2025-12-31 |  |  |  |  | 2025-12 | 224 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 241/1 | 2025-12-31 | 2026-05-02 | 2026-05-12 | 122 | 132 | 2025-12 | 224 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 141/0 | 2026-01-03 | 2026-01-28 | 2026-02-14 | 25 | 42 | 2026-01 | 221 | TRUE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 149/0 | 2026-01-03 | 2026-01-31 | 2026-03-22 | 28 | 78 | 2026-01 | 221 | TRUE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 167/0 | 2026-01-04 | 2026-04-14 | 2026-04-25 | 100 | 111 | 2026-01 | 220 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 127/1 | 2026-01-05 | 2026-03-27 | 2026-03-31 | 81 | 85 | 2026-01 | 219 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 139/1 | 2026-01-05 | 2026-01-31 | 2026-02-06 | 26 | 32 | 2026-01 | 219 | TRUE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 210/0 | 2026-01-05 | 2026-06-04 | 2026-06-14 | 150 | 160 | 2026-01 | 219 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 192/0 | 2026-01-06 | 2026-02-27 | 2026-03-12 | 52 | 65 | 2026-01 | 218 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 178/2 | 2026-01-07 | 2026-02-11 | 2026-02-23 | 35 | 47 | 2026-01 | 217 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 244/0 | 2026-01-09 | 2026-05-18 | 2026-06-05 | 129 | 147 | 2026-01 | 215 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 211/3 | 2026-01-10 | 2026-03-02 | 2026-03-27 | 51 | 76 | 2026-01 | 214 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 255/0 | 2026-01-10 | 2026-03-12 | 2026-03-25 | 61 | 74 | 2026-01 | 214 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 216/3 | 2026-01-12 |  |  |  |  | 2026-01 | 212 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 132/3 | 2026-01-13 | 2026-03-20 | 2026-03-25 | 66 | 71 | 2026-01 | 211 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 162/0 | 2026-01-13 |  |  |  |  | 2026-01 | 211 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 199/2 | 2026-01-13 | 2026-02-21 | 2026-02-27 | 39 | 45 | 2026-01 | 211 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 211/1 | 2026-01-13 | 2026-03-03 | 2026-03-10 | 49 | 56 | 2026-01 | 211 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 230/0 | 2026-01-13 | 2026-02-28 | 2026-03-11 | 46 | 57 | 2026-01 | 211 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 245/0 | 2026-01-13 | 2026-02-14 | 2026-02-25 | 32 | 43 | 2026-01 | 211 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 125/2 | 2026-01-15 | 2026-03-01 | 2026-03-14 | 45 | 58 | 2026-01 | 209 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 160/0 | 2026-01-15 | 2026-02-27 | 2026-03-11 | 43 | 55 | 2026-01 | 209 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 191/0 | 2026-01-15 | 2026-02-08 | 2026-02-20 | 24 | 36 | 2026-01 | 209 | TRUE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 178/1 | 2026-01-16 | 2026-02-05 | 2026-02-13 | 20 | 28 | 2026-01 | 208 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 199/0 | 2026-01-16 | 2026-01-21 | 2026-01-30 | 5 | 14 | 2026-01 | 208 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 245/1 | 2026-01-16 | 2026-01-31 | 2026-02-12 | 15 | 27 | 2026-01 | 208 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 194/0 | 2026-01-17 |  |  |  |  | 2026-01 | 207 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 133/0 | 2026-01-20 | 2026-04-08 | 2026-04-20 | 78 | 90 | 2026-01 | 204 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 174/3 | 2026-01-20 | 2026-03-29 | 2026-04-05 | 68 | 75 | 2026-01 | 204 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 227/0 | 2026-01-21 | 2026-03-13 | 2026-03-28 | 51 | 66 | 2026-01 | 203 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 250A/0 | 2026-01-21 | 2026-02-26 | 2026-03-24 | 36 | 62 | 2026-01 | 203 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 165/4 | 2026-01-22 |  |  |  |  | 2026-01 | 202 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 211/4 | 2026-01-22 |  |  |  |  | 2026-01 | 202 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 217/5 | 2026-01-22 | 2026-05-27 | 2026-06-02 | 125 | 131 | 2026-01 | 202 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 140/0 | 2026-01-23 | 2026-02-14 | 2026-02-27 | 22 | 35 | 2026-01 | 201 | TRUE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 193/0 | 2026-01-23 |  |  |  |  | 2026-01 | 201 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 198/0 | 2026-01-23 | 2026-02-04 | 2026-02-11 | 12 | 19 | 2026-01 | 201 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 216/0 | 2026-01-23 | 2026-02-17 | 2026-02-27 | 25 | 35 | 2026-01 | 201 | TRUE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 244/3 | 2026-01-23 | 2026-05-27 | 2026-06-07 | 124 | 135 | 2026-01 | 201 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 197/1 | 2026-01-24 | 2026-01-30 | 2026-02-04 | 6 | 11 | 2026-01 | 200 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 244/4 | 2026-01-25 | 2026-03-15 | 2026-04-04 | 49 | 69 | 2026-01 | 199 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 133/1 | 2026-01-26 | 2026-05-28 | 2026-06-05 | 122 | 130 | 2026-01 | 198 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 125/0 | 2026-01-27 | 2026-05-03 | 2026-05-16 | 96 | 109 | 2026-01 | 197 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 226/3 | 2026-01-27 | 2026-03-19 | 2026-03-27 | 51 | 59 | 2026-01 | 197 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 233/0 | 2026-01-27 |  |  |  |  | 2026-01 | 197 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 211/2 | 2026-01-28 | 2026-03-27 | 2026-03-30 | 58 | 61 | 2026-01 | 196 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 236/0 | 2026-01-28 |  |  |  |  | 2026-01 | 196 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 139/3 | 2026-01-29 | 2026-06-04 | 2026-06-14 | 126 | 136 | 2026-01 | 195 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 168/0 | 2026-01-29 |  |  |  |  | 2026-01 | 195 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 188/0 | 2026-01-29 |  |  |  |  | 2026-01 | 195 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 227/1 | 2026-01-29 | 2026-03-27 | 2026-04-08 | 57 | 69 | 2026-01 | 195 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 139/2 | 2026-01-30 | 2026-02-08 | 2026-02-25 | 9 | 26 | 2026-01 | 194 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 209/2 | 2026-01-30 | 2026-03-03 | 2026-03-10 | 32 | 39 | 2026-01 | 194 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 235/2 | 2026-01-30 | 2026-04-05 | 2026-04-12 | 65 | 72 | 2026-01 | 194 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 133/2 | 2026-01-31 | 2026-02-28 | 2026-03-12 | 28 | 40 | 2026-01 | 193 | TRUE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 211/5 | 2026-01-31 | 2026-04-05 | 2026-04-11 | 64 | 70 | 2026-01 | 193 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 211/0 | 2026-02-01 |  |  |  |  | 2026-02 | 192 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 238/0 | 2026-02-01 | 2026-06-18 | 2026-07-14 | 137 | 163 | 2026-02 | 192 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 174/2 | 2026-02-02 | 2026-03-11 | 2026-03-16 | 37 | 42 | 2026-02 | 191 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 250/1 | 2026-02-02 | 2026-06-08 | 2026-06-16 | 126 | 134 | 2026-02 | 191 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 252/4 | 2026-02-02 | 2026-03-24 | 2026-04-14 | 50 | 71 | 2026-02 | 191 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 240/0 | 2026-02-03 | 2026-02-26 | 2026-03-11 | 23 | 36 | 2026-02 | 190 | TRUE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 124/3 | 2026-02-05 | 2026-04-28 | 2026-05-03 | 82 | 87 | 2026-02 | 188 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 213/0 | 2026-02-05 | 2026-05-31 | 2026-06-26 | 115 | 141 | 2026-02 | 188 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 235/0 | 2026-02-07 |  |  |  |  | 2026-02 | 186 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 256/1 | 2026-02-07 | 2026-06-15 | 2026-06-28 | 128 | 141 | 2026-02 | 186 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 228/0 | 2026-02-10 | 2026-05-11 | 2026-05-19 | 90 | 98 | 2026-02 | 183 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 134/0 | 2026-02-11 | 2026-03-13 | 2026-03-20 | 30 | 37 | 2026-02 | 182 | TRUE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 124/2 | 2026-02-12 | 2026-05-22 | 2026-05-28 | 99 | 105 | 2026-02 | 181 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 235/3 | 2026-02-13 | 2026-03-19 | 2026-04-05 | 34 | 51 | 2026-02 | 180 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 242/0 | 2026-02-13 | 2026-04-09 | 2026-05-02 | 55 | 78 | 2026-02 | 180 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 214/0 | 2026-02-16 | 2026-04-29 | 2026-05-23 | 72 | 96 | 2026-02 | 177 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 217/1 | 2026-02-16 | 2026-06-10 | 2026-06-15 | 114 | 119 | 2026-02 | 177 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 237/0 | 2026-02-16 | 2026-05-03 | 2026-06-05 | 76 | 109 | 2026-02 | 177 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 147/0 | 2026-02-17 | 2026-04-07 | 2026-04-24 | 49 | 66 | 2026-02 | 176 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 228/1 | 2026-02-17 | 2026-03-12 | 2026-03-18 | 23 | 29 | 2026-02 | 176 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 174/0 | 2026-02-18 | 2026-05-03 | 2026-05-16 | 74 | 87 | 2026-02 | 175 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 235/1 | 2026-02-19 | 2026-06-05 | 2026-06-18 | 106 | 119 | 2026-02 | 174 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 232/4 | 2026-02-20 |  |  |  |  | 2026-02 | 173 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 240/1 | 2026-02-22 | 2026-03-12 | 2026-03-23 | 18 | 29 | 2026-02 | 171 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 133/4 | 2026-02-23 | 2026-04-03 | 2026-04-08 | 39 | 44 | 2026-02 | 170 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 214/1 | 2026-02-23 | 2026-04-09 | 2026-05-03 | 45 | 69 | 2026-02 | 170 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 217/0 | 2026-02-24 | 2026-06-02 | 2026-06-11 | 98 | 107 | 2026-02 | 169 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 173/0 | 2026-02-27 |  |  |  |  | 2026-02 | 166 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 248/0 | 2026-02-27 | 2026-06-16 | 2026-07-27 | 109 | 150 | 2026-02 | 166 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 219/0 | 2026-02-28 |  |  |  |  | 2026-02 | 165 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 239/0 | 2026-03-02 | 2026-03-25 | 2026-04-16 | 23 | 45 | 2026-03 | 163 | TRUE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 209/0 | 2026-03-03 | 2026-03-11 | 2026-03-17 | 8 | 14 | 2026-03 | 162 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 209/1 | 2026-03-03 | 2026-03-18 | 2026-03-22 | 15 | 19 | 2026-03 | 162 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 163/0 | 2026-03-04 |  |  |  |  | 2026-03 | 161 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 226/1 | 2026-03-08 | 2026-05-06 | 2026-05-18 | 59 | 71 | 2026-03 | 157 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 226/2 | 2026-03-09 | 2026-03-31 | 2026-04-17 | 22 | 39 | 2026-03 | 156 | TRUE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 232/0 | 2026-03-11 | 2026-05-21 | 2026-06-01 | 71 | 82 | 2026-03 | 154 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 239/1 | 2026-03-12 | 2026-04-05 | 2026-04-11 | 24 | 30 | 2026-03 | 153 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 133/3 | 2026-03-15 | 2026-03-25 | 2026-04-03 | 10 | 19 | 2026-03 | 150 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 207/0 | 2026-03-15 | 2026-04-02 | 2026-04-12 | 18 | 28 | 2026-03 | 150 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 227/2 | 2026-03-16 | 2026-04-08 | 2026-04-17 | 23 | 32 | 2026-03 | 149 | TRUE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 231/0 | 2026-03-16 |  |  |  |  | 2026-03 | 149 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 145/0 | 2026-03-18 | 2026-03-29 | 2026-04-07 | 11 | 20 | 2026-03 | 147 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 225/7 | 2026-03-22 | 2026-05-11 | 2026-06-07 | 50 | 77 | 2026-03 | 143 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 251/1 | 2026-03-22 | 2026-04-17 | 2026-05-08 | 26 | 47 | 2026-03 | 143 | TRUE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 121/11 | 2026-03-24 | 2026-04-01 | 2026-04-08 | 8 | 15 | 2026-03 | 141 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 150/1 | 2026-03-24 |  |  |  |  | 2026-03 | 141 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 225/5 | 2026-03-24 | 2026-05-11 | 2026-05-28 | 48 | 65 | 2026-03 | 141 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 234/0 | 2026-03-24 | 2026-05-12 | 2026-06-06 | 49 | 74 | 2026-03 | 141 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 179/2 | 2026-03-27 | 2026-03-27 | 2026-04-03 | 0 | 7 | 2026-03 | 138 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 226/0 | 2026-03-28 | 2026-04-20 | 2026-05-05 | 23 | 38 | 2026-03 | 137 | TRUE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 230/1 | 2026-03-29 | 2026-06-22 | 2026-07-20 | 85 | 113 | 2026-03 | 136 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 255/1 | 2026-03-29 | 2026-05-09 | 2026-05-26 | 41 | 58 | 2026-03 | 136 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 232/2 | 2026-03-31 | 2026-06-05 | 2026-06-23 | 66 | 84 | 2026-03 | 134 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 180/0 | 2026-04-05 |  |  |  |  | 2026-04 | 129 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 156/0 | 2026-04-06 |  |  |  |  | 2026-04 | 128 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 150/0 | 2026-04-12 |  |  |  |  | 2026-04 | 122 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 195/0 | 2026-04-12 | 2026-06-20 | 2026-07-12 | 69 | 91 | 2026-04 | 122 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 131/0 | 2026-04-16 |  |  |  |  | 2026-04 | 118 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 155/0 | 2026-04-18 |  |  |  |  | 2026-04 | 116 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 230A/0 | 2026-04-18 | 2026-06-01 | 2026-06-15 | 44 | 58 | 2026-04 | 116 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 200/0 | 2026-04-19 |  |  |  |  | 2026-04 | 115 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 131/1 | 2026-04-21 |  |  |  |  | 2026-04 | 113 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 151/0 | 2026-04-21 | 2026-05-19 | 2026-06-04 | 28 | 44 | 2026-04 | 113 | TRUE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 156/1 | 2026-04-24 | 2026-05-20 | 2026-05-27 | 26 | 33 | 2026-04 | 110 | TRUE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 153/1 | 2026-04-26 | 2026-06-08 | 2026-06-13 | 43 | 48 | 2026-04 | 108 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 159/0 | 2026-04-28 | 2026-05-27 | 2026-06-08 | 29 | 41 | 2026-04 | 106 | TRUE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 189/0 | 2026-04-28 |  |  |  |  | 2026-04 | 106 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 151A/0 | 2026-05-01 | 2026-06-06 | 2026-07-05 | 36 | 65 | 2026-05 | 103 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 164/0 | 2026-05-03 | 2026-06-22 | 2026-07-13 | 50 | 71 | 2026-05 | 101 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 235/4 | 2026-05-05 | 2026-06-05 | 2026-06-22 | 31 | 48 | 2026-05 | 99 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 169/0 | 2026-05-06 |  |  |  |  | 2026-05 | 98 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 165/0 | 2026-05-09 | 2026-06-17 | 2026-07-02 | 39 | 54 | 2026-05 | 95 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 232/3 | 2026-05-09 |  |  |  |  | 2026-05 | 95 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 129/0 | 2026-05-11 |  |  |  |  | 2026-05 | 93 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 206/0 | 2026-05-11 | 2026-06-12 | 2026-06-20 | 32 | 40 | 2026-05 | 93 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 145/1 | 2026-05-16 |  |  |  |  | 2026-05 | 88 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 206/1 | 2026-05-17 |  |  |  |  | 2026-05 | 87 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 153A/0 | 2026-05-20 | 2026-06-08 | 2026-06-17 | 19 | 28 | 2026-05 | 84 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 201/0 | 2026-05-20 | 2026-06-26 | 2026-07-15 | 37 | 56 | 2026-05 | 84 | FALSE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 229B/0 | 2026-05-22 |  |  |  |  | 2026-05 | 82 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 229A/0 | 2026-05-28 |  |  |  |  | 2026-05 | 76 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 229/0 | 2026-05-31 | 2026-06-15 | 2026-06-29 | 15 | 29 | 2026-05 | 73 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 154/0 | 2026-06-01 |  |  |  |  | 2026-06 | 72 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 212/0 | 2026-06-01 |  |  |  |  | 2026-06 | 72 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 254/0 | 2026-06-06 |  |  |  |  | 2026-06 | 67 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 132/2 | 2026-06-07 |  |  |  |  | 2026-06 | 66 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 208/0 | 2026-06-08 |  |  |  |  | 2026-06 | 65 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 225/6 | 2026-06-08 | 2026-06-18 | 2026-06-27 | 10 | 19 | 2026-06 | 65 | TRUE | TRUE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 130/0 | 2026-06-12 |  |  |  |  | 2026-06 | 61 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 152/0 | 2026-06-12 |  |  |  |  | 2026-06 | 61 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 253/0 | 2026-06-15 |  |  |  |  | 2026-06 | 58 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 165/3 | 2026-06-17 |  |  |  |  | 2026-06 | 56 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 229/1 | 2026-06-19 | 2026-06-26 | 2026-07-29 | 7 | 40 | 2026-06 | 54 | TRUE | FALSE | Yes | No | exact | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 165/1 | 2026-06-21 |  |  |  |  | 2026-06 | 52 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 202/0 | 2026-06-21 |  |  |  |  | 2026-06 | 52 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 135/0 | 2026-06-22 |  |  |  |  | 2026-06 | 51 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 153/2 | 2026-06-26 |  |  |  |  | 2026-06 | 47 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 200/1 | 2026-06-26 |  |  |  |  | 2026-06 | 47 | FALSE | FALSE | No | No |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 416 | 2/8 | 2024-05-06 | 2024-09-01 | 2024-09-16 | 118 | 133 | 2024-05 | 828 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 2/7 | 2024-05-10 | 2024-11-26 | 2024-12-03 | 200 | 207 | 2024-05 | 824 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 2/6 | 2024-05-14 | 2024-12-01 | 2024-12-09 | 201 | 209 | 2024-05 | 820 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 2/5 | 2024-05-18 | 2024-11-10 | 2024-11-24 | 176 | 190 | 2024-05 | 816 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 2/4 | 2024-05-21 | 2024-09-16 | 2024-09-29 | 118 | 131 | 2024-05 | 813 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 2/3 | 2024-05-28 | 2024-12-10 | 2024-12-16 | 196 | 202 | 2024-05 | 806 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 17/4 | 2024-06-03 | 2025-01-01 | 2025-01-10 | 212 | 221 | 2024-06 | 800 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 39/10 | 2024-06-04 | 2024-09-16 | 2024-10-01 | 104 | 119 | 2024-06 | 799 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 17/5 | 2024-06-06 | 2025-01-24 | 2025-01-29 | 232 | 237 | 2024-06 | 797 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 39/8 | 2024-06-08 | 2024-10-03 | 2024-10-15 | 117 | 129 | 2024-06 | 795 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 17/3 | 2024-06-09 | 2025-01-10 | 2025-01-17 | 215 | 222 | 2024-06 | 794 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 17/6 | 2024-06-11 | 2025-09-15 | 2025-09-24 | 461 | 470 | 2024-06 | 792 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 6/2 | 2024-06-12 | 2024-11-14 | 2024-11-25 | 155 | 166 | 2024-06 | 791 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 39/9 | 2024-06-13 | 2024-10-24 | 2024-10-31 | 133 | 140 | 2024-06 | 790 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 17/7 | 2024-06-14 | 2025-01-30 | 2025-02-05 | 230 | 236 | 2024-06 | 789 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 17/8 | 2024-06-17 | 2025-05-11 | 2025-05-15 | 328 | 332 | 2024-06 | 786 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 39/7 | 2024-06-19 | 2024-10-15 | 2024-10-24 | 118 | 127 | 2024-06 | 784 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 17/1 | 2024-06-20 | 2024-12-24 | 2024-12-31 | 187 | 194 | 2024-06 | 783 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 20/6 | 2024-06-22 | 2024-10-08 | 2024-10-13 | 108 | 113 | 2024-06 | 781 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 39/1 | 2024-06-23 | 2025-04-01 | 2025-04-12 | 282 | 293 | 2024-06 | 780 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 39/6 | 2024-06-25 | 2024-11-01 | 2024-11-14 | 129 | 142 | 2024-06 | 778 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 20/7 | 2024-06-27 | 2024-10-24 | 2024-10-29 | 119 | 124 | 2024-06 | 776 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 38/11 | 2024-06-30 | 2025-05-12 | 2025-05-19 | 316 | 323 | 2024-06 | 773 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 38/1 | 2024-07-11 | 2025-01-07 | 2025-01-17 | 180 | 190 | 2024-07 | 762 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 20/12 | 2024-07-15 | 2024-11-01 | 2024-11-04 | 109 | 112 | 2024-07 | 758 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 38/2 | 2024-07-18 | 2024-12-06 | 2024-12-19 | 141 | 154 | 2024-07 | 755 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 14/5 | 2024-07-20 | 2024-11-10 | 2024-11-17 | 113 | 120 | 2024-07 | 753 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 19/11 | 2024-07-23 | 2025-04-27 | 2025-04-30 | 278 | 281 | 2024-07 | 750 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 38/3 | 2024-07-25 | 2024-11-10 | 2024-11-25 | 108 | 123 | 2024-07 | 748 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 14/6 | 2024-07-28 | 2024-11-05 | 2024-11-10 | 100 | 105 | 2024-07 | 745 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 20/8 | 2024-07-29 | 2024-10-01 | 2024-10-07 | 64 | 70 | 2024-07 | 744 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 19/8 | 2024-07-30 | 2025-05-06 | 2025-05-09 | 280 | 283 | 2024-07 | 743 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 38/4 | 2024-07-31 | 2024-12-20 | 2024-12-31 | 142 | 153 | 2024-07 | 742 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 20/9 | 2024-08-03 | 2024-10-14 | 2024-10-19 | 72 | 77 | 2024-08 | 739 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 19/9 | 2024-08-04 | 2025-01-16 | 2025-01-27 | 165 | 176 | 2024-08 | 738 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 36/12 | 2024-08-08 | 2024-11-29 | 2024-12-06 | 113 | 120 | 2024-08 | 734 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 14/4 | 2024-08-09 | 2024-11-17 | 2024-11-22 | 100 | 105 | 2024-08 | 733 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 20/5 | 2024-08-10 | 2024-10-20 | 2024-10-24 | 71 | 75 | 2024-08 | 732 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 36/11 | 2024-08-14 | 2025-05-14 | 2025-05-19 | 273 | 278 | 2024-08 | 728 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 23/3 | 2024-08-18 | 2025-05-15 | 2025-05-22 | 270 | 277 | 2024-08 | 724 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 14/3 | 2024-08-21 | 2024-12-06 | 2024-12-12 | 107 | 113 | 2024-08 | 721 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 19/12 | 2024-08-24 | 2025-04-23 | 2025-04-26 | 242 | 245 | 2024-08 | 718 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 14/7 | 2024-08-30 | 2024-11-29 | 2024-12-05 | 91 | 97 | 2024-08 | 712 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 12/9 | 2024-08-31 | 2025-02-02 | 2025-02-08 | 155 | 161 | 2024-08 | 711 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 23/4 | 2024-08-31 | 2025-05-23 | 2025-05-28 | 265 | 270 | 2024-08 | 711 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 36/3 | 2024-08-31 | 2025-01-07 | 2025-01-15 | 129 | 137 | 2024-08 | 711 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 19/3 | 2024-09-05 | 2024-11-10 | 2024-11-26 | 66 | 82 | 2024-09 | 706 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 12/4 | 2024-09-08 | 2025-01-21 | 2025-01-25 | 135 | 139 | 2024-09 | 703 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 38/8 | 2024-09-08 | 2025-03-21 | 2025-03-31 | 194 | 204 | 2024-09 | 703 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 39/4 | 2024-09-08 | 2025-04-29 | 2025-05-04 | 233 | 238 | 2024-09 | 703 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 45/3 | 2024-09-08 | 2024-12-10 | 2024-12-20 | 93 | 103 | 2024-09 | 703 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 12/8 | 2024-09-09 | 2025-05-26 | 2025-05-31 | 259 | 264 | 2024-09 | 702 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 36/7 | 2024-09-09 | 2025-04-23 | 2025-04-28 | 226 | 231 | 2024-09 | 702 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 23/5 | 2024-09-11 | 2025-05-10 | 2025-05-27 | 241 | 258 | 2024-09 | 700 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 50/1 | 2024-09-11 | 2025-06-08 | 2025-06-13 | 270 | 275 | 2024-09 | 700 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 23/2 | 2024-09-20 | 2025-06-04 | 2025-06-09 | 257 | 262 | 2024-09 | 691 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 36/6 | 2024-09-20 | 2025-04-12 | 2025-04-22 | 204 | 214 | 2024-09 | 691 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 41/1 | 2024-09-20 | 2024-11-10 | 2024-11-29 | 51 | 70 | 2024-09 | 691 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 19/2 | 2024-09-22 | 2024-11-28 | 2024-12-05 | 67 | 74 | 2024-09 | 689 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 20/1 | 2024-09-22 | 2025-04-16 | 2025-04-22 | 206 | 212 | 2024-09 | 689 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 30/3 | 2024-09-22 | 2025-04-30 | 2025-05-06 | 220 | 226 | 2024-09 | 689 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 12/2 | 2024-09-24 | 2025-01-03 | 2025-01-11 | 101 | 109 | 2024-09 | 687 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 30/6 | 2024-09-24 | 2025-04-22 | 2025-04-28 | 210 | 216 | 2024-09 | 687 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 36/9 | 2024-09-24 | 2025-05-20 | 2025-05-24 | 238 | 242 | 2024-09 | 687 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 25/1 | 2024-09-26 | 2025-07-01 | 2025-07-12 | 278 | 289 | 2024-09 | 685 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 35/2 | 2024-09-26 | 2025-03-20 | 2025-03-30 | 175 | 185 | 2024-09 | 685 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 36/5 | 2024-09-26 | 2025-01-15 | 2025-01-24 | 111 | 120 | 2024-09 | 685 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 41/2 | 2024-09-26 | 2024-11-30 | 2024-12-10 | 65 | 75 | 2024-09 | 685 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 45/2 | 2024-09-29 | 2024-12-21 | 2024-12-27 | 83 | 89 | 2024-09 | 682 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 12/1 | 2024-09-30 | 2025-05-04 | 2025-05-10 | 216 | 222 | 2024-09 | 681 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 12/6 | 2024-09-30 | 2025-05-11 | 2025-05-22 | 223 | 234 | 2024-09 | 681 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 19/1 | 2024-09-30 | 2024-12-13 | 2024-12-21 | 74 | 82 | 2024-09 | 681 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 23/1 | 2024-09-30 | 2025-05-28 | 2025-06-03 | 240 | 246 | 2024-09 | 681 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 30/4 | 2024-09-30 | 2025-03-01 | 2025-03-09 | 152 | 160 | 2024-09 | 681 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 36/10 | 2024-09-30 | 2025-05-25 | 2025-05-31 | 237 | 243 | 2024-09 | 681 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 35/1 | 2024-10-01 | 2025-01-16 | 2025-01-28 | 107 | 119 | 2024-10 | 680 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 35/3 | 2024-10-01 | 2025-02-28 | 2025-03-08 | 150 | 158 | 2024-10 | 680 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 34/7 | 2024-10-03 | 2025-02-12 | 2025-02-20 | 132 | 140 | 2024-10 | 678 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 46/2 | 2024-10-03 | 2025-08-14 | 2025-08-26 | 315 | 327 | 2024-10 | 678 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 25/2 | 2024-10-04 | 2025-04-15 | 2025-04-23 | 193 | 201 | 2024-10 | 677 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 12/7 | 2024-10-06 | 2025-06-24 | 2025-06-30 | 261 | 267 | 2024-10 | 675 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 36/8 | 2024-10-06 | 2025-04-29 | 2025-05-05 | 205 | 211 | 2024-10 | 675 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 12/3 | 2024-10-07 | 2025-01-12 | 2025-01-21 | 97 | 106 | 2024-10 | 674 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 30/2 | 2024-10-07 | 2025-05-14 | 2025-05-20 | 219 | 225 | 2024-10 | 674 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 31/2 | 2024-10-07 | 2025-01-11 | 2025-01-19 | 96 | 104 | 2024-10 | 674 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 25/3 | 2024-10-08 | 2025-04-30 | 2025-05-07 | 204 | 211 | 2024-10 | 673 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 34/6 | 2024-10-08 | 2025-02-21 | 2025-02-27 | 136 | 142 | 2024-10 | 673 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 39/5 | 2024-10-08 | 2025-05-05 | 2025-05-11 | 209 | 215 | 2024-10 | 673 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 31/1 | 2024-10-10 | 2025-01-25 | 2025-02-02 | 107 | 115 | 2024-10 | 671 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 34/3 | 2024-10-10 | 2025-04-29 | 2025-05-03 | 201 | 205 | 2024-10 | 671 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 34/4 | 2024-10-10 | 2025-04-03 | 2025-04-10 | 175 | 182 | 2024-10 | 671 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 35/9 | 2024-10-10 | 2025-02-08 | 2025-02-15 | 121 | 128 | 2024-10 | 671 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 46/1 | 2024-10-10 | 2024-12-28 | 2025-01-04 | 79 | 86 | 2024-10 | 671 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 12/5 | 2024-10-13 | 2025-01-25 | 2025-02-01 | 104 | 111 | 2024-10 | 668 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 34/2 | 2024-10-13 | 2025-04-23 | 2025-04-28 | 192 | 197 | 2024-10 | 668 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 30/1 | 2024-10-14 | 2025-05-07 | 2025-05-13 | 205 | 211 | 2024-10 | 667 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 31/8 | 2024-10-14 | 2025-03-16 | 2025-03-23 | 153 | 160 | 2024-10 | 667 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4/2 | 2024-10-14 | 2024-12-12 | 2024-12-16 | 59 | 63 | 2024-10 | 667 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 30/5 | 2024-10-16 | 2025-03-10 | 2025-03-16 | 145 | 151 | 2024-10 | 665 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 33/1 | 2024-10-16 | 2025-03-12 | 2025-03-18 | 147 | 153 | 2024-10 | 665 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 36/2 | 2024-10-16 | 2025-02-02 | 2025-02-07 | 109 | 114 | 2024-10 | 665 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 31/10 | 2024-10-18 | 2025-03-24 | 2025-03-30 | 157 | 163 | 2024-10 | 663 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 33/11 | 2024-10-18 | 2025-02-02 | 2025-02-12 | 107 | 117 | 2024-10 | 663 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 14/2 | 2024-10-20 | 2024-12-12 | 2024-12-17 | 53 | 58 | 2024-10 | 661 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 31/3 | 2024-10-20 | 2024-12-24 | 2025-01-03 | 65 | 75 | 2024-10 | 661 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 33/2 | 2024-10-20 | 2025-03-19 | 2025-03-23 | 150 | 154 | 2024-10 | 661 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 20/2 | 2024-10-21 | 2025-02-07 | 2025-02-13 | 109 | 115 | 2024-10 | 660 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 34/1 | 2024-10-21 | 2025-03-01 | 2025-03-11 | 131 | 141 | 2024-10 | 660 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 35/8 | 2024-10-21 | 2025-03-22 | 2025-03-31 | 152 | 161 | 2024-10 | 660 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 52/9 | 2024-10-22 | 2025-05-13 | 2025-05-17 | 203 | 207 | 2024-10 | 659 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 33/10 | 2024-10-23 | 2025-01-21 | 2025-01-31 | 90 | 100 | 2024-10 | 658 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4/3 | 2024-10-23 | 2024-11-28 | 2024-12-05 | 36 | 43 | 2024-10 | 658 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 14/1 | 2024-10-24 | 2024-12-18 | 2024-12-23 | 55 | 60 | 2024-10 | 657 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 28/1 | 2024-10-24 | 2025-06-24 | 2025-07-05 | 243 | 254 | 2024-10 | 657 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 31/9 | 2024-10-24 | 2025-02-11 | 2025-02-20 | 110 | 119 | 2024-10 | 657 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 33/5 | 2024-10-24 | 2025-06-02 | 2025-06-10 | 221 | 229 | 2024-10 | 657 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 36/1 | 2024-10-24 | 2025-01-25 | 2025-01-30 | 93 | 98 | 2024-10 | 657 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 31/5 | 2024-10-25 | 2025-04-12 | 2025-04-21 | 169 | 178 | 2024-10 | 656 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 7/10 | 2024-10-25 | 2024-12-18 | 2024-12-23 | 54 | 59 | 2024-10 | 656 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 33/3 | 2024-10-26 | 2025-02-26 | 2025-03-02 | 123 | 127 | 2024-10 | 655 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 33/9 | 2024-10-26 | 2025-02-14 | 2025-02-22 | 111 | 119 | 2024-10 | 655 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 35/7 | 2024-10-26 | 2025-02-16 | 2025-02-21 | 113 | 118 | 2024-10 | 655 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 8B/3 | 2024-10-26 | 2025-03-28 | 2025-04-07 | 153 | 163 | 2024-10 | 655 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4/4 | 2024-10-27 | 2024-12-06 | 2024-12-12 | 40 | 46 | 2024-10 | 654 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 7/11 | 2024-10-27 | 2025-03-01 | 2025-03-08 | 125 | 132 | 2024-10 | 654 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 14/8 | 2024-11-01 | 2024-11-22 | 2024-11-28 | 21 | 27 | 2024-11 | 649 | TRUE | TRUE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 20/4 | 2024-11-01 | 2025-02-20 | 2025-02-25 | 111 | 116 | 2024-11 | 649 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 31/6 | 2024-11-01 | 2025-01-20 | 2025-01-25 | 80 | 85 | 2024-11 | 649 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 31/7 | 2024-11-01 | 2025-02-03 | 2025-02-10 | 94 | 101 | 2024-11 | 649 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 52/10 | 2024-11-01 | 2025-05-16 | 2025-05-21 | 196 | 201 | 2024-11 | 649 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 33/4 | 2024-11-02 | 2025-03-08 | 2025-03-11 | 126 | 129 | 2024-11 | 648 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 35/5 | 2024-11-02 | 2025-02-27 | 2025-03-03 | 117 | 121 | 2024-11 | 648 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 8B/1 | 2024-11-05 | 2025-03-22 | 2025-03-26 | 137 | 141 | 2024-11 | 645 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 33/6 | 2024-11-08 | 2025-02-14 | 2025-02-20 | 98 | 104 | 2024-11 | 642 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 31/4 | 2024-11-09 | 2025-01-04 | 2025-01-11 | 56 | 63 | 2024-11 | 641 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 34/0 | 2024-11-09 | 2025-03-24 | 2025-03-31 | 135 | 142 | 2024-11 | 641 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 17/2 | 2024-11-10 | 2025-01-17 | 2025-01-23 | 68 | 74 | 2024-11 | 640 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 35/4 | 2024-11-10 | 2025-02-20 | 2025-02-27 | 102 | 109 | 2024-11 | 640 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 19/4 | 2024-11-11 | 2024-12-06 | 2024-12-13 | 25 | 32 | 2024-11 | 639 | TRUE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 33/8 | 2024-11-11 | 2025-03-03 | 2025-03-07 | 112 | 116 | 2024-11 | 639 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 7/9 | 2024-11-11 | 2024-12-24 | 2024-12-30 | 43 | 49 | 2024-11 | 639 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 19/7 | 2024-11-13 | 2025-01-09 | 2025-01-17 | 57 | 65 | 2024-11 | 637 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 20/0 | 2024-11-13 | 2025-01-28 | 2025-02-06 | 76 | 85 | 2024-11 | 637 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 20/3 | 2024-11-13 | 2025-02-12 | 2025-02-19 | 91 | 98 | 2024-11 | 637 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 8B/2 | 2024-11-13 | 2025-04-08 | 2025-04-13 | 146 | 151 | 2024-11 | 637 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 33/7 | 2024-11-15 | 2025-02-21 | 2025-02-25 | 98 | 102 | 2024-11 | 635 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 7/8 | 2024-11-15 | 2025-01-08 | 2025-01-14 | 54 | 60 | 2024-11 | 635 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 32/0 | 2024-11-16 | 2025-04-01 | 2025-04-11 | 136 | 146 | 2024-11 | 634 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 10/1 | 2024-11-18 | 2025-04-12 | 2025-04-16 | 145 | 149 | 2024-11 | 632 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 19/5 | 2024-11-18 | 2024-12-22 | 2024-12-27 | 34 | 39 | 2024-11 | 632 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 39/3 | 2024-11-20 | 2025-03-24 | 2025-03-31 | 124 | 131 | 2024-11 | 630 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 19/6 | 2024-11-21 | 2024-12-28 | 2025-01-08 | 37 | 48 | 2024-11 | 629 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 33/0 | 2024-11-21 | 2025-04-12 | 2025-04-22 | 142 | 152 | 2024-11 | 629 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 36/4 | 2024-11-21 | 2025-05-07 | 2025-05-13 | 167 | 173 | 2024-11 | 629 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4/8 | 2024-11-21 | 2024-12-17 | 2024-12-22 | 26 | 31 | 2024-11 | 629 | TRUE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 8B/4 | 2024-11-21 | 2025-04-14 | 2025-04-21 | 144 | 151 | 2024-11 | 629 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 21/0 | 2024-11-22 | 2025-02-06 | 2025-02-13 | 76 | 83 | 2024-11 | 628 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 8/3 | 2024-11-22 | 2025-03-08 | 2025-03-12 | 106 | 110 | 2024-11 | 628 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 54/1 | 2024-11-23 | 2025-08-18 | 2025-09-04 | 268 | 285 | 2024-11 | 627 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 20/11 | 2024-11-24 | 2025-03-31 | 2025-04-08 | 127 | 135 | 2024-11 | 626 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 39/2 | 2024-11-26 | 2025-04-20 | 2025-04-26 | 145 | 151 | 2024-11 | 624 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 7/3 | 2024-11-26 | 2025-03-20 | 2025-03-27 | 114 | 121 | 2024-11 | 624 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 36/0 | 2024-11-27 | 2025-04-02 | 2025-04-14 | 126 | 138 | 2024-11 | 623 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 8/4 | 2024-11-27 | 2025-03-13 | 2025-03-21 | 106 | 114 | 2024-11 | 623 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 31/0 | 2024-11-29 | 2025-02-19 | 2025-02-28 | 82 | 91 | 2024-11 | 621 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 35/0 | 2024-11-29 | 2025-01-29 | 2025-02-11 | 61 | 74 | 2024-11 | 621 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 38/6 | 2024-11-29 | 2025-04-01 | 2025-04-11 | 123 | 133 | 2024-11 | 621 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4/7 | 2024-11-29 | 2024-12-24 | 2024-12-27 | 25 | 28 | 2024-11 | 621 | TRUE | TRUE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 7/2 | 2024-11-29 | 2024-12-31 | 2025-01-07 | 32 | 39 | 2024-11 | 621 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 8B/5 | 2024-11-29 | 2025-03-24 | 2025-03-31 | 115 | 122 | 2024-11 | 621 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 10/0 | 2024-11-30 | 2025-04-17 | 2025-04-28 | 138 | 149 | 2024-11 | 620 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 54/2 | 2024-12-01 | 2025-10-08 | 2025-10-22 | 311 | 325 | 2024-12 | 619 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 39/0 | 2024-12-02 | 2025-04-12 | 2025-04-19 | 131 | 138 | 2024-12 | 618 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 8/2 | 2024-12-03 | 2025-02-16 | 2025-02-21 | 75 | 80 | 2024-12 | 617 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 26/0 | 2024-12-04 | 2025-09-15 | 2025-09-25 | 285 | 295 | 2024-12 | 616 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 7/1 | 2024-12-04 | 2025-02-19 | 2025-02-25 | 77 | 83 | 2024-12 | 616 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4/5 | 2024-12-06 | 2024-12-28 | 2025-01-03 | 22 | 28 | 2024-12 | 614 | TRUE | TRUE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 17/0 | 2024-12-09 | 2025-09-11 | 2025-09-28 | 276 | 293 | 2024-12 | 611 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 5/1 | 2024-12-09 | 2025-03-16 | 2025-03-21 | 97 | 102 | 2024-12 | 611 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 7/4 | 2024-12-09 | 2025-02-10 | 2025-02-18 | 63 | 71 | 2024-12 | 611 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 7/7 | 2024-12-09 | 2025-01-15 | 2025-01-22 | 37 | 44 | 2024-12 | 611 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 8/1 | 2024-12-09 | 2025-02-09 | 2025-02-15 | 62 | 68 | 2024-12 | 611 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 3/0 | 2024-12-10 | 2025-06-12 | 2025-06-23 | 184 | 195 | 2024-12 | 610 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 56/5 | 2024-12-10 | 2025-05-30 | 2025-06-04 | 171 | 176 | 2024-12 | 610 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 38/10 | 2024-12-11 | 2025-05-20 | 2025-05-24 | 160 | 164 | 2024-12 | 609 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 55/1 | 2024-12-11 | 2025-11-09 | 2025-11-17 | 333 | 341 | 2024-12 | 609 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 7/5 | 2024-12-13 | 2025-01-29 | 2025-02-09 | 47 | 58 | 2024-12 | 607 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 49/0 | 2024-12-15 | 2025-11-06 | 2025-11-30 | 326 | 350 | 2024-12 | 605 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4/9 | 2024-12-16 | 2025-05-04 | 2025-05-11 | 139 | 146 | 2024-12 | 604 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 6/1 | 2024-12-16 | 2025-03-09 | 2025-03-19 | 83 | 93 | 2024-12 | 604 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 7/6 | 2024-12-16 | 2025-01-21 | 2025-01-30 | 36 | 45 | 2024-12 | 604 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 38/7 | 2024-12-17 | 2025-04-12 | 2025-04-22 | 116 | 126 | 2024-12 | 603 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4/0 | 2024-12-17 | 2025-04-06 | 2025-04-17 | 110 | 121 | 2024-12 | 603 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 56/8 | 2024-12-17 | 2025-08-18 | 2025-09-24 | 244 | 281 | 2024-12 | 603 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 52/7 | 2024-12-18 | 2025-12-06 | 2025-12-24 | 353 | 371 | 2024-12 | 602 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 48/1 | 2024-12-20 | 2025-09-15 | 2025-09-23 | 269 | 277 | 2024-12 | 600 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 7/0 | 2024-12-20 | 2025-02-27 | 2025-03-08 | 69 | 78 | 2024-12 | 600 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 8/0 | 2024-12-20 | 2025-02-22 | 2025-02-28 | 64 | 70 | 2024-12 | 600 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 47/0 | 2024-12-21 | 2025-09-07 | 2025-09-22 | 260 | 275 | 2024-12 | 599 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 56/1 | 2024-12-22 | 2025-05-14 | 2025-05-19 | 143 | 148 | 2024-12 | 598 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4/10 | 2024-12-24 | 2025-03-01 | 2025-03-05 | 67 | 71 | 2024-12 | 596 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 9/0 | 2024-12-24 | 2025-04-01 | 2025-04-11 | 98 | 108 | 2024-12 | 596 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 52/8 | 2024-12-27 | 2025-05-22 | 2025-05-27 | 146 | 151 | 2024-12 | 593 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 56/7 | 2024-12-27 | 2026-02-09 | 2026-03-09 | 409 | 437 | 2024-12 | 593 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 6/0 | 2024-12-27 | 2025-03-22 | 2025-03-29 | 85 | 92 | 2024-12 | 593 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 46/0 | 2024-12-28 | 2025-09-25 | 2025-10-08 | 271 | 284 | 2024-12 | 592 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4/6 | 2024-12-31 | 2025-03-28 | 2025-04-05 | 87 | 95 | 2024-12 | 589 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 54/0 | 2024-12-31 | 2025-09-25 | 2025-10-07 | 268 | 280 | 2024-12 | 589 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 53A/5 | 2025-01-02 | 2025-06-02 | 2025-06-14 | 151 | 163 | 2025-01 | 587 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 64/1 | 2025-01-02 | 2025-11-06 | 2025-11-30 | 308 | 332 | 2025-01 | 587 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 15/0 | 2025-01-03 | 2025-05-16 | 2025-05-25 | 133 | 142 | 2025-01 | 586 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 38/9 | 2025-01-03 | 2025-04-23 | 2025-06-01 | 110 | 149 | 2025-01 | 586 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 53A/7 | 2025-01-07 | 2025-12-08 | 2026-01-07 | 335 | 365 | 2025-01 | 582 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 5/0 | 2025-01-09 | 2025-03-01 | 2025-03-13 | 51 | 63 | 2025-01 | 580 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 8A/0 | 2025-01-09 | 2025-04-22 | 2025-04-30 | 103 | 111 | 2025-01 | 580 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 53A/0 | 2025-01-10 | 2025-11-15 | 2025-11-30 | 309 | 324 | 2025-01 | 579 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 70/0 | 2025-01-10 | 2025-12-20 | 2026-01-10 | 344 | 365 | 2025-01 | 579 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 52/0 | 2025-01-11 | 2025-09-05 | 2025-09-22 | 237 | 254 | 2025-01 | 578 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 53A/4 | 2025-01-11 | 2025-04-01 | 2025-04-12 | 80 | 91 | 2025-01 | 578 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 56/0 | 2025-01-11 | 2025-06-28 | 2025-07-22 | 168 | 192 | 2025-01 | 578 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 64/2 | 2025-01-11 | 2026-01-20 | 2026-01-29 | 374 | 383 | 2025-01 | 578 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 28/0 | 2025-01-12 | 2025-07-08 | 2025-07-31 | 177 | 200 | 2025-01 | 577 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 48/0 | 2025-01-12 | 2025-06-15 | 2025-06-29 | 154 | 168 | 2025-01 | 577 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 19/10 | 2025-01-14 | 2025-04-30 | 2025-05-06 | 106 | 112 | 2025-01 | 575 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 8B/0 | 2025-01-14 | 2025-05-05 | 2025-05-14 | 111 | 120 | 2025-01 | 575 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 53/0 | 2025-01-15 | 2025-09-26 | 2025-10-14 | 254 | 272 | 2025-01 | 574 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 22A/0 | 2025-01-17 | 2025-12-15 | 2026-01-17 | 332 | 365 | 2025-01 | 572 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 57/0 | 2025-01-17 | 2025-12-22 | 2026-01-17 | 339 | 365 | 2025-01 | 572 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 58/0 | 2025-01-17 | 2025-12-01 | 2026-01-17 | 318 | 365 | 2025-01 | 572 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 53A/2 | 2025-01-18 | 2025-06-10 | 2025-06-18 | 143 | 151 | 2025-01 | 571 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 20/10 | 2025-01-20 | 2025-04-09 | 2025-04-15 | 79 | 85 | 2025-01 | 569 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 52/3 | 2025-01-20 | 2025-04-30 | 2025-05-06 | 100 | 106 | 2025-01 | 569 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 55/0 | 2025-01-22 | 2025-10-15 | 2025-11-07 | 266 | 289 | 2025-01 | 567 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 53A/6 | 2025-01-23 | 2025-07-27 | 2025-08-17 | 185 | 206 | 2025-01 | 566 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 51/0 | 2025-01-24 | 2025-05-27 | 2025-06-07 | 123 | 134 | 2025-01 | 565 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 53A/3 | 2025-01-25 | 2025-06-20 | 2025-06-29 | 146 | 155 | 2025-01 | 564 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 27/0 | 2025-01-29 | 2025-09-22 | 2025-10-12 | 236 | 256 | 2025-01 | 560 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 45/1 | 2025-01-30 | 2025-06-10 | 2025-06-27 | 131 | 148 | 2025-01 | 559 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 0/2 | 2025-01-31 | 2025-05-23 | 2025-05-30 | 112 | 119 | 2025-01 | 558 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 0/3 | 2025-01-31 | 2025-05-25 | 2025-06-04 | 114 | 124 | 2025-01 | 558 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 21/3 | 2025-01-31 | 2025-07-01 | 2025-07-07 | 151 | 157 | 2025-01 | 558 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 52/6 | 2025-01-31 | 2025-04-05 | 2025-04-16 | 64 | 75 | 2025-01 | 558 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 53/1 | 2025-02-03 | 2025-05-12 | 2025-05-22 | 98 | 108 | 2025-02 | 555 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 24/0 | 2025-02-04 | 2025-07-26 | 2025-08-27 | 172 | 204 | 2025-02 | 554 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 42/0 | 2025-02-05 | 2025-09-23 | 2025-10-14 | 230 | 251 | 2025-02 | 553 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 35/6 | 2025-02-06 | 2025-03-10 | 2025-03-18 | 32 | 40 | 2025-02 | 552 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 22/0 | 2025-02-07 | 2025-06-12 | 2025-06-20 | 125 | 133 | 2025-02 | 551 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 56/2 | 2025-02-07 | 2025-05-07 | 2025-05-14 | 89 | 96 | 2025-02 | 551 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 0/4 | 2025-02-09 | 2025-04-12 | 2025-04-26 | 62 | 76 | 2025-02 | 549 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 29/0 | 2025-02-09 | 2025-08-06 | 2025-09-22 | 178 | 225 | 2025-02 | 549 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 52/4 | 2025-02-10 | 2025-04-26 | 2025-04-29 | 75 | 78 | 2025-02 | 548 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 0/1 | 2025-02-15 | 2025-06-04 | 2025-06-11 | 109 | 116 | 2025-02 | 543 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 40/0 | 2025-02-15 | 2025-06-04 | 2025-06-30 | 109 | 135 | 2025-02 | 543 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 52/5 | 2025-02-15 | 2025-04-17 | 2025-04-25 | 61 | 69 | 2025-02 | 543 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 59/0 | 2025-02-15 | 2025-11-16 | 2025-12-04 | 274 | 292 | 2025-02 | 543 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 25/0 | 2025-02-18 | 2025-08-28 | 2025-09-29 | 191 | 223 | 2025-02 | 540 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 64/0 | 2025-02-18 | 2025-08-31 | 2025-09-22 | 194 | 216 | 2025-02 | 540 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 30/0 | 2025-02-21 | 2025-05-25 | 2025-06-21 | 93 | 120 | 2025-02 | 537 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 43/0 | 2025-02-21 | 2025-08-10 | 2025-09-06 | 170 | 197 | 2025-02 | 537 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 52/2 | 2025-02-21 | 2025-05-07 | 2025-05-12 | 75 | 80 | 2025-02 | 537 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4/1 | 2025-02-22 | 2025-03-31 | 2025-04-11 | 37 | 48 | 2025-02 | 536 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 56/3 | 2025-02-23 | 2025-05-20 | 2025-05-24 | 86 | 90 | 2025-02 | 535 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 63/0 | 2025-02-27 | 2025-10-01 | 2025-10-12 | 216 | 227 | 2025-02 | 531 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 11/0 | 2025-02-28 | 2025-08-24 | 2025-09-14 | 177 | 198 | 2025-02 | 530 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 21/2 | 2025-02-28 | 2025-06-21 | 2025-06-26 | 113 | 118 | 2025-02 | 530 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 53A/1 | 2025-02-28 | 2025-09-18 | 2025-10-13 | 202 | 227 | 2025-02 | 530 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 13/0 | 2025-03-03 | 2025-07-09 | 2025-08-11 | 128 | 161 | 2025-03 | 527 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 50/0 | 2025-03-04 | 2025-09-25 | 2025-10-14 | 205 | 224 | 2025-03 | 526 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 23/0 | 2025-03-08 | 2025-11-17 | 2025-12-14 | 254 | 281 | 2025-03 | 522 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 60/0 | 2025-03-08 | 2025-11-08 | 2025-11-29 | 245 | 266 | 2025-03 | 522 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 14/0 | 2025-03-09 | 2025-06-01 | 2025-06-30 | 84 | 113 | 2025-03 | 521 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 34/5 | 2025-03-09 | 2025-06-12 | 2025-06-18 | 95 | 101 | 2025-03 | 521 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 12/0 | 2025-03-10 | 2025-08-12 | 2025-09-02 | 155 | 176 | 2025-03 | 520 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 56/4 | 2025-03-11 | 2025-05-23 | 2025-05-30 | 73 | 80 | 2025-03 | 519 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 61/0 | 2025-03-20 | 2025-09-25 | 2025-11-14 | 189 | 239 | 2025-03 | 510 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 67/0 | 2025-03-20 | 2026-02-09 | 2026-03-23 | 326 | 368 | 2025-03 | 510 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 52/1 | 2025-03-22 | 2025-10-27 | 2025-11-10 | 219 | 233 | 2025-03 | 508 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 18/0 | 2025-03-25 | 2025-08-04 | 2025-08-30 | 132 | 158 | 2025-03 | 505 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 64/3 | 2025-03-26 | 2025-09-24 | 2025-10-07 | 182 | 195 | 2025-03 | 504 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 66/1 | 2025-03-26 | 2025-11-27 | 2025-12-07 | 246 | 256 | 2025-03 | 504 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 62/0 | 2025-03-27 | 2025-11-10 | 2025-12-04 | 228 | 252 | 2025-03 | 503 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 19/0 | 2025-03-30 | 2025-08-31 | 2025-09-24 | 154 | 178 | 2025-03 | 500 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 56/6 | 2025-04-02 | 2025-11-01 | 2025-11-15 | 213 | 227 | 2025-04 | 497 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 57/1 | 2025-04-02 | 2025-12-07 | 2025-12-21 | 249 | 263 | 2025-04 | 497 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 21/1 | 2025-04-03 | 2025-06-27 | 2025-06-30 | 85 | 88 | 2025-04 | 496 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 16/0 | 2025-04-10 | 2025-08-16 | 2025-09-14 | 128 | 157 | 2025-04 | 489 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 66/0 A,B | 2025-04-10 | 2025-12-05 |  | 239 |  | 2025-04 | 489 | FALSE | FALSE | Yes | No | alias | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 66/0 C,D | 2025-04-10 | 2025-12-05 |  | 239 |  | 2025-04 | 489 | FALSE | FALSE | Yes | No | alias | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 68/0 | 2025-04-17 | 2025-11-30 | 2026-01-19 | 227 | 277 | 2025-04 | 482 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 2/1 | 2025-04-21 | 2025-05-12 | 2025-05-21 | 21 | 30 | 2025-04 | 478 | TRUE | TRUE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 44/0 | 2025-04-21 | 2025-07-05 | 2025-07-18 | 75 | 88 | 2025-04 | 478 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 1/0 | 2025-04-27 | 2025-08-09 | 2025-08-30 | 104 | 125 | 2025-04 | 472 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 65/0 | 2025-04-28 | 2025-08-02 | 2025-08-30 | 96 | 124 | 2025-04 | 471 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 2/0 | 2025-04-29 | 2025-09-03 | 2025-09-21 | 127 | 145 | 2025-04 | 470 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 2/2 | 2025-04-30 | 2025-11-01 | 2025-11-13 | 185 | 197 | 2025-04 | 469 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 38/5 | 2025-05-11 | 2025-05-28 | 2025-06-02 | 17 | 22 | 2025-05 | 458 | TRUE | TRUE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 45/0 | 2025-05-11 | 2025-10-09 | 2025-11-07 | 151 | 180 | 2025-05 | 458 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 0/0 | 2025-05-17 | 2025-10-03 | 2025-10-28 | 139 | 164 | 2025-05 | 452 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 69/0 | 2025-05-19 | 2026-01-20 | 2026-02-08 | 246 | 265 | 2025-05 | 450 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 37/0 | 2025-05-23 | 2025-09-23 | 2025-10-31 | 123 | 161 | 2025-05 | 446 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 69A/0 | 2025-05-28 | 2025-11-15 | 2025-11-29 | 171 | 185 | 2025-05 | 441 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 38/0 | 2025-06-03 | 2025-10-08 | 2025-10-26 | 127 | 145 | 2025-06 | 435 | FALSE | FALSE | Yes | No | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4/0-5/0 | 2025-10-14 |  |  |  |  | 2025-10 | 302 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 5/0-7/6 | 2025-10-22 |  |  |  |  | 2025-10 | 294 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 7/6-8B/0 | 2025-10-25 |  |  |  |  | 2025-10 | 291 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 34/0-35/0 | 2025-10-28 |  |  |  |  | 2025-10 | 288 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 35/0-36/0 | 2025-11-01 |  |  |  |  | 2025-11 | 284 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 33/0-34/0 | 2025-11-04 |  |  |  |  | 2025-11 | 281 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 31/0-33/0 | 2025-11-10 |  |  |  |  | 2025-11 | 275 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 30/0-31/0 | 2025-11-16 |  |  |  |  | 2025-11 | 269 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 12/0-14/0 | 2025-11-20 |  |  |  |  | 2025-11 | 265 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 20/0-21/0 | 2025-11-30 |  |  |  |  | 2025-11 | 255 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 19/0-20/0 | 2025-12-06 |  |  |  |  | 2025-12 | 249 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 66/0 | 2025-12-19 | 2025-12-05 | 2025-12-19 | -14 | 0 | 2025-12 | 236 | FALSE | FALSE | Yes | Yes | exact | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 0/0-2/0 | 2026-02-06 |  |  |  |  | 2026-02 | 187 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 2/0-3/0 | 2026-02-10 |  |  |  |  | 2026-02 | 183 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 36/0-37/0 | 2026-02-10 |  |  |  |  | 2026-02 | 183 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 14/0-17/0 | 2026-02-14 |  |  |  |  | 2026-02 | 179 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 37/0-38/11 | 2026-02-16 |  |  |  |  | 2026-02 | 177 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 8B/0-12/0 | 2026-02-18 |  |  |  |  | 2026-02 | 175 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 38/11-40/0 | 2026-02-20 |  |  |  |  | 2026-02 | 173 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 21/0-25/0 | 2026-02-23 |  |  |  |  | 2026-02 | 170 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 17/0-19/0 | 2026-02-28 |  |  |  |  | 2026-02 | 165 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 25/0-30/0 | 2026-02-28 |  |  |  |  | 2026-02 | 165 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 40/0-47/0 | 2026-05-03 |  |  |  |  | 2026-05 | 101 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 52/1-53/0 | 2026-05-06 |  |  |  |  | 2026-05 | 98 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 53/0-54/0 | 2026-05-09 |  |  |  |  | 2026-05 | 95 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 54/0-56/6 | 2026-06-29 |  |  |  |  | 2026-06 | 44 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 56/6-64/0 | 2026-07-03 |  |  |  |  | 2026-07 | 40 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 64/0-Gantry | 2026-07-08 |  |  |  |  | 2026-07 | 35 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 52/1-64/0 | 2026-07-12 |  |  |  |  | 2026-07 | 31 | FALSE | FALSE | No | No |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 418 | 33/10 | 2024-01-05 | 2024-12-29 | 2025-01-05 | 359 | 366 | 2024-01 | 950 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 40/4 | 2024-01-07 | 2024-12-30 | 2025-01-07 | 358 | 366 | 2024-01 | 948 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 42/1 | 2024-06-22 | 2024-12-12 | 2024-12-18 | 173 | 179 | 2024-06 | 781 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 42/2 | 2024-06-29 | 2024-12-03 | 2024-12-11 | 157 | 165 | 2024-06 | 774 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 54/4 | 2024-07-11 | 2024-01-09 | 2025-01-15 | -184 | 188 | 2024-07 | 762 | FALSE | FALSE | Yes | Yes | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 41/3 | 2024-07-12 | 2024-12-06 | 2024-12-11 | 147 | 152 | 2024-07 | 761 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 40/1 | 2024-07-16 | 2024-11-26 | 2024-12-01 | 133 | 138 | 2024-07 | 757 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 55/1 | 2024-07-16 | 2025-01-16 | 2025-01-23 | 184 | 191 | 2024-07 | 757 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 41/2 | 2024-07-23 | 2025-02-12 | 2025-02-17 | 204 | 209 | 2024-07 | 750 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 55/2 | 2024-07-23 | 2025-01-25 | 2025-02-02 | 186 | 194 | 2024-07 | 750 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 40/5 | 2024-07-26 | 2025-05-29 | 2025-06-02 | 307 | 311 | 2024-07 | 747 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 40/2 | 2024-07-31 | 2024-12-02 | 2024-12-06 | 124 | 128 | 2024-07 | 742 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 54/3 | 2024-08-02 | 2025-02-12 | 2025-02-20 | 194 | 202 | 2024-08 | 740 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 40/3 | 2024-08-03 | 2025-04-02 | 2025-04-05 | 242 | 245 | 2024-08 | 739 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 35/4 | 2024-08-06 | 2024-11-19 | 2024-11-24 | 105 | 110 | 2024-08 | 736 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 41/4 | 2024-08-10 | 2024-12-12 | 2024-12-18 | 124 | 130 | 2024-08 | 732 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 55/3 | 2024-08-10 | 2025-01-24 | 2025-02-11 | 167 | 185 | 2024-08 | 732 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 35/3 | 2024-08-11 | 2025-05-30 | 2025-06-04 | 292 | 297 | 2024-08 | 731 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 35/6 | 2024-08-21 |  |  |  |  | 2024-08 | 721 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 41/1 | 2024-08-26 | 2025-02-06 | 2025-02-11 | 164 | 169 | 2024-08 | 716 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 35/7 | 2024-08-27 | 2024-12-19 | 2024-12-29 | 114 | 124 | 2024-08 | 715 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 35/8 | 2024-09-03 | 2025-01-31 | 2025-02-05 | 150 | 155 | 2024-09 | 708 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 34/3 | 2024-09-08 | 2024-11-14 | 2024-11-19 | 67 | 72 | 2024-09 | 703 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 35/11 | 2024-09-10 | 2024-12-19 | 2024-12-27 | 100 | 108 | 2024-09 | 701 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 34/4 | 2024-09-12 | 2025-05-22 | 2025-05-28 | 252 | 258 | 2024-09 | 699 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 34/1 | 2024-09-16 | 2024-10-09 | 2024-10-27 | 23 | 41 | 2024-09 | 695 | TRUE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 52/2 | 2024-09-19 | 2025-12-17 | 2025-12-22 | 454 | 459 | 2024-09 | 692 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 33/12 | 2024-09-28 | 2024-10-28 | 2024-11-05 | 30 | 38 | 2024-09 | 683 | TRUE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 33/11 | 2024-10-03 | 2025-05-11 | 2025-05-26 | 220 | 235 | 2024-10 | 678 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 46/14 | 2024-10-11 | 2024-01-07 | 2025-01-11 | -278 | 92 | 2024-10 | 670 | FALSE | FALSE | Yes | Yes | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 46/8 | 2024-10-19 | 2025-01-13 | 2025-01-18 | 86 | 91 | 2024-10 | 662 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 34/0 | 2024-10-29 | 2025-04-22 | 2025-04-29 | 175 | 182 | 2024-10 | 652 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 33/7 | 2024-11-04 | 2025-06-03 | 2025-06-08 | 211 | 216 | 2024-11 | 646 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 33/9 | 2024-11-11 | 2025-06-12 | 2025-06-17 | 213 | 218 | 2024-11 | 639 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 35/06 | 2024-11-13 | 2024-11-05 | 2024-11-13 | -8 | 0 | 2024-11 | 637 | FALSE | FALSE | Yes | Yes | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 46/7 | 2024-11-22 | 2025-03-12 | 2025-03-17 | 110 | 115 | 2024-11 | 628 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 33/8 | 2024-11-27 | 2025-06-09 | 2025-06-12 | 194 | 197 | 2024-11 | 623 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 41/0 | 2024-12-05 | 2025-02-21 | 2025-02-26 | 78 | 83 | 2024-12 | 615 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 43/0 | 2024-12-18 | 2025-02-26 | 2025-03-03 | 70 | 75 | 2024-12 | 602 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 45/02 | 2024-12-20 |  |  |  |  | 2024-12 | 600 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 46/4 | 2024-12-24 | 2025-01-16 | 2025-01-23 | 23 | 30 | 2024-12 | 596 | TRUE | TRUE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 34/2 | 2024-12-26 | 2025-01-24 | 2025-01-30 | 29 | 35 | 2024-12 | 594 | TRUE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 45/0 | 2024-12-30 | 2025-03-18 | 2025-03-23 | 78 | 83 | 2024-12 | 590 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 46/0 | 2025-01-11 | 2025-03-03 | 2025-03-08 | 51 | 56 | 2025-01 | 578 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 35/0 | 2025-01-13 | 2025-05-08 | 2025-05-17 | 115 | 124 | 2025-01 | 576 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 46/15 | 2025-01-13 | 2025-04-27 | 2025-05-03 | 104 | 110 | 2025-01 | 576 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 45/1 | 2025-01-21 | 2025-03-18 | 2025-03-28 | 56 | 66 | 2025-01 | 568 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 46/9 | 2025-01-23 | 2025-03-06 | 2025-03-11 | 42 | 47 | 2025-01 | 566 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 33/5 | 2025-01-24 | 2025-04-11 | 2025-04-21 | 77 | 87 | 2025-01 | 565 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 33/1 | 2025-02-01 | 2025-09-22 | 2025-09-30 | 233 | 241 | 2025-02 | 557 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 42/0 | 2025-02-03 | 2025-04-05 | 2025-04-10 | 61 | 66 | 2025-02 | 555 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 46/5 | 2025-02-10 | 2025-05-11 | 2025-05-19 | 90 | 98 | 2025-02 | 548 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 32/0 | 2025-02-16 | 2025-10-04 | 2025-10-17 | 230 | 243 | 2025-02 | 542 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 55/0 | 2025-02-19 | 2025-04-18 | 2025-04-26 | 58 | 66 | 2025-02 | 539 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 40/0 | 2025-02-20 | 2025-07-03 | 2025-07-21 | 133 | 151 | 2025-02 | 538 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 55/4 | 2025-02-24 | 2025-04-12 | 2025-04-18 | 47 | 53 | 2025-02 | 534 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 37/0 | 2025-03-01 | 2025-07-03 | 2025-07-14 | 124 | 135 | 2025-03 | 529 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 37/1 | 2025-03-02 | 2025-04-29 | 2025-05-07 | 58 | 66 | 2025-03 | 528 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 48A/0 | 2025-03-05 | 2025-08-07 | 2025-08-16 | 155 | 164 | 2025-03 | 525 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 60/4 | 2025-03-10 | 2025-10-18 | 2025-10-27 | 222 | 231 | 2025-03 | 520 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 37/2 | 2025-03-12 | 2025-07-14 | 2025-07-20 | 124 | 130 | 2025-03 | 518 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 47/1 | 2025-03-19 | 2025-11-21 | 2025-11-27 | 247 | 253 | 2025-03 | 511 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 46/2 | 2025-03-21 | 2025-05-05 | 2025-05-10 | 45 | 50 | 2025-03 | 509 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 38/1 | 2025-03-24 | 2025-07-15 | 2025-07-23 | 113 | 121 | 2025-03 | 506 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 54/2 | 2025-03-24 | 2026-01-22 | 2026-01-28 | 304 | 310 | 2025-03 | 506 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 45/2 | 2025-04-01 | 2025-03-28 | 2025-04-01 | -4 | 0 | 2025-04 | 498 | FALSE | FALSE | Yes | Yes | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 38/2 | 2025-04-04 | 2025-07-03 | 2025-07-12 | 90 | 99 | 2025-04 | 495 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 61/0 | 2025-04-04 | 2025-09-14 | 2025-09-25 | 163 | 174 | 2025-04 | 495 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 54/1 | 2025-04-11 | 2025-09-28 | 2025-10-05 | 170 | 177 | 2025-04 | 488 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 60/2 | 2025-04-18 | 2025-08-26 | 2025-10-17 | 130 | 182 | 2025-04 | 481 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 60/0 | 2025-04-25 | 2025-11-30 | 2025-12-07 | 219 | 226 | 2025-04 | 474 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 56/0 | 2025-05-01 | 2025-09-05 | 2025-10-03 | 127 | 155 | 2025-05 | 468 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 46/13 | 2025-05-05 | 2025-08-09 | 2025-08-22 | 96 | 109 | 2025-05 | 464 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 36/0 | 2025-05-11 | 2025-06-19 | 2025-07-01 | 39 | 51 | 2025-05 | 458 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 59/0 | 2025-05-14 | 2026-01-07 | 2026-01-18 | 238 | 249 | 2025-05 | 455 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 46/12 | 2025-05-15 | 2025-09-03 | 2025-09-07 | 111 | 115 | 2025-05 | 454 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 43/2 | 2025-05-19 | 2025-11-06 | 2025-11-13 | 171 | 178 | 2025-05 | 450 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 45/3 | 2025-05-23 | 2025-09-09 | 2025-09-30 | 109 | 130 | 2025-05 | 446 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 48/1 | 2025-05-23 | 2025-08-16 | 2025-09-01 | 85 | 101 | 2025-05 | 446 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 48/2 | 2025-05-24 | 2025-09-09 | 2025-09-13 | 108 | 112 | 2025-05 | 445 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 52/0 | 2025-05-26 | 2025-08-19 | 2025-08-26 | 85 | 92 | 2025-05 | 443 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 41/5 | 2025-06-01 | 2025-07-24 | 2025-08-06 | 53 | 66 | 2025-06 | 437 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 33/6 | 2025-06-02 | 2025-06-14 | 2025-06-24 | 12 | 22 | 2025-06 | 436 | TRUE | TRUE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 35/1 | 2025-06-03 | 2025-07-21 | 2025-08-07 | 48 | 65 | 2025-06 | 435 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 35/2 | 2025-06-09 | 2025-06-29 | 2025-08-07 | 20 | 59 | 2025-06 | 429 | TRUE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 35/10 | 2025-06-10 | 2025-08-07 | 2025-08-17 | 58 | 68 | 2025-06 | 428 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 35/5 | 2025-06-11 | 2025-07-22 | 2025-07-30 | 41 | 49 | 2025-06 | 427 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 33/0 | 2025-06-16 | 2025-10-16 | 2025-11-07 | 122 | 144 | 2025-06 | 422 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 43/1 | 2025-06-18 | 2025-08-18 | 2025-08-26 | 61 | 69 | 2025-06 | 420 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 35/9 | 2025-06-20 | 2025-07-21 | 2025-07-31 | 31 | 41 | 2025-06 | 418 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 36/1 | 2025-06-20 | 2025-08-06 | 2025-08-19 | 47 | 60 | 2025-06 | 418 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 33/2 | 2025-06-21 | 2025-09-12 | 2025-09-22 | 83 | 93 | 2025-06 | 417 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 44/1 | 2025-06-24 | 2025-11-23 | 2025-12-02 | 152 | 161 | 2025-06 | 414 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 62/0 | 2025-06-25 | 2025-09-01 | 2025-09-12 | 68 | 79 | 2025-06 | 413 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 57/2 | 2025-06-27 | 2026-01-29 | 2026-02-04 | 216 | 222 | 2025-06 | 411 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 33/3 | 2025-06-30 | 2025-08-31 | 2025-09-10 | 62 | 72 | 2025-06 | 408 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 46/1 | 2025-06-30 |  | 2026-04-09 |  | 283 | 2025-06 | 408 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 39/0 | 2025-07-01 | 2025-10-16 | 2025-11-29 | 107 | 151 | 2025-07 | 407 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 33/4 | 2025-07-02 | 2025-11-12 | 2025-11-21 | 133 | 142 | 2025-07 | 406 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 57/1 | 2025-07-02 | 2025-12-26 | 2026-01-07 | 177 | 189 | 2025-07 | 406 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 46/3 | 2025-07-03 | 2025-08-22 | 2025-08-26 | 50 | 54 | 2025-07 | 405 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 46/10 | 2025-07-05 | 2025-10-29 | 2025-11-06 | 116 | 124 | 2025-07 | 403 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 52/1 | 2025-07-05 | 2025-12-10 | 2025-12-15 | 158 | 163 | 2025-07 | 403 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 48/0 | 2025-07-08 | 2025-11-11 | 2025-11-18 | 126 | 133 | 2025-07 | 400 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 46/6 | 2025-07-09 | 2025-11-04 | 2025-11-12 | 118 | 126 | 2025-07 | 399 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 60/1 | 2025-07-10 | 2025-12-16 | 2025-12-25 | 159 | 168 | 2025-07 | 398 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 47/0 | 2025-07-13 | 2025-12-01 | 2025-12-10 | 141 | 150 | 2025-07 | 395 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 53/0 | 2025-07-14 | 2025-09-16 | 2025-09-23 | 64 | 71 | 2025-07 | 394 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 43/3 | 2025-07-16 | 2026-02-20 | 2026-02-28 | 219 | 227 | 2025-07 | 392 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 58/0 | 2025-07-16 | 2025-12-26 | 2026-01-08 | 163 | 176 | 2025-07 | 392 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 57/3 | 2025-07-18 | 2026-01-08 | 2026-01-15 | 174 | 181 | 2025-07 | 390 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 44/0 | 2025-07-20 | 2025-09-25 | 2025-10-01 | 67 | 73 | 2025-07 | 388 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 46/11 | 2025-07-23 | 2025-12-04 | 2025-12-14 | 134 | 144 | 2025-07 | 385 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 56/1 | 2025-07-29 | 2025-12-07 | 2025-12-14 | 131 | 138 | 2025-07 | 379 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 56/2 | 2025-08-03 | 2025-12-15 | 2025-12-19 | 134 | 138 | 2025-08 | 374 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 56/3 | 2025-08-06 | 2025-12-20 | 2025-12-26 | 136 | 142 | 2025-08 | 371 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 54/0 | 2025-08-29 | 2025-09-29 | 2025-10-17 | 31 | 49 | 2025-08 | 348 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 42/0 - 43/0 | 2025-09-28 |  |  |  |  | 2025-09 | 318 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 41/0 - 42/0 | 2025-10-06 |  |  |  |  | 2025-10 | 310 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 36/0 - 36/1 | 2025-11-03 |  |  |  |  | 2025-11 | 282 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 55/6 | 2025-11-10 | 2026-01-08 | 2026-01-15 | 59 | 66 | 2025-11 | 275 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 55/5 | 2025-11-15 | 2026-01-20 | 2026-01-27 | 66 | 73 | 2025-11 | 270 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 35/0 - 36/0 | 2025-11-17 |  |  |  |  | 2025-11 | 268 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 51/0 | 2025-11-21 | 2026-02-05 | 2026-02-17 | 76 | 88 | 2025-11 | 264 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 50/0 | 2025-11-25 | 2026-02-04 | 2026-02-27 | 71 | 94 | 2025-11 | 260 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 48A/1 | 2025-11-27 | 2025-12-23 | 2025-12-30 | 26 | 33 | 2025-11 | 258 | TRUE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 34/0 - 35/0 | 2025-11-30 |  |  |  |  | 2025-11 | 255 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 49/0 | 2025-12-10 | 2026-01-28 | 2026-02-05 | 49 | 57 | 2025-12 | 245 | FALSE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 48A/2 | 2025-12-13 | 2025-12-31 | 2026-01-06 | 18 | 24 | 2025-12 | 242 | TRUE | TRUE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 59/1 | 2025-12-16 |  | 2026-02-05 |  | 51 | 2025-12 | 239 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 57/0 | 2025-12-20 | 2025-01-16 | 2026-01-30 | -338 | 41 | 2025-12 | 235 | FALSE | FALSE | Yes | Yes | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 60/3 | 2025-12-23 | 2026-01-16 | 2026-01-20 | 24 | 28 | 2025-12 | 232 | TRUE | TRUE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 40/0 - 41/0 | 2025-12-26 |  |  |  |  | 2025-12 | 229 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 63/0 | 2026-01-09 | 2026-02-05 | 2026-02-17 | 27 | 39 | 2026-01 | 215 | TRUE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 33/6 - 34/0 | 2026-01-27 |  |  |  |  | 2026-01 | 197 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 33/5 - 33/6 | 2026-01-30 |  |  |  |  | 2026-01 | 194 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 33/0 - 33/5 | 2026-02-09 |  |  |  |  | 2026-02 | 184 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 39/0-40/0 | 2026-02-10 |  |  |  |  | 2026-02 | 183 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 38/0 | 2026-02-17 | 2026-02-24 | 2026-04-01 | 7 | 43 | 2026-02 | 176 | TRUE | FALSE | Yes | No | fallback_single_line | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 32/0-33/0 | 2026-02-22 |  |  |  |  | 2026-02 | 171 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 45/1-46/0 | 2026-03-03 |  |  |  |  | 2026-03 | 162 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 43/0 - 44/0 | 2026-03-11 |  |  |  |  | 2026-03 | 154 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 45/0 - 45/1 | 2026-03-12 |  |  |  |  | 2026-03 | 153 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 44/0-45/0 | 2026-03-18 |  |  |  |  | 2026-03 | 147 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 56/0-56/3 | 2026-03-31 |  |  |  |  | 2026-03 | 134 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 61/0-62/0 | 2026-04-15 |  |  |  |  | 2026-04 | 119 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 63/0-GNTY | 2026-04-18 |  |  |  |  | 2026-04 | 116 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 55/0-56/0 | 2026-05-03 |  |  |  |  | 2026-05 | 101 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 37/0-38/0 | 2026-05-12 |  |  |  |  | 2026-05 | 92 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 36/01 - 37/00 | 2026-05-23 |  |  |  |  | 2026-05 | 81 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 38/0-39/0 | 2026-05-26 |  |  |  |  | 2026-05 | 78 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 52/00 - 53/00 | 2026-06-06 |  |  |  |  | 2026-06 | 67 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 51/00 - 52/00 | 2026-06-08 |  |  |  |  | 2026-06 | 65 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 56/03 - 57/00 | 2026-06-09 |  |  |  |  | 2026-06 | 64 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 54/00 - 55/00 | 2026-06-19 |  |  |  |  | 2026-06 | 54 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 53/00 - 54/00 | 2026-06-20 |  |  |  |  | 2026-06 | 53 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 57/00 - 58/00 | 2026-06-23 |  |  |  |  | 2026-06 | 50 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 48A/0-49/0 | 2026-06-26 |  |  |  |  | 2026-06 | 47 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 62/0-63/0 | 2026-06-26 |  |  |  |  | 2026-06 | 47 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 59/0 - 60/0 | 2026-06-27 |  |  |  |  | 2026-06 | 46 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 58/0 - 59/0 | 2026-06-28 |  |  |  |  | 2026-06 | 45 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 60/0-61/0 | 2026-07-04 |  |  |  |  | 2026-07 | 39 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 48/0-48A/0 | 2026-07-05 |  |  |  |  | 2026-07 | 38 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 47/0-48/0 | 2026-07-12 |  |  |  |  | 2026-07 | 31 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 49/0-50/0 | 2026-07-12 |  |  |  |  | 2026-07 | 31 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 50/0-51/0 | 2026-07-12 |  |  |  |  | 2026-07 | 31 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 46/0-46/7 | 2026-07-21 |  |  |  |  | 2026-07 | 22 | FALSE | FALSE | No | No |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 419 | 19/5 | 2024-05-24 | 2025-02-03 | 2025-02-12 | 255 | 264 | 2024-05 | 810 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 19/4 | 2024-05-28 | 2025-01-11 | 2025-01-17 | 228 | 234 | 2024-05 | 806 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 19/3 | 2024-05-29 | 2025-01-18 | 2025-01-22 | 234 | 238 | 2024-05 | 805 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 19/1 | 2024-06-01 | 2025-01-23 | 2025-01-27 | 236 | 240 | 2024-06 | 802 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 17/2 | 2024-06-04 | 2025-01-31 | 2025-02-09 | 241 | 250 | 2024-06 | 799 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 17/1 | 2024-06-07 | 2025-02-08 | 2025-02-14 | 246 | 252 | 2024-06 | 796 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 19/2 | 2024-06-09 | 2024-11-19 | 2024-12-10 | 163 | 184 | 2024-06 | 794 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 20/1 | 2024-06-21 | 2024-11-21 | 2024-11-27 | 153 | 159 | 2024-06 | 782 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 20/2 | 2024-06-23 | 2024-11-28 | 2024-12-03 | 158 | 163 | 2024-06 | 780 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 11/4 | 2024-06-26 | 2025-04-03 | 2025-04-14 | 281 | 292 | 2024-06 | 777 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 22/2 | 2024-06-29 | 2024-12-04 | 2024-12-08 | 158 | 162 | 2024-06 | 774 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 11/3 | 2024-06-30 | 2025-04-11 | 2025-04-19 | 285 | 293 | 2024-06 | 773 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 12/1 | 2024-07-07 | 2025-03-26 | 2025-04-05 | 262 | 272 | 2024-07 | 766 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 23/1 | 2024-07-09 | 2024-12-14 | 2024-12-17 | 158 | 161 | 2024-07 | 764 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 22/3 | 2024-07-10 | 2024-12-09 | 2024-12-13 | 152 | 156 | 2024-07 | 763 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 6/10 | 2024-07-10 | 2024-12-17 | 2024-12-23 | 160 | 166 | 2024-07 | 763 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 23/2 | 2024-07-14 | 2024-12-18 | 2024-12-23 | 157 | 162 | 2024-07 | 759 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 6/9 | 2024-07-14 | 2024-01-06 | 2025-01-13 | -190 | 183 | 2024-07 | 759 | FALSE | FALSE | Yes | Yes | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 6/8 | 2024-07-16 | 2024-11-21 | 2024-11-28 | 128 | 135 | 2024-07 | 757 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 6/12 | 2024-07-18 | 2024-12-22 | 2024-12-31 | 157 | 166 | 2024-07 | 755 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 23/3 | 2024-07-19 | 2025-03-06 | 2025-03-12 | 230 | 236 | 2024-07 | 754 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 3/2 | 2024-07-21 | 2025-07-29 | 2025-09-07 | 373 | 413 | 2024-07 | 752 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 26/4 | 2024-07-22 | 2025-04-17 | 2025-04-23 | 269 | 275 | 2024-07 | 751 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 26/3 | 2024-07-25 | 2025-04-12 | 2025-04-18 | 261 | 267 | 2024-07 | 748 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 6/3 | 2024-07-25 | 2024-12-06 | 2024-12-11 | 134 | 139 | 2024-07 | 748 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 3/3 | 2024-07-26 | 2025-10-06 | 2025-10-12 | 437 | 443 | 2024-07 | 747 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 6/6 | 2024-07-29 | 2025-02-18 | 2025-02-24 | 204 | 210 | 2024-07 | 744 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 24/1 | 2024-07-30 | 2025-01-03 | 2025-01-09 | 157 | 163 | 2024-07 | 743 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 3/5 | 2024-07-30 | 2025-05-05 | 2025-05-11 | 279 | 285 | 2024-07 | 743 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 3/4 | 2024-08-04 | 2025-09-28 | 2025-10-05 | 420 | 427 | 2024-08 | 738 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 6/2 | 2024-08-04 | 2024-12-12 | 2024-12-17 | 130 | 135 | 2024-08 | 738 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 26/2 | 2024-08-07 | 2025-07-28 | 2025-08-03 | 355 | 361 | 2024-08 | 735 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 6/5 | 2024-08-10 | 2025-01-17 | 2025-01-21 | 160 | 164 | 2024-08 | 732 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4/1 | 2024-08-11 | 2025-04-28 | 2025-05-04 | 260 | 266 | 2024-08 | 731 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 6/11 | 2024-08-14 | 2024-11-28 | 2024-12-05 | 106 | 113 | 2024-08 | 728 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 5/1 | 2024-08-17 | 2025-04-07 | 2025-04-17 | 233 | 243 | 2024-08 | 725 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 5/3 | 2024-08-28 | 2025-02-23 | 2025-02-28 | 179 | 184 | 2024-08 | 714 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 27/2 | 2024-09-01 | 2025-06-12 | 2025-06-20 | 284 | 292 | 2024-09 | 710 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 0D/3 | 2024-09-03 | 2025-01-28 | 2025-02-08 | 147 | 158 | 2024-09 | 708 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 5/2 | 2024-09-04 | 2025-03-24 | 2025-04-11 | 201 | 219 | 2024-09 | 707 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 0D/2 | 2024-09-10 | 2025-01-12 | 2025-01-19 | 124 | 131 | 2024-09 | 701 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 12/0 | 2024-09-16 | 2025-04-19 | 2025-04-29 | 215 | 225 | 2024-09 | 695 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4/0 | 2024-09-16 | 2025-09-15 | 2025-09-27 | 364 | 376 | 2024-09 | 695 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 0E/2 | 2024-09-18 | 2025-01-04 | 2025-01-10 | 108 | 114 | 2024-09 | 693 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 7/0 | 2024-09-21 | 2025-12-24 | 2026-01-31 | 459 | 497 | 2024-09 | 690 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 6/1 | 2024-09-23 | 2025-01-11 | 2025-01-16 | 110 | 115 | 2024-09 | 688 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 0E/1 | 2024-09-24 | 2025-01-11 | 2025-01-18 | 109 | 116 | 2024-09 | 687 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 27/1 | 2024-09-26 | 2025-06-05 | 2025-06-13 | 252 | 260 | 2024-09 | 685 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 24/2 | 2024-09-27 | 2025-04-23 | 2025-04-28 | 208 | 213 | 2024-09 | 684 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 0B/2 | 2024-09-28 | 2024-12-04 | 2024-12-23 | 67 | 86 | 2024-09 | 683 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 0D/1 | 2024-09-30 | 2024-12-22 | 2024-12-31 | 83 | 92 | 2024-09 | 681 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 0D/5 | 2024-09-30 | 2025-02-07 | 2025-02-27 | 130 | 150 | 2024-09 | 681 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 12A/0 | 2024-09-30 | 2025-04-28 | 2025-05-07 | 210 | 219 | 2024-09 | 681 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 5/0 | 2024-10-04 | 2025-04-14 | 2025-04-27 | 192 | 205 | 2024-10 | 677 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 0B/3 | 2024-10-07 | 2025-01-19 | 2025-01-27 | 104 | 112 | 2024-10 | 674 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 23/0 | 2024-10-07 | 2024-12-22 | 2024-12-31 | 76 | 85 | 2024-10 | 674 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 0D/4 | 2024-10-11 | 2025-02-08 | 2025-02-15 | 120 | 127 | 2024-10 | 670 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 5/4 | 2024-10-11 | 2025-02-09 | 2025-02-18 | 121 | 130 | 2024-10 | 670 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 28/0 | 2024-10-12 | 2025-06-27 | 2025-07-08 | 258 | 269 | 2024-10 | 669 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 0D/0 | 2024-10-14 | 2025-02-13 | 2025-02-25 | 122 | 134 | 2024-10 | 667 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 27/3 | 2024-10-14 | 2025-06-21 | 2025-06-26 | 250 | 255 | 2024-10 | 667 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 6/4 | 2024-10-15 | 2025-01-20 | 2025-01-27 | 97 | 104 | 2024-10 | 666 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 26/5 | 2024-10-16 | 2025-03-31 | 2025-04-08 | 166 | 174 | 2024-10 | 665 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 26/6 | 2024-10-19 | 2025-04-08 | 2025-04-13 | 171 | 176 | 2024-10 | 662 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 0B/1 | 2024-10-22 | 2025-02-19 | 2025-03-04 | 120 | 133 | 2024-10 | 659 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 0C/0 | 2024-10-25 | 2025-11-15 | 2025-12-08 | 386 | 409 | 2024-10 | 656 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 0C/1 | 2024-10-25 | 2025-01-20 | 2025-01-28 | 87 | 95 | 2024-10 | 656 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 27/0 | 2024-10-25 | 2025-05-19 | 2025-06-03 | 206 | 221 | 2024-10 | 656 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 24/0 | 2024-10-27 | 2025-03-08 | 2025-03-24 | 132 | 148 | 2024-10 | 654 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 6/0 | 2024-10-27 | 2025-02-02 | 2025-02-11 | 98 | 107 | 2024-10 | 654 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 0E/0 | 2024-10-28 | 2025-12-03 | 2025-12-24 | 401 | 422 | 2024-10 | 653 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 0B/0 | 2024-11-08 | 2025-09-23 | 2025-11-05 | 319 | 362 | 2024-11 | 642 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 20/0 | 2024-11-08 | 2025-02-07 | 2025-02-20 | 91 | 104 | 2024-11 | 642 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 18/0 | 2024-11-09 | 2025-02-14 | 2025-02-25 | 97 | 108 | 2024-11 | 641 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 19/0 | 2024-11-13 | 2025-01-27 | 2025-02-05 | 75 | 84 | 2024-11 | 637 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 24/3 | 2024-11-20 | 2025-03-27 | 2025-04-05 | 127 | 136 | 2024-11 | 630 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 11/2 | 2024-11-22 | 2025-08-31 | 2025-09-07 | 282 | 289 | 2024-11 | 628 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 12/2 | 2024-11-22 | 2025-09-07 | 2025-09-13 | 289 | 295 | 2024-11 | 628 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 26/1 | 2024-11-22 | 2025-03-22 | 2025-03-28 | 120 | 126 | 2024-11 | 628 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 17/0 | 2024-11-27 | 2025-02-22 | 2025-03-07 | 87 | 100 | 2024-11 | 623 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 6/7 | 2024-11-28 | 2025-01-27 | 2025-02-01 | 60 | 65 | 2024-11 | 622 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 3/1 | 2024-11-29 | 2025-08-12 | 2025-08-19 | 256 | 263 | 2024-11 | 621 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 36/6 | 2024-11-29 | 2025-10-23 | 2025-10-30 | 328 | 335 | 2024-11 | 621 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 7/1 | 2024-11-29 | 2025-03-01 | 2025-03-08 | 92 | 99 | 2024-11 | 621 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 0F/0 | 2024-11-30 | 2025-02-25 | 2025-03-31 | 87 | 121 | 2024-11 | 620 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 36/7 | 2024-12-02 | 2025-10-16 | 2025-10-23 | 318 | 325 | 2024-12 | 618 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 11/1 | 2024-12-09 | 2025-08-04 | 2025-08-13 | 238 | 247 | 2024-12 | 611 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 15A/0 | 2024-12-10 | 2025-03-02 | 2025-03-26 | 82 | 106 | 2024-12 | 610 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 22/1 | 2024-12-10 | 2025-02-19 | 2025-02-28 | 71 | 80 | 2024-12 | 610 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 0G/0 | 2024-12-11 | 2025-08-15 | 2025-08-31 | 247 | 263 | 2024-12 | 609 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 16/0 | 2024-12-14 | 2025-10-12 | 2025-10-26 | 302 | 316 | 2024-12 | 606 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 28/1 | 2024-12-17 | 2025-04-12 | 2025-04-21 | 116 | 125 | 2024-12 | 603 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 30/1 | 2024-12-21 | 2025-03-31 | 2025-04-13 | 100 | 113 | 2024-12 | 599 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 15/0 | 2024-12-23 | 2026-05-20 | 2026-06-08 | 513 | 532 | 2024-12 | 597 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 31/0 | 2024-12-23 | 2025-04-28 | 2025-05-10 | 126 | 138 | 2024-12 | 597 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 0A/0 (CT) | 2024-12-24 | 2025-01-27 | 2025-02-12 | 34 | 50 | 2024-12 | 596 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 31/1 | 2024-12-24 | 2025-04-22 | 2025-04-29 | 119 | 126 | 2024-12 | 596 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 1/0 | 2025-01-04 | 2025-08-01 | 2025-09-22 | 209 | 261 | 2025-01 | 585 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 0H/0 | 2025-01-09 | 2025-08-01 | 2025-09-15 | 204 | 249 | 2025-01 | 580 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 0G/1 | 2025-01-15 | 2025-08-20 | 2025-08-27 | 217 | 224 | 2025-01 | 574 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 10/0 | 2025-01-18 | 2025-08-14 | 2025-08-30 | 208 | 224 | 2025-01 | 571 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 22/0 | 2025-01-25 | 2025-04-29 | 2025-05-19 | 94 | 114 | 2025-01 | 564 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 36/1 | 2025-01-28 | 2025-07-26 | 2025-08-01 | 179 | 185 | 2025-01 | 561 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 36/2 | 2025-01-29 | 2025-08-02 | 2025-08-07 | 185 | 190 | 2025-01 | 560 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 36/4 | 2025-02-07 | 2026-06-08 | 2026-06-30 | 486 | 508 | 2025-02 | 551 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 36/8 | 2025-02-07 | 2025-11-01 | 2025-11-08 | 267 | 274 | 2025-02 | 551 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 38/7 | 2025-02-11 | 2025-11-12 | 2025-11-25 | 274 | 287 | 2025-02 | 547 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 62/2 | 2025-02-13 | 2025-12-04 | 2025-12-17 | 294 | 307 | 2025-02 | 545 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 38/10 | 2025-02-15 | 2025-12-04 | 2025-12-19 | 292 | 307 | 2025-02 | 543 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 38/5 | 2025-02-20 | 2025-12-04 | 2025-12-10 | 287 | 293 | 2025-02 | 538 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 62/1 | 2025-02-22 | 2025-11-15 | 2025-12-03 | 266 | 284 | 2025-02 | 536 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 38/6 | 2025-02-28 | 2025-12-01 | 2025-12-10 | 276 | 285 | 2025-02 | 530 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 38/8 | 2025-02-28 | 2025-12-11 | 2026-01-05 | 286 | 311 | 2025-02 | 530 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 62/5 | 2025-02-28 | 2025-12-10 | 2025-12-24 | 285 | 299 | 2025-02 | 530 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 62/4 | 2025-03-05 | 2025-11-29 | 2025-12-10 | 269 | 280 | 2025-03 | 525 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 38/0 | 2025-03-15 | 2025-11-12 | 2025-12-18 | 242 | 278 | 2025-03 | 515 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 38/11 | 2025-03-26 | 2025-12-10 | 2025-12-16 | 259 | 265 | 2025-03 | 504 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 38/9 | 2025-03-27 | 2025-12-17 | 2025-12-21 | 265 | 269 | 2025-03 | 503 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 34/0 | 2025-03-29 | 2025-07-01 | 2025-07-17 | 94 | 110 | 2025-03 | 501 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 40/0 | 2025-04-05 | 2025-12-18 | 2026-01-17 | 257 | 287 | 2025-04 | 494 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 20/3 | 2025-04-08 | 2025-07-19 | 2025-07-26 | 102 | 109 | 2025-04 | 491 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 40/6 | 2025-04-08 | 2025-11-17 | 2025-11-23 | 223 | 229 | 2025-04 | 491 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 62/3 | 2025-04-08 | 2025-12-28 | 2026-01-14 | 264 | 281 | 2025-04 | 491 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 40/3 | 2025-04-11 | 2025-11-29 | 2025-12-05 | 232 | 238 | 2025-04 | 488 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 40/7 | 2025-04-14 | 2025-12-10 | 2025-12-18 | 240 | 248 | 2025-04 | 485 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 40/5 | 2025-04-17 | 2025-11-08 | 2025-11-16 | 205 | 213 | 2025-04 | 482 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 40/4 | 2025-04-21 | 2025-11-24 | 2025-11-29 | 217 | 222 | 2025-04 | 478 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 40/2 | 2025-04-22 | 2025-12-05 | 2025-12-10 | 227 | 232 | 2025-04 | 477 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 46/4 | 2025-04-22 | 2025-12-04 | 2025-12-10 | 226 | 232 | 2025-04 | 477 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 40/9 | 2025-04-23 | 2025-12-17 | 2025-12-20 | 238 | 241 | 2025-04 | 476 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 41/1 | 2025-04-24 | 2025-12-10 | 2025-12-16 | 230 | 236 | 2025-04 | 475 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 41/7 | 2025-04-28 | 2025-11-29 | 2025-12-04 | 215 | 220 | 2025-04 | 471 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 41/5 | 2025-04-29 | 2025-11-08 | 2025-11-14 | 193 | 199 | 2025-04 | 470 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 41/8 | 2025-05-04 | 2025-12-05 | 2025-12-10 | 215 | 220 | 2025-05 | 465 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 41/0 | 2025-05-07 | 2026-06-21 | 2026-07-20 | 410 | 439 | 2025-05 | 462 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 41/3 | 2025-05-11 | 2025-11-24 | 2025-11-29 | 197 | 202 | 2025-05 | 458 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 41/4 | 2025-05-12 | 2025-11-15 | 2025-11-23 | 187 | 195 | 2025-05 | 457 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 84/1 | 2025-05-15 | 2025-12-16 | 2026-01-14 | 215 | 244 | 2025-05 | 454 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 25/0 | 2025-05-19 | 2026-04-14 | 2026-04-29 | 330 | 345 | 2025-05 | 450 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 83/6 | 2025-05-19 | 2026-01-05 |  | 231 |  | 2025-05 | 450 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 26/0 | 2025-05-21 | 2025-10-06 | 2025-10-18 | 138 | 150 | 2025-05 | 448 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 83/7 | 2025-06-05 | 2025-11-19 | 2025-12-20 | 167 | 198 | 2025-06 | 433 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 35/0 | 2025-06-06 | 2025-10-27 | 2025-11-13 | 143 | 160 | 2025-06 | 432 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 3/0 | 2025-06-07 | 2026-03-21 | 2026-03-30 | 287 | 296 | 2025-06 | 431 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 36/0 | 2025-06-07 | 2025-11-12 | 2025-11-30 | 158 | 176 | 2025-06 | 431 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 34/1 | 2025-06-08 | 2025-07-18 | 2025-07-24 | 40 | 46 | 2025-06 | 430 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 29/0 | 2025-06-15 | 2025-07-09 | 2025-07-18 | 24 | 33 | 2025-06 | 423 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 83/5 | 2025-06-19 | 2025-12-21 | 2026-01-07 | 185 | 202 | 2025-06 | 419 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 11/0 | 2025-06-23 | 2025-11-05 | 2025-12-20 | 135 | 180 | 2025-06 | 415 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 78/3 | 2025-06-26 | 2026-07-15 | 2026-08-09 | 384 | 409 | 2025-06 | 412 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 30/0 | 2025-06-27 | 2025-10-26 | 2025-11-12 | 121 | 138 | 2025-06 | 411 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 84/4 | 2025-07-04 | 2025-12-13 | 2025-12-26 | 162 | 175 | 2025-07 | 404 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 21/0 | 2025-07-08 | 2025-09-14 | 2025-10-05 | 68 | 89 | 2025-07 | 400 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 2/0 | 2025-07-14 | 2026-02-13 | 2026-03-15 | 214 | 244 | 2025-07 | 394 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 9/0 | 2025-07-23 | 2025-12-13 | 2025-12-31 | 143 | 161 | 2025-07 | 385 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 8/0 | 2025-07-28 | 2026-08-06 |  | 374 |  | 2025-07 | 380 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 41/6 | 2025-08-03 | 2025-12-17 | 2025-12-28 | 136 | 147 | 2025-08 | 374 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 46/0 | 2025-08-31 |  |  |  |  | 2025-08 | 346 | FALSE | FALSE | No | No |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 46/1 | 2025-09-12 | 2025-11-24 | 2025-11-30 | 73 | 79 | 2025-09 | 334 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 46/2 | 2025-09-16 | 2025-11-12 | 2025-11-25 | 57 | 70 | 2025-09 | 330 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 46/3 | 2025-09-19 | 2025-11-12 | 2025-12-02 | 54 | 74 | 2025-09 | 327 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 31/2 | 2025-10-03 | 2025-10-14 | 2025-10-27 | 11 | 24 | 2025-10 | 313 | TRUE | TRUE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 78/1 | 2025-10-03 | 2026-04-07 | 2026-04-22 | 186 | 201 | 2025-10 | 313 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 45/0 | 2025-10-09 | 2025-12-12 | 2025-12-30 | 64 | 82 | 2025-10 | 307 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 78/0 | 2025-10-23 | 2026-01-08 | 2026-01-28 | 77 | 97 | 2025-10 | 293 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 76/3 | 2025-10-24 | 2025-11-19 | 2026-01-05 | 26 | 73 | 2025-10 | 292 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 83/1 | 2025-10-30 | 2025-11-21 | 2025-12-08 | 22 | 39 | 2025-10 | 286 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 43/5 | 2025-11-04 | 2025-11-19 | 2025-12-08 | 15 | 34 | 2025-11 | 281 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 43/3 | 2025-11-09 | 2026-07-08 | 2026-07-28 | 241 | 261 | 2025-11 | 276 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 43/6 | 2025-11-09 | 2025-12-03 | 2025-12-11 | 24 | 32 | 2025-11 | 276 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 63/5 | 2025-11-09 | 2026-05-20 | 2026-07-30 | 192 | 263 | 2025-11 | 276 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 43/0 | 2025-11-10 | 2025-12-03 | 2025-12-26 | 23 | 46 | 2025-11 | 275 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 54/5 | 2025-11-11 | 2026-04-19 | 2026-04-28 | 159 | 168 | 2025-11 | 274 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 36/10 | 2025-11-13 | 2025-12-19 | 2025-12-30 | 36 | 47 | 2025-11 | 272 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 43/1 | 2025-11-13 |  |  |  |  | 2025-11 | 272 | FALSE | FALSE | No | No |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 43/2 | 2025-11-18 | 2026-07-02 | 2026-07-14 | 226 | 238 | 2025-11 | 267 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 83/0 | 2025-11-20 | 2025-12-09 | 2025-12-30 | 19 | 40 | 2025-11 | 265 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 36/9 | 2025-11-23 |  |  |  |  | 2025-11 | 262 | FALSE | FALSE | No | No |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 84/3 | 2025-11-24 | 2025-12-26 | 2026-01-04 | 32 | 41 | 2025-11 | 261 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 43/4 | 2025-11-25 | 2025-12-09 | 2025-12-17 | 14 | 22 | 2025-11 | 260 | TRUE | TRUE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 54/6 | 2025-11-25 | 2025-12-08 | 2026-01-02 | 13 | 38 | 2025-11 | 260 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 12A/1 | 2025-11-28 | 2025-12-12 | 2025-12-21 | 14 | 23 | 2025-11 | 257 | TRUE | TRUE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 83/8 | 2025-11-28 | 2026-01-15 |  | 48 |  | 2025-11 | 257 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 63/4 | 2025-11-29 | 2025-12-17 | 2025-12-28 | 18 | 29 | 2025-11 | 256 | TRUE | TRUE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 54/2 | 2025-11-30 | 2026-04-13 | 2026-04-18 | 134 | 139 | 2025-11 | 255 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 55/6 | 2025-12-04 | 2026-01-14 | 2026-02-06 | 41 | 64 | 2025-12 | 251 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 33/1 | 2025-12-07 | 2025-12-28 | 2026-01-08 | 21 | 32 | 2025-12 | 248 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 54/4 | 2025-12-07 | 2026-01-19 | 2026-01-31 | 43 | 55 | 2025-12 | 248 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 63A/0 | 2025-12-07 | 2025-12-30 | 2026-01-13 | 23 | 37 | 2025-12 | 248 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 63/2 | 2025-12-09 | 2025-12-29 | 2026-01-09 | 20 | 31 | 2025-12 | 246 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 55/5 | 2025-12-12 | 2026-01-03 | 2026-01-13 | 22 | 32 | 2025-12 | 243 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 54/3 | 2025-12-13 | 2025-12-22 | 2025-12-29 | 9 | 16 | 2025-12 | 242 | TRUE | TRUE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 84/5 | 2025-12-15 | 2026-01-08 | 2026-01-18 | 24 | 34 | 2025-12 | 240 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 54/7 | 2025-12-18 | 2026-04-01 | 2026-04-20 | 104 | 123 | 2025-12 | 237 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 64/1 | 2025-12-18 | 2026-04-21 | 2026-05-06 | 124 | 139 | 2025-12 | 237 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 78/4 | 2025-12-18 | 2025-12-26 | 2026-01-07 | 8 | 20 | 2025-12 | 237 | TRUE | TRUE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 57/1 | 2025-12-20 | 2026-01-09 | 2026-02-11 | 20 | 53 | 2025-12 | 235 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 59/1 | 2025-12-26 | 2026-01-09 | 2026-01-20 | 14 | 25 | 2025-12 | 229 | TRUE | TRUE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 84/0 | 2025-12-26 | 2026-01-09 |  | 14 |  | 2025-12 | 229 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 55/1 | 2025-12-27 | 2026-01-03 | 2026-01-18 | 7 | 22 | 2025-12 | 228 | TRUE | TRUE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 63/6 | 2025-12-28 | 2026-01-20 |  | 23 |  | 2025-12 | 227 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 36/5 | 2025-12-31 | 2026-01-10 | 2026-01-21 | 10 | 21 | 2025-12 | 224 | TRUE | TRUE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 63/0 | 2025-12-31 | 2026-01-09 | 2026-01-24 | 9 | 24 | 2025-12 | 224 | TRUE | TRUE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 63/1 | 2026-01-02 | 2026-01-22 | 2026-01-31 | 20 | 29 | 2026-01 | 222 | TRUE | TRUE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 63B/6 | 2026-01-02 |  |  |  |  | 2026-01 | 222 | FALSE | FALSE | No | No |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 62/0 | 2026-01-04 | 2026-01-15 | 2026-06-19 | 11 | 166 | 2026-01 | 220 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 64/5 | 2026-01-04 | 2026-04-30 | 2026-05-10 | 116 | 126 | 2026-01 | 220 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 84A/0 | 2026-01-07 | 2026-01-19 | 2026-01-31 | 12 | 24 | 2026-01 | 217 | TRUE | TRUE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 36/3 | 2026-01-09 | 2026-08-01 |  | 204 |  | 2026-01 | 215 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 55/4 | 2026-01-10 | 2026-01-14 | 2026-01-25 | 4 | 15 | 2026-01 | 214 | TRUE | TRUE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 55/0 | 2026-01-14 | 2026-01-20 | 2026-04-18 | 6 | 94 | 2026-01 | 210 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 63/3 | 2026-01-17 | 2026-07-30 |  | 194 |  | 2026-01 | 207 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 55/3 | 2026-01-18 | 2026-04-10 | 2026-04-20 | 82 | 92 | 2026-01 | 206 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 64A/0 | 2026-01-18 | 2026-05-25 | 2026-06-10 | 127 | 143 | 2026-01 | 206 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 38/1 | 2026-01-24 | 2026-07-16 | 2026-07-25 | 173 | 182 | 2026-01 | 200 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 64/0 | 2026-02-01 | 2026-07-29 |  | 178 |  | 2026-02 | 192 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 55/2 | 2026-02-07 | 2026-04-13 | 2026-04-25 | 65 | 77 | 2026-02 | 186 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 63B/1 | 2026-02-07 | 2026-04-26 | 2026-05-10 | 78 | 92 | 2026-02 | 186 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 64/2 | 2026-02-07 | 2026-05-11 | 2026-05-23 | 93 | 105 | 2026-02 | 186 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 78A/0 | 2026-02-13 | 2026-07-05 | 2026-08-03 | 142 | 171 | 2026-02 | 180 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 77/0 | 2026-02-19 |  |  |  |  | 2026-02 | 174 | FALSE | FALSE | No | No |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 42/0 | 2026-02-22 | 2026-05-10 | 2026-06-16 | 77 | 114 | 2026-02 | 171 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 63B/0 | 2026-03-03 | 2026-04-26 | 2026-05-10 | 54 | 68 | 2026-03 | 162 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 54/1 | 2026-03-16 | 2026-04-03 | 2026-04-12 | 18 | 27 | 2026-03 | 149 | TRUE | TRUE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 33/0 | 2026-03-18 | 2026-04-21 | 2026-05-09 | 34 | 52 | 2026-03 | 147 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 78/2 | 2026-03-25 | 2026-04-13 | 2026-04-29 | 19 | 35 | 2026-03 | 140 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 40/8 | 2026-03-27 | 2026-05-10 | 2026-05-19 | 44 | 53 | 2026-03 | 138 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 81/0 | 2026-03-29 | 2026-05-03 |  | 35 |  | 2026-03 | 136 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 13/0 | 2026-04-15 | 2026-05-10 | 2026-05-30 | 25 | 45 | 2026-04 | 119 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 32/0 | 2026-04-20 | 2026-05-25 | 2026-06-07 | 35 | 48 | 2026-04 | 114 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 14/0 | 2026-04-23 | 2026-04-30 | 2026-05-12 | 7 | 19 | 2026-04 | 111 | TRUE | TRUE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 80/0 | 2026-04-25 | 2026-08-12 |  | 109 |  | 2026-04 | 109 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 76/2 | 2026-04-28 | 2026-07-29 |  | 92 |  | 2026-04 | 106 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 14/1 | 2026-04-29 | 2026-05-13 | 2026-05-27 | 14 | 28 | 2026-04 | 105 | TRUE | TRUE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 40/1 | 2026-04-29 | 2026-05-08 | 2026-05-14 | 9 | 15 | 2026-04 | 105 | TRUE | TRUE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 60/0 | 2026-04-30 |  |  |  |  | 2026-04 | 104 | FALSE | FALSE | No | No |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 64/3 | 2026-05-04 | 2026-05-10 | 2026-06-01 | 6 | 28 | 2026-05 | 100 | TRUE | TRUE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 66/1 | 2026-05-04 | 2026-06-27 | 2026-07-15 | 54 | 72 | 2026-05 | 100 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 41/2 | 2026-05-05 | 2026-06-01 | 2026-06-19 | 27 | 45 | 2026-05 | 99 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 64/4 | 2026-05-08 | 2026-05-31 | 2026-07-03 | 23 | 56 | 2026-05 | 96 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 53/0 | 2026-05-09 | 2026-05-27 | 2026-06-10 | 18 | 32 | 2026-05 | 95 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 84/2 | 2026-05-10 | 2026-07-20 |  | 71 |  | 2026-05 | 94 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 38/3 | 2026-05-11 | 2026-06-01 | 2026-06-13 | 21 | 33 | 2026-05 | 93 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 71/0 | 2026-05-11 | 2026-06-06 | 2026-07-01 | 26 | 51 | 2026-05 | 93 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 65/0 | 2026-05-17 | 2026-06-10 | 2026-06-29 | 24 | 43 | 2026-05 | 87 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 52/0 | 2026-05-18 | 2026-06-22 | 2026-06-30 | 35 | 43 | 2026-05 | 86 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 67/0 | 2026-05-20 | 2026-07-01 | 2026-07-13 | 42 | 54 | 2026-05 | 84 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 69/0 | 2026-05-20 | 2026-07-27 |  | 68 |  | 2026-05 | 84 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 54/0 | 2026-05-25 | 2026-06-10 |  | 16 |  | 2026-05 | 79 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 37/0 | 2026-05-26 | 2026-06-10 | 2026-07-15 | 15 | 50 | 2026-05 | 78 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 68/0 | 2026-05-28 | 2026-07-13 |  | 46 |  | 2026-05 | 76 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 95A/0 | 2026-05-28 |  |  |  |  | 2026-05 | 76 | FALSE | FALSE | No | No |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 52/1 | 2026-05-31 | 2026-04-03 | 2026-07-01 | -58 | 31 | 2026-05 | 73 | FALSE | FALSE | Yes | Yes | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 65/2 | 2026-05-31 | 2026-06-12 | 2026-06-29 | 12 | 29 | 2026-05 | 73 | TRUE | TRUE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 70/0 | 2026-06-01 | 2026-07-02 | 2026-07-27 | 31 | 56 | 2026-06 | 72 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 75/0 | 2026-06-01 | 2026-06-25 |  | 24 |  | 2026-06 | 72 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 72/0 | 2026-06-05 |  |  |  |  | 2026-06 | 68 | FALSE | FALSE | No | No |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 38/2 | 2026-06-06 | 2026-06-14 | 2026-06-24 | 8 | 18 | 2026-06 | 67 | TRUE | TRUE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 65/1 | 2026-06-06 | 2026-07-13 | 2026-07-22 | 37 | 46 | 2026-06 | 67 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 76/0 | 2026-06-06 | 2026-06-10 | 2026-07-14 | 4 | 38 | 2026-06 | 67 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 73/0 | 2026-06-08 | 2026-06-17 | 2026-07-01 | 9 | 23 | 2026-06 | 65 | TRUE | TRUE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 52/2 | 2026-06-09 | 2026-06-14 | 2026-06-22 | 5 | 13 | 2026-06 | 64 | TRUE | TRUE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 76/1 | 2026-06-11 | 2026-07-13 | 2026-07-27 | 32 | 46 | 2026-06 | 62 | FALSE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 48/1 | 2026-06-13 | 2026-07-01 | 2026-07-08 | 18 | 25 | 2026-06 | 60 | TRUE | TRUE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 44/0 | 2026-06-18 | 2026-06-26 | 2026-07-07 | 8 | 19 | 2026-06 | 55 | TRUE | TRUE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 59/0 | 2026-06-23 |  |  |  |  | 2026-06 | 50 | FALSE | FALSE | No | No |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 63B/3 | 2026-06-23 |  |  |  |  | 2026-06 | 50 | FALSE | FALSE | No | No |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 74/0 | 2026-06-23 | 2026-07-13 | 2026-07-28 | 20 | 35 | 2026-06 | 50 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 48/0 | 2026-06-24 | 2026-07-09 | 2026-07-19 | 15 | 25 | 2026-06 | 49 | TRUE | TRUE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 39/0 | 2026-06-29 |  |  |  |  | 2026-06 | 44 | FALSE | FALSE | No | No |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 50/1 | 2026-07-02 | 2026-07-17 | 2026-07-27 | 15 | 25 | 2026-07 | 41 | TRUE | TRUE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 66/0 | 2026-07-04 | 2026-07-20 |  | 16 |  | 2026-07 | 39 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 96/2 | 2026-07-04 |  |  |  |  | 2026-07 | 39 | FALSE | FALSE | No | No |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 50/0 | 2026-07-14 | 2026-07-16 |  | 2 |  | 2026-07 | 29 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 96/0 | 2026-07-14 | 2026-08-12 |  | 29 |  | 2026-07 | 29 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 79/0 | 2026-07-18 |  |  |  |  | 2026-07 | 25 | FALSE | FALSE | No | No |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 98/0 | 2026-07-18 |  |  |  |  | 2026-07 | 25 | FALSE | FALSE | No | No |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 57/0 | 2026-07-19 | 2026-08-12 |  | 24 |  | 2026-07 | 24 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 38/4 | 2026-07-20 | 2026-07-26 | 2026-08-02 | 6 | 13 | 2026-07 | 23 | TRUE | TRUE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 47/0 | 2026-07-22 | 2026-07-27 |  | 5 |  | 2026-07 | 21 | TRUE | FALSE | Yes | No | exact | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 86/1 | 2026-07-23 |  |  |  |  | 2026-07 | 20 | FALSE | FALSE | No | No |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 93C/0 | 2026-07-25 |  |  |  |  | 2026-07 | 18 | FALSE | FALSE | No | No |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 51/0 | 2026-07-30 |  |  |  |  | 2026-07 | 13 | FALSE | FALSE | No | No |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 82/0 | 2026-07-31 |  |  |  |  | 2026-07 | 12 | FALSE | FALSE | No | No |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 99/0 | 2026-08-04 |  |  |  |  | 2026-08 | 8 | FALSE | FALSE | No | No |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 421 | 24/4 | 2024-05-22 | 2024-08-29 | 2024-09-06 | 99 | 107 | 2024-05 | 812 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 24/2 | 2024-06-02 | 2024-12-03 | 2024-12-11 | 184 | 192 | 2024-06 | 801 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 24/3 | 2024-06-07 | 2024-08-29 | 2024-09-12 | 83 | 97 | 2024-06 | 796 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 24/5 | 2024-06-11 | 2024-08-22 | 2024-08-29 | 72 | 79 | 2024-06 | 792 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 24/6 | 2024-06-15 | 2024-11-13 | 2024-11-18 | 151 | 156 | 2024-06 | 788 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 24/7 | 2024-06-19 | 2024-10-27 | 2024-11-01 | 130 | 135 | 2024-06 | 784 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 23/4 | 2024-06-20 | 2024-10-05 | 2024-10-14 | 107 | 116 | 2024-06 | 783 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 25/4 | 2024-06-22 | 2024-07-10 | 2024-07-19 | 18 | 27 | 2024-06 | 781 | TRUE | TRUE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 25/5 | 2024-06-25 | 2025-02-19 | 2025-02-25 | 239 | 245 | 2024-06 | 778 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 23/3 | 2024-06-27 | 2024-10-16 | 2024-11-01 | 111 | 127 | 2024-06 | 776 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 25/1 | 2024-06-28 | 2024-08-02 | 2024-08-09 | 35 | 42 | 2024-06 | 775 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 22/4 | 2024-06-29 | 2024-10-17 | 2024-10-27 | 110 | 120 | 2024-06 | 774 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 24/8 | 2024-06-29 | 2024-10-21 | 2024-10-26 | 114 | 119 | 2024-06 | 774 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 29/1 | 2024-06-29 | 2024-12-20 | 2024-12-25 | 174 | 179 | 2024-06 | 774 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 12/3 | 2024-06-30 | 2024-09-14 | 2024-09-30 | 76 | 92 | 2024-06 | 773 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 26/1 | 2024-07-04 | 2024-07-18 | 2024-07-28 | 14 | 24 | 2024-07 | 769 | TRUE | TRUE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 12/4 | 2024-07-05 | 2024-10-01 | 2024-10-19 | 88 | 106 | 2024-07 | 768 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 22/5 | 2024-07-06 | 2024-08-23 | 2024-09-08 | 48 | 64 | 2024-07 | 767 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 26/3 | 2024-07-07 | 2024-08-16 | 2024-08-18 | 40 | 42 | 2024-07 | 766 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 12/2 | 2024-07-10 | 2024-10-19 | 2024-10-30 | 101 | 112 | 2024-07 | 763 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 23/2 | 2024-07-10 | 2024-09-26 | 2024-10-03 | 78 | 85 | 2024-07 | 763 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 26/2 | 2024-07-10 | 2024-08-09 | 2024-08-14 | 30 | 35 | 2024-07 | 763 | TRUE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 12/11 | 2024-07-11 | 2025-02-11 | 2025-02-21 | 215 | 225 | 2024-07 | 762 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 26/4 | 2024-07-13 | 2024-07-27 | 2024-08-03 | 14 | 21 | 2024-07 | 760 | TRUE | TRUE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 22/3 | 2024-07-14 | 2025-03-03 | 2025-03-12 | 232 | 241 | 2024-07 | 759 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 24/1 | 2024-07-16 | 2024-11-15 | 2024-11-20 | 122 | 127 | 2024-07 | 757 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 12/7 | 2024-07-17 | 2024-11-14 | 2024-11-21 | 120 | 127 | 2024-07 | 756 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 22/2 | 2024-07-17 | 2024-10-29 | 2024-11-05 | 104 | 111 | 2024-07 | 756 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 27/1 | 2024-07-19 | 2024-08-19 | 2024-08-24 | 31 | 36 | 2024-07 | 754 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 21/9 | 2024-07-22 | 2024-09-09 | 2024-09-21 | 49 | 61 | 2024-07 | 751 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 12/6 | 2024-07-23 | 2024-11-07 | 2024-11-14 | 107 | 114 | 2024-07 | 750 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 21/8 | 2024-07-30 | 2024-10-01 | 2024-10-17 | 63 | 79 | 2024-07 | 743 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 12/5 | 2024-07-31 | 2024-11-01 | 2024-11-07 | 93 | 99 | 2024-07 | 742 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 21/7 | 2024-07-31 | 2024-09-12 | 2024-09-29 | 43 | 60 | 2024-07 | 742 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 27/8 | 2024-07-31 | 2024-12-03 | 2024-12-08 | 125 | 130 | 2024-07 | 742 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 27/4 | 2024-08-05 | 2024-09-19 | 2024-09-23 | 45 | 49 | 2024-08 | 737 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 27/5 | 2024-08-08 | 2024-09-24 | 2024-09-28 | 47 | 51 | 2024-08 | 734 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 12/8 | 2024-08-11 | 2024-11-12 | 2024-12-05 | 93 | 116 | 2024-08 | 731 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 23/0 | 2024-08-11 | 2024-11-21 | 2024-11-26 | 102 | 107 | 2024-08 | 731 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 27/0 | 2024-08-11 | 2024-11-24 | 2024-11-30 | 105 | 111 | 2024-08 | 731 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 27/6 | 2024-08-13 | 2024-09-29 | 2024-10-03 | 47 | 51 | 2024-08 | 729 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 27/7 | 2024-08-13 | 2024-10-03 | 2024-10-07 | 51 | 55 | 2024-08 | 729 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 26/0 | 2024-08-14 | 2024-11-19 | 2024-11-24 | 97 | 102 | 2024-08 | 728 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 21/4 | 2024-08-16 | 2024-11-16 | 2024-11-25 | 92 | 101 | 2024-08 | 726 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 25/0 | 2024-08-16 | 2024-11-02 | 2024-11-07 | 78 | 83 | 2024-08 | 726 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 24/0 | 2024-08-17 | 2024-11-02 | 2024-11-07 | 77 | 82 | 2024-08 | 725 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 27/2 | 2024-08-19 | 2024-09-14 | 2024-09-19 | 26 | 31 | 2024-08 | 723 | TRUE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 12/9 | 2024-08-22 | 2024-10-01 | 2024-10-26 | 40 | 65 | 2024-08 | 720 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 22/1 | 2024-08-23 | 2024-10-18 | 2024-10-27 | 56 | 65 | 2024-08 | 719 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 27/9 | 2024-08-23 | 2025-04-29 | 2025-05-02 | 249 | 252 | 2024-08 | 719 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 29/4 | 2024-08-24 | 2024-09-21 | 2024-10-04 | 28 | 41 | 2024-08 | 718 | TRUE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 22/0 | 2024-08-25 | 2024-11-05 | 2024-11-15 | 72 | 82 | 2024-08 | 717 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 29/5 | 2024-08-27 | 2024-10-05 | 2024-10-14 | 39 | 48 | 2024-08 | 715 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 11/11 | 2024-08-28 | 2024-12-12 | 2024-12-28 | 106 | 122 | 2024-08 | 714 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 29/3 | 2024-08-30 | 2024-12-09 | 2024-12-13 | 101 | 105 | 2024-08 | 712 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 21/2 | 2024-08-31 | 2024-11-26 | 2024-12-02 | 87 | 93 | 2024-08 | 711 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 12/0 | 2024-09-08 | 2024-11-22 | 2024-11-30 | 75 | 83 | 2024-09 | 703 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 29/9 | 2024-09-11 | 2025-06-06 | 2025-06-18 | 268 | 280 | 2024-09 | 700 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 30/4 | 2024-09-11 | 2024-10-16 | 2024-10-21 | 35 | 40 | 2024-09 | 700 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 29/8 | 2024-09-16 | 2024-12-15 | 2024-12-19 | 90 | 94 | 2024-09 | 695 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 23/1 | 2024-09-20 | 2024-11-09 | 2024-11-14 | 50 | 55 | 2024-09 | 691 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 29/6 | 2024-09-20 | 2025-01-16 | 2025-01-19 | 118 | 121 | 2024-09 | 691 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 30/5 | 2024-09-20 | 2025-01-23 | 2025-01-28 | 125 | 130 | 2024-09 | 691 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 12/10 | 2024-09-22 | 2024-10-27 | 2024-11-12 | 35 | 51 | 2024-09 | 689 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 30/1 | 2024-09-27 | 2025-01-04 | 2025-01-15 | 99 | 110 | 2024-09 | 684 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 13/0 | 2024-09-30 | 2025-03-08 | 2025-03-11 | 159 | 162 | 2024-09 | 681 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 30/3 | 2024-10-03 | 2024-12-26 | 2024-12-31 | 84 | 89 | 2024-10 | 678 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 25/2 | 2024-10-04 | 2024-11-08 | 2024-11-13 | 35 | 40 | 2024-10 | 677 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 19/3 | 2024-10-10 | 2024-12-11 | 2024-12-15 | 62 | 66 | 2024-10 | 671 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 30/0 | 2024-10-12 | 2025-06-03 | 2025-06-11 | 234 | 242 | 2024-10 | 669 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 12/1 | 2024-10-14 | 2025-08-23 | 2025-08-29 | 313 | 319 | 2024-10 | 667 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 19/2 | 2024-10-17 | 2024-12-16 | 2024-12-18 | 60 | 62 | 2024-10 | 664 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 27/3 | 2024-10-18 | 2025-11-26 | 2025-12-10 | 404 | 418 | 2024-10 | 663 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 31/1 | 2024-10-21 | 2025-01-28 | 2025-02-03 | 99 | 105 | 2024-10 | 660 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 39/7 | 2024-10-21 | 2025-09-13 | 2025-10-11 | 327 | 355 | 2024-10 | 660 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 17/3 | 2024-10-24 | 2025-04-12 | 2025-04-26 | 170 | 184 | 2024-10 | 657 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 13/1 | 2024-10-30 | 2025-02-09 | 2025-02-12 | 102 | 105 | 2024-10 | 651 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 21/6 | 2024-10-30 | 2024-12-03 | 2024-12-06 | 34 | 37 | 2024-10 | 651 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 42/0 | 2024-10-30 | 2025-09-13 | 2025-09-23 | 318 | 328 | 2024-10 | 651 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 41/1 | 2024-11-07 | 2025-10-22 | 2025-10-25 | 349 | 352 | 2024-11 | 643 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 15/2 | 2024-11-08 | 2025-03-27 | 2025-03-29 | 139 | 141 | 2024-11 | 642 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 11/6 | 2024-11-13 | 2025-01-16 | 2025-01-30 | 64 | 78 | 2024-11 | 637 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 18/3 | 2024-11-15 | 2024-12-19 | 2024-12-22 | 34 | 37 | 2024-11 | 635 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 15/1 | 2024-11-16 | 2025-03-23 | 2025-03-26 | 127 | 130 | 2024-11 | 634 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 39/1 | 2024-11-18 | 2025-09-16 | 2025-09-25 | 302 | 311 | 2024-11 | 632 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 11/10 | 2024-11-19 | 2025-01-02 | 2025-01-15 | 44 | 57 | 2024-11 | 631 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 15/4 | 2024-11-23 | 2025-03-29 | 2025-04-02 | 126 | 130 | 2024-11 | 627 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 11/9 | 2024-11-24 | 2025-02-22 | 2025-03-01 | 90 | 97 | 2024-11 | 626 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 13/4 | 2024-11-24 | 2025-02-19 | 2025-02-23 | 87 | 91 | 2024-11 | 626 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 38/3 | 2024-11-24 | 2025-03-03 | 2025-03-09 | 99 | 105 | 2024-11 | 626 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 16/6 | 2024-11-26 | 2025-01-14 | 2025-01-18 | 49 | 53 | 2024-11 | 624 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 17/1 | 2024-11-26 | 2025-01-03 | 2025-01-08 | 38 | 43 | 2024-11 | 624 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 38/1 | 2024-11-28 | 2025-02-26 | 2025-03-02 | 90 | 94 | 2024-11 | 622 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 13/3 | 2024-11-29 | 2025-02-13 | 2025-02-19 | 76 | 82 | 2024-11 | 621 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 18/0 | 2024-11-29 | 2024-12-27 | 2025-01-03 | 28 | 35 | 2024-11 | 621 | TRUE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 39/3 | 2024-11-29 | 2025-07-06 | 2025-07-12 | 219 | 225 | 2024-11 | 621 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 10/8 | 2024-11-30 | 2025-08-07 | 2025-08-12 | 250 | 255 | 2024-11 | 620 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 13/5 | 2024-11-30 | 2025-02-28 | 2025-03-02 | 90 | 92 | 2024-11 | 620 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 13/9 | 2024-11-30 | 2025-03-16 | 2025-03-19 | 106 | 109 | 2024-11 | 620 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 38/2 | 2024-11-30 | 2025-05-02 | 2025-05-05 | 153 | 156 | 2024-11 | 620 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 16/9 | 2024-12-05 | 2025-01-22 | 2025-01-30 | 48 | 56 | 2024-12 | 615 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 13/2 | 2024-12-06 | 2025-02-04 | 2025-02-08 | 60 | 64 | 2024-12 | 614 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 18/1 | 2024-12-07 | 2024-12-26 | 2024-12-28 | 19 | 21 | 2024-12 | 613 | TRUE | TRUE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 37/5 | 2024-12-07 | 2025-03-29 | 2025-04-04 | 112 | 118 | 2024-12 | 613 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 35/2 | 2024-12-08 | 2025-06-25 | 2025-07-04 | 199 | 208 | 2024-12 | 612 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 18/2 | 2024-12-09 | 2024-12-23 | 2024-12-25 | 14 | 16 | 2024-12 | 611 | TRUE | TRUE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 39/2 | 2024-12-10 | 2025-09-27 | 2025-10-09 | 291 | 303 | 2024-12 | 610 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 11/0 | 2024-12-11 | 2025-08-01 | 2025-08-06 | 233 | 238 | 2024-12 | 609 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 31/3 | 2024-12-11 | 2025-06-01 | 2025-06-06 | 172 | 177 | 2024-12 | 609 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 13/10 | 2024-12-12 | 2025-03-20 | 2025-03-22 | 98 | 100 | 2024-12 | 608 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 38/4 | 2024-12-12 | 2025-03-10 | 2025-03-13 | 88 | 91 | 2024-12 | 608 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 13/6 | 2024-12-13 | 2025-02-24 | 2025-02-27 | 73 | 76 | 2024-12 | 607 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 21/5 | 2024-12-13 | 2025-06-05 | 2025-06-19 | 174 | 188 | 2024-12 | 607 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 21/1 | 2024-12-14 | 2024-12-28 | 2025-01-13 | 14 | 30 | 2024-12 | 606 | TRUE | TRUE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 31/5 | 2024-12-15 | 2025-02-10 | 2025-02-14 | 57 | 61 | 2024-12 | 605 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 39/4 | 2024-12-15 | 2025-06-24 | 2025-07-05 | 191 | 202 | 2024-12 | 605 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 35/3 | 2024-12-16 | 2025-04-15 | 2025-04-18 | 120 | 123 | 2024-12 | 604 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 31/2 | 2024-12-19 | 2025-02-21 | 2025-02-25 | 64 | 68 | 2024-12 | 601 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 38/5 | 2024-12-20 | 2025-03-15 | 2025-03-19 | 85 | 89 | 2024-12 | 600 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 30/2 | 2024-12-21 | 2024-12-02 | 2025-01-06 | -19 | 16 | 2024-12 | 599 | FALSE | FALSE | Yes | Yes | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 21/3 | 2024-12-22 | 2025-03-13 | 2025-03-27 | 81 | 95 | 2024-12 | 598 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 38/7 | 2024-12-22 | 2025-03-24 | 2025-03-29 | 92 | 97 | 2024-12 | 598 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 11/3 | 2024-12-23 | 2025-06-29 | 2025-07-02 | 188 | 191 | 2024-12 | 597 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 16/11 | 2024-12-23 | 2025-11-16 | 2025-11-23 | 328 | 335 | 2024-12 | 597 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 31/4 | 2024-12-23 | 2025-02-04 | 2025-02-09 | 43 | 48 | 2024-12 | 597 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 37/4 | 2024-12-24 | 2025-04-18 | 2025-04-23 | 115 | 120 | 2024-12 | 596 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 25/3 | 2024-12-25 | 2025-02-10 | 2025-02-18 | 47 | 55 | 2024-12 | 595 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 16/10 | 2024-12-27 | 2025-01-22 | 2025-01-27 | 26 | 31 | 2024-12 | 593 | TRUE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 31/0 | 2024-12-28 | 2025-03-02 | 2025-03-07 | 64 | 69 | 2024-12 | 592 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 11/2 | 2024-12-30 | 2025-06-25 | 2025-06-28 | 177 | 180 | 2024-12 | 590 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 21/0 | 2024-12-30 | 2025-05-03 | 2025-05-08 | 124 | 129 | 2024-12 | 590 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 16/8 | 2024-12-31 | 2025-01-18 | 2025-01-22 | 18 | 22 | 2024-12 | 589 | TRUE | TRUE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 28/0 | 2024-12-31 | 2025-04-24 | 2025-04-28 | 114 | 118 | 2024-12 | 589 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 38/6 | 2024-12-31 | 2025-03-20 | 2025-03-23 | 79 | 82 | 2024-12 | 589 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 29/2 | 2025-01-03 | 2025-01-19 | 2025-01-23 | 16 | 20 | 2025-01 | 586 | TRUE | TRUE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 36/7 | 2025-01-04 | 2025-10-10 | 2025-10-19 | 279 | 288 | 2025-01 | 585 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 11/4 | 2025-01-05 | 2025-10-23 | 2025-10-27 | 291 | 295 | 2025-01 | 584 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 16/7 | 2025-01-05 | 2025-07-08 | 2025-08-02 | 184 | 209 | 2025-01 | 584 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 19/1 | 2025-01-05 | 2025-03-28 | 2025-04-11 | 82 | 96 | 2025-01 | 584 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 36/8 | 2025-01-05 | 2025-10-21 | 2025-11-02 | 289 | 301 | 2025-01 | 584 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 29/7 | 2025-01-06 | 2025-02-26 | 2025-03-01 | 51 | 54 | 2025-01 | 583 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 36/6 | 2025-01-09 | 2025-05-11 | 2025-05-24 | 122 | 135 | 2025-01 | 580 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 11/5 | 2025-01-10 | 2025-01-30 | 2025-02-10 | 20 | 31 | 2025-01 | 579 | TRUE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 31/6 | 2025-01-12 | 2025-02-15 | 2025-02-20 | 34 | 39 | 2025-01 | 577 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 13/7 | 2025-01-13 | 2025-03-03 | 2025-03-07 | 49 | 53 | 2025-01 | 576 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 38/0 | 2025-01-15 | 2025-04-05 | 2025-04-17 | 80 | 92 | 2025-01 | 574 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 17/0 | 2025-01-16 | 2025-05-10 | 2025-06-04 | 114 | 139 | 2025-01 | 573 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 33/0 | 2025-01-16 | 2025-04-02 | 2025-04-09 | 76 | 83 | 2025-01 | 573 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 37/6 | 2025-01-16 | 2025-05-11 | 2025-05-16 | 115 | 120 | 2025-01 | 573 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 11/1 | 2025-01-17 | 2025-05-05 | 2025-05-06 | 108 | 109 | 2025-01 | 572 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 17/2 | 2025-01-18 | 2025-04-27 | 2025-05-09 | 99 | 111 | 2025-01 | 571 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 36/5 | 2025-01-18 | 2025-04-14 | 2025-04-21 | 86 | 93 | 2025-01 | 571 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 29/0 | 2025-01-19 | 2025-04-19 | 2025-04-23 | 90 | 94 | 2025-01 | 570 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 16/2 | 2025-01-21 | 2025-01-30 | 2025-02-03 | 9 | 13 | 2025-01 | 568 | TRUE | TRUE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 33/2 | 2025-01-22 | 2025-06-05 | 2025-06-16 | 134 | 145 | 2025-01 | 567 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 36/4 | 2025-01-24 | 2025-04-22 | 2025-04-27 | 88 | 93 | 2025-01 | 565 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 39/5 | 2025-01-24 | 2025-08-08 | 2025-09-08 | 196 | 227 | 2025-01 | 565 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 33/1 | 2025-01-25 | 2025-03-13 | 2025-03-17 | 47 | 51 | 2025-01 | 564 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 37/1 | 2025-01-25 | 2025-12-13 | 2025-12-18 | 322 | 327 | 2025-01 | 564 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 10/0 | 2025-01-27 | 2025-07-03 | 2025-07-07 | 157 | 161 | 2025-01 | 562 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 32/1 | 2025-01-27 | 2025-03-08 | 2025-03-12 | 40 | 44 | 2025-01 | 562 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 39/6 | 2025-01-28 | 2025-10-14 | 2025-10-27 | 259 | 272 | 2025-01 | 561 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 32/2 | 2025-01-29 | 2025-03-23 | 2025-03-27 | 53 | 57 | 2025-01 | 560 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 10/2 | 2025-01-30 | 2025-05-14 | 2025-05-17 | 104 | 107 | 2025-01 | 559 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 14/0 | 2025-01-30 | 2025-07-05 | 2025-07-13 | 156 | 164 | 2025-01 | 559 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 36/3 | 2025-01-30 | 2025-03-01 | 2025-03-30 | 30 | 59 | 2025-01 | 559 | TRUE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 37/2 | 2025-01-30 | 2025-04-24 | 2025-04-30 | 84 | 90 | 2025-01 | 559 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 19/0 | 2025-01-31 | 2025-05-15 | 2025-05-22 | 104 | 111 | 2025-01 | 558 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 35/1 | 2025-01-31 | 2025-05-08 | 2025-05-31 | 97 | 120 | 2025-01 | 558 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 39/8 | 2025-01-31 | 2025-11-06 | 2025-11-23 | 279 | 296 | 2025-01 | 558 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 35/4 | 2025-02-02 | 2025-04-10 | 2025-04-14 | 67 | 71 | 2025-02 | 556 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 10/1 | 2025-02-04 | 2025-05-18 | 2025-05-20 | 103 | 105 | 2025-02 | 554 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 36/1 | 2025-02-06 | 2025-03-30 | 2025-04-05 | 52 | 58 | 2025-02 | 552 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 9/10 | 2025-02-06 | 2025-07-08 | 2025-07-12 | 152 | 156 | 2025-02 | 552 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 36/0 | 2025-02-09 | 2025-11-08 | 2025-11-19 | 272 | 283 | 2025-02 | 549 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 9/9 | 2025-02-09 | 2025-09-01 | 2025-09-04 | 204 | 207 | 2025-02 | 549 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 16/0 | 2025-02-10 | 2025-04-03 | 2025-04-10 | 52 | 59 | 2025-02 | 548 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 37/0 | 2025-02-10 | 2025-11-20 | 2025-11-26 | 283 | 289 | 2025-02 | 548 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 10/4 | 2025-02-12 | 2025-05-10 | 2025-05-13 | 87 | 90 | 2025-02 | 546 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 32/0 | 2025-02-13 | 2025-03-17 | 2025-03-23 | 32 | 38 | 2025-02 | 545 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 36/2 | 2025-02-14 | 2025-04-06 | 2025-04-13 | 51 | 58 | 2025-02 | 544 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 9/7 | 2025-02-14 | 2025-07-17 | 2025-07-20 | 153 | 156 | 2025-02 | 544 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 10/3 | 2025-02-15 | 2025-05-21 | 2025-05-28 | 95 | 102 | 2025-02 | 543 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 10/5 | 2025-02-16 | 2025-05-29 | 2025-06-02 | 102 | 106 | 2025-02 | 542 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 39/0 | 2025-02-16 | 2025-07-13 | 2025-07-30 | 147 | 164 | 2025-02 | 542 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 9/5 | 2025-02-16 | 2025-07-26 | 2025-07-31 | 160 | 165 | 2025-02 | 542 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 39/9 | 2025-02-18 | 2025-11-27 | 2025-12-21 | 282 | 306 | 2025-02 | 540 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 10/9 | 2025-02-19 | 2025-05-07 | 2025-05-10 | 77 | 80 | 2025-02 | 539 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 35/0 | 2025-02-20 | 2025-07-17 | 2025-08-03 | 147 | 164 | 2025-02 | 538 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 9/8 | 2025-02-20 | 2025-07-13 | 2025-07-16 | 143 | 146 | 2025-02 | 538 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 13/8 | 2025-02-21 | 2025-03-12 | 2025-03-16 | 19 | 23 | 2025-02 | 537 | TRUE | TRUE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 42/4 | 2025-02-21 | 2025-07-12 | 2025-07-20 | 141 | 149 | 2025-02 | 537 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 42/6 | 2025-02-21 | 2025-08-05 | 2025-08-14 | 165 | 174 | 2025-02 | 537 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 10/7 | 2025-02-23 | 2025-05-01 | 2025-05-04 | 67 | 70 | 2025-02 | 535 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 42/5 | 2025-02-23 | 2025-07-30 | 2025-08-04 | 157 | 162 | 2025-02 | 535 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 9/6 | 2025-02-24 | 2025-07-21 | 2025-07-25 | 147 | 151 | 2025-02 | 534 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 10/6 | 2025-02-25 | 2025-06-19 | 2025-06-24 | 114 | 119 | 2025-02 | 533 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 9/4 | 2025-02-27 | 2025-08-13 | 2025-08-18 | 167 | 172 | 2025-02 | 531 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 42/7 | 2025-02-28 | 2025-08-16 | 2025-08-24 | 169 | 177 | 2025-02 | 530 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 9/3 | 2025-02-28 | 2025-10-07 | 2025-10-12 | 221 | 226 | 2025-02 | 530 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 42/3 | 2025-03-01 | 2025-07-21 | 2025-07-29 | 142 | 150 | 2025-03 | 529 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 15/0 | 2025-03-04 | 2025-06-24 | 2025-07-04 | 112 | 122 | 2025-03 | 526 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 16/4 | 2025-03-04 | 2025-04-19 | 2025-04-21 | 46 | 48 | 2025-03 | 526 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 9/2 | 2025-03-04 | 2025-08-19 | 2025-08-31 | 168 | 180 | 2025-03 | 526 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 40/0 | 2025-03-06 | 2025-08-13 | 2025-08-29 | 160 | 176 | 2025-03 | 524 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 42/2 | 2025-03-07 | 2025-10-17 | 2025-10-21 | 224 | 228 | 2025-03 | 523 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 9/1 | 2025-03-07 | 2025-08-12 | 2025-08-19 | 158 | 165 | 2025-03 | 523 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 16/5 | 2025-03-08 | 2025-04-22 | 2025-04-24 | 45 | 47 | 2025-03 | 522 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 32/3 | 2025-03-08 | 2025-03-28 | 2025-04-01 | 20 | 24 | 2025-03 | 522 | TRUE | TRUE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 40/1 | 2025-03-12 | 2025-08-30 | 2025-09-05 | 171 | 177 | 2025-03 | 518 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 16/1 | 2025-03-13 | 2025-04-11 | 2025-04-15 | 29 | 33 | 2025-03 | 517 | TRUE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 8/15 | 2025-03-13 | 2025-08-31 | 2025-09-07 | 171 | 178 | 2025-03 | 517 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 16/3 | 2025-03-18 | 2025-04-16 | 2025-04-19 | 29 | 32 | 2025-03 | 512 | TRUE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 8/14 | 2025-03-18 | 2025-07-22 | 2025-07-29 | 126 | 133 | 2025-03 | 512 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 11/7 | 2025-03-19 | 2025-10-28 | 2025-11-02 | 223 | 228 | 2025-03 | 511 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 9/0 | 2025-03-24 | 2025-08-14 | 2025-08-30 | 143 | 159 | 2025-03 | 506 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 34/1 | 2025-03-26 | 2025-08-04 | 2025-08-12 | 131 | 139 | 2025-03 | 504 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 8/12 | 2025-03-28 | 2025-08-08 | 2025-08-13 | 133 | 138 | 2025-03 | 502 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 13/11 | 2025-03-30 | 2025-04-28 | 2025-04-30 | 29 | 31 | 2025-03 | 500 | TRUE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 15/3 | 2025-04-08 | 2025-04-25 | 2025-04-27 | 17 | 19 | 2025-04 | 491 | TRUE | TRUE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 34/2 | 2025-04-11 | 2025-07-05 | 2025-07-16 | 85 | 96 | 2025-04 | 488 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 11/8 | 2025-04-14 | 2025-11-15 | 2025-11-19 | 215 | 219 | 2025-04 | 485 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 6/2 | 2025-04-18 | 2025-07-19 | 2025-07-21 | 92 | 94 | 2025-04 | 481 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 37/3 | 2025-04-19 | 2025-05-06 | 2025-05-10 | 17 | 21 | 2025-04 | 480 | TRUE | TRUE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 6/1 | 2025-04-22 | 2025-07-22 | 2025-07-28 | 91 | 97 | 2025-04 | 477 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 20/0 | 2025-04-25 | 2025-05-10 | 2025-05-14 | 15 | 19 | 2025-04 | 474 | TRUE | TRUE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 6/6 | 2025-04-27 | 2025-08-02 | 2025-08-04 | 97 | 99 | 2025-04 | 472 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 42/1 | 2025-04-28 | 2025-07-29 | 2025-08-01 | 92 | 95 | 2025-04 | 471 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 6/7 | 2025-04-29 | 2025-12-14 | 2025-12-16 | 229 | 231 | 2025-04 | 470 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 20A/0 | 2025-04-30 | 2025-06-20 | 2025-07-07 | 51 | 68 | 2025-04 | 469 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 34/0 | 2025-05-03 | 2025-06-17 | 2025-06-25 | 45 | 53 | 2025-05 | 466 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 8/8 | 2025-05-03 | 2025-07-30 | 2025-08-02 | 88 | 91 | 2025-05 | 466 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4/7 | 2025-05-04 | 2025-09-08 | 2025-09-09 | 127 | 128 | 2025-05 | 465 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 8/7 | 2025-05-04 | 2025-08-03 | 2025-08-07 | 91 | 95 | 2025-05 | 465 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4/8 | 2025-05-07 | 2026-01-03 | 2026-01-06 | 241 | 244 | 2025-05 | 462 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 8/9 | 2025-05-08 | 2025-09-08 | 2025-09-15 | 123 | 130 | 2025-05 | 461 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 41/0 | 2025-05-11 | 2025-09-06 | 2025-09-13 | 118 | 125 | 2025-05 | 458 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4/9 | 2025-05-11 | 2025-09-10 | 2025-09-14 | 122 | 126 | 2025-05 | 458 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 8/5 | 2025-05-12 | 2025-12-05 | 2025-12-08 | 207 | 210 | 2025-05 | 457 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4/6 | 2025-05-13 | 2025-09-05 | 2025-09-07 | 115 | 117 | 2025-05 | 456 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 8/10 | 2025-05-13 | 2025-11-20 | 2025-11-23 | 191 | 194 | 2025-05 | 456 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 42/9 | 2025-05-15 | 2025-09-07 | 2025-09-10 | 115 | 118 | 2025-05 | 454 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 8/6 | 2025-05-15 | 2025-07-14 | 2025-07-21 | 60 | 67 | 2025-05 | 454 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4/12 | 2025-05-16 | 2025-09-09 | 2025-09-16 | 116 | 123 | 2025-05 | 453 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4/3 | 2025-05-17 | 2025-10-10 | 2025-10-15 | 146 | 151 | 2025-05 | 452 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 6/3 | 2025-05-19 | 2025-07-15 | 2025-07-18 | 57 | 60 | 2025-05 | 450 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4/19 | 2025-05-20 | 2025-10-17 | 2025-10-22 | 150 | 155 | 2025-05 | 449 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4/5 | 2025-05-20 | 2025-11-28 | 2025-11-30 | 192 | 194 | 2025-05 | 449 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 6/4 | 2025-05-20 | 2025-07-11 | 2025-07-15 | 52 | 56 | 2025-05 | 449 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4/18 | 2025-05-21 | 2025-09-28 | 2025-10-04 | 130 | 136 | 2025-05 | 448 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 43A/2 | 2025-05-22 | 2026-01-08 | 2026-01-12 | 231 | 235 | 2025-05 | 447 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 8/11 | 2025-05-22 |  | 2025-11-26 |  | 188 | 2025-05 | 447 | FALSE | FALSE | No | No |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 6/5 | 2025-05-23 | 2025-07-04 | 2025-07-10 | 42 | 48 | 2025-05 | 446 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 43A/3 | 2025-05-25 | 2025-11-23 | 2025-11-29 | 182 | 188 | 2025-05 | 444 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4/4 | 2025-05-25 | 2025-10-17 | 2025-10-21 | 145 | 149 | 2025-05 | 444 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4/17 | 2025-05-27 | 2025-09-16 | 2025-09-26 | 112 | 122 | 2025-05 | 442 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4/14 | 2025-05-28 | 2025-11-18 | 2025-11-20 | 174 | 176 | 2025-05 | 441 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 43A/4 | 2025-05-28 | 2025-11-18 | 2025-11-23 | 174 | 179 | 2025-05 | 441 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4/15 | 2025-05-30 | 2025-11-21 | 2025-11-23 | 175 | 177 | 2025-05 | 439 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 8/13 | 2025-05-30 | 2025-08-05 | 2025-08-08 | 67 | 70 | 2025-05 | 439 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 3/3 | 2025-05-31 | 2025-12-20 | 2025-12-21 | 203 | 204 | 2025-05 | 438 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4/0 | 2025-05-31 | 2025-09-05 | 2025-09-08 | 97 | 100 | 2025-05 | 438 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4/16 | 2025-05-31 |  | 2025-11-25 |  | 178 | 2025-05 | 438 | FALSE | FALSE | No | No |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 43A/5 | 2025-05-31 | 2025-11-11 | 2025-11-17 | 164 | 170 | 2025-05 | 438 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4/13 | 2025-06-01 | 2025-10-31 | 2025-11-05 | 152 | 157 | 2025-06 | 437 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4/2 | 2025-06-03 | 2025-09-21 | 2025-09-24 | 110 | 113 | 2025-06 | 435 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 43/3 | 2025-06-04 | 2025-10-07 | 2025-10-11 | 125 | 129 | 2025-06 | 434 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 3/0 | 2025-06-06 | 2025-11-11 | 2025-11-18 | 158 | 165 | 2025-06 | 432 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 1B/3 | 2025-06-08 | 2025-12-07 | 2025-12-08 | 182 | 183 | 2025-06 | 430 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 28/1 | 2025-06-08 | 2026-01-07 | 2026-01-13 | 213 | 219 | 2025-06 | 430 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 43/2 | 2025-06-09 | 2025-09-24 | 2025-09-30 | 107 | 113 | 2025-06 | 429 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 2/5 | 2025-06-14 | 2025-12-24 | 2025-12-25 | 193 | 194 | 2025-06 | 424 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 42/8 | 2025-06-14 | 2025-09-01 | 2025-09-06 | 79 | 84 | 2025-06 | 424 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 1B/2 | 2025-06-15 | 2025-12-04 | 2025-12-06 | 172 | 174 | 2025-06 | 423 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4/1 | 2025-06-15 | 2025-10-22 | 2025-10-30 | 129 | 137 | 2025-06 | 423 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 3/1 | 2025-06-17 | 2025-11-06 | 2025-11-11 | 142 | 147 | 2025-06 | 421 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 1B/0 | 2025-06-19 | 2025-12-09 | 2025-12-16 | 173 | 180 | 2025-06 | 419 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 1A/0 | 2025-06-21 | 2025-08-20 | 2025-08-30 | 60 | 70 | 2025-06 | 417 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 1B/1 | 2025-06-21 | 2025-11-30 | 2025-12-04 | 162 | 166 | 2025-06 | 417 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 3/2 | 2025-06-21 | 2025-12-17 | 2025-12-19 | 179 | 181 | 2025-06 | 417 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 43/1 | 2025-06-21 | 2025-10-26 | 2025-11-02 | 127 | 134 | 2025-06 | 417 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 2/3 | 2025-06-23 | 2025-08-31 | 2025-09-03 | 69 | 72 | 2025-06 | 415 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 43/4 | 2025-06-24 | 2025-09-21 | 2025-10-06 | 89 | 104 | 2025-06 | 414 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 8/2 | 2025-06-25 | 2025-12-17 | 2025-12-21 | 175 | 179 | 2025-06 | 413 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 1C/0 | 2025-06-29 | 2025-12-26 | 2025-12-30 | 180 | 184 | 2025-06 | 409 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 2/1 | 2025-06-29 | 2025-12-11 | 2025-12-13 | 165 | 167 | 2025-06 | 409 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 43/0 | 2025-06-30 | 2025-12-01 | 2025-12-09 | 154 | 162 | 2025-06 | 408 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 2/2 | 2025-07-03 | 2025-09-25 | 2025-09-30 | 84 | 89 | 2025-07 | 405 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 8/4 | 2025-07-08 | 2025-11-10 | 2025-11-14 | 125 | 129 | 2025-07 | 400 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 2/0 | 2025-07-10 | 2025-12-31 | 2026-01-04 | 174 | 178 | 2025-07 | 398 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 2/4 | 2025-07-12 | 2025-12-22 | 2025-12-23 | 163 | 164 | 2025-07 | 396 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 6/0 | 2025-07-13 | 2025-11-27 | 2025-12-03 | 137 | 143 | 2025-07 | 395 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 43/5 | 2025-07-14 | 2025-10-12 | 2025-10-16 | 90 | 94 | 2025-07 | 394 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 5/0 | 2025-07-16 | 2025-09-21 | 2025-09-29 | 67 | 75 | 2025-07 | 392 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 8/3 | 2025-07-18 | 2025-11-04 | 2025-11-09 | 109 | 114 | 2025-07 | 390 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 43A/1 | 2025-07-20 | 2025-12-30 | 2026-01-07 | 163 | 171 | 2025-07 | 388 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 8/1 | 2025-07-22 | 2025-12-27 | 2025-12-31 | 158 | 162 | 2025-07 | 386 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 43B/0 | 2025-07-28 | 2025-11-04 | 2025-11-11 | 99 | 106 | 2025-07 | 380 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 43A/0 | 2025-08-03 | 2025-12-19 |  | 138 |  | 2025-08 | 374 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 1/0 | 2025-08-25 | 2025-10-01 | 2025-10-09 | 37 | 45 | 2025-08 | 352 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 19/0-20/0 | 2025-10-19 |  |  |  |  | 2025-10 | 297 | FALSE | FALSE | No | No |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 18/0-19/0 | 2025-10-21 |  |  |  |  | 2025-10 | 295 | FALSE | FALSE | No | No |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 44/0 | 2025-10-26 | 2025-12-10 | 2025-12-20 | 45 | 55 | 2025-10 | 290 | FALSE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 7/0 | 2025-11-26 | 2025-12-09 | 2025-12-13 | 13 | 17 | 2025-11 | 259 | TRUE | TRUE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 8/0 | 2025-12-05 | 2025-12-22 |  | 17 |  | 2025-12 | 250 | TRUE | FALSE | Yes | No | exact | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 7/0 - 8/0 | 2026-01-31 |  |  |  |  | 2026-01 | 193 | FALSE | FALSE | No | No |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | Gantry - 1/0 | 2026-02-01 |  |  |  |  | 2026-02 | 192 | FALSE | FALSE | No | No |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 8/2 - 8/3 | 2026-02-04 |  |  |  |  | 2026-02 | 189 | FALSE | FALSE | No | No |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 1/0-1A/0 | 2026-02-08 |  |  |  |  | 2026-02 | 185 | FALSE | FALSE | No | No |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 1A/0 - 1B/0 | 2026-02-11 |  |  |  |  | 2026-02 | 182 | FALSE | FALSE | No | No |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4/12 - 5/0 | 2026-02-12 |  |  |  |  | 2026-02 | 181 | FALSE | FALSE | No | No |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 8/0 - 8/1 | 2026-02-19 |  |  |  |  | 2026-02 | 174 | FALSE | FALSE | No | No |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 8/1-8/2 | 2026-02-19 |  |  |  |  | 2026-02 | 174 | FALSE | FALSE | No | No |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 1C/0 - 2/0 | 2026-02-25 |  |  |  |  | 2026-02 | 168 | FALSE | FALSE | No | No |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 5/0 - 6/0 | 2026-03-02 |  |  |  |  | 2026-03 | 163 | FALSE | FALSE | No | No |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 3/0-4/0 | 2026-03-14 |  |  |  |  | 2026-03 | 151 | FALSE | FALSE | No | No |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 43A/0 - 43A/1 | 2026-06-18 |  |  |  |  | 2026-06 | 55 | FALSE | FALSE | No | No |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 43A/1 - 43B/0 | 2026-06-21 |  |  |  |  | 2026-06 | 52 | FALSE | FALSE | No | No |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 43B/0 - 44/0 | 2026-06-24 |  |  |  |  | 2026-06 | 49 | FALSE | FALSE | No | No |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 505 | 164/3 | 2024-03-28 | 2025-12-25 | 2025-12-30 | 637 | 642 | 2024-03 | 867 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 170/4 | 2024-04-04 | 2026-01-04 | 2026-01-10 | 640 | 646 | 2024-04 | 860 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 136/0 | 2024-04-28 | 2025-09-19 | 2025-09-28 | 509 | 518 | 2024-04 | 836 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 101/2 | 2024-10-06 | 2025-01-14 | 2025-01-19 | 100 | 105 | 2024-10 | 675 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 109/2 | 2024-10-07 | 2025-02-25 | 2025-02-28 | 141 | 144 | 2024-10 | 674 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 101/3 | 2024-10-11 | 2025-01-24 | 2025-01-27 | 105 | 108 | 2024-10 | 670 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 110A/2 | 2024-10-11 | 2025-09-10 | 2025-09-19 | 334 | 343 | 2024-10 | 670 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 101/4 | 2024-10-21 | 2025-01-27 | 2025-01-31 | 98 | 102 | 2024-10 | 660 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 110/6 | 2024-10-24 | 2025-03-15 | 2025-03-19 | 142 | 146 | 2024-10 | 657 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 101/5 | 2024-10-25 | 2025-02-01 | 2025-02-04 | 99 | 102 | 2024-10 | 656 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 108/4 | 2024-10-28 | 2025-04-03 | 2025-04-07 | 157 | 161 | 2024-10 | 653 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 109/1 | 2024-10-29 | 2025-03-01 | 2025-03-04 | 123 | 126 | 2024-10 | 652 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 101/6 | 2024-11-02 | 2025-02-05 | 2025-02-08 | 95 | 98 | 2024-11 | 648 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 111/1 | 2024-11-04 | 2025-05-02 | 2025-05-09 | 179 | 186 | 2024-11 | 646 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 101/8 | 2024-11-08 | 2025-02-13 | 2025-02-15 | 97 | 99 | 2024-11 | 642 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 110A/1 | 2024-11-10 | 2025-03-26 | 2025-03-30 | 136 | 140 | 2024-11 | 640 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 101/1 | 2024-11-14 | 2025-01-21 | 2025-01-24 | 68 | 71 | 2024-11 | 636 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 113/2 | 2024-11-14 | 2025-04-11 | 2025-04-17 | 148 | 154 | 2024-11 | 636 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 110/8 | 2024-11-15 | 2025-03-30 | 2025-04-03 | 135 | 139 | 2024-11 | 635 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 110/3 | 2024-11-17 | 2025-03-22 | 2025-03-26 | 125 | 129 | 2024-11 | 633 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 101/7 | 2024-11-18 | 2025-02-09 | 2025-02-12 | 83 | 86 | 2024-11 | 632 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 111/2 | 2024-11-18 | 2025-05-09 | 2025-05-18 | 172 | 181 | 2024-11 | 632 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 105/1 | 2024-11-19 | 2025-04-26 | 2025-04-29 | 158 | 161 | 2024-11 | 631 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 114/10 | 2024-11-20 | 2025-04-06 | 2025-04-12 | 137 | 143 | 2024-11 | 630 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 110/1 | 2024-11-22 | 2025-03-05 | 2025-03-07 | 103 | 105 | 2024-11 | 628 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 113/1 | 2024-11-22 | 2025-04-18 | 2025-04-23 | 147 | 152 | 2024-11 | 628 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 110/5 | 2024-11-23 | 2025-02-21 | 2025-02-24 | 90 | 93 | 2024-11 | 627 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 114/8 | 2024-11-23 | 2025-09-19 | 2025-09-23 | 300 | 304 | 2024-11 | 627 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 104/1 | 2024-11-27 | 2025-04-18 | 2025-04-21 | 142 | 145 | 2024-11 | 623 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 114/9 | 2024-11-27 | 2025-03-30 | 2025-04-06 | 123 | 130 | 2024-11 | 623 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 114/7 | 2024-11-28 | 2025-04-18 | 2025-04-22 | 141 | 145 | 2024-11 | 622 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 110/2 | 2024-11-29 | 2025-03-19 | 2025-03-22 | 110 | 113 | 2024-11 | 621 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 110/7 | 2024-11-29 | 2025-02-17 | 2025-02-20 | 80 | 83 | 2024-11 | 621 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 113/3 | 2024-11-29 | 2025-04-01 | 2025-04-10 | 123 | 132 | 2024-11 | 621 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 105/0 | 2024-11-30 | 2025-09-21 | 2025-09-28 | 295 | 302 | 2024-11 | 620 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 108/2 | 2024-11-30 | 2025-04-12 | 2025-04-15 | 133 | 136 | 2024-11 | 620 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 109/3 | 2024-11-30 | 2025-03-06 | 2025-03-11 | 96 | 101 | 2024-11 | 620 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 114/6 | 2024-11-30 | 2025-03-07 | 2025-03-29 | 97 | 119 | 2024-11 | 620 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 116/2 | 2024-12-01 | 2025-05-02 | 2025-05-08 | 152 | 158 | 2024-12 | 619 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 104/2 | 2024-12-03 | 2025-04-22 | 2025-04-25 | 140 | 143 | 2024-12 | 617 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 113/5 | 2024-12-05 | 2025-03-29 | 2025-03-31 | 114 | 116 | 2024-12 | 615 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 114/3 | 2024-12-07 | 2025-04-17 | 2025-04-24 | 131 | 138 | 2024-12 | 613 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 114/5 | 2024-12-07 | 2025-03-30 | 2025-04-16 | 113 | 130 | 2024-12 | 613 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 111/3 | 2024-12-08 | 2025-05-06 | 2025-05-11 | 149 | 154 | 2024-12 | 612 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 113/4 | 2024-12-09 | 2025-03-12 | 2025-03-28 | 93 | 109 | 2024-12 | 611 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 127/3 | 2024-12-10 | 2025-05-27 | 2025-05-31 | 168 | 172 | 2024-12 | 610 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 113/6 | 2024-12-12 | 2025-04-24 | 2025-05-02 | 133 | 141 | 2024-12 | 608 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 108/1 | 2024-12-13 | 2025-04-15 | 2025-04-18 | 123 | 126 | 2024-12 | 607 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 102/0 | 2024-12-14 | 2025-10-13 | 2025-10-26 | 303 | 316 | 2024-12 | 606 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 114/2 | 2024-12-14 | 2025-04-12 | 2025-04-18 | 119 | 125 | 2024-12 | 606 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 127/2 | 2024-12-15 | 2025-05-08 | 2025-05-12 | 144 | 148 | 2024-12 | 605 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 111/4 | 2024-12-16 | 2025-04-30 | 2025-05-06 | 135 | 141 | 2024-12 | 604 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 126/0 | 2024-12-16 | 2025-08-17 | 2025-08-26 | 244 | 253 | 2024-12 | 604 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 110/0 | 2024-12-17 | 2026-01-20 | 2026-01-31 | 399 | 410 | 2024-12 | 603 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 126/4 | 2024-12-17 | 2025-05-17 | 2025-05-22 | 151 | 156 | 2024-12 | 603 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 108/3 | 2024-12-19 | 2025-04-08 | 2025-04-11 | 110 | 113 | 2024-12 | 601 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 114/0 | 2024-12-19 | 2025-10-22 | 2025-10-31 | 307 | 316 | 2024-12 | 601 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 147A/4 | 2024-12-19 | 2025-06-01 | 2025-06-06 | 164 | 169 | 2024-12 | 601 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 127/1 | 2024-12-20 | 2025-05-13 | 2025-05-16 | 144 | 147 | 2024-12 | 600 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 150/3 | 2024-12-21 | 2025-06-11 | 2025-06-16 | 172 | 177 | 2024-12 | 599 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 152A/3 | 2024-12-22 | 2025-05-14 | 2025-05-16 | 143 | 145 | 2024-12 | 598 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 147A/5 | 2024-12-24 | 2025-09-01 | 2025-09-19 | 251 | 269 | 2024-12 | 596 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 150/4 | 2024-12-24 | 2025-06-27 | 2025-06-30 | 185 | 188 | 2024-12 | 596 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 116/1 | 2024-12-26 | 2025-05-08 | 2025-05-15 | 133 | 140 | 2024-12 | 594 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 152/2 | 2024-12-26 | 2025-12-28 | 2026-01-03 | 367 | 373 | 2024-12 | 594 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 147A/1 | 2024-12-27 | 2025-09-20 | 2025-09-29 | 267 | 276 | 2024-12 | 593 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 152A/4 | 2024-12-27 | 2025-05-27 | 2025-05-30 | 151 | 154 | 2024-12 | 593 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 150/5 | 2024-12-28 | 2025-06-06 | 2025-06-10 | 160 | 164 | 2024-12 | 592 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 127/0 | 2024-12-29 | 2025-08-01 | 2025-08-16 | 215 | 230 | 2024-12 | 591 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 152A/9 | 2024-12-29 | 2025-06-17 | 2025-06-25 | 170 | 178 | 2024-12 | 591 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 152/1 | 2024-12-30 | 2025-12-17 | 2025-12-27 | 352 | 362 | 2024-12 | 590 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 109/0 | 2024-12-31 | 2025-11-06 | 2025-11-18 | 310 | 322 | 2024-12 | 589 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 114/1 | 2024-12-31 | 2025-04-25 | 2025-04-30 | 115 | 120 | 2024-12 | 589 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 147A/2 | 2024-12-31 | 2025-06-07 | 2025-06-10 | 158 | 161 | 2024-12 | 589 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 152A/5 | 2025-01-02 | 2025-10-05 | 2025-10-18 | 276 | 289 | 2025-01 | 587 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 111/0 | 2025-01-04 | 2025-08-18 | 2025-09-09 | 226 | 248 | 2025-01 | 585 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 147/1 | 2025-01-05 | 2025-06-26 | 2025-07-12 | 172 | 188 | 2025-01 | 584 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 152A/7 | 2025-01-05 | 2025-12-25 | 2025-12-31 | 354 | 360 | 2025-01 | 584 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 152A/1 | 2025-01-10 | 2025-05-17 | 2025-05-21 | 127 | 131 | 2025-01 | 579 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 120/1 | 2025-01-12 | 2025-04-27 | 2025-05-02 | 105 | 110 | 2025-01 | 577 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 150/1 | 2025-01-12 | 2025-07-07 | 2025-07-17 | 176 | 186 | 2025-01 | 577 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 103/7 | 2025-01-15 | 2025-07-15 | 2025-07-24 | 181 | 190 | 2025-01 | 574 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 155/5 | 2025-01-15 | 2025-05-28 | 2025-05-31 | 133 | 136 | 2025-01 | 574 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 144A/1 | 2025-01-16 | 2025-09-12 | 2025-09-22 | 239 | 249 | 2025-01 | 573 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 152A/8 | 2025-01-16 | 2025-05-31 | 2025-06-05 | 135 | 140 | 2025-01 | 573 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 131/0 | 2025-01-17 | 2025-09-10 | 2025-09-25 | 236 | 251 | 2025-01 | 572 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 152A/0 | 2025-01-17 | 2025-12-12 | 2025-12-19 | 329 | 336 | 2025-01 | 572 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 126/2 | 2025-01-18 | 2025-05-23 | 2025-05-26 | 125 | 128 | 2025-01 | 571 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 144A/3 | 2025-01-19 | 2025-10-19 | 2025-11-02 | 273 | 287 | 2025-01 | 570 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 126/3 | 2025-01-20 | 2025-11-10 | 2025-11-16 | 294 | 300 | 2025-01 | 569 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 152A/11 | 2025-01-21 | 2026-04-01 | 2026-04-07 | 435 | 441 | 2025-01 | 568 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 155/3 | 2025-01-21 | 2025-05-23 | 2025-05-27 | 122 | 126 | 2025-01 | 568 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 150/2 | 2025-01-22 | 2025-07-01 | 2025-07-06 | 160 | 165 | 2025-01 | 567 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 152A/6 | 2025-01-23 | 2025-12-20 | 2025-12-24 | 331 | 335 | 2025-01 | 566 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 120/3 | 2025-01-24 | 2025-05-02 | 2025-05-07 | 98 | 103 | 2025-01 | 565 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 152/3 | 2025-01-25 | 2026-04-06 | 2026-04-17 | 436 | 447 | 2025-01 | 564 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 152A/10 | 2025-01-25 | 2026-04-08 | 2026-04-13 | 438 | 443 | 2025-01 | 564 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 112/0 | 2025-01-27 | 2025-10-01 | 2025-10-26 | 247 | 272 | 2025-01 | 562 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 152A/2 | 2025-01-28 | 2025-05-22 | 2025-05-26 | 114 | 118 | 2025-01 | 561 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 120/2 | 2025-01-30 | 2025-04-22 | 2025-04-27 | 82 | 87 | 2025-01 | 559 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 154/1 | 2025-01-30 | 2025-07-01 | 2025-07-07 | 152 | 158 | 2025-01 | 559 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 128/0 | 2025-01-31 | 2025-10-01 | 2025-10-12 | 243 | 254 | 2025-01 | 558 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 130/1 | 2025-01-31 | 2025-09-26 | 2025-09-30 | 238 | 242 | 2025-01 | 558 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 148/0 | 2025-01-31 | 2025-12-10 | 2025-12-31 | 313 | 334 | 2025-01 | 558 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 154/2 | 2025-02-04 | 2025-06-24 | 2025-06-30 | 140 | 146 | 2025-02 | 554 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 140/1 | 2025-02-05 | 2025-10-10 | 2025-10-18 | 247 | 255 | 2025-02 | 553 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 156/4 | 2025-02-05 | 2025-06-16 | 2025-06-22 | 131 | 137 | 2025-02 | 553 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 129A/3 | 2025-02-06 | 2025-05-19 | 2025-06-07 | 102 | 121 | 2025-02 | 552 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 104/0 | 2025-02-07 | 2025-08-23 | 2025-09-05 | 197 | 210 | 2025-02 | 551 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 154/5 | 2025-02-08 | 2025-05-16 | 2025-05-22 | 97 | 103 | 2025-02 | 550 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 130/2 | 2025-02-09 | 2025-11-23 | 2025-11-28 | 287 | 292 | 2025-02 | 549 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 129A/2 | 2025-02-10 | 2025-11-12 | 2025-11-22 | 275 | 285 | 2025-02 | 548 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 155/4 | 2025-02-10 | 2025-06-01 | 2025-06-07 | 111 | 117 | 2025-02 | 548 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 129A/1 | 2025-02-11 | 2025-06-08 | 2025-06-23 | 117 | 132 | 2025-02 | 547 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 156/1 | 2025-02-12 | 2025-06-08 | 2025-06-15 | 116 | 123 | 2025-02 | 546 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 148A/0 | 2025-02-13 | 2025-10-25 | 2025-11-10 | 254 | 270 | 2025-02 | 545 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 130/0 | 2025-02-14 | 2025-08-27 | 2025-09-09 | 194 | 207 | 2025-02 | 544 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 160/3 | 2025-02-15 | 2025-06-08 | 2025-07-31 | 113 | 166 | 2025-02 | 543 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 159/3 | 2025-02-16 | 2026-03-19 | 2026-03-24 | 396 | 401 | 2025-02 | 542 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 109/4 | 2025-02-17 | 2025-03-11 | 2025-03-15 | 22 | 26 | 2025-02 | 541 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 135/1 | 2025-02-17 | 2025-11-03 | 2025-11-10 | 259 | 266 | 2025-02 | 541 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 110A/0 | 2025-02-20 | 2025-09-20 | 2025-09-30 | 212 | 222 | 2025-02 | 538 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 135/2 | 2025-02-21 | 2025-09-08 | 2025-09-18 | 199 | 209 | 2025-02 | 537 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 135/3 | 2025-02-22 | 2026-02-25 | 2026-03-12 | 368 | 383 | 2025-02 | 536 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 156/3 | 2025-02-22 | 2026-02-18 | 2026-02-24 | 361 | 367 | 2025-02 | 536 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 155/1 | 2025-02-24 | 2026-04-23 | 2026-04-29 | 423 | 429 | 2025-02 | 534 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 159/0 | 2025-02-24 | 2025-10-19 | 2025-11-02 | 237 | 251 | 2025-02 | 534 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 136/1 | 2025-02-25 | 2025-08-25 | 2025-09-11 | 181 | 198 | 2025-02 | 533 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 160/0 | 2025-02-25 | 2025-09-26 | 2025-10-12 | 213 | 229 | 2025-02 | 533 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 164/5 | 2025-02-26 | 2025-11-09 | 2025-12-12 | 256 | 289 | 2025-02 | 532 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 118/0 | 2025-02-27 | 2025-12-11 | 2025-12-21 | 287 | 297 | 2025-02 | 531 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 136/5 | 2025-02-27 | 2025-11-11 | 2025-11-22 | 257 | 268 | 2025-02 | 531 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 161/4 | 2025-02-27 | 2025-05-08 | 2025-05-27 | 70 | 89 | 2025-02 | 531 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 154/3 | 2025-02-28 | 2025-07-08 | 2025-07-14 | 130 | 136 | 2025-02 | 530 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 155/2 | 2025-02-28 | 2026-04-30 | 2026-05-06 | 426 | 432 | 2025-02 | 530 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 160/2 | 2025-02-28 | 2025-09-26 | 2025-10-07 | 210 | 221 | 2025-02 | 530 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 160/1 | 2025-03-04 | 2025-10-08 | 2025-10-16 | 218 | 226 | 2025-03 | 526 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 135/0 | 2025-03-05 | 2025-08-25 | 2025-09-07 | 173 | 186 | 2025-03 | 525 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 161/2 | 2025-03-06 | 2025-09-10 | 2025-09-25 | 188 | 203 | 2025-03 | 524 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 164/6 | 2025-03-07 | 2025-12-12 | 2025-12-17 | 280 | 285 | 2025-03 | 523 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 160/4 | 2025-03-08 | 2025-05-24 | 2025-06-07 | 77 | 91 | 2025-03 | 522 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 161/5 | 2025-03-11 | 2025-12-31 | 2026-01-08 | 295 | 303 | 2025-03 | 519 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 140/0 | 2025-03-12 | 2025-12-01 | 2025-12-24 | 264 | 287 | 2025-03 | 518 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 164/4 | 2025-03-16 | 2025-12-18 | 2025-12-24 | 277 | 283 | 2025-03 | 514 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 159/1 | 2025-03-19 | 2025-04-22 | 2025-05-08 | 34 | 50 | 2025-03 | 511 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 144A/0 | 2025-03-22 | 2025-09-23 | 2025-10-10 | 185 | 202 | 2025-03 | 508 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 161/1 | 2025-03-26 | 2026-03-25 | 2026-04-04 | 364 | 374 | 2025-03 | 504 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 144A/2 | 2025-03-28 | 2026-03-22 | 2026-04-05 | 359 | 373 | 2025-03 | 502 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 166/4 | 2025-03-28 | 2025-12-04 | 2025-12-09 | 251 | 256 | 2025-03 | 502 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 170/3 | 2025-03-29 | 2025-12-28 | 2026-01-03 | 274 | 280 | 2025-03 | 501 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 170/2 | 2025-03-30 | 2026-05-02 | 2026-05-08 | 398 | 404 | 2025-03 | 500 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 147/0 | 2025-03-31 | 2026-02-26 | 2026-03-10 | 332 | 344 | 2025-03 | 499 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 160/5 | 2025-03-31 | 2025-05-08 | 2025-05-23 | 38 | 53 | 2025-03 | 499 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 161/3 | 2025-03-31 | 2025-05-28 | 2025-06-23 | 58 | 84 | 2025-03 | 499 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 164/2 | 2025-03-31 | 2026-01-28 | 2026-01-31 | 303 | 306 | 2025-03 | 499 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 166/5 | 2025-03-31 | 2025-11-30 | 2025-12-03 | 244 | 247 | 2025-03 | 499 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 170/8 | 2025-03-31 | 2025-11-07 | 2025-11-13 | 221 | 227 | 2025-03 | 499 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 115/0 | 2025-04-03 | 2025-09-24 | 2025-10-04 | 174 | 184 | 2025-04 | 496 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 116/0 | 2025-04-07 | 2025-10-05 | 2025-10-13 | 181 | 189 | 2025-04 | 492 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 169/3 | 2025-04-07 | 2025-09-22 | 2025-09-29 | 168 | 175 | 2025-04 | 492 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 170/9 | 2025-04-07 | 2026-04-01 | 2026-04-03 | 359 | 361 | 2025-04 | 492 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 164/7 | 2025-04-08 | 2025-12-04 | 2025-12-11 | 240 | 247 | 2025-04 | 491 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 166/8 | 2025-04-08 | 2025-11-14 | 2025-11-18 | 220 | 224 | 2025-04 | 491 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 165/6 | 2025-04-09 | 2025-11-03 | 2025-11-07 | 208 | 212 | 2025-04 | 490 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 147A/0 | 2025-04-10 | 2025-10-13 | 2025-10-24 | 186 | 197 | 2025-04 | 489 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 147A/3 | 2025-04-10 | 2025-06-11 | 2025-06-15 | 62 | 66 | 2025-04 | 489 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 172/2 | 2025-04-10 | 2025-11-29 | 2025-12-06 | 233 | 240 | 2025-04 | 489 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 170/1 | 2025-04-11 | 2025-11-21 | 2025-11-27 | 224 | 230 | 2025-04 | 488 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 120/0 | 2025-04-12 | 2025-09-08 | 2025-09-18 | 149 | 159 | 2025-04 | 487 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 148/1 | 2025-04-12 | 2025-09-30 | 2025-10-12 | 171 | 183 | 2025-04 | 487 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 170/10 | 2025-04-12 | 2026-04-04 | 2026-04-08 | 357 | 361 | 2025-04 | 487 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 173/3 | 2025-04-12 | 2025-12-31 | 2026-01-08 | 263 | 271 | 2025-04 | 487 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 165/4 | 2025-04-13 | 2026-01-09 | 2026-01-18 | 271 | 280 | 2025-04 | 486 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 166/6 | 2025-04-13 | 2025-11-25 | 2025-11-29 | 226 | 230 | 2025-04 | 486 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 169/2 | 2025-04-14 | 2025-10-22 | 2025-10-30 | 191 | 199 | 2025-04 | 485 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 119/0 | 2025-04-15 | 2025-08-25 | 2025-09-07 | 132 | 145 | 2025-04 | 484 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 164/8 | 2025-04-15 | 2025-11-25 | 2025-12-03 | 224 | 232 | 2025-04 | 484 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 173/4 | 2025-04-16 | 2026-01-02 | 2026-01-14 | 261 | 273 | 2025-04 | 483 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 170/7 | 2025-04-17 | 2025-11-14 | 2025-11-20 | 211 | 217 | 2025-04 | 482 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 165/3 | 2025-04-18 | 2026-04-11 | 2026-04-17 | 358 | 364 | 2025-04 | 481 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 172/3 | 2025-04-18 | 2025-11-18 | 2025-11-28 | 214 | 224 | 2025-04 | 481 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 166/3 | 2025-04-20 | 2026-04-05 | 2026-04-10 | 350 | 355 | 2025-04 | 479 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 166/9 | 2025-04-20 | 2025-11-04 | 2025-11-13 | 198 | 207 | 2025-04 | 479 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 173/2 | 2025-04-20 | 2025-12-13 | 2025-12-21 | 237 | 245 | 2025-04 | 479 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 103/4 | 2025-04-22 | 2025-10-27 | 2025-11-05 | 188 | 197 | 2025-04 | 477 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 106/0 | 2025-04-22 | 2025-08-04 | 2025-08-12 | 104 | 112 | 2025-04 | 477 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 132/0 | 2025-04-22 | 2025-12-17 | 2025-12-30 | 239 | 252 | 2025-04 | 477 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 170/5 | 2025-04-22 | 2026-04-09 | 2026-04-13 | 352 | 356 | 2025-04 | 477 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 171/1 | 2025-04-22 | 2026-04-09 | 2026-04-17 | 352 | 360 | 2025-04 | 477 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 166/0 | 2025-04-24 | 2025-11-08 | 2025-11-15 | 198 | 205 | 2025-04 | 475 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 169/1 | 2025-04-24 | 2025-10-31 | 2025-11-06 | 190 | 196 | 2025-04 | 475 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 175/4 | 2025-04-24 | 2026-04-08 | 2026-04-12 | 349 | 353 | 2025-04 | 475 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 167/4 | 2025-04-26 | 2025-09-26 | 2025-10-01 | 153 | 158 | 2025-04 | 473 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 171/2 | 2025-04-26 | 2026-03-05 | 2026-03-16 | 313 | 324 | 2025-04 | 473 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 172/1 | 2025-04-26 | 2025-12-07 | 2025-12-12 | 225 | 230 | 2025-04 | 473 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 173/1 | 2025-04-26 | 2025-10-27 | 2025-11-17 | 184 | 205 | 2025-04 | 473 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 175/3 | 2025-04-26 | 2026-04-13 | 2026-04-15 | 352 | 354 | 2025-04 | 473 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 108/0 | 2025-04-27 | 2025-08-12 | 2025-08-22 | 107 | 117 | 2025-04 | 472 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 161/0 | 2025-04-28 | 2025-10-16 | 2025-11-08 | 171 | 194 | 2025-04 | 471 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 166/2 | 2025-04-28 | 2026-02-14 | 2026-02-20 | 292 | 298 | 2025-04 | 471 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 170/6 | 2025-04-28 | 2026-03-26 | 2026-03-30 | 332 | 336 | 2025-04 | 471 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 165/5 | 2025-04-29 | 2026-01-19 | 2026-01-27 | 265 | 273 | 2025-04 | 470 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 165/1 | 2025-04-30 | 2026-03-10 | 2026-03-18 | 314 | 322 | 2025-04 | 469 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 167/5 | 2025-04-30 | 2025-09-14 | 2025-09-25 | 137 | 148 | 2025-04 | 469 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 176/1 | 2025-04-30 | 2026-03-22 | 2026-03-25 | 326 | 329 | 2025-04 | 469 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 103/5A | 2025-05-03 | 2025-08-21 | 2025-09-09 | 110 | 129 | 2025-05 | 466 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 136/2 | 2025-05-03 | 2025-11-23 | 2025-11-30 | 204 | 211 | 2025-05 | 466 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 167/0 | 2025-05-03 | 2025-10-16 | 2025-10-25 | 166 | 175 | 2025-05 | 466 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 159/2 | 2025-05-04 | 2025-09-13 | 2025-09-25 | 132 | 144 | 2025-05 | 465 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 169/4 | 2025-05-04 | 2025-09-30 | 2025-10-08 | 149 | 157 | 2025-05 | 465 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 171/9 | 2025-05-04 | 2026-01-15 | 2026-01-25 | 256 | 266 | 2025-05 | 465 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 176/0 | 2025-05-04 | 2026-03-15 | 2026-03-21 | 315 | 321 | 2025-05 | 465 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 103/5A1 | 2025-05-05 | 2025-08-04 | 2025-08-08 | 91 | 95 | 2025-05 | 464 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 176/2 | 2025-05-06 | 2026-04-16 | 2026-04-25 | 345 | 354 | 2025-05 | 463 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 103/3 | 2025-05-08 | 2025-09-10 | 2025-09-16 | 125 | 131 | 2025-05 | 461 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 178/1 | 2025-05-08 | 2026-02-03 | 2026-02-10 | 271 | 278 | 2025-05 | 461 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 158/3 | 2025-05-09 | 2025-08-25 | 2025-09-12 | 108 | 126 | 2025-05 | 460 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 167/1 | 2025-05-09 | 2025-10-26 | 2025-11-03 | 170 | 178 | 2025-05 | 460 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 174A/3 | 2025-05-10 | 2025-12-01 | 2025-12-08 | 205 | 212 | 2025-05 | 459 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 176/3 | 2025-05-10 | 2026-04-24 | 2026-04-26 | 349 | 351 | 2025-05 | 459 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 103/1 | 2025-05-11 | 2025-09-18 | 2025-09-24 | 130 | 136 | 2025-05 | 458 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 169/5 | 2025-05-11 | 2025-10-09 | 2025-10-16 | 151 | 158 | 2025-05 | 458 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 103/2 | 2025-05-13 | 2025-09-25 | 2025-09-30 | 135 | 140 | 2025-05 | 456 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 141/0 | 2025-05-13 | 2026-01-18 | 2026-01-30 | 250 | 262 | 2025-05 | 456 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 166/1 | 2025-05-13 | 2025-09-14 | 2025-09-28 | 124 | 138 | 2025-05 | 456 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 158/2 | 2025-05-16 | 2025-10-13 | 2025-10-18 | 150 | 155 | 2025-05 | 453 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 170/0 | 2025-05-16 | 2025-11-28 | 2025-12-08 | 196 | 206 | 2025-05 | 453 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 171/8 | 2025-05-17 | 2026-04-14 | 2026-04-19 | 332 | 337 | 2025-05 | 452 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 177/1 | 2025-05-17 | 2025-12-21 | 2025-12-27 | 218 | 224 | 2025-05 | 452 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 103/6A | 2025-05-18 | 2025-08-09 | 2025-08-21 | 83 | 95 | 2025-05 | 451 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 178/0 | 2025-05-18 | 2026-01-21 | 2026-02-03 | 248 | 261 | 2025-05 | 451 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 142/0 | 2025-05-20 | 2026-01-02 | 2026-01-23 | 227 | 248 | 2025-05 | 449 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 171/4 | 2025-05-21 | 2026-03-17 | 2026-03-22 | 300 | 305 | 2025-05 | 448 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 172/4 | 2025-05-21 | 2025-12-09 | 2025-12-31 | 202 | 224 | 2025-05 | 448 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 177/2 | 2025-05-21 | 2026-01-19 | 2026-01-24 | 243 | 248 | 2025-05 | 448 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 103/0 | 2025-05-22 | 2025-09-10 | 2025-09-20 | 111 | 121 | 2025-05 | 447 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 172/6 | 2025-05-23 | 2025-10-27 | 2025-11-24 | 157 | 185 | 2025-05 | 446 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 174A/4 | 2025-05-23 | 2026-04-26 | 2026-04-30 | 338 | 342 | 2025-05 | 446 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 177/3 | 2025-05-23 | 2025-12-28 | 2026-01-02 | 219 | 224 | 2025-05 | 446 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 103/8 | 2025-05-24 | 2025-07-25 | 2025-07-31 | 62 | 68 | 2025-05 | 445 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 169/6 | 2025-05-25 | 2025-09-11 | 2025-09-21 | 109 | 119 | 2025-05 | 444 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 177/8 | 2025-05-25 | 2026-03-09 | 2026-03-14 | 288 | 293 | 2025-05 | 444 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 167/2 | 2025-05-27 | 2025-10-02 | 2025-10-10 | 128 | 136 | 2025-05 | 442 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 177/4 | 2025-05-27 | 2026-01-03 | 2026-01-11 | 221 | 229 | 2025-05 | 442 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 167/3 | 2025-05-29 | 2025-10-10 | 2025-10-15 | 134 | 139 | 2025-05 | 440 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 174A/5 | 2025-05-29 | 2026-02-08 | 2026-02-15 | 255 | 262 | 2025-05 | 440 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 177/5 | 2025-05-29 | 2026-01-12 | 2026-01-18 | 228 | 234 | 2025-05 | 440 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 172/5 | 2025-05-30 | 2026-02-24 | 2026-03-04 | 270 | 278 | 2025-05 | 439 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 178/3 | 2025-05-30 | 2025-12-03 | 2025-12-11 | 187 | 195 | 2025-05 | 439 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 101/0 | 2025-05-31 | 2025-10-01 | 2025-10-12 | 123 | 134 | 2025-05 | 438 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 150/0 | 2025-05-31 | 2025-07-18 | 2025-07-28 | 48 | 58 | 2025-05 | 438 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 177/6 | 2025-05-31 | 2026-04-01 | 2026-04-03 | 305 | 307 | 2025-05 | 438 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 121/0 | 2025-06-02 | 2025-10-14 | 2025-10-21 | 134 | 141 | 2025-06 | 436 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 171/7 | 2025-06-03 | 2026-04-20 | 2026-04-24 | 321 | 325 | 2025-06 | 435 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 177/7 | 2025-06-03 | 2026-03-22 | 2026-03-30 | 292 | 300 | 2025-06 | 435 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 174A/1 | 2025-06-04 | 2025-12-10 | 2025-12-18 | 189 | 197 | 2025-06 | 434 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 173/0 | 2025-06-05 | 2025-12-22 | 2025-12-30 | 200 | 208 | 2025-06 | 433 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 110/4 | 2025-06-07 | 2025-08-12 | 2025-08-30 | 66 | 84 | 2025-06 | 431 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 171/0 | 2025-06-08 | 2026-03-30 | 2026-04-09 | 295 | 305 | 2025-06 | 430 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 171/3 | 2025-06-08 | 2026-03-22 | 2026-03-29 | 287 | 294 | 2025-06 | 430 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 172/0 | 2025-06-09 | 2026-01-27 | 2026-02-07 | 232 | 243 | 2025-06 | 429 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 152/0 | 2025-06-11 | 2025-11-29 | 2025-12-11 | 171 | 183 | 2025-06 | 427 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 152A/12 | 2025-06-13 | 2026-03-26 | 2026-03-31 | 286 | 291 | 2025-06 | 425 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 174A/0 | 2025-06-13 | 2025-11-10 | 2025-11-23 | 150 | 163 | 2025-06 | 425 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 174A/2 | 2025-06-28 | 2025-11-24 | 2025-11-30 | 149 | 155 | 2025-06 | 410 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 151/0 | 2025-06-29 | 2026-01-04 | 2026-01-17 | 189 | 202 | 2025-06 | 409 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 171/6 | 2025-06-29 | 2026-04-16 | 2026-04-24 | 291 | 299 | 2025-06 | 409 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 156/0 | 2025-07-15 | 2025-09-12 | 2025-10-04 | 59 | 81 | 2025-07 | 393 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 169/7 | 2025-07-17 | 2025-10-16 | 2025-10-21 | 91 | 96 | 2025-07 | 391 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 179/7 | 2025-08-29 | 2026-04-04 | 2026-04-07 | 218 | 221 | 2025-08 | 348 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 178/4 | 2025-09-04 | 2025-12-12 | 2025-12-19 | 99 | 106 | 2025-09 | 342 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 178/5 | 2025-09-12 | 2025-12-03 | 2025-12-11 | 82 | 90 | 2025-09 | 334 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 179/6 | 2025-09-12 | 2026-01-12 | 2026-01-20 | 122 | 130 | 2025-09 | 334 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 145/0 | 2025-09-14 | 2025-11-11 | 2025-12-09 | 58 | 86 | 2025-09 | 332 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 114/4 | 2025-09-19 | 2025-11-17 | 2025-11-24 | 59 | 66 | 2025-09 | 327 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 179/1 | 2025-09-23 | 2025-12-29 | 2026-01-06 | 97 | 105 | 2025-09 | 323 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 179/4 | 2025-09-26 | 2025-12-27 | 2025-12-31 | 92 | 96 | 2025-09 | 320 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 149B/3 | 2025-09-27 | 2025-10-27 | 2025-11-11 | 30 | 45 | 2025-09 | 319 | TRUE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 179/2 | 2025-09-29 | 2026-01-02 | 2026-01-06 | 95 | 99 | 2025-09 | 317 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 154/4 | 2025-09-30 | 2025-12-06 | 2025-12-16 | 67 | 77 | 2025-09 | 316 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 126/1 | 2025-10-05 | 2025-11-01 | 2025-11-09 | 27 | 35 | 2025-10 | 311 | TRUE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 149B/1 | 2025-10-09 | 2026-02-06 | 2026-02-26 | 120 | 140 | 2025-10 | 307 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 149B/2 | 2025-10-15 | 2025-11-12 | 2025-11-25 | 28 | 41 | 2025-10 | 301 | TRUE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 100/0 | 2025-10-16 | 2025-11-19 | 2025-11-29 | 34 | 44 | 2025-10 | 300 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 178/2 | 2025-10-16 | 2026-02-15 | 2026-02-22 | 122 | 129 | 2025-10 | 300 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 149B/4 | 2025-10-17 | 2025-11-26 | 2025-12-05 | 40 | 49 | 2025-10 | 299 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 155/0 | 2025-10-17 | 2026-04-14 | 2026-04-22 | 179 | 187 | 2025-10 | 299 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 99/8 | 2025-10-17 | 2025-11-30 | 2025-12-04 | 44 | 48 | 2025-10 | 299 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 165/0 | 2025-10-22 | 2025-11-16 | 2025-11-24 | 25 | 33 | 2025-10 | 294 | TRUE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 168/0 | 2025-10-25 | 2025-12-09 | 2025-12-19 | 45 | 55 | 2025-10 | 291 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 99/6 | 2025-10-25 | 2025-12-13 | 2025-12-17 | 49 | 53 | 2025-10 | 291 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 180/0 | 2025-10-30 | 2026-05-02 | 2026-05-13 | 184 | 195 | 2025-10 | 286 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 99/4 | 2025-11-01 | 2025-12-10 | 2025-12-13 | 39 | 42 | 2025-11 | 284 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 99/5 | 2025-11-03 | 2025-12-05 | 2025-12-09 | 32 | 36 | 2025-11 | 282 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 99/3 | 2025-11-06 | 2025-12-18 | 2025-12-22 | 42 | 46 | 2025-11 | 279 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 165/2 | 2025-11-07 | 2026-02-23 | 2026-03-03 | 108 | 116 | 2025-11 | 278 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 99/2 | 2025-11-09 | 2026-01-02 | 2026-01-05 | 54 | 57 | 2025-11 | 276 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 181/6 | 2025-11-10 | 2025-12-12 | 2025-12-20 | 32 | 40 | 2025-11 | 275 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 99/1 | 2025-11-11 | 2025-12-27 | 2025-12-31 | 46 | 50 | 2025-11 | 274 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 103/5 | 2025-11-14 | 2025-11-25 | 2025-12-02 | 11 | 18 | 2025-11 | 271 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 99/7 | 2025-11-16 | 2025-12-22 | 2025-12-26 | 36 | 40 | 2025-11 | 269 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 181/1 | 2025-11-18 | 2025-12-21 | 2025-12-26 | 33 | 38 | 2025-11 | 267 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 103/9 | 2025-11-19 | 2025-12-03 | 2025-12-10 | 14 | 21 | 2025-11 | 266 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 169/0 | 2025-11-20 | 2025-12-10 | 2025-12-18 | 20 | 28 | 2025-11 | 265 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 122/0 | 2025-11-26 | 2026-01-29 | 2026-02-08 | 64 | 74 | 2025-11 | 259 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 175/2 | 2025-11-26 | 2026-01-10 | 2026-01-24 | 45 | 59 | 2025-11 | 259 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 171/10 | 2025-11-27 | 2026-05-29 | 2026-06-05 | 183 | 190 | 2025-11 | 258 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 181/4 | 2025-11-27 | 2026-01-07 | 2026-01-11 | 41 | 45 | 2025-11 | 258 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 138/0 | 2025-11-29 |  |  |  |  | 2025-11 | 256 | FALSE | FALSE | No | No |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 123/0 | 2025-12-03 | 2025-12-22 | 2026-01-04 | 19 | 32 | 2025-12 | 252 | TRUE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 181/5 | 2025-12-06 | 2026-01-07 | 2026-01-11 | 32 | 36 | 2025-12 | 249 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 123/1 | 2025-12-08 | 2026-01-05 | 2026-01-14 | 28 | 37 | 2025-12 | 247 | TRUE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 169/9 | 2025-12-08 | 2025-12-20 | 2025-12-27 | 12 | 19 | 2025-12 | 247 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 179/5 | 2025-12-10 | 2025-12-21 | 2025-12-28 | 11 | 18 | 2025-12 | 245 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 123/3 | 2025-12-12 | 2026-01-15 | 2026-01-20 | 34 | 39 | 2025-12 | 243 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 153/0 | 2025-12-13 | 2026-01-11 | 2026-01-18 | 29 | 36 | 2025-12 | 242 | TRUE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 154/0 | 2025-12-14 | 2026-01-02 | 2026-01-10 | 19 | 27 | 2025-12 | 241 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 125/1 | 2025-12-15 | 2026-01-12 | 2026-01-20 | 28 | 36 | 2025-12 | 240 | TRUE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 175/1 | 2025-12-15 | 2026-02-01 | 2026-02-16 | 48 | 63 | 2025-12 | 240 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 123/2 | 2025-12-22 | 2026-01-21 | 2026-01-28 | 30 | 37 | 2025-12 | 233 | TRUE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 129A/0 | 2025-12-23 | 2025-12-31 | 2026-01-11 | 8 | 19 | 2025-12 | 232 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 181/0 | 2025-12-24 | 2026-01-12 | 2026-01-31 | 19 | 38 | 2025-12 | 231 | TRUE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 113/0 | 2025-12-28 | 2026-01-06 | 2026-01-19 | 9 | 22 | 2025-12 | 227 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 175/0 | 2025-12-30 | 2026-01-09 | 2026-01-31 | 10 | 32 | 2025-12 | 225 | TRUE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 149B/0 | 2025-12-31 |  |  |  |  | 2025-12 | 224 | FALSE | FALSE | No | No |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 158/0 | 2025-12-31 |  |  |  |  | 2025-12 | 224 | FALSE | FALSE | No | No |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 158/1 | 2025-12-31 | 2026-01-11 | 2026-01-19 | 11 | 19 | 2025-12 | 224 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 125/0 | 2026-01-04 | 2026-01-21 | 2026-01-31 | 17 | 27 | 2026-01 | 220 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 162/0 | 2026-01-07 | 2026-04-24 | 2026-05-07 | 107 | 120 | 2026-01 | 217 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 162/2 | 2026-01-08 | 2026-01-20 | 2026-01-27 | 12 | 19 | 2026-01 | 216 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 124/0 | 2026-01-09 | 2026-02-01 | 2026-02-12 | 23 | 34 | 2026-01 | 215 | TRUE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 179/9 | 2026-01-11 | 2026-02-01 | 2026-02-09 | 21 | 29 | 2026-01 | 213 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 149/0 | 2026-01-13 | 2026-01-19 | 2026-01-31 | 6 | 18 | 2026-01 | 211 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 149/2 | 2026-01-16 | 2026-01-24 | 2026-02-05 | 8 | 20 | 2026-01 | 208 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 149/1 | 2026-01-18 | 2026-02-01 | 2026-02-09 | 14 | 22 | 2026-01 | 206 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 164/0 | 2026-01-19 | 2026-02-16 | 2026-03-10 | 28 | 50 | 2026-01 | 205 | TRUE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 174B/0 | 2026-01-22 | 2026-06-03 | 2026-06-10 | 132 | 139 | 2026-01 | 202 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 163/0 | 2026-01-23 | 2026-02-06 | 2026-02-22 | 14 | 30 | 2026-01 | 201 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 162/1 | 2026-01-24 | 2026-01-28 | 2026-02-05 | 4 | 12 | 2026-01 | 200 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 146/1 | 2026-01-25 | 2026-01-31 | 2026-02-13 | 6 | 19 | 2026-01 | 199 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 164/1 | 2026-01-25 | 2026-02-01 | 2026-02-11 | 7 | 17 | 2026-01 | 199 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 182/0 | 2026-01-25 | 2026-05-14 | 2026-05-25 | 109 | 120 | 2026-01 | 199 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 148B/1 | 2026-01-29 | 2026-02-01 | 2026-02-11 | 3 | 13 | 2026-01 | 195 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 149A/0 | 2026-01-31 | 2026-02-10 | 2026-02-23 | 10 | 23 | 2026-01 | 193 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 139/0 | 2026-02-04 | 2026-02-22 | 2026-02-28 | 18 | 24 | 2026-02 | 189 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 139/1 | 2026-02-06 | 2026-02-12 | 2026-02-21 | 6 | 15 | 2026-02 | 187 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 156/6 | 2026-02-07 | 2026-02-08 | 2026-02-17 | 1 | 10 | 2026-02 | 186 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 138/1 | 2026-02-10 | 2026-02-15 | 2026-02-24 | 5 | 14 | 2026-02 | 183 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 138/3 | 2026-02-12 | 2026-03-01 | 2026-03-07 | 17 | 23 | 2026-02 | 181 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 148B/2 | 2026-02-15 | 2026-02-24 | 2026-03-14 | 9 | 27 | 2026-02 | 178 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 146/0 | 2026-02-19 | 2026-03-11 | 2026-03-25 | 20 | 34 | 2026-02 | 174 | TRUE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 148C/0 | 2026-02-21 |  |  |  |  | 2026-02 | 172 | FALSE | FALSE | No | No |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 142/1 | 2026-02-24 | 2026-02-27 | 2026-03-14 | 3 | 18 | 2026-02 | 169 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 148B/0 | 2026-02-28 |  |  |  |  | 2026-02 | 165 | FALSE | FALSE | No | No |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 156/5 | 2026-03-03 | 2026-03-15 | 2026-03-25 | 12 | 22 | 2026-03 | 162 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 169/8 | 2026-03-08 | 2026-04-24 | 2026-04-30 | 47 | 53 | 2026-03 | 157 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 156/2 | 2026-03-10 | 2026-05-07 | 2026-05-13 | 58 | 64 | 2026-03 | 155 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 157/0 | 2026-03-10 |  |  |  |  | 2026-03 | 155 | FALSE | FALSE | No | No |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 138/2 | 2026-03-11 | 2026-03-14 | 2026-04-12 | 3 | 32 | 2026-03 | 154 | TRUE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 144/0 | 2026-03-21 |  |  |  |  | 2026-03 | 144 | FALSE | FALSE | No | No |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 171/5 | 2026-03-21 | 2026-06-06 | 2026-06-10 | 77 | 81 | 2026-03 | 144 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 143/0 | 2026-03-31 |  |  |  |  | 2026-03 | 134 | FALSE | FALSE | No | No |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 134/0 | 2026-04-09 |  |  |  |  | 2026-04 | 125 | FALSE | FALSE | No | No |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 137A/0 | 2026-04-09 | 2026-04-13 | 2026-05-06 | 4 | 27 | 2026-04 | 125 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 129/0 | 2026-04-14 |  |  |  |  | 2026-04 | 120 | FALSE | FALSE | No | No |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 133/0 | 2026-04-14 |  |  |  |  | 2026-04 | 120 | FALSE | FALSE | No | No |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 136/4 | 2026-04-15 | 2026-05-16 | 2026-06-04 | 31 | 50 | 2026-04 | 119 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 136/3 | 2026-04-18 | 2026-05-07 | 2026-05-15 | 19 | 27 | 2026-04 | 116 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 129/1 | 2026-04-23 |  |  |  |  | 2026-04 | 111 | FALSE | FALSE | No | No |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 117/0 | 2026-04-30 | 2026-05-14 | 2026-05-28 | 14 | 28 | 2026-04 | 104 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 137/0 | 2026-05-15 | 2026-06-12 | 2026-06-24 | 28 | 40 | 2026-05 | 89 | TRUE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 177/0 | 2026-05-15 | 2025-12-04 | 2025-12-19 | -162 | -147 | 2026-05 | 89 | FALSE | FALSE | Yes | Yes | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 181/2 | 2026-05-18 | 2026-05-26 | 2026-05-29 | 8 | 11 | 2026-05 | 86 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 181/3 | 2026-05-25 | 2026-05-30 | 2026-06-02 | 5 | 8 | 2026-05 | 79 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 179/0 | 2026-06-15 | 2026-06-25 | 2026-07-15 | 10 | 30 | 2026-06 | 58 | TRUE | TRUE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 182B/0 | 2026-06-20 | 2026-07-27 |  | 37 |  | 2026-06 | 53 | FALSE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 179/8 | 2026-06-23 | 2026-07-17 | 2026-07-26 | 24 | 33 | 2026-06 | 50 | TRUE | FALSE | Yes | No | exact | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 179/3 | 2026-06-30 |  |  |  |  | 2026-06 | 43 | FALSE | FALSE | No | No |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 510 | 155/1 | 2025-02-17 |  |  |  |  | 2025-02 | 541 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 155/4 | 2025-02-22 |  |  |  |  | 2025-02 | 536 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 155/3 | 2025-02-25 |  |  |  |  | 2025-02 | 533 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 155/5 | 2025-02-27 |  |  |  |  | 2025-02 | 531 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 156/0 | 2025-03-12 |  |  |  |  | 2025-03 | 518 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 156/1 | 2025-03-13 |  |  |  |  | 2025-03 | 517 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 156/3 | 2025-03-16 |  |  |  |  | 2025-03 | 514 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 156/4 | 2025-03-25 |  |  |  |  | 2025-03 | 505 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 156/2 | 2025-03-30 | 2026-06-30 | 2026-07-14 | 457 | 471 | 2025-03 | 500 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 139/1 | 2025-04-16 | 2026-05-31 | 2026-06-08 | 410 | 418 | 2025-04 | 483 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 138/0 | 2025-04-21 | 2026-06-05 | 2026-06-13 | 410 | 418 | 2025-04 | 478 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 139/5 | 2025-04-21 | 2026-05-22 | 2026-05-30 | 396 | 404 | 2025-04 | 478 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 137/0 | 2025-04-27 |  |  |  |  | 2025-04 | 472 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 139/4 | 2025-04-28 |  |  |  |  | 2025-04 | 471 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 138/1 | 2025-04-29 | 2026-06-26 | 2026-07-03 | 423 | 430 | 2025-04 | 470 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 136/0 | 2025-05-14 | 2026-05-28 | 2026-06-04 | 379 | 386 | 2025-05 | 455 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 148/5 | 2025-05-15 | 2026-05-03 | 2026-05-07 | 353 | 357 | 2025-05 | 454 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 148/4 | 2025-05-21 | 2026-02-27 | 2026-03-05 | 282 | 288 | 2025-05 | 448 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 148/2 | 2025-05-23 | 2026-02-18 | 2026-02-22 | 271 | 275 | 2025-05 | 446 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 134/0 | 2025-05-25 | 2026-02-01 | 2026-02-07 | 252 | 258 | 2025-05 | 444 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 148/7 | 2025-05-28 | 2026-05-13 | 2026-05-17 | 350 | 354 | 2025-05 | 441 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 148/6 | 2025-05-31 | 2026-05-08 | 2026-05-12 | 342 | 346 | 2025-05 | 438 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 143/1 | 2025-06-02 | 2026-01-16 | 2026-01-29 | 228 | 241 | 2025-06 | 436 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 143/2 | 2025-06-05 | 2026-06-05 | 2026-06-09 | 365 | 369 | 2025-06 | 433 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 144/0 | 2025-08-06 | 2026-05-29 | 2026-06-04 | 296 | 302 | 2025-08 | 371 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 141/0 | 2025-09-16 | 2026-01-08 | 2026-01-13 | 114 | 119 | 2025-09 | 330 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 133/2 | 2025-09-18 | 2026-07-15 | 2026-08-02 | 300 | 318 | 2025-09 | 328 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 141/1 | 2025-10-04 | 2026-01-01 | 2026-01-07 | 89 | 95 | 2025-10 | 312 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 138/2 | 2025-10-05 |  |  |  |  | 2025-10 | 311 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 140/1 | 2025-10-10 | 2026-01-14 | 2026-01-21 | 96 | 103 | 2025-10 | 306 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 145/0 | 2025-10-19 | 2026-01-22 | 2026-01-30 | 95 | 103 | 2025-10 | 297 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 139/2 | 2025-10-24 | 2026-01-05 | 2026-01-12 | 73 | 80 | 2025-10 | 292 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 140/2 | 2025-11-19 | 2026-02-08 | 2026-02-13 | 81 | 86 | 2025-11 | 266 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 135/0 | 2025-11-24 | 2026-01-13 | 2026-01-25 | 50 | 62 | 2025-11 | 261 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 145/1 | 2025-11-24 | 2026-01-30 | 2026-02-11 | 67 | 79 | 2025-11 | 261 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 138/3 | 2025-11-27 | 2026-07-04 |  | 219 |  | 2025-11 | 258 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 192/11 | 2025-11-30 | 2026-03-01 | 2026-03-09 | 91 | 99 | 2025-11 | 255 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 141/2 | 2025-12-07 | 2026-03-08 | 2026-03-16 | 91 | 99 | 2025-12 | 248 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 143/0 | 2025-12-09 | 2026-02-12 | 2026-02-20 | 65 | 73 | 2025-12 | 246 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 145/5 | 2025-12-09 | 2026-01-27 | 2026-01-31 | 49 | 53 | 2025-12 | 246 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 148/3 | 2025-12-14 | 2026-02-13 | 2026-02-17 | 61 | 65 | 2025-12 | 241 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 192/13 | 2025-12-23 | 2026-02-22 | 2026-02-28 | 61 | 67 | 2025-12 | 232 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 145/3 | 2025-12-27 | 2026-04-30 | 2026-05-06 | 124 | 130 | 2025-12 | 228 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 146/1 | 2025-12-29 | 2026-04-09 | 2026-04-15 | 101 | 107 | 2025-12 | 226 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 140/0 | 2025-12-30 | 2026-03-16 | 2026-03-24 | 76 | 84 | 2025-12 | 225 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 146/3 | 2025-12-30 | 2026-04-22 | 2026-04-29 | 113 | 120 | 2025-12 | 225 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 145/4 | 2025-12-31 | 2026-01-18 | 2026-01-28 | 18 | 28 | 2025-12 | 224 | TRUE | TRUE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 192/10 | 2026-01-04 | 2026-03-26 | 2026-03-31 | 81 | 86 | 2026-01 | 220 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 147/2 | 2026-01-08 | 2026-05-18 | 2026-05-22 | 130 | 134 | 2026-01 | 216 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 146A/0 | 2026-01-13 | 2026-03-24 | 2026-03-30 | 70 | 76 | 2026-01 | 211 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 186/1 | 2026-01-13 | 2026-03-10 | 2026-03-17 | 56 | 63 | 2026-01 | 211 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 192/7 | 2026-01-21 |  |  |  |  | 2026-01 | 203 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 192/12 | 2026-01-25 |  |  |  |  | 2026-01 | 199 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 147/1 | 2026-01-30 | 2026-05-14 | 2026-05-18 | 104 | 108 | 2026-01 | 194 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 142/0 | 2026-02-02 | 2026-05-23 | 2026-05-28 | 110 | 115 | 2026-02 | 191 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 146/0 | 2026-02-03 | 2026-04-02 | 2026-04-09 | 58 | 65 | 2026-02 | 190 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 194/1 | 2026-02-10 | 2026-03-17 | 2026-03-26 | 35 | 44 | 2026-02 | 183 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 146A/1 | 2026-02-12 | 2026-05-07 | 2026-05-13 | 84 | 90 | 2026-02 | 181 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 148/1 | 2026-02-14 | 2026-02-23 | 2026-02-27 | 9 | 13 | 2026-02 | 179 | TRUE | TRUE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 148/0 | 2026-02-27 | 2026-05-19 | 2026-05-25 | 81 | 87 | 2026-02 | 166 | FALSE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 157B/0 | 2026-03-11 |  |  |  |  | 2026-03 | 154 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 157A/0 | 2026-03-22 |  |  |  |  | 2026-03 | 143 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 157/2 | 2026-03-23 |  |  |  |  | 2026-03 | 142 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 146/2 | 2026-03-31 | 2026-04-15 | 2026-04-21 | 15 | 21 | 2026-03 | 134 | TRUE | TRUE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 192/9 | 2026-04-07 |  |  |  |  | 2026-04 | 127 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 139/3 | 2026-04-13 | 2026-05-09 | 2026-05-21 | 26 | 38 | 2026-04 | 121 | TRUE | FALSE | Yes | No | fallback_single_line | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 193/2 | 2026-04-13 |  |  |  |  | 2026-04 | 121 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 193/1 | 2026-04-19 |  |  |  |  | 2026-04 | 115 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 193/5 | 2026-04-20 |  |  |  |  | 2026-04 | 114 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 139/0 | 2026-04-21 |  |  |  |  | 2026-04 | 113 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 193/0 | 2026-04-28 |  |  |  |  | 2026-04 | 106 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 193/4 | 2026-04-29 |  |  |  |  | 2026-04 | 105 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 192/8 | 2026-05-06 |  |  |  |  | 2026-05 | 98 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 167/2 | 2026-05-13 |  |  |  |  | 2026-05 | 91 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 157B/1 | 2026-05-16 |  |  |  |  | 2026-05 | 88 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 167/3 | 2026-05-17 |  |  |  |  | 2026-05 | 87 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 133/0 | 2026-05-18 |  |  |  |  | 2026-05 | 86 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 153/0 | 2026-05-20 |  |  |  |  | 2026-05 | 84 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 167/4 | 2026-05-20 |  |  |  |  | 2026-05 | 84 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 133/1 | 2026-05-23 |  |  |  |  | 2026-05 | 81 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 167/1 | 2026-05-26 |  |  |  |  | 2026-05 | 78 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 194/0 | 2026-05-27 |  |  |  |  | 2026-05 | 77 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 150/2 | 2026-05-31 |  |  |  |  | 2026-05 | 73 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 153/1 | 2026-05-31 |  |  |  |  | 2026-05 | 73 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 155/0 | 2026-05-31 |  |  |  |  | 2026-05 | 73 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 150/4 | 2026-06-06 |  |  |  |  | 2026-06 | 67 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 155/2 | 2026-06-06 |  |  |  |  | 2026-06 | 67 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 154/0 | 2026-06-10 |  |  |  |  | 2026-06 | 63 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 150/3 | 2026-06-11 |  |  |  |  | 2026-06 | 62 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 154/1 | 2026-06-14 |  |  |  |  | 2026-06 | 59 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 160/3 | 2026-06-14 |  |  |  |  | 2026-06 | 59 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 150/1 | 2026-06-15 |  |  |  |  | 2026-06 | 58 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 154/2 | 2026-06-20 |  |  |  |  | 2026-06 | 53 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 148A/0 | 2026-06-25 |  |  |  |  | 2026-06 | 48 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 152/1 | 2026-06-25 |  |  |  |  | 2026-06 | 48 | FALSE | FALSE | No | No |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 512 | 8/1 | 2025-02-23 | 2025-11-16 | 2025-11-18 | 266 | 268 | 2025-02 | 535 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 8/3 | 2025-02-26 | 2025-07-25 | 2025-08-10 | 149 | 165 | 2025-02 | 532 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 8/6 | 2025-02-28 | 2025-08-27 | 2025-09-03 | 180 | 187 | 2025-02 | 530 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 8/2 | 2025-03-05 | 2026-03-08 | 2026-03-20 | 368 | 380 | 2025-03 | 525 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 8/5 | 2025-03-05 | 2025-09-04 | 2025-09-10 | 183 | 189 | 2025-03 | 525 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 12/1 | 2025-03-07 | 2025-10-10 | 2025-10-18 | 217 | 225 | 2025-03 | 523 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 12/2 | 2025-03-10 | 2026-01-07 | 2026-03-11 | 303 | 366 | 2025-03 | 520 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 12/3 | 2025-03-10 | 2025-10-27 | 2025-11-14 | 231 | 249 | 2025-03 | 520 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 8/4 | 2025-03-10 | 2026-02-04 | 2026-02-09 | 331 | 336 | 2025-03 | 520 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 8/8 | 2025-03-10 | 2025-08-11 | 2025-08-20 | 154 | 163 | 2025-03 | 520 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 12/4 | 2025-03-13 | 2025-11-16 | 2025-11-29 | 248 | 261 | 2025-03 | 517 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 6/7 | 2025-03-15 | 2026-02-14 | 2026-02-20 | 336 | 342 | 2025-03 | 515 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 18/5 | 2025-03-17 | 2025-08-18 | 2025-08-25 | 154 | 161 | 2025-03 | 513 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 7/6 | 2025-03-17 | 2025-08-26 | 2025-09-01 | 162 | 168 | 2025-03 | 513 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 18/4 | 2025-03-18 | 2025-11-16 | 2025-11-22 | 243 | 249 | 2025-03 | 512 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 6/8 | 2025-03-20 | 2025-12-12 | 2026-01-13 | 267 | 299 | 2025-03 | 510 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 18/3 | 2025-03-21 | 2025-11-23 | 2025-11-29 | 247 | 253 | 2025-03 | 509 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 7/5 | 2025-03-21 | 2026-01-29 | 2026-02-05 | 314 | 321 | 2025-03 | 509 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 19/1 | 2025-03-23 | 2025-08-26 | 2025-09-03 | 156 | 164 | 2025-03 | 507 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 19/2 | 2025-03-24 | 2025-10-31 | 2025-11-07 | 221 | 228 | 2025-03 | 506 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 8/7 | 2025-03-24 | 2025-08-21 | 2025-08-27 | 150 | 156 | 2025-03 | 506 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 19/3 | 2025-03-25 | 2025-11-07 | 2025-11-15 | 227 | 235 | 2025-03 | 505 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 6/10 | 2025-03-26 | 2026-02-06 | 2026-02-13 | 317 | 324 | 2025-03 | 504 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 7/7 | 2025-03-26 | 2026-01-19 | 2026-01-28 | 299 | 308 | 2025-03 | 504 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 19/6 | 2025-03-27 | 2025-09-23 | 2025-09-27 | 180 | 184 | 2025-03 | 503 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 19/4 | 2025-03-28 | 2025-09-08 | 2025-09-13 | 164 | 169 | 2025-03 | 502 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 19/7 | 2025-03-30 | 2025-09-14 | 2025-09-22 | 168 | 176 | 2025-03 | 500 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 9/2 | 2025-03-30 | 2025-09-11 | 2025-09-19 | 165 | 173 | 2025-03 | 500 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 20/1 | 2025-03-31 | 2025-09-28 | 2025-10-04 | 181 | 187 | 2025-03 | 499 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 7/8 | 2025-04-01 | 2025-08-21 | 2025-08-26 | 142 | 147 | 2025-04 | 498 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 6/9 | 2025-04-02 | 2026-02-26 | 2026-03-07 | 330 | 339 | 2025-04 | 497 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 9/3 | 2025-04-03 | 2025-09-20 | 2025-09-24 | 170 | 174 | 2025-04 | 496 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 20/5 | 2025-04-04 | 2025-12-14 | 2025-12-18 | 254 | 258 | 2025-04 | 495 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 7/9 | 2025-04-06 | 2025-08-13 | 2025-08-20 | 129 | 136 | 2025-04 | 493 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 30/6 | 2025-04-07 | 2025-12-31 | 2026-01-09 | 268 | 277 | 2025-04 | 492 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 20/2 | 2025-04-10 | 2025-10-05 | 2025-10-12 | 178 | 185 | 2025-04 | 489 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 7/11 | 2025-04-11 | 2025-11-23 | 2026-01-27 | 226 | 291 | 2025-04 | 488 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 30/5 | 2025-04-13 | 2026-01-11 | 2026-01-20 | 273 | 282 | 2025-04 | 486 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 6/4 | 2025-04-13 | 2026-01-29 | 2026-02-02 | 291 | 295 | 2025-04 | 486 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 20/3 | 2025-04-15 | 2025-12-01 | 2025-12-07 | 230 | 236 | 2025-04 | 484 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 30/4 | 2025-04-15 | 2026-01-22 | 2026-01-28 | 282 | 288 | 2025-04 | 484 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 7/10 | 2025-04-16 | 2025-11-26 | 2026-01-19 | 224 | 278 | 2025-04 | 483 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 19/5 | 2025-04-19 | 2025-08-31 | 2025-09-07 | 134 | 141 | 2025-04 | 480 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 30/7 | 2025-04-19 | 2025-09-28 | 2025-10-04 | 162 | 168 | 2025-04 | 480 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 7/4 | 2025-04-21 | 2025-09-12 | 2025-09-16 | 144 | 148 | 2025-04 | 478 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 30/8 | 2025-04-23 | 2025-12-24 | 2025-12-31 | 245 | 252 | 2025-04 | 476 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 28/2 | 2025-04-24 | 2025-10-13 | 2025-10-18 | 172 | 177 | 2025-04 | 475 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 20/6 | 2025-04-25 | 2026-01-04 | 2026-01-13 | 254 | 263 | 2025-04 | 474 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 30/10 | 2025-04-26 | 2025-12-13 | 2025-12-22 | 231 | 240 | 2025-04 | 473 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 28/1 | 2025-04-28 | 2025-09-24 | 2025-10-03 | 149 | 158 | 2025-04 | 471 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 7/3 | 2025-04-28 | 2025-09-18 | 2025-09-23 | 143 | 148 | 2025-04 | 471 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 23/3 | 2025-04-30 | 2026-02-12 | 2026-02-14 | 288 | 290 | 2025-04 | 469 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 30/12 | 2025-04-30 | 2025-12-03 | 2025-12-13 | 217 | 227 | 2025-04 | 469 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 23/2 | 2025-05-04 | 2026-02-07 | 2026-02-11 | 279 | 283 | 2025-05 | 465 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 30/11 | 2025-05-04 | 2026-02-13 | 2026-02-19 | 285 | 291 | 2025-05 | 465 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 7/2 | 2025-05-04 | 2026-07-30 | 2026-08-05 | 452 | 458 | 2025-05 | 465 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 30/13 | 2025-05-07 | 2026-02-06 | 2026-02-12 | 275 | 281 | 2025-05 | 462 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 30/14 | 2025-05-09 | 2025-11-22 | 2025-12-02 | 197 | 207 | 2025-05 | 460 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 7/1 | 2025-05-10 | 2025-09-02 | 2025-09-11 | 115 | 124 | 2025-05 | 459 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 30/18 | 2025-05-11 | 2025-09-21 | 2025-09-27 | 133 | 139 | 2025-05 | 458 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 11/4 | 2025-05-12 | 2025-12-04 | 2025-12-13 | 206 | 215 | 2025-05 | 457 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 31/1 | 2025-05-14 | 2025-09-13 | 2025-09-20 | 122 | 129 | 2025-05 | 455 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 31/2 | 2025-05-15 | 2025-09-02 | 2025-09-12 | 110 | 120 | 2025-05 | 454 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 31/3 | 2025-05-17 | 2026-01-06 | 2026-01-16 | 234 | 244 | 2025-05 | 452 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 6/1 | 2025-05-17 | 2025-08-21 | 2025-09-01 | 96 | 107 | 2025-05 | 452 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 31/4 | 2025-05-18 | 2026-02-08 | 2026-02-13 | 266 | 271 | 2025-05 | 451 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 28/4 | 2025-05-19 | 2025-11-01 | 2025-11-05 | 166 | 170 | 2025-05 | 450 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5/8 | 2025-05-19 | 2026-05-21 | 2026-06-03 | 367 | 380 | 2025-05 | 450 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 31/5 | 2025-05-20 | 2026-01-11 | 2026-01-18 | 236 | 243 | 2025-05 | 449 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 11/2 | 2025-05-21 | 2025-12-25 | 2025-12-30 | 218 | 223 | 2025-05 | 448 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 31/6 | 2025-05-23 | 2026-01-19 | 2026-01-27 | 241 | 249 | 2025-05 | 446 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5/10 | 2025-05-23 | 2025-12-14 | 2025-12-20 | 205 | 211 | 2025-05 | 446 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 6/2 | 2025-05-25 | 2025-12-29 | 2026-01-17 | 218 | 237 | 2025-05 | 444 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 11/3 | 2025-05-26 | 2025-12-14 | 2025-12-19 | 202 | 207 | 2025-05 | 443 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 31/7 | 2025-05-26 | 2026-01-27 | 2026-01-31 | 246 | 250 | 2025-05 | 443 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 28/7 | 2025-05-27 | 2025-10-26 | 2025-10-31 | 152 | 157 | 2025-05 | 442 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 28/6 | 2025-06-01 | 2025-11-05 | 2025-11-08 | 157 | 160 | 2025-06 | 437 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 6/3 | 2025-06-01 | 2026-01-18 | 2026-01-27 | 231 | 240 | 2025-06 | 437 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 11/5 | 2025-06-04 | 2025-11-27 | 2025-12-03 | 176 | 182 | 2025-06 | 434 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 31/8 | 2025-06-04 | 2026-02-01 | 2026-02-07 | 242 | 248 | 2025-06 | 434 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 28/3 | 2025-06-06 | 2026-02-02 | 2026-02-06 | 241 | 245 | 2025-06 | 432 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 31/12 | 2025-06-07 | 2026-02-13 | 2026-02-20 | 251 | 258 | 2025-06 | 431 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5/9 | 2025-06-08 | 2025-12-08 | 2025-12-14 | 183 | 189 | 2025-06 | 430 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 31/11 | 2025-06-10 |  |  |  |  | 2025-06 | 428 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 28/5 | 2025-06-11 | 2025-10-03 | 2025-10-08 | 114 | 119 | 2025-06 | 427 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 31/13 | 2025-06-11 | 2026-02-07 | 2026-02-12 | 241 | 246 | 2025-06 | 427 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5/11 | 2025-06-11 | 2025-12-21 | 2025-12-27 | 193 | 199 | 2025-06 | 427 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 6/6 | 2025-06-11 | 2026-02-03 | 2026-02-08 | 237 | 242 | 2025-06 | 427 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5/5 | 2025-06-16 | 2025-12-01 | 2025-12-07 | 168 | 174 | 2025-06 | 422 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 6/5 | 2025-06-16 | 2026-02-09 | 2026-02-13 | 238 | 242 | 2025-06 | 422 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 27/2 | 2025-06-17 |  |  |  |  | 2025-06 | 421 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 31/9 | 2025-06-17 | 2026-02-21 | 2026-03-01 | 249 | 257 | 2025-06 | 421 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 30/9 | 2025-06-18 | 2026-02-21 | 2026-03-06 | 248 | 261 | 2025-06 | 420 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5/4 | 2025-06-18 | 2026-01-15 | 2026-01-24 | 211 | 220 | 2025-06 | 420 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 27/3 | 2025-06-20 | 2026-07-07 | 2026-07-12 | 382 | 387 | 2025-06 | 418 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 6/0 | 2025-06-22 | 2025-12-16 | 2026-01-02 | 177 | 194 | 2025-06 | 416 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5/3 | 2025-06-23 | 2026-02-11 | 2026-02-16 | 233 | 238 | 2025-06 | 415 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 19/0 | 2025-06-26 | 2025-10-13 | 2025-10-30 | 109 | 126 | 2025-06 | 412 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 29/1 | 2025-06-26 | 2025-11-29 | 2025-12-04 | 156 | 161 | 2025-06 | 412 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 4/14 | 2025-06-26 | 2026-03-24 | 2026-03-27 | 271 | 274 | 2025-06 | 412 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5/2 | 2025-06-26 | 2026-01-25 | 2026-01-31 | 213 | 219 | 2025-06 | 412 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 20/0 | 2025-06-30 | 2025-12-20 | 2026-01-03 | 173 | 187 | 2025-06 | 408 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 34/4 | 2025-06-30 | 2026-05-17 | 2026-05-23 | 321 | 327 | 2025-06 | 408 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 41/6 | 2025-07-01 | 2026-04-14 | 2026-04-21 | 287 | 294 | 2025-07 | 407 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 29/2 | 2025-07-03 | 2025-10-13 | 2025-10-22 | 102 | 111 | 2025-07 | 405 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5/1 | 2025-07-03 | 2026-02-26 | 2026-02-28 | 238 | 240 | 2025-07 | 405 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 12/5 | 2025-07-04 | 2025-11-17 | 2025-11-26 | 136 | 145 | 2025-07 | 404 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 29/7 | 2025-07-04 | 2025-11-13 | 2025-11-17 | 132 | 136 | 2025-07 | 404 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 4/13 | 2025-07-05 | 2026-03-07 | 2026-03-09 | 245 | 247 | 2025-07 | 403 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 41/5 | 2025-07-05 | 2026-04-07 | 2026-04-14 | 276 | 283 | 2025-07 | 403 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 11/6 | 2025-07-07 | 2025-12-31 | 2026-01-07 | 177 | 184 | 2025-07 | 401 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 29/3 | 2025-07-09 | 2025-11-03 | 2025-11-12 | 117 | 126 | 2025-07 | 399 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 4/11 | 2025-07-09 | 2026-03-01 | 2026-04-12 | 235 | 277 | 2025-07 | 399 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 16/2 | 2025-07-10 | 2026-08-08 |  | 394 |  | 2025-07 | 398 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 29/6 | 2025-07-10 | 2025-11-17 | 2025-11-21 | 130 | 134 | 2025-07 | 398 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 29/4 | 2025-07-12 | 2025-11-25 | 2025-11-29 | 136 | 140 | 2025-07 | 396 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 4/12 | 2025-07-13 | 2026-03-21 | 2026-03-23 | 251 | 253 | 2025-07 | 395 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 1A/1 | 2025-07-15 | 2026-02-23 | 2026-02-28 | 223 | 228 | 2025-07 | 393 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 29/8 | 2025-07-15 | 2025-12-24 | 2025-12-28 | 162 | 166 | 2025-07 | 393 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 37/10 | 2025-07-16 | 2025-12-22 | 2026-01-04 | 159 | 172 | 2025-07 | 392 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 31/26 | 2025-07-17 | 2025-12-01 | 2025-12-08 | 137 | 144 | 2025-07 | 391 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 4/3 | 2025-07-17 | 2026-07-26 | 2026-08-01 | 374 | 380 | 2025-07 | 391 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 37/9 | 2025-07-18 | 2026-01-05 | 2026-01-16 | 171 | 182 | 2025-07 | 390 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 29/5 | 2025-07-19 | 2025-11-21 | 2025-11-25 | 125 | 129 | 2025-07 | 389 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 1A/3 | 2025-07-20 | 2026-07-31 | 2026-08-07 | 376 | 383 | 2025-07 | 388 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 29/9 | 2025-07-20 | 2025-12-20 | 2025-12-24 | 153 | 157 | 2025-07 | 388 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 31/14 | 2025-07-21 | 2026-02-01 | 2026-02-06 | 195 | 200 | 2025-07 | 387 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 1A/2 | 2025-07-22 | 2026-03-01 | 2026-03-09 | 222 | 230 | 2025-07 | 386 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 31/15 | 2025-07-23 | 2026-01-22 | 2026-01-31 | 183 | 192 | 2025-07 | 385 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 29/10 | 2025-07-25 | 2025-12-17 | 2025-12-20 | 145 | 148 | 2025-07 | 383 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 29/11 | 2025-07-25 | 2025-12-29 | 2026-01-03 | 157 | 162 | 2025-07 | 383 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 40/2 | 2025-07-25 | 2026-07-13 | 2026-07-21 | 353 | 361 | 2025-07 | 383 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 37/8 | 2025-07-26 | 2026-01-04 | 2026-01-21 | 162 | 179 | 2025-07 | 382 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 2/2 | 2025-07-29 | 2026-02-07 | 2026-02-18 | 193 | 204 | 2025-07 | 379 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 31/24 | 2025-07-29 | 2026-07-07 | 2026-07-18 | 343 | 354 | 2025-07 | 379 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 40/3 | 2025-07-29 | 2026-05-16 | 2026-05-27 | 291 | 302 | 2025-07 | 379 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 4/0 | 2025-07-30 | 2026-01-22 | 2026-01-31 | 176 | 185 | 2025-07 | 378 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 31/20 | 2025-07-31 | 2025-12-11 | 2025-12-17 | 133 | 139 | 2025-07 | 377 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 29/0 | 2025-08-01 | 2025-10-19 | 2025-10-25 | 79 | 85 | 2025-08 | 376 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 29/12 | 2025-08-01 | 2025-12-09 | 2025-12-16 | 130 | 137 | 2025-08 | 376 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 31/19 | 2025-08-01 | 2026-03-02 | 2026-03-13 | 213 | 224 | 2025-08 | 376 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 37/7 | 2025-08-02 | 2025-12-20 | 2026-01-03 | 140 | 154 | 2025-08 | 375 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 2/4 | 2025-08-03 | 2026-01-27 | 2026-02-06 | 177 | 187 | 2025-08 | 374 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 3A/3 | 2025-08-03 | 2026-01-15 | 2026-01-21 | 165 | 171 | 2025-08 | 374 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 40/4 | 2025-08-03 | 2026-07-20 | 2026-07-25 | 351 | 356 | 2025-08 | 374 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 29/20 | 2025-08-05 | 2026-01-02 | 2026-01-08 | 150 | 156 | 2025-08 | 372 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 31/16 | 2025-08-05 | 2026-01-11 | 2026-01-22 | 159 | 170 | 2025-08 | 372 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 34/6 | 2025-08-06 | 2026-03-06 | 2026-03-10 | 212 | 216 | 2025-08 | 371 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 29/15 | 2025-08-07 | 2025-12-05 | 2025-12-09 | 120 | 124 | 2025-08 | 370 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 31/21 | 2025-08-07 | 2026-07-18 | 2026-07-24 | 345 | 351 | 2025-08 | 370 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 31/23 | 2025-08-07 | 2026-03-14 | 2026-03-21 | 219 | 226 | 2025-08 | 370 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 3A/2 | 2025-08-07 | 2026-01-15 | 2026-01-19 | 161 | 165 | 2025-08 | 370 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 2/5 | 2025-08-08 | 2026-01-10 | 2026-01-27 | 155 | 172 | 2025-08 | 369 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 2/1 | 2025-08-13 |  |  |  |  | 2025-08 | 364 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 30/2 | 2025-08-13 | 2025-10-05 | 2025-10-12 | 53 | 60 | 2025-08 | 364 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 34/5 | 2025-08-14 | 2026-05-13 | 2026-05-26 | 272 | 285 | 2025-08 | 363 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 3A/1 | 2025-08-14 | 2026-01-22 | 2026-01-27 | 161 | 166 | 2025-08 | 363 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 9/1 | 2025-08-21 | 2025-11-29 | 2025-12-07 | 100 | 108 | 2025-08 | 356 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 30/16 | 2025-08-22 | 2026-08-03 | 2026-08-10 | 346 | 353 | 2025-08 | 355 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 31/22 | 2025-08-22 | 2026-07-25 | 2026-08-01 | 337 | 344 | 2025-08 | 355 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 34/3 | 2025-08-23 | 2026-03-10 | 2026-03-14 | 199 | 203 | 2025-08 | 354 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 41/0 | 2025-08-28 | 2026-02-22 | 2026-02-25 | 178 | 181 | 2025-08 | 349 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 9/0 | 2025-08-28 | 2025-09-25 | 2025-10-09 | 28 | 42 | 2025-08 | 349 | TRUE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 34/7 | 2025-08-29 | 2026-04-30 | 2026-05-05 | 244 | 249 | 2025-08 | 348 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 29/18 | 2025-09-03 | 2026-06-25 | 2026-06-30 | 295 | 300 | 2025-09 | 343 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 36/9 | 2025-09-03 | 2026-07-13 | 2026-07-19 | 313 | 319 | 2025-09 | 343 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 4/5 | 2025-09-03 |  |  |  |  | 2025-09 | 343 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 36/8 | 2025-09-06 | 2026-01-29 | 2026-02-04 | 145 | 151 | 2025-09 | 340 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 37/6 | 2025-09-06 | 2026-08-10 |  | 338 |  | 2025-09 | 340 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 8/0 | 2025-09-06 | 2025-11-20 | 2025-11-22 | 75 | 77 | 2025-09 | 340 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 34/2 | 2025-09-09 | 2026-05-26 | 2026-06-04 | 259 | 268 | 2025-09 | 337 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 29/14 | 2025-09-11 | 2026-01-22 | 2026-01-27 | 133 | 138 | 2025-09 | 335 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 36/7 | 2025-09-11 | 2026-02-12 | 2026-02-16 | 154 | 158 | 2025-09 | 335 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 36/6 | 2025-09-16 | 2026-02-06 | 2026-02-11 | 143 | 148 | 2025-09 | 330 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 37/5 | 2025-09-16 | 2026-01-18 | 2026-02-01 | 124 | 138 | 2025-09 | 330 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 4/6 | 2025-09-16 | 2025-12-25 | 2025-12-31 | 100 | 106 | 2025-09 | 330 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 7/0 | 2025-09-16 | 2026-02-14 | 2026-02-25 | 151 | 162 | 2025-09 | 330 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 36/5 | 2025-09-21 | 2026-08-03 | 2026-08-09 | 316 | 322 | 2025-09 | 325 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 4/8 | 2025-09-22 | 2026-02-09 | 2026-02-15 | 140 | 146 | 2025-09 | 324 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 13/0 | 2025-09-23 | 2026-01-16 | 2026-01-27 | 115 | 126 | 2025-09 | 323 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 4/9 | 2025-09-25 | 2026-02-16 | 2026-02-22 | 144 | 150 | 2025-09 | 321 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 36/4 | 2025-09-26 |  |  |  |  | 2025-09 | 320 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 36/3 | 2025-09-29 | 2026-03-15 | 2026-03-21 | 167 | 173 | 2025-09 | 317 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 29/19 | 2025-10-01 | 2026-06-16 | 2026-06-20 | 258 | 262 | 2025-10 | 315 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 34/9 | 2025-10-04 | 2026-04-03 | 2026-04-07 | 181 | 185 | 2025-10 | 312 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 37/0 | 2025-10-04 | 2026-03-22 | 2026-03-29 | 169 | 176 | 2025-10 | 312 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 4/7 | 2025-10-09 | 2026-01-02 | 2026-01-14 | 85 | 97 | 2025-10 | 307 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 20/4 | 2025-10-12 | 2025-12-07 | 2025-12-12 | 56 | 61 | 2025-10 | 304 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 34/10 | 2025-10-12 | 2026-03-06 | 2026-03-10 | 145 | 149 | 2025-10 | 304 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 36/2 | 2025-10-12 | 2026-07-26 | 2026-08-01 | 287 | 293 | 2025-10 | 304 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 37/2 | 2025-10-16 | 2026-03-30 | 2026-04-02 | 165 | 168 | 2025-10 | 300 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 18/2 | 2025-10-17 | 2026-01-22 | 2026-01-27 | 97 | 102 | 2025-10 | 299 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 30/0 | 2025-10-17 | 2026-06-30 | 2026-07-09 | 256 | 265 | 2025-10 | 299 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 37/3 | 2025-10-18 | 2026-04-03 | 2026-04-08 | 167 | 172 | 2025-10 | 298 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 31/17 | 2025-10-19 | 2025-12-21 | 2025-12-29 | 63 | 71 | 2025-10 | 297 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 3/1 | 2025-10-23 | 2026-07-20 | 2026-07-30 | 270 | 280 | 2025-10 | 293 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 29/13 | 2025-10-25 | 2026-01-17 | 2026-01-21 | 84 | 88 | 2025-10 | 291 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 35/0 | 2025-10-25 | 2026-02-17 | 2026-02-25 | 115 | 123 | 2025-10 | 291 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 31/18 | 2025-10-26 | 2025-12-30 | 2026-01-12 | 65 | 78 | 2025-10 | 290 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 37/4 | 2025-10-26 | 2026-04-10 | 2026-04-12 | 166 | 168 | 2025-10 | 290 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 12/0 | 2025-10-27 | 2026-07-10 | 2026-07-17 | 256 | 263 | 2025-10 | 289 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 3/2 | 2025-10-28 |  |  |  |  | 2025-10 | 288 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 31/0 | 2025-10-30 |  |  |  |  | 2025-10 | 286 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 3/3 | 2025-10-30 | 2026-02-15 | 2026-02-24 | 108 | 117 | 2025-10 | 286 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 40/1 | 2025-10-30 | 2026-06-11 | 2026-06-19 | 224 | 232 | 2025-10 | 286 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 9/4 | 2025-10-30 | 2025-12-08 | 2025-12-10 | 39 | 41 | 2025-10 | 286 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 29/21 | 2025-11-01 | 2026-01-09 | 2026-01-13 | 69 | 73 | 2025-11 | 284 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 35/1 | 2025-11-01 | 2026-02-25 | 2026-03-02 | 116 | 121 | 2025-11 | 284 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 3/4 | 2025-11-02 | 2026-02-25 | 2026-03-05 | 115 | 123 | 2025-11 | 283 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 37/1 | 2025-11-03 |  |  |  |  | 2025-11 | 282 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 30/17 | 2025-11-04 | 2026-03-08 | 2026-03-31 | 124 | 147 | 2025-11 | 281 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 11/1 | 2025-11-05 | 2025-12-19 | 2025-12-24 | 44 | 49 | 2025-11 | 280 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 3/5 | 2025-11-06 | 2026-02-05 | 2026-02-14 | 91 | 100 | 2025-11 | 279 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 35/2 | 2025-11-07 | 2026-03-29 | 2026-04-02 | 142 | 146 | 2025-11 | 278 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 29/17 | 2025-11-09 | 2026-01-13 | 2026-01-17 | 65 | 69 | 2025-11 | 276 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 3/6 | 2025-11-09 | 2026-01-31 | 2026-02-04 | 83 | 87 | 2025-11 | 276 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 40/0 | 2025-11-10 | 2026-06-19 | 2026-06-28 | 221 | 230 | 2025-11 | 275 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 16/1 | 2025-11-11 | 2026-06-08 | 2026-06-14 | 209 | 215 | 2025-11 | 274 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 31/25 | 2025-11-12 | 2026-03-22 | 2026-03-27 | 130 | 135 | 2025-11 | 273 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 3/7 | 2025-11-12 | 2026-01-27 | 2026-01-30 | 76 | 79 | 2025-11 | 273 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 35/3 | 2025-11-13 | 2026-03-10 | 2026-03-16 | 117 | 123 | 2025-11 | 272 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 39/0 | 2025-11-14 | 2026-07-22 | 2026-08-01 | 250 | 260 | 2025-11 | 271 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 11/8 | 2025-11-16 | 2026-01-27 | 2026-02-02 | 72 | 78 | 2025-11 | 269 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 38/2 | 2025-11-16 | 2026-07-20 | 2026-07-24 | 246 | 250 | 2025-11 | 269 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 31/27 | 2025-11-17 | 2026-01-19 | 2026-01-29 | 63 | 73 | 2025-11 | 268 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 30/1 | 2025-11-18 | 2026-06-21 | 2026-06-25 | 215 | 219 | 2025-11 | 267 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 3A/0 | 2025-11-19 | 2026-03-29 | 2026-04-04 | 130 | 136 | 2025-11 | 266 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 20/7 | 2025-11-21 | 2026-01-15 | 2026-01-20 | 55 | 60 | 2025-11 | 264 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 38/0 | 2025-11-22 | 2026-04-08 | 2026-04-17 | 137 | 146 | 2025-11 | 263 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 29/16 | 2025-11-24 | 2026-06-09 | 2026-06-15 | 197 | 203 | 2025-11 | 261 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 38/1 | 2025-11-24 | 2026-07-11 | 2026-07-29 | 229 | 247 | 2025-11 | 261 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 32/0 | 2025-11-25 | 2026-06-21 | 2026-07-06 | 208 | 223 | 2025-11 | 260 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 32/4 | 2025-11-28 | 2026-07-22 | 2026-08-02 | 236 | 247 | 2025-11 | 257 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 3/0 | 2025-11-29 | 2026-07-31 | 2026-08-11 | 244 | 255 | 2025-11 | 256 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 34/8 | 2025-11-29 | 2026-05-06 | 2026-05-12 | 158 | 164 | 2025-11 | 256 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 21/0 | 2025-12-01 | 2026-06-29 | 2026-07-10 | 210 | 221 | 2025-12 | 254 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 32/1 | 2025-12-01 | 2026-08-07 |  | 249 |  | 2025-12 | 254 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 2A/5 | 2025-12-02 | 2026-07-07 | 2026-07-19 | 217 | 229 | 2025-12 | 253 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 32/3 | 2025-12-02 |  |  |  |  | 2025-12 | 253 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5/0 | 2025-12-02 | 2026-02-01 | 2026-02-10 | 61 | 70 | 2025-12 | 253 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 35/5 | 2025-12-03 | 2026-03-17 | 2026-03-22 | 104 | 109 | 2025-12 | 252 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 32/5 | 2025-12-04 | 2026-01-30 | 2026-02-03 | 57 | 61 | 2025-12 | 251 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 2A/4 | 2025-12-05 | 2026-04-06 | 2026-04-14 | 122 | 130 | 2025-12 | 250 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 32/6 | 2025-12-06 |  |  |  |  | 2025-12 | 249 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 35/4 | 2025-12-07 | 2026-03-23 | 2026-03-26 | 106 | 109 | 2025-12 | 248 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 4/4 | 2025-12-07 | 2026-02-01 | 2026-02-08 | 56 | 63 | 2025-12 | 248 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 30/3 | 2025-12-08 | 2026-01-28 | 2026-02-04 | 51 | 58 | 2025-12 | 247 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 2A/3 | 2025-12-09 |  |  |  |  | 2025-12 | 246 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 35/6 | 2025-12-10 | 2026-03-21 | 2026-03-31 | 101 | 111 | 2025-12 | 245 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 2A/2 | 2025-12-12 | 2026-05-31 | 2026-06-19 | 170 | 189 | 2025-12 | 243 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 4/2 | 2025-12-12 | 2026-07-31 | 2026-08-07 | 231 | 238 | 2025-12 | 243 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 20A/0 | 2025-12-13 | 2026-07-10 | 2026-07-20 | 209 | 219 | 2025-12 | 242 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 35/8 | 2025-12-14 | 2026-02-27 | 2026-03-06 | 75 | 82 | 2025-12 | 241 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 4/1 | 2025-12-14 |  |  |  |  | 2025-12 | 241 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 2A/1 | 2025-12-16 | 2026-06-21 | 2026-06-26 | 187 | 192 | 2025-12 | 239 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 32/7 | 2025-12-16 |  |  |  |  | 2025-12 | 239 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 23/1 | 2025-12-17 | 2026-02-24 | 2026-02-26 | 69 | 71 | 2025-12 | 238 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 28/0 | 2025-12-17 | 2026-02-15 | 2026-02-23 | 60 | 68 | 2025-12 | 238 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 33/2 | 2025-12-17 | 2026-02-27 | 2026-03-05 | 72 | 78 | 2025-12 | 238 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 35/7 | 2025-12-17 | 2026-03-12 | 2026-03-20 | 85 | 93 | 2025-12 | 238 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5/6 | 2025-12-19 | 2026-03-10 | 2026-03-13 | 81 | 84 | 2025-12 | 236 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 35/9 | 2025-12-21 | 2026-02-19 | 2026-02-26 | 60 | 67 | 2025-12 | 234 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 33/4 | 2025-12-23 | 2026-04-24 | 2026-04-29 | 122 | 127 | 2025-12 | 232 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 2A/0 | 2025-12-25 | 2026-06-27 | 2026-07-05 | 184 | 192 | 2025-12 | 230 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 36/0 | 2025-12-26 | 2026-08-10 |  | 227 |  | 2025-12 | 229 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5/7 | 2025-12-26 | 2026-03-14 | 2026-03-20 | 78 | 84 | 2025-12 | 229 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 22/0 | 2025-12-27 | 2026-06-19 | 2026-06-28 | 174 | 183 | 2025-12 | 228 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 27/1 | 2025-12-27 | 2026-07-10 | 2026-07-18 | 195 | 203 | 2025-12 | 228 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 2/6 | 2025-12-30 | 2026-03-10 | 2026-03-18 | 70 | 78 | 2025-12 | 225 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 36/1 | 2025-12-30 |  |  |  |  | 2025-12 | 225 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 29/22 | 2025-12-31 | 2026-01-27 | 2026-02-01 | 27 | 32 | 2025-12 | 224 | TRUE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 2/3 | 2026-01-03 | 2026-03-19 | 2026-03-29 | 75 | 85 | 2026-01 | 221 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 23/0 | 2026-01-04 | 2026-06-03 | 2026-06-18 | 150 | 165 | 2026-01 | 220 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 33A/0 | 2026-01-05 | 2026-06-19 | 2026-06-29 | 165 | 175 | 2026-01 | 219 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 18/1 | 2026-01-11 | 2026-02-10 | 2026-02-16 | 30 | 36 | 2026-01 | 213 | TRUE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 42/0 | 2026-01-11 | 2026-08-06 |  | 207 |  | 2026-01 | 213 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 13/1 | 2026-01-12 | 2026-07-18 | 2026-07-25 | 187 | 194 | 2026-01 | 212 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 34/0 | 2026-01-13 | 2026-06-30 | 2026-07-11 | 168 | 179 | 2026-01 | 211 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 43/0 | 2026-01-16 | 2026-07-20 | 2026-08-06 | 185 | 202 | 2026-01 | 208 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 2/0 | 2026-01-20 | 2026-07-18 | 2026-07-30 | 179 | 191 | 2026-01 | 204 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 33/3 | 2026-01-21 | 2026-04-18 | 2026-04-23 | 87 | 92 | 2026-01 | 203 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 33/1 | 2026-01-31 |  |  |  |  | 2026-01 | 193 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 10/0 | 2026-02-02 | 2026-06-24 | 2026-07-17 | 142 | 165 | 2026-02 | 191 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 16/3 | 2026-02-07 |  |  |  |  | 2026-02 | 186 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 32/8 | 2026-02-19 |  |  |  |  | 2026-02 | 174 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 32/9 | 2026-02-22 | 2026-06-12 | 2026-06-19 | 110 | 117 | 2026-02 | 171 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 33/0 | 2026-03-03 | 2026-06-05 | 2026-06-12 | 94 | 101 | 2026-03 | 162 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 44/0 | 2026-03-09 | 2026-08-09 |  | 153 |  | 2026-03 | 156 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 32/2 | 2026-03-15 | 2026-03-29 | 2026-04-14 | 14 | 30 | 2026-03 | 150 | TRUE | TRUE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 17/0 | 2026-04-03 | 2026-06-17 | 2026-07-03 | 75 | 91 | 2026-04 | 131 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 47/0 | 2026-04-08 |  |  |  |  | 2026-04 | 126 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 18/0 | 2026-04-12 | 2026-06-29 | 2026-07-10 | 78 | 89 | 2026-04 | 122 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 44/1 | 2026-04-15 |  |  |  |  | 2026-04 | 119 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 45/0 | 2026-04-24 |  |  |  |  | 2026-04 | 110 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 46/0 | 2026-04-24 |  |  |  |  | 2026-04 | 110 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 34/1 | 2026-04-29 |  |  |  |  | 2026-04 | 105 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 11/7 | 2026-05-09 | 2026-07-04 | 2026-07-09 | 56 | 61 | 2026-05 | 95 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 31/10 | 2026-05-21 | 2026-08-11 |  | 82 |  | 2026-05 | 83 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 27/0 | 2026-05-25 | 2026-07-19 | 2026-08-08 | 55 | 75 | 2026-05 | 79 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 11/0 | 2026-05-29 | 2026-07-12 | 2026-07-25 | 44 | 57 | 2026-05 | 75 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 25/1 | 2026-05-31 | 2026-07-13 | 2026-07-20 | 43 | 50 | 2026-05 | 73 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 1A/0 | 2026-06-03 | 2026-08-08 |  | 66 |  | 2026-06 | 70 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 16/0 | 2026-06-04 |  |  |  |  | 2026-06 | 69 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 26/0 | 2026-06-10 | 2026-07-21 |  | 41 |  | 2026-06 | 63 | FALSE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 23/4 | 2026-06-12 | 2026-07-11 | 2026-07-16 | 29 | 34 | 2026-06 | 61 | TRUE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 1/2 | 2026-06-24 |  |  |  |  | 2026-06 | 49 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 24/0 | 2026-06-25 |  |  |  |  | 2026-06 | 48 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 1/1 | 2026-07-01 |  |  |  |  | 2026-07 | 42 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 32/10 | 2026-07-03 |  |  |  |  | 2026-07 | 40 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 25/0 | 2026-07-05 | 2026-07-31 | 2026-08-08 | 26 | 34 | 2026-07 | 38 | TRUE | FALSE | Yes | No | exact | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 1/0 | 2026-07-09 |  |  |  |  | 2026-07 | 34 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 30/15 | 2026-08-05 |  |  |  |  | 2026-08 | 7 | FALSE | FALSE | No | No |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 513 | 25/1 | 2025-03-28 | 2025-09-23 | 2025-09-29 | 179 | 185 | 2025-03 | 502 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 25/2 | 2025-04-01 | 2025-09-17 | 2025-09-22 | 169 | 174 | 2025-04 | 498 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 24/2 | 2025-04-04 |  |  |  |  | 2025-04 | 495 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 24/1 | 2025-04-07 |  |  |  |  | 2025-04 | 492 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 26/2 | 2025-04-12 | 2025-10-03 | 2025-10-09 | 174 | 180 | 2025-04 | 487 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 30/2 | 2025-04-12 |  |  |  |  | 2025-04 | 487 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 23/6 | 2025-04-14 |  |  |  |  | 2025-04 | 485 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 23/5 | 2025-04-16 |  |  |  |  | 2025-04 | 483 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 31/1 | 2025-04-17 |  |  |  |  | 2025-04 | 482 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 30/3 | 2025-04-22 |  |  |  |  | 2025-04 | 477 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 37/1 | 2025-04-24 |  |  |  |  | 2025-04 | 475 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 30/1 | 2025-04-25 |  |  |  |  | 2025-04 | 474 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 30/2 | 2025-04-28 |  |  |  |  | 2025-04 | 471 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 24/3 | 2025-04-29 |  |  |  |  | 2025-04 | 470 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 31/2 | 2025-04-30 |  |  |  |  | 2025-04 | 469 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 29/5 | 2025-05-01 | 2025-11-11 | 2025-11-14 | 194 | 197 | 2025-05 | 468 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 29/2 | 2025-05-03 | 2025-11-27 | 2025-12-01 | 208 | 212 | 2025-05 | 466 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 29/4 | 2025-05-04 | 2025-11-03 | 2025-11-06 | 183 | 186 | 2025-05 | 465 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 29/3 | 2025-05-05 | 2025-11-15 | 2025-11-18 | 194 | 197 | 2025-05 | 464 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 29/1 | 2025-05-06 | 2025-12-03 | 2025-12-07 | 211 | 215 | 2025-05 | 463 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 28/3 | 2025-05-09 | 2025-10-25 | 2025-10-31 | 169 | 175 | 2025-05 | 460 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 28/4 | 2025-05-09 | 2025-11-06 | 2025-11-10 | 181 | 185 | 2025-05 | 460 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 28/2 | 2025-05-11 | 2025-10-31 | 2025-11-03 | 173 | 176 | 2025-05 | 458 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 24/4 | 2025-05-17 | 2025-09-29 | 2025-10-03 | 135 | 139 | 2025-05 | 452 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 3/5 | 2025-05-20 |  |  |  |  | 2025-05 | 449 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 55/7 | 2025-05-20 |  |  |  |  | 2025-05 | 449 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 23/3 | 2025-05-24 |  |  |  |  | 2025-05 | 445 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 3/6 | 2025-05-24 |  |  |  |  | 2025-05 | 445 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 3/10 | 2025-05-27 |  |  |  |  | 2025-05 | 442 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 32B/1 | 2025-05-28 |  |  |  |  | 2025-05 | 441 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 21/7 | 2025-06-02 |  |  |  |  | 2025-06 | 436 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 21/6 | 2025-06-05 |  |  |  |  | 2025-06 | 433 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 23/1 | 2025-06-07 |  |  |  |  | 2025-06 | 431 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 23/3 | 2025-06-09 |  |  |  |  | 2025-06 | 429 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 23/2 | 2025-06-11 |  |  |  |  | 2025-06 | 427 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 23/4 | 2025-06-15 |  |  |  |  | 2025-06 | 423 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 18/4 | 2025-06-28 |  |  |  |  | 2025-06 | 410 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 56/1 | 2025-06-28 | 2026-03-08 | 2026-03-11 | 253 | 256 | 2025-06 | 410 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 14/4 | 2025-07-01 |  |  |  |  | 2025-07 | 407 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 26/1 | 2025-07-03 |  |  |  |  | 2025-07 | 405 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 56/2 | 2025-07-05 | 2026-01-23 | 2026-01-29 | 202 | 208 | 2025-07 | 403 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 14/3 | 2025-07-07 |  |  |  |  | 2025-07 | 401 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 56/4 | 2025-07-10 | 2026-06-04 | 2026-06-12 | 329 | 337 | 2025-07 | 398 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 14/2 | 2025-07-13 |  |  |  |  | 2025-07 | 395 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 56/0 | 2025-07-15 |  |  |  |  | 2025-07 | 393 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 55/5 | 2025-07-20 | 2025-12-15 | 2025-12-24 | 148 | 157 | 2025-07 | 388 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 15B/4 | 2025-07-21 |  |  |  |  | 2025-07 | 387 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 55/0 | 2025-07-24 |  |  |  |  | 2025-07 | 384 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 55/6 | 2025-07-28 | 2026-01-16 | 2026-01-22 | 172 | 178 | 2025-07 | 380 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 54/6 | 2025-08-09 | 2026-01-29 | 2026-02-03 | 173 | 178 | 2025-08 | 368 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 36/3 | 2025-08-20 |  |  |  |  | 2025-08 | 357 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 56/3 | 2025-08-24 | 2026-06-12 | 2026-06-17 | 292 | 297 | 2025-08 | 353 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 36/4 | 2025-09-01 |  |  |  |  | 2025-09 | 345 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 27/0 | 2025-09-14 | 2025-10-19 | 2025-10-25 | 35 | 41 | 2025-09 | 332 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 26/0 | 2025-09-18 | 2025-10-14 | 2025-10-19 | 26 | 31 | 2025-09 | 328 | TRUE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 30/0 | 2025-09-19 |  |  |  |  | 2025-09 | 327 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 25/0 | 2025-09-20 | 2025-10-10 | 2025-10-14 | 20 | 24 | 2025-09 | 326 | TRUE | TRUE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 24/0 | 2025-09-24 |  |  |  |  | 2025-09 | 322 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 29/0 | 2025-09-24 | 2025-11-19 | 2025-11-26 | 56 | 63 | 2025-09 | 322 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 19/0 | 2025-10-01 |  |  |  |  | 2025-10 | 315 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 28/0 | 2025-10-05 |  |  |  |  | 2025-10 | 311 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 18/0 | 2025-10-06 |  |  |  |  | 2025-10 | 310 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 54/3 | 2025-11-11 | 2026-03-01 | 2026-03-07 | 110 | 116 | 2025-11 | 274 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 54/7 | 2025-11-23 | 2026-03-16 | 2026-03-20 | 113 | 117 | 2025-11 | 262 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 51/4 | 2025-12-05 | 2026-05-18 | 2026-05-23 | 164 | 169 | 2025-12 | 250 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 51/2 | 2025-12-09 | 2026-05-10 | 2026-05-18 | 152 | 160 | 2025-12 | 246 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 54/5 | 2025-12-15 | 2026-03-12 | 2026-03-16 | 87 | 91 | 2025-12 | 240 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 52/4 | 2025-12-18 | 2026-04-01 | 2026-04-07 | 104 | 110 | 2025-12 | 237 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 51/5 | 2025-12-23 | 2026-05-23 | 2026-05-31 | 151 | 159 | 2025-12 | 232 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 54/8 | 2026-02-15 | 2026-03-24 | 2026-03-31 | 37 | 44 | 2026-02 | 178 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 52/3 | 2026-02-25 | 2026-05-31 | 2026-06-04 | 95 | 99 | 2026-02 | 168 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 55/1 | 2026-03-07 |  |  |  |  | 2026-03 | 158 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 55/2 | 2026-04-11 |  |  |  |  | 2026-04 | 123 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 52/2 | 2026-05-03 | 2026-06-17 | 2026-06-22 | 45 | 50 | 2026-05 | 101 | FALSE | FALSE | Yes | No | fallback_single_line | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 55/4 | 2026-05-04 |  |  |  |  | 2026-05 | 100 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 52/0 | 2026-05-05 |  |  |  |  | 2026-05 | 99 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 52/1 | 2026-05-10 |  |  |  |  | 2026-05 | 94 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 52/5 | 2026-05-11 |  |  |  |  | 2026-05 | 93 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 55/3 | 2026-05-15 |  |  |  |  | 2026-05 | 89 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 64/2 | 2026-05-16 |  |  |  |  | 2026-05 | 88 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 30/0 | 2026-05-17 |  |  |  |  | 2026-05 | 87 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 64/5 | 2026-05-19 |  |  |  |  | 2026-05 | 85 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 64/3 | 2026-05-21 |  |  |  |  | 2026-05 | 83 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 28/1 | 2026-05-22 |  |  |  |  | 2026-05 | 82 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 51/3 | 2026-05-23 |  |  |  |  | 2026-05 | 81 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 64/4 | 2026-05-25 |  |  |  |  | 2026-05 | 79 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 64/6 | 2026-05-29 |  |  |  |  | 2026-05 | 75 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 61/2 | 2026-05-30 |  |  |  |  | 2026-05 | 74 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 74/9 | 2026-05-30 |  |  |  |  | 2026-05 | 74 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 64/1 | 2026-06-01 |  |  |  |  | 2026-06 | 72 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 54/1 | 2026-06-07 |  |  |  |  | 2026-06 | 66 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 74/8 | 2026-06-07 |  |  |  |  | 2026-06 | 66 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 55/1 | 2026-06-09 |  |  |  |  | 2026-06 | 64 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 62/1 | 2026-06-09 |  |  |  |  | 2026-06 | 64 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 61/0 | 2026-06-14 |  |  |  |  | 2026-06 | 59 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 74/7 | 2026-06-14 |  |  |  |  | 2026-06 | 59 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 51/1 | 2026-06-17 |  |  |  |  | 2026-06 | 56 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 61/1 | 2026-06-18 |  |  |  |  | 2026-06 | 55 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 51/0 | 2026-06-25 |  |  |  |  | 2026-06 | 48 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 54/2 | 2026-06-27 |  |  |  |  | 2026-06 | 46 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 44/2 | 2026-07-08 |  |  |  |  | 2026-07 | 35 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 46/1 | 2026-07-10 |  |  |  |  | 2026-07 | 33 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 36/5 | 2026-07-16 |  |  |  |  | 2026-07 | 27 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 43/0 | 2026-07-17 |  |  |  |  | 2026-07 | 26 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 45/2 | 2026-07-20 |  |  |  |  | 2026-07 | 23 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 45/1 | 2026-08-01 |  |  |  |  | 2026-08 | 11 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 42/1 | 2026-08-07 |  |  |  |  | 2026-08 | 5 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 12/4 | 2026-08-09 |  |  |  |  | 2026-08 | 3 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 45/0 | 2026-08-11 |  |  |  |  | 2026-08 | 1 | FALSE | FALSE | No | No |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 601 | 81/2 | 2025-08-07 |  |  |  |  | 2025-08 | 370 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 82/1 | 2025-08-22 | 2026-01-11 | 2026-01-16 | 142 | 147 | 2025-08 | 355 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 81/1 | 2025-09-13 | 2026-02-10 | 2026-02-13 | 150 | 153 | 2025-09 | 333 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 80/5 | 2025-09-18 | 2026-01-15 | 2026-01-20 | 119 | 124 | 2025-09 | 328 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 80/1 | 2025-10-10 | 2026-01-19 | 2026-01-25 | 101 | 107 | 2025-10 | 306 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 59/5 | 2025-10-19 | 2026-01-22 | 2026-01-27 | 95 | 100 | 2025-10 | 297 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 84/3 | 2025-10-19 | 2026-01-16 | 2026-01-21 | 89 | 94 | 2025-10 | 297 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 59/4 | 2025-10-21 | 2026-01-15 | 2026-01-21 | 86 | 92 | 2025-10 | 295 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 84/4 | 2025-10-24 | 2026-01-19 | 2026-01-24 | 87 | 92 | 2025-10 | 292 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 60/2 | 2025-10-25 | 2026-01-27 | 2026-02-02 | 94 | 100 | 2025-10 | 291 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 80/4 | 2025-10-27 |  |  |  |  | 2025-10 | 289 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 77/4 | 2025-10-31 | 2026-01-07 | 2026-01-16 | 68 | 77 | 2025-10 | 285 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 77/10 | 2025-11-05 | 2026-01-26 | 2026-01-30 | 82 | 86 | 2025-11 | 280 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 59/2 | 2025-11-08 | 2025-12-22 | 2025-12-27 | 44 | 49 | 2025-11 | 277 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 77/7 | 2025-11-09 | 2026-01-17 | 2026-01-21 | 69 | 73 | 2025-11 | 276 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 77/8 | 2025-11-13 |  |  |  |  | 2025-11 | 272 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 60/3 | 2025-11-15 | 2026-06-03 | 2026-06-13 | 200 | 210 | 2025-11 | 270 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 77/3 | 2025-11-19 | 2025-12-22 | 2025-12-31 | 33 | 42 | 2025-11 | 266 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 60/8 | 2025-11-23 |  |  |  |  | 2025-11 | 262 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 77/1 | 2025-11-25 | 2026-01-01 | 2026-01-13 | 37 | 49 | 2025-11 | 260 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 59/1 | 2025-11-29 |  |  |  |  | 2025-11 | 256 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 77/2 | 2025-11-30 | 2025-12-25 | 2026-01-08 | 25 | 39 | 2025-11 | 255 | TRUE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 58/2 | 2025-12-03 | 2025-12-25 | 2026-01-10 | 22 | 38 | 2025-12 | 252 | TRUE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 58/1 | 2025-12-08 | 2026-01-02 | 2026-01-10 | 25 | 33 | 2025-12 | 247 | TRUE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 77/6 | 2025-12-12 |  |  |  |  | 2025-12 | 243 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 58/3 | 2025-12-14 | 2026-01-09 | 2026-01-14 | 26 | 31 | 2025-12 | 241 | TRUE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 99/7 | 2025-12-15 | 2026-01-12 | 2026-01-29 | 28 | 45 | 2025-12 | 240 | TRUE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 73/1 | 2025-12-18 |  |  |  |  | 2025-12 | 237 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 56/3 | 2025-12-19 | 2026-02-25 | 2026-03-08 | 68 | 79 | 2025-12 | 236 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 99/6 | 2025-12-20 | 2026-12-05 | 2026-02-09 | 350 | 51 | 2025-12 | 235 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 99/9 | 2025-12-23 | 2026-01-31 | 2026-02-16 | 39 | 55 | 2025-12 | 232 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 56/1 | 2025-12-24 |  |  |  |  | 2025-12 | 231 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 73/2 | 2025-12-24 |  |  |  |  | 2025-12 | 231 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 79/1 | 2025-12-25 |  |  |  |  | 2025-12 | 230 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 99/8 | 2025-12-26 | 2026-01-30 | 2026-02-03 | 35 | 39 | 2025-12 | 229 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 56/2 | 2025-12-27 | 2026-02-20 | 2026-02-26 | 55 | 61 | 2025-12 | 228 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 99/10 | 2025-12-29 | 2026-01-23 | 2026-01-27 | 25 | 29 | 2025-12 | 226 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 79/3 | 2025-12-30 | 2026-02-01 | 2026-02-04 | 33 | 36 | 2025-12 | 225 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 55/3 | 2025-12-31 | 2026-03-11 | 2026-03-18 | 70 | 77 | 2025-12 | 224 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 84/6 | 2025-12-31 |  |  |  |  | 2025-12 | 224 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 94/1 | 2025-12-31 |  |  |  |  | 2025-12 | 224 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 99/11 | 2025-12-31 | 2026-01-17 | 2026-01-21 | 17 | 21 | 2025-12 | 224 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 79/2 | 2026-01-05 | 2026-01-27 | 2026-01-31 | 22 | 26 | 2026-01 | 219 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 56/4 | 2026-01-06 | 2026-03-18 | 2026-03-25 | 71 | 78 | 2026-01 | 218 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 99/12 | 2026-01-06 |  |  |  |  | 2026-01 | 218 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 84/5 | 2026-01-08 | 2026-01-28 | 2026-02-05 | 20 | 28 | 2026-01 | 216 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 56/9 | 2026-01-10 | 2026-02-10 | 2026-02-13 | 31 | 34 | 2026-01 | 214 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 100/2 | 2026-01-12 | 2026-01-27 | 2026-01-31 | 15 | 19 | 2026-01 | 212 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 84/1 | 2026-01-12 | 2026-01-25 | 2026-01-28 | 13 | 16 | 2026-01 | 212 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 100/3 | 2026-01-14 | 2026-07-28 | 2026-08-09 | 195 | 207 | 2026-01 | 210 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 83/0 | 2026-01-14 |  |  |  |  | 2026-01 | 210 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 56/7 | 2026-01-16 | 2025-12-15 | 2025-12-20 | -32 | -27 | 2026-01 | 208 | FALSE | FALSE | Yes | Yes | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 56/6 | 2026-01-17 | 2026-02-03 | 2026-02-11 | 17 | 25 | 2026-01 | 207 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 56/8 | 2026-01-21 | 2026-02-06 | 2026-02-09 | 16 | 19 | 2026-01 | 203 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 101/2 | 2026-01-22 | 2026-02-05 | 2026-02-12 | 14 | 21 | 2026-01 | 202 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 85/2 | 2026-01-22 | 2026-01-31 | 2026-02-03 | 9 | 12 | 2026-01 | 202 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 100/1 | 2026-01-23 | 2026-01-30 | 2026-02-05 | 7 | 13 | 2026-01 | 201 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 100/4 | 2026-01-24 | 2026-03-20 | 2026-03-29 | 55 | 64 | 2026-01 | 200 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 102/4 | 2026-01-26 | 2026-02-14 | 2026-02-17 | 19 | 22 | 2026-01 | 198 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 59/0 | 2026-01-26 | 2026-05-19 | 2026-06-02 | 113 | 127 | 2026-01 | 198 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 84/0 | 2026-01-26 | 2026-02-05 | 2026-02-10 | 10 | 15 | 2026-01 | 198 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 100/5 | 2026-01-27 | 2026-02-08 | 2026-02-24 | 12 | 28 | 2026-01 | 197 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 101/1 | 2026-01-28 | 2026-02-16 | 2026-02-20 | 19 | 23 | 2026-01 | 196 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 55/1 | 2026-01-28 | 2026-02-14 | 2026-02-17 | 17 | 20 | 2026-01 | 196 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 53/2 | 2026-01-30 | 2026-02-25 | 2026-02-28 | 26 | 29 | 2026-01 | 194 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 101/0 | 2026-01-31 | 2026-02-20 | 2026-03-03 | 20 | 31 | 2026-01 | 193 | TRUE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 101/3 | 2026-01-31 | 2026-02-12 | 2026-02-16 | 12 | 16 | 2026-01 | 193 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 102/5 | 2026-01-31 | 2026-02-15 | 2026-02-19 | 15 | 19 | 2026-01 | 193 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 52/0 | 2026-01-31 | 2026-02-17 | 2026-02-21 | 17 | 21 | 2026-01 | 193 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 51/9 | 2026-02-05 | 2026-02-28 | 2026-03-05 | 23 | 28 | 2026-02 | 188 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 78/3 | 2026-02-06 |  |  |  |  | 2026-02 | 187 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 102/3 | 2026-02-08 | 2026-02-22 | 2026-02-24 | 14 | 16 | 2026-02 | 185 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 53/1 | 2026-02-08 | 2026-02-22 | 2026-02-25 | 14 | 17 | 2026-02 | 185 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 77/9 | 2026-02-10 | 2026-02-24 | 2026-02-28 | 14 | 18 | 2026-02 | 183 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 102/2 | 2026-02-11 | 2026-02-20 | 2026-02-22 | 9 | 11 | 2026-02 | 182 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 50/1 | 2026-02-12 |  |  |  |  | 2026-02 | 181 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 101/5 | 2026-02-14 | 2026-02-27 | 2026-03-02 | 13 | 16 | 2026-02 | 179 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 102/1 | 2026-02-14 | 2026-02-24 | 2026-02-27 | 10 | 13 | 2026-02 | 179 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 83/1 | 2026-02-15 | 2026-02-24 | 2026-03-09 | 9 | 22 | 2026-02 | 178 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 50/2 | 2026-02-17 | 2026-06-20 | 2026-06-25 | 123 | 128 | 2026-02 | 176 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 101/6 | 2026-02-22 | 2026-03-13 | 2026-03-16 | 19 | 22 | 2026-02 | 171 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 100/6 | 2026-02-24 | 2026-03-10 | 2026-03-16 | 14 | 20 | 2026-02 | 169 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 85/1 | 2026-02-25 | 2026-03-08 | 2026-03-11 | 11 | 14 | 2026-02 | 168 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 100/8 | 2026-02-26 | 2026-03-30 | 2026-03-04 | 32 | 6 | 2026-02 | 167 | FALSE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 100/7 | 2026-02-28 | 2026-03-16 | 2025-03-23 | 16 | -342 | 2026-02 | 165 | TRUE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 101/7 | 2026-02-28 | 2026-03-16 | 2026-03-20 | 16 | 20 | 2026-02 | 165 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 89/1 | 2026-03-03 |  |  |  |  | 2026-03 | 162 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 53/4 | 2026-03-06 | 2026-03-26 | 2026-04-01 | 20 | 26 | 2026-03 | 159 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 53/5 | 2026-03-08 | 2026-04-02 | 2026-04-07 | 25 | 30 | 2026-03 | 157 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 49/10 | 2026-03-11 | 2026-06-08 | 2026-06-08 | 89 | 89 | 2026-03 | 154 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 51/7 | 2026-03-13 | 2026-07-07 | 2026-07-11 | 116 | 120 | 2026-03 | 152 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 49/11 | 2026-03-14 | 2026-06-13 | 2026-06-19 | 91 | 97 | 2026-03 | 151 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 51/8 | 2026-03-14 | 2026-06-16 | 2026-06-23 | 94 | 101 | 2026-03 | 151 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 51/10 | 2026-03-17 | 2026-06-09 | 2026-06-16 | 84 | 91 | 2026-03 | 148 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 100/0 | 2026-03-18 | 2026-04-05 | 2026-04-12 | 18 | 25 | 2026-03 | 147 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 90/0 | 2026-03-18 |  |  |  |  | 2026-03 | 147 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 51/6 | 2026-03-19 | 2026-07-01 | 2026-07-06 | 104 | 109 | 2026-03 | 146 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 52/1 | 2026-03-22 | 2026-06-24 | 2026-06-30 | 94 | 100 | 2026-03 | 143 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 50/3 | 2026-03-25 | 2026-06-19 | 2026-06-25 | 86 | 92 | 2026-03 | 140 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 51/2 | 2026-03-27 | 2026-07-15 | 2026-07-19 | 110 | 114 | 2026-03 | 138 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 53/3 | 2026-03-31 |  |  |  |  | 2026-03 | 134 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 60/0 | 2026-04-06 | 2026-05-05 | 2026-05-18 | 29 | 42 | 2026-04 | 128 | TRUE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 70/1 | 2026-04-11 | 2026-06-15 | 2026-06-28 | 65 | 78 | 2026-04 | 123 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 53/0 | 2026-04-13 | 2026-07-12 | 2026-07-19 | 90 | 97 | 2026-04 | 121 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 70/2 | 2026-04-13 | 2026-06-29 | 2026-07-09 | 77 | 87 | 2026-04 | 121 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 50/0 | 2026-04-16 | 2025-06-26 | 2026-07-06 | -294 | 81 | 2026-04 | 118 | FALSE | FALSE | Yes | Yes | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 70/4 | 2026-04-16 |  |  |  |  | 2026-04 | 118 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 70/3 | 2026-04-18 |  |  |  |  | 2026-04 | 116 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 66/1 | 2026-04-21 |  |  |  |  | 2026-04 | 113 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 49/9 | 2026-04-23 | 2026-07-20 | 2026-07-29 | 88 | 97 | 2026-04 | 111 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 67/0 | 2026-04-26 | 2026-06-29 | 2026-07-05 | 64 | 70 | 2026-04 | 108 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 65/3 | 2026-04-29 | 2026-06-19 | 2026-06-23 | 51 | 55 | 2026-04 | 105 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 49/8 | 2026-04-30 | 2026-06-06 | 2026-06-12 | 37 | 43 | 2026-04 | 104 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 66/0 | 2026-05-03 | 2026-06-24 | 2026-06-28 | 52 | 56 | 2026-05 | 101 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 67/1 | 2026-05-05 | 2026-06-10 | 2026-06-19 | 36 | 45 | 2026-05 | 99 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 48/7 | 2026-05-10 |  |  |  |  | 2026-05 | 94 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 69/0 | 2026-05-13 | 2026-06-27 | 2026-07-04 | 45 | 52 | 2026-05 | 91 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 69/2 | 2026-05-16 | 2026-06-15 | 2026-06-26 | 30 | 41 | 2026-05 | 88 | TRUE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 48/3 | 2026-05-19 | 2026-06-26 | 2026-07-03 | 38 | 45 | 2026-05 | 85 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 69/1 | 2026-05-20 |  |  |  |  | 2026-05 | 84 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 68/2 | 2026-05-23 |  |  |  |  | 2026-05 | 81 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 48/2 | 2026-05-24 | 2026-07-04 | 2026-07-08 | 41 | 45 | 2026-05 | 80 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 68/0 | 2026-05-30 |  |  |  |  | 2026-05 | 74 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 56/5 | 2026-05-31 | 2026-06-14 | 2026-06-20 | 14 | 20 | 2026-05 | 73 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 72/1 | 2026-06-01 |  |  |  |  | 2026-06 | 72 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 73/0 | 2026-06-05 |  |  |  |  | 2026-06 | 68 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 56/10 | 2026-06-07 | 2026-06-21 | 2026-06-28 | 14 | 21 | 2026-06 | 66 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 75/2 | 2026-06-07 |  |  |  |  | 2026-06 | 66 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 75/3 | 2026-06-09 |  |  |  |  | 2026-06 | 64 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 56/12 | 2026-06-12 | 2026-06-29 | 2026-07-05 | 17 | 23 | 2026-06 | 61 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 75/1 | 2026-06-12 |  |  |  |  | 2026-06 | 61 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 77/5 | 2026-06-15 |  |  |  |  | 2026-06 | 58 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 49/0 | 2026-06-17 | 2026-07-29 | 2026-08-10 | 42 | 54 | 2026-06 | 56 | FALSE | FALSE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 60/4 | 2026-06-19 |  |  |  |  | 2026-06 | 54 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 49/1 | 2026-06-20 | 2026-07-07 | 2026-07-13 | 17 | 23 | 2026-06 | 53 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 51/1 | 2026-06-20 | 2026-07-09 | 2026-07-14 | 19 | 24 | 2026-06 | 53 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 48/0 | 2026-06-22 |  |  |  |  | 2026-06 | 51 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 99/3 | 2026-06-22 | 2026-07-07 | 2026-07-12 | 15 | 20 | 2026-06 | 51 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 51/4 | 2026-06-23 |  |  |  |  | 2026-06 | 50 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 56/11 | 2026-06-23 | 2026-07-06 | 2026-07-11 | 13 | 18 | 2026-06 | 50 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 99/4 | 2026-06-24 | 2026-07-17 | 2026-07-21 | 23 | 27 | 2026-06 | 49 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 102/0 | 2026-06-25 |  |  |  |  | 2026-06 | 48 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 51/5 | 2026-06-26 |  |  |  |  | 2026-06 | 47 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 99/2 | 2026-06-26 | 2026-07-13 | 2026-07-16 | 17 | 20 | 2026-06 | 47 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 99/1 | 2026-06-27 | 2026-07-13 | 2026-07-16 | 16 | 19 | 2026-06 | 46 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 49/2 | 2026-06-30 | 2026-07-14 | 2026-07-19 | 14 | 19 | 2026-06 | 43 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 56/0 | 2026-06-30 | 2026-07-12 | 2026-07-21 | 12 | 21 | 2026-06 | 43 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 99/0 | 2026-06-30 | 2026-07-09 | 2026-07-12 | 9 | 12 | 2026-06 | 43 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 51/0 | 2026-07-03 | 2026-07-20 | 2026-07-28 | 17 | 25 | 2026-07 | 40 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 99/5 | 2026-07-03 | 2026-07-21 | 2026-07-23 | 18 | 20 | 2026-07 | 40 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 98/4 | 2026-07-04 | 2026-07-10 | 2026-07-27 | 6 | 23 | 2026-07 | 39 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 52/2 | 2026-07-05 | 2026-07-20 | 2026-07-27 | 15 | 22 | 2026-07 | 38 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 98/3 | 2026-07-06 | 2026-07-22 | 2026-07-25 | 16 | 19 | 2026-07 | 37 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 72/0 | 2026-07-07 | 2026-07-26 | 2026-08-06 | 19 | 30 | 2026-07 | 36 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 51/3 | 2026-07-08 |  |  |  |  | 2026-07 | 35 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 98/2 | 2026-07-08 | 2026-07-17 | 2026-07-20 | 9 | 12 | 2026-07 | 35 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 52/3 | 2026-07-10 |  |  |  |  | 2026-07 | 33 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 57/0 | 2026-07-10 | 2026-07-22 | 2026-08-03 | 12 | 24 | 2026-07 | 33 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 71/0 | 2026-07-10 |  |  |  |  | 2026-07 | 33 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 98/5 | 2026-07-10 | 2026-07-24 | 2026-07-27 | 14 | 17 | 2026-07 | 33 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 98/1 | 2026-07-12 | 2026-07-28 | 2026-07-31 | 16 | 19 | 2026-07 | 31 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 63/2 | 2026-07-13 |  |  |  |  | 2026-07 | 30 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 58/0 | 2026-07-15 |  |  |  |  | 2026-07 | 28 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 98/0 | 2026-07-15 |  |  |  |  | 2026-07 | 28 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 76/0 | 2026-07-16 |  |  |  |  | 2026-07 | 27 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 101/4 | 2026-07-17 |  |  |  |  | 2026-07 | 26 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 49/3 | 2026-07-17 |  |  |  |  | 2026-07 | 26 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 65/2 | 2026-07-18 |  |  |  |  | 2026-07 | 25 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 54/0 | 2026-07-21 | 2026-07-28 | 2026-08-11 | 7 | 21 | 2026-07 | 22 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 78/1 | 2026-07-21 |  |  |  |  | 2026-07 | 22 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 53/6 | 2026-07-23 |  |  |  |  | 2026-07 | 20 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 101/9 | 2026-07-24 |  |  |  |  | 2026-07 | 19 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 49/4 | 2026-07-26 | 2026-07-30 | 2026-08-08 | 4 | 13 | 2026-07 | 17 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 78/0 | 2026-07-26 |  |  |  |  | 2026-07 | 17 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 97/1 | 2026-07-26 | 2026-08-06 | 2026-08-09 | 11 | 14 | 2026-07 | 17 | TRUE | TRUE | Yes | No | exact | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 52/4 | 2026-07-27 |  |  |  |  | 2026-07 | 16 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 63/1 | 2026-07-27 |  |  |  |  | 2026-07 | 16 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 96/8 | 2026-07-27 |  | 2026-08-09 |  | 13 | 2026-07 | 16 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 80/2 | 2026-07-28 |  |  |  |  | 2026-07 | 15 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 96/7 | 2026-07-30 |  |  |  |  | 2026-07 | 13 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 97/4 | 2026-08-01 |  |  |  |  | 2026-08 | 11 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 82/2 | 2026-08-03 |  |  |  |  | 2026-08 | 9 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 97/3 | 2026-08-03 |  |  |  |  | 2026-08 | 9 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 96/4 | 2026-08-06 |  |  |  |  | 2026-08 | 6 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 101/8 | 2026-08-08 |  |  |  |  | 2026-08 | 4 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 63/3 | 2026-08-09 |  |  |  |  | 2026-08 | 3 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 96/5 | 2026-08-09 |  |  |  |  | 2026-08 | 3 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 96/6 | 2026-08-11 |  |  |  |  | 2026-08 | 1 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 49/5 | 2026-08-12 |  |  |  |  | 2026-08 | 0 | FALSE | FALSE | No | No |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TB 408 | 0 | 2023-10-01 |  |  |  |  | 2023-10 | 1046 | FALSE | FALSE | No | No |  | TB 408 - DPR - 2026-07-30.xlsx | Foundation
TB 408 | 1 | 2024-09-01 |  |  |  |  | 2024-09 | 710 | FALSE | FALSE | No | No |  | TB 408 - DPR - 2026-07-30.xlsx | Foundation
TB 408 | 2 | 2024-11-01 |  |  |  |  | 2024-11 | 649 | FALSE | FALSE | No | No |  | TB 408 - DPR - 2026-07-30.xlsx | Foundation
TB 408 | 3 | 2024-11-01 |  |  |  |  | 2024-11 | 649 | FALSE | FALSE | No | No |  | TB 408 - DPR - 2026-07-30.xlsx | Foundation
TB 408 | 4 | 2024-11-01 |  |  |  |  | 2024-11 | 649 | FALSE | FALSE | No | No |  | TB 408 - DPR - 2026-07-30.xlsx | Foundation
TB 408 | 5 | 2024-12-01 |  |  |  |  | 2024-12 | 619 | FALSE | FALSE | No | No |  | TB 408 - DPR - 2026-07-30.xlsx | Foundation
TB 501 | 20/7 | 2024-08-12 | 2025-02-19 | 2025-02-21 | 191 | 193 | 2024-08 | 730 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 20/5 | 2024-08-16 | 2025-02-17 | 2025-02-19 | 185 | 187 | 2024-08 | 726 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 18/3 | 2024-08-19 | 2025-01-05 | 2025-01-06 | 139 | 140 | 2024-08 | 723 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 10/3 | 2024-09-09 | 2025-03-11 | 2025-03-13 | 183 | 185 | 2024-09 | 702 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 15/2 | 2024-09-11 | 2024-12-24 | 2024-12-25 | 104 | 105 | 2024-09 | 700 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 15/3 | 2024-09-15 | 2024-12-25 | 2024-12-26 | 101 | 102 | 2024-09 | 696 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 21/6 | 2024-09-19 | 2025-02-13 | 2025-02-14 | 147 | 148 | 2024-09 | 692 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 15/1 | 2024-09-22 | 2024-12-19 | 2024-12-23 | 88 | 92 | 2024-09 | 689 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 21/7 | 2024-09-23 | 2025-02-14 | 2025-02-16 | 144 | 146 | 2024-09 | 688 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 9/8 | 2024-09-28 | 2025-03-13 | 2025-03-15 | 166 | 168 | 2024-09 | 683 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 16/1 | 2024-10-01 | 2025-02-14 | 2025-02-16 | 136 | 138 | 2024-10 | 680 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 19/2 | 2024-10-04 | 2025-01-20 | 2025-01-21 | 108 | 109 | 2024-10 | 677 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 17/3 | 2024-10-06 | 2025-01-29 | 2025-01-31 | 115 | 117 | 2024-10 | 675 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 22/2 | 2024-10-09 | 2025-02-25 | 2025-02-26 | 139 | 140 | 2024-10 | 672 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | AP-16 | 2024-10-10 | 2025-02-14 | 2025-02-15 | 127 | 128 | 2024-10 | 671 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 17/2 | 2024-10-11 | 2025-02-01 | 2025-02-03 | 113 | 115 | 2024-10 | 670 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 16/3 | 2024-10-16 | 2025-02-18 | 2025-02-19 | 125 | 126 | 2024-10 | 665 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 18/5 | 2024-10-18 | 2025-01-03 | 2025-01-05 | 77 | 79 | 2024-10 | 663 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | AP-12 | 2024-10-19 | 2025-03-20 | 2025-03-22 | 152 | 154 | 2024-10 | 662 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | AP-11 | 2024-10-20 | 2025-04-30 | 2025-05-02 | 192 | 194 | 2024-10 | 661 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | AP-19 | 2024-10-20 | 2025-01-16 | 2025-01-17 | 88 | 89 | 2024-10 | 661 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 21/12 | 2024-10-21 | 2025-03-03 | 2025-03-05 | 133 | 135 | 2024-10 | 660 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | AP-18 | 2024-10-21 | 2025-02-21 | 2025-02-23 | 123 | 125 | 2024-10 | 660 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 10/4 | 2024-10-22 | 2025-04-23 | 2025-04-25 | 183 | 185 | 2024-10 | 659 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 20/6 | 2024-10-22 | 2025-03-05 | 2025-03-06 | 134 | 135 | 2024-10 | 659 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 15/4 | 2024-10-24 | 2025-02-05 | 2025-02-07 | 104 | 106 | 2024-10 | 657 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 17/1 | 2024-10-24 | 2025-02-18 | 2025-02-20 | 117 | 119 | 2024-10 | 657 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 18/11 | 2024-10-24 | 2025-01-28 | 2025-01-29 | 96 | 97 | 2024-10 | 657 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 20/3 | 2024-10-26 | 2025-02-28 | 2025-03-02 | 125 | 127 | 2024-10 | 655 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 21/3 | 2024-10-26 | 2025-02-18 | 2025-02-19 | 115 | 116 | 2024-10 | 655 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 11/1 | 2024-10-27 | 2025-03-13 | 2025-03-14 | 137 | 138 | 2024-10 | 654 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 16/2 | 2024-10-27 | 2025-02-22 | 2025-02-24 | 118 | 120 | 2024-10 | 654 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 20/4 | 2024-10-30 | 2025-03-02 | 2025-03-04 | 123 | 125 | 2024-10 | 651 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 9/9 | 2024-10-30 | 2025-05-19 | 2025-05-20 | 201 | 202 | 2024-10 | 651 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | AP-17 | 2024-10-31 | 2025-02-07 | 2025-02-09 | 99 | 101 | 2024-10 | 650 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 15/7 | 2024-11-03 | 2025-02-09 | 2025-02-11 | 98 | 100 | 2024-11 | 647 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 18/4 | 2024-11-04 | 2025-01-02 | 2025-01-03 | 59 | 60 | 2024-11 | 646 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 20/2 | 2024-11-05 | 2025-02-23 | 2025-02-25 | 110 | 112 | 2024-11 | 645 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 15/6 | 2024-11-06 | 2025-02-11 | 2025-02-12 | 97 | 98 | 2024-11 | 644 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 20/1 | 2024-11-08 | 2025-02-21 | 2025-02-23 | 105 | 107 | 2024-11 | 642 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | AP-14 | 2024-11-08 | 2025-05-08 | 2025-05-08 | 181 | 181 | 2024-11 | 642 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 15/8 | 2024-11-09 | 2025-02-11 | 2025-02-13 | 94 | 96 | 2024-11 | 641 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | AP-21 | 2024-11-09 | 2025-03-06 | 2025-03-08 | 117 | 119 | 2024-11 | 641 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 15/9 | 2024-11-12 | 2025-02-16 | 2025-02-17 | 96 | 97 | 2024-11 | 638 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | AP-20 | 2024-11-12 | 2025-02-26 | 2025-02-28 | 106 | 108 | 2024-11 | 638 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 18/6 | 2024-11-14 | 2025-01-07 | 2025-01-08 | 54 | 55 | 2024-11 | 636 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 10/2 | 2024-11-15 | 2025-03-17 | 2025-03-19 | 122 | 124 | 2024-11 | 635 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 21/5 | 2024-11-15 | 2025-02-10 | 2025-02-11 | 87 | 88 | 2024-11 | 635 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 21/4 | 2024-11-17 | 2025-02-07 | 2025-02-09 | 82 | 84 | 2024-11 | 633 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 19/3 | 2024-11-18 | 2025-01-22 | 2025-01-23 | 65 | 66 | 2024-11 | 632 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 21/10 | 2024-11-19 | 2025-02-23 | 2025-02-25 | 96 | 98 | 2024-11 | 631 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 21/8 | 2024-11-19 | 2025-02-19 | 2025-02-21 | 92 | 94 | 2024-11 | 631 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 18/7 | 2024-11-20 | 2025-01-14 | 2025-01-16 | 55 | 57 | 2024-11 | 630 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 19/5 | 2024-11-21 | 2025-05-09 | 2025-05-10 | 169 | 170 | 2024-11 | 629 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 19/4 | 2024-11-24 | 2025-01-24 | 2025-01-25 | 61 | 62 | 2024-11 | 626 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 18/9 | 2024-11-26 | 2025-01-11 | 2025-01-12 | 46 | 47 | 2024-11 | 624 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 19/1 | 2024-11-26 | 2025-01-18 | 2025-01-19 | 53 | 54 | 2024-11 | 624 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | AP-10 | 2024-11-26 | 2025-03-27 | 2025-03-29 | 121 | 123 | 2024-11 | 624 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 18/1 | 2024-11-29 | 2024-12-30 | 2024-12-31 | 31 | 32 | 2024-11 | 621 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 18/10 | 2024-11-30 | 2025-01-12 | 2025-01-13 | 43 | 44 | 2024-11 | 620 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 18/8 | 2024-11-30 | 2025-01-09 | 2025-01-10 | 40 | 41 | 2024-11 | 620 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 21/9 | 2024-12-04 | 2025-02-21 | 2025-02-23 | 79 | 81 | 2024-12 | 616 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5/2 | 2024-12-06 | 2025-03-26 | 2025-03-28 | 110 | 112 | 2024-12 | 614 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5/3 | 2024-12-07 | 2025-03-29 | 2025-03-31 | 112 | 114 | 2024-12 | 613 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 18/2 | 2024-12-08 | 2024-12-27 | 2024-12-29 | 19 | 21 | 2024-12 | 612 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 15/5 | 2024-12-09 | 2025-02-07 | 2025-02-09 | 60 | 62 | 2024-12 | 611 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 8B/0 | 2024-12-11 | 2025-04-20 | 2025-04-22 | 130 | 132 | 2024-12 | 609 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | AP-22 | 2024-12-11 | 2025-02-26 | 2025-02-28 | 77 | 79 | 2024-12 | 609 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 23/4 | 2024-12-15 | 2025-03-02 | 2025-03-03 | 77 | 78 | 2024-12 | 605 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | AP-15 | 2024-12-15 | 2025-02-04 | 2025-02-05 | 51 | 52 | 2024-12 | 605 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 14/9 | 2024-12-19 | 2025-02-01 | 2025-02-02 | 44 | 45 | 2024-12 | 601 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 22/1 | 2024-12-19 | 2025-02-27 | 2025-03-01 | 70 | 72 | 2024-12 | 601 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 4/14 | 2024-12-19 | 2025-03-16 | 2025-03-18 | 87 | 89 | 2024-12 | 601 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 8B/1 | 2024-12-19 | 2025-04-02 | 2025-04-03 | 104 | 105 | 2024-12 | 601 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 29A/2 | 2024-12-20 | 2025-02-19 | 2025-02-21 | 61 | 63 | 2024-12 | 600 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 4/13 | 2024-12-20 | 2025-03-13 | 2025-03-16 | 83 | 86 | 2024-12 | 600 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 23/2 | 2024-12-23 | 2025-03-01 | 2025-03-02 | 68 | 69 | 2024-12 | 597 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 14/7 | 2024-12-25 | 2025-01-29 | 2025-01-31 | 35 | 37 | 2024-12 | 595 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 29A/3 | 2024-12-25 | 2025-02-21 | 2025-02-23 | 58 | 60 | 2024-12 | 595 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 4/15 | 2024-12-25 | 2025-03-23 | 2025-03-25 | 88 | 90 | 2024-12 | 595 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 29A/1 | 2024-12-26 | 2025-02-18 | 2025-02-19 | 54 | 55 | 2024-12 | 594 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 8B/2 | 2024-12-27 | 2025-04-03 | 2025-04-04 | 97 | 98 | 2024-12 | 593 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 30/1 | 2024-12-28 | 2025-02-26 | 2025-02-28 | 60 | 62 | 2024-12 | 592 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | AP-30 | 2024-12-28 | 2025-02-23 | 2025-02-25 | 57 | 59 | 2024-12 | 592 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5A/0 | 2024-12-29 | 2025-03-30 | 2025-03-30 | 91 | 91 | 2024-12 | 591 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 30/6 | 2024-12-30 | 2025-03-02 | 2025-03-03 | 62 | 63 | 2024-12 | 590 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 14/8 | 2024-12-31 | 2025-01-30 | 2025-02-01 | 30 | 32 | 2024-12 | 589 | TRUE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 30/3 | 2024-12-31 | 2025-01-30 | 2025-02-01 | 30 | 32 | 2024-12 | 589 | TRUE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 8A/0 | 2025-01-04 | 2025-04-28 | 2025-04-30 | 114 | 116 | 2025-01 | 585 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 30/4 | 2025-01-05 | 2025-03-05 | 2025-03-06 | 59 | 60 | 2025-01 | 584 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5/1 | 2025-01-05 | 2025-04-12 | 2025-04-13 | 97 | 98 | 2025-01 | 584 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 30/2 | 2025-01-06 | 2025-03-02 | 2025-03-03 | 55 | 56 | 2025-01 | 583 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | AP-31 | 2025-01-07 | 2025-02-28 | 2025-03-02 | 52 | 54 | 2025-01 | 582 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 4/4 | 2025-01-08 | 2025-03-20 | 2025-03-22 | 71 | 73 | 2025-01 | 581 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 30/5 | 2025-01-10 | 2025-03-03 | 2025-03-05 | 52 | 54 | 2025-01 | 579 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 4/11 | 2025-01-12 | 2025-03-11 | 2025-03-12 | 58 | 59 | 2025-01 | 577 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 4/3 | 2025-01-14 | 2025-03-18 | 2025-03-20 | 63 | 65 | 2025-01 | 575 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 4/6 | 2025-01-14 | 2025-03-09 | 2025-03-10 | 54 | 55 | 2025-01 | 575 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 31/1 | 2025-01-15 | 2025-07-11 | 2025-07-13 | 177 | 179 | 2025-01 | 574 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 8D/0 | 2025-01-16 | 2025-04-15 | 2025-04-17 | 89 | 91 | 2025-01 | 573 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 4/2 | 2025-01-18 | 2025-03-21 | 2025-03-23 | 62 | 64 | 2025-01 | 571 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 29A/4 | 2025-01-19 | 2025-02-26 | 2025-02-27 | 38 | 39 | 2025-01 | 570 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 4/5 | 2025-01-19 | 2025-03-23 | 2025-03-25 | 63 | 65 | 2025-01 | 570 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 32/1 | 2025-01-23 | 2025-05-29 | 2025-05-30 | 126 | 127 | 2025-01 | 566 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 4/1 | 2025-01-24 | 2025-03-26 | 2025-03-26 | 61 | 61 | 2025-01 | 565 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 8E/2 | 2025-01-27 | 2025-06-09 | 2025-06-11 | 133 | 135 | 2025-01 | 562 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | AP-32 | 2025-01-29 | 2025-07-14 | 2025-07-16 | 166 | 168 | 2025-01 | 560 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 4/9 | 2025-01-30 | 2025-03-15 | 2025-03-17 | 44 | 46 | 2025-01 | 559 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 1D/0 | 2025-01-31 | 2025-03-29 | 2025-03-30 | 57 | 58 | 2025-01 | 558 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 1A/2 | 2025-02-02 | 2025-04-14 | 2025-04-16 | 71 | 73 | 2025-02 | 556 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 2/0 | 2025-02-02 | 2025-04-19 | 2025-04-21 | 76 | 78 | 2025-02 | 556 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 1A/1 | 2025-02-05 | 2025-04-04 | 2025-04-06 | 58 | 60 | 2025-02 | 553 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 4/0 | 2025-02-05 | 2025-05-28 | 2025-05-30 | 112 | 114 | 2025-02 | 553 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 1/2 | 2025-02-06 | 2025-03-29 | 2025-03-31 | 51 | 53 | 2025-02 | 552 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | AP-23 | 2025-02-06 | 2025-08-17 | 2025-08-19 | 192 | 194 | 2025-02 | 552 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 4/10 | 2025-02-08 | 2025-03-11 | 2025-03-13 | 31 | 33 | 2025-02 | 550 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 0/1 | 2025-02-09 | 2025-04-02 | 2025-04-04 | 52 | 54 | 2025-02 | 549 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 23/1 | 2025-02-10 | 2025-03-05 | 2025-03-06 | 23 | 24 | 2025-02 | 548 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 4/16 | 2025-02-12 | 2025-03-21 | 2025-03-23 | 37 | 39 | 2025-02 | 546 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 32/2 | 2025-02-15 | 2025-05-24 | 2025-05-26 | 98 | 100 | 2025-02 | 543 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 4/17 | 2025-02-15 | 2025-03-19 | 2025-03-20 | 32 | 33 | 2025-02 | 543 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 1A/0 | 2025-02-17 | 2025-04-21 | 2025-04-23 | 63 | 65 | 2025-02 | 541 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 3/0 | 2025-02-18 | 2025-05-01 | 2025-05-03 | 72 | 74 | 2025-02 | 540 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 21/11 | 2025-02-19 | 2025-05-10 | 2025-05-12 | 80 | 82 | 2025-02 | 539 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 0/0 | 2025-02-20 | 2025-04-07 | 2025-04-09 | 46 | 48 | 2025-02 | 538 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 1D/1 | 2025-02-22 | 2025-03-27 | 2025-03-28 | 33 | 34 | 2025-02 | 536 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 1/1 | 2025-02-23 | 2025-03-31 | 2025-04-02 | 36 | 38 | 2025-02 | 535 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 1C/1 | 2025-02-25 | 2025-05-17 | 2025-05-19 | 81 | 83 | 2025-02 | 533 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 20/8 | 2025-02-25 | 2025-11-10 | 2025-11-12 | 258 | 260 | 2025-02 | 533 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 23/3 | 2025-02-28 | 2025-05-26 | 2025-05-28 | 87 | 89 | 2025-02 | 530 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 1B/0 | 2025-03-05 | 2025-04-25 | 2025-04-27 | 51 | 53 | 2025-03 | 525 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 7/1 | 2025-03-09 | 2025-04-05 | 2025-04-06 | 27 | 28 | 2025-03 | 521 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 7/0 | 2025-03-16 | 2025-04-08 | 2025-04-10 | 23 | 25 | 2025-03 | 514 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 7/2 | 2025-03-16 | 2025-04-05 | 2025-04-07 | 20 | 22 | 2025-03 | 514 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | AP-26 | 2025-03-16 | 2025-06-04 | 2025-06-06 | 80 | 82 | 2025-03 | 514 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 1E/0 | 2025-03-22 | 2025-05-25 | 2025-05-27 | 64 | 66 | 2025-03 | 508 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 7/3 | 2025-03-23 | 2025-04-21 | 2025-04-23 | 29 | 31 | 2025-03 | 507 | TRUE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 1/0 | 2025-03-27 | 2025-04-11 | 2025-04-13 | 15 | 17 | 2025-03 | 503 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5/0 | 2025-03-28 | 2025-07-14 | 2025-07-16 | 108 | 110 | 2025-03 | 502 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | AP-27 | 2025-04-03 | 2025-07-24 | 2025-07-26 | 112 | 114 | 2025-04 | 496 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | AP-13 | 2025-04-08 | 2025-05-23 | 2025-05-24 | 45 | 46 | 2025-04 | 491 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 21/1 | 2025-04-15 | 2025-05-17 | 2025-05-17 | 32 | 32 | 2025-04 | 484 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | AP-25 | 2025-04-17 | 2025-07-24 | 2025-07-26 | 98 | 100 | 2025-04 | 482 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 10/1 | 2025-04-19 | 2025-05-21 | 2025-05-22 | 32 | 33 | 2025-04 | 480 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 21/2 | 2025-04-21 | 2025-05-14 | 2025-05-15 | 23 | 24 | 2025-04 | 478 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 8E/5 | 2025-04-25 | 2025-06-25 | 2025-06-27 | 61 | 63 | 2025-04 | 474 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 8E/4 | 2025-04-26 | 2025-06-21 | 2025-06-23 | 56 | 58 | 2025-04 | 473 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 21/13 | 2025-04-27 | 2025-05-17 | 2025-05-19 | 20 | 22 | 2025-04 | 472 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | AP-24 | 2025-04-29 | 2025-06-09 | 2025-06-11 | 41 | 43 | 2025-04 | 470 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 23/5 | 2025-04-30 | 2025-05-29 | 2025-05-31 | 29 | 31 | 2025-04 | 469 | TRUE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 29A/0 | 2025-05-10 | 2025-08-11 | 2025-08-14 | 93 | 96 | 2025-05 | 459 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 8C/0 | 2025-05-12 | 2025-06-04 | 2025-06-06 | 23 | 25 | 2025-05 | 457 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 4/12 | 2025-05-13 | 2025-06-04 | 2025-06-04 | 22 | 22 | 2025-05 | 456 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | AP-29 | 2025-05-14 | 2025-06-13 | 2025-06-15 | 30 | 32 | 2025-05 | 455 | TRUE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 9/1 | 2025-05-17 | 2025-07-04 | 2025-07-06 | 48 | 50 | 2025-05 | 452 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 8/0 | 2025-05-18 | 2025-06-06 | 2025-06-08 | 19 | 21 | 2025-05 | 451 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | AP-9 | 2025-05-18 | 2025-07-02 | 2025-07-04 | 45 | 47 | 2025-05 | 451 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 9/2 | 2025-05-22 | 2025-07-01 | 2025-07-03 | 40 | 42 | 2025-05 | 447 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 9/6 | 2025-05-23 | 2025-06-27 | 2025-06-29 | 35 | 37 | 2025-05 | 446 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 28/1 | 2025-05-24 | 2025-10-18 | 2025-10-22 | 147 | 151 | 2025-05 | 445 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 8E/10 | 2025-05-25 | 2025-06-13 | 2025-06-14 | 19 | 20 | 2025-05 | 444 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 9/5 | 2025-05-25 | 2025-07-28 | 2025-07-30 | 64 | 66 | 2025-05 | 444 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | AP-28 | 2025-05-25 | 2025-06-15 | 2025-06-17 | 21 | 23 | 2025-05 | 444 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 8E/8 | 2025-05-26 | 2025-06-20 | 2025-06-22 | 25 | 27 | 2025-05 | 443 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 8E/12 | 2025-05-27 | 2025-07-06 | 2025-07-08 | 40 | 42 | 2025-05 | 442 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 8E/9 | 2025-05-29 | 2025-06-17 | 2025-06-19 | 19 | 21 | 2025-05 | 440 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 9/7 | 2025-05-29 | 2025-07-01 | 2025-07-01 | 33 | 33 | 2025-05 | 440 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 8E/11 | 2025-05-30 | 2025-06-15 | 2025-06-17 | 16 | 18 | 2025-05 | 439 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 8E/6 | 2025-06-04 | 2025-06-20 | 2025-06-22 | 16 | 18 | 2025-06 | 434 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 9/3 | 2025-06-05 | 2025-07-03 | 2025-07-05 | 28 | 30 | 2025-06 | 433 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 9/4 | 2025-06-05 | 2025-07-07 | 2025-07-07 | 32 | 32 | 2025-06 | 433 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 8E/3 | 2025-06-06 | 2025-06-22 | 2025-06-24 | 16 | 18 | 2025-06 | 432 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 8E/1 | 2025-06-08 | 2025-06-23 | 2025-06-25 | 15 | 17 | 2025-06 | 430 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 28/2 | 2025-06-29 | 2025-08-14 | 2025-08-17 | 46 | 49 | 2025-06 | 409 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 17/0 | 2025-07-10 | 2025-08-28 | 2025-08-31 | 49 | 52 | 2025-07 | 398 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 8D/5 | 2025-08-17 | 2025-11-03 | 2025-11-05 | 78 | 80 | 2025-08 | 360 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 8D/6 | 2025-08-23 | 2025-11-05 | 2025-11-07 | 74 | 76 | 2025-08 | 354 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 8D/4 | 2025-08-30 | 2025-11-02 | 2025-11-04 | 64 | 66 | 2025-08 | 347 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 4/8 | 2025-09-03 | 2025-12-22 | 2025-12-24 | 110 | 112 | 2025-09 | 343 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 14/1 | 2025-09-07 | 2025-10-26 | 2025-10-26 | 49 | 49 | 2025-09 | 339 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 8D/3 | 2025-09-10 | 2025-11-26 | 2025-11-27 | 77 | 78 | 2025-09 | 336 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 14/3 | 2025-09-12 | 2025-10-27 | 2025-10-29 | 45 | 47 | 2025-09 | 334 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 14/2 | 2025-09-20 | 2025-10-21 | 2025-10-23 | 31 | 33 | 2025-09 | 326 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 8E/0 | 2025-09-21 | 2025-11-07 | 2025-11-09 | 47 | 49 | 2025-09 | 325 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 4/7 | 2025-09-26 | 2026-01-19 | 2026-01-23 | 115 | 119 | 2025-09 | 320 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 14/4 | 2025-09-30 | 2025-11-14 | 2025-11-16 | 45 | 47 | 2025-09 | 316 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 14/5 | 2025-10-08 | 2025-10-29 | 2025-10-31 | 21 | 23 | 2025-10 | 308 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5A/1 | 2025-10-08 | 2025-11-23 | 2025-11-24 | 46 | 47 | 2025-10 | 308 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5A/2 | 2025-10-12 | 2025-11-22 | 2025-11-23 | 41 | 42 | 2025-10 | 304 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5B/0 | 2025-10-17 | 2025-11-21 | 2025-11-22 | 35 | 36 | 2025-10 | 299 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 16/0 | 2025-10-23 | 2025-11-12 | 2025-12-13 | 20 | 51 | 2025-10 | 293 | TRUE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 16/1 | 2025-10-27 | 2025-11-14 | 2025-11-17 | 18 | 21 | 2025-10 | 289 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 14/6 | 2025-11-05 | 2025-11-15 | 2025-11-17 | 10 | 12 | 2025-11 | 280 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 18/0 | 2025-11-07 | 2025-12-15 | 2025-12-17 | 38 | 40 | 2025-11 | 278 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 13/1 | 2025-11-08 | 2025-11-10 | 2025-11-12 | 2 | 4 | 2025-11 | 277 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 16/2 | 2025-11-15 | 2025-11-17 | 2025-11-20 | 2 | 5 | 2025-11 | 270 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 8E/7 | 2025-11-16 | 2025-11-29 | 2025-12-03 | 13 | 17 | 2025-11 | 269 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 8D/1 | 2025-11-20 | 2025-11-27 | 2025-11-29 | 7 | 9 | 2025-11 | 265 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 6/0 | 2025-11-26 | 2025-12-18 | 2025-12-20 | 22 | 24 | 2025-11 | 259 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 8D/2 | 2025-12-03 | 2025-12-07 | 2025-12-08 | 4 | 5 | 2025-12 | 252 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 8D/0A | 2025-12-07 | 2025-12-04 | 2025-12-07 | -3 | 0 | 2025-12 | 248 | FALSE | FALSE | Yes | Yes | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 10/0 | 2025-12-13 | 2025-12-28 | 2025-12-30 | 15 | 17 | 2025-12 | 242 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 15/2 | 2025-12-15 | 2025-12-27 | 2025-12-27 | 12 | 12 | 2025-12 | 240 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 11/0 | 2025-12-16 | 2026-01-11 | 2026-01-17 | 26 | 32 | 2025-12 | 239 | TRUE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 15/1 | 2025-12-16 | 2025-12-31 | 2026-01-02 | 15 | 17 | 2025-12 | 239 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 12/0 | 2025-12-17 | 2026-01-06 | 2026-01-07 | 20 | 21 | 2025-12 | 238 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 15/3 | 2025-12-19 | 2025-12-25 | 2025-12-26 | 6 | 7 | 2025-12 | 236 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 13/0 | 2025-12-25 | 2026-01-03 | 2026-01-05 | 9 | 11 | 2025-12 | 230 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 14/0 | 2025-12-28 | 2026-01-08 | 2026-01-10 | 11 | 13 | 2025-12 | 227 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 12/1 | 2026-01-10 | 2026-01-30 | 2026-01-31 | 20 | 21 | 2026-01 | 214 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 13/2 | 2026-01-10 | 2026-01-24 | 2026-01-27 | 14 | 17 | 2026-01 | 214 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 13/1 | 2026-01-14 | 2026-01-28 | 2026-01-29 | 14 | 15 | 2026-01 | 210 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 8/0 | 2026-01-21 | 2026-02-01 | 2026-02-03 | 11 | 13 | 2026-01 | 203 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 9/0 | 2026-01-21 | 2026-02-04 | 2026-02-06 | 14 | 16 | 2026-01 | 203 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 7/0 | 2026-01-25 | 2026-02-06 | 2026-02-08 | 12 | 14 | 2026-01 | 199 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 6/2 | 2026-01-27 | 2026-03-16 | 2026-03-18 | 48 | 50 | 2026-01 | 197 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 6/1 | 2026-01-30 | 2026-02-09 | 2026-02-11 | 10 | 12 | 2026-01 | 194 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 6/3 | 2026-01-31 | 2026-02-14 | 2026-02-16 | 14 | 16 | 2026-01 | 193 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5/0 | 2026-02-05 | 2026-03-14 | 2026-03-16 | 37 | 39 | 2026-02 | 188 | FALSE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 15/0 | 2026-02-10 | 2026-02-20 | 2026-02-24 | 10 | 14 | 2026-02 | 183 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 6/0 | 2026-02-19 | 2026-02-17 | 2026-02-19 | -2 | 0 | 2026-02 | 174 | FALSE | FALSE | Yes | Yes | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 1C/0 | 2026-02-24 | 2026-03-20 | 2026-03-25 | 24 | 29 | 2026-02 | 169 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 4/0 | 2026-03-08 | 2026-03-16 | 2026-03-19 | 8 | 11 | 2026-03 | 157 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 6/4 | 2026-03-14 | 2026-03-18 | 2026-03-20 | 4 | 6 | 2026-03 | 151 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 4/1 | 2026-03-16 | 2026-03-20 | 2026-03-22 | 4 | 6 | 2026-03 | 149 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 4/2 | 2026-03-17 | 2026-03-22 | 2026-03-23 | 5 | 6 | 2026-03 | 148 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 33/0 (New) | 2026-04-09 | 2026-05-08 | 2026-05-12 | 29 | 33 | 2026-04 | 125 | TRUE | FALSE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 3/1 | 2026-04-12 | 2026-04-18 | 2026-04-22 | 6 | 10 | 2026-04 | 122 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 3/0 | 2026-04-14 | 2026-04-24 | 2026-04-30 | 10 | 16 | 2026-04 | 120 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 33/1 (New) | 2026-04-20 | 2026-05-10 | 2026-05-15 | 20 | 25 | 2026-04 | 114 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 34/0 (New) | 2026-04-30 | 2026-05-16 | 2026-05-21 | 16 | 21 | 2026-04 | 104 | TRUE | TRUE | Yes | No | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 2/0 | 2026-06-19 | 2026-06-17 | 2026-06-19 | -2 | 0 | 2026-06 | 54 | FALSE | FALSE | Yes | Yes | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | SC-2 | 2026-06-19 |  |  |  |  | 2026-06 | 54 | FALSE | FALSE | No | No |  | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 1/0 | 2026-06-23 | 2026-06-20 | 2026-06-23 | -3 | 0 | 2026-06 | 50 | FALSE | FALSE | Yes | Yes | exact | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | SC-1 | 2026-07-24 |  | 2026-07-24 |  | 0 | 2026-07 | 19 | FALSE | FALSE | No | No |  | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 507 | 83/1 | 2025-01-17 | 2025-08-29 | 2025-09-11 | 224 | 237 | 2025-01 | 572 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 75/7 | 2025-01-27 | 2025-06-29 | 2025-07-05 | 153 | 159 | 2025-01 | 562 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 75/6 | 2025-02-02 | 2025-07-15 | 2025-07-18 | 163 | 166 | 2025-02 | 556 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 75/4 | 2025-02-05 | 2025-07-22 | 2025-07-25 | 167 | 170 | 2025-02 | 553 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 75/5 | 2025-02-05 | 2025-07-19 | 2025-07-22 | 164 | 167 | 2025-02 | 553 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 77/1 | 2025-02-06 | 2025-07-11 | 2025-07-14 | 155 | 158 | 2025-02 | 552 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 77/2 | 2025-02-09 | 2025-06-23 | 2025-06-28 | 134 | 139 | 2025-02 | 549 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 75/3 | 2025-02-10 | 2025-07-25 | 2025-07-28 | 165 | 168 | 2025-02 | 548 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 77/3 | 2025-02-14 | 2025-07-07 | 2025-07-10 | 143 | 146 | 2025-02 | 544 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 75/1 | 2025-02-17 | 2025-08-01 | 2025-08-04 | 165 | 168 | 2025-02 | 541 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 77/4 | 2025-02-17 | 2025-06-28 | 2025-07-02 | 131 | 135 | 2025-02 | 541 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 75/2 | 2025-02-18 | 2025-07-29 | 2025-07-31 | 161 | 163 | 2025-02 | 540 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 77/5 | 2025-02-19 | 2025-07-03 | 2025-07-05 | 134 | 136 | 2025-02 | 539 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 73/3 | 2025-02-22 | 2025-08-01 | 2025-08-08 | 160 | 167 | 2025-02 | 536 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 86/2 | 2025-02-22 | 2026-05-21 | 2026-05-30 | 453 | 462 | 2025-02 | 536 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 79/1 | 2025-02-23 | 2025-11-25 | 2025-11-30 | 275 | 280 | 2025-02 | 535 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 73/2 | 2025-02-25 | 2025-08-08 | 2025-08-16 | 164 | 172 | 2025-02 | 533 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 95A/1 | 2025-02-25 | 2025-08-23 | 2025-09-02 | 179 | 189 | 2025-02 | 533 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 80/1 | 2025-02-27 | 2025-08-23 | 2025-08-28 | 177 | 182 | 2025-02 | 531 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 66/1 | 2025-02-28 | 2026-03-22 | 2026-03-29 | 387 | 394 | 2025-02 | 530 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 74/1 | 2025-02-28 | 2025-07-24 | 2025-07-31 | 146 | 153 | 2025-02 | 530 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 96/1 | 2025-02-28 | 2025-09-01 | 2025-09-15 | 185 | 199 | 2025-02 | 530 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 76/1 | 2025-03-02 | 2025-09-19 | 2025-09-27 | 201 | 209 | 2025-03 | 528 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 66/2 | 2025-03-06 |  |  |  |  | 2025-03 | 524 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 64/3 | 2025-03-07 |  |  |  |  | 2025-03 | 523 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 96/2 | 2025-03-07 |  |  |  |  | 2025-03 | 523 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 81/2 | 2025-03-08 | 2025-09-01 | 2025-09-05 | 177 | 181 | 2025-03 | 522 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 86/1 | 2025-03-09 | 2025-08-23 | 2025-08-28 | 167 | 172 | 2025-03 | 521 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 64/4 | 2025-03-10 |  |  |  |  | 2025-03 | 520 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 85/1 | 2025-03-10 | 2025-08-17 | 2025-08-23 | 160 | 166 | 2025-03 | 520 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 99/1 | 2025-03-10 |  |  |  |  | 2025-03 | 520 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 66/3 | 2025-03-11 |  |  |  |  | 2025-03 | 519 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 87/1 | 2025-03-24 | 2026-06-27 | 2026-07-07 | 460 | 470 | 2025-03 | 506 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 64/7 | 2025-03-26 | 2026-03-17 | 2026-03-21 | 356 | 360 | 2025-03 | 504 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 64/6 | 2025-03-30 |  |  |  |  | 2025-03 | 500 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 87/2 | 2025-03-30 | 2026-06-15 | 2026-06-26 | 442 | 453 | 2025-03 | 500 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 98A/1 | 2025-03-30 | 2025-09-23 | 2025-10-01 | 177 | 185 | 2025-03 | 500 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 64/5 | 2025-03-31 |  |  |  |  | 2025-03 | 499 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 98/1 | 2025-04-04 | 2025-09-15 | 2025-09-24 | 164 | 173 | 2025-04 | 495 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 71/1 | 2025-04-09 |  |  |  |  | 2025-04 | 490 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 91/1 | 2025-04-13 | 2026-02-25 | 2026-02-27 | 318 | 320 | 2025-04 | 486 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 91/2 | 2025-04-16 |  |  |  |  | 2025-04 | 483 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 51/2 | 2025-04-17 |  |  |  |  | 2025-04 | 482 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 119/1 | 2025-04-18 | 2025-12-18 | 2025-12-21 | 244 | 247 | 2025-04 | 481 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 95/2 | 2025-04-20 |  |  |  |  | 2025-04 | 479 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 119/2 | 2025-04-22 | 2025-12-13 | 2025-12-18 | 235 | 240 | 2025-04 | 477 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 51/3 | 2025-04-23 |  |  |  |  | 2025-04 | 476 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 99/2 | 2025-04-25 |  |  |  |  | 2025-04 | 474 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 104B/1 | 2025-04-29 |  |  |  |  | 2025-04 | 470 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 62/4 | 2025-04-29 |  |  |  |  | 2025-04 | 470 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 81/4 | 2025-04-29 | 2025-09-05 | 2025-09-09 | 129 | 133 | 2025-04 | 470 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 104B/2 | 2025-05-05 | 2025-10-18 | 2025-12-21 | 166 | 230 | 2025-05 | 464 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 105/1 | 2025-05-15 | 2026-04-30 | 2025-05-10 | 350 | -5 | 2025-05 | 454 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 100/1 | 2025-05-18 | 2026-06-02 | 2026-06-14 | 380 | 392 | 2025-05 | 451 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 81/5 | 2025-05-21 | 2025-12-17 | 2025-12-26 | 210 | 219 | 2025-05 | 448 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 97/0 | 2025-05-23 | 2025-09-01 | 2025-09-11 | 101 | 111 | 2025-05 | 446 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 99C/2 | 2025-05-25 | 2026-06-17 | 2026-06-24 | 388 | 395 | 2025-05 | 444 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 105/0 | 2025-05-28 | 2026-08-04 |  | 433 |  | 2025-05 | 441 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 98A/0 | 2025-05-29 | 2025-09-26 | 2025-10-15 | 120 | 139 | 2025-05 | 440 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 62/5 | 2025-05-31 |  |  |  |  | 2025-05 | 438 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 81/3 | 2025-06-04 | 2025-08-29 | 2025-08-31 | 86 | 88 | 2025-06 | 434 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 120/1 | 2025-06-05 | 2025-12-21 | 2025-12-25 | 199 | 203 | 2025-06 | 433 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 96/0 | 2025-06-06 |  |  |  |  | 2025-06 | 432 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 75/0 | 2025-06-07 | 2025-08-04 | 2025-08-09 | 58 | 63 | 2025-06 | 431 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 147/2 | 2025-06-08 | 2025-10-15 | 2025-10-19 | 129 | 133 | 2025-06 | 430 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 82/2 | 2025-06-10 | 2025-10-19 | 2025-10-24 | 131 | 136 | 2025-06 | 428 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 147/5 | 2025-06-12 | 2025-10-27 | 2025-10-28 | 137 | 138 | 2025-06 | 426 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 79/0 | 2025-06-12 | 2025-08-17 | 2025-08-23 | 66 | 72 | 2025-06 | 426 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 119/0 | 2025-06-15 | 2026-07-28 | 2026-08-05 | 408 | 416 | 2025-06 | 423 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 147/0 | 2025-06-15 | 2025-10-10 | 2025-10-12 | 117 | 119 | 2025-06 | 423 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 82/1 | 2025-06-15 | 2025-09-09 | 2025-09-14 | 86 | 91 | 2025-06 | 423 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 147/4 | 2025-06-16 | 2025-10-28 | 2025-10-31 | 134 | 137 | 2025-06 | 422 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 78/0 | 2025-06-16 | 2025-08-10 | 2025-08-16 | 55 | 61 | 2025-06 | 422 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 74/0 | 2025-06-20 | 2026-07-27 | 2026-08-04 | 402 | 410 | 2025-06 | 418 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 147/1 | 2025-06-21 | 2025-10-19 | 2025-10-22 | 120 | 123 | 2025-06 | 417 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 147/7 | 2025-06-22 | 2025-09-30 | 2025-10-03 | 100 | 103 | 2025-06 | 416 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 95A/0 | 2025-06-23 | 2026-01-07 | 2026-01-10 | 198 | 201 | 2025-06 | 415 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 146/2 | 2025-06-25 | 2025-10-03 | 2025-10-05 | 100 | 102 | 2025-06 | 413 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 147/3 | 2025-06-25 | 2025-10-12 | 2025-10-15 | 109 | 112 | 2025-06 | 413 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 73/0 | 2025-06-26 | 2025-12-19 | 2025-12-24 | 176 | 181 | 2025-06 | 412 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 86/0 | 2025-06-27 | 2025-12-28 | 2025-12-31 | 184 | 187 | 2025-06 | 411 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 114/0 | 2025-06-30 | 2026-01-20 | 2026-01-24 | 204 | 208 | 2025-06 | 408 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 146/1 | 2025-06-30 | 2025-09-30 | 2025-10-03 | 92 | 95 | 2025-06 | 408 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 147/8 | 2025-06-30 | 2025-10-19 | 2025-10-22 | 111 | 114 | 2025-06 | 408 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 72/2 | 2025-06-30 | 2025-12-06 | 2025-12-16 | 159 | 169 | 2025-06 | 408 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 95/1 | 2025-07-04 | 2025-12-27 | 2025-12-30 | 176 | 179 | 2025-07 | 404 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 148/3 | 2025-07-05 | 2025-08-29 | 2025-09-04 | 55 | 61 | 2025-07 | 403 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 106/0 | 2025-07-06 |  |  |  |  | 2025-07 | 402 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 146/0 | 2025-07-08 | 2025-10-05 | 2025-10-10 | 89 | 94 | 2025-07 | 400 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 148/1 | 2025-07-08 | 2025-10-23 | 2025-10-27 | 107 | 111 | 2025-07 | 400 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 114/1 | 2025-07-10 | 2025-09-24 | 2025-09-26 | 76 | 78 | 2025-07 | 398 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 148/2 | 2025-07-10 | 2025-09-05 | 2025-09-10 | 57 | 62 | 2025-07 | 398 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 80/0 | 2025-07-10 | 2025-11-10 | 2025-11-15 | 123 | 128 | 2025-07 | 398 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 141/1 | 2025-07-11 | 2025-09-27 | 2025-09-30 | 78 | 81 | 2025-07 | 397 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 95/0 | 2025-07-11 | 2025-11-29 | 2025-12-07 | 141 | 149 | 2025-07 | 397 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 148/4 | 2025-07-12 | 2025-08-27 | 2025-08-29 | 46 | 48 | 2025-07 | 396 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 141/2 | 2025-07-13 | 2025-09-24 | 2025-09-27 | 73 | 76 | 2025-07 | 395 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 145/4 | 2025-07-13 | 2025-09-20 | 2025-09-30 | 69 | 79 | 2025-07 | 395 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 125/1 | 2025-07-14 |  |  |  |  | 2025-07 | 394 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 133/6 | 2025-07-14 | 2025-09-23 | 2025-09-29 | 71 | 77 | 2025-07 | 394 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 148/5 | 2025-07-15 | 2025-09-11 | 2025-09-14 | 58 | 61 | 2025-07 | 393 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 109A/0 | 2025-07-16 | 2025-11-13 | 2025-11-20 | 120 | 127 | 2025-07 | 392 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 113A/0 | 2025-07-16 | 2025-09-14 | 2025-09-21 | 60 | 67 | 2025-07 | 392 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 133/5 | 2025-07-16 | 2025-11-15 | 2025-11-20 | 122 | 127 | 2025-07 | 392 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 145/2 | 2025-07-16 | 2025-09-09 | 2025-09-14 | 55 | 60 | 2025-07 | 392 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 142/0 | 2025-07-17 | 2025-10-01 | 2025-10-07 | 76 | 82 | 2025-07 | 391 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 115/0 | 2025-07-18 | 2025-10-08 | 2025-10-13 | 82 | 87 | 2025-07 | 390 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 148/6 | 2025-07-18 | 2025-09-14 | 2025-09-19 | 58 | 63 | 2025-07 | 390 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 77/0 | 2025-07-19 | 2025-11-01 | 2025-11-05 | 105 | 109 | 2025-07 | 389 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 133/4 | 2025-07-21 | 2025-10-11 | 2025-10-15 | 82 | 86 | 2025-07 | 387 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 143/0 | 2025-07-21 | 2025-09-27 | 2025-09-30 | 68 | 71 | 2025-07 | 387 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 145/1 | 2025-07-21 | 2025-08-27 | 2025-09-09 | 37 | 50 | 2025-07 | 387 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 148/7 | 2025-07-23 | 2025-09-20 | 2025-09-23 | 59 | 62 | 2025-07 | 385 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 125/0 | 2025-07-24 |  |  |  |  | 2025-07 | 384 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 133/3 | 2025-07-24 | 2025-09-17 | 2025-09-22 | 55 | 60 | 2025-07 | 384 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 94/0 | 2025-07-24 | 2026-08-08 |  | 380 |  | 2025-07 | 384 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 145/3 | 2025-07-25 | 2025-09-14 | 2025-09-19 | 51 | 56 | 2025-07 | 383 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 126/2 | 2025-07-26 | 2025-12-06 | 2025-12-12 | 133 | 139 | 2025-07 | 382 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 143/3 | 2025-07-26 | 2025-09-21 | 2025-09-23 | 57 | 59 | 2025-07 | 382 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 133/8 | 2025-07-27 | 2025-10-05 | 2025-10-11 | 70 | 76 | 2025-07 | 381 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 149B/1 | 2025-07-27 | 2025-09-24 | 2025-09-27 | 59 | 62 | 2025-07 | 381 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 79/2 | 2025-07-27 | 2025-09-11 | 2025-09-15 | 46 | 50 | 2025-07 | 381 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 110/0 | 2025-07-28 | 2025-10-13 | 2025-10-18 | 77 | 82 | 2025-07 | 380 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 143/1 | 2025-07-29 | 2025-09-22 | 2025-09-27 | 55 | 60 | 2025-07 | 379 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 99/3 | 2025-07-29 |  |  |  |  | 2025-07 | 379 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 133/1 | 2025-07-30 | 2025-10-15 | 2025-10-19 | 77 | 81 | 2025-07 | 378 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 149B/2 | 2025-07-30 | 2025-09-27 | 2025-09-30 | 59 | 62 | 2025-07 | 378 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 111/0 | 2025-07-31 | 2025-11-03 | 2025-11-10 | 95 | 102 | 2025-07 | 377 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 116/0 | 2025-07-31 | 2025-09-30 | 2025-10-07 | 61 | 68 | 2025-07 | 377 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 129/1 | 2025-07-31 | 2025-11-01 | 2025-11-05 | 93 | 97 | 2025-07 | 377 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 133/7 | 2025-07-31 | 2025-09-29 | 2025-10-05 | 60 | 66 | 2025-07 | 377 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 143/6 | 2025-07-31 | 2025-09-18 | 2025-09-20 | 49 | 51 | 2025-07 | 377 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 145/0 | 2025-07-31 | 2025-11-12 | 2025-11-17 | 104 | 109 | 2025-07 | 377 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 76/0 | 2025-07-31 | 2025-10-24 | 2025-10-31 | 85 | 92 | 2025-07 | 377 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 98B/0 | 2025-07-31 | 2025-11-22 | 2025-11-29 | 114 | 121 | 2025-07 | 377 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 126/1 | 2025-08-02 | 2025-12-12 | 2025-12-16 | 132 | 136 | 2025-08 | 375 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 143/7 | 2025-08-02 | 2025-09-21 | 2025-09-23 | 50 | 52 | 2025-08 | 375 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 130/0 | 2025-08-04 | 2025-11-28 | 2025-12-05 | 116 | 123 | 2025-08 | 373 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 143/5 | 2025-08-04 | 2025-09-11 | 2025-09-17 | 38 | 44 | 2025-08 | 373 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 97/1 | 2025-08-05 | 2025-09-11 | 2025-09-21 | 37 | 47 | 2025-08 | 372 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 143/2 | 2025-08-06 | 2025-09-18 | 2025-09-20 | 43 | 45 | 2025-08 | 371 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 102/2 | 2025-08-07 | 2026-01-17 | 2026-01-20 | 163 | 166 | 2025-08 | 370 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 133/2 | 2025-08-07 | 2025-08-28 | 2025-09-16 | 21 | 40 | 2025-08 | 370 | TRUE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 144/0 | 2025-08-07 | 2025-10-01 | 2025-10-08 | 55 | 62 | 2025-08 | 370 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 98/0 | 2025-08-07 | 2025-11-06 | 2025-11-10 | 91 | 95 | 2025-08 | 370 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 112/0 | 2025-08-08 | 2025-10-19 | 2025-10-27 | 72 | 80 | 2025-08 | 369 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 129/0 | 2025-08-08 | 2025-11-09 | 2025-11-14 | 93 | 98 | 2025-08 | 369 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 143/4 | 2025-08-09 | 2025-09-11 | 2025-09-17 | 33 | 39 | 2025-08 | 368 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 83/0 | 2025-08-09 | 2026-01-02 | 2026-01-07 | 146 | 151 | 2025-08 | 368 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 131/1 | 2025-08-12 | 2025-11-06 | 2025-11-09 | 86 | 89 | 2025-08 | 365 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 149B/0 | 2025-08-12 | 2025-11-23 | 2025-11-28 | 103 | 108 | 2025-08 | 365 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 102/1 | 2025-08-14 | 2026-05-10 | 2026-05-24 | 269 | 283 | 2025-08 | 363 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 140/3 | 2025-08-14 | 2025-10-10 | 2025-10-11 | 57 | 58 | 2025-08 | 363 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 99/0 | 2025-08-14 |  |  |  |  | 2025-08 | 363 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 115/1 | 2025-08-16 | 2025-10-27 | 2025-11-02 | 72 | 78 | 2025-08 | 361 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 134A/4 | 2025-08-16 | 2025-11-04 | 2025-11-06 | 80 | 82 | 2025-08 | 361 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 140/2 | 2025-08-17 | 2025-10-08 | 2025-10-10 | 52 | 54 | 2025-08 | 360 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 126/0 | 2025-08-19 | 2026-01-05 | 2026-01-11 | 139 | 145 | 2025-08 | 358 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 135/0 | 2025-08-19 | 2025-10-29 | 2025-11-02 | 71 | 75 | 2025-08 | 358 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 149A/0 | 2025-08-19 | 2025-10-10 | 2025-10-15 | 52 | 57 | 2025-08 | 358 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 128/0 | 2025-08-20 | 2025-11-21 | 2025-11-28 | 93 | 100 | 2025-08 | 357 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 131/2 | 2025-08-20 | 2025-11-11 | 2025-11-15 | 83 | 87 | 2025-08 | 357 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 141/0 | 2025-08-20 | 2025-10-11 | 2025-10-16 | 52 | 57 | 2025-08 | 357 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 87/0 | 2025-08-22 | 2026-07-20 | 2026-07-30 | 332 | 342 | 2025-08 | 355 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 99/4 | 2025-08-22 |  |  |  |  | 2025-08 | 355 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 129/2 | 2025-08-23 | 2026-01-07 | 2026-01-15 | 137 | 145 | 2025-08 | 354 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 135/1 | 2025-08-23 | 2025-10-19 | 2025-10-24 | 57 | 62 | 2025-08 | 354 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 138/1 | 2025-08-23 | 2025-10-08 | 2025-10-13 | 46 | 51 | 2025-08 | 354 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 137/0 | 2025-08-24 | 2025-11-06 | 2025-11-12 | 74 | 80 | 2025-08 | 353 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 63/1 | 2025-08-24 |  |  |  |  | 2025-08 | 353 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 132/1 | 2025-08-25 | 2025-11-05 | 2025-11-07 | 72 | 74 | 2025-08 | 352 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 138/2 | 2025-08-25 | 2025-10-13 | 2025-10-16 | 49 | 52 | 2025-08 | 352 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 134A/2 | 2025-08-26 | 2025-10-24 | 2025-10-26 | 59 | 61 | 2025-08 | 351 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 56/4 | 2025-08-26 |  |  |  |  | 2025-08 | 351 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 56/2 | 2025-08-27 |  |  |  |  | 2025-08 | 350 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 138/0 | 2025-08-28 | 2025-10-19 | 2025-10-24 | 52 | 57 | 2025-08 | 349 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 149/0 | 2025-08-28 | 2025-10-03 | 2025-10-10 | 36 | 43 | 2025-08 | 349 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 134/0 | 2025-08-29 | 2025-10-27 | 2025-10-29 | 59 | 61 | 2025-08 | 348 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 134A/1 | 2025-08-29 | 2025-10-29 | 2025-11-03 | 61 | 66 | 2025-08 | 348 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 116/1 | 2025-08-31 | 2025-09-27 | 2025-09-29 | 27 | 29 | 2025-08 | 346 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 132/3 | 2025-08-31 | 2025-11-01 | 2025-11-04 | 62 | 65 | 2025-08 | 346 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 134A/0 | 2025-08-31 | 2025-10-16 | 2025-10-23 | 46 | 53 | 2025-08 | 346 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 138/3 | 2025-08-31 | 2025-10-16 | 2025-10-19 | 46 | 49 | 2025-08 | 346 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 56/5 | 2025-08-31 |  |  |  |  | 2025-08 | 346 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 82/0 | 2025-08-31 | 2025-11-15 | 2025-11-20 | 76 | 81 | 2025-08 | 346 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 85/0 | 2025-08-31 | 2025-12-12 | 2025-12-16 | 103 | 107 | 2025-08 | 346 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 99A/0 | 2025-08-31 |  |  |  |  | 2025-08 | 346 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 131/0 | 2025-09-04 | 2026-01-31 | 2026-02-05 | 149 | 154 | 2025-09 | 342 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 139/0 | 2025-09-05 | 2025-10-26 | 2025-10-28 | 51 | 53 | 2025-09 | 341 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 147/6 | 2025-09-05 | 2025-10-23 | 2025-10-26 | 48 | 51 | 2025-09 | 341 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 125/3 | 2025-09-10 | 2025-12-31 | 2026-01-04 | 112 | 116 | 2025-09 | 336 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 57/0 | 2025-09-10 |  |  |  |  | 2025-09 | 336 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 59/0 | 2025-09-12 |  |  |  |  | 2025-09 | 334 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 81/0 | 2025-09-12 | 2025-12-06 | 2025-12-11 | 85 | 90 | 2025-09 | 334 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 147/9 | 2025-09-14 | 2025-10-16 | 2025-10-19 | 32 | 35 | 2025-09 | 332 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 64/0 | 2025-09-14 |  |  |  |  | 2025-09 | 332 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 58/0 | 2025-09-17 |  |  |  |  | 2025-09 | 329 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 125/2 | 2025-09-18 |  |  |  |  | 2025-09 | 328 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 72/1 | 2025-09-19 | 2026-08-09 | 2026-08-12 | 324 | 327 | 2025-09 | 327 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 56/1 | 2025-09-20 |  |  |  |  | 2025-09 | 326 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 136/0 | 2025-09-21 | 2025-11-03 | 2025-11-08 | 43 | 48 | 2025-09 | 325 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 132/4 | 2025-09-25 | 2025-11-08 | 2025-11-11 | 44 | 47 | 2025-09 | 321 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 48/0 | 2025-09-25 |  |  |  |  | 2025-09 | 321 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 123/0 | 2025-09-30 | 2025-12-28 | 2025-12-30 | 89 | 91 | 2025-09 | 316 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 133/0 | 2025-09-30 | 2025-10-24 | 2025-10-31 | 24 | 31 | 2025-09 | 316 | TRUE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 152/0 | 2025-09-30 | 2025-11-01 | 2025-11-14 | 32 | 45 | 2025-09 | 316 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 153A/0 | 2025-09-30 | 2025-10-27 | 2025-11-01 | 27 | 32 | 2025-09 | 316 | TRUE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 135/2 | 2025-10-11 | 2025-11-25 | 2025-11-27 | 45 | 47 | 2025-10 | 305 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 149B/3 | 2025-10-13 | 2025-11-14 | 2025-11-22 | 32 | 40 | 2025-10 | 303 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 135/3 | 2025-10-16 | 2025-11-28 | 2025-11-30 | 43 | 45 | 2025-10 | 300 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 73/1 | 2025-10-16 | 2026-05-03 | 2026-05-09 | 199 | 205 | 2025-10 | 300 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 84/0 | 2025-10-19 | 2025-12-17 | 2025-12-21 | 59 | 63 | 2025-10 | 297 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 150/0 | 2025-10-29 | 2025-11-28 | 2025-12-07 | 30 | 39 | 2025-10 | 287 | TRUE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 71/2 | 2025-10-30 | 2025-01-14 | 2026-01-18 | -289 | 80 | 2025-10 | 286 | FALSE | FALSE | Yes | Yes | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 134A/3 | 2025-10-31 | 2025-11-21 | 2025-11-25 | 21 | 25 | 2025-10 | 285 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 148/0 | 2025-11-04 | 2025-11-16 | 2025-11-21 | 12 | 17 | 2025-11 | 281 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 71/3 | 2025-11-07 | 2026-01-08 | 2026-01-13 | 62 | 67 | 2025-11 | 278 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 151/0 | 2025-11-08 | 2025-12-07 | 2025-12-14 | 29 | 36 | 2025-11 | 277 | TRUE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 78/1 | 2025-11-08 | 2025-11-21 | 2025-11-25 | 13 | 17 | 2025-11 | 277 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 81/1 | 2025-11-10 | 2025-12-01 | 2025-12-05 | 21 | 25 | 2025-11 | 275 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 140/1 | 2025-11-11 | 2025-12-01 | 2025-12-03 | 20 | 22 | 2025-11 | 274 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 89/0 | 2025-11-12 | 2026-07-16 | 2026-07-20 | 246 | 250 | 2025-11 | 273 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 71/0 | 2025-11-14 |  |  |  |  | 2025-11 | 271 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 113/0 | 2025-11-16 | 2026-01-12 | 2026-01-17 | 57 | 62 | 2025-11 | 269 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 139/1 | 2025-11-16 | 2025-12-06 | 2025-12-10 | 20 | 24 | 2025-11 | 269 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 72/0 | 2025-11-17 | 2026-05-09 | 2026-05-18 | 173 | 182 | 2025-11 | 268 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 89/1 | 2025-11-18 | 2025-12-31 | 2026-01-05 | 43 | 48 | 2025-11 | 267 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 140/0 | 2025-11-22 | 2025-12-09 | 2025-12-13 | 17 | 21 | 2025-11 | 263 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 154/0 | 2025-11-22 | 2025-12-14 | 2025-12-21 | 22 | 29 | 2025-11 | 263 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 90/0 | 2025-11-22 | 2026-02-20 | 2026-02-24 | 90 | 94 | 2025-11 | 263 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 90/1 | 2025-11-26 | 2025-12-12 | 2025-12-26 | 16 | 30 | 2025-11 | 259 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 127/1 | 2025-11-28 | 2026-01-13 | 2026-01-16 | 46 | 49 | 2025-11 | 257 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 153/0 | 2025-11-30 | 2025-12-21 | 2026-01-04 | 21 | 35 | 2025-11 | 255 | TRUE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 66/0 | 2025-11-30 | 2026-02-19 | 2026-03-03 | 81 | 93 | 2025-11 | 255 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 118/0 | 2025-12-05 | 2026-01-27 | 2026-01-30 | 53 | 56 | 2025-12 | 250 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 88/0 | 2025-12-05 | 2026-07-11 | 2026-07-19 | 218 | 226 | 2025-12 | 250 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 130/1 | 2025-12-06 | 2026-02-08 | 2026-02-11 | 64 | 67 | 2025-12 | 249 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 98B/2 | 2025-12-08 |  |  |  |  | 2025-12 | 247 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 117/0 | 2025-12-13 |  |  |  |  | 2025-12 | 242 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 128/1 | 2025-12-14 | 2026-02-05 | 2026-02-08 | 53 | 56 | 2025-12 | 241 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 117/1 | 2025-12-19 | 2026-05-11 | 2026-05-19 | 143 | 151 | 2025-12 | 236 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 132/2 | 2025-12-20 | 2026-02-11 | 2026-02-13 | 53 | 55 | 2025-12 | 235 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 91/0 | 2025-12-24 | 2026-05-19 | 2026-06-06 | 146 | 164 | 2025-12 | 231 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 132/0 | 2025-12-28 | 2026-02-12 | 2026-02-18 | 46 | 52 | 2025-12 | 227 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 104A/0 | 2025-12-30 | 2026-08-09 |  | 222 |  | 2025-12 | 225 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 124/0 | 2025-12-30 |  |  |  |  | 2025-12 | 225 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 91/3 | 2025-12-31 | 2026-05-08 | 2026-05-14 | 128 | 134 | 2025-12 | 224 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 104B/0 | 2026-01-04 | 2026-05-10 | 2026-05-30 | 126 | 146 | 2026-01 | 220 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 65/0 | 2026-01-07 | 2026-03-10 | 2026-03-16 | 62 | 68 | 2026-01 | 217 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 122/2 | 2026-01-08 |  |  |  |  | 2026-01 | 216 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 126/3 | 2026-01-15 | 2026-05-24 | 2026-05-31 | 129 | 136 | 2026-01 | 209 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 65/1 | 2026-01-15 | 2026-03-01 | 2026-03-09 | 45 | 53 | 2026-01 | 209 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 69/3 | 2026-01-15 |  |  |  |  | 2026-01 | 209 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 108/0 | 2026-01-20 |  |  |  |  | 2026-01 | 204 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 10/3 | 2026-01-23 |  |  |  |  | 2026-01 | 201 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 109/0 | 2026-01-23 |  |  |  |  | 2026-01 | 201 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 120/0 | 2026-01-25 | 2026-05-19 | 2026-06-15 | 114 | 141 | 2026-01 | 199 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 10/5 | 2026-01-26 | 2026-04-10 | 2026-04-17 | 74 | 81 | 2026-01 | 198 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 10/6 | 2026-01-28 | 2026-04-17 | 2026-04-20 | 79 | 82 | 2026-01 | 196 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 92/0 | 2026-01-28 | 2026-04-27 | 2026-05-07 | 89 | 99 | 2026-01 | 196 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 10/7 | 2026-01-30 | 2026-04-20 | 2026-04-23 | 80 | 83 | 2026-01 | 194 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 93/0 | 2026-01-30 | 2026-05-14 | 2026-05-19 | 104 | 109 | 2026-01 | 194 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 7/7 | 2026-02-04 | 2026-04-24 | 2026-04-29 | 79 | 84 | 2026-02 | 189 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 7/9 | 2026-02-06 | 2026-04-16 | 2026-04-20 | 69 | 73 | 2026-02 | 187 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 7/0 | 2026-02-11 |  |  |  |  | 2026-02 | 182 | FALSE | FALSE | No | No |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 10/12 | 2026-02-12 | 2026-06-02 | 2026-06-09 | 110 | 117 | 2026-02 | 181 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 1/1 | 2026-02-14 | 2026-03-27 | 2026-04-06 | 41 | 51 | 2026-02 | 179 | FALSE | FALSE | Yes | No | fallback_single_line | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 6/2 | 2026-02-16 | 2026-06-19 | 2026-06-25 | 123 | 129 | 2026-02 | 177 | FALSE | FALSE | Yes | No | fallback_single_line | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 1/2 | 2026-02-18 | 2026-04-07 | 2026-04-15 | 48 | 56 | 2026-02 | 175 | FALSE | FALSE | Yes | No | fallback_single_line | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 6/1 | 2026-02-20 | 2026-06-21 | 2026-06-30 | 121 | 130 | 2026-02 | 173 | FALSE | FALSE | Yes | No | fallback_single_line | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 1/0 | 2026-02-28 |  |  |  |  | 2026-02 | 165 | FALSE | FALSE | No | No |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 117/2 | 2026-02-28 |  |  |  |  | 2026-02 | 165 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 4/0 | 2026-02-28 | 2026-05-25 | 2026-06-09 | 86 | 101 | 2026-02 | 165 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 6/0 | 2026-02-28 |  |  |  |  | 2026-02 | 165 | FALSE | FALSE | No | No |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 157/0 | 2026-03-04 |  |  |  |  | 2026-03 | 161 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 156/0 | 2026-03-10 | 2026-08-08 | 2026-08-11 | 151 | 154 | 2026-03 | 155 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 2/1 | 2026-03-11 | 2026-04-15 | 2026-04-26 | 35 | 46 | 2026-03 | 154 | FALSE | FALSE | Yes | No | fallback_single_line | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 98B/1 | 2026-03-11 |  |  |  |  | 2026-03 | 154 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 2/0 | 2026-03-13 |  |  |  |  | 2026-03 | 152 | FALSE | FALSE | No | No |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 2/2 | 2026-03-15 | 2026-06-11 | 2026-06-21 | 88 | 98 | 2026-03 | 150 | FALSE | FALSE | Yes | No | fallback_single_line | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 2/3 | 2026-03-16 | 2026-07-05 | 2026-07-07 | 111 | 113 | 2026-03 | 149 | FALSE | FALSE | Yes | No | fallback_single_line | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 2/4 | 2026-03-17 | 2026-07-07 | 2026-07-15 | 112 | 120 | 2026-03 | 148 | FALSE | FALSE | Yes | No | fallback_single_line | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 103/0 | 2026-03-19 |  |  |  |  | 2026-03 | 146 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 10/8 | 2026-03-22 | 2026-04-20 | 2026-04-24 | 29 | 33 | 2026-03 | 143 | TRUE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 8/2 | 2026-03-25 | 2026-04-29 | 2026-05-02 | 35 | 38 | 2026-03 | 140 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 3/0B | 2026-03-26 | 2026-08-05 | 2026-08-06 | 132 | 133 | 2026-03 | 139 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 7/1 | 2026-03-26 | 2026-05-02 | 2026-05-03 | 37 | 38 | 2026-03 | 139 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 2/5 | 2026-03-27 | 2026-07-11 | 2026-07-17 | 106 | 112 | 2026-03 | 138 | FALSE | FALSE | Yes | No | fallback_single_line | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 3/0A | 2026-03-28 | 2026-08-05 | 2026-08-06 | 130 | 131 | 2026-03 | 137 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5/2 | 2026-03-31 |  |  |  |  | 2026-03 | 134 | FALSE | FALSE | No | No |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5/1 | 2026-04-02 |  |  |  |  | 2026-04 | 132 | FALSE | FALSE | No | No |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 3/1 | 2026-04-04 |  |  |  |  | 2026-04 | 130 | FALSE | FALSE | No | No |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 8/1 | 2026-04-06 | 2026-04-23 | 2026-05-02 | 17 | 26 | 2026-04 | 128 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 3/1 | 2026-04-07 | 2026-08-06 | 2026-08-09 | 121 | 124 | 2026-04 | 127 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 2/1B | 2026-04-08 | 2026-08-04 | 2026-08-06 | 118 | 120 | 2026-04 | 126 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 2/1 A | 2026-04-09 | 2026-08-02 | 2026-08-05 | 115 | 118 | 2026-04 | 125 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 103/1 | 2026-04-10 | 2026-06-27 | 2026-07-05 | 78 | 86 | 2026-04 | 124 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 8/0 | 2026-04-11 | 2026-07-06 | 2026-07-14 | 86 | 94 | 2026-04 | 123 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5/0 | 2026-04-12 |  |  |  |  | 2026-04 | 122 | FALSE | FALSE | No | No |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 9/3 | 2026-04-14 | 2026-05-02 | 2026-05-06 | 18 | 22 | 2026-04 | 120 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 9/4 | 2026-04-15 | 2026-05-04 | 2026-05-08 | 19 | 23 | 2026-04 | 119 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 99C/0 | 2026-04-15 | 2026-07-16 | 2026-07-22 | 92 | 98 | 2026-04 | 119 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 4/5 | 2026-04-16 | 2026-07-15 | 2026-07-17 | 90 | 92 | 2026-04 | 118 | FALSE | FALSE | Yes | No | fallback_single_line | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 3/3 | 2026-04-18 |  | 2026-08-04 |  | 108 | 2026-04 | 116 | FALSE | FALSE | No | No |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 3/2 | 2026-04-21 | 2026-08-30 | 2026-08-01 | 131 | 102 | 2026-04 | 113 | FALSE | FALSE | Yes | No | fallback_single_line | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 9/5 | 2026-04-21 | 2026-05-07 | 2026-05-12 | 16 | 21 | 2026-04 | 113 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 10/14 | 2026-04-23 | 2026-05-13 | 2026-05-16 | 20 | 23 | 2026-04 | 111 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 100/0 | 2026-04-24 | 2026-04-24 | 2026-06-05 | 0 | 42 | 2026-04 | 110 | TRUE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 10/11 | 2026-04-28 | 2026-05-27 | 2026-06-03 | 29 | 36 | 2026-04 | 106 | TRUE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 3/4 | 2026-04-29 | 2026-07-18 | 2026-07-25 | 80 | 87 | 2026-04 | 105 | FALSE | FALSE | Yes | No | fallback_single_line | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 10/0 | 2026-05-02 | 2026-05-12 | 2026-07-07 | 10 | 66 | 2026-05 | 102 | TRUE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 2/0 | 2026-05-02 |  |  |  |  | 2026-05 | 102 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 10/2 | 2026-05-03 | 2026-05-08 | 2026-05-15 | 5 | 12 | 2026-05 | 101 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 155/0 | 2026-05-03 |  |  |  |  | 2026-05 | 101 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 9/2 | 2026-05-03 | 2026-05-07 | 2026-05-11 | 4 | 8 | 2026-05 | 101 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 3/5 | 2026-05-05 | 2026-07-20 | 2026-07-22 | 76 | 78 | 2026-05 | 99 | FALSE | FALSE | Yes | No | fallback_single_line | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 154/1B | 2026-05-06 |  |  |  |  | 2026-05 | 98 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 10/13 | 2026-05-08 | 2026-06-07 | 2026-06-16 | 30 | 39 | 2026-05 | 96 | TRUE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 154/2B | 2026-05-08 |  |  |  |  | 2026-05 | 96 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 4/2 | 2026-05-08 | 2026-07-17 | 2026-07-28 | 70 | 81 | 2026-05 | 96 | FALSE | FALSE | Yes | No | fallback_single_line | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 154/1A | 2026-05-09 |  |  |  |  | 2026-05 | 95 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 154/2A | 2026-05-09 |  |  |  |  | 2026-05 | 95 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 4/4 | 2026-05-10 | 2026-07-17 | 2026-07-20 | 68 | 71 | 2026-05 | 94 | FALSE | FALSE | Yes | No | fallback_single_line | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 7/6 | 2026-05-11 | 2026-05-16 | 2026-05-24 | 5 | 13 | 2026-05 | 93 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 13/2 | 2026-05-14 |  |  |  |  | 2026-05 | 90 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 4/0 | 2026-05-15 |  |  |  |  | 2026-05 | 89 | FALSE | FALSE | No | No |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 7/8 | 2026-05-16 | 2026-05-16 | 2026-05-24 | 0 | 8 | 2026-05 | 88 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 8/3 | 2026-05-17 | 2026-05-24 | 2026-05-28 | 7 | 11 | 2026-05 | 87 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 4/1 | 2026-05-18 | 2026-07-23 | 2026-07-29 | 66 | 72 | 2026-05 | 86 | FALSE | FALSE | Yes | No | fallback_single_line | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 4/3 | 2026-05-19 | 2026-07-26 | 2026-07-30 | 68 | 72 | 2026-05 | 85 | FALSE | FALSE | Yes | No | fallback_single_line | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 8/4 | 2026-05-19 | 2026-05-28 | 2026-05-31 | 9 | 12 | 2026-05 | 85 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 1/0 | 2026-05-27 |  |  |  |  | 2026-05 | 77 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 27/0 | 2026-05-27 |  |  |  |  | 2026-05 | 77 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 1A/0 | 2026-05-30 |  |  |  |  | 2026-05 | 74 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 10/10 | 2026-05-31 | 2026-06-16 | 2026-06-22 | 16 | 22 | 2026-05 | 73 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 3A/1 | 2026-05-31 |  |  |  |  | 2026-05 | 73 | FALSE | FALSE | No | No |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 7/2 | 2026-06-01 | 2026-06-27 | 2026-07-31 | 26 | 60 | 2026-06 | 72 | TRUE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5/3 | 2026-06-03 |  |  |  |  | 2026-06 | 70 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 3A/0 | 2026-06-05 |  |  |  |  | 2026-06 | 68 | FALSE | FALSE | No | No |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5/4 | 2026-06-05 | 2026-08-03 | 2026-08-05 | 59 | 61 | 2026-06 | 68 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 9/0 | 2026-06-05 | 2026-06-10 | 2026-06-16 | 5 | 11 | 2026-06 | 68 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 10/1 | 2026-06-09 | 2026-07-06 | 2026-07-09 | 27 | 30 | 2026-06 | 64 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5/5 | 2026-06-09 | 2026-07-15 | 2026-07-26 | 36 | 47 | 2026-06 | 64 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 10/4 | 2026-06-15 | 2026-06-21 | 2026-06-28 | 6 | 13 | 2026-06 | 58 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 3B/0 | 2026-06-15 |  |  |  |  | 2026-06 | 58 | FALSE | FALSE | No | No |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5/0 | 2026-06-15 |  |  |  |  | 2026-06 | 58 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 56/3 | 2026-06-17 |  |  |  |  | 2026-06 | 56 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 7/3 | 2026-06-19 | 2026-07-13 | 2026-07-16 | 24 | 27 | 2026-06 | 54 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 3/0 | 2026-06-24 | 2026-08-01 | 2026-08-08 | 38 | 45 | 2026-06 | 49 | FALSE | FALSE | Yes | No | fallback_single_line | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5/2 | 2026-06-24 | 2026-08-07 | 2026-08-09 | 44 | 46 | 2026-06 | 49 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 10/9 | 2026-06-27 | 2025-07-10 | 2026-07-13 | -352 | 16 | 2026-06 | 46 | FALSE | FALSE | Yes | Yes | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 107/1 | 2026-06-28 |  |  |  |  | 2026-06 | 45 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 43/0 | 2026-06-28 |  |  |  |  | 2026-06 | 45 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5A/0 | 2026-06-29 |  |  |  |  | 2026-06 | 44 | FALSE | FALSE | No | No |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 121/0 | 2026-06-30 |  |  |  |  | 2026-06 | 43 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 42/0 | 2026-06-30 |  |  |  |  | 2026-06 | 43 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 41/3 | 2026-07-04 |  |  |  |  | 2026-07 | 39 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 6D/5 | 2026-07-06 | 2026-07-15 | 2026-07-20 | 9 | 14 | 2026-07 | 37 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 9A/0 | 2026-07-10 | 2026-07-16 | 2026-07-24 | 6 | 14 | 2026-07 | 33 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 42/1 | 2026-07-11 |  |  |  |  | 2026-07 | 32 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5/6 | 2026-07-11 | 2026-08-11 |  | 31 |  | 2026-07 | 32 | FALSE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5/1 | 2026-07-13 | 2026-08-07 | 2026-08-11 | 25 | 29 | 2026-07 | 30 | TRUE | TRUE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 7/0 | 2026-07-16 |  |  |  |  | 2026-07 | 27 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 41/1 | 2026-07-17 |  |  |  |  | 2026-07 | 26 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 44/0 | 2026-07-18 | 2026-08-05 |  | 18 |  | 2026-07 | 25 | TRUE | FALSE | Yes | No | exact | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 122/1 | 2026-07-20 |  |  |  |  | 2026-07 | 23 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 122/0 | 2026-07-24 |  |  |  |  | 2026-07 | 19 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 102/0 | 2026-07-28 |  |  |  |  | 2026-07 | 15 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 39/4 | 2026-07-28 |  |  |  |  | 2026-07 | 15 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 2A/0 | 2026-07-30 |  |  |  |  | 2026-07 | 13 | FALSE | FALSE | No | No |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 45/3 | 2026-07-31 |  |  |  |  | 2026-07 | 12 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5A/0 | 2026-07-31 |  |  |  |  | 2026-07 | 12 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5B/0 | 2026-08-03 |  |  |  |  | 2026-08 | 9 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 39/3 | 2026-08-04 |  |  |  |  | 2026-08 | 8 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 40/0 | 2026-08-06 |  |  |  |  | 2026-08 | 6 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 40/1 | 2026-08-12 |  |  |  |  | 2026-08 | 0 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5C/0 | 2026-08-12 |  |  |  |  | 2026-08 | 0 | FALSE | FALSE | No | No |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 605 | 29/5 | 2025-08-11 | 2025-11-27 | 2025-12-03 | 108 | 114 | 2025-08 | 366 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 29/4 | 2025-09-06 | 2025-12-05 | 2025-12-10 | 90 | 95 | 2025-09 | 340 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 27/0 | 2025-09-20 | 2025-12-11 | 2025-11-21 | 82 | 62 | 2025-09 | 326 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 29/3 | 2025-09-24 | 2026-05-05 | 2026-05-09 | 223 | 227 | 2025-09 | 322 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 29/1 | 2025-10-10 | 2026-03-09 | 2026-03-23 | 150 | 164 | 2025-10 | 306 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 18/0 | 2025-10-16 |  |  |  |  | 2025-10 | 300 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | 29/6 | 2025-10-16 | 2025-12-22 | 2025-12-29 | 67 | 74 | 2025-10 | 300 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 117/1 | 2025-10-20 | 2026-02-07 | 2026-02-11 | 110 | 114 | 2025-10 | 296 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 71/3 | 2025-10-23 | 2026-05-05 | 2026-05-08 | 194 | 197 | 2025-10 | 293 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 92/3 | 2025-10-27 | 2026-02-12 | 2026-02-16 | 108 | 112 | 2025-10 | 289 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 22/1 | 2025-10-28 | 2026-05-30 | 2026-05-31 | 214 | 215 | 2025-10 | 288 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 72/2 | 2025-10-28 | 2026-04-25 | 2026-04-30 | 179 | 184 | 2025-10 | 288 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 92/2 | 2025-10-28 | 2026-02-02 | 2026-02-10 | 97 | 105 | 2025-10 | 288 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 117/3 | 2025-10-29 | 2026-02-03 | 2026-02-07 | 97 | 101 | 2025-10 | 287 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 31/1 | 2025-10-30 | 2026-01-25 | 2026-02-01 | 87 | 94 | 2025-10 | 286 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 21/1 | 2025-10-31 | 2026-06-22 | 2026-06-27 | 234 | 239 | 2025-10 | 285 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 22/0 | 2025-10-31 |  |  |  |  | 2025-10 | 285 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | 89/1 | 2025-10-31 | 2026-02-02 | 2026-02-06 | 94 | 98 | 2025-10 | 285 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 93/1 | 2025-10-31 | 2026-05-08 | 2026-05-10 | 189 | 191 | 2025-10 | 285 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 117/2 | 2025-11-04 | 2026-02-11 | 2026-02-16 | 99 | 104 | 2025-11 | 281 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 93/2 | 2025-11-04 | 2026-02-17 | 2026-02-20 | 105 | 108 | 2025-11 | 281 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 118/1 | 2025-11-06 | 2026-02-21 | 2026-02-23 | 107 | 109 | 2025-11 | 279 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 74/0 | 2025-11-06 |  |  |  |  | 2025-11 | 279 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 95/2 | 2025-11-08 | 2026-02-08 | 2026-02-11 | 92 | 95 | 2025-11 | 277 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 72/0 | 2025-11-09 |  |  |  |  | 2025-11 | 276 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 23/1 | 2025-11-10 | 2026-02-05 | 2026-02-10 | 87 | 92 | 2025-11 | 275 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 92/1 | 2025-11-10 | 2026-02-25 | 2026-02-28 | 107 | 110 | 2025-11 | 275 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 95/3 | 2025-11-10 | 2026-02-06 | 2026-02-08 | 88 | 90 | 2025-11 | 275 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 31/3 | 2025-11-11 | 2026-02-06 | 2026-02-08 | 87 | 89 | 2025-11 | 274 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 97/2 | 2025-11-12 | 2026-02-05 | 2026-02-09 | 85 | 89 | 2025-11 | 273 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 22/2 | 2025-11-13 | 2026-06-01 | 2026-06-03 | 200 | 202 | 2025-11 | 272 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 97/1 | 2025-11-13 | 2026-02-09 | 2026-02-12 | 88 | 91 | 2025-11 | 272 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 76/2 | 2025-11-14 | 2026-02-22 | 2026-02-27 | 100 | 105 | 2025-11 | 271 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 131/1 | 2025-11-15 | 2026-02-27 | 2026-03-02 | 104 | 107 | 2025-11 | 270 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 95/1 | 2025-11-15 | 2026-03-12 | 2026-03-15 | 117 | 120 | 2025-11 | 270 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP118 | 2025-11-16 | 2026-04-27 | 2026-05-05 | 162 | 170 | 2025-11 | 269 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 15/1 | 2025-11-17 | 2025-12-25 | 2026-01-05 | 38 | 49 | 2025-11 | 268 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 76/1 | 2025-11-18 | 2026-02-17 | 2026-02-22 | 91 | 96 | 2025-11 | 267 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 131/3 | 2025-11-19 | 2026-02-23 | 2026-02-27 | 96 | 100 | 2025-11 | 266 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 15/2 | 2025-11-19 | 2026-01-07 | 2026-01-16 | 49 | 58 | 2025-11 | 266 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP93 | 2025-11-19 | 2026-02-20 | 2026-02-25 | 93 | 98 | 2025-11 | 266 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 95/4 | 2025-11-20 | 2026-02-11 | 2026-02-13 | 83 | 85 | 2025-11 | 265 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 97/3 | 2025-11-20 | 2026-02-12 | 2026-02-17 | 84 | 89 | 2025-11 | 265 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP90 | 2025-11-22 | 2026-05-16 | 2026-05-21 | 175 | 180 | 2025-11 | 263 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 17/0 | 2025-11-23 |  |  |  |  | 2025-11 | 262 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | 27/1 | 2025-11-23 | 2026-05-16 | 2026-05-19 | 174 | 177 | 2025-11 | 262 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 131/2 | 2025-11-24 | 2026-04-30 | 2026-05-05 | 157 | 162 | 2025-11 | 261 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 30/3 | 2025-11-24 | 2025-12-29 | 2026-01-08 | 35 | 45 | 2025-11 | 261 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP98 | 2025-11-24 | 2026-02-22 | 2026-02-26 | 90 | 94 | 2025-11 | 261 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 98/1 | 2025-11-26 | 2026-02-17 | 2026-02-20 | 83 | 86 | 2025-11 | 259 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP32 | 2025-11-26 | 2026-02-13 | 2026-02-20 | 79 | 86 | 2025-11 | 259 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP94 | 2025-11-27 | 2026-02-17 | 2026-02-21 | 82 | 86 | 2025-11 | 258 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 103/1 | 2025-11-28 | 2026-03-02 | 2026-03-07 | 94 | 99 | 2025-11 | 257 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 30/5 | 2025-11-29 | 2026-01-09 | 2026-01-18 | 41 | 50 | 2025-11 | 256 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP96 | 2025-11-29 | 2026-02-13 | 2026-02-17 | 76 | 80 | 2025-11 | 256 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 131/4 | 2025-11-30 | 2026-02-12 | 2026-02-17 | 74 | 79 | 2025-11 | 255 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 20/0 | 2025-11-30 |  |  |  |  | 2025-11 | 255 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | 40/1 | 2025-11-30 | 2026-02-16 | 2026-02-23 | 78 | 85 | 2025-11 | 255 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP116 | 2025-11-30 |  |  |  |  | 2025-11 | 255 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP87 | 2025-11-30 | 2026-07-05 | 2026-07-31 | 217 | 243 | 2025-11 | 255 | FALSE | FALSE | Yes | No | fallback_single_line | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP99 | 2025-11-30 | 2026-02-26 | 2026-03-02 | 88 | 92 | 2025-11 | 255 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP75 | 2025-12-01 | 2026-04-21 | 2026-04-28 | 141 | 148 | 2025-12 | 254 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 40/0 | 2025-12-03 |  |  |  |  | 2025-12 | 252 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | 104/1 | 2025-12-04 | 2026-03-23 | 2026-03-25 | 109 | 111 | 2025-12 | 251 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP28 | 2025-12-04 | 2026-05-19 | 2026-05-26 | 166 | 173 | 2025-12 | 251 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 82/2 | 2025-12-05 | 2026-05-03 | 2026-05-08 | 149 | 154 | 2025-12 | 250 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 18/1 | 2025-12-06 | 2026-03-05 | 2026-03-12 | 89 | 96 | 2025-12 | 249 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 76/3 | 2025-12-06 | 2026-03-05 | 2026-03-10 | 89 | 94 | 2025-12 | 249 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 99/1 | 2025-12-06 | 2026-04-19 | 2026-04-27 | 134 | 142 | 2025-12 | 249 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP100 | 2025-12-07 | 2026-03-14 | 2026-03-19 | 97 | 102 | 2025-12 | 248 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP95 | 2025-12-07 | 2026-02-21 | 2026-02-25 | 76 | 80 | 2025-12 | 248 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 23/0 | 2025-12-09 |  |  |  |  | 2025-12 | 246 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | AP117 | 2025-12-09 | 2026-02-24 | 2026-02-28 | 77 | 81 | 2025-12 | 246 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 29/0 | 2025-12-10 |  |  |  |  | 2025-12 | 245 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | 77/2 | 2025-12-10 | 2026-03-22 | 2026-03-28 | 102 | 108 | 2025-12 | 245 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 82/1 | 2025-12-10 | 2026-04-17 | 2026-04-21 | 128 | 132 | 2025-12 | 245 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 30/2 | 2025-12-12 | 2026-05-15 | 2026-05-17 | 154 | 156 | 2025-12 | 243 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 19/2 | 2025-12-13 | 2026-02-01 | 2026-02-07 | 50 | 56 | 2025-12 | 242 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 39/2 | 2025-12-13 | 2026-02-24 | 2026-02-28 | 73 | 77 | 2025-12 | 242 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP104 | 2025-12-13 | 2026-03-20 | 2026-03-23 | 97 | 100 | 2025-12 | 242 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP77 | 2025-12-13 | 2026-03-11 | 2026-03-17 | 88 | 94 | 2025-12 | 242 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP106 | 2025-12-15 | 2026-03-01 | 2026-03-13 | 76 | 88 | 2025-12 | 240 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 77/1 | 2025-12-16 | 2026-03-17 | 2026-03-22 | 91 | 96 | 2025-12 | 239 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 85/1 | 2025-12-16 |  |  |  |  | 2025-12 | 239 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP135 | 2025-12-16 | 2026-04-18 | 2026-04-25 | 123 | 130 | 2025-12 | 239 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 106/1 | 2025-12-17 |  |  |  |  | 2025-12 | 238 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 130/2 | 2025-12-17 | 2026-03-08 | 2026-03-13 | 81 | 86 | 2025-12 | 238 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 102/1 | 2025-12-18 |  |  |  |  | 2025-12 | 237 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP103 | 2025-12-18 | 2026-03-26 | 2026-03-31 | 98 | 103 | 2025-12 | 237 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 136/1 | 2025-12-19 | 2026-03-21 | 2026-03-31 | 92 | 102 | 2025-12 | 236 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 30/4 | 2025-12-19 | 2026-01-18 | 2026-01-22 | 30 | 34 | 2025-12 | 236 | TRUE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 116/1 | 2025-12-20 | 2026-03-07 | 2026-03-09 | 77 | 79 | 2025-12 | 235 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 130/1 | 2025-12-20 | 2026-05-15 | 2026-05-20 | 146 | 151 | 2025-12 | 235 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 135/2 | 2025-12-21 | 2026-06-12 | 2026-06-15 | 173 | 176 | 2025-12 | 234 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 23/5 | 2025-12-21 | 2026-02-15 | 2026-02-19 | 56 | 60 | 2025-12 | 234 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP45 | 2025-12-23 | 2026-05-15 | 2026-05-20 | 143 | 148 | 2025-12 | 232 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 131/6 | 2025-12-24 | 2026-03-13 | 2026-03-19 | 79 | 85 | 2025-12 | 231 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 139/1 | 2025-12-24 | 2026-06-21 | 2026-06-25 | 179 | 183 | 2025-12 | 231 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP19 | 2025-12-24 | 2026-02-13 | 2026-02-24 | 51 | 62 | 2025-12 | 231 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP85 | 2025-12-24 | 2026-04-04 | 2026-04-12 | 101 | 109 | 2025-12 | 231 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 46/1 | 2025-12-25 | 2026-03-23 | 2026-03-30 | 88 | 95 | 2025-12 | 230 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP43 | 2025-12-25 | 2026-04-21 | 2026-04-30 | 117 | 126 | 2025-12 | 230 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP80 | 2025-12-25 | 2026-03-28 | 2026-04-05 | 93 | 101 | 2025-12 | 230 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 138/1 | 2025-12-26 | 2026-06-25 | 2026-06-29 | 181 | 185 | 2025-12 | 229 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 156/4 | 2025-12-26 | 2026-03-07 | 2026-03-13 | 71 | 77 | 2025-12 | 229 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 131/5 | 2025-12-27 | 2026-02-17 | 2026-02-22 | 52 | 57 | 2025-12 | 228 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 150/1 | 2025-12-27 | 2026-04-22 | 2026-04-26 | 116 | 120 | 2025-12 | 228 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 31/2 | 2025-12-27 | 2026-02-01 | 2026-02-06 | 36 | 41 | 2025-12 | 228 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 137/1 | 2025-12-28 | 2026-05-05 | 2026-05-14 | 128 | 137 | 2025-12 | 227 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 135/1 | 2025-12-29 | 2026-04-04 | 2026-04-13 | 96 | 105 | 2025-12 | 226 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP102 | 2025-12-29 | 2026-03-11 | 2026-03-14 | 72 | 75 | 2025-12 | 226 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 156/3 | 2025-12-30 | 2026-04-10 | 2026-04-14 | 101 | 105 | 2025-12 | 225 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 80/1 | 2025-12-30 | 2026-06-15 | 2026-06-22 | 167 | 174 | 2025-12 | 225 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 86/1 | 2025-12-30 | 2026-05-14 | 2026-05-16 | 135 | 137 | 2025-12 | 225 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 132/1 | 2025-12-31 | 2026-03-02 | 2026-03-08 | 61 | 67 | 2025-12 | 224 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 138/2 | 2025-12-31 |  |  |  |  | 2025-12 | 224 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 23/4 | 2025-12-31 | 2026-02-20 | 2026-02-22 | 51 | 53 | 2025-12 | 224 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP33 | 2025-12-31 | 2026-03-12 | 2026-03-24 | 71 | 83 | 2025-12 | 224 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 150/2 | 2026-01-04 | 2026-04-12 | 2026-04-16 | 98 | 102 | 2026-01 | 220 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 43/1 | 2026-01-04 | 2026-04-06 | 2026-04-10 | 92 | 96 | 2026-01 | 220 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP146 | 2026-01-05 | 2026-04-04 | 2026-04-10 | 89 | 95 | 2026-01 | 219 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 69/3 | 2026-01-07 | 2026-03-17 | 2026-03-21 | 69 | 73 | 2026-01 | 217 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 156/2 | 2026-01-08 | 2026-04-04 | 2026-04-09 | 86 | 91 | 2026-01 | 216 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 18/2 | 2026-01-08 | 2026-02-24 | 2026-03-04 | 47 | 55 | 2026-01 | 216 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP26 | 2026-01-08 | 2026-02-22 | 2026-03-03 | 45 | 54 | 2026-01 | 216 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 155/1 | 2026-01-09 | 2026-04-14 | 2026-04-17 | 95 | 98 | 2026-01 | 215 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 31/4 | 2026-01-09 | 2026-02-09 | 2026-02-13 | 31 | 35 | 2026-01 | 215 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 46/3 | 2026-01-09 | 2026-04-18 | 2026-04-21 | 99 | 102 | 2026-01 | 215 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 137/2 | 2026-01-10 |  |  |  |  | 2026-01 | 214 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 152/1 | 2026-01-11 | 2026-04-16 | 2026-04-19 | 95 | 98 | 2026-01 | 213 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 90/1 | 2026-01-11 | 2026-05-10 | 2026-05-13 | 119 | 122 | 2026-01 | 213 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP131 | 2026-01-11 | 2026-06-02 | 2026-06-08 | 142 | 148 | 2026-01 | 213 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 43/2 | 2026-01-12 | 2026-04-02 | 2026-04-06 | 80 | 84 | 2026-01 | 212 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 87/2 | 2026-01-12 | 2026-02-25 | 2026-02-28 | 44 | 47 | 2026-01 | 212 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 152/2 | 2026-01-16 |  |  |  |  | 2026-01 | 208 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 90/2 | 2026-01-16 | 2026-03-09 | 2026-03-12 | 52 | 55 | 2026-01 | 208 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP147 | 2026-01-16 | 2026-04-26 | 2026-04-30 | 100 | 104 | 2026-01 | 208 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP157 | 2026-01-17 | 2026-03-13 | 2026-03-21 | 55 | 63 | 2026-01 | 207 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP154 | 2026-01-18 | 2026-06-16 | 2026-06-19 | 149 | 152 | 2026-01 | 206 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP31 | 2026-01-18 | 2026-03-29 | 2026-04-04 | 70 | 76 | 2026-01 | 206 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 145/2 | 2026-01-20 | 2026-04-19 | 2026-04-22 | 89 | 92 | 2026-01 | 204 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 19/1 | 2026-01-20 | 2026-02-08 | 2026-02-13 | 19 | 24 | 2026-01 | 204 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP129 | 2026-01-20 | 2026-05-05 | 2026-05-15 | 105 | 115 | 2026-01 | 204 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP138 | 2026-01-20 |  |  |  |  | 2026-01 | 204 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 25/2 | 2026-01-21 | 2026-03-05 | 2026-03-12 | 43 | 50 | 2026-01 | 203 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 44/3 | 2026-01-21 | 2026-03-08 | 2026-03-12 | 46 | 50 | 2026-01 | 203 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 45/2 | 2026-01-21 | 2026-02-17 | 2026-02-25 | 27 | 35 | 2026-01 | 203 | TRUE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 71/2 | 2026-01-21 | 2026-02-27 | 2026-03-05 | 37 | 43 | 2026-01 | 203 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 156/1 | 2026-01-22 | 2026-04-27 | 2026-05-04 | 95 | 102 | 2026-01 | 202 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 31/5 | 2026-01-22 | 2026-03-07 | 2026-03-10 | 44 | 47 | 2026-01 | 202 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 69/2 | 2026-01-22 | 2026-03-21 | 2026-03-24 | 58 | 61 | 2026-01 | 202 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP115 | 2026-01-22 | 2026-02-16 | 2026-02-20 | 25 | 29 | 2026-01 | 202 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP16 | 2026-01-25 | 2026-04-15 | 2026-04-20 | 80 | 85 | 2026-01 | 199 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 69/1 | 2026-01-27 | 2026-03-29 | 2026-03-31 | 61 | 63 | 2026-01 | 197 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 155/2 | 2026-01-30 | 2026-04-18 | 2026-04-22 | 78 | 82 | 2026-01 | 194 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 32/1 | 2026-01-30 | 2026-02-20 | 2026-02-25 | 21 | 26 | 2026-01 | 194 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 115/1 | 2026-01-31 | 2026-03-26 | 2026-03-31 | 54 | 59 | 2026-01 | 193 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 151/1 | 2026-01-31 | 2026-04-10 | 2026-04-12 | 69 | 71 | 2026-01 | 193 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 155/3 | 2026-01-31 | 2026-04-22 | 2026-04-27 | 81 | 86 | 2026-01 | 193 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP30 | 2026-01-31 | 2026-04-04 | 2026-04-12 | 63 | 71 | 2026-01 | 193 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 153/0 | 2026-02-05 |  |  |  |  | 2026-02 | 188 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 45/1 | 2026-02-05 | 2026-03-16 | 2026-03-21 | 39 | 44 | 2026-02 | 188 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP139 | 2026-02-06 |  |  |  |  | 2026-02 | 187 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 151/2 | 2026-02-07 | 2026-05-07 | 2026-05-10 | 89 | 92 | 2026-02 | 186 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 44/2 | 2026-02-07 | 2026-03-12 | 2026-03-16 | 33 | 37 | 2026-02 | 186 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP15 | 2026-02-08 | 2026-06-26 | 2026-07-12 | 138 | 154 | 2026-02 | 185 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP97 | 2026-02-08 | 2026-03-01 | 2026-03-09 | 21 | 29 | 2026-02 | 185 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP155 | 2026-02-09 | 2026-05-24 | 2026-06-04 | 104 | 115 | 2026-02 | 184 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 136/2 | 2026-02-11 | 2026-04-13 | 2026-04-17 | 61 | 65 | 2026-02 | 182 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 152/4 | 2026-02-12 | 2026-05-14 | 2026-05-16 | 91 | 93 | 2026-02 | 181 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP130 | 2026-02-12 |  |  |  |  | 2026-02 | 181 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 153/1 | 2026-02-13 | 2026-05-10 | 2026-05-13 | 86 | 89 | 2026-02 | 180 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 25/1 | 2026-02-13 | 2026-03-12 | 2026-03-17 | 27 | 32 | 2026-02 | 180 | TRUE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP92 | 2026-02-13 |  |  |  |  | 2026-02 | 180 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 50A/7 | 2026-02-14 | 2026-04-20 | 2026-04-26 | 65 | 71 | 2026-02 | 179 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP156 | 2026-02-14 | 2026-03-21 | 2026-03-29 | 35 | 43 | 2026-02 | 179 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 136/3 | 2026-02-15 | 2026-04-25 | 2026-04-30 | 69 | 74 | 2026-02 | 178 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 157/1 | 2026-02-15 | 2026-03-29 | 2026-04-03 | 42 | 47 | 2026-02 | 178 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 72/1 | 2026-02-17 | 2026-04-21 | 2026-04-25 | 63 | 67 | 2026-02 | 176 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 153/2 | 2026-02-18 | 2026-05-19 | 2026-05-23 | 90 | 94 | 2026-02 | 175 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP150 | 2026-02-18 | 2026-06-09 | 2026-06-13 | 111 | 115 | 2026-02 | 175 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP70 | 2026-02-18 | 2026-03-31 | 2026-04-07 | 41 | 48 | 2026-02 | 175 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP111 | 2026-02-19 | 2026-03-13 | 2026-03-22 | 22 | 31 | 2026-02 | 174 | TRUE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 136/4 | 2026-02-20 | 2026-05-28 | 2026-06-02 | 97 | 102 | 2026-02 | 173 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP12 | 2026-02-20 | 2026-07-14 | 2026-07-26 | 144 | 156 | 2026-02 | 173 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP44 | 2026-02-20 | 2026-03-24 | 2026-03-30 | 32 | 38 | 2026-02 | 173 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP46 | 2026-02-20 | 2026-05-10 | 2026-05-15 | 79 | 84 | 2026-02 | 173 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 70/2 | 2026-02-21 | 2026-04-13 | 2026-04-17 | 51 | 55 | 2026-02 | 172 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP68 | 2026-02-21 | 2026-03-24 | 2026-03-29 | 31 | 36 | 2026-02 | 172 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP132 | 2026-02-24 | 2026-06-03 | 2026-06-13 | 99 | 109 | 2026-02 | 169 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 50A/8 | 2026-02-25 | 2026-04-26 | 2026-04-29 | 60 | 63 | 2026-02 | 168 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP25 | 2026-02-25 | 2026-03-16 | 2026-03-25 | 19 | 28 | 2026-02 | 168 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP79 | 2026-02-25 | 2026-04-06 | 2026-04-17 | 40 | 51 | 2026-02 | 168 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 67/3 | 2026-02-26 | 2026-05-08 | 2026-05-13 | 71 | 76 | 2026-02 | 167 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 70/1 | 2026-02-26 | 2026-06-26 | 2026-07-02 | 120 | 126 | 2026-02 | 167 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 44/1 | 2026-02-27 | 2026-03-16 | 2026-03-24 | 17 | 25 | 2026-02 | 166 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP137 | 2026-02-27 | 2026-06-05 | 2026-06-12 | 98 | 105 | 2026-02 | 166 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP21 | 2026-02-27 | 2026-05-28 | 2026-06-10 | 90 | 103 | 2026-02 | 166 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP91 | 2026-02-27 |  |  |  |  | 2026-02 | 166 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 145/1 | 2026-02-28 | 2026-03-31 | 2026-04-04 | 31 | 35 | 2026-02 | 165 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP114 | 2026-02-28 | 2026-04-12 | 2026-04-19 | 43 | 50 | 2026-02 | 165 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP159 | 2026-02-28 |  |  |  |  | 2026-02 | 165 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP69 | 2026-03-02 | 2026-04-17 | 2026-04-21 | 46 | 50 | 2026-03 | 163 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 46/5 | 2026-03-05 | 2026-04-05 | 2026-04-10 | 31 | 36 | 2026-03 | 160 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 50A/3 | 2026-03-06 | 2026-04-28 | 2026-04-30 | 53 | 55 | 2026-03 | 159 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 29/2 | 2026-03-07 | 2026-04-19 | 2026-04-23 | 43 | 47 | 2026-03 | 158 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 43/3 | 2026-03-08 | 2026-03-30 | 2026-04-02 | 22 | 25 | 2026-03 | 157 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP14 | 2026-03-08 | 2026-07-18 | 2026-07-27 | 132 | 141 | 2026-03 | 157 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 33/2 | 2026-03-09 | 2026-03-24 | 2026-03-29 | 15 | 20 | 2026-03 | 156 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP149 | 2026-03-10 |  |  |  |  | 2026-03 | 155 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 46/4 | 2026-03-11 | 2026-03-30 | 2026-04-05 | 19 | 25 | 2026-03 | 154 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 67/2 | 2026-03-13 |  |  |  |  | 2026-03 | 152 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP127 | 2026-03-15 |  |  |  |  | 2026-03 | 150 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP24 | 2026-03-15 | 2026-03-25 | 2026-04-06 | 10 | 22 | 2026-03 | 150 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP148 | 2026-03-16 |  |  |  |  | 2026-03 | 149 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP136 | 2026-03-18 | 2026-05-20 | 2026-05-28 | 63 | 71 | 2026-03 | 147 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 67/1 | 2026-03-19 | 2026-04-11 | 2026-04-13 | 23 | 25 | 2026-03 | 146 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 43/4 | 2026-03-21 | 2026-04-10 | 2026-04-14 | 20 | 24 | 2026-03 | 144 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP71 | 2026-03-23 | 2026-06-21 | 2026-06-29 | 90 | 98 | 2026-03 | 142 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP145 | 2026-03-25 | 2026-05-05 | 2026-05-07 | 41 | 43 | 2026-03 | 140 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP152 | 2026-03-26 |  |  |  |  | 2026-03 | 139 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 46/2 | 2026-03-28 | 2026-04-14 | 2026-04-18 | 17 | 21 | 2026-03 | 137 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP108 | 2026-03-28 |  |  |  |  | 2026-03 | 137 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 15/3 | 2026-03-30 | 2026-04-12 | 2026-04-19 | 13 | 20 | 2026-03 | 135 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 38/1 | 2026-03-30 | 2026-04-30 | 2026-05-05 | 31 | 36 | 2026-03 | 135 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP124 | 2026-03-30 | 2026-06-08 | 2026-06-17 | 70 | 79 | 2026-03 | 135 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP67 | 2026-03-30 | 2026-05-22 | 2026-05-28 | 53 | 59 | 2026-03 | 135 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 152/3 | 2026-03-31 | 2026-05-16 | 2026-05-19 | 46 | 49 | 2026-03 | 134 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 42/3 | 2026-03-31 | 2026-04-30 | 2026-05-03 | 30 | 33 | 2026-03 | 134 | TRUE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 56/3 | 2026-03-31 |  |  |  |  | 2026-03 | 134 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 144/4 | 2026-04-05 | 2026-04-30 | 2026-05-04 | 25 | 29 | 2026-04 | 129 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 47/1 | 2026-04-05 | 2026-04-24 | 2026-04-28 | 19 | 23 | 2026-04 | 129 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP125 | 2026-04-06 |  |  |  |  | 2026-04 | 128 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 144/3 | 2026-04-07 | 2026-05-28 | 2026-05-31 | 51 | 54 | 2026-04 | 127 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 65/2 | 2026-04-07 |  |  |  |  | 2026-04 | 127 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP109 | 2026-04-12 |  |  |  |  | 2026-04 | 122 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 40/2 | 2026-04-13 | 2026-04-29 | 2026-05-02 | 16 | 19 | 2026-04 | 121 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP126 | 2026-04-15 |  |  |  |  | 2026-04 | 119 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 42/2 | 2026-04-16 | 2026-05-03 | 2026-05-07 | 17 | 21 | 2026-04 | 118 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP1 | 2026-04-18 |  |  |  |  | 2026-04 | 116 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | AP61 | 2026-04-21 |  |  |  |  | 2026-04 | 113 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP165 | 2026-04-22 |  |  |  |  | 2026-04 | 112 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP86 | 2026-04-23 | 2026-07-31 |  | 99 |  | 2026-04 | 111 | FALSE | FALSE | Yes | No | fallback_single_line | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 56/2 | 2026-04-25 |  |  |  |  | 2026-04 | 109 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP34 | 2026-04-25 | 2026-05-08 | 2026-05-14 | 13 | 19 | 2026-04 | 109 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP123 | 2026-04-26 | 2026-06-14 | 2026-06-20 | 49 | 55 | 2026-04 | 108 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP47 | 2026-04-26 | 2026-05-03 | 2026-05-08 | 7 | 12 | 2026-04 | 108 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP59 | 2026-04-27 |  |  |  |  | 2026-04 | 107 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 55/1 | 2026-04-28 | 2026-06-30 | 2026-07-07 | 63 | 70 | 2026-04 | 106 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 37/1 | 2026-04-29 | 2026-05-07 | 2026-05-10 | 8 | 11 | 2026-04 | 105 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP142 | 2026-04-29 | 2026-06-03 | 2026-06-10 | 35 | 42 | 2026-04 | 105 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP7 | 2026-04-29 | 2026-07-02 | 2026-07-18 | 64 | 80 | 2026-04 | 105 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 122/1 | 2026-04-30 | 2026-05-25 | 2026-06-03 | 25 | 34 | 2026-04 | 104 | TRUE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP166 | 2026-04-30 | 2026-06-21 | 2026-06-28 | 52 | 59 | 2026-04 | 104 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP41 | 2026-04-30 |  |  |  |  | 2026-04 | 104 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | AP6 | 2026-04-30 |  |  |  |  | 2026-04 | 104 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | AP64 | 2026-05-01 |  |  |  |  | 2026-05 | 103 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 33/1 | 2026-05-07 | 2026-05-17 | 2026-05-22 | 10 | 15 | 2026-05 | 97 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 64/1 | 2026-05-07 | 2026-06-11 | 2026-06-13 | 35 | 37 | 2026-05 | 97 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP144 | 2026-05-07 |  |  |  |  | 2026-05 | 97 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP56 | 2026-05-07 | 2026-06-23 | 2026-06-30 | 47 | 54 | 2026-05 | 97 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 142/1 | 2026-05-08 | 2026-05-31 | 2026-06-03 | 23 | 26 | 2026-05 | 96 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 61/1 | 2026-05-08 |  |  |  |  | 2026-05 | 96 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP82 | 2026-05-08 | 2026-06-03 | 2026-06-15 | 26 | 38 | 2026-05 | 96 | TRUE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 57/1 | 2026-05-09 |  |  |  |  | 2026-05 | 95 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP161 | 2026-05-09 |  |  |  |  | 2026-05 | 95 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP163 | 2026-05-11 |  |  |  |  | 2026-05 | 93 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 56/4 | 2026-05-13 |  |  |  |  | 2026-05 | 91 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 62/2 | 2026-05-14 |  |  |  |  | 2026-05 | 90 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 71/1 | 2026-05-14 | 2026-06-02 | 2026-06-10 | 19 | 27 | 2026-05 | 90 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP110 | 2026-05-14 |  |  |  |  | 2026-05 | 90 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP38 | 2026-05-14 | 2026-05-21 | 2026-05-26 | 7 | 12 | 2026-05 | 90 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP57 | 2026-05-15 |  |  |  |  | 2026-05 | 89 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 159/3 | 2026-05-16 |  |  |  |  | 2026-05 | 88 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 40/3 | 2026-05-16 | 2026-05-26 | 2026-06-02 | 10 | 17 | 2026-05 | 88 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 65/4 | 2026-05-16 | 2026-05-28 | 2026-05-30 | 12 | 14 | 2026-05 | 88 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 50A/2 | 2026-05-17 |  |  |  |  | 2026-05 | 87 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | AP162 | 2026-05-17 |  |  |  |  | 2026-05 | 87 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP60 | 2026-05-17 | 2026-06-14 | 2026-06-18 | 28 | 32 | 2026-05 | 87 | TRUE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 62/1 | 2026-05-18 |  |  |  |  | 2026-05 | 86 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP128 | 2026-05-18 |  |  |  |  | 2026-05 | 86 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP143 | 2026-05-18 | 2026-06-10 | 2026-06-17 | 23 | 30 | 2026-05 | 86 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP63 | 2026-05-18 |  |  |  |  | 2026-05 | 86 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 159/2 | 2026-05-19 |  |  |  |  | 2026-05 | 85 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 23/2 | 2026-05-19 | 2026-05-26 | 2026-05-29 | 7 | 10 | 2026-05 | 85 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 57/2 | 2026-05-19 |  |  |  |  | 2026-05 | 85 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP112 | 2026-05-19 |  |  |  |  | 2026-05 | 85 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP70/3 | 2026-05-19 | 2026-06-10 | 2026-06-26 | 22 | 38 | 2026-05 | 85 | TRUE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 159/1 | 2026-05-22 |  |  |  |  | 2026-05 | 82 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 60/1 | 2026-05-22 |  |  |  |  | 2026-05 | 82 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 143/1 | 2026-05-23 |  |  |  |  | 2026-05 | 81 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 50A/1 | 2026-05-23 |  |  |  |  | 2026-05 | 81 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | AP113 | 2026-05-23 |  |  |  |  | 2026-05 | 81 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP158 | 2026-05-23 |  |  |  |  | 2026-05 | 81 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP7 | 2026-05-24 |  |  |  |  | 2026-05 | 80 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | LILO
TB 605 | AP84 | 2026-05-24 |  |  |  |  | 2026-05 | 80 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 39/1 | 2026-05-25 | 2026-06-08 | 2026-06-13 | 14 | 19 | 2026-05 | 79 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP39 | 2026-05-25 | 2026-06-02 | 2026-06-08 | 8 | 14 | 2026-05 | 79 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP55 | 2026-05-25 |  |  |  |  | 2026-05 | 79 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 59/1 | 2026-05-26 | 2026-06-17 | 2026-06-22 | 22 | 27 | 2026-05 | 78 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP42 | 2026-05-26 | 2026-08-09 |  | 75 |  | 2026-05 | 78 | FALSE | FALSE | Yes | No | fallback_single_line | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | AP66 | 2026-05-26 | 2026-05-30 | 2026-06-04 | 4 | 9 | 2026-05 | 78 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 34/1 | 2026-05-28 | 2026-06-19 | 2026-06-24 | 22 | 27 | 2026-05 | 76 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 65/1 | 2026-05-28 | 2026-06-07 | 2026-06-11 | 10 | 14 | 2026-05 | 76 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP65 | 2026-05-28 | 2026-06-04 | 2026-06-07 | 7 | 10 | 2026-05 | 76 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 65/5 | 2026-05-30 |  |  |  |  | 2026-05 | 74 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP105 | 2026-05-30 |  |  |  |  | 2026-05 | 74 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP168 | 2026-05-30 |  |  |  |  | 2026-05 | 74 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP174 | 2026-05-30 |  |  |  |  | 2026-05 | 74 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP167 | 2026-05-31 |  |  |  |  | 2026-05 | 73 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP81 | 2026-05-31 |  |  |  |  | 2026-05 | 73 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 35/1 | 2026-06-03 | 2026-06-14 | 2026-06-24 | 11 | 21 | 2026-06 | 70 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 65/3 | 2026-06-03 |  |  |  |  | 2026-06 | 70 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP35 | 2026-06-03 | 2026-06-24 | 2026-07-05 | 21 | 32 | 2026-06 | 70 | TRUE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 144/1 | 2026-06-04 | 2026-06-21 | 2026-06-25 | 17 | 21 | 2026-06 | 69 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP54 | 2026-06-05 | 2026-06-29 | 2026-07-09 | 24 | 34 | 2026-06 | 68 | TRUE | FALSE | Yes | No | fallback_single_line | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP76 | 2026-06-05 | 2026-06-15 | 2026-06-21 | 10 | 16 | 2026-06 | 68 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP89 | 2026-06-05 | 2026-07-05 | 2026-07-17 | 30 | 42 | 2026-06 | 68 | TRUE | FALSE | Yes | No | fallback_single_line | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 50A/4 | 2026-06-06 |  |  |  |  | 2026-06 | 67 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | AP173 | 2026-06-06 |  |  |  |  | 2026-06 | 67 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP58 | 2026-06-06 |  |  |  |  | 2026-06 | 67 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 143/2 | 2026-06-09 |  |  |  |  | 2026-06 | 64 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 23/3 | 2026-06-09 | 2026-06-16 | 2026-06-22 | 7 | 13 | 2026-06 | 64 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 42/1 | 2026-06-09 |  |  |  |  | 2026-06 | 64 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | AP36 | 2026-06-09 | 2026-07-26 | 2026-08-06 | 47 | 58 | 2026-06 | 64 | FALSE | FALSE | Yes | No | fallback_single_line | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | AP88 | 2026-06-09 | 2026-07-18 | 2026-07-29 | 39 | 50 | 2026-06 | 64 | FALSE | FALSE | Yes | No | fallback_single_line | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP175 | 2026-06-10 |  |  |  |  | 2026-06 | 63 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP78 | 2026-06-10 |  |  |  |  | 2026-06 | 63 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 144/2 | 2026-06-12 | 2026-06-17 | 2026-06-21 | 5 | 9 | 2026-06 | 61 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 77/3 | 2026-06-12 |  |  |  |  | 2026-06 | 61 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 37/2 | 2026-06-14 |  |  |  |  | 2026-06 | 59 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | 47/3 | 2026-06-15 |  |  |  |  | 2026-06 | 58 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | AP53 | 2026-06-17 | 2026-07-27 |  | 40 |  | 2026-06 | 56 | FALSE | FALSE | Yes | No | fallback_single_line | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 180/1 | 2026-06-19 |  |  |  |  | 2026-06 | 54 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 47/2 | 2026-06-19 | 2026-07-20 | 2026-07-30 | 31 | 41 | 2026-06 | 54 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 50A/5 | 2026-06-19 | 2026-08-06 |  | 48 |  | 2026-06 | 54 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 52/1 | 2026-06-20 | 2026-08-10 |  | 51 |  | 2026-06 | 53 | FALSE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 8/1 | 2026-06-22 |  |  |  |  | 2026-06 | 51 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | LILO
TB 605 | AP172 | 2026-06-22 | 2026-06-28 | 2026-07-07 | 6 | 15 | 2026-06 | 51 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP62 | 2026-06-22 |  |  |  |  | 2026-06 | 51 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP48 | 2026-06-23 |  |  |  |  | 2026-06 | 50 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | AP140 | 2026-06-24 | 2026-06-29 | 2026-07-23 | 5 | 29 | 2026-06 | 49 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP6 | 2026-06-24 |  |  |  |  | 2026-06 | 49 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | LILO
TB 605 | 171/1 | 2026-06-25 |  |  |  |  | 2026-06 | 48 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 50A/9 | 2026-06-25 | 2026-07-16 | 2026-07-19 | 21 | 24 | 2026-06 | 48 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP151 | 2026-06-25 |  |  |  |  | 2026-06 | 48 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 56/1 | 2026-06-26 |  |  |  |  | 2026-06 | 47 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP180 | 2026-06-27 |  |  |  |  | 2026-06 | 46 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP8 | 2026-06-27 |  |  |  |  | 2026-06 | 46 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | LILO
TB 605 | 50A/10 | 2026-06-30 | 2026-07-07 | 2026-07-16 | 7 | 16 | 2026-06 | 43 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP10 | 2026-06-30 | 2026-07-06 | 2026-07-12 | 6 | 12 | 2026-06 | 43 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP5 | 2026-06-30 |  |  |  |  | 2026-06 | 43 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | LILO
TB 605 | AP52 | 2026-07-03 | 2026-07-07 | 2026-08-09 | 4 | 37 | 2026-07 | 40 | TRUE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | AP176 | 2026-07-06 |  |  |  |  | 2026-07 | 37 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP51 | 2026-07-13 | 2026-07-20 |  | 7 |  | 2026-07 | 30 | TRUE | FALSE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP13 | 2026-07-14 | 2026-07-19 | 2026-07-31 | 5 | 17 | 2026-07 | 29 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 50A/6 | 2026-07-25 | 2026-07-30 | 2026-08-06 | 5 | 12 | 2026-07 | 18 | TRUE | TRUE | Yes | No | exact | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | AP8 | 2026-07-27 |  |  |  |  | 2026-07 | 16 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | AP182 | 2026-07-31 |  |  |  |  | 2026-07 | 12 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | AP4 | 2026-08-11 |  |  |  |  | 2026-08 | 1 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | LILO
TB 605 | AP9 | 2026-08-11 |  |  |  |  | 2026-08 | 1 | FALSE | FALSE | No | No |  | TB 605 - DPR - 2026-08-12.xlsx | LILO
TB 608 | 65/3 | 2025-10-18 | 2026-07-31 | 2026-08-11 | 286 | 297 | 2025-10 | 298 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 69/2 | 2025-10-18 | 2026-04-22 | 2026-04-30 | 186 | 194 | 2025-10 | 298 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 131/2 | 2025-11-09 | 2026-03-17 | 2026-04-23 | 128 | 165 | 2025-11 | 276 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 58/1 | 2025-11-10 | 2025-12-27 | 2026-01-10 | 47 | 61 | 2025-11 | 275 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 69/0 | 2025-11-10 | 2026-04-11 | 2026-05-11 | 152 | 182 | 2025-11 | 275 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 58/0 | 2025-11-11 | 2026-04-03 | 2026-05-08 | 143 | 178 | 2025-11 | 274 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 75/5 | 2025-11-15 |  |  |  |  | 2025-11 | 270 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 34/3 | 2025-11-18 |  |  |  |  | 2025-11 | 267 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 101/0 | 2025-11-19 |  |  |  |  | 2025-11 | 266 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 71/1 | 2025-11-20 | 2025-12-28 | 2026-01-23 | 38 | 64 | 2025-11 | 265 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 33/2 | 2025-11-22 |  |  |  |  | 2025-11 | 263 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 90/0 | 2025-11-22 | 2026-05-31 | 2026-06-14 | 190 | 204 | 2025-11 | 263 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 29/0 | 2025-11-25 |  |  |  |  | 2025-11 | 260 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 40/0 | 2025-11-25 | 2026-03-31 | 2026-04-12 | 126 | 138 | 2025-11 | 260 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 72/6 | 2025-11-28 | 2026-01-21 | 2026-01-31 | 54 | 64 | 2025-11 | 257 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 88/0 | 2025-11-28 | 2026-03-25 | 2026-04-11 | 117 | 134 | 2025-11 | 257 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 100/0 | 2025-11-30 |  |  |  |  | 2025-11 | 255 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 103/0 | 2025-11-30 | 2026-05-08 | 2026-06-02 | 159 | 184 | 2025-11 | 255 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 109/0 | 2025-11-30 | 2026-08-06 |  | 249 |  | 2025-11 | 255 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 71/0 | 2025-11-30 |  |  |  |  | 2025-11 | 255 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 85/0 | 2025-11-30 | 2026-07-26 | 2026-08-04 | 238 | 247 | 2025-11 | 255 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 89/0 | 2025-11-30 | 2026-05-12 | 2026-05-22 | 163 | 173 | 2025-11 | 255 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 29/1 | 2025-12-02 |  |  |  |  | 2025-12 | 253 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 75/3 | 2025-12-03 | 2026-02-18 | 2026-02-28 | 77 | 87 | 2025-12 | 252 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 69/3 | 2025-12-08 | 2026-05-13 | 2026-05-24 | 156 | 167 | 2025-12 | 247 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 5/0 | 2025-12-10 |  |  |  |  | 2025-12 | 245 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 80/0 | 2025-12-11 | 2026-06-19 | 2026-07-04 | 190 | 205 | 2025-12 | 244 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 108/0 | 2025-12-12 |  |  |  |  | 2025-12 | 243 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 111/0 | 2025-12-12 | 2026-06-03 | 2026-06-17 | 173 | 187 | 2025-12 | 243 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 29/4 | 2025-12-14 | 2026-01-29 | 2026-02-25 | 46 | 73 | 2025-12 | 241 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 48/0 | 2025-12-14 | 2026-05-08 | 2026-05-17 | 145 | 154 | 2025-12 | 241 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 29/3 | 2025-12-17 | 2026-02-25 | 2026-03-04 | 70 | 77 | 2025-12 | 238 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 75/4 | 2025-12-18 |  |  |  |  | 2025-12 | 237 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 99/0 | 2025-12-18 |  |  |  |  | 2025-12 | 237 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 102/0 | 2025-12-19 |  |  |  |  | 2025-12 | 236 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 84/0 | 2025-12-19 | 2026-08-11 |  | 235 |  | 2025-12 | 236 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 111/1 | 2025-12-21 |  |  |  |  | 2025-12 | 234 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 83/0 | 2025-12-21 |  |  |  |  | 2025-12 | 234 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 91/0 | 2025-12-21 |  |  |  |  | 2025-12 | 234 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 93/0 | 2025-12-21 |  |  |  |  | 2025-12 | 234 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 34/1 | 2025-12-22 |  |  |  |  | 2025-12 | 233 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 25/1 | 2025-12-23 |  |  |  |  | 2025-12 | 232 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 70/3 | 2025-12-23 | 2026-01-31 | 2026-02-09 | 39 | 48 | 2025-12 | 232 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 29/2 | 2025-12-25 | 2026-03-04 | 2026-03-11 | 69 | 76 | 2025-12 | 230 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 4/1 | 2025-12-25 |  |  |  |  | 2025-12 | 230 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 112/0 | 2025-12-27 | 2026-06-14 | 2026-07-22 | 169 | 207 | 2025-12 | 228 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 49/0 | 2025-12-27 | 2026-05-17 | 2026-05-24 | 141 | 148 | 2025-12 | 228 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 91/1 | 2025-12-27 |  |  |  |  | 2025-12 | 228 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 79/1 | 2025-12-28 | 2026-05-31 | 2026-06-09 | 154 | 163 | 2025-12 | 227 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 91/2 | 2025-12-28 |  |  |  |  | 2025-12 | 227 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 114/0 | 2025-12-31 |  |  |  |  | 2025-12 | 224 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 70/2 | 2025-12-31 | 2026-02-10 | 2026-02-17 | 41 | 48 | 2025-12 | 224 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 77/0 | 2025-12-31 | 2026-03-06 | 2026-03-15 | 65 | 74 | 2025-12 | 224 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 86/0 | 2025-12-31 |  |  |  |  | 2025-12 | 224 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 91/8 | 2025-12-31 | 2026-03-17 | 2026-03-25 | 76 | 84 | 2025-12 | 224 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 94/0 | 2025-12-31 | 2026-06-14 | 2026-06-28 | 165 | 179 | 2025-12 | 224 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 41/2 | 2026-01-02 |  |  |  |  | 2026-01 | 222 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 11/2 | 2026-01-03 |  |  |  |  | 2026-01 | 221 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 70/0 | 2026-01-04 | 2026-04-30 | 2026-05-10 | 116 | 126 | 2026-01 | 220 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 40/1 | 2026-01-07 | 2026-04-12 | 2026-04-18 | 95 | 101 | 2026-01 | 217 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 97/0 | 2026-01-09 |  |  |  |  | 2026-01 | 215 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 41/0 | 2026-01-10 | 2026-04-19 | 2026-04-30 | 99 | 110 | 2026-01 | 214 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 113/0 | 2026-01-11 |  |  |  |  | 2026-01 | 213 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 76/3 | 2026-01-11 | 2026-02-28 | 2026-03-06 | 48 | 54 | 2026-01 | 213 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 91/5 | 2026-01-12 |  |  |  |  | 2026-01 | 212 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 110/0 | 2026-01-13 |  |  |  |  | 2026-01 | 211 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 115/0 | 2026-01-14 | 2026-06-03 | 2026-07-05 | 140 | 172 | 2026-01 | 210 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 8/0 | 2026-01-14 | 2026-06-13 | 2026-06-30 | 150 | 167 | 2026-01 | 210 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 76/0 | 2026-01-15 |  |  |  |  | 2026-01 | 209 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 69/4 | 2026-01-18 |  |  |  |  | 2026-01 | 206 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 75/1 | 2026-01-19 |  |  |  |  | 2026-01 | 205 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 50/0 | 2026-01-21 | 2026-05-31 | 2026-06-16 | 130 | 146 | 2026-01 | 203 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 11/1 | 2026-01-24 |  |  |  |  | 2026-01 | 200 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 123/2 | 2026-01-25 |  |  |  |  | 2026-01 | 199 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 129/1 | 2026-01-27 |  |  |  |  | 2026-01 | 197 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 34/2 | 2026-01-27 |  |  |  |  | 2026-01 | 197 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 47/1 | 2026-01-28 | 2026-06-21 | 2026-07-05 | 144 | 158 | 2026-01 | 196 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 79/0 | 2026-01-28 | 2026-06-09 | 2026-06-19 | 132 | 142 | 2026-01 | 196 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 132/1 | 2026-01-29 |  |  |  |  | 2026-01 | 195 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 69/1 | 2026-01-29 | 2026-04-09 | 2026-04-21 | 70 | 82 | 2026-01 | 195 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 91/7 | 2026-01-29 |  |  |  |  | 2026-01 | 195 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 96/0 | 2026-01-30 |  |  |  |  | 2026-01 | 194 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 128/0 | 2026-01-31 |  |  |  |  | 2026-01 | 193 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 131/0 | 2026-01-31 |  |  |  |  | 2026-01 | 193 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 75/2 | 2026-01-31 | 2026-07-31 |  | 181 |  | 2026-01 | 193 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 91/4 | 2026-01-31 |  |  |  |  | 2026-01 | 193 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 59/1 | 2026-02-05 |  |  |  |  | 2026-02 | 188 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 73/6 | 2026-02-05 |  |  |  |  | 2026-02 | 188 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 76/1 | 2026-02-05 |  |  |  |  | 2026-02 | 188 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 81/0 | 2026-02-05 | 2026-03-22 | 2026-04-09 | 45 | 63 | 2026-02 | 188 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 96/1 | 2026-02-05 |  |  |  |  | 2026-02 | 188 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 104/0 | 2026-02-08 |  |  |  |  | 2026-02 | 185 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 42/1 | 2026-02-08 | 2026-06-21 | 2026-06-30 | 133 | 142 | 2026-02 | 185 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 126/0 | 2026-02-10 |  |  |  |  | 2026-02 | 183 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 43/0 | 2026-02-10 | 2026-06-04 | 2026-06-17 | 114 | 127 | 2026-02 | 183 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 72/7 | 2026-02-11 |  |  |  |  | 2026-02 | 182 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 9/1 | 2026-02-11 | 2026-05-31 | 2026-06-12 | 109 | 121 | 2026-02 | 182 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 78/2 | 2026-02-12 | 2026-07-05 | 2026-07-19 | 143 | 157 | 2026-02 | 181 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 95/3 | 2026-02-14 |  |  |  |  | 2026-02 | 179 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 95/1 | 2026-02-16 | 2026-07-19 | 2026-07-25 | 153 | 159 | 2026-02 | 177 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 131/3 | 2026-02-17 | 2026-04-23 | 2026-05-11 | 65 | 83 | 2026-02 | 176 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 129/2 | 2026-02-18 |  |  |  |  | 2026-02 | 175 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6/1 | 2026-02-18 |  |  |  |  | 2026-02 | 175 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 95/0 | 2026-02-18 |  |  |  |  | 2026-02 | 175 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 131/1 | 2026-02-19 |  |  |  |  | 2026-02 | 174 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 44/0 | 2026-02-19 | 2026-08-09 |  | 171 |  | 2026-02 | 174 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 30/0 | 2026-02-20 |  |  |  |  | 2026-02 | 173 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 10/3 | 2026-02-22 |  |  |  |  | 2026-02 | 171 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 124/0 | 2026-02-22 |  |  |  |  | 2026-02 | 171 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 71/2 | 2026-02-22 | 2026-04-11 | 2026-04-23 | 48 | 60 | 2026-02 | 171 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 70/1 | 2026-02-23 | 2026-05-12 | 2026-05-24 | 78 | 90 | 2026-02 | 170 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 72/0 | 2026-02-23 | 2026-04-11 | 2026-05-04 | 47 | 70 | 2026-02 | 170 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 127/0 | 2026-02-25 |  |  |  |  | 2026-02 | 168 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 132/2 | 2026-02-28 |  |  |  |  | 2026-02 | 165 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 132/3 | 2026-02-28 |  |  |  |  | 2026-02 | 165 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 95/2 | 2026-02-28 | 2026-07-11 | 2026-07-19 | 133 | 141 | 2026-02 | 165 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 31/0 | 2026-03-06 |  |  |  |  | 2026-03 | 159 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 35/0 | 2026-03-08 |  |  |  |  | 2026-03 | 157 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 10/1 | 2026-03-10 |  |  |  |  | 2026-03 | 155 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 129/0 | 2026-03-10 |  |  |  |  | 2026-03 | 155 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 130/0 | 2026-03-10 |  |  |  |  | 2026-03 | 155 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 82/2 | 2026-03-10 |  |  |  |  | 2026-03 | 155 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 82/1 | 2026-03-11 |  |  |  |  | 2026-03 | 154 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 116/0 | 2026-03-12 | 2026-07-05 | 2026-07-25 | 115 | 135 | 2026-03 | 153 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 27/0 | 2026-03-14 |  |  |  |  | 2026-03 | 151 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 125/0 | 2026-03-19 |  |  |  |  | 2026-03 | 146 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 47/0 | 2026-03-28 | 2026-07-05 | 2026-07-28 | 99 | 122 | 2026-03 | 137 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6/0 | 2026-03-28 |  |  |  |  | 2026-03 | 137 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 132/0 | 2026-03-29 | 2026-05-31 | 2026-06-14 | 63 | 77 | 2026-03 | 136 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 7/0 | 2026-03-30 |  |  |  |  | 2026-03 | 135 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 34/0 | 2026-03-31 |  |  |  |  | 2026-03 | 134 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 7/2 | 2026-03-31 |  |  |  |  | 2026-03 | 134 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 92/0 | 2026-04-13 | 2026-06-28 | 2026-07-10 | 76 | 88 | 2026-04 | 121 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 9/0 | 2026-04-14 |  |  |  |  | 2026-04 | 120 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 107/1 | 2026-04-19 |  |  |  |  | 2026-04 | 115 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 7/1 | 2026-04-21 |  |  |  |  | 2026-04 | 113 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 61A/0 | 2026-04-23 | 2026-06-09 | 2026-07-09 | 47 | 77 | 2026-04 | 111 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 106/0 | 2026-04-30 |  |  |  |  | 2026-04 | 104 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 1/0 | 2026-05-06 |  |  |  |  | 2026-05 | 98 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 38/0 | 2026-05-06 |  |  |  |  | 2026-05 | 98 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 61/0 | 2026-05-06 |  |  |  |  | 2026-05 | 98 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 105/0 | 2026-05-07 |  |  |  |  | 2026-05 | 97 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 39/0 | 2026-05-12 |  |  |  |  | 2026-05 | 92 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 20/0 | 2026-05-14 | 2026-06-30 | 2026-07-22 | 47 | 69 | 2026-05 | 90 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 3/0 | 2026-05-17 |  |  |  |  | 2026-05 | 87 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 4/0 | 2026-05-24 |  |  |  |  | 2026-05 | 80 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 18/0 | 2026-05-26 | 2026-07-22 |  | 57 |  | 2026-05 | 78 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 70/4 | 2026-06-13 | 2026-07-19 | 2026-07-31 | 36 | 48 | 2026-06 | 60 | FALSE | FALSE | Yes | No | fallback_single_line | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 91/9 | 2026-06-18 |  |  |  |  | 2026-06 | 55 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 5/1 | 2026-06-21 |  |  |  |  | 2026-06 | 52 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 118/0 | 2026-06-30 |  |  |  |  | 2026-06 | 43 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 42/0 | 2026-06-30 |  |  |  |  | 2026-06 | 43 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 73/5 | 2026-07-10 |  |  |  |  | 2026-07 | 33 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 119/0 | 2026-07-19 |  |  |  |  | 2026-07 | 24 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 14/0 | 2026-07-27 |  |  |  |  | 2026-07 | 16 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 62/3 | 2026-07-29 |  |  |  |  | 2026-07 | 14 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 20/1 | 2026-07-31 |  |  |  |  | 2026-07 | 12 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 68/0 | 2026-07-31 |  |  |  |  | 2026-07 | 12 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 37/0 | 2026-08-04 |  |  |  |  | 2026-08 | 8 | FALSE | FALSE | No | No |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN