## FDN-June25 (hidden)
Project Code |  |  | TA-416
Name of Line |  |  | NEEMRANA-II-BAREILLY (PG) 765KV D/C LINE,WZ-5 (Part-III)
Activity |  |  | Foundation | Qty
|  |  | Total | 302
|  |  | Completed (May-25) | 301
|  |  | Balance | 1
Micro Plan for month |  |  | 2025-06-01 | 1 | Nos | 4925228.89 | Rs. Cr.
Achievement for Month |  |  | Wk-1 | 1 | 100% | 4925228.89 | 100%
|  |  | Wk-2 | 0 | 0% | 0 | 0%
|  |  | Wk-3 | 0 | 0% | 0 | 0%
|  |  | Wk-4 | 0 | 0% | 0 | 0%
|  |  | Wk-5 | 0 | 0% | 0 | 0%
Actual for the Month |  |  | Total | 1 | 1 | 4925228.89 | 1
Sl | Loc No. | Tower type | Classification | Conc. Vol (CuM) | Reinf (MT) | Sub-Cont | Work Plan | [7 empty] | Revenue | Actual Completion | Physical Completion | [5 empty] | Revenue Achievement | [5 empty] | Shortfall
[7 empty] | Excavation |  | Stub-setting |  | Concreting |  | Earthing | Backfilling |  |  | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total
[7 empty] | Start | End | Start | End | Start | End |  |  | Rs. Lacs. | Date | [11 empty] | Rs. Lacs. | Rs. Lacs.
1 | 38/0 | DC2+18 | FS | 261.196 | 15.029 | AVI | 2025-05-21 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 4925228.89 | 2025-06-03 | 1 |  |  |  |  | 1 | 4925228.89 | 0 | 0 | 0 | 0 | 4925228.89 | 0
2 | [21 empty] | 0 |  |  |  |  | 0 | 0 | 0
3 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 261.196 | 15.029 | [9 empty] | 4925228.89 |  | 1 | 0 | 0 | 0 | 0 | 1 | 4925228.89 | 0 | 0 | 0 | 0 | 4925228.89 | 0
[13 empty] | STUB Setting-1 |  | 7224.33
[13 empty] | Earthing-1 |  | 7782.57
[13 empty] | Total Reve |  | 4940235.79

## Stub dispatch (hidden)
Location | Project | Tower type | Structure | B LOT | Actual PRS Date | STEEL Wt (MT) | BNA Wt | Disp Bal | May'24 Disp Plan | Wk01 | WK02 | WK03 | WK04 | Jun'24 Disp Plan MT | July'24 Disp Plan | Remark
JPR | TA416 | DA | Stub - 28 Nos | TA416-00018 | 2024-04-11 | 26.8617 | 0.46323 | 26.8617 | 0 |  |  |  | 0 | 26.8617 | 0 | As on date 160 stub reieved.
JPR | TA416 | DA | Stub - 132 Nos | TA416-00026 | 2024-04-15 | 126.634 | 2.184 | 126.634 | [5 empty] | 126.634 | 0
Total |  |  | 160 | [10 empty] | 153.4957

## Erection-Oct25
Sl | Location No. | Tower type | Tower Weight | Gang Name | Manpower | Section Incharge | Supervisor | Power Tools Issued (YES/NO) | Material Feeding | Starting Date | Completion Date | Tack-welding | Final checking | Revenue Planned | Revenue Realised
1 | 3B/2 | DA+9 | 1 | Govind Mahto-01 | 36 | Shuvam Gupta | Aman Kr Singh |  | 2025-09-25 | 2025-09-26 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 9316.84
2 | 2A/0 | DD45+0 | 2 | Govind Mahto-01 | 36 | Shuvam Gupta | Aman Kr Singh |  | 2025-10-06 | 2025-10-07 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 18633.68
3 | 9/8 | DA+0 | 3 | Govind Mahto-01 | 36 | Shuvam Gupta | Aman Kr Singh |  | 2025-10-17 | 2025-10-18 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 27950.52
4 | 9/9 | DA+0 | 4 | Govind Mahto-01 | 36 | Shuvam Gupta | Aman Kr Singh |  | 2025-10-23 | 2025-10-24 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 37267.36
5 | 4/0 | DB2+9 | 5 | Jawla Singh-1 | 28 | Shuvam Gupta | Kamal Ravidas |  | 2025-09-24 | 2025-09-25 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 46584.2
6 | 3A/0 | DD45+3 | 6 | Jawla Singh-1 | 28 | Shuvam Gupta | Kamal Ravidas |  | 2025-10-07 | 2025-10-08 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 55901.04
7 | 9/10 | DA+3 | 7 | Jawla Singh-1 | 28 | Shuvam Gupta | Kamal Ravidas |  | 2025-10-18 | 2025-10-19 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 65217.88
8 | 9/11 | DA+3 | 8 | Jawla Singh-1 | 28 | Shuvam Gupta | Kamal Ravidas |  | 2025-10-25 | 2025-10-26 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 74534.72
9 | 3B/3 | DA+6 | 9 | Jwala Singh -2 | 26 | Shuvam Gupta | Rudra Kumar |  | 2025-09-24 | 2025-09-25 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 83851.56
10 | 15/7 | DA+0 | 10 | Jwala Singh -2 | 26 | Shuvam Gupta | Rudra Kumar |  | 2025-10-09 | 2025-10-10 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 93168.4
11 | 15/9 | DA+0 | 11 | Jwala Singh -2 | 26 | Shuvam Gupta | Rudra Kumar |  | 2025-10-19 | 2025-10-20 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 102485.24
12 | 15/0 | DD60+25 | 12 | Govind Mahto-02 | 29 | Shuvam Gupta | Sanjay Kumar |  | 2025-09-30 | 2025-10-01 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 111802.08
13 | 15/1 | DA+6 | 13 | Govind Mahto-02 | 29 | Shuvam Gupta | Sanjay Kumar |  | 2025-10-11 | 2025-10-12 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 121118.92
14 | 14/0 | DD60+18 | 14 | Govind Mahto-02 | 29 | Shuvam Gupta | Sanjay Kumar |  | 2025-10-18 | 2025-10-19 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 130435.76
15 | 15/8 | DA+1.5 | 15 | Bhairaw Mahto | 47 | Shuvam Gupta | Bhupendra Choudhary |  | 2025-09-26 | 2025-09-27 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 139752.6
16 | 17/0 | DC1+3 | 16 | Bhairaw Mahto | 47 | Shuvam Gupta | Bhupendra Choudhary |  | 2025-10-05 | 2025-10-06 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 149069.44
17 | 13/0 | DD60+9 | 17 | Bhairaw Mahto | 47 | Shuvam Gupta | Bhupendra Choudhary |  | 2025-10-16 | 2025-10-17 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 158386.28
18 | 10/0 | DB1+6 | 18 | Pritam Enterprises-1 | 30 | Shuvam Gupta | Sanjay Kumar |  | 2025-09-30 | 2025-10-01 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 167703.12
19 | 10/1 | DA+3 | 19 | Pritam Enterprises-1 | 30 | Shuvam Gupta | Sanjay Kumar |  | 2025-10-12 | 2025-10-13 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 177019.96
20 | 10/2 | DA+3 | 20 | Pritam Enterprises-1 | 30 | Shuvam Gupta | Sanjay Kumar |  | 2025-10-19 | 2025-10-20 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 186336.8
21 | 3B/0 | DB1+9 | 21 | Pritam Enterprises-2 | 27 | Shuvam Gupta | Akbar Ali |  | 2025-09-30 | 2025-10-01 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 195653.64
22 | 15/11 | DA+0 | 22 | Pritam Enterprises-2 | 27 | Shuvam Gupta | Akbar Ali |  | 2025-10-09 | 2025-10-10 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 204970.48
23 | 15/12 | DA+6 | 23 | Pritam Enterprises-2 | 27 | Shuvam Gupta | Akbar Ali |  | 2025-10-16 | 2025-10-17 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 214287.32
24 | 3B/1 | DA+3 | 24 | Pritam Enterprises-3 | 38 | Shuvam Gupta | Rudra Prasad |  | 2025-08-28 | 2025-08-29 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 223604.16
25 | 11/0 | DD45+0 | 25 | Pritam Enterprises-3 | 38 | Shuvam Gupta | Rudra Prasad |  | 2025-09-07 | 2025-09-08 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 232921
26 | 21/0 | DB1+0 | 26 | Pritam Enterprises-3 | 38 | Shuvam Gupta | Rudra Prasad |  | 2025-09-19 | 2025-09-20 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 242237.84
27 | 21/1 | DA+0 | 27 | Pritam Enterprises-3 | 38 | Shuvam Gupta | Rudra Prasad |  | 2025-10-01 | 2025-10-02 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 251554.68
28 | 3A/4 | DA+0 | 28 | Pritam Enterprises-4 | 29 | Shuvam Gupta | Abhiya Ojha |  | 2025-09-30 | 2025-10-01 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 260871.52
29 | 21/3 | DA+6 | 29 | Pritam Enterprises-4 | 29 | Shuvam Gupta | Abhiya Ojha |  | 2025-10-10 | 2025-10-11 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 270188.36
30 | 21/4 | DA+0 | 30 | Pritam Enterprises-4 | 29 | Shuvam Gupta | Abhiya Ojha |  | 2025-10-16 | 2025-10-17 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 279505.2
31 | 21/5 | DA+0 | 31 | Pritam Enterprises-4 | 29 | Shuvam Gupta | Abhiya Ojha |  | 2025-10-22 | 2025-10-23 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 288822.04
32 | 30/2 | DA+9 | 32 | SK.Samiul -1 | 22 | Kartik Jhorar | Haridasn |  | 2025-09-18 | 2025-09-19 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 298138.88
33 | 29A/0 | DB1+0 | 33 | SK.Samiul -1 | 22 | Shuvam Gupta | Haridasn |  | 2025-10-03 | 2025-10-04 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 307455.72
34 | 30/5 | DA+0 | 34 | SK.Samiul -1 | 22 | Kartik Jhorar | Haridasn |  | 2025-10-09 | 2025-10-10 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 316772.56
35 | 20/0 | DD60+3 | 35 | Punam kumari-1 | 33 | Shuvam Gupta | Rahul Ravidas |  | 2025-09-30 | 2025-10-01 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 326089.4
36 | 20/3 | DA+1.5 | 36 | Punam kumari-1 | 33 | Shuvam Gupta | Rahul Ravidas |  | 2025-10-07 | 2025-10-08 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 335406.24
37 | 20/4 | DA+3 | 37 | Punam kumari-1 | 33 | Shuvam Gupta | Rahul Ravidas |  | 2025-10-15 | 2025-10-16 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 344723.08
38 | 20/5 | DA+0 | 38 | Punam kumari-1 | 33 | Shuvam Gupta | Rahul Ravidas |  | 2025-10-23 | 2025-10-24 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 354039.92
39 | 18/4 | DA-3 | 39 | Punam kumari-2 | 32 | Shuvam Gupta | Nabirul Islam |  | 2025-09-30 | 2025-10-01 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 363356.76
40 | 18/5 | DA+0 | 40 | Punam kumari-2 | 32 | Shuvam Gupta | Nabirul Islam |  | 2025-10-05 | 2025-10-06 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 372673.6
41 | 18/6 | DA+9 | 41 | Punam kumari-2 | 32 | Shuvam Gupta | Nabirul Islam |  | 2025-10-12 | 2025-10-13 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 381990.44
42 | 18/7 | DA+1.5 | 42 | Punam kumari-2 | 32 | Shuvam Gupta | Nabirul Islam |  | 2025-10-19 | 2025-10-20 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 391307.28
43 | 29A/5 | DA+6 | 43 | Punam Kumari 4 | 39 | Shuvam Gupta | Manoj Gupta |  | 2025-09-24 | 2025-09-25 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 400624.12
44 | 29A/4 | DA+3 | 44 | Punam Kumari 4 | 39 | Shuvam Gupta | Manoj Gupta |  | 2025-10-04 | 2025-10-05 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 409940.96
45 | 29A/3 | DA+6 | 45 | Punam Kumari 4 | 39 | Shuvam Gupta | Manoj Gupta |  | 2025-10-11 | 2025-10-12 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 419257.8
46 | 46/0 | DB1+12 | 46 | Fouzi Ratto | 42 | Kartik Jhorar | Khooblal |  | 2025-09-29 | 2025-09-30 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 428574.64
47 | 43/0 | DB1+0 | 47 | Fouzi Ratto | 42 | Kartik Jhorar | Khooblal |  | 2025-10-08 | 2025-10-09 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 437891.48
48 | 37/3 | DA-1.5 | 48 | Fouzi Ratto | 42 | Kartik Jhorar | Khooblal |  | 2025-10-17 | 2025-10-18 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 447208.32
49 | 45/0 | DB1+9 | 49 | Sherra Const. | 38 | Kartik Jhorar | Manoj Kumar Choudhary |  | 2025-09-27 | 2025-09-28 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 456525.16
50 | 43/1 | DA-1.5 | 50 | Sherra Const. | 38 | Kartik Jhorar | Manoj Kumar Choudhary |  | 2025-10-04 | 2025-10-05 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 465842
51 | 37/2 | DA+3 | 51 | Sherra Const. | 38 | Kartik Jhorar | Manoj Kumar Choudhary |  | 2025-10-11 | 2025-10-12 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 475158.84
52 | 41/1 | DA+9 | 52 | Amar Singh | 25 | Kartik Jhorar | Raju Mahto |  | 2025-09-20 | 2025-09-21 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 484475.68
53 | 41/0 | DB1+9 | 53 | Amar Singh | 25 | Kartik Jhorar | Raju Mahto |  | 2025-10-03 | 2025-10-04 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 493792.52
54 | 24/0 | DD60+18 | 54 | Amar Singh | 25 | Shuvam Gupta | Raju Mahto |  | 2025-10-15 | 2025-10-16 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 503109.36
55 | 40/10 | DA+3 | 55 | Kartik Mahto | 38 | Kartik Jhorar | Shuseel |  | 2025-09-28 | 2025-09-29 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 512426.2
56 | 40/8 | DA-1.5 | 56 | Kartik Mahto | 38 | Kartik Jhorar | Shuseel |  | 2025-10-08 | 2025-10-09 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 521743.04
57 | 25/0 | DD60+18 | 57 | Kartik Mahto | 38 | Shuvam Gupta | Shuseel |  | 2025-10-14 | 2025-10-15 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 531059.88
Formulas:
Material Feeding = [Starting Date]-1
Tack-welding = [Completion Date]+1
Final checking = [Tack-welding]+1
Starting Date = [Completion Date, row above]
Starting Date = [Completion Date, row above]+1
Completion Date = [Starting Date]+11

## STG-Sep25 (hidden)
Project Code
Name of Line
Activity |  |  | Stringing | Qty |  |  |  |  | Rate @Kms | 905812
|  |  | Total | 115
|  |  | Completed (Aug-25) | 32.6
|  |  | Balance | 82.4
Micro Plan for month |  |  | 2025-09-01 | 23.985 | km | 21725900.82 | Rs. Cr
Achievement for Month |  |  | Wk-1 | 0 | 0% | 0 | 0%
|  |  | Wk-2 | 0 | 0% | 0 | 0%
|  |  | Wk-3 | 0 | 0% | 0 | 0%
|  |  | Wk-4 | 0 | 0% | 0 | 0%
|  |  | Wk-5 | 0 | 0% | 0 | 0%
|  |  | Total | 0 | 0% | 0 | 0%
Sl | Section | Section Length (km) | Manual/TSE | Sub-Cont | Work Plan |  |  |  |  | Revenue | Actual Completion | Physical Completion | [5 empty] | Revenue Achievement | [5 empty] | Shortfall
[5 empty] | Matl feeding | Pay-Out |  | Final Sag |  |  |  | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total
[6 empty] | Start | End | Start | End | Rs. Cr. | Date | [11 empty] | Rs. Cr. | Rs. Cr.
1 | 14/0-15/0 | 3.611 | TSE | Anarul | 2025-08-30 | 2025-09-01 | 2025-09-08 | 2025-09-09 | 2025-09-12 | 3270887.132 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3270887.132
2 | 12/0-13/0 | 3.92 | TSE |  | 2025-09-13 | 2025-09-14 | 2025-09-19 | 2025-09-20 | 2025-09-22 | 3550783.04 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3550783.04
3 | 3/0-4/0 | 0.28 | Manual-1 |  | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-12 | 2025-09-12 | 253627.36 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253627.36
4 | 11/0-12/0 | 0.313 | Manual-1 |  | 2025-09-27 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 283519.156 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283519.156
5 | 13/0-14/0 | 0.319 | Manual-1 |  | 2025-09-15 | 2025-09-16 | 2025-09-16 | 2025-09-16 | 2025-09-16 | 288954.028 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288954.028
6 | 20/0-21/0 | 4.958 | TSE | Pankaj | 2025-09-03 | 2025-09-04 | 2025-09-09 | 2025-09-10 | 2025-09-13 | 4491015.896 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4491015.896
7 | 21/0-22/0 | 1.606 | TSE |  | 2025-09-14 | 2025-09-15 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 1454734.072 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1454734.072
8 | 18/0-19/0 | 0.323 | Manual-1 |  | 2025-09-20 | 2025-09-21 | 2025-09-26 | 2025-09-27 | 2025-09-30 | 292577.276 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292577.276
9 | 36/0-37/0 | 4.947 | TSE |  | 2025-08-30 | 2025-08-31 | 2025-09-06 | 2025-09-07 | 2025-09-10 | 4481051.964 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4481051.964
10 | 30/0-31/0 | 2.75 | TSE |  | 2025-09-11 | 2025-09-12 | 2025-09-17 | 2025-09-18 | 2025-09-21 | 2490983 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2490983
11 | 29/0-30/0 | 0.27 | TSE |  | 2025-09-20 | 2025-09-20 | 2025-09-20 | 2025-09-22 | 2025-09-22 | 244569.24 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244569.24
12 | 28/0-29/0 | 0.688 | Manual-2 |  | 2025-09-27 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 623198.656 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 623198.656
13 | [9 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 23.985 | [7 empty] | 21725900.82 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21725900.82