## Sheet Names Check
Project Code | Erection Sheet Names | Stringing Sheet Names | Erection Template Check | Stringing Template Check | Erection Line Names | Stringing Line Names
TB 605 | Erection -Jammu, Erection-Punjab |  |  |  | TA 605 - Jammu; TA 605 - Punjab
TA 414 | Erection Compiled | Stringing Compiled
TA 504 | Erection Compiled | Stringing
TA 506 | Erection Compiled | Stringing
TB 507 | Erection Compiled | Stringing Compiled
TA 512 | Erection Compiled
TA 413 | Erection Compiled | Stringing Compiled
TA 419 | Erection Compiled | Stringing Stretch Readiness
TA 418 | Erection Compiled | Stringing Compiled
TA 421 | Erection Compiled | Stringing Compiled
TA 416 | Erection Compiled | Stringing compliled
TA 505 | Erection Compiled | Stringing Compiled
TB 408 | Erection Compiled | Stringing |  | Yes
TB 401 | Erection Compiled | Stringing - PKG-G
TA 325 | Erection-Compiled | Stringing Compiled
TA 509 | Erection |  | Yes
TA 601 | Erection Compiled | Stringing Compiled | Yes | Yes
TB 501 | Progress-132kV, Progress-220kV | Stringing-132KV; Stringing-220kV | Yes | Yes | Erection 132kV; Erection 220 kV | Stringing 132kV; Stringing 220kV
TA 310
TA 513 | Erection Compiled

## TB 501 132kV Stringing
Actual
Office: Neemuch
0 |  |  |  |  | Stringing Progress (Conductor & Earthwire) | [12 empty] | OPGW Progress
Stringing Section |  |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | [7 empty] | 0 | 0 |  | 0 | 0
Sl. No. | Section |  | Section Length (m) | Stretch Readiness | Insulator Hoisting | Conductor Paying Out |  |  | Final Sag |  |  | Clipping | Spacer | Jumper | Sub-Contractor Name | MP | Remarks | OPGW Paying Out |  |  | OPGW Final Sag |  |  | Sub-Contractor Name
| From | To |  |  |  | Status | DOS | DOC | Status | DOS | DOC | Status | Status | Status |  |  |  | Status | DOS | DOC | Status | DOS | DOC
To Map
S.no | From AP | To AP | Span (M) | Section Readiness | Insulator Hoisting |  | P/O Starting Date | P/O Completion Date |  | F/S Starting Date | F/S/ Completion Date | Clipping | Spacering | Jumpering | Gang Name |  | Remarks
| Sec |  |  |  | Method |  |  |  |  | P/O | [5 empty] | Length | Status | Gang Strength | Number of Fitters | Hindrance

## TB 501 220kV Stringing
Actual
Office: Neemuch
0 |  |  |  |  | Stringing Progress (Conductor & Earthwire) | [12 empty] | OPGW Progress
Stringing Section |  |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | [7 empty] | 0 | 0 |  | 0 | 0
Sl. No. | Section |  | Section Length (m) | Stretch Readiness | Insulator Hoisting | Conductor Paying Out |  |  | Final Sag |  |  | Clipping | Spacer | Jumper | Sub-Contractor Name | MP | Remarks | OPGW Paying Out |  |  | OPGW Final Sag |  |  | Sub-Contractor Name
| From | To |  |  |  | Status | DOS | DOC | Status | DOS | DOC | Status | Status | Status |  |  |  | Status | DOS | DOC | Status | DOS | DOC
To Map
S.no | From AP | To AP | Span (M) | Section Readiness | Insulator Hoisting |  | P/O Starting Date | P/O Completion Date |  | F/S Starting Date | F/S/ Completion Date | Clipping | Spacering | Jumpering | Gang Name |  | Remarks

## TB 501 220kV Erection
Actual
Sl. No. | LOC NO | Tower Type |  |  |  |  | A | B | C | D | HT | MS | pack Washar | BnA | Total Tower Weight | HT | BnA | Total Stub Weight | Deviation of Angle | State | Span Length(m) | Classification | Excavation Volume (m3) | Concreting Volume |  |  | Cement Required |  | Total Steel (Kgs) per Tower | [7 empty] | Fnd Status (C/WIP) | Manual Checklist | JMC | Excavation |  | Concreting |  | Sub-Contractor Name | Earthing Status C/WIP | Earthing Type | DOS | DOC | S/C | Erection Status C/WIP | Manual Checklist | JMC | DOS | DOC | S/C | Status C/WIP | DOS | DOC | NB qty | Sub-Contractor Name
|  |  | B2B | B2B x 4 | Barbed Wire | RC Portion |  |  |  |  | MT | MT | MT | MT | MT | MT | MT | MT | DMS |  | m |  |  | M10 (1:3:6) (m3) | M20 (1:1.5:3) (m3) | Total | nos of bags | in kg | 8mm | 10mm | 12mm | 16mm | 20mm | 25mm | Total Steel (Kgs) | Total Steel (MT) |  |  |  | DOS | DOC | DOS | 9
To Map
SL No. | Location No. | Tower Type | [12 empty] | Tower Weight | [34 empty] | Status |  |  | Starting Date | Completion Date | Gang Name

## TB 501 132kV Erection
Actual
Office: Neemuch
0
220 KV D/C Neemuch - TS | [15 empty] | Foundation | [17 empty] | Earthing |  |  |  |  | Erection |  |  |  | Tower Checking-1 | Tack-Welding |  |  |  |  | Tower Checking-2
Sl. No. | LOC NO | Tower Type | Tower Weight |  |  |  | Stub Weight |  |  |  | Chimney Extension |  |  |  | Span Length(m) | Classification | Excavation Volume (m3) | Concreting Volume |  |  | 8mm Steel | 10mm Steel | 12mm Steel | 16mm Steel | 20mm Steel | 25mmSteel | Total Steel (MT) | Status (C/WIP) | Excavation |  | Concreting |  | Sub-Contractor Name | Status C/WIP | Type | DOS | DOC | Sub-Contractor Name | Status C/WIP | DOS | DOC | Sub-Contractor Name |  | Status C/WIP | DOS | DOC | Painting | Sub-Contractor Name
|  |  | HT | MS | BnA | Total | HT | MS | BnA | Total | A | B | C | D | m |  |  | M10 (1:3:6) (m3) | M20 (1:1.5:3) (m3) | Total | [8 empty] | DOS | DOC | DOS | DOC
To Map
SL No. | Location No. | Tower Type |  |  |  | Tower Weight | [32 empty] | Status | Starting Date | Completion Date | Gang Name

## TB 401 Stringing
Actual
S. No | Section |  |  | Paying Out |  |  | Final Sag |  |  | Name of Gang | Remarks
| From | To | Length | Start Date | Finish Date | Month | Start Date | Finish Date | Month
To Map
S.no | From AP | To AP | Span (M) | P/O Starting Date | P/O Completion Date |  | F/S Starting Date | F/S/ Completion Date |  | Gang Name

## TB 408 Stringing
Actual
SL. No. | Section |  | Type of Sections | Gang Name | Section Length | Paying Out/R-Sag |  |  | Final Sag
| From | To |  |  |  | Section Length | Start Date | End Date | Section Length | Start Date | End Date | Remarks | Completion Month
To Map
S.no | From AP | To AP |  | Gang Name | Span (M) | P/O | P/O Starting Date | P/O Completion Date | Length | F/S Starting Date | F/S/ Completion Date

## TA 509 Erection
Actual
SL NO. | LOC No. | STATUS | STARTING DATE | ENDING DATE | CONTRACTOR | JMC
To Map
SL No. | Location No. | Status | Starting Date | Completion Date | Gang Name

## TA 601 Erection
Actual
SL No. | Location No. | Tower Type | Classification | Start Date | MT | Status | End Date | Gang Name | Gang Strength
To Map
SL No. | Location No. | Tower Type |  | Starting Date | Tower Weight | Status | Completion Date | Gang Name