## Project Details
Project Code | Project Name | Client Name | NOA Start Date | LOA End Date | Planning Engineer/Manager | PCH | Regional Manager | Project Manger | Section Incharge | Supervisor
TA 416 | 765KV D/C HEXA NEEMRANA II BAREILLY TL -03 | PGCIL | 2024-02-07 | 2025-11-06 | Sanjib Samantaray | Mr Arun Felbin | Mr Rajiv Sharma | Mr Sanjay Gupta | Prabin Patra | Rupesh
[9 empty] | Shikhar Pratap | Bijendra
Rahman
Sitaram
Churamani
Saidur
Madhusudan
Ritlal
Somenath
Aflaudin
Akhtarul

## MASTER SHEET
| Project Code | TA-416 | Date | 2025-11-01 |  |  | SBU Head | Mr. Rajinder Gupta
| Project Name | 765KV D/C NEEMRANA II - BAREILLY TL (Part-3) |  |  | NOA Start Date | 07.02.2025 | PCH | Mr. Arun Felbin
| Client Name | Power Grid Corporation of India Limited |  |  | NOA End Date | 06.11.2025 | Regional Manager | Mr. Rajiv Sharma
| End Date | 06.11.2025 |  |  | Planning | Sanjib Samantaray | Project Manger | Mr Sanjay Gupta
Supply Status
Activity | Unit | Final Est. Qty | L2 till Last Month | Received till Last Month | Balance as per L2 | L2 Plan for Current Month | Plan for Current Month | Progress for the Month | Received till Current Month | Gap between Suppy & Cumm.L2 | Remarks
Stub | No's | 302 | 302 | 302 | 0 | 0 | 0 | 0 | 302 | 0
Tower | No's | 302 | 302 | 302 | 0 | 0 | 0 | 0 | 302 | 0
Survey Status
Activity | Unit | Final Est. Qty | L2 till Last Month | Completed till Last Month | Approved till Last Month | Balance to Submit | Approved in current month | Balance to Approve | L2 Submission Plan for Current Month | Survey Progress For current Month | Survey Completed till Current Month | Remarks
Detailed Survey | kms | 115.134 | 115.134 | 115.134 | 115.134 | 0 | 0 | 0 | 0 | 0 | 115.134
Check Survey | kms | 115.134 | 115.134 | 115.134 | 115.134 | 0 | 0 | 0 | 0 | 0 | 115.134
Progress Status
Activity | Unit | Final Estimated Quantity | Cumulative L2 till Last Month | Cumulative Progress till Last Month | L2 for present Month | Plan for the Month | Today's Progress | Progress till Date for the Month | L2 till Current Month | Completed till Date | Balance Work | Under Progress | Gangs at Present | Remarks
Foundation | Nos | 302 | 302 | 302 | 0 | 0 | 0 | 0 | 302 | 302 | 0 | 0 | 0 | Team demobilised due to non availability of further work front.
Earthing | Nos | 302 | 302 | 302 | 0 | 0 | 0 | 0 | 302 | 302 | 0 | 0 | 0
Tower Erection | Nos | 302 | 302 | 273 | 0 | 25 | 0 | 7 | 302 | 280 | 22 | 10 | 9
Stringing | Km | 115.134 | 107 | 49 | 0 | 21 | 0.323 | 10.402 | 115 | 69.383 | 45.751 | 6 | 3 | 1 Gang shift to PGCIL site Chatri Narela line.
Sl.No | Nature of Work | GANG NAME | WIP LOCATION |  | AS ON DATE - WORK FRONT |  | REMARKS
| TOWER ERECTION | Aloriva Global | 53A/0
| TOWER ERECTION | Gourishankar/MITHILESH | 23/0 |  | 22A/0
| TOWER ERECTION | NIRANJAN SINGH | 64/1 |  | 64/2
| TOWER ERECTION | Pankaj Kumar | 62/0
| TOWER ERECTION | Amit Choudhury | 60/0
| TOWER ERECTION | Punam Kumari-1 | 49/0
| TOWER ERECTION | Punam Kumari-2 | 66/1
| TOWER ERECTION | Pinki Dewi | 59/0
| TOWER ERECTION | Mahon Mahto | 69A/0
| TOWER ERECTION | Sarvesh Enterprise | 66/0
TOWER ERECTION
TOWER ERECTION
TOWER ERECTION
TOWER ERECTION
*SUPPORT REQUIRED :
* | Required further work front for foundation works In order to sustain the manpower and Machinary.
* | Required further work front for Erection works without frequest shifting of gang In order to sustain the manpower.
* | Tree Cutting arrangements for Planned stringing stretches.
SUPPLY STATUS:
Sl. No. | Description |  | UOM | LOA Qty | As per L2 till Oct'25 | Supplied AS on Date | Supply Shortfall against L2 | Balance Qty. | Remarks
1 | STUB |  | Sets | 302 | 302 | 302 | 0 | 0
2 | TOWER PARTS |  | Sets | 302 | 302 | 302 | 0 | 0
3 | Earthing Materials |  | EA | 302 | 302 | 302 | 0 | 0
4 | 7/3.66 G.S Earthwire |  | KM | 116 | 116 | 116 | 0 | 0
5 | Conductor - ACSR AL-59 Zebra |  | KM | 4186 | 4186 | 4186 | 0 | 0
6 | 160KN CLR Insulator Supply |  | Nos | 5784 | 5784 | 5784 | 0 | 0
7 | 210KN CLR Insulator Supply |  | Nos | 7440 | 7440 | 7440 | 0 | 0
8 | OPGW supply |  | KM | 121 | 121 | 121 | 0 | 0
9 | Quadruple Tension String |  | Set | 936 | 936 | 936 | 0 | 0
10 | Double ISuspension String |  | Set | 1350 | 1350 | 1350 | 0 | 0
11 | HEXAGONAL RIGID SPACER |  | Set | 2870 | 2870 | 2760 | 110 | 110
12 | Single ISuspension String (Pilot) |  | Set | 196 | 196 | 196 | 0 | 0
13 | Mid Span Comp. Joint For Cond. |  | Set | 2100 | 2100 | 2100 | 0 | 0
14 | Spacer Damper |  | Set | 12726 | 12726 | 12726 | 0 | 0 | Balance Quantity will be supplied in OCT'25
15 | REPAIR SLEEVE FOR CONDUCTOR |  | Set | 700 | 700 | 700 | 0 | 0
16 | FLEXIBLE AL BOND |  | Set | 381 | 381 | 379 | 2 | 2
17 | Suspension Clamp E/W |  | Set | 225 | 225 | 225 | 0 | 0
18 | Vibration Damper for E/W |  | Set | 760 | 760 | 756 | 4 | 4
19 | Tension Clamp for E/W |  | Set | 156 | 156 | 154 | 2 | 2
20 | Mid Span Comp. Joint for E/W |  | Set | 64 | 64 | 64 | 0 | 0

## Erection Compiled
SL No. | Location No. | Tower Type | Classification | Starting Date | Tower Weight | Status | Completion Date | Gang Name | Gang Strength | Remark | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | 2/8 | DA+0 |  | 2024-09-01 | 43.7758 | COMPLETED | 2024-09-16 | Dewi Construction(Girendra)
2 | 2/4 | DA+0 |  | 2024-09-16 | 43.7758 | COMPLETED | 2024-09-29 | Dewi Construction(Girendra)
3 | 39/10 | DA+0 |  | 2024-09-16 | 43.7758 | COMPLETED | 2024-10-01 | Horil Mahto
4 | 20/8 | DA+0 |  | 2024-10-01 | 43.7758 | COMPLETED | 2024-10-07 | Dewi Construction(Girendra)
5 | 39/8 | DA+0 |  | 2024-10-03 | 43.7758 | COMPLETED | 2024-10-15 | Horil Mahto
6 | 20/6 | DA+0 |  | 2024-10-08 | 43.7758 | COMPLETED | 2024-10-13 | Dewi Construction(Girendra)
7 | 20/9 | DA+3 |  | 2024-10-14 | 46.0492 | COMPLETED | 2024-10-19 | Dewi Construction(Girendra)
8 | 39/7 | DA+3 |  | 2024-10-15 | 46.0492 | COMPLETED | 2024-10-24 | Horil Mahto
9 | 20/5 | DA+3 |  | 2024-10-20 | 46.0492 | COMPLETED | 2024-10-24 | Dewi Construction(Girendra)
10 | 20/7 | DA-3 |  | 2024-10-24 | 42.3742 | COMPLETED | 2024-10-29 | Dewi Construction(Girendra)
11 | 39/9 | DA+3 |  | 2024-10-24 | 46.0492 | COMPLETED | 2024-10-31 | Horil Mahto
12 | 20/12 | DA-3 |  | 2024-11-01 | 42.3742 | COMPLETED | 2024-11-04 | Dewi Construction(Girendra)
13 | 14/6 | DA+3 |  | 2024-11-05 | 46.0492 | COMPLETED | 2024-11-10 | Dewi Construction(Girendra)
14 | 39/6 | DA+3 |  | 2024-11-01 | 46.0492 | COMPLETED | 14.11.2024 | Horil Mahto
15 | 14/5 | DA+3 |  | 2024-11-10 | 46.0492 | COMPLETED | 2024-11-17 | Dewi Construction(Girendra)
16 | 14/4 | DA+3 |  | 2024-11-17 | 46.0492 | COMPLETED | 2024-11-22 | Dewi Construction(Girendra)
17 | 2/5 | DA+3 |  | 2024-11-10 | 46.0492 | COMPLETED | 2024-11-24 | Pankaj
18 | 19/3 | DA+3 |  | 2024-11-10 | 46.0492 | COMPLETED | 2024-11-26 | Reeta Bharti
19 | 6/2 | DA+3 |  | 2024-11-14 | 46.0492 | COMPLETED | 2024-11-25 | Pinky Dewi
20 | 38/3 | DA+3 |  | 2024-11-10 | 46.0492 | COMPLETED | 2024-11-25 | Horil Mahto
21 | 14/8 | DA+3 |  | 2024-11-22 | 46.0492 | COMPLETED | 2024-11-28 | Dewi Construction(Girendra)
22 | 41/1 | DA+0 |  | 2024-11-10 | 43.7758 | COMPLETED | 2024-11-29 | Amar Singh
23 | 2/7 | DA+3 |  | 2024-11-26 | 46.0492 | COMPLETED | 2024-12-03 | Pankaj
24 | 19/2 | DA+0 |  | 2024-11-28 | 43.7758 | COMPLETED | 2024-12-05 | Reeta Bharti
25 | 14/7 | DA+0 |  | 2024-11-29 | 43.7758 | COMPLETED | 2024-12-05 | Dewi Construction(Girendra)
26 | 4/3 | DA+3 |  | 2024-11-28 | 46.0492 | COMPLETED | 2024-12-05 | Pinky Dewi
27 | 36/12 | DA+0 |  | 2024-11-29 | 43.7758 | COMPLETED | 2024-12-06 | Horil Mahto
28 | 2/6 | DA+0 |  | 2024-12-01 | 43.7758 | COMPLETED | 2024-12-09 | Pankaj
29 | 41/2 | DA+3 |  | 2024-11-30 | 46.0492 | COMPLETED | 2024-12-10 | Amar Singh
30 | 14/3 | DA+0 |  | 2024-12-06 | 43.7758 | COMPLETED | 2024-12-12 | Dewi Construction(Girendra)
31 | 4/4 | DA+0 |  | 2024-12-06 | 43.7758 | COMPLETED | 2024-12-12 | Pinky Dewi
32 | 19/4 | DA+0 |  | 2024-12-06 | 43.7758 | COMPLETED | 2024-12-13 | Reeta Bharti
33 | 2/3 | DA+3 |  | 2024-12-10 | 46.0492 | COMPLETED | 2024-12-16 | Pankaj
34 | 4/2 | DA-3 |  | 2024-12-12 | 42.3742 | COMPLETED | 2024-12-16 | Pinky Dewi
35 | 14/2 | DA+0 |  | 2024-12-12 | 43.7758 | COMPLETED | 2024-12-17 | Dewi Construction(Girendra)
36 | 38/2 | DA+3 |  | 2024-12-06 | 46.0492 | COMPLETED | 2024-12-19 | Horil Mahto
37 | 45/3 | DA-3 |  | 2024-12-10 | 42.3742 | COMPLETED | 2024-12-20 | Amar Singh
38 | 19/1 | DA+0 |  | 2024-12-13 | 43.7758 | COMPLETED | 2024-12-21 | Reeta Bharti
39 | 4/8 | DA+0 |  | 2024-12-17 | 43.7758 | COMPLETED | 2024-12-22 | Pinky Dewi
40 | 14/1 | DA+0 |  | 2024-12-18 | 43.7758 | COMPLETED | 2024-12-23 | Dewi Construction(Girendra)
41 | 7/10 | DA+3 |  | 2024-12-18 | 46.0492 | COMPLETED | 2024-12-23 | Pankaj
42 | 45/2 | DA+3 |  | 2024-12-21 | 46.0492 | COMPLETED | 2024-12-27 | Amar Singh
43 | 19/5 | DA-3 |  | 2024-12-22 | 42.3742 | COMPLETED | 2024-12-27 | Reeta Bharti
44 | 4/7 | DA+3 |  | 2024-12-24 | 46.0492 | COMPLETED | 2024-12-27 | Pinky Dewi
45 | 7/9 | DA+0 |  | 2024-12-24 | 43.7758 | COMPLETED | 2024-12-30 | Pankaj
46 | 38/4 | DA+3 |  | 2024-12-20 | 46.0492 | COMPLETED | 2024-12-31 | Horil Mahto
47 | 17/1 | DA-3 |  | 2024-12-24 | 42.3742 | COMPLETED | 2024-12-31 | Dewi Construction(Girendra)
48 | 31/3 | DA+3 |  | 2024-12-24 | 46.0492 | COMPLETED | 2025-01-03 | ASC heights
49 | 4/5 | DA+3 |  | 2024-12-28 | 46.0492 | COMPLETED | 2025-01-03 | Pinky Dewi
50 | 46/1 | DA+0 |  | 2024-12-28 | 43.7758 | COMPLETED | 2025-01-04 | Amar Singh
51 | 7/2 | DA+3 |  | 2024-12-31 | 46.0492 | COMPLETED | 2025-01-07 | Pankaj
52 | 19/6 | DA+0 |  | 2024-12-28 | 43.7758 | COMPLETED | 2025-01-08 | Reeta Bharti
53 | 17/4 | DA+3 |  | 2025-01-01 | 46.0492 | COMPLETED | 2025-01-10 | Dewi Construction(Girendra)
54 | 31/4 | DA-3 |  | 2025-01-04 | 42.3742 | COMPLETED | 2025-01-11 | ASC heights
55 | 12/2 | DA+3 |  | 2025-01-03 | 46.0492 | COMPLETED | 2025-01-11 | Pinky Dewi
56 | 7/8 | DA+3 |  | 2025-01-08 | 46.0492 | COMPLETED | 2025-01-14 | Pankaj
57 | 36/3 | DA+3 |  | 2025-01-07 | 46.0492 | COMPLETED | 2025-01-15 | Amar Singh
58 | 38/1 | DA+3 |  | 2025-01-07 | 46.0492 | COMPLETED | 2025-01-17 | Horil Mahto
59 | 19/7 | DA+3 |  | 2025-01-09 | 46.0492 | COMPLETED | 2025-01-17 | Reeta Bharti
60 | 17/3 | DA+0 |  | 2025-01-10 | 43.7758 | COMPLETED | 2025-01-17 | Dewi Construction(Girendra)
61 | 31/2 | DA+0 |  | 2025-01-11 | 43.7758 | COMPLETED | 2025-01-19 | ASC heights
62 | 12/3 | DA+3 |  | 2025-01-12 | 46.0492 | COMPLETED | 2025-01-21 | Pinky Dewi
63 | 7/7 | DA+0 |  | 2025-01-15 | 43.7758 | COMPLETED | 2025-01-22 | Pankaj
64 | 17/2 | DA+0 |  | 2025-01-17 | 43.7758 | COMPLETED | 2025-01-23 | Dewi Construction(Girendra)
65 | 36/5 | DA+0 |  | 2025-01-15 | 43.7758 | COMPLETED | 2025-01-24 | Amar Singh
66 | 31/6 | DA+3 |  | 2025-01-20 | 46.0492 | COMPLETED | 2025-01-25 | ASC heights
67 | 12/4 | DA+3 |  | 2025-01-21 | 46.0492 | COMPLETED | 2025-01-25 | Pinky Dewi
68 | 19/9 | DA+3 |  | 2025-01-16 | 46.0492 | COMPLETED | 2025-01-27 | Reeta Bharti
69 | 35/1 | DA+3 |  | 2025-01-16 | 46.0492 | COMPLETED | 2025-01-28 | Horil Mahto
70 | 17/5 | DA+3 |  | 2025-01-24 | 46.0492 | COMPLETED | 2025-01-29 | Dewi Construction(Girendra) |  |  | 1: 3; 16: 3; 17: 2; 18: 2; 19: 1; 20: 1; 21: 4; 22: 1; 23: 1; 24: 2; 25: 2; 26: 1; 27: 3; 28: 1; 29: 2; 30: 1; 31: 3
71 | 7/6 | DA+0 |  | 2025-01-21 | 43.7758 | COMPLETED | 2025-01-30 | Pankaj
72 | 36/1 | DA+3 |  | 2025-01-25 | 46.0492 | COMPLETED | 2025-01-30 | Amar Singh
73 | 33/10 | DA+3 |  | 2025-01-21 | 46.0492 | COMPLETED | 2025-01-31 | Rudra Construction
74 | 12/5 | DA+3 |  | 2025-01-25 | 46.0492 | COMPLETED | 2025-02-01 | Pinky Dewi
75 | 31/1 | DA+0 |  | 2025-01-25 | 43.7758 | COMPLETED | 2025-02-02 | ASC heights |  |  | 1: 3; 2: 1; 3: 7; 4: 2; 5: 6; 6: 1; 7: 6; 8: 5; 9: 2; 10: 1; 31: 1
76 | 17/7 | DA+3 |  | 2025-01-30 | 46.0492 | COMPLETED | 2025-02-05 | Dewi Construction(Girendra) |  |  | 1: 1; 2: 2; 3: 2; 4: 3; 5: 17; 6: 6; 7: 3; 8: 15; 9: 2; 10: 1; 11: 9; 12: 2
77 | 20/0 | DB+0 |  | 2025-01-28 | 64.4817 | COMPLETED | 2025-02-06 | Reeta Bharti |  |  | 3: 5.91; 4: 8.93; 5: 9.52; 6: 1.67; 7: 1.87
78 | 36/2 | DA+0 |  | 2025-02-02 | 43.7758 | COMPLETED | 2025-02-07 | Amar Singh
79 | 12/9 | DA+3 |  | 2025-02-02 | 46.0492 | COMPLETED | 2025-02-08 | Pinky Dewi
80 | 7/5 | DA+3 |  | 2025-01-29 | 46.0492 | COMPLETED | 2025-02-09 | Pankaj |  |  | 9: 1; 10: 2; 11: 10; 12: 13; 13: 3
81 | 31/7 | DA+0 |  | 2025-02-03 | 43.7758 | COMPLETED | 2025-02-10 | ASC heights
82 | 35/0 | DC+0 |  | 2025-01-29 | 73.4258 | COMPLETED | 2025-02-11 | Horil Mahto |  |  | 12: 3.88; 13: 3.74; 14: 2.37; 15: 2.87; 16: 4.33; 17: 1.63; 18: 3.32; 19: 4.2; 20: 1.91; 21: 0.98; 22: 4.07
83 | 33/11 | DA+3 |  | 2025-02-02 | 46.0492 | COMPLETED | 2025-02-12 | Rudra Construction |  |  | 14: 5.56; 15: 6.8; 16: 8.93; 17: 2.19; 18: 2.48; 19: 2.29; 20: 5.28; 21: 6.24; 22: 3.45; 23: 3.31; 24: 3.19; 25: 1.98
84 | 21/0 | DB+0 |  | 2025-02-06 | 64.4817 | COMPLETED | 2025-02-13 | Dewi Construction(Girendra) |  |  | 16: 17; 17: 15; 18: 4; 19: 3; 20: 2; 21: 14; 22: 1; 23: 4
85 | 20/2 | DA+0 |  | 2025-02-07 | 43.7758 | COMPLETED | 2025-02-13 | Reeta Bharti
86 | 35/9 | DA+3 |  | 2025-02-08 | 46.0492 | COMPLETED | 2025-02-15 | Amar Singh
87 | 8/1 | DA+3 |  | 2025-02-09 | 46.0492 | COMPLETED | 2025-02-15 | Pinky Dewi
88 | 7/4 | DA+0 |  | 2025-02-10 | 43.7758 | COMPLETED | 2025-02-18 | Pankaj
89 | 20/3 | DA+0 |  | 2025-02-12 | 43.7758 | COMPLETED | 2025-02-19 | Reeta Bharti
90 | 31/9 | DA+3 |  | 2025-02-11 | 46.0492 | COMPLETED | 2025-02-20 | ASC heights
91 | 34/7 | DA+3 |  | 2025-02-12 | 46.0492 | COMPLETED | 2025-02-20 | Horil Mahto
92 | 33/6 | DA+3 |  | 2025-02-14 | 46.0492 | COMPLETED | 2025-02-20 | Dewi Construction(Girendra)
93 | 8/2 | DA+0 |  | 2025-02-16 | 43.7758 | COMPLETED | 2025-02-21 | Pinky Dewi
94 | 35/7 | DA+3 |  | 2025-02-16 | 46.0492 | COMPLETED | 2025-02-21 | Amar Singh
95 | 33/9 | DA+0 |  | 2025-02-14 | 43.7758 | COMPLETED | 2025-02-22 | Rudra Construction
96 | 20/4 | DA-3 |  | 2025-02-20 | 42.3742 | COMPLETED | 2025-02-25 | Reeta Bharti
97 | 33/7 | DA+3 |  | 2025-02-21 | 46.0492 | COMPLETED | 2025-02-25 | Dewi Construction(Girendra)
98 | 7/1 | DA+0 |  | 2025-02-19 | 43.7758 | COMPLETED | 2025-02-25 | Pankaj
99 | 34/6 | DA+0 |  | 2025-02-21 | 43.7758 | COMPLETED | 2025-02-27 | Horil Mahto
100 | 35/4 | DA+0 |  | 2025-02-20 | 43.7758 | COMPLETED | 2025-02-27 | Amar Singh
101 | 31/0 | DB+0 |  | 2025-02-19 | 64.4817 | COMPLETED | 2025-02-28 | ASC heights
102 | 8/0 | DB+0 |  | 2025-02-22 | 64.4817 | COMPLETED | 2025-02-28 | Pinky Dewi
103 | 33/3 | DA+3 |  | 2025-02-26 | 46.0492 | COMPLETED | 2025-03-02 | Dewi Construction(Girendra)
104 | 35/5 | DA+3 |  | 2025-02-27 | 46.0492 | COMPLETED | 2025-03-03 | Amar Singh
105 | 4/10 | DA+3 |  | 2025-03-01 | 46.0492 | COMPLETED | 2025-03-05 | Reeta Bharti
106 | 33/8 | DA+3 |  | 2025-03-03 | 46.0492 | COMPLETED | 2025-03-07 | Dewi Construction(Girendra)
107 | 7/0 | DB+0 |  | 2025-02-27 | 64.4817 | COMPLETED | 2025-03-08 | Pankaj
108 | 7/11 | DA+0 |  | 2025-03-01 | 43.7758 | COMPLETED | 2025-03-08 | Pinky Dewi
109 | 35/3 | DA+0 |  | 2025-02-28 | 43.7758 | COMPLETED | 2025-03-08 | Horil Mahto
110 | 30/4 | DA+3 |  | 2025-03-01 | 46.0492 | COMPLETED | 2025-03-09 | ASC heights
111 | 34/1 | DA+3 |  | 2025-03-01 | 46.0492 | COMPLETED | 2025-03-11 | Rudra Construction
112 | 33/4 | DA-3 |  | 2025-03-08 | 42.3742 | COMPLETED | 2025-03-11 | Dewi Construction(Girendra)
113 | 8/3 | DA-3 |  | 2025-03-08 | 42.3742 | COMPLETED | 2025-03-12 | Pinky Dewi
114 | 5/0 | DB+0 |  | 2025-03-01 | 64.4817 | COMPLETED | 2025-03-13 | Reeta Bharti
115 | 30/5 | DA+0 |  | 2025-03-10 | 43.7758 | COMPLETED | 2025-03-16 | ASC heights
116 | 35/6 | DA+0 |  | 2025-03-10 | 43.7758 | COMPLETED | 2025-03-18 | Horil Mahto
117 | 33/1 | DA-3 |  | 2025-03-12 | 42.3742 | COMPLETED | 2025-03-18 | Dewi Construction(Girendra)
118 | 6/1 | DA+3 |  | 2025-03-09 | 46.0492 | COMPLETED | 2025-03-19 | Pankaj
119 | 8/4 | DA+9 |  | 2025-03-13 | 55.3387 | COMPLETED | 2025-03-21 | Pinky Dewi
120 | 5/1 | DA+3 |  | 2025-03-16 | 46.0492 | COMPLETED | 2025-03-21 | Reeta Bharti
121 | 31/8 | DA-3 |  | 2025-03-16 | 42.3742 | COMPLETED | 2025-03-23 | ASC heights
122 | 33/2 | DA-3 |  | 2025-03-19 | 42.3742 | COMPLETED | 2025-03-23 | Dewi Construction(Girendra)
123 | 8B/1 | DA-3 |  | 2025-03-22 | 42.3742 | COMPLETED | 2025-03-26 | Pinky Dewi
124 | 7/3 | DA-3 |  | 2025-03-20 | 42.3742 | COMPLETED | 2025-03-27 | Pankaj
125 | 6/0 | DB+0 |  | 2025-03-22 | 64.4817 | COMPLETED | 2025-03-29 | Reeta Bharti
126 | 35/2 | DA-3 |  | 2025-03-20 | 42.3742 | COMPLETED | 2025-03-30 | Horil Mahto
127 | 31/10 | DA-3 |  | 2025-03-24 | 42.3742 | COMPLETED | 2025-03-30 | ASC heights
128 | 34/0 | DB+0 |  | 2025-03-24 | 64.4817 | COMPLETED | 2025-03-31 | Dewi Construction(Girendra)
129 | 38/8 | DA+3 |  | 2025-03-21 | 46.0492 | COMPLETED | 2025-03-31 | M K infra
130 | 35/8 | DA-3 |  | 2025-03-22 | 42.3742 | COMPLETED | 2025-03-31 | Amar Singh
131 | 39/3 | DA+3 |  | 2025-03-24 | 46.0492 | COMPLETED | 2025-03-31 | Ananya Traders-1
132 | 8B/5 | DA+6 |  | 2025-03-24 | 53.3239 | COMPLETED | 2025-03-31 | Pinky Dewi
133 | 4/6 | DA+0 |  | 2025-03-28 | 43.7758 | COMPLETED | 2025-04-05 | Reeta Bharti
134 | 8B/3 | DA+3 |  | 2025-03-28 | 46.0492 | COMPLETED | 2025-04-07 | Pinky Dewi
135 | 20/11 | DA-3 |  | 2025-03-31 | 42.3742 | COMPLETED | 2025-04-08 | Gagan enterprise.1
136 | 34/4 | DA-3 |  | 2025-04-03 | 42.3742 | COMPLETED | 2025-04-10 | Dewi Construction(Girendra)
137 | 4/1 | DA+3 |  | 2025-03-31 | 46.0492 | COMPLETED | 2025-04-11 | Anand Construction
138 | 38/6 | DA+3 |  | 2025-04-01 | 46.0492 | COMPLETED | 2025-04-11 | M K infra
139 | 9/0 | DB+6 |  | 2025-04-01 | 75.8584 | COMPLETED | 2025-04-11 | Gagan enterprise.2
140 | 32/0 | DC+6 |  | 2025-04-01 | 87.0116 | COMPLETED | 2025-04-11 | ASC heights
141 | 39/1 | DA+3 |  | 2025-04-01 | 46.0492 | COMPLETED | 2025-04-12 | Ananya Traders-1
142 | 53A/4 | DA+3 |  | 2025-04-01 | 46.0492 | COMPLETED | 2025-04-12 | Horil Mahto
143 | 8B/2 | DA-3 |  | 2025-04-08 | 42.3742 | COMPLETED | 2025-04-13 | Pinky Dewi
144 | 36/0 | DB+0 |  | 2025-04-02 | 64.4817 | COMPLETED | 2025-04-14 | Amar Singh
145 | 20/10 | DA+3 |  | 2025-04-09 | 46.0492 | COMPLETED | 2025-04-15 | Gagan enterprise.1
146 | 52/6 | DA+3 |  | 2025-04-05 | 46.0492 | COMPLETED | 2025-04-16 | Ananya Traders-2
147 | 10/1 | DA-3 |  | 2025-04-12 | 42.3742 | COMPLETED | 2025-04-16 | Gagan enterprise.2
148 | 4/0 | DD45+0 |  | 2025-04-06 | 86.2562 | COMPLETED | 2025-04-17 | Reeta Bharti
149 | 39/0 | DB+0 |  | 2025-04-12 | 64.4817 | COMPLETED | 2025-04-19 | Ananya Traders-1
150 | 8B/4 | DA+6 |  | 2025-04-14 | 53.3239 | COMPLETED | 2025-04-21 | Pinky Dewi
151 | 31/5 | DA-3 |  | 2025-04-12 | 42.3742 | COMPLETED | 2025-04-21 | ASC heights
152 | 33/0 | DC+6 |  | 2025-04-12 | 87.0116 | COMPLETED | 2025-04-22 | Dewi Construction(Girendra)
153 | 38/7 | DA-3 |  | 2025-04-12 | 42.3742 | COMPLETED | 2025-04-22 | M K infra
154 | 36/6 | DA+3 |  | 2025-04-12 | 46.0492 | COMPLETED | 2025-04-22 | Amar Singh
155 | 20/1 | DA+6 |  | 2025-04-16 | 53.3239 | COMPLETED | 2025-04-22 | Gagan enterprise.1
156 | 25/2 | DA+0 |  | 2025-04-15 | 43.7758 | COMPLETED | 2025-04-23 | Rudra Construction
157 | 52/5 | DA-3 |  | 2025-04-17 | 42.3742 | COMPLETED | 2025-04-25 | Ananya Traders-2
158 | 0/4 | DA+9 |  | 2025-04-12 | 55.3387 | COMPLETED | 2025-04-26 | Anand Construction
159 | 19/12 | DA-3 |  | 2025-04-23 | 42.3742 | COMPLETED | 2025-04-26 | Gagan enterprise.1
160 | 39/2 | DA-3 |  | 2025-04-20 | 42.3742 | COMPLETED | 2025-04-26 | Ananya Traders-1
161 | 36/7 | DA+3 |  | 2025-04-23 | 46.0492 | COMPLETED | 2025-04-28 | Amar Singh
162 | 34/2 | DA+3 |  | 2025-04-23 | 46.0492 | COMPLETED | 2025-04-28 | Dewi Construction(Girendra)
163 | 10/0 | DB+9 |  | 2025-04-17 | 78.6775 | COMPLETED | 2025-04-28 | Gagan enterprise.2
164 | 30/6 | DA-3 |  | 2025-04-22 | 42.3742 | COMPLETED | 2025-04-28 | ASC heights
165 | 52/4 | DA-3 |  | 2025-04-26 | 42.3742 | COMPLETED | 2025-04-29 | Ananya Traders-2
166 | 38/9 | DA-3 |  | 2025-04-23 | 42.3742 | COMPLETED | 2025-06-01 | M K infra
167 | 8A/0 | DD60+0 |  | 2025-04-22 | 97.2286 | COMPLETED | 2025-04-30 | Pinky Dewi
168 | 19/11 | DA-3 |  | 2025-04-27 | 42.3742 | COMPLETED | 2025-04-30 | Gagan enterprise.1
169 | 34/3 | DA+3 |  | 2025-04-29 | 46.0492 | COMPLETED | 2025-05-03 | Dewi Construction(Girendra)
170 | 39/4 | DA+3 |  | 2025-04-29 | 46.0492 | COMPLETED | 2025-05-04 | Ananya Traders-1
171 | 36/8 | DA-3 |  | 2025-04-29 | 42.3742 | COMPLETED | 2025-05-05 | Amar Singh
172 | 19/10 | DA+3 |  | 2025-04-30 | 46.0492 | COMPLETED | 2025-05-06 | Gagan enterprise.1
173 | 30/3 | DA+0 |  | 2025-04-30 | 43.7758 | COMPLETED | 2025-05-06 | ASC heights
174 | 52/3 | DA-3 |  | 2025-04-30 | 42.3742 | COMPLETED | 2025-05-06 | Ananya Traders-2
175 | 25/3 | DA+3 |  | 2025-04-30 | 46.0492 | COMPLETED | 2025-05-07 | Rudra Construction
176 | 19/8 | DA-3 |  | 2025-05-06 | 42.3742 | COMPLETED | 2025-05-09 | Gagan enterprise.1
177 | 12/1 | DA-3 |  | 2025-05-04 | 42.3742 | COMPLETED | 2025-05-10 | Gagan enterprise.2
178 | 4/9 | DA-3 |  | 2025-05-04 | 42.3742 | COMPLETED | 2025-05-11 | Reeta Bharti
179 | 39/5 | DA-3 |  | 2025-05-05 | 42.3742 | COMPLETED | 2025-05-11 | Ananya Traders-1
180 | 52/2 | DA+3 |  | 2025-05-07 | 46.0492 | COMPLETED | 2025-05-12 | Ananya Traders-2
181 | 30/1 | DA-3 |  | 2025-05-07 | 42.3742 | COMPLETED | 2025-05-13 | ASC heights
182 | 36/4 | DA+0 |  | 2025-05-07 | 43.7758 | COMPLETED | 2025-05-13 | Amar Singh
183 | 56/2 | DA+3 |  | 2025-05-07 | 46.0492 | COMPLETED | 2025-05-14 | Dewi Construction(Girendra)
184 | 8B/0 | DD60+0 |  | 2025-05-05 | 97.2286 | COMPLETED | 2025-05-14 | Pinky Dewi
185 | 17/8 | DA-3 |  | 2025-05-11 | 42.3742 | COMPLETED | 2025-05-15 | Gagan enterprise.1
186 | 52/9 | DA-3 |  | 2025-05-13 | 42.3742 | COMPLETED | 2025-05-17 | Ananya Traders-2
187 | 56/1 | DA+0 |  | 2025-05-14 | 43.7758 | COMPLETED | 2025-05-19 | Dewi Construction(Girendra)
188 | 36/11 | DA-3 |  | 2025-05-14 | 42.3742 | COMPLETED | 2025-05-19 | Amar Singh
189 | 38/11 | DA+3 |  | 2025-05-12 | 46.0492 | COMPLETED | 2025-05-19 | Ananya Traders-1
190 | 30/2 | DA-3 |  | 2025-05-14 | 42.3742 | COMPLETED | 2025-05-20 | ASC heights
191 | 2/1 | DA+3 |  | 2025-05-12 | 46.0492 | COMPLETED | 2025-05-21 | Reeta Bharti
192 | 52/10 | DA+3 |  | 2025-05-16 | 46.0492 | COMPLETED | 2025-05-21 | Ananya Traders-2
193 | 23/3 | DA-3 |  | 2025-05-15 | 42.3742 | COMPLETED | 2025-05-22 | Pinky Dewi
194 | 12/6 | DA-3 |  | 2025-05-11 | 42.3742 | COMPLETED | 2025-05-22 | Gagan enterprise.2
195 | 53/1 | DA+6 |  | 2025-05-12 | 53.3239 | COMPLETED | 2025-05-22 | Amit Const
196 | 36/9 | DA-3 |  | 2025-05-20 | 42.3742 | COMPLETED | 2025-05-24 | Amar Singh
197 | 38/10 | DA-3 |  | 2025-05-20 | 42.3742 | COMPLETED | 2025-05-24 | Ananya Traders-1
198 | 56/3 | DA-3 |  | 2025-05-20 | 42.3742 | COMPLETED | 2025-05-24 | Dewi Construction(Girendra)
199 | 15/0 | DC+3 |  | 2025-05-16 | 78.0732 | COMPLETED | 2025-05-25 | Gagan enterprise.1
200 | 23/5 | DA-3 |  | 2025-05-10 | 42.3742 | COMPLETED | 2025-05-27 | Rudra Construction
201 | 52/8 | DA-3 |  | 2025-05-22 | 42.3742 | COMPLETED | 2025-05-27 | Ananya Traders-2
202 | 23/4 | DA-3 |  | 2025-05-23 | 42.3742 | COMPLETED | 2025-05-28 | Pinky Dewi
203 | 0/2 | DA-3 |  | 2025-05-23 | 42.3742 | COMPLETED | 2025-05-30 | Reeta Bharti
204 | 56/4 | DA-3 |  | 2025-05-23 | 42.3742 | COMPLETED | 2025-05-30 | Dewi Construction(Girendra)
205 | 12/8 | DA-3 |  | 2025-05-26 | 42.3742 | COMPLETED | 2025-05-31 | Gagan enterprise.1
206 | 36/10 | DA-3 |  | 2025-05-25 | 42.3742 | COMPLETED | 2025-05-31 | Amar Singh
207 | 38/5 | DA+3 |  | 2025-05-28 | 46.0492 | COMPLETED | 2025-06-02 | Ananya Traders-1
208 | 23/1 | DA+9 |  | 2025-05-28 | 55.3387 | COMPLETED | 2025-06-03 | Pinky Dewi
209 | 0/3 | DA-3 |  | 2025-05-25 | 42.3742 | COMPLETED | 2025-06-04 | Reeta Bharti
210 | 56/5 | DA-3 |  | 2025-05-30 | 42.3742 | COMPLETED | 2025-06-04 | Dewi Construction(Girendra)
211 | 51/0 | DD60+0 |  | 2025-05-27 | 97.2286 | COMPLETED | 2025-06-07 | Ananya Traders-2
212 | 23/2 | DA+0 |  | 2025-06-04 | 43.7758 | COMPLETED | 2025-06-09 | Pinky Dewi
213 | 33/5 | DA+3 |  | 2025-06-02 | 46.0492 | COMPLETED | 2025-06-10 | Amar Singh
214 | 0/1 | DA-3 |  | 2025-06-04 | 42.3742 | COMPLETED | 2025-06-11 | Reeta Bharti
215 | 50/1 | DA+0 |  | 2025-06-08 | 43.7758 | COMPLETED | 2025-06-13 | Ananya Traders-2
216 | 53A/5 | DA-3 |  | 2025-06-02 | 42.3742 | COMPLETED | 2025-06-14 | Devine
217 | 34/5 | DA+0 |  | 2025-06-12 | 43.7758 | COMPLETED | 2025-06-18 | Amar Singh
218 | 53A/2 | DA+3 |  | 2025-06-10 | 46.0492 | COMPLETED | 2025-06-18 | Amit Const
219 | 22/0 | DB+3 |  | 2025-06-12 | 67.112 | COMPLETED | 2025-06-20 | Pinky Dewi
220 | 30/0 | DD60+18 |  | 2025-05-25 | 143.4621 | COMPLETED | 2025-06-21 | ASC heights
221 | 3/0 | DC+0 |  | 2025-06-12 | 73.4258 | COMPLETED | 2025-06-23 | Reeta Bharti
222 | 21/2 | DA+3 |  | 2025-06-21 | 46.0492 | COMPLETED | 2025-06-26 | Pinky Dewi
223 | 45/1 | DA+3 |  | 2025-06-10 | 46.0492 | COMPLETED | 2025-06-27 | M K infra
224 | 53A/3 | DA+3 |  | 2025-06-20 | 46.0492 | COMPLETED | 2025-06-29 | Amit Const
225 | 48/0 | DD45+9 |  | 2025-06-15 | 104.8666 | COMPLETED | 2025-06-29 | Ananya Traders-2
226 | 12/7 | DA-3 |  | 2025-06-24 | 42.3742 | COMPLETED | 2025-06-30 | Reeta Bharti
227 | 21/1 | DA-3 |  | 2025-06-27 | 42.3742 | COMPLETED | 2025-06-30 | Pinky Dewi
228 | 40/0 | DD60+25 |  | 2025-06-04 | 161.3552 | COMPLETED | 2025-06-30 | Ananya Traders-1
229 | 14/0 | DD60+30 |  | 2025-06-01 | 188.3779 | COMPLETED | 2025-06-30 | Gagan enterprise.1
230 | 28/1 | DA+3 |  | 2025-06-24 | 46.0492 | COMPLETED | 2025-07-05 | ASC heights
231 | 21/3 | DA+3 |  | 2025-07-01 | 46.0492 | COMPLETED | 2025-07-07 | Pinky Dewi
232 | 25/1 | DA+9 |  | 2025-07-01 | 55.3387 | COMPLETED | 2025-07-12 | Reeta Bharti
233 | 44/0 | DD60+3 |  | 2025-07-05 | 101.692 | COMPLETED | 2025-07-18 | Ananya Traders-1
234 | 56/0 | DD45+0 |  | 2025-06-28 | 86.2562 | COMPLETED | 2025-07-22 | Amar singh
235 | 28/0 | DD60+0 |  | 2025-07-08 | 97.2286 | COMPLETED | 2025-07-31 | Reeta Bharti
236 | 41/0 | DD60+18 |  | 2025-07-20 | 143.4621 | COMPLETED | 2025-08-08 | Ananya Traders-1
237 | 13/0 | DD60+30 |  | 2025-07-09 | 188.3779 | COMPLETED | 2025-08-11 | Gagan enterprise.1
238 | 53A/6 | DA+3 |  | 2025-07-27 | 46.0492 | COMPLETED | 2025-08-17 | Punam Kumari
239 | 46/2 | DA+3 |  | 2025-08-14 | 46.0492 | COMPLETED | 2025-08-26 | Gagan enterprise.2 (Kajol)
240 | 24/0 | DD60+25 |  | 2025-07-26 | 161.3552 | COMPLETED | 2025-08-27 | Kongres Kumar-1
241 | 65/0 | DD60+0 |  | 2025-08-02 | 97.2286 | COMPLETED | 2025-08-30 | Kongres Kumar-2
242 | 18/0 | DB+6 |  | 2025-08-04 | 75.8584 | COMPLETED | 2025-08-30 | Sainik Trader
243 | 1/0 | DC+3 |  | 2025-08-09 | 78.0732 | COMPLETED | 2025-08-30 | Radha Construction
244 | 12/0 | DB+18 |  | 2025-08-12 | 97.6534 | COMPLETED | 2025-09-02 | Gagan enterprise.1
245 | 54/1 | DA+9 |  | 2025-08-18 | 55.3387 | COMPLETED | 2025-09-04 | Punam Kumari
246 | 43/0 | DD60+9 |  | 2025-08-10 | 118.4303 | COMPLETED | 2025-09-06 | Ananya Traders-1
247 | 16/0 | DB+25 |  | 2025-08-16 | 110.6255 | COMPLETED | 2025-09-14 | Amit Choudhury
248 | 11/0 | DB+18 |  | 2025-08-24 | 97.6534 | COMPLETED | 2025-09-14 | Gouri Shankar
249 | 2/0 | DD45+3 |  | 2025-09-03 | 89.7178 | COMPLETED | 2025-09-21 | Radha Construction
250 | 64/0 | DC+0 |  | 2025-08-31 | 73.4258 | COMPLETED | 2025-09-22 | Kongres Kumar-2
251 | 52/0 | DC+9 |  | 2025-09-05 | 90.1252 | COMPLETED | 2025-09-22 | Punam Kumari
252 | 47/0 | DC+9 |  | 2025-09-07 | 90.1252 | COMPLETED | 2025-09-22 | Ananya Traders-1
253 | 29/0 | DD60+25 |  | 2025-08-06 | 161.3552 | COMPLETED | 2025-09-22 | Reeta Bharti
254 | 56/8 | DA-3 |  | 2025-08-18 | 42.3742 | COMPLETED | 2025-09-24 | Spotyfy-3
255 | 48/1 | DA-3 |  | 2025-09-15 | 42.3742 | COMPLETED | 2025-09-23 | Ananya trader
256 | 17/6 | DA-3 |  | 2025-09-15 | 42.3742 | COMPLETED | 2025-09-24 | Amit Choudhury
257 | 19/0 | DC+6 |  | 2025-08-31 | 87.0116 | COMPLETED | 2025-09-24 | Sainik Trader
258 | 26/0 | DB+9 |  | 2025-09-15 | 78.6775 | COMPLETED | 2025-09-25 | Gouri Shankar
259 | 17/0 | DB+6 |  | 2025-09-11 | 75.8584 | COMPLETED | 2025-09-28 | Maa Construction
260 | 25/0 | DD60+25 |  | 2025-08-28 | 161.3552 | COMPLETED | 2025-09-29 | Kongres Kumar-1
261 | 64/3 | DA-3 |  | 2025-09-24 | 42.3742 | COMPLETED | 2025-10-07 | Kongres Kumar-1
262 | 54/0 | DB+3 |  | 2025-09-25 | 67.112 | COMPLETED | 2025-10-07 | Punam Kumari
263 | 46/0 | DB+0 |  | 2025-09-25 | 64.4817 | COMPLETED | 2025-10-08 | Amit Choudhury
264 | 63/0 | DC+3 |  | 2025-10-01 | 78.0732 | COMPLETED | 2025-10-12 | Mahon Mahto
265 | 27/0 | DD60+3 |  | 2025-09-22 | 101.692 | COMPLETED | 2025-10-12 | Reeta Bharti
266 | 53A/1 | DA+6 |  | 2025-09-18 | 53.3239 | COMPLETED | 2025-10-13 | Spotyfy
267 | 50/0 | DC+18 |  | 2025-09-25 | 110.6958 | COMPLETED | 2025-10-14 | Punam kumari-1
268 | 53/0 | DC+0 |  | 2025-09-26 | 73.4258 | COMPLETED | 2025-10-14 | Sainik Trader
269 | 42/0 | DD60+18 |  | 2025-09-23 | 143.4621 | COMPLETED | 2025-10-14 | Ananya trader
270 | 54/2 | DA-3 |  | 2025-10-08 | 42.3742 | COMPLETED | 2025-10-22 | Punam kumari-2
271 | 38/0 | DC+18 |  | 2025-10-08 | 110.6958 | COMPLETED | 2025-10-26 | Pankaj Kumar
272 | 0/0 | DCT+0 |  | 2025-10-03 | 97.834 | COMPLETED | 2025-10-28 | Maa Construction
273 | 37/0 | DC+18 |  | 2025-09-23 | 110.6958 | COMPLETED | 2025-10-31 | Pankaj Kumar
274 | 55/0 | DC+0 |  | 2025-10-15 | 73.4258 | COMPLETED | 2025-11-07 | Punam kumari-2
275 | 45/0 | DD60+0 |  | 2025-10-09 | 97.2286 | COMPLETED | 2025-11-07 | Amit Choudhury
276 | 52/1 | DB+6 |  | 2025-10-27 | 75.858 | COMPLETED | 2025-11-10 | Pankaj Kumar
277 | 2/2 | DA+0 |  | 2025-11-01 | 43.776 | COMPLETED | 2025-11-13 | ALORIVA GLOBAL
278 | 61/0 | DD2+30 |  | 2025-09-25 | 188.378 | COMPLETED | 2025-11-14 | Mahon Mahto
279 | 56/6 | DA+0 |  | 2025-11-01 | 43.776 | COMPLETED | 2025-11-15 | Pinky Dewi
280 | 55/1 | DA-3 |  | 2025-11-09 | 42.3742 | COMPLETED | 2025-11-17 | Punam kumari-2
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302

## Stringing compliled
|  |  | Number of TSE | 2 | [12 empty] | RATE/KM
905812
S.no | Sec | From AP | To AP | Span (M) | Method | Section Readiness | P/O Starting Date | P/O Completion Date | P/O | F/S Starting Date | F/S/ Completion Date | Length | Status | Gang Name | Hindrance | Remarks | REVENUE
1 | UP | AP7/0 | AP8/0 | 4818.75 | TSE | Ready | 2025-05-03 | 2025-05-12 | 4818.75 | 2025-05-15 | 2025-05-18 | 4818.75 | Completed | ANARUL ISLAM |  |  | 4364881.575
2 | UP | AP6/0 | AP7/0 | 1234.28 | TSE | Ready | 2025-05-14 | 2025-05-17 | 1234.28 | 2025-05-19 | 2025-05-21 | 1234.28 | Completed | ANARUL ISLAM |  |  | 1118025.6354
3 | UP | AP35/0 | AP36/0 | 3957.05 | TSE | Ready | 2025-05-18 | 2025-05-25 | 3957.05 | 2025-06-27 | 2025-06-30 | 3957.05 | Completed | S K INFRA |  |  | 3584343.3746
4 | UP | AP8/0 | AP8A/0 | 2016.72 | TSE | Ready | 2025-05-24 | 2025-05-29 | 2016.72 | 2025-05-30 | 2025-05-31 | 2016.72 | Completed | ANARUL ISLAM |  |  | 1826769.1766
5 | UP | AP31/0 | AP32/0 | 4283.67 | TSE | Ready | 2025-06-02 | 2025-06-09 | 4283.67 | 2025-06-22 | 2025-06-26 | 4283.67 | Completed | S K INFRA |  |  | 3880199.69
6 | UP | AP8A/0 | AP8B/0 | 223.61 | Manual | Ready | 2025-06-17 | 2025-06-19 | 223.61 | 2025-07-22 | 2025-07-24 | 223.61 | Completed | ANARUL ISLAM |  |  | 202548.6213
7 | UP | AP32/0 | AP33/0 | 407.17 | Manual | Ready | 2025-06-18 | 2025-06-19 | 407.17 | 2025-07-25 | 2025-07-29 | 407.17 | Completed | S K INFRA |  |  | 368819.472
8 | UP | AP8B/0 | AP9/0 | 2226.22 | TSE | Ready | 2025-07-15 | 2025-07-21 | 2226.22 | 2025-07-26 | 2025-07-28 | 2226.22 | Completed | ANARUL ISLAM |  |  | 2016536.7906
9 | UP | AP33/0 | AP34/0 | 4781.5 | TSE | Ready | 2025-07-17 | 2025-07-21 | 4781.5 | 2025-07-25 | 2025-07-29 | 4781.5 | Completed | S K INFRA |  |  | 4331140.078
10 | UP | AP5/0 | AP6/0 | 723.57 | TSE | Ready | 2025-08-05 | 2025-08-08 | 723.57 | 2025-08-26 | 2025-08-27 | 723.57 | Completed | ANARUL ISLAM |  |  | 655418.3888
11 | UP | AP9/0 | AP10/0 | 283.43 | Manual | Ready | 2025-08-11 | 2025-08-11 | 283.43 | 2025-08-11 | 2025-08-12 | 283.43 | Completed | ANARUL ISLAM |  |  | 256734.2952
12 | UP | AP34/0 | AP35/0 | 3193.23 | TSE | Ready | 2025-08-11 | 2025-08-20 | 3193.23 | 2025-08-21 | 2025-08-24 | 3193.23 | Completed | S K INFRA |  |  | 2892466.0528
13 | UP | AP4/0 | AP5/0 | 4415.745 | TSE | Ready | 2025-08-22 | 2025-08-25 | 4415.745 | 2025-08-27 | 2025-08-31 | 4415.745 | Completed | ANARUL ISLAM |  |  | 3999834.8099
14 | UP | AP14/0 | AP15/0 | 3611 | TSE | Ready | 2025-09-05 | 2025-09-10 | 3611 | 2025-09-28 | 2025-09-30 | 3611 | Completed | ANARUL ISLAM |  |  | 3270887.132
15 | UP | AP36/0 | AP37/0 | 4947.31 | TSE | Ready | 2025-09-05 | 2025-09-11 | 4947.31 |  |  |  |  | S K INFRA |  | 37/0 ERECTION WIP | 0
16 | UP | AP3/0 | AP4/0 | 280 | Manual | Ready | 2025-09-15 | 2025-09-15 | 280 | 2025-09-16 | 2025-09-16 | 280 | Completed | ANARUL ISLAM |  |  | 253627.36
17 | UP | AP30/0 | AP31/0 | 2750.46 | TSE | Ready | 2025-09-21 | 2025-09-28 | 2750.46 | 2025-09-30 | 2025-10-03 | 2750.46 | Completed | S K INFRA |  |  | 2491399.6735
18 | UP | AP20/0 | AP21/0 | 4957.98 | TSE | Ready | 2025-09-21 | 2025-09-30 | 4957.98 | 2025-10-01 | 2025-10-06 | 4957.98 | Completed | J PG CON |  |  | 4490997.7798
19 | UP | AP12/0 | AP13/0 | 3919.97 | TSE | Ready | 2025-10-12 | 2025-10-16 | 3919.97 | 2025-10-24 | 2025-10-26 | 3919.97 | Completed | ANARUL ISLAM |  |  | 3550755.8656
20 | UP | AP39/0 | AP40/0 | 4460.53 | TSE | Ready | 2025-10-14 | 2025-10-19 | 4460.53 | 2025-10-23 | 2025-10-26 | 4460.53 | Completed | S K INFRA |  | Gang shift to Chatri Narela line on PGCIL request | 4040401.6004
21 | UP | AP21/0 | AP22/0 | 1606 | TSE | Ready | 2025-10-24 | 2025-10-26 | 1606 | 2025-10-27 | 2025-10-28 | 1606 | Completed | J PG CON |  |  | 1454734.072
22 | UP | AP13/0 | AP14/0 | 319.13 | Manual | Ready | 2025-11-03 | 2025-11-03 | 319.13 | 2025-11-03 | 2025-11-04 | 319.13 | Completed | ANARUL ISLAM |  | INSULATOR HOISTING | 289071.7836
23 | UP | AP38/0 | AP39/0 | 4822.84 | TSE | Ready | 2025-11-02 | 2025-11-10 | 4822.84 | 2025-11-21 |  | 4822.84 | wip | S K INFRA |  | TSE-2
24 | UP | AP19/0 | AP20/0 | 4990.45 | TSE | Ready | 2025-11-06 | 2025-11-13 | 4990.45 | 2025-11-15 | 2025-11-19 | 4990.45 | Completed | J PG CON |  | TSE-1
25 | UP | AP17/0 | AP18/0 | 3456.56 | TSE | Ready | 2025-11-17 | [5 empty] | ROW | ANARUL ISLAM | Row from last 5 days | TSE-2
26 | UP | AP18/0 | AP19/0 | 0.323 | Manual | Ready | 2025-11-21 | 2025-11-24 | 0.323 | 2025-11-24 | 2025-11-25 | 0.323 | Completed | J PG CON
27 | UP | AP15/0 | AP16/0 | 0.46474 | Manual | Ready | 2025-11-22 | 2025-11-25 | 0.46474 |  |  |  | wip | ANARUL ISLAM
28 | UP
29 | UP
30 | UP
31 | UP
32 | UP
33 | UP
34 | UP
35 | UP
36 | UP
37 | UP
38 | UP
39 | UP
40 | UP
41 | UP
42 | UP
43 | UP
44 | UP
45 | UP
46 | UP
47 | UP
48 | UP
49 | UP
50 | UP
51 | UP
52 | UP
53 | UP
54 | UP
55 | UP
56 | UP
57 | UP
58 | UP
59 | UP
60 | UP
61 | UP
62 | UP
63 | UP
64 | UP
65 | UP
66 | UP
67 | UP
68 | UP
69 | UP
70 | UP
71 | UP
72 | UP
73 | UP
74 | UP
75 | UP
76 | UP
77
|  |  | Total | 72.688 |  |  |  |  | 69.2314 |  |  | 64.2836

## Progress.
Supply Status
Activity | Unit | Final Est. Qty | L2 till Last Month | Received till Last Month | Balance as per L2 | L2 Plan for Current Month | Plan for Current Month | Progress for the Month | Received till Current Month | Gap between Suppy & Cumm.L2 | Remarks
Stub | No's | 302 | 302 | 302 | 0 | 0 | 0 | 0 | 302 | 0
Tower | No's | 302 | 302 | 302 | 0 | 0 | 0 | 0 | 302 | 0
Survey Status
Activity | Unit | Final Est. Qty | L2 till Last Month | Completed till Last Month | Approved till Last Month | Balance to Submit | Approved in current month | Balance to Approve | L2 Submission Plan for Current Month | Survey Progress For current Month | Survey Completed till Current Month | Remarks
Detailed Survey | kms | 115.134 | 115.134 | 115.134 | 115.134 | 0 | 0 | 0 | 0 | 0 | 115.134
Check Survey | kms | 115.134 | 115.134 | 115.134 | 115.134 | 0 | 0 | 0 | 0 | 0 | 115.134
S.No | Location No. | Tower Type | Classification | Start Date | Conc Volume | Status |  |  |  | End Date | Gang Name | Gang Strength | Remark
1 | 2/8 | DA+0 | Wet Paddy | 2024-04-24 | 37.64 | Completed |  |  |  | 2024-05-06 | Sumit Constrcution
2 | 2/7 | DA+3 | Wet Paddy | 2024-05-01 | 41.37 | Completed |  |  |  | 2024-05-10 | Sumit Constrcution
3 | 2/6 | DA+0 | Wet Paddy | 2024-05-09 | 37.64 | Completed |  |  |  | 2024-05-14 | Sumit Constrcution
4 | 2/5 | DA+3 | Wet Paddy | 2024-05-13 | 41.37 | Completed |  |  |  | 2024-05-18 | Sumit Constrcution
5 | 2/4 | DA+0 | Wet Paddy | 2024-05-16 | 37.64 | Completed |  |  |  | 2024-05-21 | Sumit Constrcution
6 | 2/3 | DA+3 | Wet Paddy | 2024-05-22 | 41.37 | Completed |  |  |  | 2024-05-28 | Sumit Constrcution
7 | 39/10 | DA+0 | Wet Paddy | 2024-05-28 | 37.64 | Completed |  |  |  | 2024-06-04 | Dharamdas Contractor
8 | 17/4 | DA+3 | Wet Paddy | 2024-05-31 | 41.37 | Completed |  |  |  | 2024-06-03 | Sumit Constrcution
9 | 17/5 | DA+3 | Wet Paddy | 2024-05-31 | 41.37 | Completed |  |  |  | 2024-06-06 | Sumit Constrcution
10 | 17/3 | DA+0 | Wet Paddy | 2024-06-04 | 37.64 | Completed |  |  |  | 2024-06-09 | Sumit Constrcution
11 | 39/8 | DA+0 | Wet Paddy | 2024-06-04 | 37.64 | Completed |  |  |  | 2024-06-08 | Dharamdas Contractor
12 | 6/2 | DA+3 | Sandy | 2024-06-06 | 49.03 | Completed |  |  |  | 2024-06-12 | Khalil Const.
13 | 17/6 | DA-3 | Wet Paddy | 2024-06-07 | 37.64 | Completed |  |  |  | 2024-06-11 | Sumit Constrcution
14 | 39/9 | DA+3 | Wet Paddy | 2024-06-08 | 41.37 | Completed |  |  |  | 2024-06-13 | Dharamdas Contractor
15 | 17/7 | DA+3 | Wet Paddy | 2024-06-10 | 41.37 | Completed |  |  |  | 2024-06-14 | Sumit Constrcution
16 | 39/7 | DA+3 | Wet Paddy | 2024-06-12 | 41.37 | Completed |  |  |  | 2024-06-19 | Dharamdas Contractor
17 | 39/1 | DA+3 | Wet Paddy | 2024-06-13 | 41.37 | Completed |  |  |  | 2024-06-23 | Anshika con.
18 | 20/6 | DA+0 | Wet Paddy | 2024-06-13 | 37.64 | Completed |  |  |  | 2024-06-22 | Khalil Const.
19 | 17/8 | DA-3 | Wet Paddy | 2024-06-13 | 37.64 | Completed |  |  |  | 2024-06-17 | Sumit Constrcution
20 | 17/1 | DA-3 | Wet Paddy | 2024-06-13 | 37.64 | Completed |  |  |  | 2024-06-20 | Sumit Constrcution
21 | 39/6 | DA+3 | Wet Paddy | 2024-06-20 | 41.37 | Completed |  |  |  | 2024-06-25 | Dharamdas Contractor
22 | 20/7 | DA-3 | Wet Paddy | 2024-06-21 | 37.64 | Completed |  |  |  | 2024-06-27 | Khalil Const.
23 | 38/11 | DA+3 | Sandy | 2024-06-22 | 49.03 | Completed |  |  |  | 2024-06-30 | Anshika con.
24 | 38/1 | DA+3 | Sandy | 2024-07-01 | 49.03 | Completed |  |  |  | 2024-07-11 | Anshika con.
25 | 20/12 | DA-3 | Wet Paddy | 2024-07-08 | 37.64 | Completed |  |  |  | 2024-07-15 | Jay Sri Ram
26 | 38/2 | DA+3 | Sandy | 2024-07-11 | 49.03 | Completed |  |  |  | 2024-07-18 | Anshika con.
27 | 19/11 | DA-3 | Wet Paddy | 2024-07-12 | 37.64 | Completed |  |  |  | 2024-07-23 | K R Associates
28 | 14/5 | DA+3 | Wet Paddy | 2024-07-13 | 41.37 | Completed |  |  |  | 2024-07-20 | SSR engineering
29 | 38/3 | DA+3 | Sandy | 2024-07-15 | 49.03 | Completed |  |  |  | 2024-07-25 | Anshika con.
30 | 38/4 | DA+3 | WET | 2024-07-20 | 61.06 | Completed |  |  |  | 2024-07-31 | Anshika con.
31 | 19/8 | DA-3 | Wet Paddy | 2024-07-20 | 37.64 | Completed |  |  |  | 2024-07-30 | Jay Sri Ram
32 | 20/8 | DA+0 | Wet Paddy | 2024-07-20 | 37.64 | Completed |  |  |  | 2024-07-29 | VH Rajpoot cont.
33 | 14/6 | DA+3 | Wet Paddy | 2024-07-22 | 41.37 | Completed |  |  |  | 2024-07-28 | SSR engineering
34 | 19/9 | DA+3 | Wet Paddy | 2024-07-28 | 41.37 | Completed |  |  |  | 2024-08-04 | K R Associates
35 | 14/4 | DA+3 | Wet Paddy | 2024-07-28 | 41.37 | Completed |  |  |  | 2024-08-09 | SSR engineering
36 | 20/9 | DA+3 | Wet Paddy | 2024-07-30 | 41.37 | Completed |  |  |  | 2024-08-03 | VH Rajpoot cont.
37 | 36/12 | DA+0 | Sandy | 2025-08-01 | 46.16 | Completed |  |  |  | 2024-08-08 | Anshika con.
38 | 20/5 | DA+3 | Wet Paddy | 2024-08-05 | 41.37 | Completed |  |  |  | 2024-08-10 | VH Rajpoot cont.
39 | 36/11 | DA-3 | Wet Paddy | 2024-08-08 | 37.64 | Completed |  |  |  | 2024-08-14 | Anshika con.
40 | 14/3 | DA+0 | Wet Paddy | 2024-08-10 | 37.64 | Completed |  |  |  | 2024-08-21 | SSR engineering
41 | 23/3 | DA-3 | Wet Paddy | 2024-08-12 | 37.64 | Completed |  |  |  | 2024-08-18 | VH Rajpoot cont.
42 | 19/12 | DA-3 | Wet Paddy | 2024-08-12 | 37.64 | Completed |  |  |  | 2024-08-24 | K R Associates
43 | 12/9 | DA+3 | Wet Paddy | 2024-08-16 | 41.37 | Completed |  |  |  | 2024-08-31 | VED ENTTERPRISE
44 | 23/4 | DA-3 | Wet Paddy | 2024-08-23 | 37.64 | Completed |  |  |  | 2024-08-31 | VH Rajpoot cont.
45 | 36/3 | DA+3 | Wet Paddy | 2024-08-23 | 41.37 | Completed |  |  |  | 2024-08-31 | J M Enterprise
46 | 14/7 | DA+0 | Wet Paddy | 2024-08-24 | 37.64 | Completed |  |  |  | 2024-08-30 | SSR engineering
47 | 36/7 | DA+3 | Wet Paddy | 2024-08-24 | 41.37 | Completed |  |  |  | 2024-09-09 | SAIFI CON.
48 | 38/8 | DA+3 | WET | 2024-08-24 | 61.06 | Completed |  |  |  | 2024-09-08 | A V I ENTERPRISE
49 | 19/1 | DA+0 | Wet Paddy | 2024-08-24 | 37.64 | Completed |  |  |  | 2024-09-30 | MALLIK CON
50 | 19/3 | DA+3 | Wet Paddy | 2024-08-24 | 41.37 | Completed |  |  |  | 2024-09-05 | Garg Construction
51 | 19/2 | DA+0 | Wet Paddy | 2024-08-24 | 37.64 | Completed |  |  |  | 2024-09-22 | Shree Krishna
52 | 36/6 | DA+3 | Wet Paddy | 2024-08-24 | 41.37 | Completed |  |  |  | 2024-09-20 | SAIFI CON.
53 | 45/3 | DA-3 | WET | 2024-08-24 | 58.51 | Completed |  |  |  | 2024-09-08 | Vinayak Enterprise
54 | 50/1 | DA+0 | Wet Paddy | 2024-08-24 | 37.64 | Completed |  |  |  | 2024-09-11 | Vishal construction
55 | 39/4 | DA+3 | WET | 2024-08-29 | 61.06 | Completed |  |  |  | 2024-09-08 | Dharamdas Contractor
56 | 20/1 | DA+6 | Wet Paddy | 2024-08-30 | 41.37 | Completed |  |  |  | 2024-09-22 | K R Associates
57 | 12/8 | DA-3 | Wet Paddy | 2024-09-01 | 37.64 | Completed |  |  |  | 2024-09-09 | VED ENTTERPRISE
58 | 12/4 | DA+3 | Wet Paddy | 2024-09-01 | 41.37 | Completed |  |  |  | 2024-09-08 | SSR engineering
59 | 12/2 | DA+3 | Wet Paddy | 2024-09-08 | 41.37 | Completed |  |  |  | 2024-09-24 | SSR engineering
60 | 23/5 | DA-3 | Wet Paddy | 2024-09-08 | 37.64 | Completed |  |  |  | 2024-09-11 | VH Rajpoot cont.
61 | 30/3 | DA+0 | Wet Paddy | 2024-09-08 | 37.64 | Completed |  |  |  | 2024-09-22 | Garg Construction
62 | 41/1 | DA+0 | Wet Paddy | 2024-09-09 | 37.64 | Completed |  |  |  | 2024-09-20 | Dharamdas Contractor
63 | 36/10 | DA-3 | Wet Paddy | 2024-09-09 | 37.64 | Completed |  |  |  | 2024-09-30 | J M Enterprise
64 | 45/2 | DA+3 | Wet Paddy | 2024-09-09 | 41.37 | Completed |  |  |  | 2024-09-29 | Vinayak Enterprise
65 | 23/2 | DA+0 | Wet Paddy | 2024-09-11 | 37.64 | Completed |  |  |  | 2024-09-20 | VH Rajpoot cont.
66 | 30/6 | DA-3 | Wet Paddy | 2024-09-19 | 37.64 | Completed |  |  |  | 2024-09-24 | Laxmi Const.
67 | 35/2 | DA-3 | Wet Paddy | 2024-09-19 | 37.64 | Completed |  |  |  | 2024-09-26 | A V I ENTERPRISE
68 | 41/2 | DA+3 | Wet Paddy | 2024-09-19 | 41.37 | Completed |  |  |  | 2024-09-26 | Dharamdas Contractor
69 | 36/9 | DA-3 | Wet Paddy | 2024-09-19 | 37.64 | Completed |  |  |  | 2024-09-24 | SAIFI CON.
70 | 36/5 | DA+0 | Wet Paddy | 2024-09-20 | 37.64 | Completed |  |  |  | 2024-09-26 | J M Enterprise
71 | 25/1 | DA+9 | Wet Paddy | 2024-09-22 | 41.37 | Completed |  |  |  | 2024-09-26 | VH Rajpoot cont.
72 | 30/4 | DA+3 | Wet Paddy | 2024-09-22 | 41.37 | Completed |  |  |  | 2024-09-30 | Garg Construction
73 | 12/6 | DA-3 | Wet Paddy | 2024-09-23 | 37.64 | Completed |  |  |  | 2024-09-30 | VED ENTTERPRISE
74 | 12/1 | DA-3 | Wet Paddy | 2024-09-25 | 37.64 | Completed |  |  |  | 2024-09-30 | SSR engineering
75 | 23/1 | DA+9 | Wet Paddy | 2024-09-26 | 41.37 | Completed |  |  |  | 2024-09-30 | VH Rajpoot cont.
76 | 12/7 | DA-3 | Wet Paddy | 2024-09-27 | 37.64 | Completed |  |  |  | 2024-10-06 | VED ENTTERPRISE
77 | 46/1 | DA+0 | Wet Paddy | 2024-09-09 | 37.64 | Completed |  |  |  | 2024-10-10 | Vinayak Enterprise
78 | 35/1 | DA+3 | Wet Paddy | 2024-09-20 | 41.37 | Completed |  |  |  | 2024-10-01 | Maa Durga
79 | 46/2 | DA+3 | Wet Paddy | 2024-09-25 | 41.37 | Completed |  |  |  | 2024-10-03 | Vishal construction
80 | 36/8 | DA-3 | Wet Paddy | 2024-09-26 | 37.64 | Completed |  |  |  | 2024-10-06 | SAIFI CON.
81 | 34/7 | DA+3 | Wet Paddy | 2024-09-26 | 41.37 | Completed |  |  |  | 2024-10-03 | Aneshwar Traders
82 | 35/3 | DA+0 | Wet Paddy | 2024-09-27 | 37.64 | Completed |  |  |  | 2024-10-01 | A V I ENTERPRISE
83 | 25/2 | DA+0 | Wet Paddy | 2024-10-01 | 37.64 | Completed |  |  |  | 2024-10-04 | VH Rajpoot cont.
84 | 12/3 | DA+3 | Wet Paddy | 2024-10-01 | 41.37 | Completed |  |  |  | 2024-10-07 | SSR engineering
85 | 30/2 | DA-3 | Wet Paddy | 2024-10-01 | 37.64 | Completed |  |  |  | 2024-10-07 | Garg Construction
86 | 31/2 | DA+0 | Wet Paddy | 2024-10-03 | 37.64 | Completed |  |  |  | 2024-10-07 | Laxmi Const.
87 | 25/3 | DA+3 | Wet Paddy | 2024-10-04 | 41.37 | Completed |  |  |  | 2024-10-08 | VH Rajpoot cont.
88 | 35/9 | DA+3 | Wet Paddy | 2024-10-04 | 41.37 | Completed |  |  |  | 2024-10-10 | A V I ENTERPRISE
89 | 39/5 | DA-3 | Wet Paddy | 2024-10-04 | 37.64 | Completed |  |  |  | 2024-10-08 | Dharamdas Contractor
90 | 34/6 | DA+0 | Wet Paddy | 2024-10-04 | 37.64 | Completed |  |  |  | 2024-10-08 | Aneshwar Traders
91 | 34/3 | DA+3 | Wet Paddy | 2024-10-04 | 41.37 | Completed |  |  |  | 2024-10-10 | Maa Durga
92 | 34/4 | DA-3 | Wet Paddy | 2024-10-04 | 37.64 | Completed |  |  |  | 2024-10-10 | M A Construction
93 | 31/1 | DA+0 | Wet Paddy | 2024-10-08 | 37.64 | Completed |  |  |  | 2024-10-10 | Laxmi Const.
94 | 34/2 | DA+3 | Wet Paddy | 2024-10-08 | 41.37 | Completed |  |  |  | 2024-10-13 | Aneshwar Traders
95 | 12/5 | DA+3 | Wet Paddy | 2024-10-10 | 41.37 | Completed |  |  |  | 2024-10-13 | SSR engineering
96 | 4/2 | DA-3 | Wet Paddy | 2024-10-10 | 37.64 | Completed |  |  |  | 2024-10-14 | VED ENTTERPRISE
97 | 31/8 | DA-3 | Wet Paddy | 2024-10-10 | 37.64 | Completed |  |  |  | 2024-10-14 | VH Rajpoot cont.
98 | 30/1 | DA-3 | Wet Paddy | 2024-10-10 | 37.64 | Completed |  |  |  | 2024-10-14 | Garg Construction
99 | 30/5 | DA+0 | Wet Paddy | 2024-10-10 | 37.64 | Completed |  |  |  | 2024-10-16 | Laxmi Const.
100 | 20/2 | DA+0 | Wet Paddy | 2024-10-12 | 37.64 | Completed |  |  |  | 2024-10-21 | K R Associates
101 | 36/2 | DA+0 | Wet Paddy | 2024-10-12 | 37.64 | Completed |  |  |  | 2024-10-16 | SAIFI CON.
102 | 35/8 | DA-3 | Wet Paddy | 2024-10-12 | 37.64 | Completed |  |  |  | 2024-10-21 | A V I ENTERPRISE
103 | 52/9 | DA-3 | WET | 2024-10-13 | 58.51 | Completed |  |  |  | 2024-10-22 | Dharamdas Contractor
104 | 14/2 | DA+0 | Wet Paddy | 2024-10-13 | 37.64 | Completed |  |  |  | 2024-10-20 | SSR engineering
105 | 33/11 | DA+3 | Wet Paddy | 2024-10-13 | 41.37 | Completed |  |  |  | 2024-10-18 | Aneshwar Traders
106 | 33/1 | DA-3 | Wet Paddy | 2024-10-13 | 37.64 | Completed |  |  |  | 2024-10-16 | M A Construction
107 | 34/1 | DA+3 | Wet Paddy | 2024-10-13 | 41.37 | Completed |  |  |  | 2024-10-21 | Maa Durga
108 | 31/10 | DA-3 | Wet Paddy | 2024-10-13 | 37.64 | Completed |  |  |  | 2024-10-18 | VH Rajpoot cont.
109 | 31/3 | DA+3 | Wet Paddy | 2024-10-16 | 41.37 | Completed |  |  |  | 2024-10-20 | Laxmi Const.
110 | 33/2 | DA-3 | Wet Paddy | 2024-10-16 | 37.64 | Completed |  |  |  | 2024-10-20 | M A Construction
111 | 4/3 | DA+3 | Wet Paddy | 2024-10-17 | 41.37 | Completed |  |  |  | 2024-10-23 | VED ENTTERPRISE
112 | 8B/3 | DA+3 | Wet Paddy | 2024-10-17 | 41.37 | Completed |  |  |  | 2024-10-26 | Garg Construction
113 | 28/1 | DA+3 | Wet Paddy | 2024-10-17 | 41.37 | Completed |  |  |  | 2024-10-24 | J M Enterprise
114 | 31/9 | DA+3 | Wet Paddy | 2024-10-17 | 41.37 | Completed |  |  |  | 2024-10-24 | VH Rajpoot cont.
115 | 33/5 | DA+3 | Wet Paddy | 2024-10-17 | 41.37 | Completed |  |  |  | 2024-10-24 | Vinayak Enterprise
116 | 33/10 | DA+3 | Wet Paddy | 2024-10-17 | 41.37 | Completed |  |  |  | 2024-10-23 | Aneshwar Traders
117 | 36/1 | DA+3 | Wet Paddy | 2024-10-17 | 41.37 | Completed |  |  |  | 2024-10-24 | SAIFI CON.
118 | 7/10 | DA+3 | Wet Paddy | 2024-10-19 | 41.37 | Completed |  |  |  | 2024-10-25 | Vivan Enterprise
119 | 14/1 | DA+0 | Wet Paddy | 2024-10-21 | 37.64 | Completed |  |  |  | 2024-10-24 | SSR engineering
120 | 31/5 | DA-3 | Wet Paddy | 2024-10-22 | 37.64 | Completed |  |  |  | 2024-10-25 | Laxmi Const.
121 | 33/3 | DA+3 | Wet Paddy | 2024-10-22 | 41.37 | Completed |  |  |  | 2024-10-26 | M A Construction
122 | 33/9 | DA+0 | Wet Paddy | 2024-10-24 | 37.64 | Completed |  |  |  | 2024-10-26 | Aneshwar Traders
123 | 35/7 | DA+3 | Wet Paddy | 2024-10-24 | 41.37 | Completed |  |  |  | 2024-10-26 | A V I ENTERPRISE
124 | 4/4 | DA+0 | Wet Paddy | 2024-10-24 | 37.64 | Completed |  |  |  | 2024-10-27 | VED ENTTERPRISE
125 | 7/11 | DA+0 | Wet Paddy | 2024-10-24 | 37.64 | Completed |  |  |  | 2024-10-27 | Vivan Enterprise
126 | 14/8 | DA+3 | Wet Paddy | 2024-10-24 | 41.37 | Completed |  |  |  | 2024-11-01 | SSR engineering
127 | 31/6 | DA+3 | Wet Paddy | 2024-10-24 | 41.37 | Completed |  |  |  | 2024-11-01 | Laxmi Const.
128 | 31/7 | DA+0 | Wet Paddy | 2024-10-24 | 37.64 | Completed |  |  |  | 2024-11-01 | VH Rajpoot cont.
129 | 52/10 | DA+3 | WET | 2024-10-24 | 61.06 | Completed |  |  |  | 2024-11-01 | Dharamdas Contractor
130 | 20/4 | DA-3 | Wet Paddy | 2024-10-24 | 37.64 | Completed |  |  |  | 2024-11-01 | K R Associates
131 | 35/4 | DA+0 | Wet Paddy | 2024-10-25 | 37.64 | Completed |  |  |  | 2024-11-10 | Maa Durga
132 | 33/4 | DA-3 | Wet Paddy | 2024-10-25 | 37.64 | Completed |  |  |  | 2024-11-02 | M A Construction
133 | 35/5 | DA+3 | Wet Paddy | 2024-10-25 | 41.37 | Completed |  |  |  | 2024-11-02 | A V I ENTERPRISE
134 | 8B/1 | DA-3 | Wet Paddy | 2024-11-03 | 37.64 | Completed |  |  |  | 2024-11-05 | Garg Construction
135 | 20/0 | DB1+0 | Wet Paddy | 2024-11-03 | 58.25 | Completed |  |  |  | 2024-11-13 | J M Enterprise
136 | 7/9 | DA+0 | Wet Paddy | 2024-11-03 | 37.64 | Completed |  |  |  | 2024-11-11 | Vivan Enterprise
137 | 20/3 | DA+0 | Wet Paddy | 2024-11-03 | 37.64 | Completed |  |  |  | 2024-11-13 | K R Associates
138 | 31/4 | DA-3 | Wet Paddy | 2024-11-03 | 37.64 | Completed |  |  |  | 2024-11-09 | Laxmi Const.
139 | 8B/2 | DA-3 | Wet Paddy | 2024-11-03 | 37.64 | Completed |  |  |  | 2024-11-13 | Garg Construction
140 | 33/8 | DA+3 | Wet Paddy | 2024-11-03 | 41.37 | Completed |  |  |  | 2024-11-11 | Aneshwar Traders
141 | 33/6 | DA+3 | Wet Paddy | 2024-11-03 | 41.37 | Completed |  |  |  | 2024-11-08 | Vinayak Enterprise
142 | 34/0 | DB1+0 | Wet Paddy | 2024-11-03 | 58.25 | Completed |  |  |  | 2024-11-09 | M A Construction
143 | 19/7 | DA+3 | Wet Paddy | 2024-11-06 | 41.37 | Completed |  |  |  | 2024-11-13 | VH Rajpoot cont.
144 | 17/2 | DA+0 | Wet Paddy | 2024-11-06 | 37.64 | Completed |  |  |  | 2024-11-10 | SSR engineering
145 | 19/4 | DA+0 | Wet Paddy | 2024-11-06 | 37.64 | Completed |  |  |  | 2024-11-11 | VH Rajpoot cont.
146 | 7/8 | DA+3 | Wet Paddy | 2024-11-06 | 41.37 | Completed |  |  |  | 2024-11-15 | Vivan Enterprise
147 | 33/7 | DA+3 | Wet Paddy | 2024-11-06 | 41.37 | Completed |  |  |  | 2024-11-15 | Aneshwar Traders
148 | 32/0 | DC1+6 | Wet Paddy | 2024-11-08 | 71.04 | Completed |  |  |  | 2024-11-16 | Laxmi Const.
149 | 10/1 | DA-3 | Wet Paddy | 2024-11-09 | 37.64 | Completed |  |  |  | 2024-11-18 | SSR engineering
150 | 19/5 | DA-3 | Wet Paddy | 2024-11-10 | 37.64 | Completed |  |  |  | 2024-11-18 | VH Rajpoot cont.
151 | 39/3 | DA+3 | PS | 2024-11-12 | 71.43 | Completed |  |  |  | 2024-11-20 | M A Construction
152 | 8B/4 | DA+6 | Wet Paddy | 2024-11-14 | 41.37 | Completed |  |  |  | 2024-11-21 | Garg Construction
153 | 4/8 | DA+0 | Wet Paddy | 2024-11-14 | 37.64 | Completed |  |  |  | 2024-11-21 | R K Constrcution
154 | 33/0 | DC2+6 | Wet Paddy | 2024-11-14 | 77.81 | Completed |  |  |  | 2024-11-21 | Aneshwar Traders
155 | 19/6 | DA+0 | Wet Paddy | 2024-11-18 | 37.64 | Completed |  |  |  | 2024-11-21 | VH Rajpoot cont.
156 | 36/4 | DA+0 | Wet Paddy | 2024-11-18 | 37.64 | Completed |  |  |  | 2024-11-21 | Maa Durga
157 | 54/1 | DA+9 | PS | 2024-11-16 | 71.43 | Completed |  |  |  | 2024-11-23 | Dharamdas Contractor
158 | 21/0 | DB1+0 | Wet Paddy | 2024-11-18 | 58.25 | Completed |  |  |  | 2024-11-22 | J M Enterprise
159 | 8/3 | DA-3 | Wet Paddy | 2024-11-18 | 37.64 | Completed |  |  |  | 2024-11-22 | A V I ENTERPRISE
160 | 20/11 | DA-3 | Wet Paddy | 2024-11-18 | 37.64 | Completed |  |  |  | 2024-11-24 | K R Associates
161 | 38/6 | DA+3 | PS | 2024-11-20 | 71.43 | Completed |  |  |  | 2024-11-29 | Vinayak Enterprise
162 | 39/2 | DA-3 | Wet Paddy | 2024-11-22 | 37.64 | Completed |  |  |  | 2024-11-26 | M A Construction
163 | 35/0 | DC1+0 | Wet Paddy | 2024-11-22 | 70.25 | Completed |  |  |  | 2024-11-29 | Aneshwar Traders
164 | 36/0 | DB2+0 | Wet Paddy | 2024-11-22 | 65.714 | Completed |  |  |  | 2024-11-27 | SAIFI CON.
165 | 8/4 | DA+9 | Wet Paddy | 2024-11-22 | 41.37 | Completed |  |  |  | 2024-11-27 | A V I ENTERPRISE
166 | 4/7 | DA+3 | Wet Paddy | 2024-11-22 | 41.37 | Completed |  |  |  | 2024-11-29 | R K Constrcution
167 | 8B/5 | DA+6 | Wet Paddy | 2024-11-22 | 41.37 | Completed |  |  |  | 2024-11-29 | Garg Construction
168 | 7/3 | DA-3 | Wet Paddy | 2024-11-22 | 37.64 | Completed |  |  |  | 2024-11-26 | Laxmi Const.
169 | 7/2 | DA+3 | Wet Paddy | 2024-11-22 | 41.37 | Completed |  |  |  | 2024-11-29 | Laxmi Const.
170 | 10/0 | DB1+9 | Wet Paddy | 2024-11-22 | 58.25 | Completed |  |  |  | 2024-11-30 | SSR engineering
171 | 31/0 | DB2+0 | Wet Paddy | 2024-11-22 | 65.714 | Completed |  |  |  | 2024-11-29 | VH Rajpoot cont.
172 | 54/2 | DA-3 | PS | 2024-11-20 | 68.85 | Completed |  |  |  | 2024-12-01 | Dharamdas Contractor
173 | 39/0 | DB2+0 | Wet Paddy | 2024-11-22 | 65.714 | Completed |  |  |  | 2024-12-02 | M A Construction
174 | 8/2 | DA+0 | Wet Paddy | 2024-11-25 | 37.64 | Completed |  |  |  | 2024-12-03 | A V I ENTERPRISE
175 | 26/0 | DB2+9 | Wet Paddy | 2024-11-29 | 65.912 | Completed |  |  |  | 2024-12-04 | VH Rajpoot cont.
176 | 7/1 | DA+0 | Wet Paddy | 2024-11-30 | 37.64 | Completed |  |  |  | 2024-12-04 | Laxmi Const.
177 | 4/5 | DA+3 | Wet Paddy | 2024-11-30 | 41.37 | Completed |  |  |  | 2024-12-06 | R K Constrcution
178 | 5/1 | DA+3 | Wet Paddy | 2024-12-03 | 41.37 | Completed |  |  |  | 2024-12-09 | J M Enterprise
179 | 7/4 | DA+0 | Wet Paddy | 2024-12-03 | 37.64 | Completed |  |  |  | 2024-12-09 | Laxmi Const.
180 | 7/7 | DA+0 | Wet Paddy | 2024-12-03 | 37.64 | Completed |  |  |  | 2024-12-09 | Garg Construction
181 | 8/1 | DA+3 | Wet Paddy | 2024-12-03 | 41.37 | Completed |  |  |  | 2024-12-09 | A V I ENTERPRISE
182 | 17/0 | DB2+6 | Wet Paddy | 2024-12-03 | 65.912 | Completed |  |  |  | 2024-12-09 | SSR engineering
183 | 3/0 | DC2+0 | Wet Paddy | 2024-12-04 | 77.07 | Completed |  |  |  | 2024-12-10 | VH Rajpoot cont.
184 | 56/5 | DA-3 | WET | 2024-12-04 | 58.51 | Completed |  |  |  | 2024-12-10 | Aneshwar Traders
185 | 38/10 | DA-3 | WET | 2024-12-01 | 58.51 | Completed |  |  |  | 2024-12-11 | Maa Durga
186 | 55/1 | DA-3 | WET | 2024-12-02 | 58.51 | Completed |  |  |  | 2024-12-11 | Dharamdas Contractor
187 | 7/5 | DA+3 | Wet Paddy | 2024-12-09 | 41.37 | Completed |  |  |  | 2024-12-13 | Laxmi Const.
188 | 49/0 | DC2+9 | WET | 2024-12-09 | 113.26 | Completed |  |  |  | 2024-12-15 | M A Construction
189 | 4/9 | DA-3 | Wet Paddy | 2024-12-09 | 37.64 | Completed |  |  |  | 2024-12-16 | R K Constrcution
190 | 7/6 | DA+0 | Wet Paddy | 2024-12-09 | 37.64 | Completed |  |  |  | 2024-12-16 | Garg Construction
191 | 6/1 | DA+3 | Wet Paddy | 2024-12-09 | 41.37 | Completed |  |  |  | 2024-12-16 | J M Enterprise
192 | 4/0 | DD45+0 | Wet Paddy | 2024-12-09 | 94.55 | Completed |  |  |  | 2024-12-17 | VH Rajpoot cont.
193 | 56/8 | DA-3 | PS | 2024-12-09 | 68.85 | Completed |  |  |  | 2024-12-17 | Aneshwar Traders
194 | 38/7 | DA-3 | PS | 2024-12-09 | 68.85 | Completed |  |  |  | 2024-12-17 | Vinayak Enterprise
195 | 52/7 | DA+6 | PS | 2024-12-09 | 71.43 | Completed |  |  |  | 2024-12-18 | SAIFI CON.
196 | 7/0 | DB2+0 | Wet Paddy | 2024-12-10 | 65.714 | Completed |  |  |  | 2024-12-20 | Laxmi Const.
197 | 8/0 | DB2+0 | Wet Paddy | 2024-12-10 | 65.714 | Completed |  |  |  | 2024-12-20 | A V I ENTERPRISE
198 | 48/1 | DA-3 | Wet Paddy | 2024-12-15 | 37.64 | Completed |  |  |  | 2024-12-20 | M A Construction
199 | 47/0 | DC2+9 | Wet Paddy | 2024-12-10 | 77.81 | Completed |  |  |  | 2024-12-21 | Maa Durga
200 | 56/1 | DA+0 | WET | 2024-12-10 | 58.51 | Completed |  |  |  | 2024-12-22 | Dharamdas Contractor
201 | 9/0 | DB2+6 | Wet Paddy | 2024-12-10 | 65.912 | Completed |  |  |  | 2024-12-24 | VH Rajpoot cont.
202 | 4/10 | DA+3 | Wet Paddy | 2024-12-17 | 41.37 | Completed |  |  |  | 2024-12-24 | R K Constrcution
203 | 52/8 | DA-3 | Wet Paddy | 2024-12-19 | 37.64 | Completed |  |  |  | 2024-12-27 | SAIFI CON.
204 | 6/0 | DB1+0 | Wet Paddy | 2024-12-20 | 58.25 | Completed |  |  |  | 2024-12-27 | J M Enterprise
205 | 56/7 | DA+6 | PS | 2024-11-20 | 71.43 | Completed |  |  |  | 2024-12-27 | Aneshwar Traders
206 | 46/0 | DB2+0 | Wet Paddy | 2024-12-18 | 65.714 | Completed |  |  |  | 2024-12-28 | Vinayak Enterprise
207 | 4/6 | DA+0 | Wet Paddy | 2024-12-23 | 37.64 | Completed |  |  |  | 2024-12-31 | R K Constrcution
208 | 54/0 | DB1+3 | WET | 2024-12-23 | 82.51 | Completed |  |  |  | 2024-12-31 | Dharamdas Contractor
209 | 53A/5 | DA-3 | WET | 2024-11-24 | 58.51 | Completed |  |  |  | 2025-01-02 | A K Rajpoot
210 | 64/1 | DA+0 | WET | 2024-11-24 | 58.51 | Completed |  |  |  | 2025-01-02 | M A Construction
211 | 15/0 | DC2+3 | Wet Paddy | 2024-12-17 | 77.81 | Completed |  |  |  | 2025-01-03 | SSR engineering
212 | 38/9 | DA-3 | WET | 2024-11-24 | 58.51 | Completed |  |  |  | 2025-01-03 | Maa Durga
213 | 8A/0 | DD60+0 | Wet Paddy | 2024-11-20 | 169.71 | Completed |  |  |  | 2025-01-09 | Garg Construction
214 | 5/0 | DB1+0 | Wet Paddy | 2024-12-29 | 58.25 | Completed |  |  |  | 2025-01-09 | J M Enterprise
215 | 53A/0 | DB2+0 | WET | 2025-01-03 | 95.47 | Completed |  |  |  | 2025-01-10 | Laxmi Const.
216 | 53A/4 | DA+3 | WET | 2025-01-03 | 61.06 | Completed |  |  |  | 2025-01-11 | A K Rajpoot
217 | 56/0 | DD45+0 | WET | 2025-01-03 | 139.03 | Completed |  |  |  | 2025-01-11 | Aneshwar Traders
218 | 64/2 | DA+3 | PS | 2025-01-03 | 71.43 | Completed |  |  |  | 2025-01-11 | M A Construction
219 | 52/0 | DC2+9 | Wet Paddy | 2025-01-03 | 77.81 | Completed |  |  |  | 2025-01-11 | Vinayak Enterprise
220 | 48/0 | DD45+9 | Wet Paddy | 2025-01-04 | 94.55 | Completed |  |  |  | 2025-01-12 | Maa Durga
221 | 28/0 | DD60+0 | FS | 2024-12-28 | 326.62 | Completed |  |  |  | 2025-01-12 | VH Rajpoot cont.
222 | 8B/0 | DD60+0 | Wet Paddy | 2024-12-26 | 169.71 | Completed |  |  |  | 2025-01-14 | A V I ENTERPRISE
223 | 19/10 | DA+3 | Wet Paddy | 2025-01-10 | 41.37 | Completed |  |  |  | 2025-01-14 | SSR engineering
224 | 53/0 | DC1+0 | WET | 2025-01-03 | 98.56 | Completed |  |  |  | 2025-01-15 | SAIFI CON.
225 | 53A/2 | DA+3 | WET | 2025-01-10 | 61.06 | Completed |  |  |  | 2025-01-18 | Laxmi Const.
226 | 52/3 | DA-3 | Wet Paddy | 2025-01-12 | 37.64 | Completed |  |  |  | 2025-01-20 | Vinayak Enterprise
227 | 20/10 | DA+3 | Wet Paddy | 2025-01-10 | 41.37 | Completed |  |  |  | 2025-01-20 | Garg Construction
228 | 55/0 | DC1+0 | PS | 2025-01-04 | 111.17 | Completed |  |  |  | 2025-01-22 | Dharamdas Contractor
229 | 53A/6 | DA+3 | WET | 2025-01-12 | 61.06 | Completed |  |  |  | 2025-01-23 | A K Rajpoot
230 | 51/0 | DD60+0 | Wet paddy | 2025-01-12 | 169.71 | Completed |  |  |  | 2025-01-24 | M A Construction
231 | 53A/3 | DA-3 | WET | 2025-01-18 | 58.51 | Completed |  |  |  | 2025-01-25 | Laxmi Const.
232 | 27/0 | DD60+3 | FS | 2025-01-14 | 331.82 | Completed |  |  |  | 2025-01-29 | VH Rajpoot cont.
233 | 45/1 | DA+3 | Wet Paddy | 2025-01-21 | 41.37 | Completed |  |  |  | 2025-01-30 | Maa Durga
234 | 21/3 | DA+3 | Wet Paddy | 2025-01-25 | 41.37 | Completed |  |  |  | 2025-01-31 | A K Rajpoot
235 | 52/6 | DA+3 | WET | 2025-01-21 | 61.06 | Completed |  |  |  | 2025-01-31 | SAIFI CON.
236 | 57/0 | DB2+0 | PS | 2025-01-15 | 119.635 | Completed |  |  |  | 2025-01-31 | Aneshwar Traders
237 | 0/2 | DA-3 | Wet Paddy | 2025-01-23 | 37.64 | Completed |  |  |  | 2025-01-31 | SSR engineering
238 | 0/3 | DA-3 | Wet Paddy | 2025-01-24 | 37.64 | Completed |  |  |  | 2025-01-31 | Garg Construction
239 | 53/1 | DA+6 | WET | 2025-01-26 | 61.06 | Completed |  |  |  | 2025-02-03 | Laxmi Const.
240 | 24/0 | DD60+25 | Wet Paddy | 2025-01-18 | 165.36 | Completed |  |  |  | 2025-02-04 | A V I ENTERPRISE
241 | 42/0 | DD60+18 | Wet Paddy | 2025-01-23 | 165.36 | Completed |  |  |  | 2025-02-05 | Dharamdas Contractor
242 | 35/6 | DA+0 | Wet Paddy | 2025-02-01 | 37.64 | Completed |  |  |  | 2025-02-06 | Maa Durga
243 | 22/0 | DB2+3 | Wet Paddy | 2025-02-01 | 65.912 | Completed |  |  |  | 2025-02-07 | A K Rajpoot
244 | 56/2 | DA+3 | WET | 2025-02-01 | 61.06 | Completed |  |  |  | 2025-02-07 | R K Constrcution
245 | 0/4 | DA+9 | Wet Paddy | 2025-02-01 | 41.37 | Completed |  |  |  | 2025-02-09 | Garg Construction
246 | 29/0 | DD60+25 | Wet Paddy | 2025-01-30 | 165.36 | Completed |  |  |  | 2025-02-09 | VH Rajpoot cont.
247 | 52/4 | DA-3 | WET | 2025-02-01 | 58.51 | Completed |  |  |  | 2025-02-10 | Vinayak Enterprise
248 | 52/5 | DA-3 | WET | 2025-02-02 | 58.51 | Completed |  |  |  | 2025-02-15 | SAIFI CON.
249 | 40/0 | DD60+25 2mtr RC | Wet Paddy | 2025-02-02 | 173.792 | Completed |  |  |  | 2025-02-15 | Aneshwar Traders
250 | 59/0 | DD60+6 | WET | 2025-02-02 | 253.37 | Completed |  |  |  | 2025-02-15 | M A Construction
251 | 0/1 | DA-3 | WET | 2025-02-02 | 58.51 | Completed |  |  |  | 2025-02-15 | SSR engineering
252 | 22A/0 | DB1+25 | WET | 2025-02-09 | 85.98 | Completed |  |  |  | 2025-02-17 | A K Rajpoot
253 | 25/0 | DD60+25 | Wet Paddy | 2025-02-06 | 165.36 | Completed |  |  |  | 2025-02-18 | A V I ENTERPRISE
254 | 64/0 | DC1+0 | WET | 2025-02-06 | 98.56 | Completed |  |  |  | 2025-02-18 | Laxmi Const.
255 | 53A/7 | DA+0 | Wet Paddy | 2025-02-10 | 37.64 | Completed |  |  |  | 2025-02-20 | Maa Durga
256 | 30/0 | DD60+18 | Wet Paddy | 2025-02-10 | 165.36 | Completed |  |  |  | 2025-02-21 | VH Rajpoot cont.
257 | 52/2 | DA+3 | WET | 2025-02-11 | 61.06 | Completed |  |  |  | 2025-02-21 | Vinayak Enterprise
258 | 43/0 | DD60+9,2mtr RC | Wet Paddy | 2025-02-06 | 177.252 | Completed |  |  |  | 2025-02-21 | Dharamdas Contractor
259 | 4/1 | DA+3 Normal leg A,B | Wet Paddy | 2025-02-10 | 20.685 | Completed |  |  |  | 2025-02-22 | Garg Construction
| 4/1 | DA+3, 2mtr RC(C,D) | Wet Paddy | 2025-02-10 | 27.165 | Completed |  |  |  | 2025-02-22 | Garg Construction
260 | 56/3 | DA-3 | WET | 2025-02-10 | 58.51 | Completed |  |  |  | 2025-02-23 | R K Constrcution
261 | 41/0 | DD60+18,2mtr RC | Wet Paddy | 2025-02-16 | 173.792 | Completed |  |  |  | 2025-02-25 | Aneshwar Traders
262 | 63/0 | DC1+3 | WET | 2025-02-19 | 100.37 | Completed |  |  |  | 2025-02-27 | Laxmi Const.
263 | 11/0 | DB1+18 | Wet Paddy | 2025-02-19 | 59.55 | Completed |  |  |  | 2025-02-28 | SSR engineering
264 | 58/0 | DD60+18 | WET | 2025-02-19 | 243.46 | Completed |  |  |  | 2025-02-28 | M A Construction
265 | 53A/1 | DA+6 | WET | 2025-02-20 | 61.06 | Completed |  |  |  | 2025-02-28 | SAIFI CON.
266 | 21/2 | DA+3 | Wet Paddy | 2025-02-26 | 41.37 | Completed |  |  |  | 2025-02-28 | VH Rajpoot cont.
267 | 13/0 | DD60+30 | Wet Paddy | 2025-02-26 | 165.36 | Completed |  |  |  | 2025-03-03 | A K Rajpoot
268 | 50/0 | DC1+18 | Wet Paddy | 2025-02-26 | 90.44 | Completed |  |  |  | 2025-03-04 | Maa Durga
269 | 23/0 | DC2+18 | Wet Paddy | 2025-03-01 | 100.19 | Completed |  |  |  | 2025-03-08 | VH Rajpoot cont.
270 | 60/0 | DD45+6 | WET | 2025-02-27 | 141.75 | Completed |  |  |  | 2025-03-08 | Laxmi Const.
271 | 14/0 | DD60+30 | Wet Paddy | 2025-03-04 | 165.36 | Completed |  |  |  | 2025-03-09 | A K Rajpoot
272 | 34/5 | DA+0 | Wet Paddy | 2025-03-04 | 37.64 | Completed |  |  |  | 2025-03-09 | Maa Durga
273 | 12/0 | DB2+18 | Wet Paddy | 2025-03-01 | 68.11 | Completed |  |  |  | 2025-03-10 | Garg Construction
274 | 56/4 | DA-3 | WET | 2025-03-01 | 58.51 | Completed |  |  |  | 2025-03-11 | R K Constrcution
275 | 61/0 | DD60+30 | WET | 2025-03-01 | 243.46 | Completed |  |  |  | 2025-03-20 | M A Construction
276 | 67/0 | DD60+30 | WET | 2025-03-01 | 243.46 | Completed |  |  |  | 2025-03-20 | Aneshwar Traders
277 | 52/1 | DB1+6 | WET | 2025-03-01 | 82.51 | Completed |  |  |  | 2025-03-22 | Vinayak Enterprise
278 | 18/0 | DB1+6 | Wet Paddy | 2025-03-20 | 58.25 | Completed |  |  |  | 2025-03-25 | A K Rajpoot
279 | 64/3 | DA-3 | WET | 2025-03-20 | 58.51 | Completed |  |  |  | 2025-03-26 | Laxmi Const.
280 | 66/1 | DA+0 | WET | 2025-03-20 | 58.51 | Completed |  |  |  | 2025-03-26 | SAIFI CON.
281 | 62/0 | DC1+25 | WET | 2025-03-20 | 132.23 | Completed |  |  |  | 2025-03-27 | M A Construction
282 | 19/0 | DC2+6 | Wet Paddy | 2025-03-25 | 77.81 | Completed |  |  |  | 2025-03-30 | A K Rajpoot
283 | 57/1 | DA-3 | WET | 2025-03-25 | 58.51 | Completed |  |  |  | 2025-04-02 | Maa Durga
284 | 56/6 | DA+0 | WET | 2025-03-25 | 58.51 | Completed |  |  |  | 2025-04-02 | R K Constrcution
285 | 21/1 | DA-3 | Wet Paddy | 2025-03-31 | 37.64 | Completed |  |  |  | 2025-04-03 | A K Rajpoot
286 | 66/0 A,B | DD60+0 | FS | 2025-03-25 | 163.31 | Completed |  |  |  | 2025-04-10 | Dharamdas Contractor
| 66/0 C,D | DD60+0, 1mtr RC | FS | 2025-03-25 | 164.495 | Completed |  |  |  | 2025-04-10 | Dharamdas Contractor
287 | 16/0 | DB2+25 | Wet Paddy | 2025-04-04 | 68.11 | Completed |  |  |  | 2025-04-10 | A K Rajpoot
288 | 68/0 | DD60+30 | WET | 2025-04-04 | 243.46 | Completed |  |  |  | 2025-04-17 | Aneshwar Traders
289 | 2/1 | DA+3 | WET | 2025-04-17 | 61.06 | Completed |  |  |  | 2025-04-21 | VH Rajpoot cont.
290 | 44/0 | DD60+3 | FS | 2025-04-04 | 331.82 | Completed |  |  |  | 2025-04-21 | Laxmi Const.
291 | 1/0 | DC1+3 | Wet Paddy | 2025-04-22 | 71.04 | Completed |  |  |  | 2025-04-27 | VH Rajpoot cont.
292 | 65/0 | DD60+0 | FS | 2025-04-11 | 326.62 | Completed |  |  |  | 2025-04-28 | Dharamdas Contractor
293 | 2/0 | DD45+3 | Wet Paddy | 2025-04-22 | 94.55 | Completed |  |  |  | 2025-04-29 | A V I ENTERPRISE
294 | 70/0 | DD60+0 | WET | 2025-04-17 | 249.38 | Completed |  |  |  | 2025-04-30 | SAIFI CON.
295 | 2/2 | DA+0 | Wet Paddy | 2025-04-27 | 37.64 | Completed |  |  |  | 2025-04-30 | VH Rajpoot cont.
296 | 45/0 | DD60+0 | FS | 2025-04-25 | 326.62 | Completed |  |  |  | 2025-05-11 | Laxmi Const.
297 | 38/5 | DA+3 | WET | 2025-05-05 | 61.06 | Completed |  |  |  | 2025-05-11 | VH Rajpoot cont.
298 | 0/0 | DCT+0 | WET | 2025-05-05 | 118.54 | Completed |  |  |  | 2025-05-17 | A V I ENTERPRISE
299 | 69/0 | DC2+0 | WET | 2025-05-06 | 110.03 | Completed |  |  |  | 2025-05-19 | SAIFI CON.
300 | 37/0 | DC2+18 | FS | 2025-05-11 | 261.196 | Completed |  |  |  | 2025-05-23 | VH Rajpoot cont.
301 | 69A/0 | DD60+0 | WET | 2025-05-14 | 249.38 | Completed |  |  |  | 2025-05-28 | Aneshwar Traders
302 | 38/0 | DC2+18 | FS | 2025-05-20 | 261.196 | Completed |  |  |  | 2025-06-03 | A V I ENTERPRISE
SL No. | Location No. | Tower Type | Classification | Start Date | MT | Status |  |  |  | End Date | Gang Name | Gang Strength | Remark
1 | 2/8 | DA+0 |  | 2024-09-01 | 43.7758 | COMPLETED |  |  |  | 2024-09-16 | Dewi Construction(Girendra)
2 | 2/4 | DA+0 |  | 2024-09-16 | 43.7758 | COMPLETED |  |  |  | 2024-09-29 | Dewi Construction(Girendra)
3 | 39/10 | DA+0 |  | 2024-09-16 | 43.7758 | COMPLETED |  |  |  | 2024-10-01 | Horil Mahto
4 | 20/8 | DA+0 |  | 2024-10-01 | 43.7758 | COMPLETED |  |  |  | 2024-10-07 | Dewi Construction(Girendra)
5 | 39/8 | DA+0 |  | 2024-10-03 | 43.7758 | COMPLETED |  |  |  | 2024-10-15 | Horil Mahto
6 | 20/6 | DA+0 |  | 2024-10-08 | 43.7758 | COMPLETED |  |  |  | 2024-10-13 | Dewi Construction(Girendra)
7 | 20/9 | DA+3 |  | 2024-10-14 | 46.0492 | COMPLETED |  |  |  | 2024-10-19 | Dewi Construction(Girendra)
8 | 39/7 | DA+3 |  | 2024-10-15 | 46.0492 | COMPLETED |  |  |  | 2024-10-24 | Horil Mahto
9 | 20/5 | DA+3 |  | 2024-10-20 | 46.0492 | COMPLETED |  |  |  | 2024-10-24 | Dewi Construction(Girendra)
10 | 20/7 | DA-3 |  | 2024-10-24 | 42.3742 | COMPLETED |  |  |  | 2024-10-29 | Dewi Construction(Girendra)
11 | 39/9 | DA+3 |  | 2024-10-24 | 46.0492 | COMPLETED |  |  |  | 2024-10-31 | Horil Mahto
12 | 20/12 | DA-3 |  | 2024-11-01 | 42.3742 | COMPLETED |  |  |  | 2024-11-04 | Dewi Construction(Girendra)
13 | 14/6 | DA+3 |  | 2024-11-05 | 46.0492 | COMPLETED |  |  |  | 2024-11-10 | Dewi Construction(Girendra)
14 | 39/6 | DA+3 |  | 2024-11-01 | 46.0492 | COMPLETED |  |  |  | 14.11.2024 | Horil Mahto
15 | 14/5 | DA+3 |  | 2024-11-10 | 46.0492 | COMPLETED |  |  |  | 2024-11-17 | Dewi Construction(Girendra)
16 | 14/4 | DA+3 |  | 2024-11-17 | 46.0492 | COMPLETED |  |  |  | 2024-11-22 | Dewi Construction(Girendra)
17 | 2/5 | DA+3 |  | 2024-11-10 | 46.0492 | COMPLETED |  |  |  | 2024-11-24 | Pankaj
18 | 19/3 | DA+3 |  | 2024-11-10 | 46.0492 | COMPLETED |  |  |  | 2024-11-26 | Reeta Bharti
19 | 6/2 | DA+3 |  | 2024-11-14 | 46.0492 | COMPLETED |  |  |  | 2024-11-25 | Pinky Dewi
20 | 38/3 | DA+3 |  | 2024-11-10 | 46.0492 | COMPLETED |  |  |  | 2024-11-25 | Horil Mahto
21 | 14/8 | DA+3 |  | 2024-11-22 | 46.0492 | COMPLETED |  |  |  | 2024-11-28 | Dewi Construction(Girendra)
22 | 41/1 | DA+0 |  | 2024-11-10 | 43.7758 | COMPLETED |  |  |  | 2024-11-29 | Amar Singh
23 | 2/7 | DA+3 |  | 2024-11-26 | 46.0492 | COMPLETED |  |  |  | 2024-12-03 | Pankaj
24 | 19/2 | DA+0 |  | 2024-11-28 | 43.7758 | COMPLETED |  |  |  | 2024-12-05 | Reeta Bharti
25 | 14/7 | DA+0 |  | 2024-11-29 | 43.7758 | COMPLETED |  |  |  | 2024-12-05 | Dewi Construction(Girendra)
26 | 4/3 | DA+3 |  | 2024-11-28 | 46.0492 | COMPLETED |  |  |  | 2024-12-05 | Pinky Dewi
27 | 36/12 | DA+0 |  | 2024-11-29 | 43.7758 | COMPLETED |  |  |  | 2024-12-06 | Horil Mahto
28 | 2/6 | DA+0 |  | 2024-12-01 | 43.7758 | COMPLETED |  |  |  | 2024-12-09 | Pankaj
29 | 41/2 | DA+3 |  | 2024-11-30 | 46.0492 | COMPLETED |  |  |  | 2024-12-10 | Amar Singh
30 | 14/3 | DA+0 |  | 2024-12-06 | 43.7758 | COMPLETED |  |  |  | 2024-12-12 | Dewi Construction(Girendra)
31 | 4/4 | DA+0 |  | 2024-12-06 | 43.7758 | COMPLETED |  |  |  | 2024-12-12 | Pinky Dewi
32 | 19/4 | DA+0 |  | 2024-12-06 | 43.7758 | COMPLETED |  |  |  | 2024-12-13 | Reeta Bharti
33 | 2/3 | DA+3 |  | 2024-12-10 | 46.0492 | COMPLETED |  |  |  | 2024-12-16 | Pankaj
34 | 4/2 | DA-3 |  | 2024-12-12 | 42.3742 | COMPLETED |  |  |  | 2024-12-16 | Pinky Dewi
35 | 14/2 | DA+0 |  | 2024-12-12 | 43.7758 | COMPLETED |  |  |  | 2024-12-17 | Dewi Construction(Girendra)
36 | 38/2 | DA+3 |  | 2024-12-06 | 46.0492 | COMPLETED |  |  |  | 2024-12-19 | Horil Mahto
37 | 45/3 | DA-3 |  | 2024-12-10 | 42.3742 | COMPLETED |  |  |  | 2024-12-20 | Amar Singh
38 | 19/1 | DA+0 |  | 2024-12-13 | 43.7758 | COMPLETED |  |  |  | 2024-12-21 | Reeta Bharti
39 | 4/8 | DA+0 |  | 2024-12-17 | 43.7758 | COMPLETED |  |  |  | 2024-12-22 | Pinky Dewi
40 | 14/1 | DA+0 |  | 2024-12-18 | 43.7758 | COMPLETED |  |  |  | 2024-12-23 | Dewi Construction(Girendra)
41 | 7/10 | DA+3 |  | 2024-12-18 | 46.0492 | COMPLETED |  |  |  | 2024-12-23 | Pankaj
42 | 45/2 | DA+3 |  | 2024-12-21 | 46.0492 | COMPLETED |  |  |  | 2024-12-27 | Amar Singh
43 | 19/5 | DA-3 |  | 2024-12-22 | 42.3742 | COMPLETED |  |  |  | 2024-12-27 | Reeta Bharti
44 | 4/7 | DA+3 |  | 2024-12-24 | 46.0492 | COMPLETED |  |  |  | 2024-12-27 | Pinky Dewi
45 | 7/9 | DA+0 |  | 2024-12-24 | 43.7758 | COMPLETED |  |  |  | 2024-12-30 | Pankaj
46 | 38/4 | DA+3 |  | 2024-12-20 | 46.0492 | COMPLETED |  |  |  | 2024-12-31 | Horil Mahto
47 | 17/1 | DA-3 |  | 2024-12-24 | 42.3742 | COMPLETED |  |  |  | 2024-12-31 | Dewi Construction(Girendra)
48 | 31/3 | DA+3 |  | 2024-12-24 | 46.0492 | COMPLETED |  |  |  | 2025-01-03 | ASC heights
49 | 4/5 | DA+3 |  | 2024-12-28 | 46.0492 | COMPLETED |  |  |  | 2025-01-03 | Pinky Dewi
50 | 46/1 | DA+0 |  | 2024-12-28 | 43.7758 | COMPLETED |  |  |  | 2025-01-04 | Amar Singh
51 | 7/2 | DA+3 |  | 2024-12-31 | 46.0492 | COMPLETED |  |  |  | 2025-01-07 | Pankaj
52 | 19/6 | DA+0 |  | 2024-12-28 | 43.7758 | COMPLETED |  |  |  | 2025-01-08 | Reeta Bharti
53 | 17/4 | DA+3 |  | 2025-01-01 | 46.0492 | COMPLETED |  |  |  | 2025-01-10 | Dewi Construction(Girendra)
54 | 31/4 | DA-3 |  | 2025-01-04 | 42.3742 | COMPLETED |  |  |  | 2025-01-11 | ASC heights
55 | 12/2 | DA+3 |  | 2025-01-03 | 46.0492 | COMPLETED |  |  |  | 2025-01-11 | Pinky Dewi
56 | 7/8 | DA+3 |  | 2025-01-08 | 46.0492 | COMPLETED |  |  |  | 2025-01-14 | Pankaj
57 | 36/3 | DA+3 |  | 2025-01-07 | 46.0492 | COMPLETED |  |  |  | 2025-01-15 | Amar Singh
58 | 38/1 | DA+3 |  | 2025-01-07 | 46.0492 | COMPLETED |  |  |  | 2025-01-17 | Horil Mahto
59 | 19/7 | DA+3 |  | 2025-01-09 | 46.0492 | COMPLETED |  |  |  | 2025-01-17 | Reeta Bharti
60 | 17/3 | DA+0 |  | 2025-01-10 | 43.7758 | COMPLETED |  |  |  | 2025-01-17 | Dewi Construction(Girendra)
61 | 31/2 | DA+0 |  | 2025-01-11 | 43.7758 | COMPLETED |  |  |  | 2025-01-19 | ASC heights
62 | 12/3 | DA+3 |  | 2025-01-12 | 46.0492 | COMPLETED |  |  |  | 2025-01-21 | Pinky Dewi
63 | 7/7 | DA+0 |  | 2025-01-15 | 43.7758 | COMPLETED |  |  |  | 2025-01-22 | Pankaj
64 | 17/2 | DA+0 |  | 2025-01-17 | 43.7758 | COMPLETED |  |  |  | 2025-01-23 | Dewi Construction(Girendra)
65 | 36/5 | DA+0 |  | 2025-01-15 | 43.7758 | COMPLETED |  |  |  | 2025-01-24 | Amar Singh
66 | 31/6 | DA+3 |  | 2025-01-20 | 46.0492 | COMPLETED |  |  |  | 2025-01-25 | ASC heights
67 | 12/4 | DA+3 |  | 2025-01-21 | 46.0492 | COMPLETED |  |  |  | 2025-01-25 | Pinky Dewi
68 | 19/9 | DA+3 |  | 2025-01-16 | 46.0492 | COMPLETED |  |  |  | 2025-01-27 | Reeta Bharti
69 | 35/1 | DA+3 |  | 2025-01-16 | 46.0492 | COMPLETED |  |  |  | 2025-01-28 | Horil Mahto
70 | 17/5 | DA+3 |  | 2025-01-24 | 46.0492 | COMPLETED |  |  |  | 2025-01-29 | Dewi Construction(Girendra)
71 | 7/6 | DA+0 |  | 2025-01-21 | 43.7758 | COMPLETED |  |  |  | 2025-01-30 | Pankaj
72 | 36/1 | DA+3 |  | 2025-01-25 | 46.0492 | COMPLETED |  |  |  | 2025-01-30 | Amar Singh
73 | 33/10 | DA+3 |  | 2025-01-21 | 46.0492 | COMPLETED |  |  |  | 2025-01-31 | Rudra Construction
74 | 12/5 | DA+3 |  | 2025-01-25 | 46.0492 | COMPLETED |  |  |  | 2025-02-01 | Pinky Dewi
75 | 31/1 | DA+0 |  | 2025-01-25 | 43.7758 | COMPLETED |  |  |  | 2025-02-02 | ASC heights
76 | 17/7 | DA+3 |  | 2025-01-30 | 46.0492 | COMPLETED |  |  |  | 2025-02-05 | Dewi Construction(Girendra)
77 | 20/0 | DB+0 |  | 2025-01-28 | 64.4817 | COMPLETED |  |  |  | 2025-02-06 | Reeta Bharti
78 | 36/2 | DA+0 |  | 2025-02-02 | 43.7758 | COMPLETED |  |  |  | 2025-02-07 | Amar Singh | 27
79 | 12/9 | DA+3 |  | 2025-02-02 | 46.0492 | COMPLETED |  |  |  | 2025-02-08 | Pinky Dewi
80 | 7/5 | DA+3 |  | 2025-01-29 | 46.0492 | COMPLETED |  |  |  | 2025-02-09 | Pankaj
81 | 31/7 | DA+0 |  | 2025-02-03 | 43.7758 | COMPLETED |  |  |  | 2025-02-10 | ASC heights | 23
82 | 35/0 | DC+0 |  | 2025-01-29 | 73.4258 | COMPLETED |  |  |  | 2025-02-11 | Horil Mahto
83 | 33/11 | DA+3 |  | 2025-02-02 | 46.0492 | COMPLETED |  |  |  | 2025-02-12 | Rudra Construction
84 | 21/0 | DB+0 |  | 2025-02-06 | 64.4817 | COMPLETED |  |  |  | 2025-02-13 | Dewi Construction(Girendra)
85 | 20/2 | DA+0 |  | 2025-02-07 | 43.7758 | COMPLETED |  |  |  | 2025-02-13 | Reeta Bharti
86 | 35/9 | DA+3 |  | 2025-02-08 | 46.0492 | COMPLETED |  |  |  | 2025-02-15 | Amar Singh
87 | 8/1 | DA+3 |  | 2025-02-09 | 46.0492 | COMPLETED |  |  |  | 2025-02-15 | Pinky Dewi
88 | 7/4 | DA+0 |  | 2025-02-10 | 43.7758 | COMPLETED |  |  |  | 2025-02-18 | Pankaj
89 | 20/3 | DA+0 |  | 2025-02-12 | 43.7758 | COMPLETED |  |  |  | 2025-02-19 | Reeta Bharti
90 | 31/9 | DA+3 |  | 2025-02-11 | 46.0492 | COMPLETED |  |  |  | 2025-02-20 | ASC heights
91 | 34/7 | DA+3 |  | 2025-02-12 | 46.0492 | COMPLETED |  |  |  | 2025-02-20 | Horil Mahto
92 | 33/6 | DA+3 |  | 2025-02-14 | 46.0492 | COMPLETED |  |  |  | 2025-02-20 | Dewi Construction(Girendra)
93 | 8/2 | DA+0 |  | 2025-02-16 | 43.7758 | COMPLETED |  |  |  | 2025-02-21 | Pinky Dewi
94 | 35/7 | DA+3 |  | 2025-02-16 | 46.0492 | COMPLETED |  |  |  | 2025-02-21 | Amar Singh
95 | 33/9 | DA+0 |  | 2025-02-14 | 43.7758 | COMPLETED |  |  |  | 2025-02-22 | Rudra Construction
96 | 20/4 | DA-3 |  | 2025-02-20 | 42.3742 | COMPLETED |  |  |  | 2025-02-25 | Reeta Bharti
97 | 33/7 | DA+3 |  | 2025-02-21 | 46.0492 | COMPLETED |  |  |  | 2025-02-25 | Dewi Construction(Girendra)
98 | 7/1 | DA+0 |  | 2025-02-19 | 43.7758 | COMPLETED |  |  |  | 2025-02-25 | Pankaj
99 | 34/6 | DA+0 |  | 2025-02-21 | 43.7758 | COMPLETED |  |  |  | 2025-02-27 | Horil Mahto
100 | 35/4 | DA+0 |  | 2025-02-20 | 43.7758 | COMPLETED |  |  |  | 2025-02-27 | Amar Singh
101 | 31/0 | DB+0 |  | 2025-02-19 | 64.4817 | COMPLETED |  |  |  | 2025-02-28 | ASC heights
102 | 8/0 | DB+0 |  | 2025-02-22 | 64.4817 | COMPLETED |  |  |  | 2025-02-28 | Pinky Dewi
103 | 33/3 | DA+3 |  | 2025-02-26 | 46.0492 | COMPLETED |  |  |  | 2025-03-02 | Dewi Construction(Girendra)
104 | 35/5 | DA+3 |  | 2025-02-27 | 46.0492 | COMPLETED |  |  |  | 2025-03-03 | Amar Singh
105 | 4/10 | DA+3 |  | 2025-03-01 | 46.0492 | COMPLETED |  |  |  | 2025-03-05 | Reeta Bharti
106 | 33/8 | DA+3 |  | 2025-03-03 | 46.0492 | COMPLETED |  |  |  | 2025-03-07 | Dewi Construction(Girendra)
107 | 7/0 | DB+0 |  | 2025-02-27 | 64.4817 | COMPLETED |  |  |  | 2025-03-08 | Pankaj
108 | 7/11 | DA+0 |  | 2025-03-01 | 43.7758 | COMPLETED |  |  |  | 2025-03-08 | Pinky Dewi
109 | 35/3 | DA+0 |  | 2025-02-28 | 43.7758 | COMPLETED |  |  |  | 2025-03-08 | Horil Mahto
110 | 30/4 | DA+3 |  | 2025-03-01 | 46.0492 | COMPLETED |  |  |  | 2025-03-09 | ASC heights
111 | 34/1 | DA+3 |  | 2025-03-01 | 46.0492 | COMPLETED |  |  |  | 2025-03-11 | Rudra Construction
112 | 33/4 | DA-3 |  | 2025-03-08 | 42.3742 | COMPLETED |  |  |  | 2025-03-11 | Dewi Construction(Girendra)
113 | 8/3 | DA-3 |  | 2025-03-08 | 42.3742 | COMPLETED |  |  |  | 2025-03-12 | Pinky Dewi
114 | 5/0 | DB+0 |  | 2025-03-01 | 64.4817 | COMPLETED |  |  |  | 2025-03-13 | Reeta Bharti
115 | 30/5 | DA+0 |  | 2025-03-10 | 43.7758 | COMPLETED |  |  |  | 2025-03-16 | ASC heights
116 | 35/6 | DA+0 |  | 2025-03-10 | 43.7758 | COMPLETED |  |  |  | 2025-03-18 | Horil Mahto
117 | 33/1 | DA-3 |  | 2025-03-12 | 42.3742 | COMPLETED |  |  |  | 2025-03-18 | Dewi Construction(Girendra)
118 | 6/1 | DA+3 |  | 2025-03-09 | 46.0492 | COMPLETED |  |  |  | 2025-03-19 | Pankaj
119 | 8/4 | DA+9 |  | 2025-03-13 | 55.3387 | COMPLETED |  |  |  | 2025-03-21 | Pinky Dewi
120 | 5/1 | DA+3 |  | 2025-03-16 | 46.0492 | COMPLETED |  |  |  | 2025-03-21 | Reeta Bharti
121 | 31/8 | DA-3 |  | 2025-03-16 | 42.3742 | COMPLETED |  |  |  | 2025-03-23 | ASC heights
122 | 33/2 | DA-3 |  | 2025-03-19 | 42.3742 | COMPLETED |  |  |  | 2025-03-23 | Dewi Construction(Girendra)
123 | 8B/1 | DA-3 |  | 2025-03-22 | 42.3742 | COMPLETED |  |  |  | 2025-03-26 | Pinky Dewi
124 | 7/3 | DA-3 |  | 2025-03-20 | 42.3742 | COMPLETED |  |  |  | 2025-03-27 | Pankaj
125 | 6/0 | DB+0 |  | 2025-03-22 | 64.4817 | COMPLETED |  |  |  | 2025-03-29 | Reeta Bharti
126 | 35/2 | DA-3 |  | 2025-03-20 | 42.3742 | COMPLETED |  |  |  | 2025-03-30 | Horil Mahto
127 | 31/10 | DA-3 |  | 2025-03-24 | 42.3742 | COMPLETED |  |  |  | 2025-03-30 | ASC heights
128 | 34/0 | DB+0 |  | 2025-03-24 | 64.4817 | COMPLETED |  |  |  | 2025-03-31 | Dewi Construction(Girendra)
129 | 38/8 | DA+3 |  | 2025-03-21 | 46.0492 | COMPLETED |  |  |  | 2025-03-31 | M K infra
130 | 35/8 | DA-3 |  | 2025-03-22 | 42.3742 | COMPLETED |  |  |  | 2025-03-31 | Amar Singh
131 | 39/3 | DA+3 |  | 2025-03-24 | 46.0492 | COMPLETED |  |  |  | 2025-03-31 | Ananya Traders-1
132 | 8B/5 | DA+6 |  | 2025-03-24 | 53.3239 | COMPLETED |  |  |  | 2025-03-31 | Pinky Dewi
133 | 4/6 | DA+0 |  | 2025-03-28 | 43.7758 | COMPLETED |  |  |  | 2025-04-05 | Reeta Bharti
134 | 8B/3 | DA+3 |  | 2025-03-28 | 46.0492 | COMPLETED |  |  |  | 2025-04-07 | Pinky Dewi
135 | 20/11 | DA-3 |  | 2025-03-31 | 42.3742 | COMPLETED |  |  |  | 2025-04-08 | Gagan enterprise.1
136 | 34/4 | DA-3 |  | 2025-04-03 | 42.3742 | COMPLETED |  |  |  | 2025-04-10 | Dewi Construction(Girendra)
137 | 4/1 | DA+3 |  | 2025-03-31 | 46.0492 | COMPLETED |  |  |  | 2025-04-11 | Anand Construction
138 | 38/6 | DA+3 |  | 2025-04-01 | 46.0492 | COMPLETED |  |  |  | 2025-04-11 | M K infra
139 | 9/0 | DB+6 |  | 2025-04-01 | 75.8584 | COMPLETED |  |  |  | 2025-04-11 | Gagan enterprise.2
140 | 32/0 | DC+6 |  | 2025-04-01 | 87.0116 | COMPLETED |  |  |  | 2025-04-11 | ASC heights
141 | 39/1 | DA+3 |  | 2025-04-01 | 46.0492 | COMPLETED |  |  |  | 2025-04-12 | Ananya Traders-1
142 | 53A/4 | DA+3 |  | 2025-04-01 | 46.0492 | COMPLETED |  |  |  | 2025-04-12 | Horil Mahto
143 | 8B/2 | DA-3 |  | 2025-04-08 | 42.3742 | COMPLETED |  |  |  | 2025-04-13 | Pinky Dewi
144 | 36/0 | DB+0 |  | 2025-04-02 | 64.4817 | COMPLETED |  |  |  | 2025-04-14 | Amar Singh
145 | 20/10 | DA+3 |  | 2025-04-09 | 46.0492 | COMPLETED |  |  |  | 2025-04-15 | Gagan enterprise.1
146 | 52/6 | DA+3 |  | 2025-04-05 | 46.0492 | COMPLETED |  |  |  | 2025-04-16 | Ananya Traders-2
147 | 10/1 | DA-3 |  | 2025-04-12 | 42.3742 | COMPLETED |  |  |  | 2025-04-16 | Gagan enterprise.2
148 | 4/0 | DD45+0 |  | 2025-04-06 | 86.2562 | COMPLETED |  |  |  | 2025-04-17 | Reeta Bharti
149 | 39/0 | DB+0 |  | 2025-04-12 | 64.4817 | COMPLETED |  |  |  | 2025-04-19 | Ananya Traders-1
150 | 8B/4 | DA+6 |  | 2025-04-14 | 53.3239 | COMPLETED |  |  |  | 2025-04-21 | Pinky Dewi
151 | 31/5 | DA-3 |  | 2025-04-12 | 42.3742 | COMPLETED |  |  |  | 2025-04-21 | ASC heights
152 | 33/0 | DC+6 |  | 2025-04-12 | 87.0116 | COMPLETED |  |  |  | 2025-04-22 | Dewi Construction(Girendra)
153 | 38/7 | DA-3 |  | 2025-04-12 | 42.3742 | COMPLETED |  |  |  | 2025-04-22 | M K infra
154 | 36/6 | DA+3 |  | 2025-04-12 | 46.0492 | COMPLETED |  |  |  | 2025-04-22 | Amar Singh
155 | 20/1 | DA+6 |  | 2025-04-16 | 53.3239 | COMPLETED |  |  |  | 2025-04-22 | Gagan enterprise.1
156 | 25/2 | DA+0 |  | 2025-04-15 | 43.7758 | COMPLETED |  |  |  | 2025-04-23 | Rudra Construction
157 | 52/5 | DA-3 |  | 2025-04-17 | 42.3742 | COMPLETED |  |  |  | 2025-04-25 | Ananya Traders-2
158 | 0/4 | DA+9 |  | 2025-04-12 | 55.3387 | COMPLETED |  |  |  | 2025-04-26 | Anand Construction
159 | 19/12 | DA-3 |  | 2025-04-23 | 42.3742 | COMPLETED |  |  |  | 2025-04-26 | Gagan enterprise.1
160 | 39/2 | DA-3 |  | 2025-04-20 | 42.3742 | COMPLETED |  |  |  | 2025-04-26 | Ananya Traders-1
161 | 36/7 | DA+3 |  | 2025-04-23 | 46.0492 | COMPLETED |  |  |  | 2025-04-28 | Amar Singh
162 | 34/2 | DA+3 |  | 2025-04-23 | 46.0492 | COMPLETED |  |  |  | 2025-04-28 | Dewi Construction(Girendra)
163 | 10/0 | DB+9 |  | 2025-04-17 | 78.6775 | COMPLETED |  |  |  | 2025-04-28 | Gagan enterprise.2
164 | 30/6 | DA-3 |  | 2025-04-22 | 42.3742 | COMPLETED |  |  |  | 2025-04-28 | ASC heights
165 | 52/4 | DA-3 |  | 2025-04-26 | 42.3742 | COMPLETED |  |  |  | 2025-04-29 | Ananya Traders-2
166 | 38/9 | DA-3 |  | 2025-04-23 | 42.3742 | COMPLETED |  |  |  | 2025-06-01 | M K infra
167 | 8A/0 | DD60+0 |  | 2025-04-22 | 97.2286 | COMPLETED |  |  |  | 2025-04-30 | Pinky Dewi
168 | 19/11 | DA-3 |  | 2025-04-27 | 42.3742 | COMPLETED |  |  |  | 2025-04-30 | Gagan enterprise.1
169 | 34/3 | DA+3 |  | 2025-04-29 | 46.0492 | COMPLETED |  |  |  | 2025-05-03 | Dewi Construction(Girendra)
170 | 39/4 | DA+3 |  | 2025-04-29 | 46.0492 | COMPLETED |  |  |  | 2025-05-04 | Ananya Traders-1
171 | 36/8 | DA-3 |  | 2025-04-29 | 42.3742 | COMPLETED |  |  |  | 2025-05-05 | Amar Singh
172 | 19/10 | DA+3 |  | 2025-04-30 | 46.0492 | COMPLETED |  |  |  | 2025-05-06 | Gagan enterprise.1
173 | 30/3 | DA+0 |  | 2025-04-30 | 43.7758 | COMPLETED |  |  |  | 2025-05-06 | ASC heights
174 | 52/3 | DA-3 |  | 2025-04-30 | 42.3742 | COMPLETED |  |  |  | 2025-05-06 | Ananya Traders-2
175 | 25/3 | DA+3 |  | 2025-04-30 | 46.0492 | COMPLETED |  |  |  | 2025-05-07 | Rudra Construction
176 | 19/8 | DA-3 |  | 2025-05-06 | 42.3742 | COMPLETED |  |  |  | 2025-05-09 | Gagan enterprise.1
177 | 12/1 | DA-3 |  | 2025-05-04 | 42.3742 | COMPLETED |  |  |  | 2025-05-10 | Gagan enterprise.2
178 | 4/9 | DA-3 |  | 2025-05-04 | 42.3742 | COMPLETED |  |  |  | 2025-05-11 | Reeta Bharti
179 | 39/5 | DA-3 |  | 2025-05-05 | 42.3742 | COMPLETED |  |  |  | 2025-05-11 | Ananya Traders-1
180 | 52/2 | DA+3 |  | 2025-05-07 | 46.0492 | COMPLETED |  |  |  | 2025-05-12 | Ananya Traders-2
181 | 30/1 | DA-3 |  | 2025-05-07 | 42.3742 | COMPLETED |  |  |  | 2025-05-13 | ASC heights
182 | 36/4 | DA+0 |  | 2025-05-07 | 43.7758 | COMPLETED |  |  |  | 2025-05-13 | Amar Singh
183 | 56/2 | DA+3 |  | 2025-05-07 | 46.0492 | COMPLETED |  |  |  | 2025-05-14 | Dewi Construction(Girendra)
184 | 8B/0 | DD60+0 |  | 2025-05-05 | 97.2286 | COMPLETED |  |  |  | 2025-05-14 | Pinky Dewi
185 | 17/8 | DA-3 |  | 2025-05-11 | 42.3742 | COMPLETED |  |  |  | 2025-05-15 | Gagan enterprise.1
186 | 52/9 | DA-3 |  | 2025-05-13 | 42.3742 | COMPLETED |  |  |  | 2025-05-17 | Ananya Traders-2
187 | 56/1 | DA+0 |  | 2025-05-14 | 43.7758 | COMPLETED |  |  |  | 2025-05-19 | Dewi Construction(Girendra)
188 | 36/11 | DA-3 |  | 2025-05-14 | 42.3742 | COMPLETED |  |  |  | 2025-05-19 | Amar Singh
189 | 38/11 | DA+3 |  | 2025-05-12 | 46.0492 | COMPLETED |  |  |  | 2025-05-19 | Ananya Traders-1
190 | 30/2 | DA-3 |  | 2025-05-14 | 42.3742 | COMPLETED |  |  |  | 2025-05-20 | ASC heights
191 | 2/1 | DA+3 |  | 2025-05-12 | 46.0492 | COMPLETED |  |  |  | 2025-05-21 | Reeta Bharti
192 | 52/10 | DA+3 |  | 2025-05-16 | 46.0492 | COMPLETED |  |  |  | 2025-05-21 | Ananya Traders-2
193 | 23/3 | DA-3 |  | 2025-05-15 | 42.3742 | COMPLETED |  |  |  | 2025-05-22 | Pinky Dewi
194 | 12/6 | DA-3 |  | 2025-05-11 | 42.3742 | COMPLETED |  |  |  | 2025-05-22 | Gagan enterprise.2
195 | 53/1 | DA+6 |  | 2025-05-12 | 53.3239 | COMPLETED |  |  |  | 2025-05-22 | Amit Const
196 | 36/9 | DA-3 |  | 2025-05-20 | 42.3742 | COMPLETED |  |  |  | 2025-05-24 | Amar Singh
197 | 38/10 | DA-3 |  | 2025-05-20 | 42.3742 | COMPLETED |  |  |  | 2025-05-24 | Ananya Traders-1
198 | 56/3 | DA-3 |  | 2025-05-20 | 42.3742 | COMPLETED |  |  |  | 2025-05-24 | Dewi Construction(Girendra)
199 | 15/0 | DC+3 |  | 2025-05-16 | 78.0732 | COMPLETED |  |  |  | 2025-05-25 | Gagan enterprise.1
200 | 23/5 | DA-3 |  | 2025-05-10 | 42.3742 | COMPLETED |  |  |  | 2025-05-27 | Rudra Construction
201 | 52/8 | DA-3 |  | 2025-05-22 | 42.3742 | COMPLETED |  |  |  | 2025-05-27 | Ananya Traders-2
202 | 23/4 | DA-3 |  | 2025-05-23 | 42.3742 | COMPLETED |  |  |  | 2025-05-28 | Pinky Dewi
203 | 0/2 | DA-3 |  | 2025-05-23 | 42.3742 | COMPLETED |  |  |  | 2025-05-30 | Reeta Bharti
204 | 56/4 | DA-3 |  | 2025-05-23 | 42.3742 | COMPLETED |  |  |  | 2025-05-30 | Dewi Construction(Girendra)
205 | 12/8 | DA-3 |  | 2025-05-26 | 42.3742 | COMPLETED |  |  |  | 2025-05-31 | Gagan enterprise.1
206 | 36/10 | DA-3 |  | 2025-05-25 | 42.3742 | COMPLETED |  |  |  | 2025-05-31 | Amar Singh
207 | 38/5 | DA+3 |  | 2025-05-28 | 46.0492 | COMPLETED |  |  |  | 2025-06-02 | Ananya Traders-1
208 | 23/1 | DA+9 |  | 2025-05-28 | 55.3387 | COMPLETED |  |  |  | 2025-06-03 | Pinky Dewi
209 | 0/3 | DA-3 |  | 2025-05-25 | 42.3742 | COMPLETED |  |  |  | 2025-06-04 | Reeta Bharti
210 | 56/5 | DA-3 |  | 2025-05-30 | 42.3742 | COMPLETED |  |  |  | 2025-06-04 | Dewi Construction(Girendra)
211 | 51/0 | DD60+0 |  | 2025-05-27 | 97.2286 | COMPLETED |  |  |  | 2025-06-07 | Ananya Traders-2
212 | 23/2 | DA+0 |  | 2025-06-04 | 43.7758 | COMPLETED |  |  |  | 2025-06-09 | Pinky Dewi
213 | 33/5 | DA+3 |  | 2025-06-02 | 46.0492 | COMPLETED |  |  |  | 2025-06-10 | Amar Singh
214 | 0/1 | DA-3 |  | 2025-06-04 | 42.3742 | COMPLETED |  |  |  | 2025-06-11 | Reeta Bharti
215 | 50/1 | DA+0 |  | 2025-06-08 | 43.7758 | COMPLETED |  |  |  | 2025-06-13 | Ananya Traders-2
216 | 53A/5 | DA-3 |  | 2025-06-02 | 42.3742 | COMPLETED |  |  |  | 2025-06-14 | Devine
217 | 34/5 | DA+0 |  | 2025-06-12 | 43.7758 | COMPLETED |  |  |  | 2025-06-18 | Amar Singh
218 | 53A/2 | DA+3 |  | 2025-06-10 | 46.0492 | COMPLETED |  |  |  | 2025-06-18 | Amit Const
219 | 22/0 | DB+3 |  | 2025-06-12 | 67.112 | COMPLETED |  |  |  | 2025-06-20 | Pinky Dewi
220 | 30/0 | DD60+18 |  | 2025-05-25 | 143.4621 | COMPLETED |  |  |  | 2025-06-21 | ASC heights
221 | 3/0 | DC+0 |  | 2025-06-12 | 73.4258 | COMPLETED |  |  |  | 2025-06-23 | Reeta Bharti
222 | 21/2 | DA+3 |  | 2025-06-21 | 46.0492 | COMPLETED |  |  |  | 2025-06-26 | Pinky Dewi
223 | 45/1 | DA+3 |  | 2025-06-10 | 46.0492 | COMPLETED |  |  |  | 2025-06-27 | M K infra
224 | 53A/3 | DA+3 |  | 2025-06-20 | 46.0492 | COMPLETED |  |  |  | 2025-06-29 | Amit Const
225 | 48/0 | DD45+9 |  | 2025-06-15 | 104.8666 | COMPLETED |  |  |  | 2025-06-29 | Ananya Traders-2
226 | 12/7 | DA-3 |  | 2025-06-24 | 42.3742 | COMPLETED |  |  |  | 2025-06-30 | Reeta Bharti
227 | 21/1 | DA-3 |  | 2025-06-27 | 42.3742 | COMPLETED |  |  |  | 2025-06-30 | Pinky Dewi
228 | 40/0 | DD60+25 |  | 2025-06-04 | 161.3552 | COMPLETED |  |  |  | 2025-06-30 | Ananya Traders-1
229 | 14/0 | DD60+30 |  | 2025-06-01 | 188.3779 | COMPLETED |  |  |  | 2025-06-30 | Gagan enterprise.1
230 | 28/1 | DA+3 |  | 2025-06-24 | 46.0492 | COMPLETED |  |  |  | 2025-07-05 | ASC heights
231 | 21/3 | DA+3 |  | 2025-07-01 | 46.0492 | COMPLETED |  |  |  | 2025-07-07 | Pinky Dewi
232 | 25/1 | DA+9 |  | 2025-07-01 | 55.3387 | COMPLETED |  |  |  | 2025-07-12 | Reeta Bharti
233 | 44/0 | DD60+3 |  | 2025-07-05 | 101.692 | COMPLETED |  |  |  | 2025-07-18 | Ananya Traders-1
234 | 56/0 | DD45+0 |  | 2025-06-28 | 86.2562 | COMPLETED |  |  |  | 2025-07-22 | Amar singh
235 | 28/0 | DD60+0 |  | 2025-07-08 | 97.2286 | COMPLETED |  |  |  | 2025-07-31 | Reeta Bharti
236 | 41/0 | DD60+18 |  | 2025-07-20 | 143.4621 | COMPLETED |  |  |  | 2025-08-08 | Ananya Traders-1
237 | 13/0 | DD60+30 |  | 2025-07-09 | 188.3779 | COMPLETED |  |  |  | 2025-08-11 | Gagan enterprise.1
238 | 53A/6 | DA+3 |  | 2025-07-27 | 46.0492 | COMPLETED |  |  |  | 2025-08-17 | Punam Kumari
239 | 46/2 | DA+3 |  | 2025-08-14 | 46.0492 | COMPLETED |  |  |  | 2025-08-26 | Gagan enterprise.2 (Kajol)
240 | 24/0 | DD60+25 |  | 2025-07-26 | 161.3552 | COMPLETED |  |  |  | 2025-08-27 | Kongres Kumar-1
241 | 65/0 | DD60+0 |  | 2025-08-02 | 97.2286 | COMPLETED |  |  |  | 2025-08-30 | Kongres Kumar-2
242 | 18/0 | DB+6 |  | 2025-08-04 | 75.8584 | COMPLETED |  |  |  | 2025-08-30 | Sainik Trader
243 | 1/0 | DC+3 |  | 2025-08-09 | 78.0732 | COMPLETED |  |  |  | 2025-08-30 | Radha Construction
244 | 12/0 | DB+18 |  | 2025-08-12 | 97.6534 | COMPLETED |  |  |  | 2025-09-02 | Gagan enterprise.1
245 | 54/1 | DA+9 |  | 2025-08-18 | 55.3387 | COMPLETED |  |  |  | 2025-09-04 | Punam Kumari
246 | 43/0 | DD60+9 |  | 2025-08-10 | 118.4303 | COMPLETED |  |  |  | 2025-09-06 | Ananya Traders-1
247 | 16/0 | DB+25 |  | 2025-08-16 | 110.6255 | COMPLETED |  |  |  | 2025-09-14 | Amit Choudhury
248 | 11/0 | DB+18 |  | 2025-08-24 | 97.6534 | COMPLETED |  |  |  | 2025-09-14 | Gouri Shankar
249 | 2/0 | DD45+3 |  | 2025-09-03 | 89.7178 | COMPLETED |  |  |  | 2025-09-21 | Radha Construction
250 | 64/0 | DC+0 |  | 2025-08-31 | 73.4258 | COMPLETED |  |  |  | 2025-09-22 | Kongres Kumar-2
251 | 52/0 | DC+9 |  | 2025-09-05 | 90.1252 | COMPLETED |  |  |  | 2025-09-22 | Punam Kumari
252 | 47/0 | DC+9 |  | 2025-09-07 | 90.1252 | COMPLETED |  |  |  | 2025-09-22 | Ananya Traders-1
253 | 29/0 | DD60+25 |  | 2025-08-06 | 161.3552 | COMPLETED |  |  |  | 2025-09-22 | Reeta Bharti
254 | 56/8 | DA-3 |  | 2025-08-18 | 42.3742 | COMPLETED |  |  |  | 2025-09-24 | Spotyfy-3
255 | 48/1 | DA-3 |  | 2025-09-15 | 42.3742 | COMPLETED |  |  |  | 2025-09-23 | Ananya trader
256 | 17/6 | DA-3 |  | 2025-09-15 | 42.3742 | COMPLETED |  |  |  | 2025-09-24 | Amit Choudhury
257 | 19/0 | DC+6 |  | 2025-08-31 | 87.0116 | COMPLETED |  |  |  | 2025-09-24 | Sainik Trader
258 | 26/0 | DB+9 |  | 2025-09-15 | 78.6775 | COMPLETED |  |  |  | 2025-09-25 | Gouri Shankar
259 | 17/0 | DB+6 |  | 2025-09-11 | 75.8584 | COMPLETED |  |  |  | 2025-09-28 | Maa Construction
260 | 25/0 | DD60+25 |  | 2025-08-28 | 161.3552 | COMPLETED |  |  |  | 2025-09-29 | Kongres Kumar-
261 | 64/3 | DA-3 |  | 2025-09-24 | 42.374 | COMPLETED |  |  |  | 2025-10-07 | Kongres Kumar-
262 | 54/0 | DB+3 |  | 2025-09-25 | 67.112 | COMPLETED |  |  |  | 2025-10-07 | Punam Kumari
263 | 46/0 | DB+0 |  | 2025-09-25 | 64.4817 | COMPLETED |  |  |  | 2025-10-08 | Amit Choudhry
264 | 63/0 | DC+3 |  | 2025-10-01 | 78.0732 | COMPLETED |  |  |  | 2025-10-12 | Mahon Mahto
265 | 27/0 | DD60+3 |  | 2025-09-22 | 101.692 | COMPLETED |  |  |  | 2025-10-12 | Reeta Bharti
266 | 53A/1 | DA+6 |  | 2025-09-18 | 53.3239 | COMPLETED |  |  |  | 2025-10-13 | Spotyfy-1
267 | 42/0 | DD60+18 |  | 2025-09-23 | 143.4621 | COMPLETED |  |  |  | 2025-10-14 | Ananya trader
268 | 50/0 | DC+18 |  | 2025-09-25 | 110.6958 | COMPLETED |  |  |  | 2025-10-14 | Punam kumari-1
269 | 53/0 | DC+0 |  | 2025-09-26 | 73.4258 | COMPLETED |  |  |  | 2025-10-14 | Sainik Trader
270 | 54/2 | DA-3 |  | 2025-10-08 | 42.3742 | COMPLETED |  |  |  | 2025-10-22 | Punam kumari-2
271 | 38/0 | DC+18 |  | 2025-10-07 | 110.6958 | COMPLETED |  |  |  | 2025-10-25 | Pankaj Kumar
272 | 0/0 | DCT+0 |  | 2025-10-03 | 97.8338 | COMPLETED |  |  |  | 2025-10-28 | Maa Construction
273 | 37/0 | DC+18 |  | 2025-09-23 | 110.6958 | COMPLETED |  |  |  | 2025-10-31 | Unity India
274 | 55/0 | DC+0 |  | 2025-10-23 | 73.4258 | COMPLETED |  |  |  | 2025-11-07 | Punam kumari-2
275 | 45/0 | DD60+0 |  | 2025-10-09 | 97.2286 | COMPLETED |  |  |  | 2025-11-07 | Amit Choudhry
276 | 52/1 | DB+6 |  | 2025-10-26 | 75.8584 | COMPLETED |  |  |  | 2025-11-10 | Pankaj Kumar
277 | 2/2 | DA+0 |  | 2025-10-31 | 43.7758 | COMPLETED |  |  |  | 2025-11-13 | Aloriva Global
278 | 61/0 | DD60+30 |  | 2025-09-25 | 188.3779 | COMPLETED |  |  |  | 2025-11-14 | Mahon mahto
279 | 56/6 | DA+0 |  | 2025-09-24 | 43.7758 | COMPLETED |  |  |  | 2025-11-15 | Pinky Dewi
280 | 55/1 | DA-3 |  | 2025-11-09 | 43.7758 | COMPLETED |  |  |  | 2025-11-17 | Punam kumari-2
281 | 69A/0 | DD60+0 |  | 2025-11-15 | 97.2286 | Under Progress |  |  |  |  | Mahon Mahto
282 | 49/0 | DC+9 |  | 2025-10-15 | 90.125 | Under Progress |  |  |  |  | Punam kumari-1
284 | 64/1 | DA+0 |  | 2025-11-06 | 43.7758 | Under Progress |  |  |  |  | Niranjan Singh
285 | 60/0 | DD45+6 |  | 2025-11-08 | 101.933 | Under Progress |  |  |  |  | Amit Choudhry
286 | 62/0 | DC+25 |  | 2025-11-10 | 124.037 | Under Progress |  |  |  |  | Pankaj Kumar
287 | 53A/0 | DB+0 |  | 2025-11-15 | 64.482 | Under Progress |  |  |  |  | Aloriva Global
288 | 66/0 | DD60+0 |  | 2025-11-15 | 97.2286 | Under Progress |  |  |  |  | Sarvesh Enterprises
289 | 59/0 | DD60+6 |  | 2025-11-16 | 113.68 | Under Progress |  |  |  |  | Pinky Dewi
290 | 23/0 | DC+18 |  | 2025-11-17 | 110.6958 | Under Progress |  |  |  |  | Punam kumari-3
291 | 53A/7 | DA+0 |  | 2025-11-18 | 43.7758 | Under Progress |  |  |  |  | Punam kumari-2
Stringing
S.No | Section | Length | Status |  |  |  | Gang Name | Gang Strength | Remarks
1 | AP7/0-AP8/0 | 4.8187 | COMPLETED |  |  |  | Anarul Islam
2 | AP6/0-AP7/0 | 1.2343 | COMPLETED |  |  |  | Anarul Islam
3 | AP35/0-AP36/0 | 3.9571 | COMPLETED |  |  |  | S K Infra
4 | AP8/0-AP8A/0 | 2.0167 | COMPLETED |  |  |  | Anarul Islam
5 | AP31/0-AP32/0 | 4.2837 | COMPLETED |  |  |  | S K Infra
6 | AP8A/0-AP8B/0 | 0.22361 | COMPLETED |  |  |  | Anarul Islam |  | PIPE LINE
7 | AP32/0-AP33/0 | 0.40717 | COMPLETED |  |  |  | S K Infra
8 | AP8B/0-AP9/0 | 2.2262 | COMPLETED |  |  |  | Anarul Islam
9 | AP33/0-AP34/0 | 4.7815 | COMPLETED |  |  |  | S K Infra
10 | AP5/0-AP6/0 | 0.72357 | COMPLETED |  |  |  | Anarul Islam
11 | AP9/0-AP10/0 | 0.28343 | COMPLETED |  |  |  | Anarul Islam |  | PLC
12 | AP34/0-AP35/0 | 3.1932 | COMPLETED |  |  |  | S K Infra
13 | AP4/0-AP5/0 | 4.4157 | COMPLETED |  |  |  | Anarul Islam
14 | AP14/0-AP15/0 | 3.611 | COMPLETED |  |  |  | Anarul Islam
15 | AP3/0-AP4/0 | 0.28 | COMPLETED |  |  |  | Anarul Islam |  | PLC
16 | AP30/0-AP31/0 | 2.75 | COMPLETED |  |  |  | S K Infra
17 | AP20/0-AP21/0 | 4.958 | COMPLETED |  |  |  | G P J con.
18 | AP36/0-AP37/0 | 4.947 | Rough sag completed |  |  |  | S K Infra
19 | AP12/0-AP13/0 | 3.919 | COMPLETED |  |  |  | Anarul Islam
20 | AP21/0-AP22/0 | 1.606 | COMPLETED |  |  |  | G P J con.
21 | AP39/0-AP40/0 | 4.431 | COMPLETED |  |  |  | S K Infra
22 | AP17/0-AP18/0 | 3.432 | Paying out WIP |  |  |  | Anarul Islam |  | ROW from 17.11.2025
23 | AP38/0-AP39/0 | 4.823 | Final sag wip |  |  |  | S K Infra |  | Gang left side for PGCIL request Chatri Narela line
24 | AP19/0-AP20/0 | 4.937 | COMPLETED |  |  |  | G P J con.
25 | AP13/0-AP14/0 | 0.31913 | COMPLETED |  |  |  | Anarul Islam |  | PLC
26 | AP18/0-AP19/0 | 0.323 | COMPLETED |  |  |  | G P J con. |  | Express way
27
28
OPGW Stringing
S.No | Section | Length in MTR | Status |  |  |  | Gang Name | Gang Strength | DRUM NO.
1 | 4/0-5/0 | 4415.75 | COMPLETED |  |  |  | B K CONSTRUCTION |  | DRUM-3 | 2025-10-14 | 2025-10-18
2 | 5/0-7/6 | 4340.94 | COMPLETED |  |  |  | B K CONSTRUCTION |  | DRUM-4 | 2025-10-22 | 2025-10-24
3 | 7/6-8B/0 | 4675.98 | COMPLETED |  |  |  | B K CONSTRUCTION |  | DRUM-5 | 2025-10-25 | 2025-10-26
4 | 34/0-35/0 | 3193.228 | COMPLETED |  |  |  | B K CONSTRUCTION |  | DRUM-17 | 2025-10-28 | 2025-10-31
5 | 35/0-36/0 | 3957.049 | COMPLETED |  |  |  | B K CONSTRUCTION |  | DRUM-18 | 2025-11-01 | 2025-11-03
6 | 33/0-34/0 | 4780.496 | COMPLETED |  |  |  | B K CONSTRUCTION |  | DRUM-16 | 2025-11-04 | 2025-11-06
7 | 31/0-33/0 | 4690.836 | COMPLETED |  |  |  | B K CONSTRUCTION |  | DRUM-15 | 2025-11-10 | 2025-11-13
8 | 30/0-31/0 | 2750.461 | COMPLETED |  |  |  | B K CONSTRUCTION |  | DRUM-14 | 2025-11-16 | 2025-11-18
9 | 12/0-14/0 | 4239.103 | COMPLETED |  |  |  | B K CONSTRUCTION | 14 | DRUM-7 | 2025-11-20 | 2025-11-22
37043.843

## Visual chart.
Visual Chart :- 765kV D/C Neemrana II Bareilly Transmission Line, WZ-05, TL-03
[8 empty] | Project Code : TA416 | [25 empty] | Dated: |  | 2025-11-25
[11 empty] | LEGEND: |  |  |  |  | OPGW Stringing | [7 empty] | Description of Item |  |  |  |  | Total Line Qty |  |  | Total Completed |  | WIP locations |  |  | Total Balance
|  |  |  | Stringing Comp | [12 empty] | Location No.
|  | Erection Comp | [16 empty] | Stringing WIP |  |  |  |  | Foundation |  |  |  |  | 302 |  |  | 302 |  | 0 |  |  | 0
[13 empty] | TW |  |  |  | Erection Comp | [6 empty] | Earthing |  |  |  |  | 302 |  |  | 302 |  |  |  |  | 0
|  | Foundation Comp | [7 empty] | C | B | SPAN |  | C | B | [8 empty] | Erection |  |  |  |  | 302 |  |  | 280 |  | 10 |  |  | 22
[10 empty] | D | A |  |  | D | A |  | Foundation Comp | [6 empty] | Tack Welding |  |  |  |  | 302 |  |  | 188 |  |  |  |  | 114
|  | Earthing Comp | [18 empty] | Holdup location |  |  | Stringing (Rough Sag) |  |  |  |  | 114.985 |  |  | 69.9746 |  | 6 |  |  | 45.0104
[24 empty] | Stringing (Final Sag) |  |  |  |  | 114.985 |  |  | 59.7285 |  | 10 |  |  | 55.2565
[5 empty] | Type of Tower |  |  |  |  | TREE CUTTING CLEARANCE
|  | NH/SH Xing |  |  |  | RAILWAY Xing | [6 empty] | 132/220/400/765 Kv CROSSING |  |  | RIVER X-ING |  |  |  | Gas pipeline
|  | OPGW DRUM-1 | [21 empty] | OPGW DRUM-2
[40 empty] | 115133.98 | 301
| 0/0 |  |  |  | 0/1 |  |  |  | 0/2 |  |  |  | 0/3 |  |  | 0/4 |  |  |  | 1/0 |  |  | 2/0 |  |  | 2/1 |  |  |  | 2/2 |  |  | 2/3 |  |  |  | 2/4
| C | B | 369 |  | C | B | 367 |  | C | B | 354 |  | C | B | 381 | C | B | 450.563 |  | C | B | 245.982 | C | B | 420 | C | B | 412 |  | C | B | 413 | C | B | 415 |  | C | B | 414 | 4241.545 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| TPT+0 |  |  |  | DA-3 |  |  |  | DA-3 |  |  |  | DA-3 |  |  | DA+9 |  |  |  | DC1+3 |  |  | DD45+3 |  |  | DA+3 |  |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+0
NH 509, Agra-Moradabad
| OPGW DRUM-2 | [19 empty] | OPGW DRUM-3
| 2/5 |  |  |  | 2/6 |  |  |  | 2/7 |  |  |  | 2/8 |  |  | 3/0 |  |  |  | 4/0 |  |  | 4/1 |  |  | 4/2 |  |  |  | 4/3 |  |  | 4/4 |  |  |  | 4/5
| C | B | 410 |  | C | B | 378 |  | C | B | 420 |  | C | B | 401.695 | C | B | 279.997 |  | C | B | 383.064 | C | B | 400.004 | C | B | 397.002 |  | C | B | 414 | C | B | 415 |  | C | B | 411 | 4309.762 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DA+0 |  |  |  | DA+3 |  |  |  | DA+0 |  |  | DC2+0 |  |  |  | DD45+0 |  |  | DA+3 |  |  | DA-3 |  |  |  | DA+3 |  |  | DA+0 |  |  |  | DA+3
[17 empty] | 220 KV SC Moradabad - Narora TL | [5 empty] | 2M RC in C&D Leg
132 KV DC LINE DISMANTLED
OPGW DRUM-3 | [20 empty] | OPGW DRUM-4
| 4/6 |  |  |  | 4/7 |  |  |  | 4/8 |  |  |  | 4/9 |  |  | 4/10 |  |  |  | 5/0 |  |  | 5/1 |  |  | 6/0 |  |  |  | 6/1 |  |  | 6/2 |  |  |  | 7/0
| C | B | 416 |  | C | B | 409.231 |  | C | B | 378.001 |  | C | B | 391 | C | B | 401.443 |  | C | B | 321 | C | B | 402.569 | C | B | 408 |  | C | B | 419 | C | B | 407.275 |  | C | B | 414 | 4367.519 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+0 |  |  |  | DA+3 |  |  |  | DA+0 |  |  |  | DA-3 |  |  | DA+3 |  |  |  | DB1+0 |  |  | DA+3 |  |  | DB1+0 |  |  |  | DA+3 |  |  | DA+3 |  |  |  | DB2+0
| OPGW DRUM-4 | [19 empty] | OPGW DRUM-5
| 7/1 |  |  |  | 7/2 |  |  |  | 7/3 |  |  |  | 7/4 |  |  | 7/5 |  |  |  | 7/6 |  |  | 7/7 |  |  | 7/8 |  |  |  | 7/9 |  |  | 7/10 |  |  |  | 7/11
| C | B | 419 |  | C | B | 361.097 |  | C | B | 361 |  | C | B | 404 | C | B | 424 |  | C | B | 406 | C | B | 410 | C | B | 423 |  | C | B | 409 | C | B | 425 |  | C | B | 362.65 | 4404.747 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+0 |  |  |  | DA+3 |  |  |  | DA-3 |  |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+0 |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+0
| OPGW DRUM-5 | [22 empty] | OPGW DRUM-6
| 8/0 |  |  |  | 8/1 |  |  |  | 8/2 |  |  |  | 8/3 |  |  | 8/4 |  |  |  | 8A/0 |  |  | 8B/0 |  |  | 8B/1 |  |  |  | 8B/2 |  |  | 8B/3 |  |  |  | 8B/4
| C | B | 416 |  | C | B | 400 |  | C | B | 367 |  | C | B | 420 | C | B | 413.716 |  | C | B | 223.61 | C | B | 341 | C | B | 332 |  | C | B | 292.526 | C | B | 426.186 |  | C | B | 373 | 4005.038 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DB2+0 |  |  |  | DA+3 |  |  |  | DA+0 |  |  |  | DA-3 |  |  | DA+9 |  |  |  | DD60+0 |  |  | DD60+0 |  |  | DA-3 |  |  |  | DA-3 |  |  | DA+3 |  |  |  | DA+6
GAIL GAS PIPE LINE
OPGW DRUM-6 | [20 empty] | OPGW DRUM-7
| 8B/5 |  |  |  | 9/0 |  |  |  | 10/0 |  |  |  | 10/1 |  |  | 11/0 |  |  |  | 12/0 |  |  | 12/1 |  |  | 12/2 |  |  |  | 12/3 |  |  | 12/4 |  |  |  | 12/5
| C | B | 461.51 |  | C | B | 283.431 |  | C | B | 426 |  | C | B | 396.092 | C | B | 312.879 |  | C | B | 418.999 | C | B | 370.199 | C | B | 424.996 |  | C | B | 404 | C | B | 428 |  | C | B | 395 | 4321.106 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+6 |  |  |  | DB2+6 |  |  |  | DB1+9 |  |  |  | DA-3 |  |  | DB1+18 |  |  |  | DB2+18 |  |  | DA-3 |  |  | DA+3 |  |  |  | DA+3 |  |  | DA+3 |  |  |  | DA+3
[6 empty] | 132 Kv S/C Sambhal-Babrala | [10 empty] | 132 KV D/C CKT-I Sambhal-Babrala
& CKT-II Sambhsal-Bisauli Line
OPGW DRUM-7 | [20 empty] | OPGW DRUM-8
| 12/6 |  |  |  | 12/7 |  |  |  | 12/8 |  |  |  | 12/9 |  |  | 13/0 |  |  |  | 14/0 |  |  | 14/1 |  |  | 14/2 |  |  |  | 14/3 |  |  | 14/4 |  |  |  | 14/5
| C | B | 318 |  | C | B | 357 |  | C | B | 385 |  | C | B | 418.776 | C | B | 319.133 |  | C | B | 436 | C | B | 395 | C | B | 306 |  | C | B | 412 | C | B | 414 |  | C | B | 420 | 4180.909 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA-3 |  |  |  | DA-3 |  |  |  | DA-3 |  |  |  | DA+3 |  |  | DD60+30 |  |  |  | DD60+30 |  |  | DA+0 |  |  | DA+0 |  |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+3
400 KV D/C Sambhal - Budaun Line
OPGW DRUM-8 | [20 empty] | OPGW DRUM-9
| 14/6 |  |  |  | 14/7 |  |  |  | 14/8 |  |  |  | 15/0 |  |  | 16/0 |  |  |  | 17/0 |  |  | 17/1 |  |  | 17/2 |  |  |  | 17/3 |  |  | 17/4 |  |  |  | 17/5
| C | B | 410 |  | C | B | 410 |  | C | B | 407.995 |  | C | B | 464.742 | C | B | 264.687 |  | C | B | 400 | C | B | 310 | C | B | 361.497 |  | C | B | 366.002 | C | B | 436.999 |  | C | B | 389.999 | 4221.921 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DA+0 |  |  |  | DA+3 |  |  |  | DC2+3 |  |  | DB2+25 |  |  |  | DB2+6 |  |  | DA-3 |  |  | DA+0 |  |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+3
[16 empty] | SH-51, Islamnagr- Bhajoi Road |  | 132 KV D/C Sahaswan-Chandausi
CGD INFRA GA LINE
OPGW DRUM-9 | [16 empty] | OPGW DRUM-10
| 17/6 |  |  |  | 17/7 |  |  |  | 17/8 |  |  |  | 18/0 |  |  | 19/0 |  |  |  | 19/1 |  |  | 19/2 |  |  | 19/3 |  |  |  | 19/4 |  |  | 19/5 |  |  |  | 19/6
| C | B | 400.999 |  | C | B | 391.999 |  | C | B | 374.07 |  | C | B | 323.03 | C | B | 343.13 |  | C | B | 392 | C | B | 407 | C | B | 412 |  | C | B | 371 | C | B | 376 |  | C | B | 421 | 4212.228 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA-3 |  |  |  | DA+3 |  |  |  | DA-3 |  |  |  | DB1+6 |  |  | DC2+6 |  |  |  | DA+0 |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+0 |  |  | DA-3 |  |  |  | DA+0
Ganga Express-way
OPGW DRUM-10 | [23 empty] | OPGW DRUM-11
| 19/7 |  |  |  | 19/8 |  |  |  | 19/9 |  |  |  | 19/10 |  |  | 19/11 |  |  |  | 19/12 |  |  | 20/0 |  |  | 20/1 |  |  |  | 20/2 |  |  | 20/3 |  |  |  | 20/4
| C | B | 387 |  | C | B | 364 |  | C | B | 423 |  | C | B | 335 | C | B | 343 |  | C | B | 362.453 | C | B | 433 | C | B | 393 |  | C | B | 400 | C | B | 375.659 |  | C | B | 366.466 | 4182.578 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DA-3 |  |  |  | DA+3 |  |  |  | DA+3 |  |  | DA-3 |  |  |  | DA-3 |  |  | DB1+0 |  |  | DA+6 |  |  |  | DA+0 |  |  | DA+0 |  |  |  | DA-3
OPGW DRUM-11 | [30 empty] | OPGW DRUM-12
| 20/5 |  |  |  | 20/6 |  |  |  | 20/7 |  |  |  | 20/8 |  |  | 20/9 |  |  |  | 20/10 |  |  | 20/11 |  |  | 20/12 |  |  |  | 21/0 |  |  | 21/1 |  |  |  | 21/2
| C | B | 408 |  | C | B | 372 |  | C | B | 370 |  | C | B | 400 | C | B | 426 |  | C | B | 399 | C | B | 358 | C | B | 256.857 |  | C | B | 388 | C | B | 391 |  | C | B | 394 | 4162.857 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DA+0 |  |  |  | DA-3 |  |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+3 |  |  | DA-3 |  |  | DA-3 |  |  |  | DB1+0 |  |  | DA-3 |  |  |  | DA+3
GAIL GAS PIPE LINE
OPGW DRUM-12 | [37 empty] | OPGW DRUM-13
| 21/3 |  |  |  | 22/0 |  |  |  | 22A/0 |  |  |  | 23/0 |  |  | 23/1 |  |  |  | 23/2 |  |  | 23/3 |  |  | 23/4 |  |  |  | 23/5 |  |  | 24/0 |  |  |  | 25/0
| C | B | 432.898 |  | C | B | 190.948 |  | C | B | 267.423 |  | C | B | 371 | C | B | 438.912 |  | C | B | 340.132 | C | B | 283.996 | C | B | 323 |  | C | B | 470.227 | C | B | 231.533 |  | C | B | 386 | 3736.069 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DB2+3 |  |  |  | DB1+25 |  |  |  | DC2+18 |  |  | DA+9 |  |  |  | DA+0 |  |  | DA-3 |  |  | DA-3 |  |  |  | DA-3 |  |  | DD60+25 |  |  |  | DD60+25
|  | SH-43, |  |  |  |  | 132 Kv S/C Budaun-Chandausi Dead line | [26 empty] | 765 KV S/C Ghatampur-Hapur
Chandausi - Badaun Road | [6 empty] | 132 Kv S/C Bisauli To Chandausi
OPGW DRUM-13 | [30 empty] | OPGW DRUM-14
| 25/1 |  |  |  | 25/2 |  |  |  | 25/3 |  |  |  | 26/0 |  |  | 27/0 |  |  |  | 28/0 |  |  | 28/1 |  |  | 29/0 |  |  |  | 30/0 |  |  | 30/1 |  |  |  | 30/2
| C | B | 446 |  | C | B | 368 |  | C | B | 466.431 |  | C | B | 440.836 | C | B | 299.473 |  | C | B | 233 | C | B | 454.669 | C | B | 270.08 |  | C | B | 435 | C | B | 347 |  | C | B | 396 | 4156.489 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+9 |  |  |  | DA+0 |  |  |  | DA+3 |  |  |  | DB2+9 |  |  | DD60+3 |  |  |  | DD60+0 |  |  | DA+3 |  |  | DD60+25 |  |  |  | DD60+18 |  |  | DA-3 |  |  |  | DA-3
[19 empty] | Rly Crossing Single track, Chandausi-Bareilly | [8 empty] | 765 Kv S/c Ghatampur-Rampur
OPGW DRUM-14 | [16 empty] | OPGW DRUM-15
| 30/3 |  |  |  | 30/4 |  |  |  | 30/5 |  |  |  | 30/6 |  |  | 31/0 |  |  |  | 31/1 |  |  | 31/2 |  |  | 31/3 |  |  |  | 31/4 |  |  | 31/5 |  |  |  | 31/6
| C | B | 410 |  | C | B | 424 |  | C | B | 373 |  | C | B | 365.461 | C | B | 376 |  | C | B | 403 | C | B | 399 | C | B | 404 |  | C | B | 358 | C | B | 363 |  | C | B | 407 | 4282.461 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+0 |  |  |  | DA+3 |  |  |  | DA+0 |  |  |  | DA-3 |  |  | DB2+0 |  |  |  | DA+0 |  |  | DA+0 |  |  | DA+3 |  |  |  | DA-3 |  |  | DA-3 |  |  |  | DA+3
OPGW DRUM-15 | [20 empty] | OPGW DRUM-16
| 31/7 |  |  |  | 31/8 |  |  |  | 31/9 |  |  |  | 31/10 |  |  | 32/0 |  |  |  | 33/0 |  |  | 33/1 |  |  | 33/2 |  |  |  | 33/3 |  |  | 33/4 |  |  |  | 33/5
| C | B | 384 |  | C | B | 386 |  | C | B | 394 |  | C | B | 409.666 | C | B | 407.17 |  | C | B | 365 | C | B | 365 | C | B | 406 |  | C | B | 389 | C | B | 395 |  | C | B | 430 | 4330.836 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+0 |  |  |  | DA-3 |  |  |  | DA+3 |  |  |  | DA-3 |  |  | DC1+6 |  |  |  | DC2+6 |  |  | DA-3 |  |  | DA-3 |  |  |  | DA+3 |  |  | DA-3 |  |  |  | DA+3
OPGW DRUM-16 | [23 empty] | OPGW DRUM-17
| 33/6 |  |  |  | 33/7 |  |  |  | 33/8 |  |  |  | 33/9 |  |  | 33/10 |  |  |  | 33/11 |  |  | 34/0 |  |  | 34/1 |  |  |  | 34/2 |  |  | 34/3 |  |  |  | 34/4
| C | B | 394 |  | C | B | 439.95 |  | C | B | 355.05 |  | C | B | 410 | C | B | 410 |  | C | B | 421.496 | C | B | 418 | C | B | 378 |  | C | B | 417 | C | B | 395 |  | C | B | 364 | 4402.496 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DA+3 |  |  |  | DA+3 |  |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+3 |  |  | DB1+0 |  |  | DA+3 |  |  |  | DA+3 |  |  | DA+3 |  |  |  | DA-3
OPGW DRUM-17 | [13 empty] | OPGW DRUM-18
| 34/5 |  |  |  | 34/6 |  |  |  | 34/7 |  |  |  | 35/0 |  |  | 35/1 |  |  |  | 35/2 |  |  | 35/3 |  |  | 35/4 |  |  |  | 35/5 |  |  | 35/6 |  |  |  | 35/7
| C | B | 397 |  | C | B | 419 |  | C | B | 405.228 |  | C | B | 383 | C | B | 397 |  | C | B | 345 | C | B | 389 | C | B | 416 |  | C | B | 414 | C | B | 415 |  | C | B | 404 | 4384.228 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+0 |  |  |  | DA+0 |  |  |  | DA+3 |  |  |  | DC1+0 |  |  | DA+3 |  |  |  | DA-3 |  |  | DA+0 |  |  | DA+0 |  |  |  | DA+3 |  |  | DA+0 |  |  |  | DA+3
SH-125
Shahabad-Aonla Road
OPGW DRUM-18 | [9 empty] | OPGW DRUM-19
| 35/8 |  |  |  | 35/9 |  |  |  | 36/0 |  |  |  | 36/1 |  |  | 36/2 |  |  |  | 36/3 |  |  | 36/4 |  |  | 36/5 |  |  |  | 36/6 |  |  | 36/7 |  |  |  | 36/8
| C | B | 373 |  | C | B | 421.049 |  | C | B | 401 |  | C | B | 412 | C | B | 415 |  | C | B | 411 | C | B | 395 | C | B | 402 |  | C | B | 432 | C | B | 392.011 |  | C | B | 352.989 | 4407.049 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA-3 |  |  |  | DA+3 |  |  |  | DB2+0 |  |  |  | DA+3 |  |  | DA+0 |  |  |  | DA+3 |  |  | DA+0 |  |  | DA+0 |  |  |  | DA+3 |  |  | DA+3 |  |  |  | DA-3
OPGW DRUM-19 | [16 empty] | OPGW DRUM-20
| 36/9 |  |  |  | 36/10 |  |  |  | 36/11 |  |  |  | 36/12 |  |  | 37/0 |  |  |  | 38/0 |  |  | 38/1 |  |  | 38/2 |  |  |  | 38/3 |  |  | 38/4 |  |  |  | 38/5
| C | B | 361 |  | C | B | 302 |  | C | B | 310 |  | C | B | 361.31 | C | B | 475.951 |  | C | B | 399 | C | B | 426 | C | B | 408 |  | C | B | 419 | C | B | 415 |  | C | B | 415.118 | 4292.379 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA-3 |  |  |  | DA-3 |  |  |  | DA-3 |  |  |  | DA+0 |  |  | DC2+18 |  |  |  | DC2+18 |  |  | DA+3 |  |  | DA+3 |  |  |  | DA+3 |  |  | DA+3 |  |  |  | DA+3
[16 empty] | 5 Mtr Depth |  |  |  |  | 5 Mtr Depth
Ramganga River Crossing
OPGW DRUM-20 | [20 empty] | OPGW DRUM-21
| 38/6 |  |  |  | 38/7 |  |  |  | 38/8 |  |  |  | 38/9 |  |  | 38/10 |  |  |  | 38/11 |  |  | 39/0 |  |  | 39/1 |  |  |  | 39/2 |  |  | 39/3 |  |  |  | 39/4
| C | B | 400 |  | C | B | 408.002 |  | C | B | 393 |  | C | B | 353 | C | B | 383 |  | C | B | 403.723 | C | B | 398 | C | B | 402 |  | C | B | 393.003 | C | B | 436.597 |  | C | B | 376.011 | 4346.336 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DA-3 |  |  |  | DA+3 |  |  |  | DA-3 |  |  | DA-3 |  |  |  | DA+3 |  |  | DB2+0 |  |  | DA+3 |  |  |  | DA-3 |  |  | DA+3 |  |  |  | DA+3
OPGW DRUM-21 | [23 empty] | OPGW DRUM-22
| 39/5 |  |  |  | 39/6 |  |  |  | 39/7 |  |  |  | 39/8 |  |  | 39/9 |  |  |  | 39/10 |  |  | 40/0 |  |  | 41/0 |  |  |  | 41/1 |  |  | 41/2 |  |  |  | 42/0
| C | B | 374.389 |  | C | B | 420.398 |  | C | B | 414.002 |  | C | B | 416.001 | C | B | 408.002 |  | C | B | 422.124 | C | B | 239.302 | C | B | 425 |  | C | B | 370 | C | B | 346.556 |  | C | B | 309.23 | 4145.004 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA-3 |  |  |  | DA+3 |  |  |  | DA+3 |  |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+0 |  |  | DD60+25 |  |  | DD60+18 |  |  |  | DA+0 |  |  | DA+3 |  |  |  | DD60+18
[23 empty] | 2 M RC |  |  | 2 M RC | [10 empty] | 220 KV S/C Rampur-CB Ganj
[23 empty] | 400 Kv D/C Bareilly-Meerut | [13 empty] | 400 KV S/C Bareilly-Moradabad
OPGW DRUM-22 | [33 empty] | OPGW DRUM-23
| 43/0 |  |  |  | 44/0 |  |  |  | 45/0 |  |  |  | 45/1 |  |  | 45/2 |  |  |  | 45/3 |  |  | 46/0 |  |  | 46/1 |  |  |  | 46/2 |  |  | 47/0 |  |  |  | 48/0
| C | B | 459.669 |  | C | B | 300.001 |  | C | B | 331 |  | C | B | 422 | C | B | 395 |  | C | B | 309.881 | C | B | 331 | C | B | 421 |  | C | B | 403.606 | C | B | 358.626 |  | C | B | 388 | 4119.783 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DD60+9 |  |  |  | DD60+3 |  |  |  | DD60+0 |  |  |  | DA+3 |  |  | DA+3 |  |  |  | DA-3 |  |  | DB2+0 |  |  | DA+0 |  |  |  | DA+3 |  |  | DC2+9 |  |  |  | DD45+9
| 2 M RC |  |  |  |  | NH-530, RAILWAY TRACK, | [27 empty] | 132 KV S/c CB Ganj-Meerganj
OPGW DRUM-23 | [23 empty] | OPGW DRUM-24
| 48/1 |  |  |  | 49/0 |  |  |  | 50/0 |  |  |  | 50/1 |  |  | 51/0 |  |  |  | 52/0 |  |  | 52/1 |  |  | 52/2 |  |  |  | 52/3 |  |  | 52/4 |  |  |  | 52/5
| C | B | 387.943 |  | C | B | 372.026 |  | C | B | 435 |  | C | B | 242.996 | C | B | 238.926 |  | C | B | 461 | C | B | 421 | C | B | 375 |  | C | B | 346 | C | B | 348 |  | C | B | 357 | 3984.891 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA-3 |  |  |  | DC2+9 |  |  |  | DC1+18 |  |  |  | DA+0 |  |  | DD60+0 |  |  |  | DC2+9 |  |  | DB1+6 |  |  | DA+3 |  |  |  | DA-3 |  |  | DA-3 |  |  |  | DA-3
[5 empty] | 132 KV D/C CB Ganj-Meerganj | [10 empty] | 132 KV D/C CB-GANJ - MEERGANJ T/L
OPGW DRUM-24 | [20 empty] | OPGW DRUM-25
| 52/6 |  |  |  | 52/7 |  |  |  | 52/8 |  |  |  | 52/9 |  |  | 52/10 |  |  |  | 53/0 |  |  | 53/1 |  |  | 53A/0 |  |  |  | 53A/1 |  |  | 53A/2 |  |  |  | 53A/3
| C | B | 439 |  | C | B | 378 |  | C | B | 349 |  | C | B | 392 | C | B | 409.43 |  | C | B | 428 | C | B | 403.778 | C | B | 370 |  | C | B | 441 | C | B | 375 |  | C | B | 399 | 4384.208 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DA+6 |  |  |  | DA-3 |  |  |  | DA-3 |  |  | DA+3 |  |  |  | DC1+0 |  |  | DA+6 |  |  | DB2+0 |  |  |  | DA+6 |  |  | DA+3 |  |  |  | DA-3
OPGW DRUM-25 | [16 empty] | OPGW DRUM-26
| 53A/4 |  |  |  | 53A/5 |  |  |  | 53A/6 |  |  |  | 53A/7 |  |  | 54/0 |  |  |  | 54/1 |  |  | 54/2 |  |  | 55/0 |  |  |  | 55/1 |  |  | 56/0 |  |  |  | 56/1
| C | B | 391 |  | C | B | 392 |  | C | B | 412 |  | C | B | 385.995 | C | B | 460 |  | C | B | 360 | C | B | 366.157 | C | B | 300 |  | C | B | 307.205 | C | B | 336 |  | C | B | 409 | 4119.357 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DA-3 |  |  |  | DA+3 |  |  |  | DA+0 |  |  | DB1+3 |  |  |  | DA+9 |  |  | DA-3 |  |  | DC1+0 |  |  |  | DA-3 |  |  | DD45+0 |  |  |  | DA+0
OPGW DRUM-26 | [16 empty] | OPGW DRUM-27
| 56/2 |  |  |  | 56/3 |  |  |  | 56/4 |  |  |  | 56/5 |  |  | 56/6 |  |  |  | 56/7 |  |  | 56/8 |  |  | 57/0 |  |  |  | 57/1 |  |  | 58/0 |  |  |  | 59/0
| C | B | 374 |  | C | B | 351 |  | C | B | 345 |  | C | B | 380.058 | C | B | 422 |  | C | B | 387.54 | C | B | 369 | C | B | 291 |  | C | B | 386.28 | C | B | 281.561 |  | C | B | 418.001 | 4005.44 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DA-3 |  |  |  | DA-3 |  |  |  | DA-3 |  |  | DA+0 |  |  |  | DA+6 |  |  | DA-3 |  |  | DB2+0 |  |  |  | DA-3 |  |  | DD60+18 |  |  |  | DD60+6
400 KV S/C BAREILLY - RAMPUR T/L
OPGW DRUM-27 | [16 empty] | OPGW DRUM-28
| 60/0 |  |  |  | 61/0 |  |  |  | 62/0 |  |  |  | 63/0 |  |  | 64/0 |  |  |  | 64/1 |  |  | 64/2 |  |  | 64/3 |  |  |  | 65/0 |  |  | 66/0 |  |  |  | 66/1
| C | B | 467.857 |  | C | B | 478.067 |  | C | B | 349.189 |  | C | B | 285.978 | C | B | 395 |  | C | B | 384 | C | B | 409 | C | B | 363.017 |  | C | B | 298.042 | C | B | 387 |  | C | B | 425.359 | 4242.509 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DD45+6 |  |  |  | DD60+30 |  |  |  | DC1+25 |  |  |  | DC1+3 |  |  | DC1+0 |  |  |  | DA+0 |  |  | DA+3 |  |  | DA-3 |  |  |  | DD60+0 |  |  | DD60+0 |  |  |  | DA+0
[9 empty] | 220 KV S/C BAIKUNTHAPUR - PANTNAGAR T/L |  | 132 KV S/C DOHNA - RICHHA T/L | [21 empty] | 1M RC in C&D Leg
OPGW DRUM-28 | [30 empty] | SH-37, ELECTRIFIED, SINGLE RAILWAY TRACK
Bareilly
| 67/0 |  |  |  | 68/0 |  |  |  | 69/0 |  |  |  | 69A/0 |  |  | 70/0 |  |  |  | Gantry
| C | B | 318.405 |  | C | B | 303.77 |  | C | B | 232.6 |  | C | B | 202.46 | C | B | 127 | [21 empty] | 1184.235 | 4
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A
| DD60+30 |  |  |  | DD60+30 |  |  |  | DC2+0 |  |  |  | DD60+0 |  |  | DD60+0 |  |  |  | Gantry
400 KV D/c Bareilly-Kasipur
TW

## PENDING FDN DETAILS
765kV D/C Neemrana II Bareilly Transmission Line, WZ-05, TL-03 ¦ BALANCE WORK DETAILS
Sl. No. | Loc. No. | Type of Tower | Village | Taluk | FDN STATUS | ROW STATUS | REMARKS
1
2
3
4
5
6
7
8
9
10
11
12

## PENDING ERE DETAILS
Sl. No. | Loc. No. | Type of Tower | FDN STATUS | ERE STATUS | ROW STATUS | REMARKS
1 | 22A/0 | DB1+25 | Completed | WIP
2 | 23/0 | DC2+18 | Completed
3 | 49/0 | DC2+9 | Completed | WIP
4 | 52/7 | DA+6 | Completed
5 | 53A/0 | DB2+0 | Completed | WIP
6 | 53A/7 | DA+0 | Completed | WIP
7 | 56/7 | DA+6 | Completed
8 | 57/0 | DB2+0 | Completed
9 | 57/1 | DA-3 | Completed
10 | 58/0 | DD60+18 | Completed
11 | 59/0 | DD60+6 | Completed | WIP
12 | 60/0 | DD45+6 | Completed | WIP
13 | 62/0 | DC1+25 | Completed | WIP
14 | 64/1 | DA+0 | Completed | WIP
15 | 64/2 | DA+3 | Completed
16 | 66/0 | DD60+0 | Completed | WIP
17 | 66/1 | DA+0 | Completed
18 | 67/0 | DD60+30 | Completed |  | ROW
19 | 68/0 | DD60+30 | Completed
20 | 69/0 | DC2+0 | Completed
21 | 69A/0 | DD60+0 | Completed | WIP
22 | 70/0 | DD60+0 | Completed

## TSE-MANUAL-LT-11KV-33KV Details
765kV D/C Neemrana II Bareilly Transmission Line, WZ-05, TL-03
Sl. No | SECTION |  | Section Length | No. Of Towers B/W Angle Towers | TSE Section (In KM) | Manual Section (In KM) | LT | 11KV | 33KV
| FROM | TO
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Crossing Details
KEC INTERNATIONAL LIMITED
NOA Supply: CC/T/W-TW/DOM/A10/23/10706/NOA-1/24-101862/01 dated 07.02.24.
NOA Services: CC/T/W-TW/DOM/A10/23/10706/NOA-2/24-101862/02 dated 07.02.24.
Contract: TL03 for Neemrana-II- Bareilly (PG) 765kV D/C line - Part III associated with “Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-1) (Bikaner Complex : 7.7GW) PART-D” through tariff based competitive bidding (TBCB) route.
STATUTORY CLEARANCE
POWER LINE CROSSING | [7 empty] | 2025-09-30
Name of the Transmission | Voltage Rating in kV | Name of Owner | Name of Nearest switching/ sub-station | (Crossing in Proposed Line Loc.No) | Proposal submission Date | Status | APPROVED Date | Remark
Moradabad To Narora | 220kv S/C & 132kv Dismental | UPPTCL |  | Loc.:-AP3 - AP4 | 2024-04-29 | Approved | 2024-07-19
Sambhal-Babrala | 132kV.S/C | UPPTCL |  | Loc.:-AP9 - AP10 | 2024-05-07 | Approved | 2024-07-18
CKT-I Sambhal-Babrala & CKT-II Sambhsal-Bisauli Line | 132kV.D/C | UPPTCL |  | Loc.:-AP11 - AP12 | 2024-05-07 | Approved | 2024-07-19
400 KV D/C Sambhal - Budaun Line | 400kV.D/C | PGCIL |  | Loc.:-AP13 - AP14 | 2024-05-07 | Approved | 2024-07-19
Sahaswan-Chandausi | 132kV.D/C | UPPTCL |  | Loc.:-AP16- AP17 | 2024-05-07 | Approved | 2024-09-30
Budaun-Chandausi Dead line & Bisauli To Chandaus | 132kv S/C dead line & 132kv S/C | UPPTCL |  | Loc.:-AP22 - AP22A | 2024-04-29 | Approved | 2025-01-23
Budaun-Sambhal | 220kV.S/C | UPPTCL |  | Loc.:-AP22A - AP23 | 2024-04-29 | Approved | 2024-09-10
Ghatampur-Hapur | 765kv S/C | PGCIL |  | Loc.:-AP24 - AP25 | 2024-04-29 | Approved | 2024-07-18
Ghatampur-Rampur | 765kv S/C | PGCIL |  | Loc.:-AP29 - AP30 | 2024-04-29 | Approved | 2024-07-18
Bareilly-Mandola | 400kV.D/C |  |  | Loc.:-AP40 - AP41 | 2024-08-07 | Approved | 2024-11-13
Lucknow-Moradabad and Rampur-CB Ganj | 400kv S/C & 220kv S/C | PGCIL & UPPTCL |  | Loc.:-AP42 - AP43 | 2024-07-29 | Approved | 2024-09-28
CB Ganj-Meerganj | 132kV.S/C | UPPTCL |  | Loc.:-AP47- AP48 | 2024-08-07 | Approved | 2024-09-28
CB Ganj-Meerganj | 132kV.D/C | UPPTCL |  | Loc.:-AP49 - AP50 | 2024-07-29 | Approved | 2024-09-28
Rampur-CB Ganj | 132kV.D/C | UPPTCL |  | Loc.:-AP51- AP52 | 2024-07-17 | Approved | 2024-09-28
Bareilly-Moradabad | 400kV.S/C | PGCIL |  | Loc.:-AP58 - AP59 | 2024-07-17 | Approved | 2024-09-28
220 KV S/C Line | 220kV.S/C | UPPTCL |  | Loc.:-AP61 - AP62 | 2024-07-17 | Approved | 2024-09-28
220 KV S/C Line | 220kV.S/C | UPPTCL |  | Loc.:-AP52 - AP63 | 2024-07-17 | Approved | 2024-09-28
Bareilly-Kasipur | 400kV.D/C | PGCIL |  | Loc.:-AP67 - AP68 | 2024-07-17 | Approved | 2024-09-28
RAILWAY CROSSING
Name of the Railway Line | Type of Gauge Broad/Metre/Narrow | Single/ Double Line | Electrified / Non-electrified | Crossing loc no of proposed line | Date of Submission | Status
| Broad Gauge | Single | Under construction | AP27-AP28 | 04.08.24 | Online submission done 15/08/24, | Approvaed | 2025-01-06
| Broad Gauge | Double |  | AP44-AP45 | 10.09.24 | Online submission done 12/09/24, | Approvaed | 2025-01-06
| Broad Gauge | Single | Electrified | AP65-AP66 | 11.10.24 | Online submission done 12/09/24, | Approvaed | 2025-02-07
NH/SH/EXPRESS WAY CROSSING
Name of the Highway Line | Type of NH | Nearest town | Nearest Village | Crossing loc no of proposed line | Date of Submission | Status
| NH-509 | Gunnaur | Kuravar | AP1-AP-2 | Submitted on 20.06.24, at Moradabad | Approved | 2025-04-04
| SH51 | Islam Nagar | Talen | AP15-AP16 | Submitted on 10.06.24, at Badaun | Approved | 2024-07-25
| Ganga Express-way |  | Padana | AP18-AP19 | Submitted at Lucknow on 03-07-24 | Approved | 2025-03-07
| SH-43 | Chandausi-Bisauli |  | 21/3-AP22 | Submitted | Approved | 2024-07-25
| SH-125 |  |  | 35/3-35/4 | Submitted on 17-07-24 | Approved | 2024-09-09
| NH-530 |  |  | AP44-AP45 | Submitted on 23-08-24 | Approved | 2025-03-25
| SH-37 |  |  | AP65-AP66 | Submitted on 29-07-24 | Approved | 2024-10-18
FOREST PROPOSAL
SL.NO. | Protected Forest | Crossing span/ area in Hac. | Detail survey submission by KEC | Planning for submission letter to DFO for joint inspection for confirmation of forest area | Date of Joint inspection with local forest department | Planning for submission of Document to powergrid from KEC | Date of proposal online submission to DFO from powergrid | Date of Joint inspection with DFO | DFO to Nodal lucknow for approval | Remark
1 | AP-1/0 to AP-2/0 | 0.1742 | completed | Submitted on 13-03-2024 | Completed | Submitted to PGCIL |  |  |  | DFO not given CA land KMZ file
2 | 21/3 to AP-22/0 | 0.2594 | completed | Submitted on 13-03-2024 | Completed | Submitted to PGCIL |  |  |  | CA land DGPS map submitted to Concern DFO
3 | AP-44/0 to AP-45/0 | 0.161 | completed | Submitted on 13-03-2024 | Completed | Submitted to PGCIL |  |  |  | Letter given to DFO Badaun for CA land of Bareilly section
4 | AP-52/0 to AP-53/0 | 0.1245 | completed | Submitted on 13-03-2024 | Completed | Submitted to PGCIL
5 | AP-65/0 to AP-66/0 | 0.1038 | completed | Submitted on 13-03-2024 | Completed | Submitted to PGCIL
Total PF |  | 0.8229
Scheduled for statuary clearance: Gas Pipe Line
SL.NO. | Location | Type Tower | Location | Type Tower | Submission Date | Submission from PGCIL GAS PIPE LINE AUTHORITY | Aproved Date | Clearance / NOC | Remark
1 | AP8A/0 | DD60+0 | AP8B/0 | DD60+0 | 2024-08-08 | Online submission done on 15/09/24 | 2025-01-27 | NOC 27-01-25 | GAIL
2 | 20/10 | DA+3 | 20/11 | DA-3 | 2024-07-30 |  | 2025-05-05 | NOC 05-05-25 | GAIL

## TS (hidden)
Name of the Line :765kV D/C KOPPAL II(PS) - RAICHUR (Part-1) TRANSMISSION LINE
Sl.No | Loc. No. (Provisional) | Type of Tower | Span (Mtr)
1 | AP32 | 1DC2+6 | 249.635 | 32/0-33/0
[5 empty] | -0 | -1.5 | -3 | -4.5 | -6 | +0 | +1.5 | +3 | +4.5 | +6 | +9 | +18 | Total
2 | AP33 | 1DD45+18 | 425 | 1DA | 0 | 10 | 7 | 3 | 1 | 26 | 2 | 21 | 2 | 8 | 6 | 0 | 86
|  |  |  | 1DB1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 2 | 0 | 1 | 5 | 0 | 14 | 113 | AP57 | 1DC2+6 | 57/0 | 1DC1+3 | 73.125
3 | 33/1 | 1DA-3 | 425 | 1DB2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 2 | 0 | 7
|  |  |  | 1DC1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 0 | 6 | 114 | 57/1 | 1DA+0 | 57/1 | 1DA+0 | 71.43
4 | 33/2 | 1DA+6 | 390 | 1DC2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 6
|  |  |  | 1DD45 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 115 | 57/2 | 1DA+6 | 57/2 | 1DA+0 | 71.43
5 | 33/3 | 1DA+9 | 265 | 1DD60 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3
[5 empty] | 0 | 10 | 7 | 3 | 1 | 42 | 2 | 28 | 2 | 14 | 14 | 1 | 124 | 116 | 57/3 | 1DA+0 | 57/3 | 1DA-3 | 68.43
6 | 33/4 | 1DA+3 | 510
[18 empty] | 117 | 57/4 | 1DA+3 | 58/0 | 1DD60+6 | 76.525
7 | 33/5 | 1DB1+9 | 380
[18 empty] | 118 | AP58 | 1DD45+0 | 59/0 | 1DD60+6 | 76.525
8 | 33/6 | 1DB1+9 | 420
[18 empty] | 119 | 58/1 | 1DA-1.5 | 59/1 | 1DA-3 | 68.43
9 | 33/7 | 1DA-3 | 335
[5 empty] | -0 | -1.5 | -3 | -4.5 | -6 | +0 | +1.5 | +3 | +4.5 | +6 | +9 | +18 | Total | 120 | AP59 | 1DB2+3 | 60/0 | 1DC2+0 | 70.125
10 | 33/8 | 1DA-3 | 345 | 1DA | 0 | 2 | 18 | 0 | 0 | 37 | 0 | 19 | 0 | 7 | 6 | 0 | 89
|  |  |  | 1DB1 | 0 | 0 | 1 | 0 | 0 | 7 | 0 | 1 | 0 | 2 | 4 | 0 | 15 | 121 | AP60 | 1DD60+0 | 60/1 | 1DA+6 | 77.43
11 | 33/9 | 1DA-3 | 365 | 1DB2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 1 | 0 | 4
|  |  |  | 1DC1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 3 | 0 | 1 | 0 | 0 | 7 | 122 | GANTRY | GANTRY | 60/2 | 1DA+0 | 71.43
12 | 33/10 | 1DA+0 | 356 | 1DC2 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 2 | 0 | 0 | 6
|  |  |  | 1DD45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2 |  |  |  | 60/3 | 1DA+0 | 71.43
13 | 33/11 | 1DA-3 | 332 | 1DD60 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 4
[5 empty] | 0 | 2 | 20 | 0 | 0 | 52 | 0 | 26 | 0 | 15 | 11 | 1 | 127 |  |  |  | 60/4 | 1DA-1.5 | 69.93
14 | 33/12 | 1DA+0 | 384.424
[21 empty] | 61/0 | 1DD45+6 | 76.525
15 | AP34 | 1DB1+0 | 385
[21 empty] | AP-62 | DD60
16 | 34/1 | 1DA+0 | 423
[21 empty] | AP-63 | DD60
17 | 34/2 | 1DA+0 | 382
18 | 34/3 | 1DA+0 | 405
19 | 34/4 | 1DA+3 | 388.458
20 | AP35 | 1DB1+0 | 405
21 | 35/1 | 1DA+3 | 360
22 | 35/2 | 1DA+3 | 390
23 | 35/3 | 1DA-3 | 325
24 | 35/4 | 1DA+0 | 430
25 | 35/5 | 1DA+0 | 298
26 | 35/6 | 1DA+0 | 422
27 | 35/7 | 1DA+9 | 345
28 | 35/8 | 1DA+3 | 370
29 | 35/9 | 1DA+9 | 320
30 | 35/10 | 1DA+9 | 390
31 | 35/11 | 1DA+3 | 425.02
32 | AP36 | 1DB1+3 | 480
33 | 36/1 | 1DB1+9 | 297.315
34 | AP37 | 1DB2+3 | 417
35 | 37/1 | 1DA+3 | 409
36 | 37/2 | 1DA+0 | 432.782
37 | AP38 | 1DD60+6 | 469
38 | 38/1 | 1DA+9 | 387
39 | 38/2 | 1DA+0 | 428.876
40 | AP39 | 1DD45+18 | 248.038
41 | AP40 | 1DB2+9 | 430
42 | 40/1 | 1DA+0 | 400
43 | 40/2 | 1DA+0 | 410
44 | 40/3 | 1DA+3 | 435
45 | 40/4 | 1DA+0 | 360
46 | 40/5 | 1DA-3 | 391.451
47 | AP41 | 1DB1+0 | 380
48 | 41/1 | 1DA+6 | 475
49 | 41/2 | 1DA+3 | 380
50 | 41/3 | 1DA+0 | 390
51 | 41/4 | 1DA+3 | 465
52 | 41/5 | 1DA+3 | 383.208
53 | AP42 | 1DB2+3 | 380
54 | 42/1 | 1DA+0 | 348
55 | 42/2 | 1DA+0 | 377.784
56 | AP43 | 1DB1+0 | 410
57 | 43/1 | 1DA+0 | 380
58 | 43/2 | 1DA+0 | 325
59 | 43/3 | 1DA-3 | 329.8
60 | AP44 | 1DC1-3 | 385
61 | 44/1 | 1DA+0 | 312.558
62 | AP45 | 1DC1+3 | 242
63 | 45/1 | 1DB1+6 | 464
64 | 45/2 | 1DA+0 | 391
65 | 45/3 | 1DA+6 | 417.518
66 | AP46 | 1DB1+0 | 315
67 | 46/1 | 1DA-3 | 375
68 | 46/2 | 1DA+0 | 416
69 | 46/3 | 1DA+0 | 422
70 | 46/4 | 1DA+0 | 388
71 | 46/5 | 1DA+6 | 409
72 | 46/6 | 1DA+0 | 420
73 | 46/7 | 1DB1+0 | 399
74 | 46/8 | 1DA+3 | 381
75 | 46/9 | 1DA+0 | 382
76 | 46/10 | 1DA+0 | 391
77 | 46/11 | 1DA-1.5 | 433
78 | 46/12 | 1DA+0 | 415
79 | 46/13 | 1DA+0 | 430
80 | 46/14 | 1DA+0 | 314
81 | 46/15 | 1DA+9 | 402.249
82 | AP47 | 1DC1+0 | 394
83 | 47/1 | 1DA+3 | 419.445
84 | AP48 | 1DB2+0 | 402
85 | 48/1 | 1DA+6 | 426
86 | 48/2 | 1DA+3 | 429.059
87 | AP48A | 1DC1+0 | 336
88 | 48A/1 | 1DA+9 | 441
89 | 48A/2 | 1DA-1.5 | 324.049
90 | AP49 | 1DC1+3 | 417.219
91 | AP50 | 1DC1+0 | 249.602
92 | AP51 | 1DB1-3 | 333.602
93 | AP52 | 1DC2+0 | 313
94 | 52/1 | 1DA-3 | 337
95 | 52/2 | 1DA-3 | 384.098
96 | AP53 | 1DC2+6 | 258.616
97 | AP54 | 1DC1+6 | 390
98 | 54/1 | 1DA-3 | 290
99 | 54/2 | 1DA-3 | 345
100 | 54/3 | 1DA+3 | 423
101 | 54/4 | 1DA+0 | 388.693
102 | AP55 | 1DB2+0 | 405
103 | 55/1 | 1DA+3 | 385
104 | 55/2 | 1DA+0 | 366
105 | 55/3 | 1DA+3 | 444
106 | 55/4 | 1DA+3 | 355
107 | 55/5 | 1DA+0 | 375
108 | 55/6 | 1DA-3 | 374.49
109 | AP56 | 1DB1+0 | 434
110 | 56/1 | 1DA+6 | 406
111 | 56/2 | 1DA-3 | 390
112 | 56/3 | 1DB1+6 | 276.492
113 | AP57 | 1DC1+6 | 397
114 | 57/1 | 1DA-1.5 | 380
115 | 57/2 | 1DA+0 | 342
116 | 57/3 | 1DA-3 | 416.81
117 | AP58 | 1DD60+6 | 203.902
118 | AP59 | 1DD60+6 | 382
119 | 59/1 | 1DA-3 | 320.796
120 | AP60 | 1DC2+0 | 414
121 | 60/1 | 1DA+6 | 425
122 | 60/2 | 1DA+0 | 373
123 | 60/3 | 1DA+0 | 357
124 | 60/4 | 1DA+0 | 372.201
125 | AP61 | 1DC2+0 | 358.086
126 | AP62 | 1DD60+0 | 278.704
127 | AP63 | 1DD60+0 | 135.008
47836.988
| Koppal-II Gantry | GANTRY

## TS (2) (hidden)
Name of the Line :765kV D/C KOPPAL II(PS) - RAICHUR (Part-1) TRANSMISSION LINE
Sl.No | Loc. No. (Provisional) | Type of Tower | Span (Mtr)
1 | AP32 | 1DC2+6 | 249.635 | 32/0-33/0
[5 empty] | -0 | -1.5 | -3 | -4.5 | -6 | +0 | +1.5 | +3 | +4.5 | +6 | +9 | +18 | Total
2 | AP33 | 1DD45+18 | 425 | 1DA | 0 | 3 | 18 | 0 | 0 | 34 | 0 | 19 | 0 | 7 | 6 | 0 | 87 | 2
|  |  |  | 1DB1 | 0 | 0 | 1 | 0 | 0 | 7 | 0 | 1 | 0 | 1 | 4 | 0 | 14 | 0 | 113 | AP57 | 1DC2+6 | 57/0 | 1DC1+3 | 73.125
3 | 33/1 | 1DA-3 | 425 | 1DB2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 1 | 0 | 4 | 0
|  |  |  | 1DC1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 7 | 0 | 114 | 57/1 | 1DA+0 | 57/1 | 1DA+0 | 71.43
4 | 33/2 | 1DA+6 | 390 | 1DC2 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 2 | 0 | 0 | 6 | 1
|  |  |  | 1DD45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 115 | 57/2 | 1DA+6 | 57/2 | 1DA+0 | 71.43
5 | 33/3 | 1DA+9 | 265 | 1DD60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 2
[5 empty] | 0 | 3 | 20 | 0 | 0 | 47 | 0 | 25 | 0 | 14 | 11 | 2 | 122 |  | 116 | 57/3 | 1DA+0 | 57/3 | 1DA-3 | 68.43
6 | 33/4 | 1DA+3 | 510
[19 empty] | 117 | 57/4 | 1DA+3 | 58/0 | 1DD60+6 | 76.525
7 | 33/5 | 1DB1+9 | 380
[19 empty] | 118 | AP58 | 1DD45+0 | 59/0 | 1DD60+6 | 76.525
8 | 33/6 | 1DB1+9 | 420
[19 empty] | 119 | 58/1 | 1DA-1.5 | 59/1 | 1DA-3 | 68.43
9 | 33/7 | 1DA-3 | 335
[5 empty] | -0 | -1.5 | -3 | -4.5 | -6 | +0 | +1.5 | +3 | +4.5 | +6 | +9 | +18 | Total |  | 120 | AP59 | 1DB2+3 | 60/0 | 1DC2+0 | 70.125
10 | 33/8 | 1DA-3 | 345 | 1DA | 0 | 4 | 18 | 0 | 0 | 35 | 0 | 19 | 0 | 7 | 6 | 0 | 89
|  |  |  | 1DB1 | 0 | 0 | 1 | 0 | 0 | 7 | 0 | 1 | 0 | 1 | 4 | 0 | 14 |  | 121 | AP60 | 1DD60+0 | 60/1 | 1DA+6 | 77.43
11 | 33/9 | 1DA-3 | 365 | 1DB2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 1 | 0 | 4
|  |  |  | 1DC1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 7 |  | 122 | GANTRY | GANTRY | 60/2 | 1DA+0 | 71.43
12 | 33/10 | 1DA+0 | 356 | 1DC2 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 3 | 0 | 0 | 7
|  |  |  | 1DD45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 |  |  |  |  | 60/3 | 1DA+0 | 71.43
13 | 33/11 | 1DA-3 | 332 | 1DD60 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 4
[5 empty] | 0 | 4 | 20 | 0 | 0 | 50 | 0 | 25 | 0 | 15 | 11 | 2 | 127 |  |  |  |  | 60/4 | 1DA-1.5 | 69.93
14 | 33/12 | 1DA+0 | 384.424
[22 empty] | 61/0 | 1DD45+6 | 76.525
15 | AP34 | 1DB1+0 | 385
[22 empty] | AP-62 | DD60
16 | 34/1 | 1DA+0 | 423
[22 empty] | AP-63 | DD60
17 | 34/2 | 1DA+0 | 382
18 | 34/3 | 1DA+0 | 405
19 | 34/4 | 1DA+3 | 388.458
20 | AP35 | 1DB1+0 | 405
21 | 35/1 | 1DA+3 | 360
22 | 35/2 | 1DA+3 | 390
23 | 35/3 | 1DA-3 | 325
24 | 35/4 | 1DA+0 | 430
25 | 35/5 | 1DA+0 | 298
26 | 35/6 | 1DA+0 | 422
27 | 35/7 | 1DA+9 | 345
28 | 35/8 | 1DA+3 | 370
29 | 35/9 | 1DA+9 | 320
30 | 35/10 | 1DA+9 | 390
31 | 35/11 | 1DA+3 | 425.02
32 | AP36 | 1DB1+3 | 480
33 | 36/1 | 1DB1+9 | 297.315
34 | AP37 | 1DC2+3 | 415
35 | 37/1 | 1DA+3 | 425
36 | 37/2 | 1DA+3 | 395
37 | 37/3 | 1DA-3 | 329.074
38 | AP38 | 1DC2+0 | 390
39 | 38/1 | 1DA+3 | 444.771
40 | AP39 | 1DD45+18 | 248.038
41 | AP40 | 1DB2+9 | 430
42 | 40/1 | 1DA+0 | 400
43 | 40/2 | 1DA+0 | 410
44 | 40/3 | 1DA+3 | 435
45 | 40/4 | 1DA+0 | 360
46 | 40/5 | 1DA-3 | 391.451
47 | AP41 | 1DB1+0 | 380
48 | 41/1 | 1DA+6 | 475
49 | 41/2 | 1DA+3 | 380
50 | 41/3 | 1DA+0 | 390
51 | 41/4 | 1DA+3 | 465
52 | 41/5 | 1DA+3 | 383.208
53 | AP42 | 1DB2+3 | 380
54 | 42/1 | 1DA+0 | 348
55 | 42/2 | 1DA+0 | 377.784
56 | AP43 | 1DB1+0 | 410
57 | 43/1 | 1DA+0 | 380
58 | 43/2 | 1DA+0 | 325
59 | 43/3 | 1DA-3 | 329.8
60 | AP44 | 1DC1-3 | 385
61 | 44/1 | 1DA+0 | 312.558
62 | AP45 | 1DC1+3 | 242
63 | 45/1 | 1DB1+6 | 464
64 | 45/2 | 1DA+0 | 391
65 | 45/3 | 1DA+6 | 417.518
66 | AP46 | 1DB1+0 | 315
67 | 46/1 | 1DA-3 | 375
68 | 46/2 | 1DA+0 | 416
69 | 46/3 | 1DA+0 | 422
70 | 46/4 | 1DA+0 | 388
71 | 46/5 | 1DA+6 | 409
72 | 46/6 | 1DA+0 | 420
73 | 46/7 | 1DB1+0 | 399
74 | 46/8 | 1DA+3 | 381
75 | 46/9 | 1DA+0 | 382
76 | 46/10 | 1DA+0 | 391
77 | 46/11 | 1DA-1.5 | 433
78 | 46/12 | 1DA+0 | 415
79 | 46/13 | 1DA+0 | 430
80 | 46/14 | 1DA+0 | 314
81 | 46/15 | 1DA+9 | 402.249
82 | AP47 | 1DC1+0 | 400
83 | 47/1 | 1DA+3 | 435
84 | AP48 | 1DC1+3 | 345
85 | 48/1 | 1DA+0 | 410
86 | 48/2 | 1DA+0 | 410
87 | 48/3 | 1DA-1.5 | 320
88 | 48/4 | 1DA+6 | 400
89 | 48/5 | 1DA+9 | 410.1
90 | AP49 | 1DB2+3 | 417.219
91 | AP50 | 1DC1+0 | 249.602
92 | AP51 | 1DB1-3 | 333.602
93 | AP52 | 1DC2+0 | 313
94 | 52/1 | 1DA-3 | 337
95 | 52/2 | 1DA-3 | 384.098
96 | AP53 | 1DC2+6 | 258.616
97 | AP54 | 1DC1+6 | 390
98 | 54/1 | 1DA-3 | 290
99 | 54/2 | 1DA-3 | 345
100 | 54/3 | 1DA+3 | 423
101 | 54/4 | 1DA+0 | 388.693
102 | AP55 | 1DB2+0 | 405
103 | 55/1 | 1DA+3 | 385
104 | 55/2 | 1DA+0 | 366
105 | 55/3 | 1DA+3 | 444
106 | 55/4 | 1DA+3 | 355
107 | 55/5 | 1DA+0 | 375
108 | 55/6 | 1DA-3 | 374.49
109 | AP56 | 1DB1+0 | 434
110 | 56/1 | 1DA+6 | 406
111 | 56/2 | 1DA-3 | 390
112 | 56/3 | 1DB1+9 | 276.492
113 | AP57 | 1DC1+6 | 397
114 | 57/1 | 1DA-1.5 | 380
115 | 57/2 | 1DA+0 | 342
116 | 57/3 | 1DA-3 | 416.81
117 | AP58 | 1DD60+6 | 203.902
118 | AP59 | 1DD60+6 | 382
119 | 59/1 | 1DA-3 | 320.796
120 | AP60 | 1DC2+0 | 414
121 | 60/1 | 1DA+6 | 425
122 | 60/2 | 1DA+0 | 373
123 | 60/3 | 1DA+0 | 357
124 | 60/4 | 1DA-1.5 | 402.199
125 | AP61 | 1DC2+6 | 419
126 | AP62 | 1DD60+0 | 231
127 | AP63 | 1DD60+0 | 103
47661.922
GANTRY