## DPR
±800kV HVDC BIPOLE LINE (HEX LAPWING) BETWEEN KPS2 (HVDC) & NAGPUR (HVDC) (WITH DMR), TRANSMISSION LINE PACKAGE- 03
Daily Progress Report | [8 empty] | 2026-06-15
Sl. | Description | L2 / Actual | UOM | Total Qty | Progress upto May'26 | Todays Progress | Progress for current month (Jun'26) | Total Cum. progress since inception | Remarks
1 | Route Alignment | L2 (Plan) | KM | 83.14 | 83.14 | - | - | 83.14 | Route Alignment approved (100%)
|  | Actual |  | 83.331 | 83.331 | - | - | 83.331
2 | Detailed Survey | L2 (Plan) | KM | 83.14 | 83.14 | - | - | 83.14 | Detail survey completed. Profile submitted & approval received of 83.331 KM (100%)
|  | Actual |  | 83.331 | 83.331 | - | - | 83.331
3 | Check Survey | L2 (Plan) | KM | 83.14 | 83.14 | - | - | 83.14 | Check survey done. Report submitted & approval received for 83.331 km (100%). Land Schedule & Tree enumeration report submitted (100%)
|  | Actual |  | 83.331 | 83.331 | - | - | 83.331
4 | Soil Investigation | L2 (Plan) | Nos | 17 | 17 | - | - | 17 | Activity completed - 12 nos (100%), Report submitted - 12 nos (100%)
|  | Actual |  | 12 | 12 | - | - | 12
5 | Foundation | L2 (Plan) | Nos | 215 | 96 | - | 10 | 106 | Since inception completed - 17 location, 233/4, 241/2, 233/5 Completed(June). WIP - 233/7 (Frustum & Stepbox casting of Pit-B,C,D Completed). 233/6 (Exc. Work U/P.). Next Loc - 232/2, 223/8.
|  | Actual |  | 217 | 14 | - | 3 | 17
6 | Earthing | L2 (Plan) | Nos | 215 | 96 | - | 10 | 106 | Earthing Completed in m/o June: 241/2, 233/4, 233/5.
|  | Actual |  | 217 | 14 | - | 3 | 17
7 | Erection | L2 (Plan) | Nos | 215 | 72 | - | 12 | 84 | Completed Location no. 232/3, 194/9
|  | Actual |  | 217 | 2 | - | - | 2
8 | Stringing | L2 (Plan) | KM | 83.14 | 11 | - | 2 | 13
|  | Actual |  | 83.331 | - | - | - | -

## Foundation Compiled
Project : ±800kV HVDC BIPOLE LINE (HEX LAPWING) BETWEEN KPS2 (HVDC) & NAGPUR (HVDC) (WITH DMR), TRANSMISSION LINE PACKAGE- 03
Foundation Status | [11 empty] | 2026-06-15
Sl | Loc No. | Wind Zone | Type of Tower | Concrete Cum | Classification | Date of Excavation Start | Date of RCC Start | Date of Completion | Ageing | Status | Name of the Gang | Remarks
1 | 194/9 | WZ-5 NC | A+0 | 27.36 | DFR | 2025-08-05 | 2025-08-20 | 2025-08-21 | 16 | Completed | Oppulence Tenchnologies
2 | 198/1 | WZ-5 NC | A+0 | 27.36 | DFR | 2025-08-25 | 2025-08-30 | 2025-09-01 | 7 | Completed | Oppulence Tenchnologies
3 | 205/1 | WZ-5 NC | A+3 | 30.94 | DFR | 2025-09-05 | 2025-09-12 | 2025-09-14 | 9 | Completed | Oppulence Tenchnologies
4 | 194/1 | WZ-5 NC | A+0 | 42.97 | WFR | 2025-09-19 | 2025-09-27 | 2025-10-08 | 19 | Completed | Oppulence Tenchnologies
5 | 232/4 | WZ-5 NC | A+0 | 42.97 | WFR | 2025-11-02 | 2025-11-18 | 2025-11-20 | 18 | Completed | Jay Dada Enterprises
6 | 232/2 | WZ-5 NC | A+0 | 42.97 | WFR | 2025-11-17 |  |  |  | ROW | Jay Dada Enterprises | ROW
7 | 232/3 | WZ-5 NC | A+0 | 42.97 | WFR | 2025-11-23 | 2025-11-28 | 2025-11-30 | 7 | Completed | Jay Dada Enterprises
8 | 223/4 | WZ-5 NC | A+0 | 27.36 | DFR | 2025-11-25 |  |  |  | ROW | Sada Shiv Enterprises | ROW
9 | 217/5 | WZ-5 NC | A+3 | 44.81 | WFR | 2025-12-07 | 2025-12-13 | 2025-12-15 | 8 | Completed | Jay Dada Enterprises
10 | 221/1 | WZ-5 NC | A+6 | 44.81 | WFR | 2025-12-02 |  |  |  | ROW | Jay Dada Enterprises | ROW
11 | 217/6 | WZ-5 NC | A+0 | 46.54 | WET | 2025-12-16 | 2025-12-25 | 2025-12-26 | 10 | Completed | Jay Dada Enterprises
12 | 245/2 | WZ-5 NC | A+3 | 48.22 | WET | 2026-04-10 | 2026-05-03 | 2026-05-06 | 26 | Completed | Jay Dada Enterprises
13 | 243/2 | WZ-5 NC | A+0 | 46.54 | WET | 2026-04-24 | 2026-05-13 | 2026-05-15 | 21 | Completed | Vaibhavi Enterprises
14 | 241/3 | WZ-5 NC | A+0 | 27.36 | DFR | 2026-05-10 | 2026-05-10 | 2026-05-17 | 7 | Completed | Jay Dada Enterprises
15 | 243/1 | WZ-5 NC | A+0 | 46.54 | WET | 2026-05-16 | 2026-06-25 | 2026-05-26 | 10 | Completed | Vaibhavi Enterprises
16 | 233/3 | WZ-5 NC | A+0 | 26.6 | WC | 2026-05-19 | 2026-05-23 | 2026-05-24 | 5 | Completed | Jay Dada Enterprises
17 | 233/2 | WZ-5 NC | A+0 | 46.54 | WET | 2026-05-23 | 2026-05-28 | 2026-05-29 | 6 | Completed | Jay Dada Enterprises
18 | 241/2 | WZ-5 NC | A+0 | 42.97 | WFR | 2026-05-25 | 2026-06-07 | 2026-06-08 | 14 | Completed | Vaibhavi Enterprises
19 | 233/4 | WZ-5 NC | A+0 | 46.54 | WET | 2026-05-28 | 2026-06-03 | 2026-06-07 | 10 | Completed | Jay Dada Enterprises
20 | 233/5 | WZ-5 NC | A+0 | 46.54 | WET | 2026-06-04 | 2026-06-09 | 2026-06-10 | 6 | Completed | Jay Dada Enterprises
21 | 233/7 | WZ-5 NC | A+0 | 46.54 | WET | 2026-06-11 |  |  |  | WIP | Jay Dada Enterprises | Frustum & Stepbox casting of Pit-B,C,D Completed.
22 | 233/6 | WZ-5 NC | A+3 | 48.22 | WET | 2026-06-14 |  |  |  | WIP | Jay Dada Enterprises | Exc. Work U/P.
[6 empty] | Total | Completed | WIP
[6 empty] | 217 | 17 | 2

## Earthing
Project : ±800kV HVDC BIPOLE LINE (HEX LAPWING) BETWEEN KPS2 (HVDC) & NAGPUR (HVDC) (WITH DMR), TRANSMISSION LINE PACKAGE- 03
Status Of Earthing | [9 empty] | 2026-06-15
Sl. | Location No. | Type Of Tower | Classification | Resistance in Ω |  | Type Of Earthing | Date of FDN Completion | Date Of Earthing | Name of the Gang | Remarks
|  |  |  | Before | After
1 | 194/9 | A+0 | DFR | 2.61 | 0.98 | Counterpoise | 2025-08-21 | 2025-08-23 | Oppulence Tenchnologies
2 | 198/1 | A+0 | DFR | 4.8 | 0.9 | Counterpoise | 2025-09-01 | 2025-09-02 | Oppulence Tenchnologies
3 | 205/1 | A+3 | DFR | 5.2 | 0.3 | Counterpoise | 2025-09-14 | 2025-09-15 | Oppulence Tenchnologies
4 | 194/1 | A+0 | WFR | 5.93 | 0.3 | Counterpoise | 2025-10-08 | 2025-10-09 | Oppulence Tenchnologies
5 | 232/4 | A+0 | WFR | 4.1 | 0.2 | Counterpoise | 2025-11-20 | 2025-11-22 | Jay Dada Enterprises
6 | 232/3 | A+0 | WFR | 3.8 | 0.16 | Counterpoise | 2025-11-30 | 2025-12-02 | Jay Dada Enterprises
7 | 217/5 | A+3 | WFR | 3.95 | 0.4 | Counterpoise | 2025-12-15 | 2025-12-17 | Jay Dada Enterprises
8 | 217/6 | A+0 | WET | 3.91 | 0.15 | Pipe Type | 2025-12-26 | 2025-12-28 | Jay Dada Enterprises
9 | 245/2 | A+3 | WET | 3.68 | 0.08 | Pipe Type | 2026-05-06 | 2026-05-08 | Jay Dada Enterprises
10 | 243/2 | A+0 | WET | 4.52 | 0.16 | Pipe Type | 2026-05-15 | 2026-05-17 | Vaibhavi Enterprises
11 | 241/3 | A+0 | DFR | 4.31 | 0.59 | Counterpoise | 2026-05-17 | 2026-05-18 | Jay Dada Enterprises
12 | 243/1 | A+0 | WET | 3.98 | 0.13 | Pipe Type | 2026-05-26 | 2026-06-04 | Vaibhavi Enterprises
13 | 233/3 | A+0 | WC |  |  | Pipe Type | 2026-05-24 | 2026-05-26 | Jay Dada Enterprises
14 | 233/2 | A+0 | WET |  |  | Pipe Type | 2026-05-29 | 2026-06-01 | Jay Dada Enterprises
15 | 241/2 | A+0 | WFR | 4.83 | 0.13 | Counterpoise | 2026-06-08 | 2026-06-10 | Vaibhavi Enterprises
16 | 233/4 | A+0 | WET |  |  | Pipe Type | 2026-06-07 | 2026-06-11 | Jay Dada Enterprises
17 | 233/5 | A+0 | WET | 4.67 | 0.1 | Pipe Type | 2026-06-10 | 2026-06-12 | Jay Dada Enterprises
18 | 233/7 | A+0 | WET | [5 empty] | Jay Dada Enterprises
19 | 233/6 | A+3 | WET | [5 empty] | Jay Dada Enterprises
20
21
22

## Erection Compiled
Project : ±800kV HVDC BIPOLE LINE (HEX LAPWING) BETWEEN KPS2 (HVDC) & NAGPUR (HVDC) (WITH DMR), TRANSMISSION LINE PACKAGE- 03
Tower Erection | [12 empty] | 2026-06-15
Sl | Location No. | Type | Type of Tower | Starting Date | Revenue (Lac.) | Tower Weight (MT) | Status | Completion Date | Gang Name | Manpower | No. | District | Remarks | Ageing
1 | 232/3 | A | A+0 | 2026-02-27 | 5.4611 | 30.826 | Completed | 2026-03-08 | Rupesh Kumar | 24 |  | Surendranagar |  | 9
2 | 232/4 | A | A+0 |  | 5.4611 | 30.826 | [5 empty] | Surendranagar | Shutdown Needed+ROW | 0
3 | 217/5 | A | A+3 |  | 5.873 | 33.151 | [5 empty] | Surendranagar | We do not have tower part of A+3 | 0
4 | 217/6 | A | A+0 |  | 5.4611 | 30.826 | [5 empty] | Surendranagar | Compensation not received to Land Owner | 0
5 | 205/1 | A | A+3 |  | 5.873 | 33.151 | [5 empty] | Surendranagar | We do not have tower part of A+3 / Shutdown Needed | 0
6 | 198/1 | A | A+0 |  | 5.4611 | 30.826 | [5 empty] | Surendranagar | Private land + Crop Damage | 0
7 | 194/1 | A | A+0 |  | 5.4611 | 30.826 | [5 empty] | Morbi | Private land + Crop Damage | 0
8 | 194/9 | A | A+0 | 2026-03-12 | 5.4611 | 30.826 | Completed | 2026-03-18 | Rupesh Kumar | 24 |  | Surendranagar |  | 6
|  |  |  | Total | 44.5129 | 251.258 |  |  |  | Total completed | 0
17716
|  | Summary |  |  | Tower Type | Line Qty. | Completed | Balance
|  | A | 8 |  | A+0 | 6 | 2 | 4
|  | B | 0 |  | A+3 | 2 | 0 | 2
|  | C | 0 |  | A+6 | 0 | 0 | 0
|  | C | 0 |  | A+9 | 0 | 0 | 0
|  | D45 | 0 |  | A-3 | 0 | 0 | 0
|  | D60 | 0 |  | B1+0 | 0 | 0 | 0
|  | Total | 8 |  | B1+18 | 0 | 0 | 0
[5 empty] | B1+3 | 0 | 0 | 0
Loc. | Old | New |  |  | B1+6 | 0 | 0 | 0
167/0 | D60+0 | D60+6 |  |  | B1+9 | 0 | 0 | 0
167/1 | A+9 | D60+0 |  |  | B2+0 | 0 | 0 | 0
[5 empty] | B2+18 | 0 | 0 | 0
[5 empty] | B2+25 | 0 | 0 | 0
[5 empty] | B2+3 | 0 | 0 | 0
[5 empty] | B2+6 | 0 | 0 | 0
[5 empty] | B2+9 | 0 | 0 | 0
[5 empty] | C+0 | 0 | 0 | 0
[5 empty] | C1+0 | 0 | 0 | 0
[5 empty] | C1+18 | 0 | 0 | 0
[5 empty] | C1+3 | 0 | 0 | 0
[5 empty] | C1+6 | 0 | 0 | 0
[5 empty] | C1+9 | 0 | 0 | 0
[5 empty] | C2+0 | 0 | 0 | 0
[5 empty] | C2+18 | 0 | 0 | 0
[5 empty] | C2+25 | 0 | 0 | 0
[5 empty] | C2+3 | 0 | 0 | 0
[5 empty] | C2+6 | 0 | 0 | 0
[5 empty] | C2+9 | 0 | 0 | 0
[5 empty] | CT+0 | 0 | 0 | 0
[5 empty] | D45+0 | 0 | 0 | 0
[5 empty] | D45+18 | 0 | 0 | 0
[5 empty] | D45+25 | 0 | 0 | 0
[5 empty] | D45+3 | 0 | 0 | 0
[5 empty] | D45+35 | 0 | 0 | 0
[5 empty] | D45+6 | 0 | 0 | 0
[5 empty] | D45+9 | 0 | 0 | 0
[5 empty] | D60+0 | 0 | 0 | 0
[5 empty] | D60+18 | 0 | 0 | 0
[5 empty] | D60+25 | 0 | 0 | 0
[5 empty] | D60+3 | 0 | 0 | 0
[5 empty] | D60+35 | 0 | 0 | 0
[5 empty] | D60+55 | 0 | 0 | 0
[5 empty] | D60+6 | 0 | 0 | 0
[5 empty] | D60+9 | 0 | 0 | 0
[5 empty] | Total | 8 | 2 | 6

## Store Stock
±800kV HVDC BIPOLE LINE (HEX LAPWING) BETWEEN KPS2 (HVDC) & NAGPUR (HVDC) (WITH DMR), TRANSMISSION LINE PACKAGE- 03
Stores Stock Balance | [5 empty] | 2026-06-15
Sl. | Description | UOM | Received | Consumed | Balance in stock | Remarks
1 | Counterpoise Earthing | Nos | 114 | 10 | 104
2 | Rod Type Earthing | Nos | 36 | 9 | 27
3 | Pipe Type Earthing | Nos | 36 | 9 | 27
STUB
4 | "A" Type Stub WZ-5NC | Set | 112 | 19 | 93
5 | "A" Type Stub WZ-4NC | Set | 11 | - | 11
6 | "B" Type Stub WZ-4NC | Set | 3 | - | 3
7 | "C" Type Stub WZ-5NC | Set | 11 | - | 11
8 | "C" Type Stub WZ-4NC | Set | 2 | - | 2
9 | Bolt & Nut For stub | MT | 1.611 | 0.306 | 1.305
10 | ACSR LAPWING CONDUCTOR | KM | 952.089 | 0.004 | 952.085
11 | Tower Parts - A Type | Set | 112 | 2 | 110 | 38 Set non erectable & Receiving u/p
12 | Bolt & Nut For Tower | MT | 164 | 2.762 | 161.238
13 | Earth Wire(7/4.5MM) | KM | 61.02 | - | 61.02

## Visual chart
Visual Chart
Project : |  | ±800kV HVDC BIPOLE LINE (HEX LAPWING) BETWEEN KPS2 (HVDC) & NAGPUR (HVDC) (WITH DMR), TRANSMISSION LINE PACKAGE- 03
Client: |  | M/s POWERGRID WEST CENTRAL TRANSMISSION LIMITED
Executive Agency: |  |  |  | KEC INTERNATIONAL LIMITED
| PROGRESS AT A GLANCE : | [15 empty] | CROSSING PROPOSAL STATUS : | [9 empty] | LEGEND:
| Sl. No. | Activity |  |  |  |  | UoM |  | Total Qty |  | Completed Till Date |  |  | Balance |  |  | Sl. No. | Type of Crossing |  |  | No. of X-ing |  | Apprd |  | Balance
| 1 | Detailed Survey |  |  |  |  | Kms |  | 83.3309 |  | 83.3309 |  |  | 0 |  |  | 1 | Powerline |  |  | 17 |  | 13 |  | 4
| 2 | Check Survey |  |  |  |  | Kms |  | 83.3309 |  | 83.3309 |  |  | 0 |  |  | a. | 66 kV |  |  | 9 |  | 8 |  | 1
| 3 | Soil Investigation |  |  |  |  | Nos. |  | 12 |  | 12 |  |  | 0 |  |  | b. | 132 kV |  |  | - |  |  |  | 0
| 4 | Foundation |  |  |  |  | Nos. |  | 217 |  | 17 |  |  | 200 |  |  | c. | 220 kV |  |  | 5 |  | 3 |  | 2 |  |  |  |  | C | B | SPAN |  | C | B
| 5 | Earthing |  |  |  |  | Nos. |  | 217 |  | 17 |  |  | 200 |  |  | d. | 400 kV |  |  | 3 |  | 2 |  | 1 |  | FDN Completed |  |  | D | A |  |  | D | A | Pit Excavation WIP
| 6 | Erection |  |  |  |  | Nos. |  | 217 |  | 2 |  |  | 215 |  |  | e. | 500 kV |  |  | - |  |  |  | 0
| 7 | Tack Welding |  |  |  |  | Nos. |  | 217 |  | 0 |  |  | 217 |  |  | 2 | SH |  |  | 3 |  |  |  | 3
| 8 | Stringing (P/O) |  |  |  |  | Kms |  | 83.331 |  | 0 |  |  | 83.331 |  |  | 3 | NH |  |  | 1 |  |  |  | 1
| 9 | Stringing (F/S) |  |  |  |  | Kms |  | 83.331 |  | 0 |  |  | 83.331 |  |  | 4 | RLY |  |  | 2 |  |  |  | 2
| 10 | OPGW Stringing |  |  |  |  | Kms |  | 83.331 |  | 0 |  |  | 83.331 |  |  | 5 | GAS PIPE |  |  | 2 |  |  |  | 2 |  | PL X-ing |  | RLY X-ing |  | NH X-ing |  | Gas Pipeline |  |  | River X-ing
Completed
[38 empty] | DS (Aprd) | CS (Aprd) | SOIL INVTGN | FOUNDATION |  |  | TOWER ERECTION |  |  |  | Final Checking | TW | TIG & PUN | STR P/O | STR F/S | OPGW STR
[41 empty] | TOTAL | COMP. | BAL. | EAR | TOTAL | COMP. | BAL.
| 191/0 |  |  | 191/1 |  |  |  | 192/0 |  |  | 192/1 |  |  |  | 193/0 |  |  | 194/0 |  |  |  | 194/1 |  |  |  | 194/2 |  |  |  | 194/3 |  |  |  | 194/4 |  |  |  | 4216.624 | 4216.624 |  | 10 | 1 | 9 | 1 | 10 |  | 10
| C | B | 528 | C | B | 515.353 |  | C | B | 388 | C | B | 386.211 |  | C | B | 381.06 | C | B | 390 |  | C | B | 393 |  | C | B | 395 |  | C | B | 431 |  | C | B | 409
| D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
| D45+9 |  |  | B1+9 |  |  |  | D45 +9 |  |  | A+0 |  |  |  | C1+0 |  |  | C1+0 |  |  |  | A+0 |  |  |  | A+0 |  |  |  | A+0 |  |  |  | A+0
66KV S/C Kondh - Sara (H-POLE)
[38 empty] | 3605.888 | 3605.888 |  | 10 | 1 | 9 | 1 | 10 | 1 | 9
| 194/5 |  |  | 194/6 |  |  |  | 194/7 |  |  | 194/8 |  |  |  | 194/9 |  |  | 194/10 |  |  |  | 195/0 |  |  |  | 195/1 |  |  |  | 195/2 |  |  |  | 196/0
| C | B | 430 | C | B | 392 |  | C | B | 399 | C | B | 307 |  | C | B | 364 | C | B | 375.568 |  | C | B | 368.615 |  | C | B | 357.566 |  | C | B | 414.749 |  | C | B | 197.39
| D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
| A+6 |  |  | A+0 |  |  |  | A+0 |  |  | A+0 |  |  |  | A+0 |  |  | A+0 |  |  |  | C1+0 |  |  |  | A+0 |  |  |  | A+0 |  |  |  | D45+18
220KV D/C MANSAR - SADLA
[38 empty] | 3848.25 | 3848.25 |  | 10 | 1 | 9 | 1 | 10 |  | 10
| 197/0 |  |  | 197/1 |  |  |  | 197/2 |  |  | 197/3 |  |  |  | 197/4 |  |  | 198/0 |  |  |  | 198/1 |  |  |  | 198/2 |  |  |  | 199/0 |  |  |  | 199/1
| C | B | 477 | C | B | 420 |  | C | B | 419 | C | B | 418 |  | C | B | 254.686 | C | B | 343 |  | C | B | 357 |  | C | B | 318.423 |  | C | B | 440 |  | C | B | 401.141
| D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
| D45 +9 |  |  | B1+3 |  |  |  | A+3 |  |  | A+3 |  |  |  | A+0 |  |  | C1+0 |  |  |  | A+0 |  |  |  | A+0 |  |  |  | B1+0 |  |  |  | A+9
[38 empty] | 3924.608 | 3924.608 |  | 10 |  | 10 | 0 | 10 |  | 10
| 200/0 |  |  | 200/1 |  |  |  | 201/0 |  |  | 201/1 |  |  |  | 201/2 |  |  | 201/3 |  |  |  | 202/0 |  |  |  | 202/1 |  |  |  | 202/2 |  |  |  | 202/3
| C | B | 375 | C | B | 364.132 |  | C | B | 387 | C | B | 427 |  | C | B | 413 | C | B | 386.645 |  | C | B | 411 |  | C | B | 430 |  | C | B | 398 |  | C | B | 332.831
| D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
| B1+3 |  |  | A+0 |  |  |  | C1+0 |  |  | A+3 |  |  |  | A+3 |  |  | A+0 |  |  |  | B2+0 |  |  |  | A+3 |  |  |  | A+0 |  |  |  | A+0
[38 empty] | 3777.837 | 3777.837 |  | 10 | 1 | 9 | 1 | 10 |  | 10
| 203/0 |  |  | 203/1 |  |  |  | 203/2 |  |  | 204/0 |  |  |  | 205/0 |  |  | 205/1 |  |  |  | 205/2 |  |  |  | 205/3 |  |  |  | 205/4 |  |  |  | 206/0
| C | B | 375 | C | B | 315 |  | C | B | 420.309 | C | B | 373.659 |  | C | B | 391.999 | C | B | 416 |  | C | B | 399 |  | C | B | 358 |  | C | B | 288.192 |  | C | B | 440.678
| D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
| B1+0 |  |  | A+0 |  |  |  | A+3 |  |  | C1+3 |  |  |  | B1+0 |  |  | A+3 |  |  |  | A+3 |  |  |  | A+0 |  |  |  | A+3 |  |  |  | D45 +9
[11 empty] | 66kV S/C Raygadh - Kuntalpur(H-Pole) | [8 empty] | 0
[38 empty] | 3687.154 | 3687.154 |  | 10 |  | 10 | 0 | 10 |  | 10
| 207/0 |  |  | 208/0 |  |  |  | 209/0 |  |  | 209/1 |  |  |  | 209/2 |  |  | 209/3 |  |  |  | 209/4 |  |  |  | 210/0 |  |  |  | 211/0 |  |  |  | 211/1
| C | B | 275.26 | C | B | 366.157 |  | C | B | 357 | C | B | 380 |  | C | B | 413 | C | B | 410.112 |  | C | B | 388.813 |  | C | B | 415.812 |  | C | B | 178 |  | C | B | 503
| D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
| D45 +6 |  |  | C1+6 |  |  |  | C2+0 |  |  | A+0 |  |  |  | A+0 |  |  | A+3 |  |  |  | A+0 |  |  |  | B1+0 |  |  |  | C2+6 |  |  |  | A+9
| 66kV D/C Sadla to Kondh & Narichana | [24 empty] | 66kV S/C Sadla to Khodu Transmission Line
[38 empty] | 3979.321 | 3979.321 |  | 10 |  | 10 | 0 | 10 |  | 10
| 211/2 |  |  | 211/3 |  |  |  | 212/0 |  |  | 212/1 |  |  |  | 212/2 |  |  | 212/3 |  |  |  | 212/4 |  |  |  | 212/5 |  |  |  | 212/6 |  |  |  | 212/7
| C | B | 338 | C | B | 501.321 |  | C | B | 343 | C | B | 287 |  | C | B | 416 | C | B | 418 |  | C | B | 418 |  | C | B | 417 |  | C | B | 391 |  | C | B | 450
| D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
| A+9 |  |  | A+9 |  |  |  | B2+9 |  |  | A-3 |  |  |  | A+0 |  |  | A+3 |  |  |  | A+0 |  |  |  | A+3 |  |  |  | A+0 |  |  |  | A+6
[38 empty] | 3614.147 | 3614.147 |  | 10 |  | 10 | 0 | 10 |  | 10
| 212/8 |  |  | 212/9 |  |  |  | 213/0 |  |  | 213/1 |  |  |  | 213/2 |  |  | 213/3 |  |  |  | 213/4 |  |  |  | 213/5 |  |  |  | 213/6 |  |  |  | 214/0
| C | B | 391.296 | C | B | 431.446 |  | C | B | 401.999 | C | B | 386 |  | C | B | 374 | C | B | 343 |  | C | B | 347 |  | C | B | 296 |  | C | B | 362.804 |  | C | B | 280.602
| D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
| A+3 |  |  | A+3 |  |  |  | C2+3 |  |  | A+0 |  |  |  | A+0 |  |  | A-3 |  |  |  | A-3 |  |  |  | A-3 |  |  |  | A-3 |  |  |  | C2+0
66kV S/C Digsar - GRT TL
[38 empty] | 3730.044 | 3730.044 |  | 10 |  | 10 | 0 | 10 |  | 10
| 215/0 |  |  | 215/1 |  |  |  | 215/2 |  |  | 215/3 |  |  |  | 215/4 |  |  | 215/5 |  |  |  | 216/0 |  |  |  | 217/0 |  |  |  | 217/1 |  |  |  | 217/2
| C | B | 424.999 | C | B | 392 |  | C | B | 321 | C | B | 411 |  | C | B | 380 | C | B | 455.95 |  | C | B | 242.096 |  | C | B | 322.999 |  | C | B | 389 |  | C | B | 391
| D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
| D45 +6 |  |  | A+0 |  |  |  | A+0 |  |  | A+0 |  |  |  | A+3 |  |  | A+9 |  |  |  | D60 +3 |  |  |  | D60 +3 |  |  |  | A+0 |  |  |  | A+0
[19 empty] | GSPL GAS PIPE LINE |  |  |  |  | RAILWAY TRACK
[38 empty] | 3760.488 | 3760.488 |  | 10 | 2 | 8 | 2 | 10 |  | 10
| 217/3 |  |  | 217/4 |  |  |  | 217/5 |  |  | 217/6 |  |  |  | 217/7 |  |  | 218/0 |  |  |  | 218/1 |  |  |  | 219/0 |  |  |  | 220/0 |  |  |  | 220/1
| C | B | 322 | C | B | 449 |  | C | B | 389 | C | B | 412 |  | C | B | 402.266 | C | B | 364.999 |  | C | B | 368.845 |  | C | B | 256.128 |  | C | B | 393.999 |  | C | B | 402.251
| D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
| A+0 |  |  | A+3 |  |  |  | A+3 |  |  | A+0 |  |  |  | A+3 |  |  | C1+0 |  |  |  | A+0 |  |  |  | C2+9 |  |  |  | D45 +9 |  |  |  | A+0
[19 empty] | BHOGAWO RIVER | [6 empty] | 66kV M/C Sadla - Godavari & Dudhrej
[38 empty] | 3841.214 | 3841.214 |  | 10 |  | 10 | 0 | 10 |  | 10
| 221/0 |  |  | 221/1 |  |  |  | 222/0 |  |  | 222/1 |  |  |  | 222/2 |  |  | 222/3 |  |  |  | 222/4 |  |  |  | 222/5 |  |  |  | 222/6 |  |  |  | 222/7
| C | B | 253.999 | C | B | 394.215 |  | C | B | 398 | C | B | 417 |  | C | B | 419 | C | B | 422 |  | C | B | 395 |  | C | B | 359 |  | C | B | 376 |  | C | B | 407
| D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
| C1+0 |  |  | A+6 |  |  |  | C2+6 |  |  | A+0 |  |  |  | A+3 |  |  | A+3 |  |  |  | A+3 |  |  |  | A+0 |  |  |  | A-3 |  |  |  | A+0
STATE HIGHWAY-17
[38 empty] | 3823.057 | 3823.057 |  | 10 |  | 10 | 0 | 10 |  | 10
| 222/8 |  |  | 222/9 |  |  |  | 223/0 |  |  | 223/1 |  |  |  | 223/2 |  |  | 223/3 |  |  |  | 223/4 |  |  |  | 223/5 |  |  |  | 223/6 |  |  |  | 223/7
| C | B | 428 | C | B | 327.057 |  | C | B | 408 | C | B | 413 |  | C | B | 327 | C | B | 306 |  | C | B | 414 |  | C | B | 419 |  | C | B | 398 |  | C | B | 383
| D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
| A+3 |  |  | A+3 |  |  |  | B2+0 |  |  | A+3 |  |  |  | A+0 |  |  | A+0 |  |  |  | A+0 |  |  |  | A+6 |  |  |  | A+0 |  |  |  | A+0
[38 empty] | 4062.16 | 4062.16 |  | 10 |  | 10 | 0 | 10 |  | 10
| 223/8 |  |  | 223/9 |  |  |  | 223/10 |  |  | 223/11 |  |  |  | 224/0 |  |  | 224/1 |  |  |  | 224/2 |  |  |  | 224/3 |  |  |  | 225/0 |  |  |  | 225/1
| C | B | 432 | C | B | 394 |  | C | B | 433 | C | B | 393.544 |  | C | B | 404.999 | C | B | 401 |  | C | B | 334 |  | C | B | 452.617 |  | C | B | 425 |  | C | B | 392
| D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
| A+6 |  |  | A+0 |  |  |  | A+0 |  |  | A+6 |  |  |  | B1+0 |  |  | A+3 |  |  |  | A+0 |  |  |  | A+6 |  |  |  | C1+6 |  |  |  | A+0
[38 empty] | 3755.167 | 3755.167 |  | 10 |  | 10 | 0 | 10 |  | 10
| 225/2 |  |  | 225/3 |  |  |  | 225/4 |  |  | 225/5 |  |  |  | 226/0 |  |  | 227/0 |  |  |  | 227/1 |  |  |  | 228/0 |  |  |  | 229/0 |  |  |  | 229/1
| C | B | 386 | C | B | 346 |  | C | B | 282 | C | B | 418.236 |  | C | B | 228.74 | C | B | 424.999 |  | C | B | 323.686 |  | C | B | 419.507 |  | C | B | 442 |  | C | B | 483.999
| D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
| A+0 |  |  | A+0 |  |  |  | A+0 |  |  | A+0 |  |  |  | D60 +25 |  |  | D60 +25 |  |  |  | A+0 |  |  |  | B1+3 |  |  |  | C1+3 |  |  |  | B1+9
400KV D/C SHAPAR TO CHHARODI
[38 empty] | 3576.153 | 3576.153 |  | 10 | 2 | 8 | 2 | 10 | 1 | 9
| 229/2 |  |  | 229/3 |  |  |  | 230/0 |  |  | 231/0 |  |  |  | 232/0 |  |  | 232/1 |  |  |  | 232/2 |  |  |  | 232/3 |  |  |  | 232/4 |  |  |  | 233/0
| C | B | 356 | C | B | 483.954 |  | C | B | 432.524 | C | B | 242.956 |  | C | B | 366 | C | B | 337 |  | C | B | 348 |  | C | B | 356 |  | C | B | 268.719 |  | C | B | 385
| D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
| A+9 |  |  | A+9 |  |  |  | B2+9 |  |  | D60 +6 |  |  |  | D60 +0 |  |  | A+0 |  |  |  | A+0 |  |  |  | A+0 |  |  |  | A+0 |  |  |  | C1+0
[11 empty] | SINGLE RAILWAY TRACK | [22 empty] | GSPC GAS PIPE LINE
[38 empty] | 4024.5 | 4024.5 |  | 10 | 4 | 6 | 4 | 10 |  | 10
| 233/1 |  |  | 233/2 |  |  |  | 233/3 |  |  | 233/4 |  |  |  | 233/5 |  |  | 233/6 |  |  |  | 233/7 |  |  |  | 234/0 |  |  |  | 235/0 |  |  |  | 235/1
| C | B | 377 | C | B | 392 |  | C | B | 394 | C | B | 401 |  | C | B | 411 | C | B | 419 |  | C | B | 421 |  | C | B | 415.5 |  | C | B | 394 |  | C | B | 400
| D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
| A+0 |  |  | A+0 |  |  |  | A+0 |  |  | A+0 |  |  |  | A+0 |  |  | A+3 |  |  |  | A+0 |  |  |  | C2+9 |  |  |  | C2+9 |  |  |  | A+0
66KV D/C LIMBDI - KHARVA (CKT-I) & KHARVA - SURENDRANAGR (CKT-II) TL
[38 empty] | 3781.458 | 3781.458 |  | 10 |  | 10 | 0 | 10 |  | 10
| 235/2 |  |  | 236/0 |  |  |  | 237/0 |  |  | 238/0 |  |  |  | 239/0 |  |  | 239/1 |  |  |  | 239/2 |  |  |  | 239/3 |  |  |  | 239/4 |  |  |  | 239/5
| C | B | 431.372 | C | B | 247.048 |  | C | B | 372.047 | C | B | 425.991 |  | C | B | 410 | C | B | 409 |  | C | B | 383 |  | C | B | 390 |  | C | B | 380 |  | C | B | 333
| D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
| A+0 |  |  | D45 +6 |  |  |  | B1+18 |  |  | D60 +18 |  |  |  | C2+0 |  |  | A+3 |  |  |  | A+0 |  |  |  | A+0 |  |  |  | A+0 |  |  |  | A+0
|  |  |  | NH-51 (LIMBDI - SURENDRANAGAR) |  |  |  |  | 66KV D/C LIMBDI - SURENDRANAGAR TL, 220KV D/C CHORANIYA - DHRANGADHARA TL
[38 empty] | 3810.031 | 3810.031 |  | 10 | 1 | 9 | 1 | 10 |  | 10
| 239/6 |  |  | 239/7 |  |  |  | 239/8 |  |  | 239/9 |  |  |  | 239/10 |  |  | 239/11 |  |  |  | 240/0 |  |  |  | 241/0 |  |  |  | 241/1 |  |  |  | 241/2
| C | B | 384 | C | B | 412 |  | C | B | 426 | C | B | 415 |  | C | B | 425 | C | B | 380.769 |  | C | B | 228.262 |  | C | B | 421 |  | C | B | 391 |  | C | B | 327
| D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
| A+0 |  |  | A+0 |  |  |  | A+6 |  |  | A+0 |  |  |  | A+6 |  |  | A+0 |  |  |  | D60 +9 |  |  |  | D45 +9 |  |  |  | A+0 |  |  |  | A+0
220KV D/C CHORANIYA - BALA TRANSMISSION TL
[38 empty] | 3395.971 | 3395.971 |  | 10 | 4 | 6 | 4 | 10 | 0 | 10
| 241/3 |  |  | 242/0 |  |  |  | 243/0 |  |  | 243/1 |  |  |  | 243/2 |  |  | 244/0 |  |  |  | 245/0 |  |  |  | 245/1 |  |  |  | 245/2 |  |  |  | 246/0
| C | B | 503.111 | C | B | 297.12 |  | C | B | 471 | C | B | 311 |  | C | B | 319.169 | C | B | 202.061 |  | C | B | 298.001 |  | C | B | 352 |  | C | B | 408.139 |  | C | B | 234.37
| D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
| A+0 |  |  | D60 +25 |  |  |  | D60 +25 |  |  | A+0 |  |  |  | A+0 |  |  | B2+9 |  |  |  | C1+0 |  |  |  | A+0 |  |  |  | A+3 |  |  |  | D60 +25
|  |  |  | 400KV D/C BHACHAU - LIMBDI TL | [10 empty] | SH 38 (Limbdi-Lakhatar) |  |  |  | 220KV S/C CHORANIYA - VIRAMAGAM TL | [14 empty] | 400KV D/C (TWIN) CHORANIYA - RANCHOD PURA T/L
[38 empty] | 4046.145 | 4046.145 |  | 10 |  | 10 | 0 | 10 | 0 | 10
| 247/0 |  |  | 247/1 |  |  |  | 248/0 |  |  | 248A/0 |  |  |  | 248A/1 |  |  | 248A/2 |  |  |  | 248A/3 |  |  |  | 248A/4 |  |  |  | 248A/5 |  |  |  | 248A/6
| C | B | 440 | C | B | 460.649 |  | C | B | 242.496 | C | B | 444 |  | C | B | 369 | C | B | 455 |  | C | B | 378 |  | C | B | 421 |  | C | B | 417 |  | C | B | 419
| D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
| D60 +25 |  |  | B1+3 |  |  |  | C2+9 |  |  | D45+18 |  |  |  | A+0 |  |  | A+6 |  |  |  | A+3 |  |  |  | A+3 |  |  |  | A+3 |  |  |  | B1+0
220KV D/C CHORANIYA - AVAADA TL
[38 empty] | 4157.723 | 4157.723 |  | 10 |  | 10 | 0 | 10 |  | 10
| 248A/7 |  |  | 248A/8 |  |  |  | 248A/9 |  |  | 248A/10 |  |  |  | 248A/11 |  |  | 248B/0 |  |  |  | 248B/1 |  |  |  | 248B/2 |  |  |  | 248B/3 |  |  |  | 248B/4
| C | B | 421 | C | B | 418 |  | C | B | 409 | C | B | 402 |  | C | B | 418.722 | C | B | 457.001 |  | C | B | 382 |  | C | B | 456 |  | C | B | 374 |  | C | B | 420
| D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
| A+3 |  |  | A+3 |  |  |  | A+3 |  |  | A+0 |  |  |  | A+0 |  |  | B1+3 |  |  |  | A+6 |  |  |  | A+3 |  |  |  | A+6 |  |  |  | A+0
[26 empty] | CP L&T Portion | [11 empty] | 2913 | 2913 |  | 7 |  | 7 | 0 | 7 |  | 7
| 248B/5 |  |  | 248B/6 |  |  |  | 248B/7 |  |  | 248B/8 |  |  |  | 248B/9 |  |  | 248B/10 |  |  |  | 248B/11 |  |  |  | 249/0
| C | B | 415 | C | B | 424 |  | C | B | 390 | C | B | 451 |  | C | B | 391 | C | B | 422.158 |  | C | B | 419.842 |  | C | B
| D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  |  | D | A
| A+3 |  |  | A+0 |  |  |  | B1+6 |  |  | A+6 |  |  |  | A+0 |  |  | A+0 |  |  |  | A+3 |  |  |  | -
[38 empty] | 83.3309 | 83.3309 |  | 217 | 17 | 200 | 17 | 217 | 2 | 215
ERE WIP
ERE Completed
OPGW Stringing
Completed
Stringing
Completed
Bird Guard
Suspension Tower
Tackwelding
Stringing WIP
Tennsion Tower
Earthing
Soil Investigation