## Portfolio Summary
Metric | Value
Total Foundations | 5084
Projects | 16
Gangs With Data | 350
Active Gang-Months | 986
Avg Foundations / Active Gang-Month | 2.24
Median Foundations / Active Gang-Month | 2
Avg Duration Days | 13.91
Duration Coverage % | 62.57
Gang Name Coverage % | 43.41
First Completion Date | 2015-11-27
Last Completion Date | 2026-06-26
Snapshot Rows Excluded | 7

## Portfolio Monthly Trend
Month | Foundations Completed | Projects Active | Unique Gangs | Active Gang-Months | Avg Foundations / Active Gang-Month | Median Foundations / Active Gang-Month | Avg Duration Days | Duration Coverage % | Gang Name Coverage %
2015-11 | 1 | 1 | 0 | 0 |  |  |  | 0 | 0
2023-10 | 1 | 1 | 0 | 0 |  |  |  | 0 | 0
2023-12 | 22 | 1 | 0 | 0 |  |  |  | 0 | 0
2024-01 | 48 | 2 | 2 | 2 | 1 | 1 |  | 0 | 4.17
2024-02 | 36 | 1 | 0 | 0 |  |  |  | 0 | 0
2024-03 | 17 | 2 | 0 | 0 |  |  |  | 0 | 0
2024-04 | 9 | 2 | 0 | 0 |  |  |  | 0 | 0
2024-05 | 27 | 5 | 4 | 4 | 3 | 2.5 | 9.64 | 40.74 | 44.44
2024-06 | 65 | 6 | 11 | 11 | 3.82 | 3 | 10.71 | 64.62 | 64.62
2024-07 | 91 | 6 | 21 | 21 | 2.71 | 2 | 11.47 | 62.64 | 62.64
2024-08 | 109 | 7 | 19 | 19 | 3 | 2 | 15.54 | 51.38 | 52.29
2024-09 | 159 | 7 | 32 | 32 | 2.31 | 2 | 14.27 | 46.54 | 46.54
2024-10 | 206 | 9 | 41 | 41 | 2.68 | 2 | 10.26 | 57.77 | 53.4
2024-11 | 209 | 9 | 50 | 50 | 2.48 | 2 | 10.35 | 71.29 | 59.33
2024-12 | 275 | 9 | 55 | 55 | 2.71 | 2 | 9.4 | 66.91 | 54.18
2025-01 | 282 | 10 | 54 | 54 | 2.72 | 2 | 15.18 | 61.35 | 52.13
2025-02 | 284 | 12 | 48 | 48 | 3.12 | 2.5 | 10.01 | 71.13 | 52.82
2025-03 | 233 | 13 | 48 | 48 | 2.58 | 2 | 13.24 | 73.39 | 53.22
2025-04 | 280 | 13 | 50 | 50 | 2.68 | 2 | 9.3 | 66.07 | 47.86
2025-05 | 271 | 13 | 43 | 43 | 3.14 | 2 | 13.74 | 66.79 | 49.82
2025-06 | 200 | 13 | 35 | 35 | 2.74 | 2 | 10.92 | 77 | 48
2025-07 | 199 | 11 | 33 | 33 | 2.18 | 1 | 9.84 | 83.92 | 36.18
2025-08 | 146 | 14 | 27 | 27 | 1.85 | 1 | 14.44 | 89.73 | 34.25
2025-09 | 136 | 14 | 31 | 31 | 1.84 | 1 | 12.72 | 75.74 | 41.91
2025-10 | 150 | 15 | 41 | 41 | 1.59 | 1 | 14.18 | 63.33 | 43.33
2025-11 | 254 | 15 | 60 | 60 | 1.77 | 1 | 13.53 | 64.96 | 41.73
2025-12 | 328 | 14 | 67 | 67 | 1.9 | 1 | 14.35 | 66.16 | 38.72
2026-01 | 268 | 14 | 56 | 56 | 1.61 | 1 | 18.81 | 54.85 | 33.58
2026-02 | 227 | 16 | 49 | 49 | 1.39 | 1 | 22.32 | 43.61 | 29.96
2026-03 | 151 | 16 | 28 | 28 | 1.5 | 1 | 17.38 | 48.34 | 27.81
2026-04 | 125 | 12 | 22 | 22 | 1.55 | 1 | 18.91 | 53.6 | 27.2
2026-05 | 188 | 12 | 39 | 39 | 1.38 | 1 | 31.41 | 58.51 | 28.72
2026-06 | 87 | 11 | 20 | 20 | 1.45 | 1 | 26.71 | 56.32 | 33.33

## Project Monthly Trend
PCH | Project | Month | Foundations Completed | Unique Gangs | Avg Foundations / Active Gang-Month | Avg Duration Days | Valid Duration Foundations | Duration Coverage %
Mr. Arun Felbin | TA 414 | 2024-05 | 2 | 1 | 2 | 10.5 | 2 | 100
Mr. Arun Felbin | TA 414 | 2024-10 | 1 | 1 | 1 | 42 | 1 | 100
Mr. Arun Felbin | TA 414 | 2024-11 | 4 | 2 | 2 | 13 | 4 | 100
Mr. Arun Felbin | TA 414 | 2024-12 | 12 | 9 | 1.33 | 13.82 | 11 | 91.67
Mr. Arun Felbin | TA 414 | 2025-01 | 17 | 8 | 2.12 | 11.69 | 16 | 94.12
Mr. Arun Felbin | TA 414 | 2025-02 | 20 | 6 | 3.33 | 11.5 | 18 | 90
Mr. Arun Felbin | TA 414 | 2025-03 | 10 | 5 | 2 | 14.4 | 10 | 100
Mr. Arun Felbin | TA 414 | 2025-04 | 18 | 6 | 3 | 13.33 | 18 | 100
Mr. Arun Felbin | TA 414 | 2025-05 | 5 | 4 | 1.25 | 15.6 | 5 | 100
Mr. Arun Felbin | TA 414 | 2025-06 | 2 | 2 | 1 | 22.5 | 2 | 100
Mr. Arun Felbin | TA 414 | 2025-08 | 1 | 1 | 1 | 20 | 1 | 100
Mr. Arun Felbin | TA 414 | 2025-09 | 3 | 3 | 1 | 31.33 | 3 | 100
Mr. Arun Felbin | TA 414 | 2025-10 | 8 | 3 | 2.67 | 18 | 8 | 100
Mr. Arun Felbin | TA 414 | 2025-11 | 24 | 13 | 1.85 | 14.46 | 24 | 100
Mr. Arun Felbin | TA 414 | 2025-12 | 55 | 31 | 1.61 | 21.89 | 55 | 100
Mr. Arun Felbin | TA 414 | 2026-01 | 54 | 30 | 1.63 | 19.65 | 54 | 100
Mr. Arun Felbin | TA 414 | 2026-02 | 30 | 15 | 1.67 | 38.13 | 30 | 100
Mr. Arun Felbin | TA 414 | 2026-03 | 24 | 13 | 1.85 | 14.62 | 24 | 100
Mr. Arun Felbin | TA 414 | 2026-04 | 14 | 10 | 1.4 | 23.14 | 14 | 100
Mr. Arun Felbin | TA 414 | 2026-05 | 15 | 12 | 1.25 | 30.93 | 15 | 100
Mr. Arun Felbin | TA 414 | 2026-06 | 9 | 7 | 1.29 | 73.78 | 9 | 100
Mr. Arun Felbin | TA 416 | 2024-05 | 6 | 1 | 6 | 8 | 6 | 100
Mr. Arun Felbin | TA 416 | 2024-06 | 17 | 4 | 4.25 | 6.88 | 17 | 100
Mr. Arun Felbin | TA 416 | 2024-07 | 10 | 5 | 2 | 9.8 | 10 | 100
Mr. Arun Felbin | TA 416 | 2024-08 | 13 | 6 | 2.17 | 9.33 | 12 | 92.31
Mr. Arun Felbin | TA 416 | 2024-09 | 31 | 15 | 2.07 | 13.81 | 31 | 100
Mr. Arun Felbin | TA 416 | 2024-10 | 59 | 18 | 3.28 | 7.22 | 59 | 100
Mr. Arun Felbin | TA 416 | 2024-11 | 57 | 21 | 2.71 | 8.65 | 57 | 100
Mr. Arun Felbin | TA 416 | 2024-12 | 62 | 19 | 3.26 | 8.84 | 62 | 100
Mr. Arun Felbin | TA 416 | 2025-01 | 61 | 25 | 2.44 | 12.46 | 56 | 91.8
Mr. Arun Felbin | TA 416 | 2025-02 | 57 | 21 | 2.71 | 9.58 | 57 | 100
Mr. Arun Felbin | TA 416 | 2025-03 | 46 | 20 | 2.3 | 8.59 | 46 | 100
Mr. Arun Felbin | TA 416 | 2025-04 | 49 | 22 | 2.23 | 9.57 | 49 | 100
Mr. Arun Felbin | TA 416 | 2025-05 | 44 | 16 | 2.75 | 8.14 | 44 | 100
Mr. Arun Felbin | TA 416 | 2025-06 | 25 | 12 | 2.08 | 12.84 | 25 | 100
Mr. Arun Felbin | TA 416 | 2025-07 | 6 | 5 | 1.2 | 15.67 | 6 | 100
Mr. Arun Felbin | TA 416 | 2025-08 | 8 | 8 | 1 | 25 | 8 | 100
Mr. Arun Felbin | TA 416 | 2025-09 | 17 | 13 | 1.31 | 22.82 | 17 | 100
Mr. Arun Felbin | TA 416 | 2025-10 | 17 | 17 | 1 | 20 | 13 | 76.47
Mr. Arun Felbin | TA 416 | 2025-11 | 18 | 15 | 1.2 | 24.33 | 12 | 66.67
Mr. Arun Felbin | TA 416 | 2025-12 | 8 | 6 | 1.33 | 18.86 | 7 | 87.5
Mr. Arun Felbin | TA 416 | 2026-01 | 2 | 2 | 1 | 30.5 | 2 | 100
Mr. Arun Felbin | TA 416 | 2026-02 | 11 | 10 | 1.1 | 20 | 1 | 9.09
Mr. Arun Felbin | TA 416 | 2026-03 | 2 | 2 | 1 | 36 | 2 | 100
Mr. Arun Felbin | TA 416 | 2026-05 | 3 | 3 | 1 |  | 0 | 0
Mr. Arun Felbin | TA 418 | 2024-01 | 2 | 2 | 1 |  | 0 | 0
Mr. Arun Felbin | TA 418 | 2024-06 | 2 | 1 | 2 | 17 | 2 | 100
Mr. Arun Felbin | TA 418 | 2024-07 | 8 | 6 | 1.33 | 16.38 | 8 | 100
Mr. Arun Felbin | TA 418 | 2024-08 | 9 | 3 | 3 | 17.33 | 9 | 100
Mr. Arun Felbin | TA 418 | 2024-09 | 8 | 3 | 2.67 | 11.38 | 8 | 100
Mr. Arun Felbin | TA 418 | 2024-10 | 5 | 3 | 1.67 | 14 | 5 | 100
Mr. Arun Felbin | TA 418 | 2024-11 | 9 | 5 | 1.8 | 20.11 | 9 | 100
Mr. Arun Felbin | TA 418 | 2024-12 | 14 | 5 | 2.8 | 16.07 | 14 | 100
Mr. Arun Felbin | TA 418 | 2025-01 | 12 | 6 | 2 | 85.25 | 12 | 100
Mr. Arun Felbin | TA 418 | 2025-02 | 14 | 5 | 2.8 | 18 | 14 | 100
Mr. Arun Felbin | TA 418 | 2025-03 | 15 | 6 | 2.5 | 15.53 | 15 | 100
Mr. Arun Felbin | TA 418 | 2025-04 | 12 | 6 | 2 | 10.33 | 12 | 100
Mr. Arun Felbin | TA 418 | 2025-05 | 17 | 5 | 3.4 | 20.94 | 17 | 100
Mr. Arun Felbin | TA 418 | 2025-06 | 22 | 7 | 3.14 | 10.43 | 21 | 95.45
Mr. Arun Felbin | TA 418 | 2025-07 | 25 | 12 | 2.08 | 12.22 | 23 | 92
Mr. Arun Felbin | TA 418 | 2025-08 | 13 | 7 | 1.86 | 12.15 | 13 | 100
Mr. Arun Felbin | TA 418 | 2025-09 | 11 | 6 | 1.83 | 11.2 | 10 | 90.91
Mr. Arun Felbin | TA 418 | 2025-10 | 8 | 6 | 1.33 | 20 | 7 | 87.5
Mr. Arun Felbin | TA 418 | 2025-11 | 16 | 7 | 2.29 | 12.85 | 13 | 81.25
Mr. Arun Felbin | TA 418 | 2025-12 | 17 | 7 | 2.43 | 7.5 | 16 | 94.12
Mr. Arun Felbin | TA 418 | 2026-01 | 13 | 5 | 2.6 | 42.64 | 11 | 84.62
Mr. Arun Felbin | TA 418 | 2026-02 | 11 | 8 | 1.38 | 11.71 | 7 | 63.64
Mr. Arun Felbin | TA 418 | 2026-03 | 5 | 5 | 1 |  | 0 | 0
Mr. Arun Felbin | TA 418 | 2026-04 | 4 | 3 | 1.33 | 37 | 1 | 25
Mr. Arun Felbin | TA 418 | 2026-05 | 4 | 4 | 1 |  | 0 | 0
Mr. Arun Felbin | TA 418 | 2026-06 | 4 | 2 | 1.5 |  | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-05 | 1 | 1 | 1 | 20 | 1 | 100
Mr. Arun Felbin | TA 421 | 2024-06 | 14 | 4 | 3.5 | 17.14 | 14 | 100
Mr. Arun Felbin | TA 421 | 2024-07 | 22 | 7 | 3.14 | 13.05 | 22 | 100
Mr. Arun Felbin | TA 421 | 2024-08 | 27 | 6 | 4.5 | 19.48 | 27 | 100
Mr. Arun Felbin | TA 421 | 2024-09 | 19 | 9 | 2.11 | 17.16 | 19 | 100
Mr. Arun Felbin | TA 421 | 2024-10 | 27 | 13 | 2.08 | 15.7 | 27 | 100
Mr. Arun Felbin | TA 421 | 2024-11 | 40 | 15 | 2.67 | 12.65 | 40 | 100
Mr. Arun Felbin | TA 421 | 2024-12 | 49 | 16 | 3.06 | 10.29 | 49 | 100
Mr. Arun Felbin | TA 421 | 2025-01 | 50 | 11 | 4.55 | 10.16 | 50 | 100
Mr. Arun Felbin | TA 421 | 2025-02 | 45 | 11 | 4.09 | 11.27 | 45 | 100
Mr. Arun Felbin | TA 421 | 2025-03 | 43 | 12 | 3.58 | 25.86 | 43 | 100
Mr. Arun Felbin | TA 421 | 2025-04 | 35 | 9 | 3.89 | 9.09 | 35 | 100
Mr. Arun Felbin | TA 421 | 2025-05 | 54 | 12 | 4.5 | 21.26 | 53 | 98.15
Mr. Arun Felbin | TA 421 | 2025-06 | 35 | 9 | 3.89 | 12.86 | 35 | 100
Mr. Arun Felbin | TA 421 | 2025-07 | 36 | 13 | 2.77 | 10.32 | 34 | 94.44
Mr. Arun Felbin | TA 421 | 2025-08 | 25 | 9 | 2.78 | 9.32 | 25 | 100
Mr. Arun Felbin | TA 421 | 2025-09 | 22 | 7 | 3.14 | 7.64 | 22 | 100
Mr. Arun Felbin | TA 421 | 2025-10 | 21 | 9 | 2.33 | 13.79 | 19 | 90.48
Mr. Arun Felbin | TA 421 | 2025-11 | 25 | 7 | 3.57 | 7.3 | 23 | 92
Mr. Arun Felbin | TA 421 | 2025-12 | 24 | 6 | 4 | 6.35 | 23 | 95.83
Mr. Arun Felbin | TA 421 | 2026-01 | 7 | 5 | 1.4 | 6.33 | 6 | 85.71
Mr. Arun Felbin | TA 421 | 2026-02 | 8 | 8 | 1 |  | 0 | 0
Mr. Arun Felbin | TA 421 | 2026-03 | 2 | 1 | 1 |  | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2025-02 | 4 | 2 | 2 | 6 | 4 | 100
Mr. Arun Felbin | TA 510FDN | 2025-03 | 5 | 2 | 2.5 | 6.2 | 5 | 100
Mr. Arun Felbin | TA 510FDN | 2025-04 | 6 | 2 | 3 | 13.83 | 6 | 100
Mr. Arun Felbin | TA 510FDN | 2025-05 | 7 | 2 | 3.5 | 12.43 | 7 | 100
Mr. Arun Felbin | TA 510FDN | 2025-06 | 2 | 1 | 2 | 8 | 2 | 100
Mr. Arun Felbin | TA 510FDN | 2025-08 | 1 | 1 | 1 | 67 | 1 | 100
Mr. Arun Felbin | TA 510FDN | 2025-09 | 2 | 1 | 1 | 37.5 | 2 | 100
Mr. Arun Felbin | TA 510FDN | 2025-10 | 5 | 2 | 2.5 | 16.6 | 5 | 100
Mr. Arun Felbin | TA 510FDN | 2025-11 | 5 | 4 | 1.25 | 25 | 5 | 100
Mr. Arun Felbin | TA 510FDN | 2025-12 | 10 | 6 | 1.67 | 17.8 | 10 | 100
Mr. Arun Felbin | TA 510FDN | 2026-01 | 7 | 5 | 1.4 | 15.43 | 7 | 100
Mr. Arun Felbin | TA 510FDN | 2026-02 | 6 | 5 | 1.2 | 16 | 6 | 100
Mr. Arun Felbin | TA 510FDN | 2026-03 | 4 | 2 | 2 | 27.75 | 4 | 100
Mr. Arun Felbin | TA 510FDN | 2026-04 | 8 | 3 | 2.67 | 9.88 | 8 | 100
Mr. Arun Felbin | TA 510FDN | 2026-05 | 13 | 7 | 1.86 | 13.23 | 13 | 100
Mr. Arun Felbin | TA 510FDN | 2026-06 | 7 | 4 | 1.75 | 10.43 | 7 | 100
Mr. Arun Felbin | TA 601 | 2025-08 | 2 | 0 |  |  | 0 | 0
Mr. Arun Felbin | TA 601 | 2025-09 | 2 | 0 |  |  | 0 | 0
Mr. Arun Felbin | TA 601 | 2025-10 | 8 | 0 |  |  | 0 | 0
Mr. Arun Felbin | TA 601 | 2025-11 | 10 | 0 |  |  | 0 | 0
Mr. Arun Felbin | TA 601 | 2025-12 | 23 | 0 |  |  | 0 | 0
Mr. Arun Felbin | TA 601 | 2026-01 | 48 | 0 |  |  | 0 | 0
Mr. Arun Felbin | TA 601 | 2026-02 | 46 | 0 |  |  | 0 | 0
Mr. Arun Felbin | TA 601 | 2026-03 | 28 | 0 |  |  | 0 | 0
Mr. Arun Felbin | TA 601 | 2026-04 | 16 | 0 |  |  | 0 | 0
Mr. Arun Felbin | TA 601 | 2026-05 | 12 | 0 |  |  | 0 | 0
Mr. Arun Felbin | TA 601 | 2026-06 | 12 | 0 |  |  | 0 | 0
Mr. NK Gupta | TA 413 | 2024-06 | 14 | 0 |  |  | 0 | 0
Mr. NK Gupta | TA 413 | 2024-07 | 20 | 0 |  |  | 0 | 0
Mr. NK Gupta | TA 413 | 2024-08 | 23 | 0 |  |  | 0 | 0
Mr. NK Gupta | TA 413 | 2024-09 | 40 | 0 |  |  | 0 | 0
Mr. NK Gupta | TA 413 | 2024-10 | 36 | 0 |  |  | 0 | 0
Mr. NK Gupta | TA 413 | 2024-11 | 24 | 0 |  |  | 0 | 0
Mr. NK Gupta | TA 413 | 2024-12 | 32 | 0 |  |  | 0 | 0
Mr. NK Gupta | TA 413 | 2025-01 | 35 | 0 |  |  | 0 | 0
Mr. NK Gupta | TA 413 | 2025-02 | 31 | 0 |  |  | 0 | 0
Mr. NK Gupta | TA 413 | 2025-03 | 19 | 0 |  |  | 0 | 0
Mr. NK Gupta | TA 413 | 2025-04 | 23 | 0 |  |  | 0 | 0
Mr. NK Gupta | TA 413 | 2025-05 | 10 | 0 |  |  | 0 | 0
Mr. NK Gupta | TA 413 | 2025-06 | 4 | 0 |  |  | 0 | 0
Mr. NK Gupta | TA 413 | 2025-07 | 2 | 0 |  |  | 0 | 0
Mr. NK Gupta | TA 413 | 2026-01 | 1 | 0 |  |  | 0 | 0
Mr. NK Gupta | TA 413 | 2026-02 | 1 | 0 |  |  | 0 | 0
Mr. NK Gupta | TA 413 | 2026-03 | 1 | 0 |  |  | 0 | 0
Mr. NK Gupta | TA 419 | 2024-05 | 3 | 1 | 3 | 8.5 | 2 | 66.67
Mr. NK Gupta | TA 419 | 2024-06 | 9 | 2 | 4.5 | 6.56 | 9 | 100
Mr. NK Gupta | TA 419 | 2024-07 | 17 | 3 | 5.67 | 8.12 | 17 | 100
Mr. NK Gupta | TA 419 | 2024-08 | 8 | 4 | 2 | 9.5 | 8 | 100
Mr. NK Gupta | TA 419 | 2024-09 | 16 | 5 | 3.2 | 13.19 | 16 | 100
Mr. NK Gupta | TA 419 | 2024-10 | 18 | 6 | 3 | 12.39 | 18 | 100
Mr. NK Gupta | TA 419 | 2024-11 | 14 | 7 | 2 | 17.62 | 13 | 92.86
Mr. NK Gupta | TA 419 | 2024-12 | 12 | 6 | 2 | 12.67 | 12 | 100
Mr. NK Gupta | TA 419 | 2025-01 | 7 | 4 | 1.75 | 14.71 | 7 | 100
Mr. NK Gupta | TA 419 | 2025-02 | 10 | 4 | 2.5 | 17.5 | 10 | 100
Mr. NK Gupta | TA 419 | 2025-03 | 5 | 3 | 1.67 | 8.6 | 5 | 100
Mr. NK Gupta | TA 419 | 2025-04 | 14 | 5 | 2.8 | 10.36 | 14 | 100
Mr. NK Gupta | TA 419 | 2025-05 | 8 | 4 | 2 | 10.75 | 8 | 100
Mr. NK Gupta | TA 419 | 2025-06 | 10 | 4 | 2.5 | 18.5 | 10 | 100
Mr. NK Gupta | TA 419 | 2025-07 | 5 | 3 | 1.67 | 21.2 | 5 | 100
Mr. NK Gupta | TA 419 | 2025-08 | 2 | 1 | 2 | 21 | 2 | 100
Mr. NK Gupta | TA 419 | 2025-09 | 3 | 1 | 3 | 6.33 | 3 | 100
Mr. NK Gupta | TA 419 | 2025-10 | 6 | 4 | 1.5 | 20.83 | 6 | 100
Mr. NK Gupta | TA 419 | 2025-11 | 18 | 14 | 1.29 | 15.11 | 18 | 100
Mr. NK Gupta | TA 419 | 2025-12 | 18 | 11 | 1.64 | 13.33 | 18 | 100
Mr. NK Gupta | TA 419 | 2026-01 | 12 | 9 | 1.33 | 18.27 | 11 | 91.67
Mr. NK Gupta | TA 419 | 2026-02 | 7 | 7 | 1 | 31.43 | 7 | 100
Mr. NK Gupta | TA 419 | 2026-03 | 6 | 5 | 1.2 | 39.17 | 6 | 100
Mr. NK Gupta | TA 419 | 2026-04 | 8 | 6 | 1.33 | 46.62 | 8 | 100
Mr. NK Gupta | TA 419 | 2026-05 | 19 | 13 | 1.46 | 30.21 | 19 | 100
Mr. NK Gupta | TA 419 | 2026-06 | 10 | 7 | 1.43 | 27.7 | 10 | 100
Mr. NK Gupta | TA 512 | 2025-02 | 3 | 0 |  | 10.33 | 3 | 100
Mr. NK Gupta | TA 512 | 2025-03 | 26 | 0 |  | 6.15 | 26 | 100
Mr. NK Gupta | TA 512 | 2025-04 | 24 | 0 |  | 6.38 | 24 | 100
Mr. NK Gupta | TA 512 | 2025-05 | 23 | 0 |  | 9.04 | 23 | 100
Mr. NK Gupta | TA 512 | 2025-06 | 27 | 0 |  | 7.74 | 27 | 100
Mr. NK Gupta | TA 512 | 2025-07 | 39 | 0 |  | 8.74 | 39 | 100
Mr. NK Gupta | TA 512 | 2025-08 | 26 | 0 |  | 10.04 | 26 | 100
Mr. NK Gupta | TA 512 | 2025-09 | 19 | 0 |  | 7.11 | 19 | 100
Mr. NK Gupta | TA 512 | 2025-10 | 24 | 0 |  | 8.42 | 24 | 100
Mr. NK Gupta | TA 512 | 2025-11 | 29 | 0 |  | 6.76 | 29 | 100
Mr. NK Gupta | TA 512 | 2025-12 | 36 | 0 |  | 6.69 | 36 | 100
Mr. NK Gupta | TA 512 | 2026-01 | 11 | 0 |  | 9 | 11 | 100
Mr. NK Gupta | TA 512 | 2026-02 | 4 | 0 |  | 8.75 | 4 | 100
Mr. NK Gupta | TA 512 | 2026-03 | 3 | 0 |  | 7.67 | 3 | 100
Mr. NK Gupta | TA 512 | 2026-04 | 7 | 0 |  | 20.29 | 7 | 100
Mr. NK Gupta | TA 512 | 2026-05 | 5 | 0 |  | 11.2 | 5 | 100
Mr. NK Gupta | TA 512 | 2026-06 | 4 | 0 |  | 23.75 | 4 | 100
Mr. NK Gupta | TA 513SF | 2025-03 | 1 | 0 |  | 7 | 1 | 100
Mr. NK Gupta | TA 513SF | 2025-04 | 11 | 0 |  | 5.73 | 11 | 100
Mr. NK Gupta | TA 513SF | 2025-05 | 3 | 0 |  | 3.33 | 3 | 100
Mr. NK Gupta | TA 513SF | 2025-06 | 1 | 0 |  | 9 | 1 | 100
Mr. NK Gupta | TA 513SF | 2025-09 | 4 | 0 |  | 5.75 | 4 | 100
Mr. NK Gupta | TA 513SF | 2025-10 | 3 | 0 |  | 5.33 | 3 | 100
Mr. NK Gupta | TA 513SF | 2026-05 | 2 | 0 |  | 10 | 2 | 100
Mr. NK Gupta | TA 513SF | 2026-06 | 1 | 0 |  | 13 | 1 | 100
Mr. NK Gupta | TA 513SP | 2025-04 | 3 | 0 |  | 3.67 | 3 | 100
Mr. NK Gupta | TA 513SP | 2025-05 | 12 | 0 |  | 4.08 | 12 | 100
Mr. NK Gupta | TA 513SP | 2025-06 | 7 | 0 |  | 5.57 | 7 | 100
Mr. NK Gupta | TA 513SP | 2025-07 | 11 | 0 |  | 6.3 | 10 | 90.91
Mr. NK Gupta | TA 513SP | 2025-08 | 3 | 0 |  | 17.33 | 3 | 100
Mr. NK Gupta | TA 513SP | 2025-09 | 3 | 0 |  | 19.67 | 3 | 100
Mr. NK Gupta | TA 513SP | 2025-11 | 2 | 0 |  | 14.5 | 2 | 100
Mr. NK Gupta | TA 513SP | 2025-12 | 5 | 0 |  | 27.4 | 5 | 100
Mr. NK Gupta | TA 513SP | 2026-02 | 2 | 0 |  | 16 | 2 | 100
Mr. NK Gupta | TA 513SP | 2026-03 | 1 | 0 |  | 9 | 1 | 100
Mr. NK Gupta | TA 513SP | 2026-04 | 1 | 0 |  | 15 | 1 | 100
Mr. NK Gupta | TA 513SP | 2026-05 | 14 | 0 |  | 112.07 | 14 | 100
Mr. NK Gupta | TA 513SP | 2026-06 | 6 | 0 |  | 9.17 | 6 | 100
Mr. NK Gupta | TB 408 | 2023-10 | 1 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 408 | 2023-12 | 22 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 408 | 2024-01 | 46 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 408 | 2024-02 | 36 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 408 | 2024-03 | 16 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 408 | 2024-04 | 7 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 408 | 2024-05 | 15 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 408 | 2024-06 | 9 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 408 | 2024-07 | 14 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 408 | 2024-08 | 26 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 408 | 2024-09 | 38 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 408 | 2024-10 | 26 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 408 | 2024-11 | 9 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 408 | 2024-12 | 31 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 408 | 2025-01 | 47 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 408 | 2025-02 | 27 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 408 | 2025-03 | 17 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 408 | 2025-04 | 13 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 408 | 2025-05 | 13 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 408 | 2025-06 | 19 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 408 | 2025-07 | 22 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 408 | 2025-08 | 8 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 408 | 2025-09 | 9 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 408 | 2025-10 | 7 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 408 | 2025-11 | 3 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 408 | 2026-02 | 3 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 408 | 2026-03 | 1 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 507765KV | 2025-05 | 1 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 507765KV | 2026-02 | 7 | 0 |  | 7.29 | 7 | 100
Mr. NK Gupta | TB 507765KV | 2026-03 | 8 | 0 |  | 7.71 | 7 | 87.5
Mr. NK Gupta | TB 507765KV | 2026-04 | 7 | 0 |  | 10.86 | 7 | 100
Mr. NK Gupta | TB 507765KV | 2026-05 | 11 | 0 |  | 18.18 | 11 | 100
Mr. NK Gupta | TB 507765KV | 2026-06 | 2 | 0 |  | 15.5 | 2 | 100
Mr. NK Gupta | TB 507MAIN | 2025-01 | 2 | 0 |  | 10 | 2 | 100
Mr. NK Gupta | TB 507MAIN | 2025-02 | 20 | 0 |  | 7.16 | 19 | 95
Mr. NK Gupta | TB 507MAIN | 2025-03 | 16 | 0 |  | 8.25 | 16 | 100
Mr. NK Gupta | TB 507MAIN | 2025-04 | 13 | 0 |  | 8.85 | 13 | 100
Mr. NK Gupta | TB 507MAIN | 2025-05 | 9 | 0 |  | 14.22 | 9 | 100
Mr. NK Gupta | TB 507MAIN | 2025-06 | 25 | 0 |  | 7.88 | 24 | 96
Mr. NK Gupta | TB 507MAIN | 2025-07 | 50 | 0 |  | 8.14 | 50 | 100
Mr. NK Gupta | TB 507MAIN | 2025-08 | 52 | 0 |  | 16.5 | 52 | 100
Mr. NK Gupta | TB 507MAIN | 2025-09 | 20 | 0 |  | 11.85 | 20 | 100
Mr. NK Gupta | TB 507MAIN | 2025-10 | 8 | 0 |  | 11.25 | 8 | 100
Mr. NK Gupta | TB 507MAIN | 2025-11 | 19 | 0 |  | 13.32 | 19 | 100
Mr. NK Gupta | TB 507MAIN | 2025-12 | 13 | 0 |  | 8.62 | 13 | 100
Mr. NK Gupta | TB 507MAIN | 2026-01 | 15 | 0 |  | 6.53 | 15 | 100
Mr. NK Gupta | TB 507MAIN | 2026-02 | 5 | 0 |  | 6.4 | 5 | 100
Mr. NK Gupta | TB 507MAIN | 2026-03 | 9 | 0 |  | 10.67 | 9 | 100
Mr. NK Gupta | TB 507MAIN | 2026-04 | 13 | 0 |  | 6.77 | 13 | 100
Mr. NK Gupta | TB 507MAIN | 2026-05 | 19 | 0 |  | 9.95 | 19 | 100
Mr. NK Gupta | TB 507MAIN | 2026-06 | 8 | 0 |  | 5.75 | 8 | 100
Mr. NK Gupta | TB 605JAMMU | 2025-08 | 1 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 605JAMMU | 2025-09 | 3 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 605JAMMU | 2025-10 | 7 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 605JAMMU | 2025-11 | 12 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 605JAMMU | 2025-12 | 17 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 605JAMMU | 2026-01 | 15 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 605JAMMU | 2026-02 | 12 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 605JAMMU | 2026-03 | 13 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 605JAMMU | 2026-04 | 10 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 605JAMMU | 2026-05 | 10 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 605JAMMU | 2026-06 | 8 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 605LILO | 2026-05 | 1 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 605PUNJAB | 2025-10 | 8 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 605PUNJAB | 2025-11 | 30 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 605PUNJAB | 2025-12 | 40 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 605PUNJAB | 2026-01 | 27 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 605PUNJAB | 2026-02 | 30 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 605PUNJAB | 2026-03 | 15 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 605PUNJAB | 2026-04 | 16 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 605PUNJAB | 2026-05 | 44 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 605PUNJAB | 2026-06 | 13 | 0 |  |  | 0 | 0
Mr. NK Gupta | TB 608 | 2025-10 | 2 | 0 |  | 12.5 | 2 | 100
Mr. NK Gupta | TB 608 | 2025-11 | 20 | 0 |  | 19.15 | 20 | 100
Mr. NK Gupta | TB 608 | 2025-12 | 34 | 0 |  | 17.79 | 34 | 100
Mr. NK Gupta | TB 608 | 2026-01 | 30 | 0 |  | 21 | 30 | 100
Mr. NK Gupta | TB 608 | 2026-02 | 30 | 0 |  | 16.6 | 30 | 100
Mr. NK Gupta | TB 608 | 2026-03 | 17 | 0 |  | 18.71 | 17 | 100
Mr. NK Gupta | TB 608 | 2026-04 | 8 | 0 |  | 16.62 | 8 | 100
Mr. NK Gupta | TB 608 | 2026-05 | 12 | 0 |  | 17.58 | 12 | 100
Mr. NK Gupta | TB 608 | 2026-06 | 2 | 0 |  | 27.5 | 2 | 100
Mr. Nabajit Baruah | TA 505 | 2015-11 | 1 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TA 505 | 2024-03 | 1 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TA 505 | 2024-04 | 2 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TA 505 | 2024-10 | 9 | 0 |  | 4 | 9 | 100
Mr. Nabajit Baruah | TA 505 | 2024-11 | 26 | 0 |  | 3.12 | 26 | 100
Mr. Nabajit Baruah | TA 505 | 2024-12 | 36 | 0 |  | 4.14 | 36 | 100
Mr. Nabajit Baruah | TA 505 | 2025-01 | 30 | 0 |  | 2.93 | 30 | 100
Mr. Nabajit Baruah | TA 505 | 2025-02 | 32 | 0 |  | 4.5 | 32 | 100
Mr. Nabajit Baruah | TA 505 | 2025-03 | 21 | 0 |  | 1.75 | 4 | 19.05
Mr. Nabajit Baruah | TA 505 | 2025-04 | 48 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TA 505 | 2025-05 | 47 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TA 505 | 2025-06 | 15 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TA 505 | 2025-07 | 2 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TA 505 | 2025-08 | 1 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TA 505 | 2025-09 | 10 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TA 505 | 2025-10 | 12 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TA 505 | 2025-11 | 16 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TA 505 | 2025-12 | 18 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TA 505 | 2026-01 | 17 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TA 505 | 2026-02 | 10 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TA 505 | 2026-03 | 8 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TA 505 | 2026-04 | 8 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TA 505 | 2026-05 | 4 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TA 505 | 2026-06 | 1 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TB 501132KV | 2025-07 | 1 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TB 501132KV | 2025-10 | 2 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TB 501132KV | 2025-11 | 2 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TB 501132KV | 2025-12 | 8 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TB 501132KV | 2026-01 | 9 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TB 501132KV | 2026-02 | 3 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TB 501132KV | 2026-03 | 4 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TB 501132KV | 2026-04 | 2 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TB 501220KV | 2024-08 | 3 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TB 501220KV | 2024-09 | 7 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TB 501220KV | 2024-10 | 25 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TB 501220KV | 2024-11 | 26 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TB 501220KV | 2024-12 | 27 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TB 501220KV | 2025-01 | 21 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TB 501220KV | 2025-02 | 21 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TB 501220KV | 2025-03 | 9 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TB 501220KV | 2025-04 | 11 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TB 501220KV | 2025-05 | 18 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TB 501220KV | 2025-06 | 6 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TB 501220KV | 2025-08 | 3 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TB 501220KV | 2025-09 | 8 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TB 501220KV | 2025-10 | 4 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TB 501220KV | 2025-11 | 5 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TB 501220KV | 2025-12 | 2 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TB 501220KV | 2026-02 | 1 | 0 |  |  | 0 | 0
Mr. Nabajit Baruah | TB 501220KV | 2026-04 | 3 | 0 |  |  | 0 | 0

## Gang Monthly Productivity
PCH | Project | Month | Gang | Foundations Completed | Avg Duration Days | Valid Duration Foundations
Mr. Arun Felbin | TA 414 | 2024-05 | Suraj Construction | 2 | 10.5 | 2
Mr. Arun Felbin | TA 414 | 2024-10 | Anya Infra | 1 | 42 | 1
Mr. Arun Felbin | TA 414 | 2024-11 | Adhyey Brothers | 2 | 14.5 | 2
Mr. Arun Felbin | TA 414 | 2024-11 | Anya Infra | 2 | 11.5 | 2
Mr. Arun Felbin | TA 414 | 2024-12 | APR Associates | 1 | 23 | 1
Mr. Arun Felbin | TA 414 | 2024-12 | Adhya Enterprises | 1 | 13 | 1
Mr. Arun Felbin | TA 414 | 2024-12 | Adhyey Brothers | 1 | 7 | 1
Mr. Arun Felbin | TA 414 | 2024-12 | Arya Enterprises | 1 | 15 | 1
Mr. Arun Felbin | TA 414 | 2024-12 | Himanshi Agency | 4 | 14.25 | 4
Mr. Arun Felbin | TA 414 | 2024-12 | Integer Infratech Pvt Ltd | 1 | 17 | 1
Mr. Arun Felbin | TA 414 | 2024-12 | Khodiyarkrupa | 1 |  | 0
Mr. Arun Felbin | TA 414 | 2024-12 | Neelkant Infra Project | 1 | 9 | 1
Mr. Arun Felbin | TA 414 | 2024-12 | Unnati Construction | 1 | 11 | 1
Mr. Arun Felbin | TA 414 | 2025-01 | APR Associates | 1 | 31 | 1
Mr. Arun Felbin | TA 414 | 2025-01 | Adhya Brother | 1 | 15 | 1
Mr. Arun Felbin | TA 414 | 2025-01 | Arya Enterprises | 2 | 15.5 | 2
Mr. Arun Felbin | TA 414 | 2025-01 | Himanshi Agency | 3 | 6.33 | 3
Mr. Arun Felbin | TA 414 | 2025-01 | Integer Infratech Pvt Ltd | 2 | 13.5 | 2
Mr. Arun Felbin | TA 414 | 2025-01 | Neelkant Infra Project | 4 | 8.25 | 4
Mr. Arun Felbin | TA 414 | 2025-01 | Tower Foundation | 1 |  | 0
Mr. Arun Felbin | TA 414 | 2025-01 | Unnati Construction | 3 | 10.33 | 3
Mr. Arun Felbin | TA 414 | 2025-02 | Adhya Brother | 2 | 19 | 2
Mr. Arun Felbin | TA 414 | 2025-02 | Arya Enterprises | 2 | 15.5 | 2
Mr. Arun Felbin | TA 414 | 2025-02 | Himanshi Agency | 9 | 10.86 | 7
Mr. Arun Felbin | TA 414 | 2025-02 | Integer Infratech Pvt Ltd | 1 | 12 | 1
Mr. Arun Felbin | TA 414 | 2025-02 | Neelkant Infra Project | 2 | 8 | 2
Mr. Arun Felbin | TA 414 | 2025-02 | Unnati Construction | 4 | 8.5 | 4
Mr. Arun Felbin | TA 414 | 2025-03 | Adhya Brother | 1 | 7 | 1
Mr. Arun Felbin | TA 414 | 2025-03 | Himanshi Agency | 5 | 14.8 | 5
Mr. Arun Felbin | TA 414 | 2025-03 | Jyoti Construction | 1 | 27 | 1
Mr. Arun Felbin | TA 414 | 2025-03 | Neelkant Infra Project | 2 | 11.5 | 2
Mr. Arun Felbin | TA 414 | 2025-03 | Unnati Construction | 1 | 13 | 1
Mr. Arun Felbin | TA 414 | 2025-04 | Adhya Brother | 1 | 27 | 1
Mr. Arun Felbin | TA 414 | 2025-04 | Himanshi Agency | 6 | 9.17 | 6
Mr. Arun Felbin | TA 414 | 2025-04 | Jyoti Construction | 4 | 12.75 | 4
Mr. Arun Felbin | TA 414 | 2025-04 | Neelkant Infra Project | 2 | 15 | 2
Mr. Arun Felbin | TA 414 | 2025-04 | Sai guru Construction | 2 | 17.5 | 2
Mr. Arun Felbin | TA 414 | 2025-04 | Unnati Construction | 3 | 14 | 3
Mr. Arun Felbin | TA 414 | 2025-05 | Himanshi Agency | 2 | 24 | 2
Mr. Arun Felbin | TA 414 | 2025-05 | Jyoti Construction | 1 | 6 | 1
Mr. Arun Felbin | TA 414 | 2025-05 | Sai guru Construction | 1 | 8 | 1
Mr. Arun Felbin | TA 414 | 2025-05 | Unnati Construction | 1 | 16 | 1
Mr. Arun Felbin | TA 414 | 2025-06 | Sai guru Construction | 1 | 18 | 1
Mr. Arun Felbin | TA 414 | 2025-06 | Unnati Construction | 1 | 27 | 1
Mr. Arun Felbin | TA 414 | 2025-08 | Khodiyarkrupa | 1 | 20 | 1
Mr. Arun Felbin | TA 414 | 2025-09 | Khodiyarkrupa | 1 | 14 | 1
Mr. Arun Felbin | TA 414 | 2025-09 | Murugan | 1 | 42 | 1
Mr. Arun Felbin | TA 414 | 2025-09 | Saiguru Construction | 1 | 38 | 1
Mr. Arun Felbin | TA 414 | 2025-10 | Himanshi Agency | 2 | 10 | 2
Mr. Arun Felbin | TA 414 | 2025-10 | Jyoti Construction | 3 | 29.33 | 3
Mr. Arun Felbin | TA 414 | 2025-10 | Khodiyarkrupa | 3 | 12 | 3
Mr. Arun Felbin | TA 414 | 2025-11 | BLG Construction | 2 | 9 | 2
Mr. Arun Felbin | TA 414 | 2025-11 | Himanshi Agency | 4 | 16 | 4
Mr. Arun Felbin | TA 414 | 2025-11 | Jyoti Construction | 3 | 18.33 | 3
Mr. Arun Felbin | TA 414 | 2025-11 | Khodiyar Trader | 1 | 12 | 1
Mr. Arun Felbin | TA 414 | 2025-11 | Khodiyarkrupa | 1 | 16 | 1
Mr. Arun Felbin | TA 414 | 2025-11 | Khodiyarkrupa-1 | 1 | 15 | 1
Mr. Arun Felbin | TA 414 | 2025-11 | Khodiyarkrupa-2 | 2 | 12.5 | 2
Mr. Arun Felbin | TA 414 | 2025-11 | Murugan Gang | 2 | 19 | 2
Mr. Arun Felbin | TA 414 | 2025-11 | Sai guru Construction | 1 | 11 | 1
Mr. Arun Felbin | TA 414 | 2025-11 | Saiguru Construction | 2 | 4.5 | 2
Mr. Arun Felbin | TA 414 | 2025-11 | Shivkripa | 1 | 14 | 1
Mr. Arun Felbin | TA 414 | 2025-11 | Tower Foundation | 3 | 18.33 | 3
Mr. Arun Felbin | TA 414 | 2025-11 | Tuuasta | 1 | 15 | 1
Mr. Arun Felbin | TA 414 | 2025-12 | A P Developers | 1 | 18 | 1
Mr. Arun Felbin | TA 414 | 2025-12 | BLG Construction | 4 | 9.5 | 4
Mr. Arun Felbin | TA 414 | 2025-12 | Deep Power | 1 | 16 | 1
Mr. Arun Felbin | TA 414 | 2025-12 | Deep Power 1 | 1 | 14 | 1
Mr. Arun Felbin | TA 414 | 2025-12 | Deep Power 2 | 1 | 17 | 1
Mr. Arun Felbin | TA 414 | 2025-12 | Dev Construction | 3 | 12 | 3
Mr. Arun Felbin | TA 414 | 2025-12 | Himanshi Agency | 4 | 13 | 4
Mr. Arun Felbin | TA 414 | 2025-12 | Jayesh Electrical | 2 | 13 | 2
Mr. Arun Felbin | TA 414 | 2025-12 | Jyoti | 2 | 7.5 | 2
Mr. Arun Felbin | TA 414 | 2025-12 | Jyoti Construction | 3 | 12.67 | 3
Mr. Arun Felbin | TA 414 | 2025-12 | Kasta Bhanjan | 1 | 21 | 1
Mr. Arun Felbin | TA 414 | 2025-12 | Khodiyar 1 | 1 | 11 | 1
Mr. Arun Felbin | TA 414 | 2025-12 | Khodiyar Kripa Enterprise | 1 | 8 | 1
Mr. Arun Felbin | TA 414 | 2025-12 | Khodiyar Trader | 1 | 11 | 1
Mr. Arun Felbin | TA 414 | 2025-12 | Khodiyar Traders | 1 | 8 | 1
Mr. Arun Felbin | TA 414 | 2025-12 | Khodiyarkrupa | 3 | 8.33 | 3
Mr. Arun Felbin | TA 414 | 2025-12 | Khodiyarkrupa-2 | 1 | 21 | 1
Mr. Arun Felbin | TA 414 | 2025-12 | Krishna Construction | 1 | 15 | 1
Mr. Arun Felbin | TA 414 | 2025-12 | Murgun | 1 | 7 | 1
Mr. Arun Felbin | TA 414 | 2025-12 | Murugan Gang | 1 | 10 | 1
Mr. Arun Felbin | TA 414 | 2025-12 | Saiguru 2 | 1 | 12 | 1
Mr. Arun Felbin | TA 414 | 2025-12 | Saiguru Construction | 3 | 6.67 | 3
Mr. Arun Felbin | TA 414 | 2025-12 | Selva Murugan | 1 | 7 | 1
Mr. Arun Felbin | TA 414 | 2025-12 | Shiv Kripa Infra | 1 | 17 | 1
Mr. Arun Felbin | TA 414 | 2025-12 | Suraj Construction | 1 | 583 | 1
Mr. Arun Felbin | TA 414 | 2025-12 | Tower Foundation | 2 | 20 | 2
Mr. Arun Felbin | TA 414 | 2025-12 | Twaasta | 1 | 19 | 1
Mr. Arun Felbin | TA 414 | 2025-12 | Twasta | 1 | 16 | 1
Mr. Arun Felbin | TA 414 | 2025-12 | Unnati Construction | 2 | 9.5 | 2
Mr. Arun Felbin | TA 414 | 2025-12 | Velu Construction | 2 | 5 | 2
Mr. Arun Felbin | TA 414 | 2025-12 | Veluu | 1 | 11 | 1
Mr. Arun Felbin | TA 414 | 2026-01 | AP Developers | 2 | 29.5 | 2
Mr. Arun Felbin | TA 414 | 2026-01 | BLG | 2 | 12 | 2
Mr. Arun Felbin | TA 414 | 2026-01 | BLG (197/1) | 1 | 13 | 1
Mr. Arun Felbin | TA 414 | 2026-01 | BLG Construction | 1 | 20 | 1
Mr. Arun Felbin | TA 414 | 2026-01 | Deep Power | 1 | 18 | 1
Mr. Arun Felbin | TA 414 | 2026-01 | Deep Power 1 | 1 | 10 | 1
Mr. Arun Felbin | TA 414 | 2026-01 | Deep Power 2 | 1 | 42 | 1
Mr. Arun Felbin | TA 414 | 2026-01 | Dev Construction | 1 | 14 | 1
Mr. Arun Felbin | TA 414 | 2026-01 | Dev Contruction | 1 | 16 | 1
Mr. Arun Felbin | TA 414 | 2026-01 | Himanshi | 6 | 19.83 | 6
Mr. Arun Felbin | TA 414 | 2026-01 | Himanshi 1 | 1 | 33 | 1
Mr. Arun Felbin | TA 414 | 2026-01 | Himanshi 2 | 1 | 14 | 1
Mr. Arun Felbin | TA 414 | 2026-01 | Jyoti | 3 | 8 | 3
Mr. Arun Felbin | TA 414 | 2026-01 | Jyoti 1 | 1 | 16 | 1
Mr. Arun Felbin | TA 414 | 2026-01 | Jyoti 3 | 2 | 12 | 2
Mr. Arun Felbin | TA 414 | 2026-01 | Jyoti Construction 2 | 1 | 97 | 1
Mr. Arun Felbin | TA 414 | 2026-01 | Kasta Bhanjan | 1 | 20 | 1
Mr. Arun Felbin | TA 414 | 2026-01 | Khodiyarkrupa | 3 | 22.67 | 3
Mr. Arun Felbin | TA 414 | 2026-01 | Krishna Construction | 2 | 15 | 2
Mr. Arun Felbin | TA 414 | 2026-01 | Murgun | 1 | 40 | 1
Mr. Arun Felbin | TA 414 | 2026-01 | Om Construction | 1 | 26 | 1
Mr. Arun Felbin | TA 414 | 2026-01 | Om Enterprise | 2 | 14 | 2
Mr. Arun Felbin | TA 414 | 2026-01 | Saiguru | 1 | 9 | 1
Mr. Arun Felbin | TA 414 | 2026-01 | Saiguru 1 | 1 | 36 | 1
Mr. Arun Felbin | TA 414 | 2026-01 | Saiguru 2 | 2 | 12.5 | 2
Mr. Arun Felbin | TA 414 | 2026-01 | Shiv krupa Infra | 1 | 45 | 1
Mr. Arun Felbin | TA 414 | 2026-01 | Shivkrupa | 1 | 14 | 1
Mr. Arun Felbin | TA 414 | 2026-01 | Tower Foundation | 3 | 14 | 3
Mr. Arun Felbin | TA 414 | 2026-01 | Unnati Construction | 2 | 31.5 | 2
Mr. Arun Felbin | TA 414 | 2026-01 | Velu | 2 | 16 | 2
Mr. Arun Felbin | TA 414 | 2026-02 | BLG | 2 | 10 | 2
Mr. Arun Felbin | TA 414 | 2026-02 | Deep Power | 2 | 32.5 | 2
Mr. Arun Felbin | TA 414 | 2026-02 | Dev Construction | 2 | 8 | 2
Mr. Arun Felbin | TA 414 | 2026-02 | Himanshi | 3 | 15.33 | 3
Mr. Arun Felbin | TA 414 | 2026-02 | Jyoti | 1 | 47 | 1
Mr. Arun Felbin | TA 414 | 2026-02 | Jyoti 2 | 1 | 63 | 1
Mr. Arun Felbin | TA 414 | 2026-02 | Khodiyar | 1 | 9 | 1
Mr. Arun Felbin | TA 414 | 2026-02 | Krishna | 2 | 9.5 | 2
Mr. Arun Felbin | TA 414 | 2026-02 | Krishna Construction | 1 | 13 | 1
Mr. Arun Felbin | TA 414 | 2026-02 | Saiguru | 3 | 10.67 | 3
Mr. Arun Felbin | TA 414 | 2026-02 | Saiguru 1 | 1 | 45 | 1
Mr. Arun Felbin | TA 414 | 2026-02 | Tower Foundation | 2 | 8.5 | 2
Mr. Arun Felbin | TA 414 | 2026-02 | Unnati | 2 | 15.5 | 2
Mr. Arun Felbin | TA 414 | 2026-02 | Unnati Construction | 1 | 532 | 1
Mr. Arun Felbin | TA 414 | 2026-02 | Velu (213/0) | 1 | 19 | 1
Mr. Arun Felbin | TA 414 | 2026-03 | BLG | 2 | 6.5 | 2
Mr. Arun Felbin | TA 414 | 2026-03 | Dev Construction | 1 | 25 | 1
Mr. Arun Felbin | TA 414 | 2026-03 | Himanshi | 1 | 21 | 1
Mr. Arun Felbin | TA 414 | 2026-03 | Jyoti | 1 | 9 | 1
Mr. Arun Felbin | TA 414 | 2026-03 | Krishna | 4 | 13 | 4
Mr. Arun Felbin | TA 414 | 2026-03 | Sai guru Construction | 1 | 16 | 1
Mr. Arun Felbin | TA 414 | 2026-03 | Saiguru | 3 | 12.33 | 3
Mr. Arun Felbin | TA 414 | 2026-03 | Saiguru-2 | 1 | 9 | 1
Mr. Arun Felbin | TA 414 | 2026-03 | Shivkrupa | 2 | 12 | 2
Mr. Arun Felbin | TA 414 | 2026-03 | Tower Foundation | 3 | 21 | 3
Mr. Arun Felbin | TA 414 | 2026-03 | Unnati | 3 | 11.33 | 3
Mr. Arun Felbin | TA 414 | 2026-03 | Unnati Construction | 1 | 33 | 1
Mr. Arun Felbin | TA 414 | 2026-03 | khodiyar | 1 | 15 | 1
Mr. Arun Felbin | TA 414 | 2026-04 | Jyoti | 1 | 35 | 1
Mr. Arun Felbin | TA 414 | 2026-04 | Jyoti 1 | 2 | 7 | 2
Mr. Arun Felbin | TA 414 | 2026-04 | Jyoti 2 | 2 | 13.5 | 2
Mr. Arun Felbin | TA 414 | 2026-04 | Jyoti Const | 1 | 24 | 1
Mr. Arun Felbin | TA 414 | 2026-04 | Khodiyar Krupa | 1 | 19 | 1
Mr. Arun Felbin | TA 414 | 2026-04 | Khodiyarkripa | 2 | 14.5 | 2
Mr. Arun Felbin | TA 414 | 2026-04 | Khodiyarkrupa | 1 | 101 | 1
Mr. Arun Felbin | TA 414 | 2026-04 | Sai guru Construction | 1 | 24 | 1
Mr. Arun Felbin | TA 414 | 2026-04 | Tower Founadation | 1 | 13 | 1
Mr. Arun Felbin | TA 414 | 2026-04 | Tower Foundation | 2 | 19 | 2
Mr. Arun Felbin | TA 414 | 2026-05 | Arya Implex | 1 | 38 | 1
Mr. Arun Felbin | TA 414 | 2026-05 | Himanshi | 2 | 25 | 2
Mr. Arun Felbin | TA 414 | 2026-05 | Himanshi Agency | 1 | 18 | 1
Mr. Arun Felbin | TA 414 | 2026-05 | Jyoti Contruction | 1 | 11 | 1
Mr. Arun Felbin | TA 414 | 2026-05 | KND | 1 | 109 | 1
Mr. Arun Felbin | TA 414 | 2026-05 | Khodiyar | 1 | 12 | 1
Mr. Arun Felbin | TA 414 | 2026-05 | Sai guru Construction | 1 | 13 | 1
Mr. Arun Felbin | TA 414 | 2026-05 | Saiguru | 1 | 35 | 1
Mr. Arun Felbin | TA 414 | 2026-05 | Shivkrupa | 2 | 15.5 | 2
Mr. Arun Felbin | TA 414 | 2026-05 | Tower Founadation | 1 | 11 | 1
Mr. Arun Felbin | TA 414 | 2026-05 | Tower Foundation | 1 | 8 | 1
Mr. Arun Felbin | TA 414 | 2026-05 | jyoti const 2 | 2 | 64 | 2
Mr. Arun Felbin | TA 414 | 2026-06 | Harshvi | 1 | 399 | 1
Mr. Arun Felbin | TA 414 | 2026-06 | Himanshi | 1 | 43 | 1
Mr. Arun Felbin | TA 414 | 2026-06 | Jyoti 1 | 1 | 10 | 1
Mr. Arun Felbin | TA 414 | 2026-06 | Jyoti 2 | 2 | 20.5 | 2
Mr. Arun Felbin | TA 414 | 2026-06 | Jyoti 3 | 2 | 11.5 | 2
Mr. Arun Felbin | TA 414 | 2026-06 | Khodiyar | 1 | 137 | 1
Mr. Arun Felbin | TA 414 | 2026-06 | Shivkrupa | 1 | 11 | 1
Mr. Arun Felbin | TA 416 | 2024-05 | Sumit Constrcution | 6 | 8 | 6
Mr. Arun Felbin | TA 416 | 2024-06 | Anshika con. | 2 | 10 | 2
Mr. Arun Felbin | TA 416 | 2024-06 | Dharamdas Contractor | 5 | 6.6 | 5
Mr. Arun Felbin | TA 416 | 2024-06 | Khalil Const. | 3 | 8 | 3
Mr. Arun Felbin | TA 416 | 2024-06 | Sumit Constrcution | 7 | 5.71 | 7
Mr. Arun Felbin | TA 416 | 2024-07 | Anshika con. | 4 | 10.5 | 4
Mr. Arun Felbin | TA 416 | 2024-07 | Jay Sri Ram | 2 | 9.5 | 2
Mr. Arun Felbin | TA 416 | 2024-07 | K R Associates | 1 | 12 | 1
Mr. Arun Felbin | TA 416 | 2024-07 | SSR engineering | 2 | 7.5 | 2
Mr. Arun Felbin | TA 416 | 2024-07 | VH Rajpoot cont. | 1 | 10 | 1
Mr. Arun Felbin | TA 416 | 2024-08 | Anshika con. | 2 | 7 | 1
Mr. Arun Felbin | TA 416 | 2024-08 | J M Enterprise | 1 | 9 | 1
Mr. Arun Felbin | TA 416 | 2024-08 | K R Associates | 2 | 10.5 | 2
Mr. Arun Felbin | TA 416 | 2024-08 | SSR engineering | 3 | 10.67 | 3
Mr. Arun Felbin | TA 416 | 2024-08 | VED ENTTERPRISE | 1 | 16 | 1
Mr. Arun Felbin | TA 416 | 2024-08 | VH Rajpoot cont. | 4 | 6.75 | 4
Mr. Arun Felbin | TA 416 | 2024-09 | A V I ENTERPRISE | 2 | 12 | 2
Mr. Arun Felbin | TA 416 | 2024-09 | Dewi Construction(Girendra) | 2 | 15 | 2
Mr. Arun Felbin | TA 416 | 2024-09 | Dharamdas Contractor | 3 | 10.33 | 3
Mr. Arun Felbin | TA 416 | 2024-09 | Garg Construction | 3 | 12.33 | 3
Mr. Arun Felbin | TA 416 | 2024-09 | J M Enterprise | 2 | 14.5 | 2
Mr. Arun Felbin | TA 416 | 2024-09 | K R Associates | 1 | 24 | 1
Mr. Arun Felbin | TA 416 | 2024-09 | Laxmi Const. | 1 | 6 | 1
Mr. Arun Felbin | TA 416 | 2024-09 | MALLIK CON | 1 | 38 | 1
Mr. Arun Felbin | TA 416 | 2024-09 | SAIFI CON. | 3 | 17 | 3
Mr. Arun Felbin | TA 416 | 2024-09 | SSR engineering | 3 | 10.33 | 3
Mr. Arun Felbin | TA 416 | 2024-09 | Shree Krishna | 1 | 30 | 1
Mr. Arun Felbin | TA 416 | 2024-09 | VED ENTTERPRISE | 2 | 8.5 | 2
Mr. Arun Felbin | TA 416 | 2024-09 | VH Rajpoot cont. | 4 | 6 | 4
Mr. Arun Felbin | TA 416 | 2024-09 | Vinayak Enterprise | 2 | 18.5 | 2
Mr. Arun Felbin | TA 416 | 2024-09 | Vishal construction | 1 | 19 | 1
Mr. Arun Felbin | TA 416 | 2024-10 | A V I ENTERPRISE | 4 | 6.25 | 4
Mr. Arun Felbin | TA 416 | 2024-10 | Aneshwar Traders | 6 | 5.83 | 6
Mr. Arun Felbin | TA 416 | 2024-10 | Dewi Construction(Girendra) | 5 | 6 | 5
Mr. Arun Felbin | TA 416 | 2024-10 | Dharamdas Contractor | 2 | 7.5 | 2
Mr. Arun Felbin | TA 416 | 2024-10 | Garg Construction | 3 | 7.33 | 3
Mr. Arun Felbin | TA 416 | 2024-10 | Horil Mahto | 4 | 11.75 | 4
Mr. Arun Felbin | TA 416 | 2024-10 | J M Enterprise | 1 | 8 | 1
Mr. Arun Felbin | TA 416 | 2024-10 | K R Associates | 1 | 10 | 1
Mr. Arun Felbin | TA 416 | 2024-10 | Laxmi Const. | 5 | 4.8 | 5
Mr. Arun Felbin | TA 416 | 2024-10 | M A Construction | 4 | 5.25 | 4
Mr. Arun Felbin | TA 416 | 2024-10 | Maa Durga | 3 | 9.33 | 3
Mr. Arun Felbin | TA 416 | 2024-10 | SAIFI CON. | 3 | 8 | 3
Mr. Arun Felbin | TA 416 | 2024-10 | SSR engineering | 4 | 5.75 | 4
Mr. Arun Felbin | TA 416 | 2024-10 | VED ENTTERPRISE | 4 | 6.5 | 4
Mr. Arun Felbin | TA 416 | 2024-10 | VH Rajpoot cont. | 5 | 5.6 | 5
Mr. Arun Felbin | TA 416 | 2024-10 | Vinayak Enterprise | 2 | 20 | 2
Mr. Arun Felbin | TA 416 | 2024-10 | Vishal construction | 1 | 9 | 1
Mr. Arun Felbin | TA 416 | 2024-10 | Vivan Enterprise | 2 | 5.5 | 2
Mr. Arun Felbin | TA 416 | 2024-11 | A V I ENTERPRISE | 3 | 6.67 | 3
Mr. Arun Felbin | TA 416 | 2024-11 | Amar Singh | 1 | 20 | 1
Mr. Arun Felbin | TA 416 | 2024-11 | Aneshwar Traders | 4 | 8.75 | 4
Mr. Arun Felbin | TA 416 | 2024-11 | Dewi Construction(Girendra) | 5 | 6.2 | 5
Mr. Arun Felbin | TA 416 | 2024-11 | Dharamdas Contractor | 2 | 8.5 | 2
Mr. Arun Felbin | TA 416 | 2024-11 | Garg Construction | 4 | 7.5 | 4
Mr. Arun Felbin | TA 416 | 2024-11 | Horil Mahto | 2 | 15 | 2
Mr. Arun Felbin | TA 416 | 2024-11 | J M Enterprise | 2 | 8 | 2
Mr. Arun Felbin | TA 416 | 2024-11 | K R Associates | 3 | 9 | 3
Mr. Arun Felbin | TA 416 | 2024-11 | Laxmi Const. | 5 | 7.6 | 5
Mr. Arun Felbin | TA 416 | 2024-11 | M A Construction | 4 | 7.5 | 4
Mr. Arun Felbin | TA 416 | 2024-11 | Maa Durga | 2 | 10.5 | 2
Mr. Arun Felbin | TA 416 | 2024-11 | Pankaj | 1 | 15 | 1
Mr. Arun Felbin | TA 416 | 2024-11 | Pinky Dewi | 1 | 12 | 1
Mr. Arun Felbin | TA 416 | 2024-11 | R K Constrcution | 2 | 8 | 2
Mr. Arun Felbin | TA 416 | 2024-11 | Reeta Bharti | 1 | 17 | 1
Mr. Arun Felbin | TA 416 | 2024-11 | SAIFI CON. | 1 | 6 | 1
Mr. Arun Felbin | TA 416 | 2024-11 | SSR engineering | 4 | 8.25 | 4
Mr. Arun Felbin | TA 416 | 2024-11 | VH Rajpoot cont. | 6 | 7.33 | 6
Mr. Arun Felbin | TA 416 | 2024-11 | Vinayak Enterprise | 2 | 8 | 2
Mr. Arun Felbin | TA 416 | 2024-11 | Vivan Enterprise | 2 | 9.5 | 2
Mr. Arun Felbin | TA 416 | 2024-12 | A V I ENTERPRISE | 3 | 9 | 3
Mr. Arun Felbin | TA 416 | 2024-12 | Amar Singh | 3 | 9.67 | 3
Mr. Arun Felbin | TA 416 | 2024-12 | Aneshwar Traders | 3 | 18 | 3
Mr. Arun Felbin | TA 416 | 2024-12 | Dewi Construction(Girendra) | 5 | 6.8 | 5
Mr. Arun Felbin | TA 416 | 2024-12 | Dharamdas Contractor | 4 | 11 | 4
Mr. Arun Felbin | TA 416 | 2024-12 | Garg Construction | 2 | 7.5 | 2
Mr. Arun Felbin | TA 416 | 2024-12 | Horil Mahto | 3 | 11.33 | 3
Mr. Arun Felbin | TA 416 | 2024-12 | J M Enterprise | 3 | 7.67 | 3
Mr. Arun Felbin | TA 416 | 2024-12 | Laxmi Const. | 4 | 7 | 4
Mr. Arun Felbin | TA 416 | 2024-12 | M A Construction | 3 | 8 | 3
Mr. Arun Felbin | TA 416 | 2024-12 | Maa Durga | 2 | 11.5 | 2
Mr. Arun Felbin | TA 416 | 2024-12 | Pankaj | 5 | 7.4 | 5
Mr. Arun Felbin | TA 416 | 2024-12 | Pinky Dewi | 5 | 6 | 5
Mr. Arun Felbin | TA 416 | 2024-12 | R K Constrcution | 4 | 8 | 4
Mr. Arun Felbin | TA 416 | 2024-12 | Reeta Bharti | 4 | 7.75 | 4
Mr. Arun Felbin | TA 416 | 2024-12 | SAIFI CON. | 2 | 9.5 | 2
Mr. Arun Felbin | TA 416 | 2024-12 | SSR engineering | 1 | 7 | 1
Mr. Arun Felbin | TA 416 | 2024-12 | VH Rajpoot cont. | 4 | 9.25 | 4
Mr. Arun Felbin | TA 416 | 2024-12 | Vinayak Enterprise | 2 | 10 | 2
Mr. Arun Felbin | TA 416 | 2025-01 | A K Rajpoot | 4 | 17 | 4
Mr. Arun Felbin | TA 416 | 2025-01 | A V I ENTERPRISE | 1 | 20 | 1
Mr. Arun Felbin | TA 416 | 2025-01 | ASC heights | 4 | 8.5 | 4
Mr. Arun Felbin | TA 416 | 2025-01 | Amar Singh | 4 | 8.25 | 4
Mr. Arun Felbin | TA 416 | 2025-01 | Amit Choudhry | 1 |  | 0
Mr. Arun Felbin | TA 416 | 2025-01 | Aneshwar Traders | 2 | 13 | 2
Mr. Arun Felbin | TA 416 | 2025-01 | Dewi Construction(Girendra) | 4 | 7.75 | 4
Mr. Arun Felbin | TA 416 | 2025-01 | Dharamdas Contractor | 1 | 19 | 1
Mr. Arun Felbin | TA 416 | 2025-01 | Garg Construction | 3 | 23.33 | 3
Mr. Arun Felbin | TA 416 | 2025-01 | Horil Mahto | 2 | 12 | 2
Mr. Arun Felbin | TA 416 | 2025-01 | J M Enterprise | 1 | 12 | 1
Mr. Arun Felbin | TA 416 | 2025-01 | Laxmi Const. | 3 | 8.33 | 3
Mr. Arun Felbin | TA 416 | 2025-01 | M A Construction | 3 | 20.67 | 3
Mr. Arun Felbin | TA 416 | 2025-01 | Maa Durga | 3 | 20 | 3
Mr. Arun Felbin | TA 416 | 2025-01 | Pankaj | 4 | 8.25 | 4
Mr. Arun Felbin | TA 416 | 2025-01 | Pankaj Kumar | 1 |  | 0
Mr. Arun Felbin | TA 416 | 2025-01 | Pinky Dewi | 5 | 7.75 | 4
Mr. Arun Felbin | TA 416 | 2025-01 | Punam kumari-1 | 1 |  | 0
Mr. Arun Felbin | TA 416 | 2025-01 | Punam kumari-3 | 1 |  | 0
Mr. Arun Felbin | TA 416 | 2025-01 | Reeta Bharti | 3 | 11 | 3
Mr. Arun Felbin | TA 416 | 2025-01 | Rudra Construction | 1 | 11 | 1
Mr. Arun Felbin | TA 416 | 2025-01 | SAIFI CON. | 2 | 12 | 2
Mr. Arun Felbin | TA 416 | 2025-01 | SSR engineering | 3 | 10.67 | 3
Mr. Arun Felbin | TA 416 | 2025-01 | VH Rajpoot cont. | 2 | 16 | 2
Mr. Arun Felbin | TA 416 | 2025-01 | Vinayak Enterprise | 2 | 9 | 2
Mr. Arun Felbin | TA 416 | 2025-02 | A K Rajpoot | 2 | 8 | 2
Mr. Arun Felbin | TA 416 | 2025-02 | A V I ENTERPRISE | 2 | 15.5 | 2
Mr. Arun Felbin | TA 416 | 2025-02 | ASC heights | 4 | 9.25 | 4
Mr. Arun Felbin | TA 416 | 2025-02 | Amar Singh | 4 | 7 | 4
Mr. Arun Felbin | TA 416 | 2025-02 | Aneshwar Traders | 2 | 12 | 2
Mr. Arun Felbin | TA 416 | 2025-02 | Dewi Construction(Girendra) | 4 | 6.75 | 4
Mr. Arun Felbin | TA 416 | 2025-02 | Dharamdas Contractor | 2 | 15 | 2
Mr. Arun Felbin | TA 416 | 2025-02 | Garg Construction | 2 | 11 | 2
Mr. Arun Felbin | TA 416 | 2025-02 | Horil Mahto | 3 | 10 | 3
Mr. Arun Felbin | TA 416 | 2025-02 | Laxmi Const. | 3 | 10.33 | 3
Mr. Arun Felbin | TA 416 | 2025-02 | M A Construction | 2 | 12 | 2
Mr. Arun Felbin | TA 416 | 2025-02 | Maa Durga | 2 | 8.5 | 2
Mr. Arun Felbin | TA 416 | 2025-02 | Pankaj | 3 | 9.33 | 3
Mr. Arun Felbin | TA 416 | 2025-02 | Pinky Dewi | 5 | 7 | 5
Mr. Arun Felbin | TA 416 | 2025-02 | R K Constrcution | 2 | 10.5 | 2
Mr. Arun Felbin | TA 416 | 2025-02 | Reeta Bharti | 4 | 7.75 | 4
Mr. Arun Felbin | TA 416 | 2025-02 | Rudra Construction | 2 | 10 | 2
Mr. Arun Felbin | TA 416 | 2025-02 | SAIFI CON. | 2 | 11.5 | 2
Mr. Arun Felbin | TA 416 | 2025-02 | SSR engineering | 2 | 12 | 2
Mr. Arun Felbin | TA 416 | 2025-02 | VH Rajpoot cont. | 3 | 8.67 | 3
Mr. Arun Felbin | TA 416 | 2025-02 | Vinayak Enterprise | 2 | 10.5 | 2
Mr. Arun Felbin | TA 416 | 2025-03 | A K Rajpoot | 4 | 6 | 4
Mr. Arun Felbin | TA 416 | 2025-03 | ASC heights | 4 | 7.75 | 4
Mr. Arun Felbin | TA 416 | 2025-03 | Amar Singh | 2 | 7.5 | 2
Mr. Arun Felbin | TA 416 | 2025-03 | Ananya Traders-1 | 1 | 8 | 1
Mr. Arun Felbin | TA 416 | 2025-03 | Aneshwar Traders | 1 | 20 | 1
Mr. Arun Felbin | TA 416 | 2025-03 | Dewi Construction(Girendra) | 6 | 5.67 | 6
Mr. Arun Felbin | TA 416 | 2025-03 | Garg Construction | 1 | 10 | 1
Mr. Arun Felbin | TA 416 | 2025-03 | Horil Mahto | 3 | 9.67 | 3
Mr. Arun Felbin | TA 416 | 2025-03 | Laxmi Const. | 2 | 8.5 | 2
Mr. Arun Felbin | TA 416 | 2025-03 | M A Construction | 2 | 14 | 2
Mr. Arun Felbin | TA 416 | 2025-03 | M K infra | 1 | 11 | 1
Mr. Arun Felbin | TA 416 | 2025-03 | Maa Durga | 2 | 6.5 | 2
Mr. Arun Felbin | TA 416 | 2025-03 | Pankaj | 3 | 9.67 | 3
Mr. Arun Felbin | TA 416 | 2025-03 | Pinky Dewi | 5 | 7 | 5
Mr. Arun Felbin | TA 416 | 2025-03 | R K Constrcution | 1 | 11 | 1
Mr. Arun Felbin | TA 416 | 2025-03 | Reeta Bharti | 4 | 8 | 4
Mr. Arun Felbin | TA 416 | 2025-03 | Rudra Construction | 1 | 11 | 1
Mr. Arun Felbin | TA 416 | 2025-03 | SAIFI CON. | 1 | 7 | 1
Mr. Arun Felbin | TA 416 | 2025-03 | VH Rajpoot cont. | 1 | 8 | 1
Mr. Arun Felbin | TA 416 | 2025-03 | Vinayak Enterprise | 1 | 22 | 1
Mr. Arun Felbin | TA 416 | 2025-04 | A K Rajpoot | 2 | 5.5 | 2
Mr. Arun Felbin | TA 416 | 2025-04 | A V I ENTERPRISE | 1 | 8 | 1
Mr. Arun Felbin | TA 416 | 2025-04 | ASC heights | 3 | 9.33 | 3
Mr. Arun Felbin | TA 416 | 2025-04 | Amar Singh | 3 | 10 | 3
Mr. Arun Felbin | TA 416 | 2025-04 | Anand Construction | 2 | 13.5 | 2
Mr. Arun Felbin | TA 416 | 2025-04 | Ananya Traders-1 | 3 | 9 | 3
Mr. Arun Felbin | TA 416 | 2025-04 | Ananya Traders-2 | 3 | 8.33 | 3
Mr. Arun Felbin | TA 416 | 2025-04 | Aneshwar Traders | 1 | 14 | 1
Mr. Arun Felbin | TA 416 | 2025-04 | Dewi Construction(Girendra) | 3 | 8.33 | 3
Mr. Arun Felbin | TA 416 | 2025-04 | Dharamdas Contractor | 3 | 17.33 | 3
Mr. Arun Felbin | TA 416 | 2025-04 | Gagan enterprise.1 | 5 | 6.2 | 5
Mr. Arun Felbin | TA 416 | 2025-04 | Gagan enterprise.2 | 3 | 9.33 | 3
Mr. Arun Felbin | TA 416 | 2025-04 | Horil Mahto | 1 | 12 | 1
Mr. Arun Felbin | TA 416 | 2025-04 | Laxmi Const. | 1 | 18 | 1
Mr. Arun Felbin | TA 416 | 2025-04 | M K infra | 2 | 11 | 2
Mr. Arun Felbin | TA 416 | 2025-04 | Maa Durga | 1 | 9 | 1
Mr. Arun Felbin | TA 416 | 2025-04 | Pinky Dewi | 4 | 8.5 | 4
Mr. Arun Felbin | TA 416 | 2025-04 | R K Constrcution | 1 | 9 | 1
Mr. Arun Felbin | TA 416 | 2025-04 | Reeta Bharti | 2 | 10.5 | 2
Mr. Arun Felbin | TA 416 | 2025-04 | Rudra Construction | 1 | 9 | 1
Mr. Arun Felbin | TA 416 | 2025-04 | SAIFI CON. | 1 | 14 | 1
Mr. Arun Felbin | TA 416 | 2025-04 | VH Rajpoot cont. | 3 | 5 | 3
Mr. Arun Felbin | TA 416 | 2025-05 | A V I ENTERPRISE | 1 | 13 | 1
Mr. Arun Felbin | TA 416 | 2025-05 | ASC heights | 3 | 7 | 3
Mr. Arun Felbin | TA 416 | 2025-05 | Amar Singh | 5 | 6.4 | 5
Mr. Arun Felbin | TA 416 | 2025-05 | Amit Const | 1 | 11 | 1
Mr. Arun Felbin | TA 416 | 2025-05 | Ananya Traders-1 | 4 | 6.5 | 4
Mr. Arun Felbin | TA 416 | 2025-05 | Ananya Traders-2 | 5 | 6 | 5
Mr. Arun Felbin | TA 416 | 2025-05 | Aneshwar Traders | 1 | 15 | 1
Mr. Arun Felbin | TA 416 | 2025-05 | Dewi Construction(Girendra) | 5 | 6.4 | 5
Mr. Arun Felbin | TA 416 | 2025-05 | Gagan enterprise.1 | 5 | 6.4 | 5
Mr. Arun Felbin | TA 416 | 2025-05 | Gagan enterprise.2 | 2 | 9.5 | 2
Mr. Arun Felbin | TA 416 | 2025-05 | Laxmi Const. | 1 | 17 | 1
Mr. Arun Felbin | TA 416 | 2025-05 | Pinky Dewi | 3 | 8 | 3
Mr. Arun Felbin | TA 416 | 2025-05 | Reeta Bharti | 3 | 8.67 | 3
Mr. Arun Felbin | TA 416 | 2025-05 | Rudra Construction | 2 | 13 | 2
Mr. Arun Felbin | TA 416 | 2025-05 | SAIFI CON. | 1 | 14 | 1
Mr. Arun Felbin | TA 416 | 2025-05 | VH Rajpoot cont. | 2 | 10 | 2
Mr. Arun Felbin | TA 416 | 2025-06 | A V I ENTERPRISE | 1 | 15 | 1
Mr. Arun Felbin | TA 416 | 2025-06 | ASC heights | 1 | 28 | 1
Mr. Arun Felbin | TA 416 | 2025-06 | Amar Singh | 2 | 8 | 2
Mr. Arun Felbin | TA 416 | 2025-06 | Amit Const | 2 | 9.5 | 2
Mr. Arun Felbin | TA 416 | 2025-06 | Ananya Traders-1 | 2 | 16.5 | 2
Mr. Arun Felbin | TA 416 | 2025-06 | Ananya Traders-2 | 3 | 11 | 3
Mr. Arun Felbin | TA 416 | 2025-06 | Devine | 1 | 13 | 1
Mr. Arun Felbin | TA 416 | 2025-06 | Dewi Construction(Girendra) | 1 | 6 | 1
Mr. Arun Felbin | TA 416 | 2025-06 | Gagan enterprise.1 | 1 | 30 | 1
Mr. Arun Felbin | TA 416 | 2025-06 | M K infra | 2 | 29 | 2
Mr. Arun Felbin | TA 416 | 2025-06 | Pinky Dewi | 5 | 6.4 | 5
Mr. Arun Felbin | TA 416 | 2025-06 | Reeta Bharti | 4 | 9.5 | 4
Mr. Arun Felbin | TA 416 | 2025-07 | ASC heights | 1 | 12 | 1
Mr. Arun Felbin | TA 416 | 2025-07 | Amar singh | 1 | 25 | 1
Mr. Arun Felbin | TA 416 | 2025-07 | Ananya Traders-1 | 1 | 14 | 1
Mr. Arun Felbin | TA 416 | 2025-07 | Pinky Dewi | 1 | 7 | 1
Mr. Arun Felbin | TA 416 | 2025-07 | Reeta Bharti | 2 | 18 | 2
Mr. Arun Felbin | TA 416 | 2025-08 | Ananya Traders-1 | 1 | 20 | 1
Mr. Arun Felbin | TA 416 | 2025-08 | Gagan enterprise.1 | 1 | 34 | 1
Mr. Arun Felbin | TA 416 | 2025-08 | Gagan enterprise.2 (Kajol) | 1 | 13 | 1
Mr. Arun Felbin | TA 416 | 2025-08 | Kongres Kumar-1 | 1 | 33 | 1
Mr. Arun Felbin | TA 416 | 2025-08 | Kongres Kumar-2 | 1 | 29 | 1
Mr. Arun Felbin | TA 416 | 2025-08 | Punam Kumari | 1 | 22 | 1
Mr. Arun Felbin | TA 416 | 2025-08 | Radha Construction | 1 | 22 | 1
Mr. Arun Felbin | TA 416 | 2025-08 | Sainik Trader | 1 | 27 | 1
Mr. Arun Felbin | TA 416 | 2025-09 | Amit Choudhury | 2 | 20 | 2
Mr. Arun Felbin | TA 416 | 2025-09 | Ananya Traders-1 | 2 | 22 | 2
Mr. Arun Felbin | TA 416 | 2025-09 | Ananya trader | 1 | 9 | 1
Mr. Arun Felbin | TA 416 | 2025-09 | Gagan enterprise.1 | 1 | 22 | 1
Mr. Arun Felbin | TA 416 | 2025-09 | Gouri Shankar | 2 | 16.5 | 2
Mr. Arun Felbin | TA 416 | 2025-09 | Kongres Kumar- | 1 | 33 | 1
Mr. Arun Felbin | TA 416 | 2025-09 | Kongres Kumar-2 | 1 | 23 | 1
Mr. Arun Felbin | TA 416 | 2025-09 | Maa Construction | 1 | 18 | 1
Mr. Arun Felbin | TA 416 | 2025-09 | Punam Kumari | 2 | 18 | 2
Mr. Arun Felbin | TA 416 | 2025-09 | Radha Construction | 1 | 19 | 1
Mr. Arun Felbin | TA 416 | 2025-09 | Reeta Bharti | 1 | 48 | 1
Mr. Arun Felbin | TA 416 | 2025-09 | Sainik Trader | 1 | 25 | 1
Mr. Arun Felbin | TA 416 | 2025-09 | Spotyfy-3 | 1 | 38 | 1
Mr. Arun Felbin | TA 416 | 2025-10 | 2025-10-18 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 416 | 2025-10 | 2025-10-24 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 416 | 2025-10 | 2025-10-26 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 416 | 2025-10 | 2025-10-31 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 416 | 2025-10 | Amit Choudhry | 1 | 14 | 1
Mr. Arun Felbin | TA 416 | 2025-10 | Ananya trader | 1 | 22 | 1
Mr. Arun Felbin | TA 416 | 2025-10 | Kongres Kumar- | 1 | 14 | 1
Mr. Arun Felbin | TA 416 | 2025-10 | Maa Construction | 1 | 26 | 1
Mr. Arun Felbin | TA 416 | 2025-10 | Mahon Mahto | 1 | 12 | 1
Mr. Arun Felbin | TA 416 | 2025-10 | Pankaj Kumar | 1 | 19 | 1
Mr. Arun Felbin | TA 416 | 2025-10 | Punam Kumari | 1 | 13 | 1
Mr. Arun Felbin | TA 416 | 2025-10 | Punam kumari-1 | 1 | 20 | 1
Mr. Arun Felbin | TA 416 | 2025-10 | Punam kumari-2 | 1 | 15 | 1
Mr. Arun Felbin | TA 416 | 2025-10 | Reeta Bharti | 1 | 21 | 1
Mr. Arun Felbin | TA 416 | 2025-10 | Sainik Trader | 1 | 19 | 1
Mr. Arun Felbin | TA 416 | 2025-10 | Spotyfy-1 | 1 | 26 | 1
Mr. Arun Felbin | TA 416 | 2025-10 | Unity India | 1 | 39 | 1
Mr. Arun Felbin | TA 416 | 2025-11 | 2025-11-03 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 416 | 2025-11 | 2025-11-06 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 416 | 2025-11 | 2025-11-13 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 416 | 2025-11 | 2025-11-18 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 416 | 2025-11 | 2025-11-25 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 416 | 2025-11 | 2025-12-04 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 416 | 2025-11 | Aloriva Global | 2 | 15 | 2
Mr. Arun Felbin | TA 416 | 2025-11 | Amit Choudhry | 2 | 26 | 2
Mr. Arun Felbin | TA 416 | 2025-11 | Mahon Mahto | 1 | 15 | 1
Mr. Arun Felbin | TA 416 | 2025-11 | Mahon mahto | 1 | 51 | 1
Mr. Arun Felbin | TA 416 | 2025-11 | Niranjan Singh | 1 | 25 | 1
Mr. Arun Felbin | TA 416 | 2025-11 | Pankaj Kumar | 1 | 16 | 1
Mr. Arun Felbin | TA 416 | 2025-11 | Pinky Dewi | 1 | 53 | 1
Mr. Arun Felbin | TA 416 | 2025-11 | Punam kumari-1 | 1 | 25 | 1
Mr. Arun Felbin | TA 416 | 2025-11 | Punam kumari-2 | 2 | 12.5 | 2
Mr. Arun Felbin | TA 416 | 2025-12 | 2025-12-10 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 416 | 2025-12 | Aloriva Global | 1 | 19 | 1
Mr. Arun Felbin | TA 416 | 2025-12 | Pankaj Kumar | 2 | 20 | 2
Mr. Arun Felbin | TA 416 | 2025-12 | Pinky Dewi | 2 | 17 | 2
Mr. Arun Felbin | TA 416 | 2025-12 | Punam kumari-1 | 1 | 11 | 1
Mr. Arun Felbin | TA 416 | 2025-12 | Punam kumari-3 | 1 | 28 | 1
Mr. Arun Felbin | TA 416 | 2026-01 | Mahon mahto | 1 | 51 | 1
Mr. Arun Felbin | TA 416 | 2026-01 | Punam kumari-2 | 1 | 10 | 1
Mr. Arun Felbin | TA 416 | 2026-02 | 2026-02-09 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 416 | 2026-02 | 2026-02-11 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 416 | 2026-02 | 2026-02-14 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 416 | 2026-02 | 2026-02-17 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 416 | 2026-02 | 2026-02-19 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 416 | 2026-02 | 2026-02-20 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 416 | 2026-02 | 2026-02-22 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 416 | 2026-02 | 2026-02-26 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 416 | 2026-02 | 2026-03-02 00:00:00 | 2 |  | 0
Mr. Arun Felbin | TA 416 | 2026-02 | Mahon Mahto | 1 | 20 | 1
Mr. Arun Felbin | TA 416 | 2026-03 | Mahon Mahto | 1 | 29 | 1
Mr. Arun Felbin | TA 416 | 2026-03 | Punam Kumari-2 | 1 | 43 | 1
Mr. Arun Felbin | TA 416 | 2026-05 | 2026-05-05 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 416 | 2026-05 | 2026-05-08 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 416 | 2026-05 | 2026-05-10 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 418 | 2024-01 | Gang-01 (Sanjay) | 1 |  | 0
Mr. Arun Felbin | TA 418 | 2024-01 | Gang-02 (Sanjay) | 1 |  | 0
Mr. Arun Felbin | TA 418 | 2024-06 | GANG - 1 | 2 | 17 | 2
Mr. Arun Felbin | TA 418 | 2024-07 | GANG - 1 | 1 | 13 | 1
Mr. Arun Felbin | TA 418 | 2024-07 | GANG-1 | 1 | 18 | 1
Mr. Arun Felbin | TA 418 | 2024-07 | GANG-2 | 3 | 14.33 | 3
Mr. Arun Felbin | TA 418 | 2024-07 | Team - 1 (Sanjay) | 1 | 22 | 1
Mr. Arun Felbin | TA 418 | 2024-07 | Team - 2 (SM Constr.) | 1 | 18 | 1
Mr. Arun Felbin | TA 418 | 2024-07 | Team - 3 (ATK-01) | 1 | 17 | 1
Mr. Arun Felbin | TA 418 | 2024-08 | Team - 1 (Sanjay) | 2 | 11.5 | 2
Mr. Arun Felbin | TA 418 | 2024-08 | Team - 2 (SM Constr.) | 3 | 18 | 3
Mr. Arun Felbin | TA 418 | 2024-08 | Team - 3 (ATK-01) | 4 | 19.75 | 4
Mr. Arun Felbin | TA 418 | 2024-09 | (ATK-02) | 5 | 9 | 5
Mr. Arun Felbin | TA 418 | 2024-09 | Team - 2 (SM Constr.) | 1 | 27 | 1
Mr. Arun Felbin | TA 418 | 2024-09 | Team - 3 (ATK-01) | 2 | 9.5 | 2
Mr. Arun Felbin | TA 418 | 2024-10 | (ATK-02) | 3 | 13.33 | 3
Mr. Arun Felbin | TA 418 | 2024-10 | Bindu | 1 | 11 | 1
Mr. Arun Felbin | TA 418 | 2024-10 | Gang-01 (Sanjay) | 1 | 19 | 1
Mr. Arun Felbin | TA 418 | 2024-11 | Adarsh Gang | 1 | 24 | 1
Mr. Arun Felbin | TA 418 | 2024-11 | Bindu | 1 | 20 | 1
Mr. Arun Felbin | TA 418 | 2024-11 | GANG - 4 | 1 | 44 | 1
Mr. Arun Felbin | TA 418 | 2024-11 | Gang-01 (Sanjay) | 4 | 7.5 | 4
Mr. Arun Felbin | TA 418 | 2024-11 | LALA GANG | 2 | 31.5 | 2
Mr. Arun Felbin | TA 418 | 2024-12 | Adarsh Gang | 2 | 28.5 | 2
Mr. Arun Felbin | TA 418 | 2024-12 | Bindu | 3 | 28.67 | 3
Mr. Arun Felbin | TA 418 | 2024-12 | Gang-01 (Sanjay) | 5 | 6.6 | 5
Mr. Arun Felbin | TA 418 | 2024-12 | Gang-02 (Sanjay) | 3 | 9 | 3
Mr. Arun Felbin | TA 418 | 2024-12 | KAVAL CHAND | 1 | 22 | 1
Mr. Arun Felbin | TA 418 | 2025-01 | ADARSH | 1 | 126 | 1
Mr. Arun Felbin | TA 418 | 2025-01 | ANURADHA | 2 | 37.5 | 2
Mr. Arun Felbin | TA 418 | 2025-01 | Adarsh Gang | 1 | 11 | 1
Mr. Arun Felbin | TA 418 | 2025-01 | Gang-01 (Sanjay) | 4 | 98 | 4
Mr. Arun Felbin | TA 418 | 2025-01 | Gang-02 (Sanjay) | 2 | 190.5 | 2
Mr. Arun Felbin | TA 418 | 2025-01 | KEC GANG -02 | 2 | 19 | 2
Mr. Arun Felbin | TA 418 | 2025-02 | ANURADHA | 2 | 20 | 2
Mr. Arun Felbin | TA 418 | 2025-02 | Gang-01 (Sanjay) | 5 | 6.6 | 5
Mr. Arun Felbin | TA 418 | 2025-02 | Gang-02 (Sanjay) | 2 | 14 | 2
Mr. Arun Felbin | TA 418 | 2025-02 | Haque Constr. | 3 | 41.33 | 3
Mr. Arun Felbin | TA 418 | 2025-02 | KEC GANG -02 | 2 | 13.5 | 2
Mr. Arun Felbin | TA 418 | 2025-03 | ANURADHA | 3 | 19 | 3
Mr. Arun Felbin | TA 418 | 2025-03 | Gang-01 (Sanjay) | 2 | 6 | 2
Mr. Arun Felbin | TA 418 | 2025-03 | Gang-02 (Sanjay) | 4 | 7.25 | 4
Mr. Arun Felbin | TA 418 | 2025-03 | Haque Constr. | 4 | 10 | 4
Mr. Arun Felbin | TA 418 | 2025-03 | KEC GANG -02 | 1 | 15 | 1
Mr. Arun Felbin | TA 418 | 2025-03 | KEVAL CHAND | 1 | 80 | 1
Mr. Arun Felbin | TA 418 | 2025-04 | Gang-01 (Sanjay) | 1 | 11 | 1
Mr. Arun Felbin | TA 418 | 2025-04 | Gang-01(Sanjay) | 1 | 8 | 1
Mr. Arun Felbin | TA 418 | 2025-04 | Gang-02 (Sanjay) | 4 | 5.5 | 4
Mr. Arun Felbin | TA 418 | 2025-04 | Gang-02(Sanjay) | 1 | 9 | 1
Mr. Arun Felbin | TA 418 | 2025-04 | Haque Constr. | 4 | 12 | 4
Mr. Arun Felbin | TA 418 | 2025-04 | KEC GANG -04 | 1 | 26 | 1
Mr. Arun Felbin | TA 418 | 2025-05 | Gang-01(Sanjay) | 3 | 8.33 | 3
Mr. Arun Felbin | TA 418 | 2025-05 | Gang-02(Sanjay) | 4 | 9.75 | 4
Mr. Arun Felbin | TA 418 | 2025-05 | Haque Constr. | 4 | 15.25 | 4
Mr. Arun Felbin | TA 418 | 2025-05 | KEC GANG -04 | 4 | 35 | 4
Mr. Arun Felbin | TA 418 | 2025-05 | KPK | 2 | 45.5 | 2
Mr. Arun Felbin | TA 418 | 2025-06 | Gang-01(Sanjay) | 2 | 5.5 | 2
Mr. Arun Felbin | TA 418 | 2025-06 | Gang-02(Sanjay) | 4 | 6.75 | 4
Mr. Arun Felbin | TA 418 | 2025-06 | Haque Constr. | 3 | 17 | 2
Mr. Arun Felbin | TA 418 | 2025-06 | KEC GANG -04 | 3 | 12.33 | 3
Mr. Arun Felbin | TA 418 | 2025-06 | KEC GANG -05 | 4 | 8 | 4
Mr. Arun Felbin | TA 418 | 2025-06 | KEC GANG -06 | 3 | 9 | 3
Mr. Arun Felbin | TA 418 | 2025-06 | KPK | 3 | 17 | 3
Mr. Arun Felbin | TA 418 | 2025-07 | Gang-01(Sanjay) | 1 | 13 | 1
Mr. Arun Felbin | TA 418 | 2025-07 | Gang-02(Sanjay) | 1 | 19 | 1
Mr. Arun Felbin | TA 418 | 2025-07 | Haque Constr. | 4 | 8 | 3
Mr. Arun Felbin | TA 418 | 2025-07 | KEC - 01 (Barkat Ali) | 3 | 8.67 | 3
Mr. Arun Felbin | TA 418 | 2025-07 | KEC - 02 (Barkat Ali) | 3 | 10.67 | 3
Mr. Arun Felbin | TA 418 | 2025-07 | KEC GANG - 06 | 3 | 18.67 | 3
Mr. Arun Felbin | TA 418 | 2025-07 | KEC GANG - 08 | 2 | 21 | 2
Mr. Arun Felbin | TA 418 | 2025-07 | KEC GANG - 09 | 1 | 14 | 1
Mr. Arun Felbin | TA 418 | 2025-07 | KEC GANG -06 | 1 |  | 0
Mr. Arun Felbin | TA 418 | 2025-07 | KEC GANG -07 | 3 | 8.67 | 3
Mr. Arun Felbin | TA 418 | 2025-07 | KEC GANG -09 | 1 | 4 | 1
Mr. Arun Felbin | TA 418 | 2025-07 | KPK | 2 | 12.5 | 2
Mr. Arun Felbin | TA 418 | 2025-08 | Gang-02(Sanjay) / KEC - 02 (Barkat Ali) | 1 | 14 | 1
Mr. Arun Felbin | TA 418 | 2025-08 | KEC - 01 (Barkat Ali) | 3 | 20 | 3
Mr. Arun Felbin | TA 418 | 2025-08 | KEC - 02 (Barkat Ali) | 2 | 9.5 | 2
Mr. Arun Felbin | TA 418 | 2025-08 | KEC GANG -06 -HQ | 1 | 3 | 1
Mr. Arun Felbin | TA 418 | 2025-08 | KEC GANG -07 - HQ | 2 | 6 | 2
Mr. Arun Felbin | TA 418 | 2025-08 | SAVITHA | 2 | 16 | 2
Mr. Arun Felbin | TA 418 | 2025-08 | SUBHASH | 2 | 9 | 2
Mr. Arun Felbin | TA 418 | 2025-09 | 2025-10-13 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 418 | 2025-09 | KEC - 01 (Barkat Ali) | 1 | 11 | 1
Mr. Arun Felbin | TA 418 | 2025-09 | KEC - 02 (Barkat Ali) | 2 | 12 | 2
Mr. Arun Felbin | TA 418 | 2025-09 | M/S MDPL | 1 | 22 | 1
Mr. Arun Felbin | TA 418 | 2025-09 | M/s TOFIT | 2 | 10 | 2
Mr. Arun Felbin | TA 418 | 2025-09 | SUBHASH | 4 | 8.75 | 4
Mr. Arun Felbin | TA 418 | 2025-10 | 2025-12-22 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 418 | 2025-10 | KEC - 02 (Barkat Ali) | 3 | 23.67 | 3
Mr. Arun Felbin | TA 418 | 2025-10 | M/S MDPL | 1 | 19 | 1
Mr. Arun Felbin | TA 418 | 2025-10 | M/s TOFIT | 1 | 14 | 1
Mr. Arun Felbin | TA 418 | 2025-10 | SAVITHA | 1 | 29 | 1
Mr. Arun Felbin | TA 418 | 2025-10 | SUBHASH | 1 | 7 | 1
Mr. Arun Felbin | TA 418 | 2025-11 | 2025-11-10 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 418 | 2025-11 | 2025-12-05 00:00:00 | 2 |  | 0
Mr. Arun Felbin | TA 418 | 2025-11 | GANG - A1 | 3 | 7.67 | 3
Mr. Arun Felbin | TA 418 | 2025-11 | GANG - A2 | 2 | 12.5 | 2
Mr. Arun Felbin | TA 418 | 2025-11 | KEC - 02 (Barkat Ali) | 3 | 9.33 | 3
Mr. Arun Felbin | TA 418 | 2025-11 | M/S MDPL | 2 | 26.5 | 2
Mr. Arun Felbin | TA 418 | 2025-11 | M/s TOFIT | 3 | 12.67 | 3
Mr. Arun Felbin | TA 418 | 2025-12 | 2025-12-30 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 418 | 2025-12 | GANG - A1 | 1 | 8 | 1
Mr. Arun Felbin | TA 418 | 2025-12 | GANG - A1 (M) | 2 | 6 | 2
Mr. Arun Felbin | TA 418 | 2025-12 | GANG - A2 | 2 | 5.5 | 2
Mr. Arun Felbin | TA 418 | 2025-12 | KEC - 02 (Barkat Ali) | 3 | 10.33 | 3
Mr. Arun Felbin | TA 418 | 2025-12 | M/S MDPL | 4 | 7.5 | 4
Mr. Arun Felbin | TA 418 | 2025-12 | M/s TOFIT | 4 | 7 | 4
Mr. Arun Felbin | TA 418 | 2026-01 | 2026-01-26 00:00:00 | 2 |  | 0
Mr. Arun Felbin | TA 418 | 2026-01 | GANG - A2 | 1 | 7 | 1
Mr. Arun Felbin | TA 418 | 2026-01 | KEC - 02 (Barkat Ali) | 3 | 133.67 | 3
Mr. Arun Felbin | TA 418 | 2026-01 | M/S MDPL | 3 | 9 | 3
Mr. Arun Felbin | TA 418 | 2026-01 | M/s TOFIT | 4 | 8.5 | 4
Mr. Arun Felbin | TA 418 | 2026-02 | 2026-02-07 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 418 | 2026-02 | 2026-02-09 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 418 | 2026-02 | 2026-02-16 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 418 | 2026-02 | GANG - A2 | 1 | 7 | 1
Mr. Arun Felbin | TA 418 | 2026-02 | KEC - 02 (Barkat Ali) | 2 | 11 | 2
Mr. Arun Felbin | TA 418 | 2026-02 | KEC - 03 (Barkat Ali) | 1 |  | 0
Mr. Arun Felbin | TA 418 | 2026-02 | M/S MDPL | 2 | 16.5 | 2
Mr. Arun Felbin | TA 418 | 2026-02 | M/s TOFIT | 2 | 10 | 2
Mr. Arun Felbin | TA 418 | 2026-03 | 2026-03-06 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 418 | 2026-03 | 2026-03-09 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 418 | 2026-03 | 2026-03-14 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 418 | 2026-03 | 2026-03-22 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 418 | 2026-03 | 2026-06-05 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 418 | 2026-04 | 2026-04-16 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 418 | 2026-04 | 2026-06-15 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 418 | 2026-04 | M/S MDPL | 2 | 37 | 1
Mr. Arun Felbin | TA 418 | 2026-05 | 2026-05-02 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 418 | 2026-05 | 2026-05-24 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 418 | 2026-05 | 2026-05-26 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 418 | 2026-05 | 2026-05-30 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 418 | 2026-06 | 2026-06-05 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 418 | 2026-06 | 2026-06-15 00:00:00 | 2 |  | 0
Mr. Arun Felbin | TA 421 | 2024-05 | ATK CONSTRUCTIONS | 1 | 20 | 1
Mr. Arun Felbin | TA 421 | 2024-06 | AMMU ENG. | 3 | 17.67 | 3
Mr. Arun Felbin | TA 421 | 2024-06 | ATK CONSTRUCTIONS | 9 | 18.11 | 9
Mr. Arun Felbin | TA 421 | 2024-06 | RR CONST | 1 | 9 | 1
Mr. Arun Felbin | TA 421 | 2024-06 | TSB | 1 | 15 | 1
Mr. Arun Felbin | TA 421 | 2024-07 | AMMU ENG. | 4 | 10.25 | 4
Mr. Arun Felbin | TA 421 | 2024-07 | AMMU ENG.-2 | 3 | 10.33 | 3
Mr. Arun Felbin | TA 421 | 2024-07 | ANJU Const. | 4 | 16.75 | 4
Mr. Arun Felbin | TA 421 | 2024-07 | ATK CONSTRUCTIONS | 6 | 9.5 | 6
Mr. Arun Felbin | TA 421 | 2024-07 | Khatan | 2 | 10.5 | 2
Mr. Arun Felbin | TA 421 | 2024-07 | RR CONST | 2 | 17 | 2
Mr. Arun Felbin | TA 421 | 2024-07 | TSB | 1 | 36 | 1
Mr. Arun Felbin | TA 421 | 2024-08 | AMMU ENG. | 1 | 49 | 1
Mr. Arun Felbin | TA 421 | 2024-08 | ANJU Const. | 3 | 29.33 | 3
Mr. Arun Felbin | TA 421 | 2024-08 | ATK CONSTRUCTIONS | 10 | 20.7 | 10
Mr. Arun Felbin | TA 421 | 2024-08 | Ammu Eng | 5 | 16 | 5
Mr. Arun Felbin | TA 421 | 2024-08 | Company Gang | 2 | 31.5 | 2
Mr. Arun Felbin | TA 421 | 2024-08 | Khatan | 6 | 6.5 | 6
Mr. Arun Felbin | TA 421 | 2024-09 | AMMU ENG. | 1 | 86 | 1
Mr. Arun Felbin | TA 421 | 2024-09 | ANJU Const. | 3 | 20.67 | 3
Mr. Arun Felbin | TA 421 | 2024-09 | ATK CONSTRUCTIONS | 4 | 11 | 4
Mr. Arun Felbin | TA 421 | 2024-09 | Ashok kumar | 1 | 18 | 1
Mr. Arun Felbin | TA 421 | 2024-09 | Company Gang | 2 | 14.5 | 2
Mr. Arun Felbin | TA 421 | 2024-09 | Khatan | 5 | 8 | 5
Mr. Arun Felbin | TA 421 | 2024-09 | Maa Const. | 1 | 17 | 1
Mr. Arun Felbin | TA 421 | 2024-09 | s.K.Janarul | 1 | 17 | 1
Mr. Arun Felbin | TA 421 | 2024-09 | s.K.Janarul Sheikh | 1 | 13 | 1
Mr. Arun Felbin | TA 421 | 2024-10 | ANJU Const. | 2 | 38.5 | 2
Mr. Arun Felbin | TA 421 | 2024-10 | ATK CONSTRUCTIONS | 2 | 21 | 2
Mr. Arun Felbin | TA 421 | 2024-10 | ATK Constructions | 1 | 5 | 1
Mr. Arun Felbin | TA 421 | 2024-10 | Ammu Eng | 5 | 11.6 | 5
Mr. Arun Felbin | TA 421 | 2024-10 | Ashok | 4 | 18.75 | 4
Mr. Arun Felbin | TA 421 | 2024-10 | Company Gang + ATK | 1 | 35 | 1
Mr. Arun Felbin | TA 421 | 2024-10 | Khatan | 4 | 6.5 | 4
Mr. Arun Felbin | TA 421 | 2024-10 | Khatun | 1 | 6 | 1
Mr. Arun Felbin | TA 421 | 2024-10 | Maa Const. | 2 | 15.5 | 2
Mr. Arun Felbin | TA 421 | 2024-10 | Manirul (Islam)-Khatun | 1 | 14 | 1
Mr. Arun Felbin | TA 421 | 2024-10 | Praveen | 1 | 26 | 1
Mr. Arun Felbin | TA 421 | 2024-10 | Subash | 1 | 11 | 1
Mr. Arun Felbin | TA 421 | 2024-10 | s.K.Janarul Sheikh | 2 | 9 | 2
Mr. Arun Felbin | TA 421 | 2024-11 | Amit Kumar | 4 | 11.5 | 4
Mr. Arun Felbin | TA 421 | 2024-11 | Ammu Eng | 3 | 24.67 | 3
Mr. Arun Felbin | TA 421 | 2024-11 | Ashok | 3 | 12.33 | 3
Mr. Arun Felbin | TA 421 | 2024-11 | Ashok Kumar | 1 | 7 | 1
Mr. Arun Felbin | TA 421 | 2024-11 | Ashok kumar | 3 | 24.67 | 3
Mr. Arun Felbin | TA 421 | 2024-11 | Ashok-2 | 3 | 11.33 | 3
Mr. Arun Felbin | TA 421 | 2024-11 | Ashokkumar | 1 | 8 | 1
Mr. Arun Felbin | TA 421 | 2024-11 | Balraj | 3 | 13.67 | 3
Mr. Arun Felbin | TA 421 | 2024-11 | Khatun | 4 | 6.25 | 4
Mr. Arun Felbin | TA 421 | 2024-11 | Maa Const. | 4 | 8 | 4
Mr. Arun Felbin | TA 421 | 2024-11 | Praveen | 1 | 17 | 1
Mr. Arun Felbin | TA 421 | 2024-11 | Subash | 5 | 8.2 | 5
Mr. Arun Felbin | TA 421 | 2024-11 | Visionary Co | 1 | 40 | 1
Mr. Arun Felbin | TA 421 | 2024-11 | khatun | 2 | 6 | 2
Mr. Arun Felbin | TA 421 | 2024-11 | venkateshwarlu | 2 | 9 | 2
Mr. Arun Felbin | TA 421 | 2024-12 | ATK Constructions | 7 | 18.43 | 7
Mr. Arun Felbin | TA 421 | 2024-12 | Amit Kumar | 1 | 10 | 1
Mr. Arun Felbin | TA 421 | 2024-12 | Ammu Eng | 6 | 8.5 | 6
Mr. Arun Felbin | TA 421 | 2024-12 | Ashok kumar | 2 | 11 | 2
Mr. Arun Felbin | TA 421 | 2024-12 | Ashok-1 | 1 | 9 | 1
Mr. Arun Felbin | TA 421 | 2024-12 | Ashok-2 | 5 | 10 | 5
Mr. Arun Felbin | TA 421 | 2024-12 | BalraJ | 1 | 8 | 1
Mr. Arun Felbin | TA 421 | 2024-12 | Balraj | 2 | 8 | 2
Mr. Arun Felbin | TA 421 | 2024-12 | Khatun | 5 | 5.6 | 5
Mr. Arun Felbin | TA 421 | 2024-12 | Praveen | 2 | 20.5 | 2
Mr. Arun Felbin | TA 421 | 2024-12 | Subash | 8 | 4.75 | 8
Mr. Arun Felbin | TA 421 | 2024-12 | Tagore | 3 | 10.33 | 3
Mr. Arun Felbin | TA 421 | 2024-12 | Venkateshwarlu | 1 | 8 | 1
Mr. Arun Felbin | TA 421 | 2024-12 | Visionary & Co | 1 | 5 | 1
Mr. Arun Felbin | TA 421 | 2024-12 | Visionary Co | 2 | 14.5 | 2
Mr. Arun Felbin | TA 421 | 2024-12 | venkateshwarlu | 2 | 14.5 | 2
Mr. Arun Felbin | TA 421 | 2025-01 | ATK Constructions | 10 | 7.6 | 10
Mr. Arun Felbin | TA 421 | 2025-01 | Ammu Engineering | 4 | 10 | 4
Mr. Arun Felbin | TA 421 | 2025-01 | Ashok kumar (Thotta) | 5 | 7.2 | 5
Mr. Arun Felbin | TA 421 | 2025-01 | Ashok-2 (Venkateshwarlu) | 5 | 10.2 | 5
Mr. Arun Felbin | TA 421 | 2025-01 | BaLraJ | 2 | 11 | 2
Mr. Arun Felbin | TA 421 | 2025-01 | Khatun | 5 | 12.6 | 5
Mr. Arun Felbin | TA 421 | 2025-01 | Praveen | 2 | 14.5 | 2
Mr. Arun Felbin | TA 421 | 2025-01 | Subash | 7 | 8 | 7
Mr. Arun Felbin | TA 421 | 2025-01 | TaGore | 5 | 13.2 | 5
Mr. Arun Felbin | TA 421 | 2025-01 | Venkateshwarlu | 3 | 13.33 | 3
Mr. Arun Felbin | TA 421 | 2025-01 | Visionary & Co | 2 | 14.5 | 2
Mr. Arun Felbin | TA 421 | 2025-02 | ATK Constructions | 4 | 9 | 4
Mr. Arun Felbin | TA 421 | 2025-02 | Ammu Engineering | 8 | 16.62 | 8
Mr. Arun Felbin | TA 421 | 2025-02 | Ashok kumar (Thotta) | 4 | 7.75 | 4
Mr. Arun Felbin | TA 421 | 2025-02 | Ashok-2 (Venkateshwarlu) | 2 | 14.5 | 2
Mr. Arun Felbin | TA 421 | 2025-02 | BaLraJ | 5 | 20 | 5
Mr. Arun Felbin | TA 421 | 2025-02 | J.$lnGH | 2 | 8 | 2
Mr. Arun Felbin | TA 421 | 2025-02 | Khatun | 5 | 5.8 | 5
Mr. Arun Felbin | TA 421 | 2025-02 | Praveen | 2 | 11.5 | 2
Mr. Arun Felbin | TA 421 | 2025-02 | Subash | 6 | 5 | 6
Mr. Arun Felbin | TA 421 | 2025-02 | TaGore | 4 | 11.25 | 4
Mr. Arun Felbin | TA 421 | 2025-02 | Venkateshwarlu | 3 | 11.67 | 3
Mr. Arun Felbin | TA 421 | 2025-03 | Ammu Engineering | 6 | 70.67 | 6
Mr. Arun Felbin | TA 421 | 2025-03 | Ashok kumar (Thotta) | 2 | 14.5 | 2
Mr. Arun Felbin | TA 421 | 2025-03 | Ashok-2 (Venkateshwarlu) | 2 | 18 | 2
Mr. Arun Felbin | TA 421 | 2025-03 | BaLraJ | 4 | 9 | 4
Mr. Arun Felbin | TA 421 | 2025-03 | J.$lnGH | 5 | 5 | 5
Mr. Arun Felbin | TA 421 | 2025-03 | J.$lnGH - o1 | 1 | 6 | 1
Mr. Arun Felbin | TA 421 | 2025-03 | J.$lnGH - o2 | 1 | 30 | 1
Mr. Arun Felbin | TA 421 | 2025-03 | Khatun | 6 | 5.33 | 6
Mr. Arun Felbin | TA 421 | 2025-03 | Praveen | 3 | 11 | 3
Mr. Arun Felbin | TA 421 | 2025-03 | Subash | 8 | 3.88 | 8
Mr. Arun Felbin | TA 421 | 2025-03 | TaGore | 2 | 199.5 | 2
Mr. Arun Felbin | TA 421 | 2025-03 | Venkateshwarlu | 3 | 10.33 | 3
Mr. Arun Felbin | TA 421 | 2025-04 | ATK Constructions | 2 | 24.5 | 2
Mr. Arun Felbin | TA 421 | 2025-04 | Ashok-2 (Venkateshwarlu) | 1 | 8 | 1
Mr. Arun Felbin | TA 421 | 2025-04 | J.$lnGH - o1 | 4 | 8.25 | 4
Mr. Arun Felbin | TA 421 | 2025-04 | J.$lnGH - o2 | 4 | 7.25 | 4
Mr. Arun Felbin | TA 421 | 2025-04 | Khatun | 6 | 5.33 | 6
Mr. Arun Felbin | TA 421 | 2025-04 | Praveen | 2 | 15 | 2
Mr. Arun Felbin | TA 421 | 2025-04 | Subash | 8 | 4.25 | 8
Mr. Arun Felbin | TA 421 | 2025-04 | TaGore | 2 | 23 | 2
Mr. Arun Felbin | TA 421 | 2025-04 | Venkateshwarlu | 6 | 9.5 | 6
Mr. Arun Felbin | TA 421 | 2025-05 | ATK Constructions | 13 | 28.77 | 13
Mr. Arun Felbin | TA 421 | 2025-05 | Ammu Engineering | 5 | 39.2 | 5
Mr. Arun Felbin | TA 421 | 2025-05 | Ashok-2 (Venkateshwarlu) | 6 | 13.8 | 5
Mr. Arun Felbin | TA 421 | 2025-05 | BaLraJ | 8 | 24.25 | 8
Mr. Arun Felbin | TA 421 | 2025-05 | Hassan | 2 | 19 | 2
Mr. Arun Felbin | TA 421 | 2025-05 | J.$lnGH - o1 | 1 | 4 | 1
Mr. Arun Felbin | TA 421 | 2025-05 | Jwala Singh -01 | 2 | 5.5 | 2
Mr. Arun Felbin | TA 421 | 2025-05 | Khatun | 4 | 5.75 | 4
Mr. Arun Felbin | TA 421 | 2025-05 | Praveen | 1 | 13 | 1
Mr. Arun Felbin | TA 421 | 2025-05 | Subash | 7 | 4.14 | 7
Mr. Arun Felbin | TA 421 | 2025-05 | TaGore | 1 | 52 | 1
Mr. Arun Felbin | TA 421 | 2025-05 | Venkateshwarlu | 4 | 31 | 4
Mr. Arun Felbin | TA 421 | 2025-06 | ATK Constructions | 8 | 12.38 | 8
Mr. Arun Felbin | TA 421 | 2025-06 | Ammu Engineering | 2 | 18.5 | 2
Mr. Arun Felbin | TA 421 | 2025-06 | Ashok-2 (Venkateshwarlu) | 6 | 7.33 | 6
Mr. Arun Felbin | TA 421 | 2025-06 | BaLraJ | 4 | 17.75 | 4
Mr. Arun Felbin | TA 421 | 2025-06 | Hassan | 3 | 9 | 3
Mr. Arun Felbin | TA 421 | 2025-06 | Praveen | 2 | 20.5 | 2
Mr. Arun Felbin | TA 421 | 2025-06 | Subash | 5 | 7.4 | 5
Mr. Arun Felbin | TA 421 | 2025-06 | Tagore | 1 | 21 | 1
Mr. Arun Felbin | TA 421 | 2025-06 | Venkateshwarlu | 4 | 18.25 | 4
Mr. Arun Felbin | TA 421 | 2025-07 | ATK Constructions | 6 | 11.33 | 6
Mr. Arun Felbin | TA 421 | 2025-07 | Ammu Engineering | 1 | 43 | 1
Mr. Arun Felbin | TA 421 | 2025-07 | Ashok-2 (Venkateshwarlu) | 4 | 11.75 | 4
Mr. Arun Felbin | TA 421 | 2025-07 | D K Verma | 1 | 9 | 1
Mr. Arun Felbin | TA 421 | 2025-07 | D k Verma | 1 | 9 | 1
Mr. Arun Felbin | TA 421 | 2025-07 | Hassan | 2 | 11 | 2
Mr. Arun Felbin | TA 421 | 2025-07 | Hassan -2 | 1 | 18 | 1
Mr. Arun Felbin | TA 421 | 2025-07 | Hassan-2 | 2 | 9.5 | 2
Mr. Arun Felbin | TA 421 | 2025-07 | Khatun | 5 | 5.2 | 5
Mr. Arun Felbin | TA 421 | 2025-07 | Naziruddin | 4 | 9 | 3
Mr. Arun Felbin | TA 421 | 2025-07 | Praveen | 1 | 18 | 1
Mr. Arun Felbin | TA 421 | 2025-07 | Subash | 7 | 4.67 | 6
Mr. Arun Felbin | TA 421 | 2025-07 | Venkateshwarlu | 1 | 17 | 1
Mr. Arun Felbin | TA 421 | 2025-08 | Ashok-2 (Venkateshwarlu) | 1 | 13 | 1
Mr. Arun Felbin | TA 421 | 2025-08 | D K Verma | 1 | 6 | 1
Mr. Arun Felbin | TA 421 | 2025-08 | D k Verma | 3 | 8.67 | 3
Mr. Arun Felbin | TA 421 | 2025-08 | Hassan | 3 | 14.67 | 3
Mr. Arun Felbin | TA 421 | 2025-08 | Khatun | 6 | 5.5 | 6
Mr. Arun Felbin | TA 421 | 2025-08 | Naziruddin | 4 | 8 | 4
Mr. Arun Felbin | TA 421 | 2025-08 | Praveen | 1 | 26 | 1
Mr. Arun Felbin | TA 421 | 2025-08 | Subash | 5 | 7.6 | 5
Mr. Arun Felbin | TA 421 | 2025-08 | Venkateshwarlu | 1 | 15 | 1
Mr. Arun Felbin | TA 421 | 2025-09 | D k Verma | 4 | 7 | 4
Mr. Arun Felbin | TA 421 | 2025-09 | Hassan | 3 | 8.33 | 3
Mr. Arun Felbin | TA 421 | 2025-09 | Khatun | 2 | 8.5 | 2
Mr. Arun Felbin | TA 421 | 2025-09 | Naziruddin | 3 | 9 | 3
Mr. Arun Felbin | TA 421 | 2025-09 | Praveen | 1 | 32 | 1
Mr. Arun Felbin | TA 421 | 2025-09 | Shakila Khatun | 2 | 4 | 2
Mr. Arun Felbin | TA 421 | 2025-09 | Subash | 7 | 4.43 | 7
Mr. Arun Felbin | TA 421 | 2025-10 | 2025-09-07 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 421 | 2025-10 | 2025-10-23 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 421 | 2025-10 | Ashok-2 (Venkateshwarlu) | 1 | 103 | 1
Mr. Arun Felbin | TA 421 | 2025-10 | D k Verma | 4 | 4.75 | 4
Mr. Arun Felbin | TA 421 | 2025-10 | Hassan | 2 | 11.5 | 2
Mr. Arun Felbin | TA 421 | 2025-10 | Khatun | 5 | 5.8 | 5
Mr. Arun Felbin | TA 421 | 2025-10 | Praveen | 2 | 21.5 | 2
Mr. Arun Felbin | TA 421 | 2025-10 | Subash | 4 | 7.25 | 4
Mr. Arun Felbin | TA 421 | 2025-10 | Yadhav + D k Verma | 1 | 16 | 1
Mr. Arun Felbin | TA 421 | 2025-11 | ATK Constructions | 1 | 16 | 1
Mr. Arun Felbin | TA 421 | 2025-11 | D k Verma | 5 | 7.2 | 5
Mr. Arun Felbin | TA 421 | 2025-11 | GowriShankar | 1 | 8 | 1
Mr. Arun Felbin | TA 421 | 2025-11 | Hassan | 3 | 10.67 | 3
Mr. Arun Felbin | TA 421 | 2025-11 | Khatun | 6 | 5.2 | 5
Mr. Arun Felbin | TA 421 | 2025-11 | Praveen | 1 | 18 | 1
Mr. Arun Felbin | TA 421 | 2025-11 | Subash | 8 | 4.57 | 7
Mr. Arun Felbin | TA 421 | 2025-12 | ATK Constructions | 1 |  | 0
Mr. Arun Felbin | TA 421 | 2025-12 | D k Verma | 2 | 10 | 2
Mr. Arun Felbin | TA 421 | 2025-12 | Gauri Shankar Mahto | 3 | 10.67 | 3
Mr. Arun Felbin | TA 421 | 2025-12 | Khatun | 7 | 4.86 | 7
Mr. Arun Felbin | TA 421 | 2025-12 | Praveen | 1 | 25 | 1
Mr. Arun Felbin | TA 421 | 2025-12 | Subash | 10 | 3.5 | 10
Mr. Arun Felbin | TA 421 | 2026-01 | 2026-01-31 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 421 | 2026-01 | D k Verma | 1 | 8 | 1
Mr. Arun Felbin | TA 421 | 2026-01 | Gauri Shankar Mahto | 2 | 7 | 2
Mr. Arun Felbin | TA 421 | 2026-01 | Khatun | 1 | 4 | 1
Mr. Arun Felbin | TA 421 | 2026-01 | Subash | 2 | 6 | 2
Mr. Arun Felbin | TA 421 | 2026-02 | 2026-02-01 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 421 | 2026-02 | 2026-02-04 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 421 | 2026-02 | 2026-02-07 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 421 | 2026-02 | 2026-02-08 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 421 | 2026-02 | 2026-02-11 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 421 | 2026-02 | 2026-02-12 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 421 | 2026-02 | 2026-02-20 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 421 | 2026-02 | 2026-02-25 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 421 | 2026-03 | 2026-03-02 00:00:00 | 1 |  | 0
Mr. Arun Felbin | TA 510FDN | 2025-02 | Arya Enterprises | 2 | 7 | 2
Mr. Arun Felbin | TA 510FDN | 2025-02 | B.K.Traders | 2 | 5 | 2
Mr. Arun Felbin | TA 510FDN | 2025-03 | Arya Enterprises | 3 | 6.33 | 3
Mr. Arun Felbin | TA 510FDN | 2025-03 | B.K.Traders | 2 | 6 | 2
Mr. Arun Felbin | TA 510FDN | 2025-04 | B.K.Traders | 2 | 7 | 2
Mr. Arun Felbin | TA 510FDN | 2025-04 | Om Infra | 4 | 17.25 | 4
Mr. Arun Felbin | TA 510FDN | 2025-05 | B.K.Traders | 5 | 11.2 | 5
Mr. Arun Felbin | TA 510FDN | 2025-05 | Om Infra | 2 | 15.5 | 2
Mr. Arun Felbin | TA 510FDN | 2025-06 | Jyoti Construction | 2 | 8 | 2
Mr. Arun Felbin | TA 510FDN | 2025-08 | Jyoti Construction | 1 | 67 | 1
Mr. Arun Felbin | TA 510FDN | 2025-09 | B.K.Traders | 1 | 19 | 1
Mr. Arun Felbin | TA 510FDN | 2025-10 | Shakaldev | 3 | 13.67 | 3
Mr. Arun Felbin | TA 510FDN | 2025-10 | Vihan | 2 | 21 | 2
Mr. Arun Felbin | TA 510FDN | 2025-11 | B.K.Traders | 1 | 14 | 1
Mr. Arun Felbin | TA 510FDN | 2025-11 | MD Hussain | 1 | 14 | 1
Mr. Arun Felbin | TA 510FDN | 2025-11 | Rudra | 1 | 16 | 1
Mr. Arun Felbin | TA 510FDN | 2025-11 | Shakaldev | 2 | 40.5 | 2
Mr. Arun Felbin | TA 510FDN | 2025-12 | Ambani | 1 | 25 | 1
Mr. Arun Felbin | TA 510FDN | 2025-12 | Haji Enterprises | 2 | 14 | 2
Mr. Arun Felbin | TA 510FDN | 2025-12 | MD Hussain | 2 | 14 | 2
Mr. Arun Felbin | TA 510FDN | 2025-12 | Rudra | 1 | 23 | 1
Mr. Arun Felbin | TA 510FDN | 2025-12 | Shakaldev | 3 | 15.67 | 3
Mr. Arun Felbin | TA 510FDN | 2025-12 | Vihan | 1 | 27 | 1
Mr. Arun Felbin | TA 510FDN | 2026-01 | Chandrakant Patel | 2 | 14 | 2
Mr. Arun Felbin | TA 510FDN | 2026-01 | Haji Enterprises | 1 | 30 | 1
Mr. Arun Felbin | TA 510FDN | 2026-01 | MD Hussain | 1 | 8 | 1
Mr. Arun Felbin | TA 510FDN | 2026-01 | Maa Bhavani | 2 | 9.5 | 2
Mr. Arun Felbin | TA 510FDN | 2026-01 | Vihan | 1 | 23 | 1
Mr. Arun Felbin | TA 510FDN | 2026-02 | ABS Construction | 1 | 12 | 1
Mr. Arun Felbin | TA 510FDN | 2026-02 | Chandrakant Patel | 1 | 10 | 1
Mr. Arun Felbin | TA 510FDN | 2026-02 | Haji Enterprises | 2 | 9 | 2
Mr. Arun Felbin | TA 510FDN | 2026-02 | MD Hussain | 1 | 29 | 1
Mr. Arun Felbin | TA 510FDN | 2026-02 | Vihan | 1 | 27 | 1
Mr. Arun Felbin | TA 510FDN | 2026-03 | ABS Construction | 1 | 34 | 1
Mr. Arun Felbin | TA 510FDN | 2026-03 | Haji Enterprises | 3 | 25.67 | 3
Mr. Arun Felbin | TA 510FDN | 2026-04 | BLG Infra | 4 | 7.5 | 4
Mr. Arun Felbin | TA 510FDN | 2026-04 | Chandrakant Patel | 2 | 9 | 2
Mr. Arun Felbin | TA 510FDN | 2026-04 | Haji Enterprises | 2 | 15.5 | 2
Mr. Arun Felbin | TA 510FDN | 2026-05 | BLG Infra | 6 | 6.17 | 6
Mr. Arun Felbin | TA 510FDN | 2026-05 | Chandrakant Patel | 1 | 28 | 1
Mr. Arun Felbin | TA 510FDN | 2026-05 | Haji Enterprises | 2 | 7.5 | 2
Mr. Arun Felbin | TA 510FDN | 2026-05 | Haji Enterprises2 | 1 | 10 | 1
Mr. Arun Felbin | TA 510FDN | 2026-05 | JDG Enterprises | 1 | 25 | 1
Mr. Arun Felbin | TA 510FDN | 2026-05 | Krishna Constrction | 1 | 47 | 1
Mr. Arun Felbin | TA 510FDN | 2026-05 | Vihan | 1 | 10 | 1
Mr. Arun Felbin | TA 510FDN | 2026-06 | BLG Infra | 2 | 10.5 | 2
Mr. Arun Felbin | TA 510FDN | 2026-06 | Haji Enterprises | 1 | 7 | 1
Mr. Arun Felbin | TA 510FDN | 2026-06 | Haji Enterprises-1 | 1 | 18 | 1
Mr. Arun Felbin | TA 510FDN | 2026-06 | Vihan | 3 | 9 | 3
Mr. NK Gupta | TA 419 | 2024-05 | Garg Energy | 3 | 8.5 | 2
Mr. NK Gupta | TA 419 | 2024-06 | Bala Ji | 2 | 6 | 2
Mr. NK Gupta | TA 419 | 2024-06 | Garg Energy | 7 | 6.71 | 7
Mr. NK Gupta | TA 419 | 2024-07 | Bala Ji | 7 | 5.57 | 7
Mr. NK Gupta | TA 419 | 2024-07 | Garg Energy | 7 | 10 | 7
Mr. NK Gupta | TA 419 | 2024-07 | Kirti Construction | 3 | 9.67 | 3
Mr. NK Gupta | TA 419 | 2024-08 | Bala Ji | 2 | 9.5 | 2
Mr. NK Gupta | TA 419 | 2024-08 | Garg Energy | 2 | 6 | 2
Mr. NK Gupta | TA 419 | 2024-08 | Kirti Construction | 3 | 9 | 3
Mr. NK Gupta | TA 419 | 2024-08 | Surjeet | 1 | 18 | 1
Mr. NK Gupta | TA 419 | 2024-09 | Garg Energy | 6 | 19.17 | 6
Mr. NK Gupta | TA 419 | 2024-09 | Kirti Construction | 3 | 8.33 | 3
Mr. NK Gupta | TA 419 | 2024-09 | NV Infra | 1 | 18 | 1
Mr. NK Gupta | TA 419 | 2024-09 | Surjeet | 3 | 9.33 | 3
Mr. NK Gupta | TA 419 | 2024-09 | TDCL | 3 | 8.33 | 3
Mr. NK Gupta | TA 419 | 2024-10 | Garg Energy | 7 | 8.14 | 7
Mr. NK Gupta | TA 419 | 2024-10 | Kirti Construction | 4 | 11.25 | 4
Mr. NK Gupta | TA 419 | 2024-10 | NV Infra | 3 | 20.67 | 3
Mr. NK Gupta | TA 419 | 2024-10 | Shyam | 1 | 19 | 1
Mr. NK Gupta | TA 419 | 2024-10 | Surjeet | 1 | 17 | 1
Mr. NK Gupta | TA 419 | 2024-10 | TDCL | 2 | 11.5 | 2
Mr. NK Gupta | TA 419 | 2024-11 | Garg Energy | 5 | 16 | 5
Mr. NK Gupta | TA 419 | 2024-11 | Kirti Construction | 2 | 19.5 | 2
Mr. NK Gupta | TA 419 | 2024-11 | NV Infra | 2 | 16 | 1
Mr. NK Gupta | TA 419 | 2024-11 | Shyam Ent | 2 | 18 | 2
Mr. NK Gupta | TA 419 | 2024-11 | Shyam Infra | 1 | 11 | 1
Mr. NK Gupta | TA 419 | 2024-11 | Surjeet | 1 | 21 | 1
Mr. NK Gupta | TA 419 | 2024-11 | TDCL | 1 | 26 | 1
Mr. NK Gupta | TA 419 | 2024-12 | Garg Energy | 3 | 10.33 | 3
Mr. NK Gupta | TA 419 | 2024-12 | Kirti Construction | 2 | 10 | 2
Mr. NK Gupta | TA 419 | 2024-12 | NV Infra | 2 | 17.5 | 2
Mr. NK Gupta | TA 419 | 2024-12 | Shyam Ent | 1 | 23 | 1
Mr. NK Gupta | TA 419 | 2024-12 | Shyam Infra | 2 | 9.5 | 2
Mr. NK Gupta | TA 419 | 2024-12 | TDCL | 2 | 12 | 2
Mr. NK Gupta | TA 419 | 2025-01 | Garg Energy | 3 | 11 | 3
Mr. NK Gupta | TA 419 | 2025-01 | Kirti Construction | 1 | 13 | 1
Mr. NK Gupta | TA 419 | 2025-01 | NV Infra | 2 | 15.5 | 2
Mr. NK Gupta | TA 419 | 2025-01 | Shyam Infra | 1 | 26 | 1
Mr. NK Gupta | TA 419 | 2025-02 | Garg Energy | 5 | 11.2 | 5
Mr. NK Gupta | TA 419 | 2025-02 | NV Infra | 3 | 25 | 3
Mr. NK Gupta | TA 419 | 2025-02 | Saran Communication | 1 | 29 | 1
Mr. NK Gupta | TA 419 | 2025-02 | Shre Shyam | 1 | 15 | 1
Mr. NK Gupta | TA 419 | 2025-03 | Garg Energy | 2 | 5 | 2
Mr. NK Gupta | TA 419 | 2025-03 | NV Infra | 2 | 14 | 2
Mr. NK Gupta | TA 419 | 2025-03 | Shree Shyam | 1 | 5 | 1
Mr. NK Gupta | TA 419 | 2025-04 | GRD Enterprise | 1 | 14 | 1
Mr. NK Gupta | TA 419 | 2025-04 | GRD Enterprises | 1 | 16 | 1
Mr. NK Gupta | TA 419 | 2025-04 | Garg Energy | 7 | 10.14 | 7
Mr. NK Gupta | TA 419 | 2025-04 | NV Infra | 3 | 6.67 | 3
Mr. NK Gupta | TA 419 | 2025-04 | Tyagi Const | 2 | 12 | 2
Mr. NK Gupta | TA 419 | 2025-05 | GRD Enterprises | 1 | 17 | 1
Mr. NK Gupta | TA 419 | 2025-05 | Garg Energy | 4 | 9 | 4
Mr. NK Gupta | TA 419 | 2025-05 | MS Construction | 1 | 17 | 1
Mr. NK Gupta | TA 419 | 2025-05 | Tyagi Const | 2 | 8 | 2
Mr. NK Gupta | TA 419 | 2025-06 | Garg Energy | 6 | 11.83 | 6
Mr. NK Gupta | TA 419 | 2025-06 | Kirti Construction | 1 | 34 | 1
Mr. NK Gupta | TA 419 | 2025-06 | MS Construction | 2 | 26.5 | 2
Mr. NK Gupta | TA 419 | 2025-06 | NV Infra | 1 | 27 | 1
Mr. NK Gupta | TA 419 | 2025-07 | Garg Energy | 3 | 15.67 | 3
Mr. NK Gupta | TA 419 | 2025-07 | MS Construction | 1 | 15 | 1
Mr. NK Gupta | TA 419 | 2025-07 | NV Infra | 1 | 44 | 1
Mr. NK Gupta | TA 419 | 2025-08 | Garg Energy | 2 | 21 | 2
Mr. NK Gupta | TA 419 | 2025-09 | Garg Energy | 3 | 6.33 | 3
Mr. NK Gupta | TA 419 | 2025-10 | D&P | 1 | 26 | 1
Mr. NK Gupta | TA 419 | 2025-10 | Garg Energy | 2 | 13.5 | 2
Mr. NK Gupta | TA 419 | 2025-10 | NV Infra | 1 | 31 | 1
Mr. NK Gupta | TA 419 | 2025-10 | Virendra | 2 | 20.5 | 2
Mr. NK Gupta | TA 419 | 2025-11 | Ahlawat Const | 1 | 18 | 1
Mr. NK Gupta | TA 419 | 2025-11 | Ahlawat Cpnstruction | 1 | 6 | 1
Mr. NK Gupta | TA 419 | 2025-11 | D&B | 1 | 6 | 1
Mr. NK Gupta | TA 419 | 2025-11 | D&P | 1 | 83 | 1
Mr. NK Gupta | TA 419 | 2025-11 | DCLCSL( Ravindra) | 1 | 19 | 1
Mr. NK Gupta | TA 419 | 2025-11 | GRD | 1 | 8 | 1
Mr. NK Gupta | TA 419 | 2025-11 | GRD Enterprises 1 | 1 | 7 | 1
Mr. NK Gupta | TA 419 | 2025-11 | GRD Enterprises 2 | 2 | 9.5 | 2
Mr. NK Gupta | TA 419 | 2025-11 | GRD Enterprises1 | 1 | 22 | 1
Mr. NK Gupta | TA 419 | 2025-11 | Garg Energy | 1 | 10 | 1
Mr. NK Gupta | TA 419 | 2025-11 | MS Construction | 3 | 9 | 3
Mr. NK Gupta | TA 419 | 2025-11 | NV Infra | 1 | 8 | 1
Mr. NK Gupta | TA 419 | 2025-11 | Tyagi Construction | 1 | 7 | 1
Mr. NK Gupta | TA 419 | 2025-11 | Virendra | 2 | 16 | 2
Mr. NK Gupta | TA 419 | 2025-12 | Ahlawat Cpnstruction | 2 | 8.5 | 2
Mr. NK Gupta | TA 419 | 2025-12 | Amit Yadav 1 | 1 | 9 | 1
Mr. NK Gupta | TA 419 | 2025-12 | Bajrang Const | 1 | 11 | 1
Mr. NK Gupta | TA 419 | 2025-12 | D&B | 2 | 10.5 | 2
Mr. NK Gupta | TA 419 | 2025-12 | DCLCSL( Ravindra) | 1 | 14 | 1
Mr. NK Gupta | TA 419 | 2025-12 | GRD 1 | 2 | 10.5 | 2
Mr. NK Gupta | TA 419 | 2025-12 | GRD 2 | 3 | 6.33 | 3
Mr. NK Gupta | TA 419 | 2025-12 | MS Construction | 1 | 13 | 1
Mr. NK Gupta | TA 419 | 2025-12 | NV Infra | 2 | 30.5 | 2
Mr. NK Gupta | TA 419 | 2025-12 | Utkarsh Const | 1 | 6 | 1
Mr. NK Gupta | TA 419 | 2025-12 | Virendra | 2 | 24 | 2
Mr. NK Gupta | TA 419 | 2026-01 | Bajrang Const | 1 | 10 | 1
Mr. NK Gupta | TA 419 | 2026-01 | D&B | 2 | 30.5 | 2
Mr. NK Gupta | TA 419 | 2026-01 | DCLCSL( Ravindra) | 1 |  | 0
Mr. NK Gupta | TA 419 | 2026-01 | GRD 1 | 2 | 15.5 | 2
Mr. NK Gupta | TA 419 | 2026-01 | GRD 2 | 2 | 13.5 | 2
Mr. NK Gupta | TA 419 | 2026-01 | GRD Enterprises | 1 | 17 | 1
Mr. NK Gupta | TA 419 | 2026-01 | MS Construction | 1 | 16 | 1
Mr. NK Gupta | TA 419 | 2026-01 | Sherawali Const | 1 | 18 | 1
Mr. NK Gupta | TA 419 | 2026-01 | Virendra | 1 | 21 | 1
Mr. NK Gupta | TA 419 | 2026-02 | Bajrang Const | 1 | 42 | 1
Mr. NK Gupta | TA 419 | 2026-02 | DCLCSL( Ravindra) | 1 | 31 | 1
Mr. NK Gupta | TA 419 | 2026-02 | GRD 1 | 1 | 19 | 1
Mr. NK Gupta | TA 419 | 2026-02 | GRD 2 | 1 | 23 | 1
Mr. NK Gupta | TA 419 | 2026-02 | MS Construction | 1 | 35 | 1
Mr. NK Gupta | TA 419 | 2026-02 | NV Infra | 1 | 38 | 1
Mr. NK Gupta | TA 419 | 2026-02 | Sherawali Const | 1 | 32 | 1
Mr. NK Gupta | TA 419 | 2026-03 | D&V | 2 | 41.5 | 2
Mr. NK Gupta | TA 419 | 2026-03 | NV Infra | 1 | 46 | 1
Mr. NK Gupta | TA 419 | 2026-03 | Ravinder | 1 | 19 | 1
Mr. NK Gupta | TA 419 | 2026-03 | Shiv Shakti | 1 | 44 | 1
Mr. NK Gupta | TA 419 | 2026-03 | Utkarsh Const | 1 | 43 | 1
Mr. NK Gupta | TA 419 | 2026-04 | D&V | 2 | 26 | 2
Mr. NK Gupta | TA 419 | 2026-04 | GRD 1 | 2 | 51.5 | 2
Mr. NK Gupta | TA 419 | 2026-04 | Piroth and Sons | 1 | 35 | 1
Mr. NK Gupta | TA 419 | 2026-04 | Ravindra | 1 | 27 | 1
Mr. NK Gupta | TA 419 | 2026-04 | Shiv Shakti | 1 | 29 | 1
Mr. NK Gupta | TA 419 | 2026-04 | Utkarsh Const/ D&V | 1 | 127 | 1
Mr. NK Gupta | TA 419 | 2026-05 | D&V | 3 | 25.33 | 3
Mr. NK Gupta | TA 419 | 2026-05 | GRD | 2 | 21 | 2
Mr. NK Gupta | TA 419 | 2026-05 | GRD 2 | 1 | 26 | 1
Mr. NK Gupta | TA 419 | 2026-05 | Pachauri | 2 | 32 | 2
Mr. NK Gupta | TA 419 | 2026-05 | Radhe Enterprises | 1 | 34 | 1
Mr. NK Gupta | TA 419 | 2026-05 | Rahul Raghav | 1 | 10 | 1
Mr. NK Gupta | TA 419 | 2026-05 | Rahul Raghav | 1 | 10 | 1
Mr. NK Gupta | TA 419 | 2026-05 | Ravindra | 1 | 75 | 1
Mr. NK Gupta | TA 419 | 2026-05 | Shiv Shakti | 1 | 30 | 1
Mr. NK Gupta | TA 419 | 2026-05 | TDCL(Ravindra) | 1 | 13 | 1
Mr. NK Gupta | TA 419 | 2026-05 | Thakur Engineering | 1 | 104 | 1
Mr. NK Gupta | TA 419 | 2026-05 | Virender Const | 3 | 21.33 | 3
Mr. NK Gupta | TA 419 | 2026-05 | Vivan Const | 1 | 26 | 1
Mr. NK Gupta | TA 419 | 2026-06 | D&V | 2 | 53.5 | 2
Mr. NK Gupta | TA 419 | 2026-06 | GRD 2 | 1 | 9 | 1
Mr. NK Gupta | TA 419 | 2026-06 | Pachauri | 2 | 13.5 | 2
Mr. NK Gupta | TA 419 | 2026-06 | Piroth and Sons | 1 | 30 | 1
Mr. NK Gupta | TA 419 | 2026-06 | Radhe Enterprises | 1 | 45 | 1
Mr. NK Gupta | TA 419 | 2026-06 | Rahul Raghav | 2 | 13.5 | 2
Mr. NK Gupta | TA 419 | 2026-06 | Shiv Shakti | 1 | 32 | 1

## Gang Summary
Gang | Total Foundations | Active Months | Avg Foundations / Active Month | Median Monthly Foundations | Best Month Foundations | Projects Worked | Project List | Avg Duration Days | Valid Duration Foundations
Subash | 98 | 16 | 6.12 | 7 | 10 | 1 | TA 421 | 5.33 | 96
Garg Energy | 78 | 19 | 4.11 | 3 | 7 | 1 | TA 419 | 11.05 | 77
Khatun | 68 | 15 | 4.53 | 5 | 7 | 1 | TA 421 | 6.07 | 67
ATK Constructions | 53 | 10 | 5.3 | 5 | 13 | 1 | TA 421 | 16.38 | 52
Dewi Construction(Girendra) | 40 | 10 | 4 | 4.5 | 6 | 1 | TA 416 | 7 | 40
Himanshi Agency | 40 | 10 | 4 | 4 | 9 | 1 | TA 414 | 12.71 | 38
Pinky Dewi | 37 | 11 | 3.36 | 4 | 5 | 1 | TA 416 | 9.08 | 36
VH Rajpoot cont. | 35 | 11 | 3.18 | 3 | 6 | 1 | TA 416 | 7.74 | 35
ATK CONSTRUCTIONS | 32 | 6 | 5.33 | 5 | 10 | 1 | TA 421 | 16.66 | 32
Reeta Bharti | 29 | 11 | 2.64 | 3 | 4 | 1 | TA 416 | 11.52 | 29
Ashok-2 (Venkateshwarlu) | 28 | 9 | 3.11 | 2 | 6 | 1 | TA 421 | 14.81 | 27
Ammu Engineering | 26 | 6 | 4.33 | 4.5 | 8 | 1 | TA 421 | 33.58 | 26
NV Infra | 26 | 15 | 1.73 | 2 | 3 | 1 | TA 419 | 21.6 | 25
Venkateshwarlu | 26 | 9 | 2.89 | 3 | 6 | 1 | TA 421 | 15.38 | 26
Laxmi Const. | 25 | 9 | 2.78 | 3 | 5 | 1 | TA 416 | 8.16 | 25
Amar Singh | 24 | 8 | 3 | 3 | 5 | 1 | TA 416 | 8.46 | 24
BaLraJ | 23 | 5 | 4.6 | 4 | 8 | 1 | TA 421 | 18.39 | 23
Gang-01 (Sanjay) | 23 | 8 | 2.88 | 3 | 5 | 1 | TA 418 | 24.09 | 22
Praveen | 23 | 15 | 1.53 | 1 | 3 | 1 | TA 421 | 18.04 | 23
Dharamdas Contractor | 22 | 8 | 2.75 | 2.5 | 5 | 1 | TA 416 | 10.95 | 22
Haque Constr. | 22 | 6 | 3.67 | 4 | 4 | 1 | TA 418 | 16.55 | 20
SSR engineering | 22 | 8 | 2.75 | 3 | 4 | 1 | TA 416 | 8.95 | 22
KEC - 02 (Barkat Ali) | 21 | 8 | 2.62 | 3 | 3 | 1 | TA 418 | 29.9 | 21
ASC heights | 20 | 7 | 2.86 | 3 | 4 | 1 | TA 416 | 9.55 | 20
Aneshwar Traders | 20 | 8 | 2.5 | 2 | 6 | 1 | TA 416 | 11.15 | 20
D k Verma | 20 | 7 | 2.86 | 3 | 5 | 1 | TA 421 | 7.3 | 20
Unnati Construction | 20 | 11 | 1.82 | 1 | 4 | 1 | TA 414 | 41.05 | 20
Ammu Eng | 19 | 4 | 4.75 | 5 | 6 | 1 | TA 421 | 13.84 | 19
Kirti Construction | 19 | 8 | 2.38 | 2.5 | 4 | 1 | TA 419 | 12.21 | 19
A V I ENTERPRISE | 18 | 9 | 2 | 2 | 4 | 1 | TA 416 | 10.17 | 18
Garg Construction | 18 | 7 | 2.57 | 3 | 4 | 1 | TA 416 | 11.44 | 18
Hassan | 18 | 7 | 2.57 | 3 | 3 | 1 | TA 421 | 11.72 | 18
Horil Mahto | 18 | 7 | 2.57 | 3 | 4 | 1 | TA 416 | 11.44 | 18
Jyoti Construction | 18 | 8 | 2.25 | 2.5 | 4 | 2 | TA 414; TA 510FDN | 19.33 | 18
M A Construction | 18 | 6 | 3 | 3 | 4 | 1 | TA 416 | 10.5 | 18
Khatan | 17 | 4 | 4.25 | 4.5 | 6 | 1 | TA 421 | 7.41 | 17
Tower Foundation | 17 | 8 | 2.12 | 2 | 3 | 1 | TA 414 | 16.44 | 16
Gang-02 (Sanjay) | 16 | 6 | 2.67 | 2.5 | 4 | 1 | TA 418 | 32.47 | 15
M/s TOFIT | 16 | 6 | 2.67 | 2.5 | 4 | 1 | TA 418 | 9.62 | 16
Pankaj | 16 | 5 | 3.2 | 3 | 5 | 1 | TA 416 | 8.88 | 16
SAIFI CON. | 16 | 9 | 1.78 | 2 | 3 | 1 | TA 416 | 11.38 | 16
M/S MDPL | 15 | 7 | 2.14 | 2 | 4 | 1 | TA 418 | 15.79 | 14
Maa Durga | 15 | 7 | 2.14 | 2 | 3 | 1 | TA 416 | 11.4 | 15
Ananya Traders-1 | 14 | 7 | 2 | 2 | 4 | 1 | TA 416 | 12.29 | 14
Khodiyarkrupa | 14 | 8 | 1.75 | 1 | 3 | 1 | TA 414 | 21.54 | 13
TaGore | 14 | 5 | 2.8 | 2 | 5 | 1 | TA 421 | 43.43 | 14
B.K.Traders | 13 | 6 | 2.17 | 2 | 5 | 1 | TA 510FDN | 9.62 | 13
Gagan enterprise.1 | 13 | 5 | 2.6 | 1 | 5 | 1 | TA 416 | 11.46 | 13
Haji Enterprises | 13 | 7 | 1.86 | 2 | 3 | 1 | TA 510FDN | 15.85 | 13
Himanshi | 13 | 5 | 2.6 | 2 | 6 | 1 | TA 414 | 21.46 | 13
Sumit Constrcution | 13 | 2 | 6.5 | 6.5 | 7 | 1 | TA 416 | 6.77 | 13
Vinayak Enterprise | 13 | 7 | 1.86 | 2 | 2 | 1 | TA 416 | 13.38 | 13
A K Rajpoot | 12 | 4 | 3 | 3 | 4 | 1 | TA 416 | 9.92 | 12
ANJU Const. | 12 | 4 | 3 | 3 | 4 | 1 | TA 421 | 24.5 | 12
BLG Infra | 12 | 3 | 4 | 4 | 6 | 1 | TA 510FDN | 7.33 | 12
Ananya Traders-2 | 11 | 3 | 3.67 | 3 | 5 | 1 | TA 416 | 8 | 11
Ashok kumar (Thotta) | 11 | 3 | 3.67 | 4 | 5 | 1 | TA 421 | 8.73 | 11
Bala Ji | 11 | 3 | 3.67 | 2 | 7 | 1 | TA 419 | 6.36 | 11
Naziruddin | 11 | 3 | 3.67 | 4 | 4 | 1 | TA 421 | 8.6 | 10
Neelkant Infra Project | 11 | 5 | 2.2 | 2 | 4 | 1 | TA 414 | 10.09 | 11
Arya Enterprises | 10 | 4 | 2.5 | 2.5 | 4 | 2 | TA 414; TA 510FDN | 11 | 10
Gang-02(Sanjay) | 10 | 4 | 2.5 | 2.5 | 4 | 1 | TA 418 | 9.4 | 10
J M Enterprise | 10 | 6 | 1.67 | 1.5 | 3 | 1 | TA 416 | 9.7 | 10
MS Construction | 10 | 7 | 1.43 | 1 | 3 | 1 | TA 419 | 17.6 | 10
R K Constrcution | 10 | 5 | 2 | 2 | 4 | 1 | TA 416 | 8.9 | 10
AMMU ENG. | 9 | 4 | 2.25 | 2 | 4 | 1 | TA 421 | 25.44 | 9
D&V | 9 | 4 | 2.25 | 2 | 3 | 1 | TA 419 | 35.33 | 9
Vihan | 9 | 6 | 1.5 | 1 | 3 | 1 | TA 510FDN | 17.33 | 9
(ATK-02) | 8 | 2 | 4 | 4 | 5 | 1 | TA 418 | 10.62 | 8
Anshika con. | 8 | 3 | 2.67 | 2 | 4 | 1 | TA 416 | 9.86 | 7
Ashok-2 | 8 | 2 | 4 | 4 | 5 | 1 | TA 421 | 10.5 | 8
GRD 2 | 8 | 5 | 1.6 | 1 | 3 | 1 | TA 419 | 13 | 8
Jyoti | 8 | 5 | 1.6 | 1 | 3 | 1 | TA 414 | 16.25 | 8
K R Associates | 8 | 5 | 1.6 | 1 | 3 | 1 | TA 416 | 11.75 | 8
KEC GANG -04 | 8 | 3 | 2.67 | 3 | 4 | 1 | TA 418 | 25.38 | 8
Sai guru Construction | 8 | 7 | 1.14 | 1 | 2 | 1 | TA 414 | 15.62 | 8
Saiguru | 8 | 4 | 2 | 2 | 3 | 1 | TA 414 | 14.12 | 8
Shakaldev | 8 | 3 | 2.67 | 3 | 3 | 1 | TA 510FDN | 21.12 | 8
TDCL | 8 | 4 | 2 | 2 | 3 | 1 | TA 419 | 12.25 | 8
ANURADHA | 7 | 3 | 2.33 | 2 | 3 | 1 | TA 418 | 24.57 | 7
Ashok | 7 | 2 | 3.5 | 3.5 | 4 | 1 | TA 421 | 16 | 7
BLG Construction | 7 | 3 | 2.33 | 2 | 4 | 1 | TA 414 | 10.86 | 7
Dev Construction | 7 | 4 | 1.75 | 1.5 | 3 | 1 | TA 414 | 13 | 7
GRD 1 | 7 | 4 | 1.75 | 2 | 2 | 1 | TA 419 | 24.86 | 7
Gang-01(Sanjay) | 7 | 4 | 1.75 | 1.5 | 3 | 1 | TA 418 | 8.14 | 7
J.$lnGH | 7 | 2 | 3.5 | 3.5 | 5 | 1 | TA 421 | 5.86 | 7
KEC - 01 (Barkat Ali) | 7 | 3 | 2.33 | 3 | 3 | 1 | TA 418 | 13.86 | 7
KPK | 7 | 3 | 2.33 | 2 | 3 | 1 | TA 418 | 23.86 | 7
Maa Const. | 7 | 3 | 2.33 | 2 | 4 | 1 | TA 421 | 11.43 | 7
Rudra Construction | 7 | 5 | 1.4 | 1 | 2 | 1 | TA 416 | 11 | 7
SUBHASH | 7 | 3 | 2.33 | 2 | 4 | 1 | TA 418 | 8.57 | 7
Team - 3 (ATK-01) | 7 | 3 | 2.33 | 2 | 4 | 1 | TA 418 | 16.43 | 7
VED ENTTERPRISE | 7 | 3 | 2.33 | 2 | 4 | 1 | TA 416 | 8.43 | 7
Virendra | 7 | 4 | 1.75 | 2 | 2 | 1 | TA 419 | 20.29 | 7
Ashok kumar | 6 | 3 | 2 | 2 | 3 | 1 | TA 421 | 19 | 6
BLG | 6 | 3 | 2 | 2 | 2 | 1 | TA 414 | 9.5 | 6
Chandrakant Patel | 6 | 4 | 1.5 | 1.5 | 2 | 1 | TA 510FDN | 14 | 6
GANG - A2 | 6 | 4 | 1.5 | 1.5 | 2 | 1 | TA 418 | 8.33 | 6
J.$lnGH - o1 | 6 | 3 | 2 | 1 | 4 | 1 | TA 421 | 7.17 | 6
Krishna | 6 | 2 | 3 | 3 | 4 | 1 | TA 414 | 11.83 | 6
Om Infra | 6 | 2 | 3 | 3 | 4 | 1 | TA 510FDN | 16.67 | 6
Saiguru Construction | 6 | 3 | 2 | 2 | 3 | 1 | TA 414 | 11.17 | 6
Shivkrupa | 6 | 4 | 1.5 | 1.5 | 2 | 1 | TA 414 | 13.33 | 6
Surjeet | 6 | 4 | 1.5 | 1 | 3 | 1 | TA 419 | 14 | 6
Adhya Brother | 5 | 4 | 1.25 | 1 | 2 | 1 | TA 414 | 17.4 | 5
Amit Kumar | 5 | 2 | 2.5 | 2.5 | 4 | 1 | TA 421 | 11.2 | 5
Balraj | 5 | 2 | 2.5 | 2.5 | 3 | 1 | TA 421 | 11.4 | 5
Bindu | 5 | 3 | 1.67 | 1 | 3 | 1 | TA 418 | 23.4 | 5
D&B | 5 | 3 | 1.67 | 2 | 2 | 1 | TA 419 | 17.6 | 5
Gagan enterprise.2 | 5 | 2 | 2.5 | 2.5 | 3 | 1 | TA 416 | 9.4 | 5
Gauri Shankar Mahto | 5 | 2 | 2.5 | 2.5 | 3 | 1 | TA 421 | 9.2 | 5
J.$lnGH - o2 | 5 | 2 | 2.5 | 2.5 | 4 | 1 | TA 421 | 11.8 | 5
Jyoti 2 | 5 | 3 | 1.67 | 2 | 2 | 1 | TA 414 | 26.2 | 5
KEC GANG -02 | 5 | 3 | 1.67 | 2 | 2 | 1 | TA 418 | 16 | 5
M K infra | 5 | 3 | 1.67 | 2 | 2 | 1 | TA 416 | 18.2 | 5
MD Hussain | 5 | 4 | 1.25 | 1 | 2 | 1 | TA 510FDN | 15.8 | 5
Pankaj Kumar | 5 | 4 | 1.25 | 1 | 2 | 1 | TA 416 | 18.75 | 4
Team - 2 (SM Constr.) | 5 | 3 | 1.67 | 1 | 3 | 1 | TA 418 | 19.8 | 5
Unnati | 5 | 2 | 2.5 | 2.5 | 3 | 1 | TA 414 | 13 | 5
Adarsh Gang | 4 | 3 | 1.33 | 1 | 2 | 1 | TA 418 | 23 | 4
Amit Choudhry | 4 | 3 | 1.33 | 1 | 2 | 1 | TA 416 | 22 | 3
Company Gang | 4 | 2 | 2 | 2 | 2 | 1 | TA 421 | 23 | 4
DCLCSL( Ravindra) | 4 | 4 | 1 | 1 | 1 | 1 | TA 419 | 21.33 | 3
Deep Power | 4 | 3 | 1.33 | 1 | 2 | 1 | TA 414 | 24.75 | 4
GANG - A1 | 4 | 2 | 2 | 2 | 3 | 1 | TA 418 | 7.75 | 4
Integer Infratech Pvt Ltd | 4 | 3 | 1.33 | 1 | 2 | 1 | TA 414 | 14 | 4
Jyoti 1 | 4 | 3 | 1.33 | 1 | 2 | 1 | TA 414 | 10 | 4
Jyoti 3 | 4 | 2 | 2 | 2 | 2 | 1 | TA 414 | 11.75 | 4
KEC GANG -05 | 4 | 1 | 4 | 4 | 4 | 1 | TA 418 | 8 | 4
KEC GANG -06 | 4 | 2 | 2 | 2 | 3 | 1 | TA 418 | 9 | 3
Krishna Construction | 4 | 3 | 1.33 | 1 | 2 | 1 | TA 414 | 14.5 | 4
Mahon Mahto | 4 | 4 | 1 | 1 | 1 | 1 | TA 416 | 19 | 4
Pachauri | 4 | 2 | 2 | 2 | 2 | 1 | TA 419 | 22.75 | 4
Punam Kumari | 4 | 3 | 1.33 | 1 | 2 | 1 | TA 416 | 17.75 | 4
Punam kumari-1 | 4 | 4 | 1 | 1 | 1 | 1 | TA 416 | 18.67 | 3
Punam kumari-2 | 4 | 3 | 1.33 | 1 | 2 | 1 | TA 416 | 12.5 | 4
Shiv Shakti | 4 | 4 | 1 | 1 | 1 | 1 | TA 419 | 33.75 | 4
Shyam Infra | 4 | 3 | 1.33 | 1 | 2 | 1 | TA 419 | 14 | 4
Tagore | 4 | 2 | 2 | 2 | 3 | 1 | TA 421 | 13 | 4
Tyagi Const | 4 | 2 | 2 | 2 | 2 | 1 | TA 419 | 10 | 4
Vivan Enterprise | 4 | 2 | 2 | 2 | 2 | 1 | TA 416 | 7.5 | 4
venkateshwarlu | 4 | 2 | 2 | 2 | 2 | 1 | TA 421 | 11.75 | 4
2026-03-02 00:00:00 | 3 | 2 | 1.5 | 1.5 | 2 | 2 | TA 416; TA 421 |  | 0
2026-06-15 00:00:00 | 3 | 2 | 1.5 | 1.5 | 2 | 1 | TA 418 |  | 0
AMMU ENG.-2 | 3 | 1 | 3 | 3 | 3 | 1 | TA 421 | 10.33 | 3
Adhyey Brothers | 3 | 2 | 1.5 | 1.5 | 2 | 1 | TA 414 | 12 | 3
Ahlawat Cpnstruction | 3 | 2 | 1.5 | 1.5 | 2 | 1 | TA 419 | 7.67 | 3
Aloriva Global | 3 | 2 | 1.5 | 1.5 | 2 | 1 | TA 416 | 16.33 | 3
Amit Const | 3 | 2 | 1.5 | 1.5 | 2 | 1 | TA 416 | 10 | 3
Anya Infra | 3 | 2 | 1.5 | 1.5 | 2 | 1 | TA 414 | 21.67 | 3
Bajrang Const | 3 | 3 | 1 | 1 | 1 | 1 | TA 419 | 21 | 3
GANG - 1 | 3 | 2 | 1.5 | 1.5 | 2 | 1 | TA 418 | 15.67 | 3
GANG-2 | 3 | 1 | 3 | 3 | 3 | 1 | TA 418 | 14.33 | 3
GRD | 3 | 2 | 1.5 | 1.5 | 2 | 1 | TA 419 | 16.67 | 3
GRD Enterprises | 3 | 3 | 1 | 1 | 1 | 1 | TA 419 | 16.67 | 3
KEC GANG - 06 | 3 | 1 | 3 | 3 | 3 | 1 | TA 418 | 18.67 | 3
KEC GANG -07 | 3 | 1 | 3 | 3 | 3 | 1 | TA 418 | 8.67 | 3
Khalil Const. | 3 | 1 | 3 | 3 | 3 | 1 | TA 416 | 8 | 3
Khodiyar | 3 | 3 | 1 | 1 | 1 | 1 | TA 414 | 52.67 | 3
Khodiyarkrupa-2 | 3 | 2 | 1.5 | 1.5 | 2 | 1 | TA 414 | 15.33 | 3
Murugan Gang | 3 | 2 | 1.5 | 1.5 | 2 | 1 | TA 414 | 16 | 3
RR CONST | 3 | 2 | 1.5 | 1.5 | 2 | 1 | TA 421 | 14.33 | 3
Rahul Raghav | 3 | 2 | 1.5 | 1.5 | 2 | 1 | TA 419 | 12.33 | 3
SAVITHA | 3 | 2 | 1.5 | 1.5 | 2 | 1 | TA 418 | 20.33 | 3
Saiguru 2 | 3 | 2 | 1.5 | 1.5 | 2 | 1 | TA 414 | 12.33 | 3
Sainik Trader | 3 | 3 | 1 | 1 | 1 | 1 | TA 416 | 23.67 | 3
Shyam Ent | 3 | 2 | 1.5 | 1.5 | 2 | 1 | TA 419 | 19.67 | 3
Suraj Construction | 3 | 2 | 1.5 | 1.5 | 2 | 1 | TA 414 | 201.33 | 3
Team - 1 (Sanjay) | 3 | 2 | 1.5 | 1.5 | 2 | 1 | TA 418 | 15 | 3
Virender Const | 3 | 1 | 3 | 3 | 3 | 1 | TA 419 | 21.33 | 3
Visionary & Co | 3 | 2 | 1.5 | 1.5 | 2 | 1 | TA 421 | 11.33 | 3
Visionary Co | 3 | 2 | 1.5 | 1.5 | 2 | 1 | TA 421 | 23 | 3
s.K.Janarul Sheikh | 3 | 2 | 1.5 | 1.5 | 2 | 1 | TA 421 | 10.33 | 3
2025-12-05 00:00:00 | 2 | 1 | 2 | 2 | 2 | 1 | TA 418 |  | 0
2026-01-26 00:00:00 | 2 | 1 | 2 | 2 | 2 | 1 | TA 418 |  | 0
2026-02-07 00:00:00 | 2 | 1 | 2 | 2 | 2 | 2 | TA 418; TA 421 |  | 0
2026-02-09 00:00:00 | 2 | 1 | 2 | 2 | 2 | 2 | TA 416; TA 418 |  | 0
2026-02-11 00:00:00 | 2 | 1 | 2 | 2 | 2 | 2 | TA 416; TA 421 |  | 0
2026-02-20 00:00:00 | 2 | 1 | 2 | 2 | 2 | 2 | TA 416; TA 421 |  | 0
2026-06-05 00:00:00 | 2 | 2 | 1 | 1 | 1 | 1 | TA 418 |  | 0
ABS Construction | 2 | 2 | 1 | 1 | 1 | 1 | TA 510FDN | 23 | 2
AP Developers | 2 | 1 | 2 | 2 | 2 | 1 | TA 414 | 29.5 | 2
APR Associates | 2 | 2 | 1 | 1 | 1 | 1 | TA 414 | 27 | 2
Amit Choudhury | 2 | 1 | 2 | 2 | 2 | 1 | TA 416 | 20 | 2
Anand Construction | 2 | 1 | 2 | 2 | 2 | 1 | TA 416 | 13.5 | 2
Ananya trader | 2 | 2 | 1 | 1 | 1 | 1 | TA 416 | 15.5 | 2
D K Verma | 2 | 2 | 1 | 1 | 1 | 1 | TA 421 | 7.5 | 2
D&P | 2 | 2 | 1 | 1 | 1 | 1 | TA 419 | 54.5 | 2
Deep Power 1 | 2 | 2 | 1 | 1 | 1 | 1 | TA 414 | 12 | 2
Deep Power 2 | 2 | 2 | 1 | 1 | 1 | 1 | TA 414 | 29.5 | 2
GANG - A1 (M) | 2 | 1 | 2 | 2 | 2 | 1 | TA 418 | 6 | 2
GRD Enterprises 2 | 2 | 1 | 2 | 2 | 2 | 1 | TA 419 | 9.5 | 2
Gouri Shankar | 2 | 1 | 2 | 2 | 2 | 1 | TA 416 | 16.5 | 2
Hassan-2 | 2 | 1 | 2 | 2 | 2 | 1 | TA 421 | 9.5 | 2
Jay Sri Ram | 2 | 1 | 2 | 2 | 2 | 1 | TA 416 | 9.5 | 2
Jayesh Electrical | 2 | 1 | 2 | 2 | 2 | 1 | TA 414 | 13 | 2
Jwala Singh -01 | 2 | 1 | 2 | 2 | 2 | 1 | TA 421 | 5.5 | 2
KEC GANG - 08 | 2 | 1 | 2 | 2 | 2 | 1 | TA 418 | 21 | 2
KEC GANG -07 - HQ | 2 | 1 | 2 | 2 | 2 | 1 | TA 418 | 6 | 2
Kasta Bhanjan | 2 | 2 | 1 | 1 | 1 | 1 | TA 414 | 20.5 | 2
Khodiyar Trader | 2 | 2 | 1 | 1 | 1 | 1 | TA 414 | 11.5 | 2
Khodiyarkripa | 2 | 1 | 2 | 2 | 2 | 1 | TA 414 | 14.5 | 2
Kongres Kumar- | 2 | 2 | 1 | 1 | 1 | 1 | TA 416 | 23.5 | 2
Kongres Kumar-2 | 2 | 2 | 1 | 1 | 1 | 1 | TA 416 | 26 | 2
LALA GANG | 2 | 1 | 2 | 2 | 2 | 1 | TA 418 | 31.5 | 2
Maa Bhavani | 2 | 1 | 2 | 2 | 2 | 1 | TA 510FDN | 9.5 | 2
Maa Construction | 2 | 2 | 1 | 1 | 1 | 1 | TA 416 | 22 | 2
Mahon mahto | 2 | 2 | 1 | 1 | 1 | 1 | TA 416 | 51 | 2
Murgun | 2 | 2 | 1 | 1 | 1 | 1 | TA 414 | 23.5 | 2
Om Enterprise | 2 | 1 | 2 | 2 | 2 | 1 | TA 414 | 14 | 2
Piroth and Sons | 2 | 2 | 1 | 1 | 1 | 1 | TA 419 | 32.5 | 2
Punam kumari-3 | 2 | 2 | 1 | 1 | 1 | 1 | TA 416 | 28 | 1
Radha Construction | 2 | 2 | 1 | 1 | 1 | 1 | TA 416 | 20.5 | 2
Radhe Enterprises | 2 | 2 | 1 | 1 | 1 | 1 | TA 419 | 39.5 | 2
Ravindra | 2 | 2 | 1 | 1 | 1 | 1 | TA 419 | 51 | 2
Rudra | 2 | 2 | 1 | 1 | 1 | 1 | TA 510FDN | 19.5 | 2
Saiguru 1 | 2 | 2 | 1 | 1 | 1 | 1 | TA 414 | 40.5 | 2
Shakila Khatun | 2 | 1 | 2 | 2 | 2 | 1 | TA 421 | 4 | 2
Sherawali Const | 2 | 2 | 1 | 1 | 1 | 1 | TA 419 | 25 | 2
TSB | 2 | 2 | 1 | 1 | 1 | 1 | TA 421 | 25.5 | 2
Tower Founadation | 2 | 2 | 1 | 1 | 1 | 1 | TA 414 | 12 | 2
Utkarsh Const | 2 | 2 | 1 | 1 | 1 | 1 | TA 419 | 24.5 | 2
Velu | 2 | 1 | 2 | 2 | 2 | 1 | TA 414 | 16 | 2
Velu Construction | 2 | 1 | 2 | 2 | 2 | 1 | TA 414 | 5 | 2
Vishal construction | 2 | 2 | 1 | 1 | 1 | 1 | TA 416 | 14 | 2
jyoti const 2 | 2 | 1 | 2 | 2 | 2 | 1 | TA 414 | 64 | 2
khatun | 2 | 1 | 2 | 2 | 2 | 1 | TA 421 | 6 | 2
2025-09-07 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 421 |  | 0
2025-10-13 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 418 |  | 0
2025-10-18 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 |  | 0
2025-10-23 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 421 |  | 0
2025-10-24 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 |  | 0
2025-10-26 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 |  | 0
2025-10-31 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 |  | 0
2025-11-03 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 |  | 0
2025-11-06 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 |  | 0
2025-11-10 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 418 |  | 0
2025-11-13 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 |  | 0
2025-11-18 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 |  | 0
2025-11-25 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 |  | 0
2025-12-04 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 |  | 0
2025-12-10 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 |  | 0
2025-12-22 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 418 |  | 0
2025-12-30 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 418 |  | 0
2026-01-31 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 421 |  | 0
2026-02-01 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 421 |  | 0
2026-02-04 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 421 |  | 0
2026-02-08 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 421 |  | 0
2026-02-12 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 421 |  | 0
2026-02-14 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 |  | 0
2026-02-16 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 418 |  | 0
2026-02-17 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 |  | 0
2026-02-19 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 |  | 0
2026-02-22 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 |  | 0
2026-02-25 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 421 |  | 0
2026-02-26 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 |  | 0
2026-03-06 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 418 |  | 0
2026-03-09 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 418 |  | 0
2026-03-14 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 418 |  | 0
2026-03-22 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 418 |  | 0
2026-04-16 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 418 |  | 0
2026-05-02 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 418 |  | 0
2026-05-05 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 |  | 0
2026-05-08 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 |  | 0
2026-05-10 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 |  | 0
2026-05-24 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 418 |  | 0
2026-05-26 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 418 |  | 0
2026-05-30 00:00:00 | 1 | 1 | 1 | 1 | 1 | 1 | TA 418 |  | 0
A P Developers | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 18 | 1
ADARSH | 1 | 1 | 1 | 1 | 1 | 1 | TA 418 | 126 | 1
Adhya Enterprises | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 13 | 1
Ahlawat Const | 1 | 1 | 1 | 1 | 1 | 1 | TA 419 | 18 | 1
Amar singh | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 | 25 | 1
Ambani | 1 | 1 | 1 | 1 | 1 | 1 | TA 510FDN | 25 | 1
Amit Yadav 1 | 1 | 1 | 1 | 1 | 1 | 1 | TA 419 | 9 | 1
Arya Implex | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 38 | 1
Ashok Kumar | 1 | 1 | 1 | 1 | 1 | 1 | TA 421 | 7 | 1
Ashok-1 | 1 | 1 | 1 | 1 | 1 | 1 | TA 421 | 9 | 1
Ashokkumar | 1 | 1 | 1 | 1 | 1 | 1 | TA 421 | 8 | 1
BLG (197/1) | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 13 | 1
BalraJ | 1 | 1 | 1 | 1 | 1 | 1 | TA 421 | 8 | 1
Company Gang + ATK | 1 | 1 | 1 | 1 | 1 | 1 | TA 421 | 35 | 1
Dev Contruction | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 16 | 1
Devine | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 | 13 | 1
GANG - 4 | 1 | 1 | 1 | 1 | 1 | 1 | TA 418 | 44 | 1
GANG-1 | 1 | 1 | 1 | 1 | 1 | 1 | TA 418 | 18 | 1
GRD Enterprise | 1 | 1 | 1 | 1 | 1 | 1 | TA 419 | 14 | 1
GRD Enterprises 1 | 1 | 1 | 1 | 1 | 1 | 1 | TA 419 | 7 | 1
GRD Enterprises1 | 1 | 1 | 1 | 1 | 1 | 1 | TA 419 | 22 | 1
Gagan enterprise.2 (Kajol) | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 | 13 | 1
Gang-02(Sanjay) / KEC - 02 (Barkat Ali) | 1 | 1 | 1 | 1 | 1 | 1 | TA 418 | 14 | 1
GowriShankar | 1 | 1 | 1 | 1 | 1 | 1 | TA 421 | 8 | 1
Haji Enterprises-1 | 1 | 1 | 1 | 1 | 1 | 1 | TA 510FDN | 18 | 1
Haji Enterprises2 | 1 | 1 | 1 | 1 | 1 | 1 | TA 510FDN | 10 | 1
Harshvi | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 399 | 1
Hassan -2 | 1 | 1 | 1 | 1 | 1 | 1 | TA 421 | 18 | 1
Himanshi 1 | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 33 | 1
Himanshi 2 | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 14 | 1
JDG Enterprises | 1 | 1 | 1 | 1 | 1 | 1 | TA 510FDN | 25 | 1
Jyoti Const | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 24 | 1
Jyoti Construction 2 | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 97 | 1
Jyoti Contruction | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 11 | 1
KAVAL CHAND | 1 | 1 | 1 | 1 | 1 | 1 | TA 418 | 22 | 1
KEC - 03 (Barkat Ali) | 1 | 1 | 1 | 1 | 1 | 1 | TA 418 |  | 0
KEC GANG - 09 | 1 | 1 | 1 | 1 | 1 | 1 | TA 418 | 14 | 1
KEC GANG -06 -HQ | 1 | 1 | 1 | 1 | 1 | 1 | TA 418 | 3 | 1
KEC GANG -09 | 1 | 1 | 1 | 1 | 1 | 1 | TA 418 | 4 | 1
KEVAL CHAND | 1 | 1 | 1 | 1 | 1 | 1 | TA 418 | 80 | 1
KND | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 109 | 1
Khodiyar 1 | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 11 | 1
Khodiyar Kripa Enterprise | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 8 | 1
Khodiyar Krupa | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 19 | 1
Khodiyar Traders | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 8 | 1
Khodiyarkrupa-1 | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 15 | 1
Kongres Kumar-1 | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 | 33 | 1
Krishna Constrction | 1 | 1 | 1 | 1 | 1 | 1 | TA 510FDN | 47 | 1
MALLIK CON | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 | 38 | 1
Manirul (Islam)-Khatun | 1 | 1 | 1 | 1 | 1 | 1 | TA 421 | 14 | 1
Murugan | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 42 | 1
Niranjan Singh | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 | 25 | 1
Om Construction | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 26 | 1
Punam Kumari-2 | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 | 43 | 1
Rahul Raghav | 1 | 1 | 1 | 1 | 1 | 1 | TA 419 | 10 | 1
Ravinder | 1 | 1 | 1 | 1 | 1 | 1 | TA 419 | 19 | 1
Saiguru-2 | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 9 | 1
Saran Communication | 1 | 1 | 1 | 1 | 1 | 1 | TA 419 | 29 | 1
Selva Murugan | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 7 | 1
Shiv Kripa Infra | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 17 | 1
Shiv krupa Infra | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 45 | 1
Shivkripa | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 14 | 1
Shre Shyam | 1 | 1 | 1 | 1 | 1 | 1 | TA 419 | 15 | 1
Shree Krishna | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 | 30 | 1
Shree Shyam | 1 | 1 | 1 | 1 | 1 | 1 | TA 419 | 5 | 1
Shyam | 1 | 1 | 1 | 1 | 1 | 1 | TA 419 | 19 | 1
Spotyfy-1 | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 | 26 | 1
Spotyfy-3 | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 | 38 | 1
TDCL(Ravindra) | 1 | 1 | 1 | 1 | 1 | 1 | TA 419 | 13 | 1
Thakur Engineering | 1 | 1 | 1 | 1 | 1 | 1 | TA 419 | 104 | 1
Tuuasta | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 15 | 1
Twaasta | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 19 | 1
Twasta | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 16 | 1
Tyagi Construction | 1 | 1 | 1 | 1 | 1 | 1 | TA 419 | 7 | 1
Unity India | 1 | 1 | 1 | 1 | 1 | 1 | TA 416 | 39 | 1
Utkarsh Const/ D&V | 1 | 1 | 1 | 1 | 1 | 1 | TA 419 | 127 | 1
Velu (213/0) | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 19 | 1
Veluu | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 11 | 1
Vivan Const | 1 | 1 | 1 | 1 | 1 | 1 | TA 419 | 26 | 1
Yadhav + D k Verma | 1 | 1 | 1 | 1 | 1 | 1 | TA 421 | 16 | 1
khodiyar | 1 | 1 | 1 | 1 | 1 | 1 | TA 414 | 15 | 1
s.K.Janarul | 1 | 1 | 1 | 1 | 1 | 1 | TA 421 | 17 | 1

## Duration Summary
PCH | Project | Month | Gang | Foundations Completed | Valid Duration Foundations | Avg Duration Days | Median Duration Days | Min Duration Days | Max Duration Days | Missing Start Date Count | Invalid Duration Count
Mr. Arun Felbin | TA 414 | 2024-05 | Suraj Construction | 2 | 2 | 10.5 | 10.5 | 10 | 11 | 0 | 0
Mr. Arun Felbin | TA 414 | 2024-10 | Anya Infra | 1 | 1 | 42 | 42 | 42 | 42 | 0 | 0
Mr. Arun Felbin | TA 414 | 2024-11 | Adhyey Brothers | 2 | 2 | 14.5 | 14.5 | 11 | 18 | 0 | 0
Mr. Arun Felbin | TA 414 | 2024-11 | Anya Infra | 2 | 2 | 11.5 | 11.5 | 9 | 14 | 0 | 0
Mr. Arun Felbin | TA 414 | 2024-12 | APR Associates | 1 | 1 | 23 | 23 | 23 | 23 | 0 | 0
Mr. Arun Felbin | TA 414 | 2024-12 | Adhya Enterprises | 1 | 1 | 13 | 13 | 13 | 13 | 0 | 0
Mr. Arun Felbin | TA 414 | 2024-12 | Adhyey Brothers | 1 | 1 | 7 | 7 | 7 | 7 | 0 | 0
Mr. Arun Felbin | TA 414 | 2024-12 | Arya Enterprises | 1 | 1 | 15 | 15 | 15 | 15 | 0 | 0
Mr. Arun Felbin | TA 414 | 2024-12 | Himanshi Agency | 4 | 4 | 14.25 | 14.5 | 10 | 18 | 0 | 0
Mr. Arun Felbin | TA 414 | 2024-12 | Integer Infratech Pvt Ltd | 1 | 1 | 17 | 17 | 17 | 17 | 0 | 0
Mr. Arun Felbin | TA 414 | 2024-12 | Khodiyarkrupa | 1 | 0 |  |  |  |  | 0 | 1
Mr. Arun Felbin | TA 414 | 2024-12 | Neelkant Infra Project | 1 | 1 | 9 | 9 | 9 | 9 | 0 | 0
Mr. Arun Felbin | TA 414 | 2024-12 | Unnati Construction | 1 | 1 | 11 | 11 | 11 | 11 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-01 | APR Associates | 1 | 1 | 31 | 31 | 31 | 31 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-01 | Adhya Brother | 1 | 1 | 15 | 15 | 15 | 15 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-01 | Arya Enterprises | 2 | 2 | 15.5 | 15.5 | 11 | 20 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-01 | Himanshi Agency | 3 | 3 | 6.33 | 6 | 5 | 8 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-01 | Integer Infratech Pvt Ltd | 2 | 2 | 13.5 | 13.5 | 12 | 15 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-01 | Neelkant Infra Project | 4 | 4 | 8.25 | 8.5 | 6 | 10 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-01 | Tower Foundation | 1 | 0 |  |  |  |  | 0 | 1
Mr. Arun Felbin | TA 414 | 2025-01 | Unnati Construction | 3 | 3 | 10.33 | 9 | 8 | 14 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-02 | Adhya Brother | 2 | 2 | 19 | 19 | 14 | 24 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-02 | Arya Enterprises | 2 | 2 | 15.5 | 15.5 | 8 | 23 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-02 | Himanshi Agency | 9 | 7 | 10.86 | 9 | 6 | 21 | 0 | 2
Mr. Arun Felbin | TA 414 | 2025-02 | Integer Infratech Pvt Ltd | 1 | 1 | 12 | 12 | 12 | 12 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-02 | Neelkant Infra Project | 2 | 2 | 8 | 8 | 7 | 9 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-02 | Unnati Construction | 4 | 4 | 8.5 | 8.5 | 6 | 11 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-03 | Adhya Brother | 1 | 1 | 7 | 7 | 7 | 7 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-03 | Himanshi Agency | 5 | 5 | 14.8 | 15 | 10 | 20 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-03 | Jyoti Construction | 1 | 1 | 27 | 27 | 27 | 27 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-03 | Neelkant Infra Project | 2 | 2 | 11.5 | 11.5 | 10 | 13 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-03 | Unnati Construction | 1 | 1 | 13 | 13 | 13 | 13 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-04 | Adhya Brother | 1 | 1 | 27 | 27 | 27 | 27 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-04 | Himanshi Agency | 6 | 6 | 9.17 | 9.5 | 6 | 13 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-04 | Jyoti Construction | 4 | 4 | 12.75 | 9.5 | 5 | 27 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-04 | Neelkant Infra Project | 2 | 2 | 15 | 15 | 8 | 22 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-04 | Sai guru Construction | 2 | 2 | 17.5 | 17.5 | 11 | 24 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-04 | Unnati Construction | 3 | 3 | 14 | 8 | 8 | 26 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-05 | Himanshi Agency | 2 | 2 | 24 | 24 | 14 | 34 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-05 | Jyoti Construction | 1 | 1 | 6 | 6 | 6 | 6 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-05 | Sai guru Construction | 1 | 1 | 8 | 8 | 8 | 8 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-05 | Unnati Construction | 1 | 1 | 16 | 16 | 16 | 16 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-06 | Sai guru Construction | 1 | 1 | 18 | 18 | 18 | 18 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-06 | Unnati Construction | 1 | 1 | 27 | 27 | 27 | 27 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-08 | Khodiyarkrupa | 1 | 1 | 20 | 20 | 20 | 20 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-09 | Khodiyarkrupa | 1 | 1 | 14 | 14 | 14 | 14 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-09 | Murugan | 1 | 1 | 42 | 42 | 42 | 42 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-09 | Saiguru Construction | 1 | 1 | 38 | 38 | 38 | 38 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-10 | Himanshi Agency | 2 | 2 | 10 | 10 | 8 | 12 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-10 | Jyoti Construction | 3 | 3 | 29.33 | 12 | 9 | 67 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-10 | Khodiyarkrupa | 3 | 3 | 12 | 8 | 6 | 22 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-11 | BLG Construction | 2 | 2 | 9 | 9 | 4 | 14 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-11 | Himanshi Agency | 4 | 4 | 16 | 14.5 | 8 | 27 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-11 | Jyoti Construction | 3 | 3 | 18.33 | 21 | 11 | 23 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-11 | Khodiyar Trader | 1 | 1 | 12 | 12 | 12 | 12 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-11 | Khodiyarkrupa | 1 | 1 | 16 | 16 | 16 | 16 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-11 | Khodiyarkrupa-1 | 1 | 1 | 15 | 15 | 15 | 15 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-11 | Khodiyarkrupa-2 | 2 | 2 | 12.5 | 12.5 | 11 | 14 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-11 | Murugan Gang | 2 | 2 | 19 | 19 | 18 | 20 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-11 | Sai guru Construction | 1 | 1 | 11 | 11 | 11 | 11 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-11 | Saiguru Construction | 2 | 2 | 4.5 | 4.5 | 4 | 5 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-11 | Shivkripa | 1 | 1 | 14 | 14 | 14 | 14 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-11 | Tower Foundation | 3 | 3 | 18.33 | 20 | 11 | 24 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-11 | Tuuasta | 1 | 1 | 15 | 15 | 15 | 15 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | A P Developers | 1 | 1 | 18 | 18 | 18 | 18 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | BLG Construction | 4 | 4 | 9.5 | 9.5 | 7 | 12 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Deep Power | 1 | 1 | 16 | 16 | 16 | 16 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Deep Power 1 | 1 | 1 | 14 | 14 | 14 | 14 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Deep Power 2 | 1 | 1 | 17 | 17 | 17 | 17 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Dev Construction | 3 | 3 | 12 | 12 | 9 | 15 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Himanshi Agency | 4 | 4 | 13 | 13.5 | 10 | 15 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Jayesh Electrical | 2 | 2 | 13 | 13 | 12 | 14 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Jyoti | 2 | 2 | 7.5 | 7.5 | 4 | 11 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Jyoti Construction | 3 | 3 | 12.67 | 13 | 11 | 14 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Kasta Bhanjan | 1 | 1 | 21 | 21 | 21 | 21 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Khodiyar 1 | 1 | 1 | 11 | 11 | 11 | 11 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Khodiyar Kripa Enterprise | 1 | 1 | 8 | 8 | 8 | 8 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Khodiyar Trader | 1 | 1 | 11 | 11 | 11 | 11 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Khodiyar Traders | 1 | 1 | 8 | 8 | 8 | 8 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Khodiyarkrupa | 3 | 3 | 8.33 | 9 | 6 | 10 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Khodiyarkrupa-2 | 1 | 1 | 21 | 21 | 21 | 21 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Krishna Construction | 1 | 1 | 15 | 15 | 15 | 15 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Murgun | 1 | 1 | 7 | 7 | 7 | 7 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Murugan Gang | 1 | 1 | 10 | 10 | 10 | 10 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Saiguru 2 | 1 | 1 | 12 | 12 | 12 | 12 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Saiguru Construction | 3 | 3 | 6.67 | 7 | 4 | 9 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Selva Murugan | 1 | 1 | 7 | 7 | 7 | 7 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Shiv Kripa Infra | 1 | 1 | 17 | 17 | 17 | 17 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Suraj Construction | 1 | 1 | 583 | 583 | 583 | 583 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Tower Foundation | 2 | 2 | 20 | 20 | 12 | 28 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Twaasta | 1 | 1 | 19 | 19 | 19 | 19 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Twasta | 1 | 1 | 16 | 16 | 16 | 16 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Unassigned | 5 | 5 | 8.6 | 9 | 5 | 12 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Unnati Construction | 2 | 2 | 9.5 | 9.5 | 7 | 12 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Velu Construction | 2 | 2 | 5 | 5 | 4 | 6 | 0 | 0
Mr. Arun Felbin | TA 414 | 2025-12 | Veluu | 1 | 1 | 11 | 11 | 11 | 11 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | AP Developers | 2 | 2 | 29.5 | 29.5 | 29 | 30 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | BLG | 2 | 2 | 12 | 12 | 8 | 16 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | BLG (197/1) | 1 | 1 | 13 | 13 | 13 | 13 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | BLG Construction | 1 | 1 | 20 | 20 | 20 | 20 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | Deep Power | 1 | 1 | 18 | 18 | 18 | 18 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | Deep Power 1 | 1 | 1 | 10 | 10 | 10 | 10 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | Deep Power 2 | 1 | 1 | 42 | 42 | 42 | 42 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | Dev Construction | 1 | 1 | 14 | 14 | 14 | 14 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | Dev Contruction | 1 | 1 | 16 | 16 | 16 | 16 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | Himanshi | 6 | 6 | 19.83 | 16 | 8 | 45 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | Himanshi 1 | 1 | 1 | 33 | 33 | 33 | 33 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | Himanshi 2 | 1 | 1 | 14 | 14 | 14 | 14 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | Jyoti | 3 | 3 | 8 | 10 | 4 | 10 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | Jyoti 1 | 1 | 1 | 16 | 16 | 16 | 16 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | Jyoti 3 | 2 | 2 | 12 | 12 | 8 | 16 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | Jyoti Construction 2 | 1 | 1 | 97 | 97 | 97 | 97 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | Kasta Bhanjan | 1 | 1 | 20 | 20 | 20 | 20 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | Khodiyarkrupa | 3 | 3 | 22.67 | 21 | 12 | 35 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | Krishna Construction | 2 | 2 | 15 | 15 | 11 | 19 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | Murgun | 1 | 1 | 40 | 40 | 40 | 40 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | Om Construction | 1 | 1 | 26 | 26 | 26 | 26 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | Om Enterprise | 2 | 2 | 14 | 14 | 10 | 18 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | Saiguru | 1 | 1 | 9 | 9 | 9 | 9 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | Saiguru 1 | 1 | 1 | 36 | 36 | 36 | 36 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | Saiguru 2 | 2 | 2 | 12.5 | 12.5 | 11 | 14 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | Shiv krupa Infra | 1 | 1 | 45 | 45 | 45 | 45 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | Shivkrupa | 1 | 1 | 14 | 14 | 14 | 14 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | Tower Foundation | 3 | 3 | 14 | 12 | 10 | 20 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | Unassigned | 5 | 5 | 8 | 8 | 6 | 12 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | Unnati Construction | 2 | 2 | 31.5 | 31.5 | 22 | 41 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-01 | Velu | 2 | 2 | 16 | 16 | 8 | 24 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-02 | BLG | 2 | 2 | 10 | 10 | 8 | 12 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-02 | Deep Power | 2 | 2 | 32.5 | 32.5 | 32 | 33 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-02 | Dev Construction | 2 | 2 | 8 | 8 | 4 | 12 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-02 | Himanshi | 3 | 3 | 15.33 | 13 | 13 | 20 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-02 | Jyoti | 1 | 1 | 47 | 47 | 47 | 47 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-02 | Jyoti 2 | 1 | 1 | 63 | 63 | 63 | 63 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-02 | Khodiyar | 1 | 1 | 9 | 9 | 9 | 9 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-02 | Krishna | 2 | 2 | 9.5 | 9.5 | 7 | 12 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-02 | Krishna Construction | 1 | 1 | 13 | 13 | 13 | 13 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-02 | Saiguru | 3 | 3 | 10.67 | 9 | 8 | 15 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-02 | Saiguru 1 | 1 | 1 | 45 | 45 | 45 | 45 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-02 | Tower Foundation | 2 | 2 | 8.5 | 8.5 | 5 | 12 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-02 | Unassigned | 5 | 5 | 34 | 15 | 10 | 72 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-02 | Unnati | 2 | 2 | 15.5 | 15.5 | 13 | 18 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-02 | Unnati Construction | 1 | 1 | 532 | 532 | 532 | 532 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-02 | Velu (213/0) | 1 | 1 | 19 | 19 | 19 | 19 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-03 | BLG | 2 | 2 | 6.5 | 6.5 | 6 | 7 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-03 | Dev Construction | 1 | 1 | 25 | 25 | 25 | 25 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-03 | Himanshi | 1 | 1 | 21 | 21 | 21 | 21 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-03 | Jyoti | 1 | 1 | 9 | 9 | 9 | 9 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-03 | Krishna | 4 | 4 | 13 | 7 | 5 | 33 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-03 | Sai guru Construction | 1 | 1 | 16 | 16 | 16 | 16 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-03 | Saiguru | 3 | 3 | 12.33 | 14 | 7 | 16 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-03 | Saiguru-2 | 1 | 1 | 9 | 9 | 9 | 9 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-03 | Shivkrupa | 2 | 2 | 12 | 12 | 9 | 15 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-03 | Tower Foundation | 3 | 3 | 21 | 16 | 9 | 38 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-03 | Unnati | 3 | 3 | 11.33 | 12 | 10 | 12 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-03 | Unnati Construction | 1 | 1 | 33 | 33 | 33 | 33 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-03 | khodiyar | 1 | 1 | 15 | 15 | 15 | 15 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-04 | Jyoti | 1 | 1 | 35 | 35 | 35 | 35 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-04 | Jyoti 1 | 2 | 2 | 7 | 7 | 6 | 8 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-04 | Jyoti 2 | 2 | 2 | 13.5 | 13.5 | 13 | 14 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-04 | Jyoti Const | 1 | 1 | 24 | 24 | 24 | 24 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-04 | Khodiyar Krupa | 1 | 1 | 19 | 19 | 19 | 19 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-04 | Khodiyarkripa | 2 | 2 | 14.5 | 14.5 | 8 | 21 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-04 | Khodiyarkrupa | 1 | 1 | 101 | 101 | 101 | 101 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-04 | Sai guru Construction | 1 | 1 | 24 | 24 | 24 | 24 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-04 | Tower Founadation | 1 | 1 | 13 | 13 | 13 | 13 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-04 | Tower Foundation | 2 | 2 | 19 | 19 | 18 | 20 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-05 | Arya Implex | 1 | 1 | 38 | 38 | 38 | 38 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-05 | Himanshi | 2 | 2 | 25 | 25 | 22 | 28 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-05 | Himanshi Agency | 1 | 1 | 18 | 18 | 18 | 18 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-05 | Jyoti Contruction | 1 | 1 | 11 | 11 | 11 | 11 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-05 | KND | 1 | 1 | 109 | 109 | 109 | 109 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-05 | Khodiyar | 1 | 1 | 12 | 12 | 12 | 12 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-05 | Sai guru Construction | 1 | 1 | 13 | 13 | 13 | 13 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-05 | Saiguru | 1 | 1 | 35 | 35 | 35 | 35 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-05 | Shivkrupa | 2 | 2 | 15.5 | 15.5 | 15 | 16 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-05 | Tower Founadation | 1 | 1 | 11 | 11 | 11 | 11 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-05 | Tower Foundation | 1 | 1 | 8 | 8 | 8 | 8 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-05 | jyoti const 2 | 2 | 2 | 64 | 64 | 36 | 92 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-06 | Harshvi | 1 | 1 | 399 | 399 | 399 | 399 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-06 | Himanshi | 1 | 1 | 43 | 43 | 43 | 43 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-06 | Jyoti 1 | 1 | 1 | 10 | 10 | 10 | 10 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-06 | Jyoti 2 | 2 | 2 | 20.5 | 20.5 | 16 | 25 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-06 | Jyoti 3 | 2 | 2 | 11.5 | 11.5 | 7 | 16 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-06 | Khodiyar | 1 | 1 | 137 | 137 | 137 | 137 | 0 | 0
Mr. Arun Felbin | TA 414 | 2026-06 | Shivkrupa | 1 | 1 | 11 | 11 | 11 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-05 | Sumit Constrcution | 6 | 6 | 8 | 6.5 | 6 | 13 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-06 | Anshika con. | 2 | 2 | 10 | 10 | 9 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-06 | Dharamdas Contractor | 5 | 5 | 6.6 | 6 | 5 | 8 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-06 | Khalil Const. | 3 | 3 | 8 | 7 | 7 | 10 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-06 | Sumit Constrcution | 7 | 7 | 5.71 | 5 | 4 | 8 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-07 | Anshika con. | 4 | 4 | 10.5 | 11 | 8 | 12 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-07 | Jay Sri Ram | 2 | 2 | 9.5 | 9.5 | 8 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-07 | K R Associates | 1 | 1 | 12 | 12 | 12 | 12 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-07 | SSR engineering | 2 | 2 | 7.5 | 7.5 | 7 | 8 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-07 | VH Rajpoot cont. | 1 | 1 | 10 | 10 | 10 | 10 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-08 | Anshika con. | 2 | 1 | 7 | 7 | 7 | 7 | 0 | 1
Mr. Arun Felbin | TA 416 | 2024-08 | J M Enterprise | 1 | 1 | 9 | 9 | 9 | 9 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-08 | K R Associates | 2 | 2 | 10.5 | 10.5 | 8 | 13 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-08 | SSR engineering | 3 | 3 | 10.67 | 12 | 7 | 13 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-08 | VED ENTTERPRISE | 1 | 1 | 16 | 16 | 16 | 16 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-08 | VH Rajpoot cont. | 4 | 4 | 6.75 | 6.5 | 5 | 9 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-09 | A V I ENTERPRISE | 2 | 2 | 12 | 12 | 8 | 16 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-09 | Dewi Construction(Girendra) | 2 | 2 | 15 | 15 | 14 | 16 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-09 | Dharamdas Contractor | 3 | 3 | 10.33 | 11 | 8 | 12 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-09 | Garg Construction | 3 | 3 | 12.33 | 13 | 9 | 15 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-09 | J M Enterprise | 2 | 2 | 14.5 | 14.5 | 7 | 22 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-09 | K R Associates | 1 | 1 | 24 | 24 | 24 | 24 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-09 | Laxmi Const. | 1 | 1 | 6 | 6 | 6 | 6 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-09 | MALLIK CON | 1 | 1 | 38 | 38 | 38 | 38 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-09 | SAIFI CON. | 3 | 3 | 17 | 17 | 6 | 28 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-09 | SSR engineering | 3 | 3 | 10.33 | 8 | 6 | 17 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-09 | Shree Krishna | 1 | 1 | 30 | 30 | 30 | 30 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-09 | VED ENTTERPRISE | 2 | 2 | 8.5 | 8.5 | 8 | 9 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-09 | VH Rajpoot cont. | 4 | 4 | 6 | 5 | 4 | 10 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-09 | Vinayak Enterprise | 2 | 2 | 18.5 | 18.5 | 16 | 21 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-09 | Vishal construction | 1 | 1 | 19 | 19 | 19 | 19 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-10 | A V I ENTERPRISE | 4 | 4 | 6.25 | 6 | 3 | 10 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-10 | Aneshwar Traders | 6 | 6 | 5.83 | 6 | 3 | 8 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-10 | Dewi Construction(Girendra) | 5 | 5 | 6 | 6 | 5 | 7 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-10 | Dharamdas Contractor | 2 | 2 | 7.5 | 7.5 | 5 | 10 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-10 | Garg Construction | 3 | 3 | 7.33 | 7 | 5 | 10 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-10 | Horil Mahto | 4 | 4 | 11.75 | 11.5 | 8 | 16 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-10 | J M Enterprise | 1 | 1 | 8 | 8 | 8 | 8 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-10 | K R Associates | 1 | 1 | 10 | 10 | 10 | 10 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-10 | Laxmi Const. | 5 | 5 | 4.8 | 5 | 3 | 7 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-10 | M A Construction | 4 | 4 | 5.25 | 5 | 4 | 7 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-10 | Maa Durga | 3 | 3 | 9.33 | 9 | 7 | 12 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-10 | SAIFI CON. | 3 | 3 | 8 | 8 | 5 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-10 | SSR engineering | 4 | 4 | 5.75 | 5.5 | 4 | 8 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-10 | VED ENTTERPRISE | 4 | 4 | 6.5 | 6 | 4 | 10 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-10 | VH Rajpoot cont. | 5 | 5 | 5.6 | 5 | 4 | 8 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-10 | Vinayak Enterprise | 2 | 2 | 20 | 20 | 8 | 32 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-10 | Vishal construction | 1 | 1 | 9 | 9 | 9 | 9 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-10 | Vivan Enterprise | 2 | 2 | 5.5 | 5.5 | 4 | 7 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-11 | A V I ENTERPRISE | 3 | 3 | 6.67 | 6 | 5 | 9 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-11 | Amar Singh | 1 | 1 | 20 | 20 | 20 | 20 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-11 | Aneshwar Traders | 4 | 4 | 8.75 | 8.5 | 8 | 10 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-11 | Dewi Construction(Girendra) | 5 | 5 | 6.2 | 6 | 4 | 8 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-11 | Dharamdas Contractor | 2 | 2 | 8.5 | 8.5 | 8 | 9 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-11 | Garg Construction | 4 | 4 | 7.5 | 8 | 3 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-11 | Horil Mahto | 2 | 2 | 15 | 15 | 14 | 16 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-11 | J M Enterprise | 2 | 2 | 8 | 8 | 5 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-11 | K R Associates | 3 | 3 | 9 | 9 | 7 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-11 | Laxmi Const. | 5 | 5 | 7.6 | 8 | 5 | 9 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-11 | M A Construction | 4 | 4 | 7.5 | 8 | 5 | 9 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-11 | Maa Durga | 2 | 2 | 10.5 | 10.5 | 4 | 17 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-11 | Pankaj | 1 | 1 | 15 | 15 | 15 | 15 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-11 | Pinky Dewi | 1 | 1 | 12 | 12 | 12 | 12 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-11 | R K Constrcution | 2 | 2 | 8 | 8 | 8 | 8 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-11 | Reeta Bharti | 1 | 1 | 17 | 17 | 17 | 17 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-11 | SAIFI CON. | 1 | 1 | 6 | 6 | 6 | 6 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-11 | SSR engineering | 4 | 4 | 8.25 | 9 | 5 | 10 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-11 | VH Rajpoot cont. | 6 | 6 | 7.33 | 8 | 4 | 9 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-11 | Vinayak Enterprise | 2 | 2 | 8 | 8 | 6 | 10 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-11 | Vivan Enterprise | 2 | 2 | 9.5 | 9.5 | 9 | 10 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-12 | A V I ENTERPRISE | 3 | 3 | 9 | 9 | 7 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-12 | Amar Singh | 3 | 3 | 9.67 | 11 | 7 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-12 | Aneshwar Traders | 3 | 3 | 18 | 9 | 7 | 38 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-12 | Dewi Construction(Girendra) | 5 | 5 | 6.8 | 7 | 6 | 8 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-12 | Dharamdas Contractor | 4 | 4 | 11 | 11 | 9 | 13 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-12 | Garg Construction | 2 | 2 | 7.5 | 7.5 | 7 | 8 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-12 | Horil Mahto | 3 | 3 | 11.33 | 12 | 8 | 14 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-12 | J M Enterprise | 3 | 3 | 7.67 | 8 | 7 | 8 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-12 | Laxmi Const. | 4 | 4 | 7 | 6 | 5 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-12 | M A Construction | 3 | 3 | 8 | 7 | 6 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-12 | Maa Durga | 2 | 2 | 11.5 | 11.5 | 11 | 12 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-12 | Pankaj | 5 | 5 | 7.4 | 7 | 6 | 9 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-12 | Pinky Dewi | 5 | 5 | 6 | 6 | 4 | 8 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-12 | R K Constrcution | 4 | 4 | 8 | 8 | 7 | 9 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-12 | Reeta Bharti | 4 | 4 | 7.75 | 8 | 6 | 9 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-12 | SAIFI CON. | 2 | 2 | 9.5 | 9.5 | 9 | 10 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-12 | SSR engineering | 1 | 1 | 7 | 7 | 7 | 7 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-12 | VH Rajpoot cont. | 4 | 4 | 9.25 | 8 | 6 | 15 | 0 | 0
Mr. Arun Felbin | TA 416 | 2024-12 | Vinayak Enterprise | 2 | 2 | 10 | 10 | 9 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-01 | A K Rajpoot | 4 | 4 | 17 | 10.5 | 7 | 40 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-01 | A V I ENTERPRISE | 1 | 1 | 20 | 20 | 20 | 20 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-01 | ASC heights | 4 | 4 | 8.5 | 8.5 | 6 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-01 | Amar Singh | 4 | 4 | 8.25 | 8.5 | 6 | 10 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-01 | Amit Choudhry | 1 | 0 |  |  |  |  | 0 | 1
Mr. Arun Felbin | TA 416 | 2025-01 | Aneshwar Traders | 2 | 2 | 13 | 13 | 9 | 17 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-01 | Dewi Construction(Girendra) | 4 | 4 | 7.75 | 7.5 | 6 | 10 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-01 | Dharamdas Contractor | 1 | 1 | 19 | 19 | 19 | 19 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-01 | Garg Construction | 3 | 3 | 23.33 | 11 | 8 | 51 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-01 | Horil Mahto | 2 | 2 | 12 | 12 | 11 | 13 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-01 | J M Enterprise | 1 | 1 | 12 | 12 | 12 | 12 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-01 | Laxmi Const. | 3 | 3 | 8.33 | 8 | 8 | 9 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-01 | M A Construction | 3 | 3 | 20.67 | 13 | 9 | 40 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-01 | Maa Durga | 3 | 3 | 20 | 10 | 9 | 41 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-01 | Pankaj | 4 | 4 | 8.25 | 8 | 7 | 10 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-01 | Pankaj Kumar | 1 | 0 |  |  |  |  | 0 | 1
Mr. Arun Felbin | TA 416 | 2025-01 | Pinky Dewi | 5 | 4 | 7.75 | 8 | 5 | 10 | 0 | 1
Mr. Arun Felbin | TA 416 | 2025-01 | Punam kumari-1 | 1 | 0 |  |  |  |  | 0 | 1
Mr. Arun Felbin | TA 416 | 2025-01 | Punam kumari-3 | 1 | 0 |  |  |  |  | 0 | 1
Mr. Arun Felbin | TA 416 | 2025-01 | Reeta Bharti | 3 | 3 | 11 | 12 | 9 | 12 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-01 | Rudra Construction | 1 | 1 | 11 | 11 | 11 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-01 | SAIFI CON. | 2 | 2 | 12 | 12 | 11 | 13 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-01 | SSR engineering | 3 | 3 | 10.67 | 9 | 5 | 18 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-01 | VH Rajpoot cont. | 2 | 2 | 16 | 16 | 16 | 16 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-01 | Vinayak Enterprise | 2 | 2 | 9 | 9 | 9 | 9 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-02 | A K Rajpoot | 2 | 2 | 8 | 8 | 7 | 9 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-02 | A V I ENTERPRISE | 2 | 2 | 15.5 | 15.5 | 13 | 18 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-02 | ASC heights | 4 | 4 | 9.25 | 9.5 | 8 | 10 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-02 | Amar Singh | 4 | 4 | 7 | 7 | 6 | 8 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-02 | Aneshwar Traders | 2 | 2 | 12 | 12 | 10 | 14 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-02 | Dewi Construction(Girendra) | 4 | 4 | 6.75 | 7 | 5 | 8 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-02 | Dharamdas Contractor | 2 | 2 | 15 | 15 | 14 | 16 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-02 | Garg Construction | 2 | 2 | 11 | 11 | 9 | 13 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-02 | Horil Mahto | 3 | 3 | 10 | 9 | 7 | 14 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-02 | Laxmi Const. | 3 | 3 | 10.33 | 9 | 9 | 13 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-02 | M A Construction | 2 | 2 | 12 | 12 | 10 | 14 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-02 | Maa Durga | 2 | 2 | 8.5 | 8.5 | 6 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-02 | Pankaj | 3 | 3 | 9.33 | 9 | 7 | 12 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-02 | Pinky Dewi | 5 | 5 | 7 | 7 | 6 | 8 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-02 | R K Constrcution | 2 | 2 | 10.5 | 10.5 | 7 | 14 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-02 | Reeta Bharti | 4 | 4 | 7.75 | 7.5 | 6 | 10 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-02 | Rudra Construction | 2 | 2 | 10 | 10 | 9 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-02 | SAIFI CON. | 2 | 2 | 11.5 | 11.5 | 9 | 14 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-02 | SSR engineering | 2 | 2 | 12 | 12 | 10 | 14 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-02 | VH Rajpoot cont. | 3 | 3 | 8.67 | 11 | 3 | 12 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-02 | Vinayak Enterprise | 2 | 2 | 10.5 | 10.5 | 10 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-03 | A K Rajpoot | 4 | 4 | 6 | 6 | 6 | 6 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-03 | ASC heights | 4 | 4 | 7.75 | 7.5 | 7 | 9 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-03 | Amar Singh | 2 | 2 | 7.5 | 7.5 | 5 | 10 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-03 | Ananya Traders-1 | 1 | 1 | 8 | 8 | 8 | 8 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-03 | Aneshwar Traders | 1 | 1 | 20 | 20 | 20 | 20 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-03 | Dewi Construction(Girendra) | 6 | 6 | 5.67 | 5 | 4 | 8 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-03 | Garg Construction | 1 | 1 | 10 | 10 | 10 | 10 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-03 | Horil Mahto | 3 | 3 | 9.67 | 9 | 9 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-03 | Laxmi Const. | 2 | 2 | 8.5 | 8.5 | 7 | 10 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-03 | M A Construction | 2 | 2 | 14 | 14 | 8 | 20 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-03 | M K infra | 1 | 1 | 11 | 11 | 11 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-03 | Maa Durga | 2 | 2 | 6.5 | 6.5 | 6 | 7 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-03 | Pankaj | 3 | 3 | 9.67 | 10 | 8 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-03 | Pinky Dewi | 5 | 5 | 7 | 8 | 5 | 9 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-03 | R K Constrcution | 1 | 1 | 11 | 11 | 11 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-03 | Reeta Bharti | 4 | 4 | 8 | 7 | 5 | 13 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-03 | Rudra Construction | 1 | 1 | 11 | 11 | 11 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-03 | SAIFI CON. | 1 | 1 | 7 | 7 | 7 | 7 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-03 | VH Rajpoot cont. | 1 | 1 | 8 | 8 | 8 | 8 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-03 | Vinayak Enterprise | 1 | 1 | 22 | 22 | 22 | 22 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-04 | A K Rajpoot | 2 | 2 | 5.5 | 5.5 | 4 | 7 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-04 | A V I ENTERPRISE | 1 | 1 | 8 | 8 | 8 | 8 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-04 | ASC heights | 3 | 3 | 9.33 | 10 | 7 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-04 | Amar Singh | 3 | 3 | 10 | 11 | 6 | 13 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-04 | Anand Construction | 2 | 2 | 13.5 | 13.5 | 12 | 15 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-04 | Ananya Traders-1 | 3 | 3 | 9 | 8 | 7 | 12 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-04 | Ananya Traders-2 | 3 | 3 | 8.33 | 9 | 4 | 12 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-04 | Aneshwar Traders | 1 | 1 | 14 | 14 | 14 | 14 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-04 | Dewi Construction(Girendra) | 3 | 3 | 8.33 | 8 | 6 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-04 | Dharamdas Contractor | 3 | 3 | 17.33 | 17 | 17 | 18 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-04 | Gagan enterprise.1 | 5 | 5 | 6.2 | 7 | 4 | 9 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-04 | Gagan enterprise.2 | 3 | 3 | 9.33 | 11 | 5 | 12 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-04 | Horil Mahto | 1 | 1 | 12 | 12 | 12 | 12 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-04 | Laxmi Const. | 1 | 1 | 18 | 18 | 18 | 18 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-04 | M K infra | 2 | 2 | 11 | 11 | 11 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-04 | Maa Durga | 1 | 1 | 9 | 9 | 9 | 9 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-04 | Pinky Dewi | 4 | 4 | 8.5 | 8.5 | 6 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-04 | R K Constrcution | 1 | 1 | 9 | 9 | 9 | 9 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-04 | Reeta Bharti | 2 | 2 | 10.5 | 10.5 | 9 | 12 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-04 | Rudra Construction | 1 | 1 | 9 | 9 | 9 | 9 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-04 | SAIFI CON. | 1 | 1 | 14 | 14 | 14 | 14 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-04 | VH Rajpoot cont. | 3 | 3 | 5 | 5 | 4 | 6 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-05 | A V I ENTERPRISE | 1 | 1 | 13 | 13 | 13 | 13 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-05 | ASC heights | 3 | 3 | 7 | 7 | 7 | 7 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-05 | Amar Singh | 5 | 5 | 6.4 | 7 | 5 | 7 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-05 | Amit Const | 1 | 1 | 11 | 11 | 11 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-05 | Ananya Traders-1 | 4 | 4 | 6.5 | 6.5 | 5 | 8 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-05 | Ananya Traders-2 | 5 | 5 | 6 | 6 | 5 | 7 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-05 | Aneshwar Traders | 1 | 1 | 15 | 15 | 15 | 15 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-05 | Dewi Construction(Girendra) | 5 | 5 | 6.4 | 6 | 5 | 8 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-05 | Gagan enterprise.1 | 5 | 5 | 6.4 | 6 | 4 | 10 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-05 | Gagan enterprise.2 | 2 | 2 | 9.5 | 9.5 | 7 | 12 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-05 | Laxmi Const. | 1 | 1 | 17 | 17 | 17 | 17 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-05 | Pinky Dewi | 3 | 3 | 8 | 8 | 6 | 10 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-05 | Reeta Bharti | 3 | 3 | 8.67 | 8 | 8 | 10 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-05 | Rudra Construction | 2 | 2 | 13 | 13 | 8 | 18 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-05 | SAIFI CON. | 1 | 1 | 14 | 14 | 14 | 14 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-05 | VH Rajpoot cont. | 2 | 2 | 10 | 10 | 7 | 13 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-06 | A V I ENTERPRISE | 1 | 1 | 15 | 15 | 15 | 15 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-06 | ASC heights | 1 | 1 | 28 | 28 | 28 | 28 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-06 | Amar Singh | 2 | 2 | 8 | 8 | 7 | 9 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-06 | Amit Const | 2 | 2 | 9.5 | 9.5 | 9 | 10 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-06 | Ananya Traders-1 | 2 | 2 | 16.5 | 16.5 | 6 | 27 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-06 | Ananya Traders-2 | 3 | 3 | 11 | 12 | 6 | 15 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-06 | Devine | 1 | 1 | 13 | 13 | 13 | 13 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-06 | Dewi Construction(Girendra) | 1 | 1 | 6 | 6 | 6 | 6 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-06 | Gagan enterprise.1 | 1 | 1 | 30 | 30 | 30 | 30 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-06 | M K infra | 2 | 2 | 29 | 29 | 18 | 40 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-06 | Pinky Dewi | 5 | 5 | 6.4 | 6 | 4 | 9 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-06 | Reeta Bharti | 4 | 4 | 9.5 | 9.5 | 7 | 12 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-07 | ASC heights | 1 | 1 | 12 | 12 | 12 | 12 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-07 | Amar singh | 1 | 1 | 25 | 25 | 25 | 25 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-07 | Ananya Traders-1 | 1 | 1 | 14 | 14 | 14 | 14 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-07 | Pinky Dewi | 1 | 1 | 7 | 7 | 7 | 7 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-07 | Reeta Bharti | 2 | 2 | 18 | 18 | 12 | 24 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-08 | Ananya Traders-1 | 1 | 1 | 20 | 20 | 20 | 20 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-08 | Gagan enterprise.1 | 1 | 1 | 34 | 34 | 34 | 34 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-08 | Gagan enterprise.2 (Kajol) | 1 | 1 | 13 | 13 | 13 | 13 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-08 | Kongres Kumar-1 | 1 | 1 | 33 | 33 | 33 | 33 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-08 | Kongres Kumar-2 | 1 | 1 | 29 | 29 | 29 | 29 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-08 | Punam Kumari | 1 | 1 | 22 | 22 | 22 | 22 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-08 | Radha Construction | 1 | 1 | 22 | 22 | 22 | 22 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-08 | Sainik Trader | 1 | 1 | 27 | 27 | 27 | 27 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-09 | Amit Choudhury | 2 | 2 | 20 | 20 | 10 | 30 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-09 | Ananya Traders-1 | 2 | 2 | 22 | 22 | 16 | 28 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-09 | Ananya trader | 1 | 1 | 9 | 9 | 9 | 9 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-09 | Gagan enterprise.1 | 1 | 1 | 22 | 22 | 22 | 22 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-09 | Gouri Shankar | 2 | 2 | 16.5 | 16.5 | 11 | 22 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-09 | Kongres Kumar- | 1 | 1 | 33 | 33 | 33 | 33 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-09 | Kongres Kumar-2 | 1 | 1 | 23 | 23 | 23 | 23 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-09 | Maa Construction | 1 | 1 | 18 | 18 | 18 | 18 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-09 | Punam Kumari | 2 | 2 | 18 | 18 | 18 | 18 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-09 | Radha Construction | 1 | 1 | 19 | 19 | 19 | 19 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-09 | Reeta Bharti | 1 | 1 | 48 | 48 | 48 | 48 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-09 | Sainik Trader | 1 | 1 | 25 | 25 | 25 | 25 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-09 | Spotyfy-3 | 1 | 1 | 38 | 38 | 38 | 38 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-10 | 2025-10-18 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 416 | 2025-10 | 2025-10-24 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 416 | 2025-10 | 2025-10-26 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 416 | 2025-10 | 2025-10-31 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 416 | 2025-10 | Amit Choudhry | 1 | 1 | 14 | 14 | 14 | 14 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-10 | Ananya trader | 1 | 1 | 22 | 22 | 22 | 22 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-10 | Kongres Kumar- | 1 | 1 | 14 | 14 | 14 | 14 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-10 | Maa Construction | 1 | 1 | 26 | 26 | 26 | 26 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-10 | Mahon Mahto | 1 | 1 | 12 | 12 | 12 | 12 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-10 | Pankaj Kumar | 1 | 1 | 19 | 19 | 19 | 19 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-10 | Punam Kumari | 1 | 1 | 13 | 13 | 13 | 13 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-10 | Punam kumari-1 | 1 | 1 | 20 | 20 | 20 | 20 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-10 | Punam kumari-2 | 1 | 1 | 15 | 15 | 15 | 15 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-10 | Reeta Bharti | 1 | 1 | 21 | 21 | 21 | 21 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-10 | Sainik Trader | 1 | 1 | 19 | 19 | 19 | 19 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-10 | Spotyfy-1 | 1 | 1 | 26 | 26 | 26 | 26 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-10 | Unity India | 1 | 1 | 39 | 39 | 39 | 39 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-11 | 2025-11-03 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 416 | 2025-11 | 2025-11-06 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 416 | 2025-11 | 2025-11-13 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 416 | 2025-11 | 2025-11-18 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 416 | 2025-11 | 2025-11-25 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 416 | 2025-11 | 2025-12-04 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 416 | 2025-11 | Aloriva Global | 2 | 2 | 15 | 15 | 14 | 16 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-11 | Amit Choudhry | 2 | 2 | 26 | 26 | 22 | 30 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-11 | Mahon Mahto | 1 | 1 | 15 | 15 | 15 | 15 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-11 | Mahon mahto | 1 | 1 | 51 | 51 | 51 | 51 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-11 | Niranjan Singh | 1 | 1 | 25 | 25 | 25 | 25 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-11 | Pankaj Kumar | 1 | 1 | 16 | 16 | 16 | 16 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-11 | Pinky Dewi | 1 | 1 | 53 | 53 | 53 | 53 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-11 | Punam kumari-1 | 1 | 1 | 25 | 25 | 25 | 25 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-11 | Punam kumari-2 | 2 | 2 | 12.5 | 12.5 | 9 | 16 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-12 | 2025-12-10 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 416 | 2025-12 | Aloriva Global | 1 | 1 | 19 | 19 | 19 | 19 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-12 | Pankaj Kumar | 2 | 2 | 20 | 20 | 15 | 25 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-12 | Pinky Dewi | 2 | 2 | 17 | 17 | 15 | 19 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-12 | Punam kumari-1 | 1 | 1 | 11 | 11 | 11 | 11 | 0 | 0
Mr. Arun Felbin | TA 416 | 2025-12 | Punam kumari-3 | 1 | 1 | 28 | 28 | 28 | 28 | 0 | 0
Mr. Arun Felbin | TA 416 | 2026-01 | Mahon mahto | 1 | 1 | 51 | 51 | 51 | 51 | 0 | 0
Mr. Arun Felbin | TA 416 | 2026-01 | Punam kumari-2 | 1 | 1 | 10 | 10 | 10 | 10 | 0 | 0
Mr. Arun Felbin | TA 416 | 2026-02 | 2026-02-09 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 416 | 2026-02 | 2026-02-11 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 416 | 2026-02 | 2026-02-14 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 416 | 2026-02 | 2026-02-17 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 416 | 2026-02 | 2026-02-19 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 416 | 2026-02 | 2026-02-20 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 416 | 2026-02 | 2026-02-22 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 416 | 2026-02 | 2026-02-26 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 416 | 2026-02 | 2026-03-02 00:00:00 | 2 | 0 |  |  |  |  | 2 | 0
Mr. Arun Felbin | TA 416 | 2026-02 | Mahon Mahto | 1 | 1 | 20 | 20 | 20 | 20 | 0 | 0
Mr. Arun Felbin | TA 416 | 2026-03 | Mahon Mahto | 1 | 1 | 29 | 29 | 29 | 29 | 0 | 0
Mr. Arun Felbin | TA 416 | 2026-03 | Punam Kumari-2 | 1 | 1 | 43 | 43 | 43 | 43 | 0 | 0
Mr. Arun Felbin | TA 416 | 2026-05 | 2026-05-05 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 416 | 2026-05 | 2026-05-08 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 416 | 2026-05 | 2026-05-10 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 418 | 2024-01 | Gang-01 (Sanjay) | 1 | 0 |  |  |  |  | 0 | 1
Mr. Arun Felbin | TA 418 | 2024-01 | Gang-02 (Sanjay) | 1 | 0 |  |  |  |  | 0 | 1
Mr. Arun Felbin | TA 418 | 2024-06 | GANG - 1 | 2 | 2 | 17 | 17 | 14 | 20 | 0 | 0
Mr. Arun Felbin | TA 418 | 2024-07 | GANG - 1 | 1 | 1 | 13 | 13 | 13 | 13 | 0 | 0
Mr. Arun Felbin | TA 418 | 2024-07 | GANG-1 | 1 | 1 | 18 | 18 | 18 | 18 | 0 | 0
Mr. Arun Felbin | TA 418 | 2024-07 | GANG-2 | 3 | 3 | 14.33 | 16 | 10 | 17 | 0 | 0
Mr. Arun Felbin | TA 418 | 2024-07 | Team - 1 (Sanjay) | 1 | 1 | 22 | 22 | 22 | 22 | 0 | 0
Mr. Arun Felbin | TA 418 | 2024-07 | Team - 2 (SM Constr.) | 1 | 1 | 18 | 18 | 18 | 18 | 0 | 0
Mr. Arun Felbin | TA 418 | 2024-07 | Team - 3 (ATK-01) | 1 | 1 | 17 | 17 | 17 | 17 | 0 | 0
Mr. Arun Felbin | TA 418 | 2024-08 | Team - 1 (Sanjay) | 2 | 2 | 11.5 | 11.5 | 10 | 13 | 0 | 0
Mr. Arun Felbin | TA 418 | 2024-08 | Team - 2 (SM Constr.) | 3 | 3 | 18 | 15 | 15 | 24 | 0 | 0
Mr. Arun Felbin | TA 418 | 2024-08 | Team - 3 (ATK-01) | 4 | 4 | 19.75 | 19.5 | 15 | 25 | 0 | 0
Mr. Arun Felbin | TA 418 | 2024-09 | (ATK-02) | 5 | 5 | 9 | 8 | 7 | 12 | 0 | 0
Mr. Arun Felbin | TA 418 | 2024-09 | Team - 2 (SM Constr.) | 1 | 1 | 27 | 27 | 27 | 27 | 0 | 0
Mr. Arun Felbin | TA 418 | 2024-09 | Team - 3 (ATK-01) | 2 | 2 | 9.5 | 9.5 | 9 | 10 | 0 | 0
Mr. Arun Felbin | TA 418 | 2024-10 | (ATK-02) | 3 | 3 | 13.33 | 12 | 10 | 18 | 0 | 0
Mr. Arun Felbin | TA 418 | 2024-10 | Bindu | 1 | 1 | 11 | 11 | 11 | 11 | 0 | 0
Mr. Arun Felbin | TA 418 | 2024-10 | Gang-01 (Sanjay) | 1 | 1 | 19 | 19 | 19 | 19 | 0 | 0
Mr. Arun Felbin | TA 418 | 2024-11 | Adarsh Gang | 1 | 1 | 24 | 24 | 24 | 24 | 0 | 0
Mr. Arun Felbin | TA 418 | 2024-11 | Bindu | 1 | 1 | 20 | 20 | 20 | 20 | 0 | 0
Mr. Arun Felbin | TA 418 | 2024-11 | GANG - 4 | 1 | 1 | 44 | 44 | 44 | 44 | 0 | 0
Mr. Arun Felbin | TA 418 | 2024-11 | Gang-01 (Sanjay) | 4 | 4 | 7.5 | 7.5 | 6 | 9 | 0 | 0
Mr. Arun Felbin | TA 418 | 2024-11 | LALA GANG | 2 | 2 | 31.5 | 31.5 | 9 | 54 | 0 | 0
Mr. Arun Felbin | TA 418 | 2024-12 | Adarsh Gang | 2 | 2 | 28.5 | 28.5 | 17 | 40 | 0 | 0
Mr. Arun Felbin | TA 418 | 2024-12 | Bindu | 3 | 3 | 28.67 | 25 | 17 | 44 | 0 | 0
Mr. Arun Felbin | TA 418 | 2024-12 | Gang-01 (Sanjay) | 5 | 5 | 6.6 | 6 | 5 | 9 | 0 | 0
Mr. Arun Felbin | TA 418 | 2024-12 | Gang-02 (Sanjay) | 3 | 3 | 9 | 9 | 7 | 11 | 0 | 0
Mr. Arun Felbin | TA 418 | 2024-12 | KAVAL CHAND | 1 | 1 | 22 | 22 | 22 | 22 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-01 | ADARSH | 1 | 1 | 126 | 126 | 126 | 126 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-01 | ANURADHA | 2 | 2 | 37.5 | 37.5 | 32 | 43 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-01 | Adarsh Gang | 1 | 1 | 11 | 11 | 11 | 11 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-01 | Gang-01 (Sanjay) | 4 | 4 | 98 | 7.5 | 6 | 371 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-01 | Gang-02 (Sanjay) | 2 | 2 | 190.5 | 190.5 | 8 | 373 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-01 | KEC GANG -02 | 2 | 2 | 19 | 19 | 15 | 23 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-02 | ANURADHA | 2 | 2 | 20 | 20 | 18 | 22 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-02 | Gang-01 (Sanjay) | 5 | 5 | 6.6 | 6 | 6 | 9 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-02 | Gang-02 (Sanjay) | 2 | 2 | 14 | 14 | 9 | 19 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-02 | Haque Constr. | 3 | 3 | 41.33 | 23 | 13 | 88 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-02 | KEC GANG -02 | 2 | 2 | 13.5 | 13.5 | 10 | 17 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-03 | ANURADHA | 3 | 3 | 19 | 16 | 12 | 29 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-03 | Gang-01 (Sanjay) | 2 | 2 | 6 | 6 | 6 | 6 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-03 | Gang-02 (Sanjay) | 4 | 4 | 7.25 | 6 | 6 | 11 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-03 | Haque Constr. | 4 | 4 | 10 | 10.5 | 7 | 12 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-03 | KEC GANG -02 | 1 | 1 | 15 | 15 | 15 | 15 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-03 | KEVAL CHAND | 1 | 1 | 80 | 80 | 80 | 80 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-04 | Gang-01 (Sanjay) | 1 | 1 | 11 | 11 | 11 | 11 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-04 | Gang-01(Sanjay) | 1 | 1 | 8 | 8 | 8 | 8 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-04 | Gang-02 (Sanjay) | 4 | 4 | 5.5 | 5.5 | 4 | 7 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-04 | Gang-02(Sanjay) | 1 | 1 | 9 | 9 | 9 | 9 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-04 | Haque Constr. | 4 | 4 | 12 | 12 | 8 | 16 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-04 | KEC GANG -04 | 1 | 1 | 26 | 26 | 26 | 26 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-05 | Gang-01(Sanjay) | 3 | 3 | 8.33 | 9 | 7 | 9 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-05 | Gang-02(Sanjay) | 4 | 4 | 9.75 | 8.5 | 6 | 16 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-05 | Haque Constr. | 4 | 4 | 15.25 | 13 | 11 | 24 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-05 | KEC GANG -04 | 4 | 4 | 35 | 34 | 31 | 41 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-05 | KPK | 2 | 2 | 45.5 | 45.5 | 17 | 74 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-06 | Gang-01(Sanjay) | 2 | 2 | 5.5 | 5.5 | 5 | 6 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-06 | Gang-02(Sanjay) | 4 | 4 | 6.75 | 6 | 4 | 11 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-06 | Haque Constr. | 3 | 2 | 17 | 17 | 15 | 19 | 1 | 0
Mr. Arun Felbin | TA 418 | 2025-06 | KEC GANG -04 | 3 | 3 | 12.33 | 10 | 8 | 19 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-06 | KEC GANG -05 | 4 | 4 | 8 | 7.5 | 7 | 10 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-06 | KEC GANG -06 | 3 | 3 | 9 | 6 | 5 | 16 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-06 | KPK | 3 | 3 | 17 | 15 | 12 | 24 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-07 | Gang-01(Sanjay) | 1 | 1 | 13 | 13 | 13 | 13 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-07 | Gang-02(Sanjay) | 1 | 1 | 19 | 19 | 19 | 19 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-07 | Haque Constr. | 4 | 3 | 8 | 9 | 4 | 11 | 1 | 0
Mr. Arun Felbin | TA 418 | 2025-07 | KEC - 01 (Barkat Ali) | 3 | 3 | 8.67 | 9 | 7 | 10 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-07 | KEC - 02 (Barkat Ali) | 3 | 3 | 10.67 | 11 | 9 | 12 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-07 | KEC GANG - 06 | 3 | 3 | 18.67 | 23 | 7 | 26 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-07 | KEC GANG - 08 | 2 | 2 | 21 | 21 | 16 | 26 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-07 | KEC GANG - 09 | 1 | 1 | 14 | 14 | 14 | 14 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-07 | KEC GANG -06 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 418 | 2025-07 | KEC GANG -07 | 3 | 3 | 8.67 | 9 | 7 | 10 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-07 | KEC GANG -09 | 1 | 1 | 4 | 4 | 4 | 4 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-07 | KPK | 2 | 2 | 12.5 | 12.5 | 11 | 14 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-08 | Gang-02(Sanjay) / KEC - 02 (Barkat Ali) | 1 | 1 | 14 | 14 | 14 | 14 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-08 | KEC - 01 (Barkat Ali) | 3 | 3 | 20 | 11 | 9 | 40 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-08 | KEC - 02 (Barkat Ali) | 2 | 2 | 9.5 | 9.5 | 5 | 14 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-08 | KEC GANG -06 -HQ | 1 | 1 | 3 | 3 | 3 | 3 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-08 | KEC GANG -07 - HQ | 2 | 2 | 6 | 6 | 5 | 7 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-08 | SAVITHA | 2 | 2 | 16 | 16 | 14 | 18 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-08 | SUBHASH | 2 | 2 | 9 | 9 | 8 | 10 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-09 | 2025-10-13 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 418 | 2025-09 | KEC - 01 (Barkat Ali) | 1 | 1 | 11 | 11 | 11 | 11 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-09 | KEC - 02 (Barkat Ali) | 2 | 2 | 12 | 12 | 12 | 12 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-09 | M/S MDPL | 1 | 1 | 22 | 22 | 22 | 22 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-09 | M/s TOFIT | 2 | 2 | 10 | 10 | 9 | 11 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-09 | SUBHASH | 4 | 4 | 8.75 | 6.5 | 5 | 17 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-10 | 2025-12-22 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 418 | 2025-10 | KEC - 02 (Barkat Ali) | 3 | 3 | 23.67 | 10 | 8 | 53 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-10 | M/S MDPL | 1 | 1 | 19 | 19 | 19 | 19 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-10 | M/s TOFIT | 1 | 1 | 14 | 14 | 14 | 14 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-10 | SAVITHA | 1 | 1 | 29 | 29 | 29 | 29 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-10 | SUBHASH | 1 | 1 | 7 | 7 | 7 | 7 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-11 | 2025-11-10 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 418 | 2025-11 | 2025-12-05 00:00:00 | 2 | 0 |  |  |  |  | 2 | 0
Mr. Arun Felbin | TA 418 | 2025-11 | GANG - A1 | 3 | 3 | 7.67 | 9 | 4 | 10 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-11 | GANG - A2 | 2 | 2 | 12.5 | 12.5 | 12 | 13 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-11 | KEC - 02 (Barkat Ali) | 3 | 3 | 9.33 | 9 | 9 | 10 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-11 | M/S MDPL | 2 | 2 | 26.5 | 26.5 | 8 | 45 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-11 | M/s TOFIT | 3 | 3 | 12.67 | 8 | 7 | 23 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-12 | 2025-12-30 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 418 | 2025-12 | GANG - A1 | 1 | 1 | 8 | 8 | 8 | 8 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-12 | GANG - A1 (M) | 2 | 2 | 6 | 6 | 4 | 8 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-12 | GANG - A2 | 2 | 2 | 5.5 | 5.5 | 5 | 6 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-12 | KEC - 02 (Barkat Ali) | 3 | 3 | 10.33 | 10 | 10 | 11 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-12 | M/S MDPL | 4 | 4 | 7.5 | 7 | 6 | 10 | 0 | 0
Mr. Arun Felbin | TA 418 | 2025-12 | M/s TOFIT | 4 | 4 | 7 | 7.5 | 5 | 8 | 0 | 0
Mr. Arun Felbin | TA 418 | 2026-01 | 2026-01-26 00:00:00 | 2 | 0 |  |  |  |  | 2 | 0
Mr. Arun Felbin | TA 418 | 2026-01 | GANG - A2 | 1 | 1 | 7 | 7 | 7 | 7 | 0 | 0
Mr. Arun Felbin | TA 418 | 2026-01 | KEC - 02 (Barkat Ali) | 3 | 3 | 133.67 | 13 | 8 | 380 | 0 | 0
Mr. Arun Felbin | TA 418 | 2026-01 | M/S MDPL | 3 | 3 | 9 | 8 | 7 | 12 | 0 | 0
Mr. Arun Felbin | TA 418 | 2026-01 | M/s TOFIT | 4 | 4 | 8.5 | 7.5 | 5 | 14 | 0 | 0
Mr. Arun Felbin | TA 418 | 2026-02 | 2026-02-07 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 418 | 2026-02 | 2026-02-09 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 418 | 2026-02 | 2026-02-16 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 418 | 2026-02 | GANG - A2 | 1 | 1 | 7 | 7 | 7 | 7 | 0 | 0
Mr. Arun Felbin | TA 418 | 2026-02 | KEC - 02 (Barkat Ali) | 2 | 2 | 11 | 11 | 9 | 13 | 0 | 0
Mr. Arun Felbin | TA 418 | 2026-02 | KEC - 03 (Barkat Ali) | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 418 | 2026-02 | M/S MDPL | 2 | 2 | 16.5 | 16.5 | 9 | 24 | 0 | 0
Mr. Arun Felbin | TA 418 | 2026-02 | M/s TOFIT | 2 | 2 | 10 | 10 | 7 | 13 | 0 | 0
Mr. Arun Felbin | TA 418 | 2026-03 | 2026-03-06 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 418 | 2026-03 | 2026-03-09 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 418 | 2026-03 | 2026-03-14 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 418 | 2026-03 | 2026-03-22 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 418 | 2026-03 | 2026-06-05 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 418 | 2026-04 | 2026-04-16 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 418 | 2026-04 | 2026-06-15 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 418 | 2026-04 | M/S MDPL | 2 | 1 | 37 | 37 | 37 | 37 | 1 | 0
Mr. Arun Felbin | TA 418 | 2026-05 | 2026-05-02 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 418 | 2026-05 | 2026-05-24 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 418 | 2026-05 | 2026-05-26 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 418 | 2026-05 | 2026-05-30 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 418 | 2026-06 | 2026-06-05 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 418 | 2026-06 | 2026-06-15 00:00:00 | 2 | 0 |  |  |  |  | 2 | 0
Mr. Arun Felbin | TA 418 | 2026-06 | Unassigned | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 421 | 2024-05 | ATK CONSTRUCTIONS | 1 | 1 | 20 | 20 | 20 | 20 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-06 | AMMU ENG. | 3 | 3 | 17.67 | 21 | 7 | 25 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-06 | ATK CONSTRUCTIONS | 9 | 9 | 18.11 | 11 | 9 | 34 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-06 | RR CONST | 1 | 1 | 9 | 9 | 9 | 9 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-06 | TSB | 1 | 1 | 15 | 15 | 15 | 15 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-07 | AMMU ENG. | 4 | 4 | 10.25 | 10 | 8 | 13 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-07 | AMMU ENG.-2 | 3 | 3 | 10.33 | 11 | 7 | 13 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-07 | ANJU Const. | 4 | 4 | 16.75 | 16.5 | 14 | 20 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-07 | ATK CONSTRUCTIONS | 6 | 6 | 9.5 | 8.5 | 7 | 16 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-07 | Khatan | 2 | 2 | 10.5 | 10.5 | 10 | 11 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-07 | RR CONST | 2 | 2 | 17 | 17 | 17 | 17 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-07 | TSB | 1 | 1 | 36 | 36 | 36 | 36 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-08 | AMMU ENG. | 1 | 1 | 49 | 49 | 49 | 49 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-08 | ANJU Const. | 3 | 3 | 29.33 | 38 | 9 | 41 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-08 | ATK CONSTRUCTIONS | 10 | 10 | 20.7 | 24 | 6 | 34 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-08 | Ammu Eng | 5 | 5 | 16 | 13 | 10 | 24 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-08 | Company Gang | 2 | 2 | 31.5 | 31.5 | 13 | 50 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-08 | Khatan | 6 | 6 | 6.5 | 7 | 3 | 8 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-09 | AMMU ENG. | 1 | 1 | 86 | 86 | 86 | 86 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-09 | ANJU Const. | 3 | 3 | 20.67 | 24 | 8 | 30 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-09 | ATK CONSTRUCTIONS | 4 | 4 | 11 | 7.5 | 5 | 24 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-09 | Ashok kumar | 1 | 1 | 18 | 18 | 18 | 18 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-09 | Company Gang | 2 | 2 | 14.5 | 14.5 | 10 | 19 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-09 | Khatan | 5 | 5 | 8 | 6 | 5 | 15 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-09 | Maa Const. | 1 | 1 | 17 | 17 | 17 | 17 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-09 | s.K.Janarul | 1 | 1 | 17 | 17 | 17 | 17 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-09 | s.K.Janarul Sheikh | 1 | 1 | 13 | 13 | 13 | 13 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-10 | ANJU Const. | 2 | 2 | 38.5 | 38.5 | 32 | 45 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-10 | ATK CONSTRUCTIONS | 2 | 2 | 21 | 21 | 8 | 34 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-10 | ATK Constructions | 1 | 1 | 5 | 5 | 5 | 5 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-10 | Ammu Eng | 5 | 5 | 11.6 | 11 | 8 | 19 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-10 | Ashok | 4 | 4 | 18.75 | 19.5 | 10 | 26 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-10 | Company Gang + ATK | 1 | 1 | 35 | 35 | 35 | 35 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-10 | Khatan | 4 | 4 | 6.5 | 5.5 | 5 | 10 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-10 | Khatun | 1 | 1 | 6 | 6 | 6 | 6 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-10 | Maa Const. | 2 | 2 | 15.5 | 15.5 | 12 | 19 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-10 | Manirul (Islam)-Khatun | 1 | 1 | 14 | 14 | 14 | 14 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-10 | Praveen | 1 | 1 | 26 | 26 | 26 | 26 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-10 | Subash | 1 | 1 | 11 | 11 | 11 | 11 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-10 | s.K.Janarul Sheikh | 2 | 2 | 9 | 9 | 8 | 10 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-11 | Amit Kumar | 4 | 4 | 11.5 | 12 | 8 | 14 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-11 | Ammu Eng | 3 | 3 | 24.67 | 26 | 8 | 40 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-11 | Ashok | 3 | 3 | 12.33 | 11 | 10 | 16 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-11 | Ashok Kumar | 1 | 1 | 7 | 7 | 7 | 7 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-11 | Ashok kumar | 3 | 3 | 24.67 | 22 | 15 | 37 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-11 | Ashok-2 | 3 | 3 | 11.33 | 11 | 11 | 12 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-11 | Ashokkumar | 1 | 1 | 8 | 8 | 8 | 8 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-11 | Balraj | 3 | 3 | 13.67 | 7 | 3 | 31 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-11 | Khatun | 4 | 4 | 6.25 | 6 | 6 | 7 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-11 | Maa Const. | 4 | 4 | 8 | 8 | 7 | 9 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-11 | Praveen | 1 | 1 | 17 | 17 | 17 | 17 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-11 | Subash | 5 | 5 | 8.2 | 6 | 6 | 17 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-11 | Visionary Co | 1 | 1 | 40 | 40 | 40 | 40 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-11 | khatun | 2 | 2 | 6 | 6 | 6 | 6 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-11 | venkateshwarlu | 2 | 2 | 9 | 9 | 7 | 11 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-12 | ATK Constructions | 7 | 7 | 18.43 | 8 | 5 | 87 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-12 | Amit Kumar | 1 | 1 | 10 | 10 | 10 | 10 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-12 | Ammu Eng | 6 | 6 | 8.5 | 8 | 7 | 12 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-12 | Ashok kumar | 2 | 2 | 11 | 11 | 10 | 12 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-12 | Ashok-1 | 1 | 1 | 9 | 9 | 9 | 9 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-12 | Ashok-2 | 5 | 5 | 10 | 11 | 8 | 12 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-12 | BalraJ | 1 | 1 | 8 | 8 | 8 | 8 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-12 | Balraj | 2 | 2 | 8 | 8 | 6 | 10 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-12 | Khatun | 5 | 5 | 5.6 | 6 | 5 | 6 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-12 | Praveen | 2 | 2 | 20.5 | 20.5 | 17 | 24 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-12 | Subash | 8 | 8 | 4.75 | 4 | 3 | 9 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-12 | Tagore | 3 | 3 | 10.33 | 11 | 9 | 11 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-12 | Venkateshwarlu | 1 | 1 | 8 | 8 | 8 | 8 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-12 | Visionary & Co | 1 | 1 | 5 | 5 | 5 | 5 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-12 | Visionary Co | 2 | 2 | 14.5 | 14.5 | 14 | 15 | 0 | 0
Mr. Arun Felbin | TA 421 | 2024-12 | venkateshwarlu | 2 | 2 | 14.5 | 14.5 | 9 | 20 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-01 | ATK Constructions | 10 | 10 | 7.6 | 7 | 4 | 13 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-01 | Ammu Engineering | 4 | 4 | 10 | 10.5 | 6 | 13 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-01 | Ashok kumar (Thotta) | 5 | 5 | 7.2 | 7 | 6 | 9 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-01 | Ashok-2 (Venkateshwarlu) | 5 | 5 | 10.2 | 11 | 7 | 13 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-01 | BaLraJ | 2 | 2 | 11 | 11 | 9 | 13 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-01 | Khatun | 5 | 5 | 12.6 | 6 | 4 | 36 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-01 | Praveen | 2 | 2 | 14.5 | 14.5 | 14 | 15 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-01 | Subash | 7 | 7 | 8 | 6 | 5 | 17 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-01 | TaGore | 5 | 5 | 13.2 | 12 | 11 | 18 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-01 | Venkateshwarlu | 3 | 3 | 13.33 | 14 | 7 | 19 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-01 | Visionary & Co | 2 | 2 | 14.5 | 14.5 | 13 | 16 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-02 | ATK Constructions | 4 | 4 | 9 | 9 | 4 | 14 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-02 | Ammu Engineering | 8 | 8 | 16.62 | 15 | 10 | 28 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-02 | Ashok kumar (Thotta) | 4 | 4 | 7.75 | 7.5 | 5 | 11 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-02 | Ashok-2 (Venkateshwarlu) | 2 | 2 | 14.5 | 14.5 | 12 | 17 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-02 | BaLraJ | 5 | 5 | 20 | 15 | 10 | 36 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-02 | J.$lnGH | 2 | 2 | 8 | 8 | 7 | 9 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-02 | Khatun | 5 | 5 | 5.8 | 6 | 5 | 7 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-02 | Praveen | 2 | 2 | 11.5 | 11.5 | 11 | 12 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-02 | Subash | 6 | 6 | 5 | 5 | 4 | 7 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-02 | TaGore | 4 | 4 | 11.25 | 11.5 | 9 | 13 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-02 | Venkateshwarlu | 3 | 3 | 11.67 | 11 | 10 | 14 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-03 | Ammu Engineering | 6 | 6 | 70.67 | 10.5 | 6 | 374 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-03 | Ashok kumar (Thotta) | 2 | 2 | 14.5 | 14.5 | 14 | 15 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-03 | Ashok-2 (Venkateshwarlu) | 2 | 2 | 18 | 18 | 15 | 21 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-03 | BaLraJ | 4 | 4 | 9 | 8.5 | 5 | 14 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-03 | J.$lnGH | 5 | 5 | 5 | 5 | 4 | 7 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-03 | J.$lnGH - o1 | 1 | 1 | 6 | 6 | 6 | 6 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-03 | J.$lnGH - o2 | 1 | 1 | 30 | 30 | 30 | 30 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-03 | Khatun | 6 | 6 | 5.33 | 5 | 4 | 7 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-03 | Praveen | 3 | 3 | 11 | 10 | 8 | 15 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-03 | Subash | 8 | 8 | 3.88 | 4 | 3 | 5 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-03 | TaGore | 2 | 2 | 199.5 | 199.5 | 12 | 387 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-03 | Venkateshwarlu | 3 | 3 | 10.33 | 10 | 9 | 12 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-04 | ATK Constructions | 2 | 2 | 24.5 | 24.5 | 24 | 25 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-04 | Ashok-2 (Venkateshwarlu) | 1 | 1 | 8 | 8 | 8 | 8 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-04 | J.$lnGH - o1 | 4 | 4 | 8.25 | 7 | 6 | 13 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-04 | J.$lnGH - o2 | 4 | 4 | 7.25 | 7.5 | 6 | 8 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-04 | Khatun | 6 | 6 | 5.33 | 5 | 4 | 8 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-04 | Praveen | 2 | 2 | 15 | 15 | 15 | 15 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-04 | Subash | 8 | 8 | 4.25 | 3.5 | 3 | 8 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-04 | TaGore | 2 | 2 | 23 | 23 | 13 | 33 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-04 | Venkateshwarlu | 6 | 6 | 9.5 | 10 | 5 | 13 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-05 | ATK Constructions | 13 | 13 | 28.77 | 33 | 10 | 40 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-05 | Ammu Engineering | 5 | 5 | 39.2 | 38 | 29 | 53 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-05 | Ashok-2 (Venkateshwarlu) | 6 | 5 | 13.8 | 11 | 5 | 31 | 1 | 0
Mr. Arun Felbin | TA 421 | 2025-05 | BaLraJ | 8 | 8 | 24.25 | 27 | 7 | 39 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-05 | Hassan | 2 | 2 | 19 | 19 | 14 | 24 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-05 | J.$lnGH - o1 | 1 | 1 | 4 | 4 | 4 | 4 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-05 | Jwala Singh -01 | 2 | 2 | 5.5 | 5.5 | 5 | 6 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-05 | Khatun | 4 | 4 | 5.75 | 5.5 | 4 | 8 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-05 | Praveen | 1 | 1 | 13 | 13 | 13 | 13 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-05 | Subash | 7 | 7 | 4.14 | 4 | 2 | 8 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-05 | TaGore | 1 | 1 | 52 | 52 | 52 | 52 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-05 | Venkateshwarlu | 4 | 4 | 31 | 34.5 | 19 | 36 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-06 | ATK Constructions | 8 | 8 | 12.38 | 11.5 | 5 | 22 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-06 | Ammu Engineering | 2 | 2 | 18.5 | 18.5 | 15 | 22 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-06 | Ashok-2 (Venkateshwarlu) | 6 | 6 | 7.33 | 7.5 | 5 | 9 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-06 | BaLraJ | 4 | 4 | 17.75 | 15 | 9 | 32 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-06 | Hassan | 3 | 3 | 9 | 9 | 6 | 12 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-06 | Praveen | 2 | 2 | 20.5 | 20.5 | 15 | 26 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-06 | Subash | 5 | 5 | 7.4 | 6 | 4 | 13 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-06 | Tagore | 1 | 1 | 21 | 21 | 21 | 21 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-06 | Venkateshwarlu | 4 | 4 | 18.25 | 16 | 12 | 29 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-07 | ATK Constructions | 6 | 6 | 11.33 | 11.5 | 6 | 17 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-07 | Ammu Engineering | 1 | 1 | 43 | 43 | 43 | 43 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-07 | Ashok-2 (Venkateshwarlu) | 4 | 4 | 11.75 | 13.5 | 4 | 16 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-07 | D K Verma | 1 | 1 | 9 | 9 | 9 | 9 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-07 | D k Verma | 1 | 1 | 9 | 9 | 9 | 9 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-07 | Hassan | 2 | 2 | 11 | 11 | 10 | 12 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-07 | Hassan -2 | 1 | 1 | 18 | 18 | 18 | 18 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-07 | Hassan-2 | 2 | 2 | 9.5 | 9.5 | 7 | 12 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-07 | Khatun | 5 | 5 | 5.2 | 5 | 3 | 7 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-07 | Naziruddin | 4 | 3 | 9 | 8 | 8 | 11 | 1 | 0
Mr. Arun Felbin | TA 421 | 2025-07 | Praveen | 1 | 1 | 18 | 18 | 18 | 18 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-07 | Subash | 7 | 6 | 4.67 | 4.5 | 4 | 6 | 1 | 0
Mr. Arun Felbin | TA 421 | 2025-07 | Venkateshwarlu | 1 | 1 | 17 | 17 | 17 | 17 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-08 | Ashok-2 (Venkateshwarlu) | 1 | 1 | 13 | 13 | 13 | 13 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-08 | D K Verma | 1 | 1 | 6 | 6 | 6 | 6 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-08 | D k Verma | 3 | 3 | 8.67 | 9 | 7 | 10 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-08 | Hassan | 3 | 3 | 14.67 | 17 | 9 | 18 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-08 | Khatun | 6 | 6 | 5.5 | 4 | 3 | 11 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-08 | Naziruddin | 4 | 4 | 8 | 5.5 | 4 | 17 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-08 | Praveen | 1 | 1 | 26 | 26 | 26 | 26 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-08 | Subash | 5 | 5 | 7.6 | 6 | 6 | 13 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-08 | Venkateshwarlu | 1 | 1 | 15 | 15 | 15 | 15 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-09 | D k Verma | 4 | 4 | 7 | 6.5 | 4 | 11 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-09 | Hassan | 3 | 3 | 8.33 | 8 | 7 | 10 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-09 | Khatun | 2 | 2 | 8.5 | 8.5 | 8 | 9 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-09 | Naziruddin | 3 | 3 | 9 | 8 | 8 | 11 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-09 | Praveen | 1 | 1 | 32 | 32 | 32 | 32 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-09 | Shakila Khatun | 2 | 2 | 4 | 4 | 4 | 4 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-09 | Subash | 7 | 7 | 4.43 | 4 | 2 | 7 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-10 | 2025-09-07 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 421 | 2025-10 | 2025-10-23 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 421 | 2025-10 | Ashok-2 (Venkateshwarlu) | 1 | 1 | 103 | 103 | 103 | 103 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-10 | D k Verma | 4 | 4 | 4.75 | 5 | 4 | 5 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-10 | Hassan | 2 | 2 | 11.5 | 11.5 | 10 | 13 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-10 | Khatun | 5 | 5 | 5.8 | 6 | 5 | 7 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-10 | Praveen | 2 | 2 | 21.5 | 21.5 | 14 | 29 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-10 | Subash | 4 | 4 | 7.25 | 7.5 | 5 | 9 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-10 | Yadhav + D k Verma | 1 | 1 | 16 | 16 | 16 | 16 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-11 | ATK Constructions | 1 | 1 | 16 | 16 | 16 | 16 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-11 | D k Verma | 5 | 5 | 7.2 | 7 | 6 | 8 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-11 | GowriShankar | 1 | 1 | 8 | 8 | 8 | 8 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-11 | Hassan | 3 | 3 | 10.67 | 12 | 7 | 13 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-11 | Khatun | 6 | 5 | 5.2 | 5 | 4 | 6 | 1 | 0
Mr. Arun Felbin | TA 421 | 2025-11 | Praveen | 1 | 1 | 18 | 18 | 18 | 18 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-11 | Subash | 8 | 7 | 4.57 | 3 | 3 | 8 | 1 | 0
Mr. Arun Felbin | TA 421 | 2025-12 | ATK Constructions | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 421 | 2025-12 | D k Verma | 2 | 2 | 10 | 10 | 9 | 11 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-12 | Gauri Shankar Mahto | 3 | 3 | 10.67 | 11 | 6 | 15 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-12 | Khatun | 7 | 7 | 4.86 | 5 | 3 | 7 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-12 | Praveen | 1 | 1 | 25 | 25 | 25 | 25 | 0 | 0
Mr. Arun Felbin | TA 421 | 2025-12 | Subash | 10 | 10 | 3.5 | 3 | 2 | 8 | 0 | 0
Mr. Arun Felbin | TA 421 | 2026-01 | 2026-01-31 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 421 | 2026-01 | D k Verma | 1 | 1 | 8 | 8 | 8 | 8 | 0 | 0
Mr. Arun Felbin | TA 421 | 2026-01 | Gauri Shankar Mahto | 2 | 2 | 7 | 7 | 5 | 9 | 0 | 0
Mr. Arun Felbin | TA 421 | 2026-01 | Khatun | 1 | 1 | 4 | 4 | 4 | 4 | 0 | 0
Mr. Arun Felbin | TA 421 | 2026-01 | Subash | 2 | 2 | 6 | 6 | 5 | 7 | 0 | 0
Mr. Arun Felbin | TA 421 | 2026-02 | 2026-02-01 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 421 | 2026-02 | 2026-02-04 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 421 | 2026-02 | 2026-02-07 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 421 | 2026-02 | 2026-02-08 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 421 | 2026-02 | 2026-02-11 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 421 | 2026-02 | 2026-02-12 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 421 | 2026-02 | 2026-02-20 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 421 | 2026-02 | 2026-02-25 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 421 | 2026-03 | 2026-03-02 00:00:00 | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 421 | 2026-03 | Unassigned | 1 | 0 |  |  |  |  | 1 | 0
Mr. Arun Felbin | TA 510FDN | 2025-02 | Arya Enterprises | 2 | 2 | 7 | 7 | 6 | 8 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2025-02 | B.K.Traders | 2 | 2 | 5 | 5 | 5 | 5 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2025-03 | Arya Enterprises | 3 | 3 | 6.33 | 5 | 5 | 9 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2025-03 | B.K.Traders | 2 | 2 | 6 | 6 | 4 | 8 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2025-04 | B.K.Traders | 2 | 2 | 7 | 7 | 6 | 8 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2025-04 | Om Infra | 4 | 4 | 17.25 | 16.5 | 14 | 22 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2025-05 | B.K.Traders | 5 | 5 | 11.2 | 12 | 9 | 13 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2025-05 | Om Infra | 2 | 2 | 15.5 | 15.5 | 11 | 20 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2025-06 | Jyoti Construction | 2 | 2 | 8 | 8 | 7 | 9 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2025-08 | Jyoti Construction | 1 | 1 | 67 | 67 | 67 | 67 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2025-09 | B.K.Traders | 1 | 1 | 19 | 19 | 19 | 19 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2025-09 | Unassigned | 1 | 1 | 56 | 56 | 56 | 56 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2025-10 | Shakaldev | 3 | 3 | 13.67 | 14 | 10 | 17 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2025-10 | Vihan | 2 | 2 | 21 | 21 | 17 | 25 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2025-11 | B.K.Traders | 1 | 1 | 14 | 14 | 14 | 14 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2025-11 | MD Hussain | 1 | 1 | 14 | 14 | 14 | 14 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2025-11 | Rudra | 1 | 1 | 16 | 16 | 16 | 16 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2025-11 | Shakaldev | 2 | 2 | 40.5 | 40.5 | 10 | 71 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2025-12 | Ambani | 1 | 1 | 25 | 25 | 25 | 25 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2025-12 | Haji Enterprises | 2 | 2 | 14 | 14 | 10 | 18 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2025-12 | MD Hussain | 2 | 2 | 14 | 14 | 8 | 20 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2025-12 | Rudra | 1 | 1 | 23 | 23 | 23 | 23 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2025-12 | Shakaldev | 3 | 3 | 15.67 | 15 | 10 | 22 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2025-12 | Vihan | 1 | 1 | 27 | 27 | 27 | 27 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2026-01 | Chandrakant Patel | 2 | 2 | 14 | 14 | 13 | 15 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2026-01 | Haji Enterprises | 1 | 1 | 30 | 30 | 30 | 30 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2026-01 | MD Hussain | 1 | 1 | 8 | 8 | 8 | 8 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2026-01 | Maa Bhavani | 2 | 2 | 9.5 | 9.5 | 9 | 10 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2026-01 | Vihan | 1 | 1 | 23 | 23 | 23 | 23 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2026-02 | ABS Construction | 1 | 1 | 12 | 12 | 12 | 12 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2026-02 | Chandrakant Patel | 1 | 1 | 10 | 10 | 10 | 10 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2026-02 | Haji Enterprises | 2 | 2 | 9 | 9 | 7 | 11 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2026-02 | MD Hussain | 1 | 1 | 29 | 29 | 29 | 29 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2026-02 | Vihan | 1 | 1 | 27 | 27 | 27 | 27 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2026-03 | ABS Construction | 1 | 1 | 34 | 34 | 34 | 34 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2026-03 | Haji Enterprises | 3 | 3 | 25.67 | 24 | 10 | 43 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2026-04 | BLG Infra | 4 | 4 | 7.5 | 7 | 6 | 10 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2026-04 | Chandrakant Patel | 2 | 2 | 9 | 9 | 7 | 11 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2026-04 | Haji Enterprises | 2 | 2 | 15.5 | 15.5 | 10 | 21 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2026-05 | BLG Infra | 6 | 6 | 6.17 | 7 | 4 | 8 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2026-05 | Chandrakant Patel | 1 | 1 | 28 | 28 | 28 | 28 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2026-05 | Haji Enterprises | 2 | 2 | 7.5 | 7.5 | 5 | 10 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2026-05 | Haji Enterprises2 | 1 | 1 | 10 | 10 | 10 | 10 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2026-05 | JDG Enterprises | 1 | 1 | 25 | 25 | 25 | 25 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2026-05 | Krishna Constrction | 1 | 1 | 47 | 47 | 47 | 47 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2026-05 | Vihan | 1 | 1 | 10 | 10 | 10 | 10 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2026-06 | BLG Infra | 2 | 2 | 10.5 | 10.5 | 7 | 14 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2026-06 | Haji Enterprises | 1 | 1 | 7 | 7 | 7 | 7 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2026-06 | Haji Enterprises-1 | 1 | 1 | 18 | 18 | 18 | 18 | 0 | 0
Mr. Arun Felbin | TA 510FDN | 2026-06 | Vihan | 3 | 3 | 9 | 9 | 8 | 10 | 0 | 0
Mr. Arun Felbin | TA 601 | 2025-08 | Unassigned | 2 | 0 |  |  |  |  | 2 | 0
Mr. Arun Felbin | TA 601 | 2025-09 | Unassigned | 2 | 0 |  |  |  |  | 2 | 0
Mr. Arun Felbin | TA 601 | 2025-10 | Unassigned | 8 | 0 |  |  |  |  | 8 | 0
Mr. Arun Felbin | TA 601 | 2025-11 | Unassigned | 10 | 0 |  |  |  |  | 10 | 0
Mr. Arun Felbin | TA 601 | 2025-12 | Unassigned | 23 | 0 |  |  |  |  | 23 | 0
Mr. Arun Felbin | TA 601 | 2026-01 | Unassigned | 48 | 0 |  |  |  |  | 48 | 0
Mr. Arun Felbin | TA 601 | 2026-02 | Unassigned | 46 | 0 |  |  |  |  | 46 | 0
Mr. Arun Felbin | TA 601 | 2026-03 | Unassigned | 28 | 0 |  |  |  |  | 28 | 0
Mr. Arun Felbin | TA 601 | 2026-04 | Unassigned | 16 | 0 |  |  |  |  | 16 | 0
Mr. Arun Felbin | TA 601 | 2026-05 | Unassigned | 12 | 0 |  |  |  |  | 12 | 0
Mr. Arun Felbin | TA 601 | 2026-06 | Unassigned | 12 | 0 |  |  |  |  | 12 | 0
Mr. NK Gupta | TA 413 | 2024-06 | Unassigned | 14 | 0 |  |  |  |  | 14 | 0
Mr. NK Gupta | TA 413 | 2024-07 | Unassigned | 20 | 0 |  |  |  |  | 20 | 0
Mr. NK Gupta | TA 413 | 2024-08 | Unassigned | 23 | 0 |  |  |  |  | 23 | 0
Mr. NK Gupta | TA 413 | 2024-09 | Unassigned | 40 | 0 |  |  |  |  | 40 | 0
Mr. NK Gupta | TA 413 | 2024-10 | Unassigned | 36 | 0 |  |  |  |  | 36 | 0
Mr. NK Gupta | TA 413 | 2024-11 | Unassigned | 24 | 0 |  |  |  |  | 24 | 0
Mr. NK Gupta | TA 413 | 2024-12 | Unassigned | 32 | 0 |  |  |  |  | 32 | 0
Mr. NK Gupta | TA 413 | 2025-01 | Unassigned | 35 | 0 |  |  |  |  | 35 | 0
Mr. NK Gupta | TA 413 | 2025-02 | Unassigned | 31 | 0 |  |  |  |  | 31 | 0
Mr. NK Gupta | TA 413 | 2025-03 | Unassigned | 19 | 0 |  |  |  |  | 19 | 0
Mr. NK Gupta | TA 413 | 2025-04 | Unassigned | 23 | 0 |  |  |  |  | 23 | 0
Mr. NK Gupta | TA 413 | 2025-05 | Unassigned | 10 | 0 |  |  |  |  | 10 | 0
Mr. NK Gupta | TA 413 | 2025-06 | Unassigned | 4 | 0 |  |  |  |  | 4 | 0
Mr. NK Gupta | TA 413 | 2025-07 | Unassigned | 2 | 0 |  |  |  |  | 2 | 0
Mr. NK Gupta | TA 413 | 2026-01 | Unassigned | 1 | 0 |  |  |  |  | 1 | 0
Mr. NK Gupta | TA 413 | 2026-02 | Unassigned | 1 | 0 |  |  |  |  | 1 | 0
Mr. NK Gupta | TA 413 | 2026-03 | Unassigned | 1 | 0 |  |  |  |  | 1 | 0
Mr. NK Gupta | TA 419 | 2024-05 | Garg Energy | 3 | 2 | 8.5 | 8.5 | 8 | 9 | 1 | 0
Mr. NK Gupta | TA 419 | 2024-06 | Bala Ji | 2 | 2 | 6 | 6 | 6 | 6 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-06 | Garg Energy | 7 | 7 | 6.71 | 6 | 4 | 9 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-07 | Bala Ji | 7 | 7 | 5.57 | 5 | 4 | 7 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-07 | Garg Energy | 7 | 7 | 10 | 10 | 6 | 13 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-07 | Kirti Construction | 3 | 3 | 9.67 | 6 | 6 | 17 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-08 | Bala Ji | 2 | 2 | 9.5 | 9.5 | 8 | 11 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-08 | Garg Energy | 2 | 2 | 6 | 6 | 4 | 8 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-08 | Kirti Construction | 3 | 3 | 9 | 8 | 5 | 14 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-08 | Surjeet | 1 | 1 | 18 | 18 | 18 | 18 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-09 | Garg Energy | 6 | 6 | 19.17 | 8.5 | 4 | 63 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-09 | Kirti Construction | 3 | 3 | 8.33 | 6 | 6 | 13 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-09 | NV Infra | 1 | 1 | 18 | 18 | 18 | 18 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-09 | Surjeet | 3 | 3 | 9.33 | 6 | 6 | 16 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-09 | TDCL | 3 | 3 | 8.33 | 8 | 7 | 10 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-10 | Garg Energy | 7 | 7 | 8.14 | 8 | 4 | 12 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-10 | Kirti Construction | 4 | 4 | 11.25 | 9.5 | 5 | 21 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-10 | NV Infra | 3 | 3 | 20.67 | 19 | 8 | 35 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-10 | Shyam | 1 | 1 | 19 | 19 | 19 | 19 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-10 | Surjeet | 1 | 1 | 17 | 17 | 17 | 17 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-10 | TDCL | 2 | 2 | 11.5 | 11.5 | 7 | 16 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-11 | Garg Energy | 5 | 5 | 16 | 17 | 6 | 26 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-11 | Kirti Construction | 2 | 2 | 19.5 | 19.5 | 4 | 35 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-11 | NV Infra | 2 | 1 | 16 | 16 | 16 | 16 | 0 | 1
Mr. NK Gupta | TA 419 | 2024-11 | Shyam Ent | 2 | 2 | 18 | 18 | 16 | 20 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-11 | Shyam Infra | 1 | 1 | 11 | 11 | 11 | 11 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-11 | Surjeet | 1 | 1 | 21 | 21 | 21 | 21 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-11 | TDCL | 1 | 1 | 26 | 26 | 26 | 26 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-12 | Garg Energy | 3 | 3 | 10.33 | 10 | 8 | 13 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-12 | Kirti Construction | 2 | 2 | 10 | 10 | 8 | 12 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-12 | NV Infra | 2 | 2 | 17.5 | 17.5 | 15 | 20 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-12 | Shyam Ent | 1 | 1 | 23 | 23 | 23 | 23 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-12 | Shyam Infra | 2 | 2 | 9.5 | 9.5 | 9 | 10 | 0 | 0
Mr. NK Gupta | TA 419 | 2024-12 | TDCL | 2 | 2 | 12 | 12 | 10 | 14 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-01 | Garg Energy | 3 | 3 | 11 | 11 | 5 | 17 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-01 | Kirti Construction | 1 | 1 | 13 | 13 | 13 | 13 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-01 | NV Infra | 2 | 2 | 15.5 | 15.5 | 11 | 20 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-01 | Shyam Infra | 1 | 1 | 26 | 26 | 26 | 26 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-02 | Garg Energy | 5 | 5 | 11.2 | 11 | 8 | 14 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-02 | NV Infra | 3 | 3 | 25 | 23 | 23 | 29 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-02 | Saran Communication | 1 | 1 | 29 | 29 | 29 | 29 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-02 | Shre Shyam | 1 | 1 | 15 | 15 | 15 | 15 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-03 | Garg Energy | 2 | 2 | 5 | 5 | 5 | 5 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-03 | NV Infra | 2 | 2 | 14 | 14 | 4 | 24 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-03 | Shree Shyam | 1 | 1 | 5 | 5 | 5 | 5 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-04 | GRD Enterprise | 1 | 1 | 14 | 14 | 14 | 14 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-04 | GRD Enterprises | 1 | 1 | 16 | 16 | 16 | 16 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-04 | Garg Energy | 7 | 7 | 10.14 | 6 | 2 | 21 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-04 | NV Infra | 3 | 3 | 6.67 | 7 | 5 | 8 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-04 | Tyagi Const | 2 | 2 | 12 | 12 | 6 | 18 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-05 | GRD Enterprises | 1 | 1 | 17 | 17 | 17 | 17 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-05 | Garg Energy | 4 | 4 | 9 | 7.5 | 6 | 15 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-05 | MS Construction | 1 | 1 | 17 | 17 | 17 | 17 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-05 | Tyagi Const | 2 | 2 | 8 | 8 | 7 | 9 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-06 | Garg Energy | 6 | 6 | 11.83 | 11.5 | 5 | 20 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-06 | Kirti Construction | 1 | 1 | 34 | 34 | 34 | 34 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-06 | MS Construction | 2 | 2 | 26.5 | 26.5 | 15 | 38 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-06 | NV Infra | 1 | 1 | 27 | 27 | 27 | 27 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-07 | Garg Energy | 3 | 3 | 15.67 | 16 | 14 | 17 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-07 | MS Construction | 1 | 1 | 15 | 15 | 15 | 15 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-07 | NV Infra | 1 | 1 | 44 | 44 | 44 | 44 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-08 | Garg Energy | 2 | 2 | 21 | 21 | 11 | 31 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-09 | Garg Energy | 3 | 3 | 6.33 | 6 | 5 | 8 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-10 | D&P | 1 | 1 | 26 | 26 | 26 | 26 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-10 | Garg Energy | 2 | 2 | 13.5 | 13.5 | 8 | 19 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-10 | NV Infra | 1 | 1 | 31 | 31 | 31 | 31 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-10 | Virendra | 2 | 2 | 20.5 | 20.5 | 18 | 23 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-11 | Ahlawat Const | 1 | 1 | 18 | 18 | 18 | 18 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-11 | Ahlawat Cpnstruction | 1 | 1 | 6 | 6 | 6 | 6 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-11 | D&B | 1 | 1 | 6 | 6 | 6 | 6 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-11 | D&P | 1 | 1 | 83 | 83 | 83 | 83 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-11 | DCLCSL( Ravindra) | 1 | 1 | 19 | 19 | 19 | 19 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-11 | GRD | 1 | 1 | 8 | 8 | 8 | 8 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-11 | GRD Enterprises 1 | 1 | 1 | 7 | 7 | 7 | 7 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-11 | GRD Enterprises 2 | 2 | 2 | 9.5 | 9.5 | 9 | 10 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-11 | GRD Enterprises1 | 1 | 1 | 22 | 22 | 22 | 22 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-11 | Garg Energy | 1 | 1 | 10 | 10 | 10 | 10 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-11 | MS Construction | 3 | 3 | 9 | 8 | 7 | 12 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-11 | NV Infra | 1 | 1 | 8 | 8 | 8 | 8 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-11 | Tyagi Construction | 1 | 1 | 7 | 7 | 7 | 7 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-11 | Virendra | 2 | 2 | 16 | 16 | 8 | 24 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-12 | Ahlawat Cpnstruction | 2 | 2 | 8.5 | 8.5 | 5 | 12 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-12 | Amit Yadav 1 | 1 | 1 | 9 | 9 | 9 | 9 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-12 | Bajrang Const | 1 | 1 | 11 | 11 | 11 | 11 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-12 | D&B | 2 | 2 | 10.5 | 10.5 | 9 | 12 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-12 | DCLCSL( Ravindra) | 1 | 1 | 14 | 14 | 14 | 14 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-12 | GRD 1 | 2 | 2 | 10.5 | 10.5 | 8 | 13 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-12 | GRD 2 | 3 | 3 | 6.33 | 8 | 3 | 8 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-12 | MS Construction | 1 | 1 | 13 | 13 | 13 | 13 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-12 | NV Infra | 2 | 2 | 30.5 | 30.5 | 19 | 42 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-12 | Utkarsh Const | 1 | 1 | 6 | 6 | 6 | 6 | 0 | 0
Mr. NK Gupta | TA 419 | 2025-12 | Virendra | 2 | 2 | 24 | 24 | 9 | 39 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-01 | Bajrang Const | 1 | 1 | 10 | 10 | 10 | 10 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-01 | D&B | 2 | 2 | 30.5 | 30.5 | 29 | 32 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-01 | DCLCSL( Ravindra) | 1 | 0 |  |  |  |  | 1 | 0
Mr. NK Gupta | TA 419 | 2026-01 | GRD 1 | 2 | 2 | 15.5 | 15.5 | 14 | 17 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-01 | GRD 2 | 2 | 2 | 13.5 | 13.5 | 8 | 19 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-01 | GRD Enterprises | 1 | 1 | 17 | 17 | 17 | 17 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-01 | MS Construction | 1 | 1 | 16 | 16 | 16 | 16 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-01 | Sherawali Const | 1 | 1 | 18 | 18 | 18 | 18 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-01 | Virendra | 1 | 1 | 21 | 21 | 21 | 21 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-02 | Bajrang Const | 1 | 1 | 42 | 42 | 42 | 42 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-02 | DCLCSL( Ravindra) | 1 | 1 | 31 | 31 | 31 | 31 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-02 | GRD 1 | 1 | 1 | 19 | 19 | 19 | 19 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-02 | GRD 2 | 1 | 1 | 23 | 23 | 23 | 23 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-02 | MS Construction | 1 | 1 | 35 | 35 | 35 | 35 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-02 | NV Infra | 1 | 1 | 38 | 38 | 38 | 38 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-02 | Sherawali Const | 1 | 1 | 32 | 32 | 32 | 32 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-03 | D&V | 2 | 2 | 41.5 | 41.5 | 10 | 73 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-03 | NV Infra | 1 | 1 | 46 | 46 | 46 | 46 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-03 | Ravinder | 1 | 1 | 19 | 19 | 19 | 19 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-03 | Shiv Shakti | 1 | 1 | 44 | 44 | 44 | 44 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-03 | Utkarsh Const | 1 | 1 | 43 | 43 | 43 | 43 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-04 | D&V | 2 | 2 | 26 | 26 | 25 | 27 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-04 | GRD 1 | 2 | 2 | 51.5 | 51.5 | 7 | 96 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-04 | Piroth and Sons | 1 | 1 | 35 | 35 | 35 | 35 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-04 | Ravindra | 1 | 1 | 27 | 27 | 27 | 27 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-04 | Shiv Shakti | 1 | 1 | 29 | 29 | 29 | 29 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-04 | Utkarsh Const/ D&V | 1 | 1 | 127 | 127 | 127 | 127 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-05 | D&V | 3 | 3 | 25.33 | 17 | 12 | 47 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-05 | GRD | 2 | 2 | 21 | 21 | 19 | 23 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-05 | GRD 2 | 1 | 1 | 26 | 26 | 26 | 26 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-05 | Pachauri | 2 | 2 | 32 | 32 | 30 | 34 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-05 | Radhe Enterprises | 1 | 1 | 34 | 34 | 34 | 34 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-05 | Rahul Raghav | 1 | 1 | 10 | 10 | 10 | 10 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-05 | Rahul Raghav | 1 | 1 | 10 | 10 | 10 | 10 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-05 | Ravindra | 1 | 1 | 75 | 75 | 75 | 75 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-05 | Shiv Shakti | 1 | 1 | 30 | 30 | 30 | 30 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-05 | TDCL(Ravindra) | 1 | 1 | 13 | 13 | 13 | 13 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-05 | Thakur Engineering | 1 | 1 | 104 | 104 | 104 | 104 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-05 | Virender Const | 3 | 3 | 21.33 | 18 | 12 | 34 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-05 | Vivan Const | 1 | 1 | 26 | 26 | 26 | 26 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-06 | D&V | 2 | 2 | 53.5 | 53.5 | 28 | 79 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-06 | GRD 2 | 1 | 1 | 9 | 9 | 9 | 9 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-06 | Pachauri | 2 | 2 | 13.5 | 13.5 | 6 | 21 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-06 | Piroth and Sons | 1 | 1 | 30 | 30 | 30 | 30 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-06 | Radhe Enterprises | 1 | 1 | 45 | 45 | 45 | 45 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-06 | Rahul Raghav | 2 | 2 | 13.5 | 13.5 | 10 | 17 | 0 | 0
Mr. NK Gupta | TA 419 | 2026-06 | Shiv Shakti | 1 | 1 | 32 | 32 | 32 | 32 | 0 | 0
Mr. NK Gupta | TA 512 | 2025-02 | Unassigned | 3 | 3 | 10.33 | 10 | 9 | 12 | 0 | 0
Mr. NK Gupta | TA 512 | 2025-03 | Unassigned | 26 | 26 | 6.15 | 6 | 5 | 8 | 0 | 0
Mr. NK Gupta | TA 512 | 2025-04 | Unassigned | 24 | 24 | 6.38 | 6 | 5 | 9 | 0 | 0
Mr. NK Gupta | TA 512 | 2025-05 | Unassigned | 23 | 23 | 9.04 | 6 | 4 | 54 | 0 | 0
Mr. NK Gupta | TA 512 | 2025-06 | Unassigned | 27 | 27 | 7.74 | 7 | 4 | 19 | 0 | 0
Mr. NK Gupta | TA 512 | 2025-07 | Unassigned | 39 | 39 | 8.74 | 8 | 4 | 25 | 0 | 0
Mr. NK Gupta | TA 512 | 2025-08 | Unassigned | 26 | 26 | 10.04 | 8 | 4 | 26 | 0 | 0
Mr. NK Gupta | TA 512 | 2025-09 | Unassigned | 19 | 19 | 7.11 | 6 | 3 | 16 | 0 | 0
Mr. NK Gupta | TA 512 | 2025-10 | Unassigned | 24 | 24 | 8.42 | 6.5 | 3 | 38 | 0 | 0
Mr. NK Gupta | TA 512 | 2025-11 | Unassigned | 29 | 29 | 6.76 | 7 | 2 | 16 | 0 | 0
Mr. NK Gupta | TA 512 | 2025-12 | Unassigned | 36 | 36 | 6.69 | 5 | 3 | 16 | 0 | 0
Mr. NK Gupta | TA 512 | 2026-01 | Unassigned | 11 | 11 | 9 | 7 | 4 | 22 | 0 | 0
Mr. NK Gupta | TA 512 | 2026-02 | Unassigned | 4 | 4 | 8.75 | 6.5 | 5 | 17 | 0 | 0
Mr. NK Gupta | TA 512 | 2026-03 | Unassigned | 3 | 3 | 7.67 | 8 | 4 | 11 | 0 | 0
Mr. NK Gupta | TA 512 | 2026-04 | Unassigned | 7 | 7 | 20.29 | 13 | 7 | 72 | 0 | 0
Mr. NK Gupta | TA 512 | 2026-05 | Unassigned | 5 | 5 | 11.2 | 8 | 4 | 24 | 0 | 0
Mr. NK Gupta | TA 512 | 2026-06 | Unassigned | 4 | 4 | 23.75 | 18 | 6 | 53 | 0 | 0
Mr. NK Gupta | TA 513SF | 2025-03 | Unassigned | 1 | 1 | 7 | 7 | 7 | 7 | 0 | 0
Mr. NK Gupta | TA 513SF | 2025-04 | Unassigned | 11 | 11 | 5.73 | 6 | 3 | 9 | 0 | 0
Mr. NK Gupta | TA 513SF | 2025-05 | Unassigned | 3 | 3 | 3.33 | 4 | 2 | 4 | 0 | 0
Mr. NK Gupta | TA 513SF | 2025-06 | Unassigned | 1 | 1 | 9 | 9 | 9 | 9 | 0 | 0
Mr. NK Gupta | TA 513SF | 2025-09 | Unassigned | 4 | 4 | 5.75 | 6 | 5 | 6 | 0 | 0
Mr. NK Gupta | TA 513SF | 2025-10 | Unassigned | 3 | 3 | 5.33 | 6 | 3 | 7 | 0 | 0
Mr. NK Gupta | TA 513SF | 2026-05 | Unassigned | 2 | 2 | 10 | 10 | 6 | 14 | 0 | 0
Mr. NK Gupta | TA 513SF | 2026-06 | Unassigned | 1 | 1 | 13 | 13 | 13 | 13 | 0 | 0
Mr. NK Gupta | TA 513SP | 2025-04 | Unassigned | 3 | 3 | 3.67 | 4 | 2 | 5 | 0 | 0
Mr. NK Gupta | TA 513SP | 2025-05 | Unassigned | 12 | 12 | 4.08 | 3 | 3 | 10 | 0 | 0
Mr. NK Gupta | TA 513SP | 2025-06 | Unassigned | 7 | 7 | 5.57 | 5 | 4 | 8 | 0 | 0
Mr. NK Gupta | TA 513SP | 2025-07 | Unassigned | 11 | 10 | 6.3 | 6 | 4 | 12 | 1 | 0
Mr. NK Gupta | TA 513SP | 2025-08 | Unassigned | 3 | 3 | 17.33 | 20 | 6 | 26 | 0 | 0
Mr. NK Gupta | TA 513SP | 2025-09 | Unassigned | 3 | 3 | 19.67 | 12 | 10 | 37 | 0 | 0
Mr. NK Gupta | TA 513SP | 2025-11 | Unassigned | 2 | 2 | 14.5 | 14.5 | 10 | 19 | 0 | 0
Mr. NK Gupta | TA 513SP | 2025-12 | Unassigned | 5 | 5 | 27.4 | 5 | 4 | 117 | 0 | 0
Mr. NK Gupta | TA 513SP | 2026-02 | Unassigned | 2 | 2 | 16 | 16 | 9 | 23 | 0 | 0
Mr. NK Gupta | TA 513SP | 2026-03 | Unassigned | 1 | 1 | 9 | 9 | 9 | 9 | 0 | 0
Mr. NK Gupta | TA 513SP | 2026-04 | Unassigned | 1 | 1 | 15 | 15 | 15 | 15 | 0 | 0
Mr. NK Gupta | TA 513SP | 2026-05 | Unassigned | 14 | 14 | 112.07 | 10 | 3 | 375 | 0 | 0
Mr. NK Gupta | TA 513SP | 2026-06 | Unassigned | 6 | 6 | 9.17 | 8 | 7 | 16 | 0 | 0
Mr. NK Gupta | TB 408 | 2023-10 | Unassigned | 1 | 0 |  |  |  |  | 1 | 0
Mr. NK Gupta | TB 408 | 2023-12 | Unassigned | 22 | 0 |  |  |  |  | 22 | 0
Mr. NK Gupta | TB 408 | 2024-01 | Unassigned | 46 | 0 |  |  |  |  | 46 | 0
Mr. NK Gupta | TB 408 | 2024-02 | Unassigned | 36 | 0 |  |  |  |  | 36 | 0
Mr. NK Gupta | TB 408 | 2024-03 | Unassigned | 16 | 0 |  |  |  |  | 16 | 0
Mr. NK Gupta | TB 408 | 2024-04 | Unassigned | 7 | 0 |  |  |  |  | 7 | 0
Mr. NK Gupta | TB 408 | 2024-05 | Unassigned | 15 | 0 |  |  |  |  | 15 | 0
Mr. NK Gupta | TB 408 | 2024-06 | Unassigned | 9 | 0 |  |  |  |  | 9 | 0
Mr. NK Gupta | TB 408 | 2024-07 | Unassigned | 14 | 0 |  |  |  |  | 14 | 0
Mr. NK Gupta | TB 408 | 2024-08 | Unassigned | 26 | 0 |  |  |  |  | 26 | 0
Mr. NK Gupta | TB 408 | 2024-09 | Unassigned | 38 | 0 |  |  |  |  | 38 | 0
Mr. NK Gupta | TB 408 | 2024-10 | Unassigned | 26 | 0 |  |  |  |  | 26 | 0
Mr. NK Gupta | TB 408 | 2024-11 | Unassigned | 9 | 0 |  |  |  |  | 9 | 0
Mr. NK Gupta | TB 408 | 2024-12 | Unassigned | 31 | 0 |  |  |  |  | 31 | 0
Mr. NK Gupta | TB 408 | 2025-01 | Unassigned | 47 | 0 |  |  |  |  | 47 | 0
Mr. NK Gupta | TB 408 | 2025-02 | Unassigned | 27 | 0 |  |  |  |  | 27 | 0
Mr. NK Gupta | TB 408 | 2025-03 | Unassigned | 17 | 0 |  |  |  |  | 17 | 0
Mr. NK Gupta | TB 408 | 2025-04 | Unassigned | 13 | 0 |  |  |  |  | 13 | 0
Mr. NK Gupta | TB 408 | 2025-05 | Unassigned | 13 | 0 |  |  |  |  | 13 | 0
Mr. NK Gupta | TB 408 | 2025-06 | Unassigned | 19 | 0 |  |  |  |  | 19 | 0
Mr. NK Gupta | TB 408 | 2025-07 | Unassigned | 22 | 0 |  |  |  |  | 22 | 0
Mr. NK Gupta | TB 408 | 2025-08 | Unassigned | 8 | 0 |  |  |  |  | 8 | 0
Mr. NK Gupta | TB 408 | 2025-09 | Unassigned | 9 | 0 |  |  |  |  | 9 | 0
Mr. NK Gupta | TB 408 | 2025-10 | Unassigned | 7 | 0 |  |  |  |  | 7 | 0
Mr. NK Gupta | TB 408 | 2025-11 | Unassigned | 3 | 0 |  |  |  |  | 3 | 0
Mr. NK Gupta | TB 408 | 2026-02 | Unassigned | 3 | 0 |  |  |  |  | 3 | 0
Mr. NK Gupta | TB 408 | 2026-03 | Unassigned | 1 | 0 |  |  |  |  | 1 | 0
Mr. NK Gupta | TB 507765KV | 2025-05 | Unassigned | 1 | 0 |  |  |  |  | 0 | 1
Mr. NK Gupta | TB 507765KV | 2026-02 | Unassigned | 7 | 7 | 7.29 | 5 | 4 | 18 | 0 | 0
Mr. NK Gupta | TB 507765KV | 2026-03 | Unassigned | 8 | 7 | 7.71 | 4 | 3 | 14 | 1 | 0
Mr. NK Gupta | TB 507765KV | 2026-04 | Unassigned | 7 | 7 | 10.86 | 10 | 3 | 17 | 0 | 0
Mr. NK Gupta | TB 507765KV | 2026-05 | Unassigned | 11 | 11 | 18.18 | 14 | 4 | 48 | 0 | 0
Mr. NK Gupta | TB 507765KV | 2026-06 | Unassigned | 2 | 2 | 15.5 | 15.5 | 15 | 16 | 0 | 0
Mr. NK Gupta | TB 507MAIN | 2025-01 | Unassigned | 2 | 2 | 10 | 10 | 10 | 10 | 0 | 0
Mr. NK Gupta | TB 507MAIN | 2025-02 | Unassigned | 20 | 19 | 7.16 | 7 | 3 | 13 | 1 | 0
Mr. NK Gupta | TB 507MAIN | 2025-03 | Unassigned | 16 | 16 | 8.25 | 7 | 3 | 18 | 0 | 0
Mr. NK Gupta | TB 507MAIN | 2025-04 | Unassigned | 13 | 13 | 8.85 | 7 | 4 | 19 | 0 | 0
Mr. NK Gupta | TB 507MAIN | 2025-05 | Unassigned | 9 | 9 | 14.22 | 13 | 8 | 30 | 0 | 0
Mr. NK Gupta | TB 507MAIN | 2025-06 | Unassigned | 25 | 24 | 7.88 | 7 | 4 | 21 | 0 | 1
Mr. NK Gupta | TB 507MAIN | 2025-07 | Unassigned | 50 | 50 | 8.14 | 6 | 2 | 52 | 0 | 0
Mr. NK Gupta | TB 507MAIN | 2025-08 | Unassigned | 52 | 52 | 16.5 | 7 | 2 | 374 | 0 | 0
Mr. NK Gupta | TB 507MAIN | 2025-09 | Unassigned | 20 | 20 | 11.85 | 9 | 5 | 39 | 0 | 0
Mr. NK Gupta | TB 507MAIN | 2025-10 | Unassigned | 8 | 8 | 11.25 | 12 | 5 | 16 | 0 | 0
Mr. NK Gupta | TB 507MAIN | 2025-11 | Unassigned | 19 | 19 | 13.32 | 11 | 6 | 53 | 0 | 0
Mr. NK Gupta | TB 507MAIN | 2025-12 | Unassigned | 13 | 13 | 8.62 | 9 | 5 | 13 | 0 | 0
Mr. NK Gupta | TB 507MAIN | 2026-01 | Unassigned | 15 | 15 | 6.53 | 6 | 2 | 12 | 0 | 0
Mr. NK Gupta | TB 507MAIN | 2026-02 | Unassigned | 5 | 5 | 6.4 | 5 | 3 | 11 | 0 | 0
Mr. NK Gupta | TB 507MAIN | 2026-03 | Unassigned | 9 | 9 | 10.67 | 7 | 3 | 25 | 0 | 0
Mr. NK Gupta | TB 507MAIN | 2026-04 | Unassigned | 13 | 13 | 6.77 | 6 | 3 | 13 | 0 | 0
Mr. NK Gupta | TB 507MAIN | 2026-05 | Unassigned | 19 | 19 | 9.95 | 9 | 2 | 23 | 0 | 0
Mr. NK Gupta | TB 507MAIN | 2026-06 | Unassigned | 8 | 8 | 5.75 | 6 | 3 | 8 | 0 | 0
Mr. NK Gupta | TB 605JAMMU | 2025-08 | Unassigned | 1 | 0 |  |  |  |  | 1 | 0
Mr. NK Gupta | TB 605JAMMU | 2025-09 | Unassigned | 3 | 0 |  |  |  |  | 3 | 0
Mr. NK Gupta | TB 605JAMMU | 2025-10 | Unassigned | 7 | 0 |  |  |  |  | 7 | 0
Mr. NK Gupta | TB 605JAMMU | 2025-11 | Unassigned | 12 | 0 |  |  |  |  | 12 | 0
Mr. NK Gupta | TB 605JAMMU | 2025-12 | Unassigned | 17 | 0 |  |  |  |  | 17 | 0
Mr. NK Gupta | TB 605JAMMU | 2026-01 | Unassigned | 15 | 0 |  |  |  |  | 15 | 0
Mr. NK Gupta | TB 605JAMMU | 2026-02 | Unassigned | 12 | 0 |  |  |  |  | 12 | 0
Mr. NK Gupta | TB 605JAMMU | 2026-03 | Unassigned | 13 | 0 |  |  |  |  | 13 | 0
Mr. NK Gupta | TB 605JAMMU | 2026-04 | Unassigned | 10 | 0 |  |  |  |  | 10 | 0
Mr. NK Gupta | TB 605JAMMU | 2026-05 | Unassigned | 10 | 0 |  |  |  |  | 10 | 0
Mr. NK Gupta | TB 605JAMMU | 2026-06 | Unassigned | 8 | 0 |  |  |  |  | 8 | 0
Mr. NK Gupta | TB 605LILO | 2026-05 | Unassigned | 1 | 0 |  |  |  |  | 1 | 0
Mr. NK Gupta | TB 605PUNJAB | 2025-10 | Unassigned | 8 | 0 |  |  |  |  | 8 | 0
Mr. NK Gupta | TB 605PUNJAB | 2025-11 | Unassigned | 30 | 0 |  |  |  |  | 30 | 0
Mr. NK Gupta | TB 605PUNJAB | 2025-12 | Unassigned | 40 | 0 |  |  |  |  | 40 | 0
Mr. NK Gupta | TB 605PUNJAB | 2026-01 | Unassigned | 27 | 0 |  |  |  |  | 27 | 0
Mr. NK Gupta | TB 605PUNJAB | 2026-02 | Unassigned | 30 | 0 |  |  |  |  | 30 | 0
Mr. NK Gupta | TB 605PUNJAB | 2026-03 | Unassigned | 15 | 0 |  |  |  |  | 15 | 0
Mr. NK Gupta | TB 605PUNJAB | 2026-04 | Unassigned | 16 | 0 |  |  |  |  | 16 | 0
Mr. NK Gupta | TB 605PUNJAB | 2026-05 | Unassigned | 44 | 0 |  |  |  |  | 44 | 0
Mr. NK Gupta | TB 605PUNJAB | 2026-06 | Unassigned | 13 | 0 |  |  |  |  | 13 | 0
Mr. NK Gupta | TB 608 | 2025-10 | Unassigned | 2 | 2 | 12.5 | 12.5 | 12 | 13 | 0 | 0
Mr. NK Gupta | TB 608 | 2025-11 | Unassigned | 20 | 20 | 19.15 | 18 | 9 | 30 | 0 | 0
Mr. NK Gupta | TB 608 | 2025-12 | Unassigned | 34 | 34 | 17.79 | 15 | 9 | 42 | 0 | 0
Mr. NK Gupta | TB 608 | 2026-01 | Unassigned | 30 | 30 | 21 | 16 | 11 | 105 | 0 | 0
Mr. NK Gupta | TB 608 | 2026-02 | Unassigned | 30 | 30 | 16.6 | 15 | 6 | 45 | 0 | 0
Mr. NK Gupta | TB 608 | 2026-03 | Unassigned | 17 | 17 | 18.71 | 17 | 2 | 59 | 0 | 0
Mr. NK Gupta | TB 608 | 2026-04 | Unassigned | 8 | 8 | 16.62 | 19.5 | 1 | 34 | 0 | 0
Mr. NK Gupta | TB 608 | 2026-05 | Unassigned | 12 | 12 | 17.58 | 19 | 3 | 40 | 0 | 0
Mr. NK Gupta | TB 608 | 2026-06 | Unassigned | 2 | 2 | 27.5 | 27.5 | 21 | 34 | 0 | 0
Mr. Nabajit Baruah | TA 505 | 2015-11 | Unassigned | 1 | 0 |  |  |  |  | 1 | 0
Mr. Nabajit Baruah | TA 505 | 2024-03 | Unassigned | 1 | 0 |  |  |  |  | 1 | 0
Mr. Nabajit Baruah | TA 505 | 2024-04 | Unassigned | 2 | 0 |  |  |  |  | 2 | 0
Mr. Nabajit Baruah | TA 505 | 2024-10 | Unassigned | 9 | 9 | 4 | 4 | 2 | 7 | 0 | 0
Mr. Nabajit Baruah | TA 505 | 2024-11 | Unassigned | 26 | 26 | 3.12 | 3 | 1 | 8 | 0 | 0
Mr. Nabajit Baruah | TA 505 | 2024-12 | Unassigned | 36 | 36 | 4.14 | 3 | 1 | 37 | 0 | 0
Mr. Nabajit Baruah | TA 505 | 2025-01 | Unassigned | 30 | 30 | 2.93 | 2 | 1 | 9 | 0 | 0
Mr. Nabajit Baruah | TA 505 | 2025-02 | Unassigned | 32 | 32 | 4.5 | 2.5 | 1 | 34 | 0 | 0
Mr. Nabajit Baruah | TA 505 | 2025-03 | Unassigned | 21 | 4 | 1.75 | 1.5 | 1 | 3 | 17 | 0
Mr. Nabajit Baruah | TA 505 | 2025-04 | Unassigned | 48 | 0 |  |  |  |  | 48 | 0
Mr. Nabajit Baruah | TA 505 | 2025-05 | Unassigned | 47 | 0 |  |  |  |  | 47 | 0
Mr. Nabajit Baruah | TA 505 | 2025-06 | Unassigned | 15 | 0 |  |  |  |  | 15 | 0
Mr. Nabajit Baruah | TA 505 | 2025-07 | Unassigned | 2 | 0 |  |  |  |  | 2 | 0
Mr. Nabajit Baruah | TA 505 | 2025-08 | Unassigned | 1 | 0 |  |  |  |  | 1 | 0
Mr. Nabajit Baruah | TA 505 | 2025-09 | Unassigned | 10 | 0 |  |  |  |  | 10 | 0
Mr. Nabajit Baruah | TA 505 | 2025-10 | Unassigned | 12 | 0 |  |  |  |  | 12 | 0
Mr. Nabajit Baruah | TA 505 | 2025-11 | Unassigned | 16 | 0 |  |  |  |  | 16 | 0
Mr. Nabajit Baruah | TA 505 | 2025-12 | Unassigned | 18 | 0 |  |  |  |  | 18 | 0
Mr. Nabajit Baruah | TA 505 | 2026-01 | Unassigned | 17 | 0 |  |  |  |  | 17 | 0
Mr. Nabajit Baruah | TA 505 | 2026-02 | Unassigned | 10 | 0 |  |  |  |  | 10 | 0
Mr. Nabajit Baruah | TA 505 | 2026-03 | Unassigned | 8 | 0 |  |  |  |  | 8 | 0
Mr. Nabajit Baruah | TA 505 | 2026-04 | Unassigned | 8 | 0 |  |  |  |  | 8 | 0
Mr. Nabajit Baruah | TA 505 | 2026-05 | Unassigned | 4 | 0 |  |  |  |  | 4 | 0
Mr. Nabajit Baruah | TA 505 | 2026-06 | Unassigned | 1 | 0 |  |  |  |  | 1 | 0
Mr. Nabajit Baruah | TB 501132KV | 2025-07 | Unassigned | 1 | 0 |  |  |  |  | 1 | 0
Mr. Nabajit Baruah | TB 501132KV | 2025-10 | Unassigned | 2 | 0 |  |  |  |  | 2 | 0
Mr. Nabajit Baruah | TB 501132KV | 2025-11 | Unassigned | 2 | 0 |  |  |  |  | 2 | 0
Mr. Nabajit Baruah | TB 501132KV | 2025-12 | Unassigned | 8 | 0 |  |  |  |  | 8 | 0
Mr. Nabajit Baruah | TB 501132KV | 2026-01 | Unassigned | 9 | 0 |  |  |  |  | 9 | 0
Mr. Nabajit Baruah | TB 501132KV | 2026-02 | Unassigned | 3 | 0 |  |  |  |  | 3 | 0
Mr. Nabajit Baruah | TB 501132KV | 2026-03 | Unassigned | 4 | 0 |  |  |  |  | 4 | 0
Mr. Nabajit Baruah | TB 501132KV | 2026-04 | Unassigned | 2 | 0 |  |  |  |  | 2 | 0
Mr. Nabajit Baruah | TB 501220KV | 2024-08 | Unassigned | 3 | 0 |  |  |  |  | 3 | 0
Mr. Nabajit Baruah | TB 501220KV | 2024-09 | Unassigned | 7 | 0 |  |  |  |  | 7 | 0
Mr. Nabajit Baruah | TB 501220KV | 2024-10 | Unassigned | 25 | 0 |  |  |  |  | 25 | 0
Mr. Nabajit Baruah | TB 501220KV | 2024-11 | Unassigned | 26 | 0 |  |  |  |  | 26 | 0
Mr. Nabajit Baruah | TB 501220KV | 2024-12 | Unassigned | 27 | 0 |  |  |  |  | 27 | 0
Mr. Nabajit Baruah | TB 501220KV | 2025-01 | Unassigned | 21 | 0 |  |  |  |  | 21 | 0
Mr. Nabajit Baruah | TB 501220KV | 2025-02 | Unassigned | 21 | 0 |  |  |  |  | 21 | 0
Mr. Nabajit Baruah | TB 501220KV | 2025-03 | Unassigned | 9 | 0 |  |  |  |  | 9 | 0
Mr. Nabajit Baruah | TB 501220KV | 2025-04 | Unassigned | 11 | 0 |  |  |  |  | 11 | 0
Mr. Nabajit Baruah | TB 501220KV | 2025-05 | Unassigned | 18 | 0 |  |  |  |  | 18 | 0
Mr. Nabajit Baruah | TB 501220KV | 2025-06 | Unassigned | 6 | 0 |  |  |  |  | 6 | 0
Mr. Nabajit Baruah | TB 501220KV | 2025-08 | Unassigned | 3 | 0 |  |  |  |  | 3 | 0
Mr. Nabajit Baruah | TB 501220KV | 2025-09 | Unassigned | 8 | 0 |  |  |  |  | 8 | 0
Mr. Nabajit Baruah | TB 501220KV | 2025-10 | Unassigned | 4 | 0 |  |  |  |  | 4 | 0
Mr. Nabajit Baruah | TB 501220KV | 2025-11 | Unassigned | 5 | 0 |  |  |  |  | 5 | 0
Mr. Nabajit Baruah | TB 501220KV | 2025-12 | Unassigned | 2 | 0 |  |  |  |  | 2 | 0
Mr. Nabajit Baruah | TB 501220KV | 2026-02 | Unassigned | 1 | 0 |  |  |  |  | 1 | 0
Mr. Nabajit Baruah | TB 501220KV | 2026-04 | Unassigned | 3 | 0 |  |  |  |  | 3 | 0

## Foundation Details
PCH | Project | Project Key | Line | Location No | Gang | Start Date | Completion Date | Month | Duration Days | Duration Status | Source Type | Quality Flag | Source File | Source Sheet
Mr. NK Gupta | TA 413 | TA413 |  | 9/4 | Unassigned |  | 2024-06-06 | 2024-06 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 10/1 | Unassigned |  | 2024-06-07 | 2024-06 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 10/2 | Unassigned |  | 2024-06-09 | 2024-06 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 9/11 | Unassigned |  | 2024-06-11 | 2024-06 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 15/2 | Unassigned |  | 2024-06-17 | 2024-06 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 9/5 | Unassigned |  | 2024-06-17 | 2024-06 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 15/3 | Unassigned |  | 2024-06-18 | 2024-06 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 15/4 | Unassigned |  | 2024-06-21 | 2024-06 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 9/3 | Unassigned |  | 2024-06-23 | 2024-06 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 15/5 | Unassigned |  | 2024-06-24 | 2024-06 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 8/5 | Unassigned |  | 2024-06-26 | 2024-06 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 15/6 | Unassigned |  | 2024-06-27 | 2024-06 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 9/10 | Unassigned |  | 2024-06-28 | 2024-06 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 9/2 | Unassigned |  | 2024-06-29 | 2024-06 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 15/9 | Unassigned |  | 2024-07-03 | 2024-07 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 8/6 | Unassigned |  | 2024-07-03 | 2024-07 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 15/8 | Unassigned |  | 2024-07-06 | 2024-07 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 31/9 | Unassigned |  | 2024-07-06 | 2024-07 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 8/7 | Unassigned |  | 2024-07-09 | 2024-07 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 15/10 | Unassigned |  | 2024-07-10 | 2024-07 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 31/8 | Unassigned |  | 2024-07-10 | 2024-07 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 9/1 | Unassigned |  | 2024-07-10 | 2024-07 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 15/7 | Unassigned |  | 2024-07-11 | 2024-07 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 31/7 | Unassigned |  | 2024-07-15 | 2024-07 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 15/11 | Unassigned |  | 2024-07-18 | 2024-07 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 8/8 | Unassigned |  | 2024-07-19 | 2024-07 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 8/1 | Unassigned |  | 2024-07-20 | 2024-07 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 31/6 | Unassigned |  | 2024-07-22 | 2024-07 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 29/4 | Unassigned |  | 2024-07-24 | 2024-07 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 8/2 | Unassigned |  | 2024-07-25 | 2024-07 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 8/9 | Unassigned |  | 2024-07-25 | 2024-07 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 31/10 | Unassigned |  | 2024-07-28 | 2024-07 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 29/3 | Unassigned |  | 2024-07-29 | 2024-07 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 31/3 | Unassigned |  | 2024-07-31 | 2024-07 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 30/1 | Unassigned |  | 2024-08-01 | 2024-08 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 29/5 | Unassigned |  | 2024-08-03 | 2024-08 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 31/1 | Unassigned |  | 2024-08-03 | 2024-08 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 29A/2 | Unassigned |  | 2024-08-08 | 2024-08 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 5/3 | Unassigned |  | 2024-08-08 | 2024-08 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 7/1 | Unassigned |  | 2024-08-10 | 2024-08 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 8/10 | Unassigned |  | 2024-08-13 | 2024-08 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 29A/1 | Unassigned |  | 2024-08-14 | 2024-08 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 27/4 | Unassigned |  | 2024-08-16 | 2024-08 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 7A/5 | Unassigned |  | 2024-08-17 | 2024-08 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 5/8 | Unassigned |  | 2024-08-18 | 2024-08 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 29A/3 | Unassigned |  | 2024-08-20 | 2024-08 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 32/3 | Unassigned |  | 2024-08-20 | 2024-08 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 7A/4 | Unassigned |  | 2024-08-23 | 2024-08 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 29A/4 | Unassigned |  | 2024-08-24 | 2024-08 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 5/4 | Unassigned |  | 2024-08-25 | 2024-08 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 32/4 | Unassigned |  | 2024-08-26 | 2024-08 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 29A/5 | Unassigned |  | 2024-08-27 | 2024-08 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 6/2 | Unassigned |  | 2024-08-27 | 2024-08 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 27/5 | Unassigned |  | 2024-08-28 | 2024-08 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 33/6 | Unassigned |  | 2024-08-30 | 2024-08 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 6/1 | Unassigned |  | 2024-08-30 | 2024-08 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 29A/6 | Unassigned |  | 2024-08-31 | 2024-08 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 4A/5 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 7A/1 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 33/7 | Unassigned |  | 2024-09-04 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 5/10 | Unassigned |  | 2024-09-04 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 6/12 | Unassigned |  | 2024-09-05 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 4A/4 | Unassigned |  | 2024-09-06 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 7A/2 | Unassigned |  | 2024-09-06 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 6/3 | Unassigned |  | 2024-09-07 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 33/4 | Unassigned |  | 2024-09-09 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 4A/3 | Unassigned |  | 2024-09-09 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 29/1 | Unassigned |  | 2024-09-10 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 7A/3 | Unassigned |  | 2024-09-10 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 4A/6 | Unassigned |  | 2024-09-12 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 5/7 | Unassigned |  | 2024-09-12 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 33/3 | Unassigned |  | 2024-09-13 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 34/12 | Unassigned |  | 2024-09-13 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 6/11 | Unassigned |  | 2024-09-14 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 34/1 | Unassigned |  | 2024-09-15 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 36A/1 | Unassigned |  | 2024-09-15 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 5/6 | Unassigned |  | 2024-09-15 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 4A/2 | Unassigned |  | 2024-09-16 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 34/3 | Unassigned |  | 2024-09-18 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 36A/2 | Unassigned |  | 2024-09-19 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 27/2 | Unassigned |  | 2024-09-20 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 34/11 | Unassigned |  | 2024-09-20 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 6/4 | Unassigned |  | 2024-09-20 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 34/4 | Unassigned |  | 2024-09-21 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 4A/1 | Unassigned |  | 2024-09-21 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 37/1 | Unassigned |  | 2024-09-23 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 5/2 | Unassigned |  | 2024-09-23 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 6/6 | Unassigned |  | 2024-09-23 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 34/5 | Unassigned |  | 2024-09-25 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 35/1 | Unassigned |  | 2024-09-26 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 37/2 | Unassigned |  | 2024-09-27 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 4/1 | Unassigned |  | 2024-09-27 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 27/1 | Unassigned |  | 2024-09-28 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 34/6 | Unassigned |  | 2024-09-28 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 6/10 | Unassigned |  | 2024-09-29 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 34/8 | Unassigned |  | 2024-09-30 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 37/3 | Unassigned |  | 2024-09-30 | 2024-09 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 4A/0 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 6/9 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 7/0 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 35/5 | Unassigned |  | 2024-10-03 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 34/7 | Unassigned |  | 2024-10-04 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 3/8 | Unassigned |  | 2024-10-05 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 36A/0 | Unassigned |  | 2024-10-05 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 34/9 | Unassigned |  | 2024-10-07 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 5/9 | Unassigned |  | 2024-10-07 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 27/3 | Unassigned |  | 2024-10-08 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 7/3 | Unassigned |  | 2024-10-08 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 3/9 | Unassigned |  | 2024-10-09 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 35/6 | Unassigned |  | 2024-10-09 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 3/10 | Unassigned |  | 2024-10-12 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 34/10 | Unassigned |  | 2024-10-12 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 7/4 | Unassigned |  | 2024-10-12 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 27/6 | Unassigned |  | 2024-10-14 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 37/0 | Unassigned |  | 2024-10-14 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 3/11 | Unassigned |  | 2024-10-16 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 34/2 | Unassigned |  | 2024-10-16 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 6/7 | Unassigned |  | 2024-10-16 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 35/7 | Unassigned |  | 2024-10-17 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 6/0 | Unassigned |  | 2024-10-18 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 3/7 | Unassigned |  | 2024-10-19 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 6/5 | Unassigned |  | 2024-10-19 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 37A/4 | Unassigned |  | 2024-10-21 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 3/6 | Unassigned |  | 2024-10-22 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 33/5 | Unassigned |  | 2024-10-22 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 5/5 | Unassigned |  | 2024-10-23 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 29/2 | Unassigned |  | 2024-10-25 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 33/8 | Unassigned |  | 2024-10-25 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 37A/5 | Unassigned |  | 2024-10-25 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 35/9 | Unassigned |  | 2024-10-27 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 3/4 | Unassigned |  | 2024-10-29 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 35/8 | Unassigned |  | 2024-10-29 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 37A/3 | Unassigned |  | 2024-10-30 | 2024-10 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 29A/0 | Unassigned |  | 2024-11-07 | 2024-11 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 37A/2 | Unassigned |  | 2024-11-08 | 2024-11 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 6/8 | Unassigned |  | 2024-11-08 | 2024-11 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 35/11 | Unassigned |  | 2024-11-09 | 2024-11 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 33/9 | Unassigned |  | 2024-11-11 | 2024-11 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 18/0 | Unassigned |  | 2024-11-12 | 2024-11 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 37A/1 | Unassigned |  | 2024-11-12 | 2024-11 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 18/1 | Unassigned |  | 2024-11-16 | 2024-11 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 37/4 | Unassigned |  | 2024-11-17 | 2024-11 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 18/2 | Unassigned |  | 2024-11-19 | 2024-11 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 36/0 | Unassigned |  | 2024-11-20 | 2024-11 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 38/8 | Unassigned |  | 2024-11-20 | 2024-11 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 37/5 | Unassigned |  | 2024-11-21 | 2024-11 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 38/9 | Unassigned |  | 2024-11-21 | 2024-11 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 7A/0 | Unassigned |  | 2024-11-22 | 2024-11 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 34/0 | Unassigned |  | 2024-11-23 | 2024-11 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 38/10 | Unassigned |  | 2024-11-23 | 2024-11 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 18/3 | Unassigned |  | 2024-11-24 | 2024-11 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 38/7 | Unassigned |  | 2024-11-26 | 2024-11 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 35/4 | Unassigned |  | 2024-11-27 | 2024-11 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 37A/0 | Unassigned |  | 2024-11-27 | 2024-11 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 18/4 | Unassigned |  | 2024-11-29 | 2024-11 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 38/6 | Unassigned |  | 2024-11-29 | 2024-11 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 38/5 | Unassigned |  | 2024-11-30 | 2024-11 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 7/2 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 18/6 | Unassigned |  | 2024-12-04 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 38/0 | Unassigned |  | 2024-12-04 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 35/0 | Unassigned |  | 2024-12-06 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 38/3 | Unassigned |  | 2024-12-06 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 18/5 | Unassigned |  | 2024-12-07 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 37A/6 | Unassigned |  | 2024-12-08 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 38/4 | Unassigned |  | 2024-12-08 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 30/3 | Unassigned |  | 2024-12-10 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 38/2 | Unassigned |  | 2024-12-12 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 40/2 | Unassigned |  | 2024-12-12 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 38/1 | Unassigned |  | 2024-12-13 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 40/3 | Unassigned |  | 2024-12-14 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 39/1 | Unassigned |  | 2024-12-15 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 7/5 | Unassigned |  | 2024-12-17 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 30/0 | Unassigned |  | 2024-12-18 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 17/0 | Unassigned |  | 2024-12-19 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 40/7 | Unassigned |  | 2024-12-19 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 39/0 | Unassigned |  | 2024-12-21 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 39/2 | Unassigned |  | 2024-12-21 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 40/6 | Unassigned |  | 2024-12-21 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 30/2 | Unassigned |  | 2024-12-22 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 39/4 | Unassigned |  | 2024-12-23 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 40/8 | Unassigned |  | 2024-12-25 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 41/1 | Unassigned |  | 2024-12-27 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 16/0 | Unassigned |  | 2024-12-28 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 30/4 | Unassigned |  | 2024-12-29 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 39/3 | Unassigned |  | 2024-12-29 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 40/5 | Unassigned |  | 2024-12-29 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 7/6 | Unassigned |  | 2024-12-30 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 15/12 | Unassigned |  | 2024-12-31 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 40/4 | Unassigned |  | 2024-12-31 | 2024-12 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 30/5 | Unassigned |  | 2025-01-03 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 42/0 | Unassigned |  | 2025-01-03 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 39/5 | Unassigned |  | 2025-01-05 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 40/9 | Unassigned |  | 2025-01-05 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 8/3 | Unassigned |  | 2025-01-06 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 30/6 | Unassigned |  | 2025-01-07 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 42/1 | Unassigned |  | 2025-01-08 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 39/6 | Unassigned |  | 2025-01-09 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 40/10 | Unassigned |  | 2025-01-09 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 30/7 | Unassigned |  | 2025-01-10 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 30/8 | Unassigned |  | 2025-01-13 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 40/11 | Unassigned |  | 2025-01-13 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 42/2 | Unassigned |  | 2025-01-13 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 8/0 | Unassigned |  | 2025-01-13 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 22/0 | Unassigned |  | 2025-01-15 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 30/9 | Unassigned |  | 2025-01-17 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 39/7 | Unassigned |  | 2025-01-17 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 41/0 | Unassigned |  | 2025-01-19 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 40A/0 | Unassigned |  | 2025-01-20 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 10/0 | Unassigned |  | 2025-01-21 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 30/10 | Unassigned |  | 2025-01-21 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 43/7 | Unassigned |  | 2025-01-21 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 23/0 | Unassigned |  | 2025-01-22 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 43/3 | Unassigned |  | 2025-01-23 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 39/8 | Unassigned |  | 2025-01-24 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 8/4 | Unassigned |  | 2025-01-24 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 43/0 | Unassigned |  | 2025-01-25 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 43/8 | Unassigned |  | 2025-01-25 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 15/1 | Unassigned |  | 2025-01-27 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 43/4 | Unassigned |  | 2025-01-28 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 31/0 | Unassigned |  | 2025-01-29 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 23A/0 | Unassigned |  | 2025-01-30 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 32/1 | Unassigned |  | 2025-01-31 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 39/9 | Unassigned |  | 2025-01-31 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 42A/0 | Unassigned |  | 2025-01-31 | 2025-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 31/2 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 43/6 | Unassigned |  | 2025-02-02 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 18/7 | Unassigned |  | 2025-02-04 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 32/2 | Unassigned |  | 2025-02-04 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 44/0 | Unassigned |  | 2025-02-04 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 43/1 | Unassigned |  | 2025-02-05 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 31/4 | Unassigned |  | 2025-02-07 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 43/2 | Unassigned |  | 2025-02-08 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 32/0 | Unassigned |  | 2025-02-09 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 43A/0 | Unassigned |  | 2025-02-09 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 31/5 | Unassigned |  | 2025-02-10 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 13/0 | Unassigned |  | 2025-02-11 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 39/10 | Unassigned |  | 2025-02-11 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 20/2 | Unassigned |  | 2025-02-12 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 8/11 | Unassigned |  | 2025-02-13 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 20/1 | Unassigned |  | 2025-02-16 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 21/5 | Unassigned |  | 2025-02-16 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 32/7 | Unassigned |  | 2025-02-17 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 13A/0 | Unassigned |  | 2025-02-18 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 32A/0 | Unassigned |  | 2025-02-18 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 9/6 | Unassigned |  | 2025-02-19 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 33/2 | Unassigned |  | 2025-02-20 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 21/4 | Unassigned |  | 2025-02-22 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 32A/1 | Unassigned |  | 2025-02-22 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 29/0 | Unassigned |  | 2025-02-23 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 39/11 | Unassigned |  | 2025-02-24 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 27/0 | Unassigned |  | 2025-02-25 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 9/9 | Unassigned |  | 2025-02-25 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 28/0 | Unassigned |  | 2025-02-26 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 9/7 | Unassigned |  | 2025-02-26 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 24/0 | Unassigned |  | 2025-02-27 | 2025-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 44/1 | Unassigned |  | 2025-03-01 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 26/0 | Unassigned |  | 2025-03-05 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 9/8 | Unassigned |  | 2025-03-05 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 15/0 | Unassigned |  | 2025-03-06 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 44/2 | Unassigned |  | 2025-03-06 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 25/0 | Unassigned |  | 2025-03-08 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 40/0 | Unassigned |  | 2025-03-08 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 44/4 | Unassigned |  | 2025-03-12 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 44/3 | Unassigned |  | 2025-03-13 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 5/0 | Unassigned |  | 2025-03-16 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 44/5 | Unassigned |  | 2025-03-17 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 2A/2 | Unassigned |  | 2025-03-23 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 3B/2 | Unassigned |  | 2025-03-23 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 5/1 | Unassigned |  | 2025-03-23 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 3B/1 | Unassigned |  | 2025-03-26 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 2A/3 | Unassigned |  | 2025-03-27 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 2A/4 | Unassigned |  | 2025-03-30 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 3B/0 | Unassigned |  | 2025-03-30 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 40/1 | Unassigned |  | 2025-03-30 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 5A/0 | Unassigned |  | 2025-04-01 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 3A/6 | Unassigned |  | 2025-04-03 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 2A/5 | Unassigned |  | 2025-04-05 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 32/5 | Unassigned |  | 2025-04-08 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 3A/1 | Unassigned |  | 2025-04-08 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 3A/5 | Unassigned |  | 2025-04-08 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 3A/4 | Unassigned |  | 2025-04-10 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 32/6 | Unassigned |  | 2025-04-11 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 35/3 | Unassigned |  | 2025-04-12 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 3A/3 | Unassigned |  | 2025-04-12 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 33/1 | Unassigned |  | 2025-04-14 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 35/2 | Unassigned |  | 2025-04-15 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 3A/2 | Unassigned |  | 2025-04-15 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 14/0 | Unassigned |  | 2025-04-16 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 33/0 | Unassigned |  | 2025-04-17 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 3A/0 | Unassigned |  | 2025-04-18 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 3B/3 | Unassigned |  | 2025-04-19 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 21/3 | Unassigned |  | 2025-04-22 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 2A/6 | Unassigned |  | 2025-04-23 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 21/2 | Unassigned |  | 2025-04-24 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 4/0 | Unassigned |  | 2025-04-25 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 8A/0 | Unassigned |  | 2025-04-25 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 21/1 | Unassigned |  | 2025-04-29 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 35/10 | Unassigned |  | 2025-05-02 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 9/0 | Unassigned |  | 2025-05-03 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 45/0 | Unassigned |  | 2025-05-05 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 46/0 | Unassigned |  | 2025-05-07 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 20/6 | Unassigned |  | 2025-05-09 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 20/5 | Unassigned |  | 2025-05-13 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 21/0 | Unassigned |  | 2025-05-13 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 20/4 | Unassigned |  | 2025-05-18 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 20/3 | Unassigned |  | 2025-05-22 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 19/0 | Unassigned |  | 2025-05-26 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 20/0 | Unassigned |  | 2025-06-02 | 2025-06 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 11/0 | Unassigned |  | 2025-06-08 | 2025-06 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 12/0 | Unassigned |  | 2025-06-14 | 2025-06 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 1/0 | Unassigned |  | 2025-06-27 | 2025-06 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 2A/1 | Unassigned |  | 2025-07-05 | 2025-07 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 2A/0 | Unassigned |  | 2025-07-14 | 2025-07 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 36B/0-N | Unassigned |  | 2026-01-23 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 36C/0-N | Unassigned |  | 2026-02-08 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 413 | TA413 |  | 37/0-N | Unassigned |  | 2026-03-05 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 413 - DPR - 2026-06-16.xlsx | Foundation
Mr. Arun Felbin | TA 414 | TA414 |  | 241/2 | Suraj Construction | 2024-05-15 | 2024-05-25 | 2024-05 | 11 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 241/0 | Suraj Construction | 2024-05-21 | 2024-05-30 | 2024-05 | 10 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 118/0 | Anya Infra | 2024-09-20 | 2024-10-31 | 2024-10 | 42 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 120/3 | Anya Infra | 2024-11-04 | 2024-11-12 | 2024-11 | 9 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 121/5 | Adhyey Brothers | 2024-11-02 | 2024-11-19 | 2024-11 | 18 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 120/2 | Anya Infra | 2024-11-09 | 2024-11-22 | 2024-11 | 14 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 121/4 | Adhyey Brothers | 2024-11-19 | 2024-11-29 | 2024-11 | 11 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 121/2 | Adhyey Brothers | 2024-12-01 | 2024-12-07 | 2024-12 | 7 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 183/1 | Khodiyarkrupa | 2025-11-23 | 2024-12-09 | 2024-12 |  | Invalid Negative Duration | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 119/0 | Himanshi Agency | 2024-12-03 | 2024-12-16 | 2024-12 | 14 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 121/3 | Adhya Enterprises | 2024-12-09 | 2024-12-21 | 2024-12 | 13 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 120/0 | Himanshi Agency | 2024-12-08 | 2024-12-22 | 2024-12 | 15 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 120/5 | APR Associates | 2024-11-30 | 2024-12-22 | 2024-12 | 23 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 244/6 | Unnati Construction | 2024-12-13 | 2024-12-23 | 2024-12 | 11 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 145/4 | Integer Infratech Pvt Ltd | 2024-12-11 | 2024-12-27 | 2024-12 | 17 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 249/1 | Neelkant Infra Project | 2024-12-19 | 2024-12-27 | 2024-12 | 9 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 119/2 | Himanshi Agency | 2024-12-11 | 2024-12-28 | 2024-12 | 18 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 119/3 | Himanshi Agency | 2024-12-21 | 2024-12-30 | 2024-12 | 10 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 121/6 | Arya Enterprises | 2024-12-17 | 2024-12-31 | 2024-12 | 15 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 249/0 | Unnati Construction | 2024-12-26 | 2025-01-02 | 2025-01 | 8 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 249/2 | Neelkant Infra Project | 2024-12-28 | 2025-01-03 | 2025-01 | 7 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 120/6 | APR Associates | 2024-12-05 | 2025-01-04 | 2025-01 | 31 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 126/3 | Tower Foundation | 2025-12-31 | 2025-01-08 | 2025-01 |  | Invalid Negative Duration | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 121/1 | Himanshi Agency | 2025-01-03 | 2025-01-10 | 2025-01 | 8 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 137/2 | Adhya Brother | 2024-12-27 | 2025-01-10 | 2025-01 | 15 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 121/7 | Arya Enterprises | 2024-12-24 | 2025-01-12 | 2025-01 | 20 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 145/3 | Integer Infratech Pvt Ltd | 2024-12-30 | 2025-01-13 | 2025-01 | 15 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 120/7 | Himanshi Agency | 2025-01-10 | 2025-01-14 | 2025-01 | 5 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 244/5 | Neelkant Infra Project | 2025-01-07 | 2025-01-16 | 2025-01 | 10 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 121/8 | Arya Enterprises | 2025-01-10 | 2025-01-20 | 2025-01 | 11 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 250/0 | Unnati Construction | 2025-01-07 | 2025-01-20 | 2025-01 | 14 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 252/3 | Neelkant Infra Project | 2025-01-17 | 2025-01-22 | 2025-01 | 6 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 136/1 | Himanshi Agency | 2025-01-19 | 2025-01-24 | 2025-01 | 6 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 145/2 | Integer Infratech Pvt Ltd | 2025-01-15 | 2025-01-26 | 2025-01 | 12 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 250A/2 | Unnati Construction | 2025-01-20 | 2025-01-28 | 2025-01 | 9 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 252/0 | Neelkant Infra Project | 2025-01-22 | 2025-01-31 | 2025-01 | 10 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 248/2 | Unnati Construction | 2025-01-29 | 2025-02-03 | 2025-02 | 6 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 121/10 | Arya Enterprises | 2025-01-28 | 2025-02-04 | 2025-02 | 8 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 141/4 | Himanshi Agency | 2025-01-27 | 2025-02-04 | 2025-02 | 9 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 241/4 | Unnati Construction | 2025-01-29 | 2025-02-04 | 2025-02 | 7 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 124/1 | Himanshi Agency | 2025-01-31 | 2025-02-06 | 2025-02 | 7 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 137/1 | Adhya Brother | 2025-01-15 | 2025-02-07 | 2025-02 | 24 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 141/3 | Himanshi Agency | 2025-01-27 | 2025-02-08 | 2025-02 | 13 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 145/7 | Integer Infratech Pvt Ltd | 2025-01-28 | 2025-02-08 | 2025-02 | 12 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 121/9 | Arya Enterprises | 2025-01-20 | 2025-02-11 | 2025-02 | 23 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 126/1 | Himanshi Agency | 2025-02-07 | 2025-02-13 | 2025-02 | 7 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 141/5 | Himanshi Agency | 2025-02-08 | 2025-02-13 | 2025-02 | 6 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 243/3 | Neelkant Infra Project | 2025-02-07 | 2025-02-13 | 2025-02 | 7 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 248/1 | Unnati Construction | 2025-02-03 | 2025-02-13 | 2025-02 | 11 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 137/0 | Adhya Brother | 2025-02-01 | 2025-02-14 | 2025-02 | 14 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 124/0 | Himanshi Agency | 2025-02-07 | 2025-02-19 | 2025-02 | 13 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 243/2 | Neelkant Infra Project | 2025-02-13 | 2025-02-21 | 2025-02 | 9 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 250/3 | Unnati Construction | 2025-02-14 | 2025-02-23 | 2025-02 | 10 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 126/2 | Himanshi Agency | 2026-02-16 | 2025-02-26 | 2025-02 |  | Invalid Negative Duration | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 148/0 | Himanshi Agency | 2025-02-07 | 2025-02-27 | 2025-02 | 21 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 126/0 | Himanshi Agency | 2026-02-18 | 2025-02-28 | 2025-02 |  | Invalid Negative Duration | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 244/1 | Neelkant Infra Project | 2025-02-23 | 2025-03-07 | 2025-03 | 13 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 132/0 | Adhya Brother | 2025-03-02 | 2025-03-08 | 2025-03 | 7 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 117/1 | Himanshi Agency | 2025-03-03 | 2025-03-13 | 2025-03 | 11 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 117/2 | Himanshi Agency | 2025-03-03 | 2025-03-17 | 2025-03 | 15 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 251/0 | Neelkant Infra Project | 2025-03-11 | 2025-03-20 | 2025-03 | 10 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 171/0 | Himanshi Agency | 2025-03-13 | 2025-03-22 | 2025-03 | 10 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 121/0 | Himanshi Agency | 2025-03-06 | 2025-03-23 | 2025-03 | 18 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 180/3 | Unnati Construction | 2025-03-11 | 2025-03-23 | 2025-03 | 13 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 172/0 | Himanshi Agency | 2025-03-07 | 2025-03-26 | 2025-03 | 20 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 180/4 | Jyoti Construction | 2025-03-01 | 2025-03-27 | 2025-03 | 27 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 172/1 | Himanshi Agency | 2025-03-24 | 2025-04-01 | 2025-04 | 9 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 179/3 | Neelkant Infra Project | 2025-03-11 | 2025-04-01 | 2025-04 | 22 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 165/7 | Himanshi Agency | 2025-03-24 | 2025-04-05 | 2025-04 | 13 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 180/2 | Unnati Construction | 2025-03-11 | 2025-04-05 | 2025-04 | 26 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 180/5 | Jyoti Construction | 2025-03-11 | 2025-04-06 | 2025-04 | 27 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 180/7 | Jyoti Construction | 2025-04-03 | 2025-04-08 | 2025-04 | 6 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 179/1 | Neelkant Infra Project | 2025-04-02 | 2025-04-09 | 2025-04 | 8 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 132/1 | Adhya Brother | 2025-03-15 | 2025-04-10 | 2025-04 | 27 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 174/4 | Himanshi Agency | 2025-04-01 | 2025-04-10 | 2025-04 | 10 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 174/6 | Sai guru Construction | 2025-03-19 | 2025-04-11 | 2025-04 | 24 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 174/5 | Himanshi Agency | 2025-04-06 | 2025-04-15 | 2025-04 | 10 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 174/1 | Himanshi Agency | 2025-04-10 | 2025-04-16 | 2025-04 | 7 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 176/1 | Unnati Construction | 2025-04-11 | 2025-04-18 | 2025-04 | 8 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 175/0 | Sai guru Construction | 2025-04-13 | 2025-04-23 | 2025-04 | 11 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 177/0 | Jyoti Construction | 2025-04-11 | 2025-04-23 | 2025-04 | 13 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 176/2 | Unnati Construction | 2025-04-20 | 2025-04-27 | 2025-04 | 8 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 148/4 | Himanshi Agency | 2025-04-23 | 2025-04-28 | 2025-04 | 6 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 178/3 | Jyoti Construction | 2025-04-24 | 2025-04-28 | 2025-04 | 5 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 165/5 | Himanshi Agency | 2025-03-31 | 2025-05-03 | 2025-05 | 34 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 148/2 | Sai guru Construction | 2025-05-05 | 2025-05-12 | 2025-05 | 8 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 180/1 | Jyoti Construction | 2025-05-08 | 2025-05-13 | 2025-05 | 6 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 165/2 | Himanshi Agency | 2025-05-02 | 2025-05-15 | 2025-05 | 14 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 252/5 | Unnati Construction | 2025-05-02 | 2025-05-17 | 2025-05 | 16 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 243/0 | Sai guru Construction | 2025-05-15 | 2025-06-01 | 2025-06 | 18 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 256/0 | Unnati Construction | 2025-05-19 | 2025-06-14 | 2025-06 | 27 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 246/0 | Khodiyarkrupa | 2025-08-04 | 2025-08-23 | 2025-08 | 20 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 250A/1 | Khodiyarkrupa | 2025-08-27 | 2025-09-09 | 2025-09 | 14 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 131/2 | Murugan | 2025-08-05 | 2025-09-15 | 2025-09 | 42 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 241/3 | Saiguru Construction | 2025-08-14 | 2025-09-20 | 2025-09 | 38 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 178/0 | Khodiyarkrupa | 2025-09-23 | 2025-10-14 | 2025-10 | 22 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 120/1 | Jyoti Construction | 2025-08-11 | 2025-10-16 | 2025-10 | 67 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 224/1 | Himanshi Agency | 2025-10-12 | 2025-10-19 | 2025-10 | 8 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 119/1 | Jyoti Construction | 2025-10-12 | 2025-10-20 | 2025-10 | 9 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 224/2 | Khodiyarkrupa | 2025-10-15 | 2025-10-20 | 2025-10 | 6 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 225/0 | Khodiyarkrupa | 2025-10-15 | 2025-10-22 | 2025-10 | 8 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 120/4 | Jyoti Construction | 2025-10-15 | 2025-10-26 | 2025-10 | 12 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 223/3 | Himanshi Agency | 2025-10-16 | 2025-10-27 | 2025-10 | 12 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 221/0 | Khodiyarkrupa | 2025-10-21 | 2025-11-05 | 2025-11 | 16 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 224/0 | Himanshi Agency | 2025-10-26 | 2025-11-08 | 2025-11 | 14 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 138/0 | Jyoti Construction | 2025-11-03 | 2025-11-13 | 2025-11 | 11 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 220/1 | Murugan Gang | 2025-10-26 | 2025-11-14 | 2025-11 | 20 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 223/1 | Tower Foundation | 2025-10-26 | 2025-11-14 | 2025-11 | 20 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 222/0 | Khodiyarkrupa-1 | 2025-11-01 | 2025-11-15 | 2025-11 | 15 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 185/0 | Khodiyarkrupa-2 | 2025-11-03 | 2025-11-16 | 2025-11 | 14 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 141/6 | Himanshi Agency | 2025-11-10 | 2025-11-17 | 2025-11 | 8 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 220/0 | BLG Construction | 2025-11-04 | 2025-11-17 | 2025-11 | 14 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 223/2 | Tower Foundation | 2025-10-26 | 2025-11-18 | 2025-11 | 24 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 219/1 | BLG Construction | 2025-11-18 | 2025-11-21 | 2025-11 | 4 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 223/0 | Sai guru Construction | 2025-11-12 | 2025-11-22 | 2025-11 | 11 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 218/0 | Murugan Gang | 2025-11-06 | 2025-11-23 | 2025-11 | 18 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 144/0 | Jyoti Construction | 2025-11-04 | 2025-11-24 | 2025-11 | 21 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 196/0 | Shivkripa | 2025-11-11 | 2025-11-24 | 2025-11 | 14 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 142/0 | Himanshi Agency | 2025-11-11 | 2025-11-25 | 2025-11 | 15 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 225/1 | Saiguru Construction | 2025-11-22 | 2025-11-25 | 2025-11 | 4 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 125/1 | Himanshi Agency | 2025-10-31 | 2025-11-26 | 2025-11 | 27 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 187/0 | Khodiyarkrupa-2 | 2025-11-16 | 2025-11-26 | 2025-11 | 11 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 136/0 | Jyoti Construction | 2025-11-05 | 2025-11-27 | 2025-11 | 23 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 214/2 | Tuuasta | 2025-11-13 | 2025-11-27 | 2025-11 | 15 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 225/4 | Saiguru Construction | 2025-11-25 | 2025-11-29 | 2025-11 | 5 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 148/5 | Khodiyar Trader | 2025-11-19 | 2025-11-30 | 2025-11 | 12 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 215/0 | Tower Foundation | 2025-11-20 | 2025-11-30 | 2025-11 | 11 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 186/0 | Khodiyarkrupa-2 | 2025-11-11 | 2025-12-01 | 2025-12 | 21 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 194/1 | Khodiyarkrupa | 2025-11-24 | 2025-12-02 | 2025-12 | 9 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 176/0 | Jayesh Electrical | 2025-11-20 | 2025-12-03 | 2025-12 | 14 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 214/5 | Unnati Construction | 2025-11-22 | 2025-12-03 | 2025-12 | 12 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 214/7 | BLG Construction | 2025-11-24 | 2025-12-04 | 2025-12 | 11 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 143/0 | Himanshi Agency | 2025-11-23 | 2025-12-05 | 2025-12 | 13 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 184/0 | Khodiyarkrupa | 2025-11-26 | 2025-12-05 | 2025-12 | 10 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 214/4 | Murugan Gang | 2025-11-26 | 2025-12-05 | 2025-12 | 10 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 244/2 | Saiguru Construction | 2025-11-30 | 2025-12-06 | 2025-12 | 7 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 145/5 | Jyoti Construction | 2025-11-27 | 2025-12-07 | 2025-12 | 11 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 225/3 | Velu Construction | 2025-12-05 | 2025-12-10 | 2025-12 | 6 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 139/0 | Himanshi Agency | 2025-11-27 | 2025-12-11 | 2025-12 | 15 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 148/3 | Khodiyar Trader | 2025-12-01 | 2025-12-11 | 2025-12 | 11 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 183/0 | Jayesh Electrical | 2025-11-30 | 2025-12-11 | 2025-12 | 12 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 217/4 | Selva Murugan | 2025-12-05 | 2025-12-11 | 2025-12 | 7 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 250/2 | Unnati Construction | 2025-12-05 | 2025-12-11 | 2025-12 | 7 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 127/2 | Tower Foundation | 2025-12-01 | 2025-12-12 | 2025-12 | 12 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 183/2 | Khodiyar Kripa Enterprise | 2025-12-05 | 2025-12-12 | 2025-12 | 8 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 214/3 | Twasta | 2025-11-27 | 2025-12-12 | 2025-12 | 16 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 214/6 | BLG Construction | 2025-12-05 | 2025-12-12 | 2025-12 | 8 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 249/3 | Saiguru Construction | 2025-12-10 | 2025-12-13 | 2025-12 | 4 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 182/0 | Dev Construction | 2025-11-30 | 2025-12-14 | 2025-12 | 15 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 225/2 | Velu Construction | 2025-12-11 | 2025-12-14 | 2025-12 | 4 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 141/1 | Himanshi Agency | 2025-12-06 | 2025-12-15 | 2025-12 | 10 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 161/0 | Kasta Bhanjan | 2025-11-26 | 2025-12-16 | 2025-12 | 21 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 243/1 | Saiguru Construction | 2025-12-08 | 2025-12-16 | 2025-12 | 9 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 189/1 | Khodiyarkrupa | 2025-12-12 | 2025-12-17 | 2025-12 | 6 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 145/6 | Jyoti Construction | 2025-12-05 | 2025-12-18 | 2025-12 | 14 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 141/2 | Himanshi Agency | 2025-12-06 | 2025-12-19 | 2025-12 | 14 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 175/1 | Deep Power | 2025-12-04 | 2025-12-19 | 2025-12 | 16 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 217/2 | Unassigned | 2025-12-15 | 2025-12-19 | 2025-12 | 5 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 217/3 | Krishna Construction | 2025-12-05 | 2025-12-19 | 2025-12 | 15 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 166/0 | Jyoti Construction | 2025-12-08 | 2025-12-20 | 2025-12 | 13 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 165/6 | Jyoti | 2025-12-20 | 2025-12-23 | 2025-12 | 4 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 180/6 | Dev Construction | 2025-12-12 | 2025-12-23 | 2025-12 | 12 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 191/1 | Khodiyar 1 | 2025-12-13 | 2025-12-23 | 2025-12 | 11 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 199/1 | Veluu | 2025-12-13 | 2025-12-23 | 2025-12 | 11 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 257/0 | Unassigned | 2025-12-16 | 2025-12-23 | 2025-12 | 8 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 216/1 | Unassigned | 2025-12-16 | 2025-12-24 | 2025-12 | 9 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 254/1 | Unassigned | 2025-12-13 | 2025-12-24 | 2025-12 | 12 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 127/0 | A P Developers | 2025-12-08 | 2025-12-25 | 2025-12 | 18 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 148/1 | Khodiyar Traders | 2025-12-18 | 2025-12-25 | 2025-12 | 8 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 190/0 | Shiv Kripa Infra | 2025-12-09 | 2025-12-25 | 2025-12 | 17 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 196/1 | BLG Construction | 2025-12-19 | 2025-12-25 | 2025-12 | 7 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 197/0 | Deep Power 1 | 2025-12-13 | 2025-12-26 | 2025-12 | 14 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 170/0 | Jyoti | 2025-12-17 | 2025-12-27 | 2025-12 | 11 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 252/2 | Unassigned | 2025-12-19 | 2025-12-27 | 2025-12 | 9 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 197/2 | Deep Power 2 | 2025-12-13 | 2025-12-29 | 2025-12 | 17 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 196/2 | BLG Construction | 2025-12-19 | 2025-12-30 | 2025-12 | 12 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 252/1 | Saiguru 2 | 2025-12-19 | 2025-12-30 | 2025-12 | 12 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 128/0 | Tower Foundation | 2025-12-04 | 2025-12-31 | 2025-12 | 28 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 179/0 | Dev Construction | 2025-12-23 | 2025-12-31 | 2025-12 | 9 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 183/3 | Twaasta | 2025-12-13 | 2025-12-31 | 2025-12 | 19 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 216/2 | Murgun | 2025-12-25 | 2025-12-31 | 2025-12 | 7 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 241/1 | Suraj Construction | 2024-05-28 | 2025-12-31 | 2025-12 | 583 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 141/0 | Himanshi 2 | 2025-12-21 | 2026-01-03 | 2026-01 | 14 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 149/0 | Kasta Bhanjan | 2025-12-15 | 2026-01-03 | 2026-01 | 20 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 167/0 | Jyoti 1 | 2025-12-20 | 2026-01-04 | 2026-01 | 16 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 127/1 | Tower Foundation | 2025-12-17 | 2026-01-05 | 2026-01 | 20 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 139/1 | Himanshi | 2025-12-20 | 2026-01-05 | 2026-01 | 17 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 210/0 | Velu | 2025-12-13 | 2026-01-05 | 2026-01 | 24 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 192/0 | Khodiyarkrupa | 2025-12-26 | 2026-01-06 | 2026-01 | 12 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 178/2 | Dev Contruction | 2025-12-23 | 2026-01-07 | 2026-01 | 16 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 244/0 | Saiguru 1 | 2025-12-05 | 2026-01-09 | 2026-01 | 36 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 211/3 | Deep Power 1 | 2026-01-01 | 2026-01-10 | 2026-01 | 10 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 255/0 | Unnati Construction | 2025-12-20 | 2026-01-10 | 2026-01 | 22 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 216/3 | Krishna Construction | 2025-12-25 | 2026-01-12 | 2026-01 | 19 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 132/3 | Himanshi | 2026-01-06 | 2026-01-13 | 2026-01 | 8 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 162/0 | Jyoti 3 | 2025-12-29 | 2026-01-13 | 2026-01 | 16 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 199/2 | Deep Power | 2025-12-27 | 2026-01-13 | 2026-01 | 18 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 211/1 | Unassigned | 2026-01-08 | 2026-01-13 | 2026-01 | 6 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 230/0 | Om Enterprise | 2026-01-04 | 2026-01-13 | 2026-01 | 10 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 245/0 | Saiguru 2 | 2026-01-03 | 2026-01-13 | 2026-01 | 11 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 125/2 | Tower Foundation | 2026-01-06 | 2026-01-15 | 2026-01 | 10 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 160/0 | Jyoti | 2026-01-06 | 2026-01-15 | 2026-01 | 10 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 191/0 | Khodiyarkrupa | 2025-12-26 | 2026-01-15 | 2026-01 | 21 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 178/1 | Unassigned | 2026-01-09 | 2026-01-16 | 2026-01 | 8 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 199/0 | BLG Construction | 2025-12-28 | 2026-01-16 | 2026-01 | 20 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 245/1 | Saiguru 2 | 2026-01-03 | 2026-01-16 | 2026-01 | 14 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 194/0 | Shiv krupa Infra | 2025-12-04 | 2026-01-17 | 2026-01 | 45 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 133/0 | Himanshi | 2026-01-06 | 2026-01-20 | 2026-01 | 15 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 174/3 | Jyoti 3 | 2026-01-13 | 2026-01-20 | 2026-01 | 8 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 227/0 | Om Enterprise | 2026-01-04 | 2026-01-21 | 2026-01 | 18 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 250A/0 | Unnati Construction | 2025-12-12 | 2026-01-21 | 2026-01 | 41 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 165/4 | Jyoti | 2026-01-19 | 2026-01-22 | 2026-01 | 4 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 211/4 | Velu | 2026-01-15 | 2026-01-22 | 2026-01 | 8 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 217/5 | Krishna Construction | 2026-01-12 | 2026-01-22 | 2026-01 | 11 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 140/0 | Himanshi 1 | 2025-12-22 | 2026-01-23 | 2026-01 | 33 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 193/0 | Khodiyarkrupa | 2025-12-20 | 2026-01-23 | 2026-01 | 35 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 198/0 | Deep Power 2 | 2025-12-13 | 2026-01-23 | 2026-01 | 42 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 216/0 | Murgun | 2025-12-15 | 2026-01-23 | 2026-01 | 40 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 244/3 | AP Developers | 2025-12-26 | 2026-01-23 | 2026-01 | 29 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 197/1 | BLG | 2026-01-17 | 2026-01-24 | 2026-01 | 8 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 244/4 | AP Developers | 2025-12-27 | 2026-01-25 | 2026-01 | 30 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 133/1 | Himanshi | 2026-01-19 | 2026-01-26 | 2026-01 | 8 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 125/0 | Tower Foundation | 2026-01-16 | 2026-01-27 | 2026-01 | 12 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 226/3 | Unassigned | 2026-01-22 | 2026-01-27 | 2026-01 | 6 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 233/0 | Saiguru | 2026-01-19 | 2026-01-27 | 2026-01 | 9 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 211/2 | BLG | 2026-01-13 | 2026-01-28 | 2026-01 | 16 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 236/0 | Unassigned | 2026-01-21 | 2026-01-28 | 2026-01 | 8 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 139/3 | Himanshi | 2025-12-16 | 2026-01-29 | 2026-01 | 45 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 168/0 | Jyoti | 2026-01-20 | 2026-01-29 | 2026-01 | 10 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 188/0 | Shivkrupa | 2026-01-16 | 2026-01-29 | 2026-01 | 14 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 227/1 | Om Construction | 2026-01-04 | 2026-01-29 | 2026-01 | 26 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 139/2 | Jyoti Construction 2 | 2025-10-26 | 2026-01-30 | 2026-01 | 97 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 209/2 | BLG (197/1) | 2026-01-18 | 2026-01-30 | 2026-01 | 13 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 235/2 | Unassigned | 2026-01-19 | 2026-01-30 | 2026-01 | 12 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 133/2 | Himanshi | 2026-01-06 | 2026-01-31 | 2026-01 | 26 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 211/5 | Dev Construction | 2026-01-18 | 2026-01-31 | 2026-01 | 14 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 211/0 | Deep Power | 2026-01-01 | 2026-02-01 | 2026-02 | 32 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 238/0 | Krishna Construction | 2026-01-20 | 2026-02-01 | 2026-02 | 13 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 174/2 | Jyoti | 2025-12-18 | 2026-02-02 | 2026-02 | 47 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 250/1 | Saiguru 1 | 2025-12-20 | 2026-02-02 | 2026-02 | 45 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 252/4 | Saiguru | 2026-01-26 | 2026-02-02 | 2026-02 | 8 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 240/0 | Unassigned | 2026-01-20 | 2026-02-03 | 2026-02 | 15 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 124/3 | Tower Foundation | 2026-02-01 | 2026-02-05 | 2026-02 | 5 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 213/0 | Velu (213/0) | 2026-01-18 | 2026-02-05 | 2026-02 | 19 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 235/0 | Unnati | 2026-01-21 | 2026-02-07 | 2026-02 | 18 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 256/1 | Unassigned | 2025-12-09 | 2026-02-07 | 2026-02 | 61 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 228/0 | Unassigned | 2026-02-01 | 2026-02-10 | 2026-02 | 10 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 134/0 | Himanshi | 2026-01-30 | 2026-02-11 | 2026-02 | 13 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 124/2 | Tower Foundation | 2026-02-01 | 2026-02-12 | 2026-02 | 12 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 235/3 | Unnati Construction | 2024-08-31 | 2026-02-13 | 2026-02 | 532 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 242/0 | Saiguru | 2026-02-05 | 2026-02-13 | 2026-02 | 9 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 214/0 | Unassigned | 2026-02-05 | 2026-02-16 | 2026-02 | 12 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 217/1 | Dev Construction | 2026-02-13 | 2026-02-16 | 2026-02 | 4 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 237/0 | Krishna | 2026-02-05 | 2026-02-16 | 2026-02 | 12 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 147/0 | Himanshi | 2026-01-29 | 2026-02-17 | 2026-02 | 20 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 228/1 | BLG | 2026-02-10 | 2026-02-17 | 2026-02 | 8 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 174/0 | Jyoti 2 | 2025-12-18 | 2026-02-18 | 2026-02 | 63 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 235/1 | Unnati | 2026-02-07 | 2026-02-19 | 2026-02 | 13 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 232/4 | Deep Power | 2026-01-19 | 2026-02-20 | 2026-02 | 33 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 240/1 | Krishna | 2026-02-16 | 2026-02-22 | 2026-02 | 7 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 133/4 | Himanshi | 2026-02-11 | 2026-02-23 | 2026-02 | 13 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 214/1 | Khodiyar | 2026-02-15 | 2026-02-23 | 2026-02 | 9 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 217/0 | BLG | 2026-02-13 | 2026-02-24 | 2026-02 | 12 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 173/0 | Unassigned | 2025-12-18 | 2026-02-27 | 2026-02 | 72 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 248/0 | Saiguru | 2026-02-13 | 2026-02-27 | 2026-02 | 15 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 219/0 | Dev Construction | 2026-02-17 | 2026-02-28 | 2026-02 | 12 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 239/0 | Unnati | 2026-02-19 | 2026-03-02 | 2026-03 | 12 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 209/0 | Shivkrupa | 2026-02-17 | 2026-03-03 | 2026-03 | 15 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 209/1 | khodiyar | 2026-02-17 | 2026-03-03 | 2026-03 | 15 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 163/0 | Tower Foundation | 2026-01-26 | 2026-03-04 | 2026-03 | 38 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 226/1 | Saiguru | 2026-02-21 | 2026-03-08 | 2026-03 | 16 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 226/2 | Saiguru-2 | 2026-03-01 | 2026-03-09 | 2026-03 | 9 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 232/0 | Krishna | 2026-02-07 | 2026-03-11 | 2026-03 | 33 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 239/1 | Unnati | 2026-03-01 | 2026-03-12 | 2026-03 | 12 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 133/3 | Himanshi | 2026-02-23 | 2026-03-15 | 2026-03 | 21 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 207/0 | Dev Construction | 2026-02-19 | 2026-03-15 | 2026-03 | 25 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 227/2 | BLG | 2026-03-11 | 2026-03-16 | 2026-03 | 6 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 231/0 | Krishna | 2026-03-12 | 2026-03-16 | 2026-03 | 5 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 145/0 | Tower Foundation | 2026-03-03 | 2026-03-18 | 2026-03 | 16 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 225/7 | Krishna | 2026-03-16 | 2026-03-22 | 2026-03 | 7 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 251/1 | Unnati | 2026-03-13 | 2026-03-22 | 2026-03 | 10 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 121/11 | Jyoti | 2026-03-16 | 2026-03-24 | 2026-03 | 9 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 150/1 | Tower Foundation | 2026-03-16 | 2026-03-24 | 2026-03 | 9 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 225/5 | BLG | 2026-03-18 | 2026-03-24 | 2026-03 | 7 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 234/0 | Saiguru | 2026-03-11 | 2026-03-24 | 2026-03 | 14 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 179/2 | Shivkrupa | 2026-03-19 | 2026-03-27 | 2026-03 | 9 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 226/0 | Krishna | 2026-03-22 | 2026-03-28 | 2026-03 | 7 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 230/1 | Saiguru | 2026-03-23 | 2026-03-29 | 2026-03 | 7 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 255/1 | Unnati Construction | 2026-02-25 | 2026-03-29 | 2026-03 | 33 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 232/2 | Sai guru Construction | 2026-03-16 | 2026-03-31 | 2026-03 | 16 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 180/0 | Khodiyarkripa | 2026-03-16 | 2026-04-05 | 2026-04 | 21 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 156/0 | Jyoti 2 | 2026-03-25 | 2026-04-06 | 2026-04 | 13 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 150/0 | Tower Foundation | 2026-03-26 | 2026-04-12 | 2026-04 | 18 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 195/0 | Khodiyarkripa | 2026-04-05 | 2026-04-12 | 2026-04 | 8 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 131/0 | Jyoti | 2026-03-13 | 2026-04-16 | 2026-04 | 35 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 155/0 | Jyoti 2 | 2026-04-05 | 2026-04-18 | 2026-04 | 14 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 230A/0 | Sai guru Construction | 2026-03-26 | 2026-04-18 | 2026-04 | 24 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 200/0 | Khodiyar Krupa | 2026-04-01 | 2026-04-19 | 2026-04 | 19 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 131/1 | Jyoti 1 | 2026-04-14 | 2026-04-21 | 2026-04 | 8 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 151/0 | Tower Founadation | 2026-04-09 | 2026-04-21 | 2026-04 | 13 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 156/1 | Tower Foundation | 2026-04-05 | 2026-04-24 | 2026-04 | 20 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 153/1 | Jyoti 1 | 2026-04-21 | 2026-04-26 | 2026-04 | 6 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 159/0 | Jyoti Const | 2026-04-05 | 2026-04-28 | 2026-04 | 24 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 189/0 | Khodiyarkrupa | 2026-01-18 | 2026-04-28 | 2026-04 | 101 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 151A/0 | Tower Founadation | 2026-04-21 | 2026-05-01 | 2026-05 | 11 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 164/0 | Himanshi | 2026-04-12 | 2026-05-03 | 2026-05 | 22 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 235/4 | Sai guru Construction | 2026-04-23 | 2026-05-05 | 2026-05 | 13 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 169/0 | Jyoti Contruction | 2026-04-26 | 2026-05-06 | 2026-05 | 11 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 165/0 | Himanshi | 2026-04-12 | 2026-05-09 | 2026-05 | 28 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 232/3 | Saiguru | 2026-04-05 | 2026-05-09 | 2026-05 | 35 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 129/0 | KND | 2026-01-23 | 2026-05-11 | 2026-05 | 109 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 206/0 | Shivkrupa | 2026-04-27 | 2026-05-11 | 2026-05 | 15 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 145/1 | jyoti const 2 | 2026-02-14 | 2026-05-16 | 2026-05 | 92 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 206/1 | Shivkrupa | 2026-05-02 | 2026-05-17 | 2026-05 | 16 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 153A/0 | Tower Foundation | 2026-05-13 | 2026-05-20 | 2026-05 | 8 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 201/0 | Khodiyar | 2026-05-09 | 2026-05-20 | 2026-05 | 12 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 229B/0 | jyoti const 2 | 2026-04-17 | 2026-05-22 | 2026-05 | 36 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 229A/0 | Arya Implex | 2026-04-21 | 2026-05-28 | 2026-05 | 38 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 229/0 | Himanshi Agency | 2026-05-14 | 2026-05-31 | 2026-05 | 18 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 154/0 | Jyoti 1 | 2026-05-23 | 2026-06-01 | 2026-06 | 10 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 212/0 | Khodiyar | 2026-01-16 | 2026-06-01 | 2026-06 | 137 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 254/0 | Jyoti 2 | 2026-05-22 | 2026-06-06 | 2026-06 | 16 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 132/2 | Jyoti 3 | 2026-05-23 | 2026-06-07 | 2026-06 | 16 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 208/0 | Shivkrupa | 2026-05-29 | 2026-06-08 | 2026-06 | 11 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 225/6 | Himanshi | 2026-04-27 | 2026-06-08 | 2026-06 | 43 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 130/0 | Harshvi | 2025-05-10 | 2026-06-12 | 2026-06 | 399 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 152/0 | Jyoti 3 | 2026-06-06 | 2026-06-12 | 2026-06 | 7 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 414 | TA414 |  | 253/0 | Jyoti 2 | 2026-05-22 | 2026-06-15 | 2026-06 | 25 | Valid | detail | detail_date | TA 414 - DPR - 2026-06-17.xlsx | FDN
Mr. Arun Felbin | TA 416 | TA416 |  | 2/8 | Sumit Constrcution | 2024-04-24 | 2024-05-06 | 2024-05 | 13 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 2/7 | Sumit Constrcution | 2024-05-01 | 2024-05-10 | 2024-05 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 2/6 | Sumit Constrcution | 2024-05-09 | 2024-05-14 | 2024-05 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 2/5 | Sumit Constrcution | 2024-05-13 | 2024-05-18 | 2024-05 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 2/4 | Sumit Constrcution | 2024-05-16 | 2024-05-21 | 2024-05 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 2/3 | Sumit Constrcution | 2024-05-22 | 2024-05-28 | 2024-05 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 17/4 | Sumit Constrcution | 2024-05-31 | 2024-06-03 | 2024-06 | 4 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 39/10 | Dharamdas Contractor | 2024-05-28 | 2024-06-04 | 2024-06 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 17/5 | Sumit Constrcution | 2024-05-31 | 2024-06-06 | 2024-06 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 39/8 | Dharamdas Contractor | 2024-06-04 | 2024-06-08 | 2024-06 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 17/3 | Sumit Constrcution | 2024-06-04 | 2024-06-09 | 2024-06 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 17/6 | Sumit Constrcution | 2024-06-07 | 2024-06-11 | 2024-06 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 6/2 | Khalil Const. | 2024-06-06 | 2024-06-12 | 2024-06 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 39/9 | Dharamdas Contractor | 2024-06-08 | 2024-06-13 | 2024-06 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 17/7 | Sumit Constrcution | 2024-06-10 | 2024-06-14 | 2024-06 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 17/8 | Sumit Constrcution | 2024-06-13 | 2024-06-17 | 2024-06 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 39/7 | Dharamdas Contractor | 2024-06-12 | 2024-06-19 | 2024-06 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 17/1 | Sumit Constrcution | 2024-06-13 | 2024-06-20 | 2024-06 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 20/6 | Khalil Const. | 2024-06-13 | 2024-06-22 | 2024-06 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 39/1 | Anshika con. | 2024-06-13 | 2024-06-23 | 2024-06 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 39/6 | Dharamdas Contractor | 2024-06-20 | 2024-06-25 | 2024-06 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 20/7 | Khalil Const. | 2024-06-21 | 2024-06-27 | 2024-06 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 38/11 | Anshika con. | 2024-06-22 | 2024-06-30 | 2024-06 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 38/1 | Anshika con. | 2024-07-01 | 2024-07-11 | 2024-07 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 20/12 | Jay Sri Ram | 2024-07-08 | 2024-07-15 | 2024-07 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 38/2 | Anshika con. | 2024-07-11 | 2024-07-18 | 2024-07 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 14/5 | SSR engineering | 2024-07-13 | 2024-07-20 | 2024-07 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 19/11 | K R Associates | 2024-07-12 | 2024-07-23 | 2024-07 | 12 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 38/3 | Anshika con. | 2024-07-15 | 2024-07-25 | 2024-07 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 14/6 | SSR engineering | 2024-07-22 | 2024-07-28 | 2024-07 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 20/8 | VH Rajpoot cont. | 2024-07-20 | 2024-07-29 | 2024-07 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 19/8 | Jay Sri Ram | 2024-07-20 | 2024-07-30 | 2024-07 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 38/4 | Anshika con. | 2024-07-20 | 2024-07-31 | 2024-07 | 12 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 20/9 | VH Rajpoot cont. | 2024-07-30 | 2024-08-03 | 2024-08 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 19/9 | K R Associates | 2024-07-28 | 2024-08-04 | 2024-08 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 36/12 | Anshika con. | 2025-08-01 | 2024-08-08 | 2024-08 |  | Invalid Negative Duration | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 14/4 | SSR engineering | 2024-07-28 | 2024-08-09 | 2024-08 | 13 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 20/5 | VH Rajpoot cont. | 2024-08-05 | 2024-08-10 | 2024-08 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 36/11 | Anshika con. | 2024-08-08 | 2024-08-14 | 2024-08 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 23/3 | VH Rajpoot cont. | 2024-08-12 | 2024-08-18 | 2024-08 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 14/3 | SSR engineering | 2024-08-10 | 2024-08-21 | 2024-08 | 12 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 19/12 | K R Associates | 2024-08-12 | 2024-08-24 | 2024-08 | 13 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 14/7 | SSR engineering | 2024-08-24 | 2024-08-30 | 2024-08 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 12/9 | VED ENTTERPRISE | 2024-08-16 | 2024-08-31 | 2024-08 | 16 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 23/4 | VH Rajpoot cont. | 2024-08-23 | 2024-08-31 | 2024-08 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 36/3 | J M Enterprise | 2024-08-23 | 2024-08-31 | 2024-08 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 19/3 | Garg Construction | 2024-08-24 | 2024-09-05 | 2024-09 | 13 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 12/4 | SSR engineering | 2024-09-01 | 2024-09-08 | 2024-09 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 38/8 | A V I ENTERPRISE | 2024-08-24 | 2024-09-08 | 2024-09 | 16 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 39/4 | Dharamdas Contractor | 2024-08-29 | 2024-09-08 | 2024-09 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 45/3 | Vinayak Enterprise | 2024-08-24 | 2024-09-08 | 2024-09 | 16 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 12/8 | VED ENTTERPRISE | 2024-09-01 | 2024-09-09 | 2024-09 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 36/7 | SAIFI CON. | 2024-08-24 | 2024-09-09 | 2024-09 | 17 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 23/5 | VH Rajpoot cont. | 2024-09-08 | 2024-09-11 | 2024-09 | 4 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 50/1 | Vishal construction | 2024-08-24 | 2024-09-11 | 2024-09 | 19 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 2/8 | Dewi Construction(Girendra) | 2024-09-01 | 2024-09-16 | 2024-09 | 16 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 23/2 | VH Rajpoot cont. | 2024-09-11 | 2024-09-20 | 2024-09 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 36/6 | SAIFI CON. | 2024-08-24 | 2024-09-20 | 2024-09 | 28 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 41/1 | Dharamdas Contractor | 2024-09-09 | 2024-09-20 | 2024-09 | 12 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 19/2 | Shree Krishna | 2024-08-24 | 2024-09-22 | 2024-09 | 30 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 20/1 | K R Associates | 2024-08-30 | 2024-09-22 | 2024-09 | 24 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 30/3 | Garg Construction | 2024-09-08 | 2024-09-22 | 2024-09 | 15 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 12/2 | SSR engineering | 2024-09-08 | 2024-09-24 | 2024-09 | 17 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 30/6 | Laxmi Const. | 2024-09-19 | 2024-09-24 | 2024-09 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 36/9 | SAIFI CON. | 2024-09-19 | 2024-09-24 | 2024-09 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 25/1 | VH Rajpoot cont. | 2024-09-22 | 2024-09-26 | 2024-09 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 35/2 | A V I ENTERPRISE | 2024-09-19 | 2024-09-26 | 2024-09 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 36/5 | J M Enterprise | 2024-09-20 | 2024-09-26 | 2024-09 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 41/2 | Dharamdas Contractor | 2024-09-19 | 2024-09-26 | 2024-09 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 2/4 | Dewi Construction(Girendra) | 2024-09-16 | 2024-09-29 | 2024-09 | 14 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 45/2 | Vinayak Enterprise | 2024-09-09 | 2024-09-29 | 2024-09 | 21 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 12/1 | SSR engineering | 2024-09-25 | 2024-09-30 | 2024-09 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 12/6 | VED ENTTERPRISE | 2024-09-23 | 2024-09-30 | 2024-09 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 19/1 | MALLIK CON | 2024-08-24 | 2024-09-30 | 2024-09 | 38 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 23/1 | VH Rajpoot cont. | 2024-09-26 | 2024-09-30 | 2024-09 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 30/4 | Garg Construction | 2024-09-22 | 2024-09-30 | 2024-09 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 36/10 | J M Enterprise | 2024-09-09 | 2024-09-30 | 2024-09 | 22 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 35/1 | Maa Durga | 2024-09-20 | 2024-10-01 | 2024-10 | 12 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 35/3 | A V I ENTERPRISE | 2024-09-27 | 2024-10-01 | 2024-10 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 39/10 | Horil Mahto | 2024-09-16 | 2024-10-01 | 2024-10 | 16 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 34/7 | Aneshwar Traders | 2024-09-26 | 2024-10-03 | 2024-10 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 46/2 | Vishal construction | 2024-09-25 | 2024-10-03 | 2024-10 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 25/2 | VH Rajpoot cont. | 2024-10-01 | 2024-10-04 | 2024-10 | 4 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 12/7 | VED ENTTERPRISE | 2024-09-27 | 2024-10-06 | 2024-10 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 36/8 | SAIFI CON. | 2024-09-26 | 2024-10-06 | 2024-10 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 12/3 | SSR engineering | 2024-10-01 | 2024-10-07 | 2024-10 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 20/8 | Dewi Construction(Girendra) | 2024-10-01 | 2024-10-07 | 2024-10 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 30/2 | Garg Construction | 2024-10-01 | 2024-10-07 | 2024-10 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 31/2 | Laxmi Const. | 2024-10-03 | 2024-10-07 | 2024-10 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 25/3 | VH Rajpoot cont. | 2024-10-04 | 2024-10-08 | 2024-10 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 34/6 | Aneshwar Traders | 2024-10-04 | 2024-10-08 | 2024-10 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 39/5 | Dharamdas Contractor | 2024-10-04 | 2024-10-08 | 2024-10 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 31/1 | Laxmi Const. | 2024-10-08 | 2024-10-10 | 2024-10 | 3 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 34/3 | Maa Durga | 2024-10-04 | 2024-10-10 | 2024-10 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 34/4 | M A Construction | 2024-10-04 | 2024-10-10 | 2024-10 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 35/9 | A V I ENTERPRISE | 2024-10-04 | 2024-10-10 | 2024-10 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 46/1 | Vinayak Enterprise | 2024-09-09 | 2024-10-10 | 2024-10 | 32 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 12/5 | SSR engineering | 2024-10-10 | 2024-10-13 | 2024-10 | 4 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 20/6 | Dewi Construction(Girendra) | 2024-10-08 | 2024-10-13 | 2024-10 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 34/2 | Aneshwar Traders | 2024-10-08 | 2024-10-13 | 2024-10 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 30/1 | Garg Construction | 2024-10-10 | 2024-10-14 | 2024-10 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 31/8 | VH Rajpoot cont. | 2024-10-10 | 2024-10-14 | 2024-10 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 4/2 | VED ENTTERPRISE | 2024-10-10 | 2024-10-14 | 2024-10 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 39/8 | Horil Mahto | 2024-10-03 | 2024-10-15 | 2024-10 | 13 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 30/5 | Laxmi Const. | 2024-10-10 | 2024-10-16 | 2024-10 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 33/1 | M A Construction | 2024-10-13 | 2024-10-16 | 2024-10 | 4 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 36/2 | SAIFI CON. | 2024-10-12 | 2024-10-16 | 2024-10 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 31/10 | VH Rajpoot cont. | 2024-10-13 | 2024-10-18 | 2024-10 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 33/11 | Aneshwar Traders | 2024-10-13 | 2024-10-18 | 2024-10 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 20/9 | Dewi Construction(Girendra) | 2024-10-14 | 2024-10-19 | 2024-10 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 14/2 | SSR engineering | 2024-10-13 | 2024-10-20 | 2024-10 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 31/3 | Laxmi Const. | 2024-10-16 | 2024-10-20 | 2024-10 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 33/2 | M A Construction | 2024-10-16 | 2024-10-20 | 2024-10 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 20/2 | K R Associates | 2024-10-12 | 2024-10-21 | 2024-10 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 34/1 | Maa Durga | 2024-10-13 | 2024-10-21 | 2024-10 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 35/8 | A V I ENTERPRISE | 2024-10-12 | 2024-10-21 | 2024-10 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 52/9 | Dharamdas Contractor | 2024-10-13 | 2024-10-22 | 2024-10 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 33/10 | Aneshwar Traders | 2024-10-17 | 2024-10-23 | 2024-10 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 4/3 | VED ENTTERPRISE | 2024-10-17 | 2024-10-23 | 2024-10 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 14/1 | SSR engineering | 2024-10-21 | 2024-10-24 | 2024-10 | 4 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 20/5 | Dewi Construction(Girendra) | 2024-10-20 | 2024-10-24 | 2024-10 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 28/1 | J M Enterprise | 2024-10-17 | 2024-10-24 | 2024-10 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 31/9 | VH Rajpoot cont. | 2024-10-17 | 2024-10-24 | 2024-10 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 33/5 | Vinayak Enterprise | 2024-10-17 | 2024-10-24 | 2024-10 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 36/1 | SAIFI CON. | 2024-10-17 | 2024-10-24 | 2024-10 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 39/7 | Horil Mahto | 2024-10-15 | 2024-10-24 | 2024-10 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 31/5 | Laxmi Const. | 2024-10-22 | 2024-10-25 | 2024-10 | 4 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 7/10 | Vivan Enterprise | 2024-10-19 | 2024-10-25 | 2024-10 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 33/3 | M A Construction | 2024-10-22 | 2024-10-26 | 2024-10 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 33/9 | Aneshwar Traders | 2024-10-24 | 2024-10-26 | 2024-10 | 3 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 35/7 | A V I ENTERPRISE | 2024-10-24 | 2024-10-26 | 2024-10 | 3 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 8B/3 | Garg Construction | 2024-10-17 | 2024-10-26 | 2024-10 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 4/4 | VED ENTTERPRISE | 2024-10-24 | 2024-10-27 | 2024-10 | 4 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 7/11 | Vivan Enterprise | 2024-10-24 | 2024-10-27 | 2024-10 | 4 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 20/7 | Dewi Construction(Girendra) | 2024-10-24 | 2024-10-29 | 2024-10 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 39/9 | Horil Mahto | 2024-10-24 | 2024-10-31 | 2024-10 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 14/8 | SSR engineering | 2024-10-24 | 2024-11-01 | 2024-11 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 20/4 | K R Associates | 2024-10-24 | 2024-11-01 | 2024-11 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 31/6 | Laxmi Const. | 2024-10-24 | 2024-11-01 | 2024-11 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 31/7 | VH Rajpoot cont. | 2024-10-24 | 2024-11-01 | 2024-11 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 52/10 | Dharamdas Contractor | 2024-10-24 | 2024-11-01 | 2024-11 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 33/4 | M A Construction | 2024-10-25 | 2024-11-02 | 2024-11 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 35/5 | A V I ENTERPRISE | 2024-10-25 | 2024-11-02 | 2024-11 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 20/12 | Dewi Construction(Girendra) | 2024-11-01 | 2024-11-04 | 2024-11 | 4 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 8B/1 | Garg Construction | 2024-11-03 | 2024-11-05 | 2024-11 | 3 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 33/6 | Vinayak Enterprise | 2024-11-03 | 2024-11-08 | 2024-11 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 31/4 | Laxmi Const. | 2024-11-03 | 2024-11-09 | 2024-11 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 34/0 | M A Construction | 2024-11-03 | 2024-11-09 | 2024-11 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 14/6 | Dewi Construction(Girendra) | 2024-11-05 | 2024-11-10 | 2024-11 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 17/2 | SSR engineering | 2024-11-06 | 2024-11-10 | 2024-11 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 35/4 | Maa Durga | 2024-10-25 | 2024-11-10 | 2024-11 | 17 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 19/4 | VH Rajpoot cont. | 2024-11-06 | 2024-11-11 | 2024-11 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 33/8 | Aneshwar Traders | 2024-11-03 | 2024-11-11 | 2024-11 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 7/9 | Vivan Enterprise | 2024-11-03 | 2024-11-11 | 2024-11 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 19/7 | VH Rajpoot cont. | 2024-11-06 | 2024-11-13 | 2024-11 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 20/0 | J M Enterprise | 2024-11-03 | 2024-11-13 | 2024-11 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 20/3 | K R Associates | 2024-11-03 | 2024-11-13 | 2024-11 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 8B/2 | Garg Construction | 2024-11-03 | 2024-11-13 | 2024-11 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 39/6 | Horil Mahto | 2024-11-01 | 2024-11-14 | 2024-11 | 14 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 33/7 | Aneshwar Traders | 2024-11-06 | 2024-11-15 | 2024-11 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 7/8 | Vivan Enterprise | 2024-11-06 | 2024-11-15 | 2024-11 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 32/0 | Laxmi Const. | 2024-11-08 | 2024-11-16 | 2024-11 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 14/5 | Dewi Construction(Girendra) | 2024-11-10 | 2024-11-17 | 2024-11 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 10/1 | SSR engineering | 2024-11-09 | 2024-11-18 | 2024-11 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 19/5 | VH Rajpoot cont. | 2024-11-10 | 2024-11-18 | 2024-11 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 39/3 | M A Construction | 2024-11-12 | 2024-11-20 | 2024-11 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 19/6 | VH Rajpoot cont. | 2024-11-18 | 2024-11-21 | 2024-11 | 4 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 33/0 | Aneshwar Traders | 2024-11-14 | 2024-11-21 | 2024-11 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 36/4 | Maa Durga | 2024-11-18 | 2024-11-21 | 2024-11 | 4 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 4/8 | R K Constrcution | 2024-11-14 | 2024-11-21 | 2024-11 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 8B/4 | Garg Construction | 2024-11-14 | 2024-11-21 | 2024-11 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 14/4 | Dewi Construction(Girendra) | 2024-11-17 | 2024-11-22 | 2024-11 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 21/0 | J M Enterprise | 2024-11-18 | 2024-11-22 | 2024-11 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 8/3 | A V I ENTERPRISE | 2024-11-18 | 2024-11-22 | 2024-11 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 54/1 | Dharamdas Contractor | 2024-11-16 | 2024-11-23 | 2024-11 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 2/5 | Pankaj | 2024-11-10 | 2024-11-24 | 2024-11 | 15 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 20/11 | K R Associates | 2024-11-18 | 2024-11-24 | 2024-11 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 38/3 | Horil Mahto | 2024-11-10 | 2024-11-25 | 2024-11 | 16 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 6/2 | Pinky Dewi | 2024-11-14 | 2024-11-25 | 2024-11 | 12 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 19/3 | Reeta Bharti | 2024-11-10 | 2024-11-26 | 2024-11 | 17 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 39/2 | M A Construction | 2024-11-22 | 2024-11-26 | 2024-11 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 7/3 | Laxmi Const. | 2024-11-22 | 2024-11-26 | 2024-11 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 36/0 | SAIFI CON. | 2024-11-22 | 2024-11-27 | 2024-11 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 8/4 | A V I ENTERPRISE | 2024-11-22 | 2024-11-27 | 2024-11 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 14/8 | Dewi Construction(Girendra) | 2024-11-22 | 2024-11-28 | 2024-11 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 31/0 | VH Rajpoot cont. | 2024-11-22 | 2024-11-29 | 2024-11 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 35/0 | Aneshwar Traders | 2024-11-22 | 2024-11-29 | 2024-11 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 38/6 | Vinayak Enterprise | 2024-11-20 | 2024-11-29 | 2024-11 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 4/7 | R K Constrcution | 2024-11-22 | 2024-11-29 | 2024-11 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 41/1 | Amar Singh | 2024-11-10 | 2024-11-29 | 2024-11 | 20 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 7/2 | Laxmi Const. | 2024-11-22 | 2024-11-29 | 2024-11 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 8B/5 | Garg Construction | 2024-11-22 | 2024-11-29 | 2024-11 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 10/0 | SSR engineering | 2024-11-22 | 2024-11-30 | 2024-11 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 54/2 | Dharamdas Contractor | 2024-11-20 | 2024-12-01 | 2024-12 | 12 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 39/0 | M A Construction | 2024-11-22 | 2024-12-02 | 2024-12 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 2/7 | Pankaj | 2024-11-26 | 2024-12-03 | 2024-12 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 8/2 | A V I ENTERPRISE | 2024-11-25 | 2024-12-03 | 2024-12 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 26/0 | VH Rajpoot cont. | 2024-11-29 | 2024-12-04 | 2024-12 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 7/1 | Laxmi Const. | 2024-11-30 | 2024-12-04 | 2024-12 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 14/7 | Dewi Construction(Girendra) | 2024-11-29 | 2024-12-05 | 2024-12 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 19/2 | Reeta Bharti | 2024-11-28 | 2024-12-05 | 2024-12 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 4/3 | Pinky Dewi | 2024-11-28 | 2024-12-05 | 2024-12 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 36/12 | Horil Mahto | 2024-11-29 | 2024-12-06 | 2024-12 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 4/5 | R K Constrcution | 2024-11-30 | 2024-12-06 | 2024-12 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 17/0 | SSR engineering | 2024-12-03 | 2024-12-09 | 2024-12 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 2/6 | Pankaj | 2024-12-01 | 2024-12-09 | 2024-12 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 5/1 | J M Enterprise | 2024-12-03 | 2024-12-09 | 2024-12 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 7/4 | Laxmi Const. | 2024-12-03 | 2024-12-09 | 2024-12 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 7/7 | Garg Construction | 2024-12-03 | 2024-12-09 | 2024-12 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 8/1 | A V I ENTERPRISE | 2024-12-03 | 2024-12-09 | 2024-12 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 3/0 | VH Rajpoot cont. | 2024-12-04 | 2024-12-10 | 2024-12 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 41/2 | Amar Singh | 2024-11-30 | 2024-12-10 | 2024-12 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 56/5 | Aneshwar Traders | 2024-12-04 | 2024-12-10 | 2024-12 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 38/10 | Maa Durga | 2024-12-01 | 2024-12-11 | 2024-12 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 55/1 | Dharamdas Contractor | 2024-12-02 | 2024-12-11 | 2024-12 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 14/3 | Dewi Construction(Girendra) | 2024-12-06 | 2024-12-12 | 2024-12 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 4/4 | Pinky Dewi | 2024-12-06 | 2024-12-12 | 2024-12 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 19/4 | Reeta Bharti | 2024-12-06 | 2024-12-13 | 2024-12 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 7/5 | Laxmi Const. | 2024-12-09 | 2024-12-13 | 2024-12 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 49/0 | M A Construction | 2024-12-09 | 2024-12-15 | 2024-12 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 2/3 | Pankaj | 2024-12-10 | 2024-12-16 | 2024-12 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 4/2 | Pinky Dewi | 2024-12-12 | 2024-12-16 | 2024-12 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 4/9 | R K Constrcution | 2024-12-09 | 2024-12-16 | 2024-12 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 6/1 | J M Enterprise | 2024-12-09 | 2024-12-16 | 2024-12 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 7/6 | Garg Construction | 2024-12-09 | 2024-12-16 | 2024-12 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 14/2 | Dewi Construction(Girendra) | 2024-12-12 | 2024-12-17 | 2024-12 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 38/7 | Vinayak Enterprise | 2024-12-09 | 2024-12-17 | 2024-12 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 4/0 | VH Rajpoot cont. | 2024-12-09 | 2024-12-17 | 2024-12 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 56/8 | Aneshwar Traders | 2024-12-09 | 2024-12-17 | 2024-12 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 52/7 | SAIFI CON. | 2024-12-09 | 2024-12-18 | 2024-12 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 38/2 | Horil Mahto | 2024-12-06 | 2024-12-19 | 2024-12 | 14 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 45/3 | Amar Singh | 2024-12-10 | 2024-12-20 | 2024-12 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 48/1 | M A Construction | 2024-12-15 | 2024-12-20 | 2024-12 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 7/0 | Laxmi Const. | 2024-12-10 | 2024-12-20 | 2024-12 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 8/0 | A V I ENTERPRISE | 2024-12-10 | 2024-12-20 | 2024-12 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 19/1 | Reeta Bharti | 2024-12-13 | 2024-12-21 | 2024-12 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 47/0 | Maa Durga | 2024-12-10 | 2024-12-21 | 2024-12 | 12 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 4/8 | Pinky Dewi | 2024-12-17 | 2024-12-22 | 2024-12 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 56/1 | Dharamdas Contractor | 2024-12-10 | 2024-12-22 | 2024-12 | 13 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 14/1 | Dewi Construction(Girendra) | 2024-12-18 | 2024-12-23 | 2024-12 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 7/10 | Pankaj | 2024-12-18 | 2024-12-23 | 2024-12 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 4/10 | R K Constrcution | 2024-12-17 | 2024-12-24 | 2024-12 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 9/0 | VH Rajpoot cont. | 2024-12-10 | 2024-12-24 | 2024-12 | 15 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 19/5 | Reeta Bharti | 2024-12-22 | 2024-12-27 | 2024-12 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 4/7 | Pinky Dewi | 2024-12-24 | 2024-12-27 | 2024-12 | 4 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 45/2 | Amar Singh | 2024-12-21 | 2024-12-27 | 2024-12 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 52/8 | SAIFI CON. | 2024-12-19 | 2024-12-27 | 2024-12 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 56/7 | Aneshwar Traders | 2024-11-20 | 2024-12-27 | 2024-12 | 38 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 6/0 | J M Enterprise | 2024-12-20 | 2024-12-27 | 2024-12 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 46/0 | Vinayak Enterprise | 2024-12-18 | 2024-12-28 | 2024-12 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 7/9 | Pankaj | 2024-12-24 | 2024-12-30 | 2024-12 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 17/1 | Dewi Construction(Girendra) | 2024-12-24 | 2024-12-31 | 2024-12 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 38/4 | Horil Mahto | 2024-12-20 | 2024-12-31 | 2024-12 | 12 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 4/6 | R K Constrcution | 2024-12-23 | 2024-12-31 | 2024-12 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 54/0 | Dharamdas Contractor | 2024-12-23 | 2024-12-31 | 2024-12 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 53A/5 | A K Rajpoot | 2024-11-24 | 2025-01-02 | 2025-01 | 40 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 64/1 | M A Construction | 2024-11-24 | 2025-01-02 | 2025-01 | 40 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 15/0 | SSR engineering | 2024-12-17 | 2025-01-03 | 2025-01 | 18 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 31/3 | ASC heights | 2024-12-24 | 2025-01-03 | 2025-01 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 38/9 | Maa Durga | 2024-11-24 | 2025-01-03 | 2025-01 | 41 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 4/5 | Pinky Dewi | 2024-12-28 | 2025-01-03 | 2025-01 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 46/1 | Amar Singh | 2024-12-28 | 2025-01-04 | 2025-01 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 53A/7 | Punam kumari-1 | 2025-12-08 | 2025-01-07 | 2025-01 |  | Invalid Negative Duration | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 7/2 | Pankaj | 2024-12-31 | 2025-01-07 | 2025-01 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 19/6 | Reeta Bharti | 2024-12-28 | 2025-01-08 | 2025-01 | 12 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 5/0 | J M Enterprise | 2024-12-29 | 2025-01-09 | 2025-01 | 12 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 8A/0 | Garg Construction | 2024-11-20 | 2025-01-09 | 2025-01 | 51 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 17/4 | Dewi Construction(Girendra) | 2025-01-01 | 2025-01-10 | 2025-01 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 53A/0 | Laxmi Const. | 2025-01-03 | 2025-01-10 | 2025-01 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 70/0 | Pankaj Kumar | 2025-12-20 | 2025-01-10 | 2025-01 |  | Invalid Negative Duration | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 12/2 | Pinky Dewi | 2025-01-03 | 2025-01-11 | 2025-01 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 31/4 | ASC heights | 2025-01-04 | 2025-01-11 | 2025-01 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 52/0 | Vinayak Enterprise | 2025-01-03 | 2025-01-11 | 2025-01 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 53A/4 | A K Rajpoot | 2025-01-03 | 2025-01-11 | 2025-01 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 56/0 | Aneshwar Traders | 2025-01-03 | 2025-01-11 | 2025-01 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 64/2 | M A Construction | 2025-01-03 | 2025-01-11 | 2025-01 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 28/0 | VH Rajpoot cont. | 2024-12-28 | 2025-01-12 | 2025-01 | 16 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 48/0 | Maa Durga | 2025-01-04 | 2025-01-12 | 2025-01 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 19/10 | SSR engineering | 2025-01-10 | 2025-01-14 | 2025-01 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 7/8 | Pankaj | 2025-01-08 | 2025-01-14 | 2025-01 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 8B/0 | A V I ENTERPRISE | 2024-12-26 | 2025-01-14 | 2025-01 | 20 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 36/3 | Amar Singh | 2025-01-07 | 2025-01-15 | 2025-01 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 53/0 | SAIFI CON. | 2025-01-03 | 2025-01-15 | 2025-01 | 13 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 17/3 | Dewi Construction(Girendra) | 2025-01-10 | 2025-01-17 | 2025-01 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 19/7 | Reeta Bharti | 2025-01-09 | 2025-01-17 | 2025-01 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 22A/0 | Punam kumari-3 | 2025-12-15 | 2025-01-17 | 2025-01 |  | Invalid Negative Duration | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 38/1 | Horil Mahto | 2025-01-07 | 2025-01-17 | 2025-01 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 57/0 | Pinky Dewi | 2025-12-22 | 2025-01-17 | 2025-01 |  | Invalid Negative Duration | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 58/0 | Amit Choudhry | 2025-12-01 | 2025-01-17 | 2025-01 |  | Invalid Negative Duration | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 53A/2 | Laxmi Const. | 2025-01-10 | 2025-01-18 | 2025-01 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 31/2 | ASC heights | 2025-01-11 | 2025-01-19 | 2025-01 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 20/10 | Garg Construction | 2025-01-10 | 2025-01-20 | 2025-01 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 52/3 | Vinayak Enterprise | 2025-01-12 | 2025-01-20 | 2025-01 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 12/3 | Pinky Dewi | 2025-01-12 | 2025-01-21 | 2025-01 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 55/0 | Dharamdas Contractor | 2025-01-04 | 2025-01-22 | 2025-01 | 19 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 7/7 | Pankaj | 2025-01-15 | 2025-01-22 | 2025-01 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 17/2 | Dewi Construction(Girendra) | 2025-01-17 | 2025-01-23 | 2025-01 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 53A/6 | A K Rajpoot | 2025-01-12 | 2025-01-23 | 2025-01 | 12 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 36/5 | Amar Singh | 2025-01-15 | 2025-01-24 | 2025-01 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 51/0 | M A Construction | 2025-01-12 | 2025-01-24 | 2025-01 | 13 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 12/4 | Pinky Dewi | 2025-01-21 | 2025-01-25 | 2025-01 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 31/6 | ASC heights | 2025-01-20 | 2025-01-25 | 2025-01 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 53A/3 | Laxmi Const. | 2025-01-18 | 2025-01-25 | 2025-01 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 19/9 | Reeta Bharti | 2025-01-16 | 2025-01-27 | 2025-01 | 12 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 35/1 | Horil Mahto | 2025-01-16 | 2025-01-28 | 2025-01 | 13 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 17/5 | Dewi Construction(Girendra) | 2025-01-24 | 2025-01-29 | 2025-01 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 27/0 | VH Rajpoot cont. | 2025-01-14 | 2025-01-29 | 2025-01 | 16 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 36/1 | Amar Singh | 2025-01-25 | 2025-01-30 | 2025-01 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 45/1 | Maa Durga | 2025-01-21 | 2025-01-30 | 2025-01 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 7/6 | Pankaj | 2025-01-21 | 2025-01-30 | 2025-01 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 0/2 | SSR engineering | 2025-01-23 | 2025-01-31 | 2025-01 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 0/3 | Garg Construction | 2025-01-24 | 2025-01-31 | 2025-01 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 21/3 | A K Rajpoot | 2025-01-25 | 2025-01-31 | 2025-01 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 33/10 | Rudra Construction | 2025-01-21 | 2025-01-31 | 2025-01 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 52/6 | SAIFI CON. | 2025-01-21 | 2025-01-31 | 2025-01 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 57/0 | Aneshwar Traders | 2025-01-15 | 2025-01-31 | 2025-01 | 17 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 12/5 | Pinky Dewi | 2025-01-25 | 2025-02-01 | 2025-02 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 31/1 | ASC heights | 2025-01-25 | 2025-02-02 | 2025-02 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 53/1 | Laxmi Const. | 2025-01-26 | 2025-02-03 | 2025-02 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 24/0 | A V I ENTERPRISE | 2025-01-18 | 2025-02-04 | 2025-02 | 18 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 17/7 | Dewi Construction(Girendra) | 2025-01-30 | 2025-02-05 | 2025-02 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 42/0 | Dharamdas Contractor | 2025-01-23 | 2025-02-05 | 2025-02 | 14 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 20/0 | Reeta Bharti | 2025-01-28 | 2025-02-06 | 2025-02 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 35/6 | Maa Durga | 2025-02-01 | 2025-02-06 | 2025-02 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 22/0 | A K Rajpoot | 2025-02-01 | 2025-02-07 | 2025-02 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 36/2 | Amar Singh | 2025-02-02 | 2025-02-07 | 2025-02 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 56/2 | R K Constrcution | 2025-02-01 | 2025-02-07 | 2025-02 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 12/9 | Pinky Dewi | 2025-02-02 | 2025-02-08 | 2025-02 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 0/4 | Garg Construction | 2025-02-01 | 2025-02-09 | 2025-02 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 29/0 | VH Rajpoot cont. | 2025-01-30 | 2025-02-09 | 2025-02 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 7/5 | Pankaj | 2025-01-29 | 2025-02-09 | 2025-02 | 12 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 31/7 | ASC heights | 2025-02-03 | 2025-02-10 | 2025-02 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 52/4 | Vinayak Enterprise | 2025-02-01 | 2025-02-10 | 2025-02 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 35/0 | Horil Mahto | 2025-01-29 | 2025-02-11 | 2025-02 | 14 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 33/11 | Rudra Construction | 2025-02-02 | 2025-02-12 | 2025-02 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 20/2 | Reeta Bharti | 2025-02-07 | 2025-02-13 | 2025-02 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 21/0 | Dewi Construction(Girendra) | 2025-02-06 | 2025-02-13 | 2025-02 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 0/1 | SSR engineering | 2025-02-02 | 2025-02-15 | 2025-02 | 14 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 35/9 | Amar Singh | 2025-02-08 | 2025-02-15 | 2025-02 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 40/0 | Aneshwar Traders | 2025-02-02 | 2025-02-15 | 2025-02 | 14 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 52/5 | SAIFI CON. | 2025-02-02 | 2025-02-15 | 2025-02 | 14 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 59/0 | M A Construction | 2025-02-02 | 2025-02-15 | 2025-02 | 14 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 8/1 | Pinky Dewi | 2025-02-09 | 2025-02-15 | 2025-02 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 22A/0 | A K Rajpoot | 2025-02-09 | 2025-02-17 | 2025-02 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 25/0 | A V I ENTERPRISE | 2025-02-06 | 2025-02-18 | 2025-02 | 13 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 64/0 | Laxmi Const. | 2025-02-06 | 2025-02-18 | 2025-02 | 13 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 7/4 | Pankaj | 2025-02-10 | 2025-02-18 | 2025-02 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 20/3 | Reeta Bharti | 2025-02-12 | 2025-02-19 | 2025-02 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 31/9 | ASC heights | 2025-02-11 | 2025-02-20 | 2025-02 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 33/6 | Dewi Construction(Girendra) | 2025-02-14 | 2025-02-20 | 2025-02 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 34/7 | Horil Mahto | 2025-02-12 | 2025-02-20 | 2025-02 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 53A/7 | Maa Durga | 2025-02-10 | 2025-02-20 | 2025-02 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 30/0 | VH Rajpoot cont. | 2025-02-10 | 2025-02-21 | 2025-02 | 12 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 35/7 | Amar Singh | 2025-02-16 | 2025-02-21 | 2025-02 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 43/0 | Dharamdas Contractor | 2025-02-06 | 2025-02-21 | 2025-02 | 16 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 52/2 | Vinayak Enterprise | 2025-02-11 | 2025-02-21 | 2025-02 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 8/2 | Pinky Dewi | 2025-02-16 | 2025-02-21 | 2025-02 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 33/9 | Rudra Construction | 2025-02-14 | 2025-02-22 | 2025-02 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 4/1 | Garg Construction | 2025-02-10 | 2025-02-22 | 2025-02 | 13 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 56/3 | R K Constrcution | 2025-02-10 | 2025-02-23 | 2025-02 | 14 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 20/4 | Reeta Bharti | 2025-02-20 | 2025-02-25 | 2025-02 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 33/7 | Dewi Construction(Girendra) | 2025-02-21 | 2025-02-25 | 2025-02 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 41/0 | Aneshwar Traders | 2025-02-16 | 2025-02-25 | 2025-02 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 7/1 | Pankaj | 2025-02-19 | 2025-02-25 | 2025-02 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 34/6 | Horil Mahto | 2025-02-21 | 2025-02-27 | 2025-02 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 35/4 | Amar Singh | 2025-02-20 | 2025-02-27 | 2025-02 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 63/0 | Laxmi Const. | 2025-02-19 | 2025-02-27 | 2025-02 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 11/0 | SSR engineering | 2025-02-19 | 2025-02-28 | 2025-02 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 21/2 | VH Rajpoot cont. | 2025-02-26 | 2025-02-28 | 2025-02 | 3 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 31/0 | ASC heights | 2025-02-19 | 2025-02-28 | 2025-02 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 53A/1 | SAIFI CON. | 2025-02-20 | 2025-02-28 | 2025-02 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 58/0 | M A Construction | 2025-02-19 | 2025-02-28 | 2025-02 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 8/0 | Pinky Dewi | 2025-02-22 | 2025-02-28 | 2025-02 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 33/3 | Dewi Construction(Girendra) | 2025-02-26 | 2025-03-02 | 2025-03 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 13/0 | A K Rajpoot | 2025-02-26 | 2025-03-03 | 2025-03 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 35/5 | Amar Singh | 2025-02-27 | 2025-03-03 | 2025-03 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 50/0 | Maa Durga | 2025-02-26 | 2025-03-04 | 2025-03 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 4/10 | Reeta Bharti | 2025-03-01 | 2025-03-05 | 2025-03 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 33/8 | Dewi Construction(Girendra) | 2025-03-03 | 2025-03-07 | 2025-03 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 23/0 | VH Rajpoot cont. | 2025-03-01 | 2025-03-08 | 2025-03 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 35/3 | Horil Mahto | 2025-02-28 | 2025-03-08 | 2025-03 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 60/0 | Laxmi Const. | 2025-02-27 | 2025-03-08 | 2025-03 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 7/0 | Pankaj | 2025-02-27 | 2025-03-08 | 2025-03 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 7/11 | Pinky Dewi | 2025-03-01 | 2025-03-08 | 2025-03 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 14/0 | A K Rajpoot | 2025-03-04 | 2025-03-09 | 2025-03 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 30/4 | ASC heights | 2025-03-01 | 2025-03-09 | 2025-03 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 34/5 | Maa Durga | 2025-03-04 | 2025-03-09 | 2025-03 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 12/0 | Garg Construction | 2025-03-01 | 2025-03-10 | 2025-03 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 33/4 | Dewi Construction(Girendra) | 2025-03-08 | 2025-03-11 | 2025-03 | 4 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 34/1 | Rudra Construction | 2025-03-01 | 2025-03-11 | 2025-03 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 56/4 | R K Constrcution | 2025-03-01 | 2025-03-11 | 2025-03 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 8/3 | Pinky Dewi | 2025-03-08 | 2025-03-12 | 2025-03 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 5/0 | Reeta Bharti | 2025-03-01 | 2025-03-13 | 2025-03 | 13 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 30/5 | ASC heights | 2025-03-10 | 2025-03-16 | 2025-03 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 33/1 | Dewi Construction(Girendra) | 2025-03-12 | 2025-03-18 | 2025-03 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 35/6 | Horil Mahto | 2025-03-10 | 2025-03-18 | 2025-03 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 6/1 | Pankaj | 2025-03-09 | 2025-03-19 | 2025-03 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 61/0 | M A Construction | 2025-03-01 | 2025-03-20 | 2025-03 | 20 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 67/0 | Aneshwar Traders | 2025-03-01 | 2025-03-20 | 2025-03 | 20 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 5/1 | Reeta Bharti | 2025-03-16 | 2025-03-21 | 2025-03 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 8/4 | Pinky Dewi | 2025-03-13 | 2025-03-21 | 2025-03 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 52/1 | Vinayak Enterprise | 2025-03-01 | 2025-03-22 | 2025-03 | 22 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 31/8 | ASC heights | 2025-03-16 | 2025-03-23 | 2025-03 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 33/2 | Dewi Construction(Girendra) | 2025-03-19 | 2025-03-23 | 2025-03 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 18/0 | A K Rajpoot | 2025-03-20 | 2025-03-25 | 2025-03 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 64/3 | Laxmi Const. | 2025-03-20 | 2025-03-26 | 2025-03 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 66/1 | SAIFI CON. | 2025-03-20 | 2025-03-26 | 2025-03 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 8B/1 | Pinky Dewi | 2025-03-22 | 2025-03-26 | 2025-03 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 62/0 | M A Construction | 2025-03-20 | 2025-03-27 | 2025-03 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 7/3 | Pankaj | 2025-03-20 | 2025-03-27 | 2025-03 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 6/0 | Reeta Bharti | 2025-03-22 | 2025-03-29 | 2025-03 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 19/0 | A K Rajpoot | 2025-03-25 | 2025-03-30 | 2025-03 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 31/10 | ASC heights | 2025-03-24 | 2025-03-30 | 2025-03 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 35/2 | Horil Mahto | 2025-03-20 | 2025-03-30 | 2025-03 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 34/0 | Dewi Construction(Girendra) | 2025-03-24 | 2025-03-31 | 2025-03 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 35/8 | Amar Singh | 2025-03-22 | 2025-03-31 | 2025-03 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 38/8 | M K infra | 2025-03-21 | 2025-03-31 | 2025-03 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 39/3 | Ananya Traders-1 | 2025-03-24 | 2025-03-31 | 2025-03 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 8B/5 | Pinky Dewi | 2025-03-24 | 2025-03-31 | 2025-03 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 56/6 | R K Constrcution | 2025-03-25 | 2025-04-02 | 2025-04 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 57/1 | Maa Durga | 2025-03-25 | 2025-04-02 | 2025-04 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 21/1 | A K Rajpoot | 2025-03-31 | 2025-04-03 | 2025-04 | 4 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 4/6 | Reeta Bharti | 2025-03-28 | 2025-04-05 | 2025-04 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 8B/3 | Pinky Dewi | 2025-03-28 | 2025-04-07 | 2025-04 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 20/11 | Gagan enterprise.1 | 2025-03-31 | 2025-04-08 | 2025-04 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 16/0 | A K Rajpoot | 2025-04-04 | 2025-04-10 | 2025-04 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 34/4 | Dewi Construction(Girendra) | 2025-04-03 | 2025-04-10 | 2025-04 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 66/0 A,B | Dharamdas Contractor | 2025-03-25 | 2025-04-10 | 2025-04 | 17 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 66/0 C,D | Dharamdas Contractor | 2025-03-25 | 2025-04-10 | 2025-04 | 17 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 32/0 | ASC heights | 2025-04-01 | 2025-04-11 | 2025-04 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 38/6 | M K infra | 2025-04-01 | 2025-04-11 | 2025-04 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 4/1 | Anand Construction | 2025-03-31 | 2025-04-11 | 2025-04 | 12 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 9/0 | Gagan enterprise.2 | 2025-04-01 | 2025-04-11 | 2025-04 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 39/1 | Ananya Traders-1 | 2025-04-01 | 2025-04-12 | 2025-04 | 12 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 53A/4 | Horil Mahto | 2025-04-01 | 2025-04-12 | 2025-04 | 12 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 8B/2 | Pinky Dewi | 2025-04-08 | 2025-04-13 | 2025-04 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 36/0 | Amar Singh | 2025-04-02 | 2025-04-14 | 2025-04 | 13 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 20/10 | Gagan enterprise.1 | 2025-04-09 | 2025-04-15 | 2025-04 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 10/1 | Gagan enterprise.2 | 2025-04-12 | 2025-04-16 | 2025-04 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 52/6 | Ananya Traders-2 | 2025-04-05 | 2025-04-16 | 2025-04 | 12 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 4/0 | Reeta Bharti | 2025-04-06 | 2025-04-17 | 2025-04 | 12 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 68/0 | Aneshwar Traders | 2025-04-04 | 2025-04-17 | 2025-04 | 14 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 39/0 | Ananya Traders-1 | 2025-04-12 | 2025-04-19 | 2025-04 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 2/1 | VH Rajpoot cont. | 2025-04-17 | 2025-04-21 | 2025-04 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 31/5 | ASC heights | 2025-04-12 | 2025-04-21 | 2025-04 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 44/0 | Laxmi Const. | 2025-04-04 | 2025-04-21 | 2025-04 | 18 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 8B/4 | Pinky Dewi | 2025-04-14 | 2025-04-21 | 2025-04 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 20/1 | Gagan enterprise.1 | 2025-04-16 | 2025-04-22 | 2025-04 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 33/0 | Dewi Construction(Girendra) | 2025-04-12 | 2025-04-22 | 2025-04 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 36/6 | Amar Singh | 2025-04-12 | 2025-04-22 | 2025-04 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 38/7 | M K infra | 2025-04-12 | 2025-04-22 | 2025-04 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 25/2 | Rudra Construction | 2025-04-15 | 2025-04-23 | 2025-04 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 52/5 | Ananya Traders-2 | 2025-04-17 | 2025-04-25 | 2025-04 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 0/4 | Anand Construction | 2025-04-12 | 2025-04-26 | 2025-04 | 15 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 19/12 | Gagan enterprise.1 | 2025-04-23 | 2025-04-26 | 2025-04 | 4 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 39/2 | Ananya Traders-1 | 2025-04-20 | 2025-04-26 | 2025-04 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 1/0 | VH Rajpoot cont. | 2025-04-22 | 2025-04-27 | 2025-04 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 10/0 | Gagan enterprise.2 | 2025-04-17 | 2025-04-28 | 2025-04 | 12 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 30/6 | ASC heights | 2025-04-22 | 2025-04-28 | 2025-04 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 34/2 | Dewi Construction(Girendra) | 2025-04-23 | 2025-04-28 | 2025-04 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 36/7 | Amar Singh | 2025-04-23 | 2025-04-28 | 2025-04 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 65/0 | Dharamdas Contractor | 2025-04-11 | 2025-04-28 | 2025-04 | 18 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 2/0 | A V I ENTERPRISE | 2025-04-22 | 2025-04-29 | 2025-04 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 52/4 | Ananya Traders-2 | 2025-04-26 | 2025-04-29 | 2025-04 | 4 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 19/11 | Gagan enterprise.1 | 2025-04-27 | 2025-04-30 | 2025-04 | 4 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 2/2 | VH Rajpoot cont. | 2025-04-27 | 2025-04-30 | 2025-04 | 4 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 70/0 | SAIFI CON. | 2025-04-17 | 2025-04-30 | 2025-04 | 14 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 8A/0 | Pinky Dewi | 2025-04-22 | 2025-04-30 | 2025-04 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 34/3 | Dewi Construction(Girendra) | 2025-04-29 | 2025-05-03 | 2025-05 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 39/4 | Ananya Traders-1 | 2025-04-29 | 2025-05-04 | 2025-05 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 36/8 | Amar Singh | 2025-04-29 | 2025-05-05 | 2025-05 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 19/10 | Gagan enterprise.1 | 2025-04-30 | 2025-05-06 | 2025-05 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 30/3 | ASC heights | 2025-04-30 | 2025-05-06 | 2025-05 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 52/3 | Ananya Traders-2 | 2025-04-30 | 2025-05-06 | 2025-05 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 25/3 | Rudra Construction | 2025-04-30 | 2025-05-07 | 2025-05 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 19/8 | Gagan enterprise.1 | 2025-05-06 | 2025-05-09 | 2025-05 | 4 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 12/1 | Gagan enterprise.2 | 2025-05-04 | 2025-05-10 | 2025-05 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 38/5 | VH Rajpoot cont. | 2025-05-05 | 2025-05-11 | 2025-05 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 39/5 | Ananya Traders-1 | 2025-05-05 | 2025-05-11 | 2025-05 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 4/9 | Reeta Bharti | 2025-05-04 | 2025-05-11 | 2025-05 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 45/0 | Laxmi Const. | 2025-04-25 | 2025-05-11 | 2025-05 | 17 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 52/2 | Ananya Traders-2 | 2025-05-07 | 2025-05-12 | 2025-05 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 30/1 | ASC heights | 2025-05-07 | 2025-05-13 | 2025-05 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 36/4 | Amar Singh | 2025-05-07 | 2025-05-13 | 2025-05 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 56/2 | Dewi Construction(Girendra) | 2025-05-07 | 2025-05-14 | 2025-05 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 8B/0 | Pinky Dewi | 2025-05-05 | 2025-05-14 | 2025-05 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 17/8 | Gagan enterprise.1 | 2025-05-11 | 2025-05-15 | 2025-05 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 0/0 | A V I ENTERPRISE | 2025-05-05 | 2025-05-17 | 2025-05 | 13 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 52/9 | Ananya Traders-2 | 2025-05-13 | 2025-05-17 | 2025-05 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 36/11 | Amar Singh | 2025-05-14 | 2025-05-19 | 2025-05 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 38/11 | Ananya Traders-1 | 2025-05-12 | 2025-05-19 | 2025-05 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 56/1 | Dewi Construction(Girendra) | 2025-05-14 | 2025-05-19 | 2025-05 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 69/0 | SAIFI CON. | 2025-05-06 | 2025-05-19 | 2025-05 | 14 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 30/2 | ASC heights | 2025-05-14 | 2025-05-20 | 2025-05 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 2/1 | Reeta Bharti | 2025-05-12 | 2025-05-21 | 2025-05 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 52/10 | Ananya Traders-2 | 2025-05-16 | 2025-05-21 | 2025-05 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 12/6 | Gagan enterprise.2 | 2025-05-11 | 2025-05-22 | 2025-05 | 12 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 23/3 | Pinky Dewi | 2025-05-15 | 2025-05-22 | 2025-05 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 53/1 | Amit Const | 2025-05-12 | 2025-05-22 | 2025-05 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 37/0 | VH Rajpoot cont. | 2025-05-11 | 2025-05-23 | 2025-05 | 13 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 36/9 | Amar Singh | 2025-05-20 | 2025-05-24 | 2025-05 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 38/10 | Ananya Traders-1 | 2025-05-20 | 2025-05-24 | 2025-05 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 56/3 | Dewi Construction(Girendra) | 2025-05-20 | 2025-05-24 | 2025-05 | 5 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 15/0 | Gagan enterprise.1 | 2025-05-16 | 2025-05-25 | 2025-05 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 23/5 | Rudra Construction | 2025-05-10 | 2025-05-27 | 2025-05 | 18 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 52/8 | Ananya Traders-2 | 2025-05-22 | 2025-05-27 | 2025-05 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 23/4 | Pinky Dewi | 2025-05-23 | 2025-05-28 | 2025-05 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 69A/0 | Aneshwar Traders | 2025-05-14 | 2025-05-28 | 2025-05 | 15 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 0/2 | Reeta Bharti | 2025-05-23 | 2025-05-30 | 2025-05 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 56/4 | Dewi Construction(Girendra) | 2025-05-23 | 2025-05-30 | 2025-05 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 12/8 | Gagan enterprise.1 | 2025-05-26 | 2025-05-31 | 2025-05 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 36/10 | Amar Singh | 2025-05-25 | 2025-05-31 | 2025-05 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 38/9 | M K infra | 2025-04-23 | 2025-06-01 | 2025-06 | 40 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 38/5 | Ananya Traders-1 | 2025-05-28 | 2025-06-02 | 2025-06 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 23/1 | Pinky Dewi | 2025-05-28 | 2025-06-03 | 2025-06 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 38/0 | A V I ENTERPRISE | 2025-05-20 | 2025-06-03 | 2025-06 | 15 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 0/3 | Reeta Bharti | 2025-05-25 | 2025-06-04 | 2025-06 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 56/5 | Dewi Construction(Girendra) | 2025-05-30 | 2025-06-04 | 2025-06 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 51/0 | Ananya Traders-2 | 2025-05-27 | 2025-06-07 | 2025-06 | 12 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 23/2 | Pinky Dewi | 2025-06-04 | 2025-06-09 | 2025-06 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 33/5 | Amar Singh | 2025-06-02 | 2025-06-10 | 2025-06 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 0/1 | Reeta Bharti | 2025-06-04 | 2025-06-11 | 2025-06 | 8 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 50/1 | Ananya Traders-2 | 2025-06-08 | 2025-06-13 | 2025-06 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 53A/5 | Devine | 2025-06-02 | 2025-06-14 | 2025-06 | 13 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 34/5 | Amar Singh | 2025-06-12 | 2025-06-18 | 2025-06 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 53A/2 | Amit Const | 2025-06-10 | 2025-06-18 | 2025-06 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 22/0 | Pinky Dewi | 2025-06-12 | 2025-06-20 | 2025-06 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 30/0 | ASC heights | 2025-05-25 | 2025-06-21 | 2025-06 | 28 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 3/0 | Reeta Bharti | 2025-06-12 | 2025-06-23 | 2025-06 | 12 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 21/2 | Pinky Dewi | 2025-06-21 | 2025-06-26 | 2025-06 | 6 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 45/1 | M K infra | 2025-06-10 | 2025-06-27 | 2025-06 | 18 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 48/0 | Ananya Traders-2 | 2025-06-15 | 2025-06-29 | 2025-06 | 15 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 53A/3 | Amit Const | 2025-06-20 | 2025-06-29 | 2025-06 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 12/7 | Reeta Bharti | 2025-06-24 | 2025-06-30 | 2025-06 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 14/0 | Gagan enterprise.1 | 2025-06-01 | 2025-06-30 | 2025-06 | 30 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 21/1 | Pinky Dewi | 2025-06-27 | 2025-06-30 | 2025-06 | 4 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 40/0 | Ananya Traders-1 | 2025-06-04 | 2025-06-30 | 2025-06 | 27 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 28/1 | ASC heights | 2025-06-24 | 2025-07-05 | 2025-07 | 12 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 21/3 | Pinky Dewi | 2025-07-01 | 2025-07-07 | 2025-07 | 7 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 25/1 | Reeta Bharti | 2025-07-01 | 2025-07-12 | 2025-07 | 12 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 44/0 | Ananya Traders-1 | 2025-07-05 | 2025-07-18 | 2025-07 | 14 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 56/0 | Amar singh | 2025-06-28 | 2025-07-22 | 2025-07 | 25 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 28/0 | Reeta Bharti | 2025-07-08 | 2025-07-31 | 2025-07 | 24 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 41/0 | Ananya Traders-1 | 2025-07-20 | 2025-08-08 | 2025-08 | 20 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 13/0 | Gagan enterprise.1 | 2025-07-09 | 2025-08-11 | 2025-08 | 34 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 53A/6 | Punam Kumari | 2025-07-27 | 2025-08-17 | 2025-08 | 22 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 46/2 | Gagan enterprise.2 (Kajol) | 2025-08-14 | 2025-08-26 | 2025-08 | 13 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 24/0 | Kongres Kumar-1 | 2025-07-26 | 2025-08-27 | 2025-08 | 33 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 1/0 | Radha Construction | 2025-08-09 | 2025-08-30 | 2025-08 | 22 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 18/0 | Sainik Trader | 2025-08-04 | 2025-08-30 | 2025-08 | 27 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 65/0 | Kongres Kumar-2 | 2025-08-02 | 2025-08-30 | 2025-08 | 29 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 12/0 | Gagan enterprise.1 | 2025-08-12 | 2025-09-02 | 2025-09 | 22 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 54/1 | Punam Kumari | 2025-08-18 | 2025-09-04 | 2025-09 | 18 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 43/0 | Ananya Traders-1 | 2025-08-10 | 2025-09-06 | 2025-09 | 28 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 11/0 | Gouri Shankar | 2025-08-24 | 2025-09-14 | 2025-09 | 22 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 16/0 | Amit Choudhury | 2025-08-16 | 2025-09-14 | 2025-09 | 30 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 2/0 | Radha Construction | 2025-09-03 | 2025-09-21 | 2025-09 | 19 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 29/0 | Reeta Bharti | 2025-08-06 | 2025-09-22 | 2025-09 | 48 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 47/0 | Ananya Traders-1 | 2025-09-07 | 2025-09-22 | 2025-09 | 16 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 52/0 | Punam Kumari | 2025-09-05 | 2025-09-22 | 2025-09 | 18 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 64/0 | Kongres Kumar-2 | 2025-08-31 | 2025-09-22 | 2025-09 | 23 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 48/1 | Ananya trader | 2025-09-15 | 2025-09-23 | 2025-09 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 17/6 | Amit Choudhury | 2025-09-15 | 2025-09-24 | 2025-09 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 19/0 | Sainik Trader | 2025-08-31 | 2025-09-24 | 2025-09 | 25 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 56/8 | Spotyfy-3 | 2025-08-18 | 2025-09-24 | 2025-09 | 38 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 26/0 | Gouri Shankar | 2025-09-15 | 2025-09-25 | 2025-09 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 17/0 | Maa Construction | 2025-09-11 | 2025-09-28 | 2025-09 | 18 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 25/0 | Kongres Kumar- | 2025-08-28 | 2025-09-29 | 2025-09 | 33 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 54/0 | Punam Kumari | 2025-09-25 | 2025-10-07 | 2025-10 | 13 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 64/3 | Kongres Kumar- | 2025-09-24 | 2025-10-07 | 2025-10 | 14 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 46/0 | Amit Choudhry | 2025-09-25 | 2025-10-08 | 2025-10 | 14 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 27/0 | Reeta Bharti | 2025-09-22 | 2025-10-12 | 2025-10 | 21 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 63/0 | Mahon Mahto | 2025-10-01 | 2025-10-12 | 2025-10 | 12 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 53A/1 | Spotyfy-1 | 2025-09-18 | 2025-10-13 | 2025-10 | 26 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 4/0-5/0 | 2025-10-18 00:00:00 |  | 2025-10-14 | 2025-10 |  | Missing Start Date | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 42/0 | Ananya trader | 2025-09-23 | 2025-10-14 | 2025-10 | 22 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 50/0 | Punam kumari-1 | 2025-09-25 | 2025-10-14 | 2025-10 | 20 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 53/0 | Sainik Trader | 2025-09-26 | 2025-10-14 | 2025-10 | 19 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 5/0-7/6 | 2025-10-24 00:00:00 |  | 2025-10-22 | 2025-10 |  | Missing Start Date | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 54/2 | Punam kumari-2 | 2025-10-08 | 2025-10-22 | 2025-10 | 15 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 38/0 | Pankaj Kumar | 2025-10-07 | 2025-10-25 | 2025-10 | 19 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 7/6-8B/0 | 2025-10-26 00:00:00 |  | 2025-10-25 | 2025-10 |  | Missing Start Date | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 0/0 | Maa Construction | 2025-10-03 | 2025-10-28 | 2025-10 | 26 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 34/0-35/0 | 2025-10-31 00:00:00 |  | 2025-10-28 | 2025-10 |  | Missing Start Date | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 37/0 | Unity India | 2025-09-23 | 2025-10-31 | 2025-10 | 39 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 35/0-36/0 | 2025-11-03 00:00:00 |  | 2025-11-01 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 33/0-34/0 | 2025-11-06 00:00:00 |  | 2025-11-04 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 45/0 | Amit Choudhry | 2025-10-09 | 2025-11-07 | 2025-11 | 30 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 55/0 | Punam kumari-2 | 2025-10-23 | 2025-11-07 | 2025-11 | 16 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 31/0-33/0 | 2025-11-13 00:00:00 |  | 2025-11-10 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 52/1 | Pankaj Kumar | 2025-10-26 | 2025-11-10 | 2025-11 | 16 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 2/2 | Aloriva Global | 2025-10-31 | 2025-11-13 | 2025-11 | 14 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 61/0 | Mahon mahto | 2025-09-25 | 2025-11-14 | 2025-11 | 51 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 56/6 | Pinky Dewi | 2025-09-24 | 2025-11-15 | 2025-11 | 53 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 30/0-31/0 | 2025-11-18 00:00:00 |  | 2025-11-16 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 55/1 | Punam kumari-2 | 2025-11-09 | 2025-11-17 | 2025-11 | 9 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 12/0-14/0 | 2025-11-25 00:00:00 |  | 2025-11-20 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 60/0 | Amit Choudhry | 2025-11-08 | 2025-11-29 | 2025-11 | 22 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 69A/0 | Mahon Mahto | 2025-11-15 | 2025-11-29 | 2025-11 | 15 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 20/0-21/0 | 2025-12-04 00:00:00 |  | 2025-11-30 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 49/0 | Punam kumari-1 | 2025-11-06 | 2025-11-30 | 2025-11 | 25 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 53A/0 | Aloriva Global | 2025-11-15 | 2025-11-30 | 2025-11 | 16 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 64/1 | Niranjan Singh | 2025-11-06 | 2025-11-30 | 2025-11 | 25 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 59/0 | Pinky Dewi | 2025-11-16 | 2025-12-04 | 2025-12 | 19 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 62/0 | Pankaj Kumar | 2025-11-10 | 2025-12-04 | 2025-12 | 25 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 19/0-20/0 | 2025-12-10 00:00:00 |  | 2025-12-06 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 66/1 | Punam kumari-1 | 2025-11-27 | 2025-12-07 | 2025-12 | 11 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 23/0 | Punam kumari-3 | 2025-11-17 | 2025-12-14 | 2025-12 | 28 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 66/0 | Pankaj Kumar | 2025-12-05 | 2025-12-19 | 2025-12 | 15 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 57/1 | Pinky Dewi | 2025-12-07 | 2025-12-21 | 2025-12 | 15 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 52/7 | Aloriva Global | 2025-12-06 | 2025-12-24 | 2025-12 | 19 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 68/0 | Mahon mahto | 2025-11-30 | 2026-01-19 | 2026-01 | 51 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 64/2 | Punam kumari-2 | 2026-01-20 | 2026-01-29 | 2026-01 | 10 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 0/0-2/0 | 2026-02-09 00:00:00 |  | 2026-02-06 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 69/0 | Mahon Mahto | 2026-01-20 | 2026-02-08 | 2026-02 | 20 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 2/0-3/0 | 2026-02-11 00:00:00 |  | 2026-02-10 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 36/0-37/0 | 2026-02-14 00:00:00 |  | 2026-02-10 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 14/0-17/0 | 2026-02-17 00:00:00 |  | 2026-02-14 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 37/0-38/11 | 2026-02-19 00:00:00 |  | 2026-02-16 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 8B/0-12/0 | 2026-02-20 00:00:00 |  | 2026-02-18 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 38/11-40/0 | 2026-02-22 00:00:00 |  | 2026-02-20 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 21/0-25/0 | 2026-02-26 00:00:00 |  | 2026-02-23 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 17/0-19/0 | 2026-03-02 00:00:00 |  | 2026-02-28 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 25/0-30/0 | 2026-03-02 00:00:00 |  | 2026-02-28 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 56/7 | Mahon Mahto | 2026-02-09 | 2026-03-09 | 2026-03 | 29 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 67/0 | Punam Kumari-2 | 2026-02-09 | 2026-03-23 | 2026-03 | 43 | Valid | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 40/0-47/0 | 2026-05-05 00:00:00 |  | 2026-05-03 | 2026-05 |  | Missing Start Date | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 52/1-53/0 | 2026-05-08 00:00:00 |  | 2026-05-06 | 2026-05 |  | Missing Start Date | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 416 | TA416 |  | 53/0-54/0 | 2026-05-10 00:00:00 |  | 2026-05-09 | 2026-05 |  | Missing Start Date | detail | detail_date | TA 416 - DPR - 2026-06-15.xlsx | Progress.
Mr. Arun Felbin | TA 418 | TA418 |  | 33/10 | Gang-01 (Sanjay) | 2024-12-29 | 2024-01-05 | 2024-01 |  | Invalid Negative Duration | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 40/4 | Gang-02 (Sanjay) | 2024-12-30 | 2024-01-07 | 2024-01 |  | Invalid Negative Duration | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 42/1 | GANG - 1 | 2024-06-09 | 2024-06-22 | 2024-06 | 14 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 42/2 | GANG - 1 | 2024-06-10 | 2024-06-29 | 2024-06 | 20 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 54/4 | GANG - 1 | 2024-06-29 | 2024-07-11 | 2024-07 | 13 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 41/3 | GANG-2 | 2024-07-03 | 2024-07-12 | 2024-07 | 10 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 40/1 | GANG-2 | 2024-07-01 | 2024-07-16 | 2024-07 | 16 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 55/1 | GANG-1 | 2024-06-29 | 2024-07-16 | 2024-07 | 18 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 41/2 | GANG-2 | 2024-07-07 | 2024-07-23 | 2024-07 | 17 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 55/2 | Team - 1 (Sanjay) | 2024-07-02 | 2024-07-23 | 2024-07 | 22 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 40/5 | Team - 3 (ATK-01) | 2024-07-10 | 2024-07-26 | 2024-07 | 17 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 40/2 | Team - 2 (SM Constr.) | 2024-07-14 | 2024-07-31 | 2024-07 | 18 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 54/3 | Team - 1 (Sanjay) | 2024-07-24 | 2024-08-02 | 2024-08 | 10 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 40/3 | Team - 2 (SM Constr.) | 2024-07-20 | 2024-08-03 | 2024-08 | 15 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 35/4 | Team - 3 (ATK-01) | 2024-07-18 | 2024-08-06 | 2024-08 | 20 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 41/4 | Team - 2 (SM Constr.) | 2024-07-27 | 2024-08-10 | 2024-08 | 15 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 55/3 | Team - 1 (Sanjay) | 2024-07-29 | 2024-08-10 | 2024-08 | 13 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 35/3 | Team - 3 (ATK-01) | 2024-07-18 | 2024-08-11 | 2024-08 | 25 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 35/6 | Team - 3 (ATK-01) | 2024-08-07 | 2024-08-21 | 2024-08 | 15 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 41/1 | Team - 2 (SM Constr.) | 2024-08-03 | 2024-08-26 | 2024-08 | 24 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 35/7 | Team - 3 (ATK-01) | 2024-08-09 | 2024-08-27 | 2024-08 | 19 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 35/8 | Team - 3 (ATK-01) | 2024-08-25 | 2024-09-03 | 2024-09 | 10 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 34/3 | (ATK-02) | 2024-09-02 | 2024-09-08 | 2024-09 | 7 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 40/4 | Team - 2 (SM Constr.) | 2024-08-14 | 2024-09-09 | 2024-09 | 27 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 35/11 | Team - 3 (ATK-01) | 2024-09-02 | 2024-09-10 | 2024-09 | 9 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 34/4 | (ATK-02) | 2024-09-02 | 2024-09-12 | 2024-09 | 11 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 34/1 | (ATK-02) | 2024-09-05 | 2024-09-16 | 2024-09 | 12 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 52/2 | (ATK-02) | 2024-09-12 | 2024-09-19 | 2024-09 | 8 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/12 | (ATK-02) | 2024-09-22 | 2024-09-28 | 2024-09 | 7 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/11 | (ATK-02) | 2024-09-24 | 2024-10-03 | 2024-10 | 10 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/14 | (ATK-02) | 2024-09-24 | 2024-10-11 | 2024-10 | 18 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/8 | (ATK-02) | 2024-10-08 | 2024-10-19 | 2024-10 | 12 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 34/1 | Gang-01 (Sanjay) | 2024-10-09 | 2024-10-27 | 2024-10 | 19 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 34/0 | Bindu | 2024-10-19 | 2024-10-29 | 2024-10 | 11 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/7 | LALA GANG | 2024-10-27 | 2024-11-04 | 2024-11 | 9 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/12 | Gang-01 (Sanjay) | 2024-10-28 | 2024-11-05 | 2024-11 | 9 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/9 | GANG - 4 | 2024-09-29 | 2024-11-11 | 2024-11 | 44 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 35/06 | Gang-01 (Sanjay) | 2024-11-05 | 2024-11-13 | 2024-11 | 9 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/10 | LALA GANG | 2024-09-27 | 2024-11-19 | 2024-11 | 54 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 34/3 | Gang-01 (Sanjay) | 2024-11-14 | 2024-11-19 | 2024-11 | 6 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/7 | Adarsh Gang | 2024-10-30 | 2024-11-22 | 2024-11 | 24 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 35/4 | Gang-01 (Sanjay) | 2024-11-19 | 2024-11-24 | 2024-11 | 6 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/8 | Bindu | 2024-11-08 | 2024-11-27 | 2024-11 | 20 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 40/1 | Gang-01 (Sanjay) | 2024-11-26 | 2024-12-01 | 2024-12 | 6 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 41/0 | Adarsh Gang | 2024-11-19 | 2024-12-05 | 2024-12 | 17 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 40/2 | Gang-01 (Sanjay) | 2024-12-02 | 2024-12-06 | 2024-12 | 5 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 41/3 | Gang-01 (Sanjay) | 2024-12-06 | 2024-12-11 | 2024-12 | 6 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 42/2 | Gang-02 (Sanjay) | 2024-12-03 | 2024-12-11 | 2024-12 | 9 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 41/4 | Gang-01 (Sanjay) | 2024-12-12 | 2024-12-18 | 2024-12 | 7 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 42/1 | Gang-02 (Sanjay) | 2024-12-12 | 2024-12-18 | 2024-12 | 7 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 43/0 | Bindu | 2024-11-24 | 2024-12-18 | 2024-12 | 25 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 45/02 | Bindu | 2024-12-04 | 2024-12-20 | 2024-12 | 17 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/4 | Adarsh Gang | 2024-11-15 | 2024-12-24 | 2024-12 | 40 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 34/2 | Bindu | 2024-11-13 | 2024-12-26 | 2024-12 | 44 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 35/11 | Gang-01 (Sanjay) | 2024-12-19 | 2024-12-27 | 2024-12 | 9 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 35/7 | Gang-02 (Sanjay) | 2024-12-19 | 2024-12-29 | 2024-12 | 11 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 45/0 | KAVAL CHAND | 2024-12-09 | 2024-12-30 | 2024-12 | 22 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/0 | ANURADHA | 2024-12-11 | 2025-01-11 | 2025-01 | 32 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/14 | Gang-01 (Sanjay) | 2024-01-07 | 2025-01-11 | 2025-01 | 371 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 35/0 | KEC GANG -02 | 2024-12-22 | 2025-01-13 | 2025-01 | 23 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/15 | Adarsh Gang | 2025-01-03 | 2025-01-13 | 2025-01 | 11 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 54/4 | Gang-02 (Sanjay) | 2024-01-09 | 2025-01-15 | 2025-01 | 373 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/8 | Gang-01 (Sanjay) | 2025-01-13 | 2025-01-18 | 2025-01 | 6 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 45/1 | ANURADHA | 2024-12-10 | 2025-01-21 | 2025-01 | 43 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/4 | Gang-01 (Sanjay) | 2025-01-16 | 2025-01-23 | 2025-01 | 8 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/9 | ADARSH | 2024-09-20 | 2025-01-23 | 2025-01 | 126 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 55/1 | Gang-02 (Sanjay) | 2025-01-16 | 2025-01-23 | 2025-01 | 8 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/5 | KEC GANG -02 | 2025-01-10 | 2025-01-24 | 2025-01 | 15 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 34/2 | Gang-01 (Sanjay) | 2025-01-24 | 2025-01-30 | 2025-01 | 7 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/1 | KEC GANG -02 | 2025-01-23 | 2025-02-01 | 2025-02 | 10 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 55/2 | Gang-02 (Sanjay) | 2025-01-25 | 2025-02-02 | 2025-02 | 9 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 42/0 | ANURADHA | 2025-01-17 | 2025-02-03 | 2025-02 | 18 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 35/8 | Gang-01 (Sanjay) | 2025-01-31 | 2025-02-05 | 2025-02 | 6 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/5 | Haque Constr. | 2024-11-15 | 2025-02-10 | 2025-02 | 88 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 41/1 | Gang-01 (Sanjay) | 2025-02-06 | 2025-02-11 | 2025-02 | 6 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 55/3 | Gang-02 (Sanjay) | 2025-01-24 | 2025-02-11 | 2025-02 | 19 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 32/0 | KEC GANG -02 | 2025-01-31 | 2025-02-16 | 2025-02 | 17 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 41/2 | Gang-01 (Sanjay) | 2025-02-12 | 2025-02-17 | 2025-02 | 6 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 55/0 | Haque Constr. | 2025-01-28 | 2025-02-19 | 2025-02 | 23 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 40/0 | ANURADHA | 2025-01-30 | 2025-02-20 | 2025-02 | 22 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 54/3 | Gang-01 (Sanjay) | 2025-02-12 | 2025-02-20 | 2025-02 | 9 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 55/4 | Haque Constr. | 2025-02-12 | 2025-02-24 | 2025-02 | 13 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 41/0 | Gang-01 (Sanjay) | 2025-02-21 | 2025-02-26 | 2025-02 | 6 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 37/0 | KEC GANG -02 | 2025-02-15 | 2025-03-01 | 2025-03 | 15 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 37/1 | ANURADHA | 2025-02-15 | 2025-03-02 | 2025-03 | 16 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 43/0 | Gang-01 (Sanjay) | 2025-02-26 | 2025-03-03 | 2025-03 | 6 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 48A/0 | Haque Constr. | 2025-02-23 | 2025-03-05 | 2025-03 | 11 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/0 | Gang-01 (Sanjay) | 2025-03-03 | 2025-03-08 | 2025-03 | 6 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 60/4 | Haque Constr. | 2025-03-01 | 2025-03-10 | 2025-03 | 10 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/9 | Gang-02 (Sanjay) | 2025-03-06 | 2025-03-11 | 2025-03 | 6 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 37/2 | ANURADHA | 2025-03-01 | 2025-03-12 | 2025-03 | 12 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/7 | Gang-02 (Sanjay) | 2025-03-12 | 2025-03-17 | 2025-03 | 6 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 47/1 | Haque Constr. | 2025-03-13 | 2025-03-19 | 2025-03 | 7 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/2 | KEVAL CHAND | 2025-01-01 | 2025-03-21 | 2025-03 | 80 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 45/0 | Gang-02 (Sanjay) | 2025-03-18 | 2025-03-23 | 2025-03 | 6 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 38/1 | ANURADHA | 2025-02-24 | 2025-03-24 | 2025-03 | 29 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 54/2 | Haque Constr. | 2025-03-13 | 2025-03-24 | 2025-03 | 12 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 45/1 | Gang-02 (Sanjay) | 2025-03-18 | 2025-03-28 | 2025-03 | 11 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 45/2 | Gang-02 (Sanjay) | 2025-03-28 | 2025-04-01 | 2025-04 | 5 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 38/2 | KEC GANG -04 | 2025-03-10 | 2025-04-04 | 2025-04 | 26 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 61/0 | Haque Constr. | 2025-03-20 | 2025-04-04 | 2025-04 | 16 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 40/3 | Gang-02 (Sanjay) | 2025-04-02 | 2025-04-05 | 2025-04 | 4 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 42/0 | Gang-02 (Sanjay) | 2025-04-05 | 2025-04-10 | 2025-04 | 6 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 54/1 | Haque Constr. | 2025-03-28 | 2025-04-11 | 2025-04 | 15 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 55/4 | Gang-02 (Sanjay) | 2025-04-12 | 2025-04-18 | 2025-04 | 7 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 60/2 | Haque Constr. | 2025-04-11 | 2025-04-18 | 2025-04 | 8 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/5 | Gang-01 (Sanjay) | 2025-04-11 | 2025-04-21 | 2025-04 | 11 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 60/0 | Haque Constr. | 2025-04-17 | 2025-04-25 | 2025-04 | 9 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 55/0 | Gang-02(Sanjay) | 2025-04-18 | 2025-04-26 | 2025-04 | 9 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 34/0 | Gang-01(Sanjay) | 2025-04-22 | 2025-04-29 | 2025-04 | 8 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 56/0 | Haque Constr. | 2025-04-08 | 2025-05-01 | 2025-05 | 24 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/15 | Gang-02(Sanjay) | 2025-04-27 | 2025-05-03 | 2025-05 | 7 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/13 | KEC GANG -04 | 2025-04-02 | 2025-05-05 | 2025-05 | 34 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 37/1 | Gang-01(Sanjay) | 2025-04-29 | 2025-05-07 | 2025-05 | 9 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/2 | Gang-02(Sanjay) | 2025-05-05 | 2025-05-10 | 2025-05 | 6 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 36/0 | KPK | 2025-02-27 | 2025-05-11 | 2025-05 | 74 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 59/0 | Haque Constr. | 2025-05-02 | 2025-05-14 | 2025-05 | 13 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/12 | KEC GANG -04 | 2025-04-15 | 2025-05-15 | 2025-05 | 31 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 35/0 | Gang-02(Sanjay) | 2025-05-08 | 2025-05-17 | 2025-05 | 10 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 43/2 | KEC GANG -04 | 2025-04-16 | 2025-05-19 | 2025-05 | 34 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/5 | Gang-01(Sanjay) | 2025-05-11 | 2025-05-19 | 2025-05 | 9 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 45/3 | KEC GANG -04 | 2025-04-13 | 2025-05-23 | 2025-05 | 41 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 48/1 | Haque Constr. | 2025-05-11 | 2025-05-23 | 2025-05 | 13 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 48/2 | Haque Constr. | 2025-05-14 | 2025-05-24 | 2025-05 | 11 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/11 | Gang-02(Sanjay) | 2025-05-11 | 2025-05-26 | 2025-05 | 16 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 52/0 | KPK | 2025-05-10 | 2025-05-26 | 2025-05 | 17 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 34/4 | Gang-01(Sanjay) | 2025-05-22 | 2025-05-28 | 2025-05 | 7 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 41/5 | KEC GANG -04 | 2025-05-25 | 2025-06-01 | 2025-06 | 8 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/6 | Haque Constr. |  | 2025-06-02 | 2025-06 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 40/5 | Gang-01(Sanjay) | 2025-05-29 | 2025-06-02 | 2025-06 | 5 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 35/1 | KPK | 2025-05-11 | 2025-06-03 | 2025-06 | 24 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 35/3 | Gang-02(Sanjay) | 2025-05-30 | 2025-06-04 | 2025-06 | 6 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/7 | Gang-02(Sanjay) | 2025-06-03 | 2025-06-08 | 2025-06 | 6 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 35/2 | KPK | 2025-05-26 | 2025-06-09 | 2025-06 | 15 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 35/10 | KEC GANG -05 | 2025-06-03 | 2025-06-10 | 2025-06 | 8 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 35/5 | KEC GANG -04 | 2025-06-02 | 2025-06-11 | 2025-06 | 10 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/8 | Gang-02(Sanjay) | 2025-06-09 | 2025-06-12 | 2025-06 | 4 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/0 | Haque Constr. | 2025-06-02 | 2025-06-16 | 2025-06 | 15 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/9 | Gang-01(Sanjay) | 2025-06-12 | 2025-06-17 | 2025-06 | 6 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 43/1 | KEC GANG -05 | 2025-06-12 | 2025-06-18 | 2025-06 | 7 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 35/9 | KEC GANG -04 | 2025-06-02 | 2025-06-20 | 2025-06 | 19 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 36/1 | KPK | 2025-06-09 | 2025-06-20 | 2025-06 | 12 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/2 | KEC GANG -06 | 2025-06-06 | 2025-06-21 | 2025-06 | 16 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/6 | Gang-02(Sanjay) | 2025-06-14 | 2025-06-24 | 2025-06 | 11 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 44/1 | KEC GANG -05 | 2025-06-18 | 2025-06-24 | 2025-06 | 7 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 62/0 | KEC GANG -05 | 2025-06-16 | 2025-06-25 | 2025-06 | 10 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 57/2 | KEC GANG -06 | 2025-06-23 | 2025-06-27 | 2025-06 | 5 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/3 | Haque Constr. | 2025-06-12 | 2025-06-30 | 2025-06 | 19 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/1 | KEC GANG -06 | 2025-06-25 | 2025-06-30 | 2025-06 | 6 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 36/0 | Gang-01(Sanjay) | 2025-06-19 | 2025-07-01 | 2025-07 | 13 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 39/0 | KPK | 2025-06-18 | 2025-07-01 | 2025-07 | 14 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/4 | KEC GANG - 06 | 2025-06-10 | 2025-07-02 | 2025-07 | 23 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 57/1 | KEC GANG -09 | 2025-06-29 | 2025-07-02 | 2025-07 | 4 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/3 | KEC GANG -07 | 2025-06-24 | 2025-07-03 | 2025-07 | 10 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/10 | KEC GANG -07 | 2025-06-27 | 2025-07-05 | 2025-07 | 9 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 52/1 | Haque Constr. |  | 2025-07-05 | 2025-07 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 48/0 | Haque Constr. | 2025-06-30 | 2025-07-08 | 2025-07 | 9 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/6 | KEC GANG - 08 | 2025-06-24 | 2025-07-09 | 2025-07 | 16 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 60/1 | KEC GANG -07 | 2025-07-04 | 2025-07-10 | 2025-07 | 7 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 38/2 | KEC - 01 (Barkat Ali) | 2025-07-03 | 2025-07-12 | 2025-07 | 10 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 47/0 | KPK | 2025-07-03 | 2025-07-13 | 2025-07 | 11 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 37/0 | KEC - 02 (Barkat Ali) | 2025-07-03 | 2025-07-14 | 2025-07 | 12 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 53/0 | Haque Constr. | 2025-07-04 | 2025-07-14 | 2025-07 | 11 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 43/3 | KEC GANG - 06 | 2025-07-10 | 2025-07-16 | 2025-07 | 7 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 58/0 | KEC GANG - 09 | 2025-07-03 | 2025-07-16 | 2025-07 | 14 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 57/3 | Haque Constr. | 2025-07-15 | 2025-07-18 | 2025-07 | 4 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 37/2 | KEC - 01 (Barkat Ali) | 2025-07-14 | 2025-07-20 | 2025-07 | 7 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 44/0 | KEC GANG - 08 | 2025-06-25 | 2025-07-20 | 2025-07 | 26 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 40/0 | Gang-02(Sanjay) | 2025-07-03 | 2025-07-21 | 2025-07 | 19 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 38/1 | KEC - 02 (Barkat Ali) | 2025-07-15 | 2025-07-23 | 2025-07 | 9 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/11 | KEC GANG - 06 | 2025-06-28 | 2025-07-23 | 2025-07 | 26 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 56/1 | KEC GANG -06 |  | 2025-07-29 | 2025-07 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 35/5 | KEC - 01 (Barkat Ali) | 2025-07-22 | 2025-07-30 | 2025-07 | 9 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 35/9 | KEC - 02 (Barkat Ali) | 2025-07-21 | 2025-07-31 | 2025-07 | 11 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 56/2 | KEC GANG -06 -HQ | 2025-08-01 | 2025-08-03 | 2025-08 | 3 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 41/5 | Gang-02(Sanjay) / KEC - 02 (Barkat Ali) | 2025-07-24 | 2025-08-06 | 2025-08 | 14 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 56/3 | KEC GANG -07 - HQ | 2025-08-02 | 2025-08-06 | 2025-08 | 5 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 35/1 | SAVITHA | 2025-07-21 | 2025-08-07 | 2025-08 | 18 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 35/2 | KEC - 01 (Barkat Ali) | 2025-06-29 | 2025-08-07 | 2025-08 | 40 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 48A/0 | SUBHASH | 2025-08-07 | 2025-08-16 | 2025-08 | 10 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 35/10 | KEC - 01 (Barkat Ali) | 2025-08-07 | 2025-08-17 | 2025-08 | 11 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 36/1 | KEC - 02 (Barkat Ali) | 2025-08-06 | 2025-08-19 | 2025-08 | 14 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/13 | SAVITHA | 2025-08-09 | 2025-08-22 | 2025-08 | 14 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 43/1 | KEC - 01 (Barkat Ali) | 2025-08-18 | 2025-08-26 | 2025-08 | 9 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/3 | KEC - 02 (Barkat Ali) | 2025-08-22 | 2025-08-26 | 2025-08 | 5 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 52/0 | SUBHASH | 2025-08-19 | 2025-08-26 | 2025-08 | 8 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 54/0 | KEC GANG -07 - HQ | 2025-08-23 | 2025-08-29 | 2025-08 | 7 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 48/1 | SUBHASH | 2025-08-16 | 2025-09-01 | 2025-09 | 17 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/12 | SUBHASH | 2025-09-03 | 2025-09-07 | 2025-09 | 5 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/3 | KEC - 01 (Barkat Ali) | 2025-08-31 | 2025-09-10 | 2025-09 | 11 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 62/0 | KEC - 02 (Barkat Ali) | 2025-09-01 | 2025-09-12 | 2025-09 | 12 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 48/2 | SUBHASH | 2025-09-09 | 2025-09-13 | 2025-09 | 5 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/2 | M/s TOFIT | 2025-09-12 | 2025-09-22 | 2025-09 | 11 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 53/0 | SUBHASH | 2025-09-16 | 2025-09-23 | 2025-09 | 8 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 61/0 | KEC - 02 (Barkat Ali) | 2025-09-14 | 2025-09-25 | 2025-09 | 12 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 42/0 - 43/0 | 2025-10-13 00:00:00 |  | 2025-09-28 | 2025-09 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/1 | M/s TOFIT | 2025-09-22 | 2025-09-30 | 2025-09 | 9 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 45/3 | M/S MDPL | 2025-09-09 | 2025-09-30 | 2025-09 | 22 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 44/0 | SUBHASH | 2025-09-25 | 2025-10-01 | 2025-10 | 7 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 56/0 | SAVITHA | 2025-09-05 | 2025-10-03 | 2025-10 | 29 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 54/1 | KEC - 02 (Barkat Ali) | 2025-09-28 | 2025-10-05 | 2025-10 | 8 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 41/0 - 42/0 | 2025-12-22 00:00:00 |  | 2025-10-06 | 2025-10 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 32/0 | M/s TOFIT | 2025-10-04 | 2025-10-17 | 2025-10 | 14 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 54/0 | M/S MDPL | 2025-09-29 | 2025-10-17 | 2025-10 | 19 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 60/2 | KEC - 02 (Barkat Ali) | 2025-08-26 | 2025-10-17 | 2025-10 | 53 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 60/4 | KEC - 02 (Barkat Ali) | 2025-10-18 | 2025-10-27 | 2025-10 | 10 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 36/0 - 36/1 | 2025-11-10 00:00:00 |  | 2025-11-03 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/10 | KEC - 02 (Barkat Ali) | 2025-10-29 | 2025-11-06 | 2025-11 | 9 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/0 | M/s TOFIT | 2025-10-16 | 2025-11-07 | 2025-11 | 23 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 55/6 | GANG - A1 | 2025-11-02 | 2025-11-10 | 2025-11 | 9 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/6 | KEC - 02 (Barkat Ali) | 2025-11-04 | 2025-11-12 | 2025-11 | 9 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 43/2 | M/S MDPL | 2025-11-06 | 2025-11-13 | 2025-11 | 8 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 55/5 | GANG - A2 | 2025-11-04 | 2025-11-15 | 2025-11 | 12 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 35/0 - 36/0 | 2025-12-05 00:00:00 |  | 2025-11-17 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 48/0 | M/s TOFIT | 2025-11-11 | 2025-11-18 | 2025-11 | 8 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/4 | KEC - 02 (Barkat Ali) | 2025-11-12 | 2025-11-21 | 2025-11 | 10 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 51/0 | GANG - A1 | 2025-11-12 | 2025-11-21 | 2025-11 | 10 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 50/0 | GANG - A2 | 2025-11-13 | 2025-11-25 | 2025-11 | 13 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 47/1 | M/s TOFIT | 2025-11-21 | 2025-11-27 | 2025-11 | 7 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 48A/1 | GANG - A1 | 2025-11-24 | 2025-11-27 | 2025-11 | 4 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 39/0 | M/S MDPL | 2025-10-16 | 2025-11-29 | 2025-11 | 45 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 34/0 - 35/0 | 2025-12-05 00:00:00 |  | 2025-11-30 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 44/1 | KEC - 02 (Barkat Ali) | 2025-11-23 | 2025-12-02 | 2025-12 | 10 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 60/0 | M/s TOFIT | 2025-11-30 | 2025-12-07 | 2025-12 | 8 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 47/0 | M/S MDPL | 2025-12-01 | 2025-12-10 | 2025-12 | 10 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 49/0 | GANG - A1 | 2025-12-03 | 2025-12-10 | 2025-12 | 8 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 48A/2 | GANG - A1 (M) | 2025-12-10 | 2025-12-13 | 2025-12 | 4 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/11 | KEC - 02 (Barkat Ali) | 2025-12-04 | 2025-12-14 | 2025-12 | 11 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 56/1 | M/s TOFIT | 2025-12-07 | 2025-12-14 | 2025-12 | 8 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 52/1 | M/S MDPL | 2025-12-10 | 2025-12-15 | 2025-12 | 6 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 59/1 | GANG - A2 | 2025-12-12 | 2025-12-16 | 2025-12 | 5 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 56/2 | M/s TOFIT | 2025-12-15 | 2025-12-19 | 2025-12 | 5 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 57/0 | GANG - A1 (M) | 2025-12-13 | 2025-12-20 | 2025-12 | 8 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 52/2 | M/S MDPL | 2025-12-17 | 2025-12-22 | 2025-12 | 6 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 60/3 | GANG - A2 | 2025-12-18 | 2025-12-23 | 2025-12 | 6 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 60/1 | KEC - 02 (Barkat Ali) | 2025-12-16 | 2025-12-25 | 2025-12 | 10 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 40/0 - 41/0 | 2025-12-30 00:00:00 |  | 2025-12-26 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 56/3 | M/s TOFIT | 2025-12-20 | 2025-12-26 | 2025-12 | 7 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 48A/1 | M/S MDPL | 2025-12-23 | 2025-12-30 | 2025-12 | 8 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 48A/2 | M/S MDPL | 2025-12-31 | 2026-01-06 | 2026-01 | 7 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 57/1 | KEC - 02 (Barkat Ali) | 2025-12-26 | 2026-01-07 | 2026-01 | 13 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 58/0 | M/s TOFIT | 2025-12-26 | 2026-01-08 | 2026-01 | 14 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 63/0 | GANG - A2 | 2026-01-03 | 2026-01-09 | 2026-01 | 7 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 55/6 | M/s TOFIT | 2026-01-08 | 2026-01-15 | 2026-01 | 8 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 57/3 | KEC - 02 (Barkat Ali) | 2026-01-08 | 2026-01-15 | 2026-01 | 8 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 59/0 | M/S MDPL | 2026-01-07 | 2026-01-18 | 2026-01 | 12 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 60/3 | M/s TOFIT | 2026-01-16 | 2026-01-20 | 2026-01 | 5 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/6 - 34/0 | 2026-01-26 00:00:00 |  | 2026-01-27 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 55/5 | M/S MDPL | 2026-01-20 | 2026-01-27 | 2026-01 | 8 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 54/2 | M/s TOFIT | 2026-01-22 | 2026-01-28 | 2026-01 | 7 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/5 - 33/6 | 2026-01-26 00:00:00 |  | 2026-01-30 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 57/0 | KEC - 02 (Barkat Ali) | 2025-01-16 | 2026-01-30 | 2026-01 | 380 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 57/2 | M/s TOFIT | 2026-01-29 | 2026-02-04 | 2026-02 | 7 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 49/0 | M/S MDPL | 2026-01-28 | 2026-02-05 | 2026-02 | 9 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 59/1 | KEC - 03 (Barkat Ali) |  | 2026-02-05 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 33/0 - 33/5 | 2026-02-07 00:00:00 |  | 2026-02-09 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 39/0-40/0 | 2026-02-09 00:00:00 |  | 2026-02-10 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 38/0 | GANG - A2 | 2026-02-11 | 2026-02-17 | 2026-02 | 7 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 51/0 | KEC - 02 (Barkat Ali) | 2026-02-05 | 2026-02-17 | 2026-02 | 13 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 63/0 | M/s TOFIT | 2026-02-05 | 2026-02-17 | 2026-02 | 13 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 32/0-33/0 | 2026-02-16 00:00:00 |  | 2026-02-22 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 50/0 | M/S MDPL | 2026-02-04 | 2026-02-27 | 2026-02 | 24 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 43/3 | KEC - 02 (Barkat Ali) | 2026-02-20 | 2026-02-28 | 2026-02 | 9 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 45/1-46/0 | 2026-03-22 00:00:00 |  | 2026-03-03 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 43/0 - 44/0 | 2026-03-09 00:00:00 |  | 2026-03-11 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 45/0 - 45/1 | 2026-03-06 00:00:00 |  | 2026-03-12 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 44/0-45/0 | 2026-03-14 00:00:00 |  | 2026-03-18 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 56/0-56/3 | 2026-06-05 00:00:00 |  | 2026-03-31 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 38/0 | M/S MDPL | 2026-02-24 | 2026-04-01 | 2026-04 | 37 | Valid | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 46/1 | M/S MDPL |  | 2026-04-09 | 2026-04 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 61/0-62/0 | 2026-06-15 00:00:00 |  | 2026-04-15 | 2026-04 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 63/0-GNTY | 2026-04-16 00:00:00 |  | 2026-04-18 | 2026-04 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 55/0-56/0 | 2026-05-02 00:00:00 |  | 2026-05-03 | 2026-05 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 37/0-38/0 | 2026-05-26 00:00:00 |  | 2026-05-12 | 2026-05 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 36/01 - 37/00 | 2026-05-24 00:00:00 |  | 2026-05-23 | 2026-05 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 38/0-39/0 | 2026-05-30 00:00:00 |  | 2026-05-26 | 2026-05 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 52/00 - 53/00 | 2026-06-15 00:00:00 |  | 2026-06-06 | 2026-06 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 51/00 - 52/00 | Unassigned |  | 2026-06-08 | 2026-06 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 56/03 - 57/00 | 2026-06-05 00:00:00 |  | 2026-06-09 | 2026-06 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. Arun Felbin | TA 418 | TA418 |  | 62/0-63/0 | 2026-06-15 00:00:00 |  | 2026-06-26 | 2026-06 |  | Missing Start Date | detail | detail_date | TA 418 - DPR - 2026-06-16.xlsx | Progress
Mr. NK Gupta | TA 419 | TA419 |  | 19/5 | Garg Energy |  | 2024-05-24 | 2024-05 |  | Missing Start Date | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 19/4 | Garg Energy | 2024-05-21 | 2024-05-28 | 2024-05 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 19/3 | Garg Energy | 2024-05-21 | 2024-05-29 | 2024-05 | 9 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 19/1 | Garg Energy | 2024-05-29 | 2024-06-01 | 2024-06 | 4 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 17/2 | Garg Energy | 2024-05-30 | 2024-06-04 | 2024-06 | 6 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 17/1 | Garg Energy | 2024-05-30 | 2024-06-07 | 2024-06 | 9 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 19/2 | Garg Energy | 2024-06-04 | 2024-06-09 | 2024-06 | 6 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 20/1 | Garg Energy | 2024-06-14 | 2024-06-21 | 2024-06 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 20/2 | Garg Energy | 2024-06-16 | 2024-06-23 | 2024-06 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 11/4 | Bala Ji | 2024-06-21 | 2024-06-26 | 2024-06 | 6 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 22/2 | Garg Energy | 2024-06-24 | 2024-06-29 | 2024-06 | 6 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 11/3 | Bala Ji | 2024-06-25 | 2024-06-30 | 2024-06 | 6 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 12/1 | Bala Ji | 2024-07-01 | 2024-07-07 | 2024-07 | 7 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 23/1 | Garg Energy | 2024-06-27 | 2024-07-09 | 2024-07 | 13 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 22/3 | Garg Energy | 2024-06-29 | 2024-07-10 | 2024-07 | 12 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 6/10 | Bala Ji | 2024-07-06 | 2024-07-10 | 2024-07 | 5 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 23/2 | Garg Energy | 2024-07-09 | 2024-07-14 | 2024-07 | 6 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 6/9 | Bala Ji | 2024-07-10 | 2024-07-14 | 2024-07 | 5 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 6/8 | Bala Ji | 2024-07-12 | 2024-07-16 | 2024-07 | 5 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 6/12 | Bala Ji | 2024-07-15 | 2024-07-18 | 2024-07 | 4 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 23/3 | Garg Energy | 2024-07-10 | 2024-07-19 | 2024-07 | 10 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 3/2 | Kirti Construction | 2024-07-05 | 2024-07-21 | 2024-07 | 17 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 26/4 | Garg Energy | 2024-07-15 | 2024-07-22 | 2024-07 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 26/3 | Garg Energy | 2024-07-13 | 2024-07-25 | 2024-07 | 13 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 6/3 | Bala Ji | 2024-07-20 | 2024-07-25 | 2024-07 | 6 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 3/3 | Kirti Construction | 2024-07-21 | 2024-07-26 | 2024-07 | 6 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 6/6 | Bala Ji | 2024-07-23 | 2024-07-29 | 2024-07 | 7 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 24/1 | Garg Energy | 2024-07-23 | 2024-07-30 | 2024-07 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 3/5 | Kirti Construction | 2024-07-25 | 2024-07-30 | 2024-07 | 6 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 3/4 | Kirti Construction | 2024-07-31 | 2024-08-04 | 2024-08 | 5 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 6/2 | Bala Ji | 2024-07-28 | 2024-08-04 | 2024-08 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 26/2 | Garg Energy | 2024-07-31 | 2024-08-07 | 2024-08 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 6/5 | Bala Ji | 2024-07-31 | 2024-08-10 | 2024-08 | 11 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 4/1 | Kirti Construction | 2024-08-04 | 2024-08-11 | 2024-08 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 6/11 | Garg Energy | 2024-08-11 | 2024-08-14 | 2024-08 | 4 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 5/1 | Kirti Construction | 2024-08-04 | 2024-08-17 | 2024-08 | 14 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 5/3 | Surjeet | 2024-08-11 | 2024-08-28 | 2024-08 | 18 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 27/2 | Garg Energy | 2024-08-27 | 2024-09-01 | 2024-09 | 6 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 0D/3 | Surjeet | 2024-08-29 | 2024-09-03 | 2024-09 | 6 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 5/2 | Kirti Construction | 2024-08-30 | 2024-09-04 | 2024-09 | 6 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 0D/2 | Surjeet | 2024-09-05 | 2024-09-10 | 2024-09 | 6 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 12/0 | Garg Energy | 2024-09-09 | 2024-09-16 | 2024-09 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 4/0 | Kirti Construction | 2024-09-04 | 2024-09-16 | 2024-09 | 13 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 0E/2 | TDCL | 2024-09-09 | 2024-09-18 | 2024-09 | 10 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 7/0 | Garg Energy | 2024-09-18 | 2024-09-21 | 2024-09 | 4 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 6/1 | Kirti Construction | 2024-09-18 | 2024-09-23 | 2024-09 | 6 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 0E/1 | TDCL | 2024-09-18 | 2024-09-24 | 2024-09 | 7 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 27/1 | Garg Energy | 2024-09-02 | 2024-09-26 | 2024-09 | 25 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 24/2 | Garg Energy | 2024-07-27 | 2024-09-27 | 2024-09 | 63 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 0B/2 | NV Infra | 2024-09-11 | 2024-09-28 | 2024-09 | 18 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 0D/1 | TDCL | 2024-09-23 | 2024-09-30 | 2024-09 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 0D/5 | Surjeet | 2024-09-15 | 2024-09-30 | 2024-09 | 16 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 12A/0 | Garg Energy | 2024-09-22 | 2024-09-30 | 2024-09 | 9 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 5/0 | Kirti Construction | 2024-09-23 | 2024-10-04 | 2024-10 | 12 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 0B/3 | NV Infra | 2024-09-30 | 2024-10-07 | 2024-10 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 23/0 | Garg Energy | 2024-09-30 | 2024-10-07 | 2024-10 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 0D/4 | Surjeet | 2024-09-25 | 2024-10-11 | 2024-10 | 17 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 5/4 | Kirti Construction | 2024-10-07 | 2024-10-11 | 2024-10 | 5 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 28/0 | Garg Energy | 2024-10-06 | 2024-10-12 | 2024-10 | 7 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 0D/0 | TDCL | 2024-09-29 | 2024-10-14 | 2024-10 | 16 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 27/3 | Garg Energy | 2024-10-11 | 2024-10-14 | 2024-10 | 4 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 6/4 | Kirti Construction | 2024-10-09 | 2024-10-15 | 2024-10 | 7 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 26/5 | Garg Energy | 2024-10-08 | 2024-10-16 | 2024-10 | 9 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 26/6 | Garg Energy | 2024-10-14 | 2024-10-19 | 2024-10 | 6 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 0B/1 | NV Infra | 2024-09-18 | 2024-10-22 | 2024-10 | 35 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 0C/0 | NV Infra | 2024-10-07 | 2024-10-25 | 2024-10 | 19 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 0C/1 | TDCL | 2024-10-19 | 2024-10-25 | 2024-10 | 7 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 27/0 | Garg Energy | 2024-10-14 | 2024-10-25 | 2024-10 | 12 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 24/0 | Garg Energy | 2024-10-17 | 2024-10-27 | 2024-10 | 11 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 6/0 | Kirti Construction | 2024-10-07 | 2024-10-27 | 2024-10 | 21 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 0E/0 | Shyam | 2024-10-10 | 2024-10-28 | 2024-10 | 19 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 0B/0 | Shyam Ent | 2024-10-20 | 2024-11-08 | 2024-11 | 20 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 20/0 | Garg Energy | 2024-10-17 | 2024-11-08 | 2024-11 | 23 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 18/0 | NV Infra | 2024-10-25 | 2024-11-09 | 2024-11 | 16 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 19/0 | Garg Energy | 2024-10-19 | 2024-11-13 | 2024-11 | 26 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 24/3 | Garg Energy | 2024-11-15 | 2024-11-20 | 2024-11 | 6 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 11/2 | Kirti Construction | 2024-10-19 | 2024-11-22 | 2024-11 | 35 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 12/2 | TDCL | 2024-10-28 | 2024-11-22 | 2024-11 | 26 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 26/1 | NV Infra | 2025-11-15 | 2024-11-22 | 2024-11 |  | Invalid Negative Duration | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 17/0 | Garg Energy | 2024-11-20 | 2024-11-27 | 2024-11 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 6/7 | Surjeet | 2024-11-08 | 2024-11-28 | 2024-11 | 21 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 3/1 | Kirti Construction | 2024-11-26 | 2024-11-29 | 2024-11 | 4 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 36/6 | Garg Energy | 2024-11-13 | 2024-11-29 | 2024-11 | 17 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 7/1 | Shyam Infra | 2024-11-19 | 2024-11-29 | 2024-11 | 11 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 0F/0 | Shyam Ent | 2024-11-15 | 2024-11-30 | 2024-11 | 16 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 36/7 | NV Infra | 2024-11-13 | 2024-12-02 | 2024-12 | 20 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 11/1 | Kirti Construction | 2024-12-02 | 2024-12-09 | 2024-12 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 15A/0 | Garg Energy | 2024-12-03 | 2024-12-10 | 2024-12 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 22/1 | Shyam Infra | 2024-12-02 | 2024-12-10 | 2024-12 | 9 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 0G/0 | NV Infra | 2024-11-27 | 2024-12-11 | 2024-12 | 15 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 16/0 | Garg Energy | 2024-12-05 | 2024-12-14 | 2024-12 | 10 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 28/1 | TDCL | 2024-12-08 | 2024-12-17 | 2024-12 | 10 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 30/1 | Shyam Infra | 2024-12-12 | 2024-12-21 | 2024-12 | 10 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 15/0 | Kirti Construction | 2024-12-12 | 2024-12-23 | 2024-12 | 12 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 31/0 | Garg Energy | 2024-12-11 | 2024-12-23 | 2024-12 | 13 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 0A/0 (CT) | Shyam Ent | 2024-12-02 | 2024-12-24 | 2024-12 | 23 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 31/1 | TDCL | 2024-12-11 | 2024-12-24 | 2024-12 | 14 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 1/0 | Kirti Construction | 2024-12-23 | 2025-01-04 | 2025-01 | 13 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 0H/0 | NV Infra | 2024-12-21 | 2025-01-09 | 2025-01 | 20 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 0G/1 | Shyam Infra | 2024-12-21 | 2025-01-15 | 2025-01 | 26 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 10/0 | Garg Energy | 2025-01-02 | 2025-01-18 | 2025-01 | 17 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 22/0 | Garg Energy | 2025-01-15 | 2025-01-25 | 2025-01 | 11 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 36/1 | NV Infra | 2025-01-18 | 2025-01-28 | 2025-01 | 11 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 36/2 | Garg Energy | 2025-01-25 | 2025-01-29 | 2025-01 | 5 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 36/4 | Garg Energy | 2025-01-28 | 2025-02-07 | 2025-02 | 11 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 36/8 | NV Infra | 2025-01-10 | 2025-02-07 | 2025-02 | 29 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 38/7 | Garg Energy | 2025-01-29 | 2025-02-11 | 2025-02 | 14 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 62/2 | Saran Communication | 2025-01-16 | 2025-02-13 | 2025-02 | 29 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 38/10 | Garg Energy | 2025-02-08 | 2025-02-15 | 2025-02 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 38/5 | NV Infra | 2025-01-29 | 2025-02-20 | 2025-02 | 23 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 62/1 | Garg Energy | 2025-02-11 | 2025-02-22 | 2025-02 | 12 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 38/6 | Shre Shyam | 2025-02-14 | 2025-02-28 | 2025-02 | 15 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 38/8 | NV Infra | 2025-02-06 | 2025-02-28 | 2025-02 | 23 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 62/5 | Garg Energy | 2025-02-18 | 2025-02-28 | 2025-02 | 11 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 62/4 | Garg Energy | 2025-03-01 | 2025-03-05 | 2025-03 | 5 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 38/0 | NV Infra | 2025-02-20 | 2025-03-15 | 2025-03 | 24 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 38/11 | NV Infra | 2025-03-23 | 2025-03-26 | 2025-03 | 4 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 38/9 | Shree Shyam | 2025-03-23 | 2025-03-27 | 2025-03 | 5 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 34/0 | Garg Energy | 2025-03-25 | 2025-03-29 | 2025-03 | 5 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 40/0 | Garg Energy | 2025-03-23 | 2025-04-05 | 2025-04 | 14 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 20/3 | NV Infra | 2025-04-02 | 2025-04-08 | 2025-04 | 7 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 40/6 | Garg Energy | 2025-04-07 | 2025-04-08 | 2025-04 | 2 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 62/3 | GRD Enterprises | 2025-03-24 | 2025-04-08 | 2025-04 | 16 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 40/3 | Garg Energy | 2025-03-27 | 2025-04-11 | 2025-04 | 16 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 40/7 | Garg Energy | 2025-04-09 | 2025-04-14 | 2025-04 | 6 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 40/5 | Garg Energy | 2025-04-12 | 2025-04-17 | 2025-04 | 6 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 40/4 | Garg Energy | 2025-04-01 | 2025-04-21 | 2025-04 | 21 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 40/2 | NV Infra | 2025-04-15 | 2025-04-22 | 2025-04 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 46/4 | GRD Enterprise | 2025-04-09 | 2025-04-22 | 2025-04 | 14 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 40/9 | Tyagi Const | 2025-04-06 | 2025-04-23 | 2025-04 | 18 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 41/1 | Garg Energy | 2025-04-19 | 2025-04-24 | 2025-04 | 6 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 41/7 | Tyagi Const | 2025-04-23 | 2025-04-28 | 2025-04 | 6 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 41/5 | NV Infra | 2025-04-25 | 2025-04-29 | 2025-04 | 5 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 41/8 | Tyagi Const | 2025-04-28 | 2025-05-04 | 2025-05 | 7 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 41/0 | Garg Energy | 2025-04-23 | 2025-05-07 | 2025-05 | 15 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 41/3 | Garg Energy | 2025-05-06 | 2025-05-11 | 2025-05 | 6 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 41/4 | Tyagi Const | 2025-05-04 | 2025-05-12 | 2025-05 | 9 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 84/1 | GRD Enterprises | 2025-04-29 | 2025-05-15 | 2025-05 | 17 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 25/0 | Garg Energy | 2025-05-12 | 2025-05-19 | 2025-05 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 83/6 | MS Construction | 2025-05-03 | 2025-05-19 | 2025-05 | 17 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 26/0 | Garg Energy | 2025-05-15 | 2025-05-21 | 2025-05 | 7 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 83/7 | MS Construction | 2025-04-29 | 2025-06-05 | 2025-06 | 38 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 35/0 | Garg Energy | 2025-05-29 | 2025-06-06 | 2025-06 | 9 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 3/0 | NV Infra | 2025-05-12 | 2025-06-07 | 2025-06 | 27 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 36/0 | Garg Energy | 2025-05-19 | 2025-06-07 | 2025-06 | 20 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 34/1 | Garg Energy | 2025-06-04 | 2025-06-08 | 2025-06 | 5 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 29/0 | Garg Energy | 2025-06-09 | 2025-06-15 | 2025-06 | 7 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 83/5 | MS Construction | 2025-06-05 | 2025-06-19 | 2025-06 | 15 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 11/0 | Kirti Construction | 2025-05-21 | 2025-06-23 | 2025-06 | 34 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 78/3 | Garg Energy | 2025-06-11 | 2025-06-26 | 2025-06 | 16 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 30/0 | Garg Energy | 2025-06-14 | 2025-06-27 | 2025-06 | 14 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 84/4 | MS Construction | 2025-06-20 | 2025-07-04 | 2025-07 | 15 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 21/0 | Garg Energy | 2025-06-22 | 2025-07-08 | 2025-07 | 17 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 2/0 | NV Infra | 2025-06-01 | 2025-07-14 | 2025-07 | 44 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 9/0 | Garg Energy | 2025-07-08 | 2025-07-23 | 2025-07 | 16 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 8/0 | Garg Energy | 2025-07-15 | 2025-07-28 | 2025-07 | 14 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 41/6 | Garg Energy | 2025-07-24 | 2025-08-03 | 2025-08 | 11 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 46/0 | Garg Energy | 2025-08-01 | 2025-08-31 | 2025-08 | 31 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 46/1 | Garg Energy | 2025-09-05 | 2025-09-12 | 2025-09 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 46/2 | Garg Energy | 2025-09-11 | 2025-09-16 | 2025-09 | 6 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 46/3 | Garg Energy | 2025-09-15 | 2025-09-19 | 2025-09 | 5 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 31/2 | Garg Energy | 2025-09-26 | 2025-10-03 | 2025-10 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 78/1 | Virendra | 2025-09-16 | 2025-10-03 | 2025-10 | 18 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 45/0 | Garg Energy | 2025-09-21 | 2025-10-09 | 2025-10 | 19 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 78/0 | Virendra | 2025-10-01 | 2025-10-23 | 2025-10 | 23 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 76/3 | NV Infra | 2025-09-24 | 2025-10-24 | 2025-10 | 31 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 83/1 | D&P | 2025-10-05 | 2025-10-30 | 2025-10 | 26 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 43/5 | MS Construction | 2025-10-28 | 2025-11-04 | 2025-11 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 43/3 | GRD Enterprises 2 | 2025-11-01 | 2025-11-09 | 2025-11 | 9 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 43/6 | MS Construction | 2025-11-03 | 2025-11-09 | 2025-11 | 7 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 63/5 | NV Infra | 2025-11-02 | 2025-11-09 | 2025-11 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 43/0 | GRD Enterprises1 | 2025-10-20 | 2025-11-10 | 2025-11 | 22 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 54/5 | Virendra | 2025-11-04 | 2025-11-11 | 2025-11 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 36/10 | Garg Energy | 2025-11-04 | 2025-11-13 | 2025-11 | 10 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 43/1 | GRD Enterprises 1 | 2025-11-07 | 2025-11-13 | 2025-11 | 7 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 43/2 | GRD Enterprises 2 | 2025-11-09 | 2025-11-18 | 2025-11 | 10 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 83/0 | D&P | 2025-08-30 | 2025-11-20 | 2025-11 | 83 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 36/9 | Ahlawat Const | 2025-11-06 | 2025-11-23 | 2025-11 | 18 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 84/3 | Tyagi Construction | 2025-11-18 | 2025-11-24 | 2025-11 | 7 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 43/4 | MS Construction | 2025-11-14 | 2025-11-25 | 2025-11 | 12 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 54/6 | Virendra | 2025-11-02 | 2025-11-25 | 2025-11 | 24 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 12A/1 | GRD | 2025-11-21 | 2025-11-28 | 2025-11 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 83/8 | D&B | 2025-11-23 | 2025-11-28 | 2025-11 | 6 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 63/4 | DCLCSL( Ravindra) | 2025-11-11 | 2025-11-29 | 2025-11 | 19 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 54/2 | Ahlawat Cpnstruction | 2025-11-25 | 2025-11-30 | 2025-11 | 6 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 55/6 | GRD 2 | 2025-11-27 | 2025-12-04 | 2025-12 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 33/1 | GRD 1 | 2025-11-30 | 2025-12-07 | 2025-12 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 54/4 | Ahlawat Cpnstruction | 2025-12-03 | 2025-12-07 | 2025-12 | 5 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 63A/0 | NV Infra | 2025-10-27 | 2025-12-07 | 2025-12 | 42 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 63/2 | Utkarsh Const | 2025-12-04 | 2025-12-09 | 2025-12 | 6 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 55/5 | GRD 2 | 2025-12-05 | 2025-12-12 | 2025-12 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 54/3 | Ahlawat Cpnstruction | 2025-12-02 | 2025-12-13 | 2025-12 | 12 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 84/5 | D&B | 2025-12-07 | 2025-12-15 | 2025-12 | 9 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 54/7 | Virendra | 2025-12-10 | 2025-12-18 | 2025-12 | 9 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 64/1 | MS Construction | 2025-12-06 | 2025-12-18 | 2025-12 | 13 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 78/4 | Bajrang Const | 2025-12-08 | 2025-12-18 | 2025-12 | 11 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 57/1 | GRD 2 | 2025-12-18 | 2025-12-20 | 2025-12 | 3 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 59/1 | Amit Yadav 1 | 2025-12-18 | 2025-12-26 | 2025-12 | 9 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 84/0 | D&B | 2025-12-15 | 2025-12-26 | 2025-12 | 12 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 55/1 | Virendra | 2025-11-19 | 2025-12-27 | 2025-12 | 39 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 63/6 | NV Infra | 2025-12-10 | 2025-12-28 | 2025-12 | 19 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 36/5 | GRD 1 | 2025-12-19 | 2025-12-31 | 2025-12 | 13 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 63/0 | DCLCSL( Ravindra) | 2025-12-18 | 2025-12-31 | 2025-12 | 14 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 63/1 | Bajrang Const | 2025-12-24 | 2026-01-02 | 2026-01 | 10 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 63B/6 | MS Construction | 2025-12-18 | 2026-01-02 | 2026-01 | 16 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 62/0 | GRD Enterprises | 2025-12-19 | 2026-01-04 | 2026-01 | 17 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 64/5 | Sherawali Const | 2025-12-18 | 2026-01-04 | 2026-01 | 18 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 84A/0 | D&B | 2025-12-10 | 2026-01-07 | 2026-01 | 29 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 36/3 | GRD 1 | 2025-12-24 | 2026-01-09 | 2026-01 | 17 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 55/4 | GRD 2 | 2025-12-23 | 2026-01-10 | 2026-01 | 19 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 55/0 | Virendra | 2025-12-25 | 2026-01-14 | 2026-01 | 21 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 63/3 | DCLCSL( Ravindra) |  | 2026-01-17 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 55/3 | GRD 2 | 2026-01-11 | 2026-01-18 | 2026-01 | 8 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 64A/0 | D&B | 2025-12-18 | 2026-01-18 | 2026-01 | 32 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 38/1 | GRD 1 | 2026-01-11 | 2026-01-24 | 2026-01 | 14 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 64/0 | MS Construction | 2025-12-29 | 2026-02-01 | 2026-02 | 35 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 55/2 | GRD 2 | 2026-01-16 | 2026-02-07 | 2026-02 | 23 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 63B/1 | NV Infra | 2026-01-01 | 2026-02-07 | 2026-02 | 38 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 64/2 | Sherawali Const | 2026-01-07 | 2026-02-07 | 2026-02 | 32 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 78A/0 | Bajrang Const | 2026-01-03 | 2026-02-13 | 2026-02 | 42 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 77/0 | DCLCSL( Ravindra) | 2026-01-20 | 2026-02-19 | 2026-02 | 31 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 42/0 | GRD 1 | 2026-02-04 | 2026-02-22 | 2026-02 | 19 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 63B/0 | NV Infra | 2026-01-17 | 2026-03-03 | 2026-03 | 46 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 54/1 | Ravinder | 2026-02-26 | 2026-03-16 | 2026-03 | 19 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 33/0 | Utkarsh Const | 2026-02-04 | 2026-03-18 | 2026-03 | 43 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 78/2 | D&V | 2026-03-16 | 2026-03-25 | 2026-03 | 10 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 40/8 | Shiv Shakti | 2026-02-12 | 2026-03-27 | 2026-03 | 44 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 81/0 | D&V | 2026-01-16 | 2026-03-29 | 2026-03 | 73 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 13/0 | D&V | 2026-03-20 | 2026-04-15 | 2026-04 | 27 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 32/0 | Ravindra | 2026-03-25 | 2026-04-20 | 2026-04 | 27 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 14/0 | GRD 1 | 2026-01-18 | 2026-04-23 | 2026-04 | 96 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 80/0 | D&V | 2026-04-01 | 2026-04-25 | 2026-04 | 25 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 76/2 | Piroth and Sons | 2026-03-25 | 2026-04-28 | 2026-04 | 35 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 14/1 | GRD 1 | 2026-04-23 | 2026-04-29 | 2026-04 | 7 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 40/1 | Shiv Shakti | 2026-04-01 | 2026-04-29 | 2026-04 | 29 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 60/0 | Utkarsh Const/ D&V | 2025-12-25 | 2026-04-30 | 2026-04 | 127 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 64/3 | Pachauri | 2026-04-05 | 2026-05-04 | 2026-05 | 30 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 66/1 | Rahul Raghav | 2026-04-25 | 2026-05-04 | 2026-05 | 10 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 41/2 | GRD | 2026-04-13 | 2026-05-05 | 2026-05 | 23 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 61/0 | D&V | 2026-04-27 | 2026-05-08 | 2026-05 | 12 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 64/4 | Pachauri | 2026-04-05 | 2026-05-08 | 2026-05 | 34 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 53/0 | TDCL(Ravindra) | 2026-04-27 | 2026-05-09 | 2026-05 | 13 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 84/2 | D&V | 2026-03-25 | 2026-05-10 | 2026-05 | 47 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 38/3 | Thakur Engineering | 2026-01-28 | 2026-05-11 | 2026-05 | 104 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 71/0 | Radhe Enterprises | 2026-04-08 | 2026-05-11 | 2026-05 | 34 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 65/0 | Rahul Raghav | 2026-05-08 | 2026-05-17 | 2026-05 | 10 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 52/0 | GRD | 2026-04-30 | 2026-05-18 | 2026-05 | 19 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 67/0 | Vivan Const | 2026-04-25 | 2026-05-20 | 2026-05 | 26 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 69/0 | Virender Const | 2026-04-17 | 2026-05-20 | 2026-05 | 34 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 54/0 | GRD 2 | 2026-04-30 | 2026-05-25 | 2026-05 | 26 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 37/0 | Shiv Shakti | 2026-04-27 | 2026-05-26 | 2026-05 | 30 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 68/0 | Virender Const | 2026-05-11 | 2026-05-28 | 2026-05 | 18 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 95A/0 | D&V | 2026-05-12 | 2026-05-28 | 2026-05 | 17 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 52/1 | Ravindra | 2026-03-18 | 2026-05-31 | 2026-05 | 75 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 65/2 | Virender Const | 2026-05-20 | 2026-05-31 | 2026-05 | 12 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 70/0 | Radhe Enterprises | 2026-04-18 | 2026-06-01 | 2026-06 | 45 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 75/0 | Rahul Raghav | 2026-05-16 | 2026-06-01 | 2026-06 | 17 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 72/0 | D&V | 2026-05-09 | 2026-06-05 | 2026-06 | 28 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 38/2 | Shiv Shakti | 2026-05-06 | 2026-06-06 | 2026-06 | 32 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 65/1 | Pachauri | 2026-06-01 | 2026-06-06 | 2026-06 | 6 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 76/0 | Pachauri | 2026-05-17 | 2026-06-06 | 2026-06 | 21 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 73/0 | D&V | 2026-03-22 | 2026-06-08 | 2026-06 | 79 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 52/2 | GRD 2 | 2026-06-01 | 2026-06-09 | 2026-06 | 9 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 76/1 | Piroth and Sons | 2026-05-13 | 2026-06-11 | 2026-06 | 30 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 419 | TA419 |  | 48/1 | Rahul Raghav | 2026-06-04 | 2026-06-13 | 2026-06 | 10 | Valid | detail | detail_date | TA 419 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 421 | TA421 |  | 24/4 | ATK CONSTRUCTIONS | 2024-05-03 | 2024-05-22 | 2024-05 | 20 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 24/2 | ATK CONSTRUCTIONS | 2024-05-23 | 2024-06-02 | 2024-06 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 24/3 | ATK CONSTRUCTIONS | 2024-05-06 | 2024-06-07 | 2024-06 | 33 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 24/5 | ATK CONSTRUCTIONS | 2024-05-09 | 2024-06-11 | 2024-06 | 34 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 24/6 | ATK CONSTRUCTIONS | 2024-05-25 | 2024-06-15 | 2024-06 | 22 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 24/7 | ATK CONSTRUCTIONS | 2024-05-25 | 2024-06-19 | 2024-06 | 26 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 23/4 | AMMU ENG. | 2024-05-31 | 2024-06-20 | 2024-06 | 21 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 25/4 | ATK CONSTRUCTIONS | 2024-06-13 | 2024-06-22 | 2024-06 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 25/5 | ATK CONSTRUCTIONS | 2024-06-17 | 2024-06-25 | 2024-06 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 23/3 | AMMU ENG. | 2024-06-03 | 2024-06-27 | 2024-06 | 25 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 25/1 | ATK CONSTRUCTIONS | 2024-06-20 | 2024-06-28 | 2024-06 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 22/4 | AMMU ENG. | 2024-06-23 | 2024-06-29 | 2024-06 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 24/8 | ATK CONSTRUCTIONS | 2024-06-21 | 2024-06-29 | 2024-06 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 29/1 | TSB | 2024-06-15 | 2024-06-29 | 2024-06 | 15 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 12/3 | RR CONST | 2024-06-22 | 2024-06-30 | 2024-06 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 26/1 | ATK CONSTRUCTIONS | 2024-06-25 | 2024-07-04 | 2024-07 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 12/4 | RR CONST | 2024-06-19 | 2024-07-05 | 2024-07 | 17 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 22/5 | AMMU ENG. | 2024-06-27 | 2024-07-06 | 2024-07 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 26/3 | ATK CONSTRUCTIONS | 2024-07-01 | 2024-07-07 | 2024-07 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 12/2 | RR CONST | 2024-06-24 | 2024-07-10 | 2024-07 | 17 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 23/2 | AMMU ENG. | 2024-07-03 | 2024-07-10 | 2024-07 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 26/2 | ATK CONSTRUCTIONS | 2024-06-25 | 2024-07-10 | 2024-07 | 16 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 12/11 | ANJU Const. | 2024-06-28 | 2024-07-11 | 2024-07 | 14 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 26/4 | ATK CONSTRUCTIONS | 2024-07-07 | 2024-07-13 | 2024-07 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 22/3 | AMMU ENG. | 2024-07-02 | 2024-07-14 | 2024-07 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 24/1 | ATK CONSTRUCTIONS | 2024-07-10 | 2024-07-16 | 2024-07 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 12/7 | ANJU Const. | 2024-06-28 | 2024-07-17 | 2024-07 | 20 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 22/2 | AMMU ENG. | 2024-07-08 | 2024-07-17 | 2024-07 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 25/4 | Khatan | 2024-07-10 | 2024-07-19 | 2024-07 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 27/1 | ATK CONSTRUCTIONS | 2024-07-10 | 2024-07-19 | 2024-07 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 21/9 | AMMU ENG.-2 | 2024-07-12 | 2024-07-22 | 2024-07 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 12/6 | ANJU Const. | 2024-07-09 | 2024-07-23 | 2024-07 | 15 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 26/1 | Khatan | 2024-07-18 | 2024-07-28 | 2024-07 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 21/8 | AMMU ENG.-2 | 2024-07-24 | 2024-07-30 | 2024-07 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 12/5 | ANJU Const. | 2024-07-14 | 2024-07-31 | 2024-07 | 18 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 21/7 | AMMU ENG.-2 | 2024-07-19 | 2024-07-31 | 2024-07 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 27/8 | TSB | 2024-06-26 | 2024-07-31 | 2024-07 | 36 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 26/4 | Khatan | 2024-07-27 | 2024-08-03 | 2024-08 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 27/4 | ATK CONSTRUCTIONS | 2024-07-11 | 2024-08-05 | 2024-08 | 26 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 27/5 | ATK CONSTRUCTIONS | 2024-08-03 | 2024-08-08 | 2024-08 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 25/1 | Khatan | 2024-08-02 | 2024-08-09 | 2024-08 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 12/8 | ANJU Const. | 2024-07-05 | 2024-08-11 | 2024-08 | 38 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 23/0 | Ammu Eng | 2024-08-02 | 2024-08-11 | 2024-08 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 27/0 | ATK CONSTRUCTIONS | 2024-07-19 | 2024-08-11 | 2024-08 | 24 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 27/6 | ATK CONSTRUCTIONS | 2024-07-11 | 2024-08-13 | 2024-08 | 34 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 27/7 | Company Gang | 2024-06-25 | 2024-08-13 | 2024-08 | 50 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 26/0 | ATK CONSTRUCTIONS | 2024-07-22 | 2024-08-14 | 2024-08 | 24 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 26/2 | Khatan | 2024-08-09 | 2024-08-14 | 2024-08 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 21/4 | Ammu Eng | 2024-08-05 | 2024-08-16 | 2024-08 | 12 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 25/0 | ATK CONSTRUCTIONS | 2024-07-17 | 2024-08-16 | 2024-08 | 31 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 24/0 | Ammu Eng | 2024-07-28 | 2024-08-17 | 2024-08 | 21 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 26/3 | Khatan | 2024-08-16 | 2024-08-18 | 2024-08 | 3 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 27/2 | ATK CONSTRUCTIONS | 2024-07-20 | 2024-08-19 | 2024-08 | 31 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 12/9 | ANJU Const. | 2024-07-13 | 2024-08-22 | 2024-08 | 41 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 22/1 | AMMU ENG. | 2024-07-06 | 2024-08-23 | 2024-08 | 49 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 27/9 | Company Gang | 2024-08-11 | 2024-08-23 | 2024-08 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 27/1 | Khatan | 2024-08-19 | 2024-08-24 | 2024-08 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 29/4 | ATK CONSTRUCTIONS | 2024-08-08 | 2024-08-24 | 2024-08 | 17 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 22/0 | Ammu Eng | 2024-08-13 | 2024-08-25 | 2024-08 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 29/5 | ATK CONSTRUCTIONS | 2024-08-20 | 2024-08-27 | 2024-08 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 11/11 | ANJU Const. | 2024-08-20 | 2024-08-28 | 2024-08 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 24/5 | Khatan | 2024-08-22 | 2024-08-29 | 2024-08 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 29/3 | ATK CONSTRUCTIONS | 2024-08-25 | 2024-08-30 | 2024-08 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 21/2 | Ammu Eng | 2024-08-08 | 2024-08-31 | 2024-08 | 24 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 24/4 | Khatan | 2024-08-29 | 2024-09-06 | 2024-09 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 12/0 | ANJU Const. | 2024-08-16 | 2024-09-08 | 2024-09 | 24 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 22/5 | s.K.Janarul | 2024-08-23 | 2024-09-08 | 2024-09 | 17 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 29/9 | ATK CONSTRUCTIONS | 2024-09-05 | 2024-09-11 | 2024-09 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 30/4 | Company Gang | 2024-08-24 | 2024-09-11 | 2024-09 | 19 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 24/3 | Khatan | 2024-08-29 | 2024-09-12 | 2024-09 | 15 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 29/8 | ATK CONSTRUCTIONS | 2024-09-09 | 2024-09-16 | 2024-09 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 27/2 | Khatan | 2024-09-14 | 2024-09-19 | 2024-09 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 23/1 | AMMU ENG. | 2024-06-27 | 2024-09-20 | 2024-09 | 86 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 29/6 | ATK CONSTRUCTIONS | 2024-08-28 | 2024-09-20 | 2024-09 | 24 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 30/5 | Company Gang | 2024-09-11 | 2024-09-20 | 2024-09 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 21/9 | s.K.Janarul Sheikh | 2024-09-09 | 2024-09-21 | 2024-09 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 12/10 | ANJU Const. | 2024-08-24 | 2024-09-22 | 2024-09 | 30 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 27/4 | Khatan | 2024-09-19 | 2024-09-23 | 2024-09 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 30/1 | ATK CONSTRUCTIONS | 2024-09-23 | 2024-09-27 | 2024-09 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 27/5 | Khatan | 2024-09-24 | 2024-09-28 | 2024-09 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 21/7 | Ashok kumar | 2024-09-12 | 2024-09-29 | 2024-09 | 18 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 12/3 | Maa Const. | 2024-09-14 | 2024-09-30 | 2024-09 | 17 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 13/0 | ANJU Const. | 2024-09-23 | 2024-09-30 | 2024-09 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 23/2 | s.K.Janarul Sheikh | 2024-09-26 | 2024-10-03 | 2024-10 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 27/6 | Khatan | 2024-09-29 | 2024-10-03 | 2024-10 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 30/3 | ATK CONSTRUCTIONS | 2024-08-31 | 2024-10-03 | 2024-10 | 34 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 25/2 | Ammu Eng | 2024-09-24 | 2024-10-04 | 2024-10 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 29/4 | Manirul (Islam)-Khatun | 2024-09-21 | 2024-10-04 | 2024-10 | 14 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 27/7 | Khatan | 2024-10-03 | 2024-10-07 | 2024-10 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 19/3 | Ammu Eng | 2024-09-22 | 2024-10-10 | 2024-10 | 19 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 30/0 | ATK CONSTRUCTIONS | 2024-10-05 | 2024-10-12 | 2024-10 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 12/1 | ANJU Const. | 2024-08-31 | 2024-10-14 | 2024-10 | 45 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 23/4 | s.K.Janarul Sheikh | 2024-10-05 | 2024-10-14 | 2024-10 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 29/5 | Khatan | 2024-10-05 | 2024-10-14 | 2024-10 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 19/2 | Ammu Eng | 2024-10-10 | 2024-10-17 | 2024-10 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 21/8 | Ashok | 2024-10-01 | 2024-10-17 | 2024-10 | 17 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 27/3 | ATK Constructions | 2024-10-14 | 2024-10-18 | 2024-10 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 12/4 | Maa Const. | 2024-10-01 | 2024-10-19 | 2024-10 | 19 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 30/4 | Khatun | 2024-10-16 | 2024-10-21 | 2024-10 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 31/1 | Company Gang + ATK | 2024-09-17 | 2024-10-21 | 2024-10 | 35 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 39/7 | Ashok | 2024-09-30 | 2024-10-21 | 2024-10 | 22 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 17/3 | Ammu Eng | 2024-10-14 | 2024-10-24 | 2024-10 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 12/9 | Praveen | 2024-10-01 | 2024-10-26 | 2024-10 | 26 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 24/8 | Khatan | 2024-10-21 | 2024-10-26 | 2024-10 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 22/1 | Ashok | 2024-10-18 | 2024-10-27 | 2024-10 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 22/4 | Subash | 2024-10-17 | 2024-10-27 | 2024-10 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 12/2 | Maa Const. | 2024-10-19 | 2024-10-30 | 2024-10 | 12 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 13/1 | ANJU Const. | 2024-09-29 | 2024-10-30 | 2024-10 | 32 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 21/6 | Ammu Eng | 2024-10-22 | 2024-10-30 | 2024-10 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 42/0 | Ashok | 2024-10-05 | 2024-10-30 | 2024-10 | 26 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 23/3 | Subash | 2024-10-16 | 2024-11-01 | 2024-11 | 17 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 24/7 | khatun | 2024-10-27 | 2024-11-01 | 2024-11 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 22/2 | Ashokkumar | 2024-10-29 | 2024-11-05 | 2024-11 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 12/5 | Maa Const. | 2024-11-01 | 2024-11-07 | 2024-11 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 24/0 | Subash | 2024-11-02 | 2024-11-07 | 2024-11 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 25/0 | khatun | 2024-11-02 | 2024-11-07 | 2024-11 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 41/1 | Ashok | 2024-10-23 | 2024-11-07 | 2024-11 | 16 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 15/2 | Ashok kumar | 2024-10-18 | 2024-11-08 | 2024-11 | 22 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 12/10 | Praveen | 2024-10-27 | 2024-11-12 | 2024-11 | 17 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 11/6 | Amit Kumar | 2024-11-02 | 2024-11-13 | 2024-11 | 12 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 25/2 | Khatun | 2024-11-08 | 2024-11-13 | 2024-11 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 12/6 | Maa Const. | 2024-11-07 | 2024-11-14 | 2024-11 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 23/1 | Subash | 2024-11-09 | 2024-11-14 | 2024-11 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 18/3 | Ammu Eng | 2024-11-08 | 2024-11-15 | 2024-11 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 22/0 | Ashok | 2024-11-05 | 2024-11-15 | 2024-11 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 15/1 | Ashok Kumar | 2024-11-10 | 2024-11-16 | 2024-11 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 24/6 | Khatun | 2024-11-13 | 2024-11-18 | 2024-11 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 39/1 | Ashok-2 | 2024-11-08 | 2024-11-18 | 2024-11 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 11/10 | Amit Kumar | 2024-11-06 | 2024-11-19 | 2024-11 | 14 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 24/1 | Subash | 2024-11-15 | 2024-11-20 | 2024-11 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 12/7 | Maa Const. | 2024-11-14 | 2024-11-21 | 2024-11 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 15/4 | Ashok kumar | 2024-10-18 | 2024-11-23 | 2024-11 | 37 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 11/9 | Amit Kumar | 2024-11-13 | 2024-11-24 | 2024-11 | 12 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 13/4 | Balraj | 2024-10-25 | 2024-11-24 | 2024-11 | 31 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 26/0 | Khatun | 2024-11-19 | 2024-11-24 | 2024-11 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 38/3 | Ashok-2 | 2024-11-14 | 2024-11-24 | 2024-11 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 21/4 | Ashok | 2024-11-16 | 2024-11-25 | 2024-11 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 16/6 | Visionary Co | 2024-10-18 | 2024-11-26 | 2024-11 | 40 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 17/1 | Ammu Eng | 2024-10-18 | 2024-11-26 | 2024-11 | 40 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 23/0 | Subash | 2024-11-21 | 2024-11-26 | 2024-11 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 38/1 | venkateshwarlu | 2024-11-18 | 2024-11-28 | 2024-11 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 13/3 | Balraj | 2024-11-23 | 2024-11-29 | 2024-11 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 18/0 | Ammu Eng | 2024-11-04 | 2024-11-29 | 2024-11 | 26 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 39/3 | Ashok-2 | 2024-11-18 | 2024-11-29 | 2024-11 | 12 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 10/8 | Amit Kumar | 2024-11-23 | 2024-11-30 | 2024-11 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 12/0 | Maa Const. | 2024-11-22 | 2024-11-30 | 2024-11 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 13/5 | Balraj | 2024-11-28 | 2024-11-30 | 2024-11 | 3 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 13/9 | Ashok kumar | 2024-11-16 | 2024-11-30 | 2024-11 | 15 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 27/0 | Khatun | 2024-11-24 | 2024-11-30 | 2024-11 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 38/2 | venkateshwarlu | 2024-11-24 | 2024-11-30 | 2024-11 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 21/2 | Subash | 2024-11-26 | 2024-12-02 | 2024-12 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 12/8 | Praveen | 2024-11-12 | 2024-12-05 | 2024-12 | 24 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 16/9 | Visionary Co | 2024-11-22 | 2024-12-05 | 2024-12 | 14 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 13/2 | Balraj | 2024-12-01 | 2024-12-06 | 2024-12 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 21/6 | Subash | 2024-12-03 | 2024-12-06 | 2024-12 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 18/1 | Ammu Eng | 2024-12-01 | 2024-12-07 | 2024-12 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 37/5 | venkateshwarlu | 2024-11-18 | 2024-12-07 | 2024-12 | 20 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 27/8 | Khatun | 2024-12-03 | 2024-12-08 | 2024-12 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 35/2 | Tagore | 2024-11-28 | 2024-12-08 | 2024-12 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 18/2 | Ammu Eng | 2024-12-02 | 2024-12-09 | 2024-12 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 39/2 | Ashok-2 | 2024-11-30 | 2024-12-10 | 2024-12 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 11/0 | Amit Kumar | 2024-12-02 | 2024-12-11 | 2024-12 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 24/2 | Subash | 2024-12-03 | 2024-12-11 | 2024-12 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 31/3 | ATK Constructions | 2024-12-03 | 2024-12-11 | 2024-12 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 13/10 | Ashok kumar | 2024-12-01 | 2024-12-12 | 2024-12 | 12 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 38/4 | venkateshwarlu | 2024-12-04 | 2024-12-12 | 2024-12 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 13/6 | Balraj | 2024-12-04 | 2024-12-13 | 2024-12 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 21/5 | Ammu Eng | 2024-12-07 | 2024-12-13 | 2024-12 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 29/3 | Khatun | 2024-12-09 | 2024-12-13 | 2024-12 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 21/1 | Ammu Eng | 2024-12-07 | 2024-12-14 | 2024-12 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 19/3 | Subash | 2024-12-11 | 2024-12-15 | 2024-12 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 31/5 | ATK Constructions | 2024-12-08 | 2024-12-15 | 2024-12 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 39/4 | Ashok-2 | 2024-12-08 | 2024-12-15 | 2024-12 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 35/3 | Tagore | 2024-12-08 | 2024-12-16 | 2024-12 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 19/2 | Subash | 2024-12-16 | 2024-12-18 | 2024-12 | 3 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 29/8 | Khatun | 2024-12-15 | 2024-12-19 | 2024-12 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 31/2 | ATK Constructions | 2024-09-24 | 2024-12-19 | 2024-12 | 87 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 38/5 | Ashok-2 | 2024-12-09 | 2024-12-20 | 2024-12 | 12 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 30/2 | ATK Constructions | 2024-12-17 | 2024-12-21 | 2024-12 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 18/3 | Subash | 2024-12-19 | 2024-12-22 | 2024-12 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 21/3 | Ammu Eng | 2024-12-11 | 2024-12-22 | 2024-12 | 12 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 38/7 | Ashok-2 | 2024-12-15 | 2024-12-22 | 2024-12 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 11/3 | Ashok kumar | 2024-12-14 | 2024-12-23 | 2024-12 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 16/11 | Visionary Co | 2024-12-09 | 2024-12-23 | 2024-12 | 15 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 31/4 | ATK Constructions | 2024-12-19 | 2024-12-23 | 2024-12 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 37/4 | Ashok-2 | 2024-12-14 | 2024-12-24 | 2024-12 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 18/2 | Subash | 2024-12-23 | 2024-12-25 | 2024-12 | 3 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 25/3 | Tagore | 2024-12-15 | 2024-12-25 | 2024-12 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 29/1 | Khatun | 2024-12-20 | 2024-12-25 | 2024-12 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 16/10 | Visionary & Co | 2024-12-23 | 2024-12-27 | 2024-12 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 11/11 | Praveen | 2024-12-12 | 2024-12-28 | 2024-12 | 17 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 18/1 | Subash | 2024-12-26 | 2024-12-28 | 2024-12 | 3 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 31/0 | ATK Constructions | 2024-12-22 | 2024-12-28 | 2024-12 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 11/2 | Ashok-1 | 2024-12-22 | 2024-12-30 | 2024-12 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 21/0 | Ammu Eng | 2024-12-22 | 2024-12-30 | 2024-12 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 16/8 | BalraJ | 2024-12-24 | 2024-12-31 | 2024-12 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 28/0 | ATK Constructions | 2024-12-24 | 2024-12-31 | 2024-12 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 30/3 | Khatun | 2024-12-26 | 2024-12-31 | 2024-12 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 38/6 | Venkateshwarlu | 2024-12-24 | 2024-12-31 | 2024-12 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 18/0 | Subash | 2024-12-27 | 2025-01-03 | 2025-01 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 29/2 | ATK Constructions | 2024-12-29 | 2025-01-03 | 2025-01 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 36/7 | TaGore | 2024-12-18 | 2025-01-04 | 2025-01 | 18 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 11/4 | Ashok kumar (Thotta) | 2024-12-31 | 2025-01-05 | 2025-01 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 16/7 | Visionary & Co | 2024-12-24 | 2025-01-05 | 2025-01 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 19/1 | Ammu Engineering | 2024-12-27 | 2025-01-05 | 2025-01 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 36/8 | Ashok-2 (Venkateshwarlu) | 2024-12-26 | 2025-01-05 | 2025-01 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 29/7 | ATK Constructions | 2025-01-03 | 2025-01-06 | 2025-01 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 30/2 | Khatun | 2024-12-02 | 2025-01-06 | 2025-01 | 36 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 17/1 | Subash | 2025-01-03 | 2025-01-08 | 2025-01 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 36/6 | TaGore | 2024-12-29 | 2025-01-09 | 2025-01 | 12 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 11/5 | Ashok kumar (Thotta) | 2025-01-03 | 2025-01-10 | 2025-01 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 31/6 | ATK Constructions | 2025-01-05 | 2025-01-12 | 2025-01 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 13/7 | BaLraJ | 2025-01-05 | 2025-01-13 | 2025-01 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 21/1 | Subash | 2024-12-28 | 2025-01-13 | 2025-01 | 17 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 11/10 | Praveen | 2025-01-02 | 2025-01-15 | 2025-01 | 14 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 30/1 | Khatun | 2025-01-04 | 2025-01-15 | 2025-01 | 12 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 38/0 | Ashok-2 (Venkateshwarlu) | 2025-01-03 | 2025-01-15 | 2025-01 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 17/0 | Ammu Engineering | 2025-01-06 | 2025-01-16 | 2025-01 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 33/0 | ATK Constructions | 2025-01-09 | 2025-01-16 | 2025-01 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 37/6 | Venkateshwarlu | 2025-01-03 | 2025-01-16 | 2025-01 | 14 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 11/1 | Ashok kumar (Thotta) | 2025-01-12 | 2025-01-17 | 2025-01 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 16/6 | Subash | 2025-01-14 | 2025-01-18 | 2025-01 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 17/2 | Ammu Engineering | 2025-01-13 | 2025-01-18 | 2025-01 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 36/5 | TaGore | 2025-01-07 | 2025-01-18 | 2025-01 | 12 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 29/0 | ATK Constructions | 2025-01-08 | 2025-01-19 | 2025-01 | 12 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 29/6 | Khatun | 2025-01-16 | 2025-01-19 | 2025-01 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 16/2 | Visionary & Co | 2025-01-06 | 2025-01-21 | 2025-01 | 16 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 16/8 | Subash | 2025-01-18 | 2025-01-22 | 2025-01 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 33/2 | ATK Constructions | 2025-01-17 | 2025-01-22 | 2025-01 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 29/2 | Khatun | 2025-01-19 | 2025-01-23 | 2025-01 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 36/4 | TaGore | 2025-01-12 | 2025-01-24 | 2025-01 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 39/5 | Ashok-2 (Venkateshwarlu) | 2025-01-17 | 2025-01-24 | 2025-01 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 33/1 | ATK Constructions | 2025-01-13 | 2025-01-25 | 2025-01 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 37/1 | Venkateshwarlu | 2025-01-07 | 2025-01-25 | 2025-01 | 19 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 10/0 | Ashok kumar (Thotta) | 2025-01-19 | 2025-01-27 | 2025-01 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 16/10 | Subash | 2025-01-22 | 2025-01-27 | 2025-01 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 32/1 | ATK Constructions | 2025-01-22 | 2025-01-27 | 2025-01 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 30/5 | Khatun | 2025-01-23 | 2025-01-28 | 2025-01 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 39/6 | Ashok-2 (Venkateshwarlu) | 2025-01-17 | 2025-01-28 | 2025-01 | 12 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 32/2 | ATK Constructions | 2025-01-22 | 2025-01-29 | 2025-01 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 10/2 | Ashok kumar (Thotta) | 2025-01-24 | 2025-01-30 | 2025-01 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 11/6 | Praveen | 2025-01-16 | 2025-01-30 | 2025-01 | 15 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 14/0 | BaLraJ | 2025-01-18 | 2025-01-30 | 2025-01 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 16/9 | Subash | 2025-01-22 | 2025-01-30 | 2025-01 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 36/3 | TaGore | 2025-01-20 | 2025-01-30 | 2025-01 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 37/2 | Venkateshwarlu | 2025-01-24 | 2025-01-30 | 2025-01 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 19/0 | Ammu Engineering | 2025-01-19 | 2025-01-31 | 2025-01 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 35/1 | ATK Constructions | 2025-01-27 | 2025-01-31 | 2025-01 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 39/8 | Ashok-2 (Venkateshwarlu) | 2025-01-25 | 2025-01-31 | 2025-01 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 35/4 | ATK Constructions | 2025-01-30 | 2025-02-02 | 2025-02 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 16/2 | Subash | 2025-01-30 | 2025-02-03 | 2025-02 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 31/1 | Khatun | 2025-01-28 | 2025-02-03 | 2025-02 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 10/1 | Ashok kumar (Thotta) | 2025-01-25 | 2025-02-04 | 2025-02 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 36/1 | TaGore | 2025-01-25 | 2025-02-06 | 2025-02 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 9/10 | Ammu Engineering | 2025-01-25 | 2025-02-06 | 2025-02 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 13/2 | Subash | 2025-02-04 | 2025-02-08 | 2025-02 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 31/4 | Khatun | 2025-02-04 | 2025-02-09 | 2025-02 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 36/0 | ATK Constructions | 2025-01-27 | 2025-02-09 | 2025-02 | 14 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 9/9 | Ammu Engineering | 2025-01-27 | 2025-02-09 | 2025-02 | 14 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 11/5 | Praveen | 2025-01-30 | 2025-02-10 | 2025-02 | 12 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 16/0 | BaLraJ | 2025-02-01 | 2025-02-10 | 2025-02 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 37/0 | Venkateshwarlu | 2025-01-28 | 2025-02-10 | 2025-02 | 14 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 10/4 | Ashok kumar (Thotta) | 2025-02-05 | 2025-02-12 | 2025-02 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 13/1 | Subash | 2025-02-09 | 2025-02-12 | 2025-02 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 32/0 | ATK Constructions | 2025-02-01 | 2025-02-13 | 2025-02 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 31/5 | Khatun | 2025-02-10 | 2025-02-14 | 2025-02 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 36/2 | TaGore | 2025-02-05 | 2025-02-14 | 2025-02 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 9/7 | Ammu Engineering | 2025-01-29 | 2025-02-14 | 2025-02 | 17 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 10/3 | Ashok kumar (Thotta) | 2025-02-09 | 2025-02-15 | 2025-02 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 10/5 | BaLraJ | 2025-02-06 | 2025-02-16 | 2025-02 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 39/0 | Ashok-2 (Venkateshwarlu) | 2025-02-05 | 2025-02-16 | 2025-02 | 12 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 9/5 | Ammu Engineering | 2025-02-01 | 2025-02-16 | 2025-02 | 16 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 25/3 | J.$lnGH | 2025-02-10 | 2025-02-18 | 2025-02 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 39/9 | Ashok-2 (Venkateshwarlu) | 2025-02-02 | 2025-02-18 | 2025-02 | 17 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 10/9 | BaLraJ | 2025-01-23 | 2025-02-19 | 2025-02 | 28 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 13/3 | Subash | 2025-02-13 | 2025-02-19 | 2025-02 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 31/6 | Khatun | 2025-02-15 | 2025-02-20 | 2025-02 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 35/0 | ATK Constructions | 2025-02-16 | 2025-02-20 | 2025-02 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 9/8 | Ammu Engineering | 2025-01-24 | 2025-02-20 | 2025-02 | 28 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 12/11 | Praveen | 2025-02-11 | 2025-02-21 | 2025-02 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 13/8 | Ashok kumar (Thotta) | 2025-02-17 | 2025-02-21 | 2025-02 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 42/4 | Venkateshwarlu | 2025-02-12 | 2025-02-21 | 2025-02 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 42/6 | TaGore | 2025-02-13 | 2025-02-21 | 2025-02 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 10/7 | BaLraJ | 2025-01-19 | 2025-02-23 | 2025-02 | 36 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 13/4 | Subash | 2025-02-19 | 2025-02-23 | 2025-02 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 42/5 | Venkateshwarlu | 2025-02-13 | 2025-02-23 | 2025-02 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 9/6 | Ammu Engineering | 2025-02-04 | 2025-02-24 | 2025-02 | 21 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 10/6 | BaLraJ | 2025-02-11 | 2025-02-25 | 2025-02 | 15 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 25/5 | J.$lnGH | 2025-02-19 | 2025-02-25 | 2025-02 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 31/2 | Khatun | 2025-02-21 | 2025-02-25 | 2025-02 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 13/6 | Subash | 2025-02-24 | 2025-02-27 | 2025-02 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 9/4 | Ammu Engineering | 2025-02-14 | 2025-02-27 | 2025-02 | 14 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 42/7 | TaGore | 2025-02-16 | 2025-02-28 | 2025-02 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 9/3 | Ammu Engineering | 2025-02-19 | 2025-02-28 | 2025-02 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 11/9 | Praveen | 2025-02-22 | 2025-03-01 | 2025-03 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 29/7 | Khatun | 2025-02-26 | 2025-03-01 | 2025-03 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 42/3 | Venkateshwarlu | 2025-02-18 | 2025-03-01 | 2025-03 | 12 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 13/5 | Subash | 2025-02-28 | 2025-03-02 | 2025-03 | 3 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 38/1 | J.$lnGH | 2025-02-26 | 2025-03-02 | 2025-03 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 15/0 | Ashok kumar (Thotta) | 2025-02-18 | 2025-03-04 | 2025-03 | 15 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 16/4 | BaLraJ | 2025-02-26 | 2025-03-04 | 2025-03 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 9/2 | Ammu Engineering | 2025-02-27 | 2025-03-04 | 2025-03 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 40/0 | Ashok-2 (Venkateshwarlu) | 2025-02-20 | 2025-03-06 | 2025-03 | 15 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 13/7 | Subash | 2025-03-03 | 2025-03-07 | 2025-03 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 31/0 | Khatun | 2025-03-02 | 2025-03-07 | 2025-03 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 42/2 | Venkateshwarlu | 2025-02-26 | 2025-03-07 | 2025-03 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 9/1 | Ammu Engineering | 2025-02-27 | 2025-03-07 | 2025-03 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 16/5 | BaLraJ | 2025-03-04 | 2025-03-08 | 2025-03 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 32/3 | TaGore | 2025-02-25 | 2025-03-08 | 2025-03 | 12 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 38/3 | J.$lnGH | 2025-03-03 | 2025-03-09 | 2025-03 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 13/0 | Subash | 2025-03-08 | 2025-03-11 | 2025-03 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 22/3 | Praveen | 2025-03-03 | 2025-03-12 | 2025-03 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 32/1 | Khatun | 2025-03-08 | 2025-03-12 | 2025-03 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 40/1 | Ashok-2 (Venkateshwarlu) | 2025-02-20 | 2025-03-12 | 2025-03 | 21 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 16/1 | BaLraJ | 2025-03-04 | 2025-03-13 | 2025-03 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 38/4 | J.$lnGH | 2025-03-10 | 2025-03-13 | 2025-03 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/15 | Ammu Engineering | 2024-03-05 | 2025-03-13 | 2025-03 | 374 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 13/8 | Subash | 2025-03-12 | 2025-03-16 | 2025-03 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 33/1 | Khatun | 2025-03-13 | 2025-03-17 | 2025-03 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 16/3 | BaLraJ | 2025-03-05 | 2025-03-18 | 2025-03 | 14 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/14 | Ammu Engineering | 2025-03-13 | 2025-03-18 | 2025-03 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 11/7 | Ashok kumar (Thotta) | 2025-03-06 | 2025-03-19 | 2025-03 | 14 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 13/9 | Subash | 2025-03-16 | 2025-03-19 | 2025-03 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 38/5 | J.$lnGH | 2025-03-15 | 2025-03-19 | 2025-03 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 13/10 | Subash | 2025-03-20 | 2025-03-22 | 2025-03 | 3 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 32/0 | Khatun | 2025-03-17 | 2025-03-23 | 2025-03 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 38/6 | J.$lnGH | 2025-03-20 | 2025-03-23 | 2025-03 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 9/0 | Ammu Engineering | 2025-03-08 | 2025-03-24 | 2025-03 | 17 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 15/1 | Subash | 2025-03-23 | 2025-03-26 | 2025-03 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 34/1 | TaGore | 2024-03-05 | 2025-03-26 | 2025-03 | 387 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 21/3 | Praveen | 2025-03-13 | 2025-03-27 | 2025-03 | 15 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 32/2 | Khatun | 2025-03-23 | 2025-03-27 | 2025-03 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/12 | Ammu Engineering | 2025-03-17 | 2025-03-28 | 2025-03 | 12 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 15/2 | Subash | 2025-03-27 | 2025-03-29 | 2025-03 | 3 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 38/7 | J.$lnGH - o1 | 2025-03-24 | 2025-03-29 | 2025-03 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 13/11 | Venkateshwarlu | 2025-03-22 | 2025-03-30 | 2025-03 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 36/3 | J.$lnGH - o2 | 2025-03-01 | 2025-03-30 | 2025-03 | 30 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 32/3 | Khatun | 2025-03-28 | 2025-04-01 | 2025-04 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 15/4 | Subash | 2025-03-29 | 2025-04-02 | 2025-04 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 37/5 | J.$lnGH - o1 | 2025-03-29 | 2025-04-04 | 2025-04 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 36/1 | J.$lnGH - o2 | 2025-03-30 | 2025-04-05 | 2025-04 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 15/3 | Venkateshwarlu | 2025-03-27 | 2025-04-08 | 2025-04 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 33/0 | Khatun | 2025-04-02 | 2025-04-09 | 2025-04 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 16/0 | Subash | 2025-04-03 | 2025-04-10 | 2025-04 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 19/1 | Praveen | 2025-03-28 | 2025-04-11 | 2025-04 | 15 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 34/2 | TaGore | 2025-03-10 | 2025-04-11 | 2025-04 | 33 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 36/2 | J.$lnGH - o2 | 2025-04-06 | 2025-04-13 | 2025-04 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 11/8 | Venkateshwarlu | 2025-04-09 | 2025-04-14 | 2025-04 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 35/4 | Khatun | 2025-04-10 | 2025-04-14 | 2025-04 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 16/1 | Subash | 2025-04-11 | 2025-04-15 | 2025-04 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 38/0 | J.$lnGH - o1 | 2025-04-05 | 2025-04-17 | 2025-04 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 35/3 | Khatun | 2025-04-15 | 2025-04-18 | 2025-04 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 6/2 | Venkateshwarlu | 2025-04-08 | 2025-04-18 | 2025-04 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 16/3 | Subash | 2025-04-16 | 2025-04-19 | 2025-04 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 37/3 | TaGore | 2025-04-07 | 2025-04-19 | 2025-04 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 16/4 | Subash | 2025-04-19 | 2025-04-21 | 2025-04 | 3 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 36/5 | J.$lnGH - o2 | 2025-04-14 | 2025-04-21 | 2025-04 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 6/1 | Venkateshwarlu | 2025-04-14 | 2025-04-22 | 2025-04 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 29/0 | Khatun | 2025-04-19 | 2025-04-23 | 2025-04 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 37/4 | J.$lnGH - o1 | 2025-04-18 | 2025-04-23 | 2025-04 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 16/5 | Subash | 2025-04-22 | 2025-04-24 | 2025-04 | 3 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 20/0 | ATK Constructions | 2025-04-01 | 2025-04-25 | 2025-04 | 25 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 17/3 | Praveen | 2025-04-12 | 2025-04-26 | 2025-04 | 15 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 15/3 | Subash | 2025-04-25 | 2025-04-27 | 2025-04 | 3 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 36/4 | J.$lnGH - o2 | 2025-04-22 | 2025-04-27 | 2025-04 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 6/6 | Venkateshwarlu | 2025-04-23 | 2025-04-27 | 2025-04 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 28/0 | Khatun | 2025-04-24 | 2025-04-28 | 2025-04 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 42/1 | Ashok-2 (Venkateshwarlu) | 2025-04-21 | 2025-04-28 | 2025-04 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 6/7 | Venkateshwarlu | 2025-04-17 | 2025-04-29 | 2025-04 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 13/11 | Subash | 2025-04-28 | 2025-04-30 | 2025-04 | 3 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 20A/0 | ATK Constructions | 2025-04-07 | 2025-04-30 | 2025-04 | 24 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 37/2 | J.$lnGH - o1 | 2025-04-24 | 2025-04-30 | 2025-04 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 27/9 | Khatun | 2025-04-29 | 2025-05-02 | 2025-05 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 34/0 | TaGore | 2025-03-13 | 2025-05-03 | 2025-05 | 52 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/8 | Ammu Engineering | 2025-03-18 | 2025-05-03 | 2025-05 | 47 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 10/7 | Subash | 2025-05-01 | 2025-05-04 | 2025-05 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/7 | BaLraJ | 2025-04-19 | 2025-05-04 | 2025-05 | 16 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/7 | ATK Constructions | 2025-04-07 | 2025-05-04 | 2025-05 | 28 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 38/2 | J.$lnGH - o1 | 2025-05-02 | 2025-05-05 | 2025-05 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 11/1 | Subash | 2025-05-05 | 2025-05-06 | 2025-05 | 2 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/20 | ATK Constructions | 2025-04-11 | 2025-05-06 | 2025-05 | 26 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/8 | BaLraJ | 2025-05-01 | 2025-05-07 | 2025-05 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 21/0 | Khatun | 2025-05-03 | 2025-05-08 | 2025-05 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/9 | Ammu Engineering | 2025-04-10 | 2025-05-08 | 2025-05 | 29 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 17/2 | Praveen | 2025-04-27 | 2025-05-09 | 2025-05 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 10/9 | Subash | 2025-05-07 | 2025-05-10 | 2025-05 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 37/3 | Jwala Singh -01 | 2025-05-06 | 2025-05-10 | 2025-05 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/9 | BaLraJ | 2025-04-12 | 2025-05-11 | 2025-05 | 30 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 41/0 | Ashok-2 (Venkateshwarlu) |  | 2025-05-11 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/5 | ATK Constructions | 2025-04-06 | 2025-05-12 | 2025-05 | 37 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 10/4 | Subash | 2025-05-10 | 2025-05-13 | 2025-05 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/6 | BaLraJ | 2025-04-20 | 2025-05-13 | 2025-05 | 24 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/10 | Ammu Engineering | 2025-04-15 | 2025-05-13 | 2025-05 | 29 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 20/0 | Khatun | 2025-05-10 | 2025-05-14 | 2025-05 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 42/9 | Ashok-2 (Venkateshwarlu) | 2025-04-15 | 2025-05-15 | 2025-05 | 31 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/6 | ATK Constructions | 2025-04-06 | 2025-05-15 | 2025-05 | 40 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 37/6 | Jwala Singh -01 | 2025-05-11 | 2025-05-16 | 2025-05 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/12 | ATK Constructions | 2025-05-07 | 2025-05-16 | 2025-05 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 10/2 | Subash | 2025-05-14 | 2025-05-17 | 2025-05 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/3 | BaLraJ | 2025-04-17 | 2025-05-17 | 2025-05 | 31 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/21 | ATK Constructions | 2025-04-11 | 2025-05-18 | 2025-05 | 38 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 6/3 | Venkateshwarlu | 2025-04-16 | 2025-05-19 | 2025-05 | 34 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 10/1 | Subash | 2025-05-18 | 2025-05-20 | 2025-05 | 3 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/19 | ATK Constructions | 2025-04-17 | 2025-05-20 | 2025-05 | 34 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/5 | BaLraJ | 2025-04-17 | 2025-05-20 | 2025-05 | 34 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 6/4 | Venkateshwarlu | 2025-04-16 | 2025-05-20 | 2025-05 | 35 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/18 | ATK Constructions | 2025-04-19 | 2025-05-21 | 2025-05 | 33 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 19/0 | Khatun | 2025-05-15 | 2025-05-22 | 2025-05 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 43A/2 | Ashok-2 (Venkateshwarlu) | 2025-05-18 | 2025-05-22 | 2025-05 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/11 | Ammu Engineering | 2025-04-15 | 2025-05-22 | 2025-05 | 38 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/23 | ATK Constructions | 2025-04-17 | 2025-05-23 | 2025-05 | 37 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 6/5 | Venkateshwarlu | 2025-05-05 | 2025-05-23 | 2025-05 | 19 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 36/6 | Hassan | 2025-05-11 | 2025-05-24 | 2025-05 | 14 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/4 | BaLraJ | 2025-04-17 | 2025-05-25 | 2025-05 | 39 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 43A/3 | Ashok-2 (Venkateshwarlu) | 2025-05-18 | 2025-05-25 | 2025-05 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/17 | ATK Constructions | 2025-05-15 | 2025-05-27 | 2025-05 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 10/3 | Subash | 2025-05-21 | 2025-05-28 | 2025-05 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/14 | ATK Constructions | 2025-05-11 | 2025-05-28 | 2025-05 | 18 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 43A/4 | Ashok-2 (Venkateshwarlu) | 2025-05-18 | 2025-05-28 | 2025-05 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/15 | ATK Constructions | 2025-05-04 | 2025-05-30 | 2025-05 | 27 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/13 | Ammu Engineering | 2025-04-08 | 2025-05-30 | 2025-05 | 53 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 3/3 | Venkateshwarlu | 2025-04-26 | 2025-05-31 | 2025-05 | 36 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 35/1 | Hassan | 2025-05-08 | 2025-05-31 | 2025-05 | 24 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/0 | BaLraJ | 2025-05-19 | 2025-05-31 | 2025-05 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/16 | ATK Constructions | 2025-04-29 | 2025-05-31 | 2025-05 | 33 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 43A/5 | Ashok-2 (Venkateshwarlu) | 2025-05-18 | 2025-05-31 | 2025-05 | 14 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/13 | ATK Constructions | 2025-05-11 | 2025-06-01 | 2025-06 | 22 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 10/5 | Subash | 2025-05-29 | 2025-06-02 | 2025-06 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/11 | ATK Constructions | 2025-05-17 | 2025-06-03 | 2025-06 | 18 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/2 | BaLraJ | 2025-05-03 | 2025-06-03 | 2025-06 | 32 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 17/0 | Praveen | 2025-05-10 | 2025-06-04 | 2025-06 | 26 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 43/3 | Ashok-2 (Venkateshwarlu) | 2025-05-27 | 2025-06-04 | 2025-06 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 3/0 | Venkateshwarlu | 2025-05-24 | 2025-06-06 | 2025-06 | 14 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 31/3 | Hassan | 2025-06-01 | 2025-06-06 | 2025-06 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/10 | BaLraJ | 2025-05-24 | 2025-06-06 | 2025-06 | 14 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 1B/3 | ATK Constructions | 2025-06-01 | 2025-06-08 | 2025-06 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 28/1 | Tagore | 2025-05-19 | 2025-06-08 | 2025-06 | 21 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 43/2 | Ashok-2 (Venkateshwarlu) | 2025-06-03 | 2025-06-09 | 2025-06 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 30/0 | Subash | 2025-06-03 | 2025-06-11 | 2025-06 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 2/5 | Ammu Engineering | 2025-05-31 | 2025-06-14 | 2025-06 | 15 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 42/8 | Ashok-2 (Venkateshwarlu) | 2025-06-10 | 2025-06-14 | 2025-06 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 1B/2 | ATK Constructions | 2025-06-01 | 2025-06-15 | 2025-06 | 15 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/1 | BaLraJ | 2025-05-31 | 2025-06-15 | 2025-06 | 16 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 33/2 | Hassan | 2025-06-05 | 2025-06-16 | 2025-06 | 12 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 3/1 | Venkateshwarlu | 2025-05-31 | 2025-06-17 | 2025-06 | 18 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 29/9 | Subash | 2025-06-06 | 2025-06-18 | 2025-06 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 1B/0 | ATK Constructions | 2025-06-01 | 2025-06-19 | 2025-06 | 19 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 21/5 | Praveen | 2025-06-05 | 2025-06-19 | 2025-06 | 15 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 1A/0 | BaLraJ | 2025-06-13 | 2025-06-21 | 2025-06 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 1B/1 | ATK Constructions | 2025-06-17 | 2025-06-21 | 2025-06 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 3/2 | Venkateshwarlu | 2025-05-24 | 2025-06-21 | 2025-06 | 29 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 43/1 | Ashok-2 (Venkateshwarlu) | 2025-06-13 | 2025-06-21 | 2025-06 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 2/3 | Ammu Engineering | 2025-06-02 | 2025-06-23 | 2025-06 | 22 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 10/6 | Subash | 2025-06-19 | 2025-06-24 | 2025-06 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 43/4 | Ashok-2 (Venkateshwarlu) | 2025-06-17 | 2025-06-24 | 2025-06 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 34/0 | Hassan | 2025-06-17 | 2025-06-25 | 2025-06 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/2 | ATK Constructions | 2025-06-20 | 2025-06-25 | 2025-06 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 11/2 | Subash | 2025-06-25 | 2025-06-28 | 2025-06 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 1C/0 | ATK Constructions | 2025-06-24 | 2025-06-29 | 2025-06 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 2/1 | Venkateshwarlu | 2025-06-18 | 2025-06-29 | 2025-06 | 12 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 43/0 | Ashok-2 (Venkateshwarlu) | 2025-06-25 | 2025-06-30 | 2025-06 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 11/3 | Subash | 2025-06-29 | 2025-07-02 | 2025-07 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 2/2 | ATK Constructions | 2025-06-18 | 2025-07-03 | 2025-07 | 16 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 15/0 | Naziruddin | 2025-06-24 | 2025-07-04 | 2025-07 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 35/2 | Hassan | 2025-06-25 | 2025-07-04 | 2025-07 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 39/4 | Hassan-2 | 2025-06-24 | 2025-07-05 | 2025-07 | 12 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 10/0 | Subash | 2025-07-03 | 2025-07-07 | 2025-07 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 20A/0 | Praveen | 2025-06-20 | 2025-07-07 | 2025-07 | 18 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/4 | ATK Constructions | 2025-07-02 | 2025-07-08 | 2025-07 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 2/0 | Venkateshwarlu | 2025-06-24 | 2025-07-10 | 2025-07 | 17 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 6/5 | Khatun | 2025-07-04 | 2025-07-10 | 2025-07 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 2/4 | Ammu Engineering | 2025-05-31 | 2025-07-12 | 2025-07 | 43 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 39/3 | Hassan-2 | 2025-07-06 | 2025-07-12 | 2025-07 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 9/10 | Subash |  | 2025-07-12 | 2025-07 |  | Missing Start Date | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 14/0 | Naziruddin |  | 2025-07-13 | 2025-07 |  | Missing Start Date | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 6/0 | ATK Constructions | 2025-07-08 | 2025-07-13 | 2025-07 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 43/5 | Ashok-2 (Venkateshwarlu) | 2025-06-29 | 2025-07-14 | 2025-07 | 16 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 6/4 | Khatun | 2025-07-11 | 2025-07-15 | 2025-07 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 34/2 | Hassan | 2025-07-05 | 2025-07-16 | 2025-07 | 12 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 5/0 | ATK Constructions | 2025-07-01 | 2025-07-16 | 2025-07 | 16 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 9/8 | Subash | 2025-07-13 | 2025-07-16 | 2025-07 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 6/3 | Khatun | 2025-07-15 | 2025-07-18 | 2025-07 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/3 | ATK Constructions | 2025-07-13 | 2025-07-18 | 2025-07 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 42/4 | D k Verma | 2025-07-12 | 2025-07-20 | 2025-07 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 43A/1 | Ashok-2 (Venkateshwarlu) | 2025-07-07 | 2025-07-20 | 2025-07 | 14 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 9/7 | Subash | 2025-07-17 | 2025-07-20 | 2025-07 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 6/2 | Khatun | 2025-07-19 | 2025-07-21 | 2025-07 | 3 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/6 | Naziruddin | 2025-07-14 | 2025-07-21 | 2025-07 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/1 | Ashok-2 (Venkateshwarlu) | 2025-07-19 | 2025-07-22 | 2025-07 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/22 | ATK Constructions | 2025-07-09 | 2025-07-25 | 2025-07 | 17 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 9/6 | Subash | 2025-07-21 | 2025-07-25 | 2025-07 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 43B/0 | Ashok-2 (Venkateshwarlu) | 2025-07-16 | 2025-07-28 | 2025-07 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 6/1 | Khatun | 2025-07-22 | 2025-07-28 | 2025-07 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 42/3 | D K Verma | 2025-07-21 | 2025-07-29 | 2025-07 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/14 | Naziruddin | 2025-07-22 | 2025-07-29 | 2025-07 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 39/0 | Hassan -2 | 2025-07-13 | 2025-07-30 | 2025-07 | 18 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 9/5 | Subash | 2025-07-26 | 2025-07-31 | 2025-07 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/21 | Khatun | 2025-07-29 | 2025-08-01 | 2025-08 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 16/7 | Praveen | 2025-07-08 | 2025-08-02 | 2025-08 | 26 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/8 | Naziruddin | 2025-07-30 | 2025-08-02 | 2025-08 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 35/0 | Hassan | 2025-07-17 | 2025-08-03 | 2025-08 | 18 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 43A/0 | Ashok-2 (Venkateshwarlu) | 2025-07-22 | 2025-08-03 | 2025-08 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 42/5 | D K Verma | 2025-07-30 | 2025-08-04 | 2025-08 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 6/6 | Khatun | 2025-08-02 | 2025-08-04 | 2025-08 | 3 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 11/0 | Subash | 2025-08-01 | 2025-08-06 | 2025-08 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/7 | Naziruddin | 2025-08-03 | 2025-08-07 | 2025-08 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/13 | Khatun | 2025-08-05 | 2025-08-08 | 2025-08 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/23 | Khatun | 2025-08-09 | 2025-08-11 | 2025-08 | 3 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 10/8 | Subash | 2025-08-07 | 2025-08-12 | 2025-08 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 34/1 | Hassan | 2025-08-04 | 2025-08-12 | 2025-08 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/12 | Naziruddin | 2025-08-08 | 2025-08-13 | 2025-08 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 42/6 | D k Verma | 2025-08-05 | 2025-08-14 | 2025-08 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 9/4 | Subash | 2025-08-13 | 2025-08-18 | 2025-08 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 9/1 | Khatun | 2025-08-12 | 2025-08-19 | 2025-08 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 42/7 | D k Verma | 2025-08-16 | 2025-08-24 | 2025-08 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 1/0 | Venkateshwarlu | 2025-08-11 | 2025-08-25 | 2025-08 | 15 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 12/1 | Subash | 2025-08-23 | 2025-08-29 | 2025-08 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 40/0 | Hassan | 2025-08-13 | 2025-08-29 | 2025-08 | 17 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 1A/0 | Khatun | 2025-08-20 | 2025-08-30 | 2025-08 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 9/0 | Naziruddin | 2025-08-14 | 2025-08-30 | 2025-08 | 17 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 42/1 | D k Verma | 2025-08-25 | 2025-08-31 | 2025-08 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 9/2 | Subash | 2025-08-19 | 2025-08-31 | 2025-08 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 2/3 | Shakila Khatun | 2025-08-31 | 2025-09-03 | 2025-09 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 9/9 | Subash | 2025-09-01 | 2025-09-04 | 2025-09 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 40/1 | Hassan | 2025-08-30 | 2025-09-05 | 2025-09 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 42/8 | D k Verma | 2025-09-01 | 2025-09-06 | 2025-09 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/6 | Subash | 2025-09-05 | 2025-09-07 | 2025-09 | 3 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/15 | Naziruddin | 2025-08-31 | 2025-09-07 | 2025-09 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 39/5 | Praveen | 2025-08-08 | 2025-09-08 | 2025-09 | 32 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/0 | Shakila Khatun | 2025-09-05 | 2025-09-08 | 2025-09 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/7 | Subash | 2025-09-08 | 2025-09-09 | 2025-09 | 2 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 42/9 | D k Verma | 2025-09-07 | 2025-09-10 | 2025-09 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 41/0 | Hassan | 2025-09-06 | 2025-09-13 | 2025-09 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/9 | Subash | 2025-09-10 | 2025-09-14 | 2025-09 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/9 | Naziruddin | 2025-09-08 | 2025-09-15 | 2025-09 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/12 | Khatun | 2025-09-09 | 2025-09-16 | 2025-09 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/10 | Subash | 2025-09-14 | 2025-09-20 | 2025-09 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 42/0 | D k Verma | 2025-09-13 | 2025-09-23 | 2025-09 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/2 | Subash | 2025-09-21 | 2025-09-24 | 2025-09 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 39/1 | Hassan | 2025-09-16 | 2025-09-25 | 2025-09 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/17 | Naziruddin | 2025-09-16 | 2025-09-26 | 2025-09 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 5/0 | Khatun | 2025-09-21 | 2025-09-29 | 2025-09 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 2/2 | Subash | 2025-09-25 | 2025-09-30 | 2025-09 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 43/2 | D k Verma | 2025-09-24 | 2025-09-30 | 2025-09 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/18 | Khatun | 2025-09-28 | 2025-10-04 | 2025-10 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 43/4 | Yadhav + D k Verma | 2025-09-21 | 2025-10-06 | 2025-10 | 16 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 1/0 | Subash | 2025-10-01 | 2025-10-09 | 2025-10 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 39/2 | Hassan | 2025-09-27 | 2025-10-09 | 2025-10 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 39/7 | Praveen | 2025-09-13 | 2025-10-11 | 2025-10 | 29 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 43/3 | D k Verma | 2025-10-07 | 2025-10-11 | 2025-10 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 9/3 | Khatun | 2025-10-07 | 2025-10-12 | 2025-10 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/3 | Subash | 2025-10-10 | 2025-10-15 | 2025-10 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 43/5 | D k Verma | 2025-10-12 | 2025-10-16 | 2025-10 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/20 | Khatun | 2025-10-13 | 2025-10-17 | 2025-10 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 19/0-20/0 | 2025-09-07 00:00:00 |  | 2025-10-19 | 2025-10 |  | Missing Start Date | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 36/7 | Hassan | 2025-10-10 | 2025-10-19 | 2025-10 | 10 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 18/0-19/0 | 2025-10-23 00:00:00 |  | 2025-10-21 | 2025-10 |  | Missing Start Date | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/4 | Subash | 2025-10-17 | 2025-10-21 | 2025-10 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 42/2 | D k Verma | 2025-10-17 | 2025-10-21 | 2025-10 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/19 | Khatun | 2025-10-17 | 2025-10-22 | 2025-10 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 41/1 | D k Verma | 2025-10-22 | 2025-10-25 | 2025-10 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 44/0 | Ashok-2 (Venkateshwarlu) | 2025-07-16 | 2025-10-26 | 2025-10 | 103 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 11/4 | Khatun | 2025-10-23 | 2025-10-27 | 2025-10 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 39/6 | Praveen | 2025-10-14 | 2025-10-27 | 2025-10 | 14 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/1 | Subash | 2025-10-22 | 2025-10-30 | 2025-10 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 11/7 | Khatun | 2025-10-28 | 2025-11-02 | 2025-11 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 36/8 | Hassan | 2025-10-21 | 2025-11-02 | 2025-11 | 13 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 43/1 | D k Verma | 2025-10-26 | 2025-11-02 | 2025-11 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/13 | Subash | 2025-10-31 | 2025-11-05 | 2025-11 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/3 | Khatun | 2025-11-04 | 2025-11-09 | 2025-11 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 3/1 | Subash | 2025-11-06 | 2025-11-11 | 2025-11 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 43B/0 | D k Verma | 2025-11-04 | 2025-11-11 | 2025-11 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/4 | Khatun | 2025-11-10 | 2025-11-14 | 2025-11 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 43A/5 | D k Verma | 2025-11-11 | 2025-11-17 | 2025-11 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 3/0 | Subash | 2025-11-11 | 2025-11-18 | 2025-11 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 11/8 | Khatun | 2025-11-15 | 2025-11-19 | 2025-11 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 36/0 | Hassan | 2025-11-08 | 2025-11-19 | 2025-11 | 12 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/14 | Subash | 2025-11-18 | 2025-11-20 | 2025-11 | 3 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 16/11 | GowriShankar | 2025-11-16 | 2025-11-23 | 2025-11 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 39/8 | Praveen | 2025-11-06 | 2025-11-23 | 2025-11 | 18 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/15 | Subash | 2025-11-21 | 2025-11-23 | 2025-11 | 3 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 43A/4 | D k Verma | 2025-11-18 | 2025-11-23 | 2025-11 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/10 | Khatun | 2025-11-20 | 2025-11-23 | 2025-11 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/16 | Subash |  | 2025-11-25 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 37/0 | Hassan | 2025-11-20 | 2025-11-26 | 2025-11 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 7/0 | ATK Constructions | 2025-11-11 | 2025-11-26 | 2025-11 | 16 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/11 | Khatun |  | 2025-11-26 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/11 | Subash | 2025-11-26 | 2025-11-28 | 2025-11 | 3 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 43A/3 | D k Verma | 2025-11-23 | 2025-11-29 | 2025-11 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/5 | Subash | 2025-11-28 | 2025-11-30 | 2025-11 | 3 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 6/0 | Khatun | 2025-11-27 | 2025-12-03 | 2025-12 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 1B/1 | Subash | 2025-11-30 | 2025-12-04 | 2025-12 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/0 | ATK Constructions |  | 2025-12-05 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 1B/2 | Subash | 2025-12-04 | 2025-12-06 | 2025-12 | 3 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 1B/3 | Subash | 2025-12-07 | 2025-12-08 | 2025-12 | 2 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/5 | Khatun | 2025-12-05 | 2025-12-08 | 2025-12 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 43/0 | D k Verma | 2025-12-01 | 2025-12-09 | 2025-12 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 27/3 | Gauri Shankar Mahto | 2025-11-26 | 2025-12-10 | 2025-12 | 15 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 2/1 | Subash | 2025-12-11 | 2025-12-13 | 2025-12 | 3 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 7/0 | Khatun | 2025-12-09 | 2025-12-13 | 2025-12 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 1B/0 | Subash | 2025-12-09 | 2025-12-16 | 2025-12 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 6/7 | Khatun | 2025-12-14 | 2025-12-16 | 2025-12 | 3 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 37/1 | Gauri Shankar Mahto | 2025-12-13 | 2025-12-18 | 2025-12 | 6 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 3/2 | Subash | 2025-12-17 | 2025-12-19 | 2025-12 | 3 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 44/0 | D k Verma | 2025-12-10 | 2025-12-20 | 2025-12 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 3/3 | Subash | 2025-12-20 | 2025-12-21 | 2025-12 | 2 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 39/9 | Praveen | 2025-11-27 | 2025-12-21 | 2025-12 | 25 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/2 | Khatun | 2025-12-17 | 2025-12-21 | 2025-12 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 2/4 | Subash | 2025-12-22 | 2025-12-23 | 2025-12 | 2 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 2/5 | Subash | 2025-12-24 | 2025-12-25 | 2025-12 | 2 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/0 | Khatun | 2025-12-22 | 2025-12-26 | 2025-12 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 43A/0 | Gauri Shankar Mahto | 2025-12-19 | 2025-12-29 | 2025-12 | 11 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 1C/0 | Subash | 2025-12-26 | 2025-12-30 | 2025-12 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/1 | Khatun | 2025-12-27 | 2025-12-31 | 2025-12 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/22 | D k Verma | 2025-12-27 | 2026-01-03 | 2026-01 | 8 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 2/0 | Subash | 2025-12-31 | 2026-01-04 | 2026-01 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/8 | Khatun | 2026-01-03 | 2026-01-06 | 2026-01 | 4 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 43A/1 | Gauri Shankar Mahto | 2025-12-30 | 2026-01-07 | 2026-01 | 9 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 43A/2 | Gauri Shankar Mahto | 2026-01-08 | 2026-01-12 | 2026-01 | 5 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 28/1 | Subash | 2026-01-07 | 2026-01-13 | 2026-01 | 7 | Valid | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 7/0 - 8/0 | 2026-01-31 00:00:00 |  | 2026-01-31 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | Gantry - 1/0 | 2026-02-01 00:00:00 |  | 2026-02-01 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/2 - 8/3 | 2026-02-04 00:00:00 |  | 2026-02-04 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 1/0-1A/0 | 2026-02-08 00:00:00 |  | 2026-02-08 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 1A/0 - 1B/0 | 2026-02-11 00:00:00 |  | 2026-02-11 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 4/12 - 5/0 | 2026-02-12 00:00:00 |  | 2026-02-12 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/0 - 8/1 | 2026-02-20 00:00:00 |  | 2026-02-19 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 8/1-8/2 | 2026-02-07 00:00:00 |  | 2026-02-19 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 1C/0 - 2/0 | 2026-02-25 00:00:00 |  | 2026-02-25 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 5/0 - 6/0 | 2026-03-02 00:00:00 |  | 2026-03-02 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Arun Felbin | TA 421 | TA421 |  | 3/0-4/0 | Unassigned |  | 2026-03-14 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 421 - DPR - 2026-06-16.xlsx | ProGress Sheet
Mr. Nabajit Baruah | TA 505 | TA505 |  | 171/10 | Unassigned |  | 2015-11-27 | 2015-11 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 164/3 | Unassigned |  | 2024-03-28 | 2024-03 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 170/4 | Unassigned |  | 2024-04-04 | 2024-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 136/0 | Unassigned |  | 2024-04-28 | 2024-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 101/2 | Unassigned | 2024-10-02 | 2024-10-06 | 2024-10 | 5 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 109/2 | Unassigned | 2024-10-01 | 2024-10-07 | 2024-10 | 7 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 101/3 | Unassigned | 2024-10-08 | 2024-10-11 | 2024-10 | 4 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 110A/2 | Unassigned | 2024-10-07 | 2024-10-11 | 2024-10 | 5 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 101/4 | Unassigned | 2024-10-19 | 2024-10-21 | 2024-10 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 110/6 | Unassigned | 2024-10-22 | 2024-10-24 | 2024-10 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 101/5 | Unassigned | 2024-10-23 | 2024-10-25 | 2024-10 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 108/4 | Unassigned | 2024-10-27 | 2024-10-28 | 2024-10 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 109/1 | Unassigned | 2024-10-26 | 2024-10-29 | 2024-10 | 4 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 101/6 | Unassigned | 2024-10-30 | 2024-11-02 | 2024-11 | 4 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 111/1 | Unassigned | 2024-10-30 | 2024-11-04 | 2024-11 | 6 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 101/8 | Unassigned | 2024-11-07 | 2024-11-08 | 2024-11 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 110A/1 | Unassigned | 2024-11-08 | 2024-11-10 | 2024-11 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 101/1 | Unassigned | 2024-11-13 | 2024-11-14 | 2024-11 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 113/2 | Unassigned | 2024-11-14 | 2024-11-14 | 2024-11 | 1 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 110/8 | Unassigned | 2024-11-14 | 2024-11-15 | 2024-11 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 110/3 | Unassigned | 2024-11-14 | 2024-11-17 | 2024-11 | 4 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 101/7 | Unassigned | 2024-11-17 | 2024-11-18 | 2024-11 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 111/2 | Unassigned | 2024-11-15 | 2024-11-18 | 2024-11 | 4 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 105/1 | Unassigned | 2024-11-12 | 2024-11-19 | 2024-11 | 8 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 114/10 | Unassigned | 2024-11-19 | 2024-11-20 | 2024-11 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 110/1 | Unassigned | 2024-11-18 | 2024-11-22 | 2024-11 | 5 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 113/1 | Unassigned | 2024-11-20 | 2024-11-22 | 2024-11 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 110/5 | Unassigned | 2024-11-21 | 2024-11-23 | 2024-11 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 114/8 | Unassigned | 2024-11-22 | 2024-11-23 | 2024-11 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 104/1 | Unassigned | 2024-11-25 | 2024-11-27 | 2024-11 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 114/9 | Unassigned | 2024-11-26 | 2024-11-27 | 2024-11 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 114/7 | Unassigned | 2024-11-25 | 2024-11-28 | 2024-11 | 4 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 110/2 | Unassigned | 2024-11-25 | 2024-11-29 | 2024-11 | 5 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 110/7 | Unassigned | 2024-11-27 | 2024-11-29 | 2024-11 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 113/3 | Unassigned | 2024-11-27 | 2024-11-29 | 2024-11 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 105/0 | Unassigned | 2024-11-29 | 2024-11-30 | 2024-11 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 108/2 | Unassigned | 2024-11-29 | 2024-11-30 | 2024-11 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 109/3 | Unassigned | 2024-11-29 | 2024-11-30 | 2024-11 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 114/6 | Unassigned | 2024-11-29 | 2024-11-30 | 2024-11 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 116/2 | Unassigned | 2024-11-29 | 2024-12-01 | 2024-12 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 104/2 | Unassigned | 2024-11-29 | 2024-12-03 | 2024-12 | 5 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 113/5 | Unassigned | 2024-12-04 | 2024-12-05 | 2024-12 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 114/3 | Unassigned | 2024-12-03 | 2024-12-07 | 2024-12 | 5 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 114/5 | Unassigned | 2024-12-06 | 2024-12-07 | 2024-12 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 111/3 | Unassigned | 2024-11-02 | 2024-12-08 | 2024-12 | 37 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 113/4 | Unassigned | 2024-12-07 | 2024-12-09 | 2024-12 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 127/3 | Unassigned | 2024-12-07 | 2024-12-10 | 2024-12 | 4 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 113/6 | Unassigned | 2024-12-10 | 2024-12-12 | 2024-12 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 108/1 | Unassigned | 2024-12-08 | 2024-12-13 | 2024-12 | 6 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 102/0 | Unassigned | 2024-12-11 | 2024-12-14 | 2024-12 | 4 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 114/2 | Unassigned | 2024-12-12 | 2024-12-14 | 2024-12 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 127/2 | Unassigned | 2024-12-13 | 2024-12-15 | 2024-12 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 111/4 | Unassigned | 2024-12-14 | 2024-12-16 | 2024-12 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 126/0 | Unassigned | 2024-12-14 | 2024-12-16 | 2024-12 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 110/0 | Unassigned | 2024-12-12 | 2024-12-17 | 2024-12 | 6 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 126/4 | Unassigned | 2024-12-17 | 2024-12-17 | 2024-12 | 1 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 108/3 | Unassigned | 2024-12-14 | 2024-12-19 | 2024-12 | 6 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 114/0 | Unassigned | 2024-12-11 | 2024-12-19 | 2024-12 | 9 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 147A/4 | Unassigned | 2024-12-18 | 2024-12-19 | 2024-12 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 127/1 | Unassigned | 2024-12-18 | 2024-12-20 | 2024-12 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 150/3 | Unassigned | 2024-12-19 | 2024-12-21 | 2024-12 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 152A/3 | Unassigned | 2024-12-21 | 2024-12-22 | 2024-12 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 147A/5 | Unassigned | 2024-12-22 | 2024-12-24 | 2024-12 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 150/4 | Unassigned | 2024-12-22 | 2024-12-24 | 2024-12 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 116/1 | Unassigned | 2024-12-26 | 2024-12-26 | 2024-12 | 1 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 152/2 | Unassigned | 2024-12-25 | 2024-12-26 | 2024-12 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 147A/1 | Unassigned | 2024-12-27 | 2024-12-27 | 2024-12 | 1 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 152A/4 | Unassigned | 2024-12-26 | 2024-12-27 | 2024-12 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 150/5 | Unassigned | 2024-12-27 | 2024-12-28 | 2024-12 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 127/0 | Unassigned | 2024-12-25 | 2024-12-29 | 2024-12 | 5 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 152A/9 | Unassigned | 2024-12-29 | 2024-12-29 | 2024-12 | 1 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 152/1 | Unassigned | 2024-12-29 | 2024-12-30 | 2024-12 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 109/0 | Unassigned | 2024-12-29 | 2024-12-31 | 2024-12 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 114/1 | Unassigned | 2024-12-29 | 2024-12-31 | 2024-12 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 147A/2 | Unassigned | 2024-12-29 | 2024-12-31 | 2024-12 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 152A/5 | Unassigned | 2024-12-31 | 2025-01-02 | 2025-01 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 111/0 | Unassigned | 2025-01-03 | 2025-01-04 | 2025-01 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 147/1 | Unassigned | 2025-01-04 | 2025-01-05 | 2025-01 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 152A/7 | Unassigned | 2025-01-04 | 2025-01-05 | 2025-01 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 152A/1 | Unassigned | 2025-01-08 | 2025-01-10 | 2025-01 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 120/1 | Unassigned | 2025-01-06 | 2025-01-12 | 2025-01 | 7 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 150/1 | Unassigned | 2025-01-09 | 2025-01-12 | 2025-01 | 4 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 103/7 | Unassigned | 2025-01-11 | 2025-01-15 | 2025-01 | 5 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 155/5 | Unassigned | 2025-01-13 | 2025-01-15 | 2025-01 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 144A/1 | Unassigned | 2025-01-15 | 2025-01-16 | 2025-01 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 152A/8 | Unassigned | 2025-01-08 | 2025-01-16 | 2025-01 | 9 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 131/0 | Unassigned | 2025-01-12 | 2025-01-17 | 2025-01 | 6 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 152A/0 | Unassigned | 2025-01-14 | 2025-01-17 | 2025-01 | 4 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 126/2 | Unassigned | 2025-01-18 | 2025-01-18 | 2025-01 | 1 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 144A/3 | Unassigned | 2025-01-18 | 2025-01-19 | 2025-01 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 126/3 | Unassigned | 2025-01-20 | 2025-01-20 | 2025-01 | 1 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 152A/11 | Unassigned | 2025-01-20 | 2025-01-21 | 2025-01 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 155/3 | Unassigned | 2025-01-20 | 2025-01-21 | 2025-01 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 150/2 | Unassigned | 2025-01-19 | 2025-01-22 | 2025-01 | 4 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 152A/6 | Unassigned | 2025-01-23 | 2025-01-23 | 2025-01 | 1 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 120/3 | Unassigned | 2025-01-23 | 2025-01-24 | 2025-01 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 152/3 | Unassigned | 2025-01-24 | 2025-01-25 | 2025-01 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 152A/10 | Unassigned | 2025-01-25 | 2025-01-25 | 2025-01 | 1 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 112/0 | Unassigned | 2025-01-24 | 2025-01-27 | 2025-01 | 4 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 152A/2 | Unassigned | 2025-01-27 | 2025-01-28 | 2025-01 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 120/2 | Unassigned | 2025-01-29 | 2025-01-30 | 2025-01 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 154/1 | Unassigned | 2025-01-29 | 2025-01-30 | 2025-01 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 128/0 | Unassigned | 2025-01-29 | 2025-01-31 | 2025-01 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 130/1 | Unassigned | 2025-01-31 | 2025-01-31 | 2025-01 | 1 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 148/0 | Unassigned | 2025-01-28 | 2025-01-31 | 2025-01 | 4 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 154/2 | Unassigned | 2025-01-31 | 2025-02-04 | 2025-02 | 5 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 140/1 | Unassigned | 2025-02-04 | 2025-02-05 | 2025-02 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 156/4 | Unassigned | 2025-02-05 | 2025-02-05 | 2025-02 | 1 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 129A/3 | Unassigned | 2025-02-06 | 2025-02-06 | 2025-02 | 1 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 104/0 | Unassigned | 2025-02-05 | 2025-02-07 | 2025-02 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 154/5 | Unassigned | 2025-02-07 | 2025-02-08 | 2025-02 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 130/2 | Unassigned | 2025-02-08 | 2025-02-09 | 2025-02 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 129A/2 | Unassigned | 2025-02-10 | 2025-02-10 | 2025-02 | 1 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 155/4 | Unassigned | 2025-02-07 | 2025-02-10 | 2025-02 | 4 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 129A/1 | Unassigned | 2025-02-11 | 2025-02-11 | 2025-02 | 1 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 156/1 | Unassigned | 2025-02-08 | 2025-02-12 | 2025-02 | 5 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 148A/0 | Unassigned | 2025-02-09 | 2025-02-13 | 2025-02 | 5 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 130/0 | Unassigned | 2025-02-12 | 2025-02-14 | 2025-02 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 160/3 | Unassigned | 2025-02-15 | 2025-02-15 | 2025-02 | 1 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 159/3 | Unassigned | 2025-02-16 | 2025-02-16 | 2025-02 | 1 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 109/4 | Unassigned | 2025-02-15 | 2025-02-17 | 2025-02 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 135/1 | Unassigned | 2025-02-16 | 2025-02-17 | 2025-02 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 110A/0 | Unassigned | 2025-02-19 | 2025-02-20 | 2025-02 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 135/2 | Unassigned | 2025-02-18 | 2025-02-21 | 2025-02 | 4 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 135/3 | Unassigned | 2025-02-21 | 2025-02-22 | 2025-02 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 156/3 | Unassigned | 2025-02-19 | 2025-02-22 | 2025-02 | 4 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 155/1 | Unassigned | 2025-02-16 | 2025-02-24 | 2025-02 | 9 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 159/0 | Unassigned | 2025-02-22 | 2025-02-24 | 2025-02 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 136/1 | Unassigned | 2025-02-24 | 2025-02-25 | 2025-02 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 160/0 | Unassigned | 2025-01-23 | 2025-02-25 | 2025-02 | 34 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 164/5 | Unassigned | 2025-02-24 | 2025-02-26 | 2025-02 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 118/0 | Unassigned | 2025-02-24 | 2025-02-27 | 2025-02 | 4 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 136/5 | Unassigned | 2025-02-27 | 2025-02-27 | 2025-02 | 1 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 161/4 | Unassigned | 2025-02-26 | 2025-02-27 | 2025-02 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 154/3 | Unassigned | 2025-02-03 | 2025-02-28 | 2025-02 | 26 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 155/2 | Unassigned | 2025-02-25 | 2025-02-28 | 2025-02 | 4 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 160/2 | Unassigned | 2025-02-27 | 2025-02-28 | 2025-02 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 160/1 | Unassigned | 2025-03-04 | 2025-03-04 | 2025-03 | 1 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 135/0 | Unassigned | 2025-03-04 | 2025-03-05 | 2025-03 | 2 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 161/2 | Unassigned | 2025-03-06 | 2025-03-06 | 2025-03 | 1 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 164/6 | Unassigned |  | 2025-03-07 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 160/4 | Unassigned |  | 2025-03-08 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 161/5 | Unassigned | 2025-03-09 | 2025-03-11 | 2025-03 | 3 | Valid | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 140/0 | Unassigned |  | 2025-03-12 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 164/4 | Unassigned |  | 2025-03-16 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 159/1 | Unassigned |  | 2025-03-19 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 144A/0 | Unassigned |  | 2025-03-22 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 161/1 | Unassigned |  | 2025-03-26 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 144A/2 | Unassigned |  | 2025-03-28 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 166/4 | Unassigned |  | 2025-03-28 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 170/3 | Unassigned |  | 2025-03-29 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 170/2 | Unassigned |  | 2025-03-30 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 147/0 | Unassigned |  | 2025-03-31 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 160/5 | Unassigned |  | 2025-03-31 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 161/3 | Unassigned |  | 2025-03-31 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 164/2 | Unassigned |  | 2025-03-31 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 166/5 | Unassigned |  | 2025-03-31 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 170/8 | Unassigned |  | 2025-03-31 | 2025-03 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 115/0 | Unassigned |  | 2025-04-03 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 116/0 | Unassigned |  | 2025-04-07 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 169/3 | Unassigned |  | 2025-04-07 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 170/9 | Unassigned |  | 2025-04-07 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 164/7 | Unassigned |  | 2025-04-08 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 166/8 | Unassigned |  | 2025-04-08 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 165/6 | Unassigned |  | 2025-04-09 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 147A/0 | Unassigned |  | 2025-04-10 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 147A/3 | Unassigned |  | 2025-04-10 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 172/2 | Unassigned |  | 2025-04-10 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 170/1 | Unassigned |  | 2025-04-11 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 120/0 | Unassigned |  | 2025-04-12 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 148/1 | Unassigned |  | 2025-04-12 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 170/10 | Unassigned |  | 2025-04-12 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 173/3 | Unassigned |  | 2025-04-12 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 165/4 | Unassigned |  | 2025-04-13 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 166/6 | Unassigned |  | 2025-04-13 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 169/2 | Unassigned |  | 2025-04-14 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 119/0 | Unassigned |  | 2025-04-15 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 164/8 | Unassigned |  | 2025-04-15 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 173/4 | Unassigned |  | 2025-04-16 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 170/7 | Unassigned |  | 2025-04-17 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 165/3 | Unassigned |  | 2025-04-18 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 172/3 | Unassigned |  | 2025-04-18 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 166/3 | Unassigned |  | 2025-04-20 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 166/9 | Unassigned |  | 2025-04-20 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 173/2 | Unassigned |  | 2025-04-20 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 103/4 | Unassigned |  | 2025-04-22 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 106/0 | Unassigned |  | 2025-04-22 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 132/0 | Unassigned |  | 2025-04-22 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 170/5 | Unassigned |  | 2025-04-22 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 171/1 | Unassigned |  | 2025-04-22 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 166/0 | Unassigned |  | 2025-04-24 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 169/1 | Unassigned |  | 2025-04-24 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 175/4 | Unassigned |  | 2025-04-24 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 167/4 | Unassigned |  | 2025-04-26 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 171/2 | Unassigned |  | 2025-04-26 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 172/1 | Unassigned |  | 2025-04-26 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 173/1 | Unassigned |  | 2025-04-26 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 175/3 | Unassigned |  | 2025-04-26 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 108/0 | Unassigned |  | 2025-04-27 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 161/0 | Unassigned |  | 2025-04-28 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 166/2 | Unassigned |  | 2025-04-28 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 170/6 | Unassigned |  | 2025-04-28 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 165/5 | Unassigned |  | 2025-04-29 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 165/1 | Unassigned |  | 2025-04-30 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 167/5 | Unassigned |  | 2025-04-30 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 176/1 | Unassigned |  | 2025-04-30 | 2025-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 103/5A | Unassigned |  | 2025-05-03 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 136/2 | Unassigned |  | 2025-05-03 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 167/0 | Unassigned |  | 2025-05-03 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 159/2 | Unassigned |  | 2025-05-04 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 169/4 | Unassigned |  | 2025-05-04 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 171/9 | Unassigned |  | 2025-05-04 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 176/0 | Unassigned |  | 2025-05-04 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 103/5A1 | Unassigned |  | 2025-05-05 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 176/2 | Unassigned |  | 2025-05-06 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 103/3 | Unassigned |  | 2025-05-08 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 178/1 | Unassigned |  | 2025-05-08 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 158/3 | Unassigned |  | 2025-05-09 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 167/1 | Unassigned |  | 2025-05-09 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 174A/3 | Unassigned |  | 2025-05-10 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 176/3 | Unassigned |  | 2025-05-10 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 103/1 | Unassigned |  | 2025-05-11 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 169/5 | Unassigned |  | 2025-05-11 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 103/2 | Unassigned |  | 2025-05-13 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 141/0 | Unassigned |  | 2025-05-13 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 166/1 | Unassigned |  | 2025-05-13 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 158/2 | Unassigned |  | 2025-05-16 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 170/0 | Unassigned |  | 2025-05-16 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 171/8 | Unassigned |  | 2025-05-17 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 177/1 | Unassigned |  | 2025-05-17 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 103/6A | Unassigned |  | 2025-05-18 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 178/0 | Unassigned |  | 2025-05-18 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 142/0 | Unassigned |  | 2025-05-20 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 171/4 | Unassigned |  | 2025-05-21 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 172/4 | Unassigned |  | 2025-05-21 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 177/2 | Unassigned |  | 2025-05-21 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 103/0 | Unassigned |  | 2025-05-22 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 172/6 | Unassigned |  | 2025-05-23 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 174A/4 | Unassigned |  | 2025-05-23 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 177/3 | Unassigned |  | 2025-05-23 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 103/8 | Unassigned |  | 2025-05-24 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 169/6 | Unassigned |  | 2025-05-25 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 177/8 | Unassigned |  | 2025-05-25 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 167/2 | Unassigned |  | 2025-05-27 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 177/4 | Unassigned |  | 2025-05-27 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 167/3 | Unassigned |  | 2025-05-29 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 174A/5 | Unassigned |  | 2025-05-29 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 177/5 | Unassigned |  | 2025-05-29 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 172/5 | Unassigned |  | 2025-05-30 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 178/3 | Unassigned |  | 2025-05-30 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 101/0 | Unassigned |  | 2025-05-31 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 150/0 | Unassigned |  | 2025-05-31 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 177/6 | Unassigned |  | 2025-05-31 | 2025-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 121/0 | Unassigned |  | 2025-06-02 | 2025-06 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 171/7 | Unassigned |  | 2025-06-03 | 2025-06 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 177/7 | Unassigned |  | 2025-06-03 | 2025-06 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 174A/1 | Unassigned |  | 2025-06-04 | 2025-06 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 173/0 | Unassigned |  | 2025-06-05 | 2025-06 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 110/4 | Unassigned |  | 2025-06-07 | 2025-06 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 171/0 | Unassigned |  | 2025-06-08 | 2025-06 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 171/3 | Unassigned |  | 2025-06-08 | 2025-06 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 172/0 | Unassigned |  | 2025-06-09 | 2025-06 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 152/0 | Unassigned |  | 2025-06-11 | 2025-06 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 152A/12 | Unassigned |  | 2025-06-13 | 2025-06 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 174A/0 | Unassigned |  | 2025-06-13 | 2025-06 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 174A/2 | Unassigned |  | 2025-06-28 | 2025-06 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 151/0 | Unassigned |  | 2025-06-29 | 2025-06 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 171/6 | Unassigned |  | 2025-06-29 | 2025-06 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 156/0 | Unassigned |  | 2025-07-15 | 2025-07 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 169/7 | Unassigned |  | 2025-07-17 | 2025-07 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 179/7 | Unassigned |  | 2025-08-29 | 2025-08 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 178/4 | Unassigned |  | 2025-09-04 | 2025-09 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 178/5 | Unassigned |  | 2025-09-12 | 2025-09 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 179/6 | Unassigned |  | 2025-09-12 | 2025-09 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 145/0 | Unassigned |  | 2025-09-14 | 2025-09 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 114/4 | Unassigned |  | 2025-09-19 | 2025-09 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 179/1 | Unassigned |  | 2025-09-23 | 2025-09 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 179/4 | Unassigned |  | 2025-09-26 | 2025-09 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 149B/3 | Unassigned |  | 2025-09-27 | 2025-09 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 179/2 | Unassigned |  | 2025-09-29 | 2025-09 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 154/4 | Unassigned |  | 2025-09-30 | 2025-09 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 126/1 | Unassigned |  | 2025-10-05 | 2025-10 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 149B/1 | Unassigned |  | 2025-10-09 | 2025-10 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 149B/2 | Unassigned |  | 2025-10-15 | 2025-10 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 100/0 | Unassigned |  | 2025-10-16 | 2025-10 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 178/2 | Unassigned |  | 2025-10-16 | 2025-10 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 149B/4 | Unassigned |  | 2025-10-17 | 2025-10 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 155/0 | Unassigned |  | 2025-10-17 | 2025-10 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 99/8 | Unassigned |  | 2025-10-17 | 2025-10 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 165/0 | Unassigned |  | 2025-10-22 | 2025-10 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 168/0 | Unassigned |  | 2025-10-25 | 2025-10 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 99/6 | Unassigned |  | 2025-10-25 | 2025-10 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 180/0 | Unassigned |  | 2025-10-30 | 2025-10 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 99/4 | Unassigned |  | 2025-11-01 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 99/5 | Unassigned |  | 2025-11-03 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 99/3 | Unassigned |  | 2025-11-06 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 165/2 | Unassigned |  | 2025-11-07 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 99/2 | Unassigned |  | 2025-11-09 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 181/6 | Unassigned |  | 2025-11-10 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 99/1 | Unassigned |  | 2025-11-11 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 103/5 | Unassigned |  | 2025-11-14 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 99/7 | Unassigned |  | 2025-11-16 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 181/1 | Unassigned |  | 2025-11-18 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 103/9 | Unassigned |  | 2025-11-19 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 169/0 | Unassigned |  | 2025-11-20 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 122/0 | Unassigned |  | 2025-11-26 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 175/2 | Unassigned |  | 2025-11-26 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 181/4 | Unassigned |  | 2025-11-27 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 138/0 | Unassigned |  | 2025-11-29 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 123/0 | Unassigned |  | 2025-12-03 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 181/5 | Unassigned |  | 2025-12-06 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 123/1 | Unassigned |  | 2025-12-08 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 169/9 | Unassigned |  | 2025-12-08 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 179/5 | Unassigned |  | 2025-12-10 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 123/3 | Unassigned |  | 2025-12-12 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 153/0 | Unassigned |  | 2025-12-13 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 154/0 | Unassigned |  | 2025-12-14 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 125/1 | Unassigned |  | 2025-12-15 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 175/1 | Unassigned |  | 2025-12-15 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 123/2 | Unassigned |  | 2025-12-22 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 129A/0 | Unassigned |  | 2025-12-23 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 181/0 | Unassigned |  | 2025-12-24 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 113/0 | Unassigned |  | 2025-12-28 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 175/0 | Unassigned |  | 2025-12-30 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 149B/0 | Unassigned |  | 2025-12-31 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 158/0 | Unassigned |  | 2025-12-31 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 158/1 | Unassigned |  | 2025-12-31 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 125/0 | Unassigned |  | 2026-01-04 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 162/0 | Unassigned |  | 2026-01-07 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 162/2 | Unassigned |  | 2026-01-08 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 124/0 | Unassigned |  | 2026-01-09 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 179/9 | Unassigned |  | 2026-01-11 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 149/0 | Unassigned |  | 2026-01-13 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 149/2 | Unassigned |  | 2026-01-16 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 149/1 | Unassigned |  | 2026-01-18 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 164/0 | Unassigned |  | 2026-01-19 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 174B/0 | Unassigned |  | 2026-01-22 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 163/0 | Unassigned |  | 2026-01-23 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 162/1 | Unassigned |  | 2026-01-24 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 146/1 | Unassigned |  | 2026-01-25 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 164/1 | Unassigned |  | 2026-01-25 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 182/0 | Unassigned |  | 2026-01-25 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 148B/1 | Unassigned |  | 2026-01-29 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 149A/0 | Unassigned |  | 2026-01-31 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 139/0 | Unassigned |  | 2026-02-04 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 139/1 | Unassigned |  | 2026-02-06 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 156/6 | Unassigned |  | 2026-02-07 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 138/1 | Unassigned |  | 2026-02-10 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 138/3 | Unassigned |  | 2026-02-12 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 148B/2 | Unassigned |  | 2026-02-15 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 146/0 | Unassigned |  | 2026-02-19 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 148C/0 | Unassigned |  | 2026-02-21 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 142/1 | Unassigned |  | 2026-02-24 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 148B/0 | Unassigned |  | 2026-02-28 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 156/5 | Unassigned |  | 2026-03-03 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 169/8 | Unassigned |  | 2026-03-08 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 156/2 | Unassigned |  | 2026-03-10 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 157/0 | Unassigned |  | 2026-03-10 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 138/2 | Unassigned |  | 2026-03-11 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 144/0 | Unassigned |  | 2026-03-21 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 171/5 | Unassigned |  | 2026-03-21 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 143/0 | Unassigned |  | 2026-03-31 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 134/0 | Unassigned |  | 2026-04-09 | 2026-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 137A/0 | Unassigned |  | 2026-04-09 | 2026-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 129/0 | Unassigned |  | 2026-04-14 | 2026-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 133/0 | Unassigned |  | 2026-04-14 | 2026-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 136/4 | Unassigned |  | 2026-04-15 | 2026-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 136/3 | Unassigned |  | 2026-04-18 | 2026-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 129/1 | Unassigned |  | 2026-04-23 | 2026-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 117/0 | Unassigned |  | 2026-04-30 | 2026-04 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 137/0 | Unassigned |  | 2026-05-15 | 2026-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 177/0 | Unassigned |  | 2026-05-15 | 2026-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 181/2 | Unassigned |  | 2026-05-18 | 2026-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 181/3 | Unassigned |  | 2026-05-25 | 2026-05 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 505 | TA505 |  | 179/0 | Unassigned |  | 2026-06-15 | 2026-06 |  | Missing Start Date | detail | detail_date | TA 505 - DPR - 2026-06-16.xlsx | Foundation
Mr. Nabajit Baruah | TA 509 | TA509 |  |  | Unassigned |  | 2026-05-31 | 2026-05 |  | Missing Start Date | snapshot_fallback | snapshot_cumulative | TA 509 - DPR - 2026-05-31.xlsx | SUMMARY
Mr. Nabajit Baruah | TA 509 | TA509 |  |  | Unassigned |  | 2026-06-16 | 2026-06 |  | Missing Start Date | snapshot_fallback | snapshot_cumulative | TA 509 - DPR - 2026-06-16.xlsx | SUMMARY
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 155/1 | Arya Enterprises | 2025-02-12 | 2025-02-17 | 2025-02 | 6 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 155/4 | B.K.Traders | 2025-02-18 | 2025-02-22 | 2025-02 | 5 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 155/3 | Arya Enterprises | 2025-02-18 | 2025-02-25 | 2025-02 | 8 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 155/5 | B.K.Traders | 2025-02-23 | 2025-02-27 | 2025-02 | 5 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 156/0 | B.K.Traders | 2025-03-05 | 2025-03-12 | 2025-03 | 8 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 156/1 | Arya Enterprises | 2025-03-05 | 2025-03-13 | 2025-03 | 9 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 156/3 | B.K.Traders | 2025-03-13 | 2025-03-16 | 2025-03 | 4 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 156/4 | Arya Enterprises | 2025-03-21 | 2025-03-25 | 2025-03 | 5 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 156/2 | Arya Enterprises | 2025-03-26 | 2025-03-30 | 2025-03 | 5 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 139/1 | Om Infra | 2025-03-26 | 2025-04-16 | 2025-04 | 22 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 138/0 | Om Infra | 2025-04-05 | 2025-04-21 | 2025-04 | 17 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 139/5 | B.K.Traders | 2025-04-14 | 2025-04-21 | 2025-04 | 8 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 137/0 | Om Infra | 2025-04-14 | 2025-04-27 | 2025-04 | 14 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 139/4 | B.K.Traders | 2025-04-23 | 2025-04-28 | 2025-04 | 6 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 138/1 | Om Infra | 2025-04-14 | 2025-04-29 | 2025-04 | 16 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 136/0 | Om Infra | 2025-04-25 | 2025-05-14 | 2025-05 | 20 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 148/5 | B.K.Traders | 2025-05-03 | 2025-05-15 | 2025-05 | 13 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 148/4 | B.K.Traders | 2025-05-13 | 2025-05-21 | 2025-05 | 9 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 148/2 | B.K.Traders | 2025-05-15 | 2025-05-23 | 2025-05 | 9 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 134/0 | Om Infra | 2025-05-15 | 2025-05-25 | 2025-05 | 11 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 148/7 | B.K.Traders | 2025-05-17 | 2025-05-28 | 2025-05 | 12 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 148/6 | B.K.Traders | 2025-05-19 | 2025-05-31 | 2025-05 | 13 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 143/1 | Jyoti Construction | 2025-05-25 | 2025-06-02 | 2025-06 | 9 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 143/2 | Jyoti Construction | 2025-05-30 | 2025-06-05 | 2025-06 | 7 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 144/0 | Jyoti Construction | 2025-06-01 | 2025-08-06 | 2025-08 | 67 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 141/0 | Unassigned | 2025-07-23 | 2025-09-16 | 2025-09 | 56 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 133/2 | B.K.Traders | 2025-08-31 | 2025-09-18 | 2025-09 | 19 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 141/1 | Shakaldev | 2025-09-21 | 2025-10-04 | 2025-10 | 14 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 138/2 | Vihan | 2025-09-19 | 2025-10-05 | 2025-10 | 17 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 140/1 | Shakaldev | 2025-09-24 | 2025-10-10 | 2025-10 | 17 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 145/0 | Vihan | 2025-09-25 | 2025-10-19 | 2025-10 | 25 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 139/2 | Shakaldev | 2025-10-15 | 2025-10-24 | 2025-10 | 10 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 140/2 | Shakaldev | 2025-09-10 | 2025-11-19 | 2025-11 | 71 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 135/0 | B.K.Traders | 2025-11-11 | 2025-11-24 | 2025-11 | 14 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 145/1 | MD Hussain | 2025-11-11 | 2025-11-24 | 2025-11 | 14 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 138/3 | Shakaldev | 2025-11-18 | 2025-11-27 | 2025-11 | 10 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 192/11 | Rudra | 2025-11-15 | 2025-11-30 | 2025-11 | 16 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 141/2 | MD Hussain | 2025-11-30 | 2025-12-07 | 2025-12 | 8 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 143/0 | Shakaldev | 2025-11-30 | 2025-12-09 | 2025-12 | 10 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 145/5 | Ambani | 2025-11-15 | 2025-12-09 | 2025-12 | 25 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 148/3 | Haji Enterprises | 2025-11-27 | 2025-12-14 | 2025-12 | 18 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 192/13 | Rudra | 2025-12-01 | 2025-12-23 | 2025-12 | 23 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 145/3 | Vihan | 2025-12-01 | 2025-12-27 | 2025-12 | 27 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 146/1 | MD Hussain | 2025-12-10 | 2025-12-29 | 2025-12 | 20 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 140/0 | Shakaldev | 2025-12-16 | 2025-12-30 | 2025-12 | 15 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 146/3 | Haji Enterprises | 2025-12-21 | 2025-12-30 | 2025-12 | 10 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 145/4 | Shakaldev | 2025-12-10 | 2025-12-31 | 2025-12 | 22 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 192/10 | Chandrakant Patel | 2025-12-21 | 2026-01-04 | 2026-01 | 15 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 147/2 | MD Hussain | 2026-01-01 | 2026-01-08 | 2026-01 | 8 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 146A/0 | Haji Enterprises | 2025-12-15 | 2026-01-13 | 2026-01 | 30 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 186/1 | Maa Bhavani | 2026-01-05 | 2026-01-13 | 2026-01 | 9 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 192/7 | Chandrakant Patel | 2026-01-09 | 2026-01-21 | 2026-01 | 13 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 192/12 | Maa Bhavani | 2026-01-16 | 2026-01-25 | 2026-01 | 10 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 147/1 | Vihan | 2026-01-08 | 2026-01-30 | 2026-01 | 23 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 142/0 | Haji Enterprises | 2026-01-27 | 2026-02-02 | 2026-02 | 7 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 146/0 | MD Hussain | 2026-01-06 | 2026-02-03 | 2026-02 | 29 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 194/1 | Chandrakant Patel | 2026-02-01 | 2026-02-10 | 2026-02 | 10 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 146A/1 | Haji Enterprises | 2026-02-02 | 2026-02-12 | 2026-02 | 11 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 148/1 | ABS Construction | 2026-02-03 | 2026-02-14 | 2026-02 | 12 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 148/0 | Vihan | 2026-02-01 | 2026-02-27 | 2026-02 | 27 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 157B/0 | Haji Enterprises | 2026-02-16 | 2026-03-11 | 2026-03 | 24 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 157A/0 | ABS Construction | 2026-02-17 | 2026-03-22 | 2026-03 | 34 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 157/2 | Haji Enterprises | 2026-03-14 | 2026-03-23 | 2026-03 | 10 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 146/2 | Haji Enterprises | 2026-02-17 | 2026-03-31 | 2026-03 | 43 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 192/9 | BLG Infra | 2026-04-02 | 2026-04-07 | 2026-04 | 6 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 139/3 | Haji Enterprises | 2026-04-04 | 2026-04-13 | 2026-04 | 10 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 193/2 | BLG Infra | 2026-04-08 | 2026-04-13 | 2026-04 | 6 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 193/1 | BLG Infra | 2026-04-12 | 2026-04-19 | 2026-04 | 8 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 193/5 | Chandrakant Patel | 2026-04-14 | 2026-04-20 | 2026-04 | 7 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 139/0 | Haji Enterprises | 2026-04-01 | 2026-04-21 | 2026-04 | 21 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 193/0 | BLG Infra | 2026-04-19 | 2026-04-28 | 2026-04 | 10 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 193/4 | Chandrakant Patel | 2026-04-19 | 2026-04-29 | 2026-04 | 11 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 192/8 | BLG Infra | 2026-04-29 | 2026-05-06 | 2026-05 | 8 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 167/2 | BLG Infra | 2026-05-07 | 2026-05-13 | 2026-05 | 7 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 157B/1 | JDG Enterprises | 2026-04-22 | 2026-05-16 | 2026-05 | 25 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 167/3 | BLG Infra | 2026-05-11 | 2026-05-17 | 2026-05 | 7 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 133/0 | Haji Enterprises | 2026-05-09 | 2026-05-18 | 2026-05 | 10 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 153/0 | Krishna Constrction | 2026-04-04 | 2026-05-20 | 2026-05 | 47 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 167/4 | BLG Infra | 2026-05-17 | 2026-05-20 | 2026-05 | 4 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 133/1 | Haji Enterprises | 2026-05-19 | 2026-05-23 | 2026-05 | 5 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 167/1 | BLG Infra | 2026-05-20 | 2026-05-26 | 2026-05 | 7 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 194/0 | Chandrakant Patel | 2026-04-30 | 2026-05-27 | 2026-05 | 28 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 150/2 | Vihan | 2026-05-22 | 2026-05-31 | 2026-05 | 10 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 153/1 | BLG Infra | 2026-05-28 | 2026-05-31 | 2026-05 | 4 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 155/0 | Haji Enterprises2 | 2026-05-22 | 2026-05-31 | 2026-05 | 10 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 150/4 | Vihan | 2026-05-28 | 2026-06-06 | 2026-06 | 10 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 155/2 | Haji Enterprises-1 | 2026-05-20 | 2026-06-06 | 2026-06 | 18 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 154/0 | BLG Infra | 2026-05-28 | 2026-06-10 | 2026-06 | 14 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 150/3 | Vihan | 2026-06-03 | 2026-06-11 | 2026-06 | 9 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 154/1 | BLG Infra | 2026-06-08 | 2026-06-14 | 2026-06 | 7 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 160/3 | Haji Enterprises | 2026-06-08 | 2026-06-14 | 2026-06 | 7 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. Arun Felbin | TA 510FDN | TA510 | FDN | 150/1 | Vihan | 2026-06-08 | 2026-06-15 | 2026-06 | 8 | Valid | detail | detail_date | TA 510 - DPR - 2026-06-16.xlsx | FDN
Mr. NK Gupta | TA 512 | TA512 |  | 8/1 | Unassigned | 2025-02-12 | 2025-02-23 | 2025-02 | 12 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 8/3 | Unassigned | 2025-02-17 | 2025-02-26 | 2025-02 | 10 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 8/6 | Unassigned | 2025-02-20 | 2025-02-28 | 2025-02 | 9 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 8/2 | Unassigned | 2025-03-01 | 2025-03-05 | 2025-03 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 8/5 | Unassigned | 2025-02-27 | 2025-03-05 | 2025-03 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 12/1 | Unassigned | 2025-03-01 | 2025-03-07 | 2025-03 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 12/2 | Unassigned | 2025-03-05 | 2025-03-10 | 2025-03 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 12/3 | Unassigned | 2025-03-05 | 2025-03-10 | 2025-03 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 8/4 | Unassigned | 2025-03-05 | 2025-03-10 | 2025-03 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 8/8 | Unassigned | 2025-03-05 | 2025-03-10 | 2025-03 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 12/4 | Unassigned | 2025-03-09 | 2025-03-13 | 2025-03 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 6/7 | Unassigned | 2025-03-08 | 2025-03-15 | 2025-03 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 18/5 | Unassigned | 2025-03-11 | 2025-03-17 | 2025-03 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 7/6 | Unassigned | 2025-03-10 | 2025-03-17 | 2025-03 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 18/4 | Unassigned | 2025-03-14 | 2025-03-18 | 2025-03 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 6/8 | Unassigned | 2025-03-14 | 2025-03-20 | 2025-03 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 18/3 | Unassigned | 2025-03-16 | 2025-03-21 | 2025-03 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 7/5 | Unassigned | 2025-03-16 | 2025-03-21 | 2025-03 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 19/1 | Unassigned | 2025-03-18 | 2025-03-23 | 2025-03 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 19/2 | Unassigned | 2025-03-20 | 2025-03-24 | 2025-03 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 8/7 | Unassigned | 2025-03-17 | 2025-03-24 | 2025-03 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 19/3 | Unassigned | 2025-03-21 | 2025-03-25 | 2025-03 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 6/10 | Unassigned | 2025-03-21 | 2025-03-26 | 2025-03 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 7/7 | Unassigned | 2025-03-20 | 2025-03-26 | 2025-03 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 19/6 | Unassigned | 2025-03-23 | 2025-03-27 | 2025-03 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 19/4 | Unassigned | 2025-03-23 | 2025-03-28 | 2025-03 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 19/7 | Unassigned | 2025-03-26 | 2025-03-30 | 2025-03 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 9/2 | Unassigned | 2025-03-24 | 2025-03-30 | 2025-03 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 20/1 | Unassigned | 2025-03-27 | 2025-03-31 | 2025-03 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 7/8 | Unassigned | 2025-03-26 | 2025-04-01 | 2025-04 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 6/9 | Unassigned | 2025-03-25 | 2025-04-02 | 2025-04 | 9 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 9/3 | Unassigned | 2025-03-29 | 2025-04-03 | 2025-04 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 20/5 | Unassigned | 2025-03-31 | 2025-04-04 | 2025-04 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 7/9 | Unassigned | 2025-04-01 | 2025-04-06 | 2025-04 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 30/6 | Unassigned | 2025-04-03 | 2025-04-07 | 2025-04 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 20/2 | Unassigned | 2025-04-04 | 2025-04-10 | 2025-04 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 7/11 | Unassigned | 2025-04-05 | 2025-04-11 | 2025-04 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 30/5 | Unassigned | 2025-04-07 | 2025-04-13 | 2025-04 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 6/4 | Unassigned | 2025-04-06 | 2025-04-13 | 2025-04 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 20/3 | Unassigned | 2025-04-09 | 2025-04-15 | 2025-04 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 30/4 | Unassigned | 2025-04-11 | 2025-04-15 | 2025-04 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 7/10 | Unassigned | 2025-04-10 | 2025-04-16 | 2025-04 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 19/5 | Unassigned | 2025-04-14 | 2025-04-19 | 2025-04 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 30/7 | Unassigned | 2025-04-14 | 2025-04-19 | 2025-04 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 7/4 | Unassigned | 2025-04-16 | 2025-04-21 | 2025-04 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 30/8 | Unassigned | 2025-04-19 | 2025-04-23 | 2025-04 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 28/2 | Unassigned | 2025-04-18 | 2025-04-24 | 2025-04 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 20/6 | Unassigned | 2025-04-20 | 2025-04-25 | 2025-04 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 30/10 | Unassigned | 2025-04-22 | 2025-04-26 | 2025-04 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 28/1 | Unassigned | 2025-04-22 | 2025-04-28 | 2025-04 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 7/3 | Unassigned | 2025-04-21 | 2025-04-28 | 2025-04 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 23/3 | Unassigned | 2025-04-25 | 2025-04-30 | 2025-04 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 30/12 | Unassigned | 2025-04-26 | 2025-04-30 | 2025-04 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 23/2 | Unassigned | 2025-04-25 | 2025-05-04 | 2025-05 | 10 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 30/11 | Unassigned | 2025-04-29 | 2025-05-04 | 2025-05 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 7/2 | Unassigned | 2025-04-28 | 2025-05-04 | 2025-05 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 30/13 | Unassigned | 2025-05-02 | 2025-05-07 | 2025-05 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 30/14 | Unassigned | 2025-05-04 | 2025-05-09 | 2025-05 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 7/1 | Unassigned | 2025-05-05 | 2025-05-10 | 2025-05 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 30/18 | Unassigned | 2025-05-06 | 2025-05-11 | 2025-05 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 11/4 | Unassigned | 2025-05-05 | 2025-05-12 | 2025-05 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/1 | Unassigned | 2025-05-10 | 2025-05-14 | 2025-05 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/2 | Unassigned | 2025-05-11 | 2025-05-15 | 2025-05 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/3 | Unassigned | 2025-05-12 | 2025-05-17 | 2025-05 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 6/1 | Unassigned | 2025-05-09 | 2025-05-17 | 2025-05 | 9 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/4 | Unassigned | 2025-05-14 | 2025-05-18 | 2025-05 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 28/4 | Unassigned | 2025-03-27 | 2025-05-19 | 2025-05 | 54 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 5/8 | Unassigned | 2025-05-14 | 2025-05-19 | 2025-05 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/5 | Unassigned | 2025-05-16 | 2025-05-20 | 2025-05 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 11/2 | Unassigned | 2025-05-08 | 2025-05-21 | 2025-05 | 14 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/6 | Unassigned | 2025-05-20 | 2025-05-23 | 2025-05 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 5/10 | Unassigned | 2025-05-17 | 2025-05-23 | 2025-05 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 6/2 | Unassigned | 2025-05-16 | 2025-05-25 | 2025-05 | 10 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 11/3 | Unassigned | 2025-05-18 | 2025-05-26 | 2025-05 | 9 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/7 | Unassigned | 2025-05-22 | 2025-05-26 | 2025-05 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 28/7 | Unassigned | 2025-05-19 | 2025-05-27 | 2025-05 | 9 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 28/6 | Unassigned | 2025-05-27 | 2025-06-01 | 2025-06 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 6/3 | Unassigned | 2025-05-25 | 2025-06-01 | 2025-06 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 11/5 | Unassigned | 2025-05-22 | 2025-06-04 | 2025-06 | 14 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/8 | Unassigned | 2025-05-31 | 2025-06-04 | 2025-06 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 28/3 | Unassigned | 2025-06-01 | 2025-06-06 | 2025-06 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/12 | Unassigned | 2025-06-03 | 2025-06-07 | 2025-06 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 5/9 | Unassigned | 2025-05-21 | 2025-06-08 | 2025-06 | 19 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/11 | Unassigned | 2025-06-01 | 2025-06-10 | 2025-06 | 10 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 28/5 | Unassigned | 2025-06-05 | 2025-06-11 | 2025-06 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/13 | Unassigned | 2025-06-05 | 2025-06-11 | 2025-06 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 5/11 | Unassigned | 2025-06-08 | 2025-06-11 | 2025-06 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 6/6 | Unassigned | 2025-06-01 | 2025-06-11 | 2025-06 | 11 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 5/5 | Unassigned | 2025-06-11 | 2025-06-16 | 2025-06 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 6/5 | Unassigned | 2025-06-11 | 2025-06-16 | 2025-06 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 27/2 | Unassigned | 2025-06-11 | 2025-06-17 | 2025-06 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/9 | Unassigned | 2025-06-10 | 2025-06-17 | 2025-06 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 30/9 | Unassigned | 2025-06-11 | 2025-06-18 | 2025-06 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 5/4 | Unassigned | 2025-06-15 | 2025-06-18 | 2025-06 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 27/3 | Unassigned | 2025-06-16 | 2025-06-20 | 2025-06 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 6/0 | Unassigned | 2025-06-15 | 2025-06-22 | 2025-06 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 5/3 | Unassigned | 2025-06-16 | 2025-06-23 | 2025-06 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 19/0 | Unassigned | 2025-06-15 | 2025-06-26 | 2025-06 | 12 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 29/1 | Unassigned | 2025-06-18 | 2025-06-26 | 2025-06 | 9 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 4/14 | Unassigned | 2025-06-23 | 2025-06-26 | 2025-06 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 5/2 | Unassigned | 2025-06-23 | 2025-06-26 | 2025-06 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 20/0 | Unassigned | 2025-06-22 | 2025-06-30 | 2025-06 | 9 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 34/4 | Unassigned | 2025-06-22 | 2025-06-30 | 2025-06 | 9 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 41/6 | Unassigned | 2025-06-27 | 2025-07-01 | 2025-07 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 29/2 | Unassigned | 2025-06-21 | 2025-07-03 | 2025-07 | 13 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 5/1 | Unassigned | 2025-06-26 | 2025-07-03 | 2025-07 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 12/5 | Unassigned | 2025-06-30 | 2025-07-04 | 2025-07 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 29/7 | Unassigned | 2025-06-27 | 2025-07-04 | 2025-07 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 4/13 | Unassigned | 2025-06-29 | 2025-07-05 | 2025-07 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 41/5 | Unassigned | 2025-07-02 | 2025-07-05 | 2025-07 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 11/6 | Unassigned | 2025-06-30 | 2025-07-07 | 2025-07 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 29/3 | Unassigned | 2025-06-26 | 2025-07-09 | 2025-07 | 14 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 4/11 | Unassigned | 2025-07-06 | 2025-07-09 | 2025-07 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 41/4 | Unassigned | 2025-07-06 | 2025-07-09 | 2025-07 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 16/2 | Unassigned | 2025-07-06 | 2025-07-10 | 2025-07 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 29/6 | Unassigned | 2025-06-29 | 2025-07-10 | 2025-07 | 12 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 29/4 | Unassigned | 2025-06-30 | 2025-07-12 | 2025-07 | 13 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 4/12 | Unassigned | 2025-07-08 | 2025-07-13 | 2025-07 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 41/3 | Unassigned | 2025-07-09 | 2025-07-14 | 2025-07 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 1A/1 | Unassigned | 2025-07-06 | 2025-07-15 | 2025-07 | 10 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 29/8 | Unassigned | 2025-07-07 | 2025-07-15 | 2025-07 | 9 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 37/10 | Unassigned | 2025-07-06 | 2025-07-16 | 2025-07 | 11 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/26 | Unassigned | 2025-07-04 | 2025-07-17 | 2025-07 | 14 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 4/3 | Unassigned | 2025-07-13 | 2025-07-17 | 2025-07 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 37/9 | Unassigned | 2025-07-11 | 2025-07-18 | 2025-07 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 41/1 | Unassigned | 2025-07-15 | 2025-07-18 | 2025-07 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 29/5 | Unassigned | 2025-07-11 | 2025-07-19 | 2025-07 | 9 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 1A/3 | Unassigned | 2025-07-15 | 2025-07-20 | 2025-07 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 29/9 | Unassigned | 2025-07-15 | 2025-07-20 | 2025-07 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 41/2 | Unassigned | 2025-07-14 | 2025-07-20 | 2025-07 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/14 | Unassigned | 2025-07-04 | 2025-07-21 | 2025-07 | 18 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 1A/2 | Unassigned | 2025-07-15 | 2025-07-22 | 2025-07 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/15 | Unassigned | 2025-06-29 | 2025-07-23 | 2025-07 | 25 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 29/10 | Unassigned | 2025-07-18 | 2025-07-25 | 2025-07 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 29/11 | Unassigned | 2025-07-19 | 2025-07-25 | 2025-07 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 40/2 | Unassigned | 2025-07-21 | 2025-07-25 | 2025-07 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 37/8 | Unassigned | 2025-07-17 | 2025-07-26 | 2025-07 | 10 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 2/2 | Unassigned | 2025-07-23 | 2025-07-29 | 2025-07 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/24 | Unassigned | 2025-07-18 | 2025-07-29 | 2025-07 | 12 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 40/3 | Unassigned | 2025-07-25 | 2025-07-29 | 2025-07 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 4/0 | Unassigned | 2025-07-20 | 2025-07-30 | 2025-07 | 11 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/20 | Unassigned | 2025-07-18 | 2025-07-31 | 2025-07 | 14 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 29/0 | Unassigned | 2025-07-25 | 2025-08-01 | 2025-08 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 29/12 | Unassigned | 2025-07-25 | 2025-08-01 | 2025-08 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/19 | Unassigned | 2025-07-25 | 2025-08-01 | 2025-08 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 37/7 | Unassigned | 2025-07-25 | 2025-08-02 | 2025-08 | 9 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 2/4 | Unassigned | 2025-07-31 | 2025-08-03 | 2025-08 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 3A/3 | Unassigned | 2025-07-27 | 2025-08-03 | 2025-08 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 40/4 | Unassigned | 2025-07-27 | 2025-08-03 | 2025-08 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 29/20 | Unassigned | 2025-07-31 | 2025-08-05 | 2025-08 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/16 | Unassigned | 2025-07-31 | 2025-08-05 | 2025-08 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 34/6 | Unassigned | 2025-07-21 | 2025-08-06 | 2025-08 | 17 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 29/15 | Unassigned | 2025-07-31 | 2025-08-07 | 2025-08 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/21 | Unassigned | 2025-07-27 | 2025-08-07 | 2025-08 | 12 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/23 | Unassigned | 2025-07-27 | 2025-08-07 | 2025-08 | 12 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 3A/2 | Unassigned | 2025-08-03 | 2025-08-07 | 2025-08 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 2/5 | Unassigned | 2025-08-03 | 2025-08-08 | 2025-08 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 2/1 | Unassigned | 2025-07-22 | 2025-08-13 | 2025-08 | 23 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 30/2 | Unassigned | 2025-08-05 | 2025-08-13 | 2025-08 | 9 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 34/5 | Unassigned | 2025-08-08 | 2025-08-14 | 2025-08 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 3A/1 | Unassigned | 2025-08-07 | 2025-08-14 | 2025-08 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 9/1 | Unassigned | 2025-08-17 | 2025-08-21 | 2025-08 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 30/16 | Unassigned | 2025-08-14 | 2025-08-22 | 2025-08 | 9 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/22 | Unassigned | 2025-08-08 | 2025-08-22 | 2025-08 | 15 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 34/3 | Unassigned | 2025-08-11 | 2025-08-23 | 2025-08 | 13 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 41/0 | Unassigned | 2025-08-03 | 2025-08-28 | 2025-08 | 26 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 9/0 | Unassigned | 2025-08-22 | 2025-08-28 | 2025-08 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 34/7 | Unassigned | 2025-08-16 | 2025-08-29 | 2025-08 | 14 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 29/18 | Unassigned | 2025-08-27 | 2025-09-03 | 2025-09 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 36/9 | Unassigned | 2025-08-29 | 2025-09-03 | 2025-09 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 4/5 | Unassigned | 2025-08-22 | 2025-09-03 | 2025-09 | 13 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 36/8 | Unassigned | 2025-09-04 | 2025-09-06 | 2025-09 | 3 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 37/6 | Unassigned | 2025-08-27 | 2025-09-06 | 2025-09 | 11 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 8/0 | Unassigned | 2025-08-29 | 2025-09-06 | 2025-09 | 9 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 34/2 | Unassigned | 2025-08-25 | 2025-09-09 | 2025-09 | 16 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 29/14 | Unassigned | 2025-09-04 | 2025-09-11 | 2025-09 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 36/7 | Unassigned | 2025-09-07 | 2025-09-11 | 2025-09 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 36/6 | Unassigned | 2025-09-12 | 2025-09-16 | 2025-09 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 37/5 | Unassigned | 2025-09-07 | 2025-09-16 | 2025-09 | 10 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 4/6 | Unassigned | 2025-09-11 | 2025-09-16 | 2025-09 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 7/0 | Unassigned | 2025-09-07 | 2025-09-16 | 2025-09 | 10 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 36/5 | Unassigned | 2025-09-18 | 2025-09-21 | 2025-09 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 4/8 | Unassigned | 2025-09-18 | 2025-09-22 | 2025-09 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 13/0 | Unassigned | 2025-09-19 | 2025-09-23 | 2025-09 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 4/9 | Unassigned | 2025-09-23 | 2025-09-25 | 2025-09 | 3 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 36/4 | Unassigned | 2025-09-23 | 2025-09-26 | 2025-09 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 36/3 | Unassigned | 2025-09-26 | 2025-09-29 | 2025-09 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 29/19 | Unassigned | 2025-09-24 | 2025-10-01 | 2025-10 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 4/10 | Unassigned | 2025-09-27 | 2025-10-01 | 2025-10 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 34/9 | Unassigned | 2025-09-28 | 2025-10-04 | 2025-10 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 37/0 | Unassigned | 2025-09-29 | 2025-10-04 | 2025-10 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 4/7 | Unassigned | 2025-10-04 | 2025-10-09 | 2025-10 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 20/4 | Unassigned | 2025-10-09 | 2025-10-12 | 2025-10 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 34/10 | Unassigned | 2025-10-04 | 2025-10-12 | 2025-10 | 9 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 36/2 | Unassigned | 2025-10-04 | 2025-10-12 | 2025-10 | 9 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 37/2 | Unassigned | 2025-10-13 | 2025-10-16 | 2025-10 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 18/2 | Unassigned | 2025-10-14 | 2025-10-17 | 2025-10 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 30/0 | Unassigned | 2025-10-04 | 2025-10-17 | 2025-10 | 14 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 37/3 | Unassigned | 2025-10-16 | 2025-10-18 | 2025-10 | 3 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/17 | Unassigned | 2025-10-12 | 2025-10-19 | 2025-10 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 3/1 | Unassigned | 2025-10-10 | 2025-10-23 | 2025-10 | 14 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 29/13 | Unassigned | 2025-09-18 | 2025-10-25 | 2025-10 | 38 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 35/0 | Unassigned | 2025-10-13 | 2025-10-25 | 2025-10 | 13 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/18 | Unassigned | 2025-10-18 | 2025-10-26 | 2025-10 | 9 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 37/4 | Unassigned | 2025-10-23 | 2025-10-26 | 2025-10 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 12/0 | Unassigned | 2025-10-17 | 2025-10-27 | 2025-10 | 11 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 3/2 | Unassigned | 2025-10-23 | 2025-10-28 | 2025-10 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 3/3 | Unassigned | 2025-10-27 | 2025-10-30 | 2025-10 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/0 | Unassigned | 2025-10-22 | 2025-10-30 | 2025-10 | 9 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 40/1 | Unassigned | 2025-10-28 | 2025-10-30 | 2025-10 | 3 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 9/4 | Unassigned | 2025-10-27 | 2025-10-30 | 2025-10 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 29/21 | Unassigned | 2025-10-24 | 2025-11-01 | 2025-11 | 9 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 35/1 | Unassigned | 2025-10-26 | 2025-11-01 | 2025-11 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 3/4 | Unassigned | 2025-10-31 | 2025-11-02 | 2025-11 | 3 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 37/1 | Unassigned | 2025-10-27 | 2025-11-03 | 2025-11 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 30/17 | Unassigned | 2025-10-27 | 2025-11-04 | 2025-11 | 9 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 11/1 | Unassigned | 2025-11-01 | 2025-11-05 | 2025-11 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 3/5 | Unassigned | 2025-11-02 | 2025-11-06 | 2025-11 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 35/2 | Unassigned | 2025-11-01 | 2025-11-07 | 2025-11 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 29/17 | Unassigned | 2025-10-30 | 2025-11-09 | 2025-11 | 11 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 3/6 | Unassigned | 2025-11-06 | 2025-11-09 | 2025-11 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 40/0 | Unassigned | 2025-11-04 | 2025-11-10 | 2025-11 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 16/1 | Unassigned | 2025-11-06 | 2025-11-11 | 2025-11 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 3/7 | Unassigned | 2025-11-09 | 2025-11-12 | 2025-11 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/25 | Unassigned | 2025-11-05 | 2025-11-12 | 2025-11 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 35/3 | Unassigned | 2025-11-08 | 2025-11-13 | 2025-11 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 39/0 | Unassigned | 2025-11-09 | 2025-11-14 | 2025-11 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 11/8 | Unassigned | 2025-11-14 | 2025-11-16 | 2025-11 | 3 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 38/2 | Unassigned | 2025-11-14 | 2025-11-16 | 2025-11 | 3 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/27 | Unassigned | 2025-11-10 | 2025-11-17 | 2025-11 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 30/1 | Unassigned | 2025-11-10 | 2025-11-18 | 2025-11 | 9 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 3A/0 | Unassigned | 2025-11-13 | 2025-11-19 | 2025-11 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 20/7 | Unassigned | 2025-11-18 | 2025-11-21 | 2025-11 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 38/0 | Unassigned | 2025-11-16 | 2025-11-22 | 2025-11 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 29/16 | Unassigned | 2025-11-09 | 2025-11-24 | 2025-11 | 16 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 38/1 | Unassigned | 2025-11-23 | 2025-11-24 | 2025-11 | 2 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 32/0 | Unassigned | 2025-11-14 | 2025-11-25 | 2025-11 | 12 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 32/4 | Unassigned | 2025-11-24 | 2025-11-28 | 2025-11 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 3/0 | Unassigned | 2025-11-20 | 2025-11-29 | 2025-11 | 10 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 34/8 | Unassigned | 2025-11-25 | 2025-11-29 | 2025-11 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 21/0 | Unassigned | 2025-11-24 | 2025-12-01 | 2025-12 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 32/1 | Unassigned | 2025-11-27 | 2025-12-01 | 2025-12 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 2A/5 | Unassigned | 2025-11-29 | 2025-12-02 | 2025-12 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 32/3 | Unassigned | 2025-11-20 | 2025-12-02 | 2025-12 | 13 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 5/0 | Unassigned | 2025-11-26 | 2025-12-02 | 2025-12 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 35/5 | Unassigned | 2025-11-30 | 2025-12-03 | 2025-12 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 32/5 | Unassigned | 2025-11-30 | 2025-12-04 | 2025-12 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 2A/4 | Unassigned | 2025-12-01 | 2025-12-05 | 2025-12 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 32/6 | Unassigned | 2025-12-02 | 2025-12-06 | 2025-12 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 35/4 | Unassigned | 2025-12-03 | 2025-12-07 | 2025-12 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 4/4 | Unassigned | 2025-12-04 | 2025-12-07 | 2025-12 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 30/3 | Unassigned | 2025-11-24 | 2025-12-08 | 2025-12 | 15 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 2A/3 | Unassigned | 2025-12-05 | 2025-12-09 | 2025-12 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 35/6 | Unassigned | 2025-12-07 | 2025-12-10 | 2025-12 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 2A/2 | Unassigned | 2025-12-06 | 2025-12-12 | 2025-12 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 4/2 | Unassigned | 2025-12-06 | 2025-12-12 | 2025-12 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 20A/0 | Unassigned | 2025-12-01 | 2025-12-13 | 2025-12 | 13 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 35/8 | Unassigned | 2025-12-11 | 2025-12-14 | 2025-12 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 4/1 | Unassigned | 2025-12-11 | 2025-12-14 | 2025-12 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 2A/1 | Unassigned | 2025-12-14 | 2025-12-16 | 2025-12 | 3 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 32/7 | Unassigned | 2025-12-09 | 2025-12-16 | 2025-12 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 23/1 | Unassigned | 2025-12-13 | 2025-12-17 | 2025-12 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 28/0 | Unassigned | 2025-12-02 | 2025-12-17 | 2025-12 | 16 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 33/2 | Unassigned | 2025-12-11 | 2025-12-17 | 2025-12 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 35/7 | Unassigned | 2025-12-14 | 2025-12-17 | 2025-12 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 5/6 | Unassigned | 2025-12-15 | 2025-12-19 | 2025-12 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 35/9 | Unassigned | 2025-12-18 | 2025-12-21 | 2025-12 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 33/4 | Unassigned | 2025-12-20 | 2025-12-23 | 2025-12 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 2A/0 | Unassigned | 2025-12-17 | 2025-12-25 | 2025-12 | 9 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 36/0 | Unassigned | 2025-12-21 | 2025-12-26 | 2025-12 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 5/7 | Unassigned | 2025-12-19 | 2025-12-26 | 2025-12 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 22/0 | Unassigned | 2025-12-18 | 2025-12-27 | 2025-12 | 10 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 27/1 | Unassigned | 2025-12-18 | 2025-12-27 | 2025-12 | 10 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 2/6 | Unassigned | 2025-12-25 | 2025-12-30 | 2025-12 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 36/1 | Unassigned | 2025-12-26 | 2025-12-30 | 2025-12 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 29/22 | Unassigned | 2025-12-25 | 2025-12-31 | 2025-12 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 2/3 | Unassigned | 2025-12-30 | 2026-01-03 | 2026-01 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 23/0 | Unassigned | 2025-12-21 | 2026-01-04 | 2026-01 | 15 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 33A/0 | Unassigned | 2025-12-30 | 2026-01-05 | 2026-01 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 18/1 | Unassigned | 2026-01-05 | 2026-01-11 | 2026-01 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 42/0 | Unassigned | 2026-01-04 | 2026-01-11 | 2026-01 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 13/1 | Unassigned | 2026-01-05 | 2026-01-12 | 2026-01 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 34/0 | Unassigned | 2026-01-04 | 2026-01-13 | 2026-01 | 10 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 43/0 | Unassigned | 2026-01-11 | 2026-01-16 | 2026-01 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 2/0 | Unassigned | 2025-12-30 | 2026-01-20 | 2026-01 | 22 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 33/3 | Unassigned | 2026-01-15 | 2026-01-21 | 2026-01 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 33/1 | Unassigned | 2026-01-28 | 2026-01-31 | 2026-01 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 10/0 | Unassigned | 2026-01-17 | 2026-02-02 | 2026-02 | 17 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 16/3 | Unassigned | 2026-02-03 | 2026-02-07 | 2026-02 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 32/8 | Unassigned | 2026-02-15 | 2026-02-19 | 2026-02 | 5 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 32/9 | Unassigned | 2026-02-15 | 2026-02-22 | 2026-02 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 33/0 | Unassigned | 2026-02-24 | 2026-03-03 | 2026-03 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 44/0 | Unassigned | 2026-02-27 | 2026-03-09 | 2026-03 | 11 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 32/2 | Unassigned | 2026-03-12 | 2026-03-15 | 2026-03 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 17/0 | Unassigned | 2026-03-22 | 2026-04-03 | 2026-04 | 13 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 47/0 | Unassigned | 2026-03-27 | 2026-04-08 | 2026-04 | 13 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 18/0 | Unassigned | 2026-04-03 | 2026-04-12 | 2026-04 | 10 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 44/1 | Unassigned | 2026-04-09 | 2026-04-15 | 2026-04 | 7 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 45/0 | Unassigned | 2026-04-14 | 2026-04-24 | 2026-04 | 11 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 46/0 | Unassigned | 2026-02-12 | 2026-04-24 | 2026-04 | 72 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 34/1 | Unassigned | 2026-04-14 | 2026-04-29 | 2026-04 | 16 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 11/7 | Unassigned | 2026-05-02 | 2026-05-09 | 2026-05 | 8 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 31/10 | Unassigned | 2026-05-18 | 2026-05-21 | 2026-05 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 27/0 | Unassigned | 2026-05-02 | 2026-05-25 | 2026-05 | 24 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 11/0 | Unassigned | 2026-05-14 | 2026-05-29 | 2026-05 | 16 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 25/1 | Unassigned | 2026-05-28 | 2026-05-31 | 2026-05 | 4 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 1A/0 | Unassigned | 2026-05-20 | 2026-06-03 | 2026-06 | 15 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 16/0 | Unassigned | 2026-04-13 | 2026-06-04 | 2026-06 | 53 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 26/0 | Unassigned | 2026-05-21 | 2026-06-10 | 2026-06 | 21 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 512 | TA512 |  | 23/4 | Unassigned | 2026-06-07 | 2026-06-12 | 2026-06 | 6 | Valid | detail | detail_date | TA 512 - DPR - 2026-06-16.xlsx | Foundation
Mr. NK Gupta | TA 513SF | TA513 | S-F | 25/1 | Unassigned | 2025-03-22 | 2025-03-28 | 2025-03 | 7 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-F
Mr. NK Gupta | TA 513SF | TA513 | S-F | 25/2 | Unassigned | 2025-03-25 | 2025-04-01 | 2025-04 | 8 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-F
Mr. NK Gupta | TA 513SF | TA513 | S-F | 24/2 | Unassigned | 2025-03-30 | 2025-04-04 | 2025-04 | 6 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-F
Mr. NK Gupta | TA 513SF | TA513 | S-F | 24/1 | Unassigned | 2025-04-02 | 2025-04-07 | 2025-04 | 6 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-F
Mr. NK Gupta | TA 513SF | TA513 | S-F | 26/2 | Unassigned | 2025-04-04 | 2025-04-12 | 2025-04 | 9 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-F
Mr. NK Gupta | TA 513SF | TA513 | S-F | 30/2 | Unassigned | 2025-04-09 | 2025-04-12 | 2025-04 | 4 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-F
Mr. NK Gupta | TA 513SF | TA513 | S-F | 23/6 | Unassigned | 2025-04-12 | 2025-04-14 | 2025-04 | 3 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-F
Mr. NK Gupta | TA 513SF | TA513 | S-F | 23/5 | Unassigned | 2025-04-14 | 2025-04-16 | 2025-04 | 3 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-F
Mr. NK Gupta | TA 513SF | TA513 | S-F | 31/1 | Unassigned | 2025-04-14 | 2025-04-17 | 2025-04 | 4 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-F
Mr. NK Gupta | TA 513SP | TA513 | S-P | 30/3 | Unassigned | 2025-04-21 | 2025-04-22 | 2025-04 | 2 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SF | TA513 | S-F | 37/1 | Unassigned | 2025-04-17 | 2025-04-24 | 2025-04 | 8 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-F
Mr. NK Gupta | TA 513SP | TA513 | S-P | 30/1 | Unassigned | 2025-04-22 | 2025-04-25 | 2025-04 | 4 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 30/2 | Unassigned | 2025-04-24 | 2025-04-28 | 2025-04 | 5 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SF | TA513 | S-F | 24/3 | Unassigned | 2025-04-26 | 2025-04-29 | 2025-04 | 4 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-F
Mr. NK Gupta | TA 513SF | TA513 | S-F | 31/2 | Unassigned | 2025-04-23 | 2025-04-30 | 2025-04 | 8 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-F
Mr. NK Gupta | TA 513SP | TA513 | S-P | 29/5 | Unassigned | 2025-04-29 | 2025-05-01 | 2025-05 | 3 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 29/2 | Unassigned | 2025-05-01 | 2025-05-03 | 2025-05 | 3 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 29/4 | Unassigned | 2025-05-02 | 2025-05-04 | 2025-05 | 3 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 29/3 | Unassigned | 2025-05-03 | 2025-05-05 | 2025-05 | 3 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 29/1 | Unassigned | 2025-05-03 | 2025-05-06 | 2025-05 | 4 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 28/3 | Unassigned | 2025-05-07 | 2025-05-09 | 2025-05 | 3 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 28/4 | Unassigned | 2025-05-07 | 2025-05-09 | 2025-05 | 3 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 28/2 | Unassigned | 2025-05-09 | 2025-05-11 | 2025-05 | 3 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SF | TA513 | S-F | 24/4 | Unassigned | 2025-05-16 | 2025-05-17 | 2025-05 | 2 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-F
Mr. NK Gupta | TA 513SP | TA513 | S-P | 3/5 | Unassigned | 2025-05-16 | 2025-05-20 | 2025-05 | 5 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 55/7 | Unassigned | 2025-05-11 | 2025-05-20 | 2025-05 | 10 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SF | TA513 | S-F | 23/3 | Unassigned | 2025-05-21 | 2025-05-24 | 2025-05 | 4 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-F
Mr. NK Gupta | TA 513SP | TA513 | S-P | 3/6 | Unassigned | 2025-05-20 | 2025-05-24 | 2025-05 | 5 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 3/10 | Unassigned | 2025-05-24 | 2025-05-27 | 2025-05 | 4 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SF | TA513 | S-F | 32B/1 | Unassigned | 2025-05-25 | 2025-05-28 | 2025-05 | 4 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-F
Mr. NK Gupta | TA 513SP | TA513 | S-P | 21/7 | Unassigned | 2025-05-30 | 2025-06-02 | 2025-06 | 4 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 21/6 | Unassigned | 2025-05-30 | 2025-06-05 | 2025-06 | 7 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 23/1 | Unassigned | 2025-06-03 | 2025-06-07 | 2025-06 | 5 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 23/3 | Unassigned | 2025-06-05 | 2025-06-09 | 2025-06 | 5 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 23/2 | Unassigned | 2025-06-07 | 2025-06-11 | 2025-06 | 5 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 23/4 | Unassigned | 2025-06-11 | 2025-06-15 | 2025-06 | 5 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SF | TA513 | S-F | 18/4 | Unassigned | 2025-06-20 | 2025-06-28 | 2025-06 | 9 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-F
Mr. NK Gupta | TA 513SP | TA513 | S-P | 56/1 | Unassigned | 2025-06-21 | 2025-06-28 | 2025-06 | 8 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 14/4 | Unassigned | 2025-06-20 | 2025-07-01 | 2025-07 | 12 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 26/1 | Unassigned | 2025-06-28 | 2025-07-03 | 2025-07 | 6 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 56/2 | Unassigned | 2025-07-02 | 2025-07-05 | 2025-07 | 4 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 14/3 | Unassigned | 2025-07-02 | 2025-07-07 | 2025-07 | 6 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 56/4 | Unassigned | 2025-07-05 | 2025-07-10 | 2025-07 | 6 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 14/2 | Unassigned | 2025-07-07 | 2025-07-13 | 2025-07 | 7 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 56/0 | Unassigned |  | 2025-07-15 | 2025-07 |  | Missing Start Date | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 55/5 | Unassigned | 2025-07-16 | 2025-07-20 | 2025-07 | 5 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 15B/4 | Unassigned | 2025-07-15 | 2025-07-21 | 2025-07 | 7 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 55/0 | Unassigned | 2025-07-20 | 2025-07-24 | 2025-07 | 5 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 55/6 | Unassigned | 2025-07-24 | 2025-07-28 | 2025-07 | 5 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 54/6 | Unassigned | 2025-07-21 | 2025-08-09 | 2025-08 | 20 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 36/3 | Unassigned | 2025-07-26 | 2025-08-20 | 2025-08 | 26 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 56/3 | Unassigned | 2025-08-19 | 2025-08-24 | 2025-08 | 6 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 36/4 | Unassigned | 2025-08-21 | 2025-09-01 | 2025-09 | 12 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SF | TA513 | S-F | 27/0 | Unassigned | 2025-09-10 | 2025-09-14 | 2025-09 | 5 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-F
Mr. NK Gupta | TA 513SF | TA513 | S-F | 26/0 | Unassigned | 2025-09-13 | 2025-09-18 | 2025-09 | 6 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-F
Mr. NK Gupta | TA 513SP | TA513 | S-P | 30/0 | Unassigned | 2025-09-10 | 2025-09-19 | 2025-09 | 10 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SF | TA513 | S-F | 25/0 | Unassigned | 2025-09-15 | 2025-09-20 | 2025-09 | 6 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-F
Mr. NK Gupta | TA 513SF | TA513 | S-F | 24/0 | Unassigned | 2025-09-19 | 2025-09-24 | 2025-09 | 6 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-F
Mr. NK Gupta | TA 513SP | TA513 | S-P | 29/0 | Unassigned | 2025-08-19 | 2025-09-24 | 2025-09 | 37 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SF | TA513 | S-F | 19/0 | Unassigned | 2025-09-25 | 2025-10-01 | 2025-10 | 7 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-F
Mr. NK Gupta | TA 513SF | TA513 | S-F | 28/0 | Unassigned | 2025-09-30 | 2025-10-05 | 2025-10 | 6 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-F
Mr. NK Gupta | TA 513SF | TA513 | S-F | 18/0 | Unassigned | 2025-10-04 | 2025-10-06 | 2025-10 | 3 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-F
Mr. NK Gupta | TA 513SP | TA513 | S-P | 54/3 | Unassigned | 2025-10-24 | 2025-11-11 | 2025-11 | 19 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 54/7 | Unassigned | 2025-11-14 | 2025-11-23 | 2025-11 | 10 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 51/4 | Unassigned | 2025-11-30 | 2025-12-05 | 2025-12 | 6 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 51/2 | Unassigned | 2025-12-06 | 2025-12-09 | 2025-12 | 4 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 54/5 | Unassigned | 2025-08-21 | 2025-12-15 | 2025-12 | 117 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 52/4 | Unassigned | 2025-12-14 | 2025-12-18 | 2025-12 | 5 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 51/5 | Unassigned | 2025-12-19 | 2025-12-23 | 2025-12 | 5 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 54/8 | Unassigned | 2026-01-24 | 2026-02-15 | 2026-02 | 23 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 52/3 | Unassigned | 2026-02-17 | 2026-02-25 | 2026-02 | 9 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 55/1 | Unassigned | 2026-02-27 | 2026-03-07 | 2026-03 | 9 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 55/2 | Unassigned | 2026-03-28 | 2026-04-11 | 2026-04 | 15 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 52/2 | Unassigned | 2026-04-22 | 2026-05-03 | 2026-05 | 12 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 55/4 | Unassigned | 2026-04-27 | 2026-05-04 | 2026-05 | 8 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 52/0 | Unassigned | 2026-04-24 | 2026-05-05 | 2026-05 | 12 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 52/1 | Unassigned | 2026-05-04 | 2026-05-10 | 2026-05 | 7 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 52/5 | Unassigned | 2025-05-05 | 2026-05-11 | 2026-05 | 372 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 55/3 | Unassigned | 2025-05-06 | 2026-05-15 | 2026-05 | 375 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 64/2 | Unassigned | 2025-05-11 | 2026-05-16 | 2026-05 | 371 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SF | TA513 | S-F | 30/0 | Unassigned | 2026-05-04 | 2026-05-17 | 2026-05 | 14 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-F
Mr. NK Gupta | TA 513SP | TA513 | S-P | 64/5 | Unassigned | 2025-05-11 | 2026-05-19 | 2026-05 | 374 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 64/3 | Unassigned | 2026-05-19 | 2026-05-21 | 2026-05 | 3 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SF | TA513 | S-F | 28/1 | Unassigned | 2026-05-17 | 2026-05-22 | 2026-05 | 6 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-F
Mr. NK Gupta | TA 513SP | TA513 | S-P | 51/3 | Unassigned | 2026-05-20 | 2026-05-23 | 2026-05 | 4 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 64/4 | Unassigned | 2026-05-21 | 2026-05-25 | 2026-05 | 5 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 64/6 | Unassigned | 2026-05-24 | 2026-05-29 | 2026-05 | 6 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 61/2 | Unassigned | 2026-05-23 | 2026-05-30 | 2026-05 | 8 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 74/9 | Unassigned | 2026-05-19 | 2026-05-30 | 2026-05 | 12 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 64/1 | Unassigned | 2026-05-26 | 2026-06-01 | 2026-06 | 7 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 54/1 | Unassigned | 2026-05-23 | 2026-06-07 | 2026-06 | 16 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 74/8 | Unassigned | 2026-06-01 | 2026-06-07 | 2026-06 | 7 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SF | TA513 | S-F | 55/1 | Unassigned | 2026-05-28 | 2026-06-09 | 2026-06 | 13 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-F
Mr. NK Gupta | TA 513SP | TA513 | S-P | 62/1 | Unassigned | 2026-06-02 | 2026-06-09 | 2026-06 | 8 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 61/0 | Unassigned | 2026-06-06 | 2026-06-14 | 2026-06 | 9 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. NK Gupta | TA 513SP | TA513 | S-P | 74/7 | Unassigned | 2026-06-07 | 2026-06-14 | 2026-06 | 8 | Valid | detail | detail_date | TA 513 - DPR - 2026-06-15.xlsx | FDN S-P
Mr. Arun Felbin | TA 601 | TA601 |  | 81/2 | Unassigned |  | 2025-08-07 | 2025-08 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 82/1 | Unassigned |  | 2025-08-22 | 2025-08 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 81/1 | Unassigned |  | 2025-09-13 | 2025-09 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 80/5 | Unassigned |  | 2025-09-18 | 2025-09 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 80/1 | Unassigned |  | 2025-10-10 | 2025-10 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 59/5 | Unassigned |  | 2025-10-19 | 2025-10 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 84/3 | Unassigned |  | 2025-10-19 | 2025-10 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 59/4 | Unassigned |  | 2025-10-21 | 2025-10 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 84/4 | Unassigned |  | 2025-10-24 | 2025-10 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 60/2 | Unassigned |  | 2025-10-25 | 2025-10 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 80/4 | Unassigned |  | 2025-10-27 | 2025-10 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 77/4 | Unassigned |  | 2025-10-31 | 2025-10 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 77/10 | Unassigned |  | 2025-11-05 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 59/2 | Unassigned |  | 2025-11-08 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 77/7 | Unassigned |  | 2025-11-09 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 77/8 | Unassigned |  | 2025-11-13 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 60/3 | Unassigned |  | 2025-11-15 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 77/3 | Unassigned |  | 2025-11-19 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 60/8 | Unassigned |  | 2025-11-23 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 77/1 | Unassigned |  | 2025-11-25 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 59/1 | Unassigned |  | 2025-11-29 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 77/2 | Unassigned |  | 2025-11-30 | 2025-11 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 58/2 | Unassigned |  | 2025-12-03 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 58/1 | Unassigned |  | 2025-12-08 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 77/6 | Unassigned |  | 2025-12-12 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 58/3 | Unassigned |  | 2025-12-14 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 99/7 | Unassigned |  | 2025-12-15 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 73/1 | Unassigned |  | 2025-12-18 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 56/3 | Unassigned |  | 2025-12-19 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 59/1 | Unassigned |  | 2025-12-20 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 99/6 | Unassigned |  | 2025-12-20 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 99/9 | Unassigned |  | 2025-12-23 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 56/1 | Unassigned |  | 2025-12-24 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 73/2 | Unassigned |  | 2025-12-24 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 79/1 | Unassigned |  | 2025-12-25 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 99/8 | Unassigned |  | 2025-12-26 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 56/2 | Unassigned |  | 2025-12-27 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 59/2 | Unassigned |  | 2025-12-27 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 99/10 | Unassigned |  | 2025-12-29 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 79/3 | Unassigned |  | 2025-12-30 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 55/3 | Unassigned |  | 2025-12-31 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 77/3 | Unassigned |  | 2025-12-31 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 84/6 | Unassigned |  | 2025-12-31 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 94/1 | Unassigned |  | 2025-12-31 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 99/11 | Unassigned |  | 2025-12-31 | 2025-12 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 79/2 | Unassigned |  | 2026-01-05 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 56/4 | Unassigned |  | 2026-01-06 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 99/12 | Unassigned |  | 2026-01-06 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 77/2 | Unassigned |  | 2026-01-08 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 84/5 | Unassigned |  | 2026-01-08 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 56/9 | Unassigned |  | 2026-01-10 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 58/1 | Unassigned |  | 2026-01-10 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 58/2 | Unassigned |  | 2026-01-10 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 100/2 | Unassigned |  | 2026-01-12 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 84/1 | Unassigned |  | 2026-01-12 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 77/1 | Unassigned |  | 2026-01-13 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 100/3 | Unassigned |  | 2026-01-14 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 58/3 | Unassigned |  | 2026-01-14 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 83/0 | Unassigned |  | 2026-01-14 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 56/7 | Unassigned |  | 2026-01-16 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 77/4 | Unassigned |  | 2026-01-16 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 82/1 | Unassigned |  | 2026-01-16 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 56/6 | Unassigned |  | 2026-01-17 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 80/5 | Unassigned |  | 2026-01-20 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 56/8 | Unassigned |  | 2026-01-21 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 59/4 | Unassigned |  | 2026-01-21 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 77/7 | Unassigned |  | 2026-01-21 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 84/3 | Unassigned |  | 2026-01-21 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 99/11 | Unassigned |  | 2026-01-21 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 101/2 | Unassigned |  | 2026-01-22 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 85/2 | Unassigned |  | 2026-01-22 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 100/1 | Unassigned |  | 2026-01-23 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 100/4 | Unassigned |  | 2026-01-24 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 84/4 | Unassigned |  | 2026-01-24 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 80/1 | Unassigned |  | 2026-01-25 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 102/4 | Unassigned |  | 2026-01-26 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 59/0 | Unassigned |  | 2026-01-26 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 84/0 | Unassigned |  | 2026-01-26 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 100/5 | Unassigned |  | 2026-01-27 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 59/5 | Unassigned |  | 2026-01-27 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 99/10 | Unassigned |  | 2026-01-27 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 101/1 | Unassigned |  | 2026-01-28 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 55/1 | Unassigned |  | 2026-01-28 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 84/1 | Unassigned |  | 2026-01-28 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 99/7 | Unassigned |  | 2026-01-29 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 53/2 | Unassigned |  | 2026-01-30 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 77/10 | Unassigned |  | 2026-01-30 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 100/2 | Unassigned |  | 2026-01-31 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 101/0 | Unassigned |  | 2026-01-31 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 101/3 | Unassigned |  | 2026-01-31 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 102/5 | Unassigned |  | 2026-01-31 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 52/0 | Unassigned |  | 2026-01-31 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 79/2 | Unassigned |  | 2026-01-31 | 2026-01 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 60/2 | Unassigned |  | 2026-02-02 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 85/2 | Unassigned |  | 2026-02-03 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 99/8 | Unassigned |  | 2026-02-03 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 79/3 | Unassigned |  | 2026-02-04 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 100/1 | Unassigned |  | 2026-02-05 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 51/9 | Unassigned |  | 2026-02-05 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 84/5 | Unassigned |  | 2026-02-05 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 78/3 | Unassigned |  | 2026-02-06 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 102/3 | Unassigned |  | 2026-02-08 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 53/1 | Unassigned |  | 2026-02-08 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 56/8 | Unassigned |  | 2026-02-09 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 99/6 | Unassigned |  | 2026-02-09 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 77/9 | Unassigned |  | 2026-02-10 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 84/0 | Unassigned |  | 2026-02-10 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 102/2 | Unassigned |  | 2026-02-11 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 56/6 | Unassigned |  | 2026-02-11 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 101/2 | Unassigned |  | 2026-02-12 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 50/1 | Unassigned |  | 2026-02-12 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 56/9 | Unassigned |  | 2026-02-13 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 81/1 | Unassigned |  | 2026-02-13 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 101/5 | Unassigned |  | 2026-02-14 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 102/1 | Unassigned |  | 2026-02-14 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 83/1 | Unassigned |  | 2026-02-15 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 101/3 | Unassigned |  | 2026-02-16 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 99/9 | Unassigned |  | 2026-02-16 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 102/4 | Unassigned |  | 2026-02-17 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 50/2 | Unassigned |  | 2026-02-17 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 55/1 | Unassigned |  | 2026-02-17 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 102/5 | Unassigned |  | 2026-02-19 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 101/1 | Unassigned |  | 2026-02-20 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 56/7 | Unassigned |  | 2026-02-20 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 52/0 | Unassigned |  | 2026-02-21 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 101/6 | Unassigned |  | 2026-02-22 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 102/2 | Unassigned |  | 2026-02-22 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 100/5 | Unassigned |  | 2026-02-24 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 100/6 | Unassigned |  | 2026-02-24 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 102/3 | Unassigned |  | 2026-02-24 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 53/1 | Unassigned |  | 2026-02-25 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 85/1 | Unassigned |  | 2026-02-25 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 100/8 | Unassigned |  | 2026-02-26 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 56/2 | Unassigned |  | 2026-02-26 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 102/1 | Unassigned |  | 2026-02-27 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 100/7 | Unassigned |  | 2026-02-28 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 101/7 | Unassigned |  | 2026-02-28 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 53/2 | Unassigned |  | 2026-02-28 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 77/9 | Unassigned |  | 2026-02-28 | 2026-02 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 101/5 | Unassigned |  | 2026-03-02 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 101/0 | Unassigned |  | 2026-03-03 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 89/1 | Unassigned |  | 2026-03-03 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 51/9 | Unassigned |  | 2026-03-05 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 53/4 | Unassigned |  | 2026-03-06 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 56/3 | Unassigned |  | 2026-03-07 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 53/5 | Unassigned |  | 2026-03-08 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 83/1 | Unassigned |  | 2026-03-09 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 49/10 | Unassigned |  | 2026-03-11 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 85/1 | Unassigned |  | 2026-03-11 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 51/7 | Unassigned |  | 2026-03-13 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 49/11 | Unassigned |  | 2026-03-14 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 51/8 | Unassigned |  | 2026-03-14 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 100/6 | Unassigned |  | 2026-03-16 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 101/6 | Unassigned |  | 2026-03-16 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 51/10 | Unassigned |  | 2026-03-17 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 100/0 | Unassigned |  | 2026-03-18 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 55/3 | Unassigned |  | 2026-03-18 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 90/0 | Unassigned |  | 2026-03-18 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 51/6 | Unassigned |  | 2026-03-19 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 101/7 | Unassigned |  | 2026-03-20 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 52/1 | Unassigned |  | 2026-03-22 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 100/7 | Unassigned |  | 2026-03-23 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 50/3 | Unassigned |  | 2026-03-25 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 56/4 | Unassigned |  | 2026-03-25 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 51/2 | Unassigned |  | 2026-03-27 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 100/4 | Unassigned |  | 2026-03-29 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 53/3 | Unassigned |  | 2026-03-31 | 2026-03 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 53/4 | Unassigned |  | 2026-04-01 | 2026-04 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 100/8 | Unassigned |  | 2026-04-04 | 2026-04 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 60/0 | Unassigned |  | 2026-04-06 | 2026-04 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 53/5 | Unassigned |  | 2026-04-07 | 2026-04 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 70/1 | Unassigned |  | 2026-04-11 | 2026-04 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 100/0 | Unassigned |  | 2026-04-12 | 2026-04 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 53/0 | Unassigned |  | 2026-04-13 | 2026-04 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 70/2 | Unassigned |  | 2026-04-13 | 2026-04 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 50/0 | Unassigned |  | 2026-04-16 | 2026-04 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 70/4 | Unassigned |  | 2026-04-16 | 2026-04 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 70/3 | Unassigned |  | 2026-04-18 | 2026-04 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 66/1 | Unassigned |  | 2026-04-21 | 2026-04 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 49/9 | Unassigned |  | 2026-04-23 | 2026-04 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 67/0 | Unassigned |  | 2026-04-26 | 2026-04 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 65/3 | Unassigned |  | 2026-04-29 | 2026-04 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 49/8 | Unassigned |  | 2026-04-30 | 2026-04 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 66/0 | Unassigned |  | 2026-05-03 | 2026-05 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 67/1 | Unassigned |  | 2026-05-05 | 2026-05 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 48/7 | Unassigned |  | 2026-05-10 | 2026-05 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 69/0 | Unassigned |  | 2026-05-13 | 2026-05 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 69/2 | Unassigned |  | 2026-05-16 | 2026-05 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 60/0 | Unassigned |  | 2026-05-18 | 2026-05 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 48/3 | Unassigned |  | 2026-05-19 | 2026-05 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 69/1 | Unassigned |  | 2026-05-20 | 2026-05 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 68/2 | Unassigned |  | 2026-05-23 | 2026-05 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 48/2 | Unassigned |  | 2026-05-24 | 2026-05 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 68/0 | Unassigned |  | 2026-05-30 | 2026-05 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 56/5 | Unassigned |  | 2026-05-31 | 2026-05 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 72/1 | Unassigned |  | 2026-06-01 | 2026-06 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 59/0 | Unassigned |  | 2026-06-02 | 2026-06 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 73/0 | Unassigned |  | 2026-06-05 | 2026-06 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 56/10 | Unassigned |  | 2026-06-07 | 2026-06 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 75/2 | Unassigned |  | 2026-06-07 | 2026-06 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 75/3 | Unassigned |  | 2026-06-09 | 2026-06 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 49/8 | Unassigned |  | 2026-06-12 | 2026-06 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 56/12 | Unassigned |  | 2026-06-12 | 2026-06 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 75/1 | Unassigned |  | 2026-06-12 | 2026-06 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 60/3 | Unassigned |  | 2026-06-13 | 2026-06 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 77/5 | Unassigned |  | 2026-06-15 | 2026-06 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 601 | TA601 |  | 51/10 | Unassigned |  | 2026-06-16 | 2026-06 |  | Missing Start Date | detail | detail_date | TA 601 - DPR - 2026-06-16.xlsx | Progress Sheet
Mr. Arun Felbin | TA 602 | TA602 |  |  | Unassigned |  | 2026-06-09 | 2026-06 |  | Missing Start Date | snapshot_fallback | snapshot_cumulative | TA 602 - DPR - 2026-06-09.xlsx | DPR Sheet
Mr. Arun Felbin | TA 602 | TA602 |  |  | Unassigned |  | 2026-06-11 | 2026-06 |  | Missing Start Date | snapshot_fallback | snapshot_cumulative | TA 602 - DPR - 2026-06-11.xlsx | DPR Sheet
Mr. Arun Felbin | TA 602 | TA602 |  |  | Unassigned |  | 2026-06-12 | 2026-06 |  | Missing Start Date | snapshot_fallback | snapshot_cumulative | TA 602 - DPR - 2026-06-12.xlsx | DPR Sheet
Mr. Arun Felbin | TA 602 | TA602 |  |  | Unassigned |  | 2026-06-15 | 2026-06 |  | Missing Start Date | snapshot_fallback | snapshot_cumulative | TA 602 - DPR - 2026-06-15.xlsx | 800kV HVDC TA-602; DPR Sheet
Mr. Arun Felbin | TA 602 | TA602 |  |  | Unassigned |  | 2026-06-16 | 2026-06 |  | Missing Start Date | snapshot_fallback | snapshot_cumulative | TA 602 - DPR - 2026-06-16.xlsx | 800kV HVDC TA-602
Mr. NK Gupta | TB 408 | TB408 |  | 1 | Unassigned |  | 2023-10-01 | 2023-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 10 | Unassigned |  | 2023-12-01 | 2023-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 11 | Unassigned |  | 2023-12-01 | 2023-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 12 | Unassigned |  | 2023-12-01 | 2023-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 13 | Unassigned |  | 2023-12-01 | 2023-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 14 | Unassigned |  | 2023-12-01 | 2023-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 15 | Unassigned |  | 2023-12-01 | 2023-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 16 | Unassigned |  | 2023-12-01 | 2023-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 17 | Unassigned |  | 2023-12-01 | 2023-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 18 | Unassigned |  | 2023-12-01 | 2023-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 19 | Unassigned |  | 2023-12-01 | 2023-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 2 | Unassigned |  | 2023-12-01 | 2023-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 20 | Unassigned |  | 2023-12-01 | 2023-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 21 | Unassigned |  | 2023-12-01 | 2023-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 22 | Unassigned |  | 2023-12-01 | 2023-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 23 | Unassigned |  | 2023-12-01 | 2023-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 3 | Unassigned |  | 2023-12-01 | 2023-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 4 | Unassigned |  | 2023-12-01 | 2023-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 5 | Unassigned |  | 2023-12-01 | 2023-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 6 | Unassigned |  | 2023-12-01 | 2023-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 7 | Unassigned |  | 2023-12-01 | 2023-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 8 | Unassigned |  | 2023-12-01 | 2023-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 9 | Unassigned |  | 2023-12-01 | 2023-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 24 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 25 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 26 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 27 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 28 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 29 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 30 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 31 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 32 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 33 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 34 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 35 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 36 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 37 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 38 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 39 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 40 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 41 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 42 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 43 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 44 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 45 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 46 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 47 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 48 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 49 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 50 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 51 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 52 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 53 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 54 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 55 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 56 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 57 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 58 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 59 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 60 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 61 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 62 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 63 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 64 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 65 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 66 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 67 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 68 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 69 | Unassigned |  | 2024-01-01 | 2024-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 100 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 101 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 102 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 103 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 104 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 105 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 70 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 71 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 72 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 73 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 74 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 75 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 76 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 77 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 78 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 79 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 80 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 81 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 82 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 83 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 84 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 85 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 86 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 87 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 88 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 89 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 90 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 91 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 92 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 93 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 94 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 95 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 96 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 97 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 98 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 99 | Unassigned |  | 2024-02-01 | 2024-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 106 | Unassigned |  | 2024-03-01 | 2024-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 107 | Unassigned |  | 2024-03-01 | 2024-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 108 | Unassigned |  | 2024-03-01 | 2024-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 109 | Unassigned |  | 2024-03-01 | 2024-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 110 | Unassigned |  | 2024-03-01 | 2024-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 111 | Unassigned |  | 2024-03-01 | 2024-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 112 | Unassigned |  | 2024-03-01 | 2024-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 113 | Unassigned |  | 2024-03-01 | 2024-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 114 | Unassigned |  | 2024-03-01 | 2024-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 115 | Unassigned |  | 2024-03-01 | 2024-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 116 | Unassigned |  | 2024-03-01 | 2024-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 117 | Unassigned |  | 2024-03-01 | 2024-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 118 | Unassigned |  | 2024-03-01 | 2024-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 119 | Unassigned |  | 2024-03-01 | 2024-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 120 | Unassigned |  | 2024-03-01 | 2024-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 121 | Unassigned |  | 2024-03-01 | 2024-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 122 | Unassigned |  | 2024-04-01 | 2024-04 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 123 | Unassigned |  | 2024-04-01 | 2024-04 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 124 | Unassigned |  | 2024-04-01 | 2024-04 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 125 | Unassigned |  | 2024-04-01 | 2024-04 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 126 | Unassigned |  | 2024-04-01 | 2024-04 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 127 | Unassigned |  | 2024-04-01 | 2024-04 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 128 | Unassigned |  | 2024-04-01 | 2024-04 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 129 | Unassigned |  | 2024-05-01 | 2024-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 130 | Unassigned |  | 2024-05-01 | 2024-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 131 | Unassigned |  | 2024-05-01 | 2024-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 132 | Unassigned |  | 2024-05-01 | 2024-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 133 | Unassigned |  | 2024-05-01 | 2024-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 134 | Unassigned |  | 2024-05-01 | 2024-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 135 | Unassigned |  | 2024-05-01 | 2024-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 136 | Unassigned |  | 2024-05-01 | 2024-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 137 | Unassigned |  | 2024-05-01 | 2024-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 138 | Unassigned |  | 2024-05-01 | 2024-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 139 | Unassigned |  | 2024-05-01 | 2024-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 140 | Unassigned |  | 2024-05-01 | 2024-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 141 | Unassigned |  | 2024-05-01 | 2024-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 142 | Unassigned |  | 2024-05-01 | 2024-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 143 | Unassigned |  | 2024-05-01 | 2024-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 144 | Unassigned |  | 2024-06-01 | 2024-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 145 | Unassigned |  | 2024-06-01 | 2024-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 146 | Unassigned |  | 2024-06-01 | 2024-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 147 | Unassigned |  | 2024-06-01 | 2024-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 148 | Unassigned |  | 2024-06-01 | 2024-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 149 | Unassigned |  | 2024-06-01 | 2024-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 150 | Unassigned |  | 2024-06-01 | 2024-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 151 | Unassigned |  | 2024-06-01 | 2024-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 152 | Unassigned |  | 2024-06-01 | 2024-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 153 | Unassigned |  | 2024-07-01 | 2024-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 154 | Unassigned |  | 2024-07-01 | 2024-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 155 | Unassigned |  | 2024-07-01 | 2024-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 156 | Unassigned |  | 2024-07-01 | 2024-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 157 | Unassigned |  | 2024-07-01 | 2024-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 158 | Unassigned |  | 2024-07-01 | 2024-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 159 | Unassigned |  | 2024-07-01 | 2024-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 160 | Unassigned |  | 2024-07-01 | 2024-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 161 | Unassigned |  | 2024-07-01 | 2024-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 162 | Unassigned |  | 2024-07-01 | 2024-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 163 | Unassigned |  | 2024-07-01 | 2024-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 164 | Unassigned |  | 2024-07-01 | 2024-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 165 | Unassigned |  | 2024-07-01 | 2024-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 166 | Unassigned |  | 2024-07-01 | 2024-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 167 | Unassigned |  | 2024-08-01 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 168 | Unassigned |  | 2024-08-01 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 169 | Unassigned |  | 2024-08-01 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 170 | Unassigned |  | 2024-08-01 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 171 | Unassigned |  | 2024-08-01 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 172 | Unassigned |  | 2024-08-01 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 173 | Unassigned |  | 2024-08-01 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 174 | Unassigned |  | 2024-08-01 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 175 | Unassigned |  | 2024-08-01 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 176 | Unassigned |  | 2024-08-01 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 177 | Unassigned |  | 2024-08-01 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 178 | Unassigned |  | 2024-08-01 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 179 | Unassigned |  | 2024-08-01 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 180 | Unassigned |  | 2024-08-01 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 181 | Unassigned |  | 2024-08-01 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 182 | Unassigned |  | 2024-08-01 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 183 | Unassigned |  | 2024-08-01 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 184 | Unassigned |  | 2024-08-01 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 185 | Unassigned |  | 2024-08-01 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 186 | Unassigned |  | 2024-08-01 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 187 | Unassigned |  | 2024-08-01 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 188 | Unassigned |  | 2024-08-01 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 189 | Unassigned |  | 2024-08-01 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 190 | Unassigned |  | 2024-08-01 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 191 | Unassigned |  | 2024-08-01 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 192 | Unassigned |  | 2024-08-01 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 193 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 194 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 195 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 196 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 197 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 198 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 199 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 200 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 201 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 202 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 203 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 204 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 205 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 206 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 207 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 208 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 209 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 210 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 211 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 212 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 213 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 214 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 215 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 216 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 217 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 218 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 219 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 220 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 221 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 222 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 223 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 224 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 225 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 226 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 227 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 228 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 229 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 230 | Unassigned |  | 2024-09-01 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 231 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 232 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 233 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 234 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 235 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 236 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 237 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 238 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 239 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 240 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 241 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 242 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 243 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 244 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 245 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 246 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 247 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 248 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 249 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 250 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 251 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 252 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 253 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 254 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 255 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 256 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 257 | Unassigned |  | 2024-11-01 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 258 | Unassigned |  | 2024-11-01 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 259 | Unassigned |  | 2024-11-01 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 260 | Unassigned |  | 2024-11-01 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 261 | Unassigned |  | 2024-11-01 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 262 | Unassigned |  | 2024-11-01 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 263 | Unassigned |  | 2024-11-01 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 264 | Unassigned |  | 2024-11-01 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 265 | Unassigned |  | 2024-11-01 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 266 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 267 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 268 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 269 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 270 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 271 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 272 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 273 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 274 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 275 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 276 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 277 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 278 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 279 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 280 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 281 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 282 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 283 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 284 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 285 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 286 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 287 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 288 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 289 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 290 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 291 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 292 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 293 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 294 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 295 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 296 | Unassigned |  | 2024-12-01 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 297 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 298 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 299 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 300 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 301 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 302 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 303 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 304 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 305 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 306 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 307 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 308 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 309 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 310 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 311 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 312 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 313 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 314 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 315 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 316 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 317 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 318 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 319 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 320 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 321 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 322 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 323 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 324 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 325 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 326 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 327 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 328 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 329 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 330 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 331 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 332 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 333 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 334 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 335 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 336 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 337 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 338 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 339 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 340 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 341 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 342 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 343 | Unassigned |  | 2025-01-01 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 344 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 345 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 346 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 347 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 348 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 349 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 350 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 351 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 352 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 353 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 354 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 355 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 356 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 357 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 358 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 359 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 360 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 361 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 362 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 363 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 364 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 365 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 366 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 367 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 368 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 369 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 370 | Unassigned |  | 2025-02-01 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 371 | Unassigned |  | 2025-03-01 | 2025-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 372 | Unassigned |  | 2025-03-01 | 2025-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 373 | Unassigned |  | 2025-03-01 | 2025-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 374 | Unassigned |  | 2025-03-01 | 2025-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 375 | Unassigned |  | 2025-03-01 | 2025-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 376 | Unassigned |  | 2025-03-01 | 2025-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 377 | Unassigned |  | 2025-03-01 | 2025-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 378 | Unassigned |  | 2025-03-01 | 2025-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 379 | Unassigned |  | 2025-03-01 | 2025-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 380 | Unassigned |  | 2025-03-01 | 2025-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 381 | Unassigned |  | 2025-03-01 | 2025-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 382 | Unassigned |  | 2025-03-01 | 2025-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 383 | Unassigned |  | 2025-03-01 | 2025-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 384 | Unassigned |  | 2025-03-01 | 2025-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 385 | Unassigned |  | 2025-03-01 | 2025-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 386 | Unassigned |  | 2025-03-01 | 2025-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 387 | Unassigned |  | 2025-03-01 | 2025-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 388 | Unassigned |  | 2025-04-01 | 2025-04 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 389 | Unassigned |  | 2025-04-01 | 2025-04 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 390 | Unassigned |  | 2025-04-01 | 2025-04 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 391 | Unassigned |  | 2025-04-01 | 2025-04 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 392 | Unassigned |  | 2025-04-01 | 2025-04 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 393 | Unassigned |  | 2025-04-01 | 2025-04 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 394 | Unassigned |  | 2025-04-01 | 2025-04 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 395 | Unassigned |  | 2025-04-01 | 2025-04 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 396 | Unassigned |  | 2025-04-01 | 2025-04 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 397 | Unassigned |  | 2025-04-01 | 2025-04 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 398 | Unassigned |  | 2025-04-01 | 2025-04 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 399 | Unassigned |  | 2025-04-01 | 2025-04 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 400 | Unassigned |  | 2025-04-01 | 2025-04 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 401 | Unassigned |  | 2025-05-01 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 402 | Unassigned |  | 2025-05-01 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 403 | Unassigned |  | 2025-05-01 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 404 | Unassigned |  | 2025-05-01 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 405 | Unassigned |  | 2025-05-01 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 406 | Unassigned |  | 2025-05-01 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 407 | Unassigned |  | 2025-05-01 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 408 | Unassigned |  | 2025-05-01 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 409 | Unassigned |  | 2025-05-01 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 410 | Unassigned |  | 2025-05-01 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 411 | Unassigned |  | 2025-05-01 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 412 | Unassigned |  | 2025-05-01 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 413 | Unassigned |  | 2025-05-01 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 414 | Unassigned |  | 2025-06-01 | 2025-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 415 | Unassigned |  | 2025-06-01 | 2025-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 416 | Unassigned |  | 2025-06-01 | 2025-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 417 | Unassigned |  | 2025-06-01 | 2025-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 418 | Unassigned |  | 2025-06-01 | 2025-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 419 | Unassigned |  | 2025-06-01 | 2025-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 420 | Unassigned |  | 2025-06-01 | 2025-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 421 | Unassigned |  | 2025-06-01 | 2025-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 422 | Unassigned |  | 2025-06-01 | 2025-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 423 | Unassigned |  | 2025-06-01 | 2025-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 424 | Unassigned |  | 2025-06-01 | 2025-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 425 | Unassigned |  | 2025-06-01 | 2025-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 426 | Unassigned |  | 2025-06-01 | 2025-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 427 | Unassigned |  | 2025-06-01 | 2025-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 428 | Unassigned |  | 2025-06-01 | 2025-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 429 | Unassigned |  | 2025-06-01 | 2025-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 430 | Unassigned |  | 2025-06-01 | 2025-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 431 | Unassigned |  | 2025-06-01 | 2025-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 432 | Unassigned |  | 2025-06-01 | 2025-06 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 433 | Unassigned |  | 2025-07-01 | 2025-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 434 | Unassigned |  | 2025-07-01 | 2025-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 435 | Unassigned |  | 2025-07-01 | 2025-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 436 | Unassigned |  | 2025-07-01 | 2025-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 437 | Unassigned |  | 2025-07-01 | 2025-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 438 | Unassigned |  | 2025-07-01 | 2025-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 439 | Unassigned |  | 2025-07-01 | 2025-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 440 | Unassigned |  | 2025-07-01 | 2025-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 441 | Unassigned |  | 2025-07-01 | 2025-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 442 | Unassigned |  | 2025-07-01 | 2025-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 443 | Unassigned |  | 2025-07-01 | 2025-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 444 | Unassigned |  | 2025-07-01 | 2025-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 445 | Unassigned |  | 2025-07-01 | 2025-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 446 | Unassigned |  | 2025-07-01 | 2025-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 447 | Unassigned |  | 2025-07-01 | 2025-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 448 | Unassigned |  | 2025-07-01 | 2025-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 449 | Unassigned |  | 2025-07-01 | 2025-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 450 | Unassigned |  | 2025-07-01 | 2025-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 451 | Unassigned |  | 2025-07-01 | 2025-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 452 | Unassigned |  | 2025-07-01 | 2025-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 453 | Unassigned |  | 2025-07-01 | 2025-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 454 | Unassigned |  | 2025-07-01 | 2025-07 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 455 | Unassigned |  | 2025-08-01 | 2025-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 456 | Unassigned |  | 2025-08-01 | 2025-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 457 | Unassigned |  | 2025-08-01 | 2025-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 458 | Unassigned |  | 2025-08-01 | 2025-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 459 | Unassigned |  | 2025-08-01 | 2025-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 460 | Unassigned |  | 2025-08-01 | 2025-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 461 | Unassigned |  | 2025-08-01 | 2025-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 462 | Unassigned |  | 2025-08-01 | 2025-08 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 463 | Unassigned |  | 2025-09-01 | 2025-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 464 | Unassigned |  | 2025-09-01 | 2025-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 465 | Unassigned |  | 2025-09-01 | 2025-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 466 | Unassigned |  | 2025-09-01 | 2025-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 467 | Unassigned |  | 2025-09-01 | 2025-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 468 | Unassigned |  | 2025-09-01 | 2025-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 469 | Unassigned |  | 2025-09-01 | 2025-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 470 | Unassigned |  | 2025-09-01 | 2025-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 471 | Unassigned |  | 2025-09-01 | 2025-09 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 472 | Unassigned |  | 2025-10-01 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 473 | Unassigned |  | 2025-10-01 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 474 | Unassigned |  | 2025-10-01 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 475 | Unassigned |  | 2025-10-01 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 476 | Unassigned |  | 2025-10-01 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 477 | Unassigned |  | 2025-10-01 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 478 | Unassigned |  | 2025-10-01 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 479 | Unassigned |  | 2025-11-01 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 480 | Unassigned |  | 2025-11-01 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 481 | Unassigned |  | 2025-11-01 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 482 | Unassigned |  | 2026-02-01 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 483 | Unassigned |  | 2026-02-01 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 484 | Unassigned |  | 2026-02-01 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. NK Gupta | TB 408 | TB408 |  | 485 | Unassigned |  | 2026-03-01 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 408 - DPR - 2026-06-01.xlsx | Foundation
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 20/7 | Unassigned |  | 2024-08-12 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 20/5 | Unassigned |  | 2024-08-16 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 18/3 | Unassigned |  | 2024-08-19 | 2024-08 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 10/3 | Unassigned |  | 2024-09-09 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 15/2 | Unassigned |  | 2024-09-11 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 15/3 | Unassigned |  | 2024-09-15 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 21/6 | Unassigned |  | 2024-09-19 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 15/1 | Unassigned |  | 2024-09-22 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 21/7 | Unassigned |  | 2024-09-23 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 9/8 | Unassigned |  | 2024-09-28 | 2024-09 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 16/1 | Unassigned |  | 2024-10-01 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 19/2 | Unassigned |  | 2024-10-04 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 17/3 | Unassigned |  | 2024-10-06 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 22/2 | Unassigned |  | 2024-10-09 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | AP-16 | Unassigned |  | 2024-10-10 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 17/2 | Unassigned |  | 2024-10-11 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 16/3 | Unassigned |  | 2024-10-16 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 18/5 | Unassigned |  | 2024-10-18 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | AP-12 | Unassigned |  | 2024-10-19 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | AP-11 | Unassigned |  | 2024-10-20 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | AP-19 | Unassigned |  | 2024-10-20 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 21/12 | Unassigned |  | 2024-10-21 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | AP-18 | Unassigned |  | 2024-10-21 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 10/4 | Unassigned |  | 2024-10-22 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 20/6 | Unassigned |  | 2024-10-22 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 15/4 | Unassigned |  | 2024-10-24 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 17/1 | Unassigned |  | 2024-10-24 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 18/11 | Unassigned |  | 2024-10-24 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 20/3 | Unassigned |  | 2024-10-26 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 21/3 | Unassigned |  | 2024-10-26 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 11/1 | Unassigned |  | 2024-10-27 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 16/2 | Unassigned |  | 2024-10-27 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 20/4 | Unassigned |  | 2024-10-30 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 9/9 | Unassigned |  | 2024-10-30 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | AP-17 | Unassigned |  | 2024-10-31 | 2024-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 15/7 | Unassigned |  | 2024-11-03 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 18/4 | Unassigned |  | 2024-11-04 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 20/2 | Unassigned |  | 2024-11-05 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 15/6 | Unassigned |  | 2024-11-06 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 20/1 | Unassigned |  | 2024-11-08 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | AP-14 | Unassigned |  | 2024-11-08 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 15/8 | Unassigned |  | 2024-11-09 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | AP-21 | Unassigned |  | 2024-11-09 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 15/9 | Unassigned |  | 2024-11-12 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | AP-20 | Unassigned |  | 2024-11-12 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 18/6 | Unassigned |  | 2024-11-14 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 10/2 | Unassigned |  | 2024-11-15 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 21/5 | Unassigned |  | 2024-11-15 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 21/4 | Unassigned |  | 2024-11-17 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 19/3 | Unassigned |  | 2024-11-18 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 21/10 | Unassigned |  | 2024-11-19 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 21/8 | Unassigned |  | 2024-11-19 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 18/7 | Unassigned |  | 2024-11-20 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 19/5 | Unassigned |  | 2024-11-21 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 19/4 | Unassigned |  | 2024-11-24 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 18/9 | Unassigned |  | 2024-11-26 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 19/1 | Unassigned |  | 2024-11-26 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | AP-10 | Unassigned |  | 2024-11-26 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 18/1 | Unassigned |  | 2024-11-29 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 18/10 | Unassigned |  | 2024-11-30 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 18/8 | Unassigned |  | 2024-11-30 | 2024-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 21/9 | Unassigned |  | 2024-12-04 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 5/2 | Unassigned |  | 2024-12-06 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 5/3 | Unassigned |  | 2024-12-07 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 18/2 | Unassigned |  | 2024-12-08 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 15/5 | Unassigned |  | 2024-12-09 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 8B/0 | Unassigned |  | 2024-12-11 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | AP-22 | Unassigned |  | 2024-12-11 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 23/4 | Unassigned |  | 2024-12-15 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | AP-15 | Unassigned |  | 2024-12-15 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 14/9 | Unassigned |  | 2024-12-19 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 22/1 | Unassigned |  | 2024-12-19 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 4/14 | Unassigned |  | 2024-12-19 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 8B/1 | Unassigned |  | 2024-12-19 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 29A/2 | Unassigned |  | 2024-12-20 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 4/13 | Unassigned |  | 2024-12-20 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 23/2 | Unassigned |  | 2024-12-23 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 14/7 | Unassigned |  | 2024-12-25 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 29A/3 | Unassigned |  | 2024-12-25 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 4/15 | Unassigned |  | 2024-12-25 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 29A/1 | Unassigned |  | 2024-12-26 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 8B/2 | Unassigned |  | 2024-12-27 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 30/1 | Unassigned |  | 2024-12-28 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | AP-30 | Unassigned |  | 2024-12-28 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 5A/0 | Unassigned |  | 2024-12-29 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 30/6 | Unassigned |  | 2024-12-30 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 14/8 | Unassigned |  | 2024-12-31 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 30/3 | Unassigned |  | 2024-12-31 | 2024-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 8A/0 | Unassigned |  | 2025-01-04 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 30/4 | Unassigned |  | 2025-01-05 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 5/1 | Unassigned |  | 2025-01-05 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 30/2 | Unassigned |  | 2025-01-06 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | AP-31 | Unassigned |  | 2025-01-07 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 4/4 | Unassigned |  | 2025-01-08 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 30/5 | Unassigned |  | 2025-01-10 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 4/11 | Unassigned |  | 2025-01-12 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 4/3 | Unassigned |  | 2025-01-14 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 4/6 | Unassigned |  | 2025-01-14 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 31/1 | Unassigned |  | 2025-01-15 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 8D/0 | Unassigned |  | 2025-01-16 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 4/2 | Unassigned |  | 2025-01-18 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 29A/4 | Unassigned |  | 2025-01-19 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 4/5 | Unassigned |  | 2025-01-19 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 32/1 | Unassigned |  | 2025-01-23 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 4/1 | Unassigned |  | 2025-01-24 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 8E/2 | Unassigned |  | 2025-01-27 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | AP-32 | Unassigned |  | 2025-01-29 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 4/9 | Unassigned |  | 2025-01-30 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 1D/0 | Unassigned |  | 2025-01-31 | 2025-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 1A/2 | Unassigned |  | 2025-02-02 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 2/0 | Unassigned |  | 2025-02-02 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 1A/1 | Unassigned |  | 2025-02-05 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 4/0 | Unassigned |  | 2025-02-05 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 1/2 | Unassigned |  | 2025-02-06 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | AP-23 | Unassigned |  | 2025-02-06 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 4/10 | Unassigned |  | 2025-02-08 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 0/1 | Unassigned |  | 2025-02-09 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 23/1 | Unassigned |  | 2025-02-10 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 4/16 | Unassigned |  | 2025-02-12 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 32/2 | Unassigned |  | 2025-02-15 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 4/17 | Unassigned |  | 2025-02-15 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 1A/0 | Unassigned |  | 2025-02-17 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 3/0 | Unassigned |  | 2025-02-18 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 21/11 | Unassigned |  | 2025-02-19 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 0/0 | Unassigned |  | 2025-02-20 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 1D/1 | Unassigned |  | 2025-02-22 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 1/1 | Unassigned |  | 2025-02-23 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 1C/1 | Unassigned |  | 2025-02-25 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 20/8 | Unassigned |  | 2025-02-25 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 23/3 | Unassigned |  | 2025-02-28 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 1B/0 | Unassigned |  | 2025-03-05 | 2025-03 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 7/1 | Unassigned |  | 2025-03-09 | 2025-03 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 7/0 | Unassigned |  | 2025-03-16 | 2025-03 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 7/2 | Unassigned |  | 2025-03-16 | 2025-03 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | AP-26 | Unassigned |  | 2025-03-16 | 2025-03 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 1E/0 | Unassigned |  | 2025-03-22 | 2025-03 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 7/3 | Unassigned |  | 2025-03-23 | 2025-03 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 1/0 | Unassigned |  | 2025-03-27 | 2025-03 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 5/0 | Unassigned |  | 2025-03-28 | 2025-03 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | AP-27 | Unassigned |  | 2025-04-03 | 2025-04 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | AP-13 | Unassigned |  | 2025-04-08 | 2025-04 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 21/1 | Unassigned |  | 2025-04-15 | 2025-04 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | AP-25 | Unassigned |  | 2025-04-17 | 2025-04 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 10/1 | Unassigned |  | 2025-04-19 | 2025-04 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 21/2 | Unassigned |  | 2025-04-21 | 2025-04 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 8E/5 | Unassigned |  | 2025-04-25 | 2025-04 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 8E/4 | Unassigned |  | 2025-04-26 | 2025-04 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 21/13 | Unassigned |  | 2025-04-27 | 2025-04 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | AP-24 | Unassigned |  | 2025-04-29 | 2025-04 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 23/5 | Unassigned |  | 2025-04-30 | 2025-04 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 29A/0 | Unassigned |  | 2025-05-10 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 8C/0 | Unassigned |  | 2025-05-12 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 4/12 | Unassigned |  | 2025-05-13 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | AP-29 | Unassigned |  | 2025-05-14 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 9/1 | Unassigned |  | 2025-05-17 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 8/0 | Unassigned |  | 2025-05-18 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | AP-9 | Unassigned |  | 2025-05-18 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 9/2 | Unassigned |  | 2025-05-22 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 9/6 | Unassigned |  | 2025-05-23 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 28/1 | Unassigned |  | 2025-05-24 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 8E/10 | Unassigned |  | 2025-05-25 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 9/5 | Unassigned |  | 2025-05-25 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | AP-28 | Unassigned |  | 2025-05-25 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 8E/8 | Unassigned |  | 2025-05-26 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 8E/12 | Unassigned |  | 2025-05-27 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 8E/9 | Unassigned |  | 2025-05-29 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 9/7 | Unassigned |  | 2025-05-29 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 8E/11 | Unassigned |  | 2025-05-30 | 2025-05 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 8E/6 | Unassigned |  | 2025-06-04 | 2025-06 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 9/3 | Unassigned |  | 2025-06-05 | 2025-06 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 9/4 | Unassigned |  | 2025-06-05 | 2025-06 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 8E/3 | Unassigned |  | 2025-06-06 | 2025-06 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 8E/1 | Unassigned |  | 2025-06-08 | 2025-06 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 28/2 | Unassigned |  | 2025-06-29 | 2025-06 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 17/0 | Unassigned |  | 2025-07-10 | 2025-07 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 8D/5 | Unassigned |  | 2025-08-17 | 2025-08 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 8D/6 | Unassigned |  | 2025-08-23 | 2025-08 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 8D/4 | Unassigned |  | 2025-08-30 | 2025-08 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 4/8 | Unassigned |  | 2025-09-03 | 2025-09 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 14/1 | Unassigned |  | 2025-09-07 | 2025-09 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 8D/3 | Unassigned |  | 2025-09-10 | 2025-09 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 14/3 | Unassigned |  | 2025-09-12 | 2025-09 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 14/2 | Unassigned |  | 2025-09-20 | 2025-09 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 8E/0 | Unassigned |  | 2025-09-21 | 2025-09 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 4/7 | Unassigned |  | 2025-09-26 | 2025-09 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 14/4 | Unassigned |  | 2025-09-30 | 2025-09 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 14/5 | Unassigned |  | 2025-10-08 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 5A/1 | Unassigned |  | 2025-10-08 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 5A/2 | Unassigned |  | 2025-10-12 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 5B/0 | Unassigned |  | 2025-10-17 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 16/0 | Unassigned |  | 2025-10-23 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 16/1 | Unassigned |  | 2025-10-27 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 14/6 | Unassigned |  | 2025-11-05 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 18/0 | Unassigned |  | 2025-11-07 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 13/1 | Unassigned |  | 2025-11-08 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 16/2 | Unassigned |  | 2025-11-15 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 8E/7 | Unassigned |  | 2025-11-16 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 8D/1 | Unassigned |  | 2025-11-20 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 6/0 | Unassigned |  | 2025-11-26 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 8D/2 | Unassigned |  | 2025-12-03 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 8D/0A | Unassigned |  | 2025-12-07 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 10/0 | Unassigned |  | 2025-12-13 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 15/2 | Unassigned |  | 2025-12-15 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 11/0 | Unassigned |  | 2025-12-16 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 15/1 | Unassigned |  | 2025-12-16 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 12/0 | Unassigned |  | 2025-12-17 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 15/3 | Unassigned |  | 2025-12-19 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 13/0 | Unassigned |  | 2025-12-25 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 14/0 | Unassigned |  | 2025-12-28 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 12/1 | Unassigned |  | 2026-01-10 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 13/2 | Unassigned |  | 2026-01-10 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 13/1 | Unassigned |  | 2026-01-14 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 8/0 | Unassigned |  | 2026-01-21 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 9/0 | Unassigned |  | 2026-01-21 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 7/0 | Unassigned |  | 2026-01-25 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 6/2 | Unassigned |  | 2026-01-27 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 6/1 | Unassigned |  | 2026-01-30 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 6/3 | Unassigned |  | 2026-01-31 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 5/0 | Unassigned |  | 2026-02-05 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 15/0 | Unassigned |  | 2026-02-10 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 6/0 | Unassigned |  | 2026-02-19 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 1C/0 | Unassigned |  | 2026-02-24 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 4/0 | Unassigned |  | 2026-03-08 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 6/4 | Unassigned |  | 2026-03-14 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 4/1 | Unassigned |  | 2026-03-16 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 4/2 | Unassigned |  | 2026-03-17 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 33/0 (New) | Unassigned |  | 2026-04-09 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 3/1 | Unassigned |  | 2026-04-12 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501132KV | TB501 | 132kV | 3/0 | Unassigned |  | 2026-04-14 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-132kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 33/1 (New) | Unassigned |  | 2026-04-20 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. Nabajit Baruah | TB 501220KV | TB501 | 220kV | 34/0 (New) | Unassigned |  | 2026-04-30 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 501 - DPR - 2026-06-15.xlsx | Progress-220kV
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 83/1 | Unassigned | 2025-01-08 | 2025-01-17 | 2025-01 | 10 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 75/7 | Unassigned | 2025-01-18 | 2025-01-27 | 2025-01 | 10 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 75/6 | Unassigned | 2025-01-28 | 2025-02-02 | 2025-02 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 75/4 | Unassigned | 2025-01-29 | 2025-02-05 | 2025-02 | 8 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 75/5 | Unassigned | 2025-02-03 | 2025-02-05 | 2025-02 | 3 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 77/2 | Unassigned | 2025-02-03 | 2025-02-09 | 2025-02 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 75/3 | Unassigned |  | 2025-02-10 | 2025-02 |  | Missing Start Date | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 77/1 | Unassigned | 2025-02-03 | 2025-02-11 | 2025-02 | 9 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 77/3 | Unassigned | 2025-02-08 | 2025-02-14 | 2025-02 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 75/1 | Unassigned | 2025-02-09 | 2025-02-17 | 2025-02 | 9 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 77/4 | Unassigned | 2025-02-11 | 2025-02-17 | 2025-02 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 75/2 | Unassigned | 2025-02-12 | 2025-02-18 | 2025-02 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 77/5 | Unassigned | 2025-02-13 | 2025-02-19 | 2025-02 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 73/3 | Unassigned | 2025-02-17 | 2025-02-22 | 2025-02 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 86/2 | Unassigned | 2025-02-10 | 2025-02-22 | 2025-02 | 13 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 79/1 | Unassigned | 2025-02-17 | 2025-02-23 | 2025-02 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 73/2 | Unassigned | 2025-02-21 | 2025-02-25 | 2025-02 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 95A/1 | Unassigned | 2025-02-20 | 2025-02-25 | 2025-02 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 80/1 | Unassigned | 2025-02-20 | 2025-02-27 | 2025-02 | 8 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 66/1 | Unassigned | 2025-02-17 | 2025-02-28 | 2025-02 | 12 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 74/1 | Unassigned | 2025-02-24 | 2025-02-28 | 2025-02 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 96/1 | Unassigned | 2025-02-25 | 2025-02-28 | 2025-02 | 4 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 76/1 | Unassigned | 2025-02-24 | 2025-03-02 | 2025-03 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 66/2 | Unassigned | 2025-02-28 | 2025-03-06 | 2025-03 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 64/3 | Unassigned | 2025-03-03 | 2025-03-07 | 2025-03 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 96/2 | Unassigned | 2025-03-02 | 2025-03-07 | 2025-03 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 81/2 | Unassigned | 2025-03-02 | 2025-03-08 | 2025-03 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 86/1 | Unassigned | 2025-02-23 | 2025-03-09 | 2025-03 | 15 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 64/4 | Unassigned | 2025-03-06 | 2025-03-10 | 2025-03 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 85/1 | Unassigned | 2025-03-04 | 2025-03-10 | 2025-03 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 99/1 | Unassigned | 2025-02-27 | 2025-03-10 | 2025-03 | 12 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 66/3 | Unassigned | 2025-03-05 | 2025-03-11 | 2025-03 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 87/1 | Unassigned | 2025-03-15 | 2025-03-24 | 2025-03 | 10 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 64/7 | Unassigned | 2025-03-19 | 2025-03-26 | 2025-03 | 8 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 64/6 | Unassigned | 2025-03-25 | 2025-03-30 | 2025-03 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 87/2 | Unassigned | 2025-03-22 | 2025-03-30 | 2025-03 | 9 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 98A/1 | Unassigned | 2025-03-13 | 2025-03-30 | 2025-03 | 18 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 64/5 | Unassigned | 2025-03-29 | 2025-03-31 | 2025-03 | 3 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 98/1 | Unassigned | 2025-03-29 | 2025-04-04 | 2025-04 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 71/1 | Unassigned | 2025-04-04 | 2025-04-09 | 2025-04 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 91/1 | Unassigned | 2025-04-03 | 2025-04-13 | 2025-04 | 11 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 91/2 | Unassigned | 2025-03-30 | 2025-04-16 | 2025-04 | 18 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 51/2 | Unassigned | 2025-03-30 | 2025-04-17 | 2025-04 | 19 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 119/1 | Unassigned | 2025-04-15 | 2025-04-18 | 2025-04 | 4 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 95/2 | Unassigned | 2025-04-14 | 2025-04-20 | 2025-04 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 119/2 | Unassigned | 2025-04-18 | 2025-04-22 | 2025-04 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 51/3 | Unassigned | 2025-04-18 | 2025-04-23 | 2025-04 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 99/2 | Unassigned | 2025-04-19 | 2025-04-25 | 2025-04 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 104B/1 | Unassigned | 2025-04-22 | 2025-04-29 | 2025-04 | 8 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 62/4 | Unassigned | 2025-04-23 | 2025-04-29 | 2025-04 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 81/4 | Unassigned | 2025-04-20 | 2025-04-29 | 2025-04 | 10 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 104B/2 | Unassigned | 2025-04-28 | 2025-05-05 | 2025-05 | 8 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 105/1 | Unassigned | 2025-05-06 | 2025-05-15 | 2025-05 | 10 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 100/1 | Unassigned | 2025-05-04 | 2025-05-18 | 2025-05 | 15 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 81/5 | Unassigned | 2025-05-13 | 2025-05-21 | 2025-05 | 9 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 97/0 | Unassigned | 2025-05-07 | 2025-05-23 | 2025-05 | 17 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 99C/2 | Unassigned | 2025-05-18 | 2025-05-25 | 2025-05 | 8 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 105/0 | Unassigned | 2025-05-16 | 2025-05-28 | 2025-05 | 13 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 98A/0 | Unassigned | 2025-05-12 | 2025-05-29 | 2025-05 | 18 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 3A/1 | Unassigned | 2026-05-19 | 2025-05-31 | 2025-05 |  | Invalid Negative Duration | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 62/5 | Unassigned | 2025-05-02 | 2025-05-31 | 2025-05 | 30 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 81/3 | Unassigned | 2025-05-22 | 2025-06-04 | 2025-06 | 14 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 120/1 | Unassigned | 2025-05-30 | 2025-06-05 | 2025-06 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 96/0 | Unassigned | 2025-05-28 | 2025-06-06 | 2025-06 | 10 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 75/0 | Unassigned | 2025-06-01 | 2025-06-07 | 2025-06 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 147/2 | Unassigned | 2025-06-02 | 2025-06-08 | 2025-06 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 82/2 | Unassigned | 2025-06-02 | 2025-06-10 | 2025-06 | 9 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 147/5 | Unassigned | 2025-06-04 | 2025-06-12 | 2025-06 | 9 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 79/0 | Unassigned | 2025-08-08 | 2025-06-12 | 2025-06 |  | Invalid Negative Duration | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 119/0 | Unassigned | 2025-06-05 | 2025-06-15 | 2025-06 | 11 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 147/0 | Unassigned | 2025-06-08 | 2025-06-15 | 2025-06 | 8 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 82/1 | Unassigned | 2025-06-10 | 2025-06-15 | 2025-06 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 147/4 | Unassigned | 2025-06-13 | 2025-06-16 | 2025-06 | 4 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 78/0 | Unassigned | 2025-06-13 | 2025-06-16 | 2025-06 | 4 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 74/0 | Unassigned | 2025-06-16 | 2025-06-20 | 2025-06 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 147/1 | Unassigned | 2025-06-15 | 2025-06-21 | 2025-06 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 147/7 | Unassigned | 2025-06-15 | 2025-06-22 | 2025-06 | 8 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 95A/0 | Unassigned | 2025-06-16 | 2025-06-23 | 2025-06 | 8 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 146/2 | Unassigned | 2025-06-22 | 2025-06-25 | 2025-06 | 4 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 147/3 | Unassigned | 2025-06-22 | 2025-06-25 | 2025-06 | 4 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 73/0 | Unassigned | 2025-06-20 | 2025-06-26 | 2025-06 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 86/0 | Unassigned | 2025-06-17 | 2025-06-27 | 2025-06 | 11 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 114/0 | Unassigned | 2025-06-10 | 2025-06-30 | 2025-06 | 21 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 146/1 | Unassigned | 2025-06-25 | 2025-06-30 | 2025-06 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 147/8 | Unassigned | 2025-06-25 | 2025-06-30 | 2025-06 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 72/2 | Unassigned | 2025-06-25 | 2025-06-30 | 2025-06 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 95/1 | Unassigned | 2025-06-23 | 2025-07-04 | 2025-07 | 12 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 148/3 | Unassigned | 2025-06-27 | 2025-07-05 | 2025-07 | 9 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 106/0 | Unassigned | 2025-06-25 | 2025-07-06 | 2025-07 | 12 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 146/0 | Unassigned | 2025-07-03 | 2025-07-08 | 2025-07 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 148/1 | Unassigned | 2025-07-04 | 2025-07-08 | 2025-07 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 114/1 | Unassigned | 2025-07-04 | 2025-07-10 | 2025-07 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 148/2 | Unassigned | 2025-07-07 | 2025-07-10 | 2025-07 | 4 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 80/0 | Unassigned | 2025-06-28 | 2025-07-10 | 2025-07 | 13 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 141/1 | Unassigned | 2025-07-07 | 2025-07-11 | 2025-07 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 95/0 | Unassigned | 2025-06-27 | 2025-07-11 | 2025-07 | 15 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 148/4 | Unassigned | 2025-07-10 | 2025-07-12 | 2025-07 | 3 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 141/2 | Unassigned | 2025-07-09 | 2025-07-13 | 2025-07 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 145/4 | Unassigned | 2025-07-09 | 2025-07-13 | 2025-07 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 125/1 | Unassigned | 2025-07-04 | 2025-07-14 | 2025-07 | 11 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 133/6 | Unassigned | 2025-07-10 | 2025-07-14 | 2025-07 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 148/5 | Unassigned | 2025-07-13 | 2025-07-15 | 2025-07 | 3 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 109A/0 | Unassigned | 2025-07-09 | 2025-07-16 | 2025-07 | 8 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 113A/0 | Unassigned | 2025-07-08 | 2025-07-16 | 2025-07 | 9 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 133/5 | Unassigned | 2025-07-14 | 2025-07-16 | 2025-07 | 3 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 145/2 | Unassigned | 2025-07-14 | 2025-07-16 | 2025-07 | 3 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 142/0 | Unassigned | 2025-07-12 | 2025-07-17 | 2025-07 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 115/0 | Unassigned | 2025-07-10 | 2025-07-18 | 2025-07 | 9 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 148/6 | Unassigned | 2025-07-15 | 2025-07-18 | 2025-07 | 4 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 77/0 | Unassigned | 2025-07-08 | 2025-07-19 | 2025-07 | 12 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 133/4 | Unassigned | 2025-07-17 | 2025-07-21 | 2025-07 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 143/0 | Unassigned | 2025-07-17 | 2025-07-21 | 2025-07 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 145/1 | Unassigned | 2025-07-16 | 2025-07-21 | 2025-07 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 148/7 | Unassigned | 2025-07-19 | 2025-07-23 | 2025-07 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 125/0 | Unassigned | 2025-07-15 | 2025-07-24 | 2025-07 | 10 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 133/3 | Unassigned | 2025-07-22 | 2025-07-24 | 2025-07 | 3 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 94/0 | Unassigned | 2025-07-13 | 2025-07-24 | 2025-07 | 12 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 145/3 | Unassigned | 2025-07-22 | 2025-07-25 | 2025-07 | 4 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 126/2 | Unassigned | 2025-07-15 | 2025-07-26 | 2025-07 | 12 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 143/3 | Unassigned | 2025-07-22 | 2025-07-26 | 2025-07 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 133/8 | Unassigned | 2025-07-24 | 2025-07-27 | 2025-07 | 4 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 149B/1 | Unassigned | 2025-07-24 | 2025-07-27 | 2025-07 | 4 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 79/2 | Unassigned | 2025-07-11 | 2025-07-27 | 2025-07 | 17 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 110/0 | Unassigned | 2025-07-21 | 2025-07-28 | 2025-07 | 8 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 143/1 | Unassigned | 2025-07-25 | 2025-07-29 | 2025-07 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 99/3 | Unassigned | 2025-07-13 | 2025-07-29 | 2025-07 | 17 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 133/1 | Unassigned | 2025-07-27 | 2025-07-30 | 2025-07 | 4 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 149B/2 | Unassigned | 2025-07-27 | 2025-07-30 | 2025-07 | 4 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 111/0 | Unassigned | 2025-07-17 | 2025-07-31 | 2025-07 | 15 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 116/0 | Unassigned | 2025-07-23 | 2025-07-31 | 2025-07 | 9 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 129/1 | Unassigned | 2025-07-25 | 2025-07-31 | 2025-07 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 133/7 | Unassigned | 2025-07-30 | 2025-07-31 | 2025-07 | 2 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 143/6 | Unassigned | 2025-07-29 | 2025-07-31 | 2025-07 | 3 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 145/0 | Unassigned | 2025-07-25 | 2025-07-31 | 2025-07 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 76/0 | Unassigned | 2025-07-24 | 2025-07-31 | 2025-07 | 8 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 98B/0 | Unassigned | 2025-06-10 | 2025-07-31 | 2025-07 | 52 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 126/1 | Unassigned | 2025-07-27 | 2025-08-02 | 2025-08 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 143/7 | Unassigned | 2025-07-30 | 2025-08-02 | 2025-08 | 4 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 130/0 | Unassigned | 2025-07-07 | 2025-08-04 | 2025-08 | 29 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 143/5 | Unassigned | 2025-08-03 | 2025-08-04 | 2025-08 | 2 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 97/1 | Unassigned | 2025-07-31 | 2025-08-05 | 2025-08 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 143/2 | Unassigned | 2025-08-04 | 2025-08-06 | 2025-08 | 3 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 102/2 | Unassigned | 2025-08-01 | 2025-08-07 | 2025-08 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 133/2 | Unassigned | 2025-08-01 | 2025-08-07 | 2025-08 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 144/0 | Unassigned | 2025-08-01 | 2025-08-07 | 2025-08 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 98/0 | Unassigned | 2025-05-26 | 2025-08-07 | 2025-08 | 74 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 112/0 | Unassigned | 2025-08-02 | 2025-08-08 | 2025-08 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 129/0 | Unassigned | 2025-08-01 | 2025-08-08 | 2025-08 | 8 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 143/4 | Unassigned | 2025-08-06 | 2025-08-09 | 2025-08 | 4 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 83/0 | Unassigned | 2025-07-29 | 2025-08-09 | 2025-08 | 12 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 131/1 | Unassigned | 2025-08-06 | 2025-08-12 | 2025-08 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 149B/0 | Unassigned | 2025-08-07 | 2025-08-12 | 2025-08 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 102/1 | Unassigned | 2025-08-11 | 2025-08-14 | 2025-08 | 4 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 140/3 | Unassigned | 2025-08-10 | 2025-08-14 | 2025-08 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 99/0 | Unassigned | 2025-08-05 | 2025-08-14 | 2025-08 | 10 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 115/1 | Unassigned | 2025-08-05 | 2025-08-16 | 2025-08 | 12 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 134A/4 | Unassigned | 2025-08-06 | 2025-08-16 | 2025-08 | 11 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 140/2 | Unassigned | 2025-08-11 | 2025-08-17 | 2025-08 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 126/0 | Unassigned | 2025-08-03 | 2025-08-19 | 2025-08 | 17 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 135/0 | Unassigned | 2025-08-16 | 2025-08-19 | 2025-08 | 4 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 149A/0 | Unassigned | 2025-08-10 | 2025-08-19 | 2025-08 | 10 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 128/0 | Unassigned | 2025-08-11 | 2025-08-20 | 2025-08 | 10 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 131/2 | Unassigned | 2025-08-13 | 2025-08-20 | 2025-08 | 8 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 141/0 | Unassigned | 2025-08-16 | 2025-08-20 | 2025-08 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 87/0 | Unassigned | 2025-08-12 | 2025-08-22 | 2025-08 | 11 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 99/4 | Unassigned | 2025-08-14 | 2025-08-22 | 2025-08 | 9 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 129/2 | Unassigned | 2025-08-04 | 2025-08-23 | 2025-08 | 20 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 135/1 | Unassigned | 2025-08-20 | 2025-08-23 | 2025-08 | 4 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 138/1 | Unassigned | 2025-08-21 | 2025-08-23 | 2025-08 | 3 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 137/0 | Unassigned | 2025-08-05 | 2025-08-24 | 2025-08 | 20 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 63/1 | Unassigned | 2025-08-16 | 2025-08-24 | 2025-08 | 9 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 132/1 | Unassigned | 2025-08-20 | 2025-08-25 | 2025-08 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 138/2 | Unassigned | 2025-08-22 | 2025-08-25 | 2025-08 | 4 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 134A/2 | Unassigned | 2025-08-24 | 2025-08-26 | 2025-08 | 3 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 56/4 | Unassigned | 2025-08-20 | 2025-08-26 | 2025-08 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 56/2 | Unassigned | 2025-08-16 | 2025-08-27 | 2025-08 | 12 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 138/0 | Unassigned | 2025-08-22 | 2025-08-28 | 2025-08 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 149/0 | Unassigned | 2025-08-18 | 2025-08-28 | 2025-08 | 11 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 134/0 | Unassigned | 2025-08-24 | 2025-08-29 | 2025-08 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 134A/1 | Unassigned | 2025-08-25 | 2025-08-29 | 2025-08 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 116/1 | Unassigned | 2025-08-22 | 2025-08-31 | 2025-08 | 10 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 132/3 | Unassigned | 2025-08-26 | 2025-08-31 | 2025-08 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 134A/0 | Unassigned | 2025-08-25 | 2025-08-31 | 2025-08 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 138/3 | Unassigned | 2025-08-26 | 2025-08-31 | 2025-08 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 56/5 | Unassigned | 2025-08-26 | 2025-08-31 | 2025-08 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 82/0 | Unassigned | 2024-08-23 | 2025-08-31 | 2025-08 | 374 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 85/0 | Unassigned | 2025-08-22 | 2025-08-31 | 2025-08 | 10 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 99A/0 | Unassigned | 2025-08-23 | 2025-08-31 | 2025-08 | 9 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 131/0 | Unassigned | 2025-08-31 | 2025-09-04 | 2025-09 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 139/0 | Unassigned | 2025-08-29 | 2025-09-05 | 2025-09 | 8 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 147/6 | Unassigned | 2025-09-01 | 2025-09-05 | 2025-09 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 125/3 | Unassigned | 2025-09-05 | 2025-09-10 | 2025-09 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 57/0 | Unassigned | 2025-09-03 | 2025-09-10 | 2025-09 | 8 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 59/0 | Unassigned | 2025-09-05 | 2025-09-12 | 2025-09 | 8 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 81/0 | Unassigned | 2025-09-04 | 2025-09-12 | 2025-09 | 9 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 147/9 | Unassigned | 2025-09-06 | 2025-09-14 | 2025-09 | 9 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 64/0 | Unassigned | 2025-08-25 | 2025-09-14 | 2025-09 | 21 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 58/0 | Unassigned | 2025-09-12 | 2025-09-17 | 2025-09 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 125/2 | Unassigned | 2025-09-13 | 2025-09-18 | 2025-09 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 72/1 | Unassigned | 2025-08-12 | 2025-09-19 | 2025-09 | 39 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 56/1 | Unassigned | 2025-09-12 | 2025-09-20 | 2025-09 | 9 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 136/0 | Unassigned | 2025-09-03 | 2025-09-21 | 2025-09 | 19 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 132/4 | Unassigned | 2025-09-04 | 2025-09-25 | 2025-09 | 22 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 48/0 | Unassigned | 2025-09-21 | 2025-09-25 | 2025-09 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 123/0 | Unassigned | 2025-09-22 | 2025-09-30 | 2025-09 | 9 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 133/0 | Unassigned | 2025-09-11 | 2025-09-30 | 2025-09 | 20 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 152/0 | Unassigned | 2025-09-17 | 2025-09-30 | 2025-09 | 14 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 153A/0 | Unassigned | 2025-09-22 | 2025-09-30 | 2025-09 | 9 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 135/2 | Unassigned | 2025-10-01 | 2025-10-11 | 2025-10 | 11 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 149B/3 | Unassigned | 2025-10-01 | 2025-10-13 | 2025-10 | 13 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 135/3 | Unassigned | 2025-10-10 | 2025-10-16 | 2025-10 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 73/1 | Unassigned | 2025-10-04 | 2025-10-16 | 2025-10 | 13 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 84/0 | Unassigned | 2025-10-10 | 2025-10-19 | 2025-10 | 10 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 150/0 | Unassigned | 2025-10-14 | 2025-10-29 | 2025-10 | 16 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 71/2 | Unassigned | 2025-10-16 | 2025-10-30 | 2025-10 | 15 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 134A/3 | Unassigned | 2025-10-27 | 2025-10-31 | 2025-10 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 148/0 | Unassigned | 2025-10-16 | 2025-11-04 | 2025-11 | 20 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 71/3 | Unassigned | 2025-10-29 | 2025-11-07 | 2025-11 | 10 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 151/0 | Unassigned | 2025-10-29 | 2025-11-08 | 2025-11 | 11 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 78/1 | Unassigned | 2025-10-27 | 2025-11-08 | 2025-11 | 13 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 81/1 | Unassigned | 2025-10-29 | 2025-11-10 | 2025-11 | 13 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 140/1 | Unassigned | 2025-11-06 | 2025-11-11 | 2025-11 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 89/0 | Unassigned | 2025-11-04 | 2025-11-12 | 2025-11 | 9 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 71/0 | Unassigned | 2025-11-08 | 2025-11-14 | 2025-11 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 113/0 | Unassigned | 2025-10-31 | 2025-11-16 | 2025-11 | 17 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 139/1 | Unassigned | 2025-11-11 | 2025-11-16 | 2025-11 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 72/0 | Unassigned | 2025-09-26 | 2025-11-17 | 2025-11 | 53 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 89/1 | Unassigned | 2025-11-13 | 2025-11-18 | 2025-11 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 140/0 | Unassigned | 2025-11-14 | 2025-11-22 | 2025-11 | 9 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 154/0 | Unassigned | 2025-11-03 | 2025-11-22 | 2025-11 | 20 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 90/0 | Unassigned | 2025-11-12 | 2025-11-22 | 2025-11 | 11 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 90/1 | Unassigned | 2025-11-18 | 2025-11-26 | 2025-11 | 9 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 127/1 | Unassigned | 2025-11-23 | 2025-11-28 | 2025-11 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 153/0 | Unassigned | 2025-11-20 | 2025-11-30 | 2025-11 | 11 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 66/0 | Unassigned | 2025-11-15 | 2025-11-30 | 2025-11 | 16 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 118/0 | Unassigned | 2025-12-01 | 2025-12-05 | 2025-12 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 88/0 | Unassigned | 2025-11-23 | 2025-12-05 | 2025-12 | 13 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 130/1 | Unassigned | 2025-11-27 | 2025-12-06 | 2025-12 | 10 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 98B/2 | Unassigned | 2025-11-29 | 2025-12-08 | 2025-12 | 10 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 117/0 | Unassigned | 2025-12-07 | 2025-12-13 | 2025-12 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 128/1 | Unassigned | 2025-12-06 | 2025-12-14 | 2025-12 | 9 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 117/1 | Unassigned | 2025-12-15 | 2025-12-19 | 2025-12 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 132/2 | Unassigned | 2025-12-14 | 2025-12-20 | 2025-12 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 91/0 | Unassigned | 2025-12-14 | 2025-12-24 | 2025-12 | 11 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 132/0 | Unassigned | 2025-12-18 | 2025-12-28 | 2025-12 | 11 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 104A/0 | Unassigned | 2025-12-21 | 2025-12-30 | 2025-12 | 10 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 124/0 | Unassigned | 2025-12-22 | 2025-12-30 | 2025-12 | 9 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 91/3 | Unassigned | 2025-12-27 | 2025-12-31 | 2025-12 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 104B/0 | Unassigned | 2025-12-26 | 2026-01-04 | 2026-01 | 10 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 65/0 | Unassigned | 2025-12-27 | 2026-01-07 | 2026-01 | 12 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 122/2 | Unassigned | 2026-01-02 | 2026-01-08 | 2026-01 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 126/3 | Unassigned | 2026-01-05 | 2026-01-15 | 2026-01 | 11 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 65/1 | Unassigned | 2026-01-08 | 2026-01-15 | 2026-01 | 8 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 69/3 | Unassigned | 2026-01-05 | 2026-01-15 | 2026-01 | 11 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 108/0 | Unassigned | 2026-01-15 | 2026-01-20 | 2026-01 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 10/3 | Unassigned | 2026-01-20 | 2026-01-23 | 2026-01 | 4 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 109/0 | Unassigned | 2026-01-18 | 2026-01-23 | 2026-01 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 120/0 | Unassigned | 2026-01-21 | 2026-01-25 | 2026-01 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 10/5 | Unassigned | 2026-01-25 | 2026-01-26 | 2026-01 | 2 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 10/6 | Unassigned | 2026-01-27 | 2026-01-28 | 2026-01 | 2 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 92/0 | Unassigned | 2026-01-24 | 2026-01-28 | 2026-01 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 10/7 | Unassigned | 2026-01-28 | 2026-01-30 | 2026-01 | 3 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 93/0 | Unassigned | 2026-01-25 | 2026-01-30 | 2026-01 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 7/7 | Unassigned | 2026-02-02 | 2026-02-04 | 2026-02 | 3 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 7/9 | Unassigned | 2026-02-02 | 2026-02-06 | 2026-02 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 7/0 | Unassigned | 2026-02-06 | 2026-02-11 | 2026-02 | 6 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 10/12 | Unassigned | 2026-02-08 | 2026-02-12 | 2026-02 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 1/1 | Unassigned | 2026-02-11 | 2026-02-14 | 2026-02 | 4 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 6/2 | Unassigned | 2026-02-12 | 2026-02-16 | 2026-02 | 5 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 1/2 | Unassigned | 2026-02-15 | 2026-02-18 | 2026-02 | 4 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 6/1 | Unassigned | 2026-02-17 | 2026-02-20 | 2026-02 | 4 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 1/0 | Unassigned | 2026-02-11 | 2026-02-28 | 2026-02 | 18 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 6/0 | Unassigned | 2026-02-19 | 2026-02-28 | 2026-02 | 10 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 117/2 | Unassigned | 2026-02-21 | 2026-02-28 | 2026-02 | 8 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 4/0 | Unassigned | 2026-02-18 | 2026-02-28 | 2026-02 | 11 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 157/0 | Unassigned | 2026-02-16 | 2026-03-04 | 2026-03 | 17 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 156/0 | Unassigned | 2026-02-14 | 2026-03-10 | 2026-03 | 25 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 2/1 | Unassigned |  | 2026-03-11 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 98B/1 | Unassigned | 2026-02-19 | 2026-03-11 | 2026-03 | 21 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 2/0 | Unassigned | 2026-02-28 | 2026-03-13 | 2026-03 | 14 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 2/2 | Unassigned | 2026-03-12 | 2026-03-15 | 2026-03 | 4 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 2/3 | Unassigned | 2026-03-13 | 2026-03-16 | 2026-03 | 4 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 2/4 | Unassigned | 2026-03-15 | 2026-03-17 | 2026-03 | 3 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 103/0 | Unassigned | 2026-03-12 | 2026-03-19 | 2026-03 | 8 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 1/0 | Unassigned | 2026-03-10 | 2026-03-22 | 2026-03 | 13 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 10/8 | Unassigned | 2026-03-20 | 2026-03-22 | 2026-03 | 3 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 8/2 | Unassigned | 2026-03-20 | 2026-03-25 | 2026-03 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 3/0B | Unassigned | 2026-03-20 | 2026-03-26 | 2026-03 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 7/1 | Unassigned | 2026-03-24 | 2026-03-26 | 2026-03 | 3 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 2/5 | Unassigned | 2026-03-24 | 2026-03-27 | 2026-03 | 4 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 3/0A | Unassigned | 2026-03-23 | 2026-03-28 | 2026-03 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 5/2 | Unassigned | 2026-03-20 | 2026-03-31 | 2026-03 | 12 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 5/1 | Unassigned | 2026-03-31 | 2026-04-02 | 2026-04 | 3 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 3/1 | Unassigned | 2026-03-27 | 2026-04-04 | 2026-04 | 9 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 8/1 | Unassigned | 2026-04-02 | 2026-04-06 | 2026-04 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 3/1 | Unassigned | 2026-03-27 | 2026-04-07 | 2026-04 | 12 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 2/1B | Unassigned | 2026-04-03 | 2026-04-08 | 2026-04 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 2/1 A | Unassigned | 2026-03-28 | 2026-04-09 | 2026-04 | 13 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 103/1 | Unassigned | 2026-04-03 | 2026-04-10 | 2026-04 | 8 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 8/0 | Unassigned | 2026-04-06 | 2026-04-11 | 2026-04 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 5/0 | Unassigned | 2026-04-03 | 2026-04-12 | 2026-04 | 10 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 9/3 | Unassigned | 2026-04-10 | 2026-04-14 | 2026-04 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 9/4 | Unassigned | 2026-04-10 | 2026-04-15 | 2026-04 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 99C/0 | Unassigned | 2026-04-10 | 2026-04-15 | 2026-04 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 4/5 | Unassigned | 2026-04-06 | 2026-04-16 | 2026-04 | 11 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 3/3 | Unassigned | 2026-04-10 | 2026-04-18 | 2026-04 | 9 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 3/2 | Unassigned | 2026-04-05 | 2026-04-21 | 2026-04 | 17 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 9/5 | Unassigned | 2026-04-17 | 2026-04-21 | 2026-04 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 10/14 | Unassigned | 2026-04-20 | 2026-04-23 | 2026-04 | 4 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 100/0 | Unassigned | 2026-04-16 | 2026-04-24 | 2026-04 | 9 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 10/11 | Unassigned | 2026-04-26 | 2026-04-28 | 2026-04 | 3 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 3/4 | Unassigned | 2026-04-13 | 2026-04-29 | 2026-04 | 17 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 10/0 | Unassigned | 2026-04-25 | 2026-05-02 | 2026-05 | 8 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 2/0 | Unassigned | 2026-04-24 | 2026-05-02 | 2026-05 | 9 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 10/2 | Unassigned | 2026-04-24 | 2026-05-03 | 2026-05 | 10 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 155/0 | Unassigned | 2026-04-22 | 2026-05-03 | 2026-05 | 12 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 9/2 | Unassigned | 2026-04-30 | 2026-05-03 | 2026-05 | 4 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 3/5 | Unassigned | 2026-04-17 | 2026-05-05 | 2026-05 | 19 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 7/0 | Unassigned | 2026-03-20 | 2026-05-06 | 2026-05 | 48 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 154/1B | Unassigned | 2026-04-23 | 2026-05-06 | 2026-05 | 14 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 4/2 | Unassigned | 2026-05-05 | 2026-05-08 | 2026-05 | 4 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 10/13 | Unassigned | 2026-05-05 | 2026-05-08 | 2026-05 | 4 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 154/2B | Unassigned | 2026-04-24 | 2026-05-08 | 2026-05 | 15 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 154/1A | Unassigned | 2026-04-18 | 2026-05-09 | 2026-05 | 22 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 154/2A | Unassigned | 2026-04-18 | 2026-05-09 | 2026-05 | 22 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 4/4 | Unassigned | 2026-04-10 | 2026-05-10 | 2026-05 | 31 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 7/6 | Unassigned | 2026-05-08 | 2026-05-11 | 2026-05 | 4 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 13/2 | Unassigned | 2026-05-05 | 2026-05-14 | 2026-05 | 10 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 4/0 | Unassigned | 2026-05-05 | 2026-05-15 | 2026-05 | 11 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 7/8 | Unassigned | 2026-05-11 | 2026-05-16 | 2026-05 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 8/3 | Unassigned | 2026-05-16 | 2026-05-17 | 2026-05 | 2 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 4/1 | Unassigned | 2026-05-05 | 2026-05-18 | 2026-05 | 14 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 4/0 | Unassigned | 2026-04-21 | 2026-05-19 | 2026-05 | 29 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 4/3 | Unassigned | 2026-05-05 | 2026-05-19 | 2026-05 | 15 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 8/4 | Unassigned | 2026-05-17 | 2026-05-19 | 2026-05 | 3 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 4/1 | Unassigned | 2026-05-17 | 2026-05-21 | 2026-05 | 5 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 4/2 | Unassigned | 2026-05-14 | 2026-05-24 | 2026-05 | 11 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 4/3 | Unassigned | 2026-05-15 | 2026-05-27 | 2026-05 | 13 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 1/0 | Unassigned | 2026-05-25 | 2026-05-27 | 2026-05 | 3 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 27/0 | Unassigned | 2026-05-15 | 2026-05-27 | 2026-05 | 13 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 1A/0 | Unassigned | 2026-05-26 | 2026-05-30 | 2026-05 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 10/10 | Unassigned | 2026-05-09 | 2026-05-31 | 2026-05 | 23 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 7/2 | Unassigned | 2026-05-27 | 2026-06-01 | 2026-06 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 5/3 | Unassigned | 2026-05-30 | 2026-06-03 | 2026-06 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 3A/0 | Unassigned | 2026-05-21 | 2026-06-05 | 2026-06 | 16 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 5/4 | Unassigned | 2026-05-29 | 2026-06-05 | 2026-06 | 8 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 9/0 | Unassigned | 2026-06-01 | 2026-06-05 | 2026-06 | 5 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 10/1 | Unassigned | 2026-06-04 | 2026-06-09 | 2026-06 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 5/5 | Unassigned | 2026-06-04 | 2026-06-09 | 2026-06 | 6 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507765KV | TB507 | 765kV | 3B/0 | Unassigned | 2026-06-01 | 2026-06-15 | 2026-06 | 15 | Valid | detail | detail_date | TB 507 - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 10/4 | Unassigned | 2026-06-13 | 2026-06-15 | 2026-06 | 3 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 507MAIN | TB507 | MAIN | 5/0 | Unassigned | 2026-06-09 | 2026-06-15 | 2026-06 | 7 | Valid | detail | detail_date | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | Foundation
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 29/5 | Unassigned |  | 2025-08-11 | 2025-08 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 29/4 | Unassigned |  | 2025-09-06 | 2025-09 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 27/0 | Unassigned |  | 2025-09-20 | 2025-09 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 29/3 | Unassigned |  | 2025-09-24 | 2025-09 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 29/1 | Unassigned |  | 2025-10-10 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 18/0 | Unassigned |  | 2025-10-16 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 29/6 | Unassigned |  | 2025-10-16 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 117/1 | Unassigned |  | 2025-10-20 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 71/3 | Unassigned |  | 2025-10-23 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 92/3 | Unassigned |  | 2025-10-27 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 22/1 | Unassigned |  | 2025-10-28 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 72/2 | Unassigned |  | 2025-10-28 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 92/2 | Unassigned |  | 2025-10-28 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 117/3 | Unassigned |  | 2025-10-29 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 31/1 | Unassigned |  | 2025-10-30 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 21/1 | Unassigned |  | 2025-10-31 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 22/0 | Unassigned |  | 2025-10-31 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 89/1 | Unassigned |  | 2025-10-31 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 93/1 | Unassigned |  | 2025-10-31 | 2025-10 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 117/2 | Unassigned |  | 2025-11-04 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 93/2 | Unassigned |  | 2025-11-04 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 118/1 | Unassigned |  | 2025-11-06 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 74/0 | Unassigned |  | 2025-11-06 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 95/2 | Unassigned |  | 2025-11-08 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 72/0 | Unassigned |  | 2025-11-09 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 23/1 | Unassigned |  | 2025-11-10 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 92/1 | Unassigned |  | 2025-11-10 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 95/3 | Unassigned |  | 2025-11-10 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 31/3 | Unassigned |  | 2025-11-11 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 97/2 | Unassigned |  | 2025-11-12 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 22/2 | Unassigned |  | 2025-11-13 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 97/1 | Unassigned |  | 2025-11-13 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 76/2 | Unassigned |  | 2025-11-14 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 131/1 | Unassigned |  | 2025-11-15 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 95/1 | Unassigned |  | 2025-11-15 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP118 | Unassigned |  | 2025-11-16 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 15/1 | Unassigned |  | 2025-11-17 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 76/1 | Unassigned |  | 2025-11-18 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 15/2 | Unassigned |  | 2025-11-19 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 131/3 | Unassigned |  | 2025-11-19 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP93 | Unassigned |  | 2025-11-19 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 95/4 | Unassigned |  | 2025-11-20 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 97/3 | Unassigned |  | 2025-11-20 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP90 | Unassigned |  | 2025-11-22 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 17/0 | Unassigned |  | 2025-11-23 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 27/1 | Unassigned |  | 2025-11-23 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 30/3 | Unassigned |  | 2025-11-24 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 131/2 | Unassigned |  | 2025-11-24 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP98 | Unassigned |  | 2025-11-24 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP32 | Unassigned |  | 2025-11-26 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 98/1 | Unassigned |  | 2025-11-26 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP94 | Unassigned |  | 2025-11-27 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 103/1 | Unassigned |  | 2025-11-28 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 30/5 | Unassigned |  | 2025-11-29 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP96 | Unassigned |  | 2025-11-29 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 20/0 | Unassigned |  | 2025-11-30 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 40/1 | Unassigned |  | 2025-11-30 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 131/4 | Unassigned |  | 2025-11-30 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP116 | Unassigned |  | 2025-11-30 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP87 | Unassigned |  | 2025-11-30 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP99 | Unassigned |  | 2025-11-30 | 2025-11 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP75 | Unassigned |  | 2025-12-01 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 40/0 | Unassigned |  | 2025-12-03 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP28 | Unassigned |  | 2025-12-04 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 104/1 | Unassigned |  | 2025-12-04 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 82/2 | Unassigned |  | 2025-12-05 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 18/1 | Unassigned |  | 2025-12-06 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 76/3 | Unassigned |  | 2025-12-06 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 99/1 | Unassigned |  | 2025-12-06 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP100 | Unassigned |  | 2025-12-07 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP95 | Unassigned |  | 2025-12-07 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 23/0 | Unassigned |  | 2025-12-09 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP117 | Unassigned |  | 2025-12-09 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 29/0 | Unassigned |  | 2025-12-10 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 77/2 | Unassigned |  | 2025-12-10 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 82/1 | Unassigned |  | 2025-12-10 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 30/2 | Unassigned |  | 2025-12-12 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 19/2 | Unassigned |  | 2025-12-13 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 39/2 | Unassigned |  | 2025-12-13 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP104 | Unassigned |  | 2025-12-13 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP77 | Unassigned |  | 2025-12-13 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP106 | Unassigned |  | 2025-12-15 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 77/1 | Unassigned |  | 2025-12-16 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 85/1 | Unassigned |  | 2025-12-16 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP135 | Unassigned |  | 2025-12-16 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 106/1 | Unassigned |  | 2025-12-17 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 130/2 | Unassigned |  | 2025-12-17 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 102/1 | Unassigned |  | 2025-12-18 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP103 | Unassigned |  | 2025-12-18 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 30/4 | Unassigned |  | 2025-12-19 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 136/1 | Unassigned |  | 2025-12-19 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 116/1 | Unassigned |  | 2025-12-20 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 130/1 | Unassigned |  | 2025-12-20 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 23/5 | Unassigned |  | 2025-12-21 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 135/2 | Unassigned |  | 2025-12-21 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP45 | Unassigned |  | 2025-12-23 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP19 | Unassigned |  | 2025-12-24 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 131/6 | Unassigned |  | 2025-12-24 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 139/1 | Unassigned |  | 2025-12-24 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP85 | Unassigned |  | 2025-12-24 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 46/1 | Unassigned |  | 2025-12-25 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP43 | Unassigned |  | 2025-12-25 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP80 | Unassigned |  | 2025-12-25 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 138/1 | Unassigned |  | 2025-12-26 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 156/4 | Unassigned |  | 2025-12-26 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 31/2 | Unassigned |  | 2025-12-27 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 131/5 | Unassigned |  | 2025-12-27 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 150/1 | Unassigned |  | 2025-12-27 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 137/1 | Unassigned |  | 2025-12-28 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 135/1 | Unassigned |  | 2025-12-29 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP102 | Unassigned |  | 2025-12-29 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 156/3 | Unassigned |  | 2025-12-30 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 80/1 | Unassigned |  | 2025-12-30 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 86/1 | Unassigned |  | 2025-12-30 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 23/4 | Unassigned |  | 2025-12-31 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP33 | Unassigned |  | 2025-12-31 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 132/1 | Unassigned |  | 2025-12-31 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 138/2 | Unassigned |  | 2025-12-31 | 2025-12 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 43/1 | Unassigned |  | 2026-01-04 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 150/2 | Unassigned |  | 2026-01-04 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP146 | Unassigned |  | 2026-01-05 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 69/3 | Unassigned |  | 2026-01-07 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 18/2 | Unassigned |  | 2026-01-08 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP26 | Unassigned |  | 2026-01-08 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 156/2 | Unassigned |  | 2026-01-08 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 31/4 | Unassigned |  | 2026-01-09 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 46/3 | Unassigned |  | 2026-01-09 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 155/1 | Unassigned |  | 2026-01-09 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 137/2 | Unassigned |  | 2026-01-10 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 152/1 | Unassigned |  | 2026-01-11 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 90/1 | Unassigned |  | 2026-01-11 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP131 | Unassigned |  | 2026-01-11 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 43/2 | Unassigned |  | 2026-01-12 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 87/2 | Unassigned |  | 2026-01-12 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 152/2 | Unassigned |  | 2026-01-16 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 90/2 | Unassigned |  | 2026-01-16 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP147 | Unassigned |  | 2026-01-16 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP157 | Unassigned |  | 2026-01-17 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP31 | Unassigned |  | 2026-01-18 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP154 | Unassigned |  | 2026-01-18 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 19/1 | Unassigned |  | 2026-01-20 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 145/2 | Unassigned |  | 2026-01-20 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP129 | Unassigned |  | 2026-01-20 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP138 | Unassigned |  | 2026-01-20 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 25/2 | Unassigned |  | 2026-01-21 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 44/3 | Unassigned |  | 2026-01-21 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 45/2 | Unassigned |  | 2026-01-21 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 71/2 | Unassigned |  | 2026-01-21 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 31/5 | Unassigned |  | 2026-01-22 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 156/1 | Unassigned |  | 2026-01-22 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 69/2 | Unassigned |  | 2026-01-22 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP115 | Unassigned |  | 2026-01-22 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP16 | Unassigned |  | 2026-01-25 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 69/1 | Unassigned |  | 2026-01-27 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 32/1 | Unassigned |  | 2026-01-30 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 155/2 | Unassigned |  | 2026-01-30 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP30 | Unassigned |  | 2026-01-31 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 115/1 | Unassigned |  | 2026-01-31 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 151/1 | Unassigned |  | 2026-01-31 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 155/3 | Unassigned |  | 2026-01-31 | 2026-01 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 45/1 | Unassigned |  | 2026-02-05 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 153/0 | Unassigned |  | 2026-02-05 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP139 | Unassigned |  | 2026-02-06 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 44/2 | Unassigned |  | 2026-02-07 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 151/2 | Unassigned |  | 2026-02-07 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP15 | Unassigned |  | 2026-02-08 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP97 | Unassigned |  | 2026-02-08 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP155 | Unassigned |  | 2026-02-09 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 136/2 | Unassigned |  | 2026-02-11 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 152/4 | Unassigned |  | 2026-02-12 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP130 | Unassigned |  | 2026-02-12 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 25/1 | Unassigned |  | 2026-02-13 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 153/1 | Unassigned |  | 2026-02-13 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP92 | Unassigned |  | 2026-02-13 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 50A/7 | Unassigned |  | 2026-02-14 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP156 | Unassigned |  | 2026-02-14 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 136/3 | Unassigned |  | 2026-02-15 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 157/1 | Unassigned |  | 2026-02-15 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 72/1 | Unassigned |  | 2026-02-17 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 153/2 | Unassigned |  | 2026-02-18 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP150 | Unassigned |  | 2026-02-18 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP70 | Unassigned |  | 2026-02-18 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP111 | Unassigned |  | 2026-02-19 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP12 | Unassigned |  | 2026-02-20 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP44 | Unassigned |  | 2026-02-20 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP46 | Unassigned |  | 2026-02-20 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 136/4 | Unassigned |  | 2026-02-20 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 70/2 | Unassigned |  | 2026-02-21 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP68 | Unassigned |  | 2026-02-21 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP132 | Unassigned |  | 2026-02-24 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 50A/8 | Unassigned |  | 2026-02-25 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP25 | Unassigned |  | 2026-02-25 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP79 | Unassigned |  | 2026-02-25 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 67/3 | Unassigned |  | 2026-02-26 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 70/1 | Unassigned |  | 2026-02-26 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 44/1 | Unassigned |  | 2026-02-27 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP21 | Unassigned |  | 2026-02-27 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP137 | Unassigned |  | 2026-02-27 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP91 | Unassigned |  | 2026-02-27 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 145/1 | Unassigned |  | 2026-02-28 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP114 | Unassigned |  | 2026-02-28 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP159 | Unassigned |  | 2026-02-28 | 2026-02 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP69 | Unassigned |  | 2026-03-02 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 46/5 | Unassigned |  | 2026-03-05 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 50A/3 | Unassigned |  | 2026-03-06 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 29/2 | Unassigned |  | 2026-03-07 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 43/3 | Unassigned |  | 2026-03-08 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP14 | Unassigned |  | 2026-03-08 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 33/2 | Unassigned |  | 2026-03-09 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP149 | Unassigned |  | 2026-03-10 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 46/4 | Unassigned |  | 2026-03-11 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 67/2 | Unassigned |  | 2026-03-13 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP24 | Unassigned |  | 2026-03-15 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP127 | Unassigned |  | 2026-03-15 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP148 | Unassigned |  | 2026-03-16 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP136 | Unassigned |  | 2026-03-18 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 67/1 | Unassigned |  | 2026-03-19 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 43/4 | Unassigned |  | 2026-03-21 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP71 | Unassigned |  | 2026-03-23 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP145 | Unassigned |  | 2026-03-25 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP152 | Unassigned |  | 2026-03-26 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 46/2 | Unassigned |  | 2026-03-28 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP108 | Unassigned |  | 2026-03-28 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 15/3 | Unassigned |  | 2026-03-30 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 38/1 | Unassigned |  | 2026-03-30 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP124 | Unassigned |  | 2026-03-30 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP67 | Unassigned |  | 2026-03-30 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 42/3 | Unassigned |  | 2026-03-31 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 152/3 | Unassigned |  | 2026-03-31 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 56/3 | Unassigned |  | 2026-03-31 | 2026-03 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 47/1 | Unassigned |  | 2026-04-05 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 144/4 | Unassigned |  | 2026-04-05 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP125 | Unassigned |  | 2026-04-06 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 144/3 | Unassigned |  | 2026-04-07 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 65/2 | Unassigned |  | 2026-04-07 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP109 | Unassigned |  | 2026-04-12 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 40/2 | Unassigned |  | 2026-04-13 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP126 | Unassigned |  | 2026-04-15 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 42/2 | Unassigned |  | 2026-04-16 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP1 | Unassigned |  | 2026-04-18 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP61 | Unassigned |  | 2026-04-21 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP165 | Unassigned |  | 2026-04-22 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP86 | Unassigned |  | 2026-04-23 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP34 | Unassigned |  | 2026-04-25 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 56/2 | Unassigned |  | 2026-04-25 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP47 | Unassigned |  | 2026-04-26 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP123 | Unassigned |  | 2026-04-26 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP59 | Unassigned |  | 2026-04-27 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 55/1 | Unassigned |  | 2026-04-28 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 37/1 | Unassigned |  | 2026-04-29 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP7 | Unassigned |  | 2026-04-29 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP142 | Unassigned |  | 2026-04-29 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP41 | Unassigned |  | 2026-04-30 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP6 | Unassigned |  | 2026-04-30 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 122/1 | Unassigned |  | 2026-04-30 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP166 | Unassigned |  | 2026-04-30 | 2026-04 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP64 | Unassigned |  | 2026-05-01 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 33/1 | Unassigned |  | 2026-05-07 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 64/1 | Unassigned |  | 2026-05-07 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP144 | Unassigned |  | 2026-05-07 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP56 | Unassigned |  | 2026-05-07 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 142/1 | Unassigned |  | 2026-05-08 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 61/1 | Unassigned |  | 2026-05-08 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP82 | Unassigned |  | 2026-05-08 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 57/1 | Unassigned |  | 2026-05-09 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP161 | Unassigned |  | 2026-05-09 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP163 | Unassigned |  | 2026-05-11 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 56/4 | Unassigned |  | 2026-05-13 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP38 | Unassigned |  | 2026-05-14 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 62/2 | Unassigned |  | 2026-05-14 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 71/1 | Unassigned |  | 2026-05-14 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP110 | Unassigned |  | 2026-05-14 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP57 | Unassigned |  | 2026-05-15 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 40/3 | Unassigned |  | 2026-05-16 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 159/3 | Unassigned |  | 2026-05-16 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 65/4 | Unassigned |  | 2026-05-16 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 50A/2 | Unassigned |  | 2026-05-17 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP162 | Unassigned |  | 2026-05-17 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP60 | Unassigned |  | 2026-05-17 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 62/1 | Unassigned |  | 2026-05-18 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP128 | Unassigned |  | 2026-05-18 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP143 | Unassigned |  | 2026-05-18 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP63 | Unassigned |  | 2026-05-18 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 23/2 | Unassigned |  | 2026-05-19 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 159/2 | Unassigned |  | 2026-05-19 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 57/2 | Unassigned |  | 2026-05-19 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP112 | Unassigned |  | 2026-05-19 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP70/3 | Unassigned |  | 2026-05-19 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 159/1 | Unassigned |  | 2026-05-22 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 60/1 | Unassigned |  | 2026-05-22 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 50A/1 | Unassigned |  | 2026-05-23 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 143/1 | Unassigned |  | 2026-05-23 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP113 | Unassigned |  | 2026-05-23 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP158 | Unassigned |  | 2026-05-23 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605LILO | TB605 | LILO | AP7 | Unassigned |  | 2026-05-24 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | LILO
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP84 | Unassigned |  | 2026-05-24 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 39/1 | Unassigned |  | 2026-05-25 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP39 | Unassigned |  | 2026-05-25 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP55 | Unassigned |  | 2026-05-25 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP42 | Unassigned |  | 2026-05-26 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 59/1 | Unassigned |  | 2026-05-26 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP66 | Unassigned |  | 2026-05-26 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 34/1 | Unassigned |  | 2026-05-28 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 65/1 | Unassigned |  | 2026-05-28 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP65 | Unassigned |  | 2026-05-28 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 65/5 | Unassigned |  | 2026-05-30 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP105 | Unassigned |  | 2026-05-30 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP168 | Unassigned |  | 2026-05-30 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP174 | Unassigned |  | 2026-05-30 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP167 | Unassigned |  | 2026-05-31 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP81 | Unassigned |  | 2026-05-31 | 2026-05 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 35/1 | Unassigned |  | 2026-06-03 | 2026-06 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP35 | Unassigned |  | 2026-06-03 | 2026-06 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 65/3 | Unassigned |  | 2026-06-03 | 2026-06 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 144/1 | Unassigned |  | 2026-06-04 | 2026-06 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP54 | Unassigned |  | 2026-06-05 | 2026-06 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP76 | Unassigned |  | 2026-06-05 | 2026-06 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP89 | Unassigned |  | 2026-06-05 | 2026-06 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 50A/4 | Unassigned |  | 2026-06-06 | 2026-06 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP173 | Unassigned |  | 2026-06-06 | 2026-06 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP58 | Unassigned |  | 2026-06-06 | 2026-06 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 23/3 | Unassigned |  | 2026-06-09 | 2026-06 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 42/1 | Unassigned |  | 2026-06-09 | 2026-06 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | AP36 | Unassigned |  | 2026-06-09 | 2026-06 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 143/2 | Unassigned |  | 2026-06-09 | 2026-06 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP88 | Unassigned |  | 2026-06-09 | 2026-06 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP175 | Unassigned |  | 2026-06-10 | 2026-06 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | AP78 | Unassigned |  | 2026-06-10 | 2026-06 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 144/2 | Unassigned |  | 2026-06-12 | 2026-06 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605PUNJAB | TB605 | Punjab | 77/3 | Unassigned |  | 2026-06-12 | 2026-06 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation -JS Line- Punjab
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 37/2 | Unassigned |  | 2026-06-14 | 2026-06 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 605JAMMU | TB605 | Jammu | 47/3 | Unassigned |  | 2026-06-15 | 2026-06 |  | Missing Start Date | detail | detail_date | TB 605 - DPR - 2026-06-16.xlsx | Foundation JS-Line -Jammu
Mr. NK Gupta | TB 608 | TB608 |  | 65/3 | Unassigned | 2025-10-07 | 2025-10-18 | 2025-10 | 12 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 69/2 | Unassigned | 2025-10-06 | 2025-10-18 | 2025-10 | 13 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 131/2 | Unassigned | 2025-10-15 | 2025-11-09 | 2025-11 | 26 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 58/1 | Unassigned | 2025-10-21 | 2025-11-10 | 2025-11 | 21 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 69/0 | Unassigned | 2025-10-26 | 2025-11-10 | 2025-11 | 16 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 58/0 | Unassigned | 2025-10-17 | 2025-11-11 | 2025-11 | 26 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 75/5 | Unassigned | 2025-10-23 | 2025-11-15 | 2025-11 | 24 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 34/3 | Unassigned | 2025-11-01 | 2025-11-18 | 2025-11 | 18 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 101/0 | Unassigned | 2025-10-26 | 2025-11-19 | 2025-11 | 25 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 71/1 | Unassigned | 2025-11-12 | 2025-11-20 | 2025-11 | 9 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 33/2 | Unassigned | 2025-11-01 | 2025-11-22 | 2025-11 | 22 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 90/0 | Unassigned | 2025-11-09 | 2025-11-22 | 2025-11 | 14 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 29/0 | Unassigned | 2025-11-15 | 2025-11-25 | 2025-11 | 11 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 40/0 | Unassigned | 2025-11-10 | 2025-11-25 | 2025-11 | 16 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 72/6 | Unassigned | 2025-11-11 | 2025-11-28 | 2025-11 | 18 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 88/0 | Unassigned | 2025-11-13 | 2025-11-28 | 2025-11 | 16 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 100/0 | Unassigned | 2025-11-19 | 2025-11-30 | 2025-11 | 12 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 103/0 | Unassigned | 2025-11-01 | 2025-11-30 | 2025-11 | 30 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 109/0 | Unassigned | 2025-11-01 | 2025-11-30 | 2025-11 | 30 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 71/0 | Unassigned | 2025-11-14 | 2025-11-30 | 2025-11 | 17 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 85/0 | Unassigned | 2025-11-11 | 2025-11-30 | 2025-11 | 20 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 89/0 | Unassigned | 2025-11-19 | 2025-11-30 | 2025-11 | 12 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 29/1 | Unassigned | 2025-11-23 | 2025-12-02 | 2025-12 | 10 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 75/3 | Unassigned | 2025-11-25 | 2025-12-03 | 2025-12 | 9 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 69/3 | Unassigned | 2025-11-27 | 2025-12-08 | 2025-12 | 12 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 5/0 | Unassigned | 2025-11-26 | 2025-12-10 | 2025-12 | 15 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 80/0 | Unassigned | 2025-11-27 | 2025-12-11 | 2025-12 | 15 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 108/0 | Unassigned | 2025-11-01 | 2025-12-12 | 2025-12 | 42 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 111/0 | Unassigned | 2025-12-03 | 2025-12-12 | 2025-12 | 10 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 29/4 | Unassigned | 2025-11-27 | 2025-12-14 | 2025-12 | 18 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 48/0 | Unassigned | 2025-11-30 | 2025-12-14 | 2025-12 | 15 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 29/3 | Unassigned | 2025-12-04 | 2025-12-17 | 2025-12 | 14 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 75/4 | Unassigned | 2025-11-27 | 2025-12-18 | 2025-12 | 22 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 99/0 | Unassigned | 2025-11-30 | 2025-12-18 | 2025-12 | 19 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 102/0 | Unassigned | 2025-12-03 | 2025-12-19 | 2025-12 | 17 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 84/0 | Unassigned | 2025-11-25 | 2025-12-19 | 2025-12 | 25 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 111/1 | Unassigned | 2025-12-12 | 2025-12-21 | 2025-12 | 10 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 83/0 | Unassigned | 2025-12-08 | 2025-12-21 | 2025-12 | 14 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 91/0 | Unassigned | 2025-11-27 | 2025-12-21 | 2025-12 | 25 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 93/0 | Unassigned | 2025-11-30 | 2025-12-21 | 2025-12 | 22 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 34/1 | Unassigned | 2025-11-23 | 2025-12-22 | 2025-12 | 30 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 25/1 | Unassigned | 2025-12-12 | 2025-12-23 | 2025-12 | 12 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 70/3 | Unassigned | 2025-12-15 | 2025-12-23 | 2025-12 | 9 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 29/2 | Unassigned | 2025-12-14 | 2025-12-25 | 2025-12 | 12 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 4/1 | Unassigned | 2025-11-14 | 2025-12-25 | 2025-12 | 42 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 112/0 | Unassigned | 2025-12-12 | 2025-12-27 | 2025-12 | 16 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 49/0 | Unassigned | 2025-12-16 | 2025-12-27 | 2025-12 | 12 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 91/1 | Unassigned | 2025-11-30 | 2025-12-27 | 2025-12 | 28 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 79/1 | Unassigned | 2025-12-20 | 2025-12-28 | 2025-12 | 9 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 91/2 | Unassigned | 2025-12-03 | 2025-12-28 | 2025-12 | 26 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 114/0 | Unassigned | 2025-12-18 | 2025-12-31 | 2025-12 | 14 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 70/2 | Unassigned | 2025-12-22 | 2025-12-31 | 2025-12 | 10 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 77/0 | Unassigned | 2025-12-18 | 2025-12-31 | 2025-12 | 14 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 86/0 | Unassigned | 2025-12-03 | 2025-12-31 | 2025-12 | 29 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 91/8 | Unassigned | 2025-12-15 | 2025-12-31 | 2025-12 | 17 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 94/0 | Unassigned | 2025-12-21 | 2025-12-31 | 2025-12 | 11 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 41/2 | Unassigned | 2025-12-22 | 2026-01-02 | 2026-01 | 12 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 11/2 | Unassigned | 2025-12-23 | 2026-01-03 | 2026-01 | 12 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 70/0 | Unassigned | 2025-12-20 | 2026-01-04 | 2026-01 | 16 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 40/1 | Unassigned | 2025-12-28 | 2026-01-07 | 2026-01 | 11 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 97/0 | Unassigned | 2025-12-19 | 2026-01-09 | 2026-01 | 22 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 41/0 | Unassigned | 2025-12-23 | 2026-01-10 | 2026-01 | 19 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 113/0 | Unassigned | 2025-12-23 | 2026-01-11 | 2026-01 | 20 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 76/3 | Unassigned | 2025-12-31 | 2026-01-11 | 2026-01 | 12 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 91/5 | Unassigned | 2025-12-28 | 2026-01-12 | 2026-01 | 16 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 110/0 | Unassigned | 2025-12-27 | 2026-01-13 | 2026-01 | 18 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 115/0 | Unassigned | 2025-12-31 | 2026-01-14 | 2026-01 | 15 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 8/0 | Unassigned | 2025-12-29 | 2026-01-14 | 2026-01 | 17 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 76/0 | Unassigned | 2025-12-22 | 2026-01-15 | 2026-01 | 25 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 69/4 | Unassigned | 2026-01-02 | 2026-01-18 | 2026-01 | 17 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 75/1 | Unassigned | 2026-01-06 | 2026-01-19 | 2026-01 | 14 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 50/0 | Unassigned | 2026-01-09 | 2026-01-21 | 2026-01 | 13 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 11/1 | Unassigned | 2026-01-14 | 2026-01-24 | 2026-01 | 11 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 123/2 | Unassigned | 2025-12-29 | 2026-01-25 | 2026-01 | 28 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 129/1 | Unassigned | 2025-10-15 | 2026-01-27 | 2026-01 | 105 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 34/2 | Unassigned | 2025-12-23 | 2026-01-27 | 2026-01 | 36 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 47/1 | Unassigned | 2026-01-15 | 2026-01-28 | 2026-01 | 14 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 79/0 | Unassigned | 2026-01-15 | 2026-01-28 | 2026-01 | 14 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 132/1 | Unassigned | 2026-01-16 | 2026-01-29 | 2026-01 | 14 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 69/1 | Unassigned | 2026-01-11 | 2026-01-29 | 2026-01 | 19 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 91/7 | Unassigned | 2025-12-31 | 2026-01-29 | 2026-01 | 30 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 96/0 | Unassigned | 2026-01-17 | 2026-01-30 | 2026-01 | 14 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 128/0 | Unassigned | 2026-01-09 | 2026-01-31 | 2026-01 | 23 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 131/0 | Unassigned | 2025-12-28 | 2026-01-31 | 2026-01 | 35 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 75/2 | Unassigned | 2026-01-19 | 2026-01-31 | 2026-01 | 13 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 91/4 | Unassigned | 2026-01-17 | 2026-01-31 | 2026-01 | 15 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 59/1 | Unassigned | 2026-01-10 | 2026-02-05 | 2026-02 | 27 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 73/6 | Unassigned | 2026-01-19 | 2026-02-05 | 2026-02 | 18 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 76/1 | Unassigned | 2026-01-18 | 2026-02-05 | 2026-02 | 19 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 81/0 | Unassigned | 2026-01-11 | 2026-02-05 | 2026-02 | 26 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 96/1 | Unassigned | 2026-01-27 | 2026-02-05 | 2026-02 | 10 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 104/0 | Unassigned | 2026-01-17 | 2026-02-08 | 2026-02 | 23 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 42/1 | Unassigned | 2026-01-31 | 2026-02-08 | 2026-02 | 9 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 126/0 | Unassigned | 2025-12-28 | 2026-02-10 | 2026-02 | 45 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 43/0 | Unassigned | 2026-01-29 | 2026-02-10 | 2026-02 | 13 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 72/7 | Unassigned | 2026-01-29 | 2026-02-11 | 2026-02 | 14 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 9/1 | Unassigned | 2026-01-28 | 2026-02-11 | 2026-02 | 15 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 78/2 | Unassigned | 2026-01-29 | 2026-02-12 | 2026-02 | 15 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 95/3 | Unassigned | 2026-02-03 | 2026-02-14 | 2026-02 | 12 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 95/1 | Unassigned | 2026-02-03 | 2026-02-16 | 2026-02 | 14 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 131/3 | Unassigned | 2026-02-03 | 2026-02-17 | 2026-02 | 15 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 129/2 | Unassigned | 2026-02-08 | 2026-02-18 | 2026-02 | 11 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 6/1 | Unassigned | 2026-02-13 | 2026-02-18 | 2026-02 | 6 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 95/0 | Unassigned | 2026-02-03 | 2026-02-18 | 2026-02 | 16 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 131/1 | Unassigned | 2026-02-03 | 2026-02-19 | 2026-02 | 17 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 44/0 | Unassigned | 2026-02-08 | 2026-02-19 | 2026-02 | 12 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 30/0 | Unassigned | 2026-02-05 | 2026-02-20 | 2026-02 | 16 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 10/3 | Unassigned | 2026-02-16 | 2026-02-22 | 2026-02 | 7 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 124/0 | Unassigned | 2026-02-03 | 2026-02-22 | 2026-02 | 20 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 71/2 | Unassigned | 2026-02-12 | 2026-02-22 | 2026-02 | 11 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 70/1 | Unassigned | 2026-02-10 | 2026-02-23 | 2026-02 | 14 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 72/0 | Unassigned | 2026-02-09 | 2026-02-23 | 2026-02 | 15 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 127/0 | Unassigned | 2026-02-03 | 2026-02-25 | 2026-02 | 23 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 132/2 | Unassigned | 2026-02-12 | 2026-02-28 | 2026-02 | 17 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 132/3 | Unassigned | 2026-02-10 | 2026-02-28 | 2026-02 | 19 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 95/2 | Unassigned | 2026-02-10 | 2026-02-28 | 2026-02 | 19 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 31/0 | Unassigned | 2026-02-18 | 2026-03-06 | 2026-03 | 17 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 35/0 | Unassigned | 2026-02-20 | 2026-03-08 | 2026-03 | 17 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 10/1 | Unassigned | 2026-03-02 | 2026-03-10 | 2026-03 | 9 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 129/0 | Unassigned | 2026-02-26 | 2026-03-10 | 2026-03 | 13 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 130/0 | Unassigned | 2026-02-20 | 2026-03-10 | 2026-03 | 19 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 82/2 | Unassigned | 2026-02-24 | 2026-03-10 | 2026-03 | 15 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 82/1 | Unassigned | 2026-02-23 | 2026-03-11 | 2026-03 | 17 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 116/0 | Unassigned | 2026-02-22 | 2026-03-12 | 2026-03 | 19 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 27/0 | Unassigned | 2026-03-08 | 2026-03-14 | 2026-03 | 7 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 5/0 | Unassigned | 2026-02-26 | 2026-03-18 | 2026-03 | 21 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 125/0 | Unassigned | 2026-02-19 | 2026-03-19 | 2026-03 | 29 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 47/0 | Unassigned | 2026-02-23 | 2026-03-28 | 2026-03 | 34 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 6/0 | Unassigned | 2026-03-27 | 2026-03-28 | 2026-03 | 2 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 132/0 | Unassigned | 2026-02-28 | 2026-03-29 | 2026-03 | 30 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 7/0 | Unassigned | 2026-03-29 | 2026-03-30 | 2026-03 | 2 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 34/0 | Unassigned | 2026-02-01 | 2026-03-31 | 2026-03 | 59 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 7/2 | Unassigned | 2026-03-24 | 2026-03-31 | 2026-03 | 8 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 8/0 | Unassigned | 2026-04-12 | 2026-04-12 | 2026-04 | 1 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 92/0 | Unassigned | 2026-03-12 | 2026-04-13 | 2026-04 | 33 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 9/0 | Unassigned | 2026-04-14 | 2026-04-14 | 2026-04 | 1 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 7/0 | Unassigned | 2026-04-16 | 2026-04-16 | 2026-04 | 1 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 107/1 | Unassigned | 2026-03-17 | 2026-04-19 | 2026-04 | 34 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 7/1 | Unassigned | 2026-03-29 | 2026-04-21 | 2026-04 | 24 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 61A/0 | Unassigned | 2026-04-06 | 2026-04-23 | 2026-04 | 18 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 106/0 | Unassigned | 2026-04-10 | 2026-04-30 | 2026-04 | 21 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 9/0 | Unassigned | 2026-04-30 | 2026-05-02 | 2026-05 | 3 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 1/0 | Unassigned | 2026-04-10 | 2026-05-06 | 2026-05 | 27 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 38/0 | Unassigned | 2026-04-06 | 2026-05-06 | 2026-05 | 31 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 61/0 | Unassigned | 2026-04-18 | 2026-05-06 | 2026-05 | 19 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 105/0 | Unassigned | 2026-04-05 | 2026-05-07 | 2026-05 | 33 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 39/0 | Unassigned | 2026-04-03 | 2026-05-12 | 2026-05 | 40 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 20/0 | Unassigned | 2026-05-08 | 2026-05-14 | 2026-05 | 7 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 3/0 | Unassigned | 2026-05-15 | 2026-05-17 | 2026-05 | 3 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 4/0 | Unassigned | 2026-05-22 | 2026-05-24 | 2026-05 | 3 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 18/0 | Unassigned | 2026-05-08 | 2026-05-26 | 2026-05 | 19 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 4/0 | Unassigned | 2026-05-24 | 2026-05-26 | 2026-05 | 3 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 5/0 | Unassigned | 2026-05-06 | 2026-05-28 | 2026-05 | 23 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 3/0 | Unassigned | 2026-05-08 | 2026-06-10 | 2026-06 | 34 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN
Mr. NK Gupta | TB 608 | TB608 |  | 70/4 | Unassigned | 2026-05-24 | 2026-06-13 | 2026-06 | 21 | Valid | detail | detail_date | TB 608 - DPR - 2026-06-14.xlsm | WIP-FDN

## Data Coverage
Section | Project | Status | Metric | Value | Reason
Input |  |  | Total rows after month filter | 5091
Input |  |  | FoundationRaw rows available | 6158
Input |  |  | Detail rows used for productivity | 5084
Input |  |  | Snapshot fallback rows excluded from productivity | 7
Data Quality |  |  | Rows with missing gang | 2877
Data Quality |  |  | Rows with missing start date | 1888
Data Quality |  |  | Rows with invalid duration | 15
Data Quality |  |  | Rows with valid duration | 3181
Coverage | TA 504 | SKIPPED_BLANK_CONFIG | Project with missing/limited foundation source |  | Foundation sheet mapping left blank in DPR_Config; project explicitly skipped.
Coverage | TA 506 | SKIPPED_BLANK_CONFIG | Project with missing/limited foundation source |  | Foundation sheet mapping left blank in DPR_Config; project explicitly skipped.
Coverage | TA 515 | MISSING | Project with missing/limited foundation source |  | No parseable foundation detail/snapshot source found.
Coverage | TB 412 | SKIPPED_BLANK_CONFIG | Project with missing/limited foundation source |  | Foundation sheet mapping left blank in DPR_Config; project explicitly skipped.