## DPR_TA-504
LINE NAME- : 765 KV D/C Rishabdeo - Mandsaur & Lilo
CLIENT-Rajasthan IVE Mewar Transmission Limited (POWER GRID CORPORATION OF INDIA)
DAILY PROGRESS REPORT (TA-504)
NOA Date :- 15-July-2024 |  |  |  | Completion Date :- 14-June-2026 |  |  |  |  | Date:- 24 March 2026
SUPPLY VALUE = 212.95 Cr. |  |  |  | SERVICE VALUE = 37.28 Cr. |  |  |  |  | F&I VALUE = 5.26 Cr.
PARTICULARS | UOM | Total | Comp | Balance | 2026-03-01 |  | WIP | Cumulative | 2026-04-01 | 2026-05-02 | Remarks
|  | Qty | Till | as on | Plan | Actual |  |  | Plan | Plan
|  |  | 2026-02-01 | 1 March'26
Detail Survey | KM | 74 | 62 | 12 | 12 |  | 12 | 62
Check Survey | KM | 74 | 54 | 20 | 20 |  | 8 | 54
Stub Supply | SET | 196 | 205 | -9 |  |  |  | 205
FOUNDATION | NOS | 196 | 135 | 61 | 6 | 2 | 1 | 137 | 25 | 15 | Plan depends on hold Route clearance From Dec onwards
No of Gangs | [6 empty] | 1 | 0
Tower Supply | SETS | 196 | 168 | 28 |  |  |  | 168
TOWER ERECTION | NOS | 196 | 119 | 77 | 4 |  | 1 | 119 | 25 | 20
No of Gangs | [6 empty] | 1 | 0
AL-59 Zebra Conductor | KM | 2272 | 1424 | 848 |  |  |  | 1424
G S Earthwire 7/3.66mm size | KM | 75 | 42 | 33 |  |  |  | 42
Insulator Supply | EA | 7004 | 5685 | 1319 |  |  |  | 5685
Hardware Fittings Supply | % | 100% | 55% | 45% |  |  |  | 55%
Stringing | KM | 74 | 9 | 65 | 7 |  | 3 | 9 | 15 | 20
TSE - Section | No | 47 | 5 | 42 |  |  |  | 5
Manual - Section | No | 7 |  | 7 |  |  |  | 0
No of Gangs |  |  |  |  | 1 |  | 1 |  | 2 | 3
OPGW Stringing | KM | 74 |  | 74 |  |  |  | 0
No of Gangs

## Erection compiled
KEC International Limited
TA-504 - 765 KV D/C Rishabdeo - Mandsaur & Lilo
Details of Erection | [6 empty] | 3384.8591 | 356.7642 |  | 2026-03-24
CUMM. SR.NO | MONTH SR.NO. | Location No | Type of Tower | Starting Date | Completion date | Gang name | Tower Weight | Revenue | Name of Supervisor | Status | Prop. Name
1 |  | 11/0 | DB2+0 | 2025-09-03 | 2025-09-22 | Sainik Traders | 59.5006 | 6.2714 | Teklal Mahto | Completed
2 |  | 11/1 | DA+0 | 2025-07-21 | 2025-07-30 | Sainik Traders | 36.1598 | 3.8112 | Teklal Mahto | Completed
3 |  | 11/2 | DA+0 | 2025-08-01 | 2025-08-13 | Sainik Traders | 36.1598 | 3.8112 | Teklal Mahto | Completed
4 |  | 11/3 | DA+3 | 2025-08-14 | 2025-08-31 | Sainik Traders | 37.9311 | 3.9979 | Teklal Mahto | Completed
5 |  | 11/4 | DA+0 | 2025-07-07 | 2025-07-21 | Sainik Traders | 36.1598 | 3.8112 | Teklal Mahto | Completed
6 |  | 12/0 | DB2+0 | 2025-09-22 | 2025-10-08 | Sainik Traders | 59.5006 | 6.2714 | Teklal Mahto | Completed
7 |  | 12/1 | DA-3 | 2025-06-16 | 2025-06-20 | pankaj-2 | 34.7898 | 3.6668 | Teklal Mahto | Completed
8 |  | 12/2 | DA+0 | 2025-06-11 | 2025-06-15 | pankaj-2 | 36.1598 | 3.8112 | Teklal Mahto | Completed
9 |  | 12/3 | DA+0 | 2025-05-27 | 2025-06-03 | pankaj-2 | 36.1598 | 3.8112 | Teklal Mahto | Completed
10 |  | 12/4 | DA+6 | 2025-05-17 | 2025-05-26 | pankaj-2 | 43.8044 | 4.617 | Rameshwar Mahto | Completed
11 |  | 12/5 | DA+6 | 2025-06-04 | 2025-06-10 | pankaj-2 | 43.8044 | 4.617 | Teklal Mahto | Completed
12 |  | 13/1 | DA+0 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 3.8112 | Teklal Mahto | Completed
13 |  | 13/5 | DA+3 | 2025-01-28 | 2025-02-01 | Pankaj-2 | 37.9311 | 3.9979 | Rameshwar Mahto | Completed
14 |  | 13/6 | DA+3 | 2025-02-02 | 2025-02-05 | Pankaj-2 | 37.9311 | 3.9979 | Rameshwar Mahto | Completed
15 |  | 14/2 | DA+0 | 2025-01-19 | 2025-01-23 | Pankaj-2 | 36.1598 | 3.8112 | Rameshwar Mahto | Completed
16 |  | 14/3 | DA+0 | 2025-01-24 | 2025-01-27 | Pankaj-2 | 36.1598 | 3.8112 | Rameshwar Mahto | Completed
17 |  | 14/4 | DA+0 | 2025-04-30 | 2025-05-07 | Pankaj-2 | 36.1598 | 3.8112 | Rameshwar Mahto | Completed
18 |  | 14/5 | DA+3 | 2025-05-08 | 2025-05-16 | Pankaj-2 | 37.9311 | 3.9979 | Rameshwar Mahto | Completed
19 |  | 14/6 | DA+0 | 2025-02-06 | 2025-02-10 | Pankaj-2 | 36.1598 | 3.8112 | Rameshwar Mahto | Completed
20 |  | 14/7 | DA+3 | 2025-02-11 | 2025-02-15 | Pankaj-2 | 37.9311 | 3.9979 | Rameshwar Mahto | Completed
21 |  | 15/2 | DA+3 | 2025-02-16 | 2025-02-19 | Pankaj-2 | 37.9311 | 3.9979 | Rameshwar Mahto | Completed
22 |  | 15/3 | DA+0 | 2025-02-20 | 2025-02-23 | Pankaj-2 | 36.1598 | 3.8112 | Rameshwar Mahto | Completed
23 |  | 15/4 | DA+3 | 2025-03-01 | 2025-03-04 | Pankaj-2 | 37.9311 | 3.9979 | Rameshwar Mahto | Completed
24 |  | 15/5 | DA-3 | 2025-03-05 | 2025-03-08 | Pankaj-2 | 34.7898 | 3.6668 | Rameshwar Mahto | Completed
25 |  | 15/6 | DA+3 | 2025-02-24 | 2025-02-28 | Pankaj-2 | 37.9311 | 3.9979 | Rameshwar Mahto | Completed
26 |  | 15/7 | DA+6 | 2025-04-24 | 2025-04-29 | Pankaj-2 | 43.8044 | 4.617 | Rameshwar Mahto | Completed
27 |  | 16/1 | DA+6 | 2025-03-23 | 2025-03-27 | Pankaj-2 | 43.8044 | 4.617 | Rameshwar Mahto | Completed
28 |  | 16/2 | DA-3 | 2025-03-19 | 2025-03-22 | Pankaj-2 | 34.7898 | 3.6668 | Rameshwar Mahto | Completed
29 |  | 16/3 | DB1+6 | 2025-09-21 | 2025-09-29 | Pinki Devi | 65.0226 | 6.8534 | Rameshwar Mahto | Completed
30 |  | 16/5 | DA+0 | 2025-03-09 | 2025-03-13 | Pankaj-2 | 36.1598 | 3.8112 | Rameshwar Mahto | Completed
31 |  | 16/6 | DA-3 | 2025-03-13 | 2025-03-18 | Pankaj-2 | 34.7898 | 3.6668 | Rameshwar Mahto | Completed
32 |  | 17/0 | DB2+0 | 2025-08-25 | 2025-09-08 | Pinki Devi | 59.5006 | 6.2714 | Rameshwar Mahto | Completed
33 |  | 17/1 | DA+3 | 2025-03-28 | 2025-03-31 | Pankaj-2 | 37.9311 | 3.9979 | Rameshwar Mahto | Completed
34 |  | 17/2 | DA+0 | 2025-04-01 | 2025-04-05 | Pankaj-2 | 36.1598 | 3.8112 | Rameshwar Mahto | Completed
35 |  | 17/3 | DA+3 | 2025-04-06 | 2025-04-12 | Pankaj-2 | 37.9311 | 3.9979 | Rameshwar Mahto | Completed
36 |  | 17/5 | DA+9 | 2025-04-13 | 2025-04-18 | Pankaj-2 | 45.697 | 4.8165 | Rameshwar Mahto | Completed
37 |  | 17/6 | DA+3 | 2025-04-19 | 2025-04-23 | Pankaj-2 | 37.9311 | 3.9979 | Rameshwar Mahto | Completed
38 |  | 17/7 | DA+9 | 2025-04-21 | 2025-04-28 | Pankaj | 45.697 | 4.8165 | Rameshwar Mahto | Completed
39 |  | 17/8 | DA+0 | 2025-04-09 | 2025-04-15 | Pankaj | 36.1598 | 3.8112 | Rameshwar Mahto | Completed
40 |  | 17/9 | DA-1.5 | 2025-04-16 | 2025-04-20 | Pankaj | 35.6018 | 3.7524 | Rameshwar Mahto | Completed
41 |  | 18/0 | DB1+9 | 2025-09-09 | 2025-09-21 | Pinki Devi | 66.7757 | 7.0382 | Rameshwar Mahto | Completed
42 |  | 18/2 | DA+0 | 2025-04-05 | 2025-04-08 | Pankaj | 36.1598 | 3.8112 | Rameshwar Mahto | Completed
43 |  | 18/3 | DA+6 | 2025-03-22 | 2025-03-26 | Pankaj | 43.8044 | 4.617 | Rameshwar Mahto | Completed
44 |  | 18/4 | DA-1.5 | 2025-03-31 | 2025-04-04 | Pankaj | 35.6018 | 3.7524 | Rameshwar Mahto | Completed
45 |  | 18/5 | DA+3 | 2025-03-27 | 2025-03-30 | Pankaj | 37.9311 | 3.9979 | Rameshwar Mahto | Completed
46 |  | 18/6 | DA+3 | 2025-03-01 | 2025-03-04 | Pankaj | 37.9311 | 3.9979 | Rameshwar Mahto | Completed
47 |  | 18/7 | DA-1.5 | 2025-03-18 | 2025-03-21 | Pankaj | 35.6018 | 3.7524 | Rameshwar Mahto | Completed
48 |  | 18/8 | DA-3 | 2025-03-05 | 2025-03-07 | Pankaj | 34.7898 | 3.6668 | Rameshwar Mahto | Completed
49 |  | 19/1 | DA+3 | 2025-05-17 | 2025-05-21 | Pankaj | 37.9311 | 3.9979 | Rameshwar Mahto | Completed
50 |  | 19/3 | DA+0 | 2025-03-12 | 2025-03-17 | Pankaj | 36.1598 | 3.8112 | Rameshwar Mahto | Completed
51 |  | 21/0 | DB2+6 | 2025-09-30 | 2025-10-09 | Pinki Devi | 69.376 | 7.3122 | Teklal Mahto | Completed
52 |  | 21/1 | DA+0 | 2025-03-08 | 2025-03-11 | Pankaj | 36.1598 | 3.8112 | Rameshwar Mahto | Completed
53 |  | 21/2 | DA+3 | 2025-05-22 | 2025-05-26 | Pankaj | 37.9311 | 3.9979 | Rameshwar Mahto | Completed
54 |  | 21/4 | DA+3 | 2025-05-08 | 2025-05-16 | Pankaj | 37.9311 | 3.9979 | Rameshwar Mahto | Completed
55 |  | 21/5 | DA+3 | 2025-04-29 | 2025-05-07 | Pankaj | 37.9311 | 3.9979 | Rameshwar Mahto | Completed
56 |  | 22/0 | DD45+0 | 2025-10-18 | 2025-11-02 | Ghyansham Mahto | 73.2445 | 7.72 | Rameshwar Mahto | Completed
57 |  | 22/1 | DA+3 | 2025-02-03 | 2025-02-06 | Pankaj | 37.9311 | 3.9979 | Rameshwar Mahto | Completed
58 |  | 22/2 | DA-1.5 | 2025-02-07 | 2025-02-10 | Pankaj | 35.6018 | 3.7524 | Rameshwar Mahto | Completed
59 |  | 22/3 | DA+6 | 2025-01-30 | 2025-02-02 | Pankaj | 43.8044 | 4.617 | Rameshwar Mahto | Completed
60 |  | 22/4 | DA+3 | 2025-01-22 | 2025-01-25 | Pankaj | 37.9311 | 3.9979 | Rameshwar Mahto | Completed
61 |  | 23/1 | DA+9 | 2025-01-26 | 2025-01-29 | Pankaj | 45.697 | 4.8165 | Rameshwar Mahto | Completed
62 |  | 23/2 | DA+0 | 2025-08-26 | 2025-09-10 | Ghyansham Mahto | 36.1598 | 3.8112 | Rameshwar Mahto | Completed
63 |  | 23/3 | DA+6 | 2025-02-11 | 2025-02-14 | Pankaj | 43.8044 | 4.617 | Rameshwar Mahto | Completed
64 |  | 23/4 | DA-1.5 | 2025-02-15 | 2025-02-18 | Pankaj | 35.6018 | 3.7524 | Rameshwar Mahto | Completed
65 |  | 23/5 | DA+3 | 2025-02-19 | 2025-02-22 | Pankaj | 37.9311 | 3.9979 | Rameshwar Mahto | Completed
66 |  | 23/6 | DA-3 | 2025-02-23 | 2025-02-25 | Pankaj | 34.7898 | 3.6668 | Rameshwar Mahto | Completed
67 |  | 23/7 | DA-3 | 2025-02-26 | 2025-02-28 | Pankaj | 34.7898 | 3.6668 | Rameshwar Mahto | Completed
68 |  | 24/0 | DB2+0 | 2025-09-27 | 2025-10-16 | Ghyansham Mahto | 59.5006 | 6.2714 | Rajesh Singh | Completed
69 |  | 24/1 | DB1+9 | 2025-09-10 | 2025-09-26 | Ghyansham Mahto | 66.7757 | 7.0382 | Rajesh Singh | Completed
70 |  | 25/3. | DA+0 | 2024-12-23 | 2024-12-27 | Pankaj | 36.1598 | 3.8112 | Rajesh Singh | Completed
71 |  | 25/4 | DA+0 | 2024-12-28 | 2024-12-31 | Pankaj | 36.1598 | 3.8112 | Rajesh Singh | Completed
72 |  | 26/1 | DA+6 | 2025-01-02 | 2025-01-06 | Pankaj | 43.8044 | 4.617 | Rajesh Singh | Completed
73 |  | 26/3 | DA+3 | 2025-01-14 | 2025-01-17 | Pankaj | 37.9311 | 3.9979 | Rajesh Singh | Completed
74 |  | 26/4 | DA-3 | 2025-10-17 | 2025-10-24 | Pinki Devi | 34.7898 | 3.6668 | Rajesh Singh | Completed
75 |  | 26/5 | DA+0 | 2025-01-10 | 2025-01-13 | Pankaj | 36.1598 | 3.8112 | Rajesh Singh | Completed
76 |  | 26/6 | DA+3 | 2025-01-07 | 2025-01-09 | Pankaj | 37.9311 | 3.9979 | Rajesh Singh | Completed
77 |  | 26/8 | DA+0 | 2025-01-18 | 2025-01-21 | Pankaj | 36.1598 | 3.8112 | Rajesh Singh | Completed
78 |  | 27/1 | DA+3 | 2025-10-10 | 2025-10-16 | Pinki Devi | 37.9311 | 3.9979 | Rajesh Singh | Completed
79 |  | 29/2 | DA+0 | 2025-09-18 | 2025-09-26 | Neha Const. | 36.1598 | 3.8112 | Rajesh Singh | Completed
80 |  | 30/1 | DA+9 | 2025-10-19 | 2025-11-02 | Karam Mahto | 45.697 | 4.8165 | Rajesh Singh | Completed
81 |  | 30/2 | DA+3 | 2025-08-28 | 2025-09-17 | Neha Const. | 37.9311 | 3.9979 | Rajesh Singh | Completed
82 |  | 30/4 | DA+3 | 2025-09-26 | 2025-10-09 | Karam Mahto | 37.9311 | 3.9979 | Rajesh Singh | Completed
83 |  | 30/5 | DA+0 | 2025-10-10 | 2025-10-18 | Karam Mahto | 36.1598 | 3.8112 | Rajesh Singh | Completed
84 |  | 26/10 | DA+0 | 2025-11-04 | 2025-11-11 | Karam Mahto | 36.1598 | 3.8112 | Teklal Mahto | Completed
85 |  | 13/0 | DB2+0 | 2025-11-03 | 2025-11-17 | Sainik Traders | 59.5006 | 6.2714 | Teklal Mahto | Completed
86 |  | 19/0 | DD45+0 | 2025-11-03 | 2025-11-17 | Ghyansham Mahto | 73.2446 | 7.72 | Teklal Mahto | Completed
87 |  | 10/2 | DA+0 | 2025-11-18 | 2025-11-24 | Sainik Traders | 36.1598 | 3.8112 | Teklal Mahto | Completed
88 |  | 23/0 | DC2+3 | 2025-11-19 | 2025-12-01 | Ghyansham Mahto | 70.7447 | 7.4565 | Teklal Mahto | Completed
89 |  | 30/0 | DC2+0 | 2025-11-14 | 2025-12-03 | Karam Mahto | 67.2617 | 7.0894 | Teklal Mahto | Completed
90 |  | 11/5 | DA+3 | 2025-11-28 | 2025-12-05 | Neha Const. | 37.9311 | 3.9979 | Teklal Mahto | Completed
91 |  | 14/0 | DD45+0 | 2025-11-28 | 2025-12-07 | Sainik Traders | 73.2446 | 7.72 | Rameshwar Mahto | Completed
92 |  | 16/4 | DA+9 | 2025-12-05 | 2025-12-11 | Rajesh Kumar | 45.697 | 4.8165 | Rameshwar Mahto | Completed
93 |  | 8/1 | DA+0 | 2025-12-08 | 2025-12-14 | HOREL MAHTO | 36.1598 | 3.8112 | Rameshwar Mahto | Completed
94 |  | 13/4 | DA+3 | 2025-12-06 | 2025-12-14 | Sainik Traders | 37.9311 | 3.9979 | Rameshwar Mahto | Completed
95 |  | 19/2 | DA+3 | 2025-12-03 | 2025-12-14 | Ghyansham Mahto | 37.9311 | 3.9979 | Teklal Mahto | Completed
96 |  | 29/0 | DB2+0 | 2025-12-05 | 2025-12-14 | PUNAM KUMARI-1 | 59.5006 | 6.2714 | Teklal Mahto | Completed
97 |  | 18/1 | DB1+9 | 2025-12-09 | 2025-12-18 | PUNAM KUMARI-1 | 66.7757 | 7.0382 | Teklal Mahto | Completed
98 |  | 13/3 | DA+0 | 2025-12-15 | 2025-12-20 | Sainik Traders | 36.1598 | 3.8112 | Rameshwar Mahto | Completed
99 |  | 28/0 | DC1+0 | 2025-12-15 | 2025-12-24 | PUNAM KUMARI-1 | 62 | 6.5348 | Teklal Mahto | Completed
100 |  | 8/3 | DB1+6 | 2025-12-18 | 2025-12-29 | HOREL MAHTO | 65.0226 | 6.8534 | Rameshwar Mahto | Completed
101 |  | 15/0 | DB1+9 | 2025-12-21 | 2025-12-30 | Sainik Traders | 66.7757 | 7.0382 | Rameshwar Mahto | Completed
102 |  | 17/4 | DB1+9 | 2025-12-21 | 2025-12-30 | PUNAM KUMARI-2 | 66.7757 | 7.0382 | Teklal Mahto | Completed
103 |  | 26/7 | DA+0 | 2025-12-25 | 2025-12-30 | PUNAM KUMARI-1 | 36.1598 | 3.8112 | Teklal Mahto | Completed
104 |  | 20/0 | DD45+6 | 2025-12-16 | 2025-12-31 | Ghyansham Mahto | 85.2637 | 8.9868 | Rameshwar Mahto | Completed
105 |  | 15/1 | DA+9 | 2025-12-13 | 2026-01-02 | Rajesh Kumar | 45.697 | 4.8165 | Teklal Mahto | Completed
106 |  | 26/0 | DC2+0 | 2025-12-30 | 2026-01-07 | PUNAM KUMARI-2 | 67.2617 | 7.0894 | Teklal Mahto | Completed
107 |  | 8/2 | DA-3 | 2025-12-30 | 2026-01-08 | HOREL MAHTO | 34.7898 | 3.6668 | Rajesh Singh | Completed
108 |  | 33/0 | DC2+0 | 2025-12-30 | 2026-01-09 | PUNAM KUMARI-1 | 67.2617 | 7.0894 | Teklal Mahto | Completed
109 |  | 14/1 | DA+0 | 2026-01-02 | 2026-01-11 | Sainik Traders | 36.1598 | 3.8112 | Rajesh Singh | Completed
110 |  | 26/2 | DA+3 | 2026-01-04 | 2026-01-11 | Mukhi Lal | 37.9311 | 3.9979 | Teklal Mahto | Completed
111 |  | 25/2 | DA+0 | 2026-01-11 | 2026-01-14 | PUNAM KUMARI-2 | 36.1598 | 3.8112 | Teklal Mahto | Completed
112 |  | 30/3 | DA+9 | 2026-01-10 | 2026-01-16 | PUNAM KUMARI-1 | 45.697 | 4.8165 | Rameshwar Mahto | Completed
113 |  | 29/1 | DA+0 | 2026-01-13 | 2026-01-20 | Sainik Traders | 36.1598 | 3.8112 | Rameshwar Mahto | Completed
114 |  | 16/0 | DB2+3 | 2026-01-04 | 2026-01-24 | Ghyansham Mahto | 62.1162 | 6.547 | Rameshwar Mahto | Completed
115 |  | 21/3 | DC1+0 | 2026-01-13 | 2026-01-29 | Mukhi Lal | 82.2616 | 8.6704 | Rameshwar Mahto | Completed
116 |  | 31/0 | DD45+0 | 2026-01-17 | 2026-01-29 | PUNAM KUMARI-1 | 73.2446 | 7.72 | Rameshwar Mahto | Completed
117 |  | 32/1 | DA+6 | 2026-02-04 | 2026-02-08 | Mukhi Lal | 43.8044 | 4.617 | Rameshwar Mahto | Completed
118 |  | 25/1 | DA+0 | 2026-01-28 | 2026-02-10 | Ghyansham Mahto | 36.1598 | 3.8112 | Rameshwar Mahto | Completed
119 |  | 10/1 | DB1+6 | 2026-02-10 | 2026-02-18 | Mukhi Lal | 65.0226 | 6.8534 | Rameshwar Mahto | Completed

## Stringing
|  |  | Number of TSE | 1
S.no | Sec | From AP | To AP | Span (M) | Method | Section Readiness | Insulator Hoisting | P/O Starting Date | P/O Completion Date | P/O | F/S Starting Date | F/S/ Completion Date | Jumpering | Spacering | Clipping | Length | Status | Gang Name | Gang Strength | No of Fitters | Hindrance | Remarks
1 | Bhinder | 16/3 | 17/0 | 1466.6 | TSE | Ready |  | 2026-02-04 | 2026-02-07 | 1466.6 | 2026-02-19 | 2026-02-19 |  | Completed | Completed | 1466.6 | Completed | Lamba Construction | 50 | 13
2 | Bhinder | 17/0 | 17/4 | 1647 | TSE | Ready |  | 2026-02-11 | 2026-02-14 | 1647 | 2026-02-19 | 2026-02-22 |  | Completed | Completed | 1647 | Completed | Lamba Construction | 50 | 13
3 | Bhinder | 17/4 | 18/0 | 2304.23 | TSE | Ready |  | 2026-02-17 | 2026-02-21 | 2304.23 | 2026-02-25 | 2026-02-27 |  | Completed | Completed | 2304.23 | Completed | Lamba Construction | 50 | 13
4 | Bhinder | 18/0 | 18/1 | 503 | TSE | Ready |  | 2026-02-19 | 2026-02-24 | 0.5 | 2026-02-25 | 2026-02-28 |  | Completed | Completed | 503 | Completed | Lamba Construction | 50 | 13
5 | Bhinder | 18/1 | 19/0 | 3025.21 | TSE | Ready |  | 2026-02-19 | 2026-02-24 | 3025 | 2026-02-25 | 2026-02-28 |  | wip | Completed | 3025.21 | Completed | Lamba Construction | 50 | 13
6 | Bhinder | 15/0 | 16/0 | 3229.73 | TSE | Ready | WIP | [8 empty] | 3229.73 |  | Lamba Construction | 50 | 13
U/C 220 KV
|  |  | Total | 12.1758

## VC_RMTL
Visual Chart :- 765kV D/C Rishabdeo Mandsaur Transmission Line, WZ-04
[9 empty] | Project Code : TA504 | [23 empty] | Dated: |  | 2026-03-24
[22 empty] | Description of Item |  |  |  | UOM | Total Line Qty |  | Total Completed |  | WIP locations |  | Total Balance |  | Remarks
[9 empty] | LEGEND: |  |  |  |  | OPGW Stringing
|  |  | Stringing Comp | [11 empty] | Location No. | [6 empty] | Route Alignment |  |  |  | Kms | 62.499 |  | 62.499 |  |  |  | 0
[22 empty] | Detail Survey |  |  |  | Kms | 62.499 |  | 62.499 | 0 |  |  | 0
| Erection Comp | [15 empty] | Stringing WIP |  |  |  |  | Check Survey |  |  |  | Kms | 62.499 |  | 54 | 0 |  |  | 8.499
[15 empty] | Erection Comp | [6 empty] | Foundation |  |  |  | Nos | 164 |  | 137 |  | 1 |  | 27
| Foundation Comp | [6 empty] | C | B | SPAN |  | C | B | [8 empty] | Earthing |  |  |  | Nos | 164 |  | 85 |  |  |  | 79
[8 empty] | D | A |  |  | D | A |  | Foundation Comp | [6 empty] | Erection |  |  |  | Nos | 164 |  | 119 |  | 0 |  | 45
| Earthing Comp | [17 empty] | Holdup location |  |  | Tack Welding |  |  |  | Twr | 164 |  | 0 |  |  |  | 164
[22 empty] | Stringing (Rough Sag) |  |  |  | Kms | 62.499 |  | 8.946 |  | 3.229 |  | 53.553
|  |  |  | Type of Tower |  |  |  | TREE CUTTING CLEARANCE | [13 empty] | Stringing (Final Sag) |  |  |  | Kms | 62.499 |  | 8.946 |  | 3.229 |  | 53.553
[32 empty] | Gantry |  |  |  | 1/0
[32 empty] | 1 |  |  |  | 2
[32 empty] | C | B |  |  | C | B | 108.19 | 108.19 | 7
[32 empty] | D | A |  |  | D | A
| NH/SH Xing | [9 empty] | 132/220/400/765 Kv CROSSING | [6 empty] | Gas pipeline
[5 empty] | RAILWAY Xing | [8 empty] | RIVER X-ING | [17 empty] | DD60+0 |  |  |  | DD60+0
2/0 |  |  |  | 3/0 |  |  | 3/1 |  |  |  | 3/2 |  |  | 3/3 |  |  |  | 4/0 |  |  | 4/1 |  |  | 5/0 |  |  |  | 5/1 |  |  |  | 5A/0 |  |  |  | 5B/0
3 |  |  |  | 4 |  |  | 5 |  |  |  | 6 |  |  | 7 |  |  |  | 8 |  |  | 9 |  |  | 10 |  |  |  | 11 |  |  |  | 12 |  |  |  | 13
C | B | 216.27 |  | C | B | 280 | C | B | 388 |  | C | B | 390 | C | B | 380 |  | C | B | 272 | C | B | 290 | C | B | 368 |  | C | B | 388 |  | C | B | 234 |  | C | B | 405 | 3611.27 | 11
D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
DC1+0 |  |  |  | DD60+0 |  |  | DA+0 |  |  |  | DA+3 |  |  | DB2+0 |  |  |  | DD60+0 |  |  | DA+0 |  |  | DC1+0 |  |  |  | DA+3 |  |  |  | DD45+3 |  |  |  | DB1+9
[24 empty] | ROW |  |  |  | ROW
5B/1 |  |  |  | 5C/0 |  |  | 5D/0 |  |  |  | 5E/0 |  |  | 5F/0 |  |  |  | 5G/0 |  |  | 5G/1 |  |  | 5G/2 |  |  |  | 5G/3 |  |  |  | 5G/4 |  |  |  | 5G/5
14 |  |  |  | 15 |  |  | 16 |  |  |  | 17 |  |  | 18 | [6 empty] | 1 |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5
C | B | 340 |  | C | B | 196 | C | B | 202 |  | C | B | 478 | C | B | 216 |  | C | B | 405 | C | B | 379 | C | B | 415 |  | C | B | 400 |  | C | B | 378 |  | C | B | 457 | 3866 | 11
D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
[18 empty] | PT |  |  | PT |  |  | CP |  |  |  | CP |  |  |  | CP
DC1+9 |  |  |  | DD45+18 |  |  | DD60+6 |  |  |  | DB1+3 |  |  | DD60+18 |  |  |  | DD60+18 |  |  | DA+0 |  |  | DA+0 |  |  |  | DA+3 |  |  |  | DA+0 |  |  |  | DA+9
ROW
5H/0 |  |  |  | 5H/1 |  |  | 5I/0 |  |  |  | 6/0 |  |  | 7/0 |  |  |  | 7/1 |  |  | 7/2 |  |  | 8/0 |  |  |  | 8/1 |  |  |  | 8/2 |  |  |  | 8/3
6 |  |  |  | 7 |  |  | 8 |  |  |  | 9 |  |  | 10 |  |  |  | 11 |  |  | 12 |  |  | 13 |  |  |  | 14 |  |  |  | 15 |  |  |  | 16
C | B | 374 |  | C | B | 383 | C | B | 388 |  | C | B | 233.81 | C | B | 370.22 |  | C | B | 361.27 | C | B | 424.96 | C | B | 385.69 |  | C | B | 365 |  | C | B | 345.88 |  | C | B | 346.54 | 3978.37 | 11
D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
CP |  |  |  | PT |  |  | CP |  |  |  | PT | [9 empty] | CP |  |  | CP |  |  |  | CP |  |  |  | CP |  |  |  | PT
DC1+9 |  |  |  | DB2+0 |  |  | DC2+0 |  |  |  | DB1+6 |  |  | DD45+6 |  |  |  | DA-3 |  |  | DA+3 |  |  | DC1+0 |  |  |  | DA+0 |  |  |  | DA-3 |  |  |  | DB1+6
Powerline X-ing | [13 empty] | ROW |  |  |  | ROW
9/0 |  |  |  | 10/0 |  |  | 10/1 |  |  |  | 10/2 |  |  | 10/3 |  |  |  | 10/4 |  |  | 11/0 |  |  | 11/1 |  |  |  | 11/2 |  |  |  | 11/3 |  |  |  | 11/4
17 |  |  |  | 18 |  |  | 19 |  |  |  | 20 |  |  | 21 |  |  |  | 22 |  |  | 23 |  |  | 24 |  |  |  | 25 |  |  |  | 26 |  |  |  | 27
C | B | 195.43 |  | C | B | 327.43 | C | B | 437.14 |  | C | B | 398.45 | C | B | 385.1 |  | C | B | 418.05 | C | B | 356.43 | C | B | 400.9 |  | C | B | 414.95 |  | C | B | 418.09 |  | C | B | 397.64 | 4149.61 | 11
D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
[7 empty] | PT |  |  |  | CP |  |  | CP | [6 empty] | CP |  |  | PT |  |  |  | PT |  |  |  | CP |  |  |  | CP
DD60+35 |  |  |  | DD60+35 |  |  | DB1+6 |  |  |  | DA+0 |  |  | DA+0 |  |  |  | DA+3 |  |  | DB2+0 |  |  | DA+0 |  |  |  | DA+0 |  |  |  | DA+3 |  |  |  | DA+0
|  |  |  | ROW | [31 empty] | ROW
11/5 |  |  |  | 11/6 |  |  | 12/0 |  |  |  | 12/1 |  |  | 12/2 |  |  |  | 12/3 |  |  | 12/4 |  |  | 12/5 |  |  |  | 13/0 |  |  |  | 13/1 |  |  |  | 13/2
28 |  |  |  | 29 |  |  | 30 |  |  |  | 31 |  |  | 32 |  |  |  | 33 |  |  | 34 |  |  | 35 |  |  |  | 36 |  |  |  | 37 |  |  |  | 38
C | B | 416.4 |  | C | B | 328.49 | C | B | 369 |  | C | B | 381 | C | B | 385 |  | C | B | 403 | C | B | 436 | C | B | 398.43 |  | C | B | 387 |  | C | B | 361 |  | C | B | 371 | 4236.32 | 11
D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
CP |  |  |  | CP |  |  | PT |  |  |  | CP |  |  | CP |  |  |  | PT |  |  | PT |  |  | CP |  |  |  | CP |  |  |  | CP
DA+3 |  |  |  | DA+0 |  |  | DB2+0 |  |  |  | DA-3 |  |  | DA+0 |  |  |  | DA+0 |  |  | DA+6 |  |  | DA+6 |  |  |  | DB2+0 |  |  |  | DA-3 |  |  |  | DA+0
13/3 |  |  |  | 13/4 |  |  | 13/5 |  |  |  | 13/6 |  |  | 14/0 |  |  |  | 14/1 |  |  | 14/2 |  |  | 14/3 |  |  |  | 14/4 |  |  |  | 14/5 |  |  |  | 14/6
39 |  |  |  | 40 |  |  | 41 |  |  |  | 42 |  |  | 43 |  |  |  | 44 |  |  | 45 |  |  | 46 |  |  |  | 47 |  |  |  | 48 |  |  |  | 49
C | B | 374 |  | C | B | 441 | C | B | 376 |  | C | B | 409.1 | C | B | 388 |  | C | B | 393 | C | B | 399 | C | B | 395 |  | C | B | 395 |  | C | B | 417 |  | C | B | 415 | 4402.1 | 11
D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
PT |  |  |  | CP |  |  | CP |  |  |  | CP |  |  | CP | [6 empty] | CP |  |  | PT |  |  |  | CP |  |  |  | CP |  |  |  | CP
DA+0 |  |  |  | DA+3 |  |  | DA+3 |  |  |  | DA+3 |  |  | DD45+0 |  |  |  | DA+0 |  |  | DA+0 |  |  | DA+0 |  |  |  | DA+0 |  |  |  | DA+3 |  |  |  | DA+0
14/7 |  |  |  | 15/0 |  |  | 15/1 |  |  |  | 15/2 |  |  | 15/3 |  |  |  | 15/4 |  |  | 15/5 |  |  | 15/6 |  |  |  | 15/7 |  |  |  | 16/0 |  |  |  | 16/1
50 |  |  |  | 51 |  |  | 52 |  |  |  | 53 |  |  | 54 |  |  |  | 55 |  |  | 56 |  |  | 57 |  |  |  | 58 |  |  |  | 59 |  |  |  | 60
C | B | 417.39 |  | C | B | 482 | C | B | 357 |  | C | B | 401 | C | B | 413 |  | C | B | 380 | C | B | 364 | C | B | 443 |  | C | B | 389.73 |  | C | B | 440 |  | C | B | 398 | 4485.12 | 11
D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
CP |  |  |  | CP |  |  | PT |  |  |  | CP |  |  | CP |  |  |  | CP |  |  | CP |  |  | CP |  |  |  | CP |  |  |  | CP |  |  |  | CP
DA+3 |  |  |  | DB1+0 |  |  | DA+3 |  |  |  | DA+3 |  |  | DA+0 |  |  |  | DA+3 |  |  | DA-3 |  |  | DA+3 |  |  |  | DA+6 |  |  |  | DB2+3 |  |  |  | DA+6
16/2 |  |  |  | 16/3 |  |  | 16/4 |  |  |  | 16/5 |  |  | 16/6 |  |  |  | 17/0 |  |  | 17/1 |  |  | 17/2 |  |  |  | 17/3 |  |  |  | 17/4 |  |  |  | 17/5
61 |  |  |  | 62 |  |  | 63 |  |  |  | 64 |  |  | 65 |  |  |  | 66 |  |  | 67 |  |  | 68 |  |  |  | 69 |  |  |  | 70 |  |  |  | 71
C | B | 408 |  | C | B | 481 | C | B | 346 |  | C | B | 291 | C | B | 348.6 |  | C | B | 400 | C | B | 408 | C | B | 418 |  | C | B | 421 |  | C | B | 503 |  | C | B | 321 | 4345.6 | 11
D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
CP |  |  |  | CP |  |  | CP |  |  |  | CP |  |  | CP |  |  |  | CP |  |  | CP |  |  | CP |  |  |  | PT |  |  |  | PT |  |  |  | CP
DA-3 |  |  |  | DB1+6 |  |  | DA+9 |  |  |  | DA+0 |  |  | DA-3 |  |  |  | DB2+0 |  |  | DA+3 |  |  | DA+0 |  |  |  | DA+3 |  |  |  | DB1+9 |  |  |  | DA+9
17/6 |  |  |  | 17/7 |  |  | 17/8 |  |  |  | 17/9 |  |  | 18/0 |  |  |  | 18/1 |  |  | 18/2 |  |  | 18/3 |  |  |  | 18/4 |  |  |  | 18/5 |  |  |  | 18/6
72 |  |  |  | 73 |  |  | 74 |  |  |  | 75 |  |  | 76 |  |  |  | 77 |  |  | 78 |  |  | 79 |  |  |  | 80 |  |  |  | 81 |  |  |  | 82
C | B | 389 |  | C | B | 448 | C | B | 304 |  | C | B | 339.23 | C | B | 503 |  | C | B | 433 | C | B | 405 | C | B | 418 |  | C | B | 344 |  | C | B | 417 |  | C | B | 384 | 4384.23 | 11
D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
CP |  |  |  | PT |  |  | PT |  |  |  | PT |  |  | PT |  |  |  | PT |  |  | CP |  |  | CP |  |  |  | CP |  |  |  | CP |  |  |  | CP
DA+3 |  |  |  | DA+9 |  |  | DA+0 |  |  |  | DA-1.5 |  |  | DB1+9 |  |  |  | DB1+9 |  |  | DA+0 |  |  | DA+6 |  |  |  | DA-1.5 |  |  |  | DA+3 |  |  |  | DA+3
18/7 |  |  |  | 18/8 |  |  | 19/0 |  |  |  | 19/1 |  |  | 19/2 |  |  |  | 19/3 |  |  | 20/0 |  |  | 21/0 |  |  |  | 21/1 |  |  |  | 21/2 |  |  |  | 21/3
88
83 |  |  |  | 84 |  |  | 85 |  |  |  | 86 |  |  | 87 |  |  |  | 88 |  |  | 89 |  |  | 90 |  |  |  | 91 |  |  |  | 92 |  |  |  | 93
C | B | 326 |  | C | B | 298.21 | C | B | 415 |  | C | B | 395 | C | B | 404 |  | C | B | 359.56 | C | B | 460.68 | C | B | 431 |  | C | B | 409 |  | C | B | 359 |  | C | B | 414 | 4271.45 | 11
D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
CP |  |  |  | CP |  |  | CP |  |  |  | PT |  |  | CP |  |  |  | CP |  |  | CP |  |  | CP |  |  |  | CP |  |  |  | CP |  |  |  | CP
DA-1.5 |  |  |  | DA-3 |  |  | DD45+0 |  |  |  | DA+3 |  |  | DA+3 |  |  |  | DA+0 |  |  | DD45+6 |  |  | DB2+6 |  |  |  | DA+0 |  |  |  | DA+3 |  |  |  | DC1+0 (DCT)
21/4 |  |  |  | 21/5 |  |  | 22/0 |  |  |  | 22/1 |  |  | 22/2 |  |  |  | 22/3 |  |  | 22/4 |  |  | 23/0 |  |  |  | 23/1 |  |  |  | 23/2 |  |  |  | 23/3
94 |  |  |  | 95 |  |  | 96 |  |  |  | 97 |  |  | 98 |  |  |  | 99 |  |  | 100 |  |  | 101 |  |  |  | 102 |  |  |  | 103 |  |  |  | 104
C | B | 425 |  | C | B | 356.41 | C | B | 409 |  | C | B | 416 | C | B | 419 |  | C | B | 413 | C | B | 315.51 | C | B | 431 |  | C | B | 409 |  | C | B | 428 |  | C | B | 412 | 4433.92 | 11
D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
CP |  |  |  | CP |  |  | CP |  |  |  | CP |  |  | CP |  |  |  | CP |  |  | CP |  |  | CP |  |  |  | CP |  |  |  | CP |  |  |  | PT/CP
DA+3 |  |  |  | DA+3 |  |  | DD45+0 |  |  |  | DA+3 |  |  | DA-1.5 |  |  |  | DA+6 |  |  | DA+3 |  |  | DC2+3 |  |  |  | DA+9 |  |  |  | DA+0 |  |  |  | DA+6
[21 empty] | RC, SCA |  |  | ROW |  |  |  | RC |  |  |  | RC
23/4 |  |  |  | 23/5 |  |  | 23/6 |  |  |  | 23/7 |  |  | 24/0 |  |  |  | 24/1 |  |  | 24/2 |  |  | 25/0 |  |  |  | 25/1 |  |  |  | 25/2 |  |  |  | 25/3
105 |  |  |  | 106 |  |  | 107 |  |  |  | 108 |  |  | 109 |  |  |  | 110 |  |  | 111 |  |  | 112 |  |  |  | 113 |  |  |  | 114 |  |  |  | 115
C | B | 408 |  | C | B | 362 | C | B | 303 |  | C | B | 336.96 | C | B | 432 |  | C | B | 567 | C | B | 543.55 | C | B | 429 |  | C | B | 346 |  | C | B | 381 |  | C | B | 394 | 4502.51 | 11
D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
CP |  |  |  | CP |  |  | CP |  |  |  | CP |  |  | CP |  |  |  | PT |  |  | CP |  |  | PT | [11 empty] | CP
DA-1.5 |  |  |  | DA+3 |  |  | DA-3 |  |  |  | DA-3 |  |  | DB2+0 |  |  |  | DB1+9 |  |  | DB1+0 |  |  | DC1+9 |  |  |  | DA+0 |  |  |  | DA+0 |  |  |  | DA+0
[11 empty] | RC | [24 empty] | ROW
25/4 |  |  |  | 26/0 |  |  | 26/1 |  |  |  | 26/2 |  |  | 26/3 |  |  |  | 26/4 |  |  | 26/5 |  |  | 26/6 |  |  |  | 26/7 |  |  |  | 26/8 |  |  |  | 26/9
116 |  |  |  | 117 |  |  | 118 |  |  |  | 119 |  |  | 120 |  |  |  | 121 |  |  | 122 |  |  | 123 |  |  |  | 124 |  |  |  | 125 |  |  |  | 126
C | B | 356.87 |  | C | B | 438 | C | B | 399 |  | C | B | 347 | C | B | 400 |  | C | B | 375 | C | B | 416 | C | B | 408 |  | C | B | 404 |  | C | B | 391 |  | C | B | 371 | 4305.87 | 11
D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
CP |  |  |  | CP |  |  | CP | [6 empty] | CP |  |  |  | CP |  |  | PT/CP |  |  | CP |  |  |  | PT |  |  |  | PT |  |  |  | CP
DA+0 |  |  |  | DC2+0 |  |  | DA+6 |  |  |  | DA+3 |  |  | DA+3 |  |  |  | DA-3 |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+0 |  |  |  | DA+0 |  |  |  | DA+0
[14 empty] | FOREST |  |  |  | FOREST |  |  | FOREST
|  |  |  | ROW | [9 empty] | ULE/RC |  |  |  | RC |  |  | RC
26/10 |  |  |  | 27/0 |  |  | 27/1 |  |  |  | 28/0 |  |  | 28/1 |  |  |  | 29/0 |  |  | 29/1 |  |  | 29/2 |  |  |  | 30/0 |  |  |  | 30/1 |  |  |  | 30/2
127 |  |  |  | 128 |  |  | 129 |  |  |  | 130 |  |  | 131 |  |  |  | 132 |  |  | 133 |  |  | 134 |  |  |  | 135 |  |  |  | 136 |  |  |  | 137
C | B | 391.19 |  | C | B | 412 | C | B | 384.05 |  | C | B | 404 | C | B | 261.81 |  | C | B | 358 | C | B | 419 | C | B | 367.81 |  | C | B | 409 |  | C | B | 343 |  | C | B | 394 | 4143.86 | 11
D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  |  | D | A
PT |  |  |  | PT |  |  | CP |  |  |  | PT | [6 empty] | CP |  |  | CP |  |  | CP |  |  |  | CP |  |  |  | CP |  |  |  | CP
DA+0 |  |  |  | DC1+0 |  |  | DA+3 |  |  |  | DC1+0 |  |  | DB1+0 |  |  |  | DB2+0 |  |  | DA+0 |  |  | DA+0 |  |  |  | DC2+0 |  |  |  | DA+9 |  |  |  | DA+3
[14 empty] | ROW |  |  |  | ULE/RC |  |  | SCA |  |  | RC
30/3 |  |  |  | 30/4 |  |  | 30/5 |  |  |  | 31/0 |  |  | 31/1 |  |  |  | 31/2 |  |  | 32/0 |  |  | 32/1 |  |  |  | 32/2 |  |  |  | 33/0
138 |  |  |  | 139 |  |  | 140 |  |  |  | 141 |  |  | 142 |  |  |  | 143 |  |  | 144 |  |  | 145 |  |  |  | 146 |  |  |  | 147
C | B | 403 |  | C | B | 350 | C | B | 354.82 |  | C | B | 363 | C | B | 437 |  | C | B | 347.62 | C | B | 400 | C | B | 439 |  | C | B | 343.61 |  | C | B | [5 empty] | 3438.05 | 10
D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  |  | D | A
PT |  |  |  | CP |  |  | CP |  |  |  | CP | [9 empty] | CP | [6 empty] | PT |  |  |  | PT
DA+9 |  |  |  | DA+3 |  |  | DA+0 |  |  |  | DD45+0 |  |  | DA+6 |  |  |  | DB1+6 |  |  | DB1+0 |  |  | DA+6 |  |  |  | DB1+9 |  |  |  | DC2+0

## Visual Chart Lilo
Visual Chart :- Lilo 765KV D/C Chittorgarh-Rishabdeo Transmission line
[8 empty] | Project Code : TA504 | [26 empty] | Dated: |  | 2026-03-24
[11 empty] | LEGEND: |  |  |  |  | OPGW Stringing | [8 empty] | Description of Item |  |  |  |  | Total Line Qty |  |  | Total Completed |  | WIP locations |  |  | Total Balance
|  |  |  | Stringing Comp | [12 empty] | Location No.
|  | Erection Comp | [16 empty] | Stringing WIP | [5 empty] | Foundation |  |  |  |  | 34 |  |  | 5 |  | 0 |  |  | 29
[17 empty] | Erection Comp | [7 empty] | Earthing |  |  |  |  | 34 |  |  | 2 |  |  |  |  | 32
|  | Foundation Comp | [7 empty] | C | B | SPAN |  | C | B | [9 empty] | Erection |  |  |  |  | 34 |  |  | 0 |  | 0 |  |  | 34
[10 empty] | D | A |  |  | D | A |  | Foundation Comp | [7 empty] | Tack Welding |  |  |  |  | 34 | [7 empty] | 34
|  | Earthing Comp | [18 empty] | Holdup location |  |  |  | Stringing (Rough Sag) |  |  |  |  | 12.5149 | [7 empty] | 12.5149
[25 empty] | Stringing (Final Sag) |  |  |  |  | 12.5149 | [7 empty] | 12.5149
[5 empty] | Type of Tower |  |  |  |  | TREE CUTTING CLEARANCE
|  | NH/SH Xing | [10 empty] | 132/220/400/765 Kv CROSSING | [6 empty] | Gas pipeline
[6 empty] | RAILWAY Xing | [9 empty] | RIVER X-ING
[16 empty] | HOLDUP |  |  |  | HOLDUP | [20 empty] | 12514.88 | 34
[13 empty] | Tapping Point |  |  | 1/0 |  |  |  | 2/0 |  |  |  | 2/1 |  |  | 2/2 |  |  |  | 2/3 |  |  | 2/4 |  |  |  | 3/0
[13 empty] | 0 |  |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  | 4 |  |  |  | 5 |  |  | 6 |  |  |  | 7
[15 empty] | 41.991 | C | B | 278.586 |  | C | B | 258 |  | C | B | 310 | C | B | 362 |  | C | B | 384 | C | B | 377.014 |  | C | B | 460 | 2471.591 | 7
[16 empty] | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
[24 empty] | CP |  |  | PT |  |  |  | CP
[13 empty] | 0 |  |  | DD60+0 |  |  |  | DD60+0 |  |  |  | DA+0 |  |  | DA+0 |  |  |  | DA+0 |  |  | DA+0 |  |  |  | DD45+3
S.T.
| 3/1 |  |  |  | 3/2 |  |  |  | 4/0 |  |  |  | 4/1 |  |  | 4/2 |  |  |  | 4/3 |  |  |  | 5/0 |  |  | 5/1 |  |  |  | 5/2 |  |  | 6/0 |  |  |  | 6/1
| 8 |  |  |  | 9 |  |  |  | 10 |  |  |  | 11 |  |  | 12 |  |  |  | 13 |  |  |  | 14 |  |  | 15 |  |  |  | 16 |  |  | 17 |  |  |  | 18
| C | B | 423 |  | C | B | 346.294 |  | C | B | 356 |  | C | B | 359 | C | B | 365 |  | C | B | 392.581 |  | C | B | 398 | C | B | 435 |  | C | B | 398.534 | C | B | 383 |  | C | B | 386 | 4242.409 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| CP |  |  |  | CP |  |  |  | PT |  |  |  | PT |  |  | PT
| DB1+9 |  |  |  | DA+3 |  |  |  | DB2+0 |  |  |  | DA+0 |  |  | DA+0 |  |  |  | DA+0 |  |  |  | DC2+0 |  |  | DA+3 |  |  |  | DA+3 |  |  | DC1+0 |  |  |  | DA+0
S.T.
[20 empty] | ROW |  |  |  | ROW |  |  | ROW |  |  |  | ROW |  |  | ROW |  |  |  | ROW
| 6/2 |  |  |  | 6/3 |  |  |  | 6/4 |  |  |  | 6/5 |  |  | 7/0 |  |  |  | 7/1 |  |  |  | 7/2 |  |  | 7/3 |  |  |  | 8/0 |  |  | 8/1 |  |  |  | 8/2
| 19 |  |  |  | 20 |  |  |  | 21 |  |  |  | 22 |  |  | 23 |  |  |  | 24 |  |  |  | 25 |  |  | 26 |  |  |  | 27 |  |  | 28 |  |  |  | 29
| C | B | 381 |  | C | B | 385 |  | C | B | 378 |  | C | B | 349.613 | C | B | 421 |  | C | B | 350 |  | C | B | 357 | C | B | 469.727 |  | C | B | 329 | C | B | 333 |  | C | B | 402.727 | 4156.067 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+0 |  |  |  | DA+0 |  |  |  | DA+0 |  |  |  | DA+0 |  |  | DD60+0 |  |  |  | DA+6 |  |  |  | DA+0 |  |  | DA+9 |  |  |  | DD45+3 |  |  | DA+0 |  |  |  | DA+6
S.T.
| ROW |  |  |  | ROW |  |  |  | ROW |  |  |  | ROW |  |  | ROW
| 9/0 |  |  |  | 9/1 |  |  |  | 9/2 |  |  |  | 10/0 |  |  | 11/0 |  |  |  | Gantry
| 30 |  |  |  | 31 |  |  |  | 32 |  |  |  | 33 |  |  | 34 |  |  |  | 35
| C | B | 346 |  | C | B | 424 |  | C | B | 400.443 |  | C | B | 386.37 | C | B | 88 | [22 empty] | 1644.813 | 5
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A
| DB2+0 |  |  |  | DA+3 |  |  |  | DA+3 |  |  |  | DD60+0 |  |  | DD60+0 |  |  |  | Gantry
S.T.-ROW
Summary of Tower Quantities
Sl No |  | Twr Type |  |  |  | Total Qty |  |  | Fdn Completed |  |  | Balance | [10 empty] | Erection Completed |  |  | Balance as per Fdn |  | Total Balance
1 |  | DA-3 |  |  | = | 0 |  |  | 0 |  |  | 0 | [10 empty] | 0 |  |  | 0 |  | 0
2 |  | DA-1.5 |  |  | = | 0 |  |  | 0 |  |  | 0 | [10 empty] | 0 |  |  | 0 |  | 0
3 |  | DA+0 |  |  | = | 14 |  |  | 2 |  |  | 12 | [10 empty] | 0 |  |  | 2 |  | 14
4 |  | DA+1.5 |  |  | = | 0 |  |  | 0 |  |  | 0 | [10 empty] | 0 |  |  | 0 |  | 0
5 |  | DA+3 |  |  | = | 5 |  |  | 1 |  |  | 4 | [10 empty] | 0 |  |  | 1 |  | 5
6 |  | DA+6 |  |  | = | 2 |  |  | 0 |  |  | 2 | [10 empty] | 0 |  |  | 0 |  | 2
7 |  | DA+9 |  |  | = | 1 |  |  | 0 |  |  | 1 | [10 empty] | 0 |  |  | 0 |  | 1
8 |  | DB1+0 |  |  | = | 0 |  |  | 0 |  |  | 0 | [10 empty] | 0 |  |  | 0 |  | 0
9 |  | DB1+6 |  |  | = | 0 |  |  | 0 |  |  | 0 | [10 empty] | 0 |  |  | 0 |  | 0
10 |  | DB1+9 |  |  | = | 1 |  |  | 1 |  |  | 0 | [10 empty] | 0 |  |  | 1 |  | 1
11 |  | DB2+0 |  |  | = | 2 |  |  | 1 |  |  | 1 | [10 empty] | 0 |  |  | 1 |  | 2
12 |  | DB2+3 |  |  | = | 0 |  |  | 0 |  |  | 0 | [10 empty] | 0 |  |  | 0 |  | 0
13 |  | DB2+6 |  |  | = | 0 |  |  | 0 |  |  | 0 | [10 empty] | 0 |  |  | 0 |  | 0
14 |  | DC1+0 |  |  | = | 1 |  |  | 0 |  |  | 1 | [10 empty] | 0 |  |  | 0 |  | 1
15 |  | DC1+0(T) |  |  | = | 0 |  |  | 0 |  |  | 0 | [10 empty] | 0 |  |  | 0 |  | 0
16 |  | DC1+3 |  |  | = | 0 |  |  | 0 |  |  | 0 | [10 empty] | 0 |  |  | 0 |  | 0
17 |  | DC1+6 |  |  | = | 0 |  |  | 0 |  |  | 0 | [10 empty] | 0 |  |  | 0 |  | 0
18 |  | DC1+9 |  |  | = | 0 |  |  | 0 |  |  | 0 | [10 empty] | 0 |  |  | 0 |  | 0
19 |  | DC2+0 |  |  | = | 1 |  |  | 0 |  |  | 1 | [10 empty] | 0 |  |  | 0 |  | 1
20 |  | DC2+3 |  |  | = | 0 |  |  | 0 |  |  | 0 | [10 empty] | 0 |  |  | 0 |  | 0
21 |  | DC2+6 |  |  | = | 0 |  |  | 0 |  |  | 0 | [10 empty] | 0 |  |  | 0 |  | 0
22 |  | DC2+9 |  |  | = | 0 |  |  | 0 |  |  | 0 | [10 empty] | 0 |  |  | 0 |  | 0
23 |  | DD45+0 |  |  | = | 0 |  |  | 0 |  |  | 0 | [10 empty] | 0 |  |  | 0 |  | 0
24 |  | DD45+3 |  |  | = | 2 |  |  | 0 |  |  | 2 | [10 empty] | 0 |  |  | 0 |  | 2
25 |  | DD45+6 |  |  | = | 0 |  |  | 0 |  |  | 0 | [10 empty] | 0 |  |  | 0 |  | 0
26 |  | DD45+9 |  |  | = | 0 |  |  | 0 |  |  | 0 | [10 empty] | 0 |  |  | 0 |  | 0
27 |  | DD60+0 |  |  | = | 5 |  |  | 0 |  |  | 5 | [10 empty] | 0 |  |  | 0 |  | 5
28 |  | DD60+3 |  |  | = | 0 |  |  | 0 |  |  | 0 | [10 empty] | 0 |  |  | 0 |  | 0
29 |  | DD60+6 |  |  | = | 0 |  |  | 0 |  |  | 0 | [10 empty] | 0 |  |  | 0 |  | 0
30 |  | DD60+9 |  |  | = | 0 |  |  | 0 |  |  | 0 | [10 empty] | 0 |  |  | 0 |  | 0
31 |  | DD60+35 |  |  | = | 0 |  |  | 0 |  |  | 0 | [10 empty] | 0 |  |  | 0 |  | 0
|  | Total |  |  | = | 34 |  |  | 5 |  |  | 29 | [10 empty] | 0 |  |  | 5 |  | 34

## Project Details
Project Code | Project Name | Client Name | NOA Start Date | LOA End Date | Planning Engineer | PCH | Regional Manager | Project Manger | Section Incharge | Engineer/Supervisor
TA 504 | 765 KV D/C Rishabdeo - Mandsaur & Lilo | PGCIL | 2024-07-15 | 2026-06-14 | Mr. Abir Kumar Das | Mr. Nabajit Baruah |  | Mr. Rajiv Sharma | Prasant Kumar | Khemchand
Ashutosh Prakash
Teklal Mahto
Rameswar Mahto
Rajesh Singh

## Location Summary (hidden)
Over all Tower Location details
S. No. | No of | Location | Type of |  | RC |  | Span | Cumm. | DS Status as on | 306 | 292 | 257 | 102 | 26 | Remarks
| AP | Tower No. | Tower |  |  |  | Length (m) | Span (km) | 2025-11-01 | Foundation | Earthing | Tower Erection | Tack welding | SPT
0 |  | Gantry | Gantry |  |  |  |  | 0
[6 empty] | Gantry | 150.014
3 | AP-1 | 1/0 | DD60+0 | T |  |  |  | 0.15 | Approved | Completed | Completed | Completed
[6 empty] | 1/0 | 290.21
2 | AP-2A | 2A/0 | DD45+0 | T |  |  |  | 0.4402 | Approved | Completed | Completed
[6 empty] | 2A/0 | 378
3 | AP-3 | 2A/1 | DA+0 |  |  |  |  | 0.8182 | Approved | Completed | Completed | Completed
[6 empty] | 2A/1 | 381
4 |  | 2A/2 | DA+3 |  |  |  |  | 1.1992 | Approved | Completed | Completed | Completed
[6 empty] | 2A/2 | 419
5 |  | 2A/3 | DA+3 |  |  |  |  | 1.6182 | Approved | Completed | Completed | Completed
[6 empty] | 2A/3 | 422
6 |  | 2A/4 | DA+3 |  |  |  |  | 2.0402 | Approved | Completed | Completed | Completed
[6 empty] | 2A/4 | 399
7 |  | 2A/5 | DA+3 |  |  |  |  | 2.4392 | Approved | Completed | Completed | Completed
[6 empty] | 2A/5 | 423
8 |  | 2A/6 | DA+6 |  |  |  |  | 2.8622 | Approved | Completed | Completed | Completed
[6 empty] | 2A/6 | 414.992
9 |  | 3A/0 | DD45+3 | T |  |  |  | 3.2772 | Approved | Completed | Completed | Completed
[6 empty] | 3A/0 | 409
10 |  | 3A/1 | DA+3 |  |  |  |  | 3.6862 | Approved | Completed | Completed | Completed
[6 empty] | 3A/1 | 402
11 |  | 3A/2 | DA+3 |  |  |  |  | 4.0882 | Approved | Completed | Completed | Completed
[6 empty] | 3A/2 | 409
12 |  | 3A/3 | DA+0 |  |  |  |  | 4.4972 | Approved | Completed | Completed | Completed |  | Completed |  | 274
[6 empty] | 3A/3 | 337
13 |  | 3A/4 | DA+0 |  |  |  |  | 4.8342 | Approved | Completed | Completed | Completed
[6 empty] | 3A/4 | 365
14 |  | 3A/5 | DA+3 |  |  |  |  | 5.1992 | Approved | Completed | Completed | Completed
[6 empty] | 3A/5 | 378
15 | AP-4 | 3A/6 | DA+0 |  |  |  |  | 5.5772 | Approved | Completed | Completed | Completed
[6 empty] | 3A/6 | 391.467
16 |  | 3B/0 | DB1+9 |  |  |  |  | 5.9687 | Approved | Completed | Completed | Completed
[6 empty] | 3B/0 | 356
17 |  | 3B/1 | DA+3 |  |  |  |  | 6.3247 | Approved | Completed | Completed | Completed
[6 empty] | 3B/1 | 439
18 |  | 3B/2 | DA+9 |  |  |  |  | 6.7637 | Approved | Completed | Completed | Completed
[6 empty] | 3B/2 | 377
19 |  | 3B/3 | DA+6 |  |  |  |  | 7.1407 | Approved | Completed | Completed
[6 empty] | 3B/3 | 455.07 | [8 empty] | 39
20 |  | 4/0 | DB2+9 |  |  |  |  | 7.5958 | Approved | Completed | Completed | Completed
[6 empty] | 4/0 | 344.163
21 |  | 4/5 | DA+6 |  |  |  |  | 7.94 | Approved | Completed | Completed | Completed |  |  | NO CHANGE S
[6 empty] | 4/5 | 365
22 | AP- 4A/0 | 4A/0 | DB1+3 |  |  |  |  | 8.305 | Approved | Completed | Completed | Completed
[6 empty] | 4A/0 | 340
23 |  | 4A/1 | DA+6 |  |  |  |  | 8.645 | Approved | Completed | Completed | Completed
[6 empty] | 4A/1 | 419.999
24 |  | 4A/2 | DA+6 |  |  |  |  | 9.065 | Approved | Completed | Completed | Completed
[6 empty] | 4A/2 | 415
25 |  | 4A/3 | DA+9 |  |  |  |  | 9.48 | Approved | Completed | Completed | Completed
[6 empty] | 4A/3 | 365
26 |  | 4A/4 | DA+6 |  |  |  |  | 9.845 | Approved | Completed | Completed | Completed
[6 empty] | 4A/4 | 330
27 |  | 4A/5 | DA+9 |  |  |  |  | 10.175 | Approved | Completed | Completed | Completed
[6 empty] | 4A/5 | 457
28 |  | 4A/6 | DA+9 |  |  |  |  | 10.632 | Approved | Completed | Completed | Completed
[6 empty] | 4A/6 | 354.612
29 | AP5 | 5/0 | DB1+6 |  |  |  |  | 10.9866 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 5/0 | 428.389
30 |  | 5/1 | DA+6 |  |  |  |  | 11.415 | Approved | Completed | Completed | Completed
[6 empty] | 5/1 | 340
31 |  | 5/2 | DA+9 |  |  |  |  | 11.755 | Approved | Completed | Completed | Completed
[6 empty] | 5/2 | 375
32 |  | 5/3 | DA+9 |  |  |  |  | 12.13 | Approved | Completed | Completed | Completed
[6 empty] | 5/3 | 365
33 |  | 5/4 | DA-1.5 |  |  |  |  | 12.495 | Approved | Completed | Completed | Completed
[6 empty] | 5/4 | 460
34 |  | 5/5 | DA+6 |  |  |  |  | 12.955 | Approved | Completed | Completed | Completed
[6 empty] | 5/5 | 380
35 |  | 5/6 | DA+3 |  |  |  |  | 13.335 | Approved | Completed | Completed | Completed
[6 empty] | 5/6 | 410
36 |  | 5/7 | DA+9 |  |  |  |  | 13.745 | Approved | Completed | Completed | Completed
[6 empty] | 5/7 | 400
37 |  | 5/8 | DA+6 |  |  |  |  | 14.145 | Approved | Completed | Completed | Completed
[6 empty] | 5/8 | 420
38 |  | 5/9 | DA+6 |  |  |  |  | 14.565 | Approved | Completed | Completed | Completed
[6 empty] | 5/9 | 345
39 |  | 5/10 | DA+9 |  |  |  |  | 14.91 | Approved | Completed | Completed | Completed
[6 empty] | 5/10 | 495
40 | AP-5A | 5A/0 | DB1+12 |  |  |  |  | 15.405 | Approved | Completed | Completed | Completed
[6 empty] | 5A/0 | 419.48
41 | AP-6 | 6/0 | DB1+9 |  |  |  |  | 15.8245 | Approved | Completed | Completed | Completed
[6 empty] | 6/0 | 350.52
42 |  | 6/1 | DA+9 |  |  |  |  | 16.175 | Approved | Completed | Completed | Completed
[6 empty] | 6/1 | 445
43 |  | 6/2 | DA+6 |  |  |  |  | 16.62 | Approved | Completed | Completed | Completed
[6 empty] | 6/2 | 390
44 |  | 6/3 | DA+3 |  |  |  |  | 17.01 | Approved | Completed | Completed | Completed
[6 empty] | 6/3 | 350
45 |  | 6/4 | DA+9 |  |  |  |  | 17.36 | Approved | Completed | Completed | Completed
[6 empty] | 6/4 | 490
46 |  | 6/5 | DA+9 |  |  |  |  | 17.85 | Approved | Completed | Completed | Completed
[6 empty] | 6/5 | 350
47 |  | 6/6 | DA-3 |  |  |  |  | 18.2 | Approved | Completed | Completed | Completed
[6 empty] | 6/6 | 347
48 |  | 6/7 | DA+1.5 |  |  |  |  | 18.547 | Approved | Completed | Completed | Completed
[6 empty] | 6/7 | 373
49 |  | 6/8 | DA+3 |  |  |  |  | 18.92 | Approved | Completed | Completed | Completed
[6 empty] | 6/8 | 380
50 |  | 6/9 | DA+6 |  |  |  |  | 19.3 | Approved | Completed | Completed | Completed
[6 empty] | 6/9 | 335
51 |  | 6/10 | DA+1.5 |  |  |  |  | 19.635 | Approved | Completed | Completed | Completed
[6 empty] | 6/10 | 315
52 |  | 6/11 | DA-1.5 |  |  |  |  | 19.95 | Approved | Completed | Completed | Completed
[6 empty] | 6/11 | 410
53 |  | 6/12 | DA+1.5 |  |  |  |  | 20.36 | Approved | Completed | Completed | Completed
[6 empty] | 6/12 | 365.716
54 | AP-7 | 7/0 | DB2+0 |  |  |  |  | 20.7257 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 7/0 | 319.284
55 |  | 7/1 | DA-3 |  |  |  |  | 21.045 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7/1 | 465
56 |  | 7/2 | DA+6 |  |  |  |  | 21.51 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7/2 | 375
57 |  | 7/3 | DA+9 |  |  |  |  | 21.885 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7/3 | 355
58 |  | 7/4 | DA+6 |  |  |  |  | 22.24 | Approved | Completed | Completed | Completed
[6 empty] | 7/4 | 420
59 |  | 7/5 | DA+6 |  |  |  |  | 22.66 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7/5 | 315
60 |  | 7/6 | DA-1.5 |  |  |  |  | 22.975 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7/6 | 450
61 | AP-7A | 7A/0 | DB1+6 |  |  |  |  | 23.425 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7A/0 | 435
62 |  | 7A/1 | DA+1.5 |  |  |  |  | 23.86 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7A/1 | 385
63 |  | 7A/2 | DA+3 |  |  |  |  | 24.245 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7A/2 | 390
64 |  | 7A/3 | DA+3 |  |  |  |  | 24.635 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7A/3 | 405
65 |  | 7A/4 | DA+3 |  |  |  |  | 25.04 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 7A/4 | 390
66 |  | 7A/5 | DA+3 |  |  |  |  | 25.43 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7A/5 | 429.77
67 | AP-8 | 8/0 | DB1+0 |  |  |  |  | 25.8598 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/0 | 350
68 |  | 8/1 | DA-3 |  |  |  |  | 26.2098 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/1 | 330
69 |  | 8/2 | DA+6 |  |  |  |  | 26.5398 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/2 | 390
70 |  | 8/3 | DA+9 |  |  |  |  | 26.9298 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/3 | 400
71 |  | 8/4 | DA+6 |  |  |  |  | 27.3298 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/4 | 345
72 |  | 8/5 | DA+9 |  |  |  |  | 27.6748 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/5 | 350
73 |  | 8/6 | DA+3 |  |  |  |  | 28.0248 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/6 | 335
74 |  | 8/7 | DA+3 |  |  |  |  | 28.3598 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/7 | 415
75 |  | 8/8 | DA+9 |  |  |  |  | 28.7748 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/8 | 375
76 |  | 8/9 | DA+3 |  |  |  |  | 29.1498 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/9 | 375
77 |  | 8/10 | DA+0 |  |  |  |  | 29.5248 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/10 | 375
78 |  | 8/11 | DA+9 |  |  |  |  | 29.8998 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/11 | 415
79 | AP-8A | 8A/0 | DB1+12 |  |  |  |  | 30.3148 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8A/0 | 466.629
80 | AP-9 | 9/0 | DB1+12 |  |  |  |  | 30.7814 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 9/0 | 418.372
81 |  | 9/1 | DA+3 |  |  |  |  | 31.1998 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 9/1 | 410
82 |  | 9/2 | DA+3 |  |  |  |  | 31.6098 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 9/2 | 395
83 |  | 9/3 | DA+0 |  |  |  |  | 32.0048 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 9/3 | 395
84 |  | 9/4 | DA+6 |  |  |  |  | 32.3998 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 9/4 | 425
85 |  | 9/5 | DA+3 |  |  |  |  | 32.8248 | Approved | Completed | Completed | Completed
[6 empty] | 9/5 | 415
86 |  | 9/6 | DA+3 |  |  |  |  | 33.2398 | Approved | Completed | Completed | Completed
[6 empty] | 9/6 | 405
87 |  | 9/7 | DA+9 |  |  |  |  | 33.6448 | Approved | Completed | Completed | Completed
[6 empty] | 9/7 | 435
90 |  | 9/8 | DA+0 |  |  |  |  | 34.0798 | Approved | Completed | Completed
[6 empty] | 9/8 | 405
89 |  | 9/9 | DA+0 |  |  |  |  | 34.4848 | Approved | Completed | Completed
[6 empty] | 9/9 | 435
90 |  | 9/10 | DA+3 |  |  |  |  | 34.9198 | Approved | Completed | Completed
[6 empty] | 9/10 | 395
91 |  | 9/11 | DA+3 |  |  |  |  | 35.3148 | Approved | Completed | Completed | Completed
[6 empty] | 9/11 | 431.548
92 | AP-10 | 10/0 | DB1+6 |  |  |  |  | 35.7463 | Approved | Completed | Completed | Completed
[6 empty] | 10/0 | 363.452
93 |  | 10/1 | DA+3 |  |  |  |  | 36.1098 | Approved | Completed | Completed | Completed
[6 empty] | 10/1 | 295
94 |  | 10/2 | DA+3 |  |  |  |  | 36.4048 | Approved | Completed | Completed
[6 empty] | 10/2 | 345.731
95 | AP-11 | 11/0 | DD45+0 |  |  |  |  | 36.7505 | Approved | Completed | Completed
[6 empty] | 11/0 | 242.893 | [7 empty] | NH
96 | AP-12 | 12/0 | DB1+9 |  |  |  |  | 36.9934 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 12/0 | 329.728 | [7 empty] | 132 KV PL
97 | AP-13 | 13/0 | DD60+9 |  |  |  |  | 37.3231 | Approved | Completed | Completed |  |  | Completed
[6 empty] | 13/0 | 416.878
98 | AP-13A | 13A/0 | DB1+9 |  |  |  |  | 37.74 | Approved | Completed | Completed
[6 empty] | 13A/0 | 480.269
99 | AP-14 | 14/0 | DD60+18 |  | 2 |  |  | 38.2203 | Approved | Completed | Completed
[6 empty] | 14/0 | 223.816 | [7 empty] | 400 KV PL
100 | AP-15 | 15/0 | DD60+25 |  |  |  |  | 38.4441 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 15/0 | 405.915
101 |  | 15/1 | DA+6 |  |  |  |  | 38.85 | Approved | Completed | Completed
[6 empty] | 15/1 | 405
102 |  | 15/2 | DA+3 |  |  |  |  | 39.255 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 15/2 | 420
103 |  | 15/3 | DA+3 |  |  |  |  | 39.675 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 15/3 | 415
104 |  | 15/4 | DA+6 |  |  |  |  | 40.09 | Approved | Completed | Completed | Completed
[6 empty] | 15/4 | 410
105 |  | 15/5 | DA+3 |  |  |  |  | 40.5 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 15/5 | 285
106 |  | 15/6 | DA+9 |  |  |  |  | 40.785 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 15/6 | 355
107 |  | 15/7 | DA+0 |  |  |  |  | 41.14 | Approved | Completed | Completed
[6 empty] | 15/7 | 355
108 |  | 15/8 | DA+1.5 |  |  |  |  | 41.495 | Approved | Completed | Completed | Completed
[6 empty] | 15/8 | 410
109 |  | 15/9 | DA+0 |  |  |  |  | 41.905 | Approved | Completed | Completed
[6 empty] | 15/9 | 430
110 |  | 15/10 | DA-1.5 |  |  |  |  | 42.335 | Approved | Completed | Completed
[6 empty] | 15/10 | 385
111 |  | 15/11 | DA+0 |  |  |  |  | 42.72 | Approved | Completed | Completed
[6 empty] | 15/11 | 455
112 |  | 15/12 | DA+6 |  |  |  |  | 43.175 | Approved | Completed
[6 empty] | 15/12 | 288.425
113 | AP-16 | 16/0 | DC2+0 |  |  |  |  | 43.4634 | Approved | Completed
[6 empty] | 16/0 | 392.694 | [7 empty] | 11KV LINE
114 | AP-17 | 17/0 | DC1+3 |  |  |  |  | 43.8561 | Approved | Completed | Completed
[6 empty] | 17/0 | 398.404 | [7 empty] | 11KV LINE
115 | AP-18 | 18/0 | DB2+6 |  |  |  |  | 44.2545 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 18/0 | 307.595
116 |  | 18/1 | DA+3 |  |  |  |  | 44.5621 | Approved | Completed | Completed | Completed
[6 empty] | 18/1 | 390
117 |  | 18/2 | DA+1.5 |  |  |  |  | 44.9521 | Approved | Completed | Completed | Completed
[6 empty] | 18/2 | 380
118 |  | 18/3 | DA+6 |  |  |  |  | 45.3321 | Approved | Completed | Completed | Completed
[6 empty] | 18/3 | 405
119 |  | 18/4 | DA-3 |  |  |  |  | 45.7371 | Approved | Completed | Completed | Completed
[6 empty] | 18/4 | 335
120 |  | 18/5 | DA+0 |  |  |  |  | 46.0721 | Approved | Completed | Completed | Completed
[6 empty] | 18/5 | 425
121 |  | 18/6 | DA+9 |  |  |  |  | 46.4971 | Approved | Completed | Completed | Completed
[6 empty] | 18/6 | 402
122 |  | 18/7 | DA+1.5 |  |  |  |  | 46.8991 | Approved | Completed | Completed | Completed
[6 empty] | 18/7 | 385.434
123 | AP-19 | 19/0 | DD60+3 |  |  |  |  | 47.2845 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 19/0 | 279.36 | [7 empty] | Rly
124 | AP-20 | 20/0 | DD60+3 |  |  |  |  | 47.5639 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 20/0 | 388.515
125 |  | 20/1 | DA-3 |  |  |  |  | 47.9524 | Approved | Completed | Completed | Completed
[6 empty] | 20/1 | 330
126 |  | 20/2 | DA-3 |  |  |  |  | 48.2824 | Approved | Completed | Completed | Completed
[6 empty] | 20/2 | 340
127 |  | 20/3 | DA+1.5 |  |  |  |  | 48.6224 | Approved | Completed | Completed
[6 empty] | 20/3 | 420
128 |  | 20/4 | DA+3 |  |  |  |  | 49.0424 | Approved | Completed | Completed
[6 empty] | 20/4 | 375
129 |  | 20/5 | DA+0 |  |  |  |  | 49.4174 | Approved | Completed | Completed | Completed
[6 empty] | 20/5 | 355
130 |  | 20/6 | DA-3 |  |  |  |  | 49.7724 | Approved | Completed | Completed | Completed
[6 empty] | 20/6 | 341.652
131 | AP-21 | 21/0 | DB1+0 |  |  |  |  | 50.1141 | Approved | Completed | Completed | Completed
[6 empty] | 21/0 | 326.348
132 |  | 21/1 | DA+0 |  |  |  |  | 50.4404 | Approved | Completed | Completed | Completed
[6 empty] | 21/1 | 427
133 |  | 21/2 | DA+6 |  |  |  |  | 50.8674 | Approved | Completed | Completed
[6 empty] | 21/2 | 410
134 |  | 21/3 | DA+6 |  |  |  |  | 51.2774 | Approved | Completed | Completed
[6 empty] | 21/3 | 405
135 |  | 21/4 | DA+0 |  |  |  |  | 51.6824 | Approved | Completed | Completed
[6 empty] | 21/4 | 300
136 |  | 21/5 | DA+0 |  |  |  |  | 51.9824 | Approved | Completed | Completed
[6 empty] | 21/5 | 415.187
137 | AP-22 | 22/0 | DC2+15 |  |  |  |  | 52.3976 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 22/0 | 259.048 | [7 empty] | 220 kv PL
138 | AP-23 | 23/0 | DB2+9 |  |  |  |  | 52.6566 | Approved | Completed | Completed
[6 empty] | 23/0 | 440.455
139 | AP-23A | 23A/0 | DB1+9 |  |  |  |  | 53.0971 | Approved | Completed | Completed
[6 empty] | 23A/0 | 496.685
140 | AP-24 | 24/0 | DD60+18 |  |  |  |  | 53.5938 | Approved | Completed | Completed
[6 empty] | 24/0 | 244.029 | [7 empty] | 400 kv PL
141 | AP-25 | 25/0 | DD60+18 |  |  |  |  | 53.8378 | Approved | Completed | Completed
[6 empty] | 25/0 | 237.428
142 | AP-26 | 26/0 | DD60+35 |  |  |  |  | 54.0752 | Approved | Completed | Completed
[6 empty] | 26/0 | 203.479 | [7 empty] | 765 kv PL
143 | AP-27 | 27/0 | DD60+35 |  |  |  |  | 54.2787 | Approved | Completed | Completed |  |  | Completed
[6 empty] | 27/0 | 453.688
144 |  | 27/1 | DA+9 |  |  |  |  | 54.7324 | Approved | Completed | Completed
[6 empty] | 27/1 | 345
145 |  | 27/2 | DA-1.5 |  |  |  |  | 55.0774 | Approved | Completed | Completed
[6 empty] | 27/2 | 360
146 |  | 27/3 | DA+1.5 |  |  |  |  | 55.4374 | Approved | Completed | Completed
[6 empty] | 27/3 | 410
147 |  | 27/4 | DA+1.5 |  |  |  |  | 55.8474 | Approved | Completed | Completed
[6 empty] | 27/4 | 350
148 |  | 27/5 | DA-1.5 |  |  |  |  | 56.1974 | Approved | Completed | Completed | Completed
[6 empty] | 27/5 | 355
149 |  | 27/6 | DA-3 |  |  |  |  | 56.5524 | Approved | Completed | Completed
[6 empty] | 27/6 | 274.587
150 | AP-28 | 28/0 | DC2-3 |  |  |  |  | 56.827 | Approved | Completed | Completed
[6 empty] | 28/0 | 211.209 | [7 empty] | NH
151 | AP-29 | 29/0 | DC1+0 |  |  |  |  | 57.0382 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 29/0 | 384.204
152 |  | 29/1 | DA+6 |  |  |  |  | 57.4224 | Approved | Completed | Completed | Completed
[6 empty] | 29/1 | 430
153 |  | 29/2 | DA+0 |  |  |  |  | 57.8524 | Approved | Completed | Completed
[6 empty] | 29/2 | 370
154 |  | 29/3 | DA+0 |  |  |  |  | 58.2224 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 29/3 | 390
155 |  | 29/4 | DA+3 |  |  |  |  | 58.6124 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 29/4 | 435
156 |  | 29/5 | DA+0 |  |  |  |  | 59.0474 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 29/5 | 370
157 | AP-29A/0 | 29A/0 | DB1+0 |  |  |  |  | 59.4174 | Approved | Completed | Completed | Completed
[6 empty] | 29A/0 | 455
158 |  | 29A/1 | DA+6 |  |  |  |  | 59.8724 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 29A/1 | 325
159 |  | 29A/2 | DA+6 |  |  |  |  | 60.1974 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 29A/2 | 395
160 |  | 29A/3 | DA+6 |  |  |  |  | 60.5924 | Approved | Completed | Completed
[6 empty] | 29A/3 | 345
161 |  | 29A/4 | DA+3 |  |  |  |  | 60.9374 | Approved | Completed | Completed | Completed
[6 empty] | 29A/4 | 365
162 |  | 29A/5 | DA+6 |  |  |  |  | 61.3024 | Approved | Completed | Completed | Completed
[6 empty] | 29A/5 | 420
163 |  | 29A/6 | DA+9 |  |  |  |  | 61.7224 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 29A/6 | 364.007
164 | AP-30 | 30/0 | DB1+0 |  |  |  |  | 62.0864 | Approved | Completed | Completed | Completed
[6 empty] | 30/0 | 295.993
165 |  | 30/1 | DA+0 |  |  |  |  | 62.3824 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 30/1 | 425
166 |  | 30/2 | DA+9 |  |  |  |  | 62.8074 | Approved | Completed | Completed | Completed
[6 empty] | 30/2 | 315
167 |  | 30/3 | DA+3 |  |  |  |  | 63.1224 | Approved | Completed | Completed | Completed
[6 empty] | 30/3 | 380
168 |  | 30/4 | DA+9 |  |  |  |  | 63.5024 | Approved | Completed | Completed | Completed
[6 empty] | 30/4 | 430
169 |  | 30/5 | DA+0 |  |  |  |  | 63.9324 | Approved | Completed | Completed
[6 empty] | 30/5 | 380
170 |  | 30/6 | DA+6 |  |  |  |  | 64.3124 | Approved | Completed | Completed | Completed
[6 empty] | 30/6 | 335
171 |  | 30/7 | DA-3 |  |  |  |  | 64.6474 | Approved | Completed | Completed | Completed
[6 empty] | 30/7 | 395
172 |  | 30/8 | DA+3 |  |  |  |  | 65.0424 | Approved | Completed | Completed | Completed
[6 empty] | 30/8 | 390
173 |  | 30/9 | DA-3 |  |  |  |  | 65.4324 | Approved | Completed | Completed | Completed
[6 empty] | 30/9 | 350
174 |  | 30/10 | DA+3 |  |  |  |  | 65.7824 | Approved | Completed | Completed | Completed
[6 empty] | 30/10 | 428.239
175 | AP-31 | 31/0 | DB1+0 |  |  |  |  | 66.2106 | Approved | Completed | Completed | Completed
[6 empty] | 31/0 | 376.761
176 |  | 31/1 | DA+3 |  |  |  |  | 66.5874 | Approved | Completed | Completed | Completed
[6 empty] | 31/1 | 410
177 |  | 31/2 | DA+1.5 |  |  |  |  | 66.9974 | Approved | Completed | Completed | Completed
[6 empty] | 31/2 | 430
178 |  | 31/3 | DA+3 |  |  |  |  | 67.4274 | Approved | Completed | Completed | Completed
[6 empty] | 31/3 | 380
179 |  | 31/4 | DA-1.5 |  |  |  |  | 67.8074 | Approved | Completed | Completed | Completed
[6 empty] | 31/4 | 445
180 |  | 31/5 | DA+6 |  |  |  |  | 68.2524 | Approved | Completed | Completed | Completed
[6 empty] | 31/5 | 385
181 |  | 31/6 | DA+9 |  |  |  |  | 68.6374 | Approved | Completed | Completed | Completed
[6 empty] | 31/6 | 420
182 |  | 31/7 | DA+0 |  |  |  |  | 69.0574 | Approved | Completed | Completed | Completed
[6 empty] | 31/7 | 415
183 |  | 31/8 | DA+0 |  |  |  |  | 69.4724 | Approved | Completed | Completed | Completed
[6 empty] | 31/8 | 310
184 |  | 31/9 | DA+1.5 |  |  |  |  | 69.7824 | Approved | Completed | Completed | Completed
[6 empty] | 31/9 | 445
185 |  | 31/10 | DA+4.5 |  |  |  |  | 70.2274 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 31/10 | 316.608
186 | AP-32 | 32/0 | DB2+0 |  |  |  |  | 70.544 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32/0 | 385.51
187 |  | 32/1 | DA+6 |  |  |  |  | 70.9295 | Approved | Completed | Completed | Completed
[6 empty] | 32/1 | 390
188 |  | 32/2 | DA+9 |  |  |  |  | 71.3195 | Approved | Completed | Completed | Completed
[6 empty] | 32/2 | 410
189 |  | 32/3 | DA+6 |  |  |  |  | 71.7295 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32/3 | 430
190 |  | 32/4 | DA+9 |  |  |  |  | 72.1595 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32/4 | 390
191 |  | 32/5 | DA+9 |  | 2 |  |  | 72.5495 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32/5 | 439
192 |  | 32/6 | DA+9 |  | 2 |  |  | 72.9885 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32/6 | 360
193 |  | 32/7 | DA+3 |  |  |  |  | 73.3485 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32/7 | 479
194 | AP-32A/0 | 32A/0 | DB1+9 |  |  |  |  | 73.8275 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32A/0 | 402
195 |  | 32A/1 | DA+6 |  |  |  |  | 74.2295 | Approved | Completed | Completed | Completed
[6 empty] | 32A/1 | 438.439
196 | AP-33 | 33/0 | DB1+9 |  | 2 |  |  | 74.6679 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 33/0 | 441.561
197 |  | 33/1 | DA+9 |  | 2 |  |  | 75.1095 | Approved | Completed | Completed | Completed
[6 empty] | 33/1 | 395
198 |  | 33/2 | DA+9 |  |  |  |  | 75.5045 | Approved | Completed | Completed | Completed
[6 empty] | 33/2 | 435
199 |  | 33/3 | DA+3 |  |  |  |  | 75.9395 | Approved | Completed | Completed | Completed
[6 empty] | 33/3 | 405
200 |  | 33/4 | DA+3 |  |  |  |  | 76.3445 | Approved | Completed | Completed | Completed
[6 empty] | 33/4 | 420
201 |  | 33/5 | DA+0 |  |  |  |  | 76.7645 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 33/5 | 405
202 |  | 33/6 | DA+6 |  |  |  |  | 77.1695 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 33/6 | 415
203 |  | 33/7 | DA+6 |  |  |  |  | 77.5845 | Approved | Completed | Completed | Completed
[6 empty] | 33/7 | 355
204 |  | 33/8 | DA+3 |  |  |  |  | 77.9395 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 33/8 | 380
205 |  | 33/9 | DA+1.5 |  |  |  |  | 78.3195 | Approved | Completed | Completed | Completed
[6 empty] | 33/9 | 398.203
206 | AP-34 | 34/0 | DB1+6 |  |  |  |  | 78.7177 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 34/0 | 441.798
207 |  | 34/1 | DA+9 |  |  |  |  | 79.1595 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/1 | 395
208 |  | 34/2 | DA+9 |  |  |  |  | 79.5545 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/2 | 375
209 |  | 34/3 | DA+1.5 |  |  |  |  | 79.9295 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/3 | 445
210 |  | 34/4 | DA+6 |  |  |  |  | 80.3745 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/4 | 395
211 |  | 34/5 | DA+9 |  |  |  |  | 80.7695 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/5 | 435
212 |  | 34/6 | DA+3 |  |  |  |  | 81.2045 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/6 | 330
213 |  | 34/7 | DA+0 |  |  |  |  | 81.5345 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/7 | 330
214 |  | 34/8 | DA+0 |  |  |  |  | 81.8645 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/8 | 400
215 |  | 34/9 | DA+1.5 |  |  |  |  | 82.2645 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/9 | 310
216 |  | 34/10 | DA-3 |  |  |  |  | 82.5745 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/10 | 315
217 |  | 34/11 | DA+1.5 |  |  |  |  | 82.8895 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/11 | 375
218 |  | 34/12 | DA+3 |  |  |  |  | 83.2645 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/12 | 351.79
219 | AP-35 | 35/0 | DB2+0 |  |  |  |  | 83.6163 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 35/0 | 393.209
220 |  | 35/1 | DA+6 |  |  |  |  | 84.0095 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 35/1 | 435
221 |  | 35/2 | DA+6 |  |  |  |  | 84.4445 | Approved | Completed |  | Completed
[6 empty] | 35/2 | 390
222 |  | 35/3 | DA-3 |  |  |  |  | 84.8345 | Approved | Completed
[6 empty] | 35/3 | 405
223 |  | 35/4 | DA+9 |  |  |  |  | 85.2395 | Approved | Completed | Completed | Completed
[6 empty] | 35/4 | 435
224 |  | 35/5 | DA+9 |  |  |  |  | 85.6745 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 35/5 | 360
225 |  | 35/6 | DA+6 |  |  |  |  | 86.0345 | Approved | Completed | Completed | Completed
[6 empty] | 35/6 | 395
226 |  | 35/7 | DA+3 |  |  |  |  | 86.4295 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 35/7 | 440
227 |  | 35/8 | DA+6 |  |  |  |  | 86.8695 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 35/8 | 400
228 |  | 35/9 | DA+1.5 |  |  |  |  | 87.2695 | Approved | Completed | Completed | Completed
[6 empty] | 35/9 | 440
229 |  | 35/10 | DA+3 |  |  |  |  | 87.7095 | Approved | Completed
[6 empty] | 35/10 | 330
230 |  | 35/11 | DA+3 |  |  |  |  | 88.0395 | Approved | Completed | Completed | Completed
[6 empty] | 35/11 | 493.084
231 | AP-36 | 36/0 | DB2+3 |  |  |  |  | 88.5326 | Approved | Completed | Completed |  |  | Completed
[6 empty] | 36/0 | 453.999
232 |  | 36A/0 | DB1+9 |  |  |  |  | 88.9866 | Approved | Completed |  | Completed
[6 empty] | 36A/0 | 451
233 |  | 36A/1 | DA+3 |  |  |  |  | 89.4376 | Approved | Completed | Completed | Completed
[6 empty] | 36A/1 | 389
234 |  | 36A/2 | DA+9 |  |  |  |  | 89.8266 | Approved | Completed | Completed | Completed
[6 empty] | 36A/2 | 451.523
235 | AP-37 | 37/0 | DB2+3 |  |  |  |  | 90.2781 | Approved | Completed | Completed
[6 empty] | 37/0 | 401.394
236 |  | 37/1 | DA+3 |  |  |  |  | 90.6795 | Approved | Completed | Completed
[6 empty] | 37/1 | 430
237 |  | 37/2 | DA+3 |  |  |  |  | 91.1095 | Approved | Completed | Completed
[6 empty] | 37/2 | 405
238 |  | 37/3 | DA-1.5 |  |  |  |  | 91.5145 | Approved | Completed | Completed
[6 empty] | 37/3 | 430
239 |  | 37/4 | DA+9 |  |  |  |  | 91.9445 | Approved | Completed | Completed | Completed
[6 empty] | 37/4 | 410
240 |  | 37/5 | DA+3 |  |  |  |  | 92.3545 | Approved | Completed | Completed | Completed
[6 empty] | 37/5 | 420
241 | AP-37A | 37A/0 | DB1+0 |  |  |  |  | 92.7745 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 37A/0 | 280
242 |  | 37A/1 | DA+3 |  |  |  |  | 93.0545 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 37A/1 | 345
243 |  | 37A/2 | DA+1.5 |  |  |  |  | 93.3995 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 37A/2 | 330
244 |  | 37A/3 | DA+3 |  |  |  |  | 93.7295 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 37A/3 | 455
245 |  | 37A/4 | DA+9 |  |  |  |  | 94.1845 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 37A/4 | 340
246 |  | 37A/5 | DA+3 |  |  |  |  | 94.5245 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 37A/5 | 435
247 |  | 37A/6 | DA+3 |  |  |  |  | 94.9595 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 37A/6 | 398.589
248 | AP-38 | 38/0 | DB1+3 |  |  |  |  | 95.3581 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/0 | 426.411
249 |  | 38/1 | DA+0 |  |  |  |  | 95.7845 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/1 | 390
250 |  | 38/2 | DA+0 |  |  |  |  | 96.1745 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/2 | 335
251 |  | 38/3 | DA+3 |  |  |  |  | 96.5095 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/3 | 440
252 |  | 38/4 | DA+1.5 |  |  |  |  | 96.9495 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/4 | 280
253 |  | 38/5 | DA+3 |  |  |  |  | 97.2295 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/5 | 450
254 |  | 38/6 | DA+6 |  |  |  |  | 97.6795 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/6 | 285
255 |  | 38/7 | DA+9 |  |  |  |  | 97.9645 | Approved | Completed | Completed | Completed
[6 empty] | 38/7 | 445
256 |  | 38/8 | DA+1.5 |  |  |  |  | 98.4095 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/8 | 360
257 |  | 38/9 | DA+0 |  |  |  |  | 98.7695 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/9 | 430
258 |  | 38/10 | DA+3 |  |  |  |  | 99.1995 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/10 | 322.266
259 | AP-39 | 39/0 | DB2+0 |  |  |  |  | 99.5218 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 39/0 | 392.73
260 |  | 39/1 | DA-1.5 |  |  |  |  | 99.9145 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/1 | 395
261 |  | 39/2 | DA+3 |  |  |  |  | 100.3095 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/2 | 385
262 |  | 39/3 | DA+1.5 |  |  |  |  | 100.6945 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/3 | 340
263 |  | 39/4 | DA+3 |  |  |  |  | 101.0345 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/4 | 395
264 |  | 39/5 | DA+1.5 |  |  |  |  | 101.4295 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/5 | 410
265 |  | 39/6 | DA+1.5 |  |  |  |  | 101.8395 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/6 | 415
266 |  | 39/7 | DA+3 |  |  |  |  | 102.2545 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/7 | 415
267 |  | 39/8 | DA+1.5 |  |  |  |  | 102.6695 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/8 | 350
268 |  | 39/9 | DA+6 |  |  |  |  | 103.0195 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/9 | 425
269 |  | 39/10 | DA+3 |  |  |  |  | 103.4445 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/10 | 350
270 |  | 39/11 | DA+6 |  |  |  |  | 103.7945 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/11 | 444.081
271 | AP-40 | 40/0 | DB1+6 |  |  |  |  | 104.2386 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 40/0 | 260.918
272 |  | 40/1 | DA+9 |  | 2 |  |  | 104.4995 | Approved | Completed |  | Completed
[6 empty] | 40/1 | 385
273 |  | 40/2 | DA+6 |  |  |  |  | 104.8845 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 40/2 | 435
274 |  | 40/3 | DA+3 |  |  |  |  | 105.3195 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 40/3 | 385
275 |  | 40/4 | DA+6 |  |  |  |  | 105.7045 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 40/4 | 455
276 |  | 40/5 | DA+9 |  |  |  |  | 106.1595 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 40/5 | 370
277 |  | 40/6 | DA+9 |  |  |  |  | 106.5295 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 40/6 | 400
278 |  | 40/7 | DA+3 |  |  |  |  | 106.9295 | Approved | Completed | Completed | Completed
[6 empty] | 40/7 | 350
279 |  | 40/8 | DA-1.5 |  |  |  |  | 107.2795 | Approved | Completed | Completed | Completed
[6 empty] | 40/8 | 470
280 |  | 40/9 | DA+9 |  |  |  |  | 107.7495 | Approved | Completed | Completed | Completed
[6 empty] | 40/9 | 355
281 |  | 40/10 | DA+3 |  |  |  |  | 108.1045 | Approved | Completed | Completed | Completed
[6 empty] | 40/10 | 485
282 |  | 40/11 | DA+9 |  |  |  |  | 108.5895 | Approved | Completed | Completed | Completed
[6 empty] | 40/11 | 315
283 | AP-40A | 40A/0 | DB1+9 |  |  |  |  | 108.9045 | Approved | Completed | Completed | Completed
[6 empty] | 40A/0 | 410.607
284 | AP-41 | 41/0 | DB1+9 |  |  |  |  | 109.3151 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 41/0 | 358
285 |  | 41/1 | DA+9 |  |  |  |  | 109.6731 | Approved | Completed |  | Completed
[6 empty] | 41/1 | 465.782
286 | AP-42 | 42/0 | DB2+0 |  |  |  |  | 110.1389 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 42/0 | 419.998
287 |  | 42/1 | DA+3 |  |  |  |  | 110.5589 | Approved | Completed | Completed | Completed
[6 empty] | 42/1 | 375
288 |  | 42/2 | DA+9 |  |  |  |  | 110.9339 | Approved | Completed | Completed | Completed
[6 empty] | 42/2 | 464
289 |  | 42/3 | DB1+9 |  |  |  |  | 111.3979 | Approved | Completed | Completed | Completed
[6 empty] | 42/3 | 424.891
290 | AP-43 | 43/0 | DB1+0 |  |  |  |  | 111.8228 | Approved | Completed
[6 empty] | 43/0 | 341.866
291 |  | 43/1 | DA-1.5 |  |  |  |  | 112.1647 | Approved | Completed
[6 empty] | 43/1 | 375
292 |  | 43/2 | DA+6 |  |  |  |  | 112.5397 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 43/2 | 375
293 |  | 43/3 | DA-1.5 |  |  |  |  | 112.9147 | Approved | Completed | Completed | Completed
[6 empty] | 43/3 | 355
294 |  | 43/4 | DA+0 |  |  |  |  | 113.2697 | Approved | Completed | Completed | Completed
[6 empty] | 43/4 | 405
295 |  | 43/5 | DC2+0 |  |  |  |  | 113.6747 | Approved | Completed |  |  |  |  | TP tower modified cross arms
[6 empty] | 43/5 | 375
296 |  | 43/6 | DA+3 |  |  |  |  | 114.0497 | Approved | Completed | Completed | Completed
[6 empty] | 43/6 | 385
297 |  | 43/7 | DA+0 |  |  |  |  | 114.4347 | Approved | Completed | Completed | Completed
[6 empty] | 43/7 | 415
298 |  | 43/8 | DA+9 |  |  |  |  | 114.8497 | Approved | Completed | Completed | Completed
[6 empty] | 43/8 | 409.546
299 | AP-44 | 44/0 | DB1+6 |  |  |  |  | 115.2592 | Approved | Completed |  | Completed
[6 empty] | 44/0 | 400
300 |  | 44/1 | DA+3 |  |  |  |  | 115.6592 | Approved | Completed | Completed | Completed
[6 empty] | 44/1 | 427
301 |  | 44/2 | DA+3 |  |  |  |  | 116.0862 | Approved | Completed | Completed | Completed
[6 empty] | 44/2 | 366
302 |  | 44/3 | DA+3 |  |  |  |  | 116.4522 | Approved | Completed | Completed | Completed
[6 empty] | 44/3 | 350
303 |  | 44/4 | DA+0 |  |  |  |  | 116.8022 | Approved | Completed | Completed | Completed
[6 empty] | 44/4 | 383
304 |  | 44/5 | DA+0 |  |  |  |  | 117.1852 | Approved | Completed | Completed | Completed
[6 empty] | 44/5 | 457.155
305 | AP45 | 45/0 | DB1+9 |  |  |  |  | 117.6424 | Approved | Completed |  | Completed |  |  | PLC
[6 empty] | 45/0 | 208.53
306 | AP46 | 46/0 | DB1+12 | [5 empty] | Approved | Completed |  | Completed |  |  | PLC
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DD60+0 to gantry
Note on D6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DC2+0 to DD60+0
Note on D202: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DD60+25 to DD60+18