## TB401 DPR..... (hidden)
| Project Code |  | TB-401 |  | Date |  | 2026-08-11 | LOA Start Date |  |  | 2023-04-25 | Business Head (T&D)- India & Sri Lanka |  |  | Rajinder Gupta
| Project Name |  | 765KV D/C Fategarh-III Beawar Transmission Line |  |  |  |  | LOA End Date |  |  | 2024-07-25 | PCH |  |  | Sivaraman Nataraajan
| Client Name |  | Strelite Power |  |  |  |  | Time Extn |  |  | 2024-07-25 | Regional Manager |  |  | Sandeep Singh Kumar
| LE Value |  | Rs 312 Cr -Supply -Rs 227.5 Cr.; Service.-Rs 84.4 Cr |  |  |  |  | Planning |  |  | Shah Ali Khan | Project Manager |  |  | Virender Gupta
Activity | Unit | LOA Qty. | LE Qty | Progress till Last Month | Balance | L2 for Dec'23 | Plan for Dec.'23 | Today's Progress | Month Progress | WIP | Gangs at Present | L2 Till Month-Dec.23 | Progress Till Date | Balance Work | Remarks
Route Alignment | km | 215 | 202 | 167 | 35 | 0 | 35 |  |  |  |  | 215 | 167 | 35 | 35 Km is hold due to ROW issues
Detailed Survey | km | 215 | 202 | 202 | 0 | 0 | [5 empty] | 215 | 202 | 0 | SPTL Approved -202/202-Kms
Check Survey | km | 215 | 202 | 92.704 | 109.296 | 20 | 50 |  | 17.852 |  |  | 160 | 110.556 | 91.444 | 1. Total 7.854 Km is under review of SPTL. 2. Total check survey completed (Field work) 167 Km. 3. Total 60 Km check survey is hold due to row issues & Other issues.
Foundation | Nos | 534 | 521 | 109 | 412 | 75 | 30 |  | 1 | 4 | 3 | 399 | 110 | 411 |  | 12.48% | -2.434% | -13 | 48 | 306
Earthing | Nos | 534 | 521 | 106 | 415 | 75 | 30 |  | 2 |  |  | 399 | 108 | 413 |  | 12.48%
Tower Erection | Nos | 534 | 521 | 45 | 476 | 75 | 40 | 2 | 6 | 5 | 5 | 260 | 51 | 470 | 56/2 58/15 Complete | 12.48%
Tack welding | Nos | 534 | 521 | 15 | 506 | 75 | 40 | 1 | 3 | 1 | 1 | 260 | 18 | 503 | 56/7 complete | 12.48%
Stringing | Km | 215 | 202 | 0 | 202 | 20 | [5 empty] | 25 | 0 | 202 |  | 10.22% |  | 68.21%
#DIV/0!

## Eng. (hidden)
Tower | Tower Design |  | Test Tower |  | Balance Structural Drawing. |  | Tower | Stub & Template Drawings | Foundation
Types |  |  | Structural Drawing(BTB+0) |  | (3M/6M/9M) |  | Testing |  | Design/Drg
| Target | Status | Target | Status | Target | Status |  |  | Target | Status
DA Tower | 2023-05-12 | Approved | 2023-06-04 | Approved | 2023-06-24 | Approved for proto | Completed | Approved | 15-July | Approved
DB Tower | 2023-05-30 | Approved | 2023-07-30 | Approved | 2023-07-19 | Approvedin Cat-B | Completed | Approved for Proto | DB all Fdn. By 25 -July | Approved
DD Tower | 2023-06-21 | Approved | 30-Sept. | Approved in Cat -B | 2023-08-20 | Approved in Cat -B | Completed | Approved in Cat -B | 2023-07-31 | Approved
DC Tower | 2023-07-16 | Approved | 2023-10-08 | Approved in Cat -B | 2023-09-19 | Approved in Cat -B | Completed | Approved in Cat -B | 2023-08-25 | Approved

## Fdn (Pkg -G Section -I) (hidden)
KEC INTERNATIONAL LIMITED | [10 empty] | Date: | 2026-08-11
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
FOUNDATION
Sl. No. | Month Sl. No. | JMC No. | Location No. | Tower Type | Classification | Excavation Start | Dt. of Start | Dt. of Concrete | Name of Sub-Contractor | KEC representative | KEC Section In-Charge | Remarks
1 | 1 |  | 32/7 | DA+0 | SANDY | 23.10.23 | 25.10.23 | 28.10.23 | Shakti Construction | Kumar Nayak | Jish C Verghese | Complete
2 | 2 |  | 32/5 | DA+6 | SANDY | 29.10.23 | 31.10.23 | 04.11.2023 | Shakti Construction | Kumar Nayak | Jish C Verghese | Complete
3 | 3 |  | 32/1 | DA+9 | SANDY | 03.11.23 | 06.11.23 | 10.11.23 | Shakti Construction | Kumar Nayak | Jish C Verghese | Complete
4 | 4 |  | 30/2 | DA+0 | SANDY | 13.11.23 | 15.11.23 | 16.11.23 | Shakti Construction | Kumar Nayak | Jish C Verghese | Complete
5 | 5 |  | 32/0 | DB2+6 | SANDY | 18.11.23 | 20.11.23 | 28.11.23 | Shakti Construction | Dipesh | Jish C Verghese | Complete
Dec-23
1 | 6 |  | 31/3 | DA+0 | SANDY | 28.11.23 | 30.11.23 | 04.12.23 | Shakti Construction | Dipesh | Jish C Verghese | Complete

## Sheet2 (hidden)
S.No | Line | Activity | UOM | LOA Qty | L2 till Sep'25 | Completed till Date | Balance | WIP | Gangs | Remarks
1 | Samba- Jalandhar | Survey | Km | 144 | 70 | 129.36 | 14.64 |  | 2
|  | Foundation | Nos | 434 | 17 | 2 | 432 | 4 | 3
2 | Kishepur- Samba | Survey | Km | 33.103 | 20 | 8.56 | 24.543 | 0.3 | 1
|  | Foundation | Nos | 129 |  |  | 129
3 | LILO-Kisthwar | Survey | Km | 2.18 | 2.18 | 2.18 | 0
|  | Foundation | Nos | 14 | 6 |  | 14
| Total | Survey | Km | 179.283 | 92.18 | 140.1 | 39.183 | 0.3 | 3
|  | Foundation | Nos | 577 | 23 | 2 | 575 | 4 | 3
[11 empty] | S.No | Loc | TOT | S.No | Loc | TOT
[11 empty] | 1 | AP156 | DC+0 | 11 | AP91 | DD+25
[11 empty] | 2 | 70/2 | DA+0 | 12 | 153/2 | DA+3
[11 empty] | 3 | 153/1 | DA+0
[11 empty] | 4 | AP111 | DC+0
[11 empty] | 5 | 136/3 | DA+0
[11 empty] | 6 | 157/1 | DA+0
[11 empty] | 7 | AP150 | DC+0
[11 empty] | 8 | AP70 | DC+3
[11 empty] | 9 | 136/4 | DA+3
[11 empty] | 10 | AP68 | DB+0

## Sheet3 (hidden)
Line | Activity | Section | L2 Oct'25 | Plan Oct'25 | L2 Nov'25 | Plan Nov'25 | L2 Dec'25 | Plan Dec'25 | L2 (Oct'25-Dec'25) | Plan (Oct'25-Dec'25)
Samba-Jalandhar | FDN | Jammu | 25 | 10 | 35 | 10 | 40 | 20 | 100 | 110
| Gangs |  |  | 3 |  | 3 |  | 6
| FDN | Punjab |  | 15 |  | 25 |  | 30
| Gangs |  |  | 5 |  | 6 |  | 6
Kishenpur-Samba | FDN | Jammu | 2 |  | 7 | 5 | 10 | 8 | 19 | 13
| Gangs |  |  |  |  | 3 |  | 4
LILO-Kishtwar | FDN | Kishtwar | 2 |  | 2 | 1 |  | 1 | 4 | 2
| Gangs |  |  |  |  | 1 |  | 1
Total | FDN |  | 29 | 25 | 44 | 41 | 50 | 59 | 123 | 125
| Gangs |  |  | 8 |  | 13 |  | 17

## Sheet4 (hidden)
Line | Portion | Section | Length | ROW Lead | ROW Team | Remarks
|  |  | Km |  | Currently Working
Samba-Jalandhar | Jammu | Gantry-AP52 | 47 | Karmanya Pathania | ROW Team-1 Akhil S ( Engineer) / Radhe Shyam (Supervisor) | At site since the works are in initial phase , hence we have engaged site engineer/supervisor for ROW document collection for time being , further we can engage separate ROW team as per requirement
| Punjab | AP52 - AP115 | 47 |  | ROW Team -2 K Govind ( Section In charge) / Kuldeep Singh ( DET)
|  | AP115 - AP187 | 48 |  | ROW Team -3 Manish Nirala (Section In charge) / Govardhan (DET)
Kishenpur-Samba |  | Gantry- AP109 | 33 |  | ROW Team -4 Mukesh ( Admin) /Yadhuveer (Supervisor) | Due to heavy rains/landslides local administration blocked the roads
LILO | Kishtewar | AP1-Tapping Point | 2.1 |  |  | Due to heavy rains/landslides local administration blocked the roads

## ROW (hidden)
KEC INTERNATIONAL LIMITED |  |  |  |  | Date | 2026-03-02
400kv D/C Samba-Jalandhar T/L-Punjab Portion
|  |  | Submitted | 109 | 90
|  |  | File Ready | 10 | 8
S.No | Tower | TOT | Foundation Completion Status | Crop | Land | Remarks
1 | AP53 | DC+0
2 | AP54 | DC+6
3 | AP55 | DD+3
4 | 55/1 | DA+6
5 | AP56 | DC+3
6 | 56/1 | DA+6
7 | 56/2 | DA+3
8 | 56/3 | DA+6 | WIP
9 | 56/4 | DA+6
10 | AP57 | DD+3
11 | 57/1 | DA+0
12 | 57/2 | DA+0
13 | AP58 | DC+0
14 | AP59 | DD+6
15 | 59/1 | DA+3
16 | AP60 | DB+6
17 | 60/1 | DA+0
18 | AP61 | DC+0
19 | 61/1 | DA+0
20 | AP62 | DB+0
21 | 62/1 | DA+0
22 | 62/2 | DA+0
23 | AP63 | DB+9
24 | AP64 | DC+9
25 | 64/1 | DA+0
26 | AP65 | DB+0
27 | 65/1 | DA+0
28 | 65/2 | DA+6
29 | 65/3 | DA+0
30 | 65/4 | DA+3
31 | 65/5 | DA+3
32 | AP66 | DC+0
33 | AP67 | DD+0
34 | 67/1 | DA+0
35 | 67/2 | DA+0 | WIP
36 | 67/3 | DA+0 | C
37 | AP68 | DB+0 | C | Submitted | Submitted
38 | AP69 | DB+0 | C
39 | 69/1 | DA+0 | C | Submitted | Submitted
40 | 69/2 | DA+0 | C | Submitted | Submitted
41 | 69/3 | DA+0 | C | Submitted | Submitted
42 | AP70 | DC+3 | C | File Ready | File Ready
43 | 70/1 | DA+9 | C | File Ready
44 | 70/2 | DA+0 | C | File Ready
45 | AP70/3 | DD+18
46 | AP71 | DC+9 | WIP
47 | 71/1 | DA+3 |  | Submitted | Submitted
48 | 71/2 | DA+9 | C
49 | 71/3 | DA+6 | C | Submitted
50 | AP72 | DB+3 | C | Submitted | Submitted
51 | 72/1 | DA+3 | C | Submitted | Submitted
52 | 72/2 | DA+6 | C | Submitted
53 | AP74 | DB+0 | C | Submitted | Submitted
54 | AP75 | DB+9 | C | Submitted | Submitted
55 | AP76 | DC+9
56 | 76/1 | DA+0 | C | Submitted | Submitted
57 | 76/2 | DA+3 | C | Submitted | Submitted
58 | 76/3 | DA+3 | C | Submitted | Submitted
59 | AP77 | DB+3 | C | Submitted | Submitted
60 | 77/1 | DA+3 | C | Submitted | Submitted
61 | 77/2 | DB+0 | C | Submitted | Submitted
62 | 77/3 | DA+0
63 | AP78 | DB+9
64 | AP79 | DD+9 | C | Submitted | Submitted
65 | AP80 | DD+0 | C | Submitted | Submitted
66 | 80/1 | DB+3 | C | File Ready |  | Court Case , Indigrid rejected to submit
67 | AP81 | DD+9
68 | AP82 | DD+3
69 | 82/1 | DA+0 | C | Submitted | Submitted
70 | 82/2 | DA+3 | C | Submitted | Submitted
71 | AP83 | DD+25
72 | AP84 | DD+18
73 | AP85 | DB+0 | C | Submitted | Submitted
74 | 85/1 | DA+9 | C | Submitted | Submitted
75 | AP86 | DC+0
76 | 86/1 | DA+3 | C | File Ready | File Ready
77 | AP87 | DB+9 | C
78 | 87/1 | DA+3
79 | 87/2 | DA+3 | C | Submitted | Submitted
80 | AP88 | DD+18
81 | AP89 | DD+18
82 | 89/1 | DA+3 | C | Submitted | Submitted
83 | AP90 | DD+0 | C | Submitted | Submitted
84 | 90/1 | DA+3 | C | Submitted | Submitted
85 | 90/2 | DA+0 | C | Submitted | Submitted
86 | AP91 | DD+25 | C | File Ready
87 | AP92 | DD+25 | C | Submitted | Submitted
88 | 92/1 | DA+3 | C | Submitted | Submitted
89 | 92/2 | DA+6 | C | Submitted | Submitted
90 | 92/3 | DA+0 | C | Submitted | Submitted
91 | AP93 | DC+0 | C | Submitted | Submitted
92 | 93/1 | DA+0 | C | Submitted | Submitted
93 | 93/2 | DA+0 | C | Submitted | Submitted
94 | AP94 | DB+0 | C | Submitted | Submitted
95 | AP95 | DC+3 | C | Submitted | Submitted
96 | 95/1 | DA+0 | C | Submitted | Submitted
97 | 95/2 | DA+0 | C | Submitted | Submitted
98 | 95/3 | DA+0 | C | Submitted | Submitted
99 | 95/4 | DA+0 | C | Submitted | Submitted
100 | AP96 | DC+0 | C | Submitted | Submitted
101 | AP97 | DD+3 | C | Submitted | Submitted
102 | 97/1 | DA+0 | C | Submitted |  | Panchayat Land
103 | 97/2 | DA+0 | C | Submitted | Submitted
104 | 97/3 | DA+3 | C | Submitted | Submitted
105 | AP98 | DB+3 | C | Submitted | Submitted
106 | 98/1 | DA+3 | C | Submitted | Submitted
107 | AP99 | DB+0 | C | Submitted | Submitted
108 | 99/1 | DA+9 | C | Submitted | Submitted
109 | AP100 | DC+3 | C | File Ready | File Ready
110 | AP101 | DC+0
111 | AP102 | DB+0 | C | Submitted | Submitted
112 | 102/1 | DA+6 | C | Submitted | Submitted | Payment Dispute with landownder
113 | AP103 | DD+0 | C | Submitted | Submitted
114 | 103/1 | DA+0 | C | Submitted | Submitted
115 | AP104 | DB+0 | C | Submitted | Submitted
116 | 104/1 | DA+3 | C | Submitted | Submitted
117 | AP105 | DD+3
118 | AP106 | DD+6 | C | Submitted | Submitted
119 | 106/1 | DA+0 | C | File Ready |  | File Ready, land owner issue
120 | AP107 | DB+0
121 | AP108 | DD+25 | WIP
122 | AP109 | DD+30
123 | AP110 | DD+0
124 | AP111 | DC+0 | C | Submitted |  | Land Form pending from Indigrid
125 | AP112 | DD+30
126 | AP113 | DD+25
127 | AP114 | DB+0 | C
128 | AP115 | DB+0 | C | Submitted | Submitted
129 | 115/1 | DA+6 | C
130 | AP116 | DCT+0 | C | Submitted | Submitted
131 | 116/1 | DA+0 | C | Submitted | Submitted
132 | AP117 | DB+0 | C | Submitted | Submitted
133 | 117/1 | DA+0 | C | Submitted | Submitted
134 | 117/2 | DA+3 | C | Submitted | Submitted
135 | 117/3 | DA+0 | C | Submitted | Submitted
136 | AP118 | DC+0 | C | Submitted | Submitted
137 | 118/1 | DA+0 | C | Submitted | Submitted
138 | AP119 | DC+0
139 | 119/1 | DA+0
140 | AP120 | DD+0
141 | 120/1 | DA+3
142 | 120/2 | DA+6
143 | AP121 | DC+3
144 | 121/1 | DA+0
145 | 121/2 | DA+0
146 | AP122 | DB+0
147 | 122/1 | DA+3
148 | AP123 | DC+0
149 | AP124 | DB+9
150 | AP125 | DD+18
151 | AP126 | DB+ 0
152 | AP127 | DD+30 | WIP
153 | AP128 | DD +30
154 | AP129 | DB+9 | C | Submitted | Submitted
155 | AP130 | DD+18 | C | Submitted | Submitted
156 | 130/1 | DA +0 | C | Submitted | Submitted
157 | 130/2 | DA+0 | C | Submitted | Submitted
158 | AP131 | DC +0 | C | Submitted | Submitted
159 | 131/1 | DA+3 | C | Submitted | Submitted
160 | 131/2 | DA+3 | C | Submitted | Submitted
161 | 131/3 | DA+3 | C | Submitted | Submitted
162 | 131/4 | DA+0 | C | Submitted | Submitted
163 | 131/5 | DA+3 | C | Submitted | Submitted
164 | 131/6 | DA+9 | C | Submitted | Submitted
165 | AP132 | DC+9 | C
166 | 132/1 | DA+3 | C | Submitted
167 | AP133 | DC+6
168 | AP134 | DB+3
169 | AP135 | DB+3 | C | Submitted | Submitted
170 | 135/1 | DA+6 | C | Submitted |  | Patwari Visit pending
171 | 135/2 | DA+3 | C | Submitted | File Ready
172 | AP136 | DC+3 | WIP
173 | 136/1 | DA+3 | C | Submitted
174 | 136/2 | DA+3 | C | File Ready
175 | 136/3 | DA+0 | C | File Ready
176 | 136/4 | DA+3 | C
177 | AP137 | DC+3 | C
178 | 137/1 | DA+0 | C | Submitted
179 | 137/2 | DA+0 | C | Submitted
180 | AP138 | DD+0 | C | Submitted | File Ready
181 | 138/1 | DA+0 | C | Submitted | File Ready
182 | 138/2 | DA+0 | C | Submitted | File Ready
183 | AP139 | DB+0 | C
184 | 139/1 | DA+3 | C | Submitted | File Ready
185 | AP140 | DD+18
186 | AP142 | DD+0
187 | 142/1 | DA+0
188 | AP143 | DB+0
189 | 143/1 | DA+0
190 | 143/2 | DA+0
191 | AP144 | DB +0
192 | 144/1 | DA+3
193 | 144/2 | DA+0
194 | 144/3 | DA+6
195 | 144/4 | DA+0
196 | AP145 | DB+0 | WIP
197 | 145/1 | DA+0 | C
198 | 145/2 | DA+3 | C | Submitted
199 | AP146 | DC+0 | C | Submitted
200 | AP147 | DB+0 | C | Submitted
201 | AP148 | DD+25 | WIP
202 | AP149 | DD+25 | WIP
203 | AP150 | DC+0 | C
204 | 150/1 | DA+0 | C | Submitted | Submitted
205 | 150/2 | DA+0 | C | Submitted
206 | AP151 | DC+0
207 | 151/1 | DA+0 | C | Submitted
208 | 151/2 | DA+3 | C
209 | AP152 | DD+0 | WIP
210 | 152/1 | DA+3 | C | Submitted | Submitted
211 | 152/2 | DA+0 | C
212 | 152/3 | DA+0
213 | 152/4 | DA+0 | C | Submitted | Submitted
214 | AP153 | DC+0 | C | Submitted | Submitted
215 | 153/1 | DA+0 | C | Submitted | Submitted
216 | 153/2 | DA+3 | C | Submitted | Submitted
217 | AP154 | DC+0 | C | Submitted | Submitted
218 | AP155 | DD+0 | C | Submitted | Submitted
219 | 155/1 | DA+0 | C | Submitted | Submitted
220 | 155/2 | DA+0 | C
221 | 155/3 | DA+0 | C | Submitted | Submitted
222 | AP156 | DC+0 | C
223 | 156/1 | DA+6 | C
224 | 156/2 | DA+0 | C | Submitted | Submitted
225 | 156/3 | DA+0 | C | Submitted | Submitted
226 | 156/4 | DA+0 | C | Submitted | Submitted
227 | AP157 | DB+0 | C | Submitted | Submitted
228 | 157/1 | DA+0 | C | Submitted | Submitted
229 | AP158 | DD+9
230 | AP159 | DD+18 | C
231 | 159/1 | DA+0
232 | 159/2 | DA+0
233 | 159/3 | DA+0
234 | AP161 | DD+9
235 | AP162 | DD+18
236 | AP163 | DB+9
237 | AP164 | DB+3
238 | AP165 | DB+6
239 | AP166 | DB+6
240 | AP167 | DD+9
241 | AP168 | DD+9

## Sheet13 (2) (hidden)
Paticulars | Plain Terrain | Hilly Terrain
Line Length (KM) | 137 KM | 36 KM
| 79.19% | 20.81%

## TB-605
| Project Code | TB-605 | Date | 2026-08-11 |  |  | President-T & D | Ganesh Srinivasan
| Project Name | Transmission Line Portion for “Transmission scheme for evacuation of power from Ratle HEP (850 MW) & Kiru HEP (624 MW): Part-A” |  |  | LOA Start Date | 2025-05-16 | SBU Head- T&D | Rajinder Gupta
| Client Name | Ratle Kiru Power Transmission Ltd |  |  | LOA End Date | 2027-03-15 | PCH | NK Gupta
| Revised End Date |  |  |  | Planning | Aditya.M | Project Manager | Mithu Dutta
Progress Summary - Ratle Kiru Power Transmission Ltd
Activity | Final Estimated Qty | Cumulative L2 till Last Month | Cumulative Progress till Last Month | L2 for present Month (Revised) | Plan for the Month | Today's Progress | Progress till Date for the Month | L2 till Current Month | Completed till Date | Balance Work | Under Progress | Gangs at Present | Remarks | Gap with respect to revised L2 - Cummilative till Aug-26 | Gap with respect to monthly plan for the month Aug-26
Check Survey | 175.719 | 179.103 | 175.719 | 0 | 0 | 0 | 0 | 179.103 | 175.719 |  | 0
Foundation | 523 | 510 | 431 | 24 | 26 | 2 | 3 | 534 | 434 | 89 | 30 | 22 |  | 100 | 23
Earthing | 523 | 506 | 379 | 24 | 26 | 0 | 0 | 530 | 379 | 144 | 0 | 0 |  | 151 | 26
Tower Erection | 523 | 410 | 273 | 56 | 32 | 0 | 8 | 466 | 281 | 242 | 13 | 15 |  | 185 | 24
Tack welding | 523 | 410 | 0 | 56 | 32 | 0 | 0 | 466 | 0 | 523 | 0 | 0 |  | 466 | 32
Stringing-P/O-R/S | 175.719 | 48 | 5.655 | 22 | 11 | 0 | 0 | 70 | 5.655 | 170.064 | 4.79 | 6 | 4 Stringing + 1 Hotline+1 Drone Team | 64.345 | 11
Stringing-F/S | 175.719 | 48 | 4.715 | 22 | 11 | 0 | 0.952 | 70 | 5.667 | 170.052 | 0 |  |  | 60.333 | 10.048
Line Wise Progress
400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5-Jammu Portion
Activity | Final Estimated Qty | Cumulative L2 till Last Month | Cumulative Progress till Last Month | L2 for present Month (Revised) | Plan for the Month | Today's Progress | Progress till Date for the Month | L2 till Current Month | Completed till Date | Balance Work | Under Progress | Gangs at Present | Remarks | Gap with respect to revised L2 - Cummilative till Jun-26 | Gap with respect to monthly plan for the month June-26
Check Survey | 46.92 | 49 | 46.92 |  |  |  |  | 49 | 46.92 | 0
Foundation | 126 | 141 | 119 |  | 3 |  |  | 141 | 119 | 7 | 2 | 2 |  | 22 | 3
Earthing | 126 | 141 | 99 |  | 3 |  |  | 141 | 99 | 27 |  |  |  | 42 | 3
Tower Erection | 126 | 118 | 103 | 14 | 4 |  | 1 | 132 | 104 | 22 | 2 | 2 | Final Checking-41 Towers done | 28 | 3
Tack welding | 126 | 118 | 0 | 14 | 4 |  |  | 132 | 0 | 126 | 0 | 0 |  | 132 | 4
Stringing-P/O-R/S | 46.92 | 23 | 5.655 | 5 | 10 |  |  | 28 | 5.655 | 41.265 | 4.79 | 5 | 4 Stringing + 1 Hotline | 22.345 | 10
Stringing- F/S | 46.92 | 23 | 4.715 | 5 | 10 |  | 0.952 | 28 | 5.667 | 41.253 |  |  |  | 22.333 | 9.048 | 1.08
400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5-Punjab Portion
Activity | Final Estimated Qty | Cumulative L2 till Last Month | Cumulative Progress till Last Month | L2 for present Month (Revised) | Plan for the Month | Today's Progress | Progress till Date for the Month | L2 till Current Month | Completed till Date | Balance Work | Under Progress | Gangs at Present | Remarks | Gap with respect to revised L2 - Cummilative till Jun-26 | Gap with respect to monthly plan for the month June-26
Check Survey | 92.281 | 95 | 92.281 |  |  |  |  | 95 | 92.281 | 0
Foundation | 263 | 267 | 237 | 12 | 2 |  |  | 279 | 237 | 26 | 2 | 2 | 1FDN+1PILE | 42 | 2
Earthing | 263 | 267 | 227 | 12 | 2 |  |  | 279 | 227 | 36 | 0 |  |  | 52 | 2
Tower Erection | 263 | 227 | 154 | 20 | 2 |  | 1 | 247 | 155 | 108 | 1 | 1 | Final Checking- 44 Towers done | 92 | 1
Tack welding | 263 | 227 | 0 | 20 | 2 |  |  | 247 | 0 | 263 | 0 | 0 |  | 247 | 2
Stringing-P/O-R/S | 92.281 | 25 | 0 | 13 |  |  |  | 38 | 0 | 92.281 | 0 |  |  | 38 | 0
Stringing-F/S | 92.281 | 25 |  | 13 |  |  |  | 38 |  | 92.281 |  |  |  | 38 | 0
400 kV Kishenpur-Samba D/C Line (Quad) - Wind Zone-5
Activity | Final Estimated Qty | Cumulative L2 till Last Month | Cumulative Progress till Last Month | L2 for present Month (Revised) | Plan for the Month | Today's Progress | Progress till Date for the Month | L2 till Current Month | Completed till Date | Balance Work | Under Progress | Gangs at Present | Remarks | Gap with respect to revised L2 - Cummilative till Jun-26 | Gap with respect to monthly plan for the month June-26
Check Survey | 33.103 | 33.103 | 33.103 |  |  |  |  | 33.103 | 33.103 | 0
Foundation | 116 | 97 | 70 | 10 | 16 |  | 1 | 107 | 71 | 45 | 18 | 13 |  | 36 | 15
Earthing | 116 | 97 | 53 | 10 | 16 |  |  | 107 | 53 | 63 | 0 |  |  | 54 | 16
Tower Erection | 116 | 65 | 16 | 20 | 26 |  | 6 | 85 | 22 | 94 | 10 | 11 |  | 63 | 20
Tack welding | 116 | 65 | 0 | 20 | 26 |  |  | 85 | 0 | 116 | 0 | 0 |  | 85 | 26
Stringing-P/O-R/S | 33.103 | 0 | 0 | 4 | 1 |  |  | 4 | 0 | 33.103 |  | 1 | 1 Drone Team | 4 | 1
Stringing-F/S | 33.103 |  |  | 4 | 1 |  |  |  |  | 33.103 |  |  |  | 0 | 1
400kV DC LILO at Kistwar(Twin) Line - Wind Zone-2
Activity | Final Estimated Qty | Cumulative L2 till Last Month | Cumulative Progress till Last Month | L2 for present Month (Revised) | Plan for the Month | Today's Progress | Progress till Date for the Month | L2 till Current Month | Completed till Date | Balance Work | Under Progress | Gangs at Present | Remarks | Gap with respect to revised L2 - Cummilative till Jun-26 | Gap with respect to monthly plan for the month June-26
Check Survey | 3.415 | 2 | 3.415 |  |  |  |  | 2 | 3.415 | 0
Foundation | 18 | 5 | 5 | 2 | 5 | 2 | 2 | 7 | 7 | 11 | 8 | 5 |  | 0 | 3
Earthing | 18 | 1 | 0 | 2 | 5 |  |  | 3 | 0 | 18 | 0 |  |  | 3 | 5
Tower Erection | 18 | 0 | 0 | 2 |  |  |  | 2 | 0 | 18 | 0 | 0 |  | 2 | 0
Tack welding | 18 | 0 | 0 | 2 |  |  |  | 2 | 0 | 18 | 0 | 0 |  | 2 | 0
Stringing-P/O-R/S | 3.415 | 0 | 0 |  |  |  |  | 0 | 0 | 3.415 | 0 | 0 |  | 0
Stringing-F/S | 3.415 | [8 empty] | 3.415 |  |  |  | 0 |  |  | 899
Supply Status | [16 empty] | 1199
Line | Description | Final Estimated Qty | L2 till Aug-26 | Qty Supplied till Aug-26 | Remarks
Samba-Jalandhar | Stubs | 389 | 434 | 387
| Towers | 389 | 323 | 361
| 120 KN Ins | 3016 | 2174 | 900
| 160 KN Ins | 9132 | 7496 | 2200
| Conductor | 3393.6 | 3489 | 3787.481
| OPGW | 100% | 100%
| HWF | 100% | 100% | 40%
Samba-Kishenpur | Stubs | 116 | 129 | 111
| Towers | 116 | 129 | 102
| 120 KN Ins | 295 | 348
| 160 KN Ins | 5606 | 5880
| Conductor | 809.616 | 802 | 224
| OPGW | 100% | 100%
| GS E/W | 100% | 100% | 100%
| HWF | 100% | 100%
LILO at Kishtwar | Stubs | 18 | 18 | 12
| Towers | 18 | 18
| 120 KN Ins | 117 | 90
| 160 KN Ins | 453 | 252
| Conductor | 41.5716 | 14 | 16
| OPGW | 100% | 100%
| GS E/W | 100% | 100%
| HWF | 100% | 100%

## Sheet16 (hidden)
S.No | Gang | Line | Remarks
1 | Pawan Kumar Sharma | J-S (Jammu) | Gang idle since 4-4-26 at Loc: 40/3 due to ROW
2 | Md. Ikrar | J-S(Punjab) | Loc: 144/4 completed on 5-4-2026 and no work front available due to crop harvesting
3 | Ms. Hussain | J-S(Punjab) | Loc: 144/3 will be completed on 6-4-2026 and no work front availabl due to crop harvesting
4

## Sheet14 (hidden)
S.No | Month | Concreting |  | Cement | TMT
|  | M10 | M20
|  | M3 | M3 | Bags | MT
1 | 2025-09-01 | 14.664 | 135.088 | 1145 | 8.44
2 | 2025-10-01 | 76.132 | 667.004 | 5671 | 47.8
3 | 2025-11-01 | 283.933 | 2687.36 | 22748 | 176.38
4 | 2025-12-01 | 415.903 | 3983.996 | 33702 | 264.63 | Concreting (M3) | Tower Erection(MT)
5 | 2026-01-01 | 411.1974 | 4750.4 | 39812 | 164.07 | 21381 | 2332
6 | 2026-02-01 | 411.1974 | 4300.4 | 36212 | 264.45
7 | 2026-03-01 | 296.343 | 2947.484 | 24884 | 199.54
Total |  | 1909.3698 | 19471.732 | 164174 | 1125.31

## Sheet12 (hidden)
Supply Portion
S.No | Material | UOM | BOQ Qty | Final Estimated Qty | L2 till Mar'26 | Supplied Qty | Balance to Supply
1 | Stubs | EA | 434 | 389 | 434 | 353 | 36
2 | Towers | EA | 434 | 389 | 216 | 314 | 75
S.No | Activity | UOM | BOQ Qty | Final Estimated Qty | L2 till Feb'26 | Completed till Feb'26 | L2 Mar'26 | Progress in Mar'26 | Cumm L2 till Mar'26 | Cumm. Progress till Mar'26 | Balance | Remarks
400 kV D/C Samba - Jalandhar TL
1 | Survey | Km | 143 | 137 | 143 | 136 |  |  | 143 | 136 | 1
2 | Foundation | EA | 434 | 389 | 207 | 202 | 45 | 28 | 252 | 230 | 159 | 19 Gangs
3 | Tower Erection | EA | 434 | 389 | 125 | 55 | 45 | 48 | 170 | 103 | 286 | 10 Gangs
4 | Stringing | Km | 143 | 137 | [6 empty] | 137
400kV D/C Samba -Kishenpur TL
1 | Survey | Km | 33 | 33 | 33 | 33 |  |  | 33 | 33
2 | Foundation | EA | 129 | 116 | 39 | 37 | 11 | 7 | 50 | 44 | 72 | 6 Gangs
3 | Tower Erection | EA | 129 | 116 |  |  | 5 | 2 | 5 | 2 | 114 | 1 Gang
4 | Stringing | Km | 33 | 33 | [6 empty] | 33
LILO-Kisthwar
1 | Survey | Km | 2 | 3.4 | 2 | 3.4 |  |  | 2 | 3.4
2 | Foundation | EA | 14 | 18 | 14 |  |  |  | 14 |  | 18 | 3 Gangs
3 | Tower Erection | EA | 14 | 18 |  |  | 2 |  | 2 |  | 18
4 | Stringing | Km | 2 | 3.4 | [6 empty] | 3.4
Supply Portion
S.No | Material | UOM | BOQ Qty | Final Estimated Qty | L2 till Mar'26 | Supplied Qty | Balance to Supply
1 | Stubs | EA | 129 | 116 | 129 | 64 | 52
2 | Towers | EA | 129 | 116 | 129 | 41 | 75
Service Portion
S.No | Activity | UOM | BOQ Qty | Final Estimated Qty | L2 till Feb'26 | Completed till Feb'26 | L2 Mar'26 | Progress in Mar'26 | Cumm L2 till Mar'26 | Cumm. Progress till Mar'26 | Balance | Remarks
Supply Portion
S.No | Material | UOM | BOQ Qty | Final Estimated Qty | L2 till Mar'26 | Supplied Qty | Balance to Supply
1 | Stubs | EA | 14 | 18 | 14 | 10 | 8
2 | Towers | EA | 14 | 18 | 14 |  | 18
S.No | Activity | UOM | BOQ Qty | Final Estimated Qty | L2 till Feb'26 | Completed till Feb'26 | L2 Mar'26 | Progress in Mar'26 | Cumm L2 till Mar'26 | Cumm. Progress till Mar'26 | Balance | Remarks

## Sheet13 (hidden)
Paticulars | Jammu Portion | Punjab Portion
Line Length (KM) | 83 KM | 90 KM
| 47.98% | 52.02%

## Sheet15 (hidden)
Supply Portion
S.No | Line | LOA Cr | Billed till date Cr | Balance Cr
1 | 400 kV Samba- Jalandhar D/C line (Quad) | 155.09 | 88.06 | 67.03
2 | 400 kV Kishenpur-Samba D/C line (Quad) | 67.47 | 17.6387 | 49.8313
3 | LILO of 400 kV Kishenpur- Dulhasti line (Twin) at Kishtwar S/s | 6.43 | 0.14392 | 6.2861
Total |  | 228.99 | 105.8426 | 123.1474
Service Portion
S.No | Line | LOA Cr | Billed till date Cr | Balance Cr
1 | 400 kV Samba- Jalandhar D/C line (Quad) | 119.3227 | 30.5299 | 88.7928
2 | 400 kV Kishenpur-Samba D/C line (Quad) | 50.1304 | 4.6321 | 45.4982 | 105.84
3 | LILO of 400 kV Kishenpur- Dulhasti line (Twin) at Kishtwar S/s | 4.4045 |  | 4.4045
4 | Unit Rate Schedule for Services | 6.4654 |  | 6.4654
5 | ROW Schedule | 5.9322 |  | 5.9322
Total |  | 186.2552 | 35.1621 | 151.0932
1.5

## TB401 DPR (hidden)
Project Progress for TB-401/408,Section-II
765KV D/C Fategarh-III Beawar Transmission Line |  |  | TB-401 |  |  | LOA Date |  | Pkg-G -26.04.23 |  |  | Completion Period |  | 2025-03-31 |  |  | Date: | 2026-08-11
|  |  | TB-408 |  |  |  |  | Pkg-F - 11.09.23 |  |  | Completion Period |  | 2025-03-31
.
Activity | Qty as per LOA | Qty Received | L2 |  | Overall Progress |  | Mar'25 |  | Balance | Apr'25 |  |  |  | Plan |  | Remarks
|  |  | 2024-12-30 | Till Mar-25 | As on date | Till Mar-25 | Plan | Actual | As on date | Plan | WIP | Today comp | Actual | 2024-09-01 | 2024-07-01
Details Survey | 215 | 189.53 |  | 203 | 199.841 | 199.841
Pkg-G (Section-II) |  | 101.1 |  | 107.5 | 101.1 | 101.1
Pkg-F (Section-II) |  | 88.43 |  | 95.5 | 98.741 | 98.741
Check Survey | 215 | 189.53 | 0 | 203 | 189.526 | 184.552 | 14.88 | 6.08 | 0.004 | 0 | 0 |  | 4.974 | 0
Pkg-G (Section-II) |  | 101.1 |  | 107.5 | 101.096 | 101.096 | 6.08 | 6.08 | 0.004
Pkg-F (Section-II) |  | 88.43 |  | 95.5 | 88.43 | 83.456 | 8.8 |  | 0 |  |  |  | 4.974
Foundation | 534 | 488 | 0 | 488 | 485 | 485 | 9 | 6 | 3 | 0 | 3 |  | 0 | 0 | 0
Pkg-G (Section-II) |  | 265 |  | 265 | 265 | 265 | 5 | 5 | 0 | [8 empty] | 9649905358 | D S Jangid
Pkg-F (Section-II) |  | 223 |  | 223 | 220 | 220 | 4 | 1 | 3 |  | 3 | [6 empty] | 7014675307 | jangid
Gang / Worker | [9 empty] | 10/180 | 02/55
Erection | 534 | 488 | 0 | 488 | 367 | 365 | 36 | 24 | 121 | 0 | 4 | 1 | 2 | 0 | 0
Pkg-G (Section-II) |  | 265 |  | 265 | 201 | 201 | 20 | 11 | 64 |  | 0
Pkg-F (Section-II) |  | 223 |  | 223 | 166 | 164 | 16 | 13 | 57 |  | 4 | 1 | 2 |  |  | 70/10 Complete
Gang / Worker | [9 empty] | 7/240 | 4/241
Stringing Payout | 215 | 189.53 | 0 | 189.53 | 94.743 | 94.743 | 0 | 9.18 | 94.787 | 0 | 1.881 | 0 | 0 | 0 | 15
Pkg-G (Section-II) |  | 101.1 |  | 101.1 | 52.284 | 52.284 |  |  | 48.816
Pkg-F (Section-II) |  | 88.43 |  | 88.43 | 42.459 | 42.459 |  | 9.18 | 45.971 |  | 1.881
Gang / Worker | [10 empty] | 2/154
Stringing Final sag | 215 | 189.53 | 0 | 189.53 | 88.935 | 88.935 | 0 | 14.161 | 100.595 | 0 | 5.808 | 0 | 0 | 0 | 15
Pkg-G (Section-II) |  | 101.1 |  | 101.1 | 49.703 | 49.703 |  | 4.981 | 51.397 |  | 2.581
Pkg-F (Section-II) |  | 88.43 |  | 88.43 | 39.232 | 39.232 |  | 9.18 | 49.198 |  | 3.227
Gang / Worker | [10 empty] | 2/154

## Survey-Summary (hidden)
PROJECT NAME | INDIGRID - 400kV D/C QUAD WZ-5 SAMBA-JALANDHAR & KISHENPUR-SAMBA TL | [10 empty] | COMP | APPROVED
START DATE (NOA DATE) | 16-MAY-2025 | [10 empty] | PENDING | UNDER REVIEW
KEC PROJECT | TB-605 | [11 empty] | PENDING
NAME OF CLIENT | RATLE KIRU POWER TRANSMISSION LIMITED
TITLE | SITE SURVEY STATUS
TEAM FORMATION | [5 empty] | CHECK SURVEY SUMMARY (KM)
Portion | SURVEY LEAD | TEAM MEMBERS | MACHINE | LINE NAME | SECTION LENGTH | COMPLETED | BALANCE | SUBMITTED | APPROVED | APPROVAL PENDING | REMARK
Jammu | 1)BIPPAN SHARMA | 2) Shiv Kumar( Asst Surveyor) | DGPS-1 TS-02 | 400kV D/C Jalandar - Samba T/L (GANTRY TO AP 52) | 46.915 | 46.44 | 0.475 | 46.053 | 46.053 | 0 | 0.48 km is from Sambha Gantyry to AP 4
|  | 3) Sahil Raj(Asst Surveyor) |  | 400kV D/C Samba - Kishenpur T/L | 33 | 27.138 | 5.862 | 19.6 | 19.6 | 0 | AP4-AP14, AP24-AP55, AP55-AP70, AP70-AP86,AP95-AP109 C/S Completed AP15-AP24 - Re-routing required due to landsliding (Hold) AP86-AP95 - Hold due to under powerline crossing
|  | 4) Sunil (Survey Helper) |  | LILO at Kistwar | 2.18 | 2.18 | 0 | 2.18 | 2.18 | 0 | Contour completed 12 Locations out of 13 location AP 11 conturing not done due to ROW since 29th Jul'25
|  | 5) Sanjhi Ram((Survey Helper) |  |  |  |  | 0 |  |  | 0
Punjab | 1)RAJ KAMAL GHOSH | 2) Anupam Basak (Survayor DET) | TS-01 | 400kV D/C Jalandar - Samba T/L ( AP 52-115) | 47.25 | 46.474 | 0.776 | 45.892 | 45.892 | 0
|  | 3) Kuldeep singh (supervisor DET) |  |  |  |  | 0 |  |  | 0
|  | 4) Vickey Ghosh (Survey DET) |  |  |  |  | 0 |  |  | 0
|  | 5) Rupak Kumar (Survey Helper) | [7 empty] | 0
Punjab | 1)SAGAR MAJHI | 2) Surajit Majhi(Asst Surveyor) | TS-01 | 400kV D/C Jalandar - Samba T/L ( AP 115-187) | 47.805 | 40.97 | 6.835 | 47.81 | 23.519 | 24.291
|  | 3) Rudra Madhav (supervisor DET) |  |  |  |  | 0 |  |  | 0
|  | 4)Gordhan Ram (supervisor DET) |  |  |  |  | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
TOTAL (KM) |  |  |  |  | 177.15 | 163.202 | 13.948 | 161.535 | 137.244 | 24.291 | 0
400kV D/C Samba-Jalandhar C/S -Details
[5 empty] | S.No | Section | Section | Length | Submitted | Approval Date | Remarks
[8 empty] | Km | Date
[5 empty] | 1 | AP20-AP30 | Jammu | 10.43 | 2025-07-08 | 2025-07-16
[5 empty] | 2 | AP30-AP41 | Jammu | 13.72 | 2025-07-19 | 2025-07-24
[5 empty] | 3 | AP41-AP51 | Jammu | 15.05 | 2025-07-30 | 2025-08-04
[5 empty] | 4 | AP15-AP20 | Jammu | 4.51 | 2025-09-08 | 2025-09-09
[5 empty] | 5 | AP5-AP15 | Jammu | 2.346 | 2025-09-18 | 2025-09-30
[5 empty] | 5 | AP53-AP66 | Punjab | 11.37 | 2025-08-06 | 2025-08-25
[5 empty] | 6 | AP70-AP84 | Punjab | 11.41 | 2025-08-16 | 2025-08-31
[5 empty] | 7 | AP84-AP96 | Punjab | 10.07 | 2025-08-21 | 2025-08-25
[5 empty] | 8 | AP115-AP123 | Punjab | 6.93 | 2025-08-19 | 2025-09-04
[5 empty] | 9 | AP131-AP140 | Punjab | 10.3 | 2025-08-19 | 2025-09-04
[5 empty] | 10 | AP145-AP153 | Punjab | 6.29 | 2025-08-23 | 2025-09-04
[5 empty] | 11 | AP96-AP115 | Punjab | 9.626 | 2025-09-13 | 2025-10-31
[5 empty] | 12 | AP66-AP70 | Punjab | 3.42 | 2025-09-19 | 2025-10-31
[5 empty] | 13 | AP153-AP175 | Punjab | 12.083 | 2025-09-22 |  | Route diversion in between 168-175 to be finalized
[5 empty] | Total |  |  | 127.555
400kV D/C Kishenpur-Samba C/S -Details
[5 empty] | S.No | Section | Section | Length | Submitted | Approval Date | Remarks
[8 empty] | Km | Date
[5 empty] | 1 | AP95-AP109 | Jammu | 3.13 | 2025-09-08 | 2025-09-09
[5 empty] | 2 | AP78-AP86 | Jammu | 1.945 | 2025-09-27 | 2025-09-30
[5 empty] | 3 | AP24-AP39 | Jammu | 5.5 | 16-10-2025 30-10-2025 | 2025-11-01
[5 empty] | 4 | AP39-AP55 | Jammu | 5.463 | 2025-11-24 | 2025-12-03
[5 empty] | 5 | AP4-AP14 | Jammu | 3.597 | 2025-12-03 | 2025-12-03
[5 empty] | Total |  |  | 19.635
LILO-Kisthewar C/S -Details
[5 empty] | S.No | Section | Section | Length | Submitted | Approval Date | Remarks
[8 empty] | Km | Date
[5 empty] | 1 | TP-Gantry | Kishtwar | 2.18 | 30-08-2025 08-09-2025 27-09-2025 | 2025-09-30
[5 empty] | Total |  |  | 2.18

## Sheet6 (hidden)
Survey
Line | Portion | Scope | Completed | Submitted | Approved
S-J | Jammu | 46.92 | 46.44 | 46.44 | 46.44
S-J | Punjab | 95.06 | 95.06 | 84.936 | 72.85
K-S |  | 33.103 | 23.393 | 16.04 | 10.6
LILO |  | 2.18 | 2.18 | 2.18 | 2.18
Total |  | 177.263 | 167.073 | 149.596 | 132.07
|  | 16.04 |  |  |  | 10.58
|  | 45.892 |  |  |  | 45.892
|  | 46.06 |  |  |  | 46.06
|  | 20.674 | 18.37 |  |  | 20.674
12.08
2.18
72.856

## Approved Survey (hidden)
KEC INTERNATIONAL LIMITED
400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5 |  |  |  | 400 kV Samba- Kishenpur D/C Line(Quad) - Wind Zone - 5
Approved Check Survey Sections |  |  |  | Approved Check Survey Sections
S.No | Portion | Section | Length Km | S.No | Section | Length Km
1 | Jammu | AP5-AP6 | 0.11906 | 1 | AP78-AP86 | 1.945
2 | Jammu | AP6-AP7 | 0.092496 | 2 | AP95-AP109 | 3.13
3 | Jammu | AP7-AP8 | 0.13499 | 3 | AP24-AP39 | 5.5
4 | Jammu | AP8-AP9 | 0.36518 | Total |  | 10.575
5 | Jammu | AP9-AP10 | 0.2367
6 | Jammu | AP10-AP11 | 0.21315 | LILO-Kishtwar
7 | Jammu | AP11-AP12 | 0.20659 | Approved Check Survey Sections
8 | Jammu | AP12-AP13 | 0.28986 | S.No | Section | Length Km
9 | Jammu | AP13-AP14 | 0.40294 | 1 | AP1-TP | 2.18
10 | Jammu | AP14-AP15 | 0.28488
11 | Jammu | AP15-AP16 | 1.6734
12 | Jammu | AP16-AP17 | 0.28595
13 | Jammu | AP17-AP18 | 0.40116
14 | Jammu | AP18-AP19 | 1.0552
15 | Jammu | AP19-AP20 | 1.0887
16 | Jammu | AP20-AP21 | 0.48593
17 | Jammu | AP21-AP22 | 0.71234
18 | Jammu | AP22-AP23 | 1.1771
19 | Jammu | AP23-AP24 | 2.455
20 | Jammu | AP24-AP25 | 0.36604
21 | Jammu | AP25-AP26 | 1.028
22 | Jammu | AP26-AP27 | 0.44237
23 | Jammu | AP27-AP28 | 0.73974
24 | Jammu | AP28-AP29 | 0.44599
25 | Jammu | AP29-AP30 | 2.5736
26 | Jammu | AP30-AP31 | 2.5147
27 | Jammu | AP31-AP32 | 2.3745
28 | Jammu | AP32-AP33 | 0.83698
29 | Jammu | AP33-AP34 | 0.9678
30 | Jammu | AP34-AP35 | 0.81991
31 | Jammu | AP35-AP36 | 0.82023
32 | Jammu | AP36-AP37 | 0.4398
33 | Jammu | AP37-AP38 | 1.2034
34 | Jammu | AP38-AP39 | 0.77527
35 | Jammu | AP39-AP40 | 1.2099
36 | Jammu | AP40-AP41 | 1.7605
37 | Jammu | AP41-AP42 | 0.21244
38 | Jammu | AP42-AP43 | 1.361
39 | Jammu | AP43-AP44 | 1.9119
40 | Jammu | AP44-AP45 | 1.4747
41 | Jammu | AP45-AP46 | 1.0795
42 | Jammu | AP46-AP47 | 2.2165
43 | Jammu | AP47-AP48 | 1.3604
44 | Jammu | AP48-AP49 | 0.3715
45 | Jammu | AP49-AP50 | 0.2033
46 | Jammu | AP50-AP50A | 0.40991
47 | Jammu | AP50A-AP51 | 4.4509
48 | Punjab | AP53-AP54 | 0.41666
49 | Punjab | AP54-AP55 | 0.38929
50 | Punjab | AP55-AP56 | 0.79345
51 | Punjab | AP56-AP57 | 1.9061
52 | Punjab | AP57-AP58 | 0.98237
53 | Punjab | AP58-AP59 | 0.40644
54 | Punjab | AP59-AP60 | 0.78804
55 | Punjab | AP60-AP61 | 0.75758
56 | Punjab | AP61-AP62 | 0.56392
57 | Punjab | AP62-AP63 | 1.0812
58 | Punjab | AP63-AP64 | 0.45086
59 | Punjab | AP64-AP65 | 0.60284
60 | Punjab | AP65-AP66 | 2.2285
61 | Punjab | AP70-AP71 | 1.599
62 | Punjab | AP71-AP72 | 1.6662
63 | Punjab | AP72-AP73 | 0.80957
64 | Punjab | AP73-AP74 | 0.40669
65 | Punjab | AP74-AP75 | 0.31625
66 | Punjab | AP75-AP76 | 0.24842
67 | Punjab | AP76-AP77 | 1.6815
68 | Punjab | AP77-AP78 | 1.6304
69 | Punjab | AP78-AP79 | 0.32074
70 | Punjab | AP79-AP80 | 0.24222
71 | Punjab | AP80-AP81 | 0.83925
72 | Punjab | AP81-AP82 | 0.24266
73 | Punjab | AP82-AP83 | 1.1492
74 | Punjab | AP83-AP84 | 0.25152
75 | Punjab | AP84-AP85 | 0.44513
76 | Punjab | AP85-AP86 | 0.83855
77 | Punjab | AP86-AP87 | 0.83676
78 | Punjab | AP87-AP88 | 1.1854
79 | Punjab | AP88-AP89 | 0.21106
80 | Punjab | AP89-AP90 | 0.61823
81 | Punjab | AP90-AP91 | 1.181
82 | Punjab | AP91-AP92 | 0.24768
83 | Punjab | AP92-AP93 | 1.4552
84 | Punjab | AP93-AP94 | 0.88908
85 | Punjab | AP94-AP95 | 0.41154
86 | Punjab | AP95-AP96 | 1.751
87 | Punjab | AP115-AP116 | 0.75141
88 | Punjab | AP116-AP117 | 0.51547
89 | Punjab | AP117-AP118 | 1.4097
90 | Punjab | AP118-AP119 | 0.63436
91 | Punjab | AP119-AP120 | 0.51818
92 | Punjab | AP120-AP121 | 1.2124
93 | Punjab | AP121-AP122 | 1.1369
94 | Punjab | AP122-AP123 | 0.75355
95 | Punjab | AP131-AP132 | 2.842
96 | Punjab | AP132-AP133 | 0.81608
97 | Punjab | AP133-AP134 | 0.22737
98 | Punjab | AP134-AP135 | 0.40137
99 | Punjab | AP135-AP136 | 1.2219
100 | Punjab | AP136-AP137 | 2.0004
101 | Punjab | AP137-AP138 | 1.0376
102 | Punjab | AP138-AP139 | 0.94497
103 | Punjab | AP139-AP140 | 0.80912
104 | Punjab | AP145-AP146 | 1.0669
105 | Punjab | AP146-AP147 | 0.24568
106 | Punjab | AP147-AP148 | 0.35293
107 | Punjab | AP148-AP149 | 0.2323
108 | Punjab | AP149-AP150 | 0.47498
109 | Punjab | AP150-AP151 | 0.93803
110 | Punjab | AP151-AP152 | 1.117
111 | Punjab | AP152-AP153 | 1.8616
Total |  |  | 102.4149

## Approved CS J-S Line (hidden)
Line: 400 kV D/C Quad Jalandhar-Samba TL
Approved Check Survey Tower Schedule
AS PER DETAIL SURVEY | [7 empty] | AS PER CHECK SURVEY
Sr. No. | Tower No. | Type of Tower | Span Length (m) | Section Length (m) | Angle of Deviation | UTM Coordinates |  | Sr. No. | Tower No. | Type of Tower | Raised Chimney |  |  |  | Leg Extension |  |  |  | Span Length (m) | Section Length (m) | Reduced Level | Angle of Deviation | UTM Coordinates |  | Crossing/Remarks
[6 empty] | Easting | Northing |  |  |  | LEG A | LEG B | LEG C | LEG D | LEG A | LEG B | LEG C | LEG D |  |  |  |  | Easting | Northing
1 | AP 5/0 | DD+18 |  | 0 | 47°01'57"L | 516661.837 | 3596578.147 | 1 | AP 5/0 | DD+0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 384.3 | 47°01'59"LT | 516472.785 | 3598642.658
|  |  | 119.059 | [15 empty] | 119.059 | [5 empty] | 2 nos 11 KV,Road Crossing
2 | AP 6/0 | DA+0 |  | 119.059 | 40°54'41"R | 516805.332 | 3596183.208 | 2 | AP 6/0 | DD+9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 119.059 | 384.202 | 40°54'42"RT | 516557.855 | 3598559.362
|  |  | 92.496 | [15 empty] | 92.496
3 | AP 7/0 | DA+0 |  | 211.555 | 47°08'48"L | 516948.802 | 3595788.337 | 3 | AP 7/0 | DD+25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 211.555 | 382.166 | 47°08'48"LT | 516565.421 | 3598467.176
|  |  | 134.989 | [15 empty] | 134.988 | [5 empty] | 400 KV(JAL-SAM) line Crossing
4 | AP 8/0 | DA+6 |  | 346.544 | 41°15'08"R | 517087.159 | 3595407.541 | 4 | AP 8/0 | DD+25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 346.543 | 377.89 | 41°15'08"RT | 516671.559 | 3598383.77
|  |  | 365.175 | [15 empty] | 365.176 | [5 empty] | Nalla Crossing
5 | AP 9/0 | DC+6 |  | 711.719 | 37°05'47"R | 517233.304 | 3595005.308 | 5 | AP 9/0 | DD+9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 711.719 | 373.28 | 37°05'47"RT | 516738.65 | 3598024.81
|  |  | 236.697 | [15 empty] | 236.697 | [5 empty] | 2 nos 25KV,Railway Crossing
6 | AP 10/0 | DC+3 |  | 948.416 | 20°40'31"L | 517425.65 | 3594793.72 | 6 | AP 10/0 | DD+9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 948.416 | 364.063 | 20°40'31"LT | 516633 | 3597813
|  |  | 213.252 | [15 empty] | 213.252
7 | AP 11/0 | DC+3 |  | 1161.668 | 51°34'01"R | 517777.572 | 3594601.159 | 7 | AP 11/0 | DD+25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1161.668 | 361.99 | 51°34'02"RT | 516611.322 | 3597600.853
|  |  | 206.592 | [15 empty] | 206.593 | [5 empty] | Cannal,11 KV,Road,400 kv(JAL-SAM) Line Crossing
8 | AP 12/0 | DA+0 |  | 1368.26 | 47°50'12"L | 517986.277 | 3594326.446 | 8 | AP 12/0 | DD+30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1368.261 | 353.883 | 47°50'13"LT | 516437.274 | 3597489.552
|  |  | 289.862 | [15 empty] | 289.862 | [5 empty] | 220 kv(HRN-SAM) Line Crossing
9 | AP 13/0 | DA+0 |  | 1658.122 | 39°08'44"L | 518204.057 | 3594039.789 | 9 | AP 13/0 | DD+25 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 0 | 0 |  | 1658.123 | 348.38 | 39°08'44"LT | 516389.11 | 3597203.72
|  |  | 402.938 | [15 empty] | 402.938 | [5 empty] | Cannal,Cart Track Crossing
10 | AP 14/0 | DC+0 |  | 2061.06 | 14°33'47"R | 518415.918 | 3593760.922 | 10 | AP 14/0 | DB+9 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 2061.061 | 345.17 | 14°33'47"RT | 516588.02 | 3596853.3
|  |  | 284.883 | [15 empty] | 284.883 | [5 empty] | River,220 KV(BAR-HRN)Line Crossing
11 | AP 15/0 | DA+0 |  | 2345.943 | 4°57'01"L | 518741.122 | 3593584.451 | 11 | AP 15/0 | DD+18 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 |  | 2345.944 | 341.282 | 4°57'01"LT | 516661.837 | 3596578.147
|  |  | 420.199 | [15 empty] | 412.199 | [5 empty] | Canal crosssing
12 | 15/1 | DA+0 |  |  |  | 516805.332 | 3596183.208 | 12 | 15/1 | DA+0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 337.118 |  | 516802.6 | 3596190.728
|  |  | 420.127 | [15 empty] | 428.128
13 | 15/2 | DA+0 |  |  |  | 516948.802 | 3595788.337 | 13 | 15/2 | DA+0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 331.591 |  | 516948.803 | 3595788.337
|  |  | 405.152 | [15 empty] | 405.152 | [5 empty] | Road and LT Line crossing
14 | 15/3 | DA+6 |  |  |  | 517087.159 | 3595407.541 | 14 | 15/3 | DA+9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 327.063 |  | 517087.159 | 3595407.541
|  |  | 427.96 | [15 empty] | 427.96
15 | AP 16/0 | DC+6 |  | 1673.438 | 22°18'18"LT | 517233.304 | 3595005.308 | 15 | AP 16/0 | DC+0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1673.439 | 320.406 | 22°18'18"LT | 517233.304 | 3595005.308
|  |  | 285.948 | [15 empty] | 285.948 | [5 empty] | 11 KV,Road,LTLine Crossing
16 | AP 17/0 | DC+3 |  | 285.948 | 19°02'28"LT | 517425.65 | 3594793.72 | 16 | AP 17/0 | DC+3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 285.948 | 317.232 | 19°02'28"LT | 517425.65 | 3594793.72 | LTLine to be shifted
|  |  | 401.159 | [15 empty] | 401.159 | [5 empty] | 11KV,66KV,Road,LTLine Crossing
17 | AP 18/0 | DC+3 |  | 401.159 | 24°05'21"RT | 517777.572 | 3594601.159 | 17 | AP 18/0 | DC+0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 401.159 | 315.046 | 24°05'21"RT | 517777.572 | 3594601.159
|  |  | 345 | [15 empty] | 345 | [5 empty] | LTLine Crossing
18 | 18/1 | DA+0 |  |  |  | 517986.277 | 3594326.446 | 18 | 18/1 | DA+0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 316.217 |  | 517986.277 | 3594326.446
|  |  | 360 | [15 empty] | 360.001
19 | 18/2 | DA+0 |  |  |  | 518204.057 | 3594039.789 | 19 | 18/2 | DA+0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 317.215 |  | 518204.057 | 3594039.789
|  |  | 350.217 | [15 empty] | 350.217 | [5 empty] | Canal crosssing
20 | AP 19/0 | DC+0 |  | 1055.217 | 24°17'20"LT | 518415.918 | 3593760.922 | 20 | AP 19/0 | DC+0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1055.218 | 317.08 | 24°17'20"LT | 518415.918 | 3593760.922
|  |  | 370 | [15 empty] | 369.999 | [5 empty] | LTLine,Road Crossing
21 | 19/1 | DA+0 |  |  |  | 518741.122 | 3593584.451 | 21 | 19/1 | DA+0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 318.753 |  | 518741.122 | 3593584.451
|  |  | 360 | [15 empty] | 360 | [5 empty] | Canal,nalla crosssing
22 | 19/2 | DA+0 |  |  |  | 519057.537 | 3593412.749 | 22 | 19/2 | DA+0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 318.952 |  | 519057.537 | 3593412.749
|  |  | 358.747 | [15 empty] | 358.748 | [5 empty] | Road and LT Line crossing
23 | 20/0 | DB+6 |  | 0 |  | 519372.851 | AP24-AP39 | 23 | 20/0 | DB+6 | Raised Chimney LEG A: Comments by RKPTL , need to be rectified by M/s. KEC; Raised Chimney LEG B: 1.5; Raised Chimney LEG C: 1.5; Raised Chimney LEG D: 1.5 |  | 0 | 320.649 |  | 519372.851 | 3593241.644
|  |  | 485.93 | [15 empty] | 485.93 | [5 empty] | River Crossing
24 | 21/0 | DD+6 |  | 485.93 | 39° 17' 49"RT | 519776.097 | 3592970.498 | 24 | 21/0 | DD+6 | Raised Chimney LEG A: 1.5; Raised Chimney LEG B: 1.5; Raised Chimney LEG C: 1.5; Raised Chimney LEG D: 1.5 |  | 485.93 | 319.74 | 39°17'49" RT | 519776.097 | 3592970.498
|  |  | 325 | [15 empty] | 325 | [5 empty] | 2 nos LT Line,Cart Track
25 | 21/1 | DA+0 |  |  |  | 519869.956 | 3592659.346 | 25 | 21/1 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 316.858 |  | 519869.956 | 3592659.346 | LT Line to be shifted
|  |  | 387.337 | [15 empty] | 387.337 | [5 empty] | 11 kv Line Crossing
26 | 22/0 | DC+3 |  | 712.337 | 15°58'43"LT | 519981.816 | 3592288.512 | 26 | 22/0 | DC+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 712.337 | 312.93 | 15°58'43"LT | 519981.816 | 3592288.512
|  |  | 390 | [15 empty] | 390 | [5 empty] | 3nos LT Line,Road,11 KV Crossing
27 | 22/1 | DA+3 |  |  |  | 520192.878 | 3591960.56 | 27 | 22/1 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 310.637 |  | 520192.878 | 3591960.56
|  |  | 388.629 | [15 empty] | 388.629 | [5 empty] | LT Line crosiing
28 | 22/2 | DA+3 |  |  |  | 520403.198 | 3591633.76 | 28 | 22/2 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 306.671 |  | 520403.198 | 3591633.76
|  |  | 398.45 | [15 empty] | 398.45 | [5 empty] | 2 nos LT Line Crossing
29 | 23/0 | DB+0 |  | 1177.079 | 9°30'47"LT | 520618.833 | 3591298.703 | 29 | 23/0 | DB+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 1177.079 | 303.472 | 9°30'47"LT | 520618.833 | 3591298.703
|  |  | 419.999 | [15 empty] | 435.999 | [5 empty] | Road and LT Line Crossing
30 | 23/1 | DA+6 |  |  |  | 520901.376 | 3590987.947 | 30 | 23/1 | DA+6 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 299.951 |  | 520912.1393 | 3590976.1085
|  |  | 400 | [15 empty] | 384 | [5 empty] | Road,LT Line,11 KV Line Crossing
31 | 23/2 | DA+3 |  |  |  | 521170.464 | 3590691.989 | 31 | 23/2 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 296.476 |  | 521170.464 | 3590691.989
|  |  | 420 | [15 empty] | 420 | [5 empty] | LT Line Crossing
32 | 23/3 | DA+3 |  |  |  | 521453.008 | 3590381.233 | 32 | 23/3 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 293.587 |  | 521453.008 | 3590381.233
|  |  | 410 | [15 empty] | 410 | [5 empty] | 2 nos LT Line Crossing
33 | 23/4 | DA+3 |  |  |  | 521728.824 | 3590077.875 | 33 | 23/4 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 290.264 |  | 521728.824 | 3590077.875
|  |  | 407.25 | [15 empty] | 407.25 | [5 empty] | 2 LT Line,Nalla Crossing
34 | 23/5 | DA+3 |  |  |  | 522002.79 | 3589776.553 | 34 | 23/5 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 286.229 |  | 522002.79 | 3589776.553
|  |  | 397.702 | [15 empty] | 397.702 | [5 empty] | 11 KV,Nalla,Road Crossing
35 | 24/0 | DC+0 |  | 2454.951 | 26° 06' 39"RT | 522270.332 | 3589482.295 | 35 | 24/0 | DC+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 2454.951 | 284.901 | 26°6'39"RT | 522270.332 | 3589482.295
|  |  | 310.147 | [15 empty] | 366.004 | [5 empty] | 2 nos LT Line, Road Crossing
36 | 25/0 | DD+0 |  | 310.147 | 35° 11' 52"LT | 522356.687 | 3589184.412 | 36 | 25/0 | DD+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 366.004 | 282.934 | 36°50'56"LT | 522372.24 | 3589130.764
|  |  | 374.999 | [15 empty] | 372.4 | [5 empty] | Nalla Crossing
37 | 25/1 | DA+0 |  |  |  | 522649.611 | 3588950.275 | 37 | 25/1 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 282.874 |  | 522669.712 | 3588906.729
|  |  | 330 | [15 empty] | 311.866 | [5 empty] | Drain, 2nos LT Line,Road Crossing,
38 | 25/2 | DA+0 |  |  |  | 522907.385 | 3588744.234 | 38 | 25/2 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 283.88 |  | 522918.83 | 3588719.11
|  |  | 366.046 | [15 empty] | 343.763 | [5 empty] | LT Line Crossing
39 | 26/0 | DD+0 |  | 1071.045 | 49° 51' 22"RT | 523193.315 | 3588515.688 | 39 | 26/0 | DD+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 1028.029 | 284.271 | 51°30'37"RT | 523193.427 | 3588512.303
|  |  | 445.757 | [15 empty] | 442.371 | [5 empty] | River Crossing
40 | 27/0 | DB+0 |  | 445.757 | 10° 41' 31"RT | 523205.047 | 3588070.085 | 40 | 27/0 | DB+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 442.371 | 299.465 | 10°41'20"RT | 523205.047 | 3588070.085
|  |  | 320 | [15 empty] | 360 | [5 empty] | LT Line Crossing
41 | 27/1 | DA+3 |  |  |  | 523153.976 | 3587754.187 | 41 | 27/1 | DA+3 | [10 empty] | 295.54 |  | 523147.5919 | 3587714.6997 | Contouring Required | bar: Raised Chimney LEG A to Raised Chimney LEG D
|  |  | 419.739 | [15 empty] | 379.739 | [5 empty] | Road Crossing
42 | 28/0 | DC+6 |  | 739.739 | 27° 47' 33"LT | 523086.985 | 3587339.828 | 42 | 28/0 | DC+6 | Raised Chimney LEG A: 2; Raised Chimney LEG B: 2; Raised Chimney LEG C: 2; Raised Chimney LEG D: 2 |  | 739.739 | 299.027 | 27°47'33"LT | 523086.985 | 3587339.828 | Contouring Required
|  |  | 445.991 | [15 empty] | 445.991 | [5 empty] | 11 KV Line,Road Crossing
43 | 29/0 | DC+9 |  | 445.991 | 22° 59' 55"LT | 523229.302 | 3586917.153 | 43 | 29/0 | DC+9 | Raised Chimney LEG A: 2; Raised Chimney LEG B: 2; Raised Chimney LEG C: 2; Raised Chimney LEG D: 2 |  | 445.991 | 297.021 | 22°59'55"LT | 523229.302 | 3586917.153 | Contouring Required
|  |  | 378 | [15 empty] | 373 | [5 empty] | LT Line Crossing
44 | 29/1 | DA+0 |  |  |  | 523480.302 | 3586634.517 | 44 | 29/1 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 295.767 |  | 523476.9819 | 3586638.2556 | LT Line to be shifted,Contouring Required
|  |  | 361 | [15 empty] | 374
45 | 29/2 | DA+3 |  |  |  | 523720.014 | 3586364.593 | 45 | 29/2 | DA+3 | [10 empty] | 287.94 |  | 523725.3262 | 3586358.6113 | bar: Raised Chimney LEG A to Raised Chimney LEG D
|  |  | 356 | [15 empty] | 352
46 | 29/3 | DA+0 |  |  |  | 523956.405 | 3586098.407 | 46 | 29/3 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 296.014 |  | 523959.0613 | 3586095.4159 | Conturing Required
|  |  | 410 | [15 empty] | 406
47 | 29/4 | DA+0 |  |  |  | 524228.654 | 3585791.844 | 47 | 29/4 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 298.58 |  | 524228.654 | 3585791.844 | Conturing Required
|  |  | 358 | [15 empty] | 352 | [5 empty] | 11 KV Line Crossing
48 | 29/5 | DA+0 |  |  |  | 524466.373 | 3585524.162 | 48 | 29/5 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 296.73 |  | 524462.389 | 3585528.649
|  |  | 324 | [15 empty] | 340 | [5 empty] | Road Crossing
49 | 29/6 | DA+0 |  |  |  | 524681.516 | 3585281.903 | 49 | 29/6 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 287.329 |  | 524688.156 | 3585274.426 | Conturing Required
|  |  | 386.629 | [15 empty] | 376.629 | [5 empty] | 2 nos LTLine,Road,11KV Line Crossing
50 | AP 30/0 | DB+0 |  | 2573.629 | 05° 34' 43"LT | 524938.246 | 3584992.815 | 50 | AP 30/0 | DB+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 2573.629 | 283.957 | 05° 34' 43"LT | 524938.246 | 3584992.815
|  |  | 423 | [15 empty] | 423 | [5 empty] | 11 KV Line Crossing
51 | 30/1 | DA+6 |  |  |  | 525248.542 | 3584705.335 | 51 | 30/1 | DA+6 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 282.422 |  | 525248.542 | 3584705.335
|  |  | 417 | [15 empty] | 417 | [5 empty] | Nalla Crossing
52 | 30/2 | DA+0 |  |  |  | 525554.438 | 3584421.932 | 52 | 30/2 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 281.581 |  | 525554.437 | 3584421.932
|  |  | 415 | [15 empty] | 415 | [5 empty] | Nalla Crossing
53 | 30/3 | DA+6 |  |  |  | 525858.866 | 3584139.888 | 53 | 30/3 | DA+6 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 280.866 |  | 525858.865 | 3584139.889
|  |  | 421 | [15 empty] | 421 | [5 empty] | Cart Track,
54 | 30/4 | DA+0 |  |  |  | 526167.695 | 3583853.767 | 54 | 30/4 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 279.306 |  | 526167.695 | 3583853.768
|  |  | 404 | [15 empty] | 404
55 | 30/5 | DA+9 |  |  |  | 526464.054 | 3583579.2 | 55 | 30/5 | DA+9 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 277.739 |  | 526464.054 | 3583579.2
|  |  | 434.729 | [15 empty] | 434.73 | [5 empty] | Nalla, 2 nos 11 kv,Road Crossing
56 | AP 31/0 | DB+0 |  | 2514.729 | 12° 48' 28"LT | 526782.955 | 3583283.748 | 56 | AP 31/0 | DB+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 2514.73 | 276.594 | 12° 48' 28"LT | 526782.955 | 3583283.748
|  |  | 395 | [15 empty] | 395
57 | 31/1 | DA+3 |  |  |  | 527125.013 | 3583086.211 | 57 | 31/1 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 276.084 |  | 527125.013 | 3583086.211
|  |  | 385 | [15 empty] | 385
58 | 31/2 | DA+0 |  |  |  | 527458.413 | 3582893.675 | 58 | 31/2 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 274.623 |  | 527458.412 | 3582893.675
|  |  | 395 | [15 empty] | 395
59 | 31/3 | DA+0 |  |  |  | 527800.471 | 3582696.138 | 59 | 31/3 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 274.094 |  | 527800.471 | 3582696.138
|  |  | 390 | [15 empty] | 390
60 | 31/4 | DA+3 |  |  |  | 528138.2 | 3582501.102 | 60 | 31/4 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 271.88 |  | 528138.2 | 3582501.102
|  |  | 420 | [15 empty] | 420 | [5 empty] | Nalla,Cart Track
61 | 31/5 | DA+3 |  |  |  | 528501.908 | 3582291.063 | 61 | 31/5 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 271.69 |  | 528501.908 | 3582291.063
|  |  | 389.477 | [15 empty] | 389.48 | [5 empty] | LT Line Crossing
62 | AP 32/0 | DB+0 |  | 2374.477 | 09° 51' 20"RT | 528839.184 | 3582096.288 | 62 | AP 32/0 | DB+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 2374.48 | 270.444 | 09° 51' 20"RT | 528839.184 | 3582096.288
|  |  | 409.999 | [15 empty] | 410 | [5 empty] | Road,11KV Crossing
63 | 32/1 | DA+6 |  |  |  | 529153.896 | 3581833.504 | 63 | 32/1 | DA+6 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 268.214 |  | 529153.896 | 3581833.504
|  |  | 426.984 | [15 empty] | 426.984 | [5 empty] | Nalla Crossing
64 | AP 33/0 | DC+0 |  | 836.983 | 25° 29' 10"RT | 529481.646 | 3581559.834 | 64 | AP 33/0 | DC+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 836.984 | 266.756 | 25° 29' 10"RT | 529481.646 | 3581559.834
|  |  | 289.999 | [15 empty] | 290
65 | 33/1 | DA+0 |  |  |  | 529602.607 | 3581296.266 | 65 | 33/1 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 264.567 |  | 529602.607 | 3581296.267
|  |  | 360 | [15 empty] | 360 | [5 empty] | Nalla Crossing
66 | 33/2 | DA+0 |  |  |  | 529752.766 | 3580969.078 | 66 | 33/2 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 264.358 |  | 529752.766 | 3580969.078
|  |  | 317.799 | [15 empty] | 317.8 | [5 empty] | Nalla,LT Line Crossing
67 | AP 34/0 | DB+0 |  | 967.798 | 05° 33' 15"RT | 529885.323 | 3580680.244 | 67 | AP 34/0 | DB+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 967.8 | 264.775 | 05° 33' 15"RT | 529885.323 | 3580680.244
|  |  | 412.154 | [15 empty] | 427.154 | [5 empty] | Hut,3 nos LT Line Crossing
68 | 34/1 | DA+3 |  |  |  | 530020.173 | 3580290.775 | 68 | 34/1 | DA+6 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 264.717 |  | 530025.08 | 3580276.601
|  |  | 407.753 | [15 empty] | 392.753 | [5 empty] | Carty Track,LT Line,Nalla Crossing
69 | AP 35/0 | DD+0 |  | 819.907 | 35° 45' 17"LT | 530153.583 | 3579905.464 | 69 | AP 35/0 | DD+0 | Raised Chimney LEG A: 2; Raised Chimney LEG B: 2; Raised Chimney LEG C: 2; Raised Chimney LEG D: 2 |  | 819.907 | 263.836 | 35° 45' 17"LT | 530153.583 | 3579905.464
|  |  | 415 | [15 empty] | 415 | [5 empty] | LT Line,2nos 11 kv, Road Crossing
70 | 35/1 | DA+6 |  |  |  | 530492.917 | 3579666.555 | 70 | 35/1 | DA+6 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 264.417 |  | 530492.917 | 3579666.555
|  |  | 405.233 | [15 empty] | 405.234 | [5 empty] | LT Line Crossing
71 | AP 36/0 | DC+0 |  | 820.233 | 15° 39' 07"RT | 530824.265 | 3579433.269 | 71 | AP 36/0 | DC+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 820.234 | 263.776 | 18° 50' 40"RT | 530824.265 | 3579433.269
|  |  | 425.904 | [15 empty] | 439.8
72 | 36/1 | DA+6 |  |  |  | 531093.452 | 3579103.22 | 72 | AP 37/0 | DB+9 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 439.8 | 264.091 | 04° 23' 18"LT | 531082.822 | 3579077.502
|  |  | 380.069 | [15 empty] | 376 | [5 empty] | Road, 11 kv crossing
73 | 36/2 | DA+6 |  |  |  | 531333.669 | 3578808.69 | 73 | 37/1 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 263.543 |  | 531326.349 | 3578791.022
|  |  | 416.942 | [15 empty] | 416 | [5 empty] | 2 nos LT Line,Road, 11 kv Line Crossing
74 | 36/3 | DA+3 |  |  |  | 531597.192 | 3578485.585 | 74 | 37/2 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 261.313 |  | 531595.782 | 3578474.066
|  |  | 419.356 | [15 empty] | 411.4 | [5 empty] | Nalla, Cart Track Crossing
75 | AP 37/0 | DC+0 |  | 1642.271 | 11° 41' 21"RT | 531862.24 | 3578160.61 | 75 | AP 38/0 | DB+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 1203.4 | 261.432 | 12° 51' 19"RT | 531862.24 | 3578160.61
|  |  | 390 | [15 empty] | 390
76 | 37/1 | DA+3 |  |  |  | 532042.391 | 3577814.712 | 76 | 38/1 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 260.879 |  | 532042.391 | 3577814.712
|  |  | 385.272 | [15 empty] | 385.272
77 | AP 38/0 | DC+0 |  | 775.272 | 10° 49' 41"LT | 532220.358 | 3577473.007 | 77 | AP 39/0 | DB+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 775.272 | 260.635 | 10° 49' 41"LT | 532220.358 | 3577473.007
|  |  | 399.206 | [15 empty] | 399.206 | [5 empty] | 2 times 11 kv Line, Road, LT Line,Cart Track
78 | 38/1 | DA+3 |  |  |  | 532467.993 | 3577159.89 | 78 | 39/1 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 258.646 |  | 532467.993 | 3577159.89
|  |  | 407.487 | [15 empty] | 407.487 | [5 empty] | Nalla,2 nos 11 kv line,Road Crossing
79 | 38/2 | DA+0 |  |  |  | 532720.765 | 3576840.278 | 79 | 39/2 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 258.609 |  | 532720.765 | 3576840.278
|  |  | 403.201 | [15 empty] | 403.2 | [5 empty] | Cart Track Crossing
80 | AP 39/0 | DC+3 |  | 1209.894 | 14° 41' 57"LT | 532970.879 | 3576524.027 | 80 | AP 40/0 | DC+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 1209.893 | 258.404 | 14° 41' 57"LT | 532970.879 | 3576524.027
|  |  | 429.653 | [15 empty] | 429.653
81 | 39/1 | DA+3 |  |  |  | 533314.189 | 3576265.687 | 81 | 40/1 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 258.158 |  | 533314.189 | 3576265.687
|  |  | 400.296 | [15 empty] | 400.3 | [5 empty] | 11 kv Line,Road,Nalla Crossing
82 | 39/2 | DA+3 |  |  |  | 533634.042 | 3576024.998 | 82 | 40/2 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 256.271 |  | 533634.042 | 3576024.998
|  |  | 414.63 | [15 empty] | 414.63 | [5 empty] | Nalla,11 kv Crossing
83 | 39/3 | DB+3 |  |  |  | 533965.348 | 3575775.69 | 83 | 40/3 | DB+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 256.993 |  | 533965.348 | 3575775.69
|  |  | 515.886 | [15 empty] | 515.89 | [5 empty] | Road Crossing
84 | AP 40/0 | DD+25 |  | 1760.465 | 36° 33' 25"LT | 534377.562 | 3575465.5 | 84 | AP 41/0 | DD+25 | Raised Chimney LEG A: 4; Raised Chimney LEG B: 4; Raised Chimney LEG C: 4; Raised Chimney LEG D: 4 |  |  | 256.55 | 36° 33' 25"LT | 534377.562 | 3575465.5
|  |  | 212.443 | [15 empty] | 212.443 | [5 empty] | 400 KV D/C Crossing
85 | AP 41/0 | DD+25 |  | 212.443 | 29° 48' 40"RT | 534590 | 3575464 | 85 | AP 42/0 | DD+25 | Raised Chimney LEG A: 4; Raised Chimney LEG B: 4; Raised Chimney LEG C: 4; Raised Chimney LEG D: 4 |  | 212.443 | 255.764 | 29° 48' 40"RT | 534590 | 3575464 | LT Line to be shifted
|  |  | 440 | [15 empty] | 459.999 | [5 empty] | 2 nos 11KV, Road and Nalla Crossing
86 | 41/1 | DA+0 |  |  |  | 534970.22 | 3575242.568 | 86 | 42/1 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 255.089 |  | 534987.503 | 3575232.503
|  |  | 280 | [15 empty] | 260
87 | 41/2 | DA+0 |  |  |  | 535212.179 | 3575101.656 | 87 | 42/2 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 255.033 |  | 535212.178 | 3575101.656
|  |  | 330 | [15 empty] | 330 | [5 empty] | Nalla crossing
88 | 41/3 | DA+0 |  |  |  | 535497.344 | 3574935.582 | 88 | 42/3 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 255.023 |  | 535497.344 | 3574935.582
|  |  | 311.04 | [15 empty] | 311.04 | [5 empty] | 2 nos 11KV, and Cart Track Crossing
89 | AP 42/0 | DD+0 |  | 1361.04 | 36° 03' 25"RT | 535766.125 | 3574779.049 | 89 | AP 43/0 | DD+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 1361.039 | 255.179 | 38° 14' 17"RT | 535766.125 | 3574779.049
|  |  | 389.999 | [15 empty] | 408.948 | [5 empty] | 11 KV Line,River Crossing
90 | 42/1 | DA+3 |  |  |  | 535923.054 | 3574422.016 | 90 | 43/1 | DA+6 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 256.009 |  | 535916.313 | 3574398.678
|  |  | 385 | [15 empty] | 371.345
91 | 42/2 | DA+0 |  |  |  | 536077.972 | 3574069.559 | 91 | 43/2 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 255.012 |  | 536052.691 | 3574053.282
|  |  | 385 | [15 empty] | 364.114 | [5 empty] | LT Line,11KV Line and Road Crossing
92 | 42/3 | DA+3 |  |  |  | 536232.889 | 3573717.103 | 92 | 43/3 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 255.347 |  | 536186.413 | 3573714.612
|  |  | 400 | [15 empty] | 419.36 | [5 empty] | 11 KV Crossing
93 | 42/4 | DA+0 |  |  |  | 536393.843 | 3573350.914 | 93 | 43/4 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 255.104 |  | 536340.424 | 3573324.557
|  |  | 357.48 | [15 empty] | 348.129 | [5 empty] | Road,11 KV,LT Line Crossing
94 | 42/5 | DA+0 |  |  |  | 536537.687 | 3573023.652 | 94 | 44/0 | DB+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 1911.896 | 254.781 | 05° 00' 32"LT | 536468.276 | 3573000.755
|  |  | 367.825 | [15 empty] | 367.848 | [5 empty] | 11 KV Line,LT Line Crossing
95 | 42/6 | DA+0 |  |  |  | 536685.693 | 3572686.919 | 95 | 44/1 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 254.789 |  | 536632.726 | 3572671.713
|  |  | 387.171 | [15 empty] | 396.726 | [5 empty] | Cart Track,Nalla Crossing
96 | 42/7 | DA+0 |  |  |  | 536841.484 | 3572332.475 | 96 | 44/2 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 254.287 |  | 536810.086 | 3572316.84
|  |  | 375.543 | [15 empty] | 375.111 | [5 empty] | Cart Track,LT Line Crossing
97 | 42/8 | DA+0 |  |  |  | 536992.596 | 3571988.676 | 97 | 44/3 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 253.675 |  | 536977.783 | 3571981.302
|  |  | 335.385 | [15 empty] | 335.003 | [5 empty] | 11 KV, LT Line Road crossing
98 | AP 43/0 | DB+0 |  | 3383.403 | 09° 29' 0"RT | 537127.55 | 3571681.64 | 98 | AP 45/0 | DB+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 1474.688 | 253.7 | 12° 18' 41"RT | 537127.55 | 3571681.64 | Lcation Spotted on Bore Well
|  |  | 360 | [15 empty] | 360 | [5 empty] | Road,11 KV,Nalla Crossing
99 | 43/1 | DA+3 |  |  |  | 537216.128 | 3571332.708 | 99 | 45/1 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 252.708 |  | 537216.128 | 3571332.708
|  |  | 360 | [15 empty] | 360 | [5 empty] | 2 nos Cart Track and Road Crossing
100 | 43/2 | DA+0 |  |  |  | 537304.706 | 3570983.775 | 100 | 45/2 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 253.174 |  | 537304.706 | 3570983.775
|  |  | 359.496 | [15 empty] | 359.496 | [5 empty] | LT Line Crossing
101 | AP 44/0 | DB+0 |  | 1079.496 | 09° 05' 54"RT | 537393.16 | 3570635.331 | 101 | AP 46/0 | DB+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 1079.496 | 253.122 | 09° 05' 55"RT | 537393.16 | 3570635.331
|  |  | 350.739 | [15 empty] | 350.739 | [5 empty] | 2nos 11KV,LT Line and Road Crossing
102 | 44/1 | DA+0 |  |  |  | 537424.615 | 3570286.005 | 102 | 46/1 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 252.533 |  | 537424.615 | 3570286.005
|  |  | 337.891 | [15 empty] | 337.891 | [5 empty] | Drain Crossing
103 | 44/2 | DA+0 |  |  |  | 537454.918 | 3569949.476 | 103 | 46/2 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 251.738 |  | 537454.918 | 3569949.476
|  |  | 331.001 | [15 empty] | 331.001 | [5 empty] | 2nos 11KV Line Crossing
104 | 44/3 | DA+0 |  |  |  | 537484.604 | 3569619.809 | 104 | 46/3 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 252.177 |  | 537484.604 | 3569619.809
|  |  | 370.369 | [15 empty] | 360.369 | [5 empty] | 11 KV,3nos LTLine,Nalla Crossing and Poplar Orchard
105 | 44/4 | DA+0 |  |  |  | 537517.82 | 3569250.932 | 105 | 46/4 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 252.018 |  | 537516.923 | 3569260.892
|  |  | 415 | [15 empty] | 425 | [5 empty] | Nalla,Road Crossing
106 | 44/5 | DA+6 |  |  |  | 537555.039 | 3568837.605 | 106 | 46/5 | DA+6 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 251.398 |  | 537555.039 | 3568837.605
|  |  | 411.448 | [15 empty] | 411.448
107 | AP 45/0 | DB+0 |  | 2216.448 | 14° 19' 34"LT | 537591.939 | 3568427.815 | 107 | AP 47/0 | DB+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 2216.448 | 250.71 | 14° 19' 33"RT | 537591.939 | 3568427.815 | poplar orchard
|  |  | 288.426 | [15 empty] | 298 | [5 empty] | LTLine and Poplar orchard
108 | 45/1 | DA+0 |  |  |  | 537545.922 | 3568143.083 | 108 | 47/1 | DA+0 | [10 empty] | 251.309 |  | 537544.395 | 3568133.632 | poplar orchard | bar: Raised Chimney LEG A to Raised Chimney LEG D
|  |  | 378.896 | [15 empty] | 349
109 | 45/2 | DA+0 |  |  |  | 537485.472 | 3567769.04 | 109 | 47/2 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 250.317 |  | 537488.714 | 3567789.102 | poplar orchard
|  |  | 330.346 | [15 empty] | 350 | [5 empty] | 2nos Cart Track and 11 KV Line Crossing
110 | 45/3 | DA+0 |  |  |  | 537432.768 | 3567442.926 | 110 | 47/3 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 250.186 |  | 537432.874 | 3567443.585
|  |  | 362.696 | [15 empty] | 363.364 | [5 empty] | LTLine Crossing
111 | 45/4 | DA+0 |  |  |  | 537374.902 | 3567084.876 | 111 | AP 48 | DB+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 1360.364 | 250.509 | 11° 23' 48"RT | 537374.902 | 3567084.876
|  |  | 349.635 | [15 empty] | 371.504
112 | 45/5 | DB+0 |  |  |  | 537319.12 | 3566739.719 | 112 | AP 49 | DD+25 | Raised Chimney LEG A: 2; Raised Chimney LEG B: 2; Raised Chimney LEG C: 2; Raised Chimney LEG D: 2 |  | 371.504 | 250.679 | 49° 40' 12"RT | 537244.331 | 3566737.074 | Poplar orchard
|  |  | 313.602 | [15 empty] | 203.304 | [5 empty] | 400 KV D/C Crossing
113 | AP 46/0 | DD+25 |  | 2023.601 | 56° 14' 34"RT | 537269.087 | 3566430.134 | 113 | AP 50 | DD+25 | Raised Chimney LEG A: 2; Raised Chimney LEG B: 2; Raised Chimney LEG C: 2; Raised Chimney LEG D: 2 |  | 203.304 | 250.612 | 47° 29' 26"LT | 537052.994 | 3566668.353
|  |  | 203.662 | [15 empty] | 409.908 | [5 empty] | Cart Track and LT Line Crossing
114 | AP 47/0 | DD+30 |  | 203.662 | 56° 35' 59"LT | 537083.876 | 3566345.429 | 114 | AP 50A/0 | DC+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 409.908 | 250.497 | 26° 30' 32"LT | 536894.457 | 3566290.345
|  |  | 432.85 | [15 empty] | 412 | [5 empty] | Road Crossing
115 | 47/1 | DB+9 |  |  |  | 537017.479 | 3565917.702 | 115 | 50A/1 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 249.936 |  | 536921.443 | 3565879.23
|  |  | 475.239 | [15 empty] | 428 | [5 empty] | 2 nos 11kv Line Crossing
116 | AP 48/0 | DB+6 |  | 908.089 | 12° 39' 41"LT | 536944.579 | 3565448.087 | 116 | 50A/2 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 249.342 |  | 536949.478 | 3565452.149
|  |  | 407.305 | [15 empty] | 409 | [5 empty] | 2 nos 11kv Line and Road Crossing
117 | 48/1 | DA+0 |  |  |  | 536971.839 | 3565041.696 | 117 | 50A/3 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 249.638 |  | 536976.269 | 3565044.027
|  |  | 383.49 | [15 empty] | 416 | [5 empty] | 11 KV Line and LT Line Crossing
118 | 48/2 | DA+0 |  |  |  | 536997.505 | 3564659.066 | 118 | 50A/4 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 249.269 |  | 537003.518 | 3564628.92
|  |  | 414.162 | [15 empty] | 397
119 | 48/3 | DA+3 |  |  |  | 537025.224 | 3564245.832 | 119 | 50A/5 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 249.986 |  | 537029.522 | 3564232.773
|  |  | 375.848 | [15 empty] | 337 | [5 empty] | 11 KV Line and LT Line Crossing
120 | 48/4 | DA+3 |  |  |  | 537050.379 | 3563870.827 | 120 | 50A/6 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 249.813 |  | 537051.596 | 3563896.497 | Poplar orchard
|  |  | 424.195 | [15 empty] | 451 | [5 empty] | Cart Track Crossing
121 | 48/5 | DA+3 |  |  |  | 537078.77 | 3563447.583 | 121 | 50A/7 | DA+6 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 248.975 |  | 537081.138 | 3563446.465 | Poplar orchard
|  |  | 395 | [15 empty] | 389 | [5 empty] | Cart Track,11 kv Line Crossing
122 | 48/6 | DA+3 |  |  |  | 537105.206 | 3563053.469 | 122 | 50A/8 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 248.52 |  | 537106.618 | 3563058.301
|  |  | 390 | [15 empty] | 395
123 | 48/7 | DA+0 |  |  |  | 537131.308 | 3562664.343 | 123 | 50A/9 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 248.89 |  | 537132.491 | 3562664.149 | Poplar orchard
|  |  | 390 | [15 empty] | 391 | [5 empty] | LT Line and Cart Track
124 | 48/8 | DA+0 |  |  |  | 537157.41 | 3562275.218 | 124 | 50A/10 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 248.37 |  | 537158.102 | 3562273.989 | Poplar orchard
|  |  | 427.175 | [15 empty] | 425.903 | [5 empty] | Water Pipe Line and Cart Track Crossing
125 | AP 49/0 | DC+9 |  | 3607.175 | 17° 34' 31"LT | 537186 | 3561849 | 125 | AP 51/0 | DC+9 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 4450.903 | 246.843 |  | 537186 | 3561849
126 | AP-53/0 | DC+0 |  | 420.525 | 29°11'18" | 537906.361 | 3560968.449 | 126 | AP-53/0 | DC+0 | [9 empty] | 416.658 | 250.021 | Tentative | 537906.361 | 3560968.449
|  |  | 420.525 | [15 empty] | 416.658 | [5 empty] | 2 nos cat track,11 kv line
127 | AP-54/0 | DC+6 |  | 394.271 | 15°14'19" | 538072.032 | 3560581.933 | 127 | AP-54/0 | DC+6 | [9 empty] | 389.277 | 248.53 | 15°23'8" RT | 538071.474 | 3560585.903
|  |  | 394.271 | [15 empty] | 389.277 | [5 empty] | Pamp house,solar pamp,bore,2 nos 11 kv line
128 | AP-55/0 | DD+3 |  | 786.42 | 38°43'29" | 538126.65 | 3560191.464 | 128 | AP-55/0 | DD+3 | [9 empty] | 793.451 | 248.266 | 38°18'51"RT | 538125.383 | 3560200.377
|  |  | 377.114 | [15 empty] | 384.151 | [5 empty] | Cart Track,11 Kv Line,LT Line
129 | 55/1 | DA+3 |  |  |  | 537933.767 | 3559867.41 | 129 | 55/1 | DA+6 | [10 empty] | 247.77 |  | 537931.255 | 3559868.886
|  |  | 409.306 | [15 empty] | 409.3 | [5 empty] | Nala,POPULAR TREE
130 | AP-56/0 | DC+0 |  |  | 25°29'30" | 537724.418 | 3559515.693 | 130 | AP-56/0 | DC+3 | [10 empty] | 247.416 | 25°53'58" RT | 537724.418 | 3559515.693
|  |  | 409.72 | 1906.102 | [14 empty] | 409.72 | 1906.102 |  |  |  |  | Pamp POPULAR TREE
131 | 56/1 | DA+3 |  |  |  | 537383.735 | 3559288.086 | 131 | 56/1 | DA+6 | [10 empty] | 247.164 |  | 537383.735 | 3559288.085
|  |  | 406.732 | [15 empty] | 406.732 | [5 empty] | Peach Road,Nala POPULAR TREE
132 | 56/2 | DA+3 |  |  |  | 537045.536 | 3559062.138 | 132 | 56/2 | DA+3 | [10 empty] | 246.603 |  | 537045.536 | 3559062.138
|  |  | 389.913 | [15 empty] | 404.913 | [5 empty] | Nala
133 | 56/3 | DA+3 |  |  |  | 536721.322 | 3558845.534 | 133 | 56/3 | DA+6 | [10 empty] | 246.5 |  | 536708.849 | 3558837.201
|  |  | 325.563 | [15 empty] | 285.563 | [5 empty] | 11 Kv Line
134 | 56/4 | DA+6 |  |  |  | 536450.615 | 3558664.677 | 134 | 56/4 | DA+6 | [10 empty] | 247.63 |  | 536471.402 | 3558678.565
|  |  | 374.174 | [15 empty] | 399.174 | [5 empty] | Peach Road,3 NOS 11 KV Line,Crt Track
135 | AP-57/0 | DD+6 |  | 982.372 | 39°39'48" | 536139.488 | 3558456.816 | 135 | AP-57/0 | DD+3 | [9 empty] | 982.372 | 247.141 | 39°39'48" LT | 536139.488 | 3558456.816
|  |  | 343.784 | [15 empty] | 343.784 | [5 empty] | 2 nos Pamp House,2nos 11 Kv Line,Peach Road ,Cart Track
136 | 57/1 | DA+0 |  |  |  | 536041.329 | 3558127.343 | 136 | 57/1 | DA+0 | [10 empty] | 246.804 |  | 536041.329 | 3558127.343
|  |  | 313.063 | [15 empty] | 313.063 | [5 empty] | 2 nos 11 Kv Line, Cart Track,Pamp House
137 | 57/2 | DA+0 |  |  |  | 535951.942 | 3557827.313 | 137 | 57/2 | DA+0 | [10 empty] | 246.653 |  | 535951.941 | 3557827.313
|  |  | 325.525 | [15 empty] | 325.525 | [5 empty] | Pamp House,11 Kv Line
138 | AP-58/0 | DD+0 |  | 406.443 | 24°19'0" | 535858.996 | 3557515.339 | 138 | AP-58/0 | DC+0 | [9 empty] | 406.443 | 246.504 | 24°19'0"RT | 535858.996 | 3557515.339
|  |  | 406.443 | [15 empty] | 406.443 | [5 empty] | 2 nos 11 KV Line,Peach Road,
139 | AP-59/0 | DD+6 |  |  | 47°9'41" | 535592.844 | 3557208.16 | 139 | AP-59/0 | DD+6 | [10 empty] | 245.264 | 47°9'41"LT | 535592.844 | 3557208.16
|  |  | 393.08 | 788.039 | [14 empty] | 423.081 | 788.039 |  |  |  |  | 11 KV Line,Nala
140 | 59/1 | DA+6 |  |  |  | 535635.668 | 3556817.419 | 140 | 59/1 | DA+3 | [10 empty] | 245.759 |  | 535638.936 | 3556787.597
|  |  | 394.959 | [15 empty] | 364.958 | [5 empty] | 3 nos 11 KV Line,2 nos Peach Road
141 | AP-60/0 | DB+6 |  | 757.575 | 8°29'30" | 535678.696 | 3556424.811 | 141 | AP-60/0 | DB+6 | [9 empty] | 757.575 | 245.819 | 8°29'30"LT | 535678.696 | 3556424.811
|  |  | 380.949 | [15 empty] | 380.949 | [5 empty] | 11 KV Line
142 | 60/1 | DA+0 |  |  | 21°46'8" | 535775.661 | 3556056.409 | 142 | 60/1 | DA+0 | [10 empty] | 245.478 |  | 535775.661 | 3556056.409
|  |  | 376.626 | [15 empty] | 376.626 | [5 empty] | 11 KV Line ,Cart Track
143 | AP-61/0 | DC+0 |  | 547.975 | 21°46'8" | 535871.525 | 3555692.188 | 143 | AP-61/0 | DC+0 | [9 empty] | 563.919 | 245.252 | 21°54'40" RT | 535871.525 | 3555692.188
|  |  | 299.109 | [15 empty] | 299.077 | [5 empty] | 11 KV Line
144 | 61/1 | DA+0 |  |  |  | 535834.954 | 3555395.323 | 144 | 61/1 | DA+0 | [10 empty] | 245.05 |  | 535834.222 | 3555395.446
|  |  | 248.866 | [15 empty] | 264.842 | [5 empty] | Road,3 nos 11KVLine
145 | AP-62/0 | DB+0 |  | 1097.236 | 5°0'50" | 535804.525 | 3555148.324 | 145 | AP-62/0 | DB+0 | [9 empty] | 1081.233 | 244.83 | 4°52'29" RT | 535801.188 | 3555132.673
|  |  | 380.068 | [15 empty] | 364.064 | [5 empty] | Pamp House
146 | 62/1 | DA+0 |  |  |  | 535725.265 | 3554776.613 | 146 | 62/1 | DA+0 | [10 empty] | 244.347 |  | 535725.265 | 3554776.613
|  |  | 319.184 | [15 empty] | 319.184 | [5 empty] | 11 KV Line
147 | 62/2 | DA+0 |  |  |  | 535658.701 | 3554464.447 | 147 | 62/2 | DA+0 | [10 empty] | 244.154 |  | 535658.701 | 3554464.447
|  |  | 397.984 | [15 empty] | 397.985 | [5 empty] | 11 KV Line,Cart Track
148 | AP-63/0 | DB+9 |  | 450.859 | 12°25'24" | 535575.704 | 3554075.213 | 148 | AP-63/0 | DB+9 | [9 empty] | 450.859 | 244.074 | 12°25'23"LT | 535575.704 | 3554075.213
|  |  | 450.859 | [15 empty] | 450.859 | [5 empty] | 3 nos 11KV Line,Pamp House,CartTrack
149 | AP-64/0 | DC+9 |  |  | 17°10'17" | 535578.743 | 3553624.364 | 149 | AP-64/0 | DC+9 | [10 empty] | 243.572 | 17°10'17" RT | 535578.743 | 3553624.364
|  |  | 326.478 | 602.841 | [14 empty] | 326.477 | 602.84
150 | 64/1 | DA+0 |  |  |  | 535484.461 | 3553311.796 | 150 | 64/1 | DA+0 | [10 empty] | 243.963 |  | 535484.461 | 3553311.797
|  |  | 276.363 | [15 empty] | 276.363 | [5 empty] | Road,Cart Track, 11 KV Line, Peach Road
151 | AP-65/0 | DB+0 |  |  | 12°37'37" | 535404.652 | 3553047.208 | 151 | AP-65/0 | DB+0 | [10 empty] | 243.196 | 12°37'37" RT | 535404.652 | 3553047.208
|  |  | 307.216 | 2228.492 | [14 empty] | 307.216 | 2228.492 |  |  |  |  | Nala
152 | 65/1 | DA+0 |  |  |  | 535253.782 | 3552779.589 | 152 | 65/1 | DA+0 | [10 empty] | 243.218 |  | 535253.782 | 3552779.589
|  |  | 389.397 | [15 empty] | 389.397 | [5 empty] | 2 nos 11 KV Line
153 | 65/2 | DA+6 |  |  |  | 535062.553 | 3552440.381 | 153 | 65/2 | DA+6 | [10 empty] | 242.836 |  | 535062.554 | 3552440.382
|  |  | 368.792 | [15 empty] | 368.792 | [5 empty] | Cart Track ,Peach Road.
154 | 65/3 | DA+0 |  |  |  | 534881.444 | 3552119.123 | 154 | 65/3 | DA+0 | [10 empty] | 242.408 |  | 534881.444 | 3552119.123
|  |  | 404.386 | [15 empty] | 404.386
155 | 65/4 | DA+3 |  |  |  | 534682.855 | 3551766.858 | 155 | 65/4 | DA+3 | [10 empty] | 242.131 |  | 534682.855 | 3551766.858
|  |  | 378.135 | [15 empty] | 378.135 | [5 empty] | Cart Tarck, 2nos 11 KV Line
156 | 65/5 | DA+3 |  |  |  | 534497.158 | 3551437.461 | 156 | 65/5 | DA+3 | [10 empty] | 241.837 |  | 534497.158 | 3551437.461
|  |  | 380.566 | [15 empty] | 380.566 | [5 empty] | Peach Road,2 nos 11 KV Line
157 | 66/0 | DC+0 |  |  | 27°53'14" | 534310.267 | 3551105.946 | 157 | 66/0 | DC+0 | [10 empty] | 241.546 | Tentative | 534310.267 | 3551105.946
158 | AP 70 | DC+3 |  | 1599.782 | 28°13'44"RT | 533703.461 | 3547814.252 | 158 | AP 70 | DC+3 | [9 empty] | 1598.955 | 242.922 | Tentative | 533703.461 | 3547814.252
|  |  | 381.554 | [15 empty] | 435.863 | [5 empty] | 11kv Line
159 | 70/1 | DA+0 |  |  |  | 533491.278 | 3547497.137 | 159 | 70/1 | DA+9 | [10 empty] | 242.715 |  | 533459.001 | 3547453.398
|  |  | 392.701 | [15 empty] | 338.945
160 | 70/2 | DA+0 |  |  |  | 533272.897 | 3547170.758 | 160 | 70/2 | DA+0 | [10 empty] | 242.635 |  | 533268.899 | 3547172.783
|  |  | 414.335 | [15 empty] | 497.836 | [5 empty] | Peach Road,11kv Line nos.2 ,Cut Track
161 | 70/3 | DA+3 |  |  |  | 533042.484 | 3546826.398 | 161 | 70/3 | DD+18 | Raised Chimney LEG A: 2; Raised Chimney LEG B: 2; Raised Chimney LEG C: 2; Raised Chimney LEG D: 2 |  |  | 242.408 | 2°59'27"LT | 532989.68 | 3546760.621
|  |  | 411.192 | [15 empty] | 326.311 | [5 empty] | Cut Track,11kv Line nos.3,132kv Line,Peach Road
162 | AP 71 | DC+0 |  |  | 20°21'35"LT | 532813.82 | 3546484.65 | 162 | AP 71 | DC+9 | [9 empty] | 1666.222 | 242.52 | 17°25'49"LT | 532821.009 | 3546481.284
|  |  | 416.863 | 1667.808 | [14 empty] | 415.29 | [5 empty] | 11kv Line nos.2
163 | 71/1 | DA+3 |  |  |  | 532717.021 | 3546079.182 | 163 | 71/1 | DA+3 | [10 empty] | 242.914 |  | 532722.691 | 3546077.8
|  |  | 422.426 | [15 empty] | 422.422 | [5 empty] | RCC Road,11kv Line
164 | 71/2 | DA+6 |  |  |  | 532618.93 | 3545668.302 | 164 | 71/2 | DA+6 | [10 empty] | 243.716 |  | 532622.685 | 3545667.387
|  |  | 418.378 | [15 empty] | 418.373 | [5 empty] | Peach Road,11kv Line nos.2 ,LT Line,Pump House
165 | 71/3 | DA+6 |  |  |  | 532521.779 | 3545261.36 | 165 | 71/3 | DA+6 | [10 empty] | 243.867 |  | 532523.638 | 3545260.907
|  |  | 410.141 | [15 empty] | 410.137 | [5 empty] | Cut Track,Nala,Peach Road,Pump House nos.2,11kv Line
166 | AP 72 | DB+0 |  |  | 2°47'40"LT | 532426.54 | 3544862.43 | 166 | AP 72 | DB+0 | Raised Chimney LEG A: 1.5; Raised Chimney LEG B: 1.5; Raised Chimney LEG C: 1.5; Raised Chimney LEG D: 1.5 |  | 809.571 | 244.921 | 1°9'23"LT | 532426.54 | 3544862.43
|  |  | 422.698 | 820.509 | [14 empty] | 422.214 | [5 empty] | 11Kkv Line nos.2, Cut Track
167 | 72/1 | DA+3 |  |  |  | 532348.546 | 3544446.99 | 167 | 72/1 | DA+3 | [10 empty] | 243.634 |  | 532334.883 | 3544450.284
|  |  | 397.811 | [15 empty] | 387.357 | [5 empty] | Cut Track,11kv Live
168 | AP 73 | DB+6 |  | 397.142 | 5°50'37"RT | 532275.144 | 3544056.01 | 168 | AP 73 | DA+6 | [9 empty] | 406.688 | 244.201 |  | 532250.793 | 3544072.165
|  |  | 397.142 | [15 empty] | 406.688 | [5 empty] | 11kv Line, Cut Track
169 | AP 74 | DC+0 |  |  | 20°42'17"LT | 532162.507 | 3543675.176 | 169 | AP 74 | DB+0 | [10 empty] | 243.493 | 12°51'60"LT | 532162.507 | 3543675.176
|  |  | 305.026 | 305.026 | [14 empty] | 316.253 | 316.253 |  |  |  |  | LT Line,11kv Line nos.2,Pump House,Peach Road
170 | AP 75 | DD+18 |  | 259.883 | 1°18'37"LT | 532184.997 | 3543370.98 | 170 | AP 75 | DD+9 | [10 empty] | 243.53 | 3°17'24"LT | 532164.321 | 3543358.928
|  |  | 259.883 | [15 empty] | 248.423 | 248.423 |  |  |  |  | NH Road,11kv Line,66 kv line
171 | AP 76 | DD+18 |  |  | 12°20'42"LT | 532210.08 | 3543112.31 | 171 | AP 76 | DD+9 | [9 empty] | 1681.454 | 243.28 | 15°15'15"LT | 532180 | 3543111
|  |  | 458.101 | 1673.212 | [14 empty] | 427.328 | [5 empty] | Nala
172 | 76/1 | DA+0 |  |  |  | 532350.754 | 3542676.343 | 172 | 76/1 | DA+0 | [10 empty] | 243.937 |  | 532318.226 | 3542706.646
|  |  | 381.451 | [15 empty] | 413.234 | [5 empty] | Cart track, 11 kv line
173 | 76/2 | DA+0 |  |  |  | 532467.891 | 3542313.322 | 173 | 76/2 | DA+3 | [10 empty] | 244.927 |  | 532451.893 | 3542315.627
|  |  | 407.013 | [15 empty] | 414.719
174 | 76/3 | DA+3 |  |  |  | 532592.877 | 3541925.975 | 174 | 76/3 | DA+3 | [10 empty] | 246.9 |  | 532586.041 | 3541923.204
|  |  | 426.647 | [15 empty] | 426.173 | [5 empty] | 2 nos 11 kv line,
175 | AP 77 | DB+3 |  |  | 5°27'44"LT | 532723.893 | 3541519.942 | 175 | AP 77 | DB+3 | [10 empty] | 247.023 | 4°28'22"LT | 532723.893 | 3541519.942
|  |  | 404.809 | 1630.397 | [14 empty] | 404.809 | 1630.396 |  |  |  |  | 2 nos Pamp house,3 nos 11 kv line ,Peach Road
176 | 77/1 | DA+0 |  |  |  | 532884.309 | 3541148.274 | 176 | 77/1 | DA+0 | [10 empty] | 247.026 |  | 532884.309 | 3541148.274
|  |  | 392.738 | [15 empty] | 392.738 | [5 empty] | 11 Kv Line .LT Line,Pamp house
177 | 77/2 | DA+0 |  |  |  | 533039.942 | 3540787.689 | 177 | 77/2 | DA+0 | [10 empty] | 247.048 |  | 533039.942 | 3540787.689
|  |  | 391.939 | [15 empty] | 391.939 | [5 empty] | 2 nos 11 kv line,Peach Road
178 | 77/3 | DA+0 |  |  |  | 533195.258 | 3540427.838 | 178 | 77/3 | DA+0 | [10 empty] | 247.309 |  | 533195.259 | 3540427.837
|  |  | 440.911 | [15 empty] | 440.91
179 | AP 78 | DD+18 |  |  | 3°32'31"RT | 533369.981 | 3540023.024 | 179 | AP 78 | DD+18 | [10 empty] | 248.954 | 2°8'23"RT | 533369.981 | 3540023.024 | bar: Raised Chimney LEG A to Raised Chimney LEG D
|  |  | 186.014 | 186.014 | [14 empty] | 320.743 | 320.7425 |  |  |  |  | 132 KV Line Crossing,2nos 11kv line,Peach Road
180 | AP 79 | DD+9 |  |  | 21°37'48"LT | 533433.003 | 3539848.011 | 180 | AP 79 | DD+9 | [10 empty] | 250.76 | 31°24'00"LT | 533486 | 3539724
|  |  | 372.46 | 372.46 | [14 empty] | 242.225 | 242.225 |  |  |  |  | NH Crossing,2 nos 11 kv line,Cart Track
181 | AP 80 | DD+0 |  |  | 37°14'10"RT | 533679.48 | 3539568.77 | 181 | AP 80 | DD+0 | [9 empty] | 839.249 | 253.15 | 50°30'34"RT | 533678.443 | 3539576.899
|  |  | 378.292 | 378.292 | [14 empty] | 380.988 | [5 empty] | 2 nos 11 kv line,Cart Track,Peach Road,Nala
182 | 80/1 | DA+0 |  | 703.042 |  | 533707.17 | 3539191.493 | 182 | 80/1 | DA+0 | [10 empty] | 252.871 |  | 533692.382 | 3539196.166
|  |  | 455.595 | [15 empty] | 458.261
183 | AP 81 | DD+9 |  |  | 34°8'5"LT | 533740.519 | 3538737.12 | 183 | AP 81 | DD+9 | [10 empty] | 252.385 | 45°20'20"LT | 533709.148 | 3538738.212
|  |  | 247.447 | [15 empty] | 242.663 | 242.663 |  |  |  |  | Raliway Crossing,2 nos Cart Track,Peach Road,Pamp House,DP
184 | AP 82 | DD+9 |  |  | 27°45'23"RT | 533893.991 | 3538543.016 | 184 | AP 82 | DD+3 | [9 empty] | 1149.152 | 252.473 | 36°50'39"RT | 533887.874 | 3538574.071
|  |  | 376.607 | 1117.502 | [14 empty] | 408.258 | [5 empty] | Cart Track
185 | 82/1 | DA+0 |  |  |  | 533963.113 | 3538172.807 | 185 | 82/1 | DA+0 | [10 empty] | 252.708 |  | 533962.914 | 3538172.769
|  |  | 342.477 | [15 empty] | 342.476 | [5 empty] | Peach Road,11Kv Line
186 | 82/2 | DA+0 |  |  |  | 534025.97 | 3537836.148 | 186 | 82/2 | DA+0 | [10 empty] | 252.365 |  | 534025.863 | 3537836.128
|  |  | 398.418 | [15 empty] | 398.418
187 | AP 83 | DD+18 |  |  | 0°35'33"LT | 534099.095 | 3537444.498 | 187 | AP 83 | DD+18 | [10 empty] | 251.542 | 0°34'37"LT | 534099.095 | 3537444.498
|  |  | 251.516 | 251.516 | [14 empty] | 251.516 | 251.516 |  |  |  |  | 220 KV Line Crossing,11KV Line
188 | AP 84 | DD+18 |  |  | 2°42'43"RT | 534147.812 | 3537197.745 | 188 | AP 84 | DD+18 | [10 empty] | 251.394 | 3°10'24"RT | 534147.812 | 3537197.745
|  |  | 430.213 | 430.213 | [14 empty] | 445.126 | 445.126 |  |  |  |  | Upper Bari Doad Canal,Cart Tarck,11 Kv Line
189 | AP 85 | DB+0 |  |  | 2°42'42"RT | 534211.08 | 3536772.21 | 189 | AP 85 | DB+0 | [10 empty] | 248.76 | 1°42'24"RT | 534209.724 | 3536756.945
|  |  | 413.168 | 834.258 | [14 empty] | 418.777 | 838.553 |  |  |  |  | Village Road ,11 Kv Line ,2 Nos Pump House
190 | 85/1 | DA+6 |  |  |  | 534252.374 | 3536361.111 | 190 | 85/1 | DA+6 | [10 empty] | 249.171 |  | 534255.595 | 3536340.689
|  |  | 421.09 | [15 empty] | 419.776 | [5 empty] | Cart Tarck,Village Road
191 | AP 86 | DC+0 |  | 835.173 | 15°06'21"LT | 534294.46 | 3535942.13 | 191 | AP 86 | DC+0 | [9 empty] | 836.764 | 248.58 | 14°18'25"LT | 534301.576 | 3535923.439
|  |  | 400.632 | [15 empty] | 404.589 | [5 empty] | Nala,Village Road,11 Kv Line,LT Line
192 | 86/1 | DA+3 |  |  |  | 534437.001 | 3535567.712 | 192 | 86/1 | DA+3 | [10 empty] | 247.868 |  | 534443.898 | 3535544.708
|  |  | 434.541 | [15 empty] | 432.175 | [5 empty] | 11 Kv Line,LT Line,Village Road
193 | AP 87 | DB+9 |  |  | 9°27'32"RT | 534591.606 | 3535161.605 | 193 | AP 87 | DB+9 | [10 empty] | 247.573 | 8°55'19"RT | 534595.924 | 3535140.155
|  |  | 384.782 | 1209.716 | [14 empty] | 383.249 | 1185.42 |  |  |  |  | 11 Kv Line,Nala
194 | 87/1 | DA+3 |  |  |  | 534667.548 | 3534784.392 | 194 | 87/1 | DA+3 | [10 empty] | 259.11 |  | 534673.47 | 3534764.833
|  |  | 376.645 | [15 empty] | 382.084 | [5 empty] | 11 Kv Line ,2 Nos Pump House
195 | 87/2 | DA+3 |  |  |  | 534741.884 | 3534415.155 | 195 | 87/2 | DA+3 | [10 empty] | 259.087 |  | 534750.78 | 3534390.652
|  |  | 448.289 | [15 empty] | 420.087 | [5 empty] | 11 Kv Line,Village Road
196 | AP 88 | DD+18 |  |  | 31°55'40"LT | 534830.36 | 3533975.684 | 196 | AP 88 | DD+18 | [10 empty] | 259.185 | 29°54'06"LT | 534835.779 | 3533979.254
|  |  | 212.085 | 212.085 | [14 empty] | 211.063 | 211.063 |  |  |  |  | 220 kv Line Crossing ,3 nos11 kv Line
197 | AP 89 | DD+18 |  |  | 34°27'36"RT | 534975.841 | 3533821.361 | 197 | AP 89 | DD+18 | [10 empty] | 259.192 | 31°35'10"RT | 534975.841 | 3533821.361 | 11 kv line shifting
|  |  | 384.985 | 604.231 | [14 empty] | 385.103 | 618.229 |  |  |  |  | Cart Tarck,Village Road,11 kv Line,Bore
198 | 89/1 | DA+3 |  |  |  | 535035.073 | 3533440.96 | 198 | 89/1 | DA+3 | [10 empty] | 259.195 |  | 535042.642 | 3533442.096
|  |  | 219.246 | [15 empty] | 233.126 | [5 empty] | 2 Nos 11 Kv Line,LT Line,Village Road
199 | AP 90 | DD+0 |  |  | 41°31'33"LT | 535068.805 | 3533224.324 | 199 | AP 90 | DD+0 | [10 empty] | 259.264 | 40°23'13"LT | 535083.08 | 3533212.504
|  |  | 389.651 | 1199.544 | [14 empty] | 401.232 | 1181.01 |  |  |  |  | 3 Nos 11 Kv Line,Village Road
200 | 90/1 | DA+3 |  |  |  | 535368.932 | 3532975.826 | 200 | 90/1 | DA+3 | [10 empty] | 259.921 |  | 535392.127 | 3532956.62
|  |  | 367.11 | [15 empty] | 342.999 | [5 empty] | 11 Kv Line
201 | 90/2 | DA+0 |  |  |  | 535651.697 | 3532741.703 | 201 | 90/2 | DA+0 | [10 empty] | 260.325 |  | 535656.321 | 3532737.873
|  |  | 442.783 | [15 empty] | 436.779 | [5 empty] | 2 Nos 11 Kv Line,LT Line,Village Road
202 | AP 91 | DD+18 |  |  | 7°0'57"RT | 535992.749 | 3532459.319 | 202 | AP 91 | DD+25 | [10 empty] | 260.559 | 11°45'19"RT | 535992.749 | 3532459.319
|  |  | 242.124 | 242.124 | [14 empty] | 247.685 | 247.685 |  |  |  |  | 220 kv Line Crossing ,11 kv Line,Village Road,Nala
203 | AP 92 | DD+18 |  |  | 39°23'4"RT | 536158.986 | 3532283.282 | 203 | AP 92 | DD+18 | [10 empty] | 260.692 | 34°8'24"RT | 536147.344 | 3532265.804
|  |  | 377.468 | 1471.729 | [14 empty] | 360.878 | 1455.156 |  |  |  |  | 11 Kv Line
204 | 92/1 | DA+3 |  |  |  | 536185.157 | 3531906.723 | 204 | 92/1 | DA+3 | [10 empty] | 260.876 |  | 536175.537 | 3531906.029
|  |  | 415.652 | [15 empty] | 415.643 | [5 empty] | 2 Nos 11 Kv Line,Cart Track
205 | 92/2 | DA+6 |  |  |  | 536213.976 | 3531492.071 | 205 | 92/2 | DA+6 | [10 empty] | 259.988 |  | 536208.008 | 3531491.659
|  |  | 378.397 | [15 empty] | 379.751 | [5 empty] | Village Road
206 | 92/3 | DA+0 |  |  |  | 536240.211 | 3531114.584 | 206 | 92/3 | DA+0 | [10 empty] | 259.393 |  | 536237.676 | 3531113.066
|  |  | 300.212 | [15 empty] | 298.884 | [5 empty] | 11 Kv Line
207 | AP 93 | DC+0 |  | 889.075 | 18°10'19"RT | 536261.026 | 3530815.095 | 207 | AP 93 | DC+0 | [9 empty] | 889.075 | 259.567 | 18°40'38"RT | 536261.026 | 3530815.095
|  |  | 314.663 | [15 empty] | 314.664 | [5 empty] | Village Road,11 Kv Line
208 | 93/1 | DA+0 |  |  |  | 536183.855 | 3530510.041 | 208 | 93/1 | DA+0 | [10 empty] | 260.007 |  | 536183.855 | 3530510.041
|  |  | 301.757 | [15 empty] | 301.757 | [5 empty] | 2 Nos 11 Kv Line,Village Road
209 | 93/2 | DA+0 |  |  |  | 536109.85 | 3530217.5 | 209 | 93/2 | DA+0 | [10 empty] | 259.339 |  | 536109.85 | 3530217.499
|  |  | 272.655 | [15 empty] | 272.654
210 | AP 94 | DB+0 |  |  | 0°29'53"RT | 536042.983 | 3529953.172 | 210 | A[P 94 | DB+0 | [10 empty] | 259.192 | 0°29'54"RT | 536042.983 | 3529953.172
|  |  | 411.542 | 411.542 | [14 empty] | 411.542 | 411.542 |  |  |  |  | Road
211 | AP 95 | DC+3 |  |  | 19°44'6"LT | 535938.588 | 3529555.091 | 211 | AP 95 | DC+3 | [10 empty] | 258.815 | 19°44'6"LT | 535938.588 | 3529555.091
|  |  | 375.053 | 1751.018 | [14 empty] | 375.054 | 1751.019 |  |  |  |  | 11kv Line,Pump House
212 | 95/1 | DA+0 |  |  |  | 535971.537 | 3529181.488 | 212 | 95/1 | DA+0 | [10 empty] | 258.941 |  | 535971.537 | 3529181.487
|  |  | 357.801 | [15 empty] | 357.801 | [5 empty] | Pump House,Cart track,11kv D.P
213 | 95/2 | DA+0 |  |  |  | 536002.972 | 3528825.07 | 213 | 95/2 | DA+0 | [10 empty] | 258.584 |  | 536002.972 | 3528825.07
|  |  | 338.209 | [15 empty] | 338.209 | [5 empty] | 11kv Line
214 | 95/3 | DA+0 |  |  |  | 536032.685 | 3528488.169 | 214 | 95/3 | DA+0 | [10 empty] | 258.516 |  | 536032.685 | 3528488.169
|  |  | 358.793 | [15 empty] | 358.793 | [5 empty] | 11KV LINE,Cart Track
215 | 95/4 | DA+0 |  |  |  | 536064.206 | 3528130.763 | 215 | 95/4 | DA+0 | [10 empty] | 259.278 |  | 536064.206 | 3528130.763
|  |  | 321.162 | [15 empty] | 321.162 | [5 empty] | LT LINE, 11KV LINE,Pump House
216 | AP 96 | DC+0 |  |  | 21°39'3"LT | 536092.421 | 3527810.843 | 216 | AP 96 | DC+0 | [10 empty] | 258.704 | 21°39'3"LT | 536092.421 | 3527810.843
217 | AP 115/0 | DB+0 |  | 751.41 | 10°13'52"LT | 537339.014 | 3519225.887 | 217 | AP 115/0 | DB+0 | [9 empty] | 751.411 | 255.816 | 10°13'52"LT | 537339.014 | 3519225.887
|  |  | 373.378 | [15 empty] | 373.379 | [5 empty] | CT ROAD,LT LINE,RCC DRAIN,ROAD,LT LINE 11kV
218 | 115/1 | DA+6 |  |  |  | 537297.253 | 3518854.852 | 218 | 115/1 | DA+6 | [10 empty] | 255.913 |  | 537297.253 | 3518854.852
|  |  | 378.003 | [15 empty] | 378.032 | [5 empty] | 66kV
219 | AP 116/0 | DB+0 |  | 515.47 | 4°18'31"LT | 537254.972 | 3518479.191 | 219 | AP 116/0 | DB+0 | [9 empty] | 515.469 | 255.826 | 4°18'31"LT | 537254.972 | 3518479.191
|  |  | 283.156 | [15 empty] | 283.157 | [5 empty] | CANEL,ROAD,11 Kv
220 | 116/1 | DA+0 |  |  |  | 537244.531 | 3518196.227 | 220 | 116/1 | DC+0 | [10 empty] | 254.81 |  | 537244.531 | 3518196.227 | 2nd Transposition Tower
|  |  | 232.312 | [15 empty] | 232.312
221 | AP 117/0 | DB+0 |  |  | 6°09'51"RT | 537235.965 | 3517964.073 | 221 | AP 117/0 | DB+0 | [10 empty] | 254.461 | 6°09'51"RT | 537235.965 | 3517964.073
|  |  | 323.186 | 1409.68 | [14 empty] | 323.186 | 1409.681 |  |  |  |  | 11kV,S.H,LT LINE
222 | 117/1 | DA+0 |  |  |  | 537189.438 | 3517644.254 | 222 | 117/1 | DA+0 | [10 empty] | 254.091 |  | 537189.438 | 3517644.254
|  |  | 351.475 | [15 empty] | 351.475 | [5 empty] | 11kV,ROAD,11kV
223 | 117/2 | DA+3 |  |  |  | 537138.839 | 3517296.44 | 223 | 117/2 | DA+3 | [10 empty] | 253.624 |  | 537138.839 | 3517296.44
|  |  | 368.874 | [15 empty] | 368.874 | [5 empty] | LT LINE
224 | 117/3 | DA+0 |  |  |  | 537085.734 | 3516931.409 | 224 | 117/3 | DA+0 | [10 empty] | 252.684 |  | 537085.734 | 3516931.409
|  |  | 366.147 | [15 empty] | 366.146 | [5 empty] | ROAD,LT LINE,11kV,11kV
225 | AP 118/0 | DC+0 |  | 634.36 | 16°09'46"LT | 537033.022 | 3516569.076 | 225 | AP 118/0 | DC+0 | [9 empty] | 634.359 | 252.402 | 16°09'46"LT | 537033.022 | 3516569.076
|  |  | 326.21 | [15 empty] | 326.211 | [5 empty] | LT LINE,ROAD
226 | 118/1 | DA+0 |  |  |  | 537077.777 | 3516245.951 | 226 | 118/1 | DA+0 | [10 empty] | 253.281 |  | 537077.777 | 3516245.951
|  |  | 308.149 | [15 empty] | 308.148 | [5 empty] | LT.LINE,LT LINE,LT LINE
227 | AP 119/0 | DC+0 |  | 518.18 | 26°16'41"LT | 537120.054 | 3515940.716 | 227 | AP 119/0 | DC+0 | [9 empty] | 518.175 | 253.51 | 26°16'41"LT | 537120.054 | 3515940.716
|  |  | 285.935 | [15 empty] | 285.936 | [5 empty] | 11kV,11kV
228 | 119/1 | DA+0 |  |  |  | 537280.623 | 3515704.123 | 228 | 119/1 | DA+0 | [10 empty] | 253.748 |  | 537280.623 | 3515704.123
|  |  | 232.24 | [15 empty] | 232.239 | [5 empty] | ROAD, LT LINE ,LT LINE
229 | AP 120/0 | DD+0 |  | 1212.37 | 42°02'04"RT | 537411.04 | 3515511.959 | 229 | AP 120/0 | DD+0 | [9 empty] | 1212.369 | 254.132 | 42°02'04"RT | 537411.04 | 3515511.959
|  |  | 396.913 | [15 empty] | 396.914 | [5 empty] | RCC NALA
230 | 120/1 | DA+3 |  |  |  | 537356.687 | 3515118.785 | 230 | 120/1 | DA+3 | [10 empty] | 253.923 |  | 537356.687 | 3515118.785
|  |  | 412.776 | [15 empty] | 412.766 | [5 empty] | LT LINE,11kV,CANEL,LT LINE,CT ROAD
231 | 120/2 | DA+6 |  |  |  | 537300.163 | 3514709.907 | 231 | 120/2 | DA+6 | [10 empty] | 253.783 |  | 537300.163 | 3514709.907
|  |  | 402.69 | [15 empty] | 402.689 | [5 empty] | ROAD,11kV TRANSFORMER
232 | AP 121/0 | DC+3 |  | 1136.05 | 20°15'43"LT | 537245.018 | 3514311.011 | 232 | AP 121/0 | DC+3 | [9 empty] | 1136.859 | 253.607 | 19°30'25"LT | 537245.018 | 3514311.011
|  |  | 373.866 | [15 empty] | 374.133 | [5 empty] | LT LINE,CT ROAD,11kV
233 | 121/1 | DA+0 |  |  |  | 537325.244 | 3513945.854 | 233 | 121/1 | DA+0 | [10 empty] | 253.477 |  | 537320.478 | 3513944.567
|  |  | 377.108 | [15 empty] | 377.376 | [5 empty] | 11kV,LT LINE,LT LINE
234 | 121/2 | DA+0 |  |  |  | 537406.164 | 3513577.53 | 234 | 121/2 | DA+0 | [10 empty] | 253.354 |  | 537396.591 | 3513574.946
|  |  | 385.076 | [15 empty] | 385.35 | [5 empty] | CT ROAD,LT LINE,11kV,11kV
235 | 122/0 | DB+0 |  | 753.4 | 2°42'37"LT | 537488.795 | 3513201.424 | 235 | AP122/0 | DB+0 | [9 empty] | 753.546 | 253.229 | 4°36'22"LT | 537474.313 | 3513197.516 | AP SHIFTED DUE TO PRESENT OF HOUSE IN BETWEEN CENTER LINE AND CORRIDOR
|  |  | 395.172 | [15 empty] | 395.25 | [5 empty] | SABRAWAN NAHER,ROAD,11kV
236 | 122/1 | DA+3 |  |  |  | 537591.748 | 3512819.899 | 236 | 122/1 | DA+3 | [10 empty] | 254.136 |  | 537584.941 | 3512817.772
|  |  | 358.225 | [15 empty] | 358.296 | [5 empty] | LT LINE,11kV,11kV
237 | 123/0 | DD+0 |  |  | 17°16'00"RT | 537685.706 | 3512474.045 | 237 | AP123/0 | DD+0 | [10 empty] | 253.947 | 18°24'26"RT | 537685.076 | 3512474.045
s
238 | AP 131/0 | DC+0 |  | 2841.987 | 22°30'33"LT | 538168.009 | 3509218.148 | 238 | AP 131/0 | DC+0 | [9 empty] | 2841.988 | 252.715 | 22°30'33"LT | 538168.009 | 3509218.148
|  |  | 407.945 | [15 empty] | 407.946 | [5 empty] | LT LINE,LT LINE
239 | 131/1 | DA+3 |  |  |  | 538287.402 | 3508828.065 | 239 | 131/1 | DA+3 | [10 empty] | 253.285 |  | 538287.402 | 3508828.065
|  |  | 429.847 | [15 empty] | 429.847 | [5 empty] | LT LINE,ROAD
240 | 131/2 | DA+3 |  |  |  | 538413.205 | 3508417.039 | 240 | 131/2 | DA+3 | [10 empty] | 252.581 |  | 538413.205 | 3508417.039
|  |  | 407.778 | [15 empty] | 407.778 | [5 empty] | LT LINE
241 | 131/3 | DA+3 |  |  |  | 538532.549 | 3508027.116 | 241 | 131/3 | DA+3 | [10 empty] | 253.641 |  | 538532.549 | 3508027.116
|  |  | 416.733 | [15 empty] | 416.733 | [5 empty] | CT ROAD,LT LINE
242 | 131/4 | DA+0 |  |  |  | 538654.513 | 3507628.63 | 242 | 131/4 | DA+0 | [10 empty] | 251.638 |  | 538654.513 | 3507628.63
|  |  | 421.345 | [15 empty] | 421.345 | [5 empty] | ROAD
243 | 131/5 | DA+3 |  |  |  | 538777.828 | 3507225.734 | 243 | 131/5 | DA+3 | [10 empty] | 250.849 |  | 538777.828 | 3507225.734
|  |  | 385.64 | [15 empty] | 385.64 | [5 empty] | 11kV,ROAD,11kV
244 | 131/6 | DA+0 |  |  |  | 538890.693 | 3506856.98 | 244 | 131/6 | DA+0 | [10 empty] | 249.36 |  | 538890.693 | 3506856.98
|  |  | 372.699 | [15 empty] | 372.699 | [5 empty] | 66kV
245 | AP 132/0 | DC+6 1.5 mrc |  |  | 28°22'39"RT | 538999.77 | 3506500.6 | 245 | AP 132/0 | DC+6 | Raised Chimney LEG A: 1.5; Raised Chimney LEG B: 1.5; Raised Chimney LEG C: 1.5; Raised Chimney LEG D: 1.5 |  |  | 250.43 | 28°22'39"RT | 538999.77 | 3506500.6
|  |  | 407.912 | 816.077 | [14 empty] | 407.912 | 816.077 |  |  |  |  | LT LINE, PUMP HOUSE,ROAD,LT LINE
246 | 132/1 | DA+3 |  |  |  | 538919.425 | 3506100.679 | 246 | 132/1 | DA+3 | [10 empty] | 250.22 |  | 538919.425 | 3506100.679
|  |  | 408.165 | [15 empty] | 408.165 | [5 empty] | 11kV
247 | AP 133/0 | DC+6 |  | 227.366 | 18°40'20"LT | 538839.029 | 3505700.51 | 247 | AP 133/0 | DD+6 | [10 empty] | 249.72 | 18°40'20"LT | 538839.029 | 3505700.51
|  |  | 227.366 | [15 empty] | 227.366 | 227.366 |  |  |  |  | CT ROAD,NALA,ROAD(SH),11kV
248 | AP 134/0 | DB+3 |  | 401.366 | 2°30'44"RT | 538867.969 | 3505474.993 | 248 | AP 134/0 | DD+3 | [10 empty] | 248.902 | 2°30'44"RT | 538867.969 | 3505474.993
|  |  | 401.366 | [15 empty] | 401.366 | 401.366 |  |  |  |  | LT LINE,11kV
249 | AP 135/0 | DB+3 |  | 1221.902 | 12°42'21"RT | 538901.556 | 3505075.035 | 249 | AP 135/0 | DB+3 | [10 empty] | 249.039 | 12°42'21"RT | 538901.556 | 3505075.035
|  |  | 403.064 | [15 empty] | 403.064 | 1221.902 |  |  |  |  | LT LINE,CT ROAD
250 | 135/1 | DA+6 |  |  |  | 538846.119 | 3504675.802 | 250 | 135/1 | DA+6 | [10 empty] | 248.761 |  | 538846.119 | 3504675.802
|  |  | 398.933 | [15 empty] | 398.933 | [5 empty] | LT LINE,11 Kv,CT ROAD,LT LINE
251 | 135/2 | DA+3 |  |  |  | 538791.249 | 3504280.66 | 251 | 135/2 | DA+3 | [10 empty] | 248.543 |  | 538791.249 | 3504280.66
|  |  | 419.905 | [15 empty] | 419.905 | [5 empty] | LT LINE, 11kV, LT LINE
252 | AP 136/0 | DC+3 |  |  | 18°07'49"LT | 538733.495 | 3503864.746 | 252 | AP 136/0 | DC+3 | [10 empty] | 248.354 | 18°07'48"LT | 538733.495 | 3503864.746
|  |  | 373.389 | 2000.393 | [14 empty] | 373.389 | 2000.393 |  |  |  |  | LT LINE, CT ROAD
253 | 136/1 | DA+3 |  |  |  | 538799.775 | 3503497.287 | 253 | 136/1 | DA+3 | [10 empty] | 248.311 |  | 538799.775 | 3503497.287
|  |  | 419.813 | [15 empty] | 419.813 | [5 empty] | LT LINE
254 | 136/2 | DA+3 |  |  |  | 538874.295 | 3503084.14 | 254 | 136/2 | DA+3 | [10 empty] | 248.224 |  | 538874.295 | 3503084.14
|  |  | 410.049 | [15 empty] | 410.049 | [5 empty] | LT LINE
255 | 136/3 | DA+0 |  |  |  | 538947.081 | 3502680.603 | 255 | 136/3 | DA+0 | [10 empty] | 248.366 |  | 538947.081 | 3502680.603
|  |  | 415.171 | [15 empty] | 415.171 | [5 empty] | ROAD,SMALL CANEL
256 | 136/4 | DA+3 |  |  |  | 539020.777 | 3502272.025 | 256 | 136/4 | DA+3 | [10 empty] | 248.901 |  | 539020.777 | 3502272.025
|  |  | 381.971 | [15 empty] | 381.971
257 | AP 137/0 | DC+3 |  | 1037.588 | 28°54'26"RT | 539088.58 | 3501896.12 | 257 | AP 137/0 | DC+3 | [10 empty] | 248.51 | 28°54'25"RT | 539088.58 | 3501896.12
|  |  | 377.623 | [15 empty] | 377.623 | 1037.587 |  |  |  |  | ROAD
258 | 137/1 | DA+0 |  |  |  | 538967.619 | 3501538.395 | 258 | 137/1 | DA+0 | [10 empty] | 248.489 |  | 538967.619 | 3501538.395
|  |  | 354.138 | [15 empty] | 354.138 | [5 empty] | 11kV
259 | 137/2 | DA+0 |  |  |  | 538854.18 | 3501202.917 | 259 | 137/2 | DA+0 | [10 empty] | 248.278 |  | 538854.18 | 3501202.917
|  |  | 305.827 | [15 empty] | 305.826 | [5 empty] | 11kV,11kV,ROAD,LT LINE,11kV,11kV
260 | AP 138/0 | DD+0 |  | 944.974 | 31°45'48"LT | 538756.216 | 3500913.205 | 260 | AP 138/0 | DD+0 | [9 empty] | 944.974 | 248.041 | 31°45'48"LT | 538756.216 | 3500913.205
|  |  | 320.986 | [15 empty] | 320.987 | [5 empty] | 11kV,11kV
261 | 138/1 | DA+0 |  |  |  | 538828.865 | 3500600.548 | 261 | 138/1 | DA+0 | [10 empty] | 248.307 |  | 538828.865 | 3500600.548
|  |  | 329.946 | [15 empty] | 329.946 | [5 empty] | CT ROAD,11kV,LT LINE,11kV
262 | 138/2 | DA+0 |  |  |  | 538903.541 | 3500279.164 | 262 | 138/2 | DA+0 | [10 empty] | 248.359 |  | 538903.541 | 3500279.164
|  |  | 294.042 | [15 empty] | 294.041 | [5 empty] | 11kV,11kV, CT ROAD,11kV
263 | AP 139/0 | DB+0 |  | 809.122 | 5°55'31"LT | 538970.092 | 3499992.752 | 263 | AP 139/0 | DB+0 | [9 empty] | 809.122 | 246.903 | 5°55'30"LT | 538970.092 | 3499992.752
|  |  | 381.668 | [15 empty] | 381.669 | [5 empty] | 11kV,SOLAR PUMP
264 | 139/1 | DA+3 |  |  |  | 539094.39 | 3499631.891 | 264 | 139/1 | DA+3 | [10 empty] | 239.424 |  | 539094.39 | 3499631.891
|  |  | 427.454 | [15 empty] | 427.453 | [5 empty] | 11kV,CT ROAD,11kV
265 | AP 140/0 | DD+18 |  |  | 29°55'22"LT | 539233.6 | 3499227.741 | 265 | AP 140/0 | DD+18 | [10 empty] | 235.973 | 29°55'22"LT | 539233.6 | 3499227.741
266 | 145/0 | DB+0 |  | 1066.883 | 13°54'60"RT | 539550.52 | 3494836.47 | 266 | 145/0 | DB+0 | [9 empty] | 1066.883 | 232.373 | 13°54'60"RT | 539550.52 | 3494836.47
|  |  | 330.492 | [15 empty] | 330.492 | [5 empty] | ROAD,11kV,LT LINE
267 | 145/1 | DA+0 |  |  |  | 539481.199 | 3494513.33 | 267 | 145/1 | DA+0 | [10 empty] | 232.053 |  | 539481.199 | 3494513.33
|  |  | 342.106 | [15 empty] | 342.106 | [5 empty] | LT LINE,11kV,LT LINE
268 | 145/2 | DA+3 |  |  |  | 539409.442 | 3494178.834 | 268 | 145/2 | DA+3 | [10 empty] | 232.074 |  | 539409.442 | 3494178.834
|  |  | 394.285 | [15 empty] | 394.285 | [5 empty] | CT ROAD,11kV,LT LINE
269 | 146/0 | DC+0 |  |  | 29°42'51"LT | 539326.74 | 3493793.32 | 269 | 146/0 | DC+0 | [10 empty] | 232.347 | 29°42'51"LT | 539326.74 | 3493793.32
|  |  | 245.679 | 245.679 | [14 empty] | 245.679 | 245.679
270 | 147/0 | DB+0 |  |  |  | 539401.052 | 3493559.149 | 270 | 147/0 | DB+0 | [10 empty] | 231.946 |  | 539401.052 | 3493559.149
|  |  | 352.93 | 352.93 | [14 empty] | 352.93 | 352.93 |  |  |  |  | LT LINE,CT ROAD,ROAD
271 | 148/0 | DD+25 |  |  | 51°9'48"RT | 539507.805 | 3493222.751 | 271 | 148/0 | DD+25 | [10 empty] | 232.344 | 51°9'48"RT | 539507.805 | 3493222.751
|  |  | 232.301 | 232.301 | [14 empty] | 232.301 | 232.301 |  |  |  |  | 400kV
272 | 149/0 | DD+25 |  |  | 22°39'7"LT | 539379.397 | 3493029.166 | 272 | 149/0 | DD+25 | [10 empty] | 232.158 | 22°39'7"LT | 539379.397 | 3493029.166
|  |  | 474.983 | 474.983 | [14 empty] | 474.983 | 474.983 |  |  |  |  | LT LINE,11kV,LT LINE
273 | 150/0 | DC+0 |  |  | 24°16'48"LT | 539289.54 | 3492562.76 | 273 | 150/0 | DC+0 | [10 empty] | 232.187 | 24°16'48"LT | 539289.54 | 3492562.76
|  |  | 322.588 | 938.207 | [14 empty] | 322.588 | 938.207 |  |  |  |  | 11kV,CT ROAD,LT LINE
274 | 150/1 | DA+0 |  |  |  | 539364.162 | 3492248.922 | 274 | 150/1 | DA+0 | [10 empty] | 231.729 |  | 539364.162 | 3492248.922
|  |  | 317.884 | [15 empty] | 317.884
275 | 150/2 | DA+0 |  |  |  | 539437.697 | 3491939.66 | 275 | 150/2 | DA+0 | [10 empty] | 232.067 |  | 539437.697 | 3491939.66
|  |  | 297.735 | [15 empty] | 297.735
276 | 151/0 | DC+0 |  |  | 24°58'4"RT | 539506.57 | 3491650 | 276 | 151/0 | DC+0 | [10 empty] | 231.965 | 24°58'4"RT | 539506.57 | 3491650
|  |  | 357.249 | 1117.048 | [14 empty] | 357.249 | 1117.048
277 | 151/1 | DA+0 |  |  |  | 539434.779 | 3491300.039 | 277 | 151/1 | DA+0 | [10 empty] | 231.645 |  | 539434.779 | 3491300.039
|  |  | 353.032 | [15 empty] | 353.032 | [5 empty] | LT LINE(6 NOS),11 Kv(4 nos),ROAD(2nos),
278 | 151/2 | DA+3 |  |  |  | 539363.835 | 3490954.209 | 278 | 151/2 | DA+3 | [10 empty] | 231.556 |  | 539363.835 | 3490954.209
|  |  | 406.767 | [15 empty] | 406.767 | [5 empty] | LT LINE,11kV
279 | 152/0 | DD+0 |  |  | 39°38'38"LT | 539282.092 | 3490555.74 | 279 | 152/0 | DD+0 | [10 empty] | 231.491 | 39°38'36"LT | 539282.092 | 3490555.74
|  |  | 392.394 | 1861.602 | [14 empty] | 392.394 | 1861.602 |  |  |  |  | 11kV,LT LINE(3nos),ROAD
280 | 152/1 | DA+3 |  |  |  | 539466.617 | 3490209.44 | 280 | 152/1 | DA+3 | [10 empty] | 231.324 |  | 539466.617 | 3490209.44
|  |  | 408.835 | [15 empty] | 408.835 | [5 empty] | LT LINE
281 | 152/2 | DA+0 |  |  |  | 538658.874 | 3489848.631 | 281 | 152/2 | DA+0 | [10 empty] | 230.851 |  | 538658.874 | 3489848.631
|  |  | 343.091 | [15 empty] | 333.091 | [5 empty] | CT ROAD,11kV(2nos)
282 | 152/3 | DA+0 |  |  |  | 539820.245 | 3489545.843 | 282 | 152/3 | DA+0 | [10 empty] | 230.407 |  | 539815.512 | 3489554.668 | DUE TO PRESENCE OF ROAD TOWER SHIFTING 10 mtr TO 152/3 | bar: Raised Chimney LEG A to Raised Chimney LEG D
|  |  | 333.683 | [15 empty] | 343.683 | [5 empty] | ROAD,LT LINE(2nos),11kv(2nos)
283 | 152/4 | DA+0 |  |  |  | 539977.131 | 3489251.357 | 283 | 152/4 | DA+0 | [10 empty] | 230.115 |  | 539977.131 | 3489251.357
|  |  | 383.599 | [15 empty] | 383.599
284 | 153/0 | DC+0 |  |  | 23°26'55"RT | 540157.52 | 3488912.82 | 284 | 153/0 | DC+0 | [10 empty] | 230.15 | 23°26'55"RT | 540157.52 | 3488912.82
81
192

## Approved CS K-S Line (hidden)
Line: 400 kV D/C Quad Kishenpur-Samba TL
Approved Check Survey Tower Schedule
AS PER DETAIL SURVEY | [7 empty] | AS PER CHECK SURVEY
Sr. No. | Tower No. | Type of Tower | Span Length (m) | Section Length (m) | Angle of Deviation | UTM Coordinates |  | Sr. No. | Tower No. | Type of Tower | Raised Chimney |  |  |  | Leg Extension |  |  |  | Span Length (m) | Section Length (m) | Reduced Level | Angle of Deviation | UTM Coordinates |  | Crossing/Remarks
[6 empty] | Easting | Northing |  |  |  | LEG A | LEG B | LEG C | LEG D | LEG A | LEG B | LEG C | LEG D |  |  |  |  | Easting | Northing
1 | AP 78/0 | DC+9 |  | 0 | 28°55'39"L | 515334.466 | 3621567.153 | 1 | AP 78/0 | DC+9 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 3 |  | 0 | 524.77 | 29°55'53"L | 515334.47 | 3621567.15
|  |  | 361.044 | [15 empty] | 340.277
2 | AP 79/0 | DD+9 |  | 361.044 | 31°39'03"R | 515034.271 | 3621767.742 | 2 | AP 79/0 | DD+9 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 340.277 | 524.982 | 30°11'47"R | 515048.273 | 3621751.214 | LT LINE TO BE SHIFTED
|  |  | 374.114 | [15 empty] | 392.251 | [5 empty] | NALLA CROSSING
3 | AP 80/0 | DD+3 |  | 735.158 | 36°56'25"L | 514878.544 | 3622107.904 | 3 | AP 80/0 | DD+3 | 0 | -1.5 | 0 | 0 | 0 | 0 | 0 | 1 |  | 732.528 | 532.688 | 30°16'26"L | 514869.848 | 3622100.535
|  |  | 148.51 | [15 empty] | 144.77
4 | AP 81/0 | DD+18 |  | 883.668 | 49°18'55"L | 514747.983 | 3622178.679 | 4 | AP 81/0 | DD+18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | 877.298 | 535.86 | 53°31'26"L | 514747.98 | 3622178.68
|  |  | 195.926 | [15 empty] | 195.926 | [5 empty] | 220 KV S/C CROSSING(KSN-SRN)
5 | AP 82/0 | DD+18 |  | 1079.594 | 5°38'12"R | 514564.892 | 3622108.932 | 5 | AP 82/0 | DD+18 | 0 | 0 | 0 | 0 | 1 | 3 | 4 | 4 |  | 1073.224 | 532.66 | 5°38'20"R | 514564.89 | 3622108.93
|  |  | 194.627 | [15 empty] | 194.623 | [5 empty] | 220 D/C CROSSING(KSN-SRN)
6 | AP 83/0 | DD+25 |  | 1274.221 | 46°40'30"R | 514377.089 | 3622057.846 | 6 | AP 83/0 | DD+25 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1267.847 | 522.13 | 46°40'25"R | 514377.09 | 3622057.85
|  |  | 123.478 | [15 empty] | 123.478
7 | AP 84/0 | DC+9 |  | 1397.699 | 26°50'39"R | 514271.759 | 3622122.285 | 7 | AP 84/0 | DC+9 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 |  | 1391.325 | 525.46 | 26°50'39"R | 514271.76 | 3622122.29 | CONTOUR NOT REQUIRED
|  |  | 358.138 | [15 empty] | 358.134
8 | AP 85/0 | DC+0 |  | 1755.837 | 18°33'39"R | 514083.577 | 3622426.999 | 8 | AP 85/0 | DC+0 | 0 | -1.5 | 0 | 1 | 0 | 0 | 0 | 0 |  | 1749.459 | 513.5 | 18°33'34"R | 514083.58 | 3622427
|  |  | 195.995 | [15 empty] | 195.99 | [5 empty] | LT LINE,2 NOS 11 KV CROSSING
9 | AP 86/0 | DD+0 |  | 1951.832 | 37°33'24"L | 514039.03 | 3622617.864 | 9 | AP 86/0 | DD+0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 |  | 1945.449 | 519.05 |  | 514039.03 | 3622617.86
[19 empty] | 402.938 | [5 empty] | Cannal,Cart Track Crossing
10 | AP 95/0 | DD+0 |  | 0 | 49° 37' 37"RT | 511950.666 | 3623917.519 | 10 | AP 95/0 | DD+0 | 0 | -1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 |  | 0 | 483.848 | 47° 47' 09"RT | 511953.99 | 3623920.015
|  |  | 216.941 | [15 empty] | 215.857 | [5 empty] | LT Line,2 NOS 11KV Line Crossing
11 | AP 96/0 | DC+0 |  | 216.941 | 23° 11' 17"RT | 511872.021 | 3624119.703 | 11 | AP 96/0 | DC-3 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | 215.857 | 480.277 | 24° 15' 00"RT | 511872.021 | 3624119.703
|  |  | 166.009 | [15 empty] | 166.009 | [5 empty] | LT Line Crossing
12 | AP 97/0 | DC+0 |  | 382.95 | 25° 05' 24"LT | 511877.62 | 3624285.618 | 12 | AP 97/0 | DC-3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 381.866 | 485.367 | 25° 09' 02"LT | 511877.62 | 3624285.618 | Contour Not Required
|  |  | 242.696 | [15 empty] | 242.696 | [5 empty] | Nalla and LT Line crossing
13 | AP 98/0 | DD+9 |  | 625.646 | 48° 10' 12"LT | 511782.169 | 3624508.756 | 13 | AP 98/0 | DD+9 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 2 |  | 624.562 | 486.733 | 48° 10' 19"LT | 511782.169 | 3624508.756
|  |  | 202.992 | [15 empty] | 202.992 | [5 empty] | 132 KV S/C Line Crossing
14 | AP 99/0 | DD+18 |  | 828.638 | 58° 23' 34"RT | 511589.857 | 3624573.732 | 14 | AP 99/0 | DD+18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 827.554 | 468.882 | 58° 23' 34"RT | 511589.857 | 3624573.732 | Contour Not Required
|  |  | 155.699 | [15 empty] | 155.699
15 | AP 100/0 | DD+9 |  | 984.337 | 45° 03' 40"RT | 511554.995 | 3624725.478 | 15 | AP 100/0 | DD+9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 983.253 | 468.116 | 45° 03' 40"RT | 511554.995 | 3624725.478
|  |  | 491.503 | [15 empty] | 491.503 | [5 empty] | Nalla and LT Line crossing
16 | AP 101/0 | DD+9 |  | 1475.84 | 34° 37' 48"LT | 511816.341 | 3625141.739 | 16 | AP 101/0 | DD+9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1474.756 | 482.052 | 34° 37' 48"LT | 511816.341 | 3625141.739 | Contour Not Required
|  |  | 136.501 | [15 empty] | 136.501
17 | AP 102/0 | DD+0 |  | 1612.341 | 49° 54' 56"LT | 511810.369 | 3625278.109 | 17 | AP 102/0 | DD+0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 1611.257 | 479.213 | 49° 54' 56"LT | 511810.369 | 3625278.109
|  |  | 122.195 | [15 empty] | 122.195 | [5 empty] | 11 kv Line Crossing
18 | AP 103/0 | DD+6 |  | 1734.536 | 37° 03' 00"RT | 511713.535 | 3625352.639 | 18 | AP 103/0 | DD+6 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 |  | 1733.452 | 476.5 | 37° 03' 00"RT | 511713.535 | 3625352.639
|  |  | 185.672 | [15 empty] | 185.672 | [5 empty] | Electrified Railway crossing,11 KV Crossing
19 | AP 104/0 | DD+9 |  | 1920.208 | 24° 32' 24"LT | 511664.337 | 3625531.674 | 19 | AP 104/0 | DD+9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1919.124 | 475.575 | 24° 32' 24"LT | 511664.337 | 3625531.674 | Contour Not Required
|  |  | 303.562 | [15 empty] | 303.562
20 | AP 105/0 | DD+0 |  | 2223.77 | 55° 28' 40"RT | 511469.585 | 3625764.529 | 20 | AP 105/0 | DD+0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 2222.686 | 475.007 | 55° 28' 40"RT | 511469.585 | 3625764.529
|  |  | 287.716 | [15 empty] | 287.716 | [5 empty] | 2nos 11KV Line Crossing
21 | AP 106/0 | DB+0 |  | 2511.486 | 13° 39' 57"RT | 511546.814 | 3626041.686 | 21 | AP 106/0 | DB+0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2510.402 | 469.175 | 13° 39' 57"RT | 511546.814 | 3626041.686 | Contour Not Required
|  |  | 425.991 | [15 empty] | 425.991
22 | AP 107/0 | DC+0 |  | 2937.477 | 27° 39' 10"RT | 511754.875 | 3626413.41 | 22 | AP 107/0 | DC+0 | -1.5 | -1.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2936.393 | 457.977 | 27° 39' 10"RT | 511754.875 | 3626413.41 | 2nos LTLine crossing
|  |  | 141.744 |  |  |  | AP24-AP39 | [11 empty] | 141.744
23 | AP 108/0 | DC+0 |  | 3079.221 | 16° 58' 12"LT | 511873.602 | 3626490.839 | 23 | AP 108/0 | DC+0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3078.137 | 458.784 | 16° 58' 12"LT | 511873.602 | 3626490.839 | Contour Not Required
|  |  | 52.346 | [15 empty] | 52.346
24 | AP 109/0 | DD+0 |  | 3131.567 |  | 511907.194 | 3626530.984 | 24 | AP 109/0 | DD+0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3130.483 | 458.578 |  | 511907.194 | 3626530.984 | Contour Not Required

## Foundation JS-Line -Jammu
KEC INTERNATIONAL LIMITED | [13 empty] | Date: | 2026-08-11
400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5-Jammu Portion
FOUNDATION
S.No | Loc No. | Tower Type | Classification | Conc Volume | Start Date | Foundation | [5 empty] | Earthing | FDN Status | Gang Name | Gang Strength | Remark
[6 empty] | Excavation | Stub Setting | PCC | Rebar Placing | RCC | Completion Date
1 | 29/5 | DA+0 | WET | 34.389 | 2025-07-28 | 2025-08-07 | 2025-08-10 | 2025-08-10 | 2025-08-10 | 2025-08-11 | 2025-08-11 | 2025-12-03 | Completed | Rakesh | 8
2 | 29/4 | DA+0 | DRY | 21.318 | 2025-08-11 | 2025-08-21 | 2025-08-21 | 2025-08-22 | 2025-08-22 | 2025-09-06 | 2025-09-06 | 2025-12-03 | Completed | Rakesh | 5
3 | 29/3 | DA+0 | DRY | 21.318 | 2025-08-31 | 2025-09-21 | 2025-09-21 | 2025-09-22 | 2025-09-22 | 2025-09-24 | 2025-09-24 |  | Completed | Adishiv | 12 | Completed & 1 leg 1.5 M RC pending
4 | 27/0 | DB+0 | WET | 71.702 | 2025-09-07 | 2025-09-16 | 2025-09-18 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-20 | 2026-01-10 | Completed | Adishiv | 12
5 | 17/0 | DC+3 | FS | 142.45 | 2025-09-10 | 2025-11-21 | 2025-11-22 | 2025-11-22 | 2025-11-22 | 2025-11-23 | 2025-11-23 | 2025-12-07 | Completed | Md.Farooq | 12 | Benching work completed on 21.9.25 Pit B- Casting completed. Work on hold since 12th Oct'25 & restart from 07th Nov'25 & completed on 23rd Nov'25
6 | 18/0 | DC+0 | FS | 134.312 | 2025-09-11 | 2025-10-14 | 2025-10-14 | 2025-10-14 | 2025-10-14 | 2025-10-16 | 2025-10-16 | 2025-10-18 | Completed | Md. Sharif | 20
7 | 29/6 | DA+3 | WET |  | 2025-10-10 | 2025-10-14 | 2025-10-14 | 2025-10-15 | 2025-10-15 | 2025-10-16 | 2025-10-16 | 2025-10-18 | Completed | Adishiv | 12 | Intially work started on 26.9.25 but due to high water table work was hold till 3.10.25 and as advised by RKPTL team loc shifted about 60 mtrs and work resumed from 10.10.25 & completed on 16.10.25
8 | 30/3 | DA+6 | PS |  | 2025-10-30 | 2025-11-22 | 2025-11-23 | 2025-11-23 | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-26 | Completed | Kewal Krishan | 9
9 | 23/1 | DA+6 | WET |  | 2025-09-25 | 2025-11-04 | 2025-11-07 | 2025-11-07 | 2025-11-08 | 2025-11-10 | 2025-11-10 | 2025-12-06 | Completed | Vishal | 8
10 | 29/1 | DA+0 | WET |  | 2025-10-03 | 2025-10-07 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-10 | 2025-10-10 | 2025-10-29 | Completed | Adishiv | 12 | RC Casting done by Anil Sharma on 11.02.2026
11 | 22/1 | DA+3 | WET |  | 2025-10-10 | 2025-10-27 | 2025-10-27 | 2025-10-27 | 2025-10-27 | 2025-10-28 | 2025-10-28 | 2025-11-20 | Completed | ANB Construction | 5
12 | 15/2 | DA+0 | FS |  | 2025-10-18 | 2025-11-09 | 2025-11-18 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-12-07 | Completed | Balwanth Singh | 21
13 | 31/1 | DA+3 | PS |  | 2025-10-17 | 2025-10-27 | 2025-10-28 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-30 | 2025-11-20 | Completed | Md. Sharif | 24
14 | 22/0 | DC+3 | WET |  | 2025-10-18 | 2025-10-30 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-11-19 | Completed | Surjeet | 10
15 | 21/1 | DA+0 | WET |  | 2025-10-28 | 2025-10-30 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-11-09 | Completed | Surjeet | 19
16 | 31/3 | DA+0 | PS |  | 2025-10-30 | 2025-11-07 | 2025-11-09 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-11 | 2025-11-11 | Completed | Md. Sharif | 12
17 | 22/2 | DA+3 | WET |  | 2025-10-29 | 2025-11-10 | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-11-13 | 2025-11-13 | 2025-11-20 | Completed | ANB Construction | 8
18 | 15/1 | DA+0 | PS |  | 2025-11-06 | 2025-11-13 | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-12-02 | Completed | Balwanth Singh | 21
19 | 40/0 | DC+3 | PS |  | 2025-11-09 | 2025-11-30 | 2025-12-02 | 2025-12-02 | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-15 | Completed | Pawan Kumar Shama | 15
20 | 20/0 | DB+6 | WET |  | 2025-11-12 | 2025-11-25 | 2025-11-28 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-11-30 | 2025-12-04 | Completed | Surjeet | 8
21 | 27/1 | DA+3 | WET |  | 2025-11-14 | 2025-11-17 | 2025-11-22 | 2025-11-22 | 2025-11-23 | 2025-11-23 | 2025-11-23 | 2025-12-07 | Completed | Md.Sharif | 40 | RC Casting Pending
22 | AP32 | DB+0 | FS |  | 2025-11-12 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-23 | 2025-11-26 | 2025-11-26 | 2025-12-02 | Completed | Md.Sharif
23 | 23/0 | DB+0 | FS |  | 2025-11-15 | 2025-12-06 | 2025-12-07 | 2025-12-07 | 2025-12-08 | 2205-12-09 | 2025-12-09 | 2025-12-11 | Completed | ANB Construction | 9
24 | 30/5 | DA+9 | PS |  | 2025-11-16 | 2025-11-28 | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-12-05 | Completed | Akram | 15
25 | 40/1 | DA+3 | WET |  | 2025-11-16 | 2025-11-29 | 2025-11-30 | 2025-11-30 | 2025-11-30 | 2025-11-30 | 2025-11-30 | 2025-12-06 | Completed | Thakur Cosnt | 7
26 | 19/2 | DA+0 | FS |  | 2025-11-23 | 2025-12-11 | 2025-12-11 | 2025-12-13 | 2025-12-13 | 2025-12-13 | 2025-12-13 | 2025-12-16 | Completed | Balwanth Singh | 9
27 | 18/1 | DA+0 | PS |  | 2025-11-25 | 2025-12-05 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-07 | Completed | Md.Farooq | 12
28 | AP28 | DC+6 | WET |  | 2025-11-27 | 2025-11-28 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-04 | 2025-12-04 | 2025-12-03 | Completed | Md. Sharif | 35
29 | 30/2 | DA+0 | PS |  | 2025-11-27 | 2025-12-09 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-12 | 2025-12-12 | 2025-12-16 | Completed | Kewal Krishan | 8
30 | 23/4 | DA+3 | FS |  | 2025-11-30 | 2025-12-28 | 2025-12-30 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2026-01-07 | Completed | Anil Sharma | 7 | Pit B, C, D- Casting Completed Pit A- Prop Setting/PCC
31 | 29/0 | DC+9 | WET |  | 2025-12-03 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-10 | 2025-12-12 | Completed | Md. Sharif | 28
32 | 23/5 | DA+3 | FS |  | 2025-12-03 | 2025-12-20 | 2025-12-21 | 2025-12-21 | 2025-12-21 | 2025-12-21 | 2025-12-21 | 2026-03-24 | Completed | Balwanth Singh | 20
33 | 39/2 | DA+0 | FS |  | 2025-12-05 | 2025-12-12 | 2025-12-12 | 2025-12-13 | 2025-12-13 | 2025-12-13 | 2025-12-13 | 2025-12-15 | Completed | Pawan Kumar Shama | 17
34 | 30/4 | DA+0 | FS |  | 2025-12-05 | 2025-12-18 | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-23 | Completed | Akram | 15
35 | AP33 | DC+0 | FS |  | 2025-12-09 | 2025-12-28 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-16 | Completed | Adishiv | 8 | Pit A,D,C - Casting Completed Pit B- Excavation Completed
36 | AP19 | DC+0 | FS |  | 2025-12-10 | 2025-12-22 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-24 | 2025-12-24 | 2025-12-21 | Completed | Md.Farooq | 12
37 | AP43 | DD+3 | WET |  | 2025-12-11 | 2025-12-20 | 2025-12-21 | 2025-12-23 | 2025-12-23 | 2025-12-25 | 2025-12-25 | 2026-01-03 | Completed | Thakur Cosnt | 16
38 | AP45 | DB+0 | WET |  | 2025-12-12 | 2025-12-20 | 2025-12-22 | 2025-12-22 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-25 | Completed | Md. Sharif | 28
39 | 31/2 | DA+0 | FS |  | 2025-12-16 | 2025-12-24 | 2025-12-25 | 2025-12-25 | 2025-12-27 | 2025-12-27 | 2025-12-27 | 2026-01-19 | Completed | Gulam | 12
40 | 46/1 | DA+0 | PS |  | 2025-12-17 | 2025-12-24 | 2025-12-24 | 2025-12-25 | 2025-12-25 | 2025-12-25 | 2025-12-25 | 2026-01-02 | Completed | Pawan Kumar Shama | 17
41 | AP31 | DB+0 | FS |  | 2025-12-19 | 2026-01-11 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-18 | 2026-01-18 | 2026-01-02 | Completed | Akram | 15
42 | AP16 | DC+0 | FS |  | 2026-01-04 | 2026-01-21 | 2026-01-24 | 2026-01-24 | 2026-01-25 | 2026-01-25 | 2026-01-25 |  | Completed | Balwanth Singh | 20 | Pit B,C,D - Casting Completed
43 | 18/2 | DA+6 | FS |  | 2025-12-25 | 2026-01-06 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-08 | 2026-01-08 | 2026-01-22 | Completed | Md.Farooq | 12
44 | AP26 | DD+0 | FS |  | 2025-12-24 | 2026-01-04 | 2026-01-05 | 2026-01-07 | 2026-01-07 | 2026-01-08 | 2026-01-08 | 2026-03-18 | Completed | Balwanth Singh | 20
45 | 43/1 | DA+6 | FS |  | 2025-12-27 | 2026-01-02 | 2026-01-02 | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-04 | 2026-01-22 | Completed | Thakur Cosnt | 16
46 | 31/4 | DA+3 | FS |  | 2025-12-29 | 2026-01-07 | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-09 | 2026-01-09 | 2026-01-10 | Completed | Gulam | 12
47 | 46/3 | DA+0 | FS |  | 2025-12-29 | 2026-01-07 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-10 | Completed | Pawan Kumar Shama | 17
48 | AP30 | DB+0 | FS |  | 2026-01-04 | 2026-01-21 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-31 | 2026-01-31 | 2026-03-30 | Completed | Akram | 18
49 | 43/2 | DA+0 | FS |  | 2026-01-07 | 2026-01-11 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-21 | Completed | Thakur Cosnt | 16
50 | 32/1 | DA+6 | FS |  | 2026-01-08 | 2026-01-29 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-02-02 | Completed | Anil Sharma | 7
51 | 33/1 | DA+0 | FS/FS(SD) |  | 2026-01-09 | 2026-05-06 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-09 | Completed | Adishiv/Thakur Const-1 | 10
52 | 25/2 | DA+0 | FS |  | 2026-01-11 | 2026-01-20 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-02-01 | Completed | Balwanth Singh | 20
53 | 45/2 | DA+0 | PS |  | 2026-01-12 | 2026-01-20 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-02-08 | Completed | Pawan Kumar Shama | 12
54 | 19/1 | DA+0 | FS |  | 2026-01-12 | 2026-01-19 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-22 | Completed | Md.Farooq | 10
55 | 31/5 | DA+3 | FS |  | 2026-01-14 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | Completed | Gulam | 10
56 | 50A/7 | DA+6 | PS |  | 2026-01-31 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-14 | 2026-02-14 | 2026-02-23 |  | Wani Const | 8
57 | 44/3 | DA+0 | FS |  | 2026-01-16 | 2026-01-20 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-02-24 | Completed | Thakur Cosnt | 16
58 | 44/2 | DA+0 | FS |  | 2026-01-29 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-07 | 2026-02-07 | 2026-02-07 | 2026-02-25 | Completed | Thakur Cosnt | 16
59 | AP21 | DD+6 | WET |  | 2026-01-29 | 2026-02-26 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 |  | Completed | Akram | 18
60 | 45/1 | DA+3 | PS |  | 2026-01-29 | 2026-02-04 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-25 | Completed | Pawan Kumar Shama | 12
61 | AP15 | DD+18 | WET |  | 2026-01-31 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-08 | 2026-02-08 | 2026-03-25 | Completed | Balwanth Singh | 20
62 | AP12 | DD+30 | WET /PS |  | 2026-02-03 | 2026-02-17 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-20 | 2026-02-20 |  | Completed | Gulam | 10
63 | 25/1 | DA+0 | FS |  | 2026-02-05 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-13 | 2026-02-13 | 2026-02-26 | Completed | Balwanth Singh | 20
64 | AP35 | DD+0 | FS |  | 2026-02-05 | 2026-05-11 | 2026-05-21 | 2026-05-21 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 2026-06-03 | Completed | Adishiv | 5
65 | AP46 | DB+0 | FS |  | 2026-02-10 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-05-05 | Completed | Pawan Kumar Shama | 12
66 | AP44 | DB+0 | PS |  | 2026-02-11 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-03-17 | Completed | Thakur Cosnt | 16
67 | AP25 | DD+0 | FS |  | 2026-02-15 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-03-18 | Completed | Balwanth Singh | 20
68 | 29/2 | DA+3 | PS (SD) |  | 2026-02-13 | 2026-03-05 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-13 | Completed | Anil Sharma | 8
69 | 50A/8 | DA+0 | PS |  | 2026-02-17 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-03-13 | Completed | Wani Const | 8
70 | 44/1 | DA+0 | PS |  | 2026-02-23 | 2026-02-26 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-03-01 | Completed | Thakur Cosnt | 16
71 | 33/2 | DA+0 | PS |  | 2026-02-23 | 2026-03-08 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 |  | Completed | Gulam | 10
72 | 46/5 | DA+6 | FS |  | 2026-02-23 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-18 | Completed | Pawan Kumar Shama | 12
73 | 50A/3 | DA+3 | PS (SD) |  | 2026-03-01 | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-18 | Completed | Wani Const | 8
74 | AP14 | DB+9 | DFR |  | 2026-03-01 | 2026-03-05 | 2026-03-08 | 2026-03-08 | 2026-03-08 | 2026-03-08 | 2026-03-08 | 2026-03-24 | Completed | Balwanth Singh | 20
75 | AP24 | DC+3 | PS |  | 2026-03-01 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-15 | 2026-03-15 | 2026-03-24 | Completed | Balwanth Singh | 20
76 | 43/3 | DA+3 | PS |  | 2026-03-05 | 2026-03-07 | 2026-03-08 | 2026-03-08 | 2026-03-08 | 2026-03-08 | 2026-03-08 | 2026-03-19 | Completed | Thakur Cosnt | 16
77 | 43/4 | DA+0 | PS(SD) |  | 2026-03-08 | 2026-03-20 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-23 | Completed | Thakur Cosnt | 16
78 | 46/4 | DA+0 | FS |  | 2026-03-08 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-19 | Completed | Pawan Kumar Shama | 12
79 | AP34 | DB+0 | FS |  | 2026-03-30 | 2026-04-22 | 2026-04-24 | 2026-04-25 | 2026-04-25 | 2026-04-25 | 2026-04-25 | 2026-05-01 | Completed | Gulam | 10
80 | 46/2 | DA+0 | PS(SD) |  | 2026-03-13 | 2026-03-27 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-30 | Completed | Pawan Kumar Shama | 12
81 | 15/3 | DA+9 | FS |  | 2026-03-13 | 2026-03-29 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-05-02 | Completed | Anil Sharma | 10
82 | 38/1 | DA+3 | FS |  | 2026-03-22 | 2026-03-29 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-04-08 | Completed | Pawan Kumar Shama-2 | 8
83 | 42/3 | DA+0 | PS |  | 2026-03-25 | 2026-03-30 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-08 | Completed | Thakur Cosnt | 16
84 | 47/1 | DA+0 1M | PS |  | 2026-03-26 | 2026-04-04 | 2026-04-05 | 2026-04-05 | 2026-04-05 | 2026-04-05 | 2026-04-05 | 2026-05-02 | Completed | Sufiyan Ali | 14
85 | AP47 | DB+0 | PS (SD) |  | 2026-04-18 | 2026-04-24 | 2026-04-25 | 2026-04-25 | 2026-04-25 | 2026-04-26 | 2026-04-26 | 2026-05-02 | Completed | Sufiyan Ali | 12
86 | 40/2 | DA+3 | PS |  | 2026-03-31 | 2026-04-12 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-05-05 | Completed | Pawan Sharma-2 | 10
87 | AP7 | DD+30 | WET |  | 2026-04-01 | 2026-04-16 | 2026-04-21 | 2026-04-25 | 2026-04-29 | 2026-04-29 | 2026-04-29 |  | Completed | Anil Sharma | 10
88 | 42/2 | DA+0 | FS |  | 2026-04-11 | 2026-04-15 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-05-01 | Completed | Thakur Cosnt | 14
89 | AP1 | DD+0 | DFR |  | 2026-04-09 | 2026-04-17 | 2026-04-18 | 2026-04-18 | 2026-04-18 | 2026-04-18 | 2026-04-18 | 2026-05-01 | Completed | Pawan Sharma-1 | 12
90 | AP6 | DD+9 | WET |  | 2026-04-11 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 |  | Completed | Balwanth Singh | 10
91 | AP41 | DD+30 | PS |  | 2026-04-18 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-06 | Completed | Pawan Sharma-2 | 10
92 | 37/1 | DA+3 | FS |  | 2026-04-24 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-05-03 | Completed | Pawan Sharma-1 | 12
93 | AP38 | DB+0 | PS |  | 2026-05-03 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-16 | Completed | Pawan Sharma-1 | 12
94 | 40/3 | DB+3 | FS |  | 2026-05-05 | 2026-05-15 | 2026-05-16 | 2026-05-16 | 2026-05-16 | 2026-05-16 | 2026-05-16 | 2026-05-18 | Completed | Pawan Sharma-2 | 10
95 | 23/2 | DA+3 | FS(SD) |  | 2026-05-05 | 2026-05-17 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | Completed | Balwanth Singh | 10
96 | 50A/2 | DA+3 | PS(SD) |  | 2026-05-11 | 2026-05-16 | 2026-05-17 | 2026-05-17 | 2026-05-17 | 2026-05-17 | 2026-05-17 |  | Completed | Samsad | 21
97 | AP42 | DD+30 | PS |  | 2026-05-09 | 2026-05-23 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | Completed | Thakur Cosnt | 14
98 | 50A/4 | DA+0 | FS |  | 2026-05-15 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-06 | 2026-06-06 | 2026-06-09 | Completed | Samsad | 16
99 | 39/1 | DA+3 | PS(SD) |  | 2026-05-16 | 2026-05-24 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | Completed | Pawan Sharma-1 | 12
100 | AP39 | DB+0 | PS |  | 2026-05-17 | 2026-05-24 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | Completed | Pawan Sharma-2 | 10
101 | 50A/1 | DA+3 | FS |  | 2026-05-18 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-23 | 2026-05-23 | 2026-05-23 | 2026-05-24 | Completed | Samsad | 21
102 | 23/3 | DA+3 | FS(SD) |  | 2026-05-19 | 2026-06-06 | 2026-06-07 | 2026-06-07 | 2026-06-07 | 2026-06-09 | 2026-06-09 |  | Completed | Balwanth Singh | 10
103 | 34/1 | DA+6 | PS(SD) |  | 2026-05-19 | 2026-05-27 | 2026-05-28 | 2026-05-28 | 2026-05-28 | 2026-05-28 | 2026-05-28 | 2026-05-30 | Completed | Thakur Cosnt | 8
104 | AP36 | DC+0 | PS(SD) |  | 2026-05-28 | 2026-06-06 | 2026-06-07 | 2026-06-07 | 2026-06-07 | 2026-06-09 | 2026-06-09 | 2026-06-09 | Completed | Pawan Sharma-1 | 12
105 | 35/1 | DA+6 | PS(SD) |  | 2026-05-28 | 2026-06-01 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2026-06-03 | 2026-06-03 | 2026-06-05 | Completed | Pawan Sharma-2 | 10
106 | 42/1 | DA+0 | PS |  | 2026-06-02 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-09 | Completed | Thakur Cosnt | 12
107 | 47/2 | DA+0 | PS(SD) |  | 2026-06-02 | 2026-06-14 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-19 | 2026-06-19 |  | Completed | Deepak T | 8
108 | 47/3 | DA+0 | PS(SD) |  | 2026-06-05 | 2026-06-14 | 2026-06-14 | 2026-06-14 | 2026-06-14 | 2026-06-15 | 2026-06-15 |  | Completed | Thakur Cosnt | 12
109 | 37/2 | DA+3 | FS |  | 2026-06-07 | 2026-06-12 | 2026-06-13 | 2026-06-13 | 2026-06-13 | 2026-06-14 | 2026-06-14 | 2026-06-15 | Completed | Pawan Sharma | 10
110 | AP50A | DC+0 | PS(SD) |  | 2026-06-08 | 2026-06-13 | 2026-06-14 | 2026-06-14 | 2026-06-14 | 2026-06-15 | 2026-06-15 | 2026-06-17 | Completed | Samsad | 16
111 | 50A/10 | DB+6 | FS |  | 2026-06-08 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-30 | 2026-06-30 |  | Completed | Rajput Earth Movers | 12
112 | AP48 | DB+0 | PS(SD) |  | 2026-06-12 | 2026-06-21 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 2026-06-25 | Completed | Thakur Cosnt | 12
113 | AP13 | DD+25 | WET |  | 2026-06-12 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 2026-07-13 | 2026-07-14 | 2026-07-14 |  | Completed | Balwanth Singh | 10
114 | 50A/5 | DA+0 | PS(SD) |  | 2026-06-14 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 | Completed | Samsad | 12
115 | 50A/9 | DA+0 | FS |  | 2026-06-17 | 2026-06-23 | 2026-06-23 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-25 |  | Completed | Samsad | 18
116 | AP10 | DD+9 | PS |  | 2026-06-21 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 |  | Completed | Pawan Sharma | 18
117 | AP51 | DD+30 3MRC | FS |  | 2026-06-22 | 2026-07-06 | 2026-07-07 | 2026-07-07 | 2026-07-09 | 2026-07-13 | 2026-07-13 |  | Completed | Samsad | 18
118 | AP8 | DD+30 4M,5M RC | WET |  | 2026-06-28 | 2026-07-09 | 2026-07-10 | 2026-07-10 | 2026-07-11 | 2026-07-27 | 2026-07-27 |  | Completed | Thakur Cosnt | 16
119 | 50A/6 | DA+3 | FS |  | 2026-07-16 | 2026-07-23 | 2026-07-24 | 2026-07-24 | 2026-07-24 | 2026-07-25 | 2026-07-25 |  | Completed | Samsad | 18
120 | AP11 | DD+25 | WET | [9 empty] | WIP | Thakur Cosnt | 7 | Pit Marking
121 | AP9 | DD+9 | PS |  | 2026-06-14: 2026-08-07 | WIP | Balwanth Singh | 8 | Pit - C - PCC Done

## Erection -Jammu
KEC INTERNATIONAL LIMITED | [7 empty] | Date: | 2026-08-11
400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5-Jammu Portion
TOWER ERECTION
S.No | Loc No. | Tower Type | Weight MT | Conc Volume | Starting Date | Completion Date | Status | Gang Name | Gang Strength | Final Checking Status | Remark
1 | 29/5 | DA+0 | 18.339 | 34.389 | 2025-11-27 | 2025-12-03 | Completed | Raj Labour Suppliers | 23 | Completed
2 | 29/4 | DA+0 | 18.339 | 21.318 | 2025-12-05 | 2025-12-10 | Completed | Raj Labour Suppliers | 23 | Completed
3 | 27/0 | DB+0 | 27.92 | 21.318 | 2025-12-11 | 2025-11-21 | Completed | Raj Labour Suppliers | 23 | Completed
4 | 29/6 | DA+3 | 19.44 |  | 2025-12-22 | 2025-12-29 | Completed | Raj Labour Suppliers | 20 | Completed
5 | 15/1 | DA+0 | 18.339 |  | 2025-12-25 | 2026-01-05 | Completed | Anbi Construction | 15
6 | 30/3 | DA+6 | 22.68 |  | 2025-12-29 | 2026-01-08 | Completed | Raj Labour Suppliers | 20
7 | 15/2 | DA+0 | 18.339 |  | 2026-01-07 | 2026-01-16 | Completed | Anbi Construction | 15
8 | 30/5 | DA+9 | 24.149 |  | 2026-01-09 | 2026-01-18 | Completed | Raj Labour Suppliers | 20
9 | AP18 | DC+0 | 32.22 |  | 2026-01-18 | 2026-01-31 | Completed | Anbi Construction | 21 | Completed
10 | 30/4 | DA+0 | 18.339 |  | 2026-01-18 | 2026-01-22 | Completed | Raj Labour Suppliers | 22
11 | 31/1 | DA+3 | 19.44 |  | 2026-01-25 | 2026-02-01 | Completed | Raj Labour Suppliers | 22 | Completed
12 | 31/2 | DA+0 | 18.339 |  | 2026-02-01 | 2026-02-06 | Completed | Raj Labour Suppliers | 22 | Completed
13 | 19/2 | DA+0 | 18.339 |  | 2026-02-01 | 2026-02-07 | Completed | Anbi Construction | 21
14 | 23/1 | DA+0 | 18.339 |  | 2026-02-05 | 2026-02-10 | Completed | Kushboo Devi | 21 |  | Due to row gang idle for 2 days 07-02-2026 to 08-02-2026
15 | 31/3 | DA+0 | 18.339 |  | 2026-02-06 | 2026-02-08 | Completed | Raj Labour Suppliers | 22 | Completed
16 | 19/1 | DA+0 | 18.339 |  | 2026-02-08 | 2026-02-13 | Completed | Anvi Construction | 21
17 | 31/4 | DA+3 | 19.44 |  | 2026-02-09 | 2026-02-13 | Completed | Raj Labour Suppliers | 22 | Completed
18 | AP23 | DB+0 | 27.92 |  | 2026-02-11 | 2026-02-15 | Completed | Kushboo Devi | 21
19 | AP32 | DB+0 | 27.921 |  | 2026-02-13 | 2026-02-20 | Completed | Raj Labour Suppliers | 22 | Completed
20 | AP19 | DC+0 | 32.222 |  | 2026-02-13 | 2026-02-24 | Completed | Anvi Construction | 21 | Completed
21 | 23/5 | DA+3 | 19.44 |  | 2026-02-15 | 2026-02-19 | Completed | Kushboo Devi | 21
22 | 40/1 | DA+3 | 19.44 |  | 2026-02-16 | 2026-02-23 | Completed | ASC Infra Pvt Ltd | 26
23 | 45/2 | DA+0 | 18.339 |  | 2026-02-17 | 2026-02-25 | Completed | Raju Kumar | 23
24 | 32/1 | DA+6 | 22.68 |  | 2026-02-20 | 2026-02-25 | Completed | Raj Labour Suppliers | 22
25 | 23/4 | DA+3 | 19.44 |  | 2026-02-20 | 2026-02-22 | Completed | Kushboo Devi | 21
26 | AP26 | DD+0 | 42.226 |  | 2026-02-22 | 2026-03-03 | Completed | Kushboo Devi | 21 | Completed
27 | 39/2 | DA+0 | 18.339 |  | 2026-02-24 | 2026-02-28 | Completed | ASC Infra Pvt Ltd | 26
28 | 18/2 | DA+6 | 22.68 |  | 2026-02-24 | 2026-03-04 | Completed | Anvi Construction | 21 | Completed
29 | 31/5 | DA+3 | 19.44 |  | 2026-03-07 | 2026-03-10 | Completed | Niva Sarkar Mandal | 20 | Completed
30 | AP40 | DC+3 | 33.53 |  | 2026-02-28 | 2026-03-08 | Completed | ASC Infra Pvt Ltd | 26
31 | 18/1 | DA+0 | 18.339 |  | 2026-03-05 | 2026-03-12 | Completed | Anvi Construction | 21 | Completed
32 | 25/2 | DA+0 | 18.339 |  | 2026-03-05 | 2026-03-12 | Completed | Kushboo Devi | 20 | Completed
33 | 44/3 | DA+0 | 18.339 |  | 2026-03-08 | 2026-03-12 | Completed | ASC Infra Pvt Ltd | 26
34 | 29/1 | DA+0 | 18.339 |  | 2026-03-09 | 2026-03-23 | Completed | Century Engineering | 18
35 | 44/2 | DA+0 | 18.339 |  | 2026-03-12 | 2026-03-16 | Completed | ASC Infra Pvt Ltd | 26
36 | 25/1 | DA+0 | 18.339 |  | 2026-03-12 | 2026-03-17 | Completed | Kushboo Devi | 20 | Completed
37 | AP33 | DC+0 | 32.22 |  | 2026-03-12 | 2026-03-24 | Completed | Niva Sarkar Mandal | 20
38 | AP25 | DD+0 | 42.23 |  | 2026-03-16 | 2026-03-25 | Completed | Kushboo Devi | 20 | Completed
39 | 45/1 | DA+3 | 19.44 |  | 2026-03-16 | 2026-03-21 | Completed | ASC Infra Pvt Ltd | 20
40 | 44/1 | DA+0 | 18.34 |  | 2026-03-16 | 2026-03-24 | Completed | ASC Infra Pvt Ltd | 20
41 | 46/1 | DA+0 | 18.34 |  | 2026-03-23 | 2026-03-30 | Completed | Century Engineering | 18
42 | AP44 | DB+0 | 27.92 |  | 2026-03-24 | 2026-03-30 | Completed | ASC Infra Pvt Ltd | 20
43 | 33/2 | DA+0 | 18.34 |  | 2026-03-24 | 2026-03-29 | Completed | Niva Sarkar Mandal | 20
44 | AP24 | DC+3 | 33.53 |  | 2026-03-25 | 2026-04-06 | Completed | Kushboo Devi | 20 | Completed
45 | AP31 | DB+0 | 27.921 |  | 2026-03-29 | 2026-04-04 | Completed | Niva Sarkar Mandal | 25 | Completed
46 | 46/4 | DA+0 | 18.339 |  | 2026-03-30 | 2026-04-05 | Completed | Century Engineering | 21
47 | 43/3 | DA+3 | 19.442 |  | 2026-03-30 | 2026-04-02 | Completed | ASC Infra Pvt Ltd | 24
48 | 43/2 | DA+0 | 18.34 |  | 2026-04-02 | 2026-04-06 | Completed | ASC Infra Pvt Ltd | 24
49 | AP17 | DC+3 | 33.53 |  | 2026-04-04 | 2026-04-10 | Completed | Kushboo Devi-2 | 15
50 | AP30 | DB+0 | 27.92 |  | 2026-04-04 | 2026-04-12 | Completed | Niva Sarkar Mandal | 25 | Completed
51 | 46/5 | DA+6 | 22.68 |  | 2026-04-05 | 2026-04-10 | Completed | Century Engineering | 21
52 | 43/1 | DA+6 | 22.68 |  | 2026-04-06 | 2026-04-10 | Completed | ASC Infra Pvt Ltd | 24
53 | AP20 | DB+6 | 34.578 |  | 2026-04-06 | 2026-04-15 | Completed | Kushboo Devi | 20
54 | 43/4 | DA+0 | 18.34 |  | 2026-04-10 | 2026-04-14 | Completed | ASC Infra Pvt Ltd | 24
55 | 15/3 | DA+9 | 24.149 |  | 2026-04-12 | 2026-04-19 | Completed | Kushboo Devi-2 | 15
56 | 46/2 | DA+0 | 18.34 |  | 2026-04-14 | 2026-04-18 | Completed | ASC Infra Pvt Ltd | 24
57 | AP16 | DC+0 | 32.22 |  | 2026-04-15 | 2026-04-20 | Completed | Kushboo Devi | 20
58 | 46/3 | DA+0 | 18.34 |  | 2026-04-18 | 2026-04-21 | Completed | ASC Infra Pvt Ltd | 24
59 | 29/2 | DA+3 | 19.44 |  | 2026-04-19 | 2026-04-23 | Completed | Kushboo Devi-2 | 15
60 | 50A/7 | DA+6 | 22.68 |  | 2026-04-20 | 2026-04-26 | Completed | Kushboo Devi | 20
61 | AP43 | DD+3 | 44.071 |  | 2026-04-21 | 2026-04-30 | Completed | ASC Infra Pvt Ltd | 24
62 | 47/1 | DA+0 | 18.34 |  | 2026-04-24 | 2026-04-28 | Completed | Kushboo Devi-2 | 22
63 | 50A/8 | DA+0 | 18.34 |  | 2026-04-26 | 2026-04-29 | Completed | Kushboo Devi | 20
64 | 50A/3 | DA+3 | 19.44 |  | 2026-04-28 | 2026-04-30 | Completed | Kushboo Devi-2 | 22
65 | 40/2 | DA+3 | 19.44 |  | 2026-04-29 | 2026-05-02 | Completed | Kushboo Devi | 20
66 | 38/1 | DA+3 | 19.44 |  | 2026-04-30 | 2026-05-05 | Completed | Kushboo Devi-2 | 22
67 | 42/3 | DA+0 | 18.34 |  | 2026-04-30 | 2026-05-03 | Completed | ASC Infra Pvt Ltd | 24
68 | AP47 | DB+0 | 27.92 |  | 2026-05-03 | 2026-05-08 | Completed | Kushboo Devi | 20
69 | 42/2 | DA+0 | 18.34 |  | 2026-05-03 | 2026-05-07 | Completed | ASC Infra Pvt Ltd | 24
70 | 29/3 | DA+0 | 18.34 |  | 2026-05-05 | 2026-05-09 | Completed | Kushboo Devi-2 | 22
71 | 37/1 | DA+3 | 19.44 |  | 2026-05-07 | 2026-05-10 | Completed | ASC Infra Pvt Ltd | 24
72 | AP34 | DB+0 | 27.92 |  | 2026-05-08 | 2026-05-14 | Completed | Kushboo Devi | 20
73 | AP46 | DB+0 | 27.92 |  | 2026-05-10 | 2026-05-15 | Completed | ASC Infra Pvt Ltd | 24
74 | AP29 | DC+9 | 41.843 |  | 2026-05-10 | 2026-05-16 | Completed | Kushboo Devi-2 | 22
75 | 30/2 | DA+0 | 18.34 |  | 2026-05-15 | 2026-05-17 | Completed | Kushboo Devi | 20
76 | AP45 | DB+0 | 27.92 |  | 2026-05-15 | 2026-05-20 | Completed | ASC Infra Pvt Ltd | 24
77 | 27/1 | DA+3 | 19.44 |  | 2026-05-16 | 2026-05-19 | Completed | Kushboo Devi-2 | 22
78 | 33/1 | DA+0 | 18.34 |  | 2026-05-17 | 2026-05-22 | Completed | Kushboo Devi | 20
79 | AP28 | DC+6 | 39.484 |  | 2026-05-19 | 2026-05-26 | Completed | Kushboo Devi-2 | 22
80 | AP38 | DB+0 | 27.921 |  | 2026-05-21 | 2026-05-26 | Completed | ASC Infra Pvt Ltd | 24
81 | AP21 | DD+6 | 52.663 |  | 2026-05-28 | 2026-06-10 | Completed | Kushboo Devi | 22
82 | 40/3 | DB+3 | 29.492 |  | 2026-05-26 | 2026-06-02 | Completed | ASC Infra Pvt Ltd | 24
83 | 23/2 | DA+3 | 19.442 |  | 2026-05-26 | 2026-05-29 | Completed | Kushboo Devi-2 | 22
84 | 22/1 | DA+3 | 19.442 |  | 2026-05-30 | 2026-05-31 | Completed | Kushboo Devi-2 | 22
85 | AP39 | DB+0 | 27.921 |  | 2026-06-02 | 2026-06-08 | Completed | ASC Infra Pvt Ltd | 24
86 | 22/2 | DA+3 | 19.442 |  | 2026-06-01 | 2026-06-03 | Completed | Kushboo Devi-2 | 22
87 | 39/1 | DA+3 | 19.442 |  | 2026-06-08 | 2026-06-13 | Completed | ASC Infra Pvt Ltd | 24
88 | AP22 | DC+3 | 33.53 |  | 2026-06-10 | 2026-06-16 | Completed | Kushboo Devi | 22
89 | 35/1 | DA+6 | 22.679 |  | 2026-06-14 | 2026-06-24 | Completed | ASC Infra Pvt Ltd | 20
90 | 23/3 | DA+3 | 19.442 |  | 2026-06-16 | 2026-06-22 | Completed | Kushboo Devi | 22
91 | 34/1 | DA+6 | 22.679 |  | 2026-06-19 | 2026-06-24 | Completed | Vijay B-2 | 20
92 | 21/1 | DA+0 | 18.339 |  | 2026-06-22 | 2026-06-27 | Completed | Kushboo Devi | 22
93 | AP35 | DD+0 | 42.226 |  | 2026-06-24 | 2026-07-05 | Completed | Vijay B-2 | 20
94 | AP15 | DD+18 | 71.3103 |  | 2026-06-26 | 2026-07-12 | Completed | Jwala Singh | 25
95 | AP7 | DD+30 | 94.5555 |  | 2026-07-02 | 2026-07-18 | Completed | Kajal Const | 35
96 | 50A/10 | DB+6 | 34.5788 |  | 2026-07-07 | 2026-07-16 | Completed | Vijay B-2 | 20
97 | AP10 | DD+9 | 56.1568 |  | 2026-07-06 | 2026-07-12 | Completed | Anannya Traders | 35
98 | AP50A | DC+0 | 32.2394 |  | 2026-07-12 | 2026-07-20 | Completed | Vijay B-1 | 25
99 | AP12 | DD+30 | 94.5555 |  | 2026-07-14 | 2026-07-26 | Completed | Anannya Traders | 35
100 | 50A/9 | DA+0 | 18.3435 |  | 2026-07-16 | 2026-07-19 | Completed | Vijay B-2 | 24
101 | AP14 | DB+9 | 36.3551 |  | 2026-07-18 | 2026-07-27 | Completed | Jwala Singh | 25
102 | 47/2 | DA+0 | 18.34 |  | 2026-07-20 | 2026-07-30 | Completed | Vijay B-2 | 24
103 | AP13 | DD+25 | 79.4744 |  | 2026-07-19 | 2026-07-31 | Completed | Kajal Const | 35
104 | AP51 | DD+30 | 94.5555 |  | 2026-07-20 |  | 5th Section | Vijay B-1 | 25
105 | 50A/6 | DA+3 | 19.442 |  | 2026-07-30 | 2026-08-06 | Completed | Vijay B-2 | 24
106 | 50A/5 | DA+0 | 18.3435 |  | 2026-08-06 |  | 2nd Section | Vijay B-2 | 24

## Vertical Chart -JS Line Jammu (hidden)
KEC INTERNATIONAL LIMITED
400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5-Jammu Portion
Vertical Chart
[9 empty] | Complete |  | 95 | 83 | 73 | 59 | 0
[9 empty] | WIP |  |  | 9 | 0 | 3 | 0
S.No | Tower | TOT | Angle of Deviation | Raised Chimney |  |  |  | FDN Classification | Span Length (Mtr) | Section Length (m) | ROW | Foundation | Earthing | Tower Erection | Tack Welding | Stringing | Remarks
|  |  |  | LEG A | LEG B | LEG C | LEG D
1 | AP5 | DD+0 | 47°01'59"LT | 0 | 0 | 0 | 0 |  |  | 0
119.059
2 | AP6 | DD+9 | 40°54'42"RT | 0 | 0 | 0 | 0 |  |  | 119.059 | Clear | WIP
92.496
3 | AP7 | DD+30 | 47°08'48"LT | 4 | 5 | 4 | 3 | WET |  | 92.496 | Clear | WIP
[9 empty] | 134.988 | [7 empty] | 400 KV D/C Line Jalandhar to Samba
4 | AP8 | DD+30 | 41°15'08"RT | 4 | 5 | 4 | 3 |  |  | 134.988
365.176
5 | AP9 | DD+9 | 37°05'47"RT | 0 | 0 | 0 | 0 |  |  | 365.176
[9 empty] | 236.697 | [7 empty] | Railway Crossing Electrified (Jammu/Delhi)
6 | AP10 | DD+9 | 20°40'31"LT | 0 | 0 | 0 | 0 |  |  | 236.697
213.252
7 | AP11 | DD+25 | 51°34'02"RT | 0 | 0 | 0 | 0 |  |  | 213.252
[9 empty] | 206.593 | [7 empty] | 400 KV D/C Line Jalandhar to Samba
8 | AP12 | DD+30 | 47°50'13"LT | 0 | 0 | 0 | 0 | WET/PS |  | 206.593 | Clear | C
[9 empty] | 289.862 | [7 empty] | 220 KV D/C Line Samba To Hiranagar
9 | AP13 | DD+25 | 39°08'44"LT | 1.5 | 1.5 | 0 | 0 |  |  | 289.862
402.938
10 | AP14 | DB+9 | 14°33'47"RT | 0 | 0 | 2 | 0 | DFR |  | 402.938 | Clear | C | C
[9 empty] | 284.883 | [7 empty] | 220 KV D/C Line Bishnah-Hiranagar
11 | AP15 | DD+18 | 4°57'01"LT | 1.5 | 0 | 0 | 0 | WET |  | 284.883 | Clear | C | C
412.199
12 | 15/1 | DA+0 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C | C | C
428.128
13 | 15/2 | DA+0 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C | C
405.152
14 | 15/3 | DA+9 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C |  | C
427.96
15 | AP16 | DC+0 | 22°18'18"LT | 0 | 0 | 0 | 0 | FS |  | 1673.439 | Clear | C |  | C
285.948
16 | AP17 | DC+3 | 19°02'28"LT | 0 | 0 | 0 | 0 | FS |  | 285.948 | Clear | C | C | C
[9 empty] | 401.159 | [7 empty] | 66 KV H Pole (Sandhi) Ghagwal To Rajpura
17 | AP18 | DC+0 | 24°05'21"RT | 0 | 0 | 0 | 0 | FS |  | 401.159 | Clear | C | C | C
345
18 | 18/1 | DA+0 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C | C | C
360.001
19 | 18/2 | DA+6 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C | C
350.217
20 | AP19 | DC+0 | 24°17'20"LT | 0 | 0 | 0 | 0 | FS |  | 1055.218 | Clear | C | C | C
369.999
21 | 19/1 | DA+0 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C | C | C
360
22 | 19/2 | DA+0 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C | C
358.748
23 | AP20 | DB+6 | 5°25'51"RT | 1.5 | 1.5 | 1.5 | 1.5 | WET |  | 1088.747 | Clear | C | C | C
485.93
24 | AP21 | DD+6 | 39°17'49" RT | 1.5 | 1.5 | 1.5 | 1.5 | WET |  | 485.93 | Clear | C
325
25 | 21/1 | DA+0 |  | 0 | 0 | 0 | 0 | WET |  |  | Clear | C | C
387.337
26 | AP22 | DC+3 | 15°58'43"LT | 0 | 0 | 0 | 0 | WET |  | 712.337 | Clear | C | C
390
27 | 22/1 | DA+3 |  | 0 | 0 | 0 | 0 | WET |  |  | Clear | C | C
388.629
28 | 22/2 | DA+3 |  | 0 | 0 | 0 | 0 | WET |  |  | Clear | C | C
398.45
29 | AP23 | DB+0 | 9°30'47"LT | 0 | 0 | 0 | 0 | FS |  | 1177.079 | Clear | C | C | C
435.999
30 | 23/1 | DA+6 |  | 0 | 0 | 0 | 0 | WET |  |  | Clear | C | C | C
384
31 | 23/2 | DA+3 |  | 0 | 0 | 0 | 0 |  |  |  | Clear | WIP
420
32 | 23/3 | DA+3 |  | 0 | 0 | 0 | 0 |  |  |  | Clear
410
33 | 23/4 | DA+3 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C | C
407.25
34 | 23/5 | DA+3 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C | C
397.702
35 | AP24 | DC+3 | 26°6'39"RT | 0 | 0 | 0 | 0 | PS |  | 2454.951 | Clear | C | C | C
366.004
36 | AP25 | DD+0 | 36°50'56"LT | 0 | 0 | 0 | 0 | FS |  | 366.004 | Clear | C | C | C
372.4
37 | 25/1 | DA+0 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C | C | C
311.866
38 | 25/2 | DA+0 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C | C
343.763
39 | AP26 | DD+0 | 51°30'37"RT | 0 | 0 | 0 | 0 | FS |  | 1028.029 | Clear | C | C | C
442.371
40 | AP27 | DB+0 | 10°41'20"RT | 0 | 0 | 0 | 0 | WET |  | 442.371 | Clear | C | C | C
360
41 | 27/1 | DA+3 |  | 1.5 |  | 1.5 | 2.5 | WET |  |  | Clear | C | C
379.739
42 | AP28 | DC+6 | 27°47'33"LT | 1.5 | 2.5 | 1.5 | 1.5 | WET |  | 739.739 | Clear | C | C
445.991
43 | AP29 | DC+9 | 22°59'55"LT | 1.5 | 3 | 3 | 1.5 | WET |  | 445.991 | Clear | C | C
373
44 | 29/1 | DA+0 |  | 1.5 | 1.5 | 0 | 0 | WET |  |  | Clear | C | C | C
374
45 | 29/2 | DA+3 |  | 1 | 1 | 1 | 1 | PS(SD) |  |  | Clear | C | C | WIP
352
46 | 29/3 | DA+0 |  | 1.5 | 0 | 0 | 0 | DRY |  |  | Clear | C
406
47 | 29/4 | DA+0 |  | 0 | 0 | 0 | 0 | DRY |  |  | Clear | C | C | C
352
48 | 29/5 | DA+0 |  | 0 | 0 | 0 | 0 | WET |  |  | Clear | C | C | C
340
49 | 29/6 | DA+3 |  | 0 | 0 | 0 | 0 | WET |  |  | Clear | C | C | C
376.629
50 | AP30 | DB+0 | 05° 34' 43"LT | 0 | 0 | 0 | 0 | FS |  | 2573.629 | Clear | C | C | C
423
51 | 30/1 | DA+6 |  | 0 | 0 | 0 | 0 | FS (SD) |  |  | Clear | WIP
417
52 | 30/2 | DA+0 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C | C
415
53 | 30/3 | DA+6 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C | C | C
421
54 | 30/4 | DA+0 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C | C
404
55 | 30/5 | DA+9 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C | C | C
434.73
56 | AP31 | DB+0 | 12° 48' 28"LT | 0 | 0 | 0 | 0 | FS |  | 2514.73 | Clear | C | C | C
395
57 | 31/1 | DA+3 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C | C | C
385
58 | 31/2 | DA+0 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C | C
395
59 | 31/3 | DA+0 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C | C | C
390
60 | 31/4 | DA+3 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C | C
420
61 | 31/5 | DA+3 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C | C
389.48
62 | AP32 | DB+0 | 09° 51' 20"RT | 0 | 0 | 0 | 0 | FS |  | 2374.48 | Clear | C | C | C
410
63 | 32/1 | DA+6 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C | C
426.984
64 | AP33 | DC+0 | 25° 29' 10"RT | 0 | 0 | 0 | 0 | FS |  | 836.984 | Clear | C | C | C
290
65 | 33/1 | DA+0 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | [5 empty] | Gang went on eid festival
360
66 | 33/2 | DA+0 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C |  | C
317.8
67 | AP34 | DB+0 | 05° 33' 15"RT | 0 | 0 | 0 | 0 | FS |  | 967.8 | Clear | WIP
427.154
68 | 34/1 | DA+6 |  | 0 | 0 | 0 | 0
392.753
69 | AP35 | DD+0 | 35° 45' 17"LT | 2 | 2 | 2 | 2 | FS |  | 819.907 | Clear | WIP
415
70 | 35/1 | DA+6 |  | 0 | 0 | 0 | 0
405.234
71 | AP36 | DC+0 | 18° 50' 40"RT | 0 | 0 | 0 | 0 |  |  | 820.234
439.8
72 | AP37 | DB+9 | 04° 23' 18"LT | 0 | 0 | 0 | 0 |  |  | 439.8
376
73 | 37/1 | DA+3 |  | 0 | 0 | 0 | 0
416
74 | 37/2 | DA+3 |  | 0 | 0 | 0 | 0
411.4
75 | AP38 | DB+0 | 12° 51' 19"RT | 0 | 0 | 0 | 0 |  |  | 1203.4
390
76 | 38/1 | DA+3 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C
385.272
77 | AP39 | DB+0 | 10° 49' 41"LT | 0 | 0 | 0 | 0 |  |  | 775.272
399.206
78 | 39/1 | DA+3 |  | 0 | 0 | 0 | 0 | WET
407.487
79 | 39/2 | DA+0 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C | C
403.2
80 | AP40 | DC+3 | 14° 41' 57"LT | 0 | 0 | 0 | 0 | PS |  | 1209.893 | Clear | C | C | C
429.653
81 | 40/1 | DA+3 |  | 0 | 0 | 0 | 0 | WET |  |  | Clear | C | C | C
400.3
82 | 40/2 | DA+3 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C
414.63
83 | 40/3 | DB+3 |  | 0 | 0 | 0 | 0 |  |  |  | Clear | WIP
515.89
84 | AP41 | DD+30 | 36° 33' 25"LT | [6 empty] | 1760.473
212.443
85 | AP42 | DD+30 | 29° 48' 40"RT |  |  |  |  | PS |  | 212.443 | Clear | WIP
459.999
86 | 42/1 | DA+0 |  | 0 | 0 | 0 | 0
260
87 | 42/2 | DA+0 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C
330
88 | 42/3 | DA+0 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C | C
311.04
89 | AP43 | DD+3 | 38° 14' 17"RT | 0 | 0 | 0 | 0 | WET |  | 1361.039 | Clear | C | C | WIP
408.948
90 | 43/1 | DA+6 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C | C
371.345
91 | 43/2 | DA+0 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C | C
364.114
92 | 43/3 | DA+3 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C | C | C
419.36
93 | 43/4 | DA+0 |  | 0 | 0 | 0 | 0 | PS(SD) |  |  | Clear | C | C | C
348.129
94 | AP44 | DB+0 | 05° 00' 32"LT | 0 | 0 | 0 | 0 | PS |  | 1911.896 | Clear | C | C | C
367.848
95 | 44/1 | DA+0 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C | C | C
396.726
96 | 44/2 | DA+0 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C | C
375.111
97 | 44/3 | DA+0 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C | C
335.003
98 | AP45 | DB+0 | 12° 18' 41"RT | 0 | 0 | 0 | 0 | WET |  | 1474.688 | Clear | C | C
360
99 | 45/1 | DA+3 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C | C | C
360
100 | 45/2 | DA+0 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C | C | C
359.496
101 | AP46 | DB+0 | 09° 05' 55"RT | 0 | 0 | 0 | 0 | FS |  | 1079.496 | Clear | C
350.739
102 | 46/1 | DA+0 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C | C | C
337.891
103 | 46/2 | DA+0 |  | 0 | 0 | 0 | 0 | PS(SD) |  |  | Clear | C | C | C
331.001
104 | 46/3 | DA+0 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C | C
360.369
105 | 46/4 | DA+0 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C | C
425
106 | 46/5 | DA+6 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C | C
411.448
107 | AP47 | DB+0 | 14° 19' 33"RT | 0 | 0 | 0 | 0 |  |  | 2216.448 | Clear | WIP
298
108 | 47/1 | DA+0 |  | 1 | 1 | 1 | 1 | PS |  |  | Clear | C
349
109 | 47/2 | DA+0 |  | 0 | 0 | 0 | 0 |  |  |  | Clear
350
110 | 47/3 | DA+0 |  | 0 | 0 | 0 | 0
363.364
111 | AP48 | DB+0 | 11° 23' 48"RT | 0 | 0 | 0 | 0 |  |  | 1360.364
371.504
112 | AP49 | DD+25 | 49° 40' 12"RT | 2 | 2 | 2 | 2 |  |  | 371.504
[9 empty] | 203.304 | [7 empty] | 400 KV D/C Line Jalandhar to Samba
113 | AP50 | DD+25 | 47° 29' 26"LT | 2 | 2 | 2 | 2 |  |  | 203.304
409.908
114 | AP50A | DC+0 | 26° 30' 32"LT | 0 | 0 | 0 | 0 |  |  | 409.908
412
115 | 50A/1 | DA+3 |  | 0 | 0 | 0 | 0
428
116 | 50A/2 | DA+3 |  | 0 | 0 | 0 | 0
409
117 | 50A/3 | DA+3 |  | 0 | 0 | 0 | 0 | PS(SD) |  |  | Clear | C | C
416
118 | 50A/4 | DA+0 |  | 0 | 0 | 0 | 0
397
119 | 50A/5 | DA+0 |  | 0 | 0 | 0 | 0
337
120 | 50A/6 | DA+3 |  | 0 | 0 | 0 | 0
451
121 | 50A/7 | DA+6 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C | C
389
122 | 50A/8 | DA+0 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C | C | WIP
395
123 | 50A/9 | DA+0 |  | 0 | 0 | 0 | 0
391
124 | 50A/10 | DA+0 |  | 0 | 0 | 0 | 0
425.903
125 | AP51 | DC+9 |  | 0 | 0 | 0 | 0 |  |  | 4450.903
46.0515

## Sheet17 (hidden)
S.No | Line | Portion | Line Qty | Foundation Completed | Tower Erection Completed | Tower Erection WIP | Gap between Foundation & Erection | Tower Erection Gangs Available at Site | Remarks
1 | Samba-Jalandhar | Jammu | 137 | 81 | 51 | 4 | 26 | 5 | 10 locations ROW clear - Work front for 5 gangs i.e; 2 loc per gang 2 Locations -supply of DD18/25/30 Extensions required 5 locations -Crop harvesting required 4 locations under ROW
2 | Samba-Jalandhar | Punjab | 262 | 154 | 66 | 6 | 82 | 7 | 4 locations - ROW Clear 9 Locations - Supply of DD 18/25/30 extensions required 1 locations - Transposition tower supply required Due to standing crop (wheat) at maximum locations farmers are not allowing for tower erection work . Expected for crop harvesting in next 1 week time
3 | Samba-Kishenpur |  | 116 | 44 | 2 | 1 | 41 | 1 | 8 locations - ROW Clear 27 locations - supply of unequal leg extensions required / DD18/25/30 M extension required 5 locations under ROW

## Stringing JS-Jammu
KEC INTERNATIONAL LIMITED
400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5-Jammu Portion
Stringing
S.No | Section | Length Km | TSE/Manual | Insulator Hoisting |  | Paying Out |  | Rough Sag |  | Final Sag |  | Remarks | Gang | Manpower
|  |  |  | Start Date | End Date | Start Date | End Date | Start Date | End Date | Start Date | End Date
1 | AP25-AP26 | 1.028 | TSE | 2026-06-10 | 2026-06-12 | 2026-06-17 | 2026-06-21 | 2026-06-17 | 2026-06-21 | 2026-06-23 | 2026-06-24 | F/S Completed | Tariq | 32
2 | AP26-AP27 | 0.442 | Manual | 2026-06-14 | 2026-06-14 | 2026-06-14 | 2026-06-16 | 2026-06-14 | 2026-06-16 | 2026-06-17 | 2026-06-22 | F/S Completed | Tariq
3 | AP18-AP19 | 1.06 | TSE | 2026-06-20 | 2026-06-28 | 2026-07-07 | 2026-07-12 | 2026-07-08 | 2026-07-12 | 2026-07-16 | 2026-07-20 | F/S Completed | Janual Sheik | 25
4 | AP24-AP25 | 0.366 | Manual | 2026-06-25 | 2026-06-26 | 2026-06-26 | 2026-07-05 | 2026-06-27 | 2026-07-05 | 2026-07-04 | 2026-07-06 | F/S Completed | Tariq | 35
5 | AP20-AP21 | 0.486 | Manual | 2026-06-30 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-05 | 2026-08-03 | 2026-08-05 | F/S Completed | Janual Sheik | 25
6 | AP27-AP28 | 0.739 | Manual | 2026-07-07 | 2026-07-10 | 2026-07-11 | 2026-07-14 | 2026-07-12 | 2026-07-14 | 2026-07-17 | 2026-07-18 | F/S Completed | Tariq | 35
7 | AP19-AP20 | 1.089 | TSE | 2026-07-08 | 2026-07-10 | 2026-07-15 | 2026-07-19 | 2026-07-16 | 2026-07-19 | 2026-07-23 | 2026-07-25 | F/S Completed | Janual Sheik | 25
8 | AP28-AP29 | 0.446 | Manual | 2026-07-15 | 2026-07-16 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-29 | 2026-07-31 | 2026-08-02 | F/S Completed | Tariq | 35
9 | AP46-AP47 | 2.216 | TSE | 2026-07-17 | 2026-08-02 | [6 empty] | Pilot Paying out / Due to non availabilty of shutdown gang idle for last 8 days (Today due to Rain no Work Progres) | Musludin | 80
10 | AP29-AP30 | 2.57 | TSE | 2026-07-26 | 2026-08-04 | [6 empty] | Insulator Hoisting Pilot Wire Payingout, Back Stay WIP | Tariq | 35
11 | AP17-AP18 | 0.40116 | Manual | 2026-08-10 | [7 empty] | Insulator Hoisting WIP | Gopal Associates (Hot Line Gang) | 20

## Foundation -KS Line
KEC INTERNATIONAL LIMITED | [13 empty] | Date: | 2026-08-11
400 kV Kishenpur -Samba T/L
FOUNDATION
S.No | Loc No. | Tower Type | Classification | Forest/Non Forest | Start Date | Foundation |  |  |  |  | Completion Date | Status | Earthing | Gang Name | Gang Strength | Remark
[6 empty] | Excavation | Stub Setting | PCC | Rebar Placing | RCC
1 | 85/0 | DC+0 | DFR | Non Forest | 2025-10-01 | 2025-10-15 | 2025-10-23 | 2025-10-23 | 2025-10-24 | 2025-10-26 | 2025-10-26 | Completed | 2025-11-09 | Ankush Sharma | 8
2 | 86/0 | DD+0 | DFR | Non Forest | 2025-10-24 | 2025-11-06 | 2025-11-07 | 2025-11-09 | 2025-11-09 | 2025-11-10 | 2025-11-10 | Completed | 2025-11-11 | Ankush Sharma | 13
3 | 106/0 | DB+0 | DFR | Non Forest | 2025-10-14 | 2025-10-23 | 2025-10-30 | 2025-10-30 | 2025-10-31 | 2025-10-31 | 2025-10-31 | Completed | 2025-11-20 | Naresh | 8
4 | 28/0 | DC+3 | DFR | Non Forest | 2025-10-24 | 2025-10-30 | 2025-11-06 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-08 | Completed | 2025-11-14 | Asish Gupta | 9
5 | 27/0 | DB+3 | DFR | Non Forest | 2025-11-07 | 2025-11-29 | 2025-11-30 | 2025-11-30 | 2025-11-30 | 2025-11-30 | 2025-11-30 | Completed | 2025-12-04 | Asish Gupta | 10
6 | 25/0 | DB+0 | DFR | Non Forest | 2025-11-14 | 2025-11-18 | 2025-11-20 | 2025-11-21 | 22-11-205 | 2025-11-22 | 2025-11-22 | Completed | 2025-12-04
7 | 97/0 | DC-3 | DFR | Non Forest | 2025-10-28 | 2025-11-04 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-29 | 2025-11-29 | Completed | 2025-12-04 | BS Const | 10
8 | AP107 | DC+0 | DFR | Non Forest | 2025-11-02 | 2025-11-18 | 2025-11-20 | 2025-11-21 | 22-11-205 | 2025-11-22 | 2025-11-22 | Completed | 2025-12-03 | Naresh | 12
9 | AP79 | DD+9 | DFR | Non Forest | 2025-11-10 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | Completed | 2025-12-08 | Ankush Sharma | 13
10 | AP33 | DB+6 | DFR | Non Forest | 2025-11-14 | 2025-11-18 | 2025-11-28 | 2025-11-28 | 2025-11-29 | 2025-11-29 | 2025-11-29 | Completed | 2025-12-03 | Akthar | 10
11 | AP29 | DD-3 | WET | Non Forest | 2025-11-23 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-08 | Completed | 2026-01-02 | Asish Gupta | 10
12 | AP32 | DC-3 | WET | Non Forest | 2025-11-26 | 2025-12-17 | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-19 | 2025-12-19 | Completed | 2025-12-21 | Akthar | 10
13 | AP80 | DD+3 | DFR | Non Forest | 2025-11-28 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 2025-12-21 | 2025-12-21 | 2025-12-21 | Completed | 2025-12-23 | Ankush Sharma | 13
14 | AP105 | DD+0 | DFR | Non Forest | 2025-12-02 | 2025-12-09 | 2025-12-15 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-17 | Completed | 2025-12-18 | Naresh | 12
15 | AP96 | DC-3 | DFR | Non Forest | 2025-12-03 | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-21 | 2025-12-21 | 2025-12-21 | Completed | 2025-12-26 | BS Const | 10
16 | 30/1 | DA+0 | WET | Non Forest | 2025-12-08 | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-17 | 2025-12-17 | Completed | 2026-01-03 | Asish Gupta | 10
17 | AP43 | DC-3 | DFR | Non Forest | 2025-12-21 | 2025-12-28 | 2025-12-30 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | Completed | 2026-01-02 | Akthar | 10
18 | AP31 | DB+9 | WET | Non Forest | 2025-12-21 | 2025-12-25 | 2025-12-26 | 2025-12-26 | 2025-12-27 | 2025-12-28 | 2025-12-28 | Completed | 2026-01-10 | Asish Gupta | 10
19 | AP51 | DB+0 | DFR | Non Forest | 2025-12-25 | 2025-12-28 | 2026-01-03 | 2026-01-04 | 2026-01-04 | 2026-01-05 | 2026-01-05 | Completed | 2026-01-08 | BS Const | 10
20 | AP52 | DC-3 | DFR | Non Forest | 2025-12-25 | 2025-12-28 | 2025-12-30 | 2025-12-30 | 2025-12-30 | 2026-01-03 | 2026-01-03 | Completed | 2026-01-04 | Naresh | 12
21 | AP54 | DD+9 | DFR | Non Forest | 2025-12-25 | 2025-12-31 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-07 | 2026-01-07 | Completed | 2026-01-12 | Ankush Sharma | 13
22 | AP30 | DD+0 | WET | Non Forest | 2025-12-28 | 2026-01-09 | 2026-01-11 | 2026-01-11 | 2026-01-11 | 2026-01-12 | 2026-01-12 | Completed | Completed | Asish Gupta | 10
23 | AP44 | DD-3 | DFR | Non Forest | 2025-12-29 | 2026-01-12 | 2026-01-16 | 2026-01-17 | 2026-01-17 | 2026-01-19 | 2026-01-19 | Completed | 2026-01-21 | Akthar | 10
24 | AP26 | DB-3 | DFR | Non Forest | 2026-01-11 | 2026-01-19 | 2026-01-19 | 2026-01-20 | 2026-01-20 | 2026-01-21 | 2026-01-21 | Completed | 2026-01-22 | Asish Gupta | 10
25 | AP81 | DD+18 | WET | Non Forest | 2026-01-12 | 2026-02-23 | 2026-02-25 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | Completed | Completed | Ankush Sharma | 13
26 | AP8 | DD+0 | DRY | Non Forest | 2026-01-15 | 2026-02-03 | 2026-02-07 | 2026-02-07 | 2026-02-07 | 2026-02-10 | 2026-02-10 | Completed | 2026-02-11 | Kulbhushan | 6
27 | AP108 | DC+0 | DFR | Non Forest | 2026-01-17 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | Completed | Completed | Naresh | 12
28 | AP27A | DB+6 | FS | Non Forest | 2026-01-18 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | Completed | Completed | Asish Gupta | 10
29 | 8/2 | DB+3 | DFR | Non Forest | 2026-01-22 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | Completed | Completed | Md. Farooq | 6
30 | AP9 | DB+9 | DFR | Non Forest | 2026-02-03 | 2026-02-26 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | Completed | Completed | Asish Gupta | 10
31 | AP11 | DD+18 | DFR | Non Forest | 2026-02-03 | 2026-02-23 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | Completed | Completed | Akthar | 10
32 | 8/1 | DB+3 | DFR | Non Forest | 2026-02-05 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | Completed | Completed | Kulbhushan | 6
33 | 26/1 | DB | DFR | Non Forest | 2026-02-07 | 2026-02-24 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | Completed | Completed | Asish Gupta | 10
34 | 9/1 | DD+18 | DFR | Non Forest | 2026-02-10 | 2026-02-26 | 2026-02-28 | 2026-02-28 | 2026-02-28 | 2026-02-28 | 2026-02-28 | Completed | Completed | Asish Gupta | 10
35 | AP53 | DC+3 | DFR | Non Forest | 2026-02-11 | 2026-02-19 | 2026-02-24 | 2026-02-24 | 2026-02-26 | 2026-02-26 | 2026-02-26 | Completed | Completed | BS Const | 10
36 | AP84 | DC+9 | DFR | Non Forest | 2026-02-18 | 2026-02-23 | 2026-02-24 | 2026-02-27 | 2026-02-27 | 2026-02-28 | 2026-02-28 | Completed | Completed | Naresh | 10
37 | AP83 | DD+25 | DFR | Non Forest | 2026-02-18 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | Completed | Completed | Ankush Sharma | 10
38 | AP7 | DC+9 | DFR | Non Forest | 2026-02-20 | 2026-02-26 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | Completed | Completed | Kulbhushan | 12
39 | AP10 | DB+9 | DFR | Non Forest | 2026-02-28 | 2026-03-07 | 2026-03-08 | 2026-03-08 | 2026-03-08 | 2026-03-08 | 2026-03-08 | Completed | Completed | Akthar | 10
40 | AP24 | DC+0 | DFR | Non Forest | 2026-03-08 | 2026-03-25 | 2026-03-27 | 2026-03-27 | 2026-03-29 | 2026-03-30 | 2026-03-30 | Completed | Completed | Ganesh | 10
41 | AP6 | DC+9 | DFR | Non Forest | 2026-03-08 | 2026-03-25 | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-28 | Completed | Completed | Kulbhushan | 12
42 | AP95 | DD+0 | DFR | Non Forest | 2026-03-08 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-03-31 | Completed | Completed | BS Const | 10
43 | AP40 | DB-3 | DFR | Non Forest | 2026-03-11 | 2026-03-27 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-29 | 2026-03-29 | Completed | Completed | Ganesh | 10
44 | AP82 | DD+18 | DFR | Non Forest | 2026-03-12 | 2026-03-25 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | Completed | Completed | Naresh | 13
45 | AP87 | DC+9 | DFR | Non Forest | 2026-03-22 | 2026-04-11 | 2026-04-11 | 2026-04-13 | 2026-04-13 | 2026-04-15 | 2026-04-15 | Completed | Completed | Ankush Sharma | 10
46 | AP5 | DD+3 | DFR | Non Forest | 2026-03-30 | 2026-04-22 | 2026-04-24 | 2026-04-24 | 2026-04-26 | 2026-04-27 | 2026-04-27 | Completed | Completed | Kulbhushan | 12
47 | AP109 | DD+0 | DFR | Non Forest | 2026-04-04 | 2026-04-09 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-16 | 2026-04-20 | Completed | Completed | Naresh | 13
48 | AP94 | DC+0 | DFR | Non Forest | 2026-04-07 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | Completed | Completed | BS Const | 12
49 | AP42 | DB+3 | DFR | Non Forest | 2026-04-04 | 2026-04-18 | 2026-04-18 | 2026-04-20 | 2026-04-21 | 2026-04-27 | 2026-04-27 | Completed | Completed | Ganesh | 10
50 | AP88 | DD+0 | WET | Non Forest | 2026-04-15 | 2026-04-26 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-29 | Completed | Completed | Ankush Sharma | 10
51 | AP104 | DD+9 | DFR | Non Forest | 2026-04-19 | 2026-05-04 | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-07 | 2026-05-07 | Completed | Completed | Naresh | 13
52 | AP45 | DD+9 | DFR | Non Forest | 2026-04-19 | 2026-05-16 | 2026-05-17 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-05-29 | Completed |  | Ganesh | 10
53 | AP49 | DC+9 | DFR | Non Forest | 2026-04-21 | 2026-05-16 | 2026-05-17 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 | Completed |  | Rumal Singh | 7
54 | AP88A | DD+0 | WET | Non Forest | 2026-04-30 | 2026-05-17 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 | Completed | Completed | Ankush Sharma | 10
55 | AP90 | DD+0 | WET | Non Forest | 2026-05-05 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-29 | 2026-05-29 | Completed |  | BS Const | 10
56 | AP103 | DD+6 | WET | Non Forest | 2026-05-05 | 2026-05-19 | 2026-05-22 | 2026-05-24 | 2026-05-24 | 2026-05-31 | 2026-05-31 | Completed |  | Naresh | 13
57 | AP1 | DD+0 | DFR | Non Forest | 2026-05-10 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-05-31 | 2026-05-31 | 2026-05-31 | Completed | Completed | Kulbhushan | 10
58 | AP39 | DB+0 | DFR | Forest | 2026-05-15 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-22 | Completed |  | Ganesh | 10 |  | Forest
59 | AP35 | DC+9 | DFR | Forest | 2026-05-16 | 2026-06-19 | 2026-06-21 | 2026-06-21 | 2026-06-21 | 2026-06-23 | 2026-06-23 | Completed |  | RK Singh | 14
60 | AP88B | DD+0 | WET | Non Forest | 2026-05-23 | 2026-06-05 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | Completed |  | Ankush Sharma | 11
61 | AP50 | DD+3 | DFR | Forest | 2026-05-23 | 2026-06-26 | 2026-06-27 | 2026-06-27 | 2026-06-27 | 2026-06-29 | 2026-06-29 | Completed |  | Rumal Singh | 7
62 | AP102 | DD+0 | DFR | Non Forest | 2026-05-25 | 2026-06-05 | 2026-06-06 | 2026-06-06 | 2026-06-09 | 2026-06-25 | 2026-06-25 | Completed |  | Naresh | 13
63 | AP89 | DD+9 | WET | Non Forest | 2026-06-02 | 2026-06-12 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-17 | 2026-06-17 | Completed |  | BS Const | 11
64 | AP36 | DB+0 | DFR | Forest | 2026-06-11 | 2026-06-30 | 2026-07-07 | 2026-07-07 | 2026-07-09 | 2026-07-11 | 2026-07-11 | Completed |  | RK Singh | 14
65 | AP78 | DC+9 | DFR | Non Forest | 2026-06-21 | 2026-07-18 | [5 empty] | WIP |  | Naresh | 13 | Pit D - Casting upto frustrum Pit B,C- Excavation Completed Pit A - Steel Binding
66 | AP70 | DD+9 | DFR | Forest | 2026-06-16 | 2026-06-29 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-30 | Completed |  | Ankush Sharma | 13
67 | AP12 | DB+0 | DFR | Forest | 2026-06-20 | 2026-07-27 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-30 | Completed |  | Kalbhushan | 13
68 | AP13 | DB+9 | DFR | Forest | 2026-06-20 | 2026-06-28 | 2026-06-28 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 | Completed |  | Ganesh | 10
69 | AP2 | DD+30 | DFR | Non Forest | 2026-06-16 | [6 empty] | WIP |  | Kalbhushan | 10 | Pit C- Casting upto 1st part chimney Pit B- Casting Completed Pit D- Prop Setting
70 | AP23 | DB-3 | DFR | Forest | 2026-06-28 | 2026-07-29 | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-09 | 2026-08-09 | Completed |  | Anil Sharma | 10 | Pit A,B,C-Casting Completed Pit D- Casting upto Pyramid
71 | AP19 | DB+6 | WET | Forest | 2026-06-19 | 2026-07-14 | 2026-07-15 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-17 | Completed |  | Balwanth Singh | 13
72 | AP34 | DD+3 | DFR | Forest | 2026-06-26 | 2026-07-15 | 2026-07-16 | 2026-07-18 | 2026-07-19 | 2026-07-27 | 2026-07-27 | Completed |  | RK Singh | 14
73 | AP77 | DD+18 | DFR | Non Forest | 2026-06-28 | [6 empty] | WIP |  | BS Const |  | Pit B,C - Excavation (Dewatering) Work on hold due to rains and approach road issue
74 | AP41 | DC+6 | DFR | Forest | 2026-06-29 | [6 empty] | WIP |  | Darshan | 10 | Pit A-Casting Completed Pit B,C,D - Excavation WIP
75 | AP56 | DC+0 | DFR | Forest | 2026-07-02 | 2026-07-15 | 2026-07-17 | 2026-07-19 | 2026-07-20 | 2026-07-27 | 2026-07-27 | Completed |  | KDR Engineering | 8
76 | AP14 | DB-3 | DFR | Forest | 2026-07-05 | 2026-08-07 | [5 empty] | WIP |  | Ganesh | 10 | Pit A,B- Casting Completd Pit D-Casting upto Pyramid Pit C- Excavation
77 | AP60 | DB+0 | DFR | Forest | 2026-07-05 | [6 empty] | WIP |  | Rumal Singh | 12 | Pit A, B, D -Excavation WIP Material Shifting WIP
78 | AP48 | DC-3 | DFR | Forest | 2026-07-12 | [6 empty] | WIP |  | Darshan | 8 | Pit C,D - Excavation WIP -Manually Pit A,B, - Prop Setting Material Shifting WIP
79 | AP20 | DB+0 | DFR | Forest | 2026-07-24 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 |  |  | WIP |  | Balwanth Singh | 11 | Pit A,B- Casting Completed Pit C,D- Casting upto frustrum
80 | AP57 | DC+9 | DFR | Forest | 2026-07-30 | [6 empty] | WIP |  | Harsh | 8 | Pit D- Excavation Completed Pit A - Prop Setting and Steel Binding WIP Due to rains pits waterlogged Material Shifting WIP
81 | AP59 | DC-3 | DFR | Forest | 2026-08-01 | [6 empty] | WIP |  | Yogesh | 5 | Pit B,C- Excavation WIP
82 | AP66 | DD+9 | DFR | Forest | [7 empty] | WIP |  | Naresh |  | Approach Road Making WIP
83 | AP61 | DC+0 | DFR | Forest | 2026-08-06 | [6 empty] | WIP |  | Rumal Singh |  | Pit A, D, C - Excavation WIP
84 | AP55 | DC-3 | DFR | Forest | 2026-08-03 | [6 empty] | WIP |  | KDR Engineering | 8 | Pit A, B, - Excavation WIP Material Shifting WIP
85 | AP22 | DC+0 | DFR | Forest | [7 empty] | WIP |  | Anil Sharma |  | Approach Road Work WIP
86 | AP18 | DB+6 | DFR | Forest | [7 empty] | WIP |  | Balwanth Singh | 7 | Marking WIP
87 | AP71 | DD-3 | DFR | Forest | 2026-08-06 | [6 empty] | WIP |  | Ankush Sharma | 13 | Pit A, C - Excavation Completed
88 | AP67 | DC+9 | DFR | Forest | [7 empty] | WIP |  | BS Const | 10 | Approach Road Making WIP
89 | AP64 | DC-3 | DFR | Forest | 2026-08-08 | [6 empty] | WIP |  | Naresh |  | Pit A, B - Excavation WIP
90 | AP65 | DC-3 | DFR | Forest | 2026-08-10 | [6 empty] | WIP |  | Naresh |  | Pit A- Excavation WIP

## Erection -SK
KEC INTERNATIONAL LIMITED | [6 empty] | Date: | 2026-08-11
400kV D/C Samba -Kishenpur TL
TOWER ERECTION
S.No | Loc No. | Tower Type | Weight MT | Starting Date | Completion Date | Status | Gang Name | Gang Strength | Remark
1 | 30/1 | DA+0 | 18.34 | 2026-03-18 | 2026-03-24 | Completed | Anvi Construction | 18
2 | AP27A | DB+6 | 34.578 | 2026-03-24 | 2026-03-31 | Completed | Anvi Construction | 23
3 | AP31 | DB+9 | 36.354 | 2026-04-09 | 2026-05-21 | Completed | Anvi Construction | 18 | Work restart from 16-05-2026
4 | AP30 | DD+0 | 42.226 | 2026-05-21 | 2026-06-03 | Completed | Anvi Construction | 18
5 | AP29 | DD-3 | 38.9884 | 2026-06-03 | 2026-06-13 | Completed | Anvi Construction | 18
6 | AP27 | DB+3 | 29.31 | 2026-03-13 | 2026-06-27 | Completed | Anvi Construction | 18
7 | 26/1 | DB+9 | 30.035 | 2026-06-27 | 2026-07-12 | Completed | Anvi Construction | 20
8 | AP43 | DC-3 | 29.865 | 2026-06-28 | 2026-07-07 | Completed | Kushboo Devi | 22
9 | AP54 | DD+9 | 56.157 | 2026-06-29 | 2026-07-09 | Completed | Saritha Devi | 24
10 | AP87 | DC+9 | 41.525 | 2026-07-05 | 2026-07-31 | Completed | Neelkant | 20
11 | AP89 | DD+9 | 56.157 | 2026-07-05 | 2026-07-17 | Completed | Prem Latha-1 | 30
12 | AP39 | DB+0 | 27.922 | 2026-07-05 | 2026-07-15 | Completed | Splice Net | 22
13 | AP90 | DD+0 | 41.912 | 2026-07-09 | 2026-07-24 | Completed | Prem Latha-2 | 25
14 | AP44 | DD-3 | 39.296 | 2026-07-07 | 2026-07-18 | Completed | Kushboo Devi | 28
15 | AP26 | DB-3 | 26.709 | 2026-07-12 | 2026-07-27 | Completed | Anvi Construction | 20
16 | AP36 | DB+0 | 27.91 | 2026-07-26 | 2026-08-06 | Completed | Splice Net | 25
17 | AP88 | DD+0 | 41.773 | 2026-07-18 | 2026-07-29 | Completed | Prem Latha-1 | 30
18 | AP33 | DB+6 | 34.634 | 2026-07-26 | 2026-08-09 | Completed | Kushboo Devi | 28
19 | AP53 | DC+3 | 33.4 | 2026-07-27 |  | 3rd section | Kauleshwar Mahato | 18 | No Progress due to Rain
20 | AP85 | DC+0 | 32.066 | 2026-07-26 | 2026-08-03 | Completed | Prem Latha-2 | 25
21 | 9/1 | DD+18 | 71.31 | 2026-07-26 |  | Bottom Section | Jirwa Devi | 25 | No Progress due to Rain
22 | AP25 | DB+0 | 27.922 | 2026-07-27 | 2026-08-10 | Completed | Anvi Construction | 20
23 | AP11 | DD+18 | 71.31 | 2026-07-28 |  | 5th section | Jwala Singh | 25
24 | AP88A | DD+0 | 42.254 | 2026-07-29 | 2026-08-04 | Completed | Prem Latha-1 | 30
25 | AP86 | DD+0 | 42.43 | 2026-07-31 |  | 1st section | Neelkant | 20 | No Progress due to Rain
26 | AP10 | DB+9 | 36.355 | 2026-07-31 | 2026-08-07 | Completed | Kajal Const | 35
27 | AP88B | DD+0 | 42.744 | 2026-08-03 |  | Cross Arm WIP | Prem Latha-2 | 25
28 | AP80 | DD+3 | 43.7922 | 2026-08-05 |  | 1st section | Prem Latha-1 | 30 | No Progress due to Rain
29 | AP35 | DC+9 | 41.283 | 2026-08-07 |  | 1st section | Splice Net | 25 | No Progress due to Rain
30 | AP13 | DB+9 | 36.355 | 2026-08-07 |  | 2nd section | Kajal Const | 35
31 | AP42 | DB+3 | 29.492 | 2026-08-09 |  | Material Shifting | Kushboo Devi | 28 | Approach Road wash due to heavy rain

## Sheet7 (hidden)
S.No | Loc | TOT | RC | RC | RC | RC
1 | AP144 | DB+0
2
3
4 |  |  | 1 | 1 | 1 | 1
5
6 | AP145 | DB+0 | 2 | 2 | 2 | 2
7
8
9
10
11
12 | [6 empty] | Hussain
13 | [6 empty] | Hussain
14 | [6 empty] | Hussain
15 | [6 empty] | Hussain
16
17
18
19 |  |  | 1 | 1 | 1 | 1
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46 | AP66 | DC+0
47 | AP67 | DD+0
48 | 67/1 | DA+0
49 | 67/2 | DA+0
50 | 67/3 | DA+0
51 | AP68 | DB+0
52
53
54
55 | 69/3 | DA+0
56 | AP70 | DC+3

## Sheet8 (hidden)
Tower | Structure | Supplied Qty till date | Material DI received and will dispatch in 1 week | Total | Tower | Supplied Qty | Material Under Transit | Total
DA | Basic Tower Body | 87 |  | 87 | DA+0 | 34 |  | 34
| +0MBE | 48 |  | 48 | DA+3 | 39 |  | 39
| +3MBE | 39 |  | 39 | DA+6 | 12 |  | 12
| +6MBE | 12 |  | 12 | DA+9 | 2 |  | 2
| +9MBE | 2 |  | 2 |  |  |  | 0
DB | Basic Tower Body | 13 | 16 | 29 | DB+0 | 10 | 14 | 24
| +0MBE | 11 | 16 | 27 | DB+3 | 2 |  | 2
| +3MBE | 2 |  | 2 | DB+6 | 1 |  | 1
| +6MBE | 1 |  | 1 | DB+9 |  | 2 | 2
| +9MBE |  | 2 | 2 |  |  |  | 0
DC | Basic Tower Body | 5 |  | 5 | DC+0 |  |  | 0
| +0MBE | 2 |  | 2 | DC+3 | 3 |  | 3
| +3MBE | 3 |  | 3 | DC+6 | 2 |  | 2
| +6MBE | 2 |  | 2 | DC+9 |  |  | 0
| +9MBE | [6 empty] | 0
DD | Basic Tower Body | 5 | 19 | 24 | DD+0 |  | 13 | 13
| +0MBE | 2 | 18 | 20 | DD+3 | 3 | 1 | 4
| +3MBE | 3 | 1 | 4 | DD+6 | 2 |  | 2
| +6MBE | 2 |  | 2 | DD+9 |  | 5 | 5
| +9MBE |  | 5 | 5 |  |  |  | 0
| +18MBE | [6 empty] | 0
| +25MBE | [6 empty] | 0
| +30MBE | [6 empty] | 0
Total |  | 110 | 35 | 145 | Total | 110 | 35 | 145

## Material Status SK
400 kV Kishenpur-Samba D/C line(Quad) - Wind Zone - 5-Jammu Portion
Tower Erection Plan- Aug-26 | [6 empty] | Material Shifting from Store in % | Material Shifting from Site to Loc in % | Material Headloading Mode | Status
S.No | Loc | Tower | MT | Gang | Start Date | End Date
1 | AP25 | DB+0 | 27.9217 | Anvi Const | 2026-08-01 | 2026-08-11 | 100 | 100 | Tractor / Manual | Completed
2 | AP28 | DC+3 | 33.5472 |  | 2026-08-12 | 2026-08-21 |  |  | Tractor / Manual
3 | AP23 | DB-3 | 27.9355 |  | 2026-08-22 | 2026-08-31 |  |  | Tractor / Manual
4 | AP33 | DB+6 | 34.63 | Kushboo Devi | 2026-07-30 | 2026-08-09 | 100 | 100 | Tractor / Manual | Completed
5 | AP42 | DB+3 | 29.4921 |  | 2026-08-10 | 2026-08-19 | 40 | 20 | Tractor / Manual | Material Shifting
6 | AP45 | DD+9 | 56.1568 |  | 2026-08-20 | 2026-08-29 |  |  | Tractor / Manual
7 | AP36 | DB+0 | 27.91 | Splice Net | 2026-07-27 | 2026-08-06 | 100 | 100 | Tractor / Manual | Completed
8 | AP35 | DC+9 | 41.283 |  | 2026-08-08 | 2026-08-17 | 100 | 30 | Tractor / Manual | 1st section
9 | AP34 | DD+3 | 43.1981 |  | 2026-08-19 | 2026-08-28 | 70 | 20 | Tractor / Manual
10 | AP88A | DD+0 | 42.2539 | Prem Latha-1 | 2026-07-30 | 2026-08-09 | 100 | 100 | Tractor / Manual | Completed
11 | AP88B | DD+0 | 42.7441 |  | 2026-08-10 | 2026-08-19 | 50 | 30 | Tractor / Manual | Cross Arm WIP
12 | AP49 | DC+9 | 41.525 |  | 2026-08-20 | 2026-08-29 |  |  | Tractor / Manual
13 | AP85 | DC+0 | 32.07 | Prem Latha-2 | 2026-07-30 | 2026-08-09 | 100 | 100 | Tractor / Manual | Completed
14 | AP50 | DD+3 | 43.338 |  | 2026-08-10 | 2026-08-20 |  |  | Tractor / Manual
15 | AP86 | DD+0 | 42.4298 | Neelkant | 2026-08-08 | 2026-08-20 | 60 | 30 | Tractor / Manual | 1st section
16 | AP79 | DD+9 | 52.6905 | Maa Const | 2026-08-01 | 2026-08-11 | 50 | 50 | Tractor / Manual
17 | AP80 | DD+3 | 43.7917 |  | 2026-08-13 | 2026-08-23 | 30 | 0 | Tractor / Manual | 1st section
18 | 9/1 | DD+18 | 71.3103 | Jirwa Devi | 2026-07-30 | 2026-08-14 | 70 | 60 | Tractor / Manual | Bottom Section
19 | AP53 | DC+3 | 33.405 | Kauleshwar | 2026-08-01 | 2026-08-11 | 95 | 95 | Tractor / Manual | 3rd section
20 | AP52 | DC-3 | 30.933 |  | 2026-08-13 | 2026-08-23 |  |  | Tractor / Manual
21 | AP11 | DD+18 | 71.3103 | Jwala Singh | 2026-08-01 | 2026-08-16 | 100 | 100 | Tractor / Manual | 5th section
22 | AP12 | DB+0 | 27.921 |  | 2026-08-17 | 2026-08-27 |  |  | Tractor / Manual
23 | AP10 | DB+9 | 36.3551 | Kajal Const | 2026-08-03 | 2026-08-12 | 100 | 100 | Tractor / Manual
24 | AP13 | DB+9 | 36.355 | Maa Const-2 | 2026-08-05 | 2026-08-15 | 50 | 40 | Tractor / Manual
25 | AP19 | DB+6 | 35.48 |  | 2026-08-16 | 2026-08-26 |  |  | Tractor / Manual
Formulas:
End Date = [Start Date]+10

## Stringing SK
KEC INTERNATIONAL LIMITED
400 kV Samba- Kishenpur D/C Line(Quad) - Wind Zone - 5
Stringing
S.No | Section | Length Km | TSE/Manual | Insulator Hoisting |  | Paying Out |  | Rough Sag |  | Final Sag |  | Remarks | Gang | Manpower
|  |  |  | Start Date | End Date | Start Date | End Date | Start Date | End Date | Start Date | End Date
1 | AP25-AP27 | 1.0818 | Manual | 2026-08-10 | [7 empty] | (Today No Progress due to rain) | Nogyo Tec (Drawn) | 32

## LILO
KEC INTERNATIONAL LIMITED | [13 empty] | Date: | 2026-08-11
LILO Kishtwar - Wind Zone - 2
FOUNDATION
S.No | Loc No. | Tower Type | Classification | Conc Volume | Start Date | Foundation |  |  |  |  | Completion Date | Status | Earthing | Gang Name | Gang Strength | Remark
[6 empty] | Excavation | Stub Setting | PCC | Rebar Placing | RCC
1 | AP7 | DDM+E0+0 | DFR | 36.109 | 2026-04-09 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 2026-05-24 | 2026-05-24 | Completed |  | Zaffar | 12 | Pit A- RR Wall Completed on 7-8-2026
2 | AP8 | DDM+E6+3 | DFR | 36.109 | 2026-03-28 | 2026-06-25 | 2026-06-26 | 2026-06-26 | 2026-06-27 | 2026-06-27 | 2026-06-27 | Completed |  | Bittu | 8 | Pit A- RC WIP
3 | AP9 | DDM+E0+0 | DFR | 36.109 | 2026-03-29 | 2026-07-30 | 2026-07-30 | 2026-08-10 | 2026-08-11 | 2026-08-11 | 2026-08-11 | Completed |  | Bhat Const. | 12 | RC Pending
4 | AP10 | DDM+E6+3 | DFR | 36.109 | 2026-04-28 | [6 empty] | WIP |  | Bhat Const. |  | Pit A,B,C- Excavation WIP
5 | 8/1 | DDM+E6+3 | DFR | 36.109 | 2026-05-18 | 2026-06-20 | 2026-06-21 | 2026-06-21 | 2026-06-22 | 2026-06-22 | 2026-06-22 | Completed |  | Bittu | 5 | RC Pending
6 | AP6 | DDM+E0+0 | DFR | 36.109 | 2026-05-08 | 2026-06-19 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 2026-06-24 | Completed |  | Zaffar | 12 | RC Pending
7 | AP5 | DDM+E0+0 | DFR | 36.109 | 2026-06-06 | 2026-06-15 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 | Completed | 2026-07-02 | TR Kotwal | 12
8 | AP2 | DDM+E6+3 | DFR | 36.109 | 2026-06-14 | [6 empty] | WIP |  | Zaffar | 12 | Pit C- Casting upto step box Pit D- Excavation Completed
9 | AP11 | DDM+E6+3 | DFR | 36.109 | 2026-06-20 | 2026-08-09 | [5 empty] | WIP |  | Abdul Jabbar | 14 | Pit A- Casting Completed Pit C- Casting 1st part chimney Pit B - Excavation Completed Pit D - Casting upto Step Box
10 | AP12 | DDM+E40+0 | DFR | 36.109 | 2026-06-28 | 2026-07-30 | [5 empty] | WIP |  | Abdul Jabbar |  | Pit A,B,C,D- Excavation Completed
11 | AP4 | DDM+E6+3 | DFR | 36.109 | 2026-06-29 | 2026-07-05 | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-11 | 2026-08-11 | WIP |  | TR Kotwal | 16 | RC Pending
12 | AP3 | DDM+E6+3 | DFR | 36.109 | 2026-07-03 | [6 empty] | WIP |  | TR Kotwal |  | Pit B,D - Excavation Completed
13 | AP13 | DDM+40+0 | DFR | 36.109 | 2026-07-30 | [6 empty] | WIP |  | Abdul Jabbar | 5 | Pit A- Excavation WIP

## Erection-Punjab
KEC INTERNATIONAL LIMITED | [7 empty] | Date: | 2026-08-11
400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5- Punjab Portion
TOWER ERECTION
S.No | Loc No. | Tower Type | Weight MT | Conc Volume | Starting Date | Completion Date | Status | Gang Name | Gang Strength | Final Checking Status | Remark
1 | 89/1 | DA+3 | 19.44 | 34.389 | 2026-02-02 | 2026-02-06 | Completed | Saritha Devi | 30
2 | 117/3 | DA+0 | 18.339 |  | 2026-02-03 | 2026-02-07 | Completed | Poonam Kumari | 34
3 | 95/3 | DA+0 | 18.339 |  | 2026-02-06 | 2026-02-08 | Completed | Saritha Devi | 30 | Completed
4 | 97/2 | DA+0 | 18.339 |  | 2026-02-05 | 2026-02-09 | Completed | Jwala Singh | 22
5 | 92/2 | DA+6 | 22.68 | 21.318 | 2026-02-02 | 2026-02-10 | Completed | Dhruv Strategic | 32
6 | 117/1 | DA+0 | 18.339 |  | 2026-02-07 | 2026-02-11 | Completed | Poonam Kumari | 34
7 | 95/2 | DA+0 | 18.339 |  | 2026-02-08 | 2026-02-11 | Completed | Saritha Devi | 30 | Completed
8 | 97/1 | DA+0 | 18.339 |  | 2026-02-09 | 2026-02-12 | Completed | Jwala Singh | 22
9 | 95/4 | DA+0 | 18.339 |  | 2026-02-11 | 2026-02-13 | Completed | Saritha Devi | 30 | Completed
10 | 117/2 | DA+3 | 19.44 |  | 2026-02-11 | 2026-02-16 | Completed | Poonam Kumari-1 | 34
11 | 92/3 | DA+0 | 18.339 |  | 2026-02-12 | 2026-02-16 | Completed | Poonam Kumari-2 | 30
12 | 131/4 | DA+0 | 18.339 |  | 2026-02-12 | 2026-02-17 | Completed | ZR Construction | 30
13 | 97/3 | DA+3 | 19.44 |  | 2026-02-12 | 2026-02-17 | Completed | Jwala Singh | 22
14 | AP96 | DC+0 | 32.222 |  | 2026-02-13 | 2026-02-17 | Completed | Saritha Devi | 30 | Completed
15 | 93/2 | DA+0 | 18.339 |  | 2026-02-17 | 2026-02-20 | Completed | Poonam Kumari-2 | 30 | Completed
16 | AP115 | DB+0 | 27.92 |  | 2026-02-16 | 2026-02-20 | Completed | Poonam Kumari-1 | 34 | Completed
17 | 98/1 | DA+3 | 19.44 |  | 2026-02-17 | 2026-02-20 | Completed | Jwala Singh | 22
18 | 76/1 | DA+0 | 18.339 |  | 2026-02-17 | 2026-02-22 | Completed | Rakesh | 23 | Completed
19 | AP94 | DB+0 | 27.92 |  | 2026-02-17 | 2026-02-21 | Completed | Saritha Devi | 30 | Completed
20 | 131/5 | DA+3 | 19.44 |  | 2026-02-17 | 2026-02-22 | Completed | ZR Construction | 30
21 | 118/1 | DA+0 | 18.339 |  | 2026-02-21 | 2026-02-23 | Completed | Poonam Kumari-1 | 34
22 | AP98 | DB+3 | 29.492 |  | 2026-02-22 | 2026-02-26 | Completed | Jwala Singh | 22
23 | AP93 | DC+0 | 32.222 |  | 2026-02-20 | 2026-02-25 | Completed | Poonam Kumari-2 | 30 | Completed
24 | AP95 | DC+3 | 33.53 |  | 2026-02-21 | 2026-02-25 | Completed | Saritha Devi | 30 | Completed
25 | 76/2 | DA+3 | 19.44 |  | 2026-02-22 | 2026-02-27 | Completed | Rakesh | 23 | Completed
26 | 131/3 | DA+3 | 19.44 |  | 2026-02-23 | 2026-02-27 | Completed | ZR Construction | 30
27 | AP117 | DB+0 | 27.92 |  | 2026-02-24 | 2026-02-28 | Completed | Poonam Kumari-2 | 30 | Completed
28 | 87/2 | DA+3 | 19.44 |  | 2026-02-25 | 2026-02-28 | Completed | Saritha Devi | 30
29 | 92/1 | DA+3 | 19.44 |  | 2026-02-25 | 2026-02-28 | Completed | Poonam Kumari-2 | 30
30 | AP99 | DB+0 | 27.92 |  | 2026-02-26 | 2026-03-02 | Completed | Jwala Singh | 22
31 | 71/2 | DA+9 | 24.149 |  | 2026-02-27 | 2026-03-05 | Completed | Rakesh | 23 | Completed
32 | 131/1 | DA+3 | 19.44 |  | 2026-02-27 | 2026-03-02 | Completed | ZR Construction | 30
33 | AP97 | DD+3 | 44.071 |  | 2026-03-01 | 2026-03-09 | Completed | Saritha Devi | 30 | Completed
34 | AP106 | DD+6 | 52.663 |  | 2026-03-01 | 2026-03-13 | Completed | Poonam Kumari | 30
35 | 103/1 | DA+0 | 18.339 |  | 2026-03-02 | 2026-03-07 | Completed | Jwala Singh | 22
36 | 132/1 | DA+3 | 19.442 |  | 2026-03-02 | 2026-03-08 | Completed | ZR Construction | 30
37 | 76/3 | DA+3 | 19.442 |  | 2026-03-05 | 2026-03-10 | Completed | Rakesh | 23 | Completed
38 | 116/1 | DA+0 | 18.34 |  | 2026-03-07 | 2026-03-09 | Completed | Jwala Singh | 22
39 | 156/4 | DA+0 | 18.34 |  | 2026-03-07 | 2026-03-13 | Completed | Vijay Bhagat | 25
40 | 130/2 | DA+0 | 18.34 |  | 2026-03-08 | 2026-03-13 | Completed | ZR Construction | 30 |  | Due to ROW work hampered on 09-03-2026
41 | 90/2 | DA+0 | 18.34 |  | 2026-03-09 | 2026-03-12 | Completed | Saritha Devi | 30
42 | AP102 | DB+0 | 27.92 |  | 2026-03-11 | 2026-03-14 | Completed | Jwala Singh | 22
43 | AP77 | DB+3 | 29.492 |  | 2026-03-11 | 2026-03-17 | Completed | Rakesh | 23 | Completed
44 | 95/1 | DA+0 | 18.34 |  | 2026-03-12 | 2026-03-15 | Completed | Saritha Devi | 30 | Completed
45 | 131/6 | DA+9 | 24.149 |  | 2026-03-13 | 2026-03-19 | Completed | ZR Construction | 30
46 | AP157 | DB+0 | 27.92 |  | 2026-03-13 | 2026-03-21 | Completed | Vijay Bhagat | 25
47 | AP111 | DC+0 | 32.222 |  | 2026-03-13 | 2026-03-22 | Completed | Poonam Kumari | 30
48 | AP100 | DC+3 | 33.53 |  | 2026-03-14 | 2026-03-19 | Completed | Jwala Singh | 22
49 | 69/3 | DA+0 | 18.34 |  | 2026-03-17 | 2026-03-21 | Completed | Saritha Devi | 30
50 | 77/1 | DA+3 | 19.44 |  | 2026-03-17 | 2026-03-22 | Completed | Rakesh | 23 | Completed
51 | 136/1 | DA+3 | 19.44 |  | 2026-03-21 | 2026-03-31 | Completed | ZR Construction | 30
52 | AP104 | DB+0 | 27.92 |  | 2026-03-20 | 2026-03-23 | Completed | Jwala Singh | 22
53 | 69/2 | DA+0 | 18.34 |  | 2026-03-21 | 2026-03-24 | Completed | Saritha Devi | 30
54 | AP156 | DC+0 | 32.22 |  | 2026-03-21 | 2026-03-29 | Completed | Vijay Bhagat | 25
55 | 77/2 | DB+0 | 27.92 |  | 2026-03-22 | 2026-03-28 | Completed | Rakesh | 23 | Completed
56 | 104/1 | DA+3 | 19.44 |  | 2026-03-23 | 2026-03-25 | Completed | Jwala Singh | 22
57 | 115/1 | DA+6 | 22.68 |  | 2026-03-26 | 2026-03-31 | Completed | Vijay Bhagat-2 | 18
58 | AP68 | DB+0 | 27.92 |  | 2026-03-24 | 2026-03-29 | Completed | Saritha Devi | 30
59 | AP103 | DD+0 | 42.226 |  | 2026-03-26 | 2026-03-31 | Completed | Jwala Singh | 22
60 | AP80 | DD+0 | 42.226 |  | 2026-03-28 | 2026-04-05 | Completed | Rakesh | 23 | Completed
61 | 69/1 | DA+0 | 18.34 |  | 2026-03-29 | 2026-03-31 | Completed | Saritha Devi | 30
62 | 157/1 | DA+0 | 18.34 |  | 2026-03-29 | 2026-04-03 | Completed | Vijay Bhagat | 20
63 | AP85 | DB+0 | 27.92 |  | 2026-04-04 | 2026-04-12 | Completed | Vijay Bhagat-2 | 20
64 | 145/1 | DA+0 | 18.34 |  | 2026-03-31 | 2026-04-04 | Completed | Jwala Singh | 25
65 | AP70 | DC+3 | 33.53 |  | 2026-03-31 | 2026-04-07 | Completed | Saritha Devi | 24
66 | 135/1 | DA+6 | 22.68 |  | 2026-04-04 | 2026-04-13 | Completed | ZR Construction | 20
67 | AP146 | DC+0 | 32.22 |  | 2026-04-04 | 2026-04-10 | Completed | Jwala Singh | 25
68 | 156/2 | DA+0 | 18.34 |  | 2026-04-04 | 2026-04-09 | Completed | Vijay Bhagat-1 | 25
69 | AP79 | DD+9 | 56.129 |  | 2026-04-06 | 2026-04-17 | Completed | Rakesh | 20 | Completed
70 | 151/1 | DA+0 | 18.34 |  | 2026-04-10 | 2026-04-12 | Completed | Jwala Singh | 25
71 | 156/3 | DA+0 | 18.34 |  | 2026-04-10 | 2026-04-14 | Completed | Vijay Bhagat-1 | 25
72 | 67/1 | DA+0 | 18.34 |  | 2026-04-11 | 2026-04-13 | Completed | Saritha Devi | 24
73 | AP114 | DB+0 | 27.92 |  | 2026-04-12 | 2026-04-19 | Completed | Vijay Bhagat-2 | 20
74 | 150/2 | DA+0 | 18.34 |  | 2026-04-12 | 2026-04-16 | Completed | Jwala Singh | 25
75 | 70/2 | DA+0 | 18.34 |  | 2026-04-13 | 2026-04-17 | Completed | Saritha Devi | 24
76 | 136/2 | DA+3 | 19.44 |  | 2026-04-13 | 2026-04-17 | Completed | ZR Construction | 20
77 | 155/1 | DA+0 | 18.34 |  | 2026-04-14 | 2026-04-17 | Completed | Vijay Bhagat-1 | 25
78 | 152/1 | DA+3 | 19.44 |  | 2026-04-16 | 2026-04-19 | Completed | Jwala Singh | 25
79 | AP69 | DB+0 | 27.92 |  | 2026-04-17 | 2026-04-21 | Completed | Saritha Devi | 24
80 | 82/1 | DA+0 | 18.34 |  | 2026-04-17 | 2026-04-21 | Completed | Rakesh | 20 | Completed
81 | AP135 | DB+3 | 29.492 |  | 2026-04-18 | 2026-04-25 | Completed | ZR Construction | 20
82 | 155/2 | DA+0 | 18.34 |  | 2026-04-18 | 2026-04-22 | Completed | Vijay Bhagat-1 | 25
83 | 99/1 | DA+9 | 24.149 |  | 2026-04-19 | 2026-04-27 | Completed | Vijay Bhagat-2 | 20
84 | 145/2 | DA+3 | 19.44 |  | 2026-04-19 | 2026-04-22 | Completed | Jwala Singh | 25
85 | 72/1 | DA+3 | 19.44 |  | 2026-04-21 | 2026-04-25 | Completed | Saritha Devi | 24
86 | AP75 | DB+9 | 36.354 |  | 2026-04-21 | 2026-04-28 | Completed | Rakesh | 20 | Completed
87 | 155/3 | DA+0 | 18.34 |  | 2026-04-22 | 2026-04-27 | Completed | Vijay Bhagat-1 | 25
88 | 150/1 | DA+0 | 18.34 |  | 2026-04-22 | 2026-04-26 | Completed | Jwala Singh | 25
89 | 136/3 | DA+0 | 18.34 |  | 2026-04-25 | 2026-04-30 | Completed | ZR Construction | 20
90 | 72/2 | DA+6 | 22.68 |  | 2026-04-25 | 2026-04-30 | Completed | Saritha Devi | 24
91 | AP147 | DB+0 | 27.92 |  | 2026-04-26 | 2026-04-30 | Completed | Jwala Singh | 25
92 | 156/1 | DA+6 | 22.68 |  | 2026-04-27 | 2026-05-04 | Completed | Vijay Bhagat-1 | 25
93 | AP118 | DC+0 | 32.22 |  | 2026-04-27 | 2026-05-05 | Completed | Vijay Bhagat-2 | 20
94 | AP74 | DB+0 | 27.92 |  | 2026-04-28 | 2026-05-03 | Completed | Rakesh | 20 | Completed
95 | AP72 | DB+3 | 29.492 |  | 2026-04-30 | 2026-05-05 | Completed | Saritha Devi | 24
96 | 131/2 | DA+3 | 19.442 |  | 2026-04-30 | 2026-05-05 | Completed | ZR Construction | 20
97 | 144/4 | DA+0 | 18.34 |  | 2026-04-30 | 2026-05-04 | Completed | Jwala Singh | 25
98 | 82/2 | DA+3 | 19.44 |  | 2026-05-03 | 2026-05-08 | Completed | Rakesh | 20 | Completed
99 | AP129 | DB+9 | 36.354 |  | 2026-05-05 | 2026-05-15 | Completed | Vijay Bhagat-2 | 20
100 | 71/3 | DA+6 | 22.679 |  | 2026-05-05 | 2026-05-08 | Completed | Saritha Devi | 24
101 | 137/1 | DA+0 | 18.34 |  | 2026-05-05 | 2026-05-14 | Completed | ZR Construction | 20
102 | AP145 | DB+0 | 27.921 |  | 2026-05-05 | 2026-05-07 | Completed | Jwala Singh | 25
103 | 151/2 | DA+3 | 19.44 |  | 2026-05-07 | 2026-05-10 | Completed | Jwala Singh | 25
104 | 93/1 | DA+0 | 18.34 |  | 2026-05-08 | 2026-05-10 | Completed | Saritha Devi | 24 | Completed
105 | 67/3 | DA+0 | 18.34 |  | 2026-05-08 | 2026-05-13 | Completed | Rakesh | 20 | Completed
106 | 90/1 | DA+3 | 19.44 |  | 2026-05-10 | 2026-05-13 | Completed | Saritha Devi | 24
107 | 153/1 | DA+0 | 18.34 |  | 2026-05-10 | 2026-05-13 | Completed | Jwala Singh | 25
108 | 86/1 | DA+3 | 19.44 |  | 2026-05-14 | 2026-05-16 | Completed | Saritha Devi | 24
109 | 152/4 | DA+0 | 18.34 |  | 2026-05-14 | 2026-05-16 | Completed | Jwala Singh | 25
110 | 130/1 | DA+0 | 18.34 |  | 2026-05-15 | 2026-05-20 | Completed | Vijay Bhagat-2 | 20
111 | AP90 | DD+0 | 42.226 |  | 2026-05-16 | 2026-05-21 | Completed | Saritha Devi | 24
112 | 152/3 | DA+0 | 18.34 |  | 2026-05-16 | 2026-05-19 | Completed | Jwala Singh | 25
113 | 153/2 | DA+3 | 19.44 |  | 2026-05-19 | 2026-05-23 | Completed | Jwala Singh | 25
114 | AP136 | DC+3 | 33.53 |  | 2026-05-20 | 2026-05-28 | Completed | Vijay Bhagat-2 | 20
115 | AP67 | DD+0 | 42.226 |  | 2026-05-22 | 2026-05-28 | Completed | Saritha Devi | 24
116 | AP153 | DC+0 | 32.223 |  | 2026-05-23 | 2026-05-27 | Completed | Jwala Singh | 25
117 | AP155 | DD+0 | 42.226 |  | 2026-05-24 | 2026-06-04 | Completed | Vijay Bhagat-1 | 20
118 | 122/1 | DA+3 | 19.442 |  | 2026-05-25 | 2026-06-03 | Completed | Jirwa Devi | 26
119 | 144/3 | DA+3 | 19.442 |  | 2026-05-28 | 2026-05-31 | Completed | Jwala Singh | 25
120 | 136/4 | DA+3 | 19.442 |  | 2026-05-28 | 2026-06-02 | Completed | Vijay Bhagat-2 | 20
121 | 65/4 | DA+3 | 19.442 |  | 2026-05-28 | 2026-05-30 | Completed | Saritha Devi | 24
122 | AP66 | DC+0 | 32.223 |  | 2026-05-30 | 2026-06-04 | Completed | Saritha Devi | 24
123 | 142/1 | DA+0 | 18.34 |  | 2026-05-31 | 2026-06-03 | Completed | Jwala Singh | 25
124 | AP131 | DC+0 | 32.223 |  | 2026-06-02 | 2026-06-08 | Completed | Vijay Bhagat-2 | 20
125 | 71/1 | DA+3 | 19.442 |  | 2026-06-02 | 2026-06-10 | Completed | Spilce Net | 22
126 | AP82 | DD+3 | 44.071 |  | 2026-06-03 | 2026-06-15 | Completed | Lalman Mahato | 24
127 | AP132 | DC+9 | 41.843 |  | 2026-06-03 | 2026-06-13 | Completed | Jirwa Devi | 26
128 | AP142 | DD+0 | 42.226 |  | 2026-06-03 | 2026-06-10 | Completed | Jwala Singh | 25
129 | AP65 | DB+0 | 27.921 |  | 2026-06-04 | 2026-06-07 | Completed | Saritha Devi | 24
130 | AP150 | DC+0 | 32.223 |  | 2026-06-09 | 2026-06-13 | Completed | Vijay Bhagat-1 | 20
131 | AP137 | DC+3 | 33.53 |  | 2026-06-05 | 2026-06-12 | Completed | Vercycle | 22
132 | 65/1 | DA+0 | 18.34 |  | 2026-06-07 | 2026-06-11 | Completed | Saritha Devi | 24
133 | AP124 | DB+9 | 36.354 |  | 2026-06-08 | 2026-06-17 | Completed | Vijay Bhagat-2 | 20
134 | AP70/3 | DD+18 |  |  | 2026-06-10 | 2026-06-26 | Completed | Spilce Net | 22
135 | AP143 | DB+0 | 27.921 |  | 2026-06-10 | 2026-06-17 | Completed | Jwala Singh | 25
136 | 64/1 | DA+0 | 18.339 |  | 2026-06-11 | 2026-06-13 | Completed | Saritha Devi | 24
137 | 135/2 | DA+3 | 19.442 |  | 2026-06-12 | 2026-06-15 | Completed | Vercycle | 22
138 | AP60 | DB+6 | 34.578 |  | 2026-06-14 | 2026-06-18 | Completed | Saritha Devi | 24
139 | AP123 | DC+0 | 32.223 |  | 2026-06-14 | 2026-06-20 | Completed | Jirwa Devi | 26
140 | AP154 | DC+0 | 32.223 |  | 2026-06-16 | 2026-06-19 | Completed | Vijay Bhagat-1 | 20 |  | Dueto non availabilty of shut down gang idle for 2 days 14/6&15/6
141 | 80/1 | DB+3 | 29.492 |  | 2026-06-15 | 2026-06-22 | Completed | Lalman Mahato | 24
142 | AP76 | DC+9 | 41.843 |  | 2026-06-15 | 2026-06-21 | Completed | Vercycle | 22
143 | 59/1 | DA+3 | 19.442 |  | 2026-06-17 | 2026-06-22 | Completed | Saritha Devi | 24
144 | 144/2 | DA+0 | 18.339 |  | 2026-06-17 | 2026-06-21 | Completed | Jwala Singh | 25 |  | 0
145 | 139/1 | DA+3 | 19.442 |  | 2026-06-21 | 2026-06-25 | Completed | Jirwa Devi | 26
146 | AP71 | DC+9 | 41.843 |  | 2026-06-21 | 2026-06-29 | Completed | Saritha Devi | 24
147 | 144/1 | DA+3 | 19.442 |  | 2026-06-21 | 2026-06-25 | Completed | Jwala Singh | 25
148 | AP166 | DB+6 | 34.578 |  | 2026-06-21 | 2026-06-28 | Completed | Vijay Bhagat-1 | 20
149 | AP56 | DC+3 | 33.53 |  | 2026-06-23 | 2026-06-30 | Completed | Lalman Mahato | 24
150 | 138/1 | DA+0 | 18.339 |  | 2026-06-25 | 2026-06-29 | Completed | Jirwa Devi | 26
151 | 70/1 | DA+9 | 24.149 |  | 2026-06-26 | 2026-07-02 | Completed | Spilce Net | 22
152 | AP172 | DD+3 | 44.098 |  | 2026-06-28 | 2026-07-07 | Completed | Vijay Bhagat-1 | 20
153 | AP140 | DD+30 | 94.555 |  | 2026-06-29 | 2026-07-23 | Completed | Jirwa Devi | 26
154 | 55/1 | DA+6 | 22.684 |  | 2026-06-30 | 2026-07-07 | Completed | Lalman Mahato | 24
155 | AP52 | DD+30 | 94.555 |  | 2026-07-07 | 2026-08-09 | Completed | Lalman Mahato | 24
156 | 52/1 | DA+9 | 24.154 |  | 2026-08-10 |  | Material Shifting | Lalman Mahato | 24

## Vertical Chart -JS Line Punjab (hidden)
KEC INTERNATIONAL LIMITED
400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5-Punjab Portion
Vertical Chart
[9 empty] | Complete |  | 226 | 222 | 176 | 137 | 0
[9 empty] | WIP |  |  | 3 | 0 | 4 | 0
S.No | Tower | TOT | Angle of Deviation | Raised Chimney |  |  |  | FDN Classification | Span Length (Mtr) | Section Length (m) | ROW | Foundation | Earthing | Tower Erection | Tack Welding | Stringing | Remarks
|  |  |  | LEG A | LEG B | LEG C | LEG D
1 | AP53 | DC+0 | 29°2'38"RT |  |  |  |  | PS (SD) |  | 0 | Clear | C
416.658
2 | AP54 | DD+6 | 15°23'08"RT |  |  |  |  | PS (SD) |  | 416.658 | Clear | C
389.277
3 | AP55 | DD+3 | 38°18'51"RT |  |  |  |  | PS |  | 389.277 | Clear | C
384.151
4 | 55/1 | DA+6 | [5 empty] | PS (SD) |  | 384.151 | Clear | C | C
409.3
5 | AP56 | DC+3 | 25°53'58"RT |  |  |  |  | PS (SD) |  | 409.3 | Clear | C
409.72
6 | 56/1 | DA+6 | [7 empty] | 409.72
406.732
7 | 56/2 | DA+3 | [5 empty] | FS(PD) |  | 406.732 | Clear | C
404.913
8 | 56/3 | DA+6 | [5 empty] | PS (SD) |  | 404.913 | Clear | C | C
285.563
9 | 56/4 | DA+6 | [5 empty] | PS (SD) |  | 285.563 | Clear | C
399.174
10 | AP57 | DD+3 | 39°39'47"LT |  |  |  |  | PS(SD) |  | 399.174 | Clear | C
343.784
11 | 57/1 | DA+0 | [5 empty] | PS(SD) |  | 343.784 | Clear | C
313.063
12 | 57/2 | DA+0 | [5 empty] | PS(SD) |  |  | Clear | C
325.525
13 | AP58 | DC+0 | 24°19'0"RT |  |  |  |  | WET |  |  | Clear | C
406.443
14 | AP59 | DD+6 | 47°09'41"LT |  |  |  |  | PS(SD) |  |  | Clear | C
423.081
15 | 59/1 | DA+3 | [5 empty] | FS(PD) |  | 1468.112 | Clear | C |  | WIP
364.958
16 | AP60 | DB+6 | 8°29'30"LT |  |  |  |  | PS(SD) |  | 364.958 | Clear | C | C | C
380.949
17 | 60/1 | DA+0 | [5 empty] | PS(SD) |  | 380.949 | Clear | C | C
376.626
18 | AP61 | DC+0 | 21°54'40"RT |  |  |  |  | PS(SD) |  |  | Clear | C | C
299.077
19 | 61/1 | DA+0 | [5 empty] | PS(SD) |  |  | Clear | C | C
264.842
20 | AP62 | DB+0 | 4°52'18"RT |  |  |  |  | PS(SD) |  |  | Clear | WIP
364.064
21 | 62/1 | DA+0 | [5 empty] | PS(SD) |  |  | Clear | C
319.184
22 | 62/2 | DA+0 | [5 empty] | PS(SD) |  |  | Clear | C | C
397.985
23 | AP63 | DB+9 | 12°25'23"LT |  |  |  |  | PS(SD) |  | 1081.233 | Clear | C | C
450.859
24 | AP64 | DC+9 | 17°10'17"RT |  |  |  |  | PS(SD) |  |  | Clear | C | C
326.477
25 | 64/1 | DA+0 | [5 empty] | PS(SD) |  |  | Clear | C | C | C
276.363
26 | AP65 | DB+0 | 12°37'37"RT |  |  |  |  | PS(SD) |  | 602.84 | Clear | C |  | C
307.216
27 | 65/1 | DA+0 | [5 empty] | PS(SD) |  |  | Clear | C |  | C
389.397
28 | 65/2 | DA+6 | [5 empty] | PS(SD) |  |  | Clear | C | C
368.792
29 | 65/3 | DA+0 | [5 empty] | PS(SD) |  |  | Clear | C
404.386
30 | 65/4 | DA+3 | [5 empty] | PS(SD) |  |  | Clear | C |  | C
378.135
31 | 65/5 | DA+3 | [5 empty] | PS(SD) |  |  | Clear | C
370.482
32 | AP66 | DC+0 | 26°31'54"RT |  |  |  |  | WET |  |  | Clear | C | C | C
199.386
33 | AP67 | DD+0 | 42°51'4"LT |  |  |  |  | PS (SD) |  |  | Clear | C | C | C
294.009
34 | 67/1 | DA+0 | [5 empty] | PS (SD) |  |  | Clear | C | C | C
312.708
35 | 67/2 | DA+0 | [5 empty] | PS (SD) |  | 1959.106 | Clear | C | C
[9 empty] | 321.893 | [7 empty] | 66 KV H Pole Gurdaspur To Gahlari T/L
36 | 67/3 | DA+0 | [5 empty] | PS (SD) |  | 321.893 | Clear | C | C | C
382.475
37 | AP68 | DB+0 | 12°54'1"LT |  |  |  |  | PS (SD) |  |  | Clear | C | C | C
388.11
38 | AP69 | DB+0 | 5°21'56"RT |  |  |  |  | PS (SD) |  |  | Clear | C | C | C
382.675
39 | 69/1 | DA+0 | [5 empty] | FS |  | 1153.26 | Clear | C | C | C
390.446
40 | 69/2 | DA+0 | [5 empty] | FS |  | 390.446 | Clear | C | C | C
361.751
41 | 69/3 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
396.035
42 | AP70 | DC+3 | 28°33'28"RT |  |  |  |  | PS (SD) |  |  | Clear | C | C | C
435.862
43 | 70/1 | DA+9 | [5 empty] | PS (SD) |  | 435.862 | Clear | C | C
333.945
44 | 70/2 | DA+0 | [5 empty] | PS (SD) |  |  | Clear | C | C | C
502.836
45 | AP70/3 | DD+18 | 2°59'27"LT | 1 | 1 | 1 | 1 | PS (SD) |  |  | Clear | C |  | WIP
326.311
46 | AP71 | DC+9 | 17°25'49"LT |  |  |  |  | PS (SD) |  |  | Clear | C | C
415.29
47 | 71/1 | DA+3 | [5 empty] | PS (SD) |  |  | Clear | C |  | C
422.422
48 | 71/2 | DA+9 | [5 empty] | WET |  |  | Clear | C | C | C
418.373
49 | 71/3 | DA+6 | [5 empty] | WET |  |  | Clear | C |  | C
410.137
50 | AP72 | DB+3 | 1°09'23"LT |  |  |  |  | WET |  | 2829.314 | Clear | C | C | C
422.214
51 | 72/1 | DA+3 | [5 empty] | WET |  |  | Clear | C | C | C
387.357
52 | 72/2 | DA+6 | [5 empty] | WET |  |  | Clear | C |  | C
406.688
53 | AP74 | DB+0 | 12°51'59"LT |  |  |  |  | WET |  |  | Clear | C | C | C
316.253
54 | AP75 | DB+9 | 3°17'24"LT |  |  |  |  | FS |  |  | Clear | C | C | C
[9 empty] | 248.423 | [7 empty] | 66 KV D/C Gurdaspur To Jaura Chattran T/L N-H 354 GUDASPUR TO DERA BAB NANAK STON KM LEFT-183 RITE-182
55 | AP76 | DC+9 | 15°15'15"LT |  |  |  |  | PS |  |  | Clear | C
427.328
56 | 76/1 | DA+0 | [5 empty] | WET |  | 2208.263 | Clear | C | C | C
413.234
57 | 76/2 | DA+3 | [5 empty] | WET |  |  | Clear | C | C | C
414.719
58 | 76/3 | DA+3 | [5 empty] | WET |  |  | Clear | C | C | C
426.172
59 | AP77 | DB+3 | 4°28'22"LT |  |  |  |  | WET |  |  | Clear | C | C | C
404.81
60 | 77/1 | DA+3 | [5 empty] | WET |  |  | Clear | C | C | C
392.738
61 | 77/2 | DB+0 | [5 empty] | WET |  |  | Clear | C | C | C
391.939
62 | 77/3 | DA+9 |  | 1.5 | 1.5 | 1.5 | 1.5 | WET |  | 2443.612 | Clear | C |  |  |  |  | RC pending
440.91
63 | AP78 | DD+18 | 2°13'37"RT |  |  |  |  | PS |  |  | Clear | C
[9 empty] | 310.905 | [7 empty] | 132 KV S/C DHARIWAL-GURDASPUR
64 | AP79 | DD+9 | 33°52'12"LT |  |  |  |  | WET |  | 751.815 | Clear | C | C | C
[9 empty] | 240.527 | [7 empty] | NH-54 AMRITSAR TO GURDASPUR STON KM LEFT-41 RITE-42
65 | AP80 | DD+0 | 52°58'23"RT |  |  |  |  | PS |  |  | Clear | C | C | C
389
66 | 80/1 | DB+3 | [5 empty] | WET |  |  | Clear | C | C
468.318
67 | AP81 | DD+9 | 45°25'14"LT |  |  |  |  | FS |  | 1097.845 | Clear | C
[9 empty] | 242.663 | [7 empty] | SINGLE LINE RAIL WAY TRACK EP NO-62/9 EP NO-62/8 (Non Electrified)
68 | AP82 | DD+3 | 36°50'39"RT |  |  |  |  | FS |  |  | Clear | C |  | C
408.258
69 | 82/1 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
337.476
70 | 82/2 | DA+3 | [5 empty] | WET |  |  | Clear | C | C | C
403.418
71 | AP83 | DD+25 | 0°34'37"LT | 2 | 2 | 2 | 2 | PS |  | 740.894 | Clear | C
[9 empty] | 251.516 | [7 empty] | 220 KV D/C Sohal TES to Tibber Transmission Line
72 | AP84 | DD+18 | 3°10'24"RT | 2 | 2 | 2 | 2 |  |  | 251.516 | Clear | C
445.126
73 | AP85 | DB+0 | 2°22'29"RT |  |  |  |  | WET |  |  | Clear | C | C | C
387.7
74 | 85/1 | DA+9 | [5 empty] | WET |  |  | Clear | C | C
449.348
75 | AP86 | DC+0 | 14°12'50"LT |  |  |  |  | WET |  | 1282.174 | Clear | C | C
408.793
76 | 86/1 | DA+3 | [5 empty] | WET |  |  | Clear | C | C | C
425.487
77 | AP87 | DB+9 | 7°9'8"RT |  |  |  |  | PS |  | 834.28 | Clear | C | C
386.799
78 | 87/1 | DA+3 | [8 empty] | ROW
380.77
79 | 87/2 | DA+3 | [5 empty] | WET |  |  | Clear | C | C | C
421.314
80 | AP88 | DD+18 | 28°53'35"LT |  |  |  |  | PS |  | 1188.883 | Clear | C
[9 empty] | 211.063 | [7 empty] | 220 KV D/C Wadala Grinthian To Sarna CKT-4, 220 KV D/C Wadala Grinthian To Tibber CKT-3
81 | AP89 | DD+25 | 31°35'10"RT |  |  |  |  | PS |  |  | Clear | C
385.103
82 | 89/1 | DA+3 | [5 empty] | WET |  |  | Clear | C | C | C
233.126
83 | AP90 | DD+0 | 40°23'13"LT |  |  |  |  | WET |  |  | Clear | C | C | C
411.24
84 | 90/1 | DA+3 | [5 empty] | WET |  | 1240.532 | Clear | C |  | C
320.979
85 | 90/2 | DA+0 | [5 empty] | WET |  | 320.979 | Clear | C | C | C
448.791
86 | AP91 | DD+25 | 11°45'19"RT |  |  |  |  | PS |  |  | Clear | C | C
[9 empty] | 247.685 | [7 empty] | 220 KV D/C Sarna To Wadala Granthian T/L
87 | AP92 | DD+25 | 34°8'24"RT |  |  |  |  | PS |  |  | Clear | C | C
360.878
88 | 92/1 | DA+3 | [5 empty] | WET |  |  | Clear | C | C | C
415.643
89 | 92/2 | DA+6 | [5 empty] | WET |  | 1472.997 | Clear | C |  | C
379.751
90 | 92/3 | DA+0 | [5 empty] | WET |  |  | Clear | C |  | C
298.884
91 | AP93 | DC+0 | 18°20'38"RT |  |  |  |  | WET |  |  | Clear | C | C | C
314.664
92 | 93/1 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
301.757
93 | 93/2 | DA+0 | [5 empty] | WET |  |  | Clear | C |  | C
272.654
94 | AP94 | DB+0 | 0°29'54"RT |  |  |  |  | WET |  | 1567.71 | Clear | C | C | C
411.542
95 | AP95 | DC+3 | 19°44'06"LT |  |  |  |  | WET |  |  | Clear | C | C | C
375.054
96 | 95/1 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
357.801
97 | 95/2 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
338.209
98 | 95/3 | DA+0 | [5 empty] | WET |  | 1482.606 | Clear | C | C | C
358.793
99 | 95/4 | DA+0 | [5 empty] | WET |  | 2114.053 | Clear | C | C | C
321.162
100 | AP96 | DC+0 | 21°39'03"LT |  |  |  |  | WET |  |  | Clear | C | C | C
243.936
101 | AP97 | DD+3 | 31°16'41"RT |  |  |  |  | WET |  | 923.891 | Clear | C | C | C
406.692
102 | 97/1 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
387.95
103 | 97/2 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
401.317
104 | 97/3 | DA+3 | [5 empty] | WET |  | 2119.85 | Clear | C | C | C
419.636
105 | AP98 | DB+3 | 3°04'27"LT |  |  |  |  | WET |  |  | Clear | C | C | C
369.141
106 | 98/1 | DA+3 | [5 empty] | WET |  |  | Clear | C | C | C
280.435
107 | AP99 | DB+0 | 5°27'41"RT |  |  |  |  | WET |  | 2265.171 | Clear | C | C | C
392.603
108 | 99/1 | DA+9 | [5 empty] | WET |  |  | Clear | C | C | C
384.166
109 | AP100 | DC+3 | 22°17'08"LT |  |  |  |  | WET |  |  | Clear | C | C | C
408.003
110 | AP101 | DC+0 | 26°08'26"RT | [7 empty] | ROW
390.238
111 | AP102 | DB+0 | 11°0'39"LT |  |  |  |  | WET |  | 1575.01 | Clear | C | C | C
360.683
112 | 102/1 | DA+6 | [5 empty] | WET |  | 360.683 | Clear | C | C
350.527
113 | AP103 | DD+0 | 34°17'09"LT |  |  |  |  | WET |  | 350.527 | Clear | C | C | C
380.322
114 | 103/1 | DA+0 | [5 empty] | WET |  | 380.322 | Clear | C | C | C
331.6
115 | AP104 | DB+0 | 5°25'28"LT |  |  |  |  | WET |  |  | Clear | C | C | C
406.096
116 | 104/1 | DA+3 | [5 empty] | WET |  |  | Clear | C | C | C
313.788
117 | AP105 | DD+3 | 33°19'08"RT | 1 | 1 | 1 | 1 | WET |  |  | Clear | C
413.223
118 | AP106 | DD+6 | 32°25'19"LT |  |  |  |  | WET |  |  | Clear | C | C | C
297.539
119 | 106/1 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
283.671
120 | AP107 | DB+0 | [8 empty] | ROW
378.12
121 | AP108 | DD+25 | 42°31'57"LT |  |  |  |  | PS |  |  | Clear | C | C
[9 empty] | 249.176 | [7 empty] | 800 KV S/C Kishenpur-Moga Transmission line CKT-1
122 | AP109 | DD+30 | 42°18'19"RT |  |  |  |  | PS |  |  | Clear | C | C
198.719
123 | AP110 | DD+0 | 37°33'29"RT |  |  |  |  | WET |  |  | Clear | C | C
287.047
124 | AP111 | DC+0 | 22°58'26"RT |  |  |  |  | WET |  |  | Clear | C | C | C
317.654
125 | AP112 | DD+30 | 48°59'48"RT |  |  |  |  | PS |  | 3476.633 | Clear | C | C
[9 empty] | 245.547 | [7 empty] | 800 KV S/C Kishenpur-Moga Transmission line CKT-1
126 | AP113 | DD+25 | 53°39'13"LT |  |  |  |  | PS |  |  | Clear | C | C
342.986
127 | AP114 | DB+0 | [5 empty] | WET |  |  | Clear | C | C | C
384.064
128 | AP115 | DB+0 | 10°13'52"LT |  |  |  |  | WET |  |  | Clear | C | C | C
373
129 | 115/1 | DA+6 | [5 empty] | WET |  |  | Clear | C | C | C
[9 empty] | 378 | [7 empty] | 66 kV H-Pole Power Line Qadian to Bharth (CL- 13.300 m)
130 | AP116 | DCT+0 | [5 empty] | FS |  |  | Clear | C | C
283
131 | 116/1 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
232.015
132 | AP117 | DB+0 | 3°36'30"RT |  |  |  |  | WET |  |  | Clear | C | C | C
323.186
133 | 117/1 | DA+0 | [5 empty] | WET |  |  | Clear | C |  | C
351.475
134 | 117/2 | DA+3 | [5 empty] | WET |  |  | Clear | C | C | C
368.874
135 | 117/3 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
366.147
136 | AP118 | DC+0 | 16°09'46"LT |  |  |  |  | WET |  |  | Clear | C | C | C
326.21
137 | 118/1 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
308.149
138 | AP119 | DC+0 | 26°16'41"LT
285.935
139 | 119/1 | DA+0
232.238
140 | AP120 | DD+0 | 42°02'04"RT
396.913
141 | 120/1 | DA+3
412.767
142 | 120/2 | DA+6
402.69
143 | AP121 | DC+3 | 19°30'25"LT
374.133
144 | 121/1 | DA+0
377.376
145 | 121/2 | DA+0
385.349
146 | AP122 | DB+0 | 4°36'22"LT
395.252
147 | 122/1 | DA+3 | [5 empty] | WET |  |  | Clear | C | C | C
358.294
148 | AP123 | DC+0 | 18°24'26"RT |  |  |  |  | WET |  |  | Clear | C | C | WIP
[9 empty] | 426.276 | [7 empty] | 132 KV S/C LINE Power Wadala to Hargobindpur (CL- 9.2 M)
149 | AP124 | DB+9 | 04°41'01"RT |  |  |  |  | PS |  |  | Clear | C |  | C
217.161
150 | AP125 | DD+18 | 31°42'07"LT |  |  |  |  | PS |  |  | Clear | C | C
425.244
151 | AP126 | DB+ 0 | [5 empty] | WET |  |  | Clear | C | C
373.291
152 | AP127 | DD+30 | 28°54'28"LT | 2 | 2 | 2 | 2 | PS |  |  | Clear | C | C
[9 empty] | 240.81 | [7 empty] | 800 KV S/C Power LINE Kishanpur to Moga (CL- 9.300 M)
153 | AP128 | DD +30 | 44°0'03"RT | 2 | 2 | 2 | 2 | PS |  |  | Clear | C | C
501.813
154 | AP129 | DB+9 | 8°06'53"RT |  |  |  |  | PS |  |  | Clear | C | C | C
[9 empty] | 244.068 | [7 empty] | 132 KV S/C Power Line Wadala to Hargobindpur (CL -7.1 m)
155 | AP130 | DD+18 | 7°08'11"RT |  |  |  |  | PS |  |  | Clear | C | C
387.815
156 | 130/1 | DA +0 | [5 empty] | WET |  |  | Clear | C | C | C
303.927
157 | 130/2 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
158 | AP131 | DC +0 | 22°30'33"LT |  |  |  |  | WET |  |  | Clear | C | C | C
407.946
159 | 131/1 | DA+3 | [5 empty] | WET |  |  | Clear | C | C | C
429.847
160 | 131/2 | DA+3 | [5 empty] | WET |  |  | Clear | C | C | C
407.778
161 | 131/3 | DA+3 | [5 empty] | WET |  |  | Clear | C | C | C
416.733
162 | 131/4 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
421.345
163 | 131/5 | DA+3 | [5 empty] | WET |  |  | Clear | C | C | C
385.64
164 | 131/6 | DA+9 | [5 empty] | WET |  |  | Clear | C | C | C
[9 empty] | 372.699 | [7 empty] | 66 Kv H-Pole Power Line Crossing Ghoman to Shri Hargobindpur (CL- 6.100 m)
165 | AP132 | DC+9 | 28°22'39"RT | 1.5 | 1.5 | 1.5 | 1.5 | WET |  |  | Clear | C | C | C
407.912
166 | 132/1 | DA+3 | [5 empty] | WET |  |  | Clear | C | C | C
408.165
167 | AP133 | DC+6 | 18°40'20"LT
[9 empty] | 227.366 | [7 empty] | NHAI 503A Amritsar-Bathinda (CL- 19.400 M) ,NALA,11kV
168 | AP134 | DB+3 | 2°30'44"RT | [7 empty] | Clear
401.366
169 | AP135 | DB+3 | 12°42'21"RT |  |  |  |  | WET |  |  | Clear | C | C | C
403.064
170 | 135/1 | DA+6 | [5 empty] | WET |  |  | Clear | C | C | C
398.933
171 | 135/2 | DA+3 | [5 empty] | WET |  |  | Clear | C | C | C
419.905
172 | AP136 | DC+3 | 18°07'48"LT |  |  |  |  | WET |  |  | Clear | C | C | C
373.389
173 | 136/1 | DA+3 | [5 empty] | WET |  |  | Clear | C | C | C
419.813
174 | 136/2 | DA+3 | [5 empty] | WET |  |  | Clear | C | C | C
410.049
175 | 136/3 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
415.171
176 | 136/4 | DA+3 | [5 empty] | WET |  |  | Clear | C | C | C
381.971
177 | AP137 | DC+3 | 28°54'25"RT |  |  |  |  | WET |  |  | Clear | C | C | C
377.623
178 | 137/1 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
354.138
179 | 137/2 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
305.826
180 | AP138 | DD+0 | 31°45'48"LT |  |  |  |  | WET |  |  | Clear | C | C
320.987
181 | 138/1 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
329.946
182 | 138/2 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
294.041
183 | AP139 | DB+0 | 5°55'30"LT |  |  |  |  | WET |  |  | Clear | C
381.669
184 | 139/1 | DA+3 | [5 empty] | WET |  |  | Clear | C | C
427.453
185 | AP140 | DD+30 | 29°55'22"LT |  |  |  |  | FS |  |  | Clear | WIP
AP140-AP142( Survey Submission/Aprroval Pending)
186 | AP142 | DD+0 | 31°09'11"RT | 1 | 1 | 1 | 1 | PS(SD) |  |  | Clear | C | C | C
392.505
187 | 142/1 | DA+0 |  | 1 | 1 | 1 | 1 | PS(SD) |  |  | Clear | C | C | C
392.67
188 | AP143 | DB+0 | 9°07'39"RT | 1 | 1 | 1 | 1 | PS(SD) |  |  | Clear | C | C | C
292.264
189 | 143/1 | DA+0 |  | 1.5 | 1.5 | 1.5 | 1.5 |  |  |  | Clear | C | C
321.587
190 | 143/2 | DA+0 |  | 1 | 1 | 1 | 1 | PS(SD) |  |  | Clear | C
363.882
191 | AP144 | DB +0 | 6°57'45"LT |  |  |  |  | PS(SD) |  |  | Clear | C | C
369.226
192 | 144/1 | DA+3 | [5 empty] | PS(SD) |  |  | Clear | C
380.673
193 | 144/2 | DA+0 | [5 empty] | PS(SD) |  |  | Clear | C |  | WIP
385.667
194 | 144/3 | DA+6 | [5 empty] | PS(SD) |  |  | Clear | C | C | C
380.896
195 | 144/4 | DA+0 | [5 empty] | PS(SD) |  |  | Clear | C | C | C
391.349
196 | AP145 | DB+0 | 13°54'59"RT |  |  |  |  | PS(SD) |  |  | Clear | C | C | C
330.493
197 | 145/1 | DA+0 | [5 empty] | PS(SD) |  |  | Clear | C | C | C
342.106
198 | 145/2 | DA+3 | [5 empty] | PS |  |  | Clear | C | C | C
394.284
199 | AP146 | DC+0 | 29°42'51"LT |  |  |  |  | WET |  |  | Clear | C | C | C
245.679
200 | AP147 | DB+0 | [5 empty] | WET |  |  | Clear | C | C | C
352.93
201 | AP148 | DD+25 | 51°9'48"RT | 2 | 2 | 2 | 2 | PS |  |  | Clear | C | C
[9 empty] | 232.301 | [7 empty] | 400kv BN-ASR TRANSMISSION LINE(CL-7.0m)
202 | AP149 | DD+25 | 22°39'7"LT |  |  |  |  | PS |  |  | Clear | C | C
474.983
203 | AP150 | DC+0 | 24°16'48"LT |  |  |  |  | WET |  |  | Clear | C | C
322.588
204 | 150/1 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
317.884
205 | 150/2 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
297.735
206 | AP151 | DC+0 | 24°58'4"RT |  |  |  |  | WET |  |  | Clear | WIP
357.249
207 | 151/1 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
353.033
208 | 151/2 | DA+3 | [5 empty] | WET |  |  | Clear | C | C | C
406.766
209 | AP152 | DD+0 | 39°38'36"LT |  |  |  |  | WET |  |  | Clear | C | C
392.395
210 | 152/1 | DA+3 | [5 empty] | WET |  |  | Clear | C | C | C
408.835
211 | 152/2 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
333.09
212 | 152/3 | DA+0 |  | 1 | 1 | 1 | 1 | PS |  |  | Clear | C | C | C
343.683
213 | 152/4 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
383.599
214 | AP153 | DC+0 | 23°26'55"RT |  |  |  |  | WET |  |  | Clear | C | C | C
282.759
215 | 153/1 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
385.271
216 | 153/2 | DA+3 | [5 empty] | WET |  |  | Clear | C | C | C
361.361
217 | AP154 | DC+0 | 29°57'53"LT |  |  |  |  | WET |  |  | Clear | C | C | C
235.09
218 | AP155 | DD+0 | 34°42'34"RT |  |  |  |  | WET |  |  | Clear | C | C | C
351.743
219 | 155/1 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
386.038
220 | 155/2 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
387.695
221 | 155/3 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
389.568
222 | AP156 | DC+0 | 16°34'55"LT |  |  |  |  | WET |  |  | Clear | C | C | C
376.144
223 | 156/1 | DA+6 | [5 empty] | WET |  |  | Clear | C | C | C
408
224 | 156/2 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
365.413
225 | 156/3 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
280.471
226 | 156/4 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
305.689
227 | AP157 | DB+0 | 3°55'39"LT |  |  |  |  | WET |  |  | Clear | C | C | C
363.359
228 | 157/1 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
428.543
229 | AP158 | DD+9 | 36°59'34"RT |  |  |  |  | PS |  |  | Clear | C | C
[9 empty] | 223.002 | [7 empty] | 220kV S/C BBMB jalandhar to Butari(CL-6.3m)
230 | AP159 | DD+18 | 5°51'30"LT |  |  |  |  | PS |  |  | Clear | C | C
433.784
231 | 159/1 | DA+0 | [5 empty] | WET |  |  | Clear | C
377.777
232 | 159/2 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
375.892
233 | 159/3 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
394.944
234 | AP161 | DD+9 | 11°43'56"LT |  |  |  |  | WET |  |  | Clear | C | C
[9 empty] | 237.641 | [7 empty] | 400kV S/C ASR TO JAL T/L (CL-7.9m)
235 | AP162 | DD+18 | 32°22'36"RT |  |  |  |  | PS |  |  | Clear | C | C
222.608
236 | AP163 | DB+6 | 4°06'44"LT |  |  |  |  | WET |  |  | Clear | C
[9 empty] | 201.442 | [7 empty] | 132kV S/C, Kartarpur to Rayia(CL-8.1m)
237 | AP164 | DB+9 | 7°26'35"LT
[9 empty] | 228.755 | [7 empty] | 132kV S/C Jalandhar to Dhilwan Line
238 | AP165 | DB+6 | 1°0'33"LT | 1 | 1 | 1 | 1 | FS |  |  | Clear | C | C
[9 empty] | 241.171 | [7 empty] | NH-1(AMRITSAR-DELHI) (CL-12.3m)
239 | AP166 | DB+6 | 7°22'22"RT | 2 | 2 | 2 | 2 | FS |  |  | Clear | C | C
265.922
240 | AP167 | DD+9 | 0°43'25"RT |  |  |  |  | FS |  |  | Clear | C
[9 empty] | 215.817 | [7 empty] | RAILWAY CROSSING (CL-21.8m) &2 nos -11 kv line
241 | AP168 | DD+9 | 5°57'13"LT | [7 empty] | Clear | C
84.9301

## Sheet9 (hidden)
S.No | Loc | TOT | Classification | Start Date | End Darte | JMC
1 | 153/0 | DC+0 | WET | 2026-01-17 | 2026-02-05 | 105 | OK
2 | AP139 | DB+0 | WET | 2026-01-20 | 2026-02-06 | 106 | OK
3 | 151/2 | DA+3 | WET | 2026-02-03 | 2026-02-07 | 107 | OK
4 | AP97 | DD+3 | WET | 2026-01-29 | 2026-02-08 | 108 | OK
5 | AP155 | DD+0 | WET | 2026-01-31 | 2026-02-09 | 109 | OK
6 | 136/2 | DA+3 | WET | 2026-01-22 | 2026-02-11 | 110 | OK
7 | AP130 | DD+18 | PS | 2026-01-18 | 2026-02-12 | 111 | OK
8 | 152/4 | DA+0 | WET | 2026-02-04 | 2026-02-12 | 112 | OK
9 | AP92 | DD+25 | PS | 2026-01-21 | 2026-02-13 | 113 | OK | 104
10 | 153/1 | DA+0 | WET | 2026-02-06 | 2026-02-13 | 114 | OK
11 | AP156 | DC+0 | WET | 2026-02-05 | 2026-02-14 | 115 | OK
12 | 136/3 | DA+0 | WET | 2026-02-09 | 2026-02-15 | 116 | OK
13 | 157/1 | DA+0 | WET | 2026-02-09 | 2026-02-15 | 117 | OK
14 | 72/1 | DA+3 | WET | 2026-02-14 | 2026-02-17 | 118 | OK
15 | AP150 | DC+0 | WET | 2026-02-09 | 2026-02-18 | 119 | OK
16 | AP70 | DC+3 | PS(SD) | 2026-02-10 | 2026-02-18 | 120 | OK
17 | 153/2 | DA+3 | WET | 2026-02-13 | 2026-02-18 | 121 | OK
18 | AP111 | DC+0 | WET | 2026-02-06 | 2026-02-19 | 122 | OK
19 | 136/4 | DA+3 | WET | 2026-02-12 | 2026-02-20 | 123 | OK
20 | 70/2 | DA+0 | PS(SD) | 2026-02-05 | 2026-02-21 | 124 | OK
21 | AP68 | DB+0 | PS(SD) | 2026-02-10 | 2026-02-21 | 125 | OK
22 | AP132 | DC+9 1.5m RC | WET | 2026-02-15 | 2026-02-24 | 126 | OK
23 | AP79 | DD+9 | WET | 2026-02-15 | 2026-02-25 | 127 | OK
24 | 67/3 | DA+0 | PS (SD) | 2026-02-19 | 2026-02-26 | 128 | OK
25 | 70/1 | DA+9 | PS (SD) | 2026-02-22 | 2026-02-26 | 129 | OK
26 | AP91 | DD+25 | WET | 2026-02-12 | 2026-02-27 | 130 | OK
27 | AP137 | DC+3 | WET | 2026-02-15 | 2026-02-27 | 131 | OK
28 | AP159 | DD+18 | PS | 2026-02-19 | 2026-02-28 | 132 | OK
29 | 145/1 | DA+0 | PS (SD) | 2026-02-21 | 2026-02-28 | 133 | OK
30 | AP114 | DB+0 | WET | 2026-02-21 | 2026-02-28 | 134 | OK
31 | 71/2 | DA+9 | WET |  |  | 135 | OK
32 | 69/0 |  |  | 2026-02-24 | 2026-03-01 | 136 | OK
S.No | Loc | TOT | Classification | Start Date | End Darte | JMC
1 | AP148 | DD+25 2MRC | PS | 2026-02-19 | 2026-03-16 | 140
2 | AP149 | DD+25 | PS | 2026-02-21 | 2026-03-10 | 137
3 | 67/2 | DA+0 | PS (SD) | 2026-03-04 | 2026-03-13 | 138 | OK
4 | AP71 | DC+9 | PS (SD) | 2026-03-03 | 2026-03-23 | 143 | OK
5 | AP152 | DD+0 | WET | 2026-02-28 | 2026-03-26 | 145
6 | AP127 | DD+30 2MRC | PS | 2026-03-01 | 2026-03-15 | 139
7 | AP145 | DB+0 | PS (SD) | 2026-03-01 | 2026-03-25 | 144
8 | AP136 | DC+3 | WET | 2026-03-02 | 2026-03-18 | 141
9 | 67/1 | DA+0 | PS(SD) | 2026-03-13 | 2026-03-19 | 142 | OK
10 | AP108 | DD+25 | PS | 2026-03-01 | 2026-03-28 | 146 | OK

## ROW Front vs Progress (hidden)
S.No | Line | ROW Clearence Work Front | Completed | WIP | Balance
1 | Samba-Jalandhar (Jammu Portion) | 95 | 84 | 7 | 4
2 | Samba-Jalandhar (Punjab Portion) | 181 | 158 | 10 | 13
3 | Samba-Kishenpur | 56 | 46 | 7 | 3
4 | LILO-Kishtwar | 4 |  | 3 | 1
Total |  | 336 | 288 | 27 | 21
|  | 2026-03-17 | 3

## Foundation -JS Line- Punjab
KEC International Ltd | [13 empty] | Date: | 2026-08-11
400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5-Punjab Portion
FOUNDATION
S.No | Loc No. | Tower Type | Classification | Conc Volume | Start Date | Foundation |  |  |  |  | Completion Date | FDN Status | Earthing | Gang Name | Gang Strength | Remark
[6 empty] | Excavation | Stub Setting | PCC | Rebar Placing | RCC
1 | 90/1 | DA+3 | WET | 36.109 | 2025-09-25 | 2026-01-11 | 2026-01-11 | 2026-01-11 | 2026-01-11 | 2026-01-11 | 2026-01-11 | Completed |  | Anchal Singh | 25 | 3 pits casting completed on 24.10.25. After clearence of ROW on 09.01.26, Work resumed since 10.01.26 in the 4th pit and work completed on 11.01.26
2 | 117/1 | DA+0 | WET |  | 2025-10-13 | 2025-10-18 | 2025-10-18 | 2025-10-19 | 2025-10-19 | 2025-10-20 | 2025-10-20 | Completed |  | Sakrala Material | 10
3 | 92/3 | DA+0 | WET |  | 2025-10-16 | 2025-10-25 | 2025-10-25 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-27 | Completed |  | MS Constructions | 9
4 | 92/2 | DA+6 | WET |  | 2025-10-19 | 2025-10-25 | 2025-10-27 | 2025-10-27 | 2025-10-28 | 2025-10-28 | 2025-10-28 | Completed |  | MS Constructions | 10
5 | 71/3 | DA+6 | WET |  | 2025-10-17 | 2025-10-19 | 2025-10-20 | 2025-10-20 | 2025-10-21 | 2025-10-23 | 2025-10-23 | Completed |  | Ramesh | 12
6 | 72/2 | DA+6 | WET |  | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-25 | 2025-10-26 | 2025-10-28 | 2025-10-28 | Completed |  | Ramesh | 12
7 | 117/3 | DA+0 | WET |  | 2025-10-23 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-29 | 2025-10-29 | 2025-10-29 | Completed | 2025-11-04 | Sakrala Material | 10
8 | 74/0 | DB+0 | WET |  | 2025-10-25 | 2025-10-27 | 2025-10-31 | 2025-10-31 | 2025-11-01 | 2025-11-06 | 2025-11-06 | Completed | 2025-11-12 | Ramesh | 16
9 | 72/0 | DB+3 | WET |  | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-09 | 2025-11-09 | Completed | 2025-11-12 | Ramesh
10 | 89/1 | DA+3 | WET |  | 2025-10-26 | 2025-10-30 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | Completed | 2025-11-07 | Anchal Singh | 23
11 | 93/1 | DA+0 | WET |  | 2025-10-27 | 2025-10-28 | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-31 | 2025-10-31 | Completed | 2025-11-09 | MS Constructions | 19
12 | 117/2 | DA+3 | WET |  | 2025-10-26 | 2025-10-28 | 2025-11-01 | 2025-11-01 | 2025-11-02 | 2025-11-04 | 2025-11-04 | Completed | 2025-11-06 | Sakrala Material | 20
13 | 118/1 | DA+0 | WET |  | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-06 | 2025-11-06 | Completed | 2025-11-08 | Sakrala Material
14 | 95/2 | DA+0 | WET |  | 2025-10-29 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-06 | 2025-11-08 | 2025-11-08 | Completed | 2025-11-09 | Ikrar/MS Hussain | 13
15 | 95/3 | DA+0 | WET |  | 2025-10-31 | 2025-11-08 | 2025-11-09 | 2025-11-09 | 2025-11-09 | 2025-11-10 | 2025-11-10 | Completed | 2025-11-11 | Ikrar/MS Hussain
16 | 93/2 | DA+0 | WET |  | 2025-10-29 | 2025-10-30 | 2025-11-02 | 2025-11-02 | 2025-11-02 | 2025-11-04 | 2025-11-04 | Completed |  | MS Constructions | 19
17 | 92/1 | DA+3 | WET |  | 2025-11-03 | 2025-11-07 | 2025-11-09 | 2025-11-09 | 2025-11-10 | 2025-11-10 | 2025-11-10 | Completed | 2025-11-14 | MS Constructions
18 | 97/2 | DA+0 | WET |  | 2025-10-30 | 2025-11-02 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-12 | 2025-11-12 | Completed | 2025-11-16 | Md. Latif | 25
19 | 97/1 | DA+0 | WET |  | 2025-11-02 | 2025-11-06 | 2025-11-10 | 2025-11-11 | 2025-11-11 | 2025-11-13 | 2025-11-13 | Completed | 2025-11-16 | Md. Latif
20 | AP90 | DD+0 | WET |  | 2025-11-01 | 2025-11-17 | 2025-11-18 | 2025-11-18 | 2025-11-20 | 2025-11-22 | 2025-11-22 | Completed | 2025-11-19 | Anchal Singh | 25
21 | AP118 | DC+0 | WET |  | 2025-11-07 | 2025-11-12 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-16 | 2025-11-16 | Completed | 2025-11-19 | Sakrala Material | 20
22 | 131/1 | DA+3 | WET |  | 2025-11-06 | 2025-12-12 | 2025-12-12 | 2025-11-14 | 2025-11-14 | 2025-11-15 | 2025-11-15 | Completed | 2025-11-21 | TCC Construction | 16
23 | 95/1 | DA+0 | WET |  | 2025-11-09 | 2025-11-13 | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-15 | 2025-11-15 | Completed | 2025-11-16 | Ikrar/MS Hussain | 20
24 | AP93 | DC+0 | WET |  | 2025-11-10 | 2025-11-17 | 2025-11-18 | 2025-11-18 | 2025-11-18 | 2025-11-19 | 2025-11-19 | Completed | 2025-12-01 | MS Constructions | 19
25 | 76/2 | DA+3 | WET |  | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-14 | 2025-11-14 | Completed | 2025-11-15 | Ramesh | 16
26 | 97/3 | DA+3 | WET |  | 2025-11-11 | 2025-11-12 | 2025-11-15 | 2025-11-18 | 2025-11-18 | 2025-11-20 | 2025-11-20 | Completed | 2025-11-21 | Md. Latif | 25
27 | AP98 | DB+3 | WET |  | 2025-11-12 | 2025-11-19 | 2025-11-21 | 2025-11-21 | 2025-11-23 | 2025-11-24 | 2025-11-24 | Completed | 2025-12-01 | Md. Latif
28 | 95/4 | DA+0 | WET |  | 2025-11-13 | 2025-11-18 | 2025-11-19 | 2025-11-19 | 2025-11-20 | 2025-11-20 | 2025-11-20 | Completed | 2025-11-21 | Ikrar | 11
29 | 76/1 | DA+0 | WET |  | 2025-11-14 | 2025-11-15 | 2025-11-15 | 2025-11-16 | 2025-11-16 | 2025-11-18 | 2025-11-18 | Completed | 2025-11-19 | Ramesh | 16
30 | 131/3 | DA+3 | WET |  | 2025-11-15 | 2025-11-16 | 2025-11-18 | 2025-11-18 | 2025-11-19 | 2025-11-19 | 2025-11-19 | Completed | 2025-11-21 | TCC Construction | 16
31 | AP116 | DCT+0 | FS |  | 2025-11-16 | 2025-11-27 | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-11-30 | 2025-11-30 | Completed | 2025-12-01 | Sakrala Material | 20
32 | AP96 | DC+0 | WET |  | 2025-11-17 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-29 | Completed | 2025-12-01 | MS Hussain | 12
33 | AP77 | DB+3 | WET |  | 2025-11-18 | 2025-12-10 | 2025-12-11 | 2025-12-11 | 2025-12-11 | 2025-12-13 | 2025-12-13 | Completed | 2025-12-14 | Ramesh | 16 | 2 pits casting completed on 22.11.2025 Balance 2 pits under ROW till 08.12.2025 Work resumed from 09.12.2025 & Completed on 13.12.25
34 | 131/2 | DA+3 | WET |  | 2025-11-19 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-23 | 2025-11-24 | 2025-11-24 | Completed | 2025-11-26 | TCC Construction | 16
35 | AP94 | DB+0 | WET |  | 2025-11-20 | 2025-11-24 | 2025-11-25 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-27 | Completed | 2025-12-05 | MS Constructions | 19
36 | 98/1 | DA+3 | WET |  | 2025-11-20 | 2025-11-23 | 2025-11-25 | 2025-11-25 | 2025-11-26 | 2025-11-26 | 2025-11-26 | Completed | 2025-11-26 | Md. Latif | 12
37 | 103/1 | DA+0 | WET |  | 2025-11-22 | 2025-11-26 | 2025-11-27 | 2025-11-27 | 2025-11-28 | 2025-11-28 | 2025-11-28 | Completed | 2025-11-28 | Ikrar | 11
38 | 131/4 | DA+0 | WET |  | 2025-11-22 | 2025-11-27 | 2025-11-28 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-11-30 | Completed | 2025-12-01 | TCC Construction | 16
39 | AP87 | DB+9 | PS |  | 2025-11-21 | 2025-11-27 | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-11-30 | 2025-11-30 | Completed | 2025-12-03 | Anchal Singh | 25
40 | AP99 | DB+0 | WET |  | 2025-11-23 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-28 | 2025-11-30 | 2025-11-30 | Completed | 2025-12-10 | Md. Latif | 15
41 | AP75 | DB+9 | FS |  | 2025-11-25 | 2025-11-28 | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-12-01 | 2025-12-01 | Completed | 2025-12-01 | Ramesh | 16
42 | 82/2 | DA+3 | WET |  | 2025-11-26 | 2025-12-02 | 2025-12-03 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-05 | Completed | 2025-12-08 | Anchal Singh | 25
43 | AP100 | DC+3 | WET |  | 2025-11-26 | 2025-12-03 | 2025-12-05 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-07 | Completed | 2025-12-10 | Md. Latif | 13
44 | AP117 | DB+0 | WET |  | 2025-11-29 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-06 | 2205-12-09 | 2025-12-09 | Completed | 2025-12-09 | Sakrala Material | 20
45 | AP95 | DC+3 | WET |  | 2025-11-29 | 2025-12-05 | 2025-12-05 | 2025-12-06 | 2025-12-06 | 2025-12-07 | 2025-12-07 | Completed | 2025-12-07 | MS Constructions | 19
46 | 104/1 | DA+3 | WET |  | 2025-11-30 | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-04 | 2025-12-04 | 2025-12-04 | Completed | 2025-12-05 | MS Hussain | 12
47 | AP103 | DD+0 | WET |  | 2025-12-02 | 2025-12-15 | 2025-12-16 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-18 | Completed | 2025-12-12 | Ikrar | 11
48 | 99/1 | DA+9 | WET |  | 2025-12-01 | 2025-12-03 | 2025-12-05 | 05-12-205 | 2025-12-05 | 2025-12-06 | 2025-12-06 | Completed | 2025-12-11 | Md. Latif | 12
49 | 82/1 | DA+0 | WET |  | 2025-12-03 | 2025-12-05 | 2025-12-08 | 2025-12-09 | 2025-12-09 | 2025-12-10 | 2025-12-10 | Completed | 2025-12-11 | Anchal Singh | 25
50 | 76/3 | DA+3 | WET |  | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-04 | 2025-12-06 | 2025-12-06 | Completed | 2025-12-07 | Ramesh | 16
51 | 77/2 | DB+0 | WET |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-10 | 2025-12-10 | Completed | 2025-12-12 | Ramesh | 16
52 | AP106 | DD+6 | WET |  | 2025-12-05 | 2025-12-11 | 2025-12-12 | 2025-12-12 | 2025-12-13 | 2025-12-15 | 2025-12-15 | Completed | 2025-12-17 | Md. Latif | 25
53 | AP104 | DB+0 | WET |  | 2025-12-05 | 2025-12-11 | 2025-12-11 | 2025-12-12 | 2025-12-12 | 2025-12-13 | 2025-12-13 | Completed | 2025-12-15 | MS Hussain | 12
54 | AP135 | DB+3 | WET |  | 2025-12-05 | 2025-12-07 | 2025-12-09 | 2025-12-09 | 2025-12-12 | 2025-12-16 | 2025-12-16 | Completed | 2025-12-20 | Ram Sadotra | 40
55 | 135/1 | DA+6 | WET |  | 2025-12-07 | 2025-12-09 | 2025-12-11 | 2025-12-12 | 2025-12-14 | 2025-12-29 | 2025-12-29 | Completed | 2026-01-03 | Ram Sadotra | 40 | Since farmers left water in the field work hampered since 14.12.25. Work restarted from 28.12.25 and completed on 29.12.25
56 | 85/1 | DA+9 | WET |  | 2025-12-06 | 2025-12-12 | 2025-12-14 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-16 | Completed | 2025-12-21 | Anchal Singh | 25
57 | 106/1 | DA+0 | WET |  | 2025-12-10 | 2025-12-14 | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-17 | 2025-12-17 | Completed | 2025-12-22 | Md. Latif | 25
58 | 136/1 | DA+3 | WET |  | 2025-12-11 | 2025-12-12 | 2025-12-15 | 2025-12-15 | 2025-12-17 | 2025-12-19 | 2025-12-19 | Completed | 2025-12-24 | Ram Sadotra | 40
59 | 130/2 | DA+0 | WET |  | 2025-12-12 | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-17 | 2025-12-17 | Completed | 2025-12-20 | MS Constructions | 20
60 | AP85 | DB+0 | WET |  | 2025-12-12 | 2025-12-18 | 2025-12-20 | 2025-12-20 | 2025-12-23 | 2025-12-24 | 2025-12-24 | Completed | 2025-12-26 | Anchal Singh | 25
61 | 135/2 | DA+3 | WET |  | 2025-12-13 | 2025-12-14 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-21 | 2025-12-21 | Completed | 2025-12-25 | Ram Sadotra | 40
62 | 77/1 | DA+3 | WET |  | 2025-12-13 | 2025-12-14 | 2025-12-14 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-16 | Completed | 2025-12-18 | Ramesh | 16
63 | 102/1 | DA+6 | WET |  | 2025-12-14 | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-18 | 2025-12-18 | Completed | 2025-12-18 | MS Hussain | 12
64 | 130/1 | DA+0 | WET |  | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-19 | 2025-12-20 | 2025-12-20 | Completed | 2025-12-20 | MS Constructions | 20
65 | AP80 | DD+0 | PS |  | 2025-12-16 | 2025-12-21 | 2025-12-22 | 2025-12-22 | 2025-12-23 | 2025-12-25 | 2025-12-25 | Completed | 2025-12-26 | Ramesh | 16
66 | 116/1 | DA+0 | WET |  | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-20 | 2025-12-20 | Completed | 2025-12-21 | Md. Latif | 25
67 | 156/4 | DA+0 | WET |  | 2025-12-18 | 2025-12-21 | 2025-12-21 | 2025-12-25 | 2025-12-25 | 2025-12-26 | 2025-12-26 | Completed | 2026-01-03 | Md. Latif | 25
68 | 139/1 | DA+0 | WET |  | 2025-12-19 | 2025-12-21 | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-24 | 2025-12-24 | Completed | 2025-12-27 | Ram Sadotra | 40
69 | 69/3 | DA+0 | WET |  | 2025-12-19 | 2026-01-04 | 2026-01-04 | 2026-01-05 | 2026-01-05 | 2026-01-07 | 2026-01-07 | Completed | 2026-01-09 | Abdul Jabbar | 12
70 | 131/6 | DA+9 | WET |  | 2025-12-20 | 2025-12-21 | 2025-12-22 | 2025-12-23 | 2025-12-23 | 2025-12-24 | 2025-12-24 | Completed | 2025-12-26 | MS Constructions | 20
71 | 150/1 | DA+0 | WET |  | 2025-12-21 | 2025-12-26 | 2025-12-26 | 2025-12-26 | 2025-12-26 | 2025-12-27 | 2025-12-27 | Completed | 2025-12-31 | Ms. Hussain | 13
72 | 138/1 | DA+0 | WET |  | 2025-12-21 | 2025-12-22 | 2025-12-23 | 2025-12-23 | 2025-12-24 | 2025-12-26 | 2025-12-26 | Completed | 2025-12-31 | Ram Sadotra | 40
73 | 137/1 | DA+0 | WET |  | 2025-12-21 | 2025-12-22 | 2025-12-26 | 2025-12-26 | 2025-12-27 | 2025-12-28 | 2025-12-28 | Completed | 2026-01-09 | Ram Sadotra | 40
74 | 131/5 | DA+3 | WET |  | 2025-12-23 | 2025-12-24 | 2025-12-26 | 2025-12-26 | 2025-12-26 | 2025-12-27 | 2025-12-27 | Completed | 2025-12-27 | MS Constructions | 20
75 | AP146 | DC+0 | WET |  | 2025-12-23 | 2026-01-03 | 2026-01-03 | 2026-01-04 | 2026-01-04 | 2026-01-05 | 2026-01-05 | Completed | 2026-01-05 | Ikrar | 11
76 | AP102 | DB+0 | WET |  | 2025-12-23 | 2025-12-28 | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29 | Completed | 2026-01-02 | Md. Latif | 25
77 | 80/1 | DB+3 | WET |  | 2025-12-24 | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-30 | 2025-12-30 | 2025-12-30 | Completed | 2025-12-31 | Ramesh | 16
78 | 86/1 | DA+3 | WET |  | 2025-12-24 | 2025-12-28 | 2025-12-29 | 2025-12-29 | 2025-12-30 | 2025-12-30 | 2025-12-30 | Completed | 2025-12-31 | Anchal Singh | 25
79 | 156/3 | DA+0 | WET |  | 2025-12-24 | 2025-12-28 | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-30 | 2025-12-30 | Completed | 2026-01-07 | Md. Latif | 25
80 | 150/2 | DA+0 | WET |  | 2025-12-27 | 2026-01-02 | 2026-01-03 | 2026-01-03 | 2026-01-03 | 2026-01-04 | 2026-01-04 | Completed | 2026-01-03 | Ms. Hussain | 13
81 | 132/1 | DA+3 | WET |  | 2025-12-27 | 2025-12-29 | 2025-12-30 | 2025-12-30 | 2025-12-30 | 2025-12-31 | 2025-12-31 | Completed | 2026-01-02 | MS Constructions | 20
82 | 138/2 | DA+0 | WET |  | 2025-12-27 | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-31 | 2025-12-31 | 2025-12-31 | Completed | 2026-01-21 | Ram Sadotra | 40
83 | 156/2 | DA+0 | WET |  | 2025-12-28 | 2025-12-29 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-08 | 2026-01-08 | Completed | 2026-02-08 | Md. Latif | 25
84 | 155/1 | DA+0 | WET |  | 2025-12-31 | 2026-01-07 | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-09 | 2026-01-09 | Completed | 2026-02-13 | Md. Latif | 25
85 | AP131 | DC+0 | WET |  | 2026-01-05 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-11 | Completed | 2026-01-09 | MS Constructions | 20
86 | 90/2 | DA+0 | WET |  | 2026-01-04 | 2026-01-10 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-16 | 2026-01-16 | Completed | 2026-01-17 | Anchal Singh | 25
87 | AP115 | DB+0 | WET |  | 2026-01-05 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-22 | 2026-01-22 | Completed | 2026-01-22 | Sakrala Material | 12
88 | 152/1 | DA+3 | WET |  | 2026-01-05 | 2026-01-07 | 2026-01-09 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-11 | Completed | 2026-02-03 | Ram Sadotra | 40
89 | 137/2 | DA+0 | WET |  | 2026-01-05 | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-10 | Completed | 2026-01-20 | Ram Sadotra | 40
90 | 87/2 | DA+3 | WET |  | 2026-01-07 | 2026-01-11 | 2026-01-11 | 2026-01-11 | 2026-01-11 | 2026-01-12 | 2026-01-12 | Completed | 2026-01-13 | Ramesh | 16
91 | 145/2 | DA+3 | PS |  | 2026-01-07 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-20 | 2026-01-20 | Completed | 2026-01-20 | Ikrar | 11
92 | AP147 | DB+0 | WET |  | 2026-01-07 | 2026-01-14 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | Completed | 2026-01-16 | Ms. Hussain | 13
93 | AP154 | DC+0 | WET |  | 2026-01-08 | 2026-01-14 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-18 | 2026-01-18 | Completed | 2026-02-13 | Md. Latif | 25
94 | 152/2 | D+0 | WET |  | 2026-01-08 | 2026-01-12 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-16 | 2026-01-16 | Completed | 2026-02-03 | Ram Sadotra | 40
95 | AP138 | DD+0 | WET |  | 2026-01-08 | 2026-01-16 | 2026-01-17 | 2026-01-17 | 2026-01-18 | 2026-01-20 | 2026-01-20 | Completed | 2026-01-20 | Ram Sadotra | 40
96 | AP157 | DB+0 | WET |  | 2026-01-09 | 2026-01-13 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-17 | 2026-01-17 | Completed | 2026-01-20 | Md. Latif | 25
97 | AP129 | DB+9 | PS |  | 2026-01-11 | 2026-01-16 | 2026-01-17 | 2026-01-17 | 2026-01-19 | 2026-01-20 | 2026-01-20 | Completed | 2026-01-20 | MS Constructions | 20
98 | 69/2 | DA+0 | FS |  | 2026-01-15 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-22 | 2026-01-22 | Completed | 2026-01-25 | Sufiyan Ali | 25
99 | 156/1 | DA+6 | WET |  | 2026-01-17 | 2026-01-19 | 2026-01-20 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-22 | Completed | 2026-02-13 | Md. Latif | 25
100 | 153/0 | DC+0 | WET |  | 2026-01-17 | 2026-02-02 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-05 | 2026-02-05 | Completed | 2026-02-08 | Ram Sadotra | 40
101 | AP130 | DD+18 | PS |  | 2026-01-18 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-12 | Completed | 2026-02-12 | MS Constructions | 20
102 | AP92 | DD+25 | PS |  | 2026-01-21 | 2026-02-08 | 2026-02-09 | 2026-02-09 | 2026-02-10 | 2026-02-13 | 2026-02-13 | Completed | 2026-02-17 | Anchal Singh | 20
103 | 71/2 | DA+6 DA+9 | WET |  | 2026-01-18 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-21 | 2026-01-21 | Completed | 2026-01-22 | Ramesh | 16 | Loc: 71/2 -recasted with DA+9 Started : 11-2-26 & Completed : 12-2-26
104 | 151/1 | DA+0 | WET |  | 2026-01-18 | 2026-01-22 | 2026-01-30 | 2026-01-30 | 2026-01-31 | 2026-01-31 | 2026-01-31 | Completed | 2026-02-01 | Ms. Hussain | 13
105 | 69/1 | DA+0 | FS |  | 2026-01-18 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-27 | 2026-01-27 | Completed | 2026-02-19 | Sufiyan Ali | 25
106 | AP139 | DB+0 | WET |  | 2026-01-20 | 2026-02-04 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-06 | 2026-02-06 | Completed | 2026-02-08 | Ram Sadotra | 40
107 | 155/2 | DA+0 | WET |  | 2026-01-20 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-30 | 2026-01-30 | 2026-01-30 | Completed | 2026-01-30 | Md. Latif | 25
108 | 115/1 | DA+6 | WET |  | 2026-01-21 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-31 | 2026-01-31 | 2026-01-31 | Completed | 2026-02-02 | Sakrala Material | 20
109 | 136/2 | DA+3 | WET |  | 2026-01-22 | 2026-02-06 | 2026-02-07 | 2026-02-07 | 2026-02-10 | 2026-02-11 | 2026-02-11 | Completed | 2026-02-15 | Ram Sadotra | 40
110 | 155/3 | DA+0 | WET |  | 2026-01-23 | 2026-01-30 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | Completed | 2026-02-05 | Md. Latif | 25
111 | AP97 | DD+3 | WET |  | 2026-01-29 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-08 | Completed | 2026-02-07 | Sufiyan Ali | 20
112 | AP155 | DD+0 | WET |  | 2026-01-31 | 2026-02-06 | 2026-02-07 | 2026-02-07 | 2026-02-09 | 2026-02-09 | 2026-02-09 | Completed | 2026-02-10 | Md. Latif | 25
113 | 151/2 | DA+3 | WET |  | 2026-02-03 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-07 | 2026-02-07 | Completed | 2026-02-07 | Ms. Hussain | 13
114 | 152/4 | DA+0 | WET |  | 2026-02-04 | 2024-02-05 | 2026-02-10 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-12 | Completed | 2026-02-14 | Ram Sadotra | 40
115 | AP156 | DC+0 | WET |  | 2026-02-05 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-14 | 2026-02-14 | 2026-02-14 | Completed | 2026-02-15 | Md. Latif | 25
116 | 70/2 | DA+0 | PS(SD) |  | 2026-02-05 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-21 | 2026-02-21 | Completed | 2026-02-20 | Ramesh | 16
117 | 153/1 | DA+0 | WET |  | 2026-02-06 | 2026-02-10 | 2026-02-11 | 2026-02-11 | 2026-02-13 | 2026-02-13 | 2026-02-13 | Completed | 2026-02-14 | Ram Sadotra | 40
118 | AP111 | DC+0 | WET |  | 2026-02-06 | 2026-02-14 | 2026-02-14 | 2026-02-14 | 2026-02-15 | 2026-02-19 | 2026-02-19 | Completed | 2026-02-19 | Sakrala Material | 20
119 | 136/3 | DA+0 | WET |  | 2026-02-09 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-15 | Completed | 2026-02-20 | Ram Sadotra | 40
120 | 157/1 | DA+0 | WET |  | 2026-02-09 | 2026-02-13 | 2026-02-13 | 2026-02-14 | 2026-02-14 | 2026-02-15 | 2026-02-15 | Completed | 2026-02-15 | Md. Latif | 25
121 | AP150 | DC+0 | WET |  | 2026-02-09 | 2026-02-15 | 2026-02-16 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-18 | Completed | 2026-02-18 | Ms. Hussain | 13
122 | AP70 | DC+3 | PS(SD) |  | 2026-02-10 | 2026-02-14 | 2026-02-15 | 2026-02-15 | 2026-02-16 | 2026-02-18 | 2026-02-18 | Completed | 2026-02-19 | Sufiyan Ali-1 | 18
123 | 136/4 | DA+3 | WET |  | 2026-02-12 | 2026-02-15 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-20 | 2026-02-20 | Completed | 2026-02-20 | Ram Sadotra-1 | 25
124 | AP68 | DB+0 | PS(SD) |  | 2026-02-10 | 2026-02-19 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-21 | 2026-02-21 | Completed | 2026-02-19 | Sufiyan Ali-2 | 15
125 | AP91 | DD+25 | PS |  | 2026-02-12 | 2026-02-24 | 2026-02-25 | 2026-02-25 | 2026-02-27 | 2026-02-27 | 2026-02-27 | Completed | 2026-02-25 | Anchal Singh | 20
126 | 153/2 | DA+3 | WET |  | 2026-02-13 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-18 | 2026-02-18 | Completed | 2026-02-19 | Ram Sadotra-2 | 20
127 | AP79 | DD+9 | WET |  | 2026-02-15 | 2026-02-23 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-25 | 2026-02-25 | Completed | 2026-02-26 | Sufiyan Ali-3 | 15
128 | 72/1 | DA+3 | WET |  | 2026-02-14 | 2026-02-15 | 2026-02-15 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-17 | Completed | 2026-02-17 | Ramesh | 16
129 | AP137 | DC+3 | WET |  | 2026-02-15 | 2026-02-25 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | Completed | 2026-02-28 | Ram Sadotra-2 | 20
130 | AP132 | DC+9 1.5m RC | WET |  | 2026-02-15 | 2026-02-21 | 2026-02-21 | 2026-02-21 | 2026-02-22 | 2026-02-24 | 2026-02-24 | Completed | 2026-02-25 | MS Constructions | 20
131 | AP148 | DD+25 2MRC | PS |  | 2026-02-19 | 2026-03-01 | 2026-03-01 | 2026-03-05 | 2026-03-06 | 2026-03-16 | 2026-03-16 | Completed | 2026-03-16 | Ram Sadotra-2 | 20
132 | AP159 | DD+18 | PS |  | 2026-02-19 | 2026-02-26 | 2026-02-27 | 2026-02-27 | 2026-02-28 | 2026-02-28 | 2026-02-28 | Completed | 2026-03-03 | Md. Latif | 20
133 | 67/3 | DA+0 | PS (SD) |  | 2026-02-19 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-26 | 2026-02-26 | Completed | 2026-03-24 | Sufiyan Ali | 15
134 | AP69 | DB+0 | PS (SD) |  | 2026-02-19 | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-03-02 | 2026-03-02 | 2026-03-02 | Completed | 2026-03-14 | Sufiyan Ali | 15
135 | 145/1 | DA+0 | PS (SD) |  | 2026-02-21 | 2026-02-26 | 2026-02-27 | 2026-02-27 | 2026-02-28 | 2026-02-28 | 2026-02-28 | Completed | 2026-03-03 | Ikrar | 10
136 | AP149 | DD+25 | PS |  | 2026-02-21 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-10 | Completed | 2026-03-10 | Ms. Hussain | 13
137 | AP114 | DB+0 | WET |  | 2026-02-21 | 2026-02-26 | 2026-02-27 | 2026-02-27 | 2026-02-28 | 2026-02-28 | 2026-02-28 | Completed | 2026-03-06 | Sakrala Material | 18
138 | 70/1 | DA+9 | PS (SD) |  | 2026-02-22 | 2026-02-25 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | Completed | 2026-02-28 | Ramesh | 16
139 | 67/2 | DA+0 | PS (SD) |  | 2026-02-26 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | Completed | 2026-03-24 | Sufiyan Ali | 15
140 | AP71 | DC+9 | PS (SD) |  | 2026-02-26 | 2026-03-14 | 2026-03-22 | 2026-03-22 | 2026-03-22 | 2026-03-23 | 2026-03-23 | Completed | 2026-03-23 | Ramesh | 16
141 | 56/3 | DA+6 | PS (SD) |  | 2026-03-05 | 2026-03-29 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | Completed | 2026-04-06 | Wani Const | 10
142 | AP152 | DD+0 | WET |  | 2026-02-28 | 2026-03-20 | 2026-03-22 | 2026-03-22 | 2026-03-23 | 2026-03-26 | 2026-03-26 | Completed | 2026-04-01 | Ram Sadotra | 20
143 | AP108 | DD+25 | PS |  | 2026-03-01 | 2026-03-22 | 2026-03-23 | 2026-03-23 | 2026-03-24 | 2026-03-28 | 2026-03-28 | Completed | 2026-04-13 | Anchal Singh | 15
144 | AP127 | DD+30 2MRC | PS |  | 2026-03-01 | 2026-03-10 | 2026-03-11 | 2026-03-11 | 2026-03-13 | 2026-03-15 | 2026-03-15 | Completed | 2026-03-14 | MS Constructions | 20
145 | AP145 | DB+0 | PS (SD) |  | 2026-03-01 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-25 | Completed | 2026-03-28 | Ikrar | 10
146 | AP136 | DC+3 | WET |  | 2026-03-02 | 2026-03-12 | 2026-03-13 | 2026-03-13 | 2026-03-16 | 2026-03-18 | 2026-03-18 | Completed | 2026-03-18 | Ram Sadotra | 20
147 | AP67 | DD+0 | PS(SD) |  | 2026-03-25 | 2026-03-29 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | Completed | 2026-04-06 | Sufiyan Ali | 10
148 | 67/1 | DA+0 | PS(SD) |  | 2026-03-13 | 2026-03-18 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | Completed | 2026-03-19 | Sufiyan Ali | 20
149 | 152/3 | DA+0 1M RC | PS |  | 2026-03-16 | 2026-03-29 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | Completed | 2026-04-09 | Ram Sadotra | 14
150 | AP125 | DD+18 | PS |  | 2026-03-24 | 2026-04-03 | 2026-04-04 | 2026-04-04 | 2026-04-04 | 2026-04-06 | 2026-04-06 | Completed | 2026-04-03 | MS Constructions | 16
151 | AP124 | DB+9 | PS |  | 2026-03-23 | 2026-03-29 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | Completed | 2026-05-10 | Ram Sadotra | 16
152 | AP70/3 | DD+18 1MRC | PS(SD) |  | 2026-05-01 | 2026-05-13 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-19 | 2026-05-19 | Completed | 2026-05-16 | Ramesh | 16
153 | AP109 | DD+30 | PS |  | 2026-03-25 | 2026-04-07 | 2026-04-07 | 2026-04-10 | 2026-04-10 | 2026-04-12 | 2026-04-12 | Completed | 2026-04-13 | Anchal Singh | 15
154 | 144/4 | DA+0 | PS(SD) |  | 2026-03-25 | 2026-04-04 | 2026-04-04 | 2026-04-04 | 2026-04-04 | 2026-04-05 | 2026-04-05 | Completed | 2026-05-08 | Ikrar | 12
155 | 144/3 | DA+6 | PS(SD) |  | 2026-03-29 | 2026-04-04 | 2026-04-05 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-07 | Completed | 2026-04-07 | MS Hussain | 11
156 | 65/2 | DA+6 | PS(SD) |  | 2026-03-30 | 2026-04-04 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-07 | Completed | 2026-04-10 | Sufiyan Ai | 10
157 | AP59 | DD+6 | PS(SD) |  | 2026-04-11 | 2026-04-21 | 2026-04-21 | 2026-04-25 | 2026-04-25 | 2026-04-27 | 2026-04-27 | Completed |  | Sufiyan Ai | 13
158 | AP165 | DB+6 1MRC | FS |  | 2026-04-04 | 2026-04-17 | 2026-04-18 | 2026-04-18 | 2026-04-19 | 2026-04-22 | 2026-04-22 | Completed | 2026-05-04 | Ram Sadotra | 15
159 | 55/1 | DA+6 | PS(SD) |  | 2026-04-11 | 2026-04-26 | 2026-04-26 | 2026-04-26 | 2026-04-26 | 2026-04-28 | 2026-04-28 | Completed | 2026-05-01 | Wani Const | 8
160 | AP61 | DC+0 | PS(SD) |  | 2026-04-08 | 2026-04-15 | 2026-04-18 | 2026-04-18 | 2026-04-18 | 2026-04-21 | 2026-04-21 | Completed | 2026-05-07 | Sufiyan Ali | 12
161 | AP126 | DB+0 | WET |  | 2026-04-06 | 2026-04-12 | 2026-04-13 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-15 | Completed | 2026-04-15 | MS Constructions | 16
162 | AP142 | DD+0 | PS(SD) |  | 2026-04-11 | 2026-04-24 | 2026-04-25 | 2026-04-25 | 2026-04-27 | 2026-04-29 | 2026-04-29 | Completed | 2026-05-01 | MS Hussain | 12
163 | AP166 | DB+6 2MRC | FS |  | 2026-04-18 | 2026-04-25 | 2026-04-26 | 2026-04-26 | 2026-04-29 | 2026-04-30 | 2026-04-30 | Completed | 2026-05-04 | Ram Sadotra | 12
164 | AP123 | DC+0 | WET |  | 2026-04-14 | 2026-04-23 | 2026-04-24 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-26 | Completed | 2026-04-26 | MS Constructions | 16
165 | 56/2 | DA+3 | FS(PD) |  | 2026-04-18 | 2026-04-24 | 2026-04-25 | 2026-04-25 | 2026-04-25 | 2026-04-25 | 2026-04-25 | Completed | 2026-05-27 | Tapseer | 10
166 | AP86 | DC+0 | WET |  | 2026-04-16 | 2026-04-18 | 2026-04-20 | 2026-04-21 | 2026-04-21 | 2026-04-23 | 2026-04-23 | Completed | 2026-05-22 | Sufiyan Ali | 8
167 | AP144 | DB+0 | PS(SD) |  | 2026-04-28 | 2026-05-04 | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-07 | 2026-05-07 | Completed | 2026-05-08 | Ikrar | 10
168 | AP64 | DC+9 | PS(SD) |  | 2026-04-23 | 2026-04-26 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-05-01 | 2026-05-01 | Completed | 2026-05-07 | Sufiyan Ali | 12
169 | AP161 | DD+9 | WET |  | 2026-04-24 | 2026-05-03 | 2026-05-05 | 2026-05-05 | 2026-05-08 | 2026-05-09 | 2026-05-09 | Completed | 2026-05-20 | Ram Sadotra | 15
170 | AP82 | DD+3 | FS |  | 2026-04-28 | 2026-05-01 | 2026-05-05 | 2026-05-06 | 2026-05-06 | 2026-05-08 | 2026-05-08 | Completed | 2026-05-09 | Sufiyan Ali-3 | 10
171 | AP56 | DC+3 | PS(SD) |  | 2026-04-28 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 | 2026-05-07 | Completed | 2026-05-27 | Tapseer | 10
172 | 122/1 | DA+3 | WET |  | 2026-04-26 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | Completed | 2026-05-02 | MS Constructions | 16
173 | 64/1 | DA+0 | PS(SD) |  | 2026-05-01 | 2026-05-05 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 | 2026-05-07 | Completed | 2026-05-08 | Sufiyan Ali-1 | 12
174 | 142/1 | DA+0 | PS(SD) |  | 2026-04-30 | 2026-05-06 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 | Completed | 2026-05-10 | MS Hussain | 12
175 | 65/4 | DA+3 | PS(SD) |  | 2026-04-30 | 2026-05-09 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-16 | Completed | 2026-05-26 | KDR Engineering | 10
176 | 61/1 | DA+0 | PS(SD) |  | 2026-05-03 | 2026-05-06 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 | Completed | 2026-05-08 | Aman Mansoori | 10
177 | 57/1 | DA+0 | PS(SD) |  | 2026-05-03 | 2026-05-06 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-09 | Completed |  | Sufiyan Ali-2 | 11
178 | AP128 | DD+30 2MRC | PS |  | 2026-05-03 | 2026-05-12 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-18 | 2026-05-18 | Completed | 2026-05-15 | MS Constructions | 16
179 | AP163 | DB+6 | WET |  | 2026-04-30 | 2026-05-07 | 2026-05-09 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-11 | Completed | 2026-06-18 | Ram Sadotra | 12
180 | 159/3 | DA+0 | WET |  | 2026-05-03 | 2026-05-07 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-16 | Completed | 2026-05-20 | Ram Sadotra | 10
181 | AP 83 | DD+25 2M RC | PS |  | 2026-05-03 | 2026-05-05 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-20 | 2026-05-20 | Completed | 2026-05-22 | Sufiyan Ali-4 | 10
182 | AP158 | DD+18 | PS |  | 2026-05-07 | 2026-05-17 | 2026-05-18 | 2026-05-18 | 2026-05-20 | 2026-05-23 | 2026-05-23 | Completed | 2026-05-24 | Ikrar | 11
183 | AP162 | DD+18 | PS |  | 2026-05-07 | 2026-05-15 | 2026-05-16 | 2026-05-16 | 2026-05-16 | 2026-05-17 | 2026-05-17 | Completed | 2026-05-18 | Ram Sadotra | 12
184 | AP110 | DD+0 | WET |  | 2026-05-07 | 2026-05-11 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-14 | 2026-05-14 | Completed | 2026-05-16 | Ramji Structure | 10
185 | 71/1 | DA+3 | PS(SD) |  | 2026-05-08 | 2026-05-10 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-14 | 2026-05-14 | Completed | 2026-05-17 | Ramesh | 14
186 | AP57 | DD+3 | PS(SD) |  | 2026-05-08 | 2026-05-10 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-15 | Completed | 2026-05-31 | Sufiyan Ali-3 | 16
187 | 62/2 | DA+0 | PS(SD) |  | 2026-05-08 | 2026-05-12 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 2026-05-14 | Completed | 2026-05-18 | Sufiyan Ali-1 | 11
188 | AP143 | DB+0 | PS(SD) |  | 2026-05-08 | 2026-05-15 | 2026-05-16 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-18 | Completed | 2026-05-18 | MS Hussain | 12
189 | 56/4 | DA+6 | PS(SD) |  | 2026-05-08 | 2026-05-12 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-13 | Completed | 2026-05-13 | Tapseer | 10
190 | AP60 | DB+6 | PS(SD) |  | 2026-05-10 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-17 | 2026-05-17 | 2026-05-17 | Completed | 2026-05-23 | Aman Mansoori | 10
191 | AP63 | DB+9 | PS(SD) |  | 2026-05-11 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-16 | 2026-05-18 | 2026-05-18 | Completed | 2026-05-18 | Sufiyan Ali-1 | 12
192 | 59/1 | DA+3 | FS(PD) |  | 2026-05-12 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 | Completed | 2026-05-28 | Sufiyan Ali-2 | 10
193 | 62/1 | DA+0 | PS(SD) |  | 2026-05-13 | 2026-05-15 | 2026-05-16 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-18 | Completed | 2026-05-31 | Sufiyan Ali-5 | 11
194 | AP84 | DD+18 2MRC | PS |  | 2026-05-12 | 2026-05-14 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-24 | 2026-05-24 | Completed | 2026-05-26 | Sufiyan Ali-6 | 10
195 | AP78 | DD+18 | PS |  | 2026-05-14 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-10 | 2026-06-10 | Completed | 2026-06-07 | Md. Sharif/Sufiyan Ali | 10
196 | AP112 | DD+30 | PS |  | 2026-05-14 | 2026-05-16 | 2026-05-17 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-19 | Completed | 2026-05-23 | Ramji Structure | 10
197 | 159/2 | DA+0 | WET |  | 2026-05-14 | 2026-05-16 | 2026-05-17 | 2026-05-17 | 2026-05-17 | 2026-05-19 | 2026-05-19 | Completed | 2026-05-20 | Ram Sadotra | 15
198 | AP55 | DD+3 | PS |  | 2026-05-16 | 2026-05-21 | 2026-05-23 | 2026-05-23 | 2026-05-23 | 2026-05-25 | 2026-05-25 | Completed | 2026-05-26 | Tapseer | 10
199 | 57/2 | DA+0 | PS(SD) |  | 2026-05-16 | 2026-05-16 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | Completed | 2026-05-31 | Sufiyan Ali | 10
200 | 60/1 | DA+0 | PS(SD) |  | 2026-05-17 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-22 | Completed | 2026-05-23 | Aman Mansoori | 10
201 | 65/5 | DA+3 | PS(SD) |  | 2026-05-17 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-05-30 | 2026-05-30 | 2026-05-30 | Completed | 2026-05-29 | KDR Engineering | 10
202 | AP81 | DD+9 | FS |  | 2026-05-17 | 2026-05-28 | 2026-05-28 | 2026-05-28 | 2026-05-29 | 2026-05-31 | 2026-05-31 | Completed | 2026-05-08 | Sufiyan Ali | 10
203 | 65/1 | DA+0 | PS(SD) |  | 2026-05-18 | 2026-05-24 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-28 | Completed | 2026-05-31 | Sufiyan Ali | 10
204 | AP113 | DD+25 | PS |  | 2026-05-18 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-23 | 2026-05-23 | Completed | 2026-05-24 | Ramji Structure | 10
205 | 143/1 | DA+0 | PS(SD) |  | 2026-05-18 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-23 | 2026-05-23 | Completed | 2026-05-24 | MS Hussain | 13
206 | AP168 | DD+9 | FS |  | 2026-05-18 | 2026-05-23 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-30 | 2026-05-30 | Completed | 2026-06-08 | JRC Contractor | 10
207 | 159/1 | DA+0 | WET |  | 2026-05-19 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-22 | Completed | 2026-05-23 | Ram Sadotra | 12
208 | AP66 | DC+0 | WET |  | 2026-05-21 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-26 | 2026-05-26 | Completed | 2026-05-26 | Ramesh | 16
209 | AP174 | DD+0 | WET |  | 2026-05-22 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 2026-05-30 | 2026-05-30 | Completed | 2026-06-01 | Ram Sadotra | 12
210 | AP105 | DD+3 1MRC | WET |  | 2026-05-23 | 2026-05-28 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-05-30 | 2026-05-30 | Completed | 2026-05-30 | Ramji Structure | 10
211 | AP65 | DB+0 | PS(SD) |  | 2026-05-23 | 2026-05-25 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-28 | 2026-05-28 | Completed | 2026-06-01 | Sufiyan Ali | 10
212 | AP167 | DD+9 | FS |  | 2026-05-25 | 2026-05-28 | 2026-05-30 | 2026-05-30 | 2026-05-31 | 2026-05-31 | 2026-05-31 | Completed | 2026-06-08 | JRC Contractor | 10
213 | AP54 | DD+6 | PS(SD) |  | 2026-05-25 | 2026-05-31 | 2026-06-01 | 2026-06-01 | 2026-06-04 | 2026-06-05 | 2026-06-05 | Completed | 2026-06-05 | Tapseer | 10
214 | AP58 | DC+0 | WET |  | 2026-05-25 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-06 | 2026-06-06 | Completed | 2026-06-11 | Sufiyan Ali | 10
215 | AP76 | DC+9 | PS |  | 2026-05-26 | 2026-06-02 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-05 | Completed | 2026-06-06 | Ramesh | 16
216 | 144/1 | DA+3 | PS(SD) |  | 2026-05-26 | 2026-06-02 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 | Completed | 2026-06-06 | Md. Ikrar | 11
217 | AP173 | DD+3 | WET |  | 2026-05-27 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-06 | 2026-06-06 | Completed | 2026-06-09 | Ram Sadotra-1 | 13
218 | AP175 | DB+0 | WET |  | 2026-05-27 | 2026-05-29 | 2026-06-06 | 2026-06-06 | 2026-06-08 | 2026-06-10 | 2026-06-10 | Completed | 2026-06-11 | Ram Sadotra-2 | 8
219 | 77/3 | DA+9 1.5MRC | WET |  | 2026-05-27 | 2026-05-31 | 2026-06-01 | 2026-06-01 | 2026-06-05 | 2026-06-12 | 2026-06-12 | Completed |  | KDR Engineering | 8 | RC portion pending
220 | 65/3 | DA+0 | PS(SD) |  | 2026-05-29 | 2026-05-31 | 2026-06-01 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-03 | Completed | 2026-06-04 | Sufiyan Ali | 10
221 | AP89 | DD+25 | PS |  | 2026-05-31 | 2026-06-03 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | Completed | 2026-06-01 | Ramji Structure | 16
222 | 143/2 | DA+0 | PS(SD) |  | 2026-06-03 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | Completed | 2026-06-10 | Ms.Hussain | 11 | Pit A,C - Casting Completed Pit D- Casting Completed
223 | AP88 | DD+18 | PS |  | 2026-06-03 | 2026-06-06 | 2026-06-07 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-09 | Completed |  | Ramji Structure | 16
224 | 144/2 | DA+0 | PS(SD) |  | 2026-06-05 | 2026-06-10 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 | Completed | 2026-06-13 | Md.Ikrar | 10
225 | AP53 | DCT+0 | PS(SD) |  | 2026-06-10 | 2026-06-13 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | Completed | 2026-06-17 | Ramji Structure | 16
226 | AP62 | DB+0 | PS(SD) |  | 2026-06-09 | 2026-06-13 | 2026-06-20 | 2026-06-20 | 2026-06-20 | 2026-06-22 | 2026-06-22 | Completed | 2026-06-23 | KDR Engineering | 10
227 | 171/1 | DA+6 | WET |  | 2026-06-09 | 2026-06-13 | 2026-06-14 | 2026-06-14 | 2026-06-24 | 2026-06-25 | 2026-06-25 | Completed | 2026-06-27 | JRC Contractor | 10
228 | AP172 | DD+3 | WET |  | 2026-06-11 | 2026-06-13 | 2026-06-19 | 2026-06-19 | 2026-06-20 | 2026-06-22 | 2026-06-22 | Completed | 2026-06-05 | JRC Contractor | 10
229 | 180/1 | DA+0 | WET |  | 2026-06-12 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-19 | 2026-06-19 | Completed | 2026-06-23 | Ram Sadotra | 10
230 | AP140 | DD+30 | FS |  | 2026-06-12 | 2026-06-20 | 2026-06-20 | 2026-06-21 | 2026-06-21 | 2026-06-24 | 2026-06-24 | Completed | 2026-06-26 | Ms.Hussain | 13
231 | 52/1 | DA+9 | PS(SD) |  | 2026-06-16 | 2026-06-18 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-20 | 2026-06-20 | Completed | 2026-06-22 | Ramji Structure | 16
232 | AP180 | DB+9 | WET |  | 2026-06-16 | 2026-06-21 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-27 | 2026-06-27 | Completed | 2026-06-27 | Ram Sadotra | 8
233 | AP151 | DC+0 | WET |  | 2026-06-17 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 | Completed | 2026-07-01 | Ram Sadotra | 10
234 | AP52 | DD+30 3MRC | FS |  | 2026-06-21 | 2026-06-28 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-07-03 | 2026-07-03 | Completed | 2026-07-05 | Ramji Structure | 16
235 | 56/1 | DA+6 | PS(SD) |  | 2026-06-23 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-26 | 2026-06-26 | Completed | 2026-06-28 | Ramji Structure | 16
236 | AP176 | DD+30 2MRC | PS |  | 2026-06-25 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-06 | 2026-07-06 | Completed | 2026-07-06 | Ram Sadotra | 10
237 | AP178 | DD+18 | PS |  | 2026-06-27 | [7 empty] | 2026-07-09 | Ram Sadotra | 18 | Pit A,B,C- Casting Completed Lat pit casting not possible since landowner sowing crop since 10-07-2026
238 | AP101 | DC+6 | WET |  | 2026-07-22 | [8 empty] | KDR Engineering | 8 | Pit B- Casting Completed Pit A- Casting upto Pyramid Pit D- Casting upto frustum Pit C- Excavation WIP
239 | AP182 | DD+30 | PS |  | 2026-07-17 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-07-31 | Completed | 2026-07-31 | Ram Sadotra | 8

## Pile FDN
KEC International Ltd |  |  |  |  | Date: | 2026-08-11
400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5-Punjab Portion
PILE FOUNDATION
S.No | Loc No. | Tower Type | FDN | Start Date | Gang Name | Gang Strength | Remark
1 | AP141 | DD+30 5MRC | Pile | 2026-06-14 | Vinay Constructions | 20 | Pit | Pile | Boring Depth Mtr | Liner Depth Mtr | Concreting Date
[7 empty] | Pit C | C11 | 39.7 | 20.56 | 2026-07-21
[8 empty] | C12 | 39.7 | 38 | 2026-07-27
[8 empty] | C13 | 39.73 | 30.1 | 2026-08-11
[8 empty] | C14 | 39.7 | 20.76 | 2026-07-30
[8 empty] | C15 | 39.7 | 20.56 | 2026-08-01
[7 empty] | Pit D | D16 | 40.7 | 20.76 | 2026-07-28
[8 empty] | D17 | 20.56 | 20.76 | 2026-08-02
[8 empty] | D18 | 40 | 26.6 | 2026-07-15
[8 empty] | D19 | 39.7 | 21.87 | 2026-07-31
[8 empty] | D20 | 39.8 | 20.76 | 2026-08-11
[7 empty] | Pit B | B6 | 19.5 | 19.5
[8 empty] | B7 | 19.75 | 19.75
[8 empty] | B8 | 19.75 | 19.75
[8 empty] | B9 | 19.84 | 19.84
[8 empty] | B10 | 19.84 | 19.84
[7 empty] | Pit A | A1 | 20.1 | 20.1
[8 empty] | A2 | 19.78 | 19.78
[8 empty] | A3 | 19.6 | 19.6
[8 empty] | A4 | 19.76 | 19.76
[8 empty] | A5 | 19.76 | 19.76

## Hindrance
Hindrance Details.
S.No | Line | From | To | Days | Status | Impact Location / Work | Hindrance Details | Remarks
1 | 400 kV D/C Samba-Jalandhar | 2025-07-29 | 2025-07-30 | 2 | Closed | Loc: 29/5 (Foundation) | Due to heavy rains at site excavated Pits (B,C,D) collapsed and site works are hampered
2 | 400 kV D/C Samba-Jalandhar | 2025-08-01 | 2025-08-01 | 1 | Closed | Loc: 29/5 (Foundation) | Due to heavy rains PCC, Steel Binding, RCC work in Pit B
3 | 400 kV D/C Kishenpur-Samba | 2025-08-06 | 2025-08-06 | 1 | Closed | Check Survey Work | Due to landslides, road blocked and at site unable to carry out the survey work
4 | 400 kV D/C Samba-Jalandhar | 2025-08-07 | 2025-08-07 | 1 | Closed | Loc: 29/5 (Foundation) | Due to heavy rains at site , RCC work hampered in Pit A
5 | 400 kV D/C Samba-Jalandhar | 2025-08-09 | 2025-08-09 | 1 | Closed | Loc: 29/5 (Foundation) | Due to heavy rains at site , RCC work hampered in Pit C
6 | 400 kV D/C Samba-Jalandhar | 2025-08-12 | 2025-08-14 | 3 | Closed | Loc: 29/4 (Foundation) | Due to heavy rains for continous 3 days site excavation work hampered
7 | 400 kV D/C Kishenpur-Samba | 2025-08-12 | 2025-08-12 | 1 | Closed | Check Survey Work | Due to rains /landslides, at site unable to carry out the survey work
8 | 400 kV D/C Kishenpur-Samba | 2025-08-16 | 2025-08-18 | 3 | Closed | Check Survey Work | Due to rains/ landslides , at site unable to carry out the survey work
9 | 400 kV D/C Samba-Jalandhar | 2025-08-17 | 2025-08-18 | 2 | Closed | Loc: 29/4 (Foundation) | Due to heavy rains for continous 2 days site Stub Setting , PCC , Steel Binding work hampered
10 | 400 kV D/C Samba-Jalandhar | 2025-08-20 | 8,9&10 | 0.5 | Closed | 38 | Due to heavy rains Pit B - Stub Setting, PCC, Pit C - RCC work and also unable to carry out survey work in the line
11 | 400 kV D/C Samba-Jalandhar | 2025-08-23 | 1900-01-10 | 6 | Closed | Loc: 29/4 (Foundation) & Check Survey Work | Due to heavy rains Pit B - Stub Setting, PCC, Pit C - RCC work and also unable to carry out survey work in the line |  | 1
12 | 400 kV D/C Kishenpur-Samba | 2025-08-23 | 2025-08-28 | 6 | Closed |  | Due to continous heavy rains / floods for 6 days all site related works are hampered
13 | 400 kV D/C Samba-Jalandhar | 2025-08-30 | 2025-09-03 | 5 | Closed | Loc: 29/4 & Loc: 29/3 (Foundation) & Check Survey Work | Due to heavy rains / floods landslides occurred and there is no approach for carrying out site activities and all roads are blocked by local gov. authority
14 | 400 kV D/C Kishenpur-Samba | 2025-08-29 | 2025-09-11 | 14 | Closed | Check Survey Work
15 | LILO-Kishtwar | 2025-08-28 | 2025-09-17 | 20 | Closed | All site works | Due to heavy rains/floods NH closed & also due to local political issues administration issued section 144 , 163
16 | 400 kV D/C Samba-Jalandhar | 2025-09-28 | 2025-09-29 | 2 | Closed | Loc: 90/1 -Foundation Works | Due to farmers issues work on hold
17 | 400 kV D/C Samba-Jalandhar | 2025-10-05 | 2025-10-07 | 3 | Closed | All site works | Due to heavy rains work hampered |  | 2
18 | 400 kV D/C Kishenpur-Samba | 2025-10-05 | 2025-10-09 | 4 | Closed | All site works | Due to heavy rains work hampered Roads closed by local administration due to landslides
19 | LILO-Kishtwar | 2025-10-05 | 19&20 | 3 | Closed | All site works | Due to heavy rains work hampered
20 | 400 kV D/C Samba-Jalandhar | 2025-10-13 | 1900-01-20 | 3 | Closed | Loc: 90/1 -Foundation Works | Due to farmers issues work on hold for 3 days
21 | 400 kV D/C Samba-Jalandhar | 2025-10-18 | 1900-01-21 | 1 | Closed | Loc: 90/1 -Foundation Works | Due to farmers issues work on hold
22 | 400 kV D/C Samba-Jalandhar | 2025-10-24 | 2025-11-20 | 27 | Closed | Loc: 90/1 - 4th pit works | Due to farmers issues work on hold
23 | 400 kV D/C Samba-Jalandhar | 2025-12-04 | 2025-12-06 | 3 | Closed | Foundation works at loc: 23/4 | Due to ROW - foundation work hampered
24 | 400 kV D/C Samba-Jalandhar | 2025-12-11 | 2025-12-14 | 3 | Closed | Foundation works at loc: 115/0 | Due to ROW - foundation work hampered
25 | 400 kV D/C Samba-Jalandhar | 2025-12-14 | 2025-12-16 | 2 | Closed | Contractor pawan kumar sharma , required further work front , the team is idle since 14-12-2025 after completion of loc: 39/2 on 13.12.25 | Due to ROW - foundation work hampered
26 | 400 kV D/C Kishenpur-Samba | 2025-12-12 | 2025-12-14 | 2 | Closed | Foundation Works at AP32 , due to ROW issues | Due to ROW - foundation work hampered
27 | 400 kV D/C Samba-Jalandhar | 2025-12-19 | 2025-12-20 | 2 | Closed | Contractor Ikrar , required further work front , the team is idle since 19-12-2025 after completion of loc: 103/0 on 18.12.25 | Due to ROW - foundation work hampered
28 | 400 kV D/C Kishenpur-Samba | 2025-12-22 | 2025-12-23 | 2 | Closed | Contractor -Naresh idle for work front since 22-12-2025 at Loc: 52/0 | Due to ROW - foundation work hampered
29 | LILO-Kishtwar | 2025-12-30 | 2026-01-16 | 17 | Closed | Due to approach issue / ROW clearence required for loc: AP5 Foundation work hampered. Work on hold in LILO Line as advised by RKPTL | Due to ROW/ Route diversion
30 | 400 kV D/C Samba-Jalandhar | 2026-01-02 | 2026-01-04 | 2 | Closed | Work front required for vendor Ram Sadotra after completion of Loc: 138/2 . 2 teams engaged by Ram Sadotra - 1 team being mobilized at 152 section from 05-01-2026 & 2nd team required work front | Due to ROW
31 | 400 kV D/C Samba-Jalandhar | 2026-01-23 | 2026-02-01 | 9 | Closed | All site works | Due to heavy rains
32 | 400 kV D/C Samba-Jalandhar Kishenpur Samba Jammu Portion | 2026-02-01 | 2026-02-04 | 3 | Closed | All Foundation Works | Due to non availabilty of cement
33 | 400 kV D/C Samba-Jalandhar Jammu Portion | 2026-02-07 | 2026-02-08 | 2 | Closed | 23/1- Tower Erection Works | Due to ROW
34 | 400kV D/C Samba Kishenpur | 2026-03-06 | 2026-03-07 | 2 | Closed | AP10 - Foundation Work ROW Work Hampered , local villagers not allowing to do work | Due to ROW
35 | 400 kV D/C Samba-Jalandhar Punjab Portion | 2026-03-09 | 2026-03-09 | 1 | Closed | 130/2- Due to ROW , Tower Erection Work Hampered | Due to ROW
36 | 400 kV D/C Samba-Jalandhar 400 kV D/C Samba-Kishenpur LILO | 2026-03-15 | 2026-03-22 | 8 | Closed | Due to heavy rains all site works hampered | Due to Rains
37 | LILO -Kisthwar | 2026-03-22 | 2026-04-09 | 18 | Closed | Due to ROW work hampered at Loc: AP7 | ROW
38 | 400 kV D/C Samba-Jalandhar TL | 2026-04-04 | 2026-04-07 | 3 | Closed | Due to ROW at Loc: 40/3 - Work not yet started Since ROW not cleared as on 7-4-2026 . Loc AP1 allocated to the vendor as replacement | ROW
39 | 400 kV D/C Samba-Jalandhar 400 kV D/C Samba-Kishenpur LILO | 2026-04-07 | 2026-04-09 | 3 | Closed | Due to heavy rains all site works hampered | Due to Rains
40 | LILO -Kisthwar | 2026-04-06 | 2026-04-09 | 4 | Closed | Due to ROW work hampered at Loc: AP9 | ROW
41 | 400kV D/C Samba-Jalandhar | 2026-04-08 | 2026-04-10 | 3 | Closed | Due to ROW/ Crop Harvesting - Saritha Devi Erection Gang Idle since 08-04-2026 after completion of loc: AP70 | ROW
42 | 400kV D/C Samba-Jalandhar | 2026-04-02 | 2026-04-10 | 8 | Closed | Erection Material Shifting Completed at Loc: 114/0 , but due to ROW erection work not started. ROW resolved on 10-4-2026 . After completion of Loc AP85 gang will be engaged at loc | ROW
43 | LILO-Kisthwar | 2026-04-29 | 2026-05-01 | 3 | Closed | Due to heavy rains all site works hampered | Due to Rains
44 | LILO-Kisthwar | 2026-05-08 | 2026-05-09 | 2 | Closed | Due to ROW work hampered | ROW
45 | 400kV D/C Samba-Jalandhar | 2026-05-20 | 2026-05-21 | 2 | Closed | Due to ROW work hampered at loc: AP66 Ramesh Kumar Vendor | ROW
46 | 400kV D/C Samba-Jalandhar | 2026-05-25 | 2026-05-28 | 4 | Closed | Due to ROW erection work hampered at loc AP6. ROW not resolved gang planned to shift to loc: AP21 | ROW
47 | 400kV D/C Samba-Jalandhar | 2026-06-20 | 2026-06-22 | 3 | Closed | Erection gang idle at Loc: AP36 due to ROW ROW not resolved | ROW
48 | 400kV D/C Samba-Jalandhar | 2026-07-08 | 2026-07-09 | 2 | Closed | Erection gang work hampered at Loc: AP52 due to ROW | ROW
49 | 400kV D/C Samba-Jalandhar | 2026-07-09 | 2026-07-10 | 2 | Closed | Stringing Gang Work hampered due to ROW at section AP18-AP19 | ROW
50 | 400 kV D/C Samba-Jalandhar 400 kV D/C Samba-Kishenpur LILO | 2026-07-20 | 2026-07-25 | 6 | Closed | Due to heavy rains all site works hampered | Rains
51 | 400 kV D/C Samba-Jalandhar 400 kV D/C Samba-Kishenpur LILO | 2026-07-28 | 2026-07-31 | 4 | Closed | Due to heavy rains all site works hampered | Rains
52 | 400kV D/C Samba Jalandhar T/L (Punjab Portion) | 2026-07-03 | 2026-08-10 | 38 | Open | Due to paddy cultivation foundation /erection works hampered | Paddy Cultivaion
53 | 400kV D/C Samba Jalandhar T/L | 2026-07-31 | 2026-08-01 | 2 | Closed | Due to ROW work on hold for loc: 50A/6 | ROW
54 | 400kV D/C Samba Kishenpur T/L | 2026-08-02 | 2026-08-02 | 1 | Closed | Due to ROW issues material shifting work hampered at loc: AP86 Erection | ROW
55 | 400 kV D/C Samba-Jalandhar 400 kV D/C Samba-Kishenpur | 2026-08-03 | 2026-08-05 | 3 | Closed | Due to intermittent heavy rainfall works hampered | Rains
56 | 400kV D/C Samba Kishenpur | 2026-08-05 | 2026-08-10 | 5 | Closed | Maa Constructions gang at Loc: AP79 - Farmers not allowing to use approach road for material shifting
57 | 400 kV D/C Samba-Jalandhar 400 kV D/C Samba-Kishenpur LILO | 2026-08-08 | 2026-08-09 | 2 | Closed | Due to intermittent rainfall works hampered | Rains
58 | 400 kV D/C Samba-Jalandhar 400 kV D/C Samba-Kishenpur | 2026-08-11 | 2026-08-11 | 1 | Open | Due to heavy rainfall works hampered | Rains
Formulas:
To = [From]

## Manpower
[7 empty] | Date | 2026-08-11
Manpower in Gangs |  | Line | Qty | Manpower in Gangs |  | Line | Qty
Team | Foundation |  |  | Team | Tower Erection
1 | Thakur Const | J-S (Jammu) | 7 | 1 | Kushboo Devi | K-S | 28
2 | Vinay Constructions (Pile) | J-S (Punjab) | 20 | 2 | Jwala Singh | K-S | 25
3 | Ankush Sharma | K-S | 13 | 3 | Vijay Kumar Bhagat-2 | J-S (Jammu) | 24
4 | Naresh | K-S | 13 | 4 | Anvi Const | K-S | 20
5 | Ganesh | K-S | 10 | 5 | Vijay Kumar Bhagat-1 | J-S (Jammu) | 25
6 | BS Const | K-S | 12 | 6 | Jirwa Devi | K-S | 26
7 | Kulbhushan | K-S | 13 | 7 | Lalman Mahato | J-S (Punjab) | 24
8 | Rumal Singh | K-S | 12 | 8 | Spilce Net | K-S | 25
9 | RK Singh | K-S | 14 | 9 | Kajal Const | K-S | 30
10 | Anil Sharma | K-S | 10 | 10 | Neelkant | K-S | 20
11 | Darshan | K-S | 15 | 11 | Premlatha-1 | K-S | 30
12 | KDR Engineering | K-S | 8 | 12 | Premlatha-2 | K-S | 30
13 | Balwant Singh | K-S | 18 | 13 | Maa Construction | K-S | 28
14 | Bitu Kumar | LILO | 13 | 14 | Kauleshwar Mahato | K-S | 18
15 | Zaffar | LILO | 12 | 15 | Md.Jaleell | K-S | 15
16 | Bhat Const | LILO | 12 | Manpower in Gangs |  | Line | Qty
17 | TR Kothwal | LILO | 16 | Team | Stringing
18 | Abdul Jabbar | LILO | 14 | 1 | Tariq | J-S (Jammu) | 35
19 | KDR Engineering-2 | J-S (Punjab) | 8 | 2 | Janaual Sekh | J-S (Jammu) | 25
20 | Yogesh | K-S | 5 | 3&4 | Muslehudddin | J-S (Jammu) | 80
21 | Harsh | K-S | 8 | 5 | Nogyotech | K-S | 25
22 | Balwant Singh-2 | J-S (Jammu) | 8 | 6 | Gopal Associates | J-S (Jammu) | 15
Total |  |  | 261 |  | Total |  | 548

## Final Checking.
S.No | Line | Erection Completed | Final Checking Completed | Work Under Progress | Balance | Gangs | S.No | Gang Name | Manpower | Work done in loc- Jul-26 | Work done in Aug-26 | Working Loc-Aug-26
1 | Samba Jalandhar-Jammu | 104 | 44 | 5 | 55 | 6 | 1 | Budhi Yadav |  | AP21, AP29, AP17, 15/3, 15/2 |  | AP14
2 | Samba Jalandhar- Punjab | 155 | 44 |  | 111 |  | 2 | Amar Singh | 11 | 15/1, 29/2, 29/3, AP28, 27/1 |  | AP15
3 | Samba Kishenpur | 21 |  | 4 | 17 |  | 3&4 | Abhay Kumar Singh | 18 |  | 44/1 | 44/2
4 | LILO | [5 empty] | 5&6 | Aryan Const | 17 | AP46, AP47, 46/1, 46/2, 46/3, 46/4, 46/5 | 45/1, 45/2 | AP45, 44/3
Total |  | 280 | 88 | 9 | 183 |  | 7 | Budhi Yadav | 8 |  |  | 29/0, 30/0, 30/1, 31/0

## Sheet20
Final Checking for JS_J |  |  |  | Final Checking for JS_P
S.no | Location no | DOS | DoC | S.No | Loc | DOC
1 | 24/0 | 2026-04-16 | 2026-04-20 | 1 | 71/2 | 2026-04-16
2 | 25/0 | 2026-04-18 | 2026-04-20 | 2 | 80/0 | 2026-04-16
3 | 25/1 | 2026-04-19 | 2026-04-21 | 3 | 76/1 | 2026-04-16
4 | 25/2 | 2026-04-17 | 2026-04-21 | 4 | 76/2 | 2026-04-16
5 | 26/0 | 2026-04-22 | 2026-04-24 | 5 | 76/3 | 2026-04-16
6 | 27/0 | 2026-04-20 | 2026-04-24 | 6 | 77/0 | 2026-04-16
7 | 18/0 | 2026-05-14 | 2026-05-18 | 7 | 77/1 | 2026-04-16
8 | 18/1 | 2026-05-14 | 2026-05-18 | 8 | 77/2 | 2026-04-16
9 | 18/2 | 2026-05-18 | 2026-05-20 | 9 | 117/2 | 2026-02-17
10 | 19/0 | 2026-05-15 | 2026-05-20 | 10 | 117/3 | 2026-02-17
11 | 19/1 | 2026-05-18 | 2026-05-22 | 11 | 117/0 | 2026-04-15
12 | 19/2 | 2026-05-19 | 2026-05-22 | 12 | 117/1 | 2026-04-15
13 | 29/4 | 2026-05-20 | 2026-05-24 | 13 | 95/0 | 2026-04-27
14 | 29/5 | 2026-05-20 | 2026-05-24 | 14 | 94/0 | 2026-04-27
15 | 29/6 | 2026-05-21 | 2026-05-24 | 15 | 95/4 | 2026-04-27
16 | 31/0 | 2026-06-01 | 2026-06-05 | 16 | 95/3 | 2026-04-27
17 | 31/1 | 2026-06-03 | 2026-06-05 | 17 | 95/2 | 2026-04-27
18 | 31/2 | 2026-06-05 | 2026-06-08 | 18 | 96/O | 2026-04-27
19 | 31/3 | 2026-06-05 | 2026-06-08 | 19 | 95/1 | 2026-04-27
20 | 31/4 | 2026-06-08 | 2026-06-10 | 20 | 97/0 | 2026-03-05
21 | 31/5 | 2026-06-08 | 2026-06-10 | 21 | 92/1 | 2026-09-05
22 | 32/0 | 2026-06-07 | 2026-06-10 | 22 | 92/2 | 2026-09-05
23 | 23/2 | 2026-06-10 | 2026-06-15 | 23 | 93/0 | 2026-09-05
24 | 23/4 | 2026-06-10 | 2026-06-15 | 24 | 102/0 | 2026-07-05
25 | 23/5 | 2026-06-20 | 2026-06-23 | 25 | 103/0 | 2026-07-05
26 | 30/0 | 2026-06-20 | 2026-06-23 | 26 | 103/1 | 2026-07-05
27 | 20/0 | 2026-07-02 | 2026-07-07 | 27 | 104/0 | 2026-07-05
28 | 27/1 | 2026-07-04 | 2026-07-07 | 28 | 104/1 | 2026-08-05
29 | 46/0 | 2026-06-18 | 2026-06-20 | 29 | 106/0 | 2026-08-05
30 | 46/1 | 2026-06-18 | 2026-06-20 | 30 | 144/4 | 2026-12-05
31 | 46/2 | 2026-06-20 | 2026-06-22 | 31 | 145/1 | 2026-12-04
32 | 46/3 | 2026-06-20 | 2026-06-22 | 32 | 145/2 | 2026-12-05
33 | 46/4 | 2026-06-25 | 2026-06-28 | 33 | 97/1 | 2026-10-04
34 | 46/5 | 2026-07-04 | 2026-07-07 | 34 | 97/2 | 2026-04-17
35 | 47/0 | 2026-07-07 | 2026-07-10 | 35 | 97/3 | 2026-04-17
36 | 21/0 | 2026-07-10 | 2026-07-13 | 36 | 98/0 | 2026-10-04
37 | 28/0 | 2026-07-10 | 2026-07-13 | 37 | 99/0 | 2026-10-04
38 | 29/3 | 2026-07-14 | 2026-07-19 | 38 | 98/1 | 2026-10-04
39 | 29/1 | 2026-07-16 | 2026-07-19 | 39 | 100/0 | 2026-11-04
40 | 29/0 | 2026-07-15 | 2026-07-19 | 40 | 129/0 | 2026-05-23
41 | 44/1 | 2026-08-03 | 2026-08-09 | 41 | 130/1 | 2026-05-23
42 | 45/1 | 2026-08-05 | 2026-08-09 | 42 | 130/2 | 2026-05-23
43 | 45/2 | 2026-08-05 | 2026-08-09 | 43 | 131/2 | 2026-05-23
|  |  |  | 44 | 131/3 | 2026-05-23

## Stubs JS (hidden)
Stubs - SJ Line
Tower | Structure | UOM | Qty as per Approved C/S Jammu | Qty as per Approved C/S Punjab | Total Qty as per approved C/S | Material Received in Jammu | Material Received in Punjab | Total Received | Balance | Remarks
DA | STUB(UPTO+9M) | Set | 73 | 127 | 200 | 80 | 116 | 196 | 4
| 1M RC | Legs | 8 | 4 | 12 | 8 | 4 | 12 | 0
| 1.5M RC | Legs | 5 | 12 | 17 | 5 | 10 | 15 | 2
| 2M RC | Legs |  |  | 0 | 0 | 0 | 0 | 0
| 2M RC | Legs |  |  | 0 | 0 | 0 | 0 | 0
| 2.5M RC | Legs | 1 |  | 1 | 1 | 0 | 1 | 0
DB | STUB(UPTO+9M) | Set | 18 | 41 | 59 | 20 | 33 | 53 | 6
| 1M RC | Legs |  | 4 | 4 | 0 | 4 | 4 | 0
| 1.5M RC | Legs | 4 | 4 | 8 | 4 | 4 | 8 | 0
| 2M RC | Legs | 1 | 4 | 5 | 1 | 4 | 5 | 0
DC | STUB(UPTO+9M) | Set | 12 | 33 | 45 | 20 | 24 | 44 | 1
| 1M RC | Legs |  |  | 0 | 0 | 0 | 0 | 0
| 1.5M RC | Legs | 5 | 4 | 9 | 5 | 4 | 9 | 0
| 2M RC | Legs |  |  | 0 | 0 | 0 | 0 | 0
| 2.5M RC | Legs | 1 |  | 1 | 1 | 0 | 1 | 0
| 3M RC | Legs | 2 |  | 2 | 2 | 0 | 2 | 0
DD | STUB(UPTO+9M) | Set | 9 | 26 | 35 | 10 | 20 | 30 | 5
| 1M RC | Legs |  | 4 | 4 | 0 | 4 | 4 | 0
| 1.5M RC | Legs | 4 | 4 | 8 | 4 | 4 | 8 | 0
| 2M RC | Legs | 4 |  | 4 | 4 | 4 | 8 | -4 | Qty recived as per approved survey , but due to revison of survey qty became excess
| 3M RC | Legs |  |  | 0 | 0 | 0 | 0 | 0
| STUB (+18/+25/+30M) | Set | 10.25 | 32 | 42.25 | 5 | 25 | 30 | 12.25
| 1.5M RC | Legs | 3 |  | 3 | 3 | 0 | 3 | 0
| 2M RC | Legs | 10 | 28 | 38 | 4 | 28 | 32 | 6
| 4M RC | Legs | 4 |  | 4 | 4 | 0 | 4 | 0
| 3M RC | Legs | 6 | 4 | 10 | 2 | 0 | 2 | 8
| 5M RC | Legs | 2 | 4 | 6 | 2 | 0 | 2 | 4
Total |  |  | 126 | 263 | 389 | 138.75 | 222 | 360.75 | 28.25

## Stubs SK (hidden)
Stubs - SK Line
Tower | Structure | UOM | Qty as per C/S. Approved | Material Received | Balance to be Supplied | Inspection Completd on 18-May-26 & QCN Received | Remarks
DA | STUB(UPTO+9M) | Set | 1 | 2 | -1 |  | Qty recived as per approved survey , but due to revison of survey qty became excess
| 1M RC | Leg |  | 0 | 0
| 1.5M RC | Leg |  | 2 | -2 |  | Qty recived as per approved survey , but due to revison of survey qty became excess
| 2M RC | Leg |  | 0 | 0
| 2.5M RC | Leg |  | 0 | 0
DB | STUB(UPTO+9M) | Set | 33.5 | 31 | 2.5 | 2
| 1M RC | Leg | 6 | 6 | 0
| 1.5M RC | Leg | 16 | 15 | 1 | 1
| 2M RC | Leg | 4 | 4 | 0
| 3M RC | Leg | 8 | 8 | 0
| 5M RC | Leg | 1 | 0 | 1 | 1
| 6M RC | Leg | 1 | 0 | 1 | 1
| 8M RC | Leg | 2 | 0 | 2 | 2
| 12M RC | Leg | 1 | 0 | 1 | 1
DC | STUB(UPTO+9M) | Set | 33.25 | 31 | 2.25 | 2
| 1M RC | Leg | 7 | 7 | 0
| 1.5M RC | Leg | 4 | 4 | 0
| 2M RC | Leg | 8 | 7 | 1 | 1
| 2.5M RC | Leg |  | 0 | 0
| 3M RC | Leg | 8 | 8 | 0
| 4M RC | Leg | 1 | 0 | 1 | 1
| 5M RC | Leg | 2 | 2 | 0
| 8M RC | Leg | 1 | 0 | 1 | 1
| 10M RC | Leg | 2 | 0 | 2 | 2
DD | STUB(UPTO+9M) | Set | 33.5 | 28 | 5.5 | 3
| 1M RC | Leg | 4 | 5 | -1 |  | Qty recived as per approved survey , but due to revison of survey qty became excess
| 1.5M RC | Leg | 6 | 5 | 1
| 2M RC | Leg | 10 | 9 | 1 | 1
| 3M RC | Leg | 5 | 5 | 0
| 4M RC | Leg | 3 | 3 | 0
| 5M RC | Leg | 1 | 1 | 0
| 6M RC | Leg | 6 | 6 | 0
| 7M RC | Leg | 1
| 9M RC | Leg | 1 | 1 | 0
| STUB (+18/+25/+30M) | Set | 8.5 | 5 | 3.5 | 1
| 1M RC | Leg | 1 | 1 | 0
| 1.5M RC | Leg | 1 | 1 | 0
| 2M RC | Leg | 7 | 5 | 2 | 2
| 4M RC | Leg | 8 | 3 | 5
| 3M RC | Leg | 3 | 2 | 1 | 1
| 5M RC | Leg | 4 | 2 | 2
| 7M RC | Leg | 1 |  | 1
Total |  | Set | 116 | 103.25 | 12.75 | 8

## Towers JS (hidden)
TOWERS - SJ Line
Tower | Structure | Qty as per Approved C/S Jammu | Qty as per Approved C/S Punjab | Total Qty as per approved C/S | Material Received in Jammu | Material Received in Punjab | Total Received | Inspection Call 18th May |  | Balance | Remarks
[8 empty] | Jammu | Punjab
DA | Basic Tower Body | 75 | 128 | 203 | 84 | 100 | 184 |  |  | 19
| +0MBE | 51 | 91 | 142 | 62 | 61 | 123 |  |  | 19
| +3MBE | 24 | 37 | 61 | 22 | 39 | 61 |  |  | 0
| +6MBE | 10 | 15 | 25 | 10 | 14 | 24 |  |  | 1
| +9MBE | 2 | 6 | 8 | 2 | 5 | 7 |  |  | 1
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0
DB | Basic Tower Body | 18 | 42 | 60 | 12 | 42 | 54 |  |  | 6
| +0MBE | 17 | 36 | 53 | 6 | 33 | 39 | 5 | 3 | 6
| +3MBE | 1 | 6 | 7 | 1 | 6 | 7 |  |  | 0
| +6MBE | 2 | 4 | 6 | 1 | 2 | 3 |  | 2 | 1
| +9MBE | 2 | 7 | 9 | 2 | 5 | 7 |  | 1 | 1 |  | 17175
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0
DC | Basic Tower Body | 12 | 31 | 43 | 27 | 16 | 43 |  |  | 0
| +0MBE | 8 | 24 | 32 | 21 | 6 | 27 | 2 | 3 | 0
| +3MBE | 4 | 7 | 11 | 4 | 6 | 10 |  | 1 | 0
| +6MBE | 1 | 1 | 2 | 0 | 2 | 2 | 1 |  | -1 | Due to revision in survey , qty became excess
| +9MBE | 1 | 4 | 5 | 1 | 4 | 5 | 1 |  | -1 | Due to revision in survey , qty became excess
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0
DD | Basic Tower Body | 21 | 60 | 81 | 19 | 37 | 56 |  |  | 25
| +0MBE | 20 | 53 | 73 | 17 | 30 | 47 | 1 | 2 | 23
| +3MBE | 1 | 7 | 8 | 1 | 5 | 6 |  |  | 2
| +6MBE | 1 | 3 | 4 | 1 | 2 | 3 |  |  | 1
| +9MBE | 3 | 5 | 8 | 3 | 5 | 8 |  |  | 0
| +18MBE | 1 | 11 | 12 | 1 | 9 | 10 |  |  | 2 | Strengthening members supply pending
| +25MBE | 4 | 10 | 14 | 5 | 5 | 10 |  | 1 | 3 | Strengthening members supply pending
| +30MBE | 6 | 11 | 17 | 3 | 4 | 7 |  | 1 | 9 | Strengthening members supply pending
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0
DCT | Basic Tower Body |  | 2 | 2 | 0 | 0 | 0 |  |  | 2
| +0MBE |  | 2 | 2 | 0 | 0 | 0 |  |  | 2
Total |  | 126 | 263 | 389 | 142 | 195 | 337 | 0 | 0 | 52

## Towers SK (hidden)
Tower SK Line
Tower | Structure | Qty as per C/S. Approved | Material Received | Inspection Call 18th May | Balance | Remarks
DA | Basic Tower Body | 1 | 1 |  | 0
| +0MBE | 1 | 1 |  | 0
|  |  | 0 |  | 0
DB | Basic Tower Body | 35 | 33 |  | 2
| +0MBE | 13 | 14 |  | -1 | Will be used in JS line
| +3MBE | 3 | 2 |  | 1
| +6MBE | 1 | 1 |  | 0
| +9MBE | 6 | 5 | 1 | 0
| -3MLE | 28 | 11 | 13 | 4
| -1.5MLE | 9 | 6 | 3 | 0
| +0MLE | 12 | 8 |  | 4
| +1.5MLE | 10 | 8 | 2 | 0
| +3MLE | 17 | 7 | 10 | 0
| +4.5MLE | 1 | 1 |  | 0
| +6MLE | 7 | 2 | 5 | 0
| +7.5MLE | 1 | 1 |  | 0
| +9MLE | 7 | 0 | 7 | 0
|  |  | 0 |  | 0
DC | Basic Tower Body | 35 | 33 |  | 2
| +0MBE | 13 | 12 |  | 1
| +3MBE | 1 | 1 |  | 0
| +6MBE |  | 0 |  | 0
| +9MBE | 5 | 3 | 2 | 0
| -3MLE | 31 | 19 | 12 | 0
| -1.5MLE | 13 | 8 | 5 | 0
| +0MLE | 15 | 7 | 4 | 4
| +1.5MLE | 7 | 3 | 4 | 0
| +3MLE | 18 | 7 | 11 | 0
| +4.5MLE | 2 | 0 |  | 2
| +6MLE | 5 | 1 | 4 | 0
| +7.5MLE | 5 | 1 | 4 | 0
| +9MLE | 16 | 6 | 8 | 2
|  |  | 0 |  | 0
DD | Basic Tower Body | 41 | 35 |  | 6
| +0MBE | 27 | 15 | 7 | 5
| +3MBE | 1 | 1 |  | 0
| +6MBE | 1 | 0 |  | 1
| +9MBE | 9 | 5 | 1 | 3
| -3MLE | 10 | 7 | 3 | 0
| -1.5MLE | 5 | 2 | 1 | 2
| +0MLE | 24 | 9 | 13 | 2
| +1.5MLE | 5 | 3 | 2 | 0
| +3MLE | 8 | 7 |  | 1
| +4.5MLE |  | 0 |  | 0
| +6MLE | 5 | 1 | 3 | 1
| +7.5MLE | 3 | 0 |  | 3
| +9MLE | 12 | 0 | 12 | 0
| +18MBE | 6 | 0 | 1 | 5
| +25MBE | 1 | 0 |  | 1
Total |  | 112 | 102 | 0 | 10

## Sum (hidden)
Foundation
S.No | Line | Gangs Available | Additional Gangs |  | Total Gangs
|  |  | Planned by 3rd May | Planned by 10th May
1 | Samba-Jalandhar | 18 | 1 | 4 | 23
2 | Samba-Kishenpur | 6 |  |  | 6
3 | LILO-Kisthwar | 3 |  |  | 3
|  | 27 | 1 | 4 | 32
Tower Erection
S.No | Line | Gangs Available | Additional Gangs
|  |  | Planned by 3rd May | Planned by 10th May | Total Gangs
1 | Samba-Jalandhar | 9 | 3 | 4 | 16
2 | Samba-Kishenpur |  |  | 4 | 4
|  | 9 | 3 | 8 | 20
Stringing
S.No | Line | Gangs Available | Additional Gangs
|  |  | Planned by 3rd May | Planned by 10th May | Total Gangs
1 | Samba-Jalandhar |  |  | 1 | 1
|  |  |  | 1 | 1

## Sheet18 (hidden)
Foundation |  |  |  |  | Tower Erection |  |  |  |  | Stringing
Samba- Jalandhar TL-Jammu |  |  |  |  | Samba- Jalandhar TL-Jammu |  |  |  |  | Samba- Jalandhar TL
S.No | Sub Vendor | Available | Mobilization Planned | Remarks | S.No | Sub Vendor | Available | Mobilization Planned | Remarks | S.No | Sub Vendor | Available | Mobilization Planned | Remarks
1 | Balwant Singh-1 | 11 |  |  | 1 | Kushboo Devi-1 | 20 |  |  | 1 | Jiyaul Hoque |  | 10 | Mob Planned by 10th May
2 | Balwant Singh-2 | 10 |  |  | 2 | Kushboo Devi-2 | 22 |  |  | Total |  |  | 10
3 | Pawan Sharma-1 | 12 |  |  | 3 | ASIC Infra | 23
4 | Pawan Sharma-2 | 10 |  |  | 4 | Niva Sarkar Mandal |  | 20 | Mob Planned by 3rd May
5 | Anil Sharma | 10 |  |  | Total |  | 65 | 20
6 | TCC | 10
7 | Pawan Sharma-3 |  | 12 | Mob Planned by 10th May
8 | Samsad |  | 13 | Mob Planned by 8th May
9 | VR Construction |  | 12 | Mob Planned by 6th May
Total |  | 63 | 37
Samba- Jalandhar TL-Punjab |  |  |  |  | Samba- Jalandhar TL- Punjab
S.No | Sub Vendor | Available | Mobilization Planned | Remarks | S.No | Sub Vendor | Available | Mobilization Planned | Remarks
1 | Tapseer | 11 |  |  | 1 | Saritha Devi | 24
2 | Sufiyan Ali-1 | 11 |  |  | 2 | Jwala Singh | 25
3 | Sufiyan Ali-2 | 10 |  |  | 3 | Vijay B-1 | 20
4 | Sufiyan Ali-3 | 10 |  |  | 4 | ZR Construction-1 | 21
5 | KDR Engg | 12 |  |  | 5 | Rakesh-1 | 23
6 | Aman Enterprises | 10 |  |  | 6 | Vijay Kumar Bhagat | 20
7 | Ramesh | 12 |  |  | 7 | ZR Construction-2 |  | 20 | Mob Planned by 8th May
8 | MS Construction | 16 |  |  | 8 | Rakesh -2 |  | 24 | Mob Planned by 10th May
9 | MS Hussain | 12 |  |  | 9 | Karni Const-1 |  | 20 | Mob Planned by 3rd May
10 | Ikrar | 13 |  |  | 10 | Karni Const-2 |  | 20 | Mob Planned by 3rd May
11 | Ram Sadotra-1 | 12 |  |  | 11 | Karni Const-3 |  | 22 | Mob Planned by 6th May
12 | Ram Sadotra-2 | 10 |  |  | 12 | Karni Const-4 |  | 21 | Mob Planned by 6th May
13 | Ramji Structre-1 |  | 12 | Mob Planned by 3rd May | Total |  | 133 | 127
14 | Ramji Structre-2 |  | 12 | Mob Planned by 5th May
Total |  | 139 | 24
Samba-Kishenpur
Samba-Kishenpur |  |  |  |  | S.No | Sub Vendor | Available | Mobilization Planned | Remarks
S.No | Sub Vendor | Available | Remarks |  | 1 | Anvi Construction |  | 20 | Mob Planned by 5th May
1 | Naresh | 12 |  |  | 2 | Horil Mahato |  | 22 | Mob Planned by 7th May
2 | Ankush Sharma | 13 |  |  | 3 | Jaya Prakash Mahato |  | 23 | Mob Planned by 10th May
3 | Ganesh | 10 |  |  | 4 | Mohan Mahato |  | 20 | Mob Planned by 10th May
4 | Rumal Singh | 10 |  |  | Total |  |  | 85
5 | BS Construction | 10
6 | Kalbushan | 11
Total |  | 66
LILO -Kisthwar
S.No | Sub Vendor | Available | Remarks
1 | Zaffar | 8
2 | Bittu | 14
3 | Bhat Const. | 17
Total |  | 39

## JS-Supply Stubs (hidden)
Stubs - SJ Line
Tower | Structure | UOM | Qty as per Approved C/S Jammu | Qty as per Approved C/S Punjab | Total Qty as per approved C/S | Material Received in Jammu | Material Received in Punjab | Total Received | Balance | Remarks
DA | STUB(UPTO+9M) | Set | 74 | 124 | 198 | 80 | 116 | 196 | 2
| 1M RC | Legs | 8 | 4 | 12 | 8 | 4 | 12 | 0
| 1.5M RC | Legs | 5 | 12 | 17 | 5 | 10 | 15 | 2
| 2M RC | Legs |  |  | 0 |  | 0 | 0 | 0
| 2M RC | Legs |  |  | 0 |  | 0 | 0 | 0
| 2.5M RC | Legs | 1 |  | 1 | 1 | 0 | 1 | 0 |  | DA | 5
DB | STUB(UPTO+9M) | Set | 17 | 38 | 55 | 20 | 33 | 53 | 2 |  | DB | 5
| 1M RC | Legs |  | 4 | 4 |  | 4 | 4 | 0 |  | DC | 2
| 1.5M RC | Legs | 4 | 4 | 8 | 4 | 4 | 8 | 0 |  | DD | 2
| 2M RC | Legs | 1 |  | 1 | 1 | 4 | 5 | -4 | Qty recived as per approved survey , but due to revison of survey qty became excess
DC | STUB(UPTO+9M) | Set | 13 | 33 | 46 | 20 | 24 | 44 | 2
| 1M RC | Legs |  |  | 0 |  | 0 | 0 | 0
| 1.5M RC | Legs | 5 | 4 | 9 | 5 | 4 | 9 | 0
| 2M RC | Legs |  |  | 0 |  | 0 | 0 | 0
| 2.5M RC | Legs | 1 |  | 1 | 1 | 0 | 1 | 0
| 3M RC | Legs | 2 |  | 2 | 2 | 0 | 2 | 0
DD | STUB(UPTO+9M) | Set | 10 | 20 | 30 | 10 | 20 | 30 | 0
| 1M RC | Legs |  | 4 | 4 |  | 4 | 4 | 0
| 1.5M RC | Legs | 4 | 4 | 8 | 4 | 4 | 8 | 0
| 2M RC | Legs | 4 |  | 4 | 4 | 4 | 8 | -4 | Qty recived as per approved survey , but due to revison of survey qty became excess
| 3M RC | Legs |  |  | 0 |  | 0 | 0 | 0
| STUB (+18/+25/+30M) | Set | 9.25 | 22 | 31.25 | 8 | 22 | 30 | 1.25
| 1.5M RC | Legs | 3 |  | 3 | 3 | 0 | 3 | 0
| 2M RC | Legs | 8 | 24 | 32 | 4 | 28 | 32 | 0
| 4M RC | Legs | 4 |  | 4 | 4 | 0 | 4 | 0
| 3M RC | Legs | 2 |  | 2 | 2 | 0 | 2 | 0
| 5M RC | Legs | 2 |  | 2 | 2 | 0 | 2 | 0
Total |  |  | 127 | 241 | 368 | 141.75 | 219 | 360.75 | 7.25

## JS Supply Towers (hidden)
TOWERS - SJ Line
Tower | Structure | Qty as per Approved C/S Jammu | Qty as per Approved C/S Punjab | Total Qty as per approved C/S | Material Received in Jammu | Material Received in Punjab | Total Received | Inspection Completed on 18th Mar'26 and Material under transit | Balance | Remarks
DA | Basic Tower Body | 76 | 125 | 201 | 84 | 98 | 182 |  | 19
| +0MBE | 52 | 88 | 140 | 62 | 59 | 121 |  | 19
| +3MBE | 24 | 37 | 61 | 22 | 39 | 61 |  | 0
| +6MBE | 10 | 14 | 24 | 10 | 14 | 24 |  | 0
| +9MBE | 2 | 5 | 7 | 2 | 3 | 5 |  | 2
|  |  |  | 0 | 0 | 0 | 0 |  | 0
DB | Basic Tower Body | 17 | 39 | 56 | 7 | 39 | 46 |  | 10
| +0MBE | 16 | 33 | 49 | 6 | 33 | 39 |  | 10
| +3MBE | 1 | 6 | 7 | 1 | 6 | 7 |  | 0
| +6MBE | 1 | 4 | 5 | 1 | 2 | 3 |  | 2
| +9MBE | 2 | 6 | 8 | 2 | 5 | 7 |  | 1
|  |  |  | 0 | 0 | 0 | 0 |  | 0
DC | Basic Tower Body | 13 | 32 | 45 | 23 | 10 | 33 | 4 | 8
| +0MBE | 9 | 25 | 34 | 20 | 5 | 25 | 2 | 7
| +3MBE | 4 | 7 | 11 | 3 | 5 | 8 | 2 | 1
| +6MBE | 1 | 2 | 3 | 0 | 2 | 2 |  | 1
| +9MBE | 2 | 4 | 6 | 0 | 3 | 3 | 2 | 1
|  |  |  | 0 | 0 | 0 | 0 |  | 0
DD | Basic Tower Body | 21 | 44 | 65 | 18 | 35 | 53 |  | 12
| +0MBE | 20 | 39 | 59 | 17 | 30 | 47 |  | 12
| +3MBE | 1 | 5 | 6 | 1 | 5 | 6 |  | 0
| +6MBE | 1 | 2 | 3 | 1 | 2 | 3 |  | 0
| +9MBE | 3 | 5 | 8 | 3 | 5 | 8 |  | 0
| +18MBE | 1 | 10 | 11 | 0 | 0 | 0 | 6 | 5
| +25MBE | 4 | 8 | 12 | 0 | 0 | 0 | 8 | 4
| +30MBE | 5 | 4 | 9 | 0 | 0 | 0 | 1 | 8
|  |  |  | 0 | 0 | 0 | 0 |  | 0
DCT | Basic Tower Body |  | 1 | 1 | 0 | 0 | 0 |  | 1
| +0MBE |  | 1 | 1 | 0 | 0 | 0 |  | 1
Total |  | 127 | 241 | 368 | 132 | 182 | 314 | 4 | 50

## SK Supply Stubs (hidden)
Stubs - SK Line
Tower | Structure | UOM | Qty as per C/S. Approved | Material Received | Balance | Remarks
DA | STUB(UPTO+9M) | Set | 1 | 2 | -1 | Qty recived as per approved survey , but due to revison of survey qty became excess
| 1M RC | Leg |  | 0 | 0
| 1.5M RC | Leg |  | 2 | -2 | Qty recived as per approved survey , but due to revison of survey qty became excess
| 2M RC | Leg |  | 0 | 0
| 2.5M RC | Leg |  | 0 | 0
DB | STUB(UPTO+9M) | Set | 33.5 | 31 | 2.5 |  | 1.5
| 1M RC | Leg | 6 | 6 | 0
| 1.5M RC | Leg | 16 | 15 | 1
| 2M RC | Leg | 4 | 4 | 0
| 3M RC | Leg | 8 | 8 | 0
| 5M RC | Leg | 1 | 0 | 1
| 6M RC | Leg | 1 | 0 | 1
| 8M RC | Leg | 2 | 0 | 2
| 12M RC | Leg | 1 | 0 | 1
DC | STUB(UPTO+9M) | Set | 33.25 | 31 | 2.25
| 1M RC | Leg | 7 | 7 | 0
| 1.5M RC | Leg | 4 | 4 | 0
| 2M RC | Leg | 8 | 7 | 1
| 2.5M RC | Leg |  | 0 | 0
| 3M RC | Leg | 8 | 8 | 0
| 4M RC | Leg | 1 | 0 | 1
| 5M RC | Leg | 2 | 2 | 0
| 8M RC | Leg | 1 | 0 | 1
| 10M RC | Leg | 2 | 0 | 2
DD | STUB(UPTO+9M) | Set | 31.75 | 28 | 3.75
| 1M RC | Leg | 4 | 5 | -1 | Qty recived as per approved survey , but due to revison of survey qty became excess
| 1.5M RC | Leg | 5 | 5 | 0
| 2M RC | Leg | 10 | 9 | 1
| 3M RC | Leg | 5 | 5 | 0
| 4M RC | Leg | 3 | 3 | 0
| 5M RC | Leg | 1 | 1 | 0
| 6M RC | Leg | 6 | 6 | 0
| 7M RC | Leg | 1 | 0 | 1
| 9M RC | Leg | 1 | 1 | 0
| STUB (+18/+25/+30M) | Set | 6.5 | 5 | 1.5
| 1M RC | Leg | 1 | 1 | 0
| 1.5M RC | Leg | 1 | 1 | 0
| 2M RC | Leg | 7 | 5 | 2
| 4M RC | Leg | 3 | 3 | 0
| 3M RC | Leg | 3 | 2 | 1
| 5M RC | Leg | 2 | 2 | 0
Total |  | Set | 112 | 103.25 | 8.75

## SK Supply Towers (hidden)
Tower SK Line
Tower | Structure | Qty as per C/S. Approved | Material Supplied till date (21st Feb'26) | Inspection Completed on 18th Mar'26 and Material under transit | Balance | Remarks
DA | Basic Tower Body | 1 |  |  | 1
| +0MBE | 1 |  |  | 1
0
DB | Basic Tower Body | 35 | 14 | 7 | 14
| +0MBE | 13 | 14 |  | -1 | Will be used in JS line
| +3MBE | 3 |  | 2 | 1
| +6MBE | 1 |  | 1 | 0
| +9MBE | 6 | 4 | 1 | 1
| -3MLE | 28 |  |  | 28
| -1.5MLE | 9 |  |  | 9
| +0MLE | 12 |  | 8 | 4
| +1.5MLE | 10 |  |  | 10
| +3MLE | 17 |  | 7 | 10
| +4.5MLE | 1 |  |  | 1
| +6MLE | 7 |  | 2 | 5
| +7.5MLE | 1 |  |  | 1
| +9MLE | 7 |  |  | 7
0
DC | Basic Tower Body | 35 | 12 | 6 | 17
| +0MBE | 13 | 12 |  | 1
| +3MBE | 1 |  | 1 | 0
| +6MBE |  |  |  | 0
| +9MBE | 5 | 2 | 1 | 2
| -3MLE | 31 |  |  | 31
| -1.5MLE | 13 |  |  | 13
| +0MLE | 15 |  | 7 | 8
| +1.5MLE | 7 |  |  | 7
| +3MLE | 18 |  | 7 | 11
| +4.5MLE | 2 |  |  | 2
| +6MLE | 5 |  | 1 | 4
| +7.5MLE | 5 |  |  | 5
| +9MLE | 16 |  | 6 | 10
0
DD | Basic Tower Body | 41 | 15 | 7 | 19
| +0MBE | 27 | 15 |  | 12
| +3MBE | 1 |  | 1 | 0
| +6MBE | 1 |  |  | 1
| +9MBE | 9 | 5 |  | 4
| -3MLE | 10 |  |  | 10
| -1.5MLE | 5 |  |  | 5
| +0MLE | 24 |  | 9 | 15
| +1.5MLE | 5 |  |  | 5
| +3MLE | 8 |  | 7 | 1
| +4.5MLE |  |  |  | 0
| +6MLE | 5 |  | 1 | 4
| +7.5MLE | 3 |  |  | 3 | BOM not available
| +9MLE | 12 |  |  | 12
| +18MBE | 6 |  |  | 6
| +25MBE | 1 |  |  | 1
Total |  | 112 | 41 | 20 | 51

## Sheet11 (hidden)
Project Name | Transmission Scheme for Evacuation of Power From Ratle HEP (850 MW) & Kiru HEP (624MW): Part-A
Client | RATLE KIRU POWER TRANSMISSION EMPLOYER LIMITED
LOA DATE (Start Date) | 16th MAY 2025
Name of the Line |  | KM | Months | Comp Date
400 kV Samba- Jalandhar D/C line (Quad) |  | 137 | 20 | 2027-01-15
400 kV Kishenpur-Samba D/C line (Quad) |  | 33 | 22 | 2027-03-15
LILO of 400 kV Kishenpur- Dulhasti line (Twin) at Kishtwar S/s |  | 3.4 | 18 | 2026-11-15
173.4
Contract Value (Exc.GST) |  | 415 Cr
173.4
523

## Planned Vs Actual -FDN (hidden)
KEC INTERNATIONAL LIMITED
400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5
FOUNDATION -Plan Vs Actual
Week | W1 (1-7) | W2 (8-14) | W3 (15-21) | W4 (22-30) | Total
Planned | 1 | 3 | 7 | 8 | 19
Actual | 1 |  | 1 | 1 | 3
Sr. No. | Section | Loc. No. | Tower Type | Classification | Status | Planned | [5 empty] | Actual |  | Remark
|  | Loc. No. | Tower Type | Classification | Status | Start | End | Start | End | Start | End | Start | End
1 | Jammu | 29/3 | DA+0 | Dry | ROW Clear | 2025-08-31 | 2025-09-04 | 2025-09-02 | 2025-09-05 | 2025-09-04 | 2025-09-09 | 2025-08-31 | 2025-09-24
2 |  | AP27 | DB+0 | Wet | ROW Clear | 2025-09-09 | 2025-09-14 | 2025-09-12 | 2025-09-16 | 2025-09-14 | 2025-09-20 | 2025-09-07 | 2025-09-20
3 |  | 30/3 | DA+6 | PS | ROW Clear | 2025-09-20 | 2025-09-24 | 2025-09-22 | 2025-09-25 | 2025-09-24 | 2025-09-27 | 2025-09-30 |  | Boring u/p
4 |  | 29/6 | DA+0 | PS | ROW Clear | 2025-08-28 | 2025-09-02 | 2025-08-30 | 2025-09-03 | 2025-09-02 | 2025-09-07 | 2025-09-26 |  | Excavation u/p
5 |  | AP17 | DC+3 | FS | ROW Clear | 2025-09-07 | 2025-09-12 | 2025-09-10 | 2025-09-14 | 2025-09-12 | 2025-09-18 | 2025-09-10 |  | Excavation u/p
6 |  | AP18 | DC+0 | FS | ROW Clear | 2025-09-18 | 2025-09-23 | 2025-09-21 | 2025-09-25 | 2025-09-23 | 2025-09-29 | 2025-09-11 |  | 1 pit Casting Completed
7 |  | 23/1 | DA+3 | WET | ROW Clear | 2025-09-02 | 2025-09-05 | 2025-09-04 | 2025-09-07 | 2025-09-05 | 2025-09-09 | 2025-09-25 |  | Boring u/p
8 |  | 35/1 | DA+6 |  | Standing Crop | 2025-09-08 | 2025-09-11 | 2025-09-10 | 2025-09-13 | 2025-09-11 | 2025-09-15
9 |  | 37/1 | DA+3 |  | Standing Crop | 2025-09-14 | 2025-09-17 | 2025-09-16 | 2025-09-19 | 2025-09-17 | 2025-09-21
10 |  | 37/2 | DA+3 |  | Standing Crop | 2025-09-20 | 2025-09-23 | 2025-09-22 | 2025-09-25 | 2025-09-23 | 2025-09-27
11 | Punjab | 90/1 | DA+3 | WET | ROW Clear | 2025-09-05 | 2025-09-09 | 2025-09-07 | 2025-09-10 | 2025-09-09 | 2025-09-12 | 2025-09-25 |  | Excavation u/p
12 |  | 117/1 | DA+0 |  | Standing Crop | 2025-09-11 | 2025-09-15 | 2025-09-13 | 2025-09-16 | 2025-09-15 | 2025-09-18
13 |  | 117/3 | DA+0 |  | Standing Crop | 2025-09-20 | 2025-09-24 | 2025-09-22 | 2025-09-25 | 2025-09-24 | 2025-09-28
14 |  | 56/4 | DA+6 |  | Standing Crop | 2025-09-08 | 2025-09-12 | 2025-09-10 | 2025-09-13 | 2025-09-12 | 2025-09-15
15 |  | 56/2 | DA+3 |  | Standing Crop | 2025-09-15 | 2025-09-19 | 2025-09-17 | 2025-09-20 | 2025-09-19 | 2025-09-22
16 |  | 57/1 | DA+0 |  | Standing Crop | 2025-09-22 | 2025-09-26 | 2025-09-24 | 2025-09-27 | 2025-09-26 | 2025-09-29
17 |  | 65/3 | DA+0 |  | Standing Crop | 2025-09-08 | 2025-09-12 | 2025-09-10 | 2025-09-13 | 2025-09-12 | 2025-09-15
18 |  | 65/2 | DA+6 |  | Standing Crop | 2025-09-15 | 2025-09-19 | 2025-09-17 | 2025-09-20 | 2025-09-19 | 2025-09-22
19 |  | 65/5 | DA+0 |  | Standing Crop | 2025-09-22 | 2025-09-26 | 2025-09-24 | 2025-09-27 | 2025-09-26 | 2025-09-29
400 kV Samba- Kishanpur D/C Line(Quad) - Wind Zone - 5
FOUNDATION -Plan Vs Actual
| Week | W1 (1-7) | W2 (8-14) | W3 (15-21) | W4 (22-30) | Total
| Planned |  |  | 2 | 1 | 3
| Actual |  |  |  |  | 0
| Sr. No. | Loc. No. | Tower Type | Classification | Status | Planned | [5 empty] | Actual |  | Remark
[6 empty] | Date | Date | Start | End | Start | End | Start | End
| 1 | AP106 | DB+0 |  |  | 2025-09-04 | 2025-09-15 | 2025-09-07 | 2025-09-12 | 2025-09-09 | 2025-09-15 |  |  | Due to heavy rains/floods & lanslides works hampered
| 2 | AP107 | DC+0 |  |  | 2025-09-14 | 2025-09-25 | 2025-09-17 | 2025-09-22 | 2025-09-19 | 2025-09-25
| 3 | AP97 | DC+0 |  |  | 2025-09-10 | 2025-09-21 | 2025-09-13 | 2025-09-18 | 2025-09-15 | 2025-09-21
LILO Line
FOUNDATION -Plan Vs Actual
| Week | W1 (1-7) | W2 (8-14) | W3 (15-21) | W4 (22-30) | Total
| Planned |  |  | 1 |  | 1
Actual
| Sr. No. | Loc. No. | Tower Type | Classification | Status | Planned | [5 empty] | Actual |  | Remark
|  | Loc. No. | Tower Type | Classification | Status | Start | End | Start | End | Start | End | Start | End
| 1 | AP8 | DDM+0 |  |  | 2025-09-08 | 2025-09-15 | 2025-08-12 | 2025-09-16 | 2025-09-14 | 2025-09-21 |  |  | Due to heavy rains , landslides occurred and road blocked. Hence foundation works will be planned after improvement of weather conditions
Formulas:
End = [Planned]+5
End = [Start]+4
Start = [Planned]+3
Start = [Start]+2

## Supply Status (hidden)
Samba-Jalandhar (Stubs) | [6 empty] | Samba-Kishenpur (Stubs) | [6 empty] | LILO-Kishtwar (Stubs)
S.No | Stub | Qty asper approved Survey | L2 till Feb'26 | Supplied Qty till date | Supply u/p | Remarks | S.No | Stub | Qty asper approved Survey | L2 till Feb'26 | Supplied Qty till date | Supply u/p | Remarks | S.No | Stub | Qty asper Survey | L2 till Feb'26 | Supplied Qty till date
1 | DA | 201 | 434 | 186 |  |  | 1 | DA | 1 | 129 | 2 |  |  | 1 | DDM | 13 | 14 | 10
2 | DB | 57 |  | 49 |  |  | 2 | DB | 20 |  | 18.75 |  |  | Total |  | 13 | 14 | 10
3 | DC | 44 |  | 38 |  |  | 3 | DC | 21 |  | 16.75
4 | DD | 63 |  | 54 |  |  | 4 | DD | 29 |  | 26
Total |  | 365 | 434 | 327 |  |  | Total |  | 71 | 129 | 63.5
Samba-Jalandhar (Stubs) | [6 empty] | Samba-Kishenpur(Towers) | [6 empty] | LILO-Kishtwar (Tower)
S.No | Tower | Qty asper approved Survey | L2 till Feb'26 | Supplied Qty till date | Supply u/p | Remarks | S.No | Tower | Qty asper approved Survey | L2 till Feb'26 | Supplied Qty till date | Supply u/p | Remarks | S.No | Tower | Qty asper Survey | L2 till Feb'26 | Supplied Qty till date
38
1 | DA | 11 | 216 |  |  |  | 1 | BTB |  | 100 |  |  |  | 1 | DDM | 13 | 14
| BTB | 201 |  | 171 |  |  |  | 0M | [5 empty] | Total |  | 13 | 14
| 0M | 140 |  | 110 |  |  |  | 3M
| 3M | 61 |  | 61
| 6M | 25 |  | 22 |  |  |  | 6M
| 9M | 6 |  | 4 |  |  |  | 9M
2 | DB | [5 empty] | 2 | DB
| BTB | 57 |  | 34 |  |  |  | BTB |  |  | 14
| 0M | 19&20 |  | 31 |  |  |  | 0M |  |  | 14
| 3M | 21 |  | 3 |  |  |  | 3M
| 6M | 22 |  | 2 |  |  |  | 6M
| 9M | 9 |  | 2 |  |  |  | 9M |  |  | 4
| -3M | [6 empty] | -3M
| 1-.5M | [6 empty] | 1-.5M
3 | DC | [5 empty] | 3 | DC
| BTB | 44 |  | 33 |  |  |  | BTB |  |  | 12
| 0M | 33 |  | 25 |  |  |  | 0M |  |  | 12
| 3M | 11 |  | 8 |  |  |  | 3M
| 6M | 3 |  | 2 |  |  |  | 6M
| 9M | 6 |  | 3 |  |  |  | 9M |  |  | 2
| -3M | [6 empty] | -3M
| 1-.5M | [6 empty] | 1-.5M
4 | DD | [5 empty] | 4 | DD
| BTB | 63 |  | 36 |  |  |  | BTB |  |  | 15
400 kV D/C Samba-Jalandhar Punjab Portion | 2026-03-09 | 2026-03-09 |  | 36 | 130/2- Due to ROW , Tower Erection Work Hampered |  |  | BTB |  |  | 15
| 3M | 6 |  | 5 |  |  |  | 3M
| 6M | 3 |  | 3 |  |  |  | 6M
| 9M | 9 |  | 5 |  |  |  | 9M |  |  | 5
| 18M | 11 | [5 empty] | 18M
| 25M | 10 | [5 empty] | 25M
| 30M | 9 | [5 empty] | 30M
| -3M | [6 empty] | -3M
| 1-.5M | [6 empty] | 1-.5M
Total |  | 365 | 216 | 274 | 0 |  | Total |  | 0 | 100 | 41 | 0
Formulas:
Qty asper approved Survey = [Stub]

## Material Status-Jammu-Punjab (hidden)
CLIENT :- Ratle Kiru Power Transmission Ltd
EXECUTING AGENCY:- KEC INTERNATIONAL LTD.
Name of Project :- ''Transmission Line Portion for “Transmission scheme for evacuation of power from Ratle HEP (850 MW) & Kiru HEP (624 MW): Part-A”
Project Code :- TB605 |  |  | Date :- |  | 2026-08-11
Jammu
MATERIAL STATUS AS ON DATE
Sl No. | Description of Material | Unit | Receipt of Material | [11 empty] | Material Issued to Site |  |  | Stock Avaialbilty | Remarks
|  |  | Receipt through Direct Supply |  |  | Transfer In |  |  | Transfer Out |  |  | Net Receipt
|  |  | Since Previous | On Date | Total as on Date | Since Previous | On Date | Total as on Date | Since Previous | On Date | Total as on Date | Since Previous | On Date | Total as on Date | Since Previous | On Date | Total as on Date
1 | Cement | Bags
1.1 | (a) OPC43 - Ambuja | Bags | 8697 |  | 8697 | 0 | 0 | 0 | 0 | 0 | 0 | 8697 | 0 | 8697 | 7172 |  | 7172 | 5000
[5 empty] | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Reinforcement Steel | MT
2.1 | (a) Real Ispat | MT | 213.15 | 0 | 213.15 | 0 | 0 | 0 | 18.3727 | 0 | 18.3727 | 194.7773 | 0 | 194.7773 | 68.852 | 0 | 68.852 | 352.287
| 8 MM | MT | 8.224 | 0 | 8.224 | 0 | 0 | 0 | 0.52438 | 0 | 0.52438 | 7.6996 | 0 | 7.6996 | 1.649 |  | 1.649 | 7.922
| 10 MM | MT | 42.156 | 0 | 42.156 | 0 | 0 | 0 | 0 | 0 | 0 | 42.156 | 0 | 42.156 | 10.271 |  | 10.271 | 52.061
| 12 MM | MT | 117.2 | 0 | 117.2 | 0 | 0 | 0 | 14.7005 | 0 | 14.7005 | 102.4995 | 0 | 102.4995 | 46.856 |  | 46.856 | 133.687
| 16 MM | MT | 18.97 | 0 | 18.97 | 0 | 0 | 0 | 0 | 0 | 0 | 18.97 | 0 | 18.97 | 0.134 |  | 0.134 | 48.517
| 20 MM | MT | 13.325 | 0 | 13.325 | 0 | 0 | 0 | 0.46 | 0 | 0.46 | 12.865 | 0 | 12.865 | 3.82 |  | 3.82 | 54.777
| 25 MM | MT | 13.275 | 0 | 13.275 | 0 | 0 | 0 | 2.6878 | 0 | 2.6878 | 10.5872 | 0 | 10.5872 | 6.122 |  | 6.122 | 55.323
3 | STUBS | Set |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | DA | Set | 80 | 0 | 80 | 0 | 0 | 0 | 34 | 0 | 34 | 46 | 0 | 46 | 13 |  | 13 | 33
3.2 | DB | Set | 34 |  | 34 |  |  |  | 5 |  | 5 | 29 |  | 29 | 3 |  | 3 | 26
3.3 | DC | Set | 32 |  | 32 |  |  |  | 5 |  | 5 | 27 |  | 27 | 6 |  | 6 | 21
3.4 | DD | Set | 25 |  | 25 |  |  |  | 2 |  | 2 | 23 |  | 23 | 1 |  | 1 | 22
3.5 | DDM | Set | 10 |  | 10 |  |  | 0 |  |  | 0 | 10 | 0 | 10 | 0 |  | 0 | 10
4 | Towers | Set |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | DC |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| BTB | Set | 20 |  | 20 | [6 empty] | 20 |  | 20 |  |  | 0 | 20
| 0M | Set | 20 |  | 20 | [6 empty] | 20 |  | 20 |  |  | 0 | 20
3.2 | DA |  |  |  | 0 | [6 empty] | 0 |  | 0 |  |  | 0 | 0
| BTB | Set | 81 |  | 81 | [6 empty] | 81 |  | 81 |  |  | 0 | 81
| 0M | Set | 61 |  | 61 | [6 empty] | 61 |  | 61 |  |  | 0 | 61
| 9M | Set | 1 |  | 1 | [6 empty] | 1 |  | 1 |  |  | 0 | 1
5 | EARTHING |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Counter Poise | Sets | 51 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 51 | 3 | 0 | 3 | 48
5.2 | Pipe Type Earthing | Nos | 130 | 0 | 130 | 0 | 0 | 0 | 46 | 0 | 46 | 84 | 0 | 84 | 4 |  | 4 | 80
Punjab
MATERIAL STATUS AS ON DATE
Sl No. | Description of Material | Unit | Receipt of Material | [11 empty] | Material Issued to Site |  |  | Stock Avaialbilty | Remarks
|  |  | Receipt through Direct Supply |  |  | Transfer In |  |  | Transfer Out |  |  | Net Receipt
|  |  | Since Previous | On Date | Total as on Date | Since Previous | On Date | Total as on Date | Since Previous | On Date | Total as on Date | Since Previous | On Date | Total as on Date | Since Previous | On Date | Total as on Date
1 | Cement | Bags
1.1 | (a) OPC43 - Ambuja | Bags | 8697 |  | 8697 | 0 | 0 | 0 | 0 | 0 | 0 | 8697 | 0 | 8697 | 7172 |  | 7172 | 3150
[5 empty] | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Reinforcement Steel | MT
2.1 | (a) Real Ispat | MT | 213.15 | 0 | 213.15 | 0 | 0 | 0 | 18.3727 | 0 | 18.3727 | 194.7773 | 0 | 194.7773 | 68.852 | 0 | 68.852 | 337.9451
| 8 MM | MT | 8.224 | 0 | 8.224 | 0 | 0 | 0 | 0.52438 | 0 | 0.52438 | 7.6996 | 0 | 7.6996 | 1.649 |  | 1.649 | 6.5645
| 10 MM | MT | 42.156 | 0 | 42.156 | 0 | 0 | 0 | 0 | 0 | 0 | 42.156 | 0 | 42.156 | 10.271 |  | 10.271 | 63.8006
| 12 MM | MT | 117.2 | 0 | 117.2 | 0 | 0 | 0 | 14.7005 | 0 | 14.7005 | 102.4995 | 0 | 102.4995 | 46.856 |  | 46.856 | 217.0291
| 16 MM | MT | 18.97 | 0 | 18.97 | 0 | 0 | 0 | 0 | 0 | 0 | 18.97 | 0 | 18.97 | 0.134 |  | 0.134 | 19.874
| 20 MM | MT | 13.325 | 0 | 13.325 | 0 | 0 | 0 | 0.46 | 0 | 0.46 | 12.865 | 0 | 12.865 | 3.82 |  | 3.82 | 16.4501
| 25 MM | MT | 13.275 | 0 | 13.275 | 0 | 0 | 0 | 2.6878 | 0 | 2.6878 | 10.5872 | 0 | 10.5872 | 6.122 |  | 6.122 | 14.2267

## Material Status-Punjab (hidden)
CLIENT :- Ratle Kiru Power Transmission Ltd
EXECUTING AGENCY:- KEC INTERNATIONAL LTD. | [17 empty] | *Material supply updated / Consumption to beupdated
Name of Project :- ''Transmission Line Portion for “Transmission scheme for evacuation of power from Ratle HEP (850 MW) & Kiru HEP (624 MW): Part-A”
Project Code :- TB605 |  |  | Date :- |  | 2026-08-11
MATERIAL STATUS AS ON DATE
Sl No. | Description of Material | Unit | Receipt of Material | [11 empty] | Material Issued to Site |  |  | Balance in stock | Remarks
|  |  | Receipt through Direct Supply |  |  | Transfer In |  |  | Transfer Out |  |  | Net Receipt
|  |  | Since Previous | On Date | Total as on Date | Since Previous | On Date | Total as on Date | Since Previous | On Date | Total as on Date | Since Previous | On Date | Total as on Date | Since Previous | On Date | Total as on Date
1 | Cement | Bags
1.1 | (a) OPC43 - Ambuja | Bags | 6300 |  | 6300 | 0 | 0 | 0 | 0 | 0 | 0 | 6300 | 0 | 6300 | 5539 |  | 5539 | 761
[5 empty] | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Reinforcement Steel
2.1 | (a) Real Ispat | MT | 200.24 | 0 | 200.24 | 18.3727 | 0 | 18.3727 | 0 | 0 | 0 | 218.6127 | 0 | 218.6127 | 59.6538 | 0 | 59.6538 | 158.9588
| 8 MM | MT | 4.08 | 0 | 4.08 | 0.52438 | 0 | 0.52438 | 0 | 0 | 0 | 4.6044 | 0 | 4.6044 | 1.5444 |  | 1.5444 | 3.06
| 10 MM | MT | 27.86 | 0 | 27.86 | 0 | 0 | 0 | 0 | 0 | 0 | 27.86 | 0 | 27.86 | 3.9521 |  | 3.9521 | 23.9079
| 12 MM | MT | 140.46 | 0 | 140.46 | 14.7005 | 0 | 14.7005 | 0 | 0 | 0 | 155.1605 | 0 | 155.1605 | 45.1097 |  | 45.1097 | 110.0508
| 16 MM | MT | 8.03 | 0 | 8.03 | 0 | 0 | 0 | 0 | 0 | 0 | 8.03 | 0 | 8.03 | 0 |  | 0 | 8.03
| 20 MM | MT | 10.06 | 0 | 10.06 | 0.46 | 0 | 0.46 | 0 | 0 | 0 | 10.52 | 0 | 10.52 | 2.4705 |  | 2.4705 | 8.0495
| 25 MM | MT | 9.75 | 0 | 9.75 | 2.6878 | 0 | 2.6878 | 0 | 0 | 0 | 12.4378 | 0 | 12.4378 | 6.5772 |  | 6.5772 | 5.8605
3 | STUBS | Set |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | DA | Set |  | 0 | 0 | 34 | 0 | 34 |  | 0 | 0 | 34 | 0 | 34 | 18 |  | 18 | 16
3.2 | DB | Set |  |  | 0 | 5 |  | 5 |  |  |  | 5 |  | 5 | 2 |  | 2 | 3
3.3 | DC | Set |  |  | 0 | 5 |  | 5 |  |  |  | 5 |  | 5 | 1 |  | 1 | 4
3.4 | DD | Set |  |  | 0 | 2 |  | 2 |  |  |  | 2 |  | 2 | 1 |  | 1 | 1
3.5 | DDM | Set |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
4 | EARTHING |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Counter Poise | Sets |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2 | Pipe Type Earthing | Nos |  | 0 | 0 | 46 | 0 | 46 |  | 0 | 0 | 46 | 0 | 46 | 11 | 0 | 11 | 35

## Earthing (PKG-F) (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Earthing
Sl. No. | Cum S No | Location No. | Tower Type | Classification | Type of Earthing | Earthing | Name of Sub-Contractor | Check list
2023-12-01
1 | 1 | 61/3 | DA+6 | DRY | Pipe Type | 18.12.23 | Manoj Sharma
2 | 2 | 62/4 | DA+3 | DRY | Pipe Type | 31.12.23 | Shakti Const.
2024-01-01
3 | 1 | 59/7 | DA+3 | DRY | Pipe Type | 03.01.24 | Manoj Sharma
4 | 2 | 59/8 | DB+3 | DRY | Pipe Type | 03.01.24 | Manoj Sharma
5 | 3 | 59/9 | DA+3 | DRY | Pipe Type | 03.01.24 | Manoj Sharma
6 | 4 | 59/10 | DA+0 | DRY | Pipe Type | 03.01.24 | Manoj Sharma
7 | 5 | 59/13 | DA+3 | DRY | Pipe Type | 03.01.24 | Manoj Sharma
8 | 6 | 59/14 | DA+6 | DRY | Pipe Type | 03.01.24 | Manoj Sharma
9 | 7 | 59/5 | DA+3 | DFR | Counter Poise | 05.01.24 | om Const.
10 | 8 | 59/6 | DA+3 | DFR | Counter Poise | 05.01.24 | om Const.
11 | 9 | 60/7 | DA+3 | DRY | Pipe Type | 06.01.24 | Imran
12 | 10 | 60/8 | DA+0 | DRY | Pipe Type | 06.01.24 | Imran
13 | 11 | 60/9 | DA+3 | DRY | Pipe Type | 06.01.24 | Imran
14 | 12 | 62/2 | DA+3(RC) | DRY | Pipe Type | 07.01.24 | Shakti Const.
15 | 13 | 62/5 | DA+0 | DRY | Pipe Type | 07.01.24 | Shakti Const.
16 | 14 | 62/6 | DA+3 | DRY | Pipe Type | 07.01.24 | Shakti Const.
17 | 15 | 62/3 | DA+0 | DRY | Pipe Type | 07.01.24 | Shakti Const.
18 | 16 | 62/7 | DA+3 | DRY | Pipe Type | 09.01.24 | Shakti Const.
19 | 17 | 63/6 | DA+3 | DRY | Pipe Type | 12.01.24 | Mahadev Eng
20 | 18 | 65/2 | DA+0 | DRY | Pipe Type | 12.01.24 | Veerteja
21 | 19 | 65/11 | DA+0 | DRY | Pipe Type | 15.1.24 | Bhati Const.
22 | 20 | 65/9 | DA+0 | DRY | Pipe Type | 15.1.24 | Bhati Const.
23 | 21 | 60/5 | DA+3 | DRY | Pipe Type | 16.01.2024 | Manoj Sharma
24 | 22 | 60/6 | DA+0 | DRY | Pipe Type | 16.01.2024 | Manoj Sharma
25 | 23 | 59/12 | DA+6 | DFR | Counter Poise | 16.01.2024 | Manoj Sharma
26 | 24 | 55/4 | DA+0(RC) | SANDY | Pipe Type | 17.01.2024 | Imran
27 | 25 | 64/4 | DA+3 | DRY | Pipe Type | 19.01.24 | Mahadev Eng
28 | 26 | 65/3 | DA+3 | DRY | Pipe Type | 20.01.24 | Veerteja
29 | 27 | 63/1 | DA+3 | DFR | Counter Poise | 27.01.24 | Shakti Const.
30 | 28 | 63/2 | DA+0 | DFR | Counter Poise | 27.01.24 | Shakti Const.
31 | 29 | 64/2 | DA+3 | DRY | Pipe Type | 25.01.24 | Mahadev Eng
32 | 30 | 64/5 | DA+3 | DRY | Pipe Type | 25.01.24 | Mahadev Eng
33 | 31 | 65/4 | DA+0 | DRY | Pipe Type | 25.01.24 | Bhati Const.
34 | 32 | 62/11 | DA+3 | DRY | Pipe Type | 28.01.24 | Shakti Const.
35 | 33 | 55/5 | DA+0 RC | SANDY | Pipe Type | 29.01.24 | Imran
36 | 34 | 55/6 | DA+0 RC | SANDY | Pipe Type | 29.01.24 | Imran
Feb-24
37 | 1 | 64/8 | DA+3 | DRY | Pipe Type | 01.02.24 | Veerteja
38 | 2 | 60/10 | DA+0 | DFR | Counter Poise | 02.02.24 | Manoj Sharma
39 | 3 | 60/11 | DA+3 | DRY | Pipe Type | 02.02.24 | Manoj Sharma
40 | 4 | 61/0 | DB2+0 | DRY | Pipe Type | 02.02.24 | Manoj Sharma
41 | 5 | 61/1 | DA+6 | DFR | Counter Poise | 02.02.24 | Manoj Sharma
42 | 6 | 61/2 | DA+6 | DFR | Counter Poise | 02.02.24 | Manoj Sharma
43 | 7 | 55/3 | DA+0 | SANDY | Pipe Type | 02.02.24 | Imran
44 | 8 | 55/7 | DA+0 | SANDY | Pipe Type | 02.02.24 | Imran
45 | 9 | 52/5 | DA+9 RC | SANDY | Pipe Type | 05.02.24 | Imran
46 | 10 | 52/6 | DA+6 | SANDY | Pipe Type | 08.02.24 | Imran
47 | 11 | 65/6 | DA+0 | DRY | Pipe Type | 09.02.24 | Bhati Const.
48 | 12 | 65/5 | DA+0 | DRY | Pipe Type | 09.02.24 | Bhati Const.
49 | 13 | 67/2 | DA+0 | DRY | Pipe Type | 09.02.24 | Bhati Const.
50 | 14 | 64/10 | DA+3 | DRY | Pipe Type | 11.02.24 | Veerteja Enterprises
51 | 15 | 52/7 | DA+3 RC | SANDY | Pipe Type | 13.02.24 | Imran
52 | 16 | 64/7 | DA+3 | DRY | Pipe Type | 14.02.24 | Mahadev Eng
53 | 17 | 64/6 | DA+0 | DRY | Pipe Type | 14.02.24 | Mahadev Eng
54 | 18 | 64/3 | DA+0 | DRY | Pipe Type | 14.02.24 | Mahadev Eng
55 | 19 | 64/1 | DA+0 | DRY | Counter Poise | 14.02.24 | Mahadev Eng
56 | 20 | 64/0 | DB2+0 | DRY | Counter Poise | 14.02.24 | Mahadev Eng
57 | 21 | 63/8 | DA+3 | DRY | Pipe Type | 14.02.24 | Mahadev Eng
58 | 22 | 63/7 | DA+3 | DRY | Pipe Type | 14.02.24 | Mahadev Eng
59 | 23 | 63/4 | DA+0 | DRY | Pipe Type | 14.02.24 | Shakti Const.
60 | 24 | 57/2 | DA+3 | DRY | Pipe Type | 14.02.24 | om Const.
61 | 25 | 57/4 | DA+0 | SANDY | Pipe Type | 14.02.24 | om Const.
62 | 26 | 57/5 | DA+3 RC | SANDY | Pipe Type | 14.02.24 | om Const.
63 | 27 | 63/0 | DC1+0 | DFR | Counter Poise | 15.02.24 | Shakti Const.
64 | 28 | 63/5 | DA+3 | DFR | Counter Poise | 15.02.24 | Shakti Const.
65 | 29 | 52/10 | DA+9 RC | SANDY | Pipe Type | 17.02.24 | Imran
66 | 30 | 64/9 | DA+3 | DRY | Pipe Type | 20.02.24 | Veerteja Enterprises
67 | 31 | 57/3 | DA+0 | DRY | Pipe Type | 22.02.24 | om Const.
68 | 32 | 57/6 | DA+3 RC | SANDY | Pipe Type | 22.02.24 | om Const.
69 | 33 | 59/3 | DA+3(RC) | DFR | Counter Poise | 22.02.24 | om Const.
70 | 34 | 61/9 | DA+0 | Dry | Pipe Type | 22.02.24 | Manoj Sharma
71 | 35 | 61/8 | DA+6 RC | DRY | Pipe Type | 22.02.24 | Manoj Sharma
72 | 36 | 61/7 | DA+9 RC | Dry | Pipe Type | 22.02.24 | Manoj Sharma
73 | 37 | 61/6 | DA+3 | DRY | Pipe Type | 22.02.24 | Manoj Sharma
74 | 38 | 61/5 | DA+3 | DRY | Pipe Type | 22.02.24 | Manoj Sharma
75 | 39 | 62/10 | DA+0 | DFR | Counter Poise | 22.02.24 | Shakti Const.
76 | 40 | 62/1 | DA+3 RC | SANDY | Pipe Type | 22.02.24 | Shakti Const.
77 | 41 | 62/9 | DA+3 | DFR | Counter Poise | 21.02.24 | Shakti Const.
78 | 42 | 62/8 | DA+0 | DFR | Counter Poise | 21.02.24 | Shakti Const.
79 | 43 | 52/9 | DA+3 | SANDY | Pipe Type | 22.02.24 | Imran
80 | 44 | 52/8 | DA+6 | SANDY | Pipe Type | 22.02.24 | Imran |  | 210
81 | 45 | 63/3 | DA+3 | DFR | Pipe Type | 22.02.24 | Shakti Const.
82 | 46 | 67/1 | DA+0 | DRY | Pipe Type | 13.02.24 | Bhati Const.
83 | 47 | 60/1 | DA+6 | DRY | Pipe Type | 23.02.24 | om Const.
84 | 48 | 53/5 | DA+3 | SANDY | Pipe Type | 25.02.24 | Imran
85 | 49 | 60/2 | DA+3 | DFR | Counter Poise | 26.02.24 | om Const.
March'24
86 | 1 | 60/3 | DA+3 | DFR | Counter Poise | 01.03.24 | Manoj Sharma
87 | 2 | 60/4 | DA+3 | DFR | Counter Poise | 01.03.24 | Manoj Sharma
88 | 3 | 64/11 | DA+3 | DRY | Pipe Type | 06.03.24 | Bhati Const.
89 | 4 | 65/0 | DB1+0 | DRY | Pipe Type | 06.03.24 | Bhati Const.
90 | 5 | 65/1 | DA+0 | DRY | Pipe Type | 07.03.24 | Bhati Const.
91 | 6 | 59/16 | DA+9 | Dry | Pipe Type | 26.02.24 | om Const.
92 | 7 | 59/15 | DA+6 | DRY | Pipe Type | 26.02.24 | om Const.
93 | 8 | 49/2 | DA+3 | SANDY | Pipe Type | 08.03.24 | Veerteja Enterprises
94 | 9 | 61/10 | DA+9 | DRY | Pipe Type | 12.03.24 | Manoj Sharma
95 | 10 | 62/0 | DB2+0 | DRY | Pipe Type | 12.03.24 | Manoj Sharma
96 | 11 | 60/0 | DC1+0 | DRY | Pipe Type | 19.03.24 | Manoj Sharma
97 | 12 | 49/3 | DA+3 | SANDY | Pipe Type | 21.03.24 | Veerteja Enterprises
98 | 13 | 49/5 | DA+3 | SANDY | Pipe Type | 21.03.24 | Shakti Const.
99 | 14 | 61/4 | DA+3 | DRY | Pipe Type | 22.03.24 | Manoj Sharma
100 | 15 | 47/10 | DA+6 | SANDY | Pipe Type | 29.03.24 | Bhati Const.
101 | 16 | 47/9 | DA+3 | SANDY | Pipe Type | 29.03.24 | Bhati Const.
102 | 17 | 47/8 | DA+0 RC | SANDY | Pipe Type | 29.03.24 | Bhati Const.
April'24
103 | 1 | 47/7 | DA+3 | SANDY | Pipe Type | 02.04.24 | Bhati Const.
104 | 2 | 48/0 | DC2+0 | SANDY | Pipe Type | 07.04.24 | Bhati Const.
105 | 3 | 48/1 | DA+9 | SANDY | Pipe Type | 16.04.24 | Veerteja Enterprises
106 | 4 | 50/9 | DA+0 RC | SANDY | Pipe Type | 19.04.24 | Shakti Const.
107 | 5 | 50/10 | DA+0 RC | SANDY | Pipe Type | 19.04.24 | Shakti Const.
108 | 6 | 51/1 | DA+0 RC | SANDY | Pipe Type | 19.04.24 | Shakti Const.
109 | 7 | 50/8 | DA+9 | SANDY | Pipe Type | 20.04.24 | Shakti Const.
110 | 8 | 49/6 | DA+0 | SANDY | Pipe Type | 20.04.24 | Shakti Const.
111 | 9 | 49/4 | DA+3 | SANDY | Pipe Type | 22.04.24 | Veerteja
112 | 10 | 49/1 | DA+0 | SANDY | Pipe Type | 22.04.24 | Veerteja
May'24
113 | 1 | 49/0 | DD45+0 | SANDY | Pipe Type | 03.05.24 | Veerteja Enterprises
114 | 2 | 52/3 | DA+9 | SANDY | Pipe Type | 23.05.24 | SB MEHAR CONST.
115 | 3 | 47/2 | DA+9 | SANDY | Pipe Type | 28.05.24 | Bhati Const.
116 | 4 | 50/7 | DA+0 RC | SANDY | Pipe Type | 31.05.24 | Veerteja Enterprises
117 | 5 | 50/1 | DA+6 | SANDY | Pipe Type | 31.05.24 | Veerteja Enterprises
118 | 6 | 51/2 | DA+0 | SANDY | Pipe Type | 31.05.24 | SB MEHAR CONST. |  | 41.96 | 41.82
June'24
119 | 1 | 50/4 | DA+9 RC | SANDY | Pipe Type | 03.02.24 | Veerteja Enterprises
120 | 2 | 50/2 | DA+9 RC | SANDY | Pipe Type | 04.02.24 | Veerteja Enterprises
121 | 3 | 47/3 | DA+9 RC | SANDY | Pipe Type | 08.06.24 | Bhati Const.
122 | 4 | 47/5 | DA+0 RC | SANDY | Pipe Type | 08.06.24 | Bhati Const.
123 | 5 | 47/6 | DA+3 | SANDY | Pipe Type | 08.06.24 | Bhati Const.
124 | 6 | 51/0 | DC2+0 | SANDY | Pipe Type | 11.06.24 | SB MEHAR CONST.
July'24
125 | 1 | 53/7 | DA+3 | SANDY | Pipe Type | 02.07.24 | Bhati Const.
126 | 2 | 58/0 | DC1+3 | DFR | Counter Poise | 30.07.24 | Bhati Const.
Aug'24
127 | 1 | 50/0 | DB2+0 RC | SANDY | Pipe Type | 03.08.24 | Veerteja Enterprises
128 | 2 | 57/7 | DA+3 | DFR | Counter Poise | 12.08.24 | Bhati Const.
129 | 3 | 59/2 | DA+3 | DFR | Counter Poise | 23.08.24 | Bhati Const.
Sept'24
130 | 1 | 53/8 | DA+3 | Sandy | Pipe Type | 03.09.24 | Bhati Const.
131 | 2 | 53/6 | DA+6 RC | Sandy | Pipe Type | 13.09.24 | Bhati Const.
132 | 3 | 54/1 | DA+3 RC | Sandy | Pipe Type | 14.09.24 | Bhati Const.
133 | 4 | 54/2 | DA+3 | Sandy | Pipe Type | 14.09.24 | Bhati Const.
134 | 5 | 73/0 | DB2+0 | DRY | Pipe Type | 15.09.24 | Shree Shyam Const.
135 | 6 | 73/2 | DA+0 | DRY | Pipe Type | 16.09.24 | Shree Shyam Const.
136 | 7 | 73/1 | DA+0 | DRY | Pipe Type | 19.09.24 | Shree Shyam Const.
137 | 8 | 73/9 | DA+0 | DRY | Pipe Type | 19.09.24 | Shakti Const.
138 | 9 | 73/6 | DA+0 | DRY | Pipe Type | 22.09.24 | Shree Shyam Const.
139 | 10 | 66/0 | DC2+6 | DFR | Pipe Type | 27.09.24 | Bhati Const.
140 | 11 | 69/1 | DA+3 | DRY | Pipe Type | 27.09.24 | Bhati Const.
141 | 12 | 59/11 | DA+6 | DFR | Counter Poise | 28.09.24 | Mahadev Eng
142 | 13 | 50/3 | DA+6 | Sandy | Pipe Type | 29.09.24 | Kalpana Const.
143 | 14 | 50/6 | DA+9 RC | Sandy | Pipe Type | 29.09.24 | Kalpana Const.
Oct'24
144 | 1 | 59/1 | DA+3 RC | DRY | Pipe Type | 01.10.24 | Bhati Const.
145 | 2 | 59/0 | DC2+0 | DRY | Pipe Type | 5.10.24 | Bhati Const.
146 | 3 | 72/2 | DA+0 | DRY | Pipe Type | 07.10.24 | Shree Shyam Const.
147 | 4 | 73/3 | DA+0 | DRY | Pipe Type | 07.10.24 | Awadh Const
148 | 5 | 73/5 | DA+0 | DRY | Pipe Type | 07.10.24 | Shree Shyam Const.
149 | 6 | 73/7 | DA+0 | DRY | Pipe Type | 07.10.24 | Shakti Const.
150 | 7 | 73/8 | DA+3 | DRY | Pipe Type | 07.10.24 | Shakti Const.
151 | 8 | 73/4 | DA+0 | DRY | Pipe Type | 10.10.24 | Shree Shyam Const.
152 | 9 | 67/0 | DC1+9 | DRY | Pipe Type | 10.10.24 | Bhati Const.
153 | 10 | 69/0 | DB2+0 | DFR | Counter Poise | 16.10.24 | Bhati Const.
154 | 11 | 74/0 | DB2+0 | SANDY | Pipe Type | 16.10.24 | Shakti Const.
155 | 12 | 72/3 | DA+3 | DRY | Pipe Type | 18.10.24 | Shree Shyam Const.
156 | 13 | 71/6 | DA+0 | DRY | Pipe Type | 22.10.24 | Shree Shyam Const.
157 | 14 | 71/7 | DA+3 | DRY | Pipe Type | 22.10.24 | Shree Shyam Const.
158 | 15 | 49/7 | DA+0 RC | Sandy | Pipe Type | 23.10.24 | Kalpana Const.
159 | 16 | 59/4 | DA+3 | DFR | Counter Poise | 23.10.24 | Bhati Const.
Nov'24
160 | 1 | 54/0 | DB1+6 | Sandy | Pipe Type | 21.11.24 | Bhati Const.
Dec'24
161 | 1 | 65/8 | DA+0 | DRY | Pipe Type | 06.12.24 | Bhati Const.
162 | 2 | 65/7 | DA+0 | DRY | Pipe Type | 06.12.24 | Bhati Const.
2025-01-25
163 | 1 | 54/3 | DA+6 RC | Sandy | Pipe Type | 07.01.25 | Tantray Construction
164 | 2 | 54/4 | DA+9 RC | Sandy | Pipe Type | 10.01.25 | Tantray Construction
165 | 3 | 50/5 | DA+9 RC | SANDY | Pipe Type | 23.01.25 | om Const.
166 | 4 | 70/1 | DA+3 | DRY | Pipe Type | 25.01.25 | Meer Cost.
167 | 5 | 70/3 | DA+3 | DRY | Pipe Type | 25.01.25 | Meer Cost.
168 | 6 | 70/4 | DA+3 | DRY | Pipe Type | 25.01.25 | Meer Cost.
169 | 7 | 70/0 | DA+3 | DRY | Pipe Type | 25.01.25 | Meer Cost.
170 | 8 | 70/5 | DA+3 | DRY | Pipe Type | 27.01.25 | Meer Cost.
171 | 9 | 70/6 | DA+3 | DRY | Pipe Type | 27.01.25 | Tantray Construction
172 | 10 | 71/0 | DB2+3 | DRY | Pipe Type | 27.01.25 | Tantray Construction
173 | 11 | 71/1 | DA+3 | DRY | Pipe Type | 27.01.25 | Meer Cost.
174 | 12 | 71/2 | DA+3 | DRY | Pipe Type | 27.01.25 | Meer Cost.
175 | 13 | 71/3 | DA+6 | DRY | Pipe Type | 28.01.25 | Meer Cost.
176 | 14 | 71/4 | DA+3 | DRY | Pipe Type | 28.01.25 | Meer Cost.
177 | 15 | 72/0 | DB2+3 | DRY | Pipe Type | 28.01.25 | Meer Cost.
178 | 16 | 47/4 | DA+3 | SANDY | Pipe Type | 29.01.25 | Tantray Construction
179 | 17 | 47/1 | DA+3 | SANDY | Pipe Type | 29.01.25 | Tantray Construction
180 | 18 | 57/1 | DA | SANDY | Pipe Type | 29.01.25 | Meer Cost.
Feb-25
181 | 1 | 70/7 | DA+3 | DRY | Pipe Type | 01.02.25 | Tantray Construction
182 | 2 | 70/8 | DA+3 | DRY | Pipe Type | 01.02.25 | Tantray Construction
183 | 3 | 70/9 | DA+3 | DRY | Pipe Type | 01.02.25 | Tantray Construction
184 | 4 | 70/10 | DA+3 | DRY | Pipe Type | 01.02.25 | Tantray Construction
185 | 5 | 71/5 | DA+3 | DRY | Pipe Type | 01.02.25 | Meer Cost.
186 | 6 | 71/8 | DA+3 | DRY | Pipe Type | 01.02.25 | Meer Cost.
187 | 7 | 72/1 | DA+3 | DRY | Pipe Type | 01.02.25 | Meer Cost.
188 | 8 | 55/8 | DA+6 | SANDY | Pipe Type | 03.02.25 | Meer Cost.
189 | 9 | 55/2 | DA+0 | WFR | Counter Poise | 07.02.25 | Meer Cost.
190 | 10 | 52/0 | DC2+0 RC | Sandy | Pipe Type | 17.02.25 | Tantray Construction
191 | 11 | 52/1 | DA+6 RC | Sandy | Pipe Type | 17.02.25 | Tantray Construction
192 | 12 | 52/2 | DA+6 RC | Sandy | Pipe Type | 17.02.25 | Tantray Construction
193 | 13 | 52/4 | DA+9 RC | Sandy | Pipe Type | 17.02.25 | Tantray Construction
194 | 14 | 44/3 | DA+0 RC | SANDY | Pipe Type | 18.02.25 | Tantray Construction
195 | 15 | 44/7 | DA+9 | SANDY | Pipe Type | 18.02.25 | Iqbal
196 | 16 | 70/2 | DA+3 | DRY | Pipe Type | 19.02.25 | Bhati Const.
197 | 17 | 68/0 | DD45+0 | DRY | Pipe Type | 19.02.25 | Bhati Const.
198 | 18 | 65/10 | DA+0 | DRY | Pipe Type | 19.02.25 | Bhati Const.
199 | 19 | 54/5 | DA+9 RC | SANDY | Pipe Type | 23.02.25 | Meer const
200 | 20 | 55/0 | DB1+6 RC | SANDY | Pipe Type | 23.02.25 | Meer const
201 | 21 | 53/0 | DB2+9 RC | Sandy | Pipe Type | 23.02.25 | Meer const
202 | 22 | 53/1 | DA+9 RC | Sandy | Pipe Type | 23.02.25 | Meer const
203 | 23 | 53/2 | DA+0 RC | Sandy | Pipe Type | 23.02.25 | Meer const
204 | 24 | 53/3 | DA+6 RC | Sandy | Pipe Type | 23.02.25 | Meer const
205 | 25 | 53/4 | DA+0 RC | Sandy | Pipe Type | 23.02.25 | Meer const
206 | 26 | 45/1 | DA+9 RC | SANDY | Pipe Type | 26.02.25 | Tantray Construction
207 | 27 | 45/0 | DC2+0 RC | Sandy | Pipe Type | 26.02.25 | Nadeem
208 | 28 | 44/11 | DA+0 RC | Sandy | Pipe Type | 27.02.25 | Nadeem
209 | 29 | 44/10 | DB1+9 RC | Sandy | Pipe Type | 27.02.25 | Nadeem
210 | 30 | 44/9 | DA+9 RC | Sandy | Pipe Type | 27.02.25 | Iqbal
211 | 31 | 44/8 | DCT1+0 | SANDY | Pipe Type | 28.02.25 | Iqbal
212 | 32 | 44/5 | DA+9 RC | Sandy | Pipe Type | 28.02.25 | Tantray Construction
213 | 33 | 44/6 | DB1+3 RC | SANDY | Pipe Type | 28.02.25 | Tantray Construction
214 | 34 | 44/4 | DA+9 RC | Sandy | Pipe Type | 28.02.25 | Tantray Construction
| Mar-25 |  |  | 1 | 1 |  | 1
215 | 1 | 55/1 | DA+0 | WFR | Counter Poise | 02.03.25 | Bhati
216 | 2 | 44/0 | DB1+3 RC | SANDY | Pipe Type | 16.03.25 | OM Const
217 | 3 | 44/1 | DA+0 RC | Sandy | Pipe Type | 16.03.25 | OM Const
218 | 4 | 44/2 | DA+0 | Sandy | Pipe Type | 16.03.25 | OM Const
219 | 5 | 43/10 | DA+3 RC | SANDY | Pipe Type | 16.03.25 | OM Const
219 | 5 | 70/11 | DA+3 | DRY | Pipe Type | 29.03.25 | Bhati Const.

## Earthing (PKG-G) (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Earthing
Cum S No | Sl. No. | Location No. | Tower Type | Classification | Type of Earthing | Earthing | Name of Sub-Contractor | Check list
2023-08-01
1 | 1 | 58/1 | DA+0 | DRY | Pipe Type | 16.08.23 | Mahadev engg. | Check list submitted
2 | 2 | 58/11 | DA+3 | DRY | Pipe Type | 20.08.23 | Mahadev engg. | Check list submitted
3 | 3 | 58/3 | DA+3 | DRY | Pipe Type | 24.8.23 | Mahadev engg. | Check list submitted
4 | 4 | 58/5 | DA+3 | DRY | Pipe Type | 24.8.23 | Mahadev engg. | Check list submitted
5 | 5 | 57/10 | DA+0 | DRY | Pipe Type | 24.8.23 | Manoj Sharma | Check list submitted
6 | 6 | 57/13 | DA+0 | DRY | Pipe Type | 24.8.23 | Manoj Sharma | Check list submitted
7 | 7 | 57/11 | DA+0 | DRY | Pipe Type | 24.8.23 | Manoj Sharma | Check list submitted
8 | 8 | 57/12 | DA+3 | DRY | Pipe Type | 24.8.23 | Manoj Sharma | Check list submitted
9 | 9 | 58/6 | DA+3 | DRY | Pipe Type | 24.8.23 | Mahadev engg. | Check list submitted
10 | 10 | 57/8 | DA+3 | DRY | Pipe Type | 25.08.23 | Manoj Sharma | Check list submitted
11 | 11 | 52/2 | DA+3 | DFR | Counter Poise | 25.08.23 | Khewanjrai Electrical | Check list submitted
12 | 12 | 57/9 | DA+0 | DRY | Pipe Type | 25.08.23 | Manoj Sharma | Check list submitted
13 | 13 | 58/15 | DA+3 | DRY | Pipe Type | 26.08.23 | Mahadev engg. | Check list submitted
14 | 14 | 58/10 | DA+3 | DRY | Pipe Type | 26.08.23 | Mahadev engg. | Check list submitted
15 | 15 | 58/9 | DA+0 | DRY | Pipe Type | 26.08.23 | Mahadev engg. | Check list submitted
16 | 16 | 58/16 | DA+0 | DRY | Pipe Type | 29.08.23 | Mahadev engg. | Check list submitted
17 | 17 | 52/1 | DA+0 | DFR | Counter Poise | 31.08.23 | Khewanjrai Electrical | Check list submitted
18 | 18 | 58/12 | DA+0 | DRY | Pipe Type | 31.08.23 | Mahadev engg. | Check list submitted
19 | 19 | 51/4 | DA+3 | DFR | Counter Poise | 31.08.23 | B S Electrical | Check list submitted
20 | 20 | 58/8 | DA+0 | DRY | Pipe Type | 31.08.23 | Mahadev engg. | Check list submitted
21 | 21 | 51/3 | DA+0 | DFR | Counter Poise | 31.08.23 | B S Electrical | Check list submitted
22 | 22 | 52/4 | DA+0 | DFR | Counter Poise | 31.08.23 | Khewanjrai Electrical | Check list submitted
2023-09-01
23 | 1 | 61/1 | DA+0 | DRY | Pipe Type | 03.09.2023 | Mahadev engg. | Check list submitted
24 | 2 | 59/5 | DA+0 | DRY | Pipe Type | 05.09.23 | Mahadev engg. | Check list submitted
25 | 3 | 61/2 | DA+0 | DRY | Pipe Type | 06.09.23 | Mahadev engg. | Check list submitted
26 | 4 | 58/2 | DA+0 | DRY | Pipe Type | 10.09.23 | Mahadev engg. | Check list submitted
27 | 5 | 59/1 | DA+0 | DRY | Pipe Type | 10.09.23 | Manoj Sharma | Check list submitted
28 | 6 | 59/3 | DA+0 | DRY | Pipe Type | 10.09.23 | Manoj Sharma | Check list submitted
29 | 7 | 59/2 | DA+0 | DRY | Pipe Type | 10.09.23 | Manoj Sharma | Check list submitted
30 | 8 | 59/6 | DA+0 | DRY | Pipe Type | 10.09.23 | Manoj Sharma | Check list submitted
31 | 9 | 53/3 | DA+3 | DRY | Pipe Type | 12.09.23 | Vaishali Const | Check list submitted
32 | 10 | 53/4 | DA+3 | DRY | Pipe Type | 12.09.23 | Vaishali Const | Check list submitted
33 | 11 | 47/3 | DA+0 | DFR | Counter Poise | 18.09.23 | B S Electrical | received
34 | 12 | 47/2 | DA+0 | DFR | Counter Poise | 18.09.23 | B S Electrical | received
35 | 13 | 51/10 | DA+3 | DFR | Counter Poise | 19.09.23 | Nurul Amin | received
36 | 14 | 55/2 | DA+3 | DFR | Counter Poise | 20.09.23 | Amirul Islam | Not received
37 | 15 | 48/1 | DA+0 | DRY | Pipe Type | 21.09.23 | Shri Bhadariyarai Enterprises | received
38 | 16 | 50/4 | DA+3 | DRY | Pipe Type | 21.09.23 | Shri Bhadariyarai Enterprises | received
39 | 17 | 48/2 | DA+3 | DRY | Pipe Type | 22.09.23 | Shri Bhadariyarai Enterprises | received
40 | 18 | 52/5 | DA+3 | DRY | Pipe Type | 23.09.23 | Nurul Amin | received
41 | 19 | 55/3 | DA+0 | DFR | Counter Poise | 24.09.23 | Amirul Islam | Not received
42 | 20 | 56/3 | DA+0 | DFR | Counter Poise | 25.9.23 | Vaishali Const | Not received
43 | 21 | 43/4 | DA+9 | DRY | Pipe Type | 25.09.23 | Shakti Construction | Not received
44 | 22 | 56/6 | DA+3 | DRY | Pipe Type | 26.09.23 | Manoj Sharma | Not received
45 | 23 | 56/7 | DA+3 | DRY | Pipe Type | 26.09.23 | Manoj Sharma | Not received
46 | 24 | 55/4 | DA+3 | DFR | Counter Poise | 27.09.23 | Amirul Islam | Not received
47 | 25 | 43/5 | DA+0 | DFR | Counter Poise | 28.09.23 | Amirul Islam | received
48 | 26 | 51/2 | DA+0 | DRY | Pipe Type | 29.09.23 | B S Electrical | received
49 | 27 | 44/1 | DA+0 | WFR | Counter Poise | 29.09.23 | Shakti Construction | Not received
50 | 28 | 55/10 | DA+3 | DRY | Pipe Type | 29.09.23 | Nurul Amin | Not received
51 | 29 | 44/4 | DA+0 | WFR | Counter Poise | 30.09.23 | B S Electrical
52 | 30 | 44/2 | DA+0 | SANDY | Pipe Type | 30.09.23 | Shakti Construction
2023-10-01
53 | 1 | 50/3 | DA+0 | DFR | Counter Poise | 01.10.23 | Shri Bhadariyarai Enterprises
54 | 2 | 72/3 | DA+0 | DRY | Pipe Type | 01.10.23 | Mahadev engg.
55 | 3 | 72/4 | DA+0 | DRY | Pipe Type | 01.10.23 | Mahadev engg.
56 | 4 | 72/5 | DA+0 | DRY | Pipe Type | 01.10.23 | Mahadev engg.
57 | 5 | 72/2 | DA+0 | DRY | Pipe Type | 03.10.23 | Mahadev engg.
58 | 6 | 71/3 | DA+0 | DRY | Pipe Type | 03.10.23 | Mahadev engg.
59 | 7 | 71/4 | DA+0 | DRY | Pipe Type | 03.10.23 | Mahadev engg.
60 | 8 | 71/1 | DA+0 | DRY | Pipe Type | 03.10.23 | Mahadev engg.
61 | 9 | 57/4 | DA+0 | DRY | Pipe Type | 04.10.23 | Manoj Sharma
62 | 10 | 57/5 | DA+3 | DRY | Pipe Type | 04.10.23 | Manoj Sharma
63 | 11 | 57/2 | DA+0 | DRY | Pipe Type | 04.10.23 | Manoj Sharma
64 | 12 | 57/1 | DA+3 | DRY | Pipe Type | 04.10.23 | Manoj Sharma
65 | 13 | 57/3 | DA+0 | DRY | Pipe Type | 04.10.23 | Manoj Sharma
66 | 14 | 56/9 | DA+3 | DRY | Pipe Type | 04.10.23 | Manoj Sharma
67 | 15 | 56/8 | DA+3 | DRY | Pipe Type | 04.10.23 | Manoj Sharma
68 | 16 | 56/4 | DA+3 | DFR | Counter Poise | 04.10.23 | Manoj Sharma
69 | 17 | 57/7 | DA+3 | DRY | Pipe Type | 04.10.23 | Manoj Sharma |  | 72/1
70 | 18 | 56/5 | DA+0 | DRY | Pipe Type | 05.10.23 | Manoj Sharma |  | 71/5
71 | 19 | 55/11 | DA+3 | DRY | Pipe Type | 05.10.23 | Nurul Amin
72 | 20 | 55/7 | DA+0 | DRY | Pipe Type | 06.10.23 | Nurul Amin
73 | 21 | 55/8 | DA+3 | DRY | Pipe Type | 06.10.23 | Nurul Amin
74 | 22 | 55/9 | DA+3 | DRY | Pipe Type | 06.10.23 | Nurul Amin
75 | 23 | 55/5 | DA+0 | DFR | Counter Poise | 07.10.23 | Amirul Islam
76 | 24 | 56/1 | DA+3 | DFR | Counter Poise | 08.10.23 | Vaishali Const
77 | 25 | 58/14 | DA+0 | DRY | Pipe Type | 08.10.23 | Mahadev engg.
78 | 26 | 41/7 | DA+3 | SANDY | Pipe Type | 09.10.23 | Om Const
79 | 27 | 41/10 | DA+3 | SANDY | Pipe Type | 09.10.23 | Om Const
80 | 28 | 44/3 | DA+3 | WFR | Counter Poise | 10.10.23 | Shakti Construction
81 | 29 | 41/11 | DA+3 | SANDY | Pipe Type | 12.10.23 | Om Const
82 | 30 | 58/4 | DA+0 | DRY | Pipe Type | 11.10.23 | Mahadev engg.
83 | 31 | 56/2 | DA+3 | DFR | Counter Poise | 17.10.23 | Vaishali Const
84 | 32 | 55/1 | DA+3 | DRY | Pipe Type | 17.10.23 | Amirul Islam
85 | 33 | 58/7 | DB1+0 | DRY | Pipe Type | 19.10.23 | Mahadev engg.
86 | 34 | 57/6 | DB1+0 | DRY | Pipe Type | 22.10.23 | Manoj Sharma
87 | 35 | 51/5 | DA+0 | DRY | Pipe Type | 23.10.23 | Vaishali Const
88 | 36 | 51/7 | DA+3 | DFR | Counter Poise | 23.10.23 | Vaishali Const
89 | 37 | 53/2 | DA+3 | DFR | Counter Poise | 23.10.23 | Vaishali Const
90 | 38 | 59/0 | DB2+0 | DRY | Pipe Type | 26.10.23 | Mahadev engg.
91 | 39 | 57/0 | DB2+0 | DRY | Pipe Type | 28.10.23 | Manoj Sharma
2023-11-01
92 | 1 | 56/0 | DB1+0 | DFR | Counter Poise | 02.11.23 | Vaishali Const
93 | 2 | 51/0 | DB2+0 | DFR | Counter Poise | 02.11.23 | Manoj Sharma
94 | 3 | 48/0 | DB2+0 | SANDY | Pipe Type | 05.11.23 | Om Const
95 | 4 | 55/6 | DA+3 | DRY | Pipe Type | 07.11.23 | Amirul Islam
96 | 5 | 33/1 | DA+0 | SANDY | Pipe Type | 07.11.23 | Shakti Construction
97 | 7 | 52/0 | DB2+0 | DRY | Pipe Type | 08.11.23 | Manoj Sharma
98 | 8 | 43/1 | DA+9 | SANDY | Pipe Type | 08.11.23 | Om Const
99 | 9 | 46/2 | DA+0 | DRY | Pipe Type | 09.11.23 | Bhadariya
100 | 10 | 47/0 | DB1+0 | SANDY | Pipe Type | 09.11.23 | Om Const
101 | 13 | 51/9 | DA+0 | DRY | Pipe Type | 14.11.23 | Om Const
2023-12-01
102 | 1 | 51/6 | DA+0 | DRY | Pipe Type | 02.12.23 | Om Const
103 | 2 | 46/3 | DA+0 | SANDY | Pipe Type | 09.12.23 | Manoj Sharma
104 | 3 | 51/1 | DA+0 | DFR | Counter Poise | 09.12.23 | Om Const
105 | 4 | 41/5 | DA+0 RC | SANDY | Pipe Type | 13.12.23 | Shakti Construction
106 | 5 | 53/1 | DA+0 RC | DRY | Pipe Type | 17.12.23 | Om Const
107 | 7 | 51/8 | DA+3 | DFR | Counter Poise | 17.12.23 | Om Const
108 | 8 | 52/3 | DA+0 RC | SANDY | Pipe Type | 22.12.23 | Om Const
2024-01-01
109 | 1 | 41/6 | DA+0(RC) | SANDY | Pipe Type | 17.01.24 | Riddhika Tech.
110 | 2 | 41/4 | DA+0(RC) | SANDY | Pipe Type | 17.01.24 | Riddhika Tech.
111 | 3 | 41/12 | DA+3 RC | SANDY | Pipe Type | 27.01.24 | Riddhika Tech.
112 | 4 | 41/8 | DA+0 (RC) | SANDY | Pipe Type | 27.01.24 | Riddhika Tech.
113 | 5 | 41/9 | DA+0(RC) | SANDY | Pipe Type | 28.01.24 | Riddhika Tech.
Feb-24
114 | 1 | 53/0 | DC2+3 | DRY | Pipe Type | 02.02.24 | Om Const
115 | 2 | 55/0 | DC1+0 | DRY | Pipe Type | 06.02.24 | Manoj Sharma
116 | 3 | 58/0 | DC2+0 | DRY | Pipe Type | 19.02.24 | Mahadev engg.
117 | 4 | 65/1 | DA+3 | DRY | Pipe Type | 21.2.24 | Bhati Const.
118 | 5 | 65/4 | DA+0 | DRY | Pipe Type | 21.2.24 | Bhati Const.
119 | 6 | 63/6 | DA+3 | DRY | Pipe Type | 22.2.24 | Bhati Const.
120 | 7 | 65/3 | DA+0 | DRY | Pipe Type | 22.2.24 | Bhati Const.
121 | 8 | 65/5 | DA+0 | DRY | Pipe Type | 22.2.24 | Bhati Const.
122 | 9 | 46/4 | DA+0 (RC) | SANDY | Pipe Type | 20.02.24 | Om Const
123 | 10 | 63/5 | DA+3 | DRY | Pipe Type | 10.02.24 | Bhati Const.
124 | 11 | 40/10 | DB1+6 | SANDY | Pipe Type | 24.02.24 | Riddhika Tech.
125 | 12 | 40/11 | DA+9 RC | SANDY | Pipe Type | 24.02.24 | Riddhika Tech.
126 | 13 | 40/6 | DA+3 RC | SANDY | Pipe Type | 25.02.24 | Riddhika Tech.
March'24
127 | 1 | 40/4 | DA+9 RC | SANDY | Pipe Type | 06.03.24 | Riddhika Tech.
128 | 2 | 37/3 | DA+0 | SANDY | Pipe Type | 08.03.24 | Veerteja Enterprises
129 | 3 | 37/2 | DB1+6 | SANDY | Pipe Type | 08.03.24 | Veerteja Enterprises
130 | 4 | 38/1 | DA+3 RC | SANDY | Pipe Type | 12.03.24 | Shakti Construction
131 | 5 | 38/6 | DA+0 RC | SANDY | Pipe Type | 13.03.24 | Shakti Construction
132 | 6 | 37/4 | DA+6 RC | SANDY | Pipe Type | 13.03.24 | Veerteja Enterprises
133 | 7 | 40/3 | DA+3 RC | SANDY | Pipe Type | 14.03.24 | Riddhika Tech.
134 | 8 | 39/1 | DA+6 RC | SANDY | Pipe Type | 14.03.24 | Riddhika Tech.
135 | 9 | 65/2 | DA+0 | SANDY | Pipe Type | 14.03.24 | Bhati Const.
136 | 10 | 63/2 | DA+0 | DRY | Pipe Type | 14.03.24 | Bhati Const.
137 | 11 | 65/6 | DA+0 | Dry | Pipe Type | 14.03.24 | Bhati Const.
138 | 12 | 40/5 | DB1+9 | SANDY | Pipe Type | 14.03.24 | Riddhika Tech.
139 | 13 | 38/2 | DA+6 | SANDY | Pipe Type | 16.03.24 | Veerteja Enterprises
140 | 14 | 38/3 | DA+9 RC | SANDY | Pipe Type | 16.03.24 | Veerteja Enterprises
141 | 15 | 39/3 | DA+3 RC | SANDY | Pipe Type | 21.03.24 | Riddhika Tech.
April'24
142 | 1 | 38/8 | DA+0 RC | SANDY | Pipe Type | 21.04.24 | Shakti Construction
May'24
143 | 1 | 39/4 | DA+0(RC) | SANDY | Pipe Type | 12.05.24 | SB MEHAR CONST.
July'24
144 | 1 | 40/2 | DB1+9 | SANDY | Pipe Type | 15.07.24 | Bhati Const.
145 | 2 | 49/0 | DC1+3 | DFR | Counter Poise | 20.07.24 | Mahadev engg.
146 | 3 | 50/0 | DC2+3 | DFR | Counter Poise | 29.07.24 | Mahadev engg.
Aug'24
147 | 1 | 72/0 | DB1+0 | DRY | Pipe Type | 01.08.24 | Mahadev engg.
148 | 2 | 71/2 | DA+0 | DRY | Pipe Type | 01.08.24 | Mahadev engg. |  |  |  | 51
149 | 3 | 43/6 | DA+6 RC | SANDY | Pipe Type | 01.08.24 | Om Const |  |  |  | 22
150 | 4 | 44/0 | DB1+0 | SANDY | Pipe Type | 02.08.24 | Om Const
151 | 5 | 50/2 | DA+0 | DFR | Counter Poise | 11.08.24 | Bhati Const.
152 | 6 | 42/0 | DC2+9 RC | SANDY | Pipe Type | 11.08.24 | Om Const
153 | 7 | 47/1 | DA+0 | DRY | Pipe Type | 14.08.24 | Bhati Const.
154 | 8 | 72/7 | DB1+9 RC | SANDY | Pipe Type | 14.08.24 | Mahadev engg.
155 | 9 | 72/6 | DA+0 RC | SANDY | Pipe Type | 14.08.24 | Mahadev engg. |  |  | 48
156 | 10 | 69/6 | DA+0 | DRY | Pipe Type | 23.08.24 | Mahadev engg. |  |  | 27
157 | 11 | 68/5 | DA+3 | DRY | Pipe Type | 23.08.24 | Shakti Construction
158 | 12 | 63/0 | DD45+0 | DRY | Pipe Type | 24.08.24 | Mahadev engg.
159 | 13 | 43/0 | DB2+9 RC | SANDY | Pipe Type | 31.08.24 | Om Const
160 | 14 | 50/1 | DA+0 RC | DFR | Counter Poise | 31.08.24 | Mahadev engg.
Sept'24
161 | 1 | 69/2 | DA+0 | DRY | Pipe Type | 02.09.24 | Bhati Const.
162 | 2 | 69/3 | DA+0 | Sandy | Pipe Type | 02.09.24 | Bhati Const.
163 | 3 | 69/4 | DA+0 | DRY | Pipe Type | 02.09.24 | Bhati Const.
164 | 4 | 69/5 | DA+0 | DRY | Pipe Type | 02.09.24 | Bhati Const.
165 | 5 | 68/2 | DA+3 | DRY | Pipe Type | 02.09.24 | Shakti Construction
166 | 6 | 67/0 | DD45+0 | DRY | Pipe Type | 04.09.24 | Awadh Const.
167 | 7 | 69/7 | DA+0 | DRY | Pipe Type | 05.09.24 | Mahadev engg.
168 | 8 | 73/0 | DD45+9 | DFR | Counter Poise | 07.10.24 | Mahadev engg.
169 | 9 | 69/1 | DA+0 | DRY | Pipe Type | 05.09.24 | Bhati Const.
170 | 10 | 67/1 | DB1+9 | DRY | Pipe Type | 05.09.24 | Awadh Const.
171 | 11 | 35/5 | DA+0 RC | SANDY | Pipe Type | 09.09.24 | Om Const
172 | 12 | 68/4 | DA+3 | DRY | Pipe Type | 10.09.24 | Shakti Construction
173 | 13 | 68/6 | DA+3 | DRY | Pipe Type | 10.09.24 | Shakti Construction
174 | 14 | 35/6 | DA+9 RC | SANDY | Pipe Type | 15.09.24 | Om Const
175 | 15 | 66/1 | DA+3 | DRY | Pipe Type | 15.09.24 | Shree Shyam Const.
176 | 16 | 66/2 | DA+0 | DRY | Pipe Type | 15.09.24 | Shree Shyam Const.
177 | 17 | 66/4 | DA+3 | DRY | Pipe Type | 15.09.24 | Shree Shyam Const.
178 | 18 | 69/0 | DB1+0 | DRY | Pipe Type | 16.09.24 | Bhati Const.
179 | 19 | 71/5 | DA+0 | DRY | Pipe Type | 16.09.24 | Mahadev engg.
180 | 20 | 68/3 | DA+0 | DRY | Pipe Type | 22.09.24 | Shakti Construction
181 | 21 | 65/7 | DA+0 | DRY | Pipe Type | 23.09.24 | Shree Shyam Const.
182 | 22 | 35/4 | DA+3 RC | SANDY | Pipe Type | 27.09.24 | Om Const
183 | 23 | 43/2 | DA+9 RC | SANDY | Pipe Type | 27.09.24 | Kalpana
184 | 24 | 43/3 | DA+3 RC | SANDY | Pipe Type | 27.09.24 | Kalpana
Oct'24
185 | 1 | 35/8 | DA+0 RC | SANDY | Pipe Type | 04.10.24 | Om Const
186 | 2 | 35/7 | DA+3 RC | SANDY | Pipe Type | 04.10.24 | Om Const
187 | 3 | 68/0 | DD45+0 | DRY | Pipe Type | 07.10.23 | Shakti Construction
188 | 4 | 68/1 | DA+3 | DRY | Pipe Type | 07.10.23 | Shakti Construction
189 | 5 | 66/3 | DA+3 | DRY | Pipe Type | 07.10.23 | Shree Shyam Const.
190 | 6 | 66/0 | DD45+0 | DRY | Pipe Type | 07.10.23 | Shree Shyam Const.
191 | 7 | 62/0 | DC2+0 | DRY | Pipe Type | 07.10.23 | Mahadev engg.
192 | 8 | 72/1 | DA+0 | DRY | Pipe Type | 19.10.24 | Mahadev engg.
193 | 9 | 71/0 | DD60+0 | FS | Pipe Type | 22.10.24 | Mahadev engg.
194 | 10 | 35/2 | DA+0 (RC) | SANDY | Pipe Type | 23.10.24 | Om Const
195 | 11 | 69/9 | DA+0 | DFR | Counter Poise | 26.10.24 | Mahadev engg.
196 | 12 | 64/0 | DB2+0 | DRY | Pipe Type | 26.10.24 | Bhati Const.
197 | 13 | 35/1 | DA+0 RC | SANDY | Pipe Type | 17.10.24 | Om Const
198 | 14 | 35/0 | DB2+0 RC | SANDY | Pipe Type | 17.10.24 | Om Const
Nov'24
199 | 1 | 35/3 | DA+0 (RC) | SANDY | Pipe Type | 06.11.24 | Om Const
200 | 2 | 34/4 | DA+6 RC | SANDY | Pipe Type | 08.11.24 | Om Const
201 | 3 | 34/6 | DA+6 RC | SANDY | Pipe Type | 22.11.24 | Om Const
202 | 4 | 38/9 | DB1+6 RC | SANDY | Pipe Type | 22.11.24 | Om Const
203 | 5 | 39/0 | DC2+3 RC | SANDY | Pipe Type | 22.11.24 | Om Const
204 | 6 | 58/13 | DA+0 | DRY | Pipe Type | 29.11.24 | Bhati Const.
Dec'24
205 | 1 | 34/3 | DA+9 RC | SANDY | Pipe Type | 04.12.24 | Om Const
206 | 2 | 40/12 | DA+0 RC | SANDY | Pipe Type | 06.12.24 | Nadeem rasool
207 | 3 | 69/8 | DA+0 | DFR | Pipe Type | 08.12.24 | Mahadev engg.
208 | 4 | 64/8 | DA+0 | DRY | Pipe Type | 08.12.24 | Bhati Const.
209 | 5 | 64/7 | DA+3 | DRY | Pipe Type | 12.12.24 | Bhati Const.
210 | 6 | 34/2 | DA+9 RC | SANDY | Pipe Type | 17.12.24 | Om Const
211 | 7 | 37/8 | DA+0 | SANDY | Pipe Type | 17.12.24 | Nadeem rasool
212 | 8 | 64/1 | DA+6 | DRY | Pipe Type | 19.12.24 | Bhati Const.
213 | 9 | 64/9 | DA+0 | DRY | Pipe Type | 19.12.24 | Bhati Const.
214 | 10 | 70/0 | DD60+0 | FS | Pipe Type | 19.12.24 | Mahadev engg.
215 | 11 | 64/6 | DA+3 | DRY | Pipe Type | 28.12.24 | Bhati Const.
216 | 12 | 38/4 | DA+0 RC | SANDY | Pipe Type | 30.12.24 | Nadeem rasool
217 | 13 | 38/0 | DC1+0 | SANDY | Pipe Type | 31.12.24 | Nadeem rasool
218 | 14 | 38/5 | DA+0 RC | SANDY | Pipe Type | 31.12.24 | Nadeem rasool
219 | 15 | 38/7 | DA+0 RC | SANDY | Pipe Type | 31.12.24 | Nadeem/Iqbal
2025-01-25
220 | 1 | 34/5 | DCT+0 | SANDY | Pipe Type | 03.01.25 | Om Const
221 | 2 | 33/8 | DA+3 RC | SANDY | Pipe Type | 04.01.25 | Om Const
222 | 3 | 34/1 | DA+3 RC | SANDY | Pipe Type | 05.01.25 | Om Const
223 | 4 | 63/1 | DA+6 | DRY | Pipe Type | 06.01.25 | Bhati Const.
224 | 5 | 37/7 | DA+3 RC | SANDY | Pipe Type | 07.01.25 | Iqbal
225 | 6 | 37/5 | DA+3 RC | SANDY | Pipe Type | 07.01.25 | Iqbal
226 | 7 | 37/6 | DA+6 RC | SANDY | Pipe Type | 07.01.25 | Iqbal
227 | 8 | 40/1 | DA+0 RC | SANDY | Pipe Type | 10.01.25 | Meer Construction
228 | 9 | 40/0 | DC2+0 RC | SANDY | Pipe Type | 10.01.25 | Meer Construction
229 | 10 | 39/2 | DA+0 RC | SANDY | Pipe Type | 10.01.25 | Meer Construction
230 | 11 | 39/5 | DA+3 RC | SANDY | Pipe Type | 10.01.25 | Meer Construction
231 | 12 | 39/6 | DA+0 RC | SANDY | Pipe Type | 10.01.25 | Meer Construction
232 | 13 | 39/7 | DA+0 RC | SANDY | Pipe Type | 10.01.25 | Meer Construction
233 | 14 | 60/0 | DC2+3 | DRY | Pipe Type | 20.01.25 | Bhati Const.
234 | 15 | 41/0 | DB1+0 RC | SANDY | Pipe Type | 23.01.25 | Nadeem rasool
235 | 16 | 41/1 | DA+3 RC | SANDY | Pipe Type | 23.01.25 | Nadeem rasool
236 | 17 | 41/2 | DA+0 RC | SANDY | Pipe Type | 23.01.25 | Nadeem rasool
237 | 18 | 41/3 | DA+0 RC | SANDY | Pipe Type | 23.01.25 | Nadeem rasool
Feb'25
238 | 1 | 64/2 | DA+0 | DRY | Pipe Type | 03.02.25 | Tantary Const.
239 | 2 | 64/3 | DA+0 | DRY | Pipe Type | 03.02.25 | Tantary Const.
240 | 3 | 64/4 | DA+3 | DRY | Pipe Type | 03.02.25 | Tantary Const.
241 | 4 | 64/5 | DA+3 | DRY | Pipe Type | 03.02.25 | Tantary Const.
242 | 5 | 33/3 | DA+0 | SANDY | Pipe Type | 07.02.25 | Tantary Const.
243 | 6 | 44/5 | DA+6 | WFR | Counter Poise | 07.02.25 | Bhati Const.
244 | 7 | 33/4 | DA+0 (RC) | SANDY | Pipe Type | 14.02.25 | Tantray Construction
245 | 8 | 33/5 | DA+0 | SANDY | Pipe Type | 15.02.25 | Tantray Construction
246 | 9 | 59/4 | DA+0 | DRY | Pipe Type | 19.02.25 | Bhati Const.
247 | 10 | 61/0 | DB1+6 | DRY | Pipe Type | 19.02.25 | Bhati Const.
248 | 11 | 63/4 | DA+0 | DRY | Pipe Type | 19.02.25 | Bhati Const.
249 | 12 | 40/8 | DA+0 RC | SANDY | Pipe Type | 23.02.25 | Tantray Construction
250 | 13 | 40/9 | DA+0 RC | SANDY | Pipe Type | 23.02.25 | Tantray Construction
251 | 14 | 33/0 | DB2+3 RC | SANDY | Pipe Type | 26.02.25 | Nadeem rasool
252 | 15 | 33/2 | DA+0 RC | SANDY | Pipe Type | 26.02.25 | Iqbal
253 | 16 | 33/6 | DA+6 RC | SANDY | Pipe Type | 26.02.25 | Iqbal
Mar'25
254 | 1 | 37/0 | DD60+25 RC | SANDY | Pipe Type | 11.03.25 | OM Const
255 | 2 | 37/1 | DB1+9 RC | SANDY | Pipe Type | 11.03.25 | OM Const
256 | 3 | 33/7 | DA+9 RC | SANDY | Pipe Type | 16.03.25 | Om Const
257 | 4 | 45/0 | DD60+25 RC | SANDY | Pipe Type | 19.03.25 | Bhati Const.
258 | 5 | 46/0 | DD60+25 RC | SANDY | Pipe Type | 19.03.25 | Bhati Const.
259 | 6 | 46/1 | DA+6 RC | SANDY | Pipe Type | 19.03.25 | Bhati Const.
260 | 7 | 35/9 | DA+3 RC | SANDY | Pipe Type | 21.03.25 | Om Const
261 | 8 | 34/0 | DB1+6 RC | SANDY | Pipe Type | 21.03.25 | Om Const
262 | 9 | 36/0 | DD60+25 RC | SANDY | Pipe Type | 22.03.25 | OM Const
263 | 10 | 40/7 | DA+3 RC | SANDY | Pipe Type | 06.12.24
264 | 11 | 65/0 | DB2+3 | SANDY | Pipe Type | 28.03.25 | Bhati Const.
265 | 12 | 63/3 | DA+3 | DRY | Pipe Type | 29.03.25 | Bhati Const.
1 |  |  |  | 1 | 1 |  | 1
1 |  |  |  | 1 | 1 |  | 1
1 |  |  |  | 1 | 1 |  | 1
1 |  |  |  | 1 | 1 |  | 1
1 |  |  |  | 1 | 1 |  | 1
1 |  |  |  | 1 | 1 |  | 1

## Revetment Pkg-G (hidden)
Revetment work
SI. No | Loc No | Tower Type | Dt. of Start | Dt. of complete | Random Rubble stone masonry including excavation (1:5 Cement concrete) | Excavation Volume | Back filling and levelling of volumes enclosed by revetment. | M15 Conc Nominal Mix 1:2:4 for top seal cover | M10 (PEDDING -PCC)
1 | 35/5 | DA+0 RC | 20.11.24
Total |  |  |  |  | 0 |  | 0 | 0 | 0

## Benching Status-F (hidden)
RC, Benching & Revetment Locations
Sl No. | RC | Loc No. | Tower Type | CP Position Up/Down | Raised Chimney | Chimney Extension |  |  |  | Submitted Benching Volume (Cum) |  | Approved Benching Volume (Cum) |  | Approval Date | JMC NO | JMC Date
[6 empty] | A | B | C | D | Cutting | Filling | Cutting | Filling
|  | 47 | [7 empty] | 26947.807 |  | 10818.857 |  |  | 10
1 |  | 40/0 | DC2+0 |  |  | 1 | 1 | 0 | 0 | 91.75
2 | Y | 40/1 | DA+6 |  |  | 1 | 2 | 0 | 0 | 153.267
3 |  | 40/2 | DA+3 |  |  | 0 | 0 | 0 | 0 | 48.633
4 | Y | 40/3 | DA+6 |  |  | 1 | 2 | 0 | 0 | 238.433
5 | Y | 41/0 | DC1+6 |  |  | 3 | 1 | 0 | 1 | 249.883
6 | Y | 41/1 | DB1+9 | 4 | 4 | 4 | 1 | 6 | 6 | 120.747
7 | Y | 41/2 | DA+0 |  |  | 0 | 0 | 1 | 1 | 1170.806
8 | Y | 42/0 | DC1+0 |  |  | 1 | 0 | 0 | 2 | 339.457
9 | Y | 42/1 | DA+6 |  |  | 1 | 0 | 0 | 0 | 127.8
10 | Y | 42/2 | DA+6 |  |  | 0 | 0 | 1 | 3 | 91.933
11 |  | 42/3 | DA+0 |  |  | 0 | 0 | 0 | 0 | 9.463
12 |  | 42/4 | DA+0 |  |  | 0 | 0 | 0 | 0 | 136.417
13 | Y | 42/5 | DA+9 |  |  | 0 | 0 | 0 | 1 | 106.4
14 | Y | 42/6 | DA+0 |  |  | 2 | 1 | 0 | 2 | 144.417
15 |  | 43/0 | DB1+0 |  |  | 0 | 0 | 0 | 0 | 68.726
16 | Y | 43/1 | DA+6 |  |  | 0 | 0 | 3 | 3 | 199.917
17 | Y | 43/2 | DA+3 |  |  | 1 | 0 | 0 | 1 | 189.737
18 | Y | 43/3 | DA+0 |  |  | 0 | 1 | 0 | 0 | 275.117
19 | Y | 43/4 | DA+3 |  |  | 1 | 1 | 0 | 0 | 108.9
20 |  | 43/5 | DA+3 |  |  | 0 | 0 | 0 | 0 | 35.95
21 | Y | 43/6 | DA+3 |  |  | 0 | 0 | 0 | 0 | 17.8
22 |  | 43/7 | DA+3 | 0.2 |  | 0 | 0 | 0 | 0 | 46.75
23 | Y | 43/8 | DA+9 |  |  | 1 | 0 | 0 | 0 | 120.65
24 |  | 43/9 | DA+9 |  |  | 0 | 0 | 0 | 0 | 61.583
25 | Y | 43/10 | DA+3 |  |  | 3 | 3 | 0 | 0 | 70.8
26 | Y | 43/11 | DA+3 | 1 |  | 2 | 3 | 0 | 1 | 125.717
27 | Y | 44/0 | DB1+3 |  |  | 0 | 1 | 1 | 0 | 227.366
28 |  | 44/1 | DA+0 |  |  | 0 | 0 | 1 | 0 | 516.62
29 |  | 44/2 | DA+0 |  |  | 0 | 0 | 0 | 0 | 145.7
30 | Y | 44/3 | DA+0 |  |  | 2 | 0 | 0 | 1 | 35.453
31 | Y | 44/4 | DA+9 | 3.3 | 3 | 4 | 3 | 3 | 3 | 62.367
32 | Y | 44/5 | DA+9 |  |  | 1 | 3 | 0 | 0 | 476.6
33 | Y | 44/6 | DB1+3 |  |  | 1 | 0 | 0 | 1 | 263.667
34 |  | 44/7 | DA+9 |  |  | 0 | 0 | 0 | 0 | 107.267
35 | Y | 44/8 | DC1+0 |  |  | 1 | 2 | 0 | 1 | 114.075
36 | Y | 44/9 | DA+9 | 3 |  | 4 | 0 | 2 | 6 | 218.923
37 | Y | 44/10 | DA+9 |  |  | 0 | 1 | 0 | 0 | 68.233
38 | Y | 44/11 | DA+0 |  |  | 0 | 1 | 0 | 0 | 148.233
39 | Y | 45/0 | DC2+0 |  |  | 0 | 1 | 0 | 0 | 104.47
40 | Y | 45/1 | DA+0 |  |  | 0 | 0 | 1 | 2 | 329.483
41 | Y | 46/0 | DD60+18 | 3 |  | 0 | 4 | 4 | 0 | 773.08
42 | Y | 47/0 | DD60+18 |  | 2 | 3 | 2 | 2 | 2 | 333.585
43 | Y | 47/1 | DA+6 |  | 1 | 1 | 1 | 2 | 2 | 334.445 |  | 183.244
44 |  | 47/2 | DA+9 |  |  | 0 | 0 | 0 | 0 | 35.008 |  | 14.894 |  |  | JMC-72
45 | Y | 47/3 | DA+9 |  |  | 1 | 2 | 0 | 0 | 351.248 |  | 198.462 |  |  | JMC-73
46 |  | 47/4 | DA+3
47 | Y | 47/5 | DA+0 |  |  | 0 | 1 | 0 | 0 | 151.406 |  | 50.19 |  |  | JMC-74
48 |  | 47/6 | DA+3 |  |  | 0 | 0 | 0 | 0 | 214.683 |  | 105.461 |  |  | JMC-68
49 |  | 47/7 | DA+3 |  |  | 0 | 0 | 0 | 0 | 146.833 |  | 85.356 |  |  | JMC-55 | 31-07-24
50 | Y | 47/8 | DA+0 |  |  | 1 | 0 | 0 | 0 | 186.171 |  | 58.541 |  |  | JMC-56 | 31-07-24
51 |  | 47/9 | DA+3 |  |  | 0 | 0 | 0 | 0 | 36.917 |  | 21.243 |  |  | JMC-57 | 31-07-24
52 |  | 47/10 | DA+6 |  |  | 0 | 0 | 0 | 0 | 105.1 |  | 44.208 |  |  | JMC-58 | 31-07-24
53 |  | 48/0 | DC2+0 |  |  | 0 | 0 | 0 | 0 | 271.371 |  | 121.376
54 |  | 48/1 | DA+9 |  |  | 0 | 0 | 0 | 0 | 83.933 |  | 43.92 |  |  | JMC-64 | 31-07-24
55 |  | 49/1 | DA+0 |  |  | 0 | 0 | 0 | 0 | 28.5 |  | 20.37 |  |  | JMC-65 | 31-07-24
56 |  | 49/2 | DA+3 |  |  | 0 | 0 | 0 | 0 | 237.2 |  | 152.093 |  |  | JMC-43 | 31-07-24
57 |  | 49/3 | DA+3 |  |  | 0 | 0 | 0 | 0 | 130.95 |  | 59.392 |  |  | JMC-44 | 31-07-24
58 |  | 49/4 | DA+3 |  |  | 0 | 0 | 0 | 0 | 52.95 |  | 27.468 |  |  | JMC-45 | 31-07-24
59 |  | 49/5 | DA+3 | 0.1 |  | 0 | 0 | 0 | 0 | 68.133 |  | 33.446 |  |  | JMC-46 | 31-07-24
60 |  | 49/6 | DA+0 | 0.1 |  | 0 | 0 | 0 | 0 | 29.783 |  | 10.948 |  |  | JMC-47 | 31-07-24
61 | Y | 49/7 | DA+3 |  |  | 0 | 3 | 2 | 2 | 190.733 |  | 89.935
62 | Y | 50/0 | DB2+0 |  |  | 0 | 0 | 0 | 1 | 29.469 |  | 6.775
63 | Y | 50/1 | DA+6 |  |  | 1 | 0 | 0 | 0 | 258.417 |  | 126.731 |  |  | JMC-66 | 31-07-24
64 | Y | 50/2 | DA+9 |  | 2 | 2 | 2 | 2 | 2 | 109.183 |  | 50.596 |  |  | JMC-75
65 | Y | 50/3 | DA+6 |  |  | 0 | 0 | 1 | 0 | 82.817 |  | 40.792
66 | Y | 50/4 | DA+9 |  | 3 | 3 | 3 | 4 | 3 | 90.133 |  | 31.88 |  |  | JMC-76
67 | Y | 50/5 | DA+9 |  | 3 | 4 | 3 | 4 | 3 | 82.717 |  | 13.972
68 | Y | 50/6 | DA+9 |  | 3 | 3 | 4 | 3 | 3 | 266.417 |  | 133.278
69 | Y | 50/7 | DA+0 |  |  | 0 | 0 | 0 | 1 | 58.15 |  | 20.044 |  |  | JMC-67 | 31-07-24
70 |  | 50/8 | DA+9 |  |  | 0 | 0 | 0 | 0 | 379.65 |  | 287.607 |  |  | JMC-69
71 | Y | 50/9 | DA+0 |  |  | 0 | 0 | 1 | 0 | 551.811 |  | 283.026
72 | Y | 50/10 | DA+0 |  |  | 0 | 0 | 1 | 0 | 304.834 |  | 114.598
73 |  | 51/0 | DC2+0 |  |  | 0 | 0 | 0 | 0 | 119.229 |  | 103.624
74 | Y | 51/1 | DA+0 |  |  | 0 | 0 | 1 | 0 | 74.897 |  | 10.113 |  |  | JMC-70
75 |  | 51/2 | DA+0 | -1 |  | 0 | 0 | 0 | 0 | 73.95 |  | 12.784
76 | Y | 52/0 | DC2+0 |  |  | 0 | 0 | 3 | 3 | 474.917 |  | 226.626 |  | 2024-01-09
77 | Y | 52/1 | DA+6 |  |  | 0 | 4 | 0 | 0 | 95.517 |  | 20.215 |  | 2024-01-09
78 | Y | 52/2 | DA+6 |  |  | 0 | 0 | 0 | 3 | 74.467 |  | 56.535 |  | 2024-01-09
79 | Y | 52/3 | DA+9 |  | 3 | 4 | 3 | 3 | 3 | 54.25 |  | 21.459 |  | 2024-01-09 | JMC-71
80 | Y | 52/4 | DA+9 |  |  | 2 | 2 | 0 | 0 | 35.517 |  | 14.371 |  | 2024-01-09
81 | Y | 52/5 | DA+9 |  |  | 0 | 0 | 0 | 1 | 269.167 |  | 177.797 |  | 2024-01-09 | JMC-9 | 22.03.24
82 |  | 52/6 | DA+6 |  |  | 0 | 0 | 0 | 0 | 343.483 |  | 239.936 |  | 2024-01-09 | JMC-10 | 22.03.24
83 | Y | 52/7 | DA+3 |  |  | 0 | 3 | 1 | 0 | 464.317 |  | 306.372 |  | 2024-01-09 | JMC-11 | 22.03.24
84 |  | 52/8 | DA+6 |  |  | 0 | 0 | 0 | 0 | 644.717 |  | 582.599 |  | 2024-01-09 | JMC-12 | 22.03.24
85 |  | 52/9 | DA+3 |  |  | 0 | 0 | 0 | 0 | 192.433 |  | 139.028 |  | 2024-01-09 | JMC-13 | 22.03.24
86 | Y | 52/10 | DA+9 |  | 1 | 1 | 2 | 1 | 1 | 270.567 |  | 123.839 |  | 2024-01-09 | JMC-14 | 22.03.24
87 | Y | 53/0 | DB2+9 |  | 4 | 4 | 4 | 4 | 4 | 102.651 |  | 342.89 |  | 2024-01-09
88 | Y | 53/1 | DA+9 |  | 4 | 4 | 4 | 4 | 4 | 511.767 |  | 302.874 |  | 2024-01-09
89 | Y | 53/2 | DA+0 |  |  | 0 | 0 | 0 | 2 | 121.063 |  | 38.768 |  | 2024-01-09
90 | Y | 53/3 | DA+9 |  |  | 0 | 4 | 1 | 0 | 454.927 |  | 204.813 |  | 2024-01-09
91 | Y | 53/4 | DA+0 |  |  | 0 | 2 | 1 | 0 | 686.16 |  | 280.645 |  | 2024-01-09
92 |  | 53/5 | DA+3 |  |  | 0 | 0 | 0 | 0 | 104.9 |  | 76.75 |  | 2024-01-09 | JMC-49 | 31-07-24
93 | Y | 53/6 | DA+6 |  |  | 1 | 1 | 3 | 1 | 111.483 |  | 14.573 |  | 2024-01-09
94 |  | 53/7 | DA+0 |  |  | 0 | 0 | 0 | 0 | 245.537 |  | 112.464 |  | 2024-01-09
95 |  | 53/8 | DA+9 |  | 0 | 0 | 0 | 0 | 0 | 326.55 |  | 334.123 |  | 2024-01-09
96 |  | 54/0 | DB1+6 |  |  | 0 | 0 | 0 | 0 | 400.8 |  | 293.967 |  | 2024-01-09
97 | Y | 54/1 | DA+9 |  |  | 1 | 1 | 0 | 0 | 74.4 |  | 17.753 |  | 2024-01-09
98 |  | 54/2 | DA+3 |  |  | 0 | 0 | 0 | 0 | 105.35 |  | 63.16 |  | 2024-01-09
99 | Y | 54/3 | DA+6 |  |  | 0 | 2 | 0 | 0 | 106.517 |  | 71.292 |  | 2024-01-09
100 | Y | 54/4 | DA+9 |  | 0 | 1 | 2 | 0 | 0 | 264 |  | 131.156 |  | 2024-01-09
101 | Y | 54/5 | DA+9 |  | 1 | 1 | 3 | 3 | 1 | 210.2 |  | 91.403 |  | 2024-01-09
102 | Y | 55/0 | DB1+6 |  |  | 0 | 1 | 1 | 0 | 375.874 |  | 244.465 |  | 2024-01-09
103 | Y | 55/4 | DA+0 |  |  | 0 | 0 | 0 | 1 | 248.177 |  | 98.757 |  | 2024-01-09 | JMC-15 | 22.03.24
104 | Y | 55/5 | DA+0 |  |  | 0 | 0 | 1 | 3 | 674.16 |  | 250.709 |  | 2024-01-09 | JMC-16 | 22.03.24
105 | Y | 55/6 | DA+0 |  |  | 0 | 0 | 1 | 2 | 100.954 |  | 24.027 |  | 2024-01-09 | JMC-17 | 22.03.24
106 | Y | 55/7 | DA+0 |  |  | 0 | 0 | 1 | 0 | 551.126 |  | 317.518 |  | 2024-01-09 | JMC-18 | 22.03.24
107 | Y | 55/8 | DA+9 |  |  | 0 | 0 | 1 | 0 | 480.283 |  | 241.51 |  | 2024-01-09
108 | Y | 56/0 | DD60+9 |  | 4 | 4 | 6 | 4 | 4 | 454.562 |  | 387.425 |  | 2024-01-09
109 | Y | 57/0 | DD60+9 |  | 0 | 0 | 1 | 1 | 0 | 715.032 |  | 562.651 |  | 2024-01-09
110 |  | 57/1 | DA+3 |  |  | 0 | 0 | 0 | 0 | 38.65 |  | 24.155 |  | 2024-01-09
111 |  | 57/2 | DA+3 |  |  | 0 | 0 | 0 | 0 | 64.033 |  | 20.988 |  | 2024-01-09 | JMC-50 | 31-07-24
112 |  | 57/3 | DA+0 |  |  | 0 | 0 | 0 | 0 | 91.063 |  | 39.024 |  | 2024-01-09 | JMC-51 | 31-07-24
113 |  | 57/4 | DA+0 |  |  | 0 | 0 | 0 | 0 | 165.446 |  | 77.472 |  | 2024-01-09 | JMC-52 | 31-07-24
114 | Y | 57/5 | DA+3 |  |  | 0 | 0 | 0 | 1 | 114.817 |  | 54.629 |  | 2024-01-09 | JMC-53 | 31-07-24
115 | Y | 57/6 | DA+3 |  |  | 0 | 1 | 0 | 0 | 118.95 |  | 69.342 |  | 2024-01-09 | JMC-54 | 31-07-24
116 |  | 58/0 | DC1+3 |  |  | 0 | 0 | 0 | 0 | 16.509 |  |  |  | 2023-12-22
117 |  | 59/0 | DC2+0 |  |  | 0 | 0 | 0 | 0 | 97.629 |  | 97.629 |  | 2023-12-22
118 | Y | 59/1 | DA+3 |  |  | 0 | 0 | 0 | 1 | 30.167 |  |  |  | 2023-12-22
119 |  | 59/2 | DA+3 |  |  | 0 | 0 | 0 | 0 | 74.35 |  | 57.328 |  | 2023-12-22
120 | Y | 59/3 | DA+3 |  |  | 0 | 0 | 0 | 1 | 29.783 |  |  |  | 2023-12-22
121 |  | 59/7 | DA+3 |  |  | 0 | 0 | 0 | 0 | 88.917 |  | 67.301 |  | 2023-12-22 | JMC-19 | 31-07-24
122 |  | 59/8 | DB1+3 |  |  | 0 | 0 | 0 | 0 | 30.926 |  |  |  | 2023-12-22
123 |  | 59/9 | DA+3 |  |  | 0 | 0 | 0 | 0 | 51.683 |  |  |  | 2023-12-22
124 | Y | 59/11 | DA+6 |  |  | 0 | 0 | 2 | 0 | 609.4 |  | 443.002 |  | 2023-12-22
125 |  | 59/12 | DA+6 |  |  | 0 | 0 | 0 | 0 | 69.983 |  |  |  | 2023-12-22
126 | Y | 60/2 | DA+3 |  |  | 2 | 2 | 0 | 0 | 150.115 |  | 67.99 |  | 2023-12-22 | JMC-20 | 31-07-24
127 |  | 61/1 | DA+6 |  |  | 0 | 0 | 0 | 0 | 130.228 |  | 98.667 |  | 2023-12-22 | JMC-21 | 31-07-24
128 | Y | 61/7 | DA+9 |  |  | 0 | 0 | 0 | 1 | 237.78 |  | 155.449 |  | 2023-12-22 | JMC-22 | 31-07-24
129 | Y | 61/8 | DA+6 |  |  | 1 | 2 | 1 | 0 | 139.242 |  | 18.852 |  | 2023-12-22 | JMC-23 | 31-07-24
130 |  | 62/0 | DB2+0 |  |  | 0 | 0 | 0 | 0 | 50.997 |  | 36.79 |  | 2023-12-22 | JMC-62 | 31-07-24
131 | Y | 62/1 | DA+3 |  |  | 0 | 0 | 1 | 2 | 200.388 |  | 135.911 |  | 2023-12-22 | JMC-24 | 31-07-24
132 | Y | 62/2 | DA+3 |  |  | 0 | 1 | 0 | 0 | 22.433 |  |  |  | 2023-12-22
133 |  | 62/4 | DA+3 |  |  | 0 | 0 | 0 | 0 | 27.142 |  |  |  | 2023-12-22
134 |  | 62/5 | DA+0 |  |  | 0 | 0 | 0 | 0 | 109.341 |  | 45.234 |  | 2023-12-22 | JMC-25 | 31-07-24
135 |  | 62/6 | DA+3 |  |  | 0 | 0 | 0 | 0 | 23.573 |  |  |  | 2023-12-22
136 |  | 63/0 | DC1+0 |  |  | 0 | 0 | 0 | 0 | 199.633 |  | 199.633 |  | 2023-12-22 | JMC-63 | 31-07-24
137 |  | 63/3 | DA+3 |  |  | 0 | 0 | 0 | 0 | 173.683 |  | 140.624 |  | 2023-12-22 | JMC-48 | 31-07-24
138 |  | 63/5 | DA+3 |  |  | 0 | 0 | 0 | 0 | 31.908 |  |  |  | 2023-12-22

## Benching Status-G (hidden)
RC, Benching & Revetment Locations
Sl No. | RC | Loc No. | Tower Type | CP Position Up/Down | Raised Chimney | Chimney Extension |  |  |  | Submitted Benching Volume (Cum) |  | Approved Benching Volume (Cum) |  | Approval Date | JMC NO | JMC Date
[6 empty] | A | B | C | D | Cutting | Filling | Cutting | Filling
|  | 28 | [7 empty] | 36249.329 |  | 13738.234 |  |  | 8
1 |  | 2/0 | DC1+0
2 |  | 2/2 | DA+0 |  |  | 0 | 0 | 1 | 1 | 141.89 |  | 140.97 |  | 24-11-23
3 |  | 2/3 | DA+0 |  |  | 1 | 1 | 0 | 0 | 33.32 |  | 22.61 |  | 24-11-23
4 |  | 2/4 | DA+3 |  |  | 0 | 0 | 0 | 0 | 28.01 |  | 28.01 |  | 24-11-23
5 |  | 2/5 | DA+3 |  |  | 0 | 1 | 1 | 0 | 64.4 |  | 53.49 |  | 24-11-23
6 |  | 2/6 | DA+6 |  |  | 0 | 2 | 0 | 0 | 111.36 |  | 107.54 |  | 24-11-23
7 |  | 2/7 | DA+6 |  |  | 0 | 0 | 1 | 0 | 210 |  | 209.95 |  | 24-11-23
8 |  | 3/0 | DD60+0
9 |  | 5/0 | DB1+9 |  | 2 | 2 | 2 | 2 | 2
10 |  | 6/0 | DB2+9 |  | 2 | 2 | 2 | 2 | 2
11 |  | 6/1 | DA+0 |  |  | 1 | 0 | 0 | 0 | 57.82 |  | 53.48 |  | 24-11-23
12 |  | 7/0 | DB1+0
13 |  | 8/3 | DA+3 |  |  | 0 | 0 | 0 | 1 | 49.13
14 |  | 8/4 | DA+0 |  |  | 1 | 1 | 1 | 2 | 38.56
15 |  | 8/5 | DA+3 |  |  | 0 | 0 | 0 | 0 | 35.69
16 |  | 8/9 | DA+3 |  |  | 0 | 0 | 0 | 0 | 42.16
17 |  | 9/0 | DD60+18
18 |  | 10/0 | DD60+18
19 |  | 10/1 | DA+3 |  |  | 0 | 0 | 0 | 0 | 74.8
20 |  | 10/22 | DA+0 |  |  | 1 | 4 | 0 | 0 | 82.26
21 |  | 10/23 | DA+9 |  |  | 2 | 6 | 1 | 1 | 79.35
22 |  | 11/0 | DB1+3
23 |  | 11/12 | DA+0
24 |  | 11/13 | DA+0
25 |  | 13/3 | DA+0
26 |  | 15/5 | DA+3
27 |  | 15/6 | DA+0
28 |  | 15/7 | DA+6
29 |  | 21/2 | DA+3 |  |  | 0 | 0 | 1 | 0 | 33.758 |  | 13.878
30 |  | 21/5 | DA+3 |  |  | 0 | 0 | 0 | 2 | 301.545 |  | 175.845
31 |  | 21/10 | DA+9 |  |  | 1 | 1 | 0 | 0 | 259.925 |  | 127.123
32 |  | 21/12 | DA+9 |  |  | 0 | 0 | 1 | 0 | 175.99 |  | 80.099
33 |  | 22/6 | DA+6 |  |  | 0 | 0 | 2 | 1 | 396.942 |  | 249.598
34 |  | 22/9 | DA+6 |  |  | 0 | 0 | 0 | 1 | 330.54 |  | 176.873
35 |  | 23/0 | DB2+0 |  |  | 0 | 1 | 0 | 0 | 344.386 |  | 344.386
36 |  | 23/1 | DA+0 |  |  | 0 | 0 | 0 | 0 | 175.029 |  | 76.44
37 |  | 23/3 | DA+0 |  |  | 0 | 0 | 0 | 0 | 69.578 |  | 33.81
38 |  | 23/6 | DA+6 |  |  | 0 | 0 | 0 | 0 | 203.947 |  | 95.149
39 |  | 23/7 | DA+9 |  |  | 1 | 0 | 0 | 2 | 428.652 |  | 212.812
40 |  | 23/8 | DA+9 |  |  | 1 | 1 | 0 | 0 | 230.72 |  | 119.029
41 |  | 23/11 | DA+6 |  |  | 0 | 0 | 1 | 0 | 227.185 |  | 107.373
42 |  | 24/0 | DB2+0 |  |  | 0 | 0 | 0 | 0 | 212.246
43 |  | 24/6 | DA+0 |  |  | 1 | 0 | 0 | 0 | 77.827 |  | 20.536
44 |  | 25/0 | DC1+0
45 |  | 25/2 | DA+0 |  |  | 0 | 0 | 0 | 0 | 37.344
46 |  | 25/3 | DA+0 |  |  | 0 | 2 | 1 | 0 | 196.759
47 |  | 25/4 | DA+0 |  |  | 0 | 4 | 1 | 0 | 388.33
48 |  | 25/5 | DA+3 |  |  | 1 | 0 | 0 | 0 | 37.272
49 |  | 25/7 | DA+9 |  | 3 | 4 | 3 | 3 | 3 | 238.517
50 |  | 25/8 | DA+9 |  | 4 | 4 | 4 | 4 | 4 | 0
51 |  | 26/1 | DA+3 |  |  | 0 | 1 | 1 | 0 | 360.189
52 |  | 26/2 | DA+3 |  |  | 0 | 2 | 3 | 0 | 417.632
53 |  | 26/3 | DA+0 |  |  | 0 | 0 | 0 | 0 | 235.859
54 |  | 26/4 | DA+9 |  |  | 3 | 2 | 0 | 0 | 293.157
55 |  | 26/5 | DA+9 |  |  | 2 | 0 | 0 | 2 | 139.673
56 |  | 26/6 | DA+0 |  |  | 2 | 0 | 0 | 1 | 124.417
57 |  | 26/7 | DA+3 |  |  | 1 | 0 | 0 | 3 | 265.2
58 |  | 27/0 | DC2+9
59 |  | 27/1 | DB1+9 |  | 3 | 3 | 3 | 4 | 5 | 178.762
60 |  | 27/3 | DA+0 |  |  | 0 | 2 | 1 | 0 | 112.974
61 |  | 27/4 | DA+0 |  |  | 0 | 1 | 0 | 0 | 210.484
62 |  | 28/2 | DA+6 |  |  | 3 | 0 | 0 | 1 | 385.474
63 |  | 28/3 | DA+3 |  |  | 0 | 4 | 2 | 0 | 311.35
64 |  | 28/4 | DA+9 |  |  | 1 | 2 | 0 | 0 | 293.3
65 |  | 28/5 | DA+9 | 1.5 |  | 2 | 5 | 1 | 6 | 218.617
66 |  | 28/6 | DA+9 |  |  | 1 | 6 | 1 | 6 | 230.05
67 |  | 28/7 | DA+0 | 1.5 |  | 3 | 0 | 1 | 4 | 220.61
68 |  | 28/8 | DA+3 |  |  | 0 | 1 | 5 | 0 | 453.087
69 |  | 28/9 | DA+0 |  |  | 1 | 0 | 0 | 0 | 146.587
70 |  | 29/01 | DA+06 |  |  | 1 | 0 | 0 | 1 | 253.932
71 |  | 29/02 | DA+09 |  |  | 0 | 0 | 1 | 0 | 155.856
72 |  | 29/03 | DA+06 |  |  | 0 | 0 | 0 | 0 | 185.571
73 |  | 29/04 | DA+03 |  |  | 0 | 0 | 0 | 0 | 55.903
74 |  | 29/05 | DA+00 |  |  | 0 | 0 | 0 | 1 | 159.981
75 |  | 29/06 | DA+06 |  |  | 1 | 0 | 0 | 0 | 234.032
76 |  | 29/07 | DA+03 |  |  | 0 | 0 | 0 | 0 | 125.586
77 |  | 29/09 | DA+0 |  |  | 2 | 2 | 0 | 0 | 351.09
78 |  | 29/10 | DA+06 |  |  | 0 | 2 | 0 | 0 | 455.37
79 |  | 30/00 | DC2+00 | [6 empty] | 0
80 |  | 30/01 | DA+03 |  |  | 1 | 1 | 0 | 0 | 343.4
81 |  | 30/02 | DA+00 |  |  | 0 | 0 | 0 | 0 | 42.27
82 |  | 31/00 | DD45+3
83 |  | 31/01 | DA+09 |  | 3 | 3 | 3 | 3 | 3 | 0
84 |  | 31/02 | DA+00 |  |  | 1 | 2 | 1 | 0 | 289.42
85 |  | 31/04 | DA+03 |  |  | 0 | 0 | 0 | 1 | 67.71
86 |  | 32/00 | DB2+6
87 |  | 32/02 | DA+00 |  |  | 1 | 0 | 0 | 0 | 411.95
88 |  | 32/03 | DA+03 |  |  | 0 | 2 | 0 | 0 | 99.076
89 |  | 32/04
90 |  | 32/08 | DA+09 |  |  | 0 | 0 | 0 | 0 | 98.23
91 | Y | 33/0 | DB2+3 |  |  | 2 | 0 | 0 | 4 | 381.6 |  | 222.533 |  | 2023-12-29
92 |  | 33/1 | DA+0 |  |  | 0 | 0 | 0 | 0 | 352.48 |  | 200.16 |  |  | JMC-1 | 13.03.24
93 | Y | 33/2 | DA+0 |  |  | 1 | 1 | 0 | 0 | 492.78 |  | 226.416
94 | Y | 33/3 | DA+0 |  |  | 2 | 0 | 0 | 2 | 151.2 |  | 77.104
95 | Y | 33/4 | DA+0 | -0.4 |  | 1 | 4 | 0 | 0 | 243.1 |  | 88.432
96 | Y | 33/6 | DA+6 |  |  | 0 | 0 | 4 | 4 | 214.88 |  | 156.032
97 | Y | 33/7 | DA+9 |  |  | 3 | 1 | 0 | 0 | 645.745 |  | 359.696
98 | Y | 33/8 | DA+3 |  |  | 1 | 0 | 1 | 3 | 265.799 |  | 78.225
99 | Y | 34/0 | DB1+6 |  |  | 0 | 0 | 2 | 1 | 564.394 |  | 359.682 |  | 2023-12-29
100 | Y | 34/1 | DA+3 | 0.3 |  | 2 | 0 | 2 | 3 | 256.233 |  | 50.319
101 | Y | 34/2 | DA+9 |  |  | 0 | 0 | 0 | 1 | 32.451 |  | 5.505
102 | Y | 34/3 | DA+9 | 1 |  | 0 | 0 | 3 | 6 | 1134.87 |  | 452.318
103 | Y | 34/4 | DA+6 |  |  | 1 | 3 | 1 | 0 | 313.904 |  | 87.476
104 |  | 34/5 | DCT+0 | -0.5 |  | 0 | 0 | 0 | 0 | 361.8
105 | Y | 34/6 | DA+6 |  |  | 1 | 0 | 0 | 1 | 220.4 |  | 71.358
106 | Y | 35/0 | DB2+0 |  |  | 1 | 3 | 1 | 0 | 467.993 |  | 256.377 |  | 2023-12-29
107 | Y | 35/1 | DA+0 |  |  | 0 | 3 | 0 | 0 | 69.549 |  | 21.863
108 | Y | 35/2 | DA+0 |  |  | 1 | 3 | 0 | 0 | 44.623 |  | 5.323
109 | Y | 35/3 | DA+0 |  |  | 2 | 0 | 0 | 4 | 419.263 |  | 157.798
110 | Y | 35/4 | DA+3 |  |  | 0 | 3 | 2 | 0 | 116.817 |  | 36.068
111 | Y | 35/5 | DA+0 | 0.4 |  | 0 | 3 | 1 | 0 | 703.989 |  | 299.892
112 | Y | 35/6 | DA+9 |  |  | 0 | 2 | 0 | 0 | 401.023 |  | 155.645
113 | Y | 35/7 | DA+3 |  |  | 1 | 0 | 0 | 3 | 368.217 |  | 241.532
114 | Y | 35/8 | DA+0 |  |  | 1 | 3 | 0 | 0 | 39.017 |  | 9.15
115 | Y | 35/9 | DA+0 |  |  | 0 | 2 | 0 | 0 | 147.994 |  | 64.4
116 | Y | 36/0 | DD60+18 |  |  | 2 | 0 | 0 | 0 | 162.61 |  | 84.936
117 | Y | 37/0 | DD60+18 |  | 3 | 3 | 3 | 3 | 3 | 1384.198 |  | 1254.084
118 | Y | 37/1 | DA+9 |  | 2 | 4 | 6 | 2 | 2 | 612.6 |  | 400.141
119 |  | 37/2 | DB1+6 |  |  | 0 | 0 | 0 | 0 | 105.717 |  | 98.297 |  |  | JMC-59 | 29-07-24
120 |  | 37/3 | DA+0 |  |  | 0 | 0 | 0 | 0 | 62.64 |  | 28.816 |  |  | JMC-60 | 29-07-24
121 | Y | 37/4 | DA+6 |  |  | 2 | 0 | 0 | 3 | 327.85 |  | 144.213 |  |  | JMC-61 | 29-07-24
122 | Y | 37/5 | DA+3 |  |  | 1 | 0 | 0 | 3 | 163.167 |  | 62.312
123 | Y | 37/6 | DA+6 |  |  | 1 | 0 | 0 | 0 | 284.595 |  | 143.717
124 | Y | 37/7 | DA+3 |  |  | 1 | 1 | 0 | 0 | 360.916 |  | 181.161
125 |  | 37/8 | DA+0 |  |  | 0 | 0 | 0 | 0 | 61.657 |  | 13.36
126 | Y | 38/0 | DC1+0 |  |  | 0 | 2 | 0 | 0 | 547.123 |  | 509.174 |  | 2023-12-29
127 | Y | 38/1 | DA+3 |  |  | 0 | 2 | 0 | 0 | 539.139 |  | 361.314 |  |  | JMC-26 | 29-07-24
128 | Y | 38/3 | DA+9 |  |  | 2 | 0 | 0 | 1 | 297.4957 |  | 152.854 |  |  | JMC-27 | 29-07-24
129 | Y | 38/4 | DA+0 |  |  | 1 | 1 | 0 | 2 | 191.745 |  | 48.406
130 | Y | 38/5 | DA+0 |  |  | 2 | 0 | 1 | 2 | 295.659 |  | 71.81
131 | Y | 38/6 | DA+0 |  |  | 0 | 0 | 0 | 1 | 205.829 |  | 79.449 |  |  | JMC-28 | 29-07-24
132 | Y | 38/7 | DA+0 |  |  | 1 | 0 | 0 | 1 | 100.0663 |  | 42.547
133 | Y | 38/8 | DA+0 |  |  | 0 | 1 | 0 | 1 | 159.4651 |  | 51.758 |  |  | JMC-29 | 29-07-24
134 | Y | 38/9 | DB1+6 |  |  | 0 | 0 | 2 | 2 | 411.929 |  | 272.86
135 | Y | 39/0 | DC2+3 |  |  | 2 | 0 | 0 | 2 | 428.739 |  | 280.711 |  | 2023-12-29
136 | Y | 39/1 | DA+6 |  |  | 1 | 2 | 0 | 0 | 427.017 |  | 264.925 |  |  | JMC-30 | 29-07-24
137 | Y | 39/2 | DA+0 |  |  | 0 | 3 | 0 | 0 | 315.583 |  | 127.368
138 | Y | 39/3 | DA+3 |  |  | 1 | 0 | 0 | 1 | 258.267 |  | 154.272 |  |  | JMC-31 | 29-07-24
139 | Y | 39/4 | DA+0 |  |  | 2 | 3 | 0 | 0 | 446.297 |  | 139.368
140 | Y | 39/5 | DA+3 | -1 |  | 0 | 4 | 0 | 3 | 160.354 |  | 34.435
141 | Y | 39/6 | DA+0 |  |  | 0 | 3 | 0 | 3 | 385.92 |  | 46.854
142 | Y | 39/7 | DA+0 |  |  | 0 | 0 | 0 | 3 | 435.806 |  | 187.109
143 | Y | 40/0 | DC2+0 |  |  | 0 | 5 | 2 | 0 | 1250.246 |  | 997.507 |  | 2023-12-29
144 | Y | 40/1 | DA+0 |  |  | 2 | 4 | 0 | 0 | 401.527 |  | 104.013
145 | Y | 40/2 | DB1+9 |  |  | 0 | 2 | 1 | 0 | 501.187 |  | 408.528
146 | Y | 40/3 | DA+3 |  |  | 0 | 1 | 1 | 0 | 236.907 |  | 113.002 |  |  | JMC-32 | 29-07-24
147 | Y | 40/4 | DA+9 |  |  | 0 | 0 | 0 | 1 | 521.072 |  | 489.056 |  |  | JMC-33 | 29-07-24
148 |  | 40/5 | DB1+9 |  |  | 0 | 0 | 0 | 0 | 354.1 |  | 349.912 |  |  | JMC-4 | 22.03.24
149 | Y | 40/6 | DA+3 |  |  | 1 | 0 | 0 | 2 | 154.883 |  | 79.128 |  |  | JMC-34 | 29-07-24
150 | Y | 40/7 | DA+3 |  |  | 1 | 4 | 1 | 4 | 221.71 |  | 37.48
151 | Y | 40/8 | DA+0 |  |  | 0 | 4 | 0 | 0 | 630.783 |  | 331.389
152 | Y | 40/9 | DA+0 |  |  | 0 | 6 | 1 | 2 | 133.683 |  | 21.333
153 | Y | 40/11 | DA+9 |  |  | 1 | 0 | 0 | 0 | 104.4 |  | 58 |  |  | JMC-5 | 22.03.24
154 | Y | 40/12 | DA+0 |  |  | 2 | 0 | 0 | 5 | 599.16 |  | 200.901
155 | Y | 41/0 | DB1+0 |  |  | 0 | 1 | 1 | 0 | 299.222 |  | 165.175 |  | 2023-12-29
156 | Y | 41/1 | DA+3 |  |  | 0 | 0 | 0 | 3 | 338.21 |  | 51.94 |  | 2023-09-12
157 | Y | 41/2 | DA+0 | -0.5 |  | 1 | 0 | 1 | 3 | 290.62 | 38.76 | 67.854 |  | 2023-09-12
158 | Y | 41/3 | DA+0 |  |  | 0 | 0 | 1 | 1 | 41.922 |  | 41.922 |  | 2023-09-12
159 | Y | 41/4 | DA+0 |  |  | 0 | 1 | 0 | 1 | 38.232 |  | 38.232 |  | 2023-09-12 | JMC-35 | 29-07-24
160 | Y | 41/5 | DA+0 |  |  | 0 | 0 | 1 | 1 | 128.736 | 56.312 | 35 |  | 2023-09-12 | JMC-36 | 29-07-24
161 | Y | 41/6 | DA+0 |  |  | 2 | 0 | 0 | 1 | 213.714 |  | 57.698 |  | 2023-09-12 | JMC-37 | 29-07-24
162 | Y | 41/8 | DA+0 |  |  | 0 | 2 | 1 | 0 | 30.774 |  | 30.774 |  | 2023-09-12 | JMC-6 | 22.03.24
163 | Y | 41/9 | DA+0 |  |  | 0 | 2 | 2 | 2 | 168.2 |  | 45.88 |  | 2023-09-12 | JMC-7 | 22.03.24
164 | Y | 41/12 | DA+3 |  |  | 1 | 0 | 0 | 0 | 152.648 | 28.888 | 66.766 |  | 2023-09-12 | JMC-8 | 22.03.24
165 | Y | 42/0 | DC2+9 |  |  | 0 | 0 | 0 | 1 | 442.886 |  | 408.487 |  | 2023-12-29
166 | Y | 43/0 | DB2+9 |  |  | 0 | 3 | 0 | 3 | 254.434 |  | 132.326 |  | 2023-12-29
167 |  | 43/1 | DA+9 |  |  | 0 | 0 | 0 | 0 | 94.646 |  | 34.848 |  | 2023-09-12 | JMC-2 | 13.03.24
168 | Y | 43/2 | DA+9 |  |  | 1 | 0 | 0 | 1 | 266.086 | 72.72 | 146.712 |  | 2023-09-12 | JMC-38 | 29-07-24
169 | Y | 43/3 | DA+3 | 0.21 |  | 1 | 0 | 1 | 2 | 212.394 |  | 89.962 |  | 2023-09-12 | JMC-39 | 29-07-24
170 | Y | 43/6 | DA+6 |  |  | 1 | 1 | 0 | 2 | 128.022 |  | 56.258 |  | 2023-09-12
171 | Y | 44/0 | DB1+0 |  |  | 0 | 1 | 0 | 0 | 46.923 |  | 23.625 |  | 2023-12-29
172 |  | 45/0 | DD60+18
173 |  | 46/0 | DD60+18
174 | Y | 46/1 | DA+6 |  |  | 0 | 1 | 0 | 0 | 161.416 |  | 48.006 |  | 2023-09-12
175 |  | 46/2 | DA+0 | 0.3 |  | 0 | 0 | 0 | 0 | 226.73 |  | 168.6 |  | 2023-09-12 | JMC-3 | 13.03.24
176 |  | 46/3 | DA+0 |  |  | 0 | 0 | 0 | 0 | 113.754 |  | 44.602 |  | 2023-09-12 | JMC-40 | 29-07-24
177 | Y | 46/4 | DA+0 |  |  | 0 | 2 | 0 | 3 | 168.612 |  | 96.296 |  | 2023-09-12 | JMC-41 | 29-07-24
178 | Y | 50/1 | DA+0 |  |  | 2 | 0 | 0 | 0 | 87.804
179 | Y | 51/6 | DA+0 |  |  | 1 | 0 | 0 | 0
180 | Y | 52/3 | DA+0 |  |  | 0 | 3 | 1 | 0 | 866.16 |  |  |  |  | JMC-42 | 29-07-24
181 | Y | 53/1 | DA+0 |  | 1 | 1 | 1 | 1 | 1
182 | Y | 72/6 | DA+0 |  |  | 1 | 1 | 1 | 1
183 | Y | 72/7 | DB1+9 |  |  | 1 | 1 | 1 | 1

## Earthing Pkg -G Ist section (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
FOUNDATION
Sl. No. | Cum S No | Location No. | Tower Type | Classification | Type of Earthing | Earthing | Name of Sub-Contractor
1 | 1 | 32/7 | DA+0 | SANDY | Pipe Type | 07.11.23 | Shakti Construction
2 | 2 | 32/1 | DA+9 | SANDY | Pipe Type | 10.11.23 | Shakti Construction
3 | 3 | 32/5 | DA+6 | SANDY | Pipe Type | 10.11.23 | Shakti Construction
4 | 4 | 30/2 | DA+0 | SANDY | Pipe Type | 18.11.23 | Om Const
5 | 5 | 32/0 | DB2+6 | SANDY | Pipe Type | 28.11.23 | Shakti Construction
6 | 6 | 31/3 | DA+0 | SANDY | Pipe Type | 05.12.23 | Shakti Construction

## Earthing balance (hidden)
S no | PKG- G |  | PKG- F
1 | 72/1 | Mahadev engg. | 50/3 | Kalpana Const.
2 | 71/5 | Mahadev engg. | 73/9 | Shakti Const. -2
3 | 43/2 | Sai Infra | 73/2 | Shree Shyam Const.
4 | 43/3 | Sai Infra | 50/6 | Kalpana Const.
5 | 68/3 | Shakti Const. -2
6 | 73/0 | Mahadev engg. - 2
7 | 68/1 | Shakti Const. -2
8 | 66/3 | Shree Shyam Const.
9 | 69/0 | Bhati Const.-2

## Tack Welding - PKG-G (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Tack Welding
Cum Sl. No. | Month Sl. No. | JMC No. | Location No. | Tower Type | Dt. of Start | Dt. of Complete | Tack Welding Status | Name of Sub-Contractor | Ramarks
2023-10-01
1 | 1 |  | 57/12 | DA+3 | 24.10.23 | 25.10.23 | Done | Suraja Ram
2 | 2 |  | 57/13 | DA+0 | 24.10.23 | 25.10.23 | Done | Suraja Ram
3 | 3 |  | 57/11 | DA+0 | 25.10.23 | 26.10.23 | Done | Suraja Ram
4 | 4 |  | 57/10 | DA+3 | 26.10.23 | 27.10.23 | Done | Suraja Ram
5 | 5 |  | 57/9 | DA+0 | 27.10.23 | 29.10.23 | Done | Suraja Ram
2023-11-01
6 | 1 |  | 57/4 | DA+0 | 31.10.23 | 01.11.23 | Done | Suraja Ram
7 | 2 |  | 57/3 | DA+0 | 01.11.23 | 02.11.23 | Done | Suraja Ram
8 | 3 |  | 57/2 | DA+0 | 02.11.23 | 03.11.2023 | Done | Suraja Ram
9 | 4 |  | 57/5 | DA+3 | 03.11.2023 | 04.11.2023 | Done | Suraja Ram
10 | 5 |  | 58/8 | DA+0 | 05.11.2023 | 06.111.23 | Done | Suraja Ram
11 | 6 |  | 58/9 | DA+0 | 06.111.23 | 07.11.23 | Done | Suraja Ram
12 | 7 |  | 57/8 | DA+3 | 07.11.23 | 08.11.23 | Done | Suraja Ram
13 | 8 |  | 58/11 | DA+3 | 09.11.23 | 27.11.23 | Done | Suraja Ram
14 | 9 |  | 58/12 | DA+0 | 27.11.23 | 28.11.23 | Done | Suraja Ram
15 | 10 |  | 57/1 | DA+3 | 28.11.23 | 30.11.23 | Done | Suraja Ram
2023-12-01
16 | 1 |  | 56/9 | DA+3 | 30.11.23 | 02.12.23 | Done | Suraja Ram
17 | 2 |  | 56/8 | DA+3 | 02.12.23 | 03.12.23 | Done | Suraja Ram
18 | 3 |  | 56/7 | DA+3 | 06.12.23 | 06.12.23 | Done | Suraja Ram
19 | 4 |  | 58/14 | DA+0 | 07.12.23 | 07.12.23 | Done | Suraja Ram
20 | 5 |  | 58/16 | DA+0 | 13.12.23 | 13.12.23 | Done | Suraja Ram
21 | 6 |  | 58/10 | DA+3 | 14.12.23 | 15.12.23 | Done | Suraja Ram
22 | 7 |  | 59/1 | DA+0 | 18.12.23 | 18.12.23 | Done | Suraja Ram
23 | 8 |  | 59/2 | DA+0 | 19.12.23 | 19.12.23 | Done | Suraja Ram
24 | 9 |  | 59/3 | DA+0 | 20.12.23 | 20.12.23 | Done | Suraja Ram
25 | 10 |  | 59/5 | DA+0 | 21.12.23 | 21.12.23 | Done | Suraja Ram
26 | 11 |  | 59/6 | DA+0 | 22.12.23 | 22.12.23 | Done | Suraja Ram
27 | 12 |  | 56/3 | DA+0 | 23.12.23 | 23.12.23 | Done | Suraja Ram
28 | 13 |  | 56/4 | DA+3 | 24.12.23 | 24.12.23 | Done | Suraja Ram
29 | 14 |  | 55/4 | DA+3 | 25.12.23 | 25.12.23 | Done | Suraja Ram
30 | 15 |  | 55/5 | DA+0 | 26.12.23 | 26.12.23 | Done | Suraja Ram
31 | 16 |  | 51/5 | DA+0 | 21.12.23 | 26.12.23 | Done | Kailash Nath
32 | 17 |  | 51/4 | DA+3 | 21.12.23 | 26.12.23 | Done | Kailash Nath
33 | 18 |  | 51/3 | DA+0 | 26.12.23 | 27.12.23 | Done | Kailash Nath
34 | 19 |  | 51/2 | DA+0 | 27.12.23 | 28.12.23 | Done | Kailash Nath
35 | 20 |  | 55/6 | DA+3 | 29.12.23 | 29.12.23 | Done | Suraja Ram
36 | 21 |  | 51/7 | DA+3 | 29.12.23 | 29.12.23 | Done | Kailash Nath
37 | 22 |  | 51/10 | DA+3 | 29.12.23 | 30.12.23 | Done | Kailash Nath
38 | 23 |  | 52/1 | DA+0 | 30.12.23 | 30.12.23 | Done | Kailash Nath
39 | 24 |  | 55/7 | DA+0 | 30.12.23 | 30.12.23 | Done | Suraja Ram
40 | 25 |  | 55/9 | DA+3 | 31.12.23 | 31.12.23 | Done | Suraja Ram
41 | 26 |  | 52/2 | DA+3 | 31.12.23 | 31.12.23 | Done | Kailash Nath
2024-01-01
42 | 1 |  | 55/10 | DA+3 | 02.01.24 | 02.01.24 | Done | Suraja Ram
43 | 2 |  | 55/11 | DA+3 | 02.01.24 | 02.01.24 | Done | Suraja Ram
44 | 3 |  | 52/5 | DA+3 | 02.01.24 | 02.01.24 | Done | Kailash Nath
45 | 4 |  | 57/7 | DA+3 | 03.01.24 | 03.01.24 | Done | Suraja Ram
46 | 5 |  | 58/5 | DA+3 | 04.01.24 | 05.01.24 | Done | Suraja Ram
47 | 6 |  | 57/6 | DB1+0 | 06.01.24 | 06.01.24 | Done | Suraja Ram
48 | 7 |  | 57/0 | DB2+0 | 07.01.24 | 07.01.24 | Done | Suraja Ram
49 | 8 |  | 56/6 | DA+3 | 08.01.24 | 08.01.24 | Done | Suraja Ram
50 | 9 |  | 56/2 | DA+3 | 11.01.24 | 12.01.24 | Done | Suraja Ram
51 | 10 |  | 56/5 | DA+0 | 13.01.24 | 13.01.24 | Done | Suraja Ram
52 | 11 |  | 56/0 | DB1+0 | 13.01.24 | 13.01.24 | Done | Suraja Ram
53 | 12 |  | 55/8 | DA+3 | 14.1.24 | 14.1.24 | Done | Suraja Ram
54 | 13 |  | 58/1 | DA+0 | 16.01.2024 | 16.01.2024 | Done | Suraja Ram
55 | 14 |  | 58/4 | DA+0 | 17.01.2024 | 17.01.2024 | Done | Suraja Ram
56 | 15 |  | 58/6 | DA+3 | 19.01.24 | 19.01.24 | Done | Suraja Ram
57 | 16 |  | 50/4 | DA+3 | 22.01.24 | 22.01.24 | Done | Ramagora
58 | 17 |  | 50/3 | DA+0 | 24.01.24 | 24.01.24 | Done | Ramagora
59 | 18 |  | 44/4 | DA+0 | 25.01.24 | 25.01.24 | Done | Ramagora
60 | 19 |  | 58/3 | DA+3 | 27.01.24 | 27.01.24 | Done | Suraja Ram
61 | 20 |  | 44/2 | DA+0 | 27.01.24 | 27.01.24 | Done | Ramagora
62 | 21 |  | 41/10 | DA+0 | 28.01.24 | 28.01.24 | Done | Ramagora
63 | 22 |  | 41/11 | DA+3 | 29.01.24 | 29.01.24 | Done | Ramagora
64 | 23 |  | 58/7 | DB+0 | 29.01.24 | 29.01.24 | Done | Suraja Ram
65 | 24 |  | 41/7 | DA+3 | 30.01.24 | 30.01.24 | Done | Ramagora
66 | 25 |  | 58/15 | DA+3 | 30.01.24 | 30.01.24 | Done | Suraja Ram
67 | 26 |  | 47/2 | DA+0 | 31.01.24 | 31.01.24 | Done | Ramagora
Feb-24
68 | 1 |  | 59/0 | DB+0 | 01.02.24 | 01.02.24 | Done | Suraja Ram
69 | 2 |  | 46/3 | DA+0 | 01.02.24 | 01.02.24 | Done | Ramagora
70 | 3 |  | 61/1 | DA+0 | 02.02.24 | 02.02.24 | Done | Suraja Ram
71 | 4 |  | 48/1 | DA+0 | 03.02.24 | 03.02.24 | Done | Ramagora
72 | 5 |  | 51/9 | DA+3 | 04.02.24 | 04.02.24 | Done | Ramagora
73 | 6 |  | 55/1 | DA+3 | 04.02.24 | 04.02.24 | Done | Suraja Ram
74 | 7 |  | 55/2 | DA+3 | 04.02.24 | 05.02.24 | Done | Suraja Ram
75 | 8 |  | 52/4 | DA+0 | 04.02.24 | 05.02.24 | Done | Ramagora
76 | 9 |  | 55/3 | DA+0 | 06.02.24 | 06.02.24 | Done | Suraja Ram
77 | 10 |  | 53/4 | DA+3 | 07..02.24 | 07..02.24 | Done | Suraja Ram
78 | 11 |  | 51/8 | DA+3 | 07..02.24 | 07..02.24 | Done | Ramagora
79 | 12 |  | 53/3 | DA+3 | 08.02.24 | 08.02.24 | Done | Suraja Ram
80 | 13 |  | 51/6 | DA+0 | 09.02.24 | 09.02.24 | Done | Ramagora
81 | 14 |  | 43/1 | DA+9 | 10.02.24 | 10.02.24 | Done | Ramagora
82 | 15 |  | 48/2 | DA+3 | 12.02.24 | 12.02.24 | Done | Suraja Ram
83 | 16 |  | 41/5 | DA+0 | 14.02.24 | 14.02.24 | Done | Ramagora
84 | 17 |  | 47/0 | DB+0 | 16.02.24 | 16.02.24 | Done | Suraja Ram |  | 23
85 | 18 |  | 46/2 | DA+0 | 17.02.24 | 17.02.24 | Done | Suraja Ram |  | 16
86 | 19 |  | 53/1 | DA+0 | 23.02.24 | 23.02.24 | Done | Suraja Ram |  | 7
87 | 20 |  | 52/0 | DB+0 | 24.02.24 | 24.02.24 | Done | Suraja Ram
88 | 21 |  | 44/3 | DA+3 | 27.02.24 | 27.02.24 | Done | Ramagora
89 | 22 |  | 43/5 | DA+0 | 28.02.24 | 28.02.24 | Done | Ramagora
90 | 23 |  | 41/9 | DA+0 | 29.02.24 | 29.02.24 | Done | Ramagora
March'24
91 | 1 |  | 41/8 | DA+0 | 04.03.24 | 04.03.24 | Done | Ramagora
92 | 2 |  | 41/4 | DA+0 | 05.03.24 | 05.03.24 | Done | Ramagora
93 | 3 |  | 41/6 | DA+0 | 07.03.24 | 07.03.24 | Done | Ramagora
94 | 4 |  | 53/2 | DA+3 | 08.03.24 | 08.03.24 | Done | Suraja Ram
95 | 5 |  | 43/4 | DA+9 | 09.03.24 | 09.03.24 | Done | Ramagora
96 | 6 |  | 51/1 | DA+0 | 11.03.24 | 11.03.24 | Done | Ramagora
97 | 7 |  | 51/0 | DB+0 | 28.03.24 | 28.03.24 | Done | Ramagora |  | Sanjay
| April'24 | [8 empty] | Manoj
98 | 1 |  | 47/3 | DA+0 | 20.04.24 | 21.04.24 | Done | Ramagora
99 | 2 |  | 56/1 | DA+3 | 24.04.24 | 24.04.24 | Done | Ramagora |  | publesh
| May'24 | [8 empty] | Pradeep
100 | 1 |  | 58/0 | DC2+0 | 04.05.24 | 04.05.24 | Done | Suraja Ram
101 | 2 |  | 61/2 | DA+0 | 06.05.24 | 06.05.24 | Done | Suraja Ram
102 | 3 |  | 44/1 | DA+0 | 12.05.24 | 12.05.24 | Done | Ramagora
103 | 4 |  | 55/0 | DC+0 | 24.05.24 | 24.05.24 | Done | Suraja Ram
104 | 5 |  | 65/5 | DA+0 | 30.05.24 | 30.05.24 | Done | Suraja Ram
105 | 6 |  | 65/4 | DA+0 | 31.05.24 | 31.05.24 | Done | Suraja Ram
June'24
106 | 1 |  | 58/2 | DA+0 | 02.06.24 | 02.06.24 | Done | Suraja Ram
107 | 2 |  | 65/3 | DA+0 | 02.06.24 | 02.06.24 | Done | Suraja Ram
108 | 3 |  | 53/0 | DC2+3 | 22.06.24 | 22.06.24 | Done | Suraja Ram
109 | 4 |  | 52/3 | DA+0 | 24.06.24 | 24.06.24 | Done | Suraja Ram
July'24
110 | 1 |  | 48/0 | DB+0 | 23.07.24 | 23.07.24 | Done | Suraja Ram
Sept'24
111 | 1 |  | 46/4 | DA+0 | 16.09.24 | 16.09.24 | Done | Suraja Ram
112 | 2 |  | 47/1 | DA+0 | 19.09.24 | 19.09.24 | Done | Suraja Ram
113 | 3 |  | 50/2 | DA+0 | 20.09.24 | 20.09.24 | Done | Suraja Ram
114 | 4 |  | 50/1 | DA+0 | 22.09.24 | 22.09.24 | Done | Suraja Ram
115 | 5 |  | 72/4 | DA+0 | 26.09.24 | 26.09.24 | Done | Suraja Ram
116 | 6 |  | 72/5 | DA+0 | 26.09.24 | 26.09.24 | Done | Suraja Ram
117 | 7 |  | 72/3 | DA+0 | 29.09.24 | 29.09.24 | Done | Suraja Ram
118 | 8 |  | 72/6 | DA+0 | 29.09.24 | 29.09.24 | Done | Suraja Ram
119 | 9 |  | 71/5 | DA+0 | 29.09.24 | 29.09.24 | Done | Suraja Ram
Oct'24
120 | 1 |  | 72/0 | DB1+0 | 04.10.24 | 04.10.24 | Done | Suraja Ram
121 | 2 |  | 50/0 | DC2+3 | 04.10.24 | 05.10.24 | Done | Suraja Ram
122 | 3 |  | 71/4 | DA+0 | 13.10.24 | 13.10.24 | Done | Suraja Ram
123 | 4 |  | 72/2 | DA+0 | 14.10.24 | 14.10.24 | Done | Suraja Ram
124 | 5 |  | 71/2 | DA+0 | 15.10.24 | 15.10.24 | Done | Suraja Ram
125 | 6 |  | 71/1 | DA+0 | 16.10.24 | 16.10.24 | Done | Suraja Ram
126 | 7 |  | 68/1 | DA+3 | 19.10.24 | 19.10.24 | Done | Suraja Ram
127 | 8 |  | 72/1 | DA+0 | 19.10.24 | 19.10.24 | Done | Suraja Ram
Nov'24
128 | 1 |  | 69/6 | DA+0 | 04.11.24 | 04.11.24 | Done | Suraja Ram
129 | 2 |  | 72/7 | DB1+9 | 09.11.24 | 09.11.24 | Done | Suraja Ram
130 | 3 |  | 68/6 | DA+3 | 14.11.24 | 14.11.24 | Done | Suraja Ram
131 | 4 |  | 71/3 | DA+0 | 14.11.24 | 14.11.24 | Done | Suraja Ram
132 | 5 |  | 68/3 | DA+0 | 14.11.24 | 14.11.24 | Done | Suraja Ram
133 | 6 |  | 66/2 | DA+0 | 14.11.24 | 14.11.24 | Done | Suraja Ram
134 | 7 |  | 73/0 | DD45+9 | 17.11.24 | 17.11.24 | Done | Suraja Ram
135 | 8 |  | 68/4 | DA+3 | 20.11.24 | 20.11.24 | Done | Suraja Ram
136 | 9 |  | 68/2 | DA+3 | 20.11.24 | 20.11.24 | Done | Suraja Ram
137 | 10 |  | 68/5 | DA+3 | 20.11.24 | 20.11.24 | Done | Suraja Ram
138 | 11 |  | 69/7 | DA+0 | 22.11.24 | 22.11.24 | Done | Suraja Ram
Dec'24
139 | 1 |  | 69/5 | DA+0 | 08.12.24 | 08.12.24 | Done | Suraja Ram
140 | 2 |  | 69/1 | DA+0 | 10.12.24 | 10.12.24 | Done | Suraja Ram
141 | 3 |  | 69/2 | DA+0 | 11.12.24 | 11.12.24 | Done | Suraja Ram
142 | 4 |  | 66/4 | DA+3 | 12.12.24 | 12.12.24 | Done | Suraja Ram
143 | 5 |  | 66/1 | DA+3 | 15.12.24 | 15.12.24 | Done | Suraja Ram
144 | 6 |  | 68/0 | DD45+0 | 16.12.24 | 16.12.24 | Done | Suraja Ram
145 | 7 |  | 67/1 | DB1+9 | 20.12.24 | 20.12.24 | Done | Suraja Ram
146 | 8 |  | 43/3 | DA+3 | 21.12.24 | 21.12.24 | Done | Suraja Ram
147 | 9 |  | 69/0 | DB1+0 | 22.12.24 | 22.12.24 | Done | Suraja Ram
148 | 10 |  | 58/13 | DA+0 | 26.12.24 | 26.12.24 | Done | Suraja Ram
149 | 11 |  | 69/3 | DA+0 | 26.12.24 | 26.12.24 | Done | Suraja Ram
150 | 12 |  | 69/4 |  | 27.12.24 | 27.12.24 | Done | Suraja Ram
151 | 14 |  | 38/1 | DA+3 | 29.12.24 | 29.12.24 | Done | Suraja Ram
152 | 15 |  | 38/2 | DA+6 | 30.12.24 | 30.12.24 | Done | Suraja Ram
153 | 16 |  | 69/8 | DA+0 | 31.12.24 | 31.12.24 | Done | Suraja Ram
154 | 17 |  | 69/9 | DA+0 | 31.12.24 | 31.12.24 | Done | Suraja Ram
Jan'25
155 | 1 |  | 37/3 | DA+0 | 02.01.25 | 02.01.25 | Done | Suraja Ram
156 | 2 |  | 38/3 | DA+9 | 04.01.25 | 04.01.25 | Done | Suraja Ram
157 | 3 |  | 37/4 | DA+6 | 09.01.25 | 09.01.25 | Done | Suraja Ram
158 | 4 |  | 67/0 | DD45+0 | 15.01.25 | 15.01.25 | Done | Suraja Ram
159 | 5 |  | 59/4 | DA+0 | 16.01.25 | 16.01.25 | Done | Suraja Ram
160 | 6 |  | 41/2 | DA+0 | 18.01.25 | 18.01.25 | Done | Suraja Ram
161 | 7 |  | 71/0 | DD60+0 | 12.01.25 | 12.01.25 | Done | Suraja Ram
162 | 8 |  | 37/2 | DB1+6 | 20.01.25 | 20.01.25 | Done | Suraja Ram
163 | 9 |  | 70/0 | DD60+0 | 24.01.25 | 24.01.25 | Done | Suraja Ram
Feb'25
164 | 1 |  | 41/12 | DA+3 | 01.02.25 | 01.02.25 | Done | Suraja Ram
165 | 2 |  | 41/3 | DA+0 | 01.02.25 | 01.02.25 | Done | Suraja Ram
166 | 3 |  | 37/5 | DA+3 | 02.02.25 | 02.02.25 | Done | Suraja Ram
167 | 4 |  | 37/6 | DA+6 | 03.02.25 | 04.02.25 | Done | Suraja Ram
168 | 5 |  | 37/7 | DA+3 | 04.02.25 | 04.02.25 | Done | Suraja Ram
169 | 6 |  | 37/8 | DA+0 | 06.02.25 | 06.02.25 | Done | Suraja Ram
170 | 7 |  | 41/1 | DA+3 | 07.02.25 | 07.02.25 | Done | Suraja Ram
171 | 8 |  | 42/0 | DC2+9 | 08.02.25 | 08.02.25 | Done | Suraja Ram
172 | 9 |  | 65/6 | DA+0 | 20.02.25 | 20.02.25 | Done | Suraja Ram
173 | 10 |  | 65/7 | DA+0 | 21.02.25 | 21.02.25 | Done | Suraja Ram
174 | 11 |  | 40/11 | DA+3 | 24.02.25 | 24.02.25 | Done | Suraja Ram
175 | 12 |  | 40/10 | DA+3 | 24.02.25 | 24.02.25 | Done | Suraja Ram
176 | 13 |  | 40/2 |  | 26.02.25 | 26.02.25 | Done | Suraja Ram
177 | 14 |  | 41/0 |  | 27.02.25 | 27.02.25 | Done | Suraja Ram
Mar'25
178 | 1 |  | 40/12 |  | 03.03.25 | 03.03.25 | Done | Suraja Ram
179 | 2 |  | 38/0 |  | 06.03.25 | 06.03.25 | Done | Suraja Ram
180 | 3 |  | 40/6 |  | 07.03.25 | 07.03.25 | Done | Suraja Ram
181 | 4 |  | 40/7 |  | 08.03.25 | 08.03.25 | Done | Suraja Ram
182 | 5 |  | 60/0 |  | 13.03.25 | 13.03.25 | Done | Suraja Ram
183 | 6 |  | 39/0 |  | 18.03.25 | 18.03.25 | Done | Suraja Ram
184 | 7 |  | 40/0 |  | 19.03.25 | 19.03.25 | Done | Suraja Ram
185 | 8 |  | 40/1 |  | 20.03.25 | 20.03.25 | Done | Suraja Ram
186 | 9 |  | 38/8 |  | 22.03.25 | 22.03.25 | Done | Suraja Ram
187 | 10 |  | 38/9 |  | 23.03.25 | 23.03.25 | Done | Suraja Ram
188 | 11 |  | 38/7 |  | 24.03.35 | 24.03.35 | Done | Suraja Ram

## Tack Welding - PKG-F (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Tack Welding
Cum Sl. No. | Month Sl. No. | JMC No. | Location No. | Tower Type | Depth of Fdn | Dt. of Start | Dt. of Complete | Tack Welding Status | Name of Sub-Contractor | Ramarks
Feb-24
1 | 1 |  | 59/13 | DA+3 |  | 20.02.24 | 20.02.24 | Done | Suraja Ram
2 | 2 |  | 59/14 | DA+6 |  | 22.02.24 | 22.02.24 | Done | Suraja Ram
3 | 3 |  | 62/5 | DA+0 |  | 27.02.24 | 27.02.24 | Done | Suraja Ram
4 | 4 |  | 63/6 | DA+3 |  | 28.02.24 | 28.02.24 | Done | Suraja Ram
March'24
5 | 1 |  | 63/8 | DA+3 |  | 01.03.24 | 02.03.24 | Done | Suraja Ram
6 | 2 |  | 62/3 | DA+0 |  | 03.02.24 | 03.02.24 | Done | Suraja Ram
7 | 3 |  | 62/4 | DA+3 |  | 04.03.24 | 04.03.24 | Done | Suraja Ram
8 | 4 |  | 59/12 | DA+6 |  | 05.03.24 | 05.03.24 | Done | Suraja Ram
9 | 5 |  | 59/10 | DA+0 |  | 06.03.24 | 06.03.24 | Done | Suraja Ram
10 | 6 |  | 59/9 | DA+3 |  | 07.03.24 | 07.03.24 | Done | Suraja Ram
11 | 7 |  | 60/7 | DA+3 |  | 09.03.24 | 09.03.24 | Done | Suraja Ram
12 | 8 |  | 62/2 | DA+3 |  | 10.03.24 | 10.03.24 | Done | Suraja Ram
13 | 9 |  | 62/7 | DA+3 |  | 11.03.24 | 11.03.24 | Done | Suraja Ram
14 | 10 |  | 64/1 | DA+0 |  | 12.03.24 | 12.03.24 | Done | Suraja Ram
15 | 11 |  | 59/7 | DA+3 |  | 12.03.24 | 12.03.24 | Done | Ramagora
16 | 12 |  | 64/4 | DA+3 |  | 13.03.24 | 13.03.24 | Done | Suraja Ram
17 | 13 |  | 60/11 | DA+3 |  | 15.03.24 | 15.03.24 | Done | Ramagora
18 | 14 |  | 62/8 | DA+0 |  | 15.03.24 | 15.03.24 | Done | Suraja Ram
19 | 15 |  | 65/2 | DA+0 |  | 16.03.24 | 16.03.24 | Done | Suraja Ram
20 | 16 |  | 60/6 | DA+0 |  | 16.03.24 | 16.03.24 | Done | Ramagora
21 | 17 |  | 65/4 | DA+0 |  | 17.03.24 | 17.03.24 | Done | Suraja Ram
22 | 18 |  | 64/5 | DA+3 |  | 18.03.24 | 18.03.24 | Done | Suraja Ram
23 | 19 |  | 62/9 | DA+3 |  | 19.03.24 | 19.03.24 | Done | Suraja Ram
24 | 20 |  | 60/8 | DA+0 |  | 19.03.24 | 19.03.24 | Done | Ramagora
25 | 21 |  | 62/10 | DA+0 |  | 21.03.24 | 21.03.24 | Done | Suraja Ram
26 | 22 |  | 65/3 | DA+0 |  | 22.03.24 | 22.03.24 | Done | Suraja Ram
27 | 23 |  | 59/6 | DA+3 |  | 22.03.24 | 22.03.24 | Done | Ramagora
28 | 24 |  | 60/10 | DA+0 |  | 24.03.24 | 24.03.24 | Done | Suraja Ram
29 | 25 |  | 61/6 | DA+3 |  | 28.03.24 | 28.03.24 | Done | Suraja Ram
30 | 26 |  | 65/5 | DA+0 |  | 29.03.24 | 29.03.24 | Done | Suraja Ram
Apr'24
31 | 1 |  | 64/6 | DA+0 |  | 01.04.24 | 01.04.24 | Done | Suraja Ram
32 | 2 |  | 61/7 | DA+9 |  | 03.04.24 | 03.04.24 | Done | Suraja Ram
33 | 3 |  | 65/6 | DA+0 |  | 04.04.24 | 04.04.24 | Done | Suraja Ram
34 | 4 |  | 64/7 | DA+3 |  | 06.04.24 | 06.04.24 | Done | Suraja Ram
35 | 5 |  | 63/7 | DA+3 |  | 21.04.24 | 22.04.24 | Done | Suraja Ram
36 | 6 |  | 64/9 | DA+3 |  | 24.04.24 | 24.04.24 | Done | Suraja Ram
37 | 7 |  | 61/0 | DB+0 |  | 25.04.24 | 25.04.24 | Done | Ramagora
38 | 8 |  | 65/9 | DA+0 |  | 27.04.24 | 27.04.24 | Done | Suraja Ram
39 | 9 |  | 65/11 | DA+0 |  | 28.04.24 | 28.04.24 | Done | Suraja Ram
40 | 10 |  | 67/2 | DA+0 |  | 29.04.24 | 29.04.24 | Done | Suraja Ram
41 | 11 |  | 61/2 | DA+6 |  | 29.04.24 | 30.04.24 | Done | Ramagora
May'24
42 | 1 |  | 64/10 | DA+3 |  | 05.05.24 | 05.05.24 | Done | Suraja Ram
43 | 2 |  | 67/1 | DA+0 |  | 07.05.24 | 07.05.24 | Done | Suraja Ram
44 | 3 |  | 64/8 | DA+3 |  | 09.05.24 | 09.05.24 | Done | Suraja Ram
45 | 4 |  | 65/1 | DA+0 |  | 10.05.24 | 10.05.24 | Done | Suraja Ram
46 | 5 |  | 65/0 | DB1+0 |  | 10.05.24 | 10.05.24 | Done | Suraja Ram
47 | 6 |  | 61/1 | DA+6 |  | 10.05.24 | 10.05.24 | Done | Ramagora
48 | 7 |  | 60/9 | DA+3 |  | 11.05.24 | 11.05.24 | Done | Ramagora
49 | 8 |  | 63/4 | DA+0 |  | 14.05.24 | 14.05.24 | Done | Suraja Ram
50 | 9 |  | 63/3 | DA+3 |  | 15.05.24 | 15.05.24 | Done | Suraja Ram
51 | 10 |  | 63/5 | DA+3 |  | 16.05.24 | 16.05.24 | Done | Suraja Ram
52 | 11 |  | 61/3 | DA+6 |  | 17.05.24 | 17.05.24 | Done | Ramagora
53 | 12 |  | 62/11 | DA+3 |  | 19.05.24 | 19.05.24 | Done | Suraja Ram
54 | 13 |  | 61/4 | DA+3 |  | 23.05.24 | 23.05.24 | Done | Suraja Ram
55 | 14 |  | 61/5 | DA+3 |  | 25.05.24 | 25.05.24 | Done | Suraja Ram
Jun'24
56 | 1 |  | 64/2 | DA+3 |  | 03.06.24 | 03.06.24 | Done | Suraja Ram
57 | 2 |  | 64/3 | DA+0 |  | 06.06.24 | 06.06.24 | Done | Suraja Ram |  | 125
58 | 3 |  | 64/0 | DB2+0 |  | 06.06.24 | 06.06.24 | Done | Suraja Ram
59 | 4 |  | 61/10 | DA+9 |  | 07.06.24 | 07.06.24 | Done | Suraja Ram
60 | 5 |  | 61/8 | DA+6 |  | 08.06.24 | 08.06.24 | Done | Ramagora
61 | 6 |  | 63/2 | DA+0 |  | 08.06.24 | 08.06.24 | Done | Suraja Ram
62 | 7 |  | 61/9 | DA+0 |  | 09.06.24 | 09.06.24 | Done | Ramagora
63 | 8 |  | 63/1 | DA+3 |  | 09.06.24 | 09.06.24 | Done | Suraja Ram
64 | 9 |  | 59/5 | DA+3 |  | 10.06.24 | 10.06.24 | Done | Ramagora |  | 59/16
65 | 10 |  | 63/0 | DC1+0 |  | 10.06.24 | 11.06.24 | Done | Suraja Ram |  | 48/0
66 | 11 |  | 60/5 | DA+3 |  | 11.06.24 | 11.06.24 | Done | Ramagora
67 | 12 |  | 60/4 | DA+3 |  | 13.06.24 | 13.06.24 | Done | Ramagora
68 | 13 |  | 60/3 | DA+3 |  | 23.06.24 | 23.06.24 | Done | Ramagora
69 | 14 |  | 60/2 | DA+3 |  | 25.06.24 | 25.06.24 | Done | Ramagora
70 | 15 |  | 60/1 | DA+6 |  | 30.06.24 | 30.06.24 | Done | Ramagora
Jul'24
71 | 1 |  | 59/16 | DA+9 |  | 01.07.24 | 01.07.24 | Done | Suraja Ram
72 | 2 |  | 59/15 | DA+6 |  | 02.07.24 | 02.07.24 | Done | Suraja Ram
73 | 3 |  | 60/0 | DC+0 |  | 24.07.24 | 24.07.24 | Done | Suraja Ram
74 | 4 |  | 59/8 | DB1+3 |  | 27.07.24 | 27.07.24 | Done | Suraja Ram
Aug'24
75 | 1 |  | 55/3 | DA+0 |  | 23.08.24 | 23.08.24 | Done | Suraja Ram
76 | 2 |  | 55/4 | DA+0 |  | 24.08.24 | 24.08.24 | Done | Suraja Ram
77 | 4 |  | 57/6 | DA+3 |  | 27.08.24 | 27.08.24 | Done | Suraja Ram
78 | 5 |  | 57/3 | DA+0 |  | 28.08.24 | 28.08.24 | Done | Suraja Ram
79 | 6 |  | 57/4 | DA+0 |  | 30.08.24 | 30.08.24 | Done | Suraja Ram
80 | 7 |  | 57/5 | DA+3 |  | 30.08.24 | 30.08.24 | Done | Suraja Ram
Sept'24
81 | 1 |  | 62/0 | DB2+0 |  | 15.09.24 | 15.09.24 | Done | Suraja Ram
82 | 2 |  | 62/1 | DA+3 |  | 23.09.24 | 24.09.24 | Done | Suraja Ram
83 | 3 |  | 62/6 | DA+3 |  | 25.09.24 | 26.09.24 | Done | Suraja Ram
Oct'24
84 | 1 |  | 57/7 | DA+3 |  | 05.10.24 | 06.10.24 | Done | Suraja Ram
85 | 2 |  | 50/9 | DA+0 |  | 06.10.24 | 07.10.24 | Done | Suraja Ram
86 | 3 |  | 50/10 | DA+3 |  | 09.10.24 | 09.10.24 | Done | Suraja Ram
87 | 4 |  | 50/0 | DB2+0 |  | 10.10.24 | 10.10.24 | Done | Suraja Ram
88 | 5 |  | 50/3 | DA+6 |  | 24.10.24 | 24.10.24 | Done | Suraja Ram
89 | 6 |  | 50/1 | DA+6 |  | 25.10.24 | 25.10.24 | Done | Suraja Ram
90 | 7 |  | 51/1 | DA+0 |  | 25.10.24 | 25.10.24 | Done | Suraja Ram
91 | 8 |  | 50/2 | DA+9 |  | 28.10.24 | 28.10.24 | Done | Suraja Ram
92 | 9 |  | 64/11 | DA+3 |  | 29.10.24 | 29.10.24 | Done | Suraja Ram
Nov'24
93 | 1 |  | 59/11 | DA+6 |  | 11.11.24 | 11.11.24 | Done | Suraja Ram
94 | 2 |  | 50/7 | DA+0 |  | 14.11.24 | 14.11.24 | Done | Suraja Ram
95 | 3 |  | 73/1 | DA+0 |  | 14.11.24 | 14.11.24 | Done | Suraja Ram
96 | 4 |  | 73/2 | DA+0 |  | 19.11.24 | 19.11.24 | Done | Suraja Ram
97 | 5 |  | 73/9 | DA+0 |  | 20.11.24 | 20.11.24 | Done | Suraja Ram
98 | 6 |  | 52/7 | DA+3 |  | 25.11.24 | 25.11.24 | Done | Suraja Ram
99 | 7 |  | 52/6 | DA+6 |  | 25.11.24 | 25.11.24 | Done | Suraja Ram
100 | 8 |  | 52/8 | DA+6 |  | 26.11.24 | 26.11.24 | Done | Suraja Ram
101 | 9 |  | 48/0 | DC2+0 |  | 27.11.24 | 27.11.24 | Done | Suraja Ram
102 | 10 |  | 49/4 | DA+3 |  | 27.11.24 | 27.11.24 | Done | Suraja Ram
103 | 11 |  | 48/1 | DA+9 |  | 29.11.24 | 29.11.24 | Done | Suraja Ram
104 | 12 |  | 47/10 | DA+6 |  | 29.11.24 | 29.11.24 | Done | Suraja Ram
Dec'24
105 | 1 |  | 49/7 | DA+0 |  | 02.12.24 | 02.12.24 | Done | Suraja Ram
106 | 2 |  | 49/6 | DA+0 |  | 03.12.24 | 03.12.24 | Done | Suraja Ram
107 | 3 |  | 49/5 | DA+3 |  | 04.12.24 | 04.12.24 | Done | Suraja Ram
108 | 4 |  | 59/3 | DA+3 |  | 05.12.24 | 05.12.24 | Done | Suraja Ram |  |  | 05.12.24
109 | 5 |  | 59/4 | DA+3 |  | 06.12.24 | 06.12.24 | Done | Suraja Ram
110 | 6 |  | 73/6 | DA+0 |  | 13.12.24 | 13.12.24 | Done | Suraja Ram
111 | 7 |  | 72/3 | DA+3 |  | 17.12.24 | 17.12.24 | Done | Suraja Ram
112 | 8 |  | 59/1 | DA+3 |  | 18.12.24 | 18.12.24 | Done | Suraja Ram
113 | 9 |  | 59/2 | DA+3 |  | 20.12.24 | 20.12.24 | Done | Suraja Ram
114 | 10 |  | 50/8 | DA+9 |  | 23.12.24 | 23.12.24 | Done | Suraja Ram
115 | 11 |  | 73/8 | DA+0 |  | 25.12.24 | 25.12.24 | Done | Suraja Ram
116 | 12 |  | 51/2 | DA+0 |  | 26.12,24 | 26.12,24 | Done | Suraja Ram
117 | 13 |  | 49/2 | DA+0 |  | 26.12,24 | 26.12,24 | Done | Suraja Ram
118 | 14 |  | 49/3 | DA+3 |  | 26.12,24 | 26.12,24 | Done | Suraja Ram
119 | 15 |  | 49/1 | DA+0 |  | 28.12.24 | 28.12.24 | Done | Suraja Ram
2025-01-25
120 | 1 |  | 50/4 | DA+9 |  | 06.01.25 | 06.01.25 | Done | Suraja Ram
121 | 2 |  | 59/0 | DC2+0 |  | 07.01.25 | 07.01.25 | Done | Suraja Ram
122 | 3 |  | 50/6 | DA+9 |  | 12.01.25 | 12.01.25 | Done | Suraja Ram
123 | 4 |  | 65/7 | DA+0 |  | 17.01.25 | 17.01.25 | Done | Suraja Ram
124 | 5 |  | 65/8 | DA+0 |  | 18.01.25 | 18.01.25 | Done | Suraja Ram
125 | 6 |  | 73/3 | DA+0 |  | 27.01.25 | 27.01.25 | Done | Suraja Ram
126 | 7 |  | 73/4 | DA+0 |  | 28.01.25 | 29.01.25 | Done | Suraja Ram
2025-02-25
127 | 1 |  | 73/7 | DA+0 |  | 13.02.25 | 13.02.25 | Done | Suraja Ram
128 | 2 |  | 74/0 | DB+0 |  | 14.02.25 | 14.02.25 | Done | Suraja Ram
129 | 3 |  | 73/5 | DA+0 |  | 15.02.25 | 15.02.25 | Done | Suraja Ram
130 | 4 |  | 65/10 | DA+0 |  | 17.02.25 | 17.02.25 | Done | Suraja Ram
131 | 5 |  | 66/0 | DC2+6 |  | 19.02.25 | 19.02.25 | Done | Suraja Ram
132 | 6 |  | 51/0 | DC2+0 |  | 26.02.25 | 26.02.25 | Done | Suraja Ram
133 | 1 |  | 50/5 |  |  | 02.03.25 | 02.03.25 | Done | Suraja Ram
134 | 2 |  | 52/0 |  |  | 05.03.25 | 05.03.25 | Done | Suraja Ram
135 | 3 |  | 49/0 |  |  | 10.03.25 | 10.03.25 | Done | Suraja Ram
136 | 4 |  | 52/9 |  |  | 11.03.25 | 11.03.25 | Done | Suraja Ram
137 | 5 |  | 52/10 |  |  | 12.03.25 | 12.03.25 | Done | Suraja Ram
138 | 6 |  | 73/0 |  |  | 13.03.25 | 13.03.25 | Done | Suraja Ram
139 | 7 |  | 52/5 |  |  | 17.3.25 | 17.3.25 | Done | Suraja Ram

## Painting - PKG-G (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Painting
Cum Sl. No. | Month Sl. No. | JMC No. | Location No. | Tower Type | Depth of Fdn | Dt. of Start | Dt. of Complete | Tack Welding Status | Name of Sub-Contractor | Ramarks
2023-12-01
1 | 1 |  | 56/9 | DA+3 |  | 02.12.23 | 03.12.23 | Done | Suraja Ram
2 | 2 |  | 57/1 | DA+3 |  | 02.12.23 | 03.12.23 | Done | Suraja Ram
3 | 3 |  | 56/8 | DA+3 |  | 03.12.23 | 06.12.23 | Done | Suraja Ram
4 | 4 |  | 57/2 | DA+0 |  | 04.12.23 | 08.12.23 | Done | Suraja Ram
5 | 5 |  | 57/3 | DA+0 |  | 04.12.23 | 08.12.23 | Done | Suraja Ram
6 | 6 |  | 57/4 | DA+0 |  | 04.12.23 | 08.12.23 | Done | Suraja Ram
7 | 7 |  | 57/5 | DA+3 |  | 04.12.23 | 08.12.23 | Done | Suraja Ram
8 | 8 |  | 57/8 | DA+3 |  | 05.12.23 | 09.12.23 | Done | Suraja Ram
9 | 9 |  | 57/9 | DA+0 |  | 05.12.23 | 09.12.23 | Done | Suraja Ram
10 | 10 |  | 57/10 | DA+0 |  | 05.12.23 | 09.12.23 | Done | Suraja Ram
11 | 11 |  | 57/11 | DA+0 |  | 09.12.23 | 10.12.23 | Done | Suraja Ram
12 | 12 |  | 57/12 | DA+3 |  | 10.12.23 | 11.12.23 | Done | Suraja Ram
13 | 13 |  | 58/14 | DA+0 |  | 08.12.23 | 11.12.23 | Done | Suraja Ram
14 | 14 |  | 57/13 | DA+0 |  | 12.12.23 | 16.12.23 | Done | Suraja Ram
15 | 15 |  | 58/8 | DA+0 |  | 12.12.23 | 16.12.23 | Done | Suraja Ram
16 | 16 |  | 58/9 | DA+0 |  | 12.12.23 | 16.12.23 | Done | Suraja Ram
17 | 17 |  | 58/11 | DA+3 |  | 14.12.23 | 17.12.23 | Done | Suraja Ram
18 | 18 |  | 58/10 | DA+3 |  | 15.12.23 | 17.12.23 | Done | Suraja Ram
19 | 19 |  | 58/12 | DA+0 |  | 15.12.23 | 17.12.23 | Done | Suraja Ram
20 | 20 |  | 56/7 | DA+3 |  | 17.12.23 | 17.12.23 | Done | Suraja Ram
21 | 21 |  | 58/16 | DA+0 |  | 18.12.23 | 18.12.23 | Done | Suraja Ram
22 | 22 |  | 59/1 | DA+0 |  | 18.12.23 | 18.12.23 | Done | Suraja Ram
23 | 23 |  | 59/2 | DA+0 |  | 20.12.23 | 20.12.23 | Done | Suraja Ram
24 | 24 |  | 59/3 | DA+0 |  | 21.12.23 | 21.12.23 | Done | Suraja Ram
25 | 25 |  | 59/5 | DA+0 |  | 22.12.23 | 22.12.23 | Done | Suraja Ram
26 | 26 |  | 59/6 | DA+0 |  | 23.12.23 | 24.12.23 | Done | Suraja Ram
27 | 27 |  | 56/3 | DA+0 |  | 25.12.23 | 27.12.23 | Done | Suraja Ram
28 | 28 |  | 56/4 | DA+3 |  | 26.12.23 | 27.12.23 | Done | Suraja Ram
29 | 29 |  | 55/4 | DA+3 |  | 26.12.23 | 27.12.23 | Done | Suraja Ram
30 | 30 |  | 55/5 | DA+0 |  | 28.12.23 | 28.12.23 | Done | Suraja Ram
31 | 31 |  | 55/6 | DA+3 |  | 29.12.23 | 30.12.23 | Done | Suraja Ram
2024-01-01
32 | 1 |  | 55/11 | DA+3 |  | 08.01.24 | 09.01.24 | Done | Suraja Ram
33 | 2 |  | 55/10 | DA+3 |  | 10.01.24 | 10.01.24 | Done | Suraja Ram
34 | 3 |  | 58/1 | DA+0 |  | 18.01.24 | 19.01.24 | Done | Suraja Ram
35 | 4 |  | 58/6 | DA+3 |  | 19.01.24 | 20.01.24 | Done | Suraja Ram
36 | 5 |  | 58/5 | DA+3 |  | 19.01.24 | 20.01.24 | Done | Suraja Ram
37 | 6 |  | 58/4 | DA+0 |  | 20.01.24 | 20.01.24 | Done | Suraja Ram
38 | 7 |  | 57/6 | DB1+0 |  | 21.01.24 | 21.01.24 | Done | Suraja Ram
39 | 8 |  | 57/7 | DA+3 |  | 21.01.24 | 21.01.24 | Done | Suraja Ram
40 | 9 |  | 51/7 | DA+3 |  | 21.01.24 | 21.01.24 | Done | Kailash Nath
41 | 10 |  | 51/5 | DA+0 |  | 22.01.24 | 22.01.24 | Done | Kailash Nath
42 | 11 |  | 57/0 | DB2+0 |  | 22.01.24 | 22.01.24 | Done | Suraja Ram
43 | 12 |  | 56/6 | DA+3 |  | 22.01.24 | 22.01.24 | Done | Suraja Ram
44 | 13 |  | 56/5 | DA+0 |  | 23.01.24 | 23.01.24 | Done | Suraja Ram |  | comp
45 | 14 |  | 56/2 | DA+3 |  | 23.01.24 | 23.01.24 | Done | Suraja Ram
46 | 15 |  | 51/4 | DA+3 |  | 23.01.24 | 23.01.24 | Done | Kailash Nath
47 | 16 |  | 51/3 | DA+0 |  | 23.01.24 | 23.01.24 | Done | Kailash Nath
48 | 17 |  | 51/2 | DA+0 |  | 24.01.24 | 24.01.24 | Done | Kailash Nath
49 | 18 |  | 56/0 | DB1+0 |  | 24.01.24 | 24.01.24 | Done | Suraja Ram
50 | 19 |  | 55/9 | DA+3 |  | 25.01.24 | 25.01.24 | Done | Suraja Ram
51 | 20 |  | 55/8 | DA+3 |  | 25.01.24 | 25.01.24 | Done | Suraja Ram
52 | 21 |  | 52/2 | DA+3 |  | 25.01.24 | 25.01.24 | Done | Kailash Nath
53 | 22 |  | 52/5 | DA+3 |  | 25.01.24 | 25.01.24 | Done | Kailash Nath
54 | 23 |  | 51/10 | DA+3 |  | 27.01.24 | 27.01.24 | Done | Kailash Nath
55 | 24 |  | 52/1 | DA+0 |  | 27.01.24 | 27.01.24 | Done | Kailash Nath
56 | 25 |  | 55/7 | DA+0 |  | 26.01.24 | 26.01.24 | Done | Suraja Ram
57 | 26 |  | 58/3 | DA+3 |  | 30.01.24 | 30.01.24 | Done | Suraja Ram
58 | 27 |  | 58/7 | DB+0 |  | 29.01.24 | 29.01.24 | Done | Suraja Ram
Feb-24
59 | 1 |  | 59/0 | DB+0 |  | 02.02.24 | 02.02.24 | Done | Suraja Ram
60 | 2 |  | 58/15 | DA+3 |  | 02.02.24 | 02.02.24 | Done | Suraja Ram
61 | 3 |  | 61/1 | DA+0 |  | 03.02.24 | 03.02.24 | Done | Suraja Ram
62 | 4 |  | 55/1 | DA+3 |  | 04.02.24 | 04.02.24 | Done | Suraja Ram
63 | 5 |  | 55/3 | DA+0 |  | 06.02.24 | 06.02.24 | Done | Suraja Ram
64 | 6 |  | 55/2 | DA+3 |  | 04.02.24 | 05.02.24 | Done | Suraja Ram |  |  | 52/4
65 | 7 |  | 41/5 | DA+0 |  | 15.02.24 | 15.02.24 | Done | Ramagora
66 | 8 |  | 41/7 | DA+3 |  | 15.02.24 | 15.02.24 | Done | Ramagora
67 | 9 |  | 41/10 | DA+3 |  | 28.01.24 | 16.02.24 | Done | Ramagora
68 | 10 |  | 41/11 | DA+3 |  | 29.01.24 | 17.02.24 | Done | Ramagora
69 | 11 |  | 46/2 | DA+0 |  | 17.02.24 | 18.02.24 | Done | Suraja Ram
70 | 12 |  | 43/1 | DA+9 |  | 10.02.24 | 18.02.24 | Done | Ramagora
71 | 13 |  | 44/2 | DA+0 |  | 27.01.24 | 18.02.24 | Done | Ramagora
72 | 14 |  | 47/0 | DB+0 |  | 19.02.24 | 19.02.24 | Done | Suraja Ram
73 | 15 |  | 48/2 | DA+3 |  | 19.02.24 | 19.02.24 | Done | Suraja Ram
74 | 16 |  | 53/3 | DA+3 |  | 19.02.24 | 19.02.24 | Done | Suraja Ram
75 | 17 |  | 44/4 | DA+0 |  | 19.02.24 | 19.02.24 | Done | Ramagora
76 | 18 |  | 46/3 | DA+0 |  | 20.02.24 | 20.02.24 | Done | Ramagora
77 | 19 |  | 47/2 | DA+0 |  | 22.02.24 | 22.02.24 | Done | Ramagora
78 | 20 |  | 50/3 | DA+0 |  | 22.02.24 | 22.02.24 | Done | Ramagora
79 | 21 |  | 48/1 | DA+0 |  | 03.02.24 | 22.02.24 | Done | Ramagora
80 | 22 |  | 50/4 | DA+3 |  | 23.02.24 | 23.02.24 | Done | Ramagora
81 | 23 |  | 51/6 | DA+0 |  | 24.02.24 | 24.02.24 | Done | Ramagora
82 | 24 |  | 51/8 | DA+3 |  | 24.02.24 | 24.02.24 | Done | Ramagora
83 | 25 |  | 51/9 | DA+3 |  | 25.02.24 | 25.02.24 | Done | Ramagora
84 | 26 |  | 53/4 | DA+3 |  | 25.02.24 | 25.02.24 | Done | Suraja Ram
85 | 27 |  | 53/1 | DA+0 |  | 25.02.24 | 25.02.24 | Done | Suraja Ram
86 | 28 |  | 52/0 | DB+0 |  | 26.02.24 | 26.02.24 | Done | Suraja Ram
87 | 29 |  | 52/4 | DA+0 |  | 27.02.24 | 27.02.24 | Done | Ramagora
March'24
88 | 1 |  | 41/8 | DA+0 |  | 08.03.24 | 08.03.24 | Done | Ramagora
89 | 2 |  | 41/4 | DA+0 |  | 08.03.24 | 08.03.24 | Done | Ramagora
90 | 3 |  | 41/6 | DA+0 |  | 08.03.24 | 08.03.24 | Done | Ramagora
91 | 4 |  | 41/9 | DA+0 |  | 08.03.24 | 08.03.24 | Done | Ramagora
92 | 5 |  | 43/4 | DA+9 |  | 10.03.24 | 10.03.24 | Done | Ramagora
93 | 6 |  | 43/5 | DA+0 |  | 10.03.24 | 10.03.24 | Done | Ramagora
94 | 7 |  | 51/1 | DA+0 |  | 14.03.24 | 14.03.24 | Done | Ramagora
95 | 8 |  | 53/2 | DA+3 |  | 23.03.24 | 23.03.24 | Done | Suraja Ram
96 | 9 |  | 51/0 | DB+0 |  | 29.03.24 | 29.03.24 | Done | Ramagora
97 | 10 |  | 44/3 | DA+3 |  | 30.03.24 | 30.03.24 | Done | Ramagora
April'24
98 | 1 |  | 47/3 | DA+0 |  | 23.04.24 | 23.04.24 | Done | Ramagora
99 | 2 |  | 56/1 | DA+3 |  | 29.04.24 | 29.04.24 | Done | Ramagora
May'24
100 | 1 |  | 61/2 | DA+0 | 06.05.24 | 12.05.24 | 12.05.24 | Done | Suraja Ram
101 | 2 |  | 44/1 | DA+0 | 12.05.24 | 13.05.24 | 13.05.24 | Done | Ramagora
102 | 3 |  | 58/0 | DC2+0 | 04.05.24 | 13.05.24 | 13.05.24 | Done | Suraja Ram
103 | 4 |  | 55/0 | DC+0 | 24.05.24 | 26.05.24 | 26.05.24 | Done | Suraja Ram
June'24
104 | 1 |  | 65/5 | DA+0 | 30.05.24 | 02.06.24 | 02.06.24 | Done | Suraja Ram
105 | 2 |  | 65/4 | DA+0 | 31.05.24 | 02.06.24 | 02.06.24 | Done | Suraja Ram
106 | 3 |  | 58/2 | DA+0 | 02.06.24 | 02.06.24 | 02.06.24 | Done | Suraja Ram
107 | 4 |  | 65/3 | DA+0 | 02.06.24 | 03.06.24 | 03.06.24 | Done | Suraja Ram
108 | 5 |  | 52/3 | DA+0 |  | 24.06.24 | 24.06.24 | Done | Suraja Ram
109 | 6 |  | 53/0 | DC2+3 | 22.06.24 | 25.06.24 | 25.06.24 | Done | Suraja Ram
Sept'24
110 | 1 |  | 48/0 | DB+0 | 23.07.24 | 24.07.24 | 24.07.24 | Done | Suraja Ram
111 | 2 |  | 46/4 | DA+0 | 16.09.24 | 21.09.24 | 21.09.24 | Done | Suraja Ram
112 | 3 |  | 47/1 | DA+0 | 19.09.24 | 21.09.24 | 21.09.24 | Done | Suraja Ram
113 | 4 |  | 50/2 | DA+0 | 20.09.24 | 22.09.24 | 22.09.24 | Done | Suraja Ram
114 | 5 |  | 50/1 | DA+0 | 22.09.24 | 24.09.24 | 24.09.24 | Done | Suraja Ram
115 | 6 |  | 72/5 | DA+0 | 26.09.24 | 26.09.24 | 26.09.24 | Done | Suraja Ram
116 | 7 |  | 72/3 | DA+0 |  | 29.09.24 | 29.09.24 | Done | Suraja Ram
117 | 8 |  | 72/4 | DA+0 |  | 29.09.24 | 29.09.24 | Done | Suraja Ram
118 | 9 |  | 72/6 | DA+0 | 29.09.24 | 30.09.24 | 30.09.24 | Done | Suraja Ram
119 | 10 |  | 71/5 | DA+0 | 29.09.24 | 30.09.24 | 30.09.24 | Done | Suraja Ram
Oct'24
120 | 1 |  | 50/0 | DC2+3 | 04.10.24 | 08.10.24 | 08.10.24 | Done | Suraja Ram
121 | 2 |  | 72/0 | DB1+0 | 04.10.24 | 04.10.24 | 16.10.24 | Done | Suraja Ram
122 | 3 |  | 71/4 | DA+0 | 13.10.24 | 13.10.24 | 16.10.24 | Done | Suraja Ram
123 | 4 |  | 72/2 | DA+0 | 14.10.24 | 14.10.24 | 14.10.24 | Done | Suraja Ram
124 | 5 |  | 71/2 | DA+0 | 15.10.24 | 15.10.24 | 17.10.24 | Done | Suraja Ram
125 | 6 |  | 71/1 | DA+0 | 16.10.24 | 16.10.24 | 17.10.24 | Done | Suraja Ram
126 | 7 |  | 68/1 | DA+3 | 19.10.24 | 19.10.24 | 19.10.24 | Done | Suraja Ram
127 | 8 |  | 72/1 | DA+0 | 19.10.24 | 19.10.24 | 19.10.24 | Done | Suraja Ram
Nov'24
128 | 1 |  | 72/7 | DB1+9 | 09.11.24 | 09.11.24 | 09.11.24 | Done | Suraja Ram
129 | 2 |  | 68/6 | DA+3 | 14.11.24 | 15.11.24 | 15.11.24 | Done | Suraja Ram
130 | 3 |  | 71/3 | DA+0 | 14.11.24 | 14.11.24 | 14.11.24 | Done | Suraja Ram
131 | 4 |  | 68/3 | DA+0 | 14.11.24 | 14.11.24 | 14.11.24 | Done | Suraja Ram
132 | 5 |  | 66/2 | DA+0 | 14.11.24 | 14.11.24 | 14.11.24 | Done | Suraja Ram
133 | 6 |  | 73/0 | DD45+9 |  | 18.11.24 | 18.11.24 | Done | Suraja Ram
134 | 7 |  | 68/4 | DA+3 | 20.11.24 | 20.11.24 | 20.11.24 | Done | Suraja Ram
135 | 8 |  | 69/6 | DA+0 | 04.11.24 | 04.11.24 | 04.11.24 | Done | Suraja Ram
136 | 9 |  | 68/2 | DA+3 | 20.11.24 | 20.11.24 | 20.11.24 | Done | Suraja Ram
137 | 10 |  | 68/5 | DA+3 | 20.11.24 | 20.11.24 | 20.11.24 | Done | Suraja Ram
Dec'24
138 | 1 |  | 69/5 | DA+0 | 08.12.24 | 08.12.24 | 08.12.24 | Done | Suraja Ram
139 | 2 |  | 69/1 | DA+0 | 10.12.24 | 10.12.24 | 10.12.24 | Done | Suraja Ram
140 | 3 |  | 69/2 | DA+0 | 11.12.24 | 11.12.24 | 11.12.24 | Done | Suraja Ram
141 | 4 |  | 66/4 | DA+3 | 12.12.24 | 12.12.24 | 12.12.24 | Done | Suraja Ram
142 | 5 |  | 66/1 | DA+3 | 15.12.24 | 15.12.24 | 15.12.24 | Done | Suraja Ram
143 | 6 |  | 68/0 | DD+0 | 16.12.24 | 16.12.24 | 16.12.24 | Done | Suraja Ram
144 | 7 |  | 43/3 | DA+3 | 22.12.24 | 22.12.24 | 22.12.24 | Done | Suraja Ram
145 | 8 |  | 69/7 | DA+0 | 22.11.24 | 22.11.24 | 22.11.24 | Done | Suraja Ram
146 | 9 |  | 69/0 | DB1+0 | 22.12.24 | 25.12.24 | 25.12.24 | Done | Suraja Ram
147 | 10 |  | 69/8 | DA+0 | 31.12.24 | 31.12.24 | 31.12.24 | Done | Suraja Ram
148 | 11 |  | 69/9 | DA+0 | 31.12.24 | 31.12.24 | 31.12.24 | Done | Suraja Ram
2025-01-25
149 | 1 |  | 67/1 | DB1+9 | 20.12.24 | 02.01.25 | 02.01.25 | Done | Suraja Ram
150 | 2 |  | 38/1 | DA+3 | 29.12.24 | 03.01.25 | 03.01.25 | Done | Suraja Ram
151 | 3 |  | 38/2 | DA+6 | 30.12.24 | 03.01.25 | 03.01.25 | Done | Suraja Ram
152 | 4 |  | 69/3 | DA+0 | 26.12.24 | 04.01.25 | 04.01.25 | Done | Suraja Ram
153 | 5 |  | 69/4 |  | 27.12.24 | 04.01.25 | 04.01.25 | Done | Suraja Ram
154 | 6 |  | 37/3 | DA+0 | 02.01.25 | 04.01.25 | 04.01.25 | Done | Suraja Ram
155 | 7 |  | 38/3 | DA+9 | 04.01.25 | 04.01.25 | 04.01.25 | Done | Suraja Ram
156 | 8 |  | 37/4 | DA+6 | 09.01.25 | 09.01.25 | 09.01.25 | Done | Suraja Ram
157 | 9 |  | 41/2 | DA+0 |  | 19.01.25 | 19.01.25 | Done | Suraja Ram
158 | 10 |  | 71/0 | DD60+0 |  | 13.01.25 | 13.01.25 | Done | Suraja Ram
159 | 11 |  | 37/2 | DB1+6 | 20.01.25 | 22.01.25 | 22.01.25 | Done | Suraja Ram
160 | 12 |  | 59/4 | DA+0 | 16.01.25 | 23.01.25 | 23.01.25 | Done | Suraja Ram
161 | 13 |  | 70/0 | DD60+0 |  | 25.01.25 | 25.01.25 | Done | Suraja Ram
162 | 14 |  | 67/0 | DD45+0 |  | 24.01.25 | 24.01.25 | Done | Suraja Ram
Feb'25
163 | 1 |  | 41/12 | DA+3 |  | 02.02.25 | 02.02.25 | Done | Suraja Ram
164 | 2 |  | 41/3 | DA+0 |  | 02.02.25 | 02.02.25 | Done | Suraja Ram
165 | 3 |  | 37/5 | DA+3 |  | 03.02.25 | 03.02.25 | Done | Suraja Ram
166 | 4 |  | 37/6 | DA+6 |  | 04.02.25 | 04.02.25 | Done | Suraja Ram
167 | 5 |  | 37/7 | DA+3 |  | 05.02.25 | 05.02.25 | Done | Suraja Ram
168 | 6 |  | 37/8 | DA+0 |  | 06.02.25 | 06.02.25 | Done | Suraja Ram
169 | 7 |  | 41/1 | DA+3 |  | 08.02.25 | 08.02.25 | Done | Suraja Ram
170 | 8 |  | 42/0 | DC2+9 |  | 09.02.25 | 09.02.25 | Done | Suraja Ram
171 | 9 |  | 65/6 |  | 20.02.25 | 21.02.25 | 21.02.25 | Done | Suraja Ram
172 | 10 |  | 40/11 | DA+3 | 24.02.25 | 28.02.25 | 28.02.25 | Done | Suraja Ram
173 | 11 |  | 40/10 | DA+3 | 24.02.25 | 28.02.25 | 28.02.25 | Done | Suraja Ram
Feb'25
174 | 1 |  | 40/2 |  | 26.02.25 | 01.03.25 | 01.3.25 | Done | Suraja Ram
175 | 2 |  | 41/0 |  | 27.02.25 | 01.03.25 | 01.03.25 | Done | Suraja Ram
176 | 3 |  | 40/12 |  | 03.03.25 | 03.03.25 | 03.03.25 | Done | Suraja Ram
177 | 4 |  | 65/7 | DA+0 | 21.02.25 | 21.02.25 | 21.02.25 | Done | Suraja Ram
178 | 5 |  | 58/13 | DA+0 | 26.12.24 | 26.12.24 | 26.12.24 | Done | Suraja Ram
179 | 1 |  | 40/6 |  | 07.03.25 | 07.03.25 | 07.03.25 | Done | Suraja Ram
180 | 2 |  | 60/0 |  | 13.03.25 | 16.03.25 | 16.03.25 | Done | Suraja Ram
181 | 6 |  | 39/0 |  | 18.03.25 | 18.03.25 | 18.03.25 | Done | Suraja Ram
182 | 7 |  | 40/0 |  | 19.03.25 | 19.03.25 | 19.03.25 | Done | Suraja Ram
183 | 8 |  | 40/1 |  | 20.03.25 | 20.03.25 | 20.03.25 | Done | Suraja Ram
184 | 4 |  | 40/7 |  | 08.03.25 | 08.03.25 | 08.03.25 | Done | Suraja Ram
185 | 5 |  | 38/0 |  | 06.03.25 | 06.03.25 | 06.03.25 | Done | Suraja Ram
186 | 9 |  | 38/8 |  | 22.03.25 | 22.03.25 | 22.03.25 | Done | Suraja Ram
187 | 10 |  | 38/9 |  | 23.03.25 | 23.03.25 | 23.03.25 | Done | Suraja Ram

## Painting - PKG-F (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Painting
Cum Sl. No. | Month Sl. No. | JMC No. | Location No. | Tower Type | Depth of Fdn | Dt. of Start | Dt. of Complete | Tack Welding Status | Name of Sub-Contractor | Ramarks
1 | 1 |  | 59/14 | DA+6 |  | 26.02.24 | 26.02.24 | Done | Suraja Ram
2 | 2 |  | 63/6 | DA+3 |  | 29.02.24 | 29.02.24 | Done | Suraja Ram
March'24
3 | 1 |  | 62/3 | DA+0 |  | 11.03.24 | 11.03.24 | Done | Suraja Ram
4 | 2 |  | 62/4 | DA+3 |  | 11.03.24 | 11.03.24 | Done | Suraja Ram
5 | 3 |  | 62/2 | DA+3 |  | 11.03.24 | 11.03.24 | Done | Suraja Ram
6 | 4 |  | 59/7 | DA+3 |  | 12.03.24 | 13.03.24 | Done | Ramagora
7 | 5 |  | 59/9 | DA+3 |  | 14.03.24 | 14.03.24 | Done | Suraja Ram
8 | 6 |  | 59/12 | DA+6 |  | 14.03.24 | 14.03.24 | Done | Suraja Ram
9 | 7 |  | 59/10 | DA+0 |  | 14.03.24 | 14.03.24 | Done | Suraja Ram
10 | 8 |  | 63/8 | DA+3 |  | 15.03.24 | 15.03.24 | Done | Suraja Ram
11 | 9 |  | 62/7 | DA+3 |  | 15.03.24 | 15.03.24 | Done | Suraja Ram
12 | 10 |  | 62/8 | DA+0 |  | 16.03.24 | 16.03.24 | Done | Suraja Ram
13 | 11 |  | 64/4 | DA+3 |  | 16.03.24 | 16.03.24 | Done | Suraja Ram
14 | 12 |  | 60/6 | DA+0 |  | 16.03.24 | 16.03.24 | Done | Ramagora
15 | 13 |  | 60/11 | DA+3 |  | 18.03.24 | 18.03.24 | Done | Ramagora
16 | 14 |  | 64/5 | DA+3 |  | 20.03.24 | 20.03.24 | Done | Suraja Ram
17 | 15 |  | 62/9 | DA+3 |  | 20.03.24 | 20.03.24 | Done | Suraja Ram
18 | 16 |  | 60/8 | DA+0 |  | 21.03.24 | 21.03.24 | Done | Ramagora
19 | 17 |  | 65/4 | DA+0 |  | 21.03.24 | 21.03.24 | Done | Suraja Ram
20 | 18 |  | 65/2 | DA+0 |  | 16.03.24 | 16.03.24 | Done | Suraja Ram
21 | 19 |  | 60/7 | DA+3 |  | 23.03.24 | 23.03.24 | Done | Suraja Ram
22 | 20 |  | 59/13 | DA+3 |  | 23.03.24 | 23.03.24 | Done | Suraja Ram
23 | 21 |  | 59/6 | DA+3 |  | 23.03.24 | 23.03.24 | Done | Ramagora
24 | 22 |  | 60/10 | DA+0 |  | 26.03.24 | 26.03.24 | Done | Suraja Ram
25 | 23 |  | 62/10 | DA+0 |  | 26.03.24 | 26.03.24 | Done | Suraja Ram
26 | 24 |  | 61/6 | DA+3 |  | 28.03.24 | 28.03.24 | Done | Suraja Ram
27 | 25 |  | 64/1 | DA+0 |  | 28.03.24 | 28.03.24 | Done | Suraja Ram
28 | 26 |  | 62/5 | DA+0 |  | 28.03.24 | 28.03.24 | Done | Suraja Ram
29 | 27 |  | 65/3 | DA+0 |  | 29.03.24 | 29.03.24 | Done | Suraja Ram
30 | 28 |  | 65/5 | DA+0 |  | 31.03.24 | 31.03.24 | Done | Suraja Ram
April'24
31 | 1 |  | 61/7 | DA+9 |  | 03.04.24 | 03.04.24 | Done | Suraja Ram
32 | 2 |  | 64/6 | DA+0 |  | 06.04.24 | 06.04.24 | Done | Suraja Ram
33 | 3 |  | 65/6 | DA+0 |  | 06.04.24 | 06.04.24 | Done | Suraja Ram
34 | 4 |  | 61/0 | DB+0 |  | 28.04.24 | 28.04.24 | Done | Ramagora
35 | 5 |  | 63/7 | DA+3 |  | 29.04.24 | 30.04.24 | Done | Suraja Ram
May'24
36 | 1 |  | 65/9 | DA+0 |  | 02.05.24 | 02.05.24 | Done | Suraja Ram
37 | 2 |  | 64/7 | DA+3 |  | 02.05.24 | 02.05.24 | Done | Suraja Ram
38 | 3 |  | 61/2 | DA+6 |  | 02.05.24 | 02.05.24 | Done | Ramagora
39 | 4 |  | 64/9 | DA+3 |  | 02.05.24 | 02.05.24 | Done | Suraja Ram
40 | 5 |  | 65/11 | DA+0 |  | 03.05.24 | 03.05.24 | Done | Suraja Ram
41 | 6 |  | 64/8 | DA+3 |  | 11.05.24 | 11.05.24 | Done | Suraja Ram
42 | 7 |  | 65/1 | DA+0 |  | 11.05.24 | 11.05.24 | Done | Suraja Ram
43 | 8 |  | 64/10 | DA+3 |  | 11.05.24 | 11.05.24 | Done | Suraja Ram
44 | 9 |  | 67/1 | DA+0 |  | 12.05.24 | 12.05.24 | Done | Suraja Ram
45 | 10 |  | 67/2 | DA+0 |  | 12.05.24 | 12.05.24 | Done | Suraja Ram
46 | 11 |  | 65/0 | DB1+0 |  | 13.05.24 | 13.05.24 | Done | Suraja Ram
47 | 12 |  | 60/9 | DA+3 |  | 11.05.24 | 11.05.24 | Done | Ramagora
48 | 13 |  | 63/4 | DA+0 |  | 17.05.24 | 17.05.24 | Done | Suraja Ram
49 | 14 |  | 63/3 | DA+3 |  | 17.05.24 | 17.05.24 | Done | Suraja Ram
50 | 15 |  | 61/1 | DA+6 |  | 18.05.24 | 18.05.24 | Done | Ramagora
51 | 16 |  | 61/3 | DA+6 |  | 18.05.24 | 18.05.24 | Done | Ramagora
52 | 17 |  | 63/5 | DA+3 |  | 20.05.24 | 20.05.24 | Done | Suraja Ram
53 | 18 |  | 62/11 | DA+3 |  | 20.05.24 | 20.05.24 | Done | Suraja Ram
54 | 13 |  | 61/4 | DA+3 |  | 23.05.24 | 23.05.24 | Done | Suraja Ram
55 | 1`4 |  | 61/5 | DA+3 |  | 25.05.24 | 25.05.24 | Done | Suraja Ram
June'24
56 | 1 |  | 64/2 | DA+3 |  | 04.06.24 | 04.06.24 | Done | Suraja Ram
57 | 2 |  | 64/0 | DB2+0 |  | 06.06.24 | 06.06.24 | Done | Suraja Ram
58 | 3 |  | 63/0 | DC1+0 |  | 10.06.24 | 11.06.24 | Done | Suraja Ram
59 | 4 |  | 60/5 | DA+3 |  | 12.06.24 | 12.06.24 | Done | Ramagora
60 | 5 |  | 61/10 | DA+9 |  | 12.06.24 | 12.06.24 | Done | Suraja Ram
61 | 6 |  | 63/1 | DA+3 |  | 12.06.24 | 12.06.24 | Done | Suraja Ram
62 | 7 |  | 63/2 | DA+0 |  | 12.06.24 | 12.06.24 | Done | Suraja Ram
63 | 8 |  | 64/3 | DA+0 |  | 12.06.24 | 12.06.24 | Done | Suraja Ram
64 | 9 |  | 60/4 | DA+3 |  | 13.06.24 | 13.06.24 | Done | Ramagora
65 | 10 |  | 59/5 | DA+3 |  | 14.06.24 | 14.06.24 | Done | Ramagora
66 | 11 |  | 61/8 | DA+6 |  | 15.06.24 | 15.06.24 | Done | Ramagora
67 | 12 |  | 61/9 | DA+0 |  | 15.06.24 | 15.06.24 | Done | Ramagora
68 | 13 |  | 60/3 | DA+3 |  | 23.06.24 | 23.06.24 | Done | Ramagora
69 | 14 |  | 60/2 | DA+3 |  | 25.06.24 | 25.06.24 | Done | Ramagora
July'24
70 | 1 |  | 60/1 | DA+6 |  | 01.07.24 | 01.07.24 | Done | Ramagora
71 | 2 |  | 60/0 | DC+0 |  | 24.07.24 | 24.07.24 | Done | Suraja Ram
72 | 3 |  | 59/16 | DA+9 |  | 01.07.24 | 01.07.24 | Done | Suraja Ram
73 | 4 |  | 59/15 | DA+6 |  | 02.07.24 | 02.07.24 | Done | Suraja Ram
74 | 5 |  | 59/8 | DB1+3 |  | 27.07.24 | 27.07.24 | Done | Suraja Ram
Sept'24
75 | 1 |  | 55/3 | DA+0 |  | 01.09.24 | 01.09.24 | Done | Suraja Ram
76 | 2 |  | 55/4 | DA+0 |  | 02.09.24 | 02.09.24 | Done | Suraja Ram
77 | 3 |  | 62/6 | DA+3 |  | 03.09.24 | 03.09.24 | Done | Suraja Ram
78 | 4 |  | 57/6 | DA+3 |  | 04.09.24 | 04.09.24 | Done | Suraja Ram
79 | 5 |  | 57/3 | DA+0 |  | 05.09.24 | 05.09.24 | Done | Suraja Ram
80 | 6 |  | 57/4 | DA+0 |  | 06.09.24 | 06.09.24 | Done | Suraja Ram
81 | 7 |  | 57/5 | DA+3 |  | 07.09.24 | 07.09.24 | Done | Suraja Ram
82 | 8 |  | 62/1 | DA+3 |  | 26.09.24 | 26.09.24 | Done | Suraja Ram
83 | 9 |  | 62/0 | DB2+0 |  | 15.09.24 | 15.09.24 | Done | Suraja Ram
Oct'24
84 | 1 |  | 57/7 | DA+3 |  | 07.10.24 | 07.10.24 | Done | Suraja Ram
85 | 2 |  | 50/9 | DA+0 |  | 08.10.24 | 08.10.24 | Done | Suraja Ram
86 | 3 |  | 50/10 | DA+0 |  | 10.101.24 | 10.10.24 | Done | Suraja Ram
87 | 4 |  | 50/0 | DB2+0 |  | 11.10.24 | 11.10.24 | Done | Suraja Ram
88 | 5 |  | 50/3 | DA+6 |  | 24.10.24 | 24.10.24 | Done | Suraja Ram
89 | 6 |  | 50/1 | DA+6 |  | 25.10.24 | 25.10.24 | Done | Suraja Ram
90 | 7 |  | 51/1 | DA+0 |  | 25.10.24 | 25.10.24 | Done | Suraja Ram
91 | 8 |  | 50/2 | DA+9 |  | 28.10.24 | 28.10.24 | Done | Suraja Ram
Nov'24
92 | 1 |  | 59/11 | DA+6 |  | 11.11.24 | 11.11.24 | Done | Suraja Ram
93 | 2 |  | 50/7 | DA+0 |  | 14.11.24 | 14.11.24 | Done | Suraja Ram
94 | 3 |  | 73/1 | DA+0 |  | 14.11.24 | 14.11.24 | Done | Suraja Ram
95 | 4 |  | 73/9 | DA+0 |  | 20.11.24 | 20.11.24 | Done | Suraja Ram
96 | 5 |  | 64/11 | DA+3 |  | 21.11.24 | 21.11.24 | Done | Suraja Ram
97 | 6 |  | 73/2 | DA+0 |  | 19.11.24 | 19.11.24 | Done | Suraja Ram
98 | 7 |  | 52/6 | DA+6 |  | 25.11.24 | 25.11.24 | Done | Suraja Ram
99 | 8 |  | 52/7 | DA+3 |  | 26.11.24 | 26.11.24 | Done | Suraja Ram
100 | 9 |  | 52/8 | DA+6 |  | 26.11.24 | 26.11.24 | Done | Suraja Ram
101 | 11 |  | 48/1 | DA+9 |  | 30.11.24 | 30.11.24 | Done | Suraja Ram
Dec'24
102 | 1 |  | 49/4 | DA+3 |  | 27.11.24 | 27.11.24 | Done | Suraja Ram
103 | 2 |  | 48/0 | DC2+0 |  | 27.11.24 | 27.11.24 | Done | Suraja Ram
104 | 3 |  | 47/10 | DA+6 |  | 29.11.24 | 29.11.24 | Done | Suraja Ram
105 | 4 |  | 49/6 | DA+0 |  | 03.12.24 | 03.12.24 | Done | Suraja Ram
106 | 5 |  | 49/5 | DA+3 |  | 04.12.24 | 04.12.24 | Done | Suraja Ram
107 | 6 |  | 59/4 | DA+3 |  | 06.12.24 | 06.12.24 | Done | Suraja Ram
108 | 7 |  | 49/7 | DA+0 |  | 02.12.24 | 02.12.24 | Done | Suraja Ram
109 | 8 |  | 73/6 | DA+0 |  | 13.12.24 | 13.12.24 | Done | Suraja Ram
110 | 9 |  | 59/1 | DA+3 |  | 18.12.24 | 18.12.24 | Done | Suraja Ram
111 | 10 |  | 59/2 | DA+3 |  | 20.12.24 | 20.12.24 | Done | Suraja Ram
112 | 11 |  | 59/3 | DA+3 |  | 07.12.24 | 07.12.24 | Done | Suraja Ram
113 | 12 |  | 72/3 | DA+3 |  | 17.12.24 | 17.12.24 | Done | Suraja Ram
114 | 13 |  | 50/8 | DA+9 |  | 23.12.24 | 23.12.24 | Done | Suraja Ram
115 | 14 |  | 51/2 | DA+0 |  | 26.12,24 | 26.12,24 | Done | Suraja Ram
116 | 15 |  | 49/2 | DA+0 |  | 26.12,24 | 26.12,24 | Done | Suraja Ram
117 | 16 |  | 49/3 | DA+3 |  | 26.12,24 | 26.12,24 | Done | Suraja Ram
118 | 17 |  | 49/1 | DA+0 |  | 29.12.24 | 29.12.24 | Done | Suraja Ram
119 | 18 |  | 73/8 | DA+0 |  | 29.12.24 | 29.12.24 | Done | Suraja Ram
Jan'25
120 | 1 |  | 50/4 | DA+9 |  | 06.01.25 | 06.01.25 | Done | Suraja Ram
121 | 2 |  | 59/0 | DC2+0 |  | 07.01.25 | 07.01.25 | Done | Suraja Ram
122 | 3 |  | 50/6 | DA+9 |  | 12.01.25 | 12.01.25 | Done | Suraja Ram
123 | 4 |  | 65/7 | DA+0 |  | 23.01.25 | 23.01.25 | Done | Suraja Ram
124 | 5 |  | 65/8 | DA+0 |  | 23.01.25 | 23.01.25 | Done | Suraja Ram
125 | 6 |  | 73/3 | DA+0 |  | 28.01.25 | 28.01.25 | Done | Suraja Ram
126 | 7 |  | 73/4 | DA+0 |  | 29.01.25 | 29.01.25 | Done | Suraja Ram
Feb'25
127 | 1 |  | 73/5 | DA+0 |  | 15.02.25 | 15.02.25 | Done | Suraja Ram
128 | 2 |  | 65/10 | DA+0 |  | 17.02.25 | 17.02.25 | Done | Suraja Ram
129 | 3 |  | 66/0 | DC2+6 |  | 19.02.25 | 19.02.25 | Done | Suraja Ram
130 | 4 |  | 51/0 | DC2+0 |  | 26.02.25 | 26.02.25 | Done | Suraja Ram
131 | 5 |  | 74/0 | DB+0 |  | 14.02.25 | 14.02.25 | Done | Suraja Ram
132 | 6 |  | 73/7 | DA+0 |  | 13.02.25 | 13.02.25 | Done | Suraja Ram
Mar'25
133 | 1 |  | 52/0 |  |  | 05.03.25 | 05.03.25 | Done | Suraja Ram
134 | 2 |  | 49/0 |  |  | 10.03.25 | 10.03.25 | Done | Suraja Ram
135 | 5 |  | 52/10 |  |  | 12.03.25 | 12.03.25 | Done | Suraja Ram
136 | 6 |  | 73/0 |  |  | 13.03.25 | 13.03.25 | Done | Suraja Ram
137 | 7 |  | 52/5 |  |  | 17.3.25 | 17.3.25 | Done | Suraja Ram
138 | 4 |  | 52/9 |  |  | 11.03.25 | 11.03.25 | Done | Suraja Ram
139 | 5 |  | 50/5 |  |  | 02.03.25 | 02.03.25 | Done | Suraja Ram

## Eretion - PKG-G (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Erection
Cum Sl. No. | Month Sl. No. | JMC No. | Location No. | Tower Type | Depth of Fdn | Dt. of Start | Dt. of Complete | Name of Sub-Contractor | Ramarks
2023-09-01
1 | 1 |  | 57/9 | DA+0 |  | 13.09.23 | 21.09.23 | Sobha Devi | Complete | 37.504
2 | 2 |  | 58/12 | DA+0 |  | 18.09.23 | 25.09.23 | Sunny Const | Complete | 37.504
3 | 3 |  | 57/11 | DA+0 |  | 21.09.23 | 26.09.23 | Sobha Devi | Complete | 37.504
| 2023-10-01 | [9 empty] | 112.512
4 | 1 |  | 58/14 | DA+0 |  | 25.09.23 | 01.10.23 | Sunny Const | Complete | 37.504
5 | 2 |  | 57/13 | DA+0 |  | 26.09.23 | 01.10.23 | Sobha Devi | Complete | 37.504
6 | 3 |  | 57/10 | DA+0 |  | 01.10.23 | 06.10.23 | Sobha Devi | Complete | 37.504
7 | 4 |  | 58/9 | DA+0 |  | 01.10.23 | 07.10.23 | Sunny Const | Complete | 37.504
8 | 5 |  | 52/1 | DA+0 |  | 03.10.23 | 10.10.23 | Suraj const | Complete | 37.504
9 | 6 |  | 57/12 | DA+3 |  | 06.10.23 | 11.10.23 | Sobha Devi | Complete | 38.847
10 | 7 |  | 58/8 | DA+0 |  | 7.10.23 | 11.10.23 | Sunny Const | Complete | 37.504
11 | 8 |  | 58/1 | DA+0 |  | 25.09.23 | 12.10.23 | Ganesh Const. | Complete | 37.504
12 | 9 |  | 57/2 | DA+0 |  | 10.10.23 | 16.10.23 | Sobha Devi | Complete | 37.504
13 | 10 |  | 51/2 | DA+0 |  | 10.10.23 | 15.10.23 | Suraj const | Complete | 37.504
14 | 11 |  | 58/16 | DA+0 |  | 10.10.23 | 17.10.23 | Sunny Const | Complete | 37.504
15 | 12 |  | 57/3 | DA+0 |  | 15.10.23 | 20.10.23 | Sobha Devi | Complete | 37.504
16 | 13 |  | 51/4 | DA+3 |  | 15.10.23 | 21.10.23 | Suraj const | Complete | 38.847
17 | 14 |  | 58/3 | DA+3 |  | 12.10.23 | 22.10.23 | Ganesh Const. | Complete | 38.847
18 | 15 |  | 58/10 | DA+3 |  | 17.10.23 | 23.10.23 | Sunny Const | Complete | 38.847
19 | 16 |  | 57/4 | DA+0 |  | 20.10.23 | 26.10.23 | Sobha Devi | Complete | 37.504
20 | 17 |  | 51/5 | DA+0 |  | 20.10.23 | 29.10.23 | Suraj const | Complete | 37.504
21 | 18 |  | 57/5 | DA+3 |  | 26.10.23 | 30.10.23 | Sobha Devi | Complete | 38.847
22 | 19 |  | 58/5 | DA+3 |  | 20.10.23 | 31.10.23 | Ganesh Const. | Complete | 38.847
23 | 20 |  | 58/11 | DA+3 |  | 23.10.23 | 31.10.23 | Sunny Const | Complete | 38.847
| 2023-11-01 | [9 empty] | 759.481
24 | 1 |  | 57/8 | DA+3 |  | 30.10.23 | 03.11.2023 | Sobha Devi | Complete | 38.847
25 | 2 |  | 51/7 | DA+3 |  | 29.10.23 | 04.11.2023 | Suraj const | Complete | 38.847
26 | 3 |  | 59/6 | DA+0 |  | 31.10.23 | 07.11.2023 | Sunny Const | Complete | 37.504
27 | 4 |  | 57/7 | DA+3 |  | 03.11.23 | 07.11.2023 | Sobha Devi | Complete | 38.847
28 | 5 |  | 51/3 | DA+0 |  | 04.11.23 | 09.11.2023 | Suraj const | Complete | 37.504
29 | 6 |  | 58/4 | DA+0 |  | 31.10.23 | 11.11.2023 | Ganesh Const. | Complete | 37.504
30 | 7 |  | 57/1 | DA+3 |  | 07.11.23 | 13.11.2023 | Sobha Devi | Complete | 38.847
31 | 8 |  | 59/5 | DA+0 |  | 07.11.23 | 13.11.2023 | Sunny Const | Complete | 37.504
32 | 9 |  | 51/10 | DA+3 |  | 10.11.23 | 14.11.2023 | Suraj const | Complete | 38.847
33 | 10 |  | 56/9 | DA+3 |  | 13.11.23 | 16.11.2023 | Sobha Devi | Complete | 38.847
34 | 11 |  | 59/3 | DA+0 |  | 13.11.23 | 18.11.2023 | Sunny Const | Complete | 37.504
35 | 12 |  | 52/2 | DA+3 |  | 15.11.23 | 19.11.2023 | Suraj const | Complete | 38.847
36 | 13 |  | 55/7 | DA+0 |  | 15.11.23 | 21.11.2023 | Chinta devi | Complete | 37.504
37 | 14 |  | 58/6 | DA+3 |  | 13.11.23 | 21.11.2023 | Ganesh Const. | Complete | 38.847
38 | 15 |  | 56/8 | DA+3 |  | 16.11.23 | 21.11.2023 | Sobha Devi | Complete | 38.847
39 | 16 |  | 59/2 | DA+0 |  | 18.11.23 | 24.11.2023 | Sunny Const | Complete | 37.504
40 | 17 |  | 52/5 | DA+3 |  | 19.11.23 | 24.11.2023 | Suraj const | Complete | 38.847
41 | 18 |  | 56/7 | DA+3 |  | 22.11.23 | 24.11.2023 | Sobha Devi | Complete | 38.847
42 | 19 |  | 55/5 | DA+0 |  | 22.11.23 | 26.11.2023 | Chinta devi | Complete | 37.504
43 | 20 |  | 56/3 | DA+0 |  | 24.11.23 | 29.11.23 | Sobha Devi | Complete | 37.504
44 | 21 |  | 53/3 | DA+3 |  | 24.11.23 | 29.11.23 | Suraj const | Complete | 38.847
45 | 22 |  | 59/1 | DA+0 |  | 24.11.23 | 30.11.23 | Sunny Const | Complete | 37.504
| 2023-12-01 | [9 empty] | 841.204
46 | 1 |  | 50/4 | DA+3 |  | 22.11.23 | 01.12.23 | Ganesh Const. | Complete | 38.847
47 | 2 |  | 55/4 | DA+3 |  | 27.11.23 | 02.12.23 | Chinta devi | Complete | 38.847
48 | 3 |  | 56/4 | DA+3 |  | 29.11.23 | 02.12.23 | Sobha Devi | Complete | 38.847
49 | 4 |  | 53/4 | DA+3 |  | 29.11.23 | 03.12.23 | Suraj const | Complete | 38.847
50 | 5 |  | 58/15 | DA+3 |  | 30.11.23 | 06.12.23 | Sunny Const | Complete | 38.847
51 | 6 |  | 56/2 | DA+3 |  | 02.12.23 | 06.12.23 | Sobha Devi | Complete | 38.847
52 | 7 |  | 55/6 | DA+3 |  | 02.12.23 | 07.12.23 | Chinta devi | Complete | 38.847
53 | 8 |  | 48/1 | DA+0 |  | 02.12.23 | 09.12.23 | Ganesh Const. | Complete | 37.504
54 | 9 |  | 55/1 | DA+3 |  | 03.12.23 | 09.12.23 | Suraj const | Complete | 38.847
55 | 10 |  | 55/9 | DA+3 |  | 07.12.23 | 12.12.23 | Chinta devi | Complete | 38.847
56 | 11 |  | 57/6 | DB+0 |  | 06.12.23 | 13.12.23 | Sobha Devi | Complete | 57.597
57 | 12 |  | 61/2 | DA+0 |  | 06.12.23 | 14.12.23 | Sunny Const | Complete | 37.504
58 | 13 |  | 55/2 | DA+3 |  | 09.12.23 | 15.12.23 | Suraj const | Complete | 38.847
59 | 14 |  | 48/2 | DA+3 |  | 09.12.23 | 16.12.23 | Ganesh Const. | Complete | 38.847
60 | 15 |  | 55/10 | DA+3 |  | 12.12.23 | 17.12.23 | Chinta devi | Complete | 38.847
61 | 16 |  | 57/0 | DB+0 |  | 13.12.23 | 19.12.23 | Sobha Devi | Complete | 57.597
62 | 17 |  | 55/3 | DA+0 |  | 16.12.23 | 19.12.23 | Suraj const | Complete | 37.504
63 | 18 |  | 61/1 | DA+0 |  | 14.12.23 | 20.12.23 | Sunny Const | Complete | 37.504
64 | 19 |  | 50/3 | DA+0 |  | 16.12.23 | 22.12.23 | Ganesh Const. | Complete | 37.504
65 | 20 |  | 55/11 | DA+3 |  | 17.12.23 | 22.12.23 | Chinta devi | Complete | 38.847
66 | 21 |  | 56/5 | DA+0 |  | 20.12.23 | 24.12.23 | Sobha Devi | Complete | 37.504
67 | 22 |  | 52/4 | DA+0 |  | 20.12.23 | 24.12.23 | Suraj const | Complete | 37.504
68 | 23 |  | 55/8 | DA+3 |  | 22.12.23 | 28.12.23 | Chinta devi | Complete | 38.847
69 | 24 |  | 56/6 | DA+3 |  | 24.12.23 | 28.12.23 | Sobha Devi | Complete | 38.847
70 | 25 |  | 59/0 | DB+0 |  | 07.12.23 | 29.12.23 | Sunny Const | Complete | 57.597
71 | 26 |  | 47/3 | DA+0 |  | 22.12.23 | 29.12.23 | Ganesh Const. | Complete | 37.504
72 | 27 |  | 51/9 | DA+3 |  | 24.12.23 | 29.12.23 | Suraj const | Complete | 38.847
| 2024-01-01 | [9 empty] | 1094.375
73 | 1 |  | 56/0 | DB+0 |  | 28.12.23 | 05.01.24 | Sobha Devi | Complete | 57.597
74 | 2 |  | 44/2 | DA+0 |  | 28.12.23 | 05.01.24 | Chinta devi | Complete | 37.504
75 | 3 |  | 51/8 | DA+3 |  | 29.12.23 | 06.01.24 | Suraj const | Complete | 38.847
76 | 4 |  | 47/2 | DA+0 |  | 29.12.23 | 07.01.24 | Ganesh Const. | Complete | 37.504
77 | 5 |  | 58/7 | DB+0 |  | 29.12.23 | 09.01.24 | Sunny Const | Complete | 57.597
78 | 6 |  | 44/4 | DA+0 |  | 05.01.24 | 09.01.24 | Chinta devi | Complete | 37.504
79 | 7 |  | 53/2 | DA+3 |  | 06.01.24 | 11.01.24 | Suraj const | Complete | 38.847
80 | 8 |  | 41/11 | DA+3 |  | 05.01.24 | 12.01.24 | Sobha Devi | Complete | 38.847
81 | 9 |  | 44/3 | DA+3 |  | 09.01.24 | 15.01.24 | Chinta devi | Complete | 38.847
82 | 10 |  | 41/10 | DA+3 |  | 12.10.23 | 16.01.24 | Sobha Devi | Complete | 38.847
83 | 11 |  | 48/0 | DB+0 |  | 07.01.24 | 19.01.24 | Ganesh Const. | Complete | 57.597
84 | 12 |  | 46/3 | DA+0 |  | 12.01.24 | 19.01.24 | Sunny Const | Complete | 37.504
85 | 13 |  | 51/6 | DA+0 |  | 12.01.24 | 19.01.24 | Suraj const | Complete | 37.504
86 | 14 |  | 41/7 | DA+3 |  | 16.01.24 | 20.01.24 | Sobha Devi | Complete | 38.847
87 | 15 |  | 43/4 | DA+9 |  | 15.01.24 | 22.01.24 | Chinta devi | Complete | 47.148
88 | 16 |  | 43/5 | DA+0 |  | 22.1.24 | 27.01.24 | Chinta devi | Complete | 37.504
89 | 17 |  | 47/0 | DB+0 |  | 20.01.24 | 28.01.24 | Sunny Const | Complete | 57.597
90 | 18 |  | 51/0 | DB+0 |  | 20.01.24 | 28.01.24 | Ganesh Const. | Complete | 57.597
91 | 19 |  | 52/0 | DB+0 |  | 20.01.24 | 28.01.24 | Suraj const | Complete | 57.597
92 | 20 |  | 43/1 | DA+9 |  | 23.01.24 | 28.01.24 | Sobha Devi | Complete | 47.148
93 | 21 |  | 41/5 | DA+0 |  | 28.01.24 | 31.01.24 | Sobha Devi | Bottom complete | 37.504
| Feb-24 | [9 empty] | 935.488
94 | 1 |  | 44/1 | DA+0 |  | 28.01.24 | 01.02.24 | Chinta devi | Complete | 37.504
95 | 2 |  | 46/2 | DA+0 |  | 28.01.24 | 02.02.24 | Sunny Const | Complete | 37.504
96 | 3 |  | 51/1 | DA+0 |  | 28.01.24 | 04.02.24 | Ganesh Const. | Complete | 37.504
97 | 4 |  | 41/4 | DA+0 |  | 01.02.24 | 05.02.24 | Sobha Devi | Complete | 37.504
98 | 5 |  | 53/1 | DA+0 |  | 04.02.24 | 09.02.24 | Suraj const | Complete | 37.504
99 | 6 |  | 41/6 | DA+0 |  | 07.02.24 | 09.02.24 | Sobha Devi | Complete | 37.504
100 | 7 |  | 41/8 | DA+0 |  | 09.02.24 | 13.02.24 | Sobha Devi | Complete | 37.504
101 | 8 |  | 41/9 | DA+0 |  | 13.02.24 | 17.02.24 | Sobha Devi | Complete | 37.504
| April'24 | [9 empty] | 300.032
102 | 1 |  | 55/0 | DC+0 |  | 28.03.24 | 04.04.24 | Sobha Devi | Complete | 66.381
103 | 2 |  | 58/0 | DC2+0 |  | 08.04.24 | 16.04.24 | Sunny Const | Complete | 66.381
104 | 3 |  | 56/1 | DA+3 |  | 12.04.24 | 16.04.24 | Sobha Devi | Complete | 38.847
105 | 4 |  | 53/0 | DC2+3 |  | 08.04.24 | 18.04.24 | Ganesh Const. | Complete | 69.229
| May'24 | [9 empty] | 240.838
106 | 1 |  | 52/3 | DA+0 |  | 26.04.24 | 05.05.24 | Ganesh Const. | Complete | 37.504
107 | 2 |  | 58/2 | DA+0 |  | 05.05.24 | 10.05.24 | Sunny Const | Complete | 37.504
108 | 3 |  | 65/4 | DA+0 |  | 10.05.24 | 16.05.24 | Sunny Const | Complete | 37.504
109 | 4 |  | 65/3 | DA+0 |  | 16.05.24 | 21.05.24 | Sunny Const | Complete | 37.504
110 | 5 |  | 65/5 | DA+0 |  | 16.05.24 | 26.05.24 | Sunny Const | Complete | 37.504
| Aug'24 | [9 empty] | 187.52
111 | 1 |  | 46/4 | DA+0 |  | 27.08.24 | 30.08.24 | Sobha devi | Complete | 37.504
Sept'24
112 | 1 |  | 72/3 | DA+0 |  | 25.08.24 | 01.09.24 | Sunny Const | Complete | 37.504
113 | 2 |  | 72/4 | DA+0 |  | 01.09.24 | 06.09.24 | Sunny Const | Complete | 37.504
114 | 3 |  | 71/5 | DA+0 |  | 28.08.24 | 06.09.24 | Chinta Devi | Complete | 37.504
115 | 4 |  | 72/5 | DA+0 |  | 01.09.24 | 11.09.24 | Sunny Const | Complete | 37.504
116 | 5 |  | 47/1 | DA+0 |  | 09.09.24 | 12.09.24 | Sobha devi | Complete | 37.504
117 | 6 |  | 72/6 | DA+0 |  | 11.09.24 | 15.09.24 | Sunny Const | Complete | 37.504
118 | 7 |  | 72/0 | DB1+0 |  | 06.09.24 | 16.09.24 | Chinta Devi | Complete | 57.597
119 | 8 |  | 50/2 | DA+0 |  | 12.09.24 | 16.09.24 | Sobha devi | Complete | 37.504
120 | 9 |  | 50/1 | DA+0 |  | 16.09.24 | 20.09.24 | Sobha devi | Complete | 37.504
121 | 10 |  | 71/4 | DA+0 |  | 16.09.24 | 22.09.24 | Chinta Devi | Complete | 37.504
122 | 11 |  | 72/7 | DB1+9 |  | 15.09.24 | 25.09.24 | Sunny Const | Complete | 70.701
123 | 12 |  | 43/6 | DA+6 |  | 09.09.24 | 26.09.24 | Jirwa Devi | Complete | 45.413
124 | 13 |  | 50/0 | DC+3 |  | 20.09.24 | 26.09.24 | Sobha devi | Complete | 69.229
125 | 14 |  | 71/2 | DA+0 |  | 22.09.24 | 26.09.24 | Chinta Devi | Complete | 37.504
126 | 15 |  | 72/2 | DA+0 |  | 25.09.24 | 29.09.24 | Sunny Const | Complete | 37.504
| Oct'24 | [9 empty] | 655.484
127 | 1 |  | 71/1 | DA+0 |  | 26.09.24 | 01.10.24 | Chinta Devi | Complete | 37.504
128 | 2 |  | 72/1 | DA+0 |  | 29.09.24 | 03.10.24 | Sunny Const | Complete | 37.504
129 | 3 |  | 68/1 | DA+3 |  | 2.10.24 | 05.10.24 | Chinta Devi | Complete | 38.847
130 | 4 |  | 43/3 | DA+3 |  | 27.09.24 | 08.10.24 | Jirwa Devi | Complete | 38.847
131 | 5 |  | 68/2 | DA+3 |  | 05.10.24 | 10.10.24 | Chinta Devi | Complete | 38.847
132 | 6 |  | 66/2 | DA+0 |  | 30.09.24 | 10.10.24 | Sanjeev Kumar | Complete | 37.504
133 | 7 |  | 73/0 | DD45+9 |  | 03.10.24 | 17.10.24 | Sunny Const | Complete | 105.068
134 | 8 |  | 67/1 | DB1+9 |  | 10.10.24 | 19.10.24 | Chinta devi | Complete | 70.701
135 | 9 |  | 43/2 | DA+9 |  | 08.10.24 | 22.10.24 | Jirwa Devi | Complete | 47.148
136 | 10 |  | 71/3 | DA+0 |  | 18.10.24 | 23.10.24 | Sunny Const | Complete | 37.504 |  | 202
137 | 11 |  | 69/6 | DA+0 |  | 23.10.24 | 27.10.24 | Sunny Const | Complete | 37.504 |  | 9090
138 | 12 |  | 68/3 | DA+0 |  | 24.10.24 | 28.10.24 | Chinta devi | Complete | 37.504
139 | 13 |  | 40/11 | DA+9 |  | 23.10.24 | 30.10.24 | Ganesh Sinha | Complete | 47.148
140 | 14 |  | 69/7 | DA+0 |  | 27.10.24 | 31.10.24 | Sunny Const | Complete | 37.504
| Nov'24 | [9 empty] | 649.134
141 | 1 |  | 68/5 | DA+3 |  | 28.09.24 | 01.11.24 | Chinta devi | Complete | 38.847
142 | 2 |  | 68/6 | DA+3 |  | 01.11.24 | 05.11.24 | Chinta devi | Complete | 38.847
143 | 3 |  | 69/5 | DA+0 |  | 01.11.24 | 05.11.24 | Sunny Const | Complete | 37.504
144 | 4 |  | 68/4 | DA+3 |  | 05.11.24 | 09.11.24 | Chinta devi | Complete | 38.847
145 | 5 |  | 69/4 | DA+0 |  | 05.11.24 | 09.11.24 | Sunny Const | Complete | 37.504
146 | 6 |  | 40/10 | DB1+6 |  | 30.10.24 | 11.11.24 | Ganesh Sinha | Complete | 67.873
147 | 7 |  | 69/3 | DA+0 |  | 09.11.24 | 13.11.24 | Sunny Const | Complete | 37.504
148 | 8 |  | 66/4 | DA+3 |  | 29.10.24 | 14.11.24 | Sanjeev Kumar | Complete | 38.847
149 | 9 |  | 69/2 | DA+0 |  | 13.11.24 | 17.11.24 | Sunny Const | Complete | 37.504 |  | 840
150 | 10 |  | 69/1 | DA+0 |  | 18.11.24 | 22.11.24 | Sunny Const | Complete | 37.504 |  | 840
151 | 11 |  | 68/0 | DD45+0 |  | 22.11.24 | 29.11.24 | Chinta devi | Complete | 86.129 |  | 840
152 | 12 |  | 69/0 | DB1+0 |  | 23.11.24 | 30.11.24 | Sunny Const | Complete | 57.597 |  | 840
| Dec'24 | [9 empty] | 554.507 | 700
153 | 1 |  | 69/9 | DA+0 |  | 01.12.24 | 06.12.24 | Sunny Const | Complete | 37.504 |  | 840
154 | 2 |  | 67/0 | DD45+0 |  | 01.12.24 | 08.12.24 | Chinta devi | Complete | 86.129 |  | 4900
155 | 3 |  | 66/1 | DA+3 |  | 02.12.24 | 08.12.24 | Sanjeev Kumar | Complete | 38.847
156 | 4 |  | 38/3 | DA+9 |  | 10.12.24 | 15.12.24 | Sobha Devi | Complete | 47.148
157 | 5 |  | 41/12 | DA+3 |  | 09.12.24 | 17.12.24 | Ganesh Sinha | Complete | 38.847
158 | 6 |  | 71/0 | DD+0 |  | 07.12.24 | 17.12.24 | Sunny Const | Complete | 86.129
159 | 7 |  | 65/6 | DA+0 |  | 14.12.24 | 18.12.24 | Chinta devi | Complete | 37.504
160 | 8 |  | 58/13 | DA+0 |  | 11.12.24 | 19.12.24 | Sanjeev Kumar | Complete | 37.504
161 | 9 |  | 38/2 | DA+6 |  | 15.12.24 | 19.12.24 | Sobha Devi | Complete | 45.413
162 | 10 |  | 69/8 | DA+0 |  | 18.12.24 | 22.12.24 | Sunny Const | Complete | 37.504
163 | 11 |  | 65/7 | DA+0 |  | 18.12.24 | 22.12.24 | Chinta devi | Complete | 37.504
164 | 12 |  | 38/1 | DA+3 |  | 20.12.24 | 24.12.24 | Sobha Devi | Complete | 38.847
165 | 13 |  | 37/3 | DA+0 |  | 25.12.24 | 28.12.24 | Sobha Devi | Complete | 37.504
166 | 14 |  | 41/2 | DA+0 |  | 21.12.24 | 28.12.24 | Jirwa Devi | Complete | 37.504
167 | 15 |  | 70/0 | DD60+0 |  | 22.12.24 | 31.12.24 | Sunny Const | Complete | 86.129
168 | 16 |  | 42/0 | DC2+9 |  | 19.12.24 | 31.12.24 | Ganesh Sinha | Complete | 81.945
169 | 17 |  | 66/0 | DD45+0 |  | 22.12.24 | 31.12.24 | Chinta devi | Complete | 86.129
| Jan'25 | [9 empty] | 898.091
170 | 1 |  | 37/4 | DA+6 |  | 29.12.24 | 03.01.25 | Sobha Devi | Complete | 45.413
171 | 2 |  | 41/3 | DA+0 |  | 29.12.24 | 07.01.25 | Jirwa Devi | Complete | 37.504
172 | 3 |  | 59/4 | DA+0 |  | 06.01.25 | 10.01.25 | Sanjeev Kumar | Complete | 37.504
173 | 4 |  | 37/2 | DB1+6 |  | 04.01.25 | 10.01.25 | Sobha Devi | Complete | 67.873
174 | 5 |  | 37/5 | DA+3 |  | 10.01.25 | 16.01.25 | Sobha Devi | Complete | 38.847
175 | 6 |  | 41/1 | DA+3 |  | 10.01.25 | 17.01.25 | Jirwa Devi | Complete | 38.847 | 8
176 | 7 |  | 37/6 | DA+6 |  | 16.01.25 | 20.01.25 | Sobha Devi | Complete | 45.413
177 | 8 |  | 37/7 | DA+3 |  | 20.01.25 | 24.01.25 | Sobha Devi | Complete | 38.847
178 | 9 |  | 39/1 | DA+6 |  | 19.01.25 | 28.01.25 | Om Construction | Complete | 45.413
179 | 10 |  | 37/8 | DA+0 |  | 25.01.25 | 28.01.25 | Sobha Devi | Complete | 37.504
180 | 11 |  | 41/0 | DB1+0 |  | 18.01.25 | 29.01.25 | Jirwa Devi | Complete | 57.597
181 | 12 |  | 40/2 | DB1+9 |  | 10.01.25 | 30.01.25 | Sunny Const | Complete | 70.701
| Feb'25 | [9 empty] | 561.463
182 | 1 | -180 | 38/0 | DC1+0 |  | 29.01.25 | 04.02.25 | Sobha Devi | Complete | 66.381
183 | 2 | -179 | 40/12 | DA+0 |  | 29.01.25 | 08.02.25 | Jirwa Devi | Complete | 37.504
184 | 3 | -178 | 43/0 | DB1+9 |  | 31.01.25 | 18.02.25 | Ganesh Sinha | Complete | 70.701
185 | 4 |  | 60/0 | DC2+3 |  | 07.02.25 | 19.02.25 | Sanjeev kumar | Complete | 69.229
186 | 5 |  | 40/6 | DA+3 |  | 15.02.25 | 20.02.25 | Sunny Const. | Complete | 38.847
187 | 6 |  | 49/0 | DC1+3 |  | 09.02.25 | 23.02.25 | Jirwa Devi | Complete | 69.229
188 | 7 |  | 40/7 | DA+3 |  | 21.02.25 | 26.02.25 | Sunny Const. | Complete | 38.847
189 | 8 |  | 44/0 | DB1+0 |  | 19.02.25 | 28.02.25 | Ganesh Sinha | Complete | 57.597
190 | 9 |  | 39/0 | DC2+3 |  | 21.02.25 | 28.02.25 | Sobha Devi | Complete | 69.229
| Mar'25 | [9 empty] | 517.564
191 | 1 |  | 61/0 | DB1+6 |  | 20.01.25 |  | Sanjeev kumar | Complete | 67.873
192 | 2 |  | 40/0 | DC2+0 |  | 27.02.25 | 06.03.25 | Sunny Const. | Complete | 66.381
193 | 3 |  | 38/9 | DB1+6 |  | 01.03.25 | 07.03.25 | Sobha Devi | Complete | 67.873
194 | 4 |  | 38/8 | DA+0 |  | 08.03.25 | 11.03.25 | Sobha Devi | Complete | 37.504
195 | 5 |  | 40/1 | DA+0 |  | 08.03.25 | 12.03.25 | Sunny Const. | Complete | 37.504
196 | 6 |  | 38/7 | DA+0 |  | 13.03.25 | 17.03.25 | Sobha Devi | Complete | 37.504
197 | 7 |  | 40/4 | DA+9 |  | 13.03.25 |  | Sunny Const. | Complete | 47.148
198 | 8 |  | 38/6 | DA+0 |  | 18.03.25 | 21.03.25 | Sobha Devi | Complete | 37.504
199 | 9 |  | 38/5 | DA+0 |  | 22.03.25 | 25.03.25 | Sobha Devi | Complete | 37.504 | 436.795
200 | 10 |  | 40/5 | DB1+9 |  | 21.03.25 | 28.03.25 | Sunny Const. | Complete | 70.701
201 | 11 |  | 38/4 | DA+0 |  | 26.03.25 | 29.03.25 | Sobha Devi | Complete | 37.504
April'25
202 | 1 |  | 66/3 | DA+3 |  | 19.01.25 |  | Chinta devi | Work Hold due to unavailabilty of 33kv Shutdown
203 | 2 |  | 64/9 | DA+0 |  |  |  | Sunny Const. | ROW since 02.04.25 | 37.504

## Eretion - PKG-F (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Erection PKG-F
Cum Sl. No. | Month Sl. No. | JMC No. | Location No. | Tower Type | Depth of Fdn | Dt. of Start | Dt. of Complete | Name of Sub-Contractor | Ramarks
Feb-24
1 | 1 |  | 60/7 | DA+3 |  | 28.1.24 | 04.02.24 | Suraj const | Complete |  |  |  | 38.847
2 | 2 |  | 59/13 | DA+3 |  | 01.02.24 | 07.02.24 | Chinta Devi | Complete |  |  |  | 38.847
3 | 3 |  | 63/6 | DA+3 |  | 03.02.24 | 10.02.24 | Sunny Const. | Complete |  |  |  | 38.847
4 | 4 |  | 59/5 | DA+3 |  | 05.02.24 | 11.02.24 | Ganesh Const | Complete |  |  |  | 38.847
5 | 5 |  | 59/14 | DA+6 |  | 08.02.24 | 13.02.24 | Chinta Devi | Complete |  |  |  | 45.413
6 | 6 |  | 60/8 | DA+0 |  | 09.02.24 | 15.02.24 | Suraj const | Complete |  |  |  | 37.504
7 | 7 |  | 63/7 | DA+3 |  | 11.02.24 | 15.02.24 | Sunny Const. | Complete |  |  |  | 38.847
8 | 8 |  | 59/6 | DA+3 |  | 12.02.24 | 18.02.24 | Ganesh Const | Complete |  |  |  | 38.847
9 | 9 |  | 59/12 | DA+6 |  | 13.02.24 | 20.02.24 | Chinta Devi | Complete |  |  |  | 45.413
10 | 10 |  | 63/8 | DA+3 |  | 15.02.24 | 20.02.24 | Sunny Const. | Complete |  |  |  | 38.847
11 | 11 |  | 60/10 | DA+0 |  | 15.02.24 | 21.02.24 | Suraj const | Complete |  |  |  | 37.504
12 | 12 |  | 62/5 | DA+0 |  | 17.02.24 | 22.02.24 | Sobha Devi | Complete |  |  |  | 37.504
13 | 13 |  | 59/7 | DA+3 |  | 18.02.24 | 24.02.24 | Ganesh Const | Complete |  |  |  | 38.847
14 | 14 |  | 59/10 | DA+0 |  | 20.02.24 | 24.02.24 | Chinta Devi | Complete |  |  |  | 37.504
15 | 15 |  | 64/1 | DA+0 |  | 20.02.24 | 24.02.24 | Sunny Const. | Complete |  |  |  | 37.504
16 | 16 |  | 60/11 | DA+3 |  | 21.02.24 | 26.02.24 | Suraj const | Complete |  |  |  | 38.847
17 | 17 |  | 62/4 | DA+3 |  | 22.02.24 | 26.02.24 | Sobha Devi | Complete |  |  |  | 38.847
18 | 18 |  | 59//9 | DA+3 |  | 24.02.24 | 28.02.24 | Chinta Devi | Complete |  |  |  | 38.847
19 | 19 |  | 62/3 | DA+0 |  | 26.02.24 | 28.02.24 | Sobha Devi | Complete |  |  |  | 37.504
20 | 20 |  | 59/8 | DB1+3 |  | 24.02.24 | 29.02.24 | Ganesh Const | Complete |  |  |  | 60.097
21 | 21 |  | 64/4 | DA+3 |  | 24.02.24 | 29.02.24 | Sunny Const. | Complete |  |  |  | 38.847
22 | 22 |  | 60/6 | DA+0 |  | 26.02.24 | 29.02.24 | Suraj const | Complete |  |  |  | 37.504
| March'24 | [12 empty] | 879.615
23 | 1 |  | 62/2 | DA+3 |  | 29.02.24 | 03.03.24 | Sobha Devi | Complete |  |  |  | 38.847
24 | 2 |  | 64/5 | DA+3 |  | 29.02.24 | 04.03.24 | Sunny Const. | Complete |  |  |  | 38.847
25 | 3 |  | 65/2 | DA+0 |  | 29.02.24 | 06.03.24 | Chinta Devi | Complete |  |  |  | 37.504
26 | 4 |  | 62/7 | DA+3 |  | 04.03.24 | 07.03.24 | Sobha Devi | Complete |  |  |  | 38.847
27 | 5 |  | 59/16 | DA+9 |  | 29.02.24 | 11.03.24 | Ganesh Const. | Complete |  |  |  | 47.418
28 | 6 |  | 65/4 | DA+0 |  | 06.03.24 | 11.03.24 | Chinta Devi | Complete |  |  |  | 37.504
29 | 7 |  | 62/8 | DA+0 |  | 07.03.24 | 11.03.24 | Sobha Devi | Complete |  |  |  | 37.504
30 | 8 |  | 62/9 | DA+3 |  | 11.03.24 | 15.03.24 | Sobha Devi | Complete |  |  |  | 38.847
31 | 9 |  | 65/3 | DA+3 |  | 11.03.24 | 16.03.24 | Chinta Devi | Complete |  |  |  | 38.847
32 | 10 |  | 60/5 | DA+3 |  | 11.03.24 | 17.03.24 | Ganesh Const. | Complete |  |  |  | 38.847
33 | 11 |  | 62/10 | DA+0 |  | 15.03.24 | 18.03.24 | Sobha Devi | Complete |  |  |  | 37.504
34 | 12 |  | 65/5 | DA+0 |  | 16.03.24 | 20.03.24 | Chinta Devi | Complete |  |  |  | 37.504
35 | 13 |  | 61/6 | DA+3 |  | 18.03.24 | 22.03.24 | Sobha Devi | Complete |  |  |  | 38.847
36 | 14 |  | 60/4 | DA+3 |  | 18.03.24 | 23.03.24 | Ganesh Const. | Complete |  |  |  | 38.847
37 | 15 |  | 65/6 | DA+0 |  | 20.03.24 | 26.03.24 | Chinta Devi | Complete |  |  |  | 37.504
38 | 16 |  | 64/6 | DA+0 |  | 21.03.24 | 26.03.24 | Sunny Const. | Complete |  |  |  | 37.504
39 | 17 |  | 61/7 | DA+9 |  | 22.03.24 | 28.03.24 | Sobha Devi | Complete |  |  |  | 47.418
40 | 18 |  | 64/7 | DA+3 |  | 26.03.24 | 30.03.24 | Sunny Const. | Complete |  |  |  | 38.847
41 | 19 |  | 60/3 | DA+3 |  | 23.03.24 | 31.03.24 | Ganesh Const. | Complete |  |  |  | 38.847
42 | 20 |  | 65/9 | DA+0 |  | 26.03.24 | 31.03.24 | Chinta Devi | Complete |  |  |  | 37.504
| Apr-'24 | [12 empty] | 783.338
43 | 1 |  | 64/8 | DA+3 |  | 30.03.24 | 03.04.24 | Sunny Const. | Complete |  |  |  | 38.847
44 | 2 |  | 65/11 | DA+0 |  | 31.03.24 | 04.04.24 | Chinta Devi | Complete |  |  |  | 37.504
45 | 3 |  | 60/2 | DA+3 |  | 31.03.24 | 07.04.24 | Ganesh Const. | Complete |  |  |  | 38.847
46 | 4 |  | 63/5 | DA+3 |  | 01.04.24 | 07.04.24 | Suraj Const | Complete |  |  |  | 38.847
47 | 5 |  | 64/9 | DA+3 |  | 03.04.24 | 08.04.24 | Sunny Const. | Complete |  |  |  | 38.847
48 | 6 |  | 67/1 | DA+0 |  | 06.04.24 | 10.04.24 | Chinta Devi | Complete |  |  |  | 37.504
49 | 7 |  | 61/0 | DB+0 |  | 06.04.24 | 11.04.24 | Sobha Devi | Complete |  |  |  | 57.598
50 | 8 |  | 63/4 | DA+0 |  | 07.04.24 | 13.04.24 | Suraj Const | Complete |  |  |  | 37.504
51 | 9 |  | 67/2 | DA+0 |  | 10.04.24 | 15.04.24 | Chinta Devi | Complete |  |  |  | 37.504
52 | 10 |  | 63/3 | DA+3 |  | 13.04.24 | 17.04.24 | Suraj Const | Complete |  |  |  | 38.847
53 | 11 |  | 64/10 | DA+3 |  | 15.04.24 | 20.04.24 | Chinta Devi | Complete |  |  |  | 38.847
54 | 12 |  | 64/2 | DA+3 |  | 16.04.243 | 21.04.24 | Sunny Const. | Complete |  |  |  | 38.847
55 | 13 |  | 61/2 | DA+6 |  | 16.04.24 | 22.04.24 | Sobha Devi | Complete |  |  |  | 45.413
56 | 14 |  | 63/2 | DA+0 |  | 17.04.24 | 22.04.24 | Suraj const | Complete |  |  |  | 37.504
57 | 15 |  | 60/1 | DA+6 |  | 18.04.24 | 25.04.24 | Ganesh Const. | Complete |  |  |  | 45.413
58 | 16 |  | 64/3 | DA+0 |  | 21.04.24 | 26.04.24 | Sunny Const. | Complete |  |  |  | 37.504
59 | 17 |  | 65/0 | DB1+0 |  | 21.04.24 | 27.04.24 | Chinta Devi | Complete |  |  |  | 57.598
60 | 18 |  | 63/1 | DA+3 |  | 22.04.24 | 27.04.24 | Suraj const | Complete |  |  |  | 38.847
61 | 19 |  | 61/1 | DA+6 |  | 22.04.24 | 29.04.24 | Sobha Devi | Complete |  |  |  | 45.413
| May'24 | [12 empty] | 787.235
62 | 1 |  | 65/1 | DA+0 |  | 27.04.24 | 03.05.24 | Chinta Devi | Complete |  |  |  | 37.504
63 | 2 |  | 62/11 | DA+3 |  | 27.04.24 | 03.05.24 | Suraj const | Complete |  |  |  | 38.847
64 | 3 |  | 64/0 | DB2+0 |  | 27.04.24 | 05.05.24 | Sunny Const. | Complete |  |  |  | 57.598
65 | 4 |  | 60/9 | DA+3 |  | 29.04.24 | 05.05.24 | Sobha Devi | Complete |  |  |  | 38.847
66 | 5 |  | 61/3 | DA+6 |  | 05.05.24 | 11.5.24 | Sobha Devi | Complete |  |  |  | 45.413
67 | 6 |  | 63/0 | DC1+0 |  | 03.05.24 | 12.5.24 | Suraj const | Complete |  |  |  | 66.381
68 | 7 |  | 61/4 | DA+3 |  | 11.5.24 | 16.05.24 | Sobha Devi | Complete |  |  |  | 38.847
69 | 8 |  | 60/0 | DC+0 |  | 05.05.24 | 18.05.24 | Ganesh | Complete |  |  |  | 66.381
70 | 9 |  | 61/10 | DA+9 |  | 12.5.24 | 19.05.24 | Suraj const | Complete |  |  |  | 47.418
71 | 10 |  | 61/5 | DA+3 |  | 16.05.24 | 22.05.24 | Sobha Devi | Complete |  |  |  | 38.847
72 | 11 |  | 61/9 | DA+0 |  | 19.05.24 | 23.05.24 | Suraj const | Complete |  |  |  | 37.504
73 | 12 |  | 59/15 | DA+6 |  | 18.05.24 | 30.05.24 | Ganesh | Complete |  |  |  | 45.413
74 | 13 |  | 61/8 | DA+6 |  | 23.05.24 | 30.05.24 | Suraj const | Complete |  |  |  | 45.413
75 | 14 |  | 55/3 | DA+0 |  | 12.5.24 | 31.05.24 | Mansukh lal | Complete |  |  |  | 37.504
| June'24 | [12 empty] | 641.917
76 | 1 |  | 57/3 | DA+0 |  | 29.05.24 | 11.06.24 | Bhuvneshwar | Complete |  |  |  | 37.504
77 | 2 |  | 55/4 | DA+0 |  | 01.06.24 | 19.06.24 | Mansukh lal | Complete |  |  |  | 37.504
78 | 3 |  | 57/4 | DA+0 |  | 12.06.24 | 27.06.24 | Bhuvneshwar | Complete |  |  |  | 37.504
| July'24 | [12 empty] | 112.512
79 | 1 |  | 62/1 | DA+3 |  | 04.07.24 | 12.07.24 | Bhuvneshwar | Complete |  |  |  | 38.847
80 | 2 |  | 62/6 | DA+3 |  | 15.07.24 | 26.07.24 | Bhuvneshwar | Complete |  |  |  | 38.847
| Aug'24 | [12 empty] | 77.694
81 | 1 |  | 57/6 | DA+3 |  | 13.08.24 | 20.08.24 | Sobha devi | Complete |  |  |  | 38.847
82 | 2 |  | 57/5 | DA+3 |  | 20.08.24 | 26.08.24 | Sobha devi | Complete |  |  |  | 38.847
| Sept'24 | [12 empty] | 77.694
83 | 1 |  | 62/0 | DB2+0 |  | 31.08.24 | 08.09.24 | Sobha devi | Complete |  |  |  | 57.598
84 | 2 |  | 50/9 | DA+0 |  | 28.08.24 | 09.09.24 | Uma const | Complete |  |  |  | 37.504
85 | 3 |  | 52/5 | DA+9 |  | 27.08.24 | 19.09.24 | Ganesh Sinha | Complete |  |  |  | 47.418
86 | 4 |  | 50/10 | DA+0 |  | 10.09.24 | 19.09.24 | Uma const | Complete |  |  |  | 37.504
87 | 5 |  | 48/1 | DA+9 |  | 08.09.24 | 25.09.24 | Kaushalya const | Complete |  |  |  | 47.418
88 | 6 |  | 51/1 | DA+0 |  | 19.09.24 | 26.09.24 | Uma const | Complete |  |  |  | 37.504
89 | 7 |  | 52/6 | DA+6 |  | 19.09.24 | 30.09.24 | Ganesh Sinha | Complete |  |  |  | 45.413
| Oct'24 | [8 empty] | WT | JMC | FTR |  | 310.359
90 | 1 | 1 | 57/7 | DA+3 |  | 27.09.24 | 01.10.24 | Sobha devi | Complete | 38.847 | Received | Done | 38.847
91 | 2 | 2 | 51/2 | DA+0 |  | 26.09.24 | 04.10.24 | Uma const | Complete | 37.504 | Not received | Not checked | 37.504
92 | 3 | 3 | 50/0 | DB2+0 |  | 02.10.24 | 07.10.24 | Sobha devi | Complete | 57.597 | Received | Done | 57.598
93 | 4 |  | 52/7 | DA+3 |  | 01.10.24 | 07.10.24 | Ganesh Sinha | Complete | 38.847 | Not received | Not checked | 38.847
94 | 5 |  | 50/1 | DA+6 |  | 07.10.24 | 15.10.24 | Sobha Devi | Complete | 45.413 | Not received | Done | 45.413
95 | 6 |  | 50/8 | DA+9 |  | 07.10.24 | 16.10.24 | Uma const | Complete | 47.148 | Not received | Not checked | 47.418
96 | 7 |  | 50/3 | DA+6 |  | 13.10.24 | 18.10.24 | Sobha Devi | Complete | 45.413 | Not received | Done | 45.413
97 | 8 |  | 48/0 | DC2+0 |  | 28.09.24 | 19.10.24 | Kaushalya const | Complete | 66.381 | Not received | Not checked | 66.381
98 | 9 |  | 52/8 | DA+6 |  | 08.10.24 | 19.10.24 | Ganesh Sinha | Complete | 45.413 | Not received | Not checked | 45.413
99 | 10 |  | 73/2 | DA+0 |  | 10.10.24 | 20.10.24 | Sanjeev Kumar | Complete | 37.504 | Not received | Not checked | 37.504
100 | 11 |  | 50/2 | DA+9 |  | 18.10.24 | 24.10.24 | Sobha Devi | Complete | 47.148 | Not received | Erection completed on 24.10.24 | 47.418
101 | 12 |  | 64/11 | DA+3 |  | 20.10.24 | 24.10.24 | Chinta devi | Complete |  | Not received | Erection completed on 24.10.24 | 38.847
102 | 13 |  | 59/11 | DA+6 |  | 17.10.24 | 26.10.24 | Uma const | Complete |  |  |  | 45.413
103 | 14 |  | 73/1 | DA+0 |  | 21.10.24 | 29.10.24 | Sanjeev Kumar | Complete |  |  |  | 37.504
104 | 15 |  | 50/4 | DA+9 |  | 24.10.24 | 30.10.24 | Sobha Devi | Complete |  |  |  | 47.418
| Nov'24 | [12 empty] | 676.938
105 | 1 |  | 55/6 | DA+0 |  | 23.10.24 | 01.11.24 | Jirwa Devi | Complete |  |  |  | 37.504
106 | 2 |  | 59/3 | DA+3 |  | 27.10.24 | 02.11.24 | Uma const | Complete |  |  |  | 38.847
107 | 3 |  | 50/7 | DA+0 |  | 01.11.24 | 04.11.24 | Sobha Devi | Complete |  |  |  | 37.504
108 | 4 |  | 59/4 | DA+3 |  | 01.11.24 | 09.11.24 | Uma const | Complete |  |  |  | 38.847
109 | 5 |  | 50/6 | DA+9 |  | 04.11.24 | 10.11.24 | Sobha Devi | Complete |  |  |  | 47.418
110 | 6 |  | 55/5 | DA+0 |  | 01.11.24 | 12.11.24 | Jirwa Devi | Complete |  |  |  | 37.504
111 | 7 |  | 73/9 | DA+0 |  | 09.11.24 | 13.11.24 | Chinta devi | Complete |  |  |  | 37.504
112 | 8 |  | 49/7 | DA+0 |  | 11.11.24 | 14.11.24 | Sobha Devi | Complete |  |  |  | 37.504
113 | 9 |  | 73/8 | DA+3 |  | 13.11.24 | 17.11.24 | Chinta devi | Complete |  |  |  | 38.847
114 | 10 |  | 49/6 | DA+0 |  | 15.11.24 | 18.11.24 | Sobha Devi | Complete |  |  |  | 37.504
115 | 11 |  | 73/6 | DA+0 |  | 17.11.24 | 20.11.24 | Chinta devi | Complete |  |  |  | 37.504
116 | 12 |  | 47/10 | DA+6 |  | 02.11.24 | 22.11.24 | Kaushalya const | Complete |  |  |  | 45.413
117 | 13 |  | 49/4 | DA+3 |  | 18.11.24 | 22.11.24 | Sobha Devi | Complete |  |  |  | 38.847
118 | 14 |  | 59/2 | DA+3 |  | 12.11.24 | 24.11.24 | Jirwa Devi | Complete |  |  |  | 38.847
119 | 15 |  | 52/10 | DA+9 |  | 13.11.24 | 25.11.24 | Ganesh Sinha | Complete |  |  |  | 47.418
120 | 16 |  | 49/5 | DA+3 |  | 23.11.24 | 27.11.24 | Sobha Devi | Complete |  |  |  | 38.847
121 | 17 |  | 49/2 | DA+3 |  | 27.11.24 | 30.11.24 | Sobha Devi | Complete |  |  |  | 38.847
122 | 18 |  | 72/3 | DA+3 |  | 24.11.24 | 30.11.24 | Sanjeev Kumar | Complete |  |  |  | 38.847
| Dec'24 | [12 empty] | 713.553
123 | 1 | -121 | 59/1 | DA+3 |  | 25.11.24 | 03.12.24 | Jirwa Devi | Complete |  |  |  | 38.847
124 | 2 | -120 | 52/9 | DA+3 |  | 26.11.24 | 05.12.24 | Ganesh Sinha | Complete |  |  |  | 38.847
125 | 3 | -119 | 49/3 | DA+3 |  | 02.12.24 | 05.12.24 | Sobha Devi | Complete |  |  |  | 38.847
126 | 4 |  | 49/1 | DA+0 |  | 06.12.24 | 09.12.24 | Sobha Devi | Complete |  |  |  | 37.504
127 | 5 |  | 73/3 | DA+0 |  | 09.12.24 | 13.12.24 | Chinta devi | Complete |  |  |  | 37.504
128 | 6 |  | 59/0 | DC2+0 |  | 03.12.24 | 16.12.24 | Jirwa Devi | Complete |  |  |  | 66.381
129 | 7 |  | 65/8 | DA+0 |  | 20.12.24 | 27.12.24 | Sanjeev Kumar | Complete |  |  |  | 37.504
| Jan'25 | [12 empty] | 295.434
130 | 1 |  | 65/7 | DA+0 |  | 28.12.24 | 04.01.25 | Sanjeev Kumar | Complete |  |  |  | 37.504
131 | 2 |  | 73/0 | DB2+0 |  | 03.01.25 | 09.01.25 | Chinta devi | Complete |  |  |  | 57.598
132 | 3 |  | 53/8 | DA+3 |  | 04.01.25 | 09.01.25 | Ganesh Sinha | Complete |  |  |  | 38.847
133 | 4 |  | 74/0 | DB2+0 |  | 05.01.25 | 13.01.25 | Sunny Const | Complete |  |  |  | 57.598
134 | 5 |  | 73/4 | DA+0 |  | 10.01.25 | 14.01.25 | Chinta devi | Complete |  |  |  | 37.504
135 | 6 |  | 53/7 | DA+3 |  | 10.01.25 | 18.01.25 | Ganesh Sinha | Complete |  |  |  | 38.847
136 | 7 |  | 73/5 | DA+0 |  | 15.01.25 | 19.01.25 | Chinta devi | Complete |  |  |  | 37.504
137 | 8 |  | 73/7 | DA+0 |  | 14.01.25 | 19.01.25 | Sunny Const | Complete |  |  |  | 37.504
138 | 9 |  | 72/0 | DB2+3 |  | 21.01.25 | 27.01.25 | Chinta Devi | Complete |  |  |  | 60.097
139 | 10 |  | 66/0 | DC+6 |  | 11.01.25 | 29.01.25 | Sanjeev Kumar | Complete |  |  |  | 78.132
140 | 11 |  | 53/6 | DA+6 |  | 19.01.25 | 30.01.25 | Ganesh Sinha | Complete |  |  |  | 45.413
| Feb'25 | [12 empty] | 526.548
141 | 1 |  | 72/1 | DA+3 |  | 28.01.25 | 02.02.25 | Chinta Devi | Complete |  |  |  | 38.847
142 | 2 |  | 65/10 | DA+0 |  | 29.01.25 | 06.02.25 | Sanjeev Kumar | Complete |  |  |  | 37.504
143 | 3 |  | 72/2 | DA+0 |  | 02.02.25 | 06.02.25 | Chinta Devi | Complete |  |  |  | 37.504
144 | 4 |  | 51/0 | DC2+0 |  | 31.01.25 | 07.02.25 | Sunny Const. | Complete |  |  |  | 66.381
145 | 5 |  | 71/8 | DA+3 |  | 07.02.25 | 10.02.25 | Chinta Devi | Complete |  |  |  | 38.847
146 | 6 |  | 52/0 | DC2+0 |  | 08.02.25 | 14.02.25 | Sunny Const. | Complete |  |  |  | 66.381
147 | 7 |  | 49/0 | DD45+0 |  | 05.02.25 | 14.02.25 | Sobha Devi | Complete |  |  |  | 86.129
148 | 8 |  | 71/7 | DA+3 |  | 11.02.25 | 15.02.25 | Chinta Devi | Complete |  |  |  | 38.847
149 | 9 |  | 71/6 | DA+0 |  | 16.02.25 | 19.02.25 | Chinta Devi | Complete |  |  |  | 37.504
150 | 10 |  | 50/5 | DA+9 |  | 15.02.25 | 20.02.25 | Sobha Devi | Complete |  |  |  | 47.418
151 | 11 |  | 71/5 | DA+3 |  | 20.02.25 | 24.02.25 | Chinta Devi | Complete |  |  |  | 38.847
| March'25 | [12 empty] | 534.209
152 | 1 |  | 71/4 | DA+3 |  | 25.02.25 | 01.03.25 | Chinta Devi | Complete |  |  |  | 38.847
153 | 2 |  | 53/5 | DA+3 |  | 01.3.25 | 07.03.25 | Ganesh Sinha | Complete |  |  |  | 38.847
154 | 3 |  | 71/3 | DA+6 |  | 02.03.25 | 07.03.25 | Chinta Devi | Complete |  |  |  | 45.413
155 | 4 |  | 58/0 | DC1+3 |  | 26.02.25 | 10.03.25 | Jirwa Devi | Complete |  |  |  | 69.228
156 | 5 |  | 71/2 | DA+3 |  | 08.03.25 | 12.03.25 | Chinta Devi | Complete |  |  |  | 38.847
157 | 6 |  | 70/3 | DA+3 |  | 08.03.25 | 16.03.25 | Sanjeev kumar | Complete |  |  |  | 38.847
158 | 7 |  | 53/4 | DA+0 |  | 09.03.25 | 17.03.25 | Ganesh Sinha | Complete |  |  |  | 37.504
159 | 8 |  | 71/1 | DA+3 |  | 13.03.25 | 18.03.25 | Chinta Devi | Complete |  |  |  | 38.847
160 | 9 |  | 53/3 | DA+6 |  | 18.03.25 | 25.03.25 | Ganesh Sinha | Complete |  |  |  | 45.413
161 | 10 |  | 71/0 | DB2+3 |  | 19.03.25 | 25.03.25 | Chinta Devi | Complete |  |  |  | 60.097
162 | 11 |  | 70/5 | DA+3 |  | 20.03.25 | 29.03.25 | Sanjeev kumar | Complete |  |  |  | 38.847
163 | 12 |  | 53/2 | DA+0 |  | 26.03.25 | 31.03.25 | Ganesh Sinha | Complete |  |  |  | 37.504 | 451.89
164 | 13 |  | 70/11 | DA+3 |  | 26.03.25 | 31.03.25 | Chinta Devi | Complete |  |  |  | 38.847
April'25
165 | 1 |  | 47/9 | DA+3 |  | 31.03.25 | 02.04.25 | Sobha Devi | Complete |  |  |  | 38.847
166 | 2 |  | 70/10 | DA+3 |  | 31.03.25 | 04.04.25 | Chinta Devi | Complete |  |  |  | 38.847
167 | 3 |  | 53/1 | DA+9 |  | 02.04.25 |  | Ganesh Sinha | 2nd Section |  |  |  | 47.418
168 | 4 |  | 70/9 | DA+3 |  |  |  | Chinta Devi | TNP shifting
169 | 5 |  | 68/0 | DD+0 |  | 13.03.25 |  | Sunny Const. | 1st Section |  |  |  | 86.129
170 | 6 |  | 47/8 | DA+0 |  | 03.04.25 |  | Sobha Devi | Cage-1 |  |  |  | 37.504

## Sheet1 (hidden)
S No | Loc No | TOT | Classification
1 | 58/14 | DA+0 | DRY
2 | 51/7 | DA+3 | DFR
3 | 51/5 | DA+0 | DRY
4 | 51/2 | DA+0 | DRY
5 | 53/2 | DA+3 | DFR
6 | 57/7 | DA+3 | DRY
7 | 57/4 | DA+0 | DRY
8 | 55/7 | DA+0 | DRY
9 | 57/5 | DA+3 | DRY
10 | 55/1 | DA+3 | DRY
11 | 55/8 | DA+3 | DRY
12 | 57/2 | DA+0 | DRY
13 | 55/9 | DA+0 | DRY
14 | 57/1 | DA+3 | DRY
15 | 57/3 | DA+0 | DRY
16 | 72/3 | DA+0 | DRY
17 | 43/4 | DA+9 | DRY
18 | 72/4 | DA+0 | DRY
19 | 43/5 | DA+0 | SANDY
20 | 56/9 | DA+3 | DRY
21 | 71/1 | DA+0 | DRY
22 | 56/8 | DA+3 | DRY
23 | 55/10 | DA+3 | DRY
24 | 56/7 | DA+3 | DRY
25 | 55/4 | DA+3 | DFR

## JMC 27.9.23 (hidden)
S no | Locs no | TOT | Classification
1 | 56/3 | DA+0 | DFR | 14.09.23 | 23.09.23 | 25.09.23 | Vaishali Const | JMC required
2 | 44/1 | DA+0 | WFR | 16.09.23 | 20.09.23 | 25.09.23 | Shakti Construction | JMC required
3 | 72/5 | DA+0 | DRY | 19.09.23 | 24.09.23 | 25.09.23 | Mahadev engg. | JMC required
4 | 41/10 | DA+3 | SANDY | 19.09.23 | 22.09.23 | 25.09.23 | Om Const | JMC required
5 | 56/6 | DA+3 | DRY | 21.09.23 | 24.09.23 | 25.09.23 | Manoj Sharma | JMC required
6 | 72/2 | DA+0 | DRY | 15.09.23 | 20.09.23 | 26.09.23 | Mahadev engg. | JMC required
7 | 51/1 | DA+0 | DFR | 10.09.23 |  |  | Amirul Islam | Excavation u/p
8 | 50/3 | DA+0 | DFR | 18.09.23 | 21.09.23 |  | Shri Bhadariyarai Enterprises | Casting
9 | 56/1 | DA+3 | DFR | 21.09.23 |  |  | Vaishali Const | Excavation done
10 | 44/4 | DA+0 | WFR | 19.09.23 | 23.09.23 |  | B S Electrical | Casting
11 | 55/5 | DA+0 | DFR | 22.09.23 |  |  | Amirul Islam | Frustum complete | Manpower | 6
12 | 71/3 | DA+0 | DRY | 21.09.23 |  |  | Mahadev engg. | Block level done
13 | 71/4 | DA+0 | DRY | 23.09.23 |  |  | Mahadev engg. | Excavation complete |  |  | 51
14 | 55/11 | DA+3 | DFR | 22.09.23 |  |  | Nurul Amin | Excavation u/p |  |  | 32
15 | 44/2 | DA+0 | SANDY | 24.9.23 |  |  | Shakti Construction | PCC u/p
16 | 56/4 | DA+3 | DFR | 24.9.23 |  |  | Manoj Sharma | Excavation
17 | 41/11 | DA+3 | SANDY | 23.09.23 |  |  | Om Const | PCC u/p
18 | 56/5 | DA+3 | DRY |  |  |  | Manoj Sharma | Pit marking done
19 | 71/5 | DA+0 |  | 26.09.23 |  |  | Mahadev engg. | Excavation u/p
20 | 46/2 | DA+0 | DRY |  |  |  | Shri Bhadariyarai Enterprises | Excavation u/p
21 | 55/6 | DA+3 |  |  |  |  | Amirul Islam | Excavation u/p

## Jumpering-G (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Insulator Hoisting
Cum Sl. No. | Month Sl. No. | Location No. | Tower Type | Dt. of Jumpering | Name of Sub-Contractor | Ramarks
1 | 1 | 57/6 | DB+0 | 02.06.24 | GPJ Const. | Done
2 | 2 | 57/0 | DB2+0 | 12.07.24 | GPJ Const. | Done
3 | 3 | 56/0 | DB1+0 | 21.07.24 | GPJ Const. | Done
4 | 4 | 55/0 | DC1+0 |  | GPJ Const. | Done
5 | 5 | 53/0 | DC2+3 | 15.09.24 | GPJ Const. | Done
6 | 6 | 51/0 |  | 19.10.24 | GPJ Const. | Done
7 | 7 | 58/7 |  |  | Kuddus | Done
8 | 8 | 72/7 |  | 26.12.24 |  | Done

## Insulator Hoisting - F (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Insulator Hoisting
Cum Sl. No. | Month Sl. No. | Location No. | Tower Type | Dt. of Start | Dt. of Complete | Name of Sub-Contractor | Ramarks
July'24
1 | 1 | 60/11 | DA+3 | 21.07.24 | 21.07.24 | Kuddus | Complete
2 | 2 | 60/9 | DA+3 | 22.07.24 | 22.07.24 | Kuddus | Complete
3 | 3 | 60/10 | DA+0 | 22.07.24 | 22.07.24 | Kuddus | Complete
4 | 4 | 60/8 | DA+0 | 23.07.24 | 23.07.24 | Kuddus | Complete
5 | 5 | 60/7 | DA+3 | 23.07.24 | 23.07.24 | Kuddus | Complete
6 | 6 | 60/6 | DA+0 | 24.07.24 | 24.07.24 | Kuddus | Complete
7 | 7 | 60/5 | DA+3 | 24.07.24 | 24.07.24 | Kuddus | Complete
8 | 8 | 60/3 | DA+3 | 25.07.24 |  | Kuddus | 5 Phase hoisting done
9 | 9 | 60/4 | DA+3 | 25.07.24 | 25.07.24 | Kuddus | Complete
10 | 10 | 61/0 | DB2+0 | 26.07.24 | 26.07.24 | Kuddus | Complete
11 | 11 | 61/1 | DA+6 | 28.07.24 | 28.07.24 | Kuddus | Complete
12 | 12 | 61/2 | DA+6 | 28.07.24 | 28.07.24 | Kuddus | Complete
13 | 13 | 61/3 | DA+6 | 28.07.24 | 28.07.24 | Kuddus | Complete
14 | 14 | 61/4 | DA+3 | 29.07.24 | 29.07.24 | Kuddus | Complete
15 | 15 | 61/5 | DA+3 | 29.07.24 | 29.07.24 | Kuddus | Complete
16 | 16 | 61/6 | DA+3 | 29.07.24 | 29.07.24 | Kuddus | Complete
17 | 17 | 61/10 | DA+9 | 30.07.24 | 30.07.24 | Kuddus | Complete
18 | 18 | 61/8 | DA+6 | 31.07.24 | 31.07.24 | Kuddus | Complete
19 | 19 | 61/9 | DA+0 | 31.07.24 | 31.07.24 | Kuddus | Complete
Aug'24
20 | 1 | 61/7 | DA+9 | 01.08.24 | 01.08.24 | Kuddus | Complete
21 | 2 | 60/1 | DA+6 | 03.08.24 | 03.08.24 | Kuddus | Complete
22 | 3 | 60/2 | DA+3 | 03.08.24 | 03.08.24 | Kuddus | Complete
Sept'24
23 | 1 | 62/1 | DA+3 | 03.09.24 | 03.09.24 | Kuddus | Complete
24 | 2 | 62/2 | DA+3 | 03.09.24 | 03.09.24 | Kuddus | Complete
25 | 3 | 62/4 | DA+3 | 04.09.24 | 04.09.24 | Kuddus | Complete
26 | 4 | 62/3 | DA+0 | 05.09.24 | 05.09.24 | Kuddus | Complete
27 | 5 | 62/5 | DA+0 | 09.09.24 | 09.09.24 | Kuddus | Complete
28 | 6 | 62/6 | DA+3 | 12.09.24 | 12.09.24 | Kuddus | Complete
29 | 7 | 62/7 | DA+3 | 12.09.24 | 12.09.24 | Kuddus | Complete
30 | 8 | 62/8 | DA+0 | 14.09.24 | 14.09.24 | Kuddus | Complete
31 | 9 | 62/10 | DA+0 | 15.09.24 | 15.09.24 | Kuddus | Complete
32 | 10 | 62/11 | DA+3 | 15.09.24 | 15.09.24 | Kuddus | Complete
33 | 11 | 62/9 |  | 16.09.24 | 16.09.24 | Kuddus | Complete
34 | 1 | 63/4 |  | 05.10.24 | 05.10.24 | Kuddus | Complete
35 | 2 | 63/7 |  | 09.10.24 | 09.10.24 | Kuddus | Complete

## Insulator Hoisting - G (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Insulator Hoisting
Cum Sl. No. | Month Sl. No. | Location No. | Tower Type | Dt. of Start | Dt. of Complete | Name of Sub-Contractor | Ramarks
Jan'24
1 | 1 | 57/5 | DA+3 | 05.01.24 | 05.01.24 | Mainul Hoque | Complete
2 | 2 | 57/4 | DA+0 | 06.01.24 | 06.01.24 | Mainul Hoque | Complete
3 | 3 | 57/3 | DA+0 | 07.01.24 | 07.01.24 | Mainul Hoque | Complete
4 | 4 | 57/2 | DA+0 | 07.01.24 | 07.01.24 | Mainul Hoque | Complete
April'24
5 | 1 | 57/7 | DA+3 | 08.04.24 | 08.04.24 | GPJ Const. | Complete
6 | 2 | 57/9 | DA+0 | 09.04.24 | 09.04.24 | GPJ Const. | Complete
7 | 3 | 57/11 | DA+0 | 09.04.24 | 09.04.24 | GPJ Const. | Complete
8 | 4 | 57/12 | DA+3 | 10.04.24 | 10.04.24 | GPJ Const. | Complete
9 | 5 | 57/13 | DA+0 | 10.04.24 | 10.04.24 | GPJ Const. | Complete
10 | 6 | 57/1 | DA+3 | 11.04.24 | 11.04.24 | GPJ Const. | Complete
11 | 7 | 57/10 | DA+0 | 11.04.24 | 11.04.24 | GPJ Const. | Complete
12 | 8 | 56/8 | DA+3 | 12.04.24 | 12.04.24 | GPJ Const. | Complete
13 | 9 | 56/9 | DA+3 | 12.04.24 | 12.04.24 | GPJ Const. | Complete
14 | 10 | 56/6 | DA+3 | 13.04.24 | 13.04.24 | GPJ Const. | Complete
15 | 11 | 56/7 | DA+3 | 13.04.24 | 13.04.24 | GPJ Const. | Complete
16 | 12 | 56/4 | DA+3 | 14.04.24 | 14.04.24 | GPJ Const. | Complete
17 | 13 | 56/5 | DA+0 | 14.04.24 | 14.04.24 | GPJ Const. | Complete
18 | 14 | 56/3 | DA+0 | 15.04.24 | 15.04.24 | GPJ Const. | Complete
19 | 15 | 56/2 | DA+3 | 15.04.24 | 15.04.24 | GPJ Const. | Complete
20 | 16 | 55/10 | DA+3 | 16.04.24 | 16.04.24 | GPJ Const. | Complete
21 | 17 | 55/11 | DA+3 | 16.04.24 | 16.04.24 | GPJ Const. | Complete
22 | 18 | 55/9 | DA+3 | 17.04.24 | 17.04.24 | GPJ Const. | Complete
23 | 19 | 55/7 | DA+0 | 17.04.24 | 17.04.24 | GPJ Const. | Complete
24 | 20 | 55/6 | DA+3 | 17.04.24 | 17.04.24 | GPJ Const. | Complete
25 | 21 | 55/1 | DA+3 | 18.04.24 | 18.04.24 | GPJ Const. | Complete
26 | 22 | 55/2 | DA+3 | 18.04.24 | 18.04.24 | GPJ Const. | Complete
27 | 23 | 55/3 | DA+0 | 18.04.24 | 18.04.24 | GPJ Const. | Complete
28 | 24 | 55/5 | DA+0 | 18.04.24 | 18.04.24 | GPJ Const. | Complete
29 | 25 | 55/8 | DA+3 | 19.04.24 | 19.04.24 | GPJ Const. | Complete
30 | 26 | 53/2 | DA+3 | 20.04.24 | 20.04.24 | GPJ Const. | Complete
31 | 27 | 53/3 | DA+3 | 20.04.24 | 20.04.24 | GPJ Const. | Complete
32 | 28 | 53/4 | DA+3 | 20.04.24 | 20.04.24 | GPJ Const. | Complete
33 | 29 | 57/6 | DB+0 | 21.04.24 | 21.04.24 | GPJ Const. | Complete
34 | 30 | 57/0 | DB+0 | 22.04.24 | 22.04.24 | GPJ Const. | Complete
35 | 31 | 51/8 | DA+3 | 23.04.24 | 23.04.24 | GPJ Const. | Complete
36 | 32 | 51/9 | DA+3 | 23.04.24 | 23.04.24 | GPJ Const. | Complete
37 | 33 | 56/1 | DA+3 | 24.04.24 | 24.04.24 | GPJ Const. | Complete
38 | 34 | 56/0 | DB+0 | 26.04.24 | 26.04.24 | GPJ Const. | Complete
39 | 35 | 51/6 | DA+0 | 27.04.24 | 27.04.24 | GPJ Const. | Complete
40 | 36 | 51/7 | DA+3 | 27.04.24 | 27.04.24 | GPJ Const. | Complete
41` | 37 | 57/8 | DA+3 | 28.04.24 | 28.04.24 | GPJ Const. | Complete
May'24
42 | 1 | 58/0 | DC2+0 | 04.05.24 | 19.09.24 | GPJ Const. | Complete
June'24
43 | 1 | 55/0 | DC1+0 | 02.06.24 | 02.06.24 | GPJ Const. | Complete | 07.09.24
July'24
44 | 1 | 53/1 | DA+0 | 08.07.24 | 08.07.24 | GPJ Const. | Complete
45 | 2 | 53/0 | DC2+3 | 10.07.24 | 31.07.24 | GPJ Const. | Complete
46 | 3 | 52/1 | DA+0 | 29.07.24 | 29.07.24 | GPJ Const. | Complete
47 | 4 | 52/2 | DA+3 | 29.07.24 | 29.07.24 | GPJ Const. | Complete
48 | 5 | 52/3 | DA+0 | 30.07.24 | 30.07.24 | GPJ Const. | Complete
Aug'24
49 | 1 | 52/0 | DB2+0 | 14.08.24 | 14.08.24 | GPJ Const. | Complete
50 | 2 | 51/10 | DA+3 | 14.08.24 | 14.08.24 | GPJ Const. | Complete
51 | 3 | 51/1 | DA+0 | 23.08.24 | 23.08.24 | GPJ Const. | Complete
52 | 4 | 51/3 | DA+0 | 24.08.24 | 24.08.24 | GPJ Const. | Complete
53 | 5 | 51/4 | DA+3 | 24.08.24 | 24.08.24 | GPJ Const. | Complete
54 | 6 | 51/5 | DA+0 | 24.08.24 | 24.08.24 | GPJ Const. | Complete
55 | 7 | 51/0 | DB2+0 | 25.08.24 | 25.08.24 | GPJ Const. | Complete
56 | 8 | 51/2 | DA+0 | 25.08.24 | 25.08.24 | GPJ Const. | Complete
Sept'24
57 | 1 | 50/4 | DA+3 | 15.09.24 | 15.09.24 | GPJ Const. | Complete
58 | 2 | 50/3 | DA+0 | 16.09.24 | 16.09.24 | GPJ Const. | Complete
59 | 3 | 58/1 | DA+0 | 19.09.24 | 19.09.24 | GPJ Const. | Complete
60 | 4 | 50/2 | DA+0 | 21.09.24 | 21.09.24 | GPJ Const. | Complete
61 | 5 | 50/0 | DC2+3 | 07.10.24 | 07.10.24 | GPJ Const. | Complete

## Jumpering-F (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Insulator Hoisting
Cum Sl. No. | Month Sl. No. | Location No. | Tower Type | Dt. of Jumpering | Name of Sub-Contractor | Ramarks
1 | 1 | 61/0 |  | 23.10.24 | Kuddua Ali
2 | 2 | 62/0 |  | 11.11.24 | Kuddua Ali

## Stringing - PKG-F (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
STRINGING
Stringing - PKG-F
S. No | Section |  |  |  | Paying Out |  |  | Final Sag |  |  | Name of Gang | Remarks
| From | To | Length | Cum | Start Date | Finish Date | Month | Start Date | Finish Date | Month
1 | 60/0 | 61/0 | 4.877 | 4.877 | 21.08.24 | 28.08.24 | 2024-08-24 | 09.09.24 | 16.09.24 | 2024-09-24 | Kuddus ali | Final sag completed
2 | 61/0 | 62/0 | 4.568 | 9.445 | 06.09.24 | 16.09.24 | 2024-09-24 | 26.9.24 | 03.10.24 | 2024-10-24 | Kuddus ali | Final sag completed
3 | 62/0 | 63/0 | 4.863 | 14.308 | 23.09.24 | 02.10.24 | 2024-10-24 | 17.10.24 | 22.10.24 | 2024-10-24 | Kuddus ali | Final sag completed
4 | 63/0 | 64/0 | 3.711 | 18.019 | 14.10.24 | 21.10.24 | 2024-10-24 | 31.10.24 | 06.11.24 | 2024-11-24 | Kuddus ali | Final sag completed
5 | 64/0 | 65/0 | 4.918 | 22.937 | 30.10.24 | 05.11.24 | 2024-11-24 | 13.11.24 | 16.11.24 | 2024-11-24 | Kuddus ali | Final sag completed
6 | 59/8 | 60/0 | 3.778 | 26.715 | 22.12.24 | 27.12.24 | 2024-12-24 | 04.01.25 | 09.01.25 | 2025-01-25 | Gopal Associate | Final sag completed
7 | 59/0 | 59/8 | 3.337 | 30.052 | 02.01.25 | 08.01.25 | 2025-01-25 | 12.01.25 | 15.01.25 | 2025-01-25 | Gopal Associate | Final sag completed
8 | 65/0 | 66/0 | 4.736 | 34.788 | 3.02.25 | 22.03.25 | 2025-03-25 | 10.03.25 | 23.03.25 | 2025-03-25 | MR Power | Final sag completed
9 | 50/0 | 51/0 | 4.444 | 39.232 | 12.03.25 | 23.03.25 | 2025-03-25 | 17.03.25 | 24.03.25 | 2025-03-25 | Gopal Associate | Final sag completed & 50/6 Clipping done | 50/4 &50/6 Hoisting done-23.02.25 | 50/8 &50/9, 50/10 Hoisting done | 51/1 & 51/2 Hoisting done
10 | 49/0 | 50/0 | 3.227 | 42.459 | 06.02.25 | 19.02.25 | 2025-03-25 |  |  |  | Gopal Associate | Rough sag done & Earth wire payour rough sag done
11 | 51/0 | 52/0 | 1.049 | 43.508 | 02.04.25 |  | 2025-03-25 | 04.04.25 |  |  | Gopal Associate | Top phase Final Sag done | 35
12 | 48/0 | 49/0 | 0.832 | 44.34 |  |  | 2025-03-25 |  |  |  | Gopal Associate

## Stringing - PKG-G (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
STRINGING- PKG-G
S. No | Section |  |  | Paying Out |  |  | Final Sag |  |  | Name of Gang | Remarks
| From | To | Length | Start Date | Finish Date | Month | Start Date | Finish Date | Month
1 | 57/6 | 58/0 | 3.141 | 06.05.2024 | 10.05.24 | 2024-05-24 | 19.05.24 | 24.05.24 | 2024-05-24 | GPJ Const. | Final sag done
2 | 57/0 | 57/6 | 2.344 | 16.05.24 | 24.05.24 | 2024-05-24 | 07.06.24 | 12.06.25 | 2024-06-24 | GPJ Const. | Final sag done
3 | 56/0 | 57/0 | 4.127 | 04.06.24 | 12.06.24 | 2024-06-24 | 28.06.24 | 04.07.24 | 2024-07-24 | GPJ Const. | Final sag done
4 | 55/0 | 56/0 | 4.9 | 25.06.24 | 04.07.24 | 2024-07-24 | 17.07.24 | 22.07.24 | 2024-07-24 | GPJ Const. | Final sag done
5 | 53/0 | 55/0 | 2.013 | 16.07.24 | 22.07.24 | 2024-07-24 | 09.08.24 | 10.08.24 | 2024-08-24 | GPJ Const. | Final sag done
6 | 52/0 | 53/0 | 2.364 | 19.08.24 | 22.08.24 | 2024-08-24 | 04.09.24 | 09.09.24 | 2024-09-24 | GPJ Const. | Final sag done
7 | 51/0 | 52/0 | 4.403 | 01.09.24 | 08.09.24 | 2024-09-24 | 28.09.24 | 05.10.24 | 2024-10-24 | GPJ Const. | Final sag done
8 | 50/0 | 51/0 | 1.971 | 26.9.24 | 02.10.24 | 2024-10-24 | 08.10.24 | 10.10.24 | 2024-10-24 | GPJ Const. | Final sag done
9 | 72/7 | 73/0 | 0.49623 | 12.11.24 | 15.11.24 | 2024-11-24 | 27.11.24 | 29.11.24 | 2024-11-24 | MR Power | Final sag done
10 | 58/0 | 58/7 | 2.797 | 20.11.24 | 23.11.24 | 2024-11-24 | 01.12.245 | 05.12.24 | 2024-12-24 | Kddus Ali | Final sag done
11 | 72/0 | 72/7 | 2.589 | 18.11.24 | 23.11.24 | 2024-11-24 | 06.12.24 | 10.12.24 | 2024-12-24 | MR Power | Final sag done
12 | 67/1 | 68/0 | 0.42647 | 22.12.24 | 23.12.24 | 2024-12-24 | 23.12.24 | 25.12.25 | 2024-12-24 | Nasruddin | Final sag done
13 | 68/0 | 69/0 | 2.855 | 11.12.24 | 20.12.24 | 2024-12-24 | 01.01.25 | 05.01.25 | 2025-01-25 | Nasruddin | Final sag done
16 | 58/7 | 59/0 | 3.885 | 27.12.24 | 04.01.25 | 2025-01-25 | 07.01.25 | 09.01.25 | 2025-01-25 | MR Power | Final sag done
17 | 71/0 | 72/0 | 2.092 | 03.12.24 | 10.12.24 | 2024-12-24 | 16.01.25 | 19.01.25 | 2025-01-25 | MR Power | Final sag done
18 | 67/0 | 67/1 | 0.43755 | 21.12.24 | 22.12.24 | 2024-12-24 | 20.01.25 | 21.01.25 | 2025-01-25 | Nasruddin | Final sag done
19 | 69/0 | 70/0 | 3.881 | 30.12.24 | 05.01.25 | 2025-01-25 | 27.01.25 | 28.01.25 | 2025-01-26 | Nasruddin | Final sag done
21 | 41/0 | 42/0 | 4.981 | 13.02.25 | 20.02.25 | 2025-02-25 | 28.02.25 | 02.03.25 | 2025-03-26 | Nasruddin | Final sag done | 41/0 hoisting done
20 | 59/0 | 60/0 | 2.581 | 20.01.25 | 25.01.25 | 2025-01-25 |  |  |  | MR Power | Final sag arrangement wip

## OPGW PKG-G (hidden)
EXECUTING AGENCY : M/s. KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
OPGW Progress details(Pkg-G)
Sr. No | Section |  | Section length in Kms | OPGW Drum Length (In KMs) | Start date | End date | Splicing | Jointing Details | Agency | OTDR reading status | Splicing done by | Remarks
1 | 51/0 | 52/0 | 4.403 | 4.653 | 11.01.25 | 12.01.25 |  |  | Congent tech |  |  | Final sag completed
2 | 52/0 | 55/0 | 4.377 | 4.627 | 17.01.25 | 18.01.25 |  |  | Congent tech |  |  | Final sag completed
3 | 55/0 | 56/0 | 4.9 | 5.16 | 20.01.25 | 21.01.25 |  |  | Congent tech |  |  | Final sag completed
4 | 56/0 | 57/0 | 4.127 | 4.372 | 23.01.25 | 24.01.25 |  |  | Congent tech |  |  | Final sag completed
5 | 57/0 | 57/6 | 1.954 | 2.553 | 27.01.25 | 28.01.25 |  |  | Congent tech |  |  | Final sag completed
6 | 57/6 | 58/0 | 3.141 | 3.365 | 29.01.25 | 30.01.25 |  |  | Congent tech |  |  | Final sag completed
7 | 58/0 | 58/7 | 2.789 | 3.015 | 01.02.25 | 02.02.25 |  |  | Congent tech |  |  | Final sag completed
8 | 58/7 | 59/0 | 3.885 | 4.124 | 04.02.25 | 05.02.25 |  |  | Congent tech |  |  | Final sag completed
Total Length in Kms |  |  | 29.576 | 31.869
Total Length in Km |  |  | 29.576 | 31.869

## OPGW PKG-F (hidden)
EXECUTING AGENCY : M/s. KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
OPGW Progress details(PKG-F)
Sr. No | Section |  | Section length in Kms | OPGW Drum Length (In KMs) | Start date | End date | Splicing | Jointing Details | Agency | OTDR reading status | Splicing done by | Remarks
1 | 59/0 | 59/8 | 3.337 |  | 10.02.25 | 11.02.25 | 05.03.25 |  | Congent tech |  | Revant Sharma | Final Sag Complete
2 | 59/8 | 60/0 | 3.778 |  | 12.02.25 | 13.02.25 | 26.02.25 |  | Congent tech |  | Revant Sharma | Final Sag Complete
3 | 60/0 | 61/0 | 4.877 |  | 15.02.25 | 16.02.25 |  |  | Congent tech |  |  | Final Sag Complete
4 | 61/0 | 62/0 | 4.568 |  | 19.02.25 | 19.02.25 | 27.02.25 |  | Congent tech |  | Revant Sharma | Final Sag Complete
5 | 62/0 | 63/0 | 4.863 |  | 23.02.25 | 24.02.25 |  |  | Congent tech |  |  | Final Sag Complete
6 | 63/0 | 64/0 | 3.711 |  | 01.03.25 | 02.03.25 |  |  | Congent tech |  |  | Final Sag Complete
7 | 64/0 | 65/0 | 4.918 |  | 03.03.25 | 03.03.25 |  |  | Congent tech |  |  | Final Sag Complete
Total Length in Kms |  |  | 30.052 | 0
Total Length in Km |  |  | 30.052 | 0
31.869

## Crossing (hidden)
CROSSING DETAILS FOR 765 KV DC FATEHGARH 3 - BEAWAR T/L (Part-G & Part-F)
Sl No | Crossing Name | PART - G | [6 empty] | PART - F
|  | Section |  | Owner Name | Date of Submission | Date of Site Inspection | Proposal Status | Remarks | Section |  | Owner Name | Date of Submission | Date of Site Inspection | Proposal Status | Remarks
|  | From | To | [5 empty] | From | To
A | Power Line
1 | 400 KV D/C Rajwest - Jodhpur Line | AP 36 | AP 37 | RRVPNL |  |  | Hard copy submitted on - 08/03/24. |  | AP 46 | AP 47 | RRVPNL |  | 2 days |  |  | 5,5,5,5
2 | U/C LILO of 400 KV D/C Rajwest - Jodhpur Line at Newai S/S | AP 45 | AP 46 | RRVPNL | 2023-12-25 |  | Hard copy submitted on - 10/01/24. |  | AP 56 | AP 57 | RRVPNL |  | 1week
3 | 220 KV S/C GSS Boranada - Balotra Line | AP 60 | AP 61 | RRVPNL | 2023-11-13 |  | Approved on dated 18.07.24 |  | AP 66 | AP 67 | RRVPNL | 2024-02-13 |  | Approved on dated 18.07.24
B | Railway
1 | Electrified BG Double Track Line (Jodhpur - Barmer) | AP 70 | AP 71 | NWR |  |  | Hard copy submitted on - 21/02/24.
C | NH/SH
1 | SH - 28 (Bikaner - Barmer) | AP 44 | 44/1 | PWD |  |  | NR |  | AP 55 | 55/1 | PWD
2 | Bharatmala Expressway (Amritsar - Kandla) | AP 49 | AP 50 | NHAI | 2023-11-13 |  | Approved on dated - 01.06.24 |  | AP 58 | AP 59 | NHAI | 2024-01-21 |  | Approved on dated - 01.06.24
3 | SH - 66 (Kalyanpur - Balesar) | 51/7 | 51/8 | PWD |  |  | NR |  | 59/14 | 59/15 | PWD
4 | NH 25 (Jodhpur - Barmer) | AP 62 | AP 63 | NHAI | 2023-12-06 |  | Approved on dated - 24.06.24 |  | AP 68 | AP 69 | NHAI | 2024-02-13 |  | Approved on dated - 24.06.24
5 | SH - 68 (Shikarpura - Luni) | 72/1 | 72/2 | PWD |  |  | NR
D | River
1 | Luni River | 72/7 | AP 73 |  |  |  | NR | NR
E | Pipe Line
1 | Under Ground Oil Pipe Line | 59/2 | 59/3 | HPML |  |  |  | Format awaited from SPTL | 65/7 | 65/8 | HPML
2 | Under Ground Oil Pipe Line (Mundra - Bhatinda) | 72/3 | 72/4 | IOCL

## Clear locs shared by client (hidden)
Erection Workfront_shared by SPTL Section II_29.11.2024
SL No. | Location (G) | Current Status | SL No. | Location(F) | Current Status
1 | 33/1 | Untouch | 1 | 47/2 | Untouch | 33/8
2 | 35/0 | Untouch | 2 | 47/3 | Untouch
3 | 35/1 | Untouch | 3 | 47/5 | Untouch
4 | 35/2 | Untouch | 4 | 47/6 | Untouch
5 | 35/3 | Untouch | 5 | 47/7 | Untouch
6 | 35/4 | Untouch | 6 | 47/8 | Untouch
7 | 35/5 | Untouch | 7 | 47/9 | Untouch |  | 137
8 | 35/6 | Untouch | 8 | 49/0 | Untouch
9 | 35/7 | Untouch | 9 | 49/1 | Untouch
10 | 35/8 | Untouch | 10 | 49/3 | WIP (Sobha Devi)
11 | 37/2 | Untouch | 11 | 51/0 | Untouch
12 | 37/3 | Untouch | 12 | 52/3 | Untouch
13 | 37/4 | Untouch | 13 | 53/5 | Untouch
14 | 38/1 | Untouch | 14 | 53/6 | Untouch
15 | 38/2 | Untouch | 15 | 53/7 | Untouch
16 | 38/3 | Untouch | 16 | 53/8 | Untouch
17 | 38/6 | Untouch | 17 | 54/1 | Untouch
18 | 38/8 | Untouch | 18 | 54/2 | Untouch
19 | 39/0 | Untouch | 19 | 55/7 | Untouch
20 | 39/1 | Untouch | 20 | 57/2 | Untouch
21 | 39/4 | Untouch | 21 | 58/0 | Untouch
22 | 40/2 | Untouch | 22 | 59/0 | Materials shifting wip (Jirwa Devi)
23 | 40/3 | Untouch | 23 | 66/0 | Untouch
24 | 40/4 | Untouch | 24 | 67/0 | Untouch
25 | 40/5 | Untouch | 25 | 69/1 | Untouch
26 | 40/6 | Untouch | 26 | 71/6 | Untouch
27 | 41/12 | Untouch | 27 | 71/7 | Untouch
28 | 42/0 | Untouch | 28 | 73/3 | Untouch
29 | 43/0 | Untouch | 29 | 73/4 | Untouch
30 | 44/0 | Untouch | 30 | 73/5 | Untouch
31 | 49/0 | Untouch | 31 | 73/7 | Untouch
32 | 62/0 | Untouch | 32 | 74/0 | Untouch
33 | 63/2 | Untouch
34 | 63/5 | Untouch
35 | 63/6 | Untouch
36 | 64/0 | Untouch
37 | 65/1 | Untouch
38 | 65/2 | Untouch
39 | 65/6 | Untouch
40 | 65/7 | Untouch
41 | 66/0 | Untouch
42 | 66/1 | WIP (Sanjeev Kumar )
43 | 66/3
44 | 67/0 | WIP (Chinta Devi)
45 | 69/9 | WIP (Sunny const)
46 | 71/0