## Project Details
Project Code | Project Name | Client Name | NOA Start Date | LOA End Date | Planning Engineer | PCH | Regional Manager | Project Manger | Section Incharge | Engineer/Supervisor
TA 413 | 765kv D/C Bikaner II to Neemrana II TL-02 | PGCIL | 2024-03-12 | 2025-12-11 | Mr. Santosh Mishra | Mr. Sanjay Gupta | Mr. Tushar Grover | Mr. Anil Kumar Sharma | Surendra Kumar Patel | Suraj Chaudhary
[9 empty] | Kartik Jhorar | Rudra Prasad
[9 empty] | Shuvam Gupta | Aman Kumar Singh
[9 empty] | Govind Bhardwaj | Manoj Gupta
Raju Mahto
Khublal Mahto
Sushil Kumar
Haridashn
Manoj Kumar chaudhary
Nabirul Islam
Sanjay Kumar
Rahul Ravidas
Narayan Mahto
Akbar Ali
Kamal Ravidas
Manirul Islam
Tarique Anwar
Raju Prasad
Abhay Ojha

## Erection Compiled
CUMM. SR.NO | MONTH SR.NO. | Location No. | Type of Tower | Starting Date | Completion Date | Gang name | Tower Weight | Revenue | Name of Supervisor | Status | Prop. Name
1 | 1 | 29A/2 | DA+6 | 2024-09-12 | 2024-09-21 | Bhagwan construction | 43.8044 | 4.0812 | Manoj Kumar Gupta | Completed
2 | 2 | 29/5 | DA+0 | 2024-09-21 | 2024-09-27 | Bhagwan construction | 36.1598 | 3.3689 | Manoj Kumar Gupta | Completed
3 | 1 | 29/3 | DA+0 | 2024-09-28 | 2024-10-03 | Bhagwan construction | 36.1598 | 3.3689 | Manoj Kumar Gupta | Completed
4 | 2 | 29/4 | DA+3 | 2024-10-03 | 2024-10-08 | Bhagwan construction | 37.9311 | 3.534 | Manoj Kumar Gupta | Completed
5 | 3 | 29A/6 | DA+9 | 2024-10-03 | 2024-10-14 | Bhagwan construction | 45.697 | 4.2575 | Manoj Kumar Gupta | Completed
6 | 4 | 30/1 | DA+0 | 2024-10-09 | 2024-10-17 | Bhagwan construction | 36.1598 | 3.3689 | Kartik Mahto | Completed
7 | 5 | 29A/1 | DA+6 | 2024-10-14 | 2024-10-25 | Bhagwan construction | 43.8044 | 4.0812 | Manoj Kumar Gupta | Completed
8 | 1 | 34/8 | DA+0 | 2024-11-12 | 2024-11-24 | Vasu dev singh-1 | 36.1598 | 3.3689 | Raju Mahto | Completed
9 | 2 | 34/12 | DA+3 | 2024-11-14 | 2024-11-25 | Vasu dev singh-2 | 37.9311 | 3.534 | Mustak | Completed
10 | 1 | 34/4 | DA+6 | 2024-11-25 | 2024-12-04 | Vasu dev singh-1 | 43.8044 | 4.0812 | Raju Mahto | Completed
11 | 2 | 34/7 | DA+0 | 2024-11-26 | 2024-12-12 | Vasu dev singh-2 | 36.1598 | 3.3689 | Raju Mahto | Completed
12 | 3 | 34/3 | DA+1.5 | 2024-12-05 | 2024-12-16 | Vasu dev singh-1 | 37.1383 | 3.4601 | Manoj Kumar Gupta | Completed
13 | 4 | 8/1 | DA-3 | 2024-12-07 | 2024-12-16 | Punam Devi-2 | 34.7898 | 3.2413 | Sanjay Kumar | Completed
14 | 5 | 34/9 | DA+1.5 | 2024-12-13 | 2024-12-21 | Vasu dev singh-2 | 37.1383 | 3.4601 | Mustak & Abul | Completed
15 | 6 | 35/7 | DA+3 | 2024-12-13 | 2024-12-22 | Punam Devi-2 | 37.9311 | 3.534 | Kartik Mahto | Completed
16 | 7 | 7A/5 | DA+3 | 2024-12-17 | 2024-12-24 | Punam Devi-2 | 37.9311 | 3.534 | Sanjay Kumar | Completed
17 | 8 | 36A/1 | DA+3 | 2024-12-13 | 2024-12-25 | Punam Devi-3 | 37.9311 | 3.534 | Haridas | Completed | Sachinder
18 | 9 | 7/1 | DA-3 | 2024-12-15 | 2024-12-26 | Punam Devi-1 | 34.7898 | 3.2413 | Raju Mahto | Completed | Hazari Yadav
19 | 10 | 35/8 | DA+6 | 2024-12-23 | 2024-12-28 | Punam Devi-2 | 43.8044 | 4.0812 | Kartik Mahto | Completed | Gulshan Kumar
20 | 11 | 34/5 | DA+9 | 2024-12-17 | 2024-12-29 | Vasu dev singh-1 | 45.697 | 4.2575 | Manoj Kumar Gupta | Completed | Pawan
21 | 12 | 34/10 | DA-3 | 2024-12-22 | 2024-12-29 | Vasu dev singh-2 | 34.7898 | 3.2413 | Mustak & Abul | Completed | Praveen Kumar
22 | 13 | 7A/4 | DA+3 | 2024-12-24 | 2024-12-31 | Punam Devi-2 | 37.9311 | 3.534 | Raju Mahto | Completed | Dharmendra Das
23 | 1 | 7/2 | DA+6 | 2024-12-27 | 2025-01-03 | Punam Devi-1 | 43.8044 | 4.0812 | Gangadin sahoo | Completed | Hazari Yadav
24 | 2 | 35/11 | DA+3 | 2024-12-24 | 2025-01-03 | Punam Devi-3 | 37.9311 | 3.534 | Haridas | Completed | Sachinder
25 | 3 | 35/6 | DA+6 | 2024-12-29 | 2025-01-05 | Punam Devi-2 | 43.8044 | 4.0812 | Kartik Mahto | Completed | Gulshan Kumar
26 | 4 | 34/11 | DA+1.5 | 2024-12-30 | 2025-01-07 | Vasu dev singh-2 | 37.1383 | 3.4601 | Mustak & Abul | Completed | Praveen Kumar
27 | 5 | 7A/3 | DA+3 | 2025-01-01 | 2025-01-08 | Punam Devi-2 | 37.9311 | 3.534 | Raju Mahto | Completed | Dharmendra Das
28 | 6 | 34/6 | DA+3 | 2024-12-30 | 2025-01-09 | Vasu dev singh-1 | 37.9311 | 3.534 | Manoj Kumar Gupta | Completed | Pawan
29 | 7 | 8/5 | DA+9 | 2025-01-04 | 2025-01-09 | Punam Devi-1 | 45.697 | 4.2575 | Gangadin sahoo | Completed | Hazari Yadav
30 | 8 | 36A/2 | DA+9 | 2025-01-04 | 2025-01-11 | Punam Devi-3 | 45.697 | 4.2575 | Haridas | Completed | Sachinder
31 | 9 | 35/5 | DA+9 | 2025-01-06 | 2025-01-13 | Punam Devi-2 | 45.697 | 4.2575 | Kartik Mahto | Completed | Gulshan Kumar
32 | 10 | 8/6 | DA+3 | 2025-01-10 | 2025-01-15 | Punam Devi-1 | 37.9311 | 3.534 | Gangadin sahoo | Completed | Hazari Yadav
33 | 11 | 7A/2 | DA+3 | 2025-01-08 | 2025-01-16 | Punam Devi-2 | 37.9311 | 3.534 | Raju Mahto | Completed | Dharmendra Das
34 | 12 | 35/1 | DA+6 | 2025-01-07 | 2025-01-19 | Vasu dev singh-2 | 43.8044 | 4.0812 | Mustak & Abul | Completed | Praveen Kumar
35 | 13 | 35/4 | DA+9 | 2025-01-14 | 2025-01-19 | Punam Devi-2 | 45.697 | 4.2575 | Kartik Mahto | Completed | Gulshan Kumar
36 | 14 | 8/7 | DA+3 | 2025-01-16 | 2025-01-20 | Punam Devi-1 | 37.9311 | 3.534 | Gangadin sahoo | Completed | Hazari Yadav
37 | 15 | 34/2 | DA+9 | 2025-01-10 | 2025-01-21 | Vasu dev singh-1 | 45.697 | 4.2575 | Manoj Kumar Gupta | Completed | Pawan
38 | 16 | 37/4 | DA+9 | 2025-01-11 | 2025-01-22 | Punam Devi-3 | 45.697 | 4.2575 | Haridas | Completed | Sachinder
39 | 17 | 7A/1 | DA+1.5 | 2025-01-17 | 2025-01-22 | Punam Devi-2 | 37.1383 | 3.4601 | Raju Mahto | Completed | Dharmendra Das
40 | 18 | 35/9 | DA+1.5 | 2025-01-17 | 2025-01-24 | Punam Devi-2 | 37.1383 | 3.4601 | Kartik Mahto | Completed | Gulshan Kumar
41 | 19 | 8/8 | DA+9 | 2025-01-20 | 2025-01-25 | Punam Devi-1 | 45.697 | 4.2575 | Gangadin sahoo | Completed | Hazari Yadav
42 | 20 | 34/1 | DA+9 | 2025-01-21 | 2025-01-29 | Vasu dev singh-1 | 45.697 | 4.2575 | Manoj Kumar Gupta | Completed | Pawan
43 | 21 | 38/3 | DA+3 | 2025-01-24 | 2025-01-29 | Punam Devi-2 | 37.9311 | 3.534 | Kartik Mahto | Completed | Gulshan Kumar
44 | 22 | 8/9 | DA+3 | 2025-01-25 | 2025-01-30 | Punam Devi-4 | 37.9311 | 3.534 | Gangadin sahoo | Completed | Hazari Yadav
45 | 23 | 37/5 | DA+3 | 2025-01-22 | 2025-01-30 | Punam Devi-3 | 37.9311 | 3.534 | Haridas | Completed | Sachinder
46 | 24 | 7A/0 | DB1+6 | 2025-01-22 | 2025-01-31 | Punam Devi-2 | 65.0278 | 6.0585 | Raju Mahto | Completed | Gopal Muni
47 | 25 | 34/0 | DB1+6 | 2025-01-17 | 2025-01-31 | Vasu dev singh-1 | 65.0278 | 6.0585 | Mustak & Abul | Completed | Praveen Kumar
48 | 1 | 8/10 | DA+0 | 2025-01-30 | 2025-02-03 | Punam Devi-4 | 36.1598 | 3.3689 | Gangadin sahoo | Completed | Hazari Yadav
49 | 2 | 38/6 | DA+6 | 2025-01-29 | 2025-02-04 | Punam Devi-1 | 43.8044 | 4.0812 | Kartik Mahto | Completed | Mithilesh
50 | 3 | 37A/2 | DA+1.5 | 2025-01-29 | 2025-02-07 | Punam Devi-3 | 37.1383 | 3.4601 | Haridas | Completed | Sachinder
51 | 4 | 33/6 | DA+6 | 2025-01-29 | 2025-02-08 | Vasu dev singh-2 | 43.8044 | 4.0812 | Manoj Kumar Gupta | Completed | Pawan
52 | 5 | 8/2 | DA+6 | 2025-02-03 | 2025-02-08 | Punam Devi-4 | 43.8044 | 4.0812 | Gangadin sahoo | Completed | Hazari Yadav
53 | 6 | 7/6 | DA-1.5 | 2025-01-31 | 2025-02-10 | Punam Devi-2 | 35.6018 | 3.317 | Raju Mahto | Completed | Gopal Muni
54 | 7 | 38/4 | DA+1.5 | 2025-02-05 | 2025-02-10 | Punam Devi-1 | 37.1383 | 3.4601 | Kartik Mahto | Completed | Mithilesh
55 | 8 | 8/0 | DB1+0 | 2025-02-09 | 2025-02-14 | Punam Devi-4 | 55.4509 | 5.1663 | Gangadin sahoo | Completed | Hazari Yadav
56 | 9 | 38/5 | DA+3 | 2025-02-11 | 2025-02-15 | Punam Devi-1 | 37.9311 | 3.534 | Kartik Mahto | Completed | Mithilesh
57 | 10 | 37A/1 | DA+3 | 2025-02-08 | 2025-02-16 | Punam Devi-3 | 37.9311 | 3.534 | Haridas | Completed | Sachinder
58 | 11 | 33/5 | DA+0 | 2025-01-31 | 2025-02-18 | Vasu dev singh-1 | 36.1598 | 3.3689 | Mustak & Abul | Completed | Praveen Kumar
59 | 12 | 38/9 | DA+0 | 2025-02-15 | 2025-02-18 | Punam Devi-1 | 36.1598 | 3.3689 | Kartik Mahto | Completed | Mithilesh
60 | 13 | 7/5 | DA+6 | 2025-02-11 | 2025-02-19 | Punam Devi-2 | 43.8044 | 4.0812 | Raju Mahto | Completed | Gopal Muni
61 | 14 | 8/3 | DA+9 | 2025-02-14 | 2025-02-19 | Punam Devi-4 | 45.697 | 4.2575 | Gangadin sahoo | Completed | Hazari Yadav
62 | 15 | 35/0 | DB2+0 | 2025-02-09 | 2025-02-23 | Vasu dev singh-2 | 59.5006 | 5.5436 | Manoj Kumar Gupta | Completed | Pawan
63 | 16 | 38/10 | DA+3 | 2025-02-18 | 2025-02-24 | Punam Devi-1 | 37.9311 | 3.534 | Kartik Mahto | Completed | Mithilesh
64 | 17 | 8/4 | DA+6 | 2025-02-20 | 2025-02-24 | Punam Devi-4 | 43.8044 | 4.0812 | Gangadin sahoo | Completed | Hazari Yadav
65 | 18 | 37A/3 | DA+3 | 2025-02-16 | 2025-02-25 | Punam Devi-3 | 37.9311 | 3.534 | Haridas | Completed | Sachinder
66 | 19 | 7/4 | DA+6 | 2025-02-20 | 2025-02-27 | Punam Devi-2 | 43.8044 | 4.0812 | Raju Mahto | Completed | Gopal Muni
67 | 20 | 9/1 | DA+3 | 2025-02-24 | 2025-02-28 | Punam Devi-4 | 37.9311 | 3.534 | Raju Mahto | Completed | Hazari Yadav
68 | 21 | 37A/5 | DA+3 | 2025-02-24 | 2025-02-28 | Punam Devi-1 | 37.9311 | 3.534 | Prabhakar | Completed | Mithilesh
69 | 1 | 33/8 | DA+3 | 2025-02-18 | 2025-03-04 | Vasu dev singh-1 | 37.9311 | 3.534 | Kartik Mahto | Completed | Praveen Kumar
70 | 2 | 9/3 | DA+0 | 2025-03-01 | 2025-03-04 | Punam Devi-4 | 36.1598 | 3.3689 | Raju Mahto | Completed | Hazari Yadav
71 | 3 | 38/1 | DA+0 | 2025-03-01 | 2025-03-06 | Punam Devi-1 | 36.1598 | 3.3689 | Prabhakar | Completed | Mithilesh
72 | 4 | 37A/4 | DA+9 | 2025-02-25 | 2025-03-06 | Punam Devi-3 | 45.697 | 4.2575 | Haridas | Completed | Sachinder
73 | 5 | 37A/6 | DA+3 | 2025-02-24 | 2025-03-08 | Vasu dev singh-2 | 37.9311 | 3.534 | Prabhakar | Completed | Pawan
74 | 6 | 9/4 | DA+6 | 2025-03-05 | 2025-03-09 | Punam Devi-4 | 43.8044 | 4.0812 | Gangadin sahoo | Completed | Hazari Yadav
75 | 7 | 37A/0 | DB1+0 | 2025-02-28 | 2025-03-11 | Punam Devi-2 | 55.4509 | 5.1663 | Kartik Mahto | Completed | Gopal Muni
76 | 8 | 38/2 | DA+0 | 2025-03-07 | 2025-03-11 | Punam Devi-1 | 36.1598 | 3.3689 | Manoj Kumar Gupta | Completed | Mithilesh
77 | 9 | 39/7 | DA+3 | 2025-03-07 | 2025-03-13 | Punam Devi-3 | 37.9311 | 3.534 | Haridas | Completed | Sachinder
78 | 10 | 9/2 | DA+3 | 2025-03-10 | 2025-03-13 | Punam Devi-4 | 37.9311 | 3.534 | Gangadin sahoo | Completed | Hazari Yadav
79 | 11 | 15/2 | DA+3 | 2025-03-14 | 2025-03-18 | Punam Devi-4 | 37.9311 | 3.534 | Gangadin sahoo | Completed | Hazari Yadav
80 | 12 | 38/7 | DA+9 | 2025-03-12 | 2025-03-18 | Punam Devi-1 | 45.697 | 4.2575 | Manoj Kumar Gupta | Completed | Mithilesh
81 | 13 | 39/2 | DA+3 | 2025-03-12 | 2025-03-19 | Punam Devi-2 | 37.9311 | 3.534 | Kartik Mahto | Completed | Gopal Muni
82 | 14 | 39/5 | DA+1.5 | 2025-03-14 | 2025-03-20 | Punam Devi-3 | 37.1383 | 3.4601 | Haridas | Completed | Gulshan Kumar
83 | 15 | 39/0 | DB2+0 | 2025-03-09 | 2025-03-21 | Vasu dev singh-2 | 59.5006 | 5.5436 | Raju Mahto | Completed | Pawan
84 | 16 | 15/3 | DA+3 | 2025-03-19 | 2025-03-22 | Punam Devi-4 | 37.9311 | 3.534 | Gangadin sahoo | Completed | Hazari Yadav
85 | 17 | 38/8 | DA+1.5 | 2025-03-19 | 2025-03-24 | Punam Devi-1 | 37.1383 | 3.4601 | Manoj Kumar Gupta | Completed | Mithilesh
86 | 18 | 39/3 | DA+1.5 | 2025-03-20 | 2025-03-25 | Punam Devi-2 | 37.1383 | 3.4601 | Kartik Mahto | Completed | Gopal Muni
87 | 19 | 39/4 | DA+3 | 2025-03-21 | 2025-03-27 | Punam Devi-3 | 37.9311 | 3.534 | Haridas | Completed | Gulshan Kumar
88 | 20 | 15/4 | DA+6 | 2025-03-23 | 2025-03-27 | Punam Devi-4 | 43.8044 | 4.0812 | Gangadin sahoo | Completed | Hazari Yadav
89 | 21 | 39/1 | DA-1.5 | 2025-03-22 | 2025-03-29 | Vasu dev singh-2 | 35.6018 | 3.317 | Raju Mahto | Completed | Pawan
90 | 22 | 39/9 | DA+6 | 2025-03-25 | 2025-03-30 | Punam Devi-1 | 43.8044 | 4.0812 | Manoj Kumar Gupta | Completed | Gulshan Kumar
91 | 23 | 40/2 | DA+6 | 2025-03-26 | 2025-03-31 | Punam Devi-2 | 43.8044 | 4.0812 | Kartik Mahto | Completed | Gopal Muni
92 | 24 | 15/5 | DA+3 | 2025-03-26 | 2025-03-31 | Punam Devi-4 | 37.9311 | 3.534 | Gangadin sahoo | Completed | Hazari Yadav
93 | 25 | 39/8 | DA+1.5 | 2024-03-26 | 2025-03-31 | Punam Devi-3 | 37.1383 | 3.4601 | Haridas | Completed | Gulshan Kumar
94 | 1 | 39/10 | DA+3 | 2025-03-31 | 2025-04-05 | Punam Devi-3 | 37.9311 | 3.534 | Haridas | Completed | Mithilesh
95 | 2 | 15/6 | DA+9 | 2025-03-31 | 2025-04-06 | Punam Devi-4 | 45.697 | 4.2575 | Gangadin sahoo | Completed | Hazari Yadav
96 | 3 | 39/11 | DA+6 | 2025-03-30 | 2025-04-09 | Punam Devi-1 | 43.8044 | 4.0812 | Manoj Kumar Gupta | Completed | Gulshan Kumar
97 | 4 | 40/3 | DA+3 | 2025-03-31 | 2025-04-09 | Punam Devi-2 | 37.9311 | 3.534 | Kartik Mahto | Completed | Gopal Muni
98 | 5 | 38/0 | DB1+3 | 2025-03-29 | 2025-04-11 | Vasu dev singh-2 | 57.9632 | 5.4003 | Manoj Gupta | Completed | Pawan
99 | 6 | 40/5 | DA+9 | 2025-04-05 | 2025-04-14 | Punam Devi-3 | 45.697 | 4.2575 | Haridas | Completed | Mithilesh
100 | 7 | 40/4 | DA+6 | 2025-04-09 | 2025-04-18 | Punam Devi-2 | 43.8044 | 4.0812 | Raju Mahto | Completed | Gopal Muni
101 | 8 | 39/6 | DA+1.5 | 2025-04-09 | 2025-04-18 | Punam Devi-1 | 37.1383 | 3.4601 | Haridas | Completed | Gulshan Kumar
102 | 9 | 40/6 | DA+9 | 2025-04-14 | 2025-04-22 | Punam Devi-3 | 45.697 | 4.2575 | Haridas | Completed | Mithilesh
103 | 10 | 36A/0 | DB1+9 | 2025-04-18 | 2025-04-30 | Punam Devi-2 | 66.7809 | 6.2219 | Raju Mahto | Completed | Gopal Muni
104 | 11 | 40/0 | DB1+6 | 2025-04-18 | 2025-04-30 | Punam Devi-1 | 65.0278 | 6.0585 | Haridas | Completed | Gulshan Kumar
105 | 1 | 32/6 | DA+9 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.2575 | Manoj Gupta | Completed
106 | 2 | 32/1 | DA+6 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 4.0812 | Raju Mahto | Completed
107 | 3 | 7/3 | DA+9 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 4.2575 | Sanjay Kumar | Completed
108 | 4 | 32/5 | DA+9 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.2575 | Manoj Gupta | Completed
109 | 5 | 6/1 | DA+9 | 2025-07-16 | 2025-07-26 | Jwala Singh-1 | 45.697 | 4.2575 | Aman Singh | Completed
110 | 6 | 32/2 | DA+9 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 4.2575 | Suraj Kumar | Completed
111 | 7 | 7/0 | DB2+0 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.5436 | Sanjay Kumar | Completed
112 | 8 | 32/7 | DA+3 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 3.534 | Manoj Gupta | Completed
113 | 1 | 31/0 | DB1+0 | 2025-07-16 | 2025-08-01 | SK Samiul -1 | 55.4509 | 5.1663 | Haridas | Completed
114 | 2 | 42/0 | DB2+0 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 5.5436 | Manirul | Completed
115 | 3 | 8/11 | DA+9 | 2025-07-15 | 2025-08-03 | Jwala Singh-1 | 45.697 | 4.2575 | Rudra Prasad | Completed
116 | 4 | 30/10 | DA+3 | 2025-07-18 | 2025-08-03 | SK.Samiul -2 | 37.9311 | 3.534 | Haridas | Completed
117 | 5 | 32/3 | DA+6 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.0812 | Suraj Kumar | Completed
118 | 6 | 42/1 | DA+3 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 3.534 | Manirul | Completed
119 | 7 | 40/1 | DA+9 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 4.2575 | Susheel Kumar | Completed
120 | 8 | 6/2 | DA+6 | 2025-08-04 | 2025-08-08 | Jwala Singh-1 | 43.8044 | 4.0812 | Sanjay Kumar | Completed
121 | 9 | 32A/0 | DB1+9 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 6.2219 | Manoj Kumar Gupta | Completed
122 | 10 | 35/2 | DA+6 | 2025-08-01 | 2025-08-09 | Jwala Singh-2 | 43.8044 | 4.0812 | Rudra Prasad | Completed
123 | 11 | 6/12 | DA+1.5 | 2025-08-01 | 2025-08-09 | Pritam Enterprises-1 | 37.1383 | 3.4601 | Sanjay Kumar | Completed
124 | 12 | 31/1 | DA+3 | 2025-08-02 | 2025-08-10 | SK Samiul -1 | 37.9311 | 3.534 | Haridas | Completed
125 | 13 | 31/2 | DA+1.5 | 2025-08-04 | 2025-08-11 | SK.Samiul -2 | 37.1383 | 3.4601 | Haridas | Completed
126 | 14 | 42/2 | DA+9 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 4.2575 | Manirul | Completed
127 | 15 | 40/9 | DA+9 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 4.2575 | Manirul | Completed
128 | 16 | 6/5 | DA+9 | 2025-08-02 | 2025-08-13 | Pritam Enterprises-2 | 45.697 | 4.2575 | Sanjay Kumar | Completed
129 | 17 | 32/4 | DA+9 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 4.2575 | Suraj Kumar | Completed
130 | 18 | 6/3 | DA+3 | 2025-08-08 | 2025-08-14 | Jwala Singh-1 | 37.9311 | 3.534 | Sanjay Kumar | Completed | Sanjay
131 | 19 | 8A/0 | DB1+12 | 2025-08-07 | 2025-08-14 | Punam Kumari-2 | 70.7883 | 6.5952 | Sanjay Kumar | Completed | Hazari Yadav
132 | 20 | 33/2 | DA+9 | 2025-08-09 | 2025-08-17 | Punam Kumari-1 | 45.697 | 4.2575 | Manoj Kumar Gupta | Completed
133 | 21 | 6/10 | DA+1.5 | 2025-08-09 | 2025-08-18 | Pritam Enterprises-1 | 37.1383 | 3.4601 | Sanjay Kumar | Completed
134 | 22 | 9/5 | DA+3 | 2025-08-15 | 2025-08-19 | Punam Kumari-2 | 37.9311 | 3.534 | Narayan Mahto | Completed
135 | 23 | 42/3 | DB1+9 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 6.2219 | Manirul | Completed
136 | 24 | 5/6 | DA+3 | 2025-08-08 | 2025-08-20 | Pritam Enterprises-4 | 37.9311 | 3.534 | Deshraj | Completed | Sanjay
137 | 25 | 40/7 | DA+3 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 3.534 | Susheel Kumar | Completed
138 | 26 | 1/0 | DD60+0 | 2025-08-07 | 2025-08-21 | Pritam Enterprises-3 | 83.1335 | 7.7454 | Nishit Mondal | Completed | Suraj
139 | 27 | 6/0 | DB1+9 | 2025-08-13 | 2025-08-21 | Jwala Singh-2 | 66.7809 | 6.2219 | Rudra Prasad | Completed
140 | 28 | 6/6 | DA-3 | 2025-08-14 | 2025-08-21 | Pritam Enterprises-2 | 34.7898 | 3.2413 | Indrajeet Patel | Completed
141 | 29 | 6/4 | DA+9 | 2025-08-15 | 2025-08-21 | Jwala Singh-1 | 45.697 | 4.2575 |  | Completed
142 | 30 | 30/9 | DA-3 | 2025-08-12 | 2025-08-21 | SK.Samiul -2 | 34.7898 | 3.2413 | Haridas | Completed
143 | 31 | 31/3 | DA+3 | 2025-08-12 | 2025-08-22 | SK Samiul -1 | 37.9311 | 3.534 | Khooblal Mahto | Completed
144 | 32 | 33/9 | DA+1.5 | 2025-08-18 | 2025-08-22 | Punam Kumari-1 | 37.1383 | 3.4601 | Manoj Kumar Gupta | Completed
145 | 33 | 6/11 | DA-1.5 | 2025-08-19 | 2025-08-25 | Pritam Enterprises-1 | 35.6018 | 3.317 | Sanjay Kumar | Completed
146 | 34 | 9/6 | DA+3 | 2025-08-20 | 2025-08-25 | Punam Kumari-2 | 37.9311 | 3.534 | Narayan Mahto | Completed
147 | 35 | 43/2 | DA+6 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 4.0812 | Manirul | Completed
148 | 36 | 31/10 | DA+4.5 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.999 | Suraj Kumar | Completed
149 | 37 | 2A/1 | DA+0 | 2025-08-21 | 2025-08-27 | Pritam Enterprises-3 | 36.1598 | 3.3689 | Nishit Mondal | Completed
150 | 38 | 4A/4 | DA+6 | 2025-08-18 | 2025-08-28 | Govind Mahto-1 | 43.8044 | 4.0812 | Aman Singh | Completed
151 | 39 | 5/5 | DA+6 | 2025-08-20 | 2025-08-28 | Pritam Enterprises-4 | 43.8044 | 4.0812 | Deshraj | Completed | Sanjay
152 | 40 | 6/7 | DA+1.5 | 2025-08-22 | 2025-08-28 | Pritam Enterprises-2 | 37.1383 | 3.4601 | Indrajeet Patel | Completed
153 | 41 | 5/10 | DA+9 | 2025-08-22 | 2025-08-28 | Jwala Singh-1 | 45.697 | 4.2575 | Aman Singh | Completed
154 | 42 | 9/7 | DA+9 | 2025-08-23 | 2025-08-29 | Punam Kumari-2 | 45.697 | 4.2575 | Narayan Mahto | Completed
155 | 43 | 33/7 | DA+6 | 2025-08-23 | 2025-08-30 | Punam Kumari-1 | 43.8044 | 4.0812 | Manoj Kumar Gupta | Completed
156 | 44 | 31/4 | DA-1.5 | 2025-08-22 | 2025-08-31 | SK.Samiul -2 | 35.6018 | 3.317 | Haridas | Completed
157 | 1 | 5A/0 | DB1+12 | 2025-08-22 | 2025-09-01 | Jwala Singh-2 | 70.7883 | 6.5952 | Rudra Prasad | Completed
158 | 2 | 32A/1 | DA+6 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 4.0812 | Raju Mahto | Completed
159 | 3 | 6/9 | DA+6 | 2025-08-23 | 2025-09-02 | Pritam Enterprises-2 | 43.8044 | 4.0812 | Sanjay Kumar | Completed
160 | 4 | 2A/2 | DA+3 | 2025-08-28 | 2025-09-02 | Pritam Enterprises-3 | 37.9311 | 3.534 | Nishit Mondal | Completed
161 | 5 | 43/3 | DA-1.5 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.317 | Manirul | Completed
162 | 6 | 31/5 | DA+6 | 2025-08-23 | 2025-09-03 | SK Samiul -1 | 43.8044 | 4.0812 | Khooblal Mahto | Completed
163 | 7 | 31/9 | DA+1.5 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.4601 | Suraj Kumar | Completed
164 | 8 | 44/1 | DA+3 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.534 | Susheel Kumar | Completed
165 | 9 | 33/3 | DA+3 | 2025-08-31 | 2025-09-04 | Punam Kumari-1 | 37.9311 | 3.534 | Manoj Kumar Gupta | Completed
166 | 10 | 5/9 | DA+6 | 2025-08-29 | 2025-09-05 | Jwala Singh-1 | 43.8044 | 4.0812 | Indrajeet Patel | Completed
167 | 11 | 6/8 | DA+3 | 2025-08-29 | 2025-09-06 | Pritam Enterprises-2 | 37.9311 | 3.534 | Aman Singh | Completed
168 | 12 | 9/0 | DB1+12 | 2025-08-30 | 2025-09-06 | Punam Kumari-2 | 70.7883 | 6.5952 | Narayan Mahto | Completed
169 | 13 | 4A/3 | DA+9 | 2025-08-29 | 2025-09-06 | Govind Mahto-1 | 45.697 | 4.2575 | Aman Singh | Completed
170 | 14 | 43/4 | DA+0 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 3.3689 | Manirul | Completed
171 | 15 | 5/4 | DA-1.5 | 2025-08-29 | 2025-09-08 | Pritam Enterprises-4 | 35.6018 | 3.317 | Deshraj | Completed
172 | 16 | 2A/3 | DA+3 | 2025-09-03 | 2025-09-08 | Pritam Enterprises-3 | 37.9311 | 3.534 | Nishit Mondal | Completed
173 | 17 | 4A/5 | DA+9 | 2025-08-25 | 2025-09-08 | Govind Mahto-2 | 45.697 | 4.2575 | Aman Singh | Completed
174 | 18 | 30/6 | DA+6 | 2025-08-29 | 2025-09-08 | Punam Kumari-3 | 43.8044 | 4.0812 | kartik | Completed
175 | 19 | 5/7 | DA+9 | 2025-09-02 | 2025-09-09 | Jwala Singh-2 | 45.697 | 4.2575 | Rudra Prasad | Completed
176 | 20 | 44/2 | DA+3 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 3.534 | Susheel Kumar | Completed
177 | 21 | 33/4 | DA+3 | 2025-09-05 | 2025-09-09 | Punam Kumari-1 | 37.9311 | 3.534 | Manoj Kumar Gupta | Completed
178 | 22 | 33/1 | DA+9 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 4.2575 | Bhupendra choudhary | Completed
179 | 23 | 3A/1 | DA+3 | 2025-09-03 | 2025-09-11 | Pritam Enterprises-1 | 37.9311 | 3.534 | Sanjay Kumar | Completed
180 | 24 | 43/6 | DA+3 | 2025-09-08 | 2025-09-11 | Fouzi Ratto | 37.9311 | 3.534 | Susheel Kumar | Completed
181 | 25 | 4/5 | DA+6 | 2025-09-06 | 2025-09-12 | Jwala Singh-1 | 43.8044 | 4.0812 | Kamal Ravidas | Completed
182 | 26 | 30/7 | DA-3 | 2025-09-09 | 2025-09-13 | Punam Kumari-3 | 34.7898 | 3.2413 | Kartik | Completed
183 | 27 | 32/0 | DB2+0 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.5436 | Suraj Kumar | Completed
184 | 28 | 30/4 | DA+9 | 2025-09-09 | 2025-09-15 | Punam Kumari-4 | 45.697 | 4.2575 | Kartik | Completed
185 | 29 | 18/0 | DB2+6 | 2025-09-07 | 2025-09-15 | Punam Kumari-2 | 69.376 | 6.4637 | Kamal Ravidas | Completed
186 | 30 | 2A/4 | DA+3 | 2025-09-09 | 2025-09-15 | Pritam Enterprises-3 | 37.9311 | 3.534 | Nishit Mondal | Completed
187 | 31 | 5/8 | DA+6 | 2025-09-10 | 2025-09-15 | Jwala Singh-2 | 43.8044 | 4.0812 | Rudra Prasad | Completed
188 | 32 | 44/3 | DA+3 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 3.534 | Khooblal Mahto | Completed
189 | 33 | 3A/5 | DA+3 | 2025-09-07 | 2025-09-15 | Pritam Enterprises-2 | 37.9311 | 3.534 | Akabar Ali | Completed
190 | 34 | 4A/2 | DA+6 | 2025-09-07 | 2025-09-16 | Govind Mahto-1 | 43.8044 | 4.0812 | Aman Singh | Completed
191 | 35 | 31/7 | DA+0 | 2025-09-10 | 2025-09-16 | Punam Kumari-1 | 36.1598 | 3.3689 | Manoj Kumar Gupta | Completed
192 | 36 | 31/6 | DA+3 | 2025-09-04 | 2025-09-18 | SK Samiul -1 | 37.9311 | 3.534 | Haridas | Completed
193 | 37 | 4A/6 | DA+6 | 2025-09-09 | 2025-09-18 | Govind Mahto-2 | 43.8044 | 4.0812 | Aman Singh | Completed
194 | 38 | 43/8 | DA+0 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 36.1598 | 3.3689 | Khooblal Mahto | Completed
195 | 39 | 44/4 | DA+9 | 2025-09-16 | 2025-09-19 | Ved Prakash | 45.697 | 4.2575 | Khooblal Mahto | Completed
196 | 40 | 3A/2 | DA+9 | 2025-09-12 | 2025-09-19 | Pritam Enterprises-1 | 45.697 | 4.2575 | Sanjay Kumar | Completed
197 | 41 | 40A/0 | DA+9 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 45.697 | 4.2575 | Susheel Kumar | Completed
198 | 42 | 33/0 | DA+0 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 36.1598 | 3.3689 | Raju Mahto | Completed
199 | 43 | 18/1 | DA+3 | 2025-09-16 | 2025-09-20 | Punam Kumari-2 | 37.9311 | 3.534 | Kamal Ravidas | Completed
200 | 44 | 31/8 | DB1+9 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 66.7809 | 6.2219 | Suraj Kumar | Completed
201 | 45 | 30/8 | DA+3 | 2025-09-14 | 2025-09-22 | Punam Kumari-3 | 37.9311 | 3.534 | Abrar Ali | Completed
202 | 46 | 2A/5 | DA+3 | 2025-09-16 | 2025-09-23 | Pritam Enterprises-3 | 37.9311 | 3.534 | Nishit Mondal | Completed
203 | 47 | 44/5 | DA+0 | 2025-09-20 | 2025-09-23 | Ved Prakash | 36.1598 | 3.3689 | Khooblal Mahto | Completed
204 | 48 | 3A/6 | DA+0 | 2025-09-16 | 2025-09-24 | Pritam Enterprises-2 | 36.1598 | 3.3689 | Akabar Ali | Completed
205 | 49 | 4A/0 | DB1+3 | 2025-09-13 | 2025-09-24 | Jwala Singh-1 | 57.9632 | 5.4003 | Kamal Ravidas | Completed
206 | 50 | 30/0 | DB1+0 | 2025-09-11 | 2025-09-25 | Punam Kumari-4 | 55.4509 | 5.1663 | Manoj Gupta | Completed | Mithilesh
207 | 51 | 5/1 | DA+6 | 2025-09-13 | 2025-09-25 | Jwala Singh-2 | 43.8044 | 4.0812 | Rudra Prasad | Completed
208 | 52 | 4A/1 | DA+6 | 2025-09-18 | 2025-09-25 | Govind Mahto-1 | 43.8044 | 4.0812 | Rahul Ravidas | Completed
209 | 53 | 20/1 | DA-3 | 2025-09-19 | 2025-09-25 | Punam Kumari-1 | 34.7898 | 3.2413 | Manoj Kumar Gupta | Completed
210 | 54 | 18/2 | DA+1.5 | 2025-09-21 | 2025-09-25 | Punam Kumari-2 | 37.1383 | 3.4601 | Narayan Mahto | Completed
211 | 55 | 12/0 | DB1+9 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 6.2219 | Bhupendra choudhary | Completed
212 | 56 | 3A/3 | DA+0 | 2025-09-20 | 2025-09-27 | Pritam Enterprises-1 | 36.1598 | 3.3689 | Sanjay Kumar | Completed | Sintu
213 | 57 | 43/7 | DA+0 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 3.3689 | Khooblal Mahto | Completed
214 | 58 | 44/0 | DB1+6 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.0585 | Manoj Kumar Choudhary | Completed
215 | 59 | 40/11 | DA+9 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 4.2575 | Susheel Kumar | Completed
216 | 60 | 5/0 | DB1+6 | 2025-09-19 | 2025-09-30 | Govind Mahto-2 | 65.0278 | 6.0585 | Aman Singh | Completed
217 | 61 | 20/2 | DA-3 | 2025-09-26 | 2025-09-30 | Punam Kumari-1 | 34.7898 | 3.2413 | Rahul Ravidas | Completed
218 | 62 | 18/3 | DA+6 | 2025-09-26 | 2025-09-30 | Punam Kumari-2 | 43.8044 | 4.0812 | Najirul | Completed
219 | 63 | 2A/6 | DA+6 | 2025-09-24 | 2025-09-30 | Pritam Enterprises-3 | 43.8044 | 4.0812 | Narayan Mahto | Completed
220 | 64 | 5/3 | DA+9 | 2025-09-09 | 2025-09-30 | Pritam Enterprises-4 | 45.697 | 4.2575 | Sanjay Kumar | Completed
221 | 65 | 5/2 | DA+9 | 2025-09-26 | 2025-09-30 | Jwala Singh-2 | 45.697 | 4.2575 | Rudra Prasad | Completed
222 | 1 | 30/2 | DA+9 | 2025-09-24 | 2025-10-04 | SK Samiul -1 | 45.697 | 4.2575 | Haridas | Completed
223 | 2 | 41/1 | DA+9 | 2025-09-24 | 2025-10-04 | Amar Kumar Singh | 45.697 | 4.2575 | Suraj Kumar | Completed
224 | 3 | 29A/5 | DA+6 | 2025-09-26 | 2025-10-04 | Punam Kumari-4 | 43.8044 | 4.0812 | Manoj Gupta | Completed
225 | 4 | 15/8 | DA+1.5 | 2025-09-27 | 2025-10-04 | Bhairaw Mahto | 37.1383 | 3.4601 | Bhupendra choudhary | Completed
226 | 5 | 18/4 | DA-3 | 2025-10-01 | 2025-10-06 | Punam Kumari-2 | 34.7898 | 3.2413 | Najirul | Completed
227 | 6 | 3B/2 | DA+9 | 2025-09-26 | 2025-10-07 | Govind Mahto-1 | 45.697 | 4.2575 | Aman Singh | Completed | Tulshi
228 |  | 45/0 | DB1+9 | 2025-09-28 |  | Ved Prakash | 66.7809 | 6.2219 | Khooblal Mahto | WIP
229 |  | 40/10 | DA+3 | 2025-09-30 |  | Kartik Mahto | 37.9311 | 3.534 | Susheel Kumar | WIP
230 |  | 3B/0 | DB1+9 | 2025-09-25 |  | Pritam Enterprises-2 | 66.7809 | 6.2219 | Akabar Ali | WIP | Laxman
231 |  | 4/0 | DB2+9 | 2025-09-25 |  | Jwala Singh-1 | 72.1555 | 6.7226 | Kamal Ravidas | WIP | Dharmendra Das
232 |  | 46/0 | DB1+12 | 2025-09-30 |  | Fouzi Ratto | 70.7883 | 6.5952 | Manoj Kumar Choudhary | WIP
233 |  | 15/0 | DD60+25 | 2025-10-01 |  | Govind Mahto-2 | 137.0461 | 12.7684 | Aman Singh | WIP | Gangadhar
234 |  | 20/0 | DD60+3 | 2025-10-01 |  | Punam Kumari-1 | 87.0213 | 8.1076 | Rahul Ravidas | WIP | Gulshan Kumar
235 |  | 3A/4 | DA+0 | 2025-10-01 |  | Pritam Enterprises-3 | 36.1598 | 3.3689 | Abhiya | WIP | Suraj
236 |  | 10/0 | DB1+6 | 2025-10-01 |  | Pritam Enterprises-1 | 65.0278 | 6.0585 | Sanjay Kumar | WIP | Sintu
237 |  | 29/0 | DC1+0 | 2025-10-04 |  | Pritam Enterprises-4 | 62.4437 | 5.8178 | Raju Mahto | WIP | Gautam
238 |  | 29/1 | DA+6 | 2025-10-04 |  | Jwala Singh-2 | 43.8044 | 4.0812 | Raju Mahto | WIP | Mukesh
239 |  | 29A/0 | DB1+0 | 2025-10-05 |  | SK Samiul -1 | 55.4509 | 5.1663 | Haridas | WIP | Tajirul
240 |  | 41/0 | DB1+9 | 2025-10-05 |  | Amar Kumar Singh | 66.7809 | 6.2219 | Suraj Kumar | WIP | 03 days delay due to 11kv pole shiting
241 |  | 29A/4 | DA+3 | 2025-10-05 |  | Punam Kumari-4 | 37.9311 | 3.534 | Manoj Gupta | WIP | Mithilesh
242 |  | 17/0 | DC1+3 | 2025-10-05 |  | Bhairaw Mahto | 65.8725 | 6.1372 | Bhupendra choudhary | ROW | Guy rop issue
243 |  | 18/5 | DA+0 | 2025-10-07 |  | Punam Kumari-2 | 36.1598 | 3.3689 | Najirul | WIP | Hazari Yadav
244 |  | 3B/1 | DA+3 | 2025-10-08 |  | Govind Mahto-1 | 37.9311 | 3.534 | Rundra | WIP | Tulshi
245 |  | 26/0 | DD60+35 | 2025-10-10 |  | Ved Prakash | 173.5609 | 16.1704 | Khooblal Mahto | WIP
246 |  | 40/8 | DA-1.5 | 2025-10-10 |  | Kartik Mahto | 35.6018 | 3.317 | Susheel Kumar | WIP
|  | SL No | Tower Type | Per Tower Unit Weight (As per approved BOM)
|  |  |  | HT Steel (MT) | Mild Steel (MT) | PW (MT) | Bolts & Nuts (MT) | Total Weight of Tower (MT) |  | Construction Revenue
Tower with extensions Up to +9M
|  | 1 | DA+0 | 24.6977 | 9.9267 | 0.030435 | 1.505 | 36.1598 |  | 336894.6611
|  | 2 | DA+3 | 25.5188 | 10.8319 | 0.030629 | 1.5497 | 37.9311 |  | 353397.8779
|  | 3 | DA+6 | 29.4516 | 12.6215 | 0.030759 | 1.7006 | 43.8044 |  | 408118.8097
|  | 4 | DA+9 | 30.2474 | 13.6585 | 0.031055 | 1.76 | 45.697 |  | 425751.8425
|  | 5 | DA-1.5 | 24.4036 | 9.6764 | 0.030223 | 1.4915 | 35.6018 |  | 331695.9203
|  | 6 | DA-3 | 23.9488 | 9.3496 | 0.030211 | 1.4612 | 34.7898 |  | 324131.0934
|  | 7 | DA+4.5 | 28.9333 | 12.2838 | 0.030687 | 1.674 | 42.9218 |  | 399895.7201
|  | 8 | DA+1.5 | 25.2614 | 10.3136 | 0.030519 | 1.5328 | 37.1383 |  | 346011.8226
|  | 9 | DB1+0 | 42.0844 | 10.8263 | 0.059184 | 2.4809 | 55.4509 |  | 516626.7066
|  | 10 | DB1+3 | 43.7466 | 11.6153 | 0.061852 | 2.5394 | 57.9632 |  | 540033.5901
|  | 11 | DB1+6 | 49.1264 | 12.9888 | 0.074512 | 2.838 | 65.0278 |  | 605853.4125
|  | 12 | DB1+9 | 49.7414 | 14.0342 | 0.074608 | 2.9307 | 66.7809 |  | 622186.9697
|  | 13 | DB2+0 | 44.6465 | 12.2854 | 0.066186 | 2.5025 | 59.5006 |  | 554357.831
|  | 14 | DB2+3 | 46.2811 | 13.2142 | 0.069438 | 2.5514 | 62.1162 |  | 578726.2869
|  | 15 | DB2+6 | 51.442 | 14.984 | 0.081 | 2.869 | 69.376 |  | 646365.0918
|  | 16 | DB2+9 | 52.842 | 16.267 | 0.082046 | 2.9645 | 72.1555 |  | 672261.6213
|  | 17 | DC1+0 | 47.9692 | 11.8414 | 0.061932 | 2.5712 | 62.4437 |  | 581778.0178
|  | 18 | DC1+3 | 50.1786 | 12.959 | 0.06504 | 2.6698 | 65.8725 |  | 613723.3938
|  | 19 | DC2+0 | 51.8467 | 12.8185 | 0.062996 | 2.5335 | 67.2617 |  | 626666.7579
|  | 20 | DC2-3 | 50.4134 | 11.9351 | 0.061876 | 2.474 | 64.8843 |  | 604516.623
|  | 21 | DD45+0 | 55.8134 | 14.8039 | 0.058151 | 2.569 | 73.2445 |  | 682407.7346
|  | 22 | DD45+3 | 60.9578 | 13.3682 | 0.059057 | 2.692 | 77.0769 |  | 718113.4431
|  | 23 | DD60+0 | 62.4268 | 17.6311 | 0.067222 | 3.0084 | 83.1335 |  | 774541.7604
|  | 24 | DD60+3 | 66.1099 | 17.6755 | 0.069954 | 3.166 | 87.0213 |  | 810763.9014
|  | 25 | DD60+9 | 73.4565 | 24.8501 | 0.07859 | 3.5674 | 101.9526 |  | 949875.9872
|  | 26 | DB1+12 | 49.5411 | 18.1668 | 0.08738 | 2.993 | 70.7883 |  | 659522.9389
|  | 27 | DC2+15 | 71.12 | 22.269 | 0.097336 | 3.3936 | 96.8799 |  | 902614.5275
|  | 28 | DD60+18 | 84.6016 | 36.0432 | 0.10177 | 4.2034 | 124.95 |  | 1164138.7108
|  | 29 | DD60+25 | 90.6026 | 41.946 | 0.10993 | 4.3876 | 137.0461 |  | 1276836.6981
|  | 30 | DD60+35 | 130.9692 | 37.3037 | 0.10993 | 5.1781 | 173.5609 |  | 1617039.2474
|  | 31 | DCT+0M (TP) | 59.5334 | 19.752 | 0.11 | 2.868 | 82.2634 |  | 766434.74
Formulas:
Starting Date = [Completion Date, row above]
Starting Date = [Completion Date, row above]+1