## ProdDailyExpandedSingles
Work Date | Start Date | Complete Date | Gang name | Tower Weight | Productivity | Project Name | Location No. | Status
2023-09-30 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.7305 | 2.3582 | TA325 | 127/1 | Completed
2023-10-01 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.7305 | 2.3582 | TA325 | 127/1 | Completed
2023-10-02 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.7305 | 2.3582 | TA325 | 127/1 | Completed
2023-10-03 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.7305 | 2.3582 | TA325 | 127/1 | Completed
2023-10-04 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.7305 | 2.3582 | TA325 | 127/1 | Completed
2023-10-05 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.7305 | 2.3582 | TA325 | 127/1 | Completed
2023-10-06 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.7305 | 2.3582 | TA325 | 127/1 | Completed
2023-10-07 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.7305 | 2.3582 | TA325 | 127/1 | Completed
2023-10-08 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.7305 | 2.3582 | TA325 | 127/1 | Completed
2023-10-09 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.7305 | 2.3582 | TA325 | 127/1 | Completed
2023-10-10 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.7305 | 2.3582 | TA325 | 127/1 | Completed
2023-10-11 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.7305 | 2.3582 | TA325 | 127/1 | Completed
2023-10-12 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.7305 | 2.3582 | TA325 | 127/1 | Completed
2023-10-13 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.7305 | 2.3582 | TA325 | 127/1 | Completed
2023-10-14 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.7305 | 2.3582 | TA325 | 127/1 | Completed
2023-10-15 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.7305 | 2.3582 | TA325 | 127/1 | Completed
2023-10-16 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 127/2 | Completed
2023-10-17 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 127/2 | Completed
2023-10-18 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 127/2 | Completed
2023-10-19 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 127/2 | Completed
2023-10-20 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 127/2 | Completed
2023-10-21 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 127/2 | Completed
2023-10-22 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 127/2 | Completed
2023-10-23 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 127/2 | Completed
2023-10-24 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 127/2 | Completed
2023-10-25 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 127/2 | Completed
2023-10-26 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 127/2 | Completed
2023-10-27 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 127/2 | Completed
2023-10-28 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 127/2 | Completed
2023-10-29 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 127/2 | Completed
2023-11-01 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.7305 | 4.1923 | TA325 | 135A/4 | Completed
2023-11-02 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.7305 | 4.1923 | TA325 | 135A/4 | Completed
2023-11-03 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.7305 | 4.1923 | TA325 | 135A/4 | Completed
2023-11-04 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.7305 | 4.1923 | TA325 | 135A/4 | Completed
2023-11-05 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.7305 | 4.1923 | TA325 | 135A/4 | Completed
2023-11-06 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.7305 | 4.1923 | TA325 | 135A/4 | Completed
2023-11-07 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.7305 | 4.1923 | TA325 | 135A/4 | Completed
2023-11-08 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.7305 | 4.1923 | TA325 | 135A/4 | Completed
2023-11-09 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.7305 | 4.1923 | TA325 | 135A/4 | Completed
2023-11-11 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.7305 | 5.3901 | TA325 | 135/2 | Completed
2023-11-12 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.7305 | 5.3901 | TA325 | 135/2 | Completed
2023-11-13 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.7305 | 5.3901 | TA325 | 135/2 | Completed
2023-11-14 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.7305 | 5.3901 | TA325 | 135/2 | Completed
2023-11-15 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.7305 | 5.3901 | TA325 | 135/2 | Completed
2023-11-16 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.7305 | 5.3901 | TA325 | 135/2 | Completed
2023-11-17 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.7305 | 5.3901 | TA325 | 135/2 | Completed
2023-11-19 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.7305 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-20 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.7305 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-21 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.7305 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-22 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.7305 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-23 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.7305 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-24 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.7305 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-25 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.7305 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-26 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.7305 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-27 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.7305 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-28 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.7305 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-29 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.7305 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-30 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.7305 | 2.9023 | TA325 | 135A/7 | Completed
2023-12-01 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.7305 | 2.9023 | TA325 | 135A/7 | Completed
2023-12-02 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 133/1 | Completed
2023-12-03 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 133/1 | Completed
2023-12-04 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 133/1 | Completed
2023-12-05 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 133/1 | Completed
2023-12-06 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 133/1 | Completed
2023-12-07 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 133/1 | Completed
2023-12-08 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 133/1 | Completed
2023-12-09 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 133/1 | Completed
2023-12-10 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 133/1 | Completed
2023-12-11 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 133/1 | Completed
2023-12-12 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 133/1 | Completed
2023-12-13 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 133/1 | Completed
2023-12-14 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 133/1 | Completed
2023-12-15 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 133/1 | Completed
2024-01-04 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.7282 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-05 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.7282 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-06 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.7282 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-07 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.7282 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-08 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.7282 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-09 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.7282 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-10 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.7282 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-11 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.7282 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-12 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.7282 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-12 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.7305 | 5.3901 | TA325 | 135B/3 | Completed
2024-01-13 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.7305 | 5.3901 | TA325 | 135B/3 | Completed
2024-01-14 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.7305 | 5.3901 | TA325 | 135B/3 | Completed
2024-01-15 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.7305 | 5.3901 | TA325 | 135B/3 | Completed
2024-01-16 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.7305 | 5.3901 | TA325 | 135B/3 | Completed
2024-01-17 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.7305 | 5.3901 | TA325 | 135B/3 | Completed
2024-01-18 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.7305 | 5.3901 | TA325 | 135B/3 | Completed
2024-01-18 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135B/2 | Completed
2024-01-19 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135B/2 | Completed
2024-01-20 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135B/2 | Completed
2024-01-21 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135B/2 | Completed
2024-01-22 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135B/2 | Completed
2024-01-23 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135B/2 | Completed
2024-01-23 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135A/3 | Completed
2024-01-24 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135A/3 | Completed
2024-01-25 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135A/3 | Completed
2024-01-26 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135A/3 | Completed
2024-01-27 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135A/3 | Completed
2024-01-28 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135A/3 | Completed
2024-01-28 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135B/5 | Completed
2024-01-29 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135B/5 | Completed
2024-01-30 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135B/5 | Completed
2024-01-31 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135B/5 | Completed
2024-02-01 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135B/5 | Completed
2024-02-02 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135B/5 | Completed
2024-02-02 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.4178 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-03 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.4178 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-04 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.7305 | 3.773 | TA325 | 132/2 | Completed
2024-02-04 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.4178 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-04 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.7305 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-05 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.7305 | 3.773 | TA325 | 132/2 | Completed
2024-02-05 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.4178 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-05 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.7305 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-06 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.7305 | 3.773 | TA325 | 132/2 | Completed
2024-02-06 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.4178 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-06 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.7305 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-07 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.7305 | 3.773 | TA325 | 132/2 | Completed
2024-02-07 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.4178 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-07 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.7305 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-08 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.7305 | 3.773 | TA325 | 132/2 | Completed
2024-02-08 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.4178 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-08 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.7305 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-09 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.7305 | 3.773 | TA325 | 132/2 | Completed
2024-02-09 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.4178 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-09 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.7305 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-10 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.7305 | 3.773 | TA325 | 132/2 | Completed
2024-02-10 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.7305 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-11 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.7305 | 3.773 | TA325 | 132/2 | Completed
2024-02-11 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.7305 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-12 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.7305 | 3.773 | TA325 | 132/2 | Completed
2024-02-12 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.7305 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-13 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.7305 | 3.773 | TA325 | 132/2 | Completed
2024-02-13 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.4178 | 6.0464 | TA325 | 133/0 | Completed
2024-02-13 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.7305 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-14 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.4178 | 6.0464 | TA325 | 133/0 | Completed
2024-02-14 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.7305 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-15 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.4178 | 6.0464 | TA325 | 133/0 | Completed
2024-02-15 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.7305 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-15 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 133A/3 | Completed
2024-02-16 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.4178 | 6.0464 | TA325 | 133/0 | Completed
2024-02-16 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 133A/3 | Completed
2024-02-17 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.4178 | 6.0464 | TA325 | 133/0 | Completed
2024-02-17 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 133A/3 | Completed
2024-02-18 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.4178 | 6.0464 | TA325 | 133/0 | Completed
2024-02-18 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 133A/3 | Completed
2024-02-19 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.4178 | 6.0464 | TA325 | 133/0 | Completed
2024-02-19 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 133A/3 | Completed
2024-02-20 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.4178 | 6.0464 | TA325 | 133/0 | Completed
2024-02-20 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.7305 | 4.1923 | TA325 | 133/3 | Completed
2024-02-20 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 133A/3 | Completed
2024-02-20 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.7305 | 5.3901 | TA325 | 135B/1 | Completed
2024-02-21 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.4178 | 6.0464 | TA325 | 133/0 | Completed
2024-02-21 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.7305 | 4.1923 | TA325 | 133/3 | Completed
2024-02-21 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.7305 | 5.3901 | TA325 | 135B/1 | Completed
2024-02-22 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.7305 | 4.1923 | TA325 | 133/3 | Completed
2024-02-22 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.7305 | 5.3901 | TA325 | 135B/1 | Completed
2024-02-23 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.7305 | 4.1923 | TA325 | 133/3 | Completed
2024-02-23 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.7305 | 5.3901 | TA325 | 135B/1 | Completed
2024-02-24 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.7305 | 4.1923 | TA325 | 133/3 | Completed
2024-02-24 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.7305 | 5.3901 | TA325 | 135B/1 | Completed
2024-02-25 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.7305 | 4.1923 | TA325 | 133/3 | Completed
2024-02-25 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.7305 | 5.3901 | TA325 | 135B/1 | Completed
2024-02-26 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.7305 | 4.1923 | TA325 | 133/3 | Completed
2024-02-26 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.7305 | 5.3901 | TA325 | 135B/1 | Completed
2024-02-26 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135/3 | Completed
2024-02-27 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.7305 | 4.1923 | TA325 | 133/3 | Completed
2024-02-27 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.7305 | 6.2884 | TA325 | 133/2 | Completed
2024-02-27 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135/3 | Completed
2024-02-28 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.7305 | 4.1923 | TA325 | 133/3 | Completed
2024-02-28 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.7305 | 6.2884 | TA325 | 133/2 | Completed
2024-02-28 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135/3 | Completed
2024-02-29 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.7305 | 6.2884 | TA325 | 133/2 | Completed
2024-02-29 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135/3 | Completed
2024-03-01 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.7305 | 6.2884 | TA325 | 133/2 | Completed
2024-03-01 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135/3 | Completed
2024-03-02 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.7305 | 6.2884 | TA325 | 133/2 | Completed
2024-03-02 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135/3 | Completed
2024-03-02 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-03 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.7305 | 6.2884 | TA325 | 133/2 | Completed
2024-03-03 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.7305 | 6.2884 | TA325 | 133/5 | Completed
2024-03-03 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-04 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.7305 | 6.2884 | TA325 | 133/5 | Completed
2024-03-04 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-05 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.7305 | 6.2884 | TA325 | 133/5 | Completed
2024-03-05 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-06 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.7305 | 6.2884 | TA325 | 133/5 | Completed
2024-03-06 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-07 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.7305 | 6.2884 | TA325 | 133/5 | Completed
2024-03-07 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-08 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.7305 | 6.2884 | TA325 | 133/5 | Completed
2024-03-08 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.4178 | 9.0696 | TA325 | 133A/0 | Completed
2024-03-08 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-09 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.4178 | 9.0696 | TA325 | 133A/0 | Completed
2024-03-09 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-10 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.4178 | 9.0696 | TA325 | 133A/0 | Completed
2024-03-10 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-11 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.4178 | 9.0696 | TA325 | 133A/0 | Completed
2024-03-11 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-12 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.4178 | 9.0696 | TA325 | 133A/0 | Completed
2024-03-12 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-13 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.4178 | 9.0696 | TA325 | 133A/0 | Completed
2024-03-13 | 2024-03-13 | 2024-03-13 | Lalan Mahto | 37.7305 | 37.7305 | TA325 | 133A/1 | Completed
2024-03-13 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-14 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-15 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-16 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-17 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-18 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-19 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-20 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-21 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-22 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-23 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-24 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-25 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-26 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-27 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-28 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-29 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-30 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-31 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-01 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-02 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-03 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-04 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-05 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-06 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-07 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-08 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-09 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-10 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-11 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-13 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.7282 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-14 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.7282 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-15 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.7282 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-16 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.7282 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-17 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.7282 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-18 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.7282 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-19 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.7282 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-20 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.7305 | 7.5461 | TA325 | 133/4 | Completed
2024-04-21 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.7305 | 7.5461 | TA325 | 133/4 | Completed
2024-04-22 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.7305 | 7.5461 | TA325 | 133/4 | Completed
2024-04-23 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.7305 | 7.5461 | TA325 | 133/4 | Completed
2024-04-24 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.7305 | 7.5461 | TA325 | 133/4 | Completed
2024-04-25 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.2538 | 10.709 | TA325 | 129A/0 | Completed
2024-04-26 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.2538 | 10.709 | TA325 | 129A/0 | Completed
2024-04-27 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.2538 | 10.709 | TA325 | 129A/0 | Completed
2024-04-28 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.2538 | 10.709 | TA325 | 129A/0 | Completed
2024-04-29 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.2538 | 10.709 | TA325 | 129A/0 | Completed
2024-04-30 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.2538 | 10.709 | TA325 | 129A/0 | Completed
2024-05-01 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.7305 | 1.9858 | TA325 | 135/6 | Completed
2024-05-02 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.7305 | 1.9858 | TA325 | 135/6 | Completed
2024-05-02 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.7305 | 6.2884 | TA325 | 129A/1 | Completed
2024-05-03 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.7305 | 1.9858 | TA325 | 135/6 | Completed
2024-05-03 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.7305 | 6.2884 | TA325 | 129A/1 | Completed
2024-05-04 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.7305 | 1.9858 | TA325 | 135/6 | Completed
2024-05-04 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.7305 | 6.2884 | TA325 | 129A/1 | Completed
2024-05-05 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.7305 | 1.9858 | TA325 | 135/6 | Completed
2024-05-05 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.7305 | 6.2884 | TA325 | 129A/1 | Completed
2024-05-06 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.7305 | 1.9858 | TA325 | 135/6 | Completed
2024-05-06 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.7305 | 6.2884 | TA325 | 129A/1 | Completed
2024-05-07 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.7305 | 1.9858 | TA325 | 135/6 | Completed
2024-05-07 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.7305 | 6.2884 | TA325 | 129A/1 | Completed
2024-05-07 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.4589 | 6.5765 | TA325 | 129A/2 | Completed
2024-05-07 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.4178 | 4.5348 | TA325 | 130/0 | Completed
2024-05-07 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.7305 | 3.1442 | TA325 | 137/4 | Completed
2024-05-08 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.7305 | 1.9858 | TA325 | 135/6 | Completed
2024-05-08 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.4589 | 6.5765 | TA325 | 129A/2 | Completed
2024-05-08 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.4178 | 4.5348 | TA325 | 130/0 | Completed
2024-05-08 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.7305 | 3.1442 | TA325 | 137/4 | Completed
2024-05-09 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.7305 | 1.9858 | TA325 | 135/6 | Completed
2024-05-09 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.4589 | 6.5765 | TA325 | 129A/2 | Completed
2024-05-09 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.4178 | 4.5348 | TA325 | 130/0 | Completed
2024-05-09 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.7305 | 3.1442 | TA325 | 137/4 | Completed
2024-05-10 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.7305 | 1.9858 | TA325 | 135/6 | Completed
2024-05-10 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.4589 | 6.5765 | TA325 | 129A/2 | Completed
2024-05-10 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.4178 | 4.5348 | TA325 | 130/0 | Completed
2024-05-10 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.7305 | 3.1442 | TA325 | 137/4 | Completed
2024-05-11 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.7305 | 1.9858 | TA325 | 135/6 | Completed
2024-05-11 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.4589 | 6.5765 | TA325 | 129A/2 | Completed
2024-05-11 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.4178 | 4.5348 | TA325 | 130/0 | Completed
2024-05-11 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.7305 | 3.1442 | TA325 | 137/4 | Completed
2024-05-12 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.7305 | 1.9858 | TA325 | 135/6 | Completed
2024-05-12 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.4589 | 6.5765 | TA325 | 129A/2 | Completed
2024-05-12 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.4178 | 4.5348 | TA325 | 130/0 | Completed
2024-05-12 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.7305 | 3.1442 | TA325 | 137/4 | Completed
2024-05-13 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.7305 | 1.9858 | TA325 | 135/6 | Completed
2024-05-13 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.4178 | 4.5348 | TA325 | 130/0 | Completed
2024-05-13 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.7305 | 3.1442 | TA325 | 137/4 | Completed
2024-05-14 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.7305 | 1.9858 | TA325 | 135/6 | Completed
2024-05-14 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.4178 | 4.5348 | TA325 | 130/0 | Completed
2024-05-14 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.7305 | 3.1442 | TA325 | 137/4 | Completed
2024-05-15 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.7305 | 1.9858 | TA325 | 135/6 | Completed
2024-05-15 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.4178 | 4.5348 | TA325 | 130/0 | Completed
2024-05-15 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.7305 | 3.1442 | TA325 | 137/4 | Completed
2024-05-16 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.7305 | 1.9858 | TA325 | 135/6 | Completed
2024-05-16 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.4178 | 4.5348 | TA325 | 130/0 | Completed
2024-05-16 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.7305 | 3.1442 | TA325 | 137/4 | Completed
2024-05-17 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.7305 | 1.9858 | TA325 | 135/6 | Completed
2024-05-17 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.4178 | 4.5348 | TA325 | 130/0 | Completed
2024-05-17 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.7305 | 3.1442 | TA325 | 137/4 | Completed
2024-05-18 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.7305 | 1.9858 | TA325 | 135/6 | Completed
2024-05-18 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.4178 | 4.5348 | TA325 | 130/0 | Completed
2024-05-18 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.7305 | 3.1442 | TA325 | 137/4 | Completed
2024-05-19 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.7305 | 1.9858 | TA325 | 135/6 | Completed
2024-05-19 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.7305 | 2.9023 | TA325 | 135/5 | Completed
2024-05-19 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.4589 | 6.5765 | TA325 | 127/4 | Completed
2024-05-19 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 137/3 | Completed
2024-05-20 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.7305 | 2.9023 | TA325 | 135/5 | Completed
2024-05-20 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.4589 | 6.5765 | TA325 | 127/4 | Completed
2024-05-20 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 137/3 | Completed
2024-05-21 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.7305 | 2.9023 | TA325 | 135/5 | Completed
2024-05-21 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.4589 | 6.5765 | TA325 | 127/4 | Completed
2024-05-21 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 137/3 | Completed
2024-05-22 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.7305 | 2.9023 | TA325 | 135/5 | Completed
2024-05-22 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.4589 | 6.5765 | TA325 | 127/4 | Completed
2024-05-22 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 137/3 | Completed
2024-05-23 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.7305 | 2.9023 | TA325 | 135/5 | Completed
2024-05-23 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.4589 | 6.5765 | TA325 | 127/4 | Completed
2024-05-23 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 137/3 | Completed
2024-05-24 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.7305 | 2.9023 | TA325 | 135/5 | Completed
2024-05-24 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.4589 | 6.5765 | TA325 | 127/4 | Completed
2024-05-24 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 137/3 | Completed
2024-05-25 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.7305 | 2.9023 | TA325 | 135/5 | Completed
2024-05-25 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.7305 | 5.3901 | TA325 | 127/3 | Completed
2024-05-25 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.4589 | 5.637 | TA325 | 137/1 | Completed
2024-05-26 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.7305 | 2.9023 | TA325 | 135/5 | Completed
2024-05-26 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.7305 | 5.3901 | TA325 | 127/3 | Completed
2024-05-26 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.4589 | 5.637 | TA325 | 137/1 | Completed
2024-05-27 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.7305 | 2.9023 | TA325 | 135/5 | Completed
2024-05-27 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.7305 | 5.3901 | TA325 | 127/3 | Completed
2024-05-27 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.4589 | 5.637 | TA325 | 137/1 | Completed
2024-05-28 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.7305 | 2.9023 | TA325 | 135/5 | Completed
2024-05-28 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.7305 | 5.3901 | TA325 | 127/3 | Completed
2024-05-28 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.4589 | 5.637 | TA325 | 137/1 | Completed
2024-05-29 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.7305 | 2.9023 | TA325 | 135/5 | Completed
2024-05-29 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.7305 | 5.3901 | TA325 | 127/3 | Completed
2024-05-29 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.4589 | 5.637 | TA325 | 137/1 | Completed
2024-05-30 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.7305 | 2.9023 | TA325 | 135/5 | Completed
2024-05-30 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.7305 | 5.3901 | TA325 | 127/3 | Completed
2024-05-30 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.4589 | 5.637 | TA325 | 137/1 | Completed
2024-05-31 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.7305 | 2.9023 | TA325 | 135/5 | Completed
2024-05-31 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.7305 | 3.43 | TA325 | 135/4 | Completed
2024-05-31 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.7305 | 5.3901 | TA325 | 127/3 | Completed
2024-05-31 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.2376 | 6.5671 | TA325 | 127/0 | Completed
2024-05-31 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.4589 | 5.637 | TA325 | 137/1 | Completed
2024-06-01 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.7305 | 3.43 | TA325 | 135/4 | Completed
2024-06-01 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.2376 | 6.5671 | TA325 | 127/0 | Completed
2024-06-02 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.7305 | 3.43 | TA325 | 135/4 | Completed
2024-06-02 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.2376 | 6.5671 | TA325 | 127/0 | Completed
2024-06-03 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.7305 | 3.43 | TA325 | 135/4 | Completed
2024-06-03 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.2376 | 6.5671 | TA325 | 127/0 | Completed
2024-06-04 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.7305 | 3.43 | TA325 | 135/4 | Completed
2024-06-04 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.2376 | 6.5671 | TA325 | 127/0 | Completed
2024-06-05 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.2376 | 8.0264 | TA325 | 112/0 | Completed
2024-06-05 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.7305 | 3.43 | TA325 | 135/4 | Completed
2024-06-05 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.2376 | 6.5671 | TA325 | 127/0 | Completed
2024-06-06 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.2376 | 8.0264 | TA325 | 112/0 | Completed
2024-06-06 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.7305 | 3.43 | TA325 | 135/4 | Completed
2024-06-06 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.2376 | 6.5671 | TA325 | 127/0 | Completed
2024-06-07 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.2376 | 8.0264 | TA325 | 112/0 | Completed
2024-06-07 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.7305 | 3.43 | TA325 | 135/4 | Completed
2024-06-07 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.2376 | 6.5671 | TA325 | 127/0 | Completed
2024-06-08 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.2376 | 8.0264 | TA325 | 112/0 | Completed
2024-06-08 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.7305 | 3.43 | TA325 | 135/4 | Completed
2024-06-08 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.2376 | 6.5671 | TA325 | 127/0 | Completed
2024-06-09 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.2376 | 8.0264 | TA325 | 112/0 | Completed
2024-06-09 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.7305 | 3.43 | TA325 | 135/4 | Completed
2024-06-09 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.2376 | 6.5671 | TA325 | 127/0 | Completed
2024-06-10 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.2376 | 8.0264 | TA325 | 112/0 | Completed
2024-06-10 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.7305 | 3.43 | TA325 | 135/4 | Completed
2024-06-10 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.2376 | 6.5671 | TA325 | 127/0 | Completed
2024-06-11 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.2376 | 8.0264 | TA325 | 112/0 | Completed
2024-06-11 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.7305 | 7.5461 | TA325 | 144/2 | Completed
2024-06-12 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.2376 | 8.0264 | TA325 | 112/0 | Completed
2024-06-12 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.7305 | 5.3901 | TA325 | 132/3 | Completed
2024-06-12 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.7305 | 7.5461 | TA325 | 144/2 | Completed
2024-06-13 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.2376 | 8.0264 | TA325 | 112/0 | Completed
2024-06-13 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.7305 | 5.3901 | TA325 | 132/3 | Completed
2024-06-13 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.7305 | 7.5461 | TA325 | 144/2 | Completed
2024-06-13 | 2024-06-13 | 2024-06-15 | Rahul Kumar | 37.7305 | 12.5768 | TA325 | 144/3 | Completed
2024-06-14 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.6235 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-14 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.7305 | 5.3901 | TA325 | 132/3 | Completed
2024-06-14 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.7305 | 7.5461 | TA325 | 144/2 | Completed
2024-06-14 | 2024-06-13 | 2024-06-15 | Rahul Kumar | 37.7305 | 12.5768 | TA325 | 144/3 | Completed
2024-06-15 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.6235 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-15 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.7305 | 5.3901 | TA325 | 132/3 | Completed
2024-06-15 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.7305 | 7.5461 | TA325 | 144/2 | Completed
2024-06-15 | 2024-06-13 | 2024-06-15 | Rahul Kumar | 37.7305 | 12.5768 | TA325 | 144/3 | Completed
2024-06-16 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.6235 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-16 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.7305 | 5.3901 | TA325 | 132/3 | Completed
2024-06-16 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.7305 | 7.5461 | TA325 | 144/4 | Completed
2024-06-17 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.6235 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-17 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.7305 | 5.3901 | TA325 | 132/3 | Completed
2024-06-17 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.7305 | 7.5461 | TA325 | 144/4 | Completed
2024-06-18 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.6235 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-18 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.7305 | 5.3901 | TA325 | 132/3 | Completed
2024-06-18 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.7305 | 7.5461 | TA325 | 144/4 | Completed
2024-06-19 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.6235 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-19 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.7305 | 7.5461 | TA325 | 144/4 | Completed
2024-06-20 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.6235 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-20 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.7305 | 7.5461 | TA325 | 144/4 | Completed
2024-06-21 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.6235 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-21 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 144/5 | Completed
2024-06-22 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.6235 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-22 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 144/5 | Completed
2024-06-23 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.6235 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-23 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 144/5 | Completed
2024-06-24 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.6235 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-24 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 144/5 | Completed
2024-06-25 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.4589 | 4.9324 | TA325 | 106A/3 | Completed
2024-06-25 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 144/5 | Completed
2024-06-26 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.4589 | 4.9324 | TA325 | 106A/3 | Completed
2024-06-26 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 144/5 | Completed
2024-06-27 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.4589 | 4.9324 | TA325 | 106A/3 | Completed
2024-06-28 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.4589 | 4.9324 | TA325 | 106A/3 | Completed
2024-06-29 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.4589 | 4.9324 | TA325 | 106A/3 | Completed
2024-06-30 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.4589 | 4.9324 | TA325 | 106A/3 | Completed
2024-06-30 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 144/1 | Completed
2024-07-01 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.4589 | 4.9324 | TA325 | 106A/3 | Completed
2024-07-01 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 144/1 | Completed
2024-07-02 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.4589 | 4.9324 | TA325 | 106A/3 | Completed
2024-07-02 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.7282 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-02 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 144/1 | Completed
2024-07-03 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.7282 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-03 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 144/1 | Completed
2024-07-04 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.7282 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-04 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 144/1 | Completed
2024-07-05 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.7282 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-05 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 144/1 | Completed
2024-07-06 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.7282 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-07 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.7282 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-08 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-08 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.7282 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-08 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.7305 | 7.5461 | TA325 | 119/2 | Completed
2024-07-08 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.7305 | 2.3582 | TA325 | 159/3 | Completed
2024-07-09 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-09 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.7282 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-09 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.7305 | 7.5461 | TA325 | 119/2 | Completed
2024-07-09 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.7305 | 2.3582 | TA325 | 159/3 | Completed
2024-07-10 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-10 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-07-10 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.7282 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-10 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.7305 | 7.5461 | TA325 | 119/2 | Completed
2024-07-10 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.7305 | 2.3582 | TA325 | 159/3 | Completed
2024-07-11 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-11 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-07-11 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.7282 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-11 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.7305 | 7.5461 | TA325 | 119/2 | Completed
2024-07-11 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.7305 | 2.3582 | TA325 | 159/3 | Completed
2024-07-12 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-12 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-07-12 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.7282 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-12 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.7305 | 7.5461 | TA325 | 119/2 | Completed
2024-07-12 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.7305 | 2.3582 | TA325 | 159/3 | Completed
2024-07-13 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-13 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-07-13 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.2376 | 4.2493 | TA325 | 107/0 | Completed
2024-07-13 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 119/3 | Completed
2024-07-13 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.7305 | 2.3582 | TA325 | 159/3 | Completed
2024-07-14 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-14 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-07-14 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.2376 | 4.2493 | TA325 | 107/0 | Completed
2024-07-14 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 119/3 | Completed
2024-07-14 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.7305 | 2.3582 | TA325 | 159/3 | Completed
2024-07-15 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-15 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-07-15 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.2376 | 4.2493 | TA325 | 107/0 | Completed
2024-07-15 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 119/3 | Completed
2024-07-15 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.7305 | 2.3582 | TA325 | 159/3 | Completed
2024-07-16 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-16 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-07-16 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.2376 | 4.2493 | TA325 | 107/0 | Completed
2024-07-16 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 119/3 | Completed
2024-07-16 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.7305 | 2.3582 | TA325 | 159/3 | Completed
2024-07-17 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-17 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-07-17 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.2376 | 4.2493 | TA325 | 107/0 | Completed
2024-07-17 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 119/3 | Completed
2024-07-17 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.7305 | 2.3582 | TA325 | 159/3 | Completed
2024-07-18 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-18 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-07-18 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.2376 | 4.2493 | TA325 | 107/0 | Completed
2024-07-18 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 119/3 | Completed
2024-07-18 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.7305 | 2.3582 | TA325 | 159/3 | Completed
2024-07-19 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-19 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-07-19 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.2376 | 4.2493 | TA325 | 107/0 | Completed
2024-07-19 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.7305 | 2.3582 | TA325 | 159/3 | Completed
2024-07-20 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-20 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-07-20 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.2376 | 4.2493 | TA325 | 107/0 | Completed
2024-07-20 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.2538 | 5.3545 | TA325 | 126/0 | Completed
2024-07-20 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.7305 | 2.3582 | TA325 | 159/3 | Completed
2024-07-21 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-21 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-07-21 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.2376 | 4.2493 | TA325 | 107/0 | Completed
2024-07-21 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.2538 | 5.3545 | TA325 | 126/0 | Completed
2024-07-21 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.7305 | 2.3582 | TA325 | 159/3 | Completed
2024-07-22 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-22 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-07-22 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.2376 | 4.2493 | TA325 | 107/0 | Completed
2024-07-22 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.2538 | 5.3545 | TA325 | 126/0 | Completed
2024-07-22 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.7305 | 2.3582 | TA325 | 159/3 | Completed
2024-07-23 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-23 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-07-23 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.2376 | 4.2493 | TA325 | 107/0 | Completed
2024-07-23 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.2538 | 5.3545 | TA325 | 126/0 | Completed
2024-07-23 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.7305 | 2.3582 | TA325 | 159/3 | Completed
2024-07-24 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-24 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-07-24 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.2376 | 4.2493 | TA325 | 107/0 | Completed
2024-07-24 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.2538 | 5.3545 | TA325 | 126/0 | Completed
2024-07-25 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-25 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-07-25 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.2376 | 4.2493 | TA325 | 107/0 | Completed
2024-07-25 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.2538 | 5.3545 | TA325 | 126/0 | Completed
2024-07-26 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-07-26 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.2376 | 4.2493 | TA325 | 107/0 | Completed
2024-07-26 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.2538 | 5.3545 | TA325 | 126/0 | Completed
2024-07-27 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-07-27 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.2376 | 4.2493 | TA325 | 107/0 | Completed
2024-07-27 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.2538 | 5.3545 | TA325 | 126/0 | Completed
2024-07-27 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/2 | Completed
2024-07-28 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.6235 | 3.8853 | TA325 | 106B/1 | Completed
2024-07-28 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-07-28 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.2376 | 4.2493 | TA325 | 107/0 | Completed
2024-07-28 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.2538 | 5.3545 | TA325 | 126/0 | Completed
2024-07-28 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/2 | Completed
2024-07-29 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.6235 | 3.8853 | TA325 | 106B/1 | Completed
2024-07-29 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-07-29 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.2376 | 4.2493 | TA325 | 107/0 | Completed
2024-07-29 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.2538 | 5.3545 | TA325 | 126/0 | Completed
2024-07-29 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/2 | Completed
2024-07-30 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.6235 | 3.8853 | TA325 | 106B/1 | Completed
2024-07-30 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-07-30 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.2538 | 4.9426 | TA325 | 116A/0 | Completed
2024-07-30 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.2538 | 5.3545 | TA325 | 126/0 | Completed
2024-07-30 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/2 | Completed
2024-07-31 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.6235 | 3.8853 | TA325 | 106B/1 | Completed
2024-07-31 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-07-31 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.2538 | 4.9426 | TA325 | 116A/0 | Completed
2024-07-31 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.2538 | 5.3545 | TA325 | 126/0 | Completed
2024-07-31 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/2 | Completed
2024-08-01 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.6235 | 3.8853 | TA325 | 106B/1 | Completed
2024-08-01 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-08-01 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.2538 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-01 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.2376 | 3.6119 | TA325 | 118/0 | Completed
2024-08-01 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/2 | Completed
2024-08-02 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.6235 | 3.8853 | TA325 | 106B/1 | Completed
2024-08-02 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-08-02 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.2538 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-02 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.2376 | 3.6119 | TA325 | 118/0 | Completed
2024-08-02 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/2 | Completed
2024-08-03 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.6235 | 3.8853 | TA325 | 106B/1 | Completed
2024-08-03 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-08-03 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.2538 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-03 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.2376 | 3.6119 | TA325 | 118/0 | Completed
2024-08-03 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/2 | Completed
2024-08-04 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.6235 | 3.8853 | TA325 | 106B/1 | Completed
2024-08-04 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-08-04 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.2538 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-04 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.2376 | 3.6119 | TA325 | 118/0 | Completed
2024-08-04 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/2 | Completed
2024-08-05 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.6235 | 3.8853 | TA325 | 106B/1 | Completed
2024-08-05 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-08-05 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.2538 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-05 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.2376 | 3.6119 | TA325 | 118/0 | Completed
2024-08-05 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/2 | Completed
2024-08-06 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.6235 | 3.8853 | TA325 | 106B/1 | Completed
2024-08-06 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-08-06 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.2538 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-06 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.2376 | 3.6119 | TA325 | 118/0 | Completed
2024-08-06 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/2 | Completed
2024-08-07 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.6235 | 3.8853 | TA325 | 106B/1 | Completed
2024-08-07 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-08-07 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.2538 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-07 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.2376 | 3.6119 | TA325 | 118/0 | Completed
2024-08-07 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/2 | Completed
2024-08-08 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.6235 | 3.8853 | TA325 | 106B/1 | Completed
2024-08-08 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-08-08 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.2538 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-08 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.2376 | 3.6119 | TA325 | 118/0 | Completed
2024-08-08 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.7565 | 3.868 | TA325 | 106B/0 | Completed
2024-08-08 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/2 | Completed
2024-08-09 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-08-09 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.2538 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-09 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.2376 | 3.6119 | TA325 | 118/0 | Completed
2024-08-09 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.7565 | 3.868 | TA325 | 106B/0 | Completed
2024-08-09 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/2 | Completed
2024-08-10 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-08-10 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.2538 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-10 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.2376 | 3.6119 | TA325 | 118/0 | Completed
2024-08-10 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.7565 | 3.868 | TA325 | 106B/0 | Completed
2024-08-10 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/2 | Completed
2024-08-11 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-08-11 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.2538 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-11 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.4178 | 4.186 | TA325 | 109/0 | Completed
2024-08-11 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.2376 | 3.6119 | TA325 | 118/0 | Completed
2024-08-11 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.7565 | 3.868 | TA325 | 106B/0 | Completed
2024-08-11 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/2 | Completed
2024-08-12 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-08-12 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.4178 | 4.186 | TA325 | 109/0 | Completed
2024-08-12 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.2376 | 3.6119 | TA325 | 118/0 | Completed
2024-08-12 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.7565 | 3.868 | TA325 | 106B/0 | Completed
2024-08-12 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/2 | Completed
2024-08-13 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-08-13 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.4178 | 4.186 | TA325 | 109/0 | Completed
2024-08-13 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.2376 | 3.6119 | TA325 | 118/0 | Completed
2024-08-13 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.7565 | 3.868 | TA325 | 106B/0 | Completed
2024-08-13 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/2 | Completed
2024-08-14 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-08-14 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.4178 | 4.186 | TA325 | 109/0 | Completed
2024-08-14 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.2376 | 3.6119 | TA325 | 118/0 | Completed
2024-08-14 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.7565 | 3.868 | TA325 | 106B/0 | Completed
2024-08-14 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.4178 | 2.093 | TA325 | 159/0 | Completed
2024-08-15 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-08-15 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.4178 | 4.186 | TA325 | 109/0 | Completed
2024-08-15 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.2376 | 3.6119 | TA325 | 118/0 | Completed
2024-08-15 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.7565 | 3.868 | TA325 | 106B/0 | Completed
2024-08-15 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.4178 | 2.093 | TA325 | 159/0 | Completed
2024-08-16 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-08-16 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.4178 | 4.186 | TA325 | 109/0 | Completed
2024-08-16 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.2376 | 3.6119 | TA325 | 118/0 | Completed
2024-08-16 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.7565 | 3.868 | TA325 | 106B/0 | Completed
2024-08-16 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.4178 | 2.093 | TA325 | 159/0 | Completed
2024-08-17 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-08-17 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.4178 | 4.186 | TA325 | 109/0 | Completed
2024-08-17 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.2376 | 3.6119 | TA325 | 118/0 | Completed
2024-08-17 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.7565 | 3.868 | TA325 | 106B/0 | Completed
2024-08-17 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.4178 | 2.093 | TA325 | 159/0 | Completed
2024-08-18 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-08-18 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.4178 | 4.186 | TA325 | 109/0 | Completed
2024-08-18 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.2376 | 3.6119 | TA325 | 118/0 | Completed
2024-08-18 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.7565 | 3.868 | TA325 | 106B/0 | Completed
2024-08-18 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.4178 | 3.887 | TA325 | 110/0 | Completed
2024-08-18 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.4178 | 2.093 | TA325 | 159/0 | Completed
2024-08-19 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-08-19 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.4178 | 4.186 | TA325 | 109/0 | Completed
2024-08-19 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.2376 | 3.6119 | TA325 | 118/0 | Completed
2024-08-19 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.7565 | 3.868 | TA325 | 106B/0 | Completed
2024-08-19 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.4178 | 3.887 | TA325 | 110/0 | Completed
2024-08-19 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.4178 | 2.093 | TA325 | 159/0 | Completed
2024-08-20 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-08-20 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.4178 | 4.186 | TA325 | 109/0 | Completed
2024-08-20 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.2376 | 3.6119 | TA325 | 118/0 | Completed
2024-08-20 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.7565 | 3.868 | TA325 | 106B/0 | Completed
2024-08-20 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.4178 | 3.887 | TA325 | 110/0 | Completed
2024-08-20 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.4178 | 2.093 | TA325 | 159/0 | Completed
2024-08-21 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-08-21 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.4178 | 4.186 | TA325 | 109/0 | Completed
2024-08-21 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.7565 | 3.868 | TA325 | 106B/0 | Completed
2024-08-21 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.4178 | 3.887 | TA325 | 110/0 | Completed
2024-08-21 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.7305 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-21 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.4178 | 2.093 | TA325 | 159/0 | Completed
2024-08-22 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-08-22 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.4178 | 4.186 | TA325 | 109/0 | Completed
2024-08-22 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.7565 | 3.868 | TA325 | 106B/0 | Completed
2024-08-22 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.4178 | 3.887 | TA325 | 110/0 | Completed
2024-08-22 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.7305 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-22 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.4178 | 2.093 | TA325 | 159/0 | Completed
2024-08-23 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.4178 | 4.186 | TA325 | 109/0 | Completed
2024-08-23 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.7565 | 3.868 | TA325 | 106B/0 | Completed
2024-08-23 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.4178 | 3.887 | TA325 | 110/0 | Completed
2024-08-23 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.7305 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-23 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.4178 | 2.093 | TA325 | 159/0 | Completed
2024-08-24 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.7565 | 3.868 | TA325 | 106B/0 | Completed
2024-08-24 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.4178 | 3.887 | TA325 | 110/0 | Completed
2024-08-24 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.7305 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-24 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.4178 | 2.093 | TA325 | 159/0 | Completed
2024-08-25 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.4178 | 3.887 | TA325 | 110/0 | Completed
2024-08-25 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.7305 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-25 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.4178 | 2.093 | TA325 | 159/0 | Completed
2024-08-26 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.4178 | 3.887 | TA325 | 110/0 | Completed
2024-08-26 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.7305 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-26 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.4178 | 2.093 | TA325 | 159/0 | Completed
2024-08-27 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.4178 | 3.887 | TA325 | 110/0 | Completed
2024-08-27 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.7305 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-27 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.4178 | 2.093 | TA325 | 159/0 | Completed
2024-08-28 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.4178 | 3.887 | TA325 | 110/0 | Completed
2024-08-28 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.7305 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-28 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.4178 | 2.093 | TA325 | 159/0 | Completed
2024-08-29 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-08-29 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.4178 | 3.887 | TA325 | 110/0 | Completed
2024-08-29 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.7305 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-29 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.4178 | 2.093 | TA325 | 159/0 | Completed
2024-08-30 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-08-30 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.2538 | 2.5702 | TA325 | 257/0 | Completed
2024-08-30 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.4178 | 3.887 | TA325 | 110/0 | Completed
2024-08-30 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.7305 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-30 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.4178 | 2.093 | TA325 | 159/0 | Completed
2024-08-31 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-08-31 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.2538 | 2.5702 | TA325 | 257/0 | Completed
2024-08-31 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.4178 | 3.887 | TA325 | 110/0 | Completed
2024-08-31 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.7305 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-31 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.4178 | 2.093 | TA325 | 159/0 | Completed
2024-09-01 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-01 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.2538 | 2.5702 | TA325 | 257/0 | Completed
2024-09-01 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.7305 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-01 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.4178 | 2.093 | TA325 | 159/0 | Completed
2024-09-02 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-02 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.2538 | 2.5702 | TA325 | 257/0 | Completed
2024-09-02 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.2376 | 6.0198 | TA325 | 114/0 | Completed
2024-09-02 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.7305 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-02 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.4178 | 2.093 | TA325 | 159/0 | Completed
2024-09-03 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-03 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.2538 | 2.5702 | TA325 | 257/0 | Completed
2024-09-03 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.2376 | 6.0198 | TA325 | 114/0 | Completed
2024-09-03 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.7305 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-03 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.4178 | 2.093 | TA325 | 159/0 | Completed
2024-09-04 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-04 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.2538 | 2.5702 | TA325 | 257/0 | Completed
2024-09-04 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.2376 | 6.0198 | TA325 | 114/0 | Completed
2024-09-04 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.7305 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-04 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.4178 | 2.093 | TA325 | 159/0 | Completed
2024-09-05 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-05 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.2538 | 2.5702 | TA325 | 257/0 | Completed
2024-09-05 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.2376 | 6.0198 | TA325 | 114/0 | Completed
2024-09-05 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.7305 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-05 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.4178 | 2.093 | TA325 | 159/0 | Completed
2024-09-06 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-06 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.2538 | 2.5702 | TA325 | 257/0 | Completed
2024-09-06 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.2376 | 6.0198 | TA325 | 114/0 | Completed
2024-09-06 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.7305 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-06 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.4178 | 2.093 | TA325 | 159/0 | Completed
2024-09-07 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-07 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.2538 | 2.5702 | TA325 | 257/0 | Completed
2024-09-07 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.2376 | 6.0198 | TA325 | 114/0 | Completed
2024-09-07 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.7305 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-07 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.4178 | 2.093 | TA325 | 159/0 | Completed
2024-09-08 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-08 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.2538 | 2.5702 | TA325 | 257/0 | Completed
2024-09-08 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.2376 | 6.0198 | TA325 | 114/0 | Completed
2024-09-08 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.7305 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-08 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.4178 | 2.093 | TA325 | 159/0 | Completed
2024-09-09 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-09 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.2538 | 2.5702 | TA325 | 257/0 | Completed
2024-09-09 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.2376 | 6.0198 | TA325 | 114/0 | Completed
2024-09-09 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.2538 | 4.9426 | TA325 | 111/0 | Completed
2024-09-09 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.7305 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-09 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 165/2 | Completed
2024-09-10 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-10 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.4236 | 6.2458 | TA325 | 116/0 | Completed
2024-09-10 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.2538 | 2.5702 | TA325 | 257/0 | Completed
2024-09-10 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.2376 | 6.0198 | TA325 | 114/0 | Completed
2024-09-10 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.2538 | 4.9426 | TA325 | 111/0 | Completed
2024-09-10 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.7305 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-10 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 165/2 | Completed
2024-09-11 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-11 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.4236 | 6.2458 | TA325 | 116/0 | Completed
2024-09-11 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.2538 | 2.5702 | TA325 | 257/0 | Completed
2024-09-11 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.2376 | 6.0198 | TA325 | 114/0 | Completed
2024-09-11 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.2538 | 4.9426 | TA325 | 111/0 | Completed
2024-09-11 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.7305 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-11 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-11 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 165/2 | Completed
2024-09-12 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.2376 | 5.5567 | TA325 | 119/0 | Completed
2024-09-12 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-12 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.4236 | 6.2458 | TA325 | 116/0 | Completed
2024-09-12 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.2538 | 2.5702 | TA325 | 257/0 | Completed
2024-09-12 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.2376 | 6.0198 | TA325 | 114/0 | Completed
2024-09-12 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.2538 | 4.9426 | TA325 | 111/0 | Completed
2024-09-12 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.7305 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-12 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-12 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 165/2 | Completed
2024-09-13 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.2376 | 5.5567 | TA325 | 119/0 | Completed
2024-09-13 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-13 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.4236 | 6.2458 | TA325 | 116/0 | Completed
2024-09-13 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.2538 | 2.5702 | TA325 | 257/0 | Completed
2024-09-13 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.2376 | 6.0198 | TA325 | 114/0 | Completed
2024-09-13 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.2538 | 4.9426 | TA325 | 111/0 | Completed
2024-09-13 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.7305 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-13 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-13 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 165/2 | Completed
2024-09-14 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.2376 | 5.5567 | TA325 | 119/0 | Completed
2024-09-14 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-14 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.4236 | 6.2458 | TA325 | 116/0 | Completed
2024-09-14 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.2538 | 2.5702 | TA325 | 257/0 | Completed
2024-09-14 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.0448 | 3.6045 | TA325 | 119/1 | Completed
2024-09-14 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.2538 | 4.9426 | TA325 | 111/0 | Completed
2024-09-14 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-14 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-09-14 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 165/2 | Completed
2024-09-15 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.2376 | 5.5567 | TA325 | 119/0 | Completed
2024-09-15 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-15 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.4236 | 6.2458 | TA325 | 116/0 | Completed
2024-09-15 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.2538 | 2.5702 | TA325 | 257/0 | Completed
2024-09-15 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.0448 | 3.6045 | TA325 | 119/1 | Completed
2024-09-15 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.2538 | 4.9426 | TA325 | 111/0 | Completed
2024-09-15 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-15 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-09-15 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 165/2 | Completed
2024-09-16 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.2376 | 5.5567 | TA325 | 119/0 | Completed
2024-09-16 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.0448 | 3.2768 | TA325 | 107/1 | Completed
2024-09-16 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-16 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.4236 | 6.2458 | TA325 | 116/0 | Completed
2024-09-16 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.2538 | 2.5702 | TA325 | 257/0 | Completed
2024-09-16 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.0448 | 3.6045 | TA325 | 119/1 | Completed
2024-09-16 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.2538 | 4.9426 | TA325 | 111/0 | Completed
2024-09-16 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-16 | 2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-09-16 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-09-16 | 2024-09-16 | 2024-09-30 | Senahul | 39.4589 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-16 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 165/2 | Completed
2024-09-17 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.2376 | 5.5567 | TA325 | 119/0 | Completed
2024-09-17 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.0448 | 3.2768 | TA325 | 107/1 | Completed
2024-09-17 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-17 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.4236 | 6.2458 | TA325 | 116/0 | Completed
2024-09-17 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.2538 | 2.5702 | TA325 | 257/0 | Completed
2024-09-17 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.0448 | 3.6045 | TA325 | 119/1 | Completed
2024-09-17 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.2538 | 4.9426 | TA325 | 111/0 | Completed
2024-09-17 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-17 | 2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-09-17 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-09-17 | 2024-09-16 | 2024-09-30 | Senahul | 39.4589 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-17 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 165/2 | Completed
2024-09-18 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.2376 | 5.5567 | TA325 | 119/0 | Completed
2024-09-18 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.0448 | 3.2768 | TA325 | 107/1 | Completed
2024-09-18 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-18 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.4236 | 6.2458 | TA325 | 116/0 | Completed
2024-09-18 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.2538 | 2.5702 | TA325 | 257/0 | Completed
2024-09-18 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.0448 | 3.6045 | TA325 | 119/1 | Completed
2024-09-18 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.2538 | 4.9426 | TA325 | 111/0 | Completed
2024-09-18 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-18 | 2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-09-18 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-09-18 | 2024-09-16 | 2024-09-30 | Senahul | 39.4589 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-18 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 165/2 | Completed
2024-09-19 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.2376 | 5.5567 | TA325 | 119/0 | Completed
2024-09-19 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.0448 | 3.2768 | TA325 | 107/1 | Completed
2024-09-19 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-19 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.4236 | 6.2458 | TA325 | 116/0 | Completed
2024-09-19 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.2538 | 2.5702 | TA325 | 257/0 | Completed
2024-09-19 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.0448 | 3.6045 | TA325 | 119/1 | Completed
2024-09-19 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.2538 | 4.9426 | TA325 | 111/0 | Completed
2024-09-19 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-19 | 2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-09-19 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-09-19 | 2024-09-16 | 2024-09-30 | Senahul | 39.4589 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-19 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 165/2 | Completed
2024-09-20 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.2376 | 5.5567 | TA325 | 119/0 | Completed
2024-09-20 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.0448 | 3.2768 | TA325 | 107/1 | Completed
2024-09-20 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-20 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.4236 | 6.2458 | TA325 | 116/0 | Completed
2024-09-20 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.2538 | 2.5702 | TA325 | 257/0 | Completed
2024-09-20 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.0448 | 3.6045 | TA325 | 119/1 | Completed
2024-09-20 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.2538 | 4.9426 | TA325 | 111/0 | Completed
2024-09-20 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-20 | 2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-09-20 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-09-20 | 2024-09-16 | 2024-09-30 | Senahul | 39.4589 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-20 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 165/2 | Completed
2024-09-21 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.2376 | 5.5567 | TA325 | 119/0 | Completed
2024-09-21 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.0448 | 3.2768 | TA325 | 107/1 | Completed
2024-09-21 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-21 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.4236 | 6.2458 | TA325 | 116/0 | Completed
2024-09-21 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.2538 | 2.5702 | TA325 | 257/0 | Completed
2024-09-21 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.0448 | 3.6045 | TA325 | 119/1 | Completed
2024-09-21 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.2538 | 4.9426 | TA325 | 111/0 | Completed
2024-09-21 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-21 | 2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-09-21 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-09-21 | 2024-09-16 | 2024-09-30 | Senahul | 39.4589 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-22 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.2376 | 5.5567 | TA325 | 119/0 | Completed
2024-09-22 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.0448 | 3.2768 | TA325 | 107/1 | Completed
2024-09-22 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-22 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.4236 | 6.2458 | TA325 | 116/0 | Completed
2024-09-22 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.2538 | 2.5702 | TA325 | 257/0 | Completed
2024-09-22 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.0448 | 3.6045 | TA325 | 119/1 | Completed
2024-09-22 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-22 | 2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-09-22 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-09-22 | 2024-09-16 | 2024-09-30 | Senahul | 39.4589 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-22 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/7 | Completed
2024-09-23 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.2376 | 5.5567 | TA325 | 119/0 | Completed
2024-09-23 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.0448 | 3.2768 | TA325 | 107/1 | Completed
2024-09-23 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-23 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.4236 | 6.2458 | TA325 | 116/0 | Completed
2024-09-23 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.2538 | 2.5702 | TA325 | 257/0 | Completed
2024-09-23 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-09-23 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.0448 | 3.6045 | TA325 | 119/1 | Completed
2024-09-23 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-09-23 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-23 | 2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-09-23 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-09-23 | 2024-09-16 | 2024-09-30 | Senahul | 39.4589 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-23 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/7 | Completed
2024-09-24 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.2376 | 5.5567 | TA325 | 119/0 | Completed
2024-09-24 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.0448 | 3.2768 | TA325 | 107/1 | Completed
2024-09-24 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-24 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.4236 | 6.2458 | TA325 | 116/0 | Completed
2024-09-24 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-09-24 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-09-24 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-24 | 2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-09-24 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-09-24 | 2024-09-16 | 2024-09-30 | Senahul | 39.4589 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-24 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-09-24 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/7 | Completed
2024-09-25 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.0448 | 3.2768 | TA325 | 107/1 | Completed
2024-09-25 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-25 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.4236 | 6.2458 | TA325 | 116/0 | Completed
2024-09-25 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-09-25 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-09-25 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-25 | 2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-09-25 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-09-25 | 2024-09-16 | 2024-09-30 | Senahul | 39.4589 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-25 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-09-25 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/7 | Completed
2024-09-26 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.4077 | 6.2938 | TA325 | 123/0 | Completed
2024-09-26 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.0448 | 3.2768 | TA325 | 107/1 | Completed
2024-09-26 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-26 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.4236 | 6.2458 | TA325 | 116/0 | Completed
2024-09-26 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-09-26 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-09-26 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-26 | 2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-09-26 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-09-26 | 2024-09-16 | 2024-09-30 | Senahul | 39.4589 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-26 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-09-26 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/7 | Completed
2024-09-27 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.4077 | 6.2938 | TA325 | 123/0 | Completed
2024-09-27 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-27 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.4236 | 6.2458 | TA325 | 116/0 | Completed
2024-09-27 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-09-27 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.7282 | 2.7955 | TA325 | 133A/4 | Completed
2024-09-27 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-09-27 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-27 | 2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-09-27 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-09-27 | 2024-09-16 | 2024-09-30 | Senahul | 39.4589 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-27 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-09-27 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/7 | Completed
2024-09-28 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.4077 | 6.2938 | TA325 | 123/0 | Completed
2024-09-28 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-28 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.2376 | 4.5149 | TA325 | 108/0 | Completed
2024-09-28 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-09-28 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.7282 | 2.7955 | TA325 | 133A/4 | Completed
2024-09-28 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-09-28 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-28 | 2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-09-28 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-09-28 | 2024-09-16 | 2024-09-30 | Senahul | 39.4589 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-28 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-09-28 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/7 | Completed
2024-09-29 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.4077 | 6.2938 | TA325 | 123/0 | Completed
2024-09-29 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-29 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.2376 | 4.5149 | TA325 | 108/0 | Completed
2024-09-29 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-09-29 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.7282 | 2.7955 | TA325 | 133A/4 | Completed
2024-09-29 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-09-29 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-29 | 2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-09-29 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-09-29 | 2024-09-16 | 2024-09-30 | Senahul | 39.4589 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-29 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-09-29 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/7 | Completed
2024-09-30 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.4077 | 6.2938 | TA325 | 123/0 | Completed
2024-09-30 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-30 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.2376 | 4.5149 | TA325 | 108/0 | Completed
2024-09-30 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-09-30 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.7282 | 2.7955 | TA325 | 133A/4 | Completed
2024-09-30 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-09-30 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-30 | 2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-09-30 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-09-30 | 2024-09-16 | 2024-09-30 | Senahul | 39.4589 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-30 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-09-30 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/7 | Completed
2024-09-30 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-01 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.4077 | 6.2938 | TA325 | 123/0 | Completed
2024-10-01 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-10-01 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.2376 | 4.5149 | TA325 | 108/0 | Completed
2024-10-01 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-10-01 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.8356 | 4.1182 | TA325 | 120/0 | Completed
2024-10-01 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.7282 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-01 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-01 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-01 | 2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-10-01 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-01 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-01 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/7 | Completed
2024-10-01 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-02 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.4077 | 6.2938 | TA325 | 123/0 | Completed
2024-10-02 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-10-02 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.2376 | 4.5149 | TA325 | 108/0 | Completed
2024-10-02 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-10-02 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.8356 | 4.1182 | TA325 | 120/0 | Completed
2024-10-02 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.7282 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-02 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-02 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-02 | 2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-10-02 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-02 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-02 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/7 | Completed
2024-10-02 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-03 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.4077 | 6.2938 | TA325 | 123/0 | Completed
2024-10-03 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-10-03 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.2376 | 4.5149 | TA325 | 108/0 | Completed
2024-10-03 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-03 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-10-03 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.8356 | 4.1182 | TA325 | 120/0 | Completed
2024-10-03 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.7282 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-03 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-03 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-03 | 2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-10-03 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-03 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-03 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/7 | Completed
2024-10-03 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-04 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.4077 | 6.2938 | TA325 | 123/0 | Completed
2024-10-04 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-10-04 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.2376 | 4.5149 | TA325 | 108/0 | Completed
2024-10-04 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-04 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-10-04 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.8356 | 4.1182 | TA325 | 120/0 | Completed
2024-10-04 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.6321 | 6.2193 | TA325 | 122/0 | Completed
2024-10-04 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.7282 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-04 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-04 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-04 | 2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-10-04 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-04 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-04 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/7 | Completed
2024-10-04 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-05 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.4077 | 6.2938 | TA325 | 123/0 | Completed
2024-10-05 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-10-05 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.2376 | 4.5149 | TA325 | 108/0 | Completed
2024-10-05 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-05 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-10-05 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.8356 | 4.1182 | TA325 | 120/0 | Completed
2024-10-05 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.6321 | 6.2193 | TA325 | 122/0 | Completed
2024-10-05 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.7282 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-05 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-05 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-05 | 2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-10-05 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-05 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-05 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/7 | Completed
2024-10-05 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-06 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.4077 | 6.2938 | TA325 | 123/0 | Completed
2024-10-06 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-10-06 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.2376 | 4.5149 | TA325 | 108/0 | Completed
2024-10-06 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-06 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-10-06 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.8356 | 4.1182 | TA325 | 120/0 | Completed
2024-10-06 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.6321 | 6.2193 | TA325 | 122/0 | Completed
2024-10-06 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.7282 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-06 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-06 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-06 | 2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-10-06 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-06 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-06 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/7 | Completed
2024-10-06 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-07 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.4077 | 6.2938 | TA325 | 123/0 | Completed
2024-10-07 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.2376 | 4.5149 | TA325 | 108/0 | Completed
2024-10-07 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-07 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-10-07 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.8356 | 4.1182 | TA325 | 120/0 | Completed
2024-10-07 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.6321 | 6.2193 | TA325 | 122/0 | Completed
2024-10-07 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.7282 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-07 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-07 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-07 | 2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-10-07 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-07 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-07 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/7 | Completed
2024-10-07 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-08 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.4077 | 6.2938 | TA325 | 123/0 | Completed
2024-10-08 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-08 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.2376 | 4.5149 | TA325 | 108/0 | Completed
2024-10-08 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-08 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-10-08 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.8356 | 4.1182 | TA325 | 120/0 | Completed
2024-10-08 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.6321 | 6.2193 | TA325 | 122/0 | Completed
2024-10-08 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.7282 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-08 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-08 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-08 | 2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-10-08 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-08 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-08 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/7 | Completed
2024-10-08 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-09 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.4077 | 6.2938 | TA325 | 123/0 | Completed
2024-10-09 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-09 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.2376 | 4.5149 | TA325 | 108/0 | Completed
2024-10-09 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-09 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-10-09 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.8356 | 4.1182 | TA325 | 120/0 | Completed
2024-10-09 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.6321 | 6.2193 | TA325 | 122/0 | Completed
2024-10-09 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.7282 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-09 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-09 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-09 | 2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-10-09 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-09 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-09 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/7 | Completed
2024-10-09 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.4178 | 2.7209 | TA325 | 165/0 | Completed
2024-10-09 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-10 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.4077 | 6.2938 | TA325 | 123/0 | Completed
2024-10-10 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-10 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.2376 | 4.5149 | TA325 | 108/0 | Completed
2024-10-10 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-10 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-10-10 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.8356 | 4.1182 | TA325 | 120/0 | Completed
2024-10-10 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.6321 | 6.2193 | TA325 | 122/0 | Completed
2024-10-10 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.7282 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-10 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-10 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-10 | 2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-10-10 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-10 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-10 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.4178 | 2.7209 | TA325 | 165/0 | Completed
2024-10-10 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-11 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-11 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.2376 | 4.5149 | TA325 | 108/0 | Completed
2024-10-11 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-11 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-10-11 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.8356 | 4.1182 | TA325 | 120/0 | Completed
2024-10-11 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.6321 | 6.2193 | TA325 | 122/0 | Completed
2024-10-11 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.7282 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-11 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-11 | 2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-10-11 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-11 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-11 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.4178 | 2.7209 | TA325 | 165/0 | Completed
2024-10-11 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-12 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-12 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.2376 | 4.5149 | TA325 | 108/0 | Completed
2024-10-12 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-12 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-10-12 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.8356 | 4.1182 | TA325 | 120/0 | Completed
2024-10-12 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.6321 | 6.2193 | TA325 | 122/0 | Completed
2024-10-12 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.7282 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-12 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-12 | 2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-10-12 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-12 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-12 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.4178 | 2.7209 | TA325 | 165/0 | Completed
2024-10-12 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-13 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.2338 | 4.486 | TA325 | 116B/0 | Completed
2024-10-13 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-13 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.2376 | 4.5149 | TA325 | 108/0 | Completed
2024-10-13 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-13 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-10-13 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.8356 | 4.1182 | TA325 | 120/0 | Completed
2024-10-13 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.6321 | 6.2193 | TA325 | 122/0 | Completed
2024-10-13 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-13 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-13 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-13 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.4178 | 2.7209 | TA325 | 165/0 | Completed
2024-10-13 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-14 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.2338 | 4.486 | TA325 | 116B/0 | Completed
2024-10-14 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-14 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-14 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-10-14 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.8356 | 4.1182 | TA325 | 120/0 | Completed
2024-10-14 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.6321 | 6.2193 | TA325 | 122/0 | Completed
2024-10-14 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-14 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-14 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-14 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.4178 | 2.7209 | TA325 | 165/0 | Completed
2024-10-14 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-15 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.2338 | 4.486 | TA325 | 116B/0 | Completed
2024-10-15 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-15 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-15 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-10-15 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.8356 | 4.1182 | TA325 | 120/0 | Completed
2024-10-15 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.6321 | 6.2193 | TA325 | 122/0 | Completed
2024-10-15 | 2024-10-15 | 2024-10-24 | Mukesh | 64.2538 | 6.4254 | TA325 | 152/0 | Completed
2024-10-15 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-10-15 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-15 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-15 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-15 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.4178 | 2.7209 | TA325 | 165/0 | Completed
2024-10-15 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-16 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.2338 | 4.486 | TA325 | 116B/0 | Completed
2024-10-16 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-16 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-16 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-10-16 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.8356 | 4.1182 | TA325 | 120/0 | Completed
2024-10-16 | 2024-10-15 | 2024-10-24 | Mukesh | 64.2538 | 6.4254 | TA325 | 152/0 | Completed
2024-10-16 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-10-16 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-16 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-16 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-16 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.4178 | 2.7209 | TA325 | 165/0 | Completed
2024-10-16 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-17 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.2338 | 4.486 | TA325 | 116B/0 | Completed
2024-10-17 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-17 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-17 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-10-17 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.8356 | 4.1182 | TA325 | 120/0 | Completed
2024-10-17 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.4589 | 2.6306 | TA325 | 123/1 | Completed
2024-10-17 | 2024-10-15 | 2024-10-24 | Mukesh | 64.2538 | 6.4254 | TA325 | 152/0 | Completed
2024-10-17 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-10-17 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-17 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-17 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-17 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.4178 | 2.7209 | TA325 | 165/0 | Completed
2024-10-17 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-18 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.2338 | 4.486 | TA325 | 116B/0 | Completed
2024-10-18 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-18 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-18 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-10-18 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.8356 | 4.1182 | TA325 | 120/0 | Completed
2024-10-18 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.4589 | 2.6306 | TA325 | 123/1 | Completed
2024-10-18 | 2024-10-15 | 2024-10-24 | Mukesh | 64.2538 | 6.4254 | TA325 | 152/0 | Completed
2024-10-18 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-10-18 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-18 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-18 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-18 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.4178 | 2.7209 | TA325 | 165/0 | Completed
2024-10-18 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-19 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.2338 | 4.486 | TA325 | 116B/0 | Completed
2024-10-19 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-19 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-19 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-10-19 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.8356 | 4.1182 | TA325 | 120/0 | Completed
2024-10-19 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.4589 | 2.6306 | TA325 | 123/1 | Completed
2024-10-19 | 2024-10-15 | 2024-10-24 | Mukesh | 64.2538 | 6.4254 | TA325 | 152/0 | Completed
2024-10-19 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-10-19 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-19 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-19 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-19 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.4178 | 2.7209 | TA325 | 165/0 | Completed
2024-10-19 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-20 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.2338 | 4.486 | TA325 | 116B/0 | Completed
2024-10-20 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-20 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-20 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-10-20 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.8356 | 4.1182 | TA325 | 120/0 | Completed
2024-10-20 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.4589 | 2.6306 | TA325 | 123/1 | Completed
2024-10-20 | 2024-10-15 | 2024-10-24 | Mukesh | 64.2538 | 6.4254 | TA325 | 152/0 | Completed
2024-10-20 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-10-20 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-20 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-20 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-20 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.4178 | 2.7209 | TA325 | 165/0 | Completed
2024-10-20 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-21 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.2338 | 4.486 | TA325 | 116B/0 | Completed
2024-10-21 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-21 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-21 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-10-21 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.8356 | 4.1182 | TA325 | 120/0 | Completed
2024-10-21 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.4589 | 2.6306 | TA325 | 123/1 | Completed
2024-10-21 | 2024-10-15 | 2024-10-24 | Mukesh | 64.2538 | 6.4254 | TA325 | 152/0 | Completed
2024-10-21 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-10-21 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-21 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-21 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-21 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.4178 | 2.7209 | TA325 | 165/0 | Completed
2024-10-21 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-22 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.2338 | 4.486 | TA325 | 116B/0 | Completed
2024-10-22 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-22 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-22 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-10-22 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.8356 | 4.1182 | TA325 | 120/0 | Completed
2024-10-22 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.4589 | 2.6306 | TA325 | 123/1 | Completed
2024-10-22 | 2024-10-15 | 2024-10-24 | Mukesh | 64.2538 | 6.4254 | TA325 | 152/0 | Completed
2024-10-22 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-10-22 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-22 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-22 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-22 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.4178 | 2.7209 | TA325 | 165/0 | Completed
2024-10-22 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-23 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.2338 | 4.486 | TA325 | 116B/0 | Completed
2024-10-23 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-23 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-23 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-10-23 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.8356 | 4.1182 | TA325 | 120/0 | Completed
2024-10-23 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.4589 | 2.6306 | TA325 | 123/1 | Completed
2024-10-23 | 2024-10-15 | 2024-10-24 | Mukesh | 64.2538 | 6.4254 | TA325 | 152/0 | Completed
2024-10-23 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-10-23 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.2338 | 4.0588 | TA325 | 158A/0 | Completed
2024-10-23 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-23 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-23 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-23 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.4178 | 2.7209 | TA325 | 165/0 | Completed
2024-10-23 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-24 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.2338 | 4.486 | TA325 | 116B/0 | Completed
2024-10-24 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-24 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-24 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-10-24 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.8356 | 4.1182 | TA325 | 120/0 | Completed
2024-10-24 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.4589 | 2.6306 | TA325 | 123/1 | Completed
2024-10-24 | 2024-10-15 | 2024-10-24 | Mukesh | 64.2538 | 6.4254 | TA325 | 152/0 | Completed
2024-10-24 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-10-24 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.2338 | 4.0588 | TA325 | 158A/0 | Completed
2024-10-24 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-24 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-24 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-24 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.4178 | 2.7209 | TA325 | 165/0 | Completed
2024-10-24 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-25 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.2338 | 4.486 | TA325 | 116B/0 | Completed
2024-10-25 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-25 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-25 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 262/1 | Completed
2024-10-25 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.4589 | 2.6306 | TA325 | 123/1 | Completed
2024-10-25 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-10-25 | 2024-10-25 | 2024-10-31 | Mukesh | 36.0448 | 5.1493 | TA325 | 152/3 | Completed
2024-10-25 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.2338 | 4.0588 | TA325 | 158A/0 | Completed
2024-10-25 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-25 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-25 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-25 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.4178 | 2.7209 | TA325 | 165/0 | Completed
2024-10-25 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-26 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.2338 | 4.486 | TA325 | 116B/0 | Completed
2024-10-26 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-26 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-26 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 262/1 | Completed
2024-10-26 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.4589 | 2.6306 | TA325 | 123/1 | Completed
2024-10-26 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-10-26 | 2024-10-25 | 2024-10-31 | Mukesh | 36.0448 | 5.1493 | TA325 | 152/3 | Completed
2024-10-26 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.2338 | 4.0588 | TA325 | 158A/0 | Completed
2024-10-26 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-26 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-26 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-26 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.4178 | 2.7209 | TA325 | 165/0 | Completed
2024-10-26 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-27 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.2338 | 4.486 | TA325 | 116B/0 | Completed
2024-10-27 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-27 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-27 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 262/1 | Completed
2024-10-27 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.4589 | 2.6306 | TA325 | 123/1 | Completed
2024-10-27 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-10-27 | 2024-10-25 | 2024-10-31 | Mukesh | 36.0448 | 5.1493 | TA325 | 152/3 | Completed
2024-10-27 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.2338 | 4.0588 | TA325 | 158A/0 | Completed
2024-10-27 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-27 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-27 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-27 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.4178 | 2.7209 | TA325 | 165/0 | Completed
2024-10-27 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-28 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.2338 | 4.486 | TA325 | 116B/0 | Completed
2024-10-28 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.2679 | 4.4179 | TA325 | 124/0 | Completed
2024-10-28 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-28 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-28 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 262/1 | Completed
2024-10-28 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.4589 | 2.6306 | TA325 | 123/1 | Completed
2024-10-28 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-10-28 | 2024-10-25 | 2024-10-31 | Mukesh | 36.0448 | 5.1493 | TA325 | 152/3 | Completed
2024-10-28 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.2338 | 4.0588 | TA325 | 158A/0 | Completed
2024-10-28 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-28 | 2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-28 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-28 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.4178 | 2.7209 | TA325 | 165/0 | Completed
2024-10-28 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-29 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.2338 | 4.486 | TA325 | 116B/0 | Completed
2024-10-29 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.2679 | 4.4179 | TA325 | 124/0 | Completed
2024-10-29 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-29 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-29 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 262/1 | Completed
2024-10-29 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.4589 | 2.6306 | TA325 | 123/1 | Completed
2024-10-29 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-10-29 | 2024-10-25 | 2024-10-31 | Mukesh | 36.0448 | 5.1493 | TA325 | 152/3 | Completed
2024-10-29 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.2338 | 4.0588 | TA325 | 158A/0 | Completed
2024-10-29 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-29 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-29 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-29 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.7305 | 1.9858 | TA325 | 257/4 | Completed
2024-10-30 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.2338 | 4.486 | TA325 | 116B/0 | Completed
2024-10-30 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.2679 | 4.4179 | TA325 | 124/0 | Completed
2024-10-30 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-30 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-30 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 262/1 | Completed
2024-10-30 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.4589 | 2.6306 | TA325 | 123/1 | Completed
2024-10-30 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-10-30 | 2024-10-25 | 2024-10-31 | Mukesh | 36.0448 | 5.1493 | TA325 | 152/3 | Completed
2024-10-30 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.2338 | 4.0588 | TA325 | 158A/0 | Completed
2024-10-30 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-30 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-30 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.7282 | 2.6311 | TA325 | 165/3 | Completed
2024-10-30 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-30 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.7305 | 1.9858 | TA325 | 257/4 | Completed
2024-10-31 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.2338 | 4.486 | TA325 | 116B/0 | Completed
2024-10-31 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.2679 | 4.4179 | TA325 | 124/0 | Completed
2024-10-31 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-31 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-10-31 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 262/1 | Completed
2024-10-31 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.4589 | 2.6306 | TA325 | 123/1 | Completed
2024-10-31 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-10-31 | 2024-10-25 | 2024-10-31 | Mukesh | 36.0448 | 5.1493 | TA325 | 152/3 | Completed
2024-10-31 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.2338 | 4.0588 | TA325 | 158A/0 | Completed
2024-10-31 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-31 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-10-31 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.7282 | 2.6311 | TA325 | 165/3 | Completed
2024-10-31 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-31 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.7305 | 1.9858 | TA325 | 257/4 | Completed
2024-11-01 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.2679 | 4.4179 | TA325 | 124/0 | Completed
2024-11-01 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-11-01 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-01 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 262/1 | Completed
2024-11-01 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-11-01 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.2338 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-01 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-11-01 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.7282 | 2.6311 | TA325 | 165/3 | Completed
2024-11-01 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.7305 | 1.9858 | TA325 | 257/4 | Completed
2024-11-02 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.2679 | 4.4179 | TA325 | 124/0 | Completed
2024-11-02 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-11-02 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-02 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 262/1 | Completed
2024-11-02 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.8632 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-02 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-11-02 | 2024-11-02 | 2024-11-07 | Mukesh | 37.7305 | 6.2884 | TA325 | 152/4 | Completed
2024-11-02 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.2338 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-02 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-11-02 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.7282 | 2.6311 | TA325 | 165/3 | Completed
2024-11-02 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.7305 | 1.9858 | TA325 | 257/4 | Completed
2024-11-03 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.2679 | 4.4179 | TA325 | 124/0 | Completed
2024-11-03 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-11-03 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-03 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 262/1 | Completed
2024-11-03 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.8632 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-03 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-11-03 | 2024-11-02 | 2024-11-07 | Mukesh | 37.7305 | 6.2884 | TA325 | 152/4 | Completed
2024-11-03 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.2338 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-03 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-11-03 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.7282 | 2.6311 | TA325 | 165/3 | Completed
2024-11-03 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.7305 | 1.9858 | TA325 | 257/4 | Completed
2024-11-04 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.2679 | 4.4179 | TA325 | 124/0 | Completed
2024-11-04 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-04 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 262/1 | Completed
2024-11-04 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.8632 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-04 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-11-04 | 2024-11-02 | 2024-11-07 | Mukesh | 37.7305 | 6.2884 | TA325 | 152/4 | Completed
2024-11-04 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.2338 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-04 | 2024-11-04 | 2024-11-21 | Senahul | 54.4178 | 3.0232 | TA325 | 254/0 | Completed
2024-11-04 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-11-04 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.7282 | 2.6311 | TA325 | 165/3 | Completed
2024-11-04 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.7305 | 1.9858 | TA325 | 257/4 | Completed
2024-11-05 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.2679 | 4.4179 | TA325 | 124/0 | Completed
2024-11-05 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.7565 | 7.3063 | TA325 | 135A/2 | Completed
2024-11-05 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-05 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 262/1 | Completed
2024-11-05 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.8632 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-05 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-11-05 | 2024-11-02 | 2024-11-07 | Mukesh | 37.7305 | 6.2884 | TA325 | 152/4 | Completed
2024-11-05 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.2338 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-05 | 2024-11-04 | 2024-11-21 | Senahul | 54.4178 | 3.0232 | TA325 | 254/0 | Completed
2024-11-05 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-11-05 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.7282 | 2.6311 | TA325 | 165/3 | Completed
2024-11-05 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.7305 | 1.9858 | TA325 | 257/4 | Completed
2024-11-06 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.2679 | 4.4179 | TA325 | 124/0 | Completed
2024-11-06 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.7565 | 7.3063 | TA325 | 135A/2 | Completed
2024-11-06 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-06 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 262/1 | Completed
2024-11-06 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.8632 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-06 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-11-06 | 2024-11-02 | 2024-11-07 | Mukesh | 37.7305 | 6.2884 | TA325 | 152/4 | Completed
2024-11-06 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.2338 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-06 | 2024-11-04 | 2024-11-21 | Senahul | 54.4178 | 3.0232 | TA325 | 254/0 | Completed
2024-11-06 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-11-06 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.7282 | 2.6311 | TA325 | 165/3 | Completed
2024-11-06 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.7305 | 1.9858 | TA325 | 257/4 | Completed
2024-11-07 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.2679 | 4.4179 | TA325 | 124/0 | Completed
2024-11-07 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.7565 | 7.3063 | TA325 | 135A/2 | Completed
2024-11-07 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-07 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 262/1 | Completed
2024-11-07 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.8632 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-07 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-11-07 | 2024-11-02 | 2024-11-07 | Mukesh | 37.7305 | 6.2884 | TA325 | 152/4 | Completed
2024-11-07 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.2338 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-07 | 2024-11-04 | 2024-11-21 | Senahul | 54.4178 | 3.0232 | TA325 | 254/0 | Completed
2024-11-07 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-11-07 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.7282 | 2.6311 | TA325 | 165/3 | Completed
2024-11-07 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.7305 | 1.9858 | TA325 | 257/4 | Completed
2024-11-08 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.2679 | 4.4179 | TA325 | 124/0 | Completed
2024-11-08 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.7565 | 7.3063 | TA325 | 135A/2 | Completed
2024-11-08 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-08 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.8632 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-08 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-11-08 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.2338 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-08 | 2024-11-04 | 2024-11-21 | Senahul | 54.4178 | 3.0232 | TA325 | 254/0 | Completed
2024-11-08 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.7282 | 2.6311 | TA325 | 165/3 | Completed
2024-11-08 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.7305 | 1.9858 | TA325 | 257/4 | Completed
2024-11-09 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.2679 | 4.4179 | TA325 | 124/0 | Completed
2024-11-09 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.7565 | 7.3063 | TA325 | 135A/2 | Completed
2024-11-09 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-09 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.8632 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-09 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-11-09 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.2338 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-09 | 2024-11-04 | 2024-11-21 | Senahul | 54.4178 | 3.0232 | TA325 | 254/0 | Completed
2024-11-09 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.7282 | 2.6311 | TA325 | 165/3 | Completed
2024-11-09 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.7305 | 1.9858 | TA325 | 257/4 | Completed
2024-11-10 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.2679 | 4.4179 | TA325 | 124/0 | Completed
2024-11-10 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-11-10 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.7565 | 7.3063 | TA325 | 135A/2 | Completed
2024-11-10 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-10 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.8632 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-10 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-10 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-11-10 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.2338 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-10 | 2024-11-04 | 2024-11-21 | Senahul | 54.4178 | 3.0232 | TA325 | 254/0 | Completed
2024-11-10 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.4589 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-10 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.7282 | 2.6311 | TA325 | 165/3 | Completed
2024-11-10 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.7305 | 1.9858 | TA325 | 257/4 | Completed
2024-11-11 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.2679 | 4.4179 | TA325 | 124/0 | Completed
2024-11-11 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-11-11 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.7565 | 7.3063 | TA325 | 135A/2 | Completed
2024-11-11 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-11 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.8632 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-11 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-11 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-11-11 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.2338 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-11 | 2024-11-04 | 2024-11-21 | Senahul | 54.4178 | 3.0232 | TA325 | 254/0 | Completed
2024-11-11 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.4589 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-11 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.7282 | 2.6311 | TA325 | 165/3 | Completed
2024-11-11 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.7305 | 1.9858 | TA325 | 257/4 | Completed
2024-11-12 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-11-12 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.7565 | 7.3063 | TA325 | 135A/2 | Completed
2024-11-12 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-12 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.8632 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-12 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-12 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-11-12 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.2338 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-12 | 2024-11-04 | 2024-11-21 | Senahul | 54.4178 | 3.0232 | TA325 | 254/0 | Completed
2024-11-12 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.4589 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-12 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.7282 | 2.6311 | TA325 | 165/3 | Completed
2024-11-12 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.7305 | 1.9858 | TA325 | 257/4 | Completed
2024-11-13 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.4077 | 6.7434 | TA325 | 128/0 | Completed
2024-11-13 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-11-13 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.7565 | 7.3063 | TA325 | 135A/2 | Completed
2024-11-13 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-13 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.8632 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-13 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-13 | 2024-11-13 | 2024-12-02 | Modina India | 36.0448 | 1.8022 | TA325 | 147/3 | Completed
2024-11-13 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-11-13 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-13 | 2024-11-04 | 2024-11-21 | Senahul | 54.4178 | 3.0232 | TA325 | 254/0 | Completed
2024-11-13 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.4589 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-13 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.7282 | 2.6311 | TA325 | 165/3 | Completed
2024-11-13 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.7305 | 1.9858 | TA325 | 257/4 | Completed
2024-11-14 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.4077 | 6.7434 | TA325 | 128/0 | Completed
2024-11-14 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-11-14 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.0448 | 5.1493 | TA325 | 137A/5 | Completed
2024-11-14 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-14 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-14 | 2024-11-13 | 2024-12-02 | Modina India | 36.0448 | 1.8022 | TA325 | 147/3 | Completed
2024-11-14 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-11-14 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-14 | 2024-11-04 | 2024-11-21 | Senahul | 54.4178 | 3.0232 | TA325 | 254/0 | Completed
2024-11-14 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.4589 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-14 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.7282 | 2.6311 | TA325 | 165/3 | Completed
2024-11-14 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.7305 | 1.9858 | TA325 | 257/4 | Completed
2024-11-15 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.4077 | 6.7434 | TA325 | 128/0 | Completed
2024-11-15 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-11-15 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.0448 | 5.1493 | TA325 | 137A/5 | Completed
2024-11-15 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-15 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-15 | 2024-11-13 | 2024-12-02 | Modina India | 36.0448 | 1.8022 | TA325 | 147/3 | Completed
2024-11-15 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-11-15 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-15 | 2024-11-04 | 2024-11-21 | Senahul | 54.4178 | 3.0232 | TA325 | 254/0 | Completed
2024-11-15 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.4589 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-15 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.7282 | 2.6311 | TA325 | 165/3 | Completed
2024-11-15 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.7305 | 1.9858 | TA325 | 257/4 | Completed
2024-11-16 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.4077 | 6.7434 | TA325 | 128/0 | Completed
2024-11-16 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-11-16 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.0448 | 5.1493 | TA325 | 137A/5 | Completed
2024-11-16 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-16 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-16 | 2024-11-13 | 2024-12-02 | Modina India | 36.0448 | 1.8022 | TA325 | 147/3 | Completed
2024-11-16 | 2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-11-16 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-16 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.4589 | 5.637 | TA325 | 155/3 | Completed
2024-11-16 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.4589 | 2.6306 | TA325 | 155/2 | Completed
2024-11-16 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-16 | 2024-11-04 | 2024-11-21 | Senahul | 54.4178 | 3.0232 | TA325 | 254/0 | Completed
2024-11-16 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.4589 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-16 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 164/4 | Completed
2024-11-16 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.7305 | 1.9858 | TA325 | 257/4 | Completed
2024-11-17 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.4077 | 6.7434 | TA325 | 128/0 | Completed
2024-11-17 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-11-17 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.0448 | 5.1493 | TA325 | 137A/5 | Completed
2024-11-17 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-17 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-17 | 2024-11-13 | 2024-12-02 | Modina India | 36.0448 | 1.8022 | TA325 | 147/3 | Completed
2024-11-17 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-17 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.4589 | 5.637 | TA325 | 155/3 | Completed
2024-11-17 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.4589 | 2.6306 | TA325 | 155/2 | Completed
2024-11-17 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-17 | 2024-11-04 | 2024-11-21 | Senahul | 54.4178 | 3.0232 | TA325 | 254/0 | Completed
2024-11-17 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.4589 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-17 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 164/4 | Completed
2024-11-17 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.6321 | 3.1097 | TA325 | 264/0 | Completed
2024-11-18 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.4077 | 6.7434 | TA325 | 128/0 | Completed
2024-11-18 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-11-18 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.0448 | 5.1493 | TA325 | 137A/5 | Completed
2024-11-18 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-18 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-18 | 2024-11-13 | 2024-12-02 | Modina India | 36.0448 | 1.8022 | TA325 | 147/3 | Completed
2024-11-18 | 2024-11-18 | 2024-11-24 | Mukesh | 65.7565 | 9.3938 | TA325 | 144A/0 | Completed
2024-11-18 | 2024-11-18 | 2024-12-08 | Mukesh | 82.2388 | 3.9161 | TA325 | 145/0 | Completed
2024-11-18 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-18 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.4589 | 5.637 | TA325 | 155/3 | Completed
2024-11-18 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.4589 | 2.6306 | TA325 | 155/2 | Completed
2024-11-18 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-18 | 2024-11-04 | 2024-11-21 | Senahul | 54.4178 | 3.0232 | TA325 | 254/0 | Completed
2024-11-18 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.4589 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-18 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 164/4 | Completed
2024-11-18 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.6321 | 3.1097 | TA325 | 264/0 | Completed
2024-11-19 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.4077 | 6.7434 | TA325 | 128/0 | Completed
2024-11-19 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-11-19 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.0448 | 5.1493 | TA325 | 137A/5 | Completed
2024-11-19 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-19 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-19 | 2024-11-13 | 2024-12-02 | Modina India | 36.0448 | 1.8022 | TA325 | 147/3 | Completed
2024-11-19 | 2024-11-18 | 2024-11-24 | Mukesh | 65.7565 | 9.3938 | TA325 | 144A/0 | Completed
2024-11-19 | 2024-11-18 | 2024-12-08 | Mukesh | 82.2388 | 3.9161 | TA325 | 145/0 | Completed
2024-11-19 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-19 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.4589 | 5.637 | TA325 | 155/3 | Completed
2024-11-19 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.4589 | 2.6306 | TA325 | 155/2 | Completed
2024-11-19 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-19 | 2024-11-04 | 2024-11-21 | Senahul | 54.4178 | 3.0232 | TA325 | 254/0 | Completed
2024-11-19 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.4589 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-19 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 164/4 | Completed
2024-11-19 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.6321 | 3.1097 | TA325 | 264/0 | Completed
2024-11-20 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.4077 | 6.7434 | TA325 | 128/0 | Completed
2024-11-20 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-11-20 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.0448 | 5.1493 | TA325 | 137A/5 | Completed
2024-11-20 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.7282 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-20 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-20 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.2993 | 6.0214 | TA325 | 117/0 | Completed
2024-11-20 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-20 | 2024-11-13 | 2024-12-02 | Modina India | 36.0448 | 1.8022 | TA325 | 147/3 | Completed
2024-11-20 | 2024-11-18 | 2024-11-24 | Mukesh | 65.7565 | 9.3938 | TA325 | 144A/0 | Completed
2024-11-20 | 2024-11-18 | 2024-12-08 | Mukesh | 82.2388 | 3.9161 | TA325 | 145/0 | Completed
2024-11-20 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-20 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.4589 | 5.637 | TA325 | 155/3 | Completed
2024-11-20 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.4589 | 2.6306 | TA325 | 155/2 | Completed
2024-11-20 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-20 | 2024-11-04 | 2024-11-21 | Senahul | 54.4178 | 3.0232 | TA325 | 254/0 | Completed
2024-11-20 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.4589 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-20 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 164/4 | Completed
2024-11-20 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.6321 | 3.1097 | TA325 | 264/0 | Completed
2024-11-21 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.4077 | 6.7434 | TA325 | 128/0 | Completed
2024-11-21 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-11-21 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.7282 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-21 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-21 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.2993 | 6.0214 | TA325 | 117/0 | Completed
2024-11-21 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-21 | 2024-11-13 | 2024-12-02 | Modina India | 36.0448 | 1.8022 | TA325 | 147/3 | Completed
2024-11-21 | 2024-11-18 | 2024-11-24 | Mukesh | 65.7565 | 9.3938 | TA325 | 144A/0 | Completed
2024-11-21 | 2024-11-18 | 2024-12-08 | Mukesh | 82.2388 | 3.9161 | TA325 | 145/0 | Completed
2024-11-21 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-21 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.4589 | 5.637 | TA325 | 155/3 | Completed
2024-11-21 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.4589 | 2.6306 | TA325 | 155/2 | Completed
2024-11-21 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-21 | 2024-11-04 | 2024-11-21 | Senahul | 54.4178 | 3.0232 | TA325 | 254/0 | Completed
2024-11-21 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.4589 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-21 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 164/4 | Completed
2024-11-21 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.6321 | 3.1097 | TA325 | 264/0 | Completed
2024-11-22 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.4077 | 6.7434 | TA325 | 128/0 | Completed
2024-11-22 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-11-22 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-11-22 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.7282 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-22 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-22 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.2993 | 6.0214 | TA325 | 117/0 | Completed
2024-11-22 | 2024-11-22 | 2024-11-26 | Jwala | 37.7305 | 7.5461 | TA325 | 187/3 | Completed
2024-11-22 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-22 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.0448 | 4.005 | TA325 | 191A/1 | Completed
2024-11-22 | 2024-11-13 | 2024-12-02 | Modina India | 36.0448 | 1.8022 | TA325 | 147/3 | Completed
2024-11-22 | 2024-11-18 | 2024-11-24 | Mukesh | 65.7565 | 9.3938 | TA325 | 144A/0 | Completed
2024-11-22 | 2024-11-18 | 2024-12-08 | Mukesh | 82.2388 | 3.9161 | TA325 | 145/0 | Completed
2024-11-22 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-22 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.4589 | 5.637 | TA325 | 155/3 | Completed
2024-11-22 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.4589 | 2.6306 | TA325 | 155/2 | Completed
2024-11-22 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-22 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.4589 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-22 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 164/4 | Completed
2024-11-22 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.6321 | 3.1097 | TA325 | 264/0 | Completed
2024-11-23 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.4077 | 6.7434 | TA325 | 128/0 | Completed
2024-11-23 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-11-23 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-11-23 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.7282 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-23 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-23 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-11-23 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.2993 | 6.0214 | TA325 | 117/0 | Completed
2024-11-23 | 2024-11-22 | 2024-11-26 | Jwala | 37.7305 | 7.5461 | TA325 | 187/3 | Completed
2024-11-23 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-23 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.0448 | 4.005 | TA325 | 191A/1 | Completed
2024-11-23 | 2024-11-13 | 2024-12-02 | Modina India | 36.0448 | 1.8022 | TA325 | 147/3 | Completed
2024-11-23 | 2024-11-18 | 2024-11-24 | Mukesh | 65.7565 | 9.3938 | TA325 | 144A/0 | Completed
2024-11-23 | 2024-11-18 | 2024-12-08 | Mukesh | 82.2388 | 3.9161 | TA325 | 145/0 | Completed
2024-11-23 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-23 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.4589 | 2.6306 | TA325 | 155/2 | Completed
2024-11-23 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-23 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.7305 | 3.773 | TA325 | 150A/2 | Completed
2024-11-23 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 164/4 | Completed
2024-11-23 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.6321 | 3.1097 | TA325 | 264/0 | Completed
2024-11-24 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.4077 | 6.7434 | TA325 | 128/0 | Completed
2024-11-24 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-11-24 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-11-24 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.7282 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-24 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-24 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-11-24 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.2993 | 6.0214 | TA325 | 117/0 | Completed
2024-11-24 | 2024-11-22 | 2024-11-26 | Jwala | 37.7305 | 7.5461 | TA325 | 187/3 | Completed
2024-11-24 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-24 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.0448 | 4.005 | TA325 | 191A/1 | Completed
2024-11-24 | 2024-11-13 | 2024-12-02 | Modina India | 36.0448 | 1.8022 | TA325 | 147/3 | Completed
2024-11-24 | 2024-11-18 | 2024-11-24 | Mukesh | 65.7565 | 9.3938 | TA325 | 144A/0 | Completed
2024-11-24 | 2024-11-18 | 2024-12-08 | Mukesh | 82.2388 | 3.9161 | TA325 | 145/0 | Completed
2024-11-24 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-24 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.4589 | 2.6306 | TA325 | 155/2 | Completed
2024-11-24 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-24 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.7305 | 3.773 | TA325 | 150A/2 | Completed
2024-11-24 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 164/4 | Completed
2024-11-24 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.6321 | 3.1097 | TA325 | 264/0 | Completed
2024-11-25 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.4077 | 6.7434 | TA325 | 128/0 | Completed
2024-11-25 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-11-25 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-11-25 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.7282 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-25 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-25 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-11-25 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.2993 | 6.0214 | TA325 | 117/0 | Completed
2024-11-25 | 2024-11-22 | 2024-11-26 | Jwala | 37.7305 | 7.5461 | TA325 | 187/3 | Completed
2024-11-25 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-25 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.0448 | 4.005 | TA325 | 191A/1 | Completed
2024-11-25 | 2024-11-13 | 2024-12-02 | Modina India | 36.0448 | 1.8022 | TA325 | 147/3 | Completed
2024-11-25 | 2024-11-18 | 2024-12-08 | Mukesh | 82.2388 | 3.9161 | TA325 | 145/0 | Completed
2024-11-25 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-25 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.4589 | 2.6306 | TA325 | 155/2 | Completed
2024-11-25 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-25 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.7305 | 3.773 | TA325 | 150A/2 | Completed
2024-11-25 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 164/4 | Completed
2024-11-25 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.6321 | 3.1097 | TA325 | 264/0 | Completed
2024-11-26 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.4077 | 6.7434 | TA325 | 128/0 | Completed
2024-11-26 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-11-26 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-11-26 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.7282 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-26 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-26 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-11-26 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.2993 | 6.0214 | TA325 | 117/0 | Completed
2024-11-26 | 2024-11-22 | 2024-11-26 | Jwala | 37.7305 | 7.5461 | TA325 | 187/3 | Completed
2024-11-26 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-26 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.0448 | 4.005 | TA325 | 191A/1 | Completed
2024-11-26 | 2024-11-13 | 2024-12-02 | Modina India | 36.0448 | 1.8022 | TA325 | 147/3 | Completed
2024-11-26 | 2024-11-18 | 2024-12-08 | Mukesh | 82.2388 | 3.9161 | TA325 | 145/0 | Completed
2024-11-26 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-26 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.4589 | 2.6306 | TA325 | 155/2 | Completed
2024-11-26 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-26 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.7305 | 3.773 | TA325 | 150A/2 | Completed
2024-11-26 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 164/4 | Completed
2024-11-26 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.6321 | 3.1097 | TA325 | 264/0 | Completed
2024-11-27 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.4589 | 3.5872 | TA325 | 127/5 | Completed
2024-11-27 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-11-27 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-11-27 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.7282 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-27 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-27 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-11-27 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.2993 | 6.0214 | TA325 | 117/0 | Completed
2024-11-27 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-11-27 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-27 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.0448 | 4.005 | TA325 | 191A/1 | Completed
2024-11-27 | 2024-11-13 | 2024-12-02 | Modina India | 36.0448 | 1.8022 | TA325 | 147/3 | Completed
2024-11-27 | 2024-11-18 | 2024-12-08 | Mukesh | 82.2388 | 3.9161 | TA325 | 145/0 | Completed
2024-11-27 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-27 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.4589 | 2.6306 | TA325 | 155/2 | Completed
2024-11-27 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-27 | 2024-11-27 | 2024-12-21 | Senahul | 84.2993 | 3.372 | TA325 | 255/0 | Completed
2024-11-27 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.7305 | 3.773 | TA325 | 150A/2 | Completed
2024-11-27 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 164/4 | Completed
2024-11-27 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.6321 | 3.1097 | TA325 | 264/0 | Completed
2024-11-28 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.4589 | 3.5872 | TA325 | 127/5 | Completed
2024-11-28 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-11-28 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-11-28 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.7282 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-28 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-28 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-11-28 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.2993 | 6.0214 | TA325 | 117/0 | Completed
2024-11-28 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-11-28 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-28 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.0448 | 4.005 | TA325 | 191A/1 | Completed
2024-11-28 | 2024-11-13 | 2024-12-02 | Modina India | 36.0448 | 1.8022 | TA325 | 147/3 | Completed
2024-11-28 | 2024-11-18 | 2024-12-08 | Mukesh | 82.2388 | 3.9161 | TA325 | 145/0 | Completed
2024-11-28 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.7305 | 1.7967 | TA325 | 163/3 | Completed
2024-11-28 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-11-28 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-28 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.4589 | 2.6306 | TA325 | 155/2 | Completed
2024-11-28 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-28 | 2024-11-27 | 2024-12-21 | Senahul | 84.2993 | 3.372 | TA325 | 255/0 | Completed
2024-11-28 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.7305 | 3.773 | TA325 | 150A/2 | Completed
2024-11-28 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.7305 | 2.2194 | TA325 | 164/5 | Completed
2024-11-28 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.6321 | 3.1097 | TA325 | 264/0 | Completed
2024-11-29 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.4589 | 3.5872 | TA325 | 127/5 | Completed
2024-11-29 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-11-29 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-11-29 | 2024-11-29 | 2024-12-03 | Dhaneswar Mahto | 36.0448 | 7.209 | TA325 | 137A/4 | Completed
2024-11-29 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-29 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-11-29 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.2993 | 6.0214 | TA325 | 117/0 | Completed
2024-11-29 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-11-29 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-29 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.0448 | 4.005 | TA325 | 191A/1 | Completed
2024-11-29 | 2024-11-13 | 2024-12-02 | Modina India | 36.0448 | 1.8022 | TA325 | 147/3 | Completed
2024-11-29 | 2024-11-18 | 2024-12-08 | Mukesh | 82.2388 | 3.9161 | TA325 | 145/0 | Completed
2024-11-29 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.7305 | 1.7967 | TA325 | 163/3 | Completed
2024-11-29 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-11-29 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-29 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.4589 | 2.6306 | TA325 | 155/2 | Completed
2024-11-29 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-29 | 2024-11-27 | 2024-12-21 | Senahul | 84.2993 | 3.372 | TA325 | 255/0 | Completed
2024-11-29 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.7305 | 3.773 | TA325 | 150A/2 | Completed
2024-11-29 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.7305 | 2.2194 | TA325 | 164/5 | Completed
2024-11-29 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.6321 | 3.1097 | TA325 | 264/0 | Completed
2024-11-30 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.4589 | 3.5872 | TA325 | 127/5 | Completed
2024-11-30 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-11-30 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-11-30 | 2024-11-29 | 2024-12-03 | Dhaneswar Mahto | 36.0448 | 7.209 | TA325 | 137A/4 | Completed
2024-11-30 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-30 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-11-30 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.2993 | 6.0214 | TA325 | 117/0 | Completed
2024-11-30 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-11-30 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-30 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.0448 | 4.005 | TA325 | 191A/1 | Completed
2024-11-30 | 2024-11-13 | 2024-12-02 | Modina India | 36.0448 | 1.8022 | TA325 | 147/3 | Completed
2024-11-30 | 2024-11-18 | 2024-12-08 | Mukesh | 82.2388 | 3.9161 | TA325 | 145/0 | Completed
2024-11-30 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.7305 | 1.7967 | TA325 | 163/3 | Completed
2024-11-30 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-11-30 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-30 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.4589 | 2.6306 | TA325 | 155/2 | Completed
2024-11-30 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-30 | 2024-11-27 | 2024-12-21 | Senahul | 84.2993 | 3.372 | TA325 | 255/0 | Completed
2024-11-30 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.7305 | 3.773 | TA325 | 150A/2 | Completed
2024-11-30 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.7305 | 2.2194 | TA325 | 164/5 | Completed
2024-11-30 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.6321 | 3.1097 | TA325 | 264/0 | Completed
2024-12-01 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.4589 | 3.5872 | TA325 | 127/5 | Completed
2024-12-01 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-01 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-12-01 | 2024-11-29 | 2024-12-03 | Dhaneswar Mahto | 36.0448 | 7.209 | TA325 | 137A/4 | Completed
2024-12-01 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-12-01 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-01 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.2993 | 6.0214 | TA325 | 117/0 | Completed
2024-12-01 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-01 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-01 | 2024-11-13 | 2024-12-02 | Modina India | 36.0448 | 1.8022 | TA325 | 147/3 | Completed
2024-12-01 | 2024-11-18 | 2024-12-08 | Mukesh | 82.2388 | 3.9161 | TA325 | 145/0 | Completed
2024-12-01 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.7305 | 1.7967 | TA325 | 163/3 | Completed
2024-12-01 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-01 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-01 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-01 | 2024-11-27 | 2024-12-21 | Senahul | 84.2993 | 3.372 | TA325 | 255/0 | Completed
2024-12-01 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.7305 | 3.773 | TA325 | 150A/2 | Completed
2024-12-01 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.7305 | 2.2194 | TA325 | 164/5 | Completed
2024-12-01 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.6321 | 3.1097 | TA325 | 264/0 | Completed
2024-12-02 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.4589 | 3.5872 | TA325 | 127/5 | Completed
2024-12-02 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-02 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-12-02 | 2024-11-29 | 2024-12-03 | Dhaneswar Mahto | 36.0448 | 7.209 | TA325 | 137A/4 | Completed
2024-12-02 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-12-02 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-02 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.2993 | 6.0214 | TA325 | 117/0 | Completed
2024-12-02 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-02 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-02 | 2024-12-02 | 2024-12-16 | Mjr | 46.6235 | 3.1082 | TA325 | 272/1 | Completed
2024-12-02 | 2024-11-13 | 2024-12-02 | Modina India | 36.0448 | 1.8022 | TA325 | 147/3 | Completed
2024-12-02 | 2024-11-18 | 2024-12-08 | Mukesh | 82.2388 | 3.9161 | TA325 | 145/0 | Completed
2024-12-02 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.7305 | 1.7967 | TA325 | 163/3 | Completed
2024-12-02 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-02 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-02 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-02 | 2024-11-27 | 2024-12-21 | Senahul | 84.2993 | 3.372 | TA325 | 255/0 | Completed
2024-12-02 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.7305 | 3.773 | TA325 | 150A/2 | Completed
2024-12-02 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.7305 | 2.2194 | TA325 | 164/5 | Completed
2024-12-02 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.6321 | 3.1097 | TA325 | 264/0 | Completed
2024-12-03 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.4589 | 3.5872 | TA325 | 127/5 | Completed
2024-12-03 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-03 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-12-03 | 2024-11-29 | 2024-12-03 | Dhaneswar Mahto | 36.0448 | 7.209 | TA325 | 137A/4 | Completed
2024-12-03 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-12-03 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-03 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.2993 | 6.0214 | TA325 | 117/0 | Completed
2024-12-03 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-03 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-03 | 2024-12-02 | 2024-12-16 | Mjr | 46.6235 | 3.1082 | TA325 | 272/1 | Completed
2024-12-03 | 2024-12-03 | 2024-12-22 | Modina India | 44.7282 | 2.2364 | TA325 | 147/5 | Completed
2024-12-03 | 2024-11-18 | 2024-12-08 | Mukesh | 82.2388 | 3.9161 | TA325 | 145/0 | Completed
2024-12-03 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.7305 | 1.7967 | TA325 | 163/3 | Completed
2024-12-03 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-03 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-03 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-03 | 2024-11-27 | 2024-12-21 | Senahul | 84.2993 | 3.372 | TA325 | 255/0 | Completed
2024-12-03 | 2024-12-03 | 2024-12-28 | Senahul | 65.7565 | 2.5291 | TA325 | 251/0 | Completed
2024-12-03 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.7305 | 2.2194 | TA325 | 164/5 | Completed
2024-12-03 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.6321 | 3.1097 | TA325 | 264/0 | Completed
2024-12-04 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.4589 | 3.5872 | TA325 | 127/5 | Completed
2024-12-04 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-04 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-12-04 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.6077 | 6.4475 | TA325 | 134/0 | Completed
2024-12-04 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-12-04 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-04 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.6077 | 6.4475 | TA325 | 115/0 | Completed
2024-12-04 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-04 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-04 | 2024-12-02 | 2024-12-16 | Mjr | 46.6235 | 3.1082 | TA325 | 272/1 | Completed
2024-12-04 | 2024-12-03 | 2024-12-22 | Modina India | 44.7282 | 2.2364 | TA325 | 147/5 | Completed
2024-12-04 | 2024-11-18 | 2024-12-08 | Mukesh | 82.2388 | 3.9161 | TA325 | 145/0 | Completed
2024-12-04 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.7305 | 1.7967 | TA325 | 163/3 | Completed
2024-12-04 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-04 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-04 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-04 | 2024-11-27 | 2024-12-21 | Senahul | 84.2993 | 3.372 | TA325 | 255/0 | Completed
2024-12-04 | 2024-12-03 | 2024-12-28 | Senahul | 65.7565 | 2.5291 | TA325 | 251/0 | Completed
2024-12-04 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.7305 | 2.2194 | TA325 | 164/5 | Completed
2024-12-04 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.6321 | 3.1097 | TA325 | 264/0 | Completed
2024-12-05 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.4589 | 3.5872 | TA325 | 127/5 | Completed
2024-12-05 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-05 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-12-05 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.6077 | 6.4475 | TA325 | 134/0 | Completed
2024-12-05 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-12-05 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-05 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.6077 | 6.4475 | TA325 | 115/0 | Completed
2024-12-05 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-05 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-05 | 2024-12-02 | 2024-12-16 | Mjr | 46.6235 | 3.1082 | TA325 | 272/1 | Completed
2024-12-05 | 2024-12-03 | 2024-12-22 | Modina India | 44.7282 | 2.2364 | TA325 | 147/5 | Completed
2024-12-05 | 2024-11-18 | 2024-12-08 | Mukesh | 82.2388 | 3.9161 | TA325 | 145/0 | Completed
2024-12-05 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.7305 | 1.7967 | TA325 | 163/3 | Completed
2024-12-05 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-05 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-05 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-05 | 2024-11-27 | 2024-12-21 | Senahul | 84.2993 | 3.372 | TA325 | 255/0 | Completed
2024-12-05 | 2024-12-03 | 2024-12-28 | Senahul | 65.7565 | 2.5291 | TA325 | 251/0 | Completed
2024-12-05 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.7305 | 2.2194 | TA325 | 164/5 | Completed
2024-12-05 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.6321 | 3.1097 | TA325 | 264/0 | Completed
2024-12-06 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.4589 | 3.5872 | TA325 | 127/5 | Completed
2024-12-06 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-06 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-12-06 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.6077 | 6.4475 | TA325 | 134/0 | Completed
2024-12-06 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-12-06 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-06 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.6077 | 6.4475 | TA325 | 115/0 | Completed
2024-12-06 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-06 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-06 | 2024-12-02 | 2024-12-16 | Mjr | 46.6235 | 3.1082 | TA325 | 272/1 | Completed
2024-12-06 | 2024-12-03 | 2024-12-22 | Modina India | 44.7282 | 2.2364 | TA325 | 147/5 | Completed
2024-12-06 | 2024-11-18 | 2024-12-08 | Mukesh | 82.2388 | 3.9161 | TA325 | 145/0 | Completed
2024-12-06 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.7305 | 1.7967 | TA325 | 163/3 | Completed
2024-12-06 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-06 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-06 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-06 | 2024-11-27 | 2024-12-21 | Senahul | 84.2993 | 3.372 | TA325 | 255/0 | Completed
2024-12-06 | 2024-12-03 | 2024-12-28 | Senahul | 65.7565 | 2.5291 | TA325 | 251/0 | Completed
2024-12-06 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.7305 | 2.2194 | TA325 | 164/5 | Completed
2024-12-06 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.6321 | 3.1097 | TA325 | 264/0 | Completed
2024-12-07 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.4589 | 3.5872 | TA325 | 127/5 | Completed
2024-12-07 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-07 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-12-07 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.6077 | 6.4475 | TA325 | 134/0 | Completed
2024-12-07 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-12-07 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-07 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.6077 | 6.4475 | TA325 | 115/0 | Completed
2024-12-07 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-07 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-07 | 2024-12-02 | 2024-12-16 | Mjr | 46.6235 | 3.1082 | TA325 | 272/1 | Completed
2024-12-07 | 2024-12-03 | 2024-12-22 | Modina India | 44.7282 | 2.2364 | TA325 | 147/5 | Completed
2024-12-07 | 2024-11-18 | 2024-12-08 | Mukesh | 82.2388 | 3.9161 | TA325 | 145/0 | Completed
2024-12-07 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.7305 | 1.7967 | TA325 | 163/3 | Completed
2024-12-07 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-07 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-07 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-07 | 2024-11-27 | 2024-12-21 | Senahul | 84.2993 | 3.372 | TA325 | 255/0 | Completed
2024-12-07 | 2024-12-03 | 2024-12-28 | Senahul | 65.7565 | 2.5291 | TA325 | 251/0 | Completed
2024-12-07 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.7305 | 2.2194 | TA325 | 164/5 | Completed
2024-12-07 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.6321 | 3.1097 | TA325 | 264/0 | Completed
2024-12-08 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-08 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.6077 | 6.4475 | TA325 | 134/0 | Completed
2024-12-08 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-12-08 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-08 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.6077 | 6.4475 | TA325 | 115/0 | Completed
2024-12-08 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-08 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-08 | 2024-12-02 | 2024-12-16 | Mjr | 46.6235 | 3.1082 | TA325 | 272/1 | Completed
2024-12-08 | 2024-12-03 | 2024-12-22 | Modina India | 44.7282 | 2.2364 | TA325 | 147/5 | Completed
2024-12-08 | 2024-11-18 | 2024-12-08 | Mukesh | 82.2388 | 3.9161 | TA325 | 145/0 | Completed
2024-12-08 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.7305 | 1.7967 | TA325 | 163/3 | Completed
2024-12-08 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-08 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-08 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-08 | 2024-11-27 | 2024-12-21 | Senahul | 84.2993 | 3.372 | TA325 | 255/0 | Completed
2024-12-08 | 2024-12-03 | 2024-12-28 | Senahul | 65.7565 | 2.5291 | TA325 | 251/0 | Completed
2024-12-08 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.2679 | 4.7334 | TA325 | 132/0 | Completed
2024-12-08 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.7305 | 2.2194 | TA325 | 164/5 | Completed
2024-12-08 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.6321 | 3.1097 | TA325 | 264/0 | Completed
2024-12-09 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-09 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.6077 | 6.4475 | TA325 | 134/0 | Completed
2024-12-09 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.7305 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-09 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-09 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.6077 | 6.4475 | TA325 | 115/0 | Completed
2024-12-09 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-09 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-09 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.7305 | 2.5154 | TA325 | 191/1 | Completed
2024-12-09 | 2024-12-02 | 2024-12-16 | Mjr | 46.6235 | 3.1082 | TA325 | 272/1 | Completed
2024-12-09 | 2024-12-03 | 2024-12-22 | Modina India | 44.7282 | 2.2364 | TA325 | 147/5 | Completed
2024-12-09 | 2024-12-09 | 2024-12-16 | Mukesh | 64.2538 | 8.0317 | TA325 | 147/1 | Completed
2024-12-09 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.7305 | 1.7967 | TA325 | 163/3 | Completed
2024-12-09 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-09 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-09 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-09 | 2024-11-27 | 2024-12-21 | Senahul | 84.2993 | 3.372 | TA325 | 255/0 | Completed
2024-12-09 | 2024-12-03 | 2024-12-28 | Senahul | 65.7565 | 2.5291 | TA325 | 251/0 | Completed
2024-12-09 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.2679 | 4.7334 | TA325 | 132/0 | Completed
2024-12-09 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.7305 | 2.2194 | TA325 | 164/5 | Completed
2024-12-09 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.6321 | 3.1097 | TA325 | 264/0 | Completed
2024-12-10 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-10 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.6077 | 6.4475 | TA325 | 134/0 | Completed
2024-12-10 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.7305 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-10 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-10 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.6077 | 6.4475 | TA325 | 115/0 | Completed
2024-12-10 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-10 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-10 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.7305 | 2.5154 | TA325 | 191/1 | Completed
2024-12-10 | 2024-12-02 | 2024-12-16 | Mjr | 46.6235 | 3.1082 | TA325 | 272/1 | Completed
2024-12-10 | 2024-12-03 | 2024-12-22 | Modina India | 44.7282 | 2.2364 | TA325 | 147/5 | Completed
2024-12-10 | 2024-12-10 | 2024-12-25 | Modina India | 39.4589 | 2.4662 | TA325 | 147/4 | Completed
2024-12-10 | 2024-12-09 | 2024-12-16 | Mukesh | 64.2538 | 8.0317 | TA325 | 147/1 | Completed
2024-12-10 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.7305 | 1.7967 | TA325 | 163/3 | Completed
2024-12-10 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-10 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-10 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-10 | 2024-11-27 | 2024-12-21 | Senahul | 84.2993 | 3.372 | TA325 | 255/0 | Completed
2024-12-10 | 2024-12-03 | 2024-12-28 | Senahul | 65.7565 | 2.5291 | TA325 | 251/0 | Completed
2024-12-10 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.2679 | 4.7334 | TA325 | 132/0 | Completed
2024-12-10 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.7305 | 2.2194 | TA325 | 164/5 | Completed
2024-12-10 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.6321 | 3.1097 | TA325 | 264/0 | Completed
2024-12-11 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-11 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.7305 | 2.695 | TA325 | 270/1 | Completed
2024-12-11 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.6077 | 6.4475 | TA325 | 134/0 | Completed
2024-12-11 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.7305 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-11 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-11 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.6077 | 6.4475 | TA325 | 115/0 | Completed
2024-12-11 | 2024-12-11 | 2024-12-21 | Jwala | 94.4077 | 8.5825 | TA325 | 193/0 | Completed
2024-12-11 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-11 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.7305 | 2.5154 | TA325 | 191/1 | Completed
2024-12-11 | 2024-12-02 | 2024-12-16 | Mjr | 46.6235 | 3.1082 | TA325 | 272/1 | Completed
2024-12-11 | 2024-12-03 | 2024-12-22 | Modina India | 44.7282 | 2.2364 | TA325 | 147/5 | Completed
2024-12-11 | 2024-12-10 | 2024-12-25 | Modina India | 39.4589 | 2.4662 | TA325 | 147/4 | Completed
2024-12-11 | 2024-12-09 | 2024-12-16 | Mukesh | 64.2538 | 8.0317 | TA325 | 147/1 | Completed
2024-12-11 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.7305 | 1.7967 | TA325 | 163/3 | Completed
2024-12-11 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-11 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-11 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-11 | 2024-11-27 | 2024-12-21 | Senahul | 84.2993 | 3.372 | TA325 | 255/0 | Completed
2024-12-11 | 2024-12-03 | 2024-12-28 | Senahul | 65.7565 | 2.5291 | TA325 | 251/0 | Completed
2024-12-11 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.2679 | 4.7334 | TA325 | 132/0 | Completed
2024-12-11 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.7305 | 2.2194 | TA325 | 164/5 | Completed
2024-12-11 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.6321 | 3.5539 | TA325 | 272/0 | Completed
2024-12-12 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-12 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.7305 | 2.695 | TA325 | 270/1 | Completed
2024-12-12 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.6077 | 6.4475 | TA325 | 134/0 | Completed
2024-12-12 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.7305 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-12 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-12 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.6077 | 6.4475 | TA325 | 115/0 | Completed
2024-12-12 | 2024-12-11 | 2024-12-21 | Jwala | 94.4077 | 8.5825 | TA325 | 193/0 | Completed
2024-12-12 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-12 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.7305 | 2.5154 | TA325 | 191/1 | Completed
2024-12-12 | 2024-12-02 | 2024-12-16 | Mjr | 46.6235 | 3.1082 | TA325 | 272/1 | Completed
2024-12-12 | 2024-12-03 | 2024-12-22 | Modina India | 44.7282 | 2.2364 | TA325 | 147/5 | Completed
2024-12-12 | 2024-12-10 | 2024-12-25 | Modina India | 39.4589 | 2.4662 | TA325 | 147/4 | Completed
2024-12-12 | 2024-12-09 | 2024-12-16 | Mukesh | 64.2538 | 8.0317 | TA325 | 147/1 | Completed
2024-12-12 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.7305 | 1.7967 | TA325 | 163/3 | Completed
2024-12-12 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-12 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-12 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-12 | 2024-11-27 | 2024-12-21 | Senahul | 84.2993 | 3.372 | TA325 | 255/0 | Completed
2024-12-12 | 2024-12-03 | 2024-12-28 | Senahul | 65.7565 | 2.5291 | TA325 | 251/0 | Completed
2024-12-12 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.2679 | 4.7334 | TA325 | 132/0 | Completed
2024-12-12 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.7305 | 2.2194 | TA325 | 164/5 | Completed
2024-12-12 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.6321 | 3.5539 | TA325 | 272/0 | Completed
2024-12-13 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-13 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.7305 | 2.695 | TA325 | 270/1 | Completed
2024-12-13 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.6077 | 6.4475 | TA325 | 134/0 | Completed
2024-12-13 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.7305 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-13 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-13 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.6077 | 6.4475 | TA325 | 115/0 | Completed
2024-12-13 | 2024-12-11 | 2024-12-21 | Jwala | 94.4077 | 8.5825 | TA325 | 193/0 | Completed
2024-12-13 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-13 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.7305 | 2.5154 | TA325 | 191/1 | Completed
2024-12-13 | 2024-12-02 | 2024-12-16 | Mjr | 46.6235 | 3.1082 | TA325 | 272/1 | Completed
2024-12-13 | 2024-12-03 | 2024-12-22 | Modina India | 44.7282 | 2.2364 | TA325 | 147/5 | Completed
2024-12-13 | 2024-12-10 | 2024-12-25 | Modina India | 39.4589 | 2.4662 | TA325 | 147/4 | Completed
2024-12-13 | 2024-12-09 | 2024-12-16 | Mukesh | 64.2538 | 8.0317 | TA325 | 147/1 | Completed
2024-12-13 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.7305 | 1.7967 | TA325 | 163/3 | Completed
2024-12-13 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-13 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-13 | 2024-11-27 | 2024-12-21 | Senahul | 84.2993 | 3.372 | TA325 | 255/0 | Completed
2024-12-13 | 2024-12-03 | 2024-12-28 | Senahul | 65.7565 | 2.5291 | TA325 | 251/0 | Completed
2024-12-13 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.2679 | 4.7334 | TA325 | 132/0 | Completed
2024-12-13 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.7305 | 2.2194 | TA325 | 164/5 | Completed
2024-12-13 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.6321 | 3.5539 | TA325 | 272/0 | Completed
2024-12-14 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-14 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.7305 | 2.695 | TA325 | 270/1 | Completed
2024-12-14 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.6077 | 6.4475 | TA325 | 134/0 | Completed
2024-12-14 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.7305 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-14 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-14 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.6077 | 6.4475 | TA325 | 115/0 | Completed
2024-12-14 | 2024-12-11 | 2024-12-21 | Jwala | 94.4077 | 8.5825 | TA325 | 193/0 | Completed
2024-12-14 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-14 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.7305 | 2.5154 | TA325 | 191/1 | Completed
2024-12-14 | 2024-12-02 | 2024-12-16 | Mjr | 46.6235 | 3.1082 | TA325 | 272/1 | Completed
2024-12-14 | 2024-12-03 | 2024-12-22 | Modina India | 44.7282 | 2.2364 | TA325 | 147/5 | Completed
2024-12-14 | 2024-12-10 | 2024-12-25 | Modina India | 39.4589 | 2.4662 | TA325 | 147/4 | Completed
2024-12-14 | 2024-12-09 | 2024-12-16 | Mukesh | 64.2538 | 8.0317 | TA325 | 147/1 | Completed
2024-12-14 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.7305 | 1.7967 | TA325 | 163/3 | Completed
2024-12-14 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-14 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-14 | 2024-11-27 | 2024-12-21 | Senahul | 84.2993 | 3.372 | TA325 | 255/0 | Completed
2024-12-14 | 2024-12-03 | 2024-12-28 | Senahul | 65.7565 | 2.5291 | TA325 | 251/0 | Completed
2024-12-14 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.2679 | 4.7334 | TA325 | 132/0 | Completed
2024-12-14 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.7305 | 2.2194 | TA325 | 164/5 | Completed
2024-12-14 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 164/6 | Completed
2024-12-14 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.6321 | 3.5539 | TA325 | 272/0 | Completed
2024-12-15 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.7305 | 2.695 | TA325 | 270/1 | Completed
2024-12-15 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.6077 | 6.4475 | TA325 | 134/0 | Completed
2024-12-15 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.7305 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-15 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-15 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.6077 | 6.4475 | TA325 | 115/0 | Completed
2024-12-15 | 2024-12-11 | 2024-12-21 | Jwala | 94.4077 | 8.5825 | TA325 | 193/0 | Completed
2024-12-15 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-15 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.7305 | 2.5154 | TA325 | 191/1 | Completed
2024-12-15 | 2024-12-02 | 2024-12-16 | Mjr | 46.6235 | 3.1082 | TA325 | 272/1 | Completed
2024-12-15 | 2024-12-03 | 2024-12-22 | Modina India | 44.7282 | 2.2364 | TA325 | 147/5 | Completed
2024-12-15 | 2024-12-10 | 2024-12-25 | Modina India | 39.4589 | 2.4662 | TA325 | 147/4 | Completed
2024-12-15 | 2024-12-09 | 2024-12-16 | Mukesh | 64.2538 | 8.0317 | TA325 | 147/1 | Completed
2024-12-15 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.7305 | 1.7967 | TA325 | 163/3 | Completed
2024-12-15 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-15 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-15 | 2024-11-27 | 2024-12-21 | Senahul | 84.2993 | 3.372 | TA325 | 255/0 | Completed
2024-12-15 | 2024-12-03 | 2024-12-28 | Senahul | 65.7565 | 2.5291 | TA325 | 251/0 | Completed
2024-12-15 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.2679 | 4.7334 | TA325 | 132/0 | Completed
2024-12-15 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 164/6 | Completed
2024-12-15 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.6321 | 3.5539 | TA325 | 272/0 | Completed
2024-12-16 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.7305 | 2.695 | TA325 | 270/1 | Completed
2024-12-16 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.6077 | 6.4475 | TA325 | 134/0 | Completed
2024-12-16 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.7305 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-16 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-16 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.6077 | 6.4475 | TA325 | 115/0 | Completed
2024-12-16 | 2024-12-11 | 2024-12-21 | Jwala | 94.4077 | 8.5825 | TA325 | 193/0 | Completed
2024-12-16 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-16 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.7305 | 2.5154 | TA325 | 191/1 | Completed
2024-12-16 | 2024-12-02 | 2024-12-16 | Mjr | 46.6235 | 3.1082 | TA325 | 272/1 | Completed
2024-12-16 | 2024-12-03 | 2024-12-22 | Modina India | 44.7282 | 2.2364 | TA325 | 147/5 | Completed
2024-12-16 | 2024-12-10 | 2024-12-25 | Modina India | 39.4589 | 2.4662 | TA325 | 147/4 | Completed
2024-12-16 | 2024-12-09 | 2024-12-16 | Mukesh | 64.2538 | 8.0317 | TA325 | 147/1 | Completed
2024-12-16 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.7305 | 1.7967 | TA325 | 163/3 | Completed
2024-12-16 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-16 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-16 | 2024-11-27 | 2024-12-21 | Senahul | 84.2993 | 3.372 | TA325 | 255/0 | Completed
2024-12-16 | 2024-12-03 | 2024-12-28 | Senahul | 65.7565 | 2.5291 | TA325 | 251/0 | Completed
2024-12-16 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.2679 | 4.7334 | TA325 | 132/0 | Completed
2024-12-16 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 164/6 | Completed
2024-12-16 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.6321 | 3.5539 | TA325 | 272/0 | Completed
2024-12-17 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.7305 | 2.695 | TA325 | 270/1 | Completed
2024-12-17 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.6077 | 6.4475 | TA325 | 134/0 | Completed
2024-12-17 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.7305 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-17 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-17 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.6077 | 6.4475 | TA325 | 115/0 | Completed
2024-12-17 | 2024-12-11 | 2024-12-21 | Jwala | 94.4077 | 8.5825 | TA325 | 193/0 | Completed
2024-12-17 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-17 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.7305 | 2.5154 | TA325 | 191/1 | Completed
2024-12-17 | 2024-12-03 | 2024-12-22 | Modina India | 44.7282 | 2.2364 | TA325 | 147/5 | Completed
2024-12-17 | 2024-12-10 | 2024-12-25 | Modina India | 39.4589 | 2.4662 | TA325 | 147/4 | Completed
2024-12-17 | 2024-12-17 | 2024-12-23 | Mukesh | 64.2538 | 9.1791 | TA325 | 147/2 | Completed
2024-12-17 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.7305 | 1.7967 | TA325 | 163/3 | Completed
2024-12-17 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-17 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-17 | 2024-11-27 | 2024-12-21 | Senahul | 84.2993 | 3.372 | TA325 | 255/0 | Completed
2024-12-17 | 2024-12-03 | 2024-12-28 | Senahul | 65.7565 | 2.5291 | TA325 | 251/0 | Completed
2024-12-17 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.2679 | 4.7334 | TA325 | 132/0 | Completed
2024-12-17 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 164/6 | Completed
2024-12-17 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.6321 | 3.5539 | TA325 | 272/0 | Completed
2024-12-18 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.7305 | 2.695 | TA325 | 270/1 | Completed
2024-12-18 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.6077 | 6.4475 | TA325 | 134/0 | Completed
2024-12-18 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.7305 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-18 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-18 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.6077 | 6.4475 | TA325 | 115/0 | Completed
2024-12-18 | 2024-12-11 | 2024-12-21 | Jwala | 94.4077 | 8.5825 | TA325 | 193/0 | Completed
2024-12-18 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-18 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.7305 | 2.5154 | TA325 | 191/1 | Completed
2024-12-18 | 2024-12-03 | 2024-12-22 | Modina India | 44.7282 | 2.2364 | TA325 | 147/5 | Completed
2024-12-18 | 2024-12-10 | 2024-12-25 | Modina India | 39.4589 | 2.4662 | TA325 | 147/4 | Completed
2024-12-18 | 2024-12-17 | 2024-12-23 | Mukesh | 64.2538 | 9.1791 | TA325 | 147/2 | Completed
2024-12-18 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.7305 | 1.7967 | TA325 | 163/3 | Completed
2024-12-18 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-18 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-18 | 2024-11-27 | 2024-12-21 | Senahul | 84.2993 | 3.372 | TA325 | 255/0 | Completed
2024-12-18 | 2024-12-03 | 2024-12-28 | Senahul | 65.7565 | 2.5291 | TA325 | 251/0 | Completed
2024-12-18 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.2679 | 4.7334 | TA325 | 132/0 | Completed
2024-12-18 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 164/6 | Completed
2024-12-18 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.6321 | 3.5539 | TA325 | 272/0 | Completed
2024-12-19 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.0448 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-19 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.7305 | 2.695 | TA325 | 270/1 | Completed
2024-12-19 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.6077 | 6.4475 | TA325 | 134/0 | Completed
2024-12-19 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.7305 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-19 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-19 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.6077 | 6.4475 | TA325 | 115/0 | Completed
2024-12-19 | 2024-12-11 | 2024-12-21 | Jwala | 94.4077 | 8.5825 | TA325 | 193/0 | Completed
2024-12-19 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-19 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.7305 | 2.5154 | TA325 | 191/1 | Completed
2024-12-19 | 2024-12-03 | 2024-12-22 | Modina India | 44.7282 | 2.2364 | TA325 | 147/5 | Completed
2024-12-19 | 2024-12-10 | 2024-12-25 | Modina India | 39.4589 | 2.4662 | TA325 | 147/4 | Completed
2024-12-19 | 2024-12-17 | 2024-12-23 | Mukesh | 64.2538 | 9.1791 | TA325 | 147/2 | Completed
2024-12-19 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-19 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-19 | 2024-11-27 | 2024-12-21 | Senahul | 84.2993 | 3.372 | TA325 | 255/0 | Completed
2024-12-19 | 2024-12-03 | 2024-12-28 | Senahul | 65.7565 | 2.5291 | TA325 | 251/0 | Completed
2024-12-19 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.2679 | 4.7334 | TA325 | 132/0 | Completed
2024-12-19 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 164/6 | Completed
2024-12-19 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.6321 | 3.5539 | TA325 | 272/0 | Completed
2024-12-20 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.0448 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-20 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.7305 | 2.695 | TA325 | 270/1 | Completed
2024-12-20 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.6077 | 6.4475 | TA325 | 134/0 | Completed
2024-12-20 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.7305 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-20 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-20 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.6077 | 6.4475 | TA325 | 115/0 | Completed
2024-12-20 | 2024-12-11 | 2024-12-21 | Jwala | 94.4077 | 8.5825 | TA325 | 193/0 | Completed
2024-12-20 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-20 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.7305 | 2.5154 | TA325 | 191/1 | Completed
2024-12-20 | 2024-12-03 | 2024-12-22 | Modina India | 44.7282 | 2.2364 | TA325 | 147/5 | Completed
2024-12-20 | 2024-12-10 | 2024-12-25 | Modina India | 39.4589 | 2.4662 | TA325 | 147/4 | Completed
2024-12-20 | 2024-12-17 | 2024-12-23 | Mukesh | 64.2538 | 9.1791 | TA325 | 147/2 | Completed
2024-12-20 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-20 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-20 | 2024-11-27 | 2024-12-21 | Senahul | 84.2993 | 3.372 | TA325 | 255/0 | Completed
2024-12-20 | 2024-12-03 | 2024-12-28 | Senahul | 65.7565 | 2.5291 | TA325 | 251/0 | Completed
2024-12-20 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.2679 | 4.7334 | TA325 | 132/0 | Completed
2024-12-20 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 164/6 | Completed
2024-12-20 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.6321 | 3.5539 | TA325 | 272/0 | Completed
2024-12-21 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.0448 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-21 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.7305 | 2.695 | TA325 | 270/1 | Completed
2024-12-21 | 2024-12-21 | 2024-12-26 | Dhaneswar Mahto | 37.7305 | 6.2884 | TA325 | 135A/6 | Completed
2024-12-21 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.7305 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-21 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-21 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.7282 | 6.3897 | TA325 | 126/1 | Completed
2024-12-21 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-21 | 2024-12-11 | 2024-12-21 | Jwala | 94.4077 | 8.5825 | TA325 | 193/0 | Completed
2024-12-21 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-21 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.7305 | 2.5154 | TA325 | 191/1 | Completed
2024-12-21 | 2024-12-03 | 2024-12-22 | Modina India | 44.7282 | 2.2364 | TA325 | 147/5 | Completed
2024-12-21 | 2024-12-10 | 2024-12-25 | Modina India | 39.4589 | 2.4662 | TA325 | 147/4 | Completed
2024-12-21 | 2024-12-17 | 2024-12-23 | Mukesh | 64.2538 | 9.1791 | TA325 | 147/2 | Completed
2024-12-21 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-21 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-21 | 2024-11-27 | 2024-12-21 | Senahul | 84.2993 | 3.372 | TA325 | 255/0 | Completed
2024-12-21 | 2024-12-03 | 2024-12-28 | Senahul | 65.7565 | 2.5291 | TA325 | 251/0 | Completed
2024-12-21 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.2679 | 4.7334 | TA325 | 132/0 | Completed
2024-12-21 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 164/6 | Completed
2024-12-21 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.6321 | 3.5539 | TA325 | 272/0 | Completed
2024-12-22 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.0448 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-22 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.7305 | 2.695 | TA325 | 270/1 | Completed
2024-12-22 | 2024-12-21 | 2024-12-26 | Dhaneswar Mahto | 37.7305 | 6.2884 | TA325 | 135A/6 | Completed
2024-12-22 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.7282 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-22 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-22 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.7282 | 6.3897 | TA325 | 126/1 | Completed
2024-12-22 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-22 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-22 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.7305 | 2.5154 | TA325 | 191/1 | Completed
2024-12-22 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-22 | 2024-12-03 | 2024-12-22 | Modina India | 44.7282 | 2.2364 | TA325 | 147/5 | Completed
2024-12-22 | 2024-12-10 | 2024-12-25 | Modina India | 39.4589 | 2.4662 | TA325 | 147/4 | Completed
2024-12-22 | 2024-12-17 | 2024-12-23 | Mukesh | 64.2538 | 9.1791 | TA325 | 147/2 | Completed
2024-12-22 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-22 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-22 | 2024-12-03 | 2024-12-28 | Senahul | 65.7565 | 2.5291 | TA325 | 251/0 | Completed
2024-12-22 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.7305 | 4.1923 | TA325 | 132/1 | Completed
2024-12-22 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2024-12-22 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 164/6 | Completed
2024-12-22 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.6321 | 3.5539 | TA325 | 272/0 | Completed
2024-12-23 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.0448 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-23 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.7305 | 2.695 | TA325 | 270/1 | Completed
2024-12-23 | 2024-12-21 | 2024-12-26 | Dhaneswar Mahto | 37.7305 | 6.2884 | TA325 | 135A/6 | Completed
2024-12-23 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.7282 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-23 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-23 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.7282 | 6.3897 | TA325 | 126/1 | Completed
2024-12-23 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-23 | 2024-12-23 | 2024-12-29 | Jwala | 37.7305 | 5.3901 | TA325 | 197/4 | Completed
2024-12-23 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-23 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.7305 | 2.5154 | TA325 | 191/1 | Completed
2024-12-23 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-23 | 2024-12-10 | 2024-12-25 | Modina India | 39.4589 | 2.4662 | TA325 | 147/4 | Completed
2024-12-23 | 2024-12-23 | 2025-01-06 | Modina India | 37.7305 | 2.5154 | TA325 | 148/4 | Completed
2024-12-23 | 2024-12-17 | 2024-12-23 | Mukesh | 64.2538 | 9.1791 | TA325 | 147/2 | Completed
2024-12-23 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-23 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-23 | 2024-12-03 | 2024-12-28 | Senahul | 65.7565 | 2.5291 | TA325 | 251/0 | Completed
2024-12-23 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.7305 | 4.1923 | TA325 | 132/1 | Completed
2024-12-23 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2024-12-23 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 164/6 | Completed
2024-12-23 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.6321 | 3.5539 | TA325 | 272/0 | Completed
2024-12-24 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.0448 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-24 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.7305 | 2.695 | TA325 | 270/1 | Completed
2024-12-24 | 2024-12-21 | 2024-12-26 | Dhaneswar Mahto | 37.7305 | 6.2884 | TA325 | 135A/6 | Completed
2024-12-24 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.7282 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-24 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-24 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.7282 | 6.3897 | TA325 | 126/1 | Completed
2024-12-24 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-24 | 2024-12-23 | 2024-12-29 | Jwala | 37.7305 | 5.3901 | TA325 | 197/4 | Completed
2024-12-24 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-24 | 2024-12-10 | 2024-12-25 | Modina India | 39.4589 | 2.4662 | TA325 | 147/4 | Completed
2024-12-24 | 2024-12-23 | 2025-01-06 | Modina India | 37.7305 | 2.5154 | TA325 | 148/4 | Completed
2024-12-24 | 2024-12-24 | 2025-01-03 | Mukesh | 82.2388 | 7.4763 | TA325 | 147A/0 | Completed
2024-12-24 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-24 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-24 | 2024-12-03 | 2024-12-28 | Senahul | 65.7565 | 2.5291 | TA325 | 251/0 | Completed
2024-12-24 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.7305 | 4.1923 | TA325 | 132/1 | Completed
2024-12-24 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2024-12-24 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 164/6 | Completed
2024-12-24 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.6321 | 3.5539 | TA325 | 272/0 | Completed
2024-12-25 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.0448 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-25 | 2024-12-21 | 2024-12-26 | Dhaneswar Mahto | 37.7305 | 6.2884 | TA325 | 135A/6 | Completed
2024-12-25 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.7282 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-25 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-25 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.7282 | 6.3897 | TA325 | 126/1 | Completed
2024-12-25 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-25 | 2024-12-23 | 2024-12-29 | Jwala | 37.7305 | 5.3901 | TA325 | 197/4 | Completed
2024-12-25 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-25 | 2024-12-10 | 2024-12-25 | Modina India | 39.4589 | 2.4662 | TA325 | 147/4 | Completed
2024-12-25 | 2024-12-23 | 2025-01-06 | Modina India | 37.7305 | 2.5154 | TA325 | 148/4 | Completed
2024-12-25 | 2024-12-24 | 2025-01-03 | Mukesh | 82.2388 | 7.4763 | TA325 | 147A/0 | Completed
2024-12-25 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-25 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-25 | 2024-12-03 | 2024-12-28 | Senahul | 65.7565 | 2.5291 | TA325 | 251/0 | Completed
2024-12-25 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.7305 | 4.1923 | TA325 | 132/1 | Completed
2024-12-25 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2024-12-25 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 164/6 | Completed
2024-12-25 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.6321 | 3.5539 | TA325 | 272/0 | Completed
2024-12-26 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.0448 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-26 | 2024-12-21 | 2024-12-26 | Dhaneswar Mahto | 37.7305 | 6.2884 | TA325 | 135A/6 | Completed
2024-12-26 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.7282 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-26 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-26 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.7282 | 6.3897 | TA325 | 126/1 | Completed
2024-12-26 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-26 | 2024-12-23 | 2024-12-29 | Jwala | 37.7305 | 5.3901 | TA325 | 197/4 | Completed
2024-12-26 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.4589 | 4.9324 | TA325 | 255/3 | Completed
2024-12-26 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.0448 | 3.6045 | TA325 | 187/2 | Completed
2024-12-26 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-26 | 2024-12-23 | 2025-01-06 | Modina India | 37.7305 | 2.5154 | TA325 | 148/4 | Completed
2024-12-26 | 2024-12-24 | 2025-01-03 | Mukesh | 82.2388 | 7.4763 | TA325 | 147A/0 | Completed
2024-12-26 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-26 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-26 | 2024-12-03 | 2024-12-28 | Senahul | 65.7565 | 2.5291 | TA325 | 251/0 | Completed
2024-12-26 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.7305 | 4.1923 | TA325 | 132/1 | Completed
2024-12-26 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2024-12-26 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.6321 | 3.5539 | TA325 | 272/0 | Completed
2024-12-27 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.0448 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-27 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.2538 | 7.1393 | TA325 | 135A/0 | Completed
2024-12-27 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.7282 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-27 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-27 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.7282 | 6.3897 | TA325 | 126/1 | Completed
2024-12-27 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-27 | 2024-12-23 | 2024-12-29 | Jwala | 37.7305 | 5.3901 | TA325 | 197/4 | Completed
2024-12-27 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.4589 | 4.9324 | TA325 | 255/3 | Completed
2024-12-27 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.0448 | 3.6045 | TA325 | 187/2 | Completed
2024-12-27 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-27 | 2024-12-23 | 2025-01-06 | Modina India | 37.7305 | 2.5154 | TA325 | 148/4 | Completed
2024-12-27 | 2024-12-24 | 2025-01-03 | Mukesh | 82.2388 | 7.4763 | TA325 | 147A/0 | Completed
2024-12-27 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-27 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-27 | 2024-12-03 | 2024-12-28 | Senahul | 65.7565 | 2.5291 | TA325 | 251/0 | Completed
2024-12-27 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.7305 | 4.1923 | TA325 | 132/1 | Completed
2024-12-27 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2024-12-27 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.6321 | 3.5539 | TA325 | 272/0 | Completed
2024-12-28 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.0448 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-28 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.7305 | 3.43 | TA325 | 269/1 | Completed
2024-12-28 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.2538 | 7.1393 | TA325 | 135A/0 | Completed
2024-12-28 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.7282 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-28 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-12-28 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-28 | 2024-12-23 | 2024-12-29 | Jwala | 37.7305 | 5.3901 | TA325 | 197/4 | Completed
2024-12-28 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.4589 | 4.9324 | TA325 | 255/3 | Completed
2024-12-28 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.0448 | 3.6045 | TA325 | 187/2 | Completed
2024-12-28 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-28 | 2024-12-23 | 2025-01-06 | Modina India | 37.7305 | 2.5154 | TA325 | 148/4 | Completed
2024-12-28 | 2024-12-28 | 2025-01-16 | Modina India | 37.7305 | 1.8865 | TA325 | 164/1 | Completed
2024-12-28 | 2024-12-24 | 2025-01-03 | Mukesh | 82.2388 | 7.4763 | TA325 | 147A/0 | Completed
2024-12-28 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-28 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-28 | 2024-12-03 | 2024-12-28 | Senahul | 65.7565 | 2.5291 | TA325 | 251/0 | Completed
2024-12-28 | 2024-12-28 | 2025-01-12 | Senahul | 54.4178 | 3.4011 | TA325 | 266/0 | Completed
2024-12-28 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.7305 | 4.1923 | TA325 | 132/1 | Completed
2024-12-28 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2024-12-28 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.4178 | 3.4011 | TA325 | 164/0 | Completed
2024-12-28 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.6321 | 3.5539 | TA325 | 272/0 | Completed
2024-12-29 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.7305 | 3.43 | TA325 | 269/1 | Completed
2024-12-29 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.2538 | 7.1393 | TA325 | 135A/0 | Completed
2024-12-29 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.2538 | 10.709 | TA325 | 106A/0 | Completed
2024-12-29 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-29 | 2024-12-23 | 2024-12-29 | Jwala | 37.7305 | 5.3901 | TA325 | 197/4 | Completed
2024-12-29 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.4589 | 4.9324 | TA325 | 255/3 | Completed
2024-12-29 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.0448 | 3.6045 | TA325 | 187/2 | Completed
2024-12-29 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-29 | 2024-12-23 | 2025-01-06 | Modina India | 37.7305 | 2.5154 | TA325 | 148/4 | Completed
2024-12-29 | 2024-12-28 | 2025-01-16 | Modina India | 37.7305 | 1.8865 | TA325 | 164/1 | Completed
2024-12-29 | 2024-12-24 | 2025-01-03 | Mukesh | 82.2388 | 7.4763 | TA325 | 147A/0 | Completed
2024-12-29 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-29 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-29 | 2024-12-28 | 2025-01-12 | Senahul | 54.4178 | 3.4011 | TA325 | 266/0 | Completed
2024-12-29 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.7305 | 4.1923 | TA325 | 132/1 | Completed
2024-12-29 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2024-12-29 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.4178 | 3.4011 | TA325 | 164/0 | Completed
2024-12-29 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.6321 | 3.5539 | TA325 | 272/0 | Completed
2024-12-30 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.4077 | 4.7204 | TA325 | 129/0 | Completed
2024-12-30 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.7305 | 3.43 | TA325 | 269/1 | Completed
2024-12-30 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.2538 | 7.1393 | TA325 | 135A/0 | Completed
2024-12-30 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.2538 | 10.709 | TA325 | 106A/0 | Completed
2024-12-30 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-30 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.4589 | 4.9324 | TA325 | 255/3 | Completed
2024-12-30 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.0448 | 3.6045 | TA325 | 187/2 | Completed
2024-12-30 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-30 | 2024-12-23 | 2025-01-06 | Modina India | 37.7305 | 2.5154 | TA325 | 148/4 | Completed
2024-12-30 | 2024-12-28 | 2025-01-16 | Modina India | 37.7305 | 1.8865 | TA325 | 164/1 | Completed
2024-12-30 | 2024-12-24 | 2025-01-03 | Mukesh | 82.2388 | 7.4763 | TA325 | 147A/0 | Completed
2024-12-30 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.7305 | 3.773 | TA325 | 163/1 | Completed
2024-12-30 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-30 | 2024-12-28 | 2025-01-12 | Senahul | 54.4178 | 3.4011 | TA325 | 266/0 | Completed
2024-12-30 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.7305 | 4.1923 | TA325 | 132/1 | Completed
2024-12-30 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2024-12-30 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.4178 | 3.4011 | TA325 | 164/0 | Completed
2024-12-30 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.6321 | 3.5539 | TA325 | 272/0 | Completed
2024-12-31 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.4077 | 4.7204 | TA325 | 129/0 | Completed
2024-12-31 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.7305 | 3.43 | TA325 | 269/1 | Completed
2024-12-31 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.2538 | 7.1393 | TA325 | 135A/0 | Completed
2024-12-31 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.2538 | 10.709 | TA325 | 106A/0 | Completed
2024-12-31 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.2538 | 4.5896 | TA325 | 263/0 | Completed
2024-12-31 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-31 | 2024-12-31 | 2025-01-10 | Jwala | 98.8356 | 8.9851 | TA325 | 196/0 | Completed
2024-12-31 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.4589 | 4.9324 | TA325 | 255/3 | Completed
2024-12-31 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.0448 | 3.6045 | TA325 | 187/2 | Completed
2024-12-31 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-31 | 2024-12-23 | 2025-01-06 | Modina India | 37.7305 | 2.5154 | TA325 | 148/4 | Completed
2024-12-31 | 2024-12-28 | 2025-01-16 | Modina India | 37.7305 | 1.8865 | TA325 | 164/1 | Completed
2024-12-31 | 2024-12-24 | 2025-01-03 | Mukesh | 82.2388 | 7.4763 | TA325 | 147A/0 | Completed
2024-12-31 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.7305 | 3.773 | TA325 | 163/1 | Completed
2024-12-31 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.4589 | 3.5872 | TA325 | 158B/2 | Completed
2024-12-31 | 2024-12-28 | 2025-01-12 | Senahul | 54.4178 | 3.4011 | TA325 | 266/0 | Completed
2024-12-31 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2024-12-31 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.4178 | 3.4011 | TA325 | 164/0 | Completed
2024-12-31 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.6321 | 3.5539 | TA325 | 272/0 | Completed
2025-01-01 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.4077 | 4.7204 | TA325 | 129/0 | Completed
2025-01-01 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.7305 | 3.43 | TA325 | 269/1 | Completed
2025-01-01 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.2538 | 7.1393 | TA325 | 135A/0 | Completed
2025-01-01 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.2538 | 10.709 | TA325 | 106A/0 | Completed
2025-01-01 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.2538 | 4.5896 | TA325 | 263/0 | Completed
2025-01-01 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2025-01-01 | 2024-12-31 | 2025-01-10 | Jwala | 98.8356 | 8.9851 | TA325 | 196/0 | Completed
2025-01-01 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.4589 | 4.9324 | TA325 | 255/3 | Completed
2025-01-01 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.0448 | 3.6045 | TA325 | 187/2 | Completed
2025-01-01 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2025-01-01 | 2024-12-23 | 2025-01-06 | Modina India | 37.7305 | 2.5154 | TA325 | 148/4 | Completed
2025-01-01 | 2024-12-28 | 2025-01-16 | Modina India | 37.7305 | 1.8865 | TA325 | 164/1 | Completed
2025-01-01 | 2024-12-24 | 2025-01-03 | Mukesh | 82.2388 | 7.4763 | TA325 | 147A/0 | Completed
2025-01-01 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.7305 | 3.773 | TA325 | 163/1 | Completed
2025-01-01 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.4589 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-01 | 2024-12-28 | 2025-01-12 | Senahul | 54.4178 | 3.4011 | TA325 | 266/0 | Completed
2025-01-01 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2025-01-01 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.4178 | 3.4011 | TA325 | 164/0 | Completed
2025-01-01 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.0448 | 3.2768 | TA325 | 271/5 | Completed
2025-01-02 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.4077 | 4.7204 | TA325 | 129/0 | Completed
2025-01-02 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.7305 | 3.43 | TA325 | 269/1 | Completed
2025-01-02 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.2538 | 7.1393 | TA325 | 135A/0 | Completed
2025-01-02 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.2538 | 10.709 | TA325 | 106A/0 | Completed
2025-01-02 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.2538 | 4.5896 | TA325 | 263/0 | Completed
2025-01-02 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2025-01-02 | 2024-12-31 | 2025-01-10 | Jwala | 98.8356 | 8.9851 | TA325 | 196/0 | Completed
2025-01-02 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.4589 | 4.9324 | TA325 | 255/3 | Completed
2025-01-02 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.0448 | 3.6045 | TA325 | 187/2 | Completed
2025-01-02 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2025-01-02 | 2024-12-23 | 2025-01-06 | Modina India | 37.7305 | 2.5154 | TA325 | 148/4 | Completed
2025-01-02 | 2024-12-28 | 2025-01-16 | Modina India | 37.7305 | 1.8865 | TA325 | 164/1 | Completed
2025-01-02 | 2024-12-24 | 2025-01-03 | Mukesh | 82.2388 | 7.4763 | TA325 | 147A/0 | Completed
2025-01-02 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.7305 | 3.773 | TA325 | 163/1 | Completed
2025-01-02 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.4589 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-02 | 2024-12-28 | 2025-01-12 | Senahul | 54.4178 | 3.4011 | TA325 | 266/0 | Completed
2025-01-02 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2025-01-02 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.4178 | 3.4011 | TA325 | 164/0 | Completed
2025-01-02 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.0448 | 3.2768 | TA325 | 271/5 | Completed
2025-01-03 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.4077 | 4.7204 | TA325 | 129/0 | Completed
2025-01-03 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.7305 | 3.43 | TA325 | 269/1 | Completed
2025-01-03 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.2538 | 7.1393 | TA325 | 135A/0 | Completed
2025-01-03 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.2538 | 10.709 | TA325 | 106A/0 | Completed
2025-01-03 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.2538 | 4.5896 | TA325 | 263/0 | Completed
2025-01-03 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2025-01-03 | 2024-12-31 | 2025-01-10 | Jwala | 98.8356 | 8.9851 | TA325 | 196/0 | Completed
2025-01-03 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.7305 | 4.7163 | TA325 | 255/2 | Completed
2025-01-03 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.0448 | 3.6045 | TA325 | 187/2 | Completed
2025-01-03 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2025-01-03 | 2024-12-23 | 2025-01-06 | Modina India | 37.7305 | 2.5154 | TA325 | 148/4 | Completed
2025-01-03 | 2024-12-28 | 2025-01-16 | Modina India | 37.7305 | 1.8865 | TA325 | 164/1 | Completed
2025-01-03 | 2024-12-24 | 2025-01-03 | Mukesh | 82.2388 | 7.4763 | TA325 | 147A/0 | Completed
2025-01-03 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.7305 | 3.773 | TA325 | 163/1 | Completed
2025-01-03 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.4589 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-03 | 2024-12-28 | 2025-01-12 | Senahul | 54.4178 | 3.4011 | TA325 | 266/0 | Completed
2025-01-03 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2025-01-03 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.4178 | 3.4011 | TA325 | 164/0 | Completed
2025-01-03 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.0448 | 3.2768 | TA325 | 271/5 | Completed
2025-01-04 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.4077 | 4.7204 | TA325 | 129/0 | Completed
2025-01-04 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.7305 | 3.43 | TA325 | 269/1 | Completed
2025-01-04 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.2538 | 7.1393 | TA325 | 135A/0 | Completed
2025-01-04 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.2538 | 4.5896 | TA325 | 263/0 | Completed
2025-01-04 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2025-01-04 | 2024-12-31 | 2025-01-10 | Jwala | 98.8356 | 8.9851 | TA325 | 196/0 | Completed
2025-01-04 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.7305 | 4.7163 | TA325 | 255/2 | Completed
2025-01-04 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.0448 | 3.6045 | TA325 | 187/2 | Completed
2025-01-04 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2025-01-04 | 2024-12-23 | 2025-01-06 | Modina India | 37.7305 | 2.5154 | TA325 | 148/4 | Completed
2025-01-04 | 2024-12-28 | 2025-01-16 | Modina India | 37.7305 | 1.8865 | TA325 | 164/1 | Completed
2025-01-04 | 2025-01-04 | 2025-01-10 | Mukesh | 64.2538 | 9.1791 | TA325 | 148/0 | Completed
2025-01-04 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.7305 | 3.773 | TA325 | 163/1 | Completed
2025-01-04 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.4589 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-04 | 2024-12-28 | 2025-01-12 | Senahul | 54.4178 | 3.4011 | TA325 | 266/0 | Completed
2025-01-04 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2025-01-04 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.4178 | 3.4011 | TA325 | 164/0 | Completed
2025-01-04 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.0448 | 3.2768 | TA325 | 271/5 | Completed
2025-01-05 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.4077 | 4.7204 | TA325 | 129/0 | Completed
2025-01-05 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.7305 | 3.43 | TA325 | 269/1 | Completed
2025-01-05 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.2538 | 4.5896 | TA325 | 263/0 | Completed
2025-01-05 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2025-01-05 | 2024-12-31 | 2025-01-10 | Jwala | 98.8356 | 8.9851 | TA325 | 196/0 | Completed
2025-01-05 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.7305 | 4.7163 | TA325 | 255/2 | Completed
2025-01-05 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2025-01-05 | 2024-12-23 | 2025-01-06 | Modina India | 37.7305 | 2.5154 | TA325 | 148/4 | Completed
2025-01-05 | 2024-12-28 | 2025-01-16 | Modina India | 37.7305 | 1.8865 | TA325 | 164/1 | Completed
2025-01-05 | 2025-01-04 | 2025-01-10 | Mukesh | 64.2538 | 9.1791 | TA325 | 148/0 | Completed
2025-01-05 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.7305 | 3.773 | TA325 | 163/1 | Completed
2025-01-05 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.4589 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-05 | 2024-12-28 | 2025-01-12 | Senahul | 54.4178 | 3.4011 | TA325 | 266/0 | Completed
2025-01-05 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2025-01-05 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.4178 | 3.4011 | TA325 | 164/0 | Completed
2025-01-05 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.0448 | 3.2768 | TA325 | 271/5 | Completed
2025-01-06 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.4077 | 4.7204 | TA325 | 129/0 | Completed
2025-01-06 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.7305 | 3.43 | TA325 | 269/1 | Completed
2025-01-06 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.2538 | 4.5896 | TA325 | 263/0 | Completed
2025-01-06 | 2024-12-31 | 2025-01-10 | Jwala | 98.8356 | 8.9851 | TA325 | 196/0 | Completed
2025-01-06 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.7305 | 4.7163 | TA325 | 255/2 | Completed
2025-01-06 | 2024-12-23 | 2025-01-06 | Modina India | 37.7305 | 2.5154 | TA325 | 148/4 | Completed
2025-01-06 | 2024-12-28 | 2025-01-16 | Modina India | 37.7305 | 1.8865 | TA325 | 164/1 | Completed
2025-01-06 | 2025-01-04 | 2025-01-10 | Mukesh | 64.2538 | 9.1791 | TA325 | 148/0 | Completed
2025-01-06 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.7305 | 3.773 | TA325 | 163/1 | Completed
2025-01-06 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.4589 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-06 | 2024-12-28 | 2025-01-12 | Senahul | 54.4178 | 3.4011 | TA325 | 266/0 | Completed
2025-01-06 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2025-01-06 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.4178 | 3.4011 | TA325 | 164/0 | Completed
2025-01-06 | 2025-01-06 | 2025-01-11 | Surender Mahto | 44.7282 | 7.4547 | TA325 | 135/1 | Completed
2025-01-06 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.0448 | 3.2768 | TA325 | 271/5 | Completed
2025-01-07 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.4077 | 4.7204 | TA325 | 129/0 | Completed
2025-01-07 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.7305 | 3.43 | TA325 | 269/1 | Completed
2025-01-07 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.2538 | 4.5896 | TA325 | 263/0 | Completed
2025-01-07 | 2024-12-31 | 2025-01-10 | Jwala | 98.8356 | 8.9851 | TA325 | 196/0 | Completed
2025-01-07 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.7305 | 4.7163 | TA325 | 255/2 | Completed
2025-01-07 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.7305 | 3.773 | TA325 | 197/3 | Completed
2025-01-07 | 2024-12-28 | 2025-01-16 | Modina India | 37.7305 | 1.8865 | TA325 | 164/1 | Completed
2025-01-07 | 2025-01-04 | 2025-01-10 | Mukesh | 64.2538 | 9.1791 | TA325 | 148/0 | Completed
2025-01-07 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.7305 | 3.773 | TA325 | 163/1 | Completed
2025-01-07 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.4589 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-07 | 2024-12-28 | 2025-01-12 | Senahul | 54.4178 | 3.4011 | TA325 | 266/0 | Completed
2025-01-07 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2025-01-07 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.4178 | 3.4011 | TA325 | 164/0 | Completed
2025-01-07 | 2025-01-06 | 2025-01-11 | Surender Mahto | 44.7282 | 7.4547 | TA325 | 135/1 | Completed
2025-01-07 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.0448 | 3.2768 | TA325 | 271/5 | Completed
2025-01-08 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.4077 | 4.7204 | TA325 | 129/0 | Completed
2025-01-08 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.2538 | 4.5896 | TA325 | 263/0 | Completed
2025-01-08 | 2024-12-31 | 2025-01-10 | Jwala | 98.8356 | 8.9851 | TA325 | 196/0 | Completed
2025-01-08 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.7305 | 4.7163 | TA325 | 255/2 | Completed
2025-01-08 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.7305 | 3.773 | TA325 | 197/3 | Completed
2025-01-08 | 2024-12-28 | 2025-01-16 | Modina India | 37.7305 | 1.8865 | TA325 | 164/1 | Completed
2025-01-08 | 2025-01-04 | 2025-01-10 | Mukesh | 64.2538 | 9.1791 | TA325 | 148/0 | Completed
2025-01-08 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.7305 | 3.773 | TA325 | 163/1 | Completed
2025-01-08 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.4589 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-08 | 2024-12-28 | 2025-01-12 | Senahul | 54.4178 | 3.4011 | TA325 | 266/0 | Completed
2025-01-08 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2025-01-08 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.4178 | 3.4011 | TA325 | 164/0 | Completed
2025-01-08 | 2025-01-06 | 2025-01-11 | Surender Mahto | 44.7282 | 7.4547 | TA325 | 135/1 | Completed
2025-01-08 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.0448 | 3.2768 | TA325 | 271/5 | Completed
2025-01-09 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.4077 | 4.7204 | TA325 | 129/0 | Completed
2025-01-09 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.7305 | 4.1923 | TA325 | 257/1 | Completed
2025-01-09 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.6077 | 7.8291 | TA325 | 135/0 | Completed
2025-01-09 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.2538 | 4.5896 | TA325 | 263/0 | Completed
2025-01-09 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.4236 | 6.6132 | TA325 | 136/0 | Completed
2025-01-09 | 2024-12-31 | 2025-01-10 | Jwala | 98.8356 | 8.9851 | TA325 | 196/0 | Completed
2025-01-09 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.7305 | 4.7163 | TA325 | 255/2 | Completed
2025-01-09 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.7305 | 3.773 | TA325 | 197/3 | Completed
2025-01-09 | 2025-01-09 | 2025-01-18 | Mjr | 37.7305 | 3.773 | TA325 | 130/3 | Completed
2025-01-09 | 2024-12-28 | 2025-01-16 | Modina India | 37.7305 | 1.8865 | TA325 | 164/1 | Completed
2025-01-09 | 2025-01-04 | 2025-01-10 | Mukesh | 64.2538 | 9.1791 | TA325 | 148/0 | Completed
2025-01-09 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.4589 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-09 | 2024-12-28 | 2025-01-12 | Senahul | 54.4178 | 3.4011 | TA325 | 266/0 | Completed
2025-01-09 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2025-01-09 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.4178 | 3.4011 | TA325 | 164/0 | Completed
2025-01-09 | 2025-01-06 | 2025-01-11 | Surender Mahto | 44.7282 | 7.4547 | TA325 | 135/1 | Completed
2025-01-09 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.0448 | 3.2768 | TA325 | 271/5 | Completed
2025-01-10 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.4077 | 4.7204 | TA325 | 129/0 | Completed
2025-01-10 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.7305 | 2.3582 | TA325 | 163/6 | Completed
2025-01-10 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.7305 | 4.1923 | TA325 | 257/1 | Completed
2025-01-10 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.6077 | 7.8291 | TA325 | 135/0 | Completed
2025-01-10 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.2538 | 4.5896 | TA325 | 263/0 | Completed
2025-01-10 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.4236 | 6.6132 | TA325 | 136/0 | Completed
2025-01-10 | 2024-12-31 | 2025-01-10 | Jwala | 98.8356 | 8.9851 | TA325 | 196/0 | Completed
2025-01-10 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.7305 | 4.7163 | TA325 | 255/2 | Completed
2025-01-10 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.7305 | 3.773 | TA325 | 197/3 | Completed
2025-01-10 | 2025-01-09 | 2025-01-18 | Mjr | 37.7305 | 3.773 | TA325 | 130/3 | Completed
2025-01-10 | 2024-12-28 | 2025-01-16 | Modina India | 37.7305 | 1.8865 | TA325 | 164/1 | Completed
2025-01-10 | 2025-01-10 | 2025-01-19 | Modina India | 37.7305 | 3.773 | TA325 | 148/3 | Completed
2025-01-10 | 2025-01-04 | 2025-01-10 | Mukesh | 64.2538 | 9.1791 | TA325 | 148/0 | Completed
2025-01-10 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.4589 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-10 | 2024-12-28 | 2025-01-12 | Senahul | 54.4178 | 3.4011 | TA325 | 266/0 | Completed
2025-01-10 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2025-01-10 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.4178 | 3.4011 | TA325 | 164/0 | Completed
2025-01-10 | 2025-01-06 | 2025-01-11 | Surender Mahto | 44.7282 | 7.4547 | TA325 | 135/1 | Completed
2025-01-10 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.0448 | 3.2768 | TA325 | 271/5 | Completed
2025-01-11 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.4077 | 4.7204 | TA325 | 129/0 | Completed
2025-01-11 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.7305 | 2.3582 | TA325 | 163/6 | Completed
2025-01-11 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.7305 | 4.1923 | TA325 | 257/1 | Completed
2025-01-11 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.6077 | 7.8291 | TA325 | 135/0 | Completed
2025-01-11 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.2538 | 4.5896 | TA325 | 263/0 | Completed
2025-01-11 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.4236 | 6.6132 | TA325 | 136/0 | Completed
2025-01-11 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.7282 | 4.9698 | TA325 | 269/2 | Completed
2025-01-11 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.7305 | 3.773 | TA325 | 197/3 | Completed
2025-01-11 | 2025-01-09 | 2025-01-18 | Mjr | 37.7305 | 3.773 | TA325 | 130/3 | Completed
2025-01-11 | 2024-12-28 | 2025-01-16 | Modina India | 37.7305 | 1.8865 | TA325 | 164/1 | Completed
2025-01-11 | 2025-01-10 | 2025-01-19 | Modina India | 37.7305 | 3.773 | TA325 | 148/3 | Completed
2025-01-11 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.7305 | 3.773 | TA325 | 164/3 | Completed
2025-01-11 | 2024-12-28 | 2025-01-12 | Senahul | 54.4178 | 3.4011 | TA325 | 266/0 | Completed
2025-01-11 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2025-01-11 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.4178 | 3.4011 | TA325 | 164/0 | Completed
2025-01-11 | 2025-01-06 | 2025-01-11 | Surender Mahto | 44.7282 | 7.4547 | TA325 | 135/1 | Completed
2025-01-11 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.0448 | 3.2768 | TA325 | 271/5 | Completed
2025-01-12 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.4077 | 4.7204 | TA325 | 129/0 | Completed
2025-01-12 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.7305 | 2.3582 | TA325 | 163/6 | Completed
2025-01-12 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-01-12 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.7305 | 4.1923 | TA325 | 257/1 | Completed
2025-01-12 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.6077 | 7.8291 | TA325 | 135/0 | Completed
2025-01-12 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.2538 | 4.5896 | TA325 | 263/0 | Completed
2025-01-12 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.4236 | 6.6132 | TA325 | 136/0 | Completed
2025-01-12 | 2025-01-12 | 2025-01-22 | Jwala | 98.8356 | 8.9851 | TA325 | 197/0 | Completed
2025-01-12 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.7282 | 4.9698 | TA325 | 269/2 | Completed
2025-01-12 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.7305 | 3.773 | TA325 | 197/3 | Completed
2025-01-12 | 2025-01-09 | 2025-01-18 | Mjr | 37.7305 | 3.773 | TA325 | 130/3 | Completed
2025-01-12 | 2024-12-28 | 2025-01-16 | Modina India | 37.7305 | 1.8865 | TA325 | 164/1 | Completed
2025-01-12 | 2025-01-10 | 2025-01-19 | Modina India | 37.7305 | 3.773 | TA325 | 148/3 | Completed
2025-01-12 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.7305 | 3.773 | TA325 | 164/3 | Completed
2025-01-12 | 2024-12-28 | 2025-01-12 | Senahul | 54.4178 | 3.4011 | TA325 | 266/0 | Completed
2025-01-12 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2025-01-12 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.4178 | 3.4011 | TA325 | 164/0 | Completed
2025-01-13 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.4077 | 4.7204 | TA325 | 129/0 | Completed
2025-01-13 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.7305 | 2.3582 | TA325 | 163/6 | Completed
2025-01-13 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-01-13 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.7305 | 4.1923 | TA325 | 257/1 | Completed
2025-01-13 | 2025-01-13 | 2025-01-18 | Dhaneswar Mahto | 37.7305 | 6.2884 | TA325 | 135A/5 | Completed
2025-01-13 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.6077 | 7.8291 | TA325 | 135/0 | Completed
2025-01-13 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.2538 | 4.5896 | TA325 | 263/0 | Completed
2025-01-13 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.4236 | 6.6132 | TA325 | 136/0 | Completed
2025-01-13 | 2025-01-12 | 2025-01-22 | Jwala | 98.8356 | 8.9851 | TA325 | 197/0 | Completed
2025-01-13 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.7282 | 4.9698 | TA325 | 269/2 | Completed
2025-01-13 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.7305 | 3.773 | TA325 | 197/3 | Completed
2025-01-13 | 2025-01-09 | 2025-01-18 | Mjr | 37.7305 | 3.773 | TA325 | 130/3 | Completed
2025-01-13 | 2024-12-28 | 2025-01-16 | Modina India | 37.7305 | 1.8865 | TA325 | 164/1 | Completed
2025-01-13 | 2025-01-10 | 2025-01-19 | Modina India | 37.7305 | 3.773 | TA325 | 148/3 | Completed
2025-01-13 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.7305 | 3.773 | TA325 | 164/3 | Completed
2025-01-13 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-13 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2025-01-13 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.4178 | 4.9471 | TA325 | 272/5 | Completed
2025-01-14 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.4077 | 4.7204 | TA325 | 129/0 | Completed
2025-01-14 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.7305 | 2.3582 | TA325 | 163/6 | Completed
2025-01-14 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-01-14 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.7305 | 4.1923 | TA325 | 257/1 | Completed
2025-01-14 | 2025-01-13 | 2025-01-18 | Dhaneswar Mahto | 37.7305 | 6.2884 | TA325 | 135A/5 | Completed
2025-01-14 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.6077 | 7.8291 | TA325 | 135/0 | Completed
2025-01-14 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.4236 | 6.6132 | TA325 | 136/0 | Completed
2025-01-14 | 2025-01-12 | 2025-01-22 | Jwala | 98.8356 | 8.9851 | TA325 | 197/0 | Completed
2025-01-14 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.7282 | 4.9698 | TA325 | 269/2 | Completed
2025-01-14 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.7305 | 3.773 | TA325 | 197/3 | Completed
2025-01-14 | 2025-01-09 | 2025-01-18 | Mjr | 37.7305 | 3.773 | TA325 | 130/3 | Completed
2025-01-14 | 2024-12-28 | 2025-01-16 | Modina India | 37.7305 | 1.8865 | TA325 | 164/1 | Completed
2025-01-14 | 2025-01-10 | 2025-01-19 | Modina India | 37.7305 | 3.773 | TA325 | 148/3 | Completed
2025-01-14 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.7305 | 3.773 | TA325 | 164/3 | Completed
2025-01-14 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-14 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2025-01-14 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.4178 | 4.9471 | TA325 | 272/5 | Completed
2025-01-15 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.4077 | 4.7204 | TA325 | 129/0 | Completed
2025-01-15 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.7305 | 2.3582 | TA325 | 163/6 | Completed
2025-01-15 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-01-15 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.7305 | 4.1923 | TA325 | 257/1 | Completed
2025-01-15 | 2025-01-13 | 2025-01-18 | Dhaneswar Mahto | 37.7305 | 6.2884 | TA325 | 135A/5 | Completed
2025-01-15 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.6077 | 7.8291 | TA325 | 135/0 | Completed
2025-01-15 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.4236 | 6.6132 | TA325 | 136/0 | Completed
2025-01-15 | 2025-01-12 | 2025-01-22 | Jwala | 98.8356 | 8.9851 | TA325 | 197/0 | Completed
2025-01-15 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.7282 | 4.9698 | TA325 | 269/2 | Completed
2025-01-15 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.7305 | 3.773 | TA325 | 197/3 | Completed
2025-01-15 | 2025-01-09 | 2025-01-18 | Mjr | 37.7305 | 3.773 | TA325 | 130/3 | Completed
2025-01-15 | 2024-12-28 | 2025-01-16 | Modina India | 37.7305 | 1.8865 | TA325 | 164/1 | Completed
2025-01-15 | 2025-01-10 | 2025-01-19 | Modina India | 37.7305 | 3.773 | TA325 | 148/3 | Completed
2025-01-15 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.7305 | 3.773 | TA325 | 164/3 | Completed
2025-01-15 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-15 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2025-01-15 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.4178 | 4.9471 | TA325 | 272/5 | Completed
2025-01-16 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.4077 | 4.7204 | TA325 | 129/0 | Completed
2025-01-16 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.7305 | 2.3582 | TA325 | 163/6 | Completed
2025-01-16 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-01-16 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.7305 | 4.1923 | TA325 | 257/1 | Completed
2025-01-16 | 2025-01-13 | 2025-01-18 | Dhaneswar Mahto | 37.7305 | 6.2884 | TA325 | 135A/5 | Completed
2025-01-16 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.6077 | 7.8291 | TA325 | 135/0 | Completed
2025-01-16 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.4236 | 6.6132 | TA325 | 136/0 | Completed
2025-01-16 | 2025-01-12 | 2025-01-22 | Jwala | 98.8356 | 8.9851 | TA325 | 197/0 | Completed
2025-01-16 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.7282 | 4.9698 | TA325 | 269/2 | Completed
2025-01-16 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.7305 | 3.773 | TA325 | 197/3 | Completed
2025-01-16 | 2025-01-09 | 2025-01-18 | Mjr | 37.7305 | 3.773 | TA325 | 130/3 | Completed
2025-01-16 | 2024-12-28 | 2025-01-16 | Modina India | 37.7305 | 1.8865 | TA325 | 164/1 | Completed
2025-01-16 | 2025-01-10 | 2025-01-19 | Modina India | 37.7305 | 3.773 | TA325 | 148/3 | Completed
2025-01-16 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.7305 | 3.773 | TA325 | 164/3 | Completed
2025-01-16 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.2538 | 8.0317 | TA325 | 163/0 | Completed
2025-01-16 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-16 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2025-01-16 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.7305 | 2.695 | TA325 | 163/4 | Completed
2025-01-16 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.4178 | 4.9471 | TA325 | 272/5 | Completed
2025-01-17 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.4077 | 4.7204 | TA325 | 129/0 | Completed
2025-01-17 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.7305 | 2.3582 | TA325 | 163/6 | Completed
2025-01-17 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-01-17 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.7305 | 4.1923 | TA325 | 257/1 | Completed
2025-01-17 | 2025-01-13 | 2025-01-18 | Dhaneswar Mahto | 37.7305 | 6.2884 | TA325 | 135A/5 | Completed
2025-01-17 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.6077 | 7.8291 | TA325 | 135/0 | Completed
2025-01-17 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.4236 | 6.6132 | TA325 | 136/0 | Completed
2025-01-17 | 2025-01-12 | 2025-01-22 | Jwala | 98.8356 | 8.9851 | TA325 | 197/0 | Completed
2025-01-17 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.7282 | 4.9698 | TA325 | 269/2 | Completed
2025-01-17 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.7305 | 3.43 | TA325 | 198/1 | Completed
2025-01-17 | 2025-01-09 | 2025-01-18 | Mjr | 37.7305 | 3.773 | TA325 | 130/3 | Completed
2025-01-17 | 2025-01-10 | 2025-01-19 | Modina India | 37.7305 | 3.773 | TA325 | 148/3 | Completed
2025-01-17 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.7305 | 3.773 | TA325 | 164/3 | Completed
2025-01-17 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.2538 | 8.0317 | TA325 | 163/0 | Completed
2025-01-17 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-17 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2025-01-17 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.7305 | 2.695 | TA325 | 163/4 | Completed
2025-01-17 | 2025-01-17 | 2025-02-06 | Tajirul | 39.4589 | 1.879 | TA325 | 272/3 | Completed
2025-01-17 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.4178 | 4.9471 | TA325 | 272/5 | Completed
2025-01-18 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.4077 | 4.7204 | TA325 | 129/0 | Completed
2025-01-18 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.7305 | 2.3582 | TA325 | 163/6 | Completed
2025-01-18 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-01-18 | 2025-01-13 | 2025-01-18 | Dhaneswar Mahto | 37.7305 | 6.2884 | TA325 | 135A/5 | Completed
2025-01-18 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.6077 | 7.8291 | TA325 | 135/0 | Completed
2025-01-18 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.1461 | 3.5658 | TA325 | 262/0 | Completed
2025-01-18 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.4236 | 6.6132 | TA325 | 136/0 | Completed
2025-01-18 | 2025-01-12 | 2025-01-22 | Jwala | 98.8356 | 8.9851 | TA325 | 197/0 | Completed
2025-01-18 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.7282 | 4.9698 | TA325 | 269/2 | Completed
2025-01-18 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.7305 | 3.43 | TA325 | 198/1 | Completed
2025-01-18 | 2025-01-09 | 2025-01-18 | Mjr | 37.7305 | 3.773 | TA325 | 130/3 | Completed
2025-01-18 | 2025-01-10 | 2025-01-19 | Modina India | 37.7305 | 3.773 | TA325 | 148/3 | Completed
2025-01-18 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.7305 | 3.773 | TA325 | 164/3 | Completed
2025-01-18 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.2538 | 8.0317 | TA325 | 163/0 | Completed
2025-01-18 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-18 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2025-01-18 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.7305 | 2.695 | TA325 | 163/4 | Completed
2025-01-18 | 2025-01-17 | 2025-02-06 | Tajirul | 39.4589 | 1.879 | TA325 | 272/3 | Completed
2025-01-18 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.4178 | 4.9471 | TA325 | 272/5 | Completed
2025-01-19 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.7305 | 2.3582 | TA325 | 163/6 | Completed
2025-01-19 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-01-19 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.7282 | 4.9698 | TA325 | 255/1 | Completed
2025-01-19 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.6077 | 7.8291 | TA325 | 135/0 | Completed
2025-01-19 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.1461 | 3.5658 | TA325 | 262/0 | Completed
2025-01-19 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.4236 | 6.6132 | TA325 | 136/0 | Completed
2025-01-19 | 2025-01-12 | 2025-01-22 | Jwala | 98.8356 | 8.9851 | TA325 | 197/0 | Completed
2025-01-19 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.7282 | 4.9698 | TA325 | 269/2 | Completed
2025-01-19 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.7305 | 3.43 | TA325 | 198/1 | Completed
2025-01-19 | 2025-01-10 | 2025-01-19 | Modina India | 37.7305 | 3.773 | TA325 | 148/3 | Completed
2025-01-19 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.7305 | 3.773 | TA325 | 164/3 | Completed
2025-01-19 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.2538 | 8.0317 | TA325 | 163/0 | Completed
2025-01-19 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-19 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2025-01-19 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.7305 | 2.695 | TA325 | 163/4 | Completed
2025-01-19 | 2025-01-17 | 2025-02-06 | Tajirul | 39.4589 | 1.879 | TA325 | 272/3 | Completed
2025-01-19 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.4178 | 4.9471 | TA325 | 272/5 | Completed
2025-01-20 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.7305 | 2.3582 | TA325 | 163/6 | Completed
2025-01-20 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-01-20 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.7282 | 4.9698 | TA325 | 255/1 | Completed
2025-01-20 | 2025-01-20 | 2025-01-24 | Dhaneswar Mahto | 46.6235 | 9.3247 | TA325 | 137A/6 | Completed
2025-01-20 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.6077 | 7.8291 | TA325 | 135/0 | Completed
2025-01-20 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.1461 | 3.5658 | TA325 | 262/0 | Completed
2025-01-20 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.4236 | 6.6132 | TA325 | 136/0 | Completed
2025-01-20 | 2025-01-12 | 2025-01-22 | Jwala | 98.8356 | 8.9851 | TA325 | 197/0 | Completed
2025-01-20 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.7305 | 3.43 | TA325 | 198/1 | Completed
2025-01-20 | 2025-01-20 | 2025-01-29 | Mjr | 39.4589 | 3.9459 | TA325 | 130/2 | Completed
2025-01-20 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.7305 | 3.773 | TA325 | 164/3 | Completed
2025-01-20 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.2538 | 8.0317 | TA325 | 163/0 | Completed
2025-01-20 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-20 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2025-01-20 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.7305 | 2.695 | TA325 | 163/4 | Completed
2025-01-20 | 2025-01-17 | 2025-02-06 | Tajirul | 39.4589 | 1.879 | TA325 | 272/3 | Completed
2025-01-20 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.4178 | 4.9471 | TA325 | 272/5 | Completed
2025-01-21 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.7305 | 2.3582 | TA325 | 163/6 | Completed
2025-01-21 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-01-21 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.4524 | 4.7158 | TA325 | 131/0 | Completed
2025-01-21 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.7282 | 4.9698 | TA325 | 255/1 | Completed
2025-01-21 | 2025-01-20 | 2025-01-24 | Dhaneswar Mahto | 46.6235 | 9.3247 | TA325 | 137A/6 | Completed
2025-01-21 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.6077 | 7.8291 | TA325 | 135/0 | Completed
2025-01-21 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.1461 | 3.5658 | TA325 | 262/0 | Completed
2025-01-21 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.4236 | 6.6132 | TA325 | 136/0 | Completed
2025-01-21 | 2025-01-12 | 2025-01-22 | Jwala | 98.8356 | 8.9851 | TA325 | 197/0 | Completed
2025-01-21 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.7181 | 7.0653 | TA325 | 267/0 | Completed
2025-01-21 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.7305 | 3.43 | TA325 | 198/1 | Completed
2025-01-21 | 2025-01-20 | 2025-01-29 | Mjr | 39.4589 | 3.9459 | TA325 | 130/2 | Completed
2025-01-21 | 2025-01-21 | 2025-01-30 | Modina India | 37.7305 | 3.773 | TA325 | 148/2 | Completed
2025-01-21 | 2025-01-21 | 2025-02-03 | Modina India | 37.7305 | 2.695 | TA325 | 159/4 | Completed
2025-01-21 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.7305 | 1.6405 | TA325 | 159/1 | Completed
2025-01-21 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.2538 | 8.0317 | TA325 | 163/0 | Completed
2025-01-21 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-21 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2025-01-21 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.7305 | 2.695 | TA325 | 163/4 | Completed
2025-01-21 | 2025-01-17 | 2025-02-06 | Tajirul | 39.4589 | 1.879 | TA325 | 272/3 | Completed
2025-01-21 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.4178 | 4.9471 | TA325 | 272/5 | Completed
2025-01-22 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.7305 | 2.3582 | TA325 | 163/6 | Completed
2025-01-22 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-01-22 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.4524 | 4.7158 | TA325 | 131/0 | Completed
2025-01-22 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.7282 | 4.9698 | TA325 | 255/1 | Completed
2025-01-22 | 2025-01-20 | 2025-01-24 | Dhaneswar Mahto | 46.6235 | 9.3247 | TA325 | 137A/6 | Completed
2025-01-22 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.6077 | 7.8291 | TA325 | 135/0 | Completed
2025-01-22 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.1461 | 3.5658 | TA325 | 262/0 | Completed
2025-01-22 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.4236 | 6.6132 | TA325 | 136/0 | Completed
2025-01-22 | 2025-01-12 | 2025-01-22 | Jwala | 98.8356 | 8.9851 | TA325 | 197/0 | Completed
2025-01-22 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.7181 | 7.0653 | TA325 | 267/0 | Completed
2025-01-22 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.7305 | 3.43 | TA325 | 198/1 | Completed
2025-01-22 | 2025-01-20 | 2025-01-29 | Mjr | 39.4589 | 3.9459 | TA325 | 130/2 | Completed
2025-01-22 | 2025-01-21 | 2025-01-30 | Modina India | 37.7305 | 3.773 | TA325 | 148/2 | Completed
2025-01-22 | 2025-01-21 | 2025-02-03 | Modina India | 37.7305 | 2.695 | TA325 | 159/4 | Completed
2025-01-22 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.7305 | 1.6405 | TA325 | 159/1 | Completed
2025-01-22 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.2538 | 8.0317 | TA325 | 163/0 | Completed
2025-01-22 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-22 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.7305 | 2.695 | TA325 | 163/4 | Completed
2025-01-22 | 2025-01-17 | 2025-02-06 | Tajirul | 39.4589 | 1.879 | TA325 | 272/3 | Completed
2025-01-22 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.4178 | 4.9471 | TA325 | 272/5 | Completed
2025-01-23 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.7305 | 2.3582 | TA325 | 163/6 | Completed
2025-01-23 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-01-23 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.4524 | 4.7158 | TA325 | 131/0 | Completed
2025-01-23 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.7282 | 4.9698 | TA325 | 255/1 | Completed
2025-01-23 | 2025-01-20 | 2025-01-24 | Dhaneswar Mahto | 46.6235 | 9.3247 | TA325 | 137A/6 | Completed
2025-01-23 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.4178 | 7.774 | TA325 | 137A/0 | Completed
2025-01-23 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.1461 | 3.5658 | TA325 | 262/0 | Completed
2025-01-23 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.4236 | 6.6132 | TA325 | 136/0 | Completed
2025-01-23 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.7181 | 7.0653 | TA325 | 267/0 | Completed
2025-01-23 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.7305 | 3.43 | TA325 | 198/1 | Completed
2025-01-23 | 2025-01-20 | 2025-01-29 | Mjr | 39.4589 | 3.9459 | TA325 | 130/2 | Completed
2025-01-23 | 2025-01-21 | 2025-01-30 | Modina India | 37.7305 | 3.773 | TA325 | 148/2 | Completed
2025-01-23 | 2025-01-21 | 2025-02-03 | Modina India | 37.7305 | 2.695 | TA325 | 159/4 | Completed
2025-01-23 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.7305 | 1.6405 | TA325 | 159/1 | Completed
2025-01-23 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.2538 | 8.0317 | TA325 | 163/0 | Completed
2025-01-23 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-23 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.7305 | 2.695 | TA325 | 163/4 | Completed
2025-01-23 | 2025-01-17 | 2025-02-06 | Tajirul | 39.4589 | 1.879 | TA325 | 272/3 | Completed
2025-01-23 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.4178 | 4.9471 | TA325 | 272/5 | Completed
2025-01-24 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.7305 | 2.3582 | TA325 | 163/6 | Completed
2025-01-24 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-01-24 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.4524 | 4.7158 | TA325 | 131/0 | Completed
2025-01-24 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.7282 | 4.9698 | TA325 | 255/1 | Completed
2025-01-24 | 2025-01-20 | 2025-01-24 | Dhaneswar Mahto | 46.6235 | 9.3247 | TA325 | 137A/6 | Completed
2025-01-24 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.4178 | 7.774 | TA325 | 137A/0 | Completed
2025-01-24 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.1461 | 3.5658 | TA325 | 262/0 | Completed
2025-01-24 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.4236 | 6.6132 | TA325 | 136/0 | Completed
2025-01-24 | 2025-01-24 | 2025-01-29 | Jwala | 44.7282 | 7.4547 | TA325 | 272A/1 | Completed
2025-01-24 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.7181 | 7.0653 | TA325 | 267/0 | Completed
2025-01-24 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.7305 | 3.43 | TA325 | 198/1 | Completed
2025-01-24 | 2025-01-20 | 2025-01-29 | Mjr | 39.4589 | 3.9459 | TA325 | 130/2 | Completed
2025-01-24 | 2025-01-21 | 2025-01-30 | Modina India | 37.7305 | 3.773 | TA325 | 148/2 | Completed
2025-01-24 | 2025-01-21 | 2025-02-03 | Modina India | 37.7305 | 2.695 | TA325 | 159/4 | Completed
2025-01-24 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.7305 | 1.6405 | TA325 | 159/1 | Completed
2025-01-24 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-24 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.7305 | 2.695 | TA325 | 163/4 | Completed
2025-01-24 | 2025-01-17 | 2025-02-06 | Tajirul | 39.4589 | 1.879 | TA325 | 272/3 | Completed
2025-01-25 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.7305 | 2.3582 | TA325 | 163/6 | Completed
2025-01-25 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-01-25 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.4524 | 4.7158 | TA325 | 131/0 | Completed
2025-01-25 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.7282 | 4.9698 | TA325 | 255/1 | Completed
2025-01-25 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.4178 | 7.774 | TA325 | 137A/0 | Completed
2025-01-25 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.1461 | 3.5658 | TA325 | 262/0 | Completed
2025-01-25 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.4236 | 6.6132 | TA325 | 136/0 | Completed
2025-01-25 | 2025-01-24 | 2025-01-29 | Jwala | 44.7282 | 7.4547 | TA325 | 272A/1 | Completed
2025-01-25 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.7181 | 7.0653 | TA325 | 267/0 | Completed
2025-01-25 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.7305 | 3.43 | TA325 | 198/1 | Completed
2025-01-25 | 2025-01-20 | 2025-01-29 | Mjr | 39.4589 | 3.9459 | TA325 | 130/2 | Completed
2025-01-25 | 2025-01-21 | 2025-01-30 | Modina India | 37.7305 | 3.773 | TA325 | 148/2 | Completed
2025-01-25 | 2025-01-21 | 2025-02-03 | Modina India | 37.7305 | 2.695 | TA325 | 159/4 | Completed
2025-01-25 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.7305 | 1.6405 | TA325 | 159/1 | Completed
2025-01-25 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-25 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.7305 | 2.3582 | TA325 | 130/1 | Completed
2025-01-25 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.7305 | 2.695 | TA325 | 163/4 | Completed
2025-01-25 | 2025-01-17 | 2025-02-06 | Tajirul | 39.4589 | 1.879 | TA325 | 272/3 | Completed
2025-01-25 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.4589 | 4.3843 | TA325 | 272/4 | Completed
2025-01-26 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-01-26 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.4524 | 4.7158 | TA325 | 131/0 | Completed
2025-01-26 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.7282 | 4.9698 | TA325 | 255/1 | Completed
2025-01-26 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.4178 | 7.774 | TA325 | 137A/0 | Completed
2025-01-26 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.1461 | 3.5658 | TA325 | 262/0 | Completed
2025-01-26 | 2025-01-24 | 2025-01-29 | Jwala | 44.7282 | 7.4547 | TA325 | 272A/1 | Completed
2025-01-26 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.7181 | 7.0653 | TA325 | 267/0 | Completed
2025-01-26 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.7305 | 3.43 | TA325 | 198/1 | Completed
2025-01-26 | 2025-01-20 | 2025-01-29 | Mjr | 39.4589 | 3.9459 | TA325 | 130/2 | Completed
2025-01-26 | 2025-01-21 | 2025-01-30 | Modina India | 37.7305 | 3.773 | TA325 | 148/2 | Completed
2025-01-26 | 2025-01-21 | 2025-02-03 | Modina India | 37.7305 | 2.695 | TA325 | 159/4 | Completed
2025-01-26 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.7305 | 1.6405 | TA325 | 159/1 | Completed
2025-01-26 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-26 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.7305 | 2.3582 | TA325 | 130/1 | Completed
2025-01-26 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.7305 | 2.695 | TA325 | 163/4 | Completed
2025-01-26 | 2025-01-17 | 2025-02-06 | Tajirul | 39.4589 | 1.879 | TA325 | 272/3 | Completed
2025-01-26 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.4589 | 4.3843 | TA325 | 272/4 | Completed
2025-01-27 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.0448 | 1.5672 | TA325 | 147/6 | Completed
2025-01-27 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-01-27 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.4524 | 4.7158 | TA325 | 131/0 | Completed
2025-01-27 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.7282 | 4.9698 | TA325 | 255/1 | Completed
2025-01-27 | 2025-01-27 | 2025-01-29 | Dhaneswar Mahto | 44.7282 | 14.9094 | TA325 | 137A/1 | Completed
2025-01-27 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.4178 | 7.774 | TA325 | 137A/0 | Completed
2025-01-27 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.1461 | 3.5658 | TA325 | 262/0 | Completed
2025-01-27 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.4178 | 9.0696 | TA325 | 138/0 | Completed
2025-01-27 | 2025-01-24 | 2025-01-29 | Jwala | 44.7282 | 7.4547 | TA325 | 272A/1 | Completed
2025-01-27 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.7181 | 7.0653 | TA325 | 267/0 | Completed
2025-01-27 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.7305 | 3.43 | TA325 | 198/1 | Completed
2025-01-27 | 2025-01-20 | 2025-01-29 | Mjr | 39.4589 | 3.9459 | TA325 | 130/2 | Completed
2025-01-27 | 2025-01-21 | 2025-01-30 | Modina India | 37.7305 | 3.773 | TA325 | 148/2 | Completed
2025-01-27 | 2025-01-21 | 2025-02-03 | Modina India | 37.7305 | 2.695 | TA325 | 159/4 | Completed
2025-01-27 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.7305 | 1.6405 | TA325 | 159/1 | Completed
2025-01-27 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-27 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.7305 | 2.3582 | TA325 | 130/1 | Completed
2025-01-27 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.7305 | 3.1442 | TA325 | 137/6 | Completed
2025-01-27 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.7305 | 2.695 | TA325 | 163/4 | Completed
2025-01-27 | 2025-01-17 | 2025-02-06 | Tajirul | 39.4589 | 1.879 | TA325 | 272/3 | Completed
2025-01-27 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.4589 | 4.3843 | TA325 | 272/4 | Completed
2025-01-28 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.0448 | 1.5672 | TA325 | 147/6 | Completed
2025-01-28 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-01-28 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.4524 | 4.7158 | TA325 | 131/0 | Completed
2025-01-28 | 2025-01-27 | 2025-01-29 | Dhaneswar Mahto | 44.7282 | 14.9094 | TA325 | 137A/1 | Completed
2025-01-28 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.4178 | 7.774 | TA325 | 137A/0 | Completed
2025-01-28 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.1461 | 3.5658 | TA325 | 262/0 | Completed
2025-01-28 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.4178 | 9.0696 | TA325 | 138/0 | Completed
2025-01-28 | 2025-01-24 | 2025-01-29 | Jwala | 44.7282 | 7.4547 | TA325 | 272A/1 | Completed
2025-01-28 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.7181 | 7.0653 | TA325 | 267/0 | Completed
2025-01-28 | 2025-01-20 | 2025-01-29 | Mjr | 39.4589 | 3.9459 | TA325 | 130/2 | Completed
2025-01-28 | 2025-01-21 | 2025-01-30 | Modina India | 37.7305 | 3.773 | TA325 | 148/2 | Completed
2025-01-28 | 2025-01-21 | 2025-02-03 | Modina India | 37.7305 | 2.695 | TA325 | 159/4 | Completed
2025-01-28 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.7305 | 1.6405 | TA325 | 159/1 | Completed
2025-01-28 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-01-28 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-28 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.7305 | 2.3582 | TA325 | 130/1 | Completed
2025-01-28 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.7305 | 3.1442 | TA325 | 137/6 | Completed
2025-01-28 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.7305 | 2.695 | TA325 | 163/4 | Completed
2025-01-28 | 2025-01-17 | 2025-02-06 | Tajirul | 39.4589 | 1.879 | TA325 | 272/3 | Completed
2025-01-28 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.4589 | 4.3843 | TA325 | 272/4 | Completed
2025-01-29 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.0448 | 1.5672 | TA325 | 147/6 | Completed
2025-01-29 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-01-29 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.4524 | 4.7158 | TA325 | 131/0 | Completed
2025-01-29 | 2025-01-27 | 2025-01-29 | Dhaneswar Mahto | 44.7282 | 14.9094 | TA325 | 137A/1 | Completed
2025-01-29 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.4178 | 7.774 | TA325 | 137A/0 | Completed
2025-01-29 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.1461 | 3.5658 | TA325 | 262/0 | Completed
2025-01-29 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.4178 | 9.0696 | TA325 | 138/0 | Completed
2025-01-29 | 2025-01-24 | 2025-01-29 | Jwala | 44.7282 | 7.4547 | TA325 | 272A/1 | Completed
2025-01-29 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.7181 | 7.0653 | TA325 | 267/0 | Completed
2025-01-29 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.7305 | 3.773 | TA325 | 197/2 | Completed
2025-01-29 | 2025-01-20 | 2025-01-29 | Mjr | 39.4589 | 3.9459 | TA325 | 130/2 | Completed
2025-01-29 | 2025-01-21 | 2025-01-30 | Modina India | 37.7305 | 3.773 | TA325 | 148/2 | Completed
2025-01-29 | 2025-01-21 | 2025-02-03 | Modina India | 37.7305 | 2.695 | TA325 | 159/4 | Completed
2025-01-29 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.7305 | 1.6405 | TA325 | 159/1 | Completed
2025-01-29 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-01-29 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-29 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.7305 | 2.3582 | TA325 | 130/1 | Completed
2025-01-29 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.7305 | 3.1442 | TA325 | 137/6 | Completed
2025-01-29 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.7305 | 2.695 | TA325 | 163/4 | Completed
2025-01-29 | 2025-01-17 | 2025-02-06 | Tajirul | 39.4589 | 1.879 | TA325 | 272/3 | Completed
2025-01-29 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.4589 | 4.3843 | TA325 | 272/4 | Completed
2025-01-30 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.0448 | 1.5672 | TA325 | 147/6 | Completed
2025-01-30 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-01-30 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.4524 | 4.7158 | TA325 | 131/0 | Completed
2025-01-30 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.0448 | 6.0075 | TA325 | 272/2 | Completed
2025-01-30 | 2025-01-30 | 2025-02-02 | Dhaneswar Mahto | 37.7305 | 9.4326 | TA325 | 137A/2 | Completed
2025-01-30 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.4178 | 9.0696 | TA325 | 139/0 | Completed
2025-01-30 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.1461 | 3.5658 | TA325 | 262/0 | Completed
2025-01-30 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.4178 | 9.0696 | TA325 | 138/0 | Completed
2025-01-30 | 2025-01-30 | 2025-02-04 | Jwala | 37.7305 | 6.2884 | TA325 | 272A/2 | Completed
2025-01-30 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.7181 | 7.0653 | TA325 | 267/0 | Completed
2025-01-30 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.7305 | 3.773 | TA325 | 197/2 | Completed
2025-01-30 | 2025-01-21 | 2025-01-30 | Modina India | 37.7305 | 3.773 | TA325 | 148/2 | Completed
2025-01-30 | 2025-01-21 | 2025-02-03 | Modina India | 37.7305 | 2.695 | TA325 | 159/4 | Completed
2025-01-30 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.7305 | 1.6405 | TA325 | 159/1 | Completed
2025-01-30 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-01-30 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.7305 | 2.3582 | TA325 | 130/1 | Completed
2025-01-30 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.7305 | 3.1442 | TA325 | 137/6 | Completed
2025-01-30 | 2025-01-17 | 2025-02-06 | Tajirul | 39.4589 | 1.879 | TA325 | 272/3 | Completed
2025-01-30 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.4589 | 4.3843 | TA325 | 272/4 | Completed
2025-01-31 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.0448 | 1.5672 | TA325 | 147/6 | Completed
2025-01-31 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-01-31 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.4524 | 4.7158 | TA325 | 131/0 | Completed
2025-01-31 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.0448 | 6.0075 | TA325 | 272/2 | Completed
2025-01-31 | 2025-01-30 | 2025-02-02 | Dhaneswar Mahto | 37.7305 | 9.4326 | TA325 | 137A/2 | Completed
2025-01-31 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.4178 | 9.0696 | TA325 | 139/0 | Completed
2025-01-31 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.1461 | 3.5658 | TA325 | 262/0 | Completed
2025-01-31 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.4178 | 9.0696 | TA325 | 138/0 | Completed
2025-01-31 | 2025-01-30 | 2025-02-04 | Jwala | 37.7305 | 6.2884 | TA325 | 272A/2 | Completed
2025-01-31 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.7181 | 7.0653 | TA325 | 267/0 | Completed
2025-01-31 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.7305 | 3.773 | TA325 | 197/2 | Completed
2025-01-31 | 2025-01-21 | 2025-02-03 | Modina India | 37.7305 | 2.695 | TA325 | 159/4 | Completed
2025-01-31 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.7305 | 1.6405 | TA325 | 159/1 | Completed
2025-01-31 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-01-31 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.7305 | 2.3582 | TA325 | 130/1 | Completed
2025-01-31 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.7305 | 3.1442 | TA325 | 137/6 | Completed
2025-01-31 | 2025-01-17 | 2025-02-06 | Tajirul | 39.4589 | 1.879 | TA325 | 272/3 | Completed
2025-01-31 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.4589 | 4.3843 | TA325 | 272/4 | Completed
2025-02-01 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.0448 | 1.5672 | TA325 | 147/6 | Completed
2025-02-01 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-02-01 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.4524 | 4.7158 | TA325 | 131/0 | Completed
2025-02-01 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.0448 | 6.0075 | TA325 | 272/2 | Completed
2025-02-01 | 2025-01-30 | 2025-02-02 | Dhaneswar Mahto | 37.7305 | 9.4326 | TA325 | 137A/2 | Completed
2025-02-01 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.4178 | 9.0696 | TA325 | 139/0 | Completed
2025-02-01 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.1461 | 3.5658 | TA325 | 262/0 | Completed
2025-02-01 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.4178 | 9.0696 | TA325 | 138/0 | Completed
2025-02-01 | 2025-01-30 | 2025-02-04 | Jwala | 37.7305 | 6.2884 | TA325 | 272A/2 | Completed
2025-02-01 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.7305 | 3.773 | TA325 | 197/2 | Completed
2025-02-01 | 2025-02-01 | 2025-02-15 | Mjr | 77.7181 | 5.1812 | TA325 | 137/0 | Completed
2025-02-01 | 2025-01-21 | 2025-02-03 | Modina India | 37.7305 | 2.695 | TA325 | 159/4 | Completed
2025-02-01 | 2025-02-01 | 2025-02-09 | Modina India | 39.4589 | 4.3843 | TA325 | 148/1 | Completed
2025-02-01 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.7305 | 1.6405 | TA325 | 159/1 | Completed
2025-02-01 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-01 | 2025-02-01 | 2025-02-17 | Senahul | 64.2538 | 3.7796 | TA325 | 253/0 | Completed
2025-02-01 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.7305 | 2.3582 | TA325 | 130/1 | Completed
2025-02-01 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.7305 | 3.1442 | TA325 | 137/6 | Completed
2025-02-01 | 2025-01-17 | 2025-02-06 | Tajirul | 39.4589 | 1.879 | TA325 | 272/3 | Completed
2025-02-01 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.4589 | 4.3843 | TA325 | 272/4 | Completed
2025-02-02 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.0448 | 1.5672 | TA325 | 147/6 | Completed
2025-02-02 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-02-02 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.4524 | 4.7158 | TA325 | 131/0 | Completed
2025-02-02 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.0448 | 6.0075 | TA325 | 272/2 | Completed
2025-02-02 | 2025-01-30 | 2025-02-02 | Dhaneswar Mahto | 37.7305 | 9.4326 | TA325 | 137A/2 | Completed
2025-02-02 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.4178 | 9.0696 | TA325 | 139/0 | Completed
2025-02-02 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.1461 | 3.5658 | TA325 | 262/0 | Completed
2025-02-02 | 2025-01-30 | 2025-02-04 | Jwala | 37.7305 | 6.2884 | TA325 | 272A/2 | Completed
2025-02-02 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.7305 | 3.773 | TA325 | 197/2 | Completed
2025-02-02 | 2025-02-01 | 2025-02-15 | Mjr | 77.7181 | 5.1812 | TA325 | 137/0 | Completed
2025-02-02 | 2025-01-21 | 2025-02-03 | Modina India | 37.7305 | 2.695 | TA325 | 159/4 | Completed
2025-02-02 | 2025-02-01 | 2025-02-09 | Modina India | 39.4589 | 4.3843 | TA325 | 148/1 | Completed
2025-02-02 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.7305 | 1.6405 | TA325 | 159/1 | Completed
2025-02-02 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-02 | 2025-02-01 | 2025-02-17 | Senahul | 64.2538 | 3.7796 | TA325 | 253/0 | Completed
2025-02-02 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.7305 | 2.3582 | TA325 | 130/1 | Completed
2025-02-02 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.7305 | 3.1442 | TA325 | 137/6 | Completed
2025-02-02 | 2025-01-17 | 2025-02-06 | Tajirul | 39.4589 | 1.879 | TA325 | 272/3 | Completed
2025-02-02 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.4589 | 4.3843 | TA325 | 272/4 | Completed
2025-02-03 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.0448 | 1.5672 | TA325 | 147/6 | Completed
2025-02-03 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-02-03 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.4524 | 4.7158 | TA325 | 131/0 | Completed
2025-02-03 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.0448 | 6.0075 | TA325 | 272/2 | Completed
2025-02-03 | 2025-02-03 | 2025-02-07 | Dhaneswar Mahto | 39.4589 | 7.8918 | TA325 | 137/5 | Completed
2025-02-03 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.4178 | 9.0696 | TA325 | 139/0 | Completed
2025-02-03 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.1461 | 3.5658 | TA325 | 262/0 | Completed
2025-02-03 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.7282 | 6.3897 | TA325 | 138/1 | Completed
2025-02-03 | 2025-01-30 | 2025-02-04 | Jwala | 37.7305 | 6.2884 | TA325 | 272A/2 | Completed
2025-02-03 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.7305 | 3.773 | TA325 | 197/2 | Completed
2025-02-03 | 2025-02-01 | 2025-02-15 | Mjr | 77.7181 | 5.1812 | TA325 | 137/0 | Completed
2025-02-03 | 2025-01-21 | 2025-02-03 | Modina India | 37.7305 | 2.695 | TA325 | 159/4 | Completed
2025-02-03 | 2025-02-01 | 2025-02-09 | Modina India | 39.4589 | 4.3843 | TA325 | 148/1 | Completed
2025-02-03 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.7305 | 1.6405 | TA325 | 159/1 | Completed
2025-02-03 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-03 | 2025-02-01 | 2025-02-17 | Senahul | 64.2538 | 3.7796 | TA325 | 253/0 | Completed
2025-02-03 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.7305 | 2.3582 | TA325 | 130/1 | Completed
2025-02-03 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.7305 | 3.1442 | TA325 | 137/6 | Completed
2025-02-03 | 2025-01-17 | 2025-02-06 | Tajirul | 39.4589 | 1.879 | TA325 | 272/3 | Completed
2025-02-04 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.0448 | 1.5672 | TA325 | 147/6 | Completed
2025-02-04 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-02-04 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.4524 | 4.7158 | TA325 | 131/0 | Completed
2025-02-04 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.0448 | 6.0075 | TA325 | 272/2 | Completed
2025-02-04 | 2025-02-03 | 2025-02-07 | Dhaneswar Mahto | 39.4589 | 7.8918 | TA325 | 137/5 | Completed
2025-02-04 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.4178 | 9.0696 | TA325 | 139/0 | Completed
2025-02-04 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.1461 | 3.5658 | TA325 | 262/0 | Completed
2025-02-04 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.7282 | 6.3897 | TA325 | 138/1 | Completed
2025-02-04 | 2025-01-30 | 2025-02-04 | Jwala | 37.7305 | 6.2884 | TA325 | 272A/2 | Completed
2025-02-04 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.7305 | 4.1923 | TA325 | 266/2 | Completed
2025-02-04 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.7305 | 3.773 | TA325 | 197/2 | Completed
2025-02-04 | 2025-02-01 | 2025-02-15 | Mjr | 77.7181 | 5.1812 | TA325 | 137/0 | Completed
2025-02-04 | 2025-02-01 | 2025-02-09 | Modina India | 39.4589 | 4.3843 | TA325 | 148/1 | Completed
2025-02-04 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.7305 | 1.6405 | TA325 | 159/1 | Completed
2025-02-04 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-04 | 2025-02-01 | 2025-02-17 | Senahul | 64.2538 | 3.7796 | TA325 | 253/0 | Completed
2025-02-04 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.7305 | 2.3582 | TA325 | 130/1 | Completed
2025-02-04 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.7305 | 3.1442 | TA325 | 137/6 | Completed
2025-02-04 | 2025-01-17 | 2025-02-06 | Tajirul | 39.4589 | 1.879 | TA325 | 272/3 | Completed
2025-02-04 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.2538 | 6.4254 | TA325 | 271/0 | Completed
2025-02-05 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.0448 | 1.5672 | TA325 | 147/6 | Completed
2025-02-05 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-02-05 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.4524 | 4.7158 | TA325 | 131/0 | Completed
2025-02-05 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.2538 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-05 | 2025-02-03 | 2025-02-07 | Dhaneswar Mahto | 39.4589 | 7.8918 | TA325 | 137/5 | Completed
2025-02-05 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.7305 | 5.3901 | TA325 | 138/2 | Completed
2025-02-05 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.1461 | 3.5658 | TA325 | 262/0 | Completed
2025-02-05 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.7282 | 6.3897 | TA325 | 138/1 | Completed
2025-02-05 | 2025-02-05 | 2025-02-09 | Jwala | 37.7305 | 7.5461 | TA325 | 272A/3 | Completed
2025-02-05 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.7305 | 4.1923 | TA325 | 266/2 | Completed
2025-02-05 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.7305 | 3.773 | TA325 | 197/2 | Completed
2025-02-05 | 2025-02-01 | 2025-02-15 | Mjr | 77.7181 | 5.1812 | TA325 | 137/0 | Completed
2025-02-05 | 2025-02-01 | 2025-02-09 | Modina India | 39.4589 | 4.3843 | TA325 | 148/1 | Completed
2025-02-05 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.7305 | 1.6405 | TA325 | 159/1 | Completed
2025-02-05 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-05 | 2025-02-01 | 2025-02-17 | Senahul | 64.2538 | 3.7796 | TA325 | 253/0 | Completed
2025-02-05 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.7305 | 2.3582 | TA325 | 130/1 | Completed
2025-02-05 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.7305 | 3.1442 | TA325 | 137/6 | Completed
2025-02-05 | 2025-01-17 | 2025-02-06 | Tajirul | 39.4589 | 1.879 | TA325 | 272/3 | Completed
2025-02-05 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.2538 | 6.4254 | TA325 | 271/0 | Completed
2025-02-06 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.0448 | 1.5672 | TA325 | 147/6 | Completed
2025-02-06 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-02-06 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.2538 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-06 | 2025-02-03 | 2025-02-07 | Dhaneswar Mahto | 39.4589 | 7.8918 | TA325 | 137/5 | Completed
2025-02-06 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.7305 | 5.3901 | TA325 | 138/2 | Completed
2025-02-06 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.1461 | 3.5658 | TA325 | 262/0 | Completed
2025-02-06 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.7282 | 6.3897 | TA325 | 138/1 | Completed
2025-02-06 | 2025-02-05 | 2025-02-09 | Jwala | 37.7305 | 7.5461 | TA325 | 272A/3 | Completed
2025-02-06 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.7305 | 4.1923 | TA325 | 266/2 | Completed
2025-02-06 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.7305 | 3.773 | TA325 | 197/2 | Completed
2025-02-06 | 2025-02-01 | 2025-02-15 | Mjr | 77.7181 | 5.1812 | TA325 | 137/0 | Completed
2025-02-06 | 2025-02-01 | 2025-02-09 | Modina India | 39.4589 | 4.3843 | TA325 | 148/1 | Completed
2025-02-06 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.7305 | 1.6405 | TA325 | 159/1 | Completed
2025-02-06 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-06 | 2025-02-01 | 2025-02-17 | Senahul | 64.2538 | 3.7796 | TA325 | 253/0 | Completed
2025-02-06 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.7305 | 2.3582 | TA325 | 130/1 | Completed
2025-02-06 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.7305 | 3.1442 | TA325 | 137/6 | Completed
2025-02-06 | 2025-01-17 | 2025-02-06 | Tajirul | 39.4589 | 1.879 | TA325 | 272/3 | Completed
2025-02-06 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.2538 | 6.4254 | TA325 | 271/0 | Completed
2025-02-07 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.0448 | 1.5672 | TA325 | 147/6 | Completed
2025-02-07 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-02-07 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.2538 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-07 | 2025-02-03 | 2025-02-07 | Dhaneswar Mahto | 39.4589 | 7.8918 | TA325 | 137/5 | Completed
2025-02-07 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.7305 | 5.3901 | TA325 | 138/2 | Completed
2025-02-07 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.1461 | 3.5658 | TA325 | 262/0 | Completed
2025-02-07 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.7282 | 6.3897 | TA325 | 138/1 | Completed
2025-02-07 | 2025-02-05 | 2025-02-09 | Jwala | 37.7305 | 7.5461 | TA325 | 272A/3 | Completed
2025-02-07 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.7305 | 4.1923 | TA325 | 266/2 | Completed
2025-02-07 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.7305 | 3.773 | TA325 | 197/2 | Completed
2025-02-07 | 2025-02-01 | 2025-02-15 | Mjr | 77.7181 | 5.1812 | TA325 | 137/0 | Completed
2025-02-07 | 2025-02-01 | 2025-02-09 | Modina India | 39.4589 | 4.3843 | TA325 | 148/1 | Completed
2025-02-07 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.7305 | 1.6405 | TA325 | 159/1 | Completed
2025-02-07 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-07 | 2025-02-01 | 2025-02-17 | Senahul | 64.2538 | 3.7796 | TA325 | 253/0 | Completed
2025-02-07 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.7305 | 2.3582 | TA325 | 130/1 | Completed
2025-02-07 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.7305 | 3.1442 | TA325 | 137/6 | Completed
2025-02-07 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.2538 | 6.4254 | TA325 | 271/0 | Completed
2025-02-08 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.0448 | 1.5672 | TA325 | 147/6 | Completed
2025-02-08 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-02-08 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.2538 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-08 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.7305 | 5.3901 | TA325 | 138/2 | Completed
2025-02-08 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.1461 | 3.5658 | TA325 | 262/0 | Completed
2025-02-08 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.7282 | 6.3897 | TA325 | 138/1 | Completed
2025-02-08 | 2025-02-05 | 2025-02-09 | Jwala | 37.7305 | 7.5461 | TA325 | 272A/3 | Completed
2025-02-08 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.7305 | 4.1923 | TA325 | 266/2 | Completed
2025-02-08 | 2025-02-01 | 2025-02-15 | Mjr | 77.7181 | 5.1812 | TA325 | 137/0 | Completed
2025-02-08 | 2025-02-01 | 2025-02-09 | Modina India | 39.4589 | 4.3843 | TA325 | 148/1 | Completed
2025-02-08 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.7305 | 1.6405 | TA325 | 159/1 | Completed
2025-02-08 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-08 | 2025-02-01 | 2025-02-17 | Senahul | 64.2538 | 3.7796 | TA325 | 253/0 | Completed
2025-02-08 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.7305 | 2.3582 | TA325 | 130/1 | Completed
2025-02-08 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.2538 | 6.4254 | TA325 | 271/0 | Completed
2025-02-09 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.0448 | 1.5672 | TA325 | 147/6 | Completed
2025-02-09 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-02-09 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.2538 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-09 | 2025-02-09 | 2025-02-14 | Dhaneswar Mahto | 65.7565 | 10.9594 | TA325 | 139A/0 | Completed
2025-02-09 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.7305 | 5.3901 | TA325 | 138/2 | Completed
2025-02-09 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.1461 | 3.5658 | TA325 | 262/0 | Completed
2025-02-09 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.7282 | 6.3897 | TA325 | 138/1 | Completed
2025-02-09 | 2025-02-05 | 2025-02-09 | Jwala | 37.7305 | 7.5461 | TA325 | 272A/3 | Completed
2025-02-09 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.7305 | 4.1923 | TA325 | 266/2 | Completed
2025-02-09 | 2025-02-01 | 2025-02-15 | Mjr | 77.7181 | 5.1812 | TA325 | 137/0 | Completed
2025-02-09 | 2025-02-01 | 2025-02-09 | Modina India | 39.4589 | 4.3843 | TA325 | 148/1 | Completed
2025-02-09 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.7305 | 1.6405 | TA325 | 159/1 | Completed
2025-02-09 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-09 | 2025-02-01 | 2025-02-17 | Senahul | 64.2538 | 3.7796 | TA325 | 253/0 | Completed
2025-02-09 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.7305 | 2.3582 | TA325 | 130/1 | Completed
2025-02-09 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.7305 | 3.773 | TA325 | 157/1 | Completed
2025-02-09 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.2538 | 6.4254 | TA325 | 271/0 | Completed
2025-02-10 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.0448 | 1.5672 | TA325 | 147/6 | Completed
2025-02-10 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-02-10 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.2538 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-10 | 2025-02-09 | 2025-02-14 | Dhaneswar Mahto | 65.7565 | 10.9594 | TA325 | 139A/0 | Completed
2025-02-10 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.7305 | 5.3901 | TA325 | 138/2 | Completed
2025-02-10 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.1461 | 3.5658 | TA325 | 262/0 | Completed
2025-02-10 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.7305 | 7.5461 | TA325 | 139/2 | Completed
2025-02-10 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.7305 | 4.1923 | TA325 | 266/2 | Completed
2025-02-10 | 2025-02-01 | 2025-02-15 | Mjr | 77.7181 | 5.1812 | TA325 | 137/0 | Completed
2025-02-10 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.7305 | 1.6405 | TA325 | 159/1 | Completed
2025-02-10 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-10 | 2025-02-01 | 2025-02-17 | Senahul | 64.2538 | 3.7796 | TA325 | 253/0 | Completed
2025-02-10 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.7305 | 3.773 | TA325 | 157/1 | Completed
2025-02-10 | 2025-02-10 | 2025-03-07 | Tajirul | 46.6235 | 1.7932 | TA325 | 272/7 | Completed
2025-02-10 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.2538 | 6.4254 | TA325 | 271/0 | Completed
2025-02-11 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.0448 | 1.5672 | TA325 | 147/6 | Completed
2025-02-11 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-02-11 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.2538 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-11 | 2025-02-09 | 2025-02-14 | Dhaneswar Mahto | 65.7565 | 10.9594 | TA325 | 139A/0 | Completed
2025-02-11 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.7305 | 5.3901 | TA325 | 138/2 | Completed
2025-02-11 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.1461 | 3.5658 | TA325 | 262/0 | Completed
2025-02-11 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.7305 | 7.5461 | TA325 | 139/2 | Completed
2025-02-11 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.7305 | 4.1923 | TA325 | 266/2 | Completed
2025-02-11 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.0448 | 5.1493 | TA325 | 270/6 | Completed
2025-02-11 | 2025-02-01 | 2025-02-15 | Mjr | 77.7181 | 5.1812 | TA325 | 137/0 | Completed
2025-02-11 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.7305 | 1.6405 | TA325 | 159/1 | Completed
2025-02-11 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-11 | 2025-02-01 | 2025-02-17 | Senahul | 64.2538 | 3.7796 | TA325 | 253/0 | Completed
2025-02-11 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.7305 | 5.3901 | TA325 | 141/1 | Completed
2025-02-11 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.7305 | 3.773 | TA325 | 157/1 | Completed
2025-02-11 | 2025-02-10 | 2025-03-07 | Tajirul | 46.6235 | 1.7932 | TA325 | 272/7 | Completed
2025-02-11 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.2538 | 6.4254 | TA325 | 271/0 | Completed
2025-02-12 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.0448 | 1.5672 | TA325 | 147/6 | Completed
2025-02-12 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-02-12 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.2538 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-12 | 2025-02-09 | 2025-02-14 | Dhaneswar Mahto | 65.7565 | 10.9594 | TA325 | 139A/0 | Completed
2025-02-12 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.4589 | 6.5765 | TA325 | 139/1 | Completed
2025-02-12 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.7305 | 7.5461 | TA325 | 139/2 | Completed
2025-02-12 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.7305 | 4.1923 | TA325 | 266/2 | Completed
2025-02-12 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.0448 | 5.1493 | TA325 | 270/6 | Completed
2025-02-12 | 2025-02-01 | 2025-02-15 | Mjr | 77.7181 | 5.1812 | TA325 | 137/0 | Completed
2025-02-12 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.7305 | 1.6405 | TA325 | 159/1 | Completed
2025-02-12 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-12 | 2025-02-01 | 2025-02-17 | Senahul | 64.2538 | 3.7796 | TA325 | 253/0 | Completed
2025-02-12 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.7305 | 5.3901 | TA325 | 141/1 | Completed
2025-02-12 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.7305 | 3.773 | TA325 | 157/1 | Completed
2025-02-12 | 2025-02-10 | 2025-03-07 | Tajirul | 46.6235 | 1.7932 | TA325 | 272/7 | Completed
2025-02-12 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.2538 | 6.4254 | TA325 | 271/0 | Completed
2025-02-13 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.0448 | 1.5672 | TA325 | 147/6 | Completed
2025-02-13 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-02-13 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.2538 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-13 | 2025-02-09 | 2025-02-14 | Dhaneswar Mahto | 65.7565 | 10.9594 | TA325 | 139A/0 | Completed
2025-02-13 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.4589 | 6.5765 | TA325 | 139/1 | Completed
2025-02-13 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.7305 | 7.5461 | TA325 | 139/2 | Completed
2025-02-13 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.0448 | 5.1493 | TA325 | 270/6 | Completed
2025-02-13 | 2025-02-01 | 2025-02-15 | Mjr | 77.7181 | 5.1812 | TA325 | 137/0 | Completed
2025-02-13 | 2025-02-13 | 2025-02-21 | Modina India | 37.7305 | 4.1923 | TA325 | 147B/1 | Completed
2025-02-13 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-13 | 2025-02-01 | 2025-02-17 | Senahul | 64.2538 | 3.7796 | TA325 | 253/0 | Completed
2025-02-13 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.7305 | 5.3901 | TA325 | 141/1 | Completed
2025-02-13 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.0448 | 5.1493 | TA325 | 141/2 | Completed
2025-02-13 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.7305 | 3.773 | TA325 | 157/1 | Completed
2025-02-13 | 2025-02-10 | 2025-03-07 | Tajirul | 46.6235 | 1.7932 | TA325 | 272/7 | Completed
2025-02-13 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.2538 | 6.4254 | TA325 | 271/0 | Completed
2025-02-14 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.0448 | 1.5672 | TA325 | 147/6 | Completed
2025-02-14 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-02-14 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.2538 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-14 | 2025-02-09 | 2025-02-14 | Dhaneswar Mahto | 65.7565 | 10.9594 | TA325 | 139A/0 | Completed
2025-02-14 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.4589 | 6.5765 | TA325 | 139/1 | Completed
2025-02-14 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.0448 | 3.2768 | TA325 | 250/1 | Completed
2025-02-14 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.7305 | 7.5461 | TA325 | 139/2 | Completed
2025-02-14 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.4178 | 4.186 | TA325 | 249/0 | Completed
2025-02-14 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.0448 | 5.1493 | TA325 | 270/6 | Completed
2025-02-14 | 2025-02-01 | 2025-02-15 | Mjr | 77.7181 | 5.1812 | TA325 | 137/0 | Completed
2025-02-14 | 2025-02-13 | 2025-02-21 | Modina India | 37.7305 | 4.1923 | TA325 | 147B/1 | Completed
2025-02-14 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-14 | 2025-02-01 | 2025-02-17 | Senahul | 64.2538 | 3.7796 | TA325 | 253/0 | Completed
2025-02-14 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.7305 | 5.3901 | TA325 | 141/1 | Completed
2025-02-14 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.0448 | 5.1493 | TA325 | 141/2 | Completed
2025-02-14 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.7305 | 3.773 | TA325 | 157/1 | Completed
2025-02-14 | 2025-02-10 | 2025-03-07 | Tajirul | 46.6235 | 1.7932 | TA325 | 272/7 | Completed
2025-02-14 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.7305 | 4.7163 | TA325 | 271/2 | Completed
2025-02-15 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.0448 | 1.5672 | TA325 | 147/6 | Completed
2025-02-15 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-02-15 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.2538 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-15 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.4589 | 6.5765 | TA325 | 139/1 | Completed
2025-02-15 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.0448 | 3.2768 | TA325 | 250/1 | Completed
2025-02-15 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.4178 | 4.186 | TA325 | 249/0 | Completed
2025-02-15 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.0448 | 5.1493 | TA325 | 270/6 | Completed
2025-02-15 | 2025-02-01 | 2025-02-15 | Mjr | 77.7181 | 5.1812 | TA325 | 137/0 | Completed
2025-02-15 | 2025-02-13 | 2025-02-21 | Modina India | 37.7305 | 4.1923 | TA325 | 147B/1 | Completed
2025-02-15 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-15 | 2025-02-01 | 2025-02-17 | Senahul | 64.2538 | 3.7796 | TA325 | 253/0 | Completed
2025-02-15 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.7305 | 5.3901 | TA325 | 141/1 | Completed
2025-02-15 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.0448 | 5.1493 | TA325 | 141/2 | Completed
2025-02-15 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.7305 | 3.773 | TA325 | 157/1 | Completed
2025-02-15 | 2025-02-10 | 2025-03-07 | Tajirul | 46.6235 | 1.7932 | TA325 | 272/7 | Completed
2025-02-15 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.7305 | 4.7163 | TA325 | 271/2 | Completed
2025-02-16 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.0448 | 1.5672 | TA325 | 147/6 | Completed
2025-02-16 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-02-16 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed
2025-02-16 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.4589 | 6.5765 | TA325 | 139/1 | Completed
2025-02-16 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.0448 | 3.2768 | TA325 | 250/1 | Completed
2025-02-16 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.2993 | 10.5374 | TA325 | 141/0 | Completed
2025-02-16 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.4178 | 4.186 | TA325 | 249/0 | Completed
2025-02-16 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.0448 | 5.1493 | TA325 | 270/6 | Completed
2025-02-16 | 2025-02-13 | 2025-02-21 | Modina India | 37.7305 | 4.1923 | TA325 | 147B/1 | Completed
2025-02-16 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-16 | 2025-02-01 | 2025-02-17 | Senahul | 64.2538 | 3.7796 | TA325 | 253/0 | Completed
2025-02-16 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.7305 | 5.3901 | TA325 | 141/1 | Completed
2025-02-16 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.0448 | 5.1493 | TA325 | 141/2 | Completed
2025-02-16 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.7305 | 3.773 | TA325 | 157/1 | Completed
2025-02-16 | 2025-02-10 | 2025-03-07 | Tajirul | 46.6235 | 1.7932 | TA325 | 272/7 | Completed
2025-02-16 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.7305 | 4.7163 | TA325 | 271/2 | Completed
2025-02-17 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.0448 | 1.5672 | TA325 | 147/6 | Completed
2025-02-17 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-02-17 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.0448 | 5.1493 | TA325 | 270/7 | Completed
2025-02-17 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed
2025-02-17 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.4589 | 6.5765 | TA325 | 139/1 | Completed
2025-02-17 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.0448 | 3.2768 | TA325 | 250/1 | Completed
2025-02-17 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.2993 | 10.5374 | TA325 | 141/0 | Completed
2025-02-17 | 2025-02-17 | 2025-02-23 | Jwala | 64.2538 | 9.1791 | TA325 | 274/0 | Completed
2025-02-17 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.4178 | 4.186 | TA325 | 249/0 | Completed
2025-02-17 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.0448 | 5.1493 | TA325 | 270/6 | Completed
2025-02-17 | 2025-02-13 | 2025-02-21 | Modina India | 37.7305 | 4.1923 | TA325 | 147B/1 | Completed
2025-02-17 | 2025-02-01 | 2025-02-17 | Senahul | 64.2538 | 3.7796 | TA325 | 253/0 | Completed
2025-02-17 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.7305 | 5.3901 | TA325 | 141/1 | Completed
2025-02-17 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.0448 | 5.1493 | TA325 | 141/2 | Completed
2025-02-17 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.7305 | 3.773 | TA325 | 157/1 | Completed
2025-02-17 | 2025-02-10 | 2025-03-07 | Tajirul | 46.6235 | 1.7932 | TA325 | 272/7 | Completed
2025-02-17 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.7305 | 4.7163 | TA325 | 271/2 | Completed
2025-02-18 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.0448 | 1.5672 | TA325 | 147/6 | Completed
2025-02-18 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-02-18 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.0448 | 5.1493 | TA325 | 270/7 | Completed
2025-02-18 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed
2025-02-18 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-18 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.0448 | 3.2768 | TA325 | 250/1 | Completed
2025-02-18 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.2993 | 10.5374 | TA325 | 141/0 | Completed
2025-02-18 | 2025-02-17 | 2025-02-23 | Jwala | 64.2538 | 9.1791 | TA325 | 274/0 | Completed
2025-02-18 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.4178 | 4.186 | TA325 | 249/0 | Completed
2025-02-18 | 2025-02-18 | 2025-02-27 | Mjr | 37.7305 | 3.773 | TA325 | 137/2 | Completed
2025-02-18 | 2025-02-13 | 2025-02-21 | Modina India | 37.7305 | 4.1923 | TA325 | 147B/1 | Completed
2025-02-18 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.0448 | 5.1493 | TA325 | 141/2 | Completed
2025-02-18 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.7305 | 3.773 | TA325 | 157/1 | Completed
2025-02-18 | 2025-02-10 | 2025-03-07 | Tajirul | 46.6235 | 1.7932 | TA325 | 272/7 | Completed
2025-02-18 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.7305 | 4.7163 | TA325 | 271/2 | Completed
2025-02-19 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-02-19 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.0448 | 5.1493 | TA325 | 270/7 | Completed
2025-02-19 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed
2025-02-19 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-19 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.0448 | 3.2768 | TA325 | 250/1 | Completed
2025-02-19 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.2993 | 10.5374 | TA325 | 141/0 | Completed
2025-02-19 | 2025-02-17 | 2025-02-23 | Jwala | 64.2538 | 9.1791 | TA325 | 274/0 | Completed
2025-02-19 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.4178 | 4.186 | TA325 | 249/0 | Completed
2025-02-19 | 2025-02-18 | 2025-02-27 | Mjr | 37.7305 | 3.773 | TA325 | 137/2 | Completed
2025-02-19 | 2025-02-13 | 2025-02-21 | Modina India | 37.7305 | 4.1923 | TA325 | 147B/1 | Completed
2025-02-19 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.0448 | 5.1493 | TA325 | 141/2 | Completed
2025-02-19 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.4589 | 5.637 | TA325 | 141/3 | Completed
2025-02-19 | 2025-02-10 | 2025-03-07 | Tajirul | 46.6235 | 1.7932 | TA325 | 272/7 | Completed
2025-02-19 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.7305 | 4.7163 | TA325 | 271/2 | Completed
2025-02-20 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-02-20 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.0448 | 5.1493 | TA325 | 270/7 | Completed
2025-02-20 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed
2025-02-20 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-20 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.0448 | 3.2768 | TA325 | 250/1 | Completed
2025-02-20 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.2993 | 10.5374 | TA325 | 141/0 | Completed
2025-02-20 | 2025-02-17 | 2025-02-23 | Jwala | 64.2538 | 9.1791 | TA325 | 274/0 | Completed
2025-02-20 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.4178 | 4.186 | TA325 | 249/0 | Completed
2025-02-20 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.7305 | 4.1923 | TA325 | 270/5 | Completed
2025-02-20 | 2025-02-18 | 2025-02-27 | Mjr | 37.7305 | 3.773 | TA325 | 137/2 | Completed
2025-02-20 | 2025-02-13 | 2025-02-21 | Modina India | 37.7305 | 4.1923 | TA325 | 147B/1 | Completed
2025-02-20 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-02-20 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.4589 | 5.637 | TA325 | 141/3 | Completed
2025-02-20 | 2025-02-10 | 2025-03-07 | Tajirul | 46.6235 | 1.7932 | TA325 | 272/7 | Completed
2025-02-20 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.7305 | 4.7163 | TA325 | 271/2 | Completed
2025-02-21 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.0448 | 5.1493 | TA325 | 270/7 | Completed
2025-02-21 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed
2025-02-21 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-21 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.0448 | 3.2768 | TA325 | 250/1 | Completed
2025-02-21 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.2993 | 10.5374 | TA325 | 141/0 | Completed
2025-02-21 | 2025-02-17 | 2025-02-23 | Jwala | 64.2538 | 9.1791 | TA325 | 274/0 | Completed
2025-02-21 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.4178 | 4.186 | TA325 | 249/0 | Completed
2025-02-21 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.7305 | 4.1923 | TA325 | 270/5 | Completed
2025-02-21 | 2025-02-18 | 2025-02-27 | Mjr | 37.7305 | 3.773 | TA325 | 137/2 | Completed
2025-02-21 | 2025-02-13 | 2025-02-21 | Modina India | 37.7305 | 4.1923 | TA325 | 147B/1 | Completed
2025-02-21 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-02-21 | 2025-02-21 | 2025-03-18 | Senahul | 77.7181 | 2.9892 | TA325 | 267A/0 | Completed
2025-02-21 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.4589 | 5.637 | TA325 | 141/3 | Completed
2025-02-21 | 2025-02-10 | 2025-03-07 | Tajirul | 46.6235 | 1.7932 | TA325 | 272/7 | Completed
2025-02-21 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.7305 | 4.7163 | TA325 | 271/2 | Completed
2025-02-22 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.2376 | 3.1408 | TA325 | 270/0 | Completed
2025-02-22 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.0448 | 5.1493 | TA325 | 270/7 | Completed
2025-02-22 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed
2025-02-22 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-22 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.0448 | 3.2768 | TA325 | 250/1 | Completed
2025-02-22 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.2993 | 10.5374 | TA325 | 141/0 | Completed
2025-02-22 | 2025-02-17 | 2025-02-23 | Jwala | 64.2538 | 9.1791 | TA325 | 274/0 | Completed
2025-02-22 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.4178 | 4.186 | TA325 | 249/0 | Completed
2025-02-22 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.7305 | 4.1923 | TA325 | 270/5 | Completed
2025-02-22 | 2025-02-18 | 2025-02-27 | Mjr | 37.7305 | 3.773 | TA325 | 137/2 | Completed
2025-02-22 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-02-22 | 2025-02-21 | 2025-03-18 | Senahul | 77.7181 | 2.9892 | TA325 | 267A/0 | Completed
2025-02-22 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.4589 | 5.637 | TA325 | 141/3 | Completed
2025-02-22 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.4589 | 2.8185 | TA325 | 145A/1 | Completed
2025-02-22 | 2025-02-10 | 2025-03-07 | Tajirul | 46.6235 | 1.7932 | TA325 | 272/7 | Completed
2025-02-22 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.0448 | 3.6045 | TA325 | 271/4 | Completed
2025-02-23 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.2376 | 3.1408 | TA325 | 270/0 | Completed
2025-02-23 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.7305 | 2.2194 | TA325 | 157/2 | Completed
2025-02-23 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.0448 | 5.1493 | TA325 | 270/7 | Completed
2025-02-23 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-23 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.0448 | 3.2768 | TA325 | 250/1 | Completed
2025-02-23 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.2993 | 10.5374 | TA325 | 141/0 | Completed
2025-02-23 | 2025-02-17 | 2025-02-23 | Jwala | 64.2538 | 9.1791 | TA325 | 274/0 | Completed
2025-02-23 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.4178 | 4.186 | TA325 | 249/0 | Completed
2025-02-23 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.7305 | 4.1923 | TA325 | 270/5 | Completed
2025-02-23 | 2025-02-18 | 2025-02-27 | Mjr | 37.7305 | 3.773 | TA325 | 137/2 | Completed
2025-02-23 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-02-23 | 2025-02-21 | 2025-03-18 | Senahul | 77.7181 | 2.9892 | TA325 | 267A/0 | Completed
2025-02-23 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.4589 | 5.637 | TA325 | 141/3 | Completed
2025-02-23 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.4589 | 2.8185 | TA325 | 145A/1 | Completed
2025-02-23 | 2025-02-10 | 2025-03-07 | Tajirul | 46.6235 | 1.7932 | TA325 | 272/7 | Completed
2025-02-23 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.0448 | 3.6045 | TA325 | 271/4 | Completed
2025-02-24 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.2376 | 3.1408 | TA325 | 270/0 | Completed
2025-02-24 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.7305 | 2.2194 | TA325 | 157/2 | Completed
2025-02-24 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.2376 | 10.3197 | TA325 | 143A/0 | Completed
2025-02-24 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-24 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.0448 | 3.2768 | TA325 | 250/1 | Completed
2025-02-24 | 2025-02-24 | 2025-02-28 | Jwala | 44.7282 | 8.9456 | TA325 | 273/2 | Completed
2025-02-24 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.4178 | 4.186 | TA325 | 249/0 | Completed
2025-02-24 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.7305 | 4.1923 | TA325 | 270/5 | Completed
2025-02-24 | 2025-02-18 | 2025-02-27 | Mjr | 37.7305 | 3.773 | TA325 | 137/2 | Completed
2025-02-24 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-02-24 | 2025-02-21 | 2025-03-18 | Senahul | 77.7181 | 2.9892 | TA325 | 267A/0 | Completed
2025-02-24 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.4589 | 5.637 | TA325 | 141/3 | Completed
2025-02-24 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.4589 | 2.8185 | TA325 | 145A/1 | Completed
2025-02-24 | 2025-02-10 | 2025-03-07 | Tajirul | 46.6235 | 1.7932 | TA325 | 272/7 | Completed
2025-02-24 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.0448 | 3.6045 | TA325 | 271/4 | Completed
2025-02-25 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.2376 | 3.1408 | TA325 | 270/0 | Completed
2025-02-25 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.7305 | 2.2194 | TA325 | 157/2 | Completed
2025-02-25 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.2376 | 10.3197 | TA325 | 143A/0 | Completed
2025-02-25 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-25 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.2993 | 10.5374 | TA325 | 143/0 | Completed
2025-02-25 | 2025-02-24 | 2025-02-28 | Jwala | 44.7282 | 8.9456 | TA325 | 273/2 | Completed
2025-02-25 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.4178 | 4.186 | TA325 | 249/0 | Completed
2025-02-25 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.7305 | 4.1923 | TA325 | 270/5 | Completed
2025-02-25 | 2025-02-18 | 2025-02-27 | Mjr | 37.7305 | 3.773 | TA325 | 137/2 | Completed
2025-02-25 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-02-25 | 2025-02-21 | 2025-03-18 | Senahul | 77.7181 | 2.9892 | TA325 | 267A/0 | Completed
2025-02-25 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.4589 | 5.637 | TA325 | 141/3 | Completed
2025-02-25 | 2025-02-25 | 2025-02-28 | Sk Samuil | 37.7305 | 9.4326 | TA325 | 148/5 | Completed
2025-02-25 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.4589 | 2.8185 | TA325 | 145A/1 | Completed
2025-02-25 | 2025-02-10 | 2025-03-07 | Tajirul | 46.6235 | 1.7932 | TA325 | 272/7 | Completed
2025-02-25 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.0448 | 3.6045 | TA325 | 271/4 | Completed
2025-02-26 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.2376 | 3.1408 | TA325 | 270/0 | Completed
2025-02-26 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.7305 | 2.2194 | TA325 | 157/2 | Completed
2025-02-26 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.2376 | 10.3197 | TA325 | 143A/0 | Completed
2025-02-26 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-26 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.2993 | 10.5374 | TA325 | 143/0 | Completed
2025-02-26 | 2025-02-24 | 2025-02-28 | Jwala | 44.7282 | 8.9456 | TA325 | 273/2 | Completed
2025-02-26 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.4178 | 4.186 | TA325 | 249/0 | Completed
2025-02-26 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.7305 | 4.1923 | TA325 | 270/5 | Completed
2025-02-26 | 2025-02-18 | 2025-02-27 | Mjr | 37.7305 | 3.773 | TA325 | 137/2 | Completed
2025-02-26 | 2025-02-26 | 2025-03-22 | Modina India | 82.2388 | 3.2896 | TA325 | 147B/0 | Completed
2025-02-26 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-02-26 | 2025-02-21 | 2025-03-18 | Senahul | 77.7181 | 2.9892 | TA325 | 267A/0 | Completed
2025-02-26 | 2025-02-25 | 2025-02-28 | Sk Samuil | 37.7305 | 9.4326 | TA325 | 148/5 | Completed
2025-02-26 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-02-26 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.4589 | 2.8185 | TA325 | 145A/1 | Completed
2025-02-26 | 2025-02-10 | 2025-03-07 | Tajirul | 46.6235 | 1.7932 | TA325 | 272/7 | Completed
2025-02-26 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.0448 | 3.6045 | TA325 | 271/4 | Completed
2025-02-27 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.2376 | 3.1408 | TA325 | 270/0 | Completed
2025-02-27 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.7305 | 2.2194 | TA325 | 157/2 | Completed
2025-02-27 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.7305 | 5.3901 | TA325 | 267A/1 | Completed
2025-02-27 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.2376 | 10.3197 | TA325 | 143A/0 | Completed
2025-02-27 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-27 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.2993 | 10.5374 | TA325 | 143/0 | Completed
2025-02-27 | 2025-02-24 | 2025-02-28 | Jwala | 44.7282 | 8.9456 | TA325 | 273/2 | Completed
2025-02-27 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.7305 | 4.1923 | TA325 | 270/5 | Completed
2025-02-27 | 2025-02-18 | 2025-02-27 | Mjr | 37.7305 | 3.773 | TA325 | 137/2 | Completed
2025-02-27 | 2025-02-26 | 2025-03-22 | Modina India | 82.2388 | 3.2896 | TA325 | 147B/0 | Completed
2025-02-27 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-02-27 | 2025-02-21 | 2025-03-18 | Senahul | 77.7181 | 2.9892 | TA325 | 267A/0 | Completed
2025-02-27 | 2025-02-25 | 2025-02-28 | Sk Samuil | 37.7305 | 9.4326 | TA325 | 148/5 | Completed
2025-02-27 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-02-27 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.4589 | 2.8185 | TA325 | 145A/1 | Completed
2025-02-27 | 2025-02-10 | 2025-03-07 | Tajirul | 46.6235 | 1.7932 | TA325 | 272/7 | Completed
2025-02-27 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.0448 | 3.6045 | TA325 | 271/4 | Completed
2025-02-28 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.2376 | 3.1408 | TA325 | 270/0 | Completed
2025-02-28 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.7305 | 2.2194 | TA325 | 157/2 | Completed
2025-02-28 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.7305 | 5.3901 | TA325 | 267A/1 | Completed
2025-02-28 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.2376 | 10.3197 | TA325 | 143A/0 | Completed
2025-02-28 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-28 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.2993 | 10.5374 | TA325 | 143/0 | Completed
2025-02-28 | 2025-02-24 | 2025-02-28 | Jwala | 44.7282 | 8.9456 | TA325 | 273/2 | Completed
2025-02-28 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.7305 | 4.1923 | TA325 | 270/5 | Completed
2025-02-28 | 2025-02-26 | 2025-03-22 | Modina India | 82.2388 | 3.2896 | TA325 | 147B/0 | Completed
2025-02-28 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-02-28 | 2025-02-21 | 2025-03-18 | Senahul | 77.7181 | 2.9892 | TA325 | 267A/0 | Completed
2025-02-28 | 2025-02-25 | 2025-02-28 | Sk Samuil | 37.7305 | 9.4326 | TA325 | 148/5 | Completed
2025-02-28 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-02-28 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.4589 | 2.8185 | TA325 | 145A/1 | Completed
2025-02-28 | 2025-02-10 | 2025-03-07 | Tajirul | 46.6235 | 1.7932 | TA325 | 272/7 | Completed
2025-02-28 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.0448 | 3.6045 | TA325 | 271/4 | Completed
2025-03-01 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.2376 | 3.1408 | TA325 | 270/0 | Completed
2025-03-01 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.7305 | 2.2194 | TA325 | 157/2 | Completed
2025-03-01 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.7305 | 5.3901 | TA325 | 267A/1 | Completed
2025-03-01 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.2376 | 10.3197 | TA325 | 143A/0 | Completed
2025-03-01 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-03-01 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.2993 | 10.5374 | TA325 | 143/0 | Completed
2025-03-01 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.7305 | 4.1923 | TA325 | 249/2 | Completed
2025-03-01 | 2025-02-26 | 2025-03-22 | Modina India | 82.2388 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-01 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-01 | 2025-02-21 | 2025-03-18 | Senahul | 77.7181 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-01 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.7282 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-01 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-01 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.4589 | 2.8185 | TA325 | 145A/1 | Completed
2025-03-01 | 2025-02-10 | 2025-03-07 | Tajirul | 46.6235 | 1.7932 | TA325 | 272/7 | Completed
2025-03-01 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.0448 | 3.6045 | TA325 | 271/4 | Completed
2025-03-02 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.2376 | 3.1408 | TA325 | 270/0 | Completed
2025-03-02 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.7305 | 2.2194 | TA325 | 157/2 | Completed
2025-03-02 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.7305 | 5.3901 | TA325 | 267A/1 | Completed
2025-03-02 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.2376 | 10.3197 | TA325 | 143A/0 | Completed
2025-03-02 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-03-02 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.2993 | 10.5374 | TA325 | 143/0 | Completed
2025-03-02 | 2025-03-02 | 2025-03-05 | Jwala | 36.0448 | 9.0112 | TA325 | 272A/6 | Completed
2025-03-02 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.7305 | 4.1923 | TA325 | 249/2 | Completed
2025-03-02 | 2025-03-02 | 2025-03-10 | Mjr | 37.7305 | 4.1923 | TA325 | 143A/4 | Completed
2025-03-02 | 2025-02-26 | 2025-03-22 | Modina India | 82.2388 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-02 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-02 | 2025-02-21 | 2025-03-18 | Senahul | 77.7181 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-02 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.7282 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-02 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-02 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.4589 | 2.8185 | TA325 | 145A/1 | Completed
2025-03-02 | 2025-02-10 | 2025-03-07 | Tajirul | 46.6235 | 1.7932 | TA325 | 272/7 | Completed
2025-03-02 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.0448 | 3.6045 | TA325 | 271/4 | Completed
2025-03-03 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.2376 | 3.1408 | TA325 | 270/0 | Completed
2025-03-03 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.7305 | 2.2194 | TA325 | 157/2 | Completed
2025-03-03 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.7305 | 5.3901 | TA325 | 267A/1 | Completed
2025-03-03 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-03-03 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.2993 | 10.5374 | TA325 | 143/0 | Completed
2025-03-03 | 2025-03-02 | 2025-03-05 | Jwala | 36.0448 | 9.0112 | TA325 | 272A/6 | Completed
2025-03-03 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.7305 | 4.1923 | TA325 | 249/2 | Completed
2025-03-03 | 2025-03-02 | 2025-03-10 | Mjr | 37.7305 | 4.1923 | TA325 | 143A/4 | Completed
2025-03-03 | 2025-02-26 | 2025-03-22 | Modina India | 82.2388 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-03 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-03 | 2025-02-21 | 2025-03-18 | Senahul | 77.7181 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-03 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.7282 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-03 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.7305 | 5.3901 | TA325 | 148/6 | Completed
2025-03-03 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-03 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.4589 | 2.8185 | TA325 | 145A/1 | Completed
2025-03-03 | 2025-02-10 | 2025-03-07 | Tajirul | 46.6235 | 1.7932 | TA325 | 272/7 | Completed
2025-03-03 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.0448 | 3.6045 | TA325 | 271/4 | Completed
2025-03-04 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.2376 | 3.1408 | TA325 | 270/0 | Completed
2025-03-04 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.7305 | 2.2194 | TA325 | 157/2 | Completed
2025-03-04 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.7305 | 5.3901 | TA325 | 267A/1 | Completed
2025-03-04 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 129.341 | 9.2386 | TA325 | 143A/2 | Completed
2025-03-04 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.2993 | 10.5374 | TA325 | 143/0 | Completed
2025-03-04 | 2025-03-02 | 2025-03-05 | Jwala | 36.0448 | 9.0112 | TA325 | 272A/6 | Completed
2025-03-04 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.7305 | 4.1923 | TA325 | 249/2 | Completed
2025-03-04 | 2025-03-02 | 2025-03-10 | Mjr | 37.7305 | 4.1923 | TA325 | 143A/4 | Completed
2025-03-04 | 2025-02-26 | 2025-03-22 | Modina India | 82.2388 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-04 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-04 | 2025-02-21 | 2025-03-18 | Senahul | 77.7181 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-04 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.7282 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-04 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.7305 | 5.3901 | TA325 | 148/6 | Completed
2025-03-04 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-04 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.4589 | 2.8185 | TA325 | 145A/1 | Completed
2025-03-04 | 2025-02-10 | 2025-03-07 | Tajirul | 46.6235 | 1.7932 | TA325 | 272/7 | Completed
2025-03-04 | 2025-03-04 | 2025-03-11 | Thanu Mahto | 36.0448 | 4.5056 | TA325 | 271/3 | Completed
2025-03-05 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.2376 | 3.1408 | TA325 | 270/0 | Completed
2025-03-05 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.7305 | 2.2194 | TA325 | 157/2 | Completed
2025-03-05 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.7305 | 5.3901 | TA325 | 267A/1 | Completed
2025-03-05 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 129.341 | 9.2386 | TA325 | 143A/2 | Completed
2025-03-05 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.4589 | 6.5765 | TA325 | 143A/5 | Completed
2025-03-05 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.4524 | 10.7789 | TA325 | 143A/3 | Completed
2025-03-05 | 2025-03-02 | 2025-03-05 | Jwala | 36.0448 | 9.0112 | TA325 | 272A/6 | Completed
2025-03-05 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.7305 | 4.1923 | TA325 | 249/2 | Completed
2025-03-05 | 2025-03-02 | 2025-03-10 | Mjr | 37.7305 | 4.1923 | TA325 | 143A/4 | Completed
2025-03-05 | 2025-02-26 | 2025-03-22 | Modina India | 82.2388 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-05 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-05 | 2025-02-21 | 2025-03-18 | Senahul | 77.7181 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-05 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.7282 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-05 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.7305 | 5.3901 | TA325 | 148/6 | Completed
2025-03-05 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-05 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.4589 | 2.8185 | TA325 | 145A/1 | Completed
2025-03-05 | 2025-02-10 | 2025-03-07 | Tajirul | 46.6235 | 1.7932 | TA325 | 272/7 | Completed
2025-03-05 | 2025-03-04 | 2025-03-11 | Thanu Mahto | 36.0448 | 4.5056 | TA325 | 271/3 | Completed
2025-03-06 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.2376 | 3.1408 | TA325 | 270/0 | Completed
2025-03-06 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.7305 | 2.2194 | TA325 | 157/2 | Completed
2025-03-06 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 129.341 | 9.2386 | TA325 | 143A/2 | Completed
2025-03-06 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.4589 | 6.5765 | TA325 | 143A/5 | Completed
2025-03-06 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.4524 | 10.7789 | TA325 | 143A/3 | Completed
2025-03-06 | 2025-03-06 | 2025-03-10 | Jwala | 36.0448 | 7.209 | TA325 | 272A/7 | Completed
2025-03-06 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.7305 | 4.1923 | TA325 | 249/2 | Completed
2025-03-06 | 2025-03-02 | 2025-03-10 | Mjr | 37.7305 | 4.1923 | TA325 | 143A/4 | Completed
2025-03-06 | 2025-02-26 | 2025-03-22 | Modina India | 82.2388 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-06 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-06 | 2025-02-21 | 2025-03-18 | Senahul | 77.7181 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-06 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.7282 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-06 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.7305 | 5.3901 | TA325 | 148/6 | Completed
2025-03-06 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-06 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.4589 | 2.8185 | TA325 | 145A/1 | Completed
2025-03-06 | 2025-02-10 | 2025-03-07 | Tajirul | 46.6235 | 1.7932 | TA325 | 272/7 | Completed
2025-03-06 | 2025-03-04 | 2025-03-11 | Thanu Mahto | 36.0448 | 4.5056 | TA325 | 271/3 | Completed
2025-03-07 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.2376 | 3.1408 | TA325 | 270/0 | Completed
2025-03-07 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.7305 | 2.2194 | TA325 | 157/2 | Completed
2025-03-07 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.0448 | 4.005 | TA325 | 267A/2 | Completed
2025-03-07 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 129.341 | 9.2386 | TA325 | 143A/2 | Completed
2025-03-07 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.4589 | 6.5765 | TA325 | 143A/5 | Completed
2025-03-07 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.4524 | 10.7789 | TA325 | 143A/3 | Completed
2025-03-07 | 2025-03-06 | 2025-03-10 | Jwala | 36.0448 | 7.209 | TA325 | 272A/7 | Completed
2025-03-07 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.7305 | 4.1923 | TA325 | 249/2 | Completed
2025-03-07 | 2025-03-02 | 2025-03-10 | Mjr | 37.7305 | 4.1923 | TA325 | 143A/4 | Completed
2025-03-07 | 2025-02-26 | 2025-03-22 | Modina India | 82.2388 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-07 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-07 | 2025-02-21 | 2025-03-18 | Senahul | 77.7181 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-07 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.7282 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-07 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.7305 | 5.3901 | TA325 | 148/6 | Completed
2025-03-07 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-07 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.4589 | 2.8185 | TA325 | 145A/1 | Completed
2025-03-07 | 2025-02-10 | 2025-03-07 | Tajirul | 46.6235 | 1.7932 | TA325 | 272/7 | Completed
2025-03-07 | 2025-03-04 | 2025-03-11 | Thanu Mahto | 36.0448 | 4.5056 | TA325 | 271/3 | Completed
2025-03-08 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.2376 | 3.1408 | TA325 | 270/0 | Completed
2025-03-08 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.7305 | 2.2194 | TA325 | 157/2 | Completed
2025-03-08 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.0448 | 4.005 | TA325 | 267A/2 | Completed
2025-03-08 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 129.341 | 9.2386 | TA325 | 143A/2 | Completed
2025-03-08 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.4589 | 6.5765 | TA325 | 143A/5 | Completed
2025-03-08 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.4524 | 10.7789 | TA325 | 143A/3 | Completed
2025-03-08 | 2025-03-06 | 2025-03-10 | Jwala | 36.0448 | 7.209 | TA325 | 272A/7 | Completed
2025-03-08 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.7305 | 4.1923 | TA325 | 249/2 | Completed
2025-03-08 | 2025-03-02 | 2025-03-10 | Mjr | 37.7305 | 4.1923 | TA325 | 143A/4 | Completed
2025-03-08 | 2025-02-26 | 2025-03-22 | Modina India | 82.2388 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-08 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.7305 | 2.9023 | TA325 | 148/7 | Completed
2025-03-08 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-08 | 2025-02-21 | 2025-03-18 | Senahul | 77.7181 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-08 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.7282 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-08 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.7305 | 5.3901 | TA325 | 148/6 | Completed
2025-03-08 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-08 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 145A/3 | Completed
2025-03-08 | 2025-03-04 | 2025-03-11 | Thanu Mahto | 36.0448 | 4.5056 | TA325 | 271/3 | Completed
2025-03-09 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.2376 | 3.1408 | TA325 | 270/0 | Completed
2025-03-09 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.7305 | 2.2194 | TA325 | 157/2 | Completed
2025-03-09 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.0448 | 4.005 | TA325 | 267A/2 | Completed
2025-03-09 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 129.341 | 9.2386 | TA325 | 143A/2 | Completed
2025-03-09 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.4589 | 6.5765 | TA325 | 143A/5 | Completed
2025-03-09 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.4524 | 10.7789 | TA325 | 143A/3 | Completed
2025-03-09 | 2025-03-06 | 2025-03-10 | Jwala | 36.0448 | 7.209 | TA325 | 272A/7 | Completed
2025-03-09 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.7305 | 4.1923 | TA325 | 249/2 | Completed
2025-03-09 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.7305 | 1.8865 | TA325 | 270/4 | Completed
2025-03-09 | 2025-03-02 | 2025-03-10 | Mjr | 37.7305 | 4.1923 | TA325 | 143A/4 | Completed
2025-03-09 | 2025-02-26 | 2025-03-22 | Modina India | 82.2388 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-09 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.7305 | 2.9023 | TA325 | 148/7 | Completed
2025-03-09 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-09 | 2025-02-21 | 2025-03-18 | Senahul | 77.7181 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-09 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.7282 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-09 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.7305 | 5.3901 | TA325 | 148/6 | Completed
2025-03-09 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-09 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 145A/3 | Completed
2025-03-09 | 2025-03-04 | 2025-03-11 | Thanu Mahto | 36.0448 | 4.5056 | TA325 | 271/3 | Completed
2025-03-10 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.2376 | 3.1408 | TA325 | 270/0 | Completed
2025-03-10 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.7305 | 2.2194 | TA325 | 157/2 | Completed
2025-03-10 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.0448 | 4.005 | TA325 | 267A/2 | Completed
2025-03-10 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 129.341 | 9.2386 | TA325 | 143A/2 | Completed
2025-03-10 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.4589 | 6.5765 | TA325 | 143A/5 | Completed
2025-03-10 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.4524 | 10.7789 | TA325 | 143A/3 | Completed
2025-03-10 | 2025-03-06 | 2025-03-10 | Jwala | 36.0448 | 7.209 | TA325 | 272A/7 | Completed
2025-03-10 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.7305 | 4.1923 | TA325 | 249/3 | Completed
2025-03-10 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.7305 | 1.8865 | TA325 | 270/4 | Completed
2025-03-10 | 2025-03-02 | 2025-03-10 | Mjr | 37.7305 | 4.1923 | TA325 | 143A/4 | Completed
2025-03-10 | 2025-02-26 | 2025-03-22 | Modina India | 82.2388 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-10 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.7305 | 2.9023 | TA325 | 148/7 | Completed
2025-03-10 | 2025-02-21 | 2025-03-18 | Senahul | 77.7181 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-10 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-03-10 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-10 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 145A/3 | Completed
2025-03-10 | 2025-03-04 | 2025-03-11 | Thanu Mahto | 36.0448 | 4.5056 | TA325 | 271/3 | Completed
2025-03-11 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.2376 | 3.1408 | TA325 | 270/0 | Completed
2025-03-11 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.7305 | 2.2194 | TA325 | 157/2 | Completed
2025-03-11 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.0448 | 4.005 | TA325 | 267A/2 | Completed
2025-03-11 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 129.341 | 9.2386 | TA325 | 143A/2 | Completed
2025-03-11 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.4524 | 10.7789 | TA325 | 143A/3 | Completed
2025-03-11 | 2025-03-11 | 2025-03-16 | Jwala | 39.4589 | 6.5765 | TA325 | 272A/5 | Completed
2025-03-11 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.7305 | 4.1923 | TA325 | 249/3 | Completed
2025-03-11 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.7305 | 1.8865 | TA325 | 270/4 | Completed
2025-03-11 | 2025-02-26 | 2025-03-22 | Modina India | 82.2388 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-11 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.7305 | 2.9023 | TA325 | 148/7 | Completed
2025-03-11 | 2025-02-21 | 2025-03-18 | Senahul | 77.7181 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-11 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-03-11 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-11 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 145A/3 | Completed
2025-03-11 | 2025-03-04 | 2025-03-11 | Thanu Mahto | 36.0448 | 4.5056 | TA325 | 271/3 | Completed
2025-03-12 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.2376 | 3.1408 | TA325 | 270/0 | Completed
2025-03-12 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.0448 | 4.005 | TA325 | 267A/2 | Completed
2025-03-12 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 129.341 | 9.2386 | TA325 | 143A/2 | Completed
2025-03-12 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.7181 | 7.0653 | TA325 | 146/0 | Completed
2025-03-12 | 2025-03-11 | 2025-03-16 | Jwala | 39.4589 | 6.5765 | TA325 | 272A/5 | Completed
2025-03-12 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.7305 | 4.1923 | TA325 | 249/3 | Completed
2025-03-12 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.7305 | 1.8865 | TA325 | 270/4 | Completed
2025-03-12 | 2025-02-26 | 2025-03-22 | Modina India | 82.2388 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-12 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.7305 | 2.9023 | TA325 | 148/7 | Completed
2025-03-12 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.4077 | 5.9005 | TA325 | 157/0 | Completed
2025-03-12 | 2025-02-21 | 2025-03-18 | Senahul | 77.7181 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-12 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-03-12 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-12 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 145A/3 | Completed
2025-03-13 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.2376 | 3.1408 | TA325 | 270/0 | Completed
2025-03-13 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.0448 | 4.005 | TA325 | 267A/2 | Completed
2025-03-13 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 129.341 | 9.2386 | TA325 | 143A/2 | Completed
2025-03-13 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.7181 | 7.0653 | TA325 | 146/0 | Completed
2025-03-13 | 2025-03-11 | 2025-03-16 | Jwala | 39.4589 | 6.5765 | TA325 | 272A/5 | Completed
2025-03-13 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.7305 | 4.1923 | TA325 | 249/3 | Completed
2025-03-13 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.7305 | 1.8865 | TA325 | 270/4 | Completed
2025-03-13 | 2025-02-26 | 2025-03-22 | Modina India | 82.2388 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-13 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.7305 | 2.9023 | TA325 | 148/7 | Completed
2025-03-13 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.4077 | 5.9005 | TA325 | 157/0 | Completed
2025-03-13 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.0448 | 6.0075 | TA325 | 158/2 | Completed
2025-03-13 | 2025-02-21 | 2025-03-18 | Senahul | 77.7181 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-13 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-03-13 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-13 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 145A/3 | Completed
2025-03-14 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.2376 | 3.1408 | TA325 | 270/0 | Completed
2025-03-14 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.0448 | 4.005 | TA325 | 267A/2 | Completed
2025-03-14 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 129.341 | 9.2386 | TA325 | 143A/2 | Completed
2025-03-14 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-03-14 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.7181 | 7.0653 | TA325 | 146/0 | Completed
2025-03-14 | 2025-03-11 | 2025-03-16 | Jwala | 39.4589 | 6.5765 | TA325 | 272A/5 | Completed
2025-03-14 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.7305 | 4.1923 | TA325 | 249/3 | Completed
2025-03-14 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.7305 | 1.8865 | TA325 | 270/4 | Completed
2025-03-14 | 2025-02-26 | 2025-03-22 | Modina India | 82.2388 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-14 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.7305 | 2.9023 | TA325 | 148/7 | Completed
2025-03-14 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.4077 | 5.9005 | TA325 | 157/0 | Completed
2025-03-14 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.0448 | 6.0075 | TA325 | 158/2 | Completed
2025-03-14 | 2025-02-21 | 2025-03-18 | Senahul | 77.7181 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-14 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-03-14 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-14 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 145A/3 | Completed
2025-03-15 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.2376 | 3.1408 | TA325 | 270/0 | Completed
2025-03-15 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.0448 | 4.005 | TA325 | 155/6 | Completed
2025-03-15 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.0448 | 4.005 | TA325 | 267A/2 | Completed
2025-03-15 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 129.341 | 9.2386 | TA325 | 143A/2 | Completed
2025-03-15 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-03-15 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.7181 | 7.0653 | TA325 | 146/0 | Completed
2025-03-15 | 2025-03-11 | 2025-03-16 | Jwala | 39.4589 | 6.5765 | TA325 | 272A/5 | Completed
2025-03-15 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.7305 | 4.1923 | TA325 | 249/3 | Completed
2025-03-15 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.7305 | 1.8865 | TA325 | 270/4 | Completed
2025-03-15 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-15 | 2025-02-26 | 2025-03-22 | Modina India | 82.2388 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-15 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.7305 | 2.9023 | TA325 | 148/7 | Completed
2025-03-15 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.4077 | 5.9005 | TA325 | 157/0 | Completed
2025-03-15 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.0448 | 6.0075 | TA325 | 158/2 | Completed
2025-03-15 | 2025-02-21 | 2025-03-18 | Senahul | 77.7181 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-15 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-03-15 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-15 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 145A/3 | Completed
2025-03-16 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.2376 | 3.1408 | TA325 | 270/0 | Completed
2025-03-16 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.0448 | 4.005 | TA325 | 155/6 | Completed
2025-03-16 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 129.341 | 9.2386 | TA325 | 143A/2 | Completed
2025-03-16 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-03-16 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.7181 | 7.0653 | TA325 | 146/0 | Completed
2025-03-16 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.4178 | 10.8836 | TA325 | 152A/0 | Completed
2025-03-16 | 2025-03-11 | 2025-03-16 | Jwala | 39.4589 | 6.5765 | TA325 | 272A/5 | Completed
2025-03-16 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.7305 | 4.1923 | TA325 | 249/3 | Completed
2025-03-16 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.7305 | 1.8865 | TA325 | 270/4 | Completed
2025-03-16 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-16 | 2025-02-26 | 2025-03-22 | Modina India | 82.2388 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-16 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.7305 | 2.9023 | TA325 | 148/7 | Completed
2025-03-16 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.4077 | 5.9005 | TA325 | 157/0 | Completed
2025-03-16 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.0448 | 6.0075 | TA325 | 158/2 | Completed
2025-03-16 | 2025-02-21 | 2025-03-18 | Senahul | 77.7181 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-16 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-03-16 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-16 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 145A/3 | Completed
2025-03-17 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.0448 | 4.005 | TA325 | 155/6 | Completed
2025-03-17 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 129.341 | 9.2386 | TA325 | 143A/2 | Completed
2025-03-17 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-03-17 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.7181 | 7.0653 | TA325 | 146/0 | Completed
2025-03-17 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.4178 | 10.8836 | TA325 | 152A/0 | Completed
2025-03-17 | 2025-03-17 | 2025-03-20 | Jwala | 37.7305 | 9.4326 | TA325 | 272A/4 | Completed
2025-03-17 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.7305 | 4.1923 | TA325 | 249/3 | Completed
2025-03-17 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.7305 | 1.8865 | TA325 | 270/4 | Completed
2025-03-17 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-17 | 2025-02-26 | 2025-03-22 | Modina India | 82.2388 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-17 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.7305 | 2.9023 | TA325 | 148/7 | Completed
2025-03-17 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.4077 | 5.9005 | TA325 | 157/0 | Completed
2025-03-17 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.0448 | 6.0075 | TA325 | 158/2 | Completed
2025-03-17 | 2025-02-21 | 2025-03-18 | Senahul | 77.7181 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-17 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-03-17 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.7305 | 3.43 | TA325 | 149/1 | Completed
2025-03-17 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-18 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.9336 | 3.9173 | TA325 | 252/0 | Completed
2025-03-18 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.0448 | 4.005 | TA325 | 155/6 | Completed
2025-03-18 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-03-18 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.7181 | 7.0653 | TA325 | 146/0 | Completed
2025-03-18 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.4178 | 10.8836 | TA325 | 152A/0 | Completed
2025-03-18 | 2025-03-17 | 2025-03-20 | Jwala | 37.7305 | 9.4326 | TA325 | 272A/4 | Completed
2025-03-18 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.7305 | 4.1923 | TA325 | 249/3 | Completed
2025-03-18 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.7305 | 1.8865 | TA325 | 270/4 | Completed
2025-03-18 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-18 | 2025-02-26 | 2025-03-22 | Modina India | 82.2388 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-18 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.7305 | 2.9023 | TA325 | 148/7 | Completed
2025-03-18 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.4077 | 5.9005 | TA325 | 157/0 | Completed
2025-03-18 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.0448 | 6.0075 | TA325 | 158/2 | Completed
2025-03-18 | 2025-02-21 | 2025-03-18 | Senahul | 77.7181 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-18 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-03-18 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.7305 | 3.43 | TA325 | 149/1 | Completed
2025-03-18 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.4589 | 7.8918 | TA325 | 150/2 | Completed
2025-03-18 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-19 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.9336 | 3.9173 | TA325 | 252/0 | Completed
2025-03-19 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.0448 | 4.005 | TA325 | 155/6 | Completed
2025-03-19 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.4589 | 3.2882 | TA325 | 272/6 | Completed
2025-03-19 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-03-19 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.7181 | 7.0653 | TA325 | 146/0 | Completed
2025-03-19 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.4178 | 10.8836 | TA325 | 152A/0 | Completed
2025-03-19 | 2025-03-17 | 2025-03-20 | Jwala | 37.7305 | 9.4326 | TA325 | 272A/4 | Completed
2025-03-19 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.7305 | 1.8865 | TA325 | 270/4 | Completed
2025-03-19 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-19 | 2025-02-26 | 2025-03-22 | Modina India | 82.2388 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-19 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.7305 | 2.9023 | TA325 | 148/7 | Completed
2025-03-19 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.4077 | 5.9005 | TA325 | 157/0 | Completed
2025-03-19 | 2025-03-19 | 2025-04-01 | Rupesh | 44.7282 | 3.1949 | TA325 | 150/3 | Completed
2025-03-19 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-03-19 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.7305 | 3.43 | TA325 | 149/1 | Completed
2025-03-19 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.4589 | 7.8918 | TA325 | 150/2 | Completed
2025-03-19 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-19 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.4589 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-19 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.0448 | 3.6045 | TA325 | 270/3 | Completed
2025-03-20 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.9336 | 3.9173 | TA325 | 252/0 | Completed
2025-03-20 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.0448 | 4.005 | TA325 | 155/6 | Completed
2025-03-20 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.4589 | 3.2882 | TA325 | 272/6 | Completed
2025-03-20 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-03-20 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.7181 | 7.0653 | TA325 | 146/0 | Completed
2025-03-20 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.4178 | 10.8836 | TA325 | 152A/0 | Completed
2025-03-20 | 2025-03-17 | 2025-03-20 | Jwala | 37.7305 | 9.4326 | TA325 | 272A/4 | Completed
2025-03-20 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.7305 | 1.8865 | TA325 | 270/4 | Completed
2025-03-20 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-20 | 2025-03-20 | 2025-04-06 | Mjr | 46.6235 | 2.5902 | TA325 | 150/1 | Completed
2025-03-20 | 2025-02-26 | 2025-03-22 | Modina India | 82.2388 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-20 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.7305 | 2.9023 | TA325 | 148/7 | Completed
2025-03-20 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.4077 | 5.9005 | TA325 | 157/0 | Completed
2025-03-20 | 2025-03-19 | 2025-04-01 | Rupesh | 44.7282 | 3.1949 | TA325 | 150/3 | Completed
2025-03-20 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-03-20 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.7305 | 3.43 | TA325 | 149/1 | Completed
2025-03-20 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.4589 | 7.8918 | TA325 | 150/2 | Completed
2025-03-20 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-20 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.4589 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-20 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.0448 | 3.6045 | TA325 | 270/3 | Completed
2025-03-21 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.9336 | 3.9173 | TA325 | 252/0 | Completed
2025-03-21 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.0448 | 4.005 | TA325 | 155/6 | Completed
2025-03-21 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.4589 | 3.2882 | TA325 | 272/6 | Completed
2025-03-21 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-03-21 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.7181 | 7.0653 | TA325 | 146/0 | Completed
2025-03-21 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.8632 | 8.1233 | TA325 | 151/0 | Completed
2025-03-21 | 2025-03-21 | 2025-03-25 | Jwala | 36.0448 | 7.209 | TA325 | 271/1 | Completed
2025-03-21 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-21 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.7305 | 1.8865 | TA325 | 270/4 | Completed
2025-03-21 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-21 | 2025-03-20 | 2025-04-06 | Mjr | 46.6235 | 2.5902 | TA325 | 150/1 | Completed
2025-03-21 | 2025-02-26 | 2025-03-22 | Modina India | 82.2388 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-21 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.4077 | 5.9005 | TA325 | 157/0 | Completed
2025-03-21 | 2025-03-19 | 2025-04-01 | Rupesh | 44.7282 | 3.1949 | TA325 | 150/3 | Completed
2025-03-21 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-03-21 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.7305 | 3.43 | TA325 | 149/1 | Completed
2025-03-21 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.4589 | 7.8918 | TA325 | 150/2 | Completed
2025-03-21 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-21 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.4589 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-21 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.0448 | 3.6045 | TA325 | 270/3 | Completed
2025-03-22 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.9336 | 3.9173 | TA325 | 252/0 | Completed
2025-03-22 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.0448 | 4.005 | TA325 | 155/6 | Completed
2025-03-22 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.4589 | 3.2882 | TA325 | 272/6 | Completed
2025-03-22 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.8356 | 9.8836 | TA325 | 150/0 | Completed
2025-03-22 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-03-22 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.7181 | 7.0653 | TA325 | 146/0 | Completed
2025-03-22 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.8632 | 8.1233 | TA325 | 151/0 | Completed
2025-03-22 | 2025-03-21 | 2025-03-25 | Jwala | 36.0448 | 7.209 | TA325 | 271/1 | Completed
2025-03-22 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-22 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.7305 | 1.8865 | TA325 | 270/4 | Completed
2025-03-22 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-22 | 2025-03-20 | 2025-04-06 | Mjr | 46.6235 | 2.5902 | TA325 | 150/1 | Completed
2025-03-22 | 2025-02-26 | 2025-03-22 | Modina India | 82.2388 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-22 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.4077 | 5.9005 | TA325 | 157/0 | Completed
2025-03-22 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.2993 | 12.0428 | TA325 | 156/0 | Completed
2025-03-22 | 2025-03-19 | 2025-04-01 | Rupesh | 44.7282 | 3.1949 | TA325 | 150/3 | Completed
2025-03-22 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-03-22 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.7305 | 3.43 | TA325 | 149/1 | Completed
2025-03-22 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.4589 | 7.8918 | TA325 | 150/2 | Completed
2025-03-22 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-22 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.4589 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-22 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.0448 | 3.6045 | TA325 | 270/3 | Completed
2025-03-23 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.9336 | 3.9173 | TA325 | 252/0 | Completed
2025-03-23 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.0448 | 4.005 | TA325 | 155/6 | Completed
2025-03-23 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.4589 | 3.2882 | TA325 | 272/6 | Completed
2025-03-23 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.8356 | 9.8836 | TA325 | 150/0 | Completed
2025-03-23 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-03-23 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.8632 | 8.1233 | TA325 | 151/0 | Completed
2025-03-23 | 2025-03-21 | 2025-03-25 | Jwala | 36.0448 | 7.209 | TA325 | 271/1 | Completed
2025-03-23 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-23 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.7305 | 1.8865 | TA325 | 270/4 | Completed
2025-03-23 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-23 | 2025-03-20 | 2025-04-06 | Mjr | 46.6235 | 2.5902 | TA325 | 150/1 | Completed
2025-03-23 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.4077 | 5.9005 | TA325 | 157/0 | Completed
2025-03-23 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.2993 | 12.0428 | TA325 | 156/0 | Completed
2025-03-23 | 2025-03-19 | 2025-04-01 | Rupesh | 44.7282 | 3.1949 | TA325 | 150/3 | Completed
2025-03-23 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-03-23 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.7305 | 3.43 | TA325 | 149/1 | Completed
2025-03-23 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-23 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.4589 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-23 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.0448 | 3.6045 | TA325 | 270/3 | Completed
2025-03-24 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.9336 | 3.9173 | TA325 | 252/0 | Completed
2025-03-24 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.4589 | 3.2882 | TA325 | 272/6 | Completed
2025-03-24 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.8356 | 9.8836 | TA325 | 150/0 | Completed
2025-03-24 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-03-24 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.7181 | 8.6353 | TA325 | 147/0 | Completed
2025-03-24 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.8632 | 8.1233 | TA325 | 151/0 | Completed
2025-03-24 | 2025-03-21 | 2025-03-25 | Jwala | 36.0448 | 7.209 | TA325 | 271/1 | Completed
2025-03-24 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-24 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.7305 | 1.8865 | TA325 | 270/4 | Completed
2025-03-24 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-24 | 2025-03-20 | 2025-04-06 | Mjr | 46.6235 | 2.5902 | TA325 | 150/1 | Completed
2025-03-24 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.4077 | 5.9005 | TA325 | 157/0 | Completed
2025-03-24 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.2993 | 12.0428 | TA325 | 156/0 | Completed
2025-03-24 | 2025-03-19 | 2025-04-01 | Rupesh | 44.7282 | 3.1949 | TA325 | 150/3 | Completed
2025-03-24 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-03-24 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.7305 | 3.43 | TA325 | 149/1 | Completed
2025-03-24 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-24 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.4589 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-24 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.0448 | 3.6045 | TA325 | 270/3 | Completed
2025-03-25 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.9336 | 3.9173 | TA325 | 252/0 | Completed
2025-03-25 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.4589 | 3.2882 | TA325 | 272/6 | Completed
2025-03-25 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.8356 | 9.8836 | TA325 | 150/0 | Completed
2025-03-25 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-03-25 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.7181 | 8.6353 | TA325 | 147/0 | Completed
2025-03-25 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.8632 | 8.1233 | TA325 | 151/0 | Completed
2025-03-25 | 2025-03-21 | 2025-03-25 | Jwala | 36.0448 | 7.209 | TA325 | 271/1 | Completed
2025-03-25 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-25 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.7305 | 1.8865 | TA325 | 270/4 | Completed
2025-03-25 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-25 | 2025-03-20 | 2025-04-06 | Mjr | 46.6235 | 2.5902 | TA325 | 150/1 | Completed
2025-03-25 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.4077 | 5.9005 | TA325 | 157/0 | Completed
2025-03-25 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.2538 | 3.5697 | TA325 | 150A/0 | Completed
2025-03-25 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.2993 | 12.0428 | TA325 | 156/0 | Completed
2025-03-25 | 2025-03-19 | 2025-04-01 | Rupesh | 44.7282 | 3.1949 | TA325 | 150/3 | Completed
2025-03-25 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-03-25 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.7305 | 3.43 | TA325 | 149/1 | Completed
2025-03-25 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-25 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.4589 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-25 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.0448 | 3.6045 | TA325 | 270/3 | Completed
2025-03-26 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.9336 | 3.9173 | TA325 | 252/0 | Completed
2025-03-26 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.7305 | 4.1923 | TA325 | 155/1 | Completed
2025-03-26 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.4589 | 3.2882 | TA325 | 272/6 | Completed
2025-03-26 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.8356 | 9.8836 | TA325 | 150/0 | Completed
2025-03-26 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-03-26 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.7181 | 8.6353 | TA325 | 147/0 | Completed
2025-03-26 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.8632 | 8.1233 | TA325 | 151/0 | Completed
2025-03-26 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed
2025-03-26 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-26 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.7305 | 1.8865 | TA325 | 270/4 | Completed
2025-03-26 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-26 | 2025-03-20 | 2025-04-06 | Mjr | 46.6235 | 2.5902 | TA325 | 150/1 | Completed
2025-03-26 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.4077 | 5.9005 | TA325 | 157/0 | Completed
2025-03-26 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.2538 | 3.5697 | TA325 | 150A/0 | Completed
2025-03-26 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.2993 | 12.0428 | TA325 | 156/0 | Completed
2025-03-26 | 2025-03-19 | 2025-04-01 | Rupesh | 44.7282 | 3.1949 | TA325 | 150/3 | Completed
2025-03-26 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-03-26 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.7305 | 3.43 | TA325 | 149/1 | Completed
2025-03-26 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-26 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.4589 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-26 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.0448 | 3.6045 | TA325 | 270/3 | Completed
2025-03-27 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.9336 | 3.9173 | TA325 | 252/0 | Completed
2025-03-27 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.7305 | 4.1923 | TA325 | 155/1 | Completed
2025-03-27 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.4589 | 3.2882 | TA325 | 272/6 | Completed
2025-03-27 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.8356 | 9.8836 | TA325 | 150/0 | Completed
2025-03-27 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-03-27 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.7181 | 8.6353 | TA325 | 147/0 | Completed
2025-03-27 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.8632 | 8.1233 | TA325 | 151/0 | Completed
2025-03-27 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed
2025-03-27 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-27 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.7305 | 1.8865 | TA325 | 270/4 | Completed
2025-03-27 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-27 | 2025-03-20 | 2025-04-06 | Mjr | 46.6235 | 2.5902 | TA325 | 150/1 | Completed
2025-03-27 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.4077 | 5.9005 | TA325 | 157/0 | Completed
2025-03-27 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.2538 | 3.5697 | TA325 | 150A/0 | Completed
2025-03-27 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.2993 | 12.0428 | TA325 | 156/0 | Completed
2025-03-27 | 2025-03-19 | 2025-04-01 | Rupesh | 44.7282 | 3.1949 | TA325 | 150/3 | Completed
2025-03-27 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-03-27 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.7305 | 3.43 | TA325 | 149/1 | Completed
2025-03-27 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-27 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.4589 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-27 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.0448 | 3.6045 | TA325 | 270/3 | Completed
2025-03-28 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.9336 | 3.9173 | TA325 | 252/0 | Completed
2025-03-28 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.7305 | 4.1923 | TA325 | 155/1 | Completed
2025-03-28 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.7282 | 4.4728 | TA325 | 167/3 | Completed
2025-03-28 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.4589 | 3.2882 | TA325 | 272/6 | Completed
2025-03-28 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.8356 | 9.8836 | TA325 | 150/0 | Completed
2025-03-28 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-03-28 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.7181 | 8.6353 | TA325 | 147/0 | Completed
2025-03-28 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed
2025-03-28 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-28 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.7305 | 1.8865 | TA325 | 270/4 | Completed
2025-03-28 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-28 | 2025-03-20 | 2025-04-06 | Mjr | 46.6235 | 2.5902 | TA325 | 150/1 | Completed
2025-03-28 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.2538 | 3.5697 | TA325 | 150A/0 | Completed
2025-03-28 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.2993 | 12.0428 | TA325 | 156/0 | Completed
2025-03-28 | 2025-03-19 | 2025-04-01 | Rupesh | 44.7282 | 3.1949 | TA325 | 150/3 | Completed
2025-03-28 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-03-28 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-28 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.0448 | 3.6045 | TA325 | 270/3 | Completed
2025-03-29 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.9336 | 3.9173 | TA325 | 252/0 | Completed
2025-03-29 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.7305 | 4.1923 | TA325 | 155/1 | Completed
2025-03-29 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.7282 | 4.4728 | TA325 | 167/3 | Completed
2025-03-29 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.4589 | 3.2882 | TA325 | 272/6 | Completed
2025-03-29 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.8356 | 9.8836 | TA325 | 150/0 | Completed
2025-03-29 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-03-29 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.7181 | 8.6353 | TA325 | 147/0 | Completed
2025-03-29 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed
2025-03-29 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-29 | 2025-03-20 | 2025-04-06 | Mjr | 46.6235 | 2.5902 | TA325 | 150/1 | Completed
2025-03-29 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.2538 | 3.5697 | TA325 | 150A/0 | Completed
2025-03-29 | 2025-03-19 | 2025-04-01 | Rupesh | 44.7282 | 3.1949 | TA325 | 150/3 | Completed
2025-03-29 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-03-29 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-30 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.9336 | 3.9173 | TA325 | 252/0 | Completed
2025-03-30 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.7305 | 4.1923 | TA325 | 155/1 | Completed
2025-03-30 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.7282 | 4.4728 | TA325 | 167/3 | Completed
2025-03-30 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.4589 | 3.2882 | TA325 | 272/6 | Completed
2025-03-30 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.8356 | 9.8836 | TA325 | 150/0 | Completed
2025-03-30 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-03-30 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.7181 | 8.6353 | TA325 | 147/0 | Completed
2025-03-30 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed
2025-03-30 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-30 | 2025-03-20 | 2025-04-06 | Mjr | 46.6235 | 2.5902 | TA325 | 150/1 | Completed
2025-03-30 | 2025-03-30 | 2025-04-08 | Modina India | 37.7305 | 3.773 | TA325 | 195A/3 | Completed
2025-03-30 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.2538 | 3.5697 | TA325 | 150A/0 | Completed
2025-03-30 | 2025-03-19 | 2025-04-01 | Rupesh | 44.7282 | 3.1949 | TA325 | 150/3 | Completed
2025-03-30 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-03-31 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.9336 | 3.9173 | TA325 | 252/0 | Completed
2025-03-31 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.7305 | 4.1923 | TA325 | 155/1 | Completed
2025-03-31 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.7282 | 4.4728 | TA325 | 167/3 | Completed
2025-03-31 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.8356 | 9.8836 | TA325 | 150/0 | Completed
2025-03-31 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-03-31 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.7181 | 8.6353 | TA325 | 147/0 | Completed
2025-03-31 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed
2025-03-31 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-31 | 2025-03-20 | 2025-04-06 | Mjr | 46.6235 | 2.5902 | TA325 | 150/1 | Completed
2025-03-31 | 2025-03-30 | 2025-04-08 | Modina India | 37.7305 | 3.773 | TA325 | 195A/3 | Completed
2025-03-31 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.2538 | 3.5697 | TA325 | 150A/0 | Completed
2025-03-31 | 2025-03-19 | 2025-04-01 | Rupesh | 44.7282 | 3.1949 | TA325 | 150/3 | Completed
2025-03-31 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-04-01 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.9336 | 3.9173 | TA325 | 252/0 | Completed
2025-04-01 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.7305 | 4.1923 | TA325 | 155/1 | Completed
2025-04-01 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.7282 | 4.4728 | TA325 | 167/3 | Completed
2025-04-01 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-01 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.7181 | 8.6353 | TA325 | 147/0 | Completed
2025-04-01 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed
2025-04-01 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-01 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.7305 | 3.1442 | TA325 | 197/1 | Completed
2025-04-01 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.2538 | 4.2836 | TA325 | 198/0 | Completed
2025-04-01 | 2025-03-20 | 2025-04-06 | Mjr | 46.6235 | 2.5902 | TA325 | 150/1 | Completed
2025-04-01 | 2025-03-30 | 2025-04-08 | Modina India | 37.7305 | 3.773 | TA325 | 195A/3 | Completed
2025-04-01 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.2538 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-01 | 2025-03-19 | 2025-04-01 | Rupesh | 44.7282 | 3.1949 | TA325 | 150/3 | Completed
2025-04-01 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-04-01 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.7305 | 4.7163 | TA325 | 195/2 | Completed
2025-04-01 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.7305 | 3.1442 | TA325 | 248/5 | Completed
2025-04-02 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.9336 | 3.9173 | TA325 | 252/0 | Completed
2025-04-02 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.7305 | 4.1923 | TA325 | 155/1 | Completed
2025-04-02 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.7282 | 4.4728 | TA325 | 167/3 | Completed
2025-04-02 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-02 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-02 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.7305 | 3.1442 | TA325 | 197/1 | Completed
2025-04-02 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.2538 | 4.2836 | TA325 | 198/0 | Completed
2025-04-02 | 2025-03-20 | 2025-04-06 | Mjr | 46.6235 | 2.5902 | TA325 | 150/1 | Completed
2025-04-02 | 2025-03-30 | 2025-04-08 | Modina India | 37.7305 | 3.773 | TA325 | 195A/3 | Completed
2025-04-02 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.2538 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-02 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.4178 | 6.0464 | TA325 | 158/0 | Completed
2025-04-02 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-02 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-04-02 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.7305 | 4.7163 | TA325 | 195/2 | Completed
2025-04-02 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-02 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.7305 | 3.1442 | TA325 | 248/5 | Completed
2025-04-03 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.9336 | 3.9173 | TA325 | 252/0 | Completed
2025-04-03 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.7305 | 4.1923 | TA325 | 155/1 | Completed
2025-04-03 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.7282 | 4.4728 | TA325 | 167/3 | Completed
2025-04-03 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-03 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-03 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.7305 | 3.1442 | TA325 | 197/1 | Completed
2025-04-03 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.2538 | 4.2836 | TA325 | 198/0 | Completed
2025-04-03 | 2025-03-20 | 2025-04-06 | Mjr | 46.6235 | 2.5902 | TA325 | 150/1 | Completed
2025-04-03 | 2025-03-30 | 2025-04-08 | Modina India | 37.7305 | 3.773 | TA325 | 195A/3 | Completed
2025-04-03 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.2538 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-03 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.4178 | 6.0464 | TA325 | 158/0 | Completed
2025-04-03 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-03 | 2025-04-03 | 2025-04-26 | Senahul | 82.2388 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-03 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-04-03 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.7305 | 4.7163 | TA325 | 195/2 | Completed
2025-04-03 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-03 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.7305 | 3.1442 | TA325 | 248/5 | Completed
2025-04-03 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.4589 | 3.9459 | TA325 | 187/1 | Completed
2025-04-04 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.9336 | 3.9173 | TA325 | 252/0 | Completed
2025-04-04 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.7282 | 4.4728 | TA325 | 167/3 | Completed
2025-04-04 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.7305 | 4.1923 | TA325 | 198/2 | Completed
2025-04-04 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-04 | 2025-04-04 | 2025-04-09 | Jwala | 44.7282 | 7.4547 | TA325 | 273/1 | Completed
2025-04-04 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-04 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.7305 | 3.1442 | TA325 | 197/1 | Completed
2025-04-04 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.2538 | 4.2836 | TA325 | 198/0 | Completed
2025-04-04 | 2025-03-20 | 2025-04-06 | Mjr | 46.6235 | 2.5902 | TA325 | 150/1 | Completed
2025-04-04 | 2025-03-30 | 2025-04-08 | Modina India | 37.7305 | 3.773 | TA325 | 195A/3 | Completed
2025-04-04 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.2538 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-04 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.4178 | 6.0464 | TA325 | 158/0 | Completed
2025-04-04 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-04 | 2025-04-03 | 2025-04-26 | Senahul | 82.2388 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-04 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-04-04 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.7305 | 4.7163 | TA325 | 195/2 | Completed
2025-04-04 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-04 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.7305 | 3.1442 | TA325 | 248/5 | Completed
2025-04-04 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.4589 | 3.9459 | TA325 | 187/1 | Completed
2025-04-05 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.9336 | 3.9173 | TA325 | 252/0 | Completed
2025-04-05 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.7282 | 4.4728 | TA325 | 167/3 | Completed
2025-04-05 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.7305 | 4.1923 | TA325 | 198/2 | Completed
2025-04-05 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.7305 | 5.3901 | TA325 | 189/1 | Completed
2025-04-05 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-05 | 2025-04-04 | 2025-04-09 | Jwala | 44.7282 | 7.4547 | TA325 | 273/1 | Completed
2025-04-05 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-05 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.7305 | 3.1442 | TA325 | 197/1 | Completed
2025-04-05 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.2538 | 4.2836 | TA325 | 198/0 | Completed
2025-04-05 | 2025-03-20 | 2025-04-06 | Mjr | 46.6235 | 2.5902 | TA325 | 150/1 | Completed
2025-04-05 | 2025-03-30 | 2025-04-08 | Modina India | 37.7305 | 3.773 | TA325 | 195A/3 | Completed
2025-04-05 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.2538 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-05 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.4178 | 6.0464 | TA325 | 158/0 | Completed
2025-04-05 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-05 | 2025-04-03 | 2025-04-26 | Senahul | 82.2388 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-05 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-04-05 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.7305 | 4.7163 | TA325 | 195/2 | Completed
2025-04-05 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-05 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.7305 | 3.1442 | TA325 | 248/5 | Completed
2025-04-05 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.4589 | 3.9459 | TA325 | 187/1 | Completed
2025-04-06 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.9336 | 3.9173 | TA325 | 252/0 | Completed
2025-04-06 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.7282 | 4.4728 | TA325 | 167/3 | Completed
2025-04-06 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.7305 | 4.1923 | TA325 | 198/2 | Completed
2025-04-06 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.7305 | 5.3901 | TA325 | 189/1 | Completed
2025-04-06 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-06 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.4236 | 5.1102 | TA325 | 181/0 | Completed
2025-04-06 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.4077 | 11.801 | TA325 | 178/0 | Completed
2025-04-06 | 2025-04-04 | 2025-04-09 | Jwala | 44.7282 | 7.4547 | TA325 | 273/1 | Completed
2025-04-06 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-06 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.7305 | 3.1442 | TA325 | 197/1 | Completed
2025-04-06 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.2538 | 4.2836 | TA325 | 198/0 | Completed
2025-04-06 | 2025-03-20 | 2025-04-06 | Mjr | 46.6235 | 2.5902 | TA325 | 150/1 | Completed
2025-04-06 | 2025-03-30 | 2025-04-08 | Modina India | 37.7305 | 3.773 | TA325 | 195A/3 | Completed
2025-04-06 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.2538 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-06 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.4178 | 6.0464 | TA325 | 158/0 | Completed
2025-04-06 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-06 | 2025-04-06 | 2025-04-16 | Rupesh | 64.2538 | 5.8413 | TA325 | 168/0 | Completed
2025-04-06 | 2025-04-03 | 2025-04-26 | Senahul | 82.2388 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-06 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-04-06 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.7305 | 4.7163 | TA325 | 195/2 | Completed
2025-04-06 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-06 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.7305 | 3.1442 | TA325 | 248/5 | Completed
2025-04-06 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.4589 | 3.9459 | TA325 | 187/1 | Completed
2025-04-07 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.9336 | 3.9173 | TA325 | 252/0 | Completed
2025-04-07 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.0448 | 1.8971 | TA325 | 158/1 | Completed
2025-04-07 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.7305 | 4.1923 | TA325 | 198/2 | Completed
2025-04-07 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.7305 | 5.3901 | TA325 | 189/1 | Completed
2025-04-07 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-07 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.4236 | 5.1102 | TA325 | 181/0 | Completed
2025-04-07 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.4077 | 11.801 | TA325 | 178/0 | Completed
2025-04-07 | 2025-04-04 | 2025-04-09 | Jwala | 44.7282 | 7.4547 | TA325 | 273/1 | Completed
2025-04-07 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-07 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.7305 | 3.1442 | TA325 | 197/1 | Completed
2025-04-07 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.2538 | 4.2836 | TA325 | 198/0 | Completed
2025-04-07 | 2025-03-30 | 2025-04-08 | Modina India | 37.7305 | 3.773 | TA325 | 195A/3 | Completed
2025-04-07 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.2538 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-07 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.4178 | 6.0464 | TA325 | 158/0 | Completed
2025-04-07 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-07 | 2025-04-06 | 2025-04-16 | Rupesh | 64.2538 | 5.8413 | TA325 | 168/0 | Completed
2025-04-07 | 2025-04-03 | 2025-04-26 | Senahul | 82.2388 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-07 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.7305 | 4.7163 | TA325 | 195/2 | Completed
2025-04-07 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-07 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.7305 | 3.1442 | TA325 | 248/5 | Completed
2025-04-07 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.4589 | 3.9459 | TA325 | 187/1 | Completed
2025-04-08 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.9336 | 3.9173 | TA325 | 252/0 | Completed
2025-04-08 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.0448 | 1.8971 | TA325 | 158/1 | Completed
2025-04-08 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.7282 | 4.0662 | TA325 | 167/2 | Completed
2025-04-08 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.7305 | 4.1923 | TA325 | 198/2 | Completed
2025-04-08 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.7305 | 5.3901 | TA325 | 189/1 | Completed
2025-04-08 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-08 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.4236 | 5.1102 | TA325 | 181/0 | Completed
2025-04-08 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.4077 | 11.801 | TA325 | 178/0 | Completed
2025-04-08 | 2025-04-04 | 2025-04-09 | Jwala | 44.7282 | 7.4547 | TA325 | 273/1 | Completed
2025-04-08 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-08 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.7305 | 3.1442 | TA325 | 197/1 | Completed
2025-04-08 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.2538 | 4.2836 | TA325 | 198/0 | Completed
2025-04-08 | 2025-03-30 | 2025-04-08 | Modina India | 37.7305 | 3.773 | TA325 | 195A/3 | Completed
2025-04-08 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.2538 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-08 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.4178 | 6.0464 | TA325 | 158/0 | Completed
2025-04-08 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-08 | 2025-04-06 | 2025-04-16 | Rupesh | 64.2538 | 5.8413 | TA325 | 168/0 | Completed
2025-04-08 | 2025-04-03 | 2025-04-26 | Senahul | 82.2388 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-08 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.7305 | 4.7163 | TA325 | 195/2 | Completed
2025-04-08 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-08 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.7305 | 3.1442 | TA325 | 248/5 | Completed
2025-04-08 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.4589 | 3.9459 | TA325 | 187/1 | Completed
2025-04-09 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.9336 | 3.9173 | TA325 | 252/0 | Completed
2025-04-09 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.0448 | 1.8971 | TA325 | 158/1 | Completed
2025-04-09 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.7282 | 4.0662 | TA325 | 167/2 | Completed
2025-04-09 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.7305 | 4.1923 | TA325 | 198/2 | Completed
2025-04-09 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.7305 | 5.3901 | TA325 | 189/1 | Completed
2025-04-09 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-09 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.4236 | 5.1102 | TA325 | 181/0 | Completed
2025-04-09 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.4077 | 11.801 | TA325 | 178/0 | Completed
2025-04-09 | 2025-04-04 | 2025-04-09 | Jwala | 44.7282 | 7.4547 | TA325 | 273/1 | Completed
2025-04-09 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-09 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.7305 | 3.1442 | TA325 | 197/1 | Completed
2025-04-09 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.2538 | 4.2836 | TA325 | 198/0 | Completed
2025-04-09 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.2538 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-09 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.4178 | 6.0464 | TA325 | 158/0 | Completed
2025-04-09 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-09 | 2025-04-06 | 2025-04-16 | Rupesh | 64.2538 | 5.8413 | TA325 | 168/0 | Completed
2025-04-09 | 2025-04-03 | 2025-04-26 | Senahul | 82.2388 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-09 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.7305 | 5.3901 | TA325 | 195/4 | Completed
2025-04-09 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-09 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.7305 | 3.1442 | TA325 | 248/5 | Completed
2025-04-09 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.4589 | 3.9459 | TA325 | 187/1 | Completed
2025-04-10 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.9336 | 3.9173 | TA325 | 252/0 | Completed
2025-04-10 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.0448 | 1.8971 | TA325 | 158/1 | Completed
2025-04-10 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.7282 | 4.0662 | TA325 | 167/2 | Completed
2025-04-10 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.7305 | 4.1923 | TA325 | 198/2 | Completed
2025-04-10 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.7305 | 5.3901 | TA325 | 189/1 | Completed
2025-04-10 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-10 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.4236 | 5.1102 | TA325 | 181/0 | Completed
2025-04-10 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.4077 | 11.801 | TA325 | 178/0 | Completed
2025-04-10 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-10 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.7305 | 3.1442 | TA325 | 197/1 | Completed
2025-04-10 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.2538 | 4.2836 | TA325 | 198/0 | Completed
2025-04-10 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.2538 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-10 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.4178 | 6.0464 | TA325 | 158/0 | Completed
2025-04-10 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-10 | 2025-04-06 | 2025-04-16 | Rupesh | 64.2538 | 5.8413 | TA325 | 168/0 | Completed
2025-04-10 | 2025-04-03 | 2025-04-26 | Senahul | 82.2388 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-10 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.7305 | 5.3901 | TA325 | 195/4 | Completed
2025-04-10 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-10 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.7305 | 3.1442 | TA325 | 248/5 | Completed
2025-04-10 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.4589 | 3.9459 | TA325 | 187/1 | Completed
2025-04-11 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.9336 | 3.9173 | TA325 | 252/0 | Completed
2025-04-11 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.0448 | 1.8971 | TA325 | 158/1 | Completed
2025-04-11 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.7282 | 4.0662 | TA325 | 167/2 | Completed
2025-04-11 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.7305 | 4.1923 | TA325 | 198/2 | Completed
2025-04-11 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.7305 | 5.3901 | TA325 | 189/1 | Completed
2025-04-11 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-11 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.4236 | 5.1102 | TA325 | 181/0 | Completed
2025-04-11 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.4077 | 11.801 | TA325 | 178/0 | Completed
2025-04-11 | 2025-04-11 | 2025-04-16 | Jwala | 36.0448 | 6.0075 | TA325 | 205/1 | Completed
2025-04-11 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-11 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.7305 | 3.1442 | TA325 | 197/1 | Completed
2025-04-11 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.2538 | 4.2836 | TA325 | 198/0 | Completed
2025-04-11 | 2025-04-11 | 2025-04-22 | Modina India | 44.7282 | 3.7274 | TA325 | 195A/2 | Completed
2025-04-11 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.2538 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-11 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-11 | 2025-04-06 | 2025-04-16 | Rupesh | 64.2538 | 5.8413 | TA325 | 168/0 | Completed
2025-04-11 | 2025-04-03 | 2025-04-26 | Senahul | 82.2388 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-11 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.7305 | 5.3901 | TA325 | 195/4 | Completed
2025-04-11 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-11 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.7305 | 3.1442 | TA325 | 248/5 | Completed
2025-04-11 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.4589 | 3.9459 | TA325 | 187/1 | Completed
2025-04-12 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.0448 | 1.8971 | TA325 | 158/1 | Completed
2025-04-12 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.7282 | 4.0662 | TA325 | 167/2 | Completed
2025-04-12 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.7305 | 4.1923 | TA325 | 198/2 | Completed
2025-04-12 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-12 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.4236 | 5.1102 | TA325 | 181/0 | Completed
2025-04-12 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.4077 | 11.801 | TA325 | 178/0 | Completed
2025-04-12 | 2025-04-11 | 2025-04-16 | Jwala | 36.0448 | 6.0075 | TA325 | 205/1 | Completed
2025-04-12 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-12 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.7305 | 3.1442 | TA325 | 197/1 | Completed
2025-04-12 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.2538 | 4.2836 | TA325 | 198/0 | Completed
2025-04-12 | 2025-04-11 | 2025-04-22 | Modina India | 44.7282 | 3.7274 | TA325 | 195A/2 | Completed
2025-04-12 | 2025-04-06 | 2025-04-16 | Rupesh | 64.2538 | 5.8413 | TA325 | 168/0 | Completed
2025-04-12 | 2025-04-03 | 2025-04-26 | Senahul | 82.2388 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-12 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.7305 | 5.3901 | TA325 | 195/4 | Completed
2025-04-12 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-12 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.7305 | 3.1442 | TA325 | 248/5 | Completed
2025-04-12 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.4589 | 3.9459 | TA325 | 187/1 | Completed
2025-04-13 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.0448 | 1.8971 | TA325 | 158/1 | Completed
2025-04-13 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.7282 | 4.0662 | TA325 | 167/2 | Completed
2025-04-13 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-13 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.4236 | 5.1102 | TA325 | 181/0 | Completed
2025-04-13 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.4077 | 11.801 | TA325 | 178/0 | Completed
2025-04-13 | 2025-04-11 | 2025-04-16 | Jwala | 36.0448 | 6.0075 | TA325 | 205/1 | Completed
2025-04-13 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.2538 | 4.2836 | TA325 | 198/0 | Completed
2025-04-13 | 2025-04-13 | 2025-04-28 | Mjr | 64.2538 | 4.0159 | TA325 | 192/0 | Completed
2025-04-13 | 2025-04-11 | 2025-04-22 | Modina India | 44.7282 | 3.7274 | TA325 | 195A/2 | Completed
2025-04-13 | 2025-04-06 | 2025-04-16 | Rupesh | 64.2538 | 5.8413 | TA325 | 168/0 | Completed
2025-04-13 | 2025-04-03 | 2025-04-26 | Senahul | 82.2388 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-13 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.7305 | 5.3901 | TA325 | 195/4 | Completed
2025-04-13 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.7305 | 3.773 | TA325 | 135/7 | Completed
2025-04-13 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-13 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 249/1 | Completed
2025-04-14 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.7181 | 4.5717 | TA325 | 248/0 | Completed
2025-04-14 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.0448 | 1.8971 | TA325 | 158/1 | Completed
2025-04-14 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.7282 | 4.0662 | TA325 | 167/2 | Completed
2025-04-14 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-14 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.4236 | 5.1102 | TA325 | 181/0 | Completed
2025-04-14 | 2025-04-11 | 2025-04-16 | Jwala | 36.0448 | 6.0075 | TA325 | 205/1 | Completed
2025-04-14 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.2538 | 4.2836 | TA325 | 198/0 | Completed
2025-04-14 | 2025-04-13 | 2025-04-28 | Mjr | 64.2538 | 4.0159 | TA325 | 192/0 | Completed
2025-04-14 | 2025-04-11 | 2025-04-22 | Modina India | 44.7282 | 3.7274 | TA325 | 195A/2 | Completed
2025-04-14 | 2025-04-06 | 2025-04-16 | Rupesh | 64.2538 | 5.8413 | TA325 | 168/0 | Completed
2025-04-14 | 2025-04-03 | 2025-04-26 | Senahul | 82.2388 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-14 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.7305 | 5.3901 | TA325 | 195/4 | Completed
2025-04-14 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.7305 | 3.773 | TA325 | 135/7 | Completed
2025-04-14 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-14 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 249/1 | Completed
2025-04-15 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.7181 | 4.5717 | TA325 | 248/0 | Completed
2025-04-15 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.0448 | 1.8971 | TA325 | 158/1 | Completed
2025-04-15 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.7282 | 4.0662 | TA325 | 167/2 | Completed
2025-04-15 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-15 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.4236 | 5.1102 | TA325 | 181/0 | Completed
2025-04-15 | 2025-04-11 | 2025-04-16 | Jwala | 36.0448 | 6.0075 | TA325 | 205/1 | Completed
2025-04-15 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.2538 | 4.2836 | TA325 | 198/0 | Completed
2025-04-15 | 2025-04-13 | 2025-04-28 | Mjr | 64.2538 | 4.0159 | TA325 | 192/0 | Completed
2025-04-15 | 2025-04-11 | 2025-04-22 | Modina India | 44.7282 | 3.7274 | TA325 | 195A/2 | Completed
2025-04-15 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.4178 | 6.8022 | TA325 | 191A/0 | Completed
2025-04-15 | 2025-04-06 | 2025-04-16 | Rupesh | 64.2538 | 5.8413 | TA325 | 168/0 | Completed
2025-04-15 | 2025-04-03 | 2025-04-26 | Senahul | 82.2388 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-15 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.7305 | 5.3901 | TA325 | 195/4 | Completed
2025-04-15 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.7305 | 3.773 | TA325 | 135/7 | Completed
2025-04-15 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-15 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 249/1 | Completed
2025-04-16 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.7181 | 4.5717 | TA325 | 248/0 | Completed
2025-04-16 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.0448 | 1.8971 | TA325 | 158/1 | Completed
2025-04-16 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.7282 | 4.0662 | TA325 | 167/2 | Completed
2025-04-16 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-16 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.4236 | 5.1102 | TA325 | 181/0 | Completed
2025-04-16 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed
2025-04-16 | 2025-04-11 | 2025-04-16 | Jwala | 36.0448 | 6.0075 | TA325 | 205/1 | Completed
2025-04-16 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.7282 | 4.4728 | TA325 | 195/1 | Completed
2025-04-16 | 2025-04-13 | 2025-04-28 | Mjr | 64.2538 | 4.0159 | TA325 | 192/0 | Completed
2025-04-16 | 2025-04-11 | 2025-04-22 | Modina India | 44.7282 | 3.7274 | TA325 | 195A/2 | Completed
2025-04-16 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.7305 | 5.3901 | TA325 | 181/2 | Completed
2025-04-16 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.4178 | 6.8022 | TA325 | 191A/0 | Completed
2025-04-16 | 2025-04-06 | 2025-04-16 | Rupesh | 64.2538 | 5.8413 | TA325 | 168/0 | Completed
2025-04-16 | 2025-04-03 | 2025-04-26 | Senahul | 82.2388 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-16 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.7305 | 3.773 | TA325 | 135/7 | Completed
2025-04-16 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-16 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 249/1 | Completed
2025-04-17 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.7181 | 4.5717 | TA325 | 248/0 | Completed
2025-04-17 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.0448 | 1.8971 | TA325 | 158/1 | Completed
2025-04-17 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.7282 | 4.0662 | TA325 | 167/2 | Completed
2025-04-17 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-17 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.4236 | 5.1102 | TA325 | 181/0 | Completed
2025-04-17 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed
2025-04-17 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.7282 | 4.4728 | TA325 | 195/1 | Completed
2025-04-17 | 2025-04-13 | 2025-04-28 | Mjr | 64.2538 | 4.0159 | TA325 | 192/0 | Completed
2025-04-17 | 2025-04-17 | 2025-05-05 | Mjr | 39.4589 | 2.0768 | TA325 | 248/4 | Completed
2025-04-17 | 2025-04-11 | 2025-04-22 | Modina India | 44.7282 | 3.7274 | TA325 | 195A/2 | Completed
2025-04-17 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.7305 | 5.3901 | TA325 | 181/2 | Completed
2025-04-17 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.4178 | 6.8022 | TA325 | 191A/0 | Completed
2025-04-17 | 2025-04-03 | 2025-04-26 | Senahul | 82.2388 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-17 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.7305 | 3.773 | TA325 | 135/7 | Completed
2025-04-17 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-17 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 249/1 | Completed
2025-04-17 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.6235 | 3.3302 | TA325 | 248/2 | Completed
2025-04-18 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.7181 | 4.5717 | TA325 | 248/0 | Completed
2025-04-18 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.0448 | 1.8971 | TA325 | 158/1 | Completed
2025-04-18 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.7282 | 4.0662 | TA325 | 167/2 | Completed
2025-04-18 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.8082 | 6.4636 | TA325 | 190/0 | Completed
2025-04-18 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-18 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.4236 | 5.1102 | TA325 | 181/0 | Completed
2025-04-18 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed
2025-04-18 | 2025-04-18 | 2025-04-29 | Jwala | 84.2993 | 7.0249 | TA325 | 205/0 | Completed
2025-04-18 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.7282 | 4.4728 | TA325 | 195/1 | Completed
2025-04-18 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-04-18 | 2025-04-13 | 2025-04-28 | Mjr | 64.2538 | 4.0159 | TA325 | 192/0 | Completed
2025-04-18 | 2025-04-17 | 2025-05-05 | Mjr | 39.4589 | 2.0768 | TA325 | 248/4 | Completed
2025-04-18 | 2025-04-11 | 2025-04-22 | Modina India | 44.7282 | 3.7274 | TA325 | 195A/2 | Completed
2025-04-18 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.7305 | 5.3901 | TA325 | 181/2 | Completed
2025-04-18 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.4178 | 6.8022 | TA325 | 191A/0 | Completed
2025-04-18 | 2025-04-18 | 2025-05-05 | Rupesh | 94.4077 | 5.2449 | TA325 | 167/0 | Completed
2025-04-18 | 2025-04-03 | 2025-04-26 | Senahul | 82.2388 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-18 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.7305 | 3.773 | TA325 | 135/7 | Completed
2025-04-18 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.7282 | 4.0662 | TA325 | 195/3 | Completed
2025-04-18 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-18 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 249/1 | Completed
2025-04-18 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.6235 | 3.3302 | TA325 | 248/2 | Completed
2025-04-19 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.7181 | 4.5717 | TA325 | 248/0 | Completed
2025-04-19 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.0448 | 1.8971 | TA325 | 158/1 | Completed
2025-04-19 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.8082 | 6.4636 | TA325 | 190/0 | Completed
2025-04-19 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-19 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.4236 | 5.1102 | TA325 | 181/0 | Completed
2025-04-19 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed
2025-04-19 | 2025-04-18 | 2025-04-29 | Jwala | 84.2993 | 7.0249 | TA325 | 205/0 | Completed
2025-04-19 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.7282 | 4.4728 | TA325 | 195/1 | Completed
2025-04-19 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-04-19 | 2025-04-13 | 2025-04-28 | Mjr | 64.2538 | 4.0159 | TA325 | 192/0 | Completed
2025-04-19 | 2025-04-17 | 2025-05-05 | Mjr | 39.4589 | 2.0768 | TA325 | 248/4 | Completed
2025-04-19 | 2025-04-11 | 2025-04-22 | Modina India | 44.7282 | 3.7274 | TA325 | 195A/2 | Completed
2025-04-19 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.7305 | 5.3901 | TA325 | 181/2 | Completed
2025-04-19 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.4178 | 6.8022 | TA325 | 191A/0 | Completed
2025-04-19 | 2025-04-18 | 2025-05-05 | Rupesh | 94.4077 | 5.2449 | TA325 | 167/0 | Completed
2025-04-19 | 2025-04-03 | 2025-04-26 | Senahul | 82.2388 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-19 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.7305 | 3.773 | TA325 | 135/7 | Completed
2025-04-19 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.7282 | 4.0662 | TA325 | 195/3 | Completed
2025-04-19 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-19 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 249/1 | Completed
2025-04-19 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.6235 | 3.3302 | TA325 | 248/2 | Completed
2025-04-20 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.7181 | 4.5717 | TA325 | 248/0 | Completed
2025-04-20 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.0448 | 1.8971 | TA325 | 158/1 | Completed
2025-04-20 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.7305 | 3.773 | TA325 | 167/4 | Completed
2025-04-20 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.8082 | 6.4636 | TA325 | 190/0 | Completed
2025-04-20 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-20 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.4236 | 5.1102 | TA325 | 181/0 | Completed
2025-04-20 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed
2025-04-20 | 2025-04-18 | 2025-04-29 | Jwala | 84.2993 | 7.0249 | TA325 | 205/0 | Completed
2025-04-20 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.7282 | 4.4728 | TA325 | 195/1 | Completed
2025-04-20 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-04-20 | 2025-04-13 | 2025-04-28 | Mjr | 64.2538 | 4.0159 | TA325 | 192/0 | Completed
2025-04-20 | 2025-04-17 | 2025-05-05 | Mjr | 39.4589 | 2.0768 | TA325 | 248/4 | Completed
2025-04-20 | 2025-04-11 | 2025-04-22 | Modina India | 44.7282 | 3.7274 | TA325 | 195A/2 | Completed
2025-04-20 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.7305 | 5.3901 | TA325 | 181/2 | Completed
2025-04-20 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.4178 | 6.8022 | TA325 | 191A/0 | Completed
2025-04-20 | 2025-04-18 | 2025-05-05 | Rupesh | 94.4077 | 5.2449 | TA325 | 167/0 | Completed
2025-04-20 | 2025-04-03 | 2025-04-26 | Senahul | 82.2388 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-20 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.7305 | 3.773 | TA325 | 135/7 | Completed
2025-04-20 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.7282 | 4.0662 | TA325 | 195/3 | Completed
2025-04-20 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-20 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 249/1 | Completed
2025-04-20 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.6235 | 3.3302 | TA325 | 248/2 | Completed
2025-04-21 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.7181 | 4.5717 | TA325 | 248/0 | Completed
2025-04-21 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.0448 | 1.8971 | TA325 | 158/1 | Completed
2025-04-21 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.7305 | 3.773 | TA325 | 167/4 | Completed
2025-04-21 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.8082 | 6.4636 | TA325 | 190/0 | Completed
2025-04-21 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-21 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.4236 | 5.1102 | TA325 | 181/0 | Completed
2025-04-21 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed
2025-04-21 | 2025-04-18 | 2025-04-29 | Jwala | 84.2993 | 7.0249 | TA325 | 205/0 | Completed
2025-04-21 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.7282 | 4.4728 | TA325 | 195/1 | Completed
2025-04-21 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-04-21 | 2025-04-13 | 2025-04-28 | Mjr | 64.2538 | 4.0159 | TA325 | 192/0 | Completed
2025-04-21 | 2025-04-17 | 2025-05-05 | Mjr | 39.4589 | 2.0768 | TA325 | 248/4 | Completed
2025-04-21 | 2025-04-11 | 2025-04-22 | Modina India | 44.7282 | 3.7274 | TA325 | 195A/2 | Completed
2025-04-21 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.7305 | 5.3901 | TA325 | 181/2 | Completed
2025-04-21 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.4178 | 6.8022 | TA325 | 191A/0 | Completed
2025-04-21 | 2025-04-18 | 2025-05-05 | Rupesh | 94.4077 | 5.2449 | TA325 | 167/0 | Completed
2025-04-21 | 2025-04-03 | 2025-04-26 | Senahul | 82.2388 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-21 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.7305 | 3.773 | TA325 | 135/7 | Completed
2025-04-21 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.7282 | 4.0662 | TA325 | 195/3 | Completed
2025-04-21 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-21 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 249/1 | Completed
2025-04-21 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.6235 | 3.3302 | TA325 | 248/2 | Completed
2025-04-22 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.7181 | 4.5717 | TA325 | 248/0 | Completed
2025-04-22 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.0448 | 1.8971 | TA325 | 158/1 | Completed
2025-04-22 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.7305 | 3.773 | TA325 | 167/4 | Completed
2025-04-22 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-22 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.8082 | 6.4636 | TA325 | 190/0 | Completed
2025-04-22 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-22 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.4236 | 5.1102 | TA325 | 181/0 | Completed
2025-04-22 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed
2025-04-22 | 2025-04-18 | 2025-04-29 | Jwala | 84.2993 | 7.0249 | TA325 | 205/0 | Completed
2025-04-22 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.7282 | 4.4728 | TA325 | 195/1 | Completed
2025-04-22 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-04-22 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-04-22 | 2025-04-13 | 2025-04-28 | Mjr | 64.2538 | 4.0159 | TA325 | 192/0 | Completed
2025-04-22 | 2025-04-17 | 2025-05-05 | Mjr | 39.4589 | 2.0768 | TA325 | 248/4 | Completed
2025-04-22 | 2025-04-22 | 2025-05-15 | Mjr | 94.4077 | 3.9337 | TA325 | 194/0 | Completed
2025-04-22 | 2025-04-11 | 2025-04-22 | Modina India | 44.7282 | 3.7274 | TA325 | 195A/2 | Completed
2025-04-22 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.7305 | 5.3901 | TA325 | 181/2 | Completed
2025-04-22 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.4178 | 6.8022 | TA325 | 191A/0 | Completed
2025-04-22 | 2025-04-18 | 2025-05-05 | Rupesh | 94.4077 | 5.2449 | TA325 | 167/0 | Completed
2025-04-22 | 2025-04-03 | 2025-04-26 | Senahul | 82.2388 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-22 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.7305 | 3.773 | TA325 | 135/7 | Completed
2025-04-22 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.7282 | 4.0662 | TA325 | 195/3 | Completed
2025-04-22 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-22 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.6235 | 3.3302 | TA325 | 248/2 | Completed
2025-04-23 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.7181 | 4.5717 | TA325 | 248/0 | Completed
2025-04-23 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.0448 | 1.8971 | TA325 | 158/1 | Completed
2025-04-23 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.7305 | 3.773 | TA325 | 167/4 | Completed
2025-04-23 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-23 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.8082 | 6.4636 | TA325 | 190/0 | Completed
2025-04-23 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-23 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.4236 | 5.1102 | TA325 | 181/0 | Completed
2025-04-23 | 2025-04-18 | 2025-04-29 | Jwala | 84.2993 | 7.0249 | TA325 | 205/0 | Completed
2025-04-23 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.7282 | 4.4728 | TA325 | 195/1 | Completed
2025-04-23 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-04-23 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-04-23 | 2025-04-13 | 2025-04-28 | Mjr | 64.2538 | 4.0159 | TA325 | 192/0 | Completed
2025-04-23 | 2025-04-17 | 2025-05-05 | Mjr | 39.4589 | 2.0768 | TA325 | 248/4 | Completed
2025-04-23 | 2025-04-22 | 2025-05-15 | Mjr | 94.4077 | 3.9337 | TA325 | 194/0 | Completed
2025-04-23 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.0448 | 7.209 | TA325 | 191/2 | Completed
2025-04-23 | 2025-04-18 | 2025-05-05 | Rupesh | 94.4077 | 5.2449 | TA325 | 167/0 | Completed
2025-04-23 | 2025-04-03 | 2025-04-26 | Senahul | 82.2388 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-23 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.7282 | 4.0662 | TA325 | 195/3 | Completed
2025-04-23 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-23 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.6235 | 3.3302 | TA325 | 248/2 | Completed
2025-04-24 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.7181 | 4.5717 | TA325 | 248/0 | Completed
2025-04-24 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.0448 | 1.8971 | TA325 | 158/1 | Completed
2025-04-24 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.7305 | 3.773 | TA325 | 167/4 | Completed
2025-04-24 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-24 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.8082 | 6.4636 | TA325 | 190/0 | Completed
2025-04-24 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-24 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.4236 | 5.1102 | TA325 | 181/0 | Completed
2025-04-24 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.1461 | 8.9146 | TA325 | 180/0 | Completed
2025-04-24 | 2025-04-18 | 2025-04-29 | Jwala | 84.2993 | 7.0249 | TA325 | 205/0 | Completed
2025-04-24 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.7282 | 4.4728 | TA325 | 195/1 | Completed
2025-04-24 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-04-24 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-04-24 | 2025-04-13 | 2025-04-28 | Mjr | 64.2538 | 4.0159 | TA325 | 192/0 | Completed
2025-04-24 | 2025-04-17 | 2025-05-05 | Mjr | 39.4589 | 2.0768 | TA325 | 248/4 | Completed
2025-04-24 | 2025-04-22 | 2025-05-15 | Mjr | 94.4077 | 3.9337 | TA325 | 194/0 | Completed
2025-04-24 | 2025-04-24 | 2025-05-09 | Modina India | 44.7282 | 2.7955 | TA325 | 195A/1 | Completed
2025-04-24 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.7305 | 5.3901 | TA325 | 181/1 | Completed
2025-04-24 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.0448 | 7.209 | TA325 | 191/2 | Completed
2025-04-24 | 2025-04-18 | 2025-05-05 | Rupesh | 94.4077 | 5.2449 | TA325 | 167/0 | Completed
2025-04-24 | 2025-04-03 | 2025-04-26 | Senahul | 82.2388 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-24 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.7282 | 4.0662 | TA325 | 195/3 | Completed
2025-04-24 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-24 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.6235 | 3.3302 | TA325 | 248/2 | Completed
2025-04-25 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.7181 | 4.5717 | TA325 | 248/0 | Completed
2025-04-25 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.0448 | 1.8971 | TA325 | 158/1 | Completed
2025-04-25 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.7305 | 3.773 | TA325 | 167/4 | Completed
2025-04-25 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-25 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.8082 | 6.4636 | TA325 | 190/0 | Completed
2025-04-25 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-25 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.4236 | 5.1102 | TA325 | 181/0 | Completed
2025-04-25 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.1461 | 8.9146 | TA325 | 180/0 | Completed
2025-04-25 | 2025-04-18 | 2025-04-29 | Jwala | 84.2993 | 7.0249 | TA325 | 205/0 | Completed
2025-04-25 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.7282 | 4.4728 | TA325 | 195/1 | Completed
2025-04-25 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-04-25 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-04-25 | 2025-04-13 | 2025-04-28 | Mjr | 64.2538 | 4.0159 | TA325 | 192/0 | Completed
2025-04-25 | 2025-04-17 | 2025-05-05 | Mjr | 39.4589 | 2.0768 | TA325 | 248/4 | Completed
2025-04-25 | 2025-04-22 | 2025-05-15 | Mjr | 94.4077 | 3.9337 | TA325 | 194/0 | Completed
2025-04-25 | 2025-04-24 | 2025-05-09 | Modina India | 44.7282 | 2.7955 | TA325 | 195A/1 | Completed
2025-04-25 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.7305 | 5.3901 | TA325 | 181/1 | Completed
2025-04-25 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.0448 | 7.209 | TA325 | 191/2 | Completed
2025-04-25 | 2025-04-18 | 2025-05-05 | Rupesh | 94.4077 | 5.2449 | TA325 | 167/0 | Completed
2025-04-25 | 2025-04-03 | 2025-04-26 | Senahul | 82.2388 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-25 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.7282 | 4.0662 | TA325 | 195/3 | Completed
2025-04-25 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-25 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.6235 | 3.3302 | TA325 | 248/2 | Completed
2025-04-26 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.7181 | 4.5717 | TA325 | 248/0 | Completed
2025-04-26 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.7305 | 3.773 | TA325 | 167/4 | Completed
2025-04-26 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-26 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.8082 | 6.4636 | TA325 | 190/0 | Completed
2025-04-26 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-26 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.4236 | 5.1102 | TA325 | 181/0 | Completed
2025-04-26 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.1461 | 8.9146 | TA325 | 180/0 | Completed
2025-04-26 | 2025-04-18 | 2025-04-29 | Jwala | 84.2993 | 7.0249 | TA325 | 205/0 | Completed
2025-04-26 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-04-26 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-04-26 | 2025-04-13 | 2025-04-28 | Mjr | 64.2538 | 4.0159 | TA325 | 192/0 | Completed
2025-04-26 | 2025-04-17 | 2025-05-05 | Mjr | 39.4589 | 2.0768 | TA325 | 248/4 | Completed
2025-04-26 | 2025-04-22 | 2025-05-15 | Mjr | 94.4077 | 3.9337 | TA325 | 194/0 | Completed
2025-04-26 | 2025-04-24 | 2025-05-09 | Modina India | 44.7282 | 2.7955 | TA325 | 195A/1 | Completed
2025-04-26 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.7305 | 5.3901 | TA325 | 181/1 | Completed
2025-04-26 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.0448 | 7.209 | TA325 | 191/2 | Completed
2025-04-26 | 2025-04-18 | 2025-05-05 | Rupesh | 94.4077 | 5.2449 | TA325 | 167/0 | Completed
2025-04-26 | 2025-04-03 | 2025-04-26 | Senahul | 82.2388 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-26 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.7282 | 4.0662 | TA325 | 195/3 | Completed
2025-04-26 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-26 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.6235 | 3.3302 | TA325 | 248/2 | Completed
2025-04-27 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.7181 | 4.5717 | TA325 | 248/0 | Completed
2025-04-27 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.7305 | 3.773 | TA325 | 167/4 | Completed
2025-04-27 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-27 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.8082 | 6.4636 | TA325 | 190/0 | Completed
2025-04-27 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-27 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.4236 | 5.1102 | TA325 | 181/0 | Completed
2025-04-27 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.1461 | 8.9146 | TA325 | 180/0 | Completed
2025-04-27 | 2025-04-18 | 2025-04-29 | Jwala | 84.2993 | 7.0249 | TA325 | 205/0 | Completed
2025-04-27 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-04-27 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-04-27 | 2025-04-13 | 2025-04-28 | Mjr | 64.2538 | 4.0159 | TA325 | 192/0 | Completed
2025-04-27 | 2025-04-17 | 2025-05-05 | Mjr | 39.4589 | 2.0768 | TA325 | 248/4 | Completed
2025-04-27 | 2025-04-22 | 2025-05-15 | Mjr | 94.4077 | 3.9337 | TA325 | 194/0 | Completed
2025-04-27 | 2025-04-24 | 2025-05-09 | Modina India | 44.7282 | 2.7955 | TA325 | 195A/1 | Completed
2025-04-27 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.7305 | 5.3901 | TA325 | 181/1 | Completed
2025-04-27 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.0448 | 7.209 | TA325 | 191/2 | Completed
2025-04-27 | 2025-04-18 | 2025-05-05 | Rupesh | 94.4077 | 5.2449 | TA325 | 167/0 | Completed
2025-04-27 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.7282 | 4.0662 | TA325 | 195/3 | Completed
2025-04-27 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-27 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.6235 | 3.3302 | TA325 | 248/2 | Completed
2025-04-28 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.7181 | 4.5717 | TA325 | 248/0 | Completed
2025-04-28 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.7305 | 3.773 | TA325 | 167/4 | Completed
2025-04-28 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-28 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.8082 | 6.4636 | TA325 | 190/0 | Completed
2025-04-28 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-28 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-04-28 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.1461 | 8.9146 | TA325 | 180/0 | Completed
2025-04-28 | 2025-04-18 | 2025-04-29 | Jwala | 84.2993 | 7.0249 | TA325 | 205/0 | Completed
2025-04-28 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-04-28 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-04-28 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.2538 | 4.5896 | TA325 | 195/0 | Completed
2025-04-28 | 2025-04-13 | 2025-04-28 | Mjr | 64.2538 | 4.0159 | TA325 | 192/0 | Completed
2025-04-28 | 2025-04-17 | 2025-05-05 | Mjr | 39.4589 | 2.0768 | TA325 | 248/4 | Completed
2025-04-28 | 2025-04-22 | 2025-05-15 | Mjr | 94.4077 | 3.9337 | TA325 | 194/0 | Completed
2025-04-28 | 2025-04-24 | 2025-05-09 | Modina India | 44.7282 | 2.7955 | TA325 | 195A/1 | Completed
2025-04-28 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.7305 | 5.3901 | TA325 | 181/1 | Completed
2025-04-28 | 2025-04-18 | 2025-05-05 | Rupesh | 94.4077 | 5.2449 | TA325 | 167/0 | Completed
2025-04-28 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.7282 | 4.0662 | TA325 | 195/3 | Completed
2025-04-28 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.7305 | 2.695 | TA325 | 155/4 | Completed
2025-04-28 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-28 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.6235 | 3.3302 | TA325 | 248/2 | Completed
2025-04-29 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.7181 | 4.5717 | TA325 | 248/0 | Completed
2025-04-29 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.7305 | 3.773 | TA325 | 167/4 | Completed
2025-04-29 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.7305 | 2.9023 | TA325 | 155/5 | Completed
2025-04-29 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-29 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.8082 | 6.4636 | TA325 | 190/0 | Completed
2025-04-29 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-29 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-04-29 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.1461 | 8.9146 | TA325 | 180/0 | Completed
2025-04-29 | 2025-04-18 | 2025-04-29 | Jwala | 84.2993 | 7.0249 | TA325 | 205/0 | Completed
2025-04-29 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-04-29 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-04-29 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.2538 | 4.5896 | TA325 | 195/0 | Completed
2025-04-29 | 2025-04-17 | 2025-05-05 | Mjr | 39.4589 | 2.0768 | TA325 | 248/4 | Completed
2025-04-29 | 2025-04-22 | 2025-05-15 | Mjr | 94.4077 | 3.9337 | TA325 | 194/0 | Completed
2025-04-29 | 2025-04-24 | 2025-05-09 | Modina India | 44.7282 | 2.7955 | TA325 | 195A/1 | Completed
2025-04-29 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.7305 | 5.3901 | TA325 | 181/1 | Completed
2025-04-29 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.0448 | 6.0075 | TA325 | 191/3 | Completed
2025-04-29 | 2025-04-18 | 2025-05-05 | Rupesh | 94.4077 | 5.2449 | TA325 | 167/0 | Completed
2025-04-29 | 2025-04-29 | 2025-05-09 | Senahul | 37.7305 | 3.43 | TA325 | 248/6 | Completed
2025-04-29 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.7305 | 2.695 | TA325 | 155/4 | Completed
2025-04-29 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.6235 | 3.3302 | TA325 | 248/2 | Completed
2025-04-30 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.7181 | 4.5717 | TA325 | 248/0 | Completed
2025-04-30 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.7305 | 2.9023 | TA325 | 155/5 | Completed
2025-04-30 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-30 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.8082 | 6.4636 | TA325 | 190/0 | Completed
2025-04-30 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-04-30 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-04-30 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.1461 | 8.9146 | TA325 | 180/0 | Completed
2025-04-30 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-04-30 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-04-30 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.2538 | 4.5896 | TA325 | 195/0 | Completed
2025-04-30 | 2025-04-17 | 2025-05-05 | Mjr | 39.4589 | 2.0768 | TA325 | 248/4 | Completed
2025-04-30 | 2025-04-22 | 2025-05-15 | Mjr | 94.4077 | 3.9337 | TA325 | 194/0 | Completed
2025-04-30 | 2025-04-24 | 2025-05-09 | Modina India | 44.7282 | 2.7955 | TA325 | 195A/1 | Completed
2025-04-30 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.7305 | 5.3901 | TA325 | 181/1 | Completed
2025-04-30 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.0448 | 6.0075 | TA325 | 191/3 | Completed
2025-04-30 | 2025-04-18 | 2025-05-05 | Rupesh | 94.4077 | 5.2449 | TA325 | 167/0 | Completed
2025-04-30 | 2025-04-29 | 2025-05-09 | Senahul | 37.7305 | 3.43 | TA325 | 248/6 | Completed
2025-04-30 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.7305 | 2.695 | TA325 | 155/4 | Completed
2025-04-30 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.6235 | 3.3302 | TA325 | 248/2 | Completed
2025-05-01 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.7305 | 2.9023 | TA325 | 155/5 | Completed
2025-05-01 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-01 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.8082 | 6.4636 | TA325 | 190/0 | Completed
2025-05-01 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-01 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-05-01 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.1461 | 8.9146 | TA325 | 180/0 | Completed
2025-05-01 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-05-01 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-01 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.2538 | 4.5896 | TA325 | 195/0 | Completed
2025-05-01 | 2025-04-17 | 2025-05-05 | Mjr | 39.4589 | 2.0768 | TA325 | 248/4 | Completed
2025-05-01 | 2025-04-22 | 2025-05-15 | Mjr | 94.4077 | 3.9337 | TA325 | 194/0 | Completed
2025-05-01 | 2025-04-24 | 2025-05-09 | Modina India | 44.7282 | 2.7955 | TA325 | 195A/1 | Completed
2025-05-01 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.0448 | 6.0075 | TA325 | 191/3 | Completed
2025-05-01 | 2025-04-18 | 2025-05-05 | Rupesh | 94.4077 | 5.2449 | TA325 | 167/0 | Completed
2025-05-01 | 2025-04-29 | 2025-05-09 | Senahul | 37.7305 | 3.43 | TA325 | 248/6 | Completed
2025-05-01 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.7305 | 2.695 | TA325 | 155/4 | Completed
2025-05-02 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.7305 | 2.9023 | TA325 | 155/5 | Completed
2025-05-02 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-02 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.8082 | 6.4636 | TA325 | 190/0 | Completed
2025-05-02 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-02 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-05-02 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.1461 | 8.9146 | TA325 | 180/0 | Completed
2025-05-02 | 2025-05-02 | 2025-05-11 | Jwala | 98.8356 | 9.8836 | TA325 | 204/0 | Completed
2025-05-02 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-05-02 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-02 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.2538 | 4.5896 | TA325 | 195/0 | Completed
2025-05-02 | 2025-04-17 | 2025-05-05 | Mjr | 39.4589 | 2.0768 | TA325 | 248/4 | Completed
2025-05-02 | 2025-04-22 | 2025-05-15 | Mjr | 94.4077 | 3.9337 | TA325 | 194/0 | Completed
2025-05-02 | 2025-04-24 | 2025-05-09 | Modina India | 44.7282 | 2.7955 | TA325 | 195A/1 | Completed
2025-05-02 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.0448 | 6.0075 | TA325 | 191/3 | Completed
2025-05-02 | 2025-04-18 | 2025-05-05 | Rupesh | 94.4077 | 5.2449 | TA325 | 167/0 | Completed
2025-05-02 | 2025-04-29 | 2025-05-09 | Senahul | 37.7305 | 3.43 | TA325 | 248/6 | Completed
2025-05-02 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.7305 | 2.695 | TA325 | 155/4 | Completed
2025-05-02 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.7282 | 4.4728 | TA325 | 195/5 | Completed
2025-05-02 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.7305 | 3.773 | TA325 | 168/2 | Completed
2025-05-03 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.7305 | 2.9023 | TA325 | 155/5 | Completed
2025-05-03 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-03 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.8082 | 6.4636 | TA325 | 190/0 | Completed
2025-05-03 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-03 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-05-03 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.1461 | 8.9146 | TA325 | 180/0 | Completed
2025-05-03 | 2025-05-02 | 2025-05-11 | Jwala | 98.8356 | 9.8836 | TA325 | 204/0 | Completed
2025-05-03 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-05-03 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-03 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.2538 | 4.5896 | TA325 | 195/0 | Completed
2025-05-03 | 2025-04-17 | 2025-05-05 | Mjr | 39.4589 | 2.0768 | TA325 | 248/4 | Completed
2025-05-03 | 2025-04-22 | 2025-05-15 | Mjr | 94.4077 | 3.9337 | TA325 | 194/0 | Completed
2025-05-03 | 2025-04-24 | 2025-05-09 | Modina India | 44.7282 | 2.7955 | TA325 | 195A/1 | Completed
2025-05-03 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.7305 | 4.1923 | TA325 | 181/4 | Completed
2025-05-03 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.0448 | 6.0075 | TA325 | 191/3 | Completed
2025-05-03 | 2025-04-18 | 2025-05-05 | Rupesh | 94.4077 | 5.2449 | TA325 | 167/0 | Completed
2025-05-03 | 2025-04-29 | 2025-05-09 | Senahul | 37.7305 | 3.43 | TA325 | 248/6 | Completed
2025-05-03 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.7305 | 2.695 | TA325 | 155/4 | Completed
2025-05-03 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.7282 | 4.4728 | TA325 | 195/5 | Completed
2025-05-03 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.7305 | 3.773 | TA325 | 168/2 | Completed
2025-05-04 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.7305 | 2.9023 | TA325 | 155/5 | Completed
2025-05-04 | 2025-05-04 | 2025-05-19 | Barkat Ali | 80.408 | 5.0255 | TA325 | 167/1 | Completed
2025-05-04 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-04 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.8082 | 6.4636 | TA325 | 190/0 | Completed
2025-05-04 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-04 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-05-04 | 2025-05-02 | 2025-05-11 | Jwala | 98.8356 | 9.8836 | TA325 | 204/0 | Completed
2025-05-04 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-05-04 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-04 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.2538 | 4.5896 | TA325 | 195/0 | Completed
2025-05-04 | 2025-04-17 | 2025-05-05 | Mjr | 39.4589 | 2.0768 | TA325 | 248/4 | Completed
2025-05-04 | 2025-04-22 | 2025-05-15 | Mjr | 94.4077 | 3.9337 | TA325 | 194/0 | Completed
2025-05-04 | 2025-04-24 | 2025-05-09 | Modina India | 44.7282 | 2.7955 | TA325 | 195A/1 | Completed
2025-05-04 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.7305 | 4.1923 | TA325 | 181/4 | Completed
2025-05-04 | 2025-05-04 | 2025-05-18 | Rahim Khan 1 | 39.4589 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-04 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.0448 | 6.0075 | TA325 | 191/3 | Completed
2025-05-04 | 2025-04-18 | 2025-05-05 | Rupesh | 94.4077 | 5.2449 | TA325 | 167/0 | Completed
2025-05-04 | 2025-04-29 | 2025-05-09 | Senahul | 37.7305 | 3.43 | TA325 | 248/6 | Completed
2025-05-04 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.7305 | 2.695 | TA325 | 155/4 | Completed
2025-05-04 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.7282 | 4.4728 | TA325 | 195/5 | Completed
2025-05-04 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.7305 | 3.773 | TA325 | 168/2 | Completed
2025-05-05 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.7305 | 2.9023 | TA325 | 155/5 | Completed
2025-05-05 | 2025-05-04 | 2025-05-19 | Barkat Ali | 80.408 | 5.0255 | TA325 | 167/1 | Completed
2025-05-05 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-05 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.8082 | 6.4636 | TA325 | 190/0 | Completed
2025-05-05 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-05 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-05-05 | 2025-05-02 | 2025-05-11 | Jwala | 98.8356 | 9.8836 | TA325 | 204/0 | Completed
2025-05-05 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-05-05 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-05 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.2538 | 4.5896 | TA325 | 195/0 | Completed
2025-05-05 | 2025-04-17 | 2025-05-05 | Mjr | 39.4589 | 2.0768 | TA325 | 248/4 | Completed
2025-05-05 | 2025-04-22 | 2025-05-15 | Mjr | 94.4077 | 3.9337 | TA325 | 194/0 | Completed
2025-05-05 | 2025-04-24 | 2025-05-09 | Modina India | 44.7282 | 2.7955 | TA325 | 195A/1 | Completed
2025-05-05 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.7305 | 4.1923 | TA325 | 181/4 | Completed
2025-05-05 | 2025-05-04 | 2025-05-18 | Rahim Khan 1 | 39.4589 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-05 | 2025-04-18 | 2025-05-05 | Rupesh | 94.4077 | 5.2449 | TA325 | 167/0 | Completed
2025-05-05 | 2025-04-29 | 2025-05-09 | Senahul | 37.7305 | 3.43 | TA325 | 248/6 | Completed
2025-05-05 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.7305 | 2.695 | TA325 | 155/4 | Completed
2025-05-05 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.7282 | 4.4728 | TA325 | 195/5 | Completed
2025-05-05 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.7305 | 3.773 | TA325 | 168/2 | Completed
2025-05-06 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.7305 | 2.9023 | TA325 | 155/5 | Completed
2025-05-06 | 2025-05-04 | 2025-05-19 | Barkat Ali | 80.408 | 5.0255 | TA325 | 167/1 | Completed
2025-05-06 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-06 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.8082 | 6.4636 | TA325 | 190/0 | Completed
2025-05-06 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-06 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-05-06 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.6235 | 3.5864 | TA325 | 248/1 | Completed
2025-05-06 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-06 | 2025-05-02 | 2025-05-11 | Jwala | 98.8356 | 9.8836 | TA325 | 204/0 | Completed
2025-05-06 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-05-06 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-06 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.2538 | 4.5896 | TA325 | 195/0 | Completed
2025-05-06 | 2025-04-22 | 2025-05-15 | Mjr | 94.4077 | 3.9337 | TA325 | 194/0 | Completed
2025-05-06 | 2025-04-24 | 2025-05-09 | Modina India | 44.7282 | 2.7955 | TA325 | 195A/1 | Completed
2025-05-06 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.7305 | 4.1923 | TA325 | 181/4 | Completed
2025-05-06 | 2025-05-04 | 2025-05-18 | Rahim Khan 1 | 39.4589 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-06 | 2025-04-29 | 2025-05-09 | Senahul | 37.7305 | 3.43 | TA325 | 248/6 | Completed
2025-05-06 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.7305 | 2.695 | TA325 | 155/4 | Completed
2025-05-06 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.7282 | 4.4728 | TA325 | 195/5 | Completed
2025-05-06 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.7305 | 3.773 | TA325 | 168/2 | Completed
2025-05-07 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.7305 | 2.9023 | TA325 | 155/5 | Completed
2025-05-07 | 2025-05-04 | 2025-05-19 | Barkat Ali | 80.408 | 5.0255 | TA325 | 167/1 | Completed
2025-05-07 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-07 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-07 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.6235 | 3.5864 | TA325 | 248/1 | Completed
2025-05-07 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-07 | 2025-05-02 | 2025-05-11 | Jwala | 98.8356 | 9.8836 | TA325 | 204/0 | Completed
2025-05-07 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-05-07 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-07 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.2538 | 4.5896 | TA325 | 195/0 | Completed
2025-05-07 | 2025-04-22 | 2025-05-15 | Mjr | 94.4077 | 3.9337 | TA325 | 194/0 | Completed
2025-05-07 | 2025-04-24 | 2025-05-09 | Modina India | 44.7282 | 2.7955 | TA325 | 195A/1 | Completed
2025-05-07 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.7305 | 4.1923 | TA325 | 181/4 | Completed
2025-05-07 | 2025-05-04 | 2025-05-18 | Rahim Khan 1 | 39.4589 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-07 | 2025-04-29 | 2025-05-09 | Senahul | 37.7305 | 3.43 | TA325 | 248/6 | Completed
2025-05-07 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.7305 | 2.695 | TA325 | 155/4 | Completed
2025-05-07 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.7282 | 4.4728 | TA325 | 195/5 | Completed
2025-05-07 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.7305 | 3.773 | TA325 | 168/2 | Completed
2025-05-08 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.7305 | 2.9023 | TA325 | 155/5 | Completed
2025-05-08 | 2025-05-04 | 2025-05-19 | Barkat Ali | 80.408 | 5.0255 | TA325 | 167/1 | Completed
2025-05-08 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-08 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-08 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.6235 | 3.5864 | TA325 | 248/1 | Completed
2025-05-08 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-08 | 2025-05-02 | 2025-05-11 | Jwala | 98.8356 | 9.8836 | TA325 | 204/0 | Completed
2025-05-08 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-05-08 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-08 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.2538 | 4.5896 | TA325 | 195/0 | Completed
2025-05-08 | 2025-04-22 | 2025-05-15 | Mjr | 94.4077 | 3.9337 | TA325 | 194/0 | Completed
2025-05-08 | 2025-04-24 | 2025-05-09 | Modina India | 44.7282 | 2.7955 | TA325 | 195A/1 | Completed
2025-05-08 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.7305 | 4.1923 | TA325 | 181/4 | Completed
2025-05-08 | 2025-05-04 | 2025-05-18 | Rahim Khan 1 | 39.4589 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-08 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.2538 | 7.1393 | TA325 | 209/0 | Completed
2025-05-08 | 2025-04-29 | 2025-05-09 | Senahul | 37.7305 | 3.43 | TA325 | 248/6 | Completed
2025-05-08 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.7305 | 2.695 | TA325 | 155/4 | Completed
2025-05-08 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.7282 | 4.4728 | TA325 | 195/5 | Completed
2025-05-08 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.7305 | 3.773 | TA325 | 168/2 | Completed
2025-05-09 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.7305 | 2.9023 | TA325 | 155/5 | Completed
2025-05-09 | 2025-05-04 | 2025-05-19 | Barkat Ali | 80.408 | 5.0255 | TA325 | 167/1 | Completed
2025-05-09 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-09 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-09 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.6235 | 3.5864 | TA325 | 248/1 | Completed
2025-05-09 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-09 | 2025-05-02 | 2025-05-11 | Jwala | 98.8356 | 9.8836 | TA325 | 204/0 | Completed
2025-05-09 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-05-09 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-09 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.2538 | 4.5896 | TA325 | 195/0 | Completed
2025-05-09 | 2025-04-22 | 2025-05-15 | Mjr | 94.4077 | 3.9337 | TA325 | 194/0 | Completed
2025-05-09 | 2025-05-09 | 2025-05-20 | Mjr | 44.7282 | 3.7274 | TA325 | 248/3 | Completed
2025-05-09 | 2025-04-24 | 2025-05-09 | Modina India | 44.7282 | 2.7955 | TA325 | 195A/1 | Completed
2025-05-09 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.7305 | 4.1923 | TA325 | 181/4 | Completed
2025-05-09 | 2025-05-04 | 2025-05-18 | Rahim Khan 1 | 39.4589 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-09 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.2538 | 7.1393 | TA325 | 209/0 | Completed
2025-05-09 | 2025-04-29 | 2025-05-09 | Senahul | 37.7305 | 3.43 | TA325 | 248/6 | Completed
2025-05-09 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.7305 | 2.695 | TA325 | 155/4 | Completed
2025-05-09 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.7282 | 4.4728 | TA325 | 195/5 | Completed
2025-05-09 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.7305 | 3.773 | TA325 | 168/2 | Completed
2025-05-10 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.7305 | 2.9023 | TA325 | 155/5 | Completed
2025-05-10 | 2025-05-04 | 2025-05-19 | Barkat Ali | 80.408 | 5.0255 | TA325 | 167/1 | Completed
2025-05-10 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-10 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-10 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.6235 | 3.5864 | TA325 | 248/1 | Completed
2025-05-10 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-10 | 2025-05-02 | 2025-05-11 | Jwala | 98.8356 | 9.8836 | TA325 | 204/0 | Completed
2025-05-10 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-05-10 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-10 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.2538 | 4.5896 | TA325 | 195/0 | Completed
2025-05-10 | 2025-04-22 | 2025-05-15 | Mjr | 94.4077 | 3.9337 | TA325 | 194/0 | Completed
2025-05-10 | 2025-05-09 | 2025-05-20 | Mjr | 44.7282 | 3.7274 | TA325 | 248/3 | Completed
2025-05-10 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.7305 | 4.1923 | TA325 | 181/4 | Completed
2025-05-10 | 2025-05-04 | 2025-05-18 | Rahim Khan 1 | 39.4589 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-10 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.2538 | 7.1393 | TA325 | 209/0 | Completed
2025-05-10 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.7305 | 2.695 | TA325 | 155/4 | Completed
2025-05-10 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.7282 | 4.4728 | TA325 | 195/5 | Completed
2025-05-10 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.7305 | 3.773 | TA325 | 168/2 | Completed
2025-05-11 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.7305 | 2.9023 | TA325 | 155/5 | Completed
2025-05-11 | 2025-05-04 | 2025-05-19 | Barkat Ali | 80.408 | 5.0255 | TA325 | 167/1 | Completed
2025-05-11 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-11 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-11 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.6235 | 3.5864 | TA325 | 248/1 | Completed
2025-05-11 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-11 | 2025-05-02 | 2025-05-11 | Jwala | 98.8356 | 9.8836 | TA325 | 204/0 | Completed
2025-05-11 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-05-11 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-11 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.2538 | 4.5896 | TA325 | 195/0 | Completed
2025-05-11 | 2025-04-22 | 2025-05-15 | Mjr | 94.4077 | 3.9337 | TA325 | 194/0 | Completed
2025-05-11 | 2025-05-09 | 2025-05-20 | Mjr | 44.7282 | 3.7274 | TA325 | 248/3 | Completed
2025-05-11 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.7305 | 4.1923 | TA325 | 181/4 | Completed
2025-05-11 | 2025-05-04 | 2025-05-18 | Rahim Khan 1 | 39.4589 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-11 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.2538 | 7.1393 | TA325 | 209/0 | Completed
2025-05-11 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.7305 | 2.695 | TA325 | 155/4 | Completed
2025-05-11 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.7282 | 4.4728 | TA325 | 195/5 | Completed
2025-05-11 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.7305 | 3.773 | TA325 | 168/2 | Completed
2025-05-11 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 247/1 | Completed
2025-05-12 | 2025-05-04 | 2025-05-19 | Barkat Ali | 80.408 | 5.0255 | TA325 | 167/1 | Completed
2025-05-12 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-12 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-12 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.6235 | 3.5864 | TA325 | 248/1 | Completed
2025-05-12 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-12 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-05-12 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-12 | 2025-04-22 | 2025-05-15 | Mjr | 94.4077 | 3.9337 | TA325 | 194/0 | Completed
2025-05-12 | 2025-05-09 | 2025-05-20 | Mjr | 44.7282 | 3.7274 | TA325 | 248/3 | Completed
2025-05-12 | 2025-05-04 | 2025-05-18 | Rahim Khan 1 | 39.4589 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-12 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.2538 | 7.1393 | TA325 | 209/0 | Completed
2025-05-12 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 247/1 | Completed
2025-05-13 | 2025-05-04 | 2025-05-19 | Barkat Ali | 80.408 | 5.0255 | TA325 | 167/1 | Completed
2025-05-13 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-13 | 2025-05-13 | 2025-05-18 | Dhaneswar Mahto | 37.7305 | 6.2884 | TA325 | 211/1 | Completed
2025-05-13 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-13 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.6235 | 3.5864 | TA325 | 248/1 | Completed
2025-05-13 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-13 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-05-13 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-13 | 2025-04-22 | 2025-05-15 | Mjr | 94.4077 | 3.9337 | TA325 | 194/0 | Completed
2025-05-13 | 2025-05-09 | 2025-05-20 | Mjr | 44.7282 | 3.7274 | TA325 | 248/3 | Completed
2025-05-13 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.0448 | 4.5056 | TA325 | 168/1 | Completed
2025-05-13 | 2025-05-04 | 2025-05-18 | Rahim Khan 1 | 39.4589 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-13 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.2538 | 7.1393 | TA325 | 209/0 | Completed
2025-05-13 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-05-13 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 247/1 | Completed
2025-05-14 | 2025-05-04 | 2025-05-19 | Barkat Ali | 80.408 | 5.0255 | TA325 | 167/1 | Completed
2025-05-14 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-14 | 2025-05-13 | 2025-05-18 | Dhaneswar Mahto | 37.7305 | 6.2884 | TA325 | 211/1 | Completed
2025-05-14 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-14 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.6235 | 3.5864 | TA325 | 248/1 | Completed
2025-05-14 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-14 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-05-14 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-14 | 2025-04-22 | 2025-05-15 | Mjr | 94.4077 | 3.9337 | TA325 | 194/0 | Completed
2025-05-14 | 2025-05-09 | 2025-05-20 | Mjr | 44.7282 | 3.7274 | TA325 | 248/3 | Completed
2025-05-14 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.0448 | 4.5056 | TA325 | 168/1 | Completed
2025-05-14 | 2025-05-04 | 2025-05-18 | Rahim Khan 1 | 39.4589 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-14 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.2538 | 7.1393 | TA325 | 209/0 | Completed
2025-05-14 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-05-14 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 247/1 | Completed
2025-05-15 | 2025-05-04 | 2025-05-19 | Barkat Ali | 80.408 | 5.0255 | TA325 | 167/1 | Completed
2025-05-15 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-15 | 2025-05-13 | 2025-05-18 | Dhaneswar Mahto | 37.7305 | 6.2884 | TA325 | 211/1 | Completed
2025-05-15 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-15 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.6235 | 3.5864 | TA325 | 248/1 | Completed
2025-05-15 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-15 | 2025-05-15 | 2025-05-21 | Jwala | 39.4589 | 5.637 | TA325 | 205/2 | Completed
2025-05-15 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-05-15 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-15 | 2025-04-22 | 2025-05-15 | Mjr | 94.4077 | 3.9337 | TA325 | 194/0 | Completed
2025-05-15 | 2025-05-09 | 2025-05-20 | Mjr | 44.7282 | 3.7274 | TA325 | 248/3 | Completed
2025-05-15 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.0448 | 4.5056 | TA325 | 168/1 | Completed
2025-05-15 | 2025-05-04 | 2025-05-18 | Rahim Khan 1 | 39.4589 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-15 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.2538 | 7.1393 | TA325 | 209/0 | Completed
2025-05-15 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-05-15 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 247/1 | Completed
2025-05-16 | 2025-05-04 | 2025-05-19 | Barkat Ali | 80.408 | 5.0255 | TA325 | 167/1 | Completed
2025-05-16 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.7305 | 3.773 | TA325 | 165/1 | Completed
2025-05-16 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-16 | 2025-05-13 | 2025-05-18 | Dhaneswar Mahto | 37.7305 | 6.2884 | TA325 | 211/1 | Completed
2025-05-16 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-16 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.6235 | 3.5864 | TA325 | 248/1 | Completed
2025-05-16 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-16 | 2025-05-15 | 2025-05-21 | Jwala | 39.4589 | 5.637 | TA325 | 205/2 | Completed
2025-05-16 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-05-16 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-16 | 2025-05-09 | 2025-05-20 | Mjr | 44.7282 | 3.7274 | TA325 | 248/3 | Completed
2025-05-16 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.0448 | 4.5056 | TA325 | 168/1 | Completed
2025-05-16 | 2025-05-04 | 2025-05-18 | Rahim Khan 1 | 39.4589 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-16 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.2538 | 7.1393 | TA325 | 209/0 | Completed
2025-05-16 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-05-16 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 247/1 | Completed
2025-05-17 | 2025-05-04 | 2025-05-19 | Barkat Ali | 80.408 | 5.0255 | TA325 | 167/1 | Completed
2025-05-17 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.7305 | 3.773 | TA325 | 165/1 | Completed
2025-05-17 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-17 | 2025-05-13 | 2025-05-18 | Dhaneswar Mahto | 37.7305 | 6.2884 | TA325 | 211/1 | Completed
2025-05-17 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-17 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.6235 | 3.5864 | TA325 | 248/1 | Completed
2025-05-17 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-17 | 2025-05-15 | 2025-05-21 | Jwala | 39.4589 | 5.637 | TA325 | 205/2 | Completed
2025-05-17 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-05-17 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-17 | 2025-05-09 | 2025-05-20 | Mjr | 44.7282 | 3.7274 | TA325 | 248/3 | Completed
2025-05-17 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.0448 | 4.5056 | TA325 | 168/1 | Completed
2025-05-17 | 2025-05-04 | 2025-05-18 | Rahim Khan 1 | 39.4589 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-17 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-05-17 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 247/1 | Completed
2025-05-18 | 2025-05-04 | 2025-05-19 | Barkat Ali | 80.408 | 5.0255 | TA325 | 167/1 | Completed
2025-05-18 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.7305 | 3.773 | TA325 | 165/1 | Completed
2025-05-18 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-18 | 2025-05-13 | 2025-05-18 | Dhaneswar Mahto | 37.7305 | 6.2884 | TA325 | 211/1 | Completed
2025-05-18 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-18 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.6235 | 3.5864 | TA325 | 248/1 | Completed
2025-05-18 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-18 | 2025-05-15 | 2025-05-21 | Jwala | 39.4589 | 5.637 | TA325 | 205/2 | Completed
2025-05-18 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-05-18 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-18 | 2025-05-09 | 2025-05-20 | Mjr | 44.7282 | 3.7274 | TA325 | 248/3 | Completed
2025-05-18 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.0448 | 4.5056 | TA325 | 168/1 | Completed
2025-05-18 | 2025-05-04 | 2025-05-18 | Rahim Khan 1 | 39.4589 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-18 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-05-18 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 247/1 | Completed
2025-05-19 | 2025-05-04 | 2025-05-19 | Barkat Ali | 80.408 | 5.0255 | TA325 | 167/1 | Completed
2025-05-19 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.7305 | 3.773 | TA325 | 165/1 | Completed
2025-05-19 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-19 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.7305 | 6.2884 | TA325 | 181/3 | Completed
2025-05-19 | 2025-05-15 | 2025-05-21 | Jwala | 39.4589 | 5.637 | TA325 | 205/2 | Completed
2025-05-19 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-05-19 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-19 | 2025-05-09 | 2025-05-20 | Mjr | 44.7282 | 3.7274 | TA325 | 248/3 | Completed
2025-05-19 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.0448 | 4.5056 | TA325 | 168/1 | Completed
2025-05-19 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-05-19 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 247/1 | Completed
2025-05-20 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.7305 | 3.773 | TA325 | 165/1 | Completed
2025-05-20 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-20 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.7305 | 6.2884 | TA325 | 181/3 | Completed
2025-05-20 | 2025-05-15 | 2025-05-21 | Jwala | 39.4589 | 5.637 | TA325 | 205/2 | Completed
2025-05-20 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-05-20 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-20 | 2025-05-09 | 2025-05-20 | Mjr | 44.7282 | 3.7274 | TA325 | 248/3 | Completed
2025-05-20 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.0448 | 4.5056 | TA325 | 168/1 | Completed
2025-05-20 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-05-21 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.7305 | 3.773 | TA325 | 165/1 | Completed
2025-05-21 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-21 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.7305 | 6.2884 | TA325 | 181/3 | Completed
2025-05-21 | 2025-05-15 | 2025-05-21 | Jwala | 39.4589 | 5.637 | TA325 | 205/2 | Completed
2025-05-21 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-05-21 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-21 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-05-22 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.7305 | 3.773 | TA325 | 165/1 | Completed
2025-05-22 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-22 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.7305 | 6.2884 | TA325 | 181/3 | Completed
2025-05-22 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-05-22 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-22 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-05-23 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.7305 | 3.773 | TA325 | 165/1 | Completed
2025-05-23 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-23 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.7305 | 6.2884 | TA325 | 181/3 | Completed
2025-05-23 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-23 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-05-24 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.7305 | 3.773 | TA325 | 165/1 | Completed
2025-05-24 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-24 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.4236 | 7.0265 | TA325 | 169/0 | Completed
2025-05-24 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.7305 | 6.2884 | TA325 | 181/3 | Completed
2025-05-24 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-24 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-05-24 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-05-25 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.7305 | 3.773 | TA325 | 165/1 | Completed
2025-05-25 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-25 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.4236 | 7.0265 | TA325 | 169/0 | Completed
2025-05-25 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-25 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-05-25 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-05-26 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-26 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.4236 | 7.0265 | TA325 | 169/0 | Completed
2025-05-26 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-26 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-05-26 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-05-27 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-27 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.4236 | 7.0265 | TA325 | 169/0 | Completed
2025-05-27 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-27 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-05-27 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-05-28 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-28 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.4236 | 7.0265 | TA325 | 169/0 | Completed
2025-05-28 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.2376 | 8.0264 | TA325 | 175/0 | Completed
2025-05-28 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-28 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-05-28 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-05-29 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-29 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.4236 | 7.0265 | TA325 | 169/0 | Completed
2025-05-29 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.2376 | 8.0264 | TA325 | 175/0 | Completed
2025-05-29 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-29 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-05-29 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-05-29 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.7282 | 4.9698 | TA325 | 172/2 | Completed
2025-05-30 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-30 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.4236 | 7.0265 | TA325 | 169/0 | Completed
2025-05-30 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.2376 | 8.0264 | TA325 | 175/0 | Completed
2025-05-30 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-30 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-05-30 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-05-30 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.7282 | 4.9698 | TA325 | 172/2 | Completed
2025-05-31 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-05-31 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.4236 | 7.0265 | TA325 | 169/0 | Completed
2025-05-31 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.2376 | 8.0264 | TA325 | 175/0 | Completed
2025-05-31 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-05-31 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-05-31 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-05-31 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.7282 | 4.9698 | TA325 | 172/2 | Completed
2025-06-01 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-01 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-01 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.4236 | 7.0265 | TA325 | 169/0 | Completed
2025-06-01 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.2376 | 8.0264 | TA325 | 175/0 | Completed
2025-06-01 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-01 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-01 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-01 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.7282 | 4.9698 | TA325 | 172/2 | Completed
2025-06-02 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-02 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-02 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.4236 | 7.0265 | TA325 | 169/0 | Completed
2025-06-02 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.2376 | 8.0264 | TA325 | 175/0 | Completed
2025-06-02 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-02 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-02 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-02 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-02 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.7282 | 4.9698 | TA325 | 172/2 | Completed
2025-06-03 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-03 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-03 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.4236 | 7.0265 | TA325 | 169/0 | Completed
2025-06-03 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.2376 | 8.0264 | TA325 | 175/0 | Completed
2025-06-03 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-03 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-03 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-03 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-03 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.7282 | 4.9698 | TA325 | 172/2 | Completed
2025-06-04 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-04 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-04 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.4236 | 7.0265 | TA325 | 169/0 | Completed
2025-06-04 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.2376 | 8.0264 | TA325 | 175/0 | Completed
2025-06-04 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-04 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-04 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-04 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-04 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.7282 | 4.9698 | TA325 | 172/2 | Completed
2025-06-05 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-05 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-05 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.4236 | 7.0265 | TA325 | 169/0 | Completed
2025-06-05 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.2376 | 8.0264 | TA325 | 175/0 | Completed
2025-06-05 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-05 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-05 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-05 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-05 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.7282 | 4.9698 | TA325 | 172/2 | Completed
2025-06-06 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-06 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-06 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.4236 | 7.0265 | TA325 | 169/0 | Completed
2025-06-06 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.4178 | 6.8022 | TA325 | 174/1 | Completed
2025-06-06 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-06 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-06 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-06 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-06 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.7282 | 4.9698 | TA325 | 172/2 | Completed
2025-06-07 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-07 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-07 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.4236 | 7.0265 | TA325 | 169/0 | Completed
2025-06-07 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.4178 | 6.8022 | TA325 | 174/1 | Completed
2025-06-07 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-07 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-07 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-07 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-08 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-08 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-08 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.4236 | 7.0265 | TA325 | 169/0 | Completed
2025-06-08 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.4178 | 6.8022 | TA325 | 174/1 | Completed
2025-06-08 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-08 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-08 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-06-08 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-08 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-09 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-09 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-09 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.4178 | 6.8022 | TA325 | 174/1 | Completed
2025-06-09 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-09 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-09 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-06-09 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-09 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-10 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-10 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-10 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.4178 | 6.8022 | TA325 | 174/1 | Completed
2025-06-10 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-10 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-10 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-06-10 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-10 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-11 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-11 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-11 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-11 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.4178 | 6.8022 | TA325 | 174/1 | Completed
2025-06-11 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-11 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-11 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-06-11 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-11 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-12 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-12 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-12 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-12 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.4178 | 6.8022 | TA325 | 174/1 | Completed
2025-06-12 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-12 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-12 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-06-12 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-12 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-13 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-13 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-13 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-13 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.4178 | 6.8022 | TA325 | 174/1 | Completed
2025-06-13 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-13 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-13 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-06-13 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-13 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-14 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-14 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-14 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-14 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-14 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-14 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-06-14 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-14 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-15 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-15 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-06-15 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-15 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-15 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-15 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-15 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-06-15 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-06-15 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-15 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-16 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-16 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-06-16 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-16 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-16 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-16 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-16 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-06-16 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-06-16 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-16 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-17 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-17 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-06-17 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-17 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-17 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-17 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-17 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-06-17 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-06-17 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-17 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-18 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-18 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-06-18 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-18 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-18 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-18 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-18 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-06-18 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-06-18 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-18 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-19 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-19 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-06-19 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-19 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-19 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-19 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-19 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-06-19 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-06-19 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-19 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-20 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-20 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-06-20 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-20 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-20 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-20 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-20 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-06-20 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-06-20 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-20 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-21 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-21 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-06-21 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-21 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-21 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-21 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-21 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-06-21 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-06-21 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-21 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-22 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-22 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-06-22 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-22 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-22 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-22 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-22 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-06-22 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-06-22 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-22 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-23 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-23 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-06-23 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-23 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-23 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-23 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-23 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-06-23 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-06-23 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-23 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-24 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-24 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-06-24 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-24 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-24 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-24 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-24 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-06-24 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-06-24 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-24 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-25 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-25 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-06-25 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-25 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-25 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-25 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-25 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-06-25 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-06-25 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-25 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-26 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-26 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-06-26 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-26 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-26 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-26 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-26 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-06-26 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-06-26 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-26 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-27 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-27 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-06-27 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-27 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-27 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-27 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-27 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-06-27 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-06-27 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-27 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-28 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-28 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-06-28 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-28 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-28 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-28 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-28 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-06-28 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-06-28 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-28 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-29 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-29 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-06-29 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-29 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-29 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-29 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-29 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-06-29 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-06-29 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-29 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-06-30 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-30 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-06-30 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-06-30 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-30 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-06-30 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-06-30 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-06-30 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-06-30 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-06-30 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-01 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-01 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-01 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-01 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-07-01 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-01 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-01 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-07-01 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-01 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-01 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-02 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-02 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-02 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-02 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-07-02 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-02 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-02 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-07-02 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-02 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-02 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-03 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-03 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-03 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-03 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-07-03 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-03 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-03 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-07-03 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-03 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-03 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-04 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-04 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-04 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-04 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-07-04 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-04 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-04 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-07-04 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-04 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-04 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-05 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-05 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-05 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-05 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-05 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-05 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-07-05 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-05 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-05 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-06 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-06 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-06 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-06 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-06 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-06 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-07-06 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-06 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-06 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-07 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-07 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-07 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-07 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-07 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-07 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-07-07 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-07 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-07 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-08 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-08 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-08 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-08 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-08 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-08 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-07-08 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-08 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-08 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-09 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-09 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-09 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-09 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-09 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-09 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-07-09 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-09 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-09 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-10 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-10 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-10 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-10 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-10 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-10 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-07-10 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-10 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-10 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-11 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-11 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-11 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-11 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-11 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-11 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-07-11 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-11 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-11 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-12 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-12 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-12 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-12 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-12 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-12 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-07-12 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-12 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-12 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-13 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-13 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-13 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-13 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-13 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-13 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-07-13 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-13 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-13 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-14 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-14 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-14 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-14 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-14 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-14 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-07-14 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-14 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-14 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-15 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-15 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-15 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-15 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-15 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-15 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-07-15 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-15 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-15 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-16 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-16 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-16 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-16 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-16 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-16 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-07-16 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-16 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-16 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-17 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-17 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-17 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-17 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-17 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-17 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-07-17 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-17 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-17 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-18 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-18 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-18 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-18 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-18 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-18 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-07-18 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-18 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-18 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-19 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-19 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-19 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-19 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-19 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-19 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-07-19 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-19 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-19 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-20 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-20 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-20 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-20 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-20 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-20 | 2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-07-20 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-20 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-20 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-21 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-21 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-21 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-21 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-21 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-21 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-21 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-21 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-22 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-22 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-22 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-22 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-22 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-22 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-22 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-22 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-23 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-07-23 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-23 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-23 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-23 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-23 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-23 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-23 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-23 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-24 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-07-24 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-24 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-24 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-24 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-24 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-24 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-24 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-24 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-25 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-07-25 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-25 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-25 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-25 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-25 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-25 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-25 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-25 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-26 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-07-26 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-26 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-26 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-26 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-26 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-26 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-26 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-26 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-27 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-07-27 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-27 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-27 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-27 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-27 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-27 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-27 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-27 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-28 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-07-28 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-28 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-28 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-28 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-28 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-28 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-28 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-28 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-29 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-07-29 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-29 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-29 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-29 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-29 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-29 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-29 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-29 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-30 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-07-30 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-30 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-30 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-30 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-30 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-30 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-30 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-30 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-07-31 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-07-31 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-07-31 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-07-31 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-07-31 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-07-31 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-07-31 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-07-31 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-07-31 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-01 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-01 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-08-01 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-01 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-01 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-01 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-08-01 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-08-01 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-01 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-02 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-02 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-08-02 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-02 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-02 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-02 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-08-02 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-08-02 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-02 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-03 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-03 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-08-03 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-03 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-03 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-03 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-08-03 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-08-03 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-03 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-04 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-04 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-08-04 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-04 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-04 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-04 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-08-04 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-08-04 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-04 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-05 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-05 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-08-05 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-05 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-05 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-05 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-08-05 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-08-05 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-05 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-06 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-06 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-08-06 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-06 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-06 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-06 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-08-06 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-08-06 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-08-06 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-06 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-07 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-07 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-08-07 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-07 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-07 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-07 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-08-07 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-08-07 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-08-07 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-07 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-08 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-08 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-08-08 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-08 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-08 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-08 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-08-08 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-08-08 | 2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-08-08 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-08 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-09 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-09 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-08-09 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-09 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-09 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-09 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-08-09 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-08-09 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-09 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-10 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-10 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-08-10 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-10 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-10 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-10 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-08-10 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-08-10 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-10 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-11 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-11 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-08-11 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-11 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-11 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-11 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-08-11 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-08-11 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-11 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-12 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-12 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-08-12 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-12 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-12 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-12 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-08-12 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-08-12 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-12 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-13 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-13 | 2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-08-13 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-13 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-13 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-13 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-08-13 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-08-13 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-13 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-14 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-14 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-14 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-14 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-14 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-08-14 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-08-14 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-14 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-15 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-15 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-15 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-15 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-15 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-08-15 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-08-15 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-15 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-16 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-16 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-16 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-16 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-16 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-08-16 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-08-16 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-16 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-17 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-17 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-17 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-17 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-17 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-08-17 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-08-17 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-17 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-18 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-18 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-18 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-18 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-18 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-08-18 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-08-18 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-18 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-19 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-19 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-19 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-19 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-19 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-08-19 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-08-19 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-19 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-20 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-20 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-20 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-20 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-20 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-08-20 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-08-20 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-20 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-21 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-21 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-21 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-21 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-21 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-08-21 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-08-21 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-21 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-22 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-22 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-22 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-22 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-22 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-08-22 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-08-22 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-22 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-23 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-23 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-23 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-23 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-23 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-08-23 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-08-23 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-23 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-24 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-24 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-24 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-24 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-24 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-08-24 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-08-24 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-24 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-25 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-25 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-25 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-25 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-25 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-08-25 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-08-25 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-25 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-26 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-26 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-26 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-26 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-08-26 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-26 | 2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-08-26 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-08-26 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-26 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-27 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-27 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-27 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-27 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-08-27 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-27 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-08-27 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-27 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-28 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-28 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-28 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-28 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-08-28 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-28 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-08-28 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-28 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-29 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-29 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-29 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-29 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-08-29 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-29 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-08-29 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-29 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-30 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-30 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-30 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-30 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-08-30 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-30 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-08-30 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-30 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-08-31 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-08-31 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-08-31 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-08-31 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-08-31 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-08-31 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-08-31 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-08-31 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-01 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-01 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-09-01 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-01 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-01 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-01 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-09-01 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-09-01 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-02 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-02 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-09-02 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-02 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-02 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-02 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-09-02 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-09-02 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-03 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-03 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-09-03 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-03 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-03 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-03 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-09-03 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-09-03 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-04 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-04 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-09-04 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-04 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-04 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-04 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-09-04 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-09-04 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-05 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-05 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-09-05 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-05 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-05 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-05 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-09-05 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-09-05 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-05 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-09-06 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-06 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-09-06 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-06 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-06 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-06 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-09-06 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-09-06 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-06 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-09-07 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-07 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-09-07 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-07 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-07 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-07 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-09-07 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-09-07 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-07 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-09-08 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-08 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-09-08 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-08 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-08 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-08 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-09-08 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-09-08 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-08 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-09-09 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-09 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-09-09 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-09 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-09 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-09 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-09-09 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-09-09 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-09 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-09-10 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-10 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-09-10 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-10 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-10 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-10 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-09-10 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-09-10 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-10 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-09-11 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-11 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-09-11 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-11 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-11 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-11 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-09-11 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-09-11 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-11 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-09-12 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-12 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-09-12 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-12 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-12 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-12 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-09-12 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-09-12 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-12 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-09-13 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-13 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-09-13 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-13 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-13 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-13 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-09-13 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-13 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-09-13 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-13 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-09-14 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-14 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-09-14 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-14 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-14 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-14 | 2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-09-14 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-14 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-09-14 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-14 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-09-15 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-15 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-09-15 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-15 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-15 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-15 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-15 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-09-15 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-15 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-09-16 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-16 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-09-16 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-16 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-16 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-16 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-16 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-09-16 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-16 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-09-17 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-17 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-09-17 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-17 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-17 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-17 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-17 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-09-17 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-17 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-09-18 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-18 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-09-18 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-18 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-18 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.2376 | 3.4399 | TA325 | 234/0 | Completed
2025-09-18 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-18 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-18 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-09-18 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-18 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-09-19 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-19 | 2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-09-19 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-19 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-19 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.2376 | 3.4399 | TA325 | 234/0 | Completed
2025-09-19 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-19 | 2025-09-19 | 2025-10-05 | Nan | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-19 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-19 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-09-19 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-19 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-09-20 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-20 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-20 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-20 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.2376 | 3.4399 | TA325 | 234/0 | Completed
2025-09-20 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-20 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-09-20 | 2025-09-19 | 2025-10-05 | Nan | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-20 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-20 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-09-20 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-20 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-09-21 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-21 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-21 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-21 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.2376 | 3.4399 | TA325 | 234/0 | Completed
2025-09-21 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-21 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-09-21 | 2025-09-19 | 2025-10-05 | Nan | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-21 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-21 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-09-21 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-21 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-09-22 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-22 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-22 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-22 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.2376 | 3.4399 | TA325 | 234/0 | Completed
2025-09-22 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-22 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-09-22 | 2025-09-19 | 2025-10-05 | Nan | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-22 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-22 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-09-22 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-22 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-09-23 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-23 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-23 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-23 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.2376 | 3.4399 | TA325 | 234/0 | Completed
2025-09-23 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-23 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-09-23 | 2025-09-19 | 2025-10-05 | Nan | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-23 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-23 | 2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-09-23 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-23 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-09-23 | 2025-09-23 | 2025-10-11 | Subhash | 54.4178 | 2.8641 | TA325 | 236/0 | Completed
2025-09-24 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-24 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-24 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-24 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.2376 | 3.4399 | TA325 | 234/0 | Completed
2025-09-24 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-24 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-09-24 | 2025-09-19 | 2025-10-05 | Nan | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-24 | 2025-09-24 | 2025-10-05 | Nan | 54.4178 | 4.5348 | TA325 | 242/0 | Completed
2025-09-24 | 2025-09-24 | 2025-10-06 | Nan | 36.0448 | 2.7727 | TA325 | 237/5 | Completed
2025-09-24 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-24 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-24 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-09-24 | 2025-09-23 | 2025-10-11 | Subhash | 54.4178 | 2.8641 | TA325 | 236/0 | Completed
2025-09-24 | 2025-09-24 | 2025-10-03 | Sukhrridin | 36.0448 | 3.6045 | TA325 | 237/3 | Completed
2025-09-25 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-25 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-25 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-25 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.2376 | 3.4399 | TA325 | 234/0 | Completed
2025-09-25 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-25 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-09-25 | 2025-09-19 | 2025-10-05 | Nan | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-25 | 2025-09-24 | 2025-10-05 | Nan | 54.4178 | 4.5348 | TA325 | 242/0 | Completed
2025-09-25 | 2025-09-24 | 2025-10-06 | Nan | 36.0448 | 2.7727 | TA325 | 237/5 | Completed
2025-09-25 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-25 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-25 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-09-25 | 2025-09-23 | 2025-10-11 | Subhash | 54.4178 | 2.8641 | TA325 | 236/0 | Completed
2025-09-25 | 2025-09-24 | 2025-10-03 | Sukhrridin | 36.0448 | 3.6045 | TA325 | 237/3 | Completed
2025-09-26 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-26 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-26 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-26 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.2376 | 3.4399 | TA325 | 234/0 | Completed
2025-09-26 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-26 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-09-26 | 2025-09-19 | 2025-10-05 | Nan | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-26 | 2025-09-24 | 2025-10-05 | Nan | 54.4178 | 4.5348 | TA325 | 242/0 | Completed
2025-09-26 | 2025-09-24 | 2025-10-06 | Nan | 36.0448 | 2.7727 | TA325 | 237/5 | Completed
2025-09-26 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-26 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-26 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-09-26 | 2025-09-23 | 2025-10-11 | Subhash | 54.4178 | 2.8641 | TA325 | 236/0 | Completed
2025-09-26 | 2025-09-24 | 2025-10-03 | Sukhrridin | 36.0448 | 3.6045 | TA325 | 237/3 | Completed
2025-09-27 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-27 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-27 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-27 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.2376 | 3.4399 | TA325 | 234/0 | Completed
2025-09-27 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-27 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-09-27 | 2025-09-19 | 2025-10-05 | Nan | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-27 | 2025-09-24 | 2025-10-05 | Nan | 54.4178 | 4.5348 | TA325 | 242/0 | Completed
2025-09-27 | 2025-09-24 | 2025-10-06 | Nan | 36.0448 | 2.7727 | TA325 | 237/5 | Completed
2025-09-27 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-27 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-27 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-09-27 | 2025-09-23 | 2025-10-11 | Subhash | 54.4178 | 2.8641 | TA325 | 236/0 | Completed
2025-09-27 | 2025-09-24 | 2025-10-03 | Sukhrridin | 36.0448 | 3.6045 | TA325 | 237/3 | Completed
2025-09-28 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-28 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-28 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-28 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.2376 | 3.4399 | TA325 | 234/0 | Completed
2025-09-28 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-28 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-09-28 | 2025-09-19 | 2025-10-05 | Nan | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-28 | 2025-09-24 | 2025-10-05 | Nan | 54.4178 | 4.5348 | TA325 | 242/0 | Completed
2025-09-28 | 2025-09-24 | 2025-10-06 | Nan | 36.0448 | 2.7727 | TA325 | 237/5 | Completed
2025-09-28 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-28 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-28 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-09-28 | 2025-09-23 | 2025-10-11 | Subhash | 54.4178 | 2.8641 | TA325 | 236/0 | Completed
2025-09-28 | 2025-09-24 | 2025-10-03 | Sukhrridin | 36.0448 | 3.6045 | TA325 | 237/3 | Completed
2025-09-29 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-29 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-29 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-29 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.2376 | 3.4399 | TA325 | 234/0 | Completed
2025-09-29 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-29 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-09-29 | 2025-09-19 | 2025-10-05 | Nan | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-29 | 2025-09-24 | 2025-10-05 | Nan | 54.4178 | 4.5348 | TA325 | 242/0 | Completed
2025-09-29 | 2025-09-24 | 2025-10-06 | Nan | 36.0448 | 2.7727 | TA325 | 237/5 | Completed
2025-09-29 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-29 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-29 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-09-29 | 2025-09-23 | 2025-10-11 | Subhash | 54.4178 | 2.8641 | TA325 | 236/0 | Completed
2025-09-29 | 2025-09-24 | 2025-10-03 | Sukhrridin | 36.0448 | 3.6045 | TA325 | 237/3 | Completed
2025-09-30 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-09-30 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-30 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-30 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.2376 | 3.4399 | TA325 | 234/0 | Completed
2025-09-30 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-09-30 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-09-30 | 2025-09-19 | 2025-10-05 | Nan | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-30 | 2025-09-24 | 2025-10-05 | Nan | 54.4178 | 4.5348 | TA325 | 242/0 | Completed
2025-09-30 | 2025-09-24 | 2025-10-06 | Nan | 36.0448 | 2.7727 | TA325 | 237/5 | Completed
2025-09-30 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-30 | 2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-30 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-09-30 | 2025-09-23 | 2025-10-11 | Subhash | 54.4178 | 2.8641 | TA325 | 236/0 | Completed
2025-09-30 | 2025-09-24 | 2025-10-03 | Sukhrridin | 36.0448 | 3.6045 | TA325 | 237/3 | Completed
2025-10-01 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-10-01 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-10-01 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-10-01 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.2376 | 3.4399 | TA325 | 234/0 | Completed
2025-10-01 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-01 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-10-01 | 2025-09-19 | 2025-10-05 | Nan | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-10-01 | 2025-09-24 | 2025-10-05 | Nan | 54.4178 | 4.5348 | TA325 | 242/0 | Completed
2025-10-01 | 2025-09-24 | 2025-10-06 | Nan | 36.0448 | 2.7727 | TA325 | 237/5 | Completed
2025-10-01 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-10-01 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-10-01 | 2025-09-23 | 2025-10-11 | Subhash | 54.4178 | 2.8641 | TA325 | 236/0 | Completed
2025-10-01 | 2025-09-24 | 2025-10-03 | Sukhrridin | 36.0448 | 3.6045 | TA325 | 237/3 | Completed
2025-10-02 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-10-02 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-10-02 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-10-02 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.2376 | 3.4399 | TA325 | 234/0 | Completed
2025-10-02 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-02 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-10-02 | 2025-09-19 | 2025-10-05 | Nan | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-10-02 | 2025-09-24 | 2025-10-05 | Nan | 54.4178 | 4.5348 | TA325 | 242/0 | Completed
2025-10-02 | 2025-09-24 | 2025-10-06 | Nan | 36.0448 | 2.7727 | TA325 | 237/5 | Completed
2025-10-02 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-10-02 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-10-02 | 2025-09-23 | 2025-10-11 | Subhash | 54.4178 | 2.8641 | TA325 | 236/0 | Completed
2025-10-02 | 2025-09-24 | 2025-10-03 | Sukhrridin | 36.0448 | 3.6045 | TA325 | 237/3 | Completed
2025-10-03 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-10-03 | 2025-10-03 | 2025-10-17 | Dildar Electrical 2 Pgcil | 39.4589 | 2.6306 | TA325 | 237/6 | Completed
2025-10-03 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-10-03 | 2025-10-03 | 2025-10-12 | Gokul Sarkar 1 | 36.0448 | 3.6045 | TA325 | 242/2 | Completed
2025-10-03 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-10-03 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.2376 | 3.4399 | TA325 | 234/0 | Completed
2025-10-03 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-03 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-10-03 | 2025-09-19 | 2025-10-05 | Nan | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-10-03 | 2025-09-24 | 2025-10-05 | Nan | 54.4178 | 4.5348 | TA325 | 242/0 | Completed
2025-10-03 | 2025-09-24 | 2025-10-06 | Nan | 36.0448 | 2.7727 | TA325 | 237/5 | Completed
2025-10-03 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-10-03 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-10-03 | 2025-09-23 | 2025-10-11 | Subhash | 54.4178 | 2.8641 | TA325 | 236/0 | Completed
2025-10-03 | 2025-09-24 | 2025-10-03 | Sukhrridin | 36.0448 | 3.6045 | TA325 | 237/3 | Completed
2025-10-04 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-10-04 | 2025-10-03 | 2025-10-17 | Dildar Electrical 2 Pgcil | 39.4589 | 2.6306 | TA325 | 237/6 | Completed
2025-10-04 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-10-04 | 2025-10-03 | 2025-10-12 | Gokul Sarkar 1 | 36.0448 | 3.6045 | TA325 | 242/2 | Completed
2025-10-04 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-10-04 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.2376 | 3.4399 | TA325 | 234/0 | Completed
2025-10-04 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-04 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-10-04 | 2025-09-19 | 2025-10-05 | Nan | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-10-04 | 2025-09-24 | 2025-10-05 | Nan | 54.4178 | 4.5348 | TA325 | 242/0 | Completed
2025-10-04 | 2025-09-24 | 2025-10-06 | Nan | 36.0448 | 2.7727 | TA325 | 237/5 | Completed
2025-10-04 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-10-04 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-10-04 | 2025-09-23 | 2025-10-11 | Subhash | 54.4178 | 2.8641 | TA325 | 236/0 | Completed
2025-10-04 | 2025-10-04 | 2025-10-17 | Sukruddin | 37.7305 | 2.695 | TA325 | 217A/2 | Completed
2025-10-05 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-10-05 | 2025-10-03 | 2025-10-17 | Dildar Electrical 2 Pgcil | 39.4589 | 2.6306 | TA325 | 237/6 | Completed
2025-10-05 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-10-05 | 2025-10-03 | 2025-10-12 | Gokul Sarkar 1 | 36.0448 | 3.6045 | TA325 | 242/2 | Completed
2025-10-05 | 2025-10-05 | 2025-10-15 | Jaman Mahto 1 Ratna Devi | 77.7181 | 7.0653 | TA325 | 244/0 | Completed
2025-10-05 | 2025-10-05 | 2025-10-19 | Jwala Singh | 141.874 | 9.4583 | TA325 | 206/0 | Completed
2025-10-05 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.2376 | 3.4399 | TA325 | 234/0 | Completed
2025-10-05 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-05 | 2025-10-05 | 2025-10-14 | Modina India 1 4 Pgcil | 36.0448 | 3.6045 | TA325 | 237/2 | Completed
2025-10-05 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-10-05 | 2025-10-05 | 2025-10-15 | Modina India 3 Pgcil | 37.7305 | 3.43 | TA325 | 229/3 | Completed
2025-10-05 | 2025-10-05 | 2025-10-16 | Muni Bibi 2 | 37.7305 | 3.1442 | TA325 | 237/1 | Completed
2025-10-05 | 2025-09-19 | 2025-10-05 | Nan | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-10-05 | 2025-09-24 | 2025-10-05 | Nan | 54.4178 | 4.5348 | TA325 | 242/0 | Completed
2025-10-05 | 2025-09-24 | 2025-10-06 | Nan | 36.0448 | 2.7727 | TA325 | 237/5 | Completed
2025-10-05 | 2025-10-05 | 2025-10-14 | Nasirudin | 74.6321 | 7.4632 | TA325 | 224/0 | Completed
2025-10-05 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-10-05 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-10-05 | 2025-09-23 | 2025-10-11 | Subhash | 54.4178 | 2.8641 | TA325 | 236/0 | Completed
2025-10-05 | 2025-10-05 | 2025-10-11 | Sukhrridin | 37.7305 | 5.3901 | TA325 | 237/4 | Completed
2025-10-05 | 2025-10-04 | 2025-10-17 | Sukruddin | 37.7305 | 2.695 | TA325 | 217A/2 | Completed
2025-10-06 | 2025-10-06 | 2025-10-17 | Anita Devi | 72.2376 | 6.0198 | TA325 | 233/0 | Completed
2025-10-06 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-10-06 | 2025-10-03 | 2025-10-17 | Dildar Electrical 2 Pgcil | 39.4589 | 2.6306 | TA325 | 237/6 | Completed
2025-10-06 | 2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-10-06 | 2025-10-03 | 2025-10-12 | Gokul Sarkar 1 | 36.0448 | 3.6045 | TA325 | 242/2 | Completed
2025-10-06 | 2025-10-06 | 2025-10-16 | Gokul Sarkar 2 | 65.7565 | 5.9779 | TA325 | 244/1 | Completed
2025-10-06 | 2025-10-05 | 2025-10-15 | Jaman Mahto 1 Ratna Devi | 77.7181 | 7.0653 | TA325 | 244/0 | Completed
2025-10-06 | 2025-10-05 | 2025-10-19 | Jwala Singh | 141.874 | 9.4583 | TA325 | 206/0 | Completed
2025-10-06 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.2376 | 3.4399 | TA325 | 234/0 | Completed
2025-10-06 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-06 | 2025-10-05 | 2025-10-14 | Modina India 1 4 Pgcil | 36.0448 | 3.6045 | TA325 | 237/2 | Completed
2025-10-06 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-10-06 | 2025-10-05 | 2025-10-15 | Modina India 3 Pgcil | 37.7305 | 3.43 | TA325 | 229/3 | Completed
2025-10-06 | 2025-10-05 | 2025-10-16 | Muni Bibi 2 | 37.7305 | 3.1442 | TA325 | 237/1 | Completed
2025-10-06 | 2025-09-24 | 2025-10-06 | Nan | 36.0448 | 2.7727 | TA325 | 237/5 | Completed
2025-10-06 | 2025-10-05 | 2025-10-14 | Nasirudin | 74.6321 | 7.4632 | TA325 | 224/0 | Completed
2025-10-06 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-10-06 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-10-06 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-10-06 | 2025-09-23 | 2025-10-11 | Subhash | 54.4178 | 2.8641 | TA325 | 236/0 | Completed
2025-10-06 | 2025-10-05 | 2025-10-11 | Sukhrridin | 37.7305 | 5.3901 | TA325 | 237/4 | Completed
2025-10-06 | 2025-10-04 | 2025-10-17 | Sukruddin | 37.7305 | 2.695 | TA325 | 217A/2 | Completed
2025-10-06 | 2025-10-06 | 2025-10-17 | Teklal Mahto | 37.7305 | 3.1442 | TA325 | 223/1 | Completed
2025-10-07 | 2025-10-06 | 2025-10-17 | Anita Devi | 72.2376 | 6.0198 | TA325 | 233/0 | Completed
2025-10-07 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-10-07 | 2025-10-03 | 2025-10-17 | Dildar Electrical 2 Pgcil | 39.4589 | 2.6306 | TA325 | 237/6 | Completed
2025-10-07 | 2025-10-03 | 2025-10-12 | Gokul Sarkar 1 | 36.0448 | 3.6045 | TA325 | 242/2 | Completed
2025-10-07 | 2025-10-06 | 2025-10-16 | Gokul Sarkar 2 | 65.7565 | 5.9779 | TA325 | 244/1 | Completed
2025-10-07 | 2025-10-05 | 2025-10-15 | Jaman Mahto 1 Ratna Devi | 77.7181 | 7.0653 | TA325 | 244/0 | Completed
2025-10-07 | 2025-10-05 | 2025-10-19 | Jwala Singh | 141.874 | 9.4583 | TA325 | 206/0 | Completed
2025-10-07 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.2376 | 3.4399 | TA325 | 234/0 | Completed
2025-10-07 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-07 | 2025-10-05 | 2025-10-14 | Modina India 1 4 Pgcil | 36.0448 | 3.6045 | TA325 | 237/2 | Completed
2025-10-07 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-10-07 | 2025-10-05 | 2025-10-15 | Modina India 3 Pgcil | 37.7305 | 3.43 | TA325 | 229/3 | Completed
2025-10-07 | 2025-10-05 | 2025-10-16 | Muni Bibi 2 | 37.7305 | 3.1442 | TA325 | 237/1 | Completed
2025-10-07 | 2025-10-05 | 2025-10-14 | Nasirudin | 74.6321 | 7.4632 | TA325 | 224/0 | Completed
2025-10-07 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-10-07 | 2025-10-07 | 2025-10-19 | Satish Kumar | 65.7565 | 5.0582 | TA325 | 243/0 | Completed
2025-10-07 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-10-07 | 2025-09-23 | 2025-10-11 | Subhash | 54.4178 | 2.8641 | TA325 | 236/0 | Completed
2025-10-07 | 2025-10-05 | 2025-10-11 | Sukhrridin | 37.7305 | 5.3901 | TA325 | 237/4 | Completed
2025-10-07 | 2025-10-04 | 2025-10-17 | Sukruddin | 37.7305 | 2.695 | TA325 | 217A/2 | Completed
2025-10-07 | 2025-10-06 | 2025-10-17 | Teklal Mahto | 37.7305 | 3.1442 | TA325 | 223/1 | Completed
2025-10-08 | 2025-10-06 | 2025-10-17 | Anita Devi | 72.2376 | 6.0198 | TA325 | 233/0 | Completed
2025-10-08 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-10-08 | 2025-10-03 | 2025-10-17 | Dildar Electrical 2 Pgcil | 39.4589 | 2.6306 | TA325 | 237/6 | Completed
2025-10-08 | 2025-10-08 | 2025-10-23 | Dildar Electrical 3 | 37.7305 | 2.3582 | TA325 | 229/5 | Completed
2025-10-08 | 2025-10-03 | 2025-10-12 | Gokul Sarkar 1 | 36.0448 | 3.6045 | TA325 | 242/2 | Completed
2025-10-08 | 2025-10-06 | 2025-10-16 | Gokul Sarkar 2 | 65.7565 | 5.9779 | TA325 | 244/1 | Completed
2025-10-08 | 2025-10-05 | 2025-10-15 | Jaman Mahto 1 Ratna Devi | 77.7181 | 7.0653 | TA325 | 244/0 | Completed
2025-10-08 | 2025-10-05 | 2025-10-19 | Jwala Singh | 141.874 | 9.4583 | TA325 | 206/0 | Completed
2025-10-08 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.2376 | 3.4399 | TA325 | 234/0 | Completed
2025-10-08 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-08 | 2025-10-05 | 2025-10-14 | Modina India 1 4 Pgcil | 36.0448 | 3.6045 | TA325 | 237/2 | Completed
2025-10-08 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-10-08 | 2025-10-05 | 2025-10-15 | Modina India 3 Pgcil | 37.7305 | 3.43 | TA325 | 229/3 | Completed
2025-10-08 | 2025-10-08 | 2025-10-19 | Muni Bibi 1 | 44.7282 | 3.7274 | TA325 | 225/1 | Completed
2025-10-08 | 2025-10-05 | 2025-10-16 | Muni Bibi 2 | 37.7305 | 3.1442 | TA325 | 237/1 | Completed
2025-10-08 | 2025-10-05 | 2025-10-14 | Nasirudin | 74.6321 | 7.4632 | TA325 | 224/0 | Completed
2025-10-08 | 2025-10-08 | 2025-10-16 | Rahul Kumar | 80.408 | 8.9342 | TA325 | 247/0 | Completed
2025-10-08 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-10-08 | 2025-10-08 | 2025-10-18 | Sakila Khatun | 65.7565 | 5.9779 | TA325 | 241/0 | Completed
2025-10-08 | 2025-10-07 | 2025-10-19 | Satish Kumar | 65.7565 | 5.0582 | TA325 | 243/0 | Completed
2025-10-08 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-10-08 | 2025-09-23 | 2025-10-11 | Subhash | 54.4178 | 2.8641 | TA325 | 236/0 | Completed
2025-10-08 | 2025-10-05 | 2025-10-11 | Sukhrridin | 37.7305 | 5.3901 | TA325 | 237/4 | Completed
2025-10-08 | 2025-10-04 | 2025-10-17 | Sukruddin | 37.7305 | 2.695 | TA325 | 217A/2 | Completed
2025-10-08 | 2025-10-06 | 2025-10-17 | Teklal Mahto | 37.7305 | 3.1442 | TA325 | 223/1 | Completed
2025-10-09 | 2025-10-06 | 2025-10-17 | Anita Devi | 72.2376 | 6.0198 | TA325 | 233/0 | Completed
2025-10-09 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-10-09 | 2025-10-03 | 2025-10-17 | Dildar Electrical 2 Pgcil | 39.4589 | 2.6306 | TA325 | 237/6 | Completed
2025-10-09 | 2025-10-08 | 2025-10-23 | Dildar Electrical 3 | 37.7305 | 2.3582 | TA325 | 229/5 | Completed
2025-10-09 | 2025-10-03 | 2025-10-12 | Gokul Sarkar 1 | 36.0448 | 3.6045 | TA325 | 242/2 | Completed
2025-10-09 | 2025-10-06 | 2025-10-16 | Gokul Sarkar 2 | 65.7565 | 5.9779 | TA325 | 244/1 | Completed
2025-10-09 | 2025-10-05 | 2025-10-15 | Jaman Mahto 1 Ratna Devi | 77.7181 | 7.0653 | TA325 | 244/0 | Completed
2025-10-09 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-10-09 | 2025-10-05 | 2025-10-19 | Jwala Singh | 141.874 | 9.4583 | TA325 | 206/0 | Completed
2025-10-09 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-09 | 2025-10-05 | 2025-10-14 | Modina India 1 4 Pgcil | 36.0448 | 3.6045 | TA325 | 237/2 | Completed
2025-10-09 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-10-09 | 2025-10-05 | 2025-10-15 | Modina India 3 Pgcil | 37.7305 | 3.43 | TA325 | 229/3 | Completed
2025-10-09 | 2025-10-08 | 2025-10-19 | Muni Bibi 1 | 44.7282 | 3.7274 | TA325 | 225/1 | Completed
2025-10-09 | 2025-10-05 | 2025-10-16 | Muni Bibi 2 | 37.7305 | 3.1442 | TA325 | 237/1 | Completed
2025-10-09 | 2025-10-05 | 2025-10-14 | Nasirudin | 74.6321 | 7.4632 | TA325 | 224/0 | Completed
2025-10-09 | 2025-10-08 | 2025-10-16 | Rahul Kumar | 80.408 | 8.9342 | TA325 | 247/0 | Completed
2025-10-09 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-10-09 | 2025-10-08 | 2025-10-18 | Sakila Khatun | 65.7565 | 5.9779 | TA325 | 241/0 | Completed
2025-10-09 | 2025-10-07 | 2025-10-19 | Satish Kumar | 65.7565 | 5.0582 | TA325 | 243/0 | Completed
2025-10-09 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-10-09 | 2025-09-23 | 2025-10-11 | Subhash | 54.4178 | 2.8641 | TA325 | 236/0 | Completed
2025-10-09 | 2025-10-05 | 2025-10-11 | Sukhrridin | 37.7305 | 5.3901 | TA325 | 237/4 | Completed
2025-10-09 | 2025-10-04 | 2025-10-17 | Sukruddin | 37.7305 | 2.695 | TA325 | 217A/2 | Completed
2025-10-09 | 2025-10-06 | 2025-10-17 | Teklal Mahto | 37.7305 | 3.1442 | TA325 | 223/1 | Completed
2025-10-10 | 2025-10-06 | 2025-10-17 | Anita Devi | 72.2376 | 6.0198 | TA325 | 233/0 | Completed
2025-10-10 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-10-10 | 2025-10-03 | 2025-10-17 | Dildar Electrical 2 Pgcil | 39.4589 | 2.6306 | TA325 | 237/6 | Completed
2025-10-10 | 2025-10-08 | 2025-10-23 | Dildar Electrical 3 | 37.7305 | 2.3582 | TA325 | 229/5 | Completed
2025-10-10 | 2025-10-10 | 2025-10-24 | Dildar Electricals 1 Pgcil | 39.4589 | 2.6306 | TA325 | 247/2 | Completed
2025-10-10 | 2025-10-03 | 2025-10-12 | Gokul Sarkar 1 | 36.0448 | 3.6045 | TA325 | 242/2 | Completed
2025-10-10 | 2025-10-06 | 2025-10-16 | Gokul Sarkar 2 | 65.7565 | 5.9779 | TA325 | 244/1 | Completed
2025-10-10 | 2025-10-05 | 2025-10-15 | Jaman Mahto 1 Ratna Devi | 77.7181 | 7.0653 | TA325 | 244/0 | Completed
2025-10-10 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-10-10 | 2025-10-05 | 2025-10-19 | Jwala Singh | 141.874 | 9.4583 | TA325 | 206/0 | Completed
2025-10-10 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-10 | 2025-10-05 | 2025-10-14 | Modina India 1 4 Pgcil | 36.0448 | 3.6045 | TA325 | 237/2 | Completed
2025-10-10 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-10-10 | 2025-10-05 | 2025-10-15 | Modina India 3 Pgcil | 37.7305 | 3.43 | TA325 | 229/3 | Completed
2025-10-10 | 2025-10-08 | 2025-10-19 | Muni Bibi 1 | 44.7282 | 3.7274 | TA325 | 225/1 | Completed
2025-10-10 | 2025-10-05 | 2025-10-16 | Muni Bibi 2 | 37.7305 | 3.1442 | TA325 | 237/1 | Completed
2025-10-10 | 2025-10-05 | 2025-10-14 | Nasirudin | 74.6321 | 7.4632 | TA325 | 224/0 | Completed
2025-10-10 | 2025-10-08 | 2025-10-16 | Rahul Kumar | 80.408 | 8.9342 | TA325 | 247/0 | Completed
2025-10-10 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-10-10 | 2025-10-08 | 2025-10-18 | Sakila Khatun | 65.7565 | 5.9779 | TA325 | 241/0 | Completed
2025-10-10 | 2025-10-07 | 2025-10-19 | Satish Kumar | 65.7565 | 5.0582 | TA325 | 243/0 | Completed
2025-10-10 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-10-10 | 2025-09-23 | 2025-10-11 | Subhash | 54.4178 | 2.8641 | TA325 | 236/0 | Completed
2025-10-10 | 2025-10-05 | 2025-10-11 | Sukhrridin | 37.7305 | 5.3901 | TA325 | 237/4 | Completed
2025-10-10 | 2025-10-04 | 2025-10-17 | Sukruddin | 37.7305 | 2.695 | TA325 | 217A/2 | Completed
2025-10-10 | 2025-10-06 | 2025-10-17 | Teklal Mahto | 37.7305 | 3.1442 | TA325 | 223/1 | Completed
2025-10-11 | 2025-10-06 | 2025-10-17 | Anita Devi | 72.2376 | 6.0198 | TA325 | 233/0 | Completed
2025-10-11 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-10-11 | 2025-10-03 | 2025-10-17 | Dildar Electrical 2 Pgcil | 39.4589 | 2.6306 | TA325 | 237/6 | Completed
2025-10-11 | 2025-10-08 | 2025-10-23 | Dildar Electrical 3 | 37.7305 | 2.3582 | TA325 | 229/5 | Completed
2025-10-11 | 2025-10-10 | 2025-10-24 | Dildar Electricals 1 Pgcil | 39.4589 | 2.6306 | TA325 | 247/2 | Completed
2025-10-11 | 2025-10-03 | 2025-10-12 | Gokul Sarkar 1 | 36.0448 | 3.6045 | TA325 | 242/2 | Completed
2025-10-11 | 2025-10-06 | 2025-10-16 | Gokul Sarkar 2 | 65.7565 | 5.9779 | TA325 | 244/1 | Completed
2025-10-11 | 2025-10-05 | 2025-10-15 | Jaman Mahto 1 Ratna Devi | 77.7181 | 7.0653 | TA325 | 244/0 | Completed
2025-10-11 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-10-11 | 2025-10-05 | 2025-10-19 | Jwala Singh | 141.874 | 9.4583 | TA325 | 206/0 | Completed
2025-10-11 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-11 | 2025-10-05 | 2025-10-14 | Modina India 1 4 Pgcil | 36.0448 | 3.6045 | TA325 | 237/2 | Completed
2025-10-11 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-10-11 | 2025-10-05 | 2025-10-15 | Modina India 3 Pgcil | 37.7305 | 3.43 | TA325 | 229/3 | Completed
2025-10-11 | 2025-10-08 | 2025-10-19 | Muni Bibi 1 | 44.7282 | 3.7274 | TA325 | 225/1 | Completed
2025-10-11 | 2025-10-05 | 2025-10-16 | Muni Bibi 2 | 37.7305 | 3.1442 | TA325 | 237/1 | Completed
2025-10-11 | 2025-10-05 | 2025-10-14 | Nasirudin | 74.6321 | 7.4632 | TA325 | 224/0 | Completed
2025-10-11 | 2025-10-08 | 2025-10-16 | Rahul Kumar | 80.408 | 8.9342 | TA325 | 247/0 | Completed
2025-10-11 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-10-11 | 2025-10-08 | 2025-10-18 | Sakila Khatun | 65.7565 | 5.9779 | TA325 | 241/0 | Completed
2025-10-11 | 2025-10-07 | 2025-10-19 | Satish Kumar | 65.7565 | 5.0582 | TA325 | 243/0 | Completed
2025-10-11 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-10-11 | 2025-09-23 | 2025-10-11 | Subhash | 54.4178 | 2.8641 | TA325 | 236/0 | Completed
2025-10-11 | 2025-10-05 | 2025-10-11 | Sukhrridin | 37.7305 | 5.3901 | TA325 | 237/4 | Completed
2025-10-11 | 2025-10-04 | 2025-10-17 | Sukruddin | 37.7305 | 2.695 | TA325 | 217A/2 | Completed
2025-10-11 | 2025-10-06 | 2025-10-17 | Teklal Mahto | 37.7305 | 3.1442 | TA325 | 223/1 | Completed
2025-10-12 | 2025-10-06 | 2025-10-17 | Anita Devi | 72.2376 | 6.0198 | TA325 | 233/0 | Completed
2025-10-12 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-10-12 | 2025-10-03 | 2025-10-17 | Dildar Electrical 2 Pgcil | 39.4589 | 2.6306 | TA325 | 237/6 | Completed
2025-10-12 | 2025-10-08 | 2025-10-23 | Dildar Electrical 3 | 37.7305 | 2.3582 | TA325 | 229/5 | Completed
2025-10-12 | 2025-10-10 | 2025-10-24 | Dildar Electricals 1 Pgcil | 39.4589 | 2.6306 | TA325 | 247/2 | Completed
2025-10-12 | 2025-10-03 | 2025-10-12 | Gokul Sarkar 1 | 36.0448 | 3.6045 | TA325 | 242/2 | Completed
2025-10-12 | 2025-10-06 | 2025-10-16 | Gokul Sarkar 2 | 65.7565 | 5.9779 | TA325 | 244/1 | Completed
2025-10-12 | 2025-10-05 | 2025-10-15 | Jaman Mahto 1 Ratna Devi | 77.7181 | 7.0653 | TA325 | 244/0 | Completed
2025-10-12 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-10-12 | 2025-10-05 | 2025-10-19 | Jwala Singh | 141.874 | 9.4583 | TA325 | 206/0 | Completed
2025-10-12 | 2025-10-12 | 2025-10-19 | Md Akhtar | 66.2679 | 8.2835 | TA325 | 235/0 | Completed
2025-10-12 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-10-12 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-12 | 2025-10-05 | 2025-10-14 | Modina India 1 4 Pgcil | 36.0448 | 3.6045 | TA325 | 237/2 | Completed
2025-10-12 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-10-12 | 2025-10-05 | 2025-10-15 | Modina India 3 Pgcil | 37.7305 | 3.43 | TA325 | 229/3 | Completed
2025-10-12 | 2025-10-08 | 2025-10-19 | Muni Bibi 1 | 44.7282 | 3.7274 | TA325 | 225/1 | Completed
2025-10-12 | 2025-10-05 | 2025-10-16 | Muni Bibi 2 | 37.7305 | 3.1442 | TA325 | 237/1 | Completed
2025-10-12 | 2025-10-05 | 2025-10-14 | Nasirudin | 74.6321 | 7.4632 | TA325 | 224/0 | Completed
2025-10-12 | 2025-10-12 | 2025-10-23 | Nasirudin 2 | 80.408 | 6.7007 | TA325 | 225/0 | Completed
2025-10-12 | 2025-10-08 | 2025-10-16 | Rahul Kumar | 80.408 | 8.9342 | TA325 | 247/0 | Completed
2025-10-12 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-10-12 | 2025-10-08 | 2025-10-18 | Sakila Khatun | 65.7565 | 5.9779 | TA325 | 241/0 | Completed
2025-10-12 | 2025-10-07 | 2025-10-19 | Satish Kumar | 65.7565 | 5.0582 | TA325 | 243/0 | Completed
2025-10-12 | 2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-10-12 | 2025-10-04 | 2025-10-17 | Sukruddin | 37.7305 | 2.695 | TA325 | 217A/2 | Completed
2025-10-12 | 2025-10-06 | 2025-10-17 | Teklal Mahto | 37.7305 | 3.1442 | TA325 | 223/1 | Completed
2025-10-13 | 2025-10-06 | 2025-10-17 | Anita Devi | 72.2376 | 6.0198 | TA325 | 233/0 | Completed
2025-10-13 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-10-13 | 2025-10-03 | 2025-10-17 | Dildar Electrical 2 Pgcil | 39.4589 | 2.6306 | TA325 | 237/6 | Completed
2025-10-13 | 2025-10-08 | 2025-10-23 | Dildar Electrical 3 | 37.7305 | 2.3582 | TA325 | 229/5 | Completed
2025-10-13 | 2025-10-10 | 2025-10-24 | Dildar Electricals 1 Pgcil | 39.4589 | 2.6306 | TA325 | 247/2 | Completed
2025-10-13 | 2025-10-06 | 2025-10-16 | Gokul Sarkar 2 | 65.7565 | 5.9779 | TA325 | 244/1 | Completed
2025-10-13 | 2025-10-05 | 2025-10-15 | Jaman Mahto 1 Ratna Devi | 77.7181 | 7.0653 | TA325 | 244/0 | Completed
2025-10-13 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-10-13 | 2025-10-05 | 2025-10-19 | Jwala Singh | 141.874 | 9.4583 | TA325 | 206/0 | Completed
2025-10-13 | 2025-10-12 | 2025-10-19 | Md Akhtar | 66.2679 | 8.2835 | TA325 | 235/0 | Completed
2025-10-13 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-10-13 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-13 | 2025-10-05 | 2025-10-14 | Modina India 1 4 Pgcil | 36.0448 | 3.6045 | TA325 | 237/2 | Completed
2025-10-13 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-10-13 | 2025-10-05 | 2025-10-15 | Modina India 3 Pgcil | 37.7305 | 3.43 | TA325 | 229/3 | Completed
2025-10-13 | 2025-10-08 | 2025-10-19 | Muni Bibi 1 | 44.7282 | 3.7274 | TA325 | 225/1 | Completed
2025-10-13 | 2025-10-05 | 2025-10-16 | Muni Bibi 2 | 37.7305 | 3.1442 | TA325 | 237/1 | Completed
2025-10-13 | 2025-10-05 | 2025-10-14 | Nasirudin | 74.6321 | 7.4632 | TA325 | 224/0 | Completed
2025-10-13 | 2025-10-12 | 2025-10-23 | Nasirudin 2 | 80.408 | 6.7007 | TA325 | 225/0 | Completed
2025-10-13 | 2025-10-08 | 2025-10-16 | Rahul Kumar | 80.408 | 8.9342 | TA325 | 247/0 | Completed
2025-10-13 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-10-13 | 2025-10-08 | 2025-10-18 | Sakila Khatun | 65.7565 | 5.9779 | TA325 | 241/0 | Completed
2025-10-13 | 2025-10-07 | 2025-10-19 | Satish Kumar | 65.7565 | 5.0582 | TA325 | 243/0 | Completed
2025-10-13 | 2025-10-13 | 2025-10-24 | Subhash | 94.4077 | 7.8673 | TA325 | 231/0 | Completed
2025-10-13 | 2025-10-04 | 2025-10-17 | Sukruddin | 37.7305 | 2.695 | TA325 | 217A/2 | Completed
2025-10-13 | 2025-10-06 | 2025-10-17 | Teklal Mahto | 37.7305 | 3.1442 | TA325 | 223/1 | Completed
2025-10-14 | 2025-10-06 | 2025-10-17 | Anita Devi | 72.2376 | 6.0198 | TA325 | 233/0 | Completed
2025-10-14 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-10-14 | 2025-10-03 | 2025-10-17 | Dildar Electrical 2 Pgcil | 39.4589 | 2.6306 | TA325 | 237/6 | Completed
2025-10-14 | 2025-10-08 | 2025-10-23 | Dildar Electrical 3 | 37.7305 | 2.3582 | TA325 | 229/5 | Completed
2025-10-14 | 2025-10-10 | 2025-10-24 | Dildar Electricals 1 Pgcil | 39.4589 | 2.6306 | TA325 | 247/2 | Completed
2025-10-14 | 2025-10-06 | 2025-10-16 | Gokul Sarkar 2 | 65.7565 | 5.9779 | TA325 | 244/1 | Completed
2025-10-14 | 2025-10-14 | 2025-11-07 | Imadul Haque | 80.408 | 3.2163 | TA325 | 218/0 | Completed
2025-10-14 | 2025-10-05 | 2025-10-15 | Jaman Mahto 1 Ratna Devi | 77.7181 | 7.0653 | TA325 | 244/0 | Completed
2025-10-14 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-10-14 | 2025-10-05 | 2025-10-19 | Jwala Singh | 141.874 | 9.4583 | TA325 | 206/0 | Completed
2025-10-14 | 2025-10-12 | 2025-10-19 | Md Akhtar | 66.2679 | 8.2835 | TA325 | 235/0 | Completed
2025-10-14 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-10-14 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-14 | 2025-10-05 | 2025-10-14 | Modina India 1 4 Pgcil | 36.0448 | 3.6045 | TA325 | 237/2 | Completed
2025-10-14 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-10-14 | 2025-10-05 | 2025-10-15 | Modina India 3 Pgcil | 37.7305 | 3.43 | TA325 | 229/3 | Completed
2025-10-14 | 2025-10-08 | 2025-10-19 | Muni Bibi 1 | 44.7282 | 3.7274 | TA325 | 225/1 | Completed
2025-10-14 | 2025-10-05 | 2025-10-16 | Muni Bibi 2 | 37.7305 | 3.1442 | TA325 | 237/1 | Completed
2025-10-14 | 2025-10-05 | 2025-10-14 | Nasirudin | 74.6321 | 7.4632 | TA325 | 224/0 | Completed
2025-10-14 | 2025-10-12 | 2025-10-23 | Nasirudin 2 | 80.408 | 6.7007 | TA325 | 225/0 | Completed
2025-10-14 | 2025-10-14 | 2025-10-19 | Prayag Mahto | 36.0448 | 6.0075 | TA325 | 242/3 | Completed
2025-10-14 | 2025-10-08 | 2025-10-16 | Rahul Kumar | 80.408 | 8.9342 | TA325 | 247/0 | Completed
2025-10-14 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-10-14 | 2025-10-08 | 2025-10-18 | Sakila Khatun | 65.7565 | 5.9779 | TA325 | 241/0 | Completed
2025-10-14 | 2025-10-07 | 2025-10-19 | Satish Kumar | 65.7565 | 5.0582 | TA325 | 243/0 | Completed
2025-10-14 | 2025-10-13 | 2025-10-24 | Subhash | 94.4077 | 7.8673 | TA325 | 231/0 | Completed
2025-10-14 | 2025-10-04 | 2025-10-17 | Sukruddin | 37.7305 | 2.695 | TA325 | 217A/2 | Completed
2025-10-14 | 2025-10-06 | 2025-10-17 | Teklal Mahto | 37.7305 | 3.1442 | TA325 | 223/1 | Completed
2025-10-15 | 2025-10-06 | 2025-10-17 | Anita Devi | 72.2376 | 6.0198 | TA325 | 233/0 | Completed
2025-10-15 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-10-15 | 2025-10-03 | 2025-10-17 | Dildar Electrical 2 Pgcil | 39.4589 | 2.6306 | TA325 | 237/6 | Completed
2025-10-15 | 2025-10-08 | 2025-10-23 | Dildar Electrical 3 | 37.7305 | 2.3582 | TA325 | 229/5 | Completed
2025-10-15 | 2025-10-10 | 2025-10-24 | Dildar Electricals 1 Pgcil | 39.4589 | 2.6306 | TA325 | 247/2 | Completed
2025-10-15 | 2025-10-06 | 2025-10-16 | Gokul Sarkar 2 | 65.7565 | 5.9779 | TA325 | 244/1 | Completed
2025-10-15 | 2025-10-14 | 2025-11-07 | Imadul Haque | 80.408 | 3.2163 | TA325 | 218/0 | Completed
2025-10-15 | 2025-10-05 | 2025-10-15 | Jaman Mahto 1 Ratna Devi | 77.7181 | 7.0653 | TA325 | 244/0 | Completed
2025-10-15 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-10-15 | 2025-10-05 | 2025-10-19 | Jwala Singh | 141.874 | 9.4583 | TA325 | 206/0 | Completed
2025-10-15 | 2025-10-12 | 2025-10-19 | Md Akhtar | 66.2679 | 8.2835 | TA325 | 235/0 | Completed
2025-10-15 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-10-15 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-15 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-10-15 | 2025-10-05 | 2025-10-15 | Modina India 3 Pgcil | 37.7305 | 3.43 | TA325 | 229/3 | Completed
2025-10-15 | 2025-10-08 | 2025-10-19 | Muni Bibi 1 | 44.7282 | 3.7274 | TA325 | 225/1 | Completed
2025-10-15 | 2025-10-05 | 2025-10-16 | Muni Bibi 2 | 37.7305 | 3.1442 | TA325 | 237/1 | Completed
2025-10-15 | 2025-10-12 | 2025-10-23 | Nasirudin 2 | 80.408 | 6.7007 | TA325 | 225/0 | Completed
2025-10-15 | 2025-10-14 | 2025-10-19 | Prayag Mahto | 36.0448 | 6.0075 | TA325 | 242/3 | Completed
2025-10-15 | 2025-10-08 | 2025-10-16 | Rahul Kumar | 80.408 | 8.9342 | TA325 | 247/0 | Completed
2025-10-15 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-10-15 | 2025-10-08 | 2025-10-18 | Sakila Khatun | 65.7565 | 5.9779 | TA325 | 241/0 | Completed
2025-10-15 | 2025-10-07 | 2025-10-19 | Satish Kumar | 65.7565 | 5.0582 | TA325 | 243/0 | Completed
2025-10-15 | 2025-10-13 | 2025-10-24 | Subhash | 94.4077 | 7.8673 | TA325 | 231/0 | Completed
2025-10-15 | 2025-10-04 | 2025-10-17 | Sukruddin | 37.7305 | 2.695 | TA325 | 217A/2 | Completed
2025-10-15 | 2025-10-06 | 2025-10-17 | Teklal Mahto | 37.7305 | 3.1442 | TA325 | 223/1 | Completed
2025-10-16 | 2025-10-06 | 2025-10-17 | Anita Devi | 72.2376 | 6.0198 | TA325 | 233/0 | Completed
2025-10-16 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-10-16 | 2025-10-03 | 2025-10-17 | Dildar Electrical 2 Pgcil | 39.4589 | 2.6306 | TA325 | 237/6 | Completed
2025-10-16 | 2025-10-08 | 2025-10-23 | Dildar Electrical 3 | 37.7305 | 2.3582 | TA325 | 229/5 | Completed
2025-10-16 | 2025-10-10 | 2025-10-24 | Dildar Electricals 1 Pgcil | 39.4589 | 2.6306 | TA325 | 247/2 | Completed
2025-10-16 | 2025-10-06 | 2025-10-16 | Gokul Sarkar 2 | 65.7565 | 5.9779 | TA325 | 244/1 | Completed
2025-10-16 | 2025-10-14 | 2025-11-07 | Imadul Haque | 80.408 | 3.2163 | TA325 | 218/0 | Completed
2025-10-16 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-10-16 | 2025-10-05 | 2025-10-19 | Jwala Singh | 141.874 | 9.4583 | TA325 | 206/0 | Completed
2025-10-16 | 2025-10-12 | 2025-10-19 | Md Akhtar | 66.2679 | 8.2835 | TA325 | 235/0 | Completed
2025-10-16 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-10-16 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-16 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-10-16 | 2025-10-08 | 2025-10-19 | Muni Bibi 1 | 44.7282 | 3.7274 | TA325 | 225/1 | Completed
2025-10-16 | 2025-10-05 | 2025-10-16 | Muni Bibi 2 | 37.7305 | 3.1442 | TA325 | 237/1 | Completed
2025-10-16 | 2025-10-12 | 2025-10-23 | Nasirudin 2 | 80.408 | 6.7007 | TA325 | 225/0 | Completed
2025-10-16 | 2025-10-14 | 2025-10-19 | Prayag Mahto | 36.0448 | 6.0075 | TA325 | 242/3 | Completed
2025-10-16 | 2025-10-08 | 2025-10-16 | Rahul Kumar | 80.408 | 8.9342 | TA325 | 247/0 | Completed
2025-10-16 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-10-16 | 2025-10-08 | 2025-10-18 | Sakila Khatun | 65.7565 | 5.9779 | TA325 | 241/0 | Completed
2025-10-16 | 2025-10-07 | 2025-10-19 | Satish Kumar | 65.7565 | 5.0582 | TA325 | 243/0 | Completed
2025-10-16 | 2025-10-13 | 2025-10-24 | Subhash | 94.4077 | 7.8673 | TA325 | 231/0 | Completed
2025-10-16 | 2025-10-04 | 2025-10-17 | Sukruddin | 37.7305 | 2.695 | TA325 | 217A/2 | Completed
2025-10-16 | 2025-10-06 | 2025-10-17 | Teklal Mahto | 37.7305 | 3.1442 | TA325 | 223/1 | Completed
2025-10-17 | 2025-10-06 | 2025-10-17 | Anita Devi | 72.2376 | 6.0198 | TA325 | 233/0 | Completed
2025-10-17 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-10-17 | 2025-10-03 | 2025-10-17 | Dildar Electrical 2 Pgcil | 39.4589 | 2.6306 | TA325 | 237/6 | Completed
2025-10-17 | 2025-10-08 | 2025-10-23 | Dildar Electrical 3 | 37.7305 | 2.3582 | TA325 | 229/5 | Completed
2025-10-17 | 2025-10-10 | 2025-10-24 | Dildar Electricals 1 Pgcil | 39.4589 | 2.6306 | TA325 | 247/2 | Completed
2025-10-17 | 2025-10-17 | 2025-10-29 | Gokul 1 | 46.6235 | 3.5864 | TA325 | 185/1 | Completed
2025-10-17 | 2025-10-14 | 2025-11-07 | Imadul Haque | 80.408 | 3.2163 | TA325 | 218/0 | Completed
2025-10-17 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-10-17 | 2025-10-05 | 2025-10-19 | Jwala Singh | 141.874 | 9.4583 | TA325 | 206/0 | Completed
2025-10-17 | 2025-10-12 | 2025-10-19 | Md Akhtar | 66.2679 | 8.2835 | TA325 | 235/0 | Completed
2025-10-17 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-10-17 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-17 | 2025-10-17 | 2025-10-26 | Modina India 1 4 Pgcil | 36.0448 | 3.6045 | TA325 | 242/1 | Completed
2025-10-17 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-10-17 | 2025-10-17 | 2025-10-25 | Modina India 3 Pgcil | 37.7305 | 4.1923 | TA325 | 229/4 | Completed
2025-10-17 | 2025-10-08 | 2025-10-19 | Muni Bibi 1 | 44.7282 | 3.7274 | TA325 | 225/1 | Completed
2025-10-17 | 2025-10-12 | 2025-10-23 | Nasirudin 2 | 80.408 | 6.7007 | TA325 | 225/0 | Completed
2025-10-17 | 2025-10-14 | 2025-10-19 | Prayag Mahto | 36.0448 | 6.0075 | TA325 | 242/3 | Completed
2025-10-17 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-10-17 | 2025-10-08 | 2025-10-18 | Sakila Khatun | 65.7565 | 5.9779 | TA325 | 241/0 | Completed
2025-10-17 | 2025-10-07 | 2025-10-19 | Satish Kumar | 65.7565 | 5.0582 | TA325 | 243/0 | Completed
2025-10-17 | 2025-10-13 | 2025-10-24 | Subhash | 94.4077 | 7.8673 | TA325 | 231/0 | Completed
2025-10-17 | 2025-10-04 | 2025-10-17 | Sukruddin | 37.7305 | 2.695 | TA325 | 217A/2 | Completed
2025-10-17 | 2025-10-06 | 2025-10-17 | Teklal Mahto | 37.7305 | 3.1442 | TA325 | 223/1 | Completed
2025-10-18 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-10-18 | 2025-10-08 | 2025-10-23 | Dildar Electrical 3 | 37.7305 | 2.3582 | TA325 | 229/5 | Completed
2025-10-18 | 2025-10-10 | 2025-10-24 | Dildar Electricals 1 Pgcil | 39.4589 | 2.6306 | TA325 | 247/2 | Completed
2025-10-18 | 2025-10-17 | 2025-10-29 | Gokul 1 | 46.6235 | 3.5864 | TA325 | 185/1 | Completed
2025-10-18 | 2025-10-18 | 2025-10-29 | Gokul Sarkar 2 | 56.8632 | 4.7386 | TA325 | 222/1 | Completed
2025-10-18 | 2025-10-14 | 2025-11-07 | Imadul Haque | 80.408 | 3.2163 | TA325 | 218/0 | Completed
2025-10-18 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-10-18 | 2025-10-05 | 2025-10-19 | Jwala Singh | 141.874 | 9.4583 | TA325 | 206/0 | Completed
2025-10-18 | 2025-10-12 | 2025-10-19 | Md Akhtar | 66.2679 | 8.2835 | TA325 | 235/0 | Completed
2025-10-18 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-10-18 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-18 | 2025-10-17 | 2025-10-26 | Modina India 1 4 Pgcil | 36.0448 | 3.6045 | TA325 | 242/1 | Completed
2025-10-18 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-10-18 | 2025-10-17 | 2025-10-25 | Modina India 3 Pgcil | 37.7305 | 4.1923 | TA325 | 229/4 | Completed
2025-10-18 | 2025-10-08 | 2025-10-19 | Muni Bibi 1 | 44.7282 | 3.7274 | TA325 | 225/1 | Completed
2025-10-18 | 2025-10-12 | 2025-10-23 | Nasirudin 2 | 80.408 | 6.7007 | TA325 | 225/0 | Completed
2025-10-18 | 2025-10-14 | 2025-10-19 | Prayag Mahto | 36.0448 | 6.0075 | TA325 | 242/3 | Completed
2025-10-18 | 2025-10-18 | 2025-10-26 | Rahul Kumar | 82.2388 | 9.1376 | TA325 | 210/0 | Completed
2025-10-18 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-10-18 | 2025-10-08 | 2025-10-18 | Sakila Khatun | 65.7565 | 5.9779 | TA325 | 241/0 | Completed
2025-10-18 | 2025-10-07 | 2025-10-19 | Satish Kumar | 65.7565 | 5.0582 | TA325 | 243/0 | Completed
2025-10-18 | 2025-10-13 | 2025-10-24 | Subhash | 94.4077 | 7.8673 | TA325 | 231/0 | Completed
2025-10-19 | 2025-10-19 | 2025-11-01 | Anita Devi | 84.2993 | 6.0214 | TA325 | 232/0 | Completed
2025-10-19 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-10-19 | 2025-10-08 | 2025-10-23 | Dildar Electrical 3 | 37.7305 | 2.3582 | TA325 | 229/5 | Completed
2025-10-19 | 2025-10-10 | 2025-10-24 | Dildar Electricals 1 Pgcil | 39.4589 | 2.6306 | TA325 | 247/2 | Completed
2025-10-19 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-10-19 | 2025-10-17 | 2025-10-29 | Gokul 1 | 46.6235 | 3.5864 | TA325 | 185/1 | Completed
2025-10-19 | 2025-10-18 | 2025-10-29 | Gokul Sarkar 2 | 56.8632 | 4.7386 | TA325 | 222/1 | Completed
2025-10-19 | 2025-10-14 | 2025-11-07 | Imadul Haque | 80.408 | 3.2163 | TA325 | 218/0 | Completed
2025-10-19 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-10-19 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-10-19 | 2025-10-05 | 2025-10-19 | Jwala Singh | 141.874 | 9.4583 | TA325 | 206/0 | Completed
2025-10-19 | 2025-10-12 | 2025-10-19 | Md Akhtar | 66.2679 | 8.2835 | TA325 | 235/0 | Completed
2025-10-19 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-10-19 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-19 | 2025-10-17 | 2025-10-26 | Modina India 1 4 Pgcil | 36.0448 | 3.6045 | TA325 | 242/1 | Completed
2025-10-19 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-10-19 | 2025-10-17 | 2025-10-25 | Modina India 3 Pgcil | 37.7305 | 4.1923 | TA325 | 229/4 | Completed
2025-10-19 | 2025-10-08 | 2025-10-19 | Muni Bibi 1 | 44.7282 | 3.7274 | TA325 | 225/1 | Completed
2025-10-19 | 2025-10-12 | 2025-10-23 | Nasirudin 2 | 80.408 | 6.7007 | TA325 | 225/0 | Completed
2025-10-19 | 2025-10-14 | 2025-10-19 | Prayag Mahto | 36.0448 | 6.0075 | TA325 | 242/3 | Completed
2025-10-19 | 2025-10-18 | 2025-10-26 | Rahul Kumar | 82.2388 | 9.1376 | TA325 | 210/0 | Completed
2025-10-19 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-10-19 | 2025-10-07 | 2025-10-19 | Satish Kumar | 65.7565 | 5.0582 | TA325 | 243/0 | Completed
2025-10-19 | 2025-10-13 | 2025-10-24 | Subhash | 94.4077 | 7.8673 | TA325 | 231/0 | Completed
2025-10-20 | 2025-10-19 | 2025-11-01 | Anita Devi | 84.2993 | 6.0214 | TA325 | 232/0 | Completed
2025-10-20 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-10-20 | 2025-10-08 | 2025-10-23 | Dildar Electrical 3 | 37.7305 | 2.3582 | TA325 | 229/5 | Completed
2025-10-20 | 2025-10-10 | 2025-10-24 | Dildar Electricals 1 Pgcil | 39.4589 | 2.6306 | TA325 | 247/2 | Completed
2025-10-20 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-10-20 | 2025-10-17 | 2025-10-29 | Gokul 1 | 46.6235 | 3.5864 | TA325 | 185/1 | Completed
2025-10-20 | 2025-10-18 | 2025-10-29 | Gokul Sarkar 2 | 56.8632 | 4.7386 | TA325 | 222/1 | Completed
2025-10-20 | 2025-10-14 | 2025-11-07 | Imadul Haque | 80.408 | 3.2163 | TA325 | 218/0 | Completed
2025-10-20 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-10-20 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-10-20 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-10-20 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-20 | 2025-10-17 | 2025-10-26 | Modina India 1 4 Pgcil | 36.0448 | 3.6045 | TA325 | 242/1 | Completed
2025-10-20 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-10-20 | 2025-10-17 | 2025-10-25 | Modina India 3 Pgcil | 37.7305 | 4.1923 | TA325 | 229/4 | Completed
2025-10-20 | 2025-10-12 | 2025-10-23 | Nasirudin 2 | 80.408 | 6.7007 | TA325 | 225/0 | Completed
2025-10-20 | 2025-10-18 | 2025-10-26 | Rahul Kumar | 82.2388 | 9.1376 | TA325 | 210/0 | Completed
2025-10-20 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-10-20 | 2025-10-13 | 2025-10-24 | Subhash | 94.4077 | 7.8673 | TA325 | 231/0 | Completed
2025-10-21 | 2025-10-19 | 2025-11-01 | Anita Devi | 84.2993 | 6.0214 | TA325 | 232/0 | Completed
2025-10-21 | 2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-10-21 | 2025-10-08 | 2025-10-23 | Dildar Electrical 3 | 37.7305 | 2.3582 | TA325 | 229/5 | Completed
2025-10-21 | 2025-10-10 | 2025-10-24 | Dildar Electricals 1 Pgcil | 39.4589 | 2.6306 | TA325 | 247/2 | Completed
2025-10-21 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-10-21 | 2025-10-17 | 2025-10-29 | Gokul 1 | 46.6235 | 3.5864 | TA325 | 185/1 | Completed
2025-10-21 | 2025-10-18 | 2025-10-29 | Gokul Sarkar 2 | 56.8632 | 4.7386 | TA325 | 222/1 | Completed
2025-10-21 | 2025-10-14 | 2025-11-07 | Imadul Haque | 80.408 | 3.2163 | TA325 | 218/0 | Completed
2025-10-21 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-10-21 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-10-21 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-10-21 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-21 | 2025-10-17 | 2025-10-26 | Modina India 1 4 Pgcil | 36.0448 | 3.6045 | TA325 | 242/1 | Completed
2025-10-21 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-10-21 | 2025-10-17 | 2025-10-25 | Modina India 3 Pgcil | 37.7305 | 4.1923 | TA325 | 229/4 | Completed
2025-10-21 | 2025-10-12 | 2025-10-23 | Nasirudin 2 | 80.408 | 6.7007 | TA325 | 225/0 | Completed
2025-10-21 | 2025-10-18 | 2025-10-26 | Rahul Kumar | 82.2388 | 9.1376 | TA325 | 210/0 | Completed
2025-10-21 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-10-21 | 2025-10-13 | 2025-10-24 | Subhash | 94.4077 | 7.8673 | TA325 | 231/0 | Completed
2025-10-22 | 2025-10-19 | 2025-11-01 | Anita Devi | 84.2993 | 6.0214 | TA325 | 232/0 | Completed
2025-10-22 | 2025-10-08 | 2025-10-23 | Dildar Electrical 3 | 37.7305 | 2.3582 | TA325 | 229/5 | Completed
2025-10-22 | 2025-10-10 | 2025-10-24 | Dildar Electricals 1 Pgcil | 39.4589 | 2.6306 | TA325 | 247/2 | Completed
2025-10-22 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-10-22 | 2025-10-17 | 2025-10-29 | Gokul 1 | 46.6235 | 3.5864 | TA325 | 185/1 | Completed
2025-10-22 | 2025-10-18 | 2025-10-29 | Gokul Sarkar 2 | 56.8632 | 4.7386 | TA325 | 222/1 | Completed
2025-10-22 | 2025-10-14 | 2025-11-07 | Imadul Haque | 80.408 | 3.2163 | TA325 | 218/0 | Completed
2025-10-22 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-10-22 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-10-22 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-10-22 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-22 | 2025-10-17 | 2025-10-26 | Modina India 1 4 Pgcil | 36.0448 | 3.6045 | TA325 | 242/1 | Completed
2025-10-22 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-10-22 | 2025-10-17 | 2025-10-25 | Modina India 3 Pgcil | 37.7305 | 4.1923 | TA325 | 229/4 | Completed
2025-10-22 | 2025-10-22 | 2025-11-06 | Muni Bibi 1 2 | 63.509 | 3.9693 | TA325 | 227/0 | Completed
2025-10-22 | 2025-10-12 | 2025-10-23 | Nasirudin 2 | 80.408 | 6.7007 | TA325 | 225/0 | Completed
2025-10-22 | 2025-10-18 | 2025-10-26 | Rahul Kumar | 82.2388 | 9.1376 | TA325 | 210/0 | Completed
2025-10-22 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-10-22 | 2025-10-22 | 2025-11-13 | Sakila Khatun | 141.874 | 6.1684 | TA325 | 240/0 | Completed
2025-10-22 | 2025-10-13 | 2025-10-24 | Subhash | 94.4077 | 7.8673 | TA325 | 231/0 | Completed
2025-10-23 | 2025-10-19 | 2025-11-01 | Anita Devi | 84.2993 | 6.0214 | TA325 | 232/0 | Completed
2025-10-23 | 2025-10-08 | 2025-10-23 | Dildar Electrical 3 | 37.7305 | 2.3582 | TA325 | 229/5 | Completed
2025-10-23 | 2025-10-10 | 2025-10-24 | Dildar Electricals 1 Pgcil | 39.4589 | 2.6306 | TA325 | 247/2 | Completed
2025-10-23 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-10-23 | 2025-10-17 | 2025-10-29 | Gokul 1 | 46.6235 | 3.5864 | TA325 | 185/1 | Completed
2025-10-23 | 2025-10-18 | 2025-10-29 | Gokul Sarkar 2 | 56.8632 | 4.7386 | TA325 | 222/1 | Completed
2025-10-23 | 2025-10-14 | 2025-11-07 | Imadul Haque | 80.408 | 3.2163 | TA325 | 218/0 | Completed
2025-10-23 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-10-23 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-10-23 | 2025-10-23 | 2025-11-06 | Jwala Singh | 65.7565 | 4.3838 | TA325 | 211/0 | Completed
2025-10-23 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-10-23 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-23 | 2025-10-17 | 2025-10-26 | Modina India 1 4 Pgcil | 36.0448 | 3.6045 | TA325 | 242/1 | Completed
2025-10-23 | 2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-10-23 | 2025-10-17 | 2025-10-25 | Modina India 3 Pgcil | 37.7305 | 4.1923 | TA325 | 229/4 | Completed
2025-10-23 | 2025-10-22 | 2025-11-06 | Muni Bibi 1 2 | 63.509 | 3.9693 | TA325 | 227/0 | Completed
2025-10-23 | 2025-10-12 | 2025-10-23 | Nasirudin 2 | 80.408 | 6.7007 | TA325 | 225/0 | Completed
2025-10-23 | 2025-10-18 | 2025-10-26 | Rahul Kumar | 82.2388 | 9.1376 | TA325 | 210/0 | Completed
2025-10-23 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-10-23 | 2025-10-22 | 2025-11-13 | Sakila Khatun | 141.874 | 6.1684 | TA325 | 240/0 | Completed
2025-10-23 | 2025-10-13 | 2025-10-24 | Subhash | 94.4077 | 7.8673 | TA325 | 231/0 | Completed
2025-10-23 | 2025-10-23 | 2025-11-13 | Teklal Mahto | 64.2538 | 2.9206 | TA325 | 223/0 | Completed
2025-10-24 | 2025-10-19 | 2025-11-01 | Anita Devi | 84.2993 | 6.0214 | TA325 | 232/0 | Completed
2025-10-24 | 2025-10-10 | 2025-10-24 | Dildar Electricals 1 Pgcil | 39.4589 | 2.6306 | TA325 | 247/2 | Completed
2025-10-24 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-10-24 | 2025-10-17 | 2025-10-29 | Gokul 1 | 46.6235 | 3.5864 | TA325 | 185/1 | Completed
2025-10-24 | 2025-10-18 | 2025-10-29 | Gokul Sarkar 2 | 56.8632 | 4.7386 | TA325 | 222/1 | Completed
2025-10-24 | 2025-10-14 | 2025-11-07 | Imadul Haque | 80.408 | 3.2163 | TA325 | 218/0 | Completed
2025-10-24 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-10-24 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-10-24 | 2025-10-23 | 2025-11-06 | Jwala Singh | 65.7565 | 4.3838 | TA325 | 211/0 | Completed
2025-10-24 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-10-24 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-24 | 2025-10-17 | 2025-10-26 | Modina India 1 4 Pgcil | 36.0448 | 3.6045 | TA325 | 242/1 | Completed
2025-10-24 | 2025-10-17 | 2025-10-25 | Modina India 3 Pgcil | 37.7305 | 4.1923 | TA325 | 229/4 | Completed
2025-10-24 | 2025-10-22 | 2025-11-06 | Muni Bibi 1 2 | 63.509 | 3.9693 | TA325 | 227/0 | Completed
2025-10-24 | 2025-10-18 | 2025-10-26 | Rahul Kumar | 82.2388 | 9.1376 | TA325 | 210/0 | Completed
2025-10-24 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-10-24 | 2025-10-22 | 2025-11-13 | Sakila Khatun | 141.874 | 6.1684 | TA325 | 240/0 | Completed
2025-10-24 | 2025-10-13 | 2025-10-24 | Subhash | 94.4077 | 7.8673 | TA325 | 231/0 | Completed
2025-10-24 | 2025-10-24 | 2025-11-10 | Sukruddin | 72.2376 | 4.0132 | TA325 | 245/0 | Completed
2025-10-24 | 2025-10-23 | 2025-11-13 | Teklal Mahto | 64.2538 | 2.9206 | TA325 | 223/0 | Completed
2025-10-25 | 2025-10-19 | 2025-11-01 | Anita Devi | 84.2993 | 6.0214 | TA325 | 232/0 | Completed
2025-10-25 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-10-25 | 2025-10-17 | 2025-10-29 | Gokul 1 | 46.6235 | 3.5864 | TA325 | 185/1 | Completed
2025-10-25 | 2025-10-18 | 2025-10-29 | Gokul Sarkar 2 | 56.8632 | 4.7386 | TA325 | 222/1 | Completed
2025-10-25 | 2025-10-14 | 2025-11-07 | Imadul Haque | 80.408 | 3.2163 | TA325 | 218/0 | Completed
2025-10-25 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-10-25 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-10-25 | 2025-10-23 | 2025-11-06 | Jwala Singh | 65.7565 | 4.3838 | TA325 | 211/0 | Completed
2025-10-25 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-10-25 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-25 | 2025-10-17 | 2025-10-26 | Modina India 1 4 Pgcil | 36.0448 | 3.6045 | TA325 | 242/1 | Completed
2025-10-25 | 2025-10-17 | 2025-10-25 | Modina India 3 Pgcil | 37.7305 | 4.1923 | TA325 | 229/4 | Completed
2025-10-25 | 2025-10-22 | 2025-11-06 | Muni Bibi 1 2 | 63.509 | 3.9693 | TA325 | 227/0 | Completed
2025-10-25 | 2025-10-25 | 2025-11-08 | Nasirudin 2 | 63.509 | 4.2339 | TA325 | 229/1 | Completed
2025-10-25 | 2025-10-18 | 2025-10-26 | Rahul Kumar | 82.2388 | 9.1376 | TA325 | 210/0 | Completed
2025-10-25 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-10-25 | 2025-10-22 | 2025-11-13 | Sakila Khatun | 141.874 | 6.1684 | TA325 | 240/0 | Completed
2025-10-25 | 2025-10-24 | 2025-11-10 | Sukruddin | 72.2376 | 4.0132 | TA325 | 245/0 | Completed
2025-10-25 | 2025-10-23 | 2025-11-13 | Teklal Mahto | 64.2538 | 2.9206 | TA325 | 223/0 | Completed
2025-10-26 | 2025-10-19 | 2025-11-01 | Anita Devi | 84.2993 | 6.0214 | TA325 | 232/0 | Completed
2025-10-26 | 2025-10-26 | 2025-11-18 | Anjum | 94.4077 | 3.9337 | TA325 | 203/1 | Completed
2025-10-26 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-10-26 | 2025-10-17 | 2025-10-29 | Gokul 1 | 46.6235 | 3.5864 | TA325 | 185/1 | Completed
2025-10-26 | 2025-10-18 | 2025-10-29 | Gokul Sarkar 2 | 56.8632 | 4.7386 | TA325 | 222/1 | Completed
2025-10-26 | 2025-10-14 | 2025-11-07 | Imadul Haque | 80.408 | 3.2163 | TA325 | 218/0 | Completed
2025-10-26 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-10-26 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-10-26 | 2025-10-23 | 2025-11-06 | Jwala Singh | 65.7565 | 4.3838 | TA325 | 211/0 | Completed
2025-10-26 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-10-26 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-26 | 2025-10-17 | 2025-10-26 | Modina India 1 4 Pgcil | 36.0448 | 3.6045 | TA325 | 242/1 | Completed
2025-10-26 | 2025-10-22 | 2025-11-06 | Muni Bibi 1 2 | 63.509 | 3.9693 | TA325 | 227/0 | Completed
2025-10-26 | 2025-10-25 | 2025-11-08 | Nasirudin 2 | 63.509 | 4.2339 | TA325 | 229/1 | Completed
2025-10-26 | 2025-10-18 | 2025-10-26 | Rahul Kumar | 82.2388 | 9.1376 | TA325 | 210/0 | Completed
2025-10-26 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-10-26 | 2025-10-22 | 2025-11-13 | Sakila Khatun | 141.874 | 6.1684 | TA325 | 240/0 | Completed
2025-10-26 | 2025-10-24 | 2025-11-10 | Sukruddin | 72.2376 | 4.0132 | TA325 | 245/0 | Completed
2025-10-26 | 2025-10-23 | 2025-11-13 | Teklal Mahto | 64.2538 | 2.9206 | TA325 | 223/0 | Completed
2025-10-27 | 2025-10-19 | 2025-11-01 | Anita Devi | 84.2993 | 6.0214 | TA325 | 232/0 | Completed
2025-10-27 | 2025-10-26 | 2025-11-18 | Anjum | 94.4077 | 3.9337 | TA325 | 203/1 | Completed
2025-10-27 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-10-27 | 2025-10-17 | 2025-10-29 | Gokul 1 | 46.6235 | 3.5864 | TA325 | 185/1 | Completed
2025-10-27 | 2025-10-18 | 2025-10-29 | Gokul Sarkar 2 | 56.8632 | 4.7386 | TA325 | 222/1 | Completed
2025-10-27 | 2025-10-14 | 2025-11-07 | Imadul Haque | 80.408 | 3.2163 | TA325 | 218/0 | Completed
2025-10-27 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-10-27 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-10-27 | 2025-10-23 | 2025-11-06 | Jwala Singh | 65.7565 | 4.3838 | TA325 | 211/0 | Completed
2025-10-27 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-10-27 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-27 | 2025-10-22 | 2025-11-06 | Muni Bibi 1 2 | 63.509 | 3.9693 | TA325 | 227/0 | Completed
2025-10-27 | 2025-10-25 | 2025-11-08 | Nasirudin 2 | 63.509 | 4.2339 | TA325 | 229/1 | Completed
2025-10-27 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-10-27 | 2025-10-22 | 2025-11-13 | Sakila Khatun | 141.874 | 6.1684 | TA325 | 240/0 | Completed
2025-10-27 | 2025-10-24 | 2025-11-10 | Sukruddin | 72.2376 | 4.0132 | TA325 | 245/0 | Completed
2025-10-27 | 2025-10-23 | 2025-11-13 | Teklal Mahto | 64.2538 | 2.9206 | TA325 | 223/0 | Completed
2025-10-28 | 2025-10-19 | 2025-11-01 | Anita Devi | 84.2993 | 6.0214 | TA325 | 232/0 | Completed
2025-10-28 | 2025-10-26 | 2025-11-18 | Anjum | 94.4077 | 3.9337 | TA325 | 203/1 | Completed
2025-10-28 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-10-28 | 2025-10-17 | 2025-10-29 | Gokul 1 | 46.6235 | 3.5864 | TA325 | 185/1 | Completed
2025-10-28 | 2025-10-18 | 2025-10-29 | Gokul Sarkar 2 | 56.8632 | 4.7386 | TA325 | 222/1 | Completed
2025-10-28 | 2025-10-14 | 2025-11-07 | Imadul Haque | 80.408 | 3.2163 | TA325 | 218/0 | Completed
2025-10-28 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-10-28 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-10-28 | 2025-10-23 | 2025-11-06 | Jwala Singh | 65.7565 | 4.3838 | TA325 | 211/0 | Completed
2025-10-28 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-10-28 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-28 | 2025-10-22 | 2025-11-06 | Muni Bibi 1 2 | 63.509 | 3.9693 | TA325 | 227/0 | Completed
2025-10-28 | 2025-10-25 | 2025-11-08 | Nasirudin 2 | 63.509 | 4.2339 | TA325 | 229/1 | Completed
2025-10-28 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-10-28 | 2025-10-22 | 2025-11-13 | Sakila Khatun | 141.874 | 6.1684 | TA325 | 240/0 | Completed
2025-10-28 | 2025-10-24 | 2025-11-10 | Sukruddin | 72.2376 | 4.0132 | TA325 | 245/0 | Completed
2025-10-28 | 2025-10-23 | 2025-11-13 | Teklal Mahto | 64.2538 | 2.9206 | TA325 | 223/0 | Completed
2025-10-29 | 2025-10-19 | 2025-11-01 | Anita Devi | 84.2993 | 6.0214 | TA325 | 232/0 | Completed
2025-10-29 | 2025-10-26 | 2025-11-18 | Anjum | 94.4077 | 3.9337 | TA325 | 203/1 | Completed
2025-10-29 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-10-29 | 2025-10-17 | 2025-10-29 | Gokul 1 | 46.6235 | 3.5864 | TA325 | 185/1 | Completed
2025-10-29 | 2025-10-18 | 2025-10-29 | Gokul Sarkar 2 | 56.8632 | 4.7386 | TA325 | 222/1 | Completed
2025-10-29 | 2025-10-14 | 2025-11-07 | Imadul Haque | 80.408 | 3.2163 | TA325 | 218/0 | Completed
2025-10-29 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-10-29 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-10-29 | 2025-10-23 | 2025-11-06 | Jwala Singh | 65.7565 | 4.3838 | TA325 | 211/0 | Completed
2025-10-29 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-10-29 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-29 | 2025-10-22 | 2025-11-06 | Muni Bibi 1 2 | 63.509 | 3.9693 | TA325 | 227/0 | Completed
2025-10-29 | 2025-10-25 | 2025-11-08 | Nasirudin 2 | 63.509 | 4.2339 | TA325 | 229/1 | Completed
2025-10-29 | 2025-10-29 | 2025-11-09 | Rahul Kumar | 39.4589 | 3.2882 | TA325 | 209/1 | Completed
2025-10-29 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-10-29 | 2025-10-22 | 2025-11-13 | Sakila Khatun | 141.874 | 6.1684 | TA325 | 240/0 | Completed
2025-10-29 | 2025-10-29 | 2025-11-18 | Satish Kumar | 63.509 | 3.0242 | TA325 | 184/1 | Completed
2025-10-29 | 2025-10-29 | 2025-11-09 | Subhash | 64.2538 | 5.3545 | TA325 | 226/0 | Completed
2025-10-29 | 2025-10-24 | 2025-11-10 | Sukruddin | 72.2376 | 4.0132 | TA325 | 245/0 | Completed
2025-10-29 | 2025-10-23 | 2025-11-13 | Teklal Mahto | 64.2538 | 2.9206 | TA325 | 223/0 | Completed
2025-10-30 | 2025-10-19 | 2025-11-01 | Anita Devi | 84.2993 | 6.0214 | TA325 | 232/0 | Completed
2025-10-30 | 2025-10-26 | 2025-11-18 | Anjum | 94.4077 | 3.9337 | TA325 | 203/1 | Completed
2025-10-30 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-10-30 | 2025-10-14 | 2025-11-07 | Imadul Haque | 80.408 | 3.2163 | TA325 | 218/0 | Completed
2025-10-30 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-10-30 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-10-30 | 2025-10-23 | 2025-11-06 | Jwala Singh | 65.7565 | 4.3838 | TA325 | 211/0 | Completed
2025-10-30 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-10-30 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-30 | 2025-10-22 | 2025-11-06 | Muni Bibi 1 2 | 63.509 | 3.9693 | TA325 | 227/0 | Completed
2025-10-30 | 2025-10-25 | 2025-11-08 | Nasirudin 2 | 63.509 | 4.2339 | TA325 | 229/1 | Completed
2025-10-30 | 2025-10-29 | 2025-11-09 | Rahul Kumar | 39.4589 | 3.2882 | TA325 | 209/1 | Completed
2025-10-30 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-10-30 | 2025-10-22 | 2025-11-13 | Sakila Khatun | 141.874 | 6.1684 | TA325 | 240/0 | Completed
2025-10-30 | 2025-10-29 | 2025-11-18 | Satish Kumar | 63.509 | 3.0242 | TA325 | 184/1 | Completed
2025-10-30 | 2025-10-29 | 2025-11-09 | Subhash | 64.2538 | 5.3545 | TA325 | 226/0 | Completed
2025-10-30 | 2025-10-24 | 2025-11-10 | Sukruddin | 72.2376 | 4.0132 | TA325 | 245/0 | Completed
2025-10-30 | 2025-10-23 | 2025-11-13 | Teklal Mahto | 64.2538 | 2.9206 | TA325 | 223/0 | Completed
2025-10-31 | 2025-10-19 | 2025-11-01 | Anita Devi | 84.2993 | 6.0214 | TA325 | 232/0 | Completed
2025-10-31 | 2025-10-26 | 2025-11-18 | Anjum | 94.4077 | 3.9337 | TA325 | 203/1 | Completed
2025-10-31 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-10-31 | 2025-10-14 | 2025-11-07 | Imadul Haque | 80.408 | 3.2163 | TA325 | 218/0 | Completed
2025-10-31 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-10-31 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-10-31 | 2025-10-23 | 2025-11-06 | Jwala Singh | 65.7565 | 4.3838 | TA325 | 211/0 | Completed
2025-10-31 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-10-31 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-10-31 | 2025-10-22 | 2025-11-06 | Muni Bibi 1 2 | 63.509 | 3.9693 | TA325 | 227/0 | Completed
2025-10-31 | 2025-10-25 | 2025-11-08 | Nasirudin 2 | 63.509 | 4.2339 | TA325 | 229/1 | Completed
2025-10-31 | 2025-10-29 | 2025-11-09 | Rahul Kumar | 39.4589 | 3.2882 | TA325 | 209/1 | Completed
2025-10-31 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-10-31 | 2025-10-22 | 2025-11-13 | Sakila Khatun | 141.874 | 6.1684 | TA325 | 240/0 | Completed
2025-10-31 | 2025-10-29 | 2025-11-18 | Satish Kumar | 63.509 | 3.0242 | TA325 | 184/1 | Completed
2025-10-31 | 2025-10-29 | 2025-11-09 | Subhash | 64.2538 | 5.3545 | TA325 | 226/0 | Completed
2025-10-31 | 2025-10-24 | 2025-11-10 | Sukruddin | 72.2376 | 4.0132 | TA325 | 245/0 | Completed
2025-10-31 | 2025-10-23 | 2025-11-13 | Teklal Mahto | 64.2538 | 2.9206 | TA325 | 223/0 | Completed
2025-11-01 | 2025-10-19 | 2025-11-01 | Anita Devi | 84.2993 | 6.0214 | TA325 | 232/0 | Completed
2025-11-01 | 2025-10-26 | 2025-11-18 | Anjum | 94.4077 | 3.9337 | TA325 | 203/1 | Completed
2025-11-01 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-11-01 | 2025-10-14 | 2025-11-07 | Imadul Haque | 80.408 | 3.2163 | TA325 | 218/0 | Completed
2025-11-01 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-11-01 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-11-01 | 2025-10-23 | 2025-11-06 | Jwala Singh | 65.7565 | 4.3838 | TA325 | 211/0 | Completed
2025-11-01 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-11-01 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-11-01 | 2025-10-22 | 2025-11-06 | Muni Bibi 1 2 | 63.509 | 3.9693 | TA325 | 227/0 | Completed
2025-11-01 | 2025-10-25 | 2025-11-08 | Nasirudin 2 | 63.509 | 4.2339 | TA325 | 229/1 | Completed
2025-11-01 | 2025-10-29 | 2025-11-09 | Rahul Kumar | 39.4589 | 3.2882 | TA325 | 209/1 | Completed
2025-11-01 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-11-01 | 2025-10-22 | 2025-11-13 | Sakila Khatun | 141.874 | 6.1684 | TA325 | 240/0 | Completed
2025-11-01 | 2025-10-29 | 2025-11-18 | Satish Kumar | 63.509 | 3.0242 | TA325 | 184/1 | Completed
2025-11-01 | 2025-10-29 | 2025-11-09 | Subhash | 64.2538 | 5.3545 | TA325 | 226/0 | Completed
2025-11-01 | 2025-10-24 | 2025-11-10 | Sukruddin | 72.2376 | 4.0132 | TA325 | 245/0 | Completed
2025-11-01 | 2025-10-23 | 2025-11-13 | Teklal Mahto | 64.2538 | 2.9206 | TA325 | 223/0 | Completed
2025-11-02 | 2025-10-26 | 2025-11-18 | Anjum | 94.4077 | 3.9337 | TA325 | 203/1 | Completed
2025-11-02 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-11-02 | 2025-10-14 | 2025-11-07 | Imadul Haque | 80.408 | 3.2163 | TA325 | 218/0 | Completed
2025-11-02 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-11-02 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-11-02 | 2025-10-23 | 2025-11-06 | Jwala Singh | 65.7565 | 4.3838 | TA325 | 211/0 | Completed
2025-11-02 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-11-02 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-11-02 | 2025-11-02 | 2025-11-14 | Modina India 3 Pgcil | 44.7282 | 3.4406 | TA325 | 229/2 | Completed
2025-11-02 | 2025-10-22 | 2025-11-06 | Muni Bibi 1 2 | 63.509 | 3.9693 | TA325 | 227/0 | Completed
2025-11-02 | 2025-10-25 | 2025-11-08 | Nasirudin 2 | 63.509 | 4.2339 | TA325 | 229/1 | Completed
2025-11-02 | 2025-10-29 | 2025-11-09 | Rahul Kumar | 39.4589 | 3.2882 | TA325 | 209/1 | Completed
2025-11-02 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-11-02 | 2025-10-22 | 2025-11-13 | Sakila Khatun | 141.874 | 6.1684 | TA325 | 240/0 | Completed
2025-11-02 | 2025-10-29 | 2025-11-18 | Satish Kumar | 63.509 | 3.0242 | TA325 | 184/1 | Completed
2025-11-02 | 2025-10-29 | 2025-11-09 | Subhash | 64.2538 | 5.3545 | TA325 | 226/0 | Completed
2025-11-02 | 2025-10-24 | 2025-11-10 | Sukruddin | 72.2376 | 4.0132 | TA325 | 245/0 | Completed
2025-11-02 | 2025-10-23 | 2025-11-13 | Teklal Mahto | 64.2538 | 2.9206 | TA325 | 223/0 | Completed
2025-11-03 | 2025-10-26 | 2025-11-18 | Anjum | 94.4077 | 3.9337 | TA325 | 203/1 | Completed
2025-11-03 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-11-03 | 2025-11-03 | 2025-11-17 | Gokul Sarkar 2 | 89.1461 | 5.9431 | TA325 | 220/0 | Completed
2025-11-03 | 2025-10-14 | 2025-11-07 | Imadul Haque | 80.408 | 3.2163 | TA325 | 218/0 | Completed
2025-11-03 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-11-03 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-11-03 | 2025-10-23 | 2025-11-06 | Jwala Singh | 65.7565 | 4.3838 | TA325 | 211/0 | Completed
2025-11-03 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-11-03 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-11-03 | 2025-11-03 | 2025-11-15 | Mithun Kumar | 64.2538 | 4.9426 | TA325 | 185/0 | Completed
2025-11-03 | 2025-11-02 | 2025-11-14 | Modina India 3 Pgcil | 44.7282 | 3.4406 | TA325 | 229/2 | Completed
2025-11-03 | 2025-10-22 | 2025-11-06 | Muni Bibi 1 2 | 63.509 | 3.9693 | TA325 | 227/0 | Completed
2025-11-03 | 2025-10-25 | 2025-11-08 | Nasirudin 2 | 63.509 | 4.2339 | TA325 | 229/1 | Completed
2025-11-03 | 2025-10-29 | 2025-11-09 | Rahul Kumar | 39.4589 | 3.2882 | TA325 | 209/1 | Completed
2025-11-03 | 2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-11-03 | 2025-10-22 | 2025-11-13 | Sakila Khatun | 141.874 | 6.1684 | TA325 | 240/0 | Completed
2025-11-03 | 2025-10-29 | 2025-11-18 | Satish Kumar | 63.509 | 3.0242 | TA325 | 184/1 | Completed
2025-11-03 | 2025-10-29 | 2025-11-09 | Subhash | 64.2538 | 5.3545 | TA325 | 226/0 | Completed
2025-11-03 | 2025-10-24 | 2025-11-10 | Sukruddin | 72.2376 | 4.0132 | TA325 | 245/0 | Completed
2025-11-03 | 2025-10-23 | 2025-11-13 | Teklal Mahto | 64.2538 | 2.9206 | TA325 | 223/0 | Completed
2025-11-04 | 2025-10-26 | 2025-11-18 | Anjum | 94.4077 | 3.9337 | TA325 | 203/1 | Completed
2025-11-04 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-11-04 | 2025-11-03 | 2025-11-17 | Gokul Sarkar 2 | 89.1461 | 5.9431 | TA325 | 220/0 | Completed
2025-11-04 | 2025-10-14 | 2025-11-07 | Imadul Haque | 80.408 | 3.2163 | TA325 | 218/0 | Completed
2025-11-04 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-11-04 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-11-04 | 2025-10-23 | 2025-11-06 | Jwala Singh | 65.7565 | 4.3838 | TA325 | 211/0 | Completed
2025-11-04 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-11-04 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-11-04 | 2025-11-03 | 2025-11-15 | Mithun Kumar | 64.2538 | 4.9426 | TA325 | 185/0 | Completed
2025-11-04 | 2025-11-02 | 2025-11-14 | Modina India 3 Pgcil | 44.7282 | 3.4406 | TA325 | 229/2 | Completed
2025-11-04 | 2025-10-22 | 2025-11-06 | Muni Bibi 1 2 | 63.509 | 3.9693 | TA325 | 227/0 | Completed
2025-11-04 | 2025-10-25 | 2025-11-08 | Nasirudin 2 | 63.509 | 4.2339 | TA325 | 229/1 | Completed
2025-11-04 | 2025-10-29 | 2025-11-09 | Rahul Kumar | 39.4589 | 3.2882 | TA325 | 209/1 | Completed
2025-11-04 | 2025-10-22 | 2025-11-13 | Sakila Khatun | 141.874 | 6.1684 | TA325 | 240/0 | Completed
2025-11-04 | 2025-10-29 | 2025-11-18 | Satish Kumar | 63.509 | 3.0242 | TA325 | 184/1 | Completed
2025-11-04 | 2025-10-29 | 2025-11-09 | Subhash | 64.2538 | 5.3545 | TA325 | 226/0 | Completed
2025-11-04 | 2025-10-24 | 2025-11-10 | Sukruddin | 72.2376 | 4.0132 | TA325 | 245/0 | Completed
2025-11-04 | 2025-10-23 | 2025-11-13 | Teklal Mahto | 64.2538 | 2.9206 | TA325 | 223/0 | Completed
2025-11-05 | 2025-10-26 | 2025-11-18 | Anjum | 94.4077 | 3.9337 | TA325 | 203/1 | Completed
2025-11-05 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-11-05 | 2025-11-05 | 2025-11-13 | Gokul Sarkar 1 | 39.4589 | 4.3843 | TA325 | 220/1 | Completed
2025-11-05 | 2025-11-03 | 2025-11-17 | Gokul Sarkar 2 | 89.1461 | 5.9431 | TA325 | 220/0 | Completed
2025-11-05 | 2025-10-14 | 2025-11-07 | Imadul Haque | 80.408 | 3.2163 | TA325 | 218/0 | Completed
2025-11-05 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-11-05 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-11-05 | 2025-10-23 | 2025-11-06 | Jwala Singh | 65.7565 | 4.3838 | TA325 | 211/0 | Completed
2025-11-05 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-11-05 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-11-05 | 2025-11-03 | 2025-11-15 | Mithun Kumar | 64.2538 | 4.9426 | TA325 | 185/0 | Completed
2025-11-05 | 2025-11-02 | 2025-11-14 | Modina India 3 Pgcil | 44.7282 | 3.4406 | TA325 | 229/2 | Completed
2025-11-05 | 2025-10-22 | 2025-11-06 | Muni Bibi 1 2 | 63.509 | 3.9693 | TA325 | 227/0 | Completed
2025-11-05 | 2025-10-25 | 2025-11-08 | Nasirudin 2 | 63.509 | 4.2339 | TA325 | 229/1 | Completed
2025-11-05 | 2025-10-29 | 2025-11-09 | Rahul Kumar | 39.4589 | 3.2882 | TA325 | 209/1 | Completed
2025-11-05 | 2025-10-22 | 2025-11-13 | Sakila Khatun | 141.874 | 6.1684 | TA325 | 240/0 | Completed
2025-11-05 | 2025-10-29 | 2025-11-18 | Satish Kumar | 63.509 | 3.0242 | TA325 | 184/1 | Completed
2025-11-05 | 2025-10-29 | 2025-11-09 | Subhash | 64.2538 | 5.3545 | TA325 | 226/0 | Completed
2025-11-05 | 2025-10-24 | 2025-11-10 | Sukruddin | 72.2376 | 4.0132 | TA325 | 245/0 | Completed
2025-11-05 | 2025-10-23 | 2025-11-13 | Teklal Mahto | 64.2538 | 2.9206 | TA325 | 223/0 | Completed
2025-11-06 | 2025-10-26 | 2025-11-18 | Anjum | 94.4077 | 3.9337 | TA325 | 203/1 | Completed
2025-11-06 | 2025-11-06 | 2025-11-24 | Chitra Construction | 37.7305 | 1.9858 | TA325 | 211A/2 | Completed
2025-11-06 | 2025-11-06 | 2025-11-14 | Dildar Electricals 1 Pgcil | 37.7305 | 4.1923 | TA325 | 223/3 | Completed
2025-11-06 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-11-06 | 2025-11-05 | 2025-11-13 | Gokul Sarkar 1 | 39.4589 | 4.3843 | TA325 | 220/1 | Completed
2025-11-06 | 2025-11-03 | 2025-11-17 | Gokul Sarkar 2 | 89.1461 | 5.9431 | TA325 | 220/0 | Completed
2025-11-06 | 2025-10-14 | 2025-11-07 | Imadul Haque | 80.408 | 3.2163 | TA325 | 218/0 | Completed
2025-11-06 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-11-06 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-11-06 | 2025-10-23 | 2025-11-06 | Jwala Singh | 65.7565 | 4.3838 | TA325 | 211/0 | Completed
2025-11-06 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-11-06 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-11-06 | 2025-11-03 | 2025-11-15 | Mithun Kumar | 64.2538 | 4.9426 | TA325 | 185/0 | Completed
2025-11-06 | 2025-11-06 | 2025-11-18 | Modina India 2 Pgcil | 39.4589 | 3.0353 | TA325 | 218/1 | Completed
2025-11-06 | 2025-11-02 | 2025-11-14 | Modina India 3 Pgcil | 44.7282 | 3.4406 | TA325 | 229/2 | Completed
2025-11-06 | 2025-10-22 | 2025-11-06 | Muni Bibi 1 2 | 63.509 | 3.9693 | TA325 | 227/0 | Completed
2025-11-06 | 2025-10-25 | 2025-11-08 | Nasirudin 2 | 63.509 | 4.2339 | TA325 | 229/1 | Completed
2025-11-06 | 2025-10-29 | 2025-11-09 | Rahul Kumar | 39.4589 | 3.2882 | TA325 | 209/1 | Completed
2025-11-06 | 2025-10-22 | 2025-11-13 | Sakila Khatun | 141.874 | 6.1684 | TA325 | 240/0 | Completed
2025-11-06 | 2025-10-29 | 2025-11-18 | Satish Kumar | 63.509 | 3.0242 | TA325 | 184/1 | Completed
2025-11-06 | 2025-10-29 | 2025-11-09 | Subhash | 64.2538 | 5.3545 | TA325 | 226/0 | Completed
2025-11-06 | 2025-10-24 | 2025-11-10 | Sukruddin | 72.2376 | 4.0132 | TA325 | 245/0 | Completed
2025-11-06 | 2025-10-23 | 2025-11-13 | Teklal Mahto | 64.2538 | 2.9206 | TA325 | 223/0 | Completed
2025-11-07 | 2025-10-26 | 2025-11-18 | Anjum | 94.4077 | 3.9337 | TA325 | 203/1 | Completed
2025-11-07 | 2025-11-06 | 2025-11-24 | Chitra Construction | 37.7305 | 1.9858 | TA325 | 211A/2 | Completed
2025-11-07 | 2025-11-06 | 2025-11-14 | Dildar Electricals 1 Pgcil | 37.7305 | 4.1923 | TA325 | 223/3 | Completed
2025-11-07 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-11-07 | 2025-11-05 | 2025-11-13 | Gokul Sarkar 1 | 39.4589 | 4.3843 | TA325 | 220/1 | Completed
2025-11-07 | 2025-11-03 | 2025-11-17 | Gokul Sarkar 2 | 89.1461 | 5.9431 | TA325 | 220/0 | Completed
2025-11-07 | 2025-10-14 | 2025-11-07 | Imadul Haque | 80.408 | 3.2163 | TA325 | 218/0 | Completed
2025-11-07 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-11-07 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-11-07 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-11-07 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-11-07 | 2025-11-03 | 2025-11-15 | Mithun Kumar | 64.2538 | 4.9426 | TA325 | 185/0 | Completed
2025-11-07 | 2025-11-06 | 2025-11-18 | Modina India 2 Pgcil | 39.4589 | 3.0353 | TA325 | 218/1 | Completed
2025-11-07 | 2025-11-02 | 2025-11-14 | Modina India 3 Pgcil | 44.7282 | 3.4406 | TA325 | 229/2 | Completed
2025-11-07 | 2025-10-25 | 2025-11-08 | Nasirudin 2 | 63.509 | 4.2339 | TA325 | 229/1 | Completed
2025-11-07 | 2025-10-29 | 2025-11-09 | Rahul Kumar | 39.4589 | 3.2882 | TA325 | 209/1 | Completed
2025-11-07 | 2025-10-22 | 2025-11-13 | Sakila Khatun | 141.874 | 6.1684 | TA325 | 240/0 | Completed
2025-11-07 | 2025-10-29 | 2025-11-18 | Satish Kumar | 63.509 | 3.0242 | TA325 | 184/1 | Completed
2025-11-07 | 2025-10-29 | 2025-11-09 | Subhash | 64.2538 | 5.3545 | TA325 | 226/0 | Completed
2025-11-07 | 2025-10-24 | 2025-11-10 | Sukruddin | 72.2376 | 4.0132 | TA325 | 245/0 | Completed
2025-11-07 | 2025-10-23 | 2025-11-13 | Teklal Mahto | 64.2538 | 2.9206 | TA325 | 223/0 | Completed
2025-11-08 | 2025-10-26 | 2025-11-18 | Anjum | 94.4077 | 3.9337 | TA325 | 203/1 | Completed
2025-11-08 | 2025-11-06 | 2025-11-24 | Chitra Construction | 37.7305 | 1.9858 | TA325 | 211A/2 | Completed
2025-11-08 | 2025-11-06 | 2025-11-14 | Dildar Electricals 1 Pgcil | 37.7305 | 4.1923 | TA325 | 223/3 | Completed
2025-11-08 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-11-08 | 2025-11-05 | 2025-11-13 | Gokul Sarkar 1 | 39.4589 | 4.3843 | TA325 | 220/1 | Completed
2025-11-08 | 2025-11-03 | 2025-11-17 | Gokul Sarkar 2 | 89.1461 | 5.9431 | TA325 | 220/0 | Completed
2025-11-08 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-11-08 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-11-08 | 2025-11-08 | 2025-11-15 | Jwala Singh | 37.7305 | 4.7163 | TA325 | 211/2 | Completed
2025-11-08 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-11-08 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-11-08 | 2025-11-03 | 2025-11-15 | Mithun Kumar | 64.2538 | 4.9426 | TA325 | 185/0 | Completed
2025-11-08 | 2025-11-06 | 2025-11-18 | Modina India 2 Pgcil | 39.4589 | 3.0353 | TA325 | 218/1 | Completed
2025-11-08 | 2025-11-02 | 2025-11-14 | Modina India 3 Pgcil | 44.7282 | 3.4406 | TA325 | 229/2 | Completed
2025-11-08 | 2025-10-25 | 2025-11-08 | Nasirudin 2 | 63.509 | 4.2339 | TA325 | 229/1 | Completed
2025-11-08 | 2025-10-29 | 2025-11-09 | Rahul Kumar | 39.4589 | 3.2882 | TA325 | 209/1 | Completed
2025-11-08 | 2025-10-22 | 2025-11-13 | Sakila Khatun | 141.874 | 6.1684 | TA325 | 240/0 | Completed
2025-11-08 | 2025-10-29 | 2025-11-18 | Satish Kumar | 63.509 | 3.0242 | TA325 | 184/1 | Completed
2025-11-08 | 2025-10-29 | 2025-11-09 | Subhash | 64.2538 | 5.3545 | TA325 | 226/0 | Completed
2025-11-08 | 2025-10-24 | 2025-11-10 | Sukruddin | 72.2376 | 4.0132 | TA325 | 245/0 | Completed
2025-11-08 | 2025-10-23 | 2025-11-13 | Teklal Mahto | 64.2538 | 2.9206 | TA325 | 223/0 | Completed
2025-11-09 | 2025-10-26 | 2025-11-18 | Anjum | 94.4077 | 3.9337 | TA325 | 203/1 | Completed
2025-11-09 | 2025-11-06 | 2025-11-24 | Chitra Construction | 37.7305 | 1.9858 | TA325 | 211A/2 | Completed
2025-11-09 | 2025-11-06 | 2025-11-14 | Dildar Electricals 1 Pgcil | 37.7305 | 4.1923 | TA325 | 223/3 | Completed
2025-11-09 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-11-09 | 2025-11-05 | 2025-11-13 | Gokul Sarkar 1 | 39.4589 | 4.3843 | TA325 | 220/1 | Completed
2025-11-09 | 2025-11-03 | 2025-11-17 | Gokul Sarkar 2 | 89.1461 | 5.9431 | TA325 | 220/0 | Completed
2025-11-09 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-11-09 | 2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-11-09 | 2025-11-08 | 2025-11-15 | Jwala Singh | 37.7305 | 4.7163 | TA325 | 211/2 | Completed
2025-11-09 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-11-09 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-11-09 | 2025-11-03 | 2025-11-15 | Mithun Kumar | 64.2538 | 4.9426 | TA325 | 185/0 | Completed
2025-11-09 | 2025-11-06 | 2025-11-18 | Modina India 2 Pgcil | 39.4589 | 3.0353 | TA325 | 218/1 | Completed
2025-11-09 | 2025-11-02 | 2025-11-14 | Modina India 3 Pgcil | 44.7282 | 3.4406 | TA325 | 229/2 | Completed
2025-11-09 | 2025-10-29 | 2025-11-09 | Rahul Kumar | 39.4589 | 3.2882 | TA325 | 209/1 | Completed
2025-11-09 | 2025-10-22 | 2025-11-13 | Sakila Khatun | 141.874 | 6.1684 | TA325 | 240/0 | Completed
2025-11-09 | 2025-10-29 | 2025-11-18 | Satish Kumar | 63.509 | 3.0242 | TA325 | 184/1 | Completed
2025-11-09 | 2025-10-29 | 2025-11-09 | Subhash | 64.2538 | 5.3545 | TA325 | 226/0 | Completed
2025-11-09 | 2025-10-24 | 2025-11-10 | Sukruddin | 72.2376 | 4.0132 | TA325 | 245/0 | Completed
2025-11-09 | 2025-10-23 | 2025-11-13 | Teklal Mahto | 64.2538 | 2.9206 | TA325 | 223/0 | Completed
2025-11-10 | 2025-10-26 | 2025-11-18 | Anjum | 94.4077 | 3.9337 | TA325 | 203/1 | Completed
2025-11-10 | 2025-11-06 | 2025-11-24 | Chitra Construction | 37.7305 | 1.9858 | TA325 | 211A/2 | Completed
2025-11-10 | 2025-11-06 | 2025-11-14 | Dildar Electricals 1 Pgcil | 37.7305 | 4.1923 | TA325 | 223/3 | Completed
2025-11-10 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-11-10 | 2025-11-05 | 2025-11-13 | Gokul Sarkar 1 | 39.4589 | 4.3843 | TA325 | 220/1 | Completed
2025-11-10 | 2025-11-03 | 2025-11-17 | Gokul Sarkar 2 | 89.1461 | 5.9431 | TA325 | 220/0 | Completed
2025-11-10 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-11-10 | 2025-11-08 | 2025-11-15 | Jwala Singh | 37.7305 | 4.7163 | TA325 | 211/2 | Completed
2025-11-10 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-11-10 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-11-10 | 2025-11-03 | 2025-11-15 | Mithun Kumar | 64.2538 | 4.9426 | TA325 | 185/0 | Completed
2025-11-10 | 2025-11-06 | 2025-11-18 | Modina India 2 Pgcil | 39.4589 | 3.0353 | TA325 | 218/1 | Completed
2025-11-10 | 2025-11-02 | 2025-11-14 | Modina India 3 Pgcil | 44.7282 | 3.4406 | TA325 | 229/2 | Completed
2025-11-10 | 2025-10-22 | 2025-11-13 | Sakila Khatun | 141.874 | 6.1684 | TA325 | 240/0 | Completed
2025-11-10 | 2025-10-29 | 2025-11-18 | Satish Kumar | 63.509 | 3.0242 | TA325 | 184/1 | Completed
2025-11-10 | 2025-10-24 | 2025-11-10 | Sukruddin | 72.2376 | 4.0132 | TA325 | 245/0 | Completed
2025-11-10 | 2025-10-23 | 2025-11-13 | Teklal Mahto | 64.2538 | 2.9206 | TA325 | 223/0 | Completed
2025-11-11 | 2025-10-26 | 2025-11-18 | Anjum | 94.4077 | 3.9337 | TA325 | 203/1 | Completed
2025-11-11 | 2025-11-06 | 2025-11-24 | Chitra Construction | 37.7305 | 1.9858 | TA325 | 211A/2 | Completed
2025-11-11 | 2025-11-06 | 2025-11-14 | Dildar Electricals 1 Pgcil | 37.7305 | 4.1923 | TA325 | 223/3 | Completed
2025-11-11 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-11-11 | 2025-11-05 | 2025-11-13 | Gokul Sarkar 1 | 39.4589 | 4.3843 | TA325 | 220/1 | Completed
2025-11-11 | 2025-11-03 | 2025-11-17 | Gokul Sarkar 2 | 89.1461 | 5.9431 | TA325 | 220/0 | Completed
2025-11-11 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-11-11 | 2025-11-08 | 2025-11-15 | Jwala Singh | 37.7305 | 4.7163 | TA325 | 211/2 | Completed
2025-11-11 | 2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-11-11 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-11-11 | 2025-11-03 | 2025-11-15 | Mithun Kumar | 64.2538 | 4.9426 | TA325 | 185/0 | Completed
2025-11-11 | 2025-11-06 | 2025-11-18 | Modina India 2 Pgcil | 39.4589 | 3.0353 | TA325 | 218/1 | Completed
2025-11-11 | 2025-11-02 | 2025-11-14 | Modina India 3 Pgcil | 44.7282 | 3.4406 | TA325 | 229/2 | Completed
2025-11-11 | 2025-11-11 | 2025-11-23 | Pc Construction | 97.9336 | 7.5334 | TA325 | 201/0 | Completed
2025-11-11 | 2025-10-22 | 2025-11-13 | Sakila Khatun | 141.874 | 6.1684 | TA325 | 240/0 | Completed
2025-11-11 | 2025-10-29 | 2025-11-18 | Satish Kumar | 63.509 | 3.0242 | TA325 | 184/1 | Completed
2025-11-11 | 2025-10-23 | 2025-11-13 | Teklal Mahto | 64.2538 | 2.9206 | TA325 | 223/0 | Completed
2025-11-12 | 2025-10-26 | 2025-11-18 | Anjum | 94.4077 | 3.9337 | TA325 | 203/1 | Completed
2025-11-12 | 2025-11-06 | 2025-11-24 | Chitra Construction | 37.7305 | 1.9858 | TA325 | 211A/2 | Completed
2025-11-12 | 2025-11-06 | 2025-11-14 | Dildar Electricals 1 Pgcil | 37.7305 | 4.1923 | TA325 | 223/3 | Completed
2025-11-12 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-11-12 | 2025-11-05 | 2025-11-13 | Gokul Sarkar 1 | 39.4589 | 4.3843 | TA325 | 220/1 | Completed
2025-11-12 | 2025-11-03 | 2025-11-17 | Gokul Sarkar 2 | 89.1461 | 5.9431 | TA325 | 220/0 | Completed
2025-11-12 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-11-12 | 2025-11-08 | 2025-11-15 | Jwala Singh | 37.7305 | 4.7163 | TA325 | 211/2 | Completed
2025-11-12 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-11-12 | 2025-11-03 | 2025-11-15 | Mithun Kumar | 64.2538 | 4.9426 | TA325 | 185/0 | Completed
2025-11-12 | 2025-11-06 | 2025-11-18 | Modina India 2 Pgcil | 39.4589 | 3.0353 | TA325 | 218/1 | Completed
2025-11-12 | 2025-11-02 | 2025-11-14 | Modina India 3 Pgcil | 44.7282 | 3.4406 | TA325 | 229/2 | Completed
2025-11-12 | 2025-11-11 | 2025-11-23 | Pc Construction | 97.9336 | 7.5334 | TA325 | 201/0 | Completed
2025-11-12 | 2025-10-22 | 2025-11-13 | Sakila Khatun | 141.874 | 6.1684 | TA325 | 240/0 | Completed
2025-11-12 | 2025-10-29 | 2025-11-18 | Satish Kumar | 63.509 | 3.0242 | TA325 | 184/1 | Completed
2025-11-12 | 2025-10-23 | 2025-11-13 | Teklal Mahto | 64.2538 | 2.9206 | TA325 | 223/0 | Completed
2025-11-13 | 2025-10-26 | 2025-11-18 | Anjum | 94.4077 | 3.9337 | TA325 | 203/1 | Completed
2025-11-13 | 2025-11-06 | 2025-11-24 | Chitra Construction | 37.7305 | 1.9858 | TA325 | 211A/2 | Completed
2025-11-13 | 2025-11-06 | 2025-11-14 | Dildar Electricals 1 Pgcil | 37.7305 | 4.1923 | TA325 | 223/3 | Completed
2025-11-13 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-11-13 | 2025-11-05 | 2025-11-13 | Gokul Sarkar 1 | 39.4589 | 4.3843 | TA325 | 220/1 | Completed
2025-11-13 | 2025-11-03 | 2025-11-17 | Gokul Sarkar 2 | 89.1461 | 5.9431 | TA325 | 220/0 | Completed
2025-11-13 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-11-13 | 2025-11-08 | 2025-11-15 | Jwala Singh | 37.7305 | 4.7163 | TA325 | 211/2 | Completed
2025-11-13 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-11-13 | 2025-11-03 | 2025-11-15 | Mithun Kumar | 64.2538 | 4.9426 | TA325 | 185/0 | Completed
2025-11-13 | 2025-11-06 | 2025-11-18 | Modina India 2 Pgcil | 39.4589 | 3.0353 | TA325 | 218/1 | Completed
2025-11-13 | 2025-11-02 | 2025-11-14 | Modina India 3 Pgcil | 44.7282 | 3.4406 | TA325 | 229/2 | Completed
2025-11-13 | 2025-11-11 | 2025-11-23 | Pc Construction | 97.9336 | 7.5334 | TA325 | 201/0 | Completed
2025-11-13 | 2025-10-22 | 2025-11-13 | Sakila Khatun | 141.874 | 6.1684 | TA325 | 240/0 | Completed
2025-11-13 | 2025-10-29 | 2025-11-18 | Satish Kumar | 63.509 | 3.0242 | TA325 | 184/1 | Completed
2025-11-13 | 2025-10-23 | 2025-11-13 | Teklal Mahto | 64.2538 | 2.9206 | TA325 | 223/0 | Completed
2025-11-14 | 2025-10-26 | 2025-11-18 | Anjum | 94.4077 | 3.9337 | TA325 | 203/1 | Completed
2025-11-14 | 2025-11-06 | 2025-11-24 | Chitra Construction | 37.7305 | 1.9858 | TA325 | 211A/2 | Completed
2025-11-14 | 2025-11-06 | 2025-11-14 | Dildar Electricals 1 Pgcil | 37.7305 | 4.1923 | TA325 | 223/3 | Completed
2025-11-14 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-11-14 | 2025-11-03 | 2025-11-17 | Gokul Sarkar 2 | 89.1461 | 5.9431 | TA325 | 220/0 | Completed
2025-11-14 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-11-14 | 2025-11-08 | 2025-11-15 | Jwala Singh | 37.7305 | 4.7163 | TA325 | 211/2 | Completed
2025-11-14 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-11-14 | 2025-11-03 | 2025-11-15 | Mithun Kumar | 64.2538 | 4.9426 | TA325 | 185/0 | Completed
2025-11-14 | 2025-11-06 | 2025-11-18 | Modina India 2 Pgcil | 39.4589 | 3.0353 | TA325 | 218/1 | Completed
2025-11-14 | 2025-11-02 | 2025-11-14 | Modina India 3 Pgcil | 44.7282 | 3.4406 | TA325 | 229/2 | Completed
2025-11-14 | 2025-11-11 | 2025-11-23 | Pc Construction | 97.9336 | 7.5334 | TA325 | 201/0 | Completed
2025-11-14 | 2025-10-29 | 2025-11-18 | Satish Kumar | 63.509 | 3.0242 | TA325 | 184/1 | Completed
2025-11-15 | 2025-10-26 | 2025-11-18 | Anjum | 94.4077 | 3.9337 | TA325 | 203/1 | Completed
2025-11-15 | 2025-11-06 | 2025-11-24 | Chitra Construction | 37.7305 | 1.9858 | TA325 | 211A/2 | Completed
2025-11-15 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-11-15 | 2025-11-03 | 2025-11-17 | Gokul Sarkar 2 | 89.1461 | 5.9431 | TA325 | 220/0 | Completed
2025-11-15 | 2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-11-15 | 2025-11-08 | 2025-11-15 | Jwala Singh | 37.7305 | 4.7163 | TA325 | 211/2 | Completed
2025-11-15 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-11-15 | 2025-11-03 | 2025-11-15 | Mithun Kumar | 64.2538 | 4.9426 | TA325 | 185/0 | Completed
2025-11-15 | 2025-11-06 | 2025-11-18 | Modina India 2 Pgcil | 39.4589 | 3.0353 | TA325 | 218/1 | Completed
2025-11-15 | 2025-11-15 | 2025-11-24 | Pc 2 | 46.6235 | 4.6623 | TA325 | 215/1 | Completed
2025-11-15 | 2025-11-11 | 2025-11-23 | Pc Construction | 97.9336 | 7.5334 | TA325 | 201/0 | Completed
2025-11-15 | 2025-10-29 | 2025-11-18 | Satish Kumar | 63.509 | 3.0242 | TA325 | 184/1 | Completed
2025-11-16 | 2025-10-26 | 2025-11-18 | Anjum | 94.4077 | 3.9337 | TA325 | 203/1 | Completed
2025-11-16 | 2025-11-06 | 2025-11-24 | Chitra Construction | 37.7305 | 1.9858 | TA325 | 211A/2 | Completed
2025-11-16 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-11-16 | 2025-11-03 | 2025-11-17 | Gokul Sarkar 2 | 89.1461 | 5.9431 | TA325 | 220/0 | Completed
2025-11-16 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-11-16 | 2025-11-06 | 2025-11-18 | Modina India 2 Pgcil | 39.4589 | 3.0353 | TA325 | 218/1 | Completed
2025-11-16 | 2025-11-15 | 2025-11-24 | Pc 2 | 46.6235 | 4.6623 | TA325 | 215/1 | Completed
2025-11-16 | 2025-11-11 | 2025-11-23 | Pc Construction | 97.9336 | 7.5334 | TA325 | 201/0 | Completed
2025-11-16 | 2025-10-29 | 2025-11-18 | Satish Kumar | 63.509 | 3.0242 | TA325 | 184/1 | Completed
2025-11-17 | 2025-10-26 | 2025-11-18 | Anjum | 94.4077 | 3.9337 | TA325 | 203/1 | Completed
2025-11-17 | 2025-11-06 | 2025-11-24 | Chitra Construction | 37.7305 | 1.9858 | TA325 | 211A/2 | Completed
2025-11-17 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-11-17 | 2025-11-03 | 2025-11-17 | Gokul Sarkar 2 | 89.1461 | 5.9431 | TA325 | 220/0 | Completed
2025-11-17 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-11-17 | 2025-11-06 | 2025-11-18 | Modina India 2 Pgcil | 39.4589 | 3.0353 | TA325 | 218/1 | Completed
2025-11-17 | 2025-11-15 | 2025-11-24 | Pc 2 | 46.6235 | 4.6623 | TA325 | 215/1 | Completed
2025-11-17 | 2025-11-11 | 2025-11-23 | Pc Construction | 97.9336 | 7.5334 | TA325 | 201/0 | Completed
2025-11-17 | 2025-10-29 | 2025-11-18 | Satish Kumar | 63.509 | 3.0242 | TA325 | 184/1 | Completed
2025-11-18 | 2025-10-26 | 2025-11-18 | Anjum | 94.4077 | 3.9337 | TA325 | 203/1 | Completed
2025-11-18 | 2025-11-06 | 2025-11-24 | Chitra Construction | 37.7305 | 1.9858 | TA325 | 211A/2 | Completed
2025-11-18 | 2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-11-18 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-11-18 | 2025-11-06 | 2025-11-18 | Modina India 2 Pgcil | 39.4589 | 3.0353 | TA325 | 218/1 | Completed
2025-11-18 | 2025-11-15 | 2025-11-24 | Pc 2 | 46.6235 | 4.6623 | TA325 | 215/1 | Completed
2025-11-18 | 2025-11-11 | 2025-11-23 | Pc Construction | 97.9336 | 7.5334 | TA325 | 201/0 | Completed
2025-11-18 | 2025-10-29 | 2025-11-18 | Satish Kumar | 63.509 | 3.0242 | TA325 | 184/1 | Completed
2025-11-19 | 2025-11-06 | 2025-11-24 | Chitra Construction | 37.7305 | 1.9858 | TA325 | 211A/2 | Completed
2025-11-19 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-11-19 | 2025-11-15 | 2025-11-24 | Pc 2 | 46.6235 | 4.6623 | TA325 | 215/1 | Completed
2025-11-19 | 2025-11-11 | 2025-11-23 | Pc Construction | 97.9336 | 7.5334 | TA325 | 201/0 | Completed
2025-11-20 | 2025-11-06 | 2025-11-24 | Chitra Construction | 37.7305 | 1.9858 | TA325 | 211A/2 | Completed
2025-11-20 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-11-20 | 2025-11-15 | 2025-11-24 | Pc 2 | 46.6235 | 4.6623 | TA325 | 215/1 | Completed
2025-11-20 | 2025-11-11 | 2025-11-23 | Pc Construction | 97.9336 | 7.5334 | TA325 | 201/0 | Completed
2025-11-21 | 2025-11-06 | 2025-11-24 | Chitra Construction | 37.7305 | 1.9858 | TA325 | 211A/2 | Completed
2025-11-21 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-11-21 | 2025-11-15 | 2025-11-24 | Pc 2 | 46.6235 | 4.6623 | TA325 | 215/1 | Completed
2025-11-21 | 2025-11-11 | 2025-11-23 | Pc Construction | 97.9336 | 7.5334 | TA325 | 201/0 | Completed
2025-11-22 | 2025-11-06 | 2025-11-24 | Chitra Construction | 37.7305 | 1.9858 | TA325 | 211A/2 | Completed
2025-11-22 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-11-22 | 2025-11-15 | 2025-11-24 | Pc 2 | 46.6235 | 4.6623 | TA325 | 215/1 | Completed
2025-11-22 | 2025-11-11 | 2025-11-23 | Pc Construction | 97.9336 | 7.5334 | TA325 | 201/0 | Completed
2025-11-23 | 2025-11-06 | 2025-11-24 | Chitra Construction | 37.7305 | 1.9858 | TA325 | 211A/2 | Completed
2025-11-23 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-11-23 | 2025-11-15 | 2025-11-24 | Pc 2 | 46.6235 | 4.6623 | TA325 | 215/1 | Completed
2025-11-23 | 2025-11-11 | 2025-11-23 | Pc Construction | 97.9336 | 7.5334 | TA325 | 201/0 | Completed
2025-11-24 | 2025-11-06 | 2025-11-24 | Chitra Construction | 37.7305 | 1.9858 | TA325 | 211A/2 | Completed
2025-11-24 | 2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-11-24 | 2025-11-15 | 2025-11-24 | Pc 2 | 46.6235 | 4.6623 | TA325 | 215/1 | Completed
2024-03-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-03-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-03-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-03-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-03-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-03-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-12 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | Completed
2024-09-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-13 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | Completed
2024-09-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-14 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | Completed
2024-09-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-15 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | Completed
2024-09-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-16 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | Completed
2024-09-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-17 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | Completed
2024-09-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-18 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | Completed
2024-09-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-19 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | Completed
2024-09-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-20 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | Completed
2024-09-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-21 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | Completed
2024-09-21 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | Completed
2024-09-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-22 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | Completed
2024-09-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-23 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | Completed
2024-09-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-24 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | Completed
2024-09-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-25 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | Completed
2024-09-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-26 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | Completed
2024-09-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-27 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | Completed
2024-09-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-28 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | Completed
2024-09-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-29 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | Completed
2024-09-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-30 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | Completed
2024-09-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-01 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | Completed
2024-10-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-02 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | Completed
2024-10-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-03 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | Completed
2024-10-03 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | Completed
2024-10-03 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | Completed
2024-10-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-04 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | Completed
2024-10-04 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | Completed
2024-10-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-05 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | Completed
2024-10-05 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | Completed
2024-10-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-06 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | Completed
2024-10-06 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | Completed
2024-10-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-07 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | Completed
2024-10-07 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | Completed
2024-10-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-08 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | Completed
2024-10-08 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | Completed
2024-10-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-09 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | Completed
2024-10-09 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | Completed
2024-10-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-10 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | Completed
2024-10-10 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | Completed
2024-10-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-11 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | Completed
2024-10-11 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | Completed
2024-10-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-12 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | Completed
2024-10-12 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | Completed
2024-10-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-13 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | Completed
2024-10-13 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | Completed
2024-10-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-14 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | Completed
2024-10-14 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | Completed
2024-10-14 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | Completed
2024-10-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-15 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | Completed
2024-10-15 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | Completed
2024-10-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-16 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | Completed
2024-10-16 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | Completed
2024-10-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-17 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | Completed
2024-10-17 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | Completed
2024-10-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-18 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | Completed
2024-10-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-19 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | Completed
2024-10-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-20 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | Completed
2024-10-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-21 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | Completed
2024-10-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-22 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | Completed
2024-10-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-23 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | Completed
2024-10-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-24 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | Completed
2024-10-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-25 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | Completed
2024-10-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-12 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-13 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-14 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-14 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | Completed
2024-11-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-15 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-15 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | Completed
2024-11-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-16 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-16 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | Completed
2024-11-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-17 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-17 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | Completed
2024-11-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-18 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-18 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | Completed
2024-11-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-19 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-19 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | Completed
2024-11-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-20 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-20 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | Completed
2024-11-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-21 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-21 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | Completed
2024-11-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-22 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-22 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | Completed
2024-11-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-23 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-23 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | Completed
2024-11-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-24 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-24 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | Completed
2024-11-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-25 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | Completed
2024-11-25 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | Completed
2024-11-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-26 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | Completed
2024-11-26 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-11-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-27 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | Completed
2024-11-27 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-11-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-28 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | Completed
2024-11-28 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-11-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-29 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | Completed
2024-11-29 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-11-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-30 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | Completed
2024-11-30 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-01 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | Completed
2024-12-01 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-02 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | Completed
2024-12-02 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-03 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | Completed
2024-12-03 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-04 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | Completed
2024-12-04 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-05 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | Completed
2024-12-05 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-06 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | Completed
2024-12-06 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-07 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | Completed
2024-12-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-07 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | Completed
2024-12-07 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-08 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | Completed
2024-12-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-08 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | Completed
2024-12-08 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-09 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | Completed
2024-12-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-09 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | Completed
2024-12-09 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-10 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | Completed
2024-12-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-10 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | Completed
2024-12-10 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-11 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | Completed
2024-12-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-11 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | Completed
2024-12-11 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-12 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | Completed
2024-12-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-12 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | Completed
2024-12-12 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-13 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | Completed
2024-12-13 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | Completed
2024-12-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-13 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-13 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | Completed
2024-12-13 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | Completed
2024-12-14 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | Completed
2024-12-14 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | Completed
2024-12-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-14 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-14 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | Completed
2024-12-14 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | Completed
2024-12-15 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | Completed
2024-12-15 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | Completed
2024-12-15 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | Completed
2024-12-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-15 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-15 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | Completed
2024-12-15 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | Completed
2024-12-16 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | Completed
2024-12-16 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | Completed
2024-12-16 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | Completed
2024-12-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-16 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-16 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | Completed
2024-12-16 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | Completed
2024-12-17 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | Completed
2024-12-17 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | Completed
2024-12-17 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | Completed
2024-12-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-17 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-17 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-17 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | Completed
2024-12-18 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | Completed
2024-12-18 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | Completed
2024-12-18 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | Completed
2024-12-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-18 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-18 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-18 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | Completed
2024-12-19 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | Completed
2024-12-19 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | Completed
2024-12-19 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | Completed
2024-12-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-19 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-19 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-19 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | Completed
2024-12-20 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | Completed
2024-12-20 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | Completed
2024-12-20 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | Completed
2024-12-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-20 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-20 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-20 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | Completed
2024-12-21 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | Completed
2024-12-21 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | Completed
2024-12-21 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | Completed
2024-12-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-21 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-21 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-21 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | Completed
2024-12-22 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | Completed
2024-12-22 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | Completed
2024-12-22 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | Completed
2024-12-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-22 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-22 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-22 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | Completed
2024-12-23 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | Completed
2024-12-23 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | Completed
2024-12-23 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | Completed
2024-12-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-23 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-23 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-23 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | Completed
2024-12-24 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | Completed
2024-12-24 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | Completed
2024-12-24 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | Completed
2024-12-24 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | Completed
2024-12-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-24 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-24 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | Completed
2024-12-24 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-24 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | Completed
2024-12-25 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | Completed
2024-12-25 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | Completed
2024-12-25 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | Completed
2024-12-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-25 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-25 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | Completed
2024-12-25 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-25 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | Completed
2024-12-26 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | Completed
2024-12-26 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | Completed
2024-12-26 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | Completed
2024-12-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-26 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | Completed
2024-12-26 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-26 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | Completed
2024-12-27 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | Completed
2024-12-27 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | Completed
2024-12-27 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | Completed
2024-12-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-27 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | Completed
2024-12-27 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-27 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | Completed
2024-12-28 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | Completed
2024-12-28 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | Completed
2024-12-28 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | Completed
2024-12-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-28 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | Completed
2024-12-28 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-28 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | Completed
2024-12-29 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | Completed
2024-12-29 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | Completed
2024-12-29 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | Completed
2024-12-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-29 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | Completed
2024-12-29 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-29 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | Completed
2024-12-30 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | Completed
2024-12-30 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | Completed
2024-12-30 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | Completed
2024-12-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-30 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | Completed
2024-12-30 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | Completed
2024-12-30 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | Completed
2024-12-31 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | Completed
2024-12-31 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | Completed
2024-12-31 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | Completed
2024-12-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-31 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | Completed
2024-12-31 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | Completed
2024-12-31 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | Completed
2025-01-01 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | Completed
2025-01-01 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | Completed
2025-01-01 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | Completed
2025-01-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-01 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | Completed
2025-01-01 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | Completed
2025-01-01 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | Completed
2025-01-02 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | Completed
2025-01-02 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | Completed
2025-01-02 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | Completed
2025-01-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-02 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | Completed
2025-01-02 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | Completed
2025-01-02 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | Completed
2025-01-03 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | Completed
2025-01-03 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | Completed
2025-01-03 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | Completed
2025-01-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-03 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | Completed
2025-01-03 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | Completed
2025-01-03 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | Completed
2025-01-04 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | Completed
2025-01-04 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | Completed
2025-01-04 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | Completed
2025-01-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-04 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | Completed
2025-01-04 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | Completed
2025-01-04 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | Completed
2025-01-05 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | Completed
2025-01-05 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | Completed
2025-01-05 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | Completed
2025-01-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-05 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | Completed
2025-01-05 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | Completed
2025-01-05 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | Completed
2025-01-06 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | Completed
2025-01-06 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | Completed
2025-01-06 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | Completed
2025-01-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-06 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | Completed
2025-01-06 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | Completed
2025-01-06 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | Completed
2025-01-07 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | Completed
2025-01-07 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | Completed
2025-01-07 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | Completed
2025-01-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-07 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | Completed
2025-01-07 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | Completed
2025-01-07 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | Completed
2025-01-07 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-08 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | Completed
2025-01-08 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | Completed
2025-01-08 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | Completed
2025-01-08 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | Completed
2025-01-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-08 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | Completed
2025-01-08 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | Completed
2025-01-08 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-09 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | Completed
2025-01-09 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | Completed
2025-01-09 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | Completed
2025-01-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-09 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | Completed
2025-01-09 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | Completed
2025-01-09 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-10 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | Completed
2025-01-10 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | Completed
2025-01-10 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | Completed
2025-01-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-10 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | Completed
2025-01-10 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | Completed
2025-01-10 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-11 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | Completed
2025-01-11 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | Completed
2025-01-11 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | Completed
2025-01-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-11 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | Completed
2025-01-11 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | Completed
2025-01-11 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | Completed
2025-01-11 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-12 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | Completed
2025-01-12 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | Completed
2025-01-12 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | Completed
2025-01-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-12 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | Completed
2025-01-12 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | Completed
2025-01-12 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-13 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | Completed
2025-01-13 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | Completed
2025-01-13 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | Completed
2025-01-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-13 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | Completed
2025-01-13 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | Completed
2025-01-13 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-14 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | Completed
2025-01-14 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | Completed
2025-01-14 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | Completed
2025-01-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-14 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | Completed
2025-01-14 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | Completed
2025-01-14 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-15 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | Completed
2025-01-15 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | Completed
2025-01-15 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | Completed
2025-01-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-15 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | Completed
2025-01-15 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | Completed
2025-01-15 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-16 | 2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | Completed
2025-01-16 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | Completed
2025-01-16 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | Completed
2025-01-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-16 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | Completed
2025-01-16 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | Completed
2025-01-16 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-17 | 2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | Completed
2025-01-17 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | Completed
2025-01-17 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | Completed
2025-01-17 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | Completed
2025-01-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-17 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | Completed
2025-01-17 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | Completed
2025-01-17 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-17 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-18 | 2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | Completed
2025-01-18 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | Completed
2025-01-18 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | Completed
2025-01-18 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | Completed
2025-01-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-18 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | Completed
2025-01-18 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | Completed
2025-01-18 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-18 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-19 | 2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | Completed
2025-01-19 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | Completed
2025-01-19 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | Completed
2025-01-19 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | Completed
2025-01-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-19 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | Completed
2025-01-19 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | Completed
2025-01-19 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-19 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-20 | 2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | Completed
2025-01-20 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | Completed
2025-01-20 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | Completed
2025-01-20 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | Completed
2025-01-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-20 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | Completed
2025-01-20 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | Completed
2025-01-20 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-21 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | Completed
2025-01-21 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | Completed
2025-01-21 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | Completed
2025-01-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-21 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | Completed
2025-01-21 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | Completed
2025-01-21 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-21 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | Completed
2025-01-22 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | Completed
2025-01-22 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | Completed
2025-01-22 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | Completed
2025-01-22 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | Completed
2025-01-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-22 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | Completed
2025-01-22 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | Completed
2025-01-22 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-22 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | Completed
2025-01-23 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | Completed
2025-01-23 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | Completed
2025-01-23 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | Completed
2025-01-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-23 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | Completed
2025-01-23 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-23 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | Completed
2025-01-24 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | Completed
2025-01-24 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | Completed
2025-01-24 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | Completed
2025-01-24 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | Completed
2025-01-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-24 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | Completed
2025-01-24 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-24 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | Completed
2025-01-25 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | Completed
2025-01-25 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | Completed
2025-01-25 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | Completed
2025-01-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-25 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | Completed
2025-01-25 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | Completed
2025-01-25 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-25 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | Completed
2025-01-26 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | Completed
2025-01-26 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | Completed
2025-01-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-26 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | Completed
2025-01-26 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | Completed
2025-01-26 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-26 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | Completed
2025-01-27 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | Completed
2025-01-27 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | Completed
2025-01-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-27 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | Completed
2025-01-27 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | Completed
2025-01-27 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-27 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | Completed
2025-01-28 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | Completed
2025-01-28 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | Completed
2025-01-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-28 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | Completed
2025-01-28 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | Completed
2025-01-28 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-28 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | Completed
2025-01-29 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | Completed
2025-01-29 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | Completed
2025-01-29 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | Completed
2025-01-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-29 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | Completed
2025-01-29 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | Completed
2025-01-29 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | Completed
2025-01-29 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-29 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | Completed
2025-01-29 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | Completed
2025-01-30 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | Completed
2025-01-30 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | Completed
2025-01-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-30 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | Completed
2025-01-30 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | Completed
2025-01-30 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | Completed
2025-01-30 | 2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | Completed
2025-01-30 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-30 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | Completed
2025-01-31 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | Completed
2025-01-31 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | Completed
2025-01-31 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | Completed
2025-01-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-31 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | Completed
2025-01-31 | 2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | Completed
2025-01-31 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-31 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-01-31 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | Completed
2025-02-01 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | Completed
2025-02-01 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | Completed
2025-02-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-01 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | Completed
2025-02-01 | 2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | Completed
2025-02-01 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-01 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | Completed
2025-02-02 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | Completed
2025-02-02 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | Completed
2025-02-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-02 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | Completed
2025-02-02 | 2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | Completed
2025-02-02 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-02 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | Completed
2025-02-03 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | Completed
2025-02-03 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | Completed
2025-02-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-03 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | Completed
2025-02-03 | 2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | Completed
2025-02-03 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | Completed
2025-02-03 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-03 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | Completed
2025-02-04 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | Completed
2025-02-04 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | Completed
2025-02-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-04 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | Completed
2025-02-04 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | Completed
2025-02-04 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-04 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | Completed
2025-02-05 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | Completed
2025-02-05 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | Completed
2025-02-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-05 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | Completed
2025-02-05 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | Completed
2025-02-05 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-05 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | Completed
2025-02-06 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | Completed
2025-02-06 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | Completed
2025-02-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-06 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | Completed
2025-02-06 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | Completed
2025-02-06 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-06 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | Completed
2025-02-07 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | Completed
2025-02-07 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | Completed
2025-02-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-07 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | Completed
2025-02-07 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | Completed
2025-02-07 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-07 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | Completed
2025-02-08 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | Completed
2025-02-08 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | Completed
2025-02-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-08 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | Completed
2025-02-08 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | Completed
2025-02-08 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-08 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | Completed
2025-02-09 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | Completed
2025-02-09 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | Completed
2025-02-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-09 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | Completed
2025-02-09 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | Completed
2025-02-09 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-09 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-10 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | Completed
2025-02-10 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | Completed
2025-02-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-10 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | Completed
2025-02-10 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | Completed
2025-02-10 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-10 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-11 | 2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | Completed
2025-02-11 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | Completed
2025-02-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-11 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | Completed
2025-02-11 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | Completed
2025-02-11 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-11 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-12 | 2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | Completed
2025-02-12 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | Completed
2025-02-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-12 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | Completed
2025-02-12 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | Completed
2025-02-12 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-12 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-13 | 2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | Completed
2025-02-13 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | Completed
2025-02-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-13 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | Completed
2025-02-13 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | Completed
2025-02-13 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-13 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-14 | 2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | Completed
2025-02-14 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | Completed
2025-02-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-14 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | Completed
2025-02-14 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | Completed
2025-02-14 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | Completed
2025-02-14 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-14 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-15 | 2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | Completed
2025-02-15 | 2025-02-15 | 2025-02-18 | Punam Devi 1 | 36.1598 | 9.0399 | TA413 | 38/9 | Completed
2025-02-15 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | Completed
2025-02-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-15 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | Completed
2025-02-15 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | Completed
2025-02-15 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-15 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-16 | 2025-02-15 | 2025-02-18 | Punam Devi 1 | 36.1598 | 9.0399 | TA413 | 38/9 | Completed
2025-02-16 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | Completed
2025-02-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-16 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | Completed
2025-02-16 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | Completed
2025-02-16 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | Completed
2025-02-16 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-16 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-17 | 2025-02-15 | 2025-02-18 | Punam Devi 1 | 36.1598 | 9.0399 | TA413 | 38/9 | Completed
2025-02-17 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | Completed
2025-02-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-17 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | Completed
2025-02-17 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | Completed
2025-02-17 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-17 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-18 | 2025-02-15 | 2025-02-18 | Punam Devi 1 | 36.1598 | 9.0399 | TA413 | 38/9 | Completed
2025-02-18 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | Completed
2025-02-18 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | Completed
2025-02-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-18 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | Completed
2025-02-18 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | Completed
2025-02-18 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-18 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-02-18 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-19 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | Completed
2025-02-19 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | Completed
2025-02-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-19 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | Completed
2025-02-19 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | Completed
2025-02-19 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-02-19 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-20 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | Completed
2025-02-20 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | Completed
2025-02-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-20 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | Completed
2025-02-20 | 2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | Completed
2025-02-20 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-02-20 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-21 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | Completed
2025-02-21 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | Completed
2025-02-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-21 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | Completed
2025-02-21 | 2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | Completed
2025-02-21 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-02-21 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-22 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | Completed
2025-02-22 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | Completed
2025-02-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-22 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | Completed
2025-02-22 | 2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | Completed
2025-02-22 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-02-22 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-23 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | Completed
2025-02-23 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | Completed
2025-02-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-23 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | Completed
2025-02-23 | 2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | Completed
2025-02-23 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-02-23 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-24 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | Completed
2025-02-24 | 2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | Completed
2025-02-24 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | Completed
2025-02-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-24 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | Completed
2025-02-24 | 2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | Completed
2025-02-24 | 2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | Completed
2025-02-24 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-02-24 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-02-25 | 2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | Completed
2025-02-25 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | Completed
2025-02-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-25 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | Completed
2025-02-25 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | Completed
2025-02-25 | 2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | Completed
2025-02-25 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-02-25 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-02-26 | 2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | Completed
2025-02-26 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | Completed
2025-02-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-26 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | Completed
2025-02-26 | 2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | Completed
2025-02-26 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-02-26 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-02-27 | 2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | Completed
2025-02-27 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | Completed
2025-02-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-27 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | Completed
2025-02-27 | 2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | Completed
2025-02-27 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-02-27 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-02-28 | 2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | Completed
2025-02-28 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | Completed
2025-02-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-28 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | Completed
2025-02-28 | 2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | Completed
2025-02-28 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-02-28 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-03-01 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | Completed
2025-03-01 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | Completed
2025-03-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-01 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | Completed
2025-03-01 | 2025-03-01 | 2025-03-04 | Punam Devi 4 | 36.1598 | 9.0399 | TA413 | 9/3 | Completed
2025-03-01 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-03-01 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-03-02 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | Completed
2025-03-02 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | Completed
2025-03-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-02 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | Completed
2025-03-02 | 2025-03-01 | 2025-03-04 | Punam Devi 4 | 36.1598 | 9.0399 | TA413 | 9/3 | Completed
2025-03-02 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-03-02 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-03-03 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | Completed
2025-03-03 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | Completed
2025-03-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-03 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | Completed
2025-03-03 | 2025-03-01 | 2025-03-04 | Punam Devi 4 | 36.1598 | 9.0399 | TA413 | 9/3 | Completed
2025-03-03 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-03-03 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-03-04 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | Completed
2025-03-04 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | Completed
2025-03-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-04 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | Completed
2025-03-04 | 2025-03-01 | 2025-03-04 | Punam Devi 4 | 36.1598 | 9.0399 | TA413 | 9/3 | Completed
2025-03-04 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-03-04 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-03-05 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | Completed
2025-03-05 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | Completed
2025-03-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-05 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | Completed
2025-03-05 | 2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | Completed
2025-03-05 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-03-06 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | Completed
2025-03-06 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | Completed
2025-03-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-06 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | Completed
2025-03-06 | 2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | Completed
2025-03-06 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-03-07 | 2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | Completed
2025-03-07 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | Completed
2025-03-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-07 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | Completed
2025-03-07 | 2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | Completed
2025-03-07 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-03-08 | 2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | Completed
2025-03-08 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | Completed
2025-03-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-08 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | Completed
2025-03-08 | 2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | Completed
2025-03-08 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-03-09 | 2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | Completed
2025-03-09 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | Completed
2025-03-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-09 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | Completed
2025-03-09 | 2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | Completed
2025-03-09 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-10 | 2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | Completed
2025-03-10 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | Completed
2025-03-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-10 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | Completed
2025-03-10 | 2025-03-10 | 2025-03-13 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 9/2 | Completed
2025-03-10 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-11 | 2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | Completed
2025-03-11 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | Completed
2025-03-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-11 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | Completed
2025-03-11 | 2025-03-10 | 2025-03-13 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 9/2 | Completed
2025-03-11 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-12 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | Completed
2025-03-12 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | Completed
2025-03-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-12 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | Completed
2025-03-12 | 2025-03-10 | 2025-03-13 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 9/2 | Completed
2025-03-12 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-13 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | Completed
2025-03-13 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | Completed
2025-03-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-13 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | Completed
2025-03-13 | 2025-03-10 | 2025-03-13 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 9/2 | Completed
2025-03-13 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-14 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | Completed
2025-03-14 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | Completed
2025-03-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-14 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | Completed
2025-03-14 | 2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | Completed
2025-03-14 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-15 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | Completed
2025-03-15 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | Completed
2025-03-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-15 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | Completed
2025-03-15 | 2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | Completed
2025-03-15 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-16 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | Completed
2025-03-16 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | Completed
2025-03-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-16 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | Completed
2025-03-16 | 2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | Completed
2025-03-16 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-17 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | Completed
2025-03-17 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | Completed
2025-03-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-17 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | Completed
2025-03-17 | 2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | Completed
2025-03-17 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-18 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | Completed
2025-03-18 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | Completed
2025-03-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-18 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | Completed
2025-03-18 | 2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | Completed
2025-03-18 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-19 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | Completed
2025-03-19 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | Completed
2025-03-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-19 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | Completed
2025-03-19 | 2025-03-19 | 2025-03-22 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 15/3 | Completed
2025-03-19 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-20 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | Completed
2025-03-20 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | Completed
2025-03-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-20 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | Completed
2025-03-20 | 2025-03-19 | 2025-03-22 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 15/3 | Completed
2025-03-20 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-21 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | Completed
2025-03-21 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | Completed
2025-03-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-21 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | Completed
2025-03-21 | 2025-03-19 | 2025-03-22 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 15/3 | Completed
2025-03-21 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-22 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | Completed
2025-03-22 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | Completed
2025-03-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-22 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | Completed
2025-03-22 | 2025-03-19 | 2025-03-22 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 15/3 | Completed
2025-03-22 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | Completed
2025-03-23 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | Completed
2025-03-23 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | Completed
2025-03-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-23 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | Completed
2025-03-23 | 2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | Completed
2025-03-23 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | Completed
2025-03-24 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | Completed
2025-03-24 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | Completed
2025-03-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-24 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | Completed
2025-03-24 | 2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | Completed
2025-03-24 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | Completed
2025-03-25 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | Completed
2025-03-25 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | Completed
2025-03-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-25 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | Completed
2025-03-25 | 2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | Completed
2025-03-25 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | Completed
2025-03-26 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | Completed
2025-03-26 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | Completed
2025-03-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-26 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | Completed
2025-03-26 | 2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | Completed
2025-03-26 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | Completed
2025-03-26 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | Completed
2025-03-27 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | Completed
2025-03-27 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | Completed
2025-03-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-27 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | Completed
2025-03-27 | 2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | Completed
2025-03-27 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | Completed
2025-03-27 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | Completed
2025-03-28 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | Completed
2025-03-28 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | Completed
2025-03-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-28 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | Completed
2025-03-28 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | Completed
2025-03-29 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | Completed
2025-03-29 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | Completed
2025-03-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-29 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | Completed
2025-03-29 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | Completed
2025-03-29 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-03-30 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | Completed
2025-03-30 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | Completed
2025-03-30 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | Completed
2025-03-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-30 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | Completed
2025-03-30 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-03-31 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | Completed
2025-03-31 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | Completed
2025-03-31 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | Completed
2025-03-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-31 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | Completed
2025-03-31 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | Completed
2025-03-31 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | Completed
2025-03-31 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-04-01 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | Completed
2025-04-01 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | Completed
2025-04-01 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | Completed
2025-04-01 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | Completed
2025-04-01 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-04-02 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | Completed
2025-04-02 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | Completed
2025-04-02 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | Completed
2025-04-02 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | Completed
2025-04-02 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-04-03 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | Completed
2025-04-03 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | Completed
2025-04-03 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | Completed
2025-04-03 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | Completed
2025-04-03 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-04-04 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | Completed
2025-04-04 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | Completed
2025-04-04 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | Completed
2025-04-04 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | Completed
2025-04-04 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-04-05 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | Completed
2025-04-05 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | Completed
2025-04-05 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | Completed
2025-04-05 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | Completed
2025-04-05 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | Completed
2025-04-05 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-04-06 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | Completed
2025-04-06 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | Completed
2025-04-06 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | Completed
2025-04-06 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | Completed
2025-04-06 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-04-07 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | Completed
2025-04-07 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | Completed
2025-04-07 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | Completed
2025-04-07 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-04-08 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | Completed
2025-04-08 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | Completed
2025-04-08 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | Completed
2025-04-08 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-04-09 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | Completed
2025-04-09 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | Completed
2025-04-09 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | Completed
2025-04-09 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | Completed
2025-04-09 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | Completed
2025-04-09 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-04-10 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | Completed
2025-04-10 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | Completed
2025-04-10 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | Completed
2025-04-10 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-04-11 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | Completed
2025-04-11 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | Completed
2025-04-11 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | Completed
2025-04-11 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-04-12 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | Completed
2025-04-12 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | Completed
2025-04-12 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | Completed
2025-04-13 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | Completed
2025-04-13 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | Completed
2025-04-13 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | Completed
2025-04-14 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | Completed
2025-04-14 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | Completed
2025-04-14 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | Completed
2025-04-14 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | Completed
2025-04-15 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | Completed
2025-04-15 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | Completed
2025-04-15 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | Completed
2025-04-16 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | Completed
2025-04-16 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | Completed
2025-04-16 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | Completed
2025-04-17 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | Completed
2025-04-17 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | Completed
2025-04-17 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | Completed
2025-04-18 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | Completed
2025-04-18 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-04-18 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | Completed
2025-04-18 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-04-18 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | Completed
2025-04-19 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-04-19 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-04-19 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | Completed
2025-04-20 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-04-20 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-04-20 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | Completed
2025-04-21 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-04-21 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-04-21 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | Completed
2025-04-22 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-04-22 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-04-22 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | Completed
2025-04-23 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-04-23 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-04-24 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-04-24 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-04-25 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-04-25 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-04-26 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-04-26 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-04-27 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-04-27 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-04-28 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-04-28 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-04-29 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-04-29 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-04-30 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-04-30 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-07-05 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-06 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-06 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-06 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | Completed
2025-07-07 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-07 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-07 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | Completed
2025-07-08 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-08 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-08 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | Completed
2025-07-09 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-09 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-09 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-09 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | Completed
2025-07-10 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-10 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-10 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-10 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | Completed
2025-07-11 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-11 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-11 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-11 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | Completed
2025-07-12 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-12 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-12 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-12 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | Completed
2025-07-13 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-13 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-13 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-13 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | Completed
2025-07-14 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-14 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-14 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-14 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | Completed
2025-07-15 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-15 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-15 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-15 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-15 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | Completed
2025-07-16 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-16 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-16 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-16 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | Completed
2025-07-16 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-16 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | Completed
2025-07-16 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-17 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-17 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-17 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-17 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | Completed
2025-07-17 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-17 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | Completed
2025-07-17 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-18 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | Completed
2025-07-18 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-18 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-18 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | Completed
2025-07-18 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-18 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | Completed
2025-07-18 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-18 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-19 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | Completed
2025-07-19 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-19 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-19 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | Completed
2025-07-19 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-19 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | Completed
2025-07-19 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-19 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-20 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | Completed
2025-07-20 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-20 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-20 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | Completed
2025-07-20 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-20 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | Completed
2025-07-20 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-20 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-21 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | Completed
2025-07-21 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-21 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-07-21 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-21 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | Completed
2025-07-21 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-21 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | Completed
2025-07-21 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-21 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-22 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | Completed
2025-07-22 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-22 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-07-22 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-22 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | Completed
2025-07-22 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | Completed
2025-07-22 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | Completed
2025-07-22 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-22 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-23 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | Completed
2025-07-23 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-23 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-07-23 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-23 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | Completed
2025-07-23 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | Completed
2025-07-23 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | Completed
2025-07-23 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-23 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-24 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | Completed
2025-07-24 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-24 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-07-24 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-24 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | Completed
2025-07-24 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | Completed
2025-07-24 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | Completed
2025-07-24 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-24 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-25 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | Completed
2025-07-25 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-25 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-07-25 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-25 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | Completed
2025-07-25 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | Completed
2025-07-25 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | Completed
2025-07-25 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-25 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-26 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | Completed
2025-07-26 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-26 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-07-26 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-26 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | Completed
2025-07-26 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | Completed
2025-07-26 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | Completed
2025-07-26 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-26 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-27 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | Completed
2025-07-27 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-27 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-07-27 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-27 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | Completed
2025-07-27 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | Completed
2025-07-27 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-27 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-28 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | Completed
2025-07-28 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-28 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-07-28 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-28 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | Completed
2025-07-28 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | Completed
2025-07-28 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-28 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-29 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | Completed
2025-07-29 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-29 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-07-29 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-29 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | Completed
2025-07-29 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | Completed
2025-07-29 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-29 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-30 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | Completed
2025-07-30 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-30 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-07-30 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-30 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | Completed
2025-07-30 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | Completed
2025-07-30 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-30 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-31 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | Completed
2025-07-31 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-31 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-07-31 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-31 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | Completed
2025-07-31 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | Completed
2025-07-31 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-31 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-08-01 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | Completed
2025-08-01 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-08-01 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-08-01 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-08-01 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | Completed
2025-08-01 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-01 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | Completed
2025-08-01 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | Completed
2025-08-01 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-08-01 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-08-02 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | Completed
2025-08-02 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-08-02 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-08-02 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | Completed
2025-08-02 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-08-02 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | Completed
2025-08-02 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-02 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | Completed
2025-08-02 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | Completed
2025-08-02 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | Completed
2025-08-02 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | Completed
2025-08-02 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-08-03 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | Completed
2025-08-03 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-08-03 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | Completed
2025-08-03 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-08-03 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | Completed
2025-08-03 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-03 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | Completed
2025-08-03 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | Completed
2025-08-03 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | Completed
2025-08-03 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | Completed
2025-08-03 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-08-04 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | Completed
2025-08-04 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-08-04 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | Completed
2025-08-04 | 2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | Completed
2025-08-04 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | Completed
2025-08-04 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-04 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | Completed
2025-08-04 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | Completed
2025-08-04 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | Completed
2025-08-04 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | Completed
2025-08-04 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | Completed
2025-08-05 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | Completed
2025-08-05 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-08-05 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | Completed
2025-08-05 | 2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | Completed
2025-08-05 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | Completed
2025-08-05 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-05 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | Completed
2025-08-05 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | Completed
2025-08-05 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | Completed
2025-08-05 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | Completed
2025-08-05 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | Completed
2025-08-06 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-08-06 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | Completed
2025-08-06 | 2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | Completed
2025-08-06 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | Completed
2025-08-06 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-06 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | Completed
2025-08-06 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | Completed
2025-08-06 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | Completed
2025-08-06 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | Completed
2025-08-06 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | Completed
2025-08-07 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | Completed
2025-08-07 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-08-07 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | Completed
2025-08-07 | 2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | Completed
2025-08-07 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | Completed
2025-08-07 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-07 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | Completed
2025-08-07 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | Completed
2025-08-07 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-07 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | Completed
2025-08-07 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | Completed
2025-08-07 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | Completed
2025-08-07 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | Completed
2025-08-08 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | Completed
2025-08-08 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | Completed
2025-08-08 | 2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | Completed
2025-08-08 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | Completed
2025-08-08 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | Completed
2025-08-08 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-08 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | Completed
2025-08-08 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | Completed
2025-08-08 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-08 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-08 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | Completed
2025-08-08 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | Completed
2025-08-08 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | Completed
2025-08-08 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | Completed
2025-08-09 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | Completed
2025-08-09 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | Completed
2025-08-09 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | Completed
2025-08-09 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | Completed
2025-08-09 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-09 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | Completed
2025-08-09 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | Completed
2025-08-09 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | Completed
2025-08-09 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-09 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-09 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | Completed
2025-08-09 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | Completed
2025-08-09 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | Completed
2025-08-09 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | Completed
2025-08-09 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | Completed
2025-08-10 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | Completed
2025-08-10 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | Completed
2025-08-10 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | Completed
2025-08-10 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-10 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | Completed
2025-08-10 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | Completed
2025-08-10 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-10 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-10 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | Completed
2025-08-10 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | Completed
2025-08-10 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | Completed
2025-08-10 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | Completed
2025-08-11 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | Completed
2025-08-11 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | Completed
2025-08-11 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | Completed
2025-08-11 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-11 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | Completed
2025-08-11 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | Completed
2025-08-11 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-11 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-11 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | Completed
2025-08-11 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | Completed
2025-08-11 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | Completed
2025-08-12 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | Completed
2025-08-12 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | Completed
2025-08-12 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | Completed
2025-08-12 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-12 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | Completed
2025-08-12 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | Completed
2025-08-12 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-12 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-12 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | Completed
2025-08-12 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | Completed
2025-08-12 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | Completed
2025-08-12 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | Completed
2025-08-13 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | Completed
2025-08-13 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | Completed
2025-08-13 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | Completed
2025-08-13 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | Completed
2025-08-13 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-13 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | Completed
2025-08-13 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | Completed
2025-08-13 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-13 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-13 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | Completed
2025-08-13 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | Completed
2025-08-13 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | Completed
2025-08-13 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | Completed
2025-08-14 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-14 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | Completed
2025-08-14 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | Completed
2025-08-14 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | Completed
2025-08-14 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | Completed
2025-08-14 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | Completed
2025-08-14 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | Completed
2025-08-14 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | Completed
2025-08-14 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-14 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-14 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | Completed
2025-08-14 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | Completed
2025-08-14 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | Completed
2025-08-14 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | Completed
2025-08-15 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-15 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | Completed
2025-08-15 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | Completed
2025-08-15 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | Completed
2025-08-15 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | Completed
2025-08-15 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | Completed
2025-08-15 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | Completed
2025-08-15 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | Completed
2025-08-15 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-15 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-15 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | Completed
2025-08-15 | 2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | Completed
2025-08-15 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | Completed
2025-08-15 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | Completed
2025-08-16 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-16 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | Completed
2025-08-16 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | Completed
2025-08-16 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | Completed
2025-08-16 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | Completed
2025-08-16 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | Completed
2025-08-16 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | Completed
2025-08-16 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | Completed
2025-08-16 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-16 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-16 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | Completed
2025-08-16 | 2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | Completed
2025-08-16 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | Completed
2025-08-16 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | Completed
2025-08-17 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-17 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | Completed
2025-08-17 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | Completed
2025-08-17 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | Completed
2025-08-17 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | Completed
2025-08-17 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | Completed
2025-08-17 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | Completed
2025-08-17 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | Completed
2025-08-17 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-17 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-17 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | Completed
2025-08-17 | 2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | Completed
2025-08-17 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | Completed
2025-08-17 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | Completed
2025-08-18 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-18 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | Completed
2025-08-18 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | Completed
2025-08-18 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | Completed
2025-08-18 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | Completed
2025-08-18 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | Completed
2025-08-18 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | Completed
2025-08-18 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | Completed
2025-08-18 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | Completed
2025-08-18 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-18 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-18 | 2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | Completed
2025-08-18 | 2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | Completed
2025-08-18 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | Completed
2025-08-18 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | Completed
2025-08-19 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-19 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | Completed
2025-08-19 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | Completed
2025-08-19 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | Completed
2025-08-19 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | Completed
2025-08-19 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | Completed
2025-08-19 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | Completed
2025-08-19 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | Completed
2025-08-19 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | Completed
2025-08-19 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-19 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-19 | 2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | Completed
2025-08-19 | 2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | Completed
2025-08-19 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | Completed
2025-08-19 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | Completed
2025-08-20 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-20 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | Completed
2025-08-20 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | Completed
2025-08-20 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | Completed
2025-08-20 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | Completed
2025-08-20 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | Completed
2025-08-20 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | Completed
2025-08-20 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | Completed
2025-08-20 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | Completed
2025-08-20 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-20 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-20 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | Completed
2025-08-20 | 2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | Completed
2025-08-20 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | Completed
2025-08-20 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | Completed
2025-08-20 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | Completed
2025-08-21 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-21 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | Completed
2025-08-21 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | Completed
2025-08-21 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | Completed
2025-08-21 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | Completed
2025-08-21 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | Completed
2025-08-21 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | Completed
2025-08-21 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | Completed
2025-08-21 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-21 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | Completed
2025-08-21 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | Completed
2025-08-21 | 2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | Completed
2025-08-21 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | Completed
2025-08-21 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | Completed
2025-08-21 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | Completed
2025-08-22 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-22 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | Completed
2025-08-22 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | Completed
2025-08-22 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | Completed
2025-08-22 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | Completed
2025-08-22 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | Completed
2025-08-22 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | Completed
2025-08-22 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | Completed
2025-08-22 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | Completed
2025-08-22 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | Completed
2025-08-22 | 2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | Completed
2025-08-22 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | Completed
2025-08-22 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | Completed
2025-08-22 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | Completed
2025-08-23 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-23 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | Completed
2025-08-23 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | Completed
2025-08-23 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | Completed
2025-08-23 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | Completed
2025-08-23 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | Completed
2025-08-23 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | Completed
2025-08-23 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | Completed
2025-08-23 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | Completed
2025-08-23 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | Completed
2025-08-23 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | Completed
2025-08-23 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | Completed
2025-08-23 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | Completed
2025-08-23 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | Completed
2025-08-23 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | Completed
2025-08-23 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | Completed
2025-08-23 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | Completed
2025-08-23 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | Completed
2025-08-24 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-24 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | Completed
2025-08-24 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | Completed
2025-08-24 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | Completed
2025-08-24 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | Completed
2025-08-24 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | Completed
2025-08-24 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | Completed
2025-08-24 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | Completed
2025-08-24 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | Completed
2025-08-24 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | Completed
2025-08-24 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | Completed
2025-08-24 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | Completed
2025-08-24 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | Completed
2025-08-24 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | Completed
2025-08-24 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | Completed
2025-08-24 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | Completed
2025-08-24 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | Completed
2025-08-24 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | Completed
2025-08-25 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-25 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | Completed
2025-08-25 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | Completed
2025-08-25 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-08-25 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | Completed
2025-08-25 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | Completed
2025-08-25 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | Completed
2025-08-25 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-08-25 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | Completed
2025-08-25 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | Completed
2025-08-25 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | Completed
2025-08-25 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | Completed
2025-08-25 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | Completed
2025-08-25 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | Completed
2025-08-25 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | Completed
2025-08-25 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | Completed
2025-08-25 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | Completed
2025-08-25 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | Completed
2025-08-25 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | Completed
2025-08-25 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | Completed
2025-08-25 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | Completed
2025-08-26 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-26 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | Completed
2025-08-26 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-08-26 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | Completed
2025-08-26 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | Completed
2025-08-26 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-08-26 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | Completed
2025-08-26 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | Completed
2025-08-26 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | Completed
2025-08-26 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | Completed
2025-08-26 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | Completed
2025-08-26 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | Completed
2025-08-26 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | Completed
2025-08-26 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | Completed
2025-08-26 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | Completed
2025-08-26 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | Completed
2025-08-26 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | Completed
2025-08-27 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-27 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | Completed
2025-08-27 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-08-27 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | Completed
2025-08-27 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | Completed
2025-08-27 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-08-27 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | Completed
2025-08-27 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | Completed
2025-08-27 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | Completed
2025-08-27 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | Completed
2025-08-27 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | Completed
2025-08-27 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | Completed
2025-08-27 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | Completed
2025-08-27 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | Completed
2025-08-27 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | Completed
2025-08-27 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | Completed
2025-08-27 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | Completed
2025-08-28 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-28 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | Completed
2025-08-28 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-08-28 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | Completed
2025-08-28 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | Completed
2025-08-28 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-08-28 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | Completed
2025-08-28 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | Completed
2025-08-28 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | Completed
2025-08-28 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | Completed
2025-08-28 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | Completed
2025-08-28 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | Completed
2025-08-28 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | Completed
2025-08-28 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | Completed
2025-08-28 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | Completed
2025-08-28 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | Completed
2025-08-28 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | Completed
2025-08-29 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-29 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | Completed
2025-08-29 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-08-29 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | Completed
2025-08-29 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | Completed
2025-08-29 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-08-29 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | Completed
2025-08-29 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | Completed
2025-08-29 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | Completed
2025-08-29 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | Completed
2025-08-29 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | Completed
2025-08-29 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | Completed
2025-08-29 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | Completed
2025-08-29 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | Completed
2025-08-29 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | Completed
2025-08-29 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | Completed
2025-08-29 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | Completed
2025-08-29 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | Completed
2025-08-30 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-30 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | Completed
2025-08-30 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-08-30 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | Completed
2025-08-30 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | Completed
2025-08-30 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-08-30 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | Completed
2025-08-30 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | Completed
2025-08-30 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | Completed
2025-08-30 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | Completed
2025-08-30 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | Completed
2025-08-30 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | Completed
2025-08-30 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | Completed
2025-08-30 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | Completed
2025-08-30 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | Completed
2025-08-30 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | Completed
2025-08-30 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | Completed
2025-08-30 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | Completed
2025-08-31 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-31 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | Completed
2025-08-31 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-08-31 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | Completed
2025-08-31 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | Completed
2025-08-31 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-08-31 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | Completed
2025-08-31 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | Completed
2025-08-31 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | Completed
2025-08-31 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | Completed
2025-08-31 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | Completed
2025-08-31 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | Completed
2025-08-31 | 2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | Completed
2025-08-31 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | Completed
2025-08-31 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | Completed
2025-08-31 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | Completed
2025-08-31 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | Completed
2025-08-31 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | Completed
2025-09-01 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-09-01 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | Completed
2025-09-01 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-09-01 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | Completed
2025-09-01 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | Completed
2025-09-01 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-09-01 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | Completed
2025-09-01 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | Completed
2025-09-01 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | Completed
2025-09-01 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | Completed
2025-09-01 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | Completed
2025-09-01 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | Completed
2025-09-01 | 2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | Completed
2025-09-01 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | Completed
2025-09-01 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | Completed
2025-09-01 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | Completed
2025-09-01 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | Completed
2025-09-02 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-09-02 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | Completed
2025-09-02 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-09-02 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | Completed
2025-09-02 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | Completed
2025-09-02 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-09-02 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | Completed
2025-09-02 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | Completed
2025-09-02 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | Completed
2025-09-02 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | Completed
2025-09-02 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | Completed
2025-09-02 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | Completed
2025-09-02 | 2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | Completed
2025-09-02 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | Completed
2025-09-02 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | Completed
2025-09-02 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | Completed
2025-09-02 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | Completed
2025-09-03 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | Completed
2025-09-03 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | Completed
2025-09-03 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-09-03 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | Completed
2025-09-03 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | Completed
2025-09-03 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-09-03 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | Completed
2025-09-03 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | Completed
2025-09-03 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | Completed
2025-09-03 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | Completed
2025-09-03 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | Completed
2025-09-03 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | Completed
2025-09-03 | 2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | Completed
2025-09-03 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | Completed
2025-09-03 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | Completed
2025-09-03 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | Completed
2025-09-03 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | Completed
2025-09-04 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | Completed
2025-09-04 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | Completed
2025-09-04 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-09-04 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | Completed
2025-09-04 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | Completed
2025-09-04 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-09-04 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | Completed
2025-09-04 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | Completed
2025-09-04 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | Completed
2025-09-04 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | Completed
2025-09-04 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | Completed
2025-09-04 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | Completed
2025-09-04 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | Completed
2025-09-04 | 2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | Completed
2025-09-04 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | Completed
2025-09-04 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | Completed
2025-09-04 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | Completed
2025-09-04 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | Completed
2025-09-05 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | Completed
2025-09-05 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | Completed
2025-09-05 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-09-05 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | Completed
2025-09-05 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | Completed
2025-09-05 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-09-05 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | Completed
2025-09-05 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | Completed
2025-09-05 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | Completed
2025-09-05 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | Completed
2025-09-05 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | Completed
2025-09-05 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | Completed
2025-09-05 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | Completed
2025-09-05 | 2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | Completed
2025-09-05 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | Completed
2025-09-05 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | Completed
2025-09-05 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | Completed
2025-09-05 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | Completed
2025-09-06 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | Completed
2025-09-06 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | Completed
2025-09-06 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-09-06 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | Completed
2025-09-06 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | Completed
2025-09-06 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-09-06 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | Completed
2025-09-06 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | Completed
2025-09-06 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | Completed
2025-09-06 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | Completed
2025-09-06 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | Completed
2025-09-06 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | Completed
2025-09-06 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | Completed
2025-09-06 | 2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | Completed
2025-09-06 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | Completed
2025-09-06 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | Completed
2025-09-06 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | Completed
2025-09-06 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | Completed
2025-09-07 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | Completed
2025-09-07 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | Completed
2025-09-07 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-09-07 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | Completed
2025-09-07 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | Completed
2025-09-07 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-09-07 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | Completed
2025-09-07 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | Completed
2025-09-07 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | Completed
2025-09-07 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | Completed
2025-09-07 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | Completed
2025-09-07 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | Completed
2025-09-07 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | Completed
2025-09-07 | 2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | Completed
2025-09-07 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | Completed
2025-09-07 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | Completed
2025-09-07 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | Completed
2025-09-07 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | Completed
2025-09-08 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | Completed
2025-09-08 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | Completed
2025-09-08 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-09-08 | 2025-09-08 | 2025-09-11 | Fouzi Ratto | 37.9311 | 9.4828 | TA413 | 43/6 | Completed
2025-09-08 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | Completed
2025-09-08 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-09-08 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | Completed
2025-09-08 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | Completed
2025-09-08 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | Completed
2025-09-08 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | Completed
2025-09-08 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | Completed
2025-09-08 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | Completed
2025-09-08 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | Completed
2025-09-08 | 2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | Completed
2025-09-08 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | Completed
2025-09-08 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | Completed
2025-09-08 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | Completed
2025-09-08 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | Completed
2025-09-09 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | Completed
2025-09-09 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | Completed
2025-09-09 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-09-09 | 2025-09-08 | 2025-09-11 | Fouzi Ratto | 37.9311 | 9.4828 | TA413 | 43/6 | Completed
2025-09-09 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | Completed
2025-09-09 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | Completed
2025-09-09 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | Completed
2025-09-09 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | Completed
2025-09-09 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | Completed
2025-09-09 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | Completed
2025-09-09 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | Completed
2025-09-09 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | Completed
2025-09-09 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-09 | 2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | Completed
2025-09-09 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | Completed
2025-09-09 | 2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | Completed
2025-09-09 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | Completed
2025-09-09 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | Completed
2025-09-09 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | Completed
2025-09-10 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | Completed
2025-09-10 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | Completed
2025-09-10 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-09-10 | 2025-09-08 | 2025-09-11 | Fouzi Ratto | 37.9311 | 9.4828 | TA413 | 43/6 | Completed
2025-09-10 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | Completed
2025-09-10 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | Completed
2025-09-10 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | Completed
2025-09-10 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | Completed
2025-09-10 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | Completed
2025-09-10 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | Completed
2025-09-10 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | Completed
2025-09-10 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | Completed
2025-09-10 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-10 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | Completed
2025-09-10 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | Completed
2025-09-10 | 2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | Completed
2025-09-10 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | Completed
2025-09-10 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | Completed
2025-09-10 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | Completed
2025-09-11 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | Completed
2025-09-11 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | Completed
2025-09-11 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-11 | 2025-09-08 | 2025-09-11 | Fouzi Ratto | 37.9311 | 9.4828 | TA413 | 43/6 | Completed
2025-09-11 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | Completed
2025-09-11 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | Completed
2025-09-11 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | Completed
2025-09-11 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | Completed
2025-09-11 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | Completed
2025-09-11 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | Completed
2025-09-11 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | Completed
2025-09-11 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | Completed
2025-09-11 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-11 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | Completed
2025-09-11 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | Completed
2025-09-11 | 2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | Completed
2025-09-11 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | Completed
2025-09-11 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-11 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | Completed
2025-09-11 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | Completed
2025-09-12 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | Completed
2025-09-12 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | Completed
2025-09-12 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-12 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | Completed
2025-09-12 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | Completed
2025-09-12 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | Completed
2025-09-12 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | Completed
2025-09-12 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | Completed
2025-09-12 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | Completed
2025-09-12 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | Completed
2025-09-12 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | Completed
2025-09-12 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-12 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | Completed
2025-09-12 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | Completed
2025-09-12 | 2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | Completed
2025-09-12 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | Completed
2025-09-12 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-12 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | Completed
2025-09-12 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | Completed
2025-09-13 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | Completed
2025-09-13 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | Completed
2025-09-13 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-13 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | Completed
2025-09-13 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | Completed
2025-09-13 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | Completed
2025-09-13 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | Completed
2025-09-13 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-13 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | Completed
2025-09-13 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | Completed
2025-09-13 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | Completed
2025-09-13 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | Completed
2025-09-13 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-13 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | Completed
2025-09-13 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | Completed
2025-09-13 | 2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | Completed
2025-09-13 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | Completed
2025-09-13 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-13 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | Completed
2025-09-13 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | Completed
2025-09-14 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | Completed
2025-09-14 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | Completed
2025-09-14 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-14 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 7.6162 | TA413 | 43/8 | Completed
2025-09-14 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | Completed
2025-09-14 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | Completed
2025-09-14 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | Completed
2025-09-14 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | Completed
2025-09-14 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-14 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | Completed
2025-09-14 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | Completed
2025-09-14 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | Completed
2025-09-14 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | Completed
2025-09-14 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-14 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | Completed
2025-09-14 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | Completed
2025-09-14 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | Completed
2025-09-14 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | Completed
2025-09-14 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-14 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | Completed
2025-09-14 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | Completed
2025-09-15 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | Completed
2025-09-15 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | Completed
2025-09-15 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-15 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 7.6162 | TA413 | 43/8 | Completed
2025-09-15 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | Completed
2025-09-15 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | Completed
2025-09-15 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | Completed
2025-09-15 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | Completed
2025-09-15 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-15 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | Completed
2025-09-15 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | Completed
2025-09-15 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | Completed
2025-09-15 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | Completed
2025-09-15 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-15 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | Completed
2025-09-15 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | Completed
2025-09-15 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | Completed
2025-09-15 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | Completed
2025-09-15 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-15 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | Completed
2025-09-15 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | Completed
2025-09-16 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | Completed
2025-09-16 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | Completed
2025-09-16 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-16 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 7.6162 | TA413 | 43/8 | Completed
2025-09-16 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | Completed
2025-09-16 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | Completed
2025-09-16 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | Completed
2025-09-16 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-16 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | Completed
2025-09-16 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | Completed
2025-09-16 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | Completed
2025-09-16 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | Completed
2025-09-16 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-16 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | Completed
2025-09-16 | 2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | Completed
2025-09-16 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | Completed
2025-09-16 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-16 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | Completed
2025-09-16 | 2025-09-16 | 2025-09-19 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/4 | Completed
2025-09-17 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | Completed
2025-09-17 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | Completed
2025-09-17 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-17 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 7.6162 | TA413 | 43/8 | Completed
2025-09-17 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | Completed
2025-09-17 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | Completed
2025-09-17 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-17 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | Completed
2025-09-17 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | Completed
2025-09-17 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | Completed
2025-09-17 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | Completed
2025-09-17 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-17 | 2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | Completed
2025-09-17 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | Completed
2025-09-17 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-17 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | Completed
2025-09-17 | 2025-09-16 | 2025-09-19 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/4 | Completed
2025-09-18 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | Completed
2025-09-18 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | Completed
2025-09-18 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-18 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 7.6162 | TA413 | 43/8 | Completed
2025-09-18 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | Completed
2025-09-18 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | Completed
2025-09-18 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | Completed
2025-09-18 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-18 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | Completed
2025-09-18 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | Completed
2025-09-18 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | Completed
2025-09-18 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | Completed
2025-09-18 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-18 | 2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | Completed
2025-09-18 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | Completed
2025-09-18 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-18 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | Completed
2025-09-18 | 2025-09-16 | 2025-09-19 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/4 | Completed
2025-09-19 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | Completed
2025-09-19 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | Completed
2025-09-19 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-19 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 7.6162 | TA413 | 43/8 | Completed
2025-09-19 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | Completed
2025-09-19 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | Completed
2025-09-19 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | Completed
2025-09-19 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-19 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | Completed
2025-09-19 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | Completed
2025-09-19 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | Completed
2025-09-19 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | Completed
2025-09-19 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-19 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | Completed
2025-09-19 | 2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | Completed
2025-09-19 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | Completed
2025-09-19 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-19 | 2025-09-16 | 2025-09-19 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/4 | Completed
2025-09-20 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | Completed
2025-09-20 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | Completed
2025-09-20 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-20 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | Completed
2025-09-20 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | Completed
2025-09-20 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | Completed
2025-09-20 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | Completed
2025-09-20 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-20 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | Completed
2025-09-20 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | Completed
2025-09-20 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | Completed
2025-09-20 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | Completed
2025-09-20 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-20 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | Completed
2025-09-20 | 2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | Completed
2025-09-20 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | Completed
2025-09-20 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-20 | 2025-09-20 | 2025-09-23 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/5 | Completed
2025-09-21 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | Completed
2025-09-21 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-21 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | Completed
2025-09-21 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | Completed
2025-09-21 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | Completed
2025-09-21 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | Completed
2025-09-21 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-21 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | Completed
2025-09-21 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | Completed
2025-09-21 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | Completed
2025-09-21 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | Completed
2025-09-21 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-21 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | Completed
2025-09-21 | 2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | Completed
2025-09-21 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | Completed
2025-09-21 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-21 | 2025-09-20 | 2025-09-23 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/5 | Completed
2025-09-22 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-22 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | Completed
2025-09-22 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | Completed
2025-09-22 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | Completed
2025-09-22 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | Completed
2025-09-22 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-22 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | Completed
2025-09-22 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | Completed
2025-09-22 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | Completed
2025-09-22 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | Completed
2025-09-22 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-22 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | Completed
2025-09-22 | 2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | Completed
2025-09-22 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | Completed
2025-09-22 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-22 | 2025-09-20 | 2025-09-23 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/5 | Completed
2025-09-23 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-23 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | Completed
2025-09-23 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | Completed
2025-09-23 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | Completed
2025-09-23 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | Completed
2025-09-23 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-23 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | Completed
2025-09-23 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | Completed
2025-09-23 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | Completed
2025-09-23 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | Completed
2025-09-23 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-23 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | Completed
2025-09-23 | 2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | Completed
2025-09-23 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-23 | 2025-09-20 | 2025-09-23 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/5 | Completed
2025-09-24 | 2025-09-24 | 2025-10-04 | Amar Kumar Singh | 45.697 | 4.1543 | TA413 | 41/1 | Completed
2025-09-24 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-24 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | Completed
2025-09-24 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | Completed
2025-09-24 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | Completed
2025-09-24 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | Completed
2025-09-24 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-24 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | Completed
2025-09-24 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | Completed
2025-09-24 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | Completed
2025-09-24 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | Completed
2025-09-24 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-24 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | Completed
2025-09-24 | 2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | Completed
2025-09-24 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-24 | 2025-09-24 | 2025-10-04 | Sk Samiul 1 | 45.697 | 4.1543 | TA413 | 30/2 | Completed
2025-09-24 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | Completed
2025-09-25 | 2025-09-24 | 2025-10-04 | Amar Kumar Singh | 45.697 | 4.1543 | TA413 | 41/1 | Completed
2025-09-25 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-25 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | Completed
2025-09-25 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | Completed
2025-09-25 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | Completed
2025-09-25 | 2025-09-25 | 2025-10-12 | Jwala Singh 1 | 72.1555 | 4.0086 | TA413 | 4/0 | Completed
2025-09-25 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-25 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | Completed
2025-09-25 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | Completed
2025-09-25 | 2025-09-25 | 2025-10-12 | Pritam Enterprises 2 | 66.7809 | 3.7101 | TA413 | 3B/0 | Completed
2025-09-25 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | Completed
2025-09-25 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-25 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | Completed
2025-09-25 | 2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | Completed
2025-09-25 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-25 | 2025-09-24 | 2025-10-04 | Sk Samiul 1 | 45.697 | 4.1543 | TA413 | 30/2 | Completed
2025-09-25 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | Completed
2025-09-26 | 2025-09-24 | 2025-10-04 | Amar Kumar Singh | 45.697 | 4.1543 | TA413 | 41/1 | Completed
2025-09-26 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-26 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | Completed
2025-09-26 | 2025-09-26 | 2025-10-07 | Govind Mahto 1 | 45.697 | 3.8081 | TA413 | 3B/2 | Completed
2025-09-26 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | Completed
2025-09-26 | 2025-09-25 | 2025-10-12 | Jwala Singh 1 | 72.1555 | 4.0086 | TA413 | 4/0 | Completed
2025-09-26 | 2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | Completed
2025-09-26 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | Completed
2025-09-26 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | Completed
2025-09-26 | 2025-09-25 | 2025-10-12 | Pritam Enterprises 2 | 66.7809 | 3.7101 | TA413 | 3B/0 | Completed
2025-09-26 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | Completed
2025-09-26 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-26 | 2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | Completed
2025-09-26 | 2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | Completed
2025-09-26 | 2025-09-26 | 2025-10-04 | Punam Kumari 4 | 43.8044 | 4.8672 | TA413 | 29A/5 | Completed
2025-09-26 | 2025-09-24 | 2025-10-04 | Sk Samiul 1 | 45.697 | 4.1543 | TA413 | 30/2 | Completed
2025-09-26 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | Completed
2025-09-27 | 2025-09-24 | 2025-10-04 | Amar Kumar Singh | 45.697 | 4.1543 | TA413 | 41/1 | Completed
2025-09-27 | 2025-09-27 | 2025-10-04 | Bhairaw Mahto | 37.1383 | 4.6423 | TA413 | 15/8 | Completed
2025-09-27 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | Completed
2025-09-27 | 2025-09-26 | 2025-10-07 | Govind Mahto 1 | 45.697 | 3.8081 | TA413 | 3B/2 | Completed
2025-09-27 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | Completed
2025-09-27 | 2025-09-25 | 2025-10-12 | Jwala Singh 1 | 72.1555 | 4.0086 | TA413 | 4/0 | Completed
2025-09-27 | 2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | Completed
2025-09-27 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | Completed
2025-09-27 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | Completed
2025-09-27 | 2025-09-25 | 2025-10-12 | Pritam Enterprises 2 | 66.7809 | 3.7101 | TA413 | 3B/0 | Completed
2025-09-27 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | Completed
2025-09-27 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-27 | 2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | Completed
2025-09-27 | 2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | Completed
2025-09-27 | 2025-09-26 | 2025-10-04 | Punam Kumari 4 | 43.8044 | 4.8672 | TA413 | 29A/5 | Completed
2025-09-27 | 2025-09-24 | 2025-10-04 | Sk Samiul 1 | 45.697 | 4.1543 | TA413 | 30/2 | Completed
2025-09-27 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | Completed
2025-09-28 | 2025-09-24 | 2025-10-04 | Amar Kumar Singh | 45.697 | 4.1543 | TA413 | 41/1 | Completed
2025-09-28 | 2025-09-27 | 2025-10-04 | Bhairaw Mahto | 37.1383 | 4.6423 | TA413 | 15/8 | Completed
2025-09-28 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | Completed
2025-09-28 | 2025-09-26 | 2025-10-07 | Govind Mahto 1 | 45.697 | 3.8081 | TA413 | 3B/2 | Completed
2025-09-28 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | Completed
2025-09-28 | 2025-09-25 | 2025-10-12 | Jwala Singh 1 | 72.1555 | 4.0086 | TA413 | 4/0 | Completed
2025-09-28 | 2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | Completed
2025-09-28 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | Completed
2025-09-28 | 2025-09-25 | 2025-10-12 | Pritam Enterprises 2 | 66.7809 | 3.7101 | TA413 | 3B/0 | Completed
2025-09-28 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | Completed
2025-09-28 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-28 | 2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | Completed
2025-09-28 | 2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | Completed
2025-09-28 | 2025-09-26 | 2025-10-04 | Punam Kumari 4 | 43.8044 | 4.8672 | TA413 | 29A/5 | Completed
2025-09-28 | 2025-09-24 | 2025-10-04 | Sk Samiul 1 | 45.697 | 4.1543 | TA413 | 30/2 | Completed
2025-09-28 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | Completed
2025-09-28 | 2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 5.5651 | TA413 | 45/0 | Completed
2025-09-29 | 2025-09-24 | 2025-10-04 | Amar Kumar Singh | 45.697 | 4.1543 | TA413 | 41/1 | Completed
2025-09-29 | 2025-09-27 | 2025-10-04 | Bhairaw Mahto | 37.1383 | 4.6423 | TA413 | 15/8 | Completed
2025-09-29 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | Completed
2025-09-29 | 2025-09-26 | 2025-10-07 | Govind Mahto 1 | 45.697 | 3.8081 | TA413 | 3B/2 | Completed
2025-09-29 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | Completed
2025-09-29 | 2025-09-25 | 2025-10-12 | Jwala Singh 1 | 72.1555 | 4.0086 | TA413 | 4/0 | Completed
2025-09-29 | 2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | Completed
2025-09-29 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | Completed
2025-09-29 | 2025-09-25 | 2025-10-12 | Pritam Enterprises 2 | 66.7809 | 3.7101 | TA413 | 3B/0 | Completed
2025-09-29 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | Completed
2025-09-29 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-29 | 2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | Completed
2025-09-29 | 2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | Completed
2025-09-29 | 2025-09-26 | 2025-10-04 | Punam Kumari 4 | 43.8044 | 4.8672 | TA413 | 29A/5 | Completed
2025-09-29 | 2025-09-24 | 2025-10-04 | Sk Samiul 1 | 45.697 | 4.1543 | TA413 | 30/2 | Completed
2025-09-29 | 2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 5.5651 | TA413 | 45/0 | Completed
2025-09-30 | 2025-09-24 | 2025-10-04 | Amar Kumar Singh | 45.697 | 4.1543 | TA413 | 41/1 | Completed
2025-09-30 | 2025-09-27 | 2025-10-04 | Bhairaw Mahto | 37.1383 | 4.6423 | TA413 | 15/8 | Completed
2025-09-30 | 2025-09-30 | 2025-10-12 | Fouzi Ratto | 70.7883 | 5.4453 | TA413 | 46/0 | Completed
2025-09-30 | 2025-09-26 | 2025-10-07 | Govind Mahto 1 | 45.697 | 3.8081 | TA413 | 3B/2 | Completed
2025-09-30 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | Completed
2025-09-30 | 2025-09-25 | 2025-10-12 | Jwala Singh 1 | 72.1555 | 4.0086 | TA413 | 4/0 | Completed
2025-09-30 | 2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | Completed
2025-09-30 | 2025-09-30 | 2025-10-09 | Kartik Mahto | 37.9311 | 3.7931 | TA413 | 40/10 | Completed
2025-09-30 | 2025-09-25 | 2025-10-12 | Pritam Enterprises 2 | 66.7809 | 3.7101 | TA413 | 3B/0 | Completed
2025-09-30 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | Completed
2025-09-30 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-30 | 2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | Completed
2025-09-30 | 2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | Completed
2025-09-30 | 2025-09-26 | 2025-10-04 | Punam Kumari 4 | 43.8044 | 4.8672 | TA413 | 29A/5 | Completed
2025-09-30 | 2025-09-24 | 2025-10-04 | Sk Samiul 1 | 45.697 | 4.1543 | TA413 | 30/2 | Completed
2025-09-30 | 2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 5.5651 | TA413 | 45/0 | Completed
2025-10-01 | 2025-09-24 | 2025-10-04 | Amar Kumar Singh | 45.697 | 4.1543 | TA413 | 41/1 | Completed
2025-10-01 | 2025-09-27 | 2025-10-04 | Bhairaw Mahto | 37.1383 | 4.6423 | TA413 | 15/8 | Completed
2025-10-01 | 2025-09-30 | 2025-10-12 | Fouzi Ratto | 70.7883 | 5.4453 | TA413 | 46/0 | Completed
2025-10-01 | 2025-09-26 | 2025-10-07 | Govind Mahto 1 | 45.697 | 3.8081 | TA413 | 3B/2 | Completed
2025-10-01 | 2025-09-25 | 2025-10-12 | Jwala Singh 1 | 72.1555 | 4.0086 | TA413 | 4/0 | Completed
2025-10-01 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-01 | 2025-09-30 | 2025-10-09 | Kartik Mahto | 37.9311 | 3.7931 | TA413 | 40/10 | Completed
2025-10-01 | 2025-09-25 | 2025-10-12 | Pritam Enterprises 2 | 66.7809 | 3.7101 | TA413 | 3B/0 | Completed
2025-10-01 | 2025-10-01 | 2025-10-10 | Pritam Enterprises 3 | 36.1598 | 3.616 | TA413 | 3A/4 | Completed
2025-10-01 | 2025-10-01 | 2025-10-15 | Punam Kumari 1 | 87.0213 | 5.8014 | TA413 | 20/0 | Completed
2025-10-01 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-01 | 2025-10-01 | 2025-10-06 | Punam Kumari 2 | 34.7898 | 5.7983 | TA413 | 18/4 | Completed
2025-10-01 | 2025-09-26 | 2025-10-04 | Punam Kumari 4 | 43.8044 | 4.8672 | TA413 | 29A/5 | Completed
2025-10-01 | 2025-09-24 | 2025-10-04 | Sk Samiul 1 | 45.697 | 4.1543 | TA413 | 30/2 | Completed
2025-10-01 | 2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 5.5651 | TA413 | 45/0 | Completed
2025-10-02 | 2025-09-24 | 2025-10-04 | Amar Kumar Singh | 45.697 | 4.1543 | TA413 | 41/1 | Completed
2025-10-02 | 2025-09-27 | 2025-10-04 | Bhairaw Mahto | 37.1383 | 4.6423 | TA413 | 15/8 | Completed
2025-10-02 | 2025-09-30 | 2025-10-12 | Fouzi Ratto | 70.7883 | 5.4453 | TA413 | 46/0 | Completed
2025-10-02 | 2025-09-26 | 2025-10-07 | Govind Mahto 1 | 45.697 | 3.8081 | TA413 | 3B/2 | Completed
2025-10-02 | 2025-09-25 | 2025-10-12 | Jwala Singh 1 | 72.1555 | 4.0086 | TA413 | 4/0 | Completed
2025-10-02 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-02 | 2025-09-30 | 2025-10-09 | Kartik Mahto | 37.9311 | 3.7931 | TA413 | 40/10 | Completed
2025-10-02 | 2025-10-02 | 2025-10-17 | Pritam Enterprises 1 | 65.0278 | 4.0642 | TA413 | 10/0 | Completed
2025-10-02 | 2025-09-25 | 2025-10-12 | Pritam Enterprises 2 | 66.7809 | 3.7101 | TA413 | 3B/0 | Completed
2025-10-02 | 2025-10-01 | 2025-10-10 | Pritam Enterprises 3 | 36.1598 | 3.616 | TA413 | 3A/4 | Completed
2025-10-02 | 2025-10-01 | 2025-10-15 | Punam Kumari 1 | 87.0213 | 5.8014 | TA413 | 20/0 | Completed
2025-10-02 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-02 | 2025-10-01 | 2025-10-06 | Punam Kumari 2 | 34.7898 | 5.7983 | TA413 | 18/4 | Completed
2025-10-02 | 2025-09-26 | 2025-10-04 | Punam Kumari 4 | 43.8044 | 4.8672 | TA413 | 29A/5 | Completed
2025-10-02 | 2025-09-24 | 2025-10-04 | Sk Samiul 1 | 45.697 | 4.1543 | TA413 | 30/2 | Completed
2025-10-02 | 2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 5.5651 | TA413 | 45/0 | Completed
2025-10-03 | 2025-09-24 | 2025-10-04 | Amar Kumar Singh | 45.697 | 4.1543 | TA413 | 41/1 | Completed
2025-10-03 | 2025-09-27 | 2025-10-04 | Bhairaw Mahto | 37.1383 | 4.6423 | TA413 | 15/8 | Completed
2025-10-03 | 2025-09-30 | 2025-10-12 | Fouzi Ratto | 70.7883 | 5.4453 | TA413 | 46/0 | Completed
2025-10-03 | 2025-09-26 | 2025-10-07 | Govind Mahto 1 | 45.697 | 3.8081 | TA413 | 3B/2 | Completed
2025-10-03 | 2025-09-25 | 2025-10-12 | Jwala Singh 1 | 72.1555 | 4.0086 | TA413 | 4/0 | Completed
2025-10-03 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-03 | 2025-09-30 | 2025-10-09 | Kartik Mahto | 37.9311 | 3.7931 | TA413 | 40/10 | Completed
2025-10-03 | 2025-10-02 | 2025-10-17 | Pritam Enterprises 1 | 65.0278 | 4.0642 | TA413 | 10/0 | Completed
2025-10-03 | 2025-09-25 | 2025-10-12 | Pritam Enterprises 2 | 66.7809 | 3.7101 | TA413 | 3B/0 | Completed
2025-10-03 | 2025-10-01 | 2025-10-10 | Pritam Enterprises 3 | 36.1598 | 3.616 | TA413 | 3A/4 | Completed
2025-10-03 | 2025-10-01 | 2025-10-15 | Punam Kumari 1 | 87.0213 | 5.8014 | TA413 | 20/0 | Completed
2025-10-03 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-03 | 2025-10-01 | 2025-10-06 | Punam Kumari 2 | 34.7898 | 5.7983 | TA413 | 18/4 | Completed
2025-10-03 | 2025-09-26 | 2025-10-04 | Punam Kumari 4 | 43.8044 | 4.8672 | TA413 | 29A/5 | Completed
2025-10-03 | 2025-09-24 | 2025-10-04 | Sk Samiul 1 | 45.697 | 4.1543 | TA413 | 30/2 | Completed
2025-10-03 | 2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 5.5651 | TA413 | 45/0 | Completed
2025-10-04 | 2025-09-24 | 2025-10-04 | Amar Kumar Singh | 45.697 | 4.1543 | TA413 | 41/1 | Completed
2025-10-04 | 2025-09-27 | 2025-10-04 | Bhairaw Mahto | 37.1383 | 4.6423 | TA413 | 15/8 | Completed
2025-10-04 | 2025-09-30 | 2025-10-12 | Fouzi Ratto | 70.7883 | 5.4453 | TA413 | 46/0 | Completed
2025-10-04 | 2025-09-26 | 2025-10-07 | Govind Mahto 1 | 45.697 | 3.8081 | TA413 | 3B/2 | Completed
2025-10-04 | 2025-09-25 | 2025-10-12 | Jwala Singh 1 | 72.1555 | 4.0086 | TA413 | 4/0 | Completed
2025-10-04 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-04 | 2025-09-30 | 2025-10-09 | Kartik Mahto | 37.9311 | 3.7931 | TA413 | 40/10 | Completed
2025-10-04 | 2025-10-02 | 2025-10-17 | Pritam Enterprises 1 | 65.0278 | 4.0642 | TA413 | 10/0 | Completed
2025-10-04 | 2025-09-25 | 2025-10-12 | Pritam Enterprises 2 | 66.7809 | 3.7101 | TA413 | 3B/0 | Completed
2025-10-04 | 2025-10-01 | 2025-10-10 | Pritam Enterprises 3 | 36.1598 | 3.616 | TA413 | 3A/4 | Completed
2025-10-04 | 2025-10-01 | 2025-10-15 | Punam Kumari 1 | 87.0213 | 5.8014 | TA413 | 20/0 | Completed
2025-10-04 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-04 | 2025-10-01 | 2025-10-06 | Punam Kumari 2 | 34.7898 | 5.7983 | TA413 | 18/4 | Completed
2025-10-04 | 2025-09-26 | 2025-10-04 | Punam Kumari 4 | 43.8044 | 4.8672 | TA413 | 29A/5 | Completed
2025-10-04 | 2025-09-24 | 2025-10-04 | Sk Samiul 1 | 45.697 | 4.1543 | TA413 | 30/2 | Completed
2025-10-04 | 2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 5.5651 | TA413 | 45/0 | Completed
2025-10-05 | 2025-10-05 | 2025-10-22 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 41/0 | Completed
2025-10-05 | 2025-09-30 | 2025-10-12 | Fouzi Ratto | 70.7883 | 5.4453 | TA413 | 46/0 | Completed
2025-10-05 | 2025-09-26 | 2025-10-07 | Govind Mahto 1 | 45.697 | 3.8081 | TA413 | 3B/2 | Completed
2025-10-05 | 2025-10-05 | 2025-10-30 | Govind Mahto 2 | 137.0461 | 5.271 | TA413 | 15/0 | Completed
2025-10-05 | 2025-09-25 | 2025-10-12 | Jwala Singh 1 | 72.1555 | 4.0086 | TA413 | 4/0 | Completed
2025-10-05 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-05 | 2025-09-30 | 2025-10-09 | Kartik Mahto | 37.9311 | 3.7931 | TA413 | 40/10 | Completed
2025-10-05 | 2025-10-02 | 2025-10-17 | Pritam Enterprises 1 | 65.0278 | 4.0642 | TA413 | 10/0 | Completed
2025-10-05 | 2025-09-25 | 2025-10-12 | Pritam Enterprises 2 | 66.7809 | 3.7101 | TA413 | 3B/0 | Completed
2025-10-05 | 2025-10-01 | 2025-10-10 | Pritam Enterprises 3 | 36.1598 | 3.616 | TA413 | 3A/4 | Completed
2025-10-05 | 2025-10-01 | 2025-10-15 | Punam Kumari 1 | 87.0213 | 5.8014 | TA413 | 20/0 | Completed
2025-10-05 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-05 | 2025-10-01 | 2025-10-06 | Punam Kumari 2 | 34.7898 | 5.7983 | TA413 | 18/4 | Completed
2025-10-05 | 2025-10-05 | 2025-10-10 | Punam Kumari 4 | 37.9311 | 6.3218 | TA413 | 29A/4 | Completed
2025-10-05 | 2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 5.5651 | TA413 | 45/0 | Completed
2025-10-06 | 2025-10-05 | 2025-10-22 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 41/0 | Completed
2025-10-06 | 2025-09-30 | 2025-10-12 | Fouzi Ratto | 70.7883 | 5.4453 | TA413 | 46/0 | Completed
2025-10-06 | 2025-09-26 | 2025-10-07 | Govind Mahto 1 | 45.697 | 3.8081 | TA413 | 3B/2 | Completed
2025-10-06 | 2025-10-05 | 2025-10-30 | Govind Mahto 2 | 137.0461 | 5.271 | TA413 | 15/0 | Completed
2025-10-06 | 2025-09-25 | 2025-10-12 | Jwala Singh 1 | 72.1555 | 4.0086 | TA413 | 4/0 | Completed
2025-10-06 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-06 | 2025-09-30 | 2025-10-09 | Kartik Mahto | 37.9311 | 3.7931 | TA413 | 40/10 | Completed
2025-10-06 | 2025-10-02 | 2025-10-17 | Pritam Enterprises 1 | 65.0278 | 4.0642 | TA413 | 10/0 | Completed
2025-10-06 | 2025-09-25 | 2025-10-12 | Pritam Enterprises 2 | 66.7809 | 3.7101 | TA413 | 3B/0 | Completed
2025-10-06 | 2025-10-01 | 2025-10-10 | Pritam Enterprises 3 | 36.1598 | 3.616 | TA413 | 3A/4 | Completed
2025-10-06 | 2025-10-01 | 2025-10-15 | Punam Kumari 1 | 87.0213 | 5.8014 | TA413 | 20/0 | Completed
2025-10-06 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-06 | 2025-10-01 | 2025-10-06 | Punam Kumari 2 | 34.7898 | 5.7983 | TA413 | 18/4 | Completed
2025-10-06 | 2025-10-05 | 2025-10-10 | Punam Kumari 4 | 37.9311 | 6.3218 | TA413 | 29A/4 | Completed
2025-10-06 | 2025-10-06 | 2025-10-22 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 29A/0 | Completed
2025-10-06 | 2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 5.5651 | TA413 | 45/0 | Completed
2025-10-07 | 2025-10-05 | 2025-10-22 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 41/0 | Completed
2025-10-07 | 2025-09-30 | 2025-10-12 | Fouzi Ratto | 70.7883 | 5.4453 | TA413 | 46/0 | Completed
2025-10-07 | 2025-09-26 | 2025-10-07 | Govind Mahto 1 | 45.697 | 3.8081 | TA413 | 3B/2 | Completed
2025-10-07 | 2025-10-05 | 2025-10-30 | Govind Mahto 2 | 137.0461 | 5.271 | TA413 | 15/0 | Completed
2025-10-07 | 2025-09-25 | 2025-10-12 | Jwala Singh 1 | 72.1555 | 4.0086 | TA413 | 4/0 | Completed
2025-10-07 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-07 | 2025-10-07 | 2025-10-12 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 29/1 | Completed
2025-10-07 | 2025-09-30 | 2025-10-09 | Kartik Mahto | 37.9311 | 3.7931 | TA413 | 40/10 | Completed
2025-10-07 | 2025-10-02 | 2025-10-17 | Pritam Enterprises 1 | 65.0278 | 4.0642 | TA413 | 10/0 | Completed
2025-10-07 | 2025-09-25 | 2025-10-12 | Pritam Enterprises 2 | 66.7809 | 3.7101 | TA413 | 3B/0 | Completed
2025-10-07 | 2025-10-01 | 2025-10-10 | Pritam Enterprises 3 | 36.1598 | 3.616 | TA413 | 3A/4 | Completed
2025-10-07 | 2025-10-01 | 2025-10-15 | Punam Kumari 1 | 87.0213 | 5.8014 | TA413 | 20/0 | Completed
2025-10-07 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-07 | 2025-10-07 | 2025-10-10 | Punam Kumari 2 | 36.1598 | 9.0399 | TA413 | 18/5 | Completed
2025-10-07 | 2025-10-05 | 2025-10-10 | Punam Kumari 4 | 37.9311 | 6.3218 | TA413 | 29A/4 | Completed
2025-10-07 | 2025-10-06 | 2025-10-22 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 29A/0 | Completed
2025-10-07 | 2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 5.5651 | TA413 | 45/0 | Completed
2025-10-08 | 2025-10-05 | 2025-10-22 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 41/0 | Completed
2025-10-08 | 2025-09-30 | 2025-10-12 | Fouzi Ratto | 70.7883 | 5.4453 | TA413 | 46/0 | Completed
2025-10-08 | 2025-10-05 | 2025-10-30 | Govind Mahto 2 | 137.0461 | 5.271 | TA413 | 15/0 | Completed
2025-10-08 | 2025-09-25 | 2025-10-12 | Jwala Singh 1 | 72.1555 | 4.0086 | TA413 | 4/0 | Completed
2025-10-08 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-08 | 2025-10-07 | 2025-10-12 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 29/1 | Completed
2025-10-08 | 2025-09-30 | 2025-10-09 | Kartik Mahto | 37.9311 | 3.7931 | TA413 | 40/10 | Completed
2025-10-08 | 2025-10-02 | 2025-10-17 | Pritam Enterprises 1 | 65.0278 | 4.0642 | TA413 | 10/0 | Completed
2025-10-08 | 2025-09-25 | 2025-10-12 | Pritam Enterprises 2 | 66.7809 | 3.7101 | TA413 | 3B/0 | Completed
2025-10-08 | 2025-10-01 | 2025-10-10 | Pritam Enterprises 3 | 36.1598 | 3.616 | TA413 | 3A/4 | Completed
2025-10-08 | 2025-10-08 | 2025-10-25 | Pritam Enterprises 4 | 62.4437 | 3.4691 | TA413 | 29/0 | Completed
2025-10-08 | 2025-10-01 | 2025-10-15 | Punam Kumari 1 | 87.0213 | 5.8014 | TA413 | 20/0 | Completed
2025-10-08 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-08 | 2025-10-07 | 2025-10-10 | Punam Kumari 2 | 36.1598 | 9.0399 | TA413 | 18/5 | Completed
2025-10-08 | 2025-10-05 | 2025-10-10 | Punam Kumari 4 | 37.9311 | 6.3218 | TA413 | 29A/4 | Completed
2025-10-08 | 2025-10-06 | 2025-10-22 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 29A/0 | Completed
2025-10-08 | 2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 5.5651 | TA413 | 45/0 | Completed
2025-10-09 | 2025-10-05 | 2025-10-22 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 41/0 | Completed
2025-10-09 | 2025-09-30 | 2025-10-12 | Fouzi Ratto | 70.7883 | 5.4453 | TA413 | 46/0 | Completed
2025-10-09 | 2025-10-09 | 2025-10-16 | Govind Mahto 1 | 37.9311 | 4.7414 | TA413 | 3B/1 | Completed
2025-10-09 | 2025-10-05 | 2025-10-30 | Govind Mahto 2 | 137.0461 | 5.271 | TA413 | 15/0 | Completed
2025-10-09 | 2025-09-25 | 2025-10-12 | Jwala Singh 1 | 72.1555 | 4.0086 | TA413 | 4/0 | Completed
2025-10-09 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-09 | 2025-10-07 | 2025-10-12 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 29/1 | Completed
2025-10-09 | 2025-09-30 | 2025-10-09 | Kartik Mahto | 37.9311 | 3.7931 | TA413 | 40/10 | Completed
2025-10-09 | 2025-10-02 | 2025-10-17 | Pritam Enterprises 1 | 65.0278 | 4.0642 | TA413 | 10/0 | Completed
2025-10-09 | 2025-09-25 | 2025-10-12 | Pritam Enterprises 2 | 66.7809 | 3.7101 | TA413 | 3B/0 | Completed
2025-10-09 | 2025-10-01 | 2025-10-10 | Pritam Enterprises 3 | 36.1598 | 3.616 | TA413 | 3A/4 | Completed
2025-10-09 | 2025-10-08 | 2025-10-25 | Pritam Enterprises 4 | 62.4437 | 3.4691 | TA413 | 29/0 | Completed
2025-10-09 | 2025-10-01 | 2025-10-15 | Punam Kumari 1 | 87.0213 | 5.8014 | TA413 | 20/0 | Completed
2025-10-09 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-09 | 2025-10-07 | 2025-10-10 | Punam Kumari 2 | 36.1598 | 9.0399 | TA413 | 18/5 | Completed
2025-10-09 | 2025-10-05 | 2025-10-10 | Punam Kumari 4 | 37.9311 | 6.3218 | TA413 | 29A/4 | Completed
2025-10-09 | 2025-10-06 | 2025-10-22 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 29A/0 | Completed
2025-10-09 | 2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 5.5651 | TA413 | 45/0 | Completed
2025-10-10 | 2025-10-05 | 2025-10-22 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 41/0 | Completed
2025-10-10 | 2025-09-30 | 2025-10-12 | Fouzi Ratto | 70.7883 | 5.4453 | TA413 | 46/0 | Completed
2025-10-10 | 2025-10-09 | 2025-10-16 | Govind Mahto 1 | 37.9311 | 4.7414 | TA413 | 3B/1 | Completed
2025-10-10 | 2025-10-05 | 2025-10-30 | Govind Mahto 2 | 137.0461 | 5.271 | TA413 | 15/0 | Completed
2025-10-10 | 2025-09-25 | 2025-10-12 | Jwala Singh 1 | 72.1555 | 4.0086 | TA413 | 4/0 | Completed
2025-10-10 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-10 | 2025-10-07 | 2025-10-12 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 29/1 | Completed
2025-10-10 | 2025-10-10 | 2025-10-19 | Kartik Mahto | 35.6018 | 3.5602 | TA413 | 40/8 | Completed
2025-10-10 | 2025-10-02 | 2025-10-17 | Pritam Enterprises 1 | 65.0278 | 4.0642 | TA413 | 10/0 | Completed
2025-10-10 | 2025-09-25 | 2025-10-12 | Pritam Enterprises 2 | 66.7809 | 3.7101 | TA413 | 3B/0 | Completed
2025-10-10 | 2025-10-01 | 2025-10-10 | Pritam Enterprises 3 | 36.1598 | 3.616 | TA413 | 3A/4 | Completed
2025-10-10 | 2025-10-08 | 2025-10-25 | Pritam Enterprises 4 | 62.4437 | 3.4691 | TA413 | 29/0 | Completed
2025-10-10 | 2025-10-01 | 2025-10-15 | Punam Kumari 1 | 87.0213 | 5.8014 | TA413 | 20/0 | Completed
2025-10-10 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-10 | 2025-10-07 | 2025-10-10 | Punam Kumari 2 | 36.1598 | 9.0399 | TA413 | 18/5 | Completed
2025-10-10 | 2025-10-05 | 2025-10-10 | Punam Kumari 4 | 37.9311 | 6.3218 | TA413 | 29A/4 | Completed
2025-10-10 | 2025-10-06 | 2025-10-22 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 29A/0 | Completed
2025-10-10 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-10-11 | 2025-10-05 | 2025-10-22 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 41/0 | Completed
2025-10-11 | 2025-09-30 | 2025-10-12 | Fouzi Ratto | 70.7883 | 5.4453 | TA413 | 46/0 | Completed
2025-10-11 | 2025-10-09 | 2025-10-16 | Govind Mahto 1 | 37.9311 | 4.7414 | TA413 | 3B/1 | Completed
2025-10-11 | 2025-10-05 | 2025-10-30 | Govind Mahto 2 | 137.0461 | 5.271 | TA413 | 15/0 | Completed
2025-10-11 | 2025-09-25 | 2025-10-12 | Jwala Singh 1 | 72.1555 | 4.0086 | TA413 | 4/0 | Completed
2025-10-11 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-11 | 2025-10-07 | 2025-10-12 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 29/1 | Completed
2025-10-11 | 2025-10-10 | 2025-10-19 | Kartik Mahto | 35.6018 | 3.5602 | TA413 | 40/8 | Completed
2025-10-11 | 2025-10-02 | 2025-10-17 | Pritam Enterprises 1 | 65.0278 | 4.0642 | TA413 | 10/0 | Completed
2025-10-11 | 2025-09-25 | 2025-10-12 | Pritam Enterprises 2 | 66.7809 | 3.7101 | TA413 | 3B/0 | Completed
2025-10-11 | 2025-10-11 | 2025-10-26 | Pritam Enterprises 3 | 77.0769 | 4.8173 | TA413 | 3A/0 | Completed
2025-10-11 | 2025-10-08 | 2025-10-25 | Pritam Enterprises 4 | 62.4437 | 3.4691 | TA413 | 29/0 | Completed
2025-10-11 | 2025-10-01 | 2025-10-15 | Punam Kumari 1 | 87.0213 | 5.8014 | TA413 | 20/0 | Completed
2025-10-11 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-11 | 2025-10-11 | 2025-10-15 | Punam Kumari 2 | 45.697 | 9.1394 | TA413 | 18/6 | Completed
2025-10-11 | 2025-10-06 | 2025-10-22 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 29A/0 | Completed
2025-10-11 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-10-12 | 2025-10-05 | 2025-10-22 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 41/0 | Completed
2025-10-12 | 2025-10-12 | 2025-10-27 | Bhairaw Mahto | 72.1555 | 4.5097 | TA413 | 23/0 | Completed
2025-10-12 | 2025-09-30 | 2025-10-12 | Fouzi Ratto | 70.7883 | 5.4453 | TA413 | 46/0 | Completed
2025-10-12 | 2025-10-09 | 2025-10-16 | Govind Mahto 1 | 37.9311 | 4.7414 | TA413 | 3B/1 | Completed
2025-10-12 | 2025-10-05 | 2025-10-30 | Govind Mahto 2 | 137.0461 | 5.271 | TA413 | 15/0 | Completed
2025-10-12 | 2025-09-25 | 2025-10-12 | Jwala Singh 1 | 72.1555 | 4.0086 | TA413 | 4/0 | Completed
2025-10-12 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-12 | 2025-10-12 | 2025-10-31 | Jwala Singh 1 | 37.9311 | 1.8966 | TA413 | 10/1 | Completed
2025-10-12 | 2025-10-07 | 2025-10-12 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 29/1 | Completed
2025-10-12 | 2025-10-12 | 2025-10-22 | Jwala Singh 2 | 37.9311 | 3.4483 | TA413 | 30/3 | Completed
2025-10-12 | 2025-10-10 | 2025-10-19 | Kartik Mahto | 35.6018 | 3.5602 | TA413 | 40/8 | Completed
2025-10-12 | 2025-10-02 | 2025-10-17 | Pritam Enterprises 1 | 65.0278 | 4.0642 | TA413 | 10/0 | Completed
2025-10-12 | 2025-09-25 | 2025-10-12 | Pritam Enterprises 2 | 66.7809 | 3.7101 | TA413 | 3B/0 | Completed
2025-10-12 | 2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-10-12 | 2025-10-11 | 2025-10-26 | Pritam Enterprises 3 | 77.0769 | 4.8173 | TA413 | 3A/0 | Completed
2025-10-12 | 2025-10-08 | 2025-10-25 | Pritam Enterprises 4 | 62.4437 | 3.4691 | TA413 | 29/0 | Completed
2025-10-12 | 2025-10-01 | 2025-10-15 | Punam Kumari 1 | 87.0213 | 5.8014 | TA413 | 20/0 | Completed
2025-10-12 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-12 | 2025-10-11 | 2025-10-15 | Punam Kumari 2 | 45.697 | 9.1394 | TA413 | 18/6 | Completed
2025-10-12 | 2025-10-06 | 2025-10-22 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 29A/0 | Completed
2025-10-12 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-10-13 | 2025-10-05 | 2025-10-22 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 41/0 | Completed
2025-10-13 | 2025-10-12 | 2025-10-27 | Bhairaw Mahto | 72.1555 | 4.5097 | TA413 | 23/0 | Completed
2025-10-13 | 2025-10-09 | 2025-10-16 | Govind Mahto 1 | 37.9311 | 4.7414 | TA413 | 3B/1 | Completed
2025-10-13 | 2025-10-05 | 2025-10-30 | Govind Mahto 2 | 137.0461 | 5.271 | TA413 | 15/0 | Completed
2025-10-13 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-13 | 2025-10-12 | 2025-10-31 | Jwala Singh 1 | 37.9311 | 1.8966 | TA413 | 10/1 | Completed
2025-10-13 | 2025-10-12 | 2025-10-22 | Jwala Singh 2 | 37.9311 | 3.4483 | TA413 | 30/3 | Completed
2025-10-13 | 2025-10-10 | 2025-10-19 | Kartik Mahto | 35.6018 | 3.5602 | TA413 | 40/8 | Completed
2025-10-13 | 2025-10-02 | 2025-10-17 | Pritam Enterprises 1 | 65.0278 | 4.0642 | TA413 | 10/0 | Completed
2025-10-13 | 2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-10-13 | 2025-10-11 | 2025-10-26 | Pritam Enterprises 3 | 77.0769 | 4.8173 | TA413 | 3A/0 | Completed
2025-10-13 | 2025-10-08 | 2025-10-25 | Pritam Enterprises 4 | 62.4437 | 3.4691 | TA413 | 29/0 | Completed
2025-10-13 | 2025-10-01 | 2025-10-15 | Punam Kumari 1 | 87.0213 | 5.8014 | TA413 | 20/0 | Completed
2025-10-13 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-13 | 2025-10-11 | 2025-10-15 | Punam Kumari 2 | 45.697 | 9.1394 | TA413 | 18/6 | Completed
2025-10-13 | 2025-10-06 | 2025-10-22 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 29A/0 | Completed
2025-10-13 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-10-14 | 2025-10-05 | 2025-10-22 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 41/0 | Completed
2025-10-14 | 2025-10-12 | 2025-10-27 | Bhairaw Mahto | 72.1555 | 4.5097 | TA413 | 23/0 | Completed
2025-10-14 | 2025-10-09 | 2025-10-16 | Govind Mahto 1 | 37.9311 | 4.7414 | TA413 | 3B/1 | Completed
2025-10-14 | 2025-10-05 | 2025-10-30 | Govind Mahto 2 | 137.0461 | 5.271 | TA413 | 15/0 | Completed
2025-10-14 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-14 | 2025-10-12 | 2025-10-31 | Jwala Singh 1 | 37.9311 | 1.8966 | TA413 | 10/1 | Completed
2025-10-14 | 2025-10-12 | 2025-10-22 | Jwala Singh 2 | 37.9311 | 3.4483 | TA413 | 30/3 | Completed
2025-10-14 | 2025-10-10 | 2025-10-19 | Kartik Mahto | 35.6018 | 3.5602 | TA413 | 40/8 | Completed
2025-10-14 | 2025-10-02 | 2025-10-17 | Pritam Enterprises 1 | 65.0278 | 4.0642 | TA413 | 10/0 | Completed
2025-10-14 | 2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-10-14 | 2025-10-11 | 2025-10-26 | Pritam Enterprises 3 | 77.0769 | 4.8173 | TA413 | 3A/0 | Completed
2025-10-14 | 2025-10-08 | 2025-10-25 | Pritam Enterprises 4 | 62.4437 | 3.4691 | TA413 | 29/0 | Completed
2025-10-14 | 2025-10-01 | 2025-10-15 | Punam Kumari 1 | 87.0213 | 5.8014 | TA413 | 20/0 | Completed
2025-10-14 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-14 | 2025-10-11 | 2025-10-15 | Punam Kumari 2 | 45.697 | 9.1394 | TA413 | 18/6 | Completed
2025-10-14 | 2025-10-06 | 2025-10-22 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 29A/0 | Completed
2025-10-14 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-10-15 | 2025-10-05 | 2025-10-22 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 41/0 | Completed
2025-10-15 | 2025-10-12 | 2025-10-27 | Bhairaw Mahto | 72.1555 | 4.5097 | TA413 | 23/0 | Completed
2025-10-15 | 2025-10-09 | 2025-10-16 | Govind Mahto 1 | 37.9311 | 4.7414 | TA413 | 3B/1 | Completed
2025-10-15 | 2025-10-05 | 2025-10-30 | Govind Mahto 2 | 137.0461 | 5.271 | TA413 | 15/0 | Completed
2025-10-15 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-15 | 2025-10-12 | 2025-10-31 | Jwala Singh 1 | 37.9311 | 1.8966 | TA413 | 10/1 | Completed
2025-10-15 | 2025-10-12 | 2025-10-22 | Jwala Singh 2 | 37.9311 | 3.4483 | TA413 | 30/3 | Completed
2025-10-15 | 2025-10-10 | 2025-10-19 | Kartik Mahto | 35.6018 | 3.5602 | TA413 | 40/8 | Completed
2025-10-15 | 2025-10-02 | 2025-10-17 | Pritam Enterprises 1 | 65.0278 | 4.0642 | TA413 | 10/0 | Completed
2025-10-15 | 2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-10-15 | 2025-10-11 | 2025-10-26 | Pritam Enterprises 3 | 77.0769 | 4.8173 | TA413 | 3A/0 | Completed
2025-10-15 | 2025-10-08 | 2025-10-25 | Pritam Enterprises 4 | 62.4437 | 3.4691 | TA413 | 29/0 | Completed
2025-10-15 | 2025-10-01 | 2025-10-15 | Punam Kumari 1 | 87.0213 | 5.8014 | TA413 | 20/0 | Completed
2025-10-15 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-15 | 2025-10-11 | 2025-10-15 | Punam Kumari 2 | 45.697 | 9.1394 | TA413 | 18/6 | Completed
2025-10-15 | 2025-10-06 | 2025-10-22 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 29A/0 | Completed
2025-10-15 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-10-16 | 2025-10-05 | 2025-10-22 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 41/0 | Completed
2025-10-16 | 2025-10-12 | 2025-10-27 | Bhairaw Mahto | 72.1555 | 4.5097 | TA413 | 23/0 | Completed
2025-10-16 | 2025-10-09 | 2025-10-16 | Govind Mahto 1 | 37.9311 | 4.7414 | TA413 | 3B/1 | Completed
2025-10-16 | 2025-10-05 | 2025-10-30 | Govind Mahto 2 | 137.0461 | 5.271 | TA413 | 15/0 | Completed
2025-10-16 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-16 | 2025-10-12 | 2025-10-31 | Jwala Singh 1 | 37.9311 | 1.8966 | TA413 | 10/1 | Completed
2025-10-16 | 2025-10-12 | 2025-10-22 | Jwala Singh 2 | 37.9311 | 3.4483 | TA413 | 30/3 | Completed
2025-10-16 | 2025-10-10 | 2025-10-19 | Kartik Mahto | 35.6018 | 3.5602 | TA413 | 40/8 | Completed
2025-10-16 | 2025-10-02 | 2025-10-17 | Pritam Enterprises 1 | 65.0278 | 4.0642 | TA413 | 10/0 | Completed
2025-10-16 | 2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-10-16 | 2025-10-11 | 2025-10-26 | Pritam Enterprises 3 | 77.0769 | 4.8173 | TA413 | 3A/0 | Completed
2025-10-16 | 2025-10-08 | 2025-10-25 | Pritam Enterprises 4 | 62.4437 | 3.4691 | TA413 | 29/0 | Completed
2025-10-16 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-16 | 2025-10-16 | 2025-10-27 | Punam Kumari 1 | 87.0213 | 7.2518 | TA413 | 19/0 | Completed
2025-10-16 | 2025-10-16 | 2025-10-22 | Punam Kumari 2 | 37.1383 | 5.3055 | TA413 | 18/7 | Completed
2025-10-16 | 2025-10-06 | 2025-10-22 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 29A/0 | Completed
2025-10-16 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-10-17 | 2025-10-05 | 2025-10-22 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 41/0 | Completed
2025-10-17 | 2025-10-12 | 2025-10-27 | Bhairaw Mahto | 72.1555 | 4.5097 | TA413 | 23/0 | Completed
2025-10-17 | 2025-10-17 | 2025-10-23 | Govind Mahto 1 | 34.7898 | 4.97 | TA413 | 20/6 | Completed
2025-10-17 | 2025-10-05 | 2025-10-30 | Govind Mahto 2 | 137.0461 | 5.271 | TA413 | 15/0 | Completed
2025-10-17 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-17 | 2025-10-12 | 2025-10-31 | Jwala Singh 1 | 37.9311 | 1.8966 | TA413 | 10/1 | Completed
2025-10-17 | 2025-10-12 | 2025-10-22 | Jwala Singh 2 | 37.9311 | 3.4483 | TA413 | 30/3 | Completed
2025-10-17 | 2025-10-10 | 2025-10-19 | Kartik Mahto | 35.6018 | 3.5602 | TA413 | 40/8 | Completed
2025-10-17 | 2025-10-02 | 2025-10-17 | Pritam Enterprises 1 | 65.0278 | 4.0642 | TA413 | 10/0 | Completed
2025-10-17 | 2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-10-17 | 2025-10-11 | 2025-10-26 | Pritam Enterprises 3 | 77.0769 | 4.8173 | TA413 | 3A/0 | Completed
2025-10-17 | 2025-10-08 | 2025-10-25 | Pritam Enterprises 4 | 62.4437 | 3.4691 | TA413 | 29/0 | Completed
2025-10-17 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-17 | 2025-10-16 | 2025-10-27 | Punam Kumari 1 | 87.0213 | 7.2518 | TA413 | 19/0 | Completed
2025-10-17 | 2025-10-16 | 2025-10-22 | Punam Kumari 2 | 37.1383 | 5.3055 | TA413 | 18/7 | Completed
2025-10-17 | 2025-10-06 | 2025-10-22 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 29A/0 | Completed
2025-10-17 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-10-18 | 2025-10-05 | 2025-10-22 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 41/0 | Completed
2025-10-18 | 2025-10-12 | 2025-10-27 | Bhairaw Mahto | 72.1555 | 4.5097 | TA413 | 23/0 | Completed
2025-10-18 | 2025-10-17 | 2025-10-23 | Govind Mahto 1 | 34.7898 | 4.97 | TA413 | 20/6 | Completed
2025-10-18 | 2025-10-05 | 2025-10-30 | Govind Mahto 2 | 137.0461 | 5.271 | TA413 | 15/0 | Completed
2025-10-18 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-18 | 2025-10-12 | 2025-10-31 | Jwala Singh 1 | 37.9311 | 1.8966 | TA413 | 10/1 | Completed
2025-10-18 | 2025-10-12 | 2025-10-22 | Jwala Singh 2 | 37.9311 | 3.4483 | TA413 | 30/3 | Completed
2025-10-18 | 2025-10-10 | 2025-10-19 | Kartik Mahto | 35.6018 | 3.5602 | TA413 | 40/8 | Completed
2025-10-18 | 2025-10-18 | 2025-10-28 | Pritam Enterprises 1 | 37.9311 | 3.4483 | TA413 | 9/11 | Completed
2025-10-18 | 2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-10-18 | 2025-10-11 | 2025-10-26 | Pritam Enterprises 3 | 77.0769 | 4.8173 | TA413 | 3A/0 | Completed
2025-10-18 | 2025-10-08 | 2025-10-25 | Pritam Enterprises 4 | 62.4437 | 3.4691 | TA413 | 29/0 | Completed
2025-10-18 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-18 | 2025-10-16 | 2025-10-27 | Punam Kumari 1 | 87.0213 | 7.2518 | TA413 | 19/0 | Completed
2025-10-18 | 2025-10-16 | 2025-10-22 | Punam Kumari 2 | 37.1383 | 5.3055 | TA413 | 18/7 | Completed
2025-10-18 | 2025-10-06 | 2025-10-22 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 29A/0 | Completed
2025-10-18 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-10-19 | 2025-10-05 | 2025-10-22 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 41/0 | Completed
2025-10-19 | 2025-10-12 | 2025-10-27 | Bhairaw Mahto | 72.1555 | 4.5097 | TA413 | 23/0 | Completed
2025-10-19 | 2025-10-17 | 2025-10-23 | Govind Mahto 1 | 34.7898 | 4.97 | TA413 | 20/6 | Completed
2025-10-19 | 2025-10-05 | 2025-10-30 | Govind Mahto 2 | 137.0461 | 5.271 | TA413 | 15/0 | Completed
2025-10-19 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-19 | 2025-10-12 | 2025-10-31 | Jwala Singh 1 | 37.9311 | 1.8966 | TA413 | 10/1 | Completed
2025-10-19 | 2025-10-12 | 2025-10-22 | Jwala Singh 2 | 37.9311 | 3.4483 | TA413 | 30/3 | Completed
2025-10-19 | 2025-10-10 | 2025-10-19 | Kartik Mahto | 35.6018 | 3.5602 | TA413 | 40/8 | Completed
2025-10-19 | 2025-10-18 | 2025-10-28 | Pritam Enterprises 1 | 37.9311 | 3.4483 | TA413 | 9/11 | Completed
2025-10-19 | 2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-10-19 | 2025-10-11 | 2025-10-26 | Pritam Enterprises 3 | 77.0769 | 4.8173 | TA413 | 3A/0 | Completed
2025-10-19 | 2025-10-08 | 2025-10-25 | Pritam Enterprises 4 | 62.4437 | 3.4691 | TA413 | 29/0 | Completed
2025-10-19 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-19 | 2025-10-16 | 2025-10-27 | Punam Kumari 1 | 87.0213 | 7.2518 | TA413 | 19/0 | Completed
2025-10-19 | 2025-10-16 | 2025-10-22 | Punam Kumari 2 | 37.1383 | 5.3055 | TA413 | 18/7 | Completed
2025-10-19 | 2025-10-06 | 2025-10-22 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 29A/0 | Completed
2025-10-19 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-10-20 | 2025-10-05 | 2025-10-22 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 41/0 | Completed
2025-10-20 | 2025-10-12 | 2025-10-27 | Bhairaw Mahto | 72.1555 | 4.5097 | TA413 | 23/0 | Completed
2025-10-20 | 2025-10-17 | 2025-10-23 | Govind Mahto 1 | 34.7898 | 4.97 | TA413 | 20/6 | Completed
2025-10-20 | 2025-10-05 | 2025-10-30 | Govind Mahto 2 | 137.0461 | 5.271 | TA413 | 15/0 | Completed
2025-10-20 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-20 | 2025-10-12 | 2025-10-31 | Jwala Singh 1 | 37.9311 | 1.8966 | TA413 | 10/1 | Completed
2025-10-20 | 2025-10-12 | 2025-10-22 | Jwala Singh 2 | 37.9311 | 3.4483 | TA413 | 30/3 | Completed
2025-10-20 | 2025-10-20 | 2025-10-29 | Kartik Mahto | 55.4509 | 5.5451 | TA413 | 21/0 | Completed
2025-10-20 | 2025-10-18 | 2025-10-28 | Pritam Enterprises 1 | 37.9311 | 3.4483 | TA413 | 9/11 | Completed
2025-10-20 | 2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-10-20 | 2025-10-11 | 2025-10-26 | Pritam Enterprises 3 | 77.0769 | 4.8173 | TA413 | 3A/0 | Completed
2025-10-20 | 2025-10-08 | 2025-10-25 | Pritam Enterprises 4 | 62.4437 | 3.4691 | TA413 | 29/0 | Completed
2025-10-20 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-20 | 2025-10-16 | 2025-10-27 | Punam Kumari 1 | 87.0213 | 7.2518 | TA413 | 19/0 | Completed
2025-10-20 | 2025-10-16 | 2025-10-22 | Punam Kumari 2 | 37.1383 | 5.3055 | TA413 | 18/7 | Completed
2025-10-20 | 2025-10-06 | 2025-10-22 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 29A/0 | Completed
2025-10-20 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-10-21 | 2025-10-05 | 2025-10-22 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 41/0 | Completed
2025-10-21 | 2025-10-12 | 2025-10-27 | Bhairaw Mahto | 72.1555 | 4.5097 | TA413 | 23/0 | Completed
2025-10-21 | 2025-10-17 | 2025-10-23 | Govind Mahto 1 | 34.7898 | 4.97 | TA413 | 20/6 | Completed
2025-10-21 | 2025-10-05 | 2025-10-30 | Govind Mahto 2 | 137.0461 | 5.271 | TA413 | 15/0 | Completed
2025-10-21 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-21 | 2025-10-12 | 2025-10-31 | Jwala Singh 1 | 37.9311 | 1.8966 | TA413 | 10/1 | Completed
2025-10-21 | 2025-10-12 | 2025-10-22 | Jwala Singh 2 | 37.9311 | 3.4483 | TA413 | 30/3 | Completed
2025-10-21 | 2025-10-20 | 2025-10-29 | Kartik Mahto | 55.4509 | 5.5451 | TA413 | 21/0 | Completed
2025-10-21 | 2025-10-18 | 2025-10-28 | Pritam Enterprises 1 | 37.9311 | 3.4483 | TA413 | 9/11 | Completed
2025-10-21 | 2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-10-21 | 2025-10-11 | 2025-10-26 | Pritam Enterprises 3 | 77.0769 | 4.8173 | TA413 | 3A/0 | Completed
2025-10-21 | 2025-10-08 | 2025-10-25 | Pritam Enterprises 4 | 62.4437 | 3.4691 | TA413 | 29/0 | Completed
2025-10-21 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-21 | 2025-10-16 | 2025-10-27 | Punam Kumari 1 | 87.0213 | 7.2518 | TA413 | 19/0 | Completed
2025-10-21 | 2025-10-16 | 2025-10-22 | Punam Kumari 2 | 37.1383 | 5.3055 | TA413 | 18/7 | Completed
2025-10-21 | 2025-10-06 | 2025-10-22 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 29A/0 | Completed
2025-10-21 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-10-22 | 2025-10-05 | 2025-10-22 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 41/0 | Completed
2025-10-22 | 2025-10-12 | 2025-10-27 | Bhairaw Mahto | 72.1555 | 4.5097 | TA413 | 23/0 | Completed
2025-10-22 | 2025-10-17 | 2025-10-23 | Govind Mahto 1 | 34.7898 | 4.97 | TA413 | 20/6 | Completed
2025-10-22 | 2025-10-05 | 2025-10-30 | Govind Mahto 2 | 137.0461 | 5.271 | TA413 | 15/0 | Completed
2025-10-22 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-22 | 2025-10-12 | 2025-10-31 | Jwala Singh 1 | 37.9311 | 1.8966 | TA413 | 10/1 | Completed
2025-10-22 | 2025-10-12 | 2025-10-22 | Jwala Singh 2 | 37.9311 | 3.4483 | TA413 | 30/3 | Completed
2025-10-22 | 2025-10-20 | 2025-10-29 | Kartik Mahto | 55.4509 | 5.5451 | TA413 | 21/0 | Completed
2025-10-22 | 2025-10-18 | 2025-10-28 | Pritam Enterprises 1 | 37.9311 | 3.4483 | TA413 | 9/11 | Completed
2025-10-22 | 2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-10-22 | 2025-10-11 | 2025-10-26 | Pritam Enterprises 3 | 77.0769 | 4.8173 | TA413 | 3A/0 | Completed
2025-10-22 | 2025-10-08 | 2025-10-25 | Pritam Enterprises 4 | 62.4437 | 3.4691 | TA413 | 29/0 | Completed
2025-10-22 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-22 | 2025-10-16 | 2025-10-27 | Punam Kumari 1 | 87.0213 | 7.2518 | TA413 | 19/0 | Completed
2025-10-22 | 2025-10-16 | 2025-10-22 | Punam Kumari 2 | 37.1383 | 5.3055 | TA413 | 18/7 | Completed
2025-10-22 | 2025-10-06 | 2025-10-22 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 29A/0 | Completed
2025-10-22 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-10-23 | 2025-10-12 | 2025-10-27 | Bhairaw Mahto | 72.1555 | 4.5097 | TA413 | 23/0 | Completed
2025-10-23 | 2025-10-17 | 2025-10-23 | Govind Mahto 1 | 34.7898 | 4.97 | TA413 | 20/6 | Completed
2025-10-23 | 2025-10-05 | 2025-10-30 | Govind Mahto 2 | 137.0461 | 5.271 | TA413 | 15/0 | Completed
2025-10-23 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-23 | 2025-10-12 | 2025-10-31 | Jwala Singh 1 | 37.9311 | 1.8966 | TA413 | 10/1 | Completed
2025-10-23 | 2025-10-23 | 2025-10-30 | Jwala Singh 2 | 35.6018 | 4.4502 | TA413 | 27/5 | Completed
2025-10-23 | 2025-10-20 | 2025-10-29 | Kartik Mahto | 55.4509 | 5.5451 | TA413 | 21/0 | Completed
2025-10-23 | 2025-10-18 | 2025-10-28 | Pritam Enterprises 1 | 37.9311 | 3.4483 | TA413 | 9/11 | Completed
2025-10-23 | 2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-10-23 | 2025-10-11 | 2025-10-26 | Pritam Enterprises 3 | 77.0769 | 4.8173 | TA413 | 3A/0 | Completed
2025-10-23 | 2025-10-08 | 2025-10-25 | Pritam Enterprises 4 | 62.4437 | 3.4691 | TA413 | 29/0 | Completed
2025-10-23 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-23 | 2025-10-16 | 2025-10-27 | Punam Kumari 1 | 87.0213 | 7.2518 | TA413 | 19/0 | Completed
2025-10-23 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-10-24 | 2025-10-12 | 2025-10-27 | Bhairaw Mahto | 72.1555 | 4.5097 | TA413 | 23/0 | Completed
2025-10-24 | 2025-10-24 | 2025-10-29 | Govind Mahto 1 | 36.1598 | 6.0266 | TA413 | 21/1 | Completed
2025-10-24 | 2025-10-05 | 2025-10-30 | Govind Mahto 2 | 137.0461 | 5.271 | TA413 | 15/0 | Completed
2025-10-24 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-24 | 2025-10-12 | 2025-10-31 | Jwala Singh 1 | 37.9311 | 1.8966 | TA413 | 10/1 | Completed
2025-10-24 | 2025-10-23 | 2025-10-30 | Jwala Singh 2 | 35.6018 | 4.4502 | TA413 | 27/5 | Completed
2025-10-24 | 2025-10-20 | 2025-10-29 | Kartik Mahto | 55.4509 | 5.5451 | TA413 | 21/0 | Completed
2025-10-24 | 2025-10-18 | 2025-10-28 | Pritam Enterprises 1 | 37.9311 | 3.4483 | TA413 | 9/11 | Completed
2025-10-24 | 2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-10-24 | 2025-10-11 | 2025-10-26 | Pritam Enterprises 3 | 77.0769 | 4.8173 | TA413 | 3A/0 | Completed
2025-10-24 | 2025-10-08 | 2025-10-25 | Pritam Enterprises 4 | 62.4437 | 3.4691 | TA413 | 29/0 | Completed
2025-10-24 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-24 | 2025-10-16 | 2025-10-27 | Punam Kumari 1 | 87.0213 | 7.2518 | TA413 | 19/0 | Completed
2025-10-24 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-10-25 | 2025-10-12 | 2025-10-27 | Bhairaw Mahto | 72.1555 | 4.5097 | TA413 | 23/0 | Completed
2025-10-25 | 2025-10-24 | 2025-10-29 | Govind Mahto 1 | 36.1598 | 6.0266 | TA413 | 21/1 | Completed
2025-10-25 | 2025-10-05 | 2025-10-30 | Govind Mahto 2 | 137.0461 | 5.271 | TA413 | 15/0 | Completed
2025-10-25 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-25 | 2025-10-12 | 2025-10-31 | Jwala Singh 1 | 37.9311 | 1.8966 | TA413 | 10/1 | Completed
2025-10-25 | 2025-10-23 | 2025-10-30 | Jwala Singh 2 | 35.6018 | 4.4502 | TA413 | 27/5 | Completed
2025-10-25 | 2025-10-20 | 2025-10-29 | Kartik Mahto | 55.4509 | 5.5451 | TA413 | 21/0 | Completed
2025-10-25 | 2025-10-18 | 2025-10-28 | Pritam Enterprises 1 | 37.9311 | 3.4483 | TA413 | 9/11 | Completed
2025-10-25 | 2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-10-25 | 2025-10-11 | 2025-10-26 | Pritam Enterprises 3 | 77.0769 | 4.8173 | TA413 | 3A/0 | Completed
2025-10-25 | 2025-10-08 | 2025-10-25 | Pritam Enterprises 4 | 62.4437 | 3.4691 | TA413 | 29/0 | Completed
2025-10-25 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-25 | 2025-10-16 | 2025-10-27 | Punam Kumari 1 | 87.0213 | 7.2518 | TA413 | 19/0 | Completed
2025-10-25 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-10-26 | 2025-10-12 | 2025-10-27 | Bhairaw Mahto | 72.1555 | 4.5097 | TA413 | 23/0 | Completed
2025-10-26 | 2025-10-24 | 2025-10-29 | Govind Mahto 1 | 36.1598 | 6.0266 | TA413 | 21/1 | Completed
2025-10-26 | 2025-10-05 | 2025-10-30 | Govind Mahto 2 | 137.0461 | 5.271 | TA413 | 15/0 | Completed
2025-10-26 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-26 | 2025-10-12 | 2025-10-31 | Jwala Singh 1 | 37.9311 | 1.8966 | TA413 | 10/1 | Completed
2025-10-26 | 2025-10-23 | 2025-10-30 | Jwala Singh 2 | 35.6018 | 4.4502 | TA413 | 27/5 | Completed
2025-10-26 | 2025-10-20 | 2025-10-29 | Kartik Mahto | 55.4509 | 5.5451 | TA413 | 21/0 | Completed
2025-10-26 | 2025-10-18 | 2025-10-28 | Pritam Enterprises 1 | 37.9311 | 3.4483 | TA413 | 9/11 | Completed
2025-10-26 | 2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-10-26 | 2025-10-11 | 2025-10-26 | Pritam Enterprises 3 | 77.0769 | 4.8173 | TA413 | 3A/0 | Completed
2025-10-26 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-26 | 2025-10-16 | 2025-10-27 | Punam Kumari 1 | 87.0213 | 7.2518 | TA413 | 19/0 | Completed
2025-10-26 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-10-27 | 2025-10-12 | 2025-10-27 | Bhairaw Mahto | 72.1555 | 4.5097 | TA413 | 23/0 | Completed
2025-10-27 | 2025-10-24 | 2025-10-29 | Govind Mahto 1 | 36.1598 | 6.0266 | TA413 | 21/1 | Completed
2025-10-27 | 2025-10-05 | 2025-10-30 | Govind Mahto 2 | 137.0461 | 5.271 | TA413 | 15/0 | Completed
2025-10-27 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-27 | 2025-10-12 | 2025-10-31 | Jwala Singh 1 | 37.9311 | 1.8966 | TA413 | 10/1 | Completed
2025-10-27 | 2025-10-23 | 2025-10-30 | Jwala Singh 2 | 35.6018 | 4.4502 | TA413 | 27/5 | Completed
2025-10-27 | 2025-10-20 | 2025-10-29 | Kartik Mahto | 55.4509 | 5.5451 | TA413 | 21/0 | Completed
2025-10-27 | 2025-10-18 | 2025-10-28 | Pritam Enterprises 1 | 37.9311 | 3.4483 | TA413 | 9/11 | Completed
2025-10-27 | 2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-10-27 | 2025-10-27 | 2025-11-15 | Pritam Enterprises 4 | 37.1383 | 1.8569 | TA413 | 27/4 | Completed
2025-10-27 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-27 | 2025-10-16 | 2025-10-27 | Punam Kumari 1 | 87.0213 | 7.2518 | TA413 | 19/0 | Completed
2025-10-27 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-10-28 | 2025-10-28 | 2025-11-13 | Bhairaw Mahto | 96.8799 | 5.6988 | TA413 | 22/0 | Completed
2025-10-28 | 2025-10-24 | 2025-10-29 | Govind Mahto 1 | 36.1598 | 6.0266 | TA413 | 21/1 | Completed
2025-10-28 | 2025-10-05 | 2025-10-30 | Govind Mahto 2 | 137.0461 | 5.271 | TA413 | 15/0 | Completed
2025-10-28 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-28 | 2025-10-12 | 2025-10-31 | Jwala Singh 1 | 37.9311 | 1.8966 | TA413 | 10/1 | Completed
2025-10-28 | 2025-10-23 | 2025-10-30 | Jwala Singh 2 | 35.6018 | 4.4502 | TA413 | 27/5 | Completed
2025-10-28 | 2025-10-20 | 2025-10-29 | Kartik Mahto | 55.4509 | 5.5451 | TA413 | 21/0 | Completed
2025-10-28 | 2025-10-18 | 2025-10-28 | Pritam Enterprises 1 | 37.9311 | 3.4483 | TA413 | 9/11 | Completed
2025-10-28 | 2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-10-28 | 2025-10-27 | 2025-11-15 | Pritam Enterprises 4 | 37.1383 | 1.8569 | TA413 | 27/4 | Completed
2025-10-28 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-28 | 2025-10-28 | 2025-10-31 | Punam Kumari 1 | 36.1598 | 9.0399 | TA413 | 20/5 | Completed
2025-10-28 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-10-29 | 2025-10-28 | 2025-11-13 | Bhairaw Mahto | 96.8799 | 5.6988 | TA413 | 22/0 | Completed
2025-10-29 | 2025-10-24 | 2025-10-29 | Govind Mahto 1 | 36.1598 | 6.0266 | TA413 | 21/1 | Completed
2025-10-29 | 2025-10-05 | 2025-10-30 | Govind Mahto 2 | 137.0461 | 5.271 | TA413 | 15/0 | Completed
2025-10-29 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-29 | 2025-10-12 | 2025-10-31 | Jwala Singh 1 | 37.9311 | 1.8966 | TA413 | 10/1 | Completed
2025-10-29 | 2025-10-23 | 2025-10-30 | Jwala Singh 2 | 35.6018 | 4.4502 | TA413 | 27/5 | Completed
2025-10-29 | 2025-10-20 | 2025-10-29 | Kartik Mahto | 55.4509 | 5.5451 | TA413 | 21/0 | Completed
2025-10-29 | 2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-10-29 | 2025-10-27 | 2025-11-15 | Pritam Enterprises 4 | 37.1383 | 1.8569 | TA413 | 27/4 | Completed
2025-10-29 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-29 | 2025-10-28 | 2025-10-31 | Punam Kumari 1 | 36.1598 | 9.0399 | TA413 | 20/5 | Completed
2025-10-29 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-10-30 | 2025-10-28 | 2025-11-13 | Bhairaw Mahto | 96.8799 | 5.6988 | TA413 | 22/0 | Completed
2025-10-30 | 2025-10-30 | 2025-11-05 | Govind Mahto 1 | 37.1383 | 5.3055 | TA413 | 20/3 | Completed
2025-10-30 | 2025-10-05 | 2025-10-30 | Govind Mahto 2 | 137.0461 | 5.271 | TA413 | 15/0 | Completed
2025-10-30 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-30 | 2025-10-12 | 2025-10-31 | Jwala Singh 1 | 37.9311 | 1.8966 | TA413 | 10/1 | Completed
2025-10-30 | 2025-10-23 | 2025-10-30 | Jwala Singh 2 | 35.6018 | 4.4502 | TA413 | 27/5 | Completed
2025-10-30 | 2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-10-30 | 2025-10-27 | 2025-11-15 | Pritam Enterprises 4 | 37.1383 | 1.8569 | TA413 | 27/4 | Completed
2025-10-30 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-30 | 2025-10-28 | 2025-10-31 | Punam Kumari 1 | 36.1598 | 9.0399 | TA413 | 20/5 | Completed
2025-10-30 | 2025-10-30 | 2025-11-20 | Punam Kumari 1 | 36.1598 | 1.6436 | TA413 | 21/4 | Completed
2025-10-30 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-10-31 | 2025-10-28 | 2025-11-13 | Bhairaw Mahto | 96.8799 | 5.6988 | TA413 | 22/0 | Completed
2025-10-31 | 2025-10-30 | 2025-11-05 | Govind Mahto 1 | 37.1383 | 5.3055 | TA413 | 20/3 | Completed
2025-10-31 | 2025-10-31 | 2025-11-05 | Govind Mahto 2 | 37.9311 | 6.3218 | TA413 | 9/10 | Completed
2025-10-31 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-31 | 2025-10-12 | 2025-10-31 | Jwala Singh 1 | 37.9311 | 1.8966 | TA413 | 10/1 | Completed
2025-10-31 | 2025-10-31 | 2025-11-12 | Jwala Singh 2 | 64.8843 | 4.9911 | TA413 | 28/0 | Completed
2025-10-31 | 2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-10-31 | 2025-10-27 | 2025-11-15 | Pritam Enterprises 4 | 37.1383 | 1.8569 | TA413 | 27/4 | Completed
2025-10-31 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-31 | 2025-10-28 | 2025-10-31 | Punam Kumari 1 | 36.1598 | 9.0399 | TA413 | 20/5 | Completed
2025-10-31 | 2025-10-30 | 2025-11-20 | Punam Kumari 1 | 36.1598 | 1.6436 | TA413 | 21/4 | Completed
2025-10-31 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-11-01 | 2025-10-28 | 2025-11-13 | Bhairaw Mahto | 96.8799 | 5.6988 | TA413 | 22/0 | Completed
2025-11-01 | 2025-10-30 | 2025-11-05 | Govind Mahto 1 | 37.1383 | 5.3055 | TA413 | 20/3 | Completed
2025-11-01 | 2025-10-31 | 2025-11-05 | Govind Mahto 2 | 37.9311 | 6.3218 | TA413 | 9/10 | Completed
2025-11-01 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-11-01 | 2025-10-31 | 2025-11-12 | Jwala Singh 2 | 64.8843 | 4.9911 | TA413 | 28/0 | Completed
2025-11-01 | 2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-11-01 | 2025-10-27 | 2025-11-15 | Pritam Enterprises 4 | 37.1383 | 1.8569 | TA413 | 27/4 | Completed
2025-11-01 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-11-01 | 2025-10-30 | 2025-11-20 | Punam Kumari 1 | 36.1598 | 1.6436 | TA413 | 21/4 | Completed
2025-11-01 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-11-02 | 2025-10-28 | 2025-11-13 | Bhairaw Mahto | 96.8799 | 5.6988 | TA413 | 22/0 | Completed
2025-11-02 | 2025-10-30 | 2025-11-05 | Govind Mahto 1 | 37.1383 | 5.3055 | TA413 | 20/3 | Completed
2025-11-02 | 2025-10-31 | 2025-11-05 | Govind Mahto 2 | 37.9311 | 6.3218 | TA413 | 9/10 | Completed
2025-11-02 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-11-02 | 2025-10-31 | 2025-11-12 | Jwala Singh 2 | 64.8843 | 4.9911 | TA413 | 28/0 | Completed
2025-11-02 | 2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-11-02 | 2025-10-27 | 2025-11-15 | Pritam Enterprises 4 | 37.1383 | 1.8569 | TA413 | 27/4 | Completed
2025-11-02 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-11-02 | 2025-10-30 | 2025-11-20 | Punam Kumari 1 | 36.1598 | 1.6436 | TA413 | 21/4 | Completed
2025-11-02 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-11-03 | 2025-10-28 | 2025-11-13 | Bhairaw Mahto | 96.8799 | 5.6988 | TA413 | 22/0 | Completed
2025-11-03 | 2025-10-30 | 2025-11-05 | Govind Mahto 1 | 37.1383 | 5.3055 | TA413 | 20/3 | Completed
2025-11-03 | 2025-10-31 | 2025-11-05 | Govind Mahto 2 | 37.9311 | 6.3218 | TA413 | 9/10 | Completed
2025-11-03 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-11-03 | 2025-10-31 | 2025-11-12 | Jwala Singh 2 | 64.8843 | 4.9911 | TA413 | 28/0 | Completed
2025-11-03 | 2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-11-03 | 2025-10-27 | 2025-11-15 | Pritam Enterprises 4 | 37.1383 | 1.8569 | TA413 | 27/4 | Completed
2025-11-03 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-11-03 | 2025-10-30 | 2025-11-20 | Punam Kumari 1 | 36.1598 | 1.6436 | TA413 | 21/4 | Completed
2025-11-03 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-11-04 | 2025-10-28 | 2025-11-13 | Bhairaw Mahto | 96.8799 | 5.6988 | TA413 | 22/0 | Completed
2025-11-04 | 2025-10-30 | 2025-11-05 | Govind Mahto 1 | 37.1383 | 5.3055 | TA413 | 20/3 | Completed
2025-11-04 | 2025-10-31 | 2025-11-05 | Govind Mahto 2 | 37.9311 | 6.3218 | TA413 | 9/10 | Completed
2025-11-04 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-11-04 | 2025-10-31 | 2025-11-12 | Jwala Singh 2 | 64.8843 | 4.9911 | TA413 | 28/0 | Completed
2025-11-04 | 2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-11-04 | 2025-10-27 | 2025-11-15 | Pritam Enterprises 4 | 37.1383 | 1.8569 | TA413 | 27/4 | Completed
2025-11-04 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-11-04 | 2025-10-30 | 2025-11-20 | Punam Kumari 1 | 36.1598 | 1.6436 | TA413 | 21/4 | Completed
2025-11-04 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-11-05 | 2025-10-28 | 2025-11-13 | Bhairaw Mahto | 96.8799 | 5.6988 | TA413 | 22/0 | Completed
2025-11-05 | 2025-10-30 | 2025-11-05 | Govind Mahto 1 | 37.1383 | 5.3055 | TA413 | 20/3 | Completed
2025-11-05 | 2025-10-31 | 2025-11-05 | Govind Mahto 2 | 37.9311 | 6.3218 | TA413 | 9/10 | Completed
2025-11-05 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-11-05 | 2025-10-31 | 2025-11-12 | Jwala Singh 2 | 64.8843 | 4.9911 | TA413 | 28/0 | Completed
2025-11-05 | 2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-11-05 | 2025-10-27 | 2025-11-15 | Pritam Enterprises 4 | 37.1383 | 1.8569 | TA413 | 27/4 | Completed
2025-11-05 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-11-05 | 2025-10-30 | 2025-11-20 | Punam Kumari 1 | 36.1598 | 1.6436 | TA413 | 21/4 | Completed
2025-11-05 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-11-06 | 2025-10-28 | 2025-11-13 | Bhairaw Mahto | 96.8799 | 5.6988 | TA413 | 22/0 | Completed
2025-11-06 | 2025-11-06 | 2025-11-13 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 21/2 | Completed
2025-11-06 | 2025-11-06 | 2025-11-12 | Govind Mahto 2 | 37.9311 | 5.4187 | TA413 | 9/9 | Completed
2025-11-06 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-11-06 | 2025-10-31 | 2025-11-12 | Jwala Singh 2 | 64.8843 | 4.9911 | TA413 | 28/0 | Completed
2025-11-06 | 2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-11-06 | 2025-10-27 | 2025-11-15 | Pritam Enterprises 4 | 37.1383 | 1.8569 | TA413 | 27/4 | Completed
2025-11-06 | 2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-11-06 | 2025-10-30 | 2025-11-20 | Punam Kumari 1 | 36.1598 | 1.6436 | TA413 | 21/4 | Completed
2025-11-06 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-11-07 | 2025-10-28 | 2025-11-13 | Bhairaw Mahto | 96.8799 | 5.6988 | TA413 | 22/0 | Completed
2025-11-07 | 2025-11-06 | 2025-11-13 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 21/2 | Completed
2025-11-07 | 2025-11-06 | 2025-11-12 | Govind Mahto 2 | 37.9311 | 5.4187 | TA413 | 9/9 | Completed
2025-11-07 | 2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-11-07 | 2025-10-31 | 2025-11-12 | Jwala Singh 2 | 64.8843 | 4.9911 | TA413 | 28/0 | Completed
2025-11-07 | 2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-11-07 | 2025-10-27 | 2025-11-15 | Pritam Enterprises 4 | 37.1383 | 1.8569 | TA413 | 27/4 | Completed
2025-11-07 | 2025-10-30 | 2025-11-20 | Punam Kumari 1 | 36.1598 | 1.6436 | TA413 | 21/4 | Completed
2025-11-07 | 2025-11-07 | 2025-11-12 | Punam Kumari 1 | 37.9311 | 6.3218 | TA413 | 21/5 | Completed
2025-11-07 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-11-08 | 2025-10-28 | 2025-11-13 | Bhairaw Mahto | 96.8799 | 5.6988 | TA413 | 22/0 | Completed
2025-11-08 | 2025-11-06 | 2025-11-13 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 21/2 | Completed
2025-11-08 | 2025-11-06 | 2025-11-12 | Govind Mahto 2 | 37.9311 | 5.4187 | TA413 | 9/9 | Completed
2025-11-08 | 2025-10-31 | 2025-11-12 | Jwala Singh 2 | 64.8843 | 4.9911 | TA413 | 28/0 | Completed
2025-11-08 | 2025-10-27 | 2025-11-15 | Pritam Enterprises 4 | 37.1383 | 1.8569 | TA413 | 27/4 | Completed
2025-11-08 | 2025-10-30 | 2025-11-20 | Punam Kumari 1 | 36.1598 | 1.6436 | TA413 | 21/4 | Completed
2025-11-08 | 2025-11-07 | 2025-11-12 | Punam Kumari 1 | 37.9311 | 6.3218 | TA413 | 21/5 | Completed
2025-11-09 | 2025-10-28 | 2025-11-13 | Bhairaw Mahto | 96.8799 | 5.6988 | TA413 | 22/0 | Completed
2025-11-09 | 2025-11-06 | 2025-11-13 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 21/2 | Completed
2025-11-09 | 2025-11-06 | 2025-11-12 | Govind Mahto 2 | 37.9311 | 5.4187 | TA413 | 9/9 | Completed
2025-11-09 | 2025-10-31 | 2025-11-12 | Jwala Singh 2 | 64.8843 | 4.9911 | TA413 | 28/0 | Completed
2025-11-09 | 2025-10-27 | 2025-11-15 | Pritam Enterprises 4 | 37.1383 | 1.8569 | TA413 | 27/4 | Completed
2025-11-09 | 2025-10-30 | 2025-11-20 | Punam Kumari 1 | 36.1598 | 1.6436 | TA413 | 21/4 | Completed
2025-11-09 | 2025-11-07 | 2025-11-12 | Punam Kumari 1 | 37.9311 | 6.3218 | TA413 | 21/5 | Completed
2025-11-10 | 2025-10-28 | 2025-11-13 | Bhairaw Mahto | 96.8799 | 5.6988 | TA413 | 22/0 | Completed
2025-11-10 | 2025-11-06 | 2025-11-13 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 21/2 | Completed
2025-11-10 | 2025-11-06 | 2025-11-12 | Govind Mahto 2 | 37.9311 | 5.4187 | TA413 | 9/9 | Completed
2025-11-10 | 2025-11-10 | 2025-11-15 | Jwala Singh 1 | 37.9311 | 6.3218 | TA413 | 15/7 | Completed
2025-11-10 | 2025-10-31 | 2025-11-12 | Jwala Singh 2 | 64.8843 | 4.9911 | TA413 | 28/0 | Completed
2025-11-10 | 2025-10-27 | 2025-11-15 | Pritam Enterprises 4 | 37.1383 | 1.8569 | TA413 | 27/4 | Completed
2025-11-10 | 2025-10-30 | 2025-11-20 | Punam Kumari 1 | 36.1598 | 1.6436 | TA413 | 21/4 | Completed
2025-11-10 | 2025-11-07 | 2025-11-12 | Punam Kumari 1 | 37.9311 | 6.3218 | TA413 | 21/5 | Completed
2025-11-11 | 2025-10-28 | 2025-11-13 | Bhairaw Mahto | 96.8799 | 5.6988 | TA413 | 22/0 | Completed
2025-11-11 | 2025-11-06 | 2025-11-13 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 21/2 | Completed
2025-11-11 | 2025-11-06 | 2025-11-12 | Govind Mahto 2 | 37.9311 | 5.4187 | TA413 | 9/9 | Completed
2025-11-11 | 2025-11-10 | 2025-11-15 | Jwala Singh 1 | 37.9311 | 6.3218 | TA413 | 15/7 | Completed
2025-11-11 | 2025-10-31 | 2025-11-12 | Jwala Singh 2 | 64.8843 | 4.9911 | TA413 | 28/0 | Completed
2025-11-11 | 2025-10-27 | 2025-11-15 | Pritam Enterprises 4 | 37.1383 | 1.8569 | TA413 | 27/4 | Completed
2025-11-11 | 2025-10-30 | 2025-11-20 | Punam Kumari 1 | 36.1598 | 1.6436 | TA413 | 21/4 | Completed
2025-11-11 | 2025-11-07 | 2025-11-12 | Punam Kumari 1 | 37.9311 | 6.3218 | TA413 | 21/5 | Completed
2025-11-12 | 2025-10-28 | 2025-11-13 | Bhairaw Mahto | 96.8799 | 5.6988 | TA413 | 22/0 | Completed
2025-11-12 | 2025-11-06 | 2025-11-13 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 21/2 | Completed
2025-11-12 | 2025-11-06 | 2025-11-12 | Govind Mahto 2 | 37.9311 | 5.4187 | TA413 | 9/9 | Completed
2025-11-12 | 2025-11-10 | 2025-11-15 | Jwala Singh 1 | 37.9311 | 6.3218 | TA413 | 15/7 | Completed
2025-11-12 | 2025-10-31 | 2025-11-12 | Jwala Singh 2 | 64.8843 | 4.9911 | TA413 | 28/0 | Completed
2025-11-12 | 2025-10-27 | 2025-11-15 | Pritam Enterprises 4 | 37.1383 | 1.8569 | TA413 | 27/4 | Completed
2025-11-12 | 2025-10-30 | 2025-11-20 | Punam Kumari 1 | 36.1598 | 1.6436 | TA413 | 21/4 | Completed
2025-11-12 | 2025-11-07 | 2025-11-12 | Punam Kumari 1 | 37.9311 | 6.3218 | TA413 | 21/5 | Completed
2025-11-13 | 2025-10-28 | 2025-11-13 | Bhairaw Mahto | 96.8799 | 5.6988 | TA413 | 22/0 | Completed
2025-11-13 | 2025-11-06 | 2025-11-13 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 21/2 | Completed
2025-11-13 | 2025-11-10 | 2025-11-15 | Jwala Singh 1 | 37.9311 | 6.3218 | TA413 | 15/7 | Completed
2025-11-13 | 2025-11-13 | 2025-11-20 | Jwala Singh 2 | 34.7898 | 4.3487 | TA413 | 27/6 | Completed
2025-11-13 | 2025-10-27 | 2025-11-15 | Pritam Enterprises 4 | 37.1383 | 1.8569 | TA413 | 27/4 | Completed
2025-11-13 | 2025-10-30 | 2025-11-20 | Punam Kumari 1 | 36.1598 | 1.6436 | TA413 | 21/4 | Completed
2025-11-14 | 2025-11-10 | 2025-11-15 | Jwala Singh 1 | 37.9311 | 6.3218 | TA413 | 15/7 | Completed
2025-11-14 | 2025-11-13 | 2025-11-20 | Jwala Singh 2 | 34.7898 | 4.3487 | TA413 | 27/6 | Completed
2025-11-14 | 2025-10-27 | 2025-11-15 | Pritam Enterprises 4 | 37.1383 | 1.8569 | TA413 | 27/4 | Completed
2025-11-14 | 2025-10-30 | 2025-11-20 | Punam Kumari 1 | 36.1598 | 1.6436 | TA413 | 21/4 | Completed
2025-11-15 | 2025-11-10 | 2025-11-15 | Jwala Singh 1 | 37.9311 | 6.3218 | TA413 | 15/7 | Completed
2025-11-15 | 2025-11-13 | 2025-11-20 | Jwala Singh 2 | 34.7898 | 4.3487 | TA413 | 27/6 | Completed
2025-11-15 | 2025-10-27 | 2025-11-15 | Pritam Enterprises 4 | 37.1383 | 1.8569 | TA413 | 27/4 | Completed
2025-11-15 | 2025-10-30 | 2025-11-20 | Punam Kumari 1 | 36.1598 | 1.6436 | TA413 | 21/4 | Completed
2025-11-16 | 2025-11-16 | 2025-11-21 | Jwala Singh 1 | 35.6018 | 5.9336 | TA413 | 15/10 | Completed
2025-11-16 | 2025-11-13 | 2025-11-20 | Jwala Singh 2 | 34.7898 | 4.3487 | TA413 | 27/6 | Completed
2025-11-16 | 2025-10-30 | 2025-11-20 | Punam Kumari 1 | 36.1598 | 1.6436 | TA413 | 21/4 | Completed
2025-11-17 | 2025-11-16 | 2025-11-21 | Jwala Singh 1 | 35.6018 | 5.9336 | TA413 | 15/10 | Completed
2025-11-17 | 2025-11-13 | 2025-11-20 | Jwala Singh 2 | 34.7898 | 4.3487 | TA413 | 27/6 | Completed
2025-11-17 | 2025-10-30 | 2025-11-20 | Punam Kumari 1 | 36.1598 | 1.6436 | TA413 | 21/4 | Completed
2025-11-18 | 2025-11-16 | 2025-11-21 | Jwala Singh 1 | 35.6018 | 5.9336 | TA413 | 15/10 | Completed
2025-11-18 | 2025-11-13 | 2025-11-20 | Jwala Singh 2 | 34.7898 | 4.3487 | TA413 | 27/6 | Completed
2025-11-18 | 2025-10-30 | 2025-11-20 | Punam Kumari 1 | 36.1598 | 1.6436 | TA413 | 21/4 | Completed
2025-11-19 | 2025-11-16 | 2025-11-21 | Jwala Singh 1 | 35.6018 | 5.9336 | TA413 | 15/10 | Completed
2025-11-19 | 2025-11-13 | 2025-11-20 | Jwala Singh 2 | 34.7898 | 4.3487 | TA413 | 27/6 | Completed
2025-11-19 | 2025-10-30 | 2025-11-20 | Punam Kumari 1 | 36.1598 | 1.6436 | TA413 | 21/4 | Completed
2025-11-20 | 2025-11-16 | 2025-11-21 | Jwala Singh 1 | 35.6018 | 5.9336 | TA413 | 15/10 | Completed
2025-11-20 | 2025-11-13 | 2025-11-20 | Jwala Singh 2 | 34.7898 | 4.3487 | TA413 | 27/6 | Completed
2025-11-20 | 2025-10-30 | 2025-11-20 | Punam Kumari 1 | 36.1598 | 1.6436 | TA413 | 21/4 | Completed
2025-11-21 | 2025-11-16 | 2025-11-21 | Jwala Singh 1 | 35.6018 | 5.9336 | TA413 | 15/10 | Completed
2024-09-01 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-02 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-03 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-04 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-05 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-06 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-07 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-08 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-09 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-10 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-11 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-12 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-13 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-14 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-15 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-16 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-16 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-16 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-17 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-17 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-18 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-18 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-19 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-19 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-20 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-20 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-21 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-21 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-22 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-22 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-23 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-23 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-24 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-24 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-25 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-25 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-26 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-26 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-27 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-27 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-28 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-28 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-29 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-29 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-30 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-10-01 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-01 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-10-02 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-03 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-03 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-04 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-04 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-05 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-05 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-06 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-06 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-07 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-07 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-08 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | COMPLETED
2024-10-08 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-09 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | COMPLETED
2024-10-09 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-10 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | COMPLETED
2024-10-10 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-11 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | COMPLETED
2024-10-11 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-12 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | COMPLETED
2024-10-12 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-13 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | COMPLETED
2024-10-13 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-14 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | COMPLETED
2024-10-14 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-15 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | COMPLETED
2024-10-15 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-15 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-16 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | COMPLETED
2024-10-16 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-17 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | COMPLETED
2024-10-17 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-18 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | COMPLETED
2024-10-18 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-19 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | COMPLETED
2024-10-19 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-20 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | COMPLETED
2024-10-20 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-21 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | COMPLETED
2024-10-21 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-22 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | COMPLETED
2024-10-22 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-23 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | COMPLETED
2024-10-23 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-24 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | COMPLETED
2024-10-24 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | COMPLETED
2024-10-24 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-24 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-25 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | COMPLETED
2024-10-25 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-26 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | COMPLETED
2024-10-26 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-27 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | COMPLETED
2024-10-27 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-28 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | COMPLETED
2024-10-28 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-29 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | COMPLETED
2024-10-29 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-30 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-31 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-11-01 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 20/12 | COMPLETED
2024-11-01 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-02 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 20/12 | COMPLETED
2024-11-02 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-03 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 20/12 | COMPLETED
2024-11-03 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-04 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 20/12 | COMPLETED
2024-11-04 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-05 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | COMPLETED
2024-11-05 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-06 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | COMPLETED
2024-11-06 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-07 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | COMPLETED
2024-11-07 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-08 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | COMPLETED
2024-11-08 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-09 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | COMPLETED
2024-11-09 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-10 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-10 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | COMPLETED
2024-11-10 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-10 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-10 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | COMPLETED
2024-11-10 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-10 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-11 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-11 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-11 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-11 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | COMPLETED
2024-11-11 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-11 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-12 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-12 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-12 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-12 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | COMPLETED
2024-11-12 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-12 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-13 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-13 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-13 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-13 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | COMPLETED
2024-11-13 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-13 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-14 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-14 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-14 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-14 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | COMPLETED
2024-11-14 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-14 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416 | 6/2 | COMPLETED
2024-11-14 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-15 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-15 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-15 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | COMPLETED
2024-11-15 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-15 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416 | 6/2 | COMPLETED
2024-11-15 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-16 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-16 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-16 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | COMPLETED
2024-11-16 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-16 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416 | 6/2 | COMPLETED
2024-11-16 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-17 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-17 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-17 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | COMPLETED
2024-11-17 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | COMPLETED
2024-11-17 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-17 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416 | 6/2 | COMPLETED
2024-11-17 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-18 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-18 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | COMPLETED
2024-11-18 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | COMPLETED
2024-11-18 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-18 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416 | 6/2 | COMPLETED
2024-11-18 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-19 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-19 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | COMPLETED
2024-11-19 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | COMPLETED
2024-11-19 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-19 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416 | 6/2 | COMPLETED
2024-11-19 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-20 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-20 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | COMPLETED
2024-11-20 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | COMPLETED
2024-11-20 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-20 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416 | 6/2 | COMPLETED
2024-11-20 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-21 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-21 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | COMPLETED
2024-11-21 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | COMPLETED
2024-11-21 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-21 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416 | 6/2 | COMPLETED
2024-11-21 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-22 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-22 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | COMPLETED
2024-11-22 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-22 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | COMPLETED
2024-11-22 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-22 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416 | 6/2 | COMPLETED
2024-11-22 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-23 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-23 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-23 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | COMPLETED
2024-11-23 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-23 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416 | 6/2 | COMPLETED
2024-11-23 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-24 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-24 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-24 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | COMPLETED
2024-11-24 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-24 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416 | 6/2 | COMPLETED
2024-11-24 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-25 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-25 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-25 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | COMPLETED
2024-11-25 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416 | 6/2 | COMPLETED
2024-11-25 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-26 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-26 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-26 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-11-26 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-27 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-27 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-27 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-11-28 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-28 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-28 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-11-28 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-11-28 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-11-29 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-29 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-11-29 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-11-29 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-11-29 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-11-29 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-11-30 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-11-30 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-11-30 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-11-30 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-11-30 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-11-30 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-12-01 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-01 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-12-01 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-12-01 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-12-01 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-01 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-12-01 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-12-02 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-02 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-12-02 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-12-02 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-12-02 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-02 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-12-02 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-12-03 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-03 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-12-03 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-12-03 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-12-03 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-03 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-12-03 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-12-04 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-04 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-12-04 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-12-04 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-04 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-12-04 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-12-05 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-05 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-12-05 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-12-05 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-05 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-12-05 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-12-06 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-06 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-06 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-12-06 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-06 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-06 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-06 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-07 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-07 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-07 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-07 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-07 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-07 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-08 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-08 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-08 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-08 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-08 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-08 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-09 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-09 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-09 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-09 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-09 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-09 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-10 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-10 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-10 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-10 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-10 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-10 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-10 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-11 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-11 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-11 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-11 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-11 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-11 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-12 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-12 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-12 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | COMPLETED
2024-12-12 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-12 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-12 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-12 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | COMPLETED
2024-12-12 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-13 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-13 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | COMPLETED
2024-12-13 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-13 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-13 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | COMPLETED
2024-12-13 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-13 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-14 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-14 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | COMPLETED
2024-12-14 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-14 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-14 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | COMPLETED
2024-12-14 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-15 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-15 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | COMPLETED
2024-12-15 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-15 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-15 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | COMPLETED
2024-12-15 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-16 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-16 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | COMPLETED
2024-12-16 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-16 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-16 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | COMPLETED
2024-12-16 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-17 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-17 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | COMPLETED
2024-12-17 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-17 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | COMPLETED
2024-12-17 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-18 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-18 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | COMPLETED
2024-12-18 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-18 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | COMPLETED
2024-12-18 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | COMPLETED
2024-12-18 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-19 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-19 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | COMPLETED
2024-12-19 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-19 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | COMPLETED
2024-12-19 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | COMPLETED
2024-12-19 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-20 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-20 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | COMPLETED
2024-12-20 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-20 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | COMPLETED
2024-12-20 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | COMPLETED
2024-12-20 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-21 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-21 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | COMPLETED
2024-12-21 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-21 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | COMPLETED
2024-12-21 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | COMPLETED
2024-12-21 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-22 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-22 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | COMPLETED
2024-12-22 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-22 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | COMPLETED
2024-12-22 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | COMPLETED
2024-12-22 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | COMPLETED
2024-12-23 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-23 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | COMPLETED
2024-12-23 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-23 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | COMPLETED
2024-12-23 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | COMPLETED
2024-12-24 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-24 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-24 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-24 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-24 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-24 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 4/7 | COMPLETED
2024-12-24 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | COMPLETED
2024-12-25 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-25 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-25 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-25 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-25 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-25 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 4/7 | COMPLETED
2024-12-25 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | COMPLETED
2024-12-26 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-26 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-26 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-26 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-26 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-26 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 4/7 | COMPLETED
2024-12-26 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | COMPLETED
2024-12-27 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-27 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-27 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-27 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-27 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-27 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 4/7 | COMPLETED
2024-12-27 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | COMPLETED
2024-12-28 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2024-12-28 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-28 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-28 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-28 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-28 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2024-12-28 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2024-12-29 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2024-12-29 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-29 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-29 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-29 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-29 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2024-12-29 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2024-12-30 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2024-12-30 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-30 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-30 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-30 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-30 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2024-12-30 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2024-12-31 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2024-12-31 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-31 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-31 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-31 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2024-12-31 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2024-12-31 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-01 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2025-01-01 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2025-01-01 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-01 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-01 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2025-01-01 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-02 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2025-01-02 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2025-01-02 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-02 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-02 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2025-01-02 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-03 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2025-01-03 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2025-01-03 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-03 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-03 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2025-01-03 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-03 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-04 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2025-01-04 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-04 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-04 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-04 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-04 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-05 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-05 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-05 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-05 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-05 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-06 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-06 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-06 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-06 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-06 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-07 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-07 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-07 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-07 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-07 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-07 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-07 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-08 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-08 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-08 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-08 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-08 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-08 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-08 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-09 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-09 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-09 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-09 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-09 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-09 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-09 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-10 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-10 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-10 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-10 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-10 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-10 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-10 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-10 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-11 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-11 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-11 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-11 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-11 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-11 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-11 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-11 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-12 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-12 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-12 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-12 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-12 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-12 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-12 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-13 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-13 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-13 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-13 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-13 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-13 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-13 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-14 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-14 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-14 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-14 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-14 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-14 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-14 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-15 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-15 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-15 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-15 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-15 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-15 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-15 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-15 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-16 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-16 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-16 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-16 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-16 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-16 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-16 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-16 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-16 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-17 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-17 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-17 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-17 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-17 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-17 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-17 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-17 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-17 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-17 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-18 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-18 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-18 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-18 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-18 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-18 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-18 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-19 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-19 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-19 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-19 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-19 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-19 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-19 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-20 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-20 | 2025-01-20 | 2025-01-25 | Asc Heights | 46.0492 | 7.6749 | TA416 | 31/6 | COMPLETED
2025-01-20 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-20 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-20 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-20 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-20 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-21 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-21 | 2025-01-20 | 2025-01-25 | Asc Heights | 46.0492 | 7.6749 | TA416 | 31/6 | COMPLETED
2025-01-21 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-21 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-21 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-21 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-21 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-21 | 2025-01-21 | 2025-01-25 | Pinky Dewi | 46.0492 | 9.2098 | TA416 | 12/4 | COMPLETED
2025-01-21 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-21 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-22 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-22 | 2025-01-20 | 2025-01-25 | Asc Heights | 46.0492 | 7.6749 | TA416 | 31/6 | COMPLETED
2025-01-22 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-22 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-22 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-22 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-22 | 2025-01-21 | 2025-01-25 | Pinky Dewi | 46.0492 | 9.2098 | TA416 | 12/4 | COMPLETED
2025-01-22 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-22 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-23 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-23 | 2025-01-20 | 2025-01-25 | Asc Heights | 46.0492 | 7.6749 | TA416 | 31/6 | COMPLETED
2025-01-23 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-23 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-23 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-23 | 2025-01-21 | 2025-01-25 | Pinky Dewi | 46.0492 | 9.2098 | TA416 | 12/4 | COMPLETED
2025-01-23 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-23 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-24 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-24 | 2025-01-20 | 2025-01-25 | Asc Heights | 46.0492 | 7.6749 | TA416 | 31/6 | COMPLETED
2025-01-24 | 2025-01-24 | 2025-01-29 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 17/5 | COMPLETED
2025-01-24 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-24 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-24 | 2025-01-21 | 2025-01-25 | Pinky Dewi | 46.0492 | 9.2098 | TA416 | 12/4 | COMPLETED
2025-01-24 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-24 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-25 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | COMPLETED
2025-01-25 | 2025-01-20 | 2025-01-25 | Asc Heights | 46.0492 | 7.6749 | TA416 | 31/6 | COMPLETED
2025-01-25 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-25 | 2025-01-24 | 2025-01-29 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 17/5 | COMPLETED
2025-01-25 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-25 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-25 | 2025-01-21 | 2025-01-25 | Pinky Dewi | 46.0492 | 9.2098 | TA416 | 12/4 | COMPLETED
2025-01-25 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-25 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-25 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-26 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | COMPLETED
2025-01-26 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-26 | 2025-01-24 | 2025-01-29 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 17/5 | COMPLETED
2025-01-26 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-26 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-26 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-26 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-26 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-27 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | COMPLETED
2025-01-27 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-27 | 2025-01-24 | 2025-01-29 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 17/5 | COMPLETED
2025-01-27 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-27 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-27 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-27 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-27 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-28 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | COMPLETED
2025-01-28 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-28 | 2025-01-24 | 2025-01-29 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 17/5 | COMPLETED
2025-01-28 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-28 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-28 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-28 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-01-28 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-29 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | COMPLETED
2025-01-29 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-29 | 2025-01-24 | 2025-01-29 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 17/5 | COMPLETED
2025-01-29 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-01-29 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-29 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-01-29 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-29 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-01-29 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-30 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | COMPLETED
2025-01-30 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-30 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-01-30 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-01-30 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-30 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-01-30 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-30 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-01-30 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-31 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-31 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-01-31 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-01-31 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-01-31 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-31 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-01-31 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-02-01 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-02-01 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-02-01 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-01 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-01 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-02-01 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-02-02 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | COMPLETED
2025-02-02 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-02-02 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-02-02 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-02 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-02 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-02 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-02-02 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-03 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | COMPLETED
2025-02-03 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-03 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-02-03 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-03 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-03 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-03 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-02-03 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-04 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | COMPLETED
2025-02-04 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-04 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-02-04 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-04 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-04 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-04 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-02-04 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-05 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | COMPLETED
2025-02-05 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-05 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-02-05 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-05 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-05 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-05 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-02-05 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-06 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | COMPLETED
2025-02-06 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-06 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-06 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-06 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-06 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-06 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-02-06 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-07 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | COMPLETED
2025-02-07 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-07 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-07 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-07 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-07 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-07 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-07 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-08 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-08 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-08 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-08 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-08 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-08 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-08 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-08 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-09 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-09 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-09 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-09 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-09 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-09 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-09 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-09 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-10 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-10 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-10 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-10 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-10 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-10 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-10 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-10 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-11 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-11 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-11 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-11 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-11 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-11 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-11 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-11 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-12 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-12 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-12 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-12 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-12 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-12 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-12 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-12 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-12 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-13 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-13 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-13 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-13 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-13 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-13 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-13 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-13 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-14 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-14 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-14 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-14 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-14 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-14 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-14 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-14 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-15 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-15 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-15 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-15 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-15 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-15 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-15 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-15 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-16 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.0492 | 7.6749 | TA416 | 35/7 | COMPLETED
2025-02-16 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-16 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-16 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-16 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-16 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | COMPLETED
2025-02-16 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-16 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-17 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.0492 | 7.6749 | TA416 | 35/7 | COMPLETED
2025-02-17 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-17 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-17 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-17 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-17 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | COMPLETED
2025-02-17 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-17 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-18 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.0492 | 7.6749 | TA416 | 35/7 | COMPLETED
2025-02-18 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-18 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-18 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-18 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-18 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | COMPLETED
2025-02-18 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-18 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-19 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.0492 | 7.6749 | TA416 | 35/7 | COMPLETED
2025-02-19 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-19 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-19 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-19 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-19 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-19 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | COMPLETED
2025-02-19 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-19 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-20 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.0492 | 7.6749 | TA416 | 35/7 | COMPLETED
2025-02-20 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-20 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-20 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-20 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-20 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-20 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-20 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | COMPLETED
2025-02-20 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 20/4 | COMPLETED
2025-02-20 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-21 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.0492 | 7.6749 | TA416 | 35/7 | COMPLETED
2025-02-21 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-21 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-21 | 2025-02-21 | 2025-02-25 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/7 | COMPLETED
2025-02-21 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-21 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-21 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | COMPLETED
2025-02-21 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 20/4 | COMPLETED
2025-02-21 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-22 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-22 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-22 | 2025-02-21 | 2025-02-25 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/7 | COMPLETED
2025-02-22 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-22 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-22 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-02-22 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 20/4 | COMPLETED
2025-02-22 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-23 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-23 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-23 | 2025-02-21 | 2025-02-25 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/7 | COMPLETED
2025-02-23 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-23 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-23 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-02-23 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 20/4 | COMPLETED
2025-02-24 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-24 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-24 | 2025-02-21 | 2025-02-25 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/7 | COMPLETED
2025-02-24 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-24 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-24 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-02-24 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 20/4 | COMPLETED
2025-02-25 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-25 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-25 | 2025-02-21 | 2025-02-25 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/7 | COMPLETED
2025-02-25 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-25 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-25 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-02-25 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 20/4 | COMPLETED
2025-02-26 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-26 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-26 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | COMPLETED
2025-02-26 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-26 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-02-27 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-27 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | COMPLETED
2025-02-27 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-27 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | COMPLETED
2025-02-27 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-27 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-02-27 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-02-28 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | COMPLETED
2025-02-28 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-28 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | COMPLETED
2025-02-28 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-02-28 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-02-28 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-03-01 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | COMPLETED
2025-03-01 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-01 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | COMPLETED
2025-03-01 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-01 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-01 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-01 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | COMPLETED
2025-03-01 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-01 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-02 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | COMPLETED
2025-03-02 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-02 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | COMPLETED
2025-03-02 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-02 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-02 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-02 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | COMPLETED
2025-03-02 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-02 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-03 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | COMPLETED
2025-03-03 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-03 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | COMPLETED
2025-03-03 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-03 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-03 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-03 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | COMPLETED
2025-03-03 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-03 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-04 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-04 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | COMPLETED
2025-03-04 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-04 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-04 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-04 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | COMPLETED
2025-03-04 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-04 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-05 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-05 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | COMPLETED
2025-03-05 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-05 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-05 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-05 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | COMPLETED
2025-03-05 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-05 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-06 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-06 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | COMPLETED
2025-03-06 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-06 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-06 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-06 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-06 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-07 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-07 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | COMPLETED
2025-03-07 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-07 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-07 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-07 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-07 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-08 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-08 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 33/4 | COMPLETED
2025-03-08 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-08 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-08 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-08 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | COMPLETED
2025-03-08 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-08 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-09 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-09 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 33/4 | COMPLETED
2025-03-09 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-09 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | COMPLETED
2025-03-09 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-09 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-10 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-10 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 33/4 | COMPLETED
2025-03-10 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-10 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-10 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | COMPLETED
2025-03-10 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-10 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-11 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-11 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 33/4 | COMPLETED
2025-03-11 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-11 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-11 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | COMPLETED
2025-03-11 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-11 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-12 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-12 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-12 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-12 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-12 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | COMPLETED
2025-03-12 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-13 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-13 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-13 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-13 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-13 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-13 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-14 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-14 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-14 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-14 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-14 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-15 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-15 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-15 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-15 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-15 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-16 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-16 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-16 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-16 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-16 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-16 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-16 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | COMPLETED
2025-03-17 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-17 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-17 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-17 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-17 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-17 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | COMPLETED
2025-03-18 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-18 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-18 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-18 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-18 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-18 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | COMPLETED
2025-03-19 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-19 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | COMPLETED
2025-03-19 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-19 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-19 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | COMPLETED
2025-03-20 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-20 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | COMPLETED
2025-03-20 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-20 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-20 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-20 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | COMPLETED
2025-03-21 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-21 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | COMPLETED
2025-03-21 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-21 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-21 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-21 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-21 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | COMPLETED
2025-03-22 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-22 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-22 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | COMPLETED
2025-03-22 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-22 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-22 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-22 | 2025-03-22 | 2025-03-26 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8B/1 | COMPLETED
2025-03-22 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-23 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-23 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-23 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | COMPLETED
2025-03-23 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-23 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-23 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-23 | 2025-03-22 | 2025-03-26 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8B/1 | COMPLETED
2025-03-23 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-24 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-24 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-24 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-24 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-24 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-24 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-24 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-24 | 2025-03-22 | 2025-03-26 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8B/1 | COMPLETED
2025-03-24 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-24 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-25 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-25 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-25 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-25 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-25 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-25 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-25 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-25 | 2025-03-22 | 2025-03-26 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8B/1 | COMPLETED
2025-03-25 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-25 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-26 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-26 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-26 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-26 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-26 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-26 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-26 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-26 | 2025-03-22 | 2025-03-26 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8B/1 | COMPLETED
2025-03-26 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-26 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-27 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-27 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-27 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-27 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-27 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-27 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-27 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-27 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-27 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-28 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-28 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-28 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-28 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-28 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-28 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-28 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-28 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-03-28 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-28 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-03-29 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-29 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-29 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-29 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-29 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-29 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-29 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-29 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-03-29 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-29 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-03-30 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-30 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-30 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-30 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-30 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-30 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-30 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-30 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-03-30 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-03-31 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-31 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-03-31 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-31 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-31 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-03-31 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-31 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-31 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-03-31 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-04-01 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-01 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-01 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-01 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-01 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-01 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-01 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-01 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-01 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-04-02 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-02 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-02 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-02 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-02 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-02 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-02 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-02 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-02 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-02 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-04-03 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-03 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-03 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-03 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-03 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-03 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-03 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-03 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-03 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-03 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-03 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-04-04 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-04 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-04 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-04 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-04 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-04 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-04 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-04 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-04 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-04 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-04 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-04-05 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-05 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-05 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-05 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-05 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-05 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-05 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-05 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-05 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-05 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-05 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-05 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-04-06 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-06 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-06 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-06 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-06 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-06 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-06 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-06 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-06 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-06 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-06 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-06 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-07 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-07 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-07 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-07 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-07 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-07 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-07 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-07 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-07 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-07 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-07 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-07 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-08 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-08 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-08 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-08 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-08 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-08 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-08 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-08 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-08 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-08 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-08 | 2025-04-08 | 2025-04-13 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 8B/2 | COMPLETED
2025-04-08 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-09 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-09 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-09 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-09 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-09 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-09 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-09 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-09 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-09 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-09 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-09 | 2025-04-08 | 2025-04-13 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 8B/2 | COMPLETED
2025-04-09 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-10 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-10 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-10 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-10 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-10 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-10 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-10 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-10 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-10 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-10 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-10 | 2025-04-08 | 2025-04-13 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 8B/2 | COMPLETED
2025-04-10 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-11 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-11 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-11 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-11 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-11 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-11 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-11 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-11 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-11 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-11 | 2025-04-08 | 2025-04-13 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 8B/2 | COMPLETED
2025-04-11 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-12 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-12 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-12 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-12 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-16 | Gagan Enterprise 2 | 42.3742 | 8.4748 | TA416 | 10/1 | COMPLETED
2025-04-12 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-12 | 2025-04-08 | 2025-04-13 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 8B/2 | COMPLETED
2025-04-12 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-13 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-13 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-13 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-16 | Gagan Enterprise 2 | 42.3742 | 8.4748 | TA416 | 10/1 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-13 | 2025-04-08 | 2025-04-13 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 8B/2 | COMPLETED
2025-04-13 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-14 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-14 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-14 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-16 | Gagan Enterprise 2 | 42.3742 | 8.4748 | TA416 | 10/1 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-14 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-14 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-15 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-15 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-16 | Gagan Enterprise 2 | 42.3742 | 8.4748 | TA416 | 10/1 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-15 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-15 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-15 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-16 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-16 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-16 | Gagan Enterprise 2 | 42.3742 | 8.4748 | TA416 | 10/1 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-16 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-16 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-16 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-17 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-17 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-17 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-17 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-17 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-17 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-17 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-17 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-17 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-17 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-17 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-17 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-18 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-18 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-18 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-18 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-18 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-18 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-18 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-18 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-18 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-18 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-18 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-19 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-19 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-19 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-19 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-19 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-19 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-19 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-19 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-19 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-19 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-19 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-20 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-20 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-20 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-20 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-20 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-20 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-20 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-20 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-20 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-20 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-20 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-21 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-21 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-21 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-21 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-21 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-21 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-21 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-21 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-21 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-21 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-21 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-22 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-22 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-22 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-22 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-22 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-22 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-22 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-22 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-22 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-22 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-22 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-23 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | COMPLETED
2025-04-23 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-23 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-23 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-23 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-23 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | COMPLETED
2025-04-23 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/12 | COMPLETED
2025-04-23 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-23 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-23 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-23 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-24 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | COMPLETED
2025-04-24 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-24 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-24 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-24 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-24 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | COMPLETED
2025-04-24 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/12 | COMPLETED
2025-04-24 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-24 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-24 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-25 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | COMPLETED
2025-04-25 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-25 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-25 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-25 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-25 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | COMPLETED
2025-04-25 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/12 | COMPLETED
2025-04-25 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-25 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-25 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-26 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | COMPLETED
2025-04-26 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-26 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-26 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416 | 52/4 | COMPLETED
2025-04-26 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-26 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | COMPLETED
2025-04-26 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/12 | COMPLETED
2025-04-26 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-26 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-26 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-27 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | COMPLETED
2025-04-27 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416 | 52/4 | COMPLETED
2025-04-27 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-27 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | COMPLETED
2025-04-27 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/11 | COMPLETED
2025-04-27 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-27 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-27 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-28 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | COMPLETED
2025-04-28 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416 | 52/4 | COMPLETED
2025-04-28 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-28 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | COMPLETED
2025-04-28 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/11 | COMPLETED
2025-04-28 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-28 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-28 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-29 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-04-29 | 2025-04-29 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 39/4 | COMPLETED
2025-04-29 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416 | 52/4 | COMPLETED
2025-04-29 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | COMPLETED
2025-04-29 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/11 | COMPLETED
2025-04-29 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-29 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-30 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-04-30 | 2025-04-29 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 39/4 | COMPLETED
2025-04-30 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-04-30 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-04-30 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | COMPLETED
2025-04-30 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/11 | COMPLETED
2025-04-30 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-04-30 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-30 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-30 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-01 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-05-01 | 2025-04-29 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 39/4 | COMPLETED
2025-05-01 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-05-01 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-05-01 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | COMPLETED
2025-05-01 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-05-01 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-01 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-02 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-05-02 | 2025-04-29 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 39/4 | COMPLETED
2025-05-02 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-05-02 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-05-02 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | COMPLETED
2025-05-02 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-05-02 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-02 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-03 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-05-03 | 2025-04-29 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 39/4 | COMPLETED
2025-05-03 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-05-03 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-05-03 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | COMPLETED
2025-05-03 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-05-03 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-03 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-04 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-05-04 | 2025-04-29 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 39/4 | COMPLETED
2025-05-04 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-05-04 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-05-04 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-05-04 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-04 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-04 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-04 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-05 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-05-05 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-05 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-05-05 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-05-05 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-05-05 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-05 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-05 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-05 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-05 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-06 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-06 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-05-06 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-05-06 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-05-06 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/8 | COMPLETED
2025-05-06 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-06 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-06 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-06 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-06 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-07 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-07 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-07 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | COMPLETED
2025-05-07 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-07 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-07 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/8 | COMPLETED
2025-05-07 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-07 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-07 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-07 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-07 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-08 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-08 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-08 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | COMPLETED
2025-05-08 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-08 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-08 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/8 | COMPLETED
2025-05-08 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-08 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-08 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-08 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-09 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-09 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-09 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | COMPLETED
2025-05-09 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-09 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-09 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/8 | COMPLETED
2025-05-09 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-09 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-09 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-09 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-10 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-10 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-10 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | COMPLETED
2025-05-10 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-10 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-10 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-10 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-10 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-10 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-10 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-11 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-11 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-11 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | COMPLETED
2025-05-11 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-11 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-11 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | COMPLETED
2025-05-11 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-11 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-11 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-11 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-11 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-12 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-12 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-12 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-12 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | COMPLETED
2025-05-12 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-12 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-12 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | COMPLETED
2025-05-12 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-12 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-12 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-12 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-12 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-13 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-13 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-13 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-13 | 2025-05-13 | 2025-05-17 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/9 | COMPLETED
2025-05-13 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-13 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-13 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | COMPLETED
2025-05-13 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-13 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-13 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-13 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-13 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-14 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | COMPLETED
2025-05-14 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-14 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-14 | 2025-05-13 | 2025-05-17 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/9 | COMPLETED
2025-05-14 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-14 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-14 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | COMPLETED
2025-05-14 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | COMPLETED
2025-05-14 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-14 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-14 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-14 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-14 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-15 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | COMPLETED
2025-05-15 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-15 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-15 | 2025-05-13 | 2025-05-17 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/9 | COMPLETED
2025-05-15 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-15 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | COMPLETED
2025-05-15 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | COMPLETED
2025-05-15 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-15 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-15 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-15 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-15 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-16 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | COMPLETED
2025-05-16 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-16 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-16 | 2025-05-13 | 2025-05-17 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/9 | COMPLETED
2025-05-16 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | COMPLETED
2025-05-16 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-16 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | COMPLETED
2025-05-16 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-16 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-16 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-16 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-16 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-16 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-17 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | COMPLETED
2025-05-17 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-17 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-17 | 2025-05-13 | 2025-05-17 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/9 | COMPLETED
2025-05-17 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | COMPLETED
2025-05-17 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-17 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | COMPLETED
2025-05-17 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-17 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-17 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-17 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-17 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-17 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-18 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | COMPLETED
2025-05-18 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-18 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-18 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | COMPLETED
2025-05-18 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-18 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | COMPLETED
2025-05-18 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-18 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-18 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-18 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-18 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-18 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-19 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | COMPLETED
2025-05-19 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-19 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-19 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | COMPLETED
2025-05-19 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-19 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | COMPLETED
2025-05-19 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-19 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-19 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-19 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-19 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-19 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-20 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | COMPLETED
2025-05-20 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-20 | 2025-05-20 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 8.4748 | TA416 | 38/10 | COMPLETED
2025-05-20 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | COMPLETED
2025-05-20 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-20 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | COMPLETED
2025-05-20 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-20 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-20 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-20 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-20 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-20 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-21 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | COMPLETED
2025-05-21 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-21 | 2025-05-20 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 8.4748 | TA416 | 38/10 | COMPLETED
2025-05-21 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | COMPLETED
2025-05-21 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | COMPLETED
2025-05-21 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-21 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-21 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-21 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-21 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-21 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-22 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | COMPLETED
2025-05-22 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-22 | 2025-05-20 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 8.4748 | TA416 | 38/10 | COMPLETED
2025-05-22 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | COMPLETED
2025-05-22 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | COMPLETED
2025-05-22 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-22 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-22 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-22 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-22 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-23 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | COMPLETED
2025-05-23 | 2025-05-20 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 8.4748 | TA416 | 38/10 | COMPLETED
2025-05-23 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | COMPLETED
2025-05-23 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | COMPLETED
2025-05-23 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-23 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-23 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-23 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | COMPLETED
2025-05-23 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-23 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-24 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | COMPLETED
2025-05-24 | 2025-05-20 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 8.4748 | TA416 | 38/10 | COMPLETED
2025-05-24 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | COMPLETED
2025-05-24 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | COMPLETED
2025-05-24 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-24 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-24 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-24 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | COMPLETED
2025-05-24 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-24 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-25 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-25 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | COMPLETED
2025-05-25 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-25 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-25 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-25 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-25 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | COMPLETED
2025-05-25 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-25 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-05-25 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-26 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-26 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | COMPLETED
2025-05-26 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-26 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-26 | 2025-05-26 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 7.0624 | TA416 | 12/8 | COMPLETED
2025-05-26 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-26 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | COMPLETED
2025-05-26 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-26 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-05-26 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-27 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-27 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | COMPLETED
2025-05-27 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-05-27 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-27 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-27 | 2025-05-26 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 7.0624 | TA416 | 12/8 | COMPLETED
2025-05-27 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-27 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | COMPLETED
2025-05-27 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-27 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-05-27 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-28 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-28 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 38/5 | COMPLETED
2025-05-28 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-05-28 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-28 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-28 | 2025-05-26 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 7.0624 | TA416 | 12/8 | COMPLETED
2025-05-28 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-28 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | COMPLETED
2025-05-28 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-05-28 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-28 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-05-29 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-29 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 38/5 | COMPLETED
2025-05-29 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-05-29 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-29 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-29 | 2025-05-26 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 7.0624 | TA416 | 12/8 | COMPLETED
2025-05-29 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-29 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-05-29 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-29 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-05-30 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-30 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 38/5 | COMPLETED
2025-05-30 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-05-30 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-30 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-30 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 56/5 | COMPLETED
2025-05-30 | 2025-05-26 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 7.0624 | TA416 | 12/8 | COMPLETED
2025-05-30 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-30 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-05-30 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-30 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-05-31 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-31 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 38/5 | COMPLETED
2025-05-31 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-05-31 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-31 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 56/5 | COMPLETED
2025-05-31 | 2025-05-26 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 7.0624 | TA416 | 12/8 | COMPLETED
2025-05-31 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-31 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-05-31 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-06-01 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 38/5 | COMPLETED
2025-06-01 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-01 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-01 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 56/5 | COMPLETED
2025-06-01 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-01 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-06-01 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-06-01 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-06-02 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-02 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 38/5 | COMPLETED
2025-06-02 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-02 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-02 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-02 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 56/5 | COMPLETED
2025-06-02 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-02 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-06-02 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-06-03 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-03 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-03 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-03 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-03 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 56/5 | COMPLETED
2025-06-03 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-03 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-06-03 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-06-04 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-04 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-04 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-04 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-04 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-04 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 56/5 | COMPLETED
2025-06-04 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-04 | 2025-06-04 | 2025-06-09 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 23/2 | COMPLETED
2025-06-04 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-06-04 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-05 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-05 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-05 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-05 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-05 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-05 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-05 | 2025-06-04 | 2025-06-09 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 23/2 | COMPLETED
2025-06-05 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-06 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-06 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-06 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-06 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-06 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-06 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-06 | 2025-06-04 | 2025-06-09 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 23/2 | COMPLETED
2025-06-06 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-07 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-07 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-07 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-07 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-07 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-07 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-07 | 2025-06-04 | 2025-06-09 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 23/2 | COMPLETED
2025-06-07 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-08 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-08 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-08 | 2025-06-08 | 2025-06-13 | Ananya Traders 2 | 43.7758 | 7.296 | TA416 | 50/1 | COMPLETED
2025-06-08 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-08 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-08 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-08 | 2025-06-04 | 2025-06-09 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 23/2 | COMPLETED
2025-06-08 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-09 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-09 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-09 | 2025-06-08 | 2025-06-13 | Ananya Traders 2 | 43.7758 | 7.296 | TA416 | 50/1 | COMPLETED
2025-06-09 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-09 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-09 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-09 | 2025-06-04 | 2025-06-09 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 23/2 | COMPLETED
2025-06-09 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-10 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-10 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-10 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-10 | 2025-06-08 | 2025-06-13 | Ananya Traders 2 | 43.7758 | 7.296 | TA416 | 50/1 | COMPLETED
2025-06-10 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-10 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-10 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-10 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-10 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-11 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-11 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-11 | 2025-06-08 | 2025-06-13 | Ananya Traders 2 | 43.7758 | 7.296 | TA416 | 50/1 | COMPLETED
2025-06-11 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-11 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-11 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-11 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-11 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-12 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-12 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-12 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-12 | 2025-06-08 | 2025-06-13 | Ananya Traders 2 | 43.7758 | 7.296 | TA416 | 50/1 | COMPLETED
2025-06-12 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-12 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-12 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-12 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-12 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-12 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-13 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-13 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-13 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-13 | 2025-06-08 | 2025-06-13 | Ananya Traders 2 | 43.7758 | 7.296 | TA416 | 50/1 | COMPLETED
2025-06-13 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-13 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-13 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-13 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-13 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-13 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-14 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-14 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-14 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-14 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-14 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-14 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-14 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-14 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-14 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-15 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-15 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-15 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-15 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-15 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-15 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-15 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-15 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-15 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-16 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-16 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-16 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-16 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-16 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-16 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-16 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-16 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-16 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-17 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-17 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-17 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-17 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-17 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-17 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-17 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-17 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-17 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-18 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-18 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-18 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-18 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-18 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-18 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-18 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-18 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-18 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-19 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-19 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-19 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-19 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-19 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-19 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-19 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-20 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-20 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-20 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-20 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-20 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-20 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-20 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-20 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-21 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-21 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-21 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-21 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-21 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-21 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-21 | 2025-06-21 | 2025-06-26 | Pinky Dewi | 46.0492 | 7.6749 | TA416 | 21/2 | COMPLETED
2025-06-21 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-22 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-22 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-22 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-22 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-22 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-22 | 2025-06-21 | 2025-06-26 | Pinky Dewi | 46.0492 | 7.6749 | TA416 | 21/2 | COMPLETED
2025-06-22 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-23 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-23 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-23 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-23 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-23 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-23 | 2025-06-21 | 2025-06-26 | Pinky Dewi | 46.0492 | 7.6749 | TA416 | 21/2 | COMPLETED
2025-06-23 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-24 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-24 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-24 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-24 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-24 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-24 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-24 | 2025-06-21 | 2025-06-26 | Pinky Dewi | 46.0492 | 7.6749 | TA416 | 21/2 | COMPLETED
2025-06-24 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-06-25 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-25 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-25 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-25 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-25 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-25 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-25 | 2025-06-21 | 2025-06-26 | Pinky Dewi | 46.0492 | 7.6749 | TA416 | 21/2 | COMPLETED
2025-06-25 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-06-26 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-26 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-26 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-26 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-26 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-26 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-26 | 2025-06-21 | 2025-06-26 | Pinky Dewi | 46.0492 | 7.6749 | TA416 | 21/2 | COMPLETED
2025-06-26 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-06-27 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-27 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-27 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-27 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-27 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-27 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-27 | 2025-06-27 | 2025-06-30 | Pinky Dewi | 42.3742 | 10.5936 | TA416 | 21/1 | COMPLETED
2025-06-27 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-06-28 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-06-28 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-28 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-28 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-28 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-28 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-28 | 2025-06-27 | 2025-06-30 | Pinky Dewi | 42.3742 | 10.5936 | TA416 | 21/1 | COMPLETED
2025-06-28 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-06-29 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-06-29 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-29 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-29 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-29 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-29 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-29 | 2025-06-27 | 2025-06-30 | Pinky Dewi | 42.3742 | 10.5936 | TA416 | 21/1 | COMPLETED
2025-06-29 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-06-30 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-06-30 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-30 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-30 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-30 | 2025-06-27 | 2025-06-30 | Pinky Dewi | 42.3742 | 10.5936 | TA416 | 21/1 | COMPLETED
2025-06-30 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-07-01 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-01 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-07-01 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-01 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-02 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-02 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-07-02 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-02 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-03 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-03 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-07-03 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-03 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-04 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-04 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-07-04 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-04 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-05 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-05 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-05 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-07-05 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-05 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-06 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-06 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-06 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-06 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-07 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-07 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-07 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-07 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-08 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-08 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-08 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-08 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-09 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-09 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-09 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-09 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-09 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-10 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-10 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-10 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-10 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-10 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-11 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-11 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-11 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-11 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-11 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-12 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-12 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-12 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-12 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-12 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-13 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-13 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-13 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-13 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-14 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-14 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-14 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-14 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-15 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-15 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-15 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-15 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-16 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-16 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-16 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-16 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-17 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-17 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-17 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-17 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-18 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-18 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-18 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-18 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-19 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-19 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-19 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-20 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-20 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-20 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-20 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-21 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-21 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-21 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-21 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-22 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-22 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-22 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-22 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-23 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-23 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-23 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-24 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-24 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-24 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-25 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-25 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-25 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-26 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-26 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-26 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-07-26 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-27 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-27 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-27 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-07-27 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-07-27 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-28 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-28 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-28 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-07-28 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-07-28 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-29 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-29 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-29 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-07-29 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-07-29 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-30 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-30 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-30 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-07-30 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-07-30 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-31 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-31 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-31 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-07-31 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-07-31 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-08-01 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-01 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-01 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-01 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-02 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-02 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-02 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-02 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-02 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-03 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-03 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-03 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-03 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-03 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-04 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-04 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-04 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-04 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-04 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-04 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-05 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-05 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-05 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-05 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-05 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-05 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-06 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-06 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-06 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-06 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-06 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-06 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-06 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-07 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-07 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-07 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-07 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-07 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-07 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-07 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-08 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-08 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-08 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-08 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-08 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-08 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-08 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-09 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-09 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-09 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-09 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-09 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-09 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-09 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-10 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-10 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-10 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-10 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-10 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-10 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-10 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-10 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-11 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-11 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-11 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-11 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-11 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-11 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-11 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-11 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-12 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-12 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-12 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-12 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-12 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-12 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-12 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-12 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-13 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-13 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-13 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-13 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-13 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-13 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-13 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-13 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-14 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-14 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-14 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-14 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-14 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-14 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-14 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-14 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-14 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-15 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-15 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-15 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-15 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-15 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-15 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-15 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-15 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-15 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-16 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-16 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-16 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-16 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-16 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-16 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-16 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-16 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-16 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-16 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-17 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-17 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-17 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-17 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-17 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-17 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-17 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-17 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-17 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-17 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-18 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-18 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-18 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-18 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-18 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-18 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-18 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-18 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-18 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-18 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-18 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-19 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-19 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-19 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-19 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-19 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-19 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-19 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-19 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-19 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-19 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-19 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-20 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-20 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-20 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-20 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-20 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-20 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-20 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-20 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-20 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-20 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-20 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-21 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-21 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-21 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-21 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-21 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-21 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-21 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-21 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-21 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-21 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-21 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-22 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-22 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-22 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-22 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-22 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-22 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-22 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-22 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-22 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-22 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-22 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-23 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-23 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-23 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-23 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-23 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-23 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-23 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-23 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-23 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-23 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-23 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-24 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-24 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-24 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-24 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-24 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-24 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-24 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-24 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-24 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-24 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-24 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-24 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-25 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-25 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-25 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-25 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-25 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-25 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-25 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-25 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-25 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-25 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-25 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-25 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-26 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-26 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-26 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-26 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-26 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-26 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-26 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-26 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-26 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-26 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-26 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-26 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-27 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-27 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-27 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-27 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-27 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-27 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-27 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-27 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-27 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-27 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-27 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-28 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-28 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-28 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-28 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-28 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-08-28 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-28 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-28 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-28 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-28 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-28 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-29 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-29 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-29 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-29 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-29 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-08-29 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-29 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-29 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-29 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-29 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-29 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-30 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-30 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-30 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-30 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-30 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-08-30 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-30 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-30 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-30 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-30 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-30 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-31 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-31 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-31 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-31 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-31 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-08-31 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-08-31 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-31 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-31 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-08-31 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-01 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-01 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-09-01 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-09-01 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-01 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-01 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-01 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-09-01 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-01 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-01 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-02 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-02 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-09-02 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-09-02 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-02 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-02 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-02 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-09-02 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-02 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-02 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-03 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-03 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-09-03 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-03 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-03 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-03 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-09-03 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-03 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-03 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-03 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-04 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-04 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-09-04 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-04 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-04 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-04 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-09-04 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-04 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-04 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-04 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-05 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-05 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-09-05 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-05 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-05 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-05 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-05 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-05 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-05 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-05 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-06 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-06 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-09-06 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-06 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-06 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-06 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-06 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-06 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-06 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-06 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-07 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-07 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-07 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-07 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-07 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-07 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-07 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-07 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-07 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-07 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-08 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-08 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-08 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-08 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-08 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-08 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-08 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-08 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-08 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-08 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-09 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-09 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-09 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-09 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-09 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-09 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-09 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-09 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-09 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-09 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-10 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-10 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-10 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-10 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-10 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-10 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-10 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-10 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-10 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-10 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-11 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-11 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-11 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-11 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-11 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-11 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-11 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-11 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-11 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-11 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-11 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-12 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-12 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-12 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-12 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-12 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-12 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-12 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-12 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-12 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-12 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-12 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-13 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-13 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-13 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-13 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-13 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-13 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-13 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-13 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-13 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-13 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-13 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-14 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-14 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-14 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-14 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-14 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-14 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-14 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-14 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-14 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-14 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-14 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-15 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-15 | 2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-15 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-15 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-15 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-15 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-15 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-15 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-15 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-15 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-15 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-15 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-16 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-16 | 2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-16 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-16 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-16 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-16 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-16 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-16 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-16 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-16 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-16 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-16 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-17 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-17 | 2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-17 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-17 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-17 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-17 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-17 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-17 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-17 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-17 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-17 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-17 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-18 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-18 | 2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-18 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-18 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-18 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-18 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-18 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-18 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-18 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-18 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-18 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-18 | 2025-09-18 | 2025-10-13 | Spotyfy | 53.3239 | 2.0509 | TA416 | 53A/1 | COMPLETED
2025-09-18 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-19 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-19 | 2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-19 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-19 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-19 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-19 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-19 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-19 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-19 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-19 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-19 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-19 | 2025-09-18 | 2025-10-13 | Spotyfy | 53.3239 | 2.0509 | TA416 | 53A/1 | COMPLETED
2025-09-19 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-20 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-20 | 2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-20 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-20 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-20 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-20 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-20 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-20 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-20 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-20 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-20 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-20 | 2025-09-18 | 2025-10-13 | Spotyfy | 53.3239 | 2.0509 | TA416 | 53A/1 | COMPLETED
2025-09-20 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-21 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-21 | 2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-21 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-21 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-21 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-21 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-21 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-21 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-21 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-21 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-21 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-21 | 2025-09-18 | 2025-10-13 | Spotyfy | 53.3239 | 2.0509 | TA416 | 53A/1 | COMPLETED
2025-09-21 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-22 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-22 | 2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-22 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-22 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-22 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-22 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-22 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-22 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-22 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-22 | 2025-09-22 | 2025-10-12 | Reeta Bharti | 101.692 | 4.8425 | TA416 | 27/0 | COMPLETED
2025-09-22 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-22 | 2025-09-18 | 2025-10-13 | Spotyfy | 53.3239 | 2.0509 | TA416 | 53A/1 | COMPLETED
2025-09-22 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-23 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-23 | 2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-23 | 2025-09-23 | 2025-10-14 | Ananya Trader | 143.4621 | 6.521 | TA416 | 42/0 | COMPLETED
2025-09-23 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-23 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-23 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-23 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-09-23 | 2025-09-22 | 2025-10-12 | Reeta Bharti | 101.692 | 4.8425 | TA416 | 27/0 | COMPLETED
2025-09-23 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-23 | 2025-09-18 | 2025-10-13 | Spotyfy | 53.3239 | 2.0509 | TA416 | 53A/1 | COMPLETED
2025-09-23 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-24 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-24 | 2025-09-23 | 2025-10-14 | Ananya Trader | 143.4621 | 6.521 | TA416 | 42/0 | COMPLETED
2025-09-24 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-24 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-24 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-09-24 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-24 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-09-24 | 2025-09-22 | 2025-10-12 | Reeta Bharti | 101.692 | 4.8425 | TA416 | 27/0 | COMPLETED
2025-09-24 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-24 | 2025-09-18 | 2025-10-13 | Spotyfy | 53.3239 | 2.0509 | TA416 | 53A/1 | COMPLETED
2025-09-24 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-25 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-09-25 | 2025-09-23 | 2025-10-14 | Ananya Trader | 143.4621 | 6.521 | TA416 | 42/0 | COMPLETED
2025-09-25 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-25 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-25 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-09-25 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-25 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-09-25 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-09-25 | 2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-09-25 | 2025-09-25 | 2025-10-14 | Punam Kumari 1 | 110.6958 | 5.5348 | TA416 | 50/0 | COMPLETED
2025-09-25 | 2025-09-22 | 2025-10-12 | Reeta Bharti | 101.692 | 4.8425 | TA416 | 27/0 | COMPLETED
2025-09-25 | 2025-09-18 | 2025-10-13 | Spotyfy | 53.3239 | 2.0509 | TA416 | 53A/1 | COMPLETED
2025-09-26 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-09-26 | 2025-09-23 | 2025-10-14 | Ananya Trader | 143.4621 | 6.521 | TA416 | 42/0 | COMPLETED
2025-09-26 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-26 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-09-26 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-26 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-09-26 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-09-26 | 2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-09-26 | 2025-09-25 | 2025-10-14 | Punam Kumari 1 | 110.6958 | 5.5348 | TA416 | 50/0 | COMPLETED
2025-09-26 | 2025-09-22 | 2025-10-12 | Reeta Bharti | 101.692 | 4.8425 | TA416 | 27/0 | COMPLETED
2025-09-26 | 2025-09-26 | 2025-10-14 | Sainik Trader | 73.4258 | 3.8645 | TA416 | 53/0 | COMPLETED
2025-09-26 | 2025-09-18 | 2025-10-13 | Spotyfy | 53.3239 | 2.0509 | TA416 | 53A/1 | COMPLETED
2025-09-27 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-09-27 | 2025-09-23 | 2025-10-14 | Ananya Trader | 143.4621 | 6.521 | TA416 | 42/0 | COMPLETED
2025-09-27 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-27 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-09-27 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-27 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-09-27 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-09-27 | 2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-09-27 | 2025-09-25 | 2025-10-14 | Punam Kumari 1 | 110.6958 | 5.5348 | TA416 | 50/0 | COMPLETED
2025-09-27 | 2025-09-22 | 2025-10-12 | Reeta Bharti | 101.692 | 4.8425 | TA416 | 27/0 | COMPLETED
2025-09-27 | 2025-09-26 | 2025-10-14 | Sainik Trader | 73.4258 | 3.8645 | TA416 | 53/0 | COMPLETED
2025-09-27 | 2025-09-18 | 2025-10-13 | Spotyfy | 53.3239 | 2.0509 | TA416 | 53A/1 | COMPLETED
2025-09-28 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-09-28 | 2025-09-23 | 2025-10-14 | Ananya Trader | 143.4621 | 6.521 | TA416 | 42/0 | COMPLETED
2025-09-28 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-28 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-09-28 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-28 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-09-28 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-09-28 | 2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-09-28 | 2025-09-25 | 2025-10-14 | Punam Kumari 1 | 110.6958 | 5.5348 | TA416 | 50/0 | COMPLETED
2025-09-28 | 2025-09-22 | 2025-10-12 | Reeta Bharti | 101.692 | 4.8425 | TA416 | 27/0 | COMPLETED
2025-09-28 | 2025-09-26 | 2025-10-14 | Sainik Trader | 73.4258 | 3.8645 | TA416 | 53/0 | COMPLETED
2025-09-28 | 2025-09-18 | 2025-10-13 | Spotyfy | 53.3239 | 2.0509 | TA416 | 53A/1 | COMPLETED
2025-09-29 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-09-29 | 2025-09-23 | 2025-10-14 | Ananya Trader | 143.4621 | 6.521 | TA416 | 42/0 | COMPLETED
2025-09-29 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-29 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-09-29 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-09-29 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-09-29 | 2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-09-29 | 2025-09-25 | 2025-10-14 | Punam Kumari 1 | 110.6958 | 5.5348 | TA416 | 50/0 | COMPLETED
2025-09-29 | 2025-09-22 | 2025-10-12 | Reeta Bharti | 101.692 | 4.8425 | TA416 | 27/0 | COMPLETED
2025-09-29 | 2025-09-26 | 2025-10-14 | Sainik Trader | 73.4258 | 3.8645 | TA416 | 53/0 | COMPLETED
2025-09-29 | 2025-09-18 | 2025-10-13 | Spotyfy | 53.3239 | 2.0509 | TA416 | 53A/1 | COMPLETED
2025-09-30 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-09-30 | 2025-09-23 | 2025-10-14 | Ananya Trader | 143.4621 | 6.521 | TA416 | 42/0 | COMPLETED
2025-09-30 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-09-30 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-09-30 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-09-30 | 2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-09-30 | 2025-09-25 | 2025-10-14 | Punam Kumari 1 | 110.6958 | 5.5348 | TA416 | 50/0 | COMPLETED
2025-09-30 | 2025-09-22 | 2025-10-12 | Reeta Bharti | 101.692 | 4.8425 | TA416 | 27/0 | COMPLETED
2025-09-30 | 2025-09-26 | 2025-10-14 | Sainik Trader | 73.4258 | 3.8645 | TA416 | 53/0 | COMPLETED
2025-09-30 | 2025-09-18 | 2025-10-13 | Spotyfy | 53.3239 | 2.0509 | TA416 | 53A/1 | COMPLETED
2025-10-01 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-10-01 | 2025-09-23 | 2025-10-14 | Ananya Trader | 143.4621 | 6.521 | TA416 | 42/0 | COMPLETED
2025-10-01 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-10-01 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-01 | 2025-10-01 | 2025-10-12 | Mahon Mahto | 78.0732 | 6.5061 | TA416 | 63/0 | COMPLETED
2025-10-01 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-01 | 2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-10-01 | 2025-09-25 | 2025-10-14 | Punam Kumari 1 | 110.6958 | 5.5348 | TA416 | 50/0 | COMPLETED
2025-10-01 | 2025-09-22 | 2025-10-12 | Reeta Bharti | 101.692 | 4.8425 | TA416 | 27/0 | COMPLETED
2025-10-01 | 2025-09-26 | 2025-10-14 | Sainik Trader | 73.4258 | 3.8645 | TA416 | 53/0 | COMPLETED
2025-10-01 | 2025-09-18 | 2025-10-13 | Spotyfy | 53.3239 | 2.0509 | TA416 | 53A/1 | COMPLETED
2025-10-02 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-10-02 | 2025-09-23 | 2025-10-14 | Ananya Trader | 143.4621 | 6.521 | TA416 | 42/0 | COMPLETED
2025-10-02 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-10-02 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-02 | 2025-10-01 | 2025-10-12 | Mahon Mahto | 78.0732 | 6.5061 | TA416 | 63/0 | COMPLETED
2025-10-02 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-02 | 2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-10-02 | 2025-09-25 | 2025-10-14 | Punam Kumari 1 | 110.6958 | 5.5348 | TA416 | 50/0 | COMPLETED
2025-10-02 | 2025-09-22 | 2025-10-12 | Reeta Bharti | 101.692 | 4.8425 | TA416 | 27/0 | COMPLETED
2025-10-02 | 2025-09-26 | 2025-10-14 | Sainik Trader | 73.4258 | 3.8645 | TA416 | 53/0 | COMPLETED
2025-10-02 | 2025-09-18 | 2025-10-13 | Spotyfy | 53.3239 | 2.0509 | TA416 | 53A/1 | COMPLETED
2025-10-03 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-10-03 | 2025-09-23 | 2025-10-14 | Ananya Trader | 143.4621 | 6.521 | TA416 | 42/0 | COMPLETED
2025-10-03 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-10-03 | 2025-10-03 | 2025-10-28 | Maa Construction | 97.834 | 3.7628 | TA416 | 0/0 | COMPLETED
2025-10-03 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-03 | 2025-10-01 | 2025-10-12 | Mahon Mahto | 78.0732 | 6.5061 | TA416 | 63/0 | COMPLETED
2025-10-03 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-03 | 2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-10-03 | 2025-09-25 | 2025-10-14 | Punam Kumari 1 | 110.6958 | 5.5348 | TA416 | 50/0 | COMPLETED
2025-10-03 | 2025-09-22 | 2025-10-12 | Reeta Bharti | 101.692 | 4.8425 | TA416 | 27/0 | COMPLETED
2025-10-03 | 2025-09-26 | 2025-10-14 | Sainik Trader | 73.4258 | 3.8645 | TA416 | 53/0 | COMPLETED
2025-10-03 | 2025-09-18 | 2025-10-13 | Spotyfy | 53.3239 | 2.0509 | TA416 | 53A/1 | COMPLETED
2025-10-04 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-10-04 | 2025-09-23 | 2025-10-14 | Ananya Trader | 143.4621 | 6.521 | TA416 | 42/0 | COMPLETED
2025-10-04 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-10-04 | 2025-10-03 | 2025-10-28 | Maa Construction | 97.834 | 3.7628 | TA416 | 0/0 | COMPLETED
2025-10-04 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-04 | 2025-10-01 | 2025-10-12 | Mahon Mahto | 78.0732 | 6.5061 | TA416 | 63/0 | COMPLETED
2025-10-04 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-04 | 2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-10-04 | 2025-09-25 | 2025-10-14 | Punam Kumari 1 | 110.6958 | 5.5348 | TA416 | 50/0 | COMPLETED
2025-10-04 | 2025-09-22 | 2025-10-12 | Reeta Bharti | 101.692 | 4.8425 | TA416 | 27/0 | COMPLETED
2025-10-04 | 2025-09-26 | 2025-10-14 | Sainik Trader | 73.4258 | 3.8645 | TA416 | 53/0 | COMPLETED
2025-10-04 | 2025-09-18 | 2025-10-13 | Spotyfy | 53.3239 | 2.0509 | TA416 | 53A/1 | COMPLETED
2025-10-05 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-10-05 | 2025-09-23 | 2025-10-14 | Ananya Trader | 143.4621 | 6.521 | TA416 | 42/0 | COMPLETED
2025-10-05 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-10-05 | 2025-10-03 | 2025-10-28 | Maa Construction | 97.834 | 3.7628 | TA416 | 0/0 | COMPLETED
2025-10-05 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-05 | 2025-10-01 | 2025-10-12 | Mahon Mahto | 78.0732 | 6.5061 | TA416 | 63/0 | COMPLETED
2025-10-05 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-05 | 2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-10-05 | 2025-09-25 | 2025-10-14 | Punam Kumari 1 | 110.6958 | 5.5348 | TA416 | 50/0 | COMPLETED
2025-10-05 | 2025-09-22 | 2025-10-12 | Reeta Bharti | 101.692 | 4.8425 | TA416 | 27/0 | COMPLETED
2025-10-05 | 2025-09-26 | 2025-10-14 | Sainik Trader | 73.4258 | 3.8645 | TA416 | 53/0 | COMPLETED
2025-10-05 | 2025-09-18 | 2025-10-13 | Spotyfy | 53.3239 | 2.0509 | TA416 | 53A/1 | COMPLETED
2025-10-06 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-10-06 | 2025-09-23 | 2025-10-14 | Ananya Trader | 143.4621 | 6.521 | TA416 | 42/0 | COMPLETED
2025-10-06 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-10-06 | 2025-10-03 | 2025-10-28 | Maa Construction | 97.834 | 3.7628 | TA416 | 0/0 | COMPLETED
2025-10-06 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-06 | 2025-10-01 | 2025-10-12 | Mahon Mahto | 78.0732 | 6.5061 | TA416 | 63/0 | COMPLETED
2025-10-06 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-06 | 2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-10-06 | 2025-09-25 | 2025-10-14 | Punam Kumari 1 | 110.6958 | 5.5348 | TA416 | 50/0 | COMPLETED
2025-10-06 | 2025-09-22 | 2025-10-12 | Reeta Bharti | 101.692 | 4.8425 | TA416 | 27/0 | COMPLETED
2025-10-06 | 2025-09-26 | 2025-10-14 | Sainik Trader | 73.4258 | 3.8645 | TA416 | 53/0 | COMPLETED
2025-10-06 | 2025-09-18 | 2025-10-13 | Spotyfy | 53.3239 | 2.0509 | TA416 | 53A/1 | COMPLETED
2025-10-07 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-10-07 | 2025-09-23 | 2025-10-14 | Ananya Trader | 143.4621 | 6.521 | TA416 | 42/0 | COMPLETED
2025-10-07 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-10-07 | 2025-10-03 | 2025-10-28 | Maa Construction | 97.834 | 3.7628 | TA416 | 0/0 | COMPLETED
2025-10-07 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-07 | 2025-10-01 | 2025-10-12 | Mahon Mahto | 78.0732 | 6.5061 | TA416 | 63/0 | COMPLETED
2025-10-07 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-07 | 2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-10-07 | 2025-09-25 | 2025-10-14 | Punam Kumari 1 | 110.6958 | 5.5348 | TA416 | 50/0 | COMPLETED
2025-10-07 | 2025-09-22 | 2025-10-12 | Reeta Bharti | 101.692 | 4.8425 | TA416 | 27/0 | COMPLETED
2025-10-07 | 2025-09-26 | 2025-10-14 | Sainik Trader | 73.4258 | 3.8645 | TA416 | 53/0 | COMPLETED
2025-10-07 | 2025-09-18 | 2025-10-13 | Spotyfy | 53.3239 | 2.0509 | TA416 | 53A/1 | COMPLETED
2025-10-08 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-10-08 | 2025-09-23 | 2025-10-14 | Ananya Trader | 143.4621 | 6.521 | TA416 | 42/0 | COMPLETED
2025-10-08 | 2025-10-03 | 2025-10-28 | Maa Construction | 97.834 | 3.7628 | TA416 | 0/0 | COMPLETED
2025-10-08 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-08 | 2025-10-01 | 2025-10-12 | Mahon Mahto | 78.0732 | 6.5061 | TA416 | 63/0 | COMPLETED
2025-10-08 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-08 | 2025-10-08 | 2025-10-26 | Pankaj Kumar | 110.6958 | 5.8261 | TA416 | 38/0 | COMPLETED
2025-10-08 | 2025-09-25 | 2025-10-14 | Punam Kumari 1 | 110.6958 | 5.5348 | TA416 | 50/0 | COMPLETED
2025-10-08 | 2025-10-08 | 2025-10-22 | Punam Kumari 2 | 42.3742 | 2.8249 | TA416 | 54/2 | COMPLETED
2025-10-08 | 2025-09-22 | 2025-10-12 | Reeta Bharti | 101.692 | 4.8425 | TA416 | 27/0 | COMPLETED
2025-10-08 | 2025-09-26 | 2025-10-14 | Sainik Trader | 73.4258 | 3.8645 | TA416 | 53/0 | COMPLETED
2025-10-08 | 2025-09-18 | 2025-10-13 | Spotyfy | 53.3239 | 2.0509 | TA416 | 53A/1 | COMPLETED
2025-10-09 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-10-09 | 2025-09-23 | 2025-10-14 | Ananya Trader | 143.4621 | 6.521 | TA416 | 42/0 | COMPLETED
2025-10-09 | 2025-10-03 | 2025-10-28 | Maa Construction | 97.834 | 3.7628 | TA416 | 0/0 | COMPLETED
2025-10-09 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-09 | 2025-10-01 | 2025-10-12 | Mahon Mahto | 78.0732 | 6.5061 | TA416 | 63/0 | COMPLETED
2025-10-09 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-09 | 2025-10-08 | 2025-10-26 | Pankaj Kumar | 110.6958 | 5.8261 | TA416 | 38/0 | COMPLETED
2025-10-09 | 2025-09-25 | 2025-10-14 | Punam Kumari 1 | 110.6958 | 5.5348 | TA416 | 50/0 | COMPLETED
2025-10-09 | 2025-10-08 | 2025-10-22 | Punam Kumari 2 | 42.3742 | 2.8249 | TA416 | 54/2 | COMPLETED
2025-10-09 | 2025-09-22 | 2025-10-12 | Reeta Bharti | 101.692 | 4.8425 | TA416 | 27/0 | COMPLETED
2025-10-09 | 2025-09-26 | 2025-10-14 | Sainik Trader | 73.4258 | 3.8645 | TA416 | 53/0 | COMPLETED
2025-10-09 | 2025-09-18 | 2025-10-13 | Spotyfy | 53.3239 | 2.0509 | TA416 | 53A/1 | COMPLETED
2025-10-10 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-10-10 | 2025-09-23 | 2025-10-14 | Ananya Trader | 143.4621 | 6.521 | TA416 | 42/0 | COMPLETED
2025-10-10 | 2025-10-03 | 2025-10-28 | Maa Construction | 97.834 | 3.7628 | TA416 | 0/0 | COMPLETED
2025-10-10 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-10 | 2025-10-01 | 2025-10-12 | Mahon Mahto | 78.0732 | 6.5061 | TA416 | 63/0 | COMPLETED
2025-10-10 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-10 | 2025-10-08 | 2025-10-26 | Pankaj Kumar | 110.6958 | 5.8261 | TA416 | 38/0 | COMPLETED
2025-10-10 | 2025-09-25 | 2025-10-14 | Punam Kumari 1 | 110.6958 | 5.5348 | TA416 | 50/0 | COMPLETED
2025-10-10 | 2025-10-08 | 2025-10-22 | Punam Kumari 2 | 42.3742 | 2.8249 | TA416 | 54/2 | COMPLETED
2025-10-10 | 2025-09-22 | 2025-10-12 | Reeta Bharti | 101.692 | 4.8425 | TA416 | 27/0 | COMPLETED
2025-10-10 | 2025-09-26 | 2025-10-14 | Sainik Trader | 73.4258 | 3.8645 | TA416 | 53/0 | COMPLETED
2025-10-10 | 2025-09-18 | 2025-10-13 | Spotyfy | 53.3239 | 2.0509 | TA416 | 53A/1 | COMPLETED
2025-10-11 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-10-11 | 2025-09-23 | 2025-10-14 | Ananya Trader | 143.4621 | 6.521 | TA416 | 42/0 | COMPLETED
2025-10-11 | 2025-10-03 | 2025-10-28 | Maa Construction | 97.834 | 3.7628 | TA416 | 0/0 | COMPLETED
2025-10-11 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-11 | 2025-10-01 | 2025-10-12 | Mahon Mahto | 78.0732 | 6.5061 | TA416 | 63/0 | COMPLETED
2025-10-11 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-11 | 2025-10-08 | 2025-10-26 | Pankaj Kumar | 110.6958 | 5.8261 | TA416 | 38/0 | COMPLETED
2025-10-11 | 2025-09-25 | 2025-10-14 | Punam Kumari 1 | 110.6958 | 5.5348 | TA416 | 50/0 | COMPLETED
2025-10-11 | 2025-10-08 | 2025-10-22 | Punam Kumari 2 | 42.3742 | 2.8249 | TA416 | 54/2 | COMPLETED
2025-10-11 | 2025-09-22 | 2025-10-12 | Reeta Bharti | 101.692 | 4.8425 | TA416 | 27/0 | COMPLETED
2025-10-11 | 2025-09-26 | 2025-10-14 | Sainik Trader | 73.4258 | 3.8645 | TA416 | 53/0 | COMPLETED
2025-10-11 | 2025-09-18 | 2025-10-13 | Spotyfy | 53.3239 | 2.0509 | TA416 | 53A/1 | COMPLETED
2025-10-12 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-10-12 | 2025-09-23 | 2025-10-14 | Ananya Trader | 143.4621 | 6.521 | TA416 | 42/0 | COMPLETED
2025-10-12 | 2025-10-03 | 2025-10-28 | Maa Construction | 97.834 | 3.7628 | TA416 | 0/0 | COMPLETED
2025-10-12 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-12 | 2025-10-01 | 2025-10-12 | Mahon Mahto | 78.0732 | 6.5061 | TA416 | 63/0 | COMPLETED
2025-10-12 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-12 | 2025-10-08 | 2025-10-26 | Pankaj Kumar | 110.6958 | 5.8261 | TA416 | 38/0 | COMPLETED
2025-10-12 | 2025-09-25 | 2025-10-14 | Punam Kumari 1 | 110.6958 | 5.5348 | TA416 | 50/0 | COMPLETED
2025-10-12 | 2025-10-08 | 2025-10-22 | Punam Kumari 2 | 42.3742 | 2.8249 | TA416 | 54/2 | COMPLETED
2025-10-12 | 2025-09-22 | 2025-10-12 | Reeta Bharti | 101.692 | 4.8425 | TA416 | 27/0 | COMPLETED
2025-10-12 | 2025-09-26 | 2025-10-14 | Sainik Trader | 73.4258 | 3.8645 | TA416 | 53/0 | COMPLETED
2025-10-12 | 2025-09-18 | 2025-10-13 | Spotyfy | 53.3239 | 2.0509 | TA416 | 53A/1 | COMPLETED
2025-10-13 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-10-13 | 2025-09-23 | 2025-10-14 | Ananya Trader | 143.4621 | 6.521 | TA416 | 42/0 | COMPLETED
2025-10-13 | 2025-10-03 | 2025-10-28 | Maa Construction | 97.834 | 3.7628 | TA416 | 0/0 | COMPLETED
2025-10-13 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-13 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-13 | 2025-10-08 | 2025-10-26 | Pankaj Kumar | 110.6958 | 5.8261 | TA416 | 38/0 | COMPLETED
2025-10-13 | 2025-09-25 | 2025-10-14 | Punam Kumari 1 | 110.6958 | 5.5348 | TA416 | 50/0 | COMPLETED
2025-10-13 | 2025-10-08 | 2025-10-22 | Punam Kumari 2 | 42.3742 | 2.8249 | TA416 | 54/2 | COMPLETED
2025-10-13 | 2025-09-26 | 2025-10-14 | Sainik Trader | 73.4258 | 3.8645 | TA416 | 53/0 | COMPLETED
2025-10-13 | 2025-09-18 | 2025-10-13 | Spotyfy | 53.3239 | 2.0509 | TA416 | 53A/1 | COMPLETED
2025-10-14 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-10-14 | 2025-09-23 | 2025-10-14 | Ananya Trader | 143.4621 | 6.521 | TA416 | 42/0 | COMPLETED
2025-10-14 | 2025-10-03 | 2025-10-28 | Maa Construction | 97.834 | 3.7628 | TA416 | 0/0 | COMPLETED
2025-10-14 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-14 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-14 | 2025-10-08 | 2025-10-26 | Pankaj Kumar | 110.6958 | 5.8261 | TA416 | 38/0 | COMPLETED
2025-10-14 | 2025-09-25 | 2025-10-14 | Punam Kumari 1 | 110.6958 | 5.5348 | TA416 | 50/0 | COMPLETED
2025-10-14 | 2025-10-08 | 2025-10-22 | Punam Kumari 2 | 42.3742 | 2.8249 | TA416 | 54/2 | COMPLETED
2025-10-14 | 2025-09-26 | 2025-10-14 | Sainik Trader | 73.4258 | 3.8645 | TA416 | 53/0 | COMPLETED
2025-10-15 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-10-15 | 2025-10-03 | 2025-10-28 | Maa Construction | 97.834 | 3.7628 | TA416 | 0/0 | COMPLETED
2025-10-15 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-15 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-15 | 2025-10-08 | 2025-10-26 | Pankaj Kumar | 110.6958 | 5.8261 | TA416 | 38/0 | COMPLETED
2025-10-15 | 2025-10-08 | 2025-10-22 | Punam Kumari 2 | 42.3742 | 2.8249 | TA416 | 54/2 | COMPLETED
2025-10-15 | 2025-10-15 | 2025-11-07 | Punam Kumari 2 | 73.4258 | 3.0594 | TA416 | 55/0 | COMPLETED
2025-10-16 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-10-16 | 2025-10-03 | 2025-10-28 | Maa Construction | 97.834 | 3.7628 | TA416 | 0/0 | COMPLETED
2025-10-16 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-16 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-16 | 2025-10-08 | 2025-10-26 | Pankaj Kumar | 110.6958 | 5.8261 | TA416 | 38/0 | COMPLETED
2025-10-16 | 2025-10-08 | 2025-10-22 | Punam Kumari 2 | 42.3742 | 2.8249 | TA416 | 54/2 | COMPLETED
2025-10-16 | 2025-10-15 | 2025-11-07 | Punam Kumari 2 | 73.4258 | 3.0594 | TA416 | 55/0 | COMPLETED
2025-10-17 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-10-17 | 2025-10-03 | 2025-10-28 | Maa Construction | 97.834 | 3.7628 | TA416 | 0/0 | COMPLETED
2025-10-17 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-17 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-17 | 2025-10-08 | 2025-10-26 | Pankaj Kumar | 110.6958 | 5.8261 | TA416 | 38/0 | COMPLETED
2025-10-17 | 2025-10-08 | 2025-10-22 | Punam Kumari 2 | 42.3742 | 2.8249 | TA416 | 54/2 | COMPLETED
2025-10-17 | 2025-10-15 | 2025-11-07 | Punam Kumari 2 | 73.4258 | 3.0594 | TA416 | 55/0 | COMPLETED
2025-10-18 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-10-18 | 2025-10-03 | 2025-10-28 | Maa Construction | 97.834 | 3.7628 | TA416 | 0/0 | COMPLETED
2025-10-18 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-18 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-18 | 2025-10-08 | 2025-10-26 | Pankaj Kumar | 110.6958 | 5.8261 | TA416 | 38/0 | COMPLETED
2025-10-18 | 2025-10-08 | 2025-10-22 | Punam Kumari 2 | 42.3742 | 2.8249 | TA416 | 54/2 | COMPLETED
2025-10-18 | 2025-10-15 | 2025-11-07 | Punam Kumari 2 | 73.4258 | 3.0594 | TA416 | 55/0 | COMPLETED
2025-10-19 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-10-19 | 2025-10-03 | 2025-10-28 | Maa Construction | 97.834 | 3.7628 | TA416 | 0/0 | COMPLETED
2025-10-19 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-19 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-19 | 2025-10-08 | 2025-10-26 | Pankaj Kumar | 110.6958 | 5.8261 | TA416 | 38/0 | COMPLETED
2025-10-19 | 2025-10-08 | 2025-10-22 | Punam Kumari 2 | 42.3742 | 2.8249 | TA416 | 54/2 | COMPLETED
2025-10-19 | 2025-10-15 | 2025-11-07 | Punam Kumari 2 | 73.4258 | 3.0594 | TA416 | 55/0 | COMPLETED
2025-10-20 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-10-20 | 2025-10-03 | 2025-10-28 | Maa Construction | 97.834 | 3.7628 | TA416 | 0/0 | COMPLETED
2025-10-20 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-20 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-20 | 2025-10-08 | 2025-10-26 | Pankaj Kumar | 110.6958 | 5.8261 | TA416 | 38/0 | COMPLETED
2025-10-20 | 2025-10-08 | 2025-10-22 | Punam Kumari 2 | 42.3742 | 2.8249 | TA416 | 54/2 | COMPLETED
2025-10-20 | 2025-10-15 | 2025-11-07 | Punam Kumari 2 | 73.4258 | 3.0594 | TA416 | 55/0 | COMPLETED
2025-10-21 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-10-21 | 2025-10-03 | 2025-10-28 | Maa Construction | 97.834 | 3.7628 | TA416 | 0/0 | COMPLETED
2025-10-21 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-21 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-21 | 2025-10-08 | 2025-10-26 | Pankaj Kumar | 110.6958 | 5.8261 | TA416 | 38/0 | COMPLETED
2025-10-21 | 2025-10-08 | 2025-10-22 | Punam Kumari 2 | 42.3742 | 2.8249 | TA416 | 54/2 | COMPLETED
2025-10-21 | 2025-10-15 | 2025-11-07 | Punam Kumari 2 | 73.4258 | 3.0594 | TA416 | 55/0 | COMPLETED
2025-10-22 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-10-22 | 2025-10-03 | 2025-10-28 | Maa Construction | 97.834 | 3.7628 | TA416 | 0/0 | COMPLETED
2025-10-22 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-22 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-22 | 2025-10-08 | 2025-10-26 | Pankaj Kumar | 110.6958 | 5.8261 | TA416 | 38/0 | COMPLETED
2025-10-22 | 2025-10-08 | 2025-10-22 | Punam Kumari 2 | 42.3742 | 2.8249 | TA416 | 54/2 | COMPLETED
2025-10-22 | 2025-10-15 | 2025-11-07 | Punam Kumari 2 | 73.4258 | 3.0594 | TA416 | 55/0 | COMPLETED
2025-10-23 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-10-23 | 2025-10-03 | 2025-10-28 | Maa Construction | 97.834 | 3.7628 | TA416 | 0/0 | COMPLETED
2025-10-23 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-23 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-23 | 2025-10-08 | 2025-10-26 | Pankaj Kumar | 110.6958 | 5.8261 | TA416 | 38/0 | COMPLETED
2025-10-23 | 2025-10-15 | 2025-11-07 | Punam Kumari 2 | 73.4258 | 3.0594 | TA416 | 55/0 | COMPLETED
2025-10-24 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-10-24 | 2025-10-03 | 2025-10-28 | Maa Construction | 97.834 | 3.7628 | TA416 | 0/0 | COMPLETED
2025-10-24 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-24 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-24 | 2025-10-08 | 2025-10-26 | Pankaj Kumar | 110.6958 | 5.8261 | TA416 | 38/0 | COMPLETED
2025-10-24 | 2025-10-15 | 2025-11-07 | Punam Kumari 2 | 73.4258 | 3.0594 | TA416 | 55/0 | COMPLETED
2025-10-25 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-10-25 | 2025-10-03 | 2025-10-28 | Maa Construction | 97.834 | 3.7628 | TA416 | 0/0 | COMPLETED
2025-10-25 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-25 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-25 | 2025-10-08 | 2025-10-26 | Pankaj Kumar | 110.6958 | 5.8261 | TA416 | 38/0 | COMPLETED
2025-10-25 | 2025-10-15 | 2025-11-07 | Punam Kumari 2 | 73.4258 | 3.0594 | TA416 | 55/0 | COMPLETED
2025-10-26 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-10-26 | 2025-10-03 | 2025-10-28 | Maa Construction | 97.834 | 3.7628 | TA416 | 0/0 | COMPLETED
2025-10-26 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-26 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-26 | 2025-10-08 | 2025-10-26 | Pankaj Kumar | 110.6958 | 5.8261 | TA416 | 38/0 | COMPLETED
2025-10-26 | 2025-10-15 | 2025-11-07 | Punam Kumari 2 | 73.4258 | 3.0594 | TA416 | 55/0 | COMPLETED
2025-10-27 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-10-27 | 2025-10-03 | 2025-10-28 | Maa Construction | 97.834 | 3.7628 | TA416 | 0/0 | COMPLETED
2025-10-27 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-27 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-27 | 2025-10-27 | 2025-11-10 | Pankaj Kumar | 75.858 | 5.0572 | TA416 | 52/1 | COMPLETED
2025-10-27 | 2025-10-15 | 2025-11-07 | Punam Kumari 2 | 73.4258 | 3.0594 | TA416 | 55/0 | COMPLETED
2025-10-28 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-10-28 | 2025-10-03 | 2025-10-28 | Maa Construction | 97.834 | 3.7628 | TA416 | 0/0 | COMPLETED
2025-10-28 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-28 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-28 | 2025-10-27 | 2025-11-10 | Pankaj Kumar | 75.858 | 5.0572 | TA416 | 52/1 | COMPLETED
2025-10-28 | 2025-10-15 | 2025-11-07 | Punam Kumari 2 | 73.4258 | 3.0594 | TA416 | 55/0 | COMPLETED
2025-10-29 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-10-29 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-29 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-29 | 2025-10-27 | 2025-11-10 | Pankaj Kumar | 75.858 | 5.0572 | TA416 | 52/1 | COMPLETED
2025-10-29 | 2025-10-15 | 2025-11-07 | Punam Kumari 2 | 73.4258 | 3.0594 | TA416 | 55/0 | COMPLETED
2025-10-30 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-10-30 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-30 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-30 | 2025-10-27 | 2025-11-10 | Pankaj Kumar | 75.858 | 5.0572 | TA416 | 52/1 | COMPLETED
2025-10-30 | 2025-10-15 | 2025-11-07 | Punam Kumari 2 | 73.4258 | 3.0594 | TA416 | 55/0 | COMPLETED
2025-10-31 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-10-31 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-10-31 | 2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-31 | 2025-10-27 | 2025-11-10 | Pankaj Kumar | 75.858 | 5.0572 | TA416 | 52/1 | COMPLETED
2025-10-31 | 2025-10-15 | 2025-11-07 | Punam Kumari 2 | 73.4258 | 3.0594 | TA416 | 55/0 | COMPLETED
2025-11-01 | 2025-11-01 | 2025-11-13 | Aloriva Global | 43.776 | 3.3674 | TA416 | 2/2 | COMPLETED
2025-11-01 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-11-01 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-11-01 | 2025-10-27 | 2025-11-10 | Pankaj Kumar | 75.858 | 5.0572 | TA416 | 52/1 | COMPLETED
2025-11-01 | 2025-11-01 | 2025-11-15 | Pinky Dewi | 43.776 | 2.9184 | TA416 | 56/6 | COMPLETED
2025-11-01 | 2025-10-15 | 2025-11-07 | Punam Kumari 2 | 73.4258 | 3.0594 | TA416 | 55/0 | COMPLETED
2025-11-02 | 2025-11-01 | 2025-11-13 | Aloriva Global | 43.776 | 3.3674 | TA416 | 2/2 | COMPLETED
2025-11-02 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-11-02 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-11-02 | 2025-10-27 | 2025-11-10 | Pankaj Kumar | 75.858 | 5.0572 | TA416 | 52/1 | COMPLETED
2025-11-02 | 2025-11-01 | 2025-11-15 | Pinky Dewi | 43.776 | 2.9184 | TA416 | 56/6 | COMPLETED
2025-11-02 | 2025-10-15 | 2025-11-07 | Punam Kumari 2 | 73.4258 | 3.0594 | TA416 | 55/0 | COMPLETED
2025-11-03 | 2025-11-01 | 2025-11-13 | Aloriva Global | 43.776 | 3.3674 | TA416 | 2/2 | COMPLETED
2025-11-03 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-11-03 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-11-03 | 2025-10-27 | 2025-11-10 | Pankaj Kumar | 75.858 | 5.0572 | TA416 | 52/1 | COMPLETED
2025-11-03 | 2025-11-01 | 2025-11-15 | Pinky Dewi | 43.776 | 2.9184 | TA416 | 56/6 | COMPLETED
2025-11-03 | 2025-10-15 | 2025-11-07 | Punam Kumari 2 | 73.4258 | 3.0594 | TA416 | 55/0 | COMPLETED
2025-11-04 | 2025-11-01 | 2025-11-13 | Aloriva Global | 43.776 | 3.3674 | TA416 | 2/2 | COMPLETED
2025-11-04 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-11-04 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-11-04 | 2025-10-27 | 2025-11-10 | Pankaj Kumar | 75.858 | 5.0572 | TA416 | 52/1 | COMPLETED
2025-11-04 | 2025-11-01 | 2025-11-15 | Pinky Dewi | 43.776 | 2.9184 | TA416 | 56/6 | COMPLETED
2025-11-04 | 2025-10-15 | 2025-11-07 | Punam Kumari 2 | 73.4258 | 3.0594 | TA416 | 55/0 | COMPLETED
2025-11-05 | 2025-11-01 | 2025-11-13 | Aloriva Global | 43.776 | 3.3674 | TA416 | 2/2 | COMPLETED
2025-11-05 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-11-05 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-11-05 | 2025-10-27 | 2025-11-10 | Pankaj Kumar | 75.858 | 5.0572 | TA416 | 52/1 | COMPLETED
2025-11-05 | 2025-11-01 | 2025-11-15 | Pinky Dewi | 43.776 | 2.9184 | TA416 | 56/6 | COMPLETED
2025-11-05 | 2025-10-15 | 2025-11-07 | Punam Kumari 2 | 73.4258 | 3.0594 | TA416 | 55/0 | COMPLETED
2025-11-06 | 2025-11-01 | 2025-11-13 | Aloriva Global | 43.776 | 3.3674 | TA416 | 2/2 | COMPLETED
2025-11-06 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-11-06 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-11-06 | 2025-10-27 | 2025-11-10 | Pankaj Kumar | 75.858 | 5.0572 | TA416 | 52/1 | COMPLETED
2025-11-06 | 2025-11-01 | 2025-11-15 | Pinky Dewi | 43.776 | 2.9184 | TA416 | 56/6 | COMPLETED
2025-11-06 | 2025-10-15 | 2025-11-07 | Punam Kumari 2 | 73.4258 | 3.0594 | TA416 | 55/0 | COMPLETED
2025-11-07 | 2025-11-01 | 2025-11-13 | Aloriva Global | 43.776 | 3.3674 | TA416 | 2/2 | COMPLETED
2025-11-07 | 2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-11-07 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-11-07 | 2025-10-27 | 2025-11-10 | Pankaj Kumar | 75.858 | 5.0572 | TA416 | 52/1 | COMPLETED
2025-11-07 | 2025-11-01 | 2025-11-15 | Pinky Dewi | 43.776 | 2.9184 | TA416 | 56/6 | COMPLETED
2025-11-07 | 2025-10-15 | 2025-11-07 | Punam Kumari 2 | 73.4258 | 3.0594 | TA416 | 55/0 | COMPLETED
2025-11-08 | 2025-11-01 | 2025-11-13 | Aloriva Global | 43.776 | 3.3674 | TA416 | 2/2 | COMPLETED
2025-11-08 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-11-08 | 2025-10-27 | 2025-11-10 | Pankaj Kumar | 75.858 | 5.0572 | TA416 | 52/1 | COMPLETED
2025-11-08 | 2025-11-01 | 2025-11-15 | Pinky Dewi | 43.776 | 2.9184 | TA416 | 56/6 | COMPLETED
2025-11-09 | 2025-11-01 | 2025-11-13 | Aloriva Global | 43.776 | 3.3674 | TA416 | 2/2 | COMPLETED
2025-11-09 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-11-09 | 2025-10-27 | 2025-11-10 | Pankaj Kumar | 75.858 | 5.0572 | TA416 | 52/1 | COMPLETED
2025-11-09 | 2025-11-01 | 2025-11-15 | Pinky Dewi | 43.776 | 2.9184 | TA416 | 56/6 | COMPLETED
2025-11-09 | 2025-11-09 | 2025-11-17 | Punam Kumari 2 | 42.3742 | 4.7082 | TA416 | 55/1 | COMPLETED
2025-11-10 | 2025-11-01 | 2025-11-13 | Aloriva Global | 43.776 | 3.3674 | TA416 | 2/2 | COMPLETED
2025-11-10 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-11-10 | 2025-10-27 | 2025-11-10 | Pankaj Kumar | 75.858 | 5.0572 | TA416 | 52/1 | COMPLETED
2025-11-10 | 2025-11-01 | 2025-11-15 | Pinky Dewi | 43.776 | 2.9184 | TA416 | 56/6 | COMPLETED
2025-11-10 | 2025-11-09 | 2025-11-17 | Punam Kumari 2 | 42.3742 | 4.7082 | TA416 | 55/1 | COMPLETED
2025-11-11 | 2025-11-01 | 2025-11-13 | Aloriva Global | 43.776 | 3.3674 | TA416 | 2/2 | COMPLETED
2025-11-11 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-11-11 | 2025-11-01 | 2025-11-15 | Pinky Dewi | 43.776 | 2.9184 | TA416 | 56/6 | COMPLETED
2025-11-11 | 2025-11-09 | 2025-11-17 | Punam Kumari 2 | 42.3742 | 4.7082 | TA416 | 55/1 | COMPLETED
2025-11-12 | 2025-11-01 | 2025-11-13 | Aloriva Global | 43.776 | 3.3674 | TA416 | 2/2 | COMPLETED
2025-11-12 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-11-12 | 2025-11-01 | 2025-11-15 | Pinky Dewi | 43.776 | 2.9184 | TA416 | 56/6 | COMPLETED
2025-11-12 | 2025-11-09 | 2025-11-17 | Punam Kumari 2 | 42.3742 | 4.7082 | TA416 | 55/1 | COMPLETED
2025-11-13 | 2025-11-01 | 2025-11-13 | Aloriva Global | 43.776 | 3.3674 | TA416 | 2/2 | COMPLETED
2025-11-13 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-11-13 | 2025-11-01 | 2025-11-15 | Pinky Dewi | 43.776 | 2.9184 | TA416 | 56/6 | COMPLETED
2025-11-13 | 2025-11-09 | 2025-11-17 | Punam Kumari 2 | 42.3742 | 4.7082 | TA416 | 55/1 | COMPLETED
2025-11-14 | 2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-11-14 | 2025-11-01 | 2025-11-15 | Pinky Dewi | 43.776 | 2.9184 | TA416 | 56/6 | COMPLETED
2025-11-14 | 2025-11-09 | 2025-11-17 | Punam Kumari 2 | 42.3742 | 4.7082 | TA416 | 55/1 | COMPLETED
2025-11-15 | 2025-11-01 | 2025-11-15 | Pinky Dewi | 43.776 | 2.9184 | TA416 | 56/6 | COMPLETED
2025-11-15 | 2025-11-09 | 2025-11-17 | Punam Kumari 2 | 42.3742 | 4.7082 | TA416 | 55/1 | COMPLETED
2025-11-16 | 2025-11-09 | 2025-11-17 | Punam Kumari 2 | 42.3742 | 4.7082 | TA416 | 55/1 | COMPLETED
2025-11-17 | 2025-11-09 | 2025-11-17 | Punam Kumari 2 | 42.3742 | 4.7082 | TA416 | 55/1 | COMPLETED
2024-01-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-09 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-10 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-11 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-12 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-13 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-14 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-15 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-16 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-17 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-18 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-19 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-20 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-21 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-22 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-23 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-24 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-25 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-26 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-27 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-28 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 33/12 | COMPLETED
2024-10-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-29 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 33/12 | COMPLETED
2024-10-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-30 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 33/12 | COMPLETED
2024-10-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-31 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 33/12 | COMPLETED
2024-10-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-01 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 33/12 | COMPLETED
2024-11-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-02 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 33/12 | COMPLETED
2024-11-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-03 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 33/12 | COMPLETED
2024-11-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-04 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 33/12 | COMPLETED
2024-11-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-05 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 33/12 | COMPLETED
2024-11-05 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 35/06 | COMPLETED
2024-11-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-06 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 35/06 | COMPLETED
2024-11-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-07 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 35/06 | COMPLETED
2024-11-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-08 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 35/06 | COMPLETED
2024-11-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-09 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 35/06 | COMPLETED
2024-11-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-10 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 35/06 | COMPLETED
2024-11-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-11 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 35/06 | COMPLETED
2024-11-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-12 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 35/06 | COMPLETED
2024-11-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-13 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 35/06 | COMPLETED
2024-11-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-14 | 2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 34/3 | COMPLETED
2024-11-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-15 | 2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 34/3 | COMPLETED
2024-11-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-16 | 2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 34/3 | COMPLETED
2024-11-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-17 | 2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 34/3 | COMPLETED
2024-11-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-18 | 2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 34/3 | COMPLETED
2024-11-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-19 | 2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 34/3 | COMPLETED
2024-11-19 | 2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 35/4 | COMPLETED
2024-11-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-20 | 2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 35/4 | COMPLETED
2024-11-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-21 | 2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 35/4 | COMPLETED
2024-11-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-22 | 2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 35/4 | COMPLETED
2024-11-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-23 | 2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 35/4 | COMPLETED
2024-11-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-24 | 2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 35/4 | COMPLETED
2024-11-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-26 | 2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 40/1 | COMPLETED
2024-11-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-27 | 2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 40/1 | COMPLETED
2024-11-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-28 | 2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 40/1 | COMPLETED
2024-11-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-29 | 2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 40/1 | COMPLETED
2024-11-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-30 | 2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 40/1 | COMPLETED
2024-11-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-01 | 2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 40/1 | COMPLETED
2024-12-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-02 | 2024-12-02 | 2024-12-06 | Gang 01 Sanjay | 27.96 | 5.592 | TA418 | 40/2 | COMPLETED
2024-12-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-03 | 2024-12-02 | 2024-12-06 | Gang 01 Sanjay | 27.96 | 5.592 | TA418 | 40/2 | COMPLETED
2024-12-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-03 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 42/2 | COMPLETED
2024-12-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-04 | 2024-12-02 | 2024-12-06 | Gang 01 Sanjay | 27.96 | 5.592 | TA418 | 40/2 | COMPLETED
2024-12-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-04 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 42/2 | COMPLETED
2024-12-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-05 | 2024-12-02 | 2024-12-06 | Gang 01 Sanjay | 27.96 | 5.592 | TA418 | 40/2 | COMPLETED
2024-12-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-05 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 42/2 | COMPLETED
2024-12-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-06 | 2024-12-02 | 2024-12-06 | Gang 01 Sanjay | 27.96 | 5.592 | TA418 | 40/2 | COMPLETED
2024-12-06 | 2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 41/3 | COMPLETED
2024-12-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-06 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 42/2 | COMPLETED
2024-12-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-07 | 2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 41/3 | COMPLETED
2024-12-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-07 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 42/2 | COMPLETED
2024-12-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-08 | 2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 41/3 | COMPLETED
2024-12-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-08 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 42/2 | COMPLETED
2024-12-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-09 | 2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 41/3 | COMPLETED
2024-12-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-09 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 42/2 | COMPLETED
2024-12-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-10 | 2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 41/3 | COMPLETED
2024-12-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-10 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 42/2 | COMPLETED
2024-12-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-11 | 2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 41/3 | COMPLETED
2024-12-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-11 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 42/2 | COMPLETED
2024-12-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-12 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | TA418 | 41/4 | COMPLETED
2024-12-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-12 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | TA418 | 42/1 | COMPLETED
2024-12-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-13 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | TA418 | 41/4 | COMPLETED
2024-12-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-13 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | TA418 | 42/1 | COMPLETED
2024-12-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-14 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | TA418 | 41/4 | COMPLETED
2024-12-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-14 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | TA418 | 42/1 | COMPLETED
2024-12-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-15 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | TA418 | 41/4 | COMPLETED
2024-12-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-15 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | TA418 | 42/1 | COMPLETED
2024-12-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-16 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | TA418 | 41/4 | COMPLETED
2024-12-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-16 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | TA418 | 42/1 | COMPLETED
2024-12-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-17 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | TA418 | 41/4 | COMPLETED
2024-12-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-17 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | TA418 | 42/1 | COMPLETED
2024-12-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-18 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | TA418 | 41/4 | COMPLETED
2024-12-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-18 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | TA418 | 42/1 | COMPLETED
2024-12-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-19 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418 | 35/11 | COMPLETED
2024-12-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-19 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418 | 35/7 | COMPLETED
2024-12-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-20 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418 | 35/11 | COMPLETED
2024-12-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-20 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418 | 35/7 | COMPLETED
2024-12-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-21 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418 | 35/11 | COMPLETED
2024-12-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-21 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418 | 35/7 | COMPLETED
2024-12-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-22 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418 | 35/11 | COMPLETED
2024-12-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-22 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418 | 35/7 | COMPLETED
2024-12-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-23 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418 | 35/11 | COMPLETED
2024-12-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-23 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418 | 35/7 | COMPLETED
2024-12-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-24 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418 | 35/11 | COMPLETED
2024-12-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-24 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418 | 35/7 | COMPLETED
2024-12-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-25 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418 | 35/11 | COMPLETED
2024-12-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-25 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418 | 35/7 | COMPLETED
2024-12-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-26 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418 | 35/11 | COMPLETED
2024-12-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-26 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418 | 35/7 | COMPLETED
2024-12-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-27 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418 | 35/11 | COMPLETED
2024-12-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-27 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418 | 35/7 | COMPLETED
2024-12-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-28 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418 | 35/7 | COMPLETED
2024-12-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-29 | 2024-12-29 | 2025-01-05 | Gang 01 Sanjay | 27.96 | 3.495 | TA418 | 33/10 | COMPLETED
2024-12-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-29 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418 | 35/7 | COMPLETED
2024-12-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-30 | 2024-12-29 | 2025-01-05 | Gang 01 Sanjay | 27.96 | 3.495 | TA418 | 33/10 | COMPLETED
2024-12-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-30 | 2024-12-30 | 2025-01-07 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 40/4 | COMPLETED
2024-12-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-31 | 2024-12-29 | 2025-01-05 | Gang 01 Sanjay | 27.96 | 3.495 | TA418 | 33/10 | COMPLETED
2024-12-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-31 | 2024-12-30 | 2025-01-07 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 40/4 | COMPLETED
2025-01-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2025-01-01 | 2024-12-29 | 2025-01-05 | Gang 01 Sanjay | 27.96 | 3.495 | TA418 | 33/10 | COMPLETED
2025-01-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-01 | 2024-12-30 | 2025-01-07 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 40/4 | COMPLETED
2025-01-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2025-01-02 | 2024-12-29 | 2025-01-05 | Gang 01 Sanjay | 27.96 | 3.495 | TA418 | 33/10 | COMPLETED
2025-01-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-02 | 2024-12-30 | 2025-01-07 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 40/4 | COMPLETED
2025-01-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2025-01-03 | 2024-12-29 | 2025-01-05 | Gang 01 Sanjay | 27.96 | 3.495 | TA418 | 33/10 | COMPLETED
2025-01-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-03 | 2024-12-30 | 2025-01-07 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 40/4 | COMPLETED
2025-01-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2025-01-04 | 2024-12-29 | 2025-01-05 | Gang 01 Sanjay | 27.96 | 3.495 | TA418 | 33/10 | COMPLETED
2025-01-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-04 | 2024-12-30 | 2025-01-07 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 40/4 | COMPLETED
2025-01-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2025-01-05 | 2024-12-29 | 2025-01-05 | Gang 01 Sanjay | 27.96 | 3.495 | TA418 | 33/10 | COMPLETED
2025-01-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-05 | 2024-12-30 | 2025-01-07 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 40/4 | COMPLETED
2025-01-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2025-01-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-06 | 2024-12-30 | 2025-01-07 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 40/4 | COMPLETED
2025-01-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2025-01-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-07 | 2024-12-30 | 2025-01-07 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 40/4 | COMPLETED
2025-01-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2025-01-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2025-01-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2025-01-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2025-01-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-13 | 2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 46/8 | COMPLETED
2025-01-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-14 | 2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 46/8 | COMPLETED
2025-01-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-15 | 2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 46/8 | COMPLETED
2025-01-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-16 | 2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 46/8 | COMPLETED
2025-01-16 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | TA418 | 46/4 | COMPLETED
2025-01-16 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | TA418 | 55/1 | COMPLETED
2025-01-17 | 2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 46/8 | COMPLETED
2025-01-17 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | TA418 | 46/4 | COMPLETED
2025-01-17 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | TA418 | 55/1 | COMPLETED
2025-01-18 | 2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 46/8 | COMPLETED
2025-01-18 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | TA418 | 46/4 | COMPLETED
2025-01-18 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | TA418 | 55/1 | COMPLETED
2025-01-19 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | TA418 | 46/4 | COMPLETED
2025-01-19 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | TA418 | 55/1 | COMPLETED
2025-01-20 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | TA418 | 46/4 | COMPLETED
2025-01-20 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | TA418 | 55/1 | COMPLETED
2025-01-21 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | TA418 | 46/4 | COMPLETED
2025-01-21 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | TA418 | 55/1 | COMPLETED
2025-01-22 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | TA418 | 46/4 | COMPLETED
2025-01-22 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | TA418 | 55/1 | COMPLETED
2025-01-23 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | TA418 | 46/4 | COMPLETED
2025-01-23 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | TA418 | 55/1 | COMPLETED
2025-01-24 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | TA418 | 34/2 | COMPLETED
2025-01-24 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-01-25 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | TA418 | 34/2 | COMPLETED
2025-01-25 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-01-25 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418 | 55/2 | COMPLETED
2025-01-26 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | TA418 | 34/2 | COMPLETED
2025-01-26 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-01-26 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418 | 55/2 | COMPLETED
2025-01-27 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | TA418 | 34/2 | COMPLETED
2025-01-27 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-01-27 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418 | 55/2 | COMPLETED
2025-01-28 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | TA418 | 34/2 | COMPLETED
2025-01-28 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-01-28 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418 | 55/2 | COMPLETED
2025-01-29 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | TA418 | 34/2 | COMPLETED
2025-01-29 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-01-29 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418 | 55/2 | COMPLETED
2025-01-30 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | TA418 | 34/2 | COMPLETED
2025-01-30 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-01-30 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418 | 55/2 | COMPLETED
2025-01-31 | 2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 35/8 | COMPLETED
2025-01-31 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-01-31 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418 | 55/2 | COMPLETED
2025-02-01 | 2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 35/8 | COMPLETED
2025-02-01 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-02-01 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418 | 55/2 | COMPLETED
2025-02-02 | 2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 35/8 | COMPLETED
2025-02-02 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-02-02 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418 | 55/2 | COMPLETED
2025-02-03 | 2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 35/8 | COMPLETED
2025-02-03 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-02-04 | 2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 35/8 | COMPLETED
2025-02-04 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-02-05 | 2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 35/8 | COMPLETED
2025-02-05 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-02-06 | 2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | TA418 | 41/1 | COMPLETED
2025-02-06 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-02-07 | 2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | TA418 | 41/1 | COMPLETED
2025-02-07 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-02-08 | 2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | TA418 | 41/1 | COMPLETED
2025-02-08 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-02-09 | 2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | TA418 | 41/1 | COMPLETED
2025-02-09 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-02-10 | 2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | TA418 | 41/1 | COMPLETED
2025-02-10 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-02-11 | 2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | TA418 | 41/1 | COMPLETED
2025-02-11 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-02-12 | 2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 41/2 | COMPLETED
2025-02-12 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 54/3 | COMPLETED
2025-02-13 | 2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 41/2 | COMPLETED
2025-02-13 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 54/3 | COMPLETED
2025-02-14 | 2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 41/2 | COMPLETED
2025-02-14 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 54/3 | COMPLETED
2025-02-15 | 2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 41/2 | COMPLETED
2025-02-15 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 54/3 | COMPLETED
2025-02-16 | 2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 41/2 | COMPLETED
2025-02-16 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 54/3 | COMPLETED
2025-02-17 | 2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 41/2 | COMPLETED
2025-02-17 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 54/3 | COMPLETED
2025-02-18 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 54/3 | COMPLETED
2025-02-19 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 54/3 | COMPLETED
2025-02-20 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 54/3 | COMPLETED
2025-02-21 | 2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 41/0 | COMPLETED
2025-02-22 | 2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 41/0 | COMPLETED
2025-02-23 | 2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 41/0 | COMPLETED
2025-02-24 | 2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 41/0 | COMPLETED
2025-02-25 | 2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 41/0 | COMPLETED
2025-02-26 | 2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 41/0 | COMPLETED
2025-02-26 | 2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 43/0 | COMPLETED
2025-02-27 | 2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 43/0 | COMPLETED
2025-02-28 | 2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 43/0 | COMPLETED
2025-03-01 | 2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 43/0 | COMPLETED
2025-03-02 | 2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 43/0 | COMPLETED
2025-03-03 | 2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 43/0 | COMPLETED
2025-03-03 | 2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 46/0 | COMPLETED
2025-03-04 | 2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 46/0 | COMPLETED
2025-03-05 | 2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 46/0 | COMPLETED
2025-03-06 | 2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 46/0 | COMPLETED
2025-03-06 | 2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/9 | COMPLETED
2025-03-07 | 2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 46/0 | COMPLETED
2025-03-07 | 2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/9 | COMPLETED
2025-03-08 | 2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 46/0 | COMPLETED
2025-03-08 | 2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/9 | COMPLETED
2025-03-09 | 2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/9 | COMPLETED
2025-03-10 | 2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/9 | COMPLETED
2025-03-11 | 2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/9 | COMPLETED
2025-03-12 | 2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | TA418 | 46/7 | COMPLETED
2025-03-13 | 2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | TA418 | 46/7 | COMPLETED
2025-03-14 | 2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | TA418 | 46/7 | COMPLETED
2025-03-15 | 2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | TA418 | 46/7 | COMPLETED
2025-03-16 | 2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | TA418 | 46/7 | COMPLETED
2025-03-17 | 2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | TA418 | 46/7 | COMPLETED
2025-03-18 | 2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | TA418 | 45/0 | COMPLETED
2025-03-18 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418 | 45/1 | COMPLETED
2025-03-19 | 2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | TA418 | 45/0 | COMPLETED
2025-03-19 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418 | 45/1 | COMPLETED
2025-03-20 | 2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | TA418 | 45/0 | COMPLETED
2025-03-20 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418 | 45/1 | COMPLETED
2025-03-21 | 2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | TA418 | 45/0 | COMPLETED
2025-03-21 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418 | 45/1 | COMPLETED
2025-03-22 | 2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | TA418 | 45/0 | COMPLETED
2025-03-22 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418 | 45/1 | COMPLETED
2025-03-23 | 2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | TA418 | 45/0 | COMPLETED
2025-03-23 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418 | 45/1 | COMPLETED
2025-03-24 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418 | 45/1 | COMPLETED
2025-03-25 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418 | 45/1 | COMPLETED
2025-03-26 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418 | 45/1 | COMPLETED
2025-03-27 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418 | 45/1 | COMPLETED
2025-03-28 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418 | 45/1 | COMPLETED
2025-03-28 | 2025-03-28 | 2025-04-01 | Gang 02 Sanjay | 28 | 5.6 | TA418 | 45/2 | COMPLETED
2025-03-29 | 2025-03-28 | 2025-04-01 | Gang 02 Sanjay | 28 | 5.6 | TA418 | 45/2 | COMPLETED
2025-03-30 | 2025-03-28 | 2025-04-01 | Gang 02 Sanjay | 28 | 5.6 | TA418 | 45/2 | COMPLETED
2025-03-31 | 2025-03-28 | 2025-04-01 | Gang 02 Sanjay | 28 | 5.6 | TA418 | 45/2 | COMPLETED
2025-04-01 | 2025-03-28 | 2025-04-01 | Gang 02 Sanjay | 28 | 5.6 | TA418 | 45/2 | COMPLETED
2025-04-02 | 2025-04-02 | 2025-04-05 | Gang 02 Sanjay | 29 | 7.25 | TA418 | 40/3 | COMPLETED
2025-04-03 | 2025-04-02 | 2025-04-05 | Gang 02 Sanjay | 29 | 7.25 | TA418 | 40/3 | COMPLETED
2025-04-04 | 2025-04-02 | 2025-04-05 | Gang 02 Sanjay | 29 | 7.25 | TA418 | 40/3 | COMPLETED
2025-04-05 | 2025-04-02 | 2025-04-05 | Gang 02 Sanjay | 29 | 7.25 | TA418 | 40/3 | COMPLETED
2025-04-05 | 2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | TA418 | 42/0 | COMPLETED
2025-04-06 | 2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | TA418 | 42/0 | COMPLETED
2025-04-07 | 2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | TA418 | 42/0 | COMPLETED
2025-04-08 | 2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | TA418 | 42/0 | COMPLETED
2025-04-09 | 2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | TA418 | 42/0 | COMPLETED
2025-04-10 | 2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | TA418 | 42/0 | COMPLETED
2025-04-11 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418 | 33/5 | COMPLETED
2025-04-12 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418 | 33/5 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | TA418 | 55/4 | COMPLETED
2025-04-13 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418 | 33/5 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | TA418 | 55/4 | COMPLETED
2025-04-14 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418 | 33/5 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | TA418 | 55/4 | COMPLETED
2025-04-15 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418 | 33/5 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | TA418 | 55/4 | COMPLETED
2025-04-16 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418 | 33/5 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | TA418 | 55/4 | COMPLETED
2025-04-17 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418 | 33/5 | COMPLETED
2025-04-17 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | TA418 | 55/4 | COMPLETED
2025-04-18 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418 | 33/5 | COMPLETED
2025-04-18 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | TA418 | 55/4 | COMPLETED
2025-04-18 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418 | 55/0 | COMPLETED
2025-04-19 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418 | 33/5 | COMPLETED
2025-04-19 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418 | 55/0 | COMPLETED
2025-04-20 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418 | 33/5 | COMPLETED
2025-04-20 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418 | 55/0 | COMPLETED
2025-04-21 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418 | 33/5 | COMPLETED
2025-04-21 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418 | 55/0 | COMPLETED
2025-04-22 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | TA418 | 34/0 | COMPLETED
2025-04-22 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418 | 55/0 | COMPLETED
2025-04-23 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | TA418 | 34/0 | COMPLETED
2025-04-23 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418 | 55/0 | COMPLETED
2025-04-24 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | TA418 | 34/0 | COMPLETED
2025-04-24 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418 | 55/0 | COMPLETED
2025-04-25 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | TA418 | 34/0 | COMPLETED
2025-04-25 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418 | 55/0 | COMPLETED
2025-04-26 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | TA418 | 34/0 | COMPLETED
2025-04-26 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418 | 55/0 | COMPLETED
2025-04-27 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | TA418 | 34/0 | COMPLETED
2025-04-27 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | TA418 | 46/15 | COMPLETED
2025-04-28 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | TA418 | 34/0 | COMPLETED
2025-04-28 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | TA418 | 46/15 | COMPLETED
2025-04-29 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | TA418 | 34/0 | COMPLETED
2025-04-29 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 37/1 | COMPLETED
2025-04-29 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | TA418 | 46/15 | COMPLETED
2025-04-30 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 37/1 | COMPLETED
2025-04-30 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | TA418 | 46/15 | COMPLETED
2025-05-01 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 37/1 | COMPLETED
2025-05-01 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | TA418 | 46/15 | COMPLETED
2025-05-02 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 37/1 | COMPLETED
2025-05-02 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | TA418 | 46/15 | COMPLETED
2025-05-03 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 37/1 | COMPLETED
2025-05-03 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | TA418 | 46/15 | COMPLETED
2025-05-04 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 37/1 | COMPLETED
2025-05-05 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 37/1 | COMPLETED
2025-05-05 | 2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/2 | COMPLETED
2025-05-06 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 37/1 | COMPLETED
2025-05-06 | 2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/2 | COMPLETED
2025-05-07 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 37/1 | COMPLETED
2025-05-07 | 2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/2 | COMPLETED
2025-05-08 | 2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/2 | COMPLETED
2025-05-08 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418 | 35/0 | COMPLETED
2025-05-09 | 2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/2 | COMPLETED
2025-05-09 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418 | 35/0 | COMPLETED
2025-05-10 | 2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/2 | COMPLETED
2025-05-10 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418 | 35/0 | COMPLETED
2025-05-11 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418 | 46/5 | COMPLETED
2025-05-11 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418 | 35/0 | COMPLETED
2025-05-11 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-12 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418 | 46/5 | COMPLETED
2025-05-12 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418 | 35/0 | COMPLETED
2025-05-12 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-13 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418 | 46/5 | COMPLETED
2025-05-13 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418 | 35/0 | COMPLETED
2025-05-13 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-14 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418 | 46/5 | COMPLETED
2025-05-14 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418 | 35/0 | COMPLETED
2025-05-14 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-15 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418 | 46/5 | COMPLETED
2025-05-15 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418 | 35/0 | COMPLETED
2025-05-15 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-16 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418 | 46/5 | COMPLETED
2025-05-16 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418 | 35/0 | COMPLETED
2025-05-16 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-17 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418 | 46/5 | COMPLETED
2025-05-17 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418 | 35/0 | COMPLETED
2025-05-17 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-18 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418 | 46/5 | COMPLETED
2025-05-18 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-19 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418 | 46/5 | COMPLETED
2025-05-19 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-20 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-21 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-22 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | TA418 | 34/4 | COMPLETED
2025-05-22 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-23 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | TA418 | 34/4 | COMPLETED
2025-05-23 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-24 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | TA418 | 34/4 | COMPLETED
2025-05-24 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-25 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | TA418 | 34/4 | COMPLETED
2025-05-25 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-26 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | TA418 | 34/4 | COMPLETED
2025-05-26 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-27 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | TA418 | 34/4 | COMPLETED
2025-05-28 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | TA418 | 34/4 | COMPLETED
2025-05-29 | 2025-05-29 | 2025-06-02 | Gang 01 Sanjay | 27 | 5.4 | TA418 | 40/5 | COMPLETED
2025-05-30 | 2025-05-29 | 2025-06-02 | Gang 01 Sanjay | 27 | 5.4 | TA418 | 40/5 | COMPLETED
2025-05-30 | 2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 35/3 | COMPLETED
2025-05-31 | 2025-05-29 | 2025-06-02 | Gang 01 Sanjay | 27 | 5.4 | TA418 | 40/5 | COMPLETED
2025-05-31 | 2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 35/3 | COMPLETED
2025-06-01 | 2025-05-29 | 2025-06-02 | Gang 01 Sanjay | 27 | 5.4 | TA418 | 40/5 | COMPLETED
2025-06-01 | 2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 35/3 | COMPLETED
2025-06-02 | 2025-05-29 | 2025-06-02 | Gang 01 Sanjay | 27 | 5.4 | TA418 | 40/5 | COMPLETED
2025-06-02 | 2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 35/3 | COMPLETED
2025-06-03 | 2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 35/3 | COMPLETED
2025-06-03 | 2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 33/7 | COMPLETED
2025-06-04 | 2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 35/3 | COMPLETED
2025-06-04 | 2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 33/7 | COMPLETED
2025-06-05 | 2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 33/7 | COMPLETED
2025-06-06 | 2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 33/7 | COMPLETED
2025-06-07 | 2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 33/7 | COMPLETED
2025-06-08 | 2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 33/7 | COMPLETED
2025-06-09 | 2025-06-09 | 2025-06-12 | Gang 02 Sanjay | 27 | 6.75 | TA418 | 33/8 | COMPLETED
2025-06-10 | 2025-06-09 | 2025-06-12 | Gang 02 Sanjay | 27 | 6.75 | TA418 | 33/8 | COMPLETED
2025-06-11 | 2025-06-09 | 2025-06-12 | Gang 02 Sanjay | 27 | 6.75 | TA418 | 33/8 | COMPLETED
2025-06-12 | 2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | TA418 | 33/9 | COMPLETED
2025-06-12 | 2025-06-09 | 2025-06-12 | Gang 02 Sanjay | 27 | 6.75 | TA418 | 33/8 | COMPLETED
2025-06-13 | 2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | TA418 | 33/9 | COMPLETED
2025-06-14 | 2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | TA418 | 33/9 | COMPLETED
2025-06-14 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418 | 33/6 | COMPLETED
2025-06-15 | 2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | TA418 | 33/9 | COMPLETED
2025-06-15 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418 | 33/6 | COMPLETED
2025-06-16 | 2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | TA418 | 33/9 | COMPLETED
2025-06-16 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418 | 33/6 | COMPLETED
2025-06-17 | 2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | TA418 | 33/9 | COMPLETED
2025-06-17 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418 | 33/6 | COMPLETED
2025-06-18 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418 | 33/6 | COMPLETED
2025-06-19 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-06-19 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418 | 33/6 | COMPLETED
2025-06-20 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-06-20 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418 | 33/6 | COMPLETED
2025-06-21 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-06-21 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418 | 33/6 | COMPLETED
2025-06-22 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-06-22 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418 | 33/6 | COMPLETED
2025-06-23 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-06-23 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418 | 33/6 | COMPLETED
2025-06-24 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-06-24 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418 | 33/6 | COMPLETED
2025-06-25 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-06-26 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-06-27 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-06-28 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-06-29 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-06-29 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-06-30 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-06-30 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-01 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-07-01 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-02 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-03 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-03 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-03 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418 | 38/2 | COMPLETED
2025-07-03 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418 | 37/0 | COMPLETED
2025-07-04 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-04 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-04 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418 | 38/2 | COMPLETED
2025-07-04 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418 | 37/0 | COMPLETED
2025-07-05 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-05 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-05 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418 | 38/2 | COMPLETED
2025-07-05 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418 | 37/0 | COMPLETED
2025-07-06 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-06 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-06 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418 | 38/2 | COMPLETED
2025-07-06 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418 | 37/0 | COMPLETED
2025-07-07 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-07 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-07 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418 | 38/2 | COMPLETED
2025-07-07 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418 | 37/0 | COMPLETED
2025-07-08 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-08 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-08 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418 | 38/2 | COMPLETED
2025-07-08 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418 | 37/0 | COMPLETED
2025-07-09 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-09 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-09 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418 | 38/2 | COMPLETED
2025-07-09 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418 | 37/0 | COMPLETED
2025-07-10 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-10 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-10 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418 | 38/2 | COMPLETED
2025-07-10 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418 | 37/0 | COMPLETED
2025-07-11 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-11 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-11 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418 | 38/2 | COMPLETED
2025-07-11 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418 | 37/0 | COMPLETED
2025-07-12 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-12 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-12 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418 | 38/2 | COMPLETED
2025-07-12 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418 | 37/0 | COMPLETED
2025-07-13 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-13 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-13 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418 | 37/0 | COMPLETED
2025-07-14 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-14 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-14 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | TA418 | 37/2 | COMPLETED
2025-07-14 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418 | 37/0 | COMPLETED
2025-07-15 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-15 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-15 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | TA418 | 37/2 | COMPLETED
2025-07-15 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418 | 38/1 | COMPLETED
2025-07-16 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-16 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-16 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | TA418 | 37/2 | COMPLETED
2025-07-16 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418 | 38/1 | COMPLETED
2025-07-17 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-17 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-17 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | TA418 | 37/2 | COMPLETED
2025-07-17 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418 | 38/1 | COMPLETED
2025-07-18 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-18 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-18 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | TA418 | 37/2 | COMPLETED
2025-07-18 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418 | 38/1 | COMPLETED
2025-07-19 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-19 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-19 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | TA418 | 37/2 | COMPLETED
2025-07-19 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418 | 38/1 | COMPLETED
2025-07-20 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-20 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-20 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | TA418 | 37/2 | COMPLETED
2025-07-20 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418 | 38/1 | COMPLETED
2025-07-21 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-21 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-21 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418 | 38/1 | COMPLETED
2025-07-21 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418 | 35/9 | COMPLETED
2025-07-21 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-07-22 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-22 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 35/5 | COMPLETED
2025-07-22 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418 | 38/1 | COMPLETED
2025-07-22 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418 | 35/9 | COMPLETED
2025-07-22 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-07-23 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-23 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 35/5 | COMPLETED
2025-07-23 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418 | 38/1 | COMPLETED
2025-07-23 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418 | 35/9 | COMPLETED
2025-07-23 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-07-24 | 2025-07-24 | 2025-08-06 | Gang 02 Sanjay Kec 02 Barkat Ali | 29 | 2.0714 | TA418 | 41/5 | COMPLETED
2025-07-24 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-24 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 35/5 | COMPLETED
2025-07-24 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418 | 35/9 | COMPLETED
2025-07-24 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-07-25 | 2025-07-24 | 2025-08-06 | Gang 02 Sanjay Kec 02 Barkat Ali | 29 | 2.0714 | TA418 | 41/5 | COMPLETED
2025-07-25 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-25 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 35/5 | COMPLETED
2025-07-25 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418 | 35/9 | COMPLETED
2025-07-25 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-07-26 | 2025-07-24 | 2025-08-06 | Gang 02 Sanjay Kec 02 Barkat Ali | 29 | 2.0714 | TA418 | 41/5 | COMPLETED
2025-07-26 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-26 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 35/5 | COMPLETED
2025-07-26 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418 | 35/9 | COMPLETED
2025-07-26 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-07-27 | 2025-07-24 | 2025-08-06 | Gang 02 Sanjay Kec 02 Barkat Ali | 29 | 2.0714 | TA418 | 41/5 | COMPLETED
2025-07-27 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-27 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 35/5 | COMPLETED
2025-07-27 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418 | 35/9 | COMPLETED
2025-07-27 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-07-28 | 2025-07-24 | 2025-08-06 | Gang 02 Sanjay Kec 02 Barkat Ali | 29 | 2.0714 | TA418 | 41/5 | COMPLETED
2025-07-28 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-28 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 35/5 | COMPLETED
2025-07-28 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418 | 35/9 | COMPLETED
2025-07-28 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-07-29 | 2025-07-24 | 2025-08-06 | Gang 02 Sanjay Kec 02 Barkat Ali | 29 | 2.0714 | TA418 | 41/5 | COMPLETED
2025-07-29 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-29 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 35/5 | COMPLETED
2025-07-29 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418 | 35/9 | COMPLETED
2025-07-29 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-07-30 | 2025-07-24 | 2025-08-06 | Gang 02 Sanjay Kec 02 Barkat Ali | 29 | 2.0714 | TA418 | 41/5 | COMPLETED
2025-07-30 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-30 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 35/5 | COMPLETED
2025-07-30 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418 | 35/9 | COMPLETED
2025-07-30 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-07-31 | 2025-07-24 | 2025-08-06 | Gang 02 Sanjay Kec 02 Barkat Ali | 29 | 2.0714 | TA418 | 41/5 | COMPLETED
2025-07-31 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-31 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418 | 35/9 | COMPLETED
2025-07-31 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-08-01 | 2025-07-24 | 2025-08-06 | Gang 02 Sanjay Kec 02 Barkat Ali | 29 | 2.0714 | TA418 | 41/5 | COMPLETED
2025-08-01 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-08-01 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-08-02 | 2025-07-24 | 2025-08-06 | Gang 02 Sanjay Kec 02 Barkat Ali | 29 | 2.0714 | TA418 | 41/5 | COMPLETED
2025-08-02 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-08-02 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-08-03 | 2025-07-24 | 2025-08-06 | Gang 02 Sanjay Kec 02 Barkat Ali | 29 | 2.0714 | TA418 | 41/5 | COMPLETED
2025-08-03 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-08-03 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-08-04 | 2025-07-24 | 2025-08-06 | Gang 02 Sanjay Kec 02 Barkat Ali | 29 | 2.0714 | TA418 | 41/5 | COMPLETED
2025-08-04 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-08-04 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-08-05 | 2025-07-24 | 2025-08-06 | Gang 02 Sanjay Kec 02 Barkat Ali | 29 | 2.0714 | TA418 | 41/5 | COMPLETED
2025-08-05 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-08-05 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-08-06 | 2025-07-24 | 2025-08-06 | Gang 02 Sanjay Kec 02 Barkat Ali | 29 | 2.0714 | TA418 | 41/5 | COMPLETED
2025-08-06 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-08-06 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-06 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-08-07 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-08-07 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418 | 35/10 | COMPLETED
2025-08-07 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-07 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-08-07 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418 | 48A/0 | COMPLETED
2025-08-08 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418 | 35/10 | COMPLETED
2025-08-08 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-08 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418 | 48A/0 | COMPLETED
2025-08-09 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418 | 35/10 | COMPLETED
2025-08-09 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-09 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-09 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418 | 48A/0 | COMPLETED
2025-08-10 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418 | 35/10 | COMPLETED
2025-08-10 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-10 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-10 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418 | 48A/0 | COMPLETED
2025-08-11 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418 | 35/10 | COMPLETED
2025-08-11 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-11 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-11 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418 | 48A/0 | COMPLETED
2025-08-12 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418 | 35/10 | COMPLETED
2025-08-12 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-12 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-12 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418 | 48A/0 | COMPLETED
2025-08-13 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418 | 35/10 | COMPLETED
2025-08-13 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-13 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-13 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418 | 48A/0 | COMPLETED
2025-08-14 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418 | 35/10 | COMPLETED
2025-08-14 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-14 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-14 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418 | 48A/0 | COMPLETED
2025-08-15 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418 | 35/10 | COMPLETED
2025-08-15 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-15 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-15 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418 | 48A/0 | COMPLETED
2025-08-16 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418 | 35/10 | COMPLETED
2025-08-16 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-16 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-16 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418 | 48A/0 | COMPLETED
2025-08-16 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-17 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418 | 35/10 | COMPLETED
2025-08-17 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-17 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-17 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-18 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 43/1 | COMPLETED
2025-08-18 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-18 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-18 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-19 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 43/1 | COMPLETED
2025-08-19 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-19 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-19 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-19 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | TA418 | 52/0 | COMPLETED
2025-08-20 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 43/1 | COMPLETED
2025-08-20 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-20 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-20 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | TA418 | 52/0 | COMPLETED
2025-08-21 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 43/1 | COMPLETED
2025-08-21 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-21 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-21 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | TA418 | 52/0 | COMPLETED
2025-08-22 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 43/1 | COMPLETED
2025-08-22 | 2025-08-22 | 2025-08-26 | Kec 02 Barkat Ali | 28 | 5.6 | TA418 | 46/3 | COMPLETED
2025-08-22 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-22 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-22 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | TA418 | 52/0 | COMPLETED
2025-08-23 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 43/1 | COMPLETED
2025-08-23 | 2025-08-22 | 2025-08-26 | Kec 02 Barkat Ali | 28 | 5.6 | TA418 | 46/3 | COMPLETED
2025-08-23 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-23 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | TA418 | 52/0 | COMPLETED
2025-08-24 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 43/1 | COMPLETED
2025-08-24 | 2025-08-22 | 2025-08-26 | Kec 02 Barkat Ali | 28 | 5.6 | TA418 | 46/3 | COMPLETED
2025-08-24 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-24 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | TA418 | 52/0 | COMPLETED
2025-08-25 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 43/1 | COMPLETED
2025-08-25 | 2025-08-22 | 2025-08-26 | Kec 02 Barkat Ali | 28 | 5.6 | TA418 | 46/3 | COMPLETED
2025-08-25 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-25 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | TA418 | 52/0 | COMPLETED
2025-08-26 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 43/1 | COMPLETED
2025-08-26 | 2025-08-22 | 2025-08-26 | Kec 02 Barkat Ali | 28 | 5.6 | TA418 | 46/3 | COMPLETED
2025-08-26 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-08-26 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-26 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | TA418 | 52/0 | COMPLETED
2025-08-27 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-08-27 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-28 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-08-28 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-29 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-08-29 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-30 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-08-30 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-31 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418 | 33/3 | COMPLETED
2025-08-31 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-08-31 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-09-01 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418 | 33/3 | COMPLETED
2025-09-01 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-01 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418 | 62/0 | COMPLETED
2025-09-01 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-09-02 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418 | 33/3 | COMPLETED
2025-09-02 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-02 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418 | 62/0 | COMPLETED
2025-09-03 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418 | 33/3 | COMPLETED
2025-09-03 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-03 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418 | 62/0 | COMPLETED
2025-09-03 | 2025-09-03 | 2025-09-07 | Subhash | 27.9 | 5.58 | TA418 | 46/12 | COMPLETED
2025-09-04 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418 | 33/3 | COMPLETED
2025-09-04 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-04 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418 | 62/0 | COMPLETED
2025-09-04 | 2025-09-03 | 2025-09-07 | Subhash | 27.9 | 5.58 | TA418 | 46/12 | COMPLETED
2025-09-05 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418 | 33/3 | COMPLETED
2025-09-05 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-05 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418 | 62/0 | COMPLETED
2025-09-05 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-09-05 | 2025-09-03 | 2025-09-07 | Subhash | 27.9 | 5.58 | TA418 | 46/12 | COMPLETED
2025-09-06 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418 | 33/3 | COMPLETED
2025-09-06 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-06 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418 | 62/0 | COMPLETED
2025-09-06 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-09-06 | 2025-09-03 | 2025-09-07 | Subhash | 27.9 | 5.58 | TA418 | 46/12 | COMPLETED
2025-09-07 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418 | 33/3 | COMPLETED
2025-09-07 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-07 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418 | 62/0 | COMPLETED
2025-09-07 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-09-07 | 2025-09-03 | 2025-09-07 | Subhash | 27.9 | 5.58 | TA418 | 46/12 | COMPLETED
2025-09-08 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418 | 33/3 | COMPLETED
2025-09-08 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-08 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418 | 62/0 | COMPLETED
2025-09-08 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-09-09 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418 | 33/3 | COMPLETED
2025-09-09 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-09 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418 | 62/0 | COMPLETED
2025-09-09 | 2025-09-09 | 2025-09-30 | M S Mdpl | 33.3 | 1.5136 | TA418 | 45/3 | COMPLETED
2025-09-09 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-09-09 | 2025-09-09 | 2025-09-13 | Subhash | 29 | 5.8 | TA418 | 48/2 | COMPLETED
2025-09-10 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418 | 33/3 | COMPLETED
2025-09-10 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-10 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418 | 62/0 | COMPLETED
2025-09-10 | 2025-09-09 | 2025-09-30 | M S Mdpl | 33.3 | 1.5136 | TA418 | 45/3 | COMPLETED
2025-09-10 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-09-10 | 2025-09-09 | 2025-09-13 | Subhash | 29 | 5.8 | TA418 | 48/2 | COMPLETED
2025-09-11 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-11 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418 | 62/0 | COMPLETED
2025-09-11 | 2025-09-09 | 2025-09-30 | M S Mdpl | 33.3 | 1.5136 | TA418 | 45/3 | COMPLETED
2025-09-11 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-09-11 | 2025-09-09 | 2025-09-13 | Subhash | 29 | 5.8 | TA418 | 48/2 | COMPLETED
2025-09-12 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-12 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418 | 62/0 | COMPLETED
2025-09-12 | 2025-09-09 | 2025-09-30 | M S Mdpl | 33.3 | 1.5136 | TA418 | 45/3 | COMPLETED
2025-09-12 | 2025-09-12 | 2025-09-22 | M S Tofit | 33.3 | 3.0273 | TA418 | 33/2 | COMPLETED
2025-09-12 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-09-12 | 2025-09-09 | 2025-09-13 | Subhash | 29 | 5.8 | TA418 | 48/2 | COMPLETED
2025-09-13 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-13 | 2025-09-09 | 2025-09-30 | M S Mdpl | 33.3 | 1.5136 | TA418 | 45/3 | COMPLETED
2025-09-13 | 2025-09-12 | 2025-09-22 | M S Tofit | 33.3 | 3.0273 | TA418 | 33/2 | COMPLETED
2025-09-13 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-09-13 | 2025-09-09 | 2025-09-13 | Subhash | 29 | 5.8 | TA418 | 48/2 | COMPLETED
2025-09-14 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-14 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418 | 61/0 | COMPLETED
2025-09-14 | 2025-09-09 | 2025-09-30 | M S Mdpl | 33.3 | 1.5136 | TA418 | 45/3 | COMPLETED
2025-09-14 | 2025-09-12 | 2025-09-22 | M S Tofit | 33.3 | 3.0273 | TA418 | 33/2 | COMPLETED
2025-09-14 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-09-15 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-15 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418 | 61/0 | COMPLETED
2025-09-15 | 2025-09-09 | 2025-09-30 | M S Mdpl | 33.3 | 1.5136 | TA418 | 45/3 | COMPLETED
2025-09-15 | 2025-09-12 | 2025-09-22 | M S Tofit | 33.3 | 3.0273 | TA418 | 33/2 | COMPLETED
2025-09-15 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-09-16 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-16 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418 | 61/0 | COMPLETED
2025-09-16 | 2025-09-09 | 2025-09-30 | M S Mdpl | 33.3 | 1.5136 | TA418 | 45/3 | COMPLETED
2025-09-16 | 2025-09-12 | 2025-09-22 | M S Tofit | 33.3 | 3.0273 | TA418 | 33/2 | COMPLETED
2025-09-16 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-09-16 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | TA418 | 53/0 | COMPLETED
2025-09-17 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-17 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418 | 61/0 | COMPLETED
2025-09-17 | 2025-09-09 | 2025-09-30 | M S Mdpl | 33.3 | 1.5136 | TA418 | 45/3 | COMPLETED
2025-09-17 | 2025-09-12 | 2025-09-22 | M S Tofit | 33.3 | 3.0273 | TA418 | 33/2 | COMPLETED
2025-09-17 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-09-17 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | TA418 | 53/0 | COMPLETED
2025-09-18 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-18 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418 | 61/0 | COMPLETED
2025-09-18 | 2025-09-09 | 2025-09-30 | M S Mdpl | 33.3 | 1.5136 | TA418 | 45/3 | COMPLETED
2025-09-18 | 2025-09-12 | 2025-09-22 | M S Tofit | 33.3 | 3.0273 | TA418 | 33/2 | COMPLETED
2025-09-18 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-09-18 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | TA418 | 53/0 | COMPLETED
2025-09-19 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-19 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418 | 61/0 | COMPLETED
2025-09-19 | 2025-09-09 | 2025-09-30 | M S Mdpl | 33.3 | 1.5136 | TA418 | 45/3 | COMPLETED
2025-09-19 | 2025-09-12 | 2025-09-22 | M S Tofit | 33.3 | 3.0273 | TA418 | 33/2 | COMPLETED
2025-09-19 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-09-19 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | TA418 | 53/0 | COMPLETED
2025-09-20 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-20 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418 | 61/0 | COMPLETED
2025-09-20 | 2025-09-09 | 2025-09-30 | M S Mdpl | 33.3 | 1.5136 | TA418 | 45/3 | COMPLETED
2025-09-20 | 2025-09-12 | 2025-09-22 | M S Tofit | 33.3 | 3.0273 | TA418 | 33/2 | COMPLETED
2025-09-20 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-09-20 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | TA418 | 53/0 | COMPLETED
2025-09-21 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-21 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418 | 61/0 | COMPLETED
2025-09-21 | 2025-09-09 | 2025-09-30 | M S Mdpl | 33.3 | 1.5136 | TA418 | 45/3 | COMPLETED
2025-09-21 | 2025-09-12 | 2025-09-22 | M S Tofit | 33.3 | 3.0273 | TA418 | 33/2 | COMPLETED
2025-09-21 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-09-21 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | TA418 | 53/0 | COMPLETED
2025-09-22 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-22 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418 | 61/0 | COMPLETED
2025-09-22 | 2025-09-09 | 2025-09-30 | M S Mdpl | 33.3 | 1.5136 | TA418 | 45/3 | COMPLETED
2025-09-22 | 2025-09-12 | 2025-09-22 | M S Tofit | 33.3 | 3.0273 | TA418 | 33/2 | COMPLETED
2025-09-22 | 2025-09-22 | 2025-09-30 | M S Tofit | 27 | 3 | TA418 | 33/1 | COMPLETED
2025-09-22 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-09-22 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | TA418 | 53/0 | COMPLETED
2025-09-23 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-23 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418 | 61/0 | COMPLETED
2025-09-23 | 2025-09-09 | 2025-09-30 | M S Mdpl | 33.3 | 1.5136 | TA418 | 45/3 | COMPLETED
2025-09-23 | 2025-09-22 | 2025-09-30 | M S Tofit | 27 | 3 | TA418 | 33/1 | COMPLETED
2025-09-23 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-09-23 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | TA418 | 53/0 | COMPLETED
2025-09-24 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-24 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418 | 61/0 | COMPLETED
2025-09-24 | 2025-09-09 | 2025-09-30 | M S Mdpl | 33.3 | 1.5136 | TA418 | 45/3 | COMPLETED
2025-09-24 | 2025-09-22 | 2025-09-30 | M S Tofit | 27 | 3 | TA418 | 33/1 | COMPLETED
2025-09-24 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-09-25 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-25 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418 | 61/0 | COMPLETED
2025-09-25 | 2025-09-09 | 2025-09-30 | M S Mdpl | 33.3 | 1.5136 | TA418 | 45/3 | COMPLETED
2025-09-25 | 2025-09-22 | 2025-09-30 | M S Tofit | 27 | 3 | TA418 | 33/1 | COMPLETED
2025-09-25 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-09-25 | 2025-09-25 | 2025-10-01 | Subhash | 50 | 7.1429 | TA418 | 44/0 | COMPLETED
2025-09-26 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-26 | 2025-09-09 | 2025-09-30 | M S Mdpl | 33.3 | 1.5136 | TA418 | 45/3 | COMPLETED
2025-09-26 | 2025-09-22 | 2025-09-30 | M S Tofit | 27 | 3 | TA418 | 33/1 | COMPLETED
2025-09-26 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-09-26 | 2025-09-25 | 2025-10-01 | Subhash | 50 | 7.1429 | TA418 | 44/0 | COMPLETED
2025-09-27 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-27 | 2025-09-09 | 2025-09-30 | M S Mdpl | 33.3 | 1.5136 | TA418 | 45/3 | COMPLETED
2025-09-27 | 2025-09-22 | 2025-09-30 | M S Tofit | 27 | 3 | TA418 | 33/1 | COMPLETED
2025-09-27 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-09-27 | 2025-09-25 | 2025-10-01 | Subhash | 50 | 7.1429 | TA418 | 44/0 | COMPLETED
2025-09-28 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-28 | 2025-09-28 | 2025-10-05 | Kec 02 Barkat Ali | 27 | 3.375 | TA418 | 54/1 | COMPLETED
2025-09-28 | 2025-09-09 | 2025-09-30 | M S Mdpl | 33.3 | 1.5136 | TA418 | 45/3 | COMPLETED
2025-09-28 | 2025-09-22 | 2025-09-30 | M S Tofit | 27 | 3 | TA418 | 33/1 | COMPLETED
2025-09-28 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-09-28 | 2025-09-25 | 2025-10-01 | Subhash | 50 | 7.1429 | TA418 | 44/0 | COMPLETED
2025-09-29 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-29 | 2025-09-28 | 2025-10-05 | Kec 02 Barkat Ali | 27 | 3.375 | TA418 | 54/1 | COMPLETED
2025-09-29 | 2025-09-09 | 2025-09-30 | M S Mdpl | 33.3 | 1.5136 | TA418 | 45/3 | COMPLETED
2025-09-29 | 2025-09-29 | 2025-10-17 | M S Mdpl | 60 | 3.1579 | TA418 | 54/0 | COMPLETED
2025-09-29 | 2025-09-22 | 2025-09-30 | M S Tofit | 27 | 3 | TA418 | 33/1 | COMPLETED
2025-09-29 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-09-29 | 2025-09-25 | 2025-10-01 | Subhash | 50 | 7.1429 | TA418 | 44/0 | COMPLETED
2025-09-30 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-09-30 | 2025-09-28 | 2025-10-05 | Kec 02 Barkat Ali | 27 | 3.375 | TA418 | 54/1 | COMPLETED
2025-09-30 | 2025-09-09 | 2025-09-30 | M S Mdpl | 33.3 | 1.5136 | TA418 | 45/3 | COMPLETED
2025-09-30 | 2025-09-29 | 2025-10-17 | M S Mdpl | 60 | 3.1579 | TA418 | 54/0 | COMPLETED
2025-09-30 | 2025-09-22 | 2025-09-30 | M S Tofit | 27 | 3 | TA418 | 33/1 | COMPLETED
2025-09-30 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-09-30 | 2025-09-25 | 2025-10-01 | Subhash | 50 | 7.1429 | TA418 | 44/0 | COMPLETED
2025-10-01 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-10-01 | 2025-09-28 | 2025-10-05 | Kec 02 Barkat Ali | 27 | 3.375 | TA418 | 54/1 | COMPLETED
2025-10-01 | 2025-09-29 | 2025-10-17 | M S Mdpl | 60 | 3.1579 | TA418 | 54/0 | COMPLETED
2025-10-01 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-10-01 | 2025-09-25 | 2025-10-01 | Subhash | 50 | 7.1429 | TA418 | 44/0 | COMPLETED
2025-10-02 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-10-02 | 2025-09-28 | 2025-10-05 | Kec 02 Barkat Ali | 27 | 3.375 | TA418 | 54/1 | COMPLETED
2025-10-02 | 2025-09-29 | 2025-10-17 | M S Mdpl | 60 | 3.1579 | TA418 | 54/0 | COMPLETED
2025-10-02 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-10-03 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-10-03 | 2025-09-28 | 2025-10-05 | Kec 02 Barkat Ali | 27 | 3.375 | TA418 | 54/1 | COMPLETED
2025-10-03 | 2025-09-29 | 2025-10-17 | M S Mdpl | 60 | 3.1579 | TA418 | 54/0 | COMPLETED
2025-10-03 | 2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-10-04 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-10-04 | 2025-09-28 | 2025-10-05 | Kec 02 Barkat Ali | 27 | 3.375 | TA418 | 54/1 | COMPLETED
2025-10-04 | 2025-09-29 | 2025-10-17 | M S Mdpl | 60 | 3.1579 | TA418 | 54/0 | COMPLETED
2025-10-04 | 2025-10-04 | 2025-10-17 | M S Tofit | 60 | 4.2857 | TA418 | 32/0 | COMPLETED
2025-10-05 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-10-05 | 2025-09-28 | 2025-10-05 | Kec 02 Barkat Ali | 27 | 3.375 | TA418 | 54/1 | COMPLETED
2025-10-05 | 2025-09-29 | 2025-10-17 | M S Mdpl | 60 | 3.1579 | TA418 | 54/0 | COMPLETED
2025-10-05 | 2025-10-04 | 2025-10-17 | M S Tofit | 60 | 4.2857 | TA418 | 32/0 | COMPLETED
2025-10-06 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-10-06 | 2025-09-29 | 2025-10-17 | M S Mdpl | 60 | 3.1579 | TA418 | 54/0 | COMPLETED
2025-10-06 | 2025-10-04 | 2025-10-17 | M S Tofit | 60 | 4.2857 | TA418 | 32/0 | COMPLETED
2025-10-07 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-10-07 | 2025-09-29 | 2025-10-17 | M S Mdpl | 60 | 3.1579 | TA418 | 54/0 | COMPLETED
2025-10-07 | 2025-10-04 | 2025-10-17 | M S Tofit | 60 | 4.2857 | TA418 | 32/0 | COMPLETED
2025-10-08 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-10-08 | 2025-09-29 | 2025-10-17 | M S Mdpl | 60 | 3.1579 | TA418 | 54/0 | COMPLETED
2025-10-08 | 2025-10-04 | 2025-10-17 | M S Tofit | 60 | 4.2857 | TA418 | 32/0 | COMPLETED
2025-10-09 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-10-09 | 2025-09-29 | 2025-10-17 | M S Mdpl | 60 | 3.1579 | TA418 | 54/0 | COMPLETED
2025-10-09 | 2025-10-04 | 2025-10-17 | M S Tofit | 60 | 4.2857 | TA418 | 32/0 | COMPLETED
2025-10-10 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-10-10 | 2025-09-29 | 2025-10-17 | M S Mdpl | 60 | 3.1579 | TA418 | 54/0 | COMPLETED
2025-10-10 | 2025-10-04 | 2025-10-17 | M S Tofit | 60 | 4.2857 | TA418 | 32/0 | COMPLETED
2025-10-11 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-10-11 | 2025-09-29 | 2025-10-17 | M S Mdpl | 60 | 3.1579 | TA418 | 54/0 | COMPLETED
2025-10-11 | 2025-10-04 | 2025-10-17 | M S Tofit | 60 | 4.2857 | TA418 | 32/0 | COMPLETED
2025-10-12 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-10-12 | 2025-09-29 | 2025-10-17 | M S Mdpl | 60 | 3.1579 | TA418 | 54/0 | COMPLETED
2025-10-12 | 2025-10-04 | 2025-10-17 | M S Tofit | 60 | 4.2857 | TA418 | 32/0 | COMPLETED
2025-10-13 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-10-13 | 2025-09-29 | 2025-10-17 | M S Mdpl | 60 | 3.1579 | TA418 | 54/0 | COMPLETED
2025-10-13 | 2025-10-04 | 2025-10-17 | M S Tofit | 60 | 4.2857 | TA418 | 32/0 | COMPLETED
2025-10-14 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-10-14 | 2025-09-29 | 2025-10-17 | M S Mdpl | 60 | 3.1579 | TA418 | 54/0 | COMPLETED
2025-10-14 | 2025-10-04 | 2025-10-17 | M S Tofit | 60 | 4.2857 | TA418 | 32/0 | COMPLETED
2025-10-15 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-10-15 | 2025-09-29 | 2025-10-17 | M S Mdpl | 60 | 3.1579 | TA418 | 54/0 | COMPLETED
2025-10-15 | 2025-10-04 | 2025-10-17 | M S Tofit | 60 | 4.2857 | TA418 | 32/0 | COMPLETED
2025-10-16 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-10-16 | 2025-09-29 | 2025-10-17 | M S Mdpl | 60 | 3.1579 | TA418 | 54/0 | COMPLETED
2025-10-16 | 2025-10-04 | 2025-10-17 | M S Tofit | 60 | 4.2857 | TA418 | 32/0 | COMPLETED
2025-10-16 | 2025-10-16 | 2025-11-07 | M S Tofit | 89 | 3.8696 | TA418 | 33/0 | COMPLETED
2025-10-17 | 2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-10-17 | 2025-09-29 | 2025-10-17 | M S Mdpl | 60 | 3.1579 | TA418 | 54/0 | COMPLETED
2025-10-17 | 2025-10-04 | 2025-10-17 | M S Tofit | 60 | 4.2857 | TA418 | 32/0 | COMPLETED
2025-10-17 | 2025-10-16 | 2025-11-07 | M S Tofit | 89 | 3.8696 | TA418 | 33/0 | COMPLETED
2025-10-18 | 2025-10-18 | 2025-10-27 | Kec 02 Barkat Ali | 28 | 2.8 | TA418 | 60/4 | COMPLETED
2025-10-18 | 2025-10-16 | 2025-11-07 | M S Tofit | 89 | 3.8696 | TA418 | 33/0 | COMPLETED
2025-10-19 | 2025-10-18 | 2025-10-27 | Kec 02 Barkat Ali | 28 | 2.8 | TA418 | 60/4 | COMPLETED
2025-10-19 | 2025-10-16 | 2025-11-07 | M S Tofit | 89 | 3.8696 | TA418 | 33/0 | COMPLETED
2025-10-20 | 2025-10-18 | 2025-10-27 | Kec 02 Barkat Ali | 28 | 2.8 | TA418 | 60/4 | COMPLETED
2025-10-20 | 2025-10-16 | 2025-11-07 | M S Tofit | 89 | 3.8696 | TA418 | 33/0 | COMPLETED
2025-10-21 | 2025-10-18 | 2025-10-27 | Kec 02 Barkat Ali | 28 | 2.8 | TA418 | 60/4 | COMPLETED
2025-10-21 | 2025-10-16 | 2025-11-07 | M S Tofit | 89 | 3.8696 | TA418 | 33/0 | COMPLETED
2025-10-22 | 2025-10-18 | 2025-10-27 | Kec 02 Barkat Ali | 28 | 2.8 | TA418 | 60/4 | COMPLETED
2025-10-22 | 2025-10-16 | 2025-11-07 | M S Tofit | 89 | 3.8696 | TA418 | 33/0 | COMPLETED
2025-10-23 | 2025-10-18 | 2025-10-27 | Kec 02 Barkat Ali | 28 | 2.8 | TA418 | 60/4 | COMPLETED
2025-10-23 | 2025-10-16 | 2025-11-07 | M S Tofit | 89 | 3.8696 | TA418 | 33/0 | COMPLETED
2025-10-24 | 2025-10-18 | 2025-10-27 | Kec 02 Barkat Ali | 28 | 2.8 | TA418 | 60/4 | COMPLETED
2025-10-24 | 2025-10-16 | 2025-11-07 | M S Tofit | 89 | 3.8696 | TA418 | 33/0 | COMPLETED
2025-10-25 | 2025-10-18 | 2025-10-27 | Kec 02 Barkat Ali | 28 | 2.8 | TA418 | 60/4 | COMPLETED
2025-10-25 | 2025-10-16 | 2025-11-07 | M S Tofit | 89 | 3.8696 | TA418 | 33/0 | COMPLETED
2025-10-26 | 2025-10-18 | 2025-10-27 | Kec 02 Barkat Ali | 28 | 2.8 | TA418 | 60/4 | COMPLETED
2025-10-26 | 2025-10-16 | 2025-11-07 | M S Tofit | 89 | 3.8696 | TA418 | 33/0 | COMPLETED
2025-10-27 | 2025-10-18 | 2025-10-27 | Kec 02 Barkat Ali | 28 | 2.8 | TA418 | 60/4 | COMPLETED
2025-10-27 | 2025-10-16 | 2025-11-07 | M S Tofit | 89 | 3.8696 | TA418 | 33/0 | COMPLETED
2025-10-28 | 2025-10-16 | 2025-11-07 | M S Tofit | 89 | 3.8696 | TA418 | 33/0 | COMPLETED
2025-10-29 | 2025-10-29 | 2025-11-06 | Kec 02 Barkat Ali | 28 | 3.1111 | TA418 | 46/10 | COMPLETED
2025-10-29 | 2025-10-16 | 2025-11-07 | M S Tofit | 89 | 3.8696 | TA418 | 33/0 | COMPLETED
2025-10-30 | 2025-10-29 | 2025-11-06 | Kec 02 Barkat Ali | 28 | 3.1111 | TA418 | 46/10 | COMPLETED
2025-10-30 | 2025-10-16 | 2025-11-07 | M S Tofit | 89 | 3.8696 | TA418 | 33/0 | COMPLETED
2025-10-31 | 2025-10-29 | 2025-11-06 | Kec 02 Barkat Ali | 28 | 3.1111 | TA418 | 46/10 | COMPLETED
2025-10-31 | 2025-10-16 | 2025-11-07 | M S Tofit | 89 | 3.8696 | TA418 | 33/0 | COMPLETED
2025-11-01 | 2025-10-29 | 2025-11-06 | Kec 02 Barkat Ali | 28 | 3.1111 | TA418 | 46/10 | COMPLETED
2025-11-01 | 2025-10-16 | 2025-11-07 | M S Tofit | 89 | 3.8696 | TA418 | 33/0 | COMPLETED
2025-11-02 | 2025-10-29 | 2025-11-06 | Kec 02 Barkat Ali | 28 | 3.1111 | TA418 | 46/10 | COMPLETED
2025-11-02 | 2025-10-16 | 2025-11-07 | M S Tofit | 89 | 3.8696 | TA418 | 33/0 | COMPLETED
2025-11-03 | 2025-10-29 | 2025-11-06 | Kec 02 Barkat Ali | 28 | 3.1111 | TA418 | 46/10 | COMPLETED
2025-11-03 | 2025-10-16 | 2025-11-07 | M S Tofit | 89 | 3.8696 | TA418 | 33/0 | COMPLETED
2025-11-04 | 2025-10-29 | 2025-11-06 | Kec 02 Barkat Ali | 28 | 3.1111 | TA418 | 46/10 | COMPLETED
2025-11-04 | 2025-11-04 | 2025-11-12 | Kec 02 Barkat Ali | 28 | 3.1111 | TA418 | 46/6 | COMPLETED
2025-11-04 | 2025-10-16 | 2025-11-07 | M S Tofit | 89 | 3.8696 | TA418 | 33/0 | COMPLETED
2025-11-05 | 2025-10-29 | 2025-11-06 | Kec 02 Barkat Ali | 28 | 3.1111 | TA418 | 46/10 | COMPLETED
2025-11-05 | 2025-11-04 | 2025-11-12 | Kec 02 Barkat Ali | 28 | 3.1111 | TA418 | 46/6 | COMPLETED
2025-11-05 | 2025-10-16 | 2025-11-07 | M S Tofit | 89 | 3.8696 | TA418 | 33/0 | COMPLETED
2025-11-06 | 2025-10-29 | 2025-11-06 | Kec 02 Barkat Ali | 28 | 3.1111 | TA418 | 46/10 | COMPLETED
2025-11-06 | 2025-11-04 | 2025-11-12 | Kec 02 Barkat Ali | 28 | 3.1111 | TA418 | 46/6 | COMPLETED
2025-11-06 | 2025-11-06 | 2025-11-13 | M S Mdpl | 28 | 3.5 | TA418 | 43/2 | COMPLETED
2025-11-06 | 2025-10-16 | 2025-11-07 | M S Tofit | 89 | 3.8696 | TA418 | 33/0 | COMPLETED
2025-11-07 | 2025-11-04 | 2025-11-12 | Kec 02 Barkat Ali | 28 | 3.1111 | TA418 | 46/6 | COMPLETED
2025-11-07 | 2025-11-06 | 2025-11-13 | M S Mdpl | 28 | 3.5 | TA418 | 43/2 | COMPLETED
2025-11-07 | 2025-10-16 | 2025-11-07 | M S Tofit | 89 | 3.8696 | TA418 | 33/0 | COMPLETED
2025-11-08 | 2025-11-04 | 2025-11-12 | Kec 02 Barkat Ali | 28 | 3.1111 | TA418 | 46/6 | COMPLETED
2025-11-08 | 2025-11-06 | 2025-11-13 | M S Mdpl | 28 | 3.5 | TA418 | 43/2 | COMPLETED
2025-11-09 | 2025-11-04 | 2025-11-12 | Kec 02 Barkat Ali | 28 | 3.1111 | TA418 | 46/6 | COMPLETED
2025-11-09 | 2025-11-06 | 2025-11-13 | M S Mdpl | 28 | 3.5 | TA418 | 43/2 | COMPLETED
2025-11-10 | 2025-11-04 | 2025-11-12 | Kec 02 Barkat Ali | 28 | 3.1111 | TA418 | 46/6 | COMPLETED
2025-11-10 | 2025-11-06 | 2025-11-13 | M S Mdpl | 28 | 3.5 | TA418 | 43/2 | COMPLETED
2025-11-11 | 2025-11-04 | 2025-11-12 | Kec 02 Barkat Ali | 28 | 3.1111 | TA418 | 46/6 | COMPLETED
2025-11-11 | 2025-11-06 | 2025-11-13 | M S Mdpl | 28 | 3.5 | TA418 | 43/2 | COMPLETED
2025-11-12 | 2025-11-04 | 2025-11-12 | Kec 02 Barkat Ali | 28 | 3.1111 | TA418 | 46/6 | COMPLETED
2025-11-12 | 2025-11-06 | 2025-11-13 | M S Mdpl | 28 | 3.5 | TA418 | 43/2 | COMPLETED
2025-11-13 | 2025-11-06 | 2025-11-13 | M S Mdpl | 28 | 3.5 | TA418 | 43/2 | COMPLETED
2024-01-06 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-01-07 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-01-08 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-01-09 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-01-10 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-01-11 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-01-12 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-01-13 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-01-14 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-01-15 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-01-16 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-01-17 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-01-18 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-01-19 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-01-20 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-01-21 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-01-22 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-01-23 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-01-24 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-01-25 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-01-26 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-01-27 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-01-28 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-01-29 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-01-30 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-01-31 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-01 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-02 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-03 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-04 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-05 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-06 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-07 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-08 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-09 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-10 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-11 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-12 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-13 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-14 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-15 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-16 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-17 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-18 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-19 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-20 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-21 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-22 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-23 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-24 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-25 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-26 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-27 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-28 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-02-29 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-01 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-02 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-03 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-04 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-05 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-06 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-07 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-08 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-09 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-10 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-11 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-12 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-13 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-14 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-15 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-16 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-17 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-18 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-19 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-20 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-21 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-22 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-23 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-24 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-25 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-26 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-27 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-28 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-29 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-30 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-03-31 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-01 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-02 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-03 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-04 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-05 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-06 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-07 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-08 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-09 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-10 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-11 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-12 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-13 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-14 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-15 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-16 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-17 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-18 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-19 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-20 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-21 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-22 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-23 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-24 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-25 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-26 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-27 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-28 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-29 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-04-30 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-01 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-02 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-03 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-04 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-05 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-06 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-07 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-08 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-09 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-10 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-11 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-12 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-13 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-14 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-15 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-16 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-17 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-18 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-19 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-20 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-21 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-22 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-23 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-24 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-25 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-26 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-27 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-28 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-29 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-30 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-05-31 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-01 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-02 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-03 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-04 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-05 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-06 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-07 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-08 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-09 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-10 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-11 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-12 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-13 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-14 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-15 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-16 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-17 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-18 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-19 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-20 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-21 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-22 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-23 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-24 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-25 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-26 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-27 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-28 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-29 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-06-30 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-01 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-02 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-03 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-04 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-05 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-06 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-07 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-08 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-09 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-10 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-11 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-12 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-13 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-14 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-15 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-16 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-17 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-18 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-19 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-20 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-21 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-22 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-23 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-24 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-25 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-26 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-27 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-28 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-29 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-30 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-07-31 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-01 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-02 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-03 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-04 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-05 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-06 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-07 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-08 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-09 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-10 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-11 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-12 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-13 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-14 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-15 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-16 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-17 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-18 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-19 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-20 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-21 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-22 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-23 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-24 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-25 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-26 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-27 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-28 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-29 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-30 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-08-31 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-01 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-02 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-03 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-04 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-05 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-06 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-07 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-08 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-09 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-10 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-11 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-12 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-13 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-14 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-15 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-16 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-17 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-18 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-19 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-20 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-21 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-22 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-23 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-24 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-25 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-26 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-27 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-28 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-29 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-09-30 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-01 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-02 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-03 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-04 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-05 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-06 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-07 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-08 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-09 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-10 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-11 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-12 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-13 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-14 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-15 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-16 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-17 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-18 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-19 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-20 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-21 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-22 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-23 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-24 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-25 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-26 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-27 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-28 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-29 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-30 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-10-31 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-01 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-02 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-03 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-04 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-05 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-06 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-07 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-08 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-09 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-10 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-11 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-12 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-13 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-14 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-15 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-16 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-17 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-18 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-19 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-19 | 2024-11-19 | 2024-12-10 | Punam Kumari | 36.16 | 1.6436 | TA419 | 19/2 | Completed
2024-11-20 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-20 | 2024-11-19 | 2024-12-10 | Punam Kumari | 36.16 | 1.6436 | TA419 | 19/2 | Completed
2024-11-21 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-21 | 2024-11-21 | 2024-11-28 | Madhu Sah | 35.602 | 4.4502 | TA419 | 6/8 | Completed
2024-11-21 | 2024-11-19 | 2024-12-10 | Punam Kumari | 36.16 | 1.6436 | TA419 | 19/2 | Completed
2024-11-21 | 2024-11-21 | 2024-11-27 | Radha Enterprises | 34.79 | 4.97 | TA419 | 20/1 | Completed
2024-11-22 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-22 | 2024-11-21 | 2024-11-28 | Madhu Sah | 35.602 | 4.4502 | TA419 | 6/8 | Completed
2024-11-22 | 2024-11-19 | 2024-12-10 | Punam Kumari | 36.16 | 1.6436 | TA419 | 19/2 | Completed
2024-11-22 | 2024-11-21 | 2024-11-27 | Radha Enterprises | 34.79 | 4.97 | TA419 | 20/1 | Completed
2024-11-23 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-23 | 2024-11-21 | 2024-11-28 | Madhu Sah | 35.602 | 4.4502 | TA419 | 6/8 | Completed
2024-11-23 | 2024-11-19 | 2024-12-10 | Punam Kumari | 36.16 | 1.6436 | TA419 | 19/2 | Completed
2024-11-23 | 2024-11-21 | 2024-11-27 | Radha Enterprises | 34.79 | 4.97 | TA419 | 20/1 | Completed
2024-11-24 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-24 | 2024-11-21 | 2024-11-28 | Madhu Sah | 35.602 | 4.4502 | TA419 | 6/8 | Completed
2024-11-24 | 2024-11-19 | 2024-12-10 | Punam Kumari | 36.16 | 1.6436 | TA419 | 19/2 | Completed
2024-11-24 | 2024-11-21 | 2024-11-27 | Radha Enterprises | 34.79 | 4.97 | TA419 | 20/1 | Completed
2024-11-25 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-25 | 2024-11-21 | 2024-11-28 | Madhu Sah | 35.602 | 4.4502 | TA419 | 6/8 | Completed
2024-11-25 | 2024-11-19 | 2024-12-10 | Punam Kumari | 36.16 | 1.6436 | TA419 | 19/2 | Completed
2024-11-25 | 2024-11-21 | 2024-11-27 | Radha Enterprises | 34.79 | 4.97 | TA419 | 20/1 | Completed
2024-11-26 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-26 | 2024-11-21 | 2024-11-28 | Madhu Sah | 35.602 | 4.4502 | TA419 | 6/8 | Completed
2024-11-26 | 2024-11-19 | 2024-12-10 | Punam Kumari | 36.16 | 1.6436 | TA419 | 19/2 | Completed
2024-11-26 | 2024-11-21 | 2024-11-27 | Radha Enterprises | 34.79 | 4.97 | TA419 | 20/1 | Completed
2024-11-27 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-27 | 2024-11-21 | 2024-11-28 | Madhu Sah | 35.602 | 4.4502 | TA419 | 6/8 | Completed
2024-11-27 | 2024-11-19 | 2024-12-10 | Punam Kumari | 36.16 | 1.6436 | TA419 | 19/2 | Completed
2024-11-27 | 2024-11-21 | 2024-11-27 | Radha Enterprises | 34.79 | 4.97 | TA419 | 20/1 | Completed
2024-11-28 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-28 | 2024-11-21 | 2024-11-28 | Madhu Sah | 35.602 | 4.4502 | TA419 | 6/8 | Completed
2024-11-28 | 2024-11-28 | 2024-12-05 | Madhu Sah | 36.16 | 4.52 | TA419 | 6/11 | Completed
2024-11-28 | 2024-11-19 | 2024-12-10 | Punam Kumari | 36.16 | 1.6436 | TA419 | 19/2 | Completed
2024-11-28 | 2024-11-28 | 2024-12-03 | Radha Enterprises | 34.79 | 5.7983 | TA419 | 20/2 | Completed
2024-11-29 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-29 | 2024-11-28 | 2024-12-05 | Madhu Sah | 36.16 | 4.52 | TA419 | 6/11 | Completed
2024-11-29 | 2024-11-19 | 2024-12-10 | Punam Kumari | 36.16 | 1.6436 | TA419 | 19/2 | Completed
2024-11-29 | 2024-11-28 | 2024-12-03 | Radha Enterprises | 34.79 | 5.7983 | TA419 | 20/2 | Completed
2024-11-30 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-11-30 | 2024-11-28 | 2024-12-05 | Madhu Sah | 36.16 | 4.52 | TA419 | 6/11 | Completed
2024-11-30 | 2024-11-19 | 2024-12-10 | Punam Kumari | 36.16 | 1.6436 | TA419 | 19/2 | Completed
2024-11-30 | 2024-11-28 | 2024-12-03 | Radha Enterprises | 34.79 | 5.7983 | TA419 | 20/2 | Completed
2024-12-01 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-01 | 2024-11-28 | 2024-12-05 | Madhu Sah | 36.16 | 4.52 | TA419 | 6/11 | Completed
2024-12-01 | 2024-11-19 | 2024-12-10 | Punam Kumari | 36.16 | 1.6436 | TA419 | 19/2 | Completed
2024-12-01 | 2024-11-28 | 2024-12-03 | Radha Enterprises | 34.79 | 5.7983 | TA419 | 20/2 | Completed
2024-12-02 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-02 | 2024-11-28 | 2024-12-05 | Madhu Sah | 36.16 | 4.52 | TA419 | 6/11 | Completed
2024-12-02 | 2024-11-19 | 2024-12-10 | Punam Kumari | 36.16 | 1.6436 | TA419 | 19/2 | Completed
2024-12-02 | 2024-11-28 | 2024-12-03 | Radha Enterprises | 34.79 | 5.7983 | TA419 | 20/2 | Completed
2024-12-03 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-03 | 2024-11-28 | 2024-12-05 | Madhu Sah | 36.16 | 4.52 | TA419 | 6/11 | Completed
2024-12-03 | 2024-11-19 | 2024-12-10 | Punam Kumari | 36.16 | 1.6436 | TA419 | 19/2 | Completed
2024-12-03 | 2024-11-28 | 2024-12-03 | Radha Enterprises | 34.79 | 5.7983 | TA419 | 20/2 | Completed
2024-12-04 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-04 | 2024-11-28 | 2024-12-05 | Madhu Sah | 36.16 | 4.52 | TA419 | 6/11 | Completed
2024-12-04 | 2024-11-19 | 2024-12-10 | Punam Kumari | 36.16 | 1.6436 | TA419 | 19/2 | Completed
2024-12-04 | 2024-12-04 | 2024-12-23 | Radha Enterprises | 37.931 | 1.8965 | TA419 | 0B/2 | Completed
2024-12-04 | 2024-12-04 | 2024-12-08 | Radha Enterprises | 35.602 | 7.1204 | TA419 | 22/2 | Completed
2024-12-05 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-05 | 2024-11-28 | 2024-12-05 | Madhu Sah | 36.16 | 4.52 | TA419 | 6/11 | Completed
2024-12-05 | 2024-11-19 | 2024-12-10 | Punam Kumari | 36.16 | 1.6436 | TA419 | 19/2 | Completed
2024-12-05 | 2024-12-04 | 2024-12-23 | Radha Enterprises | 37.931 | 1.8965 | TA419 | 0B/2 | Completed
2024-12-05 | 2024-12-04 | 2024-12-08 | Radha Enterprises | 35.602 | 7.1204 | TA419 | 22/2 | Completed
2024-12-06 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-06 | 2024-12-06 | 2024-12-11 | Madhu Sah | 37.138 | 6.1897 | TA419 | 6/3 | Completed
2024-12-06 | 2024-11-19 | 2024-12-10 | Punam Kumari | 36.16 | 1.6436 | TA419 | 19/2 | Completed
2024-12-06 | 2024-12-04 | 2024-12-23 | Radha Enterprises | 37.931 | 1.8965 | TA419 | 0B/2 | Completed
2024-12-06 | 2024-12-04 | 2024-12-08 | Radha Enterprises | 35.602 | 7.1204 | TA419 | 22/2 | Completed
2024-12-07 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-07 | 2024-12-06 | 2024-12-11 | Madhu Sah | 37.138 | 6.1897 | TA419 | 6/3 | Completed
2024-12-07 | 2024-11-19 | 2024-12-10 | Punam Kumari | 36.16 | 1.6436 | TA419 | 19/2 | Completed
2024-12-07 | 2024-12-04 | 2024-12-23 | Radha Enterprises | 37.931 | 1.8965 | TA419 | 0B/2 | Completed
2024-12-07 | 2024-12-04 | 2024-12-08 | Radha Enterprises | 35.602 | 7.1204 | TA419 | 22/2 | Completed
2024-12-08 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-08 | 2024-12-06 | 2024-12-11 | Madhu Sah | 37.138 | 6.1897 | TA419 | 6/3 | Completed
2024-12-08 | 2024-11-19 | 2024-12-10 | Punam Kumari | 36.16 | 1.6436 | TA419 | 19/2 | Completed
2024-12-08 | 2024-12-04 | 2024-12-23 | Radha Enterprises | 37.931 | 1.8965 | TA419 | 0B/2 | Completed
2024-12-08 | 2024-12-04 | 2024-12-08 | Radha Enterprises | 35.602 | 7.1204 | TA419 | 22/2 | Completed
2024-12-09 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-09 | 2024-12-06 | 2024-12-11 | Madhu Sah | 37.138 | 6.1897 | TA419 | 6/3 | Completed
2024-12-09 | 2024-11-19 | 2024-12-10 | Punam Kumari | 36.16 | 1.6436 | TA419 | 19/2 | Completed
2024-12-09 | 2024-12-04 | 2024-12-23 | Radha Enterprises | 37.931 | 1.8965 | TA419 | 0B/2 | Completed
2024-12-09 | 2024-12-09 | 2024-12-13 | Radha Enterprises | 35.602 | 7.1204 | TA419 | 22/3 | Completed
2024-12-10 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-10 | 2024-12-06 | 2024-12-11 | Madhu Sah | 37.138 | 6.1897 | TA419 | 6/3 | Completed
2024-12-10 | 2024-11-19 | 2024-12-10 | Punam Kumari | 36.16 | 1.6436 | TA419 | 19/2 | Completed
2024-12-10 | 2024-12-04 | 2024-12-23 | Radha Enterprises | 37.931 | 1.8965 | TA419 | 0B/2 | Completed
2024-12-10 | 2024-12-09 | 2024-12-13 | Radha Enterprises | 35.602 | 7.1204 | TA419 | 22/3 | Completed
2024-12-11 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-11 | 2024-12-06 | 2024-12-11 | Madhu Sah | 37.138 | 6.1897 | TA419 | 6/3 | Completed
2024-12-11 | 2024-12-04 | 2024-12-23 | Radha Enterprises | 37.931 | 1.8965 | TA419 | 0B/2 | Completed
2024-12-11 | 2024-12-09 | 2024-12-13 | Radha Enterprises | 35.602 | 7.1204 | TA419 | 22/3 | Completed
2024-12-12 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-12 | 2024-12-12 | 2024-12-17 | Madhu Sah | 37.931 | 6.3218 | TA419 | 6/2 | Completed
2024-12-12 | 2024-12-04 | 2024-12-23 | Radha Enterprises | 37.931 | 1.8965 | TA419 | 0B/2 | Completed
2024-12-12 | 2024-12-09 | 2024-12-13 | Radha Enterprises | 35.602 | 7.1204 | TA419 | 22/3 | Completed
2024-12-13 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-13 | 2024-12-12 | 2024-12-17 | Madhu Sah | 37.931 | 6.3218 | TA419 | 6/2 | Completed
2024-12-13 | 2024-12-04 | 2024-12-23 | Radha Enterprises | 37.931 | 1.8965 | TA419 | 0B/2 | Completed
2024-12-13 | 2024-12-09 | 2024-12-13 | Radha Enterprises | 35.602 | 7.1204 | TA419 | 22/3 | Completed
2024-12-14 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-14 | 2024-12-12 | 2024-12-17 | Madhu Sah | 37.931 | 6.3218 | TA419 | 6/2 | Completed
2024-12-14 | 2024-12-04 | 2024-12-23 | Radha Enterprises | 37.931 | 1.8965 | TA419 | 0B/2 | Completed
2024-12-14 | 2024-12-14 | 2024-12-17 | Radha Enterprises | 34.79 | 8.6975 | TA419 | 23/1 | Completed
2024-12-15 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-15 | 2024-12-12 | 2024-12-17 | Madhu Sah | 37.931 | 6.3218 | TA419 | 6/2 | Completed
2024-12-15 | 2024-12-04 | 2024-12-23 | Radha Enterprises | 37.931 | 1.8965 | TA419 | 0B/2 | Completed
2024-12-15 | 2024-12-14 | 2024-12-17 | Radha Enterprises | 34.79 | 8.6975 | TA419 | 23/1 | Completed
2024-12-16 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-16 | 2024-12-12 | 2024-12-17 | Madhu Sah | 37.931 | 6.3218 | TA419 | 6/2 | Completed
2024-12-16 | 2024-12-04 | 2024-12-23 | Radha Enterprises | 37.931 | 1.8965 | TA419 | 0B/2 | Completed
2024-12-16 | 2024-12-14 | 2024-12-17 | Radha Enterprises | 34.79 | 8.6975 | TA419 | 23/1 | Completed
2024-12-17 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-17 | 2024-12-12 | 2024-12-17 | Madhu Sah | 37.931 | 6.3218 | TA419 | 6/2 | Completed
2024-12-17 | 2024-12-17 | 2024-12-23 | Madhu Sah | 34.79 | 4.97 | TA419 | 6/10 | Completed
2024-12-17 | 2024-12-04 | 2024-12-23 | Radha Enterprises | 37.931 | 1.8965 | TA419 | 0B/2 | Completed
2024-12-17 | 2024-12-14 | 2024-12-17 | Radha Enterprises | 34.79 | 8.6975 | TA419 | 23/1 | Completed
2024-12-18 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-18 | 2024-12-17 | 2024-12-23 | Madhu Sah | 34.79 | 4.97 | TA419 | 6/10 | Completed
2024-12-18 | 2024-12-04 | 2024-12-23 | Radha Enterprises | 37.931 | 1.8965 | TA419 | 0B/2 | Completed
2024-12-18 | 2024-12-18 | 2024-12-23 | Radha Enterprises | 36.16 | 6.0267 | TA419 | 23/2 | Completed
2024-12-19 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-19 | 2024-12-17 | 2024-12-23 | Madhu Sah | 34.79 | 4.97 | TA419 | 6/10 | Completed
2024-12-19 | 2024-12-04 | 2024-12-23 | Radha Enterprises | 37.931 | 1.8965 | TA419 | 0B/2 | Completed
2024-12-19 | 2024-12-18 | 2024-12-23 | Radha Enterprises | 36.16 | 6.0267 | TA419 | 23/2 | Completed
2024-12-20 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-20 | 2024-12-17 | 2024-12-23 | Madhu Sah | 34.79 | 4.97 | TA419 | 6/10 | Completed
2024-12-20 | 2024-12-04 | 2024-12-23 | Radha Enterprises | 37.931 | 1.8965 | TA419 | 0B/2 | Completed
2024-12-20 | 2024-12-18 | 2024-12-23 | Radha Enterprises | 36.16 | 6.0267 | TA419 | 23/2 | Completed
2024-12-21 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-21 | 2024-12-17 | 2024-12-23 | Madhu Sah | 34.79 | 4.97 | TA419 | 6/10 | Completed
2024-12-21 | 2024-12-04 | 2024-12-23 | Radha Enterprises | 37.931 | 1.8965 | TA419 | 0B/2 | Completed
2024-12-21 | 2024-12-18 | 2024-12-23 | Radha Enterprises | 36.16 | 6.0267 | TA419 | 23/2 | Completed
2024-12-22 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-22 | 2024-12-17 | 2024-12-23 | Madhu Sah | 34.79 | 4.97 | TA419 | 6/10 | Completed
2024-12-22 | 2024-12-22 | 2024-12-31 | Madhu Sah | 37.931 | 3.7931 | TA419 | 6/12 | Completed
2024-12-22 | 2024-12-04 | 2024-12-23 | Radha Enterprises | 37.931 | 1.8965 | TA419 | 0B/2 | Completed
2024-12-22 | 2024-12-18 | 2024-12-23 | Radha Enterprises | 36.16 | 6.0267 | TA419 | 23/2 | Completed
2024-12-22 | 2024-12-22 | 2024-12-31 | Radha Enterprises | 43.804 | 4.3804 | TA419 | 0D/1 | Completed
2024-12-22 | 2024-12-22 | 2024-12-31 | Radha Enterprises | 59.501 | 5.9501 | TA419 | 23/0 | Completed
2024-12-23 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-23 | 2024-12-17 | 2024-12-23 | Madhu Sah | 34.79 | 4.97 | TA419 | 6/10 | Completed
2024-12-23 | 2024-12-22 | 2024-12-31 | Madhu Sah | 37.931 | 3.7931 | TA419 | 6/12 | Completed
2024-12-23 | 2024-12-04 | 2024-12-23 | Radha Enterprises | 37.931 | 1.8965 | TA419 | 0B/2 | Completed
2024-12-23 | 2024-12-18 | 2024-12-23 | Radha Enterprises | 36.16 | 6.0267 | TA419 | 23/2 | Completed
2024-12-23 | 2024-12-22 | 2024-12-31 | Radha Enterprises | 43.804 | 4.3804 | TA419 | 0D/1 | Completed
2024-12-23 | 2024-12-22 | 2024-12-31 | Radha Enterprises | 59.501 | 5.9501 | TA419 | 23/0 | Completed
2024-12-24 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-24 | 2024-12-22 | 2024-12-31 | Madhu Sah | 37.931 | 3.7931 | TA419 | 6/12 | Completed
2024-12-24 | 2024-12-22 | 2024-12-31 | Radha Enterprises | 43.804 | 4.3804 | TA419 | 0D/1 | Completed
2024-12-24 | 2024-12-22 | 2024-12-31 | Radha Enterprises | 59.501 | 5.9501 | TA419 | 23/0 | Completed
2024-12-25 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-25 | 2024-12-22 | 2024-12-31 | Madhu Sah | 37.931 | 3.7931 | TA419 | 6/12 | Completed
2024-12-25 | 2024-12-22 | 2024-12-31 | Radha Enterprises | 43.804 | 4.3804 | TA419 | 0D/1 | Completed
2024-12-25 | 2024-12-22 | 2024-12-31 | Radha Enterprises | 59.501 | 5.9501 | TA419 | 23/0 | Completed
2024-12-26 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-26 | 2024-12-22 | 2024-12-31 | Madhu Sah | 37.931 | 3.7931 | TA419 | 6/12 | Completed
2024-12-26 | 2024-12-22 | 2024-12-31 | Radha Enterprises | 43.804 | 4.3804 | TA419 | 0D/1 | Completed
2024-12-26 | 2024-12-22 | 2024-12-31 | Radha Enterprises | 59.501 | 5.9501 | TA419 | 23/0 | Completed
2024-12-27 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-27 | 2024-12-22 | 2024-12-31 | Madhu Sah | 37.931 | 3.7931 | TA419 | 6/12 | Completed
2024-12-27 | 2024-12-22 | 2024-12-31 | Radha Enterprises | 43.804 | 4.3804 | TA419 | 0D/1 | Completed
2024-12-27 | 2024-12-22 | 2024-12-31 | Radha Enterprises | 59.501 | 5.9501 | TA419 | 23/0 | Completed
2024-12-28 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-28 | 2024-12-22 | 2024-12-31 | Madhu Sah | 37.931 | 3.7931 | TA419 | 6/12 | Completed
2024-12-28 | 2024-12-22 | 2024-12-31 | Radha Enterprises | 43.804 | 4.3804 | TA419 | 0D/1 | Completed
2024-12-28 | 2024-12-22 | 2024-12-31 | Radha Enterprises | 59.501 | 5.9501 | TA419 | 23/0 | Completed
2024-12-29 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-29 | 2024-12-22 | 2024-12-31 | Madhu Sah | 37.931 | 3.7931 | TA419 | 6/12 | Completed
2024-12-29 | 2024-12-22 | 2024-12-31 | Radha Enterprises | 43.804 | 4.3804 | TA419 | 0D/1 | Completed
2024-12-29 | 2024-12-22 | 2024-12-31 | Radha Enterprises | 59.501 | 5.9501 | TA419 | 23/0 | Completed
2024-12-30 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-30 | 2024-12-22 | 2024-12-31 | Madhu Sah | 37.931 | 3.7931 | TA419 | 6/12 | Completed
2024-12-30 | 2024-12-22 | 2024-12-31 | Radha Enterprises | 43.804 | 4.3804 | TA419 | 0D/1 | Completed
2024-12-30 | 2024-12-22 | 2024-12-31 | Radha Enterprises | 59.501 | 5.9501 | TA419 | 23/0 | Completed
2024-12-31 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-31 | 2024-12-22 | 2024-12-31 | Madhu Sah | 37.931 | 3.7931 | TA419 | 6/12 | Completed
2024-12-31 | 2024-12-22 | 2024-12-31 | Radha Enterprises | 43.804 | 4.3804 | TA419 | 0D/1 | Completed
2024-12-31 | 2024-12-22 | 2024-12-31 | Radha Enterprises | 59.501 | 5.9501 | TA419 | 23/0 | Completed
2025-01-01 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2025-01-02 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2025-01-03 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2025-01-03 | 2025-01-03 | 2025-01-09 | Radha Enterprises | 34.79 | 4.97 | TA419 | 24/1 | Completed
2025-01-04 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2025-01-04 | 2025-01-03 | 2025-01-09 | Radha Enterprises | 34.79 | 4.97 | TA419 | 24/1 | Completed
2025-01-04 | 2025-01-04 | 2025-01-10 | Radha Enterprises | 37.931 | 5.4187 | TA419 | 0E/2 | Completed
2025-01-05 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2025-01-05 | 2025-01-03 | 2025-01-09 | Radha Enterprises | 34.79 | 4.97 | TA419 | 24/1 | Completed
2025-01-05 | 2025-01-04 | 2025-01-10 | Radha Enterprises | 37.931 | 5.4187 | TA419 | 0E/2 | Completed
2025-01-06 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2025-01-06 | 2025-01-03 | 2025-01-09 | Radha Enterprises | 34.79 | 4.97 | TA419 | 24/1 | Completed
2025-01-06 | 2025-01-04 | 2025-01-10 | Radha Enterprises | 37.931 | 5.4187 | TA419 | 0E/2 | Completed
2025-01-07 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2025-01-07 | 2025-01-03 | 2025-01-09 | Radha Enterprises | 34.79 | 4.97 | TA419 | 24/1 | Completed
2025-01-07 | 2025-01-04 | 2025-01-10 | Radha Enterprises | 37.931 | 5.4187 | TA419 | 0E/2 | Completed
2025-01-08 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2025-01-08 | 2025-01-03 | 2025-01-09 | Radha Enterprises | 34.79 | 4.97 | TA419 | 24/1 | Completed
2025-01-08 | 2025-01-04 | 2025-01-10 | Radha Enterprises | 37.931 | 5.4187 | TA419 | 0E/2 | Completed
2025-01-09 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2025-01-09 | 2025-01-03 | 2025-01-09 | Radha Enterprises | 34.79 | 4.97 | TA419 | 24/1 | Completed
2025-01-09 | 2025-01-04 | 2025-01-10 | Radha Enterprises | 37.931 | 5.4187 | TA419 | 0E/2 | Completed
2025-01-10 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2025-01-10 | 2025-01-04 | 2025-01-10 | Radha Enterprises | 37.931 | 5.4187 | TA419 | 0E/2 | Completed
2025-01-11 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2025-01-11 | 2025-01-11 | 2025-01-16 | Madhu Sah | 36.16 | 6.0267 | TA419 | 6/1 | Completed
2025-01-11 | 2025-01-11 | 2025-01-18 | Radha Enterprises | 37.931 | 4.7414 | TA419 | 0E/1 | Completed
2025-01-11 | 2025-01-11 | 2025-01-17 | Radha Enterprises | 36.16 | 5.1657 | TA419 | 19/4 | Completed
2025-01-12 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2025-01-12 | 2025-01-11 | 2025-01-16 | Madhu Sah | 36.16 | 6.0267 | TA419 | 6/1 | Completed
2025-01-12 | 2025-01-12 | 2025-01-19 | Pinki Devi | 37.138 | 4.6422 | TA419 | 0D/2 | Completed
2025-01-12 | 2025-01-11 | 2025-01-18 | Radha Enterprises | 37.931 | 4.7414 | TA419 | 0E/1 | Completed
2025-01-12 | 2025-01-11 | 2025-01-17 | Radha Enterprises | 36.16 | 5.1657 | TA419 | 19/4 | Completed
2025-01-13 | 2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2025-01-13 | 2025-01-11 | 2025-01-16 | Madhu Sah | 36.16 | 6.0267 | TA419 | 6/1 | Completed
2025-01-13 | 2025-01-12 | 2025-01-19 | Pinki Devi | 37.138 | 4.6422 | TA419 | 0D/2 | Completed
2025-01-13 | 2025-01-11 | 2025-01-18 | Radha Enterprises | 37.931 | 4.7414 | TA419 | 0E/1 | Completed
2025-01-13 | 2025-01-11 | 2025-01-17 | Radha Enterprises | 36.16 | 5.1657 | TA419 | 19/4 | Completed
2025-01-14 | 2025-01-11 | 2025-01-16 | Madhu Sah | 36.16 | 6.0267 | TA419 | 6/1 | Completed
2025-01-14 | 2025-01-12 | 2025-01-19 | Pinki Devi | 37.138 | 4.6422 | TA419 | 0D/2 | Completed
2025-01-14 | 2025-01-11 | 2025-01-18 | Radha Enterprises | 37.931 | 4.7414 | TA419 | 0E/1 | Completed
2025-01-14 | 2025-01-11 | 2025-01-17 | Radha Enterprises | 36.16 | 5.1657 | TA419 | 19/4 | Completed
2025-01-15 | 2025-01-11 | 2025-01-16 | Madhu Sah | 36.16 | 6.0267 | TA419 | 6/1 | Completed
2025-01-15 | 2025-01-12 | 2025-01-19 | Pinki Devi | 37.138 | 4.6422 | TA419 | 0D/2 | Completed
2025-01-15 | 2025-01-11 | 2025-01-18 | Radha Enterprises | 37.931 | 4.7414 | TA419 | 0E/1 | Completed
2025-01-15 | 2025-01-11 | 2025-01-17 | Radha Enterprises | 36.16 | 5.1657 | TA419 | 19/4 | Completed
2025-01-16 | 2025-01-11 | 2025-01-16 | Madhu Sah | 36.16 | 6.0267 | TA419 | 6/1 | Completed
2025-01-16 | 2025-01-12 | 2025-01-19 | Pinki Devi | 37.138 | 4.6422 | TA419 | 0D/2 | Completed
2025-01-16 | 2025-01-11 | 2025-01-18 | Radha Enterprises | 37.931 | 4.7414 | TA419 | 0E/1 | Completed
2025-01-16 | 2025-01-11 | 2025-01-17 | Radha Enterprises | 36.16 | 5.1657 | TA419 | 19/4 | Completed
2025-01-17 | 2025-01-17 | 2025-01-21 | Madhu Sah | 43.804 | 8.7608 | TA419 | 6/5 | Completed
2025-01-17 | 2025-01-12 | 2025-01-19 | Pinki Devi | 37.138 | 4.6422 | TA419 | 0D/2 | Completed
2025-01-17 | 2025-01-11 | 2025-01-18 | Radha Enterprises | 37.931 | 4.7414 | TA419 | 0E/1 | Completed
2025-01-17 | 2025-01-11 | 2025-01-17 | Radha Enterprises | 36.16 | 5.1657 | TA419 | 19/4 | Completed
2025-01-18 | 2025-01-17 | 2025-01-21 | Madhu Sah | 43.804 | 8.7608 | TA419 | 6/5 | Completed
2025-01-18 | 2025-01-12 | 2025-01-19 | Pinki Devi | 37.138 | 4.6422 | TA419 | 0D/2 | Completed
2025-01-18 | 2025-01-11 | 2025-01-18 | Radha Enterprises | 37.931 | 4.7414 | TA419 | 0E/1 | Completed
2025-01-18 | 2025-01-18 | 2025-01-22 | Radha Enterprises | 37.931 | 7.5862 | TA419 | 19/3 | Completed
2025-01-19 | 2025-01-17 | 2025-01-21 | Madhu Sah | 43.804 | 8.7608 | TA419 | 6/5 | Completed
2025-01-19 | 2025-01-12 | 2025-01-19 | Pinki Devi | 37.138 | 4.6422 | TA419 | 0D/2 | Completed
2025-01-19 | 2025-01-18 | 2025-01-22 | Radha Enterprises | 37.931 | 7.5862 | TA419 | 19/3 | Completed
2025-01-19 | 2025-01-19 | 2025-01-27 | Radha Enterprises | 43.804 | 4.8671 | TA419 | 0B/3 | Completed
2025-01-20 | 2025-01-17 | 2025-01-21 | Madhu Sah | 43.804 | 8.7608 | TA419 | 6/5 | Completed
2025-01-20 | 2025-01-20 | 2025-01-27 | Madhu Sah | 36.16 | 4.52 | TA419 | 6/4 | Completed
2025-01-20 | 2025-01-20 | 2025-01-28 | Pinki Devi | 37.931 | 4.2146 | TA419 | 0C/1 | Completed
2025-01-20 | 2025-01-18 | 2025-01-22 | Radha Enterprises | 37.931 | 7.5862 | TA419 | 19/3 | Completed
2025-01-20 | 2025-01-19 | 2025-01-27 | Radha Enterprises | 43.804 | 4.8671 | TA419 | 0B/3 | Completed
2025-01-21 | 2025-01-17 | 2025-01-21 | Madhu Sah | 43.804 | 8.7608 | TA419 | 6/5 | Completed
2025-01-21 | 2025-01-20 | 2025-01-27 | Madhu Sah | 36.16 | 4.52 | TA419 | 6/4 | Completed
2025-01-21 | 2025-01-20 | 2025-01-28 | Pinki Devi | 37.931 | 4.2146 | TA419 | 0C/1 | Completed
2025-01-21 | 2025-01-18 | 2025-01-22 | Radha Enterprises | 37.931 | 7.5862 | TA419 | 19/3 | Completed
2025-01-21 | 2025-01-19 | 2025-01-27 | Radha Enterprises | 43.804 | 4.8671 | TA419 | 0B/3 | Completed
2025-01-22 | 2025-01-20 | 2025-01-27 | Madhu Sah | 36.16 | 4.52 | TA419 | 6/4 | Completed
2025-01-22 | 2025-01-20 | 2025-01-28 | Pinki Devi | 37.931 | 4.2146 | TA419 | 0C/1 | Completed
2025-01-22 | 2025-01-18 | 2025-01-22 | Radha Enterprises | 37.931 | 7.5862 | TA419 | 19/3 | Completed
2025-01-22 | 2025-01-19 | 2025-01-27 | Radha Enterprises | 43.804 | 4.8671 | TA419 | 0B/3 | Completed
2025-01-23 | 2025-01-20 | 2025-01-27 | Madhu Sah | 36.16 | 4.52 | TA419 | 6/4 | Completed
2025-01-23 | 2025-01-20 | 2025-01-28 | Pinki Devi | 37.931 | 4.2146 | TA419 | 0C/1 | Completed
2025-01-23 | 2025-01-19 | 2025-01-27 | Radha Enterprises | 43.804 | 4.8671 | TA419 | 0B/3 | Completed
2025-01-23 | 2025-01-23 | 2025-01-27 | Radha Enterprises | 35.602 | 7.1204 | TA419 | 19/1 | Completed
2025-01-24 | 2025-01-20 | 2025-01-27 | Madhu Sah | 36.16 | 4.52 | TA419 | 6/4 | Completed
2025-01-24 | 2025-01-20 | 2025-01-28 | Pinki Devi | 37.931 | 4.2146 | TA419 | 0C/1 | Completed
2025-01-24 | 2025-01-19 | 2025-01-27 | Radha Enterprises | 43.804 | 4.8671 | TA419 | 0B/3 | Completed
2025-01-24 | 2025-01-23 | 2025-01-27 | Radha Enterprises | 35.602 | 7.1204 | TA419 | 19/1 | Completed
2025-01-25 | 2025-01-20 | 2025-01-27 | Madhu Sah | 36.16 | 4.52 | TA419 | 6/4 | Completed
2025-01-25 | 2025-01-20 | 2025-01-28 | Pinki Devi | 37.931 | 4.2146 | TA419 | 0C/1 | Completed
2025-01-25 | 2025-01-19 | 2025-01-27 | Radha Enterprises | 43.804 | 4.8671 | TA419 | 0B/3 | Completed
2025-01-25 | 2025-01-23 | 2025-01-27 | Radha Enterprises | 35.602 | 7.1204 | TA419 | 19/1 | Completed
2025-01-26 | 2025-01-20 | 2025-01-27 | Madhu Sah | 36.16 | 4.52 | TA419 | 6/4 | Completed
2025-01-26 | 2025-01-20 | 2025-01-28 | Pinki Devi | 37.931 | 4.2146 | TA419 | 0C/1 | Completed
2025-01-26 | 2025-01-19 | 2025-01-27 | Radha Enterprises | 43.804 | 4.8671 | TA419 | 0B/3 | Completed
2025-01-26 | 2025-01-23 | 2025-01-27 | Radha Enterprises | 35.602 | 7.1204 | TA419 | 19/1 | Completed
2025-01-27 | 2025-01-20 | 2025-01-27 | Madhu Sah | 36.16 | 4.52 | TA419 | 6/4 | Completed
2025-01-27 | 2025-01-27 | 2025-02-01 | Madhu Sah | 36.16 | 6.0267 | TA419 | 6/7 | Completed
2025-01-27 | 2025-01-20 | 2025-01-28 | Pinki Devi | 37.931 | 4.2146 | TA419 | 0C/1 | Completed
2025-01-27 | 2025-01-19 | 2025-01-27 | Radha Enterprises | 43.804 | 4.8671 | TA419 | 0B/3 | Completed
2025-01-27 | 2025-01-23 | 2025-01-27 | Radha Enterprises | 35.602 | 7.1204 | TA419 | 19/1 | Completed
2025-01-27 | 2025-01-27 | 2025-02-12 | Radha Enterprises | 87.021 | 5.1189 | TA419 | 0A/0 (CT) | Completed
2025-01-27 | 2025-01-27 | 2025-02-05 | Radha Enterprises | 62.444 | 6.2444 | TA419 | 19/0 | Completed
2025-01-28 | 2025-01-27 | 2025-02-01 | Madhu Sah | 36.16 | 6.0267 | TA419 | 6/7 | Completed
2025-01-28 | 2025-01-20 | 2025-01-28 | Pinki Devi | 37.931 | 4.2146 | TA419 | 0C/1 | Completed
2025-01-28 | 2025-01-28 | 2025-02-08 | Pinki Devi | 45.697 | 3.8081 | TA419 | 0D/3 | Completed
2025-01-28 | 2025-01-27 | 2025-02-12 | Radha Enterprises | 87.021 | 5.1189 | TA419 | 0A/0 (CT) | Completed
2025-01-28 | 2025-01-27 | 2025-02-05 | Radha Enterprises | 62.444 | 6.2444 | TA419 | 19/0 | Completed
2025-01-29 | 2025-01-27 | 2025-02-01 | Madhu Sah | 36.16 | 6.0267 | TA419 | 6/7 | Completed
2025-01-29 | 2025-01-28 | 2025-02-08 | Pinki Devi | 45.697 | 3.8081 | TA419 | 0D/3 | Completed
2025-01-29 | 2025-01-27 | 2025-02-12 | Radha Enterprises | 87.021 | 5.1189 | TA419 | 0A/0 (CT) | Completed
2025-01-29 | 2025-01-27 | 2025-02-05 | Radha Enterprises | 62.444 | 6.2444 | TA419 | 19/0 | Completed
2025-01-30 | 2025-01-27 | 2025-02-01 | Madhu Sah | 36.16 | 6.0267 | TA419 | 6/7 | Completed
2025-01-30 | 2025-01-28 | 2025-02-08 | Pinki Devi | 45.697 | 3.8081 | TA419 | 0D/3 | Completed
2025-01-30 | 2025-01-27 | 2025-02-12 | Radha Enterprises | 87.021 | 5.1189 | TA419 | 0A/0 (CT) | Completed
2025-01-30 | 2025-01-27 | 2025-02-05 | Radha Enterprises | 62.444 | 6.2444 | TA419 | 19/0 | Completed
2025-01-31 | 2025-01-27 | 2025-02-01 | Madhu Sah | 36.16 | 6.0267 | TA419 | 6/7 | Completed
2025-01-31 | 2025-01-28 | 2025-02-08 | Pinki Devi | 45.697 | 3.8081 | TA419 | 0D/3 | Completed
2025-01-31 | 2025-01-31 | 2025-02-09 | Poonam Kumari | 37.138 | 3.7138 | TA419 | 17/2 | Completed
2025-01-31 | 2025-01-27 | 2025-02-12 | Radha Enterprises | 87.021 | 5.1189 | TA419 | 0A/0 (CT) | Completed
2025-01-31 | 2025-01-27 | 2025-02-05 | Radha Enterprises | 62.444 | 6.2444 | TA419 | 19/0 | Completed
2025-02-01 | 2025-01-27 | 2025-02-01 | Madhu Sah | 36.16 | 6.0267 | TA419 | 6/7 | Completed
2025-02-01 | 2025-01-28 | 2025-02-08 | Pinki Devi | 45.697 | 3.8081 | TA419 | 0D/3 | Completed
2025-02-01 | 2025-01-31 | 2025-02-09 | Poonam Kumari | 37.138 | 3.7138 | TA419 | 17/2 | Completed
2025-02-01 | 2025-01-27 | 2025-02-12 | Radha Enterprises | 87.021 | 5.1189 | TA419 | 0A/0 (CT) | Completed
2025-02-01 | 2025-01-27 | 2025-02-05 | Radha Enterprises | 62.444 | 6.2444 | TA419 | 19/0 | Completed
2025-02-02 | 2025-02-02 | 2025-02-11 | Madhu Sah | 62.444 | 6.2444 | TA419 | 6/0 | Completed
2025-02-02 | 2025-01-28 | 2025-02-08 | Pinki Devi | 45.697 | 3.8081 | TA419 | 0D/3 | Completed
2025-02-02 | 2025-01-31 | 2025-02-09 | Poonam Kumari | 37.138 | 3.7138 | TA419 | 17/2 | Completed
2025-02-02 | 2025-01-27 | 2025-02-12 | Radha Enterprises | 87.021 | 5.1189 | TA419 | 0A/0 (CT) | Completed
2025-02-02 | 2025-01-27 | 2025-02-05 | Radha Enterprises | 62.444 | 6.2444 | TA419 | 19/0 | Completed
2025-02-03 | 2025-02-02 | 2025-02-11 | Madhu Sah | 62.444 | 6.2444 | TA419 | 6/0 | Completed
2025-02-03 | 2025-01-28 | 2025-02-08 | Pinki Devi | 45.697 | 3.8081 | TA419 | 0D/3 | Completed
2025-02-03 | 2025-01-31 | 2025-02-09 | Poonam Kumari | 37.138 | 3.7138 | TA419 | 17/2 | Completed
2025-02-03 | 2025-01-27 | 2025-02-12 | Radha Enterprises | 87.021 | 5.1189 | TA419 | 0A/0 (CT) | Completed
2025-02-03 | 2025-01-27 | 2025-02-05 | Radha Enterprises | 62.444 | 6.2444 | TA419 | 19/0 | Completed
2025-02-03 | 2025-02-03 | 2025-02-12 | Radha Enterprises | 37.138 | 3.7138 | TA419 | 19/5 | Completed
2025-02-04 | 2025-02-02 | 2025-02-11 | Madhu Sah | 62.444 | 6.2444 | TA419 | 6/0 | Completed
2025-02-04 | 2025-01-28 | 2025-02-08 | Pinki Devi | 45.697 | 3.8081 | TA419 | 0D/3 | Completed
2025-02-04 | 2025-01-31 | 2025-02-09 | Poonam Kumari | 37.138 | 3.7138 | TA419 | 17/2 | Completed
2025-02-04 | 2025-01-27 | 2025-02-12 | Radha Enterprises | 87.021 | 5.1189 | TA419 | 0A/0 (CT) | Completed
2025-02-04 | 2025-01-27 | 2025-02-05 | Radha Enterprises | 62.444 | 6.2444 | TA419 | 19/0 | Completed
2025-02-04 | 2025-02-03 | 2025-02-12 | Radha Enterprises | 37.138 | 3.7138 | TA419 | 19/5 | Completed
2025-02-05 | 2025-02-02 | 2025-02-11 | Madhu Sah | 62.444 | 6.2444 | TA419 | 6/0 | Completed
2025-02-05 | 2025-01-28 | 2025-02-08 | Pinki Devi | 45.697 | 3.8081 | TA419 | 0D/3 | Completed
2025-02-05 | 2025-01-31 | 2025-02-09 | Poonam Kumari | 37.138 | 3.7138 | TA419 | 17/2 | Completed
2025-02-05 | 2025-01-27 | 2025-02-12 | Radha Enterprises | 87.021 | 5.1189 | TA419 | 0A/0 (CT) | Completed
2025-02-05 | 2025-01-27 | 2025-02-05 | Radha Enterprises | 62.444 | 6.2444 | TA419 | 19/0 | Completed
2025-02-05 | 2025-02-03 | 2025-02-12 | Radha Enterprises | 37.138 | 3.7138 | TA419 | 19/5 | Completed
2025-02-06 | 2025-02-02 | 2025-02-11 | Madhu Sah | 62.444 | 6.2444 | TA419 | 6/0 | Completed
2025-02-06 | 2025-01-28 | 2025-02-08 | Pinki Devi | 45.697 | 3.8081 | TA419 | 0D/3 | Completed
2025-02-06 | 2025-01-31 | 2025-02-09 | Poonam Kumari | 37.138 | 3.7138 | TA419 | 17/2 | Completed
2025-02-06 | 2025-01-27 | 2025-02-12 | Radha Enterprises | 87.021 | 5.1189 | TA419 | 0A/0 (CT) | Completed
2025-02-06 | 2025-02-03 | 2025-02-12 | Radha Enterprises | 37.138 | 3.7138 | TA419 | 19/5 | Completed
2025-02-07 | 2025-02-02 | 2025-02-11 | Madhu Sah | 62.444 | 6.2444 | TA419 | 6/0 | Completed
2025-02-07 | 2025-01-28 | 2025-02-08 | Pinki Devi | 45.697 | 3.8081 | TA419 | 0D/3 | Completed
2025-02-07 | 2025-01-31 | 2025-02-09 | Poonam Kumari | 37.138 | 3.7138 | TA419 | 17/2 | Completed
2025-02-07 | 2025-01-27 | 2025-02-12 | Radha Enterprises | 87.021 | 5.1189 | TA419 | 0A/0 (CT) | Completed
2025-02-07 | 2025-02-03 | 2025-02-12 | Radha Enterprises | 37.138 | 3.7138 | TA419 | 19/5 | Completed
2025-02-07 | 2025-02-07 | 2025-02-20 | Radha Enterprises 1 | 65.872 | 4.7051 | TA419 | 20/0 | completed
2025-02-07 | 2025-02-07 | 2025-02-27 | Radha Enterprises 2 | 66.776 | 3.1798 | TA419 | 0D/5 | Completed
2025-02-08 | 2025-02-02 | 2025-02-11 | Madhu Sah | 62.444 | 6.2444 | TA419 | 6/0 | Completed
2025-02-08 | 2025-01-28 | 2025-02-08 | Pinki Devi | 45.697 | 3.8081 | TA419 | 0D/3 | Completed
2025-02-08 | 2025-02-08 | 2025-02-15 | Pinki Devi | 36.16 | 4.52 | TA419 | 0D/4 | Completed
2025-02-08 | 2025-01-31 | 2025-02-09 | Poonam Kumari | 37.138 | 3.7138 | TA419 | 17/2 | Completed
2025-02-08 | 2025-02-08 | 2025-02-14 | Poonam Kumari | 34.79 | 4.97 | TA419 | 17/1 | Completed
2025-02-08 | 2025-01-27 | 2025-02-12 | Radha Enterprises | 87.021 | 5.1189 | TA419 | 0A/0 (CT) | Completed
2025-02-08 | 2025-02-03 | 2025-02-12 | Radha Enterprises | 37.138 | 3.7138 | TA419 | 19/5 | Completed
2025-02-08 | 2025-02-07 | 2025-02-20 | Radha Enterprises 1 | 65.872 | 4.7051 | TA419 | 20/0 | completed
2025-02-08 | 2025-02-07 | 2025-02-27 | Radha Enterprises 2 | 66.776 | 3.1798 | TA419 | 0D/5 | Completed
2025-02-09 | 2025-02-02 | 2025-02-11 | Madhu Sah | 62.444 | 6.2444 | TA419 | 6/0 | Completed
2025-02-09 | 2025-02-09 | 2025-02-18 | Madhu Sah | 43.804 | 4.3804 | TA419 | 5/4 | completed
2025-02-09 | 2025-02-08 | 2025-02-15 | Pinki Devi | 36.16 | 4.52 | TA419 | 0D/4 | Completed
2025-02-09 | 2025-01-31 | 2025-02-09 | Poonam Kumari | 37.138 | 3.7138 | TA419 | 17/2 | Completed
2025-02-09 | 2025-02-08 | 2025-02-14 | Poonam Kumari | 34.79 | 4.97 | TA419 | 17/1 | Completed
2025-02-09 | 2025-01-27 | 2025-02-12 | Radha Enterprises | 87.021 | 5.1189 | TA419 | 0A/0 (CT) | Completed
2025-02-09 | 2025-02-03 | 2025-02-12 | Radha Enterprises | 37.138 | 3.7138 | TA419 | 19/5 | Completed
2025-02-09 | 2025-02-07 | 2025-02-20 | Radha Enterprises 1 | 65.872 | 4.7051 | TA419 | 20/0 | completed
2025-02-09 | 2025-02-07 | 2025-02-27 | Radha Enterprises 2 | 66.776 | 3.1798 | TA419 | 0D/5 | Completed
2025-02-10 | 2025-02-02 | 2025-02-11 | Madhu Sah | 62.444 | 6.2444 | TA419 | 6/0 | Completed
2025-02-10 | 2025-02-09 | 2025-02-18 | Madhu Sah | 43.804 | 4.3804 | TA419 | 5/4 | completed
2025-02-10 | 2025-02-08 | 2025-02-15 | Pinki Devi | 36.16 | 4.52 | TA419 | 0D/4 | Completed
2025-02-10 | 2025-02-08 | 2025-02-14 | Poonam Kumari | 34.79 | 4.97 | TA419 | 17/1 | Completed
2025-02-10 | 2025-01-27 | 2025-02-12 | Radha Enterprises | 87.021 | 5.1189 | TA419 | 0A/0 (CT) | Completed
2025-02-10 | 2025-02-03 | 2025-02-12 | Radha Enterprises | 37.138 | 3.7138 | TA419 | 19/5 | Completed
2025-02-10 | 2025-02-07 | 2025-02-20 | Radha Enterprises 1 | 65.872 | 4.7051 | TA419 | 20/0 | completed
2025-02-10 | 2025-02-07 | 2025-02-27 | Radha Enterprises 2 | 66.776 | 3.1798 | TA419 | 0D/5 | Completed
2025-02-11 | 2025-02-02 | 2025-02-11 | Madhu Sah | 62.444 | 6.2444 | TA419 | 6/0 | Completed
2025-02-11 | 2025-02-09 | 2025-02-18 | Madhu Sah | 43.804 | 4.3804 | TA419 | 5/4 | completed
2025-02-11 | 2025-02-08 | 2025-02-15 | Pinki Devi | 36.16 | 4.52 | TA419 | 0D/4 | Completed
2025-02-11 | 2025-02-08 | 2025-02-14 | Poonam Kumari | 34.79 | 4.97 | TA419 | 17/1 | Completed
2025-02-11 | 2025-01-27 | 2025-02-12 | Radha Enterprises | 87.021 | 5.1189 | TA419 | 0A/0 (CT) | Completed
2025-02-11 | 2025-02-03 | 2025-02-12 | Radha Enterprises | 37.138 | 3.7138 | TA419 | 19/5 | Completed
2025-02-11 | 2025-02-07 | 2025-02-20 | Radha Enterprises 1 | 65.872 | 4.7051 | TA419 | 20/0 | completed
2025-02-11 | 2025-02-07 | 2025-02-27 | Radha Enterprises 2 | 66.776 | 3.1798 | TA419 | 0D/5 | Completed
2025-02-12 | 2025-02-09 | 2025-02-18 | Madhu Sah | 43.804 | 4.3804 | TA419 | 5/4 | completed
2025-02-12 | 2025-02-08 | 2025-02-15 | Pinki Devi | 36.16 | 4.52 | TA419 | 0D/4 | Completed
2025-02-12 | 2025-02-08 | 2025-02-14 | Poonam Kumari | 34.79 | 4.97 | TA419 | 17/1 | Completed
2025-02-12 | 2025-01-27 | 2025-02-12 | Radha Enterprises | 87.021 | 5.1189 | TA419 | 0A/0 (CT) | Completed
2025-02-12 | 2025-02-03 | 2025-02-12 | Radha Enterprises | 37.138 | 3.7138 | TA419 | 19/5 | Completed
2025-02-12 | 2025-02-07 | 2025-02-20 | Radha Enterprises 1 | 65.872 | 4.7051 | TA419 | 20/0 | completed
2025-02-12 | 2025-02-07 | 2025-02-27 | Radha Enterprises 2 | 66.776 | 3.1798 | TA419 | 0D/5 | Completed
2025-02-13 | 2025-02-09 | 2025-02-18 | Madhu Sah | 43.804 | 4.3804 | TA419 | 5/4 | completed
2025-02-13 | 2025-02-08 | 2025-02-15 | Pinki Devi | 36.16 | 4.52 | TA419 | 0D/4 | Completed
2025-02-13 | 2025-02-13 | 2025-02-25 | Pinki Devi | 59.501 | 4.577 | TA419 | 0D/0 | Completed
2025-02-13 | 2025-02-08 | 2025-02-14 | Poonam Kumari | 34.79 | 4.97 | TA419 | 17/1 | Completed
2025-02-13 | 2025-02-07 | 2025-02-20 | Radha Enterprises 1 | 65.872 | 4.7051 | TA419 | 20/0 | completed
2025-02-13 | 2025-02-07 | 2025-02-27 | Radha Enterprises 2 | 66.776 | 3.1798 | TA419 | 0D/5 | Completed
2025-02-14 | 2025-02-09 | 2025-02-18 | Madhu Sah | 43.804 | 4.3804 | TA419 | 5/4 | completed
2025-02-14 | 2025-02-08 | 2025-02-15 | Pinki Devi | 36.16 | 4.52 | TA419 | 0D/4 | Completed
2025-02-14 | 2025-02-13 | 2025-02-25 | Pinki Devi | 59.501 | 4.577 | TA419 | 0D/0 | Completed
2025-02-14 | 2025-02-08 | 2025-02-14 | Poonam Kumari | 34.79 | 4.97 | TA419 | 17/1 | Completed
2025-02-14 | 2025-02-14 | 2025-02-25 | Poonam Kumari | 67.262 | 5.6052 | TA419 | 18/0 | Completed
2025-02-14 | 2025-02-07 | 2025-02-20 | Radha Enterprises 1 | 65.872 | 4.7051 | TA419 | 20/0 | completed
2025-02-14 | 2025-02-07 | 2025-02-27 | Radha Enterprises 2 | 66.776 | 3.1798 | TA419 | 0D/5 | Completed
2025-02-15 | 2025-02-09 | 2025-02-18 | Madhu Sah | 43.804 | 4.3804 | TA419 | 5/4 | completed
2025-02-15 | 2025-02-08 | 2025-02-15 | Pinki Devi | 36.16 | 4.52 | TA419 | 0D/4 | Completed
2025-02-15 | 2025-02-13 | 2025-02-25 | Pinki Devi | 59.501 | 4.577 | TA419 | 0D/0 | Completed
2025-02-15 | 2025-02-14 | 2025-02-25 | Poonam Kumari | 67.262 | 5.6052 | TA419 | 18/0 | Completed
2025-02-15 | 2025-02-07 | 2025-02-20 | Radha Enterprises 1 | 65.872 | 4.7051 | TA419 | 20/0 | completed
2025-02-15 | 2025-02-07 | 2025-02-27 | Radha Enterprises 2 | 66.776 | 3.1798 | TA419 | 0D/5 | Completed
2025-02-16 | 2025-02-09 | 2025-02-18 | Madhu Sah | 43.804 | 4.3804 | TA419 | 5/4 | completed
2025-02-16 | 2025-02-13 | 2025-02-25 | Pinki Devi | 59.501 | 4.577 | TA419 | 0D/0 | Completed
2025-02-16 | 2025-02-14 | 2025-02-25 | Poonam Kumari | 67.262 | 5.6052 | TA419 | 18/0 | Completed
2025-02-16 | 2025-02-07 | 2025-02-20 | Radha Enterprises 1 | 65.872 | 4.7051 | TA419 | 20/0 | completed
2025-02-16 | 2025-02-07 | 2025-02-27 | Radha Enterprises 2 | 66.776 | 3.1798 | TA419 | 0D/5 | Completed
2025-02-17 | 2025-02-09 | 2025-02-18 | Madhu Sah | 43.804 | 4.3804 | TA419 | 5/4 | completed
2025-02-17 | 2025-02-13 | 2025-02-25 | Pinki Devi | 59.501 | 4.577 | TA419 | 0D/0 | Completed
2025-02-17 | 2025-02-14 | 2025-02-25 | Poonam Kumari | 67.262 | 5.6052 | TA419 | 18/0 | Completed
2025-02-17 | 2025-02-07 | 2025-02-20 | Radha Enterprises 1 | 65.872 | 4.7051 | TA419 | 20/0 | completed
2025-02-17 | 2025-02-07 | 2025-02-27 | Radha Enterprises 2 | 66.776 | 3.1798 | TA419 | 0D/5 | Completed
2025-02-18 | 2025-02-09 | 2025-02-18 | Madhu Sah | 43.804 | 4.3804 | TA419 | 5/4 | completed
2025-02-18 | 2025-02-18 | 2025-02-24 | Madhu Sah | 36.16 | 5.1657 | TA419 | 6/6 | Completed
2025-02-18 | 2025-02-13 | 2025-02-25 | Pinki Devi | 59.501 | 4.577 | TA419 | 0D/0 | Completed
2025-02-18 | 2025-02-14 | 2025-02-25 | Poonam Kumari | 67.262 | 5.6052 | TA419 | 18/0 | Completed
2025-02-18 | 2025-02-07 | 2025-02-20 | Radha Enterprises 1 | 65.872 | 4.7051 | TA419 | 20/0 | completed
2025-02-18 | 2025-02-07 | 2025-02-27 | Radha Enterprises 2 | 66.776 | 3.1798 | TA419 | 0D/5 | Completed
2025-02-19 | 2025-02-18 | 2025-02-24 | Madhu Sah | 36.16 | 5.1657 | TA419 | 6/6 | Completed
2025-02-19 | 2025-02-13 | 2025-02-25 | Pinki Devi | 59.501 | 4.577 | TA419 | 0D/0 | Completed
2025-02-19 | 2025-02-19 | 2025-03-04 | Pinki Devi | 37.931 | 2.7094 | TA419 | 0B/1 | Completed
2025-02-19 | 2025-02-14 | 2025-02-25 | Poonam Kumari | 67.262 | 5.6052 | TA419 | 18/0 | Completed
2025-02-19 | 2025-02-07 | 2025-02-20 | Radha Enterprises 1 | 65.872 | 4.7051 | TA419 | 20/0 | completed
2025-02-19 | 2025-02-19 | 2025-02-28 | Radha Enterprises 1 | 45.697 | 4.5697 | TA419 | 22/1 | Completed
2025-02-19 | 2025-02-07 | 2025-02-27 | Radha Enterprises 2 | 66.776 | 3.1798 | TA419 | 0D/5 | Completed
2025-02-20 | 2025-02-18 | 2025-02-24 | Madhu Sah | 36.16 | 5.1657 | TA419 | 6/6 | Completed
2025-02-20 | 2025-02-13 | 2025-02-25 | Pinki Devi | 59.501 | 4.577 | TA419 | 0D/0 | Completed
2025-02-20 | 2025-02-19 | 2025-03-04 | Pinki Devi | 37.931 | 2.7094 | TA419 | 0B/1 | Completed
2025-02-20 | 2025-02-14 | 2025-02-25 | Poonam Kumari | 67.262 | 5.6052 | TA419 | 18/0 | Completed
2025-02-20 | 2025-02-07 | 2025-02-20 | Radha Enterprises 1 | 65.872 | 4.7051 | TA419 | 20/0 | completed
2025-02-20 | 2025-02-19 | 2025-02-28 | Radha Enterprises 1 | 45.697 | 4.5697 | TA419 | 22/1 | Completed
2025-02-20 | 2025-02-07 | 2025-02-27 | Radha Enterprises 2 | 66.776 | 3.1798 | TA419 | 0D/5 | Completed
2025-02-21 | 2025-02-18 | 2025-02-24 | Madhu Sah | 36.16 | 5.1657 | TA419 | 6/6 | Completed
2025-02-21 | 2025-02-13 | 2025-02-25 | Pinki Devi | 59.501 | 4.577 | TA419 | 0D/0 | Completed
2025-02-21 | 2025-02-19 | 2025-03-04 | Pinki Devi | 37.931 | 2.7094 | TA419 | 0B/1 | Completed
2025-02-21 | 2025-02-14 | 2025-02-25 | Poonam Kumari | 67.262 | 5.6052 | TA419 | 18/0 | Completed
2025-02-21 | 2025-02-19 | 2025-02-28 | Radha Enterprises 1 | 45.697 | 4.5697 | TA419 | 22/1 | Completed
2025-02-21 | 2025-02-07 | 2025-02-27 | Radha Enterprises 2 | 66.776 | 3.1798 | TA419 | 0D/5 | Completed
2025-02-22 | 2025-02-18 | 2025-02-24 | Madhu Sah | 36.16 | 5.1657 | TA419 | 6/6 | Completed
2025-02-22 | 2025-02-13 | 2025-02-25 | Pinki Devi | 59.501 | 4.577 | TA419 | 0D/0 | Completed
2025-02-22 | 2025-02-19 | 2025-03-04 | Pinki Devi | 37.931 | 2.7094 | TA419 | 0B/1 | Completed
2025-02-22 | 2025-02-14 | 2025-02-25 | Poonam Kumari | 67.262 | 5.6052 | TA419 | 18/0 | Completed
2025-02-22 | 2025-02-22 | 2025-03-07 | Poonam Kumari | 59.501 | 4.2501 | TA419 | 17/0 | Completed
2025-02-22 | 2025-02-19 | 2025-02-28 | Radha Enterprises 1 | 45.697 | 4.5697 | TA419 | 22/1 | Completed
2025-02-22 | 2025-02-07 | 2025-02-27 | Radha Enterprises 2 | 66.776 | 3.1798 | TA419 | 0D/5 | Completed
2025-02-23 | 2025-02-18 | 2025-02-24 | Madhu Sah | 36.16 | 5.1657 | TA419 | 6/6 | Completed
2025-02-23 | 2025-02-23 | 2025-02-28 | Madhu Sah | 37.931 | 6.3218 | TA419 | 5/3 | Completed
2025-02-23 | 2025-02-13 | 2025-02-25 | Pinki Devi | 59.501 | 4.577 | TA419 | 0D/0 | Completed
2025-02-23 | 2025-02-19 | 2025-03-04 | Pinki Devi | 37.931 | 2.7094 | TA419 | 0B/1 | Completed
2025-02-23 | 2025-02-14 | 2025-02-25 | Poonam Kumari | 67.262 | 5.6052 | TA419 | 18/0 | Completed
2025-02-23 | 2025-02-22 | 2025-03-07 | Poonam Kumari | 59.501 | 4.2501 | TA419 | 17/0 | Completed
2025-02-23 | 2025-02-19 | 2025-02-28 | Radha Enterprises 1 | 45.697 | 4.5697 | TA419 | 22/1 | Completed
2025-02-23 | 2025-02-07 | 2025-02-27 | Radha Enterprises 2 | 66.776 | 3.1798 | TA419 | 0D/5 | Completed
2025-02-24 | 2025-02-18 | 2025-02-24 | Madhu Sah | 36.16 | 5.1657 | TA419 | 6/6 | Completed
2025-02-24 | 2025-02-23 | 2025-02-28 | Madhu Sah | 37.931 | 6.3218 | TA419 | 5/3 | Completed
2025-02-24 | 2025-02-13 | 2025-02-25 | Pinki Devi | 59.501 | 4.577 | TA419 | 0D/0 | Completed
2025-02-24 | 2025-02-19 | 2025-03-04 | Pinki Devi | 37.931 | 2.7094 | TA419 | 0B/1 | Completed
2025-02-24 | 2025-02-14 | 2025-02-25 | Poonam Kumari | 67.262 | 5.6052 | TA419 | 18/0 | Completed
2025-02-24 | 2025-02-22 | 2025-03-07 | Poonam Kumari | 59.501 | 4.2501 | TA419 | 17/0 | Completed
2025-02-24 | 2025-02-19 | 2025-02-28 | Radha Enterprises 1 | 45.697 | 4.5697 | TA419 | 22/1 | Completed
2025-02-24 | 2025-02-07 | 2025-02-27 | Radha Enterprises 2 | 66.776 | 3.1798 | TA419 | 0D/5 | Completed
2025-02-25 | 2025-02-23 | 2025-02-28 | Madhu Sah | 37.931 | 6.3218 | TA419 | 5/3 | Completed
2025-02-25 | 2025-02-13 | 2025-02-25 | Pinki Devi | 59.501 | 4.577 | TA419 | 0D/0 | Completed
2025-02-25 | 2025-02-19 | 2025-03-04 | Pinki Devi | 37.931 | 2.7094 | TA419 | 0B/1 | Completed
2025-02-25 | 2025-02-14 | 2025-02-25 | Poonam Kumari | 67.262 | 5.6052 | TA419 | 18/0 | Completed
2025-02-25 | 2025-02-22 | 2025-03-07 | Poonam Kumari | 59.501 | 4.2501 | TA419 | 17/0 | Completed
2025-02-25 | 2025-02-19 | 2025-02-28 | Radha Enterprises 1 | 45.697 | 4.5697 | TA419 | 22/1 | Completed
2025-02-25 | 2025-02-07 | 2025-02-27 | Radha Enterprises 2 | 66.776 | 3.1798 | TA419 | 0D/5 | Completed
2025-02-25 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-02-26 | 2025-02-23 | 2025-02-28 | Madhu Sah | 37.931 | 6.3218 | TA419 | 5/3 | Completed
2025-02-26 | 2025-02-19 | 2025-03-04 | Pinki Devi | 37.931 | 2.7094 | TA419 | 0B/1 | Completed
2025-02-26 | 2025-02-22 | 2025-03-07 | Poonam Kumari | 59.501 | 4.2501 | TA419 | 17/0 | Completed
2025-02-26 | 2025-02-19 | 2025-02-28 | Radha Enterprises 1 | 45.697 | 4.5697 | TA419 | 22/1 | Completed
2025-02-26 | 2025-02-07 | 2025-02-27 | Radha Enterprises 2 | 66.776 | 3.1798 | TA419 | 0D/5 | Completed
2025-02-26 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-02-27 | 2025-02-23 | 2025-02-28 | Madhu Sah | 37.931 | 6.3218 | TA419 | 5/3 | Completed
2025-02-27 | 2025-02-19 | 2025-03-04 | Pinki Devi | 37.931 | 2.7094 | TA419 | 0B/1 | Completed
2025-02-27 | 2025-02-22 | 2025-03-07 | Poonam Kumari | 59.501 | 4.2501 | TA419 | 17/0 | Completed
2025-02-27 | 2025-02-19 | 2025-02-28 | Radha Enterprises 1 | 45.697 | 4.5697 | TA419 | 22/1 | Completed
2025-02-27 | 2025-02-07 | 2025-02-27 | Radha Enterprises 2 | 66.776 | 3.1798 | TA419 | 0D/5 | Completed
2025-02-27 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-02-28 | 2025-02-23 | 2025-02-28 | Madhu Sah | 37.931 | 6.3218 | TA419 | 5/3 | Completed
2025-02-28 | 2025-02-19 | 2025-03-04 | Pinki Devi | 37.931 | 2.7094 | TA419 | 0B/1 | Completed
2025-02-28 | 2025-02-22 | 2025-03-07 | Poonam Kumari | 59.501 | 4.2501 | TA419 | 17/0 | Completed
2025-02-28 | 2025-02-19 | 2025-02-28 | Radha Enterprises 1 | 45.697 | 4.5697 | TA419 | 22/1 | Completed
2025-02-28 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-01 | 2025-03-01 | 2025-03-08 | Madhu Sah | 37.138 | 4.6422 | TA419 | 7/1 | Completed
2025-03-01 | 2025-02-19 | 2025-03-04 | Pinki Devi | 37.931 | 2.7094 | TA419 | 0B/1 | Completed
2025-03-01 | 2025-02-22 | 2025-03-07 | Poonam Kumari | 59.501 | 4.2501 | TA419 | 17/0 | Completed
2025-03-01 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-02 | 2025-03-01 | 2025-03-08 | Madhu Sah | 37.138 | 4.6422 | TA419 | 7/1 | Completed
2025-03-02 | 2025-02-19 | 2025-03-04 | Pinki Devi | 37.931 | 2.7094 | TA419 | 0B/1 | Completed
2025-03-02 | 2025-02-22 | 2025-03-07 | Poonam Kumari | 59.501 | 4.2501 | TA419 | 17/0 | Completed
2025-03-02 | 2025-03-02 | 2025-03-26 | Poonam Kumari | 73.245 | 2.9298 | TA419 | 15A/0 | Completed
2025-03-02 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-03 | 2025-03-01 | 2025-03-08 | Madhu Sah | 37.138 | 4.6422 | TA419 | 7/1 | Completed
2025-03-03 | 2025-02-19 | 2025-03-04 | Pinki Devi | 37.931 | 2.7094 | TA419 | 0B/1 | Completed
2025-03-03 | 2025-02-22 | 2025-03-07 | Poonam Kumari | 59.501 | 4.2501 | TA419 | 17/0 | Completed
2025-03-03 | 2025-03-02 | 2025-03-26 | Poonam Kumari | 73.245 | 2.9298 | TA419 | 15A/0 | Completed
2025-03-03 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-04 | 2025-03-01 | 2025-03-08 | Madhu Sah | 37.138 | 4.6422 | TA419 | 7/1 | Completed
2025-03-04 | 2025-02-19 | 2025-03-04 | Pinki Devi | 37.931 | 2.7094 | TA419 | 0B/1 | Completed
2025-03-04 | 2025-02-22 | 2025-03-07 | Poonam Kumari | 59.501 | 4.2501 | TA419 | 17/0 | Completed
2025-03-04 | 2025-03-02 | 2025-03-26 | Poonam Kumari | 73.245 | 2.9298 | TA419 | 15A/0 | Completed
2025-03-04 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-05 | 2025-03-01 | 2025-03-08 | Madhu Sah | 37.138 | 4.6422 | TA419 | 7/1 | Completed
2025-03-05 | 2025-02-22 | 2025-03-07 | Poonam Kumari | 59.501 | 4.2501 | TA419 | 17/0 | Completed
2025-03-05 | 2025-03-02 | 2025-03-26 | Poonam Kumari | 73.245 | 2.9298 | TA419 | 15A/0 | Completed
2025-03-05 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-06 | 2025-03-01 | 2025-03-08 | Madhu Sah | 37.138 | 4.6422 | TA419 | 7/1 | Completed
2025-03-06 | 2025-02-22 | 2025-03-07 | Poonam Kumari | 59.501 | 4.2501 | TA419 | 17/0 | Completed
2025-03-06 | 2025-03-02 | 2025-03-26 | Poonam Kumari | 73.245 | 2.9298 | TA419 | 15A/0 | Completed
2025-03-06 | 2025-03-06 | 2025-03-12 | Radha Enterprises 1 | 37.931 | 5.4187 | TA419 | 23/3 | Completed
2025-03-06 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-07 | 2025-03-01 | 2025-03-08 | Madhu Sah | 37.138 | 4.6422 | TA419 | 7/1 | Completed
2025-03-07 | 2025-02-22 | 2025-03-07 | Poonam Kumari | 59.501 | 4.2501 | TA419 | 17/0 | Completed
2025-03-07 | 2025-03-02 | 2025-03-26 | Poonam Kumari | 73.245 | 2.9298 | TA419 | 15A/0 | Completed
2025-03-07 | 2025-03-06 | 2025-03-12 | Radha Enterprises 1 | 37.931 | 5.4187 | TA419 | 23/3 | Completed
2025-03-07 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-08 | 2025-03-01 | 2025-03-08 | Madhu Sah | 37.138 | 4.6422 | TA419 | 7/1 | Completed
2025-03-08 | 2025-03-02 | 2025-03-26 | Poonam Kumari | 73.245 | 2.9298 | TA419 | 15A/0 | Completed
2025-03-08 | 2025-03-08 | 2025-03-24 | Radha Enterprises | 73.245 | 4.3085 | TA419 | 24/0 | Completed
2025-03-08 | 2025-03-06 | 2025-03-12 | Radha Enterprises 1 | 37.931 | 5.4187 | TA419 | 23/3 | Completed
2025-03-08 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-09 | 2025-03-02 | 2025-03-26 | Poonam Kumari | 73.245 | 2.9298 | TA419 | 15A/0 | Completed
2025-03-09 | 2025-03-08 | 2025-03-24 | Radha Enterprises | 73.245 | 4.3085 | TA419 | 24/0 | Completed
2025-03-09 | 2025-03-06 | 2025-03-12 | Radha Enterprises 1 | 37.931 | 5.4187 | TA419 | 23/3 | Completed
2025-03-09 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-10 | 2025-03-02 | 2025-03-26 | Poonam Kumari | 73.245 | 2.9298 | TA419 | 15A/0 | Completed
2025-03-10 | 2025-03-08 | 2025-03-24 | Radha Enterprises | 73.245 | 4.3085 | TA419 | 24/0 | Completed
2025-03-10 | 2025-03-06 | 2025-03-12 | Radha Enterprises 1 | 37.931 | 5.4187 | TA419 | 23/3 | Completed
2025-03-10 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-11 | 2025-03-02 | 2025-03-26 | Poonam Kumari | 73.245 | 2.9298 | TA419 | 15A/0 | Completed
2025-03-11 | 2025-03-08 | 2025-03-24 | Radha Enterprises | 73.245 | 4.3085 | TA419 | 24/0 | Completed
2025-03-11 | 2025-03-06 | 2025-03-12 | Radha Enterprises 1 | 37.931 | 5.4187 | TA419 | 23/3 | Completed
2025-03-11 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-12 | 2025-03-02 | 2025-03-26 | Poonam Kumari | 73.245 | 2.9298 | TA419 | 15A/0 | Completed
2025-03-12 | 2025-03-08 | 2025-03-24 | Radha Enterprises | 73.245 | 4.3085 | TA419 | 24/0 | Completed
2025-03-12 | 2025-03-06 | 2025-03-12 | Radha Enterprises 1 | 37.931 | 5.4187 | TA419 | 23/3 | Completed
2025-03-12 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-13 | 2025-03-02 | 2025-03-26 | Poonam Kumari | 73.245 | 2.9298 | TA419 | 15A/0 | Completed
2025-03-13 | 2025-03-08 | 2025-03-24 | Radha Enterprises | 73.245 | 4.3085 | TA419 | 24/0 | Completed
2025-03-13 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-14 | 2025-03-02 | 2025-03-26 | Poonam Kumari | 73.245 | 2.9298 | TA419 | 15A/0 | Completed
2025-03-14 | 2025-03-08 | 2025-03-24 | Radha Enterprises | 73.245 | 4.3085 | TA419 | 24/0 | Completed
2025-03-14 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-15 | 2025-03-02 | 2025-03-26 | Poonam Kumari | 73.245 | 2.9298 | TA419 | 15A/0 | Completed
2025-03-15 | 2025-03-08 | 2025-03-24 | Radha Enterprises | 73.245 | 4.3085 | TA419 | 24/0 | Completed
2025-03-15 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-16 | 2025-03-02 | 2025-03-26 | Poonam Kumari | 73.245 | 2.9298 | TA419 | 15A/0 | Completed
2025-03-16 | 2025-03-08 | 2025-03-24 | Radha Enterprises | 73.245 | 4.3085 | TA419 | 24/0 | Completed
2025-03-16 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-17 | 2025-03-02 | 2025-03-26 | Poonam Kumari | 73.245 | 2.9298 | TA419 | 15A/0 | Completed
2025-03-17 | 2025-03-08 | 2025-03-24 | Radha Enterprises | 73.245 | 4.3085 | TA419 | 24/0 | Completed
2025-03-17 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-18 | 2025-03-02 | 2025-03-26 | Poonam Kumari | 73.245 | 2.9298 | TA419 | 15A/0 | Completed
2025-03-18 | 2025-03-08 | 2025-03-24 | Radha Enterprises | 73.245 | 4.3085 | TA419 | 24/0 | Completed
2025-03-18 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-19 | 2025-03-02 | 2025-03-26 | Poonam Kumari | 73.245 | 2.9298 | TA419 | 15A/0 | Completed
2025-03-19 | 2025-03-08 | 2025-03-24 | Radha Enterprises | 73.245 | 4.3085 | TA419 | 24/0 | Completed
2025-03-19 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-20 | 2025-03-02 | 2025-03-26 | Poonam Kumari | 73.245 | 2.9298 | TA419 | 15A/0 | Completed
2025-03-20 | 2025-03-08 | 2025-03-24 | Radha Enterprises | 73.245 | 4.3085 | TA419 | 24/0 | Completed
2025-03-20 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-21 | 2025-03-02 | 2025-03-26 | Poonam Kumari | 73.245 | 2.9298 | TA419 | 15A/0 | Completed
2025-03-21 | 2025-03-08 | 2025-03-24 | Radha Enterprises | 73.245 | 4.3085 | TA419 | 24/0 | Completed
2025-03-21 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-22 | 2025-03-02 | 2025-03-26 | Poonam Kumari | 73.245 | 2.9298 | TA419 | 15A/0 | Completed
2025-03-22 | 2025-03-08 | 2025-03-24 | Radha Enterprises | 73.245 | 4.3085 | TA419 | 24/0 | Completed
2025-03-22 | 2025-03-22 | 2025-03-28 | Radha Enterprises 1 | 36.16 | 5.1657 | TA419 | 26/1 | Completed
2025-03-22 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-23 | 2025-03-02 | 2025-03-26 | Poonam Kumari | 73.245 | 2.9298 | TA419 | 15A/0 | Completed
2025-03-23 | 2025-03-08 | 2025-03-24 | Radha Enterprises | 73.245 | 4.3085 | TA419 | 24/0 | Completed
2025-03-23 | 2025-03-22 | 2025-03-28 | Radha Enterprises 1 | 36.16 | 5.1657 | TA419 | 26/1 | Completed
2025-03-23 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-24 | 2025-03-24 | 2025-04-11 | Madhu Sah | 36.16 | 1.9032 | TA419 | 5/2 | Completed
2025-03-24 | 2025-03-02 | 2025-03-26 | Poonam Kumari | 73.245 | 2.9298 | TA419 | 15A/0 | Completed
2025-03-24 | 2025-03-08 | 2025-03-24 | Radha Enterprises | 73.245 | 4.3085 | TA419 | 24/0 | Completed
2025-03-24 | 2025-03-22 | 2025-03-28 | Radha Enterprises 1 | 36.16 | 5.1657 | TA419 | 26/1 | Completed
2025-03-24 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-25 | 2025-03-24 | 2025-04-11 | Madhu Sah | 36.16 | 1.9032 | TA419 | 5/2 | Completed
2025-03-25 | 2025-03-02 | 2025-03-26 | Poonam Kumari | 73.245 | 2.9298 | TA419 | 15A/0 | Completed
2025-03-25 | 2025-03-22 | 2025-03-28 | Radha Enterprises 1 | 36.16 | 5.1657 | TA419 | 26/1 | Completed
2025-03-25 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-26 | 2025-03-24 | 2025-04-11 | Madhu Sah | 36.16 | 1.9032 | TA419 | 5/2 | Completed
2025-03-26 | 2025-03-02 | 2025-03-26 | Poonam Kumari | 73.245 | 2.9298 | TA419 | 15A/0 | Completed
2025-03-26 | 2025-03-26 | 2025-04-05 | Poornam Kumari | 36.16 | 3.2873 | TA419 | 12/1 | Completed
2025-03-26 | 2025-03-22 | 2025-03-28 | Radha Enterprises 1 | 36.16 | 5.1657 | TA419 | 26/1 | Completed
2025-03-26 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-27 | 2025-03-24 | 2025-04-11 | Madhu Sah | 36.16 | 1.9032 | TA419 | 5/2 | Completed
2025-03-27 | 2025-03-26 | 2025-04-05 | Poornam Kumari | 36.16 | 3.2873 | TA419 | 12/1 | Completed
2025-03-27 | 2025-03-22 | 2025-03-28 | Radha Enterprises 1 | 36.16 | 5.1657 | TA419 | 26/1 | Completed
2025-03-27 | 2025-03-27 | 2025-04-05 | Radha Enterprises 1 | 35.602 | 3.5602 | TA419 | 24/3 | Completed
2025-03-27 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-28 | 2025-03-24 | 2025-04-11 | Madhu Sah | 36.16 | 1.9032 | TA419 | 5/2 | Completed
2025-03-28 | 2025-03-26 | 2025-04-05 | Poornam Kumari | 36.16 | 3.2873 | TA419 | 12/1 | Completed
2025-03-28 | 2025-03-22 | 2025-03-28 | Radha Enterprises 1 | 36.16 | 5.1657 | TA419 | 26/1 | Completed
2025-03-28 | 2025-03-27 | 2025-04-05 | Radha Enterprises 1 | 35.602 | 3.5602 | TA419 | 24/3 | Completed
2025-03-28 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-29 | 2025-03-24 | 2025-04-11 | Madhu Sah | 36.16 | 1.9032 | TA419 | 5/2 | Completed
2025-03-29 | 2025-03-26 | 2025-04-05 | Poornam Kumari | 36.16 | 3.2873 | TA419 | 12/1 | Completed
2025-03-29 | 2025-03-27 | 2025-04-05 | Radha Enterprises 1 | 35.602 | 3.5602 | TA419 | 24/3 | Completed
2025-03-29 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-30 | 2025-03-24 | 2025-04-11 | Madhu Sah | 36.16 | 1.9032 | TA419 | 5/2 | Completed
2025-03-30 | 2025-03-26 | 2025-04-05 | Poornam Kumari | 36.16 | 3.2873 | TA419 | 12/1 | Completed
2025-03-30 | 2025-03-27 | 2025-04-05 | Radha Enterprises 1 | 35.602 | 3.5602 | TA419 | 24/3 | Completed
2025-03-30 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-03-31 | 2025-03-31 | 2025-04-13 | Gagan Enterprises | 36.16 | 2.5829 | TA419 | 30/1 | Completed
2025-03-31 | 2025-03-24 | 2025-04-11 | Madhu Sah | 36.16 | 1.9032 | TA419 | 5/2 | Completed
2025-03-31 | 2025-03-26 | 2025-04-05 | Poornam Kumari | 36.16 | 3.2873 | TA419 | 12/1 | Completed
2025-03-31 | 2025-03-27 | 2025-04-05 | Radha Enterprises 1 | 35.602 | 3.5602 | TA419 | 24/3 | Completed
2025-03-31 | 2025-03-31 | 2025-04-08 | Radha Enterprises 1 | 35.602 | 3.9558 | TA419 | 26/5 | Completed
2025-03-31 | 2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-04-01 | 2025-03-31 | 2025-04-13 | Gagan Enterprises | 36.16 | 2.5829 | TA419 | 30/1 | Completed
2025-04-01 | 2025-03-24 | 2025-04-11 | Madhu Sah | 36.16 | 1.9032 | TA419 | 5/2 | Completed
2025-04-01 | 2025-03-26 | 2025-04-05 | Poornam Kumari | 36.16 | 3.2873 | TA419 | 12/1 | Completed
2025-04-01 | 2025-03-27 | 2025-04-05 | Radha Enterprises 1 | 35.602 | 3.5602 | TA419 | 24/3 | Completed
2025-04-01 | 2025-03-31 | 2025-04-08 | Radha Enterprises 1 | 35.602 | 3.9558 | TA419 | 26/5 | Completed
2025-04-02 | 2025-03-31 | 2025-04-13 | Gagan Enterprises | 36.16 | 2.5829 | TA419 | 30/1 | Completed
2025-04-02 | 2025-03-24 | 2025-04-11 | Madhu Sah | 36.16 | 1.9032 | TA419 | 5/2 | Completed
2025-04-02 | 2025-03-26 | 2025-04-05 | Poornam Kumari | 36.16 | 3.2873 | TA419 | 12/1 | Completed
2025-04-02 | 2025-03-27 | 2025-04-05 | Radha Enterprises 1 | 35.602 | 3.5602 | TA419 | 24/3 | Completed
2025-04-02 | 2025-03-31 | 2025-04-08 | Radha Enterprises 1 | 35.602 | 3.9558 | TA419 | 26/5 | Completed
2025-04-03 | 2025-03-31 | 2025-04-13 | Gagan Enterprises | 36.16 | 2.5829 | TA419 | 30/1 | Completed
2025-04-03 | 2025-03-24 | 2025-04-11 | Madhu Sah | 36.16 | 1.9032 | TA419 | 5/2 | Completed
2025-04-03 | 2025-03-26 | 2025-04-05 | Poornam Kumari | 36.16 | 3.2873 | TA419 | 12/1 | Completed
2025-04-03 | 2025-04-03 | 2025-04-14 | Poornam Kumari | 43.804 | 3.6503 | TA419 | 11/4 | Completed
2025-04-03 | 2025-03-27 | 2025-04-05 | Radha Enterprises 1 | 35.602 | 3.5602 | TA419 | 24/3 | Completed
2025-04-03 | 2025-03-31 | 2025-04-08 | Radha Enterprises 1 | 35.602 | 3.9558 | TA419 | 26/5 | Completed
2025-04-04 | 2025-03-31 | 2025-04-13 | Gagan Enterprises | 36.16 | 2.5829 | TA419 | 30/1 | Completed
2025-04-04 | 2025-03-24 | 2025-04-11 | Madhu Sah | 36.16 | 1.9032 | TA419 | 5/2 | Completed
2025-04-04 | 2025-03-26 | 2025-04-05 | Poornam Kumari | 36.16 | 3.2873 | TA419 | 12/1 | Completed
2025-04-04 | 2025-04-03 | 2025-04-14 | Poornam Kumari | 43.804 | 3.6503 | TA419 | 11/4 | Completed
2025-04-04 | 2025-03-27 | 2025-04-05 | Radha Enterprises 1 | 35.602 | 3.5602 | TA419 | 24/3 | Completed
2025-04-04 | 2025-03-31 | 2025-04-08 | Radha Enterprises 1 | 35.602 | 3.9558 | TA419 | 26/5 | Completed
2025-04-05 | 2025-03-31 | 2025-04-13 | Gagan Enterprises | 36.16 | 2.5829 | TA419 | 30/1 | Completed
2025-04-05 | 2025-03-24 | 2025-04-11 | Madhu Sah | 36.16 | 1.9032 | TA419 | 5/2 | Completed
2025-04-05 | 2025-03-26 | 2025-04-05 | Poornam Kumari | 36.16 | 3.2873 | TA419 | 12/1 | Completed
2025-04-05 | 2025-04-03 | 2025-04-14 | Poornam Kumari | 43.804 | 3.6503 | TA419 | 11/4 | Completed
2025-04-05 | 2025-03-27 | 2025-04-05 | Radha Enterprises 1 | 35.602 | 3.5602 | TA419 | 24/3 | Completed
2025-04-05 | 2025-03-31 | 2025-04-08 | Radha Enterprises 1 | 35.602 | 3.9558 | TA419 | 26/5 | Completed
2025-04-06 | 2025-03-31 | 2025-04-13 | Gagan Enterprises | 36.16 | 2.5829 | TA419 | 30/1 | Completed
2025-04-06 | 2025-03-24 | 2025-04-11 | Madhu Sah | 36.16 | 1.9032 | TA419 | 5/2 | Completed
2025-04-06 | 2025-04-03 | 2025-04-14 | Poornam Kumari | 43.804 | 3.6503 | TA419 | 11/4 | Completed
2025-04-06 | 2025-03-31 | 2025-04-08 | Radha Enterprises 1 | 35.602 | 3.9558 | TA419 | 26/5 | Completed
2025-04-07 | 2025-03-31 | 2025-04-13 | Gagan Enterprises | 36.16 | 2.5829 | TA419 | 30/1 | Completed
2025-04-07 | 2025-03-24 | 2025-04-11 | Madhu Sah | 36.16 | 1.9032 | TA419 | 5/2 | Completed
2025-04-07 | 2025-04-07 | 2025-04-17 | Madhu Sah | 34.79 | 3.1627 | TA419 | 5/1 | Completed
2025-04-07 | 2025-04-03 | 2025-04-14 | Poornam Kumari | 43.804 | 3.6503 | TA419 | 11/4 | Completed
2025-04-07 | 2025-03-31 | 2025-04-08 | Radha Enterprises 1 | 35.602 | 3.9558 | TA419 | 26/5 | Completed
2025-04-08 | 2025-03-31 | 2025-04-13 | Gagan Enterprises | 36.16 | 2.5829 | TA419 | 30/1 | Completed
2025-04-08 | 2025-03-24 | 2025-04-11 | Madhu Sah | 36.16 | 1.9032 | TA419 | 5/2 | Completed
2025-04-08 | 2025-04-07 | 2025-04-17 | Madhu Sah | 34.79 | 3.1627 | TA419 | 5/1 | Completed
2025-04-08 | 2025-04-03 | 2025-04-14 | Poornam Kumari | 43.804 | 3.6503 | TA419 | 11/4 | Completed
2025-04-08 | 2025-03-31 | 2025-04-08 | Radha Enterprises 1 | 35.602 | 3.9558 | TA419 | 26/5 | Completed
2025-04-08 | 2025-04-08 | 2025-04-13 | Radha Enterprises 1 | 36.16 | 6.0267 | TA419 | 26/6 | Completed
2025-04-09 | 2025-03-31 | 2025-04-13 | Gagan Enterprises | 36.16 | 2.5829 | TA419 | 30/1 | Completed
2025-04-09 | 2025-03-24 | 2025-04-11 | Madhu Sah | 36.16 | 1.9032 | TA419 | 5/2 | Completed
2025-04-09 | 2025-04-07 | 2025-04-17 | Madhu Sah | 34.79 | 3.1627 | TA419 | 5/1 | Completed
2025-04-09 | 2025-04-03 | 2025-04-14 | Poornam Kumari | 43.804 | 3.6503 | TA419 | 11/4 | Completed
2025-04-09 | 2025-04-08 | 2025-04-13 | Radha Enterprises 1 | 36.16 | 6.0267 | TA419 | 26/6 | Completed
2025-04-10 | 2025-03-31 | 2025-04-13 | Gagan Enterprises | 36.16 | 2.5829 | TA419 | 30/1 | Completed
2025-04-10 | 2025-03-24 | 2025-04-11 | Madhu Sah | 36.16 | 1.9032 | TA419 | 5/2 | Completed
2025-04-10 | 2025-04-07 | 2025-04-17 | Madhu Sah | 34.79 | 3.1627 | TA419 | 5/1 | Completed
2025-04-10 | 2025-04-03 | 2025-04-14 | Poornam Kumari | 43.804 | 3.6503 | TA419 | 11/4 | Completed
2025-04-10 | 2025-04-08 | 2025-04-13 | Radha Enterprises 1 | 36.16 | 6.0267 | TA419 | 26/6 | Completed
2025-04-11 | 2025-03-31 | 2025-04-13 | Gagan Enterprises | 36.16 | 2.5829 | TA419 | 30/1 | Completed
2025-04-11 | 2025-03-24 | 2025-04-11 | Madhu Sah | 36.16 | 1.9032 | TA419 | 5/2 | Completed
2025-04-11 | 2025-04-07 | 2025-04-17 | Madhu Sah | 34.79 | 3.1627 | TA419 | 5/1 | Completed
2025-04-11 | 2025-04-03 | 2025-04-14 | Poornam Kumari | 43.804 | 3.6503 | TA419 | 11/4 | Completed
2025-04-11 | 2025-04-11 | 2025-04-19 | Poornam Kumari | 37.931 | 4.2146 | TA419 | 11/3 | Completed
2025-04-11 | 2025-04-08 | 2025-04-13 | Radha Enterprises 1 | 36.16 | 6.0267 | TA419 | 26/6 | Completed
2025-04-12 | 2025-03-31 | 2025-04-13 | Gagan Enterprises | 36.16 | 2.5829 | TA419 | 30/1 | Completed
2025-04-12 | 2025-04-12 | 2025-04-21 | Gagan Enterprises | 34.79 | 3.479 | TA419 | 28/1 | Completed
2025-04-12 | 2025-04-07 | 2025-04-17 | Madhu Sah | 34.79 | 3.1627 | TA419 | 5/1 | Completed
2025-04-12 | 2025-04-03 | 2025-04-14 | Poornam Kumari | 43.804 | 3.6503 | TA419 | 11/4 | Completed
2025-04-12 | 2025-04-11 | 2025-04-19 | Poornam Kumari | 37.931 | 4.2146 | TA419 | 11/3 | Completed
2025-04-12 | 2025-04-08 | 2025-04-13 | Radha Enterprises 1 | 36.16 | 6.0267 | TA419 | 26/6 | Completed
2025-04-12 | 2025-04-12 | 2025-04-18 | Radha Enterprises 1 | 36.16 | 5.1657 | TA419 | 26/3 | Completed
2025-04-13 | 2025-03-31 | 2025-04-13 | Gagan Enterprises | 36.16 | 2.5829 | TA419 | 30/1 | Completed
2025-04-13 | 2025-04-12 | 2025-04-21 | Gagan Enterprises | 34.79 | 3.479 | TA419 | 28/1 | Completed
2025-04-13 | 2025-04-07 | 2025-04-17 | Madhu Sah | 34.79 | 3.1627 | TA419 | 5/1 | Completed
2025-04-13 | 2025-04-03 | 2025-04-14 | Poornam Kumari | 43.804 | 3.6503 | TA419 | 11/4 | Completed
2025-04-13 | 2025-04-11 | 2025-04-19 | Poornam Kumari | 37.931 | 4.2146 | TA419 | 11/3 | Completed
2025-04-13 | 2025-04-08 | 2025-04-13 | Radha Enterprises 1 | 36.16 | 6.0267 | TA419 | 26/6 | Completed
2025-04-13 | 2025-04-12 | 2025-04-18 | Radha Enterprises 1 | 36.16 | 5.1657 | TA419 | 26/3 | Completed
2025-04-14 | 2025-04-12 | 2025-04-21 | Gagan Enterprises | 34.79 | 3.479 | TA419 | 28/1 | Completed
2025-04-14 | 2025-04-07 | 2025-04-17 | Madhu Sah | 34.79 | 3.1627 | TA419 | 5/1 | Completed
2025-04-14 | 2025-04-14 | 2025-04-27 | Madhu Sah | 59.501 | 4.2501 | TA419 | 5/0 | Completed
2025-04-14 | 2025-04-03 | 2025-04-14 | Poornam Kumari | 43.804 | 3.6503 | TA419 | 11/4 | Completed
2025-04-14 | 2025-04-11 | 2025-04-19 | Poornam Kumari | 37.931 | 4.2146 | TA419 | 11/3 | Completed
2025-04-14 | 2025-04-12 | 2025-04-18 | Radha Enterprises 1 | 36.16 | 5.1657 | TA419 | 26/3 | Completed
2025-04-15 | 2025-04-12 | 2025-04-21 | Gagan Enterprises | 34.79 | 3.479 | TA419 | 28/1 | Completed
2025-04-15 | 2025-04-07 | 2025-04-17 | Madhu Sah | 34.79 | 3.1627 | TA419 | 5/1 | Completed
2025-04-15 | 2025-04-14 | 2025-04-27 | Madhu Sah | 59.501 | 4.2501 | TA419 | 5/0 | Completed
2025-04-15 | 2025-04-11 | 2025-04-19 | Poornam Kumari | 37.931 | 4.2146 | TA419 | 11/3 | Completed
2025-04-15 | 2025-04-12 | 2025-04-18 | Radha Enterprises 1 | 36.16 | 5.1657 | TA419 | 26/3 | Completed
2025-04-16 | 2025-04-12 | 2025-04-21 | Gagan Enterprises | 34.79 | 3.479 | TA419 | 28/1 | Completed
2025-04-16 | 2025-04-07 | 2025-04-17 | Madhu Sah | 34.79 | 3.1627 | TA419 | 5/1 | Completed
2025-04-16 | 2025-04-14 | 2025-04-27 | Madhu Sah | 59.501 | 4.2501 | TA419 | 5/0 | Completed
2025-04-16 | 2025-04-11 | 2025-04-19 | Poornam Kumari | 37.931 | 4.2146 | TA419 | 11/3 | Completed
2025-04-16 | 2025-04-12 | 2025-04-18 | Radha Enterprises 1 | 36.16 | 5.1657 | TA419 | 26/3 | Completed
2025-04-17 | 2025-04-12 | 2025-04-21 | Gagan Enterprises | 34.79 | 3.479 | TA419 | 28/1 | Completed
2025-04-17 | 2025-04-07 | 2025-04-17 | Madhu Sah | 34.79 | 3.1627 | TA419 | 5/1 | Completed
2025-04-17 | 2025-04-14 | 2025-04-27 | Madhu Sah | 59.501 | 4.2501 | TA419 | 5/0 | Completed
2025-04-17 | 2025-04-11 | 2025-04-19 | Poornam Kumari | 37.931 | 4.2146 | TA419 | 11/3 | Completed
2025-04-17 | 2025-04-12 | 2025-04-18 | Radha Enterprises 1 | 36.16 | 5.1657 | TA419 | 26/3 | Completed
2025-04-17 | 2025-04-17 | 2025-04-23 | Radha Enterprises 1 | 36.16 | 5.1657 | TA419 | 26/4 | Completed
2025-04-18 | 2025-04-12 | 2025-04-21 | Gagan Enterprises | 34.79 | 3.479 | TA419 | 28/1 | Completed
2025-04-18 | 2025-04-14 | 2025-04-27 | Madhu Sah | 59.501 | 4.2501 | TA419 | 5/0 | Completed
2025-04-18 | 2025-04-11 | 2025-04-19 | Poornam Kumari | 37.931 | 4.2146 | TA419 | 11/3 | Completed
2025-04-18 | 2025-04-12 | 2025-04-18 | Radha Enterprises 1 | 36.16 | 5.1657 | TA419 | 26/3 | Completed
2025-04-18 | 2025-04-17 | 2025-04-23 | Radha Enterprises 1 | 36.16 | 5.1657 | TA419 | 26/4 | Completed
2025-04-19 | 2025-04-12 | 2025-04-21 | Gagan Enterprises | 34.79 | 3.479 | TA419 | 28/1 | Completed
2025-04-19 | 2025-04-14 | 2025-04-27 | Madhu Sah | 59.501 | 4.2501 | TA419 | 5/0 | Completed
2025-04-19 | 2025-04-11 | 2025-04-19 | Poornam Kumari | 37.931 | 4.2146 | TA419 | 11/3 | Completed
2025-04-19 | 2025-04-19 | 2025-04-29 | Poornam Kumari | 59.501 | 5.4092 | TA419 | 12/0 | Completed
2025-04-19 | 2025-04-17 | 2025-04-23 | Radha Enterprises 1 | 36.16 | 5.1657 | TA419 | 26/4 | Completed
2025-04-20 | 2025-04-12 | 2025-04-21 | Gagan Enterprises | 34.79 | 3.479 | TA419 | 28/1 | Completed
2025-04-20 | 2025-04-14 | 2025-04-27 | Madhu Sah | 59.501 | 4.2501 | TA419 | 5/0 | Completed
2025-04-20 | 2025-04-19 | 2025-04-29 | Poornam Kumari | 59.501 | 5.4092 | TA419 | 12/0 | Completed
2025-04-20 | 2025-04-17 | 2025-04-23 | Radha Enterprises 1 | 36.16 | 5.1657 | TA419 | 26/4 | Completed
2025-04-21 | 2025-04-12 | 2025-04-21 | Gagan Enterprises | 34.79 | 3.479 | TA419 | 28/1 | Completed
2025-04-21 | 2025-04-14 | 2025-04-27 | Madhu Sah | 59.501 | 4.2501 | TA419 | 5/0 | Completed
2025-04-21 | 2025-04-19 | 2025-04-29 | Poornam Kumari | 59.501 | 5.4092 | TA419 | 12/0 | Completed
2025-04-21 | 2025-04-17 | 2025-04-23 | Radha Enterprises 1 | 36.16 | 5.1657 | TA419 | 26/4 | Completed
2025-04-22 | 2025-04-22 | 2025-04-29 | Gagan Enterprises | 43.804 | 5.4755 | TA419 | 31/1 | Completed
2025-04-22 | 2025-04-14 | 2025-04-27 | Madhu Sah | 59.501 | 4.2501 | TA419 | 5/0 | Completed
2025-04-22 | 2025-04-19 | 2025-04-29 | Poornam Kumari | 59.501 | 5.4092 | TA419 | 12/0 | Completed
2025-04-22 | 2025-04-17 | 2025-04-23 | Radha Enterprises 1 | 36.16 | 5.1657 | TA419 | 26/4 | Completed
2025-04-23 | 2025-04-22 | 2025-04-29 | Gagan Enterprises | 43.804 | 5.4755 | TA419 | 31/1 | Completed
2025-04-23 | 2025-04-14 | 2025-04-27 | Madhu Sah | 59.501 | 4.2501 | TA419 | 5/0 | Completed
2025-04-23 | 2025-04-19 | 2025-04-29 | Poornam Kumari | 59.501 | 5.4092 | TA419 | 12/0 | Completed
2025-04-23 | 2025-04-23 | 2025-04-28 | Radha Enterprises | 37.138 | 6.1897 | TA419 | 24/2 | Completed
2025-04-23 | 2025-04-17 | 2025-04-23 | Radha Enterprises 1 | 36.16 | 5.1657 | TA419 | 26/4 | Completed
2025-04-24 | 2025-04-22 | 2025-04-29 | Gagan Enterprises | 43.804 | 5.4755 | TA419 | 31/1 | Completed
2025-04-24 | 2025-04-14 | 2025-04-27 | Madhu Sah | 59.501 | 4.2501 | TA419 | 5/0 | Completed
2025-04-24 | 2025-04-19 | 2025-04-29 | Poornam Kumari | 59.501 | 5.4092 | TA419 | 12/0 | Completed
2025-04-24 | 2025-04-23 | 2025-04-28 | Radha Enterprises | 37.138 | 6.1897 | TA419 | 24/2 | Completed
2025-04-25 | 2025-04-22 | 2025-04-29 | Gagan Enterprises | 43.804 | 5.4755 | TA419 | 31/1 | Completed
2025-04-25 | 2025-04-14 | 2025-04-27 | Madhu Sah | 59.501 | 4.2501 | TA419 | 5/0 | Completed
2025-04-25 | 2025-04-19 | 2025-04-29 | Poornam Kumari | 59.501 | 5.4092 | TA419 | 12/0 | Completed
2025-04-25 | 2025-04-23 | 2025-04-28 | Radha Enterprises | 37.138 | 6.1897 | TA419 | 24/2 | Completed
2025-04-26 | 2025-04-22 | 2025-04-29 | Gagan Enterprises | 43.804 | 5.4755 | TA419 | 31/1 | Completed
2025-04-26 | 2025-04-14 | 2025-04-27 | Madhu Sah | 59.501 | 4.2501 | TA419 | 5/0 | Completed
2025-04-26 | 2025-04-19 | 2025-04-29 | Poornam Kumari | 59.501 | 5.4092 | TA419 | 12/0 | Completed
2025-04-26 | 2025-04-23 | 2025-04-28 | Radha Enterprises | 37.138 | 6.1897 | TA419 | 24/2 | Completed
2025-04-27 | 2025-04-22 | 2025-04-29 | Gagan Enterprises | 43.804 | 5.4755 | TA419 | 31/1 | Completed
2025-04-27 | 2025-04-14 | 2025-04-27 | Madhu Sah | 59.501 | 4.2501 | TA419 | 5/0 | Completed
2025-04-27 | 2025-04-19 | 2025-04-29 | Poornam Kumari | 59.501 | 5.4092 | TA419 | 12/0 | Completed
2025-04-27 | 2025-04-23 | 2025-04-28 | Radha Enterprises | 37.138 | 6.1897 | TA419 | 24/2 | Completed
2025-04-28 | 2025-04-22 | 2025-04-29 | Gagan Enterprises | 43.804 | 5.4755 | TA419 | 31/1 | Completed
2025-04-28 | 2025-04-28 | 2025-05-10 | Gagan Enterprises | 83.134 | 6.3949 | TA419 | 31/0 | Completed
2025-04-28 | 2025-04-28 | 2025-05-04 | Madhu Sah | 37.931 | 5.4187 | TA419 | 4/1 | Completed
2025-04-28 | 2025-04-28 | 2025-05-07 | Poonam Kumari | 55.451 | 5.5451 | TA419 | 12A/0 | Completed
2025-04-28 | 2025-04-19 | 2025-04-29 | Poornam Kumari | 59.501 | 5.4092 | TA419 | 12/0 | Completed
2025-04-28 | 2025-04-23 | 2025-04-28 | Radha Enterprises | 37.138 | 6.1897 | TA419 | 24/2 | Completed
2025-04-29 | 2025-04-22 | 2025-04-29 | Gagan Enterprises | 43.804 | 5.4755 | TA419 | 31/1 | Completed
2025-04-29 | 2025-04-28 | 2025-05-10 | Gagan Enterprises | 83.134 | 6.3949 | TA419 | 31/0 | Completed
2025-04-29 | 2025-04-28 | 2025-05-04 | Madhu Sah | 37.931 | 5.4187 | TA419 | 4/1 | Completed
2025-04-29 | 2025-04-28 | 2025-05-07 | Poonam Kumari | 55.451 | 5.5451 | TA419 | 12A/0 | Completed
2025-04-29 | 2025-04-19 | 2025-04-29 | Poornam Kumari | 59.501 | 5.4092 | TA419 | 12/0 | Completed
2025-04-29 | 2025-04-29 | 2025-05-19 | Radha Enterprises | 137.046 | 6.526 | TA419 | 22/0 | completed
2025-04-30 | 2025-04-28 | 2025-05-10 | Gagan Enterprises | 83.134 | 6.3949 | TA419 | 31/0 | Completed
2025-04-30 | 2025-04-28 | 2025-05-04 | Madhu Sah | 37.931 | 5.4187 | TA419 | 4/1 | Completed
2025-04-30 | 2025-04-28 | 2025-05-07 | Poonam Kumari | 55.451 | 5.5451 | TA419 | 12A/0 | Completed
2025-04-30 | 2025-04-29 | 2025-05-19 | Radha Enterprises | 137.046 | 6.526 | TA419 | 22/0 | completed
2025-05-01 | 2025-04-28 | 2025-05-10 | Gagan Enterprises | 83.134 | 6.3949 | TA419 | 31/0 | Completed
2025-05-01 | 2025-04-28 | 2025-05-04 | Madhu Sah | 37.931 | 5.4187 | TA419 | 4/1 | Completed
2025-05-01 | 2025-04-28 | 2025-05-07 | Poonam Kumari | 55.451 | 5.5451 | TA419 | 12A/0 | Completed
2025-05-01 | 2025-04-29 | 2025-05-19 | Radha Enterprises | 137.046 | 6.526 | TA419 | 22/0 | completed
2025-05-02 | 2025-04-28 | 2025-05-10 | Gagan Enterprises | 83.134 | 6.3949 | TA419 | 31/0 | Completed
2025-05-02 | 2025-04-28 | 2025-05-04 | Madhu Sah | 37.931 | 5.4187 | TA419 | 4/1 | Completed
2025-05-02 | 2025-04-28 | 2025-05-07 | Poonam Kumari | 55.451 | 5.5451 | TA419 | 12A/0 | Completed
2025-05-02 | 2025-04-29 | 2025-05-19 | Radha Enterprises | 137.046 | 6.526 | TA419 | 22/0 | completed
2025-05-03 | 2025-04-28 | 2025-05-10 | Gagan Enterprises | 83.134 | 6.3949 | TA419 | 31/0 | Completed
2025-05-03 | 2025-04-28 | 2025-05-04 | Madhu Sah | 37.931 | 5.4187 | TA419 | 4/1 | Completed
2025-05-03 | 2025-04-28 | 2025-05-07 | Poonam Kumari | 55.451 | 5.5451 | TA419 | 12A/0 | Completed
2025-05-03 | 2025-04-29 | 2025-05-19 | Radha Enterprises | 137.046 | 6.526 | TA419 | 22/0 | completed
2025-05-04 | 2025-04-28 | 2025-05-10 | Gagan Enterprises | 83.134 | 6.3949 | TA419 | 31/0 | Completed
2025-05-04 | 2025-04-28 | 2025-05-04 | Madhu Sah | 37.931 | 5.4187 | TA419 | 4/1 | Completed
2025-05-04 | 2025-04-28 | 2025-05-07 | Poonam Kumari | 55.451 | 5.5451 | TA419 | 12A/0 | Completed
2025-05-04 | 2025-04-29 | 2025-05-19 | Radha Enterprises | 137.046 | 6.526 | TA419 | 22/0 | completed
2025-05-05 | 2025-04-28 | 2025-05-10 | Gagan Enterprises | 83.134 | 6.3949 | TA419 | 31/0 | Completed
2025-05-05 | 2025-05-05 | 2025-05-11 | Madhu Sah | 37.138 | 5.3054 | TA419 | 3/5 | Completed
2025-05-05 | 2025-04-28 | 2025-05-07 | Poonam Kumari | 55.451 | 5.5451 | TA419 | 12A/0 | Completed
2025-05-05 | 2025-04-29 | 2025-05-19 | Radha Enterprises | 137.046 | 6.526 | TA419 | 22/0 | completed
2025-05-06 | 2025-04-28 | 2025-05-10 | Gagan Enterprises | 83.134 | 6.3949 | TA419 | 31/0 | Completed
2025-05-06 | 2025-05-05 | 2025-05-11 | Madhu Sah | 37.138 | 5.3054 | TA419 | 3/5 | Completed
2025-05-06 | 2025-04-28 | 2025-05-07 | Poonam Kumari | 55.451 | 5.5451 | TA419 | 12A/0 | Completed
2025-05-06 | 2025-04-29 | 2025-05-19 | Radha Enterprises | 137.046 | 6.526 | TA419 | 22/0 | completed
2025-05-07 | 2025-04-28 | 2025-05-10 | Gagan Enterprises | 83.134 | 6.3949 | TA419 | 31/0 | Completed
2025-05-07 | 2025-05-05 | 2025-05-11 | Madhu Sah | 37.138 | 5.3054 | TA419 | 3/5 | Completed
2025-05-07 | 2025-04-28 | 2025-05-07 | Poonam Kumari | 55.451 | 5.5451 | TA419 | 12A/0 | Completed
2025-05-07 | 2025-04-29 | 2025-05-19 | Radha Enterprises | 137.046 | 6.526 | TA419 | 22/0 | completed
2025-05-08 | 2025-04-28 | 2025-05-10 | Gagan Enterprises | 83.134 | 6.3949 | TA419 | 31/0 | Completed
2025-05-08 | 2025-05-05 | 2025-05-11 | Madhu Sah | 37.138 | 5.3054 | TA419 | 3/5 | Completed
2025-05-08 | 2025-04-29 | 2025-05-19 | Radha Enterprises | 137.046 | 6.526 | TA419 | 22/0 | completed
2025-05-09 | 2025-04-28 | 2025-05-10 | Gagan Enterprises | 83.134 | 6.3949 | TA419 | 31/0 | Completed
2025-05-09 | 2025-05-05 | 2025-05-11 | Madhu Sah | 37.138 | 5.3054 | TA419 | 3/5 | Completed
2025-05-09 | 2025-04-29 | 2025-05-19 | Radha Enterprises | 137.046 | 6.526 | TA419 | 22/0 | completed
2025-05-10 | 2025-04-28 | 2025-05-10 | Gagan Enterprises | 83.134 | 6.3949 | TA419 | 31/0 | Completed
2025-05-10 | 2025-05-05 | 2025-05-11 | Madhu Sah | 37.138 | 5.3054 | TA419 | 3/5 | Completed
2025-05-10 | 2025-04-29 | 2025-05-19 | Radha Enterprises | 137.046 | 6.526 | TA419 | 22/0 | completed
2025-05-11 | 2025-05-05 | 2025-05-11 | Madhu Sah | 37.138 | 5.3054 | TA419 | 3/5 | Completed
2025-05-11 | 2025-04-29 | 2025-05-19 | Radha Enterprises | 137.046 | 6.526 | TA419 | 22/0 | completed
2025-05-12 | 2025-04-29 | 2025-05-19 | Radha Enterprises | 137.046 | 6.526 | TA419 | 22/0 | completed
2025-05-13 | 2025-04-29 | 2025-05-19 | Radha Enterprises | 137.046 | 6.526 | TA419 | 22/0 | completed
2025-05-14 | 2025-04-29 | 2025-05-19 | Radha Enterprises | 137.046 | 6.526 | TA419 | 22/0 | completed
2025-05-15 | 2025-04-29 | 2025-05-19 | Radha Enterprises | 137.046 | 6.526 | TA419 | 22/0 | completed
2025-05-16 | 2025-04-29 | 2025-05-19 | Radha Enterprises | 137.046 | 6.526 | TA419 | 22/0 | completed
2025-05-17 | 2025-04-29 | 2025-05-19 | Radha Enterprises | 137.046 | 6.526 | TA419 | 22/0 | completed
2025-05-18 | 2025-04-29 | 2025-05-19 | Radha Enterprises | 137.046 | 6.526 | TA419 | 22/0 | completed
2025-05-19 | 2025-04-29 | 2025-05-19 | Radha Enterprises | 137.046 | 6.526 | TA419 | 22/0 | completed
2025-05-19 | 2025-05-19 | 2025-06-03 | Radha Enterprises 1 | 73.245 | 4.5778 | TA419 | 27/0 | Completed
2025-05-20 | 2025-05-19 | 2025-06-03 | Radha Enterprises 1 | 73.245 | 4.5778 | TA419 | 27/0 | Completed
2025-05-21 | 2025-05-19 | 2025-06-03 | Radha Enterprises 1 | 73.245 | 4.5778 | TA419 | 27/0 | Completed
2025-05-22 | 2025-05-19 | 2025-06-03 | Radha Enterprises 1 | 73.245 | 4.5778 | TA419 | 27/0 | Completed
2025-05-23 | 2025-05-19 | 2025-06-03 | Radha Enterprises 1 | 73.245 | 4.5778 | TA419 | 27/0 | Completed
2025-05-24 | 2025-05-19 | 2025-06-03 | Radha Enterprises 1 | 73.245 | 4.5778 | TA419 | 27/0 | Completed
2025-05-25 | 2025-05-19 | 2025-06-03 | Radha Enterprises 1 | 73.245 | 4.5778 | TA419 | 27/0 | Completed
2025-05-26 | 2025-05-19 | 2025-06-03 | Radha Enterprises 1 | 73.245 | 4.5778 | TA419 | 27/0 | Completed
2025-05-27 | 2025-05-19 | 2025-06-03 | Radha Enterprises 1 | 73.245 | 4.5778 | TA419 | 27/0 | Completed
2025-05-28 | 2025-05-19 | 2025-06-03 | Radha Enterprises 1 | 73.245 | 4.5778 | TA419 | 27/0 | Completed
2025-05-29 | 2025-05-19 | 2025-06-03 | Radha Enterprises 1 | 73.245 | 4.5778 | TA419 | 27/0 | Completed
2025-05-30 | 2025-05-19 | 2025-06-03 | Radha Enterprises 1 | 73.245 | 4.5778 | TA419 | 27/0 | Completed
2025-05-31 | 2025-05-19 | 2025-06-03 | Radha Enterprises 1 | 73.245 | 4.5778 | TA419 | 27/0 | Completed
2025-06-01 | 2025-05-19 | 2025-06-03 | Radha Enterprises 1 | 73.245 | 4.5778 | TA419 | 27/0 | Completed
2025-06-02 | 2025-05-19 | 2025-06-03 | Radha Enterprises 1 | 73.245 | 4.5778 | TA419 | 27/0 | Completed
2025-06-03 | 2025-05-19 | 2025-06-03 | Radha Enterprises 1 | 73.245 | 4.5778 | TA419 | 27/0 | Completed
2025-06-05 | 2025-06-05 | 2025-06-13 | Radha Enterprises 1 | 43.804 | 4.8671 | TA419 | 27/1 | Completed
2025-06-06 | 2025-06-05 | 2025-06-13 | Radha Enterprises 1 | 43.804 | 4.8671 | TA419 | 27/1 | Completed
2025-06-07 | 2025-06-05 | 2025-06-13 | Radha Enterprises 1 | 43.804 | 4.8671 | TA419 | 27/1 | Completed
2025-06-08 | 2025-06-05 | 2025-06-13 | Radha Enterprises 1 | 43.804 | 4.8671 | TA419 | 27/1 | Completed
2025-06-09 | 2025-06-05 | 2025-06-13 | Radha Enterprises 1 | 43.804 | 4.8671 | TA419 | 27/1 | Completed
2025-06-10 | 2025-06-05 | 2025-06-13 | Radha Enterprises 1 | 43.804 | 4.8671 | TA419 | 27/1 | Completed
2025-06-11 | 2025-06-05 | 2025-06-13 | Radha Enterprises 1 | 43.804 | 4.8671 | TA419 | 27/1 | Completed
2025-06-12 | 2025-06-05 | 2025-06-13 | Radha Enterprises 1 | 43.804 | 4.8671 | TA419 | 27/1 | Completed
2025-06-12 | 2025-06-12 | 2025-06-20 | Radha Enterprises 1 | 34.79 | 3.8656 | TA419 | 27/2 | Completed
2025-06-13 | 2025-06-05 | 2025-06-13 | Radha Enterprises 1 | 43.804 | 4.8671 | TA419 | 27/1 | Completed
2025-06-13 | 2025-06-12 | 2025-06-20 | Radha Enterprises 1 | 34.79 | 3.8656 | TA419 | 27/2 | Completed
2025-06-14 | 2025-06-12 | 2025-06-20 | Radha Enterprises 1 | 34.79 | 3.8656 | TA419 | 27/2 | Completed
2025-06-15 | 2025-06-12 | 2025-06-20 | Radha Enterprises 1 | 34.79 | 3.8656 | TA419 | 27/2 | Completed
2025-06-16 | 2025-06-12 | 2025-06-20 | Radha Enterprises 1 | 34.79 | 3.8656 | TA419 | 27/2 | Completed
2025-06-17 | 2025-06-12 | 2025-06-20 | Radha Enterprises 1 | 34.79 | 3.8656 | TA419 | 27/2 | Completed
2025-06-18 | 2025-06-12 | 2025-06-20 | Radha Enterprises 1 | 34.79 | 3.8656 | TA419 | 27/2 | Completed
2025-06-19 | 2025-06-12 | 2025-06-20 | Radha Enterprises 1 | 34.79 | 3.8656 | TA419 | 27/2 | Completed
2025-06-20 | 2025-06-12 | 2025-06-20 | Radha Enterprises 1 | 34.79 | 3.8656 | TA419 | 27/2 | Completed
2025-06-21 | 2025-06-21 | 2025-06-26 | Radha Enterprises 1 | 36.16 | 6.0267 | TA419 | 27/3 | Completed
2025-06-22 | 2025-06-21 | 2025-06-26 | Radha Enterprises 1 | 36.16 | 6.0267 | TA419 | 27/3 | Completed
2025-06-23 | 2025-06-21 | 2025-06-26 | Radha Enterprises 1 | 36.16 | 6.0267 | TA419 | 27/3 | Completed
2025-06-24 | 2025-06-21 | 2025-06-26 | Radha Enterprises 1 | 36.16 | 6.0267 | TA419 | 27/3 | Completed
2025-06-25 | 2025-06-21 | 2025-06-26 | Radha Enterprises 1 | 36.16 | 6.0267 | TA419 | 27/3 | Completed
2025-06-26 | 2025-06-21 | 2025-06-26 | Radha Enterprises 1 | 36.16 | 6.0267 | TA419 | 27/3 | Completed
2025-06-27 | 2025-06-27 | 2025-07-08 | Radha Enterprises 1 | 67.262 | 5.6052 | TA419 | 28/0 | Completed
2025-06-28 | 2025-06-27 | 2025-07-08 | Radha Enterprises 1 | 67.262 | 5.6052 | TA419 | 28/0 | Completed
2025-06-29 | 2025-06-27 | 2025-07-08 | Radha Enterprises 1 | 67.262 | 5.6052 | TA419 | 28/0 | Completed
2025-06-30 | 2025-06-27 | 2025-07-08 | Radha Enterprises 1 | 67.262 | 5.6052 | TA419 | 28/0 | Completed
2025-07-01 | 2025-07-01 | 2025-07-17 | Madhu Sah | 83.134 | 4.8902 | TA419 | 34/0 | Completed
2025-07-01 | 2025-06-27 | 2025-07-08 | Radha Enterprises 1 | 67.262 | 5.6052 | TA419 | 28/0 | Completed
2025-07-02 | 2025-07-01 | 2025-07-17 | Madhu Sah | 83.134 | 4.8902 | TA419 | 34/0 | Completed
2025-07-02 | 2025-06-27 | 2025-07-08 | Radha Enterprises 1 | 67.262 | 5.6052 | TA419 | 28/0 | Completed
2025-07-03 | 2025-07-01 | 2025-07-17 | Madhu Sah | 83.134 | 4.8902 | TA419 | 34/0 | Completed
2025-07-03 | 2025-06-27 | 2025-07-08 | Radha Enterprises 1 | 67.262 | 5.6052 | TA419 | 28/0 | Completed
2025-07-04 | 2025-07-01 | 2025-07-17 | Madhu Sah | 83.134 | 4.8902 | TA419 | 34/0 | Completed
2025-07-04 | 2025-06-27 | 2025-07-08 | Radha Enterprises 1 | 67.262 | 5.6052 | TA419 | 28/0 | Completed
2025-07-05 | 2025-07-01 | 2025-07-17 | Madhu Sah | 83.134 | 4.8902 | TA419 | 34/0 | Completed
2025-07-05 | 2025-06-27 | 2025-07-08 | Radha Enterprises 1 | 67.262 | 5.6052 | TA419 | 28/0 | Completed
2025-07-06 | 2025-07-01 | 2025-07-17 | Madhu Sah | 83.134 | 4.8902 | TA419 | 34/0 | Completed
2025-07-06 | 2025-06-27 | 2025-07-08 | Radha Enterprises 1 | 67.262 | 5.6052 | TA419 | 28/0 | Completed
2025-07-07 | 2025-07-01 | 2025-07-17 | Madhu Sah | 83.134 | 4.8902 | TA419 | 34/0 | Completed
2025-07-07 | 2025-06-27 | 2025-07-08 | Radha Enterprises 1 | 67.262 | 5.6052 | TA419 | 28/0 | Completed
2025-07-08 | 2025-07-01 | 2025-07-17 | Madhu Sah | 83.134 | 4.8902 | TA419 | 34/0 | Completed
2025-07-08 | 2025-06-27 | 2025-07-08 | Radha Enterprises 1 | 67.262 | 5.6052 | TA419 | 28/0 | Completed
2025-07-09 | 2025-07-01 | 2025-07-17 | Madhu Sah | 83.134 | 4.8902 | TA419 | 34/0 | Completed
2025-07-09 | 2025-07-09 | 2025-07-18 | Radha Enterprises 1 | 65.023 | 6.5023 | TA419 | 29/0 | Completed
2025-07-10 | 2025-07-01 | 2025-07-17 | Madhu Sah | 83.134 | 4.8902 | TA419 | 34/0 | Completed
2025-07-10 | 2025-07-09 | 2025-07-18 | Radha Enterprises 1 | 65.023 | 6.5023 | TA419 | 29/0 | Completed
2025-07-11 | 2025-07-01 | 2025-07-17 | Madhu Sah | 83.134 | 4.8902 | TA419 | 34/0 | Completed
2025-07-11 | 2025-07-09 | 2025-07-18 | Radha Enterprises 1 | 65.023 | 6.5023 | TA419 | 29/0 | Completed
2025-07-12 | 2025-07-01 | 2025-07-17 | Madhu Sah | 83.134 | 4.8902 | TA419 | 34/0 | Completed
2025-07-12 | 2025-07-09 | 2025-07-18 | Radha Enterprises 1 | 65.023 | 6.5023 | TA419 | 29/0 | Completed
2025-07-13 | 2025-07-01 | 2025-07-17 | Madhu Sah | 83.134 | 4.8902 | TA419 | 34/0 | Completed
2025-07-13 | 2025-07-09 | 2025-07-18 | Radha Enterprises 1 | 65.023 | 6.5023 | TA419 | 29/0 | Completed
2025-07-14 | 2025-07-01 | 2025-07-17 | Madhu Sah | 83.134 | 4.8902 | TA419 | 34/0 | Completed
2025-07-14 | 2025-07-09 | 2025-07-18 | Radha Enterprises 1 | 65.023 | 6.5023 | TA419 | 29/0 | Completed
2025-07-15 | 2025-07-01 | 2025-07-17 | Madhu Sah | 83.134 | 4.8902 | TA419 | 34/0 | Completed
2025-07-15 | 2025-07-09 | 2025-07-18 | Radha Enterprises 1 | 65.023 | 6.5023 | TA419 | 29/0 | Completed
2025-07-16 | 2025-07-01 | 2025-07-17 | Madhu Sah | 83.134 | 4.8902 | TA419 | 34/0 | Completed
2025-07-16 | 2025-07-09 | 2025-07-18 | Radha Enterprises 1 | 65.023 | 6.5023 | TA419 | 29/0 | Completed
2025-07-17 | 2025-07-01 | 2025-07-17 | Madhu Sah | 83.134 | 4.8902 | TA419 | 34/0 | Completed
2025-07-17 | 2025-07-09 | 2025-07-18 | Radha Enterprises 1 | 65.023 | 6.5023 | TA419 | 29/0 | Completed
2025-07-18 | 2025-07-18 | 2025-07-24 | Madhu Sah | 36.16 | 5.1657 | TA419 | 34/1 | Completed
2025-07-18 | 2025-07-09 | 2025-07-18 | Radha Enterprises 1 | 65.023 | 6.5023 | TA419 | 29/0 | Completed
2025-07-19 | 2025-07-18 | 2025-07-24 | Madhu Sah | 36.16 | 5.1657 | TA419 | 34/1 | Completed
2025-07-19 | 2025-07-19 | 2025-07-26 | Radha Enterprises | 55.451 | 6.9314 | TA419 | 20/3 | Completed
2025-07-20 | 2025-07-18 | 2025-07-24 | Madhu Sah | 36.16 | 5.1657 | TA419 | 34/1 | Completed
2025-07-20 | 2025-07-19 | 2025-07-26 | Radha Enterprises | 55.451 | 6.9314 | TA419 | 20/3 | Completed
2025-07-21 | 2025-07-18 | 2025-07-24 | Madhu Sah | 36.16 | 5.1657 | TA419 | 34/1 | Completed
2025-07-21 | 2025-07-19 | 2025-07-26 | Radha Enterprises | 55.451 | 6.9314 | TA419 | 20/3 | Completed
2025-07-22 | 2025-07-18 | 2025-07-24 | Madhu Sah | 36.16 | 5.1657 | TA419 | 34/1 | Completed
2025-07-22 | 2025-07-19 | 2025-07-26 | Radha Enterprises | 55.451 | 6.9314 | TA419 | 20/3 | Completed
2025-07-23 | 2025-07-18 | 2025-07-24 | Madhu Sah | 36.16 | 5.1657 | TA419 | 34/1 | Completed
2025-07-23 | 2025-07-19 | 2025-07-26 | Radha Enterprises | 55.451 | 6.9314 | TA419 | 20/3 | Completed
2025-07-24 | 2025-07-18 | 2025-07-24 | Madhu Sah | 36.16 | 5.1657 | TA419 | 34/1 | Completed
2025-07-24 | 2025-07-19 | 2025-07-26 | Radha Enterprises | 55.451 | 6.9314 | TA419 | 20/3 | Completed
2025-07-25 | 2025-07-19 | 2025-07-26 | Radha Enterprises | 55.451 | 6.9314 | TA419 | 20/3 | Completed
2025-07-26 | 2025-07-26 | 2025-08-01 | Madhu Sah | 37.931 | 5.4187 | TA419 | 36/1 | Completed
2025-07-26 | 2025-07-19 | 2025-07-26 | Radha Enterprises | 55.451 | 6.9314 | TA419 | 20/3 | Completed
2025-07-27 | 2025-07-26 | 2025-08-01 | Madhu Sah | 37.931 | 5.4187 | TA419 | 36/1 | Completed
2025-07-28 | 2025-07-26 | 2025-08-01 | Madhu Sah | 37.931 | 5.4187 | TA419 | 36/1 | Completed
2025-07-28 | 2025-07-28 | 2025-08-03 | Radha Enterprises 1 | 35.602 | 5.086 | TA419 | 26/2 | Completed
2025-07-29 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-07-29 | 2025-07-26 | 2025-08-01 | Madhu Sah | 37.931 | 5.4187 | TA419 | 36/1 | Completed
2025-07-29 | 2025-07-28 | 2025-08-03 | Radha Enterprises 1 | 35.602 | 5.086 | TA419 | 26/2 | Completed
2025-07-30 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-07-30 | 2025-07-26 | 2025-08-01 | Madhu Sah | 37.931 | 5.4187 | TA419 | 36/1 | Completed
2025-07-30 | 2025-07-28 | 2025-08-03 | Radha Enterprises 1 | 35.602 | 5.086 | TA419 | 26/2 | Completed
2025-07-31 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-07-31 | 2025-07-26 | 2025-08-01 | Madhu Sah | 37.931 | 5.4187 | TA419 | 36/1 | Completed
2025-07-31 | 2025-07-28 | 2025-08-03 | Radha Enterprises 1 | 35.602 | 5.086 | TA419 | 26/2 | Completed
2025-08-01 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-01 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-01 | 2025-07-26 | 2025-08-01 | Madhu Sah | 37.931 | 5.4187 | TA419 | 36/1 | Completed
2025-08-01 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-01 | 2025-07-28 | 2025-08-03 | Radha Enterprises 1 | 35.602 | 5.086 | TA419 | 26/2 | Completed
2025-08-02 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-02 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-02 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-02 | 2025-08-02 | 2025-08-07 | Madhu Sah | 37.931 | 6.3218 | TA419 | 36/2 | Completed
2025-08-02 | 2025-07-28 | 2025-08-03 | Radha Enterprises 1 | 35.602 | 5.086 | TA419 | 26/2 | Completed
2025-08-03 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-03 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-03 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-03 | 2025-08-02 | 2025-08-07 | Madhu Sah | 37.931 | 6.3218 | TA419 | 36/2 | Completed
2025-08-03 | 2025-07-28 | 2025-08-03 | Radha Enterprises 1 | 35.602 | 5.086 | TA419 | 26/2 | Completed
2025-08-04 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-04 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-04 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-04 | 2025-08-02 | 2025-08-07 | Madhu Sah | 37.931 | 6.3218 | TA419 | 36/2 | Completed
2025-08-04 | 2025-08-04 | 2025-08-13 | Radha Enterprises | 65.023 | 6.5023 | TA419 | 11/1 | Completed
2025-08-05 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-05 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-05 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-05 | 2025-08-02 | 2025-08-07 | Madhu Sah | 37.931 | 6.3218 | TA419 | 36/2 | Completed
2025-08-05 | 2025-08-04 | 2025-08-13 | Radha Enterprises | 65.023 | 6.5023 | TA419 | 11/1 | Completed
2025-08-06 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-06 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-06 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-06 | 2025-08-02 | 2025-08-07 | Madhu Sah | 37.931 | 6.3218 | TA419 | 36/2 | Completed
2025-08-06 | 2025-08-04 | 2025-08-13 | Radha Enterprises | 65.023 | 6.5023 | TA419 | 11/1 | Completed
2025-08-07 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-07 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-07 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-07 | 2025-08-02 | 2025-08-07 | Madhu Sah | 37.931 | 6.3218 | TA419 | 36/2 | Completed
2025-08-07 | 2025-08-04 | 2025-08-13 | Radha Enterprises | 65.023 | 6.5023 | TA419 | 11/1 | Completed
2025-08-08 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-08 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-08 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-08 | 2025-08-04 | 2025-08-13 | Radha Enterprises | 65.023 | 6.5023 | TA419 | 11/1 | Completed
2025-08-09 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-09 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-09 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-09 | 2025-08-04 | 2025-08-13 | Radha Enterprises | 65.023 | 6.5023 | TA419 | 11/1 | Completed
2025-08-10 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-10 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-10 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-10 | 2025-08-04 | 2025-08-13 | Radha Enterprises | 65.023 | 6.5023 | TA419 | 11/1 | Completed
2025-08-11 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-11 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-11 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-11 | 2025-08-04 | 2025-08-13 | Radha Enterprises | 65.023 | 6.5023 | TA419 | 11/1 | Completed
2025-08-12 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-12 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-12 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-12 | 2025-08-12 | 2025-08-19 | Madhu Sah | 37.931 | 4.7414 | TA419 | 3/1 | Completed
2025-08-12 | 2025-08-04 | 2025-08-13 | Radha Enterprises | 65.023 | 6.5023 | TA419 | 11/1 | Completed
2025-08-13 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-13 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-13 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-13 | 2025-08-12 | 2025-08-19 | Madhu Sah | 37.931 | 4.7414 | TA419 | 3/1 | Completed
2025-08-13 | 2025-08-04 | 2025-08-13 | Radha Enterprises | 65.023 | 6.5023 | TA419 | 11/1 | Completed
2025-08-14 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-14 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-14 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-14 | 2025-08-12 | 2025-08-19 | Madhu Sah | 37.931 | 4.7414 | TA419 | 3/1 | Completed
2025-08-14 | 2025-08-14 | 2025-08-30 | Radha Enterprises | 124.95 | 7.35 | TA419 | 10/0 | Completed
2025-08-15 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-15 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-15 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-15 | 2025-08-12 | 2025-08-19 | Madhu Sah | 37.931 | 4.7414 | TA419 | 3/1 | Completed
2025-08-15 | 2025-08-15 | 2025-08-31 | Madhu Sah | 66.776 | 3.928 | TA419 | 0G/0 | Completed
2025-08-15 | 2025-08-14 | 2025-08-30 | Radha Enterprises | 124.95 | 7.35 | TA419 | 10/0 | Completed
2025-08-16 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-16 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-16 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-16 | 2025-08-12 | 2025-08-19 | Madhu Sah | 37.931 | 4.7414 | TA419 | 3/1 | Completed
2025-08-16 | 2025-08-15 | 2025-08-31 | Madhu Sah | 66.776 | 3.928 | TA419 | 0G/0 | Completed
2025-08-16 | 2025-08-14 | 2025-08-30 | Radha Enterprises | 124.95 | 7.35 | TA419 | 10/0 | Completed
2025-08-17 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-17 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-17 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-17 | 2025-08-12 | 2025-08-19 | Madhu Sah | 37.931 | 4.7414 | TA419 | 3/1 | Completed
2025-08-17 | 2025-08-15 | 2025-08-31 | Madhu Sah | 66.776 | 3.928 | TA419 | 0G/0 | Completed
2025-08-17 | 2025-08-14 | 2025-08-30 | Radha Enterprises | 124.95 | 7.35 | TA419 | 10/0 | Completed
2025-08-18 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-18 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-18 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-18 | 2025-08-12 | 2025-08-19 | Madhu Sah | 37.931 | 4.7414 | TA419 | 3/1 | Completed
2025-08-18 | 2025-08-15 | 2025-08-31 | Madhu Sah | 66.776 | 3.928 | TA419 | 0G/0 | Completed
2025-08-18 | 2025-08-14 | 2025-08-30 | Radha Enterprises | 124.95 | 7.35 | TA419 | 10/0 | Completed
2025-08-19 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-19 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-19 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-19 | 2025-08-12 | 2025-08-19 | Madhu Sah | 37.931 | 4.7414 | TA419 | 3/1 | Completed
2025-08-19 | 2025-08-15 | 2025-08-31 | Madhu Sah | 66.776 | 3.928 | TA419 | 0G/0 | Completed
2025-08-19 | 2025-08-14 | 2025-08-30 | Radha Enterprises | 124.95 | 7.35 | TA419 | 10/0 | Completed
2025-08-20 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-20 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-20 | 2025-08-20 | 2025-08-27 | Infinidea | 36.16 | 4.52 | TA419 | 0G/1 | Completed
2025-08-20 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-20 | 2025-08-15 | 2025-08-31 | Madhu Sah | 66.776 | 3.928 | TA419 | 0G/0 | Completed
2025-08-20 | 2025-08-14 | 2025-08-30 | Radha Enterprises | 124.95 | 7.35 | TA419 | 10/0 | Completed
2025-08-21 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-21 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-21 | 2025-08-20 | 2025-08-27 | Infinidea | 36.16 | 4.52 | TA419 | 0G/1 | Completed
2025-08-21 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-21 | 2025-08-15 | 2025-08-31 | Madhu Sah | 66.776 | 3.928 | TA419 | 0G/0 | Completed
2025-08-21 | 2025-08-14 | 2025-08-30 | Radha Enterprises | 124.95 | 7.35 | TA419 | 10/0 | Completed
2025-08-22 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-22 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-22 | 2025-08-20 | 2025-08-27 | Infinidea | 36.16 | 4.52 | TA419 | 0G/1 | Completed
2025-08-22 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-22 | 2025-08-15 | 2025-08-31 | Madhu Sah | 66.776 | 3.928 | TA419 | 0G/0 | Completed
2025-08-22 | 2025-08-14 | 2025-08-30 | Radha Enterprises | 124.95 | 7.35 | TA419 | 10/0 | Completed
2025-08-23 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-23 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-23 | 2025-08-20 | 2025-08-27 | Infinidea | 36.16 | 4.52 | TA419 | 0G/1 | Completed
2025-08-23 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-23 | 2025-08-15 | 2025-08-31 | Madhu Sah | 66.776 | 3.928 | TA419 | 0G/0 | Completed
2025-08-23 | 2025-08-14 | 2025-08-30 | Radha Enterprises | 124.95 | 7.35 | TA419 | 10/0 | Completed
2025-08-24 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-24 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-24 | 2025-08-20 | 2025-08-27 | Infinidea | 36.16 | 4.52 | TA419 | 0G/1 | Completed
2025-08-24 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-24 | 2025-08-15 | 2025-08-31 | Madhu Sah | 66.776 | 3.928 | TA419 | 0G/0 | Completed
2025-08-24 | 2025-08-14 | 2025-08-30 | Radha Enterprises | 124.95 | 7.35 | TA419 | 10/0 | Completed
2025-08-25 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-25 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-25 | 2025-08-20 | 2025-08-27 | Infinidea | 36.16 | 4.52 | TA419 | 0G/1 | Completed
2025-08-25 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-25 | 2025-08-15 | 2025-08-31 | Madhu Sah | 66.776 | 3.928 | TA419 | 0G/0 | Completed
2025-08-25 | 2025-08-14 | 2025-08-30 | Radha Enterprises | 124.95 | 7.35 | TA419 | 10/0 | Completed
2025-08-26 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-26 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-26 | 2025-08-20 | 2025-08-27 | Infinidea | 36.16 | 4.52 | TA419 | 0G/1 | Completed
2025-08-26 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-26 | 2025-08-15 | 2025-08-31 | Madhu Sah | 66.776 | 3.928 | TA419 | 0G/0 | Completed
2025-08-26 | 2025-08-14 | 2025-08-30 | Radha Enterprises | 124.95 | 7.35 | TA419 | 10/0 | Completed
2025-08-27 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-27 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-27 | 2025-08-20 | 2025-08-27 | Infinidea | 36.16 | 4.52 | TA419 | 0G/1 | Completed
2025-08-27 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-27 | 2025-08-15 | 2025-08-31 | Madhu Sah | 66.776 | 3.928 | TA419 | 0G/0 | Completed
2025-08-27 | 2025-08-14 | 2025-08-30 | Radha Enterprises | 124.95 | 7.35 | TA419 | 10/0 | Completed
2025-08-28 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-28 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-28 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-28 | 2025-08-15 | 2025-08-31 | Madhu Sah | 66.776 | 3.928 | TA419 | 0G/0 | Completed
2025-08-28 | 2025-08-14 | 2025-08-30 | Radha Enterprises | 124.95 | 7.35 | TA419 | 10/0 | Completed
2025-08-29 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-29 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-29 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-29 | 2025-08-15 | 2025-08-31 | Madhu Sah | 66.776 | 3.928 | TA419 | 0G/0 | Completed
2025-08-29 | 2025-08-14 | 2025-08-30 | Radha Enterprises | 124.95 | 7.35 | TA419 | 10/0 | Completed
2025-08-30 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-30 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-30 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-30 | 2025-08-15 | 2025-08-31 | Madhu Sah | 66.776 | 3.928 | TA419 | 0G/0 | Completed
2025-08-30 | 2025-08-14 | 2025-08-30 | Radha Enterprises | 124.95 | 7.35 | TA419 | 10/0 | Completed
2025-08-31 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-08-31 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-08-31 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-31 | 2025-08-15 | 2025-08-31 | Madhu Sah | 66.776 | 3.928 | TA419 | 0G/0 | Completed
2025-08-31 | 2025-08-31 | 2025-09-07 | Radha Enterprises | 66.776 | 8.347 | TA419 | 11/2 | Completed
2025-09-01 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-09-01 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-09-01 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-09-01 | 2025-08-31 | 2025-09-07 | Radha Enterprises | 66.776 | 8.347 | TA419 | 11/2 | Completed
2025-09-02 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-09-02 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-09-02 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-09-02 | 2025-08-31 | 2025-09-07 | Radha Enterprises | 66.776 | 8.347 | TA419 | 11/2 | Completed
2025-09-03 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-09-03 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-09-03 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-09-03 | 2025-08-31 | 2025-09-07 | Radha Enterprises | 66.776 | 8.347 | TA419 | 11/2 | Completed
2025-09-04 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-09-04 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-09-04 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-09-04 | 2025-08-31 | 2025-09-07 | Radha Enterprises | 66.776 | 8.347 | TA419 | 11/2 | Completed
2025-09-05 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-09-05 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-09-05 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-09-05 | 2025-08-31 | 2025-09-07 | Radha Enterprises | 66.776 | 8.347 | TA419 | 11/2 | Completed
2025-09-06 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-09-06 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-09-06 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-09-06 | 2025-08-31 | 2025-09-07 | Radha Enterprises | 66.776 | 8.347 | TA419 | 11/2 | Completed
2025-09-07 | 2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-09-07 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-09-07 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-09-07 | 2025-08-31 | 2025-09-07 | Radha Enterprises | 66.776 | 8.347 | TA419 | 11/2 | Completed
2025-09-07 | 2025-09-07 | 2025-09-13 | Radha Enterprises | 36.16 | 5.1657 | TA419 | 12/2 | Completed
2025-09-08 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-09-08 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-09-08 | 2025-09-07 | 2025-09-13 | Radha Enterprises | 36.16 | 5.1657 | TA419 | 12/2 | Completed
2025-09-09 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-09-09 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-09-09 | 2025-09-07 | 2025-09-13 | Radha Enterprises | 36.16 | 5.1657 | TA419 | 12/2 | Completed
2025-09-10 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-09-10 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-09-10 | 2025-09-07 | 2025-09-13 | Radha Enterprises | 36.16 | 5.1657 | TA419 | 12/2 | Completed
2025-09-11 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-09-11 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-09-11 | 2025-09-07 | 2025-09-13 | Radha Enterprises | 36.16 | 5.1657 | TA419 | 12/2 | Completed
2025-09-12 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-09-12 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-09-12 | 2025-09-07 | 2025-09-13 | Radha Enterprises | 36.16 | 5.1657 | TA419 | 12/2 | Completed
2025-09-13 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-09-13 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-09-13 | 2025-09-07 | 2025-09-13 | Radha Enterprises | 36.16 | 5.1657 | TA419 | 12/2 | Completed
2025-09-14 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-09-14 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-09-14 | 2025-09-14 | 2025-10-05 | Radha Enterprises | 137.046 | 6.2294 | TA419 | 21/0 | Completed
2025-09-15 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-09-15 | 2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-09-15 | 2025-09-15 | 2025-09-27 | Madhu Sah | 59.501 | 4.577 | TA419 | 4/0 | Completed
2025-09-15 | 2025-09-14 | 2025-10-05 | Radha Enterprises | 137.046 | 6.2294 | TA419 | 21/0 | Completed
2025-09-16 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-09-16 | 2025-09-15 | 2025-09-27 | Madhu Sah | 59.501 | 4.577 | TA419 | 4/0 | Completed
2025-09-16 | 2025-09-14 | 2025-10-05 | Radha Enterprises | 137.046 | 6.2294 | TA419 | 21/0 | Completed
2025-09-17 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-09-17 | 2025-09-15 | 2025-09-27 | Madhu Sah | 59.501 | 4.577 | TA419 | 4/0 | Completed
2025-09-17 | 2025-09-14 | 2025-10-05 | Radha Enterprises | 137.046 | 6.2294 | TA419 | 21/0 | Completed
2025-09-18 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-09-18 | 2025-09-15 | 2025-09-27 | Madhu Sah | 59.501 | 4.577 | TA419 | 4/0 | Completed
2025-09-18 | 2025-09-14 | 2025-10-05 | Radha Enterprises | 137.046 | 6.2294 | TA419 | 21/0 | Completed
2025-09-19 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-09-19 | 2025-09-15 | 2025-09-27 | Madhu Sah | 59.501 | 4.577 | TA419 | 4/0 | Completed
2025-09-19 | 2025-09-14 | 2025-10-05 | Radha Enterprises | 137.046 | 6.2294 | TA419 | 21/0 | Completed
2025-09-20 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-09-20 | 2025-09-15 | 2025-09-27 | Madhu Sah | 59.501 | 4.577 | TA419 | 4/0 | Completed
2025-09-20 | 2025-09-14 | 2025-10-05 | Radha Enterprises | 137.046 | 6.2294 | TA419 | 21/0 | Completed
2025-09-21 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-09-21 | 2025-09-15 | 2025-09-27 | Madhu Sah | 59.501 | 4.577 | TA419 | 4/0 | Completed
2025-09-21 | 2025-09-14 | 2025-10-05 | Radha Enterprises | 137.046 | 6.2294 | TA419 | 21/0 | Completed
2025-09-22 | 2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
2025-09-22 | 2025-09-15 | 2025-09-27 | Madhu Sah | 59.501 | 4.577 | TA419 | 4/0 | Completed
2025-09-22 | 2025-09-14 | 2025-10-05 | Radha Enterprises | 137.046 | 6.2294 | TA419 | 21/0 | Completed
2025-09-23 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-09-23 | 2025-09-15 | 2025-09-27 | Madhu Sah | 59.501 | 4.577 | TA419 | 4/0 | Completed
2025-09-23 | 2025-09-14 | 2025-10-05 | Radha Enterprises | 137.046 | 6.2294 | TA419 | 21/0 | Completed
2025-09-24 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-09-24 | 2025-09-15 | 2025-09-27 | Madhu Sah | 59.501 | 4.577 | TA419 | 4/0 | Completed
2025-09-24 | 2025-09-14 | 2025-10-05 | Radha Enterprises | 137.046 | 6.2294 | TA419 | 21/0 | Completed
2025-09-25 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-09-25 | 2025-09-15 | 2025-09-27 | Madhu Sah | 59.501 | 4.577 | TA419 | 4/0 | Completed
2025-09-25 | 2025-09-14 | 2025-10-05 | Radha Enterprises | 137.046 | 6.2294 | TA419 | 21/0 | Completed
2025-09-26 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-09-26 | 2025-09-15 | 2025-09-27 | Madhu Sah | 59.501 | 4.577 | TA419 | 4/0 | Completed
2025-09-26 | 2025-09-14 | 2025-10-05 | Radha Enterprises | 137.046 | 6.2294 | TA419 | 21/0 | Completed
2025-09-27 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-09-27 | 2025-09-15 | 2025-09-27 | Madhu Sah | 59.501 | 4.577 | TA419 | 4/0 | Completed
2025-09-27 | 2025-09-14 | 2025-10-05 | Radha Enterprises | 137.046 | 6.2294 | TA419 | 21/0 | Completed
2025-09-28 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-09-28 | 2025-09-28 | 2025-10-05 | Madhu Sah | 43.804 | 5.4755 | TA419 | 3/4 | Completed
2025-09-28 | 2025-09-14 | 2025-10-05 | Radha Enterprises | 137.046 | 6.2294 | TA419 | 21/0 | Completed
2025-09-29 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-09-29 | 2025-09-28 | 2025-10-05 | Madhu Sah | 43.804 | 5.4755 | TA419 | 3/4 | Completed
2025-09-29 | 2025-09-14 | 2025-10-05 | Radha Enterprises | 137.046 | 6.2294 | TA419 | 21/0 | Completed
2025-09-30 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-09-30 | 2025-09-28 | 2025-10-05 | Madhu Sah | 43.804 | 5.4755 | TA419 | 3/4 | Completed
2025-09-30 | 2025-09-14 | 2025-10-05 | Radha Enterprises | 137.046 | 6.2294 | TA419 | 21/0 | Completed
2025-10-01 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-01 | 2025-09-28 | 2025-10-05 | Madhu Sah | 43.804 | 5.4755 | TA419 | 3/4 | Completed
2025-10-01 | 2025-09-14 | 2025-10-05 | Radha Enterprises | 137.046 | 6.2294 | TA419 | 21/0 | Completed
2025-10-02 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-02 | 2025-09-28 | 2025-10-05 | Madhu Sah | 43.804 | 5.4755 | TA419 | 3/4 | Completed
2025-10-02 | 2025-09-14 | 2025-10-05 | Radha Enterprises | 137.046 | 6.2294 | TA419 | 21/0 | Completed
2025-10-03 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-03 | 2025-09-28 | 2025-10-05 | Madhu Sah | 43.804 | 5.4755 | TA419 | 3/4 | Completed
2025-10-03 | 2025-09-14 | 2025-10-05 | Radha Enterprises | 137.046 | 6.2294 | TA419 | 21/0 | Completed
2025-10-04 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-04 | 2025-09-28 | 2025-10-05 | Madhu Sah | 43.804 | 5.4755 | TA419 | 3/4 | Completed
2025-10-04 | 2025-09-14 | 2025-10-05 | Radha Enterprises | 137.046 | 6.2294 | TA419 | 21/0 | Completed
2025-10-05 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-05 | 2025-09-28 | 2025-10-05 | Madhu Sah | 43.804 | 5.4755 | TA419 | 3/4 | Completed
2025-10-05 | 2025-09-14 | 2025-10-05 | Radha Enterprises | 137.046 | 6.2294 | TA419 | 21/0 | Completed
2025-10-06 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-06 | 2025-10-06 | 2025-10-12 | Madhu Sah | 35.602 | 5.086 | TA419 | 3/3 | Completed
2025-10-06 | 2025-10-06 | 2025-10-18 | Radha Enterprises 1 | 99.779 | 7.6753 | TA419 | 26/0 | Completed
2025-10-07 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-07 | 2025-10-06 | 2025-10-12 | Madhu Sah | 35.602 | 5.086 | TA419 | 3/3 | Completed
2025-10-07 | 2025-10-06 | 2025-10-18 | Radha Enterprises 1 | 99.779 | 7.6753 | TA419 | 26/0 | Completed
2025-10-08 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-08 | 2025-10-06 | 2025-10-12 | Madhu Sah | 35.602 | 5.086 | TA419 | 3/3 | Completed
2025-10-08 | 2025-10-06 | 2025-10-18 | Radha Enterprises 1 | 99.779 | 7.6753 | TA419 | 26/0 | Completed
2025-10-09 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-09 | 2025-10-06 | 2025-10-12 | Madhu Sah | 35.602 | 5.086 | TA419 | 3/3 | Completed
2025-10-09 | 2025-10-06 | 2025-10-18 | Radha Enterprises 1 | 99.779 | 7.6753 | TA419 | 26/0 | Completed
2025-10-10 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-10 | 2025-10-06 | 2025-10-12 | Madhu Sah | 35.602 | 5.086 | TA419 | 3/3 | Completed
2025-10-10 | 2025-10-06 | 2025-10-18 | Radha Enterprises 1 | 99.779 | 7.6753 | TA419 | 26/0 | Completed
2025-10-11 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-11 | 2025-10-06 | 2025-10-12 | Madhu Sah | 35.602 | 5.086 | TA419 | 3/3 | Completed
2025-10-11 | 2025-10-06 | 2025-10-18 | Radha Enterprises 1 | 99.779 | 7.6753 | TA419 | 26/0 | Completed
2025-10-12 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-12 | 2025-10-06 | 2025-10-12 | Madhu Sah | 35.602 | 5.086 | TA419 | 3/3 | Completed
2025-10-12 | 2025-10-12 | 2025-10-26 | Poonam Kumari | 69.376 | 4.6251 | TA419 | 16/0 | Completed
2025-10-12 | 2025-10-06 | 2025-10-18 | Radha Enterprises 1 | 99.779 | 7.6753 | TA419 | 26/0 | Completed
2025-10-13 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-13 | 2025-10-12 | 2025-10-26 | Poonam Kumari | 69.376 | 4.6251 | TA419 | 16/0 | Completed
2025-10-13 | 2025-10-06 | 2025-10-18 | Radha Enterprises 1 | 99.779 | 7.6753 | TA419 | 26/0 | Completed
2025-10-14 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-14 | 2025-10-12 | 2025-10-26 | Poonam Kumari | 69.376 | 4.6251 | TA419 | 16/0 | Completed
2025-10-14 | 2025-10-14 | 2025-10-27 | Poonam Kumari 2 | 43.804 | 3.1289 | TA419 | 31/2 | Completed
2025-10-14 | 2025-10-06 | 2025-10-18 | Radha Enterprises 1 | 99.779 | 7.6753 | TA419 | 26/0 | Completed
2025-10-15 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-15 | 2025-10-12 | 2025-10-26 | Poonam Kumari | 69.376 | 4.6251 | TA419 | 16/0 | Completed
2025-10-15 | 2025-10-14 | 2025-10-27 | Poonam Kumari 2 | 43.804 | 3.1289 | TA419 | 31/2 | Completed
2025-10-15 | 2025-10-06 | 2025-10-18 | Radha Enterprises 1 | 99.779 | 7.6753 | TA419 | 26/0 | Completed
2025-10-16 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-16 | 2025-10-16 | 2025-10-23 | Jwala Singh | 36.16 | 4.52 | TA419 | 36/7 | Completed
2025-10-16 | 2025-10-12 | 2025-10-26 | Poonam Kumari | 69.376 | 4.6251 | TA419 | 16/0 | Completed
2025-10-16 | 2025-10-14 | 2025-10-27 | Poonam Kumari 2 | 43.804 | 3.1289 | TA419 | 31/2 | Completed
2025-10-16 | 2025-10-06 | 2025-10-18 | Radha Enterprises 1 | 99.779 | 7.6753 | TA419 | 26/0 | Completed
2025-10-17 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-17 | 2025-10-16 | 2025-10-23 | Jwala Singh | 36.16 | 4.52 | TA419 | 36/7 | Completed
2025-10-17 | 2025-10-12 | 2025-10-26 | Poonam Kumari | 69.376 | 4.6251 | TA419 | 16/0 | Completed
2025-10-17 | 2025-10-14 | 2025-10-27 | Poonam Kumari 2 | 43.804 | 3.1289 | TA419 | 31/2 | Completed
2025-10-17 | 2025-10-06 | 2025-10-18 | Radha Enterprises 1 | 99.779 | 7.6753 | TA419 | 26/0 | Completed
2025-10-18 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-18 | 2025-10-16 | 2025-10-23 | Jwala Singh | 36.16 | 4.52 | TA419 | 36/7 | Completed
2025-10-18 | 2025-10-12 | 2025-10-26 | Poonam Kumari | 69.376 | 4.6251 | TA419 | 16/0 | Completed
2025-10-18 | 2025-10-14 | 2025-10-27 | Poonam Kumari 2 | 43.804 | 3.1289 | TA419 | 31/2 | Completed
2025-10-18 | 2025-10-06 | 2025-10-18 | Radha Enterprises 1 | 99.779 | 7.6753 | TA419 | 26/0 | Completed
2025-10-19 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-19 | 2025-10-16 | 2025-10-23 | Jwala Singh | 36.16 | 4.52 | TA419 | 36/7 | Completed
2025-10-19 | 2025-10-12 | 2025-10-26 | Poonam Kumari | 69.376 | 4.6251 | TA419 | 16/0 | Completed
2025-10-19 | 2025-10-14 | 2025-10-27 | Poonam Kumari 2 | 43.804 | 3.1289 | TA419 | 31/2 | Completed
2025-10-20 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-20 | 2025-10-16 | 2025-10-23 | Jwala Singh | 36.16 | 4.52 | TA419 | 36/7 | Completed
2025-10-20 | 2025-10-12 | 2025-10-26 | Poonam Kumari | 69.376 | 4.6251 | TA419 | 16/0 | Completed
2025-10-20 | 2025-10-14 | 2025-10-27 | Poonam Kumari 2 | 43.804 | 3.1289 | TA419 | 31/2 | Completed
2025-10-21 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-21 | 2025-10-16 | 2025-10-23 | Jwala Singh | 36.16 | 4.52 | TA419 | 36/7 | Completed
2025-10-21 | 2025-10-12 | 2025-10-26 | Poonam Kumari | 69.376 | 4.6251 | TA419 | 16/0 | Completed
2025-10-21 | 2025-10-14 | 2025-10-27 | Poonam Kumari 2 | 43.804 | 3.1289 | TA419 | 31/2 | Completed
2025-10-22 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-22 | 2025-10-16 | 2025-10-23 | Jwala Singh | 36.16 | 4.52 | TA419 | 36/7 | Completed
2025-10-22 | 2025-10-12 | 2025-10-26 | Poonam Kumari | 69.376 | 4.6251 | TA419 | 16/0 | Completed
2025-10-22 | 2025-10-14 | 2025-10-27 | Poonam Kumari 2 | 43.804 | 3.1289 | TA419 | 31/2 | Completed
2025-10-23 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-23 | 2025-10-16 | 2025-10-23 | Jwala Singh | 36.16 | 4.52 | TA419 | 36/7 | Completed
2025-10-23 | 2025-10-23 | 2025-10-30 | Jwala Singh | 36.16 | 4.52 | TA419 | 36/6 | Completed
2025-10-23 | 2025-10-12 | 2025-10-26 | Poonam Kumari | 69.376 | 4.6251 | TA419 | 16/0 | Completed
2025-10-23 | 2025-10-14 | 2025-10-27 | Poonam Kumari 2 | 43.804 | 3.1289 | TA419 | 31/2 | Completed
2025-10-24 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-24 | 2025-10-23 | 2025-10-30 | Jwala Singh | 36.16 | 4.52 | TA419 | 36/6 | Completed
2025-10-24 | 2025-10-12 | 2025-10-26 | Poonam Kumari | 69.376 | 4.6251 | TA419 | 16/0 | Completed
2025-10-24 | 2025-10-14 | 2025-10-27 | Poonam Kumari 2 | 43.804 | 3.1289 | TA419 | 31/2 | Completed
2025-10-25 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-25 | 2025-10-23 | 2025-10-30 | Jwala Singh | 36.16 | 4.52 | TA419 | 36/6 | Completed
2025-10-25 | 2025-10-12 | 2025-10-26 | Poonam Kumari | 69.376 | 4.6251 | TA419 | 16/0 | Completed
2025-10-25 | 2025-10-14 | 2025-10-27 | Poonam Kumari 2 | 43.804 | 3.1289 | TA419 | 31/2 | Completed
2025-10-26 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-26 | 2025-10-23 | 2025-10-30 | Jwala Singh | 36.16 | 4.52 | TA419 | 36/6 | Completed
2025-10-26 | 2025-10-26 | 2025-11-12 | Nan | 73.245 | 4.0692 | TA419 | 30/0 | Completed
2025-10-26 | 2025-10-12 | 2025-10-26 | Poonam Kumari | 69.376 | 4.6251 | TA419 | 16/0 | Completed
2025-10-26 | 2025-10-14 | 2025-10-27 | Poonam Kumari 2 | 43.804 | 3.1289 | TA419 | 31/2 | Completed
2025-10-27 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-27 | 2025-10-23 | 2025-10-30 | Jwala Singh | 36.16 | 4.52 | TA419 | 36/6 | Completed
2025-10-27 | 2025-10-26 | 2025-11-12 | Nan | 73.245 | 4.0692 | TA419 | 30/0 | Completed
2025-10-27 | 2025-10-14 | 2025-10-27 | Poonam Kumari 2 | 43.804 | 3.1289 | TA419 | 31/2 | Completed
2025-10-27 | 2025-10-27 | 2025-11-13 | Pumam Kumari 1 | 77.077 | 4.2821 | TA419 | 35/0 | Completed
2025-10-28 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-28 | 2025-10-23 | 2025-10-30 | Jwala Singh | 36.16 | 4.52 | TA419 | 36/6 | Completed
2025-10-28 | 2025-10-26 | 2025-11-12 | Nan | 73.245 | 4.0692 | TA419 | 30/0 | Completed
2025-10-28 | 2025-10-27 | 2025-11-13 | Pumam Kumari 1 | 77.077 | 4.2821 | TA419 | 35/0 | Completed
2025-10-29 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-29 | 2025-10-23 | 2025-10-30 | Jwala Singh | 36.16 | 4.52 | TA419 | 36/6 | Completed
2025-10-29 | 2025-10-26 | 2025-11-12 | Nan | 73.245 | 4.0692 | TA419 | 30/0 | Completed
2025-10-29 | 2025-10-27 | 2025-11-13 | Pumam Kumari 1 | 77.077 | 4.2821 | TA419 | 35/0 | Completed
2025-10-30 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-30 | 2025-10-23 | 2025-10-30 | Jwala Singh | 36.16 | 4.52 | TA419 | 36/6 | Completed
2025-10-30 | 2025-10-26 | 2025-11-12 | Nan | 73.245 | 4.0692 | TA419 | 30/0 | Completed
2025-10-30 | 2025-10-27 | 2025-11-13 | Pumam Kumari 1 | 77.077 | 4.2821 | TA419 | 35/0 | Completed
2025-10-31 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-10-31 | 2025-10-26 | 2025-11-12 | Nan | 73.245 | 4.0692 | TA419 | 30/0 | Completed
2025-10-31 | 2025-10-27 | 2025-11-13 | Pumam Kumari 1 | 77.077 | 4.2821 | TA419 | 35/0 | Completed
2025-11-01 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-11-01 | 2025-11-01 | 2025-11-08 | Jwala Singh | 36.16 | 4.52 | TA419 | 36/8 | Completed
2025-11-01 | 2025-10-26 | 2025-11-12 | Nan | 73.245 | 4.0692 | TA419 | 30/0 | Completed
2025-11-01 | 2025-10-27 | 2025-11-13 | Pumam Kumari 1 | 77.077 | 4.2821 | TA419 | 35/0 | Completed
2025-11-02 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-11-02 | 2025-11-01 | 2025-11-08 | Jwala Singh | 36.16 | 4.52 | TA419 | 36/8 | Completed
2025-11-02 | 2025-10-26 | 2025-11-12 | Nan | 73.245 | 4.0692 | TA419 | 30/0 | Completed
2025-11-02 | 2025-10-27 | 2025-11-13 | Pumam Kumari 1 | 77.077 | 4.2821 | TA419 | 35/0 | Completed
2025-11-03 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-11-03 | 2025-11-01 | 2025-11-08 | Jwala Singh | 36.16 | 4.52 | TA419 | 36/8 | Completed
2025-11-03 | 2025-10-26 | 2025-11-12 | Nan | 73.245 | 4.0692 | TA419 | 30/0 | Completed
2025-11-03 | 2025-10-27 | 2025-11-13 | Pumam Kumari 1 | 77.077 | 4.2821 | TA419 | 35/0 | Completed
2025-11-04 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-11-04 | 2025-11-01 | 2025-11-08 | Jwala Singh | 36.16 | 4.52 | TA419 | 36/8 | Completed
2025-11-04 | 2025-10-26 | 2025-11-12 | Nan | 73.245 | 4.0692 | TA419 | 30/0 | Completed
2025-11-04 | 2025-10-27 | 2025-11-13 | Pumam Kumari 1 | 77.077 | 4.2821 | TA419 | 35/0 | Completed
2025-11-05 | 2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-11-05 | 2025-11-01 | 2025-11-08 | Jwala Singh | 36.16 | 4.52 | TA419 | 36/8 | Completed
2025-11-05 | 2025-10-26 | 2025-11-12 | Nan | 73.245 | 4.0692 | TA419 | 30/0 | Completed
2025-11-05 | 2025-10-27 | 2025-11-13 | Pumam Kumari 1 | 77.077 | 4.2821 | TA419 | 35/0 | Completed
2025-11-06 | 2025-11-01 | 2025-11-08 | Jwala Singh | 36.16 | 4.52 | TA419 | 36/8 | Completed
2025-11-06 | 2025-10-26 | 2025-11-12 | Nan | 73.245 | 4.0692 | TA419 | 30/0 | Completed
2025-11-06 | 2025-10-27 | 2025-11-13 | Pumam Kumari 1 | 77.077 | 4.2821 | TA419 | 35/0 | Completed
2025-11-07 | 2025-11-01 | 2025-11-08 | Jwala Singh | 36.16 | 4.52 | TA419 | 36/8 | Completed
2025-11-07 | 2025-10-26 | 2025-11-12 | Nan | 73.245 | 4.0692 | TA419 | 30/0 | Completed
2025-11-07 | 2025-10-27 | 2025-11-13 | Pumam Kumari 1 | 77.077 | 4.2821 | TA419 | 35/0 | Completed
2025-11-08 | 2025-11-01 | 2025-11-08 | Jwala Singh | 36.16 | 4.52 | TA419 | 36/8 | Completed
2025-11-08 | 2025-11-08 | 2025-11-14 | Jwala Singh | 37.138 | 5.3054 | TA419 | 41/5 | Completed
2025-11-08 | 2025-11-08 | 2025-11-16 | Madhu Sah | 37.138 | 4.1264 | TA419 | 40/5 | Completed
2025-11-08 | 2025-10-26 | 2025-11-12 | Nan | 73.245 | 4.0692 | TA419 | 30/0 | Completed
2025-11-08 | 2025-10-27 | 2025-11-13 | Pumam Kumari 1 | 77.077 | 4.2821 | TA419 | 35/0 | Completed
2025-11-09 | 2025-11-08 | 2025-11-14 | Jwala Singh | 37.138 | 5.3054 | TA419 | 41/5 | Completed
2025-11-09 | 2025-11-08 | 2025-11-16 | Madhu Sah | 37.138 | 4.1264 | TA419 | 40/5 | Completed
2025-11-09 | 2025-10-26 | 2025-11-12 | Nan | 73.245 | 4.0692 | TA419 | 30/0 | Completed
2025-11-09 | 2025-10-27 | 2025-11-13 | Pumam Kumari 1 | 77.077 | 4.2821 | TA419 | 35/0 | Completed
2025-11-10 | 2025-11-08 | 2025-11-14 | Jwala Singh | 37.138 | 5.3054 | TA419 | 41/5 | Completed
2025-11-10 | 2025-11-08 | 2025-11-16 | Madhu Sah | 37.138 | 4.1264 | TA419 | 40/5 | Completed
2025-11-10 | 2025-10-26 | 2025-11-12 | Nan | 73.245 | 4.0692 | TA419 | 30/0 | Completed
2025-11-10 | 2025-10-27 | 2025-11-13 | Pumam Kumari 1 | 77.077 | 4.2821 | TA419 | 35/0 | Completed
2025-11-11 | 2025-11-08 | 2025-11-14 | Jwala Singh | 37.138 | 5.3054 | TA419 | 41/5 | Completed
2025-11-11 | 2025-11-08 | 2025-11-16 | Madhu Sah | 37.138 | 4.1264 | TA419 | 40/5 | Completed
2025-11-11 | 2025-10-26 | 2025-11-12 | Nan | 73.245 | 4.0692 | TA419 | 30/0 | Completed
2025-11-11 | 2025-10-27 | 2025-11-13 | Pumam Kumari 1 | 77.077 | 4.2821 | TA419 | 35/0 | Completed
2025-11-12 | 2025-11-08 | 2025-11-14 | Jwala Singh | 37.138 | 5.3054 | TA419 | 41/5 | Completed
2025-11-12 | 2025-11-08 | 2025-11-16 | Madhu Sah | 37.138 | 4.1264 | TA419 | 40/5 | Completed
2025-11-12 | 2025-10-26 | 2025-11-12 | Nan | 73.245 | 4.0692 | TA419 | 30/0 | Completed
2025-11-12 | 2025-10-27 | 2025-11-13 | Pumam Kumari 1 | 77.077 | 4.2821 | TA419 | 35/0 | Completed
2025-11-13 | 2025-11-08 | 2025-11-14 | Jwala Singh | 37.138 | 5.3054 | TA419 | 41/5 | Completed
2025-11-13 | 2025-11-08 | 2025-11-16 | Madhu Sah | 37.138 | 4.1264 | TA419 | 40/5 | Completed
2025-11-13 | 2025-10-27 | 2025-11-13 | Pumam Kumari 1 | 77.077 | 4.2821 | TA419 | 35/0 | Completed
2025-11-14 | 2025-11-08 | 2025-11-14 | Jwala Singh | 37.138 | 5.3054 | TA419 | 41/5 | Completed
2025-11-14 | 2025-11-08 | 2025-11-16 | Madhu Sah | 37.138 | 4.1264 | TA419 | 40/5 | Completed
2025-11-15 | 2025-11-08 | 2025-11-16 | Madhu Sah | 37.138 | 4.1264 | TA419 | 40/5 | Completed
2025-11-16 | 2025-11-08 | 2025-11-16 | Madhu Sah | 37.138 | 4.1264 | TA419 | 40/5 | Completed
2024-07-10 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-11 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-12 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-13 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-14 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-15 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-16 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-17 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-18 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-18 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-19 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-19 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-20 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-21 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-22 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-23 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-24 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-25 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-26 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-27 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-27 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-07-28 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-28 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-07-29 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-07-30 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-07-31 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-08-01 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-08-02 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-08-02 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-03 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-08-03 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-04 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-05 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-06 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-07 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-08 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-09 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-09 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-10 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-11 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-12 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-13 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-14 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-16 | 2024-08-16 | 2024-08-18 | Khatan | 36.37 | 12.1233 | TA421 | 26/3 | Completed
2024-08-17 | 2024-08-16 | 2024-08-18 | Khatan | 36.37 | 12.1233 | TA421 | 26/3 | Completed
2024-08-18 | 2024-08-16 | 2024-08-18 | Khatan | 36.37 | 12.1233 | TA421 | 26/3 | Completed
2024-08-19 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-20 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-21 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-22 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-22 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-23 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-23 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-23 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-24 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-24 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-24 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-25 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-25 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-26 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-26 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-27 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-27 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-28 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-28 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-29 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-29 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-08-29 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-08-29 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-30 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-08-30 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-08-30 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-31 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-08-31 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-08-31 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-09-01 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-01 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-01 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-09-02 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-02 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-02 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-09-03 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-03 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-03 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-09-04 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-04 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-04 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-09-05 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-05 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-05 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-09-06 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-06 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-06 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-09-07 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-07 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-09-08 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-08 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-09-09 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-09 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-10 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-10 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-11 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-11 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-12 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-12 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-12 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-13 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-13 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-14 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-14 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-14 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-14 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-15 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-15 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-15 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-15 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-16 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-16 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-16 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-16 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-17 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-17 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-17 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-17 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-18 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-18 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-18 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-18 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-19 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-19 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-19 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-19 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-19 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-20 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-20 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-20 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-20 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-21 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-21 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-21 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-21 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-21 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-22 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-22 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-22 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-22 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-23 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-23 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-23 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-23 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-24 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-24 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-24 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-24 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-25 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-25 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-25 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-25 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-26 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-26 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-26 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-26 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-26 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-09-27 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-27 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-27 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-27 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-27 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-09-28 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-28 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-28 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-28 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-28 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-09-29 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-29 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-09-29 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-29 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-29 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-09-30 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-09-30 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-30 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-30 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-10-01 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-01 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-10-01 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-01 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-10-01 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-01 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-10-02 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-02 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-10-02 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-02 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-10-02 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-02 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-10-03 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-03 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-10-03 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-03 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-03 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-10-03 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-03 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-10-04 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-04 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-04 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-04 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-10-04 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-05 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-05 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-05 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-05 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-05 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-05 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-06 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-06 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-06 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-06 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-06 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-06 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-07 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-07 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-07 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-07 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-07 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-07 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-08 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-08 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-08 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-08 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-08 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-09 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-09 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-09 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-09 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-09 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-10 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-10 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-10 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-10 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-10 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-11 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-11 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-11 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-11 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-11 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-12 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-12 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-12 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-12 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-12 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-13 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-13 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-13 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-13 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-13 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-14 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-14 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-14 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-14 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-14 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-15 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-15 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-15 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-16 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-16 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-16 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-16 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-16 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-17 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-17 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-17 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-17 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-17 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-17 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-18 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-18 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-18 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-18 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-18 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-18 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-19 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-19 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-19 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-19 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-19 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-19 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-19 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-20 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-20 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-20 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-20 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-20 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-20 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-21 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-21 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-21 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-21 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-21 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-21 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-21 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-22 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-22 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-22 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-22 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-22 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-22 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-23 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-23 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-23 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-23 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-23 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-23 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-24 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-24 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-24 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-24 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-24 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-24 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-25 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-25 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-25 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-25 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-25 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-25 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-26 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-26 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-26 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-26 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-26 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-26 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-27 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-27 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-27 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-27 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-10-27 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-27 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-28 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-28 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-28 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-10-28 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-29 | 2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-10-29 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-29 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-29 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-10-29 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-30 | 2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-10-30 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-30 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-30 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-10-30 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-31 | 2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-10-31 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-31 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-10-31 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-11-01 | 2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-11-01 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-11-01 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-01 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-01 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-11-02 | 2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-11-02 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-02 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-02 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-02 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-03 | 2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-11-03 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-03 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-03 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-03 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-04 | 2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-11-04 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-04 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-04 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-04 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-05 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-05 | 2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-11-05 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-05 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-05 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-05 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-06 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-06 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-06 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-06 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-06 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-07 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-07 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-07 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-07 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-07 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-07 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-08 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-08 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-08 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-08 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-09 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-09 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-09 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-09 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-09 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-10 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-10 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-10 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-10 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-10 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-11 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-11 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-11 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-11 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-11 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-12 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-12 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-12 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-12 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-12 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-12 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-13 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-13 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-13 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-13 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-13 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-13 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-14 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-14 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-14 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-14 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-14 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-14 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-15 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-15 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-15 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-15 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-15 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-16 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-16 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-16 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-16 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-16 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-17 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-17 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-17 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-17 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-17 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-18 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-18 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-18 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-18 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-18 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-19 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-19 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-19 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-19 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-19 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-20 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-20 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-20 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-20 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-20 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-21 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-21 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-21 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-21 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-21 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-22 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-22 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-22 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-22 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-22 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-23 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-23 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-23 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-23 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-23 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-24 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-24 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-24 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-24 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-24 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-24 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-25 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-25 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-25 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-25 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-25 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-26 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-26 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-26 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-26 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-26 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-11-27 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-27 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-27 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-27 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-11-28 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-28 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-28 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-28 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-11-29 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-29 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-29 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-29 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-11-30 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-30 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-30 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-30 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-12-01 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-01 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-12-02 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-02 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-02 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-12-03 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-03 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-03 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-03 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421 | 21/6 | Completed
2024-12-03 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-04 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-04 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-04 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-04 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421 | 21/6 | Completed
2024-12-04 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-05 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-05 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-05 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-05 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421 | 21/6 | Completed
2024-12-05 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-06 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-06 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-06 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421 | 21/6 | Completed
2024-12-06 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-07 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-07 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-07 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-08 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-08 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-08 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-09 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-09 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-09 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-10 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-10 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-10 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-11 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-11 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-11 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-11 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-12 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-12 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-12 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-12 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-13 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-13 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-13 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-13 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-14 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-14 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-14 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-15 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-15 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-15 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-15 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-16 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-16 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-16 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-16 | 2024-12-16 | 2024-12-18 | Subash | 36.37 | 12.1233 | TA421 | 19/2 | Completed
2024-12-17 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-17 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-17 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-17 | 2024-12-16 | 2024-12-18 | Subash | 36.37 | 12.1233 | TA421 | 19/2 | Completed
2024-12-18 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-18 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-18 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-18 | 2024-12-16 | 2024-12-18 | Subash | 36.37 | 12.1233 | TA421 | 19/2 | Completed
2024-12-19 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-19 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-19 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-19 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421 | 18/3 | Completed
2024-12-20 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-20 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-20 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-20 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421 | 18/3 | Completed
2024-12-21 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-21 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-21 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-21 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421 | 18/3 | Completed
2024-12-22 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-22 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-22 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-22 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421 | 18/3 | Completed
2024-12-23 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-23 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-23 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-23 | 2024-12-23 | 2024-12-25 | Subash | 36.37 | 12.1233 | TA421 | 18/2 | Completed
2024-12-24 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-24 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-24 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-24 | 2024-12-23 | 2024-12-25 | Subash | 36.37 | 12.1233 | TA421 | 18/2 | Completed
2024-12-25 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-25 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-25 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-25 | 2024-12-23 | 2024-12-25 | Subash | 36.37 | 12.1233 | TA421 | 18/2 | Completed
2024-12-26 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-26 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-26 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-26 | 2024-12-26 | 2024-12-28 | Subash | 36.37 | 12.1233 | TA421 | 18/1 | Completed
2024-12-27 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-27 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-27 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-27 | 2024-12-26 | 2024-12-28 | Subash | 36.37 | 12.1233 | TA421 | 18/1 | Completed
2024-12-27 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-28 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-28 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-28 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-28 | 2024-12-26 | 2024-12-28 | Subash | 36.37 | 12.1233 | TA421 | 18/1 | Completed
2024-12-28 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-28 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2024-12-29 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-29 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-29 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-29 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2024-12-30 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-30 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-30 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-30 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2024-12-31 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-31 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-31 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-31 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-01 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-01 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2025-01-01 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-02 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-02 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-02 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2025-01-02 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-03 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-03 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-03 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2025-01-03 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-03 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-04 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-04 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-04 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-04 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-04 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-05 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-05 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-05 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-05 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-05 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-06 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-06 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-06 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-06 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-06 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-07 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-07 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-07 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-07 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-08 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-08 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-08 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-08 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-09 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-09 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-09 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-10 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-10 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-10 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-11 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-11 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-11 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-12 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-12 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-12 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-13 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-13 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-13 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-14 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-14 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-14 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-15 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-15 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-15 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-16 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421 | 29/6 | Completed
2025-01-16 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-16 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-17 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421 | 29/6 | Completed
2025-01-17 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-17 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-18 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421 | 29/6 | Completed
2025-01-18 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-18 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-18 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-19 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421 | 29/6 | Completed
2025-01-19 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-19 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-19 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-20 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-20 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-20 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-21 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-21 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-21 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-22 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-22 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-22 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-22 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-22 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-23 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-23 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-23 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-23 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-23 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-24 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-24 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-24 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-24 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-25 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-25 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-25 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-25 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-26 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-26 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-26 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-26 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-27 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-27 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-27 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-27 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-28 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-28 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-01-28 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-28 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-29 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-01-29 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-29 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-30 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-01-30 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-30 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-01-30 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-30 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-01-31 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-01-31 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-01-31 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-02-01 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-02-01 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-01 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-02-02 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-02-02 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-02 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-02-03 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-02-03 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-03 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-02-04 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-04 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-04 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-05 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-05 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-05 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-06 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-06 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-06 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-07 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-07 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-07 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-08 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-08 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-08 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-09 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-09 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-09 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421 | 13/1 | Completed
2025-02-10 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-10 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-10 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-10 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421 | 13/1 | Completed
2025-02-11 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-11 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-11 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-11 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421 | 13/1 | Completed
2025-02-12 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-12 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-12 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-12 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421 | 13/1 | Completed
2025-02-13 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-13 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-13 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-13 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-14 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-14 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-14 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-14 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-15 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-15 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-15 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-15 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-16 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-16 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-16 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-16 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-17 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-17 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-17 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-17 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-18 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-18 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-18 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-18 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-19 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-19 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-19 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-19 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-19 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-20 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-20 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-20 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-20 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-21 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-21 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-21 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-21 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-22 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-22 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-22 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-22 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-23 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-23 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-23 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-23 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-24 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-24 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-24 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-24 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421 | 13/6 | Completed
2025-02-25 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-25 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-25 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-25 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421 | 13/6 | Completed
2025-02-26 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-02-26 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421 | 29/7 | Completed
2025-02-26 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-26 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421 | 13/6 | Completed
2025-02-27 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-02-27 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421 | 29/7 | Completed
2025-02-27 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-27 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421 | 13/6 | Completed
2025-02-28 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-02-28 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421 | 29/7 | Completed
2025-02-28 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-28 | 2025-02-28 | 2025-03-02 | Subash | 36.37 | 12.1233 | TA421 | 13/5 | Completed
2025-03-01 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-03-01 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-01 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421 | 29/7 | Completed
2025-03-01 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-03-01 | 2025-02-28 | 2025-03-02 | Subash | 36.37 | 12.1233 | TA421 | 13/5 | Completed
2025-03-02 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-03-02 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-02 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-02 | 2025-02-28 | 2025-03-02 | Subash | 36.37 | 12.1233 | TA421 | 13/5 | Completed
2025-03-03 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-03 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-03 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-03 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-03 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-04 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-04 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-04 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-04 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-04 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-05 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-05 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-05 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-05 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-05 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-06 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-06 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-06 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-06 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-06 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-07 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-07 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-07 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-07 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-07 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-08 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-08 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-08 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-08 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-08 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421 | 13/0 | Completed
2025-03-09 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-09 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-09 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-09 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-09 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421 | 13/0 | Completed
2025-03-10 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421 | 38/4 | Completed
2025-03-10 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-10 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-10 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-10 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421 | 13/0 | Completed
2025-03-11 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421 | 38/4 | Completed
2025-03-11 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-11 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-11 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-11 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421 | 13/0 | Completed
2025-03-12 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421 | 38/4 | Completed
2025-03-12 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-12 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-12 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-12 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-13 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421 | 38/4 | Completed
2025-03-13 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-13 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-13 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-13 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-14 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-14 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-14 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-14 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-15 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-15 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-15 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-15 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-15 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-16 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-16 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-16 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-16 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-16 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-16 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421 | 13/9 | Completed
2025-03-17 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-17 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-17 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-17 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-17 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-17 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421 | 13/9 | Completed
2025-03-18 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-18 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-18 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-18 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-18 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421 | 13/9 | Completed
2025-03-19 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-19 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-19 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-19 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-19 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421 | 13/9 | Completed
2025-03-20 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421 | 38/6 | Completed
2025-03-20 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-20 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-20 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-20 | 2025-03-20 | 2025-03-22 | Subash | 36.37 | 12.1233 | TA421 | 13/10 | Completed
2025-03-21 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421 | 38/6 | Completed
2025-03-21 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-21 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-21 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-21 | 2025-03-20 | 2025-03-22 | Subash | 36.37 | 12.1233 | TA421 | 13/10 | Completed
2025-03-22 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421 | 38/6 | Completed
2025-03-22 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-22 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-22 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-22 | 2025-03-20 | 2025-03-22 | Subash | 36.37 | 12.1233 | TA421 | 13/10 | Completed
2025-03-23 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421 | 38/6 | Completed
2025-03-23 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-23 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-23 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-23 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-23 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421 | 15/1 | Completed
2025-03-24 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-24 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-24 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-24 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-24 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421 | 15/1 | Completed
2025-03-25 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-25 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-25 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-25 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-25 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421 | 15/1 | Completed
2025-03-26 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-26 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-26 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-26 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-26 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421 | 15/1 | Completed
2025-03-27 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-27 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-27 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-27 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-27 | 2025-03-27 | 2025-03-29 | Subash | 37.93 | 12.6433 | TA421 | 15/2 | Completed
2025-03-28 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-28 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-28 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-03-28 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-03-28 | 2025-03-27 | 2025-03-29 | Subash | 37.93 | 12.6433 | TA421 | 15/2 | Completed
2025-03-29 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-29 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-03-29 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-29 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-03-29 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-03-29 | 2025-03-27 | 2025-03-29 | Subash | 37.93 | 12.6433 | TA421 | 15/2 | Completed
2025-03-29 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-03-30 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-03-30 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-30 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-03-30 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-03-30 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-03-30 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-03-31 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-03-31 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-03-31 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-03-31 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-03-31 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-04-01 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-04-01 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-01 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-04-01 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-01 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-04-02 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-04-02 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-02 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-02 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-02 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-04-03 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-04-03 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-03 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-03 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-03 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-04 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-04-04 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-04 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-04 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-04 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-05 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-05 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-05 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-05 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-05 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-06 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-06 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-06 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-06 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-06 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-07 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-07 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-07 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-07 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-07 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-08 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-08 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-08 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-08 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-08 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-09 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-09 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-09 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-09 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-09 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-10 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-10 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-10 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-10 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-10 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-11 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-11 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-11 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-11 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-11 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-12 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-12 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-12 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-12 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-12 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-13 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-13 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-13 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-13 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-13 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-14 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-14 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-14 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-14 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-14 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-15 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-15 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-15 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421 | 35/3 | Completed
2025-04-15 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-15 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-16 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-16 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-16 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421 | 35/3 | Completed
2025-04-16 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-16 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421 | 16/3 | Completed
2025-04-17 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-17 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-17 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421 | 35/3 | Completed
2025-04-17 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-17 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421 | 16/3 | Completed
2025-04-18 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-18 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-18 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421 | 35/3 | Completed
2025-04-18 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-18 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421 | 16/3 | Completed
2025-04-19 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-19 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-19 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-19 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-19 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421 | 16/3 | Completed
2025-04-19 | 2025-04-19 | 2025-04-21 | Subash | 36.37 | 12.1233 | TA421 | 16/4 | Completed
2025-04-20 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-20 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-20 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-20 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-20 | 2025-04-19 | 2025-04-21 | Subash | 36.37 | 12.1233 | TA421 | 16/4 | Completed
2025-04-21 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-21 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-21 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-21 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-21 | 2025-04-19 | 2025-04-21 | Subash | 36.37 | 12.1233 | TA421 | 16/4 | Completed
2025-04-22 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-22 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-22 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-22 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-22 | 2025-04-22 | 2025-04-24 | Subash | 36.37 | 12.1233 | TA421 | 16/5 | Completed
2025-04-23 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-23 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-23 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-23 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-23 | 2025-04-22 | 2025-04-24 | Subash | 36.37 | 12.1233 | TA421 | 16/5 | Completed
2025-04-24 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-24 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-24 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-24 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-24 | 2025-04-22 | 2025-04-24 | Subash | 36.37 | 12.1233 | TA421 | 16/5 | Completed
2025-04-25 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-25 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-25 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-25 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-25 | 2025-04-25 | 2025-04-27 | Subash | 36.37 | 12.1233 | TA421 | 15/3 | Completed
2025-04-26 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-26 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-26 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-26 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-26 | 2025-04-25 | 2025-04-27 | Subash | 36.37 | 12.1233 | TA421 | 15/3 | Completed
2025-04-27 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-27 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-27 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-27 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-04-27 | 2025-04-25 | 2025-04-27 | Subash | 36.37 | 12.1233 | TA421 | 15/3 | Completed
2025-04-28 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-28 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-28 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-04-28 | 2025-04-28 | 2025-04-30 | Subash | 36.37 | 12.1233 | TA421 | 13/11 | Completed
2025-04-29 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-29 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421 | 27/9 | Completed
2025-04-29 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-04-29 | 2025-04-28 | 2025-04-30 | Subash | 36.37 | 12.1233 | TA421 | 13/11 | Completed
2025-04-30 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-30 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421 | 27/9 | Completed
2025-04-30 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-04-30 | 2025-04-28 | 2025-04-30 | Subash | 36.37 | 12.1233 | TA421 | 13/11 | Completed
2025-05-01 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421 | 27/9 | Completed
2025-05-01 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-01 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421 | 10/7 | Completed
2025-05-02 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421 | 38/2 | Completed
2025-05-02 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421 | 27/9 | Completed
2025-05-02 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-02 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421 | 10/7 | Completed
2025-05-03 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421 | 38/2 | Completed
2025-05-03 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-03 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-03 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421 | 10/7 | Completed
2025-05-04 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421 | 38/2 | Completed
2025-05-04 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-04 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-04 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421 | 10/7 | Completed
2025-05-05 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421 | 38/2 | Completed
2025-05-05 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-05 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-05 | 2025-05-05 | 2025-05-06 | Subash | 36.37 | 18.185 | TA421 | 11/1 | Completed
2025-05-06 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-06 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-06 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-06 | 2025-05-05 | 2025-05-06 | Subash | 36.37 | 18.185 | TA421 | 11/1 | Completed
2025-05-07 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-07 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-07 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-07 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421 | 10/9 | Completed
2025-05-08 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-08 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-08 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-08 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-08 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421 | 10/9 | Completed
2025-05-09 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-09 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-09 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-09 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421 | 10/9 | Completed
2025-05-10 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-10 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-10 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-10 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-10 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421 | 10/9 | Completed
2025-05-10 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421 | 10/4 | Completed
2025-05-11 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-11 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-11 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-11 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-11 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-11 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421 | 10/4 | Completed
2025-05-12 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-12 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-12 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-12 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-12 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-12 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421 | 10/4 | Completed
2025-05-13 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-13 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-13 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-13 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-13 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-13 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421 | 10/4 | Completed
2025-05-14 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-14 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-14 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-14 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-14 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-14 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421 | 10/2 | Completed
2025-05-15 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-15 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-15 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-15 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-15 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-15 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421 | 10/2 | Completed
2025-05-16 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-16 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-16 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-16 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-16 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-16 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421 | 10/2 | Completed
2025-05-17 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-17 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-17 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-17 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-17 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421 | 10/2 | Completed
2025-05-18 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-18 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-18 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-18 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-18 | 2025-05-18 | 2025-05-20 | Subash | 37.93 | 12.6433 | TA421 | 10/1 | Completed
2025-05-19 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-19 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-19 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-19 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-19 | 2025-05-18 | 2025-05-20 | Subash | 37.93 | 12.6433 | TA421 | 10/1 | Completed
2025-05-20 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-20 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-20 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-20 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-20 | 2025-05-18 | 2025-05-20 | Subash | 37.93 | 12.6433 | TA421 | 10/1 | Completed
2025-05-21 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-21 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-21 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-21 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-21 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-22 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-22 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-22 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-22 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-22 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-23 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-23 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-23 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-23 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-24 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-24 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-24 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-24 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-25 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-25 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-25 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-26 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-26 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-26 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-27 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-27 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-27 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-28 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-28 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-28 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-29 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-29 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-29 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-05-30 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-30 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-30 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-05-31 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-31 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-31 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-06-01 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-01 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-06-01 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-06-02 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-02 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-06-02 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-06-03 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-03 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-06-03 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-04 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-04 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-06-04 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-05 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-05 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-05 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-05 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-06 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-06 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-06 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-06 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-06 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-07 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-07 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-07 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-07 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-08 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-08 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-08 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-08 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-09 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-09 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-09 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-09 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-10 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-10 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-10 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-10 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-11 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-11 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-11 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-11 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-12 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-12 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-12 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-13 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-13 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-13 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-14 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-14 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-14 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-15 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-15 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-15 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-16 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-16 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-16 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-17 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-17 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-17 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-18 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-18 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-18 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-19 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-19 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-19 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-20 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-20 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-20 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-21 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-21 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-21 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-22 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-22 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-22 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-23 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-23 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-23 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-24 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-24 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-24 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-24 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-24 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-25 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-25 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-25 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-25 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-25 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-25 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421 | 11/2 | Completed
2025-06-26 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-26 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-26 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-26 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-26 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421 | 11/2 | Completed
2025-06-27 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-27 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-27 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-27 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-27 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421 | 11/2 | Completed
2025-06-28 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-28 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-28 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-28 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-28 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421 | 11/2 | Completed
2025-06-29 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-29 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-29 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-29 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-29 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421 | 11/3 | Completed
2025-06-30 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-30 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-30 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-30 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-30 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421 | 11/3 | Completed
2025-07-01 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-07-01 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-07-01 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-07-01 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-01 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421 | 11/3 | Completed
2025-07-02 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-07-02 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-07-02 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-07-02 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-02 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421 | 11/3 | Completed
2025-07-03 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-07-03 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-07-03 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-07-03 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-03 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-04 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-07-04 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-07-04 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-04 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-07-04 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-04 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-05 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-05 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-07-05 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-05 | 2025-07-05 | 2025-07-13 | Naziruddin | 71.706 | 7.9673 | TA421 | 14/0 | Completed
2025-07-05 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-05 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-06 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-06 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-06 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-06 | 2025-07-05 | 2025-07-13 | Naziruddin | 71.706 | 7.9673 | TA421 | 14/0 | Completed
2025-07-06 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-06 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-07 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-07 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-07 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-07 | 2025-07-05 | 2025-07-13 | Naziruddin | 71.706 | 7.9673 | TA421 | 14/0 | Completed
2025-07-07 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-07 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-08 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-08 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-08 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-08 | 2025-07-05 | 2025-07-13 | Naziruddin | 71.706 | 7.9673 | TA421 | 14/0 | Completed
2025-07-08 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-08 | 2025-07-08 | 2025-07-12 | Subash | 33.38 | 6.676 | TA421 | 9/10 | Completed
2025-07-09 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-09 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-09 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-09 | 2025-07-05 | 2025-07-13 | Naziruddin | 71.706 | 7.9673 | TA421 | 14/0 | Completed
2025-07-09 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-09 | 2025-07-08 | 2025-07-12 | Subash | 33.38 | 6.676 | TA421 | 9/10 | Completed
2025-07-10 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-10 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-10 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-10 | 2025-07-05 | 2025-07-13 | Naziruddin | 71.706 | 7.9673 | TA421 | 14/0 | Completed
2025-07-10 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-10 | 2025-07-08 | 2025-07-12 | Subash | 33.38 | 6.676 | TA421 | 9/10 | Completed
2025-07-11 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-11 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-11 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-11 | 2025-07-05 | 2025-07-13 | Naziruddin | 71.706 | 7.9673 | TA421 | 14/0 | Completed
2025-07-11 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-11 | 2025-07-08 | 2025-07-12 | Subash | 33.38 | 6.676 | TA421 | 9/10 | Completed
2025-07-12 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-12 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-12 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-12 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-12 | 2025-07-05 | 2025-07-13 | Naziruddin | 71.706 | 7.9673 | TA421 | 14/0 | Completed
2025-07-12 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-12 | 2025-07-08 | 2025-07-12 | Subash | 33.38 | 6.676 | TA421 | 9/10 | Completed
2025-07-13 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-13 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-13 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-13 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-13 | 2025-07-05 | 2025-07-13 | Naziruddin | 71.706 | 7.9673 | TA421 | 14/0 | Completed
2025-07-13 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-13 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421 | 9/8 | Completed
2025-07-14 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-14 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-14 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-14 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-14 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-14 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-14 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421 | 9/8 | Completed
2025-07-15 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-15 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-15 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-15 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-15 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421 | 6/3 | Completed
2025-07-15 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-15 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-15 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421 | 9/8 | Completed
2025-07-16 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-16 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-16 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-16 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421 | 6/3 | Completed
2025-07-16 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-16 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-16 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421 | 9/8 | Completed
2025-07-17 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-17 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-17 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-17 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421 | 6/3 | Completed
2025-07-17 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-17 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-17 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421 | 9/7 | Completed
2025-07-18 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-18 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-18 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-18 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421 | 6/3 | Completed
2025-07-18 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-18 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-18 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421 | 9/7 | Completed
2025-07-19 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-19 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-19 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-19 | 2025-07-19 | 2025-07-21 | Khatun | 31.99 | 10.6633 | TA421 | 6/2 | Completed
2025-07-19 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-19 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-19 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421 | 9/7 | Completed
2025-07-20 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-20 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-20 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-20 | 2025-07-19 | 2025-07-21 | Khatun | 31.99 | 10.6633 | TA421 | 6/2 | Completed
2025-07-20 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-20 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-20 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421 | 9/7 | Completed
2025-07-21 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-21 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-21 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-21 | 2025-07-19 | 2025-07-21 | Khatun | 31.99 | 10.6633 | TA421 | 6/2 | Completed
2025-07-21 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-21 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-21 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-22 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-22 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-22 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-22 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-22 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-22 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-22 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-23 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-23 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-23 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-23 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-23 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-23 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-23 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-24 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-24 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-24 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-24 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-24 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-24 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-24 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-25 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-25 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-25 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-25 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-25 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-25 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-25 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-26 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-26 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-26 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-26 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-26 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-26 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-26 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-27 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-27 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-27 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-27 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-27 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-27 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-27 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-28 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-28 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-28 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-28 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-28 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-28 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-28 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-29 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-29 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-29 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-29 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421 | 4/21 | Completed
2025-07-29 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-29 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-29 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-30 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-07-30 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-30 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-30 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421 | 4/21 | Completed
2025-07-30 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421 | 8/8 | Completed
2025-07-30 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-30 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-31 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-07-31 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-31 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421 | 4/21 | Completed
2025-07-31 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421 | 8/8 | Completed
2025-07-31 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-31 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-08-01 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-08-01 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-08-01 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421 | 4/21 | Completed
2025-08-01 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421 | 8/8 | Completed
2025-08-01 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-08-01 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-02 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-08-02 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-08-02 | 2025-08-02 | 2025-08-04 | Khatun | 31.99 | 10.6633 | TA421 | 6/6 | Completed
2025-08-02 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421 | 8/8 | Completed
2025-08-02 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-08-02 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-03 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-08-03 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-08-03 | 2025-08-02 | 2025-08-04 | Khatun | 31.99 | 10.6633 | TA421 | 6/6 | Completed
2025-08-03 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-03 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-04 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-08-04 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-04 | 2025-08-02 | 2025-08-04 | Khatun | 31.99 | 10.6633 | TA421 | 6/6 | Completed
2025-08-04 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-04 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-05 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-05 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-05 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421 | 8/13 | Completed
2025-08-05 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-05 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-06 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-06 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-06 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421 | 8/13 | Completed
2025-08-06 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-06 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-07 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-07 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-07 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421 | 8/13 | Completed
2025-08-07 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-07 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-08 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-08 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-08 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421 | 8/13 | Completed
2025-08-08 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-08 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-08 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-09 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-09 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-09 | 2025-08-09 | 2025-08-11 | Khatun | 31.99 | 10.6633 | TA421 | 4/23 | Completed
2025-08-09 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-09 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-09 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-10 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-10 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-10 | 2025-08-09 | 2025-08-11 | Khatun | 31.99 | 10.6633 | TA421 | 4/23 | Completed
2025-08-10 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-10 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-10 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-11 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-11 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-11 | 2025-08-09 | 2025-08-11 | Khatun | 31.99 | 10.6633 | TA421 | 4/23 | Completed
2025-08-11 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-11 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-11 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-12 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-12 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-12 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-12 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-12 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-12 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-13 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-13 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-13 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-13 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-13 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-13 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-14 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-14 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-14 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-14 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-14 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-14 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-15 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-15 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-15 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-15 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-15 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-16 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-16 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-16 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-16 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-16 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-16 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-17 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-17 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-17 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-17 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-17 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-17 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-18 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-18 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-18 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-18 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-18 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-18 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-19 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-19 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-19 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-19 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-19 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-19 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-20 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-20 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-20 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-20 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-20 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-20 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-21 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-21 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-21 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-21 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-21 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-21 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-22 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-22 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-22 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-22 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-22 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-22 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-23 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-23 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-23 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-23 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-23 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-23 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-23 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-24 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-24 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-24 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-24 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-24 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-24 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-24 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-25 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-25 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-25 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-25 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-25 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-25 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-25 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-26 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-26 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-26 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-26 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-26 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-26 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-26 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-27 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-27 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-27 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-27 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-27 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-27 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-27 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-28 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-28 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-28 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-28 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-28 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-28 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-28 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-29 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-29 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-29 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-29 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-29 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-29 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-29 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-30 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-30 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-08-30 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-30 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-30 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-30 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-31 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-31 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-08-31 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-08-31 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-31 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421 | 2/3 | Completed
2025-08-31 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-09-01 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-01 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-01 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-01 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-01 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421 | 2/3 | Completed
2025-09-01 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421 | 9/9 | Completed
2025-09-02 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-02 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-02 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-02 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-02 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421 | 2/3 | Completed
2025-09-02 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421 | 9/9 | Completed
2025-09-03 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-03 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-03 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-03 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-03 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421 | 2/3 | Completed
2025-09-03 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421 | 9/9 | Completed
2025-09-04 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-04 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-04 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-04 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-04 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421 | 9/9 | Completed
2025-09-05 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-05 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-05 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-05 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-05 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421 | 4/0 | Completed
2025-09-05 | 2025-09-05 | 2025-09-07 | Subash | 31.99 | 10.6633 | TA421 | 4/6 | Completed
2025-09-06 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-06 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-06 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-06 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-06 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421 | 4/0 | Completed
2025-09-06 | 2025-09-05 | 2025-09-07 | Subash | 31.99 | 10.6633 | TA421 | 4/6 | Completed
2025-09-07 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421 | 42/9 | Completed
2025-09-07 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-07 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-07 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-07 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421 | 4/0 | Completed
2025-09-07 | 2025-09-05 | 2025-09-07 | Subash | 31.99 | 10.6633 | TA421 | 4/6 | Completed
2025-09-08 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421 | 42/9 | Completed
2025-09-08 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-08 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-08 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-08 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421 | 4/0 | Completed
2025-09-08 | 2025-09-08 | 2025-09-09 | Subash | 33.38 | 16.69 | TA421 | 4/7 | Completed
2025-09-09 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421 | 42/9 | Completed
2025-09-09 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-09 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-09 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-09 | 2025-09-08 | 2025-09-09 | Subash | 33.38 | 16.69 | TA421 | 4/7 | Completed
2025-09-10 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421 | 42/9 | Completed
2025-09-10 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-10 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-10 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-10 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-11 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-11 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-11 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-11 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-12 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-12 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-12 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-12 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-13 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-13 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-13 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-13 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-13 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-09-13 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-14 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-14 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-14 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-14 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-09-14 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-14 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-15 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-15 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-15 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-15 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-09-15 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-16 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-16 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-16 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-16 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-16 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-09-16 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-17 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-17 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-17 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-17 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-09-17 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-18 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-18 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-18 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-18 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-09-18 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-19 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-19 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-19 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-19 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-09-19 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-20 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-20 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-20 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-20 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-09-20 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-21 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-21 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-21 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-21 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-21 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-09-21 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421 | 4/2 | Completed
2025-09-21 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-22 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-22 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-22 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-22 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-22 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-09-22 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421 | 4/2 | Completed
2025-09-22 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-23 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-23 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-23 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-23 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-23 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-09-23 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421 | 4/2 | Completed
2025-09-23 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-24 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-24 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-24 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-24 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-24 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-09-24 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421 | 4/2 | Completed
2025-09-24 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-25 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-25 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-25 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-25 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-25 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-09-25 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-25 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-26 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-26 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-26 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-26 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-09-26 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-26 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-27 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-27 | 2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-09-27 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-27 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-09-27 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-27 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-28 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-28 | 2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-09-28 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-28 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-09-28 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-09-28 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-28 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-29 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-29 | 2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-09-29 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-29 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-09-29 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-09-29 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-29 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-30 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-30 | 2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-09-30 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-09-30 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-09-30 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-30 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-10-01 | 2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-10-01 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-10-01 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-10-01 | 2025-10-01 | 2025-10-09 | Subash | 72.63 | 8.07 | TA421 | 1/0 | Completed
2025-10-01 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-10-02 | 2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-10-02 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-10-02 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-10-02 | 2025-10-01 | 2025-10-09 | Subash | 72.63 | 8.07 | TA421 | 1/0 | Completed
2025-10-02 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-10-03 | 2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-10-03 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-10-03 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-10-03 | 2025-10-01 | 2025-10-09 | Subash | 72.63 | 8.07 | TA421 | 1/0 | Completed
2025-10-03 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-10-04 | 2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-10-04 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-10-04 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-10-04 | 2025-10-01 | 2025-10-09 | Subash | 72.63 | 8.07 | TA421 | 1/0 | Completed
2025-10-04 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-10-05 | 2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-10-05 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-10-05 | 2025-10-01 | 2025-10-09 | Subash | 72.63 | 8.07 | TA421 | 1/0 | Completed
2025-10-05 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-10-06 | 2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-10-06 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-10-06 | 2025-10-01 | 2025-10-09 | Subash | 72.63 | 8.07 | TA421 | 1/0 | Completed
2025-10-06 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-10-07 | 2025-10-07 | 2025-10-11 | D K Verma | 36.37 | 7.274 | TA421 | 43/3 | Completed
2025-10-07 | 2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-10-07 | 2025-10-07 | 2025-10-12 | Khatun | 39.17 | 6.5283 | TA421 | 9/3 | Completed
2025-10-07 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-10-07 | 2025-10-01 | 2025-10-09 | Subash | 72.63 | 8.07 | TA421 | 1/0 | Completed
2025-10-08 | 2025-10-07 | 2025-10-11 | D K Verma | 36.37 | 7.274 | TA421 | 43/3 | Completed
2025-10-08 | 2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-10-08 | 2025-10-07 | 2025-10-12 | Khatun | 39.17 | 6.5283 | TA421 | 9/3 | Completed
2025-10-08 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-10-08 | 2025-10-01 | 2025-10-09 | Subash | 72.63 | 8.07 | TA421 | 1/0 | Completed
2025-10-09 | 2025-10-07 | 2025-10-11 | D K Verma | 36.37 | 7.274 | TA421 | 43/3 | Completed
2025-10-09 | 2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-10-09 | 2025-10-07 | 2025-10-12 | Khatun | 39.17 | 6.5283 | TA421 | 9/3 | Completed
2025-10-09 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-10-09 | 2025-10-01 | 2025-10-09 | Subash | 72.63 | 8.07 | TA421 | 1/0 | Completed
2025-10-10 | 2025-10-07 | 2025-10-11 | D K Verma | 36.37 | 7.274 | TA421 | 43/3 | Completed
2025-10-10 | 2025-10-10 | 2025-10-19 | Hassan | 37.931 | 3.7931 | TA421 | 36/7 | Completed
2025-10-10 | 2025-10-07 | 2025-10-12 | Khatun | 39.17 | 6.5283 | TA421 | 9/3 | Completed
2025-10-10 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-10-10 | 2025-10-10 | 2025-10-15 | Subash | 37.72 | 6.2867 | TA421 | 4/3 | Completed
2025-10-11 | 2025-10-07 | 2025-10-11 | D K Verma | 36.37 | 7.274 | TA421 | 43/3 | Completed
2025-10-11 | 2025-10-10 | 2025-10-19 | Hassan | 37.931 | 3.7931 | TA421 | 36/7 | Completed
2025-10-11 | 2025-10-07 | 2025-10-12 | Khatun | 39.17 | 6.5283 | TA421 | 9/3 | Completed
2025-10-11 | 2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-10-11 | 2025-10-10 | 2025-10-15 | Subash | 37.72 | 6.2867 | TA421 | 4/3 | Completed
2025-10-12 | 2025-10-12 | 2025-10-16 | D K Verma | 44.851 | 8.9702 | TA421 | 43/5 | Completed
2025-10-12 | 2025-10-10 | 2025-10-19 | Hassan | 37.931 | 3.7931 | TA421 | 36/7 | Completed
2025-10-12 | 2025-10-07 | 2025-10-12 | Khatun | 39.17 | 6.5283 | TA421 | 9/3 | Completed
2025-10-12 | 2025-10-10 | 2025-10-15 | Subash | 37.72 | 6.2867 | TA421 | 4/3 | Completed
2025-10-13 | 2025-10-12 | 2025-10-16 | D K Verma | 44.851 | 8.9702 | TA421 | 43/5 | Completed
2025-10-13 | 2025-10-10 | 2025-10-19 | Hassan | 37.931 | 3.7931 | TA421 | 36/7 | Completed
2025-10-13 | 2025-10-13 | 2025-10-17 | Khatun | 39.17 | 7.834 | TA421 | 4/20 | Completed
2025-10-13 | 2025-10-10 | 2025-10-15 | Subash | 37.72 | 6.2867 | TA421 | 4/3 | Completed
2025-10-14 | 2025-10-12 | 2025-10-16 | D K Verma | 44.851 | 8.9702 | TA421 | 43/5 | Completed
2025-10-14 | 2025-10-10 | 2025-10-19 | Hassan | 37.931 | 3.7931 | TA421 | 36/7 | Completed
2025-10-14 | 2025-10-13 | 2025-10-17 | Khatun | 39.17 | 7.834 | TA421 | 4/20 | Completed
2025-10-14 | 2025-10-14 | 2025-10-27 | Praveen | 36.37 | 2.5979 | TA421 | 39/6 | Completed
2025-10-14 | 2025-10-10 | 2025-10-15 | Subash | 37.72 | 6.2867 | TA421 | 4/3 | Completed
2025-10-15 | 2025-10-12 | 2025-10-16 | D K Verma | 44.851 | 8.9702 | TA421 | 43/5 | Completed
2025-10-15 | 2025-10-10 | 2025-10-19 | Hassan | 37.931 | 3.7931 | TA421 | 36/7 | Completed
2025-10-15 | 2025-10-13 | 2025-10-17 | Khatun | 39.17 | 7.834 | TA421 | 4/20 | Completed
2025-10-15 | 2025-10-14 | 2025-10-27 | Praveen | 36.37 | 2.5979 | TA421 | 39/6 | Completed
2025-10-15 | 2025-10-10 | 2025-10-15 | Subash | 37.72 | 6.2867 | TA421 | 4/3 | Completed
2025-10-16 | 2025-10-12 | 2025-10-16 | D K Verma | 44.851 | 8.9702 | TA421 | 43/5 | Completed
2025-10-16 | 2025-10-10 | 2025-10-19 | Hassan | 37.931 | 3.7931 | TA421 | 36/7 | Completed
2025-10-16 | 2025-10-13 | 2025-10-17 | Khatun | 39.17 | 7.834 | TA421 | 4/20 | Completed
2025-10-16 | 2025-10-14 | 2025-10-27 | Praveen | 36.37 | 2.5979 | TA421 | 39/6 | Completed
2025-10-17 | 2025-10-17 | 2025-10-21 | D K Verma | 36.371 | 7.2742 | TA421 | 42/2 | Completed
2025-10-17 | 2025-10-10 | 2025-10-19 | Hassan | 37.931 | 3.7931 | TA421 | 36/7 | Completed
2025-10-17 | 2025-10-13 | 2025-10-17 | Khatun | 39.17 | 7.834 | TA421 | 4/20 | Completed
2025-10-17 | 2025-10-17 | 2025-10-22 | Khatun | 37.72 | 6.2867 | TA421 | 4/19 | Completed
2025-10-17 | 2025-10-14 | 2025-10-27 | Praveen | 36.37 | 2.5979 | TA421 | 39/6 | Completed
2025-10-17 | 2025-10-17 | 2025-10-21 | Subash | 31.99 | 6.398 | TA421 | 4/4 | Completed
2025-10-18 | 2025-10-17 | 2025-10-21 | D K Verma | 36.371 | 7.2742 | TA421 | 42/2 | Completed
2025-10-18 | 2025-10-10 | 2025-10-19 | Hassan | 37.931 | 3.7931 | TA421 | 36/7 | Completed
2025-10-18 | 2025-10-17 | 2025-10-22 | Khatun | 37.72 | 6.2867 | TA421 | 4/19 | Completed
2025-10-18 | 2025-10-14 | 2025-10-27 | Praveen | 36.37 | 2.5979 | TA421 | 39/6 | Completed
2025-10-18 | 2025-10-17 | 2025-10-21 | Subash | 31.99 | 6.398 | TA421 | 4/4 | Completed
2025-10-19 | 2025-10-17 | 2025-10-21 | D K Verma | 36.371 | 7.2742 | TA421 | 42/2 | Completed
2025-10-19 | 2025-10-10 | 2025-10-19 | Hassan | 37.931 | 3.7931 | TA421 | 36/7 | Completed
2025-10-19 | 2025-10-17 | 2025-10-22 | Khatun | 37.72 | 6.2867 | TA421 | 4/19 | Completed
2025-10-19 | 2025-10-14 | 2025-10-27 | Praveen | 36.37 | 2.5979 | TA421 | 39/6 | Completed
2025-10-19 | 2025-10-17 | 2025-10-21 | Subash | 31.99 | 6.398 | TA421 | 4/4 | Completed
2025-10-20 | 2025-10-17 | 2025-10-21 | D K Verma | 36.371 | 7.2742 | TA421 | 42/2 | Completed
2025-10-20 | 2025-10-17 | 2025-10-22 | Khatun | 37.72 | 6.2867 | TA421 | 4/19 | Completed
2025-10-20 | 2025-10-14 | 2025-10-27 | Praveen | 36.37 | 2.5979 | TA421 | 39/6 | Completed
2025-10-20 | 2025-10-17 | 2025-10-21 | Subash | 31.99 | 6.398 | TA421 | 4/4 | Completed
2025-10-21 | 2025-10-17 | 2025-10-21 | D K Verma | 36.371 | 7.2742 | TA421 | 42/2 | Completed
2025-10-21 | 2025-10-21 | 2025-11-02 | Hassan | 36.37 | 2.7977 | TA421 | 36/8 | Completed
2025-10-21 | 2025-10-17 | 2025-10-22 | Khatun | 37.72 | 6.2867 | TA421 | 4/19 | Completed
2025-10-21 | 2025-10-14 | 2025-10-27 | Praveen | 36.37 | 2.5979 | TA421 | 39/6 | Completed
2025-10-21 | 2025-10-17 | 2025-10-21 | Subash | 31.99 | 6.398 | TA421 | 4/4 | Completed
2025-10-22 | 2025-10-22 | 2025-10-25 | D K Verma | 36.371 | 9.0928 | TA421 | 41/1 | Completed
2025-10-22 | 2025-10-21 | 2025-11-02 | Hassan | 36.37 | 2.7977 | TA421 | 36/8 | Completed
2025-10-22 | 2025-10-17 | 2025-10-22 | Khatun | 37.72 | 6.2867 | TA421 | 4/19 | Completed
2025-10-22 | 2025-10-14 | 2025-10-27 | Praveen | 36.37 | 2.5979 | TA421 | 39/6 | Completed
2025-10-22 | 2025-10-22 | 2025-10-30 | Subash | 33.38 | 3.7089 | TA421 | 4/1 | Completed
2025-10-23 | 2025-10-22 | 2025-10-25 | D K Verma | 36.371 | 9.0928 | TA421 | 41/1 | Completed
2025-10-23 | 2025-10-21 | 2025-11-02 | Hassan | 36.37 | 2.7977 | TA421 | 36/8 | Completed
2025-10-23 | 2025-10-23 | 2025-10-27 | Khatun | 36.37 | 7.274 | TA421 | 11/4 | Completed
2025-10-23 | 2025-10-14 | 2025-10-27 | Praveen | 36.37 | 2.5979 | TA421 | 39/6 | Completed
2025-10-23 | 2025-10-22 | 2025-10-30 | Subash | 33.38 | 3.7089 | TA421 | 4/1 | Completed
2025-10-24 | 2025-10-22 | 2025-10-25 | D K Verma | 36.371 | 9.0928 | TA421 | 41/1 | Completed
2025-10-24 | 2025-10-21 | 2025-11-02 | Hassan | 36.37 | 2.7977 | TA421 | 36/8 | Completed
2025-10-24 | 2025-10-23 | 2025-10-27 | Khatun | 36.37 | 7.274 | TA421 | 11/4 | Completed
2025-10-24 | 2025-10-14 | 2025-10-27 | Praveen | 36.37 | 2.5979 | TA421 | 39/6 | Completed
2025-10-24 | 2025-10-22 | 2025-10-30 | Subash | 33.38 | 3.7089 | TA421 | 4/1 | Completed
2025-10-25 | 2025-10-22 | 2025-10-25 | D K Verma | 36.371 | 9.0928 | TA421 | 41/1 | Completed
2025-10-25 | 2025-10-21 | 2025-11-02 | Hassan | 36.37 | 2.7977 | TA421 | 36/8 | Completed
2025-10-25 | 2025-10-23 | 2025-10-27 | Khatun | 36.37 | 7.274 | TA421 | 11/4 | Completed
2025-10-25 | 2025-10-14 | 2025-10-27 | Praveen | 36.37 | 2.5979 | TA421 | 39/6 | Completed
2025-10-25 | 2025-10-22 | 2025-10-30 | Subash | 33.38 | 3.7089 | TA421 | 4/1 | Completed
2025-10-26 | 2025-10-26 | 2025-11-02 | D K Verma | 37.931 | 4.7414 | TA421 | 43/1 | Completed
2025-10-26 | 2025-10-21 | 2025-11-02 | Hassan | 36.37 | 2.7977 | TA421 | 36/8 | Completed
2025-10-26 | 2025-10-23 | 2025-10-27 | Khatun | 36.37 | 7.274 | TA421 | 11/4 | Completed
2025-10-26 | 2025-10-14 | 2025-10-27 | Praveen | 36.37 | 2.5979 | TA421 | 39/6 | Completed
2025-10-26 | 2025-10-22 | 2025-10-30 | Subash | 33.38 | 3.7089 | TA421 | 4/1 | Completed
2025-10-27 | 2025-10-26 | 2025-11-02 | D K Verma | 37.931 | 4.7414 | TA421 | 43/1 | Completed
2025-10-27 | 2025-10-21 | 2025-11-02 | Hassan | 36.37 | 2.7977 | TA421 | 36/8 | Completed
2025-10-27 | 2025-10-23 | 2025-10-27 | Khatun | 36.37 | 7.274 | TA421 | 11/4 | Completed
2025-10-27 | 2025-10-14 | 2025-10-27 | Praveen | 36.37 | 2.5979 | TA421 | 39/6 | Completed
2025-10-27 | 2025-10-22 | 2025-10-30 | Subash | 33.38 | 3.7089 | TA421 | 4/1 | Completed
2025-10-28 | 2025-10-26 | 2025-11-02 | D K Verma | 37.931 | 4.7414 | TA421 | 43/1 | Completed
2025-10-28 | 2025-10-21 | 2025-11-02 | Hassan | 36.37 | 2.7977 | TA421 | 36/8 | Completed
2025-10-28 | 2025-10-28 | 2025-11-02 | Khatun | 36.37 | 6.0617 | TA421 | 11/7 | Completed
2025-10-28 | 2025-10-22 | 2025-10-30 | Subash | 33.38 | 3.7089 | TA421 | 4/1 | Completed
2025-10-29 | 2025-10-26 | 2025-11-02 | D K Verma | 37.931 | 4.7414 | TA421 | 43/1 | Completed
2025-10-29 | 2025-10-21 | 2025-11-02 | Hassan | 36.37 | 2.7977 | TA421 | 36/8 | Completed
2025-10-29 | 2025-10-28 | 2025-11-02 | Khatun | 36.37 | 6.0617 | TA421 | 11/7 | Completed
2025-10-29 | 2025-10-22 | 2025-10-30 | Subash | 33.38 | 3.7089 | TA421 | 4/1 | Completed
2025-10-30 | 2025-10-26 | 2025-11-02 | D K Verma | 37.931 | 4.7414 | TA421 | 43/1 | Completed
2025-10-30 | 2025-10-21 | 2025-11-02 | Hassan | 36.37 | 2.7977 | TA421 | 36/8 | Completed
2025-10-30 | 2025-10-28 | 2025-11-02 | Khatun | 36.37 | 6.0617 | TA421 | 11/7 | Completed
2025-10-30 | 2025-10-22 | 2025-10-30 | Subash | 33.38 | 3.7089 | TA421 | 4/1 | Completed
2025-10-31 | 2025-10-26 | 2025-11-02 | D K Verma | 37.931 | 4.7414 | TA421 | 43/1 | Completed
2025-10-31 | 2025-10-21 | 2025-11-02 | Hassan | 36.37 | 2.7977 | TA421 | 36/8 | Completed
2025-10-31 | 2025-10-28 | 2025-11-02 | Khatun | 36.37 | 6.0617 | TA421 | 11/7 | Completed
2025-10-31 | 2025-10-31 | 2025-11-05 | Subash | 31.99 | 5.3317 | TA421 | 4/13 | Completed
2025-11-01 | 2025-10-26 | 2025-11-02 | D K Verma | 37.931 | 4.7414 | TA421 | 43/1 | Completed
2025-11-01 | 2025-10-21 | 2025-11-02 | Hassan | 36.37 | 2.7977 | TA421 | 36/8 | Completed
2025-11-01 | 2025-10-28 | 2025-11-02 | Khatun | 36.37 | 6.0617 | TA421 | 11/7 | Completed
2025-11-01 | 2025-10-31 | 2025-11-05 | Subash | 31.99 | 5.3317 | TA421 | 4/13 | Completed
2025-11-02 | 2025-10-26 | 2025-11-02 | D K Verma | 37.931 | 4.7414 | TA421 | 43/1 | Completed
2025-11-02 | 2025-10-21 | 2025-11-02 | Hassan | 36.37 | 2.7977 | TA421 | 36/8 | Completed
2025-11-02 | 2025-10-28 | 2025-11-02 | Khatun | 36.37 | 6.0617 | TA421 | 11/7 | Completed
2025-11-02 | 2025-10-31 | 2025-11-05 | Subash | 31.99 | 5.3317 | TA421 | 4/13 | Completed
2025-11-03 | 2025-10-31 | 2025-11-05 | Subash | 31.99 | 5.3317 | TA421 | 4/13 | Completed
2025-11-04 | 2025-11-04 | 2025-11-11 | D K Verma | 64.89 | 8.1113 | TA421 | 43B/0 | Completed
2025-11-04 | 2025-11-04 | 2025-11-09 | Khatun | 61.15 | 10.1917 | TA421 | 8/3 | Completed
2025-11-04 | 2025-10-31 | 2025-11-05 | Subash | 31.99 | 5.3317 | TA421 | 4/13 | Completed
2025-11-05 | 2025-11-04 | 2025-11-11 | D K Verma | 64.89 | 8.1113 | TA421 | 43B/0 | Completed
2025-11-05 | 2025-11-04 | 2025-11-09 | Khatun | 61.15 | 10.1917 | TA421 | 8/3 | Completed
2025-11-05 | 2025-10-31 | 2025-11-05 | Subash | 31.99 | 5.3317 | TA421 | 4/13 | Completed
2025-11-06 | 2025-11-04 | 2025-11-11 | D K Verma | 64.89 | 8.1113 | TA421 | 43B/0 | Completed
2025-11-06 | 2025-11-04 | 2025-11-09 | Khatun | 61.15 | 10.1917 | TA421 | 8/3 | Completed
2025-11-06 | 2025-11-06 | 2025-11-11 | Subash | 39.17 | 6.5283 | TA421 | 3/1 | Completed
2025-11-07 | 2025-11-04 | 2025-11-11 | D K Verma | 64.89 | 8.1113 | TA421 | 43B/0 | Completed
2025-11-07 | 2025-11-04 | 2025-11-09 | Khatun | 61.15 | 10.1917 | TA421 | 8/3 | Completed
2025-11-07 | 2025-11-06 | 2025-11-11 | Subash | 39.17 | 6.5283 | TA421 | 3/1 | Completed
2025-11-08 | 2025-11-04 | 2025-11-11 | D K Verma | 64.89 | 8.1113 | TA421 | 43B/0 | Completed
2025-11-08 | 2025-11-04 | 2025-11-09 | Khatun | 61.15 | 10.1917 | TA421 | 8/3 | Completed
2025-11-08 | 2025-11-06 | 2025-11-11 | Subash | 39.17 | 6.5283 | TA421 | 3/1 | Completed
2025-11-09 | 2025-11-04 | 2025-11-11 | D K Verma | 64.89 | 8.1113 | TA421 | 43B/0 | Completed
2025-11-09 | 2025-11-04 | 2025-11-09 | Khatun | 61.15 | 10.1917 | TA421 | 8/3 | Completed
2025-11-09 | 2025-11-06 | 2025-11-11 | Subash | 39.17 | 6.5283 | TA421 | 3/1 | Completed
2025-11-10 | 2025-11-04 | 2025-11-11 | D K Verma | 64.89 | 8.1113 | TA421 | 43B/0 | Completed
2025-11-10 | 2025-11-10 | 2025-11-14 | Khatun | 58.93 | 11.786 | TA421 | 8/4 | Completed
2025-11-10 | 2025-11-06 | 2025-11-11 | Subash | 39.17 | 6.5283 | TA421 | 3/1 | Completed
2025-11-11 | 2025-11-04 | 2025-11-11 | D K Verma | 64.89 | 8.1113 | TA421 | 43B/0 | Completed
2025-11-11 | 2025-11-11 | 2025-11-17 | D K Verma | 37.931 | 5.4187 | TA421 | 43A/5 | Completed
2025-11-11 | 2025-11-10 | 2025-11-14 | Khatun | 58.93 | 11.786 | TA421 | 8/4 | Completed
2025-11-11 | 2025-11-06 | 2025-11-11 | Subash | 39.17 | 6.5283 | TA421 | 3/1 | Completed
2025-11-11 | 2025-11-11 | 2025-11-18 | Subash | 53.13 | 6.6413 | TA421 | 3/0 | Completed
2025-11-12 | 2025-11-11 | 2025-11-17 | D K Verma | 37.931 | 5.4187 | TA421 | 43A/5 | Completed
2025-11-12 | 2025-11-10 | 2025-11-14 | Khatun | 58.93 | 11.786 | TA421 | 8/4 | Completed
2025-11-12 | 2025-11-11 | 2025-11-18 | Subash | 53.13 | 6.6413 | TA421 | 3/0 | Completed
2025-11-13 | 2025-11-11 | 2025-11-17 | D K Verma | 37.931 | 5.4187 | TA421 | 43A/5 | Completed
2025-11-13 | 2025-11-10 | 2025-11-14 | Khatun | 58.93 | 11.786 | TA421 | 8/4 | Completed
2025-11-13 | 2025-11-11 | 2025-11-18 | Subash | 53.13 | 6.6413 | TA421 | 3/0 | Completed
2025-11-14 | 2025-11-11 | 2025-11-17 | D K Verma | 37.931 | 5.4187 | TA421 | 43A/5 | Completed
2025-11-14 | 2025-11-10 | 2025-11-14 | Khatun | 58.93 | 11.786 | TA421 | 8/4 | Completed
2025-11-14 | 2025-11-11 | 2025-11-18 | Subash | 53.13 | 6.6413 | TA421 | 3/0 | Completed
2025-11-15 | 2025-11-11 | 2025-11-17 | D K Verma | 37.931 | 5.4187 | TA421 | 43A/5 | Completed
2025-11-15 | 2025-11-11 | 2025-11-18 | Subash | 53.13 | 6.6413 | TA421 | 3/0 | Completed
2025-11-16 | 2025-11-11 | 2025-11-17 | D K Verma | 37.931 | 5.4187 | TA421 | 43A/5 | Completed
2025-11-16 | 2025-11-11 | 2025-11-18 | Subash | 53.13 | 6.6413 | TA421 | 3/0 | Completed
2025-11-17 | 2025-11-11 | 2025-11-17 | D K Verma | 37.931 | 5.4187 | TA421 | 43A/5 | Completed
2025-11-17 | 2025-11-11 | 2025-11-18 | Subash | 53.13 | 6.6413 | TA421 | 3/0 | Completed
2025-11-18 | 2025-11-11 | 2025-11-18 | Subash | 53.13 | 6.6413 | TA421 | 3/0 | Completed
2024-12-23 | 2024-12-23 | 2024-12-27 | Pankaj | 36.1598 | 7.232 | TA504 | 25/3. | Completed
2024-12-24 | 2024-12-23 | 2024-12-27 | Pankaj | 36.1598 | 7.232 | TA504 | 25/3. | Completed
2024-12-25 | 2024-12-23 | 2024-12-27 | Pankaj | 36.1598 | 7.232 | TA504 | 25/3. | Completed
2024-12-26 | 2024-12-23 | 2024-12-27 | Pankaj | 36.1598 | 7.232 | TA504 | 25/3. | Completed
2024-12-27 | 2024-12-23 | 2024-12-27 | Pankaj | 36.1598 | 7.232 | TA504 | 25/3. | Completed
2024-12-28 | 2024-12-28 | 2024-12-31 | Pankaj | 36.1598 | 9.0399 | TA504 | 25/4 | Completed
2024-12-29 | 2024-12-28 | 2024-12-31 | Pankaj | 36.1598 | 9.0399 | TA504 | 25/4 | Completed
2024-12-30 | 2024-12-28 | 2024-12-31 | Pankaj | 36.1598 | 9.0399 | TA504 | 25/4 | Completed
2024-12-31 | 2024-12-28 | 2024-12-31 | Pankaj | 36.1598 | 9.0399 | TA504 | 25/4 | Completed
2025-01-02 | 2025-01-02 | 2025-01-06 | Pankaj | 43.8044 | 8.7609 | TA504 | 26/1 | Completed
2025-01-03 | 2025-01-02 | 2025-01-06 | Pankaj | 43.8044 | 8.7609 | TA504 | 26/1 | Completed
2025-01-04 | 2025-01-02 | 2025-01-06 | Pankaj | 43.8044 | 8.7609 | TA504 | 26/1 | Completed
2025-01-05 | 2025-01-02 | 2025-01-06 | Pankaj | 43.8044 | 8.7609 | TA504 | 26/1 | Completed
2025-01-06 | 2025-01-02 | 2025-01-06 | Pankaj | 43.8044 | 8.7609 | TA504 | 26/1 | Completed
2025-01-07 | 2025-01-07 | 2025-01-09 | Pankaj | 37.9311 | 12.6437 | TA504 | 26/6 | Completed
2025-01-08 | 2025-01-07 | 2025-01-09 | Pankaj | 37.9311 | 12.6437 | TA504 | 26/6 | Completed
2025-01-09 | 2025-01-07 | 2025-01-09 | Pankaj | 37.9311 | 12.6437 | TA504 | 26/6 | Completed
2025-01-10 | 2025-01-10 | 2025-01-13 | Pankaj | 36.1598 | 9.0399 | TA504 | 26/5 | Completed
2025-01-11 | 2025-01-10 | 2025-01-13 | Pankaj | 36.1598 | 9.0399 | TA504 | 26/5 | Completed
2025-01-12 | 2025-01-10 | 2025-01-13 | Pankaj | 36.1598 | 9.0399 | TA504 | 26/5 | Completed
2025-01-13 | 2025-01-10 | 2025-01-13 | Pankaj | 36.1598 | 9.0399 | TA504 | 26/5 | Completed
2025-01-14 | 2025-01-14 | 2025-01-17 | Pankaj | 37.9311 | 9.4828 | TA504 | 26/3 | Completed
2025-01-15 | 2025-01-14 | 2025-01-17 | Pankaj | 37.9311 | 9.4828 | TA504 | 26/3 | Completed
2025-01-16 | 2025-01-14 | 2025-01-17 | Pankaj | 37.9311 | 9.4828 | TA504 | 26/3 | Completed
2025-01-17 | 2025-01-14 | 2025-01-17 | Pankaj | 37.9311 | 9.4828 | TA504 | 26/3 | Completed
2025-01-18 | 2025-01-18 | 2025-01-21 | Pankaj | 36.1598 | 9.0399 | TA504 | 26/8 | Completed
2025-01-19 | 2025-01-18 | 2025-01-21 | Pankaj | 36.1598 | 9.0399 | TA504 | 26/8 | Completed
2025-01-19 | 2025-01-19 | 2025-01-23 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 14/2 | Completed
2025-01-20 | 2025-01-18 | 2025-01-21 | Pankaj | 36.1598 | 9.0399 | TA504 | 26/8 | Completed
2025-01-20 | 2025-01-19 | 2025-01-23 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 14/2 | Completed
2025-01-21 | 2025-01-18 | 2025-01-21 | Pankaj | 36.1598 | 9.0399 | TA504 | 26/8 | Completed
2025-01-21 | 2025-01-19 | 2025-01-23 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 14/2 | Completed
2025-01-22 | 2025-01-22 | 2025-01-25 | Pankaj | 37.9311 | 9.4828 | TA504 | 22/4 | Completed
2025-01-22 | 2025-01-19 | 2025-01-23 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 14/2 | Completed
2025-01-23 | 2025-01-22 | 2025-01-25 | Pankaj | 37.9311 | 9.4828 | TA504 | 22/4 | Completed
2025-01-23 | 2025-01-19 | 2025-01-23 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 14/2 | Completed
2025-01-24 | 2025-01-22 | 2025-01-25 | Pankaj | 37.9311 | 9.4828 | TA504 | 22/4 | Completed
2025-01-24 | 2025-01-24 | 2025-01-27 | Pankaj 2 | 36.1598 | 9.0399 | TA504 | 14/3 | Completed
2025-01-25 | 2025-01-22 | 2025-01-25 | Pankaj | 37.9311 | 9.4828 | TA504 | 22/4 | Completed
2025-01-25 | 2025-01-24 | 2025-01-27 | Pankaj 2 | 36.1598 | 9.0399 | TA504 | 14/3 | Completed
2025-01-26 | 2025-01-26 | 2025-01-29 | Pankaj | 45.697 | 11.4243 | TA504 | 23/1 | Completed
2025-01-26 | 2025-01-24 | 2025-01-27 | Pankaj 2 | 36.1598 | 9.0399 | TA504 | 14/3 | Completed
2025-01-27 | 2025-01-26 | 2025-01-29 | Pankaj | 45.697 | 11.4243 | TA504 | 23/1 | Completed
2025-01-27 | 2025-01-24 | 2025-01-27 | Pankaj 2 | 36.1598 | 9.0399 | TA504 | 14/3 | Completed
2025-01-28 | 2025-01-26 | 2025-01-29 | Pankaj | 45.697 | 11.4243 | TA504 | 23/1 | Completed
2025-01-28 | 2025-01-28 | 2025-02-01 | Pankaj 2 | 37.9311 | 7.5862 | TA504 | 13/5 | Completed
2025-01-29 | 2025-01-26 | 2025-01-29 | Pankaj | 45.697 | 11.4243 | TA504 | 23/1 | Completed
2025-01-29 | 2025-01-28 | 2025-02-01 | Pankaj 2 | 37.9311 | 7.5862 | TA504 | 13/5 | Completed
2025-01-30 | 2025-01-30 | 2025-02-02 | Pankaj | 43.8044 | 10.9511 | TA504 | 22/3 | Completed
2025-01-30 | 2025-01-28 | 2025-02-01 | Pankaj 2 | 37.9311 | 7.5862 | TA504 | 13/5 | Completed
2025-01-31 | 2025-01-30 | 2025-02-02 | Pankaj | 43.8044 | 10.9511 | TA504 | 22/3 | Completed
2025-01-31 | 2025-01-28 | 2025-02-01 | Pankaj 2 | 37.9311 | 7.5862 | TA504 | 13/5 | Completed
2025-02-01 | 2025-01-30 | 2025-02-02 | Pankaj | 43.8044 | 10.9511 | TA504 | 22/3 | Completed
2025-02-01 | 2025-01-28 | 2025-02-01 | Pankaj 2 | 37.9311 | 7.5862 | TA504 | 13/5 | Completed
2025-02-02 | 2025-01-30 | 2025-02-02 | Pankaj | 43.8044 | 10.9511 | TA504 | 22/3 | Completed
2025-02-02 | 2025-02-02 | 2025-02-05 | Pankaj 2 | 37.9311 | 9.4828 | TA504 | 13/6 | Completed
2025-02-03 | 2025-02-03 | 2025-02-06 | Pankaj | 37.9311 | 9.4828 | TA504 | 22/1 | Completed
2025-02-03 | 2025-02-02 | 2025-02-05 | Pankaj 2 | 37.9311 | 9.4828 | TA504 | 13/6 | Completed
2025-02-04 | 2025-02-03 | 2025-02-06 | Pankaj | 37.9311 | 9.4828 | TA504 | 22/1 | Completed
2025-02-04 | 2025-02-02 | 2025-02-05 | Pankaj 2 | 37.9311 | 9.4828 | TA504 | 13/6 | Completed
2025-02-05 | 2025-02-03 | 2025-02-06 | Pankaj | 37.9311 | 9.4828 | TA504 | 22/1 | Completed
2025-02-05 | 2025-02-02 | 2025-02-05 | Pankaj 2 | 37.9311 | 9.4828 | TA504 | 13/6 | Completed
2025-02-06 | 2025-02-03 | 2025-02-06 | Pankaj | 37.9311 | 9.4828 | TA504 | 22/1 | Completed
2025-02-06 | 2025-02-06 | 2025-02-10 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 14/6 | Completed
2025-02-07 | 2025-02-07 | 2025-02-10 | Pankaj | 35.6018 | 8.9004 | TA504 | 22/2 | Completed
2025-02-07 | 2025-02-06 | 2025-02-10 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 14/6 | Completed
2025-02-08 | 2025-02-07 | 2025-02-10 | Pankaj | 35.6018 | 8.9004 | TA504 | 22/2 | Completed
2025-02-08 | 2025-02-06 | 2025-02-10 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 14/6 | Completed
2025-02-09 | 2025-02-07 | 2025-02-10 | Pankaj | 35.6018 | 8.9004 | TA504 | 22/2 | Completed
2025-02-09 | 2025-02-06 | 2025-02-10 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 14/6 | Completed
2025-02-10 | 2025-02-07 | 2025-02-10 | Pankaj | 35.6018 | 8.9004 | TA504 | 22/2 | Completed
2025-02-10 | 2025-02-06 | 2025-02-10 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 14/6 | Completed
2025-02-11 | 2025-02-11 | 2025-02-14 | Pankaj | 43.8044 | 10.9511 | TA504 | 23/3 | Completed
2025-02-11 | 2025-02-11 | 2025-02-15 | Pankaj 2 | 37.9311 | 7.5862 | TA504 | 14/7 | Completed
2025-02-12 | 2025-02-11 | 2025-02-14 | Pankaj | 43.8044 | 10.9511 | TA504 | 23/3 | Completed
2025-02-12 | 2025-02-11 | 2025-02-15 | Pankaj 2 | 37.9311 | 7.5862 | TA504 | 14/7 | Completed
2025-02-13 | 2025-02-11 | 2025-02-14 | Pankaj | 43.8044 | 10.9511 | TA504 | 23/3 | Completed
2025-02-13 | 2025-02-11 | 2025-02-15 | Pankaj 2 | 37.9311 | 7.5862 | TA504 | 14/7 | Completed
2025-02-14 | 2025-02-11 | 2025-02-14 | Pankaj | 43.8044 | 10.9511 | TA504 | 23/3 | Completed
2025-02-14 | 2025-02-11 | 2025-02-15 | Pankaj 2 | 37.9311 | 7.5862 | TA504 | 14/7 | Completed
2025-02-15 | 2025-02-15 | 2025-02-18 | Pankaj | 35.6018 | 8.9004 | TA504 | 23/4 | Completed
2025-02-15 | 2025-02-11 | 2025-02-15 | Pankaj 2 | 37.9311 | 7.5862 | TA504 | 14/7 | Completed
2025-02-16 | 2025-02-15 | 2025-02-18 | Pankaj | 35.6018 | 8.9004 | TA504 | 23/4 | Completed
2025-02-16 | 2025-02-16 | 2025-02-19 | Pankaj 2 | 37.9311 | 9.4828 | TA504 | 15/2 | Completed
2025-02-17 | 2025-02-15 | 2025-02-18 | Pankaj | 35.6018 | 8.9004 | TA504 | 23/4 | Completed
2025-02-17 | 2025-02-16 | 2025-02-19 | Pankaj 2 | 37.9311 | 9.4828 | TA504 | 15/2 | Completed
2025-02-18 | 2025-02-15 | 2025-02-18 | Pankaj | 35.6018 | 8.9004 | TA504 | 23/4 | Completed
2025-02-18 | 2025-02-16 | 2025-02-19 | Pankaj 2 | 37.9311 | 9.4828 | TA504 | 15/2 | Completed
2025-02-19 | 2025-02-19 | 2025-02-22 | Pankaj | 37.9311 | 9.4828 | TA504 | 23/5 | Completed
2025-02-19 | 2025-02-16 | 2025-02-19 | Pankaj 2 | 37.9311 | 9.4828 | TA504 | 15/2 | Completed
2025-02-20 | 2025-02-19 | 2025-02-22 | Pankaj | 37.9311 | 9.4828 | TA504 | 23/5 | Completed
2025-02-20 | 2025-02-20 | 2025-02-23 | Pankaj 2 | 36.1598 | 9.0399 | TA504 | 15/3 | Completed
2025-02-21 | 2025-02-19 | 2025-02-22 | Pankaj | 37.9311 | 9.4828 | TA504 | 23/5 | Completed
2025-02-21 | 2025-02-20 | 2025-02-23 | Pankaj 2 | 36.1598 | 9.0399 | TA504 | 15/3 | Completed
2025-02-22 | 2025-02-19 | 2025-02-22 | Pankaj | 37.9311 | 9.4828 | TA504 | 23/5 | Completed
2025-02-22 | 2025-02-20 | 2025-02-23 | Pankaj 2 | 36.1598 | 9.0399 | TA504 | 15/3 | Completed
2025-02-23 | 2025-02-23 | 2025-02-25 | Pankaj | 34.7898 | 11.5966 | TA504 | 23/6 | Completed
2025-02-23 | 2025-02-20 | 2025-02-23 | Pankaj 2 | 36.1598 | 9.0399 | TA504 | 15/3 | Completed
2025-02-24 | 2025-02-23 | 2025-02-25 | Pankaj | 34.7898 | 11.5966 | TA504 | 23/6 | Completed
2025-02-24 | 2025-02-24 | 2025-02-28 | Pankaj 2 | 37.9311 | 7.5862 | TA504 | 15/6 | Completed
2025-02-25 | 2025-02-23 | 2025-02-25 | Pankaj | 34.7898 | 11.5966 | TA504 | 23/6 | Completed
2025-02-25 | 2025-02-24 | 2025-02-28 | Pankaj 2 | 37.9311 | 7.5862 | TA504 | 15/6 | Completed
2025-02-26 | 2025-02-26 | 2025-02-28 | Pankaj | 34.7898 | 11.5966 | TA504 | 23/7 | Completed
2025-02-26 | 2025-02-24 | 2025-02-28 | Pankaj 2 | 37.9311 | 7.5862 | TA504 | 15/6 | Completed
2025-02-27 | 2025-02-26 | 2025-02-28 | Pankaj | 34.7898 | 11.5966 | TA504 | 23/7 | Completed
2025-02-27 | 2025-02-24 | 2025-02-28 | Pankaj 2 | 37.9311 | 7.5862 | TA504 | 15/6 | Completed
2025-02-28 | 2025-02-26 | 2025-02-28 | Pankaj | 34.7898 | 11.5966 | TA504 | 23/7 | Completed
2025-02-28 | 2025-02-24 | 2025-02-28 | Pankaj 2 | 37.9311 | 7.5862 | TA504 | 15/6 | Completed
2025-03-01 | 2025-03-01 | 2025-03-04 | Pankaj | 37.9311 | 9.4828 | TA504 | 18/6 | Completed
2025-03-01 | 2025-03-01 | 2025-03-04 | Pankaj 2 | 37.9311 | 9.4828 | TA504 | 15/4 | Completed
2025-03-02 | 2025-03-01 | 2025-03-04 | Pankaj | 37.9311 | 9.4828 | TA504 | 18/6 | Completed
2025-03-02 | 2025-03-01 | 2025-03-04 | Pankaj 2 | 37.9311 | 9.4828 | TA504 | 15/4 | Completed
2025-03-03 | 2025-03-01 | 2025-03-04 | Pankaj | 37.9311 | 9.4828 | TA504 | 18/6 | Completed
2025-03-03 | 2025-03-01 | 2025-03-04 | Pankaj 2 | 37.9311 | 9.4828 | TA504 | 15/4 | Completed
2025-03-04 | 2025-03-01 | 2025-03-04 | Pankaj | 37.9311 | 9.4828 | TA504 | 18/6 | Completed
2025-03-04 | 2025-03-01 | 2025-03-04 | Pankaj 2 | 37.9311 | 9.4828 | TA504 | 15/4 | Completed
2025-03-05 | 2025-03-05 | 2025-03-07 | Pankaj | 34.7898 | 11.5966 | TA504 | 18/8 | Completed
2025-03-05 | 2025-03-05 | 2025-03-08 | Pankaj 2 | 34.7898 | 8.6975 | TA504 | 15/5 | Completed
2025-03-06 | 2025-03-05 | 2025-03-07 | Pankaj | 34.7898 | 11.5966 | TA504 | 18/8 | Completed
2025-03-06 | 2025-03-05 | 2025-03-08 | Pankaj 2 | 34.7898 | 8.6975 | TA504 | 15/5 | Completed
2025-03-07 | 2025-03-05 | 2025-03-07 | Pankaj | 34.7898 | 11.5966 | TA504 | 18/8 | Completed
2025-03-07 | 2025-03-05 | 2025-03-08 | Pankaj 2 | 34.7898 | 8.6975 | TA504 | 15/5 | Completed
2025-03-08 | 2025-03-08 | 2025-03-11 | Pankaj | 36.1598 | 9.0399 | TA504 | 21/1 | Completed
2025-03-08 | 2025-03-05 | 2025-03-08 | Pankaj 2 | 34.7898 | 8.6975 | TA504 | 15/5 | Completed
2025-03-09 | 2025-03-08 | 2025-03-11 | Pankaj | 36.1598 | 9.0399 | TA504 | 21/1 | Completed
2025-03-09 | 2025-03-09 | 2025-03-13 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 16/5 | Completed
2025-03-10 | 2025-03-08 | 2025-03-11 | Pankaj | 36.1598 | 9.0399 | TA504 | 21/1 | Completed
2025-03-10 | 2025-03-09 | 2025-03-13 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 16/5 | Completed
2025-03-11 | 2025-03-08 | 2025-03-11 | Pankaj | 36.1598 | 9.0399 | TA504 | 21/1 | Completed
2025-03-11 | 2025-03-09 | 2025-03-13 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 16/5 | Completed
2025-03-12 | 2025-03-12 | 2025-03-17 | Pankaj | 36.1598 | 6.0266 | TA504 | 19/3 | Completed
2025-03-12 | 2025-03-09 | 2025-03-13 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 16/5 | Completed
2025-03-13 | 2025-03-12 | 2025-03-17 | Pankaj | 36.1598 | 6.0266 | TA504 | 19/3 | Completed
2025-03-13 | 2025-03-09 | 2025-03-13 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 16/5 | Completed
2025-03-13 | 2025-03-13 | 2025-03-18 | Pankaj 2 | 34.7898 | 5.7983 | TA504 | 16/6 | Completed
2025-03-14 | 2025-03-12 | 2025-03-17 | Pankaj | 36.1598 | 6.0266 | TA504 | 19/3 | Completed
2025-03-14 | 2025-03-13 | 2025-03-18 | Pankaj 2 | 34.7898 | 5.7983 | TA504 | 16/6 | Completed
2025-03-15 | 2025-03-12 | 2025-03-17 | Pankaj | 36.1598 | 6.0266 | TA504 | 19/3 | Completed
2025-03-15 | 2025-03-13 | 2025-03-18 | Pankaj 2 | 34.7898 | 5.7983 | TA504 | 16/6 | Completed
2025-03-16 | 2025-03-12 | 2025-03-17 | Pankaj | 36.1598 | 6.0266 | TA504 | 19/3 | Completed
2025-03-16 | 2025-03-13 | 2025-03-18 | Pankaj 2 | 34.7898 | 5.7983 | TA504 | 16/6 | Completed
2025-03-17 | 2025-03-12 | 2025-03-17 | Pankaj | 36.1598 | 6.0266 | TA504 | 19/3 | Completed
2025-03-17 | 2025-03-13 | 2025-03-18 | Pankaj 2 | 34.7898 | 5.7983 | TA504 | 16/6 | Completed
2025-03-18 | 2025-03-18 | 2025-03-21 | Pankaj | 35.6018 | 8.9004 | TA504 | 18/7 | Completed
2025-03-18 | 2025-03-13 | 2025-03-18 | Pankaj 2 | 34.7898 | 5.7983 | TA504 | 16/6 | Completed
2025-03-19 | 2025-03-18 | 2025-03-21 | Pankaj | 35.6018 | 8.9004 | TA504 | 18/7 | Completed
2025-03-19 | 2025-03-19 | 2025-03-22 | Pankaj 2 | 34.7898 | 8.6975 | TA504 | 16/2 | Completed
2025-03-20 | 2025-03-18 | 2025-03-21 | Pankaj | 35.6018 | 8.9004 | TA504 | 18/7 | Completed
2025-03-20 | 2025-03-19 | 2025-03-22 | Pankaj 2 | 34.7898 | 8.6975 | TA504 | 16/2 | Completed
2025-03-21 | 2025-03-18 | 2025-03-21 | Pankaj | 35.6018 | 8.9004 | TA504 | 18/7 | Completed
2025-03-21 | 2025-03-19 | 2025-03-22 | Pankaj 2 | 34.7898 | 8.6975 | TA504 | 16/2 | Completed
2025-03-22 | 2025-03-22 | 2025-03-26 | Pankaj | 43.8044 | 8.7609 | TA504 | 18/3 | Completed
2025-03-22 | 2025-03-19 | 2025-03-22 | Pankaj 2 | 34.7898 | 8.6975 | TA504 | 16/2 | Completed
2025-03-23 | 2025-03-22 | 2025-03-26 | Pankaj | 43.8044 | 8.7609 | TA504 | 18/3 | Completed
2025-03-23 | 2025-03-23 | 2025-03-27 | Pankaj 2 | 43.8044 | 8.7609 | TA504 | 16/1 | Completed
2025-03-24 | 2025-03-22 | 2025-03-26 | Pankaj | 43.8044 | 8.7609 | TA504 | 18/3 | Completed
2025-03-24 | 2025-03-23 | 2025-03-27 | Pankaj 2 | 43.8044 | 8.7609 | TA504 | 16/1 | Completed
2025-03-25 | 2025-03-22 | 2025-03-26 | Pankaj | 43.8044 | 8.7609 | TA504 | 18/3 | Completed
2025-03-25 | 2025-03-23 | 2025-03-27 | Pankaj 2 | 43.8044 | 8.7609 | TA504 | 16/1 | Completed
2025-03-26 | 2025-03-22 | 2025-03-26 | Pankaj | 43.8044 | 8.7609 | TA504 | 18/3 | Completed
2025-03-26 | 2025-03-23 | 2025-03-27 | Pankaj 2 | 43.8044 | 8.7609 | TA504 | 16/1 | Completed
2025-03-27 | 2025-03-27 | 2025-03-30 | Pankaj | 37.9311 | 9.4828 | TA504 | 18/5 | Completed
2025-03-27 | 2025-03-23 | 2025-03-27 | Pankaj 2 | 43.8044 | 8.7609 | TA504 | 16/1 | Completed
2025-03-28 | 2025-03-27 | 2025-03-30 | Pankaj | 37.9311 | 9.4828 | TA504 | 18/5 | Completed
2025-03-28 | 2025-03-28 | 2025-03-31 | Pankaj 2 | 37.9311 | 9.4828 | TA504 | 17/1 | Completed
2025-03-29 | 2025-03-27 | 2025-03-30 | Pankaj | 37.9311 | 9.4828 | TA504 | 18/5 | Completed
2025-03-29 | 2025-03-28 | 2025-03-31 | Pankaj 2 | 37.9311 | 9.4828 | TA504 | 17/1 | Completed
2025-03-30 | 2025-03-27 | 2025-03-30 | Pankaj | 37.9311 | 9.4828 | TA504 | 18/5 | Completed
2025-03-30 | 2025-03-28 | 2025-03-31 | Pankaj 2 | 37.9311 | 9.4828 | TA504 | 17/1 | Completed
2025-03-31 | 2025-03-31 | 2025-04-04 | Pankaj | 35.6018 | 7.1204 | TA504 | 18/4 | Completed
2025-03-31 | 2025-03-28 | 2025-03-31 | Pankaj 2 | 37.9311 | 9.4828 | TA504 | 17/1 | Completed
2025-04-01 | 2025-03-31 | 2025-04-04 | Pankaj | 35.6018 | 7.1204 | TA504 | 18/4 | Completed
2025-04-01 | 2025-04-01 | 2025-04-05 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 17/2 | Completed
2025-04-02 | 2025-03-31 | 2025-04-04 | Pankaj | 35.6018 | 7.1204 | TA504 | 18/4 | Completed
2025-04-02 | 2025-04-01 | 2025-04-05 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 17/2 | Completed
2025-04-03 | 2025-03-31 | 2025-04-04 | Pankaj | 35.6018 | 7.1204 | TA504 | 18/4 | Completed
2025-04-03 | 2025-04-01 | 2025-04-05 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 17/2 | Completed
2025-04-04 | 2025-03-31 | 2025-04-04 | Pankaj | 35.6018 | 7.1204 | TA504 | 18/4 | Completed
2025-04-04 | 2025-04-01 | 2025-04-05 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 17/2 | Completed
2025-04-05 | 2025-04-05 | 2025-04-08 | Pankaj | 36.1598 | 9.0399 | TA504 | 18/2 | Completed
2025-04-05 | 2025-04-01 | 2025-04-05 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 17/2 | Completed
2025-04-06 | 2025-04-05 | 2025-04-08 | Pankaj | 36.1598 | 9.0399 | TA504 | 18/2 | Completed
2025-04-06 | 2025-04-06 | 2025-04-12 | Pankaj 2 | 37.9311 | 5.4187 | TA504 | 17/3 | Completed
2025-04-07 | 2025-04-05 | 2025-04-08 | Pankaj | 36.1598 | 9.0399 | TA504 | 18/2 | Completed
2025-04-07 | 2025-04-06 | 2025-04-12 | Pankaj 2 | 37.9311 | 5.4187 | TA504 | 17/3 | Completed
2025-04-08 | 2025-04-05 | 2025-04-08 | Pankaj | 36.1598 | 9.0399 | TA504 | 18/2 | Completed
2025-04-08 | 2025-04-06 | 2025-04-12 | Pankaj 2 | 37.9311 | 5.4187 | TA504 | 17/3 | Completed
2025-04-09 | 2025-04-09 | 2025-04-15 | Pankaj | 36.1598 | 5.1657 | TA504 | 17/8 | Completed
2025-04-09 | 2025-04-06 | 2025-04-12 | Pankaj 2 | 37.9311 | 5.4187 | TA504 | 17/3 | Completed
2025-04-10 | 2025-04-09 | 2025-04-15 | Pankaj | 36.1598 | 5.1657 | TA504 | 17/8 | Completed
2025-04-10 | 2025-04-06 | 2025-04-12 | Pankaj 2 | 37.9311 | 5.4187 | TA504 | 17/3 | Completed
2025-04-11 | 2025-04-09 | 2025-04-15 | Pankaj | 36.1598 | 5.1657 | TA504 | 17/8 | Completed
2025-04-11 | 2025-04-06 | 2025-04-12 | Pankaj 2 | 37.9311 | 5.4187 | TA504 | 17/3 | Completed
2025-04-12 | 2025-04-09 | 2025-04-15 | Pankaj | 36.1598 | 5.1657 | TA504 | 17/8 | Completed
2025-04-12 | 2025-04-06 | 2025-04-12 | Pankaj 2 | 37.9311 | 5.4187 | TA504 | 17/3 | Completed
2025-04-13 | 2025-04-09 | 2025-04-15 | Pankaj | 36.1598 | 5.1657 | TA504 | 17/8 | Completed
2025-04-13 | 2025-04-13 | 2025-04-18 | Pankaj 2 | 45.697 | 7.6162 | TA504 | 17/5 | Completed
2025-04-14 | 2025-04-09 | 2025-04-15 | Pankaj | 36.1598 | 5.1657 | TA504 | 17/8 | Completed
2025-04-14 | 2025-04-13 | 2025-04-18 | Pankaj 2 | 45.697 | 7.6162 | TA504 | 17/5 | Completed
2025-04-15 | 2025-04-09 | 2025-04-15 | Pankaj | 36.1598 | 5.1657 | TA504 | 17/8 | Completed
2025-04-15 | 2025-04-13 | 2025-04-18 | Pankaj 2 | 45.697 | 7.6162 | TA504 | 17/5 | Completed
2025-04-16 | 2025-04-16 | 2025-04-20 | Pankaj | 35.6018 | 7.1204 | TA504 | 17/9 | Completed
2025-04-16 | 2025-04-13 | 2025-04-18 | Pankaj 2 | 45.697 | 7.6162 | TA504 | 17/5 | Completed
2025-04-17 | 2025-04-16 | 2025-04-20 | Pankaj | 35.6018 | 7.1204 | TA504 | 17/9 | Completed
2025-04-17 | 2025-04-13 | 2025-04-18 | Pankaj 2 | 45.697 | 7.6162 | TA504 | 17/5 | Completed
2025-04-18 | 2025-04-16 | 2025-04-20 | Pankaj | 35.6018 | 7.1204 | TA504 | 17/9 | Completed
2025-04-18 | 2025-04-13 | 2025-04-18 | Pankaj 2 | 45.697 | 7.6162 | TA504 | 17/5 | Completed
2025-04-19 | 2025-04-16 | 2025-04-20 | Pankaj | 35.6018 | 7.1204 | TA504 | 17/9 | Completed
2025-04-19 | 2025-04-19 | 2025-04-23 | Pankaj 2 | 37.9311 | 7.5862 | TA504 | 17/6 | Completed
2025-04-20 | 2025-04-16 | 2025-04-20 | Pankaj | 35.6018 | 7.1204 | TA504 | 17/9 | Completed
2025-04-20 | 2025-04-19 | 2025-04-23 | Pankaj 2 | 37.9311 | 7.5862 | TA504 | 17/6 | Completed
2025-04-21 | 2025-04-21 | 2025-04-28 | Pankaj | 45.697 | 5.7121 | TA504 | 17/7 | Completed
2025-04-21 | 2025-04-19 | 2025-04-23 | Pankaj 2 | 37.9311 | 7.5862 | TA504 | 17/6 | Completed
2025-04-22 | 2025-04-21 | 2025-04-28 | Pankaj | 45.697 | 5.7121 | TA504 | 17/7 | Completed
2025-04-22 | 2025-04-19 | 2025-04-23 | Pankaj 2 | 37.9311 | 7.5862 | TA504 | 17/6 | Completed
2025-04-23 | 2025-04-21 | 2025-04-28 | Pankaj | 45.697 | 5.7121 | TA504 | 17/7 | Completed
2025-04-23 | 2025-04-19 | 2025-04-23 | Pankaj 2 | 37.9311 | 7.5862 | TA504 | 17/6 | Completed
2025-04-24 | 2025-04-21 | 2025-04-28 | Pankaj | 45.697 | 5.7121 | TA504 | 17/7 | Completed
2025-04-24 | 2025-04-24 | 2025-04-29 | Pankaj 2 | 43.8044 | 7.3007 | TA504 | 15/7 | Completed
2025-04-25 | 2025-04-21 | 2025-04-28 | Pankaj | 45.697 | 5.7121 | TA504 | 17/7 | Completed
2025-04-25 | 2025-04-24 | 2025-04-29 | Pankaj 2 | 43.8044 | 7.3007 | TA504 | 15/7 | Completed
2025-04-26 | 2025-04-21 | 2025-04-28 | Pankaj | 45.697 | 5.7121 | TA504 | 17/7 | Completed
2025-04-26 | 2025-04-24 | 2025-04-29 | Pankaj 2 | 43.8044 | 7.3007 | TA504 | 15/7 | Completed
2025-04-27 | 2025-04-21 | 2025-04-28 | Pankaj | 45.697 | 5.7121 | TA504 | 17/7 | Completed
2025-04-27 | 2025-04-24 | 2025-04-29 | Pankaj 2 | 43.8044 | 7.3007 | TA504 | 15/7 | Completed
2025-04-28 | 2025-04-21 | 2025-04-28 | Pankaj | 45.697 | 5.7121 | TA504 | 17/7 | Completed
2025-04-28 | 2025-04-24 | 2025-04-29 | Pankaj 2 | 43.8044 | 7.3007 | TA504 | 15/7 | Completed
2025-04-29 | 2025-04-29 | 2025-05-07 | Pankaj | 37.9311 | 4.2146 | TA504 | 21/5 | Completed
2025-04-29 | 2025-04-24 | 2025-04-29 | Pankaj 2 | 43.8044 | 7.3007 | TA504 | 15/7 | Completed
2025-04-30 | 2025-04-29 | 2025-05-07 | Pankaj | 37.9311 | 4.2146 | TA504 | 21/5 | Completed
2025-04-30 | 2025-04-30 | 2025-05-07 | Pankaj 2 | 36.1598 | 4.52 | TA504 | 14/4 | Completed
2025-05-01 | 2025-04-29 | 2025-05-07 | Pankaj | 37.9311 | 4.2146 | TA504 | 21/5 | Completed
2025-05-01 | 2025-04-30 | 2025-05-07 | Pankaj 2 | 36.1598 | 4.52 | TA504 | 14/4 | Completed
2025-05-02 | 2025-04-29 | 2025-05-07 | Pankaj | 37.9311 | 4.2146 | TA504 | 21/5 | Completed
2025-05-02 | 2025-04-30 | 2025-05-07 | Pankaj 2 | 36.1598 | 4.52 | TA504 | 14/4 | Completed
2025-05-03 | 2025-04-29 | 2025-05-07 | Pankaj | 37.9311 | 4.2146 | TA504 | 21/5 | Completed
2025-05-03 | 2025-04-30 | 2025-05-07 | Pankaj 2 | 36.1598 | 4.52 | TA504 | 14/4 | Completed
2025-05-04 | 2025-04-29 | 2025-05-07 | Pankaj | 37.9311 | 4.2146 | TA504 | 21/5 | Completed
2025-05-04 | 2025-04-30 | 2025-05-07 | Pankaj 2 | 36.1598 | 4.52 | TA504 | 14/4 | Completed
2025-05-05 | 2025-04-29 | 2025-05-07 | Pankaj | 37.9311 | 4.2146 | TA504 | 21/5 | Completed
2025-05-05 | 2025-04-30 | 2025-05-07 | Pankaj 2 | 36.1598 | 4.52 | TA504 | 14/4 | Completed
2025-05-06 | 2025-04-29 | 2025-05-07 | Pankaj | 37.9311 | 4.2146 | TA504 | 21/5 | Completed
2025-05-06 | 2025-04-30 | 2025-05-07 | Pankaj 2 | 36.1598 | 4.52 | TA504 | 14/4 | Completed
2025-05-07 | 2025-04-29 | 2025-05-07 | Pankaj | 37.9311 | 4.2146 | TA504 | 21/5 | Completed
2025-05-07 | 2025-04-30 | 2025-05-07 | Pankaj 2 | 36.1598 | 4.52 | TA504 | 14/4 | Completed
2025-05-08 | 2025-05-08 | 2025-05-16 | Pankaj | 37.9311 | 4.2146 | TA504 | 21/4 | Completed
2025-05-08 | 2025-05-08 | 2025-05-16 | Pankaj 2 | 37.9311 | 4.2146 | TA504 | 14/5 | Completed
2025-05-09 | 2025-05-08 | 2025-05-16 | Pankaj | 37.9311 | 4.2146 | TA504 | 21/4 | Completed
2025-05-09 | 2025-05-08 | 2025-05-16 | Pankaj 2 | 37.9311 | 4.2146 | TA504 | 14/5 | Completed
2025-05-10 | 2025-05-08 | 2025-05-16 | Pankaj | 37.9311 | 4.2146 | TA504 | 21/4 | Completed
2025-05-10 | 2025-05-08 | 2025-05-16 | Pankaj 2 | 37.9311 | 4.2146 | TA504 | 14/5 | Completed
2025-05-11 | 2025-05-08 | 2025-05-16 | Pankaj | 37.9311 | 4.2146 | TA504 | 21/4 | Completed
2025-05-11 | 2025-05-08 | 2025-05-16 | Pankaj 2 | 37.9311 | 4.2146 | TA504 | 14/5 | Completed
2025-05-12 | 2025-05-08 | 2025-05-16 | Pankaj | 37.9311 | 4.2146 | TA504 | 21/4 | Completed
2025-05-12 | 2025-05-08 | 2025-05-16 | Pankaj 2 | 37.9311 | 4.2146 | TA504 | 14/5 | Completed
2025-05-13 | 2025-05-08 | 2025-05-16 | Pankaj | 37.9311 | 4.2146 | TA504 | 21/4 | Completed
2025-05-13 | 2025-05-08 | 2025-05-16 | Pankaj 2 | 37.9311 | 4.2146 | TA504 | 14/5 | Completed
2025-05-14 | 2025-05-08 | 2025-05-16 | Pankaj | 37.9311 | 4.2146 | TA504 | 21/4 | Completed
2025-05-14 | 2025-05-08 | 2025-05-16 | Pankaj 2 | 37.9311 | 4.2146 | TA504 | 14/5 | Completed
2025-05-15 | 2025-05-08 | 2025-05-16 | Pankaj | 37.9311 | 4.2146 | TA504 | 21/4 | Completed
2025-05-15 | 2025-05-08 | 2025-05-16 | Pankaj 2 | 37.9311 | 4.2146 | TA504 | 14/5 | Completed
2025-05-16 | 2025-05-08 | 2025-05-16 | Pankaj | 37.9311 | 4.2146 | TA504 | 21/4 | Completed
2025-05-16 | 2025-05-08 | 2025-05-16 | Pankaj 2 | 37.9311 | 4.2146 | TA504 | 14/5 | Completed
2025-05-17 | 2025-05-17 | 2025-05-21 | Pankaj | 37.9311 | 7.5862 | TA504 | 19/1 | Completed
2025-05-17 | 2025-05-17 | 2025-05-26 | Pankaj 2 | 43.8044 | 4.3804 | TA504 | 12/4 | Completed
2025-05-18 | 2025-05-17 | 2025-05-21 | Pankaj | 37.9311 | 7.5862 | TA504 | 19/1 | Completed
2025-05-18 | 2025-05-17 | 2025-05-26 | Pankaj 2 | 43.8044 | 4.3804 | TA504 | 12/4 | Completed
2025-05-19 | 2025-05-17 | 2025-05-21 | Pankaj | 37.9311 | 7.5862 | TA504 | 19/1 | Completed
2025-05-19 | 2025-05-17 | 2025-05-26 | Pankaj 2 | 43.8044 | 4.3804 | TA504 | 12/4 | Completed
2025-05-20 | 2025-05-17 | 2025-05-21 | Pankaj | 37.9311 | 7.5862 | TA504 | 19/1 | Completed
2025-05-20 | 2025-05-17 | 2025-05-26 | Pankaj 2 | 43.8044 | 4.3804 | TA504 | 12/4 | Completed
2025-05-21 | 2025-05-17 | 2025-05-21 | Pankaj | 37.9311 | 7.5862 | TA504 | 19/1 | Completed
2025-05-21 | 2025-05-17 | 2025-05-26 | Pankaj 2 | 43.8044 | 4.3804 | TA504 | 12/4 | Completed
2025-05-22 | 2025-05-22 | 2025-05-26 | Pankaj | 37.9311 | 7.5862 | TA504 | 21/2 | Completed
2025-05-22 | 2025-05-17 | 2025-05-26 | Pankaj 2 | 43.8044 | 4.3804 | TA504 | 12/4 | Completed
2025-05-23 | 2025-05-22 | 2025-05-26 | Pankaj | 37.9311 | 7.5862 | TA504 | 21/2 | Completed
2025-05-23 | 2025-05-17 | 2025-05-26 | Pankaj 2 | 43.8044 | 4.3804 | TA504 | 12/4 | Completed
2025-05-24 | 2025-05-22 | 2025-05-26 | Pankaj | 37.9311 | 7.5862 | TA504 | 21/2 | Completed
2025-05-24 | 2025-05-17 | 2025-05-26 | Pankaj 2 | 43.8044 | 4.3804 | TA504 | 12/4 | Completed
2025-05-25 | 2025-05-22 | 2025-05-26 | Pankaj | 37.9311 | 7.5862 | TA504 | 21/2 | Completed
2025-05-25 | 2025-05-17 | 2025-05-26 | Pankaj 2 | 43.8044 | 4.3804 | TA504 | 12/4 | Completed
2025-05-26 | 2025-05-22 | 2025-05-26 | Pankaj | 37.9311 | 7.5862 | TA504 | 21/2 | Completed
2025-05-26 | 2025-05-17 | 2025-05-26 | Pankaj 2 | 43.8044 | 4.3804 | TA504 | 12/4 | Completed
2025-05-27 | 2025-05-27 | 2025-06-03 | Pankaj 2 | 36.1598 | 4.52 | TA504 | 12/3 | Completed
2025-05-28 | 2025-05-27 | 2025-06-03 | Pankaj 2 | 36.1598 | 4.52 | TA504 | 12/3 | Completed
2025-05-29 | 2025-05-27 | 2025-06-03 | Pankaj 2 | 36.1598 | 4.52 | TA504 | 12/3 | Completed
2025-05-30 | 2025-05-27 | 2025-06-03 | Pankaj 2 | 36.1598 | 4.52 | TA504 | 12/3 | Completed
2025-05-31 | 2025-05-27 | 2025-06-03 | Pankaj 2 | 36.1598 | 4.52 | TA504 | 12/3 | Completed
2025-06-01 | 2025-05-27 | 2025-06-03 | Pankaj 2 | 36.1598 | 4.52 | TA504 | 12/3 | Completed
2025-06-02 | 2025-05-27 | 2025-06-03 | Pankaj 2 | 36.1598 | 4.52 | TA504 | 12/3 | Completed
2025-06-03 | 2025-05-27 | 2025-06-03 | Pankaj 2 | 36.1598 | 4.52 | TA504 | 12/3 | Completed
2025-06-04 | 2025-06-04 | 2025-06-10 | Pankaj 2 | 43.8044 | 6.2578 | TA504 | 12/5 | Completed
2025-06-05 | 2025-06-04 | 2025-06-10 | Pankaj 2 | 43.8044 | 6.2578 | TA504 | 12/5 | Completed
2025-06-06 | 2025-06-04 | 2025-06-10 | Pankaj 2 | 43.8044 | 6.2578 | TA504 | 12/5 | Completed
2025-06-07 | 2025-06-04 | 2025-06-10 | Pankaj 2 | 43.8044 | 6.2578 | TA504 | 12/5 | Completed
2025-06-08 | 2025-06-04 | 2025-06-10 | Pankaj 2 | 43.8044 | 6.2578 | TA504 | 12/5 | Completed
2025-06-09 | 2025-06-04 | 2025-06-10 | Pankaj 2 | 43.8044 | 6.2578 | TA504 | 12/5 | Completed
2025-06-10 | 2025-06-04 | 2025-06-10 | Pankaj 2 | 43.8044 | 6.2578 | TA504 | 12/5 | Completed
2025-06-11 | 2025-06-11 | 2025-06-15 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 12/2 | Completed
2025-06-12 | 2025-06-11 | 2025-06-15 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 12/2 | Completed
2025-06-13 | 2025-06-11 | 2025-06-15 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 12/2 | Completed
2025-06-14 | 2025-06-11 | 2025-06-15 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 12/2 | Completed
2025-06-15 | 2025-06-11 | 2025-06-15 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 12/2 | Completed
2025-06-16 | 2025-06-16 | 2025-06-20 | Pankaj 2 | 34.7898 | 6.958 | TA504 | 12/1 | Completed
2025-06-17 | 2025-06-16 | 2025-06-20 | Pankaj 2 | 34.7898 | 6.958 | TA504 | 12/1 | Completed
2025-06-18 | 2025-06-16 | 2025-06-20 | Pankaj 2 | 34.7898 | 6.958 | TA504 | 12/1 | Completed
2025-06-19 | 2025-06-16 | 2025-06-20 | Pankaj 2 | 34.7898 | 6.958 | TA504 | 12/1 | Completed
2025-06-20 | 2025-06-16 | 2025-06-20 | Pankaj 2 | 34.7898 | 6.958 | TA504 | 12/1 | Completed
2025-07-07 | 2025-07-07 | 2025-07-21 | Sainik Traders | 36.1598 | 2.4107 | TA504 | 11/4 | Completed
2025-07-08 | 2025-07-07 | 2025-07-21 | Sainik Traders | 36.1598 | 2.4107 | TA504 | 11/4 | Completed
2025-07-09 | 2025-07-07 | 2025-07-21 | Sainik Traders | 36.1598 | 2.4107 | TA504 | 11/4 | Completed
2025-07-10 | 2025-07-07 | 2025-07-21 | Sainik Traders | 36.1598 | 2.4107 | TA504 | 11/4 | Completed
2025-07-11 | 2025-07-07 | 2025-07-21 | Sainik Traders | 36.1598 | 2.4107 | TA504 | 11/4 | Completed
2025-07-12 | 2025-07-07 | 2025-07-21 | Sainik Traders | 36.1598 | 2.4107 | TA504 | 11/4 | Completed
2025-07-13 | 2025-07-07 | 2025-07-21 | Sainik Traders | 36.1598 | 2.4107 | TA504 | 11/4 | Completed
2025-07-14 | 2025-07-07 | 2025-07-21 | Sainik Traders | 36.1598 | 2.4107 | TA504 | 11/4 | Completed
2025-07-15 | 2025-07-07 | 2025-07-21 | Sainik Traders | 36.1598 | 2.4107 | TA504 | 11/4 | Completed
2025-07-16 | 2025-07-07 | 2025-07-21 | Sainik Traders | 36.1598 | 2.4107 | TA504 | 11/4 | Completed
2025-07-17 | 2025-07-07 | 2025-07-21 | Sainik Traders | 36.1598 | 2.4107 | TA504 | 11/4 | Completed
2025-07-18 | 2025-07-07 | 2025-07-21 | Sainik Traders | 36.1598 | 2.4107 | TA504 | 11/4 | Completed
2025-07-19 | 2025-07-07 | 2025-07-21 | Sainik Traders | 36.1598 | 2.4107 | TA504 | 11/4 | Completed
2025-07-20 | 2025-07-07 | 2025-07-21 | Sainik Traders | 36.1598 | 2.4107 | TA504 | 11/4 | Completed
2025-07-21 | 2025-07-07 | 2025-07-21 | Sainik Traders | 36.1598 | 2.4107 | TA504 | 11/4 | Completed
2025-07-21 | 2025-07-21 | 2025-07-30 | Sainik Traders | 36.1598 | 3.616 | TA504 | 11/1 | Completed
2025-07-22 | 2025-07-21 | 2025-07-30 | Sainik Traders | 36.1598 | 3.616 | TA504 | 11/1 | Completed
2025-07-23 | 2025-07-21 | 2025-07-30 | Sainik Traders | 36.1598 | 3.616 | TA504 | 11/1 | Completed
2025-07-24 | 2025-07-21 | 2025-07-30 | Sainik Traders | 36.1598 | 3.616 | TA504 | 11/1 | Completed
2025-07-25 | 2025-07-21 | 2025-07-30 | Sainik Traders | 36.1598 | 3.616 | TA504 | 11/1 | Completed
2025-07-26 | 2025-07-21 | 2025-07-30 | Sainik Traders | 36.1598 | 3.616 | TA504 | 11/1 | Completed
2025-07-27 | 2025-07-21 | 2025-07-30 | Sainik Traders | 36.1598 | 3.616 | TA504 | 11/1 | Completed
2025-07-28 | 2025-07-21 | 2025-07-30 | Sainik Traders | 36.1598 | 3.616 | TA504 | 11/1 | Completed
2025-07-29 | 2025-07-21 | 2025-07-30 | Sainik Traders | 36.1598 | 3.616 | TA504 | 11/1 | Completed
2025-07-30 | 2025-07-21 | 2025-07-30 | Sainik Traders | 36.1598 | 3.616 | TA504 | 11/1 | Completed
2025-08-01 | 2025-08-01 | 2025-08-13 | Sainik Traders | 36.1598 | 2.7815 | TA504 | 11/2 | Completed
2025-08-02 | 2025-08-01 | 2025-08-13 | Sainik Traders | 36.1598 | 2.7815 | TA504 | 11/2 | Completed
2025-08-03 | 2025-08-01 | 2025-08-13 | Sainik Traders | 36.1598 | 2.7815 | TA504 | 11/2 | Completed
2025-08-04 | 2025-08-01 | 2025-08-13 | Sainik Traders | 36.1598 | 2.7815 | TA504 | 11/2 | Completed
2025-08-05 | 2025-08-01 | 2025-08-13 | Sainik Traders | 36.1598 | 2.7815 | TA504 | 11/2 | Completed
2025-08-06 | 2025-08-01 | 2025-08-13 | Sainik Traders | 36.1598 | 2.7815 | TA504 | 11/2 | Completed
2025-08-07 | 2025-08-01 | 2025-08-13 | Sainik Traders | 36.1598 | 2.7815 | TA504 | 11/2 | Completed
2025-08-08 | 2025-08-01 | 2025-08-13 | Sainik Traders | 36.1598 | 2.7815 | TA504 | 11/2 | Completed
2025-08-09 | 2025-08-01 | 2025-08-13 | Sainik Traders | 36.1598 | 2.7815 | TA504 | 11/2 | Completed
2025-08-10 | 2025-08-01 | 2025-08-13 | Sainik Traders | 36.1598 | 2.7815 | TA504 | 11/2 | Completed
2025-08-11 | 2025-08-01 | 2025-08-13 | Sainik Traders | 36.1598 | 2.7815 | TA504 | 11/2 | Completed
2025-08-12 | 2025-08-01 | 2025-08-13 | Sainik Traders | 36.1598 | 2.7815 | TA504 | 11/2 | Completed
2025-08-13 | 2025-08-01 | 2025-08-13 | Sainik Traders | 36.1598 | 2.7815 | TA504 | 11/2 | Completed
2025-08-14 | 2025-08-14 | 2025-08-31 | Sainik Traders | 37.9311 | 2.1073 | TA504 | 11/3 | Completed
2025-08-15 | 2025-08-14 | 2025-08-31 | Sainik Traders | 37.9311 | 2.1073 | TA504 | 11/3 | Completed
2025-08-16 | 2025-08-14 | 2025-08-31 | Sainik Traders | 37.9311 | 2.1073 | TA504 | 11/3 | Completed
2025-08-17 | 2025-08-14 | 2025-08-31 | Sainik Traders | 37.9311 | 2.1073 | TA504 | 11/3 | Completed
2025-08-18 | 2025-08-14 | 2025-08-31 | Sainik Traders | 37.9311 | 2.1073 | TA504 | 11/3 | Completed
2025-08-19 | 2025-08-14 | 2025-08-31 | Sainik Traders | 37.9311 | 2.1073 | TA504 | 11/3 | Completed
2025-08-20 | 2025-08-14 | 2025-08-31 | Sainik Traders | 37.9311 | 2.1073 | TA504 | 11/3 | Completed
2025-08-21 | 2025-08-14 | 2025-08-31 | Sainik Traders | 37.9311 | 2.1073 | TA504 | 11/3 | Completed
2025-08-22 | 2025-08-14 | 2025-08-31 | Sainik Traders | 37.9311 | 2.1073 | TA504 | 11/3 | Completed
2025-08-23 | 2025-08-14 | 2025-08-31 | Sainik Traders | 37.9311 | 2.1073 | TA504 | 11/3 | Completed
2025-08-24 | 2025-08-14 | 2025-08-31 | Sainik Traders | 37.9311 | 2.1073 | TA504 | 11/3 | Completed
2025-08-25 | 2025-08-25 | 2025-09-08 | Pinki Devi | 59.5006 | 3.9667 | TA504 | 17/0 | Completed
2025-08-25 | 2025-08-14 | 2025-08-31 | Sainik Traders | 37.9311 | 2.1073 | TA504 | 11/3 | Completed
2025-08-26 | 2025-08-26 | 2025-09-10 | Ghyansham Mahto | 36.1598 | 2.26 | TA504 | 23/2 | Completed
2025-08-26 | 2025-08-25 | 2025-09-08 | Pinki Devi | 59.5006 | 3.9667 | TA504 | 17/0 | Completed
2025-08-26 | 2025-08-14 | 2025-08-31 | Sainik Traders | 37.9311 | 2.1073 | TA504 | 11/3 | Completed
2025-08-27 | 2025-08-26 | 2025-09-10 | Ghyansham Mahto | 36.1598 | 2.26 | TA504 | 23/2 | Completed
2025-08-27 | 2025-08-25 | 2025-09-08 | Pinki Devi | 59.5006 | 3.9667 | TA504 | 17/0 | Completed
2025-08-27 | 2025-08-14 | 2025-08-31 | Sainik Traders | 37.9311 | 2.1073 | TA504 | 11/3 | Completed
2025-08-28 | 2025-08-26 | 2025-09-10 | Ghyansham Mahto | 36.1598 | 2.26 | TA504 | 23/2 | Completed
2025-08-28 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-08-28 | 2025-08-28 | 2025-09-17 | Neha Const | 37.9311 | 1.8062 | TA504 | 30/2 | Completed
2025-08-28 | 2025-08-25 | 2025-09-08 | Pinki Devi | 59.5006 | 3.9667 | TA504 | 17/0 | Completed
2025-08-28 | 2025-08-14 | 2025-08-31 | Sainik Traders | 37.9311 | 2.1073 | TA504 | 11/3 | Completed
2025-08-29 | 2025-08-26 | 2025-09-10 | Ghyansham Mahto | 36.1598 | 2.26 | TA504 | 23/2 | Completed
2025-08-29 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-08-29 | 2025-08-28 | 2025-09-17 | Neha Const | 37.9311 | 1.8062 | TA504 | 30/2 | Completed
2025-08-29 | 2025-08-25 | 2025-09-08 | Pinki Devi | 59.5006 | 3.9667 | TA504 | 17/0 | Completed
2025-08-29 | 2025-08-14 | 2025-08-31 | Sainik Traders | 37.9311 | 2.1073 | TA504 | 11/3 | Completed
2025-08-30 | 2025-08-26 | 2025-09-10 | Ghyansham Mahto | 36.1598 | 2.26 | TA504 | 23/2 | Completed
2025-08-30 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-08-30 | 2025-08-28 | 2025-09-17 | Neha Const | 37.9311 | 1.8062 | TA504 | 30/2 | Completed
2025-08-30 | 2025-08-25 | 2025-09-08 | Pinki Devi | 59.5006 | 3.9667 | TA504 | 17/0 | Completed
2025-08-30 | 2025-08-14 | 2025-08-31 | Sainik Traders | 37.9311 | 2.1073 | TA504 | 11/3 | Completed
2025-08-31 | 2025-08-26 | 2025-09-10 | Ghyansham Mahto | 36.1598 | 2.26 | TA504 | 23/2 | Completed
2025-08-31 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-08-31 | 2025-08-28 | 2025-09-17 | Neha Const | 37.9311 | 1.8062 | TA504 | 30/2 | Completed
2025-08-31 | 2025-08-25 | 2025-09-08 | Pinki Devi | 59.5006 | 3.9667 | TA504 | 17/0 | Completed
2025-08-31 | 2025-08-14 | 2025-08-31 | Sainik Traders | 37.9311 | 2.1073 | TA504 | 11/3 | Completed
2025-09-01 | 2025-08-26 | 2025-09-10 | Ghyansham Mahto | 36.1598 | 2.26 | TA504 | 23/2 | Completed
2025-09-01 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-09-01 | 2025-08-28 | 2025-09-17 | Neha Const | 37.9311 | 1.8062 | TA504 | 30/2 | Completed
2025-09-01 | 2025-08-25 | 2025-09-08 | Pinki Devi | 59.5006 | 3.9667 | TA504 | 17/0 | Completed
2025-09-02 | 2025-08-26 | 2025-09-10 | Ghyansham Mahto | 36.1598 | 2.26 | TA504 | 23/2 | Completed
2025-09-02 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-09-02 | 2025-08-28 | 2025-09-17 | Neha Const | 37.9311 | 1.8062 | TA504 | 30/2 | Completed
2025-09-02 | 2025-08-25 | 2025-09-08 | Pinki Devi | 59.5006 | 3.9667 | TA504 | 17/0 | Completed
2025-09-03 | 2025-08-26 | 2025-09-10 | Ghyansham Mahto | 36.1598 | 2.26 | TA504 | 23/2 | Completed
2025-09-03 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-09-03 | 2025-08-28 | 2025-09-17 | Neha Const | 37.9311 | 1.8062 | TA504 | 30/2 | Completed
2025-09-03 | 2025-08-25 | 2025-09-08 | Pinki Devi | 59.5006 | 3.9667 | TA504 | 17/0 | Completed
2025-09-03 | 2025-09-03 | 2025-09-22 | Sainik Traders | 59.5006 | 2.975 | TA504 | 11/0 | Completed
2025-09-04 | 2025-08-26 | 2025-09-10 | Ghyansham Mahto | 36.1598 | 2.26 | TA504 | 23/2 | Completed
2025-09-04 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-09-04 | 2025-08-28 | 2025-09-17 | Neha Const | 37.9311 | 1.8062 | TA504 | 30/2 | Completed
2025-09-04 | 2025-08-25 | 2025-09-08 | Pinki Devi | 59.5006 | 3.9667 | TA504 | 17/0 | Completed
2025-09-04 | 2025-09-03 | 2025-09-22 | Sainik Traders | 59.5006 | 2.975 | TA504 | 11/0 | Completed
2025-09-05 | 2025-08-26 | 2025-09-10 | Ghyansham Mahto | 36.1598 | 2.26 | TA504 | 23/2 | Completed
2025-09-05 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-09-05 | 2025-08-28 | 2025-09-17 | Neha Const | 37.9311 | 1.8062 | TA504 | 30/2 | Completed
2025-09-05 | 2025-08-25 | 2025-09-08 | Pinki Devi | 59.5006 | 3.9667 | TA504 | 17/0 | Completed
2025-09-05 | 2025-09-03 | 2025-09-22 | Sainik Traders | 59.5006 | 2.975 | TA504 | 11/0 | Completed
2025-09-06 | 2025-08-26 | 2025-09-10 | Ghyansham Mahto | 36.1598 | 2.26 | TA504 | 23/2 | Completed
2025-09-06 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-09-06 | 2025-08-28 | 2025-09-17 | Neha Const | 37.9311 | 1.8062 | TA504 | 30/2 | Completed
2025-09-06 | 2025-08-25 | 2025-09-08 | Pinki Devi | 59.5006 | 3.9667 | TA504 | 17/0 | Completed
2025-09-06 | 2025-09-03 | 2025-09-22 | Sainik Traders | 59.5006 | 2.975 | TA504 | 11/0 | Completed
2025-09-07 | 2025-08-26 | 2025-09-10 | Ghyansham Mahto | 36.1598 | 2.26 | TA504 | 23/2 | Completed
2025-09-07 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-09-07 | 2025-08-28 | 2025-09-17 | Neha Const | 37.9311 | 1.8062 | TA504 | 30/2 | Completed
2025-09-07 | 2025-08-25 | 2025-09-08 | Pinki Devi | 59.5006 | 3.9667 | TA504 | 17/0 | Completed
2025-09-07 | 2025-09-03 | 2025-09-22 | Sainik Traders | 59.5006 | 2.975 | TA504 | 11/0 | Completed
2025-09-08 | 2025-08-26 | 2025-09-10 | Ghyansham Mahto | 36.1598 | 2.26 | TA504 | 23/2 | Completed
2025-09-08 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-09-08 | 2025-08-28 | 2025-09-17 | Neha Const | 37.9311 | 1.8062 | TA504 | 30/2 | Completed
2025-09-08 | 2025-08-25 | 2025-09-08 | Pinki Devi | 59.5006 | 3.9667 | TA504 | 17/0 | Completed
2025-09-08 | 2025-09-03 | 2025-09-22 | Sainik Traders | 59.5006 | 2.975 | TA504 | 11/0 | Completed
2025-09-09 | 2025-08-26 | 2025-09-10 | Ghyansham Mahto | 36.1598 | 2.26 | TA504 | 23/2 | Completed
2025-09-09 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-09-09 | 2025-08-28 | 2025-09-17 | Neha Const | 37.9311 | 1.8062 | TA504 | 30/2 | Completed
2025-09-09 | 2025-09-09 | 2025-09-21 | Pinki Devi | 66.7757 | 5.1366 | TA504 | 18/0 | Completed
2025-09-09 | 2025-09-03 | 2025-09-22 | Sainik Traders | 59.5006 | 2.975 | TA504 | 11/0 | Completed
2025-09-10 | 2025-08-26 | 2025-09-10 | Ghyansham Mahto | 36.1598 | 2.26 | TA504 | 23/2 | Completed
2025-09-10 | 2025-09-10 | 2025-09-26 | Ghyansham Mahto | 66.7757 | 3.928 | TA504 | 24/1 | Completed
2025-09-10 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-09-10 | 2025-08-28 | 2025-09-17 | Neha Const | 37.9311 | 1.8062 | TA504 | 30/2 | Completed
2025-09-10 | 2025-09-09 | 2025-09-21 | Pinki Devi | 66.7757 | 5.1366 | TA504 | 18/0 | Completed
2025-09-10 | 2025-09-03 | 2025-09-22 | Sainik Traders | 59.5006 | 2.975 | TA504 | 11/0 | Completed
2025-09-11 | 2025-09-10 | 2025-09-26 | Ghyansham Mahto | 66.7757 | 3.928 | TA504 | 24/1 | Completed
2025-09-11 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-09-11 | 2025-08-28 | 2025-09-17 | Neha Const | 37.9311 | 1.8062 | TA504 | 30/2 | Completed
2025-09-11 | 2025-09-09 | 2025-09-21 | Pinki Devi | 66.7757 | 5.1366 | TA504 | 18/0 | Completed
2025-09-11 | 2025-09-03 | 2025-09-22 | Sainik Traders | 59.5006 | 2.975 | TA504 | 11/0 | Completed
2025-09-12 | 2025-09-10 | 2025-09-26 | Ghyansham Mahto | 66.7757 | 3.928 | TA504 | 24/1 | Completed
2025-09-12 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-09-12 | 2025-08-28 | 2025-09-17 | Neha Const | 37.9311 | 1.8062 | TA504 | 30/2 | Completed
2025-09-12 | 2025-09-09 | 2025-09-21 | Pinki Devi | 66.7757 | 5.1366 | TA504 | 18/0 | Completed
2025-09-12 | 2025-09-03 | 2025-09-22 | Sainik Traders | 59.5006 | 2.975 | TA504 | 11/0 | Completed
2025-09-13 | 2025-09-10 | 2025-09-26 | Ghyansham Mahto | 66.7757 | 3.928 | TA504 | 24/1 | Completed
2025-09-13 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-09-13 | 2025-08-28 | 2025-09-17 | Neha Const | 37.9311 | 1.8062 | TA504 | 30/2 | Completed
2025-09-13 | 2025-09-09 | 2025-09-21 | Pinki Devi | 66.7757 | 5.1366 | TA504 | 18/0 | Completed
2025-09-13 | 2025-09-03 | 2025-09-22 | Sainik Traders | 59.5006 | 2.975 | TA504 | 11/0 | Completed
2025-09-14 | 2025-09-10 | 2025-09-26 | Ghyansham Mahto | 66.7757 | 3.928 | TA504 | 24/1 | Completed
2025-09-14 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-09-14 | 2025-08-28 | 2025-09-17 | Neha Const | 37.9311 | 1.8062 | TA504 | 30/2 | Completed
2025-09-14 | 2025-09-09 | 2025-09-21 | Pinki Devi | 66.7757 | 5.1366 | TA504 | 18/0 | Completed
2025-09-14 | 2025-09-03 | 2025-09-22 | Sainik Traders | 59.5006 | 2.975 | TA504 | 11/0 | Completed
2025-09-15 | 2025-09-10 | 2025-09-26 | Ghyansham Mahto | 66.7757 | 3.928 | TA504 | 24/1 | Completed
2025-09-15 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-09-15 | 2025-08-28 | 2025-09-17 | Neha Const | 37.9311 | 1.8062 | TA504 | 30/2 | Completed
2025-09-15 | 2025-09-09 | 2025-09-21 | Pinki Devi | 66.7757 | 5.1366 | TA504 | 18/0 | Completed
2025-09-15 | 2025-09-03 | 2025-09-22 | Sainik Traders | 59.5006 | 2.975 | TA504 | 11/0 | Completed
2025-09-16 | 2025-09-10 | 2025-09-26 | Ghyansham Mahto | 66.7757 | 3.928 | TA504 | 24/1 | Completed
2025-09-16 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-09-16 | 2025-08-28 | 2025-09-17 | Neha Const | 37.9311 | 1.8062 | TA504 | 30/2 | Completed
2025-09-16 | 2025-09-09 | 2025-09-21 | Pinki Devi | 66.7757 | 5.1366 | TA504 | 18/0 | Completed
2025-09-16 | 2025-09-03 | 2025-09-22 | Sainik Traders | 59.5006 | 2.975 | TA504 | 11/0 | Completed
2025-09-17 | 2025-09-10 | 2025-09-26 | Ghyansham Mahto | 66.7757 | 3.928 | TA504 | 24/1 | Completed
2025-09-17 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-09-17 | 2025-08-28 | 2025-09-17 | Neha Const | 37.9311 | 1.8062 | TA504 | 30/2 | Completed
2025-09-17 | 2025-09-09 | 2025-09-21 | Pinki Devi | 66.7757 | 5.1366 | TA504 | 18/0 | Completed
2025-09-17 | 2025-09-03 | 2025-09-22 | Sainik Traders | 59.5006 | 2.975 | TA504 | 11/0 | Completed
2025-09-18 | 2025-09-10 | 2025-09-26 | Ghyansham Mahto | 66.7757 | 3.928 | TA504 | 24/1 | Completed
2025-09-18 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-09-18 | 2025-09-18 | 2025-09-26 | Neha Const | 36.1598 | 4.0178 | TA504 | 29/2 | Completed
2025-09-18 | 2025-09-09 | 2025-09-21 | Pinki Devi | 66.7757 | 5.1366 | TA504 | 18/0 | Completed
2025-09-18 | 2025-09-03 | 2025-09-22 | Sainik Traders | 59.5006 | 2.975 | TA504 | 11/0 | Completed
2025-09-19 | 2025-09-10 | 2025-09-26 | Ghyansham Mahto | 66.7757 | 3.928 | TA504 | 24/1 | Completed
2025-09-19 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-09-19 | 2025-09-18 | 2025-09-26 | Neha Const | 36.1598 | 4.0178 | TA504 | 29/2 | Completed
2025-09-19 | 2025-09-09 | 2025-09-21 | Pinki Devi | 66.7757 | 5.1366 | TA504 | 18/0 | Completed
2025-09-19 | 2025-09-03 | 2025-09-22 | Sainik Traders | 59.5006 | 2.975 | TA504 | 11/0 | Completed
2025-09-20 | 2025-09-10 | 2025-09-26 | Ghyansham Mahto | 66.7757 | 3.928 | TA504 | 24/1 | Completed
2025-09-20 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-09-20 | 2025-09-18 | 2025-09-26 | Neha Const | 36.1598 | 4.0178 | TA504 | 29/2 | Completed
2025-09-20 | 2025-09-09 | 2025-09-21 | Pinki Devi | 66.7757 | 5.1366 | TA504 | 18/0 | Completed
2025-09-20 | 2025-09-03 | 2025-09-22 | Sainik Traders | 59.5006 | 2.975 | TA504 | 11/0 | Completed
2025-09-21 | 2025-09-10 | 2025-09-26 | Ghyansham Mahto | 66.7757 | 3.928 | TA504 | 24/1 | Completed
2025-09-21 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-09-21 | 2025-09-18 | 2025-09-26 | Neha Const | 36.1598 | 4.0178 | TA504 | 29/2 | Completed
2025-09-21 | 2025-09-09 | 2025-09-21 | Pinki Devi | 66.7757 | 5.1366 | TA504 | 18/0 | Completed
2025-09-21 | 2025-09-21 | 2025-09-29 | Pinki Devi | 65.0226 | 7.2247 | TA504 | 16/3 | Completed
2025-09-21 | 2025-09-03 | 2025-09-22 | Sainik Traders | 59.5006 | 2.975 | TA504 | 11/0 | Completed
2025-09-22 | 2025-09-10 | 2025-09-26 | Ghyansham Mahto | 66.7757 | 3.928 | TA504 | 24/1 | Completed
2025-09-22 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-09-22 | 2025-09-18 | 2025-09-26 | Neha Const | 36.1598 | 4.0178 | TA504 | 29/2 | Completed
2025-09-22 | 2025-09-21 | 2025-09-29 | Pinki Devi | 65.0226 | 7.2247 | TA504 | 16/3 | Completed
2025-09-22 | 2025-09-03 | 2025-09-22 | Sainik Traders | 59.5006 | 2.975 | TA504 | 11/0 | Completed
2025-09-22 | 2025-09-22 | 2025-10-08 | Sainik Traders | 59.5006 | 3.5 | TA504 | 12/0 | Completed
2025-09-23 | 2025-09-10 | 2025-09-26 | Ghyansham Mahto | 66.7757 | 3.928 | TA504 | 24/1 | Completed
2025-09-23 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-09-23 | 2025-09-18 | 2025-09-26 | Neha Const | 36.1598 | 4.0178 | TA504 | 29/2 | Completed
2025-09-23 | 2025-09-21 | 2025-09-29 | Pinki Devi | 65.0226 | 7.2247 | TA504 | 16/3 | Completed
2025-09-23 | 2025-09-22 | 2025-10-08 | Sainik Traders | 59.5006 | 3.5 | TA504 | 12/0 | Completed
2025-09-24 | 2025-09-10 | 2025-09-26 | Ghyansham Mahto | 66.7757 | 3.928 | TA504 | 24/1 | Completed
2025-09-24 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-09-24 | 2025-09-18 | 2025-09-26 | Neha Const | 36.1598 | 4.0178 | TA504 | 29/2 | Completed
2025-09-24 | 2025-09-21 | 2025-09-29 | Pinki Devi | 65.0226 | 7.2247 | TA504 | 16/3 | Completed
2025-09-24 | 2025-09-22 | 2025-10-08 | Sainik Traders | 59.5006 | 3.5 | TA504 | 12/0 | Completed
2025-09-25 | 2025-09-10 | 2025-09-26 | Ghyansham Mahto | 66.7757 | 3.928 | TA504 | 24/1 | Completed
2025-09-25 | 2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-09-25 | 2025-09-18 | 2025-09-26 | Neha Const | 36.1598 | 4.0178 | TA504 | 29/2 | Completed
2025-09-25 | 2025-09-21 | 2025-09-29 | Pinki Devi | 65.0226 | 7.2247 | TA504 | 16/3 | Completed
2025-09-25 | 2025-09-22 | 2025-10-08 | Sainik Traders | 59.5006 | 3.5 | TA504 | 12/0 | Completed
2025-09-26 | 2025-09-10 | 2025-09-26 | Ghyansham Mahto | 66.7757 | 3.928 | TA504 | 24/1 | Completed
2025-09-26 | 2025-09-26 | 2025-10-09 | Karam Mahto | 37.9311 | 2.7094 | TA504 | 30/4 | Completed
2025-09-26 | 2025-09-18 | 2025-09-26 | Neha Const | 36.1598 | 4.0178 | TA504 | 29/2 | Completed
2025-09-26 | 2025-09-21 | 2025-09-29 | Pinki Devi | 65.0226 | 7.2247 | TA504 | 16/3 | Completed
2025-09-26 | 2025-09-22 | 2025-10-08 | Sainik Traders | 59.5006 | 3.5 | TA504 | 12/0 | Completed
2025-09-27 | 2025-09-27 | 2025-10-16 | Ghyansham Mahto | 59.5006 | 2.975 | TA504 | 24/0 | Completed
2025-09-27 | 2025-09-26 | 2025-10-09 | Karam Mahto | 37.9311 | 2.7094 | TA504 | 30/4 | Completed
2025-09-27 | 2025-09-21 | 2025-09-29 | Pinki Devi | 65.0226 | 7.2247 | TA504 | 16/3 | Completed
2025-09-27 | 2025-09-22 | 2025-10-08 | Sainik Traders | 59.5006 | 3.5 | TA504 | 12/0 | Completed
2025-09-28 | 2025-09-27 | 2025-10-16 | Ghyansham Mahto | 59.5006 | 2.975 | TA504 | 24/0 | Completed
2025-09-28 | 2025-09-26 | 2025-10-09 | Karam Mahto | 37.9311 | 2.7094 | TA504 | 30/4 | Completed
2025-09-28 | 2025-09-21 | 2025-09-29 | Pinki Devi | 65.0226 | 7.2247 | TA504 | 16/3 | Completed
2025-09-28 | 2025-09-22 | 2025-10-08 | Sainik Traders | 59.5006 | 3.5 | TA504 | 12/0 | Completed
2025-09-29 | 2025-09-27 | 2025-10-16 | Ghyansham Mahto | 59.5006 | 2.975 | TA504 | 24/0 | Completed
2025-09-29 | 2025-09-26 | 2025-10-09 | Karam Mahto | 37.9311 | 2.7094 | TA504 | 30/4 | Completed
2025-09-29 | 2025-09-21 | 2025-09-29 | Pinki Devi | 65.0226 | 7.2247 | TA504 | 16/3 | Completed
2025-09-29 | 2025-09-22 | 2025-10-08 | Sainik Traders | 59.5006 | 3.5 | TA504 | 12/0 | Completed
2025-09-30 | 2025-09-27 | 2025-10-16 | Ghyansham Mahto | 59.5006 | 2.975 | TA504 | 24/0 | Completed
2025-09-30 | 2025-09-26 | 2025-10-09 | Karam Mahto | 37.9311 | 2.7094 | TA504 | 30/4 | Completed
2025-09-30 | 2025-09-30 | 2025-10-09 | Pinki Devi | 69.376 | 6.9376 | TA504 | 21/0 | Completed
2025-09-30 | 2025-09-22 | 2025-10-08 | Sainik Traders | 59.5006 | 3.5 | TA504 | 12/0 | Completed
2025-10-01 | 2025-09-27 | 2025-10-16 | Ghyansham Mahto | 59.5006 | 2.975 | TA504 | 24/0 | Completed
2025-10-01 | 2025-09-26 | 2025-10-09 | Karam Mahto | 37.9311 | 2.7094 | TA504 | 30/4 | Completed
2025-10-01 | 2025-09-30 | 2025-10-09 | Pinki Devi | 69.376 | 6.9376 | TA504 | 21/0 | Completed
2025-10-01 | 2025-09-22 | 2025-10-08 | Sainik Traders | 59.5006 | 3.5 | TA504 | 12/0 | Completed
2025-10-02 | 2025-09-27 | 2025-10-16 | Ghyansham Mahto | 59.5006 | 2.975 | TA504 | 24/0 | Completed
2025-10-02 | 2025-09-26 | 2025-10-09 | Karam Mahto | 37.9311 | 2.7094 | TA504 | 30/4 | Completed
2025-10-02 | 2025-09-30 | 2025-10-09 | Pinki Devi | 69.376 | 6.9376 | TA504 | 21/0 | Completed
2025-10-02 | 2025-09-22 | 2025-10-08 | Sainik Traders | 59.5006 | 3.5 | TA504 | 12/0 | Completed
2025-10-03 | 2025-09-27 | 2025-10-16 | Ghyansham Mahto | 59.5006 | 2.975 | TA504 | 24/0 | Completed
2025-10-03 | 2025-09-26 | 2025-10-09 | Karam Mahto | 37.9311 | 2.7094 | TA504 | 30/4 | Completed
2025-10-03 | 2025-09-30 | 2025-10-09 | Pinki Devi | 69.376 | 6.9376 | TA504 | 21/0 | Completed
2025-10-03 | 2025-09-22 | 2025-10-08 | Sainik Traders | 59.5006 | 3.5 | TA504 | 12/0 | Completed
2025-10-04 | 2025-09-27 | 2025-10-16 | Ghyansham Mahto | 59.5006 | 2.975 | TA504 | 24/0 | Completed
2025-10-04 | 2025-09-26 | 2025-10-09 | Karam Mahto | 37.9311 | 2.7094 | TA504 | 30/4 | Completed
2025-10-04 | 2025-09-30 | 2025-10-09 | Pinki Devi | 69.376 | 6.9376 | TA504 | 21/0 | Completed
2025-10-04 | 2025-09-22 | 2025-10-08 | Sainik Traders | 59.5006 | 3.5 | TA504 | 12/0 | Completed
2025-10-05 | 2025-09-27 | 2025-10-16 | Ghyansham Mahto | 59.5006 | 2.975 | TA504 | 24/0 | Completed
2025-10-05 | 2025-09-26 | 2025-10-09 | Karam Mahto | 37.9311 | 2.7094 | TA504 | 30/4 | Completed
2025-10-05 | 2025-09-30 | 2025-10-09 | Pinki Devi | 69.376 | 6.9376 | TA504 | 21/0 | Completed
2025-10-05 | 2025-09-22 | 2025-10-08 | Sainik Traders | 59.5006 | 3.5 | TA504 | 12/0 | Completed
2025-10-06 | 2025-09-27 | 2025-10-16 | Ghyansham Mahto | 59.5006 | 2.975 | TA504 | 24/0 | Completed
2025-10-06 | 2025-09-26 | 2025-10-09 | Karam Mahto | 37.9311 | 2.7094 | TA504 | 30/4 | Completed
2025-10-06 | 2025-09-30 | 2025-10-09 | Pinki Devi | 69.376 | 6.9376 | TA504 | 21/0 | Completed
2025-10-06 | 2025-09-22 | 2025-10-08 | Sainik Traders | 59.5006 | 3.5 | TA504 | 12/0 | Completed
2025-10-07 | 2025-09-27 | 2025-10-16 | Ghyansham Mahto | 59.5006 | 2.975 | TA504 | 24/0 | Completed
2025-10-07 | 2025-09-26 | 2025-10-09 | Karam Mahto | 37.9311 | 2.7094 | TA504 | 30/4 | Completed
2025-10-07 | 2025-09-30 | 2025-10-09 | Pinki Devi | 69.376 | 6.9376 | TA504 | 21/0 | Completed
2025-10-07 | 2025-09-22 | 2025-10-08 | Sainik Traders | 59.5006 | 3.5 | TA504 | 12/0 | Completed
2025-10-08 | 2025-09-27 | 2025-10-16 | Ghyansham Mahto | 59.5006 | 2.975 | TA504 | 24/0 | Completed
2025-10-08 | 2025-09-26 | 2025-10-09 | Karam Mahto | 37.9311 | 2.7094 | TA504 | 30/4 | Completed
2025-10-08 | 2025-09-30 | 2025-10-09 | Pinki Devi | 69.376 | 6.9376 | TA504 | 21/0 | Completed
2025-10-08 | 2025-09-22 | 2025-10-08 | Sainik Traders | 59.5006 | 3.5 | TA504 | 12/0 | Completed
2025-10-09 | 2025-09-27 | 2025-10-16 | Ghyansham Mahto | 59.5006 | 2.975 | TA504 | 24/0 | Completed
2025-10-09 | 2025-09-26 | 2025-10-09 | Karam Mahto | 37.9311 | 2.7094 | TA504 | 30/4 | Completed
2025-10-09 | 2025-09-30 | 2025-10-09 | Pinki Devi | 69.376 | 6.9376 | TA504 | 21/0 | Completed
2025-10-10 | 2025-09-27 | 2025-10-16 | Ghyansham Mahto | 59.5006 | 2.975 | TA504 | 24/0 | Completed
2025-10-10 | 2025-10-10 | 2025-10-18 | Karam Mahto | 36.1598 | 4.0178 | TA504 | 30/5 | Completed
2025-10-10 | 2025-10-10 | 2025-10-16 | Pinki Devi | 37.9311 | 5.4187 | TA504 | 27/1 | Completed
2025-10-11 | 2025-09-27 | 2025-10-16 | Ghyansham Mahto | 59.5006 | 2.975 | TA504 | 24/0 | Completed
2025-10-11 | 2025-10-10 | 2025-10-18 | Karam Mahto | 36.1598 | 4.0178 | TA504 | 30/5 | Completed
2025-10-11 | 2025-10-10 | 2025-10-16 | Pinki Devi | 37.9311 | 5.4187 | TA504 | 27/1 | Completed
2025-10-12 | 2025-09-27 | 2025-10-16 | Ghyansham Mahto | 59.5006 | 2.975 | TA504 | 24/0 | Completed
2025-10-12 | 2025-10-10 | 2025-10-18 | Karam Mahto | 36.1598 | 4.0178 | TA504 | 30/5 | Completed
2025-10-12 | 2025-10-10 | 2025-10-16 | Pinki Devi | 37.9311 | 5.4187 | TA504 | 27/1 | Completed
2025-10-13 | 2025-09-27 | 2025-10-16 | Ghyansham Mahto | 59.5006 | 2.975 | TA504 | 24/0 | Completed
2025-10-13 | 2025-10-10 | 2025-10-18 | Karam Mahto | 36.1598 | 4.0178 | TA504 | 30/5 | Completed
2025-10-13 | 2025-10-10 | 2025-10-16 | Pinki Devi | 37.9311 | 5.4187 | TA504 | 27/1 | Completed
2025-10-14 | 2025-09-27 | 2025-10-16 | Ghyansham Mahto | 59.5006 | 2.975 | TA504 | 24/0 | Completed
2025-10-14 | 2025-10-10 | 2025-10-18 | Karam Mahto | 36.1598 | 4.0178 | TA504 | 30/5 | Completed
2025-10-14 | 2025-10-10 | 2025-10-16 | Pinki Devi | 37.9311 | 5.4187 | TA504 | 27/1 | Completed
2025-10-15 | 2025-09-27 | 2025-10-16 | Ghyansham Mahto | 59.5006 | 2.975 | TA504 | 24/0 | Completed
2025-10-15 | 2025-10-10 | 2025-10-18 | Karam Mahto | 36.1598 | 4.0178 | TA504 | 30/5 | Completed
2025-10-15 | 2025-10-10 | 2025-10-16 | Pinki Devi | 37.9311 | 5.4187 | TA504 | 27/1 | Completed
2025-10-16 | 2025-09-27 | 2025-10-16 | Ghyansham Mahto | 59.5006 | 2.975 | TA504 | 24/0 | Completed
2025-10-16 | 2025-10-10 | 2025-10-18 | Karam Mahto | 36.1598 | 4.0178 | TA504 | 30/5 | Completed
2025-10-16 | 2025-10-10 | 2025-10-16 | Pinki Devi | 37.9311 | 5.4187 | TA504 | 27/1 | Completed
2025-10-17 | 2025-10-10 | 2025-10-18 | Karam Mahto | 36.1598 | 4.0178 | TA504 | 30/5 | Completed
2025-10-17 | 2025-10-17 | 2025-10-24 | Pinki Devi | 34.7898 | 4.3487 | TA504 | 26/4 | Completed
2025-10-18 | 2025-10-18 | 2025-11-02 | Ghyansham Mahto | 73.2445 | 4.5778 | TA504 | 22/0 | Completed
2025-10-18 | 2025-10-10 | 2025-10-18 | Karam Mahto | 36.1598 | 4.0178 | TA504 | 30/5 | Completed
2025-10-18 | 2025-10-17 | 2025-10-24 | Pinki Devi | 34.7898 | 4.3487 | TA504 | 26/4 | Completed
2025-10-19 | 2025-10-18 | 2025-11-02 | Ghyansham Mahto | 73.2445 | 4.5778 | TA504 | 22/0 | Completed
2025-10-19 | 2025-10-19 | 2025-11-02 | Karam Mahto | 45.697 | 3.0465 | TA504 | 30/1 | Completed
2025-10-19 | 2025-10-17 | 2025-10-24 | Pinki Devi | 34.7898 | 4.3487 | TA504 | 26/4 | Completed
2025-10-20 | 2025-10-18 | 2025-11-02 | Ghyansham Mahto | 73.2445 | 4.5778 | TA504 | 22/0 | Completed
2025-10-20 | 2025-10-19 | 2025-11-02 | Karam Mahto | 45.697 | 3.0465 | TA504 | 30/1 | Completed
2025-10-20 | 2025-10-17 | 2025-10-24 | Pinki Devi | 34.7898 | 4.3487 | TA504 | 26/4 | Completed
2025-10-21 | 2025-10-18 | 2025-11-02 | Ghyansham Mahto | 73.2445 | 4.5778 | TA504 | 22/0 | Completed
2025-10-21 | 2025-10-19 | 2025-11-02 | Karam Mahto | 45.697 | 3.0465 | TA504 | 30/1 | Completed
2025-10-21 | 2025-10-17 | 2025-10-24 | Pinki Devi | 34.7898 | 4.3487 | TA504 | 26/4 | Completed
2025-10-22 | 2025-10-18 | 2025-11-02 | Ghyansham Mahto | 73.2445 | 4.5778 | TA504 | 22/0 | Completed
2025-10-22 | 2025-10-19 | 2025-11-02 | Karam Mahto | 45.697 | 3.0465 | TA504 | 30/1 | Completed
2025-10-22 | 2025-10-17 | 2025-10-24 | Pinki Devi | 34.7898 | 4.3487 | TA504 | 26/4 | Completed
2025-10-23 | 2025-10-18 | 2025-11-02 | Ghyansham Mahto | 73.2445 | 4.5778 | TA504 | 22/0 | Completed
2025-10-23 | 2025-10-19 | 2025-11-02 | Karam Mahto | 45.697 | 3.0465 | TA504 | 30/1 | Completed
2025-10-23 | 2025-10-17 | 2025-10-24 | Pinki Devi | 34.7898 | 4.3487 | TA504 | 26/4 | Completed
2025-10-24 | 2025-10-18 | 2025-11-02 | Ghyansham Mahto | 73.2445 | 4.5778 | TA504 | 22/0 | Completed
2025-10-24 | 2025-10-19 | 2025-11-02 | Karam Mahto | 45.697 | 3.0465 | TA504 | 30/1 | Completed
2025-10-24 | 2025-10-17 | 2025-10-24 | Pinki Devi | 34.7898 | 4.3487 | TA504 | 26/4 | Completed
2025-10-25 | 2025-10-18 | 2025-11-02 | Ghyansham Mahto | 73.2445 | 4.5778 | TA504 | 22/0 | Completed
2025-10-25 | 2025-10-19 | 2025-11-02 | Karam Mahto | 45.697 | 3.0465 | TA504 | 30/1 | Completed
2025-10-26 | 2025-10-18 | 2025-11-02 | Ghyansham Mahto | 73.2445 | 4.5778 | TA504 | 22/0 | Completed
2025-10-26 | 2025-10-19 | 2025-11-02 | Karam Mahto | 45.697 | 3.0465 | TA504 | 30/1 | Completed
2025-10-27 | 2025-10-18 | 2025-11-02 | Ghyansham Mahto | 73.2445 | 4.5778 | TA504 | 22/0 | Completed
2025-10-27 | 2025-10-19 | 2025-11-02 | Karam Mahto | 45.697 | 3.0465 | TA504 | 30/1 | Completed
2025-10-28 | 2025-10-18 | 2025-11-02 | Ghyansham Mahto | 73.2445 | 4.5778 | TA504 | 22/0 | Completed
2025-10-28 | 2025-10-19 | 2025-11-02 | Karam Mahto | 45.697 | 3.0465 | TA504 | 30/1 | Completed
2025-10-29 | 2025-10-18 | 2025-11-02 | Ghyansham Mahto | 73.2445 | 4.5778 | TA504 | 22/0 | Completed
2025-10-29 | 2025-10-19 | 2025-11-02 | Karam Mahto | 45.697 | 3.0465 | TA504 | 30/1 | Completed
2025-10-30 | 2025-10-18 | 2025-11-02 | Ghyansham Mahto | 73.2445 | 4.5778 | TA504 | 22/0 | Completed
2025-10-30 | 2025-10-19 | 2025-11-02 | Karam Mahto | 45.697 | 3.0465 | TA504 | 30/1 | Completed
2025-10-31 | 2025-10-18 | 2025-11-02 | Ghyansham Mahto | 73.2445 | 4.5778 | TA504 | 22/0 | Completed
2025-10-31 | 2025-10-19 | 2025-11-02 | Karam Mahto | 45.697 | 3.0465 | TA504 | 30/1 | Completed
2025-11-01 | 2025-10-18 | 2025-11-02 | Ghyansham Mahto | 73.2445 | 4.5778 | TA504 | 22/0 | Completed
2025-11-01 | 2025-10-19 | 2025-11-02 | Karam Mahto | 45.697 | 3.0465 | TA504 | 30/1 | Completed
2025-11-02 | 2025-10-18 | 2025-11-02 | Ghyansham Mahto | 73.2445 | 4.5778 | TA504 | 22/0 | Completed
2025-11-02 | 2025-10-19 | 2025-11-02 | Karam Mahto | 45.697 | 3.0465 | TA504 | 30/1 | Completed
2025-11-03 | 2025-11-03 | 2025-11-17 | Ghyansham Mahto | 73.2446 | 4.883 | TA504 | 19/0 | Completed
2025-11-03 | 2025-11-03 | 2025-11-17 | Sainik Traders | 59.5006 | 3.9667 | TA504 | 13/0 | Completed
2025-11-04 | 2025-11-03 | 2025-11-17 | Ghyansham Mahto | 73.2446 | 4.883 | TA504 | 19/0 | Completed
2025-11-04 | 2025-11-04 | 2025-11-11 | Karam Mahto | 36.1598 | 4.52 | TA504 | 26/10 | Completed
2025-11-04 | 2025-11-03 | 2025-11-17 | Sainik Traders | 59.5006 | 3.9667 | TA504 | 13/0 | Completed
2025-11-05 | 2025-11-03 | 2025-11-17 | Ghyansham Mahto | 73.2446 | 4.883 | TA504 | 19/0 | Completed
2025-11-05 | 2025-11-04 | 2025-11-11 | Karam Mahto | 36.1598 | 4.52 | TA504 | 26/10 | Completed
2025-11-05 | 2025-11-03 | 2025-11-17 | Sainik Traders | 59.5006 | 3.9667 | TA504 | 13/0 | Completed
2025-11-06 | 2025-11-03 | 2025-11-17 | Ghyansham Mahto | 73.2446 | 4.883 | TA504 | 19/0 | Completed
2025-11-06 | 2025-11-04 | 2025-11-11 | Karam Mahto | 36.1598 | 4.52 | TA504 | 26/10 | Completed
2025-11-06 | 2025-11-03 | 2025-11-17 | Sainik Traders | 59.5006 | 3.9667 | TA504 | 13/0 | Completed
2025-11-07 | 2025-11-03 | 2025-11-17 | Ghyansham Mahto | 73.2446 | 4.883 | TA504 | 19/0 | Completed
2025-11-07 | 2025-11-04 | 2025-11-11 | Karam Mahto | 36.1598 | 4.52 | TA504 | 26/10 | Completed
2025-11-07 | 2025-11-03 | 2025-11-17 | Sainik Traders | 59.5006 | 3.9667 | TA504 | 13/0 | Completed
2025-11-08 | 2025-11-03 | 2025-11-17 | Ghyansham Mahto | 73.2446 | 4.883 | TA504 | 19/0 | Completed
2025-11-08 | 2025-11-04 | 2025-11-11 | Karam Mahto | 36.1598 | 4.52 | TA504 | 26/10 | Completed
2025-11-08 | 2025-11-03 | 2025-11-17 | Sainik Traders | 59.5006 | 3.9667 | TA504 | 13/0 | Completed
2025-11-09 | 2025-11-03 | 2025-11-17 | Ghyansham Mahto | 73.2446 | 4.883 | TA504 | 19/0 | Completed
2025-11-09 | 2025-11-04 | 2025-11-11 | Karam Mahto | 36.1598 | 4.52 | TA504 | 26/10 | Completed
2025-11-09 | 2025-11-03 | 2025-11-17 | Sainik Traders | 59.5006 | 3.9667 | TA504 | 13/0 | Completed
2025-11-10 | 2025-11-03 | 2025-11-17 | Ghyansham Mahto | 73.2446 | 4.883 | TA504 | 19/0 | Completed
2025-11-10 | 2025-11-04 | 2025-11-11 | Karam Mahto | 36.1598 | 4.52 | TA504 | 26/10 | Completed
2025-11-10 | 2025-11-03 | 2025-11-17 | Sainik Traders | 59.5006 | 3.9667 | TA504 | 13/0 | Completed
2025-11-11 | 2025-11-03 | 2025-11-17 | Ghyansham Mahto | 73.2446 | 4.883 | TA504 | 19/0 | Completed
2025-11-11 | 2025-11-04 | 2025-11-11 | Karam Mahto | 36.1598 | 4.52 | TA504 | 26/10 | Completed
2025-11-11 | 2025-11-03 | 2025-11-17 | Sainik Traders | 59.5006 | 3.9667 | TA504 | 13/0 | Completed
2025-11-12 | 2025-11-03 | 2025-11-17 | Ghyansham Mahto | 73.2446 | 4.883 | TA504 | 19/0 | Completed
2025-11-12 | 2025-11-03 | 2025-11-17 | Sainik Traders | 59.5006 | 3.9667 | TA504 | 13/0 | Completed
2025-11-13 | 2025-11-03 | 2025-11-17 | Ghyansham Mahto | 73.2446 | 4.883 | TA504 | 19/0 | Completed
2025-11-13 | 2025-11-03 | 2025-11-17 | Sainik Traders | 59.5006 | 3.9667 | TA504 | 13/0 | Completed
2025-11-14 | 2025-11-03 | 2025-11-17 | Ghyansham Mahto | 73.2446 | 4.883 | TA504 | 19/0 | Completed
2025-11-14 | 2025-11-03 | 2025-11-17 | Sainik Traders | 59.5006 | 3.9667 | TA504 | 13/0 | Completed
2025-11-15 | 2025-11-03 | 2025-11-17 | Ghyansham Mahto | 73.2446 | 4.883 | TA504 | 19/0 | Completed
2025-11-15 | 2025-11-03 | 2025-11-17 | Sainik Traders | 59.5006 | 3.9667 | TA504 | 13/0 | Completed
2025-11-16 | 2025-11-03 | 2025-11-17 | Ghyansham Mahto | 73.2446 | 4.883 | TA504 | 19/0 | Completed
2025-11-16 | 2025-11-03 | 2025-11-17 | Sainik Traders | 59.5006 | 3.9667 | TA504 | 13/0 | Completed
2025-11-17 | 2025-11-03 | 2025-11-17 | Ghyansham Mahto | 73.2446 | 4.883 | TA504 | 19/0 | Completed
2025-11-17 | 2025-11-03 | 2025-11-17 | Sainik Traders | 59.5006 | 3.9667 | TA504 | 13/0 | Completed
2025-01-14 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-15 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-16 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-17 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-18 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-19 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-21 | 2025-01-21 | 2025-01-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/1 | Completed
2025-01-22 | 2025-01-21 | 2025-01-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/1 | Completed
2025-01-23 | 2025-01-21 | 2025-01-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/1 | Completed
2025-01-24 | 2025-01-21 | 2025-01-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/1 | Completed
2025-01-24 | 2025-01-24 | 2025-01-27 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/3 | Completed
2025-01-25 | 2025-01-24 | 2025-01-27 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/3 | Completed
2025-01-26 | 2025-01-24 | 2025-01-27 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/3 | Completed
2025-01-27 | 2025-01-24 | 2025-01-27 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/3 | Completed
2025-01-27 | 2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-01-28 | 2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-01-29 | 2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-01-30 | 2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-01-31 | 2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-02-01 | 2025-02-01 | 2025-02-04 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 101/5 | Completed
2025-02-02 | 2025-02-01 | 2025-02-04 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 101/5 | Completed
2025-02-03 | 2025-02-01 | 2025-02-04 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 101/5 | Completed
2025-02-04 | 2025-02-01 | 2025-02-04 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 101/5 | Completed
2025-02-05 | 2025-02-05 | 2025-02-08 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/6 | Completed
2025-02-06 | 2025-02-05 | 2025-02-08 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/6 | Completed
2025-02-07 | 2025-02-05 | 2025-02-08 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/6 | Completed
2025-02-08 | 2025-02-05 | 2025-02-08 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/6 | Completed
2025-02-09 | 2025-02-09 | 2025-02-12 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/7 | Completed
2025-02-10 | 2025-02-09 | 2025-02-12 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/7 | Completed
2025-02-11 | 2025-02-09 | 2025-02-12 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/7 | Completed
2025-02-12 | 2025-02-09 | 2025-02-12 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/7 | Completed
2025-02-13 | 2025-02-13 | 2025-02-15 | Jwala Singh | 34.7898 | 11.5966 | TA505 | 101/8 | Completed
2025-02-14 | 2025-02-13 | 2025-02-15 | Jwala Singh | 34.7898 | 11.5966 | TA505 | 101/8 | Completed
2025-02-15 | 2025-02-13 | 2025-02-15 | Jwala Singh | 34.7898 | 11.5966 | TA505 | 101/8 | Completed
2025-02-17 | 2025-02-17 | 2025-02-20 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/7 | Completed
2025-02-18 | 2025-02-17 | 2025-02-20 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/7 | Completed
2025-02-19 | 2025-02-17 | 2025-02-20 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/7 | Completed
2025-02-20 | 2025-02-17 | 2025-02-20 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/7 | Completed
2025-02-21 | 2025-02-21 | 2025-02-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/5 | Completed
2025-02-22 | 2025-02-21 | 2025-02-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/5 | Completed
2025-02-23 | 2025-02-21 | 2025-02-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/5 | Completed
2025-02-24 | 2025-02-21 | 2025-02-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/5 | Completed
2025-02-25 | 2025-02-25 | 2025-02-28 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/2 | Completed
2025-02-26 | 2025-02-25 | 2025-02-28 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/2 | Completed
2025-02-27 | 2025-02-25 | 2025-02-28 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/2 | Completed
2025-02-28 | 2025-02-25 | 2025-02-28 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/2 | Completed
2025-03-01 | 2025-03-01 | 2025-03-04 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/1 | Completed
2025-03-02 | 2025-03-01 | 2025-03-04 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/1 | Completed
2025-03-03 | 2025-03-01 | 2025-03-04 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/1 | Completed
2025-03-04 | 2025-03-01 | 2025-03-04 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/1 | Completed
2025-03-05 | 2025-03-05 | 2025-03-07 | Jwala Singh | 35.602 | 11.8673 | TA505 | 110/1 | Completed
2025-03-06 | 2025-03-05 | 2025-03-07 | Jwala Singh | 35.602 | 11.8673 | TA505 | 110/1 | Completed
2025-03-06 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-07 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-07 | 2025-03-05 | 2025-03-07 | Jwala Singh | 35.602 | 11.8673 | TA505 | 110/1 | Completed
2025-03-07 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-08 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-08 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-09 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-09 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-10 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-10 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-11 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-11 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-11 | 2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-12 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-12 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-12 | 2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-13 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-13 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-13 | 2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-14 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-14 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-14 | 2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-15 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-15 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-15 | 2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-15 | 2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-16 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-16 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-16 | 2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-17 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-17 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-17 | 2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-18 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-18 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-18 | 2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-19 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-19 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-19 | 2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-19 | 2025-03-19 | 2025-03-22 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 110/2 | Completed
2025-03-20 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-20 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-20 | 2025-03-19 | 2025-03-22 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 110/2 | Completed
2025-03-21 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-21 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-21 | 2025-03-19 | 2025-03-22 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 110/2 | Completed
2025-03-22 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-22 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-22 | 2025-03-19 | 2025-03-22 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 110/2 | Completed
2025-03-22 | 2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-23 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-23 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-23 | 2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-24 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-24 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-24 | 2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-25 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-25 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-25 | 2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-26 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-26 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-26 | 2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-26 | 2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-27 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-27 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-27 | 2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-28 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-28 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-28 | 2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-29 | 2025-03-29 | 2025-03-31 | Eagle Enterprises | 43.8044 | 14.6015 | TA505 | 113/5 | Completed
2025-03-29 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-29 | 2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-30 | 2025-03-29 | 2025-03-31 | Eagle Enterprises | 43.8044 | 14.6015 | TA505 | 113/5 | Completed
2025-03-30 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-03-30 | 2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-30 | 2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-03-30 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-03-31 | 2025-03-29 | 2025-03-31 | Eagle Enterprises | 43.8044 | 14.6015 | TA505 | 113/5 | Completed
2025-03-31 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-03-31 | 2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-03-31 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-01 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-01 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-01 | 2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-04-01 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-02 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-02 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-02 | 2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-04-02 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-03 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-03 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-03 | 2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-04-03 | 2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-03 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-04 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-04 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-04 | 2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-04 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-05 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-05 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-05 | 2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-05 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-06 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-06 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-06 | 2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-06 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-06 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-07 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-07 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-07 | 2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-07 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-08 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-08 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-08 | 2025-04-08 | 2025-04-11 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/3 | Completed
2025-04-08 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-09 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-09 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-09 | 2025-04-08 | 2025-04-11 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/3 | Completed
2025-04-09 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-10 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-10 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-10 | 2025-04-08 | 2025-04-11 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/3 | Completed
2025-04-10 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-11 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-11 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-11 | 2025-04-08 | 2025-04-11 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/3 | Completed
2025-04-11 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-12 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-12 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-12 | 2025-04-12 | 2025-04-15 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 108/2 | Completed
2025-04-12 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-12 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-13 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-13 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-13 | 2025-04-12 | 2025-04-15 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 108/2 | Completed
2025-04-13 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-14 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-14 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-14 | 2025-04-12 | 2025-04-15 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 108/2 | Completed
2025-04-14 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-15 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-15 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-15 | 2025-04-12 | 2025-04-15 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 108/2 | Completed
2025-04-15 | 2025-04-15 | 2025-04-18 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/1 | Completed
2025-04-15 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-16 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-16 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-16 | 2025-04-15 | 2025-04-18 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/1 | Completed
2025-04-16 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-17 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-17 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-17 | 2025-04-15 | 2025-04-18 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/1 | Completed
2025-04-17 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-18 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-18 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-18 | 2025-04-15 | 2025-04-18 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/1 | Completed
2025-04-18 | 2025-04-18 | 2025-04-21 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/1 | Completed
2025-04-18 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-18 | 2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-19 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-19 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-19 | 2025-04-18 | 2025-04-21 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/1 | Completed
2025-04-19 | 2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-20 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-20 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-20 | 2025-04-18 | 2025-04-21 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/1 | Completed
2025-04-20 | 2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-21 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-21 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-21 | 2025-04-18 | 2025-04-21 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/1 | Completed
2025-04-21 | 2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-22 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-22 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-22 | 2025-04-22 | 2025-04-25 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/2 | Completed
2025-04-22 | 2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-22 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-22 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-23 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-23 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-23 | 2025-04-22 | 2025-04-25 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/2 | Completed
2025-04-23 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-23 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-24 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-24 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-24 | 2025-04-22 | 2025-04-25 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/2 | Completed
2025-04-24 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-24 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-25 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-25 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-25 | 2025-04-22 | 2025-04-25 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/2 | Completed
2025-04-25 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-25 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-26 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-26 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-26 | 2025-04-26 | 2025-04-29 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 105/1 | Completed
2025-04-26 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-26 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-27 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-27 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-27 | 2025-04-26 | 2025-04-29 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 105/1 | Completed
2025-04-27 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-27 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-04-27 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-28 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-28 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-28 | 2025-04-26 | 2025-04-29 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 105/1 | Completed
2025-04-28 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-04-28 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-29 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-29 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-29 | 2025-04-26 | 2025-04-29 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 105/1 | Completed
2025-04-29 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-04-29 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-30 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-30 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-30 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-04-30 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-04-30 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-05-01 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-05-01 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-01 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-05-01 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-05-02 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-05-02 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-02 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-02 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-02 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-05-02 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-02 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-05-03 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-03 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-03 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-03 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-03 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-05-04 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-04 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-04 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-04 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-04 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-05-05 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-05 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-05 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-05 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-05 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-05-06 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-06 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-06 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-06 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-06 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-06 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-05-07 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-07 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-07 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-07 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-07 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-05-08 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-08 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-08 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-08 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-08 | 2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-08 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-05-08 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-08 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-09 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-09 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-09 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-09 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-09 | 2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-09 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-09 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-10 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-10 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-10 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-10 | 2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-10 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-10 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-11 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-11 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-11 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-11 | 2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-11 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-11 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-12 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-12 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-12 | 2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-12 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-12 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-13 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-13 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-13 | 2025-05-13 | 2025-05-16 | Jwala Singh 2 | 36.1598 | 9.0399 | TA505 | 127/1 | Completed
2025-05-13 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-13 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-14 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-14 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-14 | 2025-05-14 | 2025-05-16 | Jwala Singh | 37.9311 | 12.6437 | TA505 | 152A/3 | Completed
2025-05-14 | 2025-05-13 | 2025-05-16 | Jwala Singh 2 | 36.1598 | 9.0399 | TA505 | 127/1 | Completed
2025-05-14 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-14 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-15 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-15 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-15 | 2025-05-14 | 2025-05-16 | Jwala Singh | 37.9311 | 12.6437 | TA505 | 152A/3 | Completed
2025-05-15 | 2025-05-13 | 2025-05-16 | Jwala Singh 2 | 36.1598 | 9.0399 | TA505 | 127/1 | Completed
2025-05-15 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-15 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-16 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-16 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-16 | 2025-05-14 | 2025-05-16 | Jwala Singh | 37.9311 | 12.6437 | TA505 | 152A/3 | Completed
2025-05-16 | 2025-05-13 | 2025-05-16 | Jwala Singh 2 | 36.1598 | 9.0399 | TA505 | 127/1 | Completed
2025-05-16 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-16 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-17 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-17 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-17 | 2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-17 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-17 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-17 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-18 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-18 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-18 | 2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-18 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-18 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-18 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-19 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-19 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-19 | 2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-19 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-19 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-19 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-20 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-20 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-20 | 2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-20 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-20 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-20 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-21 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-21 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-21 | 2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-21 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-21 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-21 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-22 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-22 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-22 | 2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-22 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-22 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-22 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-23 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-23 | 2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-23 | 2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-23 | 2025-05-23 | 2025-05-26 | Jwala Singh 2 | 34.79 | 8.6975 | TA505 | 126/2 | Completed
2025-05-23 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-23 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-24 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-24 | 2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-24 | 2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-24 | 2025-05-23 | 2025-05-26 | Jwala Singh 2 | 34.79 | 8.6975 | TA505 | 126/2 | Completed
2025-05-24 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-24 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-25 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-25 | 2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-25 | 2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-25 | 2025-05-23 | 2025-05-26 | Jwala Singh 2 | 34.79 | 8.6975 | TA505 | 126/2 | Completed
2025-05-25 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-25 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-26 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-26 | 2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-26 | 2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-26 | 2025-05-23 | 2025-05-26 | Jwala Singh 2 | 34.79 | 8.6975 | TA505 | 126/2 | Completed
2025-05-26 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-26 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-27 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-27 | 2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-27 | 2025-05-27 | 2025-05-30 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 152A/4 | Completed
2025-05-27 | 2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-27 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-27 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-28 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-28 | 2025-05-28 | 2025-05-31 | Gokul Rajwanshi | 37.9311 | 9.4828 | TA505 | 155/5 | Completed
2025-05-28 | 2025-05-27 | 2025-05-30 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 152A/4 | Completed
2025-05-28 | 2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-28 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-28 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-05-29 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-29 | 2025-05-28 | 2025-05-31 | Gokul Rajwanshi | 37.9311 | 9.4828 | TA505 | 155/5 | Completed
2025-05-29 | 2025-05-27 | 2025-05-30 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 152A/4 | Completed
2025-05-29 | 2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-29 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-29 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-05-30 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-30 | 2025-05-28 | 2025-05-31 | Gokul Rajwanshi | 37.9311 | 9.4828 | TA505 | 155/5 | Completed
2025-05-30 | 2025-05-27 | 2025-05-30 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 152A/4 | Completed
2025-05-30 | 2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-30 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-30 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-05-31 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-31 | 2025-05-28 | 2025-05-31 | Gokul Rajwanshi | 37.9311 | 9.4828 | TA505 | 155/5 | Completed
2025-05-31 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-05-31 | 2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-31 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-31 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-01 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-01 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-01 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-01 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-01 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-01 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-02 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-02 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-02 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-02 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-02 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-02 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-03 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-03 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-03 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-03 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-03 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-03 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-04 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-04 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-04 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-04 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-04 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-04 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-05 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-05 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-05 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-05 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-05 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-05 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-06 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-06 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-06 | 2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-06 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-06 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-06 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-07 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-07 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-07 | 2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-07 | 2025-06-07 | 2025-06-10 | Jwala Singh 2 | 43.8044 | 10.9511 | TA505 | 147A/2 | Completed
2025-06-07 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-07 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-08 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-08 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-08 | 2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-08 | 2025-06-07 | 2025-06-10 | Jwala Singh 2 | 43.8044 | 10.9511 | TA505 | 147A/2 | Completed
2025-06-08 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-08 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-09 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-09 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-09 | 2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-09 | 2025-06-07 | 2025-06-10 | Jwala Singh 2 | 43.8044 | 10.9511 | TA505 | 147A/2 | Completed
2025-06-09 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-09 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-10 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-10 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-10 | 2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-10 | 2025-06-07 | 2025-06-10 | Jwala Singh 2 | 43.8044 | 10.9511 | TA505 | 147A/2 | Completed
2025-06-10 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-10 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-11 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-11 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-11 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-11 | 2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-11 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-11 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-12 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-12 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-12 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-12 | 2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-12 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-12 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-13 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-13 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-13 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-13 | 2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-13 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-13 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-14 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-14 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-14 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-14 | 2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-14 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-14 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-15 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-15 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-15 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-15 | 2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-15 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-15 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-16 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-16 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-16 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-16 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-16 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-17 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-17 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-17 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-17 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-17 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-18 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-18 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-18 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-18 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-18 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-19 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-19 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-19 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-19 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-19 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-20 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-20 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-20 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-20 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-20 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-21 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-21 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-21 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-21 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-21 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-22 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-22 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-22 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-22 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-22 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-23 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-23 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-23 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-23 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-24 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-24 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-24 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-25 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-25 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-25 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-26 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-26 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-26 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-27 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-27 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-27 | 2025-06-27 | 2025-06-30 | Jwala Singh | 43.8044 | 10.9511 | TA505 | 150/4 | Completed
2025-06-27 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-28 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-28 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-28 | 2025-06-27 | 2025-06-30 | Jwala Singh | 43.8044 | 10.9511 | TA505 | 150/4 | Completed
2025-06-28 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-29 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-29 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-29 | 2025-06-27 | 2025-06-30 | Jwala Singh | 43.8044 | 10.9511 | TA505 | 150/4 | Completed
2025-06-29 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-30 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-30 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-30 | 2025-06-27 | 2025-06-30 | Jwala Singh | 43.8044 | 10.9511 | TA505 | 150/4 | Completed
2025-06-30 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-01 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-01 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-01 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-01 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-02 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-02 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-02 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-02 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-03 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-03 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-03 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-03 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-04 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-04 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-04 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-04 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-05 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-05 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-05 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-05 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-06 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-06 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-06 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-06 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-07 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-07 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-07 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-07 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-08 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-08 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-08 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-08 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-09 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-09 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-09 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-09 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-10 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-10 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-10 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-10 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-11 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-11 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-11 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-11 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-12 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-12 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-12 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-12 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-13 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-13 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-13 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-14 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-14 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-14 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-15 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-15 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-15 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-16 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-16 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-16 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-17 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-17 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-17 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-18 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-18 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-18 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-19 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-19 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-19 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-20 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-20 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-20 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-21 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-21 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-21 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-22 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-22 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-22 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-23 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-23 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-23 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-24 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-24 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-24 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-25 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-25 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-25 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-26 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-26 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-26 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-27 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-27 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-27 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-28 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-28 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-28 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-29 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-29 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-30 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-30 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-31 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-31 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-08-01 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-02 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-03 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-04 | 2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-04 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-04 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-05 | 2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-05 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-05 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-06 | 2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-06 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-06 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-07 | 2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-07 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-07 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-08 | 2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-08 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-08 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-09 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-09 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-09 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-10 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-10 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-10 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-11 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-11 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-11 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-12 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-12 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-12 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-12 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-12 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-13 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-13 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-13 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-13 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-14 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-14 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-14 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-14 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-15 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-15 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-15 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-15 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-16 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-16 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-16 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-16 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-17 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-17 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-17 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-17 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-18 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-18 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-18 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-18 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-18 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-19 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-19 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-19 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-19 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-19 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-20 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-20 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-20 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-20 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-20 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-21 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-21 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-21 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-21 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-21 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-21 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-22 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-22 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-22 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-22 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-22 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-23 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-23 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-23 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-23 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-23 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-24 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-24 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-24 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-24 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-24 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-25 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-25 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-25 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-25 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-25 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-25 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-25 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-25 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-25 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-26 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-26 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-26 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-26 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-26 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-26 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-26 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-26 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-26 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-27 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-27 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-27 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-27 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-27 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-27 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-27 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-27 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-27 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-08-28 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-28 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-28 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-28 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-28 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-28 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-28 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-28 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-28 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-08-29 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-29 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-29 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-29 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-29 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-29 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-29 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-29 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-29 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-08-30 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-30 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-30 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-30 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-30 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-30 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-30 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-30 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-30 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-08-31 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-31 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-31 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-31 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-31 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-31 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-31 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-31 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-01 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-01 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-01 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-01 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-01 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-09-01 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-01 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-01 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-01 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-02 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-02 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-02 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-02 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-02 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-09-02 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-02 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-02 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-02 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-03 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-03 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-03 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-03 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-03 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-09-03 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-03 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-03 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-03 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-04 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-04 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-04 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-04 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-04 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-09-04 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-04 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-04 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-04 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-05 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-05 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-05 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-05 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-05 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-09-05 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-05 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-05 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-05 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-06 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-06 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-06 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-06 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-06 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-06 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-06 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-06 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-07 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-07 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-07 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-07 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-07 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-07 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-07 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-07 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-08 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-08 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-08 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-08 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-08 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-08 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-08 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-08 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-09 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-09 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-09 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-09 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-09 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-09 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-09 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-09 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-10 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-10 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-10 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-10 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-10 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-10 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-10 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-10 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-10 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-10 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-11 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-11 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-11 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-11 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-11 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-11 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-11 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-11 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-11 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-11 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-11 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-12 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-12 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-12 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-12 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-12 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-12 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-12 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-12 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-12 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-12 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-12 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-12 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-13 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-13 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-13 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-13 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-13 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-13 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-13 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-13 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-13 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-13 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-13 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-13 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-14 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-14 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-14 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-14 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-14 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-14 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-14 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-14 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-14 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-14 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-14 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-14 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-14 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-14 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-15 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-15 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-15 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-15 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-15 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-15 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-15 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-15 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-15 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-15 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-15 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-15 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-15 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-15 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-16 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-16 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-16 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-16 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-16 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-16 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-16 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-16 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-16 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-16 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-16 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-16 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-16 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-16 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-17 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-17 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-17 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-17 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-17 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-17 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-17 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-17 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-17 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-17 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-17 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-17 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-17 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-18 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-18 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-18 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-18 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-18 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-18 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-18 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-18 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-18 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-18 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-18 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-18 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-18 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-18 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-19 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-19 | 2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-19 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-19 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-19 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-19 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-19 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-19 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-19 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-19 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-19 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-19 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-19 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-19 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-20 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-20 | 2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-20 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-20 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-20 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-20 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-20 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-20 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-20 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-20 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-20 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-20 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-20 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-20 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-21 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-21 | 2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-21 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-21 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-21 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-21 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-21 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-21 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-21 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-21 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-21 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-21 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-21 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-21 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-22 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-22 | 2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-22 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-22 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-22 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-22 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-22 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-22 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-22 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-22 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-22 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-22 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-22 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-22 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-23 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-23 | 2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-23 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-23 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-23 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-23 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-23 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-23 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-09-23 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-23 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-23 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-23 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-23 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-23 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-24 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-24 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-24 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-24 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-24 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-24 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-24 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-24 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-09-24 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-24 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-24 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-24 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-24 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-24 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-25 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-25 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-25 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-25 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-25 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-25 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-25 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-25 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-09-25 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-25 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-25 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-25 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-25 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-25 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-26 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-26 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-26 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-26 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-26 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-26 | 2025-09-26 | 2025-10-12 | Jagannaath Saw Mp | 55.451 | 3.2618 | TA505 | 160/0 | Completed
2025-09-26 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-26 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-09-26 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-26 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-26 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-09-26 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-09-26 | 2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-09-26 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-27 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-27 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-27 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-27 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-27 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-27 | 2025-09-26 | 2025-10-12 | Jagannaath Saw Mp | 55.451 | 3.2618 | TA505 | 160/0 | Completed
2025-09-27 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-27 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-09-27 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-27 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-27 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-09-27 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-09-27 | 2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-09-27 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-28 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-28 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-28 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-28 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-28 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-28 | 2025-09-26 | 2025-10-12 | Jagannaath Saw Mp | 55.451 | 3.2618 | TA505 | 160/0 | Completed
2025-09-28 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-28 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-09-28 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-28 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-28 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-09-28 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-09-28 | 2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-09-28 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-29 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-29 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-29 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-29 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-29 | 2025-09-26 | 2025-10-12 | Jagannaath Saw Mp | 55.451 | 3.2618 | TA505 | 160/0 | Completed
2025-09-29 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-09-29 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-29 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-09-29 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-09-29 | 2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-09-29 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-30 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-30 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-30 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-09-30 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-30 | 2025-09-26 | 2025-10-12 | Jagannaath Saw Mp | 55.451 | 3.2618 | TA505 | 160/0 | Completed
2025-09-30 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-09-30 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-30 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-09-30 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-09-30 | 2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-09-30 | 2025-09-30 | 2025-10-12 | Toshan Mahato | 36.1598 | 2.7815 | TA505 | 148/1 | Completed
2025-10-01 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-10-01 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-10-01 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-01 | 2025-09-26 | 2025-10-12 | Jagannaath Saw Mp | 55.451 | 3.2618 | TA505 | 160/0 | Completed
2025-10-01 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-10-01 | 2025-10-01 | 2025-10-12 | Jwala Singh | 65.87 | 5.4892 | TA505 | 101/0 | Completed
2025-10-01 | 2025-10-01 | 2025-10-26 | Jyoti Const | 124.95 | 4.8058 | TA505 | 112/0 | Completed
2025-10-01 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-10-01 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-01 | 2025-10-01 | 2025-10-12 | Shila Devi | 81.828 | 6.819 | TA505 | 128/0 | Completed
2025-10-01 | 2025-09-30 | 2025-10-12 | Toshan Mahato | 36.1598 | 2.7815 | TA505 | 148/1 | Completed
2025-10-02 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-10-02 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-10-02 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-02 | 2025-09-26 | 2025-10-12 | Jagannaath Saw Mp | 55.451 | 3.2618 | TA505 | 160/0 | Completed
2025-10-02 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-10-02 | 2025-10-01 | 2025-10-12 | Jwala Singh | 65.87 | 5.4892 | TA505 | 101/0 | Completed
2025-10-02 | 2025-10-01 | 2025-10-26 | Jyoti Const | 124.95 | 4.8058 | TA505 | 112/0 | Completed
2025-10-02 | 2025-10-02 | 2025-10-10 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/2 | Completed
2025-10-02 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-02 | 2025-10-01 | 2025-10-12 | Shila Devi | 81.828 | 6.819 | TA505 | 128/0 | Completed
2025-10-02 | 2025-09-30 | 2025-10-12 | Toshan Mahato | 36.1598 | 2.7815 | TA505 | 148/1 | Completed
2025-10-03 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-10-03 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-10-03 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-03 | 2025-09-26 | 2025-10-12 | Jagannaath Saw Mp | 55.451 | 3.2618 | TA505 | 160/0 | Completed
2025-10-03 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-10-03 | 2025-10-01 | 2025-10-12 | Jwala Singh | 65.87 | 5.4892 | TA505 | 101/0 | Completed
2025-10-03 | 2025-10-01 | 2025-10-26 | Jyoti Const | 124.95 | 4.8058 | TA505 | 112/0 | Completed
2025-10-03 | 2025-10-02 | 2025-10-10 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/2 | Completed
2025-10-03 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-03 | 2025-10-01 | 2025-10-12 | Shila Devi | 81.828 | 6.819 | TA505 | 128/0 | Completed
2025-10-03 | 2025-09-30 | 2025-10-12 | Toshan Mahato | 36.1598 | 2.7815 | TA505 | 148/1 | Completed
2025-10-04 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-10-04 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-10-04 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-04 | 2025-09-26 | 2025-10-12 | Jagannaath Saw Mp | 55.451 | 3.2618 | TA505 | 160/0 | Completed
2025-10-04 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-10-04 | 2025-10-01 | 2025-10-12 | Jwala Singh | 65.87 | 5.4892 | TA505 | 101/0 | Completed
2025-10-04 | 2025-10-01 | 2025-10-26 | Jyoti Const | 124.95 | 4.8058 | TA505 | 112/0 | Completed
2025-10-04 | 2025-10-02 | 2025-10-10 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/2 | Completed
2025-10-04 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-04 | 2025-10-01 | 2025-10-12 | Shila Devi | 81.828 | 6.819 | TA505 | 128/0 | Completed
2025-10-04 | 2025-09-30 | 2025-10-12 | Toshan Mahato | 36.1598 | 2.7815 | TA505 | 148/1 | Completed
2025-10-05 | 2025-10-05 | 2025-10-18 | Anil Kumar | 37.931 | 2.7094 | TA505 | 152A/5 | Completed
2025-10-05 | 2025-10-05 | 2025-10-13 | Deglal Mahato | 77.077 | 8.5641 | TA505 | 116/0 | Completed
2025-10-05 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-05 | 2025-09-26 | 2025-10-12 | Jagannaath Saw Mp | 55.451 | 3.2618 | TA505 | 160/0 | Completed
2025-10-05 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-10-05 | 2025-10-01 | 2025-10-12 | Jwala Singh | 65.87 | 5.4892 | TA505 | 101/0 | Completed
2025-10-05 | 2025-10-01 | 2025-10-26 | Jyoti Const | 124.95 | 4.8058 | TA505 | 112/0 | Completed
2025-10-05 | 2025-10-02 | 2025-10-10 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/2 | Completed
2025-10-05 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-05 | 2025-10-01 | 2025-10-12 | Shila Devi | 81.828 | 6.819 | TA505 | 128/0 | Completed
2025-10-05 | 2025-09-30 | 2025-10-12 | Toshan Mahato | 36.1598 | 2.7815 | TA505 | 148/1 | Completed
2025-10-06 | 2025-10-05 | 2025-10-18 | Anil Kumar | 37.931 | 2.7094 | TA505 | 152A/5 | Completed
2025-10-06 | 2025-10-05 | 2025-10-13 | Deglal Mahato | 77.077 | 8.5641 | TA505 | 116/0 | Completed
2025-10-06 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-06 | 2025-09-26 | 2025-10-12 | Jagannaath Saw Mp | 55.451 | 3.2618 | TA505 | 160/0 | Completed
2025-10-06 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-10-06 | 2025-10-01 | 2025-10-12 | Jwala Singh | 65.87 | 5.4892 | TA505 | 101/0 | Completed
2025-10-06 | 2025-10-01 | 2025-10-26 | Jyoti Const | 124.95 | 4.8058 | TA505 | 112/0 | Completed
2025-10-06 | 2025-10-02 | 2025-10-10 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/2 | Completed
2025-10-06 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-06 | 2025-10-01 | 2025-10-12 | Shila Devi | 81.828 | 6.819 | TA505 | 128/0 | Completed
2025-10-06 | 2025-09-30 | 2025-10-12 | Toshan Mahato | 36.1598 | 2.7815 | TA505 | 148/1 | Completed
2025-10-07 | 2025-10-05 | 2025-10-18 | Anil Kumar | 37.931 | 2.7094 | TA505 | 152A/5 | Completed
2025-10-07 | 2025-10-05 | 2025-10-13 | Deglal Mahato | 77.077 | 8.5641 | TA505 | 116/0 | Completed
2025-10-07 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-07 | 2025-09-26 | 2025-10-12 | Jagannaath Saw Mp | 55.451 | 3.2618 | TA505 | 160/0 | Completed
2025-10-07 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-10-07 | 2025-10-01 | 2025-10-12 | Jwala Singh | 65.87 | 5.4892 | TA505 | 101/0 | Completed
2025-10-07 | 2025-10-01 | 2025-10-26 | Jyoti Const | 124.95 | 4.8058 | TA505 | 112/0 | Completed
2025-10-07 | 2025-10-02 | 2025-10-10 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/2 | Completed
2025-10-07 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-07 | 2025-10-01 | 2025-10-12 | Shila Devi | 81.828 | 6.819 | TA505 | 128/0 | Completed
2025-10-07 | 2025-09-30 | 2025-10-12 | Toshan Mahato | 36.1598 | 2.7815 | TA505 | 148/1 | Completed
2025-10-08 | 2025-10-05 | 2025-10-18 | Anil Kumar | 37.931 | 2.7094 | TA505 | 152A/5 | Completed
2025-10-08 | 2025-10-05 | 2025-10-13 | Deglal Mahato | 77.077 | 8.5641 | TA505 | 116/0 | Completed
2025-10-08 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-08 | 2025-09-26 | 2025-10-12 | Jagannaath Saw Mp | 55.451 | 3.2618 | TA505 | 160/0 | Completed
2025-10-08 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-10-08 | 2025-10-01 | 2025-10-12 | Jwala Singh | 65.87 | 5.4892 | TA505 | 101/0 | Completed
2025-10-08 | 2025-10-01 | 2025-10-26 | Jyoti Const | 124.95 | 4.8058 | TA505 | 112/0 | Completed
2025-10-08 | 2025-10-02 | 2025-10-10 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/2 | Completed
2025-10-08 | 2025-10-08 | 2025-10-16 | Paramanand 1 | 35.602 | 3.9558 | TA505 | 160/1 | Completed
2025-10-08 | 2025-10-01 | 2025-10-12 | Shila Devi | 81.828 | 6.819 | TA505 | 128/0 | Completed
2025-10-08 | 2025-09-30 | 2025-10-12 | Toshan Mahato | 36.1598 | 2.7815 | TA505 | 148/1 | Completed
2025-10-09 | 2025-10-05 | 2025-10-18 | Anil Kumar | 37.931 | 2.7094 | TA505 | 152A/5 | Completed
2025-10-09 | 2025-10-05 | 2025-10-13 | Deglal Mahato | 77.077 | 8.5641 | TA505 | 116/0 | Completed
2025-10-09 | 2025-10-09 | 2025-10-16 | Deglal Mahato Mp | 36.1598 | 4.52 | TA505 | 169/5 | Completed
2025-10-09 | 2025-09-26 | 2025-10-12 | Jagannaath Saw Mp | 55.451 | 3.2618 | TA505 | 160/0 | Completed
2025-10-09 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-10-09 | 2025-10-01 | 2025-10-12 | Jwala Singh | 65.87 | 5.4892 | TA505 | 101/0 | Completed
2025-10-09 | 2025-10-01 | 2025-10-26 | Jyoti Const | 124.95 | 4.8058 | TA505 | 112/0 | Completed
2025-10-09 | 2025-10-02 | 2025-10-10 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/2 | Completed
2025-10-09 | 2025-10-08 | 2025-10-16 | Paramanand 1 | 35.602 | 3.9558 | TA505 | 160/1 | Completed
2025-10-09 | 2025-10-01 | 2025-10-12 | Shila Devi | 81.828 | 6.819 | TA505 | 128/0 | Completed
2025-10-09 | 2025-09-30 | 2025-10-12 | Toshan Mahato | 36.1598 | 2.7815 | TA505 | 148/1 | Completed
2025-10-10 | 2025-10-05 | 2025-10-18 | Anil Kumar | 37.931 | 2.7094 | TA505 | 152A/5 | Completed
2025-10-10 | 2025-10-05 | 2025-10-13 | Deglal Mahato | 77.077 | 8.5641 | TA505 | 116/0 | Completed
2025-10-10 | 2025-10-09 | 2025-10-16 | Deglal Mahato Mp | 36.1598 | 4.52 | TA505 | 169/5 | Completed
2025-10-10 | 2025-09-26 | 2025-10-12 | Jagannaath Saw Mp | 55.451 | 3.2618 | TA505 | 160/0 | Completed
2025-10-10 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-10-10 | 2025-10-10 | 2025-10-18 | Jhemon Mahato 2 | 37.931 | 4.2146 | TA505 | 140/1 | Completed
2025-10-10 | 2025-10-01 | 2025-10-12 | Jwala Singh | 65.87 | 5.4892 | TA505 | 101/0 | Completed
2025-10-10 | 2025-10-01 | 2025-10-26 | Jyoti Const | 124.95 | 4.8058 | TA505 | 112/0 | Completed
2025-10-10 | 2025-10-02 | 2025-10-10 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/2 | Completed
2025-10-10 | 2025-10-10 | 2025-10-15 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/3 | Completed
2025-10-10 | 2025-10-08 | 2025-10-16 | Paramanand 1 | 35.602 | 3.9558 | TA505 | 160/1 | Completed
2025-10-10 | 2025-10-01 | 2025-10-12 | Shila Devi | 81.828 | 6.819 | TA505 | 128/0 | Completed
2025-10-10 | 2025-09-30 | 2025-10-12 | Toshan Mahato | 36.1598 | 2.7815 | TA505 | 148/1 | Completed
2025-10-11 | 2025-10-05 | 2025-10-18 | Anil Kumar | 37.931 | 2.7094 | TA505 | 152A/5 | Completed
2025-10-11 | 2025-10-05 | 2025-10-13 | Deglal Mahato | 77.077 | 8.5641 | TA505 | 116/0 | Completed
2025-10-11 | 2025-10-09 | 2025-10-16 | Deglal Mahato Mp | 36.1598 | 4.52 | TA505 | 169/5 | Completed
2025-10-11 | 2025-09-26 | 2025-10-12 | Jagannaath Saw Mp | 55.451 | 3.2618 | TA505 | 160/0 | Completed
2025-10-11 | 2025-10-10 | 2025-10-18 | Jhemon Mahato 2 | 37.931 | 4.2146 | TA505 | 140/1 | Completed
2025-10-11 | 2025-10-01 | 2025-10-12 | Jwala Singh | 65.87 | 5.4892 | TA505 | 101/0 | Completed
2025-10-11 | 2025-10-01 | 2025-10-26 | Jyoti Const | 124.95 | 4.8058 | TA505 | 112/0 | Completed
2025-10-11 | 2025-10-10 | 2025-10-15 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/3 | Completed
2025-10-11 | 2025-10-08 | 2025-10-16 | Paramanand 1 | 35.602 | 3.9558 | TA505 | 160/1 | Completed
2025-10-11 | 2025-10-01 | 2025-10-12 | Shila Devi | 81.828 | 6.819 | TA505 | 128/0 | Completed
2025-10-11 | 2025-09-30 | 2025-10-12 | Toshan Mahato | 36.1598 | 2.7815 | TA505 | 148/1 | Completed
2025-10-12 | 2025-10-05 | 2025-10-18 | Anil Kumar | 37.931 | 2.7094 | TA505 | 152A/5 | Completed
2025-10-12 | 2025-10-05 | 2025-10-13 | Deglal Mahato | 77.077 | 8.5641 | TA505 | 116/0 | Completed
2025-10-12 | 2025-10-09 | 2025-10-16 | Deglal Mahato Mp | 36.1598 | 4.52 | TA505 | 169/5 | Completed
2025-10-12 | 2025-09-26 | 2025-10-12 | Jagannaath Saw Mp | 55.451 | 3.2618 | TA505 | 160/0 | Completed
2025-10-12 | 2025-10-10 | 2025-10-18 | Jhemon Mahato 2 | 37.931 | 4.2146 | TA505 | 140/1 | Completed
2025-10-12 | 2025-10-01 | 2025-10-12 | Jwala Singh | 65.87 | 5.4892 | TA505 | 101/0 | Completed
2025-10-12 | 2025-10-01 | 2025-10-26 | Jyoti Const | 124.95 | 4.8058 | TA505 | 112/0 | Completed
2025-10-12 | 2025-10-10 | 2025-10-15 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/3 | Completed
2025-10-12 | 2025-10-08 | 2025-10-16 | Paramanand 1 | 35.602 | 3.9558 | TA505 | 160/1 | Completed
2025-10-12 | 2025-10-01 | 2025-10-12 | Shila Devi | 81.828 | 6.819 | TA505 | 128/0 | Completed
2025-10-12 | 2025-09-30 | 2025-10-12 | Toshan Mahato | 36.1598 | 2.7815 | TA505 | 148/1 | Completed
2025-10-13 | 2025-10-05 | 2025-10-18 | Anil Kumar | 37.931 | 2.7094 | TA505 | 152A/5 | Completed
2025-10-13 | 2025-10-05 | 2025-10-13 | Deglal Mahato | 77.077 | 8.5641 | TA505 | 116/0 | Completed
2025-10-13 | 2025-10-09 | 2025-10-16 | Deglal Mahato Mp | 36.1598 | 4.52 | TA505 | 169/5 | Completed
2025-10-13 | 2025-10-13 | 2025-10-18 | Jagannaath Saw Mp | 36.1598 | 6.0266 | TA505 | 158/2 | Completed
2025-10-13 | 2025-10-10 | 2025-10-18 | Jhemon Mahato 2 | 37.931 | 4.2146 | TA505 | 140/1 | Completed
2025-10-13 | 2025-10-13 | 2025-10-26 | Jwala Singh | 70.74 | 5.0529 | TA505 | 102/0 | Completed
2025-10-13 | 2025-10-01 | 2025-10-26 | Jyoti Const | 124.95 | 4.8058 | TA505 | 112/0 | Completed
2025-10-13 | 2025-10-10 | 2025-10-15 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/3 | Completed
2025-10-13 | 2025-10-08 | 2025-10-16 | Paramanand 1 | 35.602 | 3.9558 | TA505 | 160/1 | Completed
2025-10-13 | 2025-10-13 | 2025-10-24 | Toshan Mahato | 55.451 | 4.6209 | TA505 | 147A/0 | Completed
2025-10-14 | 2025-10-05 | 2025-10-18 | Anil Kumar | 37.931 | 2.7094 | TA505 | 152A/5 | Completed
2025-10-14 | 2025-10-14 | 2025-10-21 | Deglal Mahato | 65.028 | 8.1285 | TA505 | 121/0 | Completed
2025-10-14 | 2025-10-09 | 2025-10-16 | Deglal Mahato Mp | 36.1598 | 4.52 | TA505 | 169/5 | Completed
2025-10-14 | 2025-10-13 | 2025-10-18 | Jagannaath Saw Mp | 36.1598 | 6.0266 | TA505 | 158/2 | Completed
2025-10-14 | 2025-10-10 | 2025-10-18 | Jhemon Mahato 2 | 37.931 | 4.2146 | TA505 | 140/1 | Completed
2025-10-14 | 2025-10-13 | 2025-10-26 | Jwala Singh | 70.74 | 5.0529 | TA505 | 102/0 | Completed
2025-10-14 | 2025-10-01 | 2025-10-26 | Jyoti Const | 124.95 | 4.8058 | TA505 | 112/0 | Completed
2025-10-14 | 2025-10-10 | 2025-10-15 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/3 | Completed
2025-10-14 | 2025-10-08 | 2025-10-16 | Paramanand 1 | 35.602 | 3.9558 | TA505 | 160/1 | Completed
2025-10-14 | 2025-10-13 | 2025-10-24 | Toshan Mahato | 55.451 | 4.6209 | TA505 | 147A/0 | Completed
2025-10-15 | 2025-10-05 | 2025-10-18 | Anil Kumar | 37.931 | 2.7094 | TA505 | 152A/5 | Completed
2025-10-15 | 2025-10-14 | 2025-10-21 | Deglal Mahato | 65.028 | 8.1285 | TA505 | 121/0 | Completed
2025-10-15 | 2025-10-09 | 2025-10-16 | Deglal Mahato Mp | 36.1598 | 4.52 | TA505 | 169/5 | Completed
2025-10-15 | 2025-10-13 | 2025-10-18 | Jagannaath Saw Mp | 36.1598 | 6.0266 | TA505 | 158/2 | Completed
2025-10-15 | 2025-10-10 | 2025-10-18 | Jhemon Mahato 2 | 37.931 | 4.2146 | TA505 | 140/1 | Completed
2025-10-15 | 2025-10-13 | 2025-10-26 | Jwala Singh | 70.74 | 5.0529 | TA505 | 102/0 | Completed
2025-10-15 | 2025-10-01 | 2025-10-26 | Jyoti Const | 124.95 | 4.8058 | TA505 | 112/0 | Completed
2025-10-15 | 2025-10-10 | 2025-10-15 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/3 | Completed
2025-10-15 | 2025-10-08 | 2025-10-16 | Paramanand 1 | 35.602 | 3.9558 | TA505 | 160/1 | Completed
2025-10-15 | 2025-10-13 | 2025-10-24 | Toshan Mahato | 55.451 | 4.6209 | TA505 | 147A/0 | Completed
2025-10-16 | 2025-10-05 | 2025-10-18 | Anil Kumar | 37.931 | 2.7094 | TA505 | 152A/5 | Completed
2025-10-16 | 2025-10-14 | 2025-10-21 | Deglal Mahato | 65.028 | 8.1285 | TA505 | 121/0 | Completed
2025-10-16 | 2025-10-09 | 2025-10-16 | Deglal Mahato Mp | 36.1598 | 4.52 | TA505 | 169/5 | Completed
2025-10-16 | 2025-10-16 | 2025-10-21 | Deglal Mahato Mp | 35.602 | 5.9337 | TA505 | 169/7 | Completed
2025-10-16 | 2025-10-13 | 2025-10-18 | Jagannaath Saw Mp | 36.1598 | 6.0266 | TA505 | 158/2 | Completed
2025-10-16 | 2025-10-10 | 2025-10-18 | Jhemon Mahato 2 | 37.931 | 4.2146 | TA505 | 140/1 | Completed
2025-10-16 | 2025-10-13 | 2025-10-26 | Jwala Singh | 70.74 | 5.0529 | TA505 | 102/0 | Completed
2025-10-16 | 2025-10-01 | 2025-10-26 | Jyoti Const | 124.95 | 4.8058 | TA505 | 112/0 | Completed
2025-10-16 | 2025-10-16 | 2025-10-25 | Pankaj Singh Mp | 55.451 | 5.5451 | TA505 | 167/0 | Completed
2025-10-16 | 2025-10-08 | 2025-10-16 | Paramanand 1 | 35.602 | 3.9558 | TA505 | 160/1 | Completed
2025-10-16 | 2025-10-16 | 2025-11-08 | Paramanand 1 | 62.116 | 2.5882 | TA505 | 161/0 | Completed
2025-10-16 | 2025-10-13 | 2025-10-24 | Toshan Mahato | 55.451 | 4.6209 | TA505 | 147A/0 | Completed
2025-10-17 | 2025-10-05 | 2025-10-18 | Anil Kumar | 37.931 | 2.7094 | TA505 | 152A/5 | Completed
2025-10-17 | 2025-10-14 | 2025-10-21 | Deglal Mahato | 65.028 | 8.1285 | TA505 | 121/0 | Completed
2025-10-17 | 2025-10-16 | 2025-10-21 | Deglal Mahato Mp | 35.602 | 5.9337 | TA505 | 169/7 | Completed
2025-10-17 | 2025-10-13 | 2025-10-18 | Jagannaath Saw Mp | 36.1598 | 6.0266 | TA505 | 158/2 | Completed
2025-10-17 | 2025-10-10 | 2025-10-18 | Jhemon Mahato 2 | 37.931 | 4.2146 | TA505 | 140/1 | Completed
2025-10-17 | 2025-10-13 | 2025-10-26 | Jwala Singh | 70.74 | 5.0529 | TA505 | 102/0 | Completed
2025-10-17 | 2025-10-01 | 2025-10-26 | Jyoti Const | 124.95 | 4.8058 | TA505 | 112/0 | Completed
2025-10-17 | 2025-10-16 | 2025-10-25 | Pankaj Singh Mp | 55.451 | 5.5451 | TA505 | 167/0 | Completed
2025-10-17 | 2025-10-16 | 2025-11-08 | Paramanand 1 | 62.116 | 2.5882 | TA505 | 161/0 | Completed
2025-10-17 | 2025-10-13 | 2025-10-24 | Toshan Mahato | 55.451 | 4.6209 | TA505 | 147A/0 | Completed
2025-10-18 | 2025-10-05 | 2025-10-18 | Anil Kumar | 37.931 | 2.7094 | TA505 | 152A/5 | Completed
2025-10-18 | 2025-10-14 | 2025-10-21 | Deglal Mahato | 65.028 | 8.1285 | TA505 | 121/0 | Completed
2025-10-18 | 2025-10-16 | 2025-10-21 | Deglal Mahato Mp | 35.602 | 5.9337 | TA505 | 169/7 | Completed
2025-10-18 | 2025-10-13 | 2025-10-18 | Jagannaath Saw Mp | 36.1598 | 6.0266 | TA505 | 158/2 | Completed
2025-10-18 | 2025-10-10 | 2025-10-18 | Jhemon Mahato 2 | 37.931 | 4.2146 | TA505 | 140/1 | Completed
2025-10-18 | 2025-10-13 | 2025-10-26 | Jwala Singh | 70.74 | 5.0529 | TA505 | 102/0 | Completed
2025-10-18 | 2025-10-01 | 2025-10-26 | Jyoti Const | 124.95 | 4.8058 | TA505 | 112/0 | Completed
2025-10-18 | 2025-10-16 | 2025-10-25 | Pankaj Singh Mp | 55.451 | 5.5451 | TA505 | 167/0 | Completed
2025-10-18 | 2025-10-16 | 2025-11-08 | Paramanand 1 | 62.116 | 2.5882 | TA505 | 161/0 | Completed
2025-10-18 | 2025-10-13 | 2025-10-24 | Toshan Mahato | 55.451 | 4.6209 | TA505 | 147A/0 | Completed
2025-10-19 | 2025-10-14 | 2025-10-21 | Deglal Mahato | 65.028 | 8.1285 | TA505 | 121/0 | Completed
2025-10-19 | 2025-10-16 | 2025-10-21 | Deglal Mahato Mp | 35.602 | 5.9337 | TA505 | 169/7 | Completed
2025-10-19 | 2025-10-19 | 2025-11-02 | Jagannaath Saw Mp | 59.501 | 3.9667 | TA505 | 159/0 | Completed
2025-10-19 | 2025-10-19 | 2025-11-02 | Jhemon Mahato 2 | 57.96 | 3.864 | TA505 | 144A/3 | Completed
2025-10-19 | 2025-10-13 | 2025-10-26 | Jwala Singh | 70.74 | 5.0529 | TA505 | 102/0 | Completed
2025-10-19 | 2025-10-01 | 2025-10-26 | Jyoti Const | 124.95 | 4.8058 | TA505 | 112/0 | Completed
2025-10-19 | 2025-10-16 | 2025-10-25 | Pankaj Singh Mp | 55.451 | 5.5451 | TA505 | 167/0 | Completed
2025-10-19 | 2025-10-16 | 2025-11-08 | Paramanand 1 | 62.116 | 2.5882 | TA505 | 161/0 | Completed
2025-10-19 | 2025-10-13 | 2025-10-24 | Toshan Mahato | 55.451 | 4.6209 | TA505 | 147A/0 | Completed
2025-10-20 | 2025-10-14 | 2025-10-21 | Deglal Mahato | 65.028 | 8.1285 | TA505 | 121/0 | Completed
2025-10-20 | 2025-10-16 | 2025-10-21 | Deglal Mahato Mp | 35.602 | 5.9337 | TA505 | 169/7 | Completed
2025-10-20 | 2025-10-19 | 2025-11-02 | Jagannaath Saw Mp | 59.501 | 3.9667 | TA505 | 159/0 | Completed
2025-10-20 | 2025-10-19 | 2025-11-02 | Jhemon Mahato 2 | 57.96 | 3.864 | TA505 | 144A/3 | Completed
2025-10-20 | 2025-10-13 | 2025-10-26 | Jwala Singh | 70.74 | 5.0529 | TA505 | 102/0 | Completed
2025-10-20 | 2025-10-01 | 2025-10-26 | Jyoti Const | 124.95 | 4.8058 | TA505 | 112/0 | Completed
2025-10-20 | 2025-10-16 | 2025-10-25 | Pankaj Singh Mp | 55.451 | 5.5451 | TA505 | 167/0 | Completed
2025-10-20 | 2025-10-16 | 2025-11-08 | Paramanand 1 | 62.116 | 2.5882 | TA505 | 161/0 | Completed
2025-10-20 | 2025-10-13 | 2025-10-24 | Toshan Mahato | 55.451 | 4.6209 | TA505 | 147A/0 | Completed
2025-10-21 | 2025-10-14 | 2025-10-21 | Deglal Mahato | 65.028 | 8.1285 | TA505 | 121/0 | Completed
2025-10-21 | 2025-10-16 | 2025-10-21 | Deglal Mahato Mp | 35.602 | 5.9337 | TA505 | 169/7 | Completed
2025-10-21 | 2025-10-19 | 2025-11-02 | Jagannaath Saw Mp | 59.501 | 3.9667 | TA505 | 159/0 | Completed
2025-10-21 | 2025-10-19 | 2025-11-02 | Jhemon Mahato 2 | 57.96 | 3.864 | TA505 | 144A/3 | Completed
2025-10-21 | 2025-10-13 | 2025-10-26 | Jwala Singh | 70.74 | 5.0529 | TA505 | 102/0 | Completed
2025-10-21 | 2025-10-01 | 2025-10-26 | Jyoti Const | 124.95 | 4.8058 | TA505 | 112/0 | Completed
2025-10-21 | 2025-10-16 | 2025-10-25 | Pankaj Singh Mp | 55.451 | 5.5451 | TA505 | 167/0 | Completed
2025-10-21 | 2025-10-16 | 2025-11-08 | Paramanand 1 | 62.116 | 2.5882 | TA505 | 161/0 | Completed
2025-10-21 | 2025-10-13 | 2025-10-24 | Toshan Mahato | 55.451 | 4.6209 | TA505 | 147A/0 | Completed
2025-10-22 | 2025-10-22 | 2025-10-31 | Deglal Mahato | 67.262 | 6.7262 | TA505 | 114/0 | Completed
2025-10-22 | 2025-10-22 | 2025-10-30 | Deglal Mahato Mp | 36.1598 | 4.0178 | TA505 | 169/2 | Completed
2025-10-22 | 2025-10-19 | 2025-11-02 | Jagannaath Saw Mp | 59.501 | 3.9667 | TA505 | 159/0 | Completed
2025-10-22 | 2025-10-19 | 2025-11-02 | Jhemon Mahato 2 | 57.96 | 3.864 | TA505 | 144A/3 | Completed
2025-10-22 | 2025-10-13 | 2025-10-26 | Jwala Singh | 70.74 | 5.0529 | TA505 | 102/0 | Completed
2025-10-22 | 2025-10-01 | 2025-10-26 | Jyoti Const | 124.95 | 4.8058 | TA505 | 112/0 | Completed
2025-10-22 | 2025-10-16 | 2025-10-25 | Pankaj Singh Mp | 55.451 | 5.5451 | TA505 | 167/0 | Completed
2025-10-22 | 2025-10-16 | 2025-11-08 | Paramanand 1 | 62.116 | 2.5882 | TA505 | 161/0 | Completed
2025-10-22 | 2025-10-13 | 2025-10-24 | Toshan Mahato | 55.451 | 4.6209 | TA505 | 147A/0 | Completed
2025-10-23 | 2025-10-22 | 2025-10-31 | Deglal Mahato | 67.262 | 6.7262 | TA505 | 114/0 | Completed
2025-10-23 | 2025-10-22 | 2025-10-30 | Deglal Mahato Mp | 36.1598 | 4.0178 | TA505 | 169/2 | Completed
2025-10-23 | 2025-10-19 | 2025-11-02 | Jagannaath Saw Mp | 59.501 | 3.9667 | TA505 | 159/0 | Completed
2025-10-23 | 2025-10-19 | 2025-11-02 | Jhemon Mahato 2 | 57.96 | 3.864 | TA505 | 144A/3 | Completed
2025-10-23 | 2025-10-13 | 2025-10-26 | Jwala Singh | 70.74 | 5.0529 | TA505 | 102/0 | Completed
2025-10-23 | 2025-10-01 | 2025-10-26 | Jyoti Const | 124.95 | 4.8058 | TA505 | 112/0 | Completed
2025-10-23 | 2025-10-16 | 2025-10-25 | Pankaj Singh Mp | 55.451 | 5.5451 | TA505 | 167/0 | Completed
2025-10-23 | 2025-10-16 | 2025-11-08 | Paramanand 1 | 62.116 | 2.5882 | TA505 | 161/0 | Completed
2025-10-23 | 2025-10-13 | 2025-10-24 | Toshan Mahato | 55.451 | 4.6209 | TA505 | 147A/0 | Completed
2025-10-24 | 2025-10-22 | 2025-10-31 | Deglal Mahato | 67.262 | 6.7262 | TA505 | 114/0 | Completed
2025-10-24 | 2025-10-22 | 2025-10-30 | Deglal Mahato Mp | 36.1598 | 4.0178 | TA505 | 169/2 | Completed
2025-10-24 | 2025-10-19 | 2025-11-02 | Jagannaath Saw Mp | 59.501 | 3.9667 | TA505 | 159/0 | Completed
2025-10-24 | 2025-10-19 | 2025-11-02 | Jhemon Mahato 2 | 57.96 | 3.864 | TA505 | 144A/3 | Completed
2025-10-24 | 2025-10-13 | 2025-10-26 | Jwala Singh | 70.74 | 5.0529 | TA505 | 102/0 | Completed
2025-10-24 | 2025-10-01 | 2025-10-26 | Jyoti Const | 124.95 | 4.8058 | TA505 | 112/0 | Completed
2025-10-24 | 2025-10-16 | 2025-10-25 | Pankaj Singh Mp | 55.451 | 5.5451 | TA505 | 167/0 | Completed
2025-10-24 | 2025-10-16 | 2025-11-08 | Paramanand 1 | 62.116 | 2.5882 | TA505 | 161/0 | Completed
2025-10-24 | 2025-10-13 | 2025-10-24 | Toshan Mahato | 55.451 | 4.6209 | TA505 | 147A/0 | Completed
2025-10-25 | 2025-10-22 | 2025-10-31 | Deglal Mahato | 67.262 | 6.7262 | TA505 | 114/0 | Completed
2025-10-25 | 2025-10-22 | 2025-10-30 | Deglal Mahato Mp | 36.1598 | 4.0178 | TA505 | 169/2 | Completed
2025-10-25 | 2025-10-19 | 2025-11-02 | Jagannaath Saw Mp | 59.501 | 3.9667 | TA505 | 159/0 | Completed
2025-10-25 | 2025-10-19 | 2025-11-02 | Jhemon Mahato 2 | 57.96 | 3.864 | TA505 | 144A/3 | Completed
2025-10-25 | 2025-10-13 | 2025-10-26 | Jwala Singh | 70.74 | 5.0529 | TA505 | 102/0 | Completed
2025-10-25 | 2025-10-01 | 2025-10-26 | Jyoti Const | 124.95 | 4.8058 | TA505 | 112/0 | Completed
2025-10-25 | 2025-10-16 | 2025-10-25 | Pankaj Singh Mp | 55.451 | 5.5451 | TA505 | 167/0 | Completed
2025-10-25 | 2025-10-16 | 2025-11-08 | Paramanand 1 | 62.116 | 2.5882 | TA505 | 161/0 | Completed
2025-10-25 | 2025-10-25 | 2025-11-10 | Toshan Mahato | 65.028 | 3.8252 | TA505 | 148A/0 | Completed
2025-10-26 | 2025-10-22 | 2025-10-31 | Deglal Mahato | 67.262 | 6.7262 | TA505 | 114/0 | Completed
2025-10-26 | 2025-10-22 | 2025-10-30 | Deglal Mahato Mp | 36.1598 | 4.0178 | TA505 | 169/2 | Completed
2025-10-26 | 2025-10-19 | 2025-11-02 | Jagannaath Saw Mp | 59.501 | 3.9667 | TA505 | 159/0 | Completed
2025-10-26 | 2025-10-19 | 2025-11-02 | Jhemon Mahato 2 | 57.96 | 3.864 | TA505 | 144A/3 | Completed
2025-10-26 | 2025-10-13 | 2025-10-26 | Jwala Singh | 70.74 | 5.0529 | TA505 | 102/0 | Completed
2025-10-26 | 2025-10-01 | 2025-10-26 | Jyoti Const | 124.95 | 4.8058 | TA505 | 112/0 | Completed
2025-10-26 | 2025-10-26 | 2025-11-03 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/1 | Completed
2025-10-26 | 2025-10-16 | 2025-11-08 | Paramanand 1 | 62.116 | 2.5882 | TA505 | 161/0 | Completed
2025-10-26 | 2025-10-25 | 2025-11-10 | Toshan Mahato | 65.028 | 3.8252 | TA505 | 148A/0 | Completed
2025-10-27 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-10-27 | 2025-10-27 | 2025-11-17 | Crane Erc Team Mp | 34.79 | 1.5814 | TA505 | 173/1 | Completed
2025-10-27 | 2025-10-22 | 2025-10-31 | Deglal Mahato | 67.262 | 6.7262 | TA505 | 114/0 | Completed
2025-10-27 | 2025-10-22 | 2025-10-30 | Deglal Mahato Mp | 36.1598 | 4.0178 | TA505 | 169/2 | Completed
2025-10-27 | 2025-10-19 | 2025-11-02 | Jagannaath Saw Mp | 59.501 | 3.9667 | TA505 | 159/0 | Completed
2025-10-27 | 2025-10-19 | 2025-11-02 | Jhemon Mahato 2 | 57.96 | 3.864 | TA505 | 144A/3 | Completed
2025-10-27 | 2025-10-27 | 2025-11-05 | Jwala Singh | 36.1598 | 3.616 | TA505 | 103/4 | Completed
2025-10-27 | 2025-10-27 | 2025-11-11 | Jyoti Const | 37.931 | 2.3707 | TA505 | 149B/3 | Completed
2025-10-27 | 2025-10-26 | 2025-11-03 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/1 | Completed
2025-10-27 | 2025-10-16 | 2025-11-08 | Paramanand 1 | 62.116 | 2.5882 | TA505 | 161/0 | Completed
2025-10-27 | 2025-10-25 | 2025-11-10 | Toshan Mahato | 65.028 | 3.8252 | TA505 | 148A/0 | Completed
2025-10-28 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-10-28 | 2025-10-27 | 2025-11-17 | Crane Erc Team Mp | 34.79 | 1.5814 | TA505 | 173/1 | Completed
2025-10-28 | 2025-10-22 | 2025-10-31 | Deglal Mahato | 67.262 | 6.7262 | TA505 | 114/0 | Completed
2025-10-28 | 2025-10-22 | 2025-10-30 | Deglal Mahato Mp | 36.1598 | 4.0178 | TA505 | 169/2 | Completed
2025-10-28 | 2025-10-19 | 2025-11-02 | Jagannaath Saw Mp | 59.501 | 3.9667 | TA505 | 159/0 | Completed
2025-10-28 | 2025-10-19 | 2025-11-02 | Jhemon Mahato 2 | 57.96 | 3.864 | TA505 | 144A/3 | Completed
2025-10-28 | 2025-10-27 | 2025-11-05 | Jwala Singh | 36.1598 | 3.616 | TA505 | 103/4 | Completed
2025-10-28 | 2025-10-27 | 2025-11-11 | Jyoti Const | 37.931 | 2.3707 | TA505 | 149B/3 | Completed
2025-10-28 | 2025-10-26 | 2025-11-03 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/1 | Completed
2025-10-28 | 2025-10-16 | 2025-11-08 | Paramanand 1 | 62.116 | 2.5882 | TA505 | 161/0 | Completed
2025-10-28 | 2025-10-25 | 2025-11-10 | Toshan Mahato | 65.028 | 3.8252 | TA505 | 148A/0 | Completed
2025-10-29 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-10-29 | 2025-10-27 | 2025-11-17 | Crane Erc Team Mp | 34.79 | 1.5814 | TA505 | 173/1 | Completed
2025-10-29 | 2025-10-22 | 2025-10-31 | Deglal Mahato | 67.262 | 6.7262 | TA505 | 114/0 | Completed
2025-10-29 | 2025-10-22 | 2025-10-30 | Deglal Mahato Mp | 36.1598 | 4.0178 | TA505 | 169/2 | Completed
2025-10-29 | 2025-10-19 | 2025-11-02 | Jagannaath Saw Mp | 59.501 | 3.9667 | TA505 | 159/0 | Completed
2025-10-29 | 2025-10-19 | 2025-11-02 | Jhemon Mahato 2 | 57.96 | 3.864 | TA505 | 144A/3 | Completed
2025-10-29 | 2025-10-27 | 2025-11-05 | Jwala Singh | 36.1598 | 3.616 | TA505 | 103/4 | Completed
2025-10-29 | 2025-10-27 | 2025-11-11 | Jyoti Const | 37.931 | 2.3707 | TA505 | 149B/3 | Completed
2025-10-29 | 2025-10-26 | 2025-11-03 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/1 | Completed
2025-10-29 | 2025-10-16 | 2025-11-08 | Paramanand 1 | 62.116 | 2.5882 | TA505 | 161/0 | Completed
2025-10-29 | 2025-10-25 | 2025-11-10 | Toshan Mahato | 65.028 | 3.8252 | TA505 | 148A/0 | Completed
2025-10-30 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-10-30 | 2025-10-27 | 2025-11-17 | Crane Erc Team Mp | 34.79 | 1.5814 | TA505 | 173/1 | Completed
2025-10-30 | 2025-10-22 | 2025-10-31 | Deglal Mahato | 67.262 | 6.7262 | TA505 | 114/0 | Completed
2025-10-30 | 2025-10-22 | 2025-10-30 | Deglal Mahato Mp | 36.1598 | 4.0178 | TA505 | 169/2 | Completed
2025-10-30 | 2025-10-19 | 2025-11-02 | Jagannaath Saw Mp | 59.501 | 3.9667 | TA505 | 159/0 | Completed
2025-10-30 | 2025-10-19 | 2025-11-02 | Jhemon Mahato 2 | 57.96 | 3.864 | TA505 | 144A/3 | Completed
2025-10-30 | 2025-10-27 | 2025-11-05 | Jwala Singh | 36.1598 | 3.616 | TA505 | 103/4 | Completed
2025-10-30 | 2025-10-27 | 2025-11-11 | Jyoti Const | 37.931 | 2.3707 | TA505 | 149B/3 | Completed
2025-10-30 | 2025-10-26 | 2025-11-03 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/1 | Completed
2025-10-30 | 2025-10-16 | 2025-11-08 | Paramanand 1 | 62.116 | 2.5882 | TA505 | 161/0 | Completed
2025-10-30 | 2025-10-25 | 2025-11-10 | Toshan Mahato | 65.028 | 3.8252 | TA505 | 148A/0 | Completed
2025-10-31 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-10-31 | 2025-10-27 | 2025-11-17 | Crane Erc Team Mp | 34.79 | 1.5814 | TA505 | 173/1 | Completed
2025-10-31 | 2025-10-22 | 2025-10-31 | Deglal Mahato | 67.262 | 6.7262 | TA505 | 114/0 | Completed
2025-10-31 | 2025-10-31 | 2025-11-06 | Deglal Mahato Mp | 35.602 | 5.086 | TA505 | 169/1 | Completed
2025-10-31 | 2025-10-19 | 2025-11-02 | Jagannaath Saw Mp | 59.501 | 3.9667 | TA505 | 159/0 | Completed
2025-10-31 | 2025-10-19 | 2025-11-02 | Jhemon Mahato 2 | 57.96 | 3.864 | TA505 | 144A/3 | Completed
2025-10-31 | 2025-10-27 | 2025-11-05 | Jwala Singh | 36.1598 | 3.616 | TA505 | 103/4 | Completed
2025-10-31 | 2025-10-27 | 2025-11-11 | Jyoti Const | 37.931 | 2.3707 | TA505 | 149B/3 | Completed
2025-10-31 | 2025-10-26 | 2025-11-03 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/1 | Completed
2025-10-31 | 2025-10-16 | 2025-11-08 | Paramanand 1 | 62.116 | 2.5882 | TA505 | 161/0 | Completed
2025-10-31 | 2025-10-25 | 2025-11-10 | Toshan Mahato | 65.028 | 3.8252 | TA505 | 148A/0 | Completed
2025-11-01 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-11-01 | 2025-10-27 | 2025-11-17 | Crane Erc Team Mp | 34.79 | 1.5814 | TA505 | 173/1 | Completed
2025-11-01 | 2025-11-01 | 2025-11-09 | Deglal Mahato | 45.697 | 5.0774 | TA505 | 126/1 | Completed
2025-11-01 | 2025-10-31 | 2025-11-06 | Deglal Mahato Mp | 35.602 | 5.086 | TA505 | 169/1 | Completed
2025-11-01 | 2025-10-19 | 2025-11-02 | Jagannaath Saw Mp | 59.501 | 3.9667 | TA505 | 159/0 | Completed
2025-11-01 | 2025-10-19 | 2025-11-02 | Jhemon Mahato 2 | 57.96 | 3.864 | TA505 | 144A/3 | Completed
2025-11-01 | 2025-10-27 | 2025-11-05 | Jwala Singh | 36.1598 | 3.616 | TA505 | 103/4 | Completed
2025-11-01 | 2025-10-27 | 2025-11-11 | Jyoti Const | 37.931 | 2.3707 | TA505 | 149B/3 | Completed
2025-11-01 | 2025-10-26 | 2025-11-03 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/1 | Completed
2025-11-01 | 2025-10-16 | 2025-11-08 | Paramanand 1 | 62.116 | 2.5882 | TA505 | 161/0 | Completed
2025-11-01 | 2025-10-25 | 2025-11-10 | Toshan Mahato | 65.028 | 3.8252 | TA505 | 148A/0 | Completed
2025-11-02 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-11-02 | 2025-10-27 | 2025-11-17 | Crane Erc Team Mp | 34.79 | 1.5814 | TA505 | 173/1 | Completed
2025-11-02 | 2025-11-01 | 2025-11-09 | Deglal Mahato | 45.697 | 5.0774 | TA505 | 126/1 | Completed
2025-11-02 | 2025-10-31 | 2025-11-06 | Deglal Mahato Mp | 35.602 | 5.086 | TA505 | 169/1 | Completed
2025-11-02 | 2025-10-19 | 2025-11-02 | Jagannaath Saw Mp | 59.501 | 3.9667 | TA505 | 159/0 | Completed
2025-11-02 | 2025-10-19 | 2025-11-02 | Jhemon Mahato 2 | 57.96 | 3.864 | TA505 | 144A/3 | Completed
2025-11-02 | 2025-10-27 | 2025-11-05 | Jwala Singh | 36.1598 | 3.616 | TA505 | 103/4 | Completed
2025-11-02 | 2025-10-27 | 2025-11-11 | Jyoti Const | 37.931 | 2.3707 | TA505 | 149B/3 | Completed
2025-11-02 | 2025-10-26 | 2025-11-03 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/1 | Completed
2025-11-02 | 2025-10-16 | 2025-11-08 | Paramanand 1 | 62.116 | 2.5882 | TA505 | 161/0 | Completed
2025-11-02 | 2025-10-25 | 2025-11-10 | Toshan Mahato | 65.028 | 3.8252 | TA505 | 148A/0 | Completed
2025-11-03 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-11-03 | 2025-10-27 | 2025-11-17 | Crane Erc Team Mp | 34.79 | 1.5814 | TA505 | 173/1 | Completed
2025-11-03 | 2025-11-01 | 2025-11-09 | Deglal Mahato | 45.697 | 5.0774 | TA505 | 126/1 | Completed
2025-11-03 | 2025-10-31 | 2025-11-06 | Deglal Mahato Mp | 35.602 | 5.086 | TA505 | 169/1 | Completed
2025-11-03 | 2025-11-03 | 2025-11-07 | Jagannaath Saw Mp | 34.79 | 6.958 | TA505 | 165/6 | Completed
2025-11-03 | 2025-11-03 | 2025-11-10 | Jhemon Mahato 2 | 37.931 | 4.7414 | TA505 | 135/1 | Completed
2025-11-03 | 2025-10-27 | 2025-11-05 | Jwala Singh | 36.1598 | 3.616 | TA505 | 103/4 | Completed
2025-11-03 | 2025-10-27 | 2025-11-11 | Jyoti Const | 37.931 | 2.3707 | TA505 | 149B/3 | Completed
2025-11-03 | 2025-10-26 | 2025-11-03 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/1 | Completed
2025-11-03 | 2025-10-16 | 2025-11-08 | Paramanand 1 | 62.116 | 2.5882 | TA505 | 161/0 | Completed
2025-11-03 | 2025-10-25 | 2025-11-10 | Toshan Mahato | 65.028 | 3.8252 | TA505 | 148A/0 | Completed
2025-11-04 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-11-04 | 2025-10-27 | 2025-11-17 | Crane Erc Team Mp | 34.79 | 1.5814 | TA505 | 173/1 | Completed
2025-11-04 | 2025-11-01 | 2025-11-09 | Deglal Mahato | 45.697 | 5.0774 | TA505 | 126/1 | Completed
2025-11-04 | 2025-10-31 | 2025-11-06 | Deglal Mahato Mp | 35.602 | 5.086 | TA505 | 169/1 | Completed
2025-11-04 | 2025-11-03 | 2025-11-07 | Jagannaath Saw Mp | 34.79 | 6.958 | TA505 | 165/6 | Completed
2025-11-04 | 2025-11-03 | 2025-11-10 | Jhemon Mahato 2 | 37.931 | 4.7414 | TA505 | 135/1 | Completed
2025-11-04 | 2025-10-27 | 2025-11-05 | Jwala Singh | 36.1598 | 3.616 | TA505 | 103/4 | Completed
2025-11-04 | 2025-10-27 | 2025-11-11 | Jyoti Const | 37.931 | 2.3707 | TA505 | 149B/3 | Completed
2025-11-04 | 2025-11-04 | 2025-11-13 | Pankaj Singh Mp | 37.931 | 3.7931 | TA505 | 166/9 | Completed
2025-11-04 | 2025-10-16 | 2025-11-08 | Paramanand 1 | 62.116 | 2.5882 | TA505 | 161/0 | Completed
2025-11-04 | 2025-10-25 | 2025-11-10 | Toshan Mahato | 65.028 | 3.8252 | TA505 | 148A/0 | Completed
2025-11-05 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-11-05 | 2025-10-27 | 2025-11-17 | Crane Erc Team Mp | 34.79 | 1.5814 | TA505 | 173/1 | Completed
2025-11-05 | 2025-11-01 | 2025-11-09 | Deglal Mahato | 45.697 | 5.0774 | TA505 | 126/1 | Completed
2025-11-05 | 2025-10-31 | 2025-11-06 | Deglal Mahato Mp | 35.602 | 5.086 | TA505 | 169/1 | Completed
2025-11-05 | 2025-11-03 | 2025-11-07 | Jagannaath Saw Mp | 34.79 | 6.958 | TA505 | 165/6 | Completed
2025-11-05 | 2025-11-03 | 2025-11-10 | Jhemon Mahato 2 | 37.931 | 4.7414 | TA505 | 135/1 | Completed
2025-11-05 | 2025-10-27 | 2025-11-05 | Jwala Singh | 36.1598 | 3.616 | TA505 | 103/4 | Completed
2025-11-05 | 2025-10-27 | 2025-11-11 | Jyoti Const | 37.931 | 2.3707 | TA505 | 149B/3 | Completed
2025-11-05 | 2025-11-04 | 2025-11-13 | Pankaj Singh Mp | 37.931 | 3.7931 | TA505 | 166/9 | Completed
2025-11-05 | 2025-10-16 | 2025-11-08 | Paramanand 1 | 62.116 | 2.5882 | TA505 | 161/0 | Completed
2025-11-05 | 2025-10-25 | 2025-11-10 | Toshan Mahato | 65.028 | 3.8252 | TA505 | 148A/0 | Completed
2025-11-06 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-11-06 | 2025-10-27 | 2025-11-17 | Crane Erc Team Mp | 34.79 | 1.5814 | TA505 | 173/1 | Completed
2025-11-06 | 2025-11-01 | 2025-11-09 | Deglal Mahato | 45.697 | 5.0774 | TA505 | 126/1 | Completed
2025-11-06 | 2025-10-31 | 2025-11-06 | Deglal Mahato Mp | 35.602 | 5.086 | TA505 | 169/1 | Completed
2025-11-06 | 2025-11-03 | 2025-11-07 | Jagannaath Saw Mp | 34.79 | 6.958 | TA505 | 165/6 | Completed
2025-11-06 | 2025-11-03 | 2025-11-10 | Jhemon Mahato 2 | 37.931 | 4.7414 | TA505 | 135/1 | Completed
2025-11-06 | 2025-11-06 | 2025-11-18 | Jwala Singh | 62.444 | 4.8034 | TA505 | 109/0 | Completed
2025-11-06 | 2025-10-27 | 2025-11-11 | Jyoti Const | 37.931 | 2.3707 | TA505 | 149B/3 | Completed
2025-11-06 | 2025-11-04 | 2025-11-13 | Pankaj Singh Mp | 37.931 | 3.7931 | TA505 | 166/9 | Completed
2025-11-06 | 2025-10-16 | 2025-11-08 | Paramanand 1 | 62.116 | 2.5882 | TA505 | 161/0 | Completed
2025-11-06 | 2025-10-25 | 2025-11-10 | Toshan Mahato | 65.028 | 3.8252 | TA505 | 148A/0 | Completed
2025-11-07 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-11-07 | 2025-10-27 | 2025-11-17 | Crane Erc Team Mp | 34.79 | 1.5814 | TA505 | 173/1 | Completed
2025-11-07 | 2025-11-01 | 2025-11-09 | Deglal Mahato | 45.697 | 5.0774 | TA505 | 126/1 | Completed
2025-11-07 | 2025-11-07 | 2025-11-13 | Deglal Mahato Mp | 36.1598 | 5.1657 | TA505 | 170/8 | Completed
2025-11-07 | 2025-11-03 | 2025-11-07 | Jagannaath Saw Mp | 34.79 | 6.958 | TA505 | 165/6 | Completed
2025-11-07 | 2025-11-03 | 2025-11-10 | Jhemon Mahato 2 | 37.931 | 4.7414 | TA505 | 135/1 | Completed
2025-11-07 | 2025-11-06 | 2025-11-18 | Jwala Singh | 62.444 | 4.8034 | TA505 | 109/0 | Completed
2025-11-07 | 2025-10-27 | 2025-11-11 | Jyoti Const | 37.931 | 2.3707 | TA505 | 149B/3 | Completed
2025-11-07 | 2025-11-04 | 2025-11-13 | Pankaj Singh Mp | 37.931 | 3.7931 | TA505 | 166/9 | Completed
2025-11-07 | 2025-10-16 | 2025-11-08 | Paramanand 1 | 62.116 | 2.5882 | TA505 | 161/0 | Completed
2025-11-07 | 2025-10-25 | 2025-11-10 | Toshan Mahato | 65.028 | 3.8252 | TA505 | 148A/0 | Completed
2025-11-08 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-11-08 | 2025-10-27 | 2025-11-17 | Crane Erc Team Mp | 34.79 | 1.5814 | TA505 | 173/1 | Completed
2025-11-08 | 2025-11-01 | 2025-11-09 | Deglal Mahato | 45.697 | 5.0774 | TA505 | 126/1 | Completed
2025-11-08 | 2025-11-07 | 2025-11-13 | Deglal Mahato Mp | 36.1598 | 5.1657 | TA505 | 170/8 | Completed
2025-11-08 | 2025-11-08 | 2025-11-15 | Jagannaath Saw Mp | 62.444 | 7.8055 | TA505 | 166/0 | Completed
2025-11-08 | 2025-11-03 | 2025-11-10 | Jhemon Mahato 2 | 37.931 | 4.7414 | TA505 | 135/1 | Completed
2025-11-08 | 2025-11-06 | 2025-11-18 | Jwala Singh | 62.444 | 4.8034 | TA505 | 109/0 | Completed
2025-11-08 | 2025-10-27 | 2025-11-11 | Jyoti Const | 37.931 | 2.3707 | TA505 | 149B/3 | Completed
2025-11-08 | 2025-11-04 | 2025-11-13 | Pankaj Singh Mp | 37.931 | 3.7931 | TA505 | 166/9 | Completed
2025-11-08 | 2025-10-16 | 2025-11-08 | Paramanand 1 | 62.116 | 2.5882 | TA505 | 161/0 | Completed
2025-11-08 | 2025-10-25 | 2025-11-10 | Toshan Mahato | 65.028 | 3.8252 | TA505 | 148A/0 | Completed
2025-11-09 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-11-09 | 2025-10-27 | 2025-11-17 | Crane Erc Team Mp | 34.79 | 1.5814 | TA505 | 173/1 | Completed
2025-11-09 | 2025-11-01 | 2025-11-09 | Deglal Mahato | 45.697 | 5.0774 | TA505 | 126/1 | Completed
2025-11-09 | 2025-11-07 | 2025-11-13 | Deglal Mahato Mp | 36.1598 | 5.1657 | TA505 | 170/8 | Completed
2025-11-09 | 2025-11-08 | 2025-11-15 | Jagannaath Saw Mp | 62.444 | 7.8055 | TA505 | 166/0 | Completed
2025-11-09 | 2025-11-03 | 2025-11-10 | Jhemon Mahato 2 | 37.931 | 4.7414 | TA505 | 135/1 | Completed
2025-11-09 | 2025-11-06 | 2025-11-18 | Jwala Singh | 62.444 | 4.8034 | TA505 | 109/0 | Completed
2025-11-09 | 2025-10-27 | 2025-11-11 | Jyoti Const | 37.931 | 2.3707 | TA505 | 149B/3 | Completed
2025-11-09 | 2025-11-04 | 2025-11-13 | Pankaj Singh Mp | 37.931 | 3.7931 | TA505 | 166/9 | Completed
2025-11-09 | 2025-10-25 | 2025-11-10 | Toshan Mahato | 65.028 | 3.8252 | TA505 | 148A/0 | Completed
2025-11-10 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-11-10 | 2025-10-27 | 2025-11-17 | Crane Erc Team Mp | 34.79 | 1.5814 | TA505 | 173/1 | Completed
2025-11-10 | 2025-11-10 | 2025-11-16 | Deglal Mahato | 37.931 | 5.4187 | TA505 | 126/3 | Completed
2025-11-10 | 2025-11-07 | 2025-11-13 | Deglal Mahato Mp | 36.1598 | 5.1657 | TA505 | 170/8 | Completed
2025-11-10 | 2025-11-08 | 2025-11-15 | Jagannaath Saw Mp | 62.444 | 7.8055 | TA505 | 166/0 | Completed
2025-11-10 | 2025-11-03 | 2025-11-10 | Jhemon Mahato 2 | 37.931 | 4.7414 | TA505 | 135/1 | Completed
2025-11-10 | 2025-11-06 | 2025-11-18 | Jwala Singh | 62.444 | 4.8034 | TA505 | 109/0 | Completed
2025-11-10 | 2025-10-27 | 2025-11-11 | Jyoti Const | 37.931 | 2.3707 | TA505 | 149B/3 | Completed
2025-11-10 | 2025-11-04 | 2025-11-13 | Pankaj Singh Mp | 37.931 | 3.7931 | TA505 | 166/9 | Completed
2025-11-10 | 2025-11-10 | 2025-11-23 | Prayag Shah Mp | 65.87 | 4.705 | TA505 | 174A/0 | Completed
2025-11-10 | 2025-10-25 | 2025-11-10 | Toshan Mahato | 65.028 | 3.8252 | TA505 | 148A/0 | Completed
2025-11-11 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-11-11 | 2025-10-27 | 2025-11-17 | Crane Erc Team Mp | 34.79 | 1.5814 | TA505 | 173/1 | Completed
2025-11-11 | 2025-11-10 | 2025-11-16 | Deglal Mahato | 37.931 | 5.4187 | TA505 | 126/3 | Completed
2025-11-11 | 2025-11-07 | 2025-11-13 | Deglal Mahato Mp | 36.1598 | 5.1657 | TA505 | 170/8 | Completed
2025-11-11 | 2025-11-08 | 2025-11-15 | Jagannaath Saw Mp | 62.444 | 7.8055 | TA505 | 166/0 | Completed
2025-11-11 | 2025-11-11 | 2025-11-22 | Jhemon Mahato 2 | 37.931 | 3.1609 | TA505 | 136/5 | Completed
2025-11-11 | 2025-11-06 | 2025-11-18 | Jwala Singh | 62.444 | 4.8034 | TA505 | 109/0 | Completed
2025-11-11 | 2025-10-27 | 2025-11-11 | Jyoti Const | 37.931 | 2.3707 | TA505 | 149B/3 | Completed
2025-11-11 | 2025-11-04 | 2025-11-13 | Pankaj Singh Mp | 37.931 | 3.7931 | TA505 | 166/9 | Completed
2025-11-11 | 2025-11-10 | 2025-11-23 | Prayag Shah Mp | 65.87 | 4.705 | TA505 | 174A/0 | Completed
2025-11-12 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-11-12 | 2025-10-27 | 2025-11-17 | Crane Erc Team Mp | 34.79 | 1.5814 | TA505 | 173/1 | Completed
2025-11-12 | 2025-11-10 | 2025-11-16 | Deglal Mahato | 37.931 | 5.4187 | TA505 | 126/3 | Completed
2025-11-12 | 2025-11-07 | 2025-11-13 | Deglal Mahato Mp | 36.1598 | 5.1657 | TA505 | 170/8 | Completed
2025-11-12 | 2025-11-08 | 2025-11-15 | Jagannaath Saw Mp | 62.444 | 7.8055 | TA505 | 166/0 | Completed
2025-11-12 | 2025-11-11 | 2025-11-22 | Jhemon Mahato 2 | 37.931 | 3.1609 | TA505 | 136/5 | Completed
2025-11-12 | 2025-11-06 | 2025-11-18 | Jwala Singh | 62.444 | 4.8034 | TA505 | 109/0 | Completed
2025-11-12 | 2025-11-04 | 2025-11-13 | Pankaj Singh Mp | 37.931 | 3.7931 | TA505 | 166/9 | Completed
2025-11-12 | 2025-11-10 | 2025-11-23 | Prayag Shah Mp | 65.87 | 4.705 | TA505 | 174A/0 | Completed
2025-11-12 | 2025-11-12 | 2025-11-22 | Shila Devi | 36.1598 | 3.2873 | TA505 | 129A/2 | Completed
2025-11-13 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-11-13 | 2025-10-27 | 2025-11-17 | Crane Erc Team Mp | 34.79 | 1.5814 | TA505 | 173/1 | Completed
2025-11-13 | 2025-11-10 | 2025-11-16 | Deglal Mahato | 37.931 | 5.4187 | TA505 | 126/3 | Completed
2025-11-13 | 2025-11-07 | 2025-11-13 | Deglal Mahato Mp | 36.1598 | 5.1657 | TA505 | 170/8 | Completed
2025-11-13 | 2025-11-08 | 2025-11-15 | Jagannaath Saw Mp | 62.444 | 7.8055 | TA505 | 166/0 | Completed
2025-11-13 | 2025-11-11 | 2025-11-22 | Jhemon Mahato 2 | 37.931 | 3.1609 | TA505 | 136/5 | Completed
2025-11-13 | 2025-11-06 | 2025-11-18 | Jwala Singh | 62.444 | 4.8034 | TA505 | 109/0 | Completed
2025-11-13 | 2025-11-04 | 2025-11-13 | Pankaj Singh Mp | 37.931 | 3.7931 | TA505 | 166/9 | Completed
2025-11-13 | 2025-11-10 | 2025-11-23 | Prayag Shah Mp | 65.87 | 4.705 | TA505 | 174A/0 | Completed
2025-11-13 | 2025-11-12 | 2025-11-22 | Shila Devi | 36.1598 | 3.2873 | TA505 | 129A/2 | Completed
2025-11-14 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-11-14 | 2025-10-27 | 2025-11-17 | Crane Erc Team Mp | 34.79 | 1.5814 | TA505 | 173/1 | Completed
2025-11-14 | 2025-11-10 | 2025-11-16 | Deglal Mahato | 37.931 | 5.4187 | TA505 | 126/3 | Completed
2025-11-14 | 2025-11-14 | 2025-11-20 | Deglal Mahato Mp | 36.1598 | 5.1657 | TA505 | 170/7 | Completed
2025-11-14 | 2025-11-08 | 2025-11-15 | Jagannaath Saw Mp | 62.444 | 7.8055 | TA505 | 166/0 | Completed
2025-11-14 | 2025-11-11 | 2025-11-22 | Jhemon Mahato 2 | 37.931 | 3.1609 | TA505 | 136/5 | Completed
2025-11-14 | 2025-11-06 | 2025-11-18 | Jwala Singh | 62.444 | 4.8034 | TA505 | 109/0 | Completed
2025-11-14 | 2025-11-14 | 2025-11-18 | Pankaj Singh Mp | 36.1598 | 7.232 | TA505 | 166/8 | Completed
2025-11-14 | 2025-11-10 | 2025-11-23 | Prayag Shah Mp | 65.87 | 4.705 | TA505 | 174A/0 | Completed
2025-11-14 | 2025-11-12 | 2025-11-22 | Shila Devi | 36.1598 | 3.2873 | TA505 | 129A/2 | Completed
2025-11-15 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-11-15 | 2025-10-27 | 2025-11-17 | Crane Erc Team Mp | 34.79 | 1.5814 | TA505 | 173/1 | Completed
2025-11-15 | 2025-11-10 | 2025-11-16 | Deglal Mahato | 37.931 | 5.4187 | TA505 | 126/3 | Completed
2025-11-15 | 2025-11-14 | 2025-11-20 | Deglal Mahato Mp | 36.1598 | 5.1657 | TA505 | 170/7 | Completed
2025-11-15 | 2025-11-08 | 2025-11-15 | Jagannaath Saw Mp | 62.444 | 7.8055 | TA505 | 166/0 | Completed
2025-11-15 | 2025-11-11 | 2025-11-22 | Jhemon Mahato 2 | 37.931 | 3.1609 | TA505 | 136/5 | Completed
2025-11-15 | 2025-11-06 | 2025-11-18 | Jwala Singh | 62.444 | 4.8034 | TA505 | 109/0 | Completed
2025-11-15 | 2025-11-14 | 2025-11-18 | Pankaj Singh Mp | 36.1598 | 7.232 | TA505 | 166/8 | Completed
2025-11-15 | 2025-11-10 | 2025-11-23 | Prayag Shah Mp | 65.87 | 4.705 | TA505 | 174A/0 | Completed
2025-11-15 | 2025-11-12 | 2025-11-22 | Shila Devi | 36.1598 | 3.2873 | TA505 | 129A/2 | Completed
2025-11-16 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-11-16 | 2025-10-27 | 2025-11-17 | Crane Erc Team Mp | 34.79 | 1.5814 | TA505 | 173/1 | Completed
2025-11-16 | 2025-11-10 | 2025-11-16 | Deglal Mahato | 37.931 | 5.4187 | TA505 | 126/3 | Completed
2025-11-16 | 2025-11-14 | 2025-11-20 | Deglal Mahato Mp | 36.1598 | 5.1657 | TA505 | 170/7 | Completed
2025-11-16 | 2025-11-16 | 2025-11-24 | Jagannaath Saw Mp | 65.028 | 7.2253 | TA505 | 165/0 | Completed
2025-11-16 | 2025-11-11 | 2025-11-22 | Jhemon Mahato 2 | 37.931 | 3.1609 | TA505 | 136/5 | Completed
2025-11-16 | 2025-11-06 | 2025-11-18 | Jwala Singh | 62.444 | 4.8034 | TA505 | 109/0 | Completed
2025-11-16 | 2025-11-14 | 2025-11-18 | Pankaj Singh Mp | 36.1598 | 7.232 | TA505 | 166/8 | Completed
2025-11-16 | 2025-11-10 | 2025-11-23 | Prayag Shah Mp | 65.87 | 4.705 | TA505 | 174A/0 | Completed
2025-11-16 | 2025-11-12 | 2025-11-22 | Shila Devi | 36.1598 | 3.2873 | TA505 | 129A/2 | Completed
2025-11-17 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-11-17 | 2025-10-27 | 2025-11-17 | Crane Erc Team Mp | 34.79 | 1.5814 | TA505 | 173/1 | Completed
2025-11-17 | 2025-11-17 | 2025-11-24 | Deglal Mahato | 37.931 | 4.7414 | TA505 | 114/4 | Completed
2025-11-17 | 2025-11-14 | 2025-11-20 | Deglal Mahato Mp | 36.1598 | 5.1657 | TA505 | 170/7 | Completed
2025-11-17 | 2025-11-16 | 2025-11-24 | Jagannaath Saw Mp | 65.028 | 7.2253 | TA505 | 165/0 | Completed
2025-11-17 | 2025-11-11 | 2025-11-22 | Jhemon Mahato 2 | 37.931 | 3.1609 | TA505 | 136/5 | Completed
2025-11-17 | 2025-11-06 | 2025-11-18 | Jwala Singh | 62.444 | 4.8034 | TA505 | 109/0 | Completed
2025-11-17 | 2025-11-14 | 2025-11-18 | Pankaj Singh Mp | 36.1598 | 7.232 | TA505 | 166/8 | Completed
2025-11-17 | 2025-11-10 | 2025-11-23 | Prayag Shah Mp | 65.87 | 4.705 | TA505 | 174A/0 | Completed
2025-11-17 | 2025-11-12 | 2025-11-22 | Shila Devi | 36.1598 | 3.2873 | TA505 | 129A/2 | Completed
2025-11-18 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-11-18 | 2025-11-17 | 2025-11-24 | Deglal Mahato | 37.931 | 4.7414 | TA505 | 114/4 | Completed
2025-11-18 | 2025-11-14 | 2025-11-20 | Deglal Mahato Mp | 36.1598 | 5.1657 | TA505 | 170/7 | Completed
2025-11-18 | 2025-11-16 | 2025-11-24 | Jagannaath Saw Mp | 65.028 | 7.2253 | TA505 | 165/0 | Completed
2025-11-18 | 2025-11-11 | 2025-11-22 | Jhemon Mahato 2 | 37.931 | 3.1609 | TA505 | 136/5 | Completed
2025-11-18 | 2025-11-06 | 2025-11-18 | Jwala Singh | 62.444 | 4.8034 | TA505 | 109/0 | Completed
2025-11-18 | 2025-11-14 | 2025-11-18 | Pankaj Singh Mp | 36.1598 | 7.232 | TA505 | 166/8 | Completed
2025-11-18 | 2025-11-10 | 2025-11-23 | Prayag Shah Mp | 65.87 | 4.705 | TA505 | 174A/0 | Completed
2025-11-18 | 2025-11-12 | 2025-11-22 | Shila Devi | 36.1598 | 3.2873 | TA505 | 129A/2 | Completed
2025-11-19 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-11-19 | 2025-11-17 | 2025-11-24 | Deglal Mahato | 37.931 | 4.7414 | TA505 | 114/4 | Completed
2025-11-19 | 2025-11-14 | 2025-11-20 | Deglal Mahato Mp | 36.1598 | 5.1657 | TA505 | 170/7 | Completed
2025-11-19 | 2025-11-16 | 2025-11-24 | Jagannaath Saw Mp | 65.028 | 7.2253 | TA505 | 165/0 | Completed
2025-11-19 | 2025-11-11 | 2025-11-22 | Jhemon Mahato 2 | 37.931 | 3.1609 | TA505 | 136/5 | Completed
2025-11-19 | 2025-11-19 | 2025-11-24 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 166/7 | Completed
2025-11-19 | 2025-11-10 | 2025-11-23 | Prayag Shah Mp | 65.87 | 4.705 | TA505 | 174A/0 | Completed
2025-11-19 | 2025-11-12 | 2025-11-22 | Shila Devi | 36.1598 | 3.2873 | TA505 | 129A/2 | Completed
2025-11-20 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-11-20 | 2025-11-17 | 2025-11-24 | Deglal Mahato | 37.931 | 4.7414 | TA505 | 114/4 | Completed
2025-11-20 | 2025-11-14 | 2025-11-20 | Deglal Mahato Mp | 36.1598 | 5.1657 | TA505 | 170/7 | Completed
2025-11-20 | 2025-11-16 | 2025-11-24 | Jagannaath Saw Mp | 65.028 | 7.2253 | TA505 | 165/0 | Completed
2025-11-20 | 2025-11-11 | 2025-11-22 | Jhemon Mahato 2 | 37.931 | 3.1609 | TA505 | 136/5 | Completed
2025-11-20 | 2025-11-19 | 2025-11-24 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 166/7 | Completed
2025-11-20 | 2025-11-10 | 2025-11-23 | Prayag Shah Mp | 65.87 | 4.705 | TA505 | 174A/0 | Completed
2025-11-20 | 2025-11-12 | 2025-11-22 | Shila Devi | 36.1598 | 3.2873 | TA505 | 129A/2 | Completed
2025-11-21 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-11-21 | 2025-11-17 | 2025-11-24 | Deglal Mahato | 37.931 | 4.7414 | TA505 | 114/4 | Completed
2025-11-21 | 2025-11-16 | 2025-11-24 | Jagannaath Saw Mp | 65.028 | 7.2253 | TA505 | 165/0 | Completed
2025-11-21 | 2025-11-11 | 2025-11-22 | Jhemon Mahato 2 | 37.931 | 3.1609 | TA505 | 136/5 | Completed
2025-11-21 | 2025-11-19 | 2025-11-24 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 166/7 | Completed
2025-11-21 | 2025-11-10 | 2025-11-23 | Prayag Shah Mp | 65.87 | 4.705 | TA505 | 174A/0 | Completed
2025-11-21 | 2025-11-12 | 2025-11-22 | Shila Devi | 36.1598 | 3.2873 | TA505 | 129A/2 | Completed
2025-11-22 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-11-22 | 2025-11-17 | 2025-11-24 | Deglal Mahato | 37.931 | 4.7414 | TA505 | 114/4 | Completed
2025-11-22 | 2025-11-16 | 2025-11-24 | Jagannaath Saw Mp | 65.028 | 7.2253 | TA505 | 165/0 | Completed
2025-11-22 | 2025-11-11 | 2025-11-22 | Jhemon Mahato 2 | 37.931 | 3.1609 | TA505 | 136/5 | Completed
2025-11-22 | 2025-11-19 | 2025-11-24 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 166/7 | Completed
2025-11-22 | 2025-11-10 | 2025-11-23 | Prayag Shah Mp | 65.87 | 4.705 | TA505 | 174A/0 | Completed
2025-11-22 | 2025-11-12 | 2025-11-22 | Shila Devi | 36.1598 | 3.2873 | TA505 | 129A/2 | Completed
2025-11-23 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-11-23 | 2025-11-17 | 2025-11-24 | Deglal Mahato | 37.931 | 4.7414 | TA505 | 114/4 | Completed
2025-11-23 | 2025-11-16 | 2025-11-24 | Jagannaath Saw Mp | 65.028 | 7.2253 | TA505 | 165/0 | Completed
2025-11-23 | 2025-11-19 | 2025-11-24 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 166/7 | Completed
2025-11-23 | 2025-11-10 | 2025-11-23 | Prayag Shah Mp | 65.87 | 4.705 | TA505 | 174A/0 | Completed
2025-11-24 | 2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-11-24 | 2025-11-17 | 2025-11-24 | Deglal Mahato | 37.931 | 4.7414 | TA505 | 114/4 | Completed
2025-11-24 | 2025-11-16 | 2025-11-24 | Jagannaath Saw Mp | 65.028 | 7.2253 | TA505 | 165/0 | Completed
2025-11-24 | 2025-11-19 | 2025-11-24 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 166/7 | Completed
2025-08-27 | 2025-08-27 | 2025-09-05 | Shri Karni Construction | 37.2057 | 3.7206 | TA506 | 33/0 | Completed
2025-08-27 | 2025-08-27 | 2025-09-05 | Shri Karni Construction | 34.1664 | 3.4166 | TA506 | 25/0 | Completed
2025-08-27 | 2025-08-27 | 2025-09-01 | Tejal | 16.9667 | 2.8278 | TA506 | 137/2 | Completed
2025-08-28 | 2025-08-27 | 2025-09-05 | Shri Karni Construction | 37.2057 | 3.7206 | TA506 | 33/0 | Completed
2025-08-28 | 2025-08-27 | 2025-09-05 | Shri Karni Construction | 34.1664 | 3.4166 | TA506 | 25/0 | Completed
2025-08-28 | 2025-08-27 | 2025-09-01 | Tejal | 16.9667 | 2.8278 | TA506 | 137/2 | Completed
2025-08-29 | 2025-08-27 | 2025-09-05 | Shri Karni Construction | 37.2057 | 3.7206 | TA506 | 33/0 | Completed
2025-08-29 | 2025-08-27 | 2025-09-05 | Shri Karni Construction | 34.1664 | 3.4166 | TA506 | 25/0 | Completed
2025-08-29 | 2025-08-27 | 2025-09-01 | Tejal | 16.9667 | 2.8278 | TA506 | 137/2 | Completed
2025-08-30 | 2025-08-27 | 2025-09-05 | Shri Karni Construction | 37.2057 | 3.7206 | TA506 | 33/0 | Completed
2025-08-30 | 2025-08-27 | 2025-09-05 | Shri Karni Construction | 34.1664 | 3.4166 | TA506 | 25/0 | Completed
2025-08-30 | 2025-08-27 | 2025-09-01 | Tejal | 16.9667 | 2.8278 | TA506 | 137/2 | Completed
2025-08-31 | 2025-08-31 | 2025-09-04 | Pankaj 1 | 16.9667 | 3.3933 | TA506 | 183/4 | Completed
2025-08-31 | 2025-08-27 | 2025-09-05 | Shri Karni Construction | 37.2057 | 3.7206 | TA506 | 33/0 | Completed
2025-08-31 | 2025-08-27 | 2025-09-05 | Shri Karni Construction | 34.1664 | 3.4166 | TA506 | 25/0 | Completed
2025-08-31 | 2025-08-31 | 2025-09-09 | Shri Karni Construction | 37.2057 | 3.7206 | TA506 | 12/0 | Completed
2025-08-31 | 2025-08-27 | 2025-09-01 | Tejal | 16.9667 | 2.8278 | TA506 | 137/2 | Completed
2025-09-01 | 2025-09-01 | 2025-09-10 | Mohan Mahto | 37.2057 | 3.7206 | TA506 | 68/0 | Completed
2025-09-01 | 2025-08-31 | 2025-09-04 | Pankaj 1 | 16.9667 | 3.3933 | TA506 | 183/4 | Completed
2025-09-01 | 2025-08-27 | 2025-09-05 | Shri Karni Construction | 37.2057 | 3.7206 | TA506 | 33/0 | Completed
2025-09-01 | 2025-08-27 | 2025-09-05 | Shri Karni Construction | 34.1664 | 3.4166 | TA506 | 25/0 | Completed
2025-09-01 | 2025-08-31 | 2025-09-09 | Shri Karni Construction | 37.2057 | 3.7206 | TA506 | 12/0 | Completed
2025-09-01 | 2025-09-01 | 2025-09-05 | Shri Karni Construction | 16.9667 | 3.3933 | TA506 | 13/2 | Completed
2025-09-01 | 2025-08-27 | 2025-09-01 | Tejal | 16.9667 | 2.8278 | TA506 | 137/2 | Completed
2025-09-02 | 2025-09-02 | 2025-09-12 | Govind Mahto | 37.2057 | 3.3823 | TA506 | 223/0 | Completed
2025-09-02 | 2025-09-01 | 2025-09-10 | Mohan Mahto | 37.2057 | 3.7206 | TA506 | 68/0 | Completed
2025-09-02 | 2025-08-31 | 2025-09-04 | Pankaj 1 | 16.9667 | 3.3933 | TA506 | 183/4 | Completed
2025-09-02 | 2025-09-02 | 2025-09-08 | Radhika Enterprises | 27.0921 | 3.8703 | TA506 | 2A/0 | Completed
2025-09-02 | 2025-08-27 | 2025-09-05 | Shri Karni Construction | 37.2057 | 3.7206 | TA506 | 33/0 | Completed
2025-09-02 | 2025-08-27 | 2025-09-05 | Shri Karni Construction | 34.1664 | 3.4166 | TA506 | 25/0 | Completed
2025-09-02 | 2025-08-31 | 2025-09-09 | Shri Karni Construction | 37.2057 | 3.7206 | TA506 | 12/0 | Completed
2025-09-02 | 2025-09-01 | 2025-09-05 | Shri Karni Construction | 16.9667 | 3.3933 | TA506 | 13/2 | Completed
2025-09-02 | 2025-09-02 | 2025-09-12 | Shri Karni Construction | 42.6134 | 3.8739 | TA506 | 22/0 | Completed
2025-09-03 | 2025-09-02 | 2025-09-12 | Govind Mahto | 37.2057 | 3.3823 | TA506 | 223/0 | Completed
2025-09-03 | 2025-09-01 | 2025-09-10 | Mohan Mahto | 37.2057 | 3.7206 | TA506 | 68/0 | Completed
2025-09-03 | 2025-08-31 | 2025-09-04 | Pankaj 1 | 16.9667 | 3.3933 | TA506 | 183/4 | Completed
2025-09-03 | 2025-09-02 | 2025-09-08 | Radhika Enterprises | 27.0921 | 3.8703 | TA506 | 2A/0 | Completed
2025-09-03 | 2025-08-27 | 2025-09-05 | Shri Karni Construction | 37.2057 | 3.7206 | TA506 | 33/0 | Completed
2025-09-03 | 2025-08-27 | 2025-09-05 | Shri Karni Construction | 34.1664 | 3.4166 | TA506 | 25/0 | Completed
2025-09-03 | 2025-08-31 | 2025-09-09 | Shri Karni Construction | 37.2057 | 3.7206 | TA506 | 12/0 | Completed
2025-09-03 | 2025-09-01 | 2025-09-05 | Shri Karni Construction | 16.9667 | 3.3933 | TA506 | 13/2 | Completed
2025-09-03 | 2025-09-02 | 2025-09-12 | Shri Karni Construction | 42.6134 | 3.8739 | TA506 | 22/0 | Completed
2025-09-03 | 2025-09-03 | 2025-09-12 | Tejal | 31.8647 | 3.1865 | TA506 | 141/0 | Completed
2025-09-04 | 2025-09-02 | 2025-09-12 | Govind Mahto | 37.2057 | 3.3823 | TA506 | 223/0 | Completed
2025-09-04 | 2025-09-01 | 2025-09-10 | Mohan Mahto | 37.2057 | 3.7206 | TA506 | 68/0 | Completed
2025-09-04 | 2025-08-31 | 2025-09-04 | Pankaj 1 | 16.9667 | 3.3933 | TA506 | 183/4 | Completed
2025-09-04 | 2025-09-04 | 2025-09-11 | Pankaj 1 | 42.6134 | 5.3267 | TA506 | 184/0 | Completed
2025-09-04 | 2025-09-02 | 2025-09-08 | Radhika Enterprises | 27.0921 | 3.8703 | TA506 | 2A/0 | Completed
2025-09-04 | 2025-08-27 | 2025-09-05 | Shri Karni Construction | 37.2057 | 3.7206 | TA506 | 33/0 | Completed
2025-09-04 | 2025-08-27 | 2025-09-05 | Shri Karni Construction | 34.1664 | 3.4166 | TA506 | 25/0 | Completed
2025-09-04 | 2025-08-31 | 2025-09-09 | Shri Karni Construction | 37.2057 | 3.7206 | TA506 | 12/0 | Completed
2025-09-04 | 2025-09-01 | 2025-09-05 | Shri Karni Construction | 16.9667 | 3.3933 | TA506 | 13/2 | Completed
2025-09-04 | 2025-09-02 | 2025-09-12 | Shri Karni Construction | 42.6134 | 3.8739 | TA506 | 22/0 | Completed
2025-09-04 | 2025-09-04 | 2025-09-08 | Shri Karni Construction | 21.0969 | 4.2194 | TA506 | 18/7 | Completed
2025-09-04 | 2025-09-03 | 2025-09-12 | Tejal | 31.8647 | 3.1865 | TA506 | 141/0 | Completed
2025-09-05 | 2025-09-02 | 2025-09-12 | Govind Mahto | 37.2057 | 3.3823 | TA506 | 223/0 | Completed
2025-09-05 | 2025-09-01 | 2025-09-10 | Mohan Mahto | 37.2057 | 3.7206 | TA506 | 68/0 | Completed
2025-09-05 | 2025-09-04 | 2025-09-11 | Pankaj 1 | 42.6134 | 5.3267 | TA506 | 184/0 | Completed
2025-09-05 | 2025-09-02 | 2025-09-08 | Radhika Enterprises | 27.0921 | 3.8703 | TA506 | 2A/0 | Completed
2025-09-05 | 2025-08-27 | 2025-09-05 | Shri Karni Construction | 37.2057 | 3.7206 | TA506 | 33/0 | Completed
2025-09-05 | 2025-08-27 | 2025-09-05 | Shri Karni Construction | 34.1664 | 3.4166 | TA506 | 25/0 | Completed
2025-09-05 | 2025-08-31 | 2025-09-09 | Shri Karni Construction | 37.2057 | 3.7206 | TA506 | 12/0 | Completed
2025-09-05 | 2025-09-01 | 2025-09-05 | Shri Karni Construction | 16.9667 | 3.3933 | TA506 | 13/2 | Completed
2025-09-05 | 2025-09-02 | 2025-09-12 | Shri Karni Construction | 42.6134 | 3.8739 | TA506 | 22/0 | Completed
2025-09-05 | 2025-09-04 | 2025-09-08 | Shri Karni Construction | 21.0969 | 4.2194 | TA506 | 18/7 | Completed
2025-09-05 | 2025-09-03 | 2025-09-12 | Tejal | 31.8647 | 3.1865 | TA506 | 141/0 | Completed
2025-09-06 | 2025-09-06 | 2025-09-11 | Fatima 1 | 27.0921 | 4.5154 | TA506 | 6/0 | Completed
2025-09-06 | 2025-09-02 | 2025-09-12 | Govind Mahto | 37.2057 | 3.3823 | TA506 | 223/0 | Completed
2025-09-06 | 2025-09-01 | 2025-09-10 | Mohan Mahto | 37.2057 | 3.7206 | TA506 | 68/0 | Completed
2025-09-06 | 2025-09-04 | 2025-09-11 | Pankaj 1 | 42.6134 | 5.3267 | TA506 | 184/0 | Completed
2025-09-06 | 2025-09-06 | 2025-09-15 | Pankaj 2 | 38.1379 | 3.8138 | TA506 | 218/0 | Completed
2025-09-06 | 2025-09-02 | 2025-09-08 | Radhika Enterprises | 27.0921 | 3.8703 | TA506 | 2A/0 | Completed
2025-09-06 | 2025-08-31 | 2025-09-09 | Shri Karni Construction | 37.2057 | 3.7206 | TA506 | 12/0 | Completed
2025-09-06 | 2025-09-02 | 2025-09-12 | Shri Karni Construction | 42.6134 | 3.8739 | TA506 | 22/0 | Completed
2025-09-06 | 2025-09-04 | 2025-09-08 | Shri Karni Construction | 21.0969 | 4.2194 | TA506 | 18/7 | Completed
2025-09-06 | 2025-09-06 | 2025-09-11 | Shri Karni Construction | 18.1188 | 3.0198 | TA506 | 2/4 | Completed
2025-09-06 | 2025-09-03 | 2025-09-12 | Tejal | 31.8647 | 3.1865 | TA506 | 141/0 | Completed
2025-09-07 | 2025-09-06 | 2025-09-11 | Fatima 1 | 27.0921 | 4.5154 | TA506 | 6/0 | Completed
2025-09-07 | 2025-09-02 | 2025-09-12 | Govind Mahto | 37.2057 | 3.3823 | TA506 | 223/0 | Completed
2025-09-07 | 2025-09-01 | 2025-09-10 | Mohan Mahto | 37.2057 | 3.7206 | TA506 | 68/0 | Completed
2025-09-07 | 2025-09-04 | 2025-09-11 | Pankaj 1 | 42.6134 | 5.3267 | TA506 | 184/0 | Completed
2025-09-07 | 2025-09-06 | 2025-09-15 | Pankaj 2 | 38.1379 | 3.8138 | TA506 | 218/0 | Completed
2025-09-07 | 2025-09-02 | 2025-09-08 | Radhika Enterprises | 27.0921 | 3.8703 | TA506 | 2A/0 | Completed
2025-09-07 | 2025-08-31 | 2025-09-09 | Shri Karni Construction | 37.2057 | 3.7206 | TA506 | 12/0 | Completed
2025-09-07 | 2025-09-02 | 2025-09-12 | Shri Karni Construction | 42.6134 | 3.8739 | TA506 | 22/0 | Completed
2025-09-07 | 2025-09-04 | 2025-09-08 | Shri Karni Construction | 21.0969 | 4.2194 | TA506 | 18/7 | Completed
2025-09-07 | 2025-09-06 | 2025-09-11 | Shri Karni Construction | 18.1188 | 3.0198 | TA506 | 2/4 | Completed
2025-09-07 | 2025-09-07 | 2025-09-11 | Shri Karni Construction | 18.1188 | 3.6238 | TA506 | 13/3 | Completed
2025-09-07 | 2025-09-03 | 2025-09-12 | Tejal | 31.8647 | 3.1865 | TA506 | 141/0 | Completed
2025-09-07 | 2025-09-07 | 2025-09-11 | Vinod | 18.1188 | 3.6238 | TA506 | 163/2 | Completed
2025-09-08 | 2025-09-06 | 2025-09-11 | Fatima 1 | 27.0921 | 4.5154 | TA506 | 6/0 | Completed
2025-09-08 | 2025-09-02 | 2025-09-12 | Govind Mahto | 37.2057 | 3.3823 | TA506 | 223/0 | Completed
2025-09-08 | 2025-09-01 | 2025-09-10 | Mohan Mahto | 37.2057 | 3.7206 | TA506 | 68/0 | Completed
2025-09-08 | 2025-09-08 | 2025-09-20 | Mohan Mahto | 48.342 | 3.7186 | TA506 | 27/0 | Completed
2025-09-08 | 2025-09-04 | 2025-09-11 | Pankaj 1 | 42.6134 | 5.3267 | TA506 | 184/0 | Completed
2025-09-08 | 2025-09-06 | 2025-09-15 | Pankaj 2 | 38.1379 | 3.8138 | TA506 | 218/0 | Completed
2025-09-08 | 2025-09-02 | 2025-09-08 | Radhika Enterprises | 27.0921 | 3.8703 | TA506 | 2A/0 | Completed
2025-09-08 | 2025-08-31 | 2025-09-09 | Shri Karni Construction | 37.2057 | 3.7206 | TA506 | 12/0 | Completed
2025-09-08 | 2025-09-02 | 2025-09-12 | Shri Karni Construction | 42.6134 | 3.8739 | TA506 | 22/0 | Completed
2025-09-08 | 2025-09-04 | 2025-09-08 | Shri Karni Construction | 21.0969 | 4.2194 | TA506 | 18/7 | Completed
2025-09-08 | 2025-09-06 | 2025-09-11 | Shri Karni Construction | 18.1188 | 3.0198 | TA506 | 2/4 | Completed
2025-09-08 | 2025-09-07 | 2025-09-11 | Shri Karni Construction | 18.1188 | 3.6238 | TA506 | 13/3 | Completed
2025-09-08 | 2025-09-03 | 2025-09-12 | Tejal | 31.8647 | 3.1865 | TA506 | 141/0 | Completed
2025-09-08 | 2025-09-07 | 2025-09-11 | Vinod | 18.1188 | 3.6238 | TA506 | 163/2 | Completed
2025-09-09 | 2025-09-06 | 2025-09-11 | Fatima 1 | 27.0921 | 4.5154 | TA506 | 6/0 | Completed
2025-09-09 | 2025-09-02 | 2025-09-12 | Govind Mahto | 37.2057 | 3.3823 | TA506 | 223/0 | Completed
2025-09-09 | 2025-09-09 | 2025-09-17 | Jay Prakash | 34.1664 | 3.7963 | TA506 | 76A/1 | Completed
2025-09-09 | 2025-09-01 | 2025-09-10 | Mohan Mahto | 37.2057 | 3.7206 | TA506 | 68/0 | Completed
2025-09-09 | 2025-09-08 | 2025-09-20 | Mohan Mahto | 48.342 | 3.7186 | TA506 | 27/0 | Completed
2025-09-09 | 2025-09-04 | 2025-09-11 | Pankaj 1 | 42.6134 | 5.3267 | TA506 | 184/0 | Completed
2025-09-09 | 2025-09-06 | 2025-09-15 | Pankaj 2 | 38.1379 | 3.8138 | TA506 | 218/0 | Completed
2025-09-09 | 2025-08-31 | 2025-09-09 | Shri Karni Construction | 37.2057 | 3.7206 | TA506 | 12/0 | Completed
2025-09-09 | 2025-09-02 | 2025-09-12 | Shri Karni Construction | 42.6134 | 3.8739 | TA506 | 22/0 | Completed
2025-09-09 | 2025-09-06 | 2025-09-11 | Shri Karni Construction | 18.1188 | 3.0198 | TA506 | 2/4 | Completed
2025-09-09 | 2025-09-07 | 2025-09-11 | Shri Karni Construction | 18.1188 | 3.6238 | TA506 | 13/3 | Completed
2025-09-09 | 2025-09-09 | 2025-09-13 | Shri Karni Construction | 18.1188 | 3.6238 | TA506 | 18/8 | Completed
2025-09-09 | 2025-09-03 | 2025-09-12 | Tejal | 31.8647 | 3.1865 | TA506 | 141/0 | Completed
2025-09-09 | 2025-09-07 | 2025-09-11 | Vinod | 18.1188 | 3.6238 | TA506 | 163/2 | Completed
2025-09-10 | 2025-09-06 | 2025-09-11 | Fatima 1 | 27.0921 | 4.5154 | TA506 | 6/0 | Completed
2025-09-10 | 2025-09-02 | 2025-09-12 | Govind Mahto | 37.2057 | 3.3823 | TA506 | 223/0 | Completed
2025-09-10 | 2025-09-10 | 2025-09-14 | Horil | 27.0921 | 5.4184 | TA506 | 191/0 | Completed
2025-09-10 | 2025-09-09 | 2025-09-17 | Jay Prakash | 34.1664 | 3.7963 | TA506 | 76A/1 | Completed
2025-09-10 | 2025-09-01 | 2025-09-10 | Mohan Mahto | 37.2057 | 3.7206 | TA506 | 68/0 | Completed
2025-09-10 | 2025-09-08 | 2025-09-20 | Mohan Mahto | 48.342 | 3.7186 | TA506 | 27/0 | Completed
2025-09-10 | 2025-09-04 | 2025-09-11 | Pankaj 1 | 42.6134 | 5.3267 | TA506 | 184/0 | Completed
2025-09-10 | 2025-09-10 | 2025-09-24 | Pankaj 1 | 39.5967 | 2.6398 | TA506 | 186/0 | Completed
2025-09-10 | 2025-09-06 | 2025-09-15 | Pankaj 2 | 38.1379 | 3.8138 | TA506 | 218/0 | Completed
2025-09-10 | 2025-09-02 | 2025-09-12 | Shri Karni Construction | 42.6134 | 3.8739 | TA506 | 22/0 | Completed
2025-09-10 | 2025-09-06 | 2025-09-11 | Shri Karni Construction | 18.1188 | 3.0198 | TA506 | 2/4 | Completed
2025-09-10 | 2025-09-07 | 2025-09-11 | Shri Karni Construction | 18.1188 | 3.6238 | TA506 | 13/3 | Completed
2025-09-10 | 2025-09-09 | 2025-09-13 | Shri Karni Construction | 18.1188 | 3.6238 | TA506 | 18/8 | Completed
2025-09-10 | 2025-09-10 | 2025-09-15 | Shri Karni Construction | 18.1188 | 3.0198 | TA506 | 5/3 | Completed
2025-09-10 | 2025-09-03 | 2025-09-12 | Tejal | 31.8647 | 3.1865 | TA506 | 141/0 | Completed
2025-09-10 | 2025-09-07 | 2025-09-11 | Vinod | 18.1188 | 3.6238 | TA506 | 163/2 | Completed
2025-09-11 | 2025-09-06 | 2025-09-11 | Fatima 1 | 27.0921 | 4.5154 | TA506 | 6/0 | Completed
2025-09-11 | 2025-09-02 | 2025-09-12 | Govind Mahto | 37.2057 | 3.3823 | TA506 | 223/0 | Completed
2025-09-11 | 2025-09-10 | 2025-09-14 | Horil | 27.0921 | 5.4184 | TA506 | 191/0 | Completed
2025-09-11 | 2025-09-09 | 2025-09-17 | Jay Prakash | 34.1664 | 3.7963 | TA506 | 76A/1 | Completed
2025-09-11 | 2025-09-08 | 2025-09-20 | Mohan Mahto | 48.342 | 3.7186 | TA506 | 27/0 | Completed
2025-09-11 | 2025-09-04 | 2025-09-11 | Pankaj 1 | 42.6134 | 5.3267 | TA506 | 184/0 | Completed
2025-09-11 | 2025-09-10 | 2025-09-24 | Pankaj 1 | 39.5967 | 2.6398 | TA506 | 186/0 | Completed
2025-09-11 | 2025-09-06 | 2025-09-15 | Pankaj 2 | 38.1379 | 3.8138 | TA506 | 218/0 | Completed
2025-09-11 | 2025-09-02 | 2025-09-12 | Shri Karni Construction | 42.6134 | 3.8739 | TA506 | 22/0 | Completed
2025-09-11 | 2025-09-06 | 2025-09-11 | Shri Karni Construction | 18.1188 | 3.0198 | TA506 | 2/4 | Completed
2025-09-11 | 2025-09-07 | 2025-09-11 | Shri Karni Construction | 18.1188 | 3.6238 | TA506 | 13/3 | Completed
2025-09-11 | 2025-09-09 | 2025-09-13 | Shri Karni Construction | 18.1188 | 3.6238 | TA506 | 18/8 | Completed
2025-09-11 | 2025-09-10 | 2025-09-15 | Shri Karni Construction | 18.1188 | 3.0198 | TA506 | 5/3 | Completed
2025-09-11 | 2025-09-11 | 2025-09-15 | Shri Karni Construction | 16.9667 | 3.3933 | TA506 | 11/1 | Completed
2025-09-11 | 2025-09-03 | 2025-09-12 | Tejal | 31.8647 | 3.1865 | TA506 | 141/0 | Completed
2025-09-11 | 2025-09-07 | 2025-09-11 | Vinod | 18.1188 | 3.6238 | TA506 | 163/2 | Completed
2025-09-12 | 2025-09-02 | 2025-09-12 | Govind Mahto | 37.2057 | 3.3823 | TA506 | 223/0 | Completed
2025-09-12 | 2025-09-10 | 2025-09-14 | Horil | 27.0921 | 5.4184 | TA506 | 191/0 | Completed
2025-09-12 | 2025-09-09 | 2025-09-17 | Jay Prakash | 34.1664 | 3.7963 | TA506 | 76A/1 | Completed
2025-09-12 | 2025-09-08 | 2025-09-20 | Mohan Mahto | 48.342 | 3.7186 | TA506 | 27/0 | Completed
2025-09-12 | 2025-09-10 | 2025-09-24 | Pankaj 1 | 39.5967 | 2.6398 | TA506 | 186/0 | Completed
2025-09-12 | 2025-09-06 | 2025-09-15 | Pankaj 2 | 38.1379 | 3.8138 | TA506 | 218/0 | Completed
2025-09-12 | 2025-09-02 | 2025-09-12 | Shri Karni Construction | 42.6134 | 3.8739 | TA506 | 22/0 | Completed
2025-09-12 | 2025-09-09 | 2025-09-13 | Shri Karni Construction | 18.1188 | 3.6238 | TA506 | 18/8 | Completed
2025-09-12 | 2025-09-10 | 2025-09-15 | Shri Karni Construction | 18.1188 | 3.0198 | TA506 | 5/3 | Completed
2025-09-12 | 2025-09-11 | 2025-09-15 | Shri Karni Construction | 16.9667 | 3.3933 | TA506 | 11/1 | Completed
2025-09-12 | 2025-09-03 | 2025-09-12 | Tejal | 31.8647 | 3.1865 | TA506 | 141/0 | Completed
2025-09-12 | 2025-09-12 | 2025-09-18 | Tejal | 16.9667 | 2.4238 | TA506 | 141/1 | Completed
2025-09-13 | 2025-09-10 | 2025-09-14 | Horil | 27.0921 | 5.4184 | TA506 | 191/0 | Completed
2025-09-13 | 2025-09-09 | 2025-09-17 | Jay Prakash | 34.1664 | 3.7963 | TA506 | 76A/1 | Completed
2025-09-13 | 2025-09-08 | 2025-09-20 | Mohan Mahto | 48.342 | 3.7186 | TA506 | 27/0 | Completed
2025-09-13 | 2025-09-13 | 2025-09-17 | Mohan Mahto | 22.4884 | 4.4977 | TA506 | 72/2 | Completed
2025-09-13 | 2025-09-10 | 2025-09-24 | Pankaj 1 | 39.5967 | 2.6398 | TA506 | 186/0 | Completed
2025-09-13 | 2025-09-06 | 2025-09-15 | Pankaj 2 | 38.1379 | 3.8138 | TA506 | 218/0 | Completed
2025-09-13 | 2025-09-09 | 2025-09-13 | Shri Karni Construction | 18.1188 | 3.6238 | TA506 | 18/8 | Completed
2025-09-13 | 2025-09-10 | 2025-09-15 | Shri Karni Construction | 18.1188 | 3.0198 | TA506 | 5/3 | Completed
2025-09-13 | 2025-09-11 | 2025-09-15 | Shri Karni Construction | 16.9667 | 3.3933 | TA506 | 11/1 | Completed
2025-09-13 | 2025-09-12 | 2025-09-18 | Tejal | 16.9667 | 2.4238 | TA506 | 141/1 | Completed
2025-09-14 | 2025-09-10 | 2025-09-14 | Horil | 27.0921 | 5.4184 | TA506 | 191/0 | Completed
2025-09-14 | 2025-09-14 | 2025-09-19 | Horil | 31.8647 | 5.3108 | TA506 | 194/0 | Completed
2025-09-14 | 2025-09-09 | 2025-09-17 | Jay Prakash | 34.1664 | 3.7963 | TA506 | 76A/1 | Completed
2025-09-14 | 2025-09-08 | 2025-09-20 | Mohan Mahto | 48.342 | 3.7186 | TA506 | 27/0 | Completed
2025-09-14 | 2025-09-13 | 2025-09-17 | Mohan Mahto | 22.4884 | 4.4977 | TA506 | 72/2 | Completed
2025-09-14 | 2025-09-10 | 2025-09-24 | Pankaj 1 | 39.5967 | 2.6398 | TA506 | 186/0 | Completed
2025-09-14 | 2025-09-06 | 2025-09-15 | Pankaj 2 | 38.1379 | 3.8138 | TA506 | 218/0 | Completed
2025-09-14 | 2025-09-14 | 2025-09-27 | Pankaj 2 | 29.7779 | 2.127 | TA506 | 214/0 | Completed
2025-09-14 | 2025-09-10 | 2025-09-15 | Shri Karni Construction | 18.1188 | 3.0198 | TA506 | 5/3 | Completed
2025-09-14 | 2025-09-11 | 2025-09-15 | Shri Karni Construction | 16.9667 | 3.3933 | TA506 | 11/1 | Completed
2025-09-14 | 2025-09-14 | 2025-09-18 | Shri Karni Construction | 21.0969 | 4.2194 | TA506 | 2/3 | Completed
2025-09-14 | 2025-09-12 | 2025-09-18 | Tejal | 16.9667 | 2.4238 | TA506 | 141/1 | Completed
2025-09-14 | 2025-09-14 | 2025-09-25 | Vinod | 42.6134 | 3.5511 | TA506 | 166/0 | Completed
2025-09-15 | 2025-09-14 | 2025-09-19 | Horil | 31.8647 | 5.3108 | TA506 | 194/0 | Completed
2025-09-15 | 2025-09-09 | 2025-09-17 | Jay Prakash | 34.1664 | 3.7963 | TA506 | 76A/1 | Completed
2025-09-15 | 2025-09-08 | 2025-09-20 | Mohan Mahto | 48.342 | 3.7186 | TA506 | 27/0 | Completed
2025-09-15 | 2025-09-13 | 2025-09-17 | Mohan Mahto | 22.4884 | 4.4977 | TA506 | 72/2 | Completed
2025-09-15 | 2025-09-10 | 2025-09-24 | Pankaj 1 | 39.5967 | 2.6398 | TA506 | 186/0 | Completed
2025-09-15 | 2025-09-06 | 2025-09-15 | Pankaj 2 | 38.1379 | 3.8138 | TA506 | 218/0 | Completed
2025-09-15 | 2025-09-14 | 2025-09-27 | Pankaj 2 | 29.7779 | 2.127 | TA506 | 214/0 | Completed
2025-09-15 | 2025-09-10 | 2025-09-15 | Shri Karni Construction | 18.1188 | 3.0198 | TA506 | 5/3 | Completed
2025-09-15 | 2025-09-11 | 2025-09-15 | Shri Karni Construction | 16.9667 | 3.3933 | TA506 | 11/1 | Completed
2025-09-15 | 2025-09-14 | 2025-09-18 | Shri Karni Construction | 21.0969 | 4.2194 | TA506 | 2/3 | Completed
2025-09-15 | 2025-09-15 | 2025-09-18 | Shri Karni Construction | 16.9667 | 4.2417 | TA506 | 26/1 | Completed
2025-09-15 | 2025-09-15 | 2025-09-20 | Shri Karni Construction | 21.0969 | 3.5162 | TA506 | 6/1 | Completed
2025-09-15 | 2025-09-15 | 2025-09-21 | Shri Karni Construction | 27.0921 | 3.8703 | TA506 | 19/0 | Completed
2025-09-15 | 2025-09-15 | 2025-09-18 | Shri Karni Construction | 22.4884 | 5.6221 | TA506 | 19/1 | Completed
2025-09-15 | 2025-09-12 | 2025-09-18 | Tejal | 16.9667 | 2.4238 | TA506 | 141/1 | Completed
2025-09-15 | 2025-09-14 | 2025-09-25 | Vinod | 42.6134 | 3.5511 | TA506 | 166/0 | Completed
2025-09-16 | 2025-09-16 | 2025-09-20 | Fatima | 21.0969 | 4.2194 | TA506 | 10/1 | Completed
2025-09-16 | 2025-09-16 | 2025-09-21 | Govind Mahto | 22.4884 | 3.7481 | TA506 | 220/4 | Completed
2025-09-16 | 2025-09-14 | 2025-09-19 | Horil | 31.8647 | 5.3108 | TA506 | 194/0 | Completed
2025-09-16 | 2025-09-09 | 2025-09-17 | Jay Prakash | 34.1664 | 3.7963 | TA506 | 76A/1 | Completed
2025-09-16 | 2025-09-16 | 2025-09-18 | Khemlal | 18.1188 | 6.0396 | TA506 | 220/1 | Completed
2025-09-16 | 2025-09-08 | 2025-09-20 | Mohan Mahto | 48.342 | 3.7186 | TA506 | 27/0 | Completed
2025-09-16 | 2025-09-13 | 2025-09-17 | Mohan Mahto | 22.4884 | 4.4977 | TA506 | 72/2 | Completed
2025-09-16 | 2025-09-10 | 2025-09-24 | Pankaj 1 | 39.5967 | 2.6398 | TA506 | 186/0 | Completed
2025-09-16 | 2025-09-14 | 2025-09-27 | Pankaj 2 | 29.7779 | 2.127 | TA506 | 214/0 | Completed
2025-09-16 | 2025-09-14 | 2025-09-18 | Shri Karni Construction | 21.0969 | 4.2194 | TA506 | 2/3 | Completed
2025-09-16 | 2025-09-15 | 2025-09-18 | Shri Karni Construction | 16.9667 | 4.2417 | TA506 | 26/1 | Completed
2025-09-16 | 2025-09-15 | 2025-09-20 | Shri Karni Construction | 21.0969 | 3.5162 | TA506 | 6/1 | Completed
2025-09-16 | 2025-09-15 | 2025-09-21 | Shri Karni Construction | 27.0921 | 3.8703 | TA506 | 19/0 | Completed
2025-09-16 | 2025-09-15 | 2025-09-18 | Shri Karni Construction | 22.4884 | 5.6221 | TA506 | 19/1 | Completed
2025-09-16 | 2025-09-16 | 2025-09-20 | Shri Karni Construction | 16.9667 | 3.3933 | TA506 | 12/3 | Completed
2025-09-16 | 2025-09-12 | 2025-09-18 | Tejal | 16.9667 | 2.4238 | TA506 | 141/1 | Completed
2025-09-16 | 2025-09-14 | 2025-09-25 | Vinod | 42.6134 | 3.5511 | TA506 | 166/0 | Completed
2025-09-17 | 2025-09-16 | 2025-09-20 | Fatima | 21.0969 | 4.2194 | TA506 | 10/1 | Completed
2025-09-17 | 2025-09-16 | 2025-09-21 | Govind Mahto | 22.4884 | 3.7481 | TA506 | 220/4 | Completed
2025-09-17 | 2025-09-14 | 2025-09-19 | Horil | 31.8647 | 5.3108 | TA506 | 194/0 | Completed
2025-09-17 | 2025-09-09 | 2025-09-17 | Jay Prakash | 34.1664 | 3.7963 | TA506 | 76A/1 | Completed
2025-09-17 | 2025-09-16 | 2025-09-18 | Khemlal | 18.1188 | 6.0396 | TA506 | 220/1 | Completed
2025-09-17 | 2025-09-17 | 2025-09-22 | Khemlal | 21.0969 | 3.5162 | TA506 | 212/5 | Completed
2025-09-17 | 2025-09-08 | 2025-09-20 | Mohan Mahto | 48.342 | 3.7186 | TA506 | 27/0 | Completed
2025-09-17 | 2025-09-13 | 2025-09-17 | Mohan Mahto | 22.4884 | 4.4977 | TA506 | 72/2 | Completed
2025-09-17 | 2025-09-10 | 2025-09-24 | Pankaj 1 | 39.5967 | 2.6398 | TA506 | 186/0 | Completed
2025-09-17 | 2025-09-14 | 2025-09-27 | Pankaj 2 | 29.7779 | 2.127 | TA506 | 214/0 | Completed
2025-09-17 | 2025-09-14 | 2025-09-18 | Shri Karni Construction | 21.0969 | 4.2194 | TA506 | 2/3 | Completed
2025-09-17 | 2025-09-15 | 2025-09-18 | Shri Karni Construction | 16.9667 | 4.2417 | TA506 | 26/1 | Completed
2025-09-17 | 2025-09-15 | 2025-09-20 | Shri Karni Construction | 21.0969 | 3.5162 | TA506 | 6/1 | Completed
2025-09-17 | 2025-09-15 | 2025-09-21 | Shri Karni Construction | 27.0921 | 3.8703 | TA506 | 19/0 | Completed
2025-09-17 | 2025-09-15 | 2025-09-18 | Shri Karni Construction | 22.4884 | 5.6221 | TA506 | 19/1 | Completed
2025-09-17 | 2025-09-16 | 2025-09-20 | Shri Karni Construction | 16.9667 | 3.3933 | TA506 | 12/3 | Completed
2025-09-17 | 2025-09-12 | 2025-09-18 | Tejal | 16.9667 | 2.4238 | TA506 | 141/1 | Completed
2025-09-17 | 2025-09-14 | 2025-09-25 | Vinod | 42.6134 | 3.5511 | TA506 | 166/0 | Completed
2025-09-18 | 2025-09-18 | 2025-09-22 | A B Const Birendra Panday | 16.9667 | 3.3933 | TA506 | 100/2 | Completed
2025-09-18 | 2025-09-16 | 2025-09-20 | Fatima | 21.0969 | 4.2194 | TA506 | 10/1 | Completed
2025-09-18 | 2025-09-16 | 2025-09-21 | Govind Mahto | 22.4884 | 3.7481 | TA506 | 220/4 | Completed
2025-09-18 | 2025-09-14 | 2025-09-19 | Horil | 31.8647 | 5.3108 | TA506 | 194/0 | Completed
2025-09-18 | 2025-09-16 | 2025-09-18 | Khemlal | 18.1188 | 6.0396 | TA506 | 220/1 | Completed
2025-09-18 | 2025-09-17 | 2025-09-22 | Khemlal | 21.0969 | 3.5162 | TA506 | 212/5 | Completed
2025-09-18 | 2025-09-08 | 2025-09-20 | Mohan Mahto | 48.342 | 3.7186 | TA506 | 27/0 | Completed
2025-09-18 | 2025-09-18 | 2025-09-21 | Mohan Mahto | 18.1188 | 4.5297 | TA506 | 66/1 | Completed
2025-09-18 | 2025-09-10 | 2025-09-24 | Pankaj 1 | 39.5967 | 2.6398 | TA506 | 186/0 | Completed
2025-09-18 | 2025-09-14 | 2025-09-27 | Pankaj 2 | 29.7779 | 2.127 | TA506 | 214/0 | Completed
2025-09-18 | 2025-09-14 | 2025-09-18 | Shri Karni Construction | 21.0969 | 4.2194 | TA506 | 2/3 | Completed
2025-09-18 | 2025-09-15 | 2025-09-18 | Shri Karni Construction | 16.9667 | 4.2417 | TA506 | 26/1 | Completed
2025-09-18 | 2025-09-15 | 2025-09-20 | Shri Karni Construction | 21.0969 | 3.5162 | TA506 | 6/1 | Completed
2025-09-18 | 2025-09-15 | 2025-09-21 | Shri Karni Construction | 27.0921 | 3.8703 | TA506 | 19/0 | Completed
2025-09-18 | 2025-09-15 | 2025-09-18 | Shri Karni Construction | 22.4884 | 5.6221 | TA506 | 19/1 | Completed
2025-09-18 | 2025-09-16 | 2025-09-20 | Shri Karni Construction | 16.9667 | 3.3933 | TA506 | 12/3 | Completed
2025-09-18 | 2025-09-18 | 2025-09-22 | Shri Karni Construction | 18.1188 | 3.6238 | TA506 | 60/2 | Completed
2025-09-18 | 2025-09-12 | 2025-09-18 | Tejal | 16.9667 | 2.4238 | TA506 | 141/1 | Completed
2025-09-18 | 2025-09-14 | 2025-09-25 | Vinod | 42.6134 | 3.5511 | TA506 | 166/0 | Completed
2025-09-19 | 2025-09-18 | 2025-09-22 | A B Const Birendra Panday | 16.9667 | 3.3933 | TA506 | 100/2 | Completed
2025-09-19 | 2025-09-16 | 2025-09-20 | Fatima | 21.0969 | 4.2194 | TA506 | 10/1 | Completed
2025-09-19 | 2025-09-16 | 2025-09-21 | Govind Mahto | 22.4884 | 3.7481 | TA506 | 220/4 | Completed
2025-09-19 | 2025-09-14 | 2025-09-19 | Horil | 31.8647 | 5.3108 | TA506 | 194/0 | Completed
2025-09-19 | 2025-09-17 | 2025-09-22 | Khemlal | 21.0969 | 3.5162 | TA506 | 212/5 | Completed
2025-09-19 | 2025-09-08 | 2025-09-20 | Mohan Mahto | 48.342 | 3.7186 | TA506 | 27/0 | Completed
2025-09-19 | 2025-09-18 | 2025-09-21 | Mohan Mahto | 18.1188 | 4.5297 | TA506 | 66/1 | Completed
2025-09-19 | 2025-09-10 | 2025-09-24 | Pankaj 1 | 39.5967 | 2.6398 | TA506 | 186/0 | Completed
2025-09-19 | 2025-09-14 | 2025-09-27 | Pankaj 2 | 29.7779 | 2.127 | TA506 | 214/0 | Completed
2025-09-19 | 2025-09-15 | 2025-09-20 | Shri Karni Construction | 21.0969 | 3.5162 | TA506 | 6/1 | Completed
2025-09-19 | 2025-09-15 | 2025-09-21 | Shri Karni Construction | 27.0921 | 3.8703 | TA506 | 19/0 | Completed
2025-09-19 | 2025-09-16 | 2025-09-20 | Shri Karni Construction | 16.9667 | 3.3933 | TA506 | 12/3 | Completed
2025-09-19 | 2025-09-18 | 2025-09-22 | Shri Karni Construction | 18.1188 | 3.6238 | TA506 | 60/2 | Completed
2025-09-19 | 2025-09-19 | 2025-09-24 | Shri Karni Construction | 21.0969 | 3.5162 | TA506 | 2/2 | Completed
2025-09-19 | 2025-09-14 | 2025-09-25 | Vinod | 42.6134 | 3.5511 | TA506 | 166/0 | Completed
2025-09-20 | 2025-09-18 | 2025-09-22 | A B Const Birendra Panday | 16.9667 | 3.3933 | TA506 | 100/2 | Completed
2025-09-20 | 2025-09-16 | 2025-09-20 | Fatima | 21.0969 | 4.2194 | TA506 | 10/1 | Completed
2025-09-20 | 2025-09-16 | 2025-09-21 | Govind Mahto | 22.4884 | 3.7481 | TA506 | 220/4 | Completed
2025-09-20 | 2025-09-20 | 2025-09-23 | Horil | 21.0969 | 5.2742 | TA506 | 187A/1 | Completed
2025-09-20 | 2025-09-20 | 2025-09-25 | Jay Prakash | 35.8452 | 5.9742 | TA506 | 79/0 | Completed
2025-09-20 | 2025-09-17 | 2025-09-22 | Khemlal | 21.0969 | 3.5162 | TA506 | 212/5 | Completed
2025-09-20 | 2025-09-08 | 2025-09-20 | Mohan Mahto | 48.342 | 3.7186 | TA506 | 27/0 | Completed
2025-09-20 | 2025-09-18 | 2025-09-21 | Mohan Mahto | 18.1188 | 4.5297 | TA506 | 66/1 | Completed
2025-09-20 | 2025-09-10 | 2025-09-24 | Pankaj 1 | 39.5967 | 2.6398 | TA506 | 186/0 | Completed
2025-09-20 | 2025-09-14 | 2025-09-27 | Pankaj 2 | 29.7779 | 2.127 | TA506 | 214/0 | Completed
2025-09-20 | 2025-09-15 | 2025-09-20 | Shri Karni Construction | 21.0969 | 3.5162 | TA506 | 6/1 | Completed
2025-09-20 | 2025-09-15 | 2025-09-21 | Shri Karni Construction | 27.0921 | 3.8703 | TA506 | 19/0 | Completed
2025-09-20 | 2025-09-16 | 2025-09-20 | Shri Karni Construction | 16.9667 | 3.3933 | TA506 | 12/3 | Completed
2025-09-20 | 2025-09-18 | 2025-09-22 | Shri Karni Construction | 18.1188 | 3.6238 | TA506 | 60/2 | Completed
2025-09-20 | 2025-09-19 | 2025-09-24 | Shri Karni Construction | 21.0969 | 3.5162 | TA506 | 2/2 | Completed
2025-09-20 | 2025-09-14 | 2025-09-25 | Vinod | 42.6134 | 3.5511 | TA506 | 166/0 | Completed
2025-09-21 | 2025-09-18 | 2025-09-22 | A B Const Birendra Panday | 16.9667 | 3.3933 | TA506 | 100/2 | Completed
2025-09-21 | 2025-09-16 | 2025-09-21 | Govind Mahto | 22.4884 | 3.7481 | TA506 | 220/4 | Completed
2025-09-21 | 2025-09-20 | 2025-09-23 | Horil | 21.0969 | 5.2742 | TA506 | 187A/1 | Completed
2025-09-21 | 2025-09-20 | 2025-09-25 | Jay Prakash | 35.8452 | 5.9742 | TA506 | 79/0 | Completed
2025-09-21 | 2025-09-17 | 2025-09-22 | Khemlal | 21.0969 | 3.5162 | TA506 | 212/5 | Completed
2025-09-21 | 2025-09-18 | 2025-09-21 | Mohan Mahto | 18.1188 | 4.5297 | TA506 | 66/1 | Completed
2025-09-21 | 2025-09-10 | 2025-09-24 | Pankaj 1 | 39.5967 | 2.6398 | TA506 | 186/0 | Completed
2025-09-21 | 2025-09-14 | 2025-09-27 | Pankaj 2 | 29.7779 | 2.127 | TA506 | 214/0 | Completed
2025-09-21 | 2025-09-15 | 2025-09-21 | Shri Karni Construction | 27.0921 | 3.8703 | TA506 | 19/0 | Completed
2025-09-21 | 2025-09-18 | 2025-09-22 | Shri Karni Construction | 18.1188 | 3.6238 | TA506 | 60/2 | Completed
2025-09-21 | 2025-09-19 | 2025-09-24 | Shri Karni Construction | 21.0969 | 3.5162 | TA506 | 2/2 | Completed
2025-09-21 | 2025-09-14 | 2025-09-25 | Vinod | 42.6134 | 3.5511 | TA506 | 166/0 | Completed
2025-09-22 | 2025-09-18 | 2025-09-22 | A B Const Birendra Panday | 16.9667 | 3.3933 | TA506 | 100/2 | Completed
2025-09-22 | 2025-09-20 | 2025-09-23 | Horil | 21.0969 | 5.2742 | TA506 | 187A/1 | Completed
2025-09-22 | 2025-09-22 | 2025-10-02 | Jai Prakash Mahto | 29.7779 | 2.7071 | TA506 | 66/0 | Completed
2025-09-22 | 2025-09-20 | 2025-09-25 | Jay Prakash | 35.8452 | 5.9742 | TA506 | 79/0 | Completed
2025-09-22 | 2025-09-17 | 2025-09-22 | Khemlal | 21.0969 | 3.5162 | TA506 | 212/5 | Completed
2025-09-22 | 2025-09-10 | 2025-09-24 | Pankaj 1 | 39.5967 | 2.6398 | TA506 | 186/0 | Completed
2025-09-22 | 2025-09-14 | 2025-09-27 | Pankaj 2 | 29.7779 | 2.127 | TA506 | 214/0 | Completed
2025-09-22 | 2025-09-18 | 2025-09-22 | Shri Karni Construction | 18.1188 | 3.6238 | TA506 | 60/2 | Completed
2025-09-22 | 2025-09-19 | 2025-09-24 | Shri Karni Construction | 21.0969 | 3.5162 | TA506 | 2/2 | Completed
2025-09-22 | 2025-09-22 | 2025-09-25 | Shri Karni Construction | 18.1188 | 4.5297 | TA506 | 11/2 | Completed
2025-09-22 | 2025-09-22 | 2025-09-26 | Shri Karni Construction | 22.4884 | 4.4977 | TA506 | 6/2 | Completed
2025-09-22 | 2025-09-14 | 2025-09-25 | Vinod | 42.6134 | 3.5511 | TA506 | 166/0 | Completed
2025-09-23 | 2025-09-20 | 2025-09-23 | Horil | 21.0969 | 5.2742 | TA506 | 187A/1 | Completed
2025-09-23 | 2025-09-22 | 2025-10-02 | Jai Prakash Mahto | 29.7779 | 2.7071 | TA506 | 66/0 | Completed
2025-09-23 | 2025-09-20 | 2025-09-25 | Jay Prakash | 35.8452 | 5.9742 | TA506 | 79/0 | Completed
2025-09-23 | 2025-09-23 | 2025-10-01 | Karni Const 5 | 21.0969 | 2.3441 | TA506 | 10/2 | Completed
2025-09-23 | 2025-09-23 | 2025-09-27 | Khemlal | 22.4884 | 4.4977 | TA506 | 212/4 | Completed
2025-09-23 | 2025-09-10 | 2025-09-24 | Pankaj 1 | 39.5967 | 2.6398 | TA506 | 186/0 | Completed
2025-09-23 | 2025-09-14 | 2025-09-27 | Pankaj 2 | 29.7779 | 2.127 | TA506 | 214/0 | Completed
2025-09-23 | 2025-09-19 | 2025-09-24 | Shri Karni Construction | 21.0969 | 3.5162 | TA506 | 2/2 | Completed
2025-09-23 | 2025-09-22 | 2025-09-25 | Shri Karni Construction | 18.1188 | 4.5297 | TA506 | 11/2 | Completed
2025-09-23 | 2025-09-22 | 2025-09-26 | Shri Karni Construction | 22.4884 | 4.4977 | TA506 | 6/2 | Completed
2025-09-23 | 2025-09-23 | 2025-09-26 | Shri Karni Construction | 21.0969 | 5.2742 | TA506 | 35A/1 | Completed
2025-09-23 | 2025-09-14 | 2025-09-25 | Vinod | 42.6134 | 3.5511 | TA506 | 166/0 | Completed
2025-09-24 | 2025-09-24 | 2025-09-27 | Govind Mahto | 16.4524 | 4.1131 | TA506 | 220/2 | Completed
2025-09-24 | 2025-09-24 | 2025-09-27 | Horil | 21.0969 | 5.2742 | TA506 | 187/2 | Completed
2025-09-24 | 2025-09-22 | 2025-10-02 | Jai Prakash Mahto | 29.7779 | 2.7071 | TA506 | 66/0 | Completed
2025-09-24 | 2025-09-20 | 2025-09-25 | Jay Prakash | 35.8452 | 5.9742 | TA506 | 79/0 | Completed
2025-09-24 | 2025-09-23 | 2025-10-01 | Karni Const 5 | 21.0969 | 2.3441 | TA506 | 10/2 | Completed
2025-09-24 | 2025-09-23 | 2025-09-27 | Khemlal | 22.4884 | 4.4977 | TA506 | 212/4 | Completed
2025-09-24 | 2025-09-10 | 2025-09-24 | Pankaj 1 | 39.5967 | 2.6398 | TA506 | 186/0 | Completed
2025-09-24 | 2025-09-14 | 2025-09-27 | Pankaj 2 | 29.7779 | 2.127 | TA506 | 214/0 | Completed
2025-09-24 | 2025-09-19 | 2025-09-24 | Shri Karni Construction | 21.0969 | 3.5162 | TA506 | 2/2 | Completed
2025-09-24 | 2025-09-22 | 2025-09-25 | Shri Karni Construction | 18.1188 | 4.5297 | TA506 | 11/2 | Completed
2025-09-24 | 2025-09-22 | 2025-09-26 | Shri Karni Construction | 22.4884 | 4.4977 | TA506 | 6/2 | Completed
2025-09-24 | 2025-09-23 | 2025-09-26 | Shri Karni Construction | 21.0969 | 5.2742 | TA506 | 35A/1 | Completed
2025-09-24 | 2025-09-24 | 2025-09-27 | Shri Karni Construction | 18.1188 | 4.5297 | TA506 | 5/10 | Completed
2025-09-24 | 2025-09-24 | 2025-09-30 | Shri Karni Construction | 36.5854 | 5.2265 | TA506 | 11/3 | Completed
2025-09-24 | 2025-09-24 | 2025-09-26 | Shri Karni Construction | 15.8578 | 5.2859 | TA506 | 18/5 | Completed
2025-09-24 | 2025-09-24 | 2025-09-26 | Shri Karni Construction | 16.4524 | 5.4841 | TA506 | 60/3 | Completed
2025-09-24 | 2025-09-14 | 2025-09-25 | Vinod | 42.6134 | 3.5511 | TA506 | 166/0 | Completed
2025-09-25 | 2025-09-24 | 2025-09-27 | Govind Mahto | 16.4524 | 4.1131 | TA506 | 220/2 | Completed
2025-09-25 | 2025-09-24 | 2025-09-27 | Horil | 21.0969 | 5.2742 | TA506 | 187/2 | Completed
2025-09-25 | 2025-09-22 | 2025-10-02 | Jai Prakash Mahto | 29.7779 | 2.7071 | TA506 | 66/0 | Completed
2025-09-25 | 2025-09-20 | 2025-09-25 | Jay Prakash | 35.8452 | 5.9742 | TA506 | 79/0 | Completed
2025-09-25 | 2025-09-25 | 2025-09-30 | Jay Prakash | 29.7779 | 4.963 | TA506 | 66/0 | Completed
2025-09-25 | 2025-09-25 | 2025-10-02 | Karni Const 3 | 36.5854 | 4.5732 | TA506 | 11/3 | Completed
2025-09-25 | 2025-09-23 | 2025-10-01 | Karni Const 5 | 21.0969 | 2.3441 | TA506 | 10/2 | Completed
2025-09-25 | 2025-09-23 | 2025-09-27 | Khemlal | 22.4884 | 4.4977 | TA506 | 212/4 | Completed
2025-09-25 | 2025-09-14 | 2025-09-27 | Pankaj 2 | 29.7779 | 2.127 | TA506 | 214/0 | Completed
2025-09-25 | 2025-09-22 | 2025-09-25 | Shri Karni Construction | 18.1188 | 4.5297 | TA506 | 11/2 | Completed
2025-09-25 | 2025-09-22 | 2025-09-26 | Shri Karni Construction | 22.4884 | 4.4977 | TA506 | 6/2 | Completed
2025-09-25 | 2025-09-23 | 2025-09-26 | Shri Karni Construction | 21.0969 | 5.2742 | TA506 | 35A/1 | Completed
2025-09-25 | 2025-09-24 | 2025-09-27 | Shri Karni Construction | 18.1188 | 4.5297 | TA506 | 5/10 | Completed
2025-09-25 | 2025-09-24 | 2025-09-30 | Shri Karni Construction | 36.5854 | 5.2265 | TA506 | 11/3 | Completed
2025-09-25 | 2025-09-24 | 2025-09-26 | Shri Karni Construction | 15.8578 | 5.2859 | TA506 | 18/5 | Completed
2025-09-25 | 2025-09-24 | 2025-09-26 | Shri Karni Construction | 16.4524 | 5.4841 | TA506 | 60/3 | Completed
2025-09-25 | 2025-09-25 | 2025-09-28 | Shri Karni Construction | 21.0969 | 5.2742 | TA506 | 18/6 | Completed
2025-09-25 | 2025-09-14 | 2025-09-25 | Vinod | 42.6134 | 3.5511 | TA506 | 166/0 | Completed
2025-09-26 | 2025-09-26 | 2025-10-03 | Ab Const | 48.342 | 6.0427 | TA506 | 101/0 | Completed
2025-09-26 | 2025-09-24 | 2025-09-27 | Govind Mahto | 16.4524 | 4.1131 | TA506 | 220/2 | Completed
2025-09-26 | 2025-09-24 | 2025-09-27 | Horil | 21.0969 | 5.2742 | TA506 | 187/2 | Completed
2025-09-26 | 2025-09-22 | 2025-10-02 | Jai Prakash Mahto | 29.7779 | 2.7071 | TA506 | 66/0 | Completed
2025-09-26 | 2025-09-25 | 2025-09-30 | Jay Prakash | 29.7779 | 4.963 | TA506 | 66/0 | Completed
2025-09-26 | 2025-09-25 | 2025-10-02 | Karni Const 3 | 36.5854 | 4.5732 | TA506 | 11/3 | Completed
2025-09-26 | 2025-09-23 | 2025-10-01 | Karni Const 5 | 21.0969 | 2.3441 | TA506 | 10/2 | Completed
2025-09-26 | 2025-09-23 | 2025-09-27 | Khemlal | 22.4884 | 4.4977 | TA506 | 212/4 | Completed
2025-09-26 | 2025-09-14 | 2025-09-27 | Pankaj 2 | 29.7779 | 2.127 | TA506 | 214/0 | Completed
2025-09-26 | 2025-09-22 | 2025-09-26 | Shri Karni Construction | 22.4884 | 4.4977 | TA506 | 6/2 | Completed
2025-09-26 | 2025-09-23 | 2025-09-26 | Shri Karni Construction | 21.0969 | 5.2742 | TA506 | 35A/1 | Completed
2025-09-26 | 2025-09-24 | 2025-09-27 | Shri Karni Construction | 18.1188 | 4.5297 | TA506 | 5/10 | Completed
2025-09-26 | 2025-09-24 | 2025-09-30 | Shri Karni Construction | 36.5854 | 5.2265 | TA506 | 11/3 | Completed
2025-09-26 | 2025-09-24 | 2025-09-26 | Shri Karni Construction | 15.8578 | 5.2859 | TA506 | 18/5 | Completed
2025-09-26 | 2025-09-24 | 2025-09-26 | Shri Karni Construction | 16.4524 | 5.4841 | TA506 | 60/3 | Completed
2025-09-26 | 2025-09-25 | 2025-09-28 | Shri Karni Construction | 21.0969 | 5.2742 | TA506 | 18/6 | Completed
2025-09-26 | 2025-09-26 | 2025-09-30 | Shri Karni Construction | 21.0969 | 4.2194 | TA506 | 10/2 | Completed
2025-09-26 | 2025-09-26 | 2025-09-29 | Shri Karni Construction | 21.0969 | 5.2742 | TA506 | 2/1 | Completed
2025-09-27 | 2025-09-26 | 2025-10-03 | Ab Const | 48.342 | 6.0427 | TA506 | 101/0 | Completed
2025-09-27 | 2025-09-24 | 2025-09-27 | Govind Mahto | 16.4524 | 4.1131 | TA506 | 220/2 | Completed
2025-09-27 | 2025-09-24 | 2025-09-27 | Horil | 21.0969 | 5.2742 | TA506 | 187/2 | Completed
2025-09-27 | 2025-09-27 | 2025-09-30 | Horil | 21.0969 | 5.2742 | TA506 | 194/2 | Completed
2025-09-27 | 2025-09-22 | 2025-10-02 | Jai Prakash Mahto | 29.7779 | 2.7071 | TA506 | 66/0 | Completed
2025-09-27 | 2025-09-25 | 2025-09-30 | Jay Prakash | 29.7779 | 4.963 | TA506 | 66/0 | Completed
2025-09-27 | 2025-09-25 | 2025-10-02 | Karni Const 3 | 36.5854 | 4.5732 | TA506 | 11/3 | Completed
2025-09-27 | 2025-09-23 | 2025-10-01 | Karni Const 5 | 21.0969 | 2.3441 | TA506 | 10/2 | Completed
2025-09-27 | 2025-09-27 | 2025-10-01 | Karni Const 6 | 18.1188 | 3.6238 | TA506 | 61/1 | Completed
2025-09-27 | 2025-09-23 | 2025-09-27 | Khemlal | 22.4884 | 4.4977 | TA506 | 212/4 | Completed
2025-09-27 | 2025-09-27 | 2025-09-30 | Khemlal | 21.0969 | 5.2742 | TA506 | 212/3 | Completed
2025-09-27 | 2025-09-27 | 2025-09-30 | Pankaj 1 | 18.1188 | 4.5297 | TA506 | 210/10 | Completed
2025-09-27 | 2025-09-14 | 2025-09-27 | Pankaj 2 | 29.7779 | 2.127 | TA506 | 214/0 | Completed
2025-09-27 | 2025-09-27 | 2025-10-03 | Pankaj Const | 16.9667 | 2.4238 | TA506 | 206/1 | Completed
2025-09-27 | 2025-09-24 | 2025-09-27 | Shri Karni Construction | 18.1188 | 4.5297 | TA506 | 5/10 | Completed
2025-09-27 | 2025-09-24 | 2025-09-30 | Shri Karni Construction | 36.5854 | 5.2265 | TA506 | 11/3 | Completed
2025-09-27 | 2025-09-25 | 2025-09-28 | Shri Karni Construction | 21.0969 | 5.2742 | TA506 | 18/6 | Completed
2025-09-27 | 2025-09-26 | 2025-09-30 | Shri Karni Construction | 21.0969 | 4.2194 | TA506 | 10/2 | Completed
2025-09-27 | 2025-09-26 | 2025-09-29 | Shri Karni Construction | 21.0969 | 5.2742 | TA506 | 2/1 | Completed
2025-09-27 | 2025-09-27 | 2025-09-30 | Shri Karni Construction | 22.4884 | 5.6221 | TA506 | 5/9 | Completed
2025-09-27 | 2025-09-27 | 2025-09-30 | Shri Karni Construction | 18.1188 | 4.5297 | TA506 | 61/1 | Completed
2025-09-27 | 2025-09-27 | 2025-09-29 | Tejal | 16.9667 | 5.6556 | TA506 | 142/1 | Completed
2025-09-28 | 2025-09-26 | 2025-10-03 | Ab Const | 48.342 | 6.0427 | TA506 | 101/0 | Completed
2025-09-28 | 2025-09-28 | 2025-10-09 | Binod Mahto | 35.8452 | 2.9871 | TA506 | 164/0 | Completed
2025-09-28 | 2025-09-28 | 2025-10-03 | Govind Mahto | 18.1188 | 3.0198 | TA506 | 220/1 | Completed
2025-09-28 | 2025-09-27 | 2025-09-30 | Horil | 21.0969 | 5.2742 | TA506 | 194/2 | Completed
2025-09-28 | 2025-09-22 | 2025-10-02 | Jai Prakash Mahto | 29.7779 | 2.7071 | TA506 | 66/0 | Completed
2025-09-28 | 2025-09-25 | 2025-09-30 | Jay Prakash | 29.7779 | 4.963 | TA506 | 66/0 | Completed
2025-09-28 | 2025-09-25 | 2025-10-02 | Karni Const 3 | 36.5854 | 4.5732 | TA506 | 11/3 | Completed
2025-09-28 | 2025-09-23 | 2025-10-01 | Karni Const 5 | 21.0969 | 2.3441 | TA506 | 10/2 | Completed
2025-09-28 | 2025-09-27 | 2025-10-01 | Karni Const 6 | 18.1188 | 3.6238 | TA506 | 61/1 | Completed
2025-09-28 | 2025-09-27 | 2025-09-30 | Khemlal | 21.0969 | 5.2742 | TA506 | 212/3 | Completed
2025-09-28 | 2025-09-27 | 2025-09-30 | Pankaj 1 | 18.1188 | 4.5297 | TA506 | 210/10 | Completed
2025-09-28 | 2025-09-27 | 2025-10-03 | Pankaj Const | 16.9667 | 2.4238 | TA506 | 206/1 | Completed
2025-09-28 | 2025-09-24 | 2025-09-30 | Shri Karni Construction | 36.5854 | 5.2265 | TA506 | 11/3 | Completed
2025-09-28 | 2025-09-25 | 2025-09-28 | Shri Karni Construction | 21.0969 | 5.2742 | TA506 | 18/6 | Completed
2025-09-28 | 2025-09-26 | 2025-09-30 | Shri Karni Construction | 21.0969 | 4.2194 | TA506 | 10/2 | Completed
2025-09-28 | 2025-09-26 | 2025-09-29 | Shri Karni Construction | 21.0969 | 5.2742 | TA506 | 2/1 | Completed
2025-09-28 | 2025-09-27 | 2025-09-30 | Shri Karni Construction | 22.4884 | 5.6221 | TA506 | 5/9 | Completed
2025-09-28 | 2025-09-27 | 2025-09-30 | Shri Karni Construction | 18.1188 | 4.5297 | TA506 | 61/1 | Completed
2025-09-28 | 2025-09-28 | 2025-09-30 | Shri Karni Construction | 15.8578 | 5.2859 | TA506 | 2/5 | Completed
2025-09-28 | 2025-09-28 | 2025-09-30 | Shri Karni Construction | 15.8578 | 5.2859 | TA506 | 19/2 | Completed
2025-09-28 | 2025-09-27 | 2025-09-29 | Tejal | 16.9667 | 5.6556 | TA506 | 142/1 | Completed
2025-09-29 | 2025-09-26 | 2025-10-03 | Ab Const | 48.342 | 6.0427 | TA506 | 101/0 | Completed
2025-09-29 | 2025-09-28 | 2025-10-09 | Binod Mahto | 35.8452 | 2.9871 | TA506 | 164/0 | Completed
2025-09-29 | 2025-09-28 | 2025-10-03 | Govind Mahto | 18.1188 | 3.0198 | TA506 | 220/1 | Completed
2025-09-29 | 2025-09-27 | 2025-09-30 | Horil | 21.0969 | 5.2742 | TA506 | 194/2 | Completed
2025-09-29 | 2025-09-29 | 2025-10-03 | Horil Mahto | 21.0969 | 4.2194 | TA506 | 194/2 | Completed
2025-09-29 | 2025-09-22 | 2025-10-02 | Jai Prakash Mahto | 29.7779 | 2.7071 | TA506 | 66/0 | Completed
2025-09-29 | 2025-09-25 | 2025-09-30 | Jay Prakash | 29.7779 | 4.963 | TA506 | 66/0 | Completed
2025-09-29 | 2025-09-25 | 2025-10-02 | Karni Const 3 | 36.5854 | 4.5732 | TA506 | 11/3 | Completed
2025-09-29 | 2025-09-23 | 2025-10-01 | Karni Const 5 | 21.0969 | 2.3441 | TA506 | 10/2 | Completed
2025-09-29 | 2025-09-27 | 2025-10-01 | Karni Const 6 | 18.1188 | 3.6238 | TA506 | 61/1 | Completed
2025-09-29 | 2025-09-27 | 2025-09-30 | Khemlal | 21.0969 | 5.2742 | TA506 | 212/3 | Completed
2025-09-29 | 2025-09-27 | 2025-09-30 | Pankaj 1 | 18.1188 | 4.5297 | TA506 | 210/10 | Completed
2025-09-29 | 2025-09-27 | 2025-10-03 | Pankaj Const | 16.9667 | 2.4238 | TA506 | 206/1 | Completed
2025-09-29 | 2025-09-24 | 2025-09-30 | Shri Karni Construction | 36.5854 | 5.2265 | TA506 | 11/3 | Completed
2025-09-29 | 2025-09-26 | 2025-09-30 | Shri Karni Construction | 21.0969 | 4.2194 | TA506 | 10/2 | Completed
2025-09-29 | 2025-09-26 | 2025-09-29 | Shri Karni Construction | 21.0969 | 5.2742 | TA506 | 2/1 | Completed
2025-09-29 | 2025-09-27 | 2025-09-30 | Shri Karni Construction | 22.4884 | 5.6221 | TA506 | 5/9 | Completed
2025-09-29 | 2025-09-27 | 2025-09-30 | Shri Karni Construction | 18.1188 | 4.5297 | TA506 | 61/1 | Completed
2025-09-29 | 2025-09-28 | 2025-09-30 | Shri Karni Construction | 15.8578 | 5.2859 | TA506 | 2/5 | Completed
2025-09-29 | 2025-09-28 | 2025-09-30 | Shri Karni Construction | 15.8578 | 5.2859 | TA506 | 19/2 | Completed
2025-09-29 | 2025-09-27 | 2025-09-29 | Tejal | 16.9667 | 5.6556 | TA506 | 142/1 | Completed
2025-09-29 | 2025-09-29 | 2025-10-03 | Tejal Const | 18.1188 | 3.6238 | TA506 | 140/2 | Completed
2025-09-30 | 2025-09-26 | 2025-10-03 | Ab Const | 48.342 | 6.0427 | TA506 | 101/0 | Completed
2025-09-30 | 2025-09-28 | 2025-10-09 | Binod Mahto | 35.8452 | 2.9871 | TA506 | 164/0 | Completed
2025-09-30 | 2025-09-28 | 2025-10-03 | Govind Mahto | 18.1188 | 3.0198 | TA506 | 220/1 | Completed
2025-09-30 | 2025-09-27 | 2025-09-30 | Horil | 21.0969 | 5.2742 | TA506 | 194/2 | Completed
2025-09-30 | 2025-09-29 | 2025-10-03 | Horil Mahto | 21.0969 | 4.2194 | TA506 | 194/2 | Completed
2025-09-30 | 2025-09-22 | 2025-10-02 | Jai Prakash Mahto | 29.7779 | 2.7071 | TA506 | 66/0 | Completed
2025-09-30 | 2025-09-25 | 2025-09-30 | Jay Prakash | 29.7779 | 4.963 | TA506 | 66/0 | Completed
2025-09-30 | 2025-09-25 | 2025-10-02 | Karni Const 3 | 36.5854 | 4.5732 | TA506 | 11/3 | Completed
2025-09-30 | 2025-09-30 | 2025-10-03 | Karni Const 4 | 15.8578 | 3.9644 | TA506 | 19/2 | Completed
2025-09-30 | 2025-09-23 | 2025-10-01 | Karni Const 5 | 21.0969 | 2.3441 | TA506 | 10/2 | Completed
2025-09-30 | 2025-09-27 | 2025-10-01 | Karni Const 6 | 18.1188 | 3.6238 | TA506 | 61/1 | Completed
2025-09-30 | 2025-09-27 | 2025-09-30 | Khemlal | 21.0969 | 5.2742 | TA506 | 212/3 | Completed
2025-09-30 | 2025-09-27 | 2025-09-30 | Pankaj 1 | 18.1188 | 4.5297 | TA506 | 210/10 | Completed
2025-09-30 | 2025-09-27 | 2025-10-03 | Pankaj Const | 16.9667 | 2.4238 | TA506 | 206/1 | Completed
2025-09-30 | 2025-09-24 | 2025-09-30 | Shri Karni Construction | 36.5854 | 5.2265 | TA506 | 11/3 | Completed
2025-09-30 | 2025-09-26 | 2025-09-30 | Shri Karni Construction | 21.0969 | 4.2194 | TA506 | 10/2 | Completed
2025-09-30 | 2025-09-27 | 2025-09-30 | Shri Karni Construction | 22.4884 | 5.6221 | TA506 | 5/9 | Completed
2025-09-30 | 2025-09-27 | 2025-09-30 | Shri Karni Construction | 18.1188 | 4.5297 | TA506 | 61/1 | Completed
2025-09-30 | 2025-09-28 | 2025-09-30 | Shri Karni Construction | 15.8578 | 5.2859 | TA506 | 2/5 | Completed
2025-09-30 | 2025-09-28 | 2025-09-30 | Shri Karni Construction | 15.8578 | 5.2859 | TA506 | 19/2 | Completed
2025-09-30 | 2025-09-29 | 2025-10-03 | Tejal Const | 18.1188 | 3.6238 | TA506 | 140/2 | Completed
2025-10-01 | 2025-09-26 | 2025-10-03 | Ab Const | 48.342 | 6.0427 | TA506 | 101/0 | Completed
2025-10-01 | 2025-09-28 | 2025-10-09 | Binod Mahto | 35.8452 | 2.9871 | TA506 | 164/0 | Completed
2025-10-01 | 2025-09-28 | 2025-10-03 | Govind Mahto | 18.1188 | 3.0198 | TA506 | 220/1 | Completed
2025-10-01 | 2025-09-29 | 2025-10-03 | Horil Mahto | 21.0969 | 4.2194 | TA506 | 194/2 | Completed
2025-10-01 | 2025-09-22 | 2025-10-02 | Jai Prakash Mahto | 29.7779 | 2.7071 | TA506 | 66/0 | Completed
2025-10-01 | 2025-10-01 | 2025-10-03 | Karni Const 1 | 15.8578 | 5.2859 | TA506 | 2/5 | Completed
2025-10-01 | 2025-10-01 | 2025-10-03 | Karni Const 2 | 18.1188 | 6.0396 | TA506 | 5/9 | Completed
2025-10-01 | 2025-09-25 | 2025-10-02 | Karni Const 3 | 36.5854 | 4.5732 | TA506 | 11/3 | Completed
2025-10-01 | 2025-09-30 | 2025-10-03 | Karni Const 4 | 15.8578 | 3.9644 | TA506 | 19/2 | Completed
2025-10-01 | 2025-09-23 | 2025-10-01 | Karni Const 5 | 21.0969 | 2.3441 | TA506 | 10/2 | Completed
2025-10-01 | 2025-09-27 | 2025-10-01 | Karni Const 6 | 18.1188 | 3.6238 | TA506 | 61/1 | Completed
2025-10-01 | 2025-10-01 | 2025-10-06 | Karni Const 6 | 16.4524 | 2.7421 | TA506 | 51A/2 | Completed
2025-10-01 | 2025-09-27 | 2025-10-03 | Pankaj Const | 16.9667 | 2.4238 | TA506 | 206/1 | Completed
2025-10-01 | 2025-09-29 | 2025-10-03 | Tejal Const | 18.1188 | 3.6238 | TA506 | 140/2 | Completed
2025-10-02 | 2025-09-26 | 2025-10-03 | Ab Const | 48.342 | 6.0427 | TA506 | 101/0 | Completed
2025-10-02 | 2025-09-28 | 2025-10-09 | Binod Mahto | 35.8452 | 2.9871 | TA506 | 164/0 | Completed
2025-10-02 | 2025-09-28 | 2025-10-03 | Govind Mahto | 18.1188 | 3.0198 | TA506 | 220/1 | Completed
2025-10-02 | 2025-09-29 | 2025-10-03 | Horil Mahto | 21.0969 | 4.2194 | TA506 | 194/2 | Completed
2025-10-02 | 2025-10-02 | 2025-10-11 | Horil Mahto | 37.2057 | 3.7206 | TA506 | 187/0 | Completed
2025-10-02 | 2025-09-22 | 2025-10-02 | Jai Prakash Mahto | 29.7779 | 2.7071 | TA506 | 66/0 | Completed
2025-10-02 | 2025-10-02 | 2025-10-09 | Jai Prakash Mahto | 37.2057 | 4.6507 | TA506 | 67/0 | Completed
2025-10-02 | 2025-10-01 | 2025-10-03 | Karni Const 1 | 15.8578 | 5.2859 | TA506 | 2/5 | Completed
2025-10-02 | 2025-10-01 | 2025-10-03 | Karni Const 2 | 18.1188 | 6.0396 | TA506 | 5/9 | Completed
2025-10-02 | 2025-09-25 | 2025-10-02 | Karni Const 3 | 36.5854 | 4.5732 | TA506 | 11/3 | Completed
2025-10-02 | 2025-09-30 | 2025-10-03 | Karni Const 4 | 15.8578 | 3.9644 | TA506 | 19/2 | Completed
2025-10-02 | 2025-10-02 | 2025-10-08 | Karni Const 4 | 21.0969 | 3.0138 | TA506 | 19/3 | Completed
2025-10-02 | 2025-10-01 | 2025-10-06 | Karni Const 6 | 16.4524 | 2.7421 | TA506 | 51A/2 | Completed
2025-10-02 | 2025-09-27 | 2025-10-03 | Pankaj Const | 16.9667 | 2.4238 | TA506 | 206/1 | Completed
2025-10-02 | 2025-09-29 | 2025-10-03 | Tejal Const | 18.1188 | 3.6238 | TA506 | 140/2 | Completed
2025-10-03 | 2025-09-26 | 2025-10-03 | Ab Const | 48.342 | 6.0427 | TA506 | 101/0 | Completed
2025-10-03 | 2025-09-28 | 2025-10-09 | Binod Mahto | 35.8452 | 2.9871 | TA506 | 164/0 | Completed
2025-10-03 | 2025-09-28 | 2025-10-03 | Govind Mahto | 18.1188 | 3.0198 | TA506 | 220/1 | Completed
2025-10-03 | 2025-09-29 | 2025-10-03 | Horil Mahto | 21.0969 | 4.2194 | TA506 | 194/2 | Completed
2025-10-03 | 2025-10-02 | 2025-10-11 | Horil Mahto | 37.2057 | 3.7206 | TA506 | 187/0 | Completed
2025-10-03 | 2025-10-02 | 2025-10-09 | Jai Prakash Mahto | 37.2057 | 4.6507 | TA506 | 67/0 | Completed
2025-10-03 | 2025-10-01 | 2025-10-03 | Karni Const 1 | 15.8578 | 5.2859 | TA506 | 2/5 | Completed
2025-10-03 | 2025-10-01 | 2025-10-03 | Karni Const 2 | 18.1188 | 6.0396 | TA506 | 5/9 | Completed
2025-10-03 | 2025-09-30 | 2025-10-03 | Karni Const 4 | 15.8578 | 3.9644 | TA506 | 19/2 | Completed
2025-10-03 | 2025-10-02 | 2025-10-08 | Karni Const 4 | 21.0969 | 3.0138 | TA506 | 19/3 | Completed
2025-10-03 | 2025-10-01 | 2025-10-06 | Karni Const 6 | 16.4524 | 2.7421 | TA506 | 51A/2 | Completed
2025-10-03 | 2025-09-27 | 2025-10-03 | Pankaj Const | 16.9667 | 2.4238 | TA506 | 206/1 | Completed
2025-10-03 | 2025-10-03 | 2025-10-11 | Pankaj Const | 29.7779 | 3.3087 | TA506 | 206/0 | Completed
2025-10-03 | 2025-09-29 | 2025-10-03 | Tejal Const | 18.1188 | 3.6238 | TA506 | 140/2 | Completed
2025-10-04 | 2025-09-28 | 2025-10-09 | Binod Mahto | 35.8452 | 2.9871 | TA506 | 164/0 | Completed
2025-10-04 | 2025-10-04 | 2025-10-10 | Govind Mahto | 38.1379 | 5.4483 | TA506 | 224/0 | Completed
2025-10-04 | 2025-10-02 | 2025-10-11 | Horil Mahto | 37.2057 | 3.7206 | TA506 | 187/0 | Completed
2025-10-04 | 2025-10-02 | 2025-10-09 | Jai Prakash Mahto | 37.2057 | 4.6507 | TA506 | 67/0 | Completed
2025-10-04 | 2025-10-04 | 2025-10-07 | Karni Const 1 | 16.9667 | 4.2417 | TA506 | 2/6 | Completed
2025-10-04 | 2025-10-04 | 2025-10-07 | Karni Const 2 | 18.1188 | 4.5297 | TA506 | 5/11 | Completed
2025-10-04 | 2025-10-02 | 2025-10-08 | Karni Const 4 | 21.0969 | 3.0138 | TA506 | 19/3 | Completed
2025-10-04 | 2025-10-01 | 2025-10-06 | Karni Const 6 | 16.4524 | 2.7421 | TA506 | 51A/2 | Completed
2025-10-04 | 2025-10-03 | 2025-10-11 | Pankaj Const | 29.7779 | 3.3087 | TA506 | 206/0 | Completed
2025-10-05 | 2025-09-28 | 2025-10-09 | Binod Mahto | 35.8452 | 2.9871 | TA506 | 164/0 | Completed
2025-10-05 | 2025-10-04 | 2025-10-10 | Govind Mahto | 38.1379 | 5.4483 | TA506 | 224/0 | Completed
2025-10-05 | 2025-10-02 | 2025-10-11 | Horil Mahto | 37.2057 | 3.7206 | TA506 | 187/0 | Completed
2025-10-05 | 2025-10-02 | 2025-10-09 | Jai Prakash Mahto | 37.2057 | 4.6507 | TA506 | 67/0 | Completed
2025-10-05 | 2025-10-04 | 2025-10-07 | Karni Const 1 | 16.9667 | 4.2417 | TA506 | 2/6 | Completed
2025-10-05 | 2025-10-04 | 2025-10-07 | Karni Const 2 | 18.1188 | 4.5297 | TA506 | 5/11 | Completed
2025-10-05 | 2025-10-05 | 2025-10-10 | Karni Const 3 | 22.4884 | 3.7481 | TA506 | 13/1 | Completed
2025-10-05 | 2025-10-02 | 2025-10-08 | Karni Const 4 | 21.0969 | 3.0138 | TA506 | 19/3 | Completed
2025-10-05 | 2025-10-01 | 2025-10-06 | Karni Const 6 | 16.4524 | 2.7421 | TA506 | 51A/2 | Completed
2025-10-05 | 2025-10-05 | 2025-10-10 | Khemlal Mahto | 18.1188 | 3.0198 | TA506 | 213/5 | Completed
2025-10-05 | 2025-10-03 | 2025-10-11 | Pankaj Const | 29.7779 | 3.3087 | TA506 | 206/0 | Completed
2025-10-06 | 2025-09-28 | 2025-10-09 | Binod Mahto | 35.8452 | 2.9871 | TA506 | 164/0 | Completed
2025-10-06 | 2025-10-04 | 2025-10-10 | Govind Mahto | 38.1379 | 5.4483 | TA506 | 224/0 | Completed
2025-10-06 | 2025-10-02 | 2025-10-11 | Horil Mahto | 37.2057 | 3.7206 | TA506 | 187/0 | Completed
2025-10-06 | 2025-10-02 | 2025-10-09 | Jai Prakash Mahto | 37.2057 | 4.6507 | TA506 | 67/0 | Completed
2025-10-06 | 2025-10-04 | 2025-10-07 | Karni Const 1 | 16.9667 | 4.2417 | TA506 | 2/6 | Completed
2025-10-06 | 2025-10-04 | 2025-10-07 | Karni Const 2 | 18.1188 | 4.5297 | TA506 | 5/11 | Completed
2025-10-06 | 2025-10-05 | 2025-10-10 | Karni Const 3 | 22.4884 | 3.7481 | TA506 | 13/1 | Completed
2025-10-06 | 2025-10-02 | 2025-10-08 | Karni Const 4 | 21.0969 | 3.0138 | TA506 | 19/3 | Completed
2025-10-06 | 2025-10-01 | 2025-10-06 | Karni Const 6 | 16.4524 | 2.7421 | TA506 | 51A/2 | Completed
2025-10-06 | 2025-10-05 | 2025-10-10 | Khemlal Mahto | 18.1188 | 3.0198 | TA506 | 213/5 | Completed
2025-10-06 | 2025-10-03 | 2025-10-11 | Pankaj Const | 29.7779 | 3.3087 | TA506 | 206/0 | Completed
2025-10-07 | 2025-09-28 | 2025-10-09 | Binod Mahto | 35.8452 | 2.9871 | TA506 | 164/0 | Completed
2025-10-07 | 2025-10-04 | 2025-10-10 | Govind Mahto | 38.1379 | 5.4483 | TA506 | 224/0 | Completed
2025-10-07 | 2025-10-02 | 2025-10-11 | Horil Mahto | 37.2057 | 3.7206 | TA506 | 187/0 | Completed
2025-10-07 | 2025-10-02 | 2025-10-09 | Jai Prakash Mahto | 37.2057 | 4.6507 | TA506 | 67/0 | Completed
2025-10-07 | 2025-10-04 | 2025-10-07 | Karni Const 1 | 16.9667 | 4.2417 | TA506 | 2/6 | Completed
2025-10-07 | 2025-10-04 | 2025-10-07 | Karni Const 2 | 18.1188 | 4.5297 | TA506 | 5/11 | Completed
2025-10-07 | 2025-10-05 | 2025-10-10 | Karni Const 3 | 22.4884 | 3.7481 | TA506 | 13/1 | Completed
2025-10-07 | 2025-10-02 | 2025-10-08 | Karni Const 4 | 21.0969 | 3.0138 | TA506 | 19/3 | Completed
2025-10-07 | 2025-10-07 | 2025-10-12 | Karni Const 4 | 15.8578 | 2.643 | TA506 | 19/4 | Completed
2025-10-07 | 2025-10-07 | 2025-10-10 | Karni Const 6 | 16.4524 | 4.1131 | TA506 | 51A/1 | Completed
2025-10-07 | 2025-10-05 | 2025-10-10 | Khemlal Mahto | 18.1188 | 3.0198 | TA506 | 213/5 | Completed
2025-10-07 | 2025-10-03 | 2025-10-11 | Pankaj Const | 29.7779 | 3.3087 | TA506 | 206/0 | Completed
2025-10-08 | 2025-09-28 | 2025-10-09 | Binod Mahto | 35.8452 | 2.9871 | TA506 | 164/0 | Completed
2025-10-08 | 2025-10-04 | 2025-10-10 | Govind Mahto | 38.1379 | 5.4483 | TA506 | 224/0 | Completed
2025-10-08 | 2025-10-02 | 2025-10-11 | Horil Mahto | 37.2057 | 3.7206 | TA506 | 187/0 | Completed
2025-10-08 | 2025-10-08 | 2025-10-12 | Horil Mahto | 18.1188 | 3.6238 | TA506 | 202/2 | Completed
2025-10-08 | 2025-10-02 | 2025-10-09 | Jai Prakash Mahto | 37.2057 | 4.6507 | TA506 | 67/0 | Completed
2025-10-08 | 2025-10-05 | 2025-10-10 | Karni Const 3 | 22.4884 | 3.7481 | TA506 | 13/1 | Completed
2025-10-08 | 2025-10-02 | 2025-10-08 | Karni Const 4 | 21.0969 | 3.0138 | TA506 | 19/3 | Completed
2025-10-08 | 2025-10-07 | 2025-10-12 | Karni Const 4 | 15.8578 | 2.643 | TA506 | 19/4 | Completed
2025-10-08 | 2025-10-08 | 2025-10-15 | Karni Const 4 | 21.0969 | 2.6371 | TA506 | 19/5 | Completed
2025-10-08 | 2025-10-07 | 2025-10-10 | Karni Const 6 | 16.4524 | 4.1131 | TA506 | 51A/1 | Completed
2025-10-08 | 2025-10-05 | 2025-10-10 | Khemlal Mahto | 18.1188 | 3.0198 | TA506 | 213/5 | Completed
2025-10-08 | 2025-10-03 | 2025-10-11 | Pankaj Const | 29.7779 | 3.3087 | TA506 | 206/0 | Completed
2025-10-08 | 2025-10-08 | 2025-10-14 | Tejal Const | 29.7779 | 4.254 | TA506 | 142/0 | Completed
2025-10-09 | 2025-09-28 | 2025-10-09 | Binod Mahto | 35.8452 | 2.9871 | TA506 | 164/0 | Completed
2025-10-09 | 2025-10-04 | 2025-10-10 | Govind Mahto | 38.1379 | 5.4483 | TA506 | 224/0 | Completed
2025-10-09 | 2025-10-02 | 2025-10-11 | Horil Mahto | 37.2057 | 3.7206 | TA506 | 187/0 | Completed
2025-10-09 | 2025-10-08 | 2025-10-12 | Horil Mahto | 18.1188 | 3.6238 | TA506 | 202/2 | Completed
2025-10-09 | 2025-10-09 | 2025-10-14 | Horil Mahto | 22.4884 | 3.7481 | TA506 | 193/2 | Completed
2025-10-09 | 2025-10-02 | 2025-10-09 | Jai Prakash Mahto | 37.2057 | 4.6507 | TA506 | 67/0 | Completed
2025-10-09 | 2025-10-05 | 2025-10-10 | Karni Const 3 | 22.4884 | 3.7481 | TA506 | 13/1 | Completed
2025-10-09 | 2025-10-07 | 2025-10-12 | Karni Const 4 | 15.8578 | 2.643 | TA506 | 19/4 | Completed
2025-10-09 | 2025-10-08 | 2025-10-15 | Karni Const 4 | 21.0969 | 2.6371 | TA506 | 19/5 | Completed
2025-10-09 | 2025-10-07 | 2025-10-10 | Karni Const 6 | 16.4524 | 4.1131 | TA506 | 51A/1 | Completed
2025-10-09 | 2025-10-05 | 2025-10-10 | Khemlal Mahto | 18.1188 | 3.0198 | TA506 | 213/5 | Completed
2025-10-09 | 2025-10-03 | 2025-10-11 | Pankaj Const | 29.7779 | 3.3087 | TA506 | 206/0 | Completed
2025-10-09 | 2025-10-08 | 2025-10-14 | Tejal Const | 29.7779 | 4.254 | TA506 | 142/0 | Completed
2025-10-10 | 2025-10-04 | 2025-10-10 | Govind Mahto | 38.1379 | 5.4483 | TA506 | 224/0 | Completed
2025-10-10 | 2025-10-02 | 2025-10-11 | Horil Mahto | 37.2057 | 3.7206 | TA506 | 187/0 | Completed
2025-10-10 | 2025-10-08 | 2025-10-12 | Horil Mahto | 18.1188 | 3.6238 | TA506 | 202/2 | Completed
2025-10-10 | 2025-10-09 | 2025-10-14 | Horil Mahto | 22.4884 | 3.7481 | TA506 | 193/2 | Completed
2025-10-10 | 2025-10-10 | 2025-10-16 | Jai Prakash Mahto | 34.17 | 4.8814 | TA506 | 65A/0 | Completed
2025-10-10 | 2025-10-10 | 2025-10-14 | Karni Const 1 | 15.8578 | 3.1716 | TA506 | 2/8 | Completed
2025-10-10 | 2025-10-05 | 2025-10-10 | Karni Const 3 | 22.4884 | 3.7481 | TA506 | 13/1 | Completed
2025-10-10 | 2025-10-10 | 2025-10-14 | Karni Const 3 | 15.8578 | 3.1716 | TA506 | 12/5 | Completed
2025-10-10 | 2025-10-07 | 2025-10-12 | Karni Const 4 | 15.8578 | 2.643 | TA506 | 19/4 | Completed
2025-10-10 | 2025-10-08 | 2025-10-15 | Karni Const 4 | 21.0969 | 2.6371 | TA506 | 19/5 | Completed
2025-10-10 | 2025-10-10 | 2025-10-15 | Karni Const 5 | 27.0921 | 4.5154 | TA506 | 13/0 | Completed
2025-10-10 | 2025-10-07 | 2025-10-10 | Karni Const 6 | 16.4524 | 4.1131 | TA506 | 51A/1 | Completed
2025-10-10 | 2025-10-05 | 2025-10-10 | Khemlal Mahto | 18.1188 | 3.0198 | TA506 | 213/5 | Completed
2025-10-10 | 2025-10-03 | 2025-10-11 | Pankaj Const | 29.7779 | 3.3087 | TA506 | 206/0 | Completed
2025-10-10 | 2025-10-08 | 2025-10-14 | Tejal Const | 29.7779 | 4.254 | TA506 | 142/0 | Completed
2025-10-11 | 2025-10-02 | 2025-10-11 | Horil Mahto | 37.2057 | 3.7206 | TA506 | 187/0 | Completed
2025-10-11 | 2025-10-08 | 2025-10-12 | Horil Mahto | 18.1188 | 3.6238 | TA506 | 202/2 | Completed
2025-10-11 | 2025-10-09 | 2025-10-14 | Horil Mahto | 22.4884 | 3.7481 | TA506 | 193/2 | Completed
2025-10-11 | 2025-10-10 | 2025-10-16 | Jai Prakash Mahto | 34.17 | 4.8814 | TA506 | 65A/0 | Completed
2025-10-11 | 2025-10-10 | 2025-10-14 | Karni Const 1 | 15.8578 | 3.1716 | TA506 | 2/8 | Completed
2025-10-11 | 2025-10-10 | 2025-10-14 | Karni Const 3 | 15.8578 | 3.1716 | TA506 | 12/5 | Completed
2025-10-11 | 2025-10-07 | 2025-10-12 | Karni Const 4 | 15.8578 | 2.643 | TA506 | 19/4 | Completed
2025-10-11 | 2025-10-08 | 2025-10-15 | Karni Const 4 | 21.0969 | 2.6371 | TA506 | 19/5 | Completed
2025-10-11 | 2025-10-10 | 2025-10-15 | Karni Const 5 | 27.0921 | 4.5154 | TA506 | 13/0 | Completed
2025-10-11 | 2025-10-11 | 2025-10-14 | Karni Const 6 | 16.4524 | 4.1131 | TA506 | 51C/2 | Completed
2025-10-11 | 2025-10-03 | 2025-10-11 | Pankaj Const | 29.7779 | 3.3087 | TA506 | 206/0 | Completed
2025-10-11 | 2025-10-11 | 2025-10-15 | Pankaj Const | 21.0969 | 4.2194 | TA506 | 205/1 | Completed
2025-10-11 | 2025-10-11 | 2025-10-16 | Pankaj Const | 36.85 | 6.1417 | TA506 | 213/0 | Completed
2025-10-11 | 2025-10-08 | 2025-10-14 | Tejal Const | 29.7779 | 4.254 | TA506 | 142/0 | Completed
2025-10-12 | 2025-10-08 | 2025-10-12 | Horil Mahto | 18.1188 | 3.6238 | TA506 | 202/2 | Completed
2025-10-12 | 2025-10-09 | 2025-10-14 | Horil Mahto | 22.4884 | 3.7481 | TA506 | 193/2 | Completed
2025-10-12 | 2025-10-10 | 2025-10-16 | Jai Prakash Mahto | 34.17 | 4.8814 | TA506 | 65A/0 | Completed
2025-10-12 | 2025-10-10 | 2025-10-14 | Karni Const 1 | 15.8578 | 3.1716 | TA506 | 2/8 | Completed
2025-10-12 | 2025-10-12 | 2025-10-16 | Karni Const 1 | 15.8578 | 3.1716 | TA506 | 2/7 | Completed
2025-10-12 | 2025-10-12 | 2025-10-17 | Karni Const 2 | 48.342 | 8.057 | TA506 | 9/0 | Completed
2025-10-12 | 2025-10-10 | 2025-10-14 | Karni Const 3 | 15.8578 | 3.1716 | TA506 | 12/5 | Completed
2025-10-12 | 2025-10-07 | 2025-10-12 | Karni Const 4 | 15.8578 | 2.643 | TA506 | 19/4 | Completed
2025-10-12 | 2025-10-08 | 2025-10-15 | Karni Const 4 | 21.0969 | 2.6371 | TA506 | 19/5 | Completed
2025-10-12 | 2025-10-10 | 2025-10-15 | Karni Const 5 | 27.0921 | 4.5154 | TA506 | 13/0 | Completed
2025-10-12 | 2025-10-11 | 2025-10-14 | Karni Const 6 | 16.4524 | 4.1131 | TA506 | 51C/2 | Completed
2025-10-12 | 2025-10-11 | 2025-10-15 | Pankaj Const | 21.0969 | 4.2194 | TA506 | 205/1 | Completed
2025-10-12 | 2025-10-11 | 2025-10-16 | Pankaj Const | 36.85 | 6.1417 | TA506 | 213/0 | Completed
2025-10-12 | 2025-10-08 | 2025-10-14 | Tejal Const | 29.7779 | 4.254 | TA506 | 142/0 | Completed
2025-10-13 | 2025-10-13 | 2025-10-17 | Govind Mahto | 22.4884 | 4.4977 | TA506 | 220/7 | Completed
2025-10-13 | 2025-10-09 | 2025-10-14 | Horil Mahto | 22.4884 | 3.7481 | TA506 | 193/2 | Completed
2025-10-13 | 2025-10-13 | 2025-10-20 | Horil Mahto | 31.8647 | 3.9831 | TA506 | 205/0 | Completed
2025-10-13 | 2025-10-10 | 2025-10-16 | Jai Prakash Mahto | 34.17 | 4.8814 | TA506 | 65A/0 | Completed
2025-10-13 | 2025-10-10 | 2025-10-14 | Karni Const 1 | 15.8578 | 3.1716 | TA506 | 2/8 | Completed
2025-10-13 | 2025-10-12 | 2025-10-16 | Karni Const 1 | 15.8578 | 3.1716 | TA506 | 2/7 | Completed
2025-10-13 | 2025-10-12 | 2025-10-17 | Karni Const 2 | 48.342 | 8.057 | TA506 | 9/0 | Completed
2025-10-13 | 2025-10-10 | 2025-10-14 | Karni Const 3 | 15.8578 | 3.1716 | TA506 | 12/5 | Completed
2025-10-13 | 2025-10-08 | 2025-10-15 | Karni Const 4 | 21.0969 | 2.6371 | TA506 | 19/5 | Completed
2025-10-13 | 2025-10-10 | 2025-10-15 | Karni Const 5 | 27.0921 | 4.5154 | TA506 | 13/0 | Completed
2025-10-13 | 2025-10-11 | 2025-10-14 | Karni Const 6 | 16.4524 | 4.1131 | TA506 | 51C/2 | Completed
2025-10-13 | 2025-10-11 | 2025-10-15 | Pankaj Const | 21.0969 | 4.2194 | TA506 | 205/1 | Completed
2025-10-13 | 2025-10-11 | 2025-10-16 | Pankaj Const | 36.85 | 6.1417 | TA506 | 213/0 | Completed
2025-10-13 | 2025-10-08 | 2025-10-14 | Tejal Const | 29.7779 | 4.254 | TA506 | 142/0 | Completed
2025-10-14 | 2025-10-13 | 2025-10-17 | Govind Mahto | 22.4884 | 4.4977 | TA506 | 220/7 | Completed
2025-10-14 | 2025-10-09 | 2025-10-14 | Horil Mahto | 22.4884 | 3.7481 | TA506 | 193/2 | Completed
2025-10-14 | 2025-10-13 | 2025-10-20 | Horil Mahto | 31.8647 | 3.9831 | TA506 | 205/0 | Completed
2025-10-14 | 2025-10-10 | 2025-10-16 | Jai Prakash Mahto | 34.17 | 4.8814 | TA506 | 65A/0 | Completed
2025-10-14 | 2025-10-10 | 2025-10-14 | Karni Const 1 | 15.8578 | 3.1716 | TA506 | 2/8 | Completed
2025-10-14 | 2025-10-12 | 2025-10-16 | Karni Const 1 | 15.8578 | 3.1716 | TA506 | 2/7 | Completed
2025-10-14 | 2025-10-12 | 2025-10-17 | Karni Const 2 | 48.342 | 8.057 | TA506 | 9/0 | Completed
2025-10-14 | 2025-10-10 | 2025-10-14 | Karni Const 3 | 15.8578 | 3.1716 | TA506 | 12/5 | Completed
2025-10-14 | 2025-10-14 | 2025-10-17 | Karni Const 3 | 16.9667 | 4.2417 | TA506 | 12/6 | Completed
2025-10-14 | 2025-10-08 | 2025-10-15 | Karni Const 4 | 21.0969 | 2.6371 | TA506 | 19/5 | Completed
2025-10-14 | 2025-10-10 | 2025-10-15 | Karni Const 5 | 27.0921 | 4.5154 | TA506 | 13/0 | Completed
2025-10-14 | 2025-10-11 | 2025-10-14 | Karni Const 6 | 16.4524 | 4.1131 | TA506 | 51C/2 | Completed
2025-10-14 | 2025-10-11 | 2025-10-15 | Pankaj Const | 21.0969 | 4.2194 | TA506 | 205/1 | Completed
2025-10-14 | 2025-10-11 | 2025-10-16 | Pankaj Const | 36.85 | 6.1417 | TA506 | 213/0 | Completed
2025-10-14 | 2025-10-08 | 2025-10-14 | Tejal Const | 29.7779 | 4.254 | TA506 | 142/0 | Completed
2025-10-15 | 2025-10-13 | 2025-10-17 | Govind Mahto | 22.4884 | 4.4977 | TA506 | 220/7 | Completed
2025-10-15 | 2025-10-13 | 2025-10-20 | Horil Mahto | 31.8647 | 3.9831 | TA506 | 205/0 | Completed
2025-10-15 | 2025-10-10 | 2025-10-16 | Jai Prakash Mahto | 34.17 | 4.8814 | TA506 | 65A/0 | Completed
2025-10-15 | 2025-10-12 | 2025-10-16 | Karni Const 1 | 15.8578 | 3.1716 | TA506 | 2/7 | Completed
2025-10-15 | 2025-10-12 | 2025-10-17 | Karni Const 2 | 48.342 | 8.057 | TA506 | 9/0 | Completed
2025-10-15 | 2025-10-14 | 2025-10-17 | Karni Const 3 | 16.9667 | 4.2417 | TA506 | 12/6 | Completed
2025-10-15 | 2025-10-08 | 2025-10-15 | Karni Const 4 | 21.0969 | 2.6371 | TA506 | 19/5 | Completed
2025-10-15 | 2025-10-10 | 2025-10-15 | Karni Const 5 | 27.0921 | 4.5154 | TA506 | 13/0 | Completed
2025-10-15 | 2025-10-11 | 2025-10-15 | Pankaj Const | 21.0969 | 4.2194 | TA506 | 205/1 | Completed
2025-10-15 | 2025-10-11 | 2025-10-16 | Pankaj Const | 36.85 | 6.1417 | TA506 | 213/0 | Completed
2025-10-16 | 2025-10-13 | 2025-10-17 | Govind Mahto | 22.4884 | 4.4977 | TA506 | 220/7 | Completed
2025-10-16 | 2025-10-16 | 2025-10-18 | Gulab Mahto | 18.1188 | 6.0396 | TA506 | 1/1 | Completed
2025-10-16 | 2025-10-13 | 2025-10-20 | Horil Mahto | 31.8647 | 3.9831 | TA506 | 205/0 | Completed
2025-10-16 | 2025-10-10 | 2025-10-16 | Jai Prakash Mahto | 34.17 | 4.8814 | TA506 | 65A/0 | Completed
2025-10-16 | 2025-10-12 | 2025-10-16 | Karni Const 1 | 15.8578 | 3.1716 | TA506 | 2/7 | Completed
2025-10-16 | 2025-10-12 | 2025-10-17 | Karni Const 2 | 48.342 | 8.057 | TA506 | 9/0 | Completed
2025-10-16 | 2025-10-14 | 2025-10-17 | Karni Const 3 | 16.9667 | 4.2417 | TA506 | 12/6 | Completed
2025-10-16 | 2025-10-16 | 2025-10-21 | Karni Const 5 | 27.0921 | 4.5154 | TA506 | 51C/0 | Completed
2025-10-16 | 2025-10-11 | 2025-10-16 | Pankaj Const | 36.85 | 6.1417 | TA506 | 213/0 | Completed
2025-10-17 | 2025-10-13 | 2025-10-17 | Govind Mahto | 22.4884 | 4.4977 | TA506 | 220/7 | Completed
2025-10-17 | 2025-10-16 | 2025-10-18 | Gulab Mahto | 18.1188 | 6.0396 | TA506 | 1/1 | Completed
2025-10-17 | 2025-10-13 | 2025-10-20 | Horil Mahto | 31.8647 | 3.9831 | TA506 | 205/0 | Completed
2025-10-17 | 2025-10-12 | 2025-10-17 | Karni Const 2 | 48.342 | 8.057 | TA506 | 9/0 | Completed
2025-10-17 | 2025-10-14 | 2025-10-17 | Karni Const 3 | 16.9667 | 4.2417 | TA506 | 12/6 | Completed
2025-10-17 | 2025-10-16 | 2025-10-21 | Karni Const 5 | 27.0921 | 4.5154 | TA506 | 51C/0 | Completed
2025-10-17 | 2025-10-17 | 2025-10-22 | Khemlal Mahto | 22.4884 | 3.7481 | TA506 | 211/7 | Completed
2025-10-18 | 2025-10-16 | 2025-10-18 | Gulab Mahto | 18.1188 | 6.0396 | TA506 | 1/1 | Completed
2025-10-18 | 2025-10-13 | 2025-10-20 | Horil Mahto | 31.8647 | 3.9831 | TA506 | 205/0 | Completed
2025-10-18 | 2025-10-18 | 2025-10-24 | Horil Mahto | 18.1188 | 2.5884 | TA506 | 193/1 | Completed
2025-10-18 | 2025-10-18 | 2025-10-21 | Karni Const 3 | 16.9667 | 4.2417 | TA506 | 12/7 | Completed
2025-10-18 | 2025-10-18 | 2025-10-24 | Karni Const 4 | 46.4686 | 6.6384 | TA506 | 42/0 | Completed
2025-10-18 | 2025-10-16 | 2025-10-21 | Karni Const 5 | 27.0921 | 4.5154 | TA506 | 51C/0 | Completed
2025-10-18 | 2025-10-17 | 2025-10-22 | Khemlal Mahto | 22.4884 | 3.7481 | TA506 | 211/7 | Completed
2025-10-19 | 2025-10-19 | 2025-10-26 | Ab Const | 21.0969 | 2.6371 | TA506 | 101/1 | Completed
2025-10-19 | 2025-10-19 | 2025-10-22 | Govind Mahto | 21.0969 | 5.2742 | TA506 | 220/6 | Completed
2025-10-19 | 2025-10-19 | 2025-10-21 | Gulab Mahto | 18.1188 | 6.0396 | TA506 | 1/2 | Completed
2025-10-19 | 2025-10-13 | 2025-10-20 | Horil Mahto | 31.8647 | 3.9831 | TA506 | 205/0 | Completed
2025-10-19 | 2025-10-18 | 2025-10-24 | Horil Mahto | 18.1188 | 2.5884 | TA506 | 193/1 | Completed
2025-10-19 | 2025-10-18 | 2025-10-21 | Karni Const 3 | 16.9667 | 4.2417 | TA506 | 12/7 | Completed
2025-10-19 | 2025-10-18 | 2025-10-24 | Karni Const 4 | 46.4686 | 6.6384 | TA506 | 42/0 | Completed
2025-10-19 | 2025-10-16 | 2025-10-21 | Karni Const 5 | 27.0921 | 4.5154 | TA506 | 51C/0 | Completed
2025-10-19 | 2025-10-19 | 2025-10-28 | Karni Const 5 | 36.5854 | 3.6585 | TA506 | 53/0 | Completed
2025-10-19 | 2025-10-17 | 2025-10-22 | Khemlal Mahto | 22.4884 | 3.7481 | TA506 | 211/7 | Completed
2025-10-20 | 2025-10-19 | 2025-10-26 | Ab Const | 21.0969 | 2.6371 | TA506 | 101/1 | Completed
2025-10-20 | 2025-10-19 | 2025-10-22 | Govind Mahto | 21.0969 | 5.2742 | TA506 | 220/6 | Completed
2025-10-20 | 2025-10-19 | 2025-10-21 | Gulab Mahto | 18.1188 | 6.0396 | TA506 | 1/2 | Completed
2025-10-20 | 2025-10-13 | 2025-10-20 | Horil Mahto | 31.8647 | 3.9831 | TA506 | 205/0 | Completed
2025-10-20 | 2025-10-18 | 2025-10-24 | Horil Mahto | 18.1188 | 2.5884 | TA506 | 193/1 | Completed
2025-10-20 | 2025-10-20 | 2025-10-27 | Jai Prakash Mahto | 53.1226 | 6.6403 | TA506 | 65/0 | Completed
2025-10-20 | 2025-10-20 | 2025-10-28 | Karni Const 2 | 48.342 | 5.3713 | TA506 | 10/0 | Completed
2025-10-20 | 2025-10-18 | 2025-10-21 | Karni Const 3 | 16.9667 | 4.2417 | TA506 | 12/7 | Completed
2025-10-20 | 2025-10-18 | 2025-10-24 | Karni Const 4 | 46.4686 | 6.6384 | TA506 | 42/0 | Completed
2025-10-20 | 2025-10-16 | 2025-10-21 | Karni Const 5 | 27.0921 | 4.5154 | TA506 | 51C/0 | Completed
2025-10-20 | 2025-10-19 | 2025-10-28 | Karni Const 5 | 36.5854 | 3.6585 | TA506 | 53/0 | Completed
2025-10-20 | 2025-10-17 | 2025-10-22 | Khemlal Mahto | 22.4884 | 3.7481 | TA506 | 211/7 | Completed
2025-10-21 | 2025-10-19 | 2025-10-26 | Ab Const | 21.0969 | 2.6371 | TA506 | 101/1 | Completed
2025-10-21 | 2025-10-19 | 2025-10-22 | Govind Mahto | 21.0969 | 5.2742 | TA506 | 220/6 | Completed
2025-10-21 | 2025-10-19 | 2025-10-21 | Gulab Mahto | 18.1188 | 6.0396 | TA506 | 1/2 | Completed
2025-10-21 | 2025-10-18 | 2025-10-24 | Horil Mahto | 18.1188 | 2.5884 | TA506 | 193/1 | Completed
2025-10-21 | 2025-10-21 | 2025-10-24 | Horil Mahto | 18.1188 | 4.5297 | TA506 | 205/2 | Completed
2025-10-21 | 2025-10-20 | 2025-10-27 | Jai Prakash Mahto | 53.1226 | 6.6403 | TA506 | 65/0 | Completed
2025-10-21 | 2025-10-20 | 2025-10-28 | Karni Const 2 | 48.342 | 5.3713 | TA506 | 10/0 | Completed
2025-10-21 | 2025-10-18 | 2025-10-21 | Karni Const 3 | 16.9667 | 4.2417 | TA506 | 12/7 | Completed
2025-10-21 | 2025-10-18 | 2025-10-24 | Karni Const 4 | 46.4686 | 6.6384 | TA506 | 42/0 | Completed
2025-10-21 | 2025-10-16 | 2025-10-21 | Karni Const 5 | 27.0921 | 4.5154 | TA506 | 51C/0 | Completed
2025-10-21 | 2025-10-19 | 2025-10-28 | Karni Const 5 | 36.5854 | 3.6585 | TA506 | 53/0 | Completed
2025-10-21 | 2025-10-17 | 2025-10-22 | Khemlal Mahto | 22.4884 | 3.7481 | TA506 | 211/7 | Completed
2025-10-22 | 2025-10-19 | 2025-10-26 | Ab Const | 21.0969 | 2.6371 | TA506 | 101/1 | Completed
2025-10-22 | 2025-10-19 | 2025-10-22 | Govind Mahto | 21.0969 | 5.2742 | TA506 | 220/6 | Completed
2025-10-22 | 2025-10-22 | 2025-10-25 | Gulab Mahto | 16.9667 | 4.2417 | TA506 | 1/3 | Completed
2025-10-22 | 2025-10-18 | 2025-10-24 | Horil Mahto | 18.1188 | 2.5884 | TA506 | 193/1 | Completed
2025-10-22 | 2025-10-21 | 2025-10-24 | Horil Mahto | 18.1188 | 4.5297 | TA506 | 205/2 | Completed
2025-10-22 | 2025-10-20 | 2025-10-27 | Jai Prakash Mahto | 53.1226 | 6.6403 | TA506 | 65/0 | Completed
2025-10-22 | 2025-10-20 | 2025-10-28 | Karni Const 2 | 48.342 | 5.3713 | TA506 | 10/0 | Completed
2025-10-22 | 2025-10-18 | 2025-10-24 | Karni Const 4 | 46.4686 | 6.6384 | TA506 | 42/0 | Completed
2025-10-22 | 2025-10-19 | 2025-10-28 | Karni Const 5 | 36.5854 | 3.6585 | TA506 | 53/0 | Completed
2025-10-22 | 2025-10-17 | 2025-10-22 | Khemlal Mahto | 22.4884 | 3.7481 | TA506 | 211/7 | Completed
2025-10-23 | 2025-10-19 | 2025-10-26 | Ab Const | 21.0969 | 2.6371 | TA506 | 101/1 | Completed
2025-10-23 | 2025-10-22 | 2025-10-25 | Gulab Mahto | 16.9667 | 4.2417 | TA506 | 1/3 | Completed
2025-10-23 | 2025-10-18 | 2025-10-24 | Horil Mahto | 18.1188 | 2.5884 | TA506 | 193/1 | Completed
2025-10-23 | 2025-10-21 | 2025-10-24 | Horil Mahto | 18.1188 | 4.5297 | TA506 | 205/2 | Completed
2025-10-23 | 2025-10-20 | 2025-10-27 | Jai Prakash Mahto | 53.1226 | 6.6403 | TA506 | 65/0 | Completed
2025-10-23 | 2025-10-20 | 2025-10-28 | Karni Const 2 | 48.342 | 5.3713 | TA506 | 10/0 | Completed
2025-10-23 | 2025-10-18 | 2025-10-24 | Karni Const 4 | 46.4686 | 6.6384 | TA506 | 42/0 | Completed
2025-10-23 | 2025-10-19 | 2025-10-28 | Karni Const 5 | 36.5854 | 3.6585 | TA506 | 53/0 | Completed
2025-10-24 | 2025-10-19 | 2025-10-26 | Ab Const | 21.0969 | 2.6371 | TA506 | 101/1 | Completed
2025-10-24 | 2025-10-22 | 2025-10-25 | Gulab Mahto | 16.9667 | 4.2417 | TA506 | 1/3 | Completed
2025-10-24 | 2025-10-18 | 2025-10-24 | Horil Mahto | 18.1188 | 2.5884 | TA506 | 193/1 | Completed
2025-10-24 | 2025-10-21 | 2025-10-24 | Horil Mahto | 18.1188 | 4.5297 | TA506 | 205/2 | Completed
2025-10-24 | 2025-10-20 | 2025-10-27 | Jai Prakash Mahto | 53.1226 | 6.6403 | TA506 | 65/0 | Completed
2025-10-24 | 2025-10-20 | 2025-10-28 | Karni Const 2 | 48.342 | 5.3713 | TA506 | 10/0 | Completed
2025-10-24 | 2025-10-18 | 2025-10-24 | Karni Const 4 | 46.4686 | 6.6384 | TA506 | 42/0 | Completed
2025-10-24 | 2025-10-19 | 2025-10-28 | Karni Const 5 | 36.5854 | 3.6585 | TA506 | 53/0 | Completed
2025-10-24 | 2025-10-24 | 2025-10-29 | Prem Kumar | 39.5967 | 6.5994 | TA506 | 60/0 | Completed
2025-10-25 | 2025-10-19 | 2025-10-26 | Ab Const | 21.0969 | 2.6371 | TA506 | 101/1 | Completed
2025-10-25 | 2025-10-22 | 2025-10-25 | Gulab Mahto | 16.9667 | 4.2417 | TA506 | 1/3 | Completed
2025-10-25 | 2025-10-20 | 2025-10-27 | Jai Prakash Mahto | 53.1226 | 6.6403 | TA506 | 65/0 | Completed
2025-10-25 | 2025-10-20 | 2025-10-28 | Karni Const 2 | 48.342 | 5.3713 | TA506 | 10/0 | Completed
2025-10-25 | 2025-10-19 | 2025-10-28 | Karni Const 5 | 36.5854 | 3.6585 | TA506 | 53/0 | Completed
2025-10-25 | 2025-10-24 | 2025-10-29 | Prem Kumar | 39.5967 | 6.5994 | TA506 | 60/0 | Completed
2025-10-26 | 2025-10-19 | 2025-10-26 | Ab Const | 21.0969 | 2.6371 | TA506 | 101/1 | Completed
2025-10-26 | 2025-10-26 | 2025-10-29 | Gulab Mahto | 18.1188 | 4.5297 | TA506 | 1/7 | Completed
2025-10-26 | 2025-10-20 | 2025-10-27 | Jai Prakash Mahto | 53.1226 | 6.6403 | TA506 | 65/0 | Completed
2025-10-26 | 2025-10-26 | 2025-10-30 | Jai Prakash Mahto | 22.4884 | 4.4977 | TA506 | 64A/3 | Completed
2025-10-26 | 2025-10-20 | 2025-10-28 | Karni Const 2 | 48.342 | 5.3713 | TA506 | 10/0 | Completed
2025-10-26 | 2025-10-26 | 2025-10-31 | Karni Const 3 | 39.6224 | 6.6037 | TA506 | 14/0 | Completed
2025-10-26 | 2025-10-19 | 2025-10-28 | Karni Const 5 | 36.5854 | 3.6585 | TA506 | 53/0 | Completed
2025-10-26 | 2025-10-24 | 2025-10-29 | Prem Kumar | 39.5967 | 6.5994 | TA506 | 60/0 | Completed
2025-10-27 | 2025-10-27 | 2025-10-31 | Ab Const | 17.6337 | 3.5267 | TA506 | 97/1 | Completed
2025-10-27 | 2025-10-27 | 2025-10-31 | Binod Mahto | 22.4884 | 4.4977 | TA506 | 167/1 | Completed
2025-10-27 | 2025-10-26 | 2025-10-29 | Gulab Mahto | 18.1188 | 4.5297 | TA506 | 1/7 | Completed
2025-10-27 | 2025-10-20 | 2025-10-27 | Jai Prakash Mahto | 53.1226 | 6.6403 | TA506 | 65/0 | Completed
2025-10-27 | 2025-10-26 | 2025-10-30 | Jai Prakash Mahto | 22.4884 | 4.4977 | TA506 | 64A/3 | Completed
2025-10-27 | 2025-10-20 | 2025-10-28 | Karni Const 2 | 48.342 | 5.3713 | TA506 | 10/0 | Completed
2025-10-27 | 2025-10-26 | 2025-10-31 | Karni Const 3 | 39.6224 | 6.6037 | TA506 | 14/0 | Completed
2025-10-27 | 2025-10-19 | 2025-10-28 | Karni Const 5 | 36.5854 | 3.6585 | TA506 | 53/0 | Completed
2025-10-27 | 2025-10-24 | 2025-10-29 | Prem Kumar | 39.5967 | 6.5994 | TA506 | 60/0 | Completed
2025-10-28 | 2025-10-27 | 2025-10-31 | Ab Const | 17.6337 | 3.5267 | TA506 | 97/1 | Completed
2025-10-28 | 2025-10-27 | 2025-10-31 | Binod Mahto | 22.4884 | 4.4977 | TA506 | 167/1 | Completed
2025-10-28 | 2025-10-26 | 2025-10-29 | Gulab Mahto | 18.1188 | 4.5297 | TA506 | 1/7 | Completed
2025-10-28 | 2025-10-28 | 2025-10-31 | Gulab Mahto | 18.1188 | 4.5297 | TA506 | 1/6 | Completed
2025-10-28 | 2025-10-26 | 2025-10-30 | Jai Prakash Mahto | 22.4884 | 4.4977 | TA506 | 64A/3 | Completed
2025-10-28 | 2025-10-20 | 2025-10-28 | Karni Const 2 | 48.342 | 5.3713 | TA506 | 10/0 | Completed
2025-10-28 | 2025-10-28 | 2025-11-01 | Karni Const 2 | 17.6337 | 3.5267 | TA506 | 12/2 | Completed
2025-10-28 | 2025-10-26 | 2025-10-31 | Karni Const 3 | 39.6224 | 6.6037 | TA506 | 14/0 | Completed
2025-10-28 | 2025-10-19 | 2025-10-28 | Karni Const 5 | 36.5854 | 3.6585 | TA506 | 53/0 | Completed
2025-10-28 | 2025-10-24 | 2025-10-29 | Prem Kumar | 39.5967 | 6.5994 | TA506 | 60/0 | Completed
2025-10-29 | 2025-10-27 | 2025-10-31 | Ab Const | 17.6337 | 3.5267 | TA506 | 97/1 | Completed
2025-10-29 | 2025-10-27 | 2025-10-31 | Binod Mahto | 22.4884 | 4.4977 | TA506 | 167/1 | Completed
2025-10-29 | 2025-10-29 | 2025-11-03 | Binod Mahto | 38.1379 | 6.3563 | TA506 | 167A/0 | Completed
2025-10-29 | 2025-10-29 | 2025-11-01 | Govind Mahto | 16.4524 | 4.1131 | TA506 | 220/5 | Completed
2025-10-29 | 2025-10-26 | 2025-10-29 | Gulab Mahto | 18.1188 | 4.5297 | TA506 | 1/7 | Completed
2025-10-29 | 2025-10-28 | 2025-10-31 | Gulab Mahto | 18.1188 | 4.5297 | TA506 | 1/6 | Completed
2025-10-29 | 2025-10-29 | 2025-11-02 | Horil Mahto | 18.1188 | 3.6238 | TA506 | 197/2 | Completed
2025-10-29 | 2025-10-26 | 2025-10-30 | Jai Prakash Mahto | 22.4884 | 4.4977 | TA506 | 64A/3 | Completed
2025-10-29 | 2025-10-29 | 2025-11-01 | Jai Prakash Mahto | 29.7779 | 7.4445 | TA506 | 65A/3 | Completed
2025-10-29 | 2025-10-28 | 2025-11-01 | Karni Const 2 | 17.6337 | 3.5267 | TA506 | 12/2 | Completed
2025-10-29 | 2025-10-26 | 2025-10-31 | Karni Const 3 | 39.6224 | 6.6037 | TA506 | 14/0 | Completed
2025-10-29 | 2025-10-29 | 2025-11-01 | Karni Const 5 | 16.4524 | 4.1131 | TA506 | 52/1 | Completed
2025-10-29 | 2025-10-24 | 2025-10-29 | Prem Kumar | 39.5967 | 6.5994 | TA506 | 60/0 | Completed
2025-10-30 | 2025-10-27 | 2025-10-31 | Ab Const | 17.6337 | 3.5267 | TA506 | 97/1 | Completed
2025-10-30 | 2025-10-27 | 2025-10-31 | Binod Mahto | 22.4884 | 4.4977 | TA506 | 167/1 | Completed
2025-10-30 | 2025-10-29 | 2025-11-03 | Binod Mahto | 38.1379 | 6.3563 | TA506 | 167A/0 | Completed
2025-10-30 | 2025-10-29 | 2025-11-01 | Govind Mahto | 16.4524 | 4.1131 | TA506 | 220/5 | Completed
2025-10-30 | 2025-10-28 | 2025-10-31 | Gulab Mahto | 18.1188 | 4.5297 | TA506 | 1/6 | Completed
2025-10-30 | 2025-10-30 | 2025-11-02 | Gulab Mahto | 17.6337 | 4.4084 | TA506 | 1/8 | Completed
2025-10-30 | 2025-10-29 | 2025-11-02 | Horil Mahto | 18.1188 | 3.6238 | TA506 | 197/2 | Completed
2025-10-30 | 2025-10-26 | 2025-10-30 | Jai Prakash Mahto | 22.4884 | 4.4977 | TA506 | 64A/3 | Completed
2025-10-30 | 2025-10-29 | 2025-11-01 | Jai Prakash Mahto | 29.7779 | 7.4445 | TA506 | 65A/3 | Completed
2025-10-30 | 2025-10-28 | 2025-11-01 | Karni Const 2 | 17.6337 | 3.5267 | TA506 | 12/2 | Completed
2025-10-30 | 2025-10-26 | 2025-10-31 | Karni Const 3 | 39.6224 | 6.6037 | TA506 | 14/0 | Completed
2025-10-30 | 2025-10-30 | 2025-11-01 | Karni Const 4 | 16.9667 | 5.6556 | TA506 | 42/2 | Completed
2025-10-30 | 2025-10-29 | 2025-11-01 | Karni Const 5 | 16.4524 | 4.1131 | TA506 | 52/1 | Completed
2025-10-31 | 2025-10-27 | 2025-10-31 | Ab Const | 17.6337 | 3.5267 | TA506 | 97/1 | Completed
2025-10-31 | 2025-10-27 | 2025-10-31 | Binod Mahto | 22.4884 | 4.4977 | TA506 | 167/1 | Completed
2025-10-31 | 2025-10-29 | 2025-11-03 | Binod Mahto | 38.1379 | 6.3563 | TA506 | 167A/0 | Completed
2025-10-31 | 2025-10-29 | 2025-11-01 | Govind Mahto | 16.4524 | 4.1131 | TA506 | 220/5 | Completed
2025-10-31 | 2025-10-31 | 2025-11-03 | Govind Mahto | 18.1188 | 4.5297 | TA506 | 220/8 | Completed
2025-10-31 | 2025-10-28 | 2025-10-31 | Gulab Mahto | 18.1188 | 4.5297 | TA506 | 1/6 | Completed
2025-10-31 | 2025-10-30 | 2025-11-02 | Gulab Mahto | 17.6337 | 4.4084 | TA506 | 1/8 | Completed
2025-10-31 | 2025-10-29 | 2025-11-02 | Horil Mahto | 18.1188 | 3.6238 | TA506 | 197/2 | Completed
2025-10-31 | 2025-10-29 | 2025-11-01 | Jai Prakash Mahto | 29.7779 | 7.4445 | TA506 | 65A/3 | Completed
2025-10-31 | 2025-10-28 | 2025-11-01 | Karni Const 2 | 17.6337 | 3.5267 | TA506 | 12/2 | Completed
2025-10-31 | 2025-10-26 | 2025-10-31 | Karni Const 3 | 39.6224 | 6.6037 | TA506 | 14/0 | Completed
2025-10-31 | 2025-10-30 | 2025-11-01 | Karni Const 4 | 16.9667 | 5.6556 | TA506 | 42/2 | Completed
2025-10-31 | 2025-10-29 | 2025-11-01 | Karni Const 5 | 16.4524 | 4.1131 | TA506 | 52/1 | Completed
2025-11-01 | 2025-10-29 | 2025-11-03 | Binod Mahto | 38.1379 | 6.3563 | TA506 | 167A/0 | Completed
2025-11-01 | 2025-10-29 | 2025-11-01 | Govind Mahto | 16.4524 | 4.1131 | TA506 | 220/5 | Completed
2025-11-01 | 2025-10-31 | 2025-11-03 | Govind Mahto | 18.1188 | 4.5297 | TA506 | 220/8 | Completed
2025-11-01 | 2025-10-30 | 2025-11-02 | Gulab Mahto | 17.6337 | 4.4084 | TA506 | 1/8 | Completed
2025-11-01 | 2025-11-01 | 2025-11-05 | Gulab Mahto | 17.6337 | 3.5267 | TA506 | 1/9 | Completed
2025-11-01 | 2025-10-29 | 2025-11-02 | Horil Mahto | 18.1188 | 3.6238 | TA506 | 197/2 | Completed
2025-11-01 | 2025-10-29 | 2025-11-01 | Jai Prakash Mahto | 29.7779 | 7.4445 | TA506 | 65A/3 | Completed
2025-11-01 | 2025-11-01 | 2025-11-04 | Karni Const 1 | 15.8578 | 3.9644 | TA506 | 12/8 | Completed
2025-11-01 | 2025-10-28 | 2025-11-01 | Karni Const 2 | 17.6337 | 3.5267 | TA506 | 12/2 | Completed
2025-11-01 | 2025-10-30 | 2025-11-01 | Karni Const 4 | 16.9667 | 5.6556 | TA506 | 42/2 | Completed
2025-11-01 | 2025-10-29 | 2025-11-01 | Karni Const 5 | 16.4524 | 4.1131 | TA506 | 52/1 | Completed
2025-11-02 | 2025-10-29 | 2025-11-03 | Binod Mahto | 38.1379 | 6.3563 | TA506 | 167A/0 | Completed
2025-11-02 | 2025-10-31 | 2025-11-03 | Govind Mahto | 18.1188 | 4.5297 | TA506 | 220/8 | Completed
2025-11-02 | 2025-10-30 | 2025-11-02 | Gulab Mahto | 17.6337 | 4.4084 | TA506 | 1/8 | Completed
2025-11-02 | 2025-11-01 | 2025-11-05 | Gulab Mahto | 17.6337 | 3.5267 | TA506 | 1/9 | Completed
2025-11-02 | 2025-10-29 | 2025-11-02 | Horil Mahto | 18.1188 | 3.6238 | TA506 | 197/2 | Completed
2025-11-02 | 2025-11-02 | 2025-11-06 | Horil Mahto | 31.8647 | 6.3729 | TA506 | 95/0 | Completed
2025-11-02 | 2025-11-02 | 2025-11-05 | Jai Prakash Mahto | 16.9667 | 4.2417 | TA506 | 64A/2 | Completed
2025-11-02 | 2025-11-01 | 2025-11-04 | Karni Const 1 | 15.8578 | 3.9644 | TA506 | 12/8 | Completed
2025-11-02 | 2025-11-02 | 2025-11-09 | Khemlal Mahto | 36.5854 | 4.5732 | TA506 | 76F/0 | Completed
2025-11-02 | 2025-11-02 | 2025-11-06 | Tejal Mahto | 39.6224 | 7.9245 | TA506 | 110/0 | Completed
2025-11-03 | 2025-10-29 | 2025-11-03 | Binod Mahto | 38.1379 | 6.3563 | TA506 | 167A/0 | Completed
2025-11-03 | 2025-10-31 | 2025-11-03 | Govind Mahto | 18.1188 | 4.5297 | TA506 | 220/8 | Completed
2025-11-03 | 2025-11-01 | 2025-11-05 | Gulab Mahto | 17.6337 | 3.5267 | TA506 | 1/9 | Completed
2025-11-03 | 2025-11-02 | 2025-11-06 | Horil Mahto | 31.8647 | 6.3729 | TA506 | 95/0 | Completed
2025-11-03 | 2025-11-02 | 2025-11-05 | Jai Prakash Mahto | 16.9667 | 4.2417 | TA506 | 64A/2 | Completed
2025-11-03 | 2025-11-01 | 2025-11-04 | Karni Const 1 | 15.8578 | 3.9644 | TA506 | 12/8 | Completed
2025-11-03 | 2025-11-03 | 2025-11-10 | Karni Const 2 | 48.342 | 6.0427 | TA506 | 28/0 | Completed
2025-11-03 | 2025-11-02 | 2025-11-09 | Khemlal Mahto | 36.5854 | 4.5732 | TA506 | 76F/0 | Completed
2025-11-03 | 2025-11-02 | 2025-11-06 | Tejal Mahto | 39.6224 | 7.9245 | TA506 | 110/0 | Completed
2025-11-04 | 2025-11-01 | 2025-11-05 | Gulab Mahto | 17.6337 | 3.5267 | TA506 | 1/9 | Completed
2025-11-04 | 2025-11-02 | 2025-11-06 | Horil Mahto | 31.8647 | 6.3729 | TA506 | 95/0 | Completed
2025-11-04 | 2025-11-02 | 2025-11-05 | Jai Prakash Mahto | 16.9667 | 4.2417 | TA506 | 64A/2 | Completed
2025-11-04 | 2025-11-04 | 2025-11-09 | Jai Prakash Mahto | 21.0969 | 3.5162 | TA506 | 64A/1 | Completed
2025-11-04 | 2025-11-01 | 2025-11-04 | Karni Const 1 | 15.8578 | 3.9644 | TA506 | 12/8 | Completed
2025-11-04 | 2025-11-03 | 2025-11-10 | Karni Const 2 | 48.342 | 6.0427 | TA506 | 28/0 | Completed
2025-11-04 | 2025-11-04 | 2025-11-08 | Karni Const 3 | 38.1379 | 7.6276 | TA506 | 15/0 | Completed
2025-11-04 | 2025-11-02 | 2025-11-09 | Khemlal Mahto | 36.5854 | 4.5732 | TA506 | 76F/0 | Completed
2025-11-04 | 2025-11-02 | 2025-11-06 | Tejal Mahto | 39.6224 | 7.9245 | TA506 | 110/0 | Completed
2025-11-05 | 2025-11-05 | 2025-11-08 | Ab Const | 22.4884 | 5.6221 | TA506 | 94/1 | Completed
2025-11-05 | 2025-11-01 | 2025-11-05 | Gulab Mahto | 17.6337 | 3.5267 | TA506 | 1/9 | Completed
2025-11-05 | 2025-11-05 | 2025-11-07 | Gulab Mahto | 16.9667 | 5.6556 | TA506 | 1/10 | Completed
2025-11-05 | 2025-11-02 | 2025-11-06 | Horil Mahto | 31.8647 | 6.3729 | TA506 | 95/0 | Completed
2025-11-05 | 2025-11-02 | 2025-11-05 | Jai Prakash Mahto | 16.9667 | 4.2417 | TA506 | 64A/2 | Completed
2025-11-05 | 2025-11-04 | 2025-11-09 | Jai Prakash Mahto | 21.0969 | 3.5162 | TA506 | 64A/1 | Completed
2025-11-05 | 2025-11-03 | 2025-11-10 | Karni Const 2 | 48.342 | 6.0427 | TA506 | 28/0 | Completed
2025-11-05 | 2025-11-04 | 2025-11-08 | Karni Const 3 | 38.1379 | 7.6276 | TA506 | 15/0 | Completed
2025-11-05 | 2025-11-05 | 2025-11-12 | Karni Const 4 | 48.342 | 6.0427 | TA506 | 37/0 | Completed
2025-11-05 | 2025-11-02 | 2025-11-09 | Khemlal Mahto | 36.5854 | 4.5732 | TA506 | 76F/0 | Completed
2025-11-05 | 2025-11-02 | 2025-11-06 | Tejal Mahto | 39.6224 | 7.9245 | TA506 | 110/0 | Completed
2025-11-06 | 2025-11-05 | 2025-11-08 | Ab Const | 22.4884 | 5.6221 | TA506 | 94/1 | Completed
2025-11-06 | 2025-11-06 | 2025-11-11 | Govind Mahto | 36.5854 | 6.0976 | TA506 | 221/0 | Completed
2025-11-06 | 2025-11-05 | 2025-11-07 | Gulab Mahto | 16.9667 | 5.6556 | TA506 | 1/10 | Completed
2025-11-06 | 2025-11-02 | 2025-11-06 | Horil Mahto | 31.8647 | 6.3729 | TA506 | 95/0 | Completed
2025-11-06 | 2025-11-04 | 2025-11-09 | Jai Prakash Mahto | 21.0969 | 3.5162 | TA506 | 64A/1 | Completed
2025-11-06 | 2025-11-03 | 2025-11-10 | Karni Const 2 | 48.342 | 6.0427 | TA506 | 28/0 | Completed
2025-11-06 | 2025-11-04 | 2025-11-08 | Karni Const 3 | 38.1379 | 7.6276 | TA506 | 15/0 | Completed
2025-11-06 | 2025-11-05 | 2025-11-12 | Karni Const 4 | 48.342 | 6.0427 | TA506 | 37/0 | Completed
2025-11-06 | 2025-11-02 | 2025-11-09 | Khemlal Mahto | 36.5854 | 4.5732 | TA506 | 76F/0 | Completed
2025-11-06 | 2025-11-02 | 2025-11-06 | Tejal Mahto | 39.6224 | 7.9245 | TA506 | 110/0 | Completed
2025-11-07 | 2025-11-05 | 2025-11-08 | Ab Const | 22.4884 | 5.6221 | TA506 | 94/1 | Completed
2025-11-07 | 2025-11-06 | 2025-11-11 | Govind Mahto | 36.5854 | 6.0976 | TA506 | 221/0 | Completed
2025-11-07 | 2025-11-05 | 2025-11-07 | Gulab Mahto | 16.9667 | 5.6556 | TA506 | 1/10 | Completed
2025-11-07 | 2025-11-07 | 2025-11-11 | Gulab Mahto | 27.0921 | 5.4184 | TA506 | 2/0 | Completed
2025-11-07 | 2025-11-07 | 2025-11-12 | Horil Mahto | 36.5854 | 6.0976 | TA506 | 95A/0 | Completed
2025-11-07 | 2025-11-04 | 2025-11-09 | Jai Prakash Mahto | 21.0969 | 3.5162 | TA506 | 64A/1 | Completed
2025-11-07 | 2025-11-03 | 2025-11-10 | Karni Const 2 | 48.342 | 6.0427 | TA506 | 28/0 | Completed
2025-11-07 | 2025-11-04 | 2025-11-08 | Karni Const 3 | 38.1379 | 7.6276 | TA506 | 15/0 | Completed
2025-11-07 | 2025-11-05 | 2025-11-12 | Karni Const 4 | 48.342 | 6.0427 | TA506 | 37/0 | Completed
2025-11-07 | 2025-11-07 | 2025-11-13 | Karni Const 5 | 39.6224 | 5.6603 | TA506 | 55/0 | Completed
2025-11-07 | 2025-11-02 | 2025-11-09 | Khemlal Mahto | 36.5854 | 4.5732 | TA506 | 76F/0 | Completed
2025-11-08 | 2025-11-05 | 2025-11-08 | Ab Const | 22.4884 | 5.6221 | TA506 | 94/1 | Completed
2025-11-08 | 2025-11-06 | 2025-11-11 | Govind Mahto | 36.5854 | 6.0976 | TA506 | 221/0 | Completed
2025-11-08 | 2025-11-07 | 2025-11-11 | Gulab Mahto | 27.0921 | 5.4184 | TA506 | 2/0 | Completed
2025-11-08 | 2025-11-07 | 2025-11-12 | Horil Mahto | 36.5854 | 6.0976 | TA506 | 95A/0 | Completed
2025-11-08 | 2025-11-04 | 2025-11-09 | Jai Prakash Mahto | 21.0969 | 3.5162 | TA506 | 64A/1 | Completed
2025-11-08 | 2025-11-08 | 2025-11-11 | Karni Const 1 | 17.6337 | 4.4084 | TA506 | 34/2 | Completed
2025-11-08 | 2025-11-03 | 2025-11-10 | Karni Const 2 | 48.342 | 6.0427 | TA506 | 28/0 | Completed
2025-11-08 | 2025-11-04 | 2025-11-08 | Karni Const 3 | 38.1379 | 7.6276 | TA506 | 15/0 | Completed
2025-11-08 | 2025-11-05 | 2025-11-12 | Karni Const 4 | 48.342 | 6.0427 | TA506 | 37/0 | Completed
2025-11-08 | 2025-11-07 | 2025-11-13 | Karni Const 5 | 39.6224 | 5.6603 | TA506 | 55/0 | Completed
2025-11-08 | 2025-11-02 | 2025-11-09 | Khemlal Mahto | 36.5854 | 4.5732 | TA506 | 76F/0 | Completed
2025-11-09 | 2025-11-09 | 2025-11-13 | Ab Const | 18.1188 | 3.6238 | TA506 | 95/1 | Completed
2025-11-09 | 2025-11-06 | 2025-11-11 | Govind Mahto | 36.5854 | 6.0976 | TA506 | 221/0 | Completed
2025-11-09 | 2025-11-07 | 2025-11-11 | Gulab Mahto | 27.0921 | 5.4184 | TA506 | 2/0 | Completed
2025-11-09 | 2025-11-07 | 2025-11-12 | Horil Mahto | 36.5854 | 6.0976 | TA506 | 95A/0 | Completed
2025-11-09 | 2025-11-04 | 2025-11-09 | Jai Prakash Mahto | 21.0969 | 3.5162 | TA506 | 64A/1 | Completed
2025-11-09 | 2025-11-08 | 2025-11-11 | Karni Const 1 | 17.6337 | 4.4084 | TA506 | 34/2 | Completed
2025-11-09 | 2025-11-03 | 2025-11-10 | Karni Const 2 | 48.342 | 6.0427 | TA506 | 28/0 | Completed
2025-11-09 | 2025-11-05 | 2025-11-12 | Karni Const 4 | 48.342 | 6.0427 | TA506 | 37/0 | Completed
2025-11-09 | 2025-11-07 | 2025-11-13 | Karni Const 5 | 39.6224 | 5.6603 | TA506 | 55/0 | Completed
2025-11-09 | 2025-11-02 | 2025-11-09 | Khemlal Mahto | 36.5854 | 4.5732 | TA506 | 76F/0 | Completed
2025-11-09 | 2025-11-09 | 2025-11-13 | Zainab Fatima | 34.17 | 6.834 | TA506 | 16/0 | Completed
2025-11-10 | 2025-11-09 | 2025-11-13 | Ab Const | 18.1188 | 3.6238 | TA506 | 95/1 | Completed
2025-11-10 | 2025-11-10 | 2025-11-17 | Binod Mahto | 53.1226 | 6.6403 | TA506 | 139/0 | Completed
2025-11-10 | 2025-11-06 | 2025-11-11 | Govind Mahto | 36.5854 | 6.0976 | TA506 | 221/0 | Completed
2025-11-10 | 2025-11-07 | 2025-11-11 | Gulab Mahto | 27.0921 | 5.4184 | TA506 | 2/0 | Completed
2025-11-10 | 2025-11-07 | 2025-11-12 | Horil Mahto | 36.5854 | 6.0976 | TA506 | 95A/0 | Completed
2025-11-10 | 2025-11-08 | 2025-11-11 | Karni Const 1 | 17.6337 | 4.4084 | TA506 | 34/2 | Completed
2025-11-10 | 2025-11-03 | 2025-11-10 | Karni Const 2 | 48.342 | 6.0427 | TA506 | 28/0 | Completed
2025-11-10 | 2025-11-10 | 2025-11-13 | Karni Const 3 | 18.1188 | 4.5297 | TA506 | 13/5 | Completed
2025-11-10 | 2025-11-05 | 2025-11-12 | Karni Const 4 | 48.342 | 6.0427 | TA506 | 37/0 | Completed
2025-11-10 | 2025-11-07 | 2025-11-13 | Karni Const 5 | 39.6224 | 5.6603 | TA506 | 55/0 | Completed
2025-11-10 | 2025-11-10 | 2025-11-15 | Khemlal Mahto | 31.8647 | 5.3108 | TA506 | 76G/0 | Completed
2025-11-10 | 2025-11-10 | 2025-11-16 | Prem Kumar | 53.1226 | 7.5889 | TA506 | 62/0 | Completed
2025-11-10 | 2025-11-09 | 2025-11-13 | Zainab Fatima | 34.17 | 6.834 | TA506 | 16/0 | Completed
2025-11-11 | 2025-11-09 | 2025-11-13 | Ab Const | 18.1188 | 3.6238 | TA506 | 95/1 | Completed
2025-11-11 | 2025-11-10 | 2025-11-17 | Binod Mahto | 53.1226 | 6.6403 | TA506 | 139/0 | Completed
2025-11-11 | 2025-11-06 | 2025-11-11 | Govind Mahto | 36.5854 | 6.0976 | TA506 | 221/0 | Completed
2025-11-11 | 2025-11-07 | 2025-11-11 | Gulab Mahto | 27.0921 | 5.4184 | TA506 | 2/0 | Completed
2025-11-11 | 2025-11-07 | 2025-11-12 | Horil Mahto | 36.5854 | 6.0976 | TA506 | 95A/0 | Completed
2025-11-11 | 2025-11-08 | 2025-11-11 | Karni Const 1 | 17.6337 | 4.4084 | TA506 | 34/2 | Completed
2025-11-11 | 2025-11-10 | 2025-11-13 | Karni Const 3 | 18.1188 | 4.5297 | TA506 | 13/5 | Completed
2025-11-11 | 2025-11-05 | 2025-11-12 | Karni Const 4 | 48.342 | 6.0427 | TA506 | 37/0 | Completed
2025-11-11 | 2025-11-07 | 2025-11-13 | Karni Const 5 | 39.6224 | 5.6603 | TA506 | 55/0 | Completed
2025-11-11 | 2025-11-10 | 2025-11-15 | Khemlal Mahto | 31.8647 | 5.3108 | TA506 | 76G/0 | Completed
2025-11-11 | 2025-11-10 | 2025-11-16 | Prem Kumar | 53.1226 | 7.5889 | TA506 | 62/0 | Completed
2025-11-11 | 2025-11-09 | 2025-11-13 | Zainab Fatima | 34.17 | 6.834 | TA506 | 16/0 | Completed
2025-11-12 | 2025-11-09 | 2025-11-13 | Ab Const | 18.1188 | 3.6238 | TA506 | 95/1 | Completed
2025-11-12 | 2025-11-10 | 2025-11-17 | Binod Mahto | 53.1226 | 6.6403 | TA506 | 139/0 | Completed
2025-11-12 | 2025-11-07 | 2025-11-12 | Horil Mahto | 36.5854 | 6.0976 | TA506 | 95A/0 | Completed
2025-11-12 | 2025-11-12 | 2025-11-15 | Horil Mahto | 22.4884 | 5.6221 | TA506 | 94/2 | Completed
2025-11-12 | 2025-11-10 | 2025-11-13 | Karni Const 3 | 18.1188 | 4.5297 | TA506 | 13/5 | Completed
2025-11-12 | 2025-11-05 | 2025-11-12 | Karni Const 4 | 48.342 | 6.0427 | TA506 | 37/0 | Completed
2025-11-12 | 2025-11-07 | 2025-11-13 | Karni Const 5 | 39.6224 | 5.6603 | TA506 | 55/0 | Completed
2025-11-12 | 2025-11-10 | 2025-11-15 | Khemlal Mahto | 31.8647 | 5.3108 | TA506 | 76G/0 | Completed
2025-11-12 | 2025-11-10 | 2025-11-16 | Prem Kumar | 53.1226 | 7.5889 | TA506 | 62/0 | Completed
2025-11-12 | 2025-11-12 | 2025-11-17 | Tejal Mahto | 29.7779 | 4.963 | TA506 | 111/0 | Completed
2025-11-12 | 2025-11-09 | 2025-11-13 | Zainab Fatima | 34.17 | 6.834 | TA506 | 16/0 | Completed
2025-11-13 | 2025-11-09 | 2025-11-13 | Ab Const | 18.1188 | 3.6238 | TA506 | 95/1 | Completed
2025-11-13 | 2025-11-10 | 2025-11-17 | Binod Mahto | 53.1226 | 6.6403 | TA506 | 139/0 | Completed
2025-11-13 | 2025-11-12 | 2025-11-15 | Horil Mahto | 22.4884 | 5.6221 | TA506 | 94/2 | Completed
2025-11-13 | 2025-11-13 | 2025-11-18 | Jai Prakash Mahto | 39.5967 | 6.5994 | TA506 | 64/0 | Completed
2025-11-13 | 2025-11-10 | 2025-11-13 | Karni Const 3 | 18.1188 | 4.5297 | TA506 | 13/5 | Completed
2025-11-13 | 2025-11-07 | 2025-11-13 | Karni Const 5 | 39.6224 | 5.6603 | TA506 | 55/0 | Completed
2025-11-13 | 2025-11-10 | 2025-11-15 | Khemlal Mahto | 31.8647 | 5.3108 | TA506 | 76G/0 | Completed
2025-11-13 | 2025-11-10 | 2025-11-16 | Prem Kumar | 53.1226 | 7.5889 | TA506 | 62/0 | Completed
2025-11-13 | 2025-11-12 | 2025-11-17 | Tejal Mahto | 29.7779 | 4.963 | TA506 | 111/0 | Completed
2025-11-13 | 2025-11-09 | 2025-11-13 | Zainab Fatima | 34.17 | 6.834 | TA506 | 16/0 | Completed
2025-11-14 | 2025-11-10 | 2025-11-17 | Binod Mahto | 53.1226 | 6.6403 | TA506 | 139/0 | Completed
2025-11-14 | 2025-11-12 | 2025-11-15 | Horil Mahto | 22.4884 | 5.6221 | TA506 | 94/2 | Completed
2025-11-14 | 2025-11-13 | 2025-11-18 | Jai Prakash Mahto | 39.5967 | 6.5994 | TA506 | 64/0 | Completed
2025-11-14 | 2025-11-14 | 2025-11-19 | Karni Const 1 | 39.6224 | 6.6037 | TA506 | 78/0 | Completed
2025-11-14 | 2025-11-10 | 2025-11-15 | Khemlal Mahto | 31.8647 | 5.3108 | TA506 | 76G/0 | Completed
2025-11-14 | 2025-11-10 | 2025-11-16 | Prem Kumar | 53.1226 | 7.5889 | TA506 | 62/0 | Completed
2025-11-14 | 2025-11-12 | 2025-11-17 | Tejal Mahto | 29.7779 | 4.963 | TA506 | 111/0 | Completed
2025-11-15 | 2025-11-10 | 2025-11-17 | Binod Mahto | 53.1226 | 6.6403 | TA506 | 139/0 | Completed
2025-11-15 | 2025-11-12 | 2025-11-15 | Horil Mahto | 22.4884 | 5.6221 | TA506 | 94/2 | Completed
2025-11-15 | 2025-11-15 | 2025-11-19 | Horil Mahto | 22.4884 | 4.4977 | TA506 | 94/3 | Completed
2025-11-15 | 2025-11-13 | 2025-11-18 | Jai Prakash Mahto | 39.5967 | 6.5994 | TA506 | 64/0 | Completed
2025-11-15 | 2025-11-14 | 2025-11-19 | Karni Const 1 | 39.6224 | 6.6037 | TA506 | 78/0 | Completed
2025-11-15 | 2025-11-15 | 2025-11-18 | Karni Const 4 | 16.9667 | 4.2417 | TA506 | 44A/2 | Completed
2025-11-15 | 2025-11-10 | 2025-11-15 | Khemlal Mahto | 31.8647 | 5.3108 | TA506 | 76G/0 | Completed
2025-11-15 | 2025-11-10 | 2025-11-16 | Prem Kumar | 53.1226 | 7.5889 | TA506 | 62/0 | Completed
2025-11-15 | 2025-11-12 | 2025-11-17 | Tejal Mahto | 29.7779 | 4.963 | TA506 | 111/0 | Completed
2025-11-16 | 2025-11-16 | 2025-11-19 | Ab Const | 18.1188 | 4.5297 | TA506 | 107/1 | Completed
2025-11-16 | 2025-11-10 | 2025-11-17 | Binod Mahto | 53.1226 | 6.6403 | TA506 | 139/0 | Completed
2025-11-16 | 2025-11-15 | 2025-11-19 | Horil Mahto | 22.4884 | 4.4977 | TA506 | 94/3 | Completed
2025-11-16 | 2025-11-13 | 2025-11-18 | Jai Prakash Mahto | 39.5967 | 6.5994 | TA506 | 64/0 | Completed
2025-11-16 | 2025-11-14 | 2025-11-19 | Karni Const 1 | 39.6224 | 6.6037 | TA506 | 78/0 | Completed
2025-11-16 | 2025-11-16 | 2025-11-19 | Karni Const 2 | 21.0969 | 5.2742 | TA506 | 36/2 | Completed
2025-11-16 | 2025-11-15 | 2025-11-18 | Karni Const 4 | 16.9667 | 4.2417 | TA506 | 44A/2 | Completed
2025-11-16 | 2025-11-10 | 2025-11-16 | Prem Kumar | 53.1226 | 7.5889 | TA506 | 62/0 | Completed
2025-11-16 | 2025-11-12 | 2025-11-17 | Tejal Mahto | 29.7779 | 4.963 | TA506 | 111/0 | Completed
2025-11-17 | 2025-11-16 | 2025-11-19 | Ab Const | 18.1188 | 4.5297 | TA506 | 107/1 | Completed
2025-11-17 | 2025-11-10 | 2025-11-17 | Binod Mahto | 53.1226 | 6.6403 | TA506 | 139/0 | Completed
2025-11-17 | 2025-11-15 | 2025-11-19 | Horil Mahto | 22.4884 | 4.4977 | TA506 | 94/3 | Completed
2025-11-17 | 2025-11-13 | 2025-11-18 | Jai Prakash Mahto | 39.5967 | 6.5994 | TA506 | 64/0 | Completed
2025-11-17 | 2025-11-14 | 2025-11-19 | Karni Const 1 | 39.6224 | 6.6037 | TA506 | 78/0 | Completed
2025-11-17 | 2025-11-16 | 2025-11-19 | Karni Const 2 | 21.0969 | 5.2742 | TA506 | 36/2 | Completed
2025-11-17 | 2025-11-15 | 2025-11-18 | Karni Const 4 | 16.9667 | 4.2417 | TA506 | 44A/2 | Completed
2025-11-17 | 2025-11-17 | 2025-11-22 | Karni Const 6 | 36.5854 | 6.0976 | TA506 | 56/0 | Completed
2025-11-17 | 2025-11-12 | 2025-11-17 | Tejal Mahto | 29.7779 | 4.963 | TA506 | 111/0 | Completed
2025-11-18 | 2025-11-16 | 2025-11-19 | Ab Const | 18.1188 | 4.5297 | TA506 | 107/1 | Completed
2025-11-18 | 2025-11-15 | 2025-11-19 | Horil Mahto | 22.4884 | 4.4977 | TA506 | 94/3 | Completed
2025-11-18 | 2025-11-13 | 2025-11-18 | Jai Prakash Mahto | 39.5967 | 6.5994 | TA506 | 64/0 | Completed
2025-11-18 | 2025-11-14 | 2025-11-19 | Karni Const 1 | 39.6224 | 6.6037 | TA506 | 78/0 | Completed
2025-11-18 | 2025-11-16 | 2025-11-19 | Karni Const 2 | 21.0969 | 5.2742 | TA506 | 36/2 | Completed
2025-11-18 | 2025-11-18 | 2025-11-23 | Karni Const 3 | 35.8452 | 5.9742 | TA506 | 26/0 | Completed
2025-11-18 | 2025-11-15 | 2025-11-18 | Karni Const 4 | 16.9667 | 4.2417 | TA506 | 44A/2 | Completed
2025-11-18 | 2025-11-17 | 2025-11-22 | Karni Const 6 | 36.5854 | 6.0976 | TA506 | 56/0 | Completed
2025-11-18 | 2025-11-18 | 2025-11-20 | Khemlal Mahto | 18.1188 | 6.0396 | TA506 | 76G/1 | Completed
2025-11-19 | 2025-11-16 | 2025-11-19 | Ab Const | 18.1188 | 4.5297 | TA506 | 107/1 | Completed
2025-11-19 | 2025-11-19 | 2025-11-23 | Govind Mahto | 21.0969 | 4.2194 | TA506 | 210/9 | Completed
2025-11-19 | 2025-11-15 | 2025-11-19 | Horil Mahto | 22.4884 | 4.4977 | TA506 | 94/3 | Completed
2025-11-19 | 2025-11-19 | 2025-11-22 | Jai Prakash Mahto | 15.8578 | 3.9644 | TA506 | 64/1 | Completed
2025-11-19 | 2025-11-14 | 2025-11-19 | Karni Const 1 | 39.6224 | 6.6037 | TA506 | 78/0 | Completed
2025-11-19 | 2025-11-16 | 2025-11-19 | Karni Const 2 | 21.0969 | 5.2742 | TA506 | 36/2 | Completed
2025-11-19 | 2025-11-18 | 2025-11-23 | Karni Const 3 | 35.8452 | 5.9742 | TA506 | 26/0 | Completed
2025-11-19 | 2025-11-17 | 2025-11-22 | Karni Const 6 | 36.5854 | 6.0976 | TA506 | 56/0 | Completed
2025-11-19 | 2025-11-18 | 2025-11-20 | Khemlal Mahto | 18.1188 | 6.0396 | TA506 | 76G/1 | Completed
2025-11-19 | 2025-11-19 | 2025-11-22 | Pankaj | 21.0969 | 5.2742 | TA506 | 211/4 | Completed
2025-11-20 | 2025-11-19 | 2025-11-23 | Govind Mahto | 21.0969 | 4.2194 | TA506 | 210/9 | Completed
2025-11-20 | 2025-11-19 | 2025-11-22 | Jai Prakash Mahto | 15.8578 | 3.9644 | TA506 | 64/1 | Completed
2025-11-20 | 2025-11-20 | 2025-11-23 | Karni Const 1 | 16.9667 | 4.2417 | TA506 | 17/1 | Completed
2025-11-20 | 2025-11-18 | 2025-11-23 | Karni Const 3 | 35.8452 | 5.9742 | TA506 | 26/0 | Completed
2025-11-20 | 2025-11-17 | 2025-11-22 | Karni Const 6 | 36.5854 | 6.0976 | TA506 | 56/0 | Completed
2025-11-20 | 2025-11-18 | 2025-11-20 | Khemlal Mahto | 18.1188 | 6.0396 | TA506 | 76G/1 | Completed
2025-11-20 | 2025-11-19 | 2025-11-22 | Pankaj | 21.0969 | 5.2742 | TA506 | 211/4 | Completed
2025-11-21 | 2025-11-19 | 2025-11-23 | Govind Mahto | 21.0969 | 4.2194 | TA506 | 210/9 | Completed
2025-11-21 | 2025-11-19 | 2025-11-22 | Jai Prakash Mahto | 15.8578 | 3.9644 | TA506 | 64/1 | Completed
2025-11-21 | 2025-11-20 | 2025-11-23 | Karni Const 1 | 16.9667 | 4.2417 | TA506 | 17/1 | Completed
2025-11-21 | 2025-11-18 | 2025-11-23 | Karni Const 3 | 35.8452 | 5.9742 | TA506 | 26/0 | Completed
2025-11-21 | 2025-11-17 | 2025-11-22 | Karni Const 6 | 36.5854 | 6.0976 | TA506 | 56/0 | Completed
2025-11-21 | 2025-11-19 | 2025-11-22 | Pankaj | 21.0969 | 5.2742 | TA506 | 211/4 | Completed
2025-11-22 | 2025-11-19 | 2025-11-23 | Govind Mahto | 21.0969 | 4.2194 | TA506 | 210/9 | Completed
2025-11-22 | 2025-11-19 | 2025-11-22 | Jai Prakash Mahto | 15.8578 | 3.9644 | TA506 | 64/1 | Completed
2025-11-22 | 2025-11-20 | 2025-11-23 | Karni Const 1 | 16.9667 | 4.2417 | TA506 | 17/1 | Completed
2025-11-22 | 2025-11-18 | 2025-11-23 | Karni Const 3 | 35.8452 | 5.9742 | TA506 | 26/0 | Completed
2025-11-22 | 2025-11-17 | 2025-11-22 | Karni Const 6 | 36.5854 | 6.0976 | TA506 | 56/0 | Completed
2025-11-22 | 2025-11-19 | 2025-11-22 | Pankaj | 21.0969 | 5.2742 | TA506 | 211/4 | Completed
2025-11-23 | 2025-11-19 | 2025-11-23 | Govind Mahto | 21.0969 | 4.2194 | TA506 | 210/9 | Completed
2025-11-23 | 2025-11-20 | 2025-11-23 | Karni Const 1 | 16.9667 | 4.2417 | TA506 | 17/1 | Completed
2025-11-23 | 2025-11-18 | 2025-11-23 | Karni Const 3 | 35.8452 | 5.9742 | TA506 | 26/0 | Completed
2025-08-22 | 2025-08-22 | 2025-09-15 | Deonath Mahato | 36.15 | 1.446 | TA509 | 13/2 | COMPLETED
2025-08-22 | 2025-08-22 | 2025-09-03 | Devi Const I | 36.15 | 2.7808 | TA509 | 16/4 | COMPLETED
2025-08-23 | 2025-08-22 | 2025-09-15 | Deonath Mahato | 36.15 | 1.446 | TA509 | 13/2 | COMPLETED
2025-08-23 | 2025-08-22 | 2025-09-03 | Devi Const I | 36.15 | 2.7808 | TA509 | 16/4 | COMPLETED
2025-08-24 | 2025-08-22 | 2025-09-15 | Deonath Mahato | 36.15 | 1.446 | TA509 | 13/2 | COMPLETED
2025-08-24 | 2025-08-22 | 2025-09-03 | Devi Const I | 36.15 | 2.7808 | TA509 | 16/4 | COMPLETED
2025-08-25 | 2025-08-22 | 2025-09-15 | Deonath Mahato | 36.15 | 1.446 | TA509 | 13/2 | COMPLETED
2025-08-25 | 2025-08-22 | 2025-09-03 | Devi Const I | 36.15 | 2.7808 | TA509 | 16/4 | COMPLETED
2025-08-25 | 2025-08-25 | 2025-09-08 | Jawala Singh | 36.15 | 2.41 | TA509 | 8/5 | COMPLETED
2025-08-25 | 2025-08-25 | 2025-09-18 | Modina India | 36.15 | 1.446 | TA509 | 12/6 | COMPLETED
2025-08-26 | 2025-08-22 | 2025-09-15 | Deonath Mahato | 36.15 | 1.446 | TA509 | 13/2 | COMPLETED
2025-08-26 | 2025-08-22 | 2025-09-03 | Devi Const I | 36.15 | 2.7808 | TA509 | 16/4 | COMPLETED
2025-08-26 | 2025-08-25 | 2025-09-08 | Jawala Singh | 36.15 | 2.41 | TA509 | 8/5 | COMPLETED
2025-08-26 | 2025-08-25 | 2025-09-18 | Modina India | 36.15 | 1.446 | TA509 | 12/6 | COMPLETED
2025-08-27 | 2025-08-22 | 2025-09-15 | Deonath Mahato | 36.15 | 1.446 | TA509 | 13/2 | COMPLETED
2025-08-27 | 2025-08-22 | 2025-09-03 | Devi Const I | 36.15 | 2.7808 | TA509 | 16/4 | COMPLETED
2025-08-27 | 2025-08-25 | 2025-09-08 | Jawala Singh | 36.15 | 2.41 | TA509 | 8/5 | COMPLETED
2025-08-27 | 2025-08-25 | 2025-09-18 | Modina India | 36.15 | 1.446 | TA509 | 12/6 | COMPLETED
2025-08-28 | 2025-08-22 | 2025-09-15 | Deonath Mahato | 36.15 | 1.446 | TA509 | 13/2 | COMPLETED
2025-08-28 | 2025-08-22 | 2025-09-03 | Devi Const I | 36.15 | 2.7808 | TA509 | 16/4 | COMPLETED
2025-08-28 | 2025-08-25 | 2025-09-08 | Jawala Singh | 36.15 | 2.41 | TA509 | 8/5 | COMPLETED
2025-08-28 | 2025-08-25 | 2025-09-18 | Modina India | 36.15 | 1.446 | TA509 | 12/6 | COMPLETED
2025-08-29 | 2025-08-22 | 2025-09-15 | Deonath Mahato | 36.15 | 1.446 | TA509 | 13/2 | COMPLETED
2025-08-29 | 2025-08-22 | 2025-09-03 | Devi Const I | 36.15 | 2.7808 | TA509 | 16/4 | COMPLETED
2025-08-29 | 2025-08-25 | 2025-09-08 | Jawala Singh | 36.15 | 2.41 | TA509 | 8/5 | COMPLETED
2025-08-29 | 2025-08-25 | 2025-09-18 | Modina India | 36.15 | 1.446 | TA509 | 12/6 | COMPLETED
2025-08-30 | 2025-08-22 | 2025-09-15 | Deonath Mahato | 36.15 | 1.446 | TA509 | 13/2 | COMPLETED
2025-08-30 | 2025-08-22 | 2025-09-03 | Devi Const I | 36.15 | 2.7808 | TA509 | 16/4 | COMPLETED
2025-08-30 | 2025-08-25 | 2025-09-08 | Jawala Singh | 36.15 | 2.41 | TA509 | 8/5 | COMPLETED
2025-08-30 | 2025-08-25 | 2025-09-18 | Modina India | 36.15 | 1.446 | TA509 | 12/6 | COMPLETED
2025-08-31 | 2025-08-22 | 2025-09-15 | Deonath Mahato | 36.15 | 1.446 | TA509 | 13/2 | COMPLETED
2025-08-31 | 2025-08-22 | 2025-09-03 | Devi Const I | 36.15 | 2.7808 | TA509 | 16/4 | COMPLETED
2025-08-31 | 2025-08-25 | 2025-09-08 | Jawala Singh | 36.15 | 2.41 | TA509 | 8/5 | COMPLETED
2025-08-31 | 2025-08-25 | 2025-09-18 | Modina India | 36.15 | 1.446 | TA509 | 12/6 | COMPLETED
2025-09-01 | 2025-08-22 | 2025-09-15 | Deonath Mahato | 36.15 | 1.446 | TA509 | 13/2 | COMPLETED
2025-09-01 | 2025-08-22 | 2025-09-03 | Devi Const I | 36.15 | 2.7808 | TA509 | 16/4 | COMPLETED
2025-09-01 | 2025-09-01 | 2025-09-19 | Hemlal Mahato I Anita Devi | 34.79 | 1.8311 | TA509 | 15/5 | COMPLETED
2025-09-01 | 2025-08-25 | 2025-09-08 | Jawala Singh | 36.15 | 2.41 | TA509 | 8/5 | COMPLETED
2025-09-01 | 2025-08-25 | 2025-09-18 | Modina India | 36.15 | 1.446 | TA509 | 12/6 | COMPLETED
2025-09-02 | 2025-08-22 | 2025-09-15 | Deonath Mahato | 36.15 | 1.446 | TA509 | 13/2 | COMPLETED
2025-09-02 | 2025-08-22 | 2025-09-03 | Devi Const I | 36.15 | 2.7808 | TA509 | 16/4 | COMPLETED
2025-09-02 | 2025-09-01 | 2025-09-19 | Hemlal Mahato I Anita Devi | 34.79 | 1.8311 | TA509 | 15/5 | COMPLETED
2025-09-02 | 2025-09-02 | 2025-09-12 | Hemlal Mahato I Anita Devi | 37.93 | 3.4482 | TA509 | 15/2 | COMPLETED
2025-09-02 | 2025-08-25 | 2025-09-08 | Jawala Singh | 36.15 | 2.41 | TA509 | 8/5 | COMPLETED
2025-09-02 | 2025-08-25 | 2025-09-18 | Modina India | 36.15 | 1.446 | TA509 | 12/6 | COMPLETED
2025-09-02 | 2025-09-02 | 2025-09-23 | Om Construction | 37.93 | 1.7241 | TA509 | 12/1 | COMPLETED
2025-09-03 | 2025-08-22 | 2025-09-15 | Deonath Mahato | 36.15 | 1.446 | TA509 | 13/2 | COMPLETED
2025-09-03 | 2025-08-22 | 2025-09-03 | Devi Const I | 36.15 | 2.7808 | TA509 | 16/4 | COMPLETED
2025-09-03 | 2025-09-01 | 2025-09-19 | Hemlal Mahato I Anita Devi | 34.79 | 1.8311 | TA509 | 15/5 | COMPLETED
2025-09-03 | 2025-09-02 | 2025-09-12 | Hemlal Mahato I Anita Devi | 37.93 | 3.4482 | TA509 | 15/2 | COMPLETED
2025-09-03 | 2025-08-25 | 2025-09-08 | Jawala Singh | 36.15 | 2.41 | TA509 | 8/5 | COMPLETED
2025-09-03 | 2025-08-25 | 2025-09-18 | Modina India | 36.15 | 1.446 | TA509 | 12/6 | COMPLETED
2025-09-03 | 2025-09-02 | 2025-09-23 | Om Construction | 37.93 | 1.7241 | TA509 | 12/1 | COMPLETED
2025-09-04 | 2025-08-22 | 2025-09-15 | Deonath Mahato | 36.15 | 1.446 | TA509 | 13/2 | COMPLETED
2025-09-04 | 2025-09-01 | 2025-09-19 | Hemlal Mahato I Anita Devi | 34.79 | 1.8311 | TA509 | 15/5 | COMPLETED
2025-09-04 | 2025-09-02 | 2025-09-12 | Hemlal Mahato I Anita Devi | 37.93 | 3.4482 | TA509 | 15/2 | COMPLETED
2025-09-04 | 2025-08-25 | 2025-09-08 | Jawala Singh | 36.15 | 2.41 | TA509 | 8/5 | COMPLETED
2025-09-04 | 2025-08-25 | 2025-09-18 | Modina India | 36.15 | 1.446 | TA509 | 12/6 | COMPLETED
2025-09-04 | 2025-09-02 | 2025-09-23 | Om Construction | 37.93 | 1.7241 | TA509 | 12/1 | COMPLETED
2025-09-05 | 2025-08-22 | 2025-09-15 | Deonath Mahato | 36.15 | 1.446 | TA509 | 13/2 | COMPLETED
2025-09-05 | 2025-09-01 | 2025-09-19 | Hemlal Mahato I Anita Devi | 34.79 | 1.8311 | TA509 | 15/5 | COMPLETED
2025-09-05 | 2025-09-02 | 2025-09-12 | Hemlal Mahato I Anita Devi | 37.93 | 3.4482 | TA509 | 15/2 | COMPLETED
2025-09-05 | 2025-08-25 | 2025-09-08 | Jawala Singh | 36.15 | 2.41 | TA509 | 8/5 | COMPLETED
2025-09-05 | 2025-08-25 | 2025-09-18 | Modina India | 36.15 | 1.446 | TA509 | 12/6 | COMPLETED
2025-09-05 | 2025-09-02 | 2025-09-23 | Om Construction | 37.93 | 1.7241 | TA509 | 12/1 | COMPLETED
2025-09-06 | 2025-08-22 | 2025-09-15 | Deonath Mahato | 36.15 | 1.446 | TA509 | 13/2 | COMPLETED
2025-09-06 | 2025-09-01 | 2025-09-19 | Hemlal Mahato I Anita Devi | 34.79 | 1.8311 | TA509 | 15/5 | COMPLETED
2025-09-06 | 2025-09-02 | 2025-09-12 | Hemlal Mahato I Anita Devi | 37.93 | 3.4482 | TA509 | 15/2 | COMPLETED
2025-09-06 | 2025-08-25 | 2025-09-08 | Jawala Singh | 36.15 | 2.41 | TA509 | 8/5 | COMPLETED
2025-09-06 | 2025-08-25 | 2025-09-18 | Modina India | 36.15 | 1.446 | TA509 | 12/6 | COMPLETED
2025-09-06 | 2025-09-02 | 2025-09-23 | Om Construction | 37.93 | 1.7241 | TA509 | 12/1 | COMPLETED
2025-09-07 | 2025-08-22 | 2025-09-15 | Deonath Mahato | 36.15 | 1.446 | TA509 | 13/2 | COMPLETED
2025-09-07 | 2025-09-07 | 2025-09-14 | Devi Const I | 34.79 | 4.3487 | TA509 | 20/1 | COMPLETED
2025-09-07 | 2025-09-07 | 2025-09-12 | Devi Const Ii | 36.15 | 6.025 | TA509 | 16/1 | COMPLETED
2025-09-07 | 2025-09-01 | 2025-09-19 | Hemlal Mahato I Anita Devi | 34.79 | 1.8311 | TA509 | 15/5 | COMPLETED
2025-09-07 | 2025-09-02 | 2025-09-12 | Hemlal Mahato I Anita Devi | 37.93 | 3.4482 | TA509 | 15/2 | COMPLETED
2025-09-07 | 2025-08-25 | 2025-09-08 | Jawala Singh | 36.15 | 2.41 | TA509 | 8/5 | COMPLETED
2025-09-07 | 2025-08-25 | 2025-09-18 | Modina India | 36.15 | 1.446 | TA509 | 12/6 | COMPLETED
2025-09-07 | 2025-09-02 | 2025-09-23 | Om Construction | 37.93 | 1.7241 | TA509 | 12/1 | COMPLETED
2025-09-08 | 2025-08-22 | 2025-09-15 | Deonath Mahato | 36.15 | 1.446 | TA509 | 13/2 | COMPLETED
2025-09-08 | 2025-09-07 | 2025-09-14 | Devi Const I | 34.79 | 4.3487 | TA509 | 20/1 | COMPLETED
2025-09-08 | 2025-09-07 | 2025-09-12 | Devi Const Ii | 36.15 | 6.025 | TA509 | 16/1 | COMPLETED
2025-09-08 | 2025-09-01 | 2025-09-19 | Hemlal Mahato I Anita Devi | 34.79 | 1.8311 | TA509 | 15/5 | COMPLETED
2025-09-08 | 2025-09-02 | 2025-09-12 | Hemlal Mahato I Anita Devi | 37.93 | 3.4482 | TA509 | 15/2 | COMPLETED
2025-09-08 | 2025-08-25 | 2025-09-08 | Jawala Singh | 36.15 | 2.41 | TA509 | 8/5 | COMPLETED
2025-09-08 | 2025-08-25 | 2025-09-18 | Modina India | 36.15 | 1.446 | TA509 | 12/6 | COMPLETED
2025-09-08 | 2025-09-02 | 2025-09-23 | Om Construction | 37.93 | 1.7241 | TA509 | 12/1 | COMPLETED
2025-09-09 | 2025-08-22 | 2025-09-15 | Deonath Mahato | 36.15 | 1.446 | TA509 | 13/2 | COMPLETED
2025-09-09 | 2025-09-07 | 2025-09-14 | Devi Const I | 34.79 | 4.3487 | TA509 | 20/1 | COMPLETED
2025-09-09 | 2025-09-07 | 2025-09-12 | Devi Const Ii | 36.15 | 6.025 | TA509 | 16/1 | COMPLETED
2025-09-09 | 2025-09-01 | 2025-09-19 | Hemlal Mahato I Anita Devi | 34.79 | 1.8311 | TA509 | 15/5 | COMPLETED
2025-09-09 | 2025-09-02 | 2025-09-12 | Hemlal Mahato I Anita Devi | 37.93 | 3.4482 | TA509 | 15/2 | COMPLETED
2025-09-09 | 2025-08-25 | 2025-09-18 | Modina India | 36.15 | 1.446 | TA509 | 12/6 | COMPLETED
2025-09-09 | 2025-09-02 | 2025-09-23 | Om Construction | 37.93 | 1.7241 | TA509 | 12/1 | COMPLETED
2025-09-10 | 2025-08-22 | 2025-09-15 | Deonath Mahato | 36.15 | 1.446 | TA509 | 13/2 | COMPLETED
2025-09-10 | 2025-09-07 | 2025-09-14 | Devi Const I | 34.79 | 4.3487 | TA509 | 20/1 | COMPLETED
2025-09-10 | 2025-09-07 | 2025-09-12 | Devi Const Ii | 36.15 | 6.025 | TA509 | 16/1 | COMPLETED
2025-09-10 | 2025-09-01 | 2025-09-19 | Hemlal Mahato I Anita Devi | 34.79 | 1.8311 | TA509 | 15/5 | COMPLETED
2025-09-10 | 2025-09-02 | 2025-09-12 | Hemlal Mahato I Anita Devi | 37.93 | 3.4482 | TA509 | 15/2 | COMPLETED
2025-09-10 | 2025-08-25 | 2025-09-18 | Modina India | 36.15 | 1.446 | TA509 | 12/6 | COMPLETED
2025-09-10 | 2025-09-02 | 2025-09-23 | Om Construction | 37.93 | 1.7241 | TA509 | 12/1 | COMPLETED
2025-09-11 | 2025-08-22 | 2025-09-15 | Deonath Mahato | 36.15 | 1.446 | TA509 | 13/2 | COMPLETED
2025-09-11 | 2025-09-07 | 2025-09-14 | Devi Const I | 34.79 | 4.3487 | TA509 | 20/1 | COMPLETED
2025-09-11 | 2025-09-07 | 2025-09-12 | Devi Const Ii | 36.15 | 6.025 | TA509 | 16/1 | COMPLETED
2025-09-11 | 2025-09-01 | 2025-09-19 | Hemlal Mahato I Anita Devi | 34.79 | 1.8311 | TA509 | 15/5 | COMPLETED
2025-09-11 | 2025-09-02 | 2025-09-12 | Hemlal Mahato I Anita Devi | 37.93 | 3.4482 | TA509 | 15/2 | COMPLETED
2025-09-11 | 2025-08-25 | 2025-09-18 | Modina India | 36.15 | 1.446 | TA509 | 12/6 | COMPLETED
2025-09-11 | 2025-09-02 | 2025-09-23 | Om Construction | 37.93 | 1.7241 | TA509 | 12/1 | COMPLETED
2025-09-12 | 2025-08-22 | 2025-09-15 | Deonath Mahato | 36.15 | 1.446 | TA509 | 13/2 | COMPLETED
2025-09-12 | 2025-09-07 | 2025-09-14 | Devi Const I | 34.79 | 4.3487 | TA509 | 20/1 | COMPLETED
2025-09-12 | 2025-09-07 | 2025-09-12 | Devi Const Ii | 36.15 | 6.025 | TA509 | 16/1 | COMPLETED
2025-09-12 | 2025-09-01 | 2025-09-19 | Hemlal Mahato I Anita Devi | 34.79 | 1.8311 | TA509 | 15/5 | COMPLETED
2025-09-12 | 2025-09-02 | 2025-09-12 | Hemlal Mahato I Anita Devi | 37.93 | 3.4482 | TA509 | 15/2 | COMPLETED
2025-09-12 | 2025-08-25 | 2025-09-18 | Modina India | 36.15 | 1.446 | TA509 | 12/6 | COMPLETED
2025-09-12 | 2025-09-02 | 2025-09-23 | Om Construction | 37.93 | 1.7241 | TA509 | 12/1 | COMPLETED
2025-09-13 | 2025-08-22 | 2025-09-15 | Deonath Mahato | 36.15 | 1.446 | TA509 | 13/2 | COMPLETED
2025-09-13 | 2025-09-13 | 2025-09-27 | Deonath Mahato | 34.79 | 2.3193 | TA509 | 13/4 | COMPLETED
2025-09-13 | 2025-09-07 | 2025-09-14 | Devi Const I | 34.79 | 4.3487 | TA509 | 20/1 | COMPLETED
2025-09-13 | 2025-09-13 | 2025-09-19 | Devi Const I | 34.79 | 4.97 | TA509 | 16/8 | COMPLETED
2025-09-13 | 2025-09-01 | 2025-09-19 | Hemlal Mahato I Anita Devi | 34.79 | 1.8311 | TA509 | 15/5 | COMPLETED
2025-09-13 | 2025-08-25 | 2025-09-18 | Modina India | 36.15 | 1.446 | TA509 | 12/6 | COMPLETED
2025-09-13 | 2025-09-02 | 2025-09-23 | Om Construction | 37.93 | 1.7241 | TA509 | 12/1 | COMPLETED
2025-09-14 | 2025-08-22 | 2025-09-15 | Deonath Mahato | 36.15 | 1.446 | TA509 | 13/2 | COMPLETED
2025-09-14 | 2025-09-13 | 2025-09-27 | Deonath Mahato | 34.79 | 2.3193 | TA509 | 13/4 | COMPLETED
2025-09-14 | 2025-09-07 | 2025-09-14 | Devi Const I | 34.79 | 4.3487 | TA509 | 20/1 | COMPLETED
2025-09-14 | 2025-09-13 | 2025-09-19 | Devi Const I | 34.79 | 4.97 | TA509 | 16/8 | COMPLETED
2025-09-14 | 2025-09-01 | 2025-09-19 | Hemlal Mahato I Anita Devi | 34.79 | 1.8311 | TA509 | 15/5 | COMPLETED
2025-09-14 | 2025-09-14 | 2025-09-20 | Jawala Singh | 36.15 | 5.1643 | TA509 | 8/7 | COMPLETED
2025-09-14 | 2025-08-25 | 2025-09-18 | Modina India | 36.15 | 1.446 | TA509 | 12/6 | COMPLETED
2025-09-14 | 2025-09-02 | 2025-09-23 | Om Construction | 37.93 | 1.7241 | TA509 | 12/1 | COMPLETED
2025-09-15 | 2025-08-22 | 2025-09-15 | Deonath Mahato | 36.15 | 1.446 | TA509 | 13/2 | COMPLETED
2025-09-15 | 2025-09-13 | 2025-09-27 | Deonath Mahato | 34.79 | 2.3193 | TA509 | 13/4 | COMPLETED
2025-09-15 | 2025-09-13 | 2025-09-19 | Devi Const I | 34.79 | 4.97 | TA509 | 16/8 | COMPLETED
2025-09-15 | 2025-09-15 | 2025-09-23 | Devi Const Ii | 43.8 | 4.8667 | TA509 | 22/1 | COMPLETED
2025-09-15 | 2025-09-01 | 2025-09-19 | Hemlal Mahato I Anita Devi | 34.79 | 1.8311 | TA509 | 15/5 | COMPLETED
2025-09-15 | 2025-09-14 | 2025-09-20 | Jawala Singh | 36.15 | 5.1643 | TA509 | 8/7 | COMPLETED
2025-09-15 | 2025-08-25 | 2025-09-18 | Modina India | 36.15 | 1.446 | TA509 | 12/6 | COMPLETED
2025-09-15 | 2025-09-02 | 2025-09-23 | Om Construction | 37.93 | 1.7241 | TA509 | 12/1 | COMPLETED
2025-09-16 | 2025-09-13 | 2025-09-27 | Deonath Mahato | 34.79 | 2.3193 | TA509 | 13/4 | COMPLETED
2025-09-16 | 2025-09-13 | 2025-09-19 | Devi Const I | 34.79 | 4.97 | TA509 | 16/8 | COMPLETED
2025-09-16 | 2025-09-16 | 2025-10-04 | Devi Const I | 34.79 | 1.8311 | TA509 | 12/2 | COMPLETED
2025-09-16 | 2025-09-15 | 2025-09-23 | Devi Const Ii | 43.8 | 4.8667 | TA509 | 22/1 | COMPLETED
2025-09-16 | 2025-09-01 | 2025-09-19 | Hemlal Mahato I Anita Devi | 34.79 | 1.8311 | TA509 | 15/5 | COMPLETED
2025-09-16 | 2025-09-14 | 2025-09-20 | Jawala Singh | 36.15 | 5.1643 | TA509 | 8/7 | COMPLETED
2025-09-16 | 2025-08-25 | 2025-09-18 | Modina India | 36.15 | 1.446 | TA509 | 12/6 | COMPLETED
2025-09-16 | 2025-09-02 | 2025-09-23 | Om Construction | 37.93 | 1.7241 | TA509 | 12/1 | COMPLETED
2025-09-16 | 2025-09-16 | 2025-09-24 | Om Construction | 36.15 | 4.0167 | TA509 | 14/1 | COMPLETED
2025-09-17 | 2025-09-13 | 2025-09-27 | Deonath Mahato | 34.79 | 2.3193 | TA509 | 13/4 | COMPLETED
2025-09-17 | 2025-09-13 | 2025-09-19 | Devi Const I | 34.79 | 4.97 | TA509 | 16/8 | COMPLETED
2025-09-17 | 2025-09-16 | 2025-10-04 | Devi Const I | 34.79 | 1.8311 | TA509 | 12/2 | COMPLETED
2025-09-17 | 2025-09-15 | 2025-09-23 | Devi Const Ii | 43.8 | 4.8667 | TA509 | 22/1 | COMPLETED
2025-09-17 | 2025-09-01 | 2025-09-19 | Hemlal Mahato I Anita Devi | 34.79 | 1.8311 | TA509 | 15/5 | COMPLETED
2025-09-17 | 2025-09-14 | 2025-09-20 | Jawala Singh | 36.15 | 5.1643 | TA509 | 8/7 | COMPLETED
2025-09-17 | 2025-08-25 | 2025-09-18 | Modina India | 36.15 | 1.446 | TA509 | 12/6 | COMPLETED
2025-09-17 | 2025-09-02 | 2025-09-23 | Om Construction | 37.93 | 1.7241 | TA509 | 12/1 | COMPLETED
2025-09-17 | 2025-09-16 | 2025-09-24 | Om Construction | 36.15 | 4.0167 | TA509 | 14/1 | COMPLETED
2025-09-18 | 2025-09-13 | 2025-09-27 | Deonath Mahato | 34.79 | 2.3193 | TA509 | 13/4 | COMPLETED
2025-09-18 | 2025-09-13 | 2025-09-19 | Devi Const I | 34.79 | 4.97 | TA509 | 16/8 | COMPLETED
2025-09-18 | 2025-09-16 | 2025-10-04 | Devi Const I | 34.79 | 1.8311 | TA509 | 12/2 | COMPLETED
2025-09-18 | 2025-09-15 | 2025-09-23 | Devi Const Ii | 43.8 | 4.8667 | TA509 | 22/1 | COMPLETED
2025-09-18 | 2025-09-01 | 2025-09-19 | Hemlal Mahato I Anita Devi | 34.79 | 1.8311 | TA509 | 15/5 | COMPLETED
2025-09-18 | 2025-09-14 | 2025-09-20 | Jawala Singh | 36.15 | 5.1643 | TA509 | 8/7 | COMPLETED
2025-09-18 | 2025-08-25 | 2025-09-18 | Modina India | 36.15 | 1.446 | TA509 | 12/6 | COMPLETED
2025-09-18 | 2025-09-02 | 2025-09-23 | Om Construction | 37.93 | 1.7241 | TA509 | 12/1 | COMPLETED
2025-09-18 | 2025-09-16 | 2025-09-24 | Om Construction | 36.15 | 4.0167 | TA509 | 14/1 | COMPLETED
2025-09-19 | 2025-09-13 | 2025-09-27 | Deonath Mahato | 34.79 | 2.3193 | TA509 | 13/4 | COMPLETED
2025-09-19 | 2025-09-13 | 2025-09-19 | Devi Const I | 34.79 | 4.97 | TA509 | 16/8 | COMPLETED
2025-09-19 | 2025-09-16 | 2025-10-04 | Devi Const I | 34.79 | 1.8311 | TA509 | 12/2 | COMPLETED
2025-09-19 | 2025-09-15 | 2025-09-23 | Devi Const Ii | 43.8 | 4.8667 | TA509 | 22/1 | COMPLETED
2025-09-19 | 2025-09-01 | 2025-09-19 | Hemlal Mahato I Anita Devi | 34.79 | 1.8311 | TA509 | 15/5 | COMPLETED
2025-09-19 | 2025-09-19 | 2025-09-25 | Hemlal Mahato Ii Anita Devi | 36.15 | 5.1643 | TA509 | 16/9 | COMPLETED
2025-09-19 | 2025-09-14 | 2025-09-20 | Jawala Singh | 36.15 | 5.1643 | TA509 | 8/7 | COMPLETED
2025-09-19 | 2025-09-02 | 2025-09-23 | Om Construction | 37.93 | 1.7241 | TA509 | 12/1 | COMPLETED
2025-09-19 | 2025-09-16 | 2025-09-24 | Om Construction | 36.15 | 4.0167 | TA509 | 14/1 | COMPLETED
2025-09-20 | 2025-09-13 | 2025-09-27 | Deonath Mahato | 34.79 | 2.3193 | TA509 | 13/4 | COMPLETED
2025-09-20 | 2025-09-16 | 2025-10-04 | Devi Const I | 34.79 | 1.8311 | TA509 | 12/2 | COMPLETED
2025-09-20 | 2025-09-20 | 2025-09-26 | Devi Const I | 37.93 | 5.4186 | TA509 | 9/1 | COMPLETED
2025-09-20 | 2025-09-15 | 2025-09-23 | Devi Const Ii | 43.8 | 4.8667 | TA509 | 22/1 | COMPLETED
2025-09-20 | 2025-09-19 | 2025-09-25 | Hemlal Mahato Ii Anita Devi | 36.15 | 5.1643 | TA509 | 16/9 | COMPLETED
2025-09-20 | 2025-09-14 | 2025-09-20 | Jawala Singh | 36.15 | 5.1643 | TA509 | 8/7 | COMPLETED
2025-09-20 | 2025-09-02 | 2025-09-23 | Om Construction | 37.93 | 1.7241 | TA509 | 12/1 | COMPLETED
2025-09-20 | 2025-09-16 | 2025-09-24 | Om Construction | 36.15 | 4.0167 | TA509 | 14/1 | COMPLETED
2025-09-21 | 2025-09-13 | 2025-09-27 | Deonath Mahato | 34.79 | 2.3193 | TA509 | 13/4 | COMPLETED
2025-09-21 | 2025-09-16 | 2025-10-04 | Devi Const I | 34.79 | 1.8311 | TA509 | 12/2 | COMPLETED
2025-09-21 | 2025-09-20 | 2025-09-26 | Devi Const I | 37.93 | 5.4186 | TA509 | 9/1 | COMPLETED
2025-09-21 | 2025-09-15 | 2025-09-23 | Devi Const Ii | 43.8 | 4.8667 | TA509 | 22/1 | COMPLETED
2025-09-21 | 2025-09-19 | 2025-09-25 | Hemlal Mahato Ii Anita Devi | 36.15 | 5.1643 | TA509 | 16/9 | COMPLETED
2025-09-21 | 2025-09-02 | 2025-09-23 | Om Construction | 37.93 | 1.7241 | TA509 | 12/1 | COMPLETED
2025-09-21 | 2025-09-16 | 2025-09-24 | Om Construction | 36.15 | 4.0167 | TA509 | 14/1 | COMPLETED
2025-09-22 | 2025-09-13 | 2025-09-27 | Deonath Mahato | 34.79 | 2.3193 | TA509 | 13/4 | COMPLETED
2025-09-22 | 2025-09-16 | 2025-10-04 | Devi Const I | 34.79 | 1.8311 | TA509 | 12/2 | COMPLETED
2025-09-22 | 2025-09-20 | 2025-09-26 | Devi Const I | 37.93 | 5.4186 | TA509 | 9/1 | COMPLETED
2025-09-22 | 2025-09-15 | 2025-09-23 | Devi Const Ii | 43.8 | 4.8667 | TA509 | 22/1 | COMPLETED
2025-09-22 | 2025-09-19 | 2025-09-25 | Hemlal Mahato Ii Anita Devi | 36.15 | 5.1643 | TA509 | 16/9 | COMPLETED
2025-09-22 | 2025-09-02 | 2025-09-23 | Om Construction | 37.93 | 1.7241 | TA509 | 12/1 | COMPLETED
2025-09-22 | 2025-09-16 | 2025-09-24 | Om Construction | 36.15 | 4.0167 | TA509 | 14/1 | COMPLETED
2025-09-23 | 2025-09-13 | 2025-09-27 | Deonath Mahato | 34.79 | 2.3193 | TA509 | 13/4 | COMPLETED
2025-09-23 | 2025-09-16 | 2025-10-04 | Devi Const I | 34.79 | 1.8311 | TA509 | 12/2 | COMPLETED
2025-09-23 | 2025-09-20 | 2025-09-26 | Devi Const I | 37.93 | 5.4186 | TA509 | 9/1 | COMPLETED
2025-09-23 | 2025-09-15 | 2025-09-23 | Devi Const Ii | 43.8 | 4.8667 | TA509 | 22/1 | COMPLETED
2025-09-23 | 2025-09-19 | 2025-09-25 | Hemlal Mahato Ii Anita Devi | 36.15 | 5.1643 | TA509 | 16/9 | COMPLETED
2025-09-23 | 2025-09-23 | 2025-09-29 | Jawala Singh | 34.79 | 4.97 | TA509 | 20/2 | COMPLETED
2025-09-23 | 2025-09-02 | 2025-09-23 | Om Construction | 37.93 | 1.7241 | TA509 | 12/1 | COMPLETED
2025-09-23 | 2025-09-16 | 2025-09-24 | Om Construction | 36.15 | 4.0167 | TA509 | 14/1 | COMPLETED
2025-09-24 | 2025-09-13 | 2025-09-27 | Deonath Mahato | 34.79 | 2.3193 | TA509 | 13/4 | COMPLETED
2025-09-24 | 2025-09-16 | 2025-10-04 | Devi Const I | 34.79 | 1.8311 | TA509 | 12/2 | COMPLETED
2025-09-24 | 2025-09-20 | 2025-09-26 | Devi Const I | 37.93 | 5.4186 | TA509 | 9/1 | COMPLETED
2025-09-24 | 2025-09-24 | 2025-09-30 | Devi Const Ii | 36.15 | 5.1643 | TA509 | 14/2 | COMPLETED
2025-09-24 | 2025-09-19 | 2025-09-25 | Hemlal Mahato Ii Anita Devi | 36.15 | 5.1643 | TA509 | 16/9 | COMPLETED
2025-09-24 | 2025-09-23 | 2025-09-29 | Jawala Singh | 34.79 | 4.97 | TA509 | 20/2 | COMPLETED
2025-09-24 | 2025-09-16 | 2025-09-24 | Om Construction | 36.15 | 4.0167 | TA509 | 14/1 | COMPLETED
2025-09-25 | 2025-09-13 | 2025-09-27 | Deonath Mahato | 34.79 | 2.3193 | TA509 | 13/4 | COMPLETED
2025-09-25 | 2025-09-16 | 2025-10-04 | Devi Const I | 34.79 | 1.8311 | TA509 | 12/2 | COMPLETED
2025-09-25 | 2025-09-20 | 2025-09-26 | Devi Const I | 37.93 | 5.4186 | TA509 | 9/1 | COMPLETED
2025-09-25 | 2025-09-25 | 2025-10-01 | Devi Const I | 43.8 | 6.2571 | TA509 | 16/11 | COMPLETED
2025-09-25 | 2025-09-24 | 2025-09-30 | Devi Const Ii | 36.15 | 5.1643 | TA509 | 14/2 | COMPLETED
2025-09-25 | 2025-09-19 | 2025-09-25 | Hemlal Mahato Ii Anita Devi | 36.15 | 5.1643 | TA509 | 16/9 | COMPLETED
2025-09-25 | 2025-09-23 | 2025-09-29 | Jawala Singh | 34.79 | 4.97 | TA509 | 20/2 | COMPLETED
2025-09-26 | 2025-09-13 | 2025-09-27 | Deonath Mahato | 34.79 | 2.3193 | TA509 | 13/4 | COMPLETED
2025-09-26 | 2025-09-16 | 2025-10-04 | Devi Const I | 34.79 | 1.8311 | TA509 | 12/2 | COMPLETED
2025-09-26 | 2025-09-20 | 2025-09-26 | Devi Const I | 37.93 | 5.4186 | TA509 | 9/1 | COMPLETED
2025-09-26 | 2025-09-25 | 2025-10-01 | Devi Const I | 43.8 | 6.2571 | TA509 | 16/11 | COMPLETED
2025-09-26 | 2025-09-24 | 2025-09-30 | Devi Const Ii | 36.15 | 5.1643 | TA509 | 14/2 | COMPLETED
2025-09-26 | 2025-09-23 | 2025-09-29 | Jawala Singh | 34.79 | 4.97 | TA509 | 20/2 | COMPLETED
2025-09-27 | 2025-09-13 | 2025-09-27 | Deonath Mahato | 34.79 | 2.3193 | TA509 | 13/4 | COMPLETED
2025-09-27 | 2025-09-16 | 2025-10-04 | Devi Const I | 34.79 | 1.8311 | TA509 | 12/2 | COMPLETED
2025-09-27 | 2025-09-25 | 2025-10-01 | Devi Const I | 43.8 | 6.2571 | TA509 | 16/11 | COMPLETED
2025-09-27 | 2025-09-24 | 2025-09-30 | Devi Const Ii | 36.15 | 5.1643 | TA509 | 14/2 | COMPLETED
2025-09-27 | 2025-09-23 | 2025-09-29 | Jawala Singh | 34.79 | 4.97 | TA509 | 20/2 | COMPLETED
2025-09-27 | 2025-09-27 | 2025-10-02 | Jawala Singh | 36.15 | 6.025 | TA509 | 10/1 | COMPLETED
2025-09-28 | 2025-09-16 | 2025-10-04 | Devi Const I | 34.79 | 1.8311 | TA509 | 12/2 | COMPLETED
2025-09-28 | 2025-09-25 | 2025-10-01 | Devi Const I | 43.8 | 6.2571 | TA509 | 16/11 | COMPLETED
2025-09-28 | 2025-09-24 | 2025-09-30 | Devi Const Ii | 36.15 | 5.1643 | TA509 | 14/2 | COMPLETED
2025-09-28 | 2025-09-23 | 2025-09-29 | Jawala Singh | 34.79 | 4.97 | TA509 | 20/2 | COMPLETED
2025-09-28 | 2025-09-27 | 2025-10-02 | Jawala Singh | 36.15 | 6.025 | TA509 | 10/1 | COMPLETED
2025-09-29 | 2025-09-16 | 2025-10-04 | Devi Const I | 34.79 | 1.8311 | TA509 | 12/2 | COMPLETED
2025-09-29 | 2025-09-25 | 2025-10-01 | Devi Const I | 43.8 | 6.2571 | TA509 | 16/11 | COMPLETED
2025-09-29 | 2025-09-24 | 2025-09-30 | Devi Const Ii | 36.15 | 5.1643 | TA509 | 14/2 | COMPLETED
2025-09-29 | 2025-09-23 | 2025-09-29 | Jawala Singh | 34.79 | 4.97 | TA509 | 20/2 | COMPLETED
2025-09-29 | 2025-09-27 | 2025-10-02 | Jawala Singh | 36.15 | 6.025 | TA509 | 10/1 | COMPLETED
2025-09-30 | 2025-09-16 | 2025-10-04 | Devi Const I | 34.79 | 1.8311 | TA509 | 12/2 | COMPLETED
2025-09-30 | 2025-09-25 | 2025-10-01 | Devi Const I | 43.8 | 6.2571 | TA509 | 16/11 | COMPLETED
2025-09-30 | 2025-09-24 | 2025-09-30 | Devi Const Ii | 36.15 | 5.1643 | TA509 | 14/2 | COMPLETED
2025-09-30 | 2025-09-27 | 2025-10-02 | Jawala Singh | 36.15 | 6.025 | TA509 | 10/1 | COMPLETED
2025-10-01 | 2025-10-01 | 2025-10-13 | Deonath Mahato | 35.602 | 2.7386 | TA509 | 13/1 | COMPLETED
2025-10-01 | 2025-09-16 | 2025-10-04 | Devi Const I | 34.79 | 1.8311 | TA509 | 12/2 | COMPLETED
2025-10-01 | 2025-09-25 | 2025-10-01 | Devi Const I | 43.8 | 6.2571 | TA509 | 16/11 | COMPLETED
2025-10-01 | 2025-10-01 | 2025-10-06 | Devi Const Ii | 37.93 | 6.3217 | TA509 | 24/6 | COMPLETED
2025-10-01 | 2025-10-01 | 2025-10-06 | Hemlal Mahato I Anita Devi | 36.15 | 6.025 | TA509 | 16/7 | COMPLETED
2025-10-01 | 2025-09-27 | 2025-10-02 | Jawala Singh | 36.15 | 6.025 | TA509 | 10/1 | COMPLETED
2025-10-02 | 2025-10-01 | 2025-10-13 | Deonath Mahato | 35.602 | 2.7386 | TA509 | 13/1 | COMPLETED
2025-10-02 | 2025-09-16 | 2025-10-04 | Devi Const I | 34.79 | 1.8311 | TA509 | 12/2 | COMPLETED
2025-10-02 | 2025-10-01 | 2025-10-06 | Devi Const Ii | 37.93 | 6.3217 | TA509 | 24/6 | COMPLETED
2025-10-02 | 2025-10-01 | 2025-10-06 | Hemlal Mahato I Anita Devi | 36.15 | 6.025 | TA509 | 16/7 | COMPLETED
2025-10-02 | 2025-09-27 | 2025-10-02 | Jawala Singh | 36.15 | 6.025 | TA509 | 10/1 | COMPLETED
2025-10-03 | 2025-10-01 | 2025-10-13 | Deonath Mahato | 35.602 | 2.7386 | TA509 | 13/1 | COMPLETED
2025-10-03 | 2025-09-16 | 2025-10-04 | Devi Const I | 34.79 | 1.8311 | TA509 | 12/2 | COMPLETED
2025-10-03 | 2025-10-01 | 2025-10-06 | Devi Const Ii | 37.93 | 6.3217 | TA509 | 24/6 | COMPLETED
2025-10-03 | 2025-10-01 | 2025-10-06 | Hemlal Mahato I Anita Devi | 36.15 | 6.025 | TA509 | 16/7 | COMPLETED
2025-10-04 | 2025-10-01 | 2025-10-13 | Deonath Mahato | 35.602 | 2.7386 | TA509 | 13/1 | COMPLETED
2025-10-04 | 2025-09-16 | 2025-10-04 | Devi Const I | 34.79 | 1.8311 | TA509 | 12/2 | COMPLETED
2025-10-04 | 2025-10-01 | 2025-10-06 | Devi Const Ii | 37.93 | 6.3217 | TA509 | 24/6 | COMPLETED
2025-10-04 | 2025-10-01 | 2025-10-06 | Hemlal Mahato I Anita Devi | 36.15 | 6.025 | TA509 | 16/7 | COMPLETED
2025-10-05 | 2025-10-01 | 2025-10-13 | Deonath Mahato | 35.602 | 2.7386 | TA509 | 13/1 | COMPLETED
2025-10-05 | 2025-10-01 | 2025-10-06 | Devi Const Ii | 37.93 | 6.3217 | TA509 | 24/6 | COMPLETED
2025-10-05 | 2025-10-01 | 2025-10-06 | Hemlal Mahato I Anita Devi | 36.15 | 6.025 | TA509 | 16/7 | COMPLETED
2025-10-05 | 2025-10-05 | 2025-10-16 | Om Construction | 34.79 | 2.8992 | TA509 | 14/3 | COMPLETED
2025-10-06 | 2025-10-01 | 2025-10-13 | Deonath Mahato | 35.602 | 2.7386 | TA509 | 13/1 | COMPLETED
2025-10-06 | 2025-10-01 | 2025-10-06 | Devi Const Ii | 37.93 | 6.3217 | TA509 | 24/6 | COMPLETED
2025-10-06 | 2025-10-01 | 2025-10-06 | Hemlal Mahato I Anita Devi | 36.15 | 6.025 | TA509 | 16/7 | COMPLETED
2025-10-06 | 2025-10-05 | 2025-10-16 | Om Construction | 34.79 | 2.8992 | TA509 | 14/3 | COMPLETED
2025-10-07 | 2025-10-01 | 2025-10-13 | Deonath Mahato | 35.602 | 2.7386 | TA509 | 13/1 | COMPLETED
2025-10-07 | 2025-10-07 | 2025-10-11 | Devi Const | 36.15 | 7.23 | TA509 | 24/7 | COMPLETED
2025-10-07 | 2025-10-05 | 2025-10-16 | Om Construction | 34.79 | 2.8992 | TA509 | 14/3 | COMPLETED
2025-10-08 | 2025-10-01 | 2025-10-13 | Deonath Mahato | 35.602 | 2.7386 | TA509 | 13/1 | COMPLETED
2025-10-08 | 2025-10-07 | 2025-10-11 | Devi Const | 36.15 | 7.23 | TA509 | 24/7 | COMPLETED
2025-10-08 | 2025-10-05 | 2025-10-16 | Om Construction | 34.79 | 2.8992 | TA509 | 14/3 | COMPLETED
2025-10-09 | 2025-10-01 | 2025-10-13 | Deonath Mahato | 35.602 | 2.7386 | TA509 | 13/1 | COMPLETED
2025-10-09 | 2025-10-07 | 2025-10-11 | Devi Const | 36.15 | 7.23 | TA509 | 24/7 | COMPLETED
2025-10-09 | 2025-10-05 | 2025-10-16 | Om Construction | 34.79 | 2.8992 | TA509 | 14/3 | COMPLETED
2025-10-10 | 2025-10-01 | 2025-10-13 | Deonath Mahato | 35.602 | 2.7386 | TA509 | 13/1 | COMPLETED
2025-10-10 | 2025-10-07 | 2025-10-11 | Devi Const | 36.15 | 7.23 | TA509 | 24/7 | COMPLETED
2025-10-10 | 2025-10-05 | 2025-10-16 | Om Construction | 34.79 | 2.8992 | TA509 | 14/3 | COMPLETED
2025-10-11 | 2025-10-01 | 2025-10-13 | Deonath Mahato | 35.602 | 2.7386 | TA509 | 13/1 | COMPLETED
2025-10-11 | 2025-10-07 | 2025-10-11 | Devi Const | 36.15 | 7.23 | TA509 | 24/7 | COMPLETED
2025-10-11 | 2025-10-05 | 2025-10-16 | Om Construction | 34.79 | 2.8992 | TA509 | 14/3 | COMPLETED
2025-10-12 | 2025-10-01 | 2025-10-13 | Deonath Mahato | 35.602 | 2.7386 | TA509 | 13/1 | COMPLETED
2025-10-12 | 2025-10-12 | 2025-10-16 | Devi Const | 36.15 | 7.23 | TA509 | 8/10 | COMPLETED
2025-10-12 | 2025-10-05 | 2025-10-16 | Om Construction | 34.79 | 2.8992 | TA509 | 14/3 | COMPLETED
2025-10-13 | 2025-10-01 | 2025-10-13 | Deonath Mahato | 35.602 | 2.7386 | TA509 | 13/1 | COMPLETED
2025-10-13 | 2025-10-12 | 2025-10-16 | Devi Const | 36.15 | 7.23 | TA509 | 8/10 | COMPLETED
2025-10-13 | 2025-10-05 | 2025-10-16 | Om Construction | 34.79 | 2.8992 | TA509 | 14/3 | COMPLETED
2025-10-14 | 2025-10-12 | 2025-10-16 | Devi Const | 36.15 | 7.23 | TA509 | 8/10 | COMPLETED
2025-10-14 | 2025-10-05 | 2025-10-16 | Om Construction | 34.79 | 2.8992 | TA509 | 14/3 | COMPLETED
2025-10-15 | 2025-10-12 | 2025-10-16 | Devi Const | 36.15 | 7.23 | TA509 | 8/10 | COMPLETED
2025-10-15 | 2025-10-05 | 2025-10-16 | Om Construction | 34.79 | 2.8992 | TA509 | 14/3 | COMPLETED
2025-10-16 | 2025-10-12 | 2025-10-16 | Devi Const | 36.15 | 7.23 | TA509 | 8/10 | COMPLETED
2025-10-16 | 2025-10-16 | 2025-10-22 | Devi Const | 34.79 | 4.97 | TA509 | 8/9 | COMPLETED
2025-10-16 | 2025-10-05 | 2025-10-16 | Om Construction | 34.79 | 2.8992 | TA509 | 14/3 | COMPLETED
2025-10-17 | 2025-10-16 | 2025-10-22 | Devi Const | 34.79 | 4.97 | TA509 | 8/9 | COMPLETED
2025-10-18 | 2025-10-16 | 2025-10-22 | Devi Const | 34.79 | 4.97 | TA509 | 8/9 | COMPLETED
2025-10-19 | 2025-10-16 | 2025-10-22 | Devi Const | 34.79 | 4.97 | TA509 | 8/9 | COMPLETED
2025-10-20 | 2025-10-16 | 2025-10-22 | Devi Const | 34.79 | 4.97 | TA509 | 8/9 | COMPLETED
2025-10-21 | 2025-10-16 | 2025-10-22 | Devi Const | 34.79 | 4.97 | TA509 | 8/9 | COMPLETED
2025-10-22 | 2025-10-16 | 2025-10-22 | Devi Const | 34.79 | 4.97 | TA509 | 8/9 | COMPLETED
2025-10-22 | 2025-10-22 | 2025-10-25 | Devi Const | 37.93 | 9.4825 | TA509 | 8/8 | COMPLETED
2025-10-23 | 2025-10-22 | 2025-10-25 | Devi Const | 37.93 | 9.4825 | TA509 | 8/8 | COMPLETED
2025-10-24 | 2025-10-22 | 2025-10-25 | Devi Const | 37.93 | 9.4825 | TA509 | 8/8 | COMPLETED
2025-10-25 | 2025-10-22 | 2025-10-25 | Devi Const | 37.93 | 9.4825 | TA509 | 8/8 | COMPLETED
2025-11-03 | 2025-11-03 | 2025-11-07 | Devi Const | 37.93 | 7.586 | TA509 | 8/4 | COMPLETED
2025-11-04 | 2025-11-03 | 2025-11-07 | Devi Const | 37.93 | 7.586 | TA509 | 8/4 | COMPLETED
2025-11-05 | 2025-11-03 | 2025-11-07 | Devi Const | 37.93 | 7.586 | TA509 | 8/4 | COMPLETED
2025-11-06 | 2025-11-03 | 2025-11-07 | Devi Const | 37.93 | 7.586 | TA509 | 8/4 | COMPLETED
2025-11-07 | 2025-11-03 | 2025-11-07 | Devi Const | 37.93 | 7.586 | TA509 | 8/4 | COMPLETED
2025-11-07 | 2025-11-07 | 2025-11-11 | Devi Const | 34.79 | 6.958 | TA509 | 10/2 | COMPLETED
2025-11-08 | 2025-11-07 | 2025-11-11 | Devi Const | 34.79 | 6.958 | TA509 | 10/2 | COMPLETED
2025-11-09 | 2025-11-07 | 2025-11-11 | Devi Const | 34.79 | 6.958 | TA509 | 10/2 | COMPLETED
2025-11-10 | 2025-11-07 | 2025-11-11 | Devi Const | 34.79 | 6.958 | TA509 | 10/2 | COMPLETED
2025-11-11 | 2025-11-07 | 2025-11-11 | Devi Const | 34.79 | 6.958 | TA509 | 10/2 | COMPLETED
2025-11-11 | 2025-11-11 | 2025-11-16 | Devi Const | 34.79 | 5.7983 | TA509 | 12/3 | COMPLETED
2025-11-12 | 2025-11-11 | 2025-11-16 | Devi Const | 34.79 | 5.7983 | TA509 | 12/3 | COMPLETED
2025-11-13 | 2025-11-11 | 2025-11-16 | Devi Const | 34.79 | 5.7983 | TA509 | 12/3 | COMPLETED
2025-11-14 | 2025-11-11 | 2025-11-16 | Devi Const | 34.79 | 5.7983 | TA509 | 12/3 | COMPLETED
2025-11-15 | 2025-11-11 | 2025-11-16 | Devi Const | 34.79 | 5.7983 | TA509 | 12/3 | COMPLETED
2025-11-16 | 2025-11-11 | 2025-11-16 | Devi Const | 34.79 | 5.7983 | TA509 | 12/3 | COMPLETED
2024-01-28 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TB408 | 60/7
2024-01-29 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TB408 | 60/7
2024-01-30 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TB408 | 60/7
2024-01-31 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TB408 | 60/7
2024-02-01 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 59/13
2024-02-01 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TB408 | 60/7
2024-02-02 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 59/13
2024-02-02 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TB408 | 60/7
2024-02-03 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 59/13
2024-02-03 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TB408 | 63/6
2024-02-03 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TB408 | 60/7
2024-02-04 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 59/13
2024-02-04 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TB408 | 63/6
2024-02-04 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TB408 | 60/7
2024-02-05 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 59/13
2024-02-05 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/5
2024-02-05 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TB408 | 63/6
2024-02-06 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 59/13
2024-02-06 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/5
2024-02-06 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TB408 | 63/6
2024-02-07 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 59/13
2024-02-07 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/5
2024-02-07 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TB408 | 63/6
2024-02-08 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TB408 | 59/14
2024-02-08 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/5
2024-02-08 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TB408 | 63/6
2024-02-09 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TB408 | 59/14
2024-02-09 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/5
2024-02-09 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TB408 | 63/6
2024-02-09 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/8
2024-02-10 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TB408 | 59/14
2024-02-10 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/5
2024-02-10 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TB408 | 63/6
2024-02-10 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/8
2024-02-11 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TB408 | 59/14
2024-02-11 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/5
2024-02-11 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TB408 | 63/7
2024-02-11 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/8
2024-02-12 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TB408 | 59/14
2024-02-12 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/6
2024-02-12 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TB408 | 63/7
2024-02-12 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/8
2024-02-13 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TB408 | 59/14
2024-02-13 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TB408 | 59/12
2024-02-13 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/6
2024-02-13 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TB408 | 63/7
2024-02-13 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/8
2024-02-14 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TB408 | 59/12
2024-02-14 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/6
2024-02-14 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TB408 | 63/7
2024-02-14 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/8
2024-02-15 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TB408 | 59/12
2024-02-15 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/6
2024-02-15 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TB408 | 63/7
2024-02-15 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TB408 | 63/8
2024-02-15 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/8
2024-02-15 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/10
2024-02-16 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TB408 | 59/12
2024-02-16 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/6
2024-02-16 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TB408 | 63/8
2024-02-16 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/10
2024-02-17 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TB408 | 59/12
2024-02-17 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/6
2024-02-17 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TB408 | 62/5
2024-02-17 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TB408 | 63/8
2024-02-17 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/10
2024-02-18 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TB408 | 59/12
2024-02-18 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/6
2024-02-18 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/7
2024-02-18 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TB408 | 62/5
2024-02-18 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TB408 | 63/8
2024-02-18 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/10
2024-02-19 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TB408 | 59/12
2024-02-19 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/7
2024-02-19 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TB408 | 62/5
2024-02-19 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TB408 | 63/8
2024-02-19 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/10
2024-02-20 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TB408 | 59/12
2024-02-20 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 59/10
2024-02-20 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/7
2024-02-20 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TB408 | 62/5
2024-02-20 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TB408 | 63/8
2024-02-20 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TB408 | 64/1
2024-02-20 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/10
2024-02-21 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 59/10
2024-02-21 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/7
2024-02-21 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TB408 | 62/5
2024-02-21 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TB408 | 64/1
2024-02-21 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/10
2024-02-21 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TB408 | 60/11
2024-02-22 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 59/10
2024-02-22 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/7
2024-02-22 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TB408 | 62/5
2024-02-22 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 62/4
2024-02-22 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TB408 | 64/1
2024-02-22 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TB408 | 60/11
2024-02-23 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 59/10
2024-02-23 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/7
2024-02-23 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 62/4
2024-02-23 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TB408 | 64/1
2024-02-23 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TB408 | 60/11
2024-02-24 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 59/10
2024-02-24 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 59/9
2024-02-24 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/7
2024-02-24 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TB408 | 59/8
2024-02-24 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 62/4
2024-02-24 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TB408 | 64/1
2024-02-24 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/4
2024-02-24 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TB408 | 60/11
2024-02-25 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 59/9
2024-02-25 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TB408 | 59/8
2024-02-25 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 62/4
2024-02-25 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/4
2024-02-25 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TB408 | 60/11
2024-02-26 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 59/9
2024-02-26 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TB408 | 59/8
2024-02-26 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 62/4
2024-02-26 | 2024-02-26 | 2024-02-28 | Sobha Devi | 37.5044 | 12.5015 | TB408 | 62/3
2024-02-26 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/4
2024-02-26 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TB408 | 60/11
2024-02-26 | 2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TB408 | 60/6
2024-02-27 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 59/9
2024-02-27 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TB408 | 59/8
2024-02-27 | 2024-02-26 | 2024-02-28 | Sobha Devi | 37.5044 | 12.5015 | TB408 | 62/3
2024-02-27 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/4
2024-02-27 | 2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TB408 | 60/6
2024-02-28 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 59/9
2024-02-28 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TB408 | 59/8
2024-02-28 | 2024-02-26 | 2024-02-28 | Sobha Devi | 37.5044 | 12.5015 | TB408 | 62/3
2024-02-28 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/4
2024-02-28 | 2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TB408 | 60/6
2024-02-29 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/2
2024-02-29 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TB408 | 59/8
2024-02-29 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TB408 | 59/16
2024-02-29 | 2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 62/2
2024-02-29 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/4
2024-02-29 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/5
2024-02-29 | 2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TB408 | 60/6
2024-03-01 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/2
2024-03-01 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TB408 | 59/16
2024-03-01 | 2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 62/2
2024-03-01 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/5
2024-03-02 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/2
2024-03-02 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TB408 | 59/16
2024-03-02 | 2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 62/2
2024-03-02 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/5
2024-03-03 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/2
2024-03-03 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TB408 | 59/16
2024-03-03 | 2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 62/2
2024-03-03 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/5
2024-03-04 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/2
2024-03-04 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TB408 | 59/16
2024-03-04 | 2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 62/7
2024-03-04 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/5
2024-03-05 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/2
2024-03-05 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TB408 | 59/16
2024-03-05 | 2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 62/7
2024-03-06 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/2
2024-03-06 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/4
2024-03-06 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TB408 | 59/16
2024-03-06 | 2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 62/7
2024-03-07 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/4
2024-03-07 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TB408 | 59/16
2024-03-07 | 2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 62/7
2024-03-07 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TB408 | 62/8
2024-03-08 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/4
2024-03-08 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TB408 | 59/16
2024-03-08 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TB408 | 62/8
2024-03-09 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/4
2024-03-09 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TB408 | 59/16
2024-03-09 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TB408 | 62/8
2024-03-10 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/4
2024-03-10 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TB408 | 59/16
2024-03-10 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TB408 | 62/8
2024-03-11 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/4
2024-03-11 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 65/3
2024-03-11 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TB408 | 59/16
2024-03-11 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 60/5
2024-03-11 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TB408 | 62/8
2024-03-11 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 62/9
2024-03-12 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 65/3
2024-03-12 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 60/5
2024-03-12 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 62/9
2024-03-13 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 65/3
2024-03-13 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 60/5
2024-03-13 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 62/9
2024-03-14 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 65/3
2024-03-14 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 60/5
2024-03-14 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 62/9
2024-03-15 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 65/3
2024-03-15 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 60/5
2024-03-15 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 62/9
2024-03-15 | 2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 62/10
2024-03-16 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 65/3
2024-03-16 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 65/5
2024-03-16 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 60/5
2024-03-16 | 2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 62/10
2024-03-17 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 65/5
2024-03-17 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 60/5
2024-03-17 | 2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 62/10
2024-03-18 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 65/5
2024-03-18 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TB408 | 60/4
2024-03-18 | 2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 62/10
2024-03-18 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 61/6
2024-03-19 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 65/5
2024-03-19 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TB408 | 60/4
2024-03-19 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 61/6
2024-03-20 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 65/5
2024-03-20 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/6
2024-03-20 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TB408 | 60/4
2024-03-20 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 61/6
2024-03-21 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/6
2024-03-21 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TB408 | 60/4
2024-03-21 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 61/6
2024-03-21 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/6
2024-03-22 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/6
2024-03-22 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TB408 | 60/4
2024-03-22 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 61/6
2024-03-22 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 61/7
2024-03-22 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/6
2024-03-23 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/6
2024-03-23 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TB408 | 60/4
2024-03-23 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TB408 | 60/3
2024-03-23 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 61/7
2024-03-23 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/6
2024-03-24 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/6
2024-03-24 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TB408 | 60/3
2024-03-24 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 61/7
2024-03-24 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/6
2024-03-25 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/6
2024-03-25 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TB408 | 60/3
2024-03-25 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 61/7
2024-03-25 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/6
2024-03-26 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/6
2024-03-26 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/9
2024-03-26 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TB408 | 60/3
2024-03-26 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 61/7
2024-03-26 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/6
2024-03-26 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/7
2024-03-27 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/9
2024-03-27 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TB408 | 60/3
2024-03-27 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 61/7
2024-03-27 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/7
2024-03-28 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/9
2024-03-28 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TB408 | 60/3
2024-03-28 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 61/7
2024-03-28 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/7
2024-03-29 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/9
2024-03-29 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TB408 | 60/3
2024-03-29 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/7
2024-03-30 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/9
2024-03-30 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TB408 | 60/3
2024-03-30 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/7
2024-03-30 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/8
2024-03-31 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/9
2024-03-31 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 65/11
2024-03-31 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TB408 | 60/3
2024-03-31 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TB408 | 60/2
2024-03-31 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/8
2024-04-01 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 65/11
2024-04-01 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TB408 | 60/2
2024-04-01 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/8
2024-04-01 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TB408 | 63/5
2024-04-02 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 65/11
2024-04-02 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TB408 | 60/2
2024-04-02 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/8
2024-04-02 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TB408 | 63/5
2024-04-03 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 65/11
2024-04-03 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TB408 | 60/2
2024-04-03 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/8
2024-04-03 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/9
2024-04-03 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TB408 | 63/5
2024-04-04 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 65/11
2024-04-04 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TB408 | 60/2
2024-04-04 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/9
2024-04-04 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TB408 | 63/5
2024-04-05 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TB408 | 60/2
2024-04-05 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/9
2024-04-05 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TB408 | 63/5
2024-04-06 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 67/1
2024-04-06 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TB408 | 60/2
2024-04-06 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 61/0
2024-04-06 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/9
2024-04-06 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TB408 | 63/5
2024-04-07 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 67/1
2024-04-07 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TB408 | 60/2
2024-04-07 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 61/0
2024-04-07 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/9
2024-04-07 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TB408 | 63/5
2024-04-07 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TB408 | 63/4
2024-04-08 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 67/1
2024-04-08 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 61/0
2024-04-08 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/9
2024-04-08 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TB408 | 63/4
2024-04-09 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 67/1
2024-04-09 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 61/0
2024-04-09 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TB408 | 63/4
2024-04-10 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 67/1
2024-04-10 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 67/2
2024-04-10 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 61/0
2024-04-10 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TB408 | 63/4
2024-04-11 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 67/2
2024-04-11 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 61/0
2024-04-11 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TB408 | 63/4
2024-04-12 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 67/2
2024-04-12 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TB408 | 63/4
2024-04-13 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 67/2
2024-04-13 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TB408 | 63/4
2024-04-13 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TB408 | 63/3
2024-04-14 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 67/2
2024-04-14 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TB408 | 63/3
2024-04-15 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 67/2
2024-04-15 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 64/10
2024-04-15 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TB408 | 63/3
2024-04-16 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 64/10
2024-04-16 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/2
2024-04-16 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/2
2024-04-16 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TB408 | 63/3
2024-04-17 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 64/10
2024-04-17 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/2
2024-04-17 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/2
2024-04-17 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TB408 | 63/3
2024-04-17 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TB408 | 63/2
2024-04-18 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 64/10
2024-04-18 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TB408 | 60/1
2024-04-18 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/2
2024-04-18 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/2
2024-04-18 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TB408 | 63/2
2024-04-19 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 64/10
2024-04-19 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TB408 | 60/1
2024-04-19 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/2
2024-04-19 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/2
2024-04-19 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TB408 | 63/2
2024-04-20 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 64/10
2024-04-20 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TB408 | 60/1
2024-04-20 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/2
2024-04-20 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/2
2024-04-20 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TB408 | 63/2
2024-04-21 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 65/0
2024-04-21 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TB408 | 60/1
2024-04-21 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/2
2024-04-21 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/2
2024-04-21 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/3
2024-04-21 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TB408 | 63/2
2024-04-22 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 65/0
2024-04-22 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TB408 | 60/1
2024-04-22 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/2
2024-04-22 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TB408 | 61/1
2024-04-22 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/3
2024-04-22 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TB408 | 63/2
2024-04-22 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TB408 | 63/1
2024-04-23 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 65/0
2024-04-23 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TB408 | 60/1
2024-04-23 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TB408 | 61/1
2024-04-23 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/3
2024-04-23 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TB408 | 63/1
2024-04-24 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 65/0
2024-04-24 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TB408 | 60/1
2024-04-24 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TB408 | 61/1
2024-04-24 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/3
2024-04-24 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TB408 | 63/1
2024-04-25 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 65/0
2024-04-25 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TB408 | 60/1
2024-04-25 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TB408 | 61/1
2024-04-25 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/3
2024-04-25 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TB408 | 63/1
2024-04-26 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 65/0
2024-04-26 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TB408 | 61/1
2024-04-26 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/3
2024-04-26 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TB408 | 63/1
2024-04-27 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 65/0
2024-04-27 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/1
2024-04-27 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TB408 | 61/1
2024-04-27 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TB408 | 64/0
2024-04-27 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TB408 | 63/1
2024-04-27 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TB408 | 62/11
2024-04-28 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/1
2024-04-28 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TB408 | 61/1
2024-04-28 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TB408 | 64/0
2024-04-28 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TB408 | 62/11
2024-04-29 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/1
2024-04-29 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TB408 | 61/1
2024-04-29 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 60/9
2024-04-29 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TB408 | 64/0
2024-04-29 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TB408 | 62/11
2024-04-30 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/1
2024-04-30 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 60/9
2024-04-30 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TB408 | 64/0
2024-04-30 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TB408 | 62/11
2024-05-01 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/1
2024-05-01 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 60/9
2024-05-01 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TB408 | 64/0
2024-05-01 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TB408 | 62/11
2024-05-02 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/1
2024-05-02 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 60/9
2024-05-02 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TB408 | 64/0
2024-05-02 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TB408 | 62/11
2024-05-03 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/1
2024-05-03 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 60/9
2024-05-03 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TB408 | 64/0
2024-05-03 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TB408 | 62/11
2024-05-03 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TB408 | 63/0
2024-05-04 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 60/9
2024-05-04 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TB408 | 64/0
2024-05-04 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TB408 | 63/0
2024-05-05 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-05 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 60/9
2024-05-05 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/3
2024-05-05 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TB408 | 64/0
2024-05-05 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TB408 | 63/0
2024-05-06 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-06 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/3
2024-05-06 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TB408 | 63/0
2024-05-07 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-07 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/3
2024-05-07 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TB408 | 63/0
2024-05-08 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-08 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/3
2024-05-08 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TB408 | 63/0
2024-05-09 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-09 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/3
2024-05-09 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TB408 | 63/0
2024-05-10 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-10 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/3
2024-05-10 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TB408 | 63/0
2024-05-11 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-11 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/3
2024-05-11 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TB408 | 61/4
2024-05-11 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TB408 | 63/0
2024-05-12 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-12 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-12 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TB408 | 61/4
2024-05-12 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TB408 | 63/0
2024-05-12 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TB408 | 61/10
2024-05-13 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-13 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-13 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TB408 | 61/4
2024-05-13 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TB408 | 61/10
2024-05-14 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-14 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-14 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TB408 | 61/4
2024-05-14 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TB408 | 61/10
2024-05-15 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-15 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-15 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TB408 | 61/4
2024-05-15 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TB408 | 61/10
2024-05-16 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-16 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-16 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TB408 | 61/4
2024-05-16 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 61/5
2024-05-16 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TB408 | 61/10
2024-05-17 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-17 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-17 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 61/5
2024-05-17 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TB408 | 61/10
2024-05-18 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-18 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-18 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-18 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 61/5
2024-05-18 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TB408 | 61/10
2024-05-19 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-19 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-19 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 61/5
2024-05-19 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TB408 | 61/10
2024-05-19 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TB408 | 61/9
2024-05-20 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-20 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-20 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 61/5
2024-05-20 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TB408 | 61/9
2024-05-21 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-21 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-21 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 61/5
2024-05-21 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TB408 | 61/9
2024-05-22 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-22 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-22 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 61/5
2024-05-22 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TB408 | 61/9
2024-05-23 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-23 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-23 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TB408 | 61/9
2024-05-23 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TB408 | 61/8
2024-05-24 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-24 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-24 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TB408 | 61/8
2024-05-25 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-25 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-25 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TB408 | 61/8
2024-05-26 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-26 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-26 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TB408 | 61/8
2024-05-27 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-27 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-27 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TB408 | 61/8
2024-05-28 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-28 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-28 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TB408 | 61/8
2024-05-29 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-05-29 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-29 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-29 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TB408 | 61/8
2024-05-30 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-05-30 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-30 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-30 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TB408 | 61/8
2024-05-31 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-05-31 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-06-01 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-06-01 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-02 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-06-02 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-03 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-06-03 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-04 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-06-04 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-05 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-06-05 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-06 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-06-06 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-07 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-06-07 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-08 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-06-08 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-09 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-06-09 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-10 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-06-10 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-11 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-06-11 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-12 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-12 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-13 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-13 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-14 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-14 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-15 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-15 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-16 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-16 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-17 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-17 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-18 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-18 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-19 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-19 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-20 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-21 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-22 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-23 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-24 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-25 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-26 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-27 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-07-04 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TB408 | 62/1
2024-07-05 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TB408 | 62/1
2024-07-06 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TB408 | 62/1
2024-07-07 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TB408 | 62/1
2024-07-08 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TB408 | 62/1
2024-07-09 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TB408 | 62/1
2024-07-10 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TB408 | 62/1
2024-07-11 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TB408 | 62/1
2024-07-12 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TB408 | 62/1
2024-07-15 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TB408 | 62/6
2024-07-16 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TB408 | 62/6
2024-07-17 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TB408 | 62/6
2024-07-18 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TB408 | 62/6
2024-07-19 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TB408 | 62/6
2024-07-20 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TB408 | 62/6
2024-07-21 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TB408 | 62/6
2024-07-22 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TB408 | 62/6
2024-07-23 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TB408 | 62/6
2024-07-24 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TB408 | 62/6
2024-07-25 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TB408 | 62/6
2024-07-26 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TB408 | 62/6
2024-08-13 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TB408 | 57/6
2024-08-14 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TB408 | 57/6
2024-08-15 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TB408 | 57/6
2024-08-16 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TB408 | 57/6
2024-08-17 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TB408 | 57/6
2024-08-18 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TB408 | 57/6
2024-08-19 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TB408 | 57/6
2024-08-20 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TB408 | 57/6
2024-08-20 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 57/5
2024-08-21 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 57/5
2024-08-22 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 57/5
2024-08-23 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 57/5
2024-08-23 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TB408 | 10/18
2024-08-24 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 57/5
2024-08-24 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TB408 | 10/18
2024-08-25 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 57/5
2024-08-25 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TB408 | 10/18
2024-08-26 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 57/5
2024-08-26 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TB408 | 10/18
2024-08-27 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-08-27 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TB408 | 10/18
2024-08-28 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-08-28 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TB408 | 10/3
2024-08-28 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-08-28 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TB408 | 10/18
2024-08-29 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-08-29 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TB408 | 10/3
2024-08-29 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-08-29 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TB408 | 10/18
2024-08-30 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-08-30 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TB408 | 10/3
2024-08-30 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-08-30 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TB408 | 10/18
2024-08-30 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 10/17
2024-08-31 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-08-31 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TB408 | 10/3
2024-08-31 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TB408 | 62/0
2024-08-31 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-08-31 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 10/17
2024-09-01 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-01 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TB408 | 10/3
2024-09-01 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TB408 | 62/0
2024-09-01 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-09-01 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 10/17
2024-09-02 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-02 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TB408 | 10/3
2024-09-02 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TB408 | 62/0
2024-09-02 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-09-02 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 10/17
2024-09-03 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-03 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TB408 | 10/3
2024-09-03 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TB408 | 62/0
2024-09-03 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-09-03 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 10/17
2024-09-04 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-04 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TB408 | 10/3
2024-09-04 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TB408 | 62/0
2024-09-04 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-09-04 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 10/17
2024-09-05 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-05 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TB408 | 10/3
2024-09-05 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TB408 | 62/0
2024-09-05 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-09-05 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 10/17
2024-09-06 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-06 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TB408 | 10/3
2024-09-06 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TB408 | 16/3
2024-09-06 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TB408 | 62/0
2024-09-06 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-09-06 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 10/17
2024-09-07 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-07 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TB408 | 16/3
2024-09-07 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TB408 | 62/0
2024-09-07 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-09-07 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 10/17
2024-09-08 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-08 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-08 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TB408 | 16/3
2024-09-08 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TB408 | 62/0
2024-09-08 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-09-08 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 10/17
2024-09-09 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-09 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-09 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TB408 | 16/3
2024-09-09 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-09-09 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TB408 | 10/19
2024-09-10 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-10 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-10 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TB408 | 16/3
2024-09-10 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TB408 | 50/10
2024-09-10 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TB408 | 10/19
2024-09-11 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-11 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-11 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TB408 | 16/3
2024-09-11 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TB408 | 50/10
2024-09-11 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TB408 | 10/19
2024-09-12 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-12 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-12 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TB408 | 16/3
2024-09-12 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TB408 | 50/10
2024-09-12 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TB408 | 10/19
2024-09-13 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-13 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-13 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TB408 | 16/3
2024-09-13 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TB408 | 50/10
2024-09-13 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TB408 | 10/19
2024-09-14 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-14 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-14 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TB408 | 50/10
2024-09-14 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TB408 | 10/19
2024-09-15 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-15 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-15 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TB408 | 50/10
2024-09-15 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TB408 | 10/19
2024-09-16 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-16 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-16 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TB408 | 50/10
2024-09-16 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TB408 | 10/19
2024-09-17 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-17 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-17 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TB408 | 50/10
2024-09-17 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TB408 | 10/19
2024-09-18 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/2
2024-09-18 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-18 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-18 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TB408 | 50/10
2024-09-18 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TB408 | 10/19
2024-09-19 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/2
2024-09-19 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-19 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/6
2024-09-19 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-19 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TB408 | 50/10
2024-09-19 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TB408 | 51/1
2024-09-19 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TB408 | 10/20
2024-09-20 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/2
2024-09-20 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/6
2024-09-20 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-20 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TB408 | 51/1
2024-09-20 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TB408 | 10/20
2024-09-21 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/2
2024-09-21 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/6
2024-09-21 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 15/1
2024-09-21 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-21 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TB408 | 51/1
2024-09-21 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TB408 | 10/20
2024-09-22 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/2
2024-09-22 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/6
2024-09-22 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 15/1
2024-09-22 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-22 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TB408 | 51/1
2024-09-22 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TB408 | 10/20
2024-09-23 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/4
2024-09-23 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/6
2024-09-23 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 15/1
2024-09-23 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-23 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TB408 | 51/1
2024-09-23 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TB408 | 10/20
2024-09-24 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/4
2024-09-24 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/6
2024-09-24 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 15/1
2024-09-24 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-24 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TB408 | 51/1
2024-09-24 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TB408 | 10/20
2024-09-25 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/4
2024-09-25 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/6
2024-09-25 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TB408 | 10/6
2024-09-25 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 15/1
2024-09-25 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-25 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TB408 | 51/1
2024-09-25 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TB408 | 10/20
2024-09-26 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/4
2024-09-26 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/6
2024-09-26 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TB408 | 10/6
2024-09-26 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 15/1
2024-09-26 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TB408 | 51/1
2024-09-26 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TB408 | 51/2
2024-09-27 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/4
2024-09-27 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/6
2024-09-27 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TB408 | 10/6
2024-09-27 | 2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TB408 | 10/14
2024-09-27 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TB408 | 11A/2
2024-09-27 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 57/7
2024-09-27 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TB408 | 51/2
2024-09-28 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/6
2024-09-28 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TB408 | 10/6
2024-09-28 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 14A/1
2024-09-28 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-09-28 | 2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TB408 | 10/14
2024-09-28 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TB408 | 16/4
2024-09-28 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TB408 | 11A/2
2024-09-28 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 57/7
2024-09-28 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TB408 | 51/2
2024-09-29 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/6
2024-09-29 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TB408 | 10/6
2024-09-29 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 14A/1
2024-09-29 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-09-29 | 2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TB408 | 10/14
2024-09-29 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TB408 | 16/4
2024-09-29 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TB408 | 11A/2
2024-09-29 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 57/7
2024-09-29 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TB408 | 51/2
2024-09-30 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/6
2024-09-30 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 14A/1
2024-09-30 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-09-30 | 2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TB408 | 10/14
2024-09-30 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TB408 | 16/4
2024-09-30 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TB408 | 11A/2
2024-09-30 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 57/7
2024-09-30 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TB408 | 51/2
2024-10-01 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 52/7
2024-10-01 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 14A/1
2024-10-01 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-01 | 2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TB408 | 10/14
2024-10-01 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TB408 | 16/4
2024-10-01 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TB408 | 11A/2
2024-10-01 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 57/7
2024-10-01 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TB408 | 51/2
2024-10-02 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 52/7
2024-10-02 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 14A/1
2024-10-02 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-02 | 2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TB408 | 10/14
2024-10-02 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TB408 | 16/4
2024-10-02 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TB408 | 11A/2
2024-10-02 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 50/0
2024-10-02 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TB408 | 51/2
2024-10-03 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 52/7
2024-10-03 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 14A/1
2024-10-03 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-03 | 2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TB408 | 10/14
2024-10-03 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TB408 | 16/4
2024-10-03 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TB408 | 11A/2
2024-10-03 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 50/0
2024-10-03 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TB408 | 51/2
2024-10-04 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/1
2024-10-04 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 52/7
2024-10-04 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-04 | 2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TB408 | 10/14
2024-10-04 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TB408 | 11A/2
2024-10-04 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 50/0
2024-10-04 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TB408 | 51/2
2024-10-05 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/1
2024-10-05 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 52/7
2024-10-05 | 2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TB408 | 10/9
2024-10-05 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-05 | 2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TB408 | 10/14
2024-10-05 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TB408 | 17/1
2024-10-05 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TB408 | 11A/2
2024-10-05 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 50/0
2024-10-06 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/1
2024-10-06 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 52/7
2024-10-06 | 2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TB408 | 10/9
2024-10-06 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-06 | 2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TB408 | 10/14
2024-10-06 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TB408 | 17/1
2024-10-06 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TB408 | 11A/2
2024-10-06 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 50/0
2024-10-07 | 2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TB408 | 10/21
2024-10-07 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/1
2024-10-07 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 52/7
2024-10-07 | 2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TB408 | 10/9
2024-10-07 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-07 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TB408 | 17/1
2024-10-07 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TB408 | 11A/2
2024-10-07 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 50/0
2024-10-07 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TB408 | 50/1
2024-10-07 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TB408 | 50/8
2024-10-08 | 2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TB408 | 10/21
2024-10-08 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/1
2024-10-08 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/8
2024-10-08 | 2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TB408 | 10/9
2024-10-08 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-08 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TB408 | 17/1
2024-10-08 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TB408 | 50/1
2024-10-08 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TB408 | 50/8
2024-10-09 | 2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TB408 | 10/21
2024-10-09 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/8
2024-10-09 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-09 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TB408 | 17/1
2024-10-09 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TB408 | 50/1
2024-10-09 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TB408 | 50/8
2024-10-10 | 2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TB408 | 10/21
2024-10-10 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/8
2024-10-10 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-10 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TB408 | 17/1
2024-10-10 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TB408 | 73/2
2024-10-10 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TB408 | 50/1
2024-10-10 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TB408 | 50/8
2024-10-11 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/8
2024-10-11 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-11 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TB408 | 17/2
2024-10-11 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TB408 | 73/2
2024-10-11 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TB408 | 50/1
2024-10-11 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TB408 | 50/8
2024-10-12 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/8
2024-10-12 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TB408 | 10/4
2024-10-12 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-12 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TB408 | 17/2
2024-10-12 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TB408 | 73/2
2024-10-12 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TB408 | 50/1
2024-10-12 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TB408 | 50/8
2024-10-13 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/8
2024-10-13 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TB408 | 10/4
2024-10-13 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-13 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TB408 | 17/2
2024-10-13 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TB408 | 73/2
2024-10-13 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TB408 | 50/1
2024-10-13 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TB408 | 50/3
2024-10-13 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TB408 | 50/8
2024-10-14 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/8
2024-10-14 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TB408 | 10/4
2024-10-14 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-14 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TB408 | 17/2
2024-10-14 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TB408 | 73/2
2024-10-14 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TB408 | 50/1
2024-10-14 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TB408 | 50/3
2024-10-14 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TB408 | 50/8
2024-10-15 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/8
2024-10-15 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TB408 | 10/4
2024-10-15 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-15 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TB408 | 17/2
2024-10-15 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TB408 | 73/2
2024-10-15 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TB408 | 50/1
2024-10-15 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TB408 | 50/3
2024-10-15 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TB408 | 50/8
2024-10-16 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/8
2024-10-16 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TB408 | 10/4
2024-10-16 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-16 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TB408 | 17/2
2024-10-16 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-16 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TB408 | 73/2
2024-10-16 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TB408 | 50/3
2024-10-16 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TB408 | 50/8
2024-10-17 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/8
2024-10-17 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TB408 | 10/4
2024-10-17 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-17 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TB408 | 17/2
2024-10-17 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-17 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TB408 | 73/2
2024-10-17 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TB408 | 50/3
2024-10-17 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TB408 | 59/11
2024-10-18 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/8
2024-10-18 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TB408 | 16/0
2024-10-18 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-18 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TB408 | 17/2
2024-10-18 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-18 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-18 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TB408 | 73/2
2024-10-18 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TB408 | 50/3
2024-10-18 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/2
2024-10-18 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TB408 | 59/11
2024-10-19 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TB408 | 19/0
2024-10-19 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/8
2024-10-19 | 2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TB408 | 10/8
2024-10-19 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TB408 | 16/0
2024-10-19 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-19 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TB408 | 17/2
2024-10-19 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-19 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-19 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TB408 | 73/2
2024-10-19 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/2
2024-10-19 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TB408 | 59/11
2024-10-20 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 64/11
2024-10-20 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TB408 | 19/0
2024-10-20 | 2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TB408 | 10/8
2024-10-20 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TB408 | 16/0
2024-10-20 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TB408 | 16/2
2024-10-20 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-20 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-20 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TB408 | 73/2
2024-10-20 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/2
2024-10-20 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TB408 | 59/11
2024-10-21 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TB408 | 17/3
2024-10-21 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 64/11
2024-10-21 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TB408 | 19/0
2024-10-21 | 2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TB408 | 10/8
2024-10-21 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TB408 | 16/0
2024-10-21 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TB408 | 16/2
2024-10-21 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-21 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-21 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 73/1
2024-10-21 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/2
2024-10-21 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TB408 | 59/11
2024-10-22 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TB408 | 17/3
2024-10-22 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 64/11
2024-10-22 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TB408 | 19/0
2024-10-22 | 2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TB408 | 10/8
2024-10-22 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TB408 | 16/0
2024-10-22 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TB408 | 16/2
2024-10-22 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-22 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-22 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 73/1
2024-10-22 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/2
2024-10-22 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TB408 | 59/11
2024-10-23 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TB408 | 17/3
2024-10-23 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 64/11
2024-10-23 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TB408 | 19/0
2024-10-23 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TB408 | 16/0
2024-10-23 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TB408 | 55/6
2024-10-23 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TB408 | 16/2
2024-10-23 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-23 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-23 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 73/1
2024-10-23 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/2
2024-10-23 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TB408 | 59/11
2024-10-24 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TB408 | 17/3
2024-10-24 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 64/11
2024-10-24 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TB408 | 19/0
2024-10-24 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TB408 | 16/0
2024-10-24 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TB408 | 55/6
2024-10-24 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TB408 | 16/2
2024-10-24 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-24 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-24 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 73/1
2024-10-24 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/2
2024-10-24 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/4
2024-10-24 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TB408 | 59/11
2024-10-25 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TB408 | 17/3
2024-10-25 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TB408 | 19/0
2024-10-25 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TB408 | 16/0
2024-10-25 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TB408 | 55/6
2024-10-25 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TB408 | 16/2
2024-10-25 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-25 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-25 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 73/1
2024-10-25 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/4
2024-10-25 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TB408 | 59/11
2024-10-26 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TB408 | 17/3
2024-10-26 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TB408 | 19/0
2024-10-26 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TB408 | 16/0
2024-10-26 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TB408 | 55/6
2024-10-26 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TB408 | 16/2
2024-10-26 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-26 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-26 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 73/1
2024-10-26 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/4
2024-10-26 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TB408 | 59/11
2024-10-27 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TB408 | 17/3
2024-10-27 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TB408 | 16/0
2024-10-27 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TB408 | 55/6
2024-10-27 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-27 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-27 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 73/1
2024-10-27 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/4
2024-10-27 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TB408 | 59/3
2024-10-28 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TB408 | 55/6
2024-10-28 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-28 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-28 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 73/1
2024-10-28 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/4
2024-10-28 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TB408 | 59/3
2024-10-29 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TB408 | 55/6
2024-10-29 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-29 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-29 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 73/1
2024-10-29 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/4
2024-10-29 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TB408 | 59/3
2024-10-30 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TB408 | 55/6
2024-10-30 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-30 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-30 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/4
2024-10-30 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TB408 | 59/3
2024-10-31 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TB408 | 55/6
2024-10-31 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-31 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-31 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TB408 | 59/3
2024-11-01 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TB408 | 55/6
2024-11-01 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TB408 | 55/5
2024-11-01 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-11-01 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-11-01 | 2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 50/7
2024-11-01 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TB408 | 59/3
2024-11-01 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TB408 | 59/4
2024-11-02 | 2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TB408 | 10/11
2024-11-02 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TB408 | 55/5
2024-11-02 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-02 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-11-02 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-11-02 | 2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 50/7
2024-11-02 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TB408 | 59/3
2024-11-02 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TB408 | 59/4
2024-11-03 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TB408 | 16/5
2024-11-03 | 2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TB408 | 10/11
2024-11-03 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TB408 | 55/5
2024-11-03 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-03 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-11-03 | 2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 50/7
2024-11-03 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TB408 | 59/4
2024-11-04 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TB408 | 16/5
2024-11-04 | 2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TB408 | 10/11
2024-11-04 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TB408 | 55/5
2024-11-04 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-04 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TB408 | 17/0
2024-11-04 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-11-04 | 2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 50/7
2024-11-04 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/6
2024-11-04 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TB408 | 59/4
2024-11-05 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TB408 | 16/5
2024-11-05 | 2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TB408 | 10/11
2024-11-05 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TB408 | 16/1
2024-11-05 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TB408 | 55/5
2024-11-05 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-05 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TB408 | 17/0
2024-11-05 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-11-05 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/6
2024-11-05 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TB408 | 59/4
2024-11-06 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TB408 | 16/5
2024-11-06 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TB408 | 16/1
2024-11-06 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TB408 | 55/5
2024-11-06 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-06 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TB408 | 17/0
2024-11-06 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-11-06 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/6
2024-11-06 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TB408 | 59/4
2024-11-07 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TB408 | 16/5
2024-11-07 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TB408 | 16/1
2024-11-07 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TB408 | 55/5
2024-11-07 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-07 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TB408 | 17/0
2024-11-07 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-11-07 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/6
2024-11-07 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TB408 | 59/4
2024-11-07 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TB408 | 43/9
2024-11-08 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TB408 | 16/5
2024-11-08 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TB408 | 16/1
2024-11-08 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TB408 | 55/5
2024-11-08 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-08 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TB408 | 17/0
2024-11-08 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-11-08 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/6
2024-11-08 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TB408 | 59/4
2024-11-08 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TB408 | 43/9
2024-11-09 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TB408 | 16/5
2024-11-09 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/9
2024-11-09 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TB408 | 16/1
2024-11-09 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TB408 | 55/5
2024-11-09 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-09 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TB408 | 17/0
2024-11-09 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/6
2024-11-09 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TB408 | 59/4
2024-11-09 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TB408 | 43/9
2024-11-10 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/9
2024-11-10 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TB408 | 55/5
2024-11-10 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-10 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TB408 | 17/0
2024-11-10 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TB408 | 11/5
2024-11-10 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/6
2024-11-10 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TB408 | 43/9
2024-11-11 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/9
2024-11-11 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TB408 | 13/2
2024-11-11 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TB408 | 55/5
2024-11-11 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-11 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TB408 | 17/0
2024-11-11 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TB408 | 11/5
2024-11-11 | 2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/7
2024-11-11 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TB408 | 43/9
2024-11-12 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/9
2024-11-12 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TB408 | 13/2
2024-11-12 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TB408 | 55/5
2024-11-12 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-12 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-12 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TB408 | 17/0
2024-11-12 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TB408 | 11/5
2024-11-12 | 2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/7
2024-11-12 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TB408 | 43/9
2024-11-13 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/9
2024-11-13 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 73/8
2024-11-13 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-13 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TB408 | 13/2
2024-11-13 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-13 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-13 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TB408 | 17/0
2024-11-13 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TB408 | 11/5
2024-11-13 | 2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/7
2024-11-13 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TB408 | 43/9
2024-11-14 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 73/8
2024-11-14 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-14 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TB408 | 13/2
2024-11-14 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-14 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-14 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TB408 | 17/0
2024-11-14 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TB408 | 11/5
2024-11-14 | 2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/7
2024-11-14 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TB408 | 43/9
2024-11-15 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 73/8
2024-11-15 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-15 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TB408 | 13/2
2024-11-15 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-15 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-15 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TB408 | 11/5
2024-11-15 | 2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/6
2024-11-15 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TB408 | 43/9
2024-11-16 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 73/8
2024-11-16 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-16 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TB408 | 13/2
2024-11-16 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-16 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-16 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TB408 | 11/5
2024-11-16 | 2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/6
2024-11-16 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TB408 | 43/9
2024-11-17 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 73/8
2024-11-17 | 2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TB408 | 73/6
2024-11-17 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-17 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TB408 | 13/2
2024-11-17 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-17 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-17 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TB408 | 11/5
2024-11-17 | 2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/6
2024-11-17 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TB408 | 43/9
2024-11-18 | 2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TB408 | 73/6
2024-11-18 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-18 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TB408 | 13/2
2024-11-18 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-18 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-18 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TB408 | 11/5
2024-11-18 | 2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/6
2024-11-18 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 49/4
2024-11-18 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TB408 | 43/9
2024-11-19 | 2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TB408 | 73/6
2024-11-19 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-19 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-19 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-19 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 49/4
2024-11-19 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TB408 | 43/8
2024-11-20 | 2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TB408 | 73/6
2024-11-20 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-20 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-20 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-20 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 49/4
2024-11-20 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TB408 | 43/8
2024-11-21 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-21 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-21 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-21 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 49/4
2024-11-21 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TB408 | 43/8
2024-11-22 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TB408 | 17/5
2024-11-22 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-22 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-22 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-22 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 49/4
2024-11-22 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TB408 | 43/8
2024-11-23 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TB408 | 17/5
2024-11-23 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-23 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-23 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 49/5
2024-11-23 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TB408 | 43/8
2024-11-24 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TB408 | 17/5
2024-11-24 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/9
2024-11-24 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-24 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-24 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TB408 | 72/3
2024-11-24 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 49/5
2024-11-24 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TB408 | 43/8
2024-11-25 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TB408 | 17/5
2024-11-25 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/9
2024-11-25 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-25 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TB408 | 59/1
2024-11-25 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TB408 | 72/3
2024-11-25 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 49/5
2024-11-25 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TB408 | 43/8
2024-11-26 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TB408 | 17/5
2024-11-26 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/9
2024-11-26 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TB408 | 52/9
2024-11-26 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TB408 | 59/1
2024-11-26 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TB408 | 72/3
2024-11-26 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 49/5
2024-11-26 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TB408 | 43/8
2024-11-27 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TB408 | 17/5
2024-11-27 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/9
2024-11-27 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TB408 | 52/9
2024-11-27 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TB408 | 59/1
2024-11-27 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TB408 | 72/3
2024-11-27 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 49/5
2024-11-27 | 2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 49/2
2024-11-27 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TB408 | 43/8
2024-11-28 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TB408 | 17/5
2024-11-28 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/9
2024-11-28 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TB408 | 52/9
2024-11-28 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TB408 | 11A/7
2024-11-28 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TB408 | 59/1
2024-11-28 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TB408 | 72/3
2024-11-28 | 2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 49/2
2024-11-29 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TB408 | 17/5
2024-11-29 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/9
2024-11-29 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TB408 | 52/9
2024-11-29 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TB408 | 11A/7
2024-11-29 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TB408 | 59/1
2024-11-29 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TB408 | 72/3
2024-11-29 | 2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 49/2
2024-11-30 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TB408 | 17/5
2024-11-30 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/9
2024-11-30 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TB408 | 52/9
2024-11-30 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TB408 | 10/12
2024-11-30 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TB408 | 11A/7
2024-11-30 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TB408 | 59/1
2024-11-30 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TB408 | 72/3
2024-11-30 | 2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 49/2
2024-12-01 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/3
2024-12-01 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TB408 | 52/9
2024-12-01 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TB408 | 10/12
2024-12-01 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TB408 | 11A/7
2024-12-01 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TB408 | 59/1
2024-12-02 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/3
2024-12-02 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TB408 | 52/9
2024-12-02 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TB408 | 10/12
2024-12-02 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TB408 | 11A/7
2024-12-02 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TB408 | 59/1
2024-12-02 | 2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 49/3
2024-12-03 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/3
2024-12-03 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TB408 | 52/9
2024-12-03 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TB408 | 10/12
2024-12-03 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TB408 | 11A/7
2024-12-03 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TB408 | 59/1
2024-12-03 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-03 | 2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 49/3
2024-12-04 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/3
2024-12-04 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TB408 | 52/9
2024-12-04 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TB408 | 10/12
2024-12-04 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TB408 | 11A/7
2024-12-04 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-04 | 2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 49/3
2024-12-05 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/3
2024-12-05 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TB408 | 52/9
2024-12-05 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TB408 | 10/12
2024-12-05 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TB408 | 11A/7
2024-12-05 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-05 | 2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 49/3
2024-12-06 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/3
2024-12-06 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TB408 | 10/12
2024-12-06 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TB408 | 11A/7
2024-12-06 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-06 | 2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/1
2024-12-07 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/3
2024-12-07 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TB408 | 10/12
2024-12-07 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-07 | 2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/1
2024-12-08 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TB408 | 10/12
2024-12-08 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-08 | 2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/1
2024-12-09 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/3
2024-12-09 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TB408 | 11A/6
2024-12-09 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TB408 | 10/12
2024-12-09 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-09 | 2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/1
2024-12-10 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/3
2024-12-10 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TB408 | 11A/6
2024-12-10 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TB408 | 10/12
2024-12-10 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-11 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/3
2024-12-11 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TB408 | 11A/6
2024-12-11 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TB408 | 10/12
2024-12-11 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-12 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/3
2024-12-12 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TB408 | 11A/6
2024-12-12 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-13 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/3
2024-12-13 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TB408 | 11A/6
2024-12-13 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-14 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TB408 | 11A/6
2024-12-14 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-15 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TB408 | 11A/6
2024-12-15 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-16 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TB408 | 11A/6
2024-12-16 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-20 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/8
2024-12-21 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/8
2024-12-22 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/8
2024-12-23 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/8
2024-12-24 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/8
2024-12-25 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TB408 | 11A/5
2024-12-25 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/8
2024-12-25 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2024-12-26 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TB408 | 11A/5
2024-12-26 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/8
2024-12-26 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2024-12-27 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TB408 | 11A/5
2024-12-27 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/8
2024-12-27 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2024-12-28 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TB408 | 11A/5
2024-12-28 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/7
2024-12-28 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2024-12-29 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TB408 | 11A/5
2024-12-29 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/7
2024-12-29 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2024-12-30 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TB408 | 11A/5
2024-12-30 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/7
2024-12-30 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2024-12-31 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TB408 | 11A/5
2024-12-31 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/7
2024-12-31 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2025-01-01 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TB408 | 11A/5
2025-01-01 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/7
2025-01-01 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2025-01-02 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TB408 | 11A/5
2025-01-02 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/7
2025-01-02 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2025-01-03 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 73/0
2025-01-03 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TB408 | 11A/5
2025-01-03 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/7
2025-01-03 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2025-01-04 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 73/0
2025-01-04 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TB408 | 11A/5
2025-01-04 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TB408 | 53/8
2025-01-04 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/7
2025-01-04 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2025-01-05 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 73/0
2025-01-05 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TB408 | 53/8
2025-01-05 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TB408 | 74/0
2025-01-05 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2025-01-06 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 73/0
2025-01-06 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TB408 | 53/8
2025-01-06 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TB408 | 74/0
2025-01-06 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2025-01-07 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 73/0
2025-01-07 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TB408 | 53/8
2025-01-07 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TB408 | 74/0
2025-01-07 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2025-01-08 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 73/0
2025-01-08 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TB408 | 53/8
2025-01-08 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TB408 | 74/0
2025-01-08 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 43/1
2025-01-09 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 73/0
2025-01-09 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TB408 | 53/8
2025-01-09 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TB408 | 74/0
2025-01-09 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 43/1
2025-01-10 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/4
2025-01-10 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TB408 | 53/7
2025-01-10 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TB408 | 74/0
2025-01-10 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 43/1
2025-01-11 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TB408 | 43/7
2025-01-11 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/4
2025-01-11 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TB408 | 53/7
2025-01-11 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-11 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TB408 | 74/0
2025-01-11 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 43/1
2025-01-12 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TB408 | 43/7
2025-01-12 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/4
2025-01-12 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TB408 | 53/7
2025-01-12 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-12 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TB408 | 74/0
2025-01-12 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 43/1
2025-01-13 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TB408 | 43/7
2025-01-13 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/4
2025-01-13 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TB408 | 53/7
2025-01-13 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-13 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TB408 | 74/0
2025-01-13 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 43/1
2025-01-14 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TB408 | 43/7
2025-01-14 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/4
2025-01-14 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TB408 | 53/7
2025-01-14 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-14 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TB408 | 73/7
2025-01-14 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 43/1
2025-01-15 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TB408 | 43/7
2025-01-15 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/5
2025-01-15 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TB408 | 53/7
2025-01-15 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-15 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TB408 | 73/7
2025-01-15 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 43/1
2025-01-16 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TB408 | 43/7
2025-01-16 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/5
2025-01-16 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TB408 | 53/7
2025-01-16 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-16 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TB408 | 73/7
2025-01-16 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 43/1
2025-01-17 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TB408 | 43/7
2025-01-17 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/5
2025-01-17 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TB408 | 53/7
2025-01-17 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-17 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TB408 | 73/7
2025-01-17 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 43/1
2025-01-18 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TB408 | 43/7
2025-01-18 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/5
2025-01-18 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TB408 | 53/7
2025-01-18 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-18 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TB408 | 73/7
2025-01-19 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TB408 | 43/6
2025-01-19 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/5
2025-01-19 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 53/6
2025-01-19 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-19 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TB408 | 73/7
2025-01-20 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TB408 | 43/6
2025-01-20 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 53/6
2025-01-20 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-21 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TB408 | 43/6
2025-01-21 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 72/0
2025-01-21 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 53/6
2025-01-21 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-22 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TB408 | 43/6
2025-01-22 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 72/0
2025-01-22 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 53/6
2025-01-22 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-23 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TB408 | 43/6
2025-01-23 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 72/0
2025-01-23 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 53/6
2025-01-23 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-24 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TB408 | 43/6
2025-01-24 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 72/0
2025-01-24 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 53/6
2025-01-24 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-25 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TB408 | 43/6
2025-01-25 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 72/0
2025-01-25 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 53/6
2025-01-25 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-26 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TB408 | 43/6
2025-01-26 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 72/0
2025-01-26 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 53/6
2025-01-26 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-27 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TB408 | 43/6
2025-01-27 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 72/0
2025-01-27 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 53/6
2025-01-27 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-28 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TB408 | 43/6
2025-01-28 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 72/1
2025-01-28 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 53/6
2025-01-28 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-29 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TB408 | 43/6
2025-01-29 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 72/1
2025-01-29 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 53/6
2025-01-29 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-29 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 65/10
2025-01-30 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 72/1
2025-01-30 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 53/6
2025-01-30 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 65/10
2025-01-31 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TB408 | 1A/1
2025-01-31 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 72/1
2025-01-31 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 65/10
2025-01-31 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TB408 | 51/0
2025-02-01 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TB408 | 1A/1
2025-02-01 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 72/1
2025-02-01 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 65/10
2025-02-01 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TB408 | 51/0
2025-02-02 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TB408 | 1A/1
2025-02-02 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 72/1
2025-02-02 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 72/2
2025-02-02 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 65/10
2025-02-02 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TB408 | 51/0
2025-02-03 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TB408 | 1A/1
2025-02-03 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 72/2
2025-02-03 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 65/10
2025-02-03 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TB408 | 51/0
2025-02-04 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TB408 | 1A/1
2025-02-04 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 72/2
2025-02-04 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 65/10
2025-02-04 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TB408 | 51/0
2025-02-05 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TB408 | 1A/1
2025-02-05 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 72/2
2025-02-05 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 65/10
2025-02-05 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TB408 | 49/0
2025-02-05 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TB408 | 51/0
2025-02-06 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TB408 | 1A/1
2025-02-06 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 72/2
2025-02-06 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 65/10
2025-02-06 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TB408 | 49/0
2025-02-06 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TB408 | 51/0
2025-02-07 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TB408 | 1A/1
2025-02-07 | 2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TB408 | 71/8
2025-02-07 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TB408 | 49/0
2025-02-07 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TB408 | 51/0
2025-02-08 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TB408 | 1A/1
2025-02-08 | 2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TB408 | 71/8
2025-02-08 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TB408 | 49/0
2025-02-08 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TB408 | 52/0
2025-02-09 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TB408 | 1A/1
2025-02-09 | 2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TB408 | 71/8
2025-02-09 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TB408 | 49/0
2025-02-09 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TB408 | 52/0
2025-02-10 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TB408 | 1A/1
2025-02-10 | 2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TB408 | 71/8
2025-02-10 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TB408 | 49/0
2025-02-10 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TB408 | 52/0
2025-02-11 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TB408 | 1A/2
2025-02-11 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/7
2025-02-11 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TB408 | 49/0
2025-02-11 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TB408 | 52/0
2025-02-12 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TB408 | 1A/2
2025-02-12 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/7
2025-02-12 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TB408 | 49/0
2025-02-12 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TB408 | 52/0
2025-02-13 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TB408 | 1A/2
2025-02-13 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/7
2025-02-13 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TB408 | 49/0
2025-02-13 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TB408 | 52/0
2025-02-14 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TB408 | 1A/2
2025-02-14 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/7
2025-02-14 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TB408 | 49/0
2025-02-14 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TB408 | 52/0
2025-02-15 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TB408 | 1A/2
2025-02-15 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/7
2025-02-15 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TB408 | 50/5
2025-02-16 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TB408 | 1A/2
2025-02-16 | 2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TB408 | 71/6
2025-02-16 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TB408 | 50/5
2025-02-17 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TB408 | 1A/2
2025-02-17 | 2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TB408 | 71/6
2025-02-17 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TB408 | 50/5
2025-02-18 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TB408 | 1A/2
2025-02-18 | 2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TB408 | 71/6
2025-02-18 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TB408 | 50/5
2025-02-19 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TB408 | 1A/3
2025-02-19 | 2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TB408 | 71/6
2025-02-19 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TB408 | 50/5
2025-02-20 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TB408 | 1A/3
2025-02-20 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/5
2025-02-20 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TB408 | 50/5
2025-02-21 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TB408 | 1A/3
2025-02-21 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/5
2025-02-22 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TB408 | 1A/3
2025-02-22 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/5
2025-02-23 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TB408 | 1A/3
2025-02-23 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/5
2025-02-24 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TB408 | 1A/3
2025-02-24 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/5
2025-02-25 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TB408 | 1A/3
2025-02-25 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/4
2025-02-26 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TB408 | 1A/3
2025-02-26 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/4
2025-02-26 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-02-27 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TB408 | 1A/3
2025-02-27 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/4
2025-02-27 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-02-28 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TB408 | 1A/3
2025-02-28 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/4
2025-02-28 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-03-01 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/4
2025-03-01 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 53/5
2025-03-01 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-03-02 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TB408 | 71/3
2025-03-02 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 53/5
2025-03-02 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-03-03 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TB408 | 71/3
2025-03-03 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 53/5
2025-03-03 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-03-04 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TB408 | 71/3
2025-03-04 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 53/5
2025-03-04 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-03-05 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TB408 | 71/3
2025-03-05 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 53/5
2025-03-05 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-03-06 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TB408 | 71/3
2025-03-06 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 53/5
2025-03-06 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-03-07 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TB408 | 71/3
2025-03-07 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 53/5
2025-03-07 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-03-08 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/2
2025-03-08 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-03-08 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TB408 | 70/3
2025-03-09 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/2
2025-03-09 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 53/4
2025-03-09 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-03-09 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TB408 | 70/3
2025-03-10 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/2
2025-03-10 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 53/4
2025-03-10 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-03-10 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TB408 | 70/3
2025-03-11 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/2
2025-03-11 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 53/4
2025-03-11 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TB408 | 70/3
2025-03-12 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/2
2025-03-12 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 53/4
2025-03-12 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TB408 | 70/3
2025-03-13 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 71/1
2025-03-13 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 53/4
2025-03-13 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TB408 | 70/3
2025-03-13 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-14 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 71/1
2025-03-14 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 53/4
2025-03-14 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TB408 | 70/3
2025-03-14 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-15 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 71/1
2025-03-15 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 53/4
2025-03-15 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TB408 | 70/3
2025-03-15 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-16 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 71/1
2025-03-16 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 53/4
2025-03-16 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TB408 | 70/3
2025-03-16 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-17 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 71/1
2025-03-17 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 53/4
2025-03-17 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-18 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 71/1
2025-03-18 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TB408 | 53/3
2025-03-18 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-19 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 71/0
2025-03-19 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TB408 | 53/3
2025-03-19 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-20 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 71/0
2025-03-20 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TB408 | 53/3
2025-03-20 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TB408 | 70/5
2025-03-20 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-21 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 71/0
2025-03-21 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TB408 | 53/3
2025-03-21 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TB408 | 70/5
2025-03-21 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-22 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 71/0
2025-03-22 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TB408 | 53/3
2025-03-22 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TB408 | 70/5
2025-03-22 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-23 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 71/0
2025-03-23 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TB408 | 53/3
2025-03-23 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TB408 | 70/5
2025-03-23 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-24 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 71/0
2025-03-24 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TB408 | 53/3
2025-03-24 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TB408 | 70/5
2025-03-24 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-25 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 71/0
2025-03-25 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TB408 | 53/3
2025-03-25 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TB408 | 70/5
2025-03-25 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-26 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/11
2025-03-26 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TB408 | 53/2
2025-03-26 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TB408 | 70/5
2025-03-26 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-27 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/11
2025-03-27 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TB408 | 53/2
2025-03-27 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TB408 | 70/5
2025-03-27 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-28 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/11
2025-03-28 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TB408 | 53/2
2025-03-28 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TB408 | 70/5
2025-03-28 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-29 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/11
2025-03-29 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TB408 | 53/2
2025-03-29 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TB408 | 70/5
2025-03-29 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-30 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/11
2025-03-30 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TB408 | 53/2
2025-03-30 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-31 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/11
2025-03-31 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 70/10
2025-03-31 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TB408 | 53/2
2025-03-31 | 2025-03-31 | 2025-04-02 | Sobha Devi | 38.8476 | 12.9492 | TB408 | 47/9
2025-03-31 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-01 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 70/10
2025-04-01 | 2025-03-31 | 2025-04-02 | Sobha Devi | 38.8476 | 12.9492 | TB408 | 47/9
2025-04-01 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-02 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 70/10
2025-04-02 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TB408 | 53/1
2025-04-02 | 2025-03-31 | 2025-04-02 | Sobha Devi | 38.8476 | 12.9492 | TB408 | 47/9
2025-04-02 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-03 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 70/10
2025-04-03 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TB408 | 53/1
2025-04-03 | 2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 47/8
2025-04-03 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-04 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 70/10
2025-04-04 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TB408 | 53/1
2025-04-04 | 2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 47/8
2025-04-04 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-05 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TB408 | 53/1
2025-04-05 | 2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 47/8
2025-04-05 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-06 | 2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TB408 | 70/9
2025-04-06 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TB408 | 53/1
2025-04-06 | 2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 47/8
2025-04-06 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-07 | 2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TB408 | 70/9
2025-04-07 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TB408 | 53/1
2025-04-07 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-08 | 2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TB408 | 70/9
2025-04-08 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TB408 | 53/1
2025-04-08 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-09 | 2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TB408 | 70/9
2025-04-09 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TB408 | 53/1
2025-04-09 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-10 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TB408 | 53/1
2025-04-10 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-11 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TB408 | 53/1
2025-04-11 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-12 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-12 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-13 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-13 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-14 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-14 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-15 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-16 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-17 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-18 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-19 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-20 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-21 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-22 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-23 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-24 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-25 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-26 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-27 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/4
2025-04-27 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-28 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/4
2025-04-28 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-29 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/4
2025-04-30 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/4
2025-05-01 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/4
2025-05-02 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/4
2025-05-10 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-05-11 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-05-12 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-05-13 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-05-14 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-05-15 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-05-16 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-05-17 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-05-18 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-05-19 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-05-19 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-05-20 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-05-20 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-05-20 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TB408 | 67/0
2025-05-21 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-05-21 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-05-21 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TB408 | 67/0
2025-05-22 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-05-22 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-05-22 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TB408 | 67/0
2025-05-23 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-05-23 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-05-23 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TB408 | 67/0
2025-05-24 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-05-24 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-05-24 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TB408 | 67/0
2025-05-25 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-05-25 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-05-25 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TB408 | 67/0
2025-05-26 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-05-26 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-05-26 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TB408 | 67/0
2025-05-27 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-05-27 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-05-27 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TB408 | 67/0
2025-05-28 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-05-28 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-05-28 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TB408 | 67/0
2025-05-29 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-05-29 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-05-29 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TB408 | 67/0
2025-05-30 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-05-30 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-05-31 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-05-31 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-01 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-06-01 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-02 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-06-02 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-03 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-06-03 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-04 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-04 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-06-04 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-05 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-05 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-06-05 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-06 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-06 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-06-06 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-07 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-07 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-06-07 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-08 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-08 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-06-08 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-09 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-09 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-06-09 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-10 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-10 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-06-10 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-11 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-11 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-06-11 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-06-11 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TB408 | 1A/6 | Crane erection+Derrick Pole
2025-06-11 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-12 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-12 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-06-12 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TB408 | 1A/6 | Crane erection+Derrick Pole
2025-06-12 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-13 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-13 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-06-13 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TB408 | 1A/6 | Crane erection+Derrick Pole
2025-06-13 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-14 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-14 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-06-14 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TB408 | 1A/6 | Crane erection+Derrick Pole
2025-06-14 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-15 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-15 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-06-15 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TB408 | 1A/6 | Crane erection+Derrick Pole
2025-06-15 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-16 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-16 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-06-16 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TB408 | 1A/6 | Crane erection+Derrick Pole
2025-06-16 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-17 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-17 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-06-17 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TB408 | 1A/6 | Crane erection+Derrick Pole
2025-06-17 | 2025-06-17 | 2025-06-22 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 70/7 | Derrick
2025-06-17 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-18 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-18 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-06-18 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TB408 | 1A/6 | Crane erection+Derrick Pole
2025-06-18 | 2025-06-17 | 2025-06-22 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 70/7 | Derrick
2025-06-18 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-19 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-19 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-06-19 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TB408 | 1A/6 | Crane erection+Derrick Pole
2025-06-19 | 2025-06-17 | 2025-06-22 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 70/7 | Derrick
2025-06-19 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-20 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-20 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-06-20 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TB408 | 1A/6 | Crane erection+Derrick Pole
2025-06-20 | 2025-06-17 | 2025-06-22 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 70/7 | Derrick
2025-06-20 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-21 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-21 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-06-21 | 2025-06-17 | 2025-06-22 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 70/7 | Derrick
2025-06-21 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-22 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-22 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-06-22 | 2025-06-17 | 2025-06-22 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 70/7 | Derrick
2025-06-22 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-22 | 2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TB408 | 70/2 | Derrick
2025-06-23 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-23 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-06-23 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-23 | 2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TB408 | 70/2 | Derrick
2025-06-24 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-24 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-06-24 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-24 | 2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TB408 | 70/2 | Derrick
2025-06-25 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-25 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-06-25 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-25 | 2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TB408 | 70/2 | Derrick
2025-06-26 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-26 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-06-26 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-26 | 2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TB408 | 70/2 | Derrick
2025-06-27 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-27 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-06-27 | 2025-06-27 | 2025-07-01 | Jwala Singh | 38.8476 | 7.7695 | TB408 | 8/9 | Derrick
2025-06-27 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-27 | 2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TB408 | 70/2 | Derrick
2025-06-28 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-28 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-06-28 | 2025-06-27 | 2025-07-01 | Jwala Singh | 38.8476 | 7.7695 | TB408 | 8/9 | Derrick
2025-06-28 | 2025-06-28 | 2025-07-03 | Jwala Singh Suraj Kumar | 38.8476 | 6.4746 | TB408 | 69/1 | Derrick
2025-06-28 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-28 | 2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TB408 | 70/2 | Derrick
2025-06-29 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-29 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-06-29 | 2025-06-27 | 2025-07-01 | Jwala Singh | 38.8476 | 7.7695 | TB408 | 8/9 | Derrick
2025-06-29 | 2025-06-28 | 2025-07-03 | Jwala Singh Suraj Kumar | 38.8476 | 6.4746 | TB408 | 69/1 | Derrick
2025-06-29 | 2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TB408 | 70/2 | Derrick
2025-06-30 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-30 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-06-30 | 2025-06-27 | 2025-07-01 | Jwala Singh | 38.8476 | 7.7695 | TB408 | 8/9 | Derrick
2025-06-30 | 2025-06-28 | 2025-07-03 | Jwala Singh Suraj Kumar | 38.8476 | 6.4746 | TB408 | 69/1 | Derrick
2025-06-30 | 2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TB408 | 70/2 | Derrick
2025-07-01 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-07-01 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-01 | 2025-06-27 | 2025-07-01 | Jwala Singh | 38.8476 | 7.7695 | TB408 | 8/9 | Derrick
2025-07-01 | 2025-06-28 | 2025-07-03 | Jwala Singh Suraj Kumar | 38.8476 | 6.4746 | TB408 | 69/1 | Derrick
2025-07-01 | 2025-07-01 | 2025-07-08 | Satyam Enterprises Vijay | 38.8476 | 4.856 | TB408 | 70/1 | Derrick
2025-07-02 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-07-02 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-02 | 2025-06-28 | 2025-07-03 | Jwala Singh Suraj Kumar | 38.8476 | 6.4746 | TB408 | 69/1 | Derrick
2025-07-02 | 2025-07-01 | 2025-07-08 | Satyam Enterprises Vijay | 38.8476 | 4.856 | TB408 | 70/1 | Derrick
2025-07-03 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-07-03 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-03 | 2025-06-28 | 2025-07-03 | Jwala Singh Suraj Kumar | 38.8476 | 6.4746 | TB408 | 69/1 | Derrick
2025-07-03 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TB408 | 70/0 | Derrick
2025-07-03 | 2025-07-01 | 2025-07-08 | Satyam Enterprises Vijay | 38.8476 | 4.856 | TB408 | 70/1 | Derrick
2025-07-04 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-07-04 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-04 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TB408 | 70/0 | Derrick
2025-07-04 | 2025-07-01 | 2025-07-08 | Satyam Enterprises Vijay | 38.8476 | 4.856 | TB408 | 70/1 | Derrick
2025-07-05 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-07-05 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-05 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TB408 | 70/0 | Derrick
2025-07-05 | 2025-07-01 | 2025-07-08 | Satyam Enterprises Vijay | 38.8476 | 4.856 | TB408 | 70/1 | Derrick
2025-07-06 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-07-06 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-06 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TB408 | 70/0 | Derrick
2025-07-06 | 2025-07-01 | 2025-07-08 | Satyam Enterprises Vijay | 38.8476 | 4.856 | TB408 | 70/1 | Derrick
2025-07-07 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-07-07 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-07-07 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-07 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10 | Derrick
2025-07-07 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TB408 | 70/0 | Derrick
2025-07-07 | 2025-07-01 | 2025-07-08 | Satyam Enterprises Vijay | 38.8476 | 4.856 | TB408 | 70/1 | Derrick
2025-07-08 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-07-08 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-07-08 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-08 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10 | Derrick
2025-07-08 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TB408 | 70/0 | Derrick
2025-07-08 | 2025-07-01 | 2025-07-08 | Satyam Enterprises Vijay | 38.8476 | 4.856 | TB408 | 70/1 | Derrick
2025-07-08 | 2025-07-08 | 2025-07-14 | Satyam Enterprises Vijay | 38.8476 | 5.5497 | TB408 | 70/8 | Derrick
2025-07-09 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-07-09 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-07-09 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-09 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10 | Derrick
2025-07-09 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TB408 | 70/0 | Derrick
2025-07-09 | 2025-07-08 | 2025-07-14 | Satyam Enterprises Vijay | 38.8476 | 5.5497 | TB408 | 70/8 | Derrick
2025-07-10 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-07-10 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-07-10 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5 | Derrick
2025-07-10 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-10 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10 | Derrick
2025-07-10 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TB408 | 70/0 | Derrick
2025-07-10 | 2025-07-08 | 2025-07-14 | Satyam Enterprises Vijay | 38.8476 | 5.5497 | TB408 | 70/8 | Derrick
2025-07-11 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-07-11 | 2025-07-11 | 2025-07-16 | Arawali 2 | 37.5044 | 6.2507 | TB408 | 2/8 | Derrick
2025-07-11 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-07-11 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5 | Derrick
2025-07-11 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-11 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10 | Derrick
2025-07-11 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TB408 | 70/0 | Derrick
2025-07-11 | 2025-07-08 | 2025-07-14 | Satyam Enterprises Vijay | 38.8476 | 5.5497 | TB408 | 70/8 | Derrick
2025-07-12 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-07-12 | 2025-07-11 | 2025-07-16 | Arawali 2 | 37.5044 | 6.2507 | TB408 | 2/8 | Derrick
2025-07-12 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-07-12 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5 | Derrick
2025-07-12 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-12 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10 | Derrick
2025-07-12 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TB408 | 70/0 | Derrick
2025-07-12 | 2025-07-08 | 2025-07-14 | Satyam Enterprises Vijay | 38.8476 | 5.5497 | TB408 | 70/8 | Derrick
2025-07-13 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-07-13 | 2025-07-11 | 2025-07-16 | Arawali 2 | 37.5044 | 6.2507 | TB408 | 2/8 | Derrick
2025-07-13 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-07-13 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5 | Derrick
2025-07-13 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-13 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10 | Derrick
2025-07-13 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TB408 | 70/0 | Derrick
2025-07-13 | 2025-07-08 | 2025-07-14 | Satyam Enterprises Vijay | 38.8476 | 5.5497 | TB408 | 70/8 | Derrick
2025-07-14 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-07-14 | 2025-07-11 | 2025-07-16 | Arawali 2 | 37.5044 | 6.2507 | TB408 | 2/8 | Derrick
2025-07-14 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-07-14 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5 | Derrick
2025-07-14 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-14 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10 | Derrick
2025-07-14 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TB408 | 70/0 | Derrick
2025-07-14 | 2025-07-14 | 2025-07-21 | Jwala Singh Suraj Kumar | 57.5972 | 7.1997 | TB408 | 69/0 | Derrick
2025-07-14 | 2025-07-14 | 2025-07-23 | Priyanka Devi 2 | 37.5044 | 3.7504 | TB408 | 18/3 | Derrick
2025-07-14 | 2025-07-08 | 2025-07-14 | Satyam Enterprises Vijay | 38.8476 | 5.5497 | TB408 | 70/8 | Derrick
2025-07-15 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-07-15 | 2025-07-11 | 2025-07-16 | Arawali 2 | 37.5044 | 6.2507 | TB408 | 2/8 | Derrick
2025-07-15 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-07-15 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5 | Derrick
2025-07-15 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-15 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10 | Derrick
2025-07-15 | 2025-07-14 | 2025-07-21 | Jwala Singh Suraj Kumar | 57.5972 | 7.1997 | TB408 | 69/0 | Derrick
2025-07-15 | 2025-07-14 | 2025-07-23 | Priyanka Devi 2 | 37.5044 | 3.7504 | TB408 | 18/3 | Derrick
2025-07-16 | 2025-07-11 | 2025-07-16 | Arawali 2 | 37.5044 | 6.2507 | TB408 | 2/8 | Derrick
2025-07-16 | 2025-07-16 | 2025-07-23 | Arawali 2 | 37.5044 | 4.688 | TB408 | 2/9 | Derrick
2025-07-16 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-07-16 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5 | Derrick
2025-07-16 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-16 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10 | Derrick
2025-07-16 | 2025-07-14 | 2025-07-21 | Jwala Singh Suraj Kumar | 57.5972 | 7.1997 | TB408 | 69/0 | Derrick
2025-07-16 | 2025-07-14 | 2025-07-23 | Priyanka Devi 2 | 37.5044 | 3.7504 | TB408 | 18/3 | Derrick
2025-07-17 | 2025-07-16 | 2025-07-23 | Arawali 2 | 37.5044 | 4.688 | TB408 | 2/9 | Derrick
2025-07-17 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-07-17 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5 | Derrick
2025-07-17 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-17 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10 | Derrick
2025-07-17 | 2025-07-14 | 2025-07-21 | Jwala Singh Suraj Kumar | 57.5972 | 7.1997 | TB408 | 69/0 | Derrick
2025-07-17 | 2025-07-14 | 2025-07-23 | Priyanka Devi 2 | 37.5044 | 3.7504 | TB408 | 18/3 | Derrick
2025-07-18 | 2025-07-16 | 2025-07-23 | Arawali 2 | 37.5044 | 4.688 | TB408 | 2/9 | Derrick
2025-07-18 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-07-18 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5 | Derrick
2025-07-18 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-18 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10 | Derrick
2025-07-18 | 2025-07-14 | 2025-07-21 | Jwala Singh Suraj Kumar | 57.5972 | 7.1997 | TB408 | 69/0 | Derrick
2025-07-18 | 2025-07-14 | 2025-07-23 | Priyanka Devi 2 | 37.5044 | 3.7504 | TB408 | 18/3 | Derrick
2025-07-19 | 2025-07-16 | 2025-07-23 | Arawali 2 | 37.5044 | 4.688 | TB408 | 2/9 | Derrick
2025-07-19 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-07-19 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5 | Derrick
2025-07-19 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-19 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10 | Derrick
2025-07-19 | 2025-07-14 | 2025-07-21 | Jwala Singh Suraj Kumar | 57.5972 | 7.1997 | TB408 | 69/0 | Derrick
2025-07-19 | 2025-07-14 | 2025-07-23 | Priyanka Devi 2 | 37.5044 | 3.7504 | TB408 | 18/3 | Derrick
2025-07-19 | 2025-07-19 | 2025-07-22 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/3 | Derrick
2025-07-20 | 2025-07-16 | 2025-07-23 | Arawali 2 | 37.5044 | 4.688 | TB408 | 2/9 | Derrick
2025-07-20 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-07-20 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5 | Derrick
2025-07-20 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-20 | 2025-07-14 | 2025-07-21 | Jwala Singh Suraj Kumar | 57.5972 | 7.1997 | TB408 | 69/0 | Derrick
2025-07-20 | 2025-07-14 | 2025-07-23 | Priyanka Devi 2 | 37.5044 | 3.7504 | TB408 | 18/3 | Derrick
2025-07-20 | 2025-07-19 | 2025-07-22 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/3 | Derrick
2025-07-21 | 2025-07-16 | 2025-07-23 | Arawali 2 | 37.5044 | 4.688 | TB408 | 2/9 | Derrick
2025-07-21 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-07-21 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5 | Derrick
2025-07-21 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-21 | 2025-07-21 | 2025-07-31 | Dharmendra Munnilal Pusplata | 38.8476 | 3.5316 | TB408 | 27/2 | Derrick
2025-07-21 | 2025-07-21 | 2025-07-24 | Hazarilal Yadav Poonam Kumari | 38.8476 | 9.7119 | TB408 | 26/2 | Derrick
2025-07-21 | 2025-07-14 | 2025-07-21 | Jwala Singh Suraj Kumar | 57.5972 | 7.1997 | TB408 | 69/0 | Derrick
2025-07-21 | 2025-07-14 | 2025-07-23 | Priyanka Devi 2 | 37.5044 | 3.7504 | TB408 | 18/3 | Derrick
2025-07-21 | 2025-07-19 | 2025-07-22 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/3 | Derrick
2025-07-22 | 2025-07-16 | 2025-07-23 | Arawali 2 | 37.5044 | 4.688 | TB408 | 2/9 | Derrick
2025-07-22 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-07-22 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5 | Derrick
2025-07-22 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-22 | 2025-07-21 | 2025-07-31 | Dharmendra Munnilal Pusplata | 38.8476 | 3.5316 | TB408 | 27/2 | Derrick
2025-07-22 | 2025-07-21 | 2025-07-24 | Hazarilal Yadav Poonam Kumari | 38.8476 | 9.7119 | TB408 | 26/2 | Derrick
2025-07-22 | 2025-07-14 | 2025-07-23 | Priyanka Devi 2 | 37.5044 | 3.7504 | TB408 | 18/3 | Derrick
2025-07-22 | 2025-07-19 | 2025-07-22 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/3 | Derrick
2025-07-23 | 2025-07-16 | 2025-07-23 | Arawali 2 | 37.5044 | 4.688 | TB408 | 2/9 | Derrick
2025-07-23 | 2025-07-23 | 2025-07-30 | Arawali 2 | 38.8476 | 4.856 | TB408 | 2/7 | Derrick
2025-07-23 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-07-23 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5 | Derrick
2025-07-23 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-23 | 2025-07-21 | 2025-07-31 | Dharmendra Munnilal Pusplata | 38.8476 | 3.5316 | TB408 | 27/2 | Derrick
2025-07-23 | 2025-07-21 | 2025-07-24 | Hazarilal Yadav Poonam Kumari | 38.8476 | 9.7119 | TB408 | 26/2 | Derrick
2025-07-23 | 2025-07-14 | 2025-07-23 | Priyanka Devi 2 | 37.5044 | 3.7504 | TB408 | 18/3 | Derrick
2025-07-23 | 2025-07-23 | 2025-07-26 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/2 | Derrick
2025-07-23 | 2025-07-23 | 2025-07-28 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/4 | Derrick
2025-07-24 | 2025-07-23 | 2025-07-30 | Arawali 2 | 38.8476 | 4.856 | TB408 | 2/7 | Derrick
2025-07-24 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-07-24 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5 | Derrick
2025-07-24 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-24 | 2025-07-21 | 2025-07-31 | Dharmendra Munnilal Pusplata | 38.8476 | 3.5316 | TB408 | 27/2 | Derrick
2025-07-24 | 2025-07-21 | 2025-07-24 | Hazarilal Yadav Poonam Kumari | 38.8476 | 9.7119 | TB408 | 26/2 | Derrick
2025-07-24 | 2025-07-23 | 2025-07-26 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/2 | Derrick
2025-07-24 | 2025-07-23 | 2025-07-28 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/4 | Derrick
2025-07-25 | 2025-07-25 | 2025-08-02 | Arawali 1 | 86.1293 | 9.5699 | TB408 | 12/0 | Derrick
2025-07-25 | 2025-07-23 | 2025-07-30 | Arawali 2 | 38.8476 | 4.856 | TB408 | 2/7 | Derrick
2025-07-25 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1 | Derrick
2025-07-25 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-07-25 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5 | Derrick
2025-07-25 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-25 | 2025-07-21 | 2025-07-31 | Dharmendra Munnilal Pusplata | 38.8476 | 3.5316 | TB408 | 27/2 | Derrick
2025-07-25 | 2025-07-25 | 2025-07-28 | Hazarilal Yadav Poonam Kumari | 37.5044 | 9.3761 | TB408 | 26/3 | Derrick
2025-07-25 | 2025-07-23 | 2025-07-26 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/2 | Derrick
2025-07-25 | 2025-07-23 | 2025-07-28 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/4 | Derrick
2025-07-26 | 2025-07-25 | 2025-08-02 | Arawali 1 | 86.1293 | 9.5699 | TB408 | 12/0 | Derrick
2025-07-26 | 2025-07-23 | 2025-07-30 | Arawali 2 | 38.8476 | 4.856 | TB408 | 2/7 | Derrick
2025-07-26 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1 | Derrick
2025-07-26 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-07-26 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5 | Derrick
2025-07-26 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-26 | 2025-07-21 | 2025-07-31 | Dharmendra Munnilal Pusplata | 38.8476 | 3.5316 | TB408 | 27/2 | Derrick
2025-07-26 | 2025-07-25 | 2025-07-28 | Hazarilal Yadav Poonam Kumari | 37.5044 | 9.3761 | TB408 | 26/3 | Derrick
2025-07-26 | 2025-07-23 | 2025-07-26 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/2 | Derrick
2025-07-26 | 2025-07-23 | 2025-07-28 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/4 | Derrick
2025-07-26 | 2025-07-26 | 2025-07-29 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/1 | Derrick
2025-07-26 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TB408 | 47/7 | Derrick
2025-07-27 | 2025-07-25 | 2025-08-02 | Arawali 1 | 86.1293 | 9.5699 | TB408 | 12/0 | Derrick
2025-07-27 | 2025-07-23 | 2025-07-30 | Arawali 2 | 38.8476 | 4.856 | TB408 | 2/7 | Derrick
2025-07-27 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1 | Derrick
2025-07-27 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-07-27 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-27 | 2025-07-21 | 2025-07-31 | Dharmendra Munnilal Pusplata | 38.8476 | 3.5316 | TB408 | 27/2 | Derrick
2025-07-27 | 2025-07-25 | 2025-07-28 | Hazarilal Yadav Poonam Kumari | 37.5044 | 9.3761 | TB408 | 26/3 | Derrick
2025-07-27 | 2025-07-27 | 2025-07-31 | Pusplata Kailash | 38.8476 | 7.7695 | TB408 | 27/3 | Derrick
2025-07-27 | 2025-07-27 | 2025-07-31 | Pusplata Praful | 37.5044 | 7.5009 | TB408 | 25/4 | Derrick
2025-07-27 | 2025-07-23 | 2025-07-28 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/4 | Derrick
2025-07-27 | 2025-07-26 | 2025-07-29 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/1 | Derrick
2025-07-27 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TB408 | 47/7 | Derrick
2025-07-28 | 2025-07-25 | 2025-08-02 | Arawali 1 | 86.1293 | 9.5699 | TB408 | 12/0 | Derrick
2025-07-28 | 2025-07-23 | 2025-07-30 | Arawali 2 | 38.8476 | 4.856 | TB408 | 2/7 | Derrick
2025-07-28 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1 | Derrick
2025-07-28 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-07-28 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-28 | 2025-07-21 | 2025-07-31 | Dharmendra Munnilal Pusplata | 38.8476 | 3.5316 | TB408 | 27/2 | Derrick
2025-07-28 | 2025-07-25 | 2025-07-28 | Hazarilal Yadav Poonam Kumari | 37.5044 | 9.3761 | TB408 | 26/3 | Derrick
2025-07-28 | 2025-07-27 | 2025-07-31 | Pusplata Kailash | 38.8476 | 7.7695 | TB408 | 27/3 | Derrick
2025-07-28 | 2025-07-27 | 2025-07-31 | Pusplata Praful | 37.5044 | 7.5009 | TB408 | 25/4 | Derrick
2025-07-28 | 2025-07-23 | 2025-07-28 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/4 | Derrick
2025-07-28 | 2025-07-26 | 2025-07-29 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/1 | Derrick
2025-07-28 | 2025-07-28 | 2025-08-03 | Satyam Enterprises | 47.1844 | 6.7406 | TB408 | 44/7 | Derrick
2025-07-28 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TB408 | 44/10 | Derrick
2025-07-28 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TB408 | 47/7 | Derrick
2025-07-29 | 2025-07-25 | 2025-08-02 | Arawali 1 | 86.1293 | 9.5699 | TB408 | 12/0 | Derrick
2025-07-29 | 2025-07-23 | 2025-07-30 | Arawali 2 | 38.8476 | 4.856 | TB408 | 2/7 | Derrick
2025-07-29 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1 | Derrick
2025-07-29 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-07-29 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-29 | 2025-07-21 | 2025-07-31 | Dharmendra Munnilal Pusplata | 38.8476 | 3.5316 | TB408 | 27/2 | Derrick
2025-07-29 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0 | Derrick
2025-07-29 | 2025-07-27 | 2025-07-31 | Pusplata Kailash | 38.8476 | 7.7695 | TB408 | 27/3 | Derrick
2025-07-29 | 2025-07-27 | 2025-07-31 | Pusplata Praful | 37.5044 | 7.5009 | TB408 | 25/4 | Derrick
2025-07-29 | 2025-07-26 | 2025-07-29 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/1 | Derrick
2025-07-29 | 2025-07-28 | 2025-08-03 | Satyam Enterprises | 47.1844 | 6.7406 | TB408 | 44/7 | Derrick
2025-07-29 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TB408 | 44/10 | Derrick
2025-07-29 | 2025-07-29 | 2025-08-03 | Satyam Enterprises | 60.0968 | 10.0161 | TB408 | 44/0 | Derrick
2025-07-29 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TB408 | 47/7 | Derrick
2025-07-30 | 2025-07-25 | 2025-08-02 | Arawali 1 | 86.1293 | 9.5699 | TB408 | 12/0 | Derrick
2025-07-30 | 2025-07-23 | 2025-07-30 | Arawali 2 | 38.8476 | 4.856 | TB408 | 2/7 | Derrick
2025-07-30 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1 | Derrick
2025-07-30 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2 | Derrick
2025-07-30 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-07-30 | 2025-07-21 | 2025-07-31 | Dharmendra Munnilal Pusplata | 38.8476 | 3.5316 | TB408 | 27/2 | Derrick
2025-07-30 | 2025-07-30 | 2025-08-04 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 29/1 | Derrick
2025-07-30 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0 | Derrick
2025-07-30 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0 | Derrick
2025-07-30 | 2025-07-27 | 2025-07-31 | Pusplata Kailash | 38.8476 | 7.7695 | TB408 | 27/3 | Derrick
2025-07-30 | 2025-07-27 | 2025-07-31 | Pusplata Praful | 37.5044 | 7.5009 | TB408 | 25/4 | Derrick
2025-07-30 | 2025-07-28 | 2025-08-03 | Satyam Enterprises | 47.1844 | 6.7406 | TB408 | 44/7 | Derrick
2025-07-30 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TB408 | 44/10 | Derrick
2025-07-30 | 2025-07-29 | 2025-08-03 | Satyam Enterprises | 60.0968 | 10.0161 | TB408 | 44/0 | Derrick
2025-07-30 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TB408 | 47/7 | Derrick
2025-07-31 | 2025-07-25 | 2025-08-02 | Arawali 1 | 86.1293 | 9.5699 | TB408 | 12/0 | Derrick
2025-07-31 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1 | Derrick
2025-07-31 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2 | Derrick
2025-07-31 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-07-31 | 2025-07-21 | 2025-07-31 | Dharmendra Munnilal Pusplata | 38.8476 | 3.5316 | TB408 | 27/2 | Derrick
2025-07-31 | 2025-07-30 | 2025-08-04 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 29/1 | Derrick
2025-07-31 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0 | Derrick
2025-07-31 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0 | Derrick
2025-07-31 | 2025-07-27 | 2025-07-31 | Pusplata Kailash | 38.8476 | 7.7695 | TB408 | 27/3 | Derrick
2025-07-31 | 2025-07-27 | 2025-07-31 | Pusplata Praful | 37.5044 | 7.5009 | TB408 | 25/4 | Derrick
2025-07-31 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TB408 | 25/3 | Derrick
2025-07-31 | 2025-07-28 | 2025-08-03 | Satyam Enterprises | 47.1844 | 6.7406 | TB408 | 44/7 | Derrick
2025-07-31 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TB408 | 44/10 | Derrick
2025-07-31 | 2025-07-29 | 2025-08-03 | Satyam Enterprises | 60.0968 | 10.0161 | TB408 | 44/0 | Derrick
2025-07-31 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TB408 | 47/7 | Derrick
2025-08-01 | 2025-07-25 | 2025-08-02 | Arawali 1 | 86.1293 | 9.5699 | TB408 | 12/0 | Derrick
2025-08-01 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1 | Derrick
2025-08-01 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2 | Derrick
2025-08-01 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-08-01 | 2025-07-30 | 2025-08-04 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 29/1 | Derrick
2025-08-01 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0 | Derrick
2025-08-01 | 2025-08-01 | 2025-08-05 | Priyanka Devi | 37.5044 | 7.5009 | TB408 | 19/5 | Derrick
2025-08-01 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0 | Derrick
2025-08-01 | 2025-08-01 | 2025-08-06 | Pusplata Kailash | 38.8476 | 6.4746 | TB408 | 30/3 | Derrick
2025-08-01 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TB408 | 25/3 | Derrick
2025-08-01 | 2025-07-28 | 2025-08-03 | Satyam Enterprises | 47.1844 | 6.7406 | TB408 | 44/7 | Derrick
2025-08-01 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TB408 | 44/10 | Derrick
2025-08-01 | 2025-07-29 | 2025-08-03 | Satyam Enterprises | 60.0968 | 10.0161 | TB408 | 44/0 | Derrick
2025-08-01 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TB408 | 47/7 | Derrick
2025-08-02 | 2025-07-25 | 2025-08-02 | Arawali 1 | 86.1293 | 9.5699 | TB408 | 12/0 | Derrick
2025-08-02 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1 | Derrick
2025-08-02 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2 | Derrick
2025-08-02 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-08-02 | 2025-07-30 | 2025-08-04 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 29/1 | Derrick
2025-08-02 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0 | Derrick
2025-08-02 | 2025-08-01 | 2025-08-05 | Priyanka Devi | 37.5044 | 7.5009 | TB408 | 19/5 | Derrick
2025-08-02 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0 | Derrick
2025-08-02 | 2025-08-01 | 2025-08-06 | Pusplata Kailash | 38.8476 | 6.4746 | TB408 | 30/3 | Derrick
2025-08-02 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TB408 | 25/3 | Derrick
2025-08-02 | 2025-07-28 | 2025-08-03 | Satyam Enterprises | 47.1844 | 6.7406 | TB408 | 44/7 | Derrick
2025-08-02 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TB408 | 44/10 | Derrick
2025-08-02 | 2025-07-29 | 2025-08-03 | Satyam Enterprises | 60.0968 | 10.0161 | TB408 | 44/0 | Derrick
2025-08-02 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TB408 | 47/7 | Derrick
2025-08-03 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1 | Derrick
2025-08-03 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2 | Derrick
2025-08-03 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-08-03 | 2025-07-30 | 2025-08-04 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 29/1 | Derrick
2025-08-03 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0 | Derrick
2025-08-03 | 2025-08-01 | 2025-08-05 | Priyanka Devi | 37.5044 | 7.5009 | TB408 | 19/5 | Derrick
2025-08-03 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0 | Derrick
2025-08-03 | 2025-08-01 | 2025-08-06 | Pusplata Kailash | 38.8476 | 6.4746 | TB408 | 30/3 | Derrick
2025-08-03 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TB408 | 25/3 | Derrick
2025-08-03 | 2025-07-28 | 2025-08-03 | Satyam Enterprises | 47.1844 | 6.7406 | TB408 | 44/7 | Derrick
2025-08-03 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TB408 | 44/10 | Derrick
2025-08-03 | 2025-07-29 | 2025-08-03 | Satyam Enterprises | 60.0968 | 10.0161 | TB408 | 44/0 | Derrick
2025-08-03 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TB408 | 47/7 | Derrick
2025-08-04 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1 | Derrick
2025-08-04 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2 | Derrick
2025-08-04 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-08-04 | 2025-07-30 | 2025-08-04 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 29/1 | Derrick
2025-08-04 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0 | Derrick
2025-08-04 | 2025-08-04 | 2025-08-09 | Jwala Singh | 37.5044 | 6.2507 | TB408 | 8/12 | Derrick
2025-08-04 | 2025-08-01 | 2025-08-05 | Priyanka Devi | 37.5044 | 7.5009 | TB408 | 19/5 | Derrick
2025-08-04 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0 | Derrick
2025-08-04 | 2025-08-01 | 2025-08-06 | Pusplata Kailash | 38.8476 | 6.4746 | TB408 | 30/3 | Derrick
2025-08-04 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TB408 | 25/3 | Derrick
2025-08-04 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TB408 | 44/10 | Derrick
2025-08-04 | 2025-08-04 | 2025-08-09 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/5 | Derrick
2025-08-04 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3 | Derrick
2025-08-04 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5 | Derrick
2025-08-04 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TB408 | 47/7 | Derrick
2025-08-04 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2 | Derrick
2025-08-05 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1 | Derrick
2025-08-05 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2 | Derrick
2025-08-05 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-08-05 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0 | Derrick
2025-08-05 | 2025-08-04 | 2025-08-09 | Jwala Singh | 37.5044 | 6.2507 | TB408 | 8/12 | Derrick
2025-08-05 | 2025-08-01 | 2025-08-05 | Priyanka Devi | 37.5044 | 7.5009 | TB408 | 19/5 | Derrick
2025-08-05 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0 | Derrick
2025-08-05 | 2025-08-01 | 2025-08-06 | Pusplata Kailash | 38.8476 | 6.4746 | TB408 | 30/3 | Derrick
2025-08-05 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TB408 | 25/3 | Derrick
2025-08-05 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TB408 | 44/10 | Derrick
2025-08-05 | 2025-08-04 | 2025-08-09 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/5 | Derrick
2025-08-05 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3 | Derrick
2025-08-05 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5 | Derrick
2025-08-05 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TB408 | 47/7 | Derrick
2025-08-05 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2 | Derrick
2025-08-06 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1 | Derrick
2025-08-06 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2 | Derrick
2025-08-06 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-08-06 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0 | Derrick
2025-08-06 | 2025-08-04 | 2025-08-09 | Jwala Singh | 37.5044 | 6.2507 | TB408 | 8/12 | Derrick
2025-08-06 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0 | Derrick
2025-08-06 | 2025-08-01 | 2025-08-06 | Pusplata Kailash | 38.8476 | 6.4746 | TB408 | 30/3 | Derrick
2025-08-06 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TB408 | 30/5 | Derrick
2025-08-06 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TB408 | 25/3 | Derrick
2025-08-06 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TB408 | 44/10 | Derrick
2025-08-06 | 2025-08-04 | 2025-08-09 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/5 | Derrick
2025-08-06 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3 | Derrick
2025-08-06 | 2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TB408 | 45/0 | Derrick
2025-08-06 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5 | Derrick
2025-08-06 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2 | Derrick
2025-08-06 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4 | Derrick
2025-08-07 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1 | Derrick
2025-08-07 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2 | Derrick
2025-08-07 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-08-07 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0 | Derrick
2025-08-07 | 2025-08-04 | 2025-08-09 | Jwala Singh | 37.5044 | 6.2507 | TB408 | 8/12 | Derrick
2025-08-07 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0 | Derrick
2025-08-07 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TB408 | 30/5 | Derrick
2025-08-07 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TB408 | 25/3 | Derrick
2025-08-07 | 2025-08-04 | 2025-08-09 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/5 | Derrick
2025-08-07 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3 | Derrick
2025-08-07 | 2025-08-07 | 2025-08-13 | Shobha Devi | 45.413 | 6.4876 | TB408 | 55/8 | Derrick
2025-08-07 | 2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TB408 | 45/0 | Derrick
2025-08-07 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5 | Derrick
2025-08-07 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2 | Derrick
2025-08-07 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4 | Derrick
2025-08-08 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1 | Derrick
2025-08-08 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2 | Derrick
2025-08-08 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-08-08 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0 | Derrick
2025-08-08 | 2025-08-04 | 2025-08-09 | Jwala Singh | 37.5044 | 6.2507 | TB408 | 8/12 | Derrick
2025-08-08 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0 | Derrick
2025-08-08 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TB408 | 30/5 | Derrick
2025-08-08 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TB408 | 25/3 | Derrick
2025-08-08 | 2025-08-04 | 2025-08-09 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/5 | Derrick
2025-08-08 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3 | Derrick
2025-08-08 | 2025-08-07 | 2025-08-13 | Shobha Devi | 45.413 | 6.4876 | TB408 | 55/8 | Derrick
2025-08-08 | 2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TB408 | 45/0 | Derrick
2025-08-08 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5 | Derrick
2025-08-08 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2 | Derrick
2025-08-08 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4 | Derrick
2025-08-09 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1 | Derrick
2025-08-09 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2 | Derrick
2025-08-09 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-08-09 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0 | Derrick
2025-08-09 | 2025-08-04 | 2025-08-09 | Jwala Singh | 37.5044 | 6.2507 | TB408 | 8/12 | Derrick
2025-08-09 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0 | Derrick
2025-08-09 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TB408 | 30/5 | Derrick
2025-08-09 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TB408 | 25/3 | Derrick
2025-08-09 | 2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TB408 | 27/4 | Derrick
2025-08-09 | 2025-08-04 | 2025-08-09 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/5 | Derrick
2025-08-09 | 2025-08-09 | 2025-08-16 | Satyam Enterprises | 60.0968 | 7.5121 | TB408 | 44/6 | Derrick
2025-08-09 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3 | Derrick
2025-08-09 | 2025-08-07 | 2025-08-13 | Shobha Devi | 45.413 | 6.4876 | TB408 | 55/8 | Derrick
2025-08-09 | 2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TB408 | 45/0 | Derrick
2025-08-09 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5 | Derrick
2025-08-09 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2 | Derrick
2025-08-09 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4 | Derrick
2025-08-10 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2 | Derrick
2025-08-10 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-08-10 | 2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TB408 | 41/1 | Derrick
2025-08-10 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0 | Derrick
2025-08-10 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0 | Derrick
2025-08-10 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TB408 | 30/5 | Derrick
2025-08-10 | 2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TB408 | 27/4 | Derrick
2025-08-10 | 2025-08-10 | 2025-08-17 | Rahul Kumar | 38.8476 | 4.856 | TB408 | 40/3 | Derrick
2025-08-10 | 2025-08-09 | 2025-08-16 | Satyam Enterprises | 60.0968 | 7.5121 | TB408 | 44/6 | Derrick
2025-08-10 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3 | Derrick
2025-08-10 | 2025-08-07 | 2025-08-13 | Shobha Devi | 45.413 | 6.4876 | TB408 | 55/8 | Derrick
2025-08-10 | 2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TB408 | 45/0 | Derrick
2025-08-10 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5 | Derrick
2025-08-10 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2 | Derrick
2025-08-10 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4 | Derrick
2025-08-11 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2 | Derrick
2025-08-11 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-08-11 | 2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TB408 | 41/1 | Derrick
2025-08-11 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0 | Derrick
2025-08-11 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0 | Derrick
2025-08-11 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TB408 | 30/5 | Derrick
2025-08-11 | 2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TB408 | 27/4 | Derrick
2025-08-11 | 2025-08-10 | 2025-08-17 | Rahul Kumar | 38.8476 | 4.856 | TB408 | 40/3 | Derrick
2025-08-11 | 2025-08-09 | 2025-08-16 | Satyam Enterprises | 60.0968 | 7.5121 | TB408 | 44/6 | Derrick
2025-08-11 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3 | Derrick
2025-08-11 | 2025-08-07 | 2025-08-13 | Shobha Devi | 45.413 | 6.4876 | TB408 | 55/8 | Derrick
2025-08-11 | 2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TB408 | 45/0 | Derrick
2025-08-11 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5 | Derrick
2025-08-11 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2 | Derrick
2025-08-11 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4 | Derrick
2025-08-12 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2 | Derrick
2025-08-12 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-08-12 | 2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TB408 | 41/1 | Derrick
2025-08-12 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0 | Derrick
2025-08-12 | 2025-08-12 | 2025-08-19 | Jwala Singh | 47.1844 | 5.898 | TB408 | 28/5 | Derrick
2025-08-12 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0 | Derrick
2025-08-12 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TB408 | 30/5 | Derrick
2025-08-12 | 2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TB408 | 27/4 | Derrick
2025-08-12 | 2025-08-10 | 2025-08-17 | Rahul Kumar | 38.8476 | 4.856 | TB408 | 40/3 | Derrick
2025-08-12 | 2025-08-09 | 2025-08-16 | Satyam Enterprises | 60.0968 | 7.5121 | TB408 | 44/6 | Derrick
2025-08-12 | 2025-08-12 | 2025-08-18 | Satyam Manish | 38.8476 | 5.5497 | TB408 | 43/11 | Derrick
2025-08-12 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3 | Derrick
2025-08-12 | 2025-08-07 | 2025-08-13 | Shobha Devi | 45.413 | 6.4876 | TB408 | 55/8 | Derrick
2025-08-12 | 2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TB408 | 45/0 | Derrick
2025-08-12 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5 | Derrick
2025-08-12 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2 | Derrick
2025-08-12 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4 | Derrick
2025-08-13 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2 | Derrick
2025-08-13 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-08-13 | 2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TB408 | 41/1 | Derrick
2025-08-13 | 2025-08-12 | 2025-08-19 | Jwala Singh | 47.1844 | 5.898 | TB408 | 28/5 | Derrick
2025-08-13 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0 | Derrick
2025-08-13 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TB408 | 30/5 | Derrick
2025-08-13 | 2025-08-13 | 2025-08-18 | Pusplata Pankaj | 38.8476 | 6.4746 | TB408 | 17/4 | Derrick
2025-08-13 | 2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TB408 | 27/4 | Derrick
2025-08-13 | 2025-08-10 | 2025-08-17 | Rahul Kumar | 38.8476 | 4.856 | TB408 | 40/3 | Derrick
2025-08-13 | 2025-08-09 | 2025-08-16 | Satyam Enterprises | 60.0968 | 7.5121 | TB408 | 44/6 | Derrick
2025-08-13 | 2025-08-12 | 2025-08-18 | Satyam Manish | 38.8476 | 5.5497 | TB408 | 43/11 | Derrick
2025-08-13 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3 | Derrick
2025-08-13 | 2025-08-07 | 2025-08-13 | Shobha Devi | 45.413 | 6.4876 | TB408 | 55/8 | Derrick
2025-08-13 | 2025-08-13 | 2025-08-17 | Shobha Devi | 37.5044 | 7.5009 | TB408 | 55/7 | Derrick
2025-08-13 | 2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TB408 | 45/0 | Derrick
2025-08-13 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5 | Derrick
2025-08-13 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2 | Derrick
2025-08-13 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4 | Derrick
2025-08-14 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2 | Derrick
2025-08-14 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-08-14 | 2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TB408 | 41/1 | Derrick
2025-08-14 | 2025-08-12 | 2025-08-19 | Jwala Singh | 47.1844 | 5.898 | TB408 | 28/5 | Derrick
2025-08-14 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TB408 | 30/5 | Derrick
2025-08-14 | 2025-08-13 | 2025-08-18 | Pusplata Pankaj | 38.8476 | 6.4746 | TB408 | 17/4 | Derrick
2025-08-14 | 2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TB408 | 27/4 | Derrick
2025-08-14 | 2025-08-10 | 2025-08-17 | Rahul Kumar | 38.8476 | 4.856 | TB408 | 40/3 | Derrick
2025-08-14 | 2025-08-09 | 2025-08-16 | Satyam Enterprises | 60.0968 | 7.5121 | TB408 | 44/6 | Derrick
2025-08-14 | 2025-08-12 | 2025-08-18 | Satyam Manish | 38.8476 | 5.5497 | TB408 | 43/11 | Derrick
2025-08-14 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3 | Derrick
2025-08-14 | 2025-08-13 | 2025-08-17 | Shobha Devi | 37.5044 | 7.5009 | TB408 | 55/7 | Derrick
2025-08-14 | 2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TB408 | 45/0 | Derrick
2025-08-14 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5 | Derrick
2025-08-14 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2 | Derrick
2025-08-14 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4 | Derrick
2025-08-15 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2 | Derrick
2025-08-15 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-08-15 | 2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TB408 | 41/1 | Derrick
2025-08-15 | 2025-08-12 | 2025-08-19 | Jwala Singh | 47.1844 | 5.898 | TB408 | 28/5 | Derrick
2025-08-15 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TB408 | 30/5 | Derrick
2025-08-15 | 2025-08-13 | 2025-08-18 | Pusplata Pankaj | 38.8476 | 6.4746 | TB408 | 17/4 | Derrick
2025-08-15 | 2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TB408 | 27/4 | Derrick
2025-08-15 | 2025-08-10 | 2025-08-17 | Rahul Kumar | 38.8476 | 4.856 | TB408 | 40/3 | Derrick
2025-08-15 | 2025-08-09 | 2025-08-16 | Satyam Enterprises | 60.0968 | 7.5121 | TB408 | 44/6 | Derrick
2025-08-15 | 2025-08-12 | 2025-08-18 | Satyam Manish | 38.8476 | 5.5497 | TB408 | 43/11 | Derrick
2025-08-15 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3 | Derrick
2025-08-15 | 2025-08-13 | 2025-08-17 | Shobha Devi | 37.5044 | 7.5009 | TB408 | 55/7 | Derrick
2025-08-15 | 2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TB408 | 45/0 | Derrick
2025-08-15 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5 | Derrick
2025-08-15 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2 | Derrick
2025-08-15 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4 | Derrick
2025-08-16 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2 | Derrick
2025-08-16 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-08-16 | 2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TB408 | 41/1 | Derrick
2025-08-16 | 2025-08-12 | 2025-08-19 | Jwala Singh | 47.1844 | 5.898 | TB408 | 28/5 | Derrick
2025-08-16 | 2025-08-16 | 2025-08-23 | Pusplata Dharamveer | 38.8476 | 4.856 | TB408 | 27/1 | Derrick
2025-08-16 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TB408 | 30/5 | Derrick
2025-08-16 | 2025-08-13 | 2025-08-18 | Pusplata Pankaj | 38.8476 | 6.4746 | TB408 | 17/4 | Derrick
2025-08-16 | 2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TB408 | 27/4 | Derrick
2025-08-16 | 2025-08-10 | 2025-08-17 | Rahul Kumar | 38.8476 | 4.856 | TB408 | 40/3 | Derrick
2025-08-16 | 2025-08-09 | 2025-08-16 | Satyam Enterprises | 60.0968 | 7.5121 | TB408 | 44/6 | Derrick
2025-08-16 | 2025-08-12 | 2025-08-18 | Satyam Manish | 38.8476 | 5.5497 | TB408 | 43/11 | Derrick
2025-08-16 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3 | Derrick
2025-08-16 | 2025-08-13 | 2025-08-17 | Shobha Devi | 37.5044 | 7.5009 | TB408 | 55/7 | Derrick
2025-08-16 | 2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TB408 | 45/0 | Derrick
2025-08-16 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5 | Derrick
2025-08-16 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2 | Derrick
2025-08-16 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4 | Derrick
2025-08-17 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2 | Derrick
2025-08-17 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-08-17 | 2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TB408 | 41/1 | Derrick
2025-08-17 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3 | Derrick
2025-08-17 | 2025-08-12 | 2025-08-19 | Jwala Singh | 47.1844 | 5.898 | TB408 | 28/5 | Derrick
2025-08-17 | 2025-08-16 | 2025-08-23 | Pusplata Dharamveer | 38.8476 | 4.856 | TB408 | 27/1 | Derrick
2025-08-17 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TB408 | 30/5 | Derrick
2025-08-17 | 2025-08-17 | 2025-08-21 | Pusplata Kailash | 37.5044 | 7.5009 | TB408 | 30/6 | Derrick
2025-08-17 | 2025-08-13 | 2025-08-18 | Pusplata Pankaj | 38.8476 | 6.4746 | TB408 | 17/4 | Derrick
2025-08-17 | 2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TB408 | 27/4 | Derrick
2025-08-17 | 2025-08-10 | 2025-08-17 | Rahul Kumar | 38.8476 | 4.856 | TB408 | 40/3 | Derrick
2025-08-17 | 2025-08-17 | 2025-08-24 | Satyam Enterprises | 47.1844 | 5.898 | TB408 | 44/9 | Derrick
2025-08-17 | 2025-08-12 | 2025-08-18 | Satyam Manish | 38.8476 | 5.5497 | TB408 | 43/11 | Derrick
2025-08-17 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3 | Derrick
2025-08-17 | 2025-08-13 | 2025-08-17 | Shobha Devi | 37.5044 | 7.5009 | TB408 | 55/7 | Derrick
2025-08-17 | 2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TB408 | 45/0 | Derrick
2025-08-17 | 2025-08-17 | 2025-08-24 | Sunny Construction | 37.5044 | 4.688 | TB408 | 55/1 | Derrick
2025-08-17 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5 | Derrick
2025-08-17 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5 | Derrick
2025-08-17 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4 | Derrick
2025-08-17 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3 | Derrick
2025-08-18 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2 | Derrick
2025-08-18 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-08-18 | 2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TB408 | 41/1 | Derrick
2025-08-18 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3 | Derrick
2025-08-18 | 2025-08-12 | 2025-08-19 | Jwala Singh | 47.1844 | 5.898 | TB408 | 28/5 | Derrick
2025-08-18 | 2025-08-18 | 2025-08-25 | Pusplata | 66.3811 | 8.2976 | TB408 | 18/0 | Derrick
2025-08-18 | 2025-08-16 | 2025-08-23 | Pusplata Dharamveer | 38.8476 | 4.856 | TB408 | 27/1 | Derrick
2025-08-18 | 2025-08-17 | 2025-08-21 | Pusplata Kailash | 37.5044 | 7.5009 | TB408 | 30/6 | Derrick
2025-08-18 | 2025-08-13 | 2025-08-18 | Pusplata Pankaj | 38.8476 | 6.4746 | TB408 | 17/4 | Derrick
2025-08-18 | 2025-08-18 | 2025-08-24 | Rahul Kumar | 38.8476 | 5.5497 | TB408 | 40/2 | Derrick
2025-08-18 | 2025-08-17 | 2025-08-24 | Satyam Enterprises | 47.1844 | 5.898 | TB408 | 44/9 | Derrick
2025-08-18 | 2025-08-12 | 2025-08-18 | Satyam Manish | 38.8476 | 5.5497 | TB408 | 43/11 | Derrick
2025-08-18 | 2025-08-17 | 2025-08-24 | Sunny Construction | 37.5044 | 4.688 | TB408 | 55/1 | Derrick
2025-08-18 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5 | Derrick
2025-08-18 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5 | Derrick
2025-08-18 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4 | Derrick
2025-08-18 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3 | Derrick
2025-08-19 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2 | Derrick
2025-08-19 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-08-19 | 2025-08-19 | 2025-08-25 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 44/11 | Derrick
2025-08-19 | 2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TB408 | 41/1 | Derrick
2025-08-19 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3 | Derrick
2025-08-19 | 2025-08-12 | 2025-08-19 | Jwala Singh | 47.1844 | 5.898 | TB408 | 28/5 | Derrick
2025-08-19 | 2025-08-19 | 2025-08-25 | Jwala Singh | 37.5044 | 5.3578 | TB408 | 28/2 | Derrick
2025-08-19 | 2025-08-18 | 2025-08-25 | Pusplata | 66.3811 | 8.2976 | TB408 | 18/0 | Derrick
2025-08-19 | 2025-08-16 | 2025-08-23 | Pusplata Dharamveer | 38.8476 | 4.856 | TB408 | 27/1 | Derrick
2025-08-19 | 2025-08-17 | 2025-08-21 | Pusplata Kailash | 37.5044 | 7.5009 | TB408 | 30/6 | Derrick
2025-08-19 | 2025-08-18 | 2025-08-24 | Rahul Kumar | 38.8476 | 5.5497 | TB408 | 40/2 | Derrick
2025-08-19 | 2025-08-17 | 2025-08-24 | Satyam Enterprises | 47.1844 | 5.898 | TB408 | 44/9 | Derrick
2025-08-19 | 2025-08-17 | 2025-08-24 | Sunny Construction | 37.5044 | 4.688 | TB408 | 55/1 | Derrick
2025-08-19 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5 | Derrick
2025-08-19 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5 | Derrick
2025-08-19 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4 | Derrick
2025-08-19 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3 | Derrick
2025-08-20 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2 | Derrick
2025-08-20 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-08-20 | 2025-08-19 | 2025-08-25 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 44/11 | Derrick
2025-08-20 | 2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TB408 | 41/1 | Derrick
2025-08-20 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3 | Derrick
2025-08-20 | 2025-08-19 | 2025-08-25 | Jwala Singh | 37.5044 | 5.3578 | TB408 | 28/2 | Derrick
2025-08-20 | 2025-08-18 | 2025-08-25 | Pusplata | 66.3811 | 8.2976 | TB408 | 18/0 | Derrick
2025-08-20 | 2025-08-20 | 2025-08-25 | Pusplata Ashok | 37.5044 | 6.2507 | TB408 | 4/4 | Derrick
2025-08-20 | 2025-08-16 | 2025-08-23 | Pusplata Dharamveer | 38.8476 | 4.856 | TB408 | 27/1 | Derrick
2025-08-20 | 2025-08-17 | 2025-08-21 | Pusplata Kailash | 37.5044 | 7.5009 | TB408 | 30/6 | Derrick
2025-08-20 | 2025-08-18 | 2025-08-24 | Rahul Kumar | 38.8476 | 5.5497 | TB408 | 40/2 | Derrick
2025-08-20 | 2025-08-17 | 2025-08-24 | Satyam Enterprises | 47.1844 | 5.898 | TB408 | 44/9 | Derrick
2025-08-20 | 2025-08-17 | 2025-08-24 | Sunny Construction | 37.5044 | 4.688 | TB408 | 55/1 | Derrick
2025-08-20 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5 | Derrick
2025-08-20 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4 | Derrick
2025-08-20 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3 | Derrick
2025-08-21 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2 | Derrick
2025-08-21 | 2025-08-19 | 2025-08-25 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 44/11 | Derrick
2025-08-21 | 2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TB408 | 41/1 | Derrick
2025-08-21 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3 | Derrick
2025-08-21 | 2025-08-19 | 2025-08-25 | Jwala Singh | 37.5044 | 5.3578 | TB408 | 28/2 | Derrick
2025-08-21 | 2025-08-18 | 2025-08-25 | Pusplata | 66.3811 | 8.2976 | TB408 | 18/0 | Derrick
2025-08-21 | 2025-08-20 | 2025-08-25 | Pusplata Ashok | 37.5044 | 6.2507 | TB408 | 4/4 | Derrick
2025-08-21 | 2025-08-16 | 2025-08-23 | Pusplata Dharamveer | 38.8476 | 4.856 | TB408 | 27/1 | Derrick
2025-08-21 | 2025-08-17 | 2025-08-21 | Pusplata Kailash | 37.5044 | 7.5009 | TB408 | 30/6 | Derrick
2025-08-21 | 2025-08-18 | 2025-08-24 | Rahul Kumar | 38.8476 | 5.5497 | TB408 | 40/2 | Derrick
2025-08-21 | 2025-08-17 | 2025-08-24 | Satyam Enterprises | 47.1844 | 5.898 | TB408 | 44/9 | Derrick
2025-08-21 | 2025-08-21 | 2025-08-25 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 57/2 | Derrick
2025-08-21 | 2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TB408 | 57/1 | Derrick
2025-08-21 | 2025-08-17 | 2025-08-24 | Sunny Construction | 37.5044 | 4.688 | TB408 | 55/1 | Derrick
2025-08-21 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5 | Derrick
2025-08-21 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4 | Derrick
2025-08-21 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3 | Derrick
2025-08-22 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2 | Derrick
2025-08-22 | 2025-08-19 | 2025-08-25 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 44/11 | Derrick
2025-08-22 | 2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 36/2 | Derrick
2025-08-22 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3 | Derrick
2025-08-22 | 2025-08-19 | 2025-08-25 | Jwala Singh | 37.5044 | 5.3578 | TB408 | 28/2 | Derrick
2025-08-22 | 2025-08-18 | 2025-08-25 | Pusplata | 66.3811 | 8.2976 | TB408 | 18/0 | Derrick
2025-08-22 | 2025-08-20 | 2025-08-25 | Pusplata Ashok | 37.5044 | 6.2507 | TB408 | 4/4 | Derrick
2025-08-22 | 2025-08-16 | 2025-08-23 | Pusplata Dharamveer | 38.8476 | 4.856 | TB408 | 27/1 | Derrick
2025-08-22 | 2025-08-22 | 2025-08-26 | Pusplata Kailash | 37.5044 | 7.5009 | TB408 | 31/1 | Derrick
2025-08-22 | 2025-08-18 | 2025-08-24 | Rahul Kumar | 38.8476 | 5.5497 | TB408 | 40/2 | Derrick
2025-08-22 | 2025-08-17 | 2025-08-24 | Satyam Enterprises | 47.1844 | 5.898 | TB408 | 44/9 | Derrick
2025-08-22 | 2025-08-21 | 2025-08-25 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 57/2 | Derrick
2025-08-22 | 2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TB408 | 57/1 | Derrick
2025-08-22 | 2025-08-17 | 2025-08-24 | Sunny Construction | 37.5044 | 4.688 | TB408 | 55/1 | Derrick
2025-08-22 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5 | Derrick
2025-08-22 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4 | Derrick
2025-08-22 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3 | Derrick
2025-08-22 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6 | Derrick
2025-08-23 | 2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TB408 | 8/1 | Derrick
2025-08-23 | 2025-08-19 | 2025-08-25 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 44/11 | Derrick
2025-08-23 | 2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 36/2 | Derrick
2025-08-23 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3 | Derrick
2025-08-23 | 2025-08-19 | 2025-08-25 | Jwala Singh | 37.5044 | 5.3578 | TB408 | 28/2 | Derrick
2025-08-23 | 2025-08-18 | 2025-08-25 | Pusplata | 66.3811 | 8.2976 | TB408 | 18/0 | Derrick
2025-08-23 | 2025-08-20 | 2025-08-25 | Pusplata Ashok | 37.5044 | 6.2507 | TB408 | 4/4 | Derrick
2025-08-23 | 2025-08-16 | 2025-08-23 | Pusplata Dharamveer | 38.8476 | 4.856 | TB408 | 27/1 | Derrick
2025-08-23 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TB408 | 27/0 | Derrick
2025-08-23 | 2025-08-22 | 2025-08-26 | Pusplata Kailash | 37.5044 | 7.5009 | TB408 | 31/1 | Derrick
2025-08-23 | 2025-08-18 | 2025-08-24 | Rahul Kumar | 38.8476 | 5.5497 | TB408 | 40/2 | Derrick
2025-08-23 | 2025-08-17 | 2025-08-24 | Satyam Enterprises | 47.1844 | 5.898 | TB408 | 44/9 | Derrick
2025-08-23 | 2025-08-21 | 2025-08-25 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 57/2 | Derrick
2025-08-23 | 2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TB408 | 57/1 | Derrick
2025-08-23 | 2025-08-17 | 2025-08-24 | Sunny Construction | 37.5044 | 4.688 | TB408 | 55/1 | Derrick
2025-08-23 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5 | Derrick
2025-08-23 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3 | Derrick
2025-08-23 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6 | Derrick
2025-08-24 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6 | Derrick
2025-08-24 | 2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TB408 | 8/1 | Derrick
2025-08-24 | 2025-08-19 | 2025-08-25 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 44/11 | Derrick
2025-08-24 | 2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 36/2 | Derrick
2025-08-24 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3 | Derrick
2025-08-24 | 2025-08-19 | 2025-08-25 | Jwala Singh | 37.5044 | 5.3578 | TB408 | 28/2 | Derrick
2025-08-24 | 2025-08-18 | 2025-08-25 | Pusplata | 66.3811 | 8.2976 | TB408 | 18/0 | Derrick
2025-08-24 | 2025-08-20 | 2025-08-25 | Pusplata Ashok | 37.5044 | 6.2507 | TB408 | 4/4 | Derrick
2025-08-24 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TB408 | 27/0 | Derrick
2025-08-24 | 2025-08-22 | 2025-08-26 | Pusplata Kailash | 37.5044 | 7.5009 | TB408 | 31/1 | Derrick
2025-08-24 | 2025-08-18 | 2025-08-24 | Rahul Kumar | 38.8476 | 5.5497 | TB408 | 40/2 | Derrick
2025-08-24 | 2025-08-17 | 2025-08-24 | Satyam Enterprises | 47.1844 | 5.898 | TB408 | 44/9 | Derrick
2025-08-24 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4 | Derrick
2025-08-24 | 2025-08-21 | 2025-08-25 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 57/2 | Derrick
2025-08-24 | 2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TB408 | 57/1 | Derrick
2025-08-24 | 2025-08-17 | 2025-08-24 | Sunny Construction | 37.5044 | 4.688 | TB408 | 55/1 | Derrick
2025-08-24 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5 | Derrick
2025-08-24 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3 | Derrick
2025-08-24 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6 | Derrick
2025-08-25 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6 | Derrick
2025-08-25 | 2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TB408 | 8/1 | Derrick
2025-08-25 | 2025-08-19 | 2025-08-25 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 44/11 | Derrick
2025-08-25 | 2025-08-25 | 2025-08-31 | Chinta Devi | 47.1844 | 6.7406 | TB408 | 45/1 | Derrick
2025-08-25 | 2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 36/2 | Derrick
2025-08-25 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3 | Derrick
2025-08-25 | 2025-08-19 | 2025-08-25 | Jwala Singh | 37.5044 | 5.3578 | TB408 | 28/2 | Derrick
2025-08-25 | 2025-08-18 | 2025-08-25 | Pusplata | 66.3811 | 8.2976 | TB408 | 18/0 | Derrick
2025-08-25 | 2025-08-20 | 2025-08-25 | Pusplata Ashok | 37.5044 | 6.2507 | TB408 | 4/4 | Derrick
2025-08-25 | 2025-08-25 | 2025-08-30 | Pusplata Deepak | 37.5044 | 6.2507 | TB408 | 30/1 | Derrick
2025-08-25 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TB408 | 27/0 | Derrick
2025-08-25 | 2025-08-22 | 2025-08-26 | Pusplata Kailash | 37.5044 | 7.5009 | TB408 | 31/1 | Derrick
2025-08-25 | 2025-08-25 | 2025-08-30 | Satyam Enterprises Pawan | 38.8476 | 6.4746 | TB408 | 43/10 | Derrick
2025-08-25 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4 | Derrick
2025-08-25 | 2025-08-21 | 2025-08-25 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 57/2 | Derrick
2025-08-25 | 2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TB408 | 57/1 | Derrick
2025-08-25 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5 | Derrick
2025-08-25 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3 | Derrick
2025-08-25 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6 | Derrick
2025-08-26 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6 | Derrick
2025-08-26 | 2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TB408 | 8/1 | Derrick
2025-08-26 | 2025-08-25 | 2025-08-31 | Chinta Devi | 47.1844 | 6.7406 | TB408 | 45/1 | Derrick
2025-08-26 | 2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 36/2 | Derrick
2025-08-26 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3 | Derrick
2025-08-26 | 2025-08-26 | 2025-09-03 | Priyanka Devi Santosh | 37.5044 | 4.1672 | TB408 | 20/3 | Derrick
2025-08-26 | 2025-08-25 | 2025-08-30 | Pusplata Deepak | 37.5044 | 6.2507 | TB408 | 30/1 | Derrick
2025-08-26 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TB408 | 27/0 | Derrick
2025-08-26 | 2025-08-22 | 2025-08-26 | Pusplata Kailash | 37.5044 | 7.5009 | TB408 | 31/1 | Derrick
2025-08-26 | 2025-08-26 | 2025-09-02 | Pusplata Kailash | 37.5044 | 4.688 | TB408 | 31/2 | Derrick
2025-08-26 | 2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0 | Derrick
2025-08-26 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TB408 | 26/0 | Derrick
2025-08-26 | 2025-08-26 | 2025-09-03 | Pusplata Santosh Pankaj Singh | 66.3811 | 7.3757 | TB408 | 14A/0 | Derrick
2025-08-26 | 2025-08-25 | 2025-08-30 | Satyam Enterprises Pawan | 38.8476 | 6.4746 | TB408 | 43/10 | Derrick
2025-08-26 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4 | Derrick
2025-08-26 | 2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TB408 | 57/1 | Derrick
2025-08-26 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5 | Derrick
2025-08-26 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3 | Derrick
2025-08-26 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6 | Derrick
2025-08-27 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6 | Derrick
2025-08-27 | 2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TB408 | 8/1 | Derrick
2025-08-27 | 2025-08-25 | 2025-08-31 | Chinta Devi | 47.1844 | 6.7406 | TB408 | 45/1 | Derrick
2025-08-27 | 2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 36/2 | Derrick
2025-08-27 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3 | Derrick
2025-08-27 | 2025-08-26 | 2025-09-03 | Priyanka Devi Santosh | 37.5044 | 4.1672 | TB408 | 20/3 | Derrick
2025-08-27 | 2025-08-25 | 2025-08-30 | Pusplata Deepak | 37.5044 | 6.2507 | TB408 | 30/1 | Derrick
2025-08-27 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TB408 | 27/0 | Derrick
2025-08-27 | 2025-08-26 | 2025-09-02 | Pusplata Kailash | 37.5044 | 4.688 | TB408 | 31/2 | Derrick
2025-08-27 | 2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0 | Derrick
2025-08-27 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TB408 | 26/0 | Derrick
2025-08-27 | 2025-08-26 | 2025-09-03 | Pusplata Santosh Pankaj Singh | 66.3811 | 7.3757 | TB408 | 14A/0 | Derrick
2025-08-27 | 2025-08-25 | 2025-08-30 | Satyam Enterprises Pawan | 38.8476 | 6.4746 | TB408 | 43/10 | Derrick
2025-08-27 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4 | Derrick
2025-08-27 | 2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TB408 | 57/1 | Derrick
2025-08-27 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5 | Derrick
2025-08-27 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3 | Derrick
2025-08-27 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6 | Derrick
2025-08-28 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6 | Derrick
2025-08-28 | 2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TB408 | 8/1 | Derrick
2025-08-28 | 2025-08-25 | 2025-08-31 | Chinta Devi | 47.1844 | 6.7406 | TB408 | 45/1 | Derrick
2025-08-28 | 2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 36/2 | Derrick
2025-08-28 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3 | Derrick
2025-08-28 | 2025-08-26 | 2025-09-03 | Priyanka Devi Santosh | 37.5044 | 4.1672 | TB408 | 20/3 | Derrick
2025-08-28 | 2025-08-25 | 2025-08-30 | Pusplata Deepak | 37.5044 | 6.2507 | TB408 | 30/1 | Derrick
2025-08-28 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TB408 | 27/0 | Derrick
2025-08-28 | 2025-08-26 | 2025-09-02 | Pusplata Kailash | 37.5044 | 4.688 | TB408 | 31/2 | Derrick
2025-08-28 | 2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0 | Derrick
2025-08-28 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TB408 | 26/0 | Derrick
2025-08-28 | 2025-08-26 | 2025-09-03 | Pusplata Santosh Pankaj Singh | 66.3811 | 7.3757 | TB408 | 14A/0 | Derrick
2025-08-28 | 2025-08-25 | 2025-08-30 | Satyam Enterprises Pawan | 38.8476 | 6.4746 | TB408 | 43/10 | Derrick
2025-08-28 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4 | Derrick
2025-08-28 | 2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TB408 | 57/1 | Derrick
2025-08-28 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5 | Derrick
2025-08-28 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3 | Derrick
2025-08-28 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6 | Derrick
2025-08-29 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6 | Derrick
2025-08-29 | 2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TB408 | 8/1 | Derrick
2025-08-29 | 2025-08-25 | 2025-08-31 | Chinta Devi | 47.1844 | 6.7406 | TB408 | 45/1 | Derrick
2025-08-29 | 2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 36/2 | Derrick
2025-08-29 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3 | Derrick
2025-08-29 | 2025-08-29 | 2025-09-04 | Jwala Singh | 38.8476 | 5.5497 | TB408 | 8/4 | Derrick
2025-08-29 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1 | Derrick
2025-08-29 | 2025-08-26 | 2025-09-03 | Priyanka Devi Santosh | 37.5044 | 4.1672 | TB408 | 20/3 | Derrick
2025-08-29 | 2025-08-29 | 2025-08-31 | Pusplata Ashok | 37.5044 | 12.5015 | TB408 | 4/3 | Derrick
2025-08-29 | 2025-08-25 | 2025-08-30 | Pusplata Deepak | 37.5044 | 6.2507 | TB408 | 30/1 | Derrick
2025-08-29 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TB408 | 27/0 | Derrick
2025-08-29 | 2025-08-26 | 2025-09-02 | Pusplata Kailash | 37.5044 | 4.688 | TB408 | 31/2 | Derrick
2025-08-29 | 2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0 | Derrick
2025-08-29 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TB408 | 26/0 | Derrick
2025-08-29 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-08-29 | 2025-08-26 | 2025-09-03 | Pusplata Santosh Pankaj Singh | 66.3811 | 7.3757 | TB408 | 14A/0 | Derrick
2025-08-29 | 2025-08-29 | 2025-09-03 | Satyam Enterprises Manish | 38.8476 | 6.4746 | TB408 | 43/5 | Derrick
2025-08-29 | 2025-08-25 | 2025-08-30 | Satyam Enterprises Pawan | 38.8476 | 6.4746 | TB408 | 43/10 | Derrick
2025-08-29 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4 | Derrick
2025-08-29 | 2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TB408 | 57/1 | Derrick
2025-08-29 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5 | Derrick
2025-08-29 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3 | Derrick
2025-08-29 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6 | Derrick
2025-08-30 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6 | Derrick
2025-08-30 | 2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TB408 | 8/1 | Derrick
2025-08-30 | 2025-08-25 | 2025-08-31 | Chinta Devi | 47.1844 | 6.7406 | TB408 | 45/1 | Derrick
2025-08-30 | 2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 36/2 | Derrick
2025-08-30 | 2025-08-30 | 2025-09-06 | Ganesh Sinha | 37.5044 | 4.688 | TB408 | 36/3 | Derrick
2025-08-30 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3 | Derrick
2025-08-30 | 2025-08-29 | 2025-09-04 | Jwala Singh | 38.8476 | 5.5497 | TB408 | 8/4 | Derrick
2025-08-30 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1 | Derrick
2025-08-30 | 2025-08-26 | 2025-09-03 | Priyanka Devi Santosh | 37.5044 | 4.1672 | TB408 | 20/3 | Derrick
2025-08-30 | 2025-08-29 | 2025-08-31 | Pusplata Ashok | 37.5044 | 12.5015 | TB408 | 4/3 | Derrick
2025-08-30 | 2025-08-25 | 2025-08-30 | Pusplata Deepak | 37.5044 | 6.2507 | TB408 | 30/1 | Derrick
2025-08-30 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TB408 | 27/0 | Derrick
2025-08-30 | 2025-08-26 | 2025-09-02 | Pusplata Kailash | 37.5044 | 4.688 | TB408 | 31/2 | Derrick
2025-08-30 | 2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0 | Derrick
2025-08-30 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TB408 | 26/0 | Derrick
2025-08-30 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-08-30 | 2025-08-26 | 2025-09-03 | Pusplata Santosh Pankaj Singh | 66.3811 | 7.3757 | TB408 | 14A/0 | Derrick
2025-08-30 | 2025-08-29 | 2025-09-03 | Satyam Enterprises Manish | 38.8476 | 6.4746 | TB408 | 43/5 | Derrick
2025-08-30 | 2025-08-25 | 2025-08-30 | Satyam Enterprises Pawan | 38.8476 | 6.4746 | TB408 | 43/10 | Derrick
2025-08-30 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4 | Derrick
2025-08-30 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0 | Derrick+Crane
2025-08-30 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5 | Derrick
2025-08-30 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6 | Derrick
2025-08-31 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6 | Derrick
2025-08-31 | 2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TB408 | 8/1 | Derrick
2025-08-31 | 2025-08-25 | 2025-08-31 | Chinta Devi | 47.1844 | 6.7406 | TB408 | 45/1 | Derrick
2025-08-31 | 2025-08-30 | 2025-09-06 | Ganesh Sinha | 37.5044 | 4.688 | TB408 | 36/3 | Derrick
2025-08-31 | 2025-08-29 | 2025-09-04 | Jwala Singh | 38.8476 | 5.5497 | TB408 | 8/4 | Derrick
2025-08-31 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1 | Derrick
2025-08-31 | 2025-08-26 | 2025-09-03 | Priyanka Devi Santosh | 37.5044 | 4.1672 | TB408 | 20/3 | Derrick
2025-08-31 | 2025-08-29 | 2025-08-31 | Pusplata Ashok | 37.5044 | 12.5015 | TB408 | 4/3 | Derrick
2025-08-31 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TB408 | 27/0 | Derrick
2025-08-31 | 2025-08-26 | 2025-09-02 | Pusplata Kailash | 37.5044 | 4.688 | TB408 | 31/2 | Derrick
2025-08-31 | 2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0 | Derrick
2025-08-31 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TB408 | 26/0 | Derrick
2025-08-31 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-08-31 | 2025-08-26 | 2025-09-03 | Pusplata Santosh Pankaj Singh | 66.3811 | 7.3757 | TB408 | 14A/0 | Derrick
2025-08-31 | 2025-08-29 | 2025-09-03 | Satyam Enterprises Manish | 38.8476 | 6.4746 | TB408 | 43/5 | Derrick
2025-08-31 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4 | Derrick
2025-08-31 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0 | Derrick+Crane
2025-08-31 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5 | Derrick
2025-08-31 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6 | Derrick
2025-09-01 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6 | Derrick
2025-09-01 | 2025-09-01 | 2025-09-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 47/1 | Derrick
2025-09-01 | 2025-08-30 | 2025-09-06 | Ganesh Sinha | 37.5044 | 4.688 | TB408 | 36/3 | Derrick
2025-09-01 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TB408 | 52/4 | Derrick
2025-09-01 | 2025-08-29 | 2025-09-04 | Jwala Singh | 38.8476 | 5.5497 | TB408 | 8/4 | Derrick
2025-09-01 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1 | Derrick
2025-09-01 | 2025-08-26 | 2025-09-03 | Priyanka Devi Santosh | 37.5044 | 4.1672 | TB408 | 20/3 | Derrick
2025-09-01 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TB408 | 27/0 | Derrick
2025-09-01 | 2025-08-26 | 2025-09-02 | Pusplata Kailash | 37.5044 | 4.688 | TB408 | 31/2 | Derrick
2025-09-01 | 2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0 | Derrick
2025-09-01 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TB408 | 26/0 | Derrick
2025-09-01 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-09-01 | 2025-08-26 | 2025-09-03 | Pusplata Santosh Pankaj Singh | 66.3811 | 7.3757 | TB408 | 14A/0 | Derrick
2025-09-01 | 2025-08-29 | 2025-09-03 | Satyam Enterprises Manish | 38.8476 | 6.4746 | TB408 | 43/5 | Derrick
2025-09-01 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4 | Derrick
2025-09-01 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0 | Derrick+Crane
2025-09-01 | 2025-09-01 | 2025-09-06 | Sunny Construction | 47.1844 | 7.8641 | TB408 | 54/4 | Derrick
2025-09-01 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6 | Derrick
2025-09-02 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6 | Derrick
2025-09-02 | 2025-09-01 | 2025-09-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 47/1 | Derrick
2025-09-02 | 2025-08-30 | 2025-09-06 | Ganesh Sinha | 37.5044 | 4.688 | TB408 | 36/3 | Derrick
2025-09-02 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TB408 | 52/4 | Derrick
2025-09-02 | 2025-08-29 | 2025-09-04 | Jwala Singh | 38.8476 | 5.5497 | TB408 | 8/4 | Derrick
2025-09-02 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1 | Derrick
2025-09-02 | 2025-08-26 | 2025-09-03 | Priyanka Devi Santosh | 37.5044 | 4.1672 | TB408 | 20/3 | Derrick
2025-09-02 | 2025-09-02 | 2025-09-07 | Priyanka Devi Sudheer | 37.5044 | 6.2507 | TB408 | 20/2 | Derrick
2025-09-02 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TB408 | 27/0 | Derrick
2025-09-02 | 2025-08-26 | 2025-09-02 | Pusplata Kailash | 37.5044 | 4.688 | TB408 | 31/2 | Derrick
2025-09-02 | 2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0 | Derrick
2025-09-02 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TB408 | 26/0 | Derrick
2025-09-02 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-09-02 | 2025-08-26 | 2025-09-03 | Pusplata Santosh Pankaj Singh | 66.3811 | 7.3757 | TB408 | 14A/0 | Derrick
2025-09-02 | 2025-08-29 | 2025-09-03 | Satyam Enterprises Manish | 38.8476 | 6.4746 | TB408 | 43/5 | Derrick
2025-09-02 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4 | Derrick
2025-09-02 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0 | Derrick+Crane
2025-09-02 | 2025-09-02 | 2025-09-05 | Sudheer 2 Priyanka Devi | 57.5972 | 14.3993 | TB408 | 21/0 | Derrick
2025-09-02 | 2025-09-01 | 2025-09-06 | Sunny Construction | 47.1844 | 7.8641 | TB408 | 54/4 | Derrick
2025-09-02 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6 | Derrick
2025-09-03 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6 | Derrick
2025-09-03 | 2025-09-01 | 2025-09-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 47/1 | Derrick
2025-09-03 | 2025-08-30 | 2025-09-06 | Ganesh Sinha | 37.5044 | 4.688 | TB408 | 36/3 | Derrick
2025-09-03 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TB408 | 52/4 | Derrick
2025-09-03 | 2025-08-29 | 2025-09-04 | Jwala Singh | 38.8476 | 5.5497 | TB408 | 8/4 | Derrick
2025-09-03 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TB408 | 28/0 | Derrick
2025-09-03 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1 | Derrick
2025-09-03 | 2025-08-26 | 2025-09-03 | Priyanka Devi Santosh | 37.5044 | 4.1672 | TB408 | 20/3 | Derrick
2025-09-03 | 2025-09-02 | 2025-09-07 | Priyanka Devi Sudheer | 37.5044 | 6.2507 | TB408 | 20/2 | Derrick
2025-09-03 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TB408 | 27/0 | Derrick
2025-09-03 | 2025-09-03 | 2025-09-10 | Pusplata Kailash | 38.8476 | 4.856 | TB408 | 32/1 | Derrick
2025-09-03 | 2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0 | Derrick
2025-09-03 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TB408 | 26/0 | Derrick
2025-09-03 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-09-03 | 2025-08-26 | 2025-09-03 | Pusplata Santosh Pankaj Singh | 66.3811 | 7.3757 | TB408 | 14A/0 | Derrick
2025-09-03 | 2025-08-29 | 2025-09-03 | Satyam Enterprises Manish | 38.8476 | 6.4746 | TB408 | 43/5 | Derrick
2025-09-03 | 2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TB408 | 34/3 | Derrick
2025-09-03 | 2025-09-03 | 2025-09-13 | Sheetal Singh 1 | 38.8476 | 3.5316 | TB408 | 2/1 | Derrick
2025-09-03 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4 | Derrick
2025-09-03 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0 | Derrick+Crane
2025-09-03 | 2025-09-02 | 2025-09-05 | Sudheer 2 Priyanka Devi | 57.5972 | 14.3993 | TB408 | 21/0 | Derrick
2025-09-03 | 2025-09-01 | 2025-09-06 | Sunny Construction | 47.1844 | 7.8641 | TB408 | 54/4 | Derrick
2025-09-03 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6 | Derrick
2025-09-04 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6 | Derrick
2025-09-04 | 2025-09-01 | 2025-09-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 47/1 | Derrick
2025-09-04 | 2025-08-30 | 2025-09-06 | Ganesh Sinha | 37.5044 | 4.688 | TB408 | 36/3 | Derrick
2025-09-04 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TB408 | 52/4 | Derrick
2025-09-04 | 2025-08-29 | 2025-09-04 | Jwala Singh | 38.8476 | 5.5497 | TB408 | 8/4 | Derrick
2025-09-04 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TB408 | 28/0 | Derrick
2025-09-04 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1 | Derrick
2025-09-04 | 2025-09-02 | 2025-09-07 | Priyanka Devi Sudheer | 37.5044 | 6.2507 | TB408 | 20/2 | Derrick
2025-09-04 | 2025-09-03 | 2025-09-10 | Pusplata Kailash | 38.8476 | 4.856 | TB408 | 32/1 | Derrick
2025-09-04 | 2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0 | Derrick
2025-09-04 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TB408 | 26/0 | Derrick
2025-09-04 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-09-04 | 2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TB408 | 34/3 | Derrick
2025-09-04 | 2025-09-03 | 2025-09-13 | Sheetal Singh 1 | 38.8476 | 3.5316 | TB408 | 2/1 | Derrick
2025-09-04 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4 | Derrick
2025-09-04 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0 | Derrick+Crane
2025-09-04 | 2025-09-02 | 2025-09-05 | Sudheer 2 Priyanka Devi | 57.5972 | 14.3993 | TB408 | 21/0 | Derrick
2025-09-04 | 2025-09-01 | 2025-09-06 | Sunny Construction | 47.1844 | 7.8641 | TB408 | 54/4 | Derrick
2025-09-04 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6 | Derrick
2025-09-05 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6 | Derrick
2025-09-05 | 2025-09-01 | 2025-09-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 47/1 | Derrick
2025-09-05 | 2025-08-30 | 2025-09-06 | Ganesh Sinha | 37.5044 | 4.688 | TB408 | 36/3 | Derrick
2025-09-05 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TB408 | 52/4 | Derrick
2025-09-05 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TB408 | 28/0 | Derrick
2025-09-05 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1 | Derrick
2025-09-05 | 2025-09-02 | 2025-09-07 | Priyanka Devi Sudheer | 37.5044 | 6.2507 | TB408 | 20/2 | Derrick
2025-09-05 | 2025-09-03 | 2025-09-10 | Pusplata Kailash | 38.8476 | 4.856 | TB408 | 32/1 | Derrick
2025-09-05 | 2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0 | Derrick
2025-09-05 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TB408 | 26/0 | Derrick
2025-09-05 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-09-05 | 2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TB408 | 34/3 | Derrick
2025-09-05 | 2025-09-03 | 2025-09-13 | Sheetal Singh 1 | 38.8476 | 3.5316 | TB408 | 2/1 | Derrick
2025-09-05 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4 | Derrick
2025-09-05 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0 | Derrick+Crane
2025-09-05 | 2025-09-02 | 2025-09-05 | Sudheer 2 Priyanka Devi | 57.5972 | 14.3993 | TB408 | 21/0 | Derrick
2025-09-05 | 2025-09-01 | 2025-09-06 | Sunny Construction | 47.1844 | 7.8641 | TB408 | 54/4 | Derrick
2025-09-05 | 2025-09-05 | 2025-09-12 | Usha Tower | 37.5044 | 4.688 | TB408 | 6/2 | Derrick
2025-09-05 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6 | Derrick
2025-09-06 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6 | Derrick
2025-09-06 | 2025-09-01 | 2025-09-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 47/1 | Derrick
2025-09-06 | 2025-08-30 | 2025-09-06 | Ganesh Sinha | 37.5044 | 4.688 | TB408 | 36/3 | Derrick
2025-09-06 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TB408 | 52/4 | Derrick
2025-09-06 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TB408 | 28/0 | Derrick
2025-09-06 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1 | Derrick
2025-09-06 | 2025-09-02 | 2025-09-07 | Priyanka Devi Sudheer | 37.5044 | 6.2507 | TB408 | 20/2 | Derrick
2025-09-06 | 2025-09-03 | 2025-09-10 | Pusplata Kailash | 38.8476 | 4.856 | TB408 | 32/1 | Derrick
2025-09-06 | 2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0 | Derrick
2025-09-06 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TB408 | 26/0 | Derrick
2025-09-06 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-09-06 | 2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TB408 | 34/3 | Derrick
2025-09-06 | 2025-09-03 | 2025-09-13 | Sheetal Singh 1 | 38.8476 | 3.5316 | TB408 | 2/1 | Derrick
2025-09-06 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4 | Derrick
2025-09-06 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0 | Derrick+Crane
2025-09-06 | 2025-09-01 | 2025-09-06 | Sunny Construction | 47.1844 | 7.8641 | TB408 | 54/4 | Derrick
2025-09-06 | 2025-09-05 | 2025-09-12 | Usha Tower | 37.5044 | 4.688 | TB408 | 6/2 | Derrick
2025-09-06 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6 | Derrick
2025-09-07 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6 | Derrick
2025-09-07 | 2025-09-01 | 2025-09-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 47/1 | Derrick
2025-09-07 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TB408 | 36/4 | Derrick
2025-09-07 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TB408 | 52/4 | Derrick
2025-09-07 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TB408 | 28/0 | Derrick
2025-09-07 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1 | Derrick
2025-09-07 | 2025-09-02 | 2025-09-07 | Priyanka Devi Sudheer | 37.5044 | 6.2507 | TB408 | 20/2 | Derrick
2025-09-07 | 2025-09-03 | 2025-09-10 | Pusplata Kailash | 38.8476 | 4.856 | TB408 | 32/1 | Derrick
2025-09-07 | 2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0 | Derrick
2025-09-07 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TB408 | 26/1 | Derrick
2025-09-07 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-09-07 | 2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TB408 | 34/3 | Derrick
2025-09-07 | 2025-09-03 | 2025-09-13 | Sheetal Singh 1 | 38.8476 | 3.5316 | TB408 | 2/1 | Derrick
2025-09-07 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4 | Derrick
2025-09-07 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0 | Derrick+Crane
2025-09-07 | 2025-09-07 | 2025-09-12 | Sunny Construction | 45.413 | 7.5688 | TB408 | 54/3 | Derrick
2025-09-07 | 2025-09-05 | 2025-09-12 | Usha Tower | 37.5044 | 4.688 | TB408 | 6/2 | Derrick
2025-09-07 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5 | Derrick
2025-09-08 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6 | Derrick
2025-09-08 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TB408 | 36/4 | Derrick
2025-09-08 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TB408 | 52/4 | Derrick
2025-09-08 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TB408 | 28/0 | Derrick
2025-09-08 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1 | Derrick
2025-09-08 | 2025-09-03 | 2025-09-10 | Pusplata Kailash | 38.8476 | 4.856 | TB408 | 32/1 | Derrick
2025-09-08 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TB408 | 26/1 | Derrick
2025-09-08 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-09-08 | 2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TB408 | 34/3 | Derrick
2025-09-08 | 2025-09-03 | 2025-09-13 | Sheetal Singh 1 | 38.8476 | 3.5316 | TB408 | 2/1 | Derrick
2025-09-08 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4 | Derrick
2025-09-08 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0 | Derrick+Crane
2025-09-08 | 2025-09-07 | 2025-09-12 | Sunny Construction | 45.413 | 7.5688 | TB408 | 54/3 | Derrick
2025-09-08 | 2025-09-05 | 2025-09-12 | Usha Tower | 37.5044 | 4.688 | TB408 | 6/2 | Derrick
2025-09-08 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5 | Derrick
2025-09-09 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6 | Derrick
2025-09-09 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0 | Derrick+Crane
2025-09-09 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TB408 | 36/4 | Derrick
2025-09-09 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TB408 | 52/4 | Derrick
2025-09-09 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TB408 | 28/0 | Derrick
2025-09-09 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1 | Derrick
2025-09-09 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2 | Derrick
2025-09-09 | 2025-09-09 | 2025-09-12 | Priyanka Devi Sudheer | 38.8476 | 9.7119 | TB408 | 21/4 | Derrick
2025-09-09 | 2025-09-03 | 2025-09-10 | Pusplata Kailash | 38.8476 | 4.856 | TB408 | 32/1 | Derrick
2025-09-09 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TB408 | 26/1 | Derrick
2025-09-09 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-09-09 | 2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TB408 | 34/3 | Derrick
2025-09-09 | 2025-09-03 | 2025-09-13 | Sheetal Singh 1 | 38.8476 | 3.5316 | TB408 | 2/1 | Derrick
2025-09-09 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4 | Derrick
2025-09-09 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0 | Derrick+Crane
2025-09-09 | 2025-09-07 | 2025-09-12 | Sunny Construction | 45.413 | 7.5688 | TB408 | 54/3 | Derrick
2025-09-09 | 2025-09-05 | 2025-09-12 | Usha Tower | 37.5044 | 4.688 | TB408 | 6/2 | Derrick
2025-09-09 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5 | Derrick
2025-09-09 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3 | Derrick
2025-09-10 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0 | Derrick+Crane
2025-09-10 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TB408 | 36/4 | Derrick
2025-09-10 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TB408 | 52/4 | Derrick
2025-09-10 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/2 | Derrick
2025-09-10 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TB408 | 28/0 | Derrick
2025-09-10 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3 | Derrick
2025-09-10 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1 | Derrick
2025-09-10 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2 | Derrick
2025-09-10 | 2025-09-09 | 2025-09-12 | Priyanka Devi Sudheer | 38.8476 | 9.7119 | TB408 | 21/4 | Derrick
2025-09-10 | 2025-09-03 | 2025-09-10 | Pusplata Kailash | 38.8476 | 4.856 | TB408 | 32/1 | Derrick
2025-09-10 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TB408 | 26/1 | Derrick
2025-09-10 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-09-10 | 2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TB408 | 34/3 | Derrick
2025-09-10 | 2025-09-03 | 2025-09-13 | Sheetal Singh 1 | 38.8476 | 3.5316 | TB408 | 2/1 | Derrick
2025-09-10 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0 | Derrick+Crane
2025-09-10 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3 | Derrick
2025-09-10 | 2025-09-07 | 2025-09-12 | Sunny Construction | 45.413 | 7.5688 | TB408 | 54/3 | Derrick
2025-09-10 | 2025-09-05 | 2025-09-12 | Usha Tower | 37.5044 | 4.688 | TB408 | 6/2 | Derrick
2025-09-10 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5 | Derrick
2025-09-10 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3 | Derrick
2025-09-11 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0 | Derrick+Crane
2025-09-11 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TB408 | 36/4 | Derrick
2025-09-11 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/2 | Derrick
2025-09-11 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TB408 | 28/0 | Derrick
2025-09-11 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3 | Derrick
2025-09-11 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1 | Derrick
2025-09-11 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2 | Derrick
2025-09-11 | 2025-09-09 | 2025-09-12 | Priyanka Devi Sudheer | 38.8476 | 9.7119 | TB408 | 21/4 | Derrick
2025-09-11 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TB408 | 26/1 | Derrick
2025-09-11 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-09-11 | 2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TB408 | 34/3 | Derrick
2025-09-11 | 2025-09-03 | 2025-09-13 | Sheetal Singh 1 | 38.8476 | 3.5316 | TB408 | 2/1 | Derrick
2025-09-11 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0 | Derrick+Crane
2025-09-11 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3 | Derrick
2025-09-11 | 2025-09-07 | 2025-09-12 | Sunny Construction | 45.413 | 7.5688 | TB408 | 54/3 | Derrick
2025-09-11 | 2025-09-05 | 2025-09-12 | Usha Tower | 37.5044 | 4.688 | TB408 | 6/2 | Derrick
2025-09-11 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5 | Derrick
2025-09-11 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3 | Derrick
2025-09-12 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TB408 | 8/2 | Derrick
2025-09-12 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0 | Derrick+Crane
2025-09-12 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TB408 | 36/4 | Derrick
2025-09-12 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/2 | Derrick
2025-09-12 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TB408 | 28/0 | Derrick
2025-09-12 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3 | Derrick
2025-09-12 | 2025-09-12 | 2025-09-18 | Jwala Singh 2 | 38.8476 | 5.5497 | TB408 | 8/5 | Derrick
2025-09-12 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1 | Derrick
2025-09-12 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2 | Derrick
2025-09-12 | 2025-09-09 | 2025-09-12 | Priyanka Devi Sudheer | 38.8476 | 9.7119 | TB408 | 21/4 | Derrick
2025-09-12 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TB408 | 26/1 | Derrick
2025-09-12 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-09-12 | 2025-09-03 | 2025-09-13 | Sheetal Singh 1 | 38.8476 | 3.5316 | TB408 | 2/1 | Derrick
2025-09-12 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0 | Derrick+Crane
2025-09-12 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3 | Derrick
2025-09-12 | 2025-09-07 | 2025-09-12 | Sunny Construction | 45.413 | 7.5688 | TB408 | 54/3 | Derrick
2025-09-12 | 2025-09-05 | 2025-09-12 | Usha Tower | 37.5044 | 4.688 | TB408 | 6/2 | Derrick
2025-09-12 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5 | Derrick
2025-09-12 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3 | Derrick
2025-09-13 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TB408 | 8/2 | Derrick
2025-09-13 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0 | Derrick+Crane
2025-09-13 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TB408 | 36/4 | Derrick
2025-09-13 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/2 | Derrick
2025-09-13 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3 | Derrick
2025-09-13 | 2025-09-12 | 2025-09-18 | Jwala Singh 2 | 38.8476 | 5.5497 | TB408 | 8/5 | Derrick
2025-09-13 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1 | Derrick
2025-09-13 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2 | Derrick
2025-09-13 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TB408 | 26/1 | Derrick
2025-09-13 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-09-13 | 2025-09-03 | 2025-09-13 | Sheetal Singh 1 | 38.8476 | 3.5316 | TB408 | 2/1 | Derrick
2025-09-13 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0 | Derrick+Crane
2025-09-13 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3 | Derrick
2025-09-13 | 2025-09-13 | 2025-09-18 | Sunny Construction | 38.8476 | 6.4746 | TB408 | 54/1 | Derrick
2025-09-13 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5 | Derrick
2025-09-13 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3 | Derrick
2025-09-14 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TB408 | 8/2 | Derrick
2025-09-14 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0 | Derrick+Crane
2025-09-14 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TB408 | 36/4 | Derrick
2025-09-14 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/2 | Derrick
2025-09-14 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3 | Derrick
2025-09-14 | 2025-09-12 | 2025-09-18 | Jwala Singh 2 | 38.8476 | 5.5497 | TB408 | 8/5 | Derrick
2025-09-14 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1 | Derrick
2025-09-14 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2 | Derrick
2025-09-14 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TB408 | 26/1 | Derrick
2025-09-14 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-09-14 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0 | Derrick+Crane
2025-09-14 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3 | Derrick
2025-09-14 | 2025-09-13 | 2025-09-18 | Sunny Construction | 38.8476 | 6.4746 | TB408 | 54/1 | Derrick
2025-09-14 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5 | Derrick
2025-09-14 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3 | Derrick
2025-09-15 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TB408 | 8/2 | Derrick
2025-09-15 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0 | Derrick+Crane
2025-09-15 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TB408 | 36/4 | Derrick
2025-09-15 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/2 | Derrick
2025-09-15 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3 | Derrick
2025-09-15 | 2025-09-12 | 2025-09-18 | Jwala Singh 2 | 38.8476 | 5.5497 | TB408 | 8/5 | Derrick
2025-09-15 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1 | Derrick
2025-09-15 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2 | Derrick
2025-09-15 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TB408 | 26/1 | Derrick
2025-09-15 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-09-15 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0 | Derrick+Crane
2025-09-15 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3 | Derrick
2025-09-15 | 2025-09-13 | 2025-09-18 | Sunny Construction | 38.8476 | 6.4746 | TB408 | 54/1 | Derrick
2025-09-15 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5 | Derrick
2025-09-15 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3 | Derrick
2025-09-16 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TB408 | 8/2 | Derrick
2025-09-16 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0 | Derrick+Crane
2025-09-16 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TB408 | 36/4 | Derrick
2025-09-16 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TB408 | 37/0 | Derrick
2025-09-16 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/2 | Derrick
2025-09-16 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3 | Derrick
2025-09-16 | 2025-09-12 | 2025-09-18 | Jwala Singh 2 | 38.8476 | 5.5497 | TB408 | 8/5 | Derrick
2025-09-16 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1 | Derrick
2025-09-16 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TB408 | 36/0 | Derrick
2025-09-16 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2 | Derrick
2025-09-16 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TB408 | 26/1 | Derrick
2025-09-16 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-09-16 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0 | Derrick+Crane
2025-09-16 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3 | Derrick
2025-09-16 | 2025-09-13 | 2025-09-18 | Sunny Construction | 38.8476 | 6.4746 | TB408 | 54/1 | Derrick
2025-09-16 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5 | Derrick
2025-09-16 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3 | Derrick
2025-09-17 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TB408 | 8/2 | Derrick
2025-09-17 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0 | Derrick+Crane
2025-09-17 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TB408 | 37/0 | Derrick
2025-09-17 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/2 | Derrick
2025-09-17 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3 | Derrick
2025-09-17 | 2025-09-12 | 2025-09-18 | Jwala Singh 2 | 38.8476 | 5.5497 | TB408 | 8/5 | Derrick
2025-09-17 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TB408 | 36/0 | Derrick
2025-09-17 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2 | Derrick
2025-09-17 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-09-17 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0 | Derrick+Crane
2025-09-17 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3 | Derrick
2025-09-17 | 2025-09-13 | 2025-09-18 | Sunny Construction | 38.8476 | 6.4746 | TB408 | 54/1 | Derrick
2025-09-17 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5 | Derrick
2025-09-17 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3 | Derrick
2025-09-18 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TB408 | 8/2 | Derrick
2025-09-18 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0 | Derrick+Crane
2025-09-18 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TB408 | 37/0 | Derrick
2025-09-18 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/2 | Derrick
2025-09-18 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3 | Derrick
2025-09-18 | 2025-09-12 | 2025-09-18 | Jwala Singh 2 | 38.8476 | 5.5497 | TB408 | 8/5 | Derrick
2025-09-18 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TB408 | 36/0 | Derrick
2025-09-18 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2 | Derrick
2025-09-18 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-09-18 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0 | Derrick+Crane
2025-09-18 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3 | Derrick
2025-09-18 | 2025-09-13 | 2025-09-18 | Sunny Construction | 38.8476 | 6.4746 | TB408 | 54/1 | Derrick
2025-09-18 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5 | Derrick
2025-09-18 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3 | Derrick
2025-09-19 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TB408 | 8/2 | Derrick
2025-09-19 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0 | Derrick+Crane
2025-09-19 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TB408 | 37/0 | Derrick
2025-09-19 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/2 | Derrick
2025-09-19 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3 | Derrick
2025-09-19 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TB408 | 36/0 | Derrick
2025-09-19 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2 | Derrick
2025-09-19 | 2025-09-19 | 2025-09-22 | Priyanka Devi Sudheer | 45.413 | 11.3533 | TB408 | 21/5 | Derrick
2025-09-19 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-09-19 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0 | Derrick+Crane
2025-09-19 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3 | Derrick
2025-09-19 | 2025-09-19 | 2025-09-22 | Sunny Construction | 38.8476 | 9.7119 | TB408 | 54/2 | Derrick
2025-09-19 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5 | Derrick
2025-09-19 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3 | Derrick
2025-09-20 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TB408 | 8/2 | Derrick
2025-09-20 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0 | Derrick+Crane
2025-09-20 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TB408 | 37/0 | Derrick
2025-09-20 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/2 | Derrick
2025-09-20 | 2025-09-20 | 2025-09-30 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/1 | Derrick
2025-09-20 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3 | Derrick
2025-09-20 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TB408 | 36/0 | Derrick
2025-09-20 | 2025-09-20 | 2025-09-29 | Priyanka Devi Sontosh | 57.5972 | 5.7597 | TB408 | 20/0 | Derrick
2025-09-20 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2 | Derrick
2025-09-20 | 2025-09-19 | 2025-09-22 | Priyanka Devi Sudheer | 45.413 | 11.3533 | TB408 | 21/5 | Derrick
2025-09-20 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-09-20 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0 | Derrick+Crane
2025-09-20 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3 | Derrick
2025-09-20 | 2025-09-19 | 2025-09-22 | Sunny Construction | 38.8476 | 9.7119 | TB408 | 54/2 | Derrick
2025-09-20 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5 | Derrick
2025-09-20 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3 | Derrick
2025-09-21 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TB408 | 8/2 | Derrick
2025-09-21 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0 | Derrick+Crane
2025-09-21 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TB408 | 37/0 | Derrick
2025-09-21 | 2025-09-20 | 2025-09-30 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/1 | Derrick
2025-09-21 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3 | Derrick
2025-09-21 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TB408 | 36/0 | Derrick
2025-09-21 | 2025-09-20 | 2025-09-29 | Priyanka Devi Sontosh | 57.5972 | 5.7597 | TB408 | 20/0 | Derrick
2025-09-21 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2 | Derrick
2025-09-21 | 2025-09-19 | 2025-09-22 | Priyanka Devi Sudheer | 45.413 | 11.3533 | TB408 | 21/5 | Derrick
2025-09-21 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-09-21 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0 | Derrick+Crane
2025-09-21 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3 | Derrick
2025-09-21 | 2025-09-19 | 2025-09-22 | Sunny Construction | 38.8476 | 9.7119 | TB408 | 54/2 | Derrick
2025-09-21 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5 | Derrick
2025-09-21 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3 | Derrick
2025-09-22 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TB408 | 8/2 | Derrick
2025-09-22 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0 | Derrick+Crane
2025-09-22 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TB408 | 37/0 | Derrick
2025-09-22 | 2025-09-20 | 2025-09-30 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/1 | Derrick
2025-09-22 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3 | Derrick
2025-09-22 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TB408 | 36/0 | Derrick
2025-09-22 | 2025-09-20 | 2025-09-29 | Priyanka Devi Sontosh | 57.5972 | 5.7597 | TB408 | 20/0 | Derrick
2025-09-22 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2 | Derrick
2025-09-22 | 2025-09-19 | 2025-09-22 | Priyanka Devi Sudheer | 45.413 | 11.3533 | TB408 | 21/5 | Derrick
2025-09-22 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-09-22 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0 | Derrick+Crane
2025-09-22 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3 | Derrick
2025-09-22 | 2025-09-19 | 2025-09-22 | Sunny Construction | 38.8476 | 9.7119 | TB408 | 54/2 | Derrick
2025-09-22 | 2025-09-22 | 2025-09-30 | Sunny Construction | 67.8737 | 7.5415 | TB408 | 54/0 | Derrick
2025-09-22 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5 | Derrick
2025-09-22 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3 | Derrick
2025-09-22 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6 | Derrick
2025-09-23 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TB408 | 8/2 | Derrick
2025-09-23 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0 | Derrick+Crane
2025-09-23 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TB408 | 37/0 | Derrick
2025-09-23 | 2025-09-20 | 2025-09-30 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/1 | Derrick
2025-09-23 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3 | Derrick
2025-09-23 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TB408 | 36/0 | Derrick
2025-09-23 | 2025-09-20 | 2025-09-29 | Priyanka Devi Sontosh | 57.5972 | 5.7597 | TB408 | 20/0 | Derrick
2025-09-23 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-09-23 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0 | Derrick+Crane
2025-09-23 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3 | Derrick
2025-09-23 | 2025-09-22 | 2025-09-30 | Sunny Construction | 67.8737 | 7.5415 | TB408 | 54/0 | Derrick
2025-09-23 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5 | Derrick
2025-09-23 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6 | Derrick
2025-09-24 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0 | Derrick+Crane
2025-09-24 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TB408 | 37/0 | Derrick
2025-09-24 | 2025-09-20 | 2025-09-30 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/1 | Derrick
2025-09-24 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TB408 | 36/0 | Derrick
2025-09-24 | 2025-09-20 | 2025-09-29 | Priyanka Devi Sontosh | 57.5972 | 5.7597 | TB408 | 20/0 | Derrick
2025-09-24 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-09-24 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0 | Derrick+Crane
2025-09-24 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3 | Derrick
2025-09-24 | 2025-09-22 | 2025-09-30 | Sunny Construction | 67.8737 | 7.5415 | TB408 | 54/0 | Derrick
2025-09-24 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5 | Derrick
2025-09-24 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6 | Derrick
2025-09-25 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0 | Derrick+Crane
2025-09-25 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TB408 | 37/0 | Derrick
2025-09-25 | 2025-09-20 | 2025-09-30 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/1 | Derrick
2025-09-25 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TB408 | 36/0 | Derrick
2025-09-25 | 2025-09-20 | 2025-09-29 | Priyanka Devi Sontosh | 57.5972 | 5.7597 | TB408 | 20/0 | Derrick
2025-09-25 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-09-25 | 2025-09-25 | 2025-10-03 | Sheetal Singh 1 | 37.5044 | 4.1672 | TB408 | 6/1 | Derrick
2025-09-25 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0 | Derrick+Crane
2025-09-25 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3 | Derrick
2025-09-25 | 2025-09-22 | 2025-09-30 | Sunny Construction | 67.8737 | 7.5415 | TB408 | 54/0 | Derrick
2025-09-25 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5 | Derrick
2025-09-25 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6 | Derrick
2025-09-26 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TB408 | 37/0 | Derrick
2025-09-26 | 2025-09-20 | 2025-09-30 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/1 | Derrick
2025-09-26 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TB408 | 36/0 | Derrick
2025-09-26 | 2025-09-20 | 2025-09-29 | Priyanka Devi Sontosh | 57.5972 | 5.7597 | TB408 | 20/0 | Derrick
2025-09-26 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-09-26 | 2025-09-25 | 2025-10-03 | Sheetal Singh 1 | 37.5044 | 4.1672 | TB408 | 6/1 | Derrick
2025-09-26 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0 | Derrick+Crane
2025-09-26 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3 | Derrick
2025-09-26 | 2025-09-22 | 2025-09-30 | Sunny Construction | 67.8737 | 7.5415 | TB408 | 54/0 | Derrick
2025-09-26 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5 | Derrick
2025-09-26 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6 | Derrick
2025-09-27 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TB408 | 37/0 | Derrick
2025-09-27 | 2025-09-20 | 2025-09-30 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/1 | Derrick
2025-09-27 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TB408 | 36/0 | Derrick
2025-09-27 | 2025-09-27 | 2025-10-06 | Nirmal Mahto | 37.5044 | 3.7504 | TB408 | 35/5 | Derrick
2025-09-27 | 2025-09-20 | 2025-09-29 | Priyanka Devi Sontosh | 57.5972 | 5.7597 | TB408 | 20/0 | Derrick
2025-09-27 | 2025-09-25 | 2025-10-03 | Sheetal Singh 1 | 37.5044 | 4.1672 | TB408 | 6/1 | Derrick
2025-09-27 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0 | Derrick+Crane
2025-09-27 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3 | Derrick
2025-09-27 | 2025-09-22 | 2025-09-30 | Sunny Construction | 67.8737 | 7.5415 | TB408 | 54/0 | Derrick
2025-09-27 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5 | Derrick
2025-09-27 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6 | Derrick
2025-09-28 | 2025-09-20 | 2025-09-30 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/1 | Derrick
2025-09-28 | 2025-09-27 | 2025-10-06 | Nirmal Mahto | 37.5044 | 3.7504 | TB408 | 35/5 | Derrick
2025-09-28 | 2025-09-20 | 2025-09-29 | Priyanka Devi Sontosh | 57.5972 | 5.7597 | TB408 | 20/0 | Derrick
2025-09-28 | 2025-09-25 | 2025-10-03 | Sheetal Singh 1 | 37.5044 | 4.1672 | TB408 | 6/1 | Derrick
2025-09-28 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0 | Derrick+Crane
2025-09-28 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3 | Derrick
2025-09-28 | 2025-09-22 | 2025-09-30 | Sunny Construction | 67.8737 | 7.5415 | TB408 | 54/0 | Derrick
2025-09-28 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5 | Derrick
2025-09-28 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6 | Derrick
2025-09-29 | 2025-09-29 | 2025-10-18 | Chinta Devi | 143.6019 | 7.1801 | TB408 | 46/0 | Derrick
2025-09-29 | 2025-09-20 | 2025-09-30 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/1 | Derrick
2025-09-29 | 2025-09-27 | 2025-10-06 | Nirmal Mahto | 37.5044 | 3.7504 | TB408 | 35/5 | Derrick
2025-09-29 | 2025-09-20 | 2025-09-29 | Priyanka Devi Sontosh | 57.5972 | 5.7597 | TB408 | 20/0 | Derrick
2025-09-29 | 2025-09-25 | 2025-10-03 | Sheetal Singh 1 | 37.5044 | 4.1672 | TB408 | 6/1 | Derrick
2025-09-29 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0 | Derrick+Crane
2025-09-29 | 2025-09-29 | 2025-10-08 | Shobha Devi | 66.3811 | 6.6381 | TB408 | 40/0 | Derrick
2025-09-29 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3 | Derrick
2025-09-29 | 2025-09-22 | 2025-09-30 | Sunny Construction | 67.8737 | 7.5415 | TB408 | 54/0 | Derrick
2025-09-29 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5 | Derrick
2025-09-29 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6 | Derrick
2025-09-30 | 2025-09-29 | 2025-10-18 | Chinta Devi | 143.6019 | 7.1801 | TB408 | 46/0 | Derrick
2025-09-30 | 2025-09-20 | 2025-09-30 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/1 | Derrick
2025-09-30 | 2025-09-30 | 2025-10-12 | Jirwa Devi | 37.5044 | 2.885 | TB408 | 30/2 | Derrick
2025-09-30 | 2025-09-27 | 2025-10-06 | Nirmal Mahto | 37.5044 | 3.7504 | TB408 | 35/5 | Derrick
2025-09-30 | 2025-09-25 | 2025-10-03 | Sheetal Singh 1 | 37.5044 | 4.1672 | TB408 | 6/1 | Derrick
2025-09-30 | 2025-09-29 | 2025-10-08 | Shobha Devi | 66.3811 | 6.6381 | TB408 | 40/0 | Derrick
2025-09-30 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3 | Derrick
2025-09-30 | 2025-09-22 | 2025-09-30 | Sunny Construction | 67.8737 | 7.5415 | TB408 | 54/0 | Derrick
2025-09-30 | 2025-09-30 | 2025-10-11 | Sunny Construction | 67.8737 | 5.6561 | TB408 | 55/0 | Derrick
2025-09-30 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6 | Derrick
2025-10-01 | 2025-09-29 | 2025-10-18 | Chinta Devi | 143.6019 | 7.1801 | TB408 | 46/0 | Derrick
2025-10-01 | 2025-09-30 | 2025-10-12 | Jirwa Devi | 37.5044 | 2.885 | TB408 | 30/2 | Derrick
2025-10-01 | 2025-09-27 | 2025-10-06 | Nirmal Mahto | 37.5044 | 3.7504 | TB408 | 35/5 | Derrick
2025-10-01 | 2025-09-25 | 2025-10-03 | Sheetal Singh 1 | 37.5044 | 4.1672 | TB408 | 6/1 | Derrick
2025-10-01 | 2025-09-29 | 2025-10-08 | Shobha Devi | 66.3811 | 6.6381 | TB408 | 40/0 | Derrick
2025-10-01 | 2025-09-30 | 2025-10-11 | Sunny Construction | 67.8737 | 5.6561 | TB408 | 55/0 | Derrick
2025-10-01 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6 | Derrick
2025-10-02 | 2025-09-29 | 2025-10-18 | Chinta Devi | 143.6019 | 7.1801 | TB408 | 46/0 | Derrick
2025-10-02 | 2025-09-30 | 2025-10-12 | Jirwa Devi | 37.5044 | 2.885 | TB408 | 30/2 | Derrick
2025-10-02 | 2025-09-27 | 2025-10-06 | Nirmal Mahto | 37.5044 | 3.7504 | TB408 | 35/5 | Derrick
2025-10-02 | 2025-09-25 | 2025-10-03 | Sheetal Singh 1 | 37.5044 | 4.1672 | TB408 | 6/1 | Derrick
2025-10-02 | 2025-09-29 | 2025-10-08 | Shobha Devi | 66.3811 | 6.6381 | TB408 | 40/0 | Derrick
2025-10-02 | 2025-09-30 | 2025-10-11 | Sunny Construction | 67.8737 | 5.6561 | TB408 | 55/0 | Derrick
2025-10-02 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6 | Derrick
2025-10-03 | 2025-09-29 | 2025-10-18 | Chinta Devi | 143.6019 | 7.1801 | TB408 | 46/0 | Derrick
2025-10-03 | 2025-09-30 | 2025-10-12 | Jirwa Devi | 37.5044 | 2.885 | TB408 | 30/2 | Derrick
2025-10-03 | 2025-09-27 | 2025-10-06 | Nirmal Mahto | 37.5044 | 3.7504 | TB408 | 35/5 | Derrick
2025-10-03 | 2025-10-03 | 2025-10-10 | Priyanka Devi Subodh | 37.5044 | 4.688 | TB408 | 10/1 | Derrick
2025-10-03 | 2025-09-25 | 2025-10-03 | Sheetal Singh 1 | 37.5044 | 4.1672 | TB408 | 6/1 | Derrick
2025-10-03 | 2025-09-29 | 2025-10-08 | Shobha Devi | 66.3811 | 6.6381 | TB408 | 40/0 | Derrick
2025-10-03 | 2025-09-30 | 2025-10-11 | Sunny Construction | 67.8737 | 5.6561 | TB408 | 55/0 | Derrick
2025-10-03 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6 | Derrick
2025-10-04 | 2025-09-29 | 2025-10-18 | Chinta Devi | 143.6019 | 7.1801 | TB408 | 46/0 | Derrick
2025-10-04 | 2025-09-30 | 2025-10-12 | Jirwa Devi | 37.5044 | 2.885 | TB408 | 30/2 | Derrick
2025-10-04 | 2025-09-27 | 2025-10-06 | Nirmal Mahto | 37.5044 | 3.7504 | TB408 | 35/5 | Derrick
2025-10-04 | 2025-10-03 | 2025-10-10 | Priyanka Devi Subodh | 37.5044 | 4.688 | TB408 | 10/1 | Derrick
2025-10-04 | 2025-09-29 | 2025-10-08 | Shobha Devi | 66.3811 | 6.6381 | TB408 | 40/0 | Derrick
2025-10-04 | 2025-09-30 | 2025-10-11 | Sunny Construction | 67.8737 | 5.6561 | TB408 | 55/0 | Derrick
2025-10-04 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6 | Derrick
2025-10-05 | 2025-09-29 | 2025-10-18 | Chinta Devi | 143.6019 | 7.1801 | TB408 | 46/0 | Derrick
2025-10-05 | 2025-09-30 | 2025-10-12 | Jirwa Devi | 37.5044 | 2.885 | TB408 | 30/2 | Derrick
2025-10-05 | 2025-09-27 | 2025-10-06 | Nirmal Mahto | 37.5044 | 3.7504 | TB408 | 35/5 | Derrick
2025-10-05 | 2025-10-03 | 2025-10-10 | Priyanka Devi Subodh | 37.5044 | 4.688 | TB408 | 10/1 | Derrick
2025-10-05 | 2025-09-29 | 2025-10-08 | Shobha Devi | 66.3811 | 6.6381 | TB408 | 40/0 | Derrick
2025-10-05 | 2025-09-30 | 2025-10-11 | Sunny Construction | 67.8737 | 5.6561 | TB408 | 55/0 | Derrick
2025-10-05 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6 | Derrick
2025-10-06 | 2025-09-29 | 2025-10-18 | Chinta Devi | 143.6019 | 7.1801 | TB408 | 46/0 | Derrick
2025-10-06 | 2025-09-30 | 2025-10-12 | Jirwa Devi | 37.5044 | 2.885 | TB408 | 30/2 | Derrick
2025-10-06 | 2025-09-27 | 2025-10-06 | Nirmal Mahto | 37.5044 | 3.7504 | TB408 | 35/5 | Derrick
2025-10-06 | 2025-10-03 | 2025-10-10 | Priyanka Devi Subodh | 37.5044 | 4.688 | TB408 | 10/1 | Derrick
2025-10-06 | 2025-09-29 | 2025-10-08 | Shobha Devi | 66.3811 | 6.6381 | TB408 | 40/0 | Derrick
2025-10-06 | 2025-09-30 | 2025-10-11 | Sunny Construction | 67.8737 | 5.6561 | TB408 | 55/0 | Derrick
2025-10-06 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6 | Derrick
2025-10-07 | 2025-09-29 | 2025-10-18 | Chinta Devi | 143.6019 | 7.1801 | TB408 | 46/0 | Derrick
2025-10-07 | 2025-09-30 | 2025-10-12 | Jirwa Devi | 37.5044 | 2.885 | TB408 | 30/2 | Derrick
2025-10-07 | 2025-10-07 | 2025-10-13 | Nirmal Mahto | 37.5044 | 5.3578 | TB408 | 35/4 | Derrick
2025-10-07 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-10-07 | 2025-10-03 | 2025-10-10 | Priyanka Devi Subodh | 37.5044 | 4.688 | TB408 | 10/1 | Derrick
2025-10-07 | 2025-09-29 | 2025-10-08 | Shobha Devi | 66.3811 | 6.6381 | TB408 | 40/0 | Derrick
2025-10-07 | 2025-09-30 | 2025-10-11 | Sunny Construction | 67.8737 | 5.6561 | TB408 | 55/0 | Derrick
2025-10-07 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6 | Derrick
2025-10-08 | 2025-09-29 | 2025-10-18 | Chinta Devi | 143.6019 | 7.1801 | TB408 | 46/0 | Derrick
2025-10-08 | 2025-09-30 | 2025-10-12 | Jirwa Devi | 37.5044 | 2.885 | TB408 | 30/2 | Derrick
2025-10-08 | 2025-10-07 | 2025-10-13 | Nirmal Mahto | 37.5044 | 5.3578 | TB408 | 35/4 | Derrick
2025-10-08 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-10-08 | 2025-10-03 | 2025-10-10 | Priyanka Devi Subodh | 37.5044 | 4.688 | TB408 | 10/1 | Derrick
2025-10-08 | 2025-09-29 | 2025-10-08 | Shobha Devi | 66.3811 | 6.6381 | TB408 | 40/0 | Derrick
2025-10-08 | 2025-09-30 | 2025-10-11 | Sunny Construction | 67.8737 | 5.6561 | TB408 | 55/0 | Derrick
2025-10-09 | 2025-09-29 | 2025-10-18 | Chinta Devi | 143.6019 | 7.1801 | TB408 | 46/0 | Derrick
2025-10-09 | 2025-09-30 | 2025-10-12 | Jirwa Devi | 37.5044 | 2.885 | TB408 | 30/2 | Derrick
2025-10-09 | 2025-10-07 | 2025-10-13 | Nirmal Mahto | 37.5044 | 5.3578 | TB408 | 35/4 | Derrick
2025-10-09 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-10-09 | 2025-10-03 | 2025-10-10 | Priyanka Devi Subodh | 37.5044 | 4.688 | TB408 | 10/1 | Derrick
2025-10-09 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-10-09 | 2025-09-30 | 2025-10-11 | Sunny Construction | 67.8737 | 5.6561 | TB408 | 55/0 | Derrick
2025-10-10 | 2025-09-29 | 2025-10-18 | Chinta Devi | 143.6019 | 7.1801 | TB408 | 46/0 | Derrick
2025-10-10 | 2025-10-10 | 2025-10-17 | Ganesh Sinha | 47.1844 | 5.898 | TB408 | 37/1 | Derrick
2025-10-10 | 2025-09-30 | 2025-10-12 | Jirwa Devi | 37.5044 | 2.885 | TB408 | 30/2 | Derrick
2025-10-10 | 2025-10-07 | 2025-10-13 | Nirmal Mahto | 37.5044 | 5.3578 | TB408 | 35/4 | Derrick
2025-10-10 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-10-10 | 2025-10-03 | 2025-10-10 | Priyanka Devi Subodh | 37.5044 | 4.688 | TB408 | 10/1 | Derrick
2025-10-10 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-10-10 | 2025-09-30 | 2025-10-11 | Sunny Construction | 67.8737 | 5.6561 | TB408 | 55/0 | Derrick
2025-10-10 | 2025-10-10 | 2025-10-27 | Vinay Construction | 37.5044 | 2.0836 | TB408 | 41/2 | Derrick
2025-10-11 | 2025-09-29 | 2025-10-18 | Chinta Devi | 143.6019 | 7.1801 | TB408 | 46/0 | Derrick
2025-10-11 | 2025-10-10 | 2025-10-17 | Ganesh Sinha | 47.1844 | 5.898 | TB408 | 37/1 | Derrick
2025-10-11 | 2025-09-30 | 2025-10-12 | Jirwa Devi | 37.5044 | 2.885 | TB408 | 30/2 | Derrick
2025-10-11 | 2025-10-07 | 2025-10-13 | Nirmal Mahto | 37.5044 | 5.3578 | TB408 | 35/4 | Derrick
2025-10-11 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-10-11 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-10-11 | 2025-09-30 | 2025-10-11 | Sunny Construction | 67.8737 | 5.6561 | TB408 | 55/0 | Derrick
2025-10-11 | 2025-10-10 | 2025-10-27 | Vinay Construction | 37.5044 | 2.0836 | TB408 | 41/2 | Derrick
2025-10-12 | 2025-09-29 | 2025-10-18 | Chinta Devi | 143.6019 | 7.1801 | TB408 | 46/0 | Derrick
2025-10-12 | 2025-10-10 | 2025-10-17 | Ganesh Sinha | 47.1844 | 5.898 | TB408 | 37/1 | Derrick
2025-10-12 | 2025-09-30 | 2025-10-12 | Jirwa Devi | 37.5044 | 2.885 | TB408 | 30/2 | Derrick
2025-10-12 | 2025-10-07 | 2025-10-13 | Nirmal Mahto | 37.5044 | 5.3578 | TB408 | 35/4 | Derrick
2025-10-12 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-10-12 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-10-12 | 2025-10-12 | 2025-10-14 | Sunny Construction | 37.5044 | 12.5015 | TB408 | 55/2 | Derrick
2025-10-12 | 2025-10-10 | 2025-10-27 | Vinay Construction | 37.5044 | 2.0836 | TB408 | 41/2 | Derrick
2025-10-13 | 2025-09-29 | 2025-10-18 | Chinta Devi | 143.6019 | 7.1801 | TB408 | 46/0 | Derrick
2025-10-13 | 2025-10-10 | 2025-10-17 | Ganesh Sinha | 47.1844 | 5.898 | TB408 | 37/1 | Derrick
2025-10-13 | 2025-10-13 | 2025-10-23 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 29/4 | Derrick
2025-10-13 | 2025-10-07 | 2025-10-13 | Nirmal Mahto | 37.5044 | 5.3578 | TB408 | 35/4 | Derrick
2025-10-13 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-10-13 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-10-13 | 2025-10-12 | 2025-10-14 | Sunny Construction | 37.5044 | 12.5015 | TB408 | 55/2 | Derrick
2025-10-13 | 2025-10-10 | 2025-10-27 | Vinay Construction | 37.5044 | 2.0836 | TB408 | 41/2 | Derrick
2025-10-14 | 2025-09-29 | 2025-10-18 | Chinta Devi | 143.6019 | 7.1801 | TB408 | 46/0 | Derrick
2025-10-14 | 2025-10-10 | 2025-10-17 | Ganesh Sinha | 47.1844 | 5.898 | TB408 | 37/1 | Derrick
2025-10-14 | 2025-10-13 | 2025-10-23 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 29/4 | Derrick
2025-10-14 | 2025-10-14 | 2025-10-22 | Nirmal Mahto | 57.5972 | 6.3997 | TB408 | 35/2 | Derrick
2025-10-14 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-10-14 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-10-14 | 2025-10-14 | 2025-10-18 | Shobha Devi | 67.8737 | 13.5747 | TB408 | 39/0 | Derrick
2025-10-14 | 2025-10-12 | 2025-10-14 | Sunny Construction | 37.5044 | 12.5015 | TB408 | 55/2 | Derrick
2025-10-14 | 2025-10-10 | 2025-10-27 | Vinay Construction | 37.5044 | 2.0836 | TB408 | 41/2 | Derrick
2025-10-15 | 2025-09-29 | 2025-10-18 | Chinta Devi | 143.6019 | 7.1801 | TB408 | 46/0 | Derrick
2025-10-15 | 2025-10-10 | 2025-10-17 | Ganesh Sinha | 47.1844 | 5.898 | TB408 | 37/1 | Derrick
2025-10-15 | 2025-10-13 | 2025-10-23 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 29/4 | Derrick
2025-10-15 | 2025-10-14 | 2025-10-22 | Nirmal Mahto | 57.5972 | 6.3997 | TB408 | 35/2 | Derrick
2025-10-15 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-10-15 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-10-15 | 2025-10-14 | 2025-10-18 | Shobha Devi | 67.8737 | 13.5747 | TB408 | 39/0 | Derrick
2025-10-15 | 2025-10-10 | 2025-10-27 | Vinay Construction | 37.5044 | 2.0836 | TB408 | 41/2 | Derrick
2025-10-16 | 2025-09-29 | 2025-10-18 | Chinta Devi | 143.6019 | 7.1801 | TB408 | 46/0 | Derrick
2025-10-16 | 2025-10-10 | 2025-10-17 | Ganesh Sinha | 47.1844 | 5.898 | TB408 | 37/1 | Derrick
2025-10-16 | 2025-10-13 | 2025-10-23 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 29/4 | Derrick
2025-10-16 | 2025-10-14 | 2025-10-22 | Nirmal Mahto | 57.5972 | 6.3997 | TB408 | 35/2 | Derrick
2025-10-16 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-10-16 | 2025-10-16 | 2025-10-26 | Sanjeev Kumar | 67.8737 | 6.1703 | TB408 | 35/0 | Derrick
2025-10-16 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-10-16 | 2025-10-14 | 2025-10-18 | Shobha Devi | 67.8737 | 13.5747 | TB408 | 39/0 | Derrick
2025-10-16 | 2025-10-10 | 2025-10-27 | Vinay Construction | 37.5044 | 2.0836 | TB408 | 41/2 | Derrick
2025-10-17 | 2025-09-29 | 2025-10-18 | Chinta Devi | 143.6019 | 7.1801 | TB408 | 46/0 | Derrick
2025-10-17 | 2025-10-17 | 2025-10-24 | Devi Construction | 37.5044 | 4.688 | TB408 | 11/4 | Derrick
2025-10-17 | 2025-10-10 | 2025-10-17 | Ganesh Sinha | 47.1844 | 5.898 | TB408 | 37/1 | Derrick
2025-10-17 | 2025-10-13 | 2025-10-23 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 29/4 | Derrick
2025-10-17 | 2025-10-14 | 2025-10-22 | Nirmal Mahto | 57.5972 | 6.3997 | TB408 | 35/2 | Derrick
2025-10-17 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-10-17 | 2025-10-16 | 2025-10-26 | Sanjeev Kumar | 67.8737 | 6.1703 | TB408 | 35/0 | Derrick
2025-10-17 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-10-17 | 2025-10-14 | 2025-10-18 | Shobha Devi | 67.8737 | 13.5747 | TB408 | 39/0 | Derrick
2025-10-17 | 2025-10-10 | 2025-10-27 | Vinay Construction | 37.5044 | 2.0836 | TB408 | 41/2 | Derrick
2025-10-18 | 2025-09-29 | 2025-10-18 | Chinta Devi | 143.6019 | 7.1801 | TB408 | 46/0 | Derrick
2025-10-18 | 2025-10-18 | 2025-10-31 | Chinta Devi | 94.2199 | 6.73 | TB408 | 44/8 | Derrick
2025-10-18 | 2025-10-17 | 2025-10-24 | Devi Construction | 37.5044 | 4.688 | TB408 | 11/4 | Derrick
2025-10-18 | 2025-10-18 | 2025-10-24 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 37/2 | Derrick
2025-10-18 | 2025-10-13 | 2025-10-23 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 29/4 | Derrick
2025-10-18 | 2025-10-14 | 2025-10-22 | Nirmal Mahto | 57.5972 | 6.3997 | TB408 | 35/2 | Derrick
2025-10-18 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-10-18 | 2025-10-16 | 2025-10-26 | Sanjeev Kumar | 67.8737 | 6.1703 | TB408 | 35/0 | Derrick
2025-10-18 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-10-18 | 2025-10-14 | 2025-10-18 | Shobha Devi | 67.8737 | 13.5747 | TB408 | 39/0 | Derrick
2025-10-18 | 2025-10-18 | 2025-10-22 | Shobha Devi | 37.5044 | 7.5009 | TB408 | 39/1 | Derrick
2025-10-18 | 2025-10-10 | 2025-10-27 | Vinay Construction | 37.5044 | 2.0836 | TB408 | 41/2 | Derrick
2025-10-19 | 2025-10-18 | 2025-10-31 | Chinta Devi | 94.2199 | 6.73 | TB408 | 44/8 | Derrick
2025-10-19 | 2025-10-17 | 2025-10-24 | Devi Construction | 37.5044 | 4.688 | TB408 | 11/4 | Derrick
2025-10-19 | 2025-10-18 | 2025-10-24 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 37/2 | Derrick
2025-10-19 | 2025-10-13 | 2025-10-23 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 29/4 | Derrick
2025-10-19 | 2025-10-14 | 2025-10-22 | Nirmal Mahto | 57.5972 | 6.3997 | TB408 | 35/2 | Derrick
2025-10-19 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-10-19 | 2025-10-16 | 2025-10-26 | Sanjeev Kumar | 67.8737 | 6.1703 | TB408 | 35/0 | Derrick
2025-10-19 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-10-19 | 2025-10-18 | 2025-10-22 | Shobha Devi | 37.5044 | 7.5009 | TB408 | 39/1 | Derrick
2025-10-19 | 2025-10-10 | 2025-10-27 | Vinay Construction | 37.5044 | 2.0836 | TB408 | 41/2 | Derrick
2025-10-20 | 2025-10-18 | 2025-10-31 | Chinta Devi | 94.2199 | 6.73 | TB408 | 44/8 | Derrick
2025-10-20 | 2025-10-17 | 2025-10-24 | Devi Construction | 37.5044 | 4.688 | TB408 | 11/4 | Derrick
2025-10-20 | 2025-10-18 | 2025-10-24 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 37/2 | Derrick
2025-10-20 | 2025-10-13 | 2025-10-23 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 29/4 | Derrick
2025-10-20 | 2025-10-14 | 2025-10-22 | Nirmal Mahto | 57.5972 | 6.3997 | TB408 | 35/2 | Derrick
2025-10-20 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-10-20 | 2025-10-16 | 2025-10-26 | Sanjeev Kumar | 67.8737 | 6.1703 | TB408 | 35/0 | Derrick
2025-10-20 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-10-20 | 2025-10-18 | 2025-10-22 | Shobha Devi | 37.5044 | 7.5009 | TB408 | 39/1 | Derrick
2025-10-20 | 2025-10-20 | 2025-10-31 | Shri Shyam Construction | 37.5044 | 3.1254 | TB408 | 19/2 | Derrick
2025-10-20 | 2025-10-10 | 2025-10-27 | Vinay Construction | 37.5044 | 2.0836 | TB408 | 41/2 | Derrick
2025-10-21 | 2025-10-18 | 2025-10-31 | Chinta Devi | 94.2199 | 6.73 | TB408 | 44/8 | Derrick
2025-10-21 | 2025-10-17 | 2025-10-24 | Devi Construction | 37.5044 | 4.688 | TB408 | 11/4 | Derrick
2025-10-21 | 2025-10-18 | 2025-10-24 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 37/2 | Derrick
2025-10-21 | 2025-10-13 | 2025-10-23 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 29/4 | Derrick
2025-10-21 | 2025-10-14 | 2025-10-22 | Nirmal Mahto | 57.5972 | 6.3997 | TB408 | 35/2 | Derrick
2025-10-21 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-10-21 | 2025-10-16 | 2025-10-26 | Sanjeev Kumar | 67.8737 | 6.1703 | TB408 | 35/0 | Derrick
2025-10-21 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-10-21 | 2025-10-18 | 2025-10-22 | Shobha Devi | 37.5044 | 7.5009 | TB408 | 39/1 | Derrick
2025-10-21 | 2025-10-20 | 2025-10-31 | Shri Shyam Construction | 37.5044 | 3.1254 | TB408 | 19/2 | Derrick
2025-10-21 | 2025-10-10 | 2025-10-27 | Vinay Construction | 37.5044 | 2.0836 | TB408 | 41/2 | Derrick
2025-10-22 | 2025-10-18 | 2025-10-31 | Chinta Devi | 94.2199 | 6.73 | TB408 | 44/8 | Derrick
2025-10-22 | 2025-10-17 | 2025-10-24 | Devi Construction | 37.5044 | 4.688 | TB408 | 11/4 | Derrick
2025-10-22 | 2025-10-18 | 2025-10-24 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 37/2 | Derrick
2025-10-22 | 2025-10-13 | 2025-10-23 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 29/4 | Derrick
2025-10-22 | 2025-10-14 | 2025-10-22 | Nirmal Mahto | 57.5972 | 6.3997 | TB408 | 35/2 | Derrick
2025-10-22 | 2025-10-22 | 2025-10-31 | Nirmal Mahto | 47.1844 | 4.7184 | TB408 | 35/1 | Derrick
2025-10-22 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-10-22 | 2025-10-16 | 2025-10-26 | Sanjeev Kumar | 67.8737 | 6.1703 | TB408 | 35/0 | Derrick
2025-10-22 | 2025-10-22 | 2025-11-08 | Santosh Singh | 66.3811 | 3.6878 | TB408 | 33/0 | Derrick
2025-10-22 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-10-22 | 2025-10-18 | 2025-10-22 | Shobha Devi | 37.5044 | 7.5009 | TB408 | 39/1 | Derrick
2025-10-22 | 2025-10-22 | 2025-10-26 | Shobha Devi | 47.1844 | 9.4369 | TB408 | 38/4 | Derrick
2025-10-22 | 2025-10-20 | 2025-10-31 | Shri Shyam Construction | 37.5044 | 3.1254 | TB408 | 19/2 | Derrick
2025-10-22 | 2025-10-10 | 2025-10-27 | Vinay Construction | 37.5044 | 2.0836 | TB408 | 41/2 | Derrick
2025-10-23 | 2025-10-18 | 2025-10-31 | Chinta Devi | 94.2199 | 6.73 | TB408 | 44/8 | Derrick
2025-10-23 | 2025-10-17 | 2025-10-24 | Devi Construction | 37.5044 | 4.688 | TB408 | 11/4 | Derrick
2025-10-23 | 2025-10-18 | 2025-10-24 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 37/2 | Derrick
2025-10-23 | 2025-10-13 | 2025-10-23 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 29/4 | Derrick
2025-10-23 | 2025-10-22 | 2025-10-31 | Nirmal Mahto | 47.1844 | 4.7184 | TB408 | 35/1 | Derrick
2025-10-23 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-10-23 | 2025-10-16 | 2025-10-26 | Sanjeev Kumar | 67.8737 | 6.1703 | TB408 | 35/0 | Derrick
2025-10-23 | 2025-10-22 | 2025-11-08 | Santosh Singh | 66.3811 | 3.6878 | TB408 | 33/0 | Derrick
2025-10-23 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-10-23 | 2025-10-22 | 2025-10-26 | Shobha Devi | 47.1844 | 9.4369 | TB408 | 38/4 | Derrick
2025-10-23 | 2025-10-20 | 2025-10-31 | Shri Shyam Construction | 37.5044 | 3.1254 | TB408 | 19/2 | Derrick
2025-10-23 | 2025-10-10 | 2025-10-27 | Vinay Construction | 37.5044 | 2.0836 | TB408 | 41/2 | Derrick
2025-10-24 | 2025-10-18 | 2025-10-31 | Chinta Devi | 94.2199 | 6.73 | TB408 | 44/8 | Derrick
2025-10-24 | 2025-10-17 | 2025-10-24 | Devi Construction | 37.5044 | 4.688 | TB408 | 11/4 | Derrick
2025-10-24 | 2025-10-18 | 2025-10-24 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 37/2 | Derrick
2025-10-24 | 2025-10-22 | 2025-10-31 | Nirmal Mahto | 47.1844 | 4.7184 | TB408 | 35/1 | Derrick
2025-10-24 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-10-24 | 2025-10-16 | 2025-10-26 | Sanjeev Kumar | 67.8737 | 6.1703 | TB408 | 35/0 | Derrick
2025-10-24 | 2025-10-22 | 2025-11-08 | Santosh Singh | 66.3811 | 3.6878 | TB408 | 33/0 | Derrick
2025-10-24 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-10-24 | 2025-10-22 | 2025-10-26 | Shobha Devi | 47.1844 | 9.4369 | TB408 | 38/4 | Derrick
2025-10-24 | 2025-10-20 | 2025-10-31 | Shri Shyam Construction | 37.5044 | 3.1254 | TB408 | 19/2 | Derrick
2025-10-24 | 2025-10-10 | 2025-10-27 | Vinay Construction | 37.5044 | 2.0836 | TB408 | 41/2 | Derrick
2025-10-25 | 2025-10-18 | 2025-10-31 | Chinta Devi | 94.2199 | 6.73 | TB408 | 44/8 | Derrick
2025-10-25 | 2025-10-25 | 2025-11-08 | Devi Construction | 100.968 | 6.7312 | TB408 | 4/0 | Derrick
2025-10-25 | 2025-10-25 | 2025-10-30 | Ganesh Sinha | 37.5044 | 6.2507 | TB408 | 37/3 | Derrick
2025-10-25 | 2025-10-22 | 2025-10-31 | Nirmal Mahto | 47.1844 | 4.7184 | TB408 | 35/1 | Derrick
2025-10-25 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-10-25 | 2025-10-16 | 2025-10-26 | Sanjeev Kumar | 67.8737 | 6.1703 | TB408 | 35/0 | Derrick
2025-10-25 | 2025-10-22 | 2025-11-08 | Santosh Singh | 66.3811 | 3.6878 | TB408 | 33/0 | Derrick
2025-10-25 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-10-25 | 2025-10-22 | 2025-10-26 | Shobha Devi | 47.1844 | 9.4369 | TB408 | 38/4 | Derrick
2025-10-25 | 2025-10-20 | 2025-10-31 | Shri Shyam Construction | 37.5044 | 3.1254 | TB408 | 19/2 | Derrick
2025-10-25 | 2025-10-10 | 2025-10-27 | Vinay Construction | 37.5044 | 2.0836 | TB408 | 41/2 | Derrick
2025-10-26 | 2025-10-18 | 2025-10-31 | Chinta Devi | 94.2199 | 6.73 | TB408 | 44/8 | Derrick
2025-10-26 | 2025-10-25 | 2025-11-08 | Devi Construction | 100.968 | 6.7312 | TB408 | 4/0 | Derrick
2025-10-26 | 2025-10-25 | 2025-10-30 | Ganesh Sinha | 37.5044 | 6.2507 | TB408 | 37/3 | Derrick
2025-10-26 | 2025-10-22 | 2025-10-31 | Nirmal Mahto | 47.1844 | 4.7184 | TB408 | 35/1 | Derrick
2025-10-26 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-10-26 | 2025-10-16 | 2025-10-26 | Sanjeev Kumar | 67.8737 | 6.1703 | TB408 | 35/0 | Derrick
2025-10-26 | 2025-10-22 | 2025-11-08 | Santosh Singh | 66.3811 | 3.6878 | TB408 | 33/0 | Derrick
2025-10-26 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-10-26 | 2025-10-22 | 2025-10-26 | Shobha Devi | 47.1844 | 9.4369 | TB408 | 38/4 | Derrick
2025-10-26 | 2025-10-20 | 2025-10-31 | Shri Shyam Construction | 37.5044 | 3.1254 | TB408 | 19/2 | Derrick
2025-10-26 | 2025-10-10 | 2025-10-27 | Vinay Construction | 37.5044 | 2.0836 | TB408 | 41/2 | Derrick
2025-10-27 | 2025-10-18 | 2025-10-31 | Chinta Devi | 94.2199 | 6.73 | TB408 | 44/8 | Derrick
2025-10-27 | 2025-10-27 | 2025-11-09 | Chinta Devi | 66.3811 | 4.7415 | TB408 | 42/0 | Derrick
2025-10-27 | 2025-10-25 | 2025-11-08 | Devi Construction | 100.968 | 6.7312 | TB408 | 4/0 | Derrick
2025-10-27 | 2025-10-25 | 2025-10-30 | Ganesh Sinha | 37.5044 | 6.2507 | TB408 | 37/3 | Derrick
2025-10-27 | 2025-10-22 | 2025-10-31 | Nirmal Mahto | 47.1844 | 4.7184 | TB408 | 35/1 | Derrick
2025-10-27 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-10-27 | 2025-10-27 | 2025-11-04 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 34/4 | Derrick
2025-10-27 | 2025-10-22 | 2025-11-08 | Santosh Singh | 66.3811 | 3.6878 | TB408 | 33/0 | Derrick
2025-10-27 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-10-27 | 2025-10-27 | 2025-10-31 | Shobha Devi | 67.8737 | 13.5747 | TB408 | 38/0 | Derrick
2025-10-27 | 2025-10-20 | 2025-10-31 | Shri Shyam Construction | 37.5044 | 3.1254 | TB408 | 19/2 | Derrick
2025-10-27 | 2025-10-10 | 2025-10-27 | Vinay Construction | 37.5044 | 2.0836 | TB408 | 41/2 | Derrick
2025-10-27 | 2025-10-27 | 2025-11-09 | Vinay Construction | 45.413 | 3.2438 | TB408 | 42/2 | Derrick
2025-10-28 | 2025-10-18 | 2025-10-31 | Chinta Devi | 94.2199 | 6.73 | TB408 | 44/8 | Derrick
2025-10-28 | 2025-10-27 | 2025-11-09 | Chinta Devi | 66.3811 | 4.7415 | TB408 | 42/0 | Derrick
2025-10-28 | 2025-10-25 | 2025-11-08 | Devi Construction | 100.968 | 6.7312 | TB408 | 4/0 | Derrick
2025-10-28 | 2025-10-25 | 2025-10-30 | Ganesh Sinha | 37.5044 | 6.2507 | TB408 | 37/3 | Derrick
2025-10-28 | 2025-10-22 | 2025-10-31 | Nirmal Mahto | 47.1844 | 4.7184 | TB408 | 35/1 | Derrick
2025-10-28 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-10-28 | 2025-10-27 | 2025-11-04 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 34/4 | Derrick
2025-10-28 | 2025-10-22 | 2025-11-08 | Santosh Singh | 66.3811 | 3.6878 | TB408 | 33/0 | Derrick
2025-10-28 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-10-28 | 2025-10-27 | 2025-10-31 | Shobha Devi | 67.8737 | 13.5747 | TB408 | 38/0 | Derrick
2025-10-28 | 2025-10-20 | 2025-10-31 | Shri Shyam Construction | 37.5044 | 3.1254 | TB408 | 19/2 | Derrick
2025-10-28 | 2025-10-27 | 2025-11-09 | Vinay Construction | 45.413 | 3.2438 | TB408 | 42/2 | Derrick
2025-10-29 | 2025-10-18 | 2025-10-31 | Chinta Devi | 94.2199 | 6.73 | TB408 | 44/8 | Derrick
2025-10-29 | 2025-10-27 | 2025-11-09 | Chinta Devi | 66.3811 | 4.7415 | TB408 | 42/0 | Derrick
2025-10-29 | 2025-10-25 | 2025-11-08 | Devi Construction | 100.968 | 6.7312 | TB408 | 4/0 | Derrick
2025-10-29 | 2025-10-25 | 2025-10-30 | Ganesh Sinha | 37.5044 | 6.2507 | TB408 | 37/3 | Derrick
2025-10-29 | 2025-10-29 | 2025-11-16 | Kamlesh Kumar | 70.7017 | 3.7211 | TB408 | 5/0 | Derrick
2025-10-29 | 2025-10-22 | 2025-10-31 | Nirmal Mahto | 47.1844 | 4.7184 | TB408 | 35/1 | Derrick
2025-10-29 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-10-29 | 2025-10-27 | 2025-11-04 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 34/4 | Derrick
2025-10-29 | 2025-10-22 | 2025-11-08 | Santosh Singh | 66.3811 | 3.6878 | TB408 | 33/0 | Derrick
2025-10-29 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-10-29 | 2025-10-27 | 2025-10-31 | Shobha Devi | 67.8737 | 13.5747 | TB408 | 38/0 | Derrick
2025-10-29 | 2025-10-20 | 2025-10-31 | Shri Shyam Construction | 37.5044 | 3.1254 | TB408 | 19/2 | Derrick
2025-10-29 | 2025-10-27 | 2025-11-09 | Vinay Construction | 45.413 | 3.2438 | TB408 | 42/2 | Derrick
2025-10-30 | 2025-10-18 | 2025-10-31 | Chinta Devi | 94.2199 | 6.73 | TB408 | 44/8 | Derrick
2025-10-30 | 2025-10-27 | 2025-11-09 | Chinta Devi | 66.3811 | 4.7415 | TB408 | 42/0 | Derrick
2025-10-30 | 2025-10-25 | 2025-11-08 | Devi Construction | 100.968 | 6.7312 | TB408 | 4/0 | Derrick
2025-10-30 | 2025-10-25 | 2025-10-30 | Ganesh Sinha | 37.5044 | 6.2507 | TB408 | 37/3 | Derrick
2025-10-30 | 2025-10-29 | 2025-11-16 | Kamlesh Kumar | 70.7017 | 3.7211 | TB408 | 5/0 | Derrick
2025-10-30 | 2025-10-22 | 2025-10-31 | Nirmal Mahto | 47.1844 | 4.7184 | TB408 | 35/1 | Derrick
2025-10-30 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-10-30 | 2025-10-27 | 2025-11-04 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 34/4 | Derrick
2025-10-30 | 2025-10-22 | 2025-11-08 | Santosh Singh | 66.3811 | 3.6878 | TB408 | 33/0 | Derrick
2025-10-30 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-10-30 | 2025-10-27 | 2025-10-31 | Shobha Devi | 67.8737 | 13.5747 | TB408 | 38/0 | Derrick
2025-10-30 | 2025-10-20 | 2025-10-31 | Shri Shyam Construction | 37.5044 | 3.1254 | TB408 | 19/2 | Derrick
2025-10-30 | 2025-10-27 | 2025-11-09 | Vinay Construction | 45.413 | 3.2438 | TB408 | 42/2 | Derrick
2025-10-31 | 2025-10-18 | 2025-10-31 | Chinta Devi | 94.2199 | 6.73 | TB408 | 44/8 | Derrick
2025-10-31 | 2025-10-27 | 2025-11-09 | Chinta Devi | 66.3811 | 4.7415 | TB408 | 42/0 | Derrick
2025-10-31 | 2025-10-25 | 2025-11-08 | Devi Construction | 100.968 | 6.7312 | TB408 | 4/0 | Derrick
2025-10-31 | 2025-10-31 | 2025-11-07 | Ganesh Sinha | 37.5044 | 4.688 | TB408 | 32/3 | Derrick
2025-10-31 | 2025-10-29 | 2025-11-16 | Kamlesh Kumar | 70.7017 | 3.7211 | TB408 | 5/0 | Derrick
2025-10-31 | 2025-10-22 | 2025-10-31 | Nirmal Mahto | 47.1844 | 4.7184 | TB408 | 35/1 | Derrick
2025-10-31 | 2025-10-31 | 2025-11-07 | Nirmal Mahto | 47.1844 | 5.898 | TB408 | 34/1 | Derrick
2025-10-31 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-10-31 | 2025-10-27 | 2025-11-04 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 34/4 | Derrick
2025-10-31 | 2025-10-22 | 2025-11-08 | Santosh Singh | 66.3811 | 3.6878 | TB408 | 33/0 | Derrick
2025-10-31 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-10-31 | 2025-10-27 | 2025-10-31 | Shobha Devi | 67.8737 | 13.5747 | TB408 | 38/0 | Derrick
2025-10-31 | 2025-10-20 | 2025-10-31 | Shri Shyam Construction | 37.5044 | 3.1254 | TB408 | 19/2 | Derrick
2025-10-31 | 2025-10-27 | 2025-11-09 | Vinay Construction | 45.413 | 3.2438 | TB408 | 42/2 | Derrick
2025-11-01 | 2025-10-27 | 2025-11-09 | Chinta Devi | 66.3811 | 4.7415 | TB408 | 42/0 | Derrick
2025-11-01 | 2025-10-25 | 2025-11-08 | Devi Construction | 100.968 | 6.7312 | TB408 | 4/0 | Derrick
2025-11-01 | 2025-10-31 | 2025-11-07 | Ganesh Sinha | 37.5044 | 4.688 | TB408 | 32/3 | Derrick
2025-11-01 | 2025-10-29 | 2025-11-16 | Kamlesh Kumar | 70.7017 | 3.7211 | TB408 | 5/0 | Derrick
2025-11-01 | 2025-10-31 | 2025-11-07 | Nirmal Mahto | 47.1844 | 5.898 | TB408 | 34/1 | Derrick
2025-11-01 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-11-01 | 2025-10-27 | 2025-11-04 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 34/4 | Derrick
2025-11-01 | 2025-10-22 | 2025-11-08 | Santosh Singh | 66.3811 | 3.6878 | TB408 | 33/0 | Derrick
2025-11-01 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-11-01 | 2025-11-01 | 2025-11-06 | Shobha Devi | 45.413 | 7.5688 | TB408 | 40/1 | Derrick
2025-11-01 | 2025-10-27 | 2025-11-09 | Vinay Construction | 45.413 | 3.2438 | TB408 | 42/2 | Derrick
2025-11-02 | 2025-10-27 | 2025-11-09 | Chinta Devi | 66.3811 | 4.7415 | TB408 | 42/0 | Derrick
2025-11-02 | 2025-10-25 | 2025-11-08 | Devi Construction | 100.968 | 6.7312 | TB408 | 4/0 | Derrick
2025-11-02 | 2025-10-31 | 2025-11-07 | Ganesh Sinha | 37.5044 | 4.688 | TB408 | 32/3 | Derrick
2025-11-02 | 2025-10-29 | 2025-11-16 | Kamlesh Kumar | 70.7017 | 3.7211 | TB408 | 5/0 | Derrick
2025-11-02 | 2025-10-31 | 2025-11-07 | Nirmal Mahto | 47.1844 | 5.898 | TB408 | 34/1 | Derrick
2025-11-02 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-11-02 | 2025-10-27 | 2025-11-04 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 34/4 | Derrick
2025-11-02 | 2025-10-22 | 2025-11-08 | Santosh Singh | 66.3811 | 3.6878 | TB408 | 33/0 | Derrick
2025-11-02 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-11-02 | 2025-11-01 | 2025-11-06 | Shobha Devi | 45.413 | 7.5688 | TB408 | 40/1 | Derrick
2025-11-02 | 2025-10-27 | 2025-11-09 | Vinay Construction | 45.413 | 3.2438 | TB408 | 42/2 | Derrick
2025-11-03 | 2025-10-27 | 2025-11-09 | Chinta Devi | 66.3811 | 4.7415 | TB408 | 42/0 | Derrick
2025-11-03 | 2025-10-25 | 2025-11-08 | Devi Construction | 100.968 | 6.7312 | TB408 | 4/0 | Derrick
2025-11-03 | 2025-10-31 | 2025-11-07 | Ganesh Sinha | 37.5044 | 4.688 | TB408 | 32/3 | Derrick
2025-11-03 | 2025-10-29 | 2025-11-16 | Kamlesh Kumar | 70.7017 | 3.7211 | TB408 | 5/0 | Derrick
2025-11-03 | 2025-10-31 | 2025-11-07 | Nirmal Mahto | 47.1844 | 5.898 | TB408 | 34/1 | Derrick
2025-11-03 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-11-03 | 2025-10-27 | 2025-11-04 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 34/4 | Derrick
2025-11-03 | 2025-10-22 | 2025-11-08 | Santosh Singh | 66.3811 | 3.6878 | TB408 | 33/0 | Derrick
2025-11-03 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-11-03 | 2025-11-01 | 2025-11-06 | Shobha Devi | 45.413 | 7.5688 | TB408 | 40/1 | Derrick
2025-11-03 | 2025-10-27 | 2025-11-09 | Vinay Construction | 45.413 | 3.2438 | TB408 | 42/2 | Derrick
2025-11-04 | 2025-10-27 | 2025-11-09 | Chinta Devi | 66.3811 | 4.7415 | TB408 | 42/0 | Derrick
2025-11-04 | 2025-10-25 | 2025-11-08 | Devi Construction | 100.968 | 6.7312 | TB408 | 4/0 | Derrick
2025-11-04 | 2025-10-31 | 2025-11-07 | Ganesh Sinha | 37.5044 | 4.688 | TB408 | 32/3 | Derrick
2025-11-04 | 2025-10-29 | 2025-11-16 | Kamlesh Kumar | 70.7017 | 3.7211 | TB408 | 5/0 | Derrick
2025-11-04 | 2025-10-31 | 2025-11-07 | Nirmal Mahto | 47.1844 | 5.898 | TB408 | 34/1 | Derrick
2025-11-04 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-11-04 | 2025-10-27 | 2025-11-04 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 34/4 | Derrick
2025-11-04 | 2025-10-22 | 2025-11-08 | Santosh Singh | 66.3811 | 3.6878 | TB408 | 33/0 | Derrick
2025-11-04 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-11-04 | 2025-11-01 | 2025-11-06 | Shobha Devi | 45.413 | 7.5688 | TB408 | 40/1 | Derrick
2025-11-04 | 2025-10-27 | 2025-11-09 | Vinay Construction | 45.413 | 3.2438 | TB408 | 42/2 | Derrick
2025-11-05 | 2025-10-27 | 2025-11-09 | Chinta Devi | 66.3811 | 4.7415 | TB408 | 42/0 | Derrick
2025-11-05 | 2025-10-25 | 2025-11-08 | Devi Construction | 100.968 | 6.7312 | TB408 | 4/0 | Derrick
2025-11-05 | 2025-10-31 | 2025-11-07 | Ganesh Sinha | 37.5044 | 4.688 | TB408 | 32/3 | Derrick
2025-11-05 | 2025-10-29 | 2025-11-16 | Kamlesh Kumar | 70.7017 | 3.7211 | TB408 | 5/0 | Derrick
2025-11-05 | 2025-10-31 | 2025-11-07 | Nirmal Mahto | 47.1844 | 5.898 | TB408 | 34/1 | Derrick
2025-11-05 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-11-05 | 2025-11-05 | 2025-11-11 | Sanjeev Kumar | 37.5044 | 5.3578 | TB408 | 33/1 | Derrick
2025-11-05 | 2025-10-22 | 2025-11-08 | Santosh Singh | 66.3811 | 3.6878 | TB408 | 33/0 | Derrick
2025-11-05 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-11-05 | 2025-11-01 | 2025-11-06 | Shobha Devi | 45.413 | 7.5688 | TB408 | 40/1 | Derrick
2025-11-05 | 2025-10-27 | 2025-11-09 | Vinay Construction | 45.413 | 3.2438 | TB408 | 42/2 | Derrick
2025-11-06 | 2025-10-27 | 2025-11-09 | Chinta Devi | 66.3811 | 4.7415 | TB408 | 42/0 | Derrick
2025-11-06 | 2025-10-25 | 2025-11-08 | Devi Construction | 100.968 | 6.7312 | TB408 | 4/0 | Derrick
2025-11-06 | 2025-10-31 | 2025-11-07 | Ganesh Sinha | 37.5044 | 4.688 | TB408 | 32/3 | Derrick
2025-11-06 | 2025-10-29 | 2025-11-16 | Kamlesh Kumar | 70.7017 | 3.7211 | TB408 | 5/0 | Derrick
2025-11-06 | 2025-10-31 | 2025-11-07 | Nirmal Mahto | 47.1844 | 5.898 | TB408 | 34/1 | Derrick
2025-11-06 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-11-06 | 2025-11-05 | 2025-11-11 | Sanjeev Kumar | 37.5044 | 5.3578 | TB408 | 33/1 | Derrick
2025-11-06 | 2025-10-22 | 2025-11-08 | Santosh Singh | 66.3811 | 3.6878 | TB408 | 33/0 | Derrick
2025-11-06 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-11-06 | 2025-11-01 | 2025-11-06 | Shobha Devi | 45.413 | 7.5688 | TB408 | 40/1 | Derrick
2025-11-06 | 2025-10-27 | 2025-11-09 | Vinay Construction | 45.413 | 3.2438 | TB408 | 42/2 | Derrick
2025-11-07 | 2025-10-27 | 2025-11-09 | Chinta Devi | 66.3811 | 4.7415 | TB408 | 42/0 | Derrick
2025-11-07 | 2025-10-25 | 2025-11-08 | Devi Construction | 100.968 | 6.7312 | TB408 | 4/0 | Derrick
2025-11-07 | 2025-10-31 | 2025-11-07 | Ganesh Sinha | 37.5044 | 4.688 | TB408 | 32/3 | Derrick
2025-11-07 | 2025-10-29 | 2025-11-16 | Kamlesh Kumar | 70.7017 | 3.7211 | TB408 | 5/0 | Derrick
2025-11-07 | 2025-10-31 | 2025-11-07 | Nirmal Mahto | 47.1844 | 5.898 | TB408 | 34/1 | Derrick
2025-11-07 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-11-07 | 2025-11-05 | 2025-11-11 | Sanjeev Kumar | 37.5044 | 5.3578 | TB408 | 33/1 | Derrick
2025-11-07 | 2025-10-22 | 2025-11-08 | Santosh Singh | 66.3811 | 3.6878 | TB408 | 33/0 | Derrick
2025-11-07 | 2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-11-07 | 2025-10-27 | 2025-11-09 | Vinay Construction | 45.413 | 3.2438 | TB408 | 42/2 | Derrick
2025-11-08 | 2025-10-27 | 2025-11-09 | Chinta Devi | 66.3811 | 4.7415 | TB408 | 42/0 | Derrick
2025-11-08 | 2025-10-25 | 2025-11-08 | Devi Construction | 100.968 | 6.7312 | TB408 | 4/0 | Derrick
2025-11-08 | 2025-11-08 | 2025-11-13 | Ganesh Sinha | 38.8476 | 6.4746 | TB408 | 32/2 | Derrick
2025-11-08 | 2025-11-08 | 2025-11-18 | Jirwa Devi | 66.3811 | 6.0346 | TB408 | 32/0 | Derrick
2025-11-08 | 2025-10-29 | 2025-11-16 | Kamlesh Kumar | 70.7017 | 3.7211 | TB408 | 5/0 | Derrick
2025-11-08 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-11-08 | 2025-11-05 | 2025-11-11 | Sanjeev Kumar | 37.5044 | 5.3578 | TB408 | 33/1 | Derrick
2025-11-08 | 2025-10-22 | 2025-11-08 | Santosh Singh | 66.3811 | 3.6878 | TB408 | 33/0 | Derrick
2025-11-08 | 2025-11-08 | 2025-11-14 | Shobha Devi | 37.5044 | 5.3578 | TB408 | 42/4 | Derrick
2025-11-08 | 2025-10-27 | 2025-11-09 | Vinay Construction | 45.413 | 3.2438 | TB408 | 42/2 | Derrick
2025-11-09 | 2025-10-27 | 2025-11-09 | Chinta Devi | 66.3811 | 4.7415 | TB408 | 42/0 | Derrick
2025-11-09 | 2025-11-09 | 2025-11-18 | Devi Construction | 57.5972 | 5.7597 | TB408 | 8/0 | Derrick
2025-11-09 | 2025-11-08 | 2025-11-13 | Ganesh Sinha | 38.8476 | 6.4746 | TB408 | 32/2 | Derrick
2025-11-09 | 2025-11-08 | 2025-11-18 | Jirwa Devi | 66.3811 | 6.0346 | TB408 | 32/0 | Derrick
2025-11-09 | 2025-10-29 | 2025-11-16 | Kamlesh Kumar | 70.7017 | 3.7211 | TB408 | 5/0 | Derrick
2025-11-09 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-11-09 | 2025-11-05 | 2025-11-11 | Sanjeev Kumar | 37.5044 | 5.3578 | TB408 | 33/1 | Derrick
2025-11-09 | 2025-11-08 | 2025-11-14 | Shobha Devi | 37.5044 | 5.3578 | TB408 | 42/4 | Derrick
2025-11-09 | 2025-10-27 | 2025-11-09 | Vinay Construction | 45.413 | 3.2438 | TB408 | 42/2 | Derrick
2025-11-10 | 2025-11-10 | 2025-11-13 | Chinta Devi | 38.8476 | 9.7119 | TB408 | 29/2 | Derrick
2025-11-10 | 2025-11-10 | 2025-11-17 | Chinta Devi | 37.5044 | 4.688 | TB408 | 28/1 | Derrick
2025-11-10 | 2025-11-09 | 2025-11-18 | Devi Construction | 57.5972 | 5.7597 | TB408 | 8/0 | Derrick
2025-11-10 | 2025-11-08 | 2025-11-13 | Ganesh Sinha | 38.8476 | 6.4746 | TB408 | 32/2 | Derrick
2025-11-10 | 2025-11-08 | 2025-11-18 | Jirwa Devi | 66.3811 | 6.0346 | TB408 | 32/0 | Derrick
2025-11-10 | 2025-10-29 | 2025-11-16 | Kamlesh Kumar | 70.7017 | 3.7211 | TB408 | 5/0 | Derrick
2025-11-10 | 2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-11-10 | 2025-11-05 | 2025-11-11 | Sanjeev Kumar | 37.5044 | 5.3578 | TB408 | 33/1 | Derrick
2025-11-10 | 2025-11-08 | 2025-11-14 | Shobha Devi | 37.5044 | 5.3578 | TB408 | 42/4 | Derrick
2025-11-10 | 2025-11-10 | 2025-11-21 | Vinay Construction | 45.413 | 3.7844 | TB408 | 42/1 | Derrick
2025-11-11 | 2025-11-10 | 2025-11-13 | Chinta Devi | 38.8476 | 9.7119 | TB408 | 29/2 | Derrick
2025-11-11 | 2025-11-10 | 2025-11-17 | Chinta Devi | 37.5044 | 4.688 | TB408 | 28/1 | Derrick
2025-11-11 | 2025-11-09 | 2025-11-18 | Devi Construction | 57.5972 | 5.7597 | TB408 | 8/0 | Derrick
2025-11-11 | 2025-11-08 | 2025-11-13 | Ganesh Sinha | 38.8476 | 6.4746 | TB408 | 32/2 | Derrick
2025-11-11 | 2025-11-08 | 2025-11-18 | Jirwa Devi | 66.3811 | 6.0346 | TB408 | 32/0 | Derrick
2025-11-11 | 2025-10-29 | 2025-11-16 | Kamlesh Kumar | 70.7017 | 3.7211 | TB408 | 5/0 | Derrick
2025-11-11 | 2025-11-05 | 2025-11-11 | Sanjeev Kumar | 37.5044 | 5.3578 | TB408 | 33/1 | Derrick
2025-11-11 | 2025-11-11 | 2025-11-21 | Sanjeev Kumar | 45.413 | 4.1285 | TB408 | 34/2 | Derrick
2025-11-11 | 2025-11-11 | 2025-11-18 | Santosh Singh | 37.5044 | 4.688 | TB408 | 32/4 | Derrick
2025-11-11 | 2025-11-08 | 2025-11-14 | Shobha Devi | 37.5044 | 5.3578 | TB408 | 42/4 | Derrick
2025-11-11 | 2025-11-10 | 2025-11-21 | Vinay Construction | 45.413 | 3.7844 | TB408 | 42/1 | Derrick
2025-11-12 | 2025-11-10 | 2025-11-13 | Chinta Devi | 38.8476 | 9.7119 | TB408 | 29/2 | Derrick
2025-11-12 | 2025-11-10 | 2025-11-17 | Chinta Devi | 37.5044 | 4.688 | TB408 | 28/1 | Derrick
2025-11-12 | 2025-11-09 | 2025-11-18 | Devi Construction | 57.5972 | 5.7597 | TB408 | 8/0 | Derrick
2025-11-12 | 2025-11-08 | 2025-11-13 | Ganesh Sinha | 38.8476 | 6.4746 | TB408 | 32/2 | Derrick
2025-11-12 | 2025-11-08 | 2025-11-18 | Jirwa Devi | 66.3811 | 6.0346 | TB408 | 32/0 | Derrick
2025-11-12 | 2025-10-29 | 2025-11-16 | Kamlesh Kumar | 70.7017 | 3.7211 | TB408 | 5/0 | Derrick
2025-11-12 | 2025-11-11 | 2025-11-21 | Sanjeev Kumar | 45.413 | 4.1285 | TB408 | 34/2 | Derrick
2025-11-12 | 2025-11-11 | 2025-11-18 | Santosh Singh | 37.5044 | 4.688 | TB408 | 32/4 | Derrick
2025-11-12 | 2025-11-08 | 2025-11-14 | Shobha Devi | 37.5044 | 5.3578 | TB408 | 42/4 | Derrick
2025-11-12 | 2025-11-10 | 2025-11-21 | Vinay Construction | 45.413 | 3.7844 | TB408 | 42/1 | Derrick
2025-11-13 | 2025-11-10 | 2025-11-13 | Chinta Devi | 38.8476 | 9.7119 | TB408 | 29/2 | Derrick
2025-11-13 | 2025-11-10 | 2025-11-17 | Chinta Devi | 37.5044 | 4.688 | TB408 | 28/1 | Derrick
2025-11-13 | 2025-11-09 | 2025-11-18 | Devi Construction | 57.5972 | 5.7597 | TB408 | 8/0 | Derrick
2025-11-13 | 2025-11-08 | 2025-11-13 | Ganesh Sinha | 38.8476 | 6.4746 | TB408 | 32/2 | Derrick
2025-11-13 | 2025-11-08 | 2025-11-18 | Jirwa Devi | 66.3811 | 6.0346 | TB408 | 32/0 | Derrick
2025-11-13 | 2025-10-29 | 2025-11-16 | Kamlesh Kumar | 70.7017 | 3.7211 | TB408 | 5/0 | Derrick
2025-11-13 | 2025-11-11 | 2025-11-21 | Sanjeev Kumar | 45.413 | 4.1285 | TB408 | 34/2 | Derrick
2025-11-13 | 2025-11-11 | 2025-11-18 | Santosh Singh | 37.5044 | 4.688 | TB408 | 32/4 | Derrick
2025-11-13 | 2025-11-08 | 2025-11-14 | Shobha Devi | 37.5044 | 5.3578 | TB408 | 42/4 | Derrick
2025-11-13 | 2025-11-10 | 2025-11-21 | Vinay Construction | 45.413 | 3.7844 | TB408 | 42/1 | Derrick
2025-11-14 | 2025-11-10 | 2025-11-17 | Chinta Devi | 37.5044 | 4.688 | TB408 | 28/1 | Derrick
2025-11-14 | 2025-11-09 | 2025-11-18 | Devi Construction | 57.5972 | 5.7597 | TB408 | 8/0 | Derrick
2025-11-14 | 2025-11-08 | 2025-11-18 | Jirwa Devi | 66.3811 | 6.0346 | TB408 | 32/0 | Derrick
2025-11-14 | 2025-10-29 | 2025-11-16 | Kamlesh Kumar | 70.7017 | 3.7211 | TB408 | 5/0 | Derrick
2025-11-14 | 2025-11-11 | 2025-11-21 | Sanjeev Kumar | 45.413 | 4.1285 | TB408 | 34/2 | Derrick
2025-11-14 | 2025-11-11 | 2025-11-18 | Santosh Singh | 37.5044 | 4.688 | TB408 | 32/4 | Derrick
2025-11-14 | 2025-11-08 | 2025-11-14 | Shobha Devi | 37.5044 | 5.3578 | TB408 | 42/4 | Derrick
2025-11-14 | 2025-11-10 | 2025-11-21 | Vinay Construction | 45.413 | 3.7844 | TB408 | 42/1 | Derrick
2025-11-15 | 2025-11-10 | 2025-11-17 | Chinta Devi | 37.5044 | 4.688 | TB408 | 28/1 | Derrick
2025-11-15 | 2025-11-09 | 2025-11-18 | Devi Construction | 57.5972 | 5.7597 | TB408 | 8/0 | Derrick
2025-11-15 | 2025-11-08 | 2025-11-18 | Jirwa Devi | 66.3811 | 6.0346 | TB408 | 32/0 | Derrick
2025-11-15 | 2025-10-29 | 2025-11-16 | Kamlesh Kumar | 70.7017 | 3.7211 | TB408 | 5/0 | Derrick
2025-11-15 | 2025-11-11 | 2025-11-21 | Sanjeev Kumar | 45.413 | 4.1285 | TB408 | 34/2 | Derrick
2025-11-15 | 2025-11-11 | 2025-11-18 | Santosh Singh | 37.5044 | 4.688 | TB408 | 32/4 | Derrick
2025-11-15 | 2025-11-15 | 2025-11-17 | Sobha Devi | 37.5044 | 12.5015 | TB408 | 42/3 | Derrick
2025-11-15 | 2025-11-10 | 2025-11-21 | Vinay Construction | 45.413 | 3.7844 | TB408 | 42/1 | Derrick
2025-11-16 | 2025-11-10 | 2025-11-17 | Chinta Devi | 37.5044 | 4.688 | TB408 | 28/1 | Derrick
2025-11-16 | 2025-11-09 | 2025-11-18 | Devi Construction | 57.5972 | 5.7597 | TB408 | 8/0 | Derrick
2025-11-16 | 2025-11-08 | 2025-11-18 | Jirwa Devi | 66.3811 | 6.0346 | TB408 | 32/0 | Derrick
2025-11-16 | 2025-10-29 | 2025-11-16 | Kamlesh Kumar | 70.7017 | 3.7211 | TB408 | 5/0 | Derrick
2025-11-16 | 2025-11-11 | 2025-11-21 | Sanjeev Kumar | 45.413 | 4.1285 | TB408 | 34/2 | Derrick
2025-11-16 | 2025-11-11 | 2025-11-18 | Santosh Singh | 37.5044 | 4.688 | TB408 | 32/4 | Derrick
2025-11-16 | 2025-11-15 | 2025-11-17 | Sobha Devi | 37.5044 | 12.5015 | TB408 | 42/3 | Derrick
2025-11-16 | 2025-11-10 | 2025-11-21 | Vinay Construction | 45.413 | 3.7844 | TB408 | 42/1 | Derrick
2025-11-17 | 2025-11-10 | 2025-11-17 | Chinta Devi | 37.5044 | 4.688 | TB408 | 28/1 | Derrick
2025-11-17 | 2025-11-09 | 2025-11-18 | Devi Construction | 57.5972 | 5.7597 | TB408 | 8/0 | Derrick
2025-11-17 | 2025-11-08 | 2025-11-18 | Jirwa Devi | 66.3811 | 6.0346 | TB408 | 32/0 | Derrick
2025-11-17 | 2025-11-11 | 2025-11-21 | Sanjeev Kumar | 45.413 | 4.1285 | TB408 | 34/2 | Derrick
2025-11-17 | 2025-11-11 | 2025-11-18 | Santosh Singh | 37.5044 | 4.688 | TB408 | 32/4 | Derrick
2025-11-17 | 2025-11-15 | 2025-11-17 | Sobha Devi | 37.5044 | 12.5015 | TB408 | 42/3 | Derrick
2025-11-17 | 2025-11-10 | 2025-11-21 | Vinay Construction | 45.413 | 3.7844 | TB408 | 42/1 | Derrick
2025-11-18 | 2025-11-09 | 2025-11-18 | Devi Construction | 57.5972 | 5.7597 | TB408 | 8/0 | Derrick
2025-11-18 | 2025-11-08 | 2025-11-18 | Jirwa Devi | 66.3811 | 6.0346 | TB408 | 32/0 | Derrick
2025-11-18 | 2025-11-11 | 2025-11-21 | Sanjeev Kumar | 45.413 | 4.1285 | TB408 | 34/2 | Derrick
2025-11-18 | 2025-11-11 | 2025-11-18 | Santosh Singh | 37.5044 | 4.688 | TB408 | 32/4 | Derrick
2025-11-18 | 2025-11-18 | 2025-11-22 | Shobha Devi | 45.413 | 9.0826 | TB408 | 38/2 | Derrick
2025-11-18 | 2025-11-10 | 2025-11-21 | Vinay Construction | 45.413 | 3.7844 | TB408 | 42/1 | Derrick
2025-11-19 | 2025-11-11 | 2025-11-21 | Sanjeev Kumar | 45.413 | 4.1285 | TB408 | 34/2 | Derrick
2025-11-19 | 2025-11-18 | 2025-11-22 | Shobha Devi | 45.413 | 9.0826 | TB408 | 38/2 | Derrick
2025-11-19 | 2025-11-10 | 2025-11-21 | Vinay Construction | 45.413 | 3.7844 | TB408 | 42/1 | Derrick
2025-11-20 | 2025-11-11 | 2025-11-21 | Sanjeev Kumar | 45.413 | 4.1285 | TB408 | 34/2 | Derrick
2025-11-20 | 2025-11-18 | 2025-11-22 | Shobha Devi | 45.413 | 9.0826 | TB408 | 38/2 | Derrick
2025-11-20 | 2025-11-10 | 2025-11-21 | Vinay Construction | 45.413 | 3.7844 | TB408 | 42/1 | Derrick
2025-11-21 | 2025-11-11 | 2025-11-21 | Sanjeev Kumar | 45.413 | 4.1285 | TB408 | 34/2 | Derrick
2025-11-21 | 2025-11-18 | 2025-11-22 | Shobha Devi | 45.413 | 9.0826 | TB408 | 38/2 | Derrick
2025-11-21 | 2025-11-10 | 2025-11-21 | Vinay Construction | 45.413 | 3.7844 | TB408 | 42/1 | Derrick
2025-11-22 | 2025-11-18 | 2025-11-22 | Shobha Devi | 45.413 | 9.0826 | TB408 | 38/2 | Derrick
2025-06-23 | 2025-06-23 | 2025-06-28 | Dipak | 11.145 | 1.8575 | TB507 | 77/2 | Completed
2025-06-24 | 2025-06-23 | 2025-06-28 | Dipak | 11.145 | 1.8575 | TB507 | 77/2 | Completed
2025-06-25 | 2025-06-23 | 2025-06-28 | Dipak | 11.145 | 1.8575 | TB507 | 77/2 | Completed
2025-06-26 | 2025-06-23 | 2025-06-28 | Dipak | 11.145 | 1.8575 | TB507 | 77/2 | Completed
2025-06-27 | 2025-06-23 | 2025-06-28 | Dipak | 11.145 | 1.8575 | TB507 | 77/2 | Completed
2025-06-28 | 2025-06-23 | 2025-06-28 | Dipak | 11.145 | 1.8575 | TB507 | 77/2 | Completed
2025-06-28 | 2025-06-28 | 2025-07-02 | Dipak | 11.997 | 2.3994 | TB507 | 77/4 | Completed
2025-06-29 | 2025-06-28 | 2025-07-02 | Dipak | 11.997 | 2.3994 | TB507 | 77/4 | Completed
2025-06-29 | 2025-06-29 | 2025-07-05 | Srikarni | 11.145 | 1.5921 | TB507 | 75/7 | Completed
2025-06-30 | 2025-06-28 | 2025-07-02 | Dipak | 11.997 | 2.3994 | TB507 | 77/4 | Completed
2025-06-30 | 2025-06-29 | 2025-07-05 | Srikarni | 11.145 | 1.5921 | TB507 | 75/7 | Completed
2025-07-01 | 2025-06-28 | 2025-07-02 | Dipak | 11.997 | 2.3994 | TB507 | 77/4 | Completed
2025-07-01 | 2025-06-29 | 2025-07-05 | Srikarni | 11.145 | 1.5921 | TB507 | 75/7 | Completed
2025-07-02 | 2025-06-28 | 2025-07-02 | Dipak | 11.997 | 2.3994 | TB507 | 77/4 | Completed
2025-07-02 | 2025-06-29 | 2025-07-05 | Srikarni | 11.145 | 1.5921 | TB507 | 75/7 | Completed
2025-07-03 | 2025-07-03 | 2025-07-05 | Dipak | 13.072 | 4.3573 | TB507 | 77/5 | Completed
2025-07-03 | 2025-06-29 | 2025-07-05 | Srikarni | 11.145 | 1.5921 | TB507 | 75/7 | Completed
2025-07-04 | 2025-07-03 | 2025-07-05 | Dipak | 13.072 | 4.3573 | TB507 | 77/5 | Completed
2025-07-04 | 2025-06-29 | 2025-07-05 | Srikarni | 11.145 | 1.5921 | TB507 | 75/7 | Completed
2025-07-05 | 2025-07-03 | 2025-07-05 | Dipak | 13.072 | 4.3573 | TB507 | 77/5 | Completed
2025-07-05 | 2025-06-29 | 2025-07-05 | Srikarni | 11.145 | 1.5921 | TB507 | 75/7 | Completed
2025-07-07 | 2025-07-07 | 2025-07-10 | Dipak | 11.145 | 2.7862 | TB507 | 77/3 | Completed
2025-07-08 | 2025-07-07 | 2025-07-10 | Dipak | 11.145 | 2.7862 | TB507 | 77/3 | Completed
2025-07-09 | 2025-07-07 | 2025-07-10 | Dipak | 11.145 | 2.7862 | TB507 | 77/3 | Completed
2025-07-10 | 2025-07-07 | 2025-07-10 | Dipak | 11.145 | 2.7862 | TB507 | 77/3 | Completed
2025-07-11 | 2025-07-11 | 2025-07-14 | Dipak | 11.145 | 2.7862 | TB507 | 77/1 | Completed
2025-07-12 | 2025-07-11 | 2025-07-14 | Dipak | 11.145 | 2.7862 | TB507 | 77/1 | Completed
2025-07-13 | 2025-07-11 | 2025-07-14 | Dipak | 11.145 | 2.7862 | TB507 | 77/1 | Completed
2025-07-14 | 2025-07-11 | 2025-07-14 | Dipak | 11.145 | 2.7862 | TB507 | 77/1 | Completed
2025-07-15 | 2025-07-15 | 2025-07-18 | Dipak | 11.145 | 2.7862 | TB507 | 75/6 | Completed
2025-07-16 | 2025-07-15 | 2025-07-18 | Dipak | 11.145 | 2.7862 | TB507 | 75/6 | Completed
2025-07-17 | 2025-07-15 | 2025-07-18 | Dipak | 11.145 | 2.7862 | TB507 | 75/6 | Completed
2025-07-18 | 2025-07-15 | 2025-07-18 | Dipak | 11.145 | 2.7862 | TB507 | 75/6 | Completed
2025-07-19 | 2025-07-19 | 2025-07-22 | Dipak | 11.145 | 2.7862 | TB507 | 75/5 | Completed
2025-07-20 | 2025-07-19 | 2025-07-22 | Dipak | 11.145 | 2.7862 | TB507 | 75/5 | Completed
2025-07-21 | 2025-07-19 | 2025-07-22 | Dipak | 11.145 | 2.7862 | TB507 | 75/5 | Completed
2025-07-22 | 2025-07-19 | 2025-07-22 | Dipak | 11.145 | 2.7862 | TB507 | 75/5 | Completed
2025-07-22 | 2025-07-22 | 2025-07-25 | Dipak | 11.145 | 2.7862 | TB507 | 75/4 | Completed
2025-07-23 | 2025-07-22 | 2025-07-25 | Dipak | 11.145 | 2.7862 | TB507 | 75/4 | Completed
2025-07-24 | 2025-07-24 | 2025-07-31 | Ahmed Construction | 11.145 | 1.3931 | TB507 | 74/1 | Completed
2025-07-24 | 2025-07-22 | 2025-07-25 | Dipak | 11.145 | 2.7862 | TB507 | 75/4 | Completed
2025-07-25 | 2025-07-24 | 2025-07-31 | Ahmed Construction | 11.145 | 1.3931 | TB507 | 74/1 | Completed
2025-07-25 | 2025-07-22 | 2025-07-25 | Dipak | 11.145 | 2.7862 | TB507 | 75/4 | Completed
2025-07-25 | 2025-07-25 | 2025-07-28 | Dipak | 11.997 | 2.9992 | TB507 | 75/3 | Completed
2025-07-26 | 2025-07-24 | 2025-07-31 | Ahmed Construction | 11.145 | 1.3931 | TB507 | 74/1 | Completed
2025-07-26 | 2025-07-25 | 2025-07-28 | Dipak | 11.997 | 2.9992 | TB507 | 75/3 | Completed
2025-07-27 | 2025-07-24 | 2025-07-31 | Ahmed Construction | 11.145 | 1.3931 | TB507 | 74/1 | Completed
2025-07-27 | 2025-07-25 | 2025-07-28 | Dipak | 11.997 | 2.9992 | TB507 | 75/3 | Completed
2025-07-28 | 2025-07-24 | 2025-07-31 | Ahmed Construction | 11.145 | 1.3931 | TB507 | 74/1 | Completed
2025-07-28 | 2025-07-25 | 2025-07-28 | Dipak | 11.997 | 2.9992 | TB507 | 75/3 | Completed
2025-07-29 | 2025-07-24 | 2025-07-31 | Ahmed Construction | 11.145 | 1.3931 | TB507 | 74/1 | Completed
2025-07-29 | 2025-07-29 | 2025-07-31 | Dipak | 11.145 | 3.715 | TB507 | 75/2 | Completed
2025-07-30 | 2025-07-24 | 2025-07-31 | Ahmed Construction | 11.145 | 1.3931 | TB507 | 74/1 | Completed
2025-07-30 | 2025-07-29 | 2025-07-31 | Dipak | 11.145 | 3.715 | TB507 | 75/2 | Completed
2025-07-31 | 2025-07-24 | 2025-07-31 | Ahmed Construction | 11.145 | 1.3931 | TB507 | 74/1 | Completed
2025-07-31 | 2025-07-29 | 2025-07-31 | Dipak | 11.145 | 3.715 | TB507 | 75/2 | Completed
2025-08-01 | 2025-08-01 | 2025-08-08 | Ahmed Construction | 13.958 | 1.7448 | TB507 | 73/3 | Completed
2025-08-01 | 2025-08-01 | 2025-08-04 | Dipak | 11.145 | 2.7862 | TB507 | 75/1 | Completed
2025-08-02 | 2025-08-01 | 2025-08-08 | Ahmed Construction | 13.958 | 1.7448 | TB507 | 73/3 | Completed
2025-08-02 | 2025-08-01 | 2025-08-04 | Dipak | 11.145 | 2.7862 | TB507 | 75/1 | Completed
2025-08-03 | 2025-08-01 | 2025-08-08 | Ahmed Construction | 13.958 | 1.7448 | TB507 | 73/3 | Completed
2025-08-03 | 2025-08-01 | 2025-08-04 | Dipak | 11.145 | 2.7862 | TB507 | 75/1 | Completed
2025-08-04 | 2025-08-01 | 2025-08-08 | Ahmed Construction | 13.958 | 1.7448 | TB507 | 73/3 | Completed
2025-08-04 | 2025-08-01 | 2025-08-04 | Dipak | 11.145 | 2.7862 | TB507 | 75/1 | Completed
2025-08-04 | 2025-08-04 | 2025-08-09 | Dipak | 18.727 | 3.1212 | TB507 | 75/0 | Completed
2025-08-05 | 2025-08-01 | 2025-08-08 | Ahmed Construction | 13.958 | 1.7448 | TB507 | 73/3 | Completed
2025-08-05 | 2025-08-04 | 2025-08-09 | Dipak | 18.727 | 3.1212 | TB507 | 75/0 | Completed
2025-08-06 | 2025-08-01 | 2025-08-08 | Ahmed Construction | 13.958 | 1.7448 | TB507 | 73/3 | Completed
2025-08-06 | 2025-08-04 | 2025-08-09 | Dipak | 18.727 | 3.1212 | TB507 | 75/0 | Completed
2025-08-07 | 2025-08-01 | 2025-08-08 | Ahmed Construction | 13.958 | 1.7448 | TB507 | 73/3 | Completed
2025-08-07 | 2025-08-04 | 2025-08-09 | Dipak | 18.727 | 3.1212 | TB507 | 75/0 | Completed
2025-08-08 | 2025-08-01 | 2025-08-08 | Ahmed Construction | 13.958 | 1.7448 | TB507 | 73/3 | Completed
2025-08-08 | 2025-08-08 | 2025-08-16 | Ahmed Construction | 13.958 | 1.5509 | TB507 | 73/2 | Completed
2025-08-08 | 2025-08-04 | 2025-08-09 | Dipak | 18.727 | 3.1212 | TB507 | 75/0 | Completed
2025-08-09 | 2025-08-08 | 2025-08-16 | Ahmed Construction | 13.958 | 1.5509 | TB507 | 73/2 | Completed
2025-08-09 | 2025-08-04 | 2025-08-09 | Dipak | 18.727 | 3.1212 | TB507 | 75/0 | Completed
2025-08-10 | 2025-08-08 | 2025-08-16 | Ahmed Construction | 13.958 | 1.5509 | TB507 | 73/2 | Completed
2025-08-10 | 2025-08-10 | 2025-08-16 | Dipak | 18.727 | 2.6753 | TB507 | 78/0 | Completed
2025-08-11 | 2025-08-08 | 2025-08-16 | Ahmed Construction | 13.958 | 1.5509 | TB507 | 73/2 | Completed
2025-08-11 | 2025-08-10 | 2025-08-16 | Dipak | 18.727 | 2.6753 | TB507 | 78/0 | Completed
2025-08-12 | 2025-08-08 | 2025-08-16 | Ahmed Construction | 13.958 | 1.5509 | TB507 | 73/2 | Completed
2025-08-12 | 2025-08-10 | 2025-08-16 | Dipak | 18.727 | 2.6753 | TB507 | 78/0 | Completed
2025-08-13 | 2025-08-08 | 2025-08-16 | Ahmed Construction | 13.958 | 1.5509 | TB507 | 73/2 | Completed
2025-08-13 | 2025-08-10 | 2025-08-16 | Dipak | 18.727 | 2.6753 | TB507 | 78/0 | Completed
2025-08-14 | 2025-08-08 | 2025-08-16 | Ahmed Construction | 13.958 | 1.5509 | TB507 | 73/2 | Completed
2025-08-14 | 2025-08-10 | 2025-08-16 | Dipak | 18.727 | 2.6753 | TB507 | 78/0 | Completed
2025-08-15 | 2025-08-08 | 2025-08-16 | Ahmed Construction | 13.958 | 1.5509 | TB507 | 73/2 | Completed
2025-08-15 | 2025-08-10 | 2025-08-16 | Dipak | 18.727 | 2.6753 | TB507 | 78/0 | Completed
2025-08-16 | 2025-08-08 | 2025-08-16 | Ahmed Construction | 13.958 | 1.5509 | TB507 | 73/2 | Completed
2025-08-16 | 2025-08-10 | 2025-08-16 | Dipak | 18.727 | 2.6753 | TB507 | 78/0 | Completed
2025-08-17 | 2025-08-17 | 2025-08-23 | Ahmed Construction | 11.145 | 1.5921 | TB507 | 85/1 | Completed
2025-08-17 | 2025-08-17 | 2025-08-23 | Dipak | 21.41 | 3.0586 | TB507 | 79/0 | Completed
2025-08-18 | 2025-08-17 | 2025-08-23 | Ahmed Construction | 11.145 | 1.5921 | TB507 | 85/1 | Completed
2025-08-18 | 2025-08-17 | 2025-08-23 | Dipak | 21.41 | 3.0586 | TB507 | 79/0 | Completed
2025-08-19 | 2025-08-17 | 2025-08-23 | Ahmed Construction | 11.145 | 1.5921 | TB507 | 85/1 | Completed
2025-08-19 | 2025-08-17 | 2025-08-23 | Dipak | 21.41 | 3.0586 | TB507 | 79/0 | Completed
2025-08-20 | 2025-08-17 | 2025-08-23 | Ahmed Construction | 11.145 | 1.5921 | TB507 | 85/1 | Completed
2025-08-20 | 2025-08-17 | 2025-08-23 | Dipak | 21.41 | 3.0586 | TB507 | 79/0 | Completed
2025-08-21 | 2025-08-17 | 2025-08-23 | Ahmed Construction | 11.145 | 1.5921 | TB507 | 85/1 | Completed
2025-08-21 | 2025-08-17 | 2025-08-23 | Dipak | 21.41 | 3.0586 | TB507 | 79/0 | Completed
2025-08-22 | 2025-08-17 | 2025-08-23 | Ahmed Construction | 11.145 | 1.5921 | TB507 | 85/1 | Completed
2025-08-22 | 2025-08-17 | 2025-08-23 | Dipak | 21.41 | 3.0586 | TB507 | 79/0 | Completed
2025-08-23 | 2025-08-17 | 2025-08-23 | Ahmed Construction | 11.145 | 1.5921 | TB507 | 85/1 | Completed
2025-08-23 | 2025-08-23 | 2025-08-28 | Ahmed Construction | 13.072 | 2.1787 | TB507 | 86/1 | Completed
2025-08-23 | 2025-08-23 | 2025-08-31 | Ajay Kumar | 11.145 | 1.2383 | TB507 | 95A/1 | Completed
2025-08-23 | 2025-08-17 | 2025-08-23 | Dipak | 21.41 | 3.0586 | TB507 | 79/0 | Completed
2025-08-23 | 2025-08-23 | 2025-08-28 | Dipak | 13.958 | 2.3263 | TB507 | 80/1 | Completed
2025-08-24 | 2025-08-23 | 2025-08-28 | Ahmed Construction | 13.072 | 2.1787 | TB507 | 86/1 | Completed
2025-08-24 | 2025-08-23 | 2025-08-31 | Ajay Kumar | 11.145 | 1.2383 | TB507 | 95A/1 | Completed
2025-08-24 | 2025-08-23 | 2025-08-28 | Dipak | 13.958 | 2.3263 | TB507 | 80/1 | Completed
2025-08-25 | 2025-08-23 | 2025-08-28 | Ahmed Construction | 13.072 | 2.1787 | TB507 | 86/1 | Completed
2025-08-25 | 2025-08-23 | 2025-08-31 | Ajay Kumar | 11.145 | 1.2383 | TB507 | 95A/1 | Completed
2025-08-25 | 2025-08-23 | 2025-08-28 | Dipak | 13.958 | 2.3263 | TB507 | 80/1 | Completed
2025-08-26 | 2025-08-23 | 2025-08-28 | Ahmed Construction | 13.072 | 2.1787 | TB507 | 86/1 | Completed
2025-08-26 | 2025-08-23 | 2025-08-31 | Ajay Kumar | 11.145 | 1.2383 | TB507 | 95A/1 | Completed
2025-08-26 | 2025-08-23 | 2025-08-28 | Dipak | 13.958 | 2.3263 | TB507 | 80/1 | Completed
2025-08-27 | 2025-08-23 | 2025-08-28 | Ahmed Construction | 13.072 | 2.1787 | TB507 | 86/1 | Completed
2025-08-27 | 2025-08-23 | 2025-08-31 | Ajay Kumar | 11.145 | 1.2383 | TB507 | 95A/1 | Completed
2025-08-27 | 2025-08-27 | 2025-09-09 | Ayansh Const | 11.997 | 0.85693 | TB507 | 145/1 | Completed
2025-08-27 | 2025-08-23 | 2025-08-28 | Dipak | 13.958 | 2.3263 | TB507 | 80/1 | Completed
2025-08-27 | 2025-08-27 | 2025-08-29 | Gokul Sarkar | 11.145 | 3.715 | TB507 | 148/4 | Completed
2025-08-28 | 2025-08-23 | 2025-08-28 | Ahmed Construction | 13.072 | 2.1787 | TB507 | 86/1 | Completed
2025-08-28 | 2025-08-23 | 2025-08-31 | Ajay Kumar | 11.145 | 1.2383 | TB507 | 95A/1 | Completed
2025-08-28 | 2025-08-27 | 2025-09-09 | Ayansh Const | 11.997 | 0.85693 | TB507 | 145/1 | Completed
2025-08-28 | 2025-08-23 | 2025-08-28 | Dipak | 13.958 | 2.3263 | TB507 | 80/1 | Completed
2025-08-28 | 2025-08-27 | 2025-08-29 | Gokul Sarkar | 11.145 | 3.715 | TB507 | 148/4 | Completed
2025-08-28 | 2025-08-28 | 2025-09-16 | Windbridge Energy | 11.145 | 0.55725 | TB507 | 133/2 | Completed
2025-08-29 | 2025-08-29 | 2025-09-11 | Ahmed Construction | 11.997 | 0.85693 | TB507 | 83/1 | Completed
2025-08-29 | 2025-08-23 | 2025-08-31 | Ajay Kumar | 11.145 | 1.2383 | TB507 | 95A/1 | Completed
2025-08-29 | 2025-08-27 | 2025-09-09 | Ayansh Const | 11.997 | 0.85693 | TB507 | 145/1 | Completed
2025-08-29 | 2025-08-29 | 2025-08-31 | Dipak | 11.145 | 3.715 | TB507 | 81/3 | Completed
2025-08-29 | 2025-08-27 | 2025-08-29 | Gokul Sarkar | 11.145 | 3.715 | TB507 | 148/4 | Completed
2025-08-29 | 2025-08-29 | 2025-09-04 | Gokul Sarkar | 11.145 | 1.5921 | TB507 | 148/3 | Completed
2025-08-29 | 2025-08-28 | 2025-09-16 | Windbridge Energy | 11.145 | 0.55725 | TB507 | 133/2 | Completed
2025-08-30 | 2025-08-29 | 2025-09-11 | Ahmed Construction | 11.997 | 0.85693 | TB507 | 83/1 | Completed
2025-08-30 | 2025-08-23 | 2025-08-31 | Ajay Kumar | 11.145 | 1.2383 | TB507 | 95A/1 | Completed
2025-08-30 | 2025-08-27 | 2025-09-09 | Ayansh Const | 11.997 | 0.85693 | TB507 | 145/1 | Completed
2025-08-30 | 2025-08-29 | 2025-08-31 | Dipak | 11.145 | 3.715 | TB507 | 81/3 | Completed
2025-08-30 | 2025-08-29 | 2025-09-04 | Gokul Sarkar | 11.145 | 1.5921 | TB507 | 148/3 | Completed
2025-08-30 | 2025-08-28 | 2025-09-16 | Windbridge Energy | 11.145 | 0.55725 | TB507 | 133/2 | Completed
2025-08-31 | 2025-08-29 | 2025-09-11 | Ahmed Construction | 11.997 | 0.85693 | TB507 | 83/1 | Completed
2025-08-31 | 2025-08-23 | 2025-08-31 | Ajay Kumar | 11.145 | 1.2383 | TB507 | 95A/1 | Completed
2025-08-31 | 2025-08-27 | 2025-09-09 | Ayansh Const | 11.997 | 0.85693 | TB507 | 145/1 | Completed
2025-08-31 | 2025-08-29 | 2025-08-31 | Dipak | 11.145 | 3.715 | TB507 | 81/3 | Completed
2025-08-31 | 2025-08-29 | 2025-09-04 | Gokul Sarkar | 11.145 | 1.5921 | TB507 | 148/3 | Completed
2025-08-31 | 2025-08-28 | 2025-09-16 | Windbridge Energy | 11.145 | 0.55725 | TB507 | 133/2 | Completed
2025-09-01 | 2025-08-29 | 2025-09-11 | Ahmed Construction | 11.997 | 0.85693 | TB507 | 83/1 | Completed
2025-09-01 | 2025-09-01 | 2025-09-11 | Ajay Kumar 1 | 18.727 | 1.7025 | TB507 | 97/0 | Completed
2025-09-01 | 2025-09-01 | 2025-09-15 | Ajay Kumar 1 | 11.145 | 0.743 | TB507 | 96/1 | Completed
2025-09-01 | 2025-08-27 | 2025-09-09 | Ayansh Const | 11.997 | 0.85693 | TB507 | 145/1 | Completed
2025-09-01 | 2025-09-01 | 2025-09-05 | Dipak | 11.997 | 2.3994 | TB507 | 81/2 | Completed
2025-09-01 | 2025-08-29 | 2025-09-04 | Gokul Sarkar | 11.145 | 1.5921 | TB507 | 148/3 | Completed
2025-09-01 | 2025-08-28 | 2025-09-16 | Windbridge Energy | 11.145 | 0.55725 | TB507 | 133/2 | Completed
2025-09-02 | 2025-08-29 | 2025-09-11 | Ahmed Construction | 11.997 | 0.85693 | TB507 | 83/1 | Completed
2025-09-02 | 2025-09-01 | 2025-09-11 | Ajay Kumar 1 | 18.727 | 1.7025 | TB507 | 97/0 | Completed
2025-09-02 | 2025-09-01 | 2025-09-15 | Ajay Kumar 1 | 11.145 | 0.743 | TB507 | 96/1 | Completed
2025-09-02 | 2025-08-27 | 2025-09-09 | Ayansh Const | 11.997 | 0.85693 | TB507 | 145/1 | Completed
2025-09-02 | 2025-09-01 | 2025-09-05 | Dipak | 11.997 | 2.3994 | TB507 | 81/2 | Completed
2025-09-02 | 2025-08-29 | 2025-09-04 | Gokul Sarkar | 11.145 | 1.5921 | TB507 | 148/3 | Completed
2025-09-02 | 2025-08-28 | 2025-09-16 | Windbridge Energy | 11.145 | 0.55725 | TB507 | 133/2 | Completed
2025-09-03 | 2025-08-29 | 2025-09-11 | Ahmed Construction | 11.997 | 0.85693 | TB507 | 83/1 | Completed
2025-09-03 | 2025-09-01 | 2025-09-11 | Ajay Kumar 1 | 18.727 | 1.7025 | TB507 | 97/0 | Completed
2025-09-03 | 2025-09-01 | 2025-09-15 | Ajay Kumar 1 | 11.145 | 0.743 | TB507 | 96/1 | Completed
2025-09-03 | 2025-08-27 | 2025-09-09 | Ayansh Const | 11.997 | 0.85693 | TB507 | 145/1 | Completed
2025-09-03 | 2025-09-01 | 2025-09-05 | Dipak | 11.997 | 2.3994 | TB507 | 81/2 | Completed
2025-09-03 | 2025-08-29 | 2025-09-04 | Gokul Sarkar | 11.145 | 1.5921 | TB507 | 148/3 | Completed
2025-09-03 | 2025-08-28 | 2025-09-16 | Windbridge Energy | 11.145 | 0.55725 | TB507 | 133/2 | Completed
2025-09-04 | 2025-08-29 | 2025-09-11 | Ahmed Construction | 11.997 | 0.85693 | TB507 | 83/1 | Completed
2025-09-04 | 2025-09-01 | 2025-09-11 | Ajay Kumar 1 | 18.727 | 1.7025 | TB507 | 97/0 | Completed
2025-09-04 | 2025-09-01 | 2025-09-15 | Ajay Kumar 1 | 11.145 | 0.743 | TB507 | 96/1 | Completed
2025-09-04 | 2025-08-27 | 2025-09-09 | Ayansh Const | 11.997 | 0.85693 | TB507 | 145/1 | Completed
2025-09-04 | 2025-09-01 | 2025-09-05 | Dipak | 11.997 | 2.3994 | TB507 | 81/2 | Completed
2025-09-04 | 2025-08-29 | 2025-09-04 | Gokul Sarkar | 11.145 | 1.5921 | TB507 | 148/3 | Completed
2025-09-04 | 2025-08-28 | 2025-09-16 | Windbridge Energy | 11.145 | 0.55725 | TB507 | 133/2 | Completed
2025-09-05 | 2025-08-29 | 2025-09-11 | Ahmed Construction | 11.997 | 0.85693 | TB507 | 83/1 | Completed
2025-09-05 | 2025-09-01 | 2025-09-11 | Ajay Kumar 1 | 18.727 | 1.7025 | TB507 | 97/0 | Completed
2025-09-05 | 2025-09-01 | 2025-09-15 | Ajay Kumar 1 | 11.145 | 0.743 | TB507 | 96/1 | Completed
2025-09-05 | 2025-08-27 | 2025-09-09 | Ayansh Const | 11.997 | 0.85693 | TB507 | 145/1 | Completed
2025-09-05 | 2025-09-01 | 2025-09-05 | Dipak | 11.997 | 2.3994 | TB507 | 81/2 | Completed
2025-09-05 | 2025-09-05 | 2025-09-09 | Dipak | 11.145 | 2.229 | TB507 | 81/4 | Completed
2025-09-05 | 2025-09-05 | 2025-09-10 | Gokul Sarkar | 11.145 | 1.8575 | TB507 | 148/2 | Completed
2025-09-05 | 2025-08-28 | 2025-09-16 | Windbridge Energy | 11.145 | 0.55725 | TB507 | 133/2 | Completed
2025-09-06 | 2025-08-29 | 2025-09-11 | Ahmed Construction | 11.997 | 0.85693 | TB507 | 83/1 | Completed
2025-09-06 | 2025-09-01 | 2025-09-11 | Ajay Kumar 1 | 18.727 | 1.7025 | TB507 | 97/0 | Completed
2025-09-06 | 2025-09-01 | 2025-09-15 | Ajay Kumar 1 | 11.145 | 0.743 | TB507 | 96/1 | Completed
2025-09-06 | 2025-08-27 | 2025-09-09 | Ayansh Const | 11.997 | 0.85693 | TB507 | 145/1 | Completed
2025-09-06 | 2025-09-05 | 2025-09-09 | Dipak | 11.145 | 2.229 | TB507 | 81/4 | Completed
2025-09-06 | 2025-09-05 | 2025-09-10 | Gokul Sarkar | 11.145 | 1.8575 | TB507 | 148/2 | Completed
2025-09-06 | 2025-08-28 | 2025-09-16 | Windbridge Energy | 11.145 | 0.55725 | TB507 | 133/2 | Completed
2025-09-07 | 2025-08-29 | 2025-09-11 | Ahmed Construction | 11.997 | 0.85693 | TB507 | 83/1 | Completed
2025-09-07 | 2025-09-01 | 2025-09-11 | Ajay Kumar 1 | 18.727 | 1.7025 | TB507 | 97/0 | Completed
2025-09-07 | 2025-09-01 | 2025-09-15 | Ajay Kumar 1 | 11.145 | 0.743 | TB507 | 96/1 | Completed
2025-09-07 | 2025-08-27 | 2025-09-09 | Ayansh Const | 11.997 | 0.85693 | TB507 | 145/1 | Completed
2025-09-07 | 2025-09-05 | 2025-09-09 | Dipak | 11.145 | 2.229 | TB507 | 81/4 | Completed
2025-09-07 | 2025-09-05 | 2025-09-10 | Gokul Sarkar | 11.145 | 1.8575 | TB507 | 148/2 | Completed
2025-09-07 | 2025-08-28 | 2025-09-16 | Windbridge Energy | 11.145 | 0.55725 | TB507 | 133/2 | Completed
2025-09-08 | 2025-08-29 | 2025-09-11 | Ahmed Construction | 11.997 | 0.85693 | TB507 | 83/1 | Completed
2025-09-08 | 2025-09-01 | 2025-09-11 | Ajay Kumar 1 | 18.727 | 1.7025 | TB507 | 97/0 | Completed
2025-09-08 | 2025-09-01 | 2025-09-15 | Ajay Kumar 1 | 11.145 | 0.743 | TB507 | 96/1 | Completed
2025-09-08 | 2025-08-27 | 2025-09-09 | Ayansh Const | 11.997 | 0.85693 | TB507 | 145/1 | Completed
2025-09-08 | 2025-09-05 | 2025-09-09 | Dipak | 11.145 | 2.229 | TB507 | 81/4 | Completed
2025-09-08 | 2025-09-05 | 2025-09-10 | Gokul Sarkar | 11.145 | 1.8575 | TB507 | 148/2 | Completed
2025-09-08 | 2025-08-28 | 2025-09-16 | Windbridge Energy | 11.145 | 0.55725 | TB507 | 133/2 | Completed
2025-09-09 | 2025-08-29 | 2025-09-11 | Ahmed Construction | 11.997 | 0.85693 | TB507 | 83/1 | Completed
2025-09-09 | 2025-09-01 | 2025-09-11 | Ajay Kumar 1 | 18.727 | 1.7025 | TB507 | 97/0 | Completed
2025-09-09 | 2025-09-01 | 2025-09-15 | Ajay Kumar 1 | 11.145 | 0.743 | TB507 | 96/1 | Completed
2025-09-09 | 2025-08-27 | 2025-09-09 | Ayansh Const | 11.997 | 0.85693 | TB507 | 145/1 | Completed
2025-09-09 | 2025-09-09 | 2025-09-14 | Ayansh Const | 11.145 | 1.8575 | TB507 | 145/2 | Completed
2025-09-09 | 2025-09-05 | 2025-09-09 | Dipak | 11.145 | 2.229 | TB507 | 81/4 | Completed
2025-09-09 | 2025-09-09 | 2025-09-14 | Dipak | 13.072 | 2.1787 | TB507 | 82/1 | Completed
2025-09-09 | 2025-09-05 | 2025-09-10 | Gokul Sarkar | 11.145 | 1.8575 | TB507 | 148/2 | Completed
2025-09-09 | 2025-08-28 | 2025-09-16 | Windbridge Energy | 11.145 | 0.55725 | TB507 | 133/2 | Completed
2025-09-10 | 2025-08-29 | 2025-09-11 | Ahmed Construction | 11.997 | 0.85693 | TB507 | 83/1 | Completed
2025-09-10 | 2025-09-01 | 2025-09-11 | Ajay Kumar 1 | 18.727 | 1.7025 | TB507 | 97/0 | Completed
2025-09-10 | 2025-09-01 | 2025-09-15 | Ajay Kumar 1 | 11.145 | 0.743 | TB507 | 96/1 | Completed
2025-09-10 | 2025-09-09 | 2025-09-14 | Ayansh Const | 11.145 | 1.8575 | TB507 | 145/2 | Completed
2025-09-10 | 2025-09-09 | 2025-09-14 | Dipak | 13.072 | 2.1787 | TB507 | 82/1 | Completed
2025-09-10 | 2025-09-05 | 2025-09-10 | Gokul Sarkar | 11.145 | 1.8575 | TB507 | 148/2 | Completed
2025-09-10 | 2025-08-28 | 2025-09-16 | Windbridge Energy | 11.145 | 0.55725 | TB507 | 133/2 | Completed
2025-09-11 | 2025-08-29 | 2025-09-11 | Ahmed Construction | 11.997 | 0.85693 | TB507 | 83/1 | Completed
2025-09-11 | 2025-09-11 | 2025-09-15 | Ahmed Construction | 11.145 | 2.229 | TB507 | 79/2 | Completed
2025-09-11 | 2025-09-01 | 2025-09-11 | Ajay Kumar 1 | 18.727 | 1.7025 | TB507 | 97/0 | Completed
2025-09-11 | 2025-09-01 | 2025-09-15 | Ajay Kumar 1 | 11.145 | 0.743 | TB507 | 96/1 | Completed
2025-09-11 | 2025-09-11 | 2025-09-21 | Ajay Kumar 2 | 11.997 | 1.0906 | TB507 | 97/1 | Completed
2025-09-11 | 2025-09-09 | 2025-09-14 | Ayansh Const | 11.145 | 1.8575 | TB507 | 145/2 | Completed
2025-09-11 | 2025-09-09 | 2025-09-14 | Dipak | 13.072 | 2.1787 | TB507 | 82/1 | Completed
2025-09-11 | 2025-09-11 | 2025-09-14 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 148/5 | Completed
2025-09-11 | 2025-09-11 | 2025-09-17 | Prayag Saw 1 | 11.997 | 1.7139 | TB507 | 143/5 | Completed
2025-09-11 | 2025-09-11 | 2025-09-17 | Prayag Saw 2 | 11.997 | 1.7139 | TB507 | 143/4 | Completed
2025-09-11 | 2025-08-28 | 2025-09-16 | Windbridge Energy | 11.145 | 0.55725 | TB507 | 133/2 | Completed
2025-09-12 | 2025-09-11 | 2025-09-15 | Ahmed Construction | 11.145 | 2.229 | TB507 | 79/2 | Completed
2025-09-12 | 2025-09-01 | 2025-09-15 | Ajay Kumar 1 | 11.145 | 0.743 | TB507 | 96/1 | Completed
2025-09-12 | 2025-09-11 | 2025-09-21 | Ajay Kumar 2 | 11.997 | 1.0906 | TB507 | 97/1 | Completed
2025-09-12 | 2025-09-09 | 2025-09-14 | Ayansh Const | 11.145 | 1.8575 | TB507 | 145/2 | Completed
2025-09-12 | 2025-09-09 | 2025-09-14 | Dipak | 13.072 | 2.1787 | TB507 | 82/1 | Completed
2025-09-12 | 2025-09-11 | 2025-09-14 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 148/5 | Completed
2025-09-12 | 2025-09-11 | 2025-09-17 | Prayag Saw 1 | 11.997 | 1.7139 | TB507 | 143/5 | Completed
2025-09-12 | 2025-09-11 | 2025-09-17 | Prayag Saw 2 | 11.997 | 1.7139 | TB507 | 143/4 | Completed
2025-09-12 | 2025-08-28 | 2025-09-16 | Windbridge Energy | 11.145 | 0.55725 | TB507 | 133/2 | Completed
2025-09-13 | 2025-09-11 | 2025-09-15 | Ahmed Construction | 11.145 | 2.229 | TB507 | 79/2 | Completed
2025-09-13 | 2025-09-01 | 2025-09-15 | Ajay Kumar 1 | 11.145 | 0.743 | TB507 | 96/1 | Completed
2025-09-13 | 2025-09-11 | 2025-09-21 | Ajay Kumar 2 | 11.997 | 1.0906 | TB507 | 97/1 | Completed
2025-09-13 | 2025-09-09 | 2025-09-14 | Ayansh Const | 11.145 | 1.8575 | TB507 | 145/2 | Completed
2025-09-13 | 2025-09-09 | 2025-09-14 | Dipak | 13.072 | 2.1787 | TB507 | 82/1 | Completed
2025-09-13 | 2025-09-11 | 2025-09-14 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 148/5 | Completed
2025-09-13 | 2025-09-11 | 2025-09-17 | Prayag Saw 1 | 11.997 | 1.7139 | TB507 | 143/5 | Completed
2025-09-13 | 2025-09-11 | 2025-09-17 | Prayag Saw 2 | 11.997 | 1.7139 | TB507 | 143/4 | Completed
2025-09-13 | 2025-08-28 | 2025-09-16 | Windbridge Energy | 11.145 | 0.55725 | TB507 | 133/2 | Completed
2025-09-14 | 2025-09-11 | 2025-09-15 | Ahmed Construction | 11.145 | 2.229 | TB507 | 79/2 | Completed
2025-09-14 | 2025-09-01 | 2025-09-15 | Ajay Kumar 1 | 11.145 | 0.743 | TB507 | 96/1 | Completed
2025-09-14 | 2025-09-11 | 2025-09-21 | Ajay Kumar 2 | 11.997 | 1.0906 | TB507 | 97/1 | Completed
2025-09-14 | 2025-09-09 | 2025-09-14 | Ayansh Const | 11.145 | 1.8575 | TB507 | 145/2 | Completed
2025-09-14 | 2025-09-14 | 2025-09-19 | Ayansh Const | 11.145 | 1.8575 | TB507 | 145/3 | Completed
2025-09-14 | 2025-09-09 | 2025-09-14 | Dipak | 13.072 | 2.1787 | TB507 | 82/1 | Completed
2025-09-14 | 2025-09-14 | 2025-09-21 | Dipak | 18.727 | 2.3409 | TB507 | 113A/0 | Completed
2025-09-14 | 2025-09-11 | 2025-09-14 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 148/5 | Completed
2025-09-14 | 2025-09-14 | 2025-09-19 | Gokul Sarkar | 11.145 | 1.8575 | TB507 | 148/6 | Completed
2025-09-14 | 2025-09-11 | 2025-09-17 | Prayag Saw 1 | 11.997 | 1.7139 | TB507 | 143/5 | Completed
2025-09-14 | 2025-09-11 | 2025-09-17 | Prayag Saw 2 | 11.997 | 1.7139 | TB507 | 143/4 | Completed
2025-09-14 | 2025-08-28 | 2025-09-16 | Windbridge Energy | 11.145 | 0.55725 | TB507 | 133/2 | Completed
2025-09-15 | 2025-09-11 | 2025-09-15 | Ahmed Construction | 11.145 | 2.229 | TB507 | 79/2 | Completed
2025-09-15 | 2025-09-01 | 2025-09-15 | Ajay Kumar 1 | 11.145 | 0.743 | TB507 | 96/1 | Completed
2025-09-15 | 2025-09-15 | 2025-09-24 | Ajay Kumar 1 | 11.145 | 1.1145 | TB507 | 98/1 | Completed
2025-09-15 | 2025-09-11 | 2025-09-21 | Ajay Kumar 2 | 11.997 | 1.0906 | TB507 | 97/1 | Completed
2025-09-15 | 2025-09-14 | 2025-09-19 | Ayansh Const | 11.145 | 1.8575 | TB507 | 145/3 | Completed
2025-09-15 | 2025-09-14 | 2025-09-21 | Dipak | 18.727 | 2.3409 | TB507 | 113A/0 | Completed
2025-09-15 | 2025-09-14 | 2025-09-19 | Gokul Sarkar | 11.145 | 1.8575 | TB507 | 148/6 | Completed
2025-09-15 | 2025-09-11 | 2025-09-17 | Prayag Saw 1 | 11.997 | 1.7139 | TB507 | 143/5 | Completed
2025-09-15 | 2025-09-11 | 2025-09-17 | Prayag Saw 2 | 11.997 | 1.7139 | TB507 | 143/4 | Completed
2025-09-15 | 2025-08-28 | 2025-09-16 | Windbridge Energy | 11.145 | 0.55725 | TB507 | 133/2 | Completed
2025-09-16 | 2025-09-15 | 2025-09-24 | Ajay Kumar 1 | 11.145 | 1.1145 | TB507 | 98/1 | Completed
2025-09-16 | 2025-09-11 | 2025-09-21 | Ajay Kumar 2 | 11.997 | 1.0906 | TB507 | 97/1 | Completed
2025-09-16 | 2025-09-14 | 2025-09-19 | Ayansh Const | 11.145 | 1.8575 | TB507 | 145/3 | Completed
2025-09-16 | 2025-09-14 | 2025-09-21 | Dipak | 18.727 | 2.3409 | TB507 | 113A/0 | Completed
2025-09-16 | 2025-09-14 | 2025-09-19 | Gokul Sarkar | 11.145 | 1.8575 | TB507 | 148/6 | Completed
2025-09-16 | 2025-09-11 | 2025-09-17 | Prayag Saw 1 | 11.997 | 1.7139 | TB507 | 143/5 | Completed
2025-09-16 | 2025-09-11 | 2025-09-17 | Prayag Saw 2 | 11.997 | 1.7139 | TB507 | 143/4 | Completed
2025-09-16 | 2025-08-28 | 2025-09-16 | Windbridge Energy | 11.145 | 0.55725 | TB507 | 133/2 | Completed
2025-09-17 | 2025-09-15 | 2025-09-24 | Ajay Kumar 1 | 11.145 | 1.1145 | TB507 | 98/1 | Completed
2025-09-17 | 2025-09-11 | 2025-09-21 | Ajay Kumar 2 | 11.997 | 1.0906 | TB507 | 97/1 | Completed
2025-09-17 | 2025-09-14 | 2025-09-19 | Ayansh Const | 11.145 | 1.8575 | TB507 | 145/3 | Completed
2025-09-17 | 2025-09-14 | 2025-09-21 | Dipak | 18.727 | 2.3409 | TB507 | 113A/0 | Completed
2025-09-17 | 2025-09-14 | 2025-09-19 | Gokul Sarkar | 11.145 | 1.8575 | TB507 | 148/6 | Completed
2025-09-17 | 2025-09-11 | 2025-09-17 | Prayag Saw 1 | 11.997 | 1.7139 | TB507 | 143/5 | Completed
2025-09-17 | 2025-09-11 | 2025-09-17 | Prayag Saw 2 | 11.997 | 1.7139 | TB507 | 143/4 | Completed
2025-09-17 | 2025-09-17 | 2025-09-22 | Windbridge Energy | 11.145 | 1.8575 | TB507 | 133/3 | Completed
2025-09-18 | 2025-09-15 | 2025-09-24 | Ajay Kumar 1 | 11.145 | 1.1145 | TB507 | 98/1 | Completed
2025-09-18 | 2025-09-11 | 2025-09-21 | Ajay Kumar 2 | 11.997 | 1.0906 | TB507 | 97/1 | Completed
2025-09-18 | 2025-09-14 | 2025-09-19 | Ayansh Const | 11.145 | 1.8575 | TB507 | 145/3 | Completed
2025-09-18 | 2025-09-14 | 2025-09-21 | Dipak | 18.727 | 2.3409 | TB507 | 113A/0 | Completed
2025-09-18 | 2025-09-14 | 2025-09-19 | Gokul Sarkar | 11.145 | 1.8575 | TB507 | 148/6 | Completed
2025-09-18 | 2025-09-18 | 2025-09-20 | Prayag Saw 1 | 11.145 | 3.715 | TB507 | 143/2 | Completed
2025-09-18 | 2025-09-18 | 2025-09-20 | Prayag Saw 2 | 11.145 | 3.715 | TB507 | 143/6 | Completed
2025-09-18 | 2025-09-17 | 2025-09-22 | Windbridge Energy | 11.145 | 1.8575 | TB507 | 133/3 | Completed
2025-09-19 | 2025-09-19 | 2025-09-27 | Ahmed Construction | 13.072 | 1.4524 | TB507 | 76/1 | Completed
2025-09-19 | 2025-09-15 | 2025-09-24 | Ajay Kumar 1 | 11.145 | 1.1145 | TB507 | 98/1 | Completed
2025-09-19 | 2025-09-11 | 2025-09-21 | Ajay Kumar 2 | 11.997 | 1.0906 | TB507 | 97/1 | Completed
2025-09-19 | 2025-09-14 | 2025-09-19 | Ayansh Const | 11.145 | 1.8575 | TB507 | 145/3 | Completed
2025-09-19 | 2025-09-14 | 2025-09-21 | Dipak | 18.727 | 2.3409 | TB507 | 113A/0 | Completed
2025-09-19 | 2025-09-14 | 2025-09-19 | Gokul Sarkar | 11.145 | 1.8575 | TB507 | 148/6 | Completed
2025-09-19 | 2025-09-18 | 2025-09-20 | Prayag Saw 1 | 11.145 | 3.715 | TB507 | 143/2 | Completed
2025-09-19 | 2025-09-18 | 2025-09-20 | Prayag Saw 2 | 11.145 | 3.715 | TB507 | 143/6 | Completed
2025-09-19 | 2025-09-17 | 2025-09-22 | Windbridge Energy | 11.145 | 1.8575 | TB507 | 133/3 | Completed
2025-09-20 | 2025-09-19 | 2025-09-27 | Ahmed Construction | 13.072 | 1.4524 | TB507 | 76/1 | Completed
2025-09-20 | 2025-09-15 | 2025-09-24 | Ajay Kumar 1 | 11.145 | 1.1145 | TB507 | 98/1 | Completed
2025-09-20 | 2025-09-11 | 2025-09-21 | Ajay Kumar 2 | 11.997 | 1.0906 | TB507 | 97/1 | Completed
2025-09-20 | 2025-09-20 | 2025-09-30 | Chandra Sekhar | 11.997 | 1.0906 | TB507 | 145/4 | Completed
2025-09-20 | 2025-09-14 | 2025-09-21 | Dipak | 18.727 | 2.3409 | TB507 | 113A/0 | Completed
2025-09-20 | 2025-09-20 | 2025-09-23 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 148/7 | Completed
2025-09-20 | 2025-09-18 | 2025-09-20 | Prayag Saw 1 | 11.145 | 3.715 | TB507 | 143/2 | Completed
2025-09-20 | 2025-09-18 | 2025-09-20 | Prayag Saw 2 | 11.145 | 3.715 | TB507 | 143/6 | Completed
2025-09-20 | 2025-09-17 | 2025-09-22 | Windbridge Energy | 11.145 | 1.8575 | TB507 | 133/3 | Completed
2025-09-21 | 2025-09-19 | 2025-09-27 | Ahmed Construction | 13.072 | 1.4524 | TB507 | 76/1 | Completed
2025-09-21 | 2025-09-15 | 2025-09-24 | Ajay Kumar 1 | 11.145 | 1.1145 | TB507 | 98/1 | Completed
2025-09-21 | 2025-09-11 | 2025-09-21 | Ajay Kumar 2 | 11.997 | 1.0906 | TB507 | 97/1 | Completed
2025-09-21 | 2025-09-20 | 2025-09-30 | Chandra Sekhar | 11.997 | 1.0906 | TB507 | 145/4 | Completed
2025-09-21 | 2025-09-14 | 2025-09-21 | Dipak | 18.727 | 2.3409 | TB507 | 113A/0 | Completed
2025-09-21 | 2025-09-20 | 2025-09-23 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 148/7 | Completed
2025-09-21 | 2025-09-21 | 2025-09-23 | Prayag Saw 1 | 11.997 | 3.999 | TB507 | 143/3 | Completed
2025-09-21 | 2025-09-21 | 2025-09-23 | Prayag Saw 2 | 13.072 | 4.3573 | TB507 | 143/7 | Completed
2025-09-21 | 2025-09-17 | 2025-09-22 | Windbridge Energy | 11.145 | 1.8575 | TB507 | 133/3 | Completed
2025-09-22 | 2025-09-19 | 2025-09-27 | Ahmed Construction | 13.072 | 1.4524 | TB507 | 76/1 | Completed
2025-09-22 | 2025-09-15 | 2025-09-24 | Ajay Kumar 1 | 11.145 | 1.1145 | TB507 | 98/1 | Completed
2025-09-22 | 2025-09-20 | 2025-09-30 | Chandra Sekhar | 11.997 | 1.0906 | TB507 | 145/4 | Completed
2025-09-22 | 2025-09-20 | 2025-09-23 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 148/7 | Completed
2025-09-22 | 2025-09-21 | 2025-09-23 | Prayag Saw 1 | 11.997 | 3.999 | TB507 | 143/3 | Completed
2025-09-22 | 2025-09-21 | 2025-09-23 | Prayag Saw 2 | 13.072 | 4.3573 | TB507 | 143/7 | Completed
2025-09-22 | 2025-09-22 | 2025-09-27 | Prayag Saw 2 | 13.072 | 2.1787 | TB507 | 143/1 | Completed
2025-09-22 | 2025-09-17 | 2025-09-22 | Windbridge Energy | 11.145 | 1.8575 | TB507 | 133/3 | Completed
2025-09-23 | 2025-09-19 | 2025-09-27 | Ahmed Construction | 13.072 | 1.4524 | TB507 | 76/1 | Completed
2025-09-23 | 2025-09-15 | 2025-09-24 | Ajay Kumar 1 | 11.145 | 1.1145 | TB507 | 98/1 | Completed
2025-09-23 | 2025-09-23 | 2025-09-30 | Ajay Kumar 2 | 11.145 | 1.3931 | TB507 | 98A/1 | Completed
2025-09-23 | 2025-09-20 | 2025-09-30 | Chandra Sekhar | 11.997 | 1.0906 | TB507 | 145/4 | Completed
2025-09-23 | 2025-09-20 | 2025-09-23 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 148/7 | Completed
2025-09-23 | 2025-09-21 | 2025-09-23 | Prayag Saw 1 | 11.997 | 3.999 | TB507 | 143/3 | Completed
2025-09-23 | 2025-09-21 | 2025-09-23 | Prayag Saw 2 | 13.072 | 4.3573 | TB507 | 143/7 | Completed
2025-09-23 | 2025-09-22 | 2025-09-27 | Prayag Saw 2 | 13.072 | 2.1787 | TB507 | 143/1 | Completed
2025-09-23 | 2025-09-23 | 2025-09-29 | Windbridge Energy | 11.997 | 1.7139 | TB507 | 133/6 | Completed
2025-09-24 | 2025-09-19 | 2025-09-27 | Ahmed Construction | 13.072 | 1.4524 | TB507 | 76/1 | Completed
2025-09-24 | 2025-09-15 | 2025-09-24 | Ajay Kumar 1 | 11.145 | 1.1145 | TB507 | 98/1 | Completed
2025-09-24 | 2025-09-23 | 2025-09-30 | Ajay Kumar 2 | 11.145 | 1.3931 | TB507 | 98A/1 | Completed
2025-09-24 | 2025-09-20 | 2025-09-30 | Chandra Sekhar | 11.997 | 1.0906 | TB507 | 145/4 | Completed
2025-09-24 | 2025-09-24 | 2025-09-26 | Dipak | 13.958 | 4.6527 | TB507 | 114/1 | Completed
2025-09-24 | 2025-09-24 | 2025-09-27 | Gokul Sarkar | 11.997 | 2.9992 | TB507 | 149B/1 | Completed
2025-09-24 | 2025-09-24 | 2025-09-27 | Prayag Saw 1 | 13.072 | 3.268 | TB507 | 141/2 | Completed
2025-09-24 | 2025-09-22 | 2025-09-27 | Prayag Saw 2 | 13.072 | 2.1787 | TB507 | 143/1 | Completed
2025-09-24 | 2025-09-23 | 2025-09-29 | Windbridge Energy | 11.997 | 1.7139 | TB507 | 133/6 | Completed
2025-09-25 | 2025-09-19 | 2025-09-27 | Ahmed Construction | 13.072 | 1.4524 | TB507 | 76/1 | Completed
2025-09-25 | 2025-09-23 | 2025-09-30 | Ajay Kumar 2 | 11.145 | 1.3931 | TB507 | 98A/1 | Completed
2025-09-25 | 2025-09-20 | 2025-09-30 | Chandra Sekhar | 11.997 | 1.0906 | TB507 | 145/4 | Completed
2025-09-25 | 2025-09-24 | 2025-09-26 | Dipak | 13.958 | 4.6527 | TB507 | 114/1 | Completed
2025-09-25 | 2025-09-24 | 2025-09-27 | Gokul Sarkar | 11.997 | 2.9992 | TB507 | 149B/1 | Completed
2025-09-25 | 2025-09-24 | 2025-09-27 | Prayag Saw 1 | 13.072 | 3.268 | TB507 | 141/2 | Completed
2025-09-25 | 2025-09-22 | 2025-09-27 | Prayag Saw 2 | 13.072 | 2.1787 | TB507 | 143/1 | Completed
2025-09-25 | 2025-09-23 | 2025-09-29 | Windbridge Energy | 11.997 | 1.7139 | TB507 | 133/6 | Completed
2025-09-26 | 2025-09-19 | 2025-09-27 | Ahmed Construction | 13.072 | 1.4524 | TB507 | 76/1 | Completed
2025-09-26 | 2025-09-26 | 2025-10-15 | Ajay Kumar | 18.727 | 0.93635 | TB507 | 98A/0 | Completed
2025-09-26 | 2025-09-23 | 2025-09-30 | Ajay Kumar 2 | 11.145 | 1.3931 | TB507 | 98A/1 | Completed
2025-09-26 | 2025-09-20 | 2025-09-30 | Chandra Sekhar | 11.997 | 1.0906 | TB507 | 145/4 | Completed
2025-09-26 | 2025-09-24 | 2025-09-26 | Dipak | 13.958 | 4.6527 | TB507 | 114/1 | Completed
2025-09-26 | 2025-09-24 | 2025-09-27 | Gokul Sarkar | 11.997 | 2.9992 | TB507 | 149B/1 | Completed
2025-09-26 | 2025-09-24 | 2025-09-27 | Prayag Saw 1 | 13.072 | 3.268 | TB507 | 141/2 | Completed
2025-09-26 | 2025-09-22 | 2025-09-27 | Prayag Saw 2 | 13.072 | 2.1787 | TB507 | 143/1 | Completed
2025-09-26 | 2025-09-23 | 2025-09-29 | Windbridge Energy | 11.997 | 1.7139 | TB507 | 133/6 | Completed
2025-09-27 | 2025-09-19 | 2025-09-27 | Ahmed Construction | 13.072 | 1.4524 | TB507 | 76/1 | Completed
2025-09-27 | 2025-09-26 | 2025-10-15 | Ajay Kumar | 18.727 | 0.93635 | TB507 | 98A/0 | Completed
2025-09-27 | 2025-09-23 | 2025-09-30 | Ajay Kumar 2 | 11.145 | 1.3931 | TB507 | 98A/1 | Completed
2025-09-27 | 2025-09-20 | 2025-09-30 | Chandra Sekhar | 11.997 | 1.0906 | TB507 | 145/4 | Completed
2025-09-27 | 2025-09-27 | 2025-09-29 | Dipak | 11.145 | 3.715 | TB507 | 116/1 | Completed
2025-09-27 | 2025-09-24 | 2025-09-27 | Gokul Sarkar | 11.997 | 2.9992 | TB507 | 149B/1 | Completed
2025-09-27 | 2025-09-27 | 2025-09-30 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 149B/2 | Completed
2025-09-27 | 2025-09-24 | 2025-09-27 | Prayag Saw 1 | 13.072 | 3.268 | TB507 | 141/2 | Completed
2025-09-27 | 2025-09-27 | 2025-09-30 | Prayag Saw 1 | 11.145 | 2.7862 | TB507 | 141/1 | Completed
2025-09-27 | 2025-09-22 | 2025-09-27 | Prayag Saw 2 | 13.072 | 2.1787 | TB507 | 143/1 | Completed
2025-09-27 | 2025-09-27 | 2025-09-30 | Prayag Saw 2 | 18.9798 | 4.745 | TB507 | 143/0 | Completed
2025-09-27 | 2025-09-23 | 2025-09-29 | Windbridge Energy | 11.997 | 1.7139 | TB507 | 133/6 | Completed
2025-09-28 | 2025-09-26 | 2025-10-15 | Ajay Kumar | 18.727 | 0.93635 | TB507 | 98A/0 | Completed
2025-09-28 | 2025-09-23 | 2025-09-30 | Ajay Kumar 2 | 11.145 | 1.3931 | TB507 | 98A/1 | Completed
2025-09-28 | 2025-09-20 | 2025-09-30 | Chandra Sekhar | 11.997 | 1.0906 | TB507 | 145/4 | Completed
2025-09-28 | 2025-09-27 | 2025-09-29 | Dipak | 11.145 | 3.715 | TB507 | 116/1 | Completed
2025-09-28 | 2025-09-27 | 2025-09-30 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 149B/2 | Completed
2025-09-28 | 2025-09-27 | 2025-09-30 | Prayag Saw 1 | 11.145 | 2.7862 | TB507 | 141/1 | Completed
2025-09-28 | 2025-09-27 | 2025-09-30 | Prayag Saw 2 | 18.9798 | 4.745 | TB507 | 143/0 | Completed
2025-09-28 | 2025-09-23 | 2025-09-29 | Windbridge Energy | 11.997 | 1.7139 | TB507 | 133/6 | Completed
2025-09-29 | 2025-09-26 | 2025-10-15 | Ajay Kumar | 18.727 | 0.93635 | TB507 | 98A/0 | Completed
2025-09-29 | 2025-09-23 | 2025-09-30 | Ajay Kumar 2 | 11.145 | 1.3931 | TB507 | 98A/1 | Completed
2025-09-29 | 2025-09-20 | 2025-09-30 | Chandra Sekhar | 11.997 | 1.0906 | TB507 | 145/4 | Completed
2025-09-29 | 2025-09-27 | 2025-09-29 | Dipak | 11.145 | 3.715 | TB507 | 116/1 | Completed
2025-09-29 | 2025-09-27 | 2025-09-30 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 149B/2 | Completed
2025-09-29 | 2025-09-27 | 2025-09-30 | Prayag Saw 1 | 11.145 | 2.7862 | TB507 | 141/1 | Completed
2025-09-29 | 2025-09-27 | 2025-09-30 | Prayag Saw 2 | 18.9798 | 4.745 | TB507 | 143/0 | Completed
2025-09-29 | 2025-09-23 | 2025-09-29 | Windbridge Energy | 11.997 | 1.7139 | TB507 | 133/6 | Completed
2025-09-29 | 2025-09-29 | 2025-10-05 | Windbridge Energy | 11.145 | 1.5921 | TB507 | 133/7 | Completed
2025-09-30 | 2025-09-26 | 2025-10-15 | Ajay Kumar | 18.727 | 0.93635 | TB507 | 98A/0 | Completed
2025-09-30 | 2025-09-23 | 2025-09-30 | Ajay Kumar 2 | 11.145 | 1.3931 | TB507 | 98A/1 | Completed
2025-09-30 | 2025-09-20 | 2025-09-30 | Chandra Sekhar | 11.997 | 1.0906 | TB507 | 145/4 | Completed
2025-09-30 | 2025-09-30 | 2025-10-03 | Chandra Sekhar | 11.997 | 2.9992 | TB507 | 146/1 | Completed
2025-09-30 | 2025-09-30 | 2025-10-07 | Dipak | 21.41 | 2.6763 | TB507 | 116/0 | Completed
2025-09-30 | 2025-09-27 | 2025-09-30 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 149B/2 | Completed
2025-09-30 | 2025-09-30 | 2025-10-03 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 147/7 | Completed
2025-09-30 | 2025-09-27 | 2025-09-30 | Prayag Saw 1 | 11.145 | 2.7862 | TB507 | 141/1 | Completed
2025-09-30 | 2025-09-27 | 2025-09-30 | Prayag Saw 2 | 18.9798 | 4.745 | TB507 | 143/0 | Completed
2025-09-30 | 2025-09-29 | 2025-10-05 | Windbridge Energy | 11.145 | 1.5921 | TB507 | 133/7 | Completed
2025-10-01 | 2025-09-26 | 2025-10-15 | Ajay Kumar | 18.727 | 0.93635 | TB507 | 98A/0 | Completed
2025-10-01 | 2025-09-30 | 2025-10-03 | Chandra Sekhar | 11.997 | 2.9992 | TB507 | 146/1 | Completed
2025-10-01 | 2025-09-30 | 2025-10-07 | Dipak | 21.41 | 2.6763 | TB507 | 116/0 | Completed
2025-10-01 | 2025-09-30 | 2025-10-03 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 147/7 | Completed
2025-10-01 | 2025-10-01 | 2025-10-07 | Prayag Saw 1 | 18.9798 | 2.7114 | TB507 | 142/0 | Completed
2025-10-01 | 2025-10-01 | 2025-10-08 | Prayag Saw 2 | 26.291 | 3.2864 | TB507 | 144/0 | Completed
2025-10-01 | 2025-09-29 | 2025-10-05 | Windbridge Energy | 11.145 | 1.5921 | TB507 | 133/7 | Completed
2025-10-02 | 2025-09-26 | 2025-10-15 | Ajay Kumar | 18.727 | 0.93635 | TB507 | 98A/0 | Completed
2025-10-02 | 2025-09-30 | 2025-10-03 | Chandra Sekhar | 11.997 | 2.9992 | TB507 | 146/1 | Completed
2025-10-02 | 2025-09-30 | 2025-10-07 | Dipak | 21.41 | 2.6763 | TB507 | 116/0 | Completed
2025-10-02 | 2025-09-30 | 2025-10-03 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 147/7 | Completed
2025-10-02 | 2025-10-01 | 2025-10-07 | Prayag Saw 1 | 18.9798 | 2.7114 | TB507 | 142/0 | Completed
2025-10-02 | 2025-10-01 | 2025-10-08 | Prayag Saw 2 | 26.291 | 3.2864 | TB507 | 144/0 | Completed
2025-10-02 | 2025-09-29 | 2025-10-05 | Windbridge Energy | 11.145 | 1.5921 | TB507 | 133/7 | Completed
2025-10-03 | 2025-09-26 | 2025-10-15 | Ajay Kumar | 18.727 | 0.93635 | TB507 | 98A/0 | Completed
2025-10-03 | 2025-09-30 | 2025-10-03 | Chandra Sekhar | 11.997 | 2.9992 | TB507 | 146/1 | Completed
2025-10-03 | 2025-10-03 | 2025-10-05 | Chandra Sekhar | 11.145 | 3.715 | TB507 | 146/2 | Completed
2025-10-03 | 2025-09-30 | 2025-10-07 | Dipak | 21.41 | 2.6763 | TB507 | 116/0 | Completed
2025-10-03 | 2025-09-30 | 2025-10-03 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 147/7 | Completed
2025-10-03 | 2025-10-03 | 2025-10-10 | Gokul Sarkar | 21.41 | 2.6763 | TB507 | 149/0 | Completed
2025-10-03 | 2025-10-01 | 2025-10-07 | Prayag Saw 1 | 18.9798 | 2.7114 | TB507 | 142/0 | Completed
2025-10-03 | 2025-10-01 | 2025-10-08 | Prayag Saw 2 | 26.291 | 3.2864 | TB507 | 144/0 | Completed
2025-10-03 | 2025-09-29 | 2025-10-05 | Windbridge Energy | 11.145 | 1.5921 | TB507 | 133/7 | Completed
2025-10-04 | 2025-09-26 | 2025-10-15 | Ajay Kumar | 18.727 | 0.93635 | TB507 | 98A/0 | Completed
2025-10-04 | 2025-10-03 | 2025-10-05 | Chandra Sekhar | 11.145 | 3.715 | TB507 | 146/2 | Completed
2025-10-04 | 2025-09-30 | 2025-10-07 | Dipak | 21.41 | 2.6763 | TB507 | 116/0 | Completed
2025-10-04 | 2025-10-03 | 2025-10-10 | Gokul Sarkar | 21.41 | 2.6763 | TB507 | 149/0 | Completed
2025-10-04 | 2025-10-01 | 2025-10-07 | Prayag Saw 1 | 18.9798 | 2.7114 | TB507 | 142/0 | Completed
2025-10-04 | 2025-10-01 | 2025-10-08 | Prayag Saw 2 | 26.291 | 3.2864 | TB507 | 144/0 | Completed
2025-10-04 | 2025-09-29 | 2025-10-05 | Windbridge Energy | 11.145 | 1.5921 | TB507 | 133/7 | Completed
2025-10-05 | 2025-09-26 | 2025-10-15 | Ajay Kumar | 18.727 | 0.93635 | TB507 | 98A/0 | Completed
2025-10-05 | 2025-10-03 | 2025-10-05 | Chandra Sekhar | 11.145 | 3.715 | TB507 | 146/2 | Completed
2025-10-05 | 2025-10-05 | 2025-10-10 | Chandra Sekhar | 18.727 | 3.1212 | TB507 | 146/0 | Completed
2025-10-05 | 2025-09-30 | 2025-10-07 | Dipak | 21.41 | 2.6763 | TB507 | 116/0 | Completed
2025-10-05 | 2025-10-03 | 2025-10-10 | Gokul Sarkar | 21.41 | 2.6763 | TB507 | 149/0 | Completed
2025-10-05 | 2025-10-01 | 2025-10-07 | Prayag Saw 1 | 18.9798 | 2.7114 | TB507 | 142/0 | Completed
2025-10-05 | 2025-10-01 | 2025-10-08 | Prayag Saw 2 | 26.291 | 3.2864 | TB507 | 144/0 | Completed
2025-10-05 | 2025-09-29 | 2025-10-05 | Windbridge Energy | 11.145 | 1.5921 | TB507 | 133/7 | Completed
2025-10-05 | 2025-10-05 | 2025-10-11 | Windbridge Energy | 13.072 | 1.8674 | TB507 | 133/8 | Completed
2025-10-06 | 2025-09-26 | 2025-10-15 | Ajay Kumar | 18.727 | 0.93635 | TB507 | 98A/0 | Completed
2025-10-06 | 2025-10-05 | 2025-10-10 | Chandra Sekhar | 18.727 | 3.1212 | TB507 | 146/0 | Completed
2025-10-06 | 2025-09-30 | 2025-10-07 | Dipak | 21.41 | 2.6763 | TB507 | 116/0 | Completed
2025-10-06 | 2025-10-03 | 2025-10-10 | Gokul Sarkar | 21.41 | 2.6763 | TB507 | 149/0 | Completed
2025-10-06 | 2025-10-01 | 2025-10-07 | Prayag Saw 1 | 18.9798 | 2.7114 | TB507 | 142/0 | Completed
2025-10-06 | 2025-10-01 | 2025-10-08 | Prayag Saw 2 | 26.291 | 3.2864 | TB507 | 144/0 | Completed
2025-10-06 | 2025-10-05 | 2025-10-11 | Windbridge Energy | 13.072 | 1.8674 | TB507 | 133/8 | Completed
2025-10-07 | 2025-09-26 | 2025-10-15 | Ajay Kumar | 18.727 | 0.93635 | TB507 | 98A/0 | Completed
2025-10-07 | 2025-10-05 | 2025-10-10 | Chandra Sekhar | 18.727 | 3.1212 | TB507 | 146/0 | Completed
2025-10-07 | 2025-09-30 | 2025-10-07 | Dipak | 21.41 | 2.6763 | TB507 | 116/0 | Completed
2025-10-07 | 2025-10-03 | 2025-10-10 | Gokul Sarkar | 21.41 | 2.6763 | TB507 | 149/0 | Completed
2025-10-07 | 2025-10-01 | 2025-10-07 | Prayag Saw 1 | 18.9798 | 2.7114 | TB507 | 142/0 | Completed
2025-10-07 | 2025-10-01 | 2025-10-08 | Prayag Saw 2 | 26.291 | 3.2864 | TB507 | 144/0 | Completed
2025-10-07 | 2025-10-05 | 2025-10-11 | Windbridge Energy | 13.072 | 1.8674 | TB507 | 133/8 | Completed
2025-10-08 | 2025-09-26 | 2025-10-15 | Ajay Kumar | 18.727 | 0.93635 | TB507 | 98A/0 | Completed
2025-10-08 | 2025-10-05 | 2025-10-10 | Chandra Sekhar | 18.727 | 3.1212 | TB507 | 146/0 | Completed
2025-10-08 | 2025-10-08 | 2025-10-13 | Dipak | 18.727 | 3.1212 | TB507 | 115/0 | Completed
2025-10-08 | 2025-10-03 | 2025-10-10 | Gokul Sarkar | 21.41 | 2.6763 | TB507 | 149/0 | Completed
2025-10-08 | 2025-10-08 | 2025-10-10 | Prayag Saw 1 | 11.997 | 3.999 | TB507 | 140/2 | Completed
2025-10-08 | 2025-10-01 | 2025-10-08 | Prayag Saw 2 | 26.291 | 3.2864 | TB507 | 144/0 | Completed
2025-10-08 | 2025-10-08 | 2025-10-13 | Prayag Saw 2 | 11.145 | 1.8575 | TB507 | 138/1 | Completed
2025-10-08 | 2025-10-05 | 2025-10-11 | Windbridge Energy | 13.072 | 1.8674 | TB507 | 133/8 | Completed
2025-10-09 | 2025-09-26 | 2025-10-15 | Ajay Kumar | 18.727 | 0.93635 | TB507 | 98A/0 | Completed
2025-10-09 | 2025-10-05 | 2025-10-10 | Chandra Sekhar | 18.727 | 3.1212 | TB507 | 146/0 | Completed
2025-10-09 | 2025-10-08 | 2025-10-13 | Dipak | 18.727 | 3.1212 | TB507 | 115/0 | Completed
2025-10-09 | 2025-10-03 | 2025-10-10 | Gokul Sarkar | 21.41 | 2.6763 | TB507 | 149/0 | Completed
2025-10-09 | 2025-10-08 | 2025-10-10 | Prayag Saw 1 | 11.997 | 3.999 | TB507 | 140/2 | Completed
2025-10-09 | 2025-10-08 | 2025-10-13 | Prayag Saw 2 | 11.145 | 1.8575 | TB507 | 138/1 | Completed
2025-10-09 | 2025-10-05 | 2025-10-11 | Windbridge Energy | 13.072 | 1.8674 | TB507 | 133/8 | Completed
2025-10-10 | 2025-09-26 | 2025-10-15 | Ajay Kumar | 18.727 | 0.93635 | TB507 | 98A/0 | Completed
2025-10-10 | 2025-10-05 | 2025-10-10 | Chandra Sekhar | 18.727 | 3.1212 | TB507 | 146/0 | Completed
2025-10-10 | 2025-10-10 | 2025-10-12 | Chandra Sekhar | 18.727 | 6.2423 | TB507 | 147/0 | Completed
2025-10-10 | 2025-10-08 | 2025-10-13 | Dipak | 18.727 | 3.1212 | TB507 | 115/0 | Completed
2025-10-10 | 2025-10-03 | 2025-10-10 | Gokul Sarkar | 21.41 | 2.6763 | TB507 | 149/0 | Completed
2025-10-10 | 2025-10-10 | 2025-10-15 | Gokul Sarkar | 21.41 | 3.5683 | TB507 | 149A/0 | Completed
2025-10-10 | 2025-10-08 | 2025-10-10 | Prayag Saw 1 | 11.997 | 3.999 | TB507 | 140/2 | Completed
2025-10-10 | 2025-10-10 | 2025-10-11 | Prayag Saw 1 | 11.997 | 5.9985 | TB507 | 140/3 | Completed
2025-10-10 | 2025-10-08 | 2025-10-13 | Prayag Saw 2 | 11.145 | 1.8575 | TB507 | 138/1 | Completed
2025-10-10 | 2025-10-05 | 2025-10-11 | Windbridge Energy | 13.072 | 1.8674 | TB507 | 133/8 | Completed
2025-10-11 | 2025-09-26 | 2025-10-15 | Ajay Kumar | 18.727 | 0.93635 | TB507 | 98A/0 | Completed
2025-10-11 | 2025-10-10 | 2025-10-12 | Chandra Sekhar | 18.727 | 6.2423 | TB507 | 147/0 | Completed
2025-10-11 | 2025-10-08 | 2025-10-13 | Dipak | 18.727 | 3.1212 | TB507 | 115/0 | Completed
2025-10-11 | 2025-10-10 | 2025-10-15 | Gokul Sarkar | 21.41 | 3.5683 | TB507 | 149A/0 | Completed
2025-10-11 | 2025-10-10 | 2025-10-11 | Prayag Saw 1 | 11.997 | 5.9985 | TB507 | 140/3 | Completed
2025-10-11 | 2025-10-11 | 2025-10-16 | Prayag Saw 1 | 18.727 | 3.1212 | TB507 | 141/0 | Completed
2025-10-11 | 2025-10-08 | 2025-10-13 | Prayag Saw 2 | 11.145 | 1.8575 | TB507 | 138/1 | Completed
2025-10-11 | 2025-10-05 | 2025-10-11 | Windbridge Energy | 13.072 | 1.8674 | TB507 | 133/8 | Completed
2025-10-11 | 2025-10-11 | 2025-10-15 | Windbridge Energy | 11.145 | 2.229 | TB507 | 133/4 | Completed
2025-10-12 | 2025-09-26 | 2025-10-15 | Ajay Kumar | 18.727 | 0.93635 | TB507 | 98A/0 | Completed
2025-10-12 | 2025-10-10 | 2025-10-12 | Chandra Sekhar | 18.727 | 6.2423 | TB507 | 147/0 | Completed
2025-10-12 | 2025-10-12 | 2025-10-15 | Chandra Sekhar | 11.145 | 2.7862 | TB507 | 147/3 | Completed
2025-10-12 | 2025-10-08 | 2025-10-13 | Dipak | 18.727 | 3.1212 | TB507 | 115/0 | Completed
2025-10-12 | 2025-10-10 | 2025-10-15 | Gokul Sarkar | 21.41 | 3.5683 | TB507 | 149A/0 | Completed
2025-10-12 | 2025-10-11 | 2025-10-16 | Prayag Saw 1 | 18.727 | 3.1212 | TB507 | 141/0 | Completed
2025-10-12 | 2025-10-08 | 2025-10-13 | Prayag Saw 2 | 11.145 | 1.8575 | TB507 | 138/1 | Completed
2025-10-12 | 2025-10-11 | 2025-10-15 | Windbridge Energy | 11.145 | 2.229 | TB507 | 133/4 | Completed
2025-10-13 | 2025-09-26 | 2025-10-15 | Ajay Kumar | 18.727 | 0.93635 | TB507 | 98A/0 | Completed
2025-10-13 | 2025-10-12 | 2025-10-15 | Chandra Sekhar | 11.145 | 2.7862 | TB507 | 147/3 | Completed
2025-10-13 | 2025-10-08 | 2025-10-13 | Dipak | 18.727 | 3.1212 | TB507 | 115/0 | Completed
2025-10-13 | 2025-10-10 | 2025-10-15 | Gokul Sarkar | 21.41 | 3.5683 | TB507 | 149A/0 | Completed
2025-10-13 | 2025-10-11 | 2025-10-16 | Prayag Saw 1 | 18.727 | 3.1212 | TB507 | 141/0 | Completed
2025-10-13 | 2025-10-08 | 2025-10-13 | Prayag Saw 2 | 11.145 | 1.8575 | TB507 | 138/1 | Completed
2025-10-13 | 2025-10-13 | 2025-10-16 | Prayag Saw 2 | 11.145 | 2.7862 | TB507 | 138/2 | Completed
2025-10-13 | 2025-10-11 | 2025-10-15 | Windbridge Energy | 11.145 | 2.229 | TB507 | 133/4 | Completed
2025-10-14 | 2025-09-26 | 2025-10-15 | Ajay Kumar | 18.727 | 0.93635 | TB507 | 98A/0 | Completed
2025-10-14 | 2025-10-12 | 2025-10-15 | Chandra Sekhar | 11.145 | 2.7862 | TB507 | 147/3 | Completed
2025-10-14 | 2025-10-10 | 2025-10-15 | Gokul Sarkar | 21.41 | 3.5683 | TB507 | 149A/0 | Completed
2025-10-14 | 2025-10-11 | 2025-10-16 | Prayag Saw 1 | 18.727 | 3.1212 | TB507 | 141/0 | Completed
2025-10-14 | 2025-10-13 | 2025-10-16 | Prayag Saw 2 | 11.145 | 2.7862 | TB507 | 138/2 | Completed
2025-10-14 | 2025-10-11 | 2025-10-15 | Windbridge Energy | 11.145 | 2.229 | TB507 | 133/4 | Completed
2025-10-15 | 2025-09-26 | 2025-10-15 | Ajay Kumar | 18.727 | 0.93635 | TB507 | 98A/0 | Completed
2025-10-15 | 2025-10-12 | 2025-10-15 | Chandra Sekhar | 11.145 | 2.7862 | TB507 | 147/3 | Completed
2025-10-15 | 2025-10-15 | 2025-10-19 | Chandra Sekhar | 11.145 | 2.229 | TB507 | 147/2 | Completed
2025-10-15 | 2025-10-10 | 2025-10-15 | Gokul Sarkar | 21.41 | 3.5683 | TB507 | 149A/0 | Completed
2025-10-15 | 2025-10-11 | 2025-10-16 | Prayag Saw 1 | 18.727 | 3.1212 | TB507 | 141/0 | Completed
2025-10-15 | 2025-10-13 | 2025-10-16 | Prayag Saw 2 | 11.145 | 2.7862 | TB507 | 138/2 | Completed
2025-10-15 | 2025-10-11 | 2025-10-15 | Windbridge Energy | 11.145 | 2.229 | TB507 | 133/4 | Completed
2025-10-15 | 2025-10-15 | 2025-10-19 | Windbridge Energy | 11.145 | 2.229 | TB507 | 133/1 | Completed
2025-10-16 | 2025-10-15 | 2025-10-19 | Chandra Sekhar | 11.145 | 2.229 | TB507 | 147/2 | Completed
2025-10-16 | 2025-10-16 | 2025-10-19 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 147/9 | Completed
2025-10-16 | 2025-10-11 | 2025-10-16 | Prayag Saw 1 | 18.727 | 3.1212 | TB507 | 141/0 | Completed
2025-10-16 | 2025-10-16 | 2025-10-23 | Prayag Saw 1 | 21.41 | 2.6763 | TB507 | 134A/0 | Completed
2025-10-16 | 2025-10-13 | 2025-10-16 | Prayag Saw 2 | 11.145 | 2.7862 | TB507 | 138/2 | Completed
2025-10-16 | 2025-10-16 | 2025-10-19 | Prayag Saw 2 | 11.145 | 2.7862 | TB507 | 138/3 | Completed
2025-10-16 | 2025-10-15 | 2025-10-19 | Windbridge Energy | 11.145 | 2.229 | TB507 | 133/1 | Completed
2025-10-17 | 2025-10-15 | 2025-10-19 | Chandra Sekhar | 11.145 | 2.229 | TB507 | 147/2 | Completed
2025-10-17 | 2025-10-16 | 2025-10-19 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 147/9 | Completed
2025-10-17 | 2025-10-16 | 2025-10-23 | Prayag Saw 1 | 21.41 | 2.6763 | TB507 | 134A/0 | Completed
2025-10-17 | 2025-10-16 | 2025-10-19 | Prayag Saw 2 | 11.145 | 2.7862 | TB507 | 138/3 | Completed
2025-10-17 | 2025-10-15 | 2025-10-19 | Windbridge Energy | 11.145 | 2.229 | TB507 | 133/1 | Completed
2025-10-18 | 2025-10-15 | 2025-10-19 | Chandra Sekhar | 11.145 | 2.229 | TB507 | 147/2 | Completed
2025-10-18 | 2025-10-16 | 2025-10-19 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 147/9 | Completed
2025-10-18 | 2025-10-16 | 2025-10-23 | Prayag Saw 1 | 21.41 | 2.6763 | TB507 | 134A/0 | Completed
2025-10-18 | 2025-10-16 | 2025-10-19 | Prayag Saw 2 | 11.145 | 2.7862 | TB507 | 138/3 | Completed
2025-10-18 | 2025-10-15 | 2025-10-19 | Windbridge Energy | 11.145 | 2.229 | TB507 | 133/1 | Completed
2025-10-19 | 2025-10-15 | 2025-10-19 | Chandra Sekhar | 11.145 | 2.229 | TB507 | 147/2 | Completed
2025-10-19 | 2025-10-19 | 2025-10-22 | Chandra Sekhar | 11.145 | 2.7862 | TB507 | 147/1 | Completed
2025-10-19 | 2025-10-19 | 2025-10-27 | Dipak | 24.1826 | 2.687 | TB507 | 112/0 | Completed
2025-10-19 | 2025-10-16 | 2025-10-19 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 147/9 | Completed
2025-10-19 | 2025-10-19 | 2025-10-22 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 147/8 | Completed
2025-10-19 | 2025-10-19 | 2025-10-24 | Namechand Mahto | 11.145 | 1.8575 | TB507 | 82/2 | Completed
2025-10-19 | 2025-10-16 | 2025-10-23 | Prayag Saw 1 | 21.41 | 2.6763 | TB507 | 134A/0 | Completed
2025-10-19 | 2025-10-16 | 2025-10-19 | Prayag Saw 2 | 11.145 | 2.7862 | TB507 | 138/3 | Completed
2025-10-19 | 2025-10-19 | 2025-10-24 | Prayag Saw 2 | 18.1115 | 3.0186 | TB507 | 138/0 | Completed
2025-10-19 | 2025-10-15 | 2025-10-19 | Windbridge Energy | 11.145 | 2.229 | TB507 | 133/1 | Completed
2025-10-19 | 2025-10-19 | 2025-10-24 | Windbridge Energy | 11.145 | 1.8575 | TB507 | 135/1 | Completed
2025-10-20 | 2025-10-19 | 2025-10-22 | Chandra Sekhar | 11.145 | 2.7862 | TB507 | 147/1 | Completed
2025-10-20 | 2025-10-19 | 2025-10-27 | Dipak | 24.1826 | 2.687 | TB507 | 112/0 | Completed
2025-10-20 | 2025-10-19 | 2025-10-22 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 147/8 | Completed
2025-10-20 | 2025-10-19 | 2025-10-24 | Namechand Mahto | 11.145 | 1.8575 | TB507 | 82/2 | Completed
2025-10-20 | 2025-10-16 | 2025-10-23 | Prayag Saw 1 | 21.41 | 2.6763 | TB507 | 134A/0 | Completed
2025-10-20 | 2025-10-19 | 2025-10-24 | Prayag Saw 2 | 18.1115 | 3.0186 | TB507 | 138/0 | Completed
2025-10-20 | 2025-10-19 | 2025-10-24 | Windbridge Energy | 11.145 | 1.8575 | TB507 | 135/1 | Completed
2025-10-21 | 2025-10-19 | 2025-10-22 | Chandra Sekhar | 11.145 | 2.7862 | TB507 | 147/1 | Completed
2025-10-21 | 2025-10-19 | 2025-10-27 | Dipak | 24.1826 | 2.687 | TB507 | 112/0 | Completed
2025-10-21 | 2025-10-19 | 2025-10-22 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 147/8 | Completed
2025-10-21 | 2025-10-19 | 2025-10-24 | Namechand Mahto | 11.145 | 1.8575 | TB507 | 82/2 | Completed
2025-10-21 | 2025-10-16 | 2025-10-23 | Prayag Saw 1 | 21.41 | 2.6763 | TB507 | 134A/0 | Completed
2025-10-21 | 2025-10-19 | 2025-10-24 | Prayag Saw 2 | 18.1115 | 3.0186 | TB507 | 138/0 | Completed
2025-10-21 | 2025-10-19 | 2025-10-24 | Windbridge Energy | 11.145 | 1.8575 | TB507 | 135/1 | Completed
2025-10-22 | 2025-10-19 | 2025-10-22 | Chandra Sekhar | 11.145 | 2.7862 | TB507 | 147/1 | Completed
2025-10-22 | 2025-10-19 | 2025-10-27 | Dipak | 24.1826 | 2.687 | TB507 | 112/0 | Completed
2025-10-22 | 2025-10-19 | 2025-10-22 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 147/8 | Completed
2025-10-22 | 2025-10-19 | 2025-10-24 | Namechand Mahto | 11.145 | 1.8575 | TB507 | 82/2 | Completed
2025-10-22 | 2025-10-16 | 2025-10-23 | Prayag Saw 1 | 21.41 | 2.6763 | TB507 | 134A/0 | Completed
2025-10-22 | 2025-10-19 | 2025-10-24 | Prayag Saw 2 | 18.1115 | 3.0186 | TB507 | 138/0 | Completed
2025-10-22 | 2025-10-19 | 2025-10-24 | Windbridge Energy | 11.145 | 1.8575 | TB507 | 135/1 | Completed
2025-10-23 | 2025-10-23 | 2025-10-26 | Chandra Sekhar |  |  | TB507 | 147/6 | Completed
2025-10-23 | 2025-10-19 | 2025-10-27 | Dipak | 24.1826 | 2.687 | TB507 | 112/0 | Completed
2025-10-23 | 2025-10-23 | 2025-10-27 | Gokul Sarkar |  |  | TB507 | 148/1 | Completed
2025-10-23 | 2025-10-19 | 2025-10-24 | Namechand Mahto | 11.145 | 1.8575 | TB507 | 82/2 | Completed
2025-10-23 | 2025-10-16 | 2025-10-23 | Prayag Saw 1 | 21.41 | 2.6763 | TB507 | 134A/0 | Completed
2025-10-23 | 2025-10-19 | 2025-10-24 | Prayag Saw 2 | 18.1115 | 3.0186 | TB507 | 138/0 | Completed
2025-10-23 | 2025-10-19 | 2025-10-24 | Windbridge Energy | 11.145 | 1.8575 | TB507 | 135/1 | Completed
2025-10-24 | 2025-10-23 | 2025-10-26 | Chandra Sekhar |  |  | TB507 | 147/6 | Completed
2025-10-24 | 2025-10-19 | 2025-10-27 | Dipak | 24.1826 | 2.687 | TB507 | 112/0 | Completed
2025-10-24 | 2025-10-23 | 2025-10-27 | Gokul Sarkar |  |  | TB507 | 148/1 | Completed
2025-10-24 | 2025-10-19 | 2025-10-24 | Namechand Mahto | 11.145 | 1.8575 | TB507 | 82/2 | Completed
2025-10-24 | 2025-10-24 | 2025-10-31 | Namechand Mahto | 18.727 | 2.3409 | TB507 | 76/0 | Completed
2025-10-24 | 2025-10-24 | 2025-10-26 | Prayag Saw 1 | 11.997 | 3.999 | TB507 | 134A/2 | Completed
2025-10-24 | 2025-10-19 | 2025-10-24 | Prayag Saw 2 | 18.1115 | 3.0186 | TB507 | 138/0 | Completed
2025-10-24 | 2025-10-19 | 2025-10-24 | Windbridge Energy | 11.145 | 1.8575 | TB507 | 135/1 | Completed
2025-10-24 | 2025-10-24 | 2025-10-31 | Windbridge Energy | 18.727 | 2.3409 | TB507 | 133/0 | Completed
2025-10-25 | 2025-10-23 | 2025-10-26 | Chandra Sekhar |  |  | TB507 | 147/6 | Completed
2025-10-25 | 2025-10-19 | 2025-10-27 | Dipak | 24.1826 | 2.687 | TB507 | 112/0 | Completed
2025-10-25 | 2025-10-23 | 2025-10-27 | Gokul Sarkar |  |  | TB507 | 148/1 | Completed
2025-10-25 | 2025-10-24 | 2025-10-31 | Namechand Mahto | 18.727 | 2.3409 | TB507 | 76/0 | Completed
2025-10-25 | 2025-10-24 | 2025-10-26 | Prayag Saw 1 | 11.997 | 3.999 | TB507 | 134A/2 | Completed
2025-10-25 | 2025-10-24 | 2025-10-31 | Windbridge Energy | 18.727 | 2.3409 | TB507 | 133/0 | Completed
2025-10-26 | 2025-10-23 | 2025-10-26 | Chandra Sekhar |  |  | TB507 | 147/6 | Completed
2025-10-26 | 2025-10-19 | 2025-10-27 | Dipak | 24.1826 | 2.687 | TB507 | 112/0 | Completed
2025-10-26 | 2025-10-23 | 2025-10-27 | Gokul Sarkar |  |  | TB507 | 148/1 | Completed
2025-10-26 | 2025-10-24 | 2025-10-31 | Namechand Mahto | 18.727 | 2.3409 | TB507 | 76/0 | Completed
2025-10-26 | 2025-10-24 | 2025-10-26 | Prayag Saw 1 | 11.997 | 3.999 | TB507 | 134A/2 | Completed
2025-10-26 | 2025-10-26 | 2025-10-28 | Prayag Saw 1 |  |  | TB507 | 139/0 | Completed
2025-10-26 | 2025-10-24 | 2025-10-31 | Windbridge Energy | 18.727 | 2.3409 | TB507 | 133/0 | Completed
2025-10-27 | 2025-10-27 | 2025-10-28 | Chandra Sekhar |  |  | TB507 | 147/5 | Completed
2025-10-27 | 2025-10-19 | 2025-10-27 | Dipak | 24.1826 | 2.687 | TB507 | 112/0 | Completed
2025-10-27 | 2025-10-27 | 2025-11-02 | Dipak |  |  | TB507 | 115/1 | Completed
2025-10-27 | 2025-10-23 | 2025-10-27 | Gokul Sarkar |  |  | TB507 | 148/1 | Completed
2025-10-27 | 2025-10-27 | 2025-11-01 | Gokul Sarkar |  |  | TB507 | 153A/0 | Completed
2025-10-27 | 2025-10-24 | 2025-10-31 | Namechand Mahto | 18.727 | 2.3409 | TB507 | 76/0 | Completed
2025-10-27 | 2025-10-26 | 2025-10-28 | Prayag Saw 1 |  |  | TB507 | 139/0 | Completed
2025-10-27 | 2025-10-27 | 2025-10-29 | Prayag Saw 2 |  |  | TB507 | 134/0 | Completed
2025-10-27 | 2025-10-24 | 2025-10-31 | Windbridge Energy | 18.727 | 2.3409 | TB507 | 133/0 | Completed
2025-10-28 | 2025-10-27 | 2025-10-28 | Chandra Sekhar |  |  | TB507 | 147/5 | Completed
2025-10-28 | 2025-10-28 | 2025-10-31 | Chandra Sekhar |  |  | TB507 | 147/4 | Completed
2025-10-28 | 2025-10-27 | 2025-11-02 | Dipak |  |  | TB507 | 115/1 | Completed
2025-10-28 | 2025-10-27 | 2025-11-01 | Gokul Sarkar |  |  | TB507 | 153A/0 | Completed
2025-10-28 | 2025-10-24 | 2025-10-31 | Namechand Mahto | 18.727 | 2.3409 | TB507 | 76/0 | Completed
2025-10-28 | 2025-10-26 | 2025-10-28 | Prayag Saw 1 |  |  | TB507 | 139/0 | Completed
2025-10-28 | 2025-10-27 | 2025-10-29 | Prayag Saw 2 |  |  | TB507 | 134/0 | Completed
2025-10-28 | 2025-10-24 | 2025-10-31 | Windbridge Energy | 18.727 | 2.3409 | TB507 | 133/0 | Completed
2025-10-29 | 2025-10-28 | 2025-10-31 | Chandra Sekhar |  |  | TB507 | 147/4 | Completed
2025-10-29 | 2025-10-27 | 2025-11-02 | Dipak |  |  | TB507 | 115/1 | Completed
2025-10-29 | 2025-10-27 | 2025-11-01 | Gokul Sarkar |  |  | TB507 | 153A/0 | Completed
2025-10-29 | 2025-10-24 | 2025-10-31 | Namechand Mahto | 18.727 | 2.3409 | TB507 | 76/0 | Completed
2025-10-29 | 2025-10-29 | 2025-11-02 | Prayag Saw 1 |  |  | TB507 | 135/0 | Completed
2025-10-29 | 2025-10-27 | 2025-10-29 | Prayag Saw 2 |  |  | TB507 | 134/0 | Completed
2025-10-29 | 2025-10-29 | 2025-11-03 | Prayag Saw 2 |  |  | TB507 | 134A/1 | Completed
2025-10-29 | 2025-10-24 | 2025-10-31 | Windbridge Energy | 18.727 | 2.3409 | TB507 | 133/0 | Completed
2025-10-30 | 2025-10-28 | 2025-10-31 | Chandra Sekhar |  |  | TB507 | 147/4 | Completed
2025-10-30 | 2025-10-27 | 2025-11-02 | Dipak |  |  | TB507 | 115/1 | Completed
2025-10-30 | 2025-10-27 | 2025-11-01 | Gokul Sarkar |  |  | TB507 | 153A/0 | Completed
2025-10-30 | 2025-10-24 | 2025-10-31 | Namechand Mahto | 18.727 | 2.3409 | TB507 | 76/0 | Completed
2025-10-30 | 2025-10-29 | 2025-11-02 | Prayag Saw 1 |  |  | TB507 | 135/0 | Completed
2025-10-30 | 2025-10-29 | 2025-11-03 | Prayag Saw 2 |  |  | TB507 | 134A/1 | Completed
2025-10-30 | 2025-10-24 | 2025-10-31 | Windbridge Energy | 18.727 | 2.3409 | TB507 | 133/0 | Completed
2025-10-31 | 2025-10-28 | 2025-10-31 | Chandra Sekhar |  |  | TB507 | 147/4 | Completed
2025-10-31 | 2025-10-27 | 2025-11-02 | Dipak |  |  | TB507 | 115/1 | Completed
2025-10-31 | 2025-10-27 | 2025-11-01 | Gokul Sarkar |  |  | TB507 | 153A/0 | Completed
2025-10-31 | 2025-10-24 | 2025-10-31 | Namechand Mahto | 18.727 | 2.3409 | TB507 | 76/0 | Completed
2025-10-31 | 2025-10-29 | 2025-11-02 | Prayag Saw 1 |  |  | TB507 | 135/0 | Completed
2025-10-31 | 2025-10-29 | 2025-11-03 | Prayag Saw 2 |  |  | TB507 | 134A/1 | Completed
2025-10-31 | 2025-10-24 | 2025-10-31 | Windbridge Energy | 18.727 | 2.3409 | TB507 | 133/0 | Completed
2025-11-01 | 2025-11-01 | 2025-11-05 | Chandra Sekhar |  |  | TB507 | 129/1 | Completed
2025-11-01 | 2025-10-27 | 2025-11-02 | Dipak |  |  | TB507 | 115/1 | Completed
2025-11-01 | 2025-10-27 | 2025-11-01 | Gokul Sarkar |  |  | TB507 | 153A/0 | Completed
2025-11-01 | 2025-11-01 | 2025-11-05 | Namechand Mahto |  |  | TB507 | 77/0 | Completed
2025-11-01 | 2025-10-29 | 2025-11-02 | Prayag Saw 1 |  |  | TB507 | 135/0 | Completed
2025-11-01 | 2025-10-29 | 2025-11-03 | Prayag Saw 2 |  |  | TB507 | 134A/1 | Completed
2025-11-01 | 2025-11-01 | 2025-11-04 | Windbridge Energy |  |  | TB507 | 132/3 | Completed
2025-11-02 | 2025-11-01 | 2025-11-05 | Chandra Sekhar |  |  | TB507 | 129/1 | Completed
2025-11-02 | 2025-10-27 | 2025-11-02 | Dipak |  |  | TB507 | 115/1 | Completed
2025-11-02 | 2025-11-01 | 2025-11-05 | Namechand Mahto |  |  | TB507 | 77/0 | Completed
2025-11-02 | 2025-10-29 | 2025-11-02 | Prayag Saw 1 |  |  | TB507 | 135/0 | Completed
2025-11-02 | 2025-10-29 | 2025-11-03 | Prayag Saw 2 |  |  | TB507 | 134A/1 | Completed
2025-11-02 | 2025-11-01 | 2025-11-04 | Windbridge Energy |  |  | TB507 | 132/3 | Completed
2025-11-03 | 2025-11-01 | 2025-11-05 | Chandra Sekhar |  |  | TB507 | 129/1 | Completed
2025-11-03 | 2025-11-01 | 2025-11-05 | Namechand Mahto |  |  | TB507 | 77/0 | Completed
2025-11-03 | 2025-11-03 | 2025-11-08 | Prayag Saw 1 |  |  | TB507 | 136/0 | Completed
2025-11-03 | 2025-10-29 | 2025-11-03 | Prayag Saw 2 |  |  | TB507 | 134A/1 | Completed
2025-11-03 | 2025-11-01 | 2025-11-04 | Windbridge Energy |  |  | TB507 | 132/3 | Completed
2025-11-04 | 2025-11-01 | 2025-11-05 | Chandra Sekhar |  |  | TB507 | 129/1 | Completed
2025-11-04 | 2025-11-01 | 2025-11-05 | Namechand Mahto |  |  | TB507 | 77/0 | Completed
2025-11-04 | 2025-11-03 | 2025-11-08 | Prayag Saw 1 |  |  | TB507 | 136/0 | Completed
2025-11-04 | 2025-11-04 | 2025-11-06 | Prayag Saw 2 |  |  | TB507 | 134A/4 | Completed
2025-11-04 | 2025-11-01 | 2025-11-04 | Windbridge Energy |  |  | TB507 | 132/3 | Completed
2025-11-05 | 2025-11-01 | 2025-11-05 | Chandra Sekhar |  |  | TB507 | 129/1 | Completed
2025-11-05 | 2025-11-01 | 2025-11-05 | Namechand Mahto |  |  | TB507 | 77/0 | Completed
2025-11-05 | 2025-11-03 | 2025-11-08 | Prayag Saw 1 |  |  | TB507 | 136/0 | Completed
2025-11-05 | 2025-11-04 | 2025-11-06 | Prayag Saw 2 |  |  | TB507 | 134A/4 | Completed
2025-11-05 | 2025-11-05 | 2025-11-07 | Windbridge Energy |  |  | TB507 | 132/1 | Completed
2025-11-06 | 2025-11-06 | 2025-11-09 | Chandra Sekhar |  |  | TB507 | 131/1 | Completed
2025-11-06 | 2025-11-03 | 2025-11-08 | Prayag Saw 1 |  |  | TB507 | 136/0 | Completed
2025-11-06 | 2025-11-04 | 2025-11-06 | Prayag Saw 2 |  |  | TB507 | 134A/4 | Completed
2025-11-06 | 2025-11-05 | 2025-11-07 | Windbridge Energy |  |  | TB507 | 132/1 | Completed
2025-11-07 | 2025-11-06 | 2025-11-09 | Chandra Sekhar |  |  | TB507 | 131/1 | Completed
2025-11-07 | 2025-11-03 | 2025-11-08 | Prayag Saw 1 |  |  | TB507 | 136/0 | Completed
2025-11-07 | 2025-11-05 | 2025-11-07 | Windbridge Energy |  |  | TB507 | 132/1 | Completed
2025-11-08 | 2025-11-06 | 2025-11-09 | Chandra Sekhar |  |  | TB507 | 131/1 | Completed
2025-11-08 | 2025-11-03 | 2025-11-08 | Prayag Saw 1 |  |  | TB507 | 136/0 | Completed
2025-11-09 | 2025-11-06 | 2025-11-09 | Chandra Sekhar |  |  | TB507 | 131/1 | Completed

## RawData
Start Date | Complete Date | Gang name | Tower Weight | Productivity | Project Name | Location No. | Status
2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.7305 | 2.3582 | TA325 | 127/1 | Completed
2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 127/2 | Completed
2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.7305 | 4.1923 | TA325 | 135A/4 | Completed
2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.7305 | 5.3901 | TA325 | 135/2 | Completed
2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.7305 | 2.9023 | TA325 | 135A/7 | Completed
2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 133/1 | Completed
2024-01-04 | 2024-01-12 | Poonam Kumari | 44.7282 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-12 | 2024-01-18 | Poonam Kumari | 37.7305 | 5.3901 | TA325 | 135B/3 | Completed
2024-01-18 | 2024-01-23 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135B/2 | Completed
2024-01-23 | 2024-01-28 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135A/3 | Completed
2024-01-28 | 2024-02-02 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135B/5 | Completed
2024-02-02 | 2024-02-09 | Poonam Kumari | 54.4178 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-04 | 2024-02-13 | Lalan Mahto | 37.7305 | 3.773 | TA325 | 132/2 | Completed
2024-02-04 | 2024-02-15 | Poonam Kumari | 37.7305 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-15 | 2024-02-20 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 133A/3 | Completed
2024-02-13 | 2024-02-21 | Lalan Mahto | 54.4178 | 6.0464 | TA325 | 133/0 | Completed
2024-02-20 | 2024-02-26 | Poonam Kumari | 37.7305 | 5.3901 | TA325 | 135B/1 | Completed
2024-02-20 | 2024-02-28 | Lalan Mahto | 37.7305 | 4.1923 | TA325 | 133/3 | Completed
2024-02-26 | 2024-03-02 | Poonam Kumari | 37.7305 | 6.2884 | TA325 | 135/3 | Completed
2024-02-27 | 2024-03-03 | Lalan Mahto | 37.7305 | 6.2884 | TA325 | 133/2 | Completed
2024-03-03 | 2024-03-08 | Lalan Mahto | 37.7305 | 6.2884 | TA325 | 133/5 | Completed
2024-03-08 | 2024-03-13 | Lalan Mahto | 54.4178 | 9.0696 | TA325 | 133A/0 | Completed
2024-03-13 | 2024-03-13 | Lalan Mahto | 37.7305 | 37.7305 | TA325 | 133A/1 | Completed
2024-03-02 | 2024-04-11 | Poonam Kumari | 39.4589 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-13 | 2024-04-19 | Lalan Mahto | 44.7282 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-20 | 2024-04-24 | Lalan Mahto | 37.7305 | 7.5461 | TA325 | 133/4 | Completed
2024-04-25 | 2024-04-30 | Lalan Mahto | 64.2538 | 10.709 | TA325 | 129A/0 | Completed
2024-05-02 | 2024-05-07 | Lalan Mahto | 37.7305 | 6.2884 | TA325 | 129A/1 | Completed
2024-05-07 | 2024-05-12 | Lalan Mahto | 39.4589 | 6.5765 | TA325 | 129A/2 | Completed
2024-05-07 | 2024-05-18 | Lalan Mahto | 54.4178 | 4.5348 | TA325 | 130/0 | Completed
2024-05-07 | 2024-05-18 | Rahul Kumar | 37.7305 | 3.1442 | TA325 | 137/4 | Completed
2024-05-01 | 2024-05-19 | Intizer Infratech | 37.7305 | 1.9858 | TA325 | 135/6 | Completed
2024-05-19 | 2024-05-24 | Lalan Mahto | 39.4589 | 6.5765 | TA325 | 127/4 | Completed
2024-05-19 | 2024-05-24 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 137/3 | Completed
2024-05-25 | 2024-05-31 | Lalan Mahto | 37.7305 | 5.3901 | TA325 | 127/3 | Completed
2024-05-19 | 2024-05-31 | Intizer Infratech | 37.7305 | 2.9023 | TA325 | 135/5 | Completed
2024-05-25 | 2024-05-31 | Rahul Kumar | 39.4589 | 5.637 | TA325 | 137/1 | Completed
2024-05-31 | 2024-06-10 | Lalan Mahto | 72.2376 | 6.5671 | TA325 | 127/0 | Completed
2024-05-31 | 2024-06-10 | Intizer Infratech | 37.7305 | 3.43 | TA325 | 135/4 | Completed
2024-06-05 | 2024-06-13 | Gourishankar | 72.2376 | 8.0264 | TA325 | 112/0 | Completed
2024-06-11 | 2024-06-15 | Rahul Kumar | 37.7305 | 7.5461 | TA325 | 144/2 | Completed
2024-06-13 | 2024-06-15 | Rahul Kumar | 37.7305 | 12.5768 | TA325 | 144/3 | Completed
2024-06-12 | 2024-06-18 | Lalan Mahto | 37.7305 | 5.3901 | TA325 | 132/3 | Completed
2024-06-16 | 2024-06-20 | Rahul Kumar | 37.7305 | 7.5461 | TA325 | 144/4 | Completed
2024-06-14 | 2024-06-24 | Gourishankar | 46.6235 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-21 | 2024-06-26 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 144/5 | Completed
2024-06-25 | 2024-07-02 | Gourishankar | 39.4589 | 4.9324 | TA325 | 106A/3 | Completed
2024-06-30 | 2024-07-05 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 144/1 | Completed
2024-07-02 | 2024-07-12 | Gourishankar | 44.7282 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-08 | 2024-07-12 | Rahul Kumar | 37.7305 | 7.5461 | TA325 | 119/2 | Completed
2024-07-13 | 2024-07-18 | Rahul Kumar | 37.7305 | 6.2884 | TA325 | 119/3 | Completed
2024-07-08 | 2024-07-23 | Sukhriddin | 37.7305 | 2.3582 | TA325 | 159/3 | Completed
2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-13 | 2024-07-29 | Gourishankar | 72.2376 | 4.2493 | TA325 | 107/0 | Completed
2024-07-20 | 2024-07-31 | Rahul Kumar | 64.2538 | 5.3545 | TA325 | 126/0 | Completed
2024-07-28 | 2024-08-08 | Ajay Kumar | 46.6235 | 3.8853 | TA325 | 106B/1 | Completed
2024-07-30 | 2024-08-11 | Gourishankar | 64.2538 | 4.9426 | TA325 | 116A/0 | Completed
2024-07-27 | 2024-08-13 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/2 | Completed
2024-08-01 | 2024-08-20 | Rahul Kumar | 72.2376 | 3.6119 | TA325 | 118/0 | Completed
2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.7305 | 0.85751 | TA325 | 255/4 | Completed
2024-08-11 | 2024-08-23 | Gourishankar | 54.4178 | 4.186 | TA325 | 109/0 | Completed
2024-08-08 | 2024-08-24 | Rahul Kumar | 65.7565 | 3.868 | TA325 | 106B/0 | Completed
2024-08-18 | 2024-08-31 | Rahul Kumar | 54.4178 | 3.887 | TA325 | 110/0 | Completed
2024-08-14 | 2024-09-08 | Sukhriddin | 54.4178 | 2.093 | TA325 | 159/0 | Completed
2024-09-02 | 2024-09-13 | Gourishankar | 72.2376 | 6.0198 | TA325 | 114/0 | Completed
2024-08-21 | 2024-09-13 | Ramjivan | 37.7305 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-09 | 2024-09-20 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 165/2 | Completed
2024-09-09 | 2024-09-21 | Rahul Kumar | 64.2538 | 4.9426 | TA325 | 111/0 | Completed
2024-09-14 | 2024-09-23 | Gourishankar | 36.0448 | 3.6045 | TA325 | 119/1 | Completed
2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.2538 | 2.5702 | TA325 | 257/0 | Completed
2024-09-12 | 2024-09-24 | Ajay Kumar | 72.2376 | 5.5567 | TA325 | 119/0 | Completed
2024-09-16 | 2024-09-26 | Barkat Ali | 36.0448 | 3.2768 | TA325 | 107/1 | Completed
2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.4236 | 6.2458 | TA325 | 116/0 | Completed
2024-09-16 | 2024-09-30 | Senahul | 39.4589 | 2.6306 | TA325 | 124A/1 | Completed
2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.7305 | 0.96745 | TA325 | 257/3 | Completed
2024-09-22 | 2024-10-09 | Sukhriddin | 37.7305 | 2.0961 | TA325 | 164/7 | Completed
2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-09-26 | 2024-10-10 | Ajay Kumar | 94.4077 | 6.2938 | TA325 | 123/0 | Completed
2024-09-27 | 2024-10-12 | Mithun Kumar | 44.7282 | 2.7955 | TA325 | 133A/4 | Completed
2024-09-16 | 2024-10-12 | Rejaul | 37.7305 | 1.3974 | TA325 | 152/1 | Completed
2024-09-28 | 2024-10-13 | Dk Verma | 72.2376 | 4.5149 | TA325 | 108/0 | Completed
2024-10-04 | 2024-10-15 | Gourishankar | 74.6321 | 6.2193 | TA325 | 122/0 | Completed
2024-10-01 | 2024-10-24 | Gourishankar | 98.8356 | 4.1182 | TA325 | 120/0 | Completed
2024-10-15 | 2024-10-24 | Mukesh | 64.2538 | 6.4254 | TA325 | 152/0 | Completed
2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.0448 | 1.1264 | TA325 | 257/2 | Completed
2024-10-09 | 2024-10-28 | Sukhriddin | 54.4178 | 2.7209 | TA325 | 165/0 | Completed
2024-09-14 | 2024-10-28 | Senahul | 39.4589 | 0.87686 | TA325 | 270/2 | Completed
2024-10-13 | 2024-10-31 | Ajay Kumar | 85.2338 | 4.486 | TA325 | 116B/0 | Completed
2024-10-17 | 2024-10-31 | Gourishankar | 39.4589 | 2.6306 | TA325 | 123/1 | Completed
2024-10-25 | 2024-10-31 | Mukesh | 36.0448 | 5.1493 | TA325 | 152/3 | Completed
2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-30 | 2024-10-31 | Thanu Mahto | 56.8632 | 1.777 | TA325 | 265/0 | Completed
2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.4524 | 2.7945 | TA325 | 135A/1 | Completed
2024-09-24 | 2024-11-07 | Sk Samuil | 36.0448 | 0.801 | TA325 | 152/2 | Completed
2024-11-02 | 2024-11-07 | Mukesh | 37.7305 | 6.2884 | TA325 | 152/4 | Completed
2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.7305 | 2.695 | TA325 | 262/1 | Completed
2024-10-28 | 2024-11-11 | Ajay Kumar | 66.2679 | 4.4179 | TA325 | 124/0 | Completed
2024-10-23 | 2024-11-12 | Rahul Kumar | 85.2338 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-02 | 2024-11-13 | Gourishankar | 56.8632 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.7565 | 7.3063 | TA325 | 135A/2 | Completed
2024-10-30 | 2024-11-15 | Sukhriddin | 44.7282 | 2.6311 | TA325 | 165/3 | Completed
2024-10-15 | 2024-11-16 | Mukesh | 56.8632 | 1.7231 | TA325 | 144/0 | Completed
2024-10-29 | 2024-11-16 | Thanu Mahto | 37.7305 | 1.9858 | TA325 | 257/4 | Completed
2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.0448 | 5.1493 | TA325 | 137A/5 | Completed
2024-11-04 | 2024-11-21 | Senahul | 54.4178 | 3.0232 | TA325 | 254/0 | Completed
2024-11-10 | 2024-11-22 | Sk Samuil | 39.4589 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-16 | 2024-11-22 | Rahul Kumar | 39.4589 | 5.637 | TA325 | 155/3 | Completed
2024-11-18 | 2024-11-24 | Mukesh | 65.7565 | 9.3938 | TA325 | 144A/0 | Completed
2024-11-13 | 2024-11-26 | Ajay Kumar | 94.4077 | 6.7434 | TA325 | 128/0 | Completed
2024-11-22 | 2024-11-26 | Jwala | 37.7305 | 7.5461 | TA325 | 187/3 | Completed
2024-11-16 | 2024-11-27 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 164/4 | Completed
2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.7282 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-16 | 2024-11-30 | Rahul Kumar | 39.4589 | 2.6306 | TA325 | 155/2 | Completed
2024-11-22 | 2024-11-30 | Mithun Kumar | 36.0448 | 4.005 | TA325 | 191A/1 | Completed
2024-11-13 | 2024-12-02 | Modina India | 36.0448 | 1.8022 | TA325 | 147/3 | Completed
2024-11-23 | 2024-12-02 | Sk Samuil | 37.7305 | 3.773 | TA325 | 150A/2 | Completed
2024-11-20 | 2024-12-03 | Gourishankar | 84.2993 | 6.0214 | TA325 | 117/0 | Completed
2024-11-29 | 2024-12-03 | Dhaneswar Mahto | 36.0448 | 7.209 | TA325 | 137A/4 | Completed
2024-11-27 | 2024-12-07 | Ajay Kumar | 39.4589 | 3.5872 | TA325 | 127/5 | Completed
2024-11-10 | 2024-12-07 | Daulat Mahto | 94.4077 | 3.3717 | TA325 | 268/0 | Completed
2024-10-03 | 2024-12-08 | Dk Verma | 98.8356 | 1.4752 | TA325 | 106/0 | Completed
2024-11-18 | 2024-12-08 | Mukesh | 82.2388 | 3.9161 | TA325 | 145/0 | Completed
2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-11-17 | 2024-12-10 | Thanu Mahto | 74.6321 | 3.1097 | TA325 | 264/0 | Completed
2024-11-16 | 2024-12-12 | Rahul Kumar | 39.4589 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-28 | 2024-12-14 | Sukhriddin | 37.7305 | 2.2194 | TA325 | 164/5 | Completed
2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-09 | 2024-12-16 | Mukesh | 64.2538 | 8.0317 | TA325 | 147/1 | Completed
2024-12-02 | 2024-12-16 | Mjr | 46.6235 | 3.1082 | TA325 | 272/1 | Completed
2024-11-28 | 2024-12-18 | Rahim Khan | 37.7305 | 1.7967 | TA325 | 163/3 | Completed
2024-12-04 | 2024-12-20 | Gourishankar | 109.6077 | 6.4475 | TA325 | 115/0 | Completed
2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.6077 | 6.4475 | TA325 | 134/0 | Completed
2024-12-09 | 2024-12-21 | Dk Verma | 37.7305 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-08 | 2024-12-21 | Sk Samuil | 66.2679 | 4.7334 | TA325 | 132/0 | Completed
2024-12-11 | 2024-12-21 | Jwala | 94.4077 | 8.5825 | TA325 | 193/0 | Completed
2024-11-27 | 2024-12-21 | Senahul | 84.2993 | 3.372 | TA325 | 255/0 | Completed
2024-12-03 | 2024-12-22 | Modina India | 44.7282 | 2.2364 | TA325 | 147/5 | Completed
2024-12-17 | 2024-12-23 | Mukesh | 64.2538 | 9.1791 | TA325 | 147/2 | Completed
2024-12-09 | 2024-12-23 | Mithun Kumar | 37.7305 | 2.5154 | TA325 | 191/1 | Completed
2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-11 | 2024-12-24 | Daulat Mahto | 37.7305 | 2.695 | TA325 | 270/1 | Completed
2024-12-10 | 2024-12-25 | Modina India | 39.4589 | 2.4662 | TA325 | 147/4 | Completed
2024-12-14 | 2024-12-25 | Sukhriddin | 37.7305 | 3.1442 | TA325 | 164/6 | Completed
2024-12-21 | 2024-12-26 | Dhaneswar Mahto | 37.7305 | 6.2884 | TA325 | 135A/6 | Completed
2024-12-21 | 2024-12-27 | Gourishankar | 44.7282 | 6.3897 | TA325 | 126/1 | Completed
2024-12-22 | 2024-12-28 | Dk Verma | 44.7282 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-19 | 2024-12-28 | Barkat Ali | 36.0448 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-03 | 2024-12-28 | Senahul | 65.7565 | 2.5291 | TA325 | 251/0 | Completed
2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.9336 | 2.7204 | TA325 | 261/0 | Completed
2024-11-28 | 2024-12-29 | Rahim Khan | 37.7305 | 1.1791 | TA325 | 163/2 | Completed
2024-12-23 | 2024-12-29 | Jwala | 37.7305 | 5.3901 | TA325 | 197/4 | Completed
2024-12-22 | 2024-12-30 | Sk Samuil | 37.7305 | 4.1923 | TA325 | 132/1 | Completed
2024-11-13 | 2024-12-30 | Rahul Kumar | 112.4236 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-11 | 2024-12-31 | Thanu Mahto | 74.6321 | 3.5539 | TA325 | 272/0 | Completed
2024-12-26 | 2025-01-02 | Maa Construction | 39.4589 | 4.9324 | TA325 | 255/3 | Completed
2024-12-29 | 2025-01-03 | Dk Verma | 64.2538 | 10.709 | TA325 | 106A/0 | Completed
2024-12-24 | 2025-01-03 | Mukesh | 82.2388 | 7.4763 | TA325 | 147A/0 | Completed
2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.2538 | 7.1393 | TA325 | 135A/0 | Completed
2024-12-26 | 2025-01-04 | Mithun Kumar | 36.0448 | 3.6045 | TA325 | 187/2 | Completed
2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-23 | 2025-01-06 | Modina India | 37.7305 | 2.5154 | TA325 | 148/4 | Completed
2024-12-28 | 2025-01-07 | Daulat Mahto | 37.7305 | 3.43 | TA325 | 269/1 | Completed
2024-12-30 | 2025-01-08 | Rahim Khan | 37.7305 | 3.773 | TA325 | 163/1 | Completed
2025-01-04 | 2025-01-10 | Mukesh | 64.2538 | 9.1791 | TA325 | 148/0 | Completed
2024-12-31 | 2025-01-10 | Rahul Kumar | 39.4589 | 3.5872 | TA325 | 158B/2 | Completed
2024-12-31 | 2025-01-10 | Jwala | 98.8356 | 8.9851 | TA325 | 196/0 | Completed
2025-01-03 | 2025-01-10 | Maa Construction | 37.7305 | 4.7163 | TA325 | 255/2 | Completed
2025-01-06 | 2025-01-11 | Surender Mahto | 44.7282 | 7.4547 | TA325 | 135/1 | Completed
2025-01-01 | 2025-01-11 | Thanu Mahto | 36.0448 | 3.2768 | TA325 | 271/5 | Completed
2024-12-28 | 2025-01-12 | Sukhriddin | 54.4178 | 3.4011 | TA325 | 164/0 | Completed
2024-12-28 | 2025-01-12 | Senahul | 54.4178 | 3.4011 | TA325 | 266/0 | Completed
2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.2538 | 4.5896 | TA325 | 263/0 | Completed
2024-12-28 | 2025-01-16 | Modina India | 37.7305 | 1.8865 | TA325 | 164/1 | Completed
2025-01-07 | 2025-01-16 | Mithun Kumar | 37.7305 | 3.773 | TA325 | 197/3 | Completed
2025-01-09 | 2025-01-17 | Daulat Mahto | 37.7305 | 4.1923 | TA325 | 257/1 | Completed
2024-12-30 | 2025-01-18 | Barkat Ali | 94.4077 | 4.7204 | TA325 | 129/0 | Completed
2025-01-09 | 2025-01-18 | Mjr | 37.7305 | 3.773 | TA325 | 130/3 | Completed
2025-01-13 | 2025-01-18 | Dhaneswar Mahto | 37.7305 | 6.2884 | TA325 | 135A/5 | Completed
2025-01-10 | 2025-01-19 | Modina India | 37.7305 | 3.773 | TA325 | 148/3 | Completed
2025-01-11 | 2025-01-19 | Maa Construction | 44.7282 | 4.9698 | TA325 | 269/2 | Completed
2025-01-11 | 2025-01-20 | Rahim Khan | 37.7305 | 3.773 | TA325 | 164/3 | Completed
2024-12-22 | 2025-01-21 | Sk Samuil | 39.4589 | 1.2729 | TA325 | 130/4 | Completed
2025-01-09 | 2025-01-22 | Dk Verma | 109.6077 | 7.8291 | TA325 | 135/0 | Completed
2025-01-12 | 2025-01-22 | Jwala | 98.8356 | 8.9851 | TA325 | 197/0 | Completed
2025-01-16 | 2025-01-23 | Rahul Kumar | 64.2538 | 8.0317 | TA325 | 163/0 | Completed
2025-01-13 | 2025-01-23 | Thanu Mahto | 54.4178 | 4.9471 | TA325 | 272/5 | Completed
2025-01-20 | 2025-01-24 | Dhaneswar Mahto | 46.6235 | 9.3247 | TA325 | 137A/6 | Completed
2025-01-09 | 2025-01-25 | Gourishankar | 112.4236 | 6.6132 | TA325 | 136/0 | Completed
2025-01-10 | 2025-01-25 | Barkat Ali | 37.7305 | 2.3582 | TA325 | 163/6 | Completed
2025-01-17 | 2025-01-27 | Mithun Kumar | 37.7305 | 3.43 | TA325 | 198/1 | Completed
2025-01-19 | 2025-01-27 | Daulat Mahto | 44.7282 | 4.9698 | TA325 | 255/1 | Completed
2025-01-20 | 2025-01-29 | Mjr | 39.4589 | 3.9459 | TA325 | 130/2 | Completed
2025-01-23 | 2025-01-29 | Dk Verma | 54.4178 | 7.774 | TA325 | 137A/0 | Completed
2025-01-27 | 2025-01-29 | Dhaneswar Mahto | 44.7282 | 14.9094 | TA325 | 137A/1 | Completed
2025-01-16 | 2025-01-29 | Sukhriddin | 37.7305 | 2.695 | TA325 | 163/4 | Completed
2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-24 | 2025-01-29 | Jwala | 44.7282 | 7.4547 | TA325 | 272A/1 | Completed
2025-01-21 | 2025-01-30 | Modina India | 37.7305 | 3.773 | TA325 | 148/2 | Completed
2025-01-21 | 2025-01-31 | Maa Construction | 77.7181 | 7.0653 | TA325 | 267/0 | Completed
2025-01-27 | 2025-02-01 | Gourishankar | 54.4178 | 9.0696 | TA325 | 138/0 | Completed
2025-01-30 | 2025-02-02 | Dhaneswar Mahto | 37.7305 | 9.4326 | TA325 | 137A/2 | Completed
2025-01-25 | 2025-02-02 | Thanu Mahto | 39.4589 | 4.3843 | TA325 | 272/4 | Completed
2025-01-21 | 2025-02-03 | Modina India | 37.7305 | 2.695 | TA325 | 159/4 | Completed
2025-01-30 | 2025-02-04 | Dk Verma | 54.4178 | 9.0696 | TA325 | 139/0 | Completed
2025-01-30 | 2025-02-04 | Daulat Mahto | 36.0448 | 6.0075 | TA325 | 272/2 | Completed
2025-01-30 | 2025-02-04 | Jwala | 37.7305 | 6.2884 | TA325 | 272A/2 | Completed
2025-01-21 | 2025-02-05 | Barkat Ali | 75.4524 | 4.7158 | TA325 | 131/0 | Completed
2025-01-17 | 2025-02-06 | Tajirul | 39.4589 | 1.879 | TA325 | 272/3 | Completed
2025-02-03 | 2025-02-07 | Dhaneswar Mahto | 39.4589 | 7.8918 | TA325 | 137/5 | Completed
2025-01-27 | 2025-02-07 | Sk Samuil | 37.7305 | 3.1442 | TA325 | 137/6 | Completed
2025-01-29 | 2025-02-07 | Mithun Kumar | 37.7305 | 3.773 | TA325 | 197/2 | Completed
2025-01-25 | 2025-02-09 | Sk Samuil | 37.7305 | 2.3582 | TA325 | 130/1 | Completed
2025-02-03 | 2025-02-09 | Gourishankar | 44.7282 | 6.3897 | TA325 | 138/1 | Completed
2025-02-01 | 2025-02-09 | Modina India | 39.4589 | 4.3843 | TA325 | 148/1 | Completed
2025-02-05 | 2025-02-09 | Jwala | 37.7305 | 7.5461 | TA325 | 272A/3 | Completed
2025-02-05 | 2025-02-11 | Dk Verma | 37.7305 | 5.3901 | TA325 | 138/2 | Completed
2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.1461 | 3.5658 | TA325 | 262/0 | Completed
2025-01-21 | 2025-02-12 | Rahim Khan | 37.7305 | 1.6405 | TA325 | 159/1 | Completed
2025-02-04 | 2025-02-12 | Maa Construction | 37.7305 | 4.1923 | TA325 | 266/2 | Completed
2025-02-04 | 2025-02-13 | Thanu Mahto | 64.2538 | 6.4254 | TA325 | 271/0 | Completed
2025-02-10 | 2025-02-14 | Gourishankar | 37.7305 | 7.5461 | TA325 | 139/2 | Completed
2025-02-09 | 2025-02-14 | Dhaneswar Mahto | 65.7565 | 10.9594 | TA325 | 139A/0 | Completed
2025-02-01 | 2025-02-15 | Mjr | 77.7181 | 5.1812 | TA325 | 137/0 | Completed
2025-02-05 | 2025-02-15 | Daulat Mahto | 64.2538 | 5.8413 | TA325 | 270A/0 | Completed
2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-12 | 2025-02-17 | Dk Verma | 39.4589 | 6.5765 | TA325 | 139/1 | Completed
2025-02-11 | 2025-02-17 | Sk Samuil | 37.7305 | 5.3901 | TA325 | 141/1 | Completed
2025-02-01 | 2025-02-17 | Senahul | 64.2538 | 3.7796 | TA325 | 253/0 | Completed
2025-02-11 | 2025-02-17 | Mithun Kumar | 36.0448 | 5.1493 | TA325 | 270/6 | Completed
2025-01-27 | 2025-02-18 | Ajay Kumar | 36.0448 | 1.5672 | TA325 | 147/6 | Completed
2025-02-09 | 2025-02-18 | Sukhriddin | 37.7305 | 3.773 | TA325 | 157/1 | Completed
2025-02-13 | 2025-02-19 | Sk Samuil | 36.0448 | 5.1493 | TA325 | 141/2 | Completed
2025-01-12 | 2025-02-20 | Barkat Ali | 37.7305 | 0.94326 | TA325 | 163/5 | Completed
2025-02-13 | 2025-02-21 | Modina India | 37.7305 | 4.1923 | TA325 | 147B/1 | Completed
2025-02-14 | 2025-02-21 | Thanu Mahto | 37.7305 | 4.7163 | TA325 | 271/2 | Completed
2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed
2025-02-16 | 2025-02-23 | Gourishankar | 84.2993 | 10.5374 | TA325 | 141/0 | Completed
2025-02-17 | 2025-02-23 | Daulat Mahto | 36.0448 | 5.1493 | TA325 | 270/7 | Completed
2025-02-17 | 2025-02-23 | Jwala | 64.2538 | 9.1791 | TA325 | 274/0 | Completed
2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.0448 | 3.2768 | TA325 | 250/1 | Completed
2025-02-19 | 2025-02-25 | Sk Samuil | 39.4589 | 5.637 | TA325 | 141/3 | Completed
2025-02-14 | 2025-02-26 | Maa Construction | 54.4178 | 4.186 | TA325 | 249/0 | Completed
2025-02-18 | 2025-02-27 | Mjr | 37.7305 | 3.773 | TA325 | 137/2 | Completed
2025-02-25 | 2025-02-28 | Sk Samuil | 37.7305 | 9.4326 | TA325 | 148/5 | Completed
2025-02-20 | 2025-02-28 | Mithun Kumar | 37.7305 | 4.1923 | TA325 | 270/5 | Completed
2025-02-24 | 2025-02-28 | Jwala | 44.7282 | 8.9456 | TA325 | 273/2 | Completed
2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.2376 | 10.3197 | TA325 | 143A/0 | Completed
2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-22 | 2025-03-03 | Thanu Mahto | 36.0448 | 3.6045 | TA325 | 271/4 | Completed
2025-02-25 | 2025-03-04 | Gourishankar | 84.2993 | 10.5374 | TA325 | 143/0 | Completed
2025-02-27 | 2025-03-05 | Daulat Mahto | 37.7305 | 5.3901 | TA325 | 267A/1 | Completed
2025-03-02 | 2025-03-05 | Jwala | 36.0448 | 9.0112 | TA325 | 272A/6 | Completed
2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.4589 | 2.8185 | TA325 | 145A/1 | Completed
2025-02-10 | 2025-03-07 | Tajirul | 46.6235 | 1.7932 | TA325 | 272/7 | Completed
2025-03-01 | 2025-03-09 | Sk Samuil | 44.7282 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-03 | 2025-03-09 | Sk Samuil | 37.7305 | 5.3901 | TA325 | 148/6 | Completed
2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-01 | 2025-03-09 | Maa Construction | 37.7305 | 4.1923 | TA325 | 249/2 | Completed
2025-03-02 | 2025-03-10 | Mjr | 37.7305 | 4.1923 | TA325 | 143A/4 | Completed
2025-03-05 | 2025-03-10 | Dk Verma | 39.4589 | 6.5765 | TA325 | 143A/5 | Completed
2025-03-06 | 2025-03-10 | Jwala | 36.0448 | 7.209 | TA325 | 272A/7 | Completed
2025-03-05 | 2025-03-11 | Gourishankar | 75.4524 | 10.7789 | TA325 | 143A/3 | Completed
2025-02-23 | 2025-03-11 | Barkat Ali | 37.7305 | 2.2194 | TA325 | 157/2 | Completed
2025-03-04 | 2025-03-11 | Thanu Mahto | 36.0448 | 4.5056 | TA325 | 271/3 | Completed
2025-03-07 | 2025-03-15 | Daulat Mahto | 36.0448 | 4.005 | TA325 | 267A/2 | Completed
2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 145A/3 | Completed
2025-02-22 | 2025-03-16 | Anarul Haque | 72.2376 | 3.1408 | TA325 | 270/0 | Completed
2025-03-11 | 2025-03-16 | Jwala | 39.4589 | 6.5765 | TA325 | 272A/5 | Completed
2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 129.341 | 9.2386 | TA325 | 143A/2 | Completed
2025-03-13 | 2025-03-18 | Rahul Kumar | 36.0448 | 6.0075 | TA325 | 158/2 | Completed
2025-03-10 | 2025-03-18 | Maa Construction | 37.7305 | 4.1923 | TA325 | 249/3 | Completed
2025-02-21 | 2025-03-18 | Senahul | 77.7181 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-08 | 2025-03-20 | Rahim Khan | 37.7305 | 2.9023 | TA325 | 148/7 | Completed
2025-03-16 | 2025-03-20 | Gourishankar | 54.4178 | 10.8836 | TA325 | 152A/0 | Completed
2025-03-17 | 2025-03-20 | Jwala | 37.7305 | 9.4326 | TA325 | 272A/4 | Completed
2025-03-12 | 2025-03-22 | Dk Verma | 77.7181 | 7.0653 | TA325 | 146/0 | Completed
2025-02-26 | 2025-03-22 | Modina India | 82.2388 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-18 | 2025-03-22 | Sk Samuil | 39.4589 | 7.8918 | TA325 | 150/2 | Completed
2025-03-15 | 2025-03-23 | Barkat Ali | 36.0448 | 4.005 | TA325 | 155/6 | Completed
2025-03-21 | 2025-03-25 | Jwala | 36.0448 | 7.209 | TA325 | 271/1 | Completed
2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.4589 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-17 | 2025-03-27 | Sk Samuil | 37.7305 | 3.43 | TA325 | 149/1 | Completed
2025-03-21 | 2025-03-27 | Gourishankar | 56.8632 | 8.1233 | TA325 | 151/0 | Completed
2025-03-12 | 2025-03-27 | Rahim Khan | 94.4077 | 5.9005 | TA325 | 157/0 | Completed
2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-22 | 2025-03-28 | Rahul Kumar | 84.2993 | 12.0428 | TA325 | 156/0 | Completed
2025-03-19 | 2025-03-28 | Thanu Mahto | 36.0448 | 3.6045 | TA325 | 270/3 | Completed
2025-03-09 | 2025-03-28 | Mithun Kumar | 37.7305 | 1.8865 | TA325 | 270/4 | Completed
2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-19 | 2025-03-30 | Daulat Mahto | 39.4589 | 3.2882 | TA325 | 272/6 | Completed
2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.8356 | 9.8836 | TA325 | 150/0 | Completed
2025-03-24 | 2025-04-01 | Dk Verma | 77.7181 | 8.6353 | TA325 | 147/0 | Completed
2025-03-19 | 2025-04-01 | Rupesh | 44.7282 | 3.1949 | TA325 | 150/3 | Completed
2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed
2025-03-26 | 2025-04-03 | Barkat Ali | 37.7305 | 4.1923 | TA325 | 155/1 | Completed
2025-03-10 | 2025-04-06 | Sk Samuil | 54.4178 | 1.9435 | TA325 | 149/0 | Completed
2025-03-20 | 2025-04-06 | Mjr | 46.6235 | 2.5902 | TA325 | 150/1 | Completed
2025-03-28 | 2025-04-06 | Barkat Ali | 44.7282 | 4.4728 | TA325 | 167/3 | Completed
2025-04-01 | 2025-04-08 | Sk Samuil | 37.7305 | 4.7163 | TA325 | 195/2 | Completed
2025-03-30 | 2025-04-08 | Modina India | 37.7305 | 3.773 | TA325 | 195A/3 | Completed
2025-04-04 | 2025-04-09 | Jwala | 44.7282 | 7.4547 | TA325 | 273/1 | Completed
2025-04-02 | 2025-04-10 | Rahim Khan | 54.4178 | 6.0464 | TA325 | 158/0 | Completed
2025-03-25 | 2025-04-11 | Rahim Khan | 64.2538 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.7305 | 5.3901 | TA325 | 189/1 | Completed
2025-03-18 | 2025-04-11 | Anarul Haque | 97.9336 | 3.9173 | TA325 | 252/0 | Completed
2025-04-03 | 2025-04-12 | Thanu Mahto | 39.4589 | 3.9459 | TA325 | 187/1 | Completed
2025-04-01 | 2025-04-12 | Mithun Kumar | 37.7305 | 3.1442 | TA325 | 197/1 | Completed
2025-04-04 | 2025-04-12 | Daulat Mahto | 37.7305 | 4.1923 | TA325 | 198/2 | Completed
2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.7305 | 3.1442 | TA325 | 248/5 | Completed
2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-06 | 2025-04-13 | Gourishankar | 94.4077 | 11.801 | TA325 | 178/0 | Completed
2025-04-09 | 2025-04-15 | Sk Samuil | 37.7305 | 5.3901 | TA325 | 195/4 | Completed
2025-04-01 | 2025-04-15 | Mithun Kumar | 64.2538 | 4.2836 | TA325 | 198/0 | Completed
2025-04-06 | 2025-04-16 | Rupesh | 64.2538 | 5.8413 | TA325 | 168/0 | Completed
2025-04-11 | 2025-04-16 | Jwala | 36.0448 | 6.0075 | TA325 | 205/1 | Completed
2025-04-08 | 2025-04-18 | Barkat Ali | 44.7282 | 4.0662 | TA325 | 167/2 | Completed
2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 249/1 | Completed
2025-04-13 | 2025-04-22 | Sk Samuil | 37.7305 | 3.773 | TA325 | 135/7 | Completed
2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed
2025-04-16 | 2025-04-22 | Rahim Khan | 37.7305 | 5.3901 | TA325 | 181/2 | Completed
2025-04-15 | 2025-04-22 | Rahul Kumar | 54.4178 | 6.8022 | TA325 | 191A/0 | Completed
2025-04-11 | 2025-04-22 | Modina India | 44.7282 | 3.7274 | TA325 | 195A/2 | Completed
2025-04-07 | 2025-04-25 | Barkat Ali | 36.0448 | 1.8971 | TA325 | 158/1 | Completed
2025-04-16 | 2025-04-25 | Mithun Kumar | 44.7282 | 4.4728 | TA325 | 195/1 | Completed
2025-04-03 | 2025-04-26 | Senahul | 82.2388 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-06 | 2025-04-27 | Dk Verma | 112.4236 | 5.1102 | TA325 | 181/0 | Completed
2025-04-23 | 2025-04-27 | Rahul Kumar | 36.0448 | 7.209 | TA325 | 191/2 | Completed
2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-13 | 2025-04-28 | Mjr | 64.2538 | 4.0159 | TA325 | 192/0 | Completed
2025-04-18 | 2025-04-28 | Sk Samuil | 44.7282 | 4.0662 | TA325 | 195/3 | Completed
2025-04-20 | 2025-04-29 | Barkat Ali | 37.7305 | 3.773 | TA325 | 167/4 | Completed
2025-04-18 | 2025-04-29 | Jwala | 84.2993 | 7.0249 | TA325 | 205/0 | Completed
2025-04-24 | 2025-04-30 | Rahim Khan | 37.7305 | 5.3901 | TA325 | 181/1 | Completed
2025-04-14 | 2025-04-30 | Anarul Haque | 77.7181 | 4.5717 | TA325 | 248/0 | Completed
2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.6235 | 3.3302 | TA325 | 248/2 | Completed
2025-04-24 | 2025-05-03 | Gourishankar | 89.1461 | 8.9146 | TA325 | 180/0 | Completed
2025-04-29 | 2025-05-04 | Rahul Kumar | 36.0448 | 6.0075 | TA325 | 191/3 | Completed
2025-04-18 | 2025-05-05 | Rupesh | 94.4077 | 5.2449 | TA325 | 167/0 | Completed
2025-04-17 | 2025-05-05 | Mjr | 39.4589 | 2.0768 | TA325 | 248/4 | Completed
2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.8082 | 6.4636 | TA325 | 190/0 | Completed
2025-04-24 | 2025-05-09 | Modina India | 44.7282 | 2.7955 | TA325 | 195A/1 | Completed
2025-04-29 | 2025-05-09 | Senahul | 37.7305 | 3.43 | TA325 | 248/6 | Completed
2025-04-28 | 2025-05-11 | Sk Samuil | 37.7305 | 2.695 | TA325 | 155/4 | Completed
2025-04-29 | 2025-05-11 | Barkat Ali | 37.7305 | 2.9023 | TA325 | 155/5 | Completed
2025-05-02 | 2025-05-11 | Sukhriddin | 37.7305 | 3.773 | TA325 | 168/2 | Completed
2025-05-03 | 2025-05-11 | Rahim Khan | 37.7305 | 4.1923 | TA325 | 181/4 | Completed
2025-04-28 | 2025-05-11 | Mithun Kumar | 64.2538 | 4.5896 | TA325 | 195/0 | Completed
2025-05-02 | 2025-05-11 | Sk Samuil | 44.7282 | 4.4728 | TA325 | 195/5 | Completed
2025-05-02 | 2025-05-11 | Jwala | 98.8356 | 9.8836 | TA325 | 204/0 | Completed
2025-04-22 | 2025-05-15 | Mjr | 94.4077 | 3.9337 | TA325 | 194/0 | Completed
2025-05-08 | 2025-05-16 | Rahul Kumar | 64.2538 | 7.1393 | TA325 | 209/0 | Completed
2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-04-22 | 2025-05-18 | Daulat Mahto | 54.4178 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-13 | 2025-05-18 | Dhaneswar Mahto | 37.7305 | 6.2884 | TA325 | 211/1 | Completed
2025-05-04 | 2025-05-18 | Rahim Khan 1 | 39.4589 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-06 | 2025-05-18 | Dk Verma | 46.6235 | 3.5864 | TA325 | 248/1 | Completed
2025-05-04 | 2025-05-19 | Barkat Ali | 80.408 | 5.0255 | TA325 | 167/1 | Completed
2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.7305 | 4.1923 | TA325 | 247/1 | Completed
2025-05-13 | 2025-05-20 | Rahim Khan | 36.0448 | 4.5056 | TA325 | 168/1 | Completed
2025-05-09 | 2025-05-20 | Mjr | 44.7282 | 3.7274 | TA325 | 248/3 | Completed
2025-05-15 | 2025-05-21 | Jwala | 39.4589 | 5.637 | TA325 | 205/2 | Completed
2025-04-18 | 2025-05-22 | Mithun Kumar | 112.4236 | 3.2121 | TA325 | 199/0 | Completed
2025-05-19 | 2025-05-24 | Gourishankar | 37.7305 | 6.2884 | TA325 | 181/3 | Completed
2025-05-16 | 2025-05-25 | Barkat Ali | 37.7305 | 3.773 | TA325 | 165/1 | Completed
2025-05-28 | 2025-06-05 | Gourishankar | 72.2376 | 8.0264 | TA325 | 175/0 | Completed
2025-05-29 | 2025-06-06 | Thanu Mahto | 44.7282 | 4.9698 | TA325 | 172/2 | Completed
2025-05-24 | 2025-06-08 | Dk Verma | 112.4236 | 7.0265 | TA325 | 169/0 | Completed
2025-06-06 | 2025-06-13 | Gourishankar | 54.4178 | 6.8022 | TA325 | 174/1 | Completed
2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-08 | 2025-07-20 | Nan | 37.7305 | 0.87745 | TA325 | 175/2 | Completed
2025-06-15 | 2025-08-08 | Nan | 142.1014 | 2.5837 | TA325 | 153/0 | Completed
2025-06-01 | 2025-08-13 | Dhaneshwar | 173.1266 | 2.3395 | TA325 | 104/0 | Completed
2025-06-02 | 2025-08-26 | Modina India | 122.8082 | 1.428 | TA325 | 191/0 | Completed
2025-08-06 | 2025-09-14 | Modina India | 72.2376 | 1.8059 | TA325 | 275/0 | Completed
2025-06-15 | 2025-09-19 | Dhaneshwar | 173.1266 | 1.7848 | TA325 | 101/0 | Completed
2025-05-24 | 2025-09-23 | Rupesh | 173.1266 | 1.4075 | TA325 | 105/0 | Completed
2025-05-13 | 2025-09-30 | Senahul Modina India 3 | 37.7305 | 0.26759 | TA325 | 247/4 | Completed
2025-09-24 | 2025-10-03 | Sukhrridin | 36.0448 | 3.6045 | TA325 | 237/3 | Completed
2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-24 | 2025-10-05 | Nan | 54.4178 | 4.5348 | TA325 | 242/0 | Completed
2025-09-19 | 2025-10-05 | Nan | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-24 | 2025-10-06 | Nan | 36.0448 | 2.7727 | TA325 | 237/5 | Completed
2025-03-14 | 2025-10-06 | Dildar Electricals | 36.0448 | 0.17413 | TA325 | 247/3 | Completed
2025-09-18 | 2025-10-08 | Md Akhtar | 72.2376 | 3.4399 | TA325 | 234/0 | Completed
2025-09-23 | 2025-10-11 | Subhash | 54.4178 | 2.8641 | TA325 | 236/0 | Completed
2025-10-05 | 2025-10-11 | Sukhrridin | 37.7305 | 5.3901 | TA325 | 237/4 | Completed
2025-10-03 | 2025-10-12 | Gokul Sarkar 1 | 36.0448 | 3.6045 | TA325 | 242/2 | Completed
2025-09-05 | 2025-10-12 | Senaul | 37.7305 | 0.99291 | TA325 | 245/1 | Completed
2025-10-05 | 2025-10-14 | Nasirudin | 74.6321 | 7.4632 | TA325 | 224/0 | Completed
2025-10-05 | 2025-10-14 | Modina India 1 4 Pgcil | 36.0448 | 3.6045 | TA325 | 237/2 | Completed
2025-10-05 | 2025-10-15 | Modina India 3 Pgcil | 37.7305 | 3.43 | TA325 | 229/3 | Completed
2025-10-05 | 2025-10-15 | Jaman Mahto 1 Ratna Devi | 77.7181 | 7.0653 | TA325 | 244/0 | Completed
2025-10-05 | 2025-10-16 | Muni Bibi 2 | 37.7305 | 3.1442 | TA325 | 237/1 | Completed
2025-10-06 | 2025-10-16 | Gokul Sarkar 2 | 65.7565 | 5.9779 | TA325 | 244/1 | Completed
2025-10-08 | 2025-10-16 | Rahul Kumar | 80.408 | 8.9342 | TA325 | 247/0 | Completed
2025-10-04 | 2025-10-17 | Sukruddin | 37.7305 | 2.695 | TA325 | 217A/2 | Completed
2025-10-06 | 2025-10-17 | Teklal Mahto | 37.7305 | 3.1442 | TA325 | 223/1 | Completed
2025-10-06 | 2025-10-17 | Anita Devi | 72.2376 | 6.0198 | TA325 | 233/0 | Completed
2025-10-03 | 2025-10-17 | Dildar Electrical 2 Pgcil | 39.4589 | 2.6306 | TA325 | 237/6 | Completed
2025-10-08 | 2025-10-18 | Sakila Khatun | 65.7565 | 5.9779 | TA325 | 241/0 | Completed
2025-10-05 | 2025-10-19 | Jwala Singh | 141.874 | 9.4583 | TA325 | 206/0 | Completed
2025-10-08 | 2025-10-19 | Muni Bibi 1 | 44.7282 | 3.7274 | TA325 | 225/1 | Completed
2025-10-12 | 2025-10-19 | Md Akhtar | 66.2679 | 8.2835 | TA325 | 235/0 | Completed
2025-10-07 | 2025-10-19 | Satish Kumar | 65.7565 | 5.0582 | TA325 | 243/0 | Completed
2025-10-14 | 2025-10-19 | Prayag Mahto | 36.0448 | 6.0075 | TA325 | 242/3 | Completed
2025-07-23 | 2025-10-21 | Barkat Ali Mithun Kumar Vntl | 37.7305 | 0.41462 | TA325 | 157/3 | Completed
2025-10-12 | 2025-10-23 | Nasirudin 2 | 80.408 | 6.7007 | TA325 | 225/0 | Completed
2025-10-08 | 2025-10-23 | Dildar Electrical 3 | 37.7305 | 2.3582 | TA325 | 229/5 | Completed
2025-09-20 | 2025-10-23 | Modina India 2 Pgcil | 54.4178 | 1.6005 | TA325 | 273/0 | Completed
2025-10-13 | 2025-10-24 | Subhash | 94.4077 | 7.8673 | TA325 | 231/0 | Completed
2025-10-10 | 2025-10-24 | Dildar Electricals 1 Pgcil | 39.4589 | 2.6306 | TA325 | 247/2 | Completed
2025-10-17 | 2025-10-25 | Modina India 3 Pgcil | 37.7305 | 4.1923 | TA325 | 229/4 | Completed
2025-10-17 | 2025-10-26 | Modina India 1 4 Pgcil | 36.0448 | 3.6045 | TA325 | 242/1 | Completed
2025-10-18 | 2025-10-26 | Rahul Kumar | 82.2388 | 9.1376 | TA325 | 210/0 | Completed
2025-10-17 | 2025-10-29 | Gokul 1 | 46.6235 | 3.5864 | TA325 | 185/1 | Completed
2025-10-18 | 2025-10-29 | Gokul Sarkar 2 | 56.8632 | 4.7386 | TA325 | 222/1 | Completed
2025-10-19 | 2025-11-01 | Anita Devi | 84.2993 | 6.0214 | TA325 | 232/0 | Completed
2025-10-06 | 2025-11-03 | Rupesh | 89.1461 | 3.074 | TA325 | 237/0 | Completed
2025-10-22 | 2025-11-06 | Muni Bibi 1 2 | 63.509 | 3.9693 | TA325 | 227/0 | Completed
2025-10-23 | 2025-11-06 | Jwala Singh | 65.7565 | 4.3838 | TA325 | 211/0 | Completed
2025-10-14 | 2025-11-07 | Imadul Haque | 80.408 | 3.2163 | TA325 | 218/0 | Completed
2025-10-25 | 2025-11-08 | Nasirudin 2 | 63.509 | 4.2339 | TA325 | 229/1 | Completed
2025-10-29 | 2025-11-09 | Rahul Kumar | 39.4589 | 3.2882 | TA325 | 209/1 | Completed
2025-10-29 | 2025-11-09 | Subhash | 64.2538 | 5.3545 | TA325 | 226/0 | Completed
2025-10-09 | 2025-11-09 | Javir Hossen | 80.408 | 2.5128 | TA325 | 230/0 | Completed
2025-10-24 | 2025-11-10 | Sukruddin | 72.2376 | 4.0132 | TA325 | 245/0 | Completed
2025-10-12 | 2025-11-11 | Md Akhtar | 129.341 | 4.1723 | TA325 | 229/0 | Completed
2025-11-05 | 2025-11-13 | Gokul Sarkar 1 | 39.4589 | 4.3843 | TA325 | 220/1 | Completed
2025-10-23 | 2025-11-13 | Teklal Mahto | 64.2538 | 2.9206 | TA325 | 223/0 | Completed
2025-10-22 | 2025-11-13 | Sakila Khatun | 141.874 | 6.1684 | TA325 | 240/0 | Completed
2025-11-02 | 2025-11-14 | Modina India 3 Pgcil | 44.7282 | 3.4406 | TA325 | 229/2 | Completed
2025-11-06 | 2025-11-14 | Dildar Electricals 1 Pgcil | 37.7305 | 4.1923 | TA325 | 223/3 | Completed
2025-10-19 | 2025-11-15 | Jaman Mahto 1 Ratna Devi | 141.874 | 5.0669 | TA325 | 184/0 | Completed
2025-11-03 | 2025-11-15 | Mithun Kumar | 64.2538 | 4.9426 | TA325 | 185/0 | Completed
2025-10-18 | 2025-11-15 | Nasirudin | 228.7027 | 7.8863 | TA325 | 202/0 | Completed
2025-11-08 | 2025-11-15 | Jwala Singh | 37.7305 | 4.7163 | TA325 | 211/2 | Completed
2025-11-03 | 2025-11-17 | Gokul Sarkar 2 | 89.1461 | 5.9431 | TA325 | 220/0 | Completed
2025-10-29 | 2025-11-18 | Satish Kumar | 63.509 | 3.0242 | TA325 | 184/1 | Completed
2025-10-26 | 2025-11-18 | Anjum | 94.4077 | 3.9337 | TA325 | 203/1 | Completed
2025-10-19 | 2025-11-18 | Enjamul Haque | 72.2376 | 2.3302 | TA325 | 214/0 | Completed
2025-11-06 | 2025-11-18 | Modina India 2 Pgcil | 39.4589 | 3.0353 | TA325 | 218/1 | Completed
2025-11-11 | 2025-11-23 | Pc Construction | 97.9336 | 7.5334 | TA325 | 201/0 | Completed
2025-04-22 | 2025-11-24 | Mithun Kumar | 141.874 | 0.6538 | TA325 | 187/0 | Completed
2025-11-06 | 2025-11-24 | Chitra Construction | 37.7305 | 1.9858 | TA325 | 211A/2 | Completed
2025-11-15 | 2025-11-24 | Pc 2 | 46.6235 | 4.6623 | TA325 | 215/1 | Completed
|  | Nan | 156.8261 |  | TA325 | 102/0 | WIP
|  | Nan | 156.8261 |  | TA325 | 103/0
|  | Nan | 123.649 |  | TA325 | 154/0
|  | Nan | 123.649 |  | TA325 | 154/1
|  | Nan | 101.8517 |  | TA325 | 159/2
|  | Nan | 129.341 |  | TA325 | 160/0
|  | Nan | 89.1461 |  | TA325 | 165/4
|  | Nan | 89.1461 |  | TA325 | 165/5
|  | Nan | 94.4077 |  | TA325 | 166/0 | WIP
|  | Nan | 94.4077 |  | TA325 | 167/0
|  | Nan | 80.408 |  | TA325 | 167/1
|  | Nan | 39.4589 |  | TA325 | 172/1
|  | Nan | 141.874 |  | TA325 | 173/0
|  | Nan | 129.341 |  | TA325 | 174/0
|  | Nan | 37.7305 |  | TA325 | 175/1
|  | Nan | 85.2338 |  | TA325 | 182A/0
|  | Nan | 141.874 |  | TA325 | 183/0
|  | Nan | 172.769 |  | TA325 | 186/0 | WIP
|  | Nan | 82.2388 |  | TA325 | 200/0
|  | Nan | 98.8356 |  | TA325 | 201/1
|  | Nan | 228.7027 |  | TA325 | 203/0
|  | Nan | 141.874 |  | TA325 | 208/0
|  | Nan | 54.4178 |  | TA325 | 211A/0
|  | Nan | 36.0448 |  | TA325 | 211A/1
|  | Nan | 75.4524 |  | TA325 | 212/0
|  | Nan | 84.2993 |  | TA325 | 213/0
|  | Nan | 37.7305 |  | TA325 | 213/1
|  | Nan | 44.7282 |  | TA325 | 214/1
|  | Nan | 99.7717 |  | TA325 | 216/0
|  | Nan | 122.8082 |  | TA325 | 217/0
|  | Nan | 56.8632 |  | TA325 | 217A/0
|  | Nan | 97.9336 |  | TA325 | 219/0
|  | Nan | 129.341 |  | TA325 | 221/0
|  | Nan | 141.874 |  | TA325 | 222/0
|  | Nan | 37.7305 |  | TA325 | 223/2
|  | Nan | 141.874 |  | TA325 | 228/0
|  | Nan | 141.874 |  | TA325 | 239/0
|  | Total Completed | 29546.1061 |  | TA325
|  | Nan |  |  | TA325
|  | Nan |  |  | TA325
|  | Nan |  |  | TA325
|  | Nan |  |  | TA325
|  | Total Tower Erection |  |  | TA325 |  | Completed
|  | Balance Tower Erection | 40 |  | TA325 |  | 39
|  | Nan | 146 |  | TA325 |  | 140
|  | Tower Type | 40 |  | TA325 |  | 39
|  | Da 0 | 30 |  | TA325 |  | 30
|  | Da 3 | 11 |  | TA325 |  | 10
|  | Da 6 | 267 |  | TA325 |  | 258
|  | Da 9 | 25 |  | TA325 |  | 0
|  | Da 3 | 6 |  | TA325 |  | 0
|  | Db1 0 | 8 |  | TA325 |  | 0
|  | Db1 18 | 9 |  | TA325 |  | 0
|  | Db1 3 | 6 |  | TA325 |  | 0
|  | Db1 6 | 1 |  | TA325 |  | 0
|  | Db1 9 | 55 |  | TA325 |  | 0
|  | Db2 0 | 26 |  | TA325 |  | 0
|  | Db2 18 | 3 |  | TA325 |  | 0
|  | Db2 25 | 4 |  | TA325 |  | 0
|  | Db2 3 | 7 |  | TA325 |  | 0
|  | Db2 6 | 4 |  | TA325 |  | 0
|  | Db2 9 | 3 |  | TA325 |  | 0
|  | Dc 0 | 47 |  | TA325 |  | 0
|  | Dc1 0 | 16 |  | TA325 |  | 15
|  | Dc1 18 | 4 |  | TA325 |  | 3
|  | Dc1 3 | 3 |  | TA325 |  | 2
|  | Dc1 6 | 4 |  | TA325 |  | 4
|  | Dc1 9 | 6 |  | TA325 |  | 6
|  | Dc2 0 | 5 |  | TA325 |  | 2
|  | Dc2 18 | 2 |  | TA325 |  | 0
|  | Dc2 25 | 40 |  | TA325 |  | 32
|  | Dc2 3 | 19 |  | TA325 |  | 19
|  | Dc2 6 | 8 |  | TA325 |  | 7
|  | Dc2 9 | 11 |  | TA325 |  | 11
|  | Dct 0 | 7 |  | TA325 |  | 6
|  | Dd45 0 | 7 |  | TA325 |  | 5
|  | Dd45 18 | 15 |  | TA325 |  | 9
|  | Dd45 25 | 4 |  | TA325 |  | 3
|  | Dd45 3 | 2 |  | TA325 |  | 1
|  | Dd45 35 | 73 |  | TA325 |  | 61
|  | Dd45 6 | 1 |  | TA325 |  | 0
|  | Dd45 9 | 1 |  | TA325 |  | 0
|  | Dd60 0 | 483 |  | TA325 |  | 351
|  | Dd60 18 |  |  | TA325
|  | Dd60 25 |  |  | TA325
|  | Dd60 3 |  |  | TA325
|  | Dd60 35 |  |  | TA325
|  | Dd60 55 |  |  | TA325
|  | Dd60 6 |  |  | TA325
|  | Dd60 9 |  |  | TA325
|  | Total |  |  | TA325
2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | Completed
2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | Completed
2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | Completed
2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | Completed
2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | Completed
2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | Completed
2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | Completed
2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | Completed
2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | Completed
2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | Completed
2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | Completed
2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | Completed
2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | Completed
2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | Completed
2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | Completed
2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | Completed
2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | Completed
2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | Completed
2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | Completed
2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | Completed
2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | Completed
2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | Completed
2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | Completed
2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | Completed
2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | Completed
2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | Completed
2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | Completed
2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | Completed
2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | Completed
2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | Completed
2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | Completed
2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | Completed
2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | Completed
2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | Completed
2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | Completed
2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | Completed
2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | Completed
2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | Completed
2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | Completed
2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | Completed
2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | Completed
2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | Completed
2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | Completed
2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | Completed
2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | Completed
2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | Completed
2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | Completed
2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | Completed
2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | Completed
2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | Completed
2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | Completed
2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-15 | 2025-02-18 | Punam Devi 1 | 36.1598 | 9.0399 | TA413 | 38/9 | Completed
2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | Completed
2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | Completed
2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | Completed
2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | Completed
2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | Completed
2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | Completed
2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | Completed
2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | Completed
2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-03-01 | 2025-03-04 | Punam Devi 4 | 36.1598 | 9.0399 | TA413 | 9/3 | Completed
2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | Completed
2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | Completed
2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | Completed
2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | Completed
2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | Completed
2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | Completed
2025-03-10 | 2025-03-13 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 9/2 | Completed
2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | Completed
2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | Completed
2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | Completed
2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | Completed
2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-19 | 2025-03-22 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 15/3 | Completed
2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | Completed
2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | Completed
2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | Completed
2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | Completed
2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | Completed
2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | Completed
2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | Completed
2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | Completed
2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | Completed
2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | Completed
2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | Completed
2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | Completed
2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | Completed
2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | Completed
2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | Completed
2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | Completed
2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | Completed
2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | Completed
2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | Completed
2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | Completed
2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | Completed
2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | Completed
2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | Completed
2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | Completed
2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | Completed
2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | Completed
2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | Completed
2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | Completed
2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | Completed
2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | Completed
2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | Completed
2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | Completed
2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | Completed
2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | Completed
2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | Completed
2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | Completed
2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | Completed
2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | Completed
2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | Completed
2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | Completed
2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | Completed
2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | Completed
2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | Completed
2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | Completed
2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | Completed
2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | Completed
2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | Completed
2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | Completed
2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | Completed
2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | Completed
2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | Completed
2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | Completed
2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | Completed
2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | Completed
2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | Completed
2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | Completed
2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | Completed
2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | Completed
2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | Completed
2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | Completed
2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | Completed
2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | Completed
2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | Completed
2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | Completed
2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | Completed
2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | Completed
2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | Completed
2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | Completed
2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | Completed
2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | Completed
2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | Completed
2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | Completed
2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | Completed
2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | Completed
2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | Completed
2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | Completed
2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | Completed
2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | Completed
2025-09-08 | 2025-09-11 | Fouzi Ratto | 37.9311 | 9.4828 | TA413 | 43/6 | Completed
2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | Completed
2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | Completed
2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | Completed
2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | Completed
2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | Completed
2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | Completed
2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | Completed
2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | Completed
2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | Completed
2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | Completed
2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | Completed
2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | Completed
2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | Completed
2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 7.6162 | TA413 | 43/8 | Completed
2025-09-16 | 2025-09-19 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/4 | Completed
2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | Completed
2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | Completed
2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | Completed
2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | Completed
2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | Completed
2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | Completed
2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | Completed
2025-09-20 | 2025-09-23 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/5 | Completed
2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | Completed
2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | Completed
2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | Completed
2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | Completed
2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | Completed
2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | Completed
2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | Completed
2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | Completed
2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | Completed
2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | Completed
2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | Completed
2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | Completed
2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | Completed
2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | Completed
2025-09-24 | 2025-10-04 | Sk Samiul 1 | 45.697 | 4.1543 | TA413 | 30/2 | Completed
2025-09-24 | 2025-10-04 | Amar Kumar Singh | 45.697 | 4.1543 | TA413 | 41/1 | Completed
2025-09-26 | 2025-10-04 | Punam Kumari 4 | 43.8044 | 4.8672 | TA413 | 29A/5 | Completed
2025-09-27 | 2025-10-04 | Bhairaw Mahto | 37.1383 | 4.6423 | TA413 | 15/8 | Completed
2025-10-01 | 2025-10-06 | Punam Kumari 2 | 34.7898 | 5.7983 | TA413 | 18/4 | Completed
2025-09-26 | 2025-10-07 | Govind Mahto 1 | 45.697 | 3.8081 | TA413 | 3B/2 | Completed
2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 5.5651 | TA413 | 45/0 | Completed
2025-09-30 | 2025-10-09 | Kartik Mahto | 37.9311 | 3.7931 | TA413 | 40/10 | Completed
2025-10-05 | 2025-10-10 | Punam Kumari 4 | 37.9311 | 6.3218 | TA413 | 29A/4 | Completed
2025-10-01 | 2025-10-10 | Pritam Enterprises 3 | 36.1598 | 3.616 | TA413 | 3A/4 | Completed
2025-10-07 | 2025-10-10 | Punam Kumari 2 | 36.1598 | 9.0399 | TA413 | 18/5 | Completed
2025-09-25 | 2025-10-12 | Pritam Enterprises 2 | 66.7809 | 3.7101 | TA413 | 3B/0 | Completed
2025-09-25 | 2025-10-12 | Jwala Singh 1 | 72.1555 | 4.0086 | TA413 | 4/0 | Completed
2025-09-30 | 2025-10-12 | Fouzi Ratto | 70.7883 | 5.4453 | TA413 | 46/0 | Completed
2025-10-07 | 2025-10-12 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 29/1 | Completed
2025-10-11 | 2025-10-15 | Punam Kumari 2 | 45.697 | 9.1394 | TA413 | 18/6 | Completed
2025-10-01 | 2025-10-15 | Punam Kumari 1 | 87.0213 | 5.8014 | TA413 | 20/0 | Completed
2025-10-09 | 2025-10-16 | Govind Mahto 1 | 37.9311 | 4.7414 | TA413 | 3B/1 | Completed
2025-10-02 | 2025-10-17 | Pritam Enterprises 1 | 65.0278 | 4.0642 | TA413 | 10/0 | Completed
2025-10-10 | 2025-10-19 | Kartik Mahto | 35.6018 | 3.5602 | TA413 | 40/8 | Completed
2025-10-05 | 2025-10-22 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 41/0 | Completed
2025-10-06 | 2025-10-22 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 29A/0 | Completed
2025-10-12 | 2025-10-22 | Jwala Singh 2 | 37.9311 | 3.4483 | TA413 | 30/3 | Completed
2025-10-16 | 2025-10-22 | Punam Kumari 2 | 37.1383 | 5.3055 | TA413 | 18/7 | Completed
2025-10-17 | 2025-10-23 | Govind Mahto 1 | 34.7898 | 4.97 | TA413 | 20/6 | Completed
2025-10-08 | 2025-10-25 | Pritam Enterprises 4 | 62.4437 | 3.4691 | TA413 | 29/0 | Completed
2025-10-11 | 2025-10-26 | Pritam Enterprises 3 | 77.0769 | 4.8173 | TA413 | 3A/0 | Completed
2025-10-12 | 2025-10-27 | Bhairaw Mahto | 72.1555 | 4.5097 | TA413 | 23/0 | Completed
2025-10-16 | 2025-10-27 | Punam Kumari 1 | 87.0213 | 7.2518 | TA413 | 19/0 | Completed
2025-10-18 | 2025-10-28 | Pritam Enterprises 1 | 37.9311 | 3.4483 | TA413 | 9/11 | Completed
2025-10-20 | 2025-10-29 | Kartik Mahto | 55.4509 | 5.5451 | TA413 | 21/0 | Completed
2025-10-24 | 2025-10-29 | Govind Mahto 1 | 36.1598 | 6.0266 | TA413 | 21/1 | Completed
2025-10-05 | 2025-10-30 | Govind Mahto 2 | 137.0461 | 5.271 | TA413 | 15/0 | Completed
2025-10-23 | 2025-10-30 | Jwala Singh 2 | 35.6018 | 4.4502 | TA413 | 27/5 | Completed
2025-10-12 | 2025-10-31 | Jwala Singh 1 | 37.9311 | 1.8966 | TA413 | 10/1 | Completed
2025-10-28 | 2025-10-31 | Punam Kumari 1 | 36.1598 | 9.0399 | TA413 | 20/5 | Completed
2025-10-30 | 2025-11-05 | Govind Mahto 1 | 37.1383 | 5.3055 | TA413 | 20/3 | Completed
2025-10-31 | 2025-11-05 | Govind Mahto 2 | 37.9311 | 6.3218 | TA413 | 9/10 | Completed
2025-10-01 | 2025-11-06 | Punam Kumari 1 | 37.9311 | 1.0252 | TA413 | 20/4 | Completed
2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 5.9849 | TA413 | 26/0 | Completed
2025-10-01 | 2025-11-07 | Jwala Singh 1 | 37.9311 | 0.99819 | TA413 | 10/2 | Completed
2025-10-12 | 2025-11-07 | Pritam Enterprises 2 | 43.8044 | 1.6224 | TA413 | 3B/3 | Completed
2025-11-06 | 2025-11-12 | Govind Mahto 2 | 37.9311 | 5.4187 | TA413 | 9/9 | Completed
2025-11-07 | 2025-11-12 | Punam Kumari 1 | 37.9311 | 6.3218 | TA413 | 21/5 | Completed
2025-10-31 | 2025-11-12 | Jwala Singh 2 | 64.8843 | 4.9911 | TA413 | 28/0 | Completed
2025-11-06 | 2025-11-13 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 21/2 | Completed
2025-10-28 | 2025-11-13 | Bhairaw Mahto | 96.8799 | 5.6988 | TA413 | 22/0 | Completed
2025-11-10 | 2025-11-15 | Jwala Singh 1 | 37.9311 | 6.3218 | TA413 | 15/7 | Completed
2025-10-27 | 2025-11-15 | Pritam Enterprises 4 | 37.1383 | 1.8569 | TA413 | 27/4 | Completed
2025-10-30 | 2025-11-20 | Punam Kumari 1 | 36.1598 | 1.6436 | TA413 | 21/4 | Completed
2025-11-13 | 2025-11-20 | Jwala Singh 2 | 34.7898 | 4.3487 | TA413 | 27/6 | Completed
2025-11-16 | 2025-11-21 | Jwala Singh 1 | 35.6018 | 5.9336 | TA413 | 15/10 | Completed
2025-10-12 |  | Fouzi Ratto | 124.95 |  | TA413 | 24/0 | WIP
2025-11-14 |  | Govind Mahto 1 | 66.7809 |  | TA413 | 23A/0 | WIP
2025-10-23 |  | Sk Samiul 1 | 43.8044 |  | TA413 | 29A/3 | ROW
2025-11-08 |  | Ved Prakash | 173.5609 |  | TA413 | 27/0 | WIP
2025-11-12 |  | Pritam Enterprises 2 | 43.8044 |  | TA413 | 25/0 | WIP
2025-11-13 |  | Govind Mahto 2 | 73.2445 |  | TA413 | 11/0 | WIP
2025-11-16 |  | Pritam Enterprises 4 | 37.1383 |  | TA413 | 17/0 | WIP
2025-11-21 |  | Punam Kumari 1 | 43.8044 |  | TA413 | 21/3 | WIP
2025-11-21 |  | Jwala Singh 2 | 35.6018 |  | TA413 | 27/2 | WIP
2025-11-21 |  | Jwala Singh 1 | 36.1598 |  | TA413 | 15/9 | ROW
|  | Nan |  |  | TA413 | 15/1
2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | COMPLETED
2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | COMPLETED
2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | COMPLETED
2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | COMPLETED
2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 20/12 | COMPLETED
2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | COMPLETED
2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | COMPLETED
2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416 | 6/2 | COMPLETED
2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | COMPLETED
2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | COMPLETED
2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | COMPLETED
2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | COMPLETED
2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | COMPLETED
2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | COMPLETED
2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | COMPLETED
2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 4/7 | COMPLETED
2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-20 | 2025-01-25 | Asc Heights | 46.0492 | 7.6749 | TA416 | 31/6 | COMPLETED
2025-01-21 | 2025-01-25 | Pinky Dewi | 46.0492 | 9.2098 | TA416 | 12/4 | COMPLETED
2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-24 | 2025-01-29 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 17/5 | COMPLETED
2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | COMPLETED
2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | COMPLETED
2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | COMPLETED
2025-02-16 | 2025-02-21 | Amar Singh | 46.0492 | 7.6749 | TA416 | 35/7 | COMPLETED
2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-20 | 2025-02-25 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 20/4 | COMPLETED
2025-02-21 | 2025-02-25 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/7 | COMPLETED
2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | COMPLETED
2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | COMPLETED
2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | COMPLETED
2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | COMPLETED
2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 33/4 | COMPLETED
2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | COMPLETED
2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | COMPLETED
2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | COMPLETED
2025-03-22 | 2025-03-26 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8B/1 | COMPLETED
2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-08 | 2025-04-13 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 8B/2 | COMPLETED
2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-12 | 2025-04-16 | Gagan Enterprise 2 | 42.3742 | 8.4748 | TA416 | 10/1 | COMPLETED
2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/12 | COMPLETED
2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | COMPLETED
2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | COMPLETED
2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416 | 52/4 | COMPLETED
2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/11 | COMPLETED
2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | COMPLETED
2025-04-29 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 39/4 | COMPLETED
2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/8 | COMPLETED
2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | COMPLETED
2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | COMPLETED
2025-05-13 | 2025-05-17 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/9 | COMPLETED
2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | COMPLETED
2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | COMPLETED
2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | COMPLETED
2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | COMPLETED
2025-05-20 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 8.4748 | TA416 | 38/10 | COMPLETED
2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | COMPLETED
2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | COMPLETED
2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | COMPLETED
2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-26 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 7.0624 | TA416 | 12/8 | COMPLETED
2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 38/5 | COMPLETED
2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 56/5 | COMPLETED
2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-04 | 2025-06-09 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 23/2 | COMPLETED
2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-08 | 2025-06-13 | Ananya Traders 2 | 43.7758 | 7.296 | TA416 | 50/1 | COMPLETED
2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-21 | 2025-06-26 | Pinky Dewi | 46.0492 | 7.6749 | TA416 | 21/2 | COMPLETED
2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-06-27 | 2025-06-30 | Pinky Dewi | 42.3742 | 10.5936 | TA416 | 21/1 | COMPLETED
2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-10-01 | 2025-10-12 | Mahon Mahto | 78.0732 | 6.5061 | TA416 | 63/0 | COMPLETED
2025-09-22 | 2025-10-12 | Reeta Bharti | 101.692 | 4.8425 | TA416 | 27/0 | COMPLETED
2025-09-18 | 2025-10-13 | Spotyfy | 53.3239 | 2.0509 | TA416 | 53A/1 | COMPLETED
2025-09-25 | 2025-10-14 | Punam Kumari 1 | 110.6958 | 5.5348 | TA416 | 50/0 | COMPLETED
2025-09-26 | 2025-10-14 | Sainik Trader | 73.4258 | 3.8645 | TA416 | 53/0 | COMPLETED
2025-09-23 | 2025-10-14 | Ananya Trader | 143.4621 | 6.521 | TA416 | 42/0 | COMPLETED
2025-10-08 | 2025-10-22 | Punam Kumari 2 | 42.3742 | 2.8249 | TA416 | 54/2 | COMPLETED
2025-10-08 | 2025-10-26 | Pankaj Kumar | 110.6958 | 5.8261 | TA416 | 38/0 | COMPLETED
2025-10-03 | 2025-10-28 | Maa Construction | 97.834 | 3.7628 | TA416 | 0/0 | COMPLETED
2025-09-23 | 2025-10-31 | Pankaj Kumar | 110.6958 | 2.8384 | TA416 | 37/0 | COMPLETED
2025-10-15 | 2025-11-07 | Punam Kumari 2 | 73.4258 | 3.0594 | TA416 | 55/0 | COMPLETED
2025-10-09 | 2025-11-07 | Amit Choudhury | 97.2286 | 3.241 | TA416 | 45/0 | COMPLETED
2025-10-27 | 2025-11-10 | Pankaj Kumar | 75.858 | 5.0572 | TA416 | 52/1 | COMPLETED
2025-11-01 | 2025-11-13 | Aloriva Global | 43.776 | 3.3674 | TA416 | 2/2 | COMPLETED
2025-09-25 | 2025-11-14 | Mahon Mahto | 188.378 | 3.6937 | TA416 | 61/0 | COMPLETED
2025-11-01 | 2025-11-15 | Pinky Dewi | 43.776 | 2.9184 | TA416 | 56/6 | COMPLETED
2025-11-09 | 2025-11-17 | Punam Kumari 2 | 42.3742 | 4.7082 | TA416 | 55/1 | COMPLETED
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 33/12 | COMPLETED
2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 35/06 | COMPLETED
2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 34/3 | COMPLETED
2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 35/4 | COMPLETED
2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 40/1 | COMPLETED
2024-12-02 | 2024-12-06 | Gang 01 Sanjay | 27.96 | 5.592 | TA418 | 40/2 | COMPLETED
2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 42/2 | COMPLETED
2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 41/3 | COMPLETED
2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | TA418 | 41/4 | COMPLETED
2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | TA418 | 42/1 | COMPLETED
2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418 | 35/11 | COMPLETED
2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418 | 35/7 | COMPLETED
2024-12-29 | 2025-01-05 | Gang 01 Sanjay | 27.96 | 3.495 | TA418 | 33/10 | COMPLETED
2024-12-30 | 2025-01-07 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 40/4 | COMPLETED
2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 46/8 | COMPLETED
2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | TA418 | 55/1 | COMPLETED
2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | TA418 | 46/4 | COMPLETED
2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | TA418 | 34/2 | COMPLETED
2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418 | 55/2 | COMPLETED
2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 35/8 | COMPLETED
2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | TA418 | 41/1 | COMPLETED
2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 41/2 | COMPLETED
2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 54/3 | COMPLETED
2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 41/0 | COMPLETED
2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 43/0 | COMPLETED
2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 46/0 | COMPLETED
2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/9 | COMPLETED
2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | TA418 | 46/7 | COMPLETED
2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | TA418 | 45/0 | COMPLETED
2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418 | 45/1 | COMPLETED
2025-03-28 | 2025-04-01 | Gang 02 Sanjay | 28 | 5.6 | TA418 | 45/2 | COMPLETED
2025-04-02 | 2025-04-05 | Gang 02 Sanjay | 29 | 7.25 | TA418 | 40/3 | COMPLETED
2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | TA418 | 42/0 | COMPLETED
2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418 | 33/5 | COMPLETED
2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | TA418 | 55/4 | COMPLETED
2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418 | 55/0 | COMPLETED
2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | TA418 | 34/0 | COMPLETED
2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | TA418 | 46/15 | COMPLETED
2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 37/1 | COMPLETED
2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/2 | COMPLETED
2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418 | 35/0 | COMPLETED
2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418 | 46/5 | COMPLETED
2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | TA418 | 34/4 | COMPLETED
2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 35/3 | COMPLETED
2025-05-29 | 2025-06-02 | Gang 01 Sanjay | 27 | 5.4 | TA418 | 40/5 | COMPLETED
2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 33/7 | COMPLETED
2025-06-09 | 2025-06-12 | Gang 02 Sanjay | 27 | 6.75 | TA418 | 33/8 | COMPLETED
2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | TA418 | 33/9 | COMPLETED
2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418 | 33/6 | COMPLETED
2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418 | 38/2 | COMPLETED
2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418 | 37/0 | COMPLETED
2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | TA418 | 37/2 | COMPLETED
2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418 | 38/1 | COMPLETED
2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418 | 35/9 | COMPLETED
2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 35/5 | COMPLETED
2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-07-24 | 2025-08-06 | Gang 02 Sanjay Kec 02 Barkat Ali | 29 | 2.0714 | TA418 | 41/5 | COMPLETED
2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418 | 35/10 | COMPLETED
2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418 | 48A/0 | COMPLETED
2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 43/1 | COMPLETED
2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | TA418 | 52/0 | COMPLETED
2025-08-22 | 2025-08-26 | Kec 02 Barkat Ali | 28 | 5.6 | TA418 | 46/3 | COMPLETED
2025-08-26 | 2025-10-17 | Kec 02 Barkat Ali | 28 | 0.5283 | TA418 | 60/2 | COMPLETED
2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418 | 33/3 | COMPLETED
2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418 | 62/0 | COMPLETED
2025-09-03 | 2025-09-07 | Subhash | 27.9 | 5.58 | TA418 | 46/12 | COMPLETED
2025-09-05 | 2025-10-03 | Savitha | 45 | 1.5517 | TA418 | 56/0 | COMPLETED
2025-09-08 |  | Subhash | 33 |  | TA418 | 46/11 | (ROW)
2025-09-09 | 2025-09-13 | Subhash | 29 | 5.8 | TA418 | 48/2 | COMPLETED
2025-09-09 | 2025-09-30 | M S Mdpl | 33.3 | 1.5136 | TA418 | 45/3 | COMPLETED
2025-09-12 | 2025-09-22 | M S Tofit | 33.3 | 3.0273 | TA418 | 33/2 | COMPLETED
2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418 | 61/0 | COMPLETED
2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | TA418 | 53/0 | COMPLETED
2025-09-22 | 2025-09-30 | M S Tofit | 27 | 3 | TA418 | 33/1 | COMPLETED
2025-09-25 | 2025-10-01 | Subhash | 50 | 7.1429 | TA418 | 44/0 | COMPLETED
2025-09-28 | 2025-10-05 | Kec 02 Barkat Ali | 27 | 3.375 | TA418 | 54/1 | COMPLETED
2025-09-29 | 2025-10-17 | M S Mdpl | 60 | 3.1579 | TA418 | 54/0 | COMPLETED
2025-10-04 | 2025-10-17 | M S Tofit | 60 | 4.2857 | TA418 | 32/0 | COMPLETED
2025-10-16 | 2025-11-07 | M S Tofit | 89 | 3.8696 | TA418 | 33/0 | COMPLETED
2025-10-16 |  | M S Mdpl | 89 |  | TA418 | 39/0 | 3rd section work.
2025-10-18 | 2025-10-27 | Kec 02 Barkat Ali | 28 | 2.8 | TA418 | 60/4 | COMPLETED
2025-10-29 | 2025-11-06 | Kec 02 Barkat Ali | 28 | 3.1111 | TA418 | 46/10 | COMPLETED
2025-11-04 | 2025-11-12 | Kec 02 Barkat Ali | 28 | 3.1111 | TA418 | 46/6 | COMPLETED
2025-11-06 | 2025-11-13 | M S Mdpl | 28 | 3.5 | TA418 | 43/2 | COMPLETED
2025-11-06 |  | M S Tofit | 45 |  | TA418 | 48/0 | Cage 02 section work under progress.
2025-11-06 |  | Kec 02 Barkat Ali | 29 |  | TA418 | 33/4 | 1st section work under progress.
2025-01-27 | 2025-02-12 | Radha Enterprises | 87.021 | 5.1189 | TA419 | 0A/0 (CT) | Completed
2025-09-23 | 2025-11-05 | Infinidea | 72.474 | 1.6471 | TA419 | 0B/0 | Completed
2025-02-19 | 2025-03-04 | Pinki Devi | 37.931 | 2.7094 | TA419 | 0B/1 | Completed
2024-12-04 | 2024-12-23 | Radha Enterprises | 37.931 | 1.8965 | TA419 | 0B/2 | Completed
2025-01-19 | 2025-01-27 | Radha Enterprises | 43.804 | 4.8671 | TA419 | 0B/3 | Completed
2025-11-15 |  | Dhruv | 73.245 |  | TA419 | 0C/0 | WIP
2025-01-20 | 2025-01-28 | Pinki Devi | 37.931 | 4.2146 | TA419 | 0C/1 | Completed
2025-02-13 | 2025-02-25 | Pinki Devi | 59.501 | 4.577 | TA419 | 0D/0 | Completed
2024-12-22 | 2024-12-31 | Radha Enterprises | 43.804 | 4.3804 | TA419 | 0D/1 | Completed
2025-01-12 | 2025-01-19 | Pinki Devi | 37.138 | 4.6422 | TA419 | 0D/2 | Completed
2025-01-28 | 2025-02-08 | Pinki Devi | 45.697 | 3.8081 | TA419 | 0D/3 | Completed
2025-02-08 | 2025-02-15 | Pinki Devi | 36.16 | 4.52 | TA419 | 0D/4 | Completed
2025-02-07 | 2025-02-27 | Radha Enterprises 2 | 66.776 | 3.1798 | TA419 | 0D/5 | Completed
|  | Nan | 77.077 |  | TA419 | 0E/0
2025-01-11 | 2025-01-18 | Radha Enterprises | 37.931 | 4.7414 | TA419 | 0E/1 | Completed
2025-01-04 | 2025-01-10 | Radha Enterprises | 37.931 | 5.4187 | TA419 | 0E/2 | Completed
2025-02-25 | 2025-03-31 | Radha Enterprises 2 | 67.262 | 1.9218 | TA419 | 0F/0 | Completed
2025-08-15 | 2025-08-31 | Madhu Sah | 66.776 | 3.928 | TA419 | 0G/0 | Completed
2025-08-20 | 2025-08-27 | Infinidea | 36.16 | 4.52 | TA419 | 0G/1 | Completed
2025-08-01 | 2025-09-15 | Madhu Sah | 83.134 | 1.8073 | TA419 | 0H/0 | Completed
2025-08-01 | 2025-09-22 | Infinidea | 57.963 | 1.0936 | TA419 | 1/0 | Completed
|  | Nan | 58.8823 |  | TA419 | 2/0
|  | Nan | 78.7772 |  | TA419 | 3/0
2025-08-12 | 2025-08-19 | Madhu Sah | 37.931 | 4.7414 | TA419 | 3/1 | Completed
2025-07-29 | 2025-09-07 | Infinidea | 37.931 | 0.92515 | TA419 | 3/2 | Completed
2025-10-06 | 2025-10-12 | Madhu Sah | 35.602 | 5.086 | TA419 | 3/3 | Completed
2025-09-28 | 2025-10-05 | Madhu Sah | 43.804 | 5.4755 | TA419 | 3/4 | Completed
2025-05-05 | 2025-05-11 | Madhu Sah | 37.138 | 5.3054 | TA419 | 3/5 | Completed
2025-09-15 | 2025-09-27 | Madhu Sah | 59.501 | 4.577 | TA419 | 4/0 | Completed
2025-04-28 | 2025-05-04 | Madhu Sah | 37.931 | 5.4187 | TA419 | 4/1 | Completed
2025-04-14 | 2025-04-27 | Madhu Sah | 59.501 | 4.2501 | TA419 | 5/0 | Completed
2025-04-07 | 2025-04-17 | Madhu Sah | 34.79 | 3.1627 | TA419 | 5/1 | Completed
2025-03-24 | 2025-04-11 | Madhu Sah | 36.16 | 1.9032 | TA419 | 5/2 | Completed
2025-02-23 | 2025-02-28 | Madhu Sah | 37.931 | 6.3218 | TA419 | 5/3 | Completed
2025-02-09 | 2025-02-18 | Madhu Sah | 43.804 | 4.3804 | TA419 | 5/4 | completed
2025-02-02 | 2025-02-11 | Madhu Sah | 62.444 | 6.2444 | TA419 | 6/0 | Completed
2025-01-11 | 2025-01-16 | Madhu Sah | 36.16 | 6.0267 | TA419 | 6/1 | Completed
2024-12-12 | 2024-12-17 | Madhu Sah | 37.931 | 6.3218 | TA419 | 6/2 | Completed
2024-12-06 | 2024-12-11 | Madhu Sah | 37.138 | 6.1897 | TA419 | 6/3 | Completed
2025-01-20 | 2025-01-27 | Madhu Sah | 36.16 | 4.52 | TA419 | 6/4 | Completed
2025-01-17 | 2025-01-21 | Madhu Sah | 43.804 | 8.7608 | TA419 | 6/5 | Completed
2025-02-18 | 2025-02-24 | Madhu Sah | 36.16 | 5.1657 | TA419 | 6/6 | Completed
2025-01-27 | 2025-02-01 | Madhu Sah | 36.16 | 6.0267 | TA419 | 6/7 | Completed
2024-11-21 | 2024-11-28 | Madhu Sah | 35.602 | 4.4502 | TA419 | 6/8 | Completed
2024-01-06 | 2025-01-13 | Madhu Sah | 34.79 | 0.093021 | TA419 | 6/9 | Completed
2024-12-17 | 2024-12-23 | Madhu Sah | 34.79 | 4.97 | TA419 | 6/10 | Completed
2024-11-28 | 2024-12-05 | Madhu Sah | 36.16 | 4.52 | TA419 | 6/11 | Completed
2024-12-22 | 2024-12-31 | Madhu Sah | 37.931 | 3.7931 | TA419 | 6/12 | Completed
|  | Nan | 57.963 |  | TA419 | 7/0
2025-03-01 | 2025-03-08 | Madhu Sah | 37.138 | 4.6422 | TA419 | 7/1 | Completed
|  | Nan | 58.8823 |  | TA419 | 8/0
|  | Nan | 81.828 |  | TA419 | 9/0
2025-08-14 | 2025-08-30 | Radha Enterprises | 124.95 | 7.35 | TA419 | 10/0 | Completed
2025-11-05 |  | Bhairo Mahato | 160.944 |  | TA419 | 11/0 | WIP
2025-08-04 | 2025-08-13 | Radha Enterprises | 65.023 | 6.5023 | TA419 | 11/1 | Completed
2025-08-31 | 2025-09-07 | Radha Enterprises | 66.776 | 8.347 | TA419 | 11/2 | Completed
2025-04-11 | 2025-04-19 | Poornam Kumari | 37.931 | 4.2146 | TA419 | 11/3 | Completed
2025-04-03 | 2025-04-14 | Poornam Kumari | 43.804 | 3.6503 | TA419 | 11/4 | Completed
2025-04-19 | 2025-04-29 | Poornam Kumari | 59.501 | 5.4092 | TA419 | 12/0 | Completed
2025-03-26 | 2025-04-05 | Poornam Kumari | 36.16 | 3.2873 | TA419 | 12/1 | Completed
2025-09-07 | 2025-09-13 | Radha Enterprises | 36.16 | 5.1657 | TA419 | 12/2 | Completed
2025-04-28 | 2025-05-07 | Poonam Kumari | 55.451 | 5.5451 | TA419 | 12A/0 | Completed
|  | Nan | 37.931 |  | TA419 | 12A/1
|  | Nan | 83.134 |  | TA419 | 13/0
|  | Nan | 83.134 |  | TA419 | 14/0
|  | Nan | 36.16 |  | TA419 | 14/1
|  | Nan | 62.444 |  | TA419 | 15/0
2025-03-02 | 2025-03-26 | Poonam Kumari | 73.245 | 2.9298 | TA419 | 15A/0 | Completed
2025-10-12 | 2025-10-26 | Poonam Kumari | 69.376 | 4.6251 | TA419 | 16/0 | Completed
2025-02-22 | 2025-03-07 | Poonam Kumari | 59.501 | 4.2501 | TA419 | 17/0 | Completed
2025-02-08 | 2025-02-14 | Poonam Kumari | 34.79 | 4.97 | TA419 | 17/1 | Completed
2025-01-31 | 2025-02-09 | Poonam Kumari | 37.138 | 3.7138 | TA419 | 17/2 | Completed
2025-02-14 | 2025-02-25 | Poonam Kumari | 67.262 | 5.6052 | TA419 | 18/0 | Completed
2025-01-27 | 2025-02-05 | Radha Enterprises | 62.444 | 6.2444 | TA419 | 19/0 | Completed
2025-01-23 | 2025-01-27 | Radha Enterprises | 35.602 | 7.1204 | TA419 | 19/1 | Completed
2024-11-19 | 2024-12-10 | Punam Kumari | 36.16 | 1.6436 | TA419 | 19/2 | Completed
2025-01-18 | 2025-01-22 | Radha Enterprises | 37.931 | 7.5862 | TA419 | 19/3 | Completed
2025-01-11 | 2025-01-17 | Radha Enterprises | 36.16 | 5.1657 | TA419 | 19/4 | Completed
2025-02-03 | 2025-02-12 | Radha Enterprises | 37.138 | 3.7138 | TA419 | 19/5 | Completed
2025-02-07 | 2025-02-20 | Radha Enterprises 1 | 65.872 | 4.7051 | TA419 | 20/0 | completed
2024-11-21 | 2024-11-27 | Radha Enterprises | 34.79 | 4.97 | TA419 | 20/1 | Completed
2024-11-28 | 2024-12-03 | Radha Enterprises | 34.79 | 5.7983 | TA419 | 20/2 | Completed
2025-07-19 | 2025-07-26 | Radha Enterprises | 55.451 | 6.9314 | TA419 | 20/3 | Completed
2025-09-14 | 2025-10-05 | Radha Enterprises | 137.046 | 6.2294 | TA419 | 21/0 | Completed
2025-04-29 | 2025-05-19 | Radha Enterprises | 137.046 | 6.526 | TA419 | 22/0 | completed
2025-02-19 | 2025-02-28 | Radha Enterprises 1 | 45.697 | 4.5697 | TA419 | 22/1 | Completed
2024-12-04 | 2024-12-08 | Radha Enterprises | 35.602 | 7.1204 | TA419 | 22/2 | Completed
2024-12-09 | 2024-12-13 | Radha Enterprises | 35.602 | 7.1204 | TA419 | 22/3 | Completed
2024-12-22 | 2024-12-31 | Radha Enterprises | 59.501 | 5.9501 | TA419 | 23/0 | Completed
2024-12-14 | 2024-12-17 | Radha Enterprises | 34.79 | 8.6975 | TA419 | 23/1 | Completed
2024-12-18 | 2024-12-23 | Radha Enterprises | 36.16 | 6.0267 | TA419 | 23/2 | Completed
2025-03-06 | 2025-03-12 | Radha Enterprises 1 | 37.931 | 5.4187 | TA419 | 23/3 | Completed
2025-03-08 | 2025-03-24 | Radha Enterprises | 73.245 | 4.3085 | TA419 | 24/0 | Completed
2025-01-03 | 2025-01-09 | Radha Enterprises | 34.79 | 4.97 | TA419 | 24/1 | Completed
2025-04-23 | 2025-04-28 | Radha Enterprises | 37.138 | 6.1897 | TA419 | 24/2 | Completed
2025-03-27 | 2025-04-05 | Radha Enterprises 1 | 35.602 | 3.5602 | TA419 | 24/3 | Completed
|  | Nan | 58.8823 |  | TA419 | 25/0
2025-10-06 | 2025-10-18 | Radha Enterprises 1 | 99.779 | 7.6753 | TA419 | 26/0 | Completed
2025-03-22 | 2025-03-28 | Radha Enterprises 1 | 36.16 | 5.1657 | TA419 | 26/1 | Completed
2025-07-28 | 2025-08-03 | Radha Enterprises 1 | 35.602 | 5.086 | TA419 | 26/2 | Completed
2025-04-12 | 2025-04-18 | Radha Enterprises 1 | 36.16 | 5.1657 | TA419 | 26/3 | Completed
2025-04-17 | 2025-04-23 | Radha Enterprises 1 | 36.16 | 5.1657 | TA419 | 26/4 | Completed
2025-03-31 | 2025-04-08 | Radha Enterprises 1 | 35.602 | 3.9558 | TA419 | 26/5 | Completed
2025-04-08 | 2025-04-13 | Radha Enterprises 1 | 36.16 | 6.0267 | TA419 | 26/6 | Completed
2025-05-19 | 2025-06-03 | Radha Enterprises 1 | 73.245 | 4.5778 | TA419 | 27/0 | Completed
2025-06-05 | 2025-06-13 | Radha Enterprises 1 | 43.804 | 4.8671 | TA419 | 27/1 | Completed
2025-06-12 | 2025-06-20 | Radha Enterprises 1 | 34.79 | 3.8656 | TA419 | 27/2 | Completed
2025-06-21 | 2025-06-26 | Radha Enterprises 1 | 36.16 | 6.0267 | TA419 | 27/3 | Completed
2025-06-27 | 2025-07-08 | Radha Enterprises 1 | 67.262 | 5.6052 | TA419 | 28/0 | Completed
2025-04-12 | 2025-04-21 | Gagan Enterprises | 34.79 | 3.479 | TA419 | 28/1 | Completed
2025-07-09 | 2025-07-18 | Radha Enterprises 1 | 65.023 | 6.5023 | TA419 | 29/0 | Completed
2025-10-26 | 2025-11-12 | Nan | 73.245 | 4.0692 | TA419 | 30/0 | Completed
2025-03-31 | 2025-04-13 | Gagan Enterprises | 36.16 | 2.5829 | TA419 | 30/1 | Completed
2025-04-28 | 2025-05-10 | Gagan Enterprises | 83.134 | 6.3949 | TA419 | 31/0 | Completed
2025-04-22 | 2025-04-29 | Gagan Enterprises | 43.804 | 5.4755 | TA419 | 31/1 | Completed
2025-10-14 | 2025-10-27 | Poonam Kumari 2 | 43.804 | 3.1289 | TA419 | 31/2 | Completed
|  | Nan | 87.021 |  | TA419 | 32/0
|  | Nan | 83.134 |  | TA419 | 33/0
|  | Nan | 34.79 |  | TA419 | 33/1
2025-07-01 | 2025-07-17 | Madhu Sah | 83.134 | 4.8902 | TA419 | 34/0 | Completed
2025-07-18 | 2025-07-24 | Madhu Sah | 36.16 | 5.1657 | TA419 | 34/1 | Completed
2025-10-27 | 2025-11-13 | Pumam Kumari 1 | 77.077 | 4.2821 | TA419 | 35/0 | Completed
2025-11-12 |  | Pumam Kumari 1 | 75.27 |  | TA419 | 36/0 | WIP
2025-07-26 | 2025-08-01 | Madhu Sah | 37.931 | 5.4187 | TA419 | 36/1 | Completed
2025-08-02 | 2025-08-07 | Madhu Sah | 37.931 | 6.3218 | TA419 | 36/2 | Completed
|  | Nan | 43.804 |  | TA419 | 36/3
|  | Nan | 82.264 |  | TA419 | 36/4
|  | Nan | 45.697 |  | TA419 | 36/5
2025-10-23 | 2025-10-30 | Jwala Singh | 36.16 | 4.52 | TA419 | 36/6 | Completed
2025-10-16 | 2025-10-23 | Jwala Singh | 36.16 | 4.52 | TA419 | 36/7 | Completed
2025-11-01 | 2025-11-08 | Jwala Singh | 36.16 | 4.52 | TA419 | 36/8 | Completed
|  | Nan | 37.138 |  | TA419 | 36/9
|  | Nan | 43.804 |  | TA419 | 36/10
|  | Nan | 137.046 |  | TA419 | 37/0
2025-11-12 |  | Punam Kumari 2 | 137.046 |  | TA419 | 38/0 | WIP
|  | Nan | 36.16 |  | TA419 | 38/1
|  | Nan | 36.16 |  | TA419 | 38/2
|  | Nan | 37.931 |  | TA419 | 38/3
|  | Nan | 36.16 |  | TA419 | 38/4
|  | Nan | 37.931 |  | TA419 | 38/5
|  | Nan | 37.138 |  | TA419 | 38/6
2025-11-12 |  | Infinidea 2 | 37.931 |  | TA419 | 38/7 | WIP
|  | Nan | 37.931 |  | TA419 | 38/8
|  | Nan | 35.602 |  | TA419 | 38/9
|  | Nan | 36.16 |  | TA419 | 38/10
|  | Nan | 36.16 |  | TA419 | 38/11
|  | Nan | 124.95 |  | TA419 | 39/0
|  | Nan | 124.95 |  | TA419 | 40/0
|  | Nan | 34.79 |  | TA419 | 40/1
|  | Nan | 37.931 |  | TA419 | 40/2
|  | Nan | 37.931 |  | TA419 | 40/3
|  | Nan | 37.138 |  | TA419 | 40/4
2025-11-08 | 2025-11-16 | Madhu Sah | 37.138 | 4.1264 | TA419 | 40/5 | Completed
2025-11-17 |  | Madhu Sah | 37.138 |  | TA419 | 40/6 | WIP
|  | Nan | 35.602 |  | TA419 | 40/7
|  | Nan | 36.16 |  | TA419 | 40/8
|  | Nan | 36.16 |  | TA419 | 40/9
|  | Nan | 83.134 |  | TA419 | 41/0
|  | Nan | 34.79 |  | TA419 | 41/1
|  | Nan | 35.602 |  | TA419 | 41/2
|  | Nan | 36.16 |  | TA419 | 41/3
2025-11-15 |  | Jwala Singh | 43.804 |  | TA419 | 41/4 | WIP
2025-11-08 | 2025-11-14 | Jwala Singh | 37.138 | 5.3054 | TA419 | 41/5 | Completed
|  | Nan | 37.931 |  | TA419 | 41/6
|  | Nan | 36.16 |  | TA419 | 41/7
|  | Nan | 36.16 |  | TA419 | 41/8
|  | Nan | 152.3804 |  | TA419 | 42/0
|  | Nan | 139.9685 |  | TA419 | 43/0
|  | Nan | 45.697 |  | TA419 | 43/1
|  | Nan | 35.602 |  | TA419 | 43/2
|  | Nan | 36.16 |  | TA419 | 43/3
|  | Nan | 34.79 |  | TA419 | 43/4
2025-11-19 |  | Mukhilal 1 | 37.138 |  | TA419 | 43/5 | WIP
|  | Nan | 34.79 |  | TA419 | 43/6
|  | Nan | 64.4822 |  | TA419 | 44/0
|  | Nan | 118.4303 |  | TA419 | 45/0
|  | Nan | 143.4621 |  | TA419 | 46/0
|  | Nan | 43.7757 |  | TA419 | 46/1
2025-11-12 |  | Satyam Trading | 46.0492 |  | TA419 | 46/2 | WIP
2025-11-12 |  | Maheshwar | 43.7757 |  | TA419 | 46/3 | WIP
|  | Nan | 53.3239 |  | TA419 | 46/4
|  | Nan |  |  | TA419 | 47/0
|  | Nan | 78.6863 |  | TA419 | 48/0
|  | Nan | 67.112 |  | TA419 | 48/1
|  | Nan |  |  | TA419 | 49/0
|  | Nan |  |  | TA419 | 50/0
|  | Nan | 64.4822 |  | TA419 | 50/1
|  | Nan | 89.7178 |  | TA419 | 51/0
|  | Nan | 67.112 |  | TA419 | 52/0
|  | Nan | 42.3742 |  | TA419 | 52/1
|  | Nan | 42.3742 |  | TA419 | 52/2
|  | Nan | 73.4258 |  | TA419 | 53/0
|  | Nan | 64.4822 |  | TA419 | 54/0
|  | Nan | 43.7757 |  | TA419 | 54/1
|  | Nan | 43.7757 |  | TA419 | 54/2
|  | Nan | 42.3742 |  | TA419 | 54/3
|  | Nan | 43.7757 |  | TA419 | 54/4
|  | Nan | 46.0492 |  | TA419 | 54/5
|  | Nan | 43.7757 |  | TA419 | 54/6
|  | Nan | 55.3387 |  | TA419 | 54/7
|  | Nan | 67.112 |  | TA419 | 55/0
|  | Nan | 42.3742 |  | TA419 | 55/1
|  | Nan | 42.3742 |  | TA419 | 55/2
|  | Nan | 42.3742 |  | TA419 | 55/3
|  | Nan | 46.0492 |  | TA419 | 55/4
|  | Nan | 43.7757 |  | TA419 | 55/5
|  | Nan | 55.3387 |  | TA419 | 55/6
|  | Nan | 93.2387 |  | TA419 | 56/0
|  | Nan | 83.231 |  | TA419 | 57/0
|  | Nan | 53.3239 |  | TA419 | 57/1
|  | Nan | 38.8484 |  | TA419 | 58/0
|  | Nan | 38.8484 |  | TA419 | 59/0
|  | Nan | 43.7757 |  | TA419 | 59/1
|  | Nan | 78.6863 |  | TA419 | 60/0
|  | Nan | 78.6863 |  | TA419 | 61/0
|  | Nan | 43.7757 |  | TA419 | 61/1
|  | Nan | 73.4258 |  | TA419 | 62/0
2025-11-15 |  | Rohit | 53.3239 |  | TA419 | 62/1 | WIP
|  | Nan | 53.3239 |  | TA419 | 62/2
|  | Nan | 75.9057 |  | TA419 | 62/3
|  | Nan | 42.3742 |  | TA419 | 62/4
|  | Nan | 55.3387 |  | TA419 | 62/5
|  | Nan | 64.4822 |  | TA419 | 63/0
|  | Nan | 43.7757 |  | TA419 | 63/1
|  | Nan | 43.7757 |  | TA419 | 63/2
|  | Nan | 43.7757 |  | TA419 | 63/3
|  | Nan | 42.3742 |  | TA419 | 63/4
|  | Nan | 42.3742 |  | TA419 | 63/5
|  | Nan | 43.7757 |  | TA419 | 63/6
|  | Nan | 86.2562 |  | TA419 | 63A/0
|  | Nan | 86.2562 |  | TA419 | 63B/0
|  | Nan | 43.7757 |  | TA419 | 63B/1
|  | Nan | 53.3239 |  | TA419 | 63B/2
|  | Nan | 42.3742 |  | TA419 | 63B/3
|  | Nan | 43.7757 |  | TA419 | 63B/4
|  | Nan | 42.3742 |  | TA419 | 63B/5
|  | Nan | 46.0492 |  | TA419 | 63B/6
|  | Nan | 75.9057 |  | TA419 | 64/0
|  | Nan | 42.3742 |  | TA419 | 64/1
|  | Nan | 78.6863 |  | TA419 | 64/2
|  | Nan | 55.3387 |  | TA419 | 64/3
|  | Nan | 53.3239 |  | TA419 | 64/4
|  | Nan | 43.7757 |  | TA419 | 64/5
|  | Nan | 90.1252 |  | TA419 | 64A/0
|  | Nan | 113.6796 |  | TA419 | 65/0
|  | Nan | 42.3742 |  | TA419 | 65/1
|  | Nan | 53.3239 |  | TA419 | 65/2
|  | Nan | 73.4258 |  | TA419 | 66/0
|  | Nan | 55.3387 |  | TA419 | 66/1
|  | Nan | 90.1252 |  | TA419 | 67/0
|  | Nan |  |  | TA419 | 68/0
|  | Nan |  |  | TA419 | 69/0
|  | Nan | 104.8666 |  | TA419 | 70/0
|  | Nan | 143.4621 |  | TA419 | 71/0
|  | Nan | 118.4303 |  | TA419 | 72/0
|  | Nan | 73.4258 |  | TA419 | 73/0
|  | Nan | 97.2286 |  | TA419 | 74/0
|  | Nan | 143.4621 |  | TA419 | 75/0
|  | Nan | 118.4303 |  | TA419 | 76/0
|  | Nan | 43.7757 |  | TA419 | 76/1
|  | Nan | 46.0492 |  | TA419 | 76/2
2025-11-19 |  | Ganesh Construction | 46.0492 |  | TA419 | 76/3 | WIP
|  | Nan | 73.4258 |  | TA419 | 77/0
|  | Nan | 67.112 |  | TA419 | 78/0
|  | Nan | 43.7757 |  | TA419 | 78/1
|  | Nan | 46.0492 |  | TA419 | 78/2
|  | Nan | 43.7757 |  | TA419 | 78/3
|  | Nan | 46.0492 |  | TA419 | 78/4
|  | Nan | 75.9057 |  | TA419 | 78A/0
|  | Nan | 89.7178 |  | TA419 | 79/0
|  | Nan | 93.2387 |  | TA419 | 80/0
|  | Nan | 90.1252 |  | TA419 | 81/0
|  | Nan | 104.8666 |  | TA419 | 82/0
|  | Nan | 90.1252 |  | TA419 | 83/0
|  | Nan | 55.3387 |  | TA419 | 83/1
|  | Nan | 46.0492 |  | TA419 | 83/2
|  | Nan | 55.3387 |  | TA419 | 83/3
|  | Nan | 42.3742 |  | TA419 | 83/4
|  | Nan | 42.3742 |  | TA419 | 83/5
|  | Nan | 42.3742 |  | TA419 | 83/6
2025-11-19 |  | Amit Yadav | 43.7757 |  | TA419 | 83/7 | WIP
|  | Nan | 42.3742 |  | TA419 | 83/8
|  | Nan | 46.0492 |  | TA419 | 83/9
|  | Nan | 73.4258 |  | TA419 | 84/0
|  | Nan | 43.7757 |  | TA419 | 84/1
|  | Nan | 46.0492 |  | TA419 | 84/2
|  | Nan | 42.3742 |  | TA419 | 84/3
|  | Nan | 42.3742 |  | TA419 | 84/4
|  | Nan | 43.7757 |  | TA419 | 84/5
|  | Nan | 64.4822 |  | TA419 | 84A/0
|  | Nan | 46.0492 |  | TA419 | 84A/1
|  | Nan | 73.4258 |  | TA419 | 85/0
|  | Nan | 113.6796 |  | TA419 | 85A/0
|  | Nan | 38.8484 |  | TA419 | 86/0
|  | Nan | 53.3239 |  | TA419 | 86/1
|  | Nan | 46.0492 |  | TA419 | 86/2
|  | Nan | 97.2286 |  | TA419 | 86A/0
|  | Nan | 53.3239 |  | TA419 | 86A/1
|  | Nan | 55.3387 |  | TA419 | 86A/2
|  | Nan | 46.0492 |  | TA419 | 86A/3
|  | Nan | 67.112 |  | TA419 | 86A/4
|  | Nan | 55.3387 |  | TA419 | 86A/5
|  | Nan | 64.4822 |  | TA419 | 87/0
|  | Nan | 46.0492 |  | TA419 | 87/1
|  | Nan | 43.7757 |  | TA419 | 87/2
|  | Nan | 64.4822 |  | TA419 | 88/0
|  | Nan | 42.3742 |  | TA419 | 88/1
|  | Nan | 46.0492 |  | TA419 | 88/2
|  | Nan | 73.4258 |  | TA419 | 89/0
|  | Nan | 97.2286 |  | TA419 | 90/0
|  | Nan | 73.4258 |  | TA419 | 90A/0
|  | Nan | 42.3742 |  | TA419 | 90A/1
|  | Nan | 97.2286 |  | TA419 | 90B/0
|  | Nan | 78.0732 |  | TA419 | 91/0
|  | Nan | 86.2562 |  | TA419 | 92/0
|  | Nan | 73.4258 |  | TA419 | 93/0
|  | Nan | 86.2562 |  | TA419 | 93A/0
|  | Nan | 97.2286 |  | TA419 | 93B/0
|  | Nan | 83.231 |  | TA419 | 93C/0
|  | Nan | 104.8666 |  | TA419 | 94/0
|  | Nan | 110.6958 |  | TA419 | 95/0
|  | Nan |  |  | TA419 | 95A/0
|  | Nan |  |  | TA419 | 96/0
|  | Nan | 64.4822 |  | TA419 | 96/1
|  | Nan | 55.3387 |  | TA419 | 96/2
|  | Nan | 90.1252 |  | TA419 | 97/0
|  | Nan |  |  | TA419 | 98/0
|  | Nan |  |  | TA419 | 99/0
|  | Nan | 113.6796 |  | TA419 | 100/0
|  | Nan | 97.2286 |  | TA419 | 101/0
|  | Nan |  |  | TA419
|  | Nan |  |  | TA419
|  | Nan |  |  | TA419
|  | Nan |  |  | TA419 |  | `
2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-16 | 2024-08-18 | Khatan | 36.37 | 12.1233 | TA421 | 26/3 | Completed
2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421 | 21/6 | Completed
2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-16 | 2024-12-18 | Subash | 36.37 | 12.1233 | TA421 | 19/2 | Completed
2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421 | 18/3 | Completed
2024-12-23 | 2024-12-25 | Subash | 36.37 | 12.1233 | TA421 | 18/2 | Completed
2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-26 | 2024-12-28 | Subash | 36.37 | 12.1233 | TA421 | 18/1 | Completed
2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421 | 29/6 | Completed
2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421 | 13/1 | Completed
2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421 | 13/6 | Completed
2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421 | 29/7 | Completed
2025-02-28 | 2025-03-02 | Subash | 36.37 | 12.1233 | TA421 | 13/5 | Completed
2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421 | 13/0 | Completed
2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421 | 38/4 | Completed
2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421 | 13/9 | Completed
2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-20 | 2025-03-22 | Subash | 36.37 | 12.1233 | TA421 | 13/10 | Completed
2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421 | 38/6 | Completed
2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421 | 15/1 | Completed
2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-27 | 2025-03-29 | Subash | 37.93 | 12.6433 | TA421 | 15/2 | Completed
2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421 | 35/3 | Completed
2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421 | 16/3 | Completed
2025-04-19 | 2025-04-21 | Subash | 36.37 | 12.1233 | TA421 | 16/4 | Completed
2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-22 | 2025-04-24 | Subash | 36.37 | 12.1233 | TA421 | 16/5 | Completed
2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-25 | 2025-04-27 | Subash | 36.37 | 12.1233 | TA421 | 15/3 | Completed
2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-28 | 2025-04-30 | Subash | 36.37 | 12.1233 | TA421 | 13/11 | Completed
2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421 | 27/9 | Completed
2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421 | 10/7 | Completed
2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421 | 38/2 | Completed
2025-05-05 | 2025-05-06 | Subash | 36.37 | 18.185 | TA421 | 11/1 | Completed
2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421 | 10/9 | Completed
2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421 | 10/4 | Completed
2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421 | 10/2 | Completed
2025-05-18 | 2025-05-20 | Subash | 37.93 | 12.6433 | TA421 | 10/1 | Completed
2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421 | 11/2 | Completed
2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421 | 11/3 | Completed
2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-08 | 2025-07-12 | Subash | 33.38 | 6.676 | TA421 | 9/10 | Completed
2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-05 | 2025-07-13 | Naziruddin | 71.706 | 7.9673 | TA421 | 14/0 | Completed
2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421 | 9/8 | Completed
2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421 | 6/3 | Completed
2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421 | 9/7 | Completed
2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-19 | 2025-07-21 | Khatun | 31.99 | 10.6633 | TA421 | 6/2 | Completed
2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421 | 4/21 | Completed
2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421 | 8/8 | Completed
2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-08-02 | 2025-08-04 | Khatun | 31.99 | 10.6633 | TA421 | 6/6 | Completed
2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421 | 8/13 | Completed
2025-08-09 | 2025-08-11 | Khatun | 31.99 | 10.6633 | TA421 | 4/23 | Completed
2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421 | 2/3 | Completed
2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421 | 9/9 | Completed
2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-05 | 2025-09-07 | Subash | 31.99 | 10.6633 | TA421 | 4/6 | Completed
2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421 | 4/0 | Completed
2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-08 | 2025-09-09 | Subash | 33.38 | 16.69 | TA421 | 4/7 | Completed
2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421 | 42/9 | Completed
2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421 | 4/2 | Completed
2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-10-01 | 2025-10-09 | Subash | 72.63 | 8.07 | TA421 | 1/0 | Completed
2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-09-13 | 2025-10-11 | Praveen | 43.079 | 1.4855 | TA421 | 39/7 | Completed
2025-10-07 | 2025-10-11 | D K Verma | 36.37 | 7.274 | TA421 | 43/3 | Completed
2025-10-07 | 2025-10-12 | Khatun | 39.17 | 6.5283 | TA421 | 9/3 | Completed
2025-10-10 | 2025-10-15 | Subash | 37.72 | 6.2867 | TA421 | 4/3 | Completed
2025-10-12 | 2025-10-16 | D K Verma | 44.851 | 8.9702 | TA421 | 43/5 | Completed
2025-10-13 | 2025-10-17 | Khatun | 39.17 | 7.834 | TA421 | 4/20 | Completed
2025-10-10 | 2025-10-19 | Hassan | 37.931 | 3.7931 | TA421 | 36/7 | Completed
2025-10-17 | 2025-10-21 | Subash | 31.99 | 6.398 | TA421 | 4/4 | Completed
2025-10-17 | 2025-10-21 | D K Verma | 36.371 | 7.2742 | TA421 | 42/2 | Completed
2025-10-17 | 2025-10-22 | Khatun | 37.72 | 6.2867 | TA421 | 4/19 | Completed
2025-10-22 | 2025-10-25 | D K Verma | 36.371 | 9.0928 | TA421 | 41/1 | Completed
2025-10-23 | 2025-10-27 | Khatun | 36.37 | 7.274 | TA421 | 11/4 | Completed
2025-10-14 | 2025-10-27 | Praveen | 36.37 | 2.5979 | TA421 | 39/6 | Completed
2025-10-22 | 2025-10-30 | Subash | 33.38 | 3.7089 | TA421 | 4/1 | Completed
2025-10-28 | 2025-11-02 | Khatun | 36.37 | 6.0617 | TA421 | 11/7 | Completed
2025-10-26 | 2025-11-02 | D K Verma | 37.931 | 4.7414 | TA421 | 43/1 | Completed
2025-10-21 | 2025-11-02 | Hassan | 36.37 | 2.7977 | TA421 | 36/8 | Completed
2025-10-31 | 2025-11-05 | Subash | 31.99 | 5.3317 | TA421 | 4/13 | Completed
2025-11-04 | 2025-11-09 | Khatun | 61.15 | 10.1917 | TA421 | 8/3 | Completed
2025-11-06 | 2025-11-11 | Subash | 39.17 | 6.5283 | TA421 | 3/1 | Completed
2025-11-04 | 2025-11-11 | D K Verma | 64.89 | 8.1113 | TA421 | 43B/0 | Completed
2025-11-10 | 2025-11-14 | Khatun | 58.93 | 11.786 | TA421 | 8/4 | Completed
2025-11-11 | 2025-11-17 | D K Verma | 37.931 | 5.4187 | TA421 | 43A/5 | Completed
2025-11-11 | 2025-11-18 | Subash | 53.13 | 6.6413 | TA421 | 3/0 | Completed
2025-09-03 | 2025-09-22 | Sainik Traders | 59.5006 | 2.975 | TA504 | 11/0 | Completed
2025-07-21 | 2025-07-30 | Sainik Traders | 36.1598 | 3.616 | TA504 | 11/1 | Completed
2025-08-01 | 2025-08-13 | Sainik Traders | 36.1598 | 2.7815 | TA504 | 11/2 | Completed
2025-08-14 | 2025-08-31 | Sainik Traders | 37.9311 | 2.1073 | TA504 | 11/3 | Completed
2025-07-07 | 2025-07-21 | Sainik Traders | 36.1598 | 2.4107 | TA504 | 11/4 | Completed
2025-09-22 | 2025-10-08 | Sainik Traders | 59.5006 | 3.5 | TA504 | 12/0 | Completed
2025-06-16 | 2025-06-20 | Pankaj 2 | 34.7898 | 6.958 | TA504 | 12/1 | Completed
2025-06-11 | 2025-06-15 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 12/2 | Completed
2025-05-27 | 2025-06-03 | Pankaj 2 | 36.1598 | 4.52 | TA504 | 12/3 | Completed
2025-05-17 | 2025-05-26 | Pankaj 2 | 43.8044 | 4.3804 | TA504 | 12/4 | Completed
2025-06-04 | 2025-06-10 | Pankaj 2 | 43.8044 | 6.2578 | TA504 | 12/5 | Completed
2025-08-28 | 2025-09-25 | Karam Mahto | 36.1598 | 1.2469 | TA504 | 13/1 | Completed
2025-01-28 | 2025-02-01 | Pankaj 2 | 37.9311 | 7.5862 | TA504 | 13/5 | Completed
2025-02-02 | 2025-02-05 | Pankaj 2 | 37.9311 | 9.4828 | TA504 | 13/6 | Completed
2025-01-19 | 2025-01-23 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 14/2 | Completed
2025-01-24 | 2025-01-27 | Pankaj 2 | 36.1598 | 9.0399 | TA504 | 14/3 | Completed
2025-04-30 | 2025-05-07 | Pankaj 2 | 36.1598 | 4.52 | TA504 | 14/4 | Completed
2025-05-08 | 2025-05-16 | Pankaj 2 | 37.9311 | 4.2146 | TA504 | 14/5 | Completed
2025-02-06 | 2025-02-10 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 14/6 | Completed
2025-02-11 | 2025-02-15 | Pankaj 2 | 37.9311 | 7.5862 | TA504 | 14/7 | Completed
2025-02-16 | 2025-02-19 | Pankaj 2 | 37.9311 | 9.4828 | TA504 | 15/2 | Completed
2025-02-20 | 2025-02-23 | Pankaj 2 | 36.1598 | 9.0399 | TA504 | 15/3 | Completed
2025-03-01 | 2025-03-04 | Pankaj 2 | 37.9311 | 9.4828 | TA504 | 15/4 | Completed
2025-03-05 | 2025-03-08 | Pankaj 2 | 34.7898 | 8.6975 | TA504 | 15/5 | Completed
2025-02-24 | 2025-02-28 | Pankaj 2 | 37.9311 | 7.5862 | TA504 | 15/6 | Completed
2025-04-24 | 2025-04-29 | Pankaj 2 | 43.8044 | 7.3007 | TA504 | 15/7 | Completed
2025-03-23 | 2025-03-27 | Pankaj 2 | 43.8044 | 8.7609 | TA504 | 16/1 | Completed
2025-03-19 | 2025-03-22 | Pankaj 2 | 34.7898 | 8.6975 | TA504 | 16/2 | Completed
2025-09-21 | 2025-09-29 | Pinki Devi | 65.0226 | 7.2247 | TA504 | 16/3 | Completed
2025-03-09 | 2025-03-13 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 16/5 | Completed
2025-03-13 | 2025-03-18 | Pankaj 2 | 34.7898 | 5.7983 | TA504 | 16/6 | Completed
2025-08-25 | 2025-09-08 | Pinki Devi | 59.5006 | 3.9667 | TA504 | 17/0 | Completed
2025-03-28 | 2025-03-31 | Pankaj 2 | 37.9311 | 9.4828 | TA504 | 17/1 | Completed
2025-04-01 | 2025-04-05 | Pankaj 2 | 36.1598 | 7.232 | TA504 | 17/2 | Completed
2025-04-06 | 2025-04-12 | Pankaj 2 | 37.9311 | 5.4187 | TA504 | 17/3 | Completed
2025-04-13 | 2025-04-18 | Pankaj 2 | 45.697 | 7.6162 | TA504 | 17/5 | Completed
2025-04-19 | 2025-04-23 | Pankaj 2 | 37.9311 | 7.5862 | TA504 | 17/6 | Completed
2025-04-21 | 2025-04-28 | Pankaj | 45.697 | 5.7121 | TA504 | 17/7 | Completed
2025-04-09 | 2025-04-15 | Pankaj | 36.1598 | 5.1657 | TA504 | 17/8 | Completed
2025-04-16 | 2025-04-20 | Pankaj | 35.6018 | 7.1204 | TA504 | 17/9 | Completed
2025-09-09 | 2025-09-21 | Pinki Devi | 66.7757 | 5.1366 | TA504 | 18/0 | Completed
2025-04-05 | 2025-04-08 | Pankaj | 36.1598 | 9.0399 | TA504 | 18/2 | Completed
2025-03-22 | 2025-03-26 | Pankaj | 43.8044 | 8.7609 | TA504 | 18/3 | Completed
2025-03-31 | 2025-04-04 | Pankaj | 35.6018 | 7.1204 | TA504 | 18/4 | Completed
2025-03-27 | 2025-03-30 | Pankaj | 37.9311 | 9.4828 | TA504 | 18/5 | Completed
2025-03-01 | 2025-03-04 | Pankaj | 37.9311 | 9.4828 | TA504 | 18/6 | Completed
2025-03-18 | 2025-03-21 | Pankaj | 35.6018 | 8.9004 | TA504 | 18/7 | Completed
2025-03-05 | 2025-03-07 | Pankaj | 34.7898 | 11.5966 | TA504 | 18/8 | Completed
2025-05-17 | 2025-05-21 | Pankaj | 37.9311 | 7.5862 | TA504 | 19/1 | Completed
2025-03-12 | 2025-03-17 | Pankaj | 36.1598 | 6.0266 | TA504 | 19/3 | Completed
2025-09-30 | 2025-10-09 | Pinki Devi | 69.376 | 6.9376 | TA504 | 21/0 | Completed
2025-03-08 | 2025-03-11 | Pankaj | 36.1598 | 9.0399 | TA504 | 21/1 | Completed
2025-05-22 | 2025-05-26 | Pankaj | 37.9311 | 7.5862 | TA504 | 21/2 | Completed
2025-05-08 | 2025-05-16 | Pankaj | 37.9311 | 4.2146 | TA504 | 21/4 | Completed
2025-04-29 | 2025-05-07 | Pankaj | 37.9311 | 4.2146 | TA504 | 21/5 | Completed
2025-10-18 | 2025-11-02 | Ghyansham Mahto | 73.2445 | 4.5778 | TA504 | 22/0 | Completed
2025-02-03 | 2025-02-06 | Pankaj | 37.9311 | 9.4828 | TA504 | 22/1 | Completed
2025-02-07 | 2025-02-10 | Pankaj | 35.6018 | 8.9004 | TA504 | 22/2 | Completed
2025-01-30 | 2025-02-02 | Pankaj | 43.8044 | 10.9511 | TA504 | 22/3 | Completed
2025-01-22 | 2025-01-25 | Pankaj | 37.9311 | 9.4828 | TA504 | 22/4 | Completed
2025-01-26 | 2025-01-29 | Pankaj | 45.697 | 11.4243 | TA504 | 23/1 | Completed
2025-08-26 | 2025-09-10 | Ghyansham Mahto | 36.1598 | 2.26 | TA504 | 23/2 | Completed
2025-02-11 | 2025-02-14 | Pankaj | 43.8044 | 10.9511 | TA504 | 23/3 | Completed
2025-02-15 | 2025-02-18 | Pankaj | 35.6018 | 8.9004 | TA504 | 23/4 | Completed
2025-02-19 | 2025-02-22 | Pankaj | 37.9311 | 9.4828 | TA504 | 23/5 | Completed
2025-02-23 | 2025-02-25 | Pankaj | 34.7898 | 11.5966 | TA504 | 23/6 | Completed
2025-02-26 | 2025-02-28 | Pankaj | 34.7898 | 11.5966 | TA504 | 23/7 | Completed
2025-09-27 | 2025-10-16 | Ghyansham Mahto | 59.5006 | 2.975 | TA504 | 24/0 | Completed
2025-09-10 | 2025-09-26 | Ghyansham Mahto | 66.7757 | 3.928 | TA504 | 24/1 | Completed
2024-12-23 | 2024-12-27 | Pankaj | 36.1598 | 7.232 | TA504 | 25/3. | Completed
2024-12-28 | 2024-12-31 | Pankaj | 36.1598 | 9.0399 | TA504 | 25/4 | Completed
2025-01-02 | 2025-01-06 | Pankaj | 43.8044 | 8.7609 | TA504 | 26/1 | Completed
2025-01-14 | 2025-01-17 | Pankaj | 37.9311 | 9.4828 | TA504 | 26/3 | Completed
2025-10-17 | 2025-10-24 | Pinki Devi | 34.7898 | 4.3487 | TA504 | 26/4 | Completed
2025-01-10 | 2025-01-13 | Pankaj | 36.1598 | 9.0399 | TA504 | 26/5 | Completed
2025-01-07 | 2025-01-09 | Pankaj | 37.9311 | 12.6437 | TA504 | 26/6 | Completed
2025-01-18 | 2025-01-21 | Pankaj | 36.1598 | 9.0399 | TA504 | 26/8 | Completed
2025-10-10 | 2025-10-16 | Pinki Devi | 37.9311 | 5.4187 | TA504 | 27/1 | Completed
2025-09-18 | 2025-09-26 | Neha Const | 36.1598 | 4.0178 | TA504 | 29/2 | Completed
2025-10-19 | 2025-11-02 | Karam Mahto | 45.697 | 3.0465 | TA504 | 30/1 | Completed
2025-08-28 | 2025-09-17 | Neha Const | 37.9311 | 1.8062 | TA504 | 30/2 | Completed
2025-09-26 | 2025-10-09 | Karam Mahto | 37.9311 | 2.7094 | TA504 | 30/4 | Completed
2025-10-10 | 2025-10-18 | Karam Mahto | 36.1598 | 4.0178 | TA504 | 30/5 | Completed
2025-11-04 | 2025-11-11 | Karam Mahto | 36.1598 | 4.52 | TA504 | 26/10 | Completed
2025-11-03 | 2025-11-17 | Sainik Traders | 59.5006 | 3.9667 | TA504 | 13/0 | Completed
2025-11-03 | 2025-11-17 | Ghyansham Mahto | 73.2446 | 4.883 | TA504 | 19/0 | Completed
|  | Nan | 8617.0894 |  | TA505 |  | 179
2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-21 | 2025-01-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/1 | Completed
2025-01-24 | 2025-01-27 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/3 | Completed
2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-02-01 | 2025-02-04 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 101/5 | Completed
2025-02-05 | 2025-02-08 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/6 | Completed
2025-02-09 | 2025-02-12 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/7 | Completed
2025-02-13 | 2025-02-15 | Jwala Singh | 34.7898 | 11.5966 | TA505 | 101/8 | Completed
2025-02-17 | 2025-02-20 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/7 | Completed
2025-02-21 | 2025-02-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/5 | Completed
2025-02-25 | 2025-02-28 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/2 | Completed
2025-03-01 | 2025-03-04 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/1 | Completed
2025-03-05 | 2025-03-07 | Jwala Singh | 35.602 | 11.8673 | TA505 | 110/1 | Completed
2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-19 | 2025-03-22 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 110/2 | Completed
2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-29 | 2025-03-31 | Eagle Enterprises | 43.8044 | 14.6015 | TA505 | 113/5 | Completed
2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-08 | 2025-04-11 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/3 | Completed
2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-12 | 2025-04-15 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 108/2 | Completed
2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-15 | 2025-04-18 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/1 | Completed
2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-18 | 2025-04-21 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/1 | Completed
2025-04-22 | 2025-04-25 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/2 | Completed
2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-26 | 2025-04-29 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 105/1 | Completed
2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-14 | 2025-05-16 | Jwala Singh | 37.9311 | 12.6437 | TA505 | 152A/3 | Completed
2025-05-13 | 2025-05-16 | Jwala Singh 2 | 36.1598 | 9.0399 | TA505 | 127/1 | Completed
2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-23 | 2025-05-26 | Jwala Singh 2 | 34.79 | 8.6975 | TA505 | 126/2 | Completed
2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-05-28 | 2025-05-31 | Gokul Rajwanshi | 37.9311 | 9.4828 | TA505 | 155/5 | Completed
2025-05-27 | 2025-05-30 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 152A/4 | Completed
2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-07 | 2025-06-10 | Jwala Singh 2 | 43.8044 | 10.9511 | TA505 | 147A/2 | Completed
2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-27 | 2025-06-30 | Jwala Singh | 43.8044 | 10.9511 | TA505 | 150/4 | Completed
2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-09-26 | 2025-10-12 | Jagannaath Saw Mp | 55.451 | 3.2618 | TA505 | 160/0 | Completed
2025-09-30 | 2025-10-12 | Toshan Mahato | 36.1598 | 2.7815 | TA505 | 148/1 | Completed
2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-01 | 2025-10-26 | Jyoti Const | 124.95 | 4.8058 | TA505 | 112/0 | Completed
2025-10-01 | 2025-10-12 | Shila Devi | 81.828 | 6.819 | TA505 | 128/0 | Completed
2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-10-02 | 2025-10-10 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/2 | Completed
2025-10-08 | 2025-10-16 | Paramanand 1 | 35.602 | 3.9558 | TA505 | 160/1 | Completed
2025-10-09 | 2025-10-16 | Deglal Mahato Mp | 36.1598 | 4.52 | TA505 | 169/5 | Completed
2025-10-10 | 2025-10-18 | Jhemon Mahato 2 | 37.931 | 4.2146 | TA505 | 140/1 | Completed
2025-10-10 | 2025-10-15 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/3 | Completed
2025-10-01 | 2025-10-12 | Jwala Singh | 65.87 | 5.4892 | TA505 | 101/0 | Completed
2025-10-13 | 2025-10-26 | Jwala Singh | 70.74 | 5.0529 | TA505 | 102/0 | Completed
2025-10-13 | 2025-10-24 | Toshan Mahato | 55.451 | 4.6209 | TA505 | 147A/0 | Completed
2025-10-13 | 2025-10-18 | Jagannaath Saw Mp | 36.1598 | 6.0266 | TA505 | 158/2 | Completed
2025-10-05 | 2025-10-18 | Anil Kumar | 37.931 | 2.7094 | TA505 | 152A/5 | Completed
2025-10-05 | 2025-10-13 | Deglal Mahato | 77.077 | 8.5641 | TA505 | 116/0 | Completed
2025-10-14 | 2025-10-21 | Deglal Mahato | 65.028 | 8.1285 | TA505 | 121/0 | Completed
2025-10-16 | 2025-10-21 | Deglal Mahato Mp | 35.602 | 5.9337 | TA505 | 169/7 | Completed
2025-10-16 | 2025-10-25 | Pankaj Singh Mp | 55.451 | 5.5451 | TA505 | 167/0 | Completed
2025-10-16 | 2025-11-08 | Paramanand 1 | 62.116 | 2.5882 | TA505 | 161/0 | Completed
2025-10-19 | 2025-11-02 | Jagannaath Saw Mp | 59.501 | 3.9667 | TA505 | 159/0 | Completed
2025-10-19 | 2025-11-02 | Jhemon Mahato 2 | 57.96 | 3.864 | TA505 | 144A/3 | Completed
2025-10-22 | 2025-10-30 | Deglal Mahato Mp | 36.1598 | 4.0178 | TA505 | 169/2 | Completed
2025-10-22 | 2025-10-31 | Deglal Mahato | 67.262 | 6.7262 | TA505 | 114/0 | Completed
2025-10-25 | 2025-11-10 | Toshan Mahato | 65.028 | 3.8252 | TA505 | 148A/0 | Completed
2025-10-27 | 2025-11-11 | Jyoti Const | 37.931 | 2.3707 | TA505 | 149B/3 | Completed
2025-10-27 | 2025-11-05 | Jwala Singh | 36.1598 | 3.616 | TA505 | 103/4 | Completed
2025-10-26 | 2025-11-03 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/1 | Completed
2025-10-27 | 2025-11-24 | Crane Erc Team Mp | 36.1598 | 1.2469 | TA505 | 172/6 | Completed
2025-10-31 | 2025-11-06 | Deglal Mahato Mp | 35.602 | 5.086 | TA505 | 169/1 | Completed
2025-11-01 | 2025-11-09 | Deglal Mahato | 45.697 | 5.0774 | TA505 | 126/1 | Completed
2025-11-03 | 2025-11-10 | Jhemon Mahato 2 | 37.931 | 4.7414 | TA505 | 135/1 | Completed
2025-11-03 | 2025-11-07 | Jagannaath Saw Mp | 34.79 | 6.958 | TA505 | 165/6 | Completed
2025-11-04 | 2025-11-13 | Pankaj Singh Mp | 37.931 | 3.7931 | TA505 | 166/9 | Completed
2025-11-06 | 2025-11-18 | Jwala Singh | 62.444 | 4.8034 | TA505 | 109/0 | Completed
2025-11-07 | 2025-11-13 | Deglal Mahato Mp | 36.1598 | 5.1657 | TA505 | 170/8 | Completed
2025-11-08 | 2025-11-15 | Jagannaath Saw Mp | 62.444 | 7.8055 | TA505 | 166/0 | Completed
2025-11-10 | 2025-11-16 | Deglal Mahato | 37.931 | 5.4187 | TA505 | 126/3 | Completed
2025-11-09 |  | Paramanand 1 | 43.8044 |  | TA505 | 164/5 | In-Progress
2025-11-10 | 2025-11-23 | Prayag Shah Mp | 65.87 | 4.705 | TA505 | 174A/0 | Completed
2025-11-11 |  | Toshan Mahato | 124.95 |  | TA505 | 145/0 | In-Progress
2025-11-11 | 2025-11-22 | Jhemon Mahato 2 | 37.931 | 3.1609 | TA505 | 136/5 | Completed
2025-11-12 |  | Jyoti Const | 43.8044 |  | TA505 | 149B/2 | In-Progress
2025-11-14 | 2025-11-18 | Pankaj Singh Mp | 36.1598 | 7.232 | TA505 | 166/8 | Completed
2025-11-14 | 2025-11-20 | Deglal Mahato Mp | 36.1598 | 5.1657 | TA505 | 170/7 | Completed
2025-11-12 | 2025-11-22 | Shila Devi | 36.1598 | 3.2873 | TA505 | 129A/2 | Completed
2025-11-16 | 2025-11-24 | Jagannaath Saw Mp | 65.028 | 7.2253 | TA505 | 165/0 | Completed
2025-11-17 | 2025-11-24 | Deglal Mahato | 37.931 | 4.7414 | TA505 | 114/4 | Completed
2025-10-27 | 2025-11-17 | Crane Erc Team Mp | 34.79 | 1.5814 | TA505 | 173/1 | Completed
2025-11-18 |  | Crane Erc Team Mp | 36.1598 |  | TA505 | 172/3 | In-Progress
2025-11-19 |  | Jwala Singh | 73.245 |  | TA505 | 100/0 | In-Progress
2025-11-19 | 2025-11-24 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 166/7 | Completed
2025-11-21 |  | Deglal Mahato Mp | 36.1598 |  | TA505 | 170/1 | In-Progress
2025-11-23 |  | Jhemon Mahato 2 | 37.931 |  | TA505 | 136/2 | In-Progress
2025-11-23 |  | Shila Devi | 35.602 |  | TA505 | 130/2 | In-Progress
2025-11-24 |  | Prayag Shah Mp | 36.1598 |  | TA505 | 174A/2 | In-Progress
2025-11-25 |  | Pankaj Singh Mp | 34.79 |  | TA505 | 166/6 | In-Progress
2025-11-25 |  | Jagannaath Saw Mp | 43.8044 |  | TA505 | 164/8 | In-Progress
2025-11-25 |  | Deglal Mahato | 37.931 |  | TA505 | 103/5 | In-Progress
2025-08-27 | 2025-09-01 | Tejal | 16.9667 | 2.8278 | TA506 | 137/2 | Completed
2025-09-01 | 2025-09-05 | Shri Karni Construction | 16.9667 | 3.3933 | TA506 | 13/2 | Completed
2025-08-27 | 2025-09-05 | Shri Karni Construction | 37.2057 | 3.7206 | TA506 | 33/0 | Completed
2025-08-31 | 2025-09-04 | Pankaj 1 | 16.9667 | 3.3933 | TA506 | 183/4 | Completed
2025-08-27 | 2025-09-05 | Shri Karni Construction | 34.1664 | 3.4166 | TA506 | 25/0 | Completed
2025-09-02 | 2025-09-12 | Govind Mahto | 37.2057 | 3.3823 | TA506 | 223/0 | Completed
2025-09-07 | 2025-09-11 | Vinod | 18.1188 | 3.6238 | TA506 | 163/2 | Completed
2025-09-01 | 2025-09-10 | Mohan Mahto | 37.2057 | 3.7206 | TA506 | 68/0 | Completed
2025-09-09 | 2025-09-17 | Jay Prakash | 34.1664 | 3.7963 | TA506 | 76A/1 | Completed
2025-09-03 | 2025-09-12 | Tejal | 31.8647 | 3.1865 | TA506 | 141/0 | Completed
2025-09-04 | 2025-09-08 | Shri Karni Construction | 21.0969 | 4.2194 | TA506 | 18/7 | Completed
2025-09-02 | 2025-09-12 | Shri Karni Construction | 42.6134 | 3.8739 | TA506 | 22/0 | Completed
2025-09-07 | 2025-09-11 | Shri Karni Construction | 18.1188 | 3.6238 | TA506 | 13/3 | Completed
2025-09-06 | 2025-09-11 | Shri Karni Construction | 18.1188 | 3.0198 | TA506 | 2/4 | Completed
2025-09-10 | 2025-09-15 | Shri Karni Construction | 18.1188 | 3.0198 | TA506 | 5/3 | Completed
2025-09-06 | 2025-09-15 | Pankaj 2 | 38.1379 | 3.8138 | TA506 | 218/0 | Completed
2025-09-06 | 2025-09-11 | Fatima 1 | 27.0921 | 4.5154 | TA506 | 6/0 | Completed
2025-09-02 | 2025-09-08 | Radhika Enterprises | 27.0921 | 3.8703 | TA506 | 2A/0 | Completed
2025-08-31 | 2025-09-09 | Shri Karni Construction | 37.2057 | 3.7206 | TA506 | 12/0 | Completed
2025-09-04 | 2025-09-11 | Pankaj 1 | 42.6134 | 5.3267 | TA506 | 184/0 | Completed
2025-09-09 | 2025-09-13 | Shri Karni Construction | 18.1188 | 3.6238 | TA506 | 18/8 | Completed
2025-09-16 | 2025-09-20 | Shri Karni Construction | 16.9667 | 3.3933 | TA506 | 12/3 | Completed
2025-09-16 | 2025-09-20 | Fatima | 21.0969 | 4.2194 | TA506 | 10/1 | Completed
2025-09-11 | 2025-09-15 | Shri Karni Construction | 16.9667 | 3.3933 | TA506 | 11/1 | Completed
2025-09-08 | 2025-09-20 | Mohan Mahto | 48.342 | 3.7186 | TA506 | 27/0 | Completed
2025-09-14 | 2025-09-18 | Shri Karni Construction | 21.0969 | 4.2194 | TA506 | 2/3 | Completed
2025-09-15 | 2025-09-18 | Shri Karni Construction | 16.9667 | 4.2417 | TA506 | 26/1 | Completed
2025-09-13 | 2025-09-17 | Mohan Mahto | 22.4884 | 4.4977 | TA506 | 72/2 | Completed
2025-09-18 | 2025-09-22 | A B Const Birendra Panday | 16.9667 | 3.3933 | TA506 | 100/2 | Completed
2025-09-12 | 2025-09-18 | Tejal | 16.9667 | 2.4238 | TA506 | 141/1 | Completed
2025-09-14 | 2025-09-25 | Vinod | 42.6134 | 3.5511 | TA506 | 166/0 | Completed
2025-09-10 | 2025-09-24 | Pankaj 1 | 39.5967 | 2.6398 | TA506 | 186/0 | Completed
2025-09-10 | 2025-09-14 | Horil | 27.0921 | 5.4184 | TA506 | 191/0 | Completed
2025-09-16 | 2025-09-18 | Khemlal | 18.1188 | 6.0396 | TA506 | 220/1 | Completed
2025-09-16 | 2025-09-21 | Govind Mahto | 22.4884 | 3.7481 | TA506 | 220/4 | Completed
2025-09-14 | 2025-09-19 | Horil | 31.8647 | 5.3108 | TA506 | 194/0 | Completed
2025-09-14 | 2025-09-27 | Pankaj 2 | 29.7779 | 2.127 | TA506 | 214/0 | Completed
2025-09-19 | 2025-09-24 | Shri Karni Construction | 21.0969 | 3.5162 | TA506 | 2/2 | Completed
2025-09-15 | 2025-09-20 | Shri Karni Construction | 21.0969 | 3.5162 | TA506 | 6/1 | Completed
2025-09-26 | 2025-09-30 | Shri Karni Construction | 21.0969 | 4.2194 | TA506 | 10/2 | Completed
2025-09-15 | 2025-09-21 | Shri Karni Construction | 27.0921 | 3.8703 | TA506 | 19/0 | Completed
2025-09-18 | 2025-09-22 | Shri Karni Construction | 18.1188 | 3.6238 | TA506 | 60/2 | Completed
2025-09-22 | 2025-09-25 | Shri Karni Construction | 18.1188 | 4.5297 | TA506 | 11/2 | Completed
2025-09-20 | 2025-09-25 | Jay Prakash | 35.8452 | 5.9742 | TA506 | 79/0 | Completed
2025-09-17 | 2025-09-22 | Khemlal | 21.0969 | 3.5162 | TA506 | 212/5 | Completed
2025-09-23 | 2025-09-26 | Shri Karni Construction | 21.0969 | 5.2742 | TA506 | 35A/1 | Completed
2025-09-27 | 2025-09-29 | Tejal | 16.9667 | 5.6556 | TA506 | 142/1 | Completed
2025-09-20 | 2025-09-23 | Horil | 21.0969 | 5.2742 | TA506 | 187A/1 | Completed
2025-09-18 | 2025-09-21 | Mohan Mahto | 18.1188 | 4.5297 | TA506 | 66/1 | Completed
2025-09-22 | 2025-09-26 | Shri Karni Construction | 22.4884 | 4.4977 | TA506 | 6/2 | Completed
2025-09-26 | 2025-09-29 | Shri Karni Construction | 21.0969 | 5.2742 | TA506 | 2/1 | Completed
2025-09-28 | 2025-09-30 | Shri Karni Construction | 15.8578 | 5.2859 | TA506 | 2/5 | Completed
2025-09-24 | 2025-09-27 | Shri Karni Construction | 18.1188 | 4.5297 | TA506 | 5/10 | Completed
2025-09-27 | 2025-09-30 | Shri Karni Construction | 22.4884 | 5.6221 | TA506 | 5/9 | Completed
2025-09-24 | 2025-09-30 | Shri Karni Construction | 36.5854 | 5.2265 | TA506 | 11/3 | Completed
2025-09-15 | 2025-09-18 | Shri Karni Construction | 22.4884 | 5.6221 | TA506 | 19/1 | Completed
2025-09-24 | 2025-09-26 | Shri Karni Construction | 15.8578 | 5.2859 | TA506 | 18/5 | Completed
2025-09-25 | 2025-09-28 | Shri Karni Construction | 21.0969 | 5.2742 | TA506 | 18/6 | Completed
2025-09-24 | 2025-09-26 | Shri Karni Construction | 16.4524 | 5.4841 | TA506 | 60/3 | Completed
2025-09-27 | 2025-09-30 | Shri Karni Construction | 18.1188 | 4.5297 | TA506 | 61/1 | Completed
2025-09-25 | 2025-09-30 | Jay Prakash | 29.7779 | 4.963 | TA506 | 66/0 | Completed
2025-09-24 | 2025-09-27 | Horil | 21.0969 | 5.2742 | TA506 | 187/2 | Completed
2025-09-27 | 2025-09-30 | Horil | 21.0969 | 5.2742 | TA506 | 194/2 | Completed
2025-09-27 | 2025-09-30 | Pankaj 1 | 18.1188 | 4.5297 | TA506 | 210/10 | Completed
2025-09-23 | 2025-09-27 | Khemlal | 22.4884 | 4.4977 | TA506 | 212/4 | Completed
2025-09-27 | 2025-09-30 | Khemlal | 21.0969 | 5.2742 | TA506 | 212/3 | Completed
2025-09-24 | 2025-09-27 | Govind Mahto | 16.4524 | 4.1131 | TA506 | 220/2 | Completed
2025-09-28 | 2025-09-30 | Shri Karni Construction | 15.8578 | 5.2859 | TA506 | 19/2 | Completed
2025-09-23 | 2025-10-01 | Karni Const 5 | 21.0969 | 2.3441 | TA506 | 10/2 | Completed
2025-09-27 | 2025-10-01 | Karni Const 6 | 18.1188 | 3.6238 | TA506 | 61/1 | Completed
2025-09-25 | 2025-10-02 | Karni Const 3 | 36.5854 | 4.5732 | TA506 | 11/3 | Completed
2025-09-22 | 2025-10-02 | Jai Prakash Mahto | 29.7779 | 2.7071 | TA506 | 66/0 | Completed
2025-10-01 | 2025-10-03 | Karni Const 1 | 15.8578 | 5.2859 | TA506 | 2/5 | Completed
2025-10-01 | 2025-10-03 | Karni Const 2 | 18.1188 | 6.0396 | TA506 | 5/9 | Completed
2025-09-30 | 2025-10-03 | Karni Const 4 | 15.8578 | 3.9644 | TA506 | 19/2 | Completed
2025-09-26 | 2025-10-03 | Ab Const | 48.342 | 6.0427 | TA506 | 101/0 | Completed
2025-09-29 | 2025-10-03 | Tejal Const | 18.1188 | 3.6238 | TA506 | 140/2 | Completed
2025-09-29 | 2025-10-03 | Horil Mahto | 21.0969 | 4.2194 | TA506 | 194/2 | Completed
2025-09-27 | 2025-10-03 | Pankaj Const | 16.9667 | 2.4238 | TA506 | 206/1 | Completed
2025-09-28 | 2025-10-03 | Govind Mahto | 18.1188 | 3.0198 | TA506 | 220/1 | Completed
2025-10-01 | 2025-10-06 | Karni Const 6 | 16.4524 | 2.7421 | TA506 | 51A/2 | Completed
2025-10-04 | 2025-10-07 | Karni Const 1 | 16.9667 | 4.2417 | TA506 | 2/6 | Completed
2025-10-04 | 2025-10-07 | Karni Const 2 | 18.1188 | 4.5297 | TA506 | 5/11 | Completed
2025-10-02 | 2025-10-08 | Karni Const 4 | 21.0969 | 3.0138 | TA506 | 19/3 | Completed
2025-10-02 | 2025-10-09 | Jai Prakash Mahto | 37.2057 | 4.6507 | TA506 | 67/0 | Completed
2025-09-28 | 2025-10-09 | Binod Mahto | 35.8452 | 2.9871 | TA506 | 164/0 | Completed
2025-10-05 | 2025-10-10 | Karni Const 3 | 22.4884 | 3.7481 | TA506 | 13/1 | Completed
2025-10-07 | 2025-10-10 | Karni Const 6 | 16.4524 | 4.1131 | TA506 | 51A/1 | Completed
2025-10-05 | 2025-10-10 | Khemlal Mahto | 18.1188 | 3.0198 | TA506 | 213/5 | Completed
2025-10-04 | 2025-10-10 | Govind Mahto | 38.1379 | 5.4483 | TA506 | 224/0 | Completed
2025-10-07 | 2025-10-12 | Karni Const 4 | 15.8578 | 2.643 | TA506 | 19/4 | Completed
2025-10-02 | 2025-10-11 | Horil Mahto | 37.2057 | 3.7206 | TA506 | 187/0 | Completed
2025-10-03 | 2025-10-11 | Pankaj Const | 29.7779 | 3.3087 | TA506 | 206/0 | Completed
2025-10-10 | 2025-10-14 | Karni Const 1 | 15.8578 | 3.1716 | TA506 | 2/8 | Completed
2025-10-10 | 2025-10-14 | Karni Const 3 | 15.8578 | 3.1716 | TA506 | 12/5 | Completed
2025-10-11 | 2025-10-14 | Karni Const 6 | 16.4524 | 4.1131 | TA506 | 51C/2 | Completed
2025-10-08 | 2025-10-14 | Tejal Const | 29.7779 | 4.254 | TA506 | 142/0 | Completed
2025-10-09 | 2025-10-14 | Horil Mahto | 22.4884 | 3.7481 | TA506 | 193/2 | Completed
2025-10-08 | 2025-10-15 | Karni Const 4 | 21.0969 | 2.6371 | TA506 | 19/5 | Completed
2025-10-10 | 2025-10-15 | Karni Const 5 | 27.0921 | 4.5154 | TA506 | 13/0 | Completed
2025-10-11 | 2025-10-15 | Pankaj Const | 21.0969 | 4.2194 | TA506 | 205/1 | Completed
2025-10-12 | 2025-10-16 | Karni Const 1 | 15.8578 | 3.1716 | TA506 | 2/7 | Completed
2025-10-10 | 2025-10-16 | Jai Prakash Mahto | 34.17 | 4.8814 | TA506 | 65A/0 | Completed
2025-10-11 | 2025-10-16 | Pankaj Const | 36.85 | 6.1417 | TA506 | 213/0 | Completed
2025-10-12 | 2025-10-17 | Karni Const 2 | 48.342 | 8.057 | TA506 | 9/0 | Completed
2025-10-14 | 2025-10-17 | Karni Const 3 | 16.9667 | 4.2417 | TA506 | 12/6 | Completed
2025-10-13 | 2025-10-17 | Govind Mahto | 22.4884 | 4.4977 | TA506 | 220/7 | Completed
2025-10-16 | 2025-10-18 | Gulab Mahto | 18.1188 | 6.0396 | TA506 | 1/1 | Completed
2025-10-19 | 2025-10-21 | Gulab Mahto | 18.1188 | 6.0396 | TA506 | 1/2 | Completed
2025-10-18 | 2025-10-21 | Karni Const 3 | 16.9667 | 4.2417 | TA506 | 12/7 | Completed
2025-10-16 | 2025-10-21 | Karni Const 5 | 27.0921 | 4.5154 | TA506 | 51C/0 | Completed
2025-10-17 | 2025-10-22 | Khemlal Mahto | 22.4884 | 3.7481 | TA506 | 211/7 | Completed
2025-10-19 | 2025-10-22 | Govind Mahto | 21.0969 | 5.2742 | TA506 | 220/6 | Completed
2025-10-18 | 2025-10-24 | Horil Mahto | 18.1188 | 2.5884 | TA506 | 193/1 | Completed
2025-10-21 | 2025-10-24 | Horil Mahto | 18.1188 | 4.5297 | TA506 | 205/2 | Completed
2025-10-18 | 2025-10-24 | Karni Const 4 | 46.4686 | 6.6384 | TA506 | 42/0 | Completed
2025-10-13 | 2025-10-20 | Horil Mahto | 31.8647 | 3.9831 | TA506 | 205/0 | Completed
2025-10-08 | 2025-10-12 | Horil Mahto | 18.1188 | 3.6238 | TA506 | 202/2 | Completed
2025-10-22 | 2025-10-25 | Gulab Mahto | 16.9667 | 4.2417 | TA506 | 1/3 | Completed
2025-10-19 | 2025-10-26 | Ab Const | 21.0969 | 2.6371 | TA506 | 101/1 | Completed
2025-10-20 | 2025-10-28 | Karni Const 2 | 48.342 | 5.3713 | TA506 | 10/0 | Completed
2025-10-19 | 2025-10-28 | Karni Const 5 | 36.5854 | 3.6585 | TA506 | 53/0 | Completed
2025-10-20 | 2025-10-27 | Jai Prakash Mahto | 53.1226 | 6.6403 | TA506 | 65/0 | Completed
2025-10-26 | 2025-10-29 | Gulab Mahto | 18.1188 | 4.5297 | TA506 | 1/7 | Completed
2025-10-24 | 2025-10-29 | Prem Kumar | 39.5967 | 6.5994 | TA506 | 60/0 | Completed
2025-10-28 | 2025-10-31 | Gulab Mahto | 18.1188 | 4.5297 | TA506 | 1/6 | Completed
2025-10-26 | 2025-10-31 | Karni Const 3 | 39.6224 | 6.6037 | TA506 | 14/0 | Completed
2025-10-27 | 2025-10-31 | Ab Const | 17.6337 | 3.5267 | TA506 | 97/1 | Completed
2025-10-27 | 2025-10-31 | Binod Mahto | 22.4884 | 4.4977 | TA506 | 167/1 | Completed
2025-10-26 | 2025-10-30 | Jai Prakash Mahto | 22.4884 | 4.4977 | TA506 | 64A/3 | Completed
2025-10-28 | 2025-11-01 | Karni Const 2 | 17.6337 | 3.5267 | TA506 | 12/2 | Completed
2025-10-30 | 2025-11-01 | Karni Const 4 | 16.9667 | 5.6556 | TA506 | 42/2 | Completed
2025-10-29 | 2025-11-01 | Karni Const 5 | 16.4524 | 4.1131 | TA506 | 52/1 | Completed
2025-10-29 | 2025-11-01 | Jai Prakash Mahto | 29.7779 | 7.4445 | TA506 | 65A/3 | Completed
2025-10-29 | 2025-11-01 | Govind Mahto | 16.4524 | 4.1131 | TA506 | 220/5 | Completed
2025-10-30 | 2025-11-02 | Gulab Mahto | 17.6337 | 4.4084 | TA506 | 1/8 | Completed
2025-10-29 | 2025-11-02 | Horil Mahto | 18.1188 | 3.6238 | TA506 | 197/2 | Completed
2025-10-29 | 2025-11-03 | Binod Mahto | 38.1379 | 6.3563 | TA506 | 167A/0 | Completed
2025-10-31 | 2025-11-03 | Govind Mahto | 18.1188 | 4.5297 | TA506 | 220/8 | Completed
2025-11-01 | 2025-11-04 | Karni Const 1 | 15.8578 | 3.9644 | TA506 | 12/8 | Completed
2025-11-01 | 2025-11-05 | Gulab Mahto | 17.6337 | 3.5267 | TA506 | 1/9 | Completed
2025-11-02 | 2025-11-05 | Jai Prakash Mahto | 16.9667 | 4.2417 | TA506 | 64A/2 | Completed
2025-11-02 | 2025-11-06 | Horil Mahto | 31.8647 | 6.3729 | TA506 | 95/0 | Completed
2025-11-02 | 2025-11-06 | Tejal Mahto | 39.6224 | 7.9245 | TA506 | 110/0 | Completed
2025-11-05 | 2025-11-07 | Gulab Mahto | 16.9667 | 5.6556 | TA506 | 1/10 | Completed
2025-11-04 | 2025-11-08 | Karni Const 3 | 38.1379 | 7.6276 | TA506 | 15/0 | Completed
2025-11-04 | 2025-11-09 | Jai Prakash Mahto | 21.0969 | 3.5162 | TA506 | 64A/1 | Completed
2025-11-02 | 2025-11-09 | Khemlal Mahto | 36.5854 | 4.5732 | TA506 | 76F/0 | Completed
2025-11-05 | 2025-11-08 | Ab Const | 22.4884 | 5.6221 | TA506 | 94/1 | Completed
2025-11-03 | 2025-11-10 | Karni Const 2 | 48.342 | 6.0427 | TA506 | 28/0 | Completed
2025-11-07 | 2025-11-11 | Gulab Mahto | 27.0921 | 5.4184 | TA506 | 2/0 | Completed
2025-11-08 | 2025-11-11 | Karni Const 1 | 17.6337 | 4.4084 | TA506 | 34/2 | Completed
2025-11-06 | 2025-11-11 | Govind Mahto | 36.5854 | 6.0976 | TA506 | 221/0 | Completed
2025-11-05 | 2025-11-12 | Karni Const 4 | 48.342 | 6.0427 | TA506 | 37/0 | Completed
2025-11-07 | 2025-11-12 | Horil Mahto | 36.5854 | 6.0976 | TA506 | 95A/0 | Completed
2025-11-10 | 2025-11-13 | Karni Const 3 | 18.1188 | 4.5297 | TA506 | 13/5 | Completed
2025-11-09 | 2025-11-13 | Zainab Fatima | 34.17 | 6.834 | TA506 | 16/0 | Completed
2025-11-07 | 2025-11-13 | Karni Const 5 | 39.6224 | 5.6603 | TA506 | 55/0 | Completed
2025-11-09 | 2025-11-13 | Ab Const | 18.1188 | 3.6238 | TA506 | 95/1 | Completed
2025-11-10 | 2025-11-15 | Khemlal Mahto | 31.8647 | 5.3108 | TA506 | 76G/0 | Completed
2025-11-12 | 2025-11-15 | Horil Mahto | 22.4884 | 5.6221 | TA506 | 94/2 | Completed
2025-11-10 | 2025-11-16 | Prem Kumar | 53.1226 | 7.5889 | TA506 | 62/0 | Completed
2025-11-12 | 2025-11-17 | Tejal Mahto | 29.7779 | 4.963 | TA506 | 111/0 | Completed
2025-11-10 | 2025-11-17 | Binod Mahto | 53.1226 | 6.6403 | TA506 | 139/0 | Completed
2025-11-15 | 2025-11-18 | Karni Const 4 | 16.9667 | 4.2417 | TA506 | 44A/2 | Completed
2025-11-13 | 2025-11-18 | Jai Prakash Mahto | 39.5967 | 6.5994 | TA506 | 64/0 | Completed
2025-11-16 | 2025-11-19 | Karni Const 2 | 21.0969 | 5.2742 | TA506 | 36/2 | Completed
2025-11-14 | 2025-11-19 | Karni Const 1 | 39.6224 | 6.6037 | TA506 | 78/0 | Completed
2025-11-15 | 2025-11-19 | Horil Mahto | 22.4884 | 4.4977 | TA506 | 94/3 | Completed
2025-11-16 | 2025-11-19 | Ab Const | 18.1188 | 4.5297 | TA506 | 107/1 | Completed
2025-11-18 | 2025-11-20 | Khemlal Mahto | 18.1188 | 6.0396 | TA506 | 76G/1 | Completed
2025-11-17 | 2025-11-22 | Karni Const 6 | 36.5854 | 6.0976 | TA506 | 56/0 | Completed
2025-11-19 | 2025-11-22 | Jai Prakash Mahto | 15.8578 | 3.9644 | TA506 | 64/1 | Completed
2025-11-19 | 2025-11-22 | Pankaj | 21.0969 | 5.2742 | TA506 | 211/4 | Completed
2025-11-20 | 2025-11-23 | Karni Const 1 | 16.9667 | 4.2417 | TA506 | 17/1 | Completed
2025-11-18 | 2025-11-23 | Karni Const 3 | 35.8452 | 5.9742 | TA506 | 26/0 | Completed
2025-11-19 | 2025-11-23 | Govind Mahto | 21.0969 | 4.2194 | TA506 | 210/9 | Completed
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
|  | Nan |  |  | TA506
2025-08-22 | 2025-09-03 | Devi Const I | 36.15 | 2.7808 | TA509 | 16/4 | COMPLETED
2025-08-22 | 2025-09-15 | Deonath Mahato | 36.15 | 1.446 | TA509 | 13/2 | COMPLETED
2025-08-25 | 2025-09-08 | Jawala Singh | 36.15 | 2.41 | TA509 | 8/5 | COMPLETED
2025-08-25 | 2025-09-18 | Modina India | 36.15 | 1.446 | TA509 | 12/6 | COMPLETED
2025-09-02 | 2025-09-23 | Om Construction | 37.93 | 1.7241 | TA509 | 12/1 | COMPLETED
2025-09-02 | 2025-09-12 | Hemlal Mahato I Anita Devi | 37.93 | 3.4482 | TA509 | 15/2 | COMPLETED
2025-09-07 | 2025-09-14 | Devi Const I | 34.79 | 4.3487 | TA509 | 20/1 | COMPLETED
2025-09-07 | 2025-09-12 | Devi Const Ii | 36.15 | 6.025 | TA509 | 16/1 | COMPLETED
| 2025-09-14 | Jawala Singh | 36.15 |  | TA509 | 8/6 | COMPLETED
2025-09-13 | 2025-09-27 | Deonath Mahato | 34.79 | 2.3193 | TA509 | 13/4 | COMPLETED
2025-09-01 | 2025-09-19 | Hemlal Mahato I Anita Devi | 34.79 | 1.8311 | TA509 | 15/5 | COMPLETED
2025-09-13 | 2025-09-19 | Devi Const I | 34.79 | 4.97 | TA509 | 16/8 | COMPLETED
2025-09-14 | 2025-09-20 | Jawala Singh | 36.15 | 5.1643 | TA509 | 8/7 | COMPLETED
2025-09-15 | 2025-09-23 | Devi Const Ii | 43.8 | 4.8667 | TA509 | 22/1 | COMPLETED
2025-09-16 | 2025-09-24 | Om Construction | 36.15 | 4.0167 | TA509 | 14/1 | COMPLETED
2025-09-19 | 2025-09-25 | Hemlal Mahato Ii Anita Devi | 36.15 | 5.1643 | TA509 | 16/9 | COMPLETED
2025-09-20 | 2025-09-26 | Devi Const I | 37.93 | 5.4186 | TA509 | 9/1 | COMPLETED
2025-09-23 | 2025-09-29 | Jawala Singh | 34.79 | 4.97 | TA509 | 20/2 | COMPLETED
2025-09-24 | 2025-09-30 | Devi Const Ii | 36.15 | 5.1643 | TA509 | 14/2 | COMPLETED
2025-10-01 | 2025-10-06 | Hemlal Mahato I Anita Devi | 36.15 | 6.025 | TA509 | 16/7 | COMPLETED
2025-09-16 | 2025-10-04 | Devi Const I | 34.79 | 1.8311 | TA509 | 12/2 | COMPLETED
2025-09-27 | 2025-10-02 | Jawala Singh | 36.15 | 6.025 | TA509 | 10/1 | COMPLETED
2025-10-01 | 2025-10-13 | Deonath Mahato | 35.602 | 2.7386 | TA509 | 13/1 | COMPLETED
2025-09-25 | 2025-10-01 | Devi Const I | 43.8 | 6.2571 | TA509 | 16/11 | COMPLETED
2025-10-01 | 2025-10-06 | Devi Const Ii | 37.93 | 6.3217 | TA509 | 24/6 | COMPLETED
2025-10-05 | 2025-10-16 | Om Construction | 34.79 | 2.8992 | TA509 | 14/3 | COMPLETED
2025-10-07 | 2025-10-11 | Devi Const | 36.15 | 7.23 | TA509 | 24/7 | COMPLETED
2025-10-12 | 2025-10-16 | Devi Const | 36.15 | 7.23 | TA509 | 8/10 | COMPLETED
2025-10-16 | 2025-10-22 | Devi Const | 34.79 | 4.97 | TA509 | 8/9 | COMPLETED
2025-10-22 | 2025-10-25 | Devi Const | 37.93 | 9.4825 | TA509 | 8/8 | COMPLETED
2025-10-26 | 2025-02-11 | Devi Const | 36.15 |  | TA509 | 9/2 | COMPLETED
2025-11-03 | 2025-11-07 | Devi Const | 37.93 | 7.586 | TA509 | 8/4 | COMPLETED
2025-11-07 | 2025-11-11 | Devi Const | 34.79 | 6.958 | TA509 | 10/2 | COMPLETED
2025-11-11 | 2025-11-16 | Devi Const | 34.79 | 5.7983 | TA509 | 12/3 | COMPLETED
|  | Nan |  |  | TB408
|  | Nan |  |  | TB408
2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TB408 | 60/7
2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 59/13
2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TB408 | 63/6
2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/5
2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TB408 | 59/14
2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/8
2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TB408 | 63/7
2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/6
2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TB408 | 59/12
2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TB408 | 63/8
2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/10
2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TB408 | 62/5
2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/7
2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 59/10
2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TB408 | 64/1
2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TB408 | 60/11
2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 62/4
2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 59/9
2024-02-26 | 2024-02-28 | Sobha Devi | 37.5044 | 12.5015 | TB408 | 62/3
2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TB408 | 59/8
2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/4
2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TB408 | 60/6
2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 62/2
2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/5
2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/2
2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 62/7
2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TB408 | 59/16
2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/4
2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TB408 | 62/8
2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 62/9
2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 65/3
2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 60/5
2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 62/10
2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 65/5
2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 61/6
2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TB408 | 60/4
2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/6
2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/6
2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 61/7
2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/7
2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TB408 | 60/3
2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/9
2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/8
2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 65/11
2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TB408 | 60/2
2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TB408 | 63/5
2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/9
2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 67/1
2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 61/0
2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TB408 | 63/4
2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 67/2
2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TB408 | 63/3
2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 64/10
2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/2
2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/2
2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TB408 | 63/2
2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TB408 | 60/1
2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/3
2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 65/0
2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TB408 | 63/1
2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TB408 | 61/1
2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/1
2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TB408 | 62/11
2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TB408 | 64/0
2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 60/9
2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/3
2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TB408 | 63/0
2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TB408 | 61/4
2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TB408 | 61/10
2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 61/5
2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TB408 | 61/9
2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TB408 | 61/8
2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TB408 | 62/1
2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TB408 | 62/6
2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TB408 | 57/6
2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 57/5
2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TB408 | 10/18
2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TB408 | 10/3
2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 10/17
2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TB408 | 62/0
2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TB408 | 16/3
2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TB408 | 10/19
2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TB408 | 50/10
2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/2
2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TB408 | 10/20
2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 15/1
2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TB408 | 51/1
2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/4
2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TB408 | 10/6
2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/6
2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 57/7
2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TB408 | 16/4
2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 14A/1
2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TB408 | 51/2
2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TB408 | 10/14
2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TB408 | 11A/2
2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 50/0
2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 52/7
2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TB408 | 10/9
2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/1
2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TB408 | 10/21
2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TB408 | 17/1
2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TB408 | 50/1
2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TB408 | 50/8
2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TB408 | 10/4
2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TB408 | 50/3
2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TB408 | 17/2
2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/8
2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TB408 | 73/2
2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TB408 | 10/8
2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/2
2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 64/11
2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TB408 | 16/2
2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TB408 | 19/0
2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TB408 | 59/11
2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TB408 | 16/0
2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TB408 | 17/3
2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 73/1
2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/4
2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TB408 | 55/6
2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TB408 | 59/3
2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 50/7
2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TB408 | 10/11
2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TB408 | 16/5
2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TB408 | 16/1
2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TB408 | 59/4
2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/6
2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TB408 | 55/5
2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/9
2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TB408 | 17/0
2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/7
2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 73/8
2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TB408 | 11/5
2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TB408 | 13/2
2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TB408 | 43/9
2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/6
2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TB408 | 73/6
2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 49/4
2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TB408 | 43/8
2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 49/5
2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TB408 | 17/5
2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/9
2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 49/2
2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TB408 | 72/3
2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TB408 | 59/1
2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TB408 | 52/9
2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 49/3
2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TB408 | 11A/7
2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/3
2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/1
2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TB408 | 10/12
2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/3
2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TB408 | 11A/6
2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/8
2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TB408 | 11A/5
2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/7
2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 73/0
2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TB408 | 53/8
2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TB408 | 74/0
2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/4
2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 43/1
2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TB408 | 43/7
2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TB408 | 53/7
2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/5
2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TB408 | 73/7
2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 72/0
2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TB408 | 43/6
2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 53/6
2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 72/1
2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 65/10
2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 72/2
2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TB408 | 51/0
2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TB408 | 1A/1
2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TB408 | 71/8
2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TB408 | 52/0
2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TB408 | 49/0
2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/7
2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TB408 | 1A/2
2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TB408 | 71/6
2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TB408 | 50/5
2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/5
2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TB408 | 1A/3
2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/4
2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 53/5
2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TB408 | 71/3
2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/2
2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TB408 | 70/3
2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 53/4
2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 71/1
2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TB408 | 53/3
2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 71/0
2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TB408 | 70/5
2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TB408 | 53/2
2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/11
2025-03-31 | 2025-04-02 | Sobha Devi | 38.8476 | 12.9492 | TB408 | 47/9
2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 70/10
2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 47/8
2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TB408 | 70/9
2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TB408 | 53/1
2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/4
2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TB408 | 67/0
2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4 | Crane erection+Derrick Pole
2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TB408 | 1A/6 | Crane erection+Derrick Pole
2025-06-17 | 2025-06-22 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 70/7 | Derrick
2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 | Derrick
2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7 | Crane erection+Derrick Pole
2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TB408 | 70/2 | Derrick
2025-06-27 | 2025-07-01 | Jwala Singh | 38.8476 | 7.7695 | TB408 | 8/9 | Derrick
2025-06-28 | 2025-07-03 | Jwala Singh Suraj Kumar | 38.8476 | 6.4746 | TB408 | 69/1 | Derrick
2025-07-01 | 2025-07-08 | Satyam Enterprises Vijay | 38.8476 | 4.856 | TB408 | 70/1 | Derrick
2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10 | Derrick
2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TB408 | 70/0 | Derrick
2025-07-08 | 2025-07-14 | Satyam Enterprises Vijay | 38.8476 | 5.5497 | TB408 | 70/8 | Derrick
2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8 | Crane erection+Derrick Pole
2025-07-11 | 2025-07-16 | Arawali 2 | 37.5044 | 6.2507 | TB408 | 2/8 | Derrick
2025-07-14 | 2025-07-21 | Jwala Singh Suraj Kumar | 57.5972 | 7.1997 | TB408 | 69/0 | Derrick
2025-07-19 | 2025-07-22 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/3 | Derrick
2025-07-16 | 2025-07-23 | Arawali 2 | 37.5044 | 4.688 | TB408 | 2/9 | Derrick
2025-07-14 | 2025-07-23 | Priyanka Devi 2 | 37.5044 | 3.7504 | TB408 | 18/3 | Derrick
2025-07-21 | 2025-07-24 | Hazarilal Yadav Poonam Kumari | 38.8476 | 9.7119 | TB408 | 26/2 | Derrick
2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5 | Derrick
2025-07-23 | 2025-07-26 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/2 | Derrick
2025-07-25 | 2025-07-28 | Hazarilal Yadav Poonam Kumari | 37.5044 | 9.3761 | TB408 | 26/3 | Derrick
2025-07-23 | 2025-07-28 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/4 | Derrick
2025-07-26 | 2025-07-29 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/1 | Derrick
2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 | Crane erection+Derrick
2025-07-23 | 2025-07-30 | Arawali 2 | 38.8476 | 4.856 | TB408 | 2/7 | Derrick
2025-07-27 | 2025-07-31 | Pusplata Praful | 37.5044 | 7.5009 | TB408 | 25/4 | Derrick
2025-07-21 | 2025-07-31 | Dharmendra Munnilal Pusplata | 38.8476 | 3.5316 | TB408 | 27/2 | Derrick
2025-07-27 | 2025-07-31 | Pusplata Kailash | 38.8476 | 7.7695 | TB408 | 27/3 | Derrick
2025-07-29 | 2025-08-03 | Satyam Enterprises | 60.0968 | 10.0161 | TB408 | 44/0 | Derrick
2025-07-25 | 2025-08-02 | Arawali 1 | 86.1293 | 9.5699 | TB408 | 12/0 | Derrick
2025-07-30 | 2025-08-04 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 29/1 | Derrick
2025-07-28 | 2025-08-03 | Satyam Enterprises | 47.1844 | 6.7406 | TB408 | 44/7 | Derrick
2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TB408 | 47/7 | Derrick
2025-08-01 | 2025-08-05 | Priyanka Devi | 37.5044 | 7.5009 | TB408 | 19/5 | Derrick
2025-08-01 | 2025-08-06 | Pusplata Kailash | 38.8476 | 6.4746 | TB408 | 30/3 | Derrick
2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TB408 | 44/10 | Derrick
2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TB408 | 25/3 | Derrick
2025-08-04 | 2025-08-09 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/5 | Derrick
2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1 | Derrick
2025-08-04 | 2025-08-09 | Jwala Singh | 37.5044 | 6.2507 | TB408 | 8/12 | Derrick
2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0 | Derrick
2025-08-07 | 2025-08-13 | Shobha Devi | 45.413 | 6.4876 | TB408 | 55/8 | Derrick
2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0 | Derrick
2025-08-09 | 2025-08-16 | Satyam Enterprises | 60.0968 | 7.5121 | TB408 | 44/6 | Derrick
2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2 | Derrick
2025-08-10 | 2025-08-17 | Rahul Kumar | 38.8476 | 4.856 | TB408 | 40/3 | Derrick
2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TB408 | 45/0 | Derrick
2025-08-13 | 2025-08-17 | Shobha Devi | 37.5044 | 7.5009 | TB408 | 55/7 | Derrick
2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3 | Derrick
2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TB408 | 30/5 | Derrick
2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TB408 | 27/4 | Derrick
2025-08-12 | 2025-08-18 | Satyam Manish | 38.8476 | 5.5497 | TB408 | 43/11 | Derrick
2025-08-13 | 2025-08-18 | Pusplata Pankaj | 38.8476 | 6.4746 | TB408 | 17/4 | Derrick
2025-08-12 | 2025-08-19 | Jwala Singh | 47.1844 | 5.898 | TB408 | 28/5 | Derrick
2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5 | Derrick
2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0 | Derrick
2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TB408 | 41/1 | Derrick
2025-08-17 | 2025-08-21 | Pusplata Kailash | 37.5044 | 7.5009 | TB408 | 30/6 | Derrick
2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2 | Derrick
2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4 | Derrick
2025-08-16 | 2025-08-23 | Pusplata Dharamveer | 38.8476 | 4.856 | TB408 | 27/1 | Derrick
2025-08-17 | 2025-08-24 | Satyam Enterprises | 47.1844 | 5.898 | TB408 | 44/9 | Derrick
2025-08-17 | 2025-08-24 | Sunny Construction | 37.5044 | 4.688 | TB408 | 55/1 | Derrick
2025-08-18 | 2025-08-24 | Rahul Kumar | 38.8476 | 5.5497 | TB408 | 40/2 | Derrick
2025-08-19 | 2025-08-25 | Jwala Singh | 37.5044 | 5.3578 | TB408 | 28/2 | Derrick
2025-08-18 | 2025-08-25 | Pusplata | 66.3811 | 8.2976 | TB408 | 18/0 | Derrick
2025-08-20 | 2025-08-25 | Pusplata Ashok | 37.5044 | 6.2507 | TB408 | 4/4 | Derrick
2025-08-21 | 2025-08-25 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 57/2 | Derrick
2025-08-19 | 2025-08-25 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 44/11 | Derrick
2025-08-22 | 2025-08-26 | Pusplata Kailash | 37.5044 | 7.5009 | TB408 | 31/1 | Derrick
2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3 | Derrick
2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TB408 | 57/1 | Derrick
2025-08-25 | 2025-08-30 | Pusplata Deepak | 37.5044 | 6.2507 | TB408 | 30/1 | Derrick
2025-08-25 | 2025-08-30 | Satyam Enterprises Pawan | 38.8476 | 6.4746 | TB408 | 43/10 | Derrick
2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 36/2 | Derrick
2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3 | Derrick
2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TB408 | 8/1 | Derrick
2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5 | Derrick
2025-08-29 | 2025-08-31 | Pusplata Ashok | 37.5044 | 12.5015 | TB408 | 4/3 | Derrick
2025-08-25 | 2025-08-31 | Chinta Devi | 47.1844 | 6.7406 | TB408 | 45/1 | Derrick
2025-08-26 | 2025-09-03 | Pusplata Santosh Pankaj Singh | 66.3811 | 7.3757 | TB408 | 14A/0 | Derrick
2025-08-26 | 2025-09-03 | Priyanka Devi Santosh | 37.5044 | 4.1672 | TB408 | 20/3 | Derrick
2025-08-26 | 2025-09-02 | Pusplata Kailash | 37.5044 | 4.688 | TB408 | 31/2 | Derrick
2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TB408 | 27/0 | Derrick
2025-08-29 | 2025-09-03 | Satyam Enterprises Manish | 38.8476 | 6.4746 | TB408 | 43/5 | Derrick
2025-08-29 | 2025-09-04 | Jwala Singh | 38.8476 | 5.5497 | TB408 | 8/4 | Derrick
2025-09-02 | 2025-09-05 | Sudheer 2 Priyanka Devi | 57.5972 | 14.3993 | TB408 | 21/0 | Derrick
2025-08-30 | 2025-09-06 | Ganesh Sinha | 37.5044 | 4.688 | TB408 | 36/3 | Derrick
2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6 | Derrick
2025-09-01 | 2025-09-06 | Sunny Construction | 47.1844 | 7.8641 | TB408 | 54/4 | Derrick
2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TB408 | 26/0 | Derrick
2025-09-01 | 2025-09-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 47/1 | Derrick
2025-09-02 | 2025-09-07 | Priyanka Devi Sudheer | 37.5044 | 6.2507 | TB408 | 20/2 | Derrick
2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0 | Derrick
2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4 | Derrick
2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6 | Derrick
2025-09-03 | 2025-09-10 | Pusplata Kailash | 38.8476 | 4.856 | TB408 | 32/1 | Derrick
2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TB408 | 52/4 | Derrick
2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TB408 | 34/3 | Derrick
2025-09-09 | 2025-09-12 | Priyanka Devi Sudheer | 38.8476 | 9.7119 | TB408 | 21/4 | Derrick
2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TB408 | 28/0 | Derrick
2025-09-05 | 2025-09-12 | Usha Tower | 37.5044 | 4.688 | TB408 | 6/2 | Derrick
2025-09-07 | 2025-09-12 | Sunny Construction | 45.413 | 7.5688 | TB408 | 54/3 | Derrick
2025-09-03 | 2025-09-13 | Sheetal Singh 1 | 38.8476 | 3.5316 | TB408 | 2/1 | Derrick
2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0 | Derrick+Crane
2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TB408 | 26/1 | Derrick
2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1 | Derrick
2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TB408 | 36/4 | Derrick
2025-09-13 | 2025-09-18 | Sunny Construction | 38.8476 | 6.4746 | TB408 | 54/1 | Derrick
2025-09-12 | 2025-09-18 | Jwala Singh 2 | 38.8476 | 5.5497 | TB408 | 8/5 | Derrick
2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/2 | Derrick
2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2 | Derrick
2025-09-19 | 2025-09-22 | Priyanka Devi Sudheer | 45.413 | 11.3533 | TB408 | 21/5 | Derrick
2025-09-19 | 2025-09-22 | Sunny Construction | 38.8476 | 9.7119 | TB408 | 54/2 | Derrick
2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3 | Derrick
2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3 | Derrick
2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TB408 | 8/2 | Derrick
2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0 | Derrick+Crane
2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11 | Derrick
2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TB408 | 36/0 | Derrick
2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TB408 | 37/0 | Derrick
2025-09-20 | 2025-09-29 | Priyanka Devi Sontosh | 57.5972 | 5.7597 | TB408 | 20/0 | Derrick
2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5 | Derrick
2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0 | Derrick+Crane
2025-09-20 | 2025-09-30 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/1 | Derrick
2025-09-22 | 2025-09-30 | Sunny Construction | 67.8737 | 7.5415 | TB408 | 54/0 | Derrick
2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3 | Derrick
2025-09-25 | 2025-10-03 | Sheetal Singh 1 | 37.5044 | 4.1672 | TB408 | 6/1 | Derrick
2025-09-27 | 2025-10-06 | Nirmal Mahto | 37.5044 | 3.7504 | TB408 | 35/5 | Derrick
2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6 | Derrick
2025-09-29 | 2025-10-08 | Shobha Devi | 66.3811 | 6.6381 | TB408 | 40/0 | Derrick
2025-10-03 | 2025-10-10 | Priyanka Devi Subodh | 37.5044 | 4.688 | TB408 | 10/1 | Derrick
2025-09-30 | 2025-10-11 | Sunny Construction | 67.8737 | 5.6561 | TB408 | 55/0 | Derrick
2025-09-30 | 2025-10-12 | Jirwa Devi | 37.5044 | 2.885 | TB408 | 30/2 | Derrick
2025-10-07 | 2025-10-13 | Nirmal Mahto | 37.5044 | 5.3578 | TB408 | 35/4 | Derrick
2025-10-12 | 2025-10-14 | Sunny Construction | 37.5044 | 12.5015 | TB408 | 55/2 | Derrick
2025-10-10 | 2025-10-17 | Ganesh Sinha | 47.1844 | 5.898 | TB408 | 37/1 | Derrick
2025-10-14 | 2025-10-18 | Shobha Devi | 67.8737 | 13.5747 | TB408 | 39/0 | Derrick
2025-09-29 | 2025-10-18 | Chinta Devi | 143.6019 | 7.1801 | TB408 | 46/0 | Derrick
2025-10-14 | 2025-10-22 | Nirmal Mahto | 57.5972 | 6.3997 | TB408 | 35/2 | Derrick
2025-10-18 | 2025-10-22 | Shobha Devi | 37.5044 | 7.5009 | TB408 | 39/1 | Derrick
2025-10-13 | 2025-10-23 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 29/4 | Derrick
2025-10-18 | 2025-10-24 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 37/2 | Derrick
2025-10-17 | 2025-10-24 | Devi Construction | 37.5044 | 4.688 | TB408 | 11/4 | Derrick
2025-10-16 | 2025-10-26 | Sanjeev Kumar | 67.8737 | 6.1703 | TB408 | 35/0 | Derrick
2025-10-22 | 2025-10-26 | Shobha Devi | 47.1844 | 9.4369 | TB408 | 38/4 | Derrick
2025-10-10 | 2025-10-27 | Vinay Construction | 37.5044 | 2.0836 | TB408 | 41/2 | Derrick
2025-10-25 | 2025-10-30 | Ganesh Sinha | 37.5044 | 6.2507 | TB408 | 37/3 | Derrick
2025-10-22 | 2025-10-31 | Nirmal Mahto | 47.1844 | 4.7184 | TB408 | 35/1 | Derrick
2025-10-20 | 2025-10-31 | Shri Shyam Construction | 37.5044 | 3.1254 | TB408 | 19/2 | Derrick
2025-10-18 | 2025-10-31 | Chinta Devi | 94.2199 | 6.73 | TB408 | 44/8 | Derrick
2025-10-27 | 2025-10-31 | Shobha Devi | 67.8737 | 13.5747 | TB408 | 38/0 | Derrick
2025-10-27 | 2025-11-04 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 34/4 | Derrick
2025-11-01 | 2025-11-06 | Shobha Devi | 45.413 | 7.5688 | TB408 | 40/1 | Derrick
2025-10-09 | 2025-11-07 | Shobha Devi | 47.1844 | 1.5728 | TB408 | 38/3 | Derrick
2025-10-31 | 2025-11-07 | Nirmal Mahto | 47.1844 | 5.898 | TB408 | 34/1 | Derrick
2025-10-31 | 2025-11-07 | Ganesh Sinha | 37.5044 | 4.688 | TB408 | 32/3 | Derrick
2025-10-25 | 2025-11-08 | Devi Construction | 100.968 | 6.7312 | TB408 | 4/0 | Derrick
2025-10-22 | 2025-11-08 | Santosh Singh | 66.3811 | 3.6878 | TB408 | 33/0 | Derrick
2025-10-27 | 2025-11-09 | Chinta Devi | 66.3811 | 4.7415 | TB408 | 42/0 | Derrick
2025-10-27 | 2025-11-09 | Vinay Construction | 45.413 | 3.2438 | TB408 | 42/2 | Derrick
2025-10-07 | 2025-11-10 | Panva Devi | 100.968 | 2.8848 | TB408 | 3/0 | Derrick
2025-11-05 | 2025-11-11 | Sanjeev Kumar | 37.5044 | 5.3578 | TB408 | 33/1 | Derrick
2025-11-08 | 2025-11-13 | Ganesh Sinha | 38.8476 | 6.4746 | TB408 | 32/2 | Derrick
2025-11-10 | 2025-11-13 | Chinta Devi | 38.8476 | 9.7119 | TB408 | 29/2 | Derrick
2025-11-08 | 2025-11-14 | Shobha Devi | 37.5044 | 5.3578 | TB408 | 42/4 | Derrick
2025-10-29 | 2025-11-16 | Kamlesh Kumar | 70.7017 | 3.7211 | TB408 | 5/0 | Derrick
2025-11-15 | 2025-11-17 | Sobha Devi | 37.5044 | 12.5015 | TB408 | 42/3 | Derrick
2025-11-10 | 2025-11-17 | Chinta Devi | 37.5044 | 4.688 | TB408 | 28/1 | Derrick
2025-11-09 | 2025-11-18 | Devi Construction | 57.5972 | 5.7597 | TB408 | 8/0 | Derrick
2025-11-11 | 2025-11-18 | Santosh Singh | 37.5044 | 4.688 | TB408 | 32/4 | Derrick
2025-11-08 | 2025-11-18 | Jirwa Devi | 66.3811 | 6.0346 | TB408 | 32/0 | Derrick
2025-11-11 | 2025-11-21 | Sanjeev Kumar | 45.413 | 4.1285 | TB408 | 34/2 | Derrick
2025-11-10 | 2025-11-21 | Vinay Construction | 45.413 | 3.7844 | TB408 | 42/1 | Derrick
2025-11-18 | 2025-11-22 | Shobha Devi | 45.413 | 9.0826 | TB408 | 38/2 | Derrick
|  | Nan |  |  | TB408
|  | Gang Name |  |  | TB408 |  | Erection Method
2025-11-14 |  | Ganesh Sinha |  |  | TB408 |  | Derrick
2025-11-22 |  | Vinay Construction |  |  | TB408 |  | Derrick
2025-11-22 |  | Sanjeev Kumar |  |  | TB408 |  | Derrick
2025-11-19 |  | Devi Construction |  |  | TB408 |  | Derrick
2025-11-17 |  | Kamlesh Kumar |  |  | TB408 |  | Derrick
2025-11-23 |  | Shobha Devi |  |  | TB408 |  | Derrick
2025-11-18 |  | Jirwa Devi |  |  | TB408 |  | Derrick
2025-11-08 |  | Dular Chand |  |  | TB408 |  | Derrick
2025-11-10 |  | Priyanka Devi |  |  | TB408 |  | Derrick
2025-11-21 |  | Chinta Devi |  |  | TB408 |  | Derrick
2025-11-23 |  | Panva Devi |  |  | TB408 |  | Derrick
2025-06-23 | 2025-06-28 | Dipak | 11.145 | 1.8575 | TB507 | 77/2 | Completed
2025-06-28 | 2025-07-02 | Dipak | 11.997 | 2.3994 | TB507 | 77/4 | Completed
2025-06-29 | 2025-07-05 | Srikarni | 11.145 | 1.5921 | TB507 | 75/7 | Completed
2025-07-03 | 2025-07-05 | Dipak | 13.072 | 4.3573 | TB507 | 77/5 | Completed
2025-07-07 | 2025-07-10 | Dipak | 11.145 | 2.7862 | TB507 | 77/3 | Completed
2025-07-11 | 2025-07-14 | Dipak | 11.145 | 2.7862 | TB507 | 77/1 | Completed
2025-07-15 | 2025-07-18 | Dipak | 11.145 | 2.7862 | TB507 | 75/6 | Completed
2025-07-19 | 2025-07-22 | Dipak | 11.145 | 2.7862 | TB507 | 75/5 | Completed
2025-07-22 | 2025-07-25 | Dipak | 11.145 | 2.7862 | TB507 | 75/4 | Completed
2025-07-25 | 2025-07-28 | Dipak | 11.997 | 2.9992 | TB507 | 75/3 | Completed
2025-07-29 | 2025-07-31 | Dipak | 11.145 | 3.715 | TB507 | 75/2 | Completed
2025-07-24 | 2025-07-31 | Ahmed Construction | 11.145 | 1.3931 | TB507 | 74/1 | Completed
2025-08-01 | 2025-08-04 | Dipak | 11.145 | 2.7862 | TB507 | 75/1 | Completed
2025-08-01 | 2025-08-08 | Ahmed Construction | 13.958 | 1.7448 | TB507 | 73/3 | Completed
2025-08-04 | 2025-08-09 | Dipak | 18.727 | 3.1212 | TB507 | 75/0 | Completed
2025-08-08 | 2025-08-16 | Ahmed Construction | 13.958 | 1.5509 | TB507 | 73/2 | Completed
2025-08-10 | 2025-08-16 | Dipak | 18.727 | 2.6753 | TB507 | 78/0 | Completed
2025-08-17 | 2025-08-23 | Ahmed Construction | 11.145 | 1.5921 | TB507 | 85/1 | Completed
2025-08-17 | 2025-08-23 | Dipak | 21.41 | 3.0586 | TB507 | 79/0 | Completed
2025-08-23 | 2025-08-28 | Ahmed Construction | 13.072 | 2.1787 | TB507 | 86/1 | Completed
2025-08-23 | 2025-08-28 | Dipak | 13.958 | 2.3263 | TB507 | 80/1 | Completed
2025-08-27 | 2025-08-29 | Gokul Sarkar | 11.145 | 3.715 | TB507 | 148/4 | Completed
2025-08-23 | 2025-08-31 | Ajay Kumar | 11.145 | 1.2383 | TB507 | 95A/1 | Completed
2025-08-29 | 2025-08-31 | Dipak | 11.145 | 3.715 | TB507 | 81/3 | Completed
2025-08-29 | 2025-09-04 | Gokul Sarkar | 11.145 | 1.5921 | TB507 | 148/3 | Completed
2025-09-01 | 2025-09-05 | Dipak | 11.997 | 2.3994 | TB507 | 81/2 | Completed
2025-08-27 | 2025-09-09 | Ayansh Const | 11.997 | 0.85693 | TB507 | 145/1 | Completed
2025-09-05 | 2025-09-09 | Dipak | 11.145 | 2.229 | TB507 | 81/4 | Completed
2025-09-05 | 2025-09-10 | Gokul Sarkar | 11.145 | 1.8575 | TB507 | 148/2 | Completed
2025-08-29 | 2025-09-11 | Ahmed Construction | 11.997 | 0.85693 | TB507 | 83/1 | Completed
2025-09-01 | 2025-09-11 | Ajay Kumar 1 | 18.727 | 1.7025 | TB507 | 97/0 | Completed
2025-09-11 | 2025-09-14 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 148/5 | Completed
2025-09-09 | 2025-09-14 | Ayansh Const | 11.145 | 1.8575 | TB507 | 145/2 | Completed
2025-09-09 | 2025-09-14 | Dipak | 13.072 | 2.1787 | TB507 | 82/1 | Completed
2025-09-01 | 2025-09-15 | Ajay Kumar 1 | 11.145 | 0.743 | TB507 | 96/1 | Completed
2025-09-11 | 2025-09-15 | Ahmed Construction | 11.145 | 2.229 | TB507 | 79/2 | Completed
2025-08-28 | 2025-09-16 | Windbridge Energy | 11.145 | 0.55725 | TB507 | 133/2 | Completed
2025-09-14 | 2025-09-19 | Gokul Sarkar | 11.145 | 1.8575 | TB507 | 148/6 | Completed
2025-09-14 | 2025-09-19 | Ayansh Const | 11.145 | 1.8575 | TB507 | 145/3 | Completed
2025-09-11 | 2025-09-17 | Prayag Saw 1 | 11.997 | 1.7139 | TB507 | 143/5 | Completed
2025-09-11 | 2025-09-17 | Prayag Saw 2 | 11.997 | 1.7139 | TB507 | 143/4 | Completed
2025-09-18 | 2025-09-20 | Prayag Saw 1 | 11.145 | 3.715 | TB507 | 143/2 | Completed
2025-09-18 | 2025-09-20 | Prayag Saw 2 | 11.145 | 3.715 | TB507 | 143/6 | Completed
2025-09-11 | 2025-09-21 | Ajay Kumar 2 | 11.997 | 1.0906 | TB507 | 97/1 | Completed
2025-09-14 | 2025-09-21 | Dipak | 18.727 | 2.3409 | TB507 | 113A/0 | Completed
2025-09-17 | 2025-09-22 | Windbridge Energy | 11.145 | 1.8575 | TB507 | 133/3 | Completed
2025-09-21 | 2025-09-23 | Prayag Saw 1 | 11.997 | 3.999 | TB507 | 143/3 | Completed
2025-09-21 | 2025-09-23 | Prayag Saw 2 | 13.072 | 4.3573 | TB507 | 143/7 | Completed
2025-09-20 | 2025-09-23 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 148/7 | Completed
2025-09-15 | 2025-09-24 | Ajay Kumar 1 | 11.145 | 1.1145 | TB507 | 98/1 | Completed
2025-09-24 | 2025-09-26 | Dipak | 13.958 | 4.6527 | TB507 | 114/1 | Completed
2025-09-22 | 2025-09-27 | Prayag Saw 2 | 13.072 | 2.1787 | TB507 | 143/1 | Completed
2025-09-24 | 2025-09-27 | Prayag Saw 1 | 13.072 | 3.268 | TB507 | 141/2 | Completed
2025-09-24 | 2025-09-27 | Gokul Sarkar | 11.997 | 2.9992 | TB507 | 149B/1 | Completed
2025-09-19 | 2025-09-27 | Ahmed Construction | 13.072 | 1.4524 | TB507 | 76/1 | Completed
2025-09-27 | 2025-09-29 | Dipak | 11.145 | 3.715 | TB507 | 116/1 | Completed
2025-09-23 | 2025-09-29 | Windbridge Energy | 11.997 | 1.7139 | TB507 | 133/6 | Completed
2025-09-27 | 2025-09-30 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 149B/2 | Completed
2025-09-20 | 2025-09-30 | Chandra Sekhar | 11.997 | 1.0906 | TB507 | 145/4 | Completed
2025-09-23 | 2025-09-30 | Ajay Kumar 2 | 11.145 | 1.3931 | TB507 | 98A/1 | Completed
2025-09-27 | 2025-09-30 | Prayag Saw 1 | 11.145 | 2.7862 | TB507 | 141/1 | Completed
2025-09-27 | 2025-09-30 | Prayag Saw 2 | 18.9798 | 4.745 | TB507 | 143/0 | Completed
2025-09-30 | 2025-10-03 | Chandra Sekhar | 11.997 | 2.9992 | TB507 | 146/1 | Completed
2025-09-30 | 2025-10-03 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 147/7 | Completed
2025-09-29 | 2025-10-05 | Windbridge Energy | 11.145 | 1.5921 | TB507 | 133/7 | Completed
2025-10-03 | 2025-10-05 | Chandra Sekhar | 11.145 | 3.715 | TB507 | 146/2 | Completed
2025-09-30 | 2025-10-07 | Dipak | 21.41 | 2.6763 | TB507 | 116/0 | Completed
2025-10-01 | 2025-10-07 | Prayag Saw 1 | 18.9798 | 2.7114 | TB507 | 142/0 | Completed
2025-10-01 | 2025-10-08 | Prayag Saw 2 | 26.291 | 3.2864 | TB507 | 144/0 | Completed
2025-10-05 | 2025-10-10 | Chandra Sekhar | 18.727 | 3.1212 | TB507 | 146/0 | Completed
2025-10-08 | 2025-10-10 | Prayag Saw 1 | 11.997 | 3.999 | TB507 | 140/2 | Completed
2025-10-03 | 2025-10-10 | Gokul Sarkar | 21.41 | 2.6763 | TB507 | 149/0 | Completed
2025-10-05 | 2025-10-11 | Windbridge Energy | 13.072 | 1.8674 | TB507 | 133/8 | Completed
2025-10-10 | 2025-10-11 | Prayag Saw 1 | 11.997 | 5.9985 | TB507 | 140/3 | Completed
2025-10-10 | 2025-10-12 | Chandra Sekhar | 18.727 | 6.2423 | TB507 | 147/0 | Completed
2025-10-08 | 2025-10-13 | Dipak | 18.727 | 3.1212 | TB507 | 115/0 | Completed
2025-10-08 | 2025-10-13 | Prayag Saw 2 | 11.145 | 1.8575 | TB507 | 138/1 | Completed
2025-09-26 | 2025-10-15 | Ajay Kumar | 18.727 | 0.93635 | TB507 | 98A/0 | Completed
2025-10-10 | 2025-10-15 | Gokul Sarkar | 21.41 | 3.5683 | TB507 | 149A/0 | Completed
2025-10-11 | 2025-10-15 | Windbridge Energy | 11.145 | 2.229 | TB507 | 133/4 | Completed
2025-10-11 | 2025-10-16 | Prayag Saw 1 | 18.727 | 3.1212 | TB507 | 141/0 | Completed
2025-10-12 | 2025-10-15 | Chandra Sekhar | 11.145 | 2.7862 | TB507 | 147/3 | Completed
2025-10-13 | 2025-10-16 | Prayag Saw 2 | 11.145 | 2.7862 | TB507 | 138/2 | Completed
2025-10-13 | 2012-10-18 | Dipak | 18.727 |  | TB507 | 110/0 | Completed
2025-10-15 | 2025-10-19 | Windbridge Energy | 11.145 | 2.229 | TB507 | 133/1 | Completed
2025-10-16 | 2025-10-19 | Prayag Saw 2 | 11.145 | 2.7862 | TB507 | 138/3 | Completed
2025-10-16 | 2025-10-19 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 147/9 | Completed
2025-10-15 | 2025-10-19 | Chandra Sekhar | 11.145 | 2.229 | TB507 | 147/2 | Completed
2025-10-19 | 2025-10-22 | Chandra Sekhar | 11.145 | 2.7862 | TB507 | 147/1 | Completed
2025-10-19 | 2025-10-22 | Gokul Sarkar | 11.145 | 2.7862 | TB507 | 147/8 | Completed
2025-10-16 | 2025-10-23 | Prayag Saw 1 | 21.41 | 2.6763 | TB507 | 134A/0 | Completed
2025-10-19 | 2025-10-24 | Windbridge Energy | 11.145 | 1.8575 | TB507 | 135/1 | Completed
2025-10-19 | 2025-10-24 | Namechand Mahto | 11.145 | 1.8575 | TB507 | 82/2 | Completed
2025-10-19 | 2025-10-24 | Prayag Saw 2 | 18.1115 | 3.0186 | TB507 | 138/0 | Completed
2025-10-24 | 2025-10-26 | Prayag Saw 1 | 11.997 | 3.999 | TB507 | 134A/2 | Completed
2025-10-19 | 2025-10-27 | Dipak | 24.1826 | 2.687 | TB507 | 112/0 | Completed
2025-10-23 | 2025-10-26 | Chandra Sekhar |  |  | TB507 | 147/6 | Completed
2025-10-23 | 2025-10-27 | Gokul Sarkar |  |  | TB507 | 148/1 | Completed
2025-10-27 | 2025-10-28 | Chandra Sekhar |  |  | TB507 | 147/5 | Completed
2025-10-27 | 2025-10-29 | Prayag Saw 2 |  |  | TB507 | 134/0 | Completed
2025-10-24 | 2025-10-31 | Namechand Mahto | 18.727 | 2.3409 | TB507 | 76/0 | Completed
2025-10-24 | 2025-10-31 | Windbridge Energy | 18.727 | 2.3409 | TB507 | 133/0 | Completed
2025-10-28 | 2025-10-31 | Chandra Sekhar |  |  | TB507 | 147/4 | Completed
2025-10-26 | 2025-10-28 | Prayag Saw 1 |  |  | TB507 | 139/0 | Completed
2025-10-27 | 2025-11-01 | Gokul Sarkar |  |  | TB507 | 153A/0 | Completed
2025-10-27 | 2025-11-02 | Dipak |  |  | TB507 | 115/1 | Completed
2025-10-29 | 2025-11-02 | Prayag Saw 1 |  |  | TB507 | 135/0 | Completed
2025-10-29 | 2025-11-03 | Prayag Saw 2 |  |  | TB507 | 134A/1 | Completed
2025-11-01 | 2025-11-04 | Windbridge Energy |  |  | TB507 | 132/3 | Completed
2025-11-01 | 2025-11-05 | Namechand Mahto |  |  | TB507 | 77/0 | Completed
2025-11-01 | 2025-11-05 | Chandra Sekhar |  |  | TB507 | 129/1 | Completed
2025-11-04 | 2025-11-06 | Prayag Saw 2 |  |  | TB507 | 134A/4 | Completed
2025-11-05 | 2025-11-07 | Windbridge Energy |  |  | TB507 | 132/1 | Completed
2025-11-03 | 2025-11-08 | Prayag Saw 1 |  |  | TB507 | 136/0 | Completed
2025-11-06 | 2025-11-09 | Chandra Sekhar |  |  | TB507 | 131/1 | Completed
2025-10-18 |  | Namechand Mahto |  |  | TB507 | 104B/2 | Strong ROW. Landowner stopped work not allowing to enter at location and Tower material left without watchmen.
2025-11-06 |  | Namechand Mahto | 18.727 |  | TB507 | 98/0 | WIP
2025-11-03 |  | Dipak |  |  | TB507 | 111/0 | WIP
2025-11-01 |  | Gokul Sarkar |  |  | TB507 | 152/0 | WIP
2025-11-06 |  | Prayag Saw 2 |  |  | TB507 | 137/0 | WIP
2025-11-08 |  | Windbridge Energy |  |  | TB507 | 132/4 | WIP
2025-11-09 |  | Chandra Sekhar |  |  | TB507 | 129/0 | WIP
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507
|  | Nan |  |  | TB507

## Data Issues
Start Date | Complete Date | Gang name | Tower Weight | Productivity | Project Name | Location No. | Status | Issues
|  | Nan | 156.8261 |  | TA325 | 102/0 | WIP | Missing start/end date (not expanded)
|  | Nan | 156.8261 |  | TA325 | 103/0 |  | Missing start/end date (not expanded)
|  | Nan | 123.649 |  | TA325 | 154/0 |  | Missing start/end date (not expanded)
|  | Nan | 123.649 |  | TA325 | 154/1 |  | Missing start/end date (not expanded)
|  | Nan | 101.8517 |  | TA325 | 159/2 |  | Missing start/end date (not expanded)
|  | Nan | 129.341 |  | TA325 | 160/0 |  | Missing start/end date (not expanded)
|  | Nan | 89.1461 |  | TA325 | 165/4 |  | Missing start/end date (not expanded)
|  | Nan | 89.1461 |  | TA325 | 165/5 |  | Missing start/end date (not expanded)
|  | Nan | 94.4077 |  | TA325 | 166/0 | WIP | Missing start/end date (not expanded)
|  | Nan | 94.4077 |  | TA325 | 167/0 |  | Missing start/end date (not expanded)
|  | Nan | 80.408 |  | TA325 | 167/1 |  | Missing start/end date (not expanded)
|  | Nan | 39.4589 |  | TA325 | 172/1 |  | Missing start/end date (not expanded)
|  | Nan | 141.874 |  | TA325 | 173/0 |  | Missing start/end date (not expanded)
|  | Nan | 129.341 |  | TA325 | 174/0 |  | Missing start/end date (not expanded)
|  | Nan | 37.7305 |  | TA325 | 175/1 |  | Missing start/end date (not expanded)
|  | Nan | 85.2338 |  | TA325 | 182A/0 |  | Missing start/end date (not expanded)
|  | Nan | 141.874 |  | TA325 | 183/0 |  | Missing start/end date (not expanded)
|  | Nan | 172.769 |  | TA325 | 186/0 | WIP | Missing start/end date (not expanded)
|  | Nan | 82.2388 |  | TA325 | 200/0 |  | Missing start/end date (not expanded)
|  | Nan | 98.8356 |  | TA325 | 201/1 |  | Missing start/end date (not expanded)
|  | Nan | 228.7027 |  | TA325 | 203/0 |  | Missing start/end date (not expanded)
|  | Nan | 141.874 |  | TA325 | 208/0 |  | Missing start/end date (not expanded)
|  | Nan | 54.4178 |  | TA325 | 211A/0 |  | Missing start/end date (not expanded)
|  | Nan | 36.0448 |  | TA325 | 211A/1 |  | Missing start/end date (not expanded)
|  | Nan | 75.4524 |  | TA325 | 212/0 |  | Missing start/end date (not expanded)
|  | Nan | 84.2993 |  | TA325 | 213/0 |  | Missing start/end date (not expanded)
|  | Nan | 37.7305 |  | TA325 | 213/1 |  | Missing start/end date (not expanded)
|  | Nan | 44.7282 |  | TA325 | 214/1 |  | Missing start/end date (not expanded)
|  | Nan | 99.7717 |  | TA325 | 216/0 |  | Missing start/end date (not expanded)
|  | Nan | 122.8082 |  | TA325 | 217/0 |  | Missing start/end date (not expanded)
|  | Nan | 56.8632 |  | TA325 | 217A/0 |  | Missing start/end date (not expanded)
|  | Nan | 97.9336 |  | TA325 | 219/0 |  | Missing start/end date (not expanded)
|  | Nan | 129.341 |  | TA325 | 221/0 |  | Missing start/end date (not expanded)
|  | Nan | 141.874 |  | TA325 | 222/0 |  | Missing start/end date (not expanded)
|  | Nan | 37.7305 |  | TA325 | 223/2 |  | Missing start/end date (not expanded)
|  | Nan | 141.874 |  | TA325 | 228/0 |  | Missing start/end date (not expanded)
|  | Nan | 141.874 |  | TA325 | 239/0 |  | Missing start/end date (not expanded)
|  | Total Completed | 29546.1061 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Total Tower Erection |  |  | TA325 |  | Completed | Missing start/end date (not expanded)
|  | Balance Tower Erection | 40 |  | TA325 |  | 39 | Missing start/end date (not expanded)
|  | Nan | 146 |  | TA325 |  | 140 | Missing start/end date (not expanded)
|  | Tower Type | 40 |  | TA325 |  | 39 | Missing start/end date (not expanded)
|  | Da 0 | 30 |  | TA325 |  | 30 | Missing start/end date (not expanded)
|  | Da 3 | 11 |  | TA325 |  | 10 | Missing start/end date (not expanded)
|  | Da 6 | 267 |  | TA325 |  | 258 | Missing start/end date (not expanded)
|  | Da 9 | 25 |  | TA325 |  | 0 | Missing start/end date (not expanded)
|  | Da 3 | 6 |  | TA325 |  | 0 | Missing start/end date (not expanded)
|  | Db1 0 | 8 |  | TA325 |  | 0 | Missing start/end date (not expanded)
|  | Db1 18 | 9 |  | TA325 |  | 0 | Missing start/end date (not expanded)
|  | Db1 3 | 6 |  | TA325 |  | 0 | Missing start/end date (not expanded)
|  | Db1 6 | 1 |  | TA325 |  | 0 | Missing start/end date (not expanded)
|  | Db1 9 | 55 |  | TA325 |  | 0 | Missing start/end date (not expanded)
|  | Db2 0 | 26 |  | TA325 |  | 0 | Missing start/end date (not expanded)
|  | Db2 18 | 3 |  | TA325 |  | 0 | Missing start/end date (not expanded)
|  | Db2 25 | 4 |  | TA325 |  | 0 | Missing start/end date (not expanded)
|  | Db2 3 | 7 |  | TA325 |  | 0 | Missing start/end date (not expanded)
|  | Db2 6 | 4 |  | TA325 |  | 0 | Missing start/end date (not expanded)
|  | Db2 9 | 3 |  | TA325 |  | 0 | Missing start/end date (not expanded)
|  | Dc 0 | 47 |  | TA325 |  | 0 | Missing start/end date (not expanded)
|  | Dc1 0 | 16 |  | TA325 |  | 15 | Missing start/end date (not expanded)
|  | Dc1 18 | 4 |  | TA325 |  | 3 | Missing start/end date (not expanded)
|  | Dc1 3 | 3 |  | TA325 |  | 2 | Missing start/end date (not expanded)
|  | Dc1 6 | 4 |  | TA325 |  | 4 | Missing start/end date (not expanded)
|  | Dc1 9 | 6 |  | TA325 |  | 6 | Missing start/end date (not expanded)
|  | Dc2 0 | 5 |  | TA325 |  | 2 | Missing start/end date (not expanded)
|  | Dc2 18 | 2 |  | TA325 |  | 0 | Missing start/end date (not expanded)
|  | Dc2 25 | 40 |  | TA325 |  | 32 | Missing start/end date (not expanded)
|  | Dc2 3 | 19 |  | TA325 |  | 19 | Missing start/end date (not expanded)
|  | Dc2 6 | 8 |  | TA325 |  | 7 | Missing start/end date (not expanded)
|  | Dc2 9 | 11 |  | TA325 |  | 11 | Missing start/end date (not expanded)
|  | Dct 0 | 7 |  | TA325 |  | 6 | Missing start/end date (not expanded)
|  | Dd45 0 | 7 |  | TA325 |  | 5 | Missing start/end date (not expanded)
|  | Dd45 18 | 15 |  | TA325 |  | 9 | Missing start/end date (not expanded)
|  | Dd45 25 | 4 |  | TA325 |  | 3 | Missing start/end date (not expanded)
|  | Dd45 3 | 2 |  | TA325 |  | 1 | Missing start/end date (not expanded)
|  | Dd45 35 | 73 |  | TA325 |  | 61 | Missing start/end date (not expanded)
|  | Dd45 6 | 1 |  | TA325 |  | 0 | Missing start/end date (not expanded)
|  | Dd45 9 | 1 |  | TA325 |  | 0 | Missing start/end date (not expanded)
|  | Dd60 0 | 483 |  | TA325 |  | 351 | Missing start/end date (not expanded)
|  | Dd60 18 |  |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Dd60 25 |  |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Dd60 3 |  |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Dd60 35 |  |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Dd60 55 |  |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Dd60 6 |  |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Dd60 9 |  |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Total |  |  | TA325 |  |  | Missing start/end date (not expanded)
2025-10-18 | 2025-11-15 | Nasirudin | 228.7027 | 7.8863 | TA325 | 202/0 | Completed | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 228.7027 |  | TA325 | 203/0 |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Total Completed | 29546.1061 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Da 6 | 267 |  | TA325 |  | 258 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Da 3 | 6 |  | TA325 |  | 0 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Db1 0 | 8 |  | TA325 |  | 0 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Db1 18 | 9 |  | TA325 |  | 0 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Db1 3 | 6 |  | TA325 |  | 0 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Db1 6 | 1 |  | TA325 |  | 0 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Db2 18 | 3 |  | TA325 |  | 0 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Db2 25 | 4 |  | TA325 |  | 0 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Db2 3 | 7 |  | TA325 |  | 0 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Db2 6 | 4 |  | TA325 |  | 0 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Db2 9 | 3 |  | TA325 |  | 0 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Dc1 18 | 4 |  | TA325 |  | 3 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Dc1 3 | 3 |  | TA325 |  | 2 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Dc1 6 | 4 |  | TA325 |  | 4 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Dc1 9 | 6 |  | TA325 |  | 6 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Dc2 0 | 5 |  | TA325 |  | 2 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Dc2 18 | 2 |  | TA325 |  | 0 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Dc2 6 | 8 |  | TA325 |  | 7 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Dct 0 | 7 |  | TA325 |  | 6 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Dd45 0 | 7 |  | TA325 |  | 5 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Dd45 25 | 4 |  | TA325 |  | 3 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Dd45 3 | 2 |  | TA325 |  | 1 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Dd45 6 | 1 |  | TA325 |  | 0 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Dd45 9 | 1 |  | TA325 |  | 0 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Dd60 0 | 483 |  | TA325 |  | 351 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
2025-10-12 |  | Fouzi Ratto | 124.95 |  | TA413 | 24/0 | WIP | Missing start/end date (not expanded)
2025-11-14 |  | Govind Mahto 1 | 66.7809 |  | TA413 | 23A/0 | WIP | Missing start/end date (not expanded)
2025-10-23 |  | Sk Samiul 1 | 43.8044 |  | TA413 | 29A/3 | ROW | Missing start/end date (not expanded)
2025-11-08 |  | Ved Prakash | 173.5609 |  | TA413 | 27/0 | WIP | Missing start/end date (not expanded)
2025-11-12 |  | Pritam Enterprises 2 | 43.8044 |  | TA413 | 25/0 | WIP | Missing start/end date (not expanded)
2025-11-13 |  | Govind Mahto 2 | 73.2445 |  | TA413 | 11/0 | WIP | Missing start/end date (not expanded)
2025-11-16 |  | Pritam Enterprises 4 | 37.1383 |  | TA413 | 17/0 | WIP | Missing start/end date (not expanded)
2025-11-21 |  | Punam Kumari 1 | 43.8044 |  | TA413 | 21/3 | WIP | Missing start/end date (not expanded)
2025-11-21 |  | Jwala Singh 2 | 35.6018 |  | TA413 | 27/2 | WIP | Missing start/end date (not expanded)
2025-11-21 |  | Jwala Singh 1 | 36.1598 |  | TA413 | 15/9 | ROW | Missing start/end date (not expanded)
|  | Nan |  |  | TA413 | 15/1 |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
2025-09-08 |  | Subhash | 33 |  | TA418 | 46/11 | (ROW) | Missing start/end date (not expanded)
2025-10-16 |  | M S Mdpl | 89 |  | TA418 | 39/0 | 3rd section work. | Missing start/end date (not expanded)
2025-11-06 |  | M S Tofit | 45 |  | TA418 | 48/0 | Cage 02 section work under progress. | Missing start/end date (not expanded)
2025-11-06 |  | Kec 02 Barkat Ali | 29 |  | TA418 | 33/4 | 1st section work under progress. | Missing start/end date (not expanded)
2025-11-15 |  | Dhruv | 73.245 |  | TA419 | 0C/0 | WIP | Missing start/end date (not expanded)
|  | Nan | 77.077 |  | TA419 | 0E/0 |  | Missing start/end date (not expanded)
|  | Nan | 58.8823 |  | TA419 | 2/0 |  | Missing start/end date (not expanded)
|  | Nan | 78.7772 |  | TA419 | 3/0 |  | Missing start/end date (not expanded)
|  | Nan | 57.963 |  | TA419 | 7/0 |  | Missing start/end date (not expanded)
|  | Nan | 58.8823 |  | TA419 | 8/0 |  | Missing start/end date (not expanded)
|  | Nan | 81.828 |  | TA419 | 9/0 |  | Missing start/end date (not expanded)
2025-11-05 |  | Bhairo Mahato | 160.944 |  | TA419 | 11/0 | WIP | Missing start/end date (not expanded)
|  | Nan | 37.931 |  | TA419 | 12A/1 |  | Missing start/end date (not expanded)
|  | Nan | 83.134 |  | TA419 | 13/0 |  | Missing start/end date (not expanded)
|  | Nan | 83.134 |  | TA419 | 14/0 |  | Missing start/end date (not expanded)
|  | Nan | 36.16 |  | TA419 | 14/1 |  | Missing start/end date (not expanded)
|  | Nan | 62.444 |  | TA419 | 15/0 |  | Missing start/end date (not expanded)
|  | Nan | 58.8823 |  | TA419 | 25/0 |  | Missing start/end date (not expanded)
|  | Nan | 87.021 |  | TA419 | 32/0 |  | Missing start/end date (not expanded)
|  | Nan | 83.134 |  | TA419 | 33/0 |  | Missing start/end date (not expanded)
|  | Nan | 34.79 |  | TA419 | 33/1 |  | Missing start/end date (not expanded)
2025-11-12 |  | Pumam Kumari 1 | 75.27 |  | TA419 | 36/0 | WIP | Missing start/end date (not expanded)
|  | Nan | 43.804 |  | TA419 | 36/3 |  | Missing start/end date (not expanded)
|  | Nan | 82.264 |  | TA419 | 36/4 |  | Missing start/end date (not expanded)
|  | Nan | 45.697 |  | TA419 | 36/5 |  | Missing start/end date (not expanded)
|  | Nan | 37.138 |  | TA419 | 36/9 |  | Missing start/end date (not expanded)
|  | Nan | 43.804 |  | TA419 | 36/10 |  | Missing start/end date (not expanded)
|  | Nan | 137.046 |  | TA419 | 37/0 |  | Missing start/end date (not expanded)
2025-11-12 |  | Punam Kumari 2 | 137.046 |  | TA419 | 38/0 | WIP | Missing start/end date (not expanded)
|  | Nan | 36.16 |  | TA419 | 38/1 |  | Missing start/end date (not expanded)
|  | Nan | 36.16 |  | TA419 | 38/2 |  | Missing start/end date (not expanded)
|  | Nan | 37.931 |  | TA419 | 38/3 |  | Missing start/end date (not expanded)
|  | Nan | 36.16 |  | TA419 | 38/4 |  | Missing start/end date (not expanded)
|  | Nan | 37.931 |  | TA419 | 38/5 |  | Missing start/end date (not expanded)
|  | Nan | 37.138 |  | TA419 | 38/6 |  | Missing start/end date (not expanded)
2025-11-12 |  | Infinidea 2 | 37.931 |  | TA419 | 38/7 | WIP | Missing start/end date (not expanded)
|  | Nan | 37.931 |  | TA419 | 38/8 |  | Missing start/end date (not expanded)
|  | Nan | 35.602 |  | TA419 | 38/9 |  | Missing start/end date (not expanded)
|  | Nan | 36.16 |  | TA419 | 38/10 |  | Missing start/end date (not expanded)
|  | Nan | 36.16 |  | TA419 | 38/11 |  | Missing start/end date (not expanded)
|  | Nan | 124.95 |  | TA419 | 39/0 |  | Missing start/end date (not expanded)
|  | Nan | 124.95 |  | TA419 | 40/0 |  | Missing start/end date (not expanded)
|  | Nan | 34.79 |  | TA419 | 40/1 |  | Missing start/end date (not expanded)
|  | Nan | 37.931 |  | TA419 | 40/2 |  | Missing start/end date (not expanded)
|  | Nan | 37.931 |  | TA419 | 40/3 |  | Missing start/end date (not expanded)
|  | Nan | 37.138 |  | TA419 | 40/4 |  | Missing start/end date (not expanded)
2025-11-17 |  | Madhu Sah | 37.138 |  | TA419 | 40/6 | WIP | Missing start/end date (not expanded)
|  | Nan | 35.602 |  | TA419 | 40/7 |  | Missing start/end date (not expanded)
|  | Nan | 36.16 |  | TA419 | 40/8 |  | Missing start/end date (not expanded)
|  | Nan | 36.16 |  | TA419 | 40/9 |  | Missing start/end date (not expanded)
|  | Nan | 83.134 |  | TA419 | 41/0 |  | Missing start/end date (not expanded)
|  | Nan | 34.79 |  | TA419 | 41/1 |  | Missing start/end date (not expanded)
|  | Nan | 35.602 |  | TA419 | 41/2 |  | Missing start/end date (not expanded)
|  | Nan | 36.16 |  | TA419 | 41/3 |  | Missing start/end date (not expanded)
2025-11-15 |  | Jwala Singh | 43.804 |  | TA419 | 41/4 | WIP | Missing start/end date (not expanded)
|  | Nan | 37.931 |  | TA419 | 41/6 |  | Missing start/end date (not expanded)
|  | Nan | 36.16 |  | TA419 | 41/7 |  | Missing start/end date (not expanded)
|  | Nan | 36.16 |  | TA419 | 41/8 |  | Missing start/end date (not expanded)
|  | Nan | 152.3804 |  | TA419 | 42/0 |  | Missing start/end date (not expanded)
|  | Nan | 139.9685 |  | TA419 | 43/0 |  | Missing start/end date (not expanded)
|  | Nan | 45.697 |  | TA419 | 43/1 |  | Missing start/end date (not expanded)
|  | Nan | 35.602 |  | TA419 | 43/2 |  | Missing start/end date (not expanded)
|  | Nan | 36.16 |  | TA419 | 43/3 |  | Missing start/end date (not expanded)
|  | Nan | 34.79 |  | TA419 | 43/4 |  | Missing start/end date (not expanded)
2025-11-19 |  | Mukhilal 1 | 37.138 |  | TA419 | 43/5 | WIP | Missing start/end date (not expanded)
|  | Nan | 34.79 |  | TA419 | 43/6 |  | Missing start/end date (not expanded)
|  | Nan | 64.4822 |  | TA419 | 44/0 |  | Missing start/end date (not expanded)
|  | Nan | 118.4303 |  | TA419 | 45/0 |  | Missing start/end date (not expanded)
|  | Nan | 143.4621 |  | TA419 | 46/0 |  | Missing start/end date (not expanded)
|  | Nan | 43.7757 |  | TA419 | 46/1 |  | Missing start/end date (not expanded)
2025-11-12 |  | Satyam Trading | 46.0492 |  | TA419 | 46/2 | WIP | Missing start/end date (not expanded)
2025-11-12 |  | Maheshwar | 43.7757 |  | TA419 | 46/3 | WIP | Missing start/end date (not expanded)
|  | Nan | 53.3239 |  | TA419 | 46/4 |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA419 | 47/0 |  | Missing start/end date (not expanded)
|  | Nan | 78.6863 |  | TA419 | 48/0 |  | Missing start/end date (not expanded)
|  | Nan | 67.112 |  | TA419 | 48/1 |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA419 | 49/0 |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA419 | 50/0 |  | Missing start/end date (not expanded)
|  | Nan | 64.4822 |  | TA419 | 50/1 |  | Missing start/end date (not expanded)
|  | Nan | 89.7178 |  | TA419 | 51/0 |  | Missing start/end date (not expanded)
|  | Nan | 67.112 |  | TA419 | 52/0 |  | Missing start/end date (not expanded)
|  | Nan | 42.3742 |  | TA419 | 52/1 |  | Missing start/end date (not expanded)
|  | Nan | 42.3742 |  | TA419 | 52/2 |  | Missing start/end date (not expanded)
|  | Nan | 73.4258 |  | TA419 | 53/0 |  | Missing start/end date (not expanded)
|  | Nan | 64.4822 |  | TA419 | 54/0 |  | Missing start/end date (not expanded)
|  | Nan | 43.7757 |  | TA419 | 54/1 |  | Missing start/end date (not expanded)
|  | Nan | 43.7757 |  | TA419 | 54/2 |  | Missing start/end date (not expanded)
|  | Nan | 42.3742 |  | TA419 | 54/3 |  | Missing start/end date (not expanded)
|  | Nan | 43.7757 |  | TA419 | 54/4 |  | Missing start/end date (not expanded)
|  | Nan | 46.0492 |  | TA419 | 54/5 |  | Missing start/end date (not expanded)
|  | Nan | 43.7757 |  | TA419 | 54/6 |  | Missing start/end date (not expanded)
|  | Nan | 55.3387 |  | TA419 | 54/7 |  | Missing start/end date (not expanded)
|  | Nan | 67.112 |  | TA419 | 55/0 |  | Missing start/end date (not expanded)
|  | Nan | 42.3742 |  | TA419 | 55/1 |  | Missing start/end date (not expanded)
|  | Nan | 42.3742 |  | TA419 | 55/2 |  | Missing start/end date (not expanded)
|  | Nan | 42.3742 |  | TA419 | 55/3 |  | Missing start/end date (not expanded)
|  | Nan | 46.0492 |  | TA419 | 55/4 |  | Missing start/end date (not expanded)
|  | Nan | 43.7757 |  | TA419 | 55/5 |  | Missing start/end date (not expanded)
|  | Nan | 55.3387 |  | TA419 | 55/6 |  | Missing start/end date (not expanded)
|  | Nan | 93.2387 |  | TA419 | 56/0 |  | Missing start/end date (not expanded)
|  | Nan | 83.231 |  | TA419 | 57/0 |  | Missing start/end date (not expanded)
|  | Nan | 53.3239 |  | TA419 | 57/1 |  | Missing start/end date (not expanded)
|  | Nan | 38.8484 |  | TA419 | 58/0 |  | Missing start/end date (not expanded)
|  | Nan | 38.8484 |  | TA419 | 59/0 |  | Missing start/end date (not expanded)
|  | Nan | 43.7757 |  | TA419 | 59/1 |  | Missing start/end date (not expanded)
|  | Nan | 78.6863 |  | TA419 | 60/0 |  | Missing start/end date (not expanded)
|  | Nan | 78.6863 |  | TA419 | 61/0 |  | Missing start/end date (not expanded)
|  | Nan | 43.7757 |  | TA419 | 61/1 |  | Missing start/end date (not expanded)
|  | Nan | 73.4258 |  | TA419 | 62/0 |  | Missing start/end date (not expanded)
2025-11-15 |  | Rohit | 53.3239 |  | TA419 | 62/1 | WIP | Missing start/end date (not expanded)
|  | Nan | 53.3239 |  | TA419 | 62/2 |  | Missing start/end date (not expanded)
|  | Nan | 75.9057 |  | TA419 | 62/3 |  | Missing start/end date (not expanded)
|  | Nan | 42.3742 |  | TA419 | 62/4 |  | Missing start/end date (not expanded)
|  | Nan | 55.3387 |  | TA419 | 62/5 |  | Missing start/end date (not expanded)
|  | Nan | 64.4822 |  | TA419 | 63/0 |  | Missing start/end date (not expanded)
|  | Nan | 43.7757 |  | TA419 | 63/1 |  | Missing start/end date (not expanded)
|  | Nan | 43.7757 |  | TA419 | 63/2 |  | Missing start/end date (not expanded)
|  | Nan | 43.7757 |  | TA419 | 63/3 |  | Missing start/end date (not expanded)
|  | Nan | 42.3742 |  | TA419 | 63/4 |  | Missing start/end date (not expanded)
|  | Nan | 42.3742 |  | TA419 | 63/5 |  | Missing start/end date (not expanded)
|  | Nan | 43.7757 |  | TA419 | 63/6 |  | Missing start/end date (not expanded)
|  | Nan | 86.2562 |  | TA419 | 63A/0 |  | Missing start/end date (not expanded)
|  | Nan | 86.2562 |  | TA419 | 63B/0 |  | Missing start/end date (not expanded)
|  | Nan | 43.7757 |  | TA419 | 63B/1 |  | Missing start/end date (not expanded)
|  | Nan | 53.3239 |  | TA419 | 63B/2 |  | Missing start/end date (not expanded)
|  | Nan | 42.3742 |  | TA419 | 63B/3 |  | Missing start/end date (not expanded)
|  | Nan | 43.7757 |  | TA419 | 63B/4 |  | Missing start/end date (not expanded)
|  | Nan | 42.3742 |  | TA419 | 63B/5 |  | Missing start/end date (not expanded)
|  | Nan | 46.0492 |  | TA419 | 63B/6 |  | Missing start/end date (not expanded)
|  | Nan | 75.9057 |  | TA419 | 64/0 |  | Missing start/end date (not expanded)
|  | Nan | 42.3742 |  | TA419 | 64/1 |  | Missing start/end date (not expanded)
|  | Nan | 78.6863 |  | TA419 | 64/2 |  | Missing start/end date (not expanded)
|  | Nan | 55.3387 |  | TA419 | 64/3 |  | Missing start/end date (not expanded)
|  | Nan | 53.3239 |  | TA419 | 64/4 |  | Missing start/end date (not expanded)
|  | Nan | 43.7757 |  | TA419 | 64/5 |  | Missing start/end date (not expanded)
|  | Nan | 90.1252 |  | TA419 | 64A/0 |  | Missing start/end date (not expanded)
|  | Nan | 113.6796 |  | TA419 | 65/0 |  | Missing start/end date (not expanded)
|  | Nan | 42.3742 |  | TA419 | 65/1 |  | Missing start/end date (not expanded)
|  | Nan | 53.3239 |  | TA419 | 65/2 |  | Missing start/end date (not expanded)
|  | Nan | 73.4258 |  | TA419 | 66/0 |  | Missing start/end date (not expanded)
|  | Nan | 55.3387 |  | TA419 | 66/1 |  | Missing start/end date (not expanded)
|  | Nan | 90.1252 |  | TA419 | 67/0 |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA419 | 68/0 |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA419 | 69/0 |  | Missing start/end date (not expanded)
|  | Nan | 104.8666 |  | TA419 | 70/0 |  | Missing start/end date (not expanded)
|  | Nan | 143.4621 |  | TA419 | 71/0 |  | Missing start/end date (not expanded)
|  | Nan | 118.4303 |  | TA419 | 72/0 |  | Missing start/end date (not expanded)
|  | Nan | 73.4258 |  | TA419 | 73/0 |  | Missing start/end date (not expanded)
|  | Nan | 97.2286 |  | TA419 | 74/0 |  | Missing start/end date (not expanded)
|  | Nan | 143.4621 |  | TA419 | 75/0 |  | Missing start/end date (not expanded)
|  | Nan | 118.4303 |  | TA419 | 76/0 |  | Missing start/end date (not expanded)
|  | Nan | 43.7757 |  | TA419 | 76/1 |  | Missing start/end date (not expanded)
|  | Nan | 46.0492 |  | TA419 | 76/2 |  | Missing start/end date (not expanded)
2025-11-19 |  | Ganesh Construction | 46.0492 |  | TA419 | 76/3 | WIP | Missing start/end date (not expanded)
|  | Nan | 73.4258 |  | TA419 | 77/0 |  | Missing start/end date (not expanded)
|  | Nan | 67.112 |  | TA419 | 78/0 |  | Missing start/end date (not expanded)
|  | Nan | 43.7757 |  | TA419 | 78/1 |  | Missing start/end date (not expanded)
|  | Nan | 46.0492 |  | TA419 | 78/2 |  | Missing start/end date (not expanded)
|  | Nan | 43.7757 |  | TA419 | 78/3 |  | Missing start/end date (not expanded)
|  | Nan | 46.0492 |  | TA419 | 78/4 |  | Missing start/end date (not expanded)
|  | Nan | 75.9057 |  | TA419 | 78A/0 |  | Missing start/end date (not expanded)
|  | Nan | 89.7178 |  | TA419 | 79/0 |  | Missing start/end date (not expanded)
|  | Nan | 93.2387 |  | TA419 | 80/0 |  | Missing start/end date (not expanded)
|  | Nan | 90.1252 |  | TA419 | 81/0 |  | Missing start/end date (not expanded)
|  | Nan | 104.8666 |  | TA419 | 82/0 |  | Missing start/end date (not expanded)
|  | Nan | 90.1252 |  | TA419 | 83/0 |  | Missing start/end date (not expanded)
|  | Nan | 55.3387 |  | TA419 | 83/1 |  | Missing start/end date (not expanded)
|  | Nan | 46.0492 |  | TA419 | 83/2 |  | Missing start/end date (not expanded)
|  | Nan | 55.3387 |  | TA419 | 83/3 |  | Missing start/end date (not expanded)
|  | Nan | 42.3742 |  | TA419 | 83/4 |  | Missing start/end date (not expanded)
|  | Nan | 42.3742 |  | TA419 | 83/5 |  | Missing start/end date (not expanded)
|  | Nan | 42.3742 |  | TA419 | 83/6 |  | Missing start/end date (not expanded)
2025-11-19 |  | Amit Yadav | 43.7757 |  | TA419 | 83/7 | WIP | Missing start/end date (not expanded)
|  | Nan | 42.3742 |  | TA419 | 83/8 |  | Missing start/end date (not expanded)
|  | Nan | 46.0492 |  | TA419 | 83/9 |  | Missing start/end date (not expanded)
|  | Nan | 73.4258 |  | TA419 | 84/0 |  | Missing start/end date (not expanded)
|  | Nan | 43.7757 |  | TA419 | 84/1 |  | Missing start/end date (not expanded)
|  | Nan | 46.0492 |  | TA419 | 84/2 |  | Missing start/end date (not expanded)
|  | Nan | 42.3742 |  | TA419 | 84/3 |  | Missing start/end date (not expanded)
|  | Nan | 42.3742 |  | TA419 | 84/4 |  | Missing start/end date (not expanded)
|  | Nan | 43.7757 |  | TA419 | 84/5 |  | Missing start/end date (not expanded)
|  | Nan | 64.4822 |  | TA419 | 84A/0 |  | Missing start/end date (not expanded)
|  | Nan | 46.0492 |  | TA419 | 84A/1 |  | Missing start/end date (not expanded)
|  | Nan | 73.4258 |  | TA419 | 85/0 |  | Missing start/end date (not expanded)
|  | Nan | 113.6796 |  | TA419 | 85A/0 |  | Missing start/end date (not expanded)
|  | Nan | 38.8484 |  | TA419 | 86/0 |  | Missing start/end date (not expanded)
|  | Nan | 53.3239 |  | TA419 | 86/1 |  | Missing start/end date (not expanded)
|  | Nan | 46.0492 |  | TA419 | 86/2 |  | Missing start/end date (not expanded)
|  | Nan | 97.2286 |  | TA419 | 86A/0 |  | Missing start/end date (not expanded)
|  | Nan | 53.3239 |  | TA419 | 86A/1 |  | Missing start/end date (not expanded)
|  | Nan | 55.3387 |  | TA419 | 86A/2 |  | Missing start/end date (not expanded)
|  | Nan | 46.0492 |  | TA419 | 86A/3 |  | Missing start/end date (not expanded)
|  | Nan | 67.112 |  | TA419 | 86A/4 |  | Missing start/end date (not expanded)
|  | Nan | 55.3387 |  | TA419 | 86A/5 |  | Missing start/end date (not expanded)
|  | Nan | 64.4822 |  | TA419 | 87/0 |  | Missing start/end date (not expanded)
|  | Nan | 46.0492 |  | TA419 | 87/1 |  | Missing start/end date (not expanded)
|  | Nan | 43.7757 |  | TA419 | 87/2 |  | Missing start/end date (not expanded)
|  | Nan | 64.4822 |  | TA419 | 88/0 |  | Missing start/end date (not expanded)
|  | Nan | 42.3742 |  | TA419 | 88/1 |  | Missing start/end date (not expanded)
|  | Nan | 46.0492 |  | TA419 | 88/2 |  | Missing start/end date (not expanded)
|  | Nan | 73.4258 |  | TA419 | 89/0 |  | Missing start/end date (not expanded)
|  | Nan | 97.2286 |  | TA419 | 90/0 |  | Missing start/end date (not expanded)
|  | Nan | 73.4258 |  | TA419 | 90A/0 |  | Missing start/end date (not expanded)
|  | Nan | 42.3742 |  | TA419 | 90A/1 |  | Missing start/end date (not expanded)
|  | Nan | 97.2286 |  | TA419 | 90B/0 |  | Missing start/end date (not expanded)
|  | Nan | 78.0732 |  | TA419 | 91/0 |  | Missing start/end date (not expanded)
|  | Nan | 86.2562 |  | TA419 | 92/0 |  | Missing start/end date (not expanded)
|  | Nan | 73.4258 |  | TA419 | 93/0 |  | Missing start/end date (not expanded)
|  | Nan | 86.2562 |  | TA419 | 93A/0 |  | Missing start/end date (not expanded)
|  | Nan | 97.2286 |  | TA419 | 93B/0 |  | Missing start/end date (not expanded)
|  | Nan | 83.231 |  | TA419 | 93C/0 |  | Missing start/end date (not expanded)
|  | Nan | 104.8666 |  | TA419 | 94/0 |  | Missing start/end date (not expanded)
|  | Nan | 110.6958 |  | TA419 | 95/0 |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA419 | 95A/0 |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA419 | 96/0 |  | Missing start/end date (not expanded)
|  | Nan | 64.4822 |  | TA419 | 96/1 |  | Missing start/end date (not expanded)
|  | Nan | 55.3387 |  | TA419 | 96/2 |  | Missing start/end date (not expanded)
|  | Nan | 90.1252 |  | TA419 | 97/0 |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA419 | 98/0 |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA419 | 99/0 |  | Missing start/end date (not expanded)
|  | Nan | 113.6796 |  | TA419 | 100/0 |  | Missing start/end date (not expanded)
|  | Nan | 97.2286 |  | TA419 | 101/0 |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA419 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA419 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA419 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA419 |  | ` | Missing start/end date (not expanded)
|  | Nan | 8617.0894 |  | TA505 |  | 179 | Missing start/end date (not expanded)
2025-11-09 |  | Paramanand 1 | 43.8044 |  | TA505 | 164/5 | In-Progress | Missing start/end date (not expanded)
2025-11-11 |  | Toshan Mahato | 124.95 |  | TA505 | 145/0 | In-Progress | Missing start/end date (not expanded)
2025-11-12 |  | Jyoti Const | 43.8044 |  | TA505 | 149B/2 | In-Progress | Missing start/end date (not expanded)
2025-11-18 |  | Crane Erc Team Mp | 36.1598 |  | TA505 | 172/3 | In-Progress | Missing start/end date (not expanded)
2025-11-19 |  | Jwala Singh | 73.245 |  | TA505 | 100/0 | In-Progress | Missing start/end date (not expanded)
2025-11-21 |  | Deglal Mahato Mp | 36.1598 |  | TA505 | 170/1 | In-Progress | Missing start/end date (not expanded)
2025-11-23 |  | Jhemon Mahato 2 | 37.931 |  | TA505 | 136/2 | In-Progress | Missing start/end date (not expanded)
2025-11-23 |  | Shila Devi | 35.602 |  | TA505 | 130/2 | In-Progress | Missing start/end date (not expanded)
2025-11-24 |  | Prayag Shah Mp | 36.1598 |  | TA505 | 174A/2 | In-Progress | Missing start/end date (not expanded)
2025-11-25 |  | Pankaj Singh Mp | 34.79 |  | TA505 | 166/6 | In-Progress | Missing start/end date (not expanded)
2025-11-25 |  | Jagannaath Saw Mp | 43.8044 |  | TA505 | 164/8 | In-Progress | Missing start/end date (not expanded)
2025-11-25 |  | Deglal Mahato | 37.931 |  | TA505 | 103/5 | In-Progress | Missing start/end date (not expanded)
|  | Nan | 8617.0894 |  | TA505 |  | 179 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA506 |  |  | Missing start/end date (not expanded)
| 2025-09-14 | Jawala Singh | 36.15 |  | TA509 | 8/6 | COMPLETED | Missing start/end date (not expanded)
2025-10-26 | 2025-02-11 | Devi Const | 36.15 |  | TA509 | 9/2 | COMPLETED | Non-positive duration (Start > End or 0) (not expanded)
|  | Nan |  |  | TB408 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB408 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB408 |  |  | Missing start/end date (not expanded)
|  | Gang Name |  |  | TB408 |  | Erection Method | Missing start/end date (not expanded)
2025-11-14 |  | Ganesh Sinha |  |  | TB408 |  | Derrick | Missing start/end date (not expanded)
2025-11-22 |  | Vinay Construction |  |  | TB408 |  | Derrick | Missing start/end date (not expanded)
2025-11-22 |  | Sanjeev Kumar |  |  | TB408 |  | Derrick | Missing start/end date (not expanded)
2025-11-19 |  | Devi Construction |  |  | TB408 |  | Derrick | Missing start/end date (not expanded)
2025-11-17 |  | Kamlesh Kumar |  |  | TB408 |  | Derrick | Missing start/end date (not expanded)
2025-11-23 |  | Shobha Devi |  |  | TB408 |  | Derrick | Missing start/end date (not expanded)
2025-11-18 |  | Jirwa Devi |  |  | TB408 |  | Derrick | Missing start/end date (not expanded)
2025-11-08 |  | Dular Chand |  |  | TB408 |  | Derrick | Missing start/end date (not expanded)
2025-11-10 |  | Priyanka Devi |  |  | TB408 |  | Derrick | Missing start/end date (not expanded)
2025-11-21 |  | Chinta Devi |  |  | TB408 |  | Derrick | Missing start/end date (not expanded)
2025-11-23 |  | Panva Devi |  |  | TB408 |  | Derrick | Missing start/end date (not expanded)
2025-10-18 |  | Namechand Mahto |  |  | TB507 | 104B/2 | Strong ROW. Landowner stopped work not allowing to enter at location and Tower material left without watchmen. | Missing start/end date (not expanded)
2025-11-06 |  | Namechand Mahto | 18.727 |  | TB507 | 98/0 | WIP | Missing start/end date (not expanded)
2025-11-03 |  | Dipak |  |  | TB507 | 111/0 | WIP | Missing start/end date (not expanded)
2025-11-01 |  | Gokul Sarkar |  |  | TB507 | 152/0 | WIP | Missing start/end date (not expanded)
2025-11-06 |  | Prayag Saw 2 |  |  | TB507 | 137/0 | WIP | Missing start/end date (not expanded)
2025-11-08 |  | Windbridge Energy |  |  | TB507 | 132/4 | WIP | Missing start/end date (not expanded)
2025-11-09 |  | Chandra Sekhar |  |  | TB507 | 129/0 | WIP | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB507 |  |  | Missing start/end date (not expanded)
2025-10-13 | 2012-10-18 | Dipak | 18.727 |  | TB507 | 110/0 | Completed | Non-positive duration (Start > End or 0) (not expanded)

## Issues
file | issue
TA 413 - DPR - 2025-11-23.xlsx | XML scrub fallback used for sheet 'Project Details'
TA 413 - DPR - 2025-11-23.xlsx | XML scrub fallback used for sheet 'Erection Compiled'
TA 504 - DPR - 2025-11-23.xlsx | XML scrub fallback used for sheet 'Project Details'
TA 504 - DPR - 2025-11-23.xlsx | XML scrub fallback used for sheet 'Erection compiled'
TA 506 - DPR - 2025-11-23.xlsx | XML scrub fallback used for sheet 'Project Details'
TA 506 - DPR - 2025-11-23.xlsx | XML scrub fallback used for sheet 'Erection compiled'
TA 509 - DPR - 2025-11-20.xlsx | XML scrub fallback used for sheet 'Project Details'
TA 509 - DPR - 2025-11-20.xlsx | XML scrub fallback used for sheet 'Erection Compiled '

## Diagnostics
file | project | sheet | detected_header_row | columns_detected
TA 325 - DPR - 2025-11-24.xlsx | TA325 | Erection-Compiled | 0 | sl no, location no, type, type of tower, starting date, revenue, tower weight, status, completion date, gang name, no, district, remarks, ageing
TA 413 - DPR - 2025-11-23.xlsx | TA413 | Erection Compiled | 3 | cumm sr no, month sr no, location no, type of tower, starting date, completion date, gang name, tower weight, revenue, name of supervisor, status, prop name
TA 416 - DPR - 2025-11-23.xlsx | TA416 | Erection Compiled | 0 | sl no, location no, tower type, classification, starting date, tower weight, status, nan, nan, nan, completion date, gang name, gang strength, remark, nan, nan, 1 0, 2 0, 3 0, 4 0
TA 418 - DPR - 2025-11-24.xlsx | TA418 | Erection Compiled | 1 | sl no, location no, tower type, classification, starting date, tower weight, status, nan, nan, nan, completion date, gang name, gang strength, remark
TA 419 - DPR - 2025-11-21.xlsx | TA419 | ERECTION COMPILED | 1 | s no, location no, tower type, tower weight, starting date, completion date, gang name, status, remarks, offered for tower checking, report status, ra bill no, revenue in cr
TA 421 - DPR - 2025-11-18.xlsx | TA421 | Erection Compiled | 1 | sl no, location no, tower type, classification, starting date, tower weight, status, completion date, gang name, gang strength
TA 504 - DPR - 2025-11-23.xlsx | TA504 | Erection compiled | 3 | cumm sr no, month sr no, location no, type of tower, starting date, completion date, gang name, tower weight, revenue, name of supervisor, status, prop name
TA 505 - DPR - 2025-11-24.xlsx | TA505 | Erection Compiled | 3 | nan, sr no, location no, tower type, tower weight, rev inr, month of execution, gang name, status, starting date, completion date, no of compl days, region, remarks
TA 506 - DPR - 2025-11-23.xlsx | TA506 | Erection compiled | 3 | cumm sr no, month sr no, location no, type of tower, starting date, completion date, gang name, tower weight, revenue, name of supervisor, status, prop name
TA 509 - DPR - 2025-11-20.xlsx | TA509 | Erection Compiled | 0 | sl no, location no, tower type, classification, starting date, tower weight, status, nan, nan, nan, completion date, gang name, gang strength, remark, nan, nan, 1 0, 2 0, 3 0, 4 0
TB 408 - DPR - 2025-11-23.xlsx | TB408 | Erection Compiled | 3 | sl no, month sl no, location no, tower type, classification, starting date, completion date, gang name, gang strength, tower weight, status, nan, nan, nan, nan, nan, nan, nan, nan, nan
TB 507 - DPR - 2025-11-09.xlsx | TB507 | Erection Compiled | 4 | sl no, location no, tower type, tower weight, gang name, starting date, completion date, status, nan, nan, nan, nan, nan, nan, nan, nan, nan, nan, nan, nan

## ProjectDetails
project_code | project_name | client_name | noa_start | loa_end | project_mgr | regional_mgr | planning_eng | pch | section_inch | supervisor | _source_file | Project Name
TA 325 | 765 KV D/C Hexa Ahmedabad - Navsari Transmission Line | PGCIL | 2023-03-23 | 2024-12-22 | Mr. Sanjeev Garg | Mr. Nitin Bendale | Mr. Janvendra Kumar | Mr. Arun Felbin | Mithun Samui, Milan Mal, Gurveet Singh, Bibhu Kalyan Das, Sanjeet Singh, Ranjeet Kumar Singh | Sandeep Kumar, Laxman Prasad Nayak, Abdul Matin, Khemlal Mahto, Bibek Kumar Choubey, Birkha Bahadur, Ramchandra Prasad, Tapan Sarkar, Ajay Kumar Mahto, Mohan Kumar, Dularchand Kumar, Sushanta Rajbanshi, Anil Kumar. G, Deo Prakash, Vikas Bishnoi, Rajesh Kumar, Mukesh Kumar Mahto, Mohit Kumar Mahto, Kalicharan Patel, Nageshwar Mahto, Madan Malik, Rakesh Kumar Thakur, Jagarnath Kumar Mahto, Ravi Kumar, Pramod Singh, Atul Kumar, Jitendra Kumar, Vikash Sharma, Abbu Alam, Rejaul Hoque, Pankaj Kumar Mahto, Nageshwar Kumar Mahto, Baleshwar Kumar, Manoj Kumar Mahto, Jagdeo Mahto, Lalmohan Mahto, Rewatlal Mahto, Yugal Kishor, Dhiraj Mahto, Govind Mahto, Dularchand Mahto, Amit Kumar Shrivastava, Nunuchand Mahto, Aman Yadav, Ruplal Mahto, Amit Kumar, Mukul Singh, Ramlagan Prasad | TA 325 - DPR - 2025-11-24.xlsx | TA325
TA 413 | 765kv D/C Bikaner II to Neemrana II TL-02 | PGCIL | 2024-03-12 | 2025-12-11 | Mr. Anil Kumar Sharma | Mr. Tushar Grover | Mr. Santosh Mishra | Mr. Sanjay Gupta | Surendra Kumar Patel, Kartik Jhorar, Shuvam Gupta, Govind Bhardwaj | Rudra Prasad, Aman Kumar Singh, Manoj Gupta, Raju Mahto, Khublal Mahto, Sushil Kumar, Haridashn, Manoj Kumar chaudhary, Nabirul Islam, Sanjay Kumar, Rahul Ravidas, Narayan Mahto, Kamal Ravidas, Manirul Islam, Tarique Anwar, Raju Prasad, Abhay Ojha | TA 413 - DPR - 2025-11-23.xlsx | TA413
TA 416 | 765KV D/C HEXA NEEMRANA II BAREILLY TL -03 | PGCIL | 2024-02-07 | 2025-11-06 | Mr Sanjay Gupta | Mr Rajiv Sharma | Sanjib Samantaray | Mr Arun Felbin | Prabin Patra, Shikhar Pratap | Rupesh, Bijendra, Rahman, Sitaram, Churamani, Saidur, Madhusudan, Ritlal, Somenath, Aflaudin, Akhtarul | TA 416 - DPR - 2025-11-23.xlsx | TA416
TA 418 | 765KV D/C KOPPAL II(PS) - RAICHUR TL (Part-1) | PGCIL | 2024-12-03 | 2025-11-12 | Mr. Tamil Velan | Mr. Ajith Kumar MG | Mr. Ajith Jayasurya | Mr. Arun Felbin | Not Available, Mr. Ajith Jayasurya | Prathab DK, Subha Parui, Prabhu Prasad, Ashok Prasad, Basudev Mahato, Ajay Kumar, Rahman, Jitender, Durai swamy, Umesh Kumar, Vennilavan | TA 418 - DPR - 2025-11-24.xlsx | TA418
TA-419 | 765 KV D/C Sikar II - Narela TL02 | Power Grid Corporation of India | 2024-02-06 | 2025-05-05 | Mr. Shashi Bhusan | Mr. Tushar Grover | Mr.Suraj Chaudhary | Mr. Sanjay Gupta | Mr. Tanay Kumar, Mr.Ravindra nath Tyagi | Mr.Shivam Som, Mr. Satyaprakash, Mr. Sunil Kumar Shetty, Mr. Yogendra Singh, Mr. PD Sharma, Mr. Bishswar Behera, Mr. Suresh Ram, Mr. Manoj Yadav, Mr. Shivbrat Kumar, Mr. Gagandeep, Mr. Pramod, Mr. Arjun Singh, Mr. Chetram Sharma, Mr. Dasrath Mahato | TA 419 - DPR - 2025-11-21.xlsx | TA419
TA 421 | 765KV D/C HEXA BIDAR PS - MAHESHWARAM (PG) TL | Power Grid Bidar | 2024-02-15 | 2025-11-14 | Mr. Appala Naidu | Mr. Ajith Kumar | Mr. Bharath A D | Mr.Arun Felbin | Mr.Manikandan, Mr. Satyam Tiwari | Mr. Ramasish, Mr. Godvin John, Mr. Karunakar Nayak, Mr. Sudalaimuthu, Mr. Susanthpal, Mr. Srinivasan, Mr. Bhim Mahto, Mr. Ganesan, Mr. Ballu Thakur, Mr. Chandrasekar, Mr.Chandrasekharan, Mr. Anand | TA 421 - DPR - 2025-11-18.xlsx | TA421
TA 504 | 765 KV D/C Rishabdeo - Mandsaur & Lilo | PGCIL | 2024-07-15 | 2026-06-14 | Mr. Rajiv Sharma | Mr. Vijay Kute | Mr. Abir Kumar Das | Mr. Arun Felbin | Prasant Kumar | Khemchand, Ashutosh Prakash, Teklal Mahto, Rameswar Mahto, Rajesh Singh | TA 504 - DPR - 2025-11-23.xlsx | TA504
TA 505 | 765 Kv D/C Beawar-Mandsaur T/L | PBMTL | 2024-07-22 | 2026-06-21 | Mr. Sushil Kr Tiwari | Mr. Vijay Kute | Mr. Partha Pratim Pal | Mr. Arun Felbin | Mr.Deepak Anand, Mr.Bapan Mandal, Mr.Panneri Satish | Nunuchand Mahto, Birkha Subba, Dilip Kumar, Teklal Mahato, Munid Meena, Mortuj Ali, Devdas Malik, Jayprakash Nishad, Kumar Singh, K. Sanjeevan, Mridul Baruah, Binda Shah, Prasanta Sahana, Lalit Sahoo, Sujit Roy, Ramprasad, Gourshankar, Vipin Mall, Aadesh | TA 505 - DPR - 2025-11-24.xlsx | TA505
TA 506 | 400 KV D/C Sirohi - Chittorgarh Line | PGCIL | 2024-07-23 | 2026-06-22 | Mr. Rajiv Sharma | Mr. Vijay Kute | Mr. Abir Kumar Das | Mr. Arun Felbin | Dharmendra Pandey, Rajkumar Tomar, Rajib Biswas, Abhishek Kumar | Anil Kumar, Bipattaran Dolui, Sahadeo Gope, Sunil Kumar, Mrityunjay Thakur, Bhola Karmakat | TA 506 - DPR - 2025-11-23.xlsx | TA506
TA 509 | 765KV D/C MANDSAUR-KURAWAR(PART-1) TRANSMISSION LINE(WZ-4) | PGCIL | 2025-11-26 | 2026-10-26 | Mr Prithviraj | Mr Vijay Kute | Pawan Sharma | Mr Arun Felbin | Prasanta Das, Himanshu Yadav | Faljeet kumar, Abhishek Yadav, Manjur Alam, Abhishek Mishra, Teklal Mahato, Manoj Kumar Mahato, Bendict Lakra, Shashi Paswan, Sunil Chauhan, Dhamender Singh | TA 509 - DPR - 2025-11-20.xlsx | TA509
TB408 | 765 KV Beawer Transmission Line, PKG F | Resonia Limited | 2023-12-06 | 2025-10-30 | Mr. Partha Pal | Mr. Sandeep Singh Kumar | Mr. Raghav Ranjan | Mr. Sanjay Kumar Gupta | Sumit Kumar, Vivek Shukla, Vivek Kumar, Vijay Yadav, Ram Tirath Singh | Pradeep Kumar, Vikas Kumar, Ganesh Singh, Dineshwar Mahto, Kamla Pal Prasad, Bisun Saw, Shakib Hussain, Umesh Prasad, Prince Kumar Nirala, Pramod Kumar Sahoo, Jainath Mahto, Rajesh Pal, Ramji Tanti, Rakesh Pramanik, Sam Mahammad, Suresh Kumar Pal, Hulas Kumar Mahto, Akash Dadarao Thul, Vaibhav Sharma, Dasharath Mahto, Mukesh Kumar, Dashrath Mahto, Kartik Mahato, Gangadin Sahu, Dev Narayan Mahto, Ashok Kumar, Debananda Ray, Dev Prakash, Jai Lal Mahto, Jitendra Kumar, Deo Prakash, Tribhuwan Mahto, Umesh Kumar Mahto, Rahul Sharma, Karan Pal Singh, Pritish Kumar Pradhan, Akshay Lal, Laxman, Jaylal Mahto | TB 408 - DPR - 2025-11-23.xlsx | TB408
TB 507 | 400kV D/C Fatehgarh IV (Section-2)PS - Bhinmal (PG) Transmission Line | RAJASTHAN IV A POWER TRANSMISSION LTD | 2024-12-06 | 2026-06-05 | ALOK SINHA |  | Amartya sarkar | Sanjay Kr Gupta | ALOK JANA, VARUN TYAGI |  | TB 507 - DPR - 2025-11-09.xlsx | TB507

## README_Assumptions
Notes
Assumptions & Cleaning Rules:
- Start date cutoff: rows with Start Date before 2021-01-01 are not expanded and logged in 'Data Issues'.
- Completion date must be before 2025-11-25 (future completions go to 'Data Issues').
- Tower Weight range: only [10, 200] MT is considered valid for expansion; out-of-range rows go to 'Data Issues'.
- Missing or non-positive durations (Start/End missing or Start > End or 0) are logged to 'Data Issues' and not expanded.
- Gang name normalization: remove special characters (digits kept), Title Case words, and insert a space before trailing digits (e.g., 'xyz4' â†’ 'Xyz 4').
- Sheets:
â€¢ ProdDailyExpanded : per-day expanded rows used by the dashboard
â€¢ ProdDailyExpandedSingles : per-day expanded rows including single-occurrence gangs
â€¢ RawData : per-erection rows (unexpanded), for traceability
â€¢ Data Issues : row-level data problems (reason in 'Issues' column)
â€¢ Issues : file-level problems (missing sheet/headers, read/open errors, etc.)
â€¢ Diagnostics : which sheet used, detected header row, and normalized header text
- Dashboard note: a 15-day productivity loss cap is used in downstream analytics.

## MicroPlanResponsibilities
project_key | project_name | plan_month | entity_type | entity_name | location_no | revenue_planned | revenue_realised | tower_weight | tower_type | manpower | power_tools_issued | material_feeding | starting_date | completion_date | tack_welding | final_checking
ta325 | TA325 | 2025-11-01 | Gang | Dhaneshwar Mahto | 102/0 | 1182783 | 0 | 156.8261 | DD45+35 | 45 | Yes | Yes | 2025-10-19 | 2025-11-01 | 2025-11-21 | 2025-11-20
ta325 | TA325 | 2025-11-01 | Gang | Prayag Mahto | 154/1 | 934927 | 0 | 122.8048 | DD45+25 | 53 | Yes | Yes | 2025-10-29 | 2025-11-01 | 2025-11-18 | 2025-11-17
ta325 | TA325 | 2025-11-01 | Gang | Modina India-1&4 (PGCIL) | 159/2 | 470077 | 0 | 101.852 | DCT+0 | 55 | Yes | Yes | 2025-11-04 | 2025-11-01 | 2025-11-22 | 2025-11-21
ta325 | TA325 | 2025-11-01 | Gang | Dildar Electrical-2 & 3 PGCIL | 160/0 | 1003256 | 0 | 129.341 | DD60+18 | 58 | Yes | Yes | 2025-10-29 | 2025-11-01 | 2025-11-18 | 2025-11-17
ta325 | TA325 | 2025-11-01 | Gang | New Gang 4 | 165/4 | 680590 | 0 | 89.1428 | DD45+9 |  | Yes | Yes | 2025-11-08 | 2025-11-01 | 2025-11-25 | 2025-11-24
ta325 | TA325 | 2025-11-01 | Gang | New Gang 5 | 165/5 | 680590 | 0 | 89.1428 | DD45+9 |  | Yes | Yes | 2025-11-08 | 2025-11-01 | 2025-11-25 | 2025-11-24
ta325 | TA325 | 2025-11-01 | Gang | Aamir Khan | 166/0 | 719574 | 0 | 94.4077 | DD60+6 | 19 | Yes | Yes | 2025-11-05 | 2025-11-01 | 2025-11-26 | 2025-11-25
ta325 | TA325 | 2025-11-01 | Gang | Anjum | 167/0 | 719574 | 0 | 94.4077 | DD60+6 |  | Yes | Yes | 2025-11-08 | 2025-11-01 | 2025-11-26 | 2025-11-25
ta325 | TA325 | 2025-11-01 | Gang | Sakila Khatun | 167/1 | 604881 | 0 | 80.408 | DD60+0 |  | Yes | Yes | 2025-11-12 | 2025-11-01 | 2025-11-30 | 2025-11-29
ta325 | TA325 | 2025-11-01 | Gang | Gokul Sarkar-1 | 172/1 | 297143 | 0 | 39.4589 | DA+3 |  | Yes | Yes | 2025-11-12 | 2025-11-01 | 2025-11-22 | 2025-11-21
ta325 | TA325 | 2025-11-01 | Gang | Muni Bibi- 1 & 2 | 173/0 | 1099828 | 0 | 142.1014 | DD60+25 |  | Yes | Yes | 2025-11-06 | 2025-11-01 | 2025-12-01 | 2025-11-30
ta325 | TA325 | 2025-11-01 | Gang | Muni Bibi 1 | 174/0 | 1003256 | 0 | 129.341 | DD60+18 |  | Yes | Yes | 2025-11-07 | 2025-11-01 | 2025-11-30 | 2025-11-29
ta325 | TA325 | 2025-11-01 | Gang | Imadul Haque | 175/1 | 286911 | 0 | 37.7305 | DA+0 |  | Yes | Yes | 2025-11-06 | 2025-11-01 | 2025-11-16 | 2025-11-15
ta325 | TA325 | 2025-11-01 | Gang | Dildar Electricals-1 (PGCIL) | 182A/0 | 650023 | 0 | 85.2305 | DD45+6 |  | Yes | Yes | 2025-11-08 | 2025-11-01 | 2025-11-25 | 2025-11-24
ta325 | TA325 | 2025-11-01 | Gang | Anita Devi | 183/0 | 1099828 | 0 | 142.1014 | DD60+25 | 47 | Yes | Yes | 2025-11-04 | 2025-11-01 | 2025-11-27 | 2025-11-26
ta325 | TA325 | 2025-11-01 | Gang | Jaman Mahto-1 (Ratna Devi) | 184/0 | 1099828 | 0 | 142.1014 | DD60+25 | 37 | Yes | Yes | 2025-10-19 | 2025-11-01 | 2025-11-17 | 2025-11-16
ta325 | TA325 | 2025-11-01 | Gang | Satish Kumar | 184/1 | 480757 | 0 | 63.509 | DB1+6 | 17 | Yes | Yes | 2025-10-29 | 2025-11-01 | 2025-11-11 | 2025-11-10
ta325 | TA325 | 2025-11-01 | Gang | Mithun Kumar | 185/0 | 470077 | 0 | 64.2536 | DC2+0 | 45 | Yes | Yes | 2025-11-03 | 2025-11-01 | 2025-11-14 | 2025-11-13
ta325 | TA325 | 2025-11-01 | Gang | New Gang 3 | 186/0 | 1294023 | 0 | 173.1266 | DD60+35 |  | Yes | Yes | 2025-11-09 | 2025-11-01 | 2025-12-08 | 2025-12-07
ta325 | TA325 | 2025-11-01 | Gang | Rupesh | 187/0 | 1099828 | 0 | 142.1014 | DD60+25 | 28 | Yes | Yes | 2025-11-04 | 2025-11-01 | 2025-11-17 | 2025-11-16
ta325 | TA325 | 2025-11-01 | Gang | New Gang 2 | 200/0 | 670636 | 0 | 82.2388 | DB2+18 |  | Yes | Yes | 2025-11-09 | 2025-11-01 | 2025-11-25 | 2025-11-24
ta325 | TA325 | 2025-11-01 | Gang | Satish Kumar | 201/0 | 780122 | 0 | 97.9334 | DC2+18 |  | Yes | Yes | 2025-11-09 | 2025-11-01 | 2025-11-27 | 2025-11-26
ta325 | TA325 | 2025-11-01 | Gang | SK Samiul | 201/1 | 753337 | 0 | 98.8356 | DD60+9 | 20 | Yes | Yes | 2025-11-04 | 2025-11-01 | 2025-11-25 | 2025-11-24
ta325 | TA325 | 2025-11-01 | Gang | Nasirudin | 202/0 | 1878263 | 0 | 226.737 | DD60+55 | 32 | Yes | Yes | 2025-10-18 | 2025-11-01 | 2025-11-23 | 2025-11-22
ta325 | TA325 | 2025-11-01 | Gang | Anjum | 203/1 | 719574 | 0 | 94.4077 | DD60+6 | 28 | Yes | Yes | 2025-10-26 | 2025-11-01 | 2025-11-10 | 2025-11-09
ta325 | TA325 | 2025-11-01 | Gang | Javir Hossen | 208/0 | 1099828 | 0 | 142.1014 | DD60+25 |  | Yes | Yes | 2025-11-06 | 2025-11-01 | 2025-11-29 | 2025-11-28
ta325 | TA325 | 2025-11-01 | Gang | Rahul Kumar | 209/1 | 297143 | 0 | 39.4589 | DA+3 | 18 | Yes | Yes | 2025-10-29 | 2025-11-01 | 2025-11-09 | 2025-11-08
ta325 | TA325 | 2025-11-01 | Gang | Jwala Singh | 211/0 | 503365 | 0 | 65.7565 | DB1+9 | 25 | Yes | Yes | 2025-10-23 | 2025-11-01 | 2025-11-08 | 2025-11-07
ta325 | TA325 | 2025-11-01 | Gang | Dildar Electrical-2 & 3 PGCIL | 211/2 | 286911 | 0 | 37.7305 | DA+0 |  | Yes | Yes | 2025-11-16 | 2025-11-01 | 2025-11-26 | 2025-11-25
ta325 | TA325 | 2025-11-01 | Gang | Jwala Singh | 211A/0 | 403998 | 0 | 54.4178 | DB2+0 |  | Yes | Yes | 2025-11-06 | 2025-11-01 | 2025-11-17 | 2025-11-16
ta325 | TA325 | 2025-11-01 | Gang | Nasirudin 2 | 211A/1 | 273608.9283 | 0 | 36.0448 | DA-3 |  | Yes | Yes | 2025-11-08 | 2025-11-01 | 2025-11-18 | 2025-11-17
ta325 | TA325 | 2025-11-01 | Gang | Chitra Construction | 211A/2 | 286911 | 0 | 37.7305 | DA+0 | 20 | Yes | Yes | 2025-11-04 | 2025-11-01 | 2025-11-15 | 2025-11-14
ta325 | TA325 | 2025-11-01 | Gang | Jaman Mahto-1 (Ratna Devi) | 212/0 | 573550 | 0 | 75.4524 | DD45+3 |  | Yes | Yes | 2025-11-15 | 2025-11-01 | 2025-11-30 | 2025-11-29
ta325 | TA325 | 2025-11-01 | Gang | Teklal Mahto | 213/0 | 635073 | 0 | 84.2993 | DD60+3 |  | Yes | Yes | 2025-11-08 | 2025-11-01 | 2025-11-25 | 2025-11-24
ta325 | TA325 | 2025-11-01 | Gang | Mithun Kumar | 213/1 | 286911 | 0 | 37.7305 | DA+0 |  | Yes | Yes | 2025-11-12 | 2025-11-01 | 2025-11-22 | 2025-11-21
ta325 | TA325 | 2025-11-01 | Gang | Enjamul Haque | 214/0 | 546238 | 0 | 72.2342 | DD45+0 | 18 | Yes | Yes | 2025-10-19 | 2025-11-01 | 2025-11-10 | 2025-11-09
ta325 | TA325 | 2025-11-01 | Gang | Modina India-3 (PGCIL) | 214/1 | 342192 | 0 | 44.7282 | DA+6 |  | Yes | Yes | 2025-11-10 | 2025-11-01 | 2025-11-20 | 2025-11-19
ta325 | TA325 | 2025-11-01 | Gang | Chitra Construction | 215/1 | 357181 | 0 | 46.6235 | DA+9 |  | Yes | Yes | 2025-11-13 | 2025-11-01 | 2025-11-23 | 2025-11-22
ta325 | TA325 | 2025-11-01 | Gang | Rahul Kumar | 216/0 | 676263.874 | 0 | 91.0829 | DB2+25 |  | Yes | Yes | 2025-11-07 | 2025-11-01 | 2025-11-25 | 2025-11-24
ta325 | TA325 | 2025-11-01 | Gang | Enjamul Haque | 217/0 | 994153 | 0 | 122.8048 | DD45+25 |  | Yes | Yes | 2025-11-08 | 2025-11-01 | 2025-12-01 | 2025-11-30
ta325 | TA325 | 2025-11-01 | Gang | Rupesh | 217A/0 | 424198 | 0 | 56.8632 | DB1+3 |  | Yes | Yes | 2025-11-15 | 2025-11-01 | 2025-11-27 | 2025-11-26
ta325 | TA325 | 2025-11-01 | Gang | Imadul Haque | 218/0 | 604881 | 0 | 80.408 | DD60+0 | 24 | Yes | Yes | 2025-10-14 | 2025-11-01 | 2025-11-08 | 2025-11-07
ta325 | TA325 | 2025-11-01 | Gang | Modina India-2 (PGCIL) | 218/1 | 297143 | 0 | 39.4589 | DA+3 | 30 | Yes | Yes | 2025-11-04 | 2025-11-01 | 2025-11-14 | 2025-11-13
ta325 | TA325 | 2025-11-01 | Gang | Raj Labour | 219/0 | 780122 | 0 | 97.9334 | DC2+18 | 27 | Yes | Yes | 2025-11-04 | 2025-11-01 | 2025-11-25 | 2025-11-24
ta325 | TA325 | 2025-11-01 | Gang | Gokul Sarkar-2 | 220/0 | 680590 | 0 | 89.1428 | DD45+9 | 29 | Yes | Yes | 2025-11-03 | 2025-11-01 | 2025-11-21 | 2025-11-20
ta325 | TA325 | 2025-11-01 | Gang | Gokul Sarkar-1 | 220/1 | 297143 | 0 | 39.4589 | DA+3 | 27 | Yes | Yes | 2025-11-04 | 2025-11-01 | 2025-11-14 | 2025-11-13
ta325 | TA325 | 2025-11-01 | Gang | MD Akhtar | 221/0 | 1003256 | 0 | 129.341 | DD60+18 |  | Yes | Yes | 2025-11-08 | 2025-11-01 | 2025-11-30 | 2025-11-29
ta325 | TA325 | 2025-11-01 | Gang | New Gang 1 | 222/0 | 1099828 | 0 | 142.1014 | DD60+25 |  | Yes | Yes | 2025-11-09 | 2025-11-01 | 2025-12-03 | 2025-12-02
ta325 | TA325 | 2025-11-01 | Gang | Teklal Mahto | 223/0 | 470077 | 0 | 64.2536 | DC1+0 | 24 | Yes | Yes | 2025-10-23 | 2025-11-01 | 2025-11-10 | 2025-11-09
ta325 | TA325 | 2025-11-01 | Gang | Modina India-2 (PGCIL) | 223/2 | 286911 | 0 | 37.7305 | DA+0 |  | Yes | Yes | 2025-11-12 | 2025-11-01 | 2025-11-22 | 2025-11-21
ta325 | TA325 | 2025-11-01 | Gang | Dildar Electricals-1 (PGCIL) | 223/3 | 286911 | 0 | 37.7305 | DA+0 | 30 | Yes | Yes | 2025-11-04 | 2025-11-01 | 2025-11-14 | 2025-11-13
ta325 | TA325 | 2025-11-01 | Gang | Subhash | 226/0 | 470077 | 0 | 64.2536 | DC2+0 | 26 | Yes | Yes | 2025-10-29 | 2025-11-01 | 2025-11-11 | 2025-11-10
ta325 | TA325 | 2025-11-01 | Gang | Muni Bibi- 1 & 2 | 227/0 | 480757 | 0 | 63.509 | DB1+6 | 56 | Yes | Yes | 2025-10-22 | 2025-11-01 | 2025-11-08 | 2025-11-07
ta325 | TA325 | 2025-11-01 | Gang | Sukruddin | 228/0 | 1099828 | 0 | 142.1014 | DD60+25 |  | Yes | Yes | 2025-11-07 | 2025-11-01 | 2025-12-02 | 2025-12-01
ta325 | TA325 | 2025-11-01 | Gang | MD Akhtar | 229/0 | 1003256 | 0 | 129.341 | DD60+18 | 36 | Yes | Yes | 2025-10-12 | 2025-11-01 | 2025-11-10 | 2025-11-09
ta325 | TA325 | 2025-11-01 | Gang | Nasirudin 2 | 229/1 | 480757 | 0 | 63.509 | DB1+6 | 28 | Yes | Yes | 2025-10-25 | 2025-11-01 | 2025-11-10 | 2025-11-09
ta325 | TA325 | 2025-11-01 | Gang | Modina India-3 (PGCIL) | 229/2 | 342192 | 0 | 44.7282 | DA+6 | 30 | Yes | Yes | 2025-11-02 | 2025-11-01 | 2025-11-12 | 2025-11-11
ta325 | TA325 | 2025-11-01 | Gang | Javir Hossen | 230/0 | 604881 | 0 | 80.408 | DD60+0 | 24 | Yes | Yes | 2025-10-09 | 2025-11-01 | 2025-11-08 | 2025-11-07
ta325 | TA325 | 2025-11-01 | Gang | Subhash | 239/0 | 1099828 | 0 | 142.1014 | DD60+25 |  | Yes | Yes | 2025-11-09 | 2025-11-01 | 2025-12-02 | 2025-12-01
ta325 | TA325 | 2025-11-01 | Gang | Sakila Khatun | 240/0 | 1099828 | 0 | 142.1014 | DD60+25 | 37 | Yes | Yes | 2025-10-22 | 2025-11-01 | 2025-11-14 | 2025-11-13
ta325 | TA325 | 2025-11-01 | Gang | Sukruddin | 245/0 | 546238 | 0 | 72.2342 | DD45+0 | 32 | Yes | Yes | 2025-10-24 | 2025-11-01 | 2025-11-09 | 2025-11-08
ta325 | TA325 | 2025-11-01 | Section Incharge | None | 102/0 | 1182783 | 0 | 156.8261 | DD45+35 | 45 | Yes | Yes | 2025-10-19 | 2025-11-01 | 2025-11-21 | 2025-11-20
ta325 | TA325 | 2025-11-01 | Section Incharge | Milan Mal | 154/1 | 934927 | 0 | 122.8048 | DD45+25 | 53 | Yes | Yes | 2025-10-29 | 2025-11-01 | 2025-11-18 | 2025-11-17
ta325 | TA325 | 2025-11-01 | Section Incharge | Milan Mal | 159/2 | 470077 | 0 | 101.852 | DCT+0 | 55 | Yes | Yes | 2025-11-04 | 2025-11-01 | 2025-11-22 | 2025-11-21
ta325 | TA325 | 2025-11-01 | Section Incharge | Milan Mal | 160/0 | 1003256 | 0 | 129.341 | DD60+18 | 58 | Yes | Yes | 2025-10-29 | 2025-11-01 | 2025-11-18 | 2025-11-17
ta325 | TA325 | 2025-11-01 | Section Incharge | Milan Mal | 165/4 | 680590 | 0 | 89.1428 | DD45+9 |  | Yes | Yes | 2025-11-08 | 2025-11-01 | 2025-11-25 | 2025-11-24
ta325 | TA325 | 2025-11-01 | Section Incharge | Milan Mal | 165/5 | 680590 | 0 | 89.1428 | DD45+9 |  | Yes | Yes | 2025-11-08 | 2025-11-01 | 2025-11-25 | 2025-11-24
ta325 | TA325 | 2025-11-01 | Section Incharge | Milan Mal | 166/0 | 719574 | 0 | 94.4077 | DD60+6 | 19 | Yes | Yes | 2025-11-05 | 2025-11-01 | 2025-11-26 | 2025-11-25
ta325 | TA325 | 2025-11-01 | Section Incharge | Milan Mal | 167/0 | 719574 | 0 | 94.4077 | DD60+6 |  | Yes | Yes | 2025-11-08 | 2025-11-01 | 2025-11-26 | 2025-11-25
ta325 | TA325 | 2025-11-01 | Section Incharge | Milan Mal | 167/1 | 604881 | 0 | 80.408 | DD60+0 |  | Yes | Yes | 2025-11-12 | 2025-11-01 | 2025-11-30 | 2025-11-29
ta325 | TA325 | 2025-11-01 | Section Incharge | Milan Mal | 172/1 | 297143 | 0 | 39.4589 | DA+3 |  | Yes | Yes | 2025-11-12 | 2025-11-01 | 2025-11-22 | 2025-11-21
ta325 | TA325 | 2025-11-01 | Section Incharge | Milan Mal | 173/0 | 1099828 | 0 | 142.1014 | DD60+25 |  | Yes | Yes | 2025-11-06 | 2025-11-01 | 2025-12-01 | 2025-11-30
ta325 | TA325 | 2025-11-01 | Section Incharge | Milan Mal | 174/0 | 1003256 | 0 | 129.341 | DD60+18 |  | Yes | Yes | 2025-11-07 | 2025-11-01 | 2025-11-30 | 2025-11-29
ta325 | TA325 | 2025-11-01 | Section Incharge | Milan Mal | 175/1 | 286911 | 0 | 37.7305 | DA+0 |  | Yes | Yes | 2025-11-06 | 2025-11-01 | 2025-11-16 | 2025-11-15
ta325 | TA325 | 2025-11-01 | Section Incharge | Milan Mal | 182A/0 | 650023 | 0 | 85.2305 | DD45+6 |  | Yes | Yes | 2025-11-08 | 2025-11-01 | 2025-11-25 | 2025-11-24
ta325 | TA325 | 2025-11-01 | Section Incharge | Milan Mal | 183/0 | 1099828 | 0 | 142.1014 | DD60+25 | 47 | Yes | Yes | 2025-11-04 | 2025-11-01 | 2025-11-27 | 2025-11-26
ta325 | TA325 | 2025-11-01 | Section Incharge | Milan Mal | 184/0 | 1099828 | 0 | 142.1014 | DD60+25 | 37 | Yes | Yes | 2025-10-19 | 2025-11-01 | 2025-11-17 | 2025-11-16
ta325 | TA325 | 2025-11-01 | Section Incharge | Milan Mal | 184/1 | 480757 | 0 | 63.509 | DB1+6 | 17 | Yes | Yes | 2025-10-29 | 2025-11-01 | 2025-11-11 | 2025-11-10
ta325 | TA325 | 2025-11-01 | Section Incharge | Milan Mal | 185/0 | 470077 | 0 | 64.2536 | DC2+0 | 45 | Yes | Yes | 2025-11-03 | 2025-11-01 | 2025-11-14 | 2025-11-13
ta325 | TA325 | 2025-11-01 | Section Incharge | Milan Mal | 186/0 | 1294023 | 0 | 173.1266 | DD60+35 |  | Yes | Yes | 2025-11-09 | 2025-11-01 | 2025-12-08 | 2025-12-07
ta325 | TA325 | 2025-11-01 | Section Incharge | Milan Mal | 187/0 | 1099828 | 0 | 142.1014 | DD60+25 | 28 | Yes | Yes | 2025-11-04 | 2025-11-01 | 2025-11-17 | 2025-11-16
ta325 | TA325 | 2025-11-01 | Section Incharge | Milan Mal | 200/0 | 670636 | 0 | 82.2388 | DB2+18 |  | Yes | Yes | 2025-11-09 | 2025-11-01 | 2025-11-25 | 2025-11-24
ta325 | TA325 | 2025-11-01 | Section Incharge | Milan Mal | 201/0 | 780122 | 0 | 97.9334 | DC2+18 |  | Yes | Yes | 2025-11-09 | 2025-11-01 | 2025-11-27 | 2025-11-26
ta325 | TA325 | 2025-11-01 | Section Incharge | Milan Mal | 201/1 | 753337 | 0 | 98.8356 | DD60+9 | 20 | Yes | Yes | 2025-11-04 | 2025-11-01 | 2025-11-25 | 2025-11-24
ta325 | TA325 | 2025-11-01 | Section Incharge | Milan Mal | 202/0 | 1878263 | 0 | 226.737 | DD60+55 | 32 | Yes | Yes | 2025-10-18 | 2025-11-01 | 2025-11-23 | 2025-11-22
ta325 | TA325 | 2025-11-01 | Section Incharge | Bibhu Kalyan Das | 203/1 | 719574 | 0 | 94.4077 | DD60+6 | 28 | Yes | Yes | 2025-10-26 | 2025-11-01 | 2025-11-10 | 2025-11-09
ta325 | TA325 | 2025-11-01 | Section Incharge | Bibhu Kalyan Das | 208/0 | 1099828 | 0 | 142.1014 | DD60+25 |  | Yes | Yes | 2025-11-06 | 2025-11-01 | 2025-11-29 | 2025-11-28
ta325 | TA325 | 2025-11-01 | Section Incharge | Bibhu Kalyan Das | 209/1 | 297143 | 0 | 39.4589 | DA+3 | 18 | Yes | Yes | 2025-10-29 | 2025-11-01 | 2025-11-09 | 2025-11-08
ta325 | TA325 | 2025-11-01 | Section Incharge | Bibhu Kalyan Das | 211/0 | 503365 | 0 | 65.7565 | DB1+9 | 25 | Yes | Yes | 2025-10-23 | 2025-11-01 | 2025-11-08 | 2025-11-07
ta325 | TA325 | 2025-11-01 | Section Incharge | Bibhu Kalyan Das | 211/2 | 286911 | 0 | 37.7305 | DA+0 |  | Yes | Yes | 2025-11-16 | 2025-11-01 | 2025-11-26 | 2025-11-25
ta325 | TA325 | 2025-11-01 | Section Incharge | Bibhu Kalyan Das | 211A/0 | 403998 | 0 | 54.4178 | DB2+0 |  | Yes | Yes | 2025-11-06 | 2025-11-01 | 2025-11-17 | 2025-11-16
ta325 | TA325 | 2025-11-01 | Section Incharge | Bibhu Kalyan Das | 211A/1 | 273608.9283 | 0 | 36.0448 | DA-3 |  | Yes | Yes | 2025-11-08 | 2025-11-01 | 2025-11-18 | 2025-11-17
ta325 | TA325 | 2025-11-01 | Section Incharge | Bibhu Kalyan Das | 211A/2 | 286911 | 0 | 37.7305 | DA+0 | 20 | Yes | Yes | 2025-11-04 | 2025-11-01 | 2025-11-15 | 2025-11-14
ta325 | TA325 | 2025-11-01 | Section Incharge | Bibhu Kalyan Das | 212/0 | 573550 | 0 | 75.4524 | DD45+3 |  | Yes | Yes | 2025-11-15 | 2025-11-01 | 2025-11-30 | 2025-11-29
ta325 | TA325 | 2025-11-01 | Section Incharge | Bibhu Kalyan Das | 213/0 | 635073 | 0 | 84.2993 | DD60+3 |  | Yes | Yes | 2025-11-08 | 2025-11-01 | 2025-11-25 | 2025-11-24
ta325 | TA325 | 2025-11-01 | Section Incharge | Bibhu Kalyan Das | 213/1 | 286911 | 0 | 37.7305 | DA+0 |  | Yes | Yes | 2025-11-12 | 2025-11-01 | 2025-11-22 | 2025-11-21
ta325 | TA325 | 2025-11-01 | Section Incharge | Bibhu Kalyan Das | 214/0 | 546238 | 0 | 72.2342 | DD45+0 | 18 | Yes | Yes | 2025-10-19 | 2025-11-01 | 2025-11-10 | 2025-11-09
ta325 | TA325 | 2025-11-01 | Section Incharge | Bibhu Kalyan Das | 214/1 | 342192 | 0 | 44.7282 | DA+6 |  | Yes | Yes | 2025-11-10 | 2025-11-01 | 2025-11-20 | 2025-11-19
ta325 | TA325 | 2025-11-01 | Section Incharge | Bibhu Kalyan Das | 215/1 | 357181 | 0 | 46.6235 | DA+9 |  | Yes | Yes | 2025-11-13 | 2025-11-01 | 2025-11-23 | 2025-11-22
ta325 | TA325 | 2025-11-01 | Section Incharge | Bibhu Kalyan Das | 216/0 | 676263.874 | 0 | 91.0829 | DB2+25 |  | Yes | Yes | 2025-11-07 | 2025-11-01 | 2025-11-25 | 2025-11-24
ta325 | TA325 | 2025-11-01 | Section Incharge | Bibhu Kalyan Das | 217/0 | 994153 | 0 | 122.8048 | DD45+25 |  | Yes | Yes | 2025-11-08 | 2025-11-01 | 2025-12-01 | 2025-11-30
ta325 | TA325 | 2025-11-01 | Section Incharge | Bibhu Kalyan Das | 217A/0 | 424198 | 0 | 56.8632 | DB1+3 |  | Yes | Yes | 2025-11-15 | 2025-11-01 | 2025-11-27 | 2025-11-26
ta325 | TA325 | 2025-11-01 | Section Incharge | Gurveet Singh | 218/0 | 604881 | 0 | 80.408 | DD60+0 | 24 | Yes | Yes | 2025-10-14 | 2025-11-01 | 2025-11-08 | 2025-11-07
ta325 | TA325 | 2025-11-01 | Section Incharge | Gurveet Singh | 218/1 | 297143 | 0 | 39.4589 | DA+3 | 30 | Yes | Yes | 2025-11-04 | 2025-11-01 | 2025-11-14 | 2025-11-13
ta325 | TA325 | 2025-11-01 | Section Incharge | Gurveet Singh | 219/0 | 780122 | 0 | 97.9334 | DC2+18 | 27 | Yes | Yes | 2025-11-04 | 2025-11-01 | 2025-11-25 | 2025-11-24
ta325 | TA325 | 2025-11-01 | Section Incharge | Gurveet Singh | 220/0 | 680590 | 0 | 89.1428 | DD45+9 | 29 | Yes | Yes | 2025-11-03 | 2025-11-01 | 2025-11-21 | 2025-11-20
ta325 | TA325 | 2025-11-01 | Section Incharge | Gurveet Singh | 220/1 | 297143 | 0 | 39.4589 | DA+3 | 27 | Yes | Yes | 2025-11-04 | 2025-11-01 | 2025-11-14 | 2025-11-13
ta325 | TA325 | 2025-11-01 | Section Incharge | Gurveet Singh | 221/0 | 1003256 | 0 | 129.341 | DD60+18 |  | Yes | Yes | 2025-11-08 | 2025-11-01 | 2025-11-30 | 2025-11-29
ta325 | TA325 | 2025-11-01 | Section Incharge | Gurveet Singh | 222/0 | 1099828 | 0 | 142.1014 | DD60+25 |  | Yes | Yes | 2025-11-09 | 2025-11-01 | 2025-12-03 | 2025-12-02
ta325 | TA325 | 2025-11-01 | Section Incharge | Gurveet Singh | 223/0 | 470077 | 0 | 64.2536 | DC1+0 | 24 | Yes | Yes | 2025-10-23 | 2025-11-01 | 2025-11-10 | 2025-11-09
ta325 | TA325 | 2025-11-01 | Section Incharge | Gurveet Singh | 223/2 | 286911 | 0 | 37.7305 | DA+0 |  | Yes | Yes | 2025-11-12 | 2025-11-01 | 2025-11-22 | 2025-11-21
ta325 | TA325 | 2025-11-01 | Section Incharge | Gurveet Singh | 223/3 | 286911 | 0 | 37.7305 | DA+0 | 30 | Yes | Yes | 2025-11-04 | 2025-11-01 | 2025-11-14 | 2025-11-13
ta325 | TA325 | 2025-11-01 | Section Incharge | Gurveet Singh | 226/0 | 470077 | 0 | 64.2536 | DC2+0 | 26 | Yes | Yes | 2025-10-29 | 2025-11-01 | 2025-11-11 | 2025-11-10
ta325 | TA325 | 2025-11-01 | Section Incharge | Gurveet Singh | 227/0 | 480757 | 0 | 63.509 | DB1+6 | 56 | Yes | Yes | 2025-10-22 | 2025-11-01 | 2025-11-08 | 2025-11-07
ta325 | TA325 | 2025-11-01 | Section Incharge | Gurveet Singh | 228/0 | 1099828 | 0 | 142.1014 | DD60+25 |  | Yes | Yes | 2025-11-07 | 2025-11-01 | 2025-12-02 | 2025-12-01
ta325 | TA325 | 2025-11-01 | Section Incharge | Gurveet Singh | 229/0 | 1003256 | 0 | 129.341 | DD60+18 | 36 | Yes | Yes | 2025-10-12 | 2025-11-01 | 2025-11-10 | 2025-11-09
ta325 | TA325 | 2025-11-01 | Section Incharge | Gurveet Singh | 229/1 | 480757 | 0 | 63.509 | DB1+6 | 28 | Yes | Yes | 2025-10-25 | 2025-11-01 | 2025-11-10 | 2025-11-09
ta325 | TA325 | 2025-11-01 | Section Incharge | Gurveet Singh | 229/2 | 342192 | 0 | 44.7282 | DA+6 | 30 | Yes | Yes | 2025-11-02 | 2025-11-01 | 2025-11-12 | 2025-11-11
ta325 | TA325 | 2025-11-01 | Section Incharge | Gurveet Singh | 230/0 | 604881 | 0 | 80.408 | DD60+0 | 24 | Yes | Yes | 2025-10-09 | 2025-11-01 | 2025-11-08 | 2025-11-07
ta325 | TA325 | 2025-11-01 | Section Incharge | Gurveet Singh | 239/0 | 1099828 | 0 | 142.1014 | DD60+25 |  | Yes | Yes | 2025-11-09 | 2025-11-01 | 2025-12-02 | 2025-12-01
ta325 | TA325 | 2025-11-01 | Section Incharge | Gurveet Singh | 240/0 | 1099828 | 0 | 142.1014 | DD60+25 | 37 | Yes | Yes | 2025-10-22 | 2025-11-01 | 2025-11-14 | 2025-11-13
ta325 | TA325 | 2025-11-01 | Section Incharge | Gurveet Singh | 245/0 | 546238 | 0 | 72.2342 | DD45+0 | 32 | Yes | Yes | 2025-10-24 | 2025-11-01 | 2025-11-09 | 2025-11-08
ta325 | TA325 | 2025-11-01 | Supervisor | Mohit | 102/0 | 1182783 | 0 | 156.8261 | DD45+35 | 45 | Yes | Yes | 2025-10-19 | 2025-11-01 | 2025-11-21 | 2025-11-20
ta325 | TA325 | 2025-11-01 | Supervisor | Khemlal Mahto | 154/1 | 934927 | 0 | 122.8048 | DD45+25 | 53 | Yes | Yes | 2025-10-29 | 2025-11-01 | 2025-11-18 | 2025-11-17
ta325 | TA325 | 2025-11-01 | Supervisor | Abu Alam | 159/2 | 470077 | 0 | 101.852 | DCT+0 | 55 | Yes | Yes | 2025-11-04 | 2025-11-01 | 2025-11-22 | 2025-11-21
ta325 | TA325 | 2025-11-01 | Supervisor | Jaylal Mahto | 160/0 | 1003256 | 0 | 129.341 | DD60+18 | 58 | Yes | Yes | 2025-10-29 | 2025-11-01 | 2025-11-18 | 2025-11-17
ta325 | TA325 | 2025-11-01 | Supervisor | Jaggarnath | 165/4 | 680590 | 0 | 89.1428 | DD45+9 |  | Yes | Yes | 2025-11-08 | 2025-11-01 | 2025-11-25 | 2025-11-24
ta325 | TA325 | 2025-11-01 | Supervisor | Jaggarnath | 165/5 | 680590 | 0 | 89.1428 | DD45+9 |  | Yes | Yes | 2025-11-08 | 2025-11-01 | 2025-11-25 | 2025-11-24
ta325 | TA325 | 2025-11-01 | Supervisor | Jaggarnath | 166/0 | 719574 | 0 | 94.4077 | DD60+6 | 19 | Yes | Yes | 2025-11-05 | 2025-11-01 | 2025-11-26 | 2025-11-25
ta325 | TA325 | 2025-11-01 | Supervisor | Gaurishankar | 167/0 | 719574 | 0 | 94.4077 | DD60+6 |  | Yes | Yes | 2025-11-08 | 2025-11-01 | 2025-11-26 | 2025-11-25
ta325 | TA325 | 2025-11-01 | Supervisor | Baleshwar | 167/1 | 604881 | 0 | 80.408 | DD60+0 |  | Yes | Yes | 2025-11-12 | 2025-11-01 | 2025-11-30 | 2025-11-29
ta325 | TA325 | 2025-11-01 | Supervisor | Birkha Subba | 172/1 | 297143 | 0 | 39.4589 | DA+3 |  | Yes | Yes | 2025-11-12 | 2025-11-01 | 2025-11-22 | 2025-11-21
ta325 | TA325 | 2025-11-01 | Supervisor | Abbu alam | 173/0 | 1099828 | 0 | 142.1014 | DD60+25 |  | Yes | Yes | 2025-11-06 | 2025-11-01 | 2025-12-01 | 2025-11-30
ta325 | TA325 | 2025-11-01 | Supervisor | Abbu alam | 174/0 | 1003256 | 0 | 129.341 | DD60+18 |  | Yes | Yes | 2025-11-07 | 2025-11-01 | 2025-11-30 | 2025-11-29
ta325 | TA325 | 2025-11-01 | Supervisor | Vikash Sharma | 175/1 | 286911 | 0 | 37.7305 | DA+0 |  | Yes | Yes | 2025-11-06 | 2025-11-01 | 2025-11-16 | 2025-11-15
ta325 | TA325 | 2025-11-01 | Supervisor | Janki Mahto | 182A/0 | 650023 | 0 | 85.2305 | DD45+6 |  | Yes | Yes | 2025-11-08 | 2025-11-01 | 2025-11-25 | 2025-11-24
ta325 | TA325 | 2025-11-01 | Supervisor | Janki Mahto | 183/0 | 1099828 | 0 | 142.1014 | DD60+25 | 47 | Yes | Yes | 2025-11-04 | 2025-11-01 | 2025-11-27 | 2025-11-26
ta325 | TA325 | 2025-11-01 | Supervisor | Mukesh Kumar | 184/0 | 1099828 | 0 | 142.1014 | DD60+25 | 37 | Yes | Yes | 2025-10-19 | 2025-11-01 | 2025-11-17 | 2025-11-16
ta325 | TA325 | 2025-11-01 | Supervisor | Aman Yadav | 184/1 | 480757 | 0 | 63.509 | DB1+6 | 17 | Yes | Yes | 2025-10-29 | 2025-11-01 | 2025-11-11 | 2025-11-10
ta325 | TA325 | 2025-11-01 | Supervisor | Nunuchand | 185/0 | 470077 | 0 | 64.2536 | DC2+0 | 45 | Yes | Yes | 2025-11-03 | 2025-11-01 | 2025-11-14 | 2025-11-13
ta325 | TA325 | 2025-11-01 | Supervisor | Nunuchand | 186/0 | 1294023 | 0 | 173.1266 | DD60+35 |  | Yes | Yes | 2025-11-09 | 2025-11-01 | 2025-12-08 | 2025-12-07
ta325 | TA325 | 2025-11-01 | Supervisor | Pankaj Kumar Mahto | 187/0 | 1099828 | 0 | 142.1014 | DD60+25 | 28 | Yes | Yes | 2025-11-04 | 2025-11-01 | 2025-11-17 | 2025-11-16
ta325 | TA325 | 2025-11-01 | Supervisor | Aman Yadav | 200/0 | 670636 | 0 | 82.2388 | DB2+18 |  | Yes | Yes | 2025-11-09 | 2025-11-01 | 2025-11-25 | 2025-11-24
ta325 | TA325 | 2025-11-01 | Supervisor | Aman Yadav | 201/0 | 780122 | 0 | 97.9334 | DC2+18 |  | Yes | Yes | 2025-11-09 | 2025-11-01 | 2025-11-27 | 2025-11-26
ta325 | TA325 | 2025-11-01 | Supervisor | Aman Yadav | 201/1 | 753337 | 0 | 98.8356 | DD60+9 | 20 | Yes | Yes | 2025-11-04 | 2025-11-01 | 2025-11-25 | 2025-11-24
ta325 | TA325 | 2025-11-01 | Supervisor | Ruplal Mahto | 202/0 | 1878263 | 0 | 226.737 | DD60+55 | 32 | Yes | Yes | 2025-10-18 | 2025-11-01 | 2025-11-23 | 2025-11-22
ta325 | TA325 | 2025-11-01 | Supervisor | Gaurishankar | 203/1 | 719574 | 0 | 94.4077 | DD60+6 | 28 | Yes | Yes | 2025-10-26 | 2025-11-01 | 2025-11-10 | 2025-11-09
ta325 | TA325 | 2025-11-01 | Supervisor | Dularchand Mahto | 208/0 | 1099828 | 0 | 142.1014 | DD60+25 |  | Yes | Yes | 2025-11-06 | 2025-11-01 | 2025-11-29 | 2025-11-28
ta325 | TA325 | 2025-11-01 | Supervisor | Ravi Kumar | 209/1 | 297143 | 0 | 39.4589 | DA+3 | 18 | Yes | Yes | 2025-10-29 | 2025-11-01 | 2025-11-09 | 2025-11-08
ta325 | TA325 | 2025-11-01 | Supervisor | Abshik | 211/0 | 503365 | 0 | 65.7565 | DB1+9 | 25 | Yes | Yes | 2025-10-23 | 2025-11-01 | 2025-11-08 | 2025-11-07
ta325 | TA325 | 2025-11-01 | Supervisor | Jaylal Mahto | 211/2 | 286911 | 0 | 37.7305 | DA+0 |  | Yes | Yes | 2025-11-16 | 2025-11-01 | 2025-11-26 | 2025-11-25
ta325 | TA325 | 2025-11-01 | Supervisor | Abshik | 211A/0 | 403998 | 0 | 54.4178 | DB2+0 |  | Yes | Yes | 2025-11-06 | 2025-11-01 | 2025-11-17 | 2025-11-16
ta325 | TA325 | 2025-11-01 | Supervisor | Govind Mahto | 211A/1 | 273608.9283 | 0 | 36.0448 | DA-3 |  | Yes | Yes | 2025-11-08 | 2025-11-01 | 2025-11-18 | 2025-11-17
ta325 | TA325 | 2025-11-01 | Supervisor | Govind Mahto | 211A/2 | 286911 | 0 | 37.7305 | DA+0 | 20 | Yes | Yes | 2025-11-04 | 2025-11-01 | 2025-11-15 | 2025-11-14
ta325 | TA325 | 2025-11-01 | Supervisor | Mukesh Kumar | 212/0 | 573550 | 0 | 75.4524 | DD45+3 |  | Yes | Yes | 2025-11-15 | 2025-11-01 | 2025-11-30 | 2025-11-29
ta325 | TA325 | 2025-11-01 | Supervisor | Kalicharan | 213/0 | 635073 | 0 | 84.2993 | DD60+3 |  | Yes | Yes | 2025-11-08 | 2025-11-01 | 2025-11-25 | 2025-11-24
ta325 | TA325 | 2025-11-01 | Supervisor | Nunuchand | 213/1 | 286911 | 0 | 37.7305 | DA+0 |  | Yes | Yes | 2025-11-12 | 2025-11-01 | 2025-11-22 | 2025-11-21
ta325 | TA325 | 2025-11-01 | Supervisor | Amit Shrivastav | 214/0 | 546238 | 0 | 72.2342 | DD45+0 | 18 | Yes | Yes | 2025-10-19 | 2025-11-01 | 2025-11-10 | 2025-11-09
ta325 | TA325 | 2025-11-01 | Supervisor | Dhiraj Mahto | 214/1 | 342192 | 0 | 44.7282 | DA+6 |  | Yes | Yes | 2025-11-10 | 2025-11-01 | 2025-11-20 | 2025-11-19
ta325 | TA325 | 2025-11-01 | Supervisor | Dhiraj Mahto | 215/1 | 357181 | 0 | 46.6235 | DA+9 |  | Yes | Yes | 2025-11-13 | 2025-11-01 | 2025-11-23 | 2025-11-22
ta325 | TA325 | 2025-11-01 | Supervisor | Ravi Kumar | 216/0 | 676263.874 | 0 | 91.0829 | DB2+25 |  | Yes | Yes | 2025-11-07 | 2025-11-01 | 2025-11-25 | 2025-11-24
ta325 | TA325 | 2025-11-01 | Supervisor | Amit Shrivastav | 217/0 | 994153 | 0 | 122.8048 | DD45+25 |  | Yes | Yes | 2025-11-08 | 2025-11-01 | 2025-12-01 | 2025-11-30
ta325 | TA325 | 2025-11-01 | Supervisor | Pankaj Kumar Mahto | 217A/0 | 424198 | 0 | 56.8632 | DB1+3 |  | Yes | Yes | 2025-11-15 | 2025-11-01 | 2025-11-27 | 2025-11-26
ta325 | TA325 | 2025-11-01 | Supervisor | Vikash Sharma | 218/0 | 604881 | 0 | 80.408 | DD60+0 | 24 | Yes | Yes | 2025-10-14 | 2025-11-01 | 2025-11-08 | 2025-11-07
ta325 | TA325 | 2025-11-01 | Supervisor | Vikash Bishnoi | 218/1 | 297143 | 0 | 39.4589 | DA+3 | 30 | Yes | Yes | 2025-11-04 | 2025-11-01 | 2025-11-14 | 2025-11-13
ta325 | TA325 | 2025-11-01 | Supervisor | Pankaj Kumar Mahto | 219/0 | 780122 | 0 | 97.9334 | DC2+18 | 27 | Yes | Yes | 2025-11-04 | 2025-11-01 | 2025-11-25 | 2025-11-24
ta325 | TA325 | 2025-11-01 | Supervisor | Birkha Subba | 220/0 | 680590 | 0 | 89.1428 | DD45+9 | 29 | Yes | Yes | 2025-11-03 | 2025-11-01 | 2025-11-21 | 2025-11-20
ta325 | TA325 | 2025-11-01 | Supervisor | Birkha Subba | 220/1 | 297143 | 0 | 39.4589 | DA+3 | 27 | Yes | Yes | 2025-11-04 | 2025-11-01 | 2025-11-14 | 2025-11-13
ta325 | TA325 | 2025-11-01 | Supervisor | Rewatlal Mahto | 221/0 | 1003256 | 0 | 129.341 | DD60+18 |  | Yes | Yes | 2025-11-08 | 2025-11-01 | 2025-11-30 | 2025-11-29
ta325 | TA325 | 2025-11-01 | Supervisor | Rewatlal Mahto | 222/0 | 1099828 | 0 | 142.1014 | DD60+25 |  | Yes | Yes | 2025-11-09 | 2025-11-01 | 2025-12-03 | 2025-12-02
ta325 | TA325 | 2025-11-01 | Supervisor | Kalicharan | 223/0 | 470077 | 0 | 64.2536 | DC1+0 | 24 | Yes | Yes | 2025-10-23 | 2025-11-01 | 2025-11-10 | 2025-11-09
ta325 | TA325 | 2025-11-01 | Supervisor | Vikash Bishnoi | 223/2 | 286911 | 0 | 37.7305 | DA+0 |  | Yes | Yes | 2025-11-12 | 2025-11-01 | 2025-11-22 | 2025-11-21
ta325 | TA325 | 2025-11-01 | Supervisor | Vikash Bishnoi | 223/3 | 286911 | 0 | 37.7305 | DA+0 | 30 | Yes | Yes | 2025-11-04 | 2025-11-01 | 2025-11-14 | 2025-11-13
ta325 | TA325 | 2025-11-01 | Supervisor | Yugal Kishor | 226/0 | 470077 | 0 | 64.2536 | DC2+0 | 26 | Yes | Yes | 2025-10-29 | 2025-11-01 | 2025-11-11 | 2025-11-10
ta325 | TA325 | 2025-11-01 | Supervisor | Abbu alam | 227/0 | 480757 | 0 | 63.509 | DB1+6 | 56 | Yes | Yes | 2025-10-22 | 2025-11-01 | 2025-11-08 | 2025-11-07
ta325 | TA325 | 2025-11-01 | Supervisor | Lal Mohan | 228/0 | 1099828 | 0 | 142.1014 | DD60+25 |  | Yes | Yes | 2025-11-07 | 2025-11-01 | 2025-12-02 | 2025-12-01
ta325 | TA325 | 2025-11-01 | Supervisor | Rewatlal Mahto | 229/0 | 1003256 | 0 | 129.341 | DD60+18 | 36 | Yes | Yes | 2025-10-12 | 2025-11-01 | 2025-11-10 | 2025-11-09
ta325 | TA325 | 2025-11-01 | Supervisor | Govind Mahto | 229/1 | 480757 | 0 | 63.509 | DB1+6 | 28 | Yes | Yes | 2025-10-25 | 2025-11-01 | 2025-11-10 | 2025-11-09
ta325 | TA325 | 2025-11-01 | Supervisor | Dhiraj Mahto | 229/2 | 342192 | 0 | 44.7282 | DA+6 | 30 | Yes | Yes | 2025-11-02 | 2025-11-01 | 2025-11-12 | 2025-11-11
ta325 | TA325 | 2025-11-01 | Supervisor | Dularchand Mahto | 230/0 | 604881 | 0 | 80.408 | DD60+0 | 24 | Yes | Yes | 2025-10-09 | 2025-11-01 | 2025-11-08 | 2025-11-07
ta325 | TA325 | 2025-11-01 | Supervisor | Yugal Kishor | 239/0 | 1099828 | 0 | 142.1014 | DD60+25 |  | Yes | Yes | 2025-11-09 | 2025-11-01 | 2025-12-02 | 2025-12-01
ta325 | TA325 | 2025-11-01 | Supervisor | Baleshwar | 240/0 | 1099828 | 0 | 142.1014 | DD60+25 | 37 | Yes | Yes | 2025-10-22 | 2025-11-01 | 2025-11-14 | 2025-11-13
ta325 | TA325 | 2025-11-01 | Supervisor | Lal Mohan | 245/0 | 546238 | 0 | 72.2342 | DD45+0 | 32 | Yes | Yes | 2025-10-24 | 2025-11-01 | 2025-11-09 | 2025-11-08
ta413 | TA413 | 2025-11-01 | Gang | Govind Mahto-01 | 20/3 | 346011.8226 | 0 | 37.1383 | DA+1.5 | 28 |  | 2025-10-29 | 2025-10-30 | 2025-11-01 | 2025-11-06 | 2025-11-07
ta413 | TA413 | 2025-11-01 | Gang | Govind Mahto-01 | 21/2 | 408118.8097 | 0 | 43.8044 | DA+6 | 28 |  | 2025-11-05 | 2025-11-06 | 2025-11-01 | 2025-11-13 | 2025-11-14
ta413 | TA413 | 2025-11-01 | Gang | Govind Mahto-01 | 21/3 | 408118.8097 | 0 | 43.8044 | DA+6 | 28 |  | 2025-11-12 | 2025-11-13 | 2025-11-01 | 2025-11-20 | 2025-11-21
ta413 | TA413 | 2025-11-01 | Gang | Jawla Singh-1 | 10/2 | 353397.8779 | 0 | 37.9311 | DA+3 | 20 |  | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-09 | 2025-11-10
ta413 | TA413 | 2025-11-01 | Gang | Jawla Singh-1 | 14/0 | 1164138.7108 | 0 | 124.95 | DD60+18 | 20 |  | 2025-11-08 | 2025-11-09 | 2025-11-01 | 2025-11-25 | 2025-11-26
ta413 | TA413 | 2025-11-01 | Gang | Jwala Singh -2 | 28/0 | 604516.623 | 0 | 64.8843 | DC2-3 | 26 |  | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-08 | 2025-11-09
ta413 | TA413 | 2025-11-01 | Gang | Jwala Singh -2 | 27/6 | 324131.0934 | 0 | 34.7898 | DA-3 | 26 |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-11-17 | 2025-11-18
ta413 | TA413 | 2025-11-01 | Gang | Jwala Singh -2 | 23A/0 | 622186.9697 | 0 | 66.7809 | DB1+9 | 26 |  | 2025-11-16 | 2025-11-17 | 2025-11-01 | 2025-11-29 | 2025-11-30
ta413 | TA413 | 2025-11-01 | Gang | Jwala Singh -2 | 29/2 | 336894.6611 | 0 | 36.1598 | DA+0 | 26 |  | 2025-11-28 | 2025-11-29 | 2025-11-01 | 2025-12-08 | 2025-12-09
ta413 | TA413 | 2025-11-01 | Gang | Govind Mahto-02 | 9/10 | 353397.8779 | 0 | 37.9311 | DA+3 | 25 |  | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-08 | 2025-11-09
ta413 | TA413 | 2025-11-01 | Gang | Govind Mahto-02 | 9/9 | 336894.6611 | 0 | 36.1598 | DA+0 | 25 |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-11-15 | 2025-11-16
ta413 | TA413 | 2025-11-01 | Gang | Govind Mahto-02 | 9/8 | 336894.6611 | 0 | 36.1598 | DA+0 | 25 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-11-22 | 2025-11-23
ta413 | TA413 | 2025-11-01 | Gang | Bhairaw Mahto | 22/0 | 902614.5275 | 0 | 96.8799 | DC2+15 | 41 |  | 2025-10-27 | 2025-10-28 | 2025-11-01 | 2025-11-08 | 2025-11-09
ta413 | TA413 | 2025-11-01 | Gang | Bhairaw Mahto | 11/0 | 682407.7346 | 0 | 73.2445 | DD45+0 | 41 |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-11-19 | 2025-11-20
ta413 | TA413 | 2025-11-01 | Gang | Bhairaw Mahto | 13/0 | 949875.9872 | 0 | 101.9526 | DD60+9 | 41 |  | 2025-11-18 | 2025-11-19 | 2025-11-01 | 2025-11-29 | 2025-11-30
ta413 | TA413 | 2025-11-01 | Gang | Bhairaw Mahto | 13A/0 | 622186.9697 | 0 | 66.7809 | DB1+9 | 41 |  | 2025-11-28 | 2025-11-29 | 2025-11-01 | 2025-12-06 | 2025-12-07
ta413 | TA413 | 2025-11-01 | Gang | Pritam Enterprises-3 | 27/4 | 346011.8226 | 0 | 37.1383 | DA+1.5 | 25 |  | 2025-11-04 | 2025-11-05 | 2025-11-01 | 2025-11-11 | 2025-11-12
ta413 | TA413 | 2025-11-01 | Gang | Pritam Enterprises-3 | 27/3 | 346011.8226 | 0 | 37.1383 | DA+1.5 | 25 |  | 2025-11-10 | 2025-11-11 | 2025-11-01 | 2025-11-17 | 2025-11-18
ta413 | TA413 | 2025-11-01 | Gang | Pritam Enterprises-3 | 27/2 | 331695.9203 | 0 | 35.6018 | DA-1.5 | 25 |  | 2025-11-16 | 2025-11-17 | 2025-11-01 | 2025-11-23 | 2025-11-24
ta413 | TA413 | 2025-11-01 | Gang | Pritam Enterprises-3 | 27/1 | 425751.8425 | 0 | 45.697 | DA+9 | 25 |  | 2025-10-29 | 2025-10-30 | 2025-11-01 | 2025-11-06 | 2025-11-07
ta413 | TA413 | 2025-11-01 | Gang | Pritam Enterprises-4 | 3B/3 | 408118.8097 | 0 | 43.8044 | DA+6 | 24 |  | 2025-11-05 | 2025-11-06 | 2025-11-01 | 2025-11-17 | 2025-11-18
ta413 | TA413 | 2025-11-01 | Gang | Pritam Enterprises-4 | 2A/0 | 682407.7346 | 0 | 73.2445 | DD45+0 | 24 |  | 2025-11-16 | 2025-11-17 | 2025-11-01 | 2025-11-24 | 2025-11-25
ta413 | TA413 | 2025-11-01 | Gang | Pritam Enterprises-4 | 35/10 | 353397.8779 | 0 | 37.9311 | DA+3 | 24 |  | 2025-11-23 | 2025-11-24 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta413 | TA413 | 2025-11-01 | Gang | Pritam Enterprises-4 | 35/3 | 324131.0934 | 0 | 34.7898 | DA-3 | 24 |  | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-08 | 2025-11-09
ta413 | TA413 | 2025-11-01 | Gang | Punam kumari-1 | 20/4 | 353397.8779 | 0 | 37.9311 | DA+3 | 36 |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-11-15 | 2025-11-16
ta413 | TA413 | 2025-11-01 | Gang | Punam kumari-1 | 15/9 | 336894.6611 | 0 | 36.1598 | DA+0 | 36 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-11-22 | 2025-11-23
ta413 | TA413 | 2025-11-01 | Gang | Punam kumari-1 | 15/10 | 331695.9203 | 0 | 35.6018 | DA-1.5 | 36 |  | 2025-11-21 | 2025-11-22 | 2025-11-01 | 2025-11-29 | 2025-11-30
ta413 | TA413 | 2025-11-01 | Gang | Fouzi Ratto | 24/0 | 1164138.7108 | 0 | 124.95 | DD60+18 | 18 |  | 2025-10-12 | 2025-10-13 | 2025-11-01 | 2025-11-11 | 2025-11-12
ta413 | TA413 | 2025-11-01 | Gang | Fouzi Ratto | 25/0 | 1164138.7108 | 0 | 124.95 | DD60+18 | 18 |  | 2025-11-10 | 2025-11-11 | 2025-11-01 | 2025-11-27 | 2025-11-28
ta413 | TA413 | 2025-11-01 | Gang | Sherra Const. | 26/0 | 1617039.2474 | 0 | 173.5609 | DD60+35 | 38 |  | 2025-10-10 | 2025-10-11 | 2025-11-01 | 2025-11-01 | 2025-11-02
ta413 | TA413 | 2025-11-01 | Gang | Sherra Const. | 27/0 | 1617039.2474 | 0 | 173.5609 | DD60+35 | 38 |  | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-17 | 2025-11-18
ta413 | TA413 | 2025-11-01 | Gang | Amit kumar singh | 37/2 | 353397.8779 | 0 | 37.9311 | DA+3 | 28 |  | 2025-11-08 | 2025-11-09 | 2025-11-01 | 2025-11-15 | 2025-11-16
ta413 | TA413 | 2025-11-01 | Gang | Amit kumar singh | 37/3 | 331695.9203 | 0 | 35.6018 | DA-1.5 | 28 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-11-21 | 2025-11-22
ta413 | TA413 | 2025-11-01 | Gang | Amit kumar singh | 37/0 | 578726.2869 | 0 | 62.1162 | DB2+3 | 28 |  | 2025-11-20 | 2025-11-21 | 2025-11-01 | 2025-11-27 | 2025-11-28
ta413 | TA413 | 2025-11-01 | Gang | Amit kumar singh | 37/1 | 353397.8779 | 0 | 37.9311 | DA+3 | 28 |  | 2025-11-26 | 2025-11-27 | 2025-11-01 | 2025-12-03 | 2025-12-04
ta413 | TA413 | 2025-11-01 | Gang | Vikas kumar Singh | 29A/3 | 408118.8097 | 0 | 43.8044 | DA+6 | 30 |  | 2025-11-11 | 2025-11-12 | 2025-11-01 | 2025-11-18 | 2025-11-19
ta413 | TA413 | 2025-11-01 | Gang | Vikas kumar Singh | 30/5 | 336894.6611 | 0 | 36.1598 | DA+0 | 30 |  | 2025-11-17 | 2025-11-18 | 2025-11-01 | 2025-11-23 | 2025-11-24
ta413 | TA413 | 2025-11-01 | Gang | Vikas kumar Singh | 36/0 | 578726.2869 | 0 | 62.1162 | DB2+3 | 30 |  | 2025-11-22 | 2025-11-23 | 2025-11-01 | 2025-11-28 | 2025-11-29
ta413 | TA413 | 2025-11-01 | Gang | Ramji Structure | 16/0 | 626666.7579 | 0 | 67.2617 | DC2+0 | 30 |  | 2025-11-09 | 2025-11-10 | 2025-11-01 | 2025-11-21 | 2025-11-22
ta413 | TA413 | 2025-11-01 | Gang | Ramji Structure | 17/0 | 613723.3938 | 0 | 65.8725 | DC1+3 | 30 |  | 2025-11-20 | 2025-11-21 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta413 | TA413 | 2025-11-01 | Gang | Punam kumari-2 | 43/0 | 516626.7066 | 0 | 55.4509 | DB1+0 | 30 |  | 2025-11-09 | 2025-11-10 | 2025-11-01 | 2025-11-19 | 2025-11-20
ta413 | TA413 | 2025-11-01 | Gang | Punam kumari-2 | 43/1 | 331695.9203 | 0 | 35.6018 | DA-1.5 | 30 |  | 2025-11-18 | 2025-11-19 | 2025-11-01 | 2025-12-05 | 2025-12-06
ta413 | TA413 | 2025-11-01 | Gang | Punam kumari-2 | 43/5 | 626666.7579 | 0 | 67.2617 | DC2+0 | 30 |  | 2025-12-04 | 2025-12-05 | 2025-11-01 | 2025-12-12 | 2025-12-13
ta413 | TA413 | 2025-11-01 | Gang | Kartik Mahto | 15/1 | 408118.8097 | 0 | 43.8044 | DA+6 | 30 |  | 2025-11-09 | 2025-11-10 | 2025-11-01 | 2025-11-18 | 2025-11-19
ta413 | TA413 | 2025-11-01 | Gang | Kartik Mahto | 15/7 | 336894.6611 | 0 | 36.1598 | DA+0 | 30 |  | 2025-11-17 | 2025-11-18 | 2025-11-01 | 2025-11-24 | 2025-11-25
ta413 | TA413 | 2025-11-01 | Gang | Kartik Mahto | 15/11 | 336894.6611 | 0 | 36.1598 | DA+0 | 30 |  | 2025-11-23 | 2025-11-24 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta413 | TA413 | 2025-11-01 | Gang | SK. Samiul-2 | 21/4 | 336894.6611 | 0 | 36.1598 | DA+0 | 28 |  | 2025-11-10 | 2025-11-11 | 2025-11-01 | 2025-11-18 | 2025-11-19
ta413 | TA413 | 2025-11-01 | Gang | SK. Samiul-2 | 21/5 | 336894.6611 | 0 | 36.1598 | DA+0 | 28 |  | 2025-11-17 | 2025-11-18 | 2025-11-01 | 2025-11-24 | 2025-11-25
ta413 | TA413 | 2025-11-01 | Gang | SK. Samiul-2 | 15/12 | 408118.8097 | 0 | 43.8044 | DA+6 | 36 |  | 2025-11-23 | 2025-11-24 | 2025-11-01 | 2025-11-29 | 2025-11-30
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 20/3 | 346011.8226 | 0 | 37.1383 | DA+1.5 | 28 |  | 2025-10-29 | 2025-10-30 | 2025-11-01 | 2025-11-06 | 2025-11-07
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 21/2 | 408118.8097 | 0 | 43.8044 | DA+6 | 28 |  | 2025-11-05 | 2025-11-06 | 2025-11-01 | 2025-11-13 | 2025-11-14
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 21/3 | 408118.8097 | 0 | 43.8044 | DA+6 | 28 |  | 2025-11-12 | 2025-11-13 | 2025-11-01 | 2025-11-20 | 2025-11-21
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 10/2 | 353397.8779 | 0 | 37.9311 | DA+3 | 20 |  | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-09 | 2025-11-10
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 14/0 | 1164138.7108 | 0 | 124.95 | DD60+18 | 20 |  | 2025-11-08 | 2025-11-09 | 2025-11-01 | 2025-11-25 | 2025-11-26
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 28/0 | 604516.623 | 0 | 64.8843 | DC2-3 | 26 |  | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-08 | 2025-11-09
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 27/6 | 324131.0934 | 0 | 34.7898 | DA-3 | 26 |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-11-17 | 2025-11-18
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 23A/0 | 622186.9697 | 0 | 66.7809 | DB1+9 | 26 |  | 2025-11-16 | 2025-11-17 | 2025-11-01 | 2025-11-29 | 2025-11-30
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 29/2 | 336894.6611 | 0 | 36.1598 | DA+0 | 26 |  | 2025-11-28 | 2025-11-29 | 2025-11-01 | 2025-12-08 | 2025-12-09
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 9/10 | 353397.8779 | 0 | 37.9311 | DA+3 | 25 |  | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-08 | 2025-11-09
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 9/9 | 336894.6611 | 0 | 36.1598 | DA+0 | 25 |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-11-15 | 2025-11-16
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 9/8 | 336894.6611 | 0 | 36.1598 | DA+0 | 25 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-11-22 | 2025-11-23
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 22/0 | 902614.5275 | 0 | 96.8799 | DC2+15 | 41 |  | 2025-10-27 | 2025-10-28 | 2025-11-01 | 2025-11-08 | 2025-11-09
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 11/0 | 682407.7346 | 0 | 73.2445 | DD45+0 | 41 |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-11-19 | 2025-11-20
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 13/0 | 949875.9872 | 0 | 101.9526 | DD60+9 | 41 |  | 2025-11-18 | 2025-11-19 | 2025-11-01 | 2025-11-29 | 2025-11-30
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 13A/0 | 622186.9697 | 0 | 66.7809 | DB1+9 | 41 |  | 2025-11-28 | 2025-11-29 | 2025-11-01 | 2025-12-06 | 2025-12-07
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 27/4 | 346011.8226 | 0 | 37.1383 | DA+1.5 | 25 |  | 2025-11-04 | 2025-11-05 | 2025-11-01 | 2025-11-11 | 2025-11-12
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 27/3 | 346011.8226 | 0 | 37.1383 | DA+1.5 | 25 |  | 2025-11-10 | 2025-11-11 | 2025-11-01 | 2025-11-17 | 2025-11-18
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 27/2 | 331695.9203 | 0 | 35.6018 | DA-1.5 | 25 |  | 2025-11-16 | 2025-11-17 | 2025-11-01 | 2025-11-23 | 2025-11-24
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 27/1 | 425751.8425 | 0 | 45.697 | DA+9 | 25 |  | 2025-10-29 | 2025-10-30 | 2025-11-01 | 2025-11-06 | 2025-11-07
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 3B/3 | 408118.8097 | 0 | 43.8044 | DA+6 | 24 |  | 2025-11-05 | 2025-11-06 | 2025-11-01 | 2025-11-17 | 2025-11-18
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 2A/0 | 682407.7346 | 0 | 73.2445 | DD45+0 | 24 |  | 2025-11-16 | 2025-11-17 | 2025-11-01 | 2025-11-24 | 2025-11-25
ta413 | TA413 | 2025-11-01 | Section Incharge | Kartik Jhorar | 35/10 | 353397.8779 | 0 | 37.9311 | DA+3 | 24 |  | 2025-11-23 | 2025-11-24 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta413 | TA413 | 2025-11-01 | Section Incharge | Kartik Jhorar | 35/3 | 324131.0934 | 0 | 34.7898 | DA-3 | 24 |  | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-08 | 2025-11-09
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 20/4 | 353397.8779 | 0 | 37.9311 | DA+3 | 36 |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-11-15 | 2025-11-16
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 15/9 | 336894.6611 | 0 | 36.1598 | DA+0 | 36 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-11-22 | 2025-11-23
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 15/10 | 331695.9203 | 0 | 35.6018 | DA-1.5 | 36 |  | 2025-11-21 | 2025-11-22 | 2025-11-01 | 2025-11-29 | 2025-11-30
ta413 | TA413 | 2025-11-01 | Section Incharge | Kartik Jhorar | 24/0 | 1164138.7108 | 0 | 124.95 | DD60+18 | 18 |  | 2025-10-12 | 2025-10-13 | 2025-11-01 | 2025-11-11 | 2025-11-12
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 25/0 | 1164138.7108 | 0 | 124.95 | DD60+18 | 18 |  | 2025-11-10 | 2025-11-11 | 2025-11-01 | 2025-11-27 | 2025-11-28
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 26/0 | 1617039.2474 | 0 | 173.5609 | DD60+35 | 38 |  | 2025-10-10 | 2025-10-11 | 2025-11-01 | 2025-11-01 | 2025-11-02
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 27/0 | 1617039.2474 | 0 | 173.5609 | DD60+35 | 38 |  | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-17 | 2025-11-18
ta413 | TA413 | 2025-11-01 | Section Incharge | Kartik Jhorar | 37/2 | 353397.8779 | 0 | 37.9311 | DA+3 | 28 |  | 2025-11-08 | 2025-11-09 | 2025-11-01 | 2025-11-15 | 2025-11-16
ta413 | TA413 | 2025-11-01 | Section Incharge | Kartik Jhorar | 37/3 | 331695.9203 | 0 | 35.6018 | DA-1.5 | 28 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-11-21 | 2025-11-22
ta413 | TA413 | 2025-11-01 | Section Incharge | Kartik Jhorar | 37/0 | 578726.2869 | 0 | 62.1162 | DB2+3 | 28 |  | 2025-11-20 | 2025-11-21 | 2025-11-01 | 2025-11-27 | 2025-11-28
ta413 | TA413 | 2025-11-01 | Section Incharge | Kartik Jhorar | 37/1 | 353397.8779 | 0 | 37.9311 | DA+3 | 28 |  | 2025-11-26 | 2025-11-27 | 2025-11-01 | 2025-12-03 | 2025-12-04
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 29A/3 | 408118.8097 | 0 | 43.8044 | DA+6 | 30 |  | 2025-11-11 | 2025-11-12 | 2025-11-01 | 2025-11-18 | 2025-11-19
ta413 | TA413 | 2025-11-01 | Section Incharge | Kartik Jhorar | 30/5 | 336894.6611 | 0 | 36.1598 | DA+0 | 30 |  | 2025-11-17 | 2025-11-18 | 2025-11-01 | 2025-11-23 | 2025-11-24
ta413 | TA413 | 2025-11-01 | Section Incharge | Kartik Jhorar | 36/0 | 578726.2869 | 0 | 62.1162 | DB2+3 | 30 |  | 2025-11-22 | 2025-11-23 | 2025-11-01 | 2025-11-28 | 2025-11-29
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 16/0 | 626666.7579 | 0 | 67.2617 | DC2+0 | 30 |  | 2025-11-09 | 2025-11-10 | 2025-11-01 | 2025-11-21 | 2025-11-22
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 17/0 | 613723.3938 | 0 | 65.8725 | DC1+3 | 30 |  | 2025-11-20 | 2025-11-21 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta413 | TA413 | 2025-11-01 | Section Incharge | Kartik Jhorar | 43/0 | 516626.7066 | 0 | 55.4509 | DB1+0 | 30 |  | 2025-11-09 | 2025-11-10 | 2025-11-01 | 2025-11-19 | 2025-11-20
ta413 | TA413 | 2025-11-01 | Section Incharge | Kartik Jhorar | 43/1 | 331695.9203 | 0 | 35.6018 | DA-1.5 | 30 |  | 2025-11-18 | 2025-11-19 | 2025-11-01 | 2025-12-05 | 2025-12-06
ta413 | TA413 | 2025-11-01 | Section Incharge | Kartik Jhorar | 43/5 | 626666.7579 | 0 | 67.2617 | DC2+0 | 30 |  | 2025-12-04 | 2025-12-05 | 2025-11-01 | 2025-12-12 | 2025-12-13
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 15/1 | 408118.8097 | 0 | 43.8044 | DA+6 | 30 |  | 2025-11-09 | 2025-11-10 | 2025-11-01 | 2025-11-18 | 2025-11-19
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 15/7 | 336894.6611 | 0 | 36.1598 | DA+0 | 30 |  | 2025-11-17 | 2025-11-18 | 2025-11-01 | 2025-11-24 | 2025-11-25
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 15/11 | 336894.6611 | 0 | 36.1598 | DA+0 | 30 |  | 2025-11-23 | 2025-11-24 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 21/4 | 336894.6611 | 0 | 36.1598 | DA+0 | 28 |  | 2025-11-10 | 2025-11-11 | 2025-11-01 | 2025-11-18 | 2025-11-19
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 21/5 | 336894.6611 | 0 | 36.1598 | DA+0 | 28 |  | 2025-11-17 | 2025-11-18 | 2025-11-01 | 2025-11-24 | 2025-11-25
ta413 | TA413 | 2025-11-01 | Section Incharge | Shuvam Gupta | 15/12 | 408118.8097 | 0 | 43.8044 | DA+6 | 36 |  | 2025-11-23 | 2025-11-24 | 2025-11-01 | 2025-11-29 | 2025-11-30
ta413 | TA413 | 2025-11-01 | Supervisor | Rudra Prasad | 20/3 | 346011.8226 | 0 | 37.1383 | DA+1.5 | 28 |  | 2025-10-29 | 2025-10-30 | 2025-11-01 | 2025-11-06 | 2025-11-07
ta413 | TA413 | 2025-11-01 | Supervisor | Rudra Prasad | 21/2 | 408118.8097 | 0 | 43.8044 | DA+6 | 28 |  | 2025-11-05 | 2025-11-06 | 2025-11-01 | 2025-11-13 | 2025-11-14
ta413 | TA413 | 2025-11-01 | Supervisor | Rudra Prasad | 21/3 | 408118.8097 | 0 | 43.8044 | DA+6 | 28 |  | 2025-11-12 | 2025-11-13 | 2025-11-01 | 2025-11-20 | 2025-11-21
ta413 | TA413 | 2025-11-01 | Supervisor | Akil Hussain | 10/2 | 353397.8779 | 0 | 37.9311 | DA+3 | 20 |  | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-09 | 2025-11-10
ta413 | TA413 | 2025-11-01 | Supervisor | Akil Hussain | 14/0 | 1164138.7108 | 0 | 124.95 | DD60+18 | 20 |  | 2025-11-08 | 2025-11-09 | 2025-11-01 | 2025-11-25 | 2025-11-26
ta413 | TA413 | 2025-11-01 | Supervisor | Haridasn | 28/0 | 604516.623 | 0 | 64.8843 | DC2-3 | 26 |  | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-08 | 2025-11-09
ta413 | TA413 | 2025-11-01 | Supervisor | Haridasn | 27/6 | 324131.0934 | 0 | 34.7898 | DA-3 | 26 |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-11-17 | 2025-11-18
ta413 | TA413 | 2025-11-01 | Supervisor | Haridasn | 23A/0 | 622186.9697 | 0 | 66.7809 | DB1+9 | 26 |  | 2025-11-16 | 2025-11-17 | 2025-11-01 | 2025-11-29 | 2025-11-30
ta413 | TA413 | 2025-11-01 | Supervisor | Haridasn | 29/2 | 336894.6611 | 0 | 36.1598 | DA+0 | 26 |  | 2025-11-28 | 2025-11-29 | 2025-11-01 | 2025-12-08 | 2025-12-09
ta413 | TA413 | 2025-11-01 | Supervisor | Aman Kr Singh | 9/10 | 353397.8779 | 0 | 37.9311 | DA+3 | 25 |  | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-08 | 2025-11-09
ta413 | TA413 | 2025-11-01 | Supervisor | Aman Kr Singh | 9/9 | 336894.6611 | 0 | 36.1598 | DA+0 | 25 |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-11-15 | 2025-11-16
ta413 | TA413 | 2025-11-01 | Supervisor | Aman Kr Singh | 9/8 | 336894.6611 | 0 | 36.1598 | DA+0 | 25 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-11-22 | 2025-11-23
ta413 | TA413 | 2025-11-01 | Supervisor | Dhalchand Mahto | 22/0 | 902614.5275 | 0 | 96.8799 | DC2+15 | 41 |  | 2025-10-27 | 2025-10-28 | 2025-11-01 | 2025-11-08 | 2025-11-09
ta413 | TA413 | 2025-11-01 | Supervisor | Dhalchand Mahto | 11/0 | 682407.7346 | 0 | 73.2445 | DD45+0 | 41 |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-11-19 | 2025-11-20
ta413 | TA413 | 2025-11-01 | Supervisor | Dhalchand Mahto | 13/0 | 949875.9872 | 0 | 101.9526 | DD60+9 | 41 |  | 2025-11-18 | 2025-11-19 | 2025-11-01 | 2025-11-29 | 2025-11-30
ta413 | TA413 | 2025-11-01 | Supervisor | Dhalchand Mahto | 13A/0 | 622186.9697 | 0 | 66.7809 | DB1+9 | 41 |  | 2025-11-28 | 2025-11-29 | 2025-11-01 | 2025-12-06 | 2025-12-07
ta413 | TA413 | 2025-11-01 | Supervisor | Nabirul Islam | 27/4 | 346011.8226 | 0 | 37.1383 | DA+1.5 | 25 |  | 2025-11-04 | 2025-11-05 | 2025-11-01 | 2025-11-11 | 2025-11-12
ta413 | TA413 | 2025-11-01 | Supervisor | Nabirul Islam | 27/3 | 346011.8226 | 0 | 37.1383 | DA+1.5 | 25 |  | 2025-11-10 | 2025-11-11 | 2025-11-01 | 2025-11-17 | 2025-11-18
ta413 | TA413 | 2025-11-01 | Supervisor | Nabirul Islam | 27/2 | 331695.9203 | 0 | 35.6018 | DA-1.5 | 25 |  | 2025-11-16 | 2025-11-17 | 2025-11-01 | 2025-11-23 | 2025-11-24
ta413 | TA413 | 2025-11-01 | Supervisor | Nabirul Islam | 27/1 | 425751.8425 | 0 | 45.697 | DA+9 | 25 |  | 2025-10-29 | 2025-10-30 | 2025-11-01 | 2025-11-06 | 2025-11-07
ta413 | TA413 | 2025-11-01 | Supervisor | Abhaiya Ojha | 3B/3 | 408118.8097 | 0 | 43.8044 | DA+6 | 24 |  | 2025-11-05 | 2025-11-06 | 2025-11-01 | 2025-11-17 | 2025-11-18
ta413 | TA413 | 2025-11-01 | Supervisor | Abhaiya Ojha | 2A/0 | 682407.7346 | 0 | 73.2445 | DD45+0 | 24 |  | 2025-11-16 | 2025-11-17 | 2025-11-01 | 2025-11-24 | 2025-11-25
ta413 | TA413 | 2025-11-01 | Supervisor | Abhaiya Ojha | 35/10 | 353397.8779 | 0 | 37.9311 | DA+3 | 24 |  | 2025-11-23 | 2025-11-24 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta413 | TA413 | 2025-11-01 | Supervisor | Abhaiya Ojha | 35/3 | 324131.0934 | 0 | 34.7898 | DA-3 | 24 |  | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-08 | 2025-11-09
ta413 | TA413 | 2025-11-01 | Supervisor | Manoj Kr choudhary | 20/4 | 353397.8779 | 0 | 37.9311 | DA+3 | 36 |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-11-15 | 2025-11-16
ta413 | TA413 | 2025-11-01 | Supervisor | Manoj Kr choudhary | 15/9 | 336894.6611 | 0 | 36.1598 | DA+0 | 36 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-11-22 | 2025-11-23
ta413 | TA413 | 2025-11-01 | Supervisor | Manoj Kr choudhary | 15/10 | 331695.9203 | 0 | 35.6018 | DA-1.5 | 36 |  | 2025-11-21 | 2025-11-22 | 2025-11-01 | 2025-11-29 | 2025-11-30
ta413 | TA413 | 2025-11-01 | Supervisor | Manoj Gupta | 24/0 | 1164138.7108 | 0 | 124.95 | DD60+18 | 18 |  | 2025-10-12 | 2025-10-13 | 2025-11-01 | 2025-11-11 | 2025-11-12
ta413 | TA413 | 2025-11-01 | Supervisor | Manoj Gupta | 25/0 | 1164138.7108 | 0 | 124.95 | DD60+18 | 18 |  | 2025-11-10 | 2025-11-11 | 2025-11-01 | 2025-11-27 | 2025-11-28
ta413 | TA413 | 2025-11-01 | Supervisor | Khooblal | 26/0 | 1617039.2474 | 0 | 173.5609 | DD60+35 | 38 |  | 2025-10-10 | 2025-10-11 | 2025-11-01 | 2025-11-01 | 2025-11-02
ta413 | TA413 | 2025-11-01 | Supervisor | Khooblal | 27/0 | 1617039.2474 | 0 | 173.5609 | DD60+35 | 38 |  | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-17 | 2025-11-18
ta413 | TA413 | 2025-11-01 | Supervisor | Akabr Ali | 37/2 | 353397.8779 | 0 | 37.9311 | DA+3 | 28 |  | 2025-11-08 | 2025-11-09 | 2025-11-01 | 2025-11-15 | 2025-11-16
ta413 | TA413 | 2025-11-01 | Supervisor | Akabr Ali | 37/3 | 331695.9203 | 0 | 35.6018 | DA-1.5 | 28 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-11-21 | 2025-11-22
ta413 | TA413 | 2025-11-01 | Supervisor | Akabr Ali | 37/0 | 578726.2869 | 0 | 62.1162 | DB2+3 | 28 |  | 2025-11-20 | 2025-11-21 | 2025-11-01 | 2025-11-27 | 2025-11-28
ta413 | TA413 | 2025-11-01 | Supervisor | Akabr Ali | 37/1 | 353397.8779 | 0 | 37.9311 | DA+3 | 28 |  | 2025-11-26 | 2025-11-27 | 2025-11-01 | 2025-12-03 | 2025-12-04
ta413 | TA413 | 2025-11-01 | Supervisor | Rahul Ravidas | 29A/3 | 408118.8097 | 0 | 43.8044 | DA+6 | 30 |  | 2025-11-11 | 2025-11-12 | 2025-11-01 | 2025-11-18 | 2025-11-19
ta413 | TA413 | 2025-11-01 | Supervisor | Rahul Ravidas | 30/5 | 336894.6611 | 0 | 36.1598 | DA+0 | 30 |  | 2025-11-17 | 2025-11-18 | 2025-11-01 | 2025-11-23 | 2025-11-24
ta413 | TA413 | 2025-11-01 | Supervisor | Rahul Ravidas | 36/0 | 578726.2869 | 0 | 62.1162 | DB2+3 | 30 |  | 2025-11-22 | 2025-11-23 | 2025-11-01 | 2025-11-28 | 2025-11-29
ta413 | TA413 | 2025-11-01 | Supervisor | Kamal Ravidas | 16/0 | 626666.7579 | 0 | 67.2617 | DC2+0 | 30 |  | 2025-11-09 | 2025-11-10 | 2025-11-01 | 2025-11-21 | 2025-11-22
ta413 | TA413 | 2025-11-01 | Supervisor | Kamal Ravidas | 17/0 | 613723.3938 | 0 | 65.8725 | DC1+3 | 30 |  | 2025-11-20 | 2025-11-21 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta413 | TA413 | 2025-11-01 | Supervisor | Sanjay Kumar | 43/0 | 516626.7066 | 0 | 55.4509 | DB1+0 | 30 |  | 2025-11-09 | 2025-11-10 | 2025-11-01 | 2025-11-19 | 2025-11-20
ta413 | TA413 | 2025-11-01 | Supervisor | Sanjay Kumar | 43/1 | 331695.9203 | 0 | 35.6018 | DA-1.5 | 30 |  | 2025-11-18 | 2025-11-19 | 2025-11-01 | 2025-12-05 | 2025-12-06
ta413 | TA413 | 2025-11-01 | Supervisor | Sanjay Kumar | 43/5 | 626666.7579 | 0 | 67.2617 | DC2+0 | 30 |  | 2025-12-04 | 2025-12-05 | 2025-11-01 | 2025-12-12 | 2025-12-13
ta413 | TA413 | 2025-11-01 | Supervisor | Tarique | 15/1 | 408118.8097 | 0 | 43.8044 | DA+6 | 30 |  | 2025-11-09 | 2025-11-10 | 2025-11-01 | 2025-11-18 | 2025-11-19
ta413 | TA413 | 2025-11-01 | Supervisor | Tarique | 15/7 | 336894.6611 | 0 | 36.1598 | DA+0 | 30 |  | 2025-11-17 | 2025-11-18 | 2025-11-01 | 2025-11-24 | 2025-11-25
ta413 | TA413 | 2025-11-01 | Supervisor | Tarique | 15/11 | 336894.6611 | 0 | 36.1598 | DA+0 | 30 |  | 2025-11-23 | 2025-11-24 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta413 | TA413 | 2025-11-01 | Supervisor | Raju Mahto | 21/4 | 336894.6611 | 0 | 36.1598 | DA+0 | 28 |  | 2025-11-10 | 2025-11-11 | 2025-11-01 | 2025-11-18 | 2025-11-19
ta413 | TA413 | 2025-11-01 | Supervisor | Raju Mahto | 21/5 | 336894.6611 | 0 | 36.1598 | DA+0 | 28 |  | 2025-11-17 | 2025-11-18 | 2025-11-01 | 2025-11-24 | 2025-11-25
ta413 | TA413 | 2025-11-01 | Supervisor | Raju Mahto | 15/12 | 408118.8097 | 0 | 43.8044 | DA+6 | 36 |  | 2025-11-23 | 2025-11-24 | 2025-11-01 | 2025-11-29 | 2025-11-30
ta416 | TA416 | 2025-11-01 | Gang | MAA CONSTRUCTION | 2/2 | 371402 | 0 | 43.776 | DA+0 | 27 | NO | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-08 | 2025-11-09
ta416 | TA416 | 2025-11-01 | Gang | MAA CONSTRUCTION | 53A/0 | 568303.9 | 0 | 64.482 | DB+0 | 27 | NO | 2025-11-08 | 2025-11-09 | 2025-11-01 | 2025-11-19 | 2025-11-20
ta416 | TA416 | 2025-11-01 | Gang | MAA CONSTRUCTION | 66/0 | 837742.5 | 0 | 97.229 | DD60+0 | 27 | NO | 2025-11-19 | 2025-11-20 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta416 | TA416 | 2025-11-01 | Gang | GOURISHANKAR | 22A/0 | 974538 | 0 | 110.575 | DB+25 |  |  | 2025-10-18 | 2025-10-19 | 2025-11-01 | 2025-11-11 | 2025-11-12
ta416 | TA416 | 2025-11-01 | Gang | GOURISHANKAR | 23/0 | 1004656 | 0 | 110.696 | DC+18 |  | NO | 2025-11-11 | 2025-11-12 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta416 | TA416 | 2025-11-01 | Gang | AMIT CHOUDHURY | 45/0 | 837742.5 | 837742.5 | 97.229 | DD60+0 | 25 | NO | 2025-10-24 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-09
ta416 | TA416 | 2025-11-01 | Gang | AMIT CHOUDHURY | 60/0 | 900193 | 0 | 101.933 | DD45+6 | 25 |  | 2025-11-05 | 2025-11-06 | 2025-11-01 | 2025-11-18 | 2025-11-19
ta416 | TA416 | 2025-11-01 | Gang | PUNAM KUMARI-1 | 49/0 | 828626.51 | 0 | 90.125 | DC+9 |  | NO | 2025-11-01 | 2025-11-02 | 2025-11-01 | 2025-11-14 | 2025-11-15
ta416 | TA416 | 2025-11-01 | Gang | PUNAM KUMARI-2 | 59/0 | 1005828 | 0 | 113.682 | DD60+6 |  | NO | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta416 | TA416 | 2025-11-01 | Gang | NIRANJAN SINGH | 64/1 | 371402 | 0 | 43.776 | DA+0 | 20 | NO | 2025-11-01 | 2025-11-02 | 2025-11-01 | 2025-11-14 | 2025-11-15
ta416 | TA416 | 2025-11-01 | Gang | NIRANJAN SINGH | 53A/7 | 371402 | 0 | 43.776 | DA+0 | 20 | NO | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta416 | TA416 | 2025-11-01 | Gang | PANKAJ KUMAR | 52/1 | 669569.35 | 669569.35 | 75.897 | DB+6 | 27 |  | 2025-11-01 | 2025-11-02 | 2025-11-01 | 2025-11-10 | 2025-11-11
ta416 | TA416 | 2025-11-01 | Gang | PANKAJ KUMAR | 62/0 | 1125399 | 0 | 124.037 | DC+25 | 27 | NO | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta416 | TA416 | 2025-11-01 | Gang | PUNAM KUMARI-2 | 55/0 | 666437.35 | 666437.35 | 73.426 | DC+0 | 24 |  | 2025-10-24 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-09
ta416 | TA416 | 2025-11-01 | Gang | PUNAM KUMARI-3 | 55/1 | 359483 | 0 | 42.374 | DA-3 | 24 |  | 2025-11-06 | 2025-11-07 | 2025-11-01 | 2025-11-13 | 2025-11-14
ta416 | TA416 | 2025-11-01 | Gang | PUNAM KUMARI-4 | 57/0 | 568303.9 | 0 | 64.482 | DB+0 | 24 | NO | 2025-11-13 | 2025-11-14 | 2025-11-01 | 2025-11-22 | 2025-11-23
ta416 | TA416 | 2025-11-01 | Gang | PUNAM KUMARI-5 | 57/1 | 359483 | 0 | 42.374 | DA-3 | 24 |  | 2025-11-22 | 2025-11-23 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta416 | TA416 | 2025-11-01 | Gang | PINKI DEWI | 56/6 | 371402 | 0 | 43.776 | DA+0 | 20 |  | 2025-11-03 | 2025-11-04 | 2025-11-01 | 2025-11-10 | 2025-11-11
ta416 | TA416 | 2025-11-01 | Gang | PINKI DEWI | 56/7 | 450627.94 | 0 | 53.324 | DA+6 | 20 | NO | 2025-11-10 | 2025-11-11 | 2025-11-01 | 2025-11-18 | 2025-11-19
ta416 | TA416 | 2025-11-01 | Gang | PINKI DEWI | 52/7 | 450627.94 | 0 | 53.324 | DA+6 | 20 | NO | 2025-11-18 | 2025-11-19 | 2025-11-01 | 2025-11-24 | 2025-11-25
ta416 | TA416 | 2025-11-01 | Gang | PINKI DEWI | 64/2 | 418848 | 0 | 46.049 | DA+3 | 20 |  | 2025-11-24 | 2025-11-25 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta416 | TA416 | 2025-11-01 | Gang | MAHON MAHTO | 61/0 | 1853580.61 | 0 | 188.378 | DD60+30 | 40 | NO | 2025-10-20 | 2025-10-21 | 2025-11-01 | 2025-11-07 | 2025-11-08
ta416 | TA416 | 2025-11-01 | Gang | MAHON MAHTO | 66/1 | 371402 | 0 | 43.776 | DA+0 | 40 |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta416 | TA416 | 2025-11-01 | Gang | KONGRESS | 69A/0 | 837742.5 | 0 | 97.229 | DD60+0 |  |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-11-19 | 2025-11-20
ta416 | TA416 | 2025-11-01 | Gang | KONGRESS | 70/0 | 837742.5 | 0 | 97.229 | DD60+0 |  | NO | 2025-11-19 | 2025-11-20 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta416 | TA416 | 2025-11-01 | Section Incharge | Prabin Patra | 2/2 | 371402 | 0 | 43.776 | DA+0 | 27 | NO | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-08 | 2025-11-09
ta416 | TA416 | 2025-11-01 | Section Incharge | D N Prasad | 53A/0 | 568303.9 | 0 | 64.482 | DB+0 | 27 | NO | 2025-11-08 | 2025-11-09 | 2025-11-01 | 2025-11-19 | 2025-11-20
ta416 | TA416 | 2025-11-01 | Section Incharge | D N Prasad | 66/0 | 837742.5 | 0 | 97.229 | DD60+0 | 27 | NO | 2025-11-19 | 2025-11-20 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta416 | TA416 | 2025-11-01 | Section Incharge | Prabin Patra | 22A/0 | 974538 | 0 | 110.575 | DB+25 |  |  | 2025-10-18 | 2025-10-19 | 2025-11-01 | 2025-11-11 | 2025-11-12
ta416 | TA416 | 2025-11-01 | Section Incharge | Prabin Patra | 23/0 | 1004656 | 0 | 110.696 | DC+18 |  | NO | 2025-11-11 | 2025-11-12 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta416 | TA416 | 2025-11-01 | Section Incharge | D N Prasad | 45/0 | 837742.5 | 837742.5 | 97.229 | DD60+0 | 25 | NO | 2025-10-24 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-09
ta416 | TA416 | 2025-11-01 | Section Incharge | D N Prasad | 60/0 | 900193 | 0 | 101.933 | DD45+6 | 25 |  | 2025-11-05 | 2025-11-06 | 2025-11-01 | 2025-11-18 | 2025-11-19
ta416 | TA416 | 2025-11-01 | Section Incharge | D N Prasad | 49/0 | 828626.51 | 0 | 90.125 | DC+9 |  | NO | 2025-11-01 | 2025-11-02 | 2025-11-01 | 2025-11-14 | 2025-11-15
ta416 | TA416 | 2025-11-01 | Section Incharge | D N Prasad | 59/0 | 1005828 | 0 | 113.682 | DD60+6 |  | NO | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta416 | TA416 | 2025-11-01 | Section Incharge | D N Prasad | 64/1 | 371402 | 0 | 43.776 | DA+0 | 20 | NO | 2025-11-01 | 2025-11-02 | 2025-11-01 | 2025-11-14 | 2025-11-15
ta416 | TA416 | 2025-11-01 | Section Incharge | D N Prasad | 53A/7 | 371402 | 0 | 43.776 | DA+0 | 20 | NO | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta416 | TA416 | 2025-11-01 | Section Incharge | D N Prasad | 52/1 | 669569.35 | 669569.35 | 75.897 | DB+6 | 27 |  | 2025-11-01 | 2025-11-02 | 2025-11-01 | 2025-11-10 | 2025-11-11
ta416 | TA416 | 2025-11-01 | Section Incharge | D N Prasad | 62/0 | 1125399 | 0 | 124.037 | DC+25 | 27 | NO | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta416 | TA416 | 2025-11-01 | Section Incharge | D N Prasad | 55/0 | 666437.35 | 666437.35 | 73.426 | DC+0 | 24 |  | 2025-10-24 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-09
ta416 | TA416 | 2025-11-01 | Section Incharge | D N Prasad | 55/1 | 359483 | 0 | 42.374 | DA-3 | 24 |  | 2025-11-06 | 2025-11-07 | 2025-11-01 | 2025-11-13 | 2025-11-14
ta416 | TA416 | 2025-11-01 | Section Incharge | D N Prasad | 57/0 | 568303.9 | 0 | 64.482 | DB+0 | 24 | NO | 2025-11-13 | 2025-11-14 | 2025-11-01 | 2025-11-22 | 2025-11-23
ta416 | TA416 | 2025-11-01 | Section Incharge | D N Prasad | 57/1 | 359483 | 0 | 42.374 | DA-3 | 24 |  | 2025-11-22 | 2025-11-23 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta416 | TA416 | 2025-11-01 | Section Incharge | D N Prasad | 56/6 | 371402 | 0 | 43.776 | DA+0 | 20 |  | 2025-11-03 | 2025-11-04 | 2025-11-01 | 2025-11-10 | 2025-11-11
ta416 | TA416 | 2025-11-01 | Section Incharge | D N Prasad | 56/7 | 450627.94 | 0 | 53.324 | DA+6 | 20 | NO | 2025-11-10 | 2025-11-11 | 2025-11-01 | 2025-11-18 | 2025-11-19
ta416 | TA416 | 2025-11-01 | Section Incharge | D N Prasad | 52/7 | 450627.94 | 0 | 53.324 | DA+6 | 20 | NO | 2025-11-18 | 2025-11-19 | 2025-11-01 | 2025-11-24 | 2025-11-25
ta416 | TA416 | 2025-11-01 | Section Incharge | D N Prasad | 64/2 | 418848 | 0 | 46.049 | DA+3 | 20 |  | 2025-11-24 | 2025-11-25 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta416 | TA416 | 2025-11-01 | Section Incharge | D N Prasad | 61/0 | 1853580.61 | 0 | 188.378 | DD60+30 | 40 | NO | 2025-10-20 | 2025-10-21 | 2025-11-01 | 2025-11-07 | 2025-11-08
ta416 | TA416 | 2025-11-01 | Section Incharge | D N Prasad | 66/1 | 371402 | 0 | 43.776 | DA+0 | 40 |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta416 | TA416 | 2025-11-01 | Section Incharge | D N Prasad | 69A/0 | 837742.5 | 0 | 97.229 | DD60+0 |  |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-11-19 | 2025-11-20
ta416 | TA416 | 2025-11-01 | Section Incharge | D N Prasad | 70/0 | 837742.5 | 0 | 97.229 | DD60+0 |  | NO | 2025-11-19 | 2025-11-20 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta416 | TA416 | 2025-11-01 | Supervisor | Churamani | 2/2 | 371402 | 0 | 43.776 | DA+0 | 27 | NO | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-08 | 2025-11-09
ta416 | TA416 | 2025-11-01 | Supervisor | Churamani | 53A/0 | 568303.9 | 0 | 64.482 | DB+0 | 27 | NO | 2025-11-08 | 2025-11-09 | 2025-11-01 | 2025-11-19 | 2025-11-20
ta416 | TA416 | 2025-11-01 | Supervisor | Churamani | 66/0 | 837742.5 | 0 | 97.229 | DD60+0 | 27 | NO | 2025-11-19 | 2025-11-20 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta416 | TA416 | 2025-11-01 | Supervisor | Rupesh | 22A/0 | 974538 | 0 | 110.575 | DB+25 |  |  | 2025-10-18 | 2025-10-19 | 2025-11-01 | 2025-11-11 | 2025-11-12
ta416 | TA416 | 2025-11-01 | Supervisor | Rupesh | 23/0 | 1004656 | 0 | 110.696 | DC+18 |  | NO | 2025-11-11 | 2025-11-12 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta416 | TA416 | 2025-11-01 | Supervisor | Afeludin | 45/0 | 837742.5 | 837742.5 | 97.229 | DD60+0 | 25 | NO | 2025-10-24 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-09
ta416 | TA416 | 2025-11-01 | Supervisor | Afeludin | 60/0 | 900193 | 0 | 101.933 | DD45+6 | 25 |  | 2025-11-05 | 2025-11-06 | 2025-11-01 | 2025-11-18 | 2025-11-19
ta416 | TA416 | 2025-11-01 | Supervisor | Saidur | 49/0 | 828626.51 | 0 | 90.125 | DC+9 |  | NO | 2025-11-01 | 2025-11-02 | 2025-11-01 | 2025-11-14 | 2025-11-15
ta416 | TA416 | 2025-11-01 | Supervisor | Saidur | 59/0 | 1005828 | 0 | 113.682 | DD60+6 |  | NO | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta416 | TA416 | 2025-11-01 | Supervisor | Ali raza | 64/1 | 371402 | 0 | 43.776 | DA+0 | 20 | NO | 2025-11-01 | 2025-11-02 | 2025-11-01 | 2025-11-14 | 2025-11-15
ta416 | TA416 | 2025-11-01 | Supervisor | Ali raza | 53A/7 | 371402 | 0 | 43.776 | DA+0 | 20 | NO | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta416 | TA416 | 2025-11-01 | Supervisor | Saidur | 52/1 | 669569.35 | 669569.35 | 75.897 | DB+6 | 27 |  | 2025-11-01 | 2025-11-02 | 2025-11-01 | 2025-11-10 | 2025-11-11
ta416 | TA416 | 2025-11-01 | Supervisor | Saidur | 62/0 | 1125399 | 0 | 124.037 | DC+25 | 27 | NO | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta416 | TA416 | 2025-11-01 | Supervisor | Akhtarul | 55/0 | 666437.35 | 666437.35 | 73.426 | DC+0 | 24 |  | 2025-10-24 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-09
ta416 | TA416 | 2025-11-01 | Supervisor | Akhtarul | 55/1 | 359483 | 0 | 42.374 | DA-3 | 24 |  | 2025-11-06 | 2025-11-07 | 2025-11-01 | 2025-11-13 | 2025-11-14
ta416 | TA416 | 2025-11-01 | Supervisor | Akhtarul | 57/0 | 568303.9 | 0 | 64.482 | DB+0 | 24 | NO | 2025-11-13 | 2025-11-14 | 2025-11-01 | 2025-11-22 | 2025-11-23
ta416 | TA416 | 2025-11-01 | Supervisor | Akhtarul | 57/1 | 359483 | 0 | 42.374 | DA-3 | 24 |  | 2025-11-22 | 2025-11-23 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta416 | TA416 | 2025-11-01 | Supervisor | Akhtarul | 56/6 | 371402 | 0 | 43.776 | DA+0 | 20 |  | 2025-11-03 | 2025-11-04 | 2025-11-01 | 2025-11-10 | 2025-11-11
ta416 | TA416 | 2025-11-01 | Supervisor | Akhtarul | 56/7 | 450627.94 | 0 | 53.324 | DA+6 | 20 | NO | 2025-11-10 | 2025-11-11 | 2025-11-01 | 2025-11-18 | 2025-11-19
ta416 | TA416 | 2025-11-01 | Supervisor | Akhtarul | 52/7 | 450627.94 | 0 | 53.324 | DA+6 | 20 | NO | 2025-11-18 | 2025-11-19 | 2025-11-01 | 2025-11-24 | 2025-11-25
ta416 | TA416 | 2025-11-01 | Supervisor | Akhtarul | 64/2 | 418848 | 0 | 46.049 | DA+3 | 20 |  | 2025-11-24 | 2025-11-25 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta416 | TA416 | 2025-11-01 | Supervisor | Somnath | 61/0 | 1853580.61 | 0 | 188.378 | DD60+30 | 40 | NO | 2025-10-20 | 2025-10-21 | 2025-11-01 | 2025-11-07 | 2025-11-08
ta416 | TA416 | 2025-11-01 | Supervisor | Somnath | 66/1 | 371402 | 0 | 43.776 | DA+0 | 40 |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta416 | TA416 | 2025-11-01 | Supervisor | Somnath | 69A/0 | 837742.5 | 0 | 97.229 | DD60+0 |  |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-11-19 | 2025-11-20
ta416 | TA416 | 2025-11-01 | Supervisor | Somnath | 70/0 | 837742.5 | 0 | 97.229 | DD60+0 |  | NO | 2025-11-19 | 2025-11-20 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta418 | TA418 | 2025-11-01 | Gang | M/s TOFIT MIA | 33/0 | 1150500 | 0 | 89.029 | DD45+18 | 28 |  | 2025-10-16 | 2025-10-19 | 2025-11-01 | 2025-11-07 | 2025-11-08
ta418 | TA418 | 2025-11-01 | Gang | M/s TOFIT MIA | 33/4 | 360000 | 0 | 29.122 | DA+3 | 28 |  | 2025-11-05 | 2025-11-06 | 2025-11-01 | 2025-11-11 | 2025-11-12
ta418 | TA418 | 2025-11-01 | Gang | M/s TOFIT MIA | 43/2 | 308000 | 0 | 27.963 | DA+0 | 28 |  | 2025-11-10 | 2025-11-11 | 2025-11-01 | 2025-11-15 | 2025-11-16
ta418 | TA418 | 2025-11-01 | Gang | M/s TOFIT MIA | 43/3 | 295000 | 0 | 26.846 | DA-3 | 28 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-11-19 | 2025-11-20
ta418 | TA418 | 2025-11-01 | Gang | M/s TOFIT MIA | 44/1 | 308000 | 0 | 27.963 | DA+0 | 28 |  | 2025-11-18 | 2025-11-19 | 2025-11-01 | 2025-11-24 | 2025-11-25
ta418 | TA418 | 2025-11-01 | Gang | M/s TOFIT MIA | 38/0 | 809000 | 0 | 73.176 | DD60+6 | 28 |  | 2025-11-23 | 2025-11-24 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta418 | TA418 | 2025-11-01 | Gang | M/s BARKAT ALI | 46/10 | 295000 | 0 | 26.846 | DA-3 | 25 |  | 2025-10-29 | 2025-10-30 | 2025-11-01 | 2025-11-06 | 2025-11-07
ta418 | TA418 | 2025-11-01 | Gang | M/s BARKAT ALI | 46/6 | 308000 | 0 | 27.963 | DA+0 | 25 |  | 2025-11-05 | 2025-11-06 | 2025-11-01 | 2025-11-11 | 2025-11-12
ta418 | TA418 | 2025-11-01 | Gang | M/s BARKAT ALI | 46/11 | 304000 | 0 | 27.601 | DA-1.5 | 25 |  | 2025-11-11 | 2025-11-12 | 2025-11-01 | 2025-11-17 | 2025-11-18
ta418 | TA418 | 2025-11-01 | Gang | M/s BARKAT ALI | 46/1 | 295000 | 0 | 26.846 | DA-3 | 25 |  | 2025-11-16 | 2025-11-17 | 2025-11-01 | 2025-11-22 | 2025-11-23
ta418 | TA418 | 2025-11-01 | Gang | M/s BARKAT ALI | 48/0 | 488000 | 0 | 45.136 | DB2+0 | 25 |  | 2025-11-22 | 2025-11-23 | 2025-11-01 | 2025-11-30 | 2025-12-01
ta418 | TA418 | 2025-11-01 | Gang | M/s MDPL | 39/0 | 1151000 | 0 | 89.029 | DD45+18 | 24 |  | 2025-10-16 | 2025-10-19 | 2025-11-01 | 2025-11-08 | 2025-11-09
ta418 | TA418 | 2025-11-01 | Gang | M/s MDPL | 47/0 | 562000 | 0 | 51.673 | DC1+0 | 24 |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-11-15 | 2025-11-16
ta418 | TA418 | 2025-11-01 | Gang | M/s MDPL | 47/1 | 360000 | 0 | 29.122 | DA+3 | 24 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-11-20 | 2025-11-21
ta418 | TA418 | 2025-11-01 | Gang | M/s MDPL | 54/2 | 295000 | 0 | 26.846 | DA-3 | 24 |  | 2025-11-19 | 2025-11-20 | 2025-11-01 | 2025-11-25 | 2025-11-26
ta418 | TA418 | 2025-11-01 | Gang | M/s MDPL | 52/1 | 295000 | 0 | 26.846 | DA-3 | 24 |  | 2025-11-24 | 2025-11-25 | 2025-11-01 | 2025-11-30 | 2025-12-01
ta418 | TA418 | 2025-11-01 | Gang | Team - 04 | 52/2 | 295000 | 0 | 26.846 | DA-3 | 25 |  | 2025-11-08 | 2025-11-09 | 2025-11-01 | 2025-11-14 | 2025-11-15
ta418 | TA418 | 2025-11-01 | Gang | Team - 04 | 56/1 | 374000 | 0 | 33.304 | DA+6 | 25 |  | 2025-11-13 | 2025-11-14 | 2025-11-01 | 2025-11-19 | 2025-11-20
ta418 | TA418 | 2025-11-01 | Gang | Team - 04 | 56/2 | 295000 | 0 | 26.846 | DA-3 | 25 |  | 2025-11-18 | 2025-11-19 | 2025-11-01 | 2025-11-24 | 2025-11-25
ta418 | TA418 | 2025-11-01 | Gang | Team - 04 | 56/3 | 594000 | 0 | 52.141 | DB1+6 | 25 |  | 2025-11-23 | 2025-11-24 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta418 | TA418 | 2025-11-01 | Section Incharge | Ajith | 33/0 | 1150500 | 0 | 89.029 | DD45+18 | 28 |  | 2025-10-16 | 2025-10-19 | 2025-11-01 | 2025-11-07 | 2025-11-08
ta418 | TA418 | 2025-11-01 | Section Incharge | Ajith | 33/4 | 360000 | 0 | 29.122 | DA+3 | 28 |  | 2025-11-05 | 2025-11-06 | 2025-11-01 | 2025-11-11 | 2025-11-12
ta418 | TA418 | 2025-11-01 | Section Incharge | Ajith | 43/2 | 308000 | 0 | 27.963 | DA+0 | 28 |  | 2025-11-10 | 2025-11-11 | 2025-11-01 | 2025-11-15 | 2025-11-16
ta418 | TA418 | 2025-11-01 | Section Incharge | Ajith | 43/3 | 295000 | 0 | 26.846 | DA-3 | 28 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-11-19 | 2025-11-20
ta418 | TA418 | 2025-11-01 | Section Incharge | Ajith | 44/1 | 308000 | 0 | 27.963 | DA+0 | 28 |  | 2025-11-18 | 2025-11-19 | 2025-11-01 | 2025-11-24 | 2025-11-25
ta418 | TA418 | 2025-11-01 | Section Incharge | Ajith | 38/0 | 809000 | 0 | 73.176 | DD60+6 | 28 |  | 2025-11-23 | 2025-11-24 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta418 | TA418 | 2025-11-01 | Section Incharge | Ajith | 46/10 | 295000 | 0 | 26.846 | DA-3 | 25 |  | 2025-10-29 | 2025-10-30 | 2025-11-01 | 2025-11-06 | 2025-11-07
ta418 | TA418 | 2025-11-01 | Section Incharge | Ajith | 46/6 | 308000 | 0 | 27.963 | DA+0 | 25 |  | 2025-11-05 | 2025-11-06 | 2025-11-01 | 2025-11-11 | 2025-11-12
ta418 | TA418 | 2025-11-01 | Section Incharge | Ajith | 46/11 | 304000 | 0 | 27.601 | DA-1.5 | 25 |  | 2025-11-11 | 2025-11-12 | 2025-11-01 | 2025-11-17 | 2025-11-18
ta418 | TA418 | 2025-11-01 | Section Incharge | Ajith | 46/1 | 295000 | 0 | 26.846 | DA-3 | 25 |  | 2025-11-16 | 2025-11-17 | 2025-11-01 | 2025-11-22 | 2025-11-23
ta418 | TA418 | 2025-11-01 | Section Incharge | Ajith | 48/0 | 488000 | 0 | 45.136 | DB2+0 | 25 |  | 2025-11-22 | 2025-11-23 | 2025-11-01 | 2025-11-30 | 2025-12-01
ta418 | TA418 | 2025-11-01 | Section Incharge | Ajith | 39/0 | 1151000 | 0 | 89.029 | DD45+18 | 24 |  | 2025-10-16 | 2025-10-19 | 2025-11-01 | 2025-11-08 | 2025-11-09
ta418 | TA418 | 2025-11-01 | Section Incharge | Ajith | 47/0 | 562000 | 0 | 51.673 | DC1+0 | 24 |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-11-15 | 2025-11-16
ta418 | TA418 | 2025-11-01 | Section Incharge | Ajith | 47/1 | 360000 | 0 | 29.122 | DA+3 | 24 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-11-20 | 2025-11-21
ta418 | TA418 | 2025-11-01 | Section Incharge | Ajith | 54/2 | 295000 | 0 | 26.846 | DA-3 | 24 |  | 2025-11-19 | 2025-11-20 | 2025-11-01 | 2025-11-25 | 2025-11-26
ta418 | TA418 | 2025-11-01 | Section Incharge | Ajith | 52/1 | 295000 | 0 | 26.846 | DA-3 | 24 |  | 2025-11-24 | 2025-11-25 | 2025-11-01 | 2025-11-30 | 2025-12-01
ta418 | TA418 | 2025-11-01 | Section Incharge | Ajith | 52/2 | 295000 | 0 | 26.846 | DA-3 | 25 |  | 2025-11-08 | 2025-11-09 | 2025-11-01 | 2025-11-14 | 2025-11-15
ta418 | TA418 | 2025-11-01 | Section Incharge | Ajith | 56/1 | 374000 | 0 | 33.304 | DA+6 | 25 |  | 2025-11-13 | 2025-11-14 | 2025-11-01 | 2025-11-19 | 2025-11-20
ta418 | TA418 | 2025-11-01 | Section Incharge | Ajith | 56/2 | 295000 | 0 | 26.846 | DA-3 | 25 |  | 2025-11-18 | 2025-11-19 | 2025-11-01 | 2025-11-24 | 2025-11-25
ta418 | TA418 | 2025-11-01 | Section Incharge | Ajith | 56/3 | 594000 | 0 | 52.141 | DB1+6 | 25 |  | 2025-11-23 | 2025-11-24 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta418 | TA418 | 2025-11-01 | Supervisor | Rahman | 33/0 | 1150500 | 0 | 89.029 | DD45+18 | 28 |  | 2025-10-16 | 2025-10-19 | 2025-11-01 | 2025-11-07 | 2025-11-08
ta418 | TA418 | 2025-11-01 | Supervisor | Rahman | 33/4 | 360000 | 0 | 29.122 | DA+3 | 28 |  | 2025-11-05 | 2025-11-06 | 2025-11-01 | 2025-11-11 | 2025-11-12
ta418 | TA418 | 2025-11-01 | Supervisor | Rahman | 43/2 | 308000 | 0 | 27.963 | DA+0 | 28 |  | 2025-11-10 | 2025-11-11 | 2025-11-01 | 2025-11-15 | 2025-11-16
ta418 | TA418 | 2025-11-01 | Supervisor | Rahman | 43/3 | 295000 | 0 | 26.846 | DA-3 | 28 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-11-19 | 2025-11-20
ta418 | TA418 | 2025-11-01 | Supervisor | Rahman | 44/1 | 308000 | 0 | 27.963 | DA+0 | 28 |  | 2025-11-18 | 2025-11-19 | 2025-11-01 | 2025-11-24 | 2025-11-25
ta418 | TA418 | 2025-11-01 | Supervisor | Rahman | 38/0 | 809000 | 0 | 73.176 | DD60+6 | 28 |  | 2025-11-23 | 2025-11-24 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta418 | TA418 | 2025-11-01 | Supervisor | Jitender Kumar | 46/10 | 295000 | 0 | 26.846 | DA-3 | 25 |  | 2025-10-29 | 2025-10-30 | 2025-11-01 | 2025-11-06 | 2025-11-07
ta418 | TA418 | 2025-11-01 | Supervisor | Jitender Kumar | 46/6 | 308000 | 0 | 27.963 | DA+0 | 25 |  | 2025-11-05 | 2025-11-06 | 2025-11-01 | 2025-11-11 | 2025-11-12
ta418 | TA418 | 2025-11-01 | Supervisor | Jitender Kumar | 46/11 | 304000 | 0 | 27.601 | DA-1.5 | 25 |  | 2025-11-11 | 2025-11-12 | 2025-11-01 | 2025-11-17 | 2025-11-18
ta418 | TA418 | 2025-11-01 | Supervisor | Jitender Kumar | 46/1 | 295000 | 0 | 26.846 | DA-3 | 25 |  | 2025-11-16 | 2025-11-17 | 2025-11-01 | 2025-11-22 | 2025-11-23
ta418 | TA418 | 2025-11-01 | Supervisor | Jitender Kumar | 48/0 | 488000 | 0 | 45.136 | DB2+0 | 25 |  | 2025-11-22 | 2025-11-23 | 2025-11-01 | 2025-11-30 | 2025-12-01
ta418 | TA418 | 2025-11-01 | Supervisor | Prabhu Prasad | 39/0 | 1151000 | 0 | 89.029 | DD45+18 | 24 |  | 2025-10-16 | 2025-10-19 | 2025-11-01 | 2025-11-08 | 2025-11-09
ta418 | TA418 | 2025-11-01 | Supervisor | Prabhu Prasad | 47/0 | 562000 | 0 | 51.673 | DC1+0 | 24 |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-11-15 | 2025-11-16
ta418 | TA418 | 2025-11-01 | Supervisor | Prabhu Prasad | 47/1 | 360000 | 0 | 29.122 | DA+3 | 24 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-11-20 | 2025-11-21
ta418 | TA418 | 2025-11-01 | Supervisor | Prabhu Prasad | 54/2 | 295000 | 0 | 26.846 | DA-3 | 24 |  | 2025-11-19 | 2025-11-20 | 2025-11-01 | 2025-11-25 | 2025-11-26
ta418 | TA418 | 2025-11-01 | Supervisor | Prabhu Prasad | 52/1 | 295000 | 0 | 26.846 | DA-3 | 24 |  | 2025-11-24 | 2025-11-25 | 2025-11-01 | 2025-11-30 | 2025-12-01
ta418 | TA418 | 2025-11-01 | Supervisor | Basudev Mahato | 52/2 | 295000 | 0 | 26.846 | DA-3 | 25 |  | 2025-11-08 | 2025-11-09 | 2025-11-01 | 2025-11-14 | 2025-11-15
ta418 | TA418 | 2025-11-01 | Supervisor | Basudev Mahato | 56/1 | 374000 | 0 | 33.304 | DA+6 | 25 |  | 2025-11-13 | 2025-11-14 | 2025-11-01 | 2025-11-19 | 2025-11-20
ta418 | TA418 | 2025-11-01 | Supervisor | Basudev Mahato | 56/2 | 295000 | 0 | 26.846 | DA-3 | 25 |  | 2025-11-18 | 2025-11-19 | 2025-11-01 | 2025-11-24 | 2025-11-25
ta418 | TA418 | 2025-11-01 | Supervisor | Basudev Mahato | 56/3 | 594000 | 0 | 52.141 | DB1+6 | 25 |  | 2025-11-23 | 2025-11-24 | 2025-11-01 | 2025-12-01 | 2025-12-02
ta419 | TA419 | 2025-11-01 | Gang | Infineda 1 | 2/0 | 651015 | 0 | 85 | DB2+18 | 20 |  | 2025-11-02 | 2025-11-03 | 2025-11-01 | 2025-11-22 | 2025-11-17
ta419 | TA419 | 2025-11-01 | Gang | Infineda 1 | 3/0 | 804195 | 0 | 105 | DD45+18 | 20 |  | 2025-11-13 | 2025-11-14 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Gang | Radha Enterpises 1 | 38/8 | 290514.203 | 0 | 37.9311 | DA+3 | 25 |  | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-17 | 2025-11-12
ta419 | TA419 | 2025-11-01 | Gang | Radha Enterpises 1 | 38/9 | 272673.8952 | 0 | 35.6018 | DA-1.5 | 25 |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-11-24 | 2025-11-19
ta419 | TA419 | 2025-11-01 | Gang | Radha Enterpises 1 | 38/10 | 276947.5712 | 0 | 36.1598 | DA+0 | 25 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-12-01 | 2025-11-26
ta419 | TA419 | 2025-11-01 | Gang | Radha Enterpises 1 | 38/11 | 276947.5712 | 0 | 36.1598 | DA+0 | 25 |  | 2025-11-21 | 2025-11-22 | 2025-11-01
ta419 | TA419 | 2025-11-01 | Gang | Poonam Kumari 1 | 35/0 | 590332.2222 | 0 | 77.0769 | DD45+3 | 27 |  | 2025-10-26 | 2025-10-27 | 2025-11-01 | 2025-11-16 | 2025-11-11
ta419 | TA419 | 2025-11-01 | Gang | Poonam Kumari 1 | 36/0 | 576492.93 | 0 | 75.27 | DC1+9 | 27 |  | 2025-11-06 | 2025-11-07 | 2025-11-01 | 2025-11-26 | 2025-11-21
ta419 | TA419 | 2025-11-01 | Gang | Poonam Kumari 1 | 41/1 | 266455.1548 | 0 | 34.7898 | DA-3 | 27 |  | 2025-11-16 | 2025-11-17 | 2025-11-01 | 2025-12-02 | 2025-11-27
ta419 | TA419 | 2025-11-01 | Gang | Poonam Kumari 1 | 41/3 | 276947.5712 | 0 | 36.1598 | DA+0 | 27 |  | 2025-11-22 | 2025-11-23 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Gang | Poonam kumari 2 | 30/0 | 560979.9931 | 0 | 73.2445 | DD45+0 | 26 |  | 2025-10-25 | 2025-10-26 | 2025-11-01 | 2025-11-18 | 2025-11-13
ta419 | TA419 | 2025-11-01 | Gang | Poonam kumari 2 | 38/0 | 1049636.1718 | 0 | 137.0461 | DD60+25 | 26 |  | 2025-11-09 | 2025-11-10 | 2025-11-01 | 2025-12-03 | 2025-11-28
ta419 | TA419 | 2025-11-01 | Gang | Poonam kumari 2 | 43/1 | 349993.4915 | 0 | 45.697 | DA+9 | 26 |  | 2025-11-23 | 2025-11-24 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Gang | Jwala Singh | 36/8 | 276947.5712 | 0 | 36.1598 | DA+0 | 22 |  | 2025-11-01 | 2025-11-02 | 2025-11-01 | 2025-11-18 | 2025-11-13
ta419 | TA419 | 2025-11-01 | Gang | Jwala Singh | 38/5 | 335498.0834 | 0 | 43.8044 | DA+6 | 22 |  | 2025-11-08 | 2025-11-09 | 2025-11-01 | 2025-11-24 | 2025-11-19
ta419 | TA419 | 2025-11-01 | Gang | Jwala Singh | 38/6 | 284442.4235 | 0 | 37.1383 | DA+1.5 | 22 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-12-01 | 2025-11-26
ta419 | TA419 | 2025-11-01 | Gang | Jwala Singh | 38/7 | 290514.203 | 0 | 37.9311 | DA+3 | 22 |  | 2025-11-21 | 2025-11-22 | 2025-11-01 | 2025-12-09 | 2025-12-04
ta419 | TA419 | 2025-11-01 | Gang | Madhu Sah | 40/2 | 290514.203 | 0 | 37.9311 | DA+3 | 24 |  | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-17 | 2025-11-12
ta419 | TA419 | 2025-11-01 | Gang | Madhu Sah | 40/3 | 290514.203 | 0 | 37.9311 | DA+3 | 24 |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-11-24 | 2025-11-19
ta419 | TA419 | 2025-11-01 | Gang | Madhu Sah | 40/4 | 284442.4235 | 0 | 37.1383 | DA+1.5 | 24 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-12-01 | 2025-11-26
ta419 | TA419 | 2025-11-01 | Gang | Madhu Sah | 40/5 | 284442.4235 | 0 | 37.1383 | DA+1.5 | 24 |  | 2025-11-21 | 2025-11-22 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Gang | Dasrath Mahato | 9/0 | 626720.652 | 0 | 81.828 | DC2+9 | 33 |  | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-22 | 2025-11-17
ta419 | TA419 | 2025-11-01 | Gang | Dasrath Mahato | 11/0 | 1232670.096 | 0 | 160.944 | DD60+30 | 33 |  | 2025-11-12 | 2025-11-13 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Gang | Infineda 2 | 62/1 | 408408.516 | 0 | 53.324 | 5DA+6 | 27 |  | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-17 | 2025-11-12
ta419 | TA419 | 2025-11-01 | Gang | Infineda 2 | 62/2 | 408408.516 | 0 | 53.324 | 5DA+6 | 27 |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-11-24 | 2025-11-19
ta419 | TA419 | 2025-11-01 | Gang | Infineda 2 | 62/3 | 581057.694 | 0 | 75.866 | 5DB1+6 | 27 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 1900-02-01 | 1900-01-27
ta419 | TA419 | 2025-11-01 | Gang | Infineda 2 | 62/4 | 324542.466 | 0 | 42.374 | 5DA-3 | 27 |  | 2025-11-23 | 2025-11-24 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Gang | GRD 1 | 46/1 | 335280.384 | 0 | 43.776 | 5DA+0 | 23 |  | 2025-11-05 | 2025-11-06 | 2025-11-01 | 2025-11-23 | 2025-11-18
ta419 | TA419 | 2025-11-01 | Gang | GRD 1 | 46/2 | 352689.291 | 0 | 46.049 | 5DA+3 | 23 |  | 2025-11-13 | 2025-11-14 | 2025-11-01 | 2025-12-02 | 2025-11-27
ta419 | TA419 | 2025-11-01 | Gang | GRD 1 | 46/3 | 335280.384 | 0 | 43.776 | 5DA+0 | 23 |  | 2025-11-22 | 2025-11-23 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Gang | Sanjeev | 78/1 | 335280.384 | 0 | 43.776 | 5DA+0 | 28 |  | 2025-11-05 | 2025-11-06 | 2025-11-01 | 2025-11-23 | 2025-11-18
ta419 | TA419 | 2025-11-01 | Gang | Sanjeev | 78/3 | 335280.384 | 0 | 43.776 | 5DA+0 | 28 |  | 2025-11-13 | 2025-11-14 | 2025-11-01 | 2025-12-02 | 2025-11-27
ta419 | TA419 | 2025-11-01 | Gang | Sanjeev | 76/3 | 352689.291 | 0 | 46.049 | 5DA+3 | 28 |  | 2025-11-22 | 2025-11-23 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Gang | Samuel | 83/5 | 324542.466 | 0 | 42.374 | 5DA-3 | 30 |  | 2025-11-09 | 2025-11-10 | 2025-11-01 | 2025-11-29 | 2025-11-24
ta419 | TA419 | 2025-11-01 | Gang | Samuel | 83/6 | 324542.466 | 0 | 42.374 | 5DA-3 | 30 |  | 2025-11-19 | 2025-11-20 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Gang | Mukhilal 1 | 84/1 | 335280.384 | 0 | 43.776 | 5DA+0 | 26 |  | 2025-11-09 | 2025-11-10 | 2025-11-01 | 2025-11-29 | 2025-11-24
ta419 | TA419 | 2025-11-01 | Gang | Mukhilal 1 | 84/4 | 324542.466 | 0 | 42.374 | 5DA-3 | 26 |  | 2025-11-19 | 2025-11-20 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Gang | Nandlal | 41/4 | 335498.0834 | 0 | 43.8044 | DA+6 | 29 |  | 2025-11-09 | 2025-11-10 | 2025-11-01 | 2025-11-29 | 2025-11-24
ta419 | TA419 | 2025-11-01 | Gang | Nandlal | 41/5 | 284442.4235 | 0 | 37.1383 | DA+1.5 | 29 |  | 2025-11-19 | 2025-11-20 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Gang | Jagdish | 40/6 | 284442.4235 | 0 | 37.1383 | DA+1.5 | 24 |  | 2025-11-09 | 2025-11-10 | 2025-11-01 | 2025-11-30 | 2025-11-25
ta419 | TA419 | 2025-11-01 | Gang | Jagdish | 40/7 | 272673.8952 | 0 | 35.6018 | DA-1.5 | 24 |  | 2025-11-20 | 2025-11-21 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Gang | GRD 2 | 41/6 | 290514.203 | 0 | 37.9311 | DA+3 | 27 |  | 2025-01-11 | 2025-01-12 | 2025-11-01 | 2025-12-01 | 2025-11-26
ta419 | TA419 | 2025-11-01 | Gang | GRD 2 | 41/7 | 276947.5712 | 0 | 36.1598 | DA+0 | 27 |  | 2025-11-21 | 2025-11-22 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Gang | Radha Enterpises 2 | 45/0 | 907055.37 | 0 | 118.43 | 5DD60+9 | 28 |  | 2025-11-11 | 2025-11-12 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Gang | Mukhilal 2 | 83/7 | 335280.384 | 0 | 43.776 | 5DA+0 | 25 |  | 2025-11-11 | 2025-11-12 | 2025-11-01 | 2025-11-30 | 2025-11-25
ta419 | TA419 | 2025-11-01 | Gang | Mukhilal 2 | 83/1 | 423841.401 | 0 | 55.339 | 5DA+9 | 25 |  | 2025-11-20 | 2025-11-21 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Gang | Sanjeet | 40/0 | 956991.6824 | 0 | 124.95 | DD60+18 | 29 |  | 2025-11-12 | 2025-11-13 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Gang | Lillo Mahato | 41/0 | 636719.6756 | 0 | 83.1335 | DD60+0 | 29 |  | 2025-11-12 | 2025-11-13 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Gang | Jwala Singh 2 | 43/0 | 956991.6824 | 0 | 124.95 | DD60+18 | 30 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Gang | Punam Kumari 3 | 46/0 | 1098775.458 | 0 | 143.462 | 5DD60+18 | 29 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 2/0 | 651015 | 0 | 85 | DB2+18 | 20 |  | 2025-11-02 | 2025-11-03 | 2025-11-01 | 2025-11-22 | 2025-11-17
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 3/0 | 804195 | 0 | 105 | DD45+18 | 20 |  | 2025-11-13 | 2025-11-14 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 38/8 | 290514.203 | 0 | 37.9311 | DA+3 | 25 |  | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-17 | 2025-11-12
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 38/9 | 272673.8952 | 0 | 35.6018 | DA-1.5 | 25 |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-11-24 | 2025-11-19
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 38/10 | 276947.5712 | 0 | 36.1598 | DA+0 | 25 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-12-01 | 2025-11-26
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 38/11 | 276947.5712 | 0 | 36.1598 | DA+0 | 25 |  | 2025-11-21 | 2025-11-22 | 2025-11-01
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 35/0 | 590332.2222 | 0 | 77.0769 | DD45+3 | 27 |  | 2025-10-26 | 2025-10-27 | 2025-11-01 | 2025-11-16 | 2025-11-11
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 36/0 | 576492.93 | 0 | 75.27 | DC1+9 | 27 |  | 2025-11-06 | 2025-11-07 | 2025-11-01 | 2025-11-26 | 2025-11-21
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 41/1 | 266455.1548 | 0 | 34.7898 | DA-3 | 27 |  | 2025-11-16 | 2025-11-17 | 2025-11-01 | 2025-12-02 | 2025-11-27
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 41/3 | 276947.5712 | 0 | 36.1598 | DA+0 | 27 |  | 2025-11-22 | 2025-11-23 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 30/0 | 560979.9931 | 0 | 73.2445 | DD45+0 | 26 |  | 2025-10-25 | 2025-10-26 | 2025-11-01 | 2025-11-18 | 2025-11-13
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 38/0 | 1049636.1718 | 0 | 137.0461 | DD60+25 | 26 |  | 2025-11-09 | 2025-11-10 | 2025-11-01 | 2025-12-03 | 2025-11-28
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 43/1 | 349993.4915 | 0 | 45.697 | DA+9 | 26 |  | 2025-11-23 | 2025-11-24 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 36/8 | 276947.5712 | 0 | 36.1598 | DA+0 | 22 |  | 2025-11-01 | 2025-11-02 | 2025-11-01 | 2025-11-18 | 2025-11-13
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 38/5 | 335498.0834 | 0 | 43.8044 | DA+6 | 22 |  | 2025-11-08 | 2025-11-09 | 2025-11-01 | 2025-11-24 | 2025-11-19
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 38/6 | 284442.4235 | 0 | 37.1383 | DA+1.5 | 22 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-12-01 | 2025-11-26
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 38/7 | 290514.203 | 0 | 37.9311 | DA+3 | 22 |  | 2025-11-21 | 2025-11-22 | 2025-11-01 | 2025-12-09 | 2025-12-04
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 40/2 | 290514.203 | 0 | 37.9311 | DA+3 | 24 |  | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-17 | 2025-11-12
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 40/3 | 290514.203 | 0 | 37.9311 | DA+3 | 24 |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-11-24 | 2025-11-19
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 40/4 | 284442.4235 | 0 | 37.1383 | DA+1.5 | 24 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-12-01 | 2025-11-26
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 40/5 | 284442.4235 | 0 | 37.1383 | DA+1.5 | 24 |  | 2025-11-21 | 2025-11-22 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 9/0 | 626720.652 | 0 | 81.828 | DC2+9 | 33 |  | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-22 | 2025-11-17
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 11/0 | 1232670.096 | 0 | 160.944 | DD60+30 | 33 |  | 2025-11-12 | 2025-11-13 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. R.N Tyagi | 62/1 | 408408.516 | 0 | 53.324 | 5DA+6 | 27 |  | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-17 | 2025-11-12
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. R.N Tyagi | 62/2 | 408408.516 | 0 | 53.324 | 5DA+6 | 27 |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-11-24 | 2025-11-19
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. R.N Tyagi | 62/3 | 581057.694 | 0 | 75.866 | 5DB1+6 | 27 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 1900-02-01 | 1900-01-27
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. R.N Tyagi | 62/4 | 324542.466 | 0 | 42.374 | 5DA-3 | 27 |  | 2025-11-23 | 2025-11-24 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. R.N Tyagi | 46/1 | 335280.384 | 0 | 43.776 | 5DA+0 | 23 |  | 2025-11-05 | 2025-11-06 | 2025-11-01 | 2025-11-23 | 2025-11-18
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. R.N Tyagi | 46/2 | 352689.291 | 0 | 46.049 | 5DA+3 | 23 |  | 2025-11-13 | 2025-11-14 | 2025-11-01 | 2025-12-02 | 2025-11-27
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. R.N Tyagi | 46/3 | 335280.384 | 0 | 43.776 | 5DA+0 | 23 |  | 2025-11-22 | 2025-11-23 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. R.N Tyagi | 78/1 | 335280.384 | 0 | 43.776 | 5DA+0 | 28 |  | 2025-11-05 | 2025-11-06 | 2025-11-01 | 2025-11-23 | 2025-11-18
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. R.N Tyagi | 78/3 | 335280.384 | 0 | 43.776 | 5DA+0 | 28 |  | 2025-11-13 | 2025-11-14 | 2025-11-01 | 2025-12-02 | 2025-11-27
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. R.N Tyagi | 76/3 | 352689.291 | 0 | 46.049 | 5DA+3 | 28 |  | 2025-11-22 | 2025-11-23 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. R.N Tyagi | 83/5 | 324542.466 | 0 | 42.374 | 5DA-3 | 30 |  | 2025-11-09 | 2025-11-10 | 2025-11-01 | 2025-11-29 | 2025-11-24
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. R.N Tyagi | 83/6 | 324542.466 | 0 | 42.374 | 5DA-3 | 30 |  | 2025-11-19 | 2025-11-20 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. R.N Tyagi | 84/1 | 335280.384 | 0 | 43.776 | 5DA+0 | 26 |  | 2025-11-09 | 2025-11-10 | 2025-11-01 | 2025-11-29 | 2025-11-24
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. R.N Tyagi | 84/4 | 324542.466 | 0 | 42.374 | 5DA-3 | 26 |  | 2025-11-19 | 2025-11-20 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 41/4 | 335498.0834 | 0 | 43.8044 | DA+6 | 29 |  | 2025-11-09 | 2025-11-10 | 2025-11-01 | 2025-11-29 | 2025-11-24
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 41/5 | 284442.4235 | 0 | 37.1383 | DA+1.5 | 29 |  | 2025-11-19 | 2025-11-20 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 40/6 | 284442.4235 | 0 | 37.1383 | DA+1.5 | 24 |  | 2025-11-09 | 2025-11-10 | 2025-11-01 | 2025-11-30 | 2025-11-25
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 40/7 | 272673.8952 | 0 | 35.6018 | DA-1.5 | 24 |  | 2025-11-20 | 2025-11-21 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 41/6 | 290514.203 | 0 | 37.9311 | DA+3 | 27 |  | 2025-01-11 | 2025-01-12 | 2025-11-01 | 2025-12-01 | 2025-11-26
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 41/7 | 276947.5712 | 0 | 36.1598 | DA+0 | 27 |  | 2025-11-21 | 2025-11-22 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. R.N Tyagi | 45/0 | 907055.37 | 0 | 118.43 | 5DD60+9 | 28 |  | 2025-11-11 | 2025-11-12 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. R.N Tyagi | 83/7 | 335280.384 | 0 | 43.776 | 5DA+0 | 25 |  | 2025-11-11 | 2025-11-12 | 2025-11-01 | 2025-11-30 | 2025-11-25
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. R.N Tyagi | 83/1 | 423841.401 | 0 | 55.339 | 5DA+9 | 25 |  | 2025-11-20 | 2025-11-21 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 40/0 | 956991.6824 | 0 | 124.95 | DD60+18 | 29 |  | 2025-11-12 | 2025-11-13 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 41/0 | 636719.6756 | 0 | 83.1335 | DD60+0 | 29 |  | 2025-11-12 | 2025-11-13 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. Tanay Kumar | 43/0 | 956991.6824 | 0 | 124.95 | DD60+18 | 30 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Section Incharge | Mr. R.N Tyagi | 46/0 | 1098775.458 | 0 | 143.462 | 5DD60+18 | 29 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. P.D Sharma | 2/0 | 651015 | 0 | 85 | DB2+18 | 20 |  | 2025-11-02 | 2025-11-03 | 2025-11-01 | 2025-11-22 | 2025-11-17
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. P.D Sharma | 3/0 | 804195 | 0 | 105 | DD45+18 | 20 |  | 2025-11-13 | 2025-11-14 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Prince | 38/8 | 290514.203 | 0 | 37.9311 | DA+3 | 25 |  | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-17 | 2025-11-12
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Prince | 38/9 | 272673.8952 | 0 | 35.6018 | DA-1.5 | 25 |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-11-24 | 2025-11-19
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Prince | 38/10 | 276947.5712 | 0 | 36.1598 | DA+0 | 25 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-12-01 | 2025-11-26
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Prince | 38/11 | 276947.5712 | 0 | 36.1598 | DA+0 | 25 |  | 2025-11-21 | 2025-11-22 | 2025-11-01
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Shivbrat | 35/0 | 590332.2222 | 0 | 77.0769 | DD45+3 | 27 |  | 2025-10-26 | 2025-10-27 | 2025-11-01 | 2025-11-16 | 2025-11-11
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Shivbrat | 36/0 | 576492.93 | 0 | 75.27 | DC1+9 | 27 |  | 2025-11-06 | 2025-11-07 | 2025-11-01 | 2025-11-26 | 2025-11-21
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Shivbrat | 41/1 | 266455.1548 | 0 | 34.7898 | DA-3 | 27 |  | 2025-11-16 | 2025-11-17 | 2025-11-01 | 2025-12-02 | 2025-11-27
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Shivbrat | 41/3 | 276947.5712 | 0 | 36.1598 | DA+0 | 27 |  | 2025-11-22 | 2025-11-23 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Suresh Ram | 30/0 | 560979.9931 | 0 | 73.2445 | DD45+0 | 26 |  | 2025-10-25 | 2025-10-26 | 2025-11-01 | 2025-11-18 | 2025-11-13
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Suresh Ram | 38/0 | 1049636.1718 | 0 | 137.0461 | DD60+25 | 26 |  | 2025-11-09 | 2025-11-10 | 2025-11-01 | 2025-12-03 | 2025-11-28
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Suresh Ram | 43/1 | 349993.4915 | 0 | 45.697 | DA+9 | 26 |  | 2025-11-23 | 2025-11-24 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 36/8 | 276947.5712 | 0 | 36.1598 | DA+0 | 22 |  | 2025-11-01 | 2025-11-02 | 2025-11-01 | 2025-11-18 | 2025-11-13
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 38/5 | 335498.0834 | 0 | 43.8044 | DA+6 | 22 |  | 2025-11-08 | 2025-11-09 | 2025-11-01 | 2025-11-24 | 2025-11-19
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 38/6 | 284442.4235 | 0 | 37.1383 | DA+1.5 | 22 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-12-01 | 2025-11-26
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 38/7 | 290514.203 | 0 | 37.9311 | DA+3 | 22 |  | 2025-11-21 | 2025-11-22 | 2025-11-01 | 2025-12-09 | 2025-12-04
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 40/2 | 290514.203 | 0 | 37.9311 | DA+3 | 24 |  | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-17 | 2025-11-12
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 40/3 | 290514.203 | 0 | 37.9311 | DA+3 | 24 |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-11-24 | 2025-11-19
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 40/4 | 284442.4235 | 0 | 37.1383 | DA+1.5 | 24 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-12-01 | 2025-11-26
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 40/5 | 284442.4235 | 0 | 37.1383 | DA+1.5 | 24 |  | 2025-11-21 | 2025-11-22 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 9/0 | 626720.652 | 0 | 81.828 | DC2+9 | 33 |  | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-22 | 2025-11-17
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 11/0 | 1232670.096 | 0 | 160.944 | DD60+30 | 33 |  | 2025-11-12 | 2025-11-13 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 62/1 | 408408.516 | 0 | 53.324 | 5DA+6 | 27 |  | 2025-10-31 | 2025-11-01 | 2025-11-01 | 2025-11-17 | 2025-11-12
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 62/2 | 408408.516 | 0 | 53.324 | 5DA+6 | 27 |  | 2025-11-07 | 2025-11-08 | 2025-11-01 | 2025-11-24 | 2025-11-19
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 62/3 | 581057.694 | 0 | 75.866 | 5DB1+6 | 27 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 1900-02-01 | 1900-01-27
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 62/4 | 324542.466 | 0 | 42.374 | 5DA-3 | 27 |  | 2025-11-23 | 2025-11-24 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 46/1 | 335280.384 | 0 | 43.776 | 5DA+0 | 23 |  | 2025-11-05 | 2025-11-06 | 2025-11-01 | 2025-11-23 | 2025-11-18
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 46/2 | 352689.291 | 0 | 46.049 | 5DA+3 | 23 |  | 2025-11-13 | 2025-11-14 | 2025-11-01 | 2025-12-02 | 2025-11-27
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 46/3 | 335280.384 | 0 | 43.776 | 5DA+0 | 23 |  | 2025-11-22 | 2025-11-23 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 78/1 | 335280.384 | 0 | 43.776 | 5DA+0 | 28 |  | 2025-11-05 | 2025-11-06 | 2025-11-01 | 2025-11-23 | 2025-11-18
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 78/3 | 335280.384 | 0 | 43.776 | 5DA+0 | 28 |  | 2025-11-13 | 2025-11-14 | 2025-11-01 | 2025-12-02 | 2025-11-27
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 76/3 | 352689.291 | 0 | 46.049 | 5DA+3 | 28 |  | 2025-11-22 | 2025-11-23 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 83/5 | 324542.466 | 0 | 42.374 | 5DA-3 | 30 |  | 2025-11-09 | 2025-11-10 | 2025-11-01 | 2025-11-29 | 2025-11-24
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 83/6 | 324542.466 | 0 | 42.374 | 5DA-3 | 30 |  | 2025-11-19 | 2025-11-20 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 84/1 | 335280.384 | 0 | 43.776 | 5DA+0 | 26 |  | 2025-11-09 | 2025-11-10 | 2025-11-01 | 2025-11-29 | 2025-11-24
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 84/4 | 324542.466 | 0 | 42.374 | 5DA-3 | 26 |  | 2025-11-19 | 2025-11-20 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 41/4 | 335498.0834 | 0 | 43.8044 | DA+6 | 29 |  | 2025-11-09 | 2025-11-10 | 2025-11-01 | 2025-11-29 | 2025-11-24
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 41/5 | 284442.4235 | 0 | 37.1383 | DA+1.5 | 29 |  | 2025-11-19 | 2025-11-20 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 40/6 | 284442.4235 | 0 | 37.1383 | DA+1.5 | 24 |  | 2025-11-09 | 2025-11-10 | 2025-11-01 | 2025-11-30 | 2025-11-25
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 40/7 | 272673.8952 | 0 | 35.6018 | DA-1.5 | 24 |  | 2025-11-20 | 2025-11-21 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 41/6 | 290514.203 | 0 | 37.9311 | DA+3 | 27 |  | 2025-01-11 | 2025-01-12 | 2025-11-01 | 2025-12-01 | 2025-11-26
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 41/7 | 276947.5712 | 0 | 36.1598 | DA+0 | 27 |  | 2025-11-21 | 2025-11-22 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 45/0 | 907055.37 | 0 | 118.43 | 5DD60+9 | 28 |  | 2025-11-11 | 2025-11-12 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 83/7 | 335280.384 | 0 | 43.776 | 5DA+0 | 25 |  | 2025-11-11 | 2025-11-12 | 2025-11-01 | 2025-11-30 | 2025-11-25
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 83/1 | 423841.401 | 0 | 55.339 | 5DA+9 | 25 |  | 2025-11-20 | 2025-11-21 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 40/0 | 956991.6824 | 0 | 124.95 | DD60+18 | 29 |  | 2025-11-12 | 2025-11-13 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 41/0 | 636719.6756 | 0 | 83.1335 | DD60+0 | 29 |  | 2025-11-12 | 2025-11-13 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 43/0 | 956991.6824 | 0 | 124.95 | DD60+18 | 30 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta419 | TA419 | 2025-11-01 | Supervisor | Mr. Satyaprakash | 46/0 | 1098775.458 | 0 | 143.462 | 5DD60+18 | 29 |  | 2025-11-14 | 2025-11-15 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta421 | TA421 | 2025-11-01 | Gang | Subash Kumar | 4/13 | 292211 | 0 | 31.99 | 2DA+0 | 27 | No | YES | WIP | 2025-11-01 | 2025-11-15 | 2025-11-10
ta421 | TA421 | 2025-11-01 | Gang | Subash Kumar | 4/22. | 347642 | 0 | 37.7169 | 2DA+6 | 27 | No | No | 2025-11-05 | 2025-11-01 | 2025-11-17 | 2025-11-12
ta421 | TA421 | 2025-11-01 | Gang | Subash Kumar | 6/0. | 708468.86 | 0 | 77.32 | 2DD45+6 | 27 | No | No | 2025-11-08 | 2025-11-01 | 2025-11-21 | 2025-11-16
ta421 | TA421 | 2025-11-01 | Gang | Subash Kumar | 6/7. | 307108 | 0 | 33.38 | 2DA+3 | 27 | No | No | 2025-11-12 | 2025-11-01 | 2025-11-24 | 2025-11-19
ta421 | TA421 | 2025-11-01 | Gang | Subash Kumar | 8/1. | 530631.65 | 0 | 58.93 | 2DB1+6 | 27 | No | No | 2025-11-18 | 2025-11-01 | 2025-12-04 | 2025-11-29
ta421 | TA421 | 2025-11-01 | Gang | Subash Kumar | 8/2. | 530631.65 | 0 | 58.93 | 2DB1+6 | 27 | No | No | 2025-11-25 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta421 | TA421 | 2025-11-01 | Gang | Shakila Khatun | 11/7. | 327992 | 0 | 36.372 | 3DA+0 | 35 | No |  |  | 2025-11-01
ta421 | TA421 | 2025-11-01 | Gang | Shakila Khatun | 8/3 | 550294.3 | 0 | 61.15 | 2DB1+9 | 35 | No | Yes | 2025-11-03 | 2025-11-01 | 2025-11-17 | 2025-11-12
ta421 | TA421 | 2025-11-01 | Gang | Shakila Khatun | 11/8. | 292211 | 0 | 36.372 | 3DA+0 | 35 | No | No | 2025-11-08 | 2025-11-01 | 2025-11-21 | 2025-11-16
ta421 | TA421 | 2025-11-01 | Gang | Shakila Khatun | 8/10. | 292211 | 0 | 31.99 | 2DA+0 | 35 | No | No | 2025-11-12 | 2025-11-01 | 2025-11-24 | 2025-11-19
ta421 | TA421 | 2025-11-01 | Gang | Shakila Khatun | 8/11. | 292211 | 0 | 31.99 | 2DA+0 | 35 | No | No | 2025-11-15 | 2025-11-01 | 2025-11-30 | 2025-11-25
ta421 | TA421 | 2025-11-01 | Gang | Shakila Khatun | 8/5. | 292211 | 0 | 31.99 | 2DA+0 | 35 | No | No | 2025-11-21 | 2025-11-01 | 2025-12-05 | 2025-11-30
ta421 | TA421 | 2025-11-01 | Gang | Shakila Khatun | 8/4. | 550294.3 | 0 | 58.93 | 2DB1+6 | 35 | No | No | 2025-11-26 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta421 | TA421 | 2025-11-01 | Gang | Nasiruddin | 36/8. | 327992 | 0 | 36.372 | 3DA+0 | 30 | No |  |  | 2025-11-01
ta421 | TA421 | 2025-11-01 | Gang | Nasiruddin | 36/0 | 749941.09 | 0 | 83.81 | 3DD60+3 | 30 | No | Yes | 2025-11-06 | 2025-11-01 | 2025-11-11 | 2025-11-16
ta421 | TA421 | 2025-11-01 | Gang | Nasiruddin | 37/1. | 342752 | 0 | 37.931 | 3DA+3 | 30 | No | No | 2025-11-17 | 2025-11-01 | 2025-12-01 | 2025-11-26
ta421 | TA421 | 2025-11-01 | Gang | Nasiruddin | 37/0 | 478941 | 0 | 54.66 | 3DB2+0 | 30 | No | No | 2025-11-23 | 2025-11-01 | 2025-12-09 | 2025-12-04
ta421 | TA421 | 2025-11-01 | Gang | Praveen | 39/8. | 342752 | 0 | 37.931 | 3DA+3 | 20 | No | Yes | WIP | 2025-11-01 | 2025-11-17 | 2025-11-12
ta421 | TA421 | 2025-11-01 | Gang | Praveen | 39/9 | 406294 | 0 | 44.85 | 3DA+9 | 20 | No | No | 2025-11-08 | 2025-11-01 | 2025-11-24 | 2025-11-19
ta421 | TA421 | 2025-11-01 | Gang | Praveen | 43A/2 | 327992 | 0 | 36.372 | 3DA+0 | 20 | No | No | 2025-11-15 | 2025-11-01 | 2025-12-02 | 2025-11-27
ta421 | TA421 | 2025-11-01 | Gang | Praveen | 43A/3 | 327992 | 0 | 36.372 | 3DA+0 | 20 | No | No | 2025-11-23 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta421 | TA421 | 2025-11-01 | Gang | D k Verma | 43/1. | 342752 | 0 | 37.931 | 3DA+3 | 20 | YES | YES |  | 2025-11-01
ta421 | TA421 | 2025-11-01 | Gang | D k Verma | 43B/0 | 586943 | 0 | 64.89 | 3DB1+9 | 20 | YES | Yes | 2025-11-04 | 2025-11-01 | 2025-11-20 | 2025-11-15
ta421 | TA421 | 2025-11-01 | Gang | D k Verma | 43/0 | 478941 | 0 | 54.66 | 3DB2+0 | 20 | YES | YES | 2025-11-11 | 2025-11-01 | 2025-11-25 | 2025-11-20
ta421 | TA421 | 2025-11-01 | Gang | D k Verma | 43A/4 | 327992 | 0 | 36.372 | 3DA+0 | 20 | YES | YES | 2025-11-16 | 2025-11-01 | 2025-12-01 | 2025-11-26
ta421 | TA421 | 2025-11-01 | Gang | D k Verma | 43A/5 | 342752 | 0 | 37.931 | 3DA+3 | 20 | YES | YES | 2025-11-22 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta421 | TA421 | 2025-11-01 | Gang | Pankaj | 43A/0 | 796222 | 0 | 90.24 | 3DD45+9 |  | No | No | 2025-11-15 | 2025-11-01 | 2025-12-01 | 2025-11-26
ta421 | TA421 | 2025-11-01 | Gang | Pankaj | 43A/1 | 500493 | 0 | 57.14 | 3DB1+3 |  | No | No | 2025-11-22 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta421 | TA421 | 2025-11-01 | Gang | Tofitmiya | 16/11 | 342752 | 0 | 37.931 | 3DA+3 |  | No | No | 2025-11-03 | 2025-11-01 | 2025-11-15 | 2025-11-10
ta421 | TA421 | 2025-11-01 | Gang | Tofitmiya | 27/3 | 550754 | 0 | 101.9 | 3DC1+0 (TR) |  | No | No | 2025-11-08 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Karunakar | 4/13 | 292211 | 0 | 31.99 | 2DA+0 | 27 | No | YES | WIP | 2025-11-01 | 2025-11-15 | 2025-11-10
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Karunakar | 4/22. | 347642 | 0 | 37.7169 | 2DA+6 | 27 | No | No | 2025-11-05 | 2025-11-01 | 2025-11-17 | 2025-11-12
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Karunakar | 6/0. | 708468.86 | 0 | 77.32 | 2DD45+6 | 27 | No | No | 2025-11-08 | 2025-11-01 | 2025-11-21 | 2025-11-16
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Karunakar | 6/7. | 307108 | 0 | 33.38 | 2DA+3 | 27 | No | No | 2025-11-12 | 2025-11-01 | 2025-11-24 | 2025-11-19
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Karunakar | 8/1. | 530631.65 | 0 | 58.93 | 2DB1+6 | 27 | No | No | 2025-11-18 | 2025-11-01 | 2025-12-04 | 2025-11-29
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Karunakar | 8/2. | 530631.65 | 0 | 58.93 | 2DB1+6 | 27 | No | No | 2025-11-25 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Karunakar | 11/7. | 327992 | 0 | 36.372 | 3DA+0 | 35 | No |  |  | 2025-11-01
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Karunakar | 8/3 | 550294.3 | 0 | 61.15 | 2DB1+9 | 35 | No | Yes | 2025-11-03 | 2025-11-01 | 2025-11-17 | 2025-11-12
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Karunakar | 11/8. | 292211 | 0 | 36.372 | 3DA+0 | 35 | No | No | 2025-11-08 | 2025-11-01 | 2025-11-21 | 2025-11-16
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Karunakar | 8/10. | 292211 | 0 | 31.99 | 2DA+0 | 35 | No | No | 2025-11-12 | 2025-11-01 | 2025-11-24 | 2025-11-19
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Karunakar | 8/11. | 292211 | 0 | 31.99 | 2DA+0 | 35 | No | No | 2025-11-15 | 2025-11-01 | 2025-11-30 | 2025-11-25
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Karunakar | 8/5. | 292211 | 0 | 31.99 | 2DA+0 | 35 | No | No | 2025-11-21 | 2025-11-01 | 2025-12-05 | 2025-11-30
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Karunakar | 8/4. | 550294.3 | 0 | 58.93 | 2DB1+6 | 35 | No | No | 2025-11-26 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Ram Asish | 36/8. | 327992 | 0 | 36.372 | 3DA+0 | 30 | No |  |  | 2025-11-01
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Ram Asish | 36/0 | 749941.09 | 0 | 83.81 | 3DD60+3 | 30 | No | Yes | 2025-11-06 | 2025-11-01 | 2025-11-11 | 2025-11-16
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Ram Asish | 37/1. | 342752 | 0 | 37.931 | 3DA+3 | 30 | No | No | 2025-11-17 | 2025-11-01 | 2025-12-01 | 2025-11-26
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Ram Asish | 37/0 | 478941 | 0 | 54.66 | 3DB2+0 | 30 | No | No | 2025-11-23 | 2025-11-01 | 2025-12-09 | 2025-12-04
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Ram Asish | 39/8. | 342752 | 0 | 37.931 | 3DA+3 | 20 | No | Yes | WIP | 2025-11-01 | 2025-11-17 | 2025-11-12
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Ram Asish | 39/9 | 406294 | 0 | 44.85 | 3DA+9 | 20 | No | No | 2025-11-08 | 2025-11-01 | 2025-11-24 | 2025-11-19
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Ram Asish | 43A/2 | 327992 | 0 | 36.372 | 3DA+0 | 20 | No | No | 2025-11-15 | 2025-11-01 | 2025-12-02 | 2025-11-27
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Ram Asish | 43A/3 | 327992 | 0 | 36.372 | 3DA+0 | 20 | No | No | 2025-11-23 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Ram Asish | 43/1. | 342752 | 0 | 37.931 | 3DA+3 | 20 | YES | YES |  | 2025-11-01
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Ram Asish | 43B/0 | 586943 | 0 | 64.89 | 3DB1+9 | 20 | YES | Yes | 2025-11-04 | 2025-11-01 | 2025-11-20 | 2025-11-15
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Ram Asish | 43/0 | 478941 | 0 | 54.66 | 3DB2+0 | 20 | YES | YES | 2025-11-11 | 2025-11-01 | 2025-11-25 | 2025-11-20
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Ram Asish | 43A/4 | 327992 | 0 | 36.372 | 3DA+0 | 20 | YES | YES | 2025-11-16 | 2025-11-01 | 2025-12-01 | 2025-11-26
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Ram Asish | 43A/5 | 342752 | 0 | 37.931 | 3DA+3 | 20 | YES | YES | 2025-11-22 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Ram Asish | 43A/0 | 796222 | 0 | 90.24 | 3DD45+9 |  | No | No | 2025-11-15 | 2025-11-01 | 2025-12-01 | 2025-11-26
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Ram Asish | 43A/1 | 500493 | 0 | 57.14 | 3DB1+3 |  | No | No | 2025-11-22 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Ram Asish | 16/11 | 342752 | 0 | 37.931 | 3DA+3 |  | No | No | 2025-11-03 | 2025-11-01 | 2025-11-15 | 2025-11-10
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Ram Asish | 27/3 | 550754 | 0 | 101.9 | 3DC1+0 (TR) |  | No | No | 2025-11-08 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Chandrasekahar | 4/13 | 292211 | 0 | 31.99 | 2DA+0 | 27 | No | YES | WIP | 2025-11-01 | 2025-11-15 | 2025-11-10
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Chandrasekahar | 4/22. | 347642 | 0 | 37.7169 | 2DA+6 | 27 | No | No | 2025-11-05 | 2025-11-01 | 2025-11-17 | 2025-11-12
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Chandrasekahar | 6/0. | 708468.86 | 0 | 77.32 | 2DD45+6 | 27 | No | No | 2025-11-08 | 2025-11-01 | 2025-11-21 | 2025-11-16
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Chandrasekahar | 6/7. | 307108 | 0 | 33.38 | 2DA+3 | 27 | No | No | 2025-11-12 | 2025-11-01 | 2025-11-24 | 2025-11-19
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Chandrasekahar | 8/1. | 530631.65 | 0 | 58.93 | 2DB1+6 | 27 | No | No | 2025-11-18 | 2025-11-01 | 2025-12-04 | 2025-11-29
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Chandrasekahar | 8/2. | 530631.65 | 0 | 58.93 | 2DB1+6 | 27 | No | No | 2025-11-25 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Srinivasan | 11/7. | 327992 | 0 | 36.372 | 3DA+0 | 35 | No |  |  | 2025-11-01
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Srinivasan | 8/3 | 550294.3 | 0 | 61.15 | 2DB1+9 | 35 | No | Yes | 2025-11-03 | 2025-11-01 | 2025-11-17 | 2025-11-12
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Srinivasan | 11/8. | 292211 | 0 | 36.372 | 3DA+0 | 35 | No | No | 2025-11-08 | 2025-11-01 | 2025-11-21 | 2025-11-16
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Srinivasan | 8/10. | 292211 | 0 | 31.99 | 2DA+0 | 35 | No | No | 2025-11-12 | 2025-11-01 | 2025-11-24 | 2025-11-19
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Srinivasan | 8/11. | 292211 | 0 | 31.99 | 2DA+0 | 35 | No | No | 2025-11-15 | 2025-11-01 | 2025-11-30 | 2025-11-25
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Srinivasan | 8/5. | 292211 | 0 | 31.99 | 2DA+0 | 35 | No | No | 2025-11-21 | 2025-11-01 | 2025-12-05 | 2025-11-30
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Srinivasan | 8/4. | 550294.3 | 0 | 58.93 | 2DB1+6 | 35 | No | No | 2025-11-26 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Bhim Mahto | 36/8. | 327992 | 0 | 36.372 | 3DA+0 | 30 | No |  |  | 2025-11-01
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Bhim Mahto | 36/0 | 749941.09 | 0 | 83.81 | 3DD60+3 | 30 | No | Yes | 2025-11-06 | 2025-11-01 | 2025-11-11 | 2025-11-16
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Bhim Mahto | 37/1. | 342752 | 0 | 37.931 | 3DA+3 | 30 | No | No | 2025-11-17 | 2025-11-01 | 2025-12-01 | 2025-11-26
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Bhim Mahto | 37/0 | 478941 | 0 | 54.66 | 3DB2+0 | 30 | No | No | 2025-11-23 | 2025-11-01 | 2025-12-09 | 2025-12-04
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Ballu Thakur | 39/8. | 342752 | 0 | 37.931 | 3DA+3 | 20 | No | Yes | WIP | 2025-11-01 | 2025-11-17 | 2025-11-12
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Ballu Thakur | 39/9 | 406294 | 0 | 44.85 | 3DA+9 | 20 | No | No | 2025-11-08 | 2025-11-01 | 2025-11-24 | 2025-11-19
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Ballu Thakur | 43A/2 | 327992 | 0 | 36.372 | 3DA+0 | 20 | No | No | 2025-11-15 | 2025-11-01 | 2025-12-02 | 2025-11-27
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Ballu Thakur | 43A/3 | 327992 | 0 | 36.372 | 3DA+0 | 20 | No | No | 2025-11-23 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Muthu | 43/1. | 342752 | 0 | 37.931 | 3DA+3 | 20 | YES | YES |  | 2025-11-01
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Muthu | 43B/0 | 586943 | 0 | 64.89 | 3DB1+9 | 20 | YES | Yes | 2025-11-04 | 2025-11-01 | 2025-11-20 | 2025-11-15
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Muthu | 43/0 | 478941 | 0 | 54.66 | 3DB2+0 | 20 | YES | YES | 2025-11-11 | 2025-11-01 | 2025-11-25 | 2025-11-20
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Muthu | 43A/4 | 327992 | 0 | 36.372 | 3DA+0 | 20 | YES | YES | 2025-11-16 | 2025-11-01 | 2025-12-01 | 2025-11-26
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Muthu | 43A/5 | 342752 | 0 | 37.931 | 3DA+3 | 20 | YES | YES | 2025-11-22 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Anand | 43A/0 | 796222 | 0 | 90.24 | 3DD45+9 |  | No | No | 2025-11-15 | 2025-11-01 | 2025-12-01 | 2025-11-26
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Anand | 43A/1 | 500493 | 0 | 57.14 | 3DB1+3 |  | No | No | 2025-11-22 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Ram Asish | 16/11 | 342752 | 0 | 37.931 | 3DA+3 |  | No | No | 2025-11-03 | 2025-11-01 | 2025-11-15 | 2025-11-10
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Ram Asish | 27/3 | 550754 | 0 | 101.9 | 3DC1+0 (TR) |  | No | No | 2025-11-08 | 2025-11-01 | 2025-12-10 | 2025-12-05
ta504 | TA504 | 2025-11-01 | Gang | None | 11/5 | 399793.6675 | 0 | 37.9311 | DA+3 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Gang | None | 13/0 | 627136.6191 | 0 | 59.5006 | DB2+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Gang | None | 22/0 | 771997.5359 | 0 | 73.2445 | DD45+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Gang | None | 26/9 | 381123.8282 | 0 | 36.1598 | DA+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Gang | None | 30/1 | 481646.6119 | 0 | 45.697 | DA+9 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Gang | None | 14/0 | 771997.5359 | 0 | 73.2445 | DD45+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Gang | None | 16/4 | 481646.6119 | 0 | 45.697 | DA+9 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Gang | None | 19/2 | 399793.6675 | 0 | 37.9311 | DA+3 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Gang | None | 23/0 | 745649.3488 | 0 | 70.7447 | DC2+3 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Gang | None | 26/0 | 708938.6131 | 0 | 67.2617 | DC2+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Gang | None | 26/7 | 381123.8282 | 0 | 36.1598 | DA+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Gang | None | 26/10 | 381123.8282 | 0 | 36.1598 | DA+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Gang | None | 27/0 | 658156.6612 | 0 | 62.4437 | DC1+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Gang | None | 28/0 | 658156.6612 | 0 | 62.4437 | DC1+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Gang | None | 30/0 | 708938.6131 | 0 | 67.2617 | DC2+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Gang | None | 30/3 | 481646.6119 | 0 | 45.697 | DA+9 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Gang | None | 31/0 | 771997.5359 | 0 | 73.2445 | DD45+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Gang | None | 31/2 | 685337.9827 | 0 | 65.0226 | DB1+6 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Gang | None | 32/0 | 584451.9695 | 0 | 55.4509 | DB1+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Gang | None | 32/2 | 703815.8885 | 0 | 66.7757 | DB1+9 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Gang | None | 33/0 | 708938.6131 | 0 | 67.2617 | DC2+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Section Incharge | Prasant Kumar | 11/5 | 399793.6675 | 0 | 37.9311 | DA+3 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Section Incharge | Prasant Kumar | 13/0 | 627136.6191 | 0 | 59.5006 | DB2+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Section Incharge | Prasant Kumar | 22/0 | 771997.5359 | 0 | 73.2445 | DD45+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Section Incharge | Prasant Kumar | 26/9 | 381123.8282 | 0 | 36.1598 | DA+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Section Incharge | Prasant Kumar | 30/1 | 481646.6119 | 0 | 45.697 | DA+9 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Section Incharge | Prasant Kumar | 14/0 | 771997.5359 | 0 | 73.2445 | DD45+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Section Incharge | Prasant Kumar | 16/4 | 481646.6119 | 0 | 45.697 | DA+9 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Section Incharge | Prasant Kumar | 19/2 | 399793.6675 | 0 | 37.9311 | DA+3 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Section Incharge | Prasant Kumar | 23/0 | 745649.3488 | 0 | 70.7447 | DC2+3 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Section Incharge | Prasant Kumar | 26/0 | 708938.6131 | 0 | 67.2617 | DC2+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Section Incharge | Prasant Kumar | 26/7 | 381123.8282 | 0 | 36.1598 | DA+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Section Incharge | Prasant Kumar | 26/10 | 381123.8282 | 0 | 36.1598 | DA+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Section Incharge | Prasant Kumar | 27/0 | 658156.6612 | 0 | 62.4437 | DC1+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Section Incharge | Prasant Kumar | 28/0 | 658156.6612 | 0 | 62.4437 | DC1+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Section Incharge | Prasant Kumar | 30/0 | 708938.6131 | 0 | 67.2617 | DC2+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Section Incharge | Prasant Kumar | 30/3 | 481646.6119 | 0 | 45.697 | DA+9 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Section Incharge | Prasant Kumar | 31/0 | 771997.5359 | 0 | 73.2445 | DD45+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Section Incharge | Prasant Kumar | 31/2 | 685337.9827 | 0 | 65.0226 | DB1+6 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Section Incharge | Prasant Kumar | 32/0 | 584451.9695 | 0 | 55.4509 | DB1+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Section Incharge | Prasant Kumar | 32/2 | 703815.8885 | 0 | 66.7757 | DB1+9 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Section Incharge | Prasant Kumar | 33/0 | 708938.6131 | 0 | 67.2617 | DC2+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Supervisor | Rajesh Singh | 11/5 | 399793.6675 | 0 | 37.9311 | DA+3 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Supervisor | Rajesh Singh | 13/0 | 627136.6191 | 0 | 59.5006 | DB2+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Supervisor | Teklal Mahto | 22/0 | 771997.5359 | 0 | 73.2445 | DD45+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Supervisor | Teklal Mahto | 26/9 | 381123.8282 | 0 | 36.1598 | DA+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Supervisor | Teklal Mahto | 30/1 | 481646.6119 | 0 | 45.697 | DA+9 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Supervisor | Rajesh Singh | 14/0 | 771997.5359 | 0 | 73.2445 | DD45+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Supervisor | Rajesh Singh | 16/4 | 481646.6119 | 0 | 45.697 | DA+9 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Supervisor | Rajesh Singh | 19/2 | 399793.6675 | 0 | 37.9311 | DA+3 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Supervisor | Teklal Mahto | 23/0 | 745649.3488 | 0 | 70.7447 | DC2+3 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Supervisor | Teklal Mahto | 26/0 | 708938.6131 | 0 | 67.2617 | DC2+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Supervisor | Teklal Mahto | 26/7 | 381123.8282 | 0 | 36.1598 | DA+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Supervisor | Teklal Mahto | 26/10 | 381123.8282 | 0 | 36.1598 | DA+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Supervisor | Teklal Mahto | 27/0 | 658156.6612 | 0 | 62.4437 | DC1+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Supervisor | Teklal Mahto | 28/0 | 658156.6612 | 0 | 62.4437 | DC1+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Supervisor | Rameswar Mahto | 30/0 | 708938.6131 | 0 | 67.2617 | DC2+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Supervisor | Rameswar Mahto | 30/3 | 481646.6119 | 0 | 45.697 | DA+9 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Supervisor | Rameswar Mahto | 31/0 | 771997.5359 | 0 | 73.2445 | DD45+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Supervisor | Rameswar Mahto | 31/2 | 685337.9827 | 0 | 65.0226 | DB1+6 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Supervisor | Rameswar Mahto | 32/0 | 584451.9695 | 0 | 55.4509 | DB1+0 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Supervisor | Rameswar Mahto | 32/2 | 703815.8885 | 0 | 66.7757 | DB1+9 |  |  |  |  | 2025-11-01
ta504 | TA504 | 2025-11-01 | Supervisor | Rameswar Mahto | 33/0 | 708938.6131 | 0 | 67.2617 | DC2+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 1/8 | 236872.9816 | 0 | 17.6337 | DA+1.5 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 1/9 | 236872.9816 | 0 | 17.6337 | DA+1.5 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 12/2 | 236872.9816 | 0 | 17.6337 | DA+1.5 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 12/8 | 213017.3707 | 0 | 15.8578 | DA-3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 15/0 | 512306.1286 | 0 | 38.1379 | DD45+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 16/0 | 458957.6676 | 0 | 34.1664 | DB2+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 28/0 | 649377.9651 | 0 | 48.342 | DD45+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 37/0 | 649377.9651 | 0 | 48.342 | DD45+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 42/2 | 213017.3707 | 0 | 15.8578 | DA-3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 52/1 | 221005.7071 | 0 | 16.4524 | DA-1.5 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 62/0 | 713596.356 | 0 | 53.1226 | DD60+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 65A/3 | 400006.7322 | 0 | 29.7779 | DC1+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 110/0 | 428038.2061 | 0 | 31.8647 | DC2+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 167A/0 | 512306.1286 | 0 | 38.1379 | DD45+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 197/2 | 243390.0553 | 0 | 18.1188 | DA+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 211/1 | 227914.0035 | 0 | 16.9667 | DA+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 220/5 | 221005.7071 | 0 | 16.4524 | DA-1.5 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 2/0 | 363928.8375 | 0 | 27.0921 | DB2+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 2A/1 | 213017.3707 | 0 | 15.8578 | DA-3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 13/4 | 302086.3279 | 0 | 22.4884 | DA+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 13/5 | 243390.0553 | 0 | 18.1188 | DA+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 34/2 | 236872.9816 | 0 | 17.6337 | DA+1.5 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 35A/0 | 331796.2955 | 0 | 24.7001 | DB2-3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 36/0 | 366046.8186 | 0 | 27.2498 | DC1-3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 36/1 | 302086.3279 | 0 | 22.4884 | DA+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 36/2 | 283394.8726 | 0 | 21.0969 | DA+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 40/0 | 481508.8 | 0 | 35.8452 | DD45+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 42/1 | 227914.0035 | 0 | 16.9667 | DA+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 44/0 | 428038.2061 | 0 | 31.8647 | DC2+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 44/1 | 227914.0035 | 0 | 16.9667 | DA+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 44A/0 | 428038.2061 | 0 | 31.8647 | DC2+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 44A/1 | 221005.7071 | 0 | 16.4524 | DA-1.5 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 44A/2 | 227914.0035 | 0 | 16.9667 | DA+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 45/0 | 481508.8 | 0 | 35.8452 | DD45+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 46/0 | 713596.356 | 0 | 53.1226 | DD60+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 94/0 | 624212.9859 | 0 | 46.4686 | DD45+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 94/1 | 302086.3279 | 0 | 22.4884 | DA+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 94/2 | 302086.3279 | 0 | 22.4884 | DA+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 94/3 | 302086.3279 | 0 | 22.4884 | DA+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 95/0 | 532248.3306 | 0 | 39.6224 | DC2+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 95/1 | 243390.0553 | 0 | 18.1188 | DA+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 95A/0 | 491451.0468 | 0 | 36.5854 | DB1+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 97/0 | 374243.689 | 0 | 27.86 | DB2+1.5 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 107/1 | 243390.0553 | 0 | 18.1188 | DA+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 111/0 | 400006.7322 | 0 | 29.7779 | DC1+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 114/1 | 458957.6676 | 0 | 34.1664 | DB1+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 166/1 | 458957.6676 | 0 | 34.1664 | DB1+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 167A/1 | 400006.7322 | 0 | 29.7779 | DC1+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 181/3 | 283394.8726 | 0 | 21.0969 | DA+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 182/0 | 531902.4039 | 0 | 39.5967 | DD60+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 182/6 | 243390.0553 | 0 | 18.1188 | DA+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 184/1 | 243390.0553 | 0 | 18.1188 | DA+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 193/0 | 458957.6676 | 0 | 34.1664 | DB2+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 195/0 | 363928.8375 | 0 | 27.0921 | DB1+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 199/1 | 283394.8726 | 0 | 21.0969 | DA+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 199/3 | 243390.0553 | 0 | 18.1188 | DA+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 211/4 | 283394.8726 | 0 | 21.0969 | DA+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 211/5 | 283394.8726 | 0 | 21.0969 | DA+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 211/6 | 283394.8726 | 0 | 21.0969 | DA+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 212/0 | 381068.0559 | 0 | 28.3681 | DB2+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 212/1 | 283394.8726 | 0 | 21.0969 | DA+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 215/0 | 458957.6676 | 0 | 34.1664 | DB1+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 220/8 | 243390.0553 | 0 | 18.1188 | DA+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 221/0 | 491451.0468 | 0 | 36.5854 | DB2+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 17/0 | 715154.6646 | 0 | 53.2386 | DC1+18 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 17/1 | 227914.0035 | 0 | 16.9667 | DA+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 18/0 | 481508.8 | 0 | 35.8452 | DD45+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 25/2 | 236872.9816 | 0 | 17.6337 | DA+1.5 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 26/0 | 481508.8 | 0 | 35.8452 | DD45+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 30/0 | 561941.0367 | 0 | 41.8329 | DD60+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Gang | None | 31/0 | 624212.9859 | 0 | 46.4686 | DD45+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 1/8 | 236872.9816 | 0 | 17.6337 | DA+1.5 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 1/9 | 236872.9816 | 0 | 17.6337 | DA+1.5 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 12/2 | 236872.9816 | 0 | 17.6337 | DA+1.5 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 12/8 | 213017.3707 | 0 | 15.8578 | DA-3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 15/0 | 512306.1286 | 0 | 38.1379 | DD45+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 16/0 | 458957.6676 | 0 | 34.1664 | DB2+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 28/0 | 649377.9651 | 0 | 48.342 | DD45+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 37/0 | 649377.9651 | 0 | 48.342 | DD45+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 42/2 | 213017.3707 | 0 | 15.8578 | DA-3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 52/1 | 221005.7071 | 0 | 16.4524 | DA-1.5 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 62/0 | 713596.356 | 0 | 53.1226 | DD60+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 65A/3 | 400006.7322 | 0 | 29.7779 | DC1+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Rajkumar Tomar | 110/0 | 428038.2061 | 0 | 31.8647 | DC2+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Rajkumar Tomar | 167A/0 | 512306.1286 | 0 | 38.1379 | DD45+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Abhishek Kumar | 197/2 | 243390.0553 | 0 | 18.1188 | DA+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Abhishek Kumar | 211/1 | 227914.0035 | 0 | 16.9667 | DA+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Abhishek Kumar | 220/5 | 221005.7071 | 0 | 16.4524 | DA-1.5 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 2/0 | 363928.8375 | 0 | 27.0921 | DB2+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 2A/1 | 213017.3707 | 0 | 15.8578 | DA-3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 13/4 | 302086.3279 | 0 | 22.4884 | DA+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 13/5 | 243390.0553 | 0 | 18.1188 | DA+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 34/2 | 236872.9816 | 0 | 17.6337 | DA+1.5 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 35A/0 | 331796.2955 | 0 | 24.7001 | DB2-3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 36/0 | 366046.8186 | 0 | 27.2498 | DC1-3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 36/1 | 302086.3279 | 0 | 22.4884 | DA+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 36/2 | 283394.8726 | 0 | 21.0969 | DA+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 40/0 | 481508.8 | 0 | 35.8452 | DD45+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 42/1 | 227914.0035 | 0 | 16.9667 | DA+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 44/0 | 428038.2061 | 0 | 31.8647 | DC2+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 44/1 | 227914.0035 | 0 | 16.9667 | DA+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 44A/0 | 428038.2061 | 0 | 31.8647 | DC2+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 44A/1 | 221005.7071 | 0 | 16.4524 | DA-1.5 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 44A/2 | 227914.0035 | 0 | 16.9667 | DA+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 45/0 | 481508.8 | 0 | 35.8452 | DD45+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 46/0 | 713596.356 | 0 | 53.1226 | DD60+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Rajkumar Tomar | 94/0 | 624212.9859 | 0 | 46.4686 | DD45+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Rajkumar Tomar | 94/1 | 302086.3279 | 0 | 22.4884 | DA+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Rajkumar Tomar | 94/2 | 302086.3279 | 0 | 22.4884 | DA+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Rajkumar Tomar | 94/3 | 302086.3279 | 0 | 22.4884 | DA+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Rajkumar Tomar | 95/0 | 532248.3306 | 0 | 39.6224 | DC2+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Rajkumar Tomar | 95/1 | 243390.0553 | 0 | 18.1188 | DA+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Rajkumar Tomar | 95A/0 | 491451.0468 | 0 | 36.5854 | DB1+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Rajkumar Tomar | 97/0 | 374243.689 | 0 | 27.86 | DB2+1.5 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Rajkumar Tomar | 107/1 | 243390.0553 | 0 | 18.1188 | DA+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Rajkumar Tomar | 111/0 | 400006.7322 | 0 | 29.7779 | DC1+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Rajkumar Tomar | 114/1 | 458957.6676 | 0 | 34.1664 | DB1+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Rajkumar Tomar | 166/1 | 458957.6676 | 0 | 34.1664 | DB1+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Rajkumar Tomar | 167A/1 | 400006.7322 | 0 | 29.7779 | DC1+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Abhishek Kumar | 181/3 | 283394.8726 | 0 | 21.0969 | DA+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Abhishek Kumar | 182/0 | 531902.4039 | 0 | 39.5967 | DD60+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Abhishek Kumar | 182/6 | 243390.0553 | 0 | 18.1188 | DA+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Abhishek Kumar | 184/1 | 243390.0553 | 0 | 18.1188 | DA+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Abhishek Kumar | 193/0 | 458957.6676 | 0 | 34.1664 | DB2+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Abhishek Kumar | 195/0 | 363928.8375 | 0 | 27.0921 | DB1+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Abhishek Kumar | 199/1 | 283394.8726 | 0 | 21.0969 | DA+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Abhishek Kumar | 199/3 | 243390.0553 | 0 | 18.1188 | DA+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Abhishek Kumar | 211/4 | 283394.8726 | 0 | 21.0969 | DA+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Abhishek Kumar | 211/5 | 283394.8726 | 0 | 21.0969 | DA+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Abhishek Kumar | 211/6 | 283394.8726 | 0 | 21.0969 | DA+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Abhishek Kumar | 212/0 | 381068.0559 | 0 | 28.3681 | DB2+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Abhishek Kumar | 212/1 | 283394.8726 | 0 | 21.0969 | DA+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Abhishek Kumar | 215/0 | 458957.6676 | 0 | 34.1664 | DB1+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Abhishek Kumar | 220/8 | 243390.0553 | 0 | 18.1188 | DA+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Abhishek Kumar | 221/0 | 491451.0468 | 0 | 36.5854 | DB2+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 17/0 | 715154.6646 | 0 | 53.2386 | DC1+18 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 17/1 | 227914.0035 | 0 | 16.9667 | DA+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 18/0 | 481508.8 | 0 | 35.8452 | DD45+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 25/2 | 236872.9816 | 0 | 17.6337 | DA+1.5 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 26/0 | 481508.8 | 0 | 35.8452 | DD45+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 30/0 | 561941.0367 | 0 | 41.8329 | DD60+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Section Incharge | Dharmendra Pandey | 31/0 | 624212.9859 | 0 | 46.4686 | DD45+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Anil Kumar | 1/8 | 236872.9816 | 0 | 17.6337 | DA+1.5 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Anil Kumar | 1/9 | 236872.9816 | 0 | 17.6337 | DA+1.5 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Anil Kumar | 12/2 | 236872.9816 | 0 | 17.6337 | DA+1.5 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Anil Kumar | 12/8 | 213017.3707 | 0 | 15.8578 | DA-3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Anil Kumar | 15/0 | 512306.1286 | 0 | 38.1379 | DD45+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Anil Kumar | 16/0 | 458957.6676 | 0 | 34.1664 | DB2+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bipattaran Dolui | 28/0 | 649377.9651 | 0 | 48.342 | DD45+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bipattaran Dolui | 37/0 | 649377.9651 | 0 | 48.342 | DD45+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bipattaran Dolui | 42/2 | 213017.3707 | 0 | 15.8578 | DA-3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bipattaran Dolui | 52/1 | 221005.7071 | 0 | 16.4524 | DA-1.5 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bipattaran Dolui | 62/0 | 713596.356 | 0 | 53.1226 | DD60+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bipattaran Dolui | 65A/3 | 400006.7322 | 0 | 29.7779 | DC1+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Sahadev Gope | 110/0 | 428038.2061 | 0 | 31.8647 | DC2+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Sahadev Gope | 167A/0 | 512306.1286 | 0 | 38.1379 | DD45+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bhola Karmakat | 197/2 | 243390.0553 | 0 | 18.1188 | DA+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Sunil Kumar | 211/1 | 227914.0035 | 0 | 16.9667 | DA+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Sunil Kumar | 220/5 | 221005.7071 | 0 | 16.4524 | DA-1.5 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Anil Kumar | 2/0 | 363928.8375 | 0 | 27.0921 | DB2+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Anil Kumar | 2A/1 | 213017.3707 | 0 | 15.8578 | DA-3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Anil Kumar | 13/4 | 302086.3279 | 0 | 22.4884 | DA+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Anil Kumar | 13/5 | 243390.0553 | 0 | 18.1188 | DA+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bipattaran Dolui | 34/2 | 236872.9816 | 0 | 17.6337 | DA+1.5 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bipattaran Dolui | 35A/0 | 331796.2955 | 0 | 24.7001 | DB2-3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bipattaran Dolui | 36/0 | 366046.8186 | 0 | 27.2498 | DC1-3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bipattaran Dolui | 36/1 | 302086.3279 | 0 | 22.4884 | DA+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bipattaran Dolui | 36/2 | 283394.8726 | 0 | 21.0969 | DA+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bipattaran Dolui | 40/0 | 481508.8 | 0 | 35.8452 | DD45+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bipattaran Dolui | 42/1 | 227914.0035 | 0 | 16.9667 | DA+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bipattaran Dolui | 44/0 | 428038.2061 | 0 | 31.8647 | DC2+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bipattaran Dolui | 44/1 | 227914.0035 | 0 | 16.9667 | DA+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bipattaran Dolui | 44A/0 | 428038.2061 | 0 | 31.8647 | DC2+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bipattaran Dolui | 44A/1 | 221005.7071 | 0 | 16.4524 | DA-1.5 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bipattaran Dolui | 44A/2 | 227914.0035 | 0 | 16.9667 | DA+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bipattaran Dolui | 45/0 | 481508.8 | 0 | 35.8452 | DD45+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bipattaran Dolui | 46/0 | 713596.356 | 0 | 53.1226 | DD60+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Sahadev Gope | 94/0 | 624212.9859 | 0 | 46.4686 | DD45+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Sahadev Gope | 94/1 | 302086.3279 | 0 | 22.4884 | DA+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Sahadev Gope | 94/2 | 302086.3279 | 0 | 22.4884 | DA+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Sahadev Gope | 94/3 | 302086.3279 | 0 | 22.4884 | DA+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Sahadev Gope | 95/0 | 532248.3306 | 0 | 39.6224 | DC2+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Sahadev Gope | 95/1 | 243390.0553 | 0 | 18.1188 | DA+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Sahadev Gope | 95A/0 | 491451.0468 | 0 | 36.5854 | DB1+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Sahadev Gope | 97/0 | 374243.689 | 0 | 27.86 | DB2+1.5 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Sahadev Gope | 107/1 | 243390.0553 | 0 | 18.1188 | DA+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Sahadev Gope | 111/0 | 400006.7322 | 0 | 29.7779 | DC1+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Sahadev Gope | 114/1 | 458957.6676 | 0 | 34.1664 | DB1+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Sahadev Gope | 166/1 | 458957.6676 | 0 | 34.1664 | DB1+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Sahadev Gope | 167A/1 | 400006.7322 | 0 | 29.7779 | DC1+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bhola Karmakat | 181/3 | 283394.8726 | 0 | 21.0969 | DA+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bhola Karmakat | 182/0 | 531902.4039 | 0 | 39.5967 | DD60+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bhola Karmakat | 182/6 | 243390.0553 | 0 | 18.1188 | DA+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bhola Karmakat | 184/1 | 243390.0553 | 0 | 18.1188 | DA+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bhola Karmakat | 193/0 | 458957.6676 | 0 | 34.1664 | DB2+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bhola Karmakat | 195/0 | 363928.8375 | 0 | 27.0921 | DB1+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bhola Karmakat | 199/1 | 283394.8726 | 0 | 21.0969 | DA+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Bhola Karmakat | 199/3 | 243390.0553 | 0 | 18.1188 | DA+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Sunil Kumar | 211/4 | 283394.8726 | 0 | 21.0969 | DA+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Sunil Kumar | 211/5 | 283394.8726 | 0 | 21.0969 | DA+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Sunil Kumar | 211/6 | 283394.8726 | 0 | 21.0969 | DA+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Sunil Kumar | 212/0 | 381068.0559 | 0 | 28.3681 | DB2+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Sunil Kumar | 212/1 | 283394.8726 | 0 | 21.0969 | DA+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Sunil Kumar | 215/0 | 458957.6676 | 0 | 34.1664 | DB1+6 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Sunil Kumar | 220/8 | 243390.0553 | 0 | 18.1188 | DA+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Sunil Kumar | 221/0 | 491451.0468 | 0 | 36.5854 | DB2+9 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Anil Kumar | 17/0 | 715154.6646 | 0 | 53.2386 | DC1+18 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Anil Kumar | 17/1 | 227914.0035 | 0 | 16.9667 | DA+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Anil Kumar | 18/0 | 481508.8 | 0 | 35.8452 | DD45+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Anil Kumar | 25/2 | 236872.9816 | 0 | 17.6337 | DA+1.5 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Anil Kumar | 26/0 | 481508.8 | 0 | 35.8452 | DD45+0 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Anil Kumar | 30/0 | 561941.0367 | 0 | 41.8329 | DD60+3 |  |  |  |  | 2025-11-01
ta506 | TA506 | 2025-11-01 | Supervisor | Anil Kumar | 31/0 | 624212.9859 | 0 | 46.4686 | DD45+6 |  |  |  |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | DEVI CONST. | 9/2. | 363759 | 0 | 36.159 | DA+0 | 25 | YES | YES | 26.10.2025 | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | DEVI CONST. | 7/2. | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | DEVI CONST. | 7/4. | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | DEVI CONST. | 8/1. | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | DEVI CONST. | 8/2. | 381585 | 0 | 37.931 | DA+3 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | DEVI CONST. | 8/3. | 381585 | 0 | 37.931 | DA+3 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | DEVI CONST. | 8/4. | 381585 | 0 | 37.931 | DA+3 | 40 | YES | YES | 03.11.2025 | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | DEVI CONST. | 9/3. | 440668 | 0 | 43.804 | DA+6 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | DEVI CONST. | 12/3. | 349997 | 0 | 34.789 | DA-3 | 40 | YES | YES | 11.11.2025 | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | DEVI CONST. | 12/4. | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | DEVI CONST. | 12/5. | 373608 | 0 | 37.138 | DA+1.5 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | Aravali Infra-1 | 15/3. | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | Aravali Infra-1 | 15/1. | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | Aravali Infra-1 | 15/4. | 440668 | 0 | 43.804 | DA+6 | 38 | YES | YES | WIP | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | DEVI CONST. | 7/0 | 676645 | 0 | 67.261 | DC2+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | DEVI CONST. | 7/3 | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | DEVI CONST. | 8/0 | 557827 | 0 | 55.45 | DB1+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | DEVI CONST. | 9/0 | 598570 | 0 | 59.5 | DB2+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | DEVI CONST. | 10/0 | 557827 | 0 | 55.45 | DB1+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | DEVI CONST. | 10/2 | 349997 | 0 | 34.789 | DA(-)3 | 40 | YES | YES | 08.11.2025 | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | DEVI CONST. | 10/3 | 381585 | 0 | 37.931 | DA+3 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | DEVI CONST. | 13/5 | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | Aravali Infra-1 | 15/7 | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | Aravali Infra-1 | 15/8 | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | Aravali Infra-1 | 15/9 | 381585 | 0 | 37.931 | DA+3 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | Aravali Infra-2 | 16/2 | 381585 | 0 | 36.159 | DA+0 | 25 | YES | YES | WIP | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | Aravali Infra-2 | 16/3 | 459711 | 0 | 45.697 | DA+9 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | Aravali Infra-2 | 16/5 | 440668 | 0 | 43.804 | DA+6 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | Aravali Infra-2 | 16/10 | 440668 | 0 | 43.804 | DA+6 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Gang | Aravali Infra-2 | 21/1 | 349997 | 0 | 34.789 | DA(-)3 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 9/2. | 363759 | 0 | 36.159 | DA+0 | 25 | YES | YES | 26.10.2025 | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 7/2. | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 7/4. | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 8/1. | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 8/2. | 381585 | 0 | 37.931 | DA+3 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 8/3. | 381585 | 0 | 37.931 | DA+3 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 8/4. | 381585 | 0 | 37.931 | DA+3 | 40 | YES | YES | 03.11.2025 | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 9/3. | 440668 | 0 | 43.804 | DA+6 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 12/3. | 349997 | 0 | 34.789 | DA-3 | 40 | YES | YES | 11.11.2025 | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 12/4. | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 12/5. | 373608 | 0 | 37.138 | DA+1.5 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 15/3. | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 15/1. | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 15/4. | 440668 | 0 | 43.804 | DA+6 | 38 | YES | YES | WIP | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 7/0 | 676645 | 0 | 67.261 | DC2+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 7/3 | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 8/0 | 557827 | 0 | 55.45 | DB1+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 9/0 | 598570 | 0 | 59.5 | DB2+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 10/0 | 557827 | 0 | 55.45 | DB1+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 10/2 | 349997 | 0 | 34.789 | DA(-)3 | 40 | YES | YES | 08.11.2025 | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 10/3 | 381585 | 0 | 37.931 | DA+3 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 13/5 | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 15/7 | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 15/8 | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 15/9 | 381585 | 0 | 37.931 | DA+3 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 16/2 | 381585 | 0 | 36.159 | DA+0 | 25 | YES | YES | WIP | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 16/3 | 459711 | 0 | 45.697 | DA+9 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 16/5 | 440668 | 0 | 43.804 | DA+6 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 16/10 | 440668 | 0 | 43.804 | DA+6 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Section Incharge | Prasanta Das | 21/1 | 349997 | 0 | 34.789 | DA(-)3 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Mr. Sunil chouhan | 9/2. | 363759 | 0 | 36.159 | DA+0 | 25 | YES | YES | 26.10.2025 | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Mr. Sunil chouhan | 7/2. | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Mr. Sunil chouhan | 7/4. | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Mr. Sunil chouhan | 8/1. | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Mr. Sunil chouhan | 8/2. | 381585 | 0 | 37.931 | DA+3 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Mr. Abhishekh Yadav | 8/3. | 381585 | 0 | 37.931 | DA+3 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Mr. Abhishekh Yadav | 8/4. | 381585 | 0 | 37.931 | DA+3 | 40 | YES | YES | 03.11.2025 | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Mr. Abhishekh Yadav | 9/3. | 440668 | 0 | 43.804 | DA+6 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Mr. Abhishekh Yadav | 12/3. | 349997 | 0 | 34.789 | DA-3 | 40 | YES | YES | 11.11.2025 | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Mr. Abhishekh Yadav | 12/4. | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Mr. Abhishekh Yadav | 12/5. | 373608 | 0 | 37.138 | DA+1.5 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Mr. Abhishekh Yadav | 15/3. | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Mr.Sumanta Bashu | 15/1. | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Tek lal maheto | 15/4. | 440668 | 0 | 43.804 | DA+6 | 38 | YES | YES | WIP | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Tek lal maheto | 7/0 | 676645 | 0 | 67.261 | DC2+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Tek lal maheto | 7/3 | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Tek lal maheto | 8/0 | 557827 | 0 | 55.45 | DB1+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Tek lal maheto | 9/0 | 598570 | 0 | 59.5 | DB2+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Mr.Sumanta Bashu | 10/0 | 557827 | 0 | 55.45 | DB1+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Mr.Sumanta Bashu | 10/2 | 349997 | 0 | 34.789 | DA(-)3 | 40 | YES | YES | 08.11.2025 | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Mr.Sumanta Bashu | 10/3 | 381585 | 0 | 37.931 | DA+3 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Mr.Sumanta Bashu | 13/5 | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Mr.Manjur alam | 15/7 | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Mr.Manjur alam | 15/8 | 363759 | 0 | 36.159 | DA+0 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Mr.Manjur alam | 15/9 | 381585 | 0 | 37.931 | DA+3 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Mr.Manjur alam | 16/2 | 381585 | 0 | 36.159 | DA+0 | 25 | YES | YES | WIP | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Mr. Sunil chouhan | 16/3 | 459711 | 0 | 45.697 | DA+9 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Mr.Manjur alam | 16/5 | 440668 | 0 | 43.804 | DA+6 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Mr.Sumanta Bashu | 16/10 | 440668 | 0 | 43.804 | DA+6 |  | YES | YES |  | 2025-11-01
ta509 | TA509 | 2025-11-01 | Supervisor | Tek lal maheto | 21/1 | 349997 | 0 | 34.789 | DA(-)3 |  | YES | YES |  | 2025-11-01
ta413 | TA413 | 2025-10-01 | Gang | Govind Mahto-01 | 3B/2 | 9316.84 | 0 | 1 | DA+9 | 36 |  | 2025-09-25 | 2025-09-26 | 2025-10-01 | 2025-10-08 | 2025-10-09
ta413 | TA413 | 2025-10-01 | Gang | Govind Mahto-01 | 2A/0 | 18633.68 | 0 | 2 | DD45+0 | 36 |  | 2025-10-06 | 2025-10-07 | 2025-10-01 | 2025-10-19 | 2025-10-20
ta413 | TA413 | 2025-10-01 | Gang | Govind Mahto-01 | 9/8 | 27950.52 | 0 | 3 | DA+0 | 36 |  | 2025-10-17 | 2025-10-18 | 2025-10-01 | 2025-10-25 | 2025-10-26
ta413 | TA413 | 2025-10-01 | Gang | Govind Mahto-01 | 9/9 | 37267.36 | 0 | 4 | DA+0 | 36 |  | 2025-10-23 | 2025-10-24 | 2025-10-01 | 2025-11-01 | 2025-11-02
ta413 | TA413 | 2025-10-01 | Gang | Jawla Singh-1 | 4/0 | 46584.2 | 0 | 5 | DB2+9 | 28 |  | 2025-09-24 | 2025-09-25 | 2025-10-01 | 2025-10-09 | 2025-10-10
ta413 | TA413 | 2025-10-01 | Gang | Jawla Singh-1 | 3A/0 | 55901.04 | 0 | 6 | DD45+3 | 28 |  | 2025-10-07 | 2025-10-08 | 2025-10-01 | 2025-10-19 | 2025-10-20
ta413 | TA413 | 2025-10-01 | Gang | Jawla Singh-1 | 9/10 | 65217.88 | 0 | 7 | DA+3 | 28 |  | 2025-10-18 | 2025-10-19 | 2025-10-01 | 2025-10-27 | 2025-10-28
ta413 | TA413 | 2025-10-01 | Gang | Jawla Singh-1 | 9/11 | 74534.72 | 0 | 8 | DA+3 | 28 |  | 2025-10-25 | 2025-10-26 | 2025-10-01 | 2025-11-03 | 2025-11-04
ta413 | TA413 | 2025-10-01 | Gang | Jwala Singh -2 | 3B/3 | 83851.56 | 0 | 9 | DA+6 | 26 |  | 2025-09-24 | 2025-09-25 | 2025-10-01 | 2025-10-10 | 2025-10-11
ta413 | TA413 | 2025-10-01 | Gang | Jwala Singh -2 | 15/7 | 93168.4 | 0 | 10 | DA+0 | 26 |  | 2025-10-09 | 2025-10-10 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta413 | TA413 | 2025-10-01 | Gang | Jwala Singh -2 | 15/9 | 102485.24 | 0 | 11 | DA+0 | 26 |  | 2025-10-19 | 2025-10-20 | 2025-10-01 | 2025-10-30 | 2025-10-31
ta413 | TA413 | 2025-10-01 | Gang | Govind Mahto-02 | 15/0 | 111802.08 | 0 | 12 | DD60+25 | 29 |  | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-10-13 | 2025-10-14
ta413 | TA413 | 2025-10-01 | Gang | Govind Mahto-02 | 15/1 | 121118.92 | 0 | 13 | DA+6 | 29 |  | 2025-10-11 | 2025-10-12 | 2025-10-01 | 2025-10-20 | 2025-10-21
ta413 | TA413 | 2025-10-01 | Gang | Govind Mahto-02 | 14/0 | 130435.76 | 0 | 14 | DD60+18 | 29 |  | 2025-10-18 | 2025-10-19 | 2025-10-01 | 2025-11-01 | 2025-11-02
ta413 | TA413 | 2025-10-01 | Gang | Bhairaw Mahto | 15/8 | 139752.6 | 0 | 15 | DA+1.5 | 47 |  | 2025-09-26 | 2025-09-27 | 2025-10-01 | 2025-10-07 | 2025-10-08
ta413 | TA413 | 2025-10-01 | Gang | Bhairaw Mahto | 17/0 | 149069.44 | 0 | 16 | DC1+3 | 47 |  | 2025-10-05 | 2025-10-06 | 2025-10-01 | 2025-10-18 | 2025-10-19
ta413 | TA413 | 2025-10-01 | Gang | Bhairaw Mahto | 13/0 | 158386.28 | 0 | 17 | DD60+9 | 47 |  | 2025-10-16 | 2025-10-17 | 2025-10-01 | 2025-11-01 | 2025-11-02
ta413 | TA413 | 2025-10-01 | Gang | Pritam Enterprises-1 | 10/0 | 167703.12 | 0 | 18 | DB1+6 | 30 |  | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-10-14 | 2025-10-15
ta413 | TA413 | 2025-10-01 | Gang | Pritam Enterprises-1 | 10/1 | 177019.96 | 0 | 19 | DA+3 | 30 |  | 2025-10-12 | 2025-10-13 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta413 | TA413 | 2025-10-01 | Gang | Pritam Enterprises-1 | 10/2 | 186336.8 | 0 | 20 | DA+3 | 30 |  | 2025-10-19 | 2025-10-20 | 2025-10-01 | 2025-10-28 | 2025-10-29
ta413 | TA413 | 2025-10-01 | Gang | Pritam Enterprises-2 | 3B/0 | 195653.64 | 0 | 21 | DB1+9 | 27 |  | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-10-11 | 2025-10-12
ta413 | TA413 | 2025-10-01 | Gang | Pritam Enterprises-2 | 15/11 | 204970.48 | 0 | 22 | DA+0 | 27 |  | 2025-10-09 | 2025-10-10 | 2025-10-01 | 2025-10-18 | 2025-10-19
ta413 | TA413 | 2025-10-01 | Gang | Pritam Enterprises-2 | 15/12 | 214287.32 | 0 | 23 | DA+6 | 27 |  | 2025-10-16 | 2025-10-17 | 2025-10-01 | 2025-10-25 | 2025-10-26
ta413 | TA413 | 2025-10-01 | Gang | Pritam Enterprises-3 | 3B/1 | 223604.16 | 0 | 24 | DA+3 | 38 |  | 2025-08-28 | 2025-08-29 | 2025-10-01 | 2025-09-09 | 2025-09-10
ta413 | TA413 | 2025-10-01 | Gang | Pritam Enterprises-3 | 11/0 | 232921 | 0 | 25 | DD45+0 | 38 |  | 2025-09-07 | 2025-09-08 | 2025-10-01 | 2025-09-21 | 2025-09-22
ta413 | TA413 | 2025-10-01 | Gang | Pritam Enterprises-3 | 21/0 | 242237.84 | 0 | 26 | DB1+0 | 38 |  | 2025-09-19 | 2025-09-20 | 2025-10-01 | 2025-10-03 | 2025-10-04
ta413 | TA413 | 2025-10-01 | Gang | Pritam Enterprises-3 | 21/1 | 251554.68 | 0 | 27 | DA+0 | 38 |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-10 | 2025-10-11
ta413 | TA413 | 2025-10-01 | Gang | Pritam Enterprises-4 | 3A/4 | 260871.52 | 0 | 28 | DA+0 | 29 |  | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-10-12 | 2025-10-13
ta413 | TA413 | 2025-10-01 | Gang | Pritam Enterprises-4 | 21/3 | 270188.36 | 0 | 29 | DA+6 | 29 |  | 2025-10-10 | 2025-10-11 | 2025-10-01 | 2025-10-18 | 2025-10-19
ta413 | TA413 | 2025-10-01 | Gang | Pritam Enterprises-4 | 21/4 | 279505.2 | 0 | 30 | DA+0 | 29 |  | 2025-10-16 | 2025-10-17 | 2025-10-01 | 2025-10-24 | 2025-10-25
ta413 | TA413 | 2025-10-01 | Gang | Pritam Enterprises-4 | 21/5 | 288822.04 | 0 | 31 | DA+0 | 29 |  | 2025-10-22 | 2025-10-23 | 2025-10-01 | 2025-10-30 | 2025-10-31
ta413 | TA413 | 2025-10-01 | Gang | SK.Samiul -1 | 30/2 | 298138.88 | 0 | 32 | DA+9 | 22 |  | 2025-09-18 | 2025-09-19 | 2025-10-01 | 2025-10-05 | 2025-10-06
ta413 | TA413 | 2025-10-01 | Gang | SK.Samiul -1 | 29A/0 | 307455.72 | 0 | 33 | DB1+0 | 22 |  | 2025-10-03 | 2025-10-04 | 2025-10-01 | 2025-10-11 | 2025-10-12
ta413 | TA413 | 2025-10-01 | Gang | SK.Samiul -1 | 30/5 | 316772.56 | 0 | 34 | DA+0 | 22 |  | 2025-10-09 | 2025-10-10 | 2025-10-01 | 2025-10-17 | 2025-10-18
ta413 | TA413 | 2025-10-01 | Gang | Punam kumari-1 | 20/0 | 326089.4 | 0 | 35 | DD60+3 | 33 |  | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-10-09 | 2025-10-10
ta413 | TA413 | 2025-10-01 | Gang | Punam kumari-1 | 20/3 | 335406.24 | 0 | 36 | DA+1.5 | 33 |  | 2025-10-07 | 2025-10-08 | 2025-10-01 | 2025-10-17 | 2025-10-18
ta413 | TA413 | 2025-10-01 | Gang | Punam kumari-1 | 20/4 | 344723.08 | 0 | 37 | DA+3 | 33 |  | 2025-10-15 | 2025-10-16 | 2025-10-01 | 2025-10-25 | 2025-10-26
ta413 | TA413 | 2025-10-01 | Gang | Punam kumari-1 | 20/5 | 354039.92 | 0 | 38 | DA+0 | 33 |  | 2025-10-23 | 2025-10-24 | 2025-10-01 | 2025-11-02 | 2025-11-03
ta413 | TA413 | 2025-10-01 | Gang | Punam kumari-2 | 18/4 | 363356.76 | 0 | 39 | DA-3 | 32 |  | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-10-07 | 2025-10-08
ta413 | TA413 | 2025-10-01 | Gang | Punam kumari-2 | 18/5 | 372673.6 | 0 | 40 | DA+0 | 32 |  | 2025-10-05 | 2025-10-06 | 2025-10-01 | 2025-10-14 | 2025-10-15
ta413 | TA413 | 2025-10-01 | Gang | Punam kumari-2 | 18/6 | 381990.44 | 0 | 41 | DA+9 | 32 |  | 2025-10-12 | 2025-10-13 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta413 | TA413 | 2025-10-01 | Gang | Punam kumari-2 | 18/7 | 391307.28 | 0 | 42 | DA+1.5 | 32 |  | 2025-10-19 | 2025-10-20 | 2025-10-01 | 2025-10-28 | 2025-10-29
ta413 | TA413 | 2025-10-01 | Gang | Punam Kumari 4 | 29A/5 | 400624.12 | 0 | 43 | DA+6 | 39 |  | 2025-09-24 | 2025-09-25 | 2025-10-01 | 2025-10-06 | 2025-10-07
ta413 | TA413 | 2025-10-01 | Gang | Punam Kumari 4 | 29A/4 | 409940.96 | 0 | 44 | DA+3 | 39 |  | 2025-10-04 | 2025-10-05 | 2025-10-01 | 2025-10-13 | 2025-10-14
ta413 | TA413 | 2025-10-01 | Gang | Punam Kumari 4 | 29A/3 | 419257.8 | 0 | 45 | DA+6 | 39 |  | 2025-10-11 | 2025-10-12 | 2025-10-01 | 2025-10-20 | 2025-10-21
ta413 | TA413 | 2025-10-01 | Gang | Fouzi Ratto | 46/0 | 428574.64 | 0 | 46 | DB1+12 | 42 |  | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-10 | 2025-10-11
ta413 | TA413 | 2025-10-01 | Gang | Fouzi Ratto | 43/0 | 437891.48 | 0 | 47 | DB1+0 | 42 |  | 2025-10-08 | 2025-10-09 | 2025-10-01 | 2025-10-19 | 2025-10-20
ta413 | TA413 | 2025-10-01 | Gang | Fouzi Ratto | 37/3 | 447208.32 | 0 | 48 | DA-1.5 | 42 |  | 2025-10-17 | 2025-10-18 | 2025-10-01 | 2025-10-28 | 2025-10-29
ta413 | TA413 | 2025-10-01 | Gang | Sherra Const. | 45/0 | 456525.16 | 0 | 49 | DB1+9 | 38 |  | 2025-09-27 | 2025-09-28 | 2025-10-01 | 2025-10-06 | 2025-10-07
ta413 | TA413 | 2025-10-01 | Gang | Sherra Const. | 43/1 | 465842 | 0 | 50 | DA-1.5 | 38 |  | 2025-10-04 | 2025-10-05 | 2025-10-01 | 2025-10-13 | 2025-10-14
ta413 | TA413 | 2025-10-01 | Gang | Sherra Const. | 37/2 | 475158.84 | 0 | 51 | DA+3 | 38 |  | 2025-10-11 | 2025-10-12 | 2025-10-01 | 2025-10-20 | 2025-10-21
ta413 | TA413 | 2025-10-01 | Gang | Amar Singh | 41/1 | 484475.68 | 0 | 52 | DA+9 | 25 |  | 2025-09-20 | 2025-09-21 | 2025-10-01 | 2025-10-05 | 2025-10-06
ta413 | TA413 | 2025-10-01 | Gang | Amar Singh | 41/0 | 493792.52 | 0 | 53 | DB1+9 | 25 |  | 2025-10-03 | 2025-10-04 | 2025-10-01 | 2025-10-17 | 2025-10-18
ta413 | TA413 | 2025-10-01 | Gang | Amar Singh | 24/0 | 503109.36 | 0 | 54 | DD60+18 | 25 |  | 2025-10-15 | 2025-10-16 | 2025-10-01 | 2025-10-31 | 2025-11-01
ta413 | TA413 | 2025-10-01 | Gang | Kartik Mahto | 40/10 | 512426.2 | 0 | 55 | DA+3 | 38 |  | 2025-09-28 | 2025-09-29 | 2025-10-01 | 2025-10-10 | 2025-10-11
ta413 | TA413 | 2025-10-01 | Gang | Kartik Mahto | 40/8 | 521743.04 | 0 | 56 | DA-1.5 | 38 |  | 2025-10-08 | 2025-10-09 | 2025-10-01 | 2025-10-16 | 2025-10-17
ta413 | TA413 | 2025-10-01 | Gang | Kartik Mahto | 25/0 | 531059.88 | 0 | 57 | DD60+18 | 38 |  | 2025-10-14 | 2025-10-15 | 2025-10-01 | 2025-11-05 | 2025-11-06
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 3B/2 | 9316.84 | 0 | 1 | DA+9 | 36 |  | 2025-09-25 | 2025-09-26 | 2025-10-01 | 2025-10-08 | 2025-10-09
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 2A/0 | 18633.68 | 0 | 2 | DD45+0 | 36 |  | 2025-10-06 | 2025-10-07 | 2025-10-01 | 2025-10-19 | 2025-10-20
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 9/8 | 27950.52 | 0 | 3 | DA+0 | 36 |  | 2025-10-17 | 2025-10-18 | 2025-10-01 | 2025-10-25 | 2025-10-26
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 9/9 | 37267.36 | 0 | 4 | DA+0 | 36 |  | 2025-10-23 | 2025-10-24 | 2025-10-01 | 2025-11-01 | 2025-11-02
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 4/0 | 46584.2 | 0 | 5 | DB2+9 | 28 |  | 2025-09-24 | 2025-09-25 | 2025-10-01 | 2025-10-09 | 2025-10-10
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 3A/0 | 55901.04 | 0 | 6 | DD45+3 | 28 |  | 2025-10-07 | 2025-10-08 | 2025-10-01 | 2025-10-19 | 2025-10-20
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 9/10 | 65217.88 | 0 | 7 | DA+3 | 28 |  | 2025-10-18 | 2025-10-19 | 2025-10-01 | 2025-10-27 | 2025-10-28
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 9/11 | 74534.72 | 0 | 8 | DA+3 | 28 |  | 2025-10-25 | 2025-10-26 | 2025-10-01 | 2025-11-03 | 2025-11-04
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 3B/3 | 83851.56 | 0 | 9 | DA+6 | 26 |  | 2025-09-24 | 2025-09-25 | 2025-10-01 | 2025-10-10 | 2025-10-11
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 15/7 | 93168.4 | 0 | 10 | DA+0 | 26 |  | 2025-10-09 | 2025-10-10 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 15/9 | 102485.24 | 0 | 11 | DA+0 | 26 |  | 2025-10-19 | 2025-10-20 | 2025-10-01 | 2025-10-30 | 2025-10-31
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 15/0 | 111802.08 | 0 | 12 | DD60+25 | 29 |  | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-10-13 | 2025-10-14
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 15/1 | 121118.92 | 0 | 13 | DA+6 | 29 |  | 2025-10-11 | 2025-10-12 | 2025-10-01 | 2025-10-20 | 2025-10-21
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 14/0 | 130435.76 | 0 | 14 | DD60+18 | 29 |  | 2025-10-18 | 2025-10-19 | 2025-10-01 | 2025-11-01 | 2025-11-02
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 15/8 | 139752.6 | 0 | 15 | DA+1.5 | 47 |  | 2025-09-26 | 2025-09-27 | 2025-10-01 | 2025-10-07 | 2025-10-08
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 17/0 | 149069.44 | 0 | 16 | DC1+3 | 47 |  | 2025-10-05 | 2025-10-06 | 2025-10-01 | 2025-10-18 | 2025-10-19
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 13/0 | 158386.28 | 0 | 17 | DD60+9 | 47 |  | 2025-10-16 | 2025-10-17 | 2025-10-01 | 2025-11-01 | 2025-11-02
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 10/0 | 167703.12 | 0 | 18 | DB1+6 | 30 |  | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-10-14 | 2025-10-15
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 10/1 | 177019.96 | 0 | 19 | DA+3 | 30 |  | 2025-10-12 | 2025-10-13 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 10/2 | 186336.8 | 0 | 20 | DA+3 | 30 |  | 2025-10-19 | 2025-10-20 | 2025-10-01 | 2025-10-28 | 2025-10-29
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 3B/0 | 195653.64 | 0 | 21 | DB1+9 | 27 |  | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-10-11 | 2025-10-12
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 15/11 | 204970.48 | 0 | 22 | DA+0 | 27 |  | 2025-10-09 | 2025-10-10 | 2025-10-01 | 2025-10-18 | 2025-10-19
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 15/12 | 214287.32 | 0 | 23 | DA+6 | 27 |  | 2025-10-16 | 2025-10-17 | 2025-10-01 | 2025-10-25 | 2025-10-26
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 3B/1 | 223604.16 | 0 | 24 | DA+3 | 38 |  | 2025-08-28 | 2025-08-29 | 2025-10-01 | 2025-09-09 | 2025-09-10
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 11/0 | 232921 | 0 | 25 | DD45+0 | 38 |  | 2025-09-07 | 2025-09-08 | 2025-10-01 | 2025-09-21 | 2025-09-22
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 21/0 | 242237.84 | 0 | 26 | DB1+0 | 38 |  | 2025-09-19 | 2025-09-20 | 2025-10-01 | 2025-10-03 | 2025-10-04
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 21/1 | 251554.68 | 0 | 27 | DA+0 | 38 |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-10 | 2025-10-11
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 3A/4 | 260871.52 | 0 | 28 | DA+0 | 29 |  | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-10-12 | 2025-10-13
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 21/3 | 270188.36 | 0 | 29 | DA+6 | 29 |  | 2025-10-10 | 2025-10-11 | 2025-10-01 | 2025-10-18 | 2025-10-19
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 21/4 | 279505.2 | 0 | 30 | DA+0 | 29 |  | 2025-10-16 | 2025-10-17 | 2025-10-01 | 2025-10-24 | 2025-10-25
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 21/5 | 288822.04 | 0 | 31 | DA+0 | 29 |  | 2025-10-22 | 2025-10-23 | 2025-10-01 | 2025-10-30 | 2025-10-31
ta413 | TA413 | 2025-10-01 | Section Incharge | Kartik Jhorar | 30/2 | 298138.88 | 0 | 32 | DA+9 | 22 |  | 2025-09-18 | 2025-09-19 | 2025-10-01 | 2025-10-05 | 2025-10-06
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 29A/0 | 307455.72 | 0 | 33 | DB1+0 | 22 |  | 2025-10-03 | 2025-10-04 | 2025-10-01 | 2025-10-11 | 2025-10-12
ta413 | TA413 | 2025-10-01 | Section Incharge | Kartik Jhorar | 30/5 | 316772.56 | 0 | 34 | DA+0 | 22 |  | 2025-10-09 | 2025-10-10 | 2025-10-01 | 2025-10-17 | 2025-10-18
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 20/0 | 326089.4 | 0 | 35 | DD60+3 | 33 |  | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-10-09 | 2025-10-10
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 20/3 | 335406.24 | 0 | 36 | DA+1.5 | 33 |  | 2025-10-07 | 2025-10-08 | 2025-10-01 | 2025-10-17 | 2025-10-18
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 20/4 | 344723.08 | 0 | 37 | DA+3 | 33 |  | 2025-10-15 | 2025-10-16 | 2025-10-01 | 2025-10-25 | 2025-10-26
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 20/5 | 354039.92 | 0 | 38 | DA+0 | 33 |  | 2025-10-23 | 2025-10-24 | 2025-10-01 | 2025-11-02 | 2025-11-03
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 18/4 | 363356.76 | 0 | 39 | DA-3 | 32 |  | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-10-07 | 2025-10-08
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 18/5 | 372673.6 | 0 | 40 | DA+0 | 32 |  | 2025-10-05 | 2025-10-06 | 2025-10-01 | 2025-10-14 | 2025-10-15
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 18/6 | 381990.44 | 0 | 41 | DA+9 | 32 |  | 2025-10-12 | 2025-10-13 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 18/7 | 391307.28 | 0 | 42 | DA+1.5 | 32 |  | 2025-10-19 | 2025-10-20 | 2025-10-01 | 2025-10-28 | 2025-10-29
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 29A/5 | 400624.12 | 0 | 43 | DA+6 | 39 |  | 2025-09-24 | 2025-09-25 | 2025-10-01 | 2025-10-06 | 2025-10-07
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 29A/4 | 409940.96 | 0 | 44 | DA+3 | 39 |  | 2025-10-04 | 2025-10-05 | 2025-10-01 | 2025-10-13 | 2025-10-14
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 29A/3 | 419257.8 | 0 | 45 | DA+6 | 39 |  | 2025-10-11 | 2025-10-12 | 2025-10-01 | 2025-10-20 | 2025-10-21
ta413 | TA413 | 2025-10-01 | Section Incharge | Kartik Jhorar | 46/0 | 428574.64 | 0 | 46 | DB1+12 | 42 |  | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-10 | 2025-10-11
ta413 | TA413 | 2025-10-01 | Section Incharge | Kartik Jhorar | 43/0 | 437891.48 | 0 | 47 | DB1+0 | 42 |  | 2025-10-08 | 2025-10-09 | 2025-10-01 | 2025-10-19 | 2025-10-20
ta413 | TA413 | 2025-10-01 | Section Incharge | Kartik Jhorar | 37/3 | 447208.32 | 0 | 48 | DA-1.5 | 42 |  | 2025-10-17 | 2025-10-18 | 2025-10-01 | 2025-10-28 | 2025-10-29
ta413 | TA413 | 2025-10-01 | Section Incharge | Kartik Jhorar | 45/0 | 456525.16 | 0 | 49 | DB1+9 | 38 |  | 2025-09-27 | 2025-09-28 | 2025-10-01 | 2025-10-06 | 2025-10-07
ta413 | TA413 | 2025-10-01 | Section Incharge | Kartik Jhorar | 43/1 | 465842 | 0 | 50 | DA-1.5 | 38 |  | 2025-10-04 | 2025-10-05 | 2025-10-01 | 2025-10-13 | 2025-10-14
ta413 | TA413 | 2025-10-01 | Section Incharge | Kartik Jhorar | 37/2 | 475158.84 | 0 | 51 | DA+3 | 38 |  | 2025-10-11 | 2025-10-12 | 2025-10-01 | 2025-10-20 | 2025-10-21
ta413 | TA413 | 2025-10-01 | Section Incharge | Kartik Jhorar | 41/1 | 484475.68 | 0 | 52 | DA+9 | 25 |  | 2025-09-20 | 2025-09-21 | 2025-10-01 | 2025-10-05 | 2025-10-06
ta413 | TA413 | 2025-10-01 | Section Incharge | Kartik Jhorar | 41/0 | 493792.52 | 0 | 53 | DB1+9 | 25 |  | 2025-10-03 | 2025-10-04 | 2025-10-01 | 2025-10-17 | 2025-10-18
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 24/0 | 503109.36 | 0 | 54 | DD60+18 | 25 |  | 2025-10-15 | 2025-10-16 | 2025-10-01 | 2025-10-31 | 2025-11-01
ta413 | TA413 | 2025-10-01 | Section Incharge | Kartik Jhorar | 40/10 | 512426.2 | 0 | 55 | DA+3 | 38 |  | 2025-09-28 | 2025-09-29 | 2025-10-01 | 2025-10-10 | 2025-10-11
ta413 | TA413 | 2025-10-01 | Section Incharge | Kartik Jhorar | 40/8 | 521743.04 | 0 | 56 | DA-1.5 | 38 |  | 2025-10-08 | 2025-10-09 | 2025-10-01 | 2025-10-16 | 2025-10-17
ta413 | TA413 | 2025-10-01 | Section Incharge | Shuvam Gupta | 25/0 | 531059.88 | 0 | 57 | DD60+18 | 38 |  | 2025-10-14 | 2025-10-15 | 2025-10-01 | 2025-11-05 | 2025-11-06
ta413 | TA413 | 2025-10-01 | Supervisor | Aman Kr Singh | 3B/2 | 9316.84 | 0 | 1 | DA+9 | 36 |  | 2025-09-25 | 2025-09-26 | 2025-10-01 | 2025-10-08 | 2025-10-09
ta413 | TA413 | 2025-10-01 | Supervisor | Aman Kr Singh | 2A/0 | 18633.68 | 0 | 2 | DD45+0 | 36 |  | 2025-10-06 | 2025-10-07 | 2025-10-01 | 2025-10-19 | 2025-10-20
ta413 | TA413 | 2025-10-01 | Supervisor | Aman Kr Singh | 9/8 | 27950.52 | 0 | 3 | DA+0 | 36 |  | 2025-10-17 | 2025-10-18 | 2025-10-01 | 2025-10-25 | 2025-10-26
ta413 | TA413 | 2025-10-01 | Supervisor | Aman Kr Singh | 9/9 | 37267.36 | 0 | 4 | DA+0 | 36 |  | 2025-10-23 | 2025-10-24 | 2025-10-01 | 2025-11-01 | 2025-11-02
ta413 | TA413 | 2025-10-01 | Supervisor | Kamal Ravidas | 4/0 | 46584.2 | 0 | 5 | DB2+9 | 28 |  | 2025-09-24 | 2025-09-25 | 2025-10-01 | 2025-10-09 | 2025-10-10
ta413 | TA413 | 2025-10-01 | Supervisor | Kamal Ravidas | 3A/0 | 55901.04 | 0 | 6 | DD45+3 | 28 |  | 2025-10-07 | 2025-10-08 | 2025-10-01 | 2025-10-19 | 2025-10-20
ta413 | TA413 | 2025-10-01 | Supervisor | Kamal Ravidas | 9/10 | 65217.88 | 0 | 7 | DA+3 | 28 |  | 2025-10-18 | 2025-10-19 | 2025-10-01 | 2025-10-27 | 2025-10-28
ta413 | TA413 | 2025-10-01 | Supervisor | Kamal Ravidas | 9/11 | 74534.72 | 0 | 8 | DA+3 | 28 |  | 2025-10-25 | 2025-10-26 | 2025-10-01 | 2025-11-03 | 2025-11-04
ta413 | TA413 | 2025-10-01 | Supervisor | Rudra Kumar | 3B/3 | 83851.56 | 0 | 9 | DA+6 | 26 |  | 2025-09-24 | 2025-09-25 | 2025-10-01 | 2025-10-10 | 2025-10-11
ta413 | TA413 | 2025-10-01 | Supervisor | Rudra Kumar | 15/7 | 93168.4 | 0 | 10 | DA+0 | 26 |  | 2025-10-09 | 2025-10-10 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta413 | TA413 | 2025-10-01 | Supervisor | Rudra Kumar | 15/9 | 102485.24 | 0 | 11 | DA+0 | 26 |  | 2025-10-19 | 2025-10-20 | 2025-10-01 | 2025-10-30 | 2025-10-31
ta413 | TA413 | 2025-10-01 | Supervisor | Sanjay Kumar | 15/0 | 111802.08 | 0 | 12 | DD60+25 | 29 |  | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-10-13 | 2025-10-14
ta413 | TA413 | 2025-10-01 | Supervisor | Sanjay Kumar | 15/1 | 121118.92 | 0 | 13 | DA+6 | 29 |  | 2025-10-11 | 2025-10-12 | 2025-10-01 | 2025-10-20 | 2025-10-21
ta413 | TA413 | 2025-10-01 | Supervisor | Sanjay Kumar | 14/0 | 130435.76 | 0 | 14 | DD60+18 | 29 |  | 2025-10-18 | 2025-10-19 | 2025-10-01 | 2025-11-01 | 2025-11-02
ta413 | TA413 | 2025-10-01 | Supervisor | Bhupendra Choudhary | 15/8 | 139752.6 | 0 | 15 | DA+1.5 | 47 |  | 2025-09-26 | 2025-09-27 | 2025-10-01 | 2025-10-07 | 2025-10-08
ta413 | TA413 | 2025-10-01 | Supervisor | Bhupendra Choudhary | 17/0 | 149069.44 | 0 | 16 | DC1+3 | 47 |  | 2025-10-05 | 2025-10-06 | 2025-10-01 | 2025-10-18 | 2025-10-19
ta413 | TA413 | 2025-10-01 | Supervisor | Bhupendra Choudhary | 13/0 | 158386.28 | 0 | 17 | DD60+9 | 47 |  | 2025-10-16 | 2025-10-17 | 2025-10-01 | 2025-11-01 | 2025-11-02
ta413 | TA413 | 2025-10-01 | Supervisor | Sanjay Kumar | 10/0 | 167703.12 | 0 | 18 | DB1+6 | 30 |  | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-10-14 | 2025-10-15
ta413 | TA413 | 2025-10-01 | Supervisor | Sanjay Kumar | 10/1 | 177019.96 | 0 | 19 | DA+3 | 30 |  | 2025-10-12 | 2025-10-13 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta413 | TA413 | 2025-10-01 | Supervisor | Sanjay Kumar | 10/2 | 186336.8 | 0 | 20 | DA+3 | 30 |  | 2025-10-19 | 2025-10-20 | 2025-10-01 | 2025-10-28 | 2025-10-29
ta413 | TA413 | 2025-10-01 | Supervisor | Akbar Ali | 3B/0 | 195653.64 | 0 | 21 | DB1+9 | 27 |  | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-10-11 | 2025-10-12
ta413 | TA413 | 2025-10-01 | Supervisor | Akbar Ali | 15/11 | 204970.48 | 0 | 22 | DA+0 | 27 |  | 2025-10-09 | 2025-10-10 | 2025-10-01 | 2025-10-18 | 2025-10-19
ta413 | TA413 | 2025-10-01 | Supervisor | Akbar Ali | 15/12 | 214287.32 | 0 | 23 | DA+6 | 27 |  | 2025-10-16 | 2025-10-17 | 2025-10-01 | 2025-10-25 | 2025-10-26
ta413 | TA413 | 2025-10-01 | Supervisor | Rudra Prasad | 3B/1 | 223604.16 | 0 | 24 | DA+3 | 38 |  | 2025-08-28 | 2025-08-29 | 2025-10-01 | 2025-09-09 | 2025-09-10
ta413 | TA413 | 2025-10-01 | Supervisor | Rudra Prasad | 11/0 | 232921 | 0 | 25 | DD45+0 | 38 |  | 2025-09-07 | 2025-09-08 | 2025-10-01 | 2025-09-21 | 2025-09-22
ta413 | TA413 | 2025-10-01 | Supervisor | Rudra Prasad | 21/0 | 242237.84 | 0 | 26 | DB1+0 | 38 |  | 2025-09-19 | 2025-09-20 | 2025-10-01 | 2025-10-03 | 2025-10-04
ta413 | TA413 | 2025-10-01 | Supervisor | Rudra Prasad | 21/1 | 251554.68 | 0 | 27 | DA+0 | 38 |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-10 | 2025-10-11
ta413 | TA413 | 2025-10-01 | Supervisor | Abhiya Ojha | 3A/4 | 260871.52 | 0 | 28 | DA+0 | 29 |  | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-10-12 | 2025-10-13
ta413 | TA413 | 2025-10-01 | Supervisor | Abhiya Ojha | 21/3 | 270188.36 | 0 | 29 | DA+6 | 29 |  | 2025-10-10 | 2025-10-11 | 2025-10-01 | 2025-10-18 | 2025-10-19
ta413 | TA413 | 2025-10-01 | Supervisor | Abhiya Ojha | 21/4 | 279505.2 | 0 | 30 | DA+0 | 29 |  | 2025-10-16 | 2025-10-17 | 2025-10-01 | 2025-10-24 | 2025-10-25
ta413 | TA413 | 2025-10-01 | Supervisor | Abhiya Ojha | 21/5 | 288822.04 | 0 | 31 | DA+0 | 29 |  | 2025-10-22 | 2025-10-23 | 2025-10-01 | 2025-10-30 | 2025-10-31
ta413 | TA413 | 2025-10-01 | Supervisor | Haridasn | 30/2 | 298138.88 | 0 | 32 | DA+9 | 22 |  | 2025-09-18 | 2025-09-19 | 2025-10-01 | 2025-10-05 | 2025-10-06
ta413 | TA413 | 2025-10-01 | Supervisor | Haridasn | 29A/0 | 307455.72 | 0 | 33 | DB1+0 | 22 |  | 2025-10-03 | 2025-10-04 | 2025-10-01 | 2025-10-11 | 2025-10-12
ta413 | TA413 | 2025-10-01 | Supervisor | Haridasn | 30/5 | 316772.56 | 0 | 34 | DA+0 | 22 |  | 2025-10-09 | 2025-10-10 | 2025-10-01 | 2025-10-17 | 2025-10-18
ta413 | TA413 | 2025-10-01 | Supervisor | Rahul Ravidas | 20/0 | 326089.4 | 0 | 35 | DD60+3 | 33 |  | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-10-09 | 2025-10-10
ta413 | TA413 | 2025-10-01 | Supervisor | Rahul Ravidas | 20/3 | 335406.24 | 0 | 36 | DA+1.5 | 33 |  | 2025-10-07 | 2025-10-08 | 2025-10-01 | 2025-10-17 | 2025-10-18
ta413 | TA413 | 2025-10-01 | Supervisor | Rahul Ravidas | 20/4 | 344723.08 | 0 | 37 | DA+3 | 33 |  | 2025-10-15 | 2025-10-16 | 2025-10-01 | 2025-10-25 | 2025-10-26
ta413 | TA413 | 2025-10-01 | Supervisor | Rahul Ravidas | 20/5 | 354039.92 | 0 | 38 | DA+0 | 33 |  | 2025-10-23 | 2025-10-24 | 2025-10-01 | 2025-11-02 | 2025-11-03
ta413 | TA413 | 2025-10-01 | Supervisor | Nabirul Islam | 18/4 | 363356.76 | 0 | 39 | DA-3 | 32 |  | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-10-07 | 2025-10-08
ta413 | TA413 | 2025-10-01 | Supervisor | Nabirul Islam | 18/5 | 372673.6 | 0 | 40 | DA+0 | 32 |  | 2025-10-05 | 2025-10-06 | 2025-10-01 | 2025-10-14 | 2025-10-15
ta413 | TA413 | 2025-10-01 | Supervisor | Nabirul Islam | 18/6 | 381990.44 | 0 | 41 | DA+9 | 32 |  | 2025-10-12 | 2025-10-13 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta413 | TA413 | 2025-10-01 | Supervisor | Nabirul Islam | 18/7 | 391307.28 | 0 | 42 | DA+1.5 | 32 |  | 2025-10-19 | 2025-10-20 | 2025-10-01 | 2025-10-28 | 2025-10-29
ta413 | TA413 | 2025-10-01 | Supervisor | Manoj Gupta | 29A/5 | 400624.12 | 0 | 43 | DA+6 | 39 |  | 2025-09-24 | 2025-09-25 | 2025-10-01 | 2025-10-06 | 2025-10-07
ta413 | TA413 | 2025-10-01 | Supervisor | Manoj Gupta | 29A/4 | 409940.96 | 0 | 44 | DA+3 | 39 |  | 2025-10-04 | 2025-10-05 | 2025-10-01 | 2025-10-13 | 2025-10-14
ta413 | TA413 | 2025-10-01 | Supervisor | Manoj Gupta | 29A/3 | 419257.8 | 0 | 45 | DA+6 | 39 |  | 2025-10-11 | 2025-10-12 | 2025-10-01 | 2025-10-20 | 2025-10-21
ta413 | TA413 | 2025-10-01 | Supervisor | Khooblal | 46/0 | 428574.64 | 0 | 46 | DB1+12 | 42 |  | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-10 | 2025-10-11
ta413 | TA413 | 2025-10-01 | Supervisor | Khooblal | 43/0 | 437891.48 | 0 | 47 | DB1+0 | 42 |  | 2025-10-08 | 2025-10-09 | 2025-10-01 | 2025-10-19 | 2025-10-20
ta413 | TA413 | 2025-10-01 | Supervisor | Khooblal | 37/3 | 447208.32 | 0 | 48 | DA-1.5 | 42 |  | 2025-10-17 | 2025-10-18 | 2025-10-01 | 2025-10-28 | 2025-10-29
ta413 | TA413 | 2025-10-01 | Supervisor | Manoj Kumar Choudhary | 45/0 | 456525.16 | 0 | 49 | DB1+9 | 38 |  | 2025-09-27 | 2025-09-28 | 2025-10-01 | 2025-10-06 | 2025-10-07
ta413 | TA413 | 2025-10-01 | Supervisor | Manoj Kumar Choudhary | 43/1 | 465842 | 0 | 50 | DA-1.5 | 38 |  | 2025-10-04 | 2025-10-05 | 2025-10-01 | 2025-10-13 | 2025-10-14
ta413 | TA413 | 2025-10-01 | Supervisor | Manoj Kumar Choudhary | 37/2 | 475158.84 | 0 | 51 | DA+3 | 38 |  | 2025-10-11 | 2025-10-12 | 2025-10-01 | 2025-10-20 | 2025-10-21
ta413 | TA413 | 2025-10-01 | Supervisor | Raju Mahto | 41/1 | 484475.68 | 0 | 52 | DA+9 | 25 |  | 2025-09-20 | 2025-09-21 | 2025-10-01 | 2025-10-05 | 2025-10-06
ta413 | TA413 | 2025-10-01 | Supervisor | Raju Mahto | 41/0 | 493792.52 | 0 | 53 | DB1+9 | 25 |  | 2025-10-03 | 2025-10-04 | 2025-10-01 | 2025-10-17 | 2025-10-18
ta413 | TA413 | 2025-10-01 | Supervisor | Raju Mahto | 24/0 | 503109.36 | 0 | 54 | DD60+18 | 25 |  | 2025-10-15 | 2025-10-16 | 2025-10-01 | 2025-10-31 | 2025-11-01
ta413 | TA413 | 2025-10-01 | Supervisor | Shuseel | 40/10 | 512426.2 | 0 | 55 | DA+3 | 38 |  | 2025-09-28 | 2025-09-29 | 2025-10-01 | 2025-10-10 | 2025-10-11
ta413 | TA413 | 2025-10-01 | Supervisor | Shuseel | 40/8 | 521743.04 | 0 | 56 | DA-1.5 | 38 |  | 2025-10-08 | 2025-10-09 | 2025-10-01 | 2025-10-16 | 2025-10-17
ta413 | TA413 | 2025-10-01 | Supervisor | Shuseel | 25/0 | 531059.88 | 0 | 57 | DD60+18 | 38 |  | 2025-10-14 | 2025-10-15 | 2025-10-01 | 2025-11-05 | 2025-11-06
ta416 | TA416 | 2025-10-01 | Gang | Maa Construction | 0/0 | 666437.14 | 0 | 98.118 | DCT+0 | 20 | NO | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta416 | TA416 | 2025-10-01 | Gang | Maa Construction | 2/2 | 371402 | 0 | 43.776 | DA+0 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-01 | 2025-10-29 | 2025-10-30
ta416 | TA416 | 2025-10-01 | Gang | Gourishankar | 22A/0 | 974538 | 0 | 110.575 | DB+25 | 23 | YES | 2025-09-27 | 2025-09-29 | 2025-10-01 | 2025-10-15 | 2025-10-16
ta416 | TA416 | 2025-10-01 | Gang | Gourishankar | 23/0 | 1004656 | 0 | 110.696 | DC+18 |  |  | 2025-09-14 | 2025-10-15 | 2025-10-01 | 2025-10-28 | 2025-10-29
ta416 | TA416 | 2025-10-01 | Gang | Reeta Bharti | 27/0 | 875860 | 0 | 101.692 | DD60+3 | 21 | NO | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta416 | TA416 | 2025-10-01 | Gang | Unity India | 37/0 | 1004656 | 0 | 110.696 | DC+18 | 22 | NO | 2025-09-24 | 2025-09-25 | 2025-10-01 | 2025-10-11 | 2025-10-12
ta416 | TA416 | 2025-10-01 | Gang | Unity India | 57/0 | 568303.9 | 0 | 64.482 | DB+0 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-01 | 2025-10-31 | 2025-11-01
ta416 | TA416 | 2025-10-01 | Gang | Ananya Trader-1 | 42/0 | 1492772 | 0 | 143.462 | DD60+18 | 36 | NO | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta416 | TA416 | 2025-10-01 | Gang | Amit choudhury | 46/0 | 568303.9 | 0 | 64.482 | DB+0 | 34 | NO | 2025-09-28 | 2025-10-01 | 2025-10-01 | 2025-10-11 | 2025-10-12
ta416 | TA416 | 2025-10-01 | Gang | Amit choudhury | 45/0 | 837742.5 | 0 | 97.229 | DD60+0 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-01 | 2025-10-31 | 2025-11-01
ta416 | TA416 | 2025-10-01 | Gang | Punam Kumari-1 | 50/0 | 1004656 | 0 | 110.696 | DC+18 | 31 | YES | 2025-09-28 | 2025-10-01 | 2025-10-01 | 2025-10-16 | 2025-10-17
ta416 | TA416 | 2025-10-01 | Gang | Punam Kumari-1 | 49/0 | 828626.51 | 0 | 90.125 | DC+9 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-01 | 2025-10-31 | 2025-11-01
ta416 | TA416 | 2025-10-01 | Gang | Sainik Trader | 53/0 | 666437.35 | 0 | 73.426 | DC+0 | 25 | NO | 2025-09-28 | 2025-10-01 | 2025-10-01 | 2025-10-13 | 2025-10-14
ta416 | TA416 | 2025-10-01 | Gang | Sainik Trader | 52/1 | 669569.35 | 0 | 75.897 | DB+6 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-01 | 2025-10-23 | 2025-10-24
ta416 | TA416 | 2025-10-01 | Gang | Sainik Trader | 53A/0 | 568303.9 | 0 | 64.482 | DB+0 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-01 | 2025-10-31 | 2025-11-01
ta416 | TA416 | 2025-10-01 | Gang | Spotify-1 | 53A/1 | 450627.94 | 0 | 53.324 | DA+6 | 26 | NO | 2025-09-28 | 2025-10-01 | 2025-10-01 | 2025-10-13 | 2025-10-14
ta416 | TA416 | 2025-10-01 | Gang | Spotify-1 | 52/7 | 450627.94 | 0 | 53.324 | DA+6 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-01 | 2025-10-23 | 2025-10-24
ta416 | TA416 | 2025-10-01 | Gang | Spotify-1 | 53A/7 | 371402 | 0 | 43.776 | DA+0 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-01 | 2025-10-24 | 2025-10-25
ta416 | TA416 | 2025-10-01 | Gang | Punam Kumari-2 | 54/0 | 601785.72 | 601785.72 | 67.112 | DB+3 | 24 | NO | 2025-09-25 | 2025-10-01 | 2025-10-01 | 2025-10-08 | 2025-10-09
ta416 | TA416 | 2025-10-01 | Gang | Punam Kumari-2 | 54/2 | 359483 | 0 | 42.374 | DA-3 |  | NO | 2025-10-12 | 2025-10-13 | 2025-10-01 | 2025-10-23 | 2025-10-24
ta416 | TA416 | 2025-10-01 | Gang | Punam Kumari-2 | 55/0 | 666437.35 | 0 | 73.426 | DC+0 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-01 | 2025-10-24 | 2025-10-25
ta416 | TA416 | 2025-10-01 | Gang | Spotify-1 | 56/6 | 371402 | 0 | 43.776 | DA+0 | 22 | NO | 2025-09-28 | 2025-10-01 | 2025-10-01 | 2025-10-13 | 2025-10-14
ta416 | TA416 | 2025-10-01 | Gang | Spotify-1 | 56/7 | 450627.94 | 0 | 53.324 | DA+6 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-01 | 2025-10-23 | 2025-10-24
ta416 | TA416 | 2025-10-01 | Gang | Spotify-1 | 55/1 | 359483 | 0 | 42.374 | DA-3 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-01 | 2025-10-24 | 2025-10-25
ta416 | TA416 | 2025-10-01 | Gang | Pankaj | 38/0 | 1004656 | 0 | 110.696 | DC+18 | 31 | NO | 2025-10-04 | 2025-10-05 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta416 | TA416 | 2025-10-01 | Gang | Pankaj | 57/1 | 359483 | 0 | 42.374 | DA-3 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-01 | 2025-10-31 | 2025-11-01
ta416 | TA416 | 2025-10-01 | Gang | Mahon Mahto | 63/0 | 708133.71 | 0 | 78.073 | DC+3 | 40 | NO | 2025-09-28 | 2025-10-01 | 2025-10-01 | 2025-10-08 | 2025-10-09
ta416 | TA416 | 2025-10-01 | Gang | Mahon Mahto | 61/0 | 1853580.61 | 0 | 188.378 | DD60+30 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-01 | 2025-10-22 | 2025-10-23
ta416 | TA416 | 2025-10-01 | Gang | Mahon Mahto | 62/0 | 1125399 | 0 | 124.037 | DC+25 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-01 | 2025-11-01 | 2025-11-02
ta416 | TA416 | 2025-10-01 | Gang | Kongres | 64/3 | 359483 | 359483 | 42.374 | DA-3 | 36 | NO | 2025-09-24 | 2025-09-28 | 2025-10-01 | 2025-10-08 | 2025-10-09
ta416 | TA416 | 2025-10-01 | Gang | Kongres | 69A/0 | 837742.5 | 0 | 97.229 | DD60+0 |  | NO | 2025-10-06 | 2025-10-07 | 2025-10-01 | 2025-10-16 | 2025-10-17
ta416 | TA416 | 2025-10-01 | Gang | Kongres | 58/0 | 1492772 | 0 | 143.462 | DD60+18 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-01 | 2025-10-31 | 2025-11-01
ta416 | TA416 | 2025-10-01 | Section Incharge | Prabin Patra | 0/0 | 666437.14 | 0 | 98.118 | DCT+0 | 20 | NO | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta416 | TA416 | 2025-10-01 | Section Incharge | Prabin Patra | 2/2 | 371402 | 0 | 43.776 | DA+0 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-01 | 2025-10-29 | 2025-10-30
ta416 | TA416 | 2025-10-01 | Section Incharge | Prabin Patra | 22A/0 | 974538 | 0 | 110.575 | DB+25 | 23 | YES | 2025-09-27 | 2025-09-29 | 2025-10-01 | 2025-10-15 | 2025-10-16
ta416 | TA416 | 2025-10-01 | Section Incharge | Prabin Patra | 23/0 | 1004656 | 0 | 110.696 | DC+18 |  |  | 2025-09-14 | 2025-10-15 | 2025-10-01 | 2025-10-28 | 2025-10-29
ta416 | TA416 | 2025-10-01 | Section Incharge | Prabin Patra | 27/0 | 875860 | 0 | 101.692 | DD60+3 | 21 | NO | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta416 | TA416 | 2025-10-01 | Section Incharge | D N Prasad | 37/0 | 1004656 | 0 | 110.696 | DC+18 | 22 | NO | 2025-09-24 | 2025-09-25 | 2025-10-01 | 2025-10-11 | 2025-10-12
ta416 | TA416 | 2025-10-01 | Section Incharge | D N Prasad | 57/0 | 568303.9 | 0 | 64.482 | DB+0 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-01 | 2025-10-31 | 2025-11-01
ta416 | TA416 | 2025-10-01 | Section Incharge | D N Prasad | 42/0 | 1492772 | 0 | 143.462 | DD60+18 | 36 | NO | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta416 | TA416 | 2025-10-01 | Section Incharge | D N Prasad | 46/0 | 568303.9 | 0 | 64.482 | DB+0 | 34 | NO | 2025-09-28 | 2025-10-01 | 2025-10-01 | 2025-10-11 | 2025-10-12
ta416 | TA416 | 2025-10-01 | Section Incharge | D N Prasad | 45/0 | 837742.5 | 0 | 97.229 | DD60+0 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-01 | 2025-10-31 | 2025-11-01
ta416 | TA416 | 2025-10-01 | Section Incharge | D N Prasad | 50/0 | 1004656 | 0 | 110.696 | DC+18 | 31 | YES | 2025-09-28 | 2025-10-01 | 2025-10-01 | 2025-10-16 | 2025-10-17
ta416 | TA416 | 2025-10-01 | Section Incharge | D N Prasad | 49/0 | 828626.51 | 0 | 90.125 | DC+9 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-01 | 2025-10-31 | 2025-11-01
ta416 | TA416 | 2025-10-01 | Section Incharge | D N Prasad | 53/0 | 666437.35 | 0 | 73.426 | DC+0 | 25 | NO | 2025-09-28 | 2025-10-01 | 2025-10-01 | 2025-10-13 | 2025-10-14
ta416 | TA416 | 2025-10-01 | Section Incharge | D N Prasad | 52/1 | 669569.35 | 0 | 75.897 | DB+6 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-01 | 2025-10-23 | 2025-10-24
ta416 | TA416 | 2025-10-01 | Section Incharge | D N Prasad | 53A/0 | 568303.9 | 0 | 64.482 | DB+0 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-01 | 2025-10-31 | 2025-11-01
ta416 | TA416 | 2025-10-01 | Section Incharge | D N Prasad | 53A/1 | 450627.94 | 0 | 53.324 | DA+6 | 26 | NO | 2025-09-28 | 2025-10-01 | 2025-10-01 | 2025-10-13 | 2025-10-14
ta416 | TA416 | 2025-10-01 | Section Incharge | D N Prasad | 52/7 | 450627.94 | 0 | 53.324 | DA+6 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-01 | 2025-10-23 | 2025-10-24
ta416 | TA416 | 2025-10-01 | Section Incharge | D N Prasad | 53A/7 | 371402 | 0 | 43.776 | DA+0 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-01 | 2025-10-24 | 2025-10-25
ta416 | TA416 | 2025-10-01 | Section Incharge | D N Prasad | 54/0 | 601785.72 | 601785.72 | 67.112 | DB+3 | 24 | NO | 2025-09-25 | 2025-10-01 | 2025-10-01 | 2025-10-08 | 2025-10-09
ta416 | TA416 | 2025-10-01 | Section Incharge | D N Prasad | 54/2 | 359483 | 0 | 42.374 | DA-3 |  | NO | 2025-10-12 | 2025-10-13 | 2025-10-01 | 2025-10-23 | 2025-10-24
ta416 | TA416 | 2025-10-01 | Section Incharge | D N Prasad | 55/0 | 666437.35 | 0 | 73.426 | DC+0 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-01 | 2025-10-24 | 2025-10-25
ta416 | TA416 | 2025-10-01 | Section Incharge | D N Prasad | 56/6 | 371402 | 0 | 43.776 | DA+0 | 22 | NO | 2025-09-28 | 2025-10-01 | 2025-10-01 | 2025-10-13 | 2025-10-14
ta416 | TA416 | 2025-10-01 | Section Incharge | D N Prasad | 56/7 | 450627.94 | 0 | 53.324 | DA+6 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-01 | 2025-10-23 | 2025-10-24
ta416 | TA416 | 2025-10-01 | Section Incharge | D N Prasad | 55/1 | 359483 | 0 | 42.374 | DA-3 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-01 | 2025-10-24 | 2025-10-25
ta416 | TA416 | 2025-10-01 | Section Incharge | D N Prasad | 38/0 | 1004656 | 0 | 110.696 | DC+18 | 31 | NO | 2025-10-04 | 2025-10-05 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta416 | TA416 | 2025-10-01 | Section Incharge | D N Prasad | 57/1 | 359483 | 0 | 42.374 | DA-3 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-01 | 2025-10-31 | 2025-11-01
ta416 | TA416 | 2025-10-01 | Section Incharge | D N Prasad | 63/0 | 708133.71 | 0 | 78.073 | DC+3 | 40 | NO | 2025-09-28 | 2025-10-01 | 2025-10-01 | 2025-10-08 | 2025-10-09
ta416 | TA416 | 2025-10-01 | Section Incharge | D N Prasad | 61/0 | 1853580.61 | 0 | 188.378 | DD60+30 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-01 | 2025-10-22 | 2025-10-23
ta416 | TA416 | 2025-10-01 | Section Incharge | D N Prasad | 62/0 | 1125399 | 0 | 124.037 | DC+25 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-01 | 2025-11-01 | 2025-11-02
ta416 | TA416 | 2025-10-01 | Section Incharge | D N Prasad | 64/3 | 359483 | 359483 | 42.374 | DA-3 | 36 | NO | 2025-09-24 | 2025-09-28 | 2025-10-01 | 2025-10-08 | 2025-10-09
ta416 | TA416 | 2025-10-01 | Section Incharge | D N Prasad | 69A/0 | 837742.5 | 0 | 97.229 | DD60+0 |  | NO | 2025-10-06 | 2025-10-07 | 2025-10-01 | 2025-10-16 | 2025-10-17
ta416 | TA416 | 2025-10-01 | Section Incharge | D N Prasad | 58/0 | 1492772 | 0 | 143.462 | DD60+18 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-01 | 2025-10-31 | 2025-11-01
ta416 | TA416 | 2025-10-01 | Supervisor | Churamani | 0/0 | 666437.14 | 0 | 98.118 | DCT+0 | 20 | NO | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta416 | TA416 | 2025-10-01 | Supervisor | Churamani | 2/2 | 371402 | 0 | 43.776 | DA+0 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-01 | 2025-10-29 | 2025-10-30
ta416 | TA416 | 2025-10-01 | Supervisor | Bijendra | 22A/0 | 974538 | 0 | 110.575 | DB+25 | 23 | YES | 2025-09-27 | 2025-09-29 | 2025-10-01 | 2025-10-15 | 2025-10-16
ta416 | TA416 | 2025-10-01 | Supervisor | Bijendra | 23/0 | 1004656 | 0 | 110.696 | DC+18 |  |  | 2025-09-14 | 2025-10-15 | 2025-10-01 | 2025-10-28 | 2025-10-29
ta416 | TA416 | 2025-10-01 | Supervisor | Rupesh | 27/0 | 875860 | 0 | 101.692 | DD60+3 | 21 | NO | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta416 | TA416 | 2025-10-01 | Supervisor | Maqbul | 37/0 | 1004656 | 0 | 110.696 | DC+18 | 22 | NO | 2025-09-24 | 2025-09-25 | 2025-10-01 | 2025-10-11 | 2025-10-12
ta416 | TA416 | 2025-10-01 | Supervisor | Maqbul | 57/0 | 568303.9 | 0 | 64.482 | DB+0 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-01 | 2025-10-31 | 2025-11-01
ta416 | TA416 | 2025-10-01 | Supervisor | Saidur | 42/0 | 1492772 | 0 | 143.462 | DD60+18 | 36 | NO | 2025-09-30 | 2025-10-01 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta416 | TA416 | 2025-10-01 | Supervisor | Ali raza | 46/0 | 568303.9 | 0 | 64.482 | DB+0 | 34 | NO | 2025-09-28 | 2025-10-01 | 2025-10-01 | 2025-10-11 | 2025-10-12
ta416 | TA416 | 2025-10-01 | Supervisor | Ali raza | 45/0 | 837742.5 | 0 | 97.229 | DD60+0 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-01 | 2025-10-31 | 2025-11-01
ta416 | TA416 | 2025-10-01 | Supervisor | Somenath | 50/0 | 1004656 | 0 | 110.696 | DC+18 | 31 | YES | 2025-09-28 | 2025-10-01 | 2025-10-01 | 2025-10-16 | 2025-10-17
ta416 | TA416 | 2025-10-01 | Supervisor | Somenath | 49/0 | 828626.51 | 0 | 90.125 | DC+9 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-01 | 2025-10-31 | 2025-11-01
ta416 | TA416 | 2025-10-01 | Supervisor | Afeludin | 53/0 | 666437.35 | 0 | 73.426 | DC+0 | 25 | NO | 2025-09-28 | 2025-10-01 | 2025-10-01 | 2025-10-13 | 2025-10-14
ta416 | TA416 | 2025-10-01 | Supervisor | Afeludin | 52/1 | 669569.35 | 0 | 75.897 | DB+6 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-01 | 2025-10-23 | 2025-10-24
ta416 | TA416 | 2025-10-01 | Supervisor | Afeludin | 53A/0 | 568303.9 | 0 | 64.482 | DB+0 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-01 | 2025-10-31 | 2025-11-01
ta416 | TA416 | 2025-10-01 | Supervisor | Akhtarul | 53A/1 | 450627.94 | 0 | 53.324 | DA+6 | 26 | NO | 2025-09-28 | 2025-10-01 | 2025-10-01 | 2025-10-13 | 2025-10-14
ta416 | TA416 | 2025-10-01 | Supervisor | Akhtarul | 52/7 | 450627.94 | 0 | 53.324 | DA+6 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-01 | 2025-10-23 | 2025-10-24
ta416 | TA416 | 2025-10-01 | Supervisor | Akhtarul | 53A/7 | 371402 | 0 | 43.776 | DA+0 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-01 | 2025-10-24 | 2025-10-25
ta416 | TA416 | 2025-10-01 | Supervisor | madhusudan | 54/0 | 601785.72 | 601785.72 | 67.112 | DB+3 | 24 | NO | 2025-09-25 | 2025-10-01 | 2025-10-01 | 2025-10-08 | 2025-10-09
ta416 | TA416 | 2025-10-01 | Supervisor | madhusudan | 54/2 | 359483 | 0 | 42.374 | DA-3 |  | NO | 2025-10-12 | 2025-10-13 | 2025-10-01 | 2025-10-23 | 2025-10-24
ta416 | TA416 | 2025-10-01 | Supervisor | madhusudan | 55/0 | 666437.35 | 0 | 73.426 | DC+0 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-01 | 2025-10-24 | 2025-10-25
ta416 | TA416 | 2025-10-01 | Supervisor | Akhtarul | 56/6 | 371402 | 0 | 43.776 | DA+0 | 22 | NO | 2025-09-28 | 2025-10-01 | 2025-10-01 | 2025-10-13 | 2025-10-14
ta416 | TA416 | 2025-10-01 | Supervisor | Akhtarul | 56/7 | 450627.94 | 0 | 53.324 | DA+6 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-01 | 2025-10-23 | 2025-10-24
ta416 | TA416 | 2025-10-01 | Supervisor | Akhtarul | 55/1 | 359483 | 0 | 42.374 | DA-3 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-01 | 2025-10-24 | 2025-10-25
ta416 | TA416 | 2025-10-01 | Supervisor | Maqbul | 38/0 | 1004656 | 0 | 110.696 | DC+18 | 31 | NO | 2025-10-04 | 2025-10-05 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta416 | TA416 | 2025-10-01 | Supervisor | Maqbul | 57/1 | 359483 | 0 | 42.374 | DA-3 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-01 | 2025-10-31 | 2025-11-01
ta416 | TA416 | 2025-10-01 | Supervisor | Ritlal | 63/0 | 708133.71 | 0 | 78.073 | DC+3 | 40 | NO | 2025-09-28 | 2025-10-01 | 2025-10-01 | 2025-10-08 | 2025-10-09
ta416 | TA416 | 2025-10-01 | Supervisor | Ritlal | 61/0 | 1853580.61 | 0 | 188.378 | DD60+30 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-01 | 2025-10-22 | 2025-10-23
ta416 | TA416 | 2025-10-01 | Supervisor | Ritlal | 62/0 | 1125399 | 0 | 124.037 | DC+25 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-01 | 2025-11-01 | 2025-11-02
ta416 | TA416 | 2025-10-01 | Supervisor | Ritlal | 64/3 | 359483 | 359483 | 42.374 | DA-3 | 36 | NO | 2025-09-24 | 2025-09-28 | 2025-10-01 | 2025-10-08 | 2025-10-09
ta416 | TA416 | 2025-10-01 | Supervisor | Ritlal | 69A/0 | 837742.5 | 0 | 97.229 | DD60+0 |  | NO | 2025-10-06 | 2025-10-07 | 2025-10-01 | 2025-10-16 | 2025-10-17
ta416 | TA416 | 2025-10-01 | Supervisor | Ritlal | 58/0 | 1492772 | 0 | 143.462 | DD60+18 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-01 | 2025-10-31 | 2025-11-01
ta419 | TA419 | 2025-10-01 | Gang | Infinidea 1 | 0B/0 | 555078.366 | 0 | 72.474 | DC1+6 | 25 | No | 2025-09-23 | WIP | 2025-10-01 | 2025-10-30 | 2025-10-25
ta419 | TA419 | 2025-10-01 | Gang | Infidia 1 | 40/4 | 284439.942 | 0 | 37.138 | DA+1.5 | 25 | No |  | 2025-10-21 | 2025-10-01 | 2025-11-04 | 2025-10-30
ta419 | TA419 | 2025-10-01 | Gang | Infidia 1 | 40/5 | 284439.942 | 0 | 37.138 | DA+1.5 | 25 | No |  | 2025-10-26 | 2025-10-01 | 2025-11-10 | 2025-11-05
ta419 | TA419 | 2025-10-01 | Gang | Madhu Sah | 3/3 | 272675.718 | 0 | 35.602 | DA-1.5 | 27 | No | 2025-09-27 | 2025-09-28 | 2025-10-01 | 2025-10-15 | 2025-10-10
ta419 | TA419 | 2025-10-01 | Gang | Madhu Sah | 3/4 | 335494.836 | 0 | 43.804 | DA+6 | 27 | No | 2025-10-10 | 2025-10-06 | 2025-10-01 | 2025-10-23 | 2025-10-18
ta419 | TA419 | 2025-10-01 | Gang | Madhu Sah | 38/5 | 290513.529 | 0 | 37.931 | DA+3 | 27 | No |  | 2025-10-15 | 2025-10-01 | 2025-11-01 | 2025-10-27
ta419 | TA419 | 2025-10-01 | Gang | Madhu Sah | 38/6 | 284439.942 | 0 | 37.138 | DA+1.5 | 27 | No |  | 2025-10-23 | 2025-10-01 | 2025-11-10 | 2025-11-05
ta419 | TA419 | 2025-10-01 | Gang | Poonam Kumari 1 | 16/0 | 531350.784 | 0 | 69.376 | DB2+6 | 29 | No | 2025-10-11 | WIP | 2025-10-01 | 2025-10-31 | 2025-10-26
ta419 | TA419 | 2025-10-01 | Gang | Poonam Kumari 1 | 15/0 | 478258.596 | 0 | 62.444 | DC1+0 | 29 | No |  | 2025-10-23 | 2025-10-01 | 2025-11-10 | 2025-11-05
ta419 | TA419 | 2025-10-01 | Gang | Poonam Kumari 2 | 31/2 | 276949.44 | 0 | 36.16 | DA+0 | 30 | No | 2025-10-14 | WIP | 2025-10-01 | 2025-10-31 | 2025-10-26
ta419 | TA419 | 2025-10-01 | Gang | Poonam Kumari 2 | 30/0 | 290513.529 | 0 | 37.931 | DA+3 | 30 | No |  | 2025-10-22 | 2025-10-01 | 2025-11-10 | 2025-11-05
ta419 | TA419 | 2025-10-01 | Gang | Radha Enterprises | 21/0 | 1049635.314 | 0 | 137.046 | DD60+25 | 24 | No | 2025-09-12 | 2025-09-14 | 2025-10-01 | 2025-10-15 | 2025-10-10
ta419 | TA419 | 2025-10-01 | Gang | Radha Enterprises | 26/0 | 764207.361 | 0 | 99.779 | DC2+18 | 24 | No | 2025-10-16 | WIP | 2025-10-01 | 2025-11-03 | 2025-10-29
ta419 | TA419 | 2025-10-01 | Gang | Radha Enterprises | 38/11 | 276949.44 | 0 | 36.16 | DA+0 | 24 | No |  | 2025-10-25 | 2025-10-01 | 2025-11-10 | 2025-11-05
ta419 | TA419 | 2025-10-01 | Gang | Jwala Singh | 36/6 | 276949.44 | 0 | 36.16 | DA+0 | 28 | No |  | 2025-10-17 | 2025-10-01 | 2025-10-31 | 2025-10-26
ta419 | TA419 | 2025-10-01 | Gang | Jwala Singh | 36/7 | 276949.44 | 0 | 36.16 | DA+0 | 28 | No |  | 2025-10-21 | 2025-10-01 | 2025-11-05 | 2025-10-31
ta419 | TA419 | 2025-10-01 | Gang | Jwala Singh | 36/8 | 276949.44 | 0 | 36.16 | DA+0 | 28 | No |  | 2025-10-26 | 2025-10-01 | 2025-11-10 | 2025-11-05
ta419 | TA419 | 2025-10-01 | Section Incharge | Mr. Tanay Kumar | 0B/0 | 555078.366 | 0 | 72.474 | DC1+6 | 25 | No | 2025-09-23 | WIP | 2025-10-01 | 2025-10-30 | 2025-10-25
ta419 | TA419 | 2025-10-01 | Section Incharge | Mr. Tanay Kumar | 40/4 | 284439.942 | 0 | 37.138 | DA+1.5 | 25 | No |  | 2025-10-21 | 2025-10-01 | 2025-11-04 | 2025-10-30
ta419 | TA419 | 2025-10-01 | Section Incharge | Mr. Tanay Kumar | 40/5 | 284439.942 | 0 | 37.138 | DA+1.5 | 25 | No |  | 2025-10-26 | 2025-10-01 | 2025-11-10 | 2025-11-05
ta419 | TA419 | 2025-10-01 | Section Incharge | Mr. Tanay Kumar | 3/3 | 272675.718 | 0 | 35.602 | DA-1.5 | 27 | No | 2025-09-27 | 2025-09-28 | 2025-10-01 | 2025-10-15 | 2025-10-10
ta419 | TA419 | 2025-10-01 | Section Incharge | Mr. Tanay Kumar | 3/4 | 335494.836 | 0 | 43.804 | DA+6 | 27 | No | 2025-10-10 | 2025-10-06 | 2025-10-01 | 2025-10-23 | 2025-10-18
ta419 | TA419 | 2025-10-01 | Section Incharge | Mr. Tanay Kumar | 38/5 | 290513.529 | 0 | 37.931 | DA+3 | 27 | No |  | 2025-10-15 | 2025-10-01 | 2025-11-01 | 2025-10-27
ta419 | TA419 | 2025-10-01 | Section Incharge | Mr. Tanay Kumar | 38/6 | 284439.942 | 0 | 37.138 | DA+1.5 | 27 | No |  | 2025-10-23 | 2025-10-01 | 2025-11-10 | 2025-11-05
ta419 | TA419 | 2025-10-01 | Section Incharge | Mr. Tanay Kumar | 16/0 | 531350.784 | 0 | 69.376 | DB2+6 | 29 | No | 2025-10-11 | WIP | 2025-10-01 | 2025-10-31 | 2025-10-26
ta419 | TA419 | 2025-10-01 | Section Incharge | Mr. Tanay Kumar | 15/0 | 478258.596 | 0 | 62.444 | DC1+0 | 29 | No |  | 2025-10-23 | 2025-10-01 | 2025-11-10 | 2025-11-05
ta419 | TA419 | 2025-10-01 | Section Incharge | Mr. Tanay Kumar | 31/2 | 276949.44 | 0 | 36.16 | DA+0 | 30 | No | 2025-10-14 | WIP | 2025-10-01 | 2025-10-31 | 2025-10-26
ta419 | TA419 | 2025-10-01 | Section Incharge | Mr. Tanay Kumar | 30/0 | 290513.529 | 0 | 37.931 | DA+3 | 30 | No |  | 2025-10-22 | 2025-10-01 | 2025-11-10 | 2025-11-05
ta419 | TA419 | 2025-10-01 | Section Incharge | Mr. Tanay Kumar | 21/0 | 1049635.314 | 0 | 137.046 | DD60+25 | 24 | No | 2025-09-12 | 2025-09-14 | 2025-10-01 | 2025-10-15 | 2025-10-10
ta419 | TA419 | 2025-10-01 | Section Incharge | Mr. Tanay Kumar | 26/0 | 764207.361 | 0 | 99.779 | DC2+18 | 24 | No | 2025-10-16 | WIP | 2025-10-01 | 2025-11-03 | 2025-10-29
ta419 | TA419 | 2025-10-01 | Section Incharge | Mr. Tanay Kumar | 38/11 | 276949.44 | 0 | 36.16 | DA+0 | 24 | No |  | 2025-10-25 | 2025-10-01 | 2025-11-10 | 2025-11-05
ta419 | TA419 | 2025-10-01 | Section Incharge | Mr. Tanay Kumar | 36/6 | 276949.44 | 0 | 36.16 | DA+0 | 28 | No |  | 2025-10-17 | 2025-10-01 | 2025-10-31 | 2025-10-26
ta419 | TA419 | 2025-10-01 | Section Incharge | Mr. Tanay Kumar | 36/7 | 276949.44 | 0 | 36.16 | DA+0 | 28 | No |  | 2025-10-21 | 2025-10-01 | 2025-11-05 | 2025-10-31
ta419 | TA419 | 2025-10-01 | Section Incharge | Mr. Tanay Kumar | 36/8 | 276949.44 | 0 | 36.16 | DA+0 | 28 | No |  | 2025-10-26 | 2025-10-01 | 2025-11-10 | 2025-11-05
ta419 | TA419 | 2025-10-01 | Supervisor | Mr. Abhishek | 0B/0 | 555078.366 | 0 | 72.474 | DC1+6 | 25 | No | 2025-09-23 | WIP | 2025-10-01 | 2025-10-30 | 2025-10-25
ta419 | TA419 | 2025-10-01 | Supervisor | Mr. Abhishek | 40/4 | 284439.942 | 0 | 37.138 | DA+1.5 | 25 | No |  | 2025-10-21 | 2025-10-01 | 2025-11-04 | 2025-10-30
ta419 | TA419 | 2025-10-01 | Supervisor | Mr. Abhishek | 40/5 | 284439.942 | 0 | 37.138 | DA+1.5 | 25 | No |  | 2025-10-26 | 2025-10-01 | 2025-11-10 | 2025-11-05
ta419 | TA419 | 2025-10-01 | Supervisor | Mr. prince | 3/3 | 272675.718 | 0 | 35.602 | DA-1.5 | 27 | No | 2025-09-27 | 2025-09-28 | 2025-10-01 | 2025-10-15 | 2025-10-10
ta419 | TA419 | 2025-10-01 | Supervisor | Mr. prince | 3/4 | 335494.836 | 0 | 43.804 | DA+6 | 27 | No | 2025-10-10 | 2025-10-06 | 2025-10-01 | 2025-10-23 | 2025-10-18
ta419 | TA419 | 2025-10-01 | Supervisor | Mr. prince | 38/5 | 290513.529 | 0 | 37.931 | DA+3 | 27 | No |  | 2025-10-15 | 2025-10-01 | 2025-11-01 | 2025-10-27
ta419 | TA419 | 2025-10-01 | Supervisor | Mr. prince | 38/6 | 284439.942 | 0 | 37.138 | DA+1.5 | 27 | No |  | 2025-10-23 | 2025-10-01 | 2025-11-10 | 2025-11-05
ta419 | TA419 | 2025-10-01 | Supervisor | Mr. PD Sharma | 16/0 | 531350.784 | 0 | 69.376 | DB2+6 | 29 | No | 2025-10-11 | WIP | 2025-10-01 | 2025-10-31 | 2025-10-26
ta419 | TA419 | 2025-10-01 | Supervisor | Mr. PD Sharma | 15/0 | 478258.596 | 0 | 62.444 | DC1+0 | 29 | No |  | 2025-10-23 | 2025-10-01 | 2025-11-10 | 2025-11-05
ta419 | TA419 | 2025-10-01 | Supervisor | Mr. Satyaprakash | 31/2 | 276949.44 | 0 | 36.16 | DA+0 | 30 | No | 2025-10-14 | WIP | 2025-10-01 | 2025-10-31 | 2025-10-26
ta419 | TA419 | 2025-10-01 | Supervisor | Mr. Satyaprakash | 30/0 | 290513.529 | 0 | 37.931 | DA+3 | 30 | No |  | 2025-10-22 | 2025-10-01 | 2025-11-10 | 2025-11-05
ta419 | TA419 | 2025-10-01 | Supervisor | Mr Sunil | 21/0 | 1049635.314 | 0 | 137.046 | DD60+25 | 24 | No | 2025-09-12 | 2025-09-14 | 2025-10-01 | 2025-10-15 | 2025-10-10
ta419 | TA419 | 2025-10-01 | Supervisor | Mr Sunil | 26/0 | 764207.361 | 0 | 99.779 | DC2+18 | 24 | No | 2025-10-16 | WIP | 2025-10-01 | 2025-11-03 | 2025-10-29
ta419 | TA419 | 2025-10-01 | Supervisor | Mr Sunil | 38/11 | 276949.44 | 0 | 36.16 | DA+0 | 24 | No |  | 2025-10-25 | 2025-10-01 | 2025-11-10 | 2025-11-05
ta419 | TA419 | 2025-10-01 | Supervisor | Mr. Yogendra | 36/6 | 276949.44 | 0 | 36.16 | DA+0 | 28 | No |  | 2025-10-17 | 2025-10-01 | 2025-10-31 | 2025-10-26
ta419 | TA419 | 2025-10-01 | Supervisor | Mr. Yogendra | 36/7 | 276949.44 | 0 | 36.16 | DA+0 | 28 | No |  | 2025-10-21 | 2025-10-01 | 2025-11-05 | 2025-10-31
ta419 | TA419 | 2025-10-01 | Supervisor | Mr. Yogendra | 36/8 | 276949.44 | 0 | 36.16 | DA+0 | 28 | No |  | 2025-10-26 | 2025-10-01 | 2025-11-10 | 2025-11-05
ta421 | TA421 | 2025-10-01 | Gang | Subash | 1/0 | 661012 | 0 | 72.63 | 2D60+0 | 33 | No |  | WIP | 2025-10-01 | 2025-10-18 | 2025-10-13
ta421 | TA421 | 2025-10-01 | Gang | Subash | 4/3 | 347642 | 0 | 37.7169 | 2DA+6 | 33 | No | 2025-10-08 | 2025-10-09 | 2025-10-01 | 2025-10-22 | 2025-10-17
ta421 | TA421 | 2025-10-01 | Gang | Subash | 4/1 | 307108 | 0 | 33.38 | 2DA+3 | 33 | No | 2025-10-10 | 2025-10-13 | 2025-10-01 | 2025-10-26 | 2025-10-21
ta421 | TA421 | 2025-10-01 | Gang | Subash | 4/4 | 292211 | 0 | 31.99 | 2DA+0 | 33 | No | 2025-10-15 | 2025-10-17 | 2025-10-01 | 2025-10-30 | 2025-10-25
ta421 | TA421 | 2025-10-01 | Gang | Subash | 4/5 | 307108 | 0 | 33.38 | 2DA+3 | 33 | No | 2025-10-17 | 2025-10-21 | 2025-10-01 | 2025-11-03 | 2025-10-29
ta421 | TA421 | 2025-10-01 | Gang | Subash | 4/8 | 307108 | 0 | 33.38 | 2DA+3 | 33 | No | 2025-10-21 | 2025-10-25 | 2025-10-01 | 2025-11-06 | 2025-11-01
ta421 | TA421 | 2025-10-01 | Gang | Subash | 4/11 | 347642 | 0 | 37.7169 | 2DA+6 | 33 | No | 2025-10-25 | 2025-10-28 | 2025-10-01 | 2025-11-10 | 2025-11-05
ta421 | TA421 | 2025-10-01 | Gang | Shakila Khatun | 4/18 | 292211 | 0 | 31.99 | 2DA+0 | 32 | No |  | Completed | 2025-10-01 | 2025-10-15 | 2025-10-10
ta421 | TA421 | 2025-10-01 | Gang | Shakila Khatun | 9/3 | 362229 | 0 | 39.1682 | 2DA+9 | 32 | No | 2025-10-05 | 2025-10-06 | 2025-10-01 | 2025-10-19 | 2025-10-14
ta421 | TA421 | 2025-10-01 | Gang | Shakila Khatun | 4/19 | 347642 | 0 | 37.7169 | 2DA+6 | 32 | No | 2025-10-07 | 2025-10-10 | 2025-10-01 | 2025-10-24 | 2025-10-19
ta421 | TA421 | 2025-10-01 | Gang | Shakila Khatun | 4/20 | 362229 | 0 | 39.1682 | 2DA+9 | 32 | No | 2025-10-11 | 2025-10-15 | 2025-10-01 | 2025-10-29 | 2025-10-24
ta421 | TA421 | 2025-10-01 | Gang | Shakila Khatun | 4/13 | 292211 | 0 | 31.99 | 2DA+0 | 32 | No | 2025-10-16 | 2025-10-20 | 2025-10-01 | 2025-11-04 | 2025-10-30
ta421 | TA421 | 2025-10-01 | Gang | Shakila Khatun | 4/14 | 307108 | 0 | 33.38 | 2DA+3 | 32 | No | 2025-10-23 | 2025-10-26 | 2025-10-01 | 2025-11-10 | 2025-11-05
ta421 | TA421 | 2025-10-01 | Gang | Nasiruddin (Bulbul ) | 39/2 | 327992 | 0 | 36.372 | 3DA+0 | 24 | No |  | WIP | 2025-10-01 | 2025-10-15 | 2025-10-10
ta421 | TA421 | 2025-10-01 | Gang | Nasiruddin (Bulbul ) | 39/9 | 406294 | 0 | 44.85 | 3DA+9 | 24 | No | 2025-09-29 | 2025-10-06 | 2025-10-01 | 2025-10-20 | 2025-10-15
ta421 | TA421 | 2025-10-01 | Gang | Nasiruddin (Bulbul ) | 36/7 | 342752 | 0 | 37.931 | 3DA+3 | 24 | No | 2025-10-09 | 2025-10-11 | 2025-10-01 | 2025-10-25 | 2025-10-20
ta421 | TA421 | 2025-10-01 | Gang | Nasiruddin (Bulbul ) | 36/8 | 327992 | 0 | 36.372 | 3DA+0 | 24 | No | 2025-10-14 | 2025-10-16 | 2025-10-01 | 2025-11-01 | 2025-10-27
ta421 | TA421 | 2025-10-01 | Gang | Nasiruddin (Bulbul ) | 37/0 | 478941 | 0 | 54.66 | 3DB2+0 | 24 | No | 2025-10-20 | 2025-10-23 | 2025-10-01 | 2025-11-09 | 2025-11-04
ta421 | TA421 | 2025-10-01 | Gang | Sabhnam Praveen | 39/7 | 391124 | 0 | 43.08 | 3DA+6 | 20 | No |  | WIP | 2025-10-01 | 2025-10-17 | 2025-10-12
ta421 | TA421 | 2025-10-01 | Gang | Sabhnam Praveen | 16/11 | 342752 | 0 | 37.931 | 3DA+3 | 20 | No | 2025-10-07 | 2025-10-08 | 2025-10-01 | 2025-10-27 | 2025-10-22
ta421 | TA421 | 2025-10-01 | Gang | Sabhnam Praveen | 11/4 | 327992 | 0 | 36.372 | 3DA+0 | 20 | No | 2025-10-15 | 2025-10-18 | 2025-10-01 | 2025-10-29 | 2025-10-30
ta421 | TA421 | 2025-10-01 | Gang | Rajiv Yadhav | 11/7 | 327992 | 0 | 36.372 | 3DA+0 | 22 | No | 2025-10-09 | 2025-10-11 | 2025-10-01 | 2025-10-25 | 2025-10-24
ta421 | TA421 | 2025-10-01 | Gang | Rajiv Yadhav | 11/8 | 327992 | 0 | 36.372 | 3DA+0 | 22 | No | 2025-10-18 | 2025-10-21 | 2025-10-01 | 2025-10-30 | 2025-10-29
ta421 | TA421 | 2025-10-01 | Gang | D K Verma | 43/4 | 342752 | 0 | 37.931 | 3DA+3 | 25 | yes |  | Completed | 2025-10-01 | 2025-10-17 | 2025-10-12
ta421 | TA421 | 2025-10-01 | Gang | D K Verma | 43/5 | 406294 | 0 | 44.85 | 3DA+9 | 25 | yes | 2025-09-25 | 2025-10-08 | 2025-10-01 | 2025-10-23 | 2025-10-18
ta421 | TA421 | 2025-10-01 | Gang | D K Verma | 43/3 | 327992 | 0 | 36.372 | 3DA+0 | 25 | yes | 2025-10-03 | 2025-10-14 | 2025-10-01 | 2025-10-28 | 2025-10-23
ta421 | TA421 | 2025-10-01 | Gang | D K Verma | 41/1 | 342752 | 0 | 36.372 | 3DA+3 | 25 | yes | 2025-10-12 | 2025-10-19 | 2025-10-01 | 2025-11-03 | 2025-10-29
ta421 | TA421 | 2025-10-01 | Gang | D K Verma | 42/2 | 327992 | 0 | 36.372 | 3DA+0 | 25 | yes | 2025-10-20 | 2025-10-25 | 2025-10-01 | 2025-11-10 | 2025-11-05
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Manikandan | 1/0 | 661012 | 0 | 72.63 | 2D60+0 | 33 | No |  | WIP | 2025-10-01 | 2025-10-18 | 2025-10-13
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Manikandan | 4/3 | 347642 | 0 | 37.7169 | 2DA+6 | 33 | No | 2025-10-08 | 2025-10-09 | 2025-10-01 | 2025-10-22 | 2025-10-17
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Manikandan | 4/1 | 307108 | 0 | 33.38 | 2DA+3 | 33 | No | 2025-10-10 | 2025-10-13 | 2025-10-01 | 2025-10-26 | 2025-10-21
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Manikandan | 4/4 | 292211 | 0 | 31.99 | 2DA+0 | 33 | No | 2025-10-15 | 2025-10-17 | 2025-10-01 | 2025-10-30 | 2025-10-25
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Manikandan | 4/5 | 307108 | 0 | 33.38 | 2DA+3 | 33 | No | 2025-10-17 | 2025-10-21 | 2025-10-01 | 2025-11-03 | 2025-10-29
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Manikandan | 4/8 | 307108 | 0 | 33.38 | 2DA+3 | 33 | No | 2025-10-21 | 2025-10-25 | 2025-10-01 | 2025-11-06 | 2025-11-01
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Manikandan | 4/11 | 347642 | 0 | 37.7169 | 2DA+6 | 33 | No | 2025-10-25 | 2025-10-28 | 2025-10-01 | 2025-11-10 | 2025-11-05
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Manikandan | 4/18 | 292211 | 0 | 31.99 | 2DA+0 | 32 | No |  | Completed | 2025-10-01 | 2025-10-15 | 2025-10-10
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Manikandan | 9/3 | 362229 | 0 | 39.1682 | 2DA+9 | 32 | No | 2025-10-05 | 2025-10-06 | 2025-10-01 | 2025-10-19 | 2025-10-14
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Manikandan | 4/19 | 347642 | 0 | 37.7169 | 2DA+6 | 32 | No | 2025-10-07 | 2025-10-10 | 2025-10-01 | 2025-10-24 | 2025-10-19
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Manikandan | 4/20 | 362229 | 0 | 39.1682 | 2DA+9 | 32 | No | 2025-10-11 | 2025-10-15 | 2025-10-01 | 2025-10-29 | 2025-10-24
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Manikandan | 4/13 | 292211 | 0 | 31.99 | 2DA+0 | 32 | No | 2025-10-16 | 2025-10-20 | 2025-10-01 | 2025-11-04 | 2025-10-30
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Manikandan | 4/14 | 307108 | 0 | 33.38 | 2DA+3 | 32 | No | 2025-10-23 | 2025-10-26 | 2025-10-01 | 2025-11-10 | 2025-11-05
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Satyam Tiwari | 39/2 | 327992 | 0 | 36.372 | 3DA+0 | 24 | No |  | WIP | 2025-10-01 | 2025-10-15 | 2025-10-10
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Satyam Tiwari | 39/9 | 406294 | 0 | 44.85 | 3DA+9 | 24 | No | 2025-09-29 | 2025-10-06 | 2025-10-01 | 2025-10-20 | 2025-10-15
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Satyam Tiwari | 36/7 | 342752 | 0 | 37.931 | 3DA+3 | 24 | No | 2025-10-09 | 2025-10-11 | 2025-10-01 | 2025-10-25 | 2025-10-20
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Satyam Tiwari | 36/8 | 327992 | 0 | 36.372 | 3DA+0 | 24 | No | 2025-10-14 | 2025-10-16 | 2025-10-01 | 2025-11-01 | 2025-10-27
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Satyam Tiwari | 37/0 | 478941 | 0 | 54.66 | 3DB2+0 | 24 | No | 2025-10-20 | 2025-10-23 | 2025-10-01 | 2025-11-09 | 2025-11-04
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Satyam Tiwari | 39/7 | 391124 | 0 | 43.08 | 3DA+6 | 20 | No |  | WIP | 2025-10-01 | 2025-10-17 | 2025-10-12
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Manikandan | 16/11 | 342752 | 0 | 37.931 | 3DA+3 | 20 | No | 2025-10-07 | 2025-10-08 | 2025-10-01 | 2025-10-27 | 2025-10-22
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Manikandan | 11/4 | 327992 | 0 | 36.372 | 3DA+0 | 20 | No | 2025-10-15 | 2025-10-18 | 2025-10-01 | 2025-10-29 | 2025-10-30
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Manikandan | 11/7 | 327992 | 0 | 36.372 | 3DA+0 | 22 | No | 2025-10-09 | 2025-10-11 | 2025-10-01 | 2025-10-25 | 2025-10-24
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Manikandan | 11/8 | 327992 | 0 | 36.372 | 3DA+0 | 22 | No | 2025-10-18 | 2025-10-21 | 2025-10-01 | 2025-10-30 | 2025-10-29
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Satyam Tiwari | 43/4 | 342752 | 0 | 37.931 | 3DA+3 | 25 | yes |  | Completed | 2025-10-01 | 2025-10-17 | 2025-10-12
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Satyam Tiwari | 43/5 | 406294 | 0 | 44.85 | 3DA+9 | 25 | yes | 2025-09-25 | 2025-10-08 | 2025-10-01 | 2025-10-23 | 2025-10-18
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Satyam Tiwari | 43/3 | 327992 | 0 | 36.372 | 3DA+0 | 25 | yes | 2025-10-03 | 2025-10-14 | 2025-10-01 | 2025-10-28 | 2025-10-23
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Satyam Tiwari | 41/1 | 342752 | 0 | 36.372 | 3DA+3 | 25 | yes | 2025-10-12 | 2025-10-19 | 2025-10-01 | 2025-11-03 | 2025-10-29
ta421 | TA421 | 2025-10-01 | Section Incharge | Mr. Satyam Tiwari | 42/2 | 327992 | 0 | 36.372 | 3DA+0 | 25 | yes | 2025-10-20 | 2025-10-25 | 2025-10-01 | 2025-11-10 | 2025-11-05
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Chandrasekar | 1/0 | 661012 | 0 | 72.63 | 2D60+0 | 33 | No |  | WIP | 2025-10-01 | 2025-10-18 | 2025-10-13
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Chandrasekar | 4/3 | 347642 | 0 | 37.7169 | 2DA+6 | 33 | No | 2025-10-08 | 2025-10-09 | 2025-10-01 | 2025-10-22 | 2025-10-17
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Chandrasekar | 4/1 | 307108 | 0 | 33.38 | 2DA+3 | 33 | No | 2025-10-10 | 2025-10-13 | 2025-10-01 | 2025-10-26 | 2025-10-21
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Chandrasekar | 4/4 | 292211 | 0 | 31.99 | 2DA+0 | 33 | No | 2025-10-15 | 2025-10-17 | 2025-10-01 | 2025-10-30 | 2025-10-25
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Chandrasekar | 4/5 | 307108 | 0 | 33.38 | 2DA+3 | 33 | No | 2025-10-17 | 2025-10-21 | 2025-10-01 | 2025-11-03 | 2025-10-29
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Chandrasekar | 4/8 | 307108 | 0 | 33.38 | 2DA+3 | 33 | No | 2025-10-21 | 2025-10-25 | 2025-10-01 | 2025-11-06 | 2025-11-01
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Chandrasekar | 4/11 | 347642 | 0 | 37.7169 | 2DA+6 | 33 | No | 2025-10-25 | 2025-10-28 | 2025-10-01 | 2025-11-10 | 2025-11-05
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Srinivasan | 4/18 | 292211 | 0 | 31.99 | 2DA+0 | 32 | No |  | Completed | 2025-10-01 | 2025-10-15 | 2025-10-10
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Srinivasan | 9/3 | 362229 | 0 | 39.1682 | 2DA+9 | 32 | No | 2025-10-05 | 2025-10-06 | 2025-10-01 | 2025-10-19 | 2025-10-14
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Srinivasan | 4/19 | 347642 | 0 | 37.7169 | 2DA+6 | 32 | No | 2025-10-07 | 2025-10-10 | 2025-10-01 | 2025-10-24 | 2025-10-19
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Srinivasan | 4/20 | 362229 | 0 | 39.1682 | 2DA+9 | 32 | No | 2025-10-11 | 2025-10-15 | 2025-10-01 | 2025-10-29 | 2025-10-24
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Srinivasan | 4/13 | 292211 | 0 | 31.99 | 2DA+0 | 32 | No | 2025-10-16 | 2025-10-20 | 2025-10-01 | 2025-11-04 | 2025-10-30
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Srinivasan | 4/14 | 307108 | 0 | 33.38 | 2DA+3 | 32 | No | 2025-10-23 | 2025-10-26 | 2025-10-01 | 2025-11-10 | 2025-11-05
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Bhimmahto | 39/2 | 327992 | 0 | 36.372 | 3DA+0 | 24 | No |  | WIP | 2025-10-01 | 2025-10-15 | 2025-10-10
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Bhimmahto | 39/9 | 406294 | 0 | 44.85 | 3DA+9 | 24 | No | 2025-09-29 | 2025-10-06 | 2025-10-01 | 2025-10-20 | 2025-10-15
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Bhimmahto | 36/7 | 342752 | 0 | 37.931 | 3DA+3 | 24 | No | 2025-10-09 | 2025-10-11 | 2025-10-01 | 2025-10-25 | 2025-10-20
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Bhimmahto | 36/8 | 327992 | 0 | 36.372 | 3DA+0 | 24 | No | 2025-10-14 | 2025-10-16 | 2025-10-01 | 2025-11-01 | 2025-10-27
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Bhimmahto | 37/0 | 478941 | 0 | 54.66 | 3DB2+0 | 24 | No | 2025-10-20 | 2025-10-23 | 2025-10-01 | 2025-11-09 | 2025-11-04
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Anand | 39/7 | 391124 | 0 | 43.08 | 3DA+6 | 20 | No |  | WIP | 2025-10-01 | 2025-10-17 | 2025-10-12
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Anand | 16/11 | 342752 | 0 | 37.931 | 3DA+3 | 20 | No | 2025-10-07 | 2025-10-08 | 2025-10-01 | 2025-10-27 | 2025-10-22
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Anand | 11/4 | 327992 | 0 | 36.372 | 3DA+0 | 20 | No | 2025-10-15 | 2025-10-18 | 2025-10-01 | 2025-10-29 | 2025-10-30
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Ram Asish | 11/7 | 327992 | 0 | 36.372 | 3DA+0 | 22 | No | 2025-10-09 | 2025-10-11 | 2025-10-01 | 2025-10-25 | 2025-10-24
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Ram Asish | 11/8 | 327992 | 0 | 36.372 | 3DA+0 | 22 | No | 2025-10-18 | 2025-10-21 | 2025-10-01 | 2025-10-30 | 2025-10-29
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Sudalaimuthu | 43/4 | 342752 | 0 | 37.931 | 3DA+3 | 25 | yes |  | Completed | 2025-10-01 | 2025-10-17 | 2025-10-12
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Sudalaimuthu | 43/5 | 406294 | 0 | 44.85 | 3DA+9 | 25 | yes | 2025-09-25 | 2025-10-08 | 2025-10-01 | 2025-10-23 | 2025-10-18
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Sudalaimuthu | 43/3 | 327992 | 0 | 36.372 | 3DA+0 | 25 | yes | 2025-10-03 | 2025-10-14 | 2025-10-01 | 2025-10-28 | 2025-10-23
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Sudalaimuthu | 41/1 | 342752 | 0 | 36.372 | 3DA+3 | 25 | yes | 2025-10-12 | 2025-10-19 | 2025-10-01 | 2025-11-03 | 2025-10-29
ta421 | TA421 | 2025-10-01 | Supervisor | Mr. Sudalaimuthu | 42/2 | 327992 | 0 | 36.372 | 3DA+0 | 25 | yes | 2025-10-20 | 2025-10-25 | 2025-10-01 | 2025-11-10 | 2025-11-05
tb408 | TB408 | 2025-10-01 | Gang | Sheetal Singh | 6/1 | 331201.1091 | 0 | 37.5044 | DA+0 | 30 | Yes | Yes | 2025-09-25 | 2025-10-01 | 2025-10-05 | 2025-10-04
tb408 | TB408 | 2025-10-01 | Gang | Priyanka Devi (Santosh) | 21/10 | 401042.4503 | 0 | 45.413 | DA+6 | 32 | No | No | 2025-10-07 | 2025-10-01 | 2025-10-14 | 2025-10-13
tb408 | TB408 | 2025-10-01 | Gang | Priyanka Devi (Santosh) | 21/9 | 343063.2086 | 0 | 38.8476 | DA+3 |  | No | No | 2025-10-13 | 2025-10-01 | 2025-10-20 | 2025-10-19
tb408 | TB408 | 2025-10-01 | Gang | Priyanka Devi (Santosh) | 21/7 | 343063.2086 | 0 | 38.8476 | DA+3 |  | No | No | 2025-10-19 | 2025-10-01 | 2025-10-26 | 2025-10-25
tb408 | TB408 | 2025-10-01 | Gang | Priyanka Devi (Santosh) | 22/0 | 530714.6377 | 0 | 60.0968 | DB2+3 |  | No | No | 2025-10-25 | 2025-10-01 | 2025-11-01 | 2025-10-31
tb408 | TB408 | 2025-10-01 | Gang | Jirwa Devi | 30/2 | 331162.5 | 0 | 37.5 | DA+0 | 34 | Yes | Yes | 2025-09-30 | 2025-10-01 | 2025-10-12 | 2025-10-11
tb408 | TB408 | 2025-10-01 | Gang | Jirwa Devi | 35/0 | 599392.212 | 0 | 67.8737 | DB2+6 |  | No | No | 2025-10-07 | 2025-10-01 | 2025-10-14 | 2025-10-13
tb408 | TB408 | 2025-10-01 | Gang | Jirwa Devi | 35/1 | 416684.9949 | 0 | 47.1844 | DA+9 |  | No | No | 2025-10-13 | 2025-10-01 | 2025-10-20 | 2025-10-19
tb408 | TB408 | 2025-10-01 | Gang | Nimal Mahto | 35/2 | 508641.2353 | 0 | 57.5972 | DB1+0 | 29 | No | No | 2025-10-19 | 2025-10-01 | 2025-10-26 | 2025-10-25
tb408 | TB408 | 2025-10-01 | Gang | Nimal Mahto | 35/3 | 599392.212 | 0 | 67.8737 | DB1+6 |  | No | No | 2025-10-25 | 2025-10-01 | 2025-11-01 | 2025-10-31
tb408 | TB408 | 2025-10-01 | Gang | Nimal Mahto | 35/4 | 331201.1091 | 0 | 37.5044 | DA+0 |  | Yes | Yes | 2025-10-07 | 2025-10-01 | 2025-10-19 | 2025-10-18
tb408 | TB408 | 2025-10-01 | Gang | Nimal Mahto | 35/5 | 331201.1091 | 0 | 37.5044 | DA+0 |  | Yes | Yes | 2025-09-27 | 2025-10-01 | 2025-10-08 | 2025-10-07
tb408 | TB408 | 2025-10-01 | Gang | Shobha Devi | 40/0 | 586211.5559 | 0 | 66.3811 | DC2+0 | 32 | Yes | Yes | 2025-09-29 | 2025-10-01 | 2025-10-11 | 2025-10-10
tb408 | TB408 | 2025-10-01 | Gang | Shobha Devi | 40/1 | 401042.4503 | 0 | 45.413 | DA+6 |  | No | No | 2025-10-10 | 2025-10-01 | 2025-10-16 | 2025-10-15
tb408 | TB408 | 2025-10-01 | Gang | Shobha Devi | 41/0 | 689984.1071 | 0 | 78.132 | DC1+6 |  | No | No | 2025-10-15 | 2025-10-01 | 2025-10-21 | 2025-10-20
tb408 | TB408 | 2025-10-01 | Gang | Shobha Devi | 41/2 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-20 | 2025-10-01 | 2025-10-27 | 2025-10-26
tb408 | TB408 | 2025-10-01 | Gang | Shobha Devi | 42/0 | 586211.5559 | 0 | 66.3811 | DC1+0 |  | No | No | 2025-10-26 | 2025-10-01 | 2025-11-02 | 2025-11-01
tb408 | TB408 | 2025-10-01 | Gang | Vivek Ganju | 42/1 | 401042.4503 | 0 | 45.413 | DA+6 | 35 | No | No | 2025-10-07 | 2025-10-01 | 2025-10-13 | 2025-10-12
tb408 | TB408 | 2025-10-01 | Gang | Vivek Ganju | 42/2 | 401042.4503 | 0 | 45.413 | DA+6 |  | No | No | 2025-10-12 | 2025-10-01 | 2025-10-18 | 2025-10-17
tb408 | TB408 | 2025-10-01 | Gang | Vivek Ganju | 42/3 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-17 | 2025-10-01 | 2025-10-23 | 2025-10-22
tb408 | TB408 | 2025-10-01 | Gang | Vivek Ganju | 42/4 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-22 | 2025-10-01 | 2025-10-28 | 2025-10-27
tb408 | TB408 | 2025-10-01 | Gang | Vivek Ganju | 42/5 | 416684.9949 | 0 | 47.1844 | DA+9 |  | No | No | 2025-10-27 | 2025-10-01 | 2025-11-02 | 2025-11-01
tb408 | TB408 | 2025-10-01 | Gang | Vivek Ganju | 42/6 | 331201.1091 | 0 | 37.5044 | DA+0 |  | Yes | Yes | 2025-09-22 | 2025-10-01 | 2025-10-09 | 2025-10-08
tb408 | TB408 | 2025-10-01 | Gang | Chinta Devi | 43/2 | 331201.1091 | 0 | 37.5044 | DA+0 | 31 | No | No | 2025-10-08 | 2025-10-01 | 2025-10-15 | 2025-10-14
tb408 | TB408 | 2025-10-01 | Gang | Chinta Devi | 43/4 | 343063.2086 | 0 | 38.8476 | DA+3 |  | No | No | 2025-10-14 | 2025-10-01 | 2025-10-21 | 2025-10-20
tb408 | TB408 | 2025-10-01 | Gang | Chinta Devi | 44/8 | 786842.1 | 0 | 89.1 | DCT+0 |  | No | No | 2025-10-20 | 2025-10-01 | 2025-10-27 | 2025-10-26
tb408 | TB408 | 2025-10-01 | Gang | Chinta Devi | 46/0 | 1409883.1891 | 0 | 143.6019 | DD60+25 |  | Yes | Yes | 2025-09-29 | 2025-10-01 | 2025-10-11 | 2025-10-10
tb408 | TB408 | 2025-10-01 | Gang | Sunny Construction | 55/0 | 599392.212 | 0 | 67.8737 | DB1+6 | 37 | Yes | Yes | 2025-09-30 | 2025-10-01 | 2025-10-12 | 2025-10-11
tb408 | TB408 | 2025-10-01 | Gang | Sunny Construction | 55/2 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-11 | 2025-10-01 | 2025-10-23 | 2025-10-22
tb408 | TB408 | 2025-10-01 | Section Incharge | Sumit Singh | 6/1 | 331201.1091 | 0 | 37.5044 | DA+0 | 30 | Yes | Yes | 2025-09-25 | 2025-10-01 | 2025-10-05 | 2025-10-04
tb408 | TB408 | 2025-10-01 | Section Incharge | Vijay Yadav | 21/10 | 401042.4503 | 0 | 45.413 | DA+6 | 32 | No | No | 2025-10-07 | 2025-10-01 | 2025-10-14 | 2025-10-13
tb408 | TB408 | 2025-10-01 | Section Incharge | Vijay Yadav | 21/9 | 343063.2086 | 0 | 38.8476 | DA+3 |  | No | No | 2025-10-13 | 2025-10-01 | 2025-10-20 | 2025-10-19
tb408 | TB408 | 2025-10-01 | Section Incharge | Vijay Yadav | 21/7 | 343063.2086 | 0 | 38.8476 | DA+3 |  | No | No | 2025-10-19 | 2025-10-01 | 2025-10-26 | 2025-10-25
tb408 | TB408 | 2025-10-01 | Section Incharge | Vijay Yadav | 22/0 | 530714.6377 | 0 | 60.0968 | DB2+3 |  | No | No | 2025-10-25 | 2025-10-01 | 2025-11-01 | 2025-10-31
tb408 | TB408 | 2025-10-01 | Section Incharge | Vijay Yadav | 30/2 | 331162.5 | 0 | 37.5 | DA+0 | 34 | Yes | Yes | 2025-09-30 | 2025-10-01 | 2025-10-12 | 2025-10-11
tb408 | TB408 | 2025-10-01 | Section Incharge | Ram Tirath Singh | 35/0 | 599392.212 | 0 | 67.8737 | DB2+6 |  | No | No | 2025-10-07 | 2025-10-01 | 2025-10-14 | 2025-10-13
tb408 | TB408 | 2025-10-01 | Section Incharge | Ram Tirath Singh | 35/1 | 416684.9949 | 0 | 47.1844 | DA+9 |  | No | No | 2025-10-13 | 2025-10-01 | 2025-10-20 | 2025-10-19
tb408 | TB408 | 2025-10-01 | Section Incharge | Ram Tirath Singh | 35/2 | 508641.2353 | 0 | 57.5972 | DB1+0 | 29 | No | No | 2025-10-19 | 2025-10-01 | 2025-10-26 | 2025-10-25
tb408 | TB408 | 2025-10-01 | Section Incharge | Ram Tirath Singh | 35/3 | 599392.212 | 0 | 67.8737 | DB1+6 |  | No | No | 2025-10-25 | 2025-10-01 | 2025-11-01 | 2025-10-31
tb408 | TB408 | 2025-10-01 | Section Incharge | Ram Tirath Singh | 35/4 | 331201.1091 | 0 | 37.5044 | DA+0 |  | Yes | Yes | 2025-10-07 | 2025-10-01 | 2025-10-19 | 2025-10-18
tb408 | TB408 | 2025-10-01 | Section Incharge | Ram Tirath Singh | 35/5 | 331201.1091 | 0 | 37.5044 | DA+0 |  | Yes | Yes | 2025-09-27 | 2025-10-01 | 2025-10-08 | 2025-10-07
tb408 | TB408 | 2025-10-01 | Section Incharge | Ram Tirath Singh | 40/0 | 586211.5559 | 0 | 66.3811 | DC2+0 | 32 | Yes | Yes | 2025-09-29 | 2025-10-01 | 2025-10-11 | 2025-10-10
tb408 | TB408 | 2025-10-01 | Section Incharge | Ram Tirath Singh | 40/1 | 401042.4503 | 0 | 45.413 | DA+6 |  | No | No | 2025-10-10 | 2025-10-01 | 2025-10-16 | 2025-10-15
tb408 | TB408 | 2025-10-01 | Section Incharge | Ram Tirath Singh | 41/0 | 689984.1071 | 0 | 78.132 | DC1+6 |  | No | No | 2025-10-15 | 2025-10-01 | 2025-10-21 | 2025-10-20
tb408 | TB408 | 2025-10-01 | Section Incharge | Ram Tirath Singh | 41/2 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-20 | 2025-10-01 | 2025-10-27 | 2025-10-26
tb408 | TB408 | 2025-10-01 | Section Incharge | Ram Tirath Singh | 42/0 | 586211.5559 | 0 | 66.3811 | DC1+0 |  | No | No | 2025-10-26 | 2025-10-01 | 2025-11-02 | 2025-11-01
tb408 | TB408 | 2025-10-01 | Section Incharge | Ram Tirath Singh | 42/1 | 401042.4503 | 0 | 45.413 | DA+6 | 35 | No | No | 2025-10-07 | 2025-10-01 | 2025-10-13 | 2025-10-12
tb408 | TB408 | 2025-10-01 | Section Incharge | Ram Tirath Singh | 42/2 | 401042.4503 | 0 | 45.413 | DA+6 |  | No | No | 2025-10-12 | 2025-10-01 | 2025-10-18 | 2025-10-17
tb408 | TB408 | 2025-10-01 | Section Incharge | Ram Tirath Singh | 42/3 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-17 | 2025-10-01 | 2025-10-23 | 2025-10-22
tb408 | TB408 | 2025-10-01 | Section Incharge | Ram Tirath Singh | 42/4 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-22 | 2025-10-01 | 2025-10-28 | 2025-10-27
tb408 | TB408 | 2025-10-01 | Section Incharge | Ram Tirath Singh | 42/5 | 416684.9949 | 0 | 47.1844 | DA+9 |  | No | No | 2025-10-27 | 2025-10-01 | 2025-11-02 | 2025-11-01
tb408 | TB408 | 2025-10-01 | Section Incharge | Ram Tirath Singh | 42/6 | 331201.1091 | 0 | 37.5044 | DA+0 |  | Yes | Yes | 2025-09-22 | 2025-10-01 | 2025-10-09 | 2025-10-08
tb408 | TB408 | 2025-10-01 | Section Incharge | Ram Tirath Singh | 43/2 | 331201.1091 | 0 | 37.5044 | DA+0 | 31 | No | No | 2025-10-08 | 2025-10-01 | 2025-10-15 | 2025-10-14
tb408 | TB408 | 2025-10-01 | Section Incharge | Ram Tirath Singh | 43/4 | 343063.2086 | 0 | 38.8476 | DA+3 |  | No | No | 2025-10-14 | 2025-10-01 | 2025-10-21 | 2025-10-20
tb408 | TB408 | 2025-10-01 | Section Incharge | Ram Tirath Singh | 44/8 | 786842.1 | 0 | 89.1 | DCT+0 |  | No | No | 2025-10-20 | 2025-10-01 | 2025-10-27 | 2025-10-26
tb408 | TB408 | 2025-10-01 | Section Incharge | Ram Tirath Singh | 46/0 | 1409883.1891 | 0 | 143.6019 | DD60+25 |  | Yes | Yes | 2025-09-29 | 2025-10-01 | 2025-10-11 | 2025-10-10
tb408 | TB408 | 2025-10-01 | Section Incharge | Ram Tirath Singh | 55/0 | 599392.212 | 0 | 67.8737 | DB1+6 | 37 | Yes | Yes | 2025-09-30 | 2025-10-01 | 2025-10-12 | 2025-10-11
tb408 | TB408 | 2025-10-01 | Section Incharge | Ram Tirath Singh | 55/2 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-11 | 2025-10-01 | 2025-10-23 | 2025-10-22
tb408 | TB408 | 2025-10-01 | Supervisor | Vaibhav Sharma | 6/1 | 331201.1091 | 0 | 37.5044 | DA+0 | 30 | Yes | Yes | 2025-09-25 | 2025-10-01 | 2025-10-05 | 2025-10-04
tb408 | TB408 | 2025-10-01 | Supervisor | Gangadin Sahu | 21/10 | 401042.4503 | 0 | 45.413 | DA+6 | 32 | No | No | 2025-10-07 | 2025-10-01 | 2025-10-14 | 2025-10-13
tb408 | TB408 | 2025-10-01 | Supervisor | Gangadin Sahu | 21/9 | 343063.2086 | 0 | 38.8476 | DA+3 |  | No | No | 2025-10-13 | 2025-10-01 | 2025-10-20 | 2025-10-19
tb408 | TB408 | 2025-10-01 | Supervisor | Gangadin Sahu | 21/7 | 343063.2086 | 0 | 38.8476 | DA+3 |  | No | No | 2025-10-19 | 2025-10-01 | 2025-10-26 | 2025-10-25
tb408 | TB408 | 2025-10-01 | Supervisor | Gangadin Sahu | 22/0 | 530714.6377 | 0 | 60.0968 | DB2+3 |  | No | No | 2025-10-25 | 2025-10-01 | 2025-11-01 | 2025-10-31
tb408 | TB408 | 2025-10-01 | Supervisor | Gangadin Sahu | 30/2 | 331162.5 | 0 | 37.5 | DA+0 | 34 | Yes | Yes | 2025-09-30 | 2025-10-01 | 2025-10-12 | 2025-10-11
tb408 | TB408 | 2025-10-01 | Supervisor | Ganesh Singh | 35/0 | 599392.212 | 0 | 67.8737 | DB2+6 |  | No | No | 2025-10-07 | 2025-10-01 | 2025-10-14 | 2025-10-13
tb408 | TB408 | 2025-10-01 | Supervisor | Ganesh Singh | 35/1 | 416684.9949 | 0 | 47.1844 | DA+9 |  | No | No | 2025-10-13 | 2025-10-01 | 2025-10-20 | 2025-10-19
tb408 | TB408 | 2025-10-01 | Supervisor | Ganesh Singh | 35/2 | 508641.2353 | 0 | 57.5972 | DB1+0 | 29 | No | No | 2025-10-19 | 2025-10-01 | 2025-10-26 | 2025-10-25
tb408 | TB408 | 2025-10-01 | Supervisor | Ganesh Singh | 35/3 | 599392.212 | 0 | 67.8737 | DB1+6 |  | No | No | 2025-10-25 | 2025-10-01 | 2025-11-01 | 2025-10-31
tb408 | TB408 | 2025-10-01 | Supervisor | Ganesh Singh | 35/4 | 331201.1091 | 0 | 37.5044 | DA+0 |  | Yes | Yes | 2025-10-07 | 2025-10-01 | 2025-10-19 | 2025-10-18
tb408 | TB408 | 2025-10-01 | Supervisor | Ganesh Singh | 35/5 | 331201.1091 | 0 | 37.5044 | DA+0 |  | Yes | Yes | 2025-09-27 | 2025-10-01 | 2025-10-08 | 2025-10-07
tb408 | TB408 | 2025-10-01 | Supervisor | Umesh Prasad | 40/0 | 586211.5559 | 0 | 66.3811 | DC2+0 | 32 | Yes | Yes | 2025-09-29 | 2025-10-01 | 2025-10-11 | 2025-10-10
tb408 | TB408 | 2025-10-01 | Supervisor | Umesh Prasad | 40/1 | 401042.4503 | 0 | 45.413 | DA+6 |  | No | No | 2025-10-10 | 2025-10-01 | 2025-10-16 | 2025-10-15
tb408 | TB408 | 2025-10-01 | Supervisor | Umesh Prasad | 41/0 | 689984.1071 | 0 | 78.132 | DC1+6 |  | No | No | 2025-10-15 | 2025-10-01 | 2025-10-21 | 2025-10-20
tb408 | TB408 | 2025-10-01 | Supervisor | Umesh Prasad | 41/2 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-20 | 2025-10-01 | 2025-10-27 | 2025-10-26
tb408 | TB408 | 2025-10-01 | Supervisor | Umesh Prasad | 42/0 | 586211.5559 | 0 | 66.3811 | DC1+0 |  | No | No | 2025-10-26 | 2025-10-01 | 2025-11-02 | 2025-11-01
tb408 | TB408 | 2025-10-01 | Supervisor | Pramod Kumar Sahoo | 42/1 | 401042.4503 | 0 | 45.413 | DA+6 | 35 | No | No | 2025-10-07 | 2025-10-01 | 2025-10-13 | 2025-10-12
tb408 | TB408 | 2025-10-01 | Supervisor | Pramod Kumar Sahoo | 42/2 | 401042.4503 | 0 | 45.413 | DA+6 |  | No | No | 2025-10-12 | 2025-10-01 | 2025-10-18 | 2025-10-17
tb408 | TB408 | 2025-10-01 | Supervisor | Pramod Kumar Sahoo | 42/3 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-17 | 2025-10-01 | 2025-10-23 | 2025-10-22
tb408 | TB408 | 2025-10-01 | Supervisor | Pramod Kumar Sahoo | 42/4 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-22 | 2025-10-01 | 2025-10-28 | 2025-10-27
tb408 | TB408 | 2025-10-01 | Supervisor | Pramod Kumar Sahoo | 42/5 | 416684.9949 | 0 | 47.1844 | DA+9 |  | No | No | 2025-10-27 | 2025-10-01 | 2025-11-02 | 2025-11-01
tb408 | TB408 | 2025-10-01 | Supervisor | Pramod Kumar Sahoo | 42/6 | 331201.1091 | 0 | 37.5044 | DA+0 |  | Yes | Yes | 2025-09-22 | 2025-10-01 | 2025-10-09 | 2025-10-08
tb408 | TB408 | 2025-10-01 | Supervisor | Shakib Hussain | 43/2 | 331201.1091 | 0 | 37.5044 | DA+0 | 31 | No | No | 2025-10-08 | 2025-10-01 | 2025-10-15 | 2025-10-14
tb408 | TB408 | 2025-10-01 | Supervisor | Shakib Hussain | 43/4 | 343063.2086 | 0 | 38.8476 | DA+3 |  | No | No | 2025-10-14 | 2025-10-01 | 2025-10-21 | 2025-10-20
tb408 | TB408 | 2025-10-01 | Supervisor | Shakib Hussain | 44/8 | 786842.1 | 0 | 89.1 | DCT+0 |  | No | No | 2025-10-20 | 2025-10-01 | 2025-10-27 | 2025-10-26
tb408 | TB408 | 2025-10-01 | Supervisor | Shakib Hussain | 46/0 | 1409883.1891 | 0 | 143.6019 | DD60+25 |  | Yes | Yes | 2025-09-29 | 2025-10-01 | 2025-10-11 | 2025-10-10
tb408 | TB408 | 2025-10-01 | Supervisor | Shakib Hussain | 55/0 | 599392.212 | 0 | 67.8737 | DB1+6 | 37 | Yes | Yes | 2025-09-30 | 2025-10-01 | 2025-10-12 | 2025-10-11
tb408 | TB408 | 2025-10-01 | Supervisor | Shakib Hussain | 55/2 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-11 | 2025-10-01 | 2025-10-23 | 2025-10-22
ta505 | TA505 | 2025-10-01 | Gang | Jwala Singh | 110/0 | 773950.3 | 0 | 70.745 | DC2+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-09 | 2025-10-11
ta505 | TA505 | 2025-10-01 | Gang | Jwala Singh | 126/1 | 499925.18 | 0 | 45.697 | DA+9 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-01 | 2025-10-16 | 2025-10-18
ta505 | TA505 | 2025-10-01 | Gang | Jwala Singh | 109/0 | 683137.36 | 0 | 62.444 | DC1+0 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-01 | 2025-10-23 | 2025-10-24
ta505 | TA505 | 2025-10-01 | Gang | Jwala Singh | 101/0 | 720650.62 | 0 | 65.873 | DC1+3 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-01 | 2025-10-30 | 2025-10-31
ta505 | TA505 | 2025-10-01 | Gang | New Gang-1 | 116/0 | 843222.38 | 0 | 77.077 | DD45+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-11 | 2025-10-13
ta505 | TA505 | 2025-10-01 | Gang | New Gang-1 | 102/0 | 773950.3 | 0 | 70.745 | DC2+3 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-01 | 2025-10-20 | 2025-10-22
ta505 | TA505 | 2025-10-01 | Gang | New Gang-1 | 118/0 | 1063017.92 | 0 | 97.168 | DD60+6 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-01 | 2025-10-29 | 2025-10-30
ta505 | TA505 | 2025-10-01 | Gang | New Gang-2 | 103/4 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-11 | 2025-10-13
ta505 | TA505 | 2025-10-01 | Gang | New Gang-2 | 114/4 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-01 | 2025-10-20 | 2025-10-22
ta505 | TA505 | 2025-10-01 | Gang | New Gang-2 | 121/0 | 711406.32 | 0 | 65.028 | DB1+6 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-01 | 2025-10-29 | 2025-10-30
ta505 | TA505 | 2025-10-01 | Gang | Shila Devi | 126/3 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-08 | 2025-10-10
ta505 | TA505 | 2025-10-01 | Gang | Shila Devi | 141/0 | 801300.3 | 0 | 73.245 | DD45+0 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-01 | 2025-10-14 | 2025-10-16
ta505 | TA505 | 2025-10-01 | Gang | Shila Devi | 130/2 | 389485.88 | 0 | 35.602 | DA-1.5 |  |  | 2025-10-13 | 2025-10-14 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta505 | TA505 | 2025-10-01 | Gang | Shila Devi | 128/0 | 895209.26 | 0 | 81.829 | DC2+9 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-01 | 2025-10-30 | 2025-10-31
ta505 | TA505 | 2025-10-01 | Gang | Jyoti Enterprises | 129A/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-07 | 2025-10-09
ta505 | TA505 | 2025-10-01 | Gang | Jyoti Enterprises | 132/0 | 1063017.92 | 0 | 97.168 | DD60+6 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-01 | 2025-10-17 | 2025-10-19
ta505 | TA505 | 2025-10-01 | Gang | Jyoti Enterprises | 112/0 | 1366953 | 0 | 124.95 | DD60+18 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-01 | 2025-10-30 | 2025-10-31
ta505 | TA505 | 2025-10-01 | Gang | Deglal Mahto | 115/0 | 952009.74 | 0 | 87.021 | DD60+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-09 | 2025-10-11
ta505 | TA505 | 2025-10-01 | Gang | Deglal Mahto | 114/0 | 735846.28 | 0 | 67.262 | DC2+0 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-01 | 2025-10-18 | 2025-10-20
ta505 | TA505 | 2025-10-01 | Gang | Deglal Mahto | 136/2 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-17 | 2025-10-18 | 2025-10-01 | 2025-10-24 | 2025-10-25
ta505 | TA505 | 2025-10-01 | Gang | Deglal Mahto | 136/5 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-23 | 2025-10-24 | 2025-10-01 | 2025-10-30 | 2025-10-31
ta505 | TA505 | 2025-10-01 | Gang | Anil Kumar | 156/0 | 683137.36 | 0 | 62.444 | DC1+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-13 | 2025-10-15
ta505 | TA505 | 2025-10-01 | Gang | Anil Kumar | 140/0 | 823552.26 | 0 | 75.279 | DC1+9 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-01 | 2025-10-24 | 2025-10-26
ta505 | TA505 | 2025-10-01 | Gang | Anil Kumar | 140/1 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-23 | 2025-10-24 | 2025-10-01 | 2025-10-30 | 2025-10-31
ta505 | TA505 | 2025-10-01 | Gang | Toshan Mahto | 135/1 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-08 | 2025-10-10
ta505 | TA505 | 2025-10-01 | Gang | Toshan Mahto | 135/3 | 499925.18 | 0 | 45.697 | DA+9 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-01 | 2025-10-14 | 2025-10-16
ta505 | TA505 | 2025-10-01 | Gang | Toshan Mahto | 142/0 | 843222.38 | 0 | 77.077 | DD45+3 |  |  | 2025-10-13 | 2025-10-14 | 2025-10-01 | 2025-10-20 | 2025-10-21
ta505 | TA505 | 2025-10-01 | Gang | Toshan Mahto | 148/1 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-01 | 2025-10-26 | 2025-10-27
ta505 | TA505 | 2025-10-01 | Gang | Toshan Mahto | 148A/0 | 606633.94 | 0 | 55.451 | DB1+0 |  |  | 2025-10-25 | 2025-10-26 | 2025-10-01 | 2025-11-01 | 2025-11-02
ta505 | TA505 | 2025-10-01 | Gang | Parmanand (MP) | 158/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-07 | 2025-10-09
ta505 | TA505 | 2025-10-01 | Gang | Parmanand (MP) | 160/2 | 389485.88 | 0 | 35.602 | DA-1.5 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-01 | 2025-10-16 | 2025-10-18
ta505 | TA505 | 2025-10-01 | Gang | Parmanand (MP) | 159/3 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta505 | TA505 | 2025-10-01 | Gang | Parmanand (MP) | 160/1 | 389485.88 | 0 | 35.602 | DA-1.5 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-01 | 2025-10-30 | 2025-10-31
ta505 | TA505 | 2025-10-01 | Gang | Jagannath Mahto | 160/0 | 606633.94 | 0 | 55.451 | DB1+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-09 | 2025-10-11
ta505 | TA505 | 2025-10-01 | Gang | Jagannath Mahto | 161/0 | 679549.04 | 0 | 62.116 | DB2+3 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-01 | 2025-10-16 | 2025-10-18
ta505 | TA505 | 2025-10-01 | Gang | Jagannath Mahto | 161/1 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta505 | TA505 | 2025-10-01 | Gang | Jagannath Mahto | 164/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-01 | 2025-10-26 | 2025-10-27
ta505 | TA505 | 2025-10-01 | Gang | Jagannath Mahto | 164/3 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-25 | 2025-10-26 | 2025-10-01 | 2025-10-31 | 2025-11-01
ta505 | TA505 | 2025-10-01 | Gang | Pankaj Singh | 167/4 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-07 | 2025-10-09
ta505 | TA505 | 2025-10-01 | Gang | Pankaj Singh | 164/6 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-01 | 2025-10-12 | 2025-10-14
ta505 | TA505 | 2025-10-01 | Gang | Pankaj Singh | 164/7 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-11 | 2025-10-12 | 2025-10-01 | 2025-10-17 | 2025-10-18
ta505 | TA505 | 2025-10-01 | Gang | Pankaj Singh | 164/5 | 479215.76 | 0 | 43.804 | DA+6 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-01 | 2025-10-22 | 2025-10-23
ta505 | TA505 | 2025-10-01 | Gang | Pankaj Singh | 167/3 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-21 | 2025-10-22 | 2025-10-01 | 2025-10-27 | 2025-10-28
ta505 | TA505 | 2025-10-01 | Gang | Deglal Mahto (MP) | 167/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-07 | 2025-10-09
ta505 | TA505 | 2025-10-01 | Gang | Deglal Mahto (MP) | 167/1 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-01 | 2025-10-12 | 2025-10-14
ta505 | TA505 | 2025-10-01 | Gang | Deglal Mahto (MP) | 169/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-11 | 2025-10-12 | 2025-10-01 | 2025-10-17 | 2025-10-18
ta505 | TA505 | 2025-10-01 | Gang | Deglal Mahto (MP) | 169/4 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-01 | 2025-10-22 | 2025-10-23
ta505 | TA505 | 2025-10-01 | Gang | Deglal Mahto (MP) | 169/5 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-21 | 2025-10-22 | 2025-10-01 | 2025-10-27 | 2025-10-28
ta505 | TA505 | 2025-10-01 | Section Incharge | Deepak Anand | 110/0 | 773950.3 | 0 | 70.745 | DC2+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-09 | 2025-10-11
ta505 | TA505 | 2025-10-01 | Section Incharge | Deepak Anand | 126/1 | 499925.18 | 0 | 45.697 | DA+9 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-01 | 2025-10-16 | 2025-10-18
ta505 | TA505 | 2025-10-01 | Section Incharge | Deepak Anand | 109/0 | 683137.36 | 0 | 62.444 | DC1+0 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-01 | 2025-10-23 | 2025-10-24
ta505 | TA505 | 2025-10-01 | Section Incharge | Deepak Anand | 101/0 | 720650.62 | 0 | 65.873 | DC1+3 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-01 | 2025-10-30 | 2025-10-31
ta505 | TA505 | 2025-10-01 | Section Incharge | Deepak Anand | 116/0 | 843222.38 | 0 | 77.077 | DD45+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-11 | 2025-10-13
ta505 | TA505 | 2025-10-01 | Section Incharge | Deepak Anand | 102/0 | 773950.3 | 0 | 70.745 | DC2+3 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-01 | 2025-10-20 | 2025-10-22
ta505 | TA505 | 2025-10-01 | Section Incharge | Deepak Anand | 118/0 | 1063017.92 | 0 | 97.168 | DD60+6 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-01 | 2025-10-29 | 2025-10-30
ta505 | TA505 | 2025-10-01 | Section Incharge | Deepak Anand | 103/4 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-11 | 2025-10-13
ta505 | TA505 | 2025-10-01 | Section Incharge | Deepak Anand | 114/4 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-01 | 2025-10-20 | 2025-10-22
ta505 | TA505 | 2025-10-01 | Section Incharge | Deepak Anand | 121/0 | 711406.32 | 0 | 65.028 | DB1+6 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-01 | 2025-10-29 | 2025-10-30
ta505 | TA505 | 2025-10-01 | Section Incharge | Deepak Anand | 126/3 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-08 | 2025-10-10
ta505 | TA505 | 2025-10-01 | Section Incharge | Deepak Anand | 141/0 | 801300.3 | 0 | 73.245 | DD45+0 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-01 | 2025-10-14 | 2025-10-16
ta505 | TA505 | 2025-10-01 | Section Incharge | Deepak Anand | 130/2 | 389485.88 | 0 | 35.602 | DA-1.5 |  |  | 2025-10-13 | 2025-10-14 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta505 | TA505 | 2025-10-01 | Section Incharge | Deepak Anand | 128/0 | 895209.26 | 0 | 81.829 | DC2+9 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-01 | 2025-10-30 | 2025-10-31
ta505 | TA505 | 2025-10-01 | Section Incharge | Deepak Anand | 129A/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-07 | 2025-10-09
ta505 | TA505 | 2025-10-01 | Section Incharge | Deepak Anand | 132/0 | 1063017.92 | 0 | 97.168 | DD60+6 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-01 | 2025-10-17 | 2025-10-19
ta505 | TA505 | 2025-10-01 | Section Incharge | Deepak Anand | 112/0 | 1366953 | 0 | 124.95 | DD60+18 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-01 | 2025-10-30 | 2025-10-31
ta505 | TA505 | 2025-10-01 | Section Incharge | Deepak Anand | 115/0 | 952009.74 | 0 | 87.021 | DD60+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-09 | 2025-10-11
ta505 | TA505 | 2025-10-01 | Section Incharge | Deepak Anand | 114/0 | 735846.28 | 0 | 67.262 | DC2+0 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-01 | 2025-10-18 | 2025-10-20
ta505 | TA505 | 2025-10-01 | Section Incharge | Deepak Anand | 136/2 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-17 | 2025-10-18 | 2025-10-01 | 2025-10-24 | 2025-10-25
ta505 | TA505 | 2025-10-01 | Section Incharge | Deepak Anand | 136/5 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-23 | 2025-10-24 | 2025-10-01 | 2025-10-30 | 2025-10-31
ta505 | TA505 | 2025-10-01 | Section Incharge | Deepak Anand | 156/0 | 683137.36 | 0 | 62.444 | DC1+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-13 | 2025-10-15
ta505 | TA505 | 2025-10-01 | Section Incharge | Bapan Mandal | 140/0 | 823552.26 | 0 | 75.279 | DC1+9 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-01 | 2025-10-24 | 2025-10-26
ta505 | TA505 | 2025-10-01 | Section Incharge | Bapan Mandal | 140/1 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-23 | 2025-10-24 | 2025-10-01 | 2025-10-30 | 2025-10-31
ta505 | TA505 | 2025-10-01 | Section Incharge | Bapan Mandal | 135/1 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-08 | 2025-10-10
ta505 | TA505 | 2025-10-01 | Section Incharge | Bapan Mandal | 135/3 | 499925.18 | 0 | 45.697 | DA+9 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-01 | 2025-10-14 | 2025-10-16
ta505 | TA505 | 2025-10-01 | Section Incharge | Bapan Mandal | 142/0 | 843222.38 | 0 | 77.077 | DD45+3 |  |  | 2025-10-13 | 2025-10-14 | 2025-10-01 | 2025-10-20 | 2025-10-21
ta505 | TA505 | 2025-10-01 | Section Incharge | Bapan Mandal | 148/1 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-01 | 2025-10-26 | 2025-10-27
ta505 | TA505 | 2025-10-01 | Section Incharge | Bapan Mandal | 148A/0 | 606633.94 | 0 | 55.451 | DB1+0 |  |  | 2025-10-25 | 2025-10-26 | 2025-10-01 | 2025-11-01 | 2025-11-02
ta505 | TA505 | 2025-10-01 | Section Incharge | Vinod Hankare | 158/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-07 | 2025-10-09
ta505 | TA505 | 2025-10-01 | Section Incharge | Vinod Hankare | 160/2 | 389485.88 | 0 | 35.602 | DA-1.5 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-01 | 2025-10-16 | 2025-10-18
ta505 | TA505 | 2025-10-01 | Section Incharge | Vinod Hankare | 159/3 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta505 | TA505 | 2025-10-01 | Section Incharge | Vinod Hankare | 160/1 | 389485.88 | 0 | 35.602 | DA-1.5 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-01 | 2025-10-30 | 2025-10-31
ta505 | TA505 | 2025-10-01 | Section Incharge | Vinod Hankare | 160/0 | 606633.94 | 0 | 55.451 | DB1+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-09 | 2025-10-11
ta505 | TA505 | 2025-10-01 | Section Incharge | Vinod Hankare | 161/0 | 679549.04 | 0 | 62.116 | DB2+3 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-01 | 2025-10-16 | 2025-10-18
ta505 | TA505 | 2025-10-01 | Section Incharge | Vinod Hankare | 161/1 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta505 | TA505 | 2025-10-01 | Section Incharge | Vinod Hankare | 164/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-01 | 2025-10-26 | 2025-10-27
ta505 | TA505 | 2025-10-01 | Section Incharge | Vinod Hankare | 164/3 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-25 | 2025-10-26 | 2025-10-01 | 2025-10-31 | 2025-11-01
ta505 | TA505 | 2025-10-01 | Section Incharge | Vinod Hankare | 167/4 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-07 | 2025-10-09
ta505 | TA505 | 2025-10-01 | Section Incharge | Vinod Hankare | 164/6 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-01 | 2025-10-12 | 2025-10-14
ta505 | TA505 | 2025-10-01 | Section Incharge | Vinod Hankare | 164/7 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-11 | 2025-10-12 | 2025-10-01 | 2025-10-17 | 2025-10-18
ta505 | TA505 | 2025-10-01 | Section Incharge | Vinod Hankare | 164/5 | 479215.76 | 0 | 43.804 | DA+6 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-01 | 2025-10-22 | 2025-10-23
ta505 | TA505 | 2025-10-01 | Section Incharge | Vinod Hankare | 167/3 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-21 | 2025-10-22 | 2025-10-01 | 2025-10-27 | 2025-10-28
ta505 | TA505 | 2025-10-01 | Section Incharge | Vinod Hankare | 167/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-07 | 2025-10-09
ta505 | TA505 | 2025-10-01 | Section Incharge | Vinod Hankare | 167/1 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-01 | 2025-10-12 | 2025-10-14
ta505 | TA505 | 2025-10-01 | Section Incharge | Vinod Hankare | 169/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-11 | 2025-10-12 | 2025-10-01 | 2025-10-17 | 2025-10-18
ta505 | TA505 | 2025-10-01 | Section Incharge | Vinod Hankare | 169/4 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-01 | 2025-10-22 | 2025-10-23
ta505 | TA505 | 2025-10-01 | Section Incharge | Vinod Hankare | 169/5 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-21 | 2025-10-22 | 2025-10-01 | 2025-10-27 | 2025-10-28
ta505 | TA505 | 2025-10-01 | Supervisor | None | 110/0 | 773950.3 | 0 | 70.745 | DC2+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-09 | 2025-10-11
ta505 | TA505 | 2025-10-01 | Supervisor | None | 126/1 | 499925.18 | 0 | 45.697 | DA+9 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-01 | 2025-10-16 | 2025-10-18
ta505 | TA505 | 2025-10-01 | Supervisor | None | 109/0 | 683137.36 | 0 | 62.444 | DC1+0 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-01 | 2025-10-23 | 2025-10-24
ta505 | TA505 | 2025-10-01 | Supervisor | None | 101/0 | 720650.62 | 0 | 65.873 | DC1+3 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-01 | 2025-10-30 | 2025-10-31
ta505 | TA505 | 2025-10-01 | Supervisor | None | 116/0 | 843222.38 | 0 | 77.077 | DD45+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-11 | 2025-10-13
ta505 | TA505 | 2025-10-01 | Supervisor | None | 102/0 | 773950.3 | 0 | 70.745 | DC2+3 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-01 | 2025-10-20 | 2025-10-22
ta505 | TA505 | 2025-10-01 | Supervisor | None | 118/0 | 1063017.92 | 0 | 97.168 | DD60+6 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-01 | 2025-10-29 | 2025-10-30
ta505 | TA505 | 2025-10-01 | Supervisor | None | 103/4 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-11 | 2025-10-13
ta505 | TA505 | 2025-10-01 | Supervisor | None | 114/4 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-01 | 2025-10-20 | 2025-10-22
ta505 | TA505 | 2025-10-01 | Supervisor | None | 121/0 | 711406.32 | 0 | 65.028 | DB1+6 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-01 | 2025-10-29 | 2025-10-30
ta505 | TA505 | 2025-10-01 | Supervisor | None | 126/3 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-08 | 2025-10-10
ta505 | TA505 | 2025-10-01 | Supervisor | None | 141/0 | 801300.3 | 0 | 73.245 | DD45+0 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-01 | 2025-10-14 | 2025-10-16
ta505 | TA505 | 2025-10-01 | Supervisor | None | 130/2 | 389485.88 | 0 | 35.602 | DA-1.5 |  |  | 2025-10-13 | 2025-10-14 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta505 | TA505 | 2025-10-01 | Supervisor | None | 128/0 | 895209.26 | 0 | 81.829 | DC2+9 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-01 | 2025-10-30 | 2025-10-31
ta505 | TA505 | 2025-10-01 | Supervisor | None | 129A/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-07 | 2025-10-09
ta505 | TA505 | 2025-10-01 | Supervisor | None | 132/0 | 1063017.92 | 0 | 97.168 | DD60+6 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-01 | 2025-10-17 | 2025-10-19
ta505 | TA505 | 2025-10-01 | Supervisor | None | 112/0 | 1366953 | 0 | 124.95 | DD60+18 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-01 | 2025-10-30 | 2025-10-31
ta505 | TA505 | 2025-10-01 | Supervisor | None | 115/0 | 952009.74 | 0 | 87.021 | DD60+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-09 | 2025-10-11
ta505 | TA505 | 2025-10-01 | Supervisor | None | 114/0 | 735846.28 | 0 | 67.262 | DC2+0 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-01 | 2025-10-18 | 2025-10-20
ta505 | TA505 | 2025-10-01 | Supervisor | None | 136/2 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-17 | 2025-10-18 | 2025-10-01 | 2025-10-24 | 2025-10-25
ta505 | TA505 | 2025-10-01 | Supervisor | None | 136/5 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-23 | 2025-10-24 | 2025-10-01 | 2025-10-30 | 2025-10-31
ta505 | TA505 | 2025-10-01 | Supervisor | None | 156/0 | 683137.36 | 0 | 62.444 | DC1+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-13 | 2025-10-15
ta505 | TA505 | 2025-10-01 | Supervisor | None | 140/0 | 823552.26 | 0 | 75.279 | DC1+9 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-01 | 2025-10-24 | 2025-10-26
ta505 | TA505 | 2025-10-01 | Supervisor | None | 140/1 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-23 | 2025-10-24 | 2025-10-01 | 2025-10-30 | 2025-10-31
ta505 | TA505 | 2025-10-01 | Supervisor | None | 135/1 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-08 | 2025-10-10
ta505 | TA505 | 2025-10-01 | Supervisor | None | 135/3 | 499925.18 | 0 | 45.697 | DA+9 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-01 | 2025-10-14 | 2025-10-16
ta505 | TA505 | 2025-10-01 | Supervisor | None | 142/0 | 843222.38 | 0 | 77.077 | DD45+3 |  |  | 2025-10-13 | 2025-10-14 | 2025-10-01 | 2025-10-20 | 2025-10-21
ta505 | TA505 | 2025-10-01 | Supervisor | None | 148/1 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-01 | 2025-10-26 | 2025-10-27
ta505 | TA505 | 2025-10-01 | Supervisor | None | 148A/0 | 606633.94 | 0 | 55.451 | DB1+0 |  |  | 2025-10-25 | 2025-10-26 | 2025-10-01 | 2025-11-01 | 2025-11-02
ta505 | TA505 | 2025-10-01 | Supervisor | None | 158/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-07 | 2025-10-09
ta505 | TA505 | 2025-10-01 | Supervisor | None | 160/2 | 389485.88 | 0 | 35.602 | DA-1.5 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-01 | 2025-10-16 | 2025-10-18
ta505 | TA505 | 2025-10-01 | Supervisor | None | 159/3 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta505 | TA505 | 2025-10-01 | Supervisor | None | 160/1 | 389485.88 | 0 | 35.602 | DA-1.5 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-01 | 2025-10-30 | 2025-10-31
ta505 | TA505 | 2025-10-01 | Supervisor | None | 160/0 | 606633.94 | 0 | 55.451 | DB1+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-09 | 2025-10-11
ta505 | TA505 | 2025-10-01 | Supervisor | None | 161/0 | 679549.04 | 0 | 62.116 | DB2+3 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-01 | 2025-10-16 | 2025-10-18
ta505 | TA505 | 2025-10-01 | Supervisor | None | 161/1 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-01 | 2025-10-21 | 2025-10-22
ta505 | TA505 | 2025-10-01 | Supervisor | None | 164/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-01 | 2025-10-26 | 2025-10-27
ta505 | TA505 | 2025-10-01 | Supervisor | None | 164/3 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-25 | 2025-10-26 | 2025-10-01 | 2025-10-31 | 2025-11-01
ta505 | TA505 | 2025-10-01 | Supervisor | None | 167/4 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-07 | 2025-10-09
ta505 | TA505 | 2025-10-01 | Supervisor | None | 164/6 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-01 | 2025-10-12 | 2025-10-14
ta505 | TA505 | 2025-10-01 | Supervisor | None | 164/7 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-11 | 2025-10-12 | 2025-10-01 | 2025-10-17 | 2025-10-18
ta505 | TA505 | 2025-10-01 | Supervisor | None | 164/5 | 479215.76 | 0 | 43.804 | DA+6 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-01 | 2025-10-22 | 2025-10-23
ta505 | TA505 | 2025-10-01 | Supervisor | None | 167/3 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-21 | 2025-10-22 | 2025-10-01 | 2025-10-27 | 2025-10-28
ta505 | TA505 | 2025-10-01 | Supervisor | None | 167/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-07 | 2025-10-09
ta505 | TA505 | 2025-10-01 | Supervisor | None | 167/1 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-01 | 2025-10-12 | 2025-10-14
ta505 | TA505 | 2025-10-01 | Supervisor | None | 169/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-11 | 2025-10-12 | 2025-10-01 | 2025-10-17 | 2025-10-18
ta505 | TA505 | 2025-10-01 | Supervisor | None | 169/4 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-01 | 2025-10-22 | 2025-10-23
ta505 | TA505 | 2025-10-01 | Supervisor | None | 169/5 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-21 | 2025-10-22 | 2025-10-01 | 2025-10-27 | 2025-10-28

## MicroPlanIndex
file_path | project_name | project_key | rows_cleaned | status | error | plan_month
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-325 Nov 25.xlsx | TA325 | ta325 | 61 | ok |  | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-413 Nov'25.xlsx | TA413 | ta413 | 49 | ok |  | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-416 Nov'25.xlsx | TA416 | ta416 | 25 | ok |  | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-418 Nov'25.xlsx | TA418 | ta418 | 20 | ok |  | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-419 Nov'25.xlsx | TA419 | ta419 | 50 | ok |  | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-421 Nov'25.xlsx | TA421 | ta421 | 30 | ok |  | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-504 Nov'25.xlsx | TA504 | ta504 | 21 | ok |  | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-506 Nov'25.xlsx | TA506 | ta506 | 71 | ok |  | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-509 Nov'25.xlsx | TA509 | ta509 | 30 | ok |  | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\October 2025\Micro Plan - TA-413 Oct'25.xlsx | TA413 | ta413 | 57 | ok |  | 2025-10-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\October 2025\Micro Plan - TA-416 Oct'25.xlsx | TA416 | ta416 | 34 | ok |  | 2025-10-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\October 2025\Micro Plan - TA-419 Oct'25.xlsx | TA419 | ta419 | 17 | ok |  | 2025-10-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\October 2025\Micro Plan - TA-421 Oct'25.xlsx | TA421 | ta421 | 28 | ok |  | 2025-10-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\October 2025\Micro Plan - TB-408 Oct'25.xlsx | TB408 | tb408 | 29 | ok |  | 2025-10-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\October 2025\Micro Plan TA-505 Oct '25.xlsx | TA505 | ta505 | 49 | ok |  | 2025-10-01

## MicroPlanDataIssues
file_path | project_name | project_key | location_no | gang_name | section_incharge | supervisor | completion_date | expected_month
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-325 Nov 25.xlsx | TA325 | ta325 | 186/0 | New Gang 3 | Milan Mal | Nunuchand | 2025-12-05 | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-413 Nov'25.xlsx | TA413 | ta413 | 29/2 | Jwala Singh -2 | Shuvam Gupta | Haridasn | 2025-12-07 | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-413 Nov'25.xlsx | TA413 | ta413 | 13A/0 | Bhairaw Mahto | Shuvam Gupta | Dhalchand Mahto | 2025-12-05 | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-413 Nov'25.xlsx | TA413 | ta413 | 26/0 | Sherra Const. | Shuvam Gupta | Khooblal | 2025-10-31 | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-413 Nov'25.xlsx | TA413 | ta413 | 37/1 | Amit kumar singh | Kartik Jhorar | Akabr Ali | 2025-12-02 | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-413 Nov'25.xlsx | TA413 | ta413 | 43/1 | Punam kumari-2 | Kartik Jhorar | Sanjay Kumar | 2025-12-04 | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-413 Nov'25.xlsx | TA413 | ta413 | 43/5 | Punam kumari-2 | Kartik Jhorar | Sanjay Kumar | 2025-12-11 | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-419 Nov'25.xlsx | TA419 | ta419 | 62/3 | Infineda 2 | Mr. R.N Tyagi | Mr. Satyaprakash | 1900-01-22 | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-509 Nov'25.xlsx | TA509 | ta509 | 9/2. | DEVI CONST. | Prasanta Das | Mr. Sunil chouhan | 02.11.2025 | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-509 Nov'25.xlsx | TA509 | ta509 | 8/4. | DEVI CONST. | Prasanta Das | Mr. Abhishekh Yadav | 07.11.2025 | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\October 2025\Micro Plan - TA-413 Oct'25.xlsx | TA413 | ta413 | 9/11 | Jawla Singh-1 | Shuvam Gupta | Kamal Ravidas | 2025-11-02 | 2025-10-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\October 2025\Micro Plan - TA-413 Oct'25.xlsx | TA413 | ta413 | 3B/1 | Pritam Enterprises-3 | Shuvam Gupta | Rudra Prasad | 2025-09-08 | 2025-10-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\October 2025\Micro Plan - TA-413 Oct'25.xlsx | TA413 | ta413 | 11/0 | Pritam Enterprises-3 | Shuvam Gupta | Rudra Prasad | 2025-09-20 | 2025-10-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\October 2025\Micro Plan - TA-413 Oct'25.xlsx | TA413 | ta413 | 20/5 | Punam kumari-1 | Shuvam Gupta | Rahul Ravidas | 2025-11-01 | 2025-10-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\October 2025\Micro Plan - TA-413 Oct'25.xlsx | TA413 | ta413 | 25/0 | Kartik Mahto | Shuvam Gupta | Shuseel | 2025-11-04 | 2025-10-01