## PCH Mr. Arun Felbin
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD)
Mr. Arun Felbin | TA325 | 2.93 | 4.1 | 4.09 | 3.73 | 3.56 | 3.72 | 4.15 | 4.52 | 4.38 | 3.67 | 3.3 | 3.42 | 3.92 | 7657.89 | 102
Mr. Arun Felbin | TA414 | 3.24 | 0 | 0 | 0 | 0 | 0 | 0 | 3.24 | 3.04 | 3.48 | 3.69 | 4.23 | 3.81 | 747.7 | 16
Mr. Arun Felbin | TA416 | 4.38 | 4.27 | 3.61 | 3.65 | 3.48 | 3.72 | 4.4 | 4.37 | 4.54 | 3.5 | 3.14 | 1.73 | 3.95 | 2643.72 | 32
Mr. Arun Felbin | TA418 | 2.65 | 2.66 | 2.81 | 2.92 | 3.04 | 3.26 | 3.2 | 3.03 | 4.83 | 3.83 | 4.65 | 4.41 | 3.42 | 1055 | 26
Mr. Arun Felbin | TA421 | 4.02 | 5.61 | 5.51 | 4.65 | 6.28 | 6.75 | 6.12 | 7.2 | 6.84 | 7.38 | 7.9 | 12.27 | 6.43 | 2682.41 | 61
Mr. Arun Felbin | TA504 | 4.03 | 4.13 | 4.1 | 3.88 | 4.31 | 4.39 | 4.35 | 4.85 | 5.25 | 5 | 5.24 | 5.37 | 4.73 | 1610.53 | 30
Mr. Arun Felbin | TA505 | 4.55 | 4.83 | 4.94 | 3.93 | 3.66 | 3.88 | 4.11 | 4.69 | 4.8 | 4.88 | 5.1 | 5.51 | 4.62 | 5272.99 | 109
Mr. Arun Felbin | TA506 | 3.84 | 3.97 | 4.68 | 4.82 | 5.34 | 5.67 | 5.45 | 4.8 | 4.52 | 3.88 | 3.18 | 3.56 | 4.51 | 4236.09 | 159
Mr. Arun Felbin | TA509 | 4.51 | 4.4 | 5.68 | 7.7 | 6.46 | 5.76 | 3.32 | 4.23 | 4.4 | 4.64 | 5.62 | 4.23 | 4.69 | 1502.38 | 40
Mr. Arun Felbin | TA601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.1 | 3.96 | 4.31 | 109.72 | 3
Mr. Arun Felbin | TB501 | 0 | 0 | 1.4 | 2.37 | 2.24 | 1.5 | 1.13 | 1.6 | 1.41 | 0.66 | 3.07 | 3.08 | 1.74 | 202.43 | 30
[14 empty] | Total | 27720.86 | 608
Erection productivity | Oct'25 | Week 1: Nov'25; Week 2: Dec'25
PCH Overall
Erection productivity | Oct'25 | Week 1: Nov'25; Week 2: Dec'25
Weight/day (Avg) | 4.09 | Week 1: 4.32; Week 2: 4.57
No of Gangs engaged (Avg) | 102 | Week 1: 104; Week 2: 101
Erection productivity | Oct'25 | Week 1: Nov'25; Week 2: Dec'25
Project: TA325
Erection productivity | Oct'25 | Week 1: Nov'25; Week 2: Dec'25
Weight/day (Avg) | 3.77 | Week 1: 4.05; Week 2: 3.9
No of Gangs engaged (Avg) | 40 | Week 1: 42; Week 2: 22
Erection productivity | Oct'25 | Week 1: Nov'25; Week 2: Dec'25
Project: TA414
Erection productivity | Oct'25 | Week 1: Nov'25; Week 2: Dec'25
Weight/day (Avg) | 3.24 | Week 1: 3.24; Week 2: 3.82
No of Gangs engaged (Avg) | 1 | Week 1: 1; Week 2: 17
Erection productivity | Oct'25 | Week 1: Nov'25; Week 2: Dec'25
Project: TA416
Erection productivity | Oct'25 | Week 1: Nov'25; Week 2: Dec'25
Weight/day (Avg) | 4.05 | Week 1: 4.05; Week 2: 3.47
No of Gangs engaged (Avg) | 12 | Week 1: 9; Week 2: 5
Erection productivity | Oct'25 | Week 1: Nov'25; Week 2: Dec'25
Project: TA418
Erection productivity | Oct'25 | Week 1: Nov'25; Week 2: Dec'25
Weight/day (Avg) | 2.77 | Week 1: 3.13; Week 2: 4.42
No of Gangs engaged (Avg) | 5 | Week 1: 3; Week 2: 3
Erection productivity | Oct'25 | Week 1: Nov'25; Week 2: Dec'25
Project: TA421
Erection productivity | Oct'25 | Week 1: Nov'25; Week 2: Dec'25
Weight/day (Avg) | 4.93 | Week 1: 6.62; Week 2: 8.05
No of Gangs engaged (Avg) | 6 | Week 1: 7; Week 2: 5
Erection productivity | Oct'25 | Week 1: Nov'25; Week 2: Dec'25
Project: TA504
Erection productivity | Oct'25 | Week 1: Nov'25; Week 2: Dec'25
Weight/day (Avg) | 4.03 | Week 1: 4.51; Week 2: 5.23
No of Gangs engaged (Avg) | 4 | Week 1: 4; Week 2: 8
Erection productivity | Oct'25 | Week 1: Nov'25; Week 2: Dec'25
Project: TA505
Erection productivity | Oct'25 | Week 1: Nov'25; Week 2: Dec'25
Weight/day (Avg) | 4.51 | Week 1: 4.14; Week 2: 5.1
No of Gangs engaged (Avg) | 12 | Week 1: 12; Week 2: 16
Erection productivity | Oct'25 | Week 1: Nov'25; Week 2: Dec'25
Project: TA506
Erection productivity | Oct'25 | Week 1: Nov'25; Week 2: Dec'25
Weight/day (Avg) | 4.31 | Week 1: 5.27; Week 2: 3.86
No of Gangs engaged (Avg) | 16 | Week 1: 17; Week 2: 17
Erection productivity | Oct'25 | Week 1: Nov'25; Week 2: Dec'25
Project: TA509
Erection productivity | Oct'25 | Week 1: Nov'25; Week 2: Dec'25
Weight/day (Avg) | 5.06 | Week 1: 4.38; Week 2: 4.7
No of Gangs engaged (Avg) | 6 | Week 1: 5; Week 2: 6
Erection productivity | Oct'25 | Week 1: Nov'25; Week 2: Dec'25
Project: TA601
Erection productivity | Oct'25 | Week 1: Nov'25; Week 2: Dec'25
Weight/day (Avg) | 0 | Week 1: 0; Week 2: 4.31
No of Gangs engaged (Avg) | 0 | Week 1: 0; Week 2: 3
Erection productivity | Oct'25 | Week 1: Nov'25; Week 2: Dec'25
Project: TB501
Erection productivity | Oct'25 | Week 1: Nov'25; Week 2: Dec'25
Weight/day (Avg) | 2.04 | Week 1: 1.53; Week 2: 1.97
No of Gangs engaged (Avg) | 2 | Week 1: 5; Week 2: 3