## NKTL DPR PGCIL
KEC INTERNATIONAL LIMITED
DAILY PROGRESS REPORT : SUBMISSION STATUS AS ON |  |  |  |  | 2026-01-12
Name of the Project: | TW02: 400kV M/c Navasari-Kala Transmission Line.
NOA Ref.No: | 5002002222/Tower/DOM/A02-CC CS -3/NOA-II/WR2-400010
ROUTE ALIGNMENT PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
8.572 | 8.572 | 0 | 8.572 | 0
SOIL INVESTIGATION PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
14 | 10 | 0 | 10 | 4
DETAILED SURVEY PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
8.572 | 8.572 | 0 | 8.572 | 0
CHECK SURVEY PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
8.572 | 8.572 | 0 | 8.572 | 0
FOUNDATION PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
37 | 23 | 2 | 25 | 12
EARTHING PROGRESS SUMMARY
TOTAL QTY | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
37 | 5 | 0 | 5 | 32
TOWER ERECTION PROGRESS SUMMARY
TOTAL QTY | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
37 | 0 | 0 | 0 | 37
STRINGING PROGRESS SUMMARY
TOTAL QTY | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY(KM)
8.572 | 0 | 0 | 0 | 8.572
OPGW STRINGING PROGRESS SUMMARY
TOTAL QTY | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
8.572 | 0 | 0 | 0 | 8.572

## Visual Chart NKTL
Name of Line :- TW02: 400KV D/C Navsari-Kala Transmission Line.
Agency: M/S KEC International Limited | [21 empty] | Date:- | 2026-01-12
LEGENDS | [12 empty] | ABSTRACT
[13 empty] | Sl.No | Type of Work |  | Unit | Scope | ROW | Drawing Req. | Comp. | Balance | WIP | Front Available | Remark
| Erection Progress |  |  |  | 220 KV Line X-Ing |  |  |  |  | National Highway Crossing |  |  | 01 | Tower Foundation |  | Nos. | 29 | 4 |  | 22 | 7 | 2 | 1
Foundation Progress
| Excavation Progress | [8 empty] | Stringing Progress |  |  | 02 | Monopole Foundation |  | Nos. | 8 | 1 |  | 3 | 5 | 1 | 1 | 2 waterlogged
132 KV Line X-Ing
[10 empty] | Stringing Complete |  |  | 03 | Tower Erection |  | Nos. | 29 |  | 0 | 0 | 0
[5 empty] | 66 KV Line X-Ing |  |  |  |  | Railway Crossing. |  |  | 04 | Monopole Erection. |  | Nos. | 8 |  | 0 | 0 | 0
| Erection Completed | [6 empty] | ::::::::::: |  | Gas Pipe Line |  |  | 05 | Stringing |  | Km. | 8.572 |  | 0 | 0 | 0
| Foundation Completed |  |  |  | Earthing
| Excavation Completed | [8 empty] | River Crossing
. |  | 275.478 | 17 | 192.959 | 4 | 229.775 | 14 | 263.916 |  | 253.672 | 3 | 266.296 | 5 | 325.859 | 9 | 143.609 | 6 | 203.188 | 7 | 110.476 | 8 | 90.61 | 2 | 155.951
| DRY |  | WFR |  | DRY | [5 empty] | DFR |  | DFR |  | WFR |  | DFR |  | WFR |  | WFR |  | DFR
| 67/3(New) |  | 67/4 |  | 68/0 |  | 69/0 |  | 70/0 |  | 70/1 |  | 70A/0 |  | 71/0 |  | 72/0 |  | 72A/0 |  | 72B/0 |  | 72B/1
| QD60+9 |  | QDD60+9 |  | DD60-3 |  | PDD+9 |  | PDD+6 |  | DD60-3 |  | DD60-3 |  | DC2-3 |  | DD60-3 |  | DDH+0 |  | DDH+0 |  | DD60-3
400KV Crossing
DAMAN SECTION
. | 1 | 295.706 |  | 169.148 |  | 320.246 | 1 | 218.016 | 21 | 214.693 | 16 | 319.855 | 13 | 195.031 | 23 | 253.495 | 18 | 187.3435 | 11 | 187.3435 |  | 250.188 | ROW-01 | 367.454
| DFR | [9 empty] | WET |  | WFR |  | WFR |  | WFR |  | WFR |  | HR
| 73/0 |  | 74/0 |  | 75/0 |  | 75A/0 |  | 75B/0 |  | 75C/0 |  | 76/0 |  | 77/0 |  | 77A/0 |  | 77B/0 |  | 78/0 |  | 78A/0
| DD60+3 |  | PDD+9 |  | PDD+21 | 66KV Crossing | PDD+9 |  | PDD+6 |  | DD60+0 |  | DD45+0 |  | DD60+0 |  | DD60+0 |  | DD60+0 |  | QDD60+12 |  | QDD60+12
[5 empty] | (With Auxiliary X-arm) |  | Truncated | [13 empty] | 4MRC | 66 & 220KV Crossing | 4MRC
3
DAMAN SECTION
[11 empty] | 66 & 220KV Line Crossing |  | ROW-03 | 614.493 | 15
[11 empty] | Daman Ganga River Crossing |  |  |  | WET
[13 empty] | 84L/0 |  | 85L/0
[11 empty] | FALSE |  | QDS+0 | 66KV | QDS+0
| 25 | 241.759 | ROW-02 | 138.29 | 22 | 158.822 | 20 | 354.232 | 10 | 281.34 | 19 | 369.337 | ROW-04 | 614.493 | 2 | 275.996 | 12 | 321.281 | 3 | 312.662
[5 empty] | PS |  | WFR |  | WET |  | WET |  |  |  | WET |  | WET |  | WET |  | WET
| 79/0 |  | 80/0 |  | 80A/0 |  | 81/0 |  | 82/0 |  | 83/0 |  | 84/0 |  | 85/0 |  | 85/1 |  | 86/0 |  | 76/0(New)
| PDD+6 |  | PDD+6 |  | DD60+0 |  | DB2+0 |  | DD60+0 |  | DD60+0 |  | QDS+0 |  | QDS+0 |  | QDD60+0 |  | QDD60+9 |  | QD60+BB
|  |  | ROW |  |  |  | 1MRC
|  | SH Crossing | [10 empty] | ROW-05 | 614.493 | 24 |  |  |  |  | Proposed Coastal Highway
WET
[13 empty] | 84R/0 |  | 85R/0
[13 empty] | QDS+0 | 220KV | QDS+0
DAMAN SECTION

## NKTL DPR
Project Code |  |  |  | TA 310 |  |  |  | Date:- | 2026-01-12 | LOA Start Date |  | 2022-08-11 |  | President - T&D |  | Ganesh Srinivasan
Project Name |  |  |  | TW02: 400kV M/c Navasari-Kala Transmission Line. | [9 empty] | Chief Executive - T&D |  | Rajinder Gupta
Client Name |  |  |  | Power Grid Corporation of India Limited (PGCIL) |  |  |  | LOA Value | Amndt-11 | LOA End Date |  | 2023-11-10 |  | Vice President |  | Arun Felbin R
LOAValue / LE Value |  |  |  | Ex-Work Price component |  |  |  | 208.3623 | 242.5047 |  |  |  |  | Regional Manager |  | Nitin Bendale
|  |  |  | Local Transportation, In-transit insurance, loading-unloading Charges etc. (CR) |  |  |  | 3.1806 | 4.2275 | Time Extn |  | 2026-03-31 |  | Chief Manager
|  |  |  | Installation Charges (CR) |  |  |  | 74.121 | 124.7377 |  |  |  |  | Project Manager |  | Vivek Kumar Gupta
|  |  |  | Total Contract Value ( CR) |  |  |  | 285.6639 | 371.4699 |  |  |  |  | Planning Engineer |  | Dillip Kumar Jena
Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line.
Activity |  | Unit | LOA Qty. | Final Estimated Quantity | Cumulative L2 till Dec-2025 | Cumulative Progress till Dec'2025 | Balance | L2 for Jan'26 | Plan for Jan'2026 | Today's Progress | Progress till for Jan'2026 | WIP | Gangs at Present | Cumulative Progress till date | Balance Work | Remarks
Survey
Route Alignment |  | KM | 8.572 | 8.572 | 0 | 8.572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.572 | 0
Detailed Survey |  | KM | 8.572 | 8.572 | 0 | 8.572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.572 | 0
Check Survey |  | KM | 8.572 | 8.572 | 0 | 8.572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.572 | 0
Foundation |  | Nos | 37 | 37 | 0 | 23 | 14 | 0 | 5 |  | 2 | 3 | 3 | 25 | 12
Earthing-Pipe |  | Nos | 7 | 7 | 0 | 2 | 5 | 0 |  | 0 |  |  |  | 2 | 5
Earthing-CP/SE/CE |  | Nos | 30 | 30 | 0 | 8 | 22 | 0 | 5 | 0 |  |  |  | 8 | 22
Tower Erection |  | Nos | 37 | 37 | 0 | 0 | 37 | 0 | 6 |  | 0 |  |  | 0 | 37
Tack welding |  | Nos | 134 | 8.822 | 134 | 52 | -43.178 | 0 | 0 | 0 |  | 1 | 1 | 52 | 82
Stringing |  | KM | 8.572 | 8.572 | 0 | 0 | 8.572 | 0 | 0 |  | 0 |  |  | 0 | 8.572
Paying Out |  | KM | 52.39 | 52.876 | 52.39 | 15.1581 | 37.2319 | [6 empty] | 15.1581 | 50.853
Final Sag |  | KM | 52.39 | 52.876 | 52.39 | 15.1581 | 37.7179 | [6 empty] | 15.1581 | 50.853
OPGW |  | KM | 8.572 | 8.572 | 0 | 0 | 8.572 | [6 empty] | 0 | 8.572
Foundation | [17 empty] | Excavation | Steel | Approval Letter Reff Date-27/08/2025
SL No. | Loc. No. | T.0.T | Tower Configuration. | Classification | Classification date. | Start Date | RCC Qty | PCC Qty. | Status |  |  |  | End Date | Gang Name | Gang | Manpower | Remarks
1 | 67/4 | QDD60+9 | Danube Tower | WFR | 2025-10-16 | 2025-11-15 | 125.96 | 8.53 | Foundation Completed. |  |  |  | 2025-11-23 | Maa Bhawani Const.
2 | 68/0 | DD60-3 | Narrow base DC Tower. | DRY | 2025-05-03 | 2025-05-05 | 63.39 | 5.55 | Foundation Completed. |  |  |  | 2025-06-07 | Maa Bhawani Const. |  |  |  | 435.35 | 3.613 | WRTS-II/Valsad TLC/NMTL/195, Date-27/08/2025
3 | 69/0 | PDD+9 | Monopole, 3.8 mtr dia caisson Foundation. |  |  | 2025-09-23 | 148 | 0 | Foundation Completed. |  |  |  | 2025-11-09 | Harshiv Project Pvt Ltd.
4 | 70/0 | PDD+6 | Monopole,1.2mtr dia 08Nos Pile Foundation | [5 empty] | Yet to start. |  |  |  |  | Harshiv Project Pvt Ltd. |  |  | Front availability -01
5 | 70/1 | DD60-3 | Narrow base DC Tower. | DFR | 2025-05-27 | 2025-05-27 | 62.68 | 5.45 | Foundation Completed. |  |  |  | 2025-06-02 | Maa Bhawani Const. |  |  |  | 321.78 | 3.556 | WRTS-II/Valsad TLC/NMTL/195, Date-27/08/2025
6 | 70A/0 | DD60-3 | Narrow base DC Tower. | DFR | 2025-06-03 | 2025-06-09 | 62.68 | 5.45 | Foundation Completed. |  |  |  | 2025-06-14 | Maa Bhawani Const. |  |  |  | 321.78 | 3.556 | WRTS-II/Valsad TLC/NMTL/195, Date-27/08/2025
7 | 71/0 | DC2-3 | Narrow base DC Tower. | WFR | 2025-08-05 | 2025-08-08 | 46.37 | 5.26 | Foundation Completed. |  |  |  | 2025-09-03 | Maa Bhawani Const. |  |  |  | 317.14 | 2.854
8 | 72/0 | DD60-3 | Narrow base DC Tower. | DFR | 2025-08-04 | 2025-08-04 | 62.68 | 5.45 | Foundation Completed. |  |  |  | 2025-08-14 | Maa Bhawani Const. |  |  |  | 321.78 | 3.556 | WRTS-II/Valsad TLC/NMTL/195, Date-27/08/2025
9 | 72A/0 | DDH+0 | Dwarf Tower | WFR | 2025-07-26 | 2025-07-30 | 47.11 | 4.27 | Foundation Completed. |  |  |  | 2025-08-21 | Maa Bhawani Const. |  |  |  | 252.83 | 3.607 | WRTS-II/Valsad TLC/NMTL/195, Date-27/08/2025
10 | 72B/0 | DDH+0 | Dwarf Tower | WFR | 2025-08-05 | 2025-08-21 | 47.11 | 4.27 | Foundation Completed. |  |  |  | 2025-08-29 | Maa Bhawani Const.
11 | 72B/1 | DD60-3 | Narrow base DC Tower. | DFR | 2025-05-22 | 2025-05-22 | 62.68 | 5.45 | Foundation Completed. |  |  |  | 2025-05-30 | Maa Bhawani Const. |  |  |  | 321.78 | 3.556 | WRTS-II/Valsad TLC/NMTL/195, Date-27/08/2025
12 | 73/0 | DD60+3 | Narrow base DC Tower. | DFR | 2025-05-01 | 2025-05-01 | 69.72 | 6.18 | Foundation Completed. |  |  |  | 2025-05-28 | Maa Bhawani Const. |  |  |  | 369.37 | 4.067 | WRTS-II/Valsad TLC/NMTL/195, Date-27/08/2025
13 | 76/0 | DD45+0 | Narrow base DC Tower. | WFR | 2025-10-23 | 2025-10-24 | 61.71 | 6.61 | Foundation Completed. |  |  |  | 2025-11-04 | Maa Bhawani Const.
14 | 74/0 | PDD+9 | Monopole, Open Cast Foundation | HR |  | 2025-12-02 |  |  | Excavation, RQD testing, and soil investigation tests completed. Location waterlogged. |  |  |  |  | Maa Bhawani Const.
15 | 75/0 | PDD+18 | Monopole, Open Cast Foundation | HR |  | 2025-12-07 |  |  | RQD testing completed; excavation work stopped due to waterlogging at location.. |  |  |  |  | Maa Bhawani Const.
16 | 75A/0 | PDD+9 | Monopole,1.2mtr dia 08Nos Pile Foundation | Pile |  | 21/12/205 |  |  | P1, P3, P4, P5, P6 & P7 completed; P2 boring Work in progress.(14.5mtr completed). Casting plan for tomorrow. |  |  |  | WIP-1 | Harshiv Project Pvt Ltd. | Gang-1 | 11 | WIP-1
17 | 75B/0 | PDD+3 | Monopole, 3.8 mtr dia caisson Foundation. | Caisson |  | 2025-10-28 |  |  | Foundation Completed. |  |  |  | 2025-12-06 | Harshiv Project Pvt Ltd.
18 | 75C/0 | DD60+0 | Narrow base DC Tower. | WET | 2025-10-16 | 2025-10-21 | 89.54 | 9.33 | Foundation completed. |  |  |  | 2025-11-14 | Maa Bhawani Const.
19 | 77/0 | DD60+0 | Narrow base DC Tower. | WFR | 2025-12-17 | 2025-12-18 | 81.63 | 8.24 | Foundation completed. |  |  |  | 2025-12-23 | Maa Bhawani Const.
20 | 77A/0 | DD60+0 | Narrow base DC Tower. | WFR | 2025-06-02 | 2025-06-02 | 81.63 | 8.24 | Foundation Completed. |  |  |  | 2025-11-26 | Maa Bhawani Const. |  |  |  | 321.78 | 3.556
21 | 77B/0 | DD60+0 | Narrow base DC Tower. | WFR | 2025-09-18 | 2025-09-27 | 81.63 | 8.24 | Foundation completed. |  |  |  | 2025-10-13 | Maa Bhawani Const.
22 | 78/0 | QDD60+12 | Danube Tower | HR |  |  |  |  | HR classification approval Date-06/01/2026, Yet to start |  |  |  |  | Maa Bhawani Const.
23 | 78A/0 | QDD60+12 | Danube Tower | [5 empty] | Work stopped due to ROW issues (effective from 11/09/2025 |  |  |  | ROW-1 | Maa Bhawani Const. |  |  | ROW-1
24 | 79/0 | PDD+6 | Monopole, 3.8 mtr dia caisson Foundation. |  |  | 2025-11-25 |  |  | Foundation completed. |  |  |  | 2026-01-09 | Harshiv Project Pvt Ltd. | Gang-2 | 11 |  |  |  | The monopole inauguration on 11/09/2025. However, work was subsequently halted due to issues related to the ROW. The designated effective ROW period was from 11/09/2025 to 15/11/2025. Excavation work in Progress
25 | 80/0 | PDD+6 | Monopole, 3.8 mtr dia caisson Foundation. | [5 empty] | Work stopped due to ROW issues (effective from 11/09/2025 |  |  |  | ROW-2 | Maa Bhawani Const. |  |  | ROW-2
26 | 80A/0 | DD60+0 | Narrow base DC Tower. | PS | 2025-12-09 | 2025-12-13 |  |  | Foundation Completed. |  |  |  | 2025-12-19 | Maa Bhawani Const.
27 | 81/0 | DB2+0 | Narrow base DC Tower. | WFR | 2025-11-14 | 2025-11-23 | 34.9 | 3.78 | Foundation Completed., Raft, Pyramid & chimney casting is completed, Dt-03/12/25 & RC Casting 06/12/25. |  |  |  | 2025-12-03 | Maa Bhawani Const.
28 | 82/0 | DD60+0 | Narrow base DC Tower. | WET | 2025-09-20 | 2025-09-24 | 89.54 | 9.33 | Foundation Completed. |  |  |  | 2025-10-03 | Maa Bhawani Const.
29 | 83/0 | DD60+0 | Narrow base DC Tower. | WET | 2025-11-14 | 2025-11-25 | 89.54 | 9.33 | Foundation Completed. |  |  |  | 2025-11-30 | Maa Bhawani Const.
30 | 84L/0 | QDS+0 | River Crossing Tower | [5 empty] | Work stopped due to ROW issues (effective from 11/09/2025 |  |  |  | ROW-3 | Maa Bhawani Const. |  |  | ROW-3
31 | 84/0 | QDS+0 | River Crossing Tower | [5 empty] | Work stopped due to ROW issues (effective from 11/09/2025 |  |  |  | ROW-4 | Maa Bhawani Const. |  |  | ROW-4
32 | 84R/0 | QDS+0 | River Crossing Tower | [5 empty] | Work stopped due to ROW issues (effective from 11/09/2025 |  |  |  | ROW-5 | Maa Bhawani Const. |  |  | ROW-5
33 | 85L/0 | QDS+0 | River Crossing Tower | WET | 2025-10-12 | 2025-10-12 | 93.056 | 8.166 | Foundation Completed. |  |  |  | 2025-11-09 | Maa Bhawani Const.
34 | 85/0 | QDS+0 | River Crossing Tower | WET | 2025-11-08 | 2026-01-08 | 93.056 | 8.166 | 02 Pit casting completed, Plan for tomorrow steel binding & Casting (ROW effective from 12/11/25 to 08/01/2026) |  |  |  | WIP-2 | Maa Bhawani Const. |  |  | WIP-2
35 | 85R/0 | QDS+0 | River Crossing Tower | WET | 2025-11-08 | 2025-11-05 | 93.056 | 8.166 | Foundation Completed (ROW effective from 12/11/25- 08/11/25) |  |  |  | 2026-01-09 | Maa Bhawani Const.
36 | 85/1 | QDD60+0 | Danube Tower | WET | 2025-10-06 | 13/102025 | 113.03 | 7.54 | Foundation Completed. |  |  |  | 2025-10-19 | Maa Bhawani Const. |  |  |  | 580.63 | 4.137
37 | 86/0 | QDD60+9 | Danube Tower | WET | 2025-10-14 | 2025-10-19 |  |  | Plan for tomorrow steel Binding (ROW effective from 12/11/25 -08/01/26 ) |  |  |  | WIP-3 | Maa Bhawani Const. |  |  | WIP-3
Erection
SL No. | Loc. No. | T.0.T | Tower Configuration. | Start Date | Tower Wights (MT) | Status |  |  |  |  | End Date | Gang Name | Manpower | Gang No | Remarks
1 | 67/4 | QDD60+9 | Danube Tower | 2026-01-09 | 62.9236 | Materials shifting working progress. | [5 empty] | Rupesh Kumar | 30
2 | 68/0 | DD60-3 | Narrow base DC Tower. |  | 24.5577
3 | 69/0 | PDD+9 | Monopole |  | 67.6876
4 | 70/0 | PDD+6 | Monopole |  | 55.3997
5 | 70/1 | DD60-3 | Narrow base DC Tower. |  | 24.5577
6 | 70A/0 | DD60-3 | Narrow base DC Tower. |  | 24.5577
7 | 71/0 | DC2-3 | Narrow base DC Tower. |  | 18.4045
8 | 72/0 | DD60-3 | Narrow base DC Tower. |  | 24.5577
9 | 72A/0 | DDH+0 | Dwarf Tower |  | 33.0959
10 | 72B/0 | DDH+0 | Dwarf Tower |  | 33.0959
11 | 72B/1 | DD60-3 | Narrow base DC Tower. |  | 24.5577
12 | 73/0 | DD60+3 | Narrow base DC Tower. |  | 28.5847
13 | 74/0 | PDD+9 | Monopole |  | 68.9801
14 | 75/0 | PDD+18 | Monopole |  | 152.9682
15 | 75A/0 | PDD+9 | Monopole |  | 73.9382
16 | 75B/0 | PDD+3 | Monopole |  | 57.7091
17 | 75C/0 | DD60+0 | Narrow base DC Tower. |  | 27.1431
18 | 76/0 | DD45+0 | Narrow base DC Tower. |  | 26.3163
19 | 77/0 | DD60+0 | Narrow base DC Tower. |  | 27.1431
20 | 77A/0 | DD60+0 | Narrow base DC Tower. |  | 27.1431
21 | 77B/0 | DD60+0 | Narrow base DC Tower. |  | 27.1431
22 | 78/0 |  | Danube Tower |  | 66.4875
23 | 78A/0 |  | Danube Tower |  | 66.4875
24 | 79/0 | PDD+6 | Monopole |  | 57.7091
25 | 80/0 | PDD+6 | Monopole |  | 57.7091
26 | 80A/0 | DD60+0 | Narrow base DC Tower. |  | 27.1431
27 | 81/0 | DB2+0 | Narrow base DC Tower. |  | 20.5239
28 | 82/0 | DD60+0 | Narrow base DC Tower. |  | 27.1431
29 | 83/0 | DD60+0 | Narrow base DC Tower. |  | 27.1431
30 | 84L/0 | QDS+0 | River Crossing Tower |  | 39.2686
31 | 84/0 | QDS+0 | River Crossing Tower |  | 39.2686
32 | 84R/0 | QDS+0 | River Crossing Tower |  | 39.2686
33 | 85L/0 | QDS+0 | River Crossing Tower |  | 39.2686
34 | 85/0 | QDS+0 | River Crossing Tower |  | 39.2686
35 | 85R/0 | QDS+0 | River Crossing Tower |  | 39.2686
36 | 85/1 | QDD60+0 | Danube Tower |  | 48.58
37 | 86/0 | QDD60+9 | Danube Tower |  | 62.9236
Stringing
SL No. | Section |  | length | Tower Configuration. | Stringing Status |  | Paying Out / Rough Sag |  | Final Sag |  | Status |  |  | Gang Name | Manpower | Type of STR | Remarks
| Start | END |  |  | Rough Sag | Final Sag | Start Date | End Date | Start Date | End Date
1 | 67/3 | 67/4 | 275.478
2 | 67/4 | 68/0 | 192.96
3 | 68/0 | 69/0 | 229.775
4 | 69/0 | 70/0 | 263.916
5 | 70/0 | 70/1 | 253.627
6 | 70/1 | 70A/0 | 266.296
7 | 70A/0 | 71/0 | 325.859
8 | 71/0 | 72/0 | 143.609
9 | 72/0 | 72A/0 | 203.188
10 | 72A/0 | 72B/0 | 110.476
11 | 72B/0 | 72B/1 | 90.61
12 | 72B/1 | 73/0 | 155.951
13 | 73/0 | 74/0 | 295.706
14 | 74/0 | 75/0 | 169.148
15 | 75/0 | 75A/0 | 320.247
16 | 75A/0 | 75B/0 | 218.016
17 | 75B/0 | 75C/0 | 214.693
18 | 75C/0 | 76/0 | 319.855
19 | 76/0 | 77/0 | 195.031
20 | 77/0 | 77A/0 | 253.495
21 | 77A/0 | 77B/0 | 247.826
22 | 77B/0 | 78/0 | 149.17
23 | 78/0 | 78A/0 | 182.476
24 | 78A/0 | 79/0 | 426.82
25 | 79/0 | 80/0 | 241.759
26 | 80/0 | 80A/0 | 138.29
27 | 80A/0 | 81/0 | 158.822
28 | 81/0 | 82/0 | 354.232
29 | 82/0 | 83/0 | 281.34
30 | 83/0 | 84/0 | 369.337
31 | 84/0 | 85/0 | 614.493
32 | 85/0 | 85/1 | 275.996
33 | 85/1 | 86/0 | 321.281
34 | 86/0 | 76/0 | 312.663
8572.441
Formulas:
Cumulative Progress till Dec'2025 = [Cumulative L2 till Dec-2025]
Cumulative Progress till Dec'2025 = [Cumulative L2 till Dec-2025]+1

## Sheet2 (hidden)
Count of Classification | Column Labels
Row Labels | DFR | DRY | PS | WBC | WET | WET PADDY | WFR | WFR(3M RC) | WFR,3M RC | Grand Total
QA+0 | 2 | 7 |  |  | 3 |  | 1 |  |  | 13
QA+3 | 2 | 2 |  |  | 3 |  | 3 |  |  | 10
QA+6 | 2 | 7 |  |  | 4 |  | 1 |  |  | 14
QA+9 | 3 | 3 |  |  | 11 | 1 |  |  |  | 18
QB1+0 |  |  |  |  | 1 |  |  |  |  | 1
QB1+6 |  |  |  |  | 1 |  | 1 |  |  | 2
QB2+0 | 1 | 1 | [7 empty] | 2
QB2+3 |  |  |  |  | 1 |  |  |  |  | 1
QB2+6 |  | 1 |  |  | 1 |  |  |  |  | 2
QC1+0 | 1 |  |  |  | 2 |  |  |  |  | 3
QC1+3 |  |  |  |  | 1 |  | 1 |  |  | 2
QC1+9 |  |  |  |  | 1 |  | 1 |  |  | 2
QC2+0 |  |  |  |  | 1 |  | 1 |  |  | 2
QC2+18 | 1 |  |  |  | 3 |  |  |  |  | 4
QC2+25 |  |  |  |  | 1 |  |  |  |  | 1
QC2+3 |  |  |  |  | 1 |  |  |  |  | 1
QC2+9 |  |  |  |  | 1 |  |  |  |  | 1
QCT1+3 | [8 empty] | 1 | 1
QD45+0 |  |  |  |  | 3 |  |  |  |  | 3
QD45+3 | 1 |  | 1 |  | 3 |  |  |  |  | 5
QD45+6 |  | 1 |  |  | 2 |  |  |  |  | 3
QD45+9 |  |  |  |  | 2 |  |  | 1 |  | 3
QD60+0 | 1 |  |  |  | 1 |  |  |  |  | 2
QD60+18 | 1 |  |  |  | 1 |  |  |  |  | 2
QD60+25 | 1 |  |  |  | 4 |  | 1 |  |  | 6
QD60+3 |  |  |  |  | 1 |  |  | 1 |  | 2
QD60+3 RC |  |  |  | 1 | [5 empty] | 1
QD60+6 |  |  |  |  | 2 |  |  |  |  | 2
QD60+9 | 2 |  | 1 |  | 2 |  |  |  |  | 5
Grand Total | 18 | 22 | 2 | 1 | 57 | 1 | 10 | 2 | 1 | 114

## Sheet1 (hidden)
Row Labels | DFR | DRY | PS | WBC | WET | WET PADDY | WFR | WFR(3M RC) | WFR,3M RC | Grand Total
QA+0 | 2 | 7 |  |  | 3 |  | 1 |  |  | 13
QA+3 | 2 | 2 |  |  | 3 |  | 3 |  |  | 10
QA+6 | 2 | 7 |  |  | 4 |  | 1 |  |  | 14
QA+9 | 3 | 3 |  |  | 11 | 1 |  |  |  | 18
QB1+0 |  |  |  |  | 1 |  |  |  |  | 1
QB1+6 |  |  |  |  | 1 |  | 1 |  |  | 2
QB2+0 | 1 | 1 | [7 empty] | 2
QB2+3 |  |  |  |  | 1 |  |  |  |  | 1
QB2+6 |  | 1 |  |  | 1 |  |  |  |  | 2
QC1+0 | 1 |  |  |  | 2 |  |  |  |  | 3
QC1+3 |  |  |  |  | 1 |  | 1 |  |  | 2
QC1+9 |  |  |  |  | 1 |  | 1 |  |  | 2
QC2+0 |  |  |  |  | 1 |  | 1 |  |  | 2
QC2+18 | 1 |  |  |  | 3 |  |  |  |  | 4
QC2+25 |  |  |  |  | 1 |  |  |  |  | 1
QC2+3 |  |  |  |  | 1 |  |  |  |  | 1
QC2+9 |  |  |  |  | 1 |  |  |  |  | 1
QCT1+3 | [8 empty] | 1 | 1
QD45+0 |  |  |  |  | 3 |  |  |  |  | 3
QD45+3 | 1 |  | 1 |  | 3 |  |  |  |  | 5
QD45+6 |  | 1 |  |  | 2 |  |  |  |  | 3
QD45+9 |  |  |  |  | 2 |  |  | 1 |  | 3
QD60+0 | 1 |  |  |  | 1 |  |  |  |  | 2
QD60+18 | 1 |  |  |  | 1 |  |  |  |  | 2
QD60+25 | 1 |  |  |  | 4 |  | 1 |  |  | 6
QD60+3 |  |  |  |  | 1 |  |  | 1 |  | 2
QD60+3 RC |  |  |  | 1 | [5 empty] | 1
QD60+6 |  |  |  |  | 2 |  |  |  |  | 2
QD60+9 | 2 |  | 1 |  | 2 |  |  |  |  | 5
Grand Total | 18 | 22 | 2 | 1 | 57 | 1 | 10 | 2 | 1 | 114

## Visual Chart-Old (hidden)
1 | VISUAL CHART
2 | Name of Line :- TW02: 400KV M/C Navsari-Magarwada Transmission Line.
3 | Agency: M/S KEC International Limited | [21 empty] | Date:- | 2026-01-12
4 | LEGENDS | [13 empty] | ABSTRACT | [13 empty] | Name of Line :- TW02: 400KV M/C Navsari-Magarwada Transmission Line. | [8 empty] | Date | 2024-05-07
5 | [14 empty] | Sl.No | Type of Work |  | Unit | Scope | L2 Till Date | Completion | Balance | WIP | ROW | Front Available |  |  |  | Sl.No | Type of Work | Unit | Scope | L2 Till Date | Completion | Balance | WIP | ROW | Gang | Front Available
6 |  | Erection Progress | [12 empty] | 01 | Foundation |  | Nos. | 152 | 134 | 25 | 127 | 2 | 123 | 2 |  |  |  | 01 | Foundation | Nos. | 151 | 134 | 118 | 33 | 6 | 26 | 6 | 1
7 |  | Foundation Progress | [8 empty] | National Highway Crossing
8 |  | Excavation Progress | [12 empty] | 02 | Erection |  | Nos. | 152 | 134 | 0 | 152 | 2 | 149 | 1 |  |  |  | 02 | Erection | Nos. | 151 | 134 | 68 | 83 | 5 | 38 | 6
9 | [10 empty] | Stringing Progress
10 | [14 empty] | 03 | Stringing |  | Km. | 52.821 | 52.39 | 0 | 52.821 | 0 | [5 empty] | 03 | Stringing | Km. | 52.816 | 39 | 0 | 52.816 | 2 |  | 4
11 |  | Earthing | [8 empty] | Stringing Complete
12 | [5 empty] | 220 KV Line X-Ing
13 | [10 empty] | Railway Crossing.
14 |  | Erection Completed
15 |  | Foundation Completed |  |  |  | 132 KV Line X-Ing
16 |  | Excavation Completed | [6 empty] | ::::::::::: |  | Gas Pipe Line
17 | [5 empty] | 66 KV Line X-Ing
18 | [8 empty] | .
19 |  |  |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11
20 | [25 empty] | Span Length | No of Tower
21
22 | . | 1 | 184.716 | 2 | 365 | 3 | 370 | 4 | 392 | 5 | 387 | 6 | 426 | 7 | 402 | 8 | 424 | 9 | 394.831 | 10 | 292.868 | 11 | 428 | 12 | 392 | 4458.419 | 12
23 |  | WBC |  | WET |  | WET |  | WET |  | DRY |  | WET |  | WET |  | WET |  | DFR |  | DFR |  | DFR |  | DFR
24 |  | 19/0 |  | 20/0 |  | 20/1 |  | 20/2 |  | 20/3 |  | 20/4 |  | 20/5 |  | 20/6 |  | 20/7 |  | 21/0 |  | 22/0 |  | 22/1
25 |  | QD60+3 |  | QD45+6 |  | QA+6 |  | QA+6 |  | QCT+0 |  | QA+0 |  | QA+9 |  | QA+9 |  | QA+3 |  | QD60+9 |  | QD60+9 |  | QA+6
26 |  | RC-3M | SH | [6 empty] | TP-01 | [10 empty] | Railway
27 |  | 3
28 | 0 | NAVSARI SECTION | [14 empty] | VALSAD SECTION
30 | 1 |  | 184.716 |  | 365 |  | 370 |  | 392 |  | 387 |  | 426 |  | 402 |  | 424 |  | 394.831 |  | 292.868 |  | 428 |  | 392
31 | 2
32 | 3 | 19/0 |  | 20/0 |  | 20/1 |  | 20/2 |  | 20/3 |  | 20/4 |  | 20/5 |  | 20/6 |  | 20/7 |  | 21/0 |  | 22/0 |  | 22/1
33 | 4 | QD60+3 |  | QD45+6 |  | QA+6 |  | QA+6 |  | QCT+0 |  | QA+0 |  | QA+9 |  | QA+9 |  | QA+3 |  | QD60+9 |  | QD60+9 |  | QA+6
34 | 5 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE
35 | 6 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE |  | TRUE | FALSE | TRUE
36 | 7 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
37 | 8 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
38 | 9
39 | 10
40 |  | 12 |  | 13 |  | 14 |  | 15 |  |  |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22
41
42
43 |  | 13 | 337.419 | 14 | 481.369 | 15 | 384.662 | 16 | 431.029 | 17 | 249.615 | 18 | 360 | 19 | 425 | 20 | 303 | 21 | 402 | 22 | 375 | 23 | 364.58 | 24 | 164.914 | 4282.924 | 12
44 |  | DFR |  | DFR |  | WFR |  | WET |  | WET |  | WET |  | WET |  | WET |  | WET |  | DFR |  | DFR |  | DRY
45 |  | 22/2 |  | 23/0 |  | 24/0 |  | 25/0 |  | 26/0 |  | 27/0 |  | 27/1 |  | 27/2 |  | 27/3 |  | 27/4 |  | 27/5 |  | 28/0
46 |  | QA+9 |  | QD60+18 |  | QC1+9 |  | QC2+9 |  | QD60+9 |  | QD60+9 |  | QA+3 |  | QA+9 |  | QA+9 |  | QA+9 |  | QA+0 |  | QB2+6
47 | [10 empty] | NH | [5 empty] | 2 NOS 66KV | [7 empty] | 132KV
48
49 | 0 | VALSAD SECTION
50 | 1 |  | 337.419 |  | 481.369 |  | 384.662 |  | 431.029 |  | 249.615 |  | 360 |  | 425 |  | 303 |  | 402 |  | 375 |  | 364.58 |  | 164.914
51 | 2
52 | 3 | 22/2 |  | 23/0 |  | 24/0 |  | 25/0 |  | 26/0 |  | 27/0 |  | 27/1 |  | 27/2 |  | 27/3 |  | 27/4 |  | 27/5 |  | 28/0
53 | 4 | QA+9 |  | QD60+18 |  | QC1+9 |  | QC2+9 |  | QD60+9 |  | QD60+3 |  | QA+3 |  | QA+9 |  | QA+9 |  | QA+9 |  | QA+0 |  | QB2+6
54 | 5 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE
55 | 6 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE
56 | 7 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
57 | 8 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
58 | 9
59 | 10
60 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34
61 | [5 empty] | .
62
63 |  | 25 | 266.196 | 26 | 169.548 | 27 | 262.6 | 28 | 263.029 | 29 | 410.653 | 30 | 426.947 | 31 | 395.001 | 32 | 355 | 33 | 308 | 34 | 342 | 35 | 344 | 36 | 374 | 3911.477 | 12
64 |  | WFR |  | DFR |  | WET |  | WET |  | WET |  | WET |  | WET |  | WET |  | WFR |  | WFR |  | WET |  | DRY
65 |  | 29/0 |  | 30/0 |  | 30/1 |  | 30/2 |  | 30A/0 |  | 30B/0 |  | 30C/0 |  | 30C/1 |  | 30C/2 |  | 30C/3 |  | 30C/4 |  | 30C/5
66 |  | QD60+25 |  | QD60+25 |  | QB1+6 |  | QB1+0 |  | QC2+18 |  | QD45+25 |  | QB2+6 |  | QA+9 |  | QA+3 |  | QA+3 |  | QA+3 |  | QA+3
67 |  |  | Bullet Train | [7 empty] | 66KV
68 | 0 | VALSAD SECTION | [25 empty] | #REF!
70 | 1 |  | 266.196 |  | 169.548 |  | 262.6 |  | 263.029 |  | 410.653 |  | 426.947 |  | 395.001 |  | 355 |  | 308 |  | 342 |  | 344 |  | 374
71 | 2
72 | 3 | 29/0 |  | 30/0 |  | 30/1 |  | 30/2 |  | 30A/0 |  | 30B/0 |  | 30C/0 |  | 30C/1 |  | 30C/2 |  | 30C/3 |  | 30C/4 |  | 30C/5
73 | 4 | QD60+25 |  | QD60+25 |  | QB1+6 |  | QB1+0 |  | QC2+18 |  | QD45+25 |  | QB2+6 |  | QA+9 |  | QA+3 |  | QA+3 |  | QA+3 |  | QA+3
74 | 5 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE
75 | 6 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE
76 | 7 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
77 | 8 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
78 | 9
79 | 10
80 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | ROW |  | 42 |  | 43 |  | 44 |  | 45
81
82
83 |  | 37 | 319 | 38 | 351 | 39 | 399.33 | 40 | 357.628 | 41 | 285.007 | 42 | 410 | 43 | 348.415 | 44 | 397 | 45 | 406 | 46 | 437.67 | 47 | 370 | 48 | 369.149 | 4450.199 | 12
84 |  | WET |  | DRY |  | WET |  | WET |  | WET |  | WET |  | DRY |  | WET |  | DRY |  | DRY |  | WET |  | DRY
85 |  | 30C/6 |  | 30C/7 |  | 30C/8 |  | 31/0 |  | 32/0 |  | 33/0 |  | 33/1 |  | 34/0 |  | 34/1 |  | 34/2 |  | 35/0 |  | 35/1
86 |  | QA+6 |  | QA+0 |  | QA+9 |  | QD60+25 |  | QD60+25 |  | QD60+6 |  | QA+6 |  | QC2+0 |  | QA+6 |  | QA+9 |  | QD45+3 |  | QA+6
87 | [8 empty] | 220KV |  | Express way & SH
88 | 0 | VALSAD SECTION
90 | 1 |  | 319 |  | 351 |  | 399.33 |  | 357.628 |  | 285.007 |  | 410 |  | 348.415 |  | 397 |  | 406 |  | 437.67 |  | 370 |  | 369.149
91 | 2
92 | 3 | 30C/6 |  | 30C/7 |  | 30C/8 |  | 31/0 |  | 32/0 |  | 33/0 |  | 33/1 |  | 34/0 |  | 34/1 |  | 34/2 |  | 35/0 |  | 35/1
93 | 4 | QA+6 |  | QA+0 |  | QA+9 |  | QD60+25 |  | QD60+25 |  | QD60+6 |  | QA+6 |  | QC2+0 |  | QA+6 |  | QA+9 |  | QD45+3 |  | QA+6
94 | 5 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE
95 | 6 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE
96 | 7 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
97 | 8 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
98 | 9
99 | 10
100 |  | 46 |  | 47 |  | 48 |  | 49 |  | 50 |  | 51 |  | 52 |  | 53 |  | 54 |  |  |  | 55 |  | 56
101
102 |  |  |  | .
103 |  | 49 | 386 | 50 | 432 | 51 | 348 | 52 | 373.235 | 53 | 326 | 54 | 357 | 55 | 328 | 56 | 348 | 57 | 289 | 58 | 311.119 | 59 | 355.5 | 60 | 448.5 | 4302.354 | 12
104 |  | WET |  | WP |  | DRY |  | DFR |  | DRY |  | DRY |  | DRY |  | WET |  | WET |  | WET |  | DRY |  | WET
105 |  | 36/0 |  | 36/1 |  | 36/2 |  | 36/3 |  | 37/0 |  | 37/1 |  | 37/2 |  | 37/3 |  | 37/4 |  | 37/5 |  | 38/0 |  | 38/1
106 |  | QD45+0 |  | QA+9 |  | QA+0 |  | QA+0 |  | QB2+0 |  | QA+6 |  | QA+0 |  | QA+6 |  | QA+0 |  | QA+0 |  | QC1+0 |  | QA+9
107 | [24 empty] | SH
108 | 0 | VALSAD SECTION
110 | 1 |  | 386 |  | 432 |  | 348 |  | 373.235 |  | 326 |  | 357 |  | 328 |  | 348 |  | 289 |  | 311.119 |  | 355.5 |  | 448.5
111 | 2
112 | 3 | 36/0 |  | 36/1 |  | 36/2 |  | 36/3 |  | 37/0 |  | 37/1 |  | 37/2 |  | 37/3 |  | 37/4 |  | 37/5 |  | 38/0 |  | 38/1
113 | 4 | QD45+0 |  | QA+9 |  | QA+0 |  | QA+0 |  | QB2+0 |  | QA+6 |  | QA+0 |  | QA+6 |  | QA+0 |  | QA+0 |  | QC1+0 |  | QA+9
114 | 5 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | #REF! | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE
115 | 6 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | #REF! | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE
116 | 7 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
117 | 8 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
118 | 9
119 | 10
120
121 |  | 57 |  | 58 |  | 59 |  | 60 |  | 61 |  | 62 |  | 63 |  | 64 |  | 65 |  | 66 |  | 67 |  | 68
122
123
124 |  | 61 | 395 | 62 | 420 | 63 | 399 | 64 | 394.01 | 65 | 348.995 | 66 | 410 | 67 | 472.768 | 68 | 320 | 69 | 282.722 | 70 | 425.001 | 71 | 408 | 72 | 435 | 4710.485 | 12
125 |  | DRY |  | DRY |  | WFR |  | WFR |  | WFR |  | DFR |  | DFR |  | WET |  | WFR |  | WFR |  | WET |  | WET
126 |  | 38/2 |  | 38/3 |  | 38/4 |  | 38/5 |  | 39/0 |  | 39/1 |  | 39/2 |  | 40/0 |  | 40/1 |  | 41/0 |  | 41/1 |  | 41/2
127 |  | QA+9 |  | QA+6 | 66KV | QA+3 |  | QA+6 |  | QC2+0 |  | QA+3 |  | QB1+9 |  | QD45+9 |  | QA+0 |  | QC1+3 |  | QA+9 |  | QA+9
128
#REF! | 0 | VALSAD SECTION
#REF! | 1 |  | 395 |  | 420 |  | 399 |  | 394.01 |  | 348.995 |  | 410 |  | 472.768 |  | 320 |  | 282.722 |  | 425.001 |  | 408 |  | 435
#REF! | 2
#REF! | 3 | 38/2 |  | 38/3 |  | 38/4 |  | 38/5 |  | 39/0 |  | 39/1 |  | 39/2 |  | 40/0 |  | 40/1 |  | 41/0 |  | 41/1 |  | 41/2
#REF! | 4 | QA+9 |  | QA+6 |  | QA+3 |  | QA+6 |  | QC2+0 |  | QA+3 |  | QB1+9 |  | QD45+9 |  | QA+0 |  | QC1+3 |  | QA+9 |  | QA+9
#REF! | 5 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE
#REF! | 6 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE
#REF! | 7 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
#REF! | 8 | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
#REF! | 9
#REF! | 10
#REF! |  | 69 |  | 70 |  | 71 |  | 72 |  | 73 |  | 74 |  | 75 |  | 76 |  | 77 |  | 78 |  | 79 |  | 80
#REF!
#REF!
#REF! |  | 73 | 408 | 74 | 453 | 75 | 389.793 | 76 | 392 | 77 | 432 | 78 | 358 | 79 | 344 | 80 | 250.001 | 81 | 543.999 | 82 | 428.859 | 83 | 400 | 84 | 405 | 4804.652 | 12
#REF! |  | DRY |  | WFR |  | DFR |  | DFR |  | WET |  | DRY |  | DRY |  | WET |  | WET |  | WET |  | WET |  | WET
#REF! |  | 41/3 |  | 41/4 |  | 41/5 |  | 42/0 |  | 42/1 |  | 42/2 |  | 42/3 |  | 42A/0 |  | 42B/0 |  | 42B/1 |  | 43/0 |  | 43/1
#REF! |  | QA+6 |  | QB1+6 |  | QA+6 |  | QC2+18 | 66KV | QC2+25 |  | QA+3 |  | QA+0 |  | QD60+3 |  | QD60+18 |  | QB2+18 |  | QD45+3 |  | QA+9
#REF! | [16 empty] | NH
#REF!
#REF! | 0 | VALSAD SECTION
#REF! | 1 |  | 408 |  | 453 |  | 389.793 |  | 392 |  | 432 |  | 358 |  | 344 |  | 250.001 |  | 543.999 |  | 428.859 |  | 400 |  | 405
#REF! | 2
#REF! | 3 | 41/3 |  | 41/4 |  | 41/5 |  | 42/0 |  | 42/1 |  | 42/2 |  | 42/3 |  | 42A/0 |  | 42B/0 |  | 42B/1 |  | 43/0 |  | 43/1
#REF! | 4 | QA+6 |  | QB1+6 |  | QA+6 |  | QC2+18 |  | QC2+25 |  | QA+3 |  | QA+0 |  | QD60+3 |  | QD60+18 |  | QB2+18 |  | QD45+3 |  | QA+9
#REF! | 5 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE
#REF! | 6 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE
#REF! | 7 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
#REF! | 8 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
#REF! | 9
#REF! | 10
#REF! |  | ROW |  | ROW |  | ROW |  | 81 |  | 82 |  | 83 |  | 84 |  | 85 |  | 86 |  |  |  | 87 |  | 88
#REF!
#REF!
#REF! |  | 85 | 431 | 86 | 318.871 | 87 | 261.815 | 88 | 298.812 | 89 | 356 | 90 | 213.698 | 91 | 376.838 | 92 | 365.849 | 93 | 386.389 |  | 430 | 94 | 457 | 95 | 229 | 4274.906 | 12
#REF! |  | DRY |  | DRY |  | WET |  | WET |  | WET |  | WET |  | WET |  | DRY |  | DRY |  | DRY |  | DRY |  | WET
#REF! |  | 43/2 |  | 43/3 |  | 44/0 |  | 45/0 |  | 46/0 |  | 46/1 |  | 47/0 |  | 48/0 |  | 48A/0 |  | 49/0 |  | 49A/0 |  | 49B/0
#REF! |  | QA+9 |  | QA+0 |  | QD60+9 |  | QD60+25 |  | QD60+25 |  | QA+9 |  | QC1+3 |  | QB2+3 |  | QC1+0 |  | QB2+9 |  | QD60+6 |  | QB2+9
#REF! | [6 empty] | Express way |  | Bullet Train
#REF!
#REF! | 0 | VALSAD SECTION
#REF! | 1 |  | 431 |  | 318.871 |  | 261.815 |  | 298.812 |  | 356 |  | 213.698 |  | 376.838 |  | 365.849 |  | 386.389 |  | 430 |  | 412.989 |  | 422.643
#REF! | 2
#REF! | 3 | 43/2 |  | 43/3 |  | 44/0 |  | 45/0 |  | 46/0 |  | 46/1 |  | 47/0 |  | 48/0 |  | 48A/0 |  | 49/0 |  | 49/1 |  | 49A/0
#REF! | 4 | QA+9 |  | QA+0 |  | QD60+9 |  | QD60+25 |  | QD60+25 |  | QA+9 |  | QC1+3 |  | QB2+3 |  | QC1+0 |  | QD60+6 |  | QA+9 |  | QB1+9
#REF! | 5 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE
#REF! | 6 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE
#REF! | 7 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | TRUE
#REF! | 8 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE
#REF! | 9
#REF! | 10
#REF! |  | ROW-1 |  | 89 |  | 90 |  | 91 |  | 92 |  | 93 |  | 94 |  | 95 |  | 96 |  | 97 |  | 98 |  | 99
#REF!
#REF!
#REF! |  |  | 422.643 | 96 | 387.062 | 97 | 179.201 | 98 | 366.607 | 99 | 347 | 100 | 369.041 | 101 | 458.626 | 102 | 366.651 | 103 | 225.87 | 104 | 280.032 | 105 | 253.999 | 106 | 291.335 | 3699.352 | 12
#REF! |  |  |  | WET |  | WET |  | WET |  | WET |  | WET |  | WET |  | WET |  | PS |  | WET |  | DRY |  | WET
#REF! |  | 49C/0 |  | 50/0 |  | 51/0 |  | 52/0 |  | 53/0 |  | 53/1 |  | 54/0 |  | 55/0 |  | 56/0 |  | 57/0 |  | 58/0 |  | 58/1
#REF! |  | QA+9 |  | QD60+9 |  | QD45+3 |  | QC2+3 |  | QD45+6 |  | QA+0 |  | QD45+9 |  | QC1+9 |  | QD45+3 |  | QD45+0 |  | QB2+0 |  | QA+3
#REF! |  | 3
#REF! | 0 | VALSAD SECTION
#REF! | 1 |  | 387.062 |  | 179.201 |  | 366.607 |  | 347 |  | 369.041 |  | 458.626 |  | 366.651 |  | 225.87 |  | 280.032 |  | 253.999 |  | 291.335 |  | 173.928
#REF! | 2
#REF! | 3 | 50/0 |  | 51/0 |  | 52/0 |  | 53/0 |  | 53/1 |  | 54/0 |  | 55/0 |  | 56/0 |  | 57/0 |  | 58/0 |  | 58/1 |  | 59/0
#REF! | 4 | QD60+9 |  | QD45+3 |  | QC2+3 |  | QD45+6 |  | QA+0 |  | QD45+9 |  | QC1+9 |  | QD45+3 |  | QD45+0 |  | QB2+0 |  | QA+3 |  | QD60+9
#REF! | 5 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | #REF! | #REF!
#REF! | 6 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | #REF! | #REF!
#REF! | 7 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | #REF! | #REF!
#REF! | 8 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | #REF! | #REF!
#REF! | 9
#REF! | 10
#REF! |  | 100 |  | 101 |  | 102 |  | 103 | [9 empty] | 104 |  | 105 |  | 106 |  | 107
#REF!
#REF!
#REF! |  | 107 | 173.928 | 108 | 512.188 | 109 | 400 | 110 | 336.181 |  | 297.73 | 111 | 296 |  | 189.685 | 112 | 261 | 113 | 251.978 | 114 | 358 | 115 | 473.351 | 116 | 306.676 | 4031.53 | 12
#REF! |  | WET |  | WET |  | WET |  | DRY |  |  |  | WET |  | DRY |  | DRY |  | DRY |  | WET |  | DRY |  | WET
#REF! |  | 59/0 |  | 60/0 |  | 61/0 |  | 61/1 |  | 62/0 |  | 63/0 |  | 63/1 |  | 64/0 |  | 64/1 |  | 65/0 |  | 65/1 |  | 66/0
#REF! |  | QD60+9 |  | QC2+18 |  | QD60+18 |  | QA+0 |  | QD60+6 |  | QD60+6 |  | QA+0 |  | QD45+0 |  | QA+0 |  | QC1+0 |  | QA+6 |  | QC2+18
#REF! |  |  | 220KV |  | 2NOS 66KV | [19 empty] | 66KV
#REF! | [9 empty] | ROW | NH & Railway.
#REF! | [9 empty] | 2
#REF! | 0 | VALSAD SECTION
#REF! | 1 |  | 512.188 |  | 400 |  | 336.181 |  | 297.73 |  | 296 |  | 189.685 |  | 261 |  | 251.978 |  | 358 |  | 473.351 |  | 306.676 |  | 348
#REF! | 2
#REF! | 3 | 60/0 |  | 61/0 |  | 61/1 |  | 62/0 |  | 63/0 |  | 63/1 |  | 64/0 |  | 64/1 |  | 65/0 |  | 65/1 |  | 66/0 |  | 67/0
#REF! | 4 | QC2+18 |  | QD60+18 |  | QA+0 |  | QD60+6 |  | QD60+6 |  | QA+0 |  | QD45+0 |  | QA+0 |  | QC1+0 |  | QA+6 |  | QC2+18 |  | QD45+9
#REF! | 5 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE
#REF! | 6 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE
#REF! | 7 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
#REF! | 8 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
#REF! | 9
#REF! | 10
#REF! | [13 empty] | 108
#REF!
#REF!
#REF! |  | 117 | 348 | 118 | 323 | 119 | 357 | 120 | 337.781 | 121 | 213.588 | 122 | 406 | 123 | 416 | 124 | 386.693 | 125 | 375.998 |  | 259 |  | 327 | 126 | 356 | 4228.248 | 12
#REF! |  | WET |  | DRY |  | WET |  | DRY |  | DFR |  | DFR |  | DFR |  | WET |  | DFR | [5 empty] | DFR
#REF! |  | 67/0 |  | 67/1 |  | 67/2 |  | 67/3 |  | 68/0 |  | 69/0 |  | 69/1 |  | 69/2 |  | 70/0 |  | 70/1 |  | 70/2 |  | 70/3
#REF! |  | QD45+9 |  | QA+9 |  | QA+9 |  | QA+9 |  | QD60+0 |  | QC2+3 |  | QA+9 |  | QA+6 |  | QD45+3 |  | QA+9 | 66KV | QA+9 |  | QA+3
#REF! | [19 empty] | ROW |  | ROW
#REF! | [19 empty] | 3 |  | 4
#REF! | 0 | VALSAD SECTION
#REF! | 1 |  | 323 |  | 357 |  | 337.781 |  | 213.588 |  | 406 |  | 416 |  | 386.693 |  | 375.998 |  | 259 |  | 327 |  | 356 |  | 470.188
#REF! | 2
#REF! | 3 | 67/1 |  | 67/2 |  | 67/3 |  | 68/0 |  | 69/0 |  | 69/1 |  | 69/2 |  | 70/0 |  | 70/1 |  | 70/2 |  | 70/3 |  | 70A/0
#REF! | 4 | QA+0 |  | QA+3 |  | QA+3 |  | QD60+0 |  | QC2+3 |  | QA+9 |  | QA+6 |  | QD45+3 |  | QA+9 |  | QA+9 |  | QA+3 |  | QC1+18
#REF! | 5 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE
#REF! | 6 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE
#REF! | 7 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
#REF! | 8 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
#REF! | 9
#REF! | 10
#REF! |  |  |  | 109 |  | 110 | [9 empty] | 111 |  | 112 | [5 empty] | ROW
#REF!
#REF!
#REF! |  |  | 470.188 | 127 | 319.467 | 128 | 417.397 |  | 375.633 |  | 223.903 |  | 226.09 |  | 221.93 | 129 | 259.639 | 130 | 394 |  | 290 | 131 | 371.161 | 132 | 364 | 3918.721 | 12
#REF! |  |  |  | DFR |  | DFR | [9 empty] | WFR |  | WFR |  |  |  | WFR |  | DRY
#REF! |  | 70A/0 |  | 70B/0 |  | 71/0 |  | 72/0 |  | 73/0 |  | 73A/0 |  | 73B/0 |  | 74/0 |  | 74A/0 |  | 74B/0 |  | 74B/1 |  | 75/0
#REF! |  | QC1+18 |  | QD45+3 |  | QC1+0 | 66KV | QC2+18 |  | QD45+9 |  | QD60+18 |  | QD60+9 |  | QD45+9 |  | QD60+3 |  | QD60+0 |  | QCT+3 |  | QD45+6
#REF! | [8 empty] | 66KV |  |  | RC | 66KV | RC | 66KV | RC |  | RC |  | RC |  | RC
#REF! | [11 empty] | 3 |  | 3 |  | 3 |  | 3 |  | 4 |  | 3
#REF! |  | ROW | [5 empty] | ROW |  | ROW |  | ROW |  | ROW | [7 empty] | TP-02
#REF! |  | 5 | [5 empty] | 6 |  | 7 |  | 8 |  | 9
#REF! | 0 | VALSAD |  |  | DAMAN SECTION
#REF! | 1 |  | 319.467 |  | 417.397 |  | 375.633 |  | 223.903 |  | 226.09 |  | 221.93 |  | 259.639 |  | 394 |  | 290 |  | 371.161 |  | 364 |  | 450
#REF! | 2
#REF! | 3 | 70B/0 |  | 71/0 |  | 72/0 |  | 73/0 |  | 73A/0 |  | 73B/0 |  | 74/0 |  | 74A/0 |  | 74B/0 |  | 74B/1 |  | 75/0 |  | 75/1
#REF! | 4 | QD45+3 |  | QC1+0 |  | QC2+18 |  | QD45+9 |  | QD60+18 |  | QD60+9 |  | QD45+9 |  | QD60+3 |  | QD60+0 |  | QCT+3 |  | QD45+6 |  | QA+6
#REF! | 5 | FALSE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE
#REF! | 6 | FALSE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE
#REF! | 7 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
#REF! | 8 | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
#REF! | 9
#REF! | 10
#REF! | [5 empty] | 113 |  | 114 |  | 115 |  | 116 |  |  |  | 117
#REF!
#REF!
#REF! |  | 133 | 450 | 134 | 384 | 135 | 410.31 | 136 | 239.566 | 137 | 299.5 | 138 | 210.86 | 139 | 103.659 | 140 | 99.872 | [8 empty] | 1747.766 | 8
#REF! |  | DRY |  | DRY |  | DRY |  | WET |  | WET |  | WET |  | WET |  | WET
#REF! |  | 75/1 |  | 75/2 |  | 75/3 |  | 76/0 |  | 77/0 |  | 78/0 |  | 79/0 |  | 80/0 |  | S/S
#REF! |  | QA+6 |  | QA+9 |  | QA+0 |  | QD45+3 |  | QD45+0 |  | QD45+0 |  | QD60+9 |  | QD60+0 |  | GANTRY | [7 empty] | 52.821 | 152
#REF! | [13 empty] | COMMON POINT
#REF! | 0 | DAMAN SECTION
#REF! | 1 |  | 384 |  | 410.31 |  | 239.566 |  | 299.5 |  | 210.86 |  | 103.659 |  | 99.872
#REF! | 2
#REF! | 3 | 75/2 |  | 75/3 |  | 76/0 |  | 77/0 |  | 78/0 |  | 79/0 |  | 80/0
#REF! | 4 | QA+9 |  | QA+0 |  | QD45+3 |  | QD45+0 |  | QD45+0 |  | QD60+9 |  | QD60+0
#REF! | 5 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | TRUE | #REF! | #REF! | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
#REF! | 6 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | TRUE | #REF! | #REF! | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
#REF! | 7 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | #REF! | #REF! | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
#REF! | 8 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | #REF! | #REF! | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
#REF! | 9
#REF! | 10
#REF! |  | Tower Type | Extension
#REF! |  |  | +0 | +3 | +6 | +9 | +18 | +25 | Total | Remark
#REF! |  | QA | 16 | 11 | 16 | 25 | 0 | 0 | 68 | QA+6=01
#REF! |  | QB1 | 1 | 0 | 2 | 2 | 0 | 0 | 5 | QB+9=01
#REF! |  | QB2 | 2 | 1 | 2 | 0 | 1 | 0 | 6
#REF! |  | QC1 | 4 | 2 | 0 | 2 | 1 | 0 | 9
#REF! |  | QC2 | 2 | 2 | 0 | 1 | 5 | 1 | 11
#REF! |  | QCT | 1 | 1 | 0 | 0 | 0 | 0 | 2
#REF! |  | QD45 | 5 | 7 | 3 | 5 | 0 | 1 | 21
#REF! |  | QD60 | 3 | 3 | 4 | 9 | 4 | 6 | 29
#REF! |  | Total Nos of Tower | [6 empty] | 151

## Location wise status
Name of the Line:-400kV D/c Navasari-Kala Transmission Line.
Status Summary: |  |  |  |  | Tower | Monopole |  | Date:- | 2026-01-07
Total Locations: |  |  | 37 |  | 29 | 8
Completed: |  |  | 23 |  | 21 | 2
Balance: |  |  | 14 |  | 8 | 6
Work in Progress (WIP): |  |  | 4 |  | 0 | 4
Work front Available:- |  |  | 2 |  | 1 | 1
ROW Pending: |  |  | 8 |  | 7 | 1
Sl. No. | Loc. No. | T.O.T | Tower configuration | Balance Location status | Start Date | End Date | Foundation Gang | Present Status | Remark.
1 | 70/0 | PDD+6 | Monopole,1.2mtr dia 08Nos Pile Foundation | Yet to start. | 2026-01-17 | 2026-02-12 | Harshiv Project Pvt Ltd. |  | Start of Pile-17/01/2026 End-31/02/2026, Pile cap completion-10/02/2026. Chimney 12/02/2026 Subject to steel supply Revised Amendment to be submitted-12/01/2025
2 | 74/0 | PDD+9 | Monopole, Open Cast Foundation | Excavation, RQD testing, and soil investigation test completed Date-05/01/2026 |  |  | Maa Bhawani Const. | WIP-1 | (05/01/2026 )Soil investigation Report to be submitted-13/01/2026, drawing to be provided by 17/01/2026.
3 | 75/0 | PDD+18 | Monopole, Open Cast Foundation | Excavation WIP. | 2025-12-07 | 2026-02-10 | Maa Bhawani Const. | WIP‑2 | Excavation to be completed-15/01/2026, Anchoring to be completed-30/01/2026, Steel binding to be completed-05/03/2025, Raft Casting to be completed -07/02/2026, Chimney to be completed-10/02/2026.
4 | 75A/0 | PDD+9 | Monopole,1.2mtr dia 08Nos Pile Foundation | P1, P3, P5, and P7 completed; P4 boring completed up to 14.5 m depth. Casing Plan for tomorrow. | 2025-12-18 | 2026-01-31 | Harshiv Project Pvt Ltd. | WIP-3 | End of Pile -16/01/2026, Pile Cap completion-26/01/2026. Chimney Completion-30/01/2026
5 | 78/0 | QDD60+12 | Danube Tower | HR classification approval Date-06/01/2026, Yet to start | 2026-01-08 |  | Maa Bhawani Const. |  | Excavation to be completed-24/01/2026, Anchoring to be completed-30/01/2026, Steel binding to be completed-02/02/2025, Raft Casting to be completed -04/02/2026, Chimney to be completed-10/02/2026.
6 | 78A/0 | QDD60+12 | Danube Tower | Work stopped due to ROW issues (effective from 11/09/2025 |  |  | Maa Bhawani Const. | ROW‑1 | ROW Clearance to be provided-09/01/2026.
7 | 79/0 | PDD+6 | Monopole, 3.8 mtr dia caisson Foundation. | Bolt fixing work in progress; casting planned for tomorrow. | 2025-12-31 | 2026-01-08 | Harshiv Project Pvt Ltd. | WIP-4 | Location to be completed-08/01/2026.
8 | 80/0 | PDD+6 | Monopole, 3.8 mtr dia caisson Foundation. | Work stopped due to ROW issues (effective from 11/09/2025 |  |  | Maa Bhawani Const. | ROW‑2 | ROW Clearance to be provided-09/01/2026.
9 | 84L/0 | QDS+0 | River Crossing Tower | Work stopped due to ROW issues (effective from 11/12/2025 |  |  | Maa Bhawani Const. | ROW‑3 | ROW Clearance to be provided-09/01/2026.
10 | 84/0 | QDS+0 | River Crossing Tower | Work stopped due to ROW issues (effective from 11/12/2025 |  |  | Maa Bhawani Const. | ROW‑4 | ROW Clearance to be provided-09/01/2026.
11 | 84R/0 | QDS+0 | River Crossing Tower | Work stopped due to ROW issues (effective from 11/12/2025 |  |  | Maa Bhawani Const. | ROW‑5 | ROW Clearance to be provided-09/01/2026.
12 | 85/0 | QDS+0 | River Crossing Tower | Work stopped due to ROW issues (effective from 12/11/2025). 02 Pit Excavation completed, then backfilling by land landowner. |  |  | Maa Bhawani Const. | ROW‑6 | ROW Clearance to be provided-09/01/2026.
13 | 85R/0 | QDS+0 | River Crossing Tower | Work stopped due to ROW issues (effective from 12/11/2025). (Only 02 chiminy casting Balance) |  |  | Maa Bhawani Const. | ROW‑7 | ROW Clearance to be provided-09/01/2026.
14 | 86/0 | QDD60+9 | Danube Tower | Work stopped due to ROW issues (effective from 12/11/2025).(Excavation & PCC Completed.) |  |  | Maa Bhawani Const. | ROW‑8 | ROW Clearance to be provided-09/01/2026.

## Survey Status
Survey Status for 400Kv M/C New Navsari to Magarwada Transmission Line. | [13 empty] | Date | 2026-01-12
Sl. No. | Section | Detail Survey | [6 empty] | Check Survey
|  | Complited | Submitted Kms with Date |  | Revised | Approved with Date |  | Revised | Complited | Submitted Kms with Date |  | Revised | Approved with Date | Revised | Remarks | Detailed Survey Status
| 8.882 | 8.822 | 8.822 | Date | Date | 7.212 | Date | Date | 8.822 | Date |  | Date | 0 | Date |  | AP-19/0 | TO | AP-28/0 | = | 8.564 | Approved 15.10.2022
1 | 67/3-76/0 | 8.822 | 8.822 | 2025-03-17 |  | 7.212 | 21.03.2025 |  | 8.822 | 7.583 | 2025-03-28 |  |  |  |  | AP-38/0 | TO | AP-44/0 | = | 11.051 | Approved
2 | [15 empty] | AP-44/0 | TO | 52/0 | = | 4.087 | Approved
3 | [15 empty] | AP-52/0 | TO | AP-76/0 | = | 16.089 | Approved
4 | [15 empty] | Total |  |  |  | 39.791
5
6 | [15 empty] | AP34/0 to 35/0 Check Survey Pending.
7
8
9
10
| Total | 8.822 | 8.822 |  |  | 7.212 |  | 0 | 8.822 | 7.583 |  |  | 0

## Soil investigation
Soil Investigation Letter Ref No.
Ref.WRTS-II/Valsad TLC/NMTL Date-09/02/2025
Ref.WRTS-II/Valsad TLC/NMTL Date-17/02/2025
SL. No | Loc.No | Type of Tower | RC | Tower Structure | Depth | Start Date | End Date | Status | REMARKS
#VALUE! | 79/0 | PDD+6 |  | Monopole | 20 | 2025-02-19 | 2025-02-22 | Completed
#VALUE! | 78A/0 | QDD60+9 | 4 | Danube Tower | 20 | 2025-02-23 | 2025-02-24 | Completed
#VALUE! | 75/0 | PDD+18 |  | MonoPole (with AUX Arm) | 20 | 2025-02-27 | 2025-03-01 | Completed
#VALUE! | 74/0 | PDD+9 |  | Monopole | 20 | 2025-03-02 | 2025-03-04 | Completed
#VALUE! | 78/0 | QDD60+9 | 4 | Danube Tower | 20 | 2025-02-25 | 2025-03-11 | Completed
#VALUE! | 75A/0 | PDD+9 |  | Monopole | 20 | 2025-03-10 | 2025-03-20 | Completed
#VALUE! | 80/0 | PDD+6 |  | Monopole | 20 | 2025-02-18 | 2025-03-21 | Completed
#VALUE! | 75B/0 | PDD+3 |  | Monopole | 20 | 2025-03-22 | 2025-03-25 | Completed
#VALUE! | 70/0 | PDD+6 |  | Monopole | 20 | 2025-05-19 | 2025-05-22 | Completed
1 | 69/0 | PDD+9 |  | Monopole | 20 | 2025-06-07 | 2025-06-08 | Completed
2 | 78/0 | QDD60+12 | 4 | Danube Tower | 10 | 2025-11-12 | 2025-11-14 | Completed
3 | 77/0 | DD60+0 |  | Narrow Base DC Tower | 10 | 2025-11-15 | 2025-11-18 | Completed
4 | 80A/0 | DD60+0 |  | Narrow Base DC Tower |  |  |  | Pending
5 | 84/1 | QDD60+9 | 5 | Danube Tower | 40 |  |  | Pending | Location changed as check survey.
6 | 85/0 | DD60+0 |  | Narrow Base DC Tower | 40 |  |  | Pending
Formulas:
End Date = [Start Date]+2

## Crossing Details
CROSSINGS PROPOSAL STATUS
Transmission Line Tower Package-TW02 400KV D/C Navsari - Kala Transmission line.( Twin HTLS)
Power Line Crossings
Sl. No. | Section |  | NAME OF CROSSING | Check Survey Status | Date of Submission | Status of proposal | Approving Authority | Exp. date of Approval | Remarks
1 | 72A/0 | 72B/0 | 400KV M/C Navsari - Magarawada - Kala Transmission line. | Approved | 2025-07-03 | Under Process | PGCIL
2 | 75/0 | 75A/0 | 66KV D/C Dalwada -Dabhel transmission line. | Approved | 2025-07-19 | Under Process | GETCO
3 | 78/0 | 78A/0 | 220KV D/C Magarwada -Ringanwada Transmission line. | Approved | 2025-09-08 | Under Process | PGCIL
4 | 78/0 | 78A/0 | 66KV D/C Ringanwada-Varkund Transmission line. | Approved | 2025-09-08 | Under Process | GETCO
5 | 84/0 | 85/0 | 220KV D/C Magarwada -Ringanwada Transmission line. | Approved | 2025-07-27 | Under Process | PGCIL
6 | 84/0 | 85/0 | 66KV D/C Ringanwada-Varkund Transmission line.(Tap to Magarwada-Varkund line.) | Approved | 2025-07-27 | Under Process | GETCO
Total | 6 |  |  |  | 6
SH Crossing
Sl. No. | FROM (AP) | TO (AP) | NAME OF CROSSING | Type of Crossing | Date of Submission | Status of proposal | Approving Authority | Exp. date of Approval | Remarks
1 | 79/0 | 80/0 | State high way | SH-185 |  | NA
Gas Pipe line
Sl. No. | FROM (AP) | TO (AP) | NAME OF CROSSING | Type of Crossing | Date of Submission | Status of proposal | Approving Authority | Exp. date of Approval | Remarks
1 | 81/0 | 82/0 |  |  |  | NA
PROPOSED COASTAL HIGHWAY
Sl. No. | FROM (AP) | TO (AP) | NAME OF CROSSING | Type of Crossing | Date of Submission | Status of proposal | Approving Authority | Exp. date of Approval | Remarks
1 | 86/0 | 76/0 | Proposed Costal Highway |  |  | NA
River Crossing
Sl. No. | FROM (AP) | TO (AP) | NAME OF CROSSING | Type of Crossing | Date of Submission | Status of proposal | Approving Authority | Exp. date of Approval | Remarks
1 | 84/0 | 85/0 | Daman Ganga River | River |  | NA
Aviation
Sl. No. | NAME OF CROSSINGS |  |  |  | Date of Submission | Status of proposal | Approving Authority | Exp. date of Approval | Remarks
1 | PTCC |  |  |  | 2025-09-08
2 | Civil Aviation |  |  |  | 2025-08-21
3 | Defense Aviation |  |  |  | 2025-08-21

## Line Scenario
Line Scenario for M/c 400KV New Navsari to Magarwada & 400KV Navsari to Kala transmission line.
From MC location 76/0 to 76/0, 8.75kM Navsari to Kala work balance otherwise all work completed.
Kala Substation | From CommonPoint 79/0 to Kala Sustation scope by M/s Bajaj | [9 empty] | From CommonPoint 19/0 to Navsari Sustation scope by M/s Bajaj | Navsari Substation
D/C Navsari - Magarwada (8.822KM)
D/c Navsari to Kala
|  |  | Loc-79/0 |  | Loc-76/0 |  | Loc-67/3 |  |  | Loc-19/0
|  |  |  | M/C Navsari-Magarwada |  |  |  | M/C Navsari-Magarwada
|  | Magarwada Substation |  |  |  | D/C Navsari- Kala (8.75KM)
From Common Point 19/0 to Magarwda Substation Gantry scope by MS KEC.

## Sheet3
TA310 | 400 KV M/C NKTL |  | Unit | Total Project Volume | Compltd. As on Apr'25 | Bal. as on 01.05.25 | Executed for the month of May'25 | Executed for the month of Jun'25 | Bal. as on 01.07.2025 | Remarks
Proj. code | Project Name | Foundation | Nos. | 34 | 34 | 34 | 2 | 3 | 29 | Workforce demobilization was necessitated by the unavailability of work fronts and unfavorable weather conditions
|  |  | Cum | 2429 | 2429 | 2429 | 144.03 | 205.2 | 2079.77
|  | Erection | Nos. | 34 | 34 | 34 | 0 | 0 | 34 | No. of gangs
|  |  | MT | 879.19 | 879.19 | 879.19 | 0 | 0 | 879.19
|  | Stringing (RS) | Kms. | 8.822 | 8.822 | 8.822 | 0 | 0 | 8.822 | TSE & Manual gangs
|  | Stringing (FS) | Kms. | 8.822 | 8.822 | 8.822 | 0 | 0 | 8.822

## Supply Status
400KV Navsari To Kala Transmission status, Supply Status:- | [10 empty] | 2026-01-12
Description |  | Line Qty. | Spare Qty | NKTL Req. | Total Req. | Damage Qty. | Received Qty. | Total Issue Qty. | Balance Qty Available at Store. | Balance Qty Required. | Remark
Conductor | TWIN HTLS MOOSE CONDUCTOR | 1265.3631 | 40 | 103.902 | 1409.2651 |  | 1309.984 | 1191.92 | 118.064
OPGW | 24 FIBRE (DWSM) OPGW FIBRE OPTIC CABLE | 99.1169 | 4 | 8.57 | 111.6869 |  | 111 | 99.589 | 11.411
Composite long rod Insulators | 120kN | 1040 | 117 | 117 | 1274 | 68 | 1249 | 1098 | 83 | 93 | Req
| 160kN | 3792 | 271 | 816 | 4879 | 108 | 4267 | 4618 | -1109 | 1370 | Req
Hardware Fittings | Twin HTLS Conductor-Single "I" Suspension String(without clamps) | 738 | 19 | 0 | 757 | 53 | 851 | 719 | 79 | -41
| Twin HTLS Conductor-Single I Suspension String(Pilot) (without clamps)(1x120KN) | 302 | 5 | 117 | 424 |  | 305 | 305 | 0 | 119 | Req
| Twin HTLS Conductor-Double TensionString (without clamps) | 1896 | 27 | 408 | 2331 | 15 | 2025 | 1892 | 118 | 321 | Req
| Twin HTLS Conductor-Single Tension String(without clamps) | 4 | 1 | 0 | 5 |  | 9 | 8 | 1 | -4
| Suspension clamp suitable for suspension insulator string | 1500 | 240 | 0 | 1740 |  | 1872 | 400 | 1472 | -132
| Deadend clamp suitable for tension insulator string | 3792 | 192 | 816 | 4800 |  | 4188 | 3848 | 340 | 612 | Req
| Suspension clamp suitable for suspension Pilot insulator string | 604 | 24 | 234 | 862 | 25 | 640 | 610 | 5 | 247 | Req
Conductor Accessories for HTLS Moose | MSCJ | 54 | 50 | 0 | 104 |  | 782 | 359 | 423 | -678
| Repair Sleeve | 15 | 50 | 0 | 65 |  | 294 | 114 | 180 | -229
| T- connector | 13 |  | 0 | 13 | 13 | 128 | 24 | 91 | -102
| Spacer Damper for TWIN Moose conductor | 10074 | 1008 | 888 | 11970 |  | 12264 | 10319 | 1945 | -294
| Rigid spacer for TWIN Moose conductor | 3378 | 72 | 731 | 4181 |  | 3504 | 3273 | 231 | 677 | Req