## 765KV TA 414 VNTL
| Project Code | TA 414 | Date |  | 2026-01-14 |  | President-T&D | Mr. Ganesh Srinivasan
| Project Name | 765KV D/C HEXA VATAMAN - NAVSARI TL (PKG 04) |  |  | NOA Start Date | 2024-03-12 | PCH | Mr. Arun Felbin
| Client Name | Powergrid Vataman Transmission Ltd |  |  | LOA End Date | 2025-12-11 | Regional Manager | Mr. Nitin Bandale
| Revised End Date | 2026-05-11 |  |  | Planning Engineer | Nishant Giri | Project Manger | Mr. Vivek Kumar Gupta
\
Check Survey
Activity | Unit | Final Est. Qty | L2 till Last Month | Submitted till Last Month | Approved till Last Month | Balance to Submit | Balance to Approve | L2 Submission Plan for Current Month | Progress For Month | Approved till Current Month | Remarks
Rout Alignment | km | 127.854 | 127.854 | 127.854 | 127.854 |  |  |  |  | 127.854 | Completed
Detailed Survey | km | 127.854 | 127.854 | 127.854 | 127.854 |  |  |  |  | 127.854 | Completed
Check Survey | km | 127.854 | 127.854 | 127.854 | 127.854 |  |  |  |  | 127.854 | Completed
Progress Status
Activity | Final Estimated Quantity | Cumulative L2 till Last Month (Dec'25) | Cumulative Progress till Last Month(Dec'25) | L2 for present Month | Plan for the Month | Today's Progress | Progress till Date for the Month | L2 till Current Month | Completed till Date | Balance Work | Under Progress | Gangs at Present | Remarks
Soil Investigation | 28 |  | 0 | 0 | 0 |  |  | 0 | 0 | 28 |  |  | Completed.
Foundation | 351 | 340 | 181 | 0 | 100 | 0 | 19 | 340 | 200 | 151 | 26 | 24
Earthing | 351 | 340 | 155 | 0 | 100 | 2 | 8 | 340 | 163 | 188
Tower Erection | 351 | 340 | 28 | 0 | 60 | 2 | 16 | 340 | 44 | 307 | 19 | 19
Tack welding | 351 | 340 |  | 0 | 30 |  |  | 340 | 0 | 351
Stringing(Km) | 127.854 | 130 |  | 0 | 5.7 |  |  | 130 | 0 | 127.854

## Project Details (hidden)
Project Code | Project Name | Client Name | NOA Start Date | LOA End Date | Planning Engineer | PCH | Regional Manager | Project Manager | Section Incharge | Supervisor
TA 414 | 765kV D/C VATAMAN NAVSARI TL04 | Powergrid Vataman Transmission Limited | 2024-03-12 | 2025-12-11 | Mr. Nishant Giri | Mr Arun Felbin | Mr. Nitin Ashok Bendale | Mr Vivek Kumar Gupta | Mr. Vivekanand Bera | Mr. Noton Ghosh
[9 empty] | Mr. Vipin Chandra Deshmukh | Mr. Kalicharan Patel
Mr. Ishwar Mahto
Mr. Raju Mahto
Mr. Shankar Mahto
Mr. Daulat Mahto
Mr. Atul kumar
Mr. Himanshu Behera
Mr. Shubendhu Kumar Sahoo
Mr. Hareshkumar Hirabhai Patel

## VNTL - KEC
KEC INTERNATIONAL LIMITED | [11 empty] | 2026-01-14
Name of Client: Powergrid Vataman Transmission Limited
Name of Line:Tl-04 , 765 kV D/C Vataman - Navsari Transmission Line
NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24
Sr No. | Activity | Estimated Quantity | Cumm. Progress up to till last Month (DEC'25) | Target as per L2 Schedule Cummulative (upto Jan'26) | L3 Plan for the month (Jan'26 ) | Today's Progress | Progress in this month | Cumm. Progress till date | Cumm. Balance | WIP | No of Gangs | Remark
1 | Route Alignment (Km) | 127.83 | 127.83 | 130 |  |  |  | 127.83 | 0
2 | Detailed Survey (Km) | 127.8541 | 127.8541 | 130 |  |  |  | 127.8541 | 0
3 | Profiling (Km) | 127.8541 | 127.8541 | 130 |  |  |  | 127.8541 | 0
4 | Check Survey (Km) | 127.8541 | 127.8541 | 130 |  |  |  | 127.8541 | 0
5 | Soil Investigation (Nos.) | 28 | 28 |  |  |  |  | 28 | 0
6 | Excavation | 351 | 181 | 340 | 100 | 0 | 19 | 200 | 151 | 26 | 24
7 | Foundation (Nos.) | 351 | 181 | 340 | 100 | 0 | 19 | 200 | 151 | 26 | 24
8 | Earthing (Nos.) | 351 | 155 | 340 | 100 | 2 | 8 | 163 | 188
9 | Tower Erection (Nos) | 351 | 28 | 340 | 60 | 2 | 16 | 44 | 307 | 19 | 19
10 | Tack Welding | 351 | 0 | 340 |  |  |  | 0 | 351
11 | Stringing (Km) | 127.8541 |  | 130 | 5.7 |  |  | 0 | 127.8541
a) | Paying Out | 127.8541 |  | 130 |  |  |  | 0 | 127.8541
b) | Final Sag | 127.8541 |  | 130 |  |  |  | 0 | 127.8541
12 | OPGW (Km) | 127.8541 |  | 130 |  |  |  | 0 | 127.8541

## DPR Sheet
KEC INTERNATIONAL LIMITED
DAILY PROGRESS REPORT : SUBMISSION STATUS AS ON |  |  |  |  | 2026-01-14
Name of the Project: |  | Tl-04 , 765 kV D/C Vataman - Navsari Transmission Line
Contract No. & Date : |  | CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24
ROUTE ALIGNMENT PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
127.8541 | 127.83 | 0 | 127.83 | 0
SOIL INVESTIGATION PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
28 | 28 | 0 | 28 | 0
DETAILED SURVEY PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
127.8541 | 127.8541 | 0 | 127.8541 | 0
CHECK SURVEY PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
127.8541 | 127.8541 | 0 | 127.8541 | 0
FOUNDATION PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
351 | 181 | 19 | 200 | 151
EARTHING PROGRESS SUMMARY
TOTAL QTY | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
351 | 155 | 8 | 163 | 188
TOWER ERECTION PROGRESS SUMMARY
TOTAL QTY | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
351 | 28 | 16 | 44 | 307
STRINGING PROGRESS SUMMARY
TOTAL QTY | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY(KM)
127.8541 | 0 | 0 | 0 | 127.8541
OPGW STRINGING PROGRESS SUMMARY
TOTAL QTY | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
127.8541 | 0 | 0 | 0 | 127.8541

## FDN
VNTL Foundation
Sl. No. | Location No. | Tower Type | Classification | Concreting Volume in M3 | Starting Date | Todays Status | Cumulative Status | Completion Date | Remarks | Gang name | Earthing Status | Earthing Completion Date
1 | 241/2 | DA+0 | Wet |  | 2024-05-15 |  | Completed | 2024-05-25 |  | Suraj Construction | Completed | 2024-05-26
2 | 241/0 | DD60+0 | Wet Paddy |  | 2024-05-21 |  | Completed | 2024-05-30 |  | Suraj Construction | Completed | 2024-05-31
3 | 241/1 | DA+0 | WPS |  | 2024-05-28 |  | Completed | 2025-12-31 | ROW Cleared On 28-12-25 | Suraj Construction
4 | 118/0 | DB2+0 | Wet |  | 2024-09-20 |  | Completed | 2024-10-31 |  | Anya Infra
5 | 121/5 | DA-3 | Wet |  | 2024-11-02 |  | Completed | 2024-11-19 |  | Adhyey Brothers
6 | 120/3 | DA+6 | Wet Paddy |  | 2024-11-04 |  | Completed | 2024-11-12 |  | Anya Infra
7 | 120/2 | DA+0 | wet |  | 2024-11-09 |  | Completed | 2024-11-22 |  | Anya Infra
8 | 121/4 | DA+0 | Wet |  | 2024-11-19 |  | Completed | 2024-11-29 |  | Adhyey Brothers
9 | 120/5 | DA-3 | Wet |  | 2024-11-30 |  | Completed | 2024-12-22 |  | APR Associates
10 | 121/2 | DA+9 | Wet |  | 2024-12-01 |  | Completed | 2024-12-07 |  | Adhyey Brothers
11 | 119/0 | DD60+0 | Wet |  | 2024-12-03 |  | Completed | 2024-12-16 |  | Himanshi Agency | Completed | 2024-12-17
12 | 120/6 | DA+0 | Wet Paddy |  | 2024-12-05 |  | Completed | 2025-01-04 |  | APR Associates
13 | 120/0 | DD60+3 | Wet |  | 2024-12-08 |  | Completed | 2024-12-22 |  | Himanshi Agency
14 | 121/3 | DA+0 | Wet |  | 2024-12-09 |  | Completed | 2024-12-21 |  | Adhya Enterprises
15 | 145/4 | DA+0 | Wet |  | 2024-12-11 |  | Completed | 2024-12-27 |  | Integer Infratech Pvt Ltd
16 | 119/2 | DA-3 | Wet Paddy |  | 2024-12-11 |  | Completed | 2024-12-28 |  | Himanshi Agency | Completed | 2024-12-29
17 | 244/6 | DA+3 | Wet |  | 2024-12-13 |  | Completed | 2024-12-23 |  | Unnati Construction | Completed | 2024-12-24
18 | 121/6 | DA+0 | Wet |  | 2024-12-17 |  | Completed | 2024-12-31 |  | Arya Enterprises | Completed | 2025-01-01
19 | 249/1 | DA+9 | Wet Paddy |  | 2024-12-19 |  | Completed | 2024-12-27 |  | Neelkant Infra Project | Completed | 2024-12-28
20 | 119/3 | DA+9 | Wet |  | 2024-12-21 |  | Completed | 2024-12-30 |  | Himanshi Agency | Completed | 2024-12-31
21 | 121/7 | DB1+0 | Wet |  | 2024-12-24 |  | Completed | 2025-01-12 |  | Arya Enterprises | Completed | 2025-01-13
22 | 249/0 | DD60+3 | Wet Paddy |  | 2024-12-26 |  | Completed | 2025-01-02 |  | Unnati Construction | Completed | 2025-01-03
23 | 137/2 | DA-3 | WET |  | 2024-12-27 |  | Completed | 2025-01-10 |  | Adhya Brother
24 | 249/2 | DA+3 | Wet |  | 2024-12-28 |  | Completed | 2025-01-03 |  | Neelkant Infra Project | Completed | 2025-01-04
25 | 145/3 | DA-3 | FS |  | 2024-12-30 |  | Completed | 2025-01-13 |  | Integer Infratech Pvt Ltd | Completed
26 | 121/1 | DB1+25 | WPS |  | 2025-01-03 |  | Completed | 2025-01-10 |  | Himanshi Agency | Completed | 2025-01-11
27 | 244/5 | DA+0 | PS |  | 2025-01-07 |  | Completed | 2025-01-16 |  | Neelkant Infra Project | Completed | 2025-01-17
28 | 250/0 | DD45+3 | PS |  | 2025-01-07 |  | Completed | 2025-01-20 |  | Unnati Construction | Completed | 2025-01-21
29 | 120/7 | DA+3 | WPS |  | 2025-01-10 |  | Completed | 2025-01-14 |  | Himanshi Agency | Completed | 2025-01-15
30 | 121/8 | DA+0 | WET |  | 2025-01-10 |  | Completed | 2025-01-20 |  | Arya Enterprises | Completed | 2025-01-21
31 | 145/2 | DA+0 | WET |  | 2025-01-15 |  | Completed | 2025-01-26 |  | Integer Infratech Pvt Ltd | Completed | 2025-01-27
32 | 137/1 | DA+6 | PS |  | 2025-01-15 |  | Completed | 2025-02-07 |  | Adhya Brother
33 | 252/3 | DA+6 | WET |  | 2025-01-17 |  | Completed | 2025-01-22 |  | Neelkant Infra Project | Completed | 2025-01-23
34 | 136/1 | DB1+9 | WPS |  | 2025-01-19 |  | Completed | 2025-01-24 |  | Himanshi Agency | Completed | 2025-01-25
35 | 250A/2 | DA+0 | WET |  | 2025-01-20 |  | Completed | 2025-01-28 |  | Unnati Construction | Completed | 2025-01-29
36 | 121/9 | DA+0 | PS |  | 2025-01-20 |  | Completed | 2025-02-11 |  | Arya Enterprises | Completed | 2025-02-12
37 | 252/0 | DB2+0 | WET |  | 2025-01-22 |  | Completed | 2025-01-31 |  | Neelkant Infra Project | Completed | 2025-02-01
38 | 141/4 | DA-3 | WET |  | 2025-01-27 |  | Completed | 2025-02-04 |  | Himanshi Agency | Completed
39 | 141/3 | DA+0 | Wet |  | 2025-01-27 |  | Completed | 2025-02-08 |  | Himanshi Agency | Completed | 2025-02-09
40 | 121/10 | DA+0 | Wet |  | 2025-01-28 |  | Completed | 2025-02-04 |  | Arya Enterprises | Completed | 2025-02-05
41 | 145/7 | DB1+0 | Wet |  | 2025-01-28 |  | Completed | 2025-02-08 |  | Integer Infratech Pvt Ltd | Completed | 2025-02-09
42 | 248/2 | DA+6 | Wet |  | 2025-01-29 |  | Completed | 2025-02-03 |  | Unnati Construction | Completed | 2025-02-04
43 | 241/4 | DA+3 | Wet |  | 2025-01-29 |  | Completed | 2025-02-04 |  | Unnati Construction | Completed | 2025-02-05
44 | 124/1 | DA-3 | WPS |  | 2025-01-31 |  | Completed | 2025-02-06 |  | Himanshi Agency | Completed | 2025-02-07
45 | 137/0 | DB2+3 | Wet |  | 2025-02-01 |  | Completed | 2025-02-14 |  | Adhya Brother
46 | 248/1 | DB1+9 | Wet |  | 2025-02-03 |  | Completed | 2025-02-13 |  | Unnati Construction | Completed | 2025-02-14
47 | 243/3 | DA+0 | Wet |  | 2025-02-07 |  | Completed | 2025-02-13 |  | Neelkant Infra Project | Completed | 2025-02-14
48 | 126/1 | DA+3 | WPS |  | 2025-02-07 |  | Completed | 2025-02-13 |  | Himanshi Agency | Completed | 2025-02-14
49 | 124/0 | DD45+3 | Wet |  | 2025-02-07 |  | Completed | 2025-02-19 |  | Himanshi Agency | Completed | 2025-02-20
50 | 148/0 | DD60+25 | Wet |  | 2025-02-07 |  | Completed | 2025-02-27 |  | Himanshi Agency | Completed | 2025-02-28
51 | 141/5 | DA-3 | Wet |  | 2025-02-08 |  | Completed | 2025-02-13 |  | Himanshi Agency | Completed | 2025-02-14
52 | 243/2 | DA+0 | Wet |  | 2025-02-13 |  | Completed | 2025-02-21 |  | Neelkant Infra Project | Completed | 2025-02-22
53 | 250/3 | DA+9 | Wet |  | 2025-02-14 |  | Completed | 2025-02-23 |  | Unnati Construction | Completed | 2025-02-24
54 | 244/1 | DA+0 | FS |  | 2025-02-23 |  | Completed | 2025-03-07 |  | Neelkant Infra Project | Completed | 2025-03-08
55 | 180/4 | DA-3 | Wet |  | 2025-03-01 |  | Completed | 2025-03-27 |  | Jyoti Construction | Completed | 2025-03-28
56 | 132/0 | DB2+0 | FS |  | 2025-03-02 |  | Completed | 2025-03-08 |  | Adhya Brother
57 | 117/1 | DA-3 | WPS |  | 2025-03-03 |  | Completed | 2025-03-13 |  | Himanshi Agency | Completed | 2025-03-14
58 | 117/2 | DA+6 | WPS |  | 2025-03-03 |  | Completed | 2025-03-17 |  | Himanshi Agency | Completed | 2025-03-18
59 | 121/0 | DB2+9 | WBC |  | 2025-03-06 |  | Completed | 2025-03-23 |  | Himanshi Agency | Completed
60 | 172/0 | DD45+9 | Wet |  | 2025-03-07 |  | Completed | 2025-03-26 |  | Himanshi Agency | Completed | 2025-03-27
61 | 251/0 | DD45+0 | WPS |  | 2025-03-11 |  | Completed | 2025-03-20 |  | Neelkant Infra Project | Completed | 2025-03-21
62 | 180/3 | DA+9 | Wet |  | 2025-03-11 |  | Completed | 2025-03-23 |  | Unnati Construction | Completed | 2025-03-24
63 | 179/3 | DA+0 | PS |  | 2025-03-11 |  | Completed | 2025-04-01 |  | Neelkant Infra Project | Completed | 2025-04-02
64 | 180/2 | DB1+3 | PS |  | 2025-03-11 |  | Completed | 2025-04-05 |  | Unnati Construction | Completed | 2025-04-06
65 | 180/5 | DA+3 | PS |  | 2025-03-11 |  | Completed | 2025-04-06 |  | Jyoti Construction | Completed | 2025-04-07
66 | 171/0 | DB1+18 | WPS |  | 2025-03-13 |  | Completed | 2025-03-22 |  | Himanshi Agency | Completed | 2025-03-23
67 | 132/1 | DA-3 | Wet |  | 2025-03-15 |  | Completed | 2025-04-10 |  | Adhya Brother
68 | 174/6 | DA+3 | Wet |  | 2025-03-19 |  | Completed | 2025-04-11 |  | Sai guru Construction | Completed | 2025-04-12
69 | 172/1 | DA+9 | PS |  | 2025-03-24 |  | Completed | 2025-04-01 |  | Himanshi Agency | Completed | 2025-04-02
70 | 165/7 | DA+0 | Wet |  | 2025-03-24 |  | Completed | 2025-04-05 |  | Himanshi Agency | Completed
71 | 165/5 | DA-3 | Wet |  | 2025-03-31 |  | Completed | 2025-05-03 |  | Himanshi Agency | Completed | 2025-05-04
72 | 174/4 | DA+0 | FS |  | 2025-04-01 |  | Completed | 2025-04-10 |  | Himanshi Agency | Completed | 2025-04-11
73 | 179/1 | DA+3 | Wet |  | 2025-04-02 |  | Completed | 2025-04-09 |  | Neelkant Infra Project | Completed | 2025-04-10
74 | 180/7 | DA+0 | WPS |  | 2025-04-03 |  | Completed | 2025-04-08 |  | Jyoti Construction | Completed | 2025-04-09
75 | 174/5 | DA+0 | Wet |  | 2025-04-06 |  | Completed | 2025-04-15 |  | Himanshi Agency | Completed | 2025-04-16
76 | 174/1 | DA+3 | Wet |  | 2025-04-10 |  | Completed | 2025-04-16 |  | Himanshi Agency | Completed | 2025-04-17
77 | 176/1 | DA+0 | FS |  | 2025-04-11 |  | Completed | 2025-04-18 |  | Unnati Construction | Completed | 2025-04-19
78 | 177/0 | DD60+6 | Wet |  | 2025-04-11 |  | Completed | 2025-04-23 |  | Jyoti Construction | Completed
79 | 175/0 | DC2+6 | Wet |  | 2025-04-13 |  | Completed | 2025-04-23 |  | Sai guru Construction | Completed | 2025-04-24
80 | 176/2 | DA-3 | Wet |  | 2025-04-20 |  | Completed | 2025-04-27 |  | Unnati Construction | Completed
81 | 148/4 | DA+3 | PS |  | 2025-04-23 |  | Completed | 2025-04-28 |  | Himanshi Agency | Completed | 2025-04-29
82 | 178/3 | DA-3 | Wet |  | 2025-04-24 |  | Completed | 2025-04-28 |  | Jyoti Construction | Completed
83 | 165/2 | DA+6 | PS |  | 2025-05-02 |  | Completed | 2025-05-15 |  | Himanshi Agency
84 | 252/5 | DB1+9 | FS |  | 2025-05-02 |  | Completed | 2025-05-17 |  | Unnati Construction | Completed
85 | 148/2 | DA+0 | Wet |  | 2025-05-05 |  | Completed | 2025-05-12 |  | Sai guru Construction | Completed | 2025-05-13 | ROW Cleared on 29/04/25
86 | 180/1 | DA+3 | Wet |  | 2025-05-08 |  | Completed | 2025-05-13 |  | Jyoti Construction | Completed | 2025-05-13
87 | 243/0 | DD60+3 | WBC |  | 2025-05-15 |  | Completed | 2025-06-01 |  | Sai guru Construction | Completed | 2025-06-02
88 | 256/0 | DD60+0 | WBC |  | 2025-05-19 |  | Completed | 2025-06-14 |  | Unnati Construction | Completed | 2025-06-16
89 | 246/0 | DD45+9 | PS |  | 2025-08-04 |  | Completed | 2025-08-23 |  | Khodiyarkrupa | Completed
90 | 131/2 | DA+0 | Wet |  | 2025-08-05 |  | Completed | 2025-09-15 |  | Murugan | Completed
91 | 120/1 | DA-3 | Wet Paddy |  | 2025-08-11 |  | Completed | 2025-10-16 |  | Jyoti Construction | Completed
92 | 241/3 | DA+0 | FS |  | 2025-08-14 |  | Completed | 2025-09-20 |  | Saiguru Construction | Completed
93 | 250A/1 | DA+6 | Wet |  | 2025-08-27 |  | Completed | 2025-09-09 |  | Khodiyarkrupa | Completed | 2025-09-10
94 | 178/0 | DD60+6 | WBC |  | 2025-09-23 |  | Completed | 2025-10-14 |  | Khodiyarkrupa | Completed
95 | 119/1 | DA-3 | Wet Paddy |  | 2025-10-12 |  | Completed | 2025-10-20 |  | Jyoti Construction | Completed
96 | 224/1 | DA+3 | WPS |  | 2025-10-12 |  | Completed | 2025-10-19 |  | Himanshi Agency | Completed
97 | 120/4 | DA+0 | wet |  | 2025-10-15 |  | Completed | 2025-10-26 |  | Jyoti Construction | Completed
98 | 224/2 | DB1+6 | WPS |  | 2025-10-15 |  | Completed | 2025-10-20 |  | Khodiyarkrupa | Completed
99 | 225/0 | DB2+0 | WPS |  | 2025-10-15 |  | Completed | 2025-10-22 |  | Khodiyarkrupa | Completed
100 | 223/3 | DA-3 | WPS |  | 2025-10-16 |  | Completed | 2025-10-27 |  | Himanshi Agency | Completed
101 | 221/0 | DD60+18 | WPS |  | 2025-10-21 |  | Completed | 2025-11-05 |  | Khodiyarkrupa | Completed
102 | 224/0 | DC1+0 | WPS |  | 2025-10-26 |  | Completed | 2025-11-08 |  | Himanshi Agency | Completed
103 | 223/1 | DA+0 | Wet |  | 2025-10-26 |  | Completed | 2025-11-14 |  | Tower Foundation | Completed | 2025-11-14
104 | 223/2 | DA+0 | Wet |  | 2025-10-26 |  | Completed | 2025-11-18 |  | Tower Foundation
105 | 220/1 | DA+6 | Wet |  | 2025-10-26 |  | Completed | 2025-11-14 |  | Murugan Gang | Completed | 2025-11-17
106 | 125/1 | DA+9 | wet |  | 2025-10-31 |  | Completed | 2025-11-26 |  | Himanshi Agency
107 | 222/0 | DD60+25 | Wet |  | 2025-11-01 |  | Completed | 2025-11-15 |  | Khodiyarkrupa-1 | Completed | 2025-11-16
108 | 138/0 | DC2+6 | PS |  | 2025-11-03 |  | Completed | 2025-11-13 |  | Jyoti Construction
109 | 185/0 | DD45+25 | Wet |  | 2025-11-03 |  | Completed | 2025-11-16 |  | Khodiyarkrupa-2 | Completed | 2025-11-16
110 | 220/0 | DD45+0 | WPS |  | 2025-11-04 |  | Completed | 2025-11-17 |  | BLG Construction
111 | 144/0 | DD60+18 | WBC |  | 2025-11-04 |  | Completed | 2025-11-24 |  | Jyoti Construction
112 | 136/0 | DD60+6 | FS |  | 2025-11-05 |  | Completed | 2025-11-27 |  | Jyoti Construction
113 | 218/0 | DD60+3 | Wet |  | 2025-11-06 |  | Completed | 2025-11-23 |  | Murugan Gang
114 | 141/6 | DA+3 | Wet |  | 2025-11-10 |  | Completed | 2025-11-17 |  | Himanshi Agency
115 | 196/0 | DB2+18 | PS |  | 2025-11-11 |  | Completed | 2025-11-24 |  | Shivkripa
116 | 186/0 | DC1+18 | Wet |  | 2025-11-11 |  | Completed | 2025-12-01 |  | Khodiyarkrupa-2
117 | 142/0 | DC1+9 | PS |  | 2025-11-11 |  | Completed | 2025-11-25 |  | Himanshi Agency | Completed | 2025-12-13
118 | 223/0 | DC1+6 | WBC |  | 2025-11-12 |  | Completed | 2025-11-22 |  | Sai guru Construction
119 | 214/2 | DA-3 | Wet |  | 2025-11-13 |  | Completed | 2025-11-27 |  | Tuuasta
120 | 187/0 | DC1+0 | Wet |  | 2025-11-16 |  | Completed | 2025-11-26 |  | Khodiyarkrupa-2
121 | 219/1 | DA+9 | WPS |  | 2025-11-18 |  | Completed | 2025-11-21 |  | BLG Construction
122 | 148/5 | DB1+3 | Wet |  | 2025-11-19 |  | Completed | 2025-11-30 |  | Khodiyar Trader
123 | 176/0 | DD45+0 | FS |  | 2025-11-20 |  | Completed | 2025-12-03 |  | Jayesh Electrical
124 | 215/0 | DD60+3 | FS |  | 2025-11-20 |  | Completed | 2025-11-30 |  | Tower Foundation
125 | 214/5 | DA+0 | FS |  | 2025-11-22 |  | Completed | 2025-12-03 |  | Unnati Construction
126 | 225/1 | DA+9 | WPS |  | 2025-11-22 |  | Completed | 2025-11-25 |  | Saiguru Construction
127 | 143/0 | DD60+18 | FS |  | 2025-11-23 |  | Completed | 2025-12-05 |  | Himanshi Agency | Completed | 2025-12-13
128 | 183/1 | DA+0 | FS |  | 2025-11-23 |  | Completed | 2024-12-09 |  | Khodiyarkrupa | Completed | 2025-12-10
129 | 194/1 | DB1+9 | Wet |  | 2025-11-24 |  | Completed | 2025-12-02 |  | Khodiyarkrupa
130 | 214/7 | DA+3 | FS |  | 2025-11-24 |  | Completed | 2025-12-04 |  | BLG Construction
131 | 225/4 | DA+3 | WPS |  | 2025-11-25 |  | Completed | 2025-11-29 |  | Saiguru Construction
132 | 214/4 | DA-3 | FS |  | 2025-11-26 |  | Completed | 2025-12-05 |  | Murugan Gang
133 | 184/0 | DB1+18 | Wet |  | 2025-11-26 |  | Completed | 2025-12-05 |  | Khodiyarkrupa
134 | 161/0 | DB1+3 | PS |  | 2025-11-26 |  | Completed | 2025-12-16 |  | Kasta Bhanjan
135 | 145/5 | DA+3 | PS |  | 2025-11-27 |  | Completed | 2025-12-07 |  | Jyoti Construction
136 | 139/0 | DD45+6 | FS |  | 2025-11-27 |  | Completed | 2025-12-11 |  | Himanshi Agency | Completed | 2025-12-13
137 | 214/3 | DA-3 | PS |  | 2025-11-27 |  | Completed | 2025-12-12 |  | Twasta
138 | 244/2 | DA+0 | Wet |  | 2025-11-30 |  | Completed | 2025-12-06 |  | Saiguru Construction
139 | 183/0 | DD60+0 | PS |  | 2025-11-30 |  | Completed | 2025-12-11 |  | Jayesh Electrical | Completed | 2025-12-12
140 | 182/0 | DD45+0 | WBC |  | 2025-11-30 |  | Completed | 2025-12-14 |  | Dev Construction
141 | 148/3 | DA+6 | Wet |  | 2025-12-01 |  | Completed | 2025-12-11 |  | Khodiyar Trader
142 | 127/2 | DB1+9 | Wet |  | 2025-12-01 |  | Completed | 2025-12-12 |  | Tower Foundation
143 | 128/0 | DD60+25 (2MRC) | Wet |  | 2025-12-04 |  | Completed | 2025-12-31 |  | Tower Foundation
144 | 175/1 | DB1+9 | FS |  | 2025-12-04 |  | Completed | 2025-12-19 |  | Deep Power
145 | 130/0 | DD45+25 (11.9MRC) | WPS |  | 2025-05-10 |  | 16 Pile Boring Done & 16 Pile Concreting done |  |  | Harshvi
146 | 225/3 | DA-3 | WPS |  | 2025-12-05 |  | Completed | 2025-12-10 |  | Velu Construction | Completed | 2025-12-11
147 | 217/4 | DA+9 | Wet |  | 2025-12-05 |  | Completed | 2025-12-11 |  | Selva Murugan
148 | 250/2 | DA+0 | Wet |  | 2025-12-05 |  | Completed | 2025-12-11 |  | Unnati Construction | Completed | 2025-12-12
149 | 214/6 | DA+3 | FS |  | 2025-12-05 |  | Completed | 2025-12-12 |  | BLG Construction
150 | 183/2 | DA+0 | Wet |  | 2025-12-05 |  | Completed | 2025-12-12 |  | Khodiyar Kripa Enterprise
151 | 145/6 | DA+3 | PS |  | 2025-12-05 |  | Completed | 2025-12-18 |  | Jyoti Construction
152 | 217/3 | DA+9 | WPS |  | 2025-12-05 |  | Completed | 2025-12-19 |  | Krishna Construction
153 | 244/0 | DD45+0 | FS |  | 2025-12-05 |  | Completed | 2026-01-09 | Waterlogged | Saiguru 1
154 | 141/1 | DA+0 | PS |  | 2025-12-06 |  | Completed | 2025-12-15 |  | Himanshi Agency
155 | 141/2 | DA+0 | PS |  | 2025-12-06 |  | Completed | 2025-12-19 |  | Himanshi Agency
156 | 127/0 | DB2+0 | WPS |  | 2025-12-08 |  | Done | 2025-12-25 |  | A P Developers
157 | 243/1 | DA+0 | PS |  | 2025-12-08 |  | Completed | 2025-12-16 |  | Saiguru Construction
158 | 166/0 | DD60+0 | WBC |  | 2025-12-08 |  | Completed | 2025-12-20 |  | Jyoti Construction
159 | 135/0 | DD60+3 | WBC |  | 2025-11-04 | Pit C Excavation Done. | Pit C Excavation Done. |  |  | Jyoti Construction 1
160 | 190/0 | DD60+9 | Wet |  | 2025-12-09 |  | Completed | 2025-12-25 |  | Shiv Kripa Infra
161 | 249/3 | DA+3 | Wet |  | 2025-12-10 |  | Completed | 2025-12-13 |  | Saiguru Construction
162 | 225/2 | DA-3 | WPS |  | 2025-12-11 |  | Completed | 2025-12-14 |  | Velu Construction
163 | 189/1 | DA+9 | WPS |  | 2025-12-12 |  | Completed | 2025-12-17 |  | Khodiyarkrupa
164 | 180/6 | DA+0 | PS |  | 2025-12-12 |  | Completed | 2025-12-23 |  | Dev Construction
165 | 139/2 | DB2+0 | Wet |  | 2025-10-26 | Pit A,B & C RCC Chimney Done. | Pit A,B & C RCC Chimney Done. |  | Pit D Canal Water Hinderance. | Jyoti Construction 2
166 | 191/1 | DB1+3 | Wet |  | 2025-12-13 |  | Completed | 2025-12-23 | 189/1 | Khodiyar 1
167 | 139/3 | DB1+0 | FS |  | 2025-12-16 | Excavation U/P | Excavation U/P |  | From 139/3 Approach Road Issue | Himanshi
168 | 140/0 | DD60+25 | WBC |  | 2025-12-22 | Pit B Block Level & Stub Setting Pit B,C Rod Binding Done & Pit B,C Frustum Done | Pit B Block Level & Stub Setting Pit B,C Rod Binding Done & Pit B,C Frustum Done |  |  | Himanshi 1
169 | 199/1 | DA+3 | PS |  | 2025-12-13 |  | Completed | 2025-12-23 |  | Veluu
170 | 183/3 | DA+3 | PS |  | 2025-12-13 | . | Completed | 2025-12-31 |  | Twaasta
171 | 197/0 | DB1+0 | Wet |  | 2025-12-13 |  | Completed | 2025-12-26 |  | Deep Power 1
172 | 197/2 | DA-3 | Wet |  | 2025-12-13 |  | Completed | 2025-12-29 |  | Deep Power 2
173 | 162/0 | DD60+25 | WBC |  | 2025-12-29 |  | Completed | 2026-01-13 |  | Jyoti 3
174 | 210/0 | DB2+9 (2MRC) | PS |  | 2025-12-13 |  | Completed | 2026-01-05 | 2MRC | Velu
175 | 254/1 | DB1+9 | FS |  | 2025-12-13 |  | Completed | 2025-12-24
176 | 173/0 | DC2+18 |  |  | 2025-12-18 | Trial Pit Done. | Trial Pit Done. |  | waterlogged
177 | 217/2 | DA+0 | Wet |  | 2025-12-15 |  | Completed | 2025-12-19
178 | 174/0 | DD60+9 | Wet |  | 2025-12-18 | Pit C,D Frustum Done. | Pit C,D Frustum Done. |  | Raised Chimney | Jyoti 2
179 | 174/2 | DA+0 | PS |  | 2025-12-18 | Trial Pit Done. | Trial Pit Done. |  | Sugarcane Available ROW
180 | 149/0 | DD60+25 | Wet |  | 2025-12-15 |  | Completed | 2026-01-03 |  | Kasta Bhanjan
181 | 257/0 | DC1+9 |  |  | 2025-12-16 |  | Completed | 2025-12-23
182 | 216/1 | DA+9 (2MRC) | Wet |  | 2025-12-16 |  | Completed | 2025-12-24
183 | 127/1 | DA-3 | WPS |  | 2025-12-17 |  | Completed | 2026-01-05 |  | Tower Foundation
184 | 170/0 | DD60+6 | Wet |  | 2025-12-17 |  | Completed | 2025-12-27 |  | Jyoti
185 | 148/1 | DA+3 | Wet |  | 2025-12-18 |  | Completed | 2025-12-25 |  | Khodiyar Traders
186 | 252/2 | DA+3 | PS |  | 2025-12-19 |  | Completed | 2025-12-27
187 | 196/1 | DA+9 | Wet |  | 2025-12-19 |  | Completed | 2025-12-25 |  | BLG Construction
188 | 191/0 | DD60+9 | WPS |  | 2025-12-26 | Pit A Chimney Done & Pit D Chimney Step-1 Done & Pit B,C Chimney Done | Pit A Chimney Done & Pit D Chimney Step-1 Done & Pit B,C Chimney Done |  |  | Khodiyarkrupa
189 | 196/2 | DA+3 | Wet |  | 2025-12-19 |  | Completed | 2025-12-30 | 196/1 | BLG Construction
190 | 252/1 | DA+0 | PS |  | 2025-12-19 |  | Completed | 2025-12-30 |  | Saiguru 2
191 | 139/1 | DA+6 | Wet |  | 2025-12-20 |  | Completed | 2026-01-05 |  | Himanshi
192 | 167/0 | DD60+9 | Wet |  | 2025-12-20 |  | Completed | 2026-01-04 |  | Jyoti 1
193 | 193/0 | DD60+30 |  |  | 2025-12-20 | Pit A,C,D Block Level Done | Pit A,C,D Block Level Done
194 | 165/6 | DCT+0 | Wet |  | 2025-12-20 |  | Completed | 2025-12-23 |  | Jyoti
195 | 255/0 | DD60+0 | FS |  | 2025-12-20 |  | Completed | 2026-01-10 |  | Unnati Construction
196 | 141/0 | DD60+25 | FS |  | 2025-12-21 |  | Completed |  |  | Himanshi 2
197 | 194/0 | DD60+30 | WBC |  | 2025-12-04 | Pit C Pyramid Chimney Done & Pit B Chimney Done & Pit A,D PCC Done & Pit D Frustum Step1,2 Done & Pit A Block level Prop setting Done. | Pit C Pyramid Chimney Done & Pit B Chimney Done & Pit A,D PCC Done & Pit D Frustum Step1,2 Done & Pit A Block level Prop setting Done. |  | Drawing Approval Done | Shiv krupa Infra
198 | 198/0 | DD60+6 | WBC |  | 2025-12-13 | Pit C,D Excavation Done & Pit C Rebar Binding U/P. | Pit C,D Excavation Done & Pit C Rebar Binding U/P. |  |  | Deep Power 2
199 | 199/0 | DD60+6 | PS |  | 2025-12-28 | Pit A,D,C Pyramid Chimney Done & Pit B Steel Binding u/P | Pit A,D,C Pyramid Chimney Done & Pit B Steel Binding u/P |  | Row Mango Tree Leg A,B,C | BLG Construction
200 | 199/2 | DA+6 | PS |  | 2025-12-27 |  | Completed | 2026-01-13 |  | Deep Power
201 | 179/0 | DB1+0 | Wet |  | 2025-12-23 | . | Completed | 2025-12-31 |  | Dev Construction
202 | 178/2 | DA+0 |  |  | 2025-12-23 |  | Completed | 2026-01-07 |  | Dev Contruction
203 | 211/0 | DB2+9 | PS |  | 2026-01-01 | Trial Pit Done. | Trial Pit Done. |  | Sugarcane Available ROW | Deep Power
204 | 216/2 | DB1+18 (2MRC) | PS |  | 2025-12-25 |  | Completed | 2025-12-31 |  | Murgun
205 | 211/1 | DA-3 | Wet |  | 2026-01-08 |  | Completed | 2026-01-13
206 | 192/0 | DC2+9 | Wet |  | 2025-12-26 |  | Completed | 2026-01-06 |  | Khodiyarkrupa
207 | 216/0 | DD60+3 | FS |  | 2025-12-15 | Pit B,D Pyramid Chimney Done & Pit A Block Level Prop Setting Done | Pit B,D Pyramid Chimney Done & Pit A Block Level Prop Setting Done |  |  | Murgun
208 | 216/3 | DA+9 | Wet |  | 2025-12-25 |  | Completed | 2026-01-12 |  | Krishna Construction
209 | 235/3 | DA+0 | PS |  | 2024-08-31 |  | 2 Pit RCC Done Upto Chimney |  |  | Unnati Construction
210 | 126/3 | DA+0 | WPS |  | 2025-12-31 |  | Completed | 2025-01-08 |  | Tower Foundation
211 | 211/3 | DA+9 | PS |  | 2026-01-01 |  | Completed | 2026-01-10 |  | Deep Power 1
212 | 227/0 | DD45+0 |  |  | 2026-01-04 | Pit Marking Done | Pit Marking Done |  |  | Om Enterprise
213 | 227/1 | DA+6 |  |  | 2026-01-04 | Trial Pit Done | Trial Pit Done
214 | 230/0 | DC1+6 | Wet |  | 2026-01-04 |  | Completed | 2026-01-13 |  | Om Enterprise
215 | 126/2 | DA+0 | WPS |  |  |  | Completed | 2025-02-26 |  | Himanshi Agency | Completed | 2025-02-27
216 | 244/3 | DA+3 | PS |  | 2025-12-26 | Pit C,D Pyramid Chimney Done & Pit B Block Level Steel Binding Done | Pit C,D Pyramid Chimney Done & Pit B Block Level Steel Binding Done |  |  | AP Developers
217 | 244/4 | DA+3 | Wet |  | 2025-12-27 | Pit B,D Frustum Done & Pit A Prop Setting Steel Binding Done | Pit B,D Frustum Done & Pit A Prop Setting Steel Binding Done |  |  | AP Developers
218 | 245/0 | DD45+0 | Wet |  | 2026-01-03 |  | Completed | 2026-01-13 | From 245/1 | Saiguru 2
219 | 245/1 | DA+0 | Wet |  | 2026-01-03 | Pit A,B,C,D prop setting & steel binding Done | Pit A,B,C,D prop setting & steel binding Done |  |  | Saiguru 2
220 | 250/1 | DA+9 (1MRC) | PS |  | 2025-12-20 | Pit Marking Done | Pit Marking Done |  | From 244/0 | Saiguru 1
221 | 250A/0 | DB1+3 (3MRC) | FS |  | 2025-12-12 | Pit C,D Block Level Prop Setting Steel Binding Done | Pit C,D Block Level Prop Setting Steel Binding Done |  |  | Unnati Construction
222 | 126/0 | DD45+3 | WPS |  |  |  | Completed | 2025-02-28 |  | Himanshi Agency | Completed | 2025-03-01
223 | 255/1 | DA+0 | [7 empty] | Unnati Construction
224 | 256/1 | DA+9 |  |  | 2025-12-09 | Trial Pit Done. | Trial Pit Done. |  | Waterlogged
224 | 160/0 | DC2+0 | Wet |  | 2026-01-06 | Pit A,D Frustum Done & Pit B,C Pyramid Chimney Done | Pit A,D Frustum Done & Pit B,C Pyramid Chimney Done |  | JYOTI FROM 167/0 | Jyoti
225 | 132/3 | DA-3 | Wet |  | 2026-01-06 |  | Completed | 2026-01-13 | Himanshi | Himanshi
226 | 133/0 | DC1+0 | Wet |  | 2026-01-06 | Pit A,B Steel Binding Done & Pit D Frustum Done | Pit A,B Steel Binding Done & Pit D Frustum Done |  |  | Himanshi
227 | 133/2 | DB1+0 |  |  | 2026-01-06 | Trial Pit Done | Trial Pit Done |  |  | Himanshi
228 | 125/2 | DA+9 | Wet |  | 2026-01-06 | Pit A,B,C,D Frustum Done & Pit A,B Pyramid Chimney Done | Pit A,B,C,D Frustum Done & Pit A,B Pyramid Chimney Done |  |  | Tower Foundation
229 | 178/1 | DA+0 | FS |  | 2026-01-09 | Pit A,B,C Block Level & Prop Setting Done | Pit A,B,C Block Level & Prop Setting Done
230 | 217/5 | DA+0 |  |  | 2026-01-12 | Pit Marking Done | Pit Marking Done
231 | 174/3 | DA+0 | PS |  | 2026-01-13 | Trial Pit Done | Trial Pit Done |  |  | Jyoti 3
232 | 211/2 | DA+0 |  |  | 2026-01-13 | Trial Pit Done | Trial Pit Done
141/6
196/0
186/0
142/0
139/0
145/5
145/6
141/1
141/2
143/0
127/0
127/2
128/0
223/0
214/2
214/3
219/1
215/0
214/5
225/1
214/6
214/7
225/4
214/4
217/3
217/4
225/2
244/2
244/0
161/0
166/0
187/0
148/3
148/5
182/0
183/0
183/1
183/2
184/0
194/1
176/0
175/1
194/0
190/0
243/1
249/3
250/2
225/3
256/1
180/6
250A/0
Formulas:
Earthing Completion Date = [Completion Date]+1

## Sheet5 (hidden)
127/1
135/0
139/1
139/2
139/3
140/0
167/0
173/0
174/0
174/2
178/2
179/0
183/3
191/0
192/0
193/0
194/0
198/0
199/2
210/0
216/0
216/2
216/3
244/3
244/4
250/1
250A/0
255/0
256/1
211/0
162/0
199/0
127/1
128/0
135/0
139/1
139/2
139/3
140/0
141/0
149/0
162/0
167/0
173/0
174/0
174/2
178/2
179/0
183/3
191/0
192/0
193/0
194/0
198/0
199/2
210/0
216/0
216/2
216/3
241/1
244/0
244/3
244/4
250/1
250A/0
255/0
256/1
211/0
199/0

## Sheet3 (hidden)
A
127/2 | 127/2128/0135/0139/0139/2141/1141/2145/5145/6148/3161/0166/0175/1182/0183/0183/1183/3194/0214/3214/6217/4225/3244/0244/2250/2
128/0
135/0
139/0 | 127/2128/0135/0139/0139/2141/1141/2145/5145/6148/3161/0166/0175/1182/0183/0183/1183/3194/0214/3214/6217/4225/3244/0244/2250/2
139/2
141/1
141/2
145/5
145/6
148/3
161/0
166/0
175/1
182/0
183/0
183/1
183/3
194/0
214/3
214/6
217/4
225/3
244/0
244/2
250/2

## Sheet1 (hidden)
District | Till Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25
Bharuch | 14 | 9 | 14 | 4 | 1
Surat |  |  |  | 4 | 17 | 4
Navsari | 4 | 7 | 6 | 2

## Erection Compiled
VNTL Tower Erection
Sl. No. | Location Number | Type of Tower | Starting Date | Tower Weight (MT) | Status | Completion Date | Gang Name | Manpower | Hindarnce Days | Remarks | Tackweldng Status | Tackwelding start date | Tackwelding Completion date | Sub Contractor name
1 | 117/2 | DA+6 | 2025-08-19 | 44.727 | Tower Erection Completed | 2025-08-28 | M/S Sakkurddin | 32
2 | 118/0 | DB2+0 | 2025-05-31 | 54.405 | Tower Erection Completed | 2025-06-15 | M/s MGR | 24
3 | 119/0 | DD60+0 | 2025-08-10 | 80.243 | Tower Erection Completed | 2025-08-30 | M/S Midhun | 42
4 | 119/2 | DA-3 | 2025-08-07 | 36.043 | Tower Erection Completed | 2025-08-14 | M/S Sakkurddin | 32
5 | 119/3 | DA+9 | 2025-07-26 | 46.622 | Tower Erection Completed | 2025-08-05 | M/S Sakkurddin | 32
6 | 120/7 | DA+3 | 2025-12-28 | 37.729 | Tower Erection Completed | 2026-01-09 | Subhash | 26
7 | 120/2 | DA+0 | 2025-06-02 | 37.729 | Tower Erection Completed | 2025-06-07 | M/S Rahul | 26
8 | 120/3 | DA+6 | 2025-06-09 | 44.727 | Tower Erection Completed | 2025-06-14 | M/S Rahul | 26
9 | 120/4 | DA+0 | 2025-12-28 | 34.7046 | Tower Erection Completed | 2026-01-02 | Subhash | 26
10 | 120/5 | DA-3 | 2025-12-08 | 36.043 | Tower Erection Completed | 2025-12-27 | Subhash Kumar | 26
11 | 120/6 | DA+0 | 2025-06-16 | 37.729 | Tower Erection Completed | 2025-06-29 | M/S Rahul | 26
12 | 121/10 | DA+0 | 2025-09-08 | 37.729 | Tower Erection Completed | 2025-09-18 | M/S Sakkurddin | 32
62 | 119/1 | DA-3 | 2026-01-09 | 37.729 | Cage Section U/P |  | Subhash | 26 |  | 117/1
63 | 121/4 | DA+0 | 2024-03-27 | 37.729 | Tower Erection Completed | 2025-04-01 | M/S Gauri Shankar | 28
64 | 121/7 | DB1+0 | 2025-09-15 | 55.045 | Tower Erection Completed | 2025-10-01 | M/S Midhun | 42
65 | 121/2 | DA+9 | 2025-12-30 | 45.0419 | Middle Section U/P |  | Modina India 2 | 20
66 | 131/2 | DA+0 | 2025-12-15 | 37.729 | Tower Erection Completed | 2025-12-20 | Rahul Kumar | 33
67 | 132/0 | DB2+0 | 2025-12-08 |  | Tower Erection Completed | 2025-12-15 | Rahul Kumar | 22
68 | 136/1 | DB1+9 | 2025-12-20 | 62.9457 | Tower Erection Completed | 2025-12-28 | Rahul Kumar | 24
69 | 137/2 | DA-3 | 2025-12-28 | 34.705 | Tower Erection Completed | 2026-01-04 | Rahul Kumar
70 | 141/1 | DA+0 | 2025-12-25 | 37.729 | Tower Erection Completed | 2025-12-31 | Srvan Kumar | 18
71 | 141/2 | DA+0 | 2026-01-02 | 34.7046 | Tower Erection Completed | 2026-01-04 | Srvan Kumar ( Dhirendra Kumar Verma) | 18
72 | 141/6 | DA+3 | 2025-12-04 | 38.0377 | Tower Erection Completed | 2025-12-19 | Chitra Construction | 23
73 | 126/1 | DA+3 | 2025-12-30 | 38.0377 | Top Section U/P |  | Modina India 3 | 23
74 | 145/5 | DA+3 | 2025-12-28 | 38.0377 | Tower Erection Completed | 2026-01-04 | Anannya Traders | 35
75 | 148/2 | DA+0 | 2025-12-06 | 37.729 | Tower Erection Completed | 2025-12-20 | Zakir Hussain | 25
76 | 148/4 | DA+3 | 2025-12-20 | 38.0377 | Tower Erection Completed | 2026-01-06 | Jabir Hussian | 21
77 | 175/1 | DB1+9 | 2025-12-28 | 62.9457 | Tower Erection Completed | 2026-01-06 | Sakila Khatun | 35
78 | 176/0 | DD45+0 | 2025-12-21 | 69.2873 | Tower Erection Completed | 2025-12-28 | Sakhila Khatun | 23
79 | 179/1 | DA+3 | 2025-12-08 | 38.0377 | Tower Erection Completed | 2025-12-12 | Sakhila Khatun | 24
80 | 141/3 | DA+0 | 2026-01-04 | 37.729 | Tower Erection Completed | 2026-01-09 | DK Construction (sarvan Kumar) | 18
81 | 137/0 | DB2+3 | 2026-01-04 |  | Tower Erection Completed | 2026-01-12 | Rahul Kumar | 24
82 | 180/5 | DA+3 | 2025-12-17 | 38.0377 | Tower Erection Completed | 2025-12-29 | Md. Emdadul Hoque | 19
83 | 145/6 | DA+3 | 2026-01-04 | 38.0377 | Tower Erection Completed | 2026-01-09 | Anannya Traders | 35
84 | 187/0 | DC1+0 | 2025-12-11 | 61.5512 | Tower Erection Completed | 2025-12-20 | Sakhila Khatun | 35
85 | 241/0 | DD60+0 | 2025-09-02 | 80.243 | Tower Erection Completed | 2025-09-15 | M/S Israul Hoque | 38
86 | 241/4 | DA+3 | 2025-12-06 | 38.0377 | Tower Erection Completed | 2025-12-19 | Sk Samirul | 23
87 | 243/0 | DD60+3 | 2025-11-30 | 84.299 | Tower Erection Completed | 2025-12-25 | Anjum Construction | 22
63 | 138/0 | DC2+6 | 2026-01-12 |  | 1st Section U/P |  | Rahul Kumar | 24
64 | 243/2 | DA+0 | 2025-12-19 | 37.729 | Tower Erection Completed | 2025-12-29 | Sk Samiul ( Sima Khatun) | 23
65 | 244/1 | DA+0 | 2025-12-04 | 37.729 | Tower Erection Completed | 2025-12-13 | Pramod Kumar | 35
66 | 244/5 | DA+0 | 2025-12-14 | 37.729 | Tower Erection Completed | 2025-12-23 | Ranjan Kumar | 35
64 | 141/5 | DA-3 | 2026-01-09 | 37.729 | Tower Erection Completed | 2026-01-13 | DK Construction (sarvan Kumar) | 18
65 | 142/0 | DC1+9 | 2025-12-19 | 74.4389 | Cage Section U/P |  | Chitra Construction | 23
64 | 143/0 | DD60+18 | 2026-01-13 |  | Leg Erection U/P |  | DK Construction (sarvan Kumar) | 18
65 | 249/3 | DA+3 | 2025-12-24 | 38.0377 | Tower Erection Completed | 2026-01-04 | Mithun Kumar | 20
66 | 250/3 | DA+9 | 2025-12-23 | 45.0419 | Tower Erection Completed | 2026-01-03 | Ranjan Kumar | 35
63 | 145/4 | DA+0 | 2026-01-09 | 37.729 | Tower Erection Completed | 2026-01-15 | Anannya Traders | 35
55 | 148/3 | DA+6 | 2026-01-06 | 44.727 | Middle Section U/P |  | Jabir Hussian | 21
53 | 175/0 | DC2+6 | 2026-01-06 |  | Top Section U/P |  | Sakila Khatun | 35 |  |  | 12.39
54 | 180/3 | DA+9 | 2025-12-29 | 45.0419 | 2nd Section U/P |  | Dildar Electrical 1 | 22
55 | 180/4 | DA-3 | 2025-12-30 | 37.729 | Top Section Done |  | Modina India 1 | 22
54 | 180/6 | DA+0 | 2026-01-06 | 37.729 | Middle Section U/P |  | TAFIJUL SK | 20
55 | 182/0 | DD45+0 | 2026-01-03 |  | 2nd Section U/P |  | Dildar Electrical 2 | 20
62 | 183/0 | DD60+0 | 2026-01-11 |  | 1st Section U/P |  | Prayag Mahto | 19
63 | 243/1 | DA+0 | 2025-12-29 | 34.7046 | 3rd Section U/P |  | Anjum Construction | 22 |  | 244/2
64 | 250A/2 | DA+0 | 2026-01-04 | 37.729 | Tower Erection Completed | 2026-01-13 | Mithun Kumar | 20
65 | 246/0 | DD45+9 | 2026-01-03 |  | 3rd Section Done |  | Ranjan Kumar | 35
66 | 248/1 | DB1+9 | 2025-12-26 | 62.9457 | Tower Erection Completed | 2026-01-14 | Sk Samiul ( Sima Khatun) | 23
67 | 248/2 | DA+6 | 2025-09-11 | 44.727 | Middle Section Underprogress
65 | 250A/1 | DA+6 | 2026-01-13 | 44.727 | Leg Erection U/P |  | Mithun Kumar | 20
66 | 252/5 | DB1+9 | 2026-01-02 | 62.9457 | 3rd Section Done |  | Crestless Wave Trading (OPC) | 35
67 | 241/2 | DA+0 | 2026-01-14 | 34.7046 | Material Shifting & Segregation U/P |  | Sk Samiul ( Sima Khatun) | 23
68 | 145/3 | DA-3 | 2026-01-15 | 37.729 | Material Shifting & Segregation U/P |  | Anannya Traders | 35

## Sheet4 (hidden)
|  | 117/1 | 117/2 | 118/0 | 119/0 | 119/1 | 119/2 | 119/3 | 120/0 | 120/1 | 120/2 | 120/3 | 120/4 | 120/5 | 120/6 | 120/7 | 121/0 | 121/1 | 121/2 | 121/3 | 121/4 | 121/5 | 121/6 | 121/7 | 121/8 | 121/9 | 121/10 | 121/11 | 124/0 | 124/1 | 124/2 | 124/3 | 125/0 | 125/1 | 125/2 | 126/0 | 126/1 | 126/2 | 126/3 | 127/0 | 127/1 | 127/2 | 128/0 | 129/0 | 130/0 | 131/0 | 131/1 | 131/2 | 131/3 | 131/4 | 131/5 | 132/0 | 132/1 | 132/2 | 132/3 | 133/0 | 133/1 | 133/2 | 133/3 | 133/4 | 134/0 | 135/0 | 136/0 | 136/1 | 137/0 | 137/1 | 137/2 | 138/0 | 139/0 | 139/1 | 139/2 | 139/3 | 140/0 | 141/0 | 141/1 | 141/2 | 141/3 | 141/4 | 141/5 | 141/6 | 142/0 | 143/0 | 144/0 | 145/0 | 145/1 | 145/2 | 145/3 | 145/4 | 145/5 | 145/6 | 145/7 | 147/0 | 148/0 | 148/1 | 148/2 | 148/3 | 148/4 | 148/5 | 149/0 | 150/0 | 150/1 | 151/0 | 151A/0 | 152/0 | 153/0 | 153/1 | 153/2 | 153A/0 | 154/0 | 155/0 | 156/0 | 156/1 | 157/0 | 158/0 | 159/0 | 160/0 | 161/0 | 162/0 | 163/0 | 163/1 | 164/0 | 165/0 | 165/1 | 165/2 | 165/3 | 165/4 | 165/5 | 165/6 | 165/7 | 166/0 | 167/0 | 168/0 | 169/0 | 170/0 | 171/0 | 172/0 | 172/1 | 173/0 | 174/0 | 174/1 | 174/2 | 174/3 | 174/4 | 174/5 | 174/6 | 175/0 | 175/1 | 176/0 | 176/1 | 176/2 | 177/0 | 178/0 | 178/1 | 178/2 | 178/3 | 179/0 | 179/1 | 179/2 | 179/3 | 180/0 | 180/1 | 180/2 | 180/3 | 180/4 | 180/5 | 180/6 | 180/7 | 182/0 | 183/0 | 183/1 | 183/2 | 183/3 | 184/0 | 185/0 | 186/0 | 187/0 | 188/0 | 189/0 | 189/1 | 190/0 | 191/0 | 191/1 | 192/0 | 193/0 | 194/0 | 194/1 | 195/0 | 196/0 | 196/1 | 196/2 | 197/0 | 197/1 | 197/2 | 198/0 | 199/0 | 199/1 | 199/2 | 200/0 | 200/1 | 201/0 | 202/0 | 203/0 | 203/1 | 204/0 | 205/0 | 205/1 | 205/2 | 206/0 | 206/1 | 207/0 | 208/0 | 209/0 | 209/1 | 209/2 | 210/0 | 211/0 | 211/1 | 211/2 | 211/3 | 211/4 | 211/5 | 212/0 | 213/0 | 214/0 | 214/1 | 214/2 | 214/3 | 214/4 | 214/5 | 214/6 | 214/7 | 215/0 | 216/0 | 216/1 | 216/2 | 216/3 | 217/0 | 217/1 | 217/2 | 217/3 | 217/4 | 217/5 | 218/0 | 219/0 | 219/1 | 220/0 | 220/1 | 221/0 | 222/0 | 223/0 | 223/1 | 223/2 | 223/3 | 224/0 | 224/1 | 224/2 | 225/0 | 225/1 | 225/2 | 225/3 | 225/4 | 225/5 | 225/6 | 225/7 | 226/0 | 226/1 | 226/2 | 226/3 | 227/0 | 227/1 | 227/2 | 228/0 | 228/1 | 229/0 | 229/1 | 229A/0 | 229B/0 | 230/0 | 230/1 | 230A/0 | 231/0 | 232/0 | 232/1 | 232/2 | 232/3 | 232/4 | 233/0 | 234/0 | 235/0 | 235/1 | 235/2 | 235/3 | 235/4 | 236/0 | 237/0 | 238/0 | 239/0 | 239/1 | 240/0 | 240/1 | 241/0 | 241/1 | 241/2 | 241/3 | 241/4 | 242/0 | 243/0 | 243/1 | 243/2 | 243/3 | 244/0 | 244/1 | 244/2 | 244/3 | 244/4 | 244/5 | 244/6 | 245/0 | 245/1 | 246/0 | 247/0 | 248/0 | 248/1 | 248/2 | 249/0 | 249/1 | 249/2 | 249/3 | 250/0 | 250/1 | 250/2 | 250/3 | 250A/0 | 250A/1 | 250A/2 | 251/0 | 251/1 | 252/0 | 252/1 | 252/2 | 252/3 | 252/4 | 252/5 | 253/0 | 254/0 | 254/1 | 255/0 | 255/1 | 256/0 | 256/1 | 257/0 | 258/0
|  | DA-3 | DA+6 | DB2+0 | DD60+0 | DA-3 | DA-3 | DA+9 | DD60+3 | DA-3 | DA+0 | DA+6 | DA+0 | DA-3 | DA+0 | DA+3 | DB2+9 | DB1+25 | DA+9 | DA+0 | DA+0 | DA-3 | DA+0 | DB1+0 | DA+0 | DA+0 | DA+0 | DA+9 | DD45+3 | DA-3 | DA+0 | DA+0 | DC2+3 | DA+9 | DA+9 | DD45+3 | DA+3 | DA+0 | DA+0 | DB2+0 | DA-3 | DB1+9 | DD60+25 (2MRC) | DD45+25 (15.87MRC) | DD45+25 (11.9MRC) | DD60+9 (7MRC) | DA+3 | DA+0 | DA+3 | DA-3 | DA-3 | DB2+0 | DA-3 | DA-3 | DA-3 | DC1+0 | DA+0 | DB1+0 | DB1+0 | DA+3 | DD45+0 | DD60+3 | DD60+6 | DB1+9 | DB2+3 | DA+6 | DA-3 | DC2+6 | DD45+6 | DA+6 | DB2+0 | DB1+0 | DD60+25 | DD60+25 | DA+0 | DA+0 | DA+0 | DA-3 | DA-3 | DA+3 | DC1+9 | DD60+18 | DD60+18 | DD45+9 | DA+0 | DA+0 | DA-3 | DA+0 | DA+3 | DA+3 | DB1+0 | DD60+25 | DD60+25 | DA+3 | DA+0 | DA+6 | DA+3 | DB1+3 | DD60+25 | DD60+25 | DB1+0 | DD60+6 | DD60+18 | DD60+3 | DD60+3 | DA+3 | DA+0 | DD45+9 | DD60+9 | DD60+18 | DD45+18 | DB2+9 | DD60+41 | DD60+41 | DD60+9 (2MRC) | DC2+0 | DB1+3 | DD60+25 | DD60+30 | DB1+6 | DC2+6 | DB1+25 | DA+9 | DA+6 | DA+6 | DA-3 | DA-3 | DCT+0 | DA+0 | DD60+0 | DD60+9 | DD60+30 | DD60+25 | DD60+6 | DB1+18 | DD45+9 | DA+9 | DC2+18 | DD60+9 (2MRC) | DA+3 | DA+0 | DA+0 | DA+0 | DA+0 | DA+3 | DC2+6 | DB1+9 | DD45+0 | DA+0 | DA-3 | DD60+6 | DD60+6 | DA+0 | DA+0 | DA-3 | DB1+0 | DA+3 | DA+3 (A,B 1.5 RC) | DA+0 | DD45+0LE (3 Leg)+1.5LE (1 Leg) & (B1MRC & C0.5MRS) | DA+3 | DB1+3 | DA+9 | DA-3 | DA+3 | DA+0 | DA+0 | DD45+0 | DD60+0 | DA+0 | DA+0 | DA+3 | DB1+18 | DD45+25 | DC1+18 | DC1+0 | DD60+35 | DD60+35 | DA+9 | DD60+9 | DD60+9 | DB1+3 | DC2+9 | DD60+30 | DD60+30 | DB1+9 | DC1+18 | DB2+18 | DA+9 | DA+3 | DB1+0 | DA-3 | DA-3 | DD60+6 | DD60+6 | DA+3 | DA+6 | DC2+0 | DA+6 | DC1+9 | DC1+18 | DC1+18 | DB1+0 | DD60+25 (2MRC) | DD60+25 (3MRC) | DB2+9 | DA+9 | DC2+0 | DB1+6 | DD60+25 | DD45+35 | DD60+9 | DA+0 | DA-3 | DB2+9 (2MRC) | DB2+9 | DA-3 | DA+0 | DA+9 | DA-3 | DB1+9 | DD45+30 (2MRC) | DD60+35 | DD60+25 | DA+6 | DA-3 | DA-3 | DA-3 | DA+0 | DA+3 | DA+3 | DD60+3 | DD60+3 | DA+9 (2MRC) | DB1+18 (2MRC) | DA+9 | DC2+9 | DA+3 | DA+0 | DA+9 | DA+9 | DA+0 | DD60+3 | DD45+3 | DA+9 | DD45+0 | DA+6 | DD60+18 | DD60+25 | DC1+6 | DA+0 | DA+0 | DA-3 | DC1+0 | DA+3 | DB1+6 | DB2+0 | DA+9 | DA-3 | DA-3 | DA+3 | DA+0 | DA+0 | DA+6 | DB2+3 | DA+6 | DA+0 | DA+0 | DD45+0 | DA+6 | DA+3 | DD45+0 | DA+0 | DD45+0 | DA+9 | DB1+25 | DB2+25 | DC1+6 | DA+9 | DD45+0 | DB1+0 | DB1+0 | DA+0 | DA+0 | DA+0 | DA+3 | DC1+0 | DD60+18 | DD60+9 (2MRC) | DA+9 | DA+0 | DA+0 | DA+3 | DB2+18 | DB1+25 (2MRC) | DC1+25 | DD45+0 | DA+0 | DB2+0 | DA+3 | DD60+0 | DA+0 | DA+0 | DA+0 | DA+3 | DD60+3 | DD60+3 | DA+0 | DA+0 | DA+0 | DD45+0 | DA+0 | DA+0 | DA+3 | DA+3 | DA+0 | DA+3 | DD45+0 | DA+0 | DD45+9 | DD60+35 (2MRC) | DD60+35 (2MRC) | DB1+9 | DA+6 | DD60+3 | DA+9 | DA+3 | DA+3 | DD45+3 | DA+9 (1MRC) | DA+0 | DA+9 | DB1+3 (3MRC) | DA+6 | DA+0 | DD45+0 | DA+6 (1MRC) | DB2+0 | DA+0 | DA+3 | DA+6 | DA+0 | DB1+9 | DD45+35 (2MRC) | DD45+35 (2MRC) | DB1+9 | DD60+0 | DA+0 | DD60+0 | DA+9 | DC1+9 | DD60+0 (1.5MRC)
Loc No | Tower Type
117/1 | DA-3
117/2 | DA+6
118/0 | DB2+0
119/0 | DD60+0
119/1 | DA-3
119/2 | DA-3
119/3 | DA+9
120/0 | DD60+3
120/1 | DA-3
120/2 | DA+0
120/3 | DA+6
120/4 | DA+0
120/5 | DA-3
120/6 | DA+0
120/7 | DA+3
121/0 | DB2+9
121/1 | DB1+25
121/2 | DA+9
121/3 | DA+0
121/4 | DA+0
121/5 | DA-3
121/6 | DA+0
121/7 | DB1+0
121/8 | DA+0
121/9 | DA+0
121/10 | DA+0
121/11 | DA+9
124/0 | DD45+3
124/1 | DA-3
124/2 | DA+0
124/3 | DA+0
125/0 | DC2+3
125/1 | DA+9
125/2 | DA+9
126/0 | DD45+3
126/1 | DA+3
126/2 | DA+0
126/3 | DA+0
127/0 | DB2+0
127/1 | DA-3
127/2 | DB1+9
128/0 | DD60+25 (2MRC)
129/0 | DD45+25 (15.87MRC)
130/0 | DD45+25 (11.9MRC)
131/0 | DD60+9 (7MRC)
131/1 | DA+3
131/2 | DA+0
131/3 | DA+3
131/4 | DA-3
131/5 | DA-3
132/0 | DB2+0
132/1 | DA-3
132/2 | DA-3
132/3 | DA-3
133/0 | DC1+0
133/1 | DA+0
133/2 | DB1+0
133/3 | DB1+0
133/4 | DA+3
134/0 | DD45+0
135/0 | DD60+3
136/0 | DD60+6
136/1 | DB1+9
137/0 | DB2+3
137/1 | DA+6
137/2 | DA-3
138/0 | DC2+6
139/0 | DD45+6
139/1 | DA+6
139/2 | DB2+0
139/3 | DB1+0
140/0 | DD60+25
141/0 | DD60+25
141/1 | DA+0
141/2 | DA+0
141/3 | DA+0
141/4 | DA-3
141/5 | DA-3
141/6 | DA+3
142/0 | DC1+9
143/0 | DD60+18
144/0 | DD60+18
145/0 | DD45+9
145/1 | DA+0
145/2 | DA+0
145/3 | DA-3
145/4 | DA+0
145/5 | DA+3
145/6 | DA+3
145/7 | DB1+0
147/0 | DD60+25
148/0 | DD60+25
148/1 | DA+3
148/2 | DA+0
148/3 | DA+6
148/4 | DA+3
148/5 | DB1+3
149/0 | DD60+25
150/0 | DD60+25
150/1 | DB1+0
151/0 | DD60+6
151A/0 | DD60+18
152/0 | DD60+3
153/0 | DD60+3
153/1 | DA+3
153/2 | DA+0
153A/0 | DD45+9
154/0 | DD60+9
155/0 | DD60+18
156/0 | DD45+18
156/1 | DB2+9
157/0 | DD60+41
158/0 | DD60+41
159/0 | DD60+9 (2MRC)
160/0 | DC2+0
161/0 | DB1+3
162/0 | DD60+25
163/0 | DD60+30
163/1 | DB1+6
164/0 | DC2+6
165/0 | DB1+25
165/1 | DA+9
165/2 | DA+6
165/3 | DA+6
165/4 | DA-3
165/5 | DA-3
165/6 | DCT+0
165/7 | DA+0
166/0 | DD60+0
167/0 | DD60+9
168/0 | DD60+30
169/0 | DD60+25
170/0 | DD60+6
171/0 | DB1+18
172/0 | DD45+9
172/1 | DA+9
173/0 | DC2+18
174/0 | DD60+9 (2MRC)
174/1 | DA+3
174/2 | DA+0
174/3 | DA+0
174/4 | DA+0
174/5 | DA+0
174/6 | DA+3
175/0 | DC2+6
175/1 | DB1+9
176/0 | DD45+0
176/1 | DA+0
176/2 | DA-3
177/0 | DD60+6
178/0 | DD60+6
178/1 | DA+0
178/2 | DA+0
178/3 | DA-3
179/0 | DB1+0
179/1 | DA+3
179/2 | DA+3 (A,B 1.5 RC)
179/3 | DA+0
180/0 | DD45+0LE (3 Leg)+1.5LE (1 Leg) & (B1MRC & C0.5MRS)
180/1 | DA+3
180/2 | DB1+3
180/3 | DA+9
180/4 | DA-3
180/5 | DA+3
180/6 | DA+0
180/7 | DA+0
182/0 | DD45+0
183/0 | DD60+0
183/1 | DA+0
183/2 | DA+0
183/3 | DA+3
184/0 | DB1+18
185/0 | DD45+25
186/0 | DC1+18
187/0 | DC1+0
188/0 | DD60+35
189/0 | DD60+35
189/1 | DA+9
190/0 | DD60+9
191/0 | DD60+9
191/1 | DB1+3
192/0 | DC2+9
193/0 | DD60+30
194/0 | DD60+30
194/1 | DB1+9
195/0 | DC1+18
196/0 | DB2+18
196/1 | DA+9
196/2 | DA+3
197/0 | DB1+0
197/1 | DA-3
197/2 | DA-3
198/0 | DD60+6
199/0 | DD60+6
199/1 | DA+3
199/2 | DA+6
200/0 | DC2+0
200/1 | DA+6
201/0 | DC1+9
202/0 | DC1+18
203/0 | DC1+18
203/1 | DB1+0
204/0 | DD60+25 (2MRC)
205/0 | DD60+25 (3MRC)
205/1 | DB2+9
205/2 | DA+9
206/0 | DC2+0
206/1 | DB1+6
207/0 | DD60+25
208/0 | DD45+35
209/0 | DD60+9
209/1 | DA+0
209/2 | DA-3
210/0 | DB2+9 (2MRC)
211/0 | DB2+9
211/1 | DA-3
211/2 | DA+0
211/3 | DA+9
211/4 | DA-3
211/5 | DB1+9
212/0 | DD45+30 (2MRC)
213/0 | DD60+35
214/0 | DD60+25
214/1 | DA+6
214/2 | DA-3
214/3 | DA-3
214/4 | DA-3
214/5 | DA+0
214/6 | DA+3
214/7 | DA+3
215/0 | DD60+3
216/0 | DD60+3
216/1 | DA+9 (2MRC)
216/2 | DB1+18 (2MRC)
216/3 | DA+9
217/0 | DC2+9
217/1 | DA+3
217/2 | DA+0
217/3 | DA+9
217/4 | DA+9
217/5 | DA+0
218/0 | DD60+3
219/0 | DD45+3
219/1 | DA+9
220/0 | DD45+0
220/1 | DA+6
221/0 | DD60+18
222/0 | DD60+25
223/0 | DC1+6
223/1 | DA+0
223/2 | DA+0
223/3 | DA-3
224/0 | DC1+0
224/1 | DA+3
224/2 | DB1+6
225/0 | DB2+0
225/1 | DA+9
225/2 | DA-3
225/3 | DA-3
225/4 | DA+3
225/5 | DA+0
225/6 | DA+0
225/7 | DA+6
226/0 | DB2+3
226/1 | DA+6
226/2 | DA+0
226/3 | DA+0
227/0 | DD45+0
227/1 | DA+6
227/2 | DA+3
228/0 | DD45+0
228/1 | DA+0
229/0 | DD45+0
229/1 | DA+9
229A/0 | DB1+25
229B/0 | DB2+25
230/0 | DC1+6
230/1 | DA+9
230A/0 | DD45+0
231/0 | DB1+0
232/0 | DB1+0
232/1 | DA+0
232/2 | DA+0
232/3 | DA+0
232/4 | DA+3
233/0 | DC1+0
234/0 | DD60+18
235/0 | DD60+9 (2MRC)
235/1 | DA+9
235/2 | DA+0
235/3 | DA+0
235/4 | DA+3
236/0 | DB2+18
237/0 | DB1+25 (2MRC)
238/0 | DC1+25
239/0 | DD45+0
239/1 | DA+0
240/0 | DB2+0
240/1 | DA+3
241/0 | DD60+0
241/1 | DA+0
241/2 | DA+0
241/3 | DA+0
241/4 | DA+3
242/0 | DD60+3
243/0 | DD60+3
243/1 | DA+0
243/2 | DA+0
243/3 | DA+0
244/0 | DD45+0
244/1 | DA+0
244/2 | DA+0
244/3 | DA+3
244/4 | DA+3
244/5 | DA+0
244/6 | DA+3
245/0 | DD45+0
245/1 | DA+0
246/0 | DD45+9
247/0 | DD60+35 (2MRC)
248/0 | DD60+35 (2MRC)
248/1 | DB1+9
248/2 | DA+6
249/0 | DD60+3
249/1 | DA+9
249/2 | DA+3
249/3 | DA+3
250/0 | DD45+3
250/1 | DA+9 (1MRC)
250/2 | DA+0
250/3 | DA+9
250A/0 | DB1+3 (3MRC)
250A/1 | DA+6
250A/2 | DA+0
251/0 | DD45+0
251/1 | DA+6 (1MRC)
252/0 | DB2+0
252/1 | DA+0
252/2 | DA+3
252/3 | DA+6
252/4 | DA+0
252/5 | DB1+9
253/0 | DD45+35 (2MRC)
254/0 | DD45+35 (2MRC)
254/1 | DB1+9
255/0 | DD60+0
255/1 | DA+0
256/0 | DD60+0
256/1 | DA+9
257/0 | DC1+9
258/0 | DD60+0 (1.5MRC)

## String
VNTL Stringing
Sr. No. | Section | length | Manual/TSE | Engaged Date | Paying Out |  | Final Sag |  | P/O Completed | F/S Completed | Stringing Status As on Today | Cumulative Status | Sub Contractor name | Manpower | Hindarnce Days | Remarks
[5 empty] | Start Date | End Date | Start Date | End Date

## Visual chart 1
Visual Chart | [31 empty] | 2026-01-14
Name of the Line : |  |  |  | 765 kV D/C Vataman - Navsari Transmission Line | [17 empty] | Completed
Name of Project: |  |  |  | Powergrid Vataman Transmission Limited | [17 empty] | DS (Aprd) | CS (Aprd) | SOIL INVSTGN | FOUNDATION |  |  | TOWER ERECTION |  |  |  | TW | TIG & PUN | STR P/O | STR F/S | OPGW STR
Name of Contractor: |  |  |  | KEC International Limited
[25 empty] | TOTAL | COMP. | BAL. | EAR | TOTAL | COMP. | BAL.
PROGRESS AT A GLANCE : | [10 empty] | CROSSING PROPOSAL STATUS :
Sl. No. | Activity |  |  | UoM | Total Qty |  | Completed Till Date |  | Balance |  | Sl. No. | Type of Crossing |  |  |  | No. of X-ing |  | Approved |  | Balance
1 | Detailed Survey |  |  | Kms | 127.8541 |  | 127.8541 |  | 0 |  | 1 | Powerline X-ing |  |  |  | 48 |  | 43 |  | 5
2 | Check Survey |  |  | Kms | 127.8541 |  | 127.8541 |  | 0 |  | TRUE | 66 kV |  |  |  | 18 |  | 17 |  | 1
3 | Soil Investigation |  |  | Nos. | 28 |  | 28 |  | 0 |  | TRUE | 132 kV |  |  |  | 2 |  | 2 |  | 0
4 | Foundation |  |  | Nos. | 351 |  | 200 |  | 151 |  | TRUE | 220 kV |  |  |  | 15 |  | 13 |  | 2
5 | Earthing |  |  | Nos. | 351 |  | 163 |  | 188 |  | TRUE | 400 kV &765 kV |  |  |  | 13 |  | 11 |  | 2
6 | Erection |  |  | Nos. | 351 |  | 44 |  | 307 |  | 2 | RLY X-ING |  |  |  | 4 |  | 2 |  | 2
7 | Tack Welding |  |  | Nos. | 351 | [5 empty] | 3 | NH X-ING |  |  |  | 3 |  | 3 |  | 0
8 | Stringing (P/O) |  |  | Kms | 127.8541 | [5 empty] | 4 | Bullet Train |  |  |  | 2 |  | 2 |  | 0
9 | Stringing (F/S) |  |  | Kms | 127.8541 | [5 empty] | 5 | Express-way |  |  |  | 4 |  | 4 |  | 0
10 | OPGW Stringing |  |  | Kms | 127.8541 | [5 empty] | 6 | GAS PIPELINE |  |  |  | 6 |  |  |  | 6
[22 empty] | 3.516 | 3.516 |  | 9 | 9 | 0 | 7 | 9 | 5 | 4
BHARUCH DISTRICT FROM 117/0 - 148/0, 92 Locations (Length 34.264 Kms)
| 117/0 |  | 117/1 |  | 117/2 |  | 118/0 |  | 119/0 |  | 119/1 |  | 119/2 |  | 119/3 |  | 120/0 |  | 120/1
| KPIL Tower | 347 |  | 352 |  | 443.762 |  | 243.824 |  | 339.414 |  | 316 |  | 408 |  | 358.181 |  | 358.819 |  | 349 | 3516
|  |  | DA-3 |  | DA+6 |  | DB2+0 |  | DD60+0 |  | DA-3 |  | DA-3 |  | DA+9 |  | DD60+3 |  | DA-3
|  |  | Material Shifted | [18 empty] | 3.631 | 3.631 |  | 10 | 10 | 0 | 4 | 10 | 6 | 4
| 120/2 |  | 120/3 |  | 120/4 |  | 120/5 |  | 120/6 |  | 120/7 |  | 121/0 |  | 121/1 |  | 121/2 |  | 121/3
|  | 400 |  | 428 |  | 368 |  | 359 |  | 277 |  | 321.859 |  | 276.141 |  | 433 |  | 384 |  | 384 | 3631
| DA+0 |  | DA+6 |  | DA+0 |  | DA-3 |  | DA+0 |  | DA+3 |  | DB2+9 |  | DB1+25 |  | DA+9 |  | DA+0
[7 empty] | Material Shifted | [14 empty] | 3.717 | 3.717 |  | 10 | 9 | 1 | 7 | 10 | 3 | 7
| 121/4 |  | 121/5 |  | 121/6 |  | 121/7 |  | 121/8 |  | 121/9 |  | 121/10 |  | 121/11 |  | 124/0 |  | 124/1
|  | 343 |  | 352 |  | 388 |  | 368 |  | 386 |  | 397 |  | 390 |  | 396.394 |  | 334.606 |  | 362 | 3717
| DA+0 |  | DA-3 |  | DA+0 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+9 |  | DD45+3 |  | DA-3
[22 empty] | 3.9561 | 3.9561 |  | 10 | 6 | 4 | 3 | 10 | 0 | 10
| 124/2 |  | 124/3 |  | 125/0 |  | 125/1 |  | 125/2 |  | 126/0 |  | 126/1 |  | 126/2 |  | 126/3 |  | 127/0
|  | 378 |  | 397.983 |  | 459.017 |  | 383 |  | 446.914 |  | 411.086 |  | 404 |  | 397 |  | 372.138 |  | 307.002 | 3956.14
| DA+0 |  | DA+0 |  | DC2+3 |  | DA+9 |  | DA+9 |  | DD45+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DB2+0
[22 empty] | 4.4012 | 4.4012 |  | 10 | 4 | 6 | 1 | 10 | 1 | 9
| 127/1 |  | 127/2 |  | 128/0 |  | 129/0 |  | 130/0 |  | 131/0 |  | 131/1 |  | 131/2 |  | 131/3 |  | 131/4
|  | 402.977 |  | 339.134 |  | 619.999 |  | 620.058 |  | 535.071 |  | 437.001 |  | 396 |  | 416 |  | 351 |  | 284 | 4401.24
| DA-3 |  | DB1+9 |  | DD60+25 (2MRC) |  | DD45+25 (15.87MRC) |  | DD45+25 (11.9MRC) |  | DD60+9 (7MRC) |  | DA+3 |  | DA+0 |  | DA+3 |  | DA-3
[22 empty] | 3.386 | 3.386 |  | 10 | 3 | 7 |  | 10 | 1 | 9
| 131/5 |  | 132/0 |  | 132/1 |  | 132/2 |  | 132/3 |  | 133/0 |  | 133/1 |  | 133/2 |  | 133/3 |  | 133/4
|  | 317.617 |  | 323.003 |  | 305 |  | 283 |  | 306.533 |  | 373 |  | 394 |  | 250 |  | 418 |  | 415.85 | 3386.003
| DA-3 |  | DB2+0 |  | DA-3 |  | DA-3 |  | DA-3 |  | DC1+0 |  | DA+0 |  | DB1+0 |  | DB1+0 |  | DA+3
[22 empty] | 3.7772 | 3.7772 |  | 10 | 8 | 2 | 3 | 10 | 3 | 7
| 134/0 |  | 135/0 |  | 136/0 |  | 136/1 |  | 137/0 |  | 137/1 |  | 137/2 |  | 138/0 |  | 139/0 |  | 139/1
|  | 360.678 |  | 247.871 |  | 459.998 |  | 455.963 |  | 447.997 |  | 330 |  | 338.117 |  | 460.541 |  | 309.001 |  | 367 | 3777.166
| DD45+0 |  | DD60+3 |  | DD60+6 |  | DB1+9 |  | DB2+3 |  | DA+6 |  | DA-3 |  | DC2+6 |  | DD45+6 |  | DA+6
[22 empty] | 3.602 | 3.602 |  | 10 | 7 | 3 | 5 | 10 | 5 | 5
| 139/2 |  | 139/3 |  | 140/0 |  | 141/0 |  | 141/1 |  | 141/2 |  | 141/3 |  | 141/4 |  | 141/5 |  | 141/6
|  | 253 |  | 505.404 |  | 171.929 |  | 456.997 |  | 347 |  | 379 |  | 356 |  | 316 |  | 364 |  | 452.63 | 3601.96
| DB2+0 |  | DB1+0 |  | DD60+25 |  | DD60+25 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA-3 |  | DA-3 |  | DA+3
[22 empty] | 3.6824 | 3.6824 |  | 10 | 8 | 2 | 4 | 10 | 3 | 7
| 142/0 |  | 143/0 |  | 144/0 |  | 145/0 |  | 145/1 |  | 145/2 |  | 145/3 |  | 145/4 |  | 145/5 |  | 145/6
|  | 192.597 |  | 252.547 |  | 461.272 |  | 441 |  | 396 |  | 359 |  | 339 |  | 416 |  | 423 |  | 402 | 3682.416
| DC1+9 |  | DD60+18 |  | DD60+18 |  | DD45+9 |  | DA+0 |  | DA+0 |  | DA-3 |  | DA+0 |  | DA+3 |  | DA+3
[22 empty] | 3.722 | 3.722 |  | 10 | 8 | 2 | 4 | 10 | 2 | 8
[6 empty] | BHARUCH SECTION <<<<<<<<< | SURAT DISTRICT FROM 148/1-225/4 =168 Locations (Length 60.449 Kms)
| 145/7 |  | 147/0 |  | 148/0 |  | 148/1 |  | 148/2 |  | 148/3 |  | 148/4 |  | 148/5 |  | 149/0 |  | 150/0
|  | 344.268 |  | 251.645 |  | 439.997 |  | 355 |  | 441 |  | 402 |  | 440 |  | 508.088 |  | 258.002 |  | 282 | 3722
| DB1+0 |  | DD60+25 |  | DD60+25 |  | DA+3 |  | DA+0 |  | DA+6 |  | DA+3 |  | DB1+3 |  | DD60+25 |  | DD60+25
[22 empty] | 3.6135 | 3.6135 |  | 10 |  | 10 |  | 10 | 0 | 10
| 150/1 |  | 151/0 |  | 151A/0 |  | 152/0 |  | 153/0 |  | 153/1 |  | 153/2 |  | 153A/0 |  | 154/0 |  | 155/0
|  | 417 |  | 402 |  | 408.718 |  | 347.617 |  | 297.024 |  | 426.054 |  | 339.996 |  | 391 |  | 326.743 |  | 257.341 | 3613.493
| DB1+0 |  | DD60+6 |  | DD60+18 |  | DD60+3 |  | DD60+3 |  | DA+3 |  | DA+0 |  | DD45+9 |  | DD60+9 |  | DD60+18
[22 empty] | 3.3066 | 3.3066 |  | 10 | 2 | 8 | 1 | 10 | 0 | 10
| 156/0 |  | 156/1 |  | 157/0 |  | 158/0 |  | 159/0 |  | 160/0 |  | 161/0 |  | 162/0 |  | 163/0 |  | 163/1
|  | 342.995 |  | 356.5 |  | 279.356 |  | 223.815 |  | 410.872 |  | 325.015 |  | 248.002 |  | 328.496 |  | 382.995 |  | 408.589 | 3306.635
| DD45+18 |  | DB2+9 |  | DD60+41 |  | DD60+41 |  | DD60+9 (2MRC) |  | DC2+0 |  | DB1+3 |  | DD60+25 |  | DD60+30 |  | DB1+6
[22 empty] | 3.5875 | 3.5875 |  | 10 | 5 | 5 | 3 | 10 | 0 | 10
| 164/0 |  | 165/0 |  | 165/1 |  | 165/2 |  | 165/3 |  | 165/4 |  | 165/5 |  | 165/6 |  | 165/7 |  | 166/0
|  | 285.055 |  | 399.996 |  | 375 |  | 468 |  | 375 |  | 314 |  | 366 |  | 381 |  | 349.096 |  | 274.311 | 3587.458
| DC2+6 |  | DB1+25 |  | DA+9 |  | DA+6 |  | DA+6 |  | DA-3 |  | DA-3 |  | DCT+0 |  | DA+0 |  | DD60+0
[22 empty] | 3.4431 | 3.4431 |  | 10 | 6 | 4 | 4 | 10 | 0 | 10
| 167/0 |  | 168/0 |  | 169/0 |  | 170/0 |  | 171/0 |  | 172/0 |  | 172/1 |  | 173/0 |  | 174/0 |  | 174/1
|  | 576.145 |  | 255.601 |  | 521.312 |  | 261.446 |  | 186.772 |  | 253.996 |  | 435.633 |  | 215.227 |  | 327 |  | 410 | 3443.132
| DD60+9 |  | DD60+30 |  | DD60+25 |  | DD60+6 |  | DB1+18 |  | DD45+9 |  | DA+9 |  | DC2+18 |  | DD60+9 (2MRC) |  | DA+3
[22 empty] | 3.8532 | 3.8532 |  | 10 | 8 | 2 | 7 | 10 | 2 | 8
| 174/2 |  | 174/3 |  | 174/4 |  | 174/5 |  | 174/6 |  | 175/0 |  | 175/1 |  | 176/0 |  | 176/1 |  | 176/2
|  | 386 |  | 372 |  | 375 |  | 431 |  | 332.369 |  | 468.001 |  | 445.528 |  | 390.002 |  | 295 |  | 358.332 | 3853.232
| DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DC2+6 |  | DB1+9 |  | DD45+0 |  | DA+0 |  | DA-3
[22 empty] | 3.5181 | 3.5181 |  | 10 | 7 | 3 | 6 | 10 | 1 | 9
| 177/0 |  | 178/0 |  | 178/1 |  | 178/2 |  | 178/3 |  | 179/0 |  | 179/1 |  | 179/2 |  | 179/3 |  | 180/0
|  | 228.09 |  | 368.998 |  | 305 |  | 316 |  | 336.509 |  | 416.001 |  | 386 |  | 410 |  | 370.473 |  | 380.997 | 3518.068
| DD60+6 |  | DD60+6 |  | DA+0 |  | DA+0 |  | DA-3 |  | DB1+0 |  | DA+3 |  | DA+3 (A,B 1.5 RC) |  | DA+0 |  | DD45+0LE (3 Leg)+1.5LE (1 Leg) & (B1MRC & C0.5MRS)
[22 empty] | 3.8005 | 3.8005 |  | 10 | 10 | 2 | 9 | 10 | 1 | 9
| 180/1 |  | 180/2 |  | 180/3 |  | 180/4 |  | 180/5 |  | 180/6 |  | 180/7 |  | 182/0 |  | 183/0 |  | 183/1
|  | 441 |  | 455 |  | 383 |  | 345 |  | 424 |  | 413 |  | 392.62 |  | 208.909 |  | 348.001 |  | 390 | 3800.53
| DA+3 |  | DB1+3 |  | DA+9 |  | DA-3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DD45+0 |  | DD60+0 |  | DA+0
[22 empty] | 3.7569 | 3.7569 |  | 10 | 8 | 2 | 3 | 10 | 1 | 9
| 183/2 |  | 183/3 |  | 184/0 |  | 185/0 |  | 186/0 |  | 187/0 |  | 188/0 |  | 189/0 |  | 189/1 |  | 190/0
|  | 329 |  | 412.409 |  | 245.489 |  | 266.092 |  | 370.267 |  | 426.643 |  | 672.587 |  | 447.476 |  | 360.501 |  | 226.477 | 3756.941
| DA+0 |  | DA+3 |  | DB1+18 |  | DD45+25 |  | DC1+18 |  | DC1+0 |  | DD60+35 |  | DD60+35 |  | DA+9 |  | DD60+9
[22 empty] | 3.693 | 3.693 |  | 10 | 6 | 4 | 4 | 10 | 0 | 10
| 191/0 |  | 191/1 |  | 192/0 |  | 193/0 |  | 194/0 |  | 194/1 |  | 195/0 |  | 196/0 |  | 196/1 |  | 196/2
|  | 465.474 |  | 389.513 |  | 222.827 |  | 277.415 |  | 470 |  | 479.7 |  | 239.69 |  | 350.922 |  | 450.389 |  | 347.112 | 3693.042
| DD60+9 |  | DB1+3 |  | DC2+9 |  | DD60+30 |  | DD60+30 |  | DB1+9 |  | DC1+18 |  | DB2+18 |  | DA+9 |  | DA+3
[22 empty] | 3.7132 | 3.7132 |  | 10 | 4 | 6 | 4 | 10 | 0 | 10
| 197/0 |  | 197/1 |  | 197/2 |  | 198/0 |  | 199/0 |  | 199/1 |  | 199/2 |  | 200/0 |  | 200/1 |  | 201/0
|  | 320.84 |  | 311.867 |  | 351.014 |  | 246.736 |  | 436.269 |  | 404.296 |  | 425.721 |  | 393.992 |  | 315.989 |  | 506.5 | 3713.224
| DB1+0 |  | DA-3 |  | DA-3 |  | DD60+6 |  | DD60+6 |  | DA+3 |  | DA+6 |  | DC2+0 |  | DA+6 |  | DC1+9
[22 empty] | 3.2259 | 3.2259 |  | 10 |  | 10 |  | 10 | 0 | 10
| 202/0 |  | 203/0 |  | 203/1 |  | 204/0 |  | 205/0 |  | 205/1 |  | 205/2 |  | 206/0 |  | 206/1 |  | 207/0
|  | 252.01 |  | 399.806 |  | 292.2 |  | 275.783 |  | 294.335 |  | 504.736 |  | 301.2 |  | 234.481 |  | 399.081 |  | 272.301 | 3225.933
| DC1+18 |  | DC1+18 |  | DB1+0 |  | DD60+25 (2MRC) |  | DD60+25 (3MRC) |  | DB2+9 |  | DA+9 |  | DC2+0 |  | DB1+6 |  | DD60+25
[22 empty] | 3.5906 | 3.5906 |  | 10 | 3 | 7 | 2 | 10 | 0 | 10
| 208/0 |  | 209/0 |  | 209/1 |  | 209/2 |  | 210/0 |  | 211/0 |  | 211/1 |  | 211/2 |  | 211/3 |  | 211/4
|  | 284.637 |  | 316.283 |  | 323.184 |  | 396.819 |  | 397.662 |  | 367.998 |  | 291 |  | 440 |  | 397 |  | 376 | 3590.583
| DD45+35 |  | DD60+9 |  | DA+0 |  | DA-3 |  | DB2+9 (2MRC) |  | DB2+9 |  | DA-3 |  | DA+0 |  | DA+9 |  | DA-3
[22 empty] | 3.5494 | 3.5494 |  | 10 | 5 | 5 | 1 | 10 | 0 | 10
| 211/5 |  | 212/0 |  | 213/0 |  | 214/0 |  | 214/1 |  | 214/2 |  | 214/3 |  | 214/4 |  | 214/5 |  | 214/6
|  | 266.961 |  | 378.221 |  | 325.229 |  | 451.997 |  | 390 |  | 278 |  | 281 |  | 338 |  | 410 |  | 430 | 3549.408
| DB1+9 |  | DD45+30 (2MRC) |  | DD60+35 |  | DD60+25 |  | DA+6 |  | DA-3 |  | DA-3 |  | DA-3 |  | DA+0 |  | DA+3
[22 empty] | 3.8121 | 3.8121 |  | 10 | 7 | 3 | 4 | 10 | 0 | 10
| 214/7 |  | 215/0 |  | 216/0 |  | 216/1 |  | 216/2 |  | 216/3 |  | 217/0 |  | 217/1 |  | 217/2 |  | 217/3
|  | 407.687 |  | 231.411 |  | 415.001 |  | 388 |  | 359 |  | 390.965 |  | 398.005 |  | 380 |  | 345 |  | 497 | 3812.069
| DA+3 |  | DD60+3 |  | DD60+3 |  | DA+9 (2MRC) |  | DB1+18 (2MRC) |  | DA+9 |  | DC2+9 |  | DA+3 |  | DA+0 |  | DA+9
[22 empty] | 3.3016 | 3.3016 |  | 10 | 8 | 2 |  | 10 | 0 | 10
| 217/4 |  | 217/5 |  | 218/0 |  | 219/0 |  | 219/1 |  | 220/0 |  | 220/1 |  | 221/0 |  | 222/0 |  | 223/0
|  | 340 |  | 285.806 |  | 239.469 |  | 343.001 |  | 455.41 |  | 336 |  | 483.268 |  | 213.017 |  | 225.594 |  | 380.001 | 3301.566
| DA+9 |  | DA+0 |  | DD60+3 |  | DD45+3 |  | DA+9 |  | DD45+0 |  | DA+6 |  | DD60+18 |  | DD60+25 |  | DC1+6
[22 empty] | 3.5584 | 3.5584 |  | 10 | 10 | 0 | 10 | 10 | 0 | 10
| 223/1 |  | 223/2 |  | 223/3 |  | 224/0 |  | 224/1 |  | 224/2 |  | 225/0 |  | 225/1 |  | 225/2 |  | 225/3
|  | 359.46 |  | 320.54 |  | 326.173 |  | 259.997 |  | 454 |  | 431.2 |  | 357 |  | 374 |  | 316 |  | 360 | 3558.37
| DA+0 |  | DA+0 |  | DA-3 |  | DC1+0 |  | DA+3 |  | DB1+6 |  | DB2+0 |  | DA+9 |  | DA-3 |  | DA-3
[22 empty] | 3.9661 | 3.9661 |  | 10 | 1 | 9 |  | 10 | 0 | 10
|  | SURAT <<<< | NAVSARI DISTRICT FROM 225/4-258/0 =168 Locations (Length 33.139 Kms)
| 225/4 |  | 225/5 |  | 225/6 |  | 225/7 |  | 226/0 |  | 226/1 |  | 226/2 |  | 226/3 |  | 227/0 |  | 227/1
|  | 380 |  | 364 |  | 406 |  | 408.44 |  | 443 |  | 385 |  | 362 |  | 384.678 |  | 395.002 |  | 438 | 3966.12
| DA+3 |  | DA+0 |  | DA+0 |  | DA+6 |  | DB2+3 |  | DA+6 |  | DA+0 |  | DA+0 |  | DD45+0 |  | DA+6
[22 empty] | 3.5611 | 3.5611 |  | 10 | 1 | 9 |  | 10 | 0 | 10
| 227/2 |  | 228/0 |  | 228/1 |  | 229/0 |  | 229/1 |  | 229A/0 |  | 229B/0 |  | 230/0 |  | 230/1 |  | 230A/0
|  | 405.735 |  | 379.005 |  | 388.062 |  | 419.998 |  | 371.499 |  | 179.981 |  | 390.653 |  | 475.997 |  | 310.675 |  | 239.51 | 3561.115
| DA+3 |  | DD45+0 |  | DA+0 |  | DD45+0 |  | DA+9 |  | DB1+25 |  | DB2+25 |  | DC1+6 |  | DA+9 |  | DD45+0
[22 empty] | 3.3018 | 3.3018 |  | 10 |  | 10 |  | 10 | 0 | 10
| 231/0 |  | 232/0 |  | 232/1 |  | 232/2 |  | 232/3 |  | 232/4 |  | 233/0 |  | 234/0 |  | 235/0 |  | 235/1
|  | 246.982 |  | 311 |  | 367 |  | 352 |  | 322 |  | 376.185 |  | 393.633 |  | 313.955 |  | 265.996 |  | 353 | 3301.751
| DB1+0 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DC1+0 |  | DD60+18 |  | DD60+9 (2MRC) |  | DA+9
[22 empty] | 3.3824 | 3.3824 |  | 10 |  | 10 | 1 | 10 | 0 | 10
| 235/2 |  | 235/3 |  | 235/4 |  | 236/0 |  | 237/0 |  | 238/0 |  | 239/0 |  | 239/1 |  | 240/0 |  | 240/1
|  | 301 |  | 418 |  | 425.545 |  | 200.821 |  | 202.277 |  | 363.321 |  | 363.996 |  | 373.407 |  | 335.003 |  | 399.045 | 3382.415
| DA+0 |  | DA+0 |  | DA+3 |  | DB2+18 |  | DB1+25 (2MRC) |  | DC1+25 |  | DD45+0 |  | DA+0 |  | DB2+0 |  | DA+3
ROW
[22 empty] | 3.4884 | 3.4884 |  | 10 | 9 | 1 | 8 | 10 | 4 | 6
| 241/0 |  | 241/1 |  | 241/2 |  | 241/3 |  | 241/4 |  | 242/0 |  | 243/0 |  | 243/1 |  | 243/2 |  | 243/3
|  | 366.005 |  | 273 |  | 372 |  | 417 |  | 407.733 |  | 280.015 |  | 337.002 |  | 374 |  | 359 |  | 302.598 | 3488.353
| DD60+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DD60+3 |  | DD60+3 |  | DA+0 |  | DA+0 |  | DA+0
[22 empty] | 4.018 | 4.018 |  | 10 | 7 | 3 | 4 | 10 | 2 | 8
| 244/0 |  | 244/1 |  | 244/2 |  | 244/3 |  | 244/4 |  | 244/5 |  | 244/6 |  | 245/0 |  | 245/1 |  | 246/0
|  | 371.002 |  | 374 |  | 376 |  | 435 |  | 400 |  | 414 |  | 408.119 |  | 384.001 |  | 407.625 |  | 448.281 | 4018.028
| DD45+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DD45+0 |  | DA+0 |  | DD45+9
[22 empty] | 3.7082 | 3.7082 |  | 10 | 7 | 3 | 7 | 10 | 2 | 8
| 247/0 |  | 248/0 |  | 248/1 |  | 248/2 |  | 249/0 |  | 249/1 |  | 249/2 |  | 249/3 |  | 250/0 |  | 250/1
|  | 286.451 |  | 418.219 |  | 285.004 |  | 281.902 |  | 459.998 |  | 322 |  | 432.495 |  | 406.133 |  | 448.999 |  | 367 | 3708.201
| DD60+35 (2MRC) |  | DD60+35 (2MRC) |  | DB1+9 |  | DA+6 |  | DD60+3 |  | DA+9 |  | DA+3 |  | DA+3 |  | DD45+3 |  | DA+9 (1MRC)
[22 empty] | 3.9698 | 3.9698 |  | 10 | 8 | 2 | 6 | 10 | 2 | 8
| 250/2 |  | 250/3 |  | 250A/0 |  | 250A/1 |  | 250A/2 |  | 251/0 |  | 251/1 |  | 252/0 |  | 252/1 |  | 252/2
|  | 432 |  | 382.952 |  | 472.998 |  | 317 |  | 343.976 |  | 408.004 |  | 432.864 |  | 339.996 |  | 394 |  | 446 | 3969.79
| DA+0 |  | DA+9 |  | DB1+3 (3MRC) |  | DA+6 |  | DA+0 |  | DD45+0 |  | DA+6 (1MRC) |  | DB2+0 |  | DA+0 |  | DA+3
[22 empty] | 3.5845 | 3.5845 |  | 10 | 5 | 5 | 3 | 10 | 0 | 10
| 252/3 |  | 252/4 |  | 252/5 |  | 253/0 |  | 254/0 |  | 254/1 |  | 255/0 |  | 255/1 |  | 256/0 |  | 256/1
|  | 393 |  | 449 |  | 487.454 |  | 304.46 |  | 353.19 |  | 263.06 |  | 371.81 |  | 364.945 |  | 324.823 |  | 272.781 | 3584.523
| DA+6 |  | DA+0 |  | DB1+9 |  | DD45+35 (2MRC) |  | DD45+35 (2MRC) |  | DB1+9 |  | DD60+0 |  | DA+0 |  | DD60+0 |  | DA+9
[22 empty] | 0.15936 | 0.15936 |  | 2 | 1 | 1 | 1 | 2 | 0 | 2
NAVSARI SECTION <<<<
| 257/0 |  | 258/0 |  | Gantry
|  | 99.355 |  | 60 | [16 empty] | 159.355
| DC1+9 |  | DD60+0 (1.5MRC)
GAS PIPELINE

## Crossing
765KV D/C HEXA VATAMAN - NAVSARI TL -04 - CROSSING STATUS
Sl No | AP NO | Towe Type | AP No | Tower Type | Type of Crossings | Span Length | LINE OWNER | Line Name | Nos. | Work Portion | Status | Submitted to Client for Review | Proposal Submitted (Y/N) | Inspection Status (Y/N) | Remarks
1 | 118/0 | DB2+0 | 119/0 | DD60+0 | Power Line | 243.824 | GETCO | 66 KV S/C NANDEWAR-WAGRA LINE (H FRAME) | 1 | Bharuch | Submitted | 2024-07-10 | Y | Y | Approved
2 | 119/3 | DA+9 | 120/0 | DD60+3 | Power Line | 358.181 | GETCO | 66 KV D/C BHARUCH B TO VAGRA TAP VILAGAT LINE | 1 | Bharuch | Submitted | 2024-07-15 | Y | Y | Approved
3 | 121/0 | DB2+9 | 121/1 | DB1+25 | Power Line | 276.141 | GETCO | 220 kv D/C VAGRA- THAM TSS LINE (U/C) | 1 | Bharuch | Submitted | 2024-09-12 | Y | Y | Approved
4 | 121/11 | DA+9 | 124/0 | DD45+3 | Power Line | 396.394 | GETCO | 66 KV D/C Vilayat - Kukarwada Line | 1 | Bharuch | Submitted | 2024-07-15 | Y | Y | Approved
5 | 136/1 | DB1+9 | 137/0 | DB2+3 | Power Line | 455.963 | GETCO | 66 KV S/C Hansot Robban Line | 1 | Bharuch | Submitted | 2024-09-12 | Y | Y | Approved
6 | 140/0 | DD60+25 | 141/0 | DD60+25 | Power Line | 171.929 | ESSAR | 400 KV D/C HZR-GDR | 1 | Bharuch | Submitted | 2024-11-23 | Y | Y | Approved
7 | 141/6 | DA+3 | 142/0 | DC1+9 | Power Line | 452.63 | GETCO | 66 KV S/C Panoli-Hansot | 1 | Bharuch | Submitted | 2024-07-10 | Y | Y | Approved
8 | 147/0 | DD60+25 | 148/0 | DD60+25 | Power Line | 251.645 | GETCO | 400 KV D/C KOSAMBA - CHORANIA | 1 | Bharuch | Submitted | 2024-07-10 | Y | Y | Approved
9 | 149/0 | DD60+25 | 150/0 | DD60+25 | Power Line | 258.002 | TORRENT | 400 KV D/C DGEN-NAVASARI | 1 | Surat | Submitted | 2024-07-15 | Y | Y | Approved
10 | 155/0 | DC1+18 | 156/0 | DD45+18 | Power Line | 257.341 | POWERGRID | 220 KV D/C KWS-HAL | 1 | Surat | Submitted | 2024-07-15 | Y | Y | IN RHQ (PGCIL)
11 | 157/0 | #N/A | 158/0 | #N/A | Power Line | 279.356 | POWERGRID | 765 KV D/C AHMEDABAD-NAVSARI | 1 | Surat | Submitted | 2024-07-15 | Y | Y | Approved
12 | 159/0 | #N/A | 160/0 | DC2+0 | Power Line | 410.872 | GETCO | 66 KV S/C DINODA-KHARCH | 1 | Surat | Submitted | 2024-07-15 | Y | Y | Approved
13 | 162/0 | DD60+25 | 163/0 | DD60+30 | Power Line | 328.496 | TORRENT | 400 KV D/C DGEN-NAVASARI | 1 | Surat | Submitted | 2024-07-15 | Y | Y | Approved
14 | 163/0 | DD60+30 | 163/2 | DB1+6 | Power Line | 382.995 | GETCO | 66 KV D/C PALOD-KOSAMBA | 1 | Surat | Submitted | 2024-07-15 | Y | Y | Approved
15 | 164/0 | DC2+6 | 165/0 | DB1+25 | Power Line | 285.055 | GETCO | 220KV D/C GSECL(Hazira)-KOSAMBA | 1 | Surat | Submitted | 2024-07-15 | Y | Y | Approved
16 | 168/0 | DD60+30 | 169/0 | DD60+25 | Power Line | 255.601 | TORRENT | 400 KV D/C SUG-PIR | 1 | Surat | Submitted | 2024-07-22 | Y | Y | Approved
17 | 171/0 | DB1+18 | 172/0 | DD45+9 | Power Line | 186.772 | GETCO | 220 KV D/C KOSAMBA-VAV | 1 | Surat | Submitted | 2024-07-22 | Y | Y | Approved
18 | 173/0 | DC2+18 | 174/0 | #N/A | Power Line | 215.227 | GETCO | 220 KV D/C KIM-KOSAMBA | 1 | Surat | Submitted | 2024-07-22 | Y | Y | Approved
19 | 175/0 | DC2+6 | 175/1 | DB1+9 | Power Line | 468.001 | GETCO | 66 KV S/C KIM-MASOLI | 1 | Surat | Submitted | 2024-07-22 | Y | Y | Approved
20 | 177/0 | DD60+6 | 178/0 | DD60+6 | Power Line | 228.09 | TORRENT | 400 KV S/C GHT-TPL | 1 | Surat | Submitted | 2024-07-22 | Y | Y | Approved
21 | 184/0 | DB1+18 | 185/0 | DD45+25 | Power Line | 245.489 | TORRENT Power | 220 KV D/C SUGEN-BHATAR | 1 | Surat | Submitted | 2025-04-14 | Y | Y | Approved
22 | 185/0 | DD45+25 | 186/0 | DC1+18 | Power Line | 266.092 | TORRENT Power | 220 KV D/C SUGNA-PUNE | 1 | Surat | Submitted | 2025-04-14 | Y | Y | Approved
23 | 186/0 | DC1+18 | 187/0 | DC1+0 | Power Line | 370.267 | GETCO | 66 KV S/C KAMRAJ-ARETH | 1 | Surat | Submitted | 2025-04-14 | Y | Y | Approved
24 | 190/0 | DD60+9 | 191/0 | DD60+9 | Power Line | 226.477 | TORRENT Power | 400 KV S/C TPL-VAP | 1 | Surat | Submitted | 2025-04-14 | Y | Y | Approved
25 | 192/0 | DC2+9 | 193/0 | DD60+25 | Power Line | 222.827 | TORRENT Power | 220 KV D/C SUGEN-PUNE | 1 | Surat | Submitted | 2025-04-14 | Y | Y | Approved
26 | 193/0 | DD60+25 | 194/0 | DD60+25 | Power Line | 277.415 | GETCO | 400 KV D/C KOSAMBA-VAV | 1 | Surat | Submitted | 2025-04-14 | Y | Y | Approved
27 | 195/0 | DC1+18 | 196/0 | DB2+18 | Power Line | 239.69 | TORRENT Power | 220 KV D/C SUGEN-BHATAR | 1 | Surat | Submitted | 2025-04-14 | Y | Y | Approved
28 | 201/0 | DB2+6 | 202/0 | DC2+18 | Power Line | 506.5 | GETCO | 66 KV S/C VAV-SHAMPURA | 1 | Surat | Submitted | 2025-04-14 | Y | Y | Approved
29 | 202/0 | DC2+18 | 203/0 | DD45+9 | Power Line | 252.01 | PGCIL | 220 KV D/C KAP-VAV | 1 | Surat | Submitted | 2025-04-14 | Y | Y | IN RHQ (PGCIL)
30 | 204/0 | DD60+18 | 205/0 | DD60+25 | Power Line | 294.335 | PGCIL | 400 KV D/C GND-NAV | 1 | Surat | Submitted | 2025-04-14 | Y | Y | IN RHQ (PGCIL)
31 | 207/0 | DD60+9 | 208/0 | DB1+18 | Power Line | 272.301 | GETCO | 220 KV D/C | 1 | Surat | Submitted | 2025-04-14 | Y | Y | Approved
32 | 208/0 | DB1+18 | 209/0 | DD60+0 | Power Line | 284.637 | GETCO | 66 KV D/C | 1 | Surat | Submitted | 2025-04-14 | Y | Y | Approved
33 | 210/0 | DB2+9+2MRC | 211/0 | DB2+9 | Power Line | 397.662 | GETCO | 66 KV D/C Mota Madhi | 1 | Surat | Submitted | 2024-08-14 | Y | Y | Approved
34 | 210/0 | DB2+9+2MRC | 211/0 | DB2+9 | Power Line |  | GETCO | 66 KV D/C MOTA-Moti Fadoo | 1 | Surat | Submitted | 2024-08-14 | Y | Y | Approved
35 | 212/0 | DD45+9 | 213/0 | DD60+35 | Power Line | 378.221 | GETCO | 220kV D/C MOTA - AMBHETA TRANSMISSION LINE | 1 | Surat | Submitted | 2024-08-12 | Y | Y | Approved
36 | 213/0 | DD60+35 | 214/0 | DD60+30 | Power Line | 325.229 | POWERGRID | 400 KV D/C KAKARPAR - NAVSARI TRANSMISSION LINE | 1 | Surat | Submitted | 2024-08-12 | Y | Y | IN CORPORATE (PGCIL)
37 | 216/1 | DA+0 | 216/2 | DA+0 | Power Line | 388 | GETCO | 66 KV KORODAR- AFVA LINE H FEAM | 1 | Surat | Submitted | 2024-08-12 | Y | Y | Approved
38 | 217/0 | DC2+9 | 217/1 | DA+3 | Power Line | 398.005 | GETCO | 66 KV D/C LINE MOTA TO SARWAN TRANSMISSION LINE | 1 | Surat | Submitted | 2024-08-12 | Y | Y | IN GETCO CORPORATE
39 | 221/0 | DD60+30 | 222/0 | DD60+25 | Power Line | 213.017 | PGCIL | 400 KV D/C NAV-BSR | 1 | Surat | Submitted | 2025-04-14 | Y | Y | Approved
40 | 229/0 | DD45+0 | 230/0 | DC1+6 | Power Line | 179.981 | GETCO | 220 KV D/C Nav-Popda/Nav-Talangpur | 1 | Navsari | Submitted | 2025-04-14 | Y | Y | Approved
41 | 234/0 | DD60+18 | 235/0 | DD60+9 | Power Line | 313.955 | POWERGRID | 220 KV D/C NAVSARI-NAVSARI LINE | 1 | Navsari | Submitted | 2024-08-16 | Y | Y | Approved
42 | 236/0 | DB+18 | 237/0 | DB+25 | Power Line | 200.821 | GETCO | 132 KV S/C NAVSARI - POPDA CKT-1 LINE | 1 | Navsari | Submitted | 2024-07-07 | Y | Y | Approved
43 | 236/0 | DB+18 | 237/0 | DB+25 | Power Line |  | GETCO | 66 KV D/C NAV-EKL & TAVDI-VESSMA LINE | 1 | Navsari | Submitted | 2024-07-07 | Y | Y | Approved
44 | 237/0 | DB+25 | 238/0 | DC+25 | Power Line | 202.277 | GETCO | 132 KV S/C NAV-POPDA CKT-2 LINE | 1 | Navsari | Submitted | 2024-07-07 | Y | Y | Approved
45 | 247/0 | DD60+35 | 248/0 | DD60+35 | Power Line | 286.451 | POWERGRD | 765 KV D/C AHMEDABAD-NAVSARI | 1 | Navsari | Submitted | 2024-12-03 | Y | Y | Approved
46 | 250/3 | DA+9 | 250A/0 | DB1+3(RC+2) | Power Line | 382.952 | GETCO | 66 KV D/C Talangpur-Mangrol line | 1 | Navsari | Submitted | 2025-01-10 | Y | Y | Approved
47 | 253/0 | DD45+35 | 254/0 | DD45+35 | Power Line | 304.46 | GETCO | LILO OF 220 KV TALANGPORE (SACHIN)-NAVSARI LINE AND TALANGPORE (SACHIN)-VAV LINE AT 765 KV NAVSARI(NEW)S/S OF ISTS | 1 | Navsari | Submitted | 2025-03-14 | Y | Y | Approved
48 | 256/1 | DA+9 | 257/0 | DB2+9 | Power Line | 272.781 | GETCO | 66 KV D/C Mangrol-Ubarhat Line | 1 | Navsari | Submitted | 2024-07-07 | Y | Y | Approved
49 | 152/0 | DD60+3 | 153/0 | DD60+3 | Railway | 297.024 | IR | RAILWAY LINE KOSAMBA-HATURAN | 1 | Navsari | Submitted | 2024-09-25
50 | 166/0 | DD60+0 | 167/0 | DD60+9 | Railway | 274.311 | IR | RAILWAY LINE NOT IN USE | 1 | Navsari | Submitted | 2024-09-21 | Y | Y
51 | 215/0 | DD60+3 | 216/0 | DD60+3 | Railway | 231.411 | IR | RAILWAY LINE BARDOLI-GANGADHARA | 1 | Navsari | Submitted | 2024-10-26 | Y | Y | Approved
52 | 242/0 | DD60+3 | 243/0 | DD60+3 | Railway | 280.015 | IR | RAILWAY LINE NAVSARI-MAROLI | 1 | Navsari | Submitted | 2024-09-12 | Y | Y | Approved
53 | 234/0 | DD60+18 | 235/0 | DD60+9 | Bullet Train |  | NHSRL | BULLET TRAIN | 1 | Navsari | Submitted | 2024-09-11 | Y | Y | Approved
54 | 143/0 | DD60+25 | 144/0 | DD60+25 | Bullet Train | 252.547 | NHSRL | BULLET TRAIN | 1 | Bharuch | Submitted | 2024-09-16 | Y | Y | Approved
55 | 133/2 | DB1+0 | 133/3 | DB1+0 | NH | 250 | NH | NH 64 ( Delhi - Mumbai ) | 1 | Bharuch | Submitted | 2024-09-04 | Y | Y | Approved
56 | 218/0 | DD60+3 | 219/0 | DD45+3 | NH | 239.469 | NH | NH 53 | 1 | Surat | Submitted | 2025-04-19 | Y | Y | Approved
57 | 231/0 | DB1+0 | 232/0 | DB1+0 | NH | 246.982 | NH | NH 48 | 1 | Navsari | Submitted | 2025-04-18 | Y | Y | Approved
58 | 135/0 | DD60+0 | 136/0 | DD60+6 | NH | 247.871 | Express Way | NE- 4 (Delhi - Mumbai) | 1 | Bharuch | Submitted | 2024-08-24 | Y | Y | Approved
59 | 182/0 | DD45+0 | 183/0 | DD60+0 | NH | 208.909 | Express Way | NE- 4 (Delhi - Mumbai) | 1 | Surat | Submitted | 2024-08-24 | Y | Y | Approved
60 | 222/0 | DD60+25 | 223/0 | DC1+6 | NH | 225.594 | Express Way | NE- 4 (Delhi - Mumbai) | 1 | Surat | Submitted | 2025-04-21 | Y | Y | Approved
61 | 198/0 | DD60+6 | 199/0 | DD60+6 | NH | 246.736 | Express Way | NE- 4 (Delhi - Mumbai) | 1 | Surat | Submitted | 2025-04-17 | Y | Y | Approved
62 | 161/0 | DB1+3 | 162/0 | DD60+25 | NH | 248.002 | NH | NH 48 | 1 | Surat | Submitted | 2024-09-04 | Y | Y | Approved
63 | 133/4 | DA+3 | 134/0 | DD45+0 | Gas Pipe Line |  | GSPL | GSPL (133/4 - 134/0) Gas Pipe Line Crossing | 1 | Bharuch | Submitted | 2024-09-16 | Y | Y
64 | 155/0 | DC1+18 | 156/0 | DD45+18 | Gas Pipe Line |  | GAIL | GAIL (155/0 - 156/0) Gas Pipe Line Crossing | 1 | Surat | Submitted | 2024-09-23 | Y | Y
65 | 233/0 | DC1+0 | 234/0 | DD60+18 | Gas Pipe Line |  | REPL | REPL (233/0 - 234/0) Gas Pipe Line Crossing | 1 | Navsari | Submitted | 2024-09-16 | Y | Y
66 | 233/0 | DC1+0 | 234/0 | DD60+18 | Gas Pipe Line |  | PIL | PIL (233/0 - 234/0) Gas Pipe Line Crossing | 1 | Navsari | Submitted | 2024-09-16 | Y | Y
67 | 239/0 | DD45+0 | 239/1 | DA+0 | Gas Pipe Line |  | GSPL | GSPL (239/0 - 239/1) Gas Pipe Line Crossing | 1 | Navsari | Submitted | 2024-09-16 | Y | Y
68 | 245/0 | DD45+0 | 245/1 | DA+0 | Gas Pipe Line |  | GAIL | GAIL (245/0 - 245/1) Gas Pipe Line Crossing | 1 | Navsari | Submitted | 2024-09-16 | Y | Y

## Sheet2 (hidden)
Hotline Stringing total KM : 17.112 Km
Sl NO | Description | Dec'25 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | June'25
1 | Hotline Stringing | 2.4446 | 2.4446 | 2.4446 | 2.4446 | 2.4446 | 2.4446 | 2.4446

## Soil Inv.
VNTL PROJECT - SOIL INVESTIGATION LOCATIONS
Sl. No. | Loc. No. | TOT | RC | Status | Classification | Approval Letter Status
1 | 121/0 | DB2+9 |  | Done | WBC | Approved
2 | 129/0 | DD45+25 |  | Done | PILE | Approved
3 | 130/0 | DD45+25 |  | Done | PILE | Approved
4 | 131/0 | DD60+9 | 7 | Done | Sandy Dry Soil | Approved
5 | 135/0 | DD60+0 |  | Done | 2 Mtr WBC & 1.5 Mtr FS | Approved
6 | 140/0 | DD60+25 |  | Done | WBC | Approved
7 | 144/0 | DD60+25 |  | Done | WBC | Approved
8 | 147/0 | DD60+25 |  | Done | WBC | Approved
9 | 150/0 | DD60+25 |  | Done | WBC | Approved
10 | 153/0 | DD60+3 |  | Done | WBC | Approved
11 | 158/0 | DD60+43 | 1 | Done | WBC | Approved
12 | 162/0 | DD60+25 |  | Done | WBC | Approved
13 | 166/0 | DD60+0 |  | Done | WBC | Approved
14 | 169/0 | DD60+25 |  | Done | WBC | Approved
15 | 178/0 | DD60+6 |  | Done | WBC | Approved
16 | 182/0 | DD45+0 |  | Done | WBC | Approved
17 | 191/0 | DD60+9 |  | Done | 2 Mtr WBC & 1.5 Mtr Normal Dry | Approved
18 | 194/0 | DD60+25 |  | Done | WBC | Approved
19 | 198/0 | DD60+6 |  | Done | WBC | Approved
20 | 205/0 | DD60+25 |  | Done | WBC | Approved
21 | 214/0 | DD60+30 |  | Done | WBC | Approved
22 | 216/0 | DD60+3 |  | Done | WBC | Approved
23 | 219/0 | DD45+3 |  | Done | WBC | Approved
24 | 223/0 | DC2+6 |  | Done | WBC | Approved
25 | 232/0 | DB1+0 |  | Done | WBC | Approved
26 | 235/0 | DD60+9 | 2 | Done | WBC | Approved
27 | 243/0 | DD60+3 |  | Done | WBC | Approved
28 | 248/0 | DD60+35 | 2 | Done | WBC | Approved

## Survey Anx
TL- 04 765 kV D/C Vataman-Navsari Transmission Line
District | Section | Total | Detail Survey |  |  | Check Survey
|  |  | Completed | Submitted | Approved | Completed | Submitted | Approved
Bharuch | AP117-AP127 | 14.513 | 14.513 | 14.513 | 14.513 | 14.513 | 14.513 | 14.513
Bharuch | AP127-AP128 | 1.049 | 1.049 | 1.049 | 1.049 | 1.049 | 1.049 | 1.049
Bharuch | AP128-AP131 | 1.7751 | 1.7751 | 1.7751 | 1.7751 | 1.7751 | 1.7751 | 1.7751
Bharuch | AP131-AP132 | 2.2016 | 2.2016 | 2.2016 | 2.2016 | 2.2016 | 2.2016 | 2.2016
Bharuch | AP132-AP137 | 4.5929 | 4.5929 | 4.5929 | 4.5929 | 4.5929 | 4.5929 | 4.5929
Bharuch | AP137-AP142 | 5.8546 | 5.8546 | 5.8546 | 5.8546 | 5.8546 | 5.8546 | 5.8546
Bharuch | AP142-AP145 | 0.9064 | 0.9064 | 0.9064 | 0.9064 | 0.9064 | 0.9064 | 0.9064
Bharuch | AP145-AP149 | 5.958 | 5.958 | 5.958 | 5.958 | 5.958 | 5.958 | 5.958
Surat | AP149-AP151 | 1.768
Surat | AP151-AP155 | 2.128
Surat | AP151-AP183 | 21.029 | 21.029 | 21.029 | 21.029 | 21.029 | 21.029 | 21.029
Surat | AP183-AP211 | 16.847 | 16.847 | 16.847 | 16.847 | 16.847 | 16.847 | 16.847
Surat | AP211-AP215 | 5.829 | 5.829 | 5.829 | 5.829 | 5.829 | 5.829 | 5.829
Surat | AP215-AP218 | 4.03 | 4.03 | 4.03 | 4.03 | 4.03 | 4.03 | 4.03
Surat | AP218-AP226 | 7.7925 | 7.7925 | 7.7925 | 7.7925 | 7.7925 | 7.7925 | 7.7925
Navsari | AP226-AP232 | 6.215 | 6.215 | 6.215 | 6.215 | 6.215 | 6.215 | 6.215
Navsari | AP232-AP245 | 12.704 | 12.704 | 12.704 | 12.704 | 12.704 | 12.704 | 12.704
Navsari | AP245-AP250 | 4.132 | 4.132 | 4.132 | 4.132 | 4.132 | 4.132 | 4.132
Navsari | AP250-AP253 | 6.115 | 6.115 | 6.115 | 6.115 | 6.115 | 6.115 | 6.115
Navsari | AP253-AP258 | 2.4139 | 2.4139 | 2.4139 | 2.3539 | 2.3539 | 2.3539 | 2.3539
Total |  | 127.8541 | 123.9581 | 123.9581 | 123.8981 | 123.8981 | 123.8981 | 123.8981

## Survey
|  |  | Date | 2026-01-14
TA414 ¦ VNTL PROJECT ¦ SURVEY STATUS ¦
Sl. No. | Particulars | UoM | Qty. | Remarks
1 | Total Section Length | Kms. | 127.854
2 | Detail Survey Submitted | Kms. | 123.9581
3 | Balance to Submit | Kms. | 3.8959
4 | Detail Survey Approved | Kms. | 123.9581
5 | Balance to Approve | Kms. | 3.8959
6 | Check Survey Submitted | Kms. | 123.9581
7 | Check Survey Approved | Kms. | 123.9581
8 | Balance to Approve | Kms. | 3.8959
9 | Route Diversion Approve with D/Survey Balance | Kms. | 3.8959
10 | Balanceto Submit due to Crossing Section | Kms. | 0