## Visual Chart (hidden)
VISUAL PROGRESS CHART
TL-02 765 KV D/C Kurnool IV - Bidar Transmission Line
Foundation (Nos.):- |  | 0 | / 297 | Erection (Nos.):- |  |  | / 297 | Earthing (Nos.):- |  |  | / 297 | Rough Sag (Kms):- |  |  | 113.292 | Final Sag (Kms):- |  |  | 113.292 | Date:- | 08.01.2026
COMPLETION CHART | -3 | +0 | +3 | +6 | +9 | Total | Line Qty
[8 empty] | ERECTION | [5 empty] | Rough Sag |  | SH / NH Road Crossing
[8 empty] | WIP | [11 empty] | River
DA | [5 empty] | 0 |  |  | Type |  | Angle Tower |  |  |  |  | Gas Pipeline
DB1 | [5 empty] | 0 |  | FOUNDATION
DB2 | [5 empty] | 0 | [6 empty] | Final Sag
DC1 | [5 empty] | 0
DC2 | [5 empty] | 0 | [10 empty] | Railway
DCT | [5 empty] | 0 | [8 empty] | WIP
DD45 | [5 empty] | 0 |  | Section Tower | SC | [7 empty] | Crossing |  |  | 110-800 KV
DD60 | [5 empty] | 0 |  | TP | TT |  | Earthing |  |  | OPGW | [5 empty] | Line
Total Completed Foundations | [5 empty] | 0 | 0
110kv OHTL
SH -122
| 411 |  | 432 |  | 408 |  | 433 |  | 409 |  | 432 |  | 375 |  | 414 |  | 403 |  | 406 |  | 319 |  | 384
48/0 |  | 48/1 |  | 48/2 |  | 48/3 |  | 48/4 |  | 48/5 |  | 48/6 |  | 48/7 |  | 49/0 |  | 49/1 |  | 49/2 |  | 49/3
3DB1+0 |  | 3DA+6 |  | 3DA+0 |  | 3DA+6 |  | 3DA+3 |  | 3DA+3 |  | 3DA+3 |  | 3DA+6 |  | 3DC1+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0
| 385 |  | 409 |  | 369 |  | 350 |  | 395 |  | 412 |  | 366 |  | 383 |  | 300 |  | 393 |  | 414 |  | 412
49/4 |  | 49/5 |  | 49/6 |  | 49/7 |  | 49/8 |  | 49/9 |  | 49/10 |  | 49/11 |  | 50/0 |  | 50/1 |  | 50/2 |  | 50/3
3DA+0 |  | 3DA+6 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DC2+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3
| 377 |  | 369 |  | 369 |  | 403 |  | 374 |  | 416 |  | 424 |  | 401 |  | 437 |  | 369 |  | 361 |  | 458
51/0 |  | 51/1 |  | 51/2 |  | 51/3 |  | 51/4 |  | 51/5 |  | 51/6 |  | 51/7 |  | 51/8 |  | 51/9 |  | 51/10 |  | 52/0
3DC2+0 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3 |  | 3DA+3 |  | 3DA+3 |  | 3DA+3 |  | 3DA+0 |  | 3DB2+0
[22 empty] | RWY Xing | TDR-VBD
| 355 |  | 347 |  | 430 |  | 408 |  | 402 |  | 411 |  | 397 |  | 404 |  | 398 |  | 430 |  | 320 |  | 230
52/1 |  | 52/2 |  | 52/3 |  | 52/4 |  | 53/0 |  | 53/1 |  | 53/2 |  | 53/3 |  | 53/4 |  | 53/5 |  | 53/6 |  | 54/0
3DA+9 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DB2+3 |  | 3DA+3 |  | 3DA+0 |  | 3DA+3 |  | 3DA+3 |  | 3DA+0 |  | 3DA+3 |  | 3DD60+0
| 339 |  | 365 |  | 409 |  | 343 |  | 352 |  | 419 |  | 410 |  | 413 |  | 407 |  | 352 |  | 405 |  | 393
55/0 |  | 55/1 |  | 55/2 |  | 55/3 |  | 56/0 |  | 56/1 |  | 56/2 |  | 56/3 |  | 56/4 |  | 56/5 |  | 56/6 |  | 56/7
3DD60+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DC1+0 |  | 3DA+3 |  | 3DA+3 |  | 3DA+0 |  | 3DA+3 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0
220KV D/C OHTL
TDR-GBL
| 439 |  | 398 |  | 445 |  | 355 |  | 447 |  | 215 |  | 498 |  | 325 |  | 388 |  | 381 |  | 349 |  | 373
56/8 |  | 56/9 |  | 56/10 |  | 56/11 |  | 56/12 |  | 57/0 |  | 58/0 |  | 58/1 |  | 58/2 |  | 58/3 |  | 59/0 |  | 59/1
3DA+0 |  | 3DA+6 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DC1+9 |  | 3DB2+6 |  | 3DA+6 |  | 3DA+0 |  | 3DA+3 |  |  |  | 3DA+0
| 386 |  | 429 |  | 377 |  | 405 |  | 425 |  | 344 |  | 399 |  | 439 |  | 403 |  | 480 |  | 535 |  | 389
59/2 |  | 59/3 |  | 59/4 |  | 59/5 |  | 60/0 |  | 60/1 |  | 60/2 |  | 60/3 |  | 60/4 |  | 60/5 |  | 60/6 |  | 60/7
3DA+0 |  | 3DA+0 |  | 3DA+6 |  | 3DA+0 |  | 3DB2+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+6 |  | 3DA+0 |  | 3DB1+6 |  | 3DB1+9 |  | 3DB1+9
NH-163
KDL-HYD
| 454 |  | 247 |  | 373 |  | 401 |  | 388 |  | 328 |  | 330 |  | 331 |  | 361 |  | 306 |  | 336 |  | 278
60/8 |  | 61/0 |  | 62/0 |  | 62/1 |  | 62/2 |  | 62/3 |  | 62/4 |  | 63/0 |  | 63/1 |  | 63/2 |  | 63/3 |  | 63/4
3DA+3 |  | 3DB1+0 |  | 3DC1+0 |  | 3DA+0 |  | 3DA+9 |  | 3DA+0 |  | 3DA+0 |  | 3DC2+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0
| 439 |  | 401 |  | 350 |  | 335 |  | 314 |  | 421 |  | 466 |  | 352 |  | 403 |  | 373 |  | 362 |  | 351
64/0 |  | 65/0 |  | 65/1 |  | 65/2 |  | 65/3 |  | 66/0 |  | 66/1 |  | 67/0 |  | 67/1 |  | 67/2 |  | 67/3 |  | 67/4
3DC2+0 |  | 3DC2+3 |  | 3DA+0 |  | 3DA+3 |  | 3DA+0 |  | 3DC1+3 |  | 3DB1+6 |  | 3DD45+6 |  | 3DA+9 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3
220KV D/C OHTL
TDR-MBR
| 361 |  | 375 |  | 425 |  | 429 |  | 350 |  | 483 |  | 453 |  | 388 |  | 317 |  | 324 |  | 485 |  | 249
68/0 |  | 68/1 |  | 68/2 |  | 69/0 |  | 69/1 |  | 69/2 |  | 70/0 |  | 70/1 |  | 70/2 |  | 70/3 |  | 70/4 |  | 71/0
3DB2+0 |  | 3DA+3 |  | 3DA+6 |  | 3DB2+6 |  | 3DA+9 |  | 3DA+6 |  | 3DC2+3 |  | 3DA+9 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3 |  | 3DC2+9
[11 empty] | NH-167N | [9 empty] | 132KV S/C OHTL
[11 empty] | KDL-KSG | [9 empty] | KSG-PRG
| 429 |  | 399 |  | 435 |  | 404 |  | 374 |  | 250 |  | 398 |  | 364 |  | 380 |  | 459 |  | 206 |  | 385
72/0 |  | 72/1 |  | 73/0 |  | 73/1 |  | 73/2 |  | 74/0 |  | 75/0 |  | 75/1 |  | 75/2 |  | 75/3 |  | 76/0 |  | 77/0
3DB2+9 |  | 3DA+3 |  | 3DB2+0 |  | 3DA+6 |  | 3DA+0 |  | 3DC1+0 |  | 3DC1+0 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DC1+9 |  | 3DD45+6
| 372 |  | 384 |  | 400 |  | 386 |  | 398 |  | 393 |  | 387 |  | 378 |  | 410 |  | 368 |  | 396 |  | 395
77/1 |  | 77/2 |  | 77/3 |  | 77/4 |  | 77/5 |  | 77/6 |  | 77/7 |  | 77/8 |  | 77/9 |  | 77/10 |  | 78/0 |  | 78/1
3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3 |  | 3DC1+0 |  | 3DA+3
NH-161B
| 414 |  | 350 |  | 356 |  | 460 |  | 379 |  | 383 |  | 400 |  | 421 |  | 323 |  | 312 |  | 360 |  | 301
78/2 |  | 78/3 |  | 79/0 |  | 79/1 |  | 79/2 |  | 79/3 |  | 80/0 |  | 80/1 |  | 80/2 |  | 80/3 |  | 80/4 |  | 80/5
3DA+3 |  | 3DA+0 |  | 3DC1+0 |  | 3DA+3 |  | 3DA+6 |  | 3DA+9 |  | 3DB2+9 |  | 3DA+3 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0
| 379 |  | 394 |  | 410 |  | 404 |  | 436 |  | 437 |  | 406 |  | 438 |  | 412 |  | 413 |  | 328 |  | 385
80/6 |  | 81/0 |  | 81/1 |  | 81/2 |  | 81/3 |  | 82/0 |  | 82/1 |  | 82/2 |  | 83/0 |  | 83/1 |  | 83/2 |  | 84/0
3DA+0 |  | 3DD45+9 |  | 3DA+0 |  | 3DA+3 |  | 3DA+0 |  | 3DC1+9 |  | 3DA+0 |  | 3DA+6 |  | 3DB2+6 |  | 3DA+0 |  | 3DA+3 |  | 3DB1+0
| 415 |  | 394 |  | 362 |  | 386 |  | 425 |  | 412 |  | 337 |  | 323 |  | 329 |  | 315 |  | 465 |  | 374
84/1 |  | 84/2 |  | 84/3 |  | 84/4 |  | 84/5 |  | 84/6 |  | 84/7 |  | 85/0 |  | 85/1 |  | 85/2 |  | 85/3 |  | 85/4
3DA+6 |  | 3DA+6 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DB1+6 |  | 3DA+9 |  | 3DA+6 |  | 3DA+3 |  | 3DA+3
| 400 |  | 359 |  | 468 |  | 287 |  | 416 |  | 352 |  | 361 |  | 426 |  | 394 |  | 384 |  | 414 |  | 480
86/0 |  | 86/1 |  | 87/0 |  | 88/0 |  | 89/0 |  | 89/1 |  | 90/0 |  | 90/1 |  | 90/2 |  | 90/3 |  | 90/4 |  | 90/5
3DC1+6 |  | 3DA+3 |  | 3DC1+3 |  | 3DB1+9 |  | 3DC1+6 |  | 3DA+0 |  | 3DB2+0 |  | 3DA+3 |  | 3DA+0 |  | 3DA+3 |  | 3DA+0 |  | 3DB1+9
| 395 |  | 329 |  | 418 |  | 467 |  | 443 |  | 311 |  | 479 |  | 321 |  | 506 |  | 421 |  | 421 |  | 406
91/0 |  | 91/1 |  | 91/2 |  | 92/0 |  | 92/1 |  | 92/2 |  | 93/0 |  | 93/1 |  | 93/2 |  | 93/3 |  | 94/0 |  | 94/1
3DC2+3 |  | 3DA+3 |  | 3DA+6 |  | 3DD45+0 |  | 3DB1+9 |  | 3DA+0 |  | 3DB2+3 |  | 3DA+3 |  | 3DA+9 |  | 3DB1+9 |  | 3DC1+3 |  | 3DA+0
| 435 |  | 533 |  | 265 |  | 484 |  | 611 |  | 367 |  | 469 |  | 371 |  | 370 |  | 327 |  | 318 |  | 340
94/2 |  | 94/3 |  | 95/0 |  | 96/0 |  | 96/1 |  | 96/2 |  | 96/3 |  | 96/4 |  | 96/5 |  | 96/6 |  | 96/7 |  | 96/8
3DA+3 |  | 3DB1+9 |  | 3DD45+9 |  | 3DD45+9 |  | 3DB1+0 |  | 3DB1+0 |  | 3DA+6 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0
| 396 |  | 377 |  | 398 |  | 393 |  | 374 |  | 363 |  | 349 |  | 386 |  | 390 |  | 417 |  | 423 |  | 340
97/0 |  | 97/1 |  | 97/2 |  | 97/3 |  | 97/4 |  | 98/0 |  | 98/1 |  | 98/2 |  | 98/3 |  | 98/4 |  | 98/5 |  | 99/0
3DB2+0 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3 |  | 3DC1+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+6 |  | 3DC1+0
| 365 |  | 403 |  | 382 |  | 395 |  | 385 |  | 381 |  | 395 |  | 403 |  | 383 |  | 386 |  | 397 |  | 371
99/1 |  | 99/2 |  | 99/3 |  | 99/4 |  | 99/5 |  | 99/6 |  | 99/7 |  | 99/8 |  | 99/9 |  | 99/10 |  | 99/11 |  | 99/12
3DA+0 |  | 3DA+0 |  | 3DA+3 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0
| 422 |  | 417 |  | 400 |  | 421 |  | 419 |  | 402 |  | 402 |  | 411 |  | 355 |  | 390 |  | 380 |  | 390
100/0 |  | 100/1 |  | 100/2 |  | 100/3 |  | 100/4 |  | 100/5 |  | 100/6 |  | 100/7 |  | 100/8 |  | 101/0 |  | 101/1 |  | 101/2
3DB2+0 |  | 3DA+3 |  | 3DA+3 |  | 3DA+0 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3 |  | 3DA+0 |  | 3DB1+0 |  | 3DA+0 |  | 3DA+0
| 422 |  | 417 |  | 400 |  | 421 |  | 419 |  | 402 |  | 402 |  | 411 |  | 355 |  | 390 |  | 380 |  | 390
100/0 |  | 100/1 |  | 100/2 |  | 100/3 |  | 100/4 |  | 100/5 |  | 100/6 |  | 100/7 |  | 100/8 |  | 101/0 |  | 101/1 |  | 101/2
3DB2+0 |  | 3DA+3 |  | 3DA+3 |  | 3DA+0 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3 |  | 3DA+0 |  | 3DB1+0 |  | 3DA+0 |  | 3DA+0
C

## Master Sheet
| Project Code | TA-601 |  |  | Date as on | 08.01.2026 | SBU Head | Mr. Rajinder Gupta
| Project Name | 765kV D/C Kurnool IV - Bidar trnasmission line (Part II) |  |  | LOA Start Date | 13.05.2025 | PCH | Mr. Arun Felbin
| Client Name | POWERGRID KURNOOL IV TRANSMISSION LIMITED |  |  | LOA End Date | 12.04.2027 | Regional Manager | Mr. Ajith Kumar MG
| Duration | 23 Months |  |  | Planning Engineer | Mr. Siddhesh Bhoyar | Chief Manger | Mr. Senthil Jayaraman
Survey Status
Activity | Unit | Final Est. Qty | L2 till Last Month | Completed till Last Month | Approved till Last Month | Balance to Submit | Progress For Month | Balance to Approve | L2 Submission Plan for Current Month | Approved till Current Month | Remarks
Detailed Survey | kms | 113.286 | 0 | 113.286 | 109.04 | 0 | 0 | 4.25 | 0 | 109.04
Check Survey | kms | 113.286 | 110 | 111.745 | 96.901 | 9.448 | 0 | 16.385 | 8.6 | 96.901
.
Activity | Scope Quantity | Cumulative L2 till Last Month | Cumulative Progress till Last Month | L2 for present Month | Plan for the Month | Today's Progress | Progress till Date for the Month | L2 till Current Month | Completed till Date | Balance Work | Under Progress | Gangs at Present | Remarks
Foundation | 292 | 92 | 42 | 40 | 50 | 1 | 4 | 132 | 46 | 246 | 6 | 5 | 1) 56/9 - Pit A,B,C,D PCC Completed. 2) 83/0 - Excavation Completed. 3) 84/1 - Pit C,D Prop Setting Completed. 4) 84/5 - Foundation Completed.
Earthing | 292 | 92 | 10 | 40 | 50 | 0 | 5 | 132 | 15 | 277
Tower Erection | 292 | 50 | 3 | 35 | 30 | 1 | 2 | 85 | 5 | 287 | 2 | 2 | 1) 77/2 - Erection Completed. 2) 77/1 - Bottom Section Completed. 3) 58/1 - Cage2 WIP.
Stringing -R/S | 113.286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113.286
Stringing -F/S | 113.286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113.286
OPGW | 113.286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113.286
NH Crossing | 3 | [8 empty] | 3
SH Crossing | 1 | [8 empty] | 1
Railway crossing | 2 | [8 empty] | 2
Power Line Crossing | 6 | [8 empty] | 6
[6 empty] | Foundation Gangs at Site: | 1) MARC Contractors Ltd - 83/0 ( WIP) |  |  | 4) BALAJI INFRA - 84/5, 84/1, 85/2 (WIP)
[7 empty] | 2) SHRIARSHINI CONSTRUCTIONS - 56/9, 59/0 (WIP) |  |  | 5) SAI SREE VARSHINI - 100/1, 100/2
3) VKP Traders - 101/1, 101/2 (WIP)
Supply Status
Activity | Unit | Final Est. Qty | L2 till Last Month | Received till Last Month | Balance | L2 Plan for Current Month | Plan for Current Month | Progress for the Month | Received till Current Month | Gap between Supply & Cumm.L2 | Remarks
Stub | Set | 292 | 260 | 132 | 160 | 56 | 0 | 0 | 132 | 184
Tower | No's | 292 | 160 | 160 | 132 | 0 | 0 | 0 | 160 | 0
Conductor | kms | 4314 | 1700 | 1931.873 | 2382.127 | 400 | 400 | 163.577 | 2095.45 | 4.55 | AL59 Conductor 2095.45 Km/704 Drums Received.
Support Required :
1) DA Type RC Foundation Drawings (1MRC,2MRC,3MRC)
2) RC Stub Drawings Required- DB,DC,DD45,DD60 (1MRC,2MRC,3MRC)
3) RC Foundation Drawings Required- DB,DC,DD45,DD60 (1MRC,2MRC,3MRC)

## Progress Sheet
Survey Status
Activity | Unit | Final Est. Qty | L2 till Last Month |  | Completed till Last Month | Approved till Last Month | Balance to Submit | Balance to Approve | L2 Submission Plan for Current Month | Progress For Month | Approved till Current Month | Remarks
Detailed Survey | kms | 113.286 | 0 |  | 113.286 | 109.04 | 0 | 4.25 | 0 | 0 | 109.04
Check Survey | kms | 113.286 | 110 |  | 111.745 | 96.901 | 9.448 | 16.385 | 20 | 0 | 96.901
PROGRESS - Check Survey
S.No | Section |  | Length |  | Check survey status
PROGRESS - FDN & EREC
S.No | Location No. | Tower Type | Classification | ROW cleared date | Start Date | Conc Volume | Foundation Status |  |  |  | End Date | Gang Name | Erection Status | Gang Strength | Remarks
1 | 82/1 | DA+0 | WC | 2025-07-10 | 2025-07-11 | 22.4 | Foundation completed. |  |  |  | 2025-08-22 | MARC |  | 10
2 | 81/2 | DA+3 | DFR | 2025-07-16 | 2025-07-16 | 26.43 | Foundation completed. |  |  |  | 2025-08-07 | MARC |  | 10
3 | 81/1 | DA+0 | DFR | 2025-08-12 | 2025-08-23 | 23.27 | Foundation completed. |  |  |  | 2025-09-13 | MARC |  | 10
4 | 80/1 | DA+6 | WFR | 2025-08-28 | 2025-08-29 | 36.66 | Foundation completed. |  |  |  | 2025-10-10 | MARC |  | 10
5 | 80/5 | DA+0 | DRY | 2025-08-29 | 2025-09-02 | 21.96 | Foundation completed. |  |  |  | 2025-09-18 | MARC |  | 10
6 | 77/4 | DA+0 | DRY | 2025-09-16 | 2025-09-17 | 21.96 | Foundation Completed. |  |  |  | 2025-10-31 | BALRAJ CONSTRUCTION. |  | 10
7 | 80/4 | DA+3 | WFR | 2025-09-19 | 2025-09-23 | 36.66 | Foundation Completed. |  |  |  | 2025-10-27 | MARC |  | 10
8 | 59/5 | DA+0 | DRY | 2025-09-30 | 2025-10-08 | 21.96 | Foundation completed. |  |  |  | 2025-10-19 | SHRIARSHINI CONSTRUCTION. |  | 10
9 | 84/3 | DA+0 | DRY | 2025-09-19 | 2025-10-10 | 21.96 | Foundation completed. |  |  |  | 2025-10-19 | BALRAJ CONSTRUCTION. |  | 10
10 | 59/4 | DA+6 | DRY | 2025-10-03 | 2025-10-08 | 25.04 | Foundation completed. |  |  |  | 2025-10-21 | SHRIARSHINI CONSTRUCTION. |  | 20
11 | 84/4 | DA+0 | DRY | 2025-09-25 | 2025-10-11 | 21.96 | Foundation completed. |  |  |  | 2025-10-24 | BALRAJ CONSTRUCTION. |  | 10
12 | 60/2 | DA+0 | DFR |  | 2025-10-14 | 23.27 | Foundation completed. |  |  |  | 2025-10-25 | SHRIARSHINI CONSTRUCTION |  | 20
13 | 60/3 | DA+6 | DRY |  | 2025-10-23 | 25.04 | Foundation completed. |  |  |  | 2025-11-15 | SHRIARSHINI CONSTRUCTION |  | 15
14 | 77/10 | DA+3 | DRY |  | 2025-10-27 | 25.04 | Foundation completed. |  |  |  | 2025-11-05 | BALRAJ CONSTRUCTION. |  | 10
15 | 58/3 | DA+0 | DRY |  | 2025-12-09 | 21.96 | Foundation completed. |  |  |  | 2025-12-14 | SHRIARSHINI CONSTRUCTION |  | 21
16 | 84/2 | DA+0 |  |  |  |  | 2 Pits Excavated.
17 | 59/2 | DA+0 | DRY |  | 2025-10-29 | 21.96 | Foundation Completed. |  |  |  | 2025-11-08 | SHRIARSHINI CONSTRUCTION |  | 15
18 | 77/7 | DA+0 | DFR |  | 2025-11-02 | 23.27 | Foundation Completed. |  |  |  | 2025-11-09 | BALRAJ CONSTRUCTION. |  | 10
19 | 77/8 | DA+0 | DFR |  | 2025-11-02 | 23.27 | Foundation Completed. |  |  |  | 2025-11-13 | MARC |  | 10
20 | 77/1 | DA+0 | DRY |  | 2025-11-07 | 21.96 | Foundation Completed. |  |  |  | 2025-11-25 | MARC |  | 10
21 | 77/3 | DA+0 | DFR |  | 2025-11-07 | 23.27 | Foundation Completed. |  |  |  | 2025-11-19 | MARC |  | 10
22 | 60/8 | DA+3 | DFR |  | 2025-11-12 | 26.43 | Foundation Completed. |  |  |  | 2025-11-23 | SHRIARSHINI CONSTRUCTION |  | 10
23 | 77/2 | DA+0 | DRY |  | 2025-11-18 | 21.96 | Foundation Completed. |  |  |  | 2025-11-30 | MARC |  | 10
24 | 60/1 | DA+0 |  |  | 2025-11-22 |  | Trial Pit Excavated.
25 | 59/1 | DA+0 | DFR |  | 2025-11-23 | 23.27 | Foundation Completed. |  |  |  | 2025-11-29 | SHRIARSHINI CONSTRUCTION |  | 10
26 | 77/6 | DA+0 | WC |  | 2025-11-27 | 22.4 | Foundation Completed. |  |  |  | 2025-12-12 | MARC |  | 15
27 | 58/2 | DA+0 | DRY |  | 2025-11-27 | 21.96 | Foundation Completed. |  |  |  | 2025-12-03 | SHRIARSHINI CONSTRUCTION |  | 16
28 | 58/1 | DA+6 | DRY |  | 2025-12-01 | 25.04 | Foundation Completed. |  |  |  | 2025-12-08 | SHRIARSHINI CONSTRUCTION |  | 16
29 | 73/1 | DA+6 | WC |  | 2025-12-04 | 25.77 | Foundation Completed. |  |  |  | 2025-12-18 | BALAJI INFRA |  | 10
30 | 73/2 | DA+0 | WC |  | 2025-12-04 | 22.4 | Foundation Completed. |  |  |  | 2025-12-24 | BALAJI INFRA |  | 10
31 | 79/1 | DA+3 | WET |  | 2025-12-06 | 38.98 | Foundation Completed. |  |  |  | 2025-12-25 | MARC |  | 18
32 | 94/2 | DA+3 | WFR |  | 2025-12-06 | 36.66 | Excavation Completed. |  |  |  |  | VKP TRADERS
33 | 99/6 | DA+0 | DFR |  | 2025-12-07 | 23.27 | Foundation Completed. |  |  |  | 2025-12-20 | SAI SREE VARSHINI |  | 17
34 | 99/7 | DA+0 | DRY |  | 2025-12-07 | 21.96 | Foundation Completed. |  |  |  | 2025-12-15 | SAI SREE VARSHINI |  | 17
35 | 94/1 | DA+0 | DRY |  | 2025-12-10 | 21.96 | Foundation Completed. |  |  |  | 2025-12-31 | VKP TRADERS |  | 10
36 | 99/8 | DA+0 | DFR |  | 2025-12-14 |  | Foundation Completed. |  |  |  | 2025-12-26 | SAI SREE VARSHINI |  | 17
37 | 99/9 | DA+0 | DRY |  | 2025-12-14 | 21.96 | Foundation Completed. |  |  |  | 2025-12-23 | SAI SREE VARSHINI |  | 17
39 | 55/3 | DA+0 | DRY |  | 2025-12-25 |  | Foundation Completed. |  |  |  | 2025-12-31 | SHRIARSHINI CONSTRUCTION |  | 21
40 | 56/2 | DA+3 | DRY |  | 2025-12-17 | 25.04 | Foundation Completed. |  |  |  | 2025-12-27 | SHRIARSHINI CONSTRUCTION |  | 21
41 | 56/3 | DA+0 | DFR |  | 2025-12-14 | 23.27 | Foundation Completed. |  |  |  | 2025-12-19 | SHRIARSHINI CONSTRUCTION |  | 21
42 | 79/2 | DA+6 | DFR |  |  |  | Foundation Completed. |  |  |  | 2026-01-05 | MARC |  | 18
43 | 79/3 | DA+9 | DFR |  | 2025-12-19 |  | Foundation Completed. |  |  |  | 2025-12-30 | MARC |  | 18
44 | 56/1 | DA+3 | DFR |  | 2025-12-21 | 26.43 | Foundation Completed. |  |  |  | 2025-12-24 | SHRIARSHINI CONSTRUCTION |  | 21
45 | 99/10 | DA+0 | DFR |  | 2025-12-22 | 23.27 | Foundation Completed. |  |  |  | 2025-12-29 | SAI SREE VARSHINI |  | 17
46 | 99/11 | DA+0 |  |  | 2025-12-27 |  | Foundation Completed. |  |  |  | 2025-12-31 | SAI SREE VARSHINI |  | 17
47 | 84/5 | DA+9 | DRY |  |  |  | Pit A,C RCC Chimney Completed. |  |  |  | 2026-01-08 | BALAJI INFRA |  | 10
48 | 84//6 | DA+0 |  |  |  |  | Foundation Completed. |  |  |  | 2025-12-31 | BALAJI INFRA |  | 10
49 | 56/4 | DA+3 | WET |  | 2025-12-01 |  | Foundation Completed. |  |  |  | 2026-01-06 | SHRIARSHINI CONSTRUCTION |  | 21
50 | 99/12 | DA+0 | DRY |  | 2025-12-31 |  | Foundation Completed. |  |  |  | 2026-01-06 | SAI SREE VARSHINI |  | 17
51 | 56/9 | DA+6 | DRY |  | 2026-01-04 |  | Pit A,B,C,D PCC Completed. |  |  |  |  | SHRIARSHINI CONSTRUCTION |  | 21
52 | 100/1 | DA+3 |  |  | 2026-01-04 |  | Excavation Completed. |  |  |  |  | SAI SREE VARSHINI
53 | 100/2 | DA+3 |  |  |  |  | Excavation Completed. |  |  |  |  | SAI SREE VARSHINI
54 | 83/0 | DB2+6 |  |  | 2026-01-06 |  | Excavation Completed. |  |  |  |  | BALAJI INFRA
55 | 84/1 | DA+6 |  |  | 2026-01-04 |  | Pit C,D Prop Setting Completed. |  |  |  |  | BALAJI INFRA |  | 12
56 | 85/2 | DA+0 |  |  | 2026-01-06 |  | Excavation WIP. |  |  |  |  | BALAJI INFRA
57 | 59/0 | DC1+0 |  |  | 2026-01-07 |  | Excavation WIP. |  |  |  |  | SHRIARSHINI CONSTRUCTION
EARTHING
SL No. | Location No. | Tower Type | Classification | ROW cleared date | Start Date | Status |  |  |  | End Date | Gang Name | Remark
1 | 82/1 | DA+0 | WC | 2025-07-10 | 2025-09-08 | Earthing Completed. |  |  |  | 2025-09-08 | MARC
2 | 80/5 | DA+0 | DRY | 2025-08-29 | 2025-09-24 | Earthing Completed. |  |  |  | 2025-09-24 | MARC
3 | 59/4 | DA+6 | DRY | 2025-10-03 | 2025-10-19 | Earthing Completed. |  |  |  | 2025-10-19 | SHRIARSHINI CONSTRUCTION
4 | 77/1 | DA+0 | DRY |  | 2025-12-01 | Earthing Completed. |  |  |  | 2025-12-01 | MARC
5 | 77/2 | DA+0 | DRY |  | 2025-12-19 | Earthing Completed. |  |  |  | 2025-12-19 | MARC
6 | 77/3 | DA+0 | DFR |  |  | Earthing Completed. |  |  |  |  | MARC
7 | 77/6 | DA+0 | WC |  | 2025-12-20 | Earthing Completed. |  |  |  | 2025-12-20 | MARC
8 | 56/3 | DA+0 | DFR |  | 2025-12-25 | Earthing Completed. |  |  |  | 2025-12-25 | SHRIARSHINI CONSTRUCTION
9 | 80/1 | DA+6 | WFR |  | 2025-12-30 | Earthing Completed. |  |  |  | 2025-12-30 | MARC
10 | 79/1 | DA+3 | WET |  |  | Earthing Completed. |  |  |  |  | MARC
11 | 99/7 | DA+0 | DRY |  |  | Earthing Completed. |  |  |  |  | SAI SREE VARSHINI
12 | 99/8 | DA+0 | DFR |  |  | Earthing Completed. |  |  |  |  | SAI SREE VARSHINI
13 | 99/10 | DA+0 | DFR |  |  | Earthing Completed. |  |  |  |  | SAI SREE VARSHINI
14 | 99/11 | DA+0 | DFR |  |  | Earthing Completed. |  |  |  |  | SAI SREE VARSHINI
Stringing
S.No | Section | Length | Status |  |  |  |  | Gang Name | Gang Strength | RouGH SaG | F!n@L sAG | E@rthwire
OPGW Stringing
S.No | Section | Length | Status |  |  |  |  | Gang Name | Gang Strength | Remarks
Erection
SL No. | Location No. | Tower Type | Classification |  | Start Date | MT | Status |  |  |  | End Date | Gang Name | Gang Strength | Remark
1 | 59/1 | DA+0 | DFR |  | 2025-12-15 | 36.574 | Erection Completed. |  |  |  | 2025-12-20 | NASIRUDDIN | 35
2 | 77/3 | DA+0 | DFR |  | 2025-12-22 | 36.574 | Erection Completed. |  |  |  | 2025-12-31 | ALI USLAM | 25
3 | 59/2 | DA+0 | DRY |  | 2025-12-22 | 36.574 | Erection Completed. |  |  |  | 2025-12-27 | NASIRUDDIN | 35
4 | 77/2 | DA+0 | DRY |  | 2025-12-25 | 36.574 | Erection Completed. |  |  |  | 2026-01-08 | UMA DEVI | 25
5 | 58/2 | DA+0 | DRY |  | 2025-12-25 | 36.574 | Erection Completed. |  |  |  | 2026-01-02 | NASIRUDDIN | 35
6 | 77/1 | DA+0 | DRY |  | 2026-01-01 | 36.574 | Bottom Section Completed. |  |  |  |  | UMA DEVI | 25
7 | 58/1 | DA+6 | DRY |  | 2026-01-02 |  | Cage2 WIP. |  |  |  |  | NASIRUDDIN | 35
Formulas:
ROW cleared date = [Completed till Last Month]

## Erection Compiled
SL No. | Location No. | Tower Type | Classification | Starting Date | Tower Weight | Status | Completion Date | Gang Name | Gang Strength | Remark
1 | 59/1 | DA+0 | DFR | 2025-12-15 | 36.574 | Erection Completed. | 2025-12-20 | NASIRUDDIN | 35
2 | 77/3 | DA+0 | DFR | 2025-12-22 | 36.574 | Erection Completed. | 2025-12-31 | ALI USLAM | 25
3 | 59/2 | DA+0 | DRY | 2025-12-22 | 36.574 | Erection Completed. | 2025-12-27 | NASIRUDDIN | 35
4 | 77/2 | DA+0 | DRY | 2025-12-25 | 36.574 | Erection Completed. | 2026-01-08 | UMA DEVI | 25
5 | 58/2 | DA+0 | DRY | 2025-12-25 | 36.574 | Erection Completed. | 2026-01-02 | NASIRUDDIN | 35
6 | 77/1 | DA+0 | DRY | 2026-01-01 | 36.574 | Bottom Section Completed. |  | UMA DEVI | 25
7 | 58/1 | DA+6 | DRY | 2026-01-02 |  | Cage2 WIP. |  | NASIRUDDIN | 35

## ROW
TL-02 765kV Kurnool IV - Bidar line
Foundation
Sr. No. | Location no. | Type of tower | Date of clearance
1 | 82/1 | DA+0 | 2025-07-10
2 | 81/2 | DA+3 | 2025-07-16
3 | 81/1 | DA+0 | 2025-08-12
4 | 83/2 | DA+9 | 2025-08-14
5 | 84/2 | DA+0 | 2025-08-16
6 | 80/1 | DA+6 | 2025-08-28
7 | 80/5 | DA+3 | 2025-08-29
8 | 77/4 | DA+0 | 2025-09-16
9 | 84/3 | DA+0 | 2025-09-19
10 | 84/2 | DA+0 | 2025-09-19
11 | 80/4 | DA+3 | 2025-09-19
12 | 84/4 | DA+0 | 2025-09-25
13 | 59/5 | DA+0 | 2025-09-30
14 | 60/3 | DA+6 | 2025-10-01
15 | 59/4 | DA+6 | 2025-10-03
16 | 60/2 | DA+0

## X-ing Details
CROSSINGS PROPOSAL STATUS : 765 KV D/C Kurnool IV - Bidar TL (Part-2)
Crossing Type | 132 KV | 220kV | SH-Xing | NH-Xing | Railway-Xing | Total
Total Nos | 4 | 2 | 1 | 3 | 2 | 12
Submitted Till Date | 4 | 2 | 0 | 3 | 2 | 11
Approved Till Date | 0 | 0 | 0 | 0 | 0 | 0
Balance to Execute | 0 | 0 | 1 | 0 | 0 | 0
Crossings Details
Sl. No. | FROM (AP) | TO (AP) | Name of the Line | NAME OF CROSSING | Date of First Submission | Joint Inspection Status | Provisional approval status
1 | AP54 | AP55 | Railway crossing (Tandur - Vikarabad) | Railway crossing | 2025-11-26
2 | AP57 | AP58 | 220kV D/C transmission line Tandur - Gachibowli (HYD) | Power line | 2025-10-16
3 | AP61 | AP62 | NATIONAL HIGHWAY-163 (Kodangal - Hyderabad) | National highway crossing | 2025-11-28
4 | AP71 | AP72 | 132kV D/C transmission line Tandur - Mahabubnagar | Power line | 2025-10-14
5 | AP74 | AP75 | NATIONAL HIGHWAY-167N (Kodangal - Kosgi) | National highway crossing | 2025-11-28
6 | AP76 | AP77 | 220kV D/C transmission line Kosgi - Pargi | Power line | 2025-10-16
7 | AP88 | AP89 | 132kV S/C transmission line Maddur - Mahabubnagar | Power line | 2025-10-16
8 | AP95 | AP96 | 132kV S/C transmission line Maddur - Makthal | Power line | 2025-10-16
9 | AP98 | AP99 | STATE HIGHWAY-22 (Narayanpet - Marikal) | State highway crossing
10 | AP106 | AP107 | Railway crossing (Raichur - Makthal) | Railway crossing | 2025-11-27
11 | AP109 | AP110 | 132kV S/C transmission line Makthal - Krishna Railway junction | Power line | 08.12.2025
12 | AP110 | AP111 | NATIONAL HIGHWAY-167N (Raichur - Marikal) | National highway crossing | 08.12.2025

## SuPPLY
Supply Status - Stubs & Towers
Stub Details
SL No | Description | Unit | Line Qty | Received | Balance
1 | 3DA Stub | Set |  | 120
2 | 3DB Stub | Set |  | 5
3 | 3DC Stub | Set |  | 3
4 | 3D45 Stub | Set |  | 2
5 | 3D60 Stub | Set |  | 2
| Total | Set | 0 | 132 | 0 | 0 | 0
Tower Details
SL No | Tower Type | Description | Line Qty | Received | Balance |  |  | Remarks
1 | 3DA Type | Basic body |  | 126
|  | +0m BE |  | 104
|  | +3m BE |  | 22
|  | +6m BE |  | 13
|  | +9m BE |  | 5
2 | 3DB Type | Basic body |  | 20
|  | +0m BE |  | 20
+3m BE
+6m BE
|  | +9m BE |  | 5
3 | 3DC Type | Basic body |  | 14
|  | +0m BE |  | 11
|  | +3m BE |  | 3
+6m BE
|  | +9m BE |  | 3
4 | 3DD45 Type | Basic body | [6 empty] | Balance after June'25
+0m BE
+3m BE
+6m BE
+9m BE
5 | 3DD60 Type | Basic body
+0m BE
+3m BE
+6m BE
+9m BE
Total
Activity | Unit | Final Est. Qty | L2 till Last Month | Received till Last Month | Balance | L2 Plan for Current Month | Plan for Current Month | Progress for the Month | Received till Current Month | Gap between Suppy & Cumm.L2 | Remarks
Stub | Set | 292 | 260 | 132 | 160 | 56 | 0 | 0 | 132 | 184
Tower | No's | 292 | 160 | 160 | 132 | 0 | 0 | 0 | 160 | 0
Conductor | kms | 4314 | 1700 | 1931.873 | 2382.127 | 400 | 400 | 163.577 | 2095.45 | 4.55 | AL59 Conductor 1931.873 Km/ 649 Drums Received.
Cummulative progress till Previous Month
S No | Item | Unit | Total QTY | Planned L2 till Previous Month (Nov'25) | Completed till Previous month (Nov'25) | L2 Planned for Current Month (Approved L2) | Balance after Nov'25 | Jan'25 Month Plan | Jan Month Progress | Cummulative Completed | Balance
1 | Supply of Stubs | Sets | 292 | 260 | 132 | 56 | 160 | 0 | 0 | 132 | 160
2 | Supply of Towers | Nos | 292 | 80 | 79 | 0 | 213 | 80 | 81 | 160 | 132
3 | Supply of Earthwire | Km | 121 | 50 | 50.07 | 0 | 70.93 | 0 | 0 | 50.07 | 70.93
4 | Supply of Conductor | Km | 4314 | 1300 | 1516.153 | 400 | 2797.847 | 400 | 415.72 | 2095.45 | 2218.55
5 | Supply of H/W Fittings | % | 100% | 0% | 0% | 40% | 100% | 40% | 0 | 0 | 100%
6 | Supply of Insultor | Nos | 7200 | 0 | 0 | 2450 | 7200 | 2450 | 0 | 0 | 7200
7 | Supply of OPGW | km | 123 | 0 | 0 | 0 | 123 | 0 | 0 | 0 | 123
8 | Supply of OPGW Accessories | % | 100% | 0 | 0% | 0 | 100% | 0 | 0 | 0 | 100%
9 | Supply of Earthing Materials | % | 100% | 25% | 42% | 30% | 58% | 23% | 0% | 42% | 58% | 0.16892
10 | Supply of Earthwire Accessories | % | 100% | 0 | 0% | 40% | 100% | 40% | 0% | 0% | 100% | 0.44595
11 | Supply of Tower Accessories | % | 100% | 0 | 0% | 0 | 100% | 0% | 0% | 0 | 100%
12 | Supply of Conductor Accessories | % | 100% | 0 | 0% | 40% | 100% | 40% | 0% | 0 | 100%

## Visual Chart
VISUAL PROGRESS CHART
765 kV DC Kurnool IV - Bidar Transmission Line (TL-02)
| Foundation (Nos.):- |  | 46 | / 292 | Erection (Nos.):- |  | 5 | /292 | Earthing (Nos.):- |  |  | 15/292 | Rough Sag (Kms):- |  | 0 / | 113.292 | Final Sag (Kms):- |  | 0 / | 113.292 | Date:- | 2026-01-13
| COMPLETION CHART | Unit |  | +3 | +6 | +9 | 18 | Line Qty
[9 empty] | ERECTION | [5 empty] | Rough Sag |  | SH / NH Road Crossing
[9 empty] | WIP | [11 empty] | River
| DA | Nos | 136 | 47 | 21 | 12 | 216 | 216 | FOUNDATION | Type |  | Angle Tower |  |  |  |  | Gas Pipeline
| DB1 | Nos | 8 | 2 | 1 | 9 | 20 | 20
| DB2 | Nos | 11 | 2 | 4 | 1 | 18 | 18 | [5 empty] | Final Sag
| DC1 | Nos | 10 | 2 | 1 | 4 | 17 | 17
| DC2 | Nos | 3 | 3 | 1 | 0 | 7 | 7 | [9 empty] | Railway
| DCT | Nos | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | WIP |  | Crossing
| DD45 | Nos | 3 | 1 | 1 | 4 | 9 | 9 | Section Tower | SC | [10 empty] | 110-800 KV
| DD60 | Nos | 2 | 2 | 0 | 1 | 5 | 5 | TP | TT |  | Earthing |  |  | OPGW | [5 empty] | Line
| Total Completed Foundations | [5 empty] | 46 | 246
| Wind Zone - 3 [AP48 - AP111] |  |  |  | AP48 to AP77 : VIKRABAD DISTRICT
AP77 to AP111 : NARAYANPET DISTRICT
COMMON POINT
|  | 411 |  | 432 |  | 411 |  | 432 |  | 411 |  | 432 |  | 411 |  | 374.437 |  | 376.003 |  | 405 | RC | 340 |  | 397
| AP48/0 |  | 48/1 |  | 48/2 |  | 48/3 |  | 48/4 |  | 48/5 |  | 48/6 |  | 48/7 |  | AP49/0 |  | 49/1 |  | 49/2 |  | 49/3
| DB1+0 |  | 3DA+6 |  | 3DA+0 |  | 3DA+6 |  | 3DA+3 |  | 3DA+3 |  | 3DA+3 |  | 3DA+3 |  | 3DC1+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0
| 3.314 | [22 empty] | 4.832
|  | 399 | RC | 393 | RC | 370 | RC | 350 | RC | 395 |  | 413 | RC | 366 |  | 377.77 |  | 300 |  | 393 |  | 415 |  | 411
| 49/4 |  | 49/5 |  | 49/6 |  | 49/7 |  | 49/8 |  | 49/9 |  | 49/10 |  | 49/11 |  | AP50/0 |  | 50/1 |  | 50/2 |  | 50/3
| 3DA+0 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DC2+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3
| 4.582 | [15 empty] | 1.519 | [6 empty] | 4.583
|  | 378 |  | 370 |  | 370 |  | 404 |  | 374 |  | 416 | RC | 425 | RC | 411 | RC | 427 |  | 370 | RC | 356 |  | 459
| AP51/0 |  | 51/1 |  | 51/2 |  | 51/3 |  | 51/4 |  | 51/5 |  | 51/6 |  | 51/7 |  | 51/8 |  | 51/9 |  | 51/10 |  | AP52/0
| 3DC2+0 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3 |  | 3DA+3 |  | 3DA+0 |  | 3DA+3 |  | 3DA+0 |  | 3DB2+0
| 4.301 | [22 empty] | 4.76
| RC | 355 | RC | 348 |  | 434 | RC | 401 |  | 400 |  | 413 |  | 406 | RC | 390 |  | 390 | RC | 430 | RC | 332 |  | 229.642
| 52/1 |  | 52/2 |  | 52/3 |  | 52/4 |  | AP53/0 |  | 53/1 |  | 53/2 |  | 53/3 |  | 53/4 |  | 53/5 |  | 53/6 |  | AP54/0
| 3DA+9 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DB1+3 |  | 3DA+3 |  | 3DA+0 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3 |  | 3DD60+0
| 1.997 | [7 empty] | 2.761 | [13 empty] | 0.23 | 4.529
|  | 339 |  | 365 |  | 409 | SRIARSHINI | 340.462 | RC | 352 | SRIARSHINI | 419 | SRIARSHINI | 410 | SRIARSHINI | 413 | SRIARSHINI | 407 | RC | 351 |  | 405 | SRIARSHINI | 393
| AP55/0 |  | 55/1 |  | 55/2 |  | 55/3 |  | AP56/0 |  | 56/1 |  | 56/2 |  | 56/3 |  | 56/4 |  | 56/5 |  | 56/6 |  | 56/7
| 3DD60+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DB2+0 |  | 3DA+3 |  | 3DA+3 |  | 3DA+0 |  | 3DA+3 |  | 3DA+3 |  | 3DA+0 | 2.757 | 3DB1+0
| 1.453 | [22 empty] | 4.603
|  | 439 | SRIARSHINI | 398 | RC | 445 | RC | 355 |  | 445.645 | RC | 214.742 |  | 498 | SRIARSHINI | 325 | SRIARSHINI | 372 | SRIARSHINI | 393.054 | SRIARSHINI | 349 | SRIARSHINI | 373
| 56/8 |  | 56/9 |  | 56/10 |  | 56/11 |  | 56/12 |  | AP57/0 |  | AP58/0 |  | 58/1 |  | 58/2 |  | 58/3 |  | AP59/0 |  | 59/1
| 3DA+0 |  | 3DA+6 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 | 2.4756 | 3DC1+9 |  | 3DB2+6 |  | 3DA+6 |  | 3DA+0 |  | 3DA+0 |  | 3DC1+0 |  | 3DA+0 |  | `
| 5.233 | [9 empty] | 0.215 |  | 1.588 | [10 empty] | 4.607
| SRIARSHINI | 386 |  | 429 | SRIARSHINI | 377 | SRIARSHINI | 401.837 |  | 402 |  | 344 | SRIARSHINI | 399 | SRIHARSHINI | 439 | RC | 403 |  | 480 | RC | 535 | RC | 389.004
| 59/2 |  | 59/3 |  | 59/4 |  | 59/5 |  | AP60/0 |  | 60/1 |  | 60/2 |  | 60/3 |  | 60/4 |  | 60/5 |  | 60/6 |  | 60/7
| 3DA+0 |  | 3DA+0 |  | 3DA+6 |  | 3DA+0 |  | 3DB2+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+6 |  | 3DA+0 | 1.987 | 3DB1+6 | 0.48 | 3DB1+9 | 0.535 | 3DB1+9
| 2.316 | [22 empty] | 4.985
| SRIARSHINI | 454.047 |  | 247.492 | RC | 373 | RC | 401 | RC | 388 | RC | 328 | RC | 329.982 | RC | 433 |  | 410 | RC | 307 | RC | 461.927 | RC | 439.047
| 60/8 |  | AP61/0 |  | AP62/0 |  | 62/1 |  | 62/2 |  | 62/3 |  | 62/4 |  | AP63/0 |  | 63/1 |  | 63/2 |  | 63/3 |  | AP64/0
| 3DA+3 | 0.84305 | 3DB1+0 |  | 3DC1+0 |  | 3DA+0 |  | 3DA+9 |  | 3DA+0 |  | 3DA+0 |  | 3DC2+0 |  | 3DA+9 |  | 3DA+3 |  | 3DA+9 |  | 3DD45+9 | 0.43905
| 3.845 |  | 0.247 |  | 1.82 | [9 empty] | 1.612 | [7 empty] | 0.439 | 4.572
| RC | 401 |  | 350 | RC | 335 |  | 313.49 | RC | 421 |  | 465.818 | RC | 352 |  | 403 | RC | 373 | RC | 362 | RC | 351.24 | RC | 361
| AP65/0 |  | 65/1 |  | 65/2 |  | 65/3 |  | AP66/0 |  | 66/1 |  | AP67/0 |  | 67/1 |  | 67/2 |  | 67/3 |  | 67/4 |  | AP68/0
| 3DC2+3 |  | 3DA+0 |  | 3DA+3 |  | 3DA+0 |  | 3DB2+0 | 0.421 | 3DB1+9 | 0.46582 | 3DD45+3 |  | 3DA+6 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3 |  | 3DB2+0
| 1.399 | [7 empty] | 0.887 |  |  |  | 1.841 | [10 empty] | 4.489
| RC | 375 | RC | 424.851 |  | 414 |  | 345 | RC | 502.628 | RC | 453 |  | 388 | RC | 317 |  | 324 |  | 484.984 | RC | 248.518 |  | 429
| 68/1 |  | 68/2 |  | AP69/0 |  | 69/1 |  | 69/2 |  | AP70/0 |  | 70/1 |  | 70/2 |  | 70/3 |  | 70/4 |  | AP71/0 |  | AP72/0
| 3DA+3 |  | 3DA+3 |  | 3DB2+6 |  | 3DA+9 |  | 3DA+6 |  | 3DC2+3 |  | 3DA+9 |  | 3DA+0 |  | 3DA+0 |  | 3DA+6 |  | 3DC2+6 |  | 3DB2+6
| 1.161 |  |  |  | 1.262 | [5 empty] | 1.967 | [9 empty] | 0.249 |  |  | 4.706
|  | 398.684 |  | 435 | Balaji Infra | 404 | Balaji Infra | 374.353 |  | 250.119 | RC | 398 | RC | 364 | RC | 380 | RC | 459.272 | RC | 206.441 | RC | 385 | MARC | 372
| 72/1 |  | AP73/0 |  | 73/1 |  | 73/2 |  | AP74/0 |  | AP75/0 |  | 75/1 |  | 75/2 |  | 75/3 |  | AP76/0 |  | AP77/0 |  | 77/1
| 3DA+3 |  | 3DB2+0 |  | 3DA+6 |  | 3DA+0 |  | 3DC1+0 |  | 3DC1+0 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DC1+9 |  | 3DD45+9 |  | 3DA+0
| 0.828 |  | 1.213 | [5 empty] | 0.25 |  | 1.601 | [7 empty] | 0.206 |  |  |  |  | 4.427
| MARC | 384 | MARC | 400 | BALRAJ | 386 |  | 398 | MARC | 393 | BALRAJ | 387 | BALRAJ | 378 | RC | 410 | BALRAJ | 367.58 | RC | 396 | RC | 395 |  | 414
| 77/2 |  | 77/3 |  | 77/4 |  | 77/5 |  | 77/6 |  | 77/7 |  | 77/8 |  | 77/9 |  | 77/10 |  | AP78/0 |  | 78/1 |  | 78/2
| 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3 |  | 3DC1+0 |  | 3DA+3 |  | 3DA+3
| 4.261 | [22 empty] | 4.709
|  | 350.09 | RC | 364 | MARC | 452 | MARC | 392 | MARC | 369.645 | RC | 446 | MARC | 386 |  | 451 |  | 428.504 | MARC | 354.496 | MARC | 430.207 | RC | 394
| 78/3 |  | AP79/0 |  | 79/1 |  | 79/2 |  | 79/3 |  | AP80/0 |  | 80/1 |  | 80/2 |  | 80/3 |  | 80/4 |  | 80/5 |  | AP81/0
| 3DA+0 |  | 3DC1+0 |  | 3DA+3 |  | 3DA+6 |  | 3DA+9 |  | 3DB2+9 |  | 3DA+6 |  | 3DA+9 | 1.283 | 3DB1+3 |  | 3DA+3 |  | 3DA+0 | 1.2132 | 3DD45+9
| 1.555 |  | 1.578 | [7 empty] | 2.496 | [12 empty] | 4.818
| MARC | 415 | MARC | 399 |  | 436.295 |  | 437 | MARC | 406 | RC | 437.796 | MARC | 412 |  | 356.628 | RC | 384.624 | RC | 391 | MARC | 436 |  | 406
| 81/1 |  | 81/2 |  | 81/3 |  | AP82/0 |  | 82/1 |  | 82/2 |  | AP83/0 |  | 83/1 |  | 83/2 |  | AP 84/0 |  | 84/1 |  | 84/2
| 3DA+0 |  | 3DA+3 |  | 3DA+0 |  | 3DC1+9 |  | 3DA+0 |  | 3DA+6 |  | 3DB2+6 |  | 3DA+0 |  | 3DA+9 |  | 3DB1+0 |  | 3DA+6 |  | 3DA+0
| 1.644 | [5 empty] | 1.281 | [5 empty] | 1.153 | [10 empty] | 4.917
| BALRAJ | 359 | BALRAJ | 439 | Balaji Infra | 393 | Balaji Infra | 314.949 |  | 437.001 |  | 399 | Balaji Infra | 303 |  | 337 |  | 339.169 | RC | 400 | RC | 358.849 | RC | 468.492
| 84/3 |  | 84/4 |  | 84/5 |  | 84/6 |  | AP 85/0 |  | 85/1 |  | 85/2 |  | 85/3 |  | 85/4 |  | AP 86/0 |  | 86/1 |  | AP 87/0
| 3DA+0 |  | 3DA+0 |  | 3DA+9 |  | 3DA+0 |  | 3DB1+0 |  | 3DA+9 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DC1+6 |  | 3DA+3 |  | 3DC1+3 | 0.46849
| 2.739 | [7 empty] | 1.815 | [9 empty] | 0.759 |  |  |  | 0.468 | 4.548
| RC | 287.352 | RC | 416 | RC | 352.354 |  | 361 |  | 426 | RC | 394 | RC | 384 | RC | 414 | RC | 480 | RC | 395 | RC | 329 | RC | 417.945
| AP 88/0 |  | AP 89/0 |  | 89/1 |  | AP 90/0 |  | 90/1 |  | 90/2 |  | 90/3 |  | 90/4 |  | 90/5 |  | AP 91/0 |  | 91/1 |  | 91/2
| 3DB1+9 |  | 3DC1+9 |  | 3DA+0 |  | 3DB2+0 |  | 3DA+3 |  | 3DA+0 |  | 3DA+3 |  | 3DA+0 | 1.979 | 3DB1+9 | 0.48 | 3DC2+3 |  | 3DA+3 |  | 3DA+6
| 0.287 |  | 0.768 |  |  |  | 2.459 | [11 empty] | 1.142 |  |  |  |  | 4.657
| RC | 467 | RC | 443 | RC | 310.743 | RC | 479 | RC | 321 |  | 506 | RC | 421.207 | RC | 421 | VKP Traders | 406 |  | 435 | RC | 532.759 | RC | 265.465
| AP 92/0 |  | 92/1 |  | 92/2 |  | AP 93/0 |  | 93/1 |  | 93/2 |  | 93/3 |  | AP 94/0 |  | 94/1 |  | 94/2 |  | 94/3 |  | AP 95/0
| 3DD45+0 | 0.467 | 3DB1+9 |  | 3DA+0 | 0.75374 | 3DB2+3 |  | 3DA+3 |  | 3DA+9 | 1.306 | 3DB1+9 | 0.42121 | 3DC1+3 |  | 3DA+0 |  | 3DA+3 | 1.262 | 3DB1+9 | 0.53276 | 3DD45+9 | 0.26546
| 1.221 | [5 empty] | 1.727 | [7 empty] | 1.795 | [7 empty] | 0.265 | 5.008
| RC | 484 | RC | 611 | RC | 367 | RC | 468.584 | RC | 371.416 | RC | 370 |  | 327 | RC | 318 |  | 339.769 |  | 395.999 |  | 377 |  | 398
| AP 96/0 |  | 96/1 |  | 96/2 |  | 96/3 |  | 96/4 |  | 96/5 |  | 96/6 |  | 96/7 |  | 96/8 |  | AP 97/0 |  | 97/1 |  | 97/2
| 3DD45+6 | 0.484 | 3DB1+0 | 0.611 | 3DB1+0 |  | 3DA+6 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 | 2.5618 | 3DB2+0 |  | 3DA+3 |  | 3DA+0
| 3.657 | [22 empty] | 4.828
|  | 393 |  | 373.66 |  | 363 |  | 349 |  | 386 |  | 390 |  | 417 |  | 422.997 |  | 340 |  | 365 | RC | 403 |  | 382
| 97/3 |  | 97/4 |  | AP 98/0 |  | 98/1 |  | 98/2 |  | 98/3 |  | 98/4 |  | 98/5 |  | AP 99/0 |  | 99/1 |  | 99/2 |  | 99/3
| 3DA+0 |  | 3DA+3 |  | 3DC1+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+6 |  | 3DC1+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3
| 1.938 |  |  |  | 2.328 | [18 empty] | 4.585
| RC | 395 | RC | 385 | S S Varshini | 381 | S S Varshini | 395 | S S Varshini | 403 | S S Varshini | 383 | S S Varshini | 386 | S S Varshini | 397 | S S Varshini | 370.834 |  | 422 | S S Varshini | 417 | S S Varshini | 400
| 99/4 |  | 99/5 |  | 99/6 |  | 99/7 |  | 99/8 |  | 99/9 |  | 99/10 |  | 99/11 |  | 99/12 |  | AP 100/0 |  | 100/1 |  | 100/2
| 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DB2+0 |  | 3DA+3 |  | 3DA+3
| 4.986 | [22 empty] | 4.735
|  | 421 |  | 419 | RC | 402 |  | 402 |  | 411 |  | 355.169 | S S Varshini | 390 |  | 380 |  | 390 |  | 398 |  | 406 |  | 371
| 100/3 |  | 100/4 |  | 100/5 |  | 100/6 |  | 100/7 |  | 100/8 |  | AP 101/0 |  | 101/1 |  | 101/2 |  | 101/3 |  | 101/4 |  | 101/5
| 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3 |  | 3DA+0 | 3.6492 | 3DB1+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0
| 3.649 | [22 empty] | 4.745
|  | 392 |  | 390 | RC | 401 | RC | 406.005 |  | 385 |  | 380 |  | 380 |  | 382 |  | 383.991 |  | 392.295 | RC | 401.31 |  | 352
| 101/6 |  | 101/7 |  | 101/8 |  | 101/9 |  | AP 102/0 |  | 102/1 |  | 102/2 |  | 102/3 |  | 102/4 |  | 102/5 |  | 102/6 |  | AP 103/0
| 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DB2+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DB2+0
| 3.924 | [7 empty] | 2.705 | [14 empty] | 4.646
|  | 368 |  | 440 |  | 364.132 |  | 407 |  | 375 |  | 313 |  | 388 | RC | 414 | RC | 385 |  | 360 |  | 382 |  | 415
| 103/1 |  | 103/2 |  | 103/3 |  | AP 104/0 |  | 104/1 |  | 104/2 |  | 104/3 |  | 104/4 |  | 104/5 |  | 104/6 |  | 104/7 |  | 104/8
| 3DA+0 |  | 3DA+0 |  | 3DA+6 |  | 3DC1+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+6 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0
| 1.524 | [22 empty] | 4.611
| RC | 429 |  | 383 |  | 447.107 | RC | 416 |  | 389 |  | 380 | RC | 362.384 | RC | 263.31 |  | 393 | RC | 384.17 |  | 348 |  | 350
| 104/9 |  | 104/10 |  | 104/11 |  | AP 105/0 |  | 105/1 |  | 105/2 |  | 105/3 |  | AP 106/0 |  | AP 107/0 |  | 107/1 |  | AP 108/0 |  | 108/1
| 3DA+3 |  | 3DA+6 |  | 3DA+6 |  | 3DB2+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DD60+3 |  | 3DD60+3 |  | 3DA+0 |  | 3DD45+0 |  | 3DA+0
| 4.698 | [5 empty] | 1.547 | [7 empty] | 0.263 |  | 0.777 | [6 empty] | 4.545
[11 empty] | Foundation: | [5 empty] | Erection:
|  | 429 |  | 194.628 |  | 203.141 |  |  |  | 1 | G1 | MARC |  |  | WORKING |  | G1 | NASIRUDDIN |  | WORKING
[10 empty] | 2 | G2 | BALAJI INFRA |  |  | WORKING |  | G2 | ALI USLAM |  | WORKING
| 108/2 |  | AP 109/0 |  | AP 110/0 |  | AP 111/0 |  |  | 3 | G3 | VKP TRADERS |  |  | WORKING |  | G3 | UMA DEVI |  | WORKING
| 3DA+0 |  | 3DB1+9 |  | 3DD60+9 |  | 3DD45+0 |  |  | 4 | G4 | SRIHARSHINI |  |  | WORKING
| 1.127 |  | 0.195 |  | 0.203 |  | COMMON POINT |  | 0.826 | 5 | G5 | S S VARSHINI |  |  | WORKING
C
B