## Visual Chart
Name of Line:- 765 KV D/C Mandsaur - Kurawar (Part-1)Transmission Line(WZ-4)
[19 empty] | Visual Chart of 765kV Line | [16 empty] | Date |  |  | 2026-06-29 |  |  |  | FDN | EARTH | EREC | T/W | Rough Sag | Final Sag | Length in MTR
[43 empty] | 274 | 249 | 219 | 33 | 3.461 | 0 | 118387.007
[19 empty] | RC |  |  | RC
[43 empty] | 12 | 12 | 3 | 0 |  | 0 | 5498.422
107.961 | DD60+0 |  | 148.478 | DD60+0 |  | 408.832 | DD45+3 |  | 380 | DA(-)1.5 |  | 422 | DA+6 |  | 408.352 | DC1+0 |  | 419.453 | DA+9 |  | 381 | DA+9 |  | 417 | DA(-)3 |  | 417 | DA+6 |  | 417 | DA(-)3 |  | 388.003 | DA+6 |  | 452.343 | DB1+0 |  | 401 | DA(-)3 |  | 330
| 1/0 |  |  | 2/0 |  |  | 3/0 |  |  | 3/1 |  |  | 3/2 |  |  | 4/0 |  |  | 4/1 |  |  | 4/2 |  |  | 4/3 |  |  | 4/4 |  |  | 4/5 |  |  | 4/6 |  |  | 5/0 |  |  | 5/1
| MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP
[43 empty] | 14 | 14 | 14 | 9 | 2.68 | 0 | 5348
| DA+0 |  | 413 | DA+3 |  | 422 | DA+1.5 |  | 396 | DA+0 |  | 385 | DA+0 |  | 338 | DA(-)3 |  | 324 | DC2+0 |  | 380 | DA(-)1.5 |  | 374 | DA+1.5 |  | 415 | DA+1.5 |  | 386 | DC2+0 |  | 352 | DA+0 |  | 392 | DA+0 |  | 381 | DA+0 |  | 390
| 5/2 |  |  | 5/3 |  |  | 5/4 |  |  | 5/5 |  |  | 5/6 |  |  | 5/7 |  |  | 6/0 |  |  | 6/1 |  |  | 6/2 |  |  | 6/3 |  |  | 7/0 |  |  | 7/1 |  |  | 7/2 |  |  | 7/3
| MP |  |  | MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  | MP |  |  | MP |  |  |  | MP |  | MP |  |  |  | MP |  | MP
[43 empty] | 14 | 14 | 14 | 14 | 0.781 | 0 | 5480
| DA+0 |  | 391 | DB1+0 |  | 331 | DA+0 |  | 404 | DA+3 |  | 410 | DA+3 |  | 398 | DA+3 |  | 432 | DA+0 |  | 356 | DA+0 |  | 408 | DA+0 |  | 415 | DA+3 |  | 371 | DA(-)3 |  | 364 | DA+0 |  | 415 | DB2+0 |  | 389 | DA+3 |  | 396
| 7/4 |  |  | 8/0 |  |  | 8/1 |  |  | 8/2 |  |  | 8/3 |  |  | 8/4 |  |  | 8/5 |  |  | 8/6 |  |  | 8/7 |  |  | 8/8 |  |  | 8/9 |  |  | 8/10 |  |  | 9/0 |  |  | 9/1
| MP |  |  |  | MP |  | MP |  |  | MP |  |  | MP |  |  |  | MP |  | MP |  |  | MP |  |  | MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  | MP
Stub Requerd
400KV D/C
E. RC
[43 empty] | 13 | 13 | 13 | 10 |  | 0 | 5326
| DA+0 |  | 439 | DA+6 |  | 381 | DB1+0 |  | 386 | DA+0 |  | 356 | DA(-)3 |  | 365 | DA+3 |  | 475 | DD60+25 |  | 196 | DD60+25 |  | 477 | DA+3 |  | 363 | DA(-)3 |  | 328 | DA(-)3 |  | 376 | DA+0 |  | 393 | DA+1.5 |  | 397 | DA+0 |  | 394
| 9/2 |  |  | 9/3 |  |  | 10/0 |  |  | 10/1 |  |  | 10/2 |  |  | 10/3 |  |  | 11/0 |  |  | 12/0 |  |  | 12/1 |  |  | 12/2 |  |  | 12/3 |  |  | 12/4 |  |  | 12/5 |  |  | 12/6
| MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  | MP
[43 empty] | 14 | 14 | 13 | 0 |  | 0 | 5154
| DA+0 |  | 373 | DB2+0 |  | 357 | DA(-)1.5 |  | 374 | DA+0 |  | 380 | DA+0 |  | 344 | DA(-)3 |  | 330 | DA+0 |  | 367 | DC1+0 |  | 385 | DA+0 |  | 355 | DA+0 |  | 357 | DA(-)3 |  | 393 | DA+3 |  | 383 | DA+0 |  | 388 | DB2+0 |  | 368
| 12/7 |  |  | 13/0 |  |  | 13/1 |  |  | 13/2 |  |  | 13/3 |  |  | 13/4 |  |  | 13/5 |  |  | 14/0 |  |  | 14/1 |  |  | 14/2 |  |  | 14/3 |  |  | 14/4 |  |  | 14/5 |  |  | 15/0
|  | MP |  |  | MP |  |  | MP |  |  | MP |  | MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  | MP |  |  | MP
RC
[43 empty] | 13 | 13 | 13 |  |  |  | 5549
| DA+0 |  | 412 | DA+3 |  | 416 | DA+0 |  | 407 | DA+6 |  | 425 | DA(-)3 |  | 386 | DA+0 |  | 359 | DA+0 |  | 368 | DA+0 |  | 390 | DA+3 |  | 410 | DB1+0 |  | 380 | DA+0 |  | 367 | DA+0 |  | 433 | DA+9 |  | 400 | DA+0 |  | 396
| 15/1 |  |  | 15/2 |  |  | 15/3 |  |  | 15/4 |  |  | 15/5 |  |  | 15/6 |  |  | 15/7 |  |  | 15/8 |  |  | 15/9 |  |  | 16/0 |  |  | 16/1 |  |  | 16/2 |  |  | 16/3 |  |  | 16/4
| MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  |  | MP
NH Crossing
[31 empty] | RC |  |  | RC
[43 empty] | 12 | 12 | 12 |  |  |  | 5373
| DA+6 |  | 420 | DA(-)3 |  | 354 | DA+0 |  | 348 | DA(-)3 |  | 319 | DA+0 |  | 379 | DA+6 |  | 428 | DA+0 |  | 397 | DB2+3 |  | 247 | DD45+0 |  | 423 | DA+6 |  | 395 | DD45+9 |  | 499 | DD60+6 |  | 377 | DA(-)3 |  | 443 | DA(-)3 |  | 344
| 16/5 |  |  | 16/6 |  |  | 16/7 |  |  | 16/8 |  |  | 16/9 |  |  | 16/10 |  |  | 16/11 |  |  | 17/0 |  |  | 18/0 |  |  | 18/1 |  |  | 19/0 |  |  | 20/0 |  |  | 20/1 |  |  | 20/2
|  | MP |  |  | MP |  |  | MP |  |  | MP |  | MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  | MP |  |  |  | MP |  |  | MP |  | MP |  |  | MP
[16 empty] | RC | [11 empty] | RC
[43 empty] | 12 | 12 | 9 | 0 |  | 0 | 5451
| DC2+0 |  | 390 | DA(-)3 |  | 352 | DA+0 |  | 426 | DA+0 |  | 394 | DA+3 |  | 408 | DD45+0 |  | 373 | DA+6 |  | 408 | DD45+3 |  | 379 | DA+3 |  | 406 | DC2+3 |  | 385 | DA+0 |  | 400 | DA+0 |  | 439 | DA+6 |  | 400 | DA(-)3 |  | 291
| 21/0 |  |  | 21/1 |  |  | 21/2 |  |  | 21/3 |  |  | 21/4 |  |  | 22/0 |  |  | 22/1 |  |  | 23/0 |  |  | 23/1 |  |  | 24/0 |  |  | 24/1 |  |  | 24/2 |  |  | 24/3 |  |  | 24/4
| MP |  |  | MP |  |  | MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  | MP |  |  | MP |  |  | MP |  |  |  | MP |  | MP |  |  | MP |  |  |  | MP
Stub Requerd
220KV D/C
[43 empty] | 14 | 14 | 13 | 0 |  | 0 | 5597
| DA(-)3 |  | 390 | DA+3 |  | 403 | DA+0 |  | 422 | DA+6 |  | 389 | DA(-)1.5 |  | 436 | DA+1.5 |  | 380 | DA+0 |  | 445 | DC2+18 |  | 220 | DC2+12 |  | 435 | DA+1.5 |  | 405 | DA+6 |  | 434 | DA+6 |  | 380 | DA(-)3 |  | 379 | DB2+9 |  | 479
| 24/5 |  |  | 24/6 |  |  | 24/7 |  |  | 24/8 |  |  | 24/9 |  |  | 24/10 |  |  | 24/11 |  |  | 25/0 |  |  | 26/0 |  |  | 26/1 |  |  | 26/2 |  |  | 26/3 |  |  | 26/4 |  |  | 27/0
| MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  | MP
Approch Issue | [33 empty] | Railway crossing
220 KV DC
[43 empty] | 14 | 14 | 14 | 0 |  | 0 | 5226
| DB1+9 |  | 464 | DA+0 |  | 376 | DA+1.5 |  | 380 | DA(-)3 |  | 352 | DA(-)1.5 |  | 361 | DD45+6 |  | 252 | DD45+18 |  | 394 | DA+1.5 |  | 389 | DA+1.5 |  | 399 | DC1+0 |  | 392 | DA+1.5 |  | 363 | DA+0 |  | 379 | DD60+0 |  | 226 | DD60+9 |  | 499
| 27/1 |  |  | 27/2 |  |  | 27/3 |  |  | 27/4 |  |  | 27/5 |  |  | 28/0 |  |  | 29/0 |  |  | 29/1 |  |  | 29/2 |  |  | 30/0 |  |  | 30/1 |  |  | 30/2 |  |  | 31/0 |  |  | 32/0
| MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  | MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP
Railway crossing | [36 empty] | NH Crossing
132KV D/C
[43 empty] | 14 | 13 | 13 | 0 |  |  | 5119
| DB1+9 |  | 446 | DA+1.5 |  | 394 | DA+1.5 |  | 391 | DA+0 |  | 409 | DA+1.5 |  | 379 | DA+0 |  | 364 | DA(-)1.5 |  | 447 | DD45+9 |  | 257 | DC1+3 |  | 232 | DA+3 |  | 365 | DA(-)3 |  | 379 | DA+6 |  | 440 | DB2+3 |  | 221 | DC2+0 |  | 395
| 32/1 |  |  | 32/2 |  |  | 32/3 |  |  | 32/4 |  |  | 32/5 |  |  | 32/6 |  |  | 32/7 |  |  | 33/0 |  |  | 34/0 |  |  | 34/1 |  |  | 34/2 |  |  | 34/3 |  |  | 35/0 |  |  | 36/0
| MP |  |  | MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP
220KV
[43 empty] | 14 | 12 | 14 | 0 |  |  | 5433
| DA+0 |  | 356 | DA+0 |  | 404 | DA+0 |  | 380 | DA+3 |  | 460 | DA+6 |  | 380 | DA(-)1.5 |  | 413 | DA+3 |  | 413 | DA+0 |  | 427 | DD45+12 |  | 220 | DD45+9 |  | 430 | DA(-)3 |  | 344 | DA+0 |  | 373 | DA(-)3 |  | 389 | DA+3 |  | 444
| 36/1 |  |  | 36/2 |  |  | 36/3 |  |  | 36/4 |  |  | 36/5 |  |  | 36/6 |  |  | 36/7 |  |  | 36/8 |  |  | 37/0 |  |  | 38/0 |  |  | 38/1 |  |  | 38/2 |  |  | 38/3 |  |  | 38/4
| MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP
| RC | [29 empty] | TP
[43 empty] | 13 | 13 | 10 | 0 |  |  | 5408
| DA+6 |  | 308 | DA(-)3 |  | 345 | DA+0 |  | 425 | DA+6 |  | 412 | DC1+0 |  | 399 | DA+3 |  | 420 | DA+0 |  | 367 | DA+0 |  | 354 | DA+0 |  | 399 | DA+0 |  | 375 | DC2+0 |  | 380 | DA+0 |  | 405 | DA+3 |  | 420 | DA+3 |  | 399
| 38/5 |  |  | 38/6 |  |  | 38/7 |  |  | 38/8 |  |  | 39/0 |  |  | 39/1 |  |  | 39/2 |  |  | 39/3 |  |  | 39/4 |  |  | 39/5 |  |  | 39/6 |  |  | 39/7 |  |  | 39/8 |  |  | 39/9
| MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ
ROW
[43 empty] | 13 | 10 | 11 | 0 |  |  | 5539
| DA+0 |  | 380 | DA+3 |  | 415 | DC1+0 |  | 400 | DA+3 |  | 392 | DA+0 |  | 387 | DA+0 |  | 346 | DD45+0 |  | 400 | DA+6 |  | 418 | DA(-)1.5 |  | 351 | DA+1.5 |  | 429 | DA+3 |  | 411 | DA+0 |  | 381 | DA+6 |  | 459 | DA+6 |  | 370
| 39/10 |  |  | 39/11 |  |  | 40/0 |  |  | 40/1 |  |  | 40/2 |  |  | 40/3 |  |  | 41/0 |  |  | 41/1 |  |  | 41/2 |  |  | 41/3 |  |  | 41/4 |  |  | 41/5 |  |  | 41/6 |  |  | 41/7
| RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ
ROW Route Daivarsion
|  |  |  | ROW | [35 empty] | RC
[43 empty] | 9 | 8 | 5 | 0 |  |  | 5550.31
| DA+3 |  | 425 | DC1+3 |  | 256 | DC1+6 |  | 443 | DB2+6 |  | 451 | DB1+3 |  | 420 | DA+3 |  | 418 | DA+0 |  | 349 | DC1+0 |  | 407 | DA-(3) |  | 323 | DA+0 |  | 419 | DA+0 |  | 402 | DA+1.5 |  | 402.31 | DC2+0 |  | 416 | DA+1.5 |  | 419
| 41/8 |  |  | 42/0 |  |  | 43/0 |  |  | 44/0 |  |  | 44/1 |  |  | 44/2 |  |  | 44/3 |  |  | 45/0 |  |  | 45/1 |  |  | 45/2 |  |  | 45/3 |  |  | 45/4 |  |  | 45A/0 |  |  | 45A/1
| RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  |  | RAJ |  |  | RAJ |  |  | RAJ
RC
[43 empty] | 13 | 10 | 7 | 0 |  |  | 5528.79
| DD45+0 |  | 377 | DA+1.5 |  | 440 | DA+3 |  | 400.28 | DC1+0 |  | 386 | DA+3 |  | 420 | DA(-)3 |  | 337 | DA(-)3 |  | 336.51 | DC1+3 |  | 412 | DA+0 |  | 408 | DA+6 |  | 413 | DA+0 |  | 410 | DA+3 |  | 406 | DA+3 |  | 411 | DA+3 |  | 372
| 46/0 |  |  | 46/1 |  |  | 46/2 |  |  | 46A/0 |  |  | 46A/1 |  |  | 46A/2 |  |  | 46A/3 |  |  | 47/0 |  |  | 47/1 |  |  | 47/2 |  |  | 47/3 |  |  | 47/4 |  |  | 47/5 |  |  | 47/6
| RAJ |  |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  | RAJ |  |  | RAJ
RC
[43 empty] | 13 | 12 | 8 | 0 |  |  | 5453
| DA+0 |  | 386 | DA+0 |  | 370 | DA+0 |  | 382 | DA+3 |  | 384 | DA+6 |  | 382 | DB1+0 |  | 357 | DA+0 |  | 351 | DA(-)1.5 |  | 413 | DA+3 |  | 423 | DA(-)1.5 |  | 390 | DA+0 |  | 406 | DA+3 |  | 390 | DA(-)1.5 |  | 393 | DA+0 |  | 426
| 47/7 |  |  | 47/8 |  |  | 47/9 |  |  | 47/10 |  |  | 47/11 |  |  | 48/0 |  |  | 48/1 |  |  | 48/2 |  |  | 48/3 |  |  | 48/4 |  |  | 48/5 |  |  | 48/6 |  |  | 48/7 |  |  | 48/8
| RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP
Power Line Crossing
[43 empty] | 14 | 11 | 9 | 0 |  |  | 5377
| DA+3 |  | 407 | DB1+0 |  | 404 | DA+6 |  | 418 | DA+0 |  | 413 | DA+3 |  | 410 | DA+0 |  | 426 | DA+0 |  | 397 | DA+6 |  | 404 | DC2+18 |  | 224 | DD45+9 |  | 422 | DA+0 |  | 343 | DA(-)3 |  | 360 | DA(-)3 |  | 340 | DC2+0 |  | 409
| 48/9 |  |  | 49/0 |  |  | 49/1 |  |  | 49/2 |  |  | 49/3 |  |  | 49/4 |  |  | 49/5 |  |  | 49/6 |  |  | 50/0 |  |  | 51/0 |  |  | 51/1 |  |  | 51/2 |  |  | 51/3 |  |  | 52/0
| MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP
[7 empty] | Gas Pipe Line BPCL | [8 empty] | Power Line Crossing | [23 empty] | Route Finalization pending on account of daiversion due to solar plant
[28 empty] | RC |  |  | RC | [5 empty] | RC |  |  | RC
[43 empty] | 9 | 6 | 5 | 0 |  |  | 4749.269
| DA+1.5 |  | 391.06 | DB2+3 |  | 386 | DB1(-)1.5 |  | 372.887 | DB2(-)1.5 |  | 333 | DA+3 |  | 357.142 | DC2+18 |  | 234.171 | DD60+9 |  | 352 | DA+6 |  | 353 | DA+3 |  | 352.606 | DB2+9 |  | 268 | DB1+18 |  | 306 | DB1+6 |  | 297 | DA(-)3 |  | 414.403 | DB2+0 |  | 332
| 52/1 |  |  | 53/0 |  |  | 53A/0 |  |  | 53B/0 |  |  | 53B/1 |  |  | 54/0 |  |  | 55/0 |  |  | 55/1 |  |  | 55/2 |  |  | 56/0 |  |  | 56/1 |  |  | 56/2 |  |  | 56/3 |  |  | 57/0
| MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP
| Route Finalization pending on account of daiversion due to solar plant | [20 empty] | NH Crossinng | [5 empty] | Water Pipe Line |  |  | Power Line Crossing
[16 empty] | RC | [11 empty] | ROW
[43 empty] | 5 | 3 | 1 | 0 |  |  | 5209.907
| DB1+3 |  | 410 | DA+1.5 |  | 414 | DA+3 |  | 407 | DA+0 |  | 421.884 | DC1+6 |  | 532.192 | DD45+18 |  | 415 | DA+9 |  | 350 | DC2+6 |  | 249.013 | DB1+9 |  | 351 | DA+6 |  | 307.261 | DB1+12 |  | 250.557 | DC2+12 |  | 423 | DA(-)3 |  | 339 | DA(-)3 |  | 340
| 57/1 |  |  | 57/2 |  |  | 57/3 |  |  | 57/4 |  |  | 58/0 |  |  | 59/0 |  |  | 59/1 |  |  | 60/0 |  |  | 61/0 |  |  | 61/1 |  |  | 62/0 |  |  | 63/0 |  |  | 63/1 |  |  | 63/2 |  | 340
| MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP
Approch Issue
[22 empty] | ROW | [5 empty] | ROW | [11 empty] | RC
[43 empty] | 12 | 11 | 7 | 0 |  |  | 5440.061
| DA(-)3 |  | 339.061 | DD45+0 |  | 383 | DA+6 |  | 400 | DC2+0 |  | 386 | DA(-)1.5 |  | 393 | DA+0 |  | 422 | DA+6 |  | 408 | DA(-)1.5 |  | 370 | DA(-)3 |  | 345 | DA+0 |  | 352 | DA(-)3 |  | 440 | DA+1.5 |  | 380 | DA(-)3 |  | 416 | DA+9 |  | 406
| 63/3 |  |  | 64/0 |  |  | 64/1 |  |  | 65/0 |  |  | 65/1 |  |  | 65/2 |  |  | 65/3 |  |  | 65/4 |  |  | 65/5 |  |  | 65/6 |  |  | 65/7 |  |  | 65/8 |  |  | 65/9 |  |  | 65/10
| MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP
Approch Issue
[7 empty] | RC | [32 empty] | RC
[43 empty] | 12 | 8 | 10 | 0 |  |  | 5577.248
| DA+6 |  | 433 | DB1+0 |  | 353.248 | DA+6 |  | 407 | DA(-)1.5 |  | 416 | DA+6 |  | 373 | DA(-)3 |  | 389 | DA+3 |  | 399 | DA(-)1.5 |  | 412 | DA+6 |  | 418 | DA(-)3 |  | 394 | DB2+6 |  | 399 | DA(-)3 |  | 348 | DA(-)3 |  | 358 | DA+9 |  | 478
| 65/11 |  |  | 66/0 |  |  | 66/1 |  |  | 66/2 |  |  | 66/3 |  |  | 66/4 |  |  | 66/5 |  |  | 66/6 |  |  | 66/7 |  |  | 66/8 |  |  | 67/0 |  |  | 67/1 |  |  | 67/2 |  |  | 67/3
| MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP
Approch Issue
[43 empty] | 1 | 0 | 1 | 0 |  |  | 0
DB2+6
68/0
MP
MP
| Legend | [11 empty] | Crossing | [8 empty] | Progress at a Glance (765kV Line)
| Tack-Welding |  |  |  | final sag |  |  | rough sag |  |  |  |  | LT Line |  |  |  | NH/SH |  |  |  |  | Sl. No. |  | Activity |  |  |  | Unit |  | Total Qty |  |  | Completed |  |  | Balance |  |  | Remarks
[22 empty] | 1 |  | Detailed Survey |  |  |  | Kms |  | 119.178 |  |  | 119.178 |  |  | 0
| Erection | [11 empty] | 11kV Line | [8 empty] | 2 |  | Check Survey |  |  |  | Kms |  | 119.178 |  |  | 118.387 |  |  | 0.791
[22 empty] | 3 |  | Foundation |  |  |  | Nos |  | 309 |  |  | 274 |  |  | 35
[13 empty] | 33kV Line |  |  |  | Railway |  |  |  |  | 4 |  | Earthing |  |  |  | Nos |  | 309 |  |  | 249 |  |  | 60
[22 empty] | 5 |  | Erection |  |  |  | Nos |  | 309 |  |  | 219 |  |  | 90
| Foundation | [11 empty] | 220kV Line | [8 empty] | 6 |  | Tack-welding |  |  |  | Nos |  | 309 |  |  | 33 |  |  | 276
| Location No |  |  | 1/0 |  | 293 | 1/1 |  | 391 | 1A/0 | [11 empty] | 7 |  | Rough Sag |  |  |  | Kms |  | 119.178 |  |  | 3.461 |  |  | 115.717
| Tower Type |  |  | DC+0 |  |  | DA+3 |  |  | DC+3 |  |  | 400kV Line | [8 empty] | 8 |  | Final Sag |  |  |  | Kms |  | 119.178 |  |  | 0 |  |  | 119.178
[5 empty] | Earthing |  |  |  | Forest | [12 empty] | 9 |  | OPGW |  |  |  | Kms |  | 119.178 |  |  | 0 |  |  | 119.178
132kV Line
[8 empty] | FDN | EARTH | ERE | T/W | Rough Sag | Final Sag | Length in MTR | [18 empty] | Raise Chimney 4/1, 4/2,12/0, 15/6, 19/0, 20/0, 22/0, 24/0, 38/5, 45A/1, 46/1, 48/7, 55/0,56/0, 56/1, 56/3, 57/0, 59/0, 65/10, 66/1, 67/3- Total - 21 N0's
[8 empty] | 274 | 249 | 219 | 33 | 3.461 | 0 | 0
.
.

## VC-765kV MKTL (hidden)
Name of Line:- 765 KV D/C Mandsaur - Kurawar (Part-1)Transmission Line(WZ-4)
[19 empty] | Visual Chart of 765kV Line | [16 empty] | Date |  |  | 2026-05-28 |  |  |  | FDN | EARTH | EREC | T/W | Strng | Length in MTR
[43 empty] | 267 | 235 | 208 | 4 | 0 | 118387.007
[19 empty] | RC |  |  | RC
[43 empty] | 11 | 7 | 2 | 0 | 0 | 5498.422
107.961 | DD60+0 |  | 148.478 | DD60+0 |  | 408.832 | DD45+3 |  | 380 | DA(-)1.5 |  | 422 | DA+6 |  | 408.352 | DC1+0 |  | 419.453 | DA+9 |  | 381 | DA+9 |  | 417 | DA(-)3 |  | 417 | DA+6 |  | 417 | DA(-)3 |  | 388.003 | DA+6 |  | 452.343 | DB1+0 |  | 401 | DA(-)3 |  | 330
| 1/0 |  |  | 2/0 |  |  | 3/0 |  |  | 3/1 |  |  | 3/2 |  |  | 4/0 |  |  | 4/1 |  |  | 4/2 |  |  | 4/3 |  |  | 4/4 |  |  | 4/5 |  |  | 4/6 |  |  | 5/0 |  |  | 5/1
| MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP
[43 empty] | 14 | 11 | 14 | 4 | 0 | 5348
| DA+0 |  | 413 | DA+3 |  | 422 | DA+1.5 |  | 396 | DA+0 |  | 385 | DA+0 |  | 338 | DA(-)3 |  | 324 | DC2+0 |  | 380 | DA(-)1.5 |  | 374 | DA+1.5 |  | 415 | DA+1.5 |  | 386 | DC2+0 |  | 352 | DA+0 |  | 392 | DA+0 |  | 381 | DA+0 |  | 390
| 5/2 |  |  | 5/3 |  |  | 5/4 |  |  | 5/5 |  |  | 5/6 |  |  | 5/7 |  |  | 6/0 |  |  | 6/1 |  |  | 6/2 |  |  | 6/3 |  |  | 7/0 |  |  | 7/1 |  |  | 7/2 |  |  | 7/3
| MP |  |  | MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  | MP |  |  | MP |  |  |  | MP |  | MP |  |  |  | MP |  | MP
[43 empty] | 14 | 14 | 14 | 0 | 0 | 5480
| DA+0 |  | 391 | DB1+0 |  | 331 | DA+0 |  | 404 | DA+3 |  | 410 | DA+3 |  | 398 | DA+3 |  | 432 | DA+0 |  | 356 | DA+0 |  | 408 | DA+0 |  | 415 | DA+3 |  | 371 | DA(-)3 |  | 364 | DA+0 |  | 415 | DB2+0 |  | 389 | DA+3 |  | 396
| 7/4 |  |  | 8/0 |  |  | 8/1 |  |  | 8/2 |  |  | 8/3 |  |  | 8/4 |  |  | 8/5 |  |  | 8/6 |  |  | 8/7 |  |  | 8/8 |  |  | 8/9 |  |  | 8/10 |  |  | 9/0 |  |  | 9/1
| MP |  |  |  | MP |  | MP |  |  | MP |  |  | MP |  |  |  | MP |  | MP |  |  | MP |  |  | MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  | MP
Stub Requerd
400KV D/C
E. RC
[43 empty] | 13 | 13 | 13 | 0 | 0 | 5326
| DA+0 |  | 439 | DA+6 |  | 381 | DB1+0 |  | 386 | DA+0 |  | 356 | DA(-)3 |  | 365 | DA+3 |  | 475 | DD60+25 |  | 196 | DD60+25 |  | 477 | DA+3 |  | 363 | DA(-)3 |  | 328 | DA(-)3 |  | 376 | DA+0 |  | 393 | DA+1.5 |  | 397 | DA+0 |  | 394
| 9/2 |  |  | 9/3 |  |  | 10/0 |  |  | 10/1 |  |  | 10/2 |  |  | 10/3 |  |  | 11/0 |  |  | 12/0 |  |  | 12/1 |  |  | 12/2 |  |  | 12/3 |  |  | 12/4 |  |  | 12/5 |  |  | 12/6
| MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  | MP
[43 empty] | 14 | 12 | 13 | 0 | 0 | 5154
| DA+0 |  | 373 | DB2+0 |  | 357 | DA(-)1.5 |  | 374 | DA+0 |  | 380 | DA+0 |  | 344 | DA(-)3 |  | 330 | DA+0 |  | 367 | DC1+0 |  | 385 | DA+0 |  | 355 | DA+0 |  | 357 | DA(-)3 |  | 393 | DA+3 |  | 383 | DA+0 |  | 388 | DB2+0 |  | 368
| 12/7 |  |  | 13/0 |  |  | 13/1 |  |  | 13/2 |  |  | 13/3 |  |  | 13/4 |  |  | 13/5 |  |  | 14/0 |  |  | 14/1 |  |  | 14/2 |  |  | 14/3 |  |  | 14/4 |  |  | 14/5 |  |  | 15/0
|  | MP |  |  | MP |  |  | MP |  |  | MP |  | MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  | MP |  |  | MP
RC
[43 empty] | 13 | 13 | 13 |  |  | 5549
| DA+0 |  | 412 | DA+3 |  | 416 | DA+0 |  | 407 | DA+6 |  | 425 | DA(-)3 |  | 386 | DA+0 |  | 359 | DA+0 |  | 368 | DA+0 |  | 390 | DA+3 |  | 410 | DB1+0 |  | 380 | DA+0 |  | 367 | DA+0 |  | 433 | DA+9 |  | 400 | DA+0 |  | 396
| 15/1 |  |  | 15/2 |  |  | 15/3 |  |  | 15/4 |  |  | 15/5 |  |  | 15/6 |  |  | 15/7 |  |  | 15/8 |  |  | 15/9 |  |  | 16/0 |  |  | 16/1 |  |  | 16/2 |  |  | 16/3 |  |  | 16/4
| MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  |  | MP
NH Crossing
[31 empty] | RC |  |  | RC
[43 empty] | 12 | 12 | 12 |  |  | 5373
| DA+6 |  | 420 | DA(-)3 |  | 354 | DA+0 |  | 348 | DA(-)3 |  | 319 | DA+0 |  | 379 | DA+6 |  | 428 | DA+0 |  | 397 | DB2+3 |  | 247 | DD45+0 |  | 423 | DA+6 |  | 395 | DD45+9 |  | 499 | DD60+6 |  | 377 | DA(-)3 |  | 443 | DA(-)3 |  | 344
| 16/5 |  |  | 16/6 |  |  | 16/7 |  |  | 16/8 |  |  | 16/9 |  |  | 16/10 |  |  | 16/11 |  |  | 17/0 |  |  | 18/0 |  |  | 18/1 |  |  | 19/0 |  |  | 20/0 |  |  | 20/1 |  |  | 20/2
|  | MP |  |  | MP |  |  | MP |  |  | MP |  | MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  | MP |  |  |  | MP |  |  | MP |  | MP |  |  | MP
[16 empty] | RC | [11 empty] | RC
[43 empty] | 12 | 8 | 7 | 0 | 0 | 5451
| DC2+0 |  | 390 | DA(-)3 |  | 352 | DA+0 |  | 426 | DA+0 |  | 394 | DA+3 |  | 408 | DD45+0 |  | 373 | DA+6 |  | 408 | DD45+3 |  | 379 | DA+3 |  | 406 | DC2+3 |  | 385 | DA+0 |  | 400 | DA+0 |  | 439 | DA+6 |  | 400 | DA(-)3 |  | 291
| 21/0 |  |  | 21/1 |  |  | 21/2 |  |  | 21/3 |  |  | 21/4 |  |  | 22/0 |  |  | 22/1 |  |  | 23/0 |  |  | 23/1 |  |  | 24/0 |  |  | 24/1 |  |  | 24/2 |  |  | 24/3 |  |  | 24/4
| MP |  |  | MP |  |  | MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  | MP |  |  | MP |  |  | MP |  |  |  | MP |  | MP |  |  | MP |  |  |  | MP
Stub Requerd
220KV D/C
[43 empty] | 14 | 14 | 12 | 0 | 0 | 5597
| DA(-)3 |  | 390 | DA+3 |  | 403 | DA+0 |  | 422 | DA+6 |  | 389 | DA(-)1.5 |  | 436 | DA+1.5 |  | 380 | DA+0 |  | 445 | DC2+18 |  | 220 | DC2+12 |  | 435 | DA+1.5 |  | 405 | DA+6 |  | 434 | DA+6 |  | 380 | DA(-)3 |  | 379 | DB2+9 |  | 479
| 24/5 |  |  | 24/6 |  |  | 24/7 |  |  | 24/8 |  |  | 24/9 |  |  | 24/10 |  |  | 24/11 |  |  | 25/0 |  |  | 26/0 |  |  | 26/1 |  |  | 26/2 |  |  | 26/3 |  |  | 26/4 |  |  | 27/0
| MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  | MP
Approch Issue | [33 empty] | Railway crossing
220 KV DC
[43 empty] | 14 | 14 | 14 | 0 | 0 | 5226
| DB1+9 |  | 464 | DA+0 |  | 376 | DA+1.5 |  | 380 | DA(-)3 |  | 352 | DA(-)1.5 |  | 361 | DD45+6 |  | 252 | DD45+18 |  | 394 | DA+1.5 |  | 389 | DA+1.5 |  | 399 | DC1+0 |  | 392 | DA+1.5 |  | 363 | DA+0 |  | 379 | DD60+0 |  | 226 | DD60+9 |  | 499
| 27/1 |  |  | 27/2 |  |  | 27/3 |  |  | 27/4 |  |  | 27/5 |  |  | 28/0 |  |  | 29/0 |  |  | 29/1 |  |  | 29/2 |  |  | 30/0 |  |  | 30/1 |  |  | 30/2 |  |  | 31/0 |  |  | 32/0
| MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  | MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP
Railway crossing | [36 empty] | NH Crossing
132KV D/C
[43 empty] | 14 | 13 | 13 | 0 |  | 5119
| DB1+9 |  | 446 | DA+1.5 |  | 394 | DA+1.5 |  | 391 | DA+0 |  | 409 | DA+1.5 |  | 379 | DA+0 |  | 364 | DA(-)1.5 |  | 447 | DD45+9 |  | 257 | DC1+3 |  | 232 | DA+3 |  | 365 | DA(-)3 |  | 379 | DA+6 |  | 440 | DB2+3 |  | 221 | DC2+0 |  | 395
| 32/1 |  |  | 32/2 |  |  | 32/3 |  |  | 32/4 |  |  | 32/5 |  |  | 32/6 |  |  | 32/7 |  |  | 33/0 |  |  | 34/0 |  |  | 34/1 |  |  | 34/2 |  |  | 34/3 |  |  | 35/0 |  |  | 36/0
| MP |  |  | MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP
220KV
[43 empty] | 14 | 12 | 14 | 0 |  | 5433
| DA+0 |  | 356 | DA+0 |  | 404 | DA+0 |  | 380 | DA+3 |  | 460 | DA+6 |  | 380 | DA(-)1.5 |  | 413 | DA+3 |  | 413 | DA+0 |  | 427 | DD45+12 |  | 220 | DD45+9 |  | 430 | DA(-)3 |  | 344 | DA+0 |  | 373 | DA(-)3 |  | 389 | DA+3 |  | 444
| 36/1 |  |  | 36/2 |  |  | 36/3 |  |  | 36/4 |  |  | 36/5 |  |  | 36/6 |  |  | 36/7 |  |  | 36/8 |  |  | 37/0 |  |  | 38/0 |  |  | 38/1 |  |  | 38/2 |  |  | 38/3 |  |  | 38/4
| MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP
RC
[43 empty] | 13 | 13 | 9 | 0 |  | 5408
| DA+6 |  | 308 | DA(-)3 |  | 345 | DA+0 |  | 425 | DA+6 |  | 412 | DC1+0 |  | 399 | DA+3 |  | 420 | DA+0 |  | 367 | DA+0 |  | 354 | DA+0 |  | 399 | DA+0 |  | 375 | DC2+0 |  | 380 | DA+0 |  | 405 | DA+3 |  | 420 | DA+3 |  | 399
| 38/5 |  |  | 38/6 |  |  | 38/7 |  |  | 38/8 |  |  | 39/0 |  |  | 39/1 |  |  | 39/2 |  |  | 39/3 |  |  | 39/4 |  |  | 39/5 |  |  | 39/6 |  |  | 39/7 |  |  | 39/8 |  |  | 39/9
| MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ
ROW
[43 empty] | 13 | 10 | 5 | 0 |  | 5539
| DA+0 |  | 380 | DA+3 |  | 415 | DC1+0 |  | 400 | DA+3 |  | 392 | DA+0 |  | 387 | DA+0 |  | 346 | DD45+0 |  | 400 | DA+6 |  | 418 | DA(-)1.5 |  | 351 | DA+1.5 |  | 429 | DA+3 |  | 411 | DA+0 |  | 381 | DA+6 |  | 459 | DA+6 |  | 370
| 39/10 |  |  | 39/11 |  |  | 40/0 |  |  | 40/1 |  |  | 40/2 |  |  | 40/3 |  |  | 41/0 |  |  | 41/1 |  |  | 41/2 |  |  | 41/3 |  |  | 41/4 |  |  | 41/5 |  |  | 41/6 |  |  | 41/7
| RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ
ROW Route Daivarsion
|  |  |  | ROW | [35 empty] | RC
[43 empty] | 9 | 8 | 5 | 0 |  | 5550.31
| DA+3 |  | 425 | DC1+3 |  | 256 | DC1+6 |  | 443 | DB2+6 |  | 451 | DB1+3 |  | 420 | DA+3 |  | 418 | DA+0 |  | 349 | DC1+0 |  | 407 | DA-(3) |  | 323 | DA+0 |  | 419 | DA+0 |  | 402 | DA+1.5 |  | 402.31 | DC2+0 |  | 416 | DA+1.5 |  | 419
| 41/8 |  |  | 42/0 |  |  | 43/0 |  |  | 44/0 |  |  | 44/1 |  |  | 44/2 |  |  | 44/3 |  |  | 45/0 |  |  | 45/1 |  |  | 45/2 |  |  | 45/3 |  |  | 45/4 |  |  | 45A/0 |  |  | 45A/1
| RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  |  | RAJ |  |  | RAJ |  |  | RAJ
RC
[43 empty] | 11 | 10 | 7 | 0 |  | 5528.79
| DD45+0 |  | 377 | DA+1.5 |  | 440 | DA+3 |  | 400.28 | DC1+0 |  | 386 | DA+3 |  | 420 | DA(-)3 |  | 337 | DA(-)3 |  | 336.51 | DC1+3 |  | 412 | DA+0 |  | 408 | DA+6 |  | 413 | DA+0 |  | 410 | DA+3 |  | 406 | DA+3 |  | 411 | DA+3 |  | 372
| 46/0 |  |  | 46/1 |  |  | 46/2 |  |  | 46A/0 |  |  | 46A/1 |  |  | 46A/2 |  |  | 46A/3 |  |  | 47/0 |  |  | 47/1 |  |  | 47/2 |  |  | 47/3 |  |  | 47/4 |  |  | 47/5 |  |  | 47/6
| RAJ |  |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  | RAJ |  |  | RAJ
RC
[43 empty] | 13 | 13 | 8 | 0 |  | 5453
| DA+0 |  | 386 | DA+0 |  | 370 | DA+0 |  | 382 | DA+3 |  | 384 | DA+6 |  | 382 | DB1+0 |  | 357 | DA+0 |  | 351 | DA(-)1.5 |  | 413 | DA+3 |  | 423 | DA(-)1.5 |  | 390 | DA+0 |  | 406 | DA+3 |  | 390 | DA(-)1.5 |  | 393 | DA+0 |  | 426
| 47/7 |  |  | 47/8 |  |  | 47/9 |  |  | 47/10 |  |  | 47/11 |  |  | 48/0 |  |  | 48/1 |  |  | 48/2 |  |  | 48/3 |  |  | 48/4 |  |  | 48/5 |  |  | 48/6 |  |  | 48/7 |  |  | 48/8
| RAJ |  |  | RAJ |  |  | RAJ |  |  | RAJ |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP
Power Line Crossing
[43 empty] | 13 | 11 | 9 | 0 |  | 5377
| DA+3 |  | 407 | DB1+0 |  | 404 | DA+6 |  | 418 | DA+0 |  | 413 | DA+3 |  | 410 | DA+0 |  | 426 | DA+0 |  | 397 | DA+6 |  | 404 | DC2+18 |  | 224 | DD45+9 |  | 422 | DA+0 |  | 343 | DA(-)3 |  | 360 | DA(-)3 |  | 340 | DC2+0 |  | 409
| 48/9 |  |  | 49/0 |  |  | 49/1 |  |  | 49/2 |  |  | 49/3 |  |  | 49/4 |  |  | 49/5 |  |  | 49/6 |  |  | 50/0 |  |  | 51/0 |  |  | 51/1 |  |  | 51/2 |  |  | 51/3 |  |  | 52/0
| MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP
[7 empty] | Gas Pipe Line BPCL | [8 empty] | Power Line Crossing | [23 empty] | Route Finalization pending on account of daiversion due to solar plant
[28 empty] | RC |  |  | RC | [5 empty] | RC |  |  | RC
[43 empty] | 9 | 6 | 5 | 0 |  | 4749.269
| DA+1.5 |  | 391.06 | DB2+3 |  | 386 | DB1(-)1.5 |  | 372.887 | DB2(-)1.5 |  | 333 | DA+3 |  | 357.142 | DC2+18 |  | 234.171 | DD60+9 |  | 352 | DA+6 |  | 353 | DA+3 |  | 352.606 | DB2+9 |  | 268 | DB1+18 |  | 306 | DB1+6 |  | 297 | DA(-)3 |  | 414.403 | DB2+0 |  | 332
| 52/1 |  |  | 53/0 |  |  | 53A/0 |  |  | 53B/0 |  |  | 53B/1 |  |  | 54/0 |  |  | 55/0 |  |  | 55/1 |  |  | 55/2 |  |  | 56/0 |  |  | 56/1 |  |  | 56/2 |  |  | 56/3 |  |  | 57/0
| MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP
| Route Finalization pending on account of daiversion due to solar plant | [20 empty] | NH Crossinng | [5 empty] | Water Pipe Line |  |  | Power Line Crossing
[16 empty] | RC | [11 empty] | ROW
[43 empty] | 2 | 2 | 1 | 0 |  | 5209.907
| DB1+3 |  | 410 | DA+1.5 |  | 414 | DA+3 |  | 407 | DA+0 |  | 421.884 | DC1+6 |  | 532.192 | DD45+18 |  | 415 | DA+9 |  | 350 | DC2+6 |  | 249.013 | DB1+9 |  | 351 | DA+6 |  | 307.261 | DB1+12 |  | 250.557 | DC2+12 |  | 423 | DA(-)3 |  | 339 | DA(-)3 |  | 340
| 57/1 |  |  | 57/2 |  |  | 57/3 |  |  | 57/4 |  |  | 58/0 |  |  | 59/0 |  |  | 59/1 |  |  | 60/0 |  |  | 61/0 |  |  | 61/1 |  |  | 62/0 |  |  | 63/0 |  |  | 63/1 |  |  | 63/2 |  | 340
| MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP
Approch Issue
[22 empty] | ROW | [5 empty] | ROW | [11 empty] | RC
[43 empty] | 12 | 11 | 7 | 0 |  | 5440.061
| DA(-)3 |  | 339.061 | DD45+0 |  | 383 | DA+6 |  | 400 | DC2+0 |  | 386 | DA(-)1.5 |  | 393 | DA+0 |  | 422 | DA+6 |  | 408 | DA(-)1.5 |  | 370 | DA(-)3 |  | 345 | DA+0 |  | 352 | DA(-)3 |  | 440 | DA+1.5 |  | 380 | DA(-)3 |  | 416 | DA+9 |  | 406
| 63/3 |  |  | 64/0 |  |  | 64/1 |  |  | 65/0 |  |  | 65/1 |  |  | 65/2 |  |  | 65/3 |  |  | 65/4 |  |  | 65/5 |  |  | 65/6 |  |  | 65/7 |  |  | 65/8 |  |  | 65/9 |  |  | 65/10
| MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP
Approch Issue
[7 empty] | RC | [32 empty] | RC
[43 empty] | 12 | 8 | 10 | 0 |  | 5577.248
| DA+6 |  | 433 | DB1+0 |  | 353.248 | DA+6 |  | 407 | DA(-)1.5 |  | 416 | DA+6 |  | 373 | DA(-)3 |  | 389 | DA+3 |  | 399 | DA(-)1.5 |  | 412 | DA+6 |  | 418 | DA(-)3 |  | 394 | DB2+6 |  | 399 | DA(-)3 |  | 348 | DA(-)3 |  | 358 | DA+9 |  | 478
| 65/11 |  |  | 66/0 |  |  | 66/1 |  |  | 66/2 |  |  | 66/3 |  |  | 66/4 |  |  | 66/5 |  |  | 66/6 |  |  | 66/7 |  |  | 66/8 |  |  | 67/0 |  |  | 67/1 |  |  | 67/2 |  |  | 67/3
| MP |  |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP |  |  | MP
Approch Issue
[43 empty] | 1 | 0 | 1 | 0 |  | 0
DB2+6
68/0
MP
MP
| Legend | [11 empty] | Crossing | [8 empty] | Progress at a Glance (765kV Line)
| Tack-Welding |  |  |  | final sag |  |  | rough sag |  |  |  |  | LT Line |  |  |  | NH/SH |  |  |  |  | Sl. No. |  | Activity |  |  |  | Unit |  | Total Qty |  |  | Completed |  |  | Balance |  |  | Remarks
[22 empty] | 1 |  | Detailed Survey |  |  |  | Kms |  | 118.406 |  |  | 118.387 |  |  | 0.019
| Erection | [11 empty] | 11kV Line | [8 empty] | 2 |  | Check Survey |  |  |  | Kms |  | 118.406 |  |  | 118.387 |  |  | 0.019
[22 empty] | 3 |  | Foundation |  |  |  | Nos |  | 309 |  |  | 267 |  |  | 42
[13 empty] | 33kV Line |  |  |  | Railway |  |  |  |  | 4 |  | Earthing |  |  |  | Nos |  | 309 |  |  | 235 |  |  | 74
[22 empty] | 5 |  | Erection |  |  |  | Nos |  | 309 |  |  | 208 |  |  | 101
| Foundation | [11 empty] | 220kV Line | [8 empty] | 6 |  | Tack-welding |  |  |  | Nos |  | 309 |  |  | 4 |  |  | 305
| Location No |  |  | 1/0 |  | 293 | 1/1 |  | 391 | 1A/0 | [11 empty] | 7 |  | Stringing (P/O) |  |  |  | Kms |  | 118.406 |  |  | 0 |  |  | 118.406
| Tower Type |  |  | DC+0 |  |  | DA+3 |  |  | DC+3 |  |  | 400kV Line | [8 empty] | 8 |  | Stringing (F/O) |  |  |  | Kms |  | 118.406 |  |  | 0 |  |  | 118.406
[5 empty] | Earthing |  |  |  | Forest | [12 empty] | 9 |  | OPGW |  |  |  | Kms |  | 118.406 |  |  | 0 |  |  | 118
132kV Line
[8 empty] | FDN | EARTH | ERE | T/W | Strng | Length in MTR | [19 empty] | Raise Chimney 4/1, 4/2,12/0, 15/6, 19/0, 20/0, 22/0, 24/0, 38/5, 45A/1, 46/1, 48/7, 55/0,56/0, 56/1, 56/3, 57/0, 59/0, 65/10, 66/1, 67/3- Total - 21 N0's
[8 empty] | 267 | 235 | 208 | 4 | 0 | 0
.
.

## DPR
| Project Code - | TA-509 | Date | 2026-06-29 |  | Head - T&D | Rajinder Gupta |  | Head T&D-Central | Nabajit Baruah |  |  |  |  | Shortcut for previous of Full description
| Client Name- | PGCIL |  |  |  | Project Manager | Prithviraj Dutta Choudhury |  |  |  | Planning Engineer | Shuvayu Das |  |  | Link for go through
| Project Name- | 765KV D/C Mandsaur-Kurawar TL line |  |  |  | Effective Date | 26/11/24 |  | End Date | 25/10/26 | LOA Value | Rs 474. Cr |  |  | X-ing Status'!A1
Sr. No. | Activity | As per L2 (till June'26) | Cumm. Progress up to last Month | Opening Balance (L2) | Plan for this Month | Today Progress | MTD (Loc) | WIP (Loc) | Cumulative Progress | Balance | Gangs at present | Remarks | Support Required | % Completion | L2 Schedule'!A1
1 | Check Survey (Kms) | 118.397 | 118.397 | 0 | 0 |  |  |  | 118.397 | 0 | - |  |  | 100% | Hindrance Register (Row)'!A1
2 | Foundation (Nos.) | 306 | 268 | 38 | 13 |  | 6 | 2 | 274 | 32 | 2 | WIP- 60/0, 61/0 Today Completed - | ROW- 61/1, 41/6 | 89.54% | Survey!A1
3 | Earthing (Nos.) | 306 | 247 | 59 | 10 |  | 2 | 0 | 249 | 57 |  | WIP- Today Completed - |  | 81.37% | Foundation!A1
4 | Tower Erection (Nos) | 306 | 208 | 98 | 30 |  | 11 | 3 | 219 | 87 | 3 | WIP- 2/0, 41/5, 39/6 Today Completed - |  | 71.57% | Earthing!A1
5 | Final Checking | 150 | 1 | 149 | 48 |  | 50 | 45 | 51 | 99 | 5 | WIP- 10/2, 12/5, 12/4, 40/1,40/2, 40/3, 41/0, Today Completed - 12/1, 12/2, 12/3 |  | 34%
6 | Tack Welding | 150 | 2 | 148 | 48 |  | 31 | 4 | 33 | 117 | 2 | WIP- 12/4 Today Completed - 12/1, 12/2, 12/3
7 | Paying Out (Kms) | 108 |  | 108 | 12.364 |  | 3.461 | 4.304 | 3.461 | 104.539 | 1 | WIP- . Today Completed - 8/0 to 9/0 Insulator Hoisting completed |  | 3.205% | Tackwelding!A1
8 | Rough Sag (Kms) | 108 |  | 108 | 12.364 |  | 3.461 |  | 3.461 | 104.539 | 1 | WIP- Today Completed -
9 | Final Sag (Kms) | 108 |  | 108 | 12.364 |  |  |  | 0 | 108 |  | WIP- Today Completed - |  | 0% | Stringing!A1
10 | OPGW (Kms) | 90 |  | 90 |  |  |  |  | 0 | 90 |  | WIP- Today Completed - |  | 0% | Stringing associated works'!A1
OPGW!A1
Workfront Status | [14 empty] | Visual chart'!A1
Page Chart'!A1
A. Foundation | [14 empty] | Benching F'!A1
Balance on 1st of this month | Progress MTD | WIP | Clear/Yet to attempt | ROW | Remarks
38 | 6 | 2 |  | 30
B. Erection
Balance on 1st of this month | Progress MTD | WIP | Clear/Yet to attempt | ROW | Linked With Fnd | Remarks
98 | 11 | 3 |  | 5 | 30
C. Stringing
STR P/Out Bal. on starting of this month | Progress MTD | WIP | Clear/Yet to attempt | ROW | Readiness awaited due to Erec. | Readiness awaited due to Tower Inspection
108 | 3.461 | 4.304
FDN (WIP) | Pit A | Pit B | Pit C | Pit D | Gang name | Gang man power | Gang leader contact | Start date | Target Finish Date | Remarks
3/0 | Frustum & Step box 1, Step Box 2 completed | Chimney completed | Chimney completed | Steel binding | Musauddin Sk | 15 | 7863971676 | 2026-05-07 | 2026-11-07
47/9 | Excavation | Excavation | Excavation | Excavation | Afflux Construction
51/0 | Excavation | Excavation | Excavation | Excavation | Balaji Cons.
Erection (WIP) | MT | Status | Gange name | Gang man power | Gang leader contact | Start date | Target Finish Date | Completed today (MT) | Completed So far (MT) | Remarks
21/2 | 36.1598 | Erection completed | Jwala Singh | 25 | [5 empty] | Next loc - 24/3
29/0 | 125.8496 | Cage 1 WIP |  | 25 |  |  |  |  | 67.2436

## FDN pivot (hidden)
Count of LOC No. | Column Labels
Row Labels | COMPLETED | COMPLETED | No Progress (Water pipe line) | ROW | Excavation u/p | Grand Total
AP 47/11 - AP68 | 26 | 34 | 1 |  | 1 | 62
AP39/1 - 47/10 | 22 | 25 |  | 1 |  | 48
Gantry - AP39/0 | 117 | 46 |  |  | 1 | 164
Grand Total | 165 | 105 | 1 | 1 | 2 | 274

## Erc pivot (hidden)
Count of LOC No. | Column Labels
Row Labels | COMPLETED | COMPLETED | 1st section u/p | Material shifting | Grand Total
AP 47/11 - AP68 | 39 |  |  | 1 | 40
AP39/1 - 47/10 | 23 |  | 1 |  | 24
Gantry - AP39/0 | 144 | 1 | 1 |  | 146
Grand Total | 206 | 1 | 2 | 1 | 210

## SUMMARY
Name of Line: 765 kV D/C Mandsaur - Kurawar (Part-1)Transmission Line(WZ-4)
Agency: - M/s KEC INTERNATIONAL LIMITED
NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024
[13 empty] | Date: | 2026-06-29 |  | 2026-06-29
Activity |  |  | LOA Quantity | Final Estimated Quantity | Cum. L2 till Last Month | Cum Progress till Last Month | L2 for present Month | Plan for the Month | Progress for Today | Progress for the Month | Cum. L2 till date | Cum. Progress till date | Balance Work | Under Progress | Gangs at Present | Completed LOC. (Today) | Remarks
Foundation (Loc) |  |  | 309 | 309 | 306 | 268 | 0 | 13 |  | 6 | 306 | 274 | 35 | 60/0, 61/0 | 2
Earthing (Loc) |  |  | 309 | 309 | 262 | 247 | 20 | 10 |  | 2 | 282 | 249 | 60
Erection (Loc) |  |  | 309 | 309 | 270 | 208 | 16 | 30 |  | 11 | 286 | 219 | 90 | (2/0, 41/5, 39/6) | 3
Stringing (Km) |  | Rough Sag | 118.397 | 119.178 | 60 | 0 | 12 | 12 |  | 3.461 | 72 | 3.461 | 115.717 | 8/0 to 9/0 Insulator Hoisting u/p. Today Completed - (7/0 to 8/0 Rough sag completed) | 1 |  | 8/0 to 9/0 Insulator Hoisting u/p. Today Completed - (7/0 to 8/0 Rough sag completed)
|  | Final Sag | 118.397 | 119.178 |  |  | 0 |  |  |  | 72 | 0 | 119.178 |  | 0
| S. No. | Item | Anticipated Qty | UPTO July-25 L2 Schedule | Completed | Balance | Remarks
| 1 | Detailed Survey | 119.178 | 118.397 | 119.178 | 0 | Route alignment Approval Pending from PGCIL AP 41 and AP 45 (6.465 km) & (MPIDC - AP 21 and AP 24 - 3.843 km)
| 2 | Check Survey | 119.178 | 118.397 | 108.859 | 10.319

## FOUNDATION
FOUNDATION-STATUS | [5 empty] | 193.0399 | 0
SL NO. | LOC No. | District wise section | TOWER-TYPE | CLASSIFICATION | WK | Rev | MT | STATUS | STARTING DATE | ENDING DATE | Work started month | Completed month | Sub-Contractor | JMC | EARTHING | TFR
1 | 8/1 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-01-01 |  | Jan'25 | JSC Enterprises | DONE | COMPLETED
2 | 8/3 | Gantry - AP39/0 | DA+3 | DFR |  |  |  | COMPLETED |  | 2025-01-01 |  | Jan'25 | JSC Enterprises | DONE | COMPLETED
3 | 8/4 | Gantry - AP39/0 | DA+3 | DFR |  |  |  | COMPLETED |  | 2025-01-01 |  | Jan'25 | JSC Enterprises | DONE | COMPLETED
4 | 8/6 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-01-01 |  | Jan'25 | Afflux Construction | DONE | COMPLETED
5 | 16/4 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-01-01 |  | Jan'25 | JSC Enterprises | DONE
6 | 8/5 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-02-01 |  | Feb'25 | JSC Enterprises | DONE | COMPLETED
7 | 8/7 | Gantry - AP39/0 | DA+0 | WC |  |  |  | COMPLETED |  | 2025-02-01 |  | Feb'25 | Afflux Construction | DONE | COMPLETED
8 | 8/8 | Gantry - AP39/0 | DA+3 | WC |  |  |  | COMPLETED |  | 2025-02-01 |  | Feb'25 | Afflux Construction | DONE | COMPLETED
9 | 8/2 | Gantry - AP39/0 | DA+3 | DFR |  |  |  | COMPLETED |  | 2025-02-01 |  | Feb'25 | JSC Enterprises | DONE | COMPLETED
10 | 16/1 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-02-01 |  | Feb'25 | Surya Group | DONE | COMPLETED
11 | 15/7 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-02-01 |  | Feb'25 | Surya Group | DONE | COMPLETED
12 | 7/3 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-02-01 |  | Feb'25 | Afflux Construction | DONE | COMPLETED
13 | 9/3 | Gantry - AP39/0 | DA+6 | DFR |  |  |  | COMPLETED |  | 2025-02-01 |  | Feb'25 | JSC Enterprises | DONE
14 | 15/8 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-02-01 |  | Feb'25 | Surya Group | DONE | COMPLETED
15 | 13/1 | Gantry - AP39/0 | DA-1.5 | DFR |  |  |  | COMPLETED |  | 2025-02-01 |  | Feb'25 | Urmila Bibi | DONE | COMPLETED
16 | 15/2 | Gantry - AP39/0 | DA+3 | DFR |  |  |  | COMPLETED |  | 2025-02-01 |  | Feb'25 | Shree Shyam Granite | DONE | COMPLETED
17 | 15/9 | Gantry - AP39/0 | DA+3 | DFR |  |  |  | COMPLETED |  | 2025-02-01 |  | Feb'25 | Surya Group | DONE | COMPLETED
18 | 9/2 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-02-01 |  | Feb'25 | JSC Enterprises | DONE | COMPLETED
19 | 13/2 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-02-01 |  | Feb'25 | Urmila Bibi | DONE | COMPLETED
20 | 7/4 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Afflux Construction | DONE | COMPLETED
21 | 15/4 | Gantry - AP39/0 | DA+6 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Shree Shyam Granite | DONE | COMPLETED
22 | 16/2 | Gantry - AP39/0 | DA-3 | WFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Surya Group | DONE | COMPLETED
23 | 13/4 | Gantry - AP39/0 | DA-3 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Urmila Bibi | DONE
24 | 16/8 | Gantry - AP39/0 | DA-3 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Surya Group | DONE | COMPLETED
25 | 7/2 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Afflux Construction | DONE | COMPLETED
26 | 13/3 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Urmila Bibi | DONE
27 | 10/2 | Gantry - AP39/0 | DA(-)3 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | JSC Enterprises | DONE
28 | 15/1 | Gantry - AP39/0 | DA+0 | WFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Shree Shyam Granite | DONE
29 | 15/5 | Gantry - AP39/0 | DA(-)3 | WFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Surya Group | DONE | COMPLETED
30 | 13/5 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Urmila Bibi | DONE
31 | 10/1 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | JSC Enterprises | DONE
32 | 16/3 | Gantry - AP39/0 | DA+9 | WFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Surya Group | DONE | COMPLETED
33 | 15/3 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Shree Shyam Granite | DONE | COMPLETED
34 | 14/1 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Urmila Bibi | DONE
35 | 16/7 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Surya Group | DONE | COMPLETED
36 | 12/2 | Gantry - AP39/0 | DA-3 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Afflux Construction | DONE | COMPLETED
37 | 14/3 | Gantry - AP39/0 | DA(-)3 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Urmila Bibi | DONE
38 | 12/5 | Gantry - AP39/0 | DA+1.5 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Shree Shyam Granite | DONE
39 | 14/4 | Gantry - AP39/0 | DA+3 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Urmila Bibi | DONE
40 | 16/6 | Gantry - AP39/0 | DA-3 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Surya Group | DONE | COMPLETED
41 | 12/1 | Gantry - AP39/0 | DA+3 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Afflux Construction | DONE | COMPLETED
42 | 12/6 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Shree Shyam Granite | DONE
43 | 14/2 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Urmila Bibi | DONE
44 | 16/9 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Surya Group | DONE | COMPLETED
45 | 16/5 | Gantry - AP39/0 | DA+6 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Surya Group | DONE | COMPLETED
46 | 12/3 | Gantry - AP39/0 | DA(-)3 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Afflux Construction | DONE | COMPLETED
47 | 12/4 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Shree Shyam Granite | DONE
48 | 16/11 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Surya Group | DONE | COMPLETED
49 | 16/10 | Gantry - AP39/0 | DA+6 | WFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Surya Group | DONE | COMPLETED
50 | 24/3 | Gantry - AP39/0 | DA+6 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Surya Group | DONE | COMPLETED
51 | 24/1 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Surya Group | DONE | COMPLETED
52 | 39/4 | AP39/1 - 47/10 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-03-01 |  | Mar'25 | Shree Shyam Granite | DONE | COMPLETED
53 | 39/7 | AP39/1 - 47/10 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Afflux Construction | DONE | COMPLETED
54 | 24/6 | Gantry - AP39/0 | DA+3 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Surya Group | DONE | COMPLETED
55 | 24/2 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Surya Group | DONE | COMPLETED
56 | 39/2 | AP39/1 - 47/10 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Shree Shyam Granite | DONE | COMPLETED
57 | 39/3 | AP39/1 - 47/10 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Shree Shyam Granite | DONE | COMPLETED
58 | 39/5 | AP39/1 - 47/10 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Afflux Construction | DONE | COMPLETED
59 | 24/9 | Gantry - AP39/0 | DA(-)1.5 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Surya Group | DONE | COMPLETED
60 | 24/7 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Surya Group | DONE
61 | 21/1 | Gantry - AP39/0 | DA(-)3 | WC |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Yatharth Construction | DONE
62 | 24/8 | Gantry - AP39/0 | DA+6 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Surya Group | DONE | COMPLETED
63 | 39/1 | AP39/1 - 47/10 | DA+3 | WC |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Shree Shyam Granite | DONE | COMPLETED
64 | 24/10 | Gantry - AP39/0 | DA+1.5 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Surya Group | DONE | COMPLETED
65 | 40/1 | AP39/1 - 47/10 | DA+3 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Afflux Construction | DONE | COMPLETED
66 | 24/11 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Surya Group | DONE | COMPLETED
67 | 24/5 | Gantry - AP39/0 | DA(-)3 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Surya Group | DONE | COMPLETED
68 | 21/2 | Gantry - AP39/0 | DA+0 | WC |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Yatharth Construction | DONE
69 | 41/1 | AP39/1 - 47/10 | DA+6 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Shree Shyam Granite | DONE | COMPLETED
70 | 24/4 | Gantry - AP39/0 | DA(-)3 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Surya Group | DONE | COMPLETED
71 | 44/2 | AP39/1 - 47/10 | DA+3 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Urmila Bibi | DONE | COMPLETED
72 | 40/2 | AP39/1 - 47/10 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Afflux Construction | DONE | COMPLETED
73 | 26/1 | Gantry - AP39/0 | DA+1.5 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Surya Group | DONE | COMPLETED
74 | 8/9 | Gantry - AP39/0 | DA-3 | WC |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | JSC Enterprises | DONE
75 | 26/2 | Gantry - AP39/0 | DA+6 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Surya Group | DONE | COMPLETED
76 | 44/3 | AP39/1 - 47/10 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Urmila Bibi | DONE | COMPLETED
77 | 41/2 | AP39/1 - 47/10 | DA(-)1.5 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Shree Shyam Granite | DONE | COMPLETED
78 | 40/3 | AP39/1 - 47/10 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Afflux Construction | DONE | COMPLETED
79 | 21/3 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Yatharth Construction | DONE
80 | 9/1 | Gantry - AP39/0 | DA+3 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | GM Construction | DONE
81 | 26/3 | Gantry - AP39/0 | DA+6 | WFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Surya Group | DONE | COMPLETED
82 | 26/4 | Gantry - AP39/0 | DA(-)3 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Surya Group | DONE | COMPLETED
83 | 27/2 | Gantry - AP39/0 | DA+0 | WFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Surya Group | DONE | COMPLETED
84 | 27/5 | Gantry - AP39/0 | DA(-)1.5 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Surya Group | DONE | COMPLETED
85 | 8/10 | Gantry - AP39/0 | DA+0 | WC |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | JSC Enterprises | DONE
86 | 41/5 | AP39/1 - 47/10 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Shree Shyam Granite | DONE | COMPLETED
87 | 39/8 | AP39/1 - 47/10 | DA+3 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Afflux Construction | DONE | COMPLETED
88 | 36/8 | Gantry - AP39/0 | DA+0 | WFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Urmila Bibi | DONE | COMPLETED
89 | 27/4 | Gantry - AP39/0 | DA(-)3 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Surya Group | DONE | COMPLETED
90 | 21/4 | Gantry - AP39/0 | DA+3 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Yatharth Construction | DONE
91 | 36/7 | Gantry - AP39/0 | DA+3 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Urmila Bibi | DONE | COMPLETED
92 | 41/8 | AP39/1 - 47/10 | DA+3 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Jeenmata Infratech | DONE | COMPLETED
93 | 5/2 | Gantry - AP39/0 | DA+0 | WC |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | GM Construction | DONE | COMPLETED
94 | 29/1 | Gantry - AP39/0 | DA+1.5 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Surya Group | DONE
95 | 22/1 | Gantry - AP39/0 | DA+6 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Yatharth Construction | DONE
96 | 7/1 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | JSC Enterprises | DONE | COMPLETED
97 | 36/2 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Afflux Construction | DONE | COMPLETED
98 | 36/6 | Gantry - AP39/0 | DA(-)1.5 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Urmila Bibi | DONE | COMPLETED
99 | 34/2 | Gantry - AP39/0 | DA(-)3 | WC |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Jeenmata Infratech | DONE
100 | 29/2 | Gantry - AP39/0 | DA+1.5 | DFR |  |  |  | COMPLETED |  | 2025-04-01 |  | Apr'25 | Surya Group | DONE
101 | 36/3 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED | 23/04/2025 | 02/05/2025 | Apr'25 | May'25 | URMILA-BIBI | DONE
102 | 5/1 | Gantry - AP39/0 | DA(-)3 | DFR |  |  |  | COMPLETED | 28/04/2025 | 2025-03-05 | Apr'25 | May'25 | GM Construction | DONE | COMPLETED
103 | 27/3 | Gantry - AP39/0 | DA+1.5 | DFR |  |  |  | COMPLETED | 28/04/2025 | 2025-03-05 | Apr'25 | May'25 | SURYA-GROUP | DONE | COMPLETED
104 | 23/1 | Gantry - AP39/0 | DA+3 | DFR |  |  |  | COMPLETED | 1/5/2025 | 2025-04-05 | May'25 | May'25 | Yatharth Construction | DONE
105 | 30/1 | Gantry - AP39/0 | DA+1.5 | DFR |  |  |  | COMPLETED | 2/5/2025 | 2025-05-05 | May'25 | May'25 | SURYA-GROUP | DONE | COMPLETED
106 | 34/1 | Gantry - AP39/0 | DA+3 | WFR |  |  |  | COMPLETED | 27/4/2025 | 2025-05-05 | Apr'25 | May'25 | SREE SHAYAM GRANTE | DONE | COMPLETED
107 | 36/4 | Gantry - AP39/0 | DA+3 | DFR |  |  |  | COMPLETED | 23/04/2025 | 2025-05-05 | Apr'25 | May'25 | URMILA-BIBI | DONE
108 | 36/5 | Gantry - AP39/0 | DA+6 | WC |  |  |  | COMPLETED | 30/04/2025 | 2025-05-05 | Apr'25 | May'25 | AFFLUX CONSTRUCTION | DONE | COMPLETED
109 | 5/5 | Gantry - AP39/0 | DA+0 | WC |  |  |  | COMPLETED |  | 2025-05-06 |  | May'25 | GM Construction | DONE
110 | 6/3 | Gantry - AP39/0 | DA+1.5 | DFR |  |  |  | COMPLETED |  | 2025-05-07 |  | May'25 | JSC Enterprises | DONE
111 | 20/1 | Gantry - AP39/0 | DA(-)3 | DFR |  |  |  | COMPLETED |  | 2025-05-08 |  | May'25 | Yatharth Construction | DONE | COMPLETED
112 | 34/3 | Gantry - AP39/0 | DA+6 | WFR |  |  |  | COMPLETED |  | 2025-05-08 |  | May'25 | Jeenmata Infratech | DONE | COMPLETED
113 | 32/3 | Gantry - AP39/0 | DA+1.5 | DFR |  |  |  | COMPLETED |  | 2025-05-08 |  | May'25 | SURYA-GROUP | DONE | COMPLETED
114 | 36/1 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-05-09 |  | May'25 | AFFLUX CONSTRUCTION | DONE | COMPLETED
115 | 5/3 | Gantry - AP39/0 | DA+3 | WC |  |  |  | COMPLETED |  | 2025-05-09 |  | May'25 | GM Construction | DONE | COMPLETED
116 | 32/4 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-05-10 |  | May'25 | SURYA-GROUP | DONE | COMPLETED
117 | 38/4 | Gantry - AP39/0 | DA+3 | DFR |  |  |  | COMPLETED |  | 2025-05-11 |  | May'25 | URMILA-BIBI | DONE | COMPLETED
118 | 20/2 | Gantry - AP39/0 | DA(-)3 | DFR |  |  |  | COMPLETED |  | 2025-05-12 |  | May'25 | YATHARTH-CONSTRUCTION | DONE | COMPLETED
119 | 5/4 | Gantry - AP39/0 | DA+1.5 | WC |  |  |  | COMPLETED |  | 2025-05-13 |  | May'25 | GM Construction | DONE | COMPLETED
120 | 38/3 | Gantry - AP39/0 | DA(-)3 | DFR |  |  |  | COMPLETED |  | 2025-05-13 |  | May'25 | URMILA-BIBI | DONE | COMPLETED
121 | 32/5 | Gantry - AP39/0 | DA+1.5 | DFR |  |  |  | COMPLETED |  | 2025-05-15 |  | May'25 | SURYA-GROUP | DONE | COMPLETED
122 | 6/1 | Gantry - AP39/0 | DA(-)1.5 | DFR |  |  |  | COMPLETED | 2025-05-15 | 2025-05-16 | May'25 | May'25 | JSC Enterprises | DONE | COMPLETED
123 | 38/1 | Gantry - AP39/0 | DA(-)3 | DFR |  |  |  | COMPLETED |  | 2025-05-17 |  | May'25 | URMILA-BIBI | DONE | COMPLETED
124 | 38/7 | Gantry - AP39/0 | DA+0 | WC |  |  |  | COMPLETED | 2025-05-14 | 2025-05-19 | May'25 | May'25 | AFFLUX CONSTRUCTION | DONE | COMPLETED
125 | 47/8 | AP39/1 - 47/10 | DA+0 | DFR |  |  |  | COMPLETED | 14.05.2025 | 19.05.2025 | May'25 | May'25 | Jeenmata Infratech | DONE | COMPLETED
126 | 49/1 | AP 47/11 - AP68 | DA+6 | DFR |  |  |  | COMPLETED | 15/05/2025 | 19.05.2025 | May'25 | May'25 | GM Construction | DONE | COMPLETED
127 | 32/7 | Gantry - AP39/0 | DA(-)1.5 | DFR |  |  |  | COMPLETED | 16/05/2025 | 21/5/2025 | May'25 | May'25 | SURYA-GROUP | DONE | COMPLETED
128 | 32/6 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED | 14/05/2025 | 21/05/2025 | May'25 | May'25 | SURYA-GROUP | DONE | COMPLETED
129 | 51/2 | AP 47/11 - AP68 | DA(-)3 | DFR |  |  |  | COMPLETED | 14.05.2025 | 22.05.2025 | May'25 | May'25 | YATHARTH-CONSTRUCTION | DONE | COMPLETED
130 | 47/11 | AP 47/11 - AP68 | DA+6 | DFR |  |  |  | COMPLETED | 19.05.2025 | 23/5/2025 | May'25 | May'25 | Jeenmata Infratech | DONE | COMPLETED
131 | 5/7 | Gantry - AP39/0 | DA(-)3 | WC |  |  |  | COMPLETED | 19.05.2025 | 23/5/2025 | May'25 | May'25 | URMILA-BIBI | DONE
132 | 38/6 | Gantry - AP39/0 | DA(-)3 | DFR |  |  |  | COMPLETED | 15.05.2025 | 23.05.2025 | May'25 | May'25 | AFFLUX CONSTRUCTION | DONE | COMPLETED
133 | 49/3 | AP 47/11 - AP68 | DA+3 | WC |  |  |  | COMPLETED | 15.05.2025 | 23.05.2025 | May'25 | May'25 | GM Construction | DONE | COMPLETED
134 | 51/1 | AP 47/11 - AP68 | DA+0 | DFR |  |  |  | COMPLETED | 17.05.2025 | 24.05.2025 | May'25 | May'25 | YATHARTH-CONSTRUCTION | DONE | COMPLETED
135 | 32/2 | Gantry - AP39/0 | DA+1.5 | DFR |  |  |  | COMPLETED | 20.05.2025 | 25.05.2025 | May'25 | May'25 | SURYA-GROUP | DONE | COMPLETED
136 | 5/6 | Gantry - AP39/0 | DA+0 | WC |  |  |  | COMPLETED | 20.05.2025 | 25.05.2025 | May'25 | May'25 | URMILA-BIBI | DONE
137 | 49/2 | AP 47/11 - AP68 | DA+0 | DFR |  |  |  | COMPLETED |  | 2025-05-26 |  | May'25 | GM Construction | DONE | COMPLETED
138 | 47/4 | AP39/1 - 47/10 | DA+3 | DFR |  |  |  | COMPLETED | 20.05.2025 | 27.05.2025 | May'25 | May'25 | Jeenmata Infratech | DONE | COMPLETED
139 | 51/3 | AP 47/11 - AP68 | DA(-)3 | DFR |  |  |  | COMPLETED |  | 26.05.2025 |  | May'25 | YATHARTH-CONSTRUCTION | DONE | COMPLETED
140 | 13/0 | Gantry - AP39/0 | DB2+0 | DFR |  |  |  | COMPLETED |  | 30.05.2025 |  | May'25 | URMILA-BIBI | DONE | COMPLETED
141 | 38/8 | Gantry - AP39/0 | DA+6 | WC |  |  |  | COMPLETED |  | 2025-05-29 |  | May'25 | AFFLUX CONSTRUCTION | DONE | COMPLETED
142 | 48/2 | AP 47/11 - AP68 | DA(-)1.5 | DFR |  |  |  | COMPLETED |  | 2025-05-29 |  | May'25 | Jeenmata Infratech | DONE | COMPLETED
143 | 67/2 | AP 47/11 - AP68 | DA(-)3 | WC |  |  |  | COMPLETED | 28.05.2024 | 31.05.2025 | May'25 | May'25 | Shri Sai Brick Udyog | DONE
144 | 48/6 | AP 47/11 - AP68 | DA+3 | DFR |  |  |  | COMPLETED | 26.05.2025 | 01.06.2025 | May'25 | Jun'25 | GM Infratech | SUBMITTED | COMPLETED
145 | 49/4 | AP 47/11 - AP68 | DA+0 | WC |  |  |  | COMPLETED | 19/05/2025 | 01.06.2025 | May'25 | Jun'25 | YATHARTH-CONSTRUCTION | SUBMITTED
146 | 38/2 | Gantry - AP39/0 | DA+0 | DFR |  |  |  | COMPLETED | 19/05/2025 | 02.06.2025 | May'25 | Jun'25 | AFFLUX CONSTRUCTION | SUBMITTED | COMPLETED
147 | 47/6 | AP39/1 - 47/10 | DA+3 | DFR |  |  |  | COMPLETED | 01.06.2025 | 04.06.2025 | Jun'25 | Jun'25 | Jeenmata Infratech | SUBMITTED | COMPLETED
148 | 48/8 | AP 47/11 - AP68 | DA+0 | DFR |  |  |  | COMPLETED | 01.06.2025 | 05.06.2025 | Jun'25 | Jun'25 | GM CONSTRUCTION | SUBMITTED
149 | 49/5 | AP 47/11 - AP68 | DA+0 | WC |  |  |  | COMPLETED | 02.06.2025 | 2025-06-06 | Jun'25 | Jun'25 | YATHARTH-CONSTRUCTION | SUBMITTED
150 | 67/1 | AP 47/11 - AP68 | DA(-)3 | DFR |  |  |  | COMPLETED | 02.06.2025 | 2025-07-06 | Jun'25 | Jul'25 | Shri Sai Brick Udyog | SUBMITTED
151 | 41/4 | AP39/1 - 47/10 | DA+3 | DFR |  |  |  | COMPLETED | 02.06.2025 | 2025-08-06 | Jun'25 | Aug'25 | Jeenmata Infratech | SUBMITTED | COMPLETED
152 | 48/9 | AP 47/11 - AP68 | DA+3 | WC |  |  |  | COMPLETED | 04.06.2025 | 2025-06-10 | Jun'25 | Jun'25 | GM Construction | SUBMITTED
153 | 47/7 | AP39/1 - 47/10 | DA+0 | DFR |  |  |  | COMPLETED | 07.06.2025 | 2025-11-06 | Jun'25 | Jun'25 | Jeenmata Infratech | SUBMITTED | COMPLETED
154 | 66/8 | AP 47/11 - AP68 | DA(-)3 | DFR |  |  |  | COMPLETED | 01.06.2025 | 2025-11-06 | Jun'25 | Jun'25 | Shri Sai Brick Udyog | SUBMITTED | COMPLETED
155 | 49/6 | AP 47/11 - AP68 | DA+6 | DFR |  |  |  | COMPLETED | 03.06.2025 | 14/06/2025 | Jun'25 | Jun'25 | YATHARTH-CONSTRUCTION | SUBMITTED | COMPLETED
156 | 49/0 | AP 47/11 - AP68 | DB1+0 | DFR |  |  |  | COMPLETED | 2025-10-06 | 16/06/2025 | Jun'25 | Jun'25 | GM CONSTRUCTION | SUBMITTED
157 | 66/5 | AP 47/11 - AP68 | DA+3 | DFR |  |  |  | COMPLETED |  | 17.06.2025 | Jun'25 | Jun'25 | Shri Sai Brick Udyog
158 | 65/1 | AP 47/11 - AP68 | DA(-)1.5 | DFR |  |  |  | COMPLETED | 08.06.2025 | 18/6/2025 | Jun'25 | Jun'25 | AFFLUX CONSTRUCTION | SUBMITTED
159 | 41/0 | AP39/1 - 47/10 | DD45+0 | DFR |  |  |  | COMPLETED | 09.06.2025 | 21/06/2025 | Jun'25 | Jun'25 | Jeenmata Infratech | SUBMITTED
160 | 65/2 | AP 47/11 - AP68 | DA+0 | DFR |  |  |  | COMPLETED | 19.06.2025 | 2025-06-23 | Jun'25 | Jun'25 | AFFLUX CONSTRUCTION | NOT SUBMITTED
161 | 66/7 | AP 47/11 - AP68 | DA+6 | DFR |  |  |  | COMPLETED | 08.06.2025 | 27/06/2025 | Jun'25 | Jun'25 | Shri Sai Brick Udyog | NOT SUBMITTED
162 | 65/3 | AP 47/11 - AP68 | DA+0 | DFR |  |  |  | COMPLETED | 16/06/2025 | 30/06/2025 | Jun'25 | Jun'25 | AFFLUX CONSTRUCTION | NOT SUBMITTED
163 | 65/9 | AP 47/11 - AP68 | DA(-)3 | DFR |  |  |  | COMPLETED |  | 2025-07-07 |  | Jul'25 | Shri Sai Brick Udyog
164 | 65/7 | AP 47/11 - AP68 | DA(-)3 | DFR |  |  |  | COMPLETED |  | 14/07/2025 |  |  | Shri Sai Brick Udyog
165 | 63/1 | AP 47/11 - AP68 | DA(-)3 | DFR |  |  |  | COMPLETED | 30.06.2025 | 11.07.2025 | Jun'25 | Jul'25 | AFFLUX CONSTRUCTION
166 | 63/2 | AP 47/11 - AP68 | DA(-)3 | DFR |  |  |  | COMPLETED | 01.07.2025 | 16.07.2025 | Jul'25 | Jul'25 | AFFLUX CONSTRUCTION
167 | 65/11 | AP 47/11 - AP68 | DA+6 | DFR |  |  |  | COMPLETED |  | 22.07.2025 |  | Jul'25 | Shri Sai Brick Udyog
168 | 7/0 | Gantry - AP39/0 | DC2+0 | WC |  |  |  | COMPLETED | 16.07.2025 | 19.08.2025 | Jul'25 | Aug'25 | AFFLUX CONSTRUCTION
169 | 21/0 | Gantry - AP39/0 | DC2+0 | WFR |  |  |  | COMPLETED | 02.08.2025 | 12.08.2025 | Aug'25 | Aug'25 | SHAKHINA BIBI
170 | 46/0 | AP39/1 - 47/10 | DD45+0 | DFR |  |  |  | COMPLETED | 26.07.2025 | 12.08.2025 | Jul'25 | Aug'25 | Shri Sai Brick Udyog
171 | 45/1 | AP39/1 - 47/10 | DA+0 | DFR |  |  |  | COMPLETED | 06.08.2025 | 19.08.2025 | Aug'25 | Aug'25 | SHREE KHATUSHAYAM CONST.
172 | 15/0 | Gantry - AP39/0 | DB2+0 | WFR |  |  |  | COMPLETED | 11.08.2025 | 18.08.2025 | Aug'25 | Aug'25 | Shakhina Bibi
173 | 46A/0 | AP39/1 - 47/10 | DC1+0 | WFR |  |  |  | COMPLETED | 12.08.2025 | 14.09.2025 | Aug'25 | Sep'25 | Shri Sai Brick Udyog
174 | 45/3 | AP39/1 - 47/10 | DA+0 | DFR |  |  |  | COMPLETED | 20.08.2025 | 16.09.2025 | Aug'25 | Sep'25 | SHREE KHATUSHAYAM CONST.
175 | 33/0 | Gantry - AP39/0 | DD45+0 | WFR |  |  |  | COMPLETED | 20.08.2025 | 22.09.2025 | Aug'25 | Sep'25 | Shakhina Bibi
176 | 10/0 | Gantry - AP39/0 | DB1+0 | WFR |  |  |  | COMPLETED | 20.08.2025 | 13.10.2025 | Aug'25 | Oct'25 | AFFLUX CONSTRUCTION
177 | 34/0 | Gantry - AP39/0 | DC1+3 | WFR |  |  |  | COMPLETED | 25.08.2025 | 14.09.2025 | Aug'25 | Sep'25 | SHAKHINA BIBI
178 | 45/4 | AP39/1 - 47/10 | DA+1.5 | WFR |  |  |  | COMPLETED | 22.09.2025 | 30.09.2025 | Sep'25 | Sep'25 | SHREE KHATUSHAYAM CONST.
179 | 46/2 | AP39/1 - 47/10 | DA+3 | WFR |  |  |  | COMPLETED | 19.09.2025 | 13.10.2025 | Sep'25 | Oct'25 | Shri Balaji Contractor
180 | 46A/1 | AP39/1 - 47/10 | DA+3 | DFR |  |  |  | COMPLETED | 22.09.2025 | 11.10.2025 | Sep'25 | Oct'25 | Durga construction
181 | 12/7 | Gantry - AP39/0 | DA+0 | WFR |  |  |  | COMPLETED | 22.09.2025 | 29.09.2025 | Sep'25 | Sep'25 | SHAKHINA BIBI
182 | 10/3 | Gantry - AP39/0 | DA+3 | WFR |  |  |  | COMPLETED | 27.09.2025 | 01.10.2025 | Sep'25 | Oct'25 | SHAKHINA BIBI
183 | 14/5 | Gantry - AP39/0 | DA+0 | WFR |  |  |  | COMPLETED | 01.10.2025 | 06.10.2025 | Oct'25 | Oct'25 | MAUSAUDDIN SK
184 | 8/0 | Gantry - AP39/0 | DB1+0 | WFR |  |  |  | COMPLETED | 09.10.2025 | 15.10.2025 | Oct'25 | Oct'25 | MAUSAUDDIN SK
185 | 9/0 | Gantry - AP39/0 | DB2+0 | DFR |  |  |  | COMPLETED | 15.10.2025 | 23/10/2025 | Oct'25 | Oct'25 | MAUSAUDDIN SK
186 | 45A/0 | AP39/1 - 47/10 | DC2+0 | DFR |  |  |  | COMPLETED | 29.09.2205 | 07.11.2025 | Sep'25 | Nov'25 | SHREE KHATUSHAYAM CONST.
187 | 46A/2 | AP39/1 - 47/10 | DA(-)3 | WFR |  |  |  | COMPLETED | 07.10.2025 | 06.11.2025 | Oct'25 | Nov'25 | Durga construction
188 | 66/0 | AP 47/11 - AP68 | DB1+0 | WC |  |  |  | COMPLETED | 07.10.2025 | 03.11.2025 | Oct'25 | Nov'25 | DS Construction
189 | 46A/3 | AP39/1 - 47/10 | DA(-)3 | WFR |  |  |  | COMPLETED | 11.10.2025 | 26.10.2025 | Oct'25 | Oct'25 | Shri Balaji Contractor
190 | 47/1 | AP39/1 - 47/10 | DA+0 | WFR |  |  |  | COMPLETED | 15.10.2025 | 08.11.2025 | Oct'25 | Nov'25 | Shri Balaji Contractor
191 | 47/2 | AP39/1 - 47/10 | DA+6 | WFR |  |  |  | COMPLETED | 15.10.2025 | 05.11.2025 | Oct'25 | Nov'25 | Durga construction
192 | 66/2 | AP 47/11 - AP68 | DA+0 | WFR |  |  |  | COMPLETED | 15.10.2025 | 05.11.2025 | Oct'25 | Nov'25 | Jay bhawani construction
193 | 47/3 | AP39/1 - 47/10 | DA+0 | WFR |  |  |  | COMPLETED | 17.10.2025 | 13.11.2025 | Oct'25 | Nov'25 | SHREE KHATUSHAYAM CONST.
194 | 16/0 | Gantry - AP39/0 | DB1+0 | DFR |  |  |  | COMPLETED | 19.10.2025 | 25.10.2025 | Oct'25 | Oct'25 | MAUSAUDDIN SK
195 | 18/1 | Gantry - AP39/0 | DA+6 | WET |  |  |  | COMPLETED | 28.10.2025 | 05.11.2025 | Oct'25 | Nov'25 | MAUSAUDDIN SK
196 | 65/8 | AP 47/11 - AP68 | DA+1.5 | DFR |  |  |  | COMPLETED | 31.10.2025 | 13.11.2025 | Oct'25 | Nov'25 | AFFLUX CONSTRUCTION
197 | 66/6 | AP 47/11 - AP68 | DA(-)1.5 | WFR |  |  |  | COMPLETED | 03.11.2025 | 20.11.2025 | Nov'25 | Nov'25 | Hemraj yadav
198 | 61/1 | AP 47/11 - AP68 | DA+6 |  |  |  |  | No Progress (Water pipe line) | 24.11.2025 |  |  |  | Shri Balaji Contractor
199 | 64/0 | AP 47/11 - AP68 | DD45+0 | DFR |  |  |  | COMPLETED | 24.07.2025 | 29.10.2025 | Jul'25 | Oct'25 | AFFLUX CONSTRUCTION
200 | 64/1 | AP 47/11 - AP68 | DA+6 | WFR |  |  |  | COMPLETED | 06.09.2025 | 30.10.2025 | Jul'25 | Oct'25 | AFFLUX CONSTRUCTION
201 | 17/0 | Gantry - AP39/0 | DB2+3 | DFR |  |  |  | COMPLETED | 30.10.2025 | 03.11.2025 | Oct'25 | Nov'25 | MAUSAUDDIN SK
202 | 63/3 | AP 47/11 - AP68 | DA(-)3 | DFR |  |  |  | COMPLETED | 30.10.2025 | 08.11.2025 | Oct'25 | Nov'25 | AFFLUX CONSTRUCTION
203 | 18/0 | Gantry - AP39/0 | DA+6 | WFR |  |  |  | COMPLETED | 03.11.2025 | 15.11.2025 | Nov'25 | Nov'25 | MAUSAUDDIN SK
204 | 65/5 | AP 47/11 - AP68 | DA(-)3 | DFR |  |  |  | COMPLETED | 28.10.2025 | 19.11.2025 | Oct'25 | Nov'25 | Shree Mahakal const.
205 | 66/3 | AP 47/11 - AP68 | DA+6 | WFR |  |  |  | COMPLETED | 07.11.2025 | 18.11.2025 | Nov'25 | Nov'25 | Jai bhawani construction
206 | 66/4 | AP 47/11 - AP68 | DA(-)3 | WFR |  |  |  | COMPLETED | 08.11.2025 | 23.11.2025 | Nov'25 | Nov'25 | DS Construction
207 | 65/0 | AP 47/11 - AP68 | DC2+0 | DFR |  |  |  | COMPLETED | 13.11.2025 | 02.12.2025 | Nov'25 | Dec'25 | AFFLUX CONSTRUCTION
208 | 45/0 | AP39/1 - 47/10 | DC1+0 | DFR |  |  |  | COMPLETED | 12.11.2025 | 21.11.2025 | Nov'25 | Nov'25 | Durga construction
209 | 67/0 | AP 47/11 - AP68 | DB2+6 | DFR |  |  |  | COMPLETED | 13.11.2025 | 04.12.2025 | Nov'25 | Dec'25 | Shri Balaji Contractor
210 | 40/0 | AP39/1 - 47/10 | DC1+0 | WET |  |  |  | COMPLETED | 14.11.2025 | 07.12.2025 | Nov'25 | Dec'25 | SHREE KHATUSHAYAM CONST.
211 | 6/0 | Gantry - AP39/0 | DC2+0 | WET |  |  |  | COMPLETED | 13.11.2025 | 21.11.2025 | Nov'25 | Nov'25 | MAUSAUDDIN SK
212 | 23/0 | Gantry - AP39/0 | DD45+3 | DFR |  |  |  | COMPLETED | 15.11.2025 | 29.11.2025 | Nov'25 | Nov'25 | MAUSAUDDIN SK
213 | 55/2 | AP 47/11 - AP68 | DA+3 | DFR |  |  |  | COMPLETED | 10.11.2025 | 23.11.2025 | Nov'25 | Nov'25 | Shree ram construction
214 | 6/2 | Gantry - AP39/0 | DA+1.5 | WFR |  |  |  | COMPLETED | 17.11.2025 | 24.11.2025 | Nov'25 | Nov'25 | MAUSAUDDIN SK
215 | 55/1 | AP 47/11 - AP68 | DA+6 | WFR |  |  |  | COMPLETED | 04.12.2025 | 16.12.2025 | Dec'25 | Dec'25 | Shree ram construction
216 | 14/0 | Gantry - AP39/0 | DC1+0 | DFR |  |  |  | COMPLETED | 25.11.2025 | 01.12.2025 | Nov'25 | Dec'25 | MAUSAUDDIN SK
217 | 52/1 | AP 47/11 - AP68 | DA+1.5 | DFR |  |  |  | COMPLETED | 19.11.2025 | 03.12.2025 | Nov'25 | Dec'25 | Shree ram construction
218 | 53/0 | AP 47/11 - AP68 | DB2+3 | DFR |  |  |  | COMPLETED | 27.11.2025 | 13.12.2025 | Nov'25 | Dec'25 | AFFLUX CONSTRUCTION
219 | 68/0 | AP 47/11 - AP68 | DB2+6 | WC |  |  |  | COMPLETED | 27.11.2025 | 27.12.2025 | Nov'25 | Dec'25 | Durga construction
220 | 32/1 | Gantry - AP39/0 | DB1+9 | WFR |  |  |  | COMPLETED | 29.11.2025 | 07.12.2025 | Nov'25 | Dec'25 | MAUSAUDDIN SK
221 | 48/4 | AP 47/11 - AP68 | DA(-)1.5 | DFR |  |  |  | COMPLETED | 29.11.2025 | 09.12.2025 | Nov'25 | Dec'25 | Durga construction
222 | 11/0 | Gantry - AP39/0 | DD60+25 | WFR |  |  |  | COMPLETED | 01.12.2025 | 09.12.2025 | Dec'25 | Dec'25 | MAUSAUDDIN SK -II
223 | 56/2 | AP 47/11 - AP68 | DB1+6 | WFR |  |  |  | COMPLETED | 05.12.2025 | 19.12.2025 | Dec'25 | Dec'25 | Shri Balaji Contractor
224 | 39/0 | Gantry - AP39/0 | DC1+0 | WC |  |  |  | COMPLETED | 06.12.2025 | 20.12.2025 | Dec'25 | Dec'25 | Jai bhawani construction
225 | 53B/1 | AP 47/11 - AP68 | DA+3 | DFR |  |  |  | COMPLETED | 10.12.2025 | 21.12.2025 | Dec'25 | Dec'25 | Jai shree ram construction
226 | 52/0 | AP 47/11 - AP68 | DC2+0 | DFR |  |  |  | COMPLETED | 15.12.2025 | 09.01.2026 | Dec'25 | Jan'26 | AFFLUX CONSTRUCTION
227 | 29/0 | Gantry - AP39/0 | DD45+18 | DFR |  |  |  | COMPLETED | 10.12.2025 | 16.12.2025 | Dec'25 | Dec'25 | MAUSAUDDIN SK-I
228 | 25/0 | Gantry - AP39/0 | DC2+18 | WFR |  |  |  | COMPLETED | 10.12.2025 | 22.12.2025 | Dec'25 | Dec'25 | MAUSAUDDIN SK -II
229 | 38/0 | Gantry - AP39/0 | DD45+9 | DFR |  |  |  | COMPLETED | 16.12.2025 | 07.01.2025 | Dec'25 | Dec'25 | Shri Balaji Contractor
230 | 27/0 | Gantry - AP39/0 | DB2+9 | WFR |  |  |  | COMPLETED | 17.12.2025 | 26.12.2025 | Dec'25 | Dec'25 | MAUSAUDDIN SK-I
231 | 30/2 | Gantry - AP39/0 | DA+0 | WFR |  |  |  | COMPLETED | 23.12.2025 | 30.12.2025 | Dec'25 | Dec'25 | MAUSAUDDIN SK-I
232 | 36/0 | Gantry - AP39/0 | DC2+0 | WC |  |  |  | COMPLETED | 09.01.2026 | 21.01.2026 | Jan'26 | Jan'26 | MAUSAUDDIN SK-I
233 | 48/3 | AP 47/11 - AP68 | DA+3 | WC |  |  |  | COMPLETED | 27.12.2025 | 4.01.2026 | Dec'25 | Jan'26 | Jai bhawani construction
234 | 30/0 | Gantry - AP39/0 | DC1+0 | DFR |  |  |  | COMPLETED | 13.01.2026 | 29.01.2026 | Jan'26 | Jan'26 | MAUSAUDDIN SK-I
235 | 48/1 | AP 47/11 - AP68 | DA+0 | DFR |  |  |  | COMPLETED | 14.01.2026 | 24.01.2026 | Jan'26 | Jan'26 | Jai bhawani construction
236 | 48/5 | AP 47/11 - AP68 | DA+0 | DFR |  |  |  | COMPLETED | 24.01.2026 | 01.02.2026 | Jan'26 | Feb'26 | Jai bhawani construction
237 | 26/0 | Gantry - AP39/0 | DC2+12 | DFR |  |  |  | COMPLETED | 28.01.2026 | 06.02.2026 | Jan'26 | Feb'26 | MAUSAUDDIN SK-I
238 | 27/1 | Gantry - AP39/0 | DB1+9 | WFR |  |  |  | COMPLETED | 06.02.2026 | 12.02.2026 | Feb'26 | Feb'26 | MAUSAUDDIN SK-I
239 | 37/0 | Gantry - AP39/0 | DD45+12 | DFR |  |  |  | COMPLETED | 11.02.2026 | 25.02.2026 | Feb'26 | Feb'26 | Hemraj yadav
240 | 31/0 | Gantry - AP39/0 | DD60+0 | WFR |  |  |  | COMPLETED | 12.02.2026 | 23.02.2026 | Feb'26 | Feb'26 | MAUSAUDDIN SK-I
241 | 32/0 | Gantry - AP39/0 | DC2+0 | DFR |  |  |  | COMPLETED | 22.02.2026 | 28.02.2026 | Feb'26 | Feb'26 | MAUSAUDDIN SK-I
242 | 53A/0 | AP 47/11 - AP68 | DB1(-)1.5 | DFR |  |  |  | COMPLETED | 28.02.2026 | 14.03.2026 | Feb'26 | Mar'26 | Hemraj yadav
243 | 39/6 | AP39/1 - 47/10 | DC2+0 | DFR |  |  |  | COMPLETED | 26.02.2026 | 21.03.2026 | Feb'26 | Mar'26 | AFFLUX CONSTRUCTION
244 | 41/7 | AP39/1 - 47/10 | DA+6 | DFR |  |  |  | COMPLETED | 11.03.2026 | 26.03.2026 | Mar'26 | Mar'26 | Khatu Shyam construction
245 | 53B/0 | AP 47/11 - AP68 | DB2(-)1.5 | DFR |  |  |  | COMPLETED | 17.03.2026 | 30.03.2026 | Mar'26 | Mar'26 | Hemraj yadav
246 | 48/0 | AP 47/11 - AP68 | DB1+0 | WET |  |  |  | COMPLETED | 15.03.2026 | 05.04.2026 | Mar'26 | Apr'26 | Jai bhawani construction
247 | 41/3 | AP39/1 - 47/10 | DA+1.5 | WC |  |  |  | COMPLETED | 19.03.2026 | 2026-04-10 | Mar'26 | Apr'26 | Khatu Shyam construction
248 | 65/4 | AP 47/11 - AP68 | DA(-)1.5 | DFR |  |  |  | COMPLETED | 19.03.2026 | 05.04.2026 | Mar'26 | Apr'26 | Shri Balaji Contractor
249 | 39/10 | AP39/1 - 47/10 | DA+0 | DFR |  |  |  | COMPLETED | 22.03.2026 | 31.03.2026 | Mar'26 | Mar'26 | AFFLUX CONSTRUCTION
250 | 39/11 | AP39/1 - 47/10 | DA+3 | WC |  |  |  | COMPLETED | 26.03.2026 | 2026-04-08 | Mar'26 | Apr'26 | AFFLUX CONSTRUCTION
251 | 28/0 | Gantry - AP39/0 | DD45+6 | DFR |  |  |  | COMPLETED | 27.03.2026 | 04.04.2026 | Mar'26 | Apr'26 | MAUSAUDDIN SK-I
252 | 54/0 | AP 47/11 - AP68 | DC2+18 | DFR |  |  |  | COMPLETED | 31.03.2026 | 2026-04-18 | Apr'26 | Apr'26 | Hemraj yadav
253 | 35/0 | Gantry - AP39/0 | DB2+3 | WET |  |  |  | COMPLETED | 01.04.2026 | 2026-04-09 | Apr'26 | Apr'26 | MAUSAUDDIN SK-I
254 | 47/10 | AP39/1 - 47/10 | DA+3 | WC | W3 | 6.5744 |  | COMPLETED | 2026-04-14 | 2026-05-22 | Apr'26 | May'26 | Hemraj Yadav
255 | 5/0 | Gantry - AP39/0 | DB1+0 | WC |  |  |  | COMPLETED | 2026-04-10 | 2026-04-14 | Apr'26 | Apr'26 | MAUSAUDDIN SK-I
256 | 50/0 | AP 47/11 - AP68 | DC2+18 | DFR | W1 | 22.4353 |  | COMPLETED | 2026-04-10 | 2026-05-05 | Apr'26 | May'26 | Jai bhawani construction
257 | 39/9 | AP39/1 - 47/10 | DA+3 | DFR |  |  |  | COMPLETED | 2026-04-10 | 2026-04-25 | Apr'26 | Apr'26 | AFFLUX CONSTRUCTION
258 | 45/2 | AP39/1 - 47/10 | DA+0 | DFR | W1 | 6.3707 |  | COMPLETED | 2026-04-14 | 2026-05-04 | Apr'26 | May'26 | AFFLUX CONSTRUCTION
259 | 4/6 | Gantry - AP39/0 | DA+6 | DFR |  |  |  | COMPLETED | 2026-04-10 | 2026-04-16 | Apr'26 | Apr'26 | MAUSAUDDIN SK-I
260 | 47/9 | AP39/1 - 47/10 | DA+0 | WC | W2 | 5.496 |  | COMPLETED | 2026-05-05 | 2026-05-14 | May'26 | May'26 | AFFLUX CONSTRUCTION
261 | 4/3 | Gantry - AP39/0 | DA(-)3 | DFR |  |  |  | COMPLETED | 2026-04-16 | 2026-04-20 | Apr'26 | Apr'26 | MAUSAUDDIN SK-I
262 | 4/4 | Gantry - AP39/0 | DA+6 | DFR |  |  |  | COMPLETED | 2026-04-16 | 2026-04-18 | Apr'26 | Apr'26 | MAUSAUDDIN SK-I
263 | 3/1 | Gantry - AP39/0 | DA(-)1.5 | DFR |  |  |  | COMPLETED | 2026-04-27 | 2026-04-29 | Apr'26 | Apr'26 | MAUSAUDDIN SK-I
264 | 4/0 | Gantry - AP39/0 | DC1+0 | DFR | W1 | 16.9383 |  | COMPLETED | 2026-05-01 | 2026-05-06 | May'26 | May'26 | MAUSAUDDIN SK-I
265 | 4/5 | Gantry - AP39/0 | DA(-)3 | DFR | W1 | 6.232 |  | COMPLETED | 2026-04-28 | 2026-05-02 | Apr'26 | May'26 | MAUSAUDDIN SK-I
266 | 51/0 | AP 47/11 - AP68 | DD45+9 | DFR | W4 | 26.7456 |  | COMPLETED | 2026-05-08 | 2026-05-31 | May'26 | May'26 | Balaji Construction
267 | 3/0 | Gantry - AP39/0 | DD45+3 | DFR | W2 | 26.7446 |  | COMPLETED | 2026-05-07 | 2026-05-12 | May'26 | May'26 | Musauddin Sk
268 | 2/0 | Gantry - AP39/0 | DD60+0 | DFR | W3 | 31.6817 |  | COMPLETED | 2026-05-13 | 2026-05-19 | May'26 | May'26 | Musauddin Sk
269 | 63/0 | AP 47/11 - AP68 | DC2+12 | DFR | W4 | 19.3131 |  | COMPLETED | 2026-05-12 | 2026-06-07 | May'26 | June'26 | Hemraj yadav
270 | 47/0 | AP39/1 - 47/10 | DC1+3 | DFR | W4 | 17.271 |  | COMPLETED | 2026-05-16 | 2026-06-06 | May'26 | June'26 | Khatu Shyam construction
271 | 3/2 | Gantry - AP39/0 | DA+6 | DFR | W3 | 7.2372 |  | COMPLETED | 2026-05-16 | 2026-05-20 | May'26 | May'26 | Musauddin Sk
272 | 47/5 | AP39/1 - 47/10 | DA+3 | DFR |  |  |  | COMPLETED | 2026-06-15 | 2026-06-20 | Jun'26 | June'26 | Mausauddin sk
273 | 1/0 | Gantry - AP39/0 | DD60+0 | DFR |  |  |  | COMPLETED | 2026-06-06 | 2026-06-15 | Jun'26 | June'26 | Musauddin Sk
274 | 62/0 | AP 47/11 - AP68 | DB1+12 | DFR |  |  |  | COMPLETED | 2026-06-07 | 2026-06-14 | Jun'26 | June'26 | Hemraj Yadav
275 | 59/1 | AP 47/11 - AP68 | DA+9 | DFR |  |  |  | COMPLETED | 2026-06-15 | 2026-06-23 | Jun'26 | June'26 | Hemraj Yadav
276 | 60/0 | AP 47/11 - AP68 | DC2+6 | DFR |  |  |  | Pit-B Frustum Complete Pit C- Pyramid & Chimney completed, Pit-D - Excavation u/p | 2026-06-15 |  | Jun'26 | June'26 | Mausauddin sk
277 | 61/0 | AP 47/11 - AP68 | DB1+9 |  |  |  |  | Excavation u/p | 2026-06-15 |  | Jun'26 | June'26 | Hemraj Yadav
278 | 65/10 | AP 47/11 - AP68 | DA+9 |  |  |  |  | Excavation u/p | 2026-06-24 |  | Jun'26 |  | Hemraj Yadav

## ERECTION
ERECTION-STATUS |  |  |  | 141.4961 | 3255.9122
SL NO. | LOC No. | Tower Type | Comp WK | Rev | MT | District wise section | STATUS | STARTING DATE | ENDING DATE | Work starting month | Work completion Month | Sub-Contractor | JMC
1 | 16/4 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 22/08/2025 | 2025-09-03 | Aug'25 | Sep'25 | DEVI CONST.-I
2 | 13/2 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 22/08/2025 | 15.09.2025 | Aug'25 | Sep'25 | DEONATH MAHATO
3 | 8/5 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 25/08/2025 | 08.09.2025 | Aug'25 | Sep'25 | JWALA SINGH
4 | 12/6 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 25/08/2025 | 18.09.2025 | Aug'25 | Sep'25 | MODINA INDIA
5 | 12/1 | DA+3 |  |  |  | Gantry - AP39/0 | COMPLETED | 02.09.2025 | 23.09.2025 | Sep'25 | Sep'25 | OM CONSTRUCTION
6 | 15/2 | DA+3 |  |  |  | Gantry - AP39/0 | COMPLETED | 02.09.2025 | 12.09.2025 | Sep'25 | Sep'25 | HEMLAL MAHATO-I (Anita Devi)
7 | 20/1 | DA(-)3 |  |  |  | Gantry - AP39/0 | COMPLETED | 07.09.2025 | 14.09.2025 | Sep'25 | Sep'25 | DEVI CONST.-I
8 | 16/1 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 07.09.2025 | 12.09.2025 | Sep'25 | Sep'25 | DEVI CONST.-II
9 | 8/6 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 25/08/2025 | 14.09.2025 | Aug'25 | Sep'25 | JWALA SINGH
10 | 13/4 | DA(-)3 |  |  |  | Gantry - AP39/0 | COMPLETED | 13.09.2025 | 27.09.2025 | Sep'25 | Sep'25 | DEONATH MAHATO
11 | 15/5 | DA(-)3 |  |  |  | Gantry - AP39/0 | COMPLETED | 11.09.2025 | 19.09.2025 | Sep'25 | Sep'25 | HEMLAL MAHATO-I (Anita Devi)
12 | 16/8 | DA(-)3 |  |  |  | Gantry - AP39/0 | COMPLETED | 13.09.2025 | 19.09.2025 | Sep'25 | Sep'25 | DEVI CONST.-I
13 | 8/7 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 14.09.2025 | 20.09.2025 | Sep'25 | Sep'25 | JWALA SINGH
14 | 22/1 | DA+6 |  |  |  | Gantry - AP39/0 | COMPLETED | 15.09.2025 | 23.09.2025 | Sep'25 | Sep'25 | DEVI CONST.-II
15 | 12/2 | DA(-)3 |  |  |  | Gantry - AP39/0 | COMPLETED | 25.09.2025 | 04.10.2025 | Sep'25 | Oct'25 | OM CONSTRUCTION
16 | 14/1 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 16.09.2025 | 24.09.2025 | Sep'25 | Sep'25 | HEMLAL MAHATO-II (Anita Devi)
17 | 16/9 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 19.09.2025 | 25.09.2025 | Sep'25 | Sep'25 | DEVI CONST.-I
18 | 9/1 | DA+3 |  |  |  | Gantry - AP39/0 | COMPLETED | 20.09.2025 | 26.09.2025 | Sep'25 | Sep'25 | JWALA SINGH
19 | 20/2 | DA(-)3 |  |  |  | Gantry - AP39/0 | COMPLETED | 23.09.2025 | 29.09.2025 | Sep'25 | Sep'25 | DEVI CONST.-II
20 | 14/2 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 24.09.2025 | 30.09.2025 | Sep'25 | Sep'25 | HEMLAL MAHATO-I (Anita Devi)
21 | 16/7 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 01.10.2025 | 06.10.2025 | Oct'25 | Oct'25 | DEVI CONST.-I
22 | 10/1 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 27.09.2025 | 02.10.2025 | Sep'25 | Oct'25 | JWALA SINGH
23 | 13/1 | DA(-)1.5 |  |  |  | Gantry - AP39/0 | COMPLETED | 01.10.2025 | 13.10.2025 | Oct'25 | Oct'25 | DEONATH MAHATO
24 | 16/11 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 25.09.2025 | 01.10.2025 | Sep'25 | Oct'25 | DEVI CONST.-I
25 | 24/6 | DA+3 |  |  |  | Gantry - AP39/0 | COMPLETED | 01.10.2025 | 06.10.2025 | Oct'25 | Oct'25 | DEVI CONST.-II
26 | 14/3 | DA(-)3 |  |  |  | Gantry - AP39/0 | COMPLETED | 05.10.2025 | 16.10.2025 | Oct'25 | Oct'25 | OM CONSTRUCTION
27 | 24/7 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 07.10.2025 | 11.10.2025 | Oct'25 | Oct'25 | DEVI CONST.
28 | 8/10 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 12.10.2025 | 16.10.2025 | Oct'25 | Oct'25 | DEVI CONST.
29 | 8/9 | DA(-)3 |  |  |  | Gantry - AP39/0 | COMPLETED | 17.10.2025 | 22.10.2025 | Oct'25 | Oct'25 | DEVI CONST.
30 | 8/8 | DA+3 |  |  |  | Gantry - AP39/0 | COMPLETED | 24.10.2025 | 2025-10-25 | Oct'25 | Oct'25 | DEVI CONST.
31 | 9/2 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 26.10.2025 | 02.11.2025 | Oct'25 | Nov'25 | DEVI CONST.
32 | 8/4 | DA+3 |  |  |  | Gantry - AP39/0 | COMPLETED | 03.11.2025 | 07.11.2025 | Nov'25 | Nov'25 | DEVI CONST.
33 | 10/2 | DA(-)3 |  |  |  | Gantry - AP39/0 | COMPLETED | 08.11.2025 | 11.11.2025 | Nov'25 | Nov'25 | DEVI CONST.
34 | 15/4 | DA+6 |  |  |  | Gantry - AP39/0 | COMPLETED | 13.11.2025 | 25.11.2025 | Nov'25 | Nov'25 | Arawali infra-1
35 | 16/2 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 13.11.2025 | 24.11.2025 | Nov'25 | Nov'25 | Arawali infra-2
36 | 21/4 | DA+3 |  |  |  | Gantry - AP39/0 | COMPLETED | 27.11.2025 | 09.12.2025 | Nov'25 | Dec'25 | Kaushlya Devi | 44
37 | 12/3 | DA(-)3 |  |  |  | Gantry - AP39/0 | COMPLETED | 11.11.2025 | 16.11.2025 | Nov'25 | Nov'25 | DEVI CONST.
38 | 13/0 | DB2+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 16.11.2025 | 27.11.2025 | Nov'25 | Nov'25 | DEVI CONST.
39 | 5/1 | DA(-)3 |  |  |  | Gantry - AP39/0 | COMPLETED | 20.11.2025 | 25.11.2025 | Nov'25 | Nov'25 | JWALA SINGH
40 | 5/3 | DA+3 |  |  |  | Gantry - AP39/0 | COMPLETED | 26.11.2025 | 30.11.2025 | Nov'25 | Nov'25 | JWALA SINGH
41 | 15/9 | DA+3 |  |  |  | Gantry - AP39/0 | COMPLETED | 26.11.2025 | 04.12.2025 | Nov'25 | Dec'25 | Arawali infra-2
42 | 15/3 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 27.11.2025 | 05.12.2025 | Nov'25 | Dec'25 | Arawali infra-1
43 | 8/1 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 28.11.2025 | 03.12.2025 | Nov'25 | Dec'25 | DEVI CONST.
44 | 5/5 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 01.12.2025 | 05.12.2025 | Dec'25 | Dec'25 | JWALA SINGH
45 | 15/1 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 07.12.2025 | 15.12.2025 | Dec'25 | Dec'25 | Arawali infra-1
46 | 15/8 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 04.12.2025 | 12.12.2025 | Dec'25 | Dec'25 | Arawali infra-2
47 | 5/7 | DA(-)3 |  |  |  | Gantry - AP39/0 | COMPLETED | 06.12.2025 | 11.12.2025 | Dec'25 | Dec'25 | JWALA SINGH
48 | 8/0 | DB1+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 05.12.2025 | 16.12.2025 | Dec'25 | Dec'25 | DEVI CONST.
49 | 15/7 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 11.12.2025 | 19.12.2025 | Dec'25 | Dec'25 | Arawali infra-2
50 | 65/7 | DA(-)3 |  |  |  | AP 47/11 - AP68 | COMPLETED | 11.12.2025 | 17.12.2025 | Dec'25 | Dec'25 | Anita Devi
51 | 7/3 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 12.12.2025 | 16.12.2025 | Dec'25 | Dec'25 | JWALA SINGH
52 | 18/1 | DA+6 |  |  |  | Gantry - AP39/0 | COMPLETED | 14.12.2025 | 06.01.2026 | Dec'25 | Jan'26 | Kaushlya Devi
53 | 32/3 | DA+1.5 |  |  |  | Gantry - AP39/0 | COMPLETED | 16.12.2025 | 23.12.2025 | Dec'25 | Dec'25 | Arawali infra-1
54 | 7/2 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 17.12.2025 | 21.12.2025 | Dec'25 | Dec'25 | JWALA SINGH
55 | 8/2 | DA+3 |  |  |  | Gantry - AP39/0 | COMPLETED | 18.12.2025 | 22.12.2025 | Dec'25 | Dec'25 | DEVI CONST.
56 | 66/0 | DB1+0 |  |  |  | AP 47/11 - AP68 | COMPLETED | 19.12.2025 | 28.12.2025 | Dec'25 | Dec'25 | Anita Devi
57 | 16/0 | DB1+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 21.12.2025 | 31.12.2025 | Dec'25 | Dec'25 | Arawali infra-2
58 | 9/0 | DB2+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 22.12.2025 | 29.12.2025 | Dec'25 | Dec'25 | JWALA SINGH
59 | 8/3 | DA+3 |  |  |  | Gantry - AP39/0 | COMPLETED | 23.12.2025 | 28.12.2025 | Dec'25 | Dec'25 | DEVI CONST.
60 | 32/4 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 24.12.2025 | 30.12.2025 | Dec'25 | Dec'25 | Arawali infra-1
61 | 9/3 | DA+6 |  |  |  | Gantry - AP39/0 | COMPLETED | 30.12.2025 | 04.01.2026 | Dec'25 | Jan'26 | JWALA SINGH
62 | 6/3 | DA+1.5 |  |  |  | Gantry - AP39/0 | COMPLETED | 30.12.2025 | 03.01.2026 | Dec'25 | Jan'26 | DEVI CONST.
63 | 16/10 | DA+6 |  |  |  | Gantry - AP39/0 | COMPLETED | 02.01.2026 | 12.01.2026 | Jan'26 | Jan'26 | Arawali infra-2
64 | 65/2 | DA+0 |  |  |  | AP 47/11 - AP68 | COMPLETED | 31.12.2025 | 09.01.2026 | Dec'25 | Jan'26 | Anita Devi
65 | 32/6 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 31.12.2025 | 06.01.2026 | Dec'25 | Jan'26 | Arawali infra-1
66 | 7/4 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 04.01.2026 | 09.01.2026 | Jan'26 | Jan'26 | DEVI CONST.
67 | 10/3 | DA+3 |  |  |  | Gantry - AP39/0 | COMPLETED | 05.01.2026 | 10.01.2026 | Jan'26 | Jan'26 | JWALA SINGH
68 | 32/5 | DA+1.5 |  |  |  | Gantry - AP39/0 | COMPLETED | 08.01.2026 | 14.01.2026 | Jan'26 | Jan'26 | Arawali infra-2
69 | 14/0 | DC1+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 11.01.2026 | 19.01.2026 | Jan'26 | Jan'26 | DEVI CONST.
70 | 68/0 | DB2+6 |  |  |  | AP 47/11 - AP68 | COMPLETED | 12.01.2026 | 25.01.2026 | Jan'26 | Jan'26 | Anita Devi
71 | 12/4 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 11.01.2026 | 15.01.2026 | Jan'26 | Jan'26 | JWALA SINGH
72 | 16/6 | DA(-)3 |  |  |  | Gantry - AP39/0 | COMPLETED | 15.01.2026 | 20.01.2026 | Jan'26 | Jan'26 | Arawali infra-2
73 | 12/5 | DA+1.5 |  |  |  | Gantry - AP39/0 | COMPLETED | 16.01.2026 | 19.01.2026 | Jan'26 | Jan'26 | JWALA SINGH
74 | 48/4 | DA(-)1.5 |  |  |  | AP 47/11 - AP68 | COMPLETED | 19.01.2026 | 24.01.2026 | Jan'26 | Jan'26 | DEVI CONST.
75 | 18/0 | DD45+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 25.01.2026 | 06.02.2026 | Jan'26 | Feb'26 | Senaul Haque
76 | 38/1 | DA(-)3 |  |  |  | Gantry - AP39/0 | COMPLETED | 20.01.2026 | 25.01.2026 | Jan'26 | Jan'26 | JWALA SINGH
77 | 24/8 | DA+6 |  |  |  | Gantry - AP39/0 | COMPLETED | 21.01.2026 | 27.01.2026 | Jan'26 | Jan'26 | DEVI CONST.
78 | 10/0 | DB1+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 21.01.2026 | 28.01.2026 | Jan'26 | Jan'26 | JWALA SINGH
79 | 16/5 | DA+6 |  |  |  | Gantry - AP39/0 | COMPLETED | 21.01.2026 | 27.01.2026 | Jan'26 | Jan'26 | Arawali infra-1
80 | 32/1 | DB1+9 |  |  |  | Gantry - AP39/0 | COMPLETED | 25.01.2026 | 06.02.2026 | Jan'26 | Feb'26 | Arawali infra-1
81 | 46/0 | DD45+0 |  |  |  | AP39/1 - 47/10 | COMPLETED | 27.01.2026 | 06.02.2026 | Jan'26 | Feb'26 | Amit construction
82 | 64/0 | DD45+0 |  |  |  | AP 47/11 - AP68 | COMPLETED | 27.01.2026 | 09.02.2026 | Jan'26 | Feb'26 | Anita Devi
83 | 47/11 | DA+6 |  |  |  | AP 47/11 - AP68 | COMPLETED | 25.01.2026 | 30.01.2026 | Jan'26 | Jan'26 | DEVI CONST.-2
84 | 16/3 | DA+9 |  |  |  | Gantry - AP39/0 | COMPLETED | 28.01.2026 | 03.02.2026 | Jan'26 | Feb'26 | Arawali infra-2
85 | 38/2 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 27.01.2026 | 30.01.2026 | Jan'26 | Jan'26 | JWALA SINGH
86 | 24/9 | DA(-)1.5 |  |  |  | Gantry - AP39/0 | COMPLETED | 28.01.2026 | 01.02.2026 | Jan'26 | Feb'26 | DEVI CONST.
87 | 7/0 | DC2+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 31.01.2026 | 06.02.2026 | Jan'26 | Feb'26 | JWALA SINGH
88 | 48/2 | DA(-)1.5 |  |  |  | AP 47/11 - AP68 | COMPLETED | 31.01.2026 | 06.02.2026 | Jan'26 | Feb'26 | DEVI CONST.-2
89 | 36/3 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 01.02.2026 | 05.02.2026 | Feb'26 | Feb'26 | JWALA SINGH
90 | 24/10 | DA+1.5 |  |  |  | Gantry - AP39/0 | COMPLETED | 02.02.2026 | 08.02.2026 | Feb'26 | Feb'26 | DEVI CONST.
91 | 26/2 | DA+6 |  |  |  | Gantry - AP39/0 | COMPLETED | 03.02.2026 | 13.02.2026 | Feb'26 | Feb'26 | SONI KUMARI
92 | 15/0 | DB2+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 07.02.2026 | 14.02.2026 | Feb'26 | Feb'26 | ARAVALI INFRA-2
93 | 38/0 | DD45+9 |  |  |  | Gantry - AP39/0 | COMPLETED | 07.02.2026 | 16.02.2026 | Feb'26 | Feb'26 | JWALA SINGH
94 | 11/0 | DD60+25 |  |  |  | Gantry - AP39/0 | COMPLETED | 21.02.2026 | 16.03.2026 | Feb'26 | Mar'26 | JWALA SINGH
95 | 32/7 | DA(-)1.5 |  |  |  | Gantry - AP39/0 | COMPLETED | 08.02.2026 | 14.02.2026 | Feb'26 | Feb'26 | JWALA SINGH
96 | 45/0 | DC1+0 |  |  |  | AP39/1 - 47/10 | COMPLETED | 08.02.2026 | 17.02.2026 | Feb'26 | Feb'26 | Amit construction
97 | 7/1 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 08.02.2026 | 12.02.2026 | Feb'26 | Feb'26 | JWALA SINGH
98 | 47/8 | DA+0 |  |  |  | AP39/1 - 47/10 | COMPLETED | 07.02.2026 | 12.02.2026 | Feb'26 | Feb'26 | DEVI CONST.-2
99 | 24/11 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 10.02.2026 | 13.02.2026 | Feb'26 | Feb'26 | DEVI CONST.
100 | 65/9 | DA(-)3 |  |  |  | AP 47/11 - AP68 | COMPLETED | 10.02.2026 | 16.02.2026 | Feb'26 | Feb'26 | Anita Devi
101 | 5/6 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 13.02.2026 | 17.02.2026 | Feb'26 | Feb'26 | JWALA SINGH
102 | 49/0 | DB1+0 |  |  |  | AP 47/11 - AP68 | COMPLETED | 14.02.2026 | 22.02.2026 | Feb'26 | Feb'26 | DEVI CONST.-2
103 | 26/1 | DA+1.5 |  |  |  | Gantry - AP39/0 | COMPLETED | 15.02.2026 | 25.02.2026 | Feb'26 | Feb'26 | SONI KUMARI
104 | 27/0 | DB2+9 |  |  |  | Gantry - AP39/0 | COMPLETED | 15.02.2026 | 27.02.2026 | Feb'26 | Feb'26 | DEVI CONST.
105 | 55/1 | DA+6 |  |  |  | AP 47/11 - AP68 | COMPLETED | 15.02.2026 | 25.02.2026 | Feb'26 | Feb'26 | ARAVALI INFRA-2
106 | 33/0 | DD45+9 |  |  |  | Gantry - AP39/0 | COMPLETED | 15.02.2026 | 28.02.2026 | Feb'26 | Feb'26 | ARAVALI INFRA-1
107 | 36/0 | DC2+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 17.02.2026 | 26.02.2026 | Feb'26 | Feb'26 | JWALA SINGH-2
108 | 65/11 | DA+6 |  |  |  | AP 47/11 - AP68 | COMPLETED | 17.02.2026 | 25.02.2026 | Feb'26 | Feb'26 | Anita Devi
109 | 40/0 | DC1+0 |  |  |  | AP39/1 - 47/10 | COMPLETED | 19.02.2026 | 27.02.2026 | Feb'26 | Feb'26 | Amit construction
110 | 5/4 | DA+1.5 |  |  |  | Gantry - AP39/0 | COMPLETED | 18.02.2026 | 22.02.2026 | Feb'26 | Feb'26 | JWALA SINGH
111 | 49/1 | DA+6 |  |  |  | AP 47/11 - AP68 | COMPLETED | 23.02.2026 | 28.02.2026 | Feb'26 | Feb'26 | DEVI CONST.-2
112 | 6/1 | DA(-)1.5 |  |  |  | Gantry - AP39/0 | COMPLETED | 23.02.2026 | 27.02.2026 | Feb'26 | Feb'26 | JWALA SINGH
113 | 65/8 | DA+1.5 |  |  |  | AP 47/11 - AP68 | COMPLETED | 28.02.2026 | 09.03.2026 | Feb'26 | Mar'26 | Anita Devi
114 | 52/0 | DC2+0 |  |  |  | AP 47/11 - AP68 | COMPLETED | 27.02.2026 | 12.03.2026 | Feb'26 | Mar'26 | ARAVALI INFRA-2
115 | 39/0 | DC1+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 28.02.2026 | 09.03.2026 | Feb'26 | Mar'26 | JWALA SINGH-2
116 | 39/4 | DA+0 |  |  |  | AP39/1 - 47/10 | COMPLETED | 01.03.2026 | 09.03.2026 | Mar'26 | Mar'26 | Amit construction
117 | 27/1 | DB1+9 |  |  |  | Gantry - AP39/0 | COMPLETED | 01.03.2026 | 15.03.2026 | Mar'26 | Mar'26 | DEVI CONST.
118 | 49/6 | DA+6 |  |  |  | AP 47/11 - AP68 | COMPLETED | 03.03.2026 | 10.03.2026 | Mar'26 | Mar'26 | DEVI CONST.-2
119 | 34/0 | DC1+3 |  |  | 65.8725 | Gantry - AP39/0 | COMPLETED | 19.03.2026 | 02.04.2026 | Mar'26 | Apr'26 | ARAVALI INFRA-1
120 | 63/1 | DA(-)3 |  |  |  | AP 47/11 - AP68 | COMPLETED | 12.03.2026 | 17.03.2026 | Mar'26 | Mar'26 | Anita Devi
121 | 39/3 | DA+0 |  |  |  | AP39/1 - 47/10 | COMPLETED | 10.03.2026 | 15.03.2026 | Mar'26 | Mar'26 | Amit construction
122 | 39/1 | DA+3 |  |  |  | AP39/1 - 47/10 | COMPLETED | 11.03.2026 | 16.03.2026 | Mar'26 | Mar'26 | JWALA SINGH-2
123 | 51/2 | DA(-)3 |  |  |  | AP 47/11 - AP68 | COMPLETED | 12.03.2026 | 16.03.2026 | Mar'26 | Mar'26 | DEVI CONST.-2
124 | 53/0 | DB2+3 |  |  |  | AP 47/11 - AP68 | COMPLETED | 15.03.2026 | 30.03.2026 | Mar'26 | Mar'26 | ARAVALI INFRA-2
125 | 27/3 | DA+1.5 |  |  |  | Gantry - AP39/0 | COMPLETED | 17.03.2026 | 23.03.2026 | Mar'26 | Mar'26 | DEVI CONST.
126 | 40/3 | DA+0 |  |  |  | AP39/1 - 47/10 | COMPLETED | 17.03.2026 | 21.03.2026 | Mar'26 | Mar'26 | Amit construction
127 | 51/1 | DA+0 |  |  |  | AP 47/11 - AP68 | COMPLETED | 18.03.2026 | 23.03.2026 | Mar'26 | Mar'26 | DEVI CONST.-2
128 | 39/2 | DA+0 |  |  |  | AP39/1 - 47/10 | COMPLETED | 17.03.2026 | 20.03.2026 | Mar'26 | Mar'26 | JWALA SINGH-2
129 | 12/7 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 17.03.2026 | 21.03.2026 | Mar'26 | Mar'26 | JWALA SINGH
130 | 66/5 | DA+3 |  |  |  | AP 47/11 - AP68 | COMPLETED | 20.03.2026 | 23.03.2026 | Mar'26 | Mar'26 | Anita Devi
131 | 37/0 | DD45+12 |  |  |  | Gantry - AP39/0 | COMPLETED | 22.03.2026 | 31.03.2026 | Mar'26 | Mar'26 | JWALA SINGH-2
132 | 45A/0 | DC2+0 |  |  |  | AP39/1 - 47/10 | COMPLETED | 23.03.2026 | 29.03.2026 | Mar'26 | Mar'26 | Amit construction
133 | 17/0 | DB2+3 |  |  |  | Gantry - AP39/0 | COMPLETED | 23.03.2026 | 29.03.2026 | Mar'26 | Mar'26 | JWALA SINGH
134 | 30/2 | DA+0 |  |  |  | Gantry - AP39/0 | COMPLETED | 23.03.2026 | 28.03.2026 | Mar'26 | Mar'26 | Splicenet construction
135 | 40/1 | DA+3 |  |  | 37.9311 | AP39/1 - 47/10 | COMPLETED | 24.03.2026 | 2026-04-09 | Mar'26 | Apr'26 | ARAVALI INFRA-3
136 | 27/4 | DA(-)3 |  |  | 34.7898 | Gantry - AP39/0 | COMPLETED | 25.03.2026 | 01.04.2026 | Mar'26 | Apr'26 | DEVI CONST.
137 | 66/6 | DA(-)1.5 |  |  |  | AP 47/11 - AP68 | COMPLETED | 26.03.2026 | 29.03.2026 | Mar'26 | Mar'26 | Anita Devi
138 | 48/8 | DA+0 |  |  |  | AP 47/11 - AP68 | COMPLETED | 25.03.2026 | 31.03.2026 | Mar'26 | Mar'26 | DEVI CONST.-2
139 | 29/2 | DA+1.5 |  |  | 37.1383 | Gantry - AP39/0 | COMPLETED | 25.03.2026 | 04.04.2026 | Mar'26 | Apr'26 | Splicenet construction-II
140 | 30/1 | DA+1.5 |  |  | 37.1383 | Gantry - AP39/0 | COMPLETED | 30.03.2026 | 05.04.2026 | Mar'26 | Apr'26 | Splicenet construction
141 | 13/3 | DA+0 |  |  | 36.1598 | Gantry - AP39/0 | COMPLETED | 30.03.2026 | 02.04.2026 | Mar'26 | Apr'26 | JWALA SINGH
142 | 45/3 | DA+0 |  |  | 36.1598 | AP39/1 - 47/10 | COMPLETED | 31.03.2026 | 04.04.2026 | Mar'26 | Apr'26 | Amit construction
143 | 66/4 | DA(-)3 |  |  | 34.7898 | AP 47/11 - AP68 | COMPLETED | 31.03.2026 | 04.04.2026 | Mar'26 | Apr'26 | Anita Devi
144 | 53B/1 | DA+3 |  |  | 37.9311 | AP 47/11 - AP68 | COMPLETED | 01.04.2026 | 2026-04-07 | Apr'26 | Apr'26 | ARAVALI INFRA-2
145 | 38/3 | DA(-)3 |  |  | 34.7898 | Gantry - AP39/0 | COMPLETED | 02.04.2026 | 05.04.2026 | Apr'26 | Apr'26 | JWALA SINGH-2
146 | 48/5 | DA+0 |  |  | 36.1598 | AP 47/11 - AP68 | COMPLETED | 02.04.2026 | 2026-04-07 | Apr'26 | Apr'26 | DEVI CONST.-2
147 | 27/5 | DA(-)1.5 |  |  | 35.6018 | Gantry - AP39/0 | COMPLETED | 03.04.2026 | 2026-04-09 | Apr'26 | Apr'26 | DEVI CONST.
148 | 14/5 | DA+0 |  |  | 36.1598 | Gantry - AP39/0 | COMPLETED | 03.04.2026 | 06.04.2026 | Apr'26 | Apr'26 | JWALA SINGH
149 | 32/2 | DA+1.5 |  |  | 37.1383 | Gantry - AP39/0 | COMPLETED | 03.04.2026 | 2026-04-10 | Apr'26 | Apr'26 | ARAVALI INFRA-1
150 | 29/1 | DA+1.5 |  |  | 37.1383 | Gantry - AP39/0 | COMPLETED | 06.04.2026 | 2026-04-13 | Apr'26 | Apr'26 | Splicenet construction-II
151 | 45/1 | DA(-)3 |  |  | 34.7898 | AP39/1 - 47/10 | COMPLETED | 06.04.2026 | 2026-04-09 | Apr'26 | Apr'26 | Amit construction
152 | 67/0 | DB2+6 |  |  | 69.376 | AP 47/11 - AP68 | COMPLETED | 06.04.2026 | 2026-04-15 | Apr'26 | Apr'26 | Anita Devi
153 | 30/0 | DC1+0 |  |  | 62.4437 | Gantry - AP39/0 | COMPLETED | 06.04.2026 | 2026-04-16 | Apr'26 | Apr'26 | Splicenet construction
154 | 36/4 | DA+3 |  |  | 37.9311 | Gantry - AP39/0 | COMPLETED | 06.04.2026 | 2026-04-09 | Apr'26 | Apr'26 | JWALA SINGH-2
155 | 14/4 | DA+3 |  |  | 37.9311 | Gantry - AP39/0 | COMPLETED | 2026-04-08 | 2026-04-11 | Apr'26 | Apr'26 | JWALA SINGH
156 | 52/1 | DA+1.5 |  |  | 37.1383 | AP 47/11 - AP68 | COMPLETED | 2026-04-09 | 2026-04-14 | Apr'26 | Apr'26 | ARAVALI INFRA-2
157 | 38/8 | DA+6 |  |  | 43.8044 | Gantry - AP39/0 | COMPLETED | 2026-04-08 | 2026-04-29 | Apr'26 | Apr'26 | Splicenet construction-III
158 | 27/2 | DA+0 |  |  | 36.1598 | Gantry - AP39/0 | COMPLETED | 2026-04-11 | 2026-04-14 | Apr'26 | Apr'26 | DEVI CONST.
159 | 40/2 | DA+0 |  |  | 36.1598 | AP39/1 - 47/10 | COMPLETED | 2026-04-12 | 2026-04-21 | Apr'26 | Apr'26 | ARAVALI INFRA-3
160 | 36/6 | DA(-)1.5 |  |  | 35.6018 | Gantry - AP39/0 | COMPLETED | 2026-04-10 | 2026-04-13 | Apr'26 | Apr'26 | JWALA SINGH-2
161 | 45/4 | DA+1.5 |  |  | 37.1383 | AP39/1 - 47/10 | COMPLETED | 2026-04-10 | 2026-04-15 | Apr'26 | Apr'26 | Amit construction
162 | 34/3 | DA+6 |  |  | 43.8044 | Gantry - AP39/0 | COMPLETED | 2026-04-12 | 2026-04-18 | Apr'26 | Apr'26 | ARAVALI INFRA-1
163 | 26/4 | DA(-)3 |  |  | 34.7898 | Gantry - AP39/0 | COMPLETED | 2026-04-13 | 2026-04-21 | Apr'26 | Apr'26 | Splicenet construction-II
164 | 36/5 | DA+6 |  |  | 43.8044 | Gantry - AP39/0 | COMPLETED | 2026-04-13 | 2026-04-16 | Apr'26 | Apr'26 | JWALA SINGH-2
165 | 25/0 | DC2+18 |  |  | 99.7789 | Gantry - AP39/0 | COMPLETED | 2026-04-16 | 2026-04-29 | Apr'26 | Apr'26 | Devi construction
166 | 55/2 | DA+3 |  |  | 37.9311 | AP 47/11 - AP68 | COMPLETED | 2026-04-14 | 2026-04-23 | Apr'26 | Apr'26 | Aravali infra-2
167 | 6/0 | DC2+0 |  |  | 67.2617 | Gantry - AP39/0 | COMPLETED | 2026-04-12 | 2026-04-18 | Apr'26 | Apr'26 | Jwala Singh
168 | 46/2 | DA+3 |  |  | 37.9311 | AP39/1 - 47/10 | COMPLETED | 2026-04-16 | 2026-04-22 | Apr'26 | Apr'26 | Amit construction
169 | 66/8 | DA(-)3 |  |  | 34.7898 | AP 47/11 - AP68 | COMPLETED | 2026-04-17 | 2026-04-22 | Apr'26 | Apr'26 | Anita Devi
170 | 36/7 | DA+3 |  |  | 37.9311 | Gantry - AP39/0 | COMPLETED | 2026-04-18 | 2026-04-21 | Apr'26 | Apr'26 | JWALA SINGH-2
171 | 6/2 | DA+1.5 |  |  | 37.1383 | Gantry - AP39/0 | COMPLETED | 2026-04-19 | 2026-04-22 | Apr'26 | Apr'26 | Jwala Singh
172 | 34/1 | DA+3 |  |  | 37.9311 | Gantry - AP39/0 | COMPLETED | 2026-04-19 | 2026-04-28 | Apr'26 | Apr'26 | ARAVALI INFRA-1
173 | 47/1 | DA+0 |  |  | 36.1598 | AP39/1 - 47/10 | COMPLETED | 2026-04-21 | 2026-04-26 | Apr'26 | Apr'26 | Splicenet Cons 1
174 | 26/3 | DA+6 |  |  | 43.8044 | Gantry - AP39/0 | COMPLETED | 2026-04-22 | 2026-04-30 | Apr'26 | Apr'26 | Splicenet construction-II
175 | 36/2 | DA+0 |  |  | 36.1598 | Gantry - AP39/0 | COMPLETED | 2026-04-22 | 2026-04-25 | Apr'26 | Apr'26 | JWALA SINGH-2
176 | 41/0 | DD45+0 |  | 7.3684 | 73.2445 | AP39/1 - 47/10 | COMPLETED | 2026-04-22 | 2026-05-21 | Apr'26 | May'26 | ARAVALI INFRA-3
177 | 5/2 | DA+0 |  |  | 36.1598 | Gantry - AP39/0 | COMPLETED | 2026-04-23 | 2026-04-26 | Apr'26 | Apr'26 | Jwala Singh
178 | 46A/1 | DA+3 |  |  | 37.9311 | AP39/1 - 47/10 | COMPLETED | 2026-04-23 | 2026-04-28 | Apr'26 | Apr'26 | Amit construction
179 | 65/5 | DA(-)3 |  |  | 34.7898 | AP 47/11 - AP68 | COMPLETED | 2026-04-23 | 2026-04-28 | Apr'26 | Apr'26 | Anita Devi
180 | 36/1 | DA+0 |  |  | 36.1598 | Gantry - AP39/0 | COMPLETED | 2026-04-26 | 2026-04-28 | Apr'26 | Apr'26 | JWALA SINGH-2
181 | 63/3 | DA(-)3 |  |  | 34.7898 | AP 47/11 - AP68 | COMPLETED | 2026-04-26 | 2026-04-30 | Apr'26 | Apr'26 | ARAVALI INFRA-2
182 | 5/0 | DB1+0 | W1 | 5.5784 | 55.4 | Gantry - AP39/0 | COMPLETED | 2026-04-26 | 2026-05-02 | Apr'26 | May'26 | Jwala Singh
184 | 29/0 | DD45+18 | W2 | 11.1289 | 110.626 | Gantry - AP39/0 | COMPLETED | 2026-04-30 | 2026-05-14 | Apr'26 | May'26 | Devi construction
185 | 32/0 | DD60+9 | W2 | 10.2565 | 101.9526 | Gantry - AP39/0 | COMPLETED | 2026-04-30 | 2026-05-12 | Apr'26 | May'26 | ARAVALI INFRA-1
186 | 36/8 | DA+0 | W1 | 3.6377 | 36.1598 | Gantry - AP39/0 | COMPLETED | 2026-04-29 | 2026-05-02 | Apr'26 | May'26 | JWALA SINGH-2
187 | 38/4 | DA+3 | W2 | 3.8159 | 37.9311 | Gantry - AP39/0 | COMPLETED | 2026-04-30 | 2026-05-11 | Apr'26 | May'26 | Splicenet construction-III
188 | 46A/0 | DC1+0 | W2 | 6.2819 | 62.44 | AP39/1 - 47/10 | COMPLETED | 2026-04-29 | 2026-05-08 | Apr'26 | May'26 | Amit construction
189 | 66/2 | DA(-)1.5 | W1 | 3.5816 | 35.6 | AP 47/11 - AP68 | COMPLETED | 2026-04-30 | 2026-05-06 | Apr'26 | May'26 | Anita Devi
190 | 31/0 | DD60+0 | W2 | 8.3633 | 83.13 | Gantry - AP39/0 | COMPLETED | 2026-04-30 | 2026-05-12 | Apr'26 | May'26 | Splicenet construction-II
191 | 38/6 | DA(-)3 | W1 | 3.4999 | 34.79 | Gantry - AP39/0 | COMPLETED | 2026-05-03 | 2026-05-06 | May'26 | May'26 | JWALA SINGH-2
192 | 49/4 | DA+0 | W3 | 3.6377 | 36.1598 | AP 47/11 - AP68 | COMPLETED | 2026-05-03 | 2026-05-17 | May'26 | May'26 | ARAVALI INFRA-2
193 | 21/1 | DA(-)3 | W1 | 3.4999 | 34.79 | Gantry - AP39/0 | COMPLETED | 2026-05-04 | 2026-05-07 | May'26 | May'26 | Jwala Singh
194 | 38/7 | DA+0 | W2 | 3.6377 | 36.1598 | Gantry - AP39/0 | COMPLETED | 2026-05-07 | 2026-05-11 | May'26 | May'26 | Jwala singh -2
195 | 67/2 | DA(-)3 | W2 | 3.4999 | 34.79 | AP 47/11 - AP68 | COMPLETED | 2026-05-07 | 2026-05-14 | May'26 | May'26 | Anita Devi
196 | 21/2 | DA+0 | W2 | 3.6377 | 36.1598 | Gantry - AP39/0 | COMPLETED | 2026-05-08 | 2026-05-11 | May'26 | May'26 | Jwala Singh
197 | 46A/3 | DA(-)3 | W3 | 3.4999 | 34.79 | AP39/1 - 47/10 | COMPLETED | 2026-05-09 | 2026-05-16 | May'26 | May'26 | Amit construction
198 | 24/3 | DA+6 | W3 | 4.4067 | 43.8 | Gantry - AP39/0 | COMPLETED | 2026-05-12 | 2026-05-16 | May'26 | May'26 | Jwala Singh
199 | 39/5 | DA+0 | W3 | 3.6377 | 36.1598 | AP39/1 - 47/10 | COMPLETED | 2026-05-12 | 2026-05-16 | May'26 | May'26 | Jwala singh -2
200 | 34/2 | DA(-)3 | W3 | 3.4999 | 34.79 | Gantry - AP39/0 | COMPLETED | 2026-05-15 | 2026-05-18 | May'26 | May'26 | ARAVALI INFRA-1
201 | 28/0 | DD45+6 | W4 | 8.8999 | 85.5068 | Gantry - AP39/0 | COMPLETED | 2026-05-16 | 2026-05-24 | May'26 | May'26 | Devi construction
202 | 67/1 | DA(-)3 | W3 | 3.4999 | 34.79 | AP 47/11 - AP68 | COMPLETED | 2026-05-15 | 2026-05-20 | May'26 | May'26 | Anita Devi
203 | 23/1 | DA+3 | W4 | 3.8159 | 37.9311 | Gantry - AP39/0 | COMPLETED | 2026-05-18 | 2026-05-22 | May'26 | May'26 | Jwala Singh
204 | 48/1 | DA+0 | W3 | 3.6377 | 36.1598 | AP 47/11 - AP68 | COMPLETED | 2026-05-18 | 2026-05-21 | May'26 | May'26 | Jwala singh -2
205 | 46A/2 | DA(-)3 | W4 | 3.4999 | 34.79 | AP39/1 - 47/10 | COMPLETED | 2026-05-18 | 2026-05-25 | May'26 | May'26 | Amit construction
206 | 49/2 | DA+0 | W4 | 3.6377 | 36.1598 | AP 47/11 - AP68 | COMPLETED | 2026-05-19 | 2026-05-27 | May'26 | May'26 | ARAVALI INFRA-2
207 | 48/9 | DA+3 | W4 | 3.8159 | 37.9311 | AP 47/11 - AP68 | COMPLETED | 2026-05-23 | 2026-05-26 | May'26 | May'26 | Jwala singh -2
208 | 24/2 | DA+0 | W4 | 3.6377 | 36.1598 | Gantry - AP39/0 | COMPLETED | 2026-05-22 | 2026-05-26 | May'26 | May'26 | Jwala Singh
209 | 21/0 | DC2+0 | W1 | 6.7666 | 67.2617 | Gantry - AP39/0 | COMPLETED | 2026-05-26 | 2026-06-02 | May'26 | Jun'26 | Jwala Singh
210 | 48/6 | DA+3 | W4 | 3.8159 | 37.9311 | AP 47/11 - AP68 | COMPLETED | 2026-05-27 | 2026-05-31 | May'26 | May'26 | Jwala Singh 2
211 | 41/1 | DA+6 | W1 | 6.7666 | 67.2617 | AP39/1 - 47/10 | COMPLETED | 2025-05-27 | 2026-06-07 | May'26 | Jun'26 | Amit construction
212 | 24/5 | DA(-)3 | W2 | 3.4999 | 34.79 | Gantry - AP39/0 | COMPLETED | 2026-06-03 | 2026-06-08 | Jun'26 | Jun'26 | Jwala Singh
213 | 39/10 | DA+0 | W2 | 3.6377 | 36.16 | AP39/1 - 47/10 | COMPLETED | 2026-06-03 | 2026-06-08 | Jun'26 | Jun'26 | Jwala Singh 2
214 | 24/4 | DA(-)3 | W2 | 3.4999 | 34.79 | Gantry - AP39/0 | COMPLETED | 2026-06-08 | 2026-06-13 | Jun'26 | Jun'26 | Jwala Singh
215 | 41/2 | DA(-)1.5 | W2 | 3.5816 | 35.602 | AP39/1 - 47/10 | COMPLETED | 2026-06-08 | 2026-06-13 | Jun'26 | Jun'26 | Amit construction
216 | 39/7 | DA+0 | W2 | 3.6377 | 36.16 | AP39/1 - 47/10 | COMPLETED | 2026-06-08 | 2026-06-13 | Jun'26 | Jun'26 | Jwala Singh 2
217 | 3/0 | DD45+3 | W3 | 7.4684 | 77 | Gantry - AP39/0 | COMPLETED | 2026-06-14 | 2026-06-22 | Jun'26 | Jun'26 | Jwala Singh
218 | 41/3 | DA+1.5 | W3 | 3.7361 | 37.138 | AP39/1 - 47/10 | COMPLETED | 2026-06-14 | 2026-06-20 | Jun'26 | Jun'26 | Amit construction
219 | 39/11 | DA+3 | W3 | 3.8159 | 37.931 | AP39/1 - 47/10 | COMPLETED | 2026-06-14 | 2026-06-18 | Jun'26 | Jun'26 | Jwala Singh 2
220 | 39/6 | DC2+0 | W4 | 6.7666 | 67.2617 | AP39/1 - 47/10 | Cross Arm u/p | 2026-06-19 |  | Jun'26 |  | Jwala Singh 2
221 | 41/4 | DA+3 | W4 | 3.8159 | 37.931 | AP39/1 - 47/10 | COMPLETED | 2026-06-20 | 2026-06-27 | Jun'26 | Jun'26 | Amit construction
222 | 2/0 | DD60+0 | W4 | 8.3633 | 83.1335 | Gantry - AP39/0 | Cage 2 u/p | 2026-06-23 |  | Jun'26 |  | Jwala Singh
223 | 41/5 | DA+0 |  |  |  | AP39/1 - 47/10 | Basic body u/p | 2026-06-28 |  | Jun'26 |  | Amit construction
Note on J108: Boddepalli Sagar: 33/0 Was completed in March , But it is being counted in February

## Sheet2 (hidden)
LOC No. | Type | WK | Rev |  | FDN
41/0 | #REF! | W2 | 5.496 |  | (May) Week wise | Sum of Rev
5/0 | #REF! | W1 | 16.9383 |  | W1 | 16.9383
29/0 | #REF! | W4 | 26.7456 |  | W2 | 32.2406
32/0 | #REF! | W2 | 26.7446 |  | W3 | 38.9189
36/8 | #REF! | W3 | 31.6817 |  | W4 | 63.3298
38/4 | #REF! | W4 | 19.3131 |  | Grand Total | 151.4275
46A/0 | #REF! | W4 | 17.271
66/2 | #REF! | W3 | 7.2372
31/0 | #REF!
38/6 | #REF! | [5 empty] | 292.9237
49/4 | #REF! |  |  |  | Erection
21/1 | #REF! | WK | Rev | MT | (May) Week wise | Sum of Rev
38/7 | #REF! | W3 | 7.3684 | 73.2445 | W1 | 19.7974
67/2 | #REF! | W1 | 5.5784 | 55.4 | W2 | 50.6216
21/2 | #REF! | W2 | 11.1289 | 110.626 | W3 | 33.1878
46A/3 | #REF! | W2 | 10.2565 | 101.9526 | W4 | 37.8893
24/3 | #REF! | W1 | 3.6377 | 36.1598 | Grand Total | 141.4961
39/5 | #REF! | W2 | 3.8159 | 37.9311
34/2 | #REF! | W2 | 6.2819 | 62.44
28/0 | #REF! | W1 | 3.5816 | 35.6 |  |  |  | 88.1
67/1 | #REF! | W2 | 8.3633 | 83.13 |  |  |  | 127
23/1 | #REF! | W1 | 3.4999 | 34.79
48/1 | #REF! | W3 | 3.6377 | 36.1598
46A/2 | #REF! | W1 | 3.4999 | 34.79
48/9 | #REF! | W2 | 3.6377 | 36.1598
24/2 | #REF! | W2 | 3.4999 | 34.79
|  | W2 | 3.6377 | 36.1598
|  | W3 | 3.4999 | 34.79
|  | W3 | 4.4067 | 43.8
|  | W3 | 3.6377 | 36.1598
|  | W3 | 3.4999 | 34.79
|  | W4 | 8.8999 | 85.5068
|  | W3 | 3.4999 | 34.79
|  | W4 | 3.8159 | 37.9311
|  | W3 | 3.6377 | 36.1598
|  | W4 | 3.4999 | 34.79
|  | W4 | 3.6377 | 36.1598
|  | W4 | 3.8159 | 37.9311
|  | W4 | 3.6377 | 36.1598
|  | W4 | 6.7666 | 67.2617
|  | W4 | 3.8159 | 37.9311

## XING (hidden)
Sl. No. | Location No. | Affected Towers/ Locations (Nos) | Area of concern | Name of Transmission Line/Section in between stations | Authority | Type | Proposal Submission date | Status as on date | Place of follow up | Expected date for Work Permission | Responsibility KEC | Responsibility Power Grid | Remarks
1 | Power Line Crossing
i) | 11/0-12/0 | 2 | Power Line Crossing of Power Grid | EXISTING 400 KV DC NEEMUCH-MANDSAUR TRANSMISSION LINE | Power Grid | OH | 22.05.2025 | Joint inspection Done date on- 04.06.25 | Power Grid Vadodara (RHQ), Neemuch Sub-station of Powergrid | Approved On 21.07.2025 | Devesh | Onkar singh Bharti(DGM)
ii) | 25/0-26/0 | 2 | Power Line Crossing of MPPTCL | 220 KV DC MANDSAUR - NIPANIA TL | Power Grid | OH | 22.05.2025 (Revised submission on 12.06 25) | Joint inspection Done date on- 04.06.25 | Office of Chief Enginneer, MPPTCL, Jabalpur | Approved On 18.08.2025
iii) | 28/0-29/0 | 2 |  | 220 KV DC SITAMAU-SUWASRA OHTL MPPTCL | Power Grid | OH | 22.05.2025 (Revised submission on 12.06 25, 04.07.2025) | Joint inspection Done date on- 04.06.25 |  | Approved On 18.08.2025
iv) | 33/0-34/0 | 2 |  | 132KV D/C SUWASARA - BADOD TL (Joint joint inspection Done) | Power Grid | OH | 22.05.2025 (Revised submission on 12.06 25) | Joint inspection Done date on- 04.06.25 |  | Approved On 18.08.2025
v) | 37/0-38/0 | 2 |  | 220 KV OHTL DC BHANPUR-BAROD MPPTCL | Power Grid | OH | 22.05.2025 (Revised submission on 12.06 25) | Joint inspection Done date on- 04.06.25 |  | Approved On 18.08.2025
vi) | 54/0-55/0 | 2 |  | 220kV D/C Badod-Nalkheda T/Line | Power Grid | OH | Submission on 18.09.2025 | pending due to finalization of survey for avoiding forest in between section 52/0 - 58/0 | - | - | - | -
vii) | 62/0-63/0 | 2 |  | 132 KV DC CKT-1 AGAR -SUSNER , CKT-2 AGAR - NALKHEDA OHTL | Power Grid | OH | 22.05.2025 (Revised submission on 12.06 25) | Joint inspection Pending | - | - | - | -
viii) | 42/0-43/0 | 2 | Power Line Crossing of RVPNL | 132 KV SC BHAWANI MANDI - DAG T/L (RRVPNL) | Power Grid | OH | 22.05.2025 | Approved on 04.07.2025 | Office of Chief Enginneer, RVPNL, Jaipur | Approved on 04.07.2025 | Devesh | Onkar singh Bharti(DGM)
ix) | 50/0-51/0 | 2 | Power Line Crossing of RTL | 220 KV S/C SUSNER - PACHORA T/L | Power Grid | OH | 22.05.2025 (Revised submission on 12.06 25) | Joint inspection Pending | Office of Chief Enginneer, RTL, Bhopal |  | Devesh | Onkar singh Bharti(DGM)
2 | NH - Crossing
i) | 17/0-18/0 | 2 | NHAI | NE-4 DELHI MUMBAI EXPRESSWAY | Power Grid | OH | 02.06.2025 | Joint inspection Pending | Power Grid Suwasra/Mandsaur | Approved on 07.11.2027 | Devesh | Onkar singh Bharti(DGM)
ii) | 35/0-36/0 | 2 | NHAI | NATIONAL HIGHWAY-752D | Power Grid | OH | 02.06.2025 | joint inspection Done on 22-07-2025 | Power Grid Suwasra/Mandsaur | - | Devesh | Onkar singh Bharti(DGM)
iii) | 60/0-61/0 | 2 | NHAI | NATIONAL HIGHWAY-552G | Power Grid | OH | 02.06.2025 | Joint inspection Pending | Power Grid Suwasra/Mandsaur | - | Devesh | Onkar singh Bharti(DGM)
3 | Railway Crossing
i) | 31/0-32/0 | 2 | Indian Railway Kota Division | Between Suwasra & Nathukheri Railway station BG | Power Grid | OH | 17.06.2025(Revised submission on 30.06 25) | Joint inspection Done date on- 27.06.2025 revised inspection date pending | Power Grid Suwasra/Mandsaur | Approved on 10.12.2025 | Devesh | Onkar singh Bharti(DGM)
| Total | 26

## EARTHING (hidden)
EARTHING
SL NO. | LOC NO. | TYPE OF TOWER | TODAY'S PLAN | TODAY'S PROGRESS | TOMMOROW'S PLAN | START DATE | COMPLETION DATE | GANG
1 | 8/1 | DA+0 | COMPLETED |  |  | 13.05.2025 | 13.05.2025 | JSC CONST.
2 | 8/2 | DA+3 | COMPLETED |  |  | 13.05.2025 | 13.05.2025 | JSC CONST.
3 | 8/3 | DA+3 | COMPLETED |  |  | 13.05.2025 | 13.05.2025 | JSC CONST.
4 | 20/1 | DA(-)3 | COMPLETED |  |  | 13.05.2025 | 13.05.2025 | YATHATHART
5 | 20/2 | DA(-)3 | COMPLETED |  |  | 13.05.2025 | 13.05.2025 | YATHATHART
6 | 5/3 | DA+3 | COMPLETED |  |  | 14.05.2025 | 14.05.2025 | GM CONST.
7 | 5/4 | DA+1.5 | COMPLETED |  |  | 14.05.2025 | 14.05.2025 | GM CONST.
8 | 6/1 | DA(-)1.5 | COMPLETED |  |  | 16.05.2025 | 16.05.2025
9 | 38/1 | DA(-)3 | COMPLETED |  |  | 17.05.2025 | 17.05.2025
10 | 38/3 | DA(-)3 | COMPLETED |  |  | 17.05.2025 | 17.05.2025
11 | 16/3 | DA+9 | COMPLETED |  |  | 19.05.2025 | 19.05.2025
12 | 16/6 | DA(-)3 | COMPLETED |  |  | 19.05.2025 | 19.05.2025
13 | 16/7 | DA+0 | COMPLETED |  |  | 19.05.2025 | 19.05.2025
14 | 16/8 | DA(-)3 | COMPLETED |  |  | 19.05.2025 | 19.05.2025
15 | 16/9 | DA+0 | COMPLETED |  |  | 19.05.2025 | 19.05.2025
16 | 66/8 | DA(-)3 | COMPLETED |  |  | 13.06.2025 | 13.06.2025
17 | 49/6 | DA+6 | COMPLETED |  |  | 17.06.2025 | 17.06.2025 | YATHATHART
18 | 49/0 | DB1+0 | COMPLETED |  |  | 17.06.2025 | 17.06.2025 | GM CONST.
19 | 66/5 | DA+3 | COMPLETED |  |  | 2025-06-19 | 2025-06-19 | SREE SAI BRICKS
20 | 65/1 | DA(-)1.5 | COMPLETED |  |  | 20.06.2025 | 20.06.2025
21 | 65/2 | DA+0 | COMPLETED |  |  | 30.06.2025 | 30.06.2025
22 | 65/9 | DA(-)3 | COMPLETED |  |  | 10.07.2025 | 10.07.2025
23 | 63/1 | DA(-)3 | COMPLETED |  |  | 15.07.2025 | 15.07.2025
24 | 65/7 | DA(-)3 | COMPLETED |  |  | 17.07.2025 | 17.07.2025
25 | 21/0 | DC2+0 | COMPLETED |  |  | 13/08/2025 | 13/08/2025 | Shakhina Bibi
26 | 46/0 | DD45+0 | COMPLETED |  |  | 16/08/2025 | 16/08/2025
27 | 15/0 | DB2+0 | COMPLETED |  |  | 20.08.2025 | 20.08.2025
28 | 5/1 | DA(-)3 | COMPLETED
29 | 5/2 | DA+0 | COMPLETED
30 | 7/1 | DA+0 | COMPLETED
31 | 7/2 | DA+0 | COMPLETED
32 | 7/3 | DA+0 | COMPLETED
33 | 7/4 | DA+0 | COMPLETED
34 | 8/4 | DA+3 | COMPLETED
35 | 8/5 | DA+0 | COMPLETED
36 | 8/6 | DA+0 | COMPLETED
37 | 8/7 | DA+0 | COMPLETED
38 | 8/8 | DA+3 | COMPLETED
39 | 9/2 | DA+0 | COMPLETED
40 | 12/1 | DA+3 | COMPLETED
41 | 12/2 | DA(-)3 | COMPLETED
42 | 12/3 | DA(-)3 | COMPLETED
43 | 13/0 | DB2+0 | COMPLETED
44 | 13/1 | DA(-)1.5 | COMPLETED
45 | 13/2 | DA+0 | COMPLETED
46 | 15/2 | DA+3 | COMPLETED
47 | 15/3 | DA+0 | COMPLETED
48 | 15/4 | DA+6 | COMPLETED
49 | 15/5 | DA(-)3 | COMPLETED
50 | 15/7 | DA+0 | COMPLETED
51 | 15/8 | DA+0 | COMPLETED
52 | 15/9 | DA+3 | COMPLETED
53 | 16/1 | DA+0 | COMPLETED
54 | 16/2 | DA+0 | COMPLETED
55 | 16/5 | DA+6 | COMPLETED
56 | 16/10 | DA+6 | COMPLETED
57 | 16/11 | DA+0 | COMPLETED
58 | 24/1 | DA+0 | COMPLETED
59 | 24/2 | DA+0 | COMPLETED
60 | 24/3 | DA+6 | COMPLETED
61 | 24/4 | DA(-)3 | COMPLETED
62 | 24/5 | DA(-)3 | COMPLETED
63 | 24/6 | DA+3 | COMPLETED
64 | 24/8 | DA+6 | COMPLETED
65 | 24/9 | DA(-)1.5 | COMPLETED
66 | 24/10 | DA+1.5 | COMPLETED
67 | 24/11 | DA+0 | COMPLETED
68 | 26/1 | DA+1.5 | COMPLETED
69 | 26/2 | DA+6 | COMPLETED
70 | 26/3 | DA+6 | COMPLETED
71 | 26/4 | DA(-)3 | COMPLETED
72 | 27/2 | DA+0 | COMPLETED
73 | 27/3 | DA+1.5 | COMPLETED
74 | 27/4 | DA(-)3 | COMPLETED
75 | 27/5 | DA(-)1.5 | COMPLETED
76 | 29/2 | DA+1.5 | COMPLETED
77 | 30/1 | DA+1.5 | COMPLETED
78 | 32/2 | DA+1.5 | COMPLETED
79 | 32/3 | DA+1.5 | COMPLETED
80 | 32/4 | DA+0 | COMPLETED
81 | 32/5 | DA+1.5 | COMPLETED
82 | 32/6 | DA+0 | COMPLETED
83 | 32/7 | DA(-)1.5 | COMPLETED
84 | 34/1 | DA+3 | COMPLETED
85 | 34/3 | DA+6 | COMPLETED
86 | 36/1 | DA+0 | COMPLETED
87 | 36/2 | DA+0 | COMPLETED
88 | 36/5 | DA+6 | COMPLETED
89 | 36/6 | DA(-)1.5 | COMPLETED
90 | 36/7 | DA+3 | COMPLETED
91 | 36/8 | DA+0 | COMPLETED
92 | 38/2 | DA+0 | COMPLETED
93 | 38/4 | DA+0 | COMPLETED
94 | 38/6 | DA(-)3 | COMPLETED
95 | 38/7 | DA+0 | COMPLETED
96 | 38/8 | DA+6 | COMPLETED
97 | 39/1 | DA+3 | COMPLETED
98 | 39/3 | DA+0 | COMPLETED
99 | 39/4 | DA+0 | COMPLETED
100 | 39/5 | DA+0 | COMPLETED
101 | 39/7 | DA+0 | COMPLETED
102 | 39/8 | DA+3 | COMPLETED
103 | 40/1 | DA+3 | COMPLETED
104 | 40/2 | DA+0 | COMPLETED
105 | 40/3 | DA+0 | COMPLETED
106 | 41/1 | DA+6 | COMPLETED
107 | 41/4 | DA+3 | COMPLETED
108 | 41/2 | DA(-)1.5 | COMPLETED
109 | 41/5 | DA+0 | COMPLETED
110 | 41/8 | DA+3 | COMPLETED
111 | 44/2 | DA+3 | COMPLETED
112 | 44/3 | DA+0 | COMPLETED
113 | 47/6 | DA+3 | COMPLETED
114 | 47/4 | DA+3 | COMPLETED
115 | 47/7 | DA+0 | COMPLETED
116 | 47/8 | DA+0 | COMPLETED
117 | 47/11 | DA+6 | COMPLETED
118 | 48/2 | DA(-)1.5 | COMPLETED
119 | 48/6 | DA+3 | COMPLETED
120 | 48/8 | DA+0 | COMPLETED
121 | 48/9 | DA+3 | COMPLETED
122 | 49/1 | DA+6 | COMPLETED
123 | 49/2 | DA+0 | COMPLETED
124 | 49/3 | DA+3 | COMPLETED
125 | 51/1 | DA+0 | COMPLETED
126 | 51/2 | DA(-)3 | COMPLETED
127 | 51/3 | DA(-)3 | COMPLETED
128 | 63/2 | DA(-)3 | COMPLETED
129 | 65/3 | DA+6 | COMPLETED
130 | 65/11 | DA+6 | COMPLETED
131 | 67/1 | DA(-)3 | COMPLETED
132 | 45/1 | DA(-)3 | COMPLETED
133 | 45/3 | DA+0 | COMPLETED
134 | 33/0 | DD45+9 | COMPLETED
135 | 12/7 | DA+0 | COMPLETED
136 | 10/3 | DA+3 | COMPLETED
137 | 34/0 | DC1+3 | COMPLETED
138 | 7/0 | DC2+0 | COMPLETED
139 | 8/9 | DA(-)3 | COMPLETED
140 | 46/2 | DA(-)3 | COMPLETED
141 | 8/0 | DB1+0 | COMPLETED
142 | 14/5 | DA+0 | COMPLETED
143 | 46A/1 | DA+3 | COMPLETED
144 | 10/0 | DB1+0 | COMPLETED
145 | 46A/0 | DC1+0 | COMPLETED
146 | 64/0 | DD45+0 | COMPLETED
147 | 21/3 | 'DA+0 | COMPLETED
148 | 21/4 | 'DA+3 | COMPLETED
149 | 9/0 | 'DB2+0 | COMPLETED
150 | 9/1 | 'DA+3 | COMPLETED
151 | 10/1 | 'DA+0 | COMPLETED
152 | 10/2 | DA(-)3 | COMPLETED
153 | 45/4 | DA+1.5 | COMPLETED
154 | 46A/3 | DA(-)3 | COMPLETED
155 | 17/0 | DB2+3 | COMPLETED
156 | 9/3 | DA+6 | COMPLETED
157 | 16/4 | DA+0 | COMPLETED
158 | 46A/2 | DA+0 | COMPLETED
159 | 66/0 | DB1+0 | COMPLETED
160 | 16/0 | DB1+0 | COMPLETED
161 | 63/3 | DA(-)3 | COMPLETED
162 | 64/1 | DA+6 | COMPLETED
163 | 47/1 | DA+0 | COMPLETED
164 | 47/3 | DA+0 | COMPLETED
165 | 65/8 | DA+1.5 | COMPLETED
166 | 18/0 | DD45+0 | COMPLETED
167 | 66/3 | DA+6 | COMPLETED
168 | 45/0 | DC1+0 | COMPLETED
169 | 65/5 | DA(-)3 | COMPLETED
170 | 66/4 | DA(-)3 | COMPLETED
171 | 6/0 | DC2+0 | COMPLETED
172 | 23/0 | DD45+3 | COMPLETED
173 | 65/0 | DC2+0 | COMPLETED
174 | 52/1 | DA+1.5 | COMPLETED
175 | 67/0 | DB2+6 | COMPLETED
176 | 40/0 | DC1+0 | COMPLETED
177 | 53/0 | DB2+3 | COMPLETED
178 | 55/1 | DA+6 | COMPLETED
179 | 56/2 | DB1+6 | COMPLETED
180 | 25/0 | DC2+18 | COMPLETED
181 | 27/0 | DB2+9 | COMPLETED
182 | 14/0 | DC1+0 | COMPLETED
183 | 32/1 | DB1+9 | COMPLETED
184 | 11/0 | DD60+25 | COMPLETED
185 | 29/0 | DD45+18 | COMPLETED
186 | 48/4 | DA(-)1.5 | COMPLETED
187 | 39/0 | DC1+0 | COMPLETED
188 | 53B/1 | DA+3 | COMPLETED
189 | 30/2 | DA+0 | COMPLETED
190 | 48/3 | DA+3 | COMPLETED
191 | 38/0 | DD45+9 | COMPLETED
192 | 6/3 | DA+1.5 | COMPLETED
193 | 6/2 | DA+1.5 | COMPLETED
194 | 18/1 | DA+6 | COMPLETED
195 | 36/0 | DC2+0 | COMPLETED
196 | 30/0 | DC1+0 | COMPLETED
199 | 52/0 | DC2+0 | COMPLETED
200 | 48/1 | DA+1 | COMPLETED
201 | 48/5 | DA+0 | COMPLETED
202 | 37/0 | DD45+12 | COMPLETED
203 | 31/0 | DD60+0 | COMPLETED
204 | 32/0 | DC2+0 | COMPLETED
205 | 53A/0 | DB1(-)1.5 | COMPLETED
206 | 39/6 | DC2+0 | COMPLETED
207 | 5/5 | DA+0 | COMPLETED
208 | 41/7 | DA+6 | COMPLETED
209 | 28/0 | DD45+6 | COMPLETED
210 | 48/0 | DB1+0 | COMPLETED
211 | 14/1 | DA+0 | COMPLETED
212 | 13/4 | DA(-)3 | COMPLETED
213 | 14/2 | DA+0 | COMPLETED
214 | 14/3 | DA(-)3 | COMPLETED
215 | 35/0 | DB2+3 | COMPLETED
216 | 13/3 | DA+0 | COMPLETED
217 | 13/5 | DA+0 | COMPLETED
218 | 41/3 | DA+1.5 | COMPLETED
219 | 8/10 | DA+0 | COMPLETED
220 | 12/4 | DA+0 | COMPLETED
221 | 12/5 | DA+1.5 | COMPLETED
222 | 12/6 | DA+0 | COMPLETED
223 | 24/7 | DA+0 | COMPLETED
224 | 26/0 | DC2+12 | COMPLETED
225 | 27/1 | DB1+9 | COMPLETED
226 | 29/1 | DA+1.5 | COMPLETED
227 | 4/4 | DA+6 | COMPLETED
228 | 39/9 | DA+3 | COMPLETED
229 | 3/1 | DA(-)1.5 | COMPLETED
230 | 4/3 | DA(-)3 | COMPLETED
231 | 45/2 | DA+0 | COMPLETED |  |  |  | 2026-05-05
232 | 50/0 | DC2+18 | COMPLETED
233 | 4/0 | DC1+0 | COMPLETED
234 | 47/10 | DA+3 | COMPLETED

## SUPPLY (hidden)
Line Name: | 765KV D/C Mandsaur- Kurawar Transmission Line
Package: | TA-509
Agency: | M/s KEC International Limited
Status as on: | 2026-03-26
Supply Status
S. No. | Item Name | Supplier Name | Anticipated Qty | UPTO Dec-25 L2 Schedule | Supplied Qty | Supply In progress | Balance supply | Remarks
1 | Stub | KEC Int'l Ltd. | 312 | 306 | 281 |  | 31
2 | Tower | KEC Int'l Ltd. | 312 | 306 | 297 |  | 15
3 | Conductor | Sterlite | 4343 | 3900 | 4300.418 |  | 42.582 | Conductor Qty in KM
4 | H/W fittings | Mosdorfer | 2432 | 95% | 2310.4 |  | 121.6 | H/W Fitting Qty in Sets
5 | Insulator | Aditya Birla | 13552 | 11388 | 12832 |  | 720 | Insulator Qty in Nos | 160KN=5536 | 210KN=7296
6 | E/W | GK Wires | 121 | 85% | 84 |  | 37 | E/W Qty in KM.
7 | OPGW | Nirmal Wire Pvt. Ltd. | 126 | 63 | 0 |  | 126 | OPGW Qty in KM. |  | 5566 | 7296

## CST Gantry To AP 68 Common Poin (hidden)
CLIENT :- POWER GRID CORPORATION OF INDIA LIMITED
NAME OF PROJECT :- 765 KV D/C Mandsaur - Kurawar (Part 1) Transmission Line
M/s. KEC INTERNATIONAL LIMITED
TOWER SCHEDULE SECTION:- GANTRY TO AP 68 LENGTH:- 118.386 KM
KEC/TA509/MKTL/CS/AS ON Dt-06.03.2026
Sl.No | AP NO. | TOWER NO. | TYPE OF TOWER | DEVIATION ANGLE (Deg) | SPAN (Mtr) | Section Length (m) | CUMULATIVE SPAN | R.L (Mtr) | HT of Tower (Mtr) | Sum of Adjacent Spans | WIND SPAN (Mtr) | WEIGHT SPAN IN Mtr (Cold) |  |  | WEIGHT SPAN IN Mtr (Hot) |  |  | Spherical Coordinate |  | UTM Coordinates |  | CROSSING DETAILS | NAME OF VILLAGE | NAME OF TEHSIL | NAME OF STATAT | LEG EXTENSION
[12 empty] | Left | Right | Total | Left | Right | Total | Longitude (Easting) | Latitude (Northing) | Easting | Northing |  |  |  |  | A | B | C | D
0 |  | Mandsur Gantry | Gantry |  |  |  | 0 | 435.03 | 46.3 | 107.961 | 53.9805 | 0 | 6 | 6 | 0 | 11 | 11 | 75°10'24.829"E | 24°12'17.524"N | 517625.299 | 2676919.49
[5 empty] | 107.961 | [16 empty] | BOUNDARY WALL
1 | AP1/0 | 1/0 | DD60+0 | 7° 41' 29"LT |  | 107.961 | 107.961 | 434.455 | 70.72 | 256.439 | 128.2195 | 33 | 141 | 174 | 35 | 95 | 130 | 75°10'21.828"E | 24°12'15.345"N | 517540.723 | 2676852.389 | Tower cast at 0deg w.r.t. Gantry | Talabpipalya | Malhargarh | MP
148.478
2 | AP2/0 | 2/0 | DD60+0 | 58° 40' 0"LT |  | 148.478 | 256.439 | 431.101 | 70.72 | 557.31 | 278.655 | 7 | 220 | 227 | 53 | 215 | 268 | 75°10'18.175"E | 24°12'11.87"N | 517437.804 | 2676745.368 |  | Talabpipalya | Malhargarh | MP
[5 empty] | 408.832 | [16 empty] | NALA/LT LINE
3 | AP3/0 | 3/0 | DD45+3 | 42° 45' 44"LT |  | 408.832 | 665.271 | 425.18 | 73.72 | 788.832 | 394.416 | 190 | 213 | 403 | 194 | 206 | 400 | 75°10'21.856"E | 24°11'59.012"N | 517542.143 | 2676350.074 |  | Talabpipalya | Malhargarh | MP
[5 empty] | 380 | [16 empty] | ROAD/WELL
4 |  | 3/1 | DA(-)1.5 |  |  |  | 1045.271 | 425.63 | 71 | 802 | 401 | 167 | 198 | 365 | 175 | 202 | 377 | 75°10'33.214"E | 24°11'52.369"N | 517862.804 | 2676146.17 |  | Talabpipalya | Malhargarh | MP
[5 empty] | 422 | [16 empty] | LT/CT, WELL/NALA
5 |  | 3/2 | DA+6 |  |  |  | 1467.271 | 420.86 | 78.5 | 830.352 | 415.176 | 225 | 237 | 462 | 221 | 228 | 449 | 75°10'45.827"E | 24°11'44.992"N | 518218.906 | 2675919.73 |  | Talabpipalya | Malhargarh | MP
[5 empty] | 408.352 | [16 empty] | LT LINE, LT T POINT, WELL, CT, NALA/11KV LINE/ LT/CT/ WELL/ SAMADHI
6 | AP4/0 | 4/0 | DC1+0 | 19° 8' 15"LT |  | 1210.352 | 1875.623 | 420.532 | 70.72 | 827.805 | 413.9025 | 171 | 124 | 295 | 182 | 149 | 331 | 75°10'58.032"E | 24°11'37.853"N | 518563.491 | 2675700.613 |  | Kachariya | Malhargarh | MP
[5 empty] | 419.453 | [16 empty] | NALA, POND, WELL
7 |  | 4/1 | DA+9 |  |  |  | 2295.076 | 429.129 | 81.5 | 800.453 | 400.2265 | 297 | 175 | 472 | 272 | 179 | 451 | 75°11'12.496"E | 24°11'34.694"N | 518971.67 | 2675604.017 | Benching / Raised Chimney Expected | Kachariya | Malhargarh | MP | 1.5 |  |  | 0.5
[5 empty] | 381 | [16 empty] | CT
8 |  | 4/2 | DA+9 |  |  |  | 2676.076 | 432.129 | 81.5 | 798.002 | 399.001 | 207 | 312 | 519 | 203 | 282 | 485 | 75°11'25.634"E | 24°11'31.825"N | 519342.43 | 2675516.275 | Benching / Raised Chimney Expected | Kachariya | Malhargarh | MP | 1.5 | 2
417.002
9 |  | 4/3 | DA(-)3 |  |  |  | 3093.078 | 423.427 | 69.5 | 834.004 | 417.002 | 107 | 196 | 303 | 136 | 200 | 336 | 75°11'40.014"E | 24°11'28.684"N | 519748.223 | 2675420.243 |  | Sohangara | Malhargarh | MP
[5 empty] | 417.002 | [16 empty] | METAL ROAD, CT, 11KV, LT
10 |  | 4/4 | DA+6 |  |  |  | 3510.08 | 416.978 | 78.5 | 834.004 | 417.002 | 221 | 270 | 491 | 218 | 253 | 471 | 75°11'54.393"E | 24°11'25.543"N | 520154.016 | 2675324.211 |  | Sohangara | Malhargarh | MP
[5 empty] | 417.002 | [16 empty] | WELL, LT
11 |  | 4/5 | DA(-)3 |  |  |  | 3927.082 | 413.573 | 69.5 | 805.005 | 402.5025 | 148 | 163 | 311 | 166 | 172 | 338 | 75°12'8.772"E | 24°11'22.402"N | 520559.81 | 2675228.179 |  | Sohangara | Malhargarh | MP
[5 empty] | 388.003 | [16 empty] | CT
12 |  | 4/6 | DA+6 |  |  |  | 4315.085 | 410.487 | 78.5 | 840.346 | 420.173 | 226 | 248 | 474 | 217 | 242 | 459 | 75°12'22.151"E | 24°11'19.479"N | 520937.383 | 2675138.826 |  | Sohangara | Malhargarh | MP
[5 empty] | 452.343 | [16 empty] | 11 KV LINE/SHIVNA RIVER/CART TRACK
13 | AP5/0 | 5/0 | DB1+0 | 0° 56' 36"LT |  | 2891.805 | 4767.428 | 411.761 | 70.72 | 853.343 | 426.6715 | 205 | 239 | 444 | 212 | 227 | 439 | 75°12'37.748"E | 24°11'16.07"N | 521377.568 | 2675034.655 |  | Aabakhedi | Sitamau | MP
[5 empty] | 401 | [16 empty] | NALA, PIPAL TREE
14 |  | 5/1 | DA(-)3 |  |  |  | 5168.428 | 407.682 | 69.5 | 731 | 365.5 | 162 | 118 | 280 | 175 | 134 | 309 | 75°12'51.627"E | 24°11'13.257"N | 521769.257 | 2674948.744 |  | Aabakhedi | Sitamau | MP
[5 empty] | 330 | [16 empty] | LT LINE, HUT, CART TRACK
15 |  | 5/2 | DA+0 |  |  |  | 5498.428 | 411.854 | 72.5 | 743 | 371.5 | 212 | 194 | 406 | 197 | 199 | 396 | 75°13'3.049"E | 24°11'10.942"N | 522091.595 | 2674878.045 |  | Nahargarh | Sitamau | MP
[5 empty] | 413 | [16 empty] | LT LINE, 11KV LINE, CART TRACK, WELL, LT T POINT
16 |  | 5/3 | DA+3 |  |  |  | 5911.428 | 411.285 | 75.5 | 835 | 417.5 | 220 | 223 | 443 | 216 | 219 | 435 | 75°13'17.343"E | 24°11'8.045"N | 522495.005 | 2674789.563 |  | Nahargarh | Sitamau | MP
[5 empty] | 422 | [16 empty] | GUAVA GARDEN, CART TRACK, WELL, ORANGE GARDEN
17 |  | 5/4 | DA+1.5 |  |  |  | 6333.428 | 410.546 | 74 | 818 | 409 | 200 | 210 | 410 | 204 | 206 | 410 | 75°13'31.948"E | 24°11'5.084"N | 522907.207 | 2674699.153 |  | Nahargarh | Sitamau | MP
[5 empty] | 396 | [16 empty] | GUAVA GARDEN, CART TRACK, ORANGE GARDEN
18 |  | 5/5 | DA+0 |  |  |  | 6729.428 | 409.91 | 72.5 | 781 | 390.5 | 186 | 194 | 380 | 190 | 194 | 384 | 75°13'45.65"E | 24°11'2.29"N | 523294.01 | 2674614.31 |  | Nahargarh | Sitamau | MP
[5 empty] | 385 | [16 empty] | 11KV LINE, CART TRACK, WELL, 11KV T POINT
19 |  | 5/6 | DA+0 |  |  |  | 7114.428 | 409.514 | 72.5 | 723 | 361.5 | 191 | 188 | 379 | 191 | 182 | 373 | 75°13'58.978"E | 24°10'59.603"N | 523670.073 | 2674531.831 |  | Nahargarh | Sitamau | MP
[5 empty] | 338 | [16 empty] | LT LINE, SAMADHI, WELL, CART TRACK
20 |  | 5/7 | DA(-)3 |  |  |  | 7452.428 | 409.625 | 69.5 | 662 | 331 | 151 | 146 | 297 | 157 | 152 | 309 | 75°14'10.676"E | 24°10'57.23"N | 524000.224 | 2674459.418 |  | Nahargarh | Sitamau | MP
[5 empty] | 324 | [16 empty] | NALA, METAL ROAD, WELL, CART TRACK
21 | AP6/0 | 6/0 | DC2+0 | 28° 53' 29"RT |  | 3009 | 7776.428 | 408.99 | 70.72 | 704 | 352 | 178 | 203 | 381 | 173 | 199 | 372 | 75°14'21.884"E | 24°10'54.956"N | 524316.58 | 2674390.03 |  | Nahargarh | Sitamau | MP
[5 empty] | 380 | [16 empty] | CART TRACK
22 |  | 6/1 | DA(-)1.5 |  |  |  | 8156.428 | 408.326 | 71 | 754 | 377 | 178 | 161 | 339 | 182 | 169 | 351 | 75°14'31.994"E | 24°10'46.792"N | 524602.224 | 2674139.416 |  | Nahargarh | Sitamau | MP
[5 empty] | 374 | [16 empty] | CART TRACK, ORANGE GARDEN, 33 KV LINE, WELL, LT LINE, LT T POINT, 11KVTF, 11 KV LINE (TO BE DIVERTED)
23 |  | 6/2 | DA+1.5 |  |  |  | 8530.428 | 409.895 | 74 | 789 | 394.5 | 213 | 196 | 409 | 205 | 200 | 405 | 75°14'41.93"E | 24°10'38.73"N | 524883.36 | 2673892.76 |  | Nahargarh | Sitamau | MP
[5 empty] | 415 | [16 empty] | 11 KV LINE , 11KV T POINT
24 |  | 6/3 | DA+1.5 |  |  |  | 8945.428 | 412.132 | 74 | 801 | 400.5 | 219 | 192 | 411 | 215 | 192 | 407 | 75°14'52.982"E | 24°10'29.838"N | 525195.313 | 2673619.063 |  | Nahargarh | Sitamau | MP
[5 empty] | 386 | [16 empty] | METAL ROAD, LT LINE, CART TRACK, 11 KV LINE
25 | AP7/0 | 7/0 | DC2+0 | 22° 44' 15"LT |  | 1555 | 9331.428 | 413.89 | 70.72 | 738 | 369 |  | 178 | 178 |  | 179 | 179 | 75°15'3.249"E | 24°10'21.544"N | 525485.462 | 2673364.497 |  | Khajuri_chandrawat | Sitamau | MP
[5 empty] | 352 | [16 empty] | LT line & Cart track
26 |  | 7/1 | DA+0 |  |  |  | 9683.428 | 413.39 | 72.5 | 744 | 372 | 174 | 200 | 374 | 173 | 202 | 375 | 75° 15' 15.02"E | 24° 10' 17.75"N | 525817.81 | 2673248.52 |  | Khajuri_chandrawat | Sitamau | MP
[5 empty] | 392 | [16 empty] | 11kV line & Cart track
27 |  | 7/2 | DA+0 |  |  |  | 10075.428 | 412.24 | 72.5 | 773 | 386.5 | 192 | 195 | 387 | 190 | 198 | 388 | 75° 15' 28.13"E | 24° 10' 13.53"N | 526187.92 | 2673119.37 |  | Khajuri_chandrawat | Sitamau | MP
[5 empty] | 381 | [16 empty] | Cart track
28 |  | 7/3 | DA+0 |  |  |  | 10456.428 | 410.96 | 72.5 | 771 | 385.5 | 186 | 190 | 376 | 183 | 187 | 370 | 75° 15' 40.87"E | 24° 10' 9.43"N | 526547.65 | 2672993.84 |  | Khajuri_chandrawat | Sitamau | MP
[5 empty] | 390 | [16 empty] | LT line, Cart track & Nala
29 |  | 7/4 | DA+0 |  |  |  | 10846.428 | 412.34 | 72.5 | 781 | 390.5 | 200 | 188 | 388 | 203 | 185 | 388 | 75° 15' 53.91"E | 24° 10' 5.23"N | 526915.87 | 2672865.34 |  | Khajuri_chandrawat | Sitamau | MP
[5 empty] | 391 | [16 empty] | 11kV line, LT line & Cart track
30 | AP8/0 | 8/0 | DB1+0 | 2° 0' 34"RT |  | 1906 | 11237.428 | 414.33 | 70.72 | 722 | 361 | 203 | 155 | 358 | 206 | 150 | 356 | 75° 16' 6.98"E | 24° 10' 1.02"N | 527284.94 | 2672736.55 |  | Khajuri_chandrawat | Sitamau | MP
[5 empty] | 331 | [16 empty] | Cart track & Nala
31 |  | 8/1 | DA+0 |  |  |  | 11568.428 | 416.74 | 72.5 | 735 | 367.5 | 176 | 177 | 353 | 181 | 165 | 346 | 75° 16' 17.91"E | 24° 9' 57.1"N | 527593.44 | 2672616.6 |  | Khajuri_chandrawat | Sitamau | MP
[5 empty] | 404 | [16 empty] | LT line & Cart track
32 |  | 8/2 | DA+3 |  |  |  | 11972.428 | 420.745 | 75.5 | 814 | 407 | 227 | 195 | 422 | 239 | 190 | 429 | 75° 16' 31.24"E | 24° 9' 52.31"N | 527969.98 | 2672470.2 |  | Khajuri_chandrawat | Sitamau | MP
[5 empty] | 410 | [16 empty] | 11kV line, LT line & Cart track
33 |  | 8/3 | DA+3 |  |  |  | 12382.428 | 423.53 | 75.5 | 808 | 404 | 215 | 203 | 418 | 220 | 205 | 425 | 75° 16' 44.77"E | 24° 9' 47.46"N | 528352.12 | 2672321.62 |  | Khajuri_chandrawat | Sitamau | MP
[5 empty] | 398 | [16 empty] | LT line & Cart track
34 |  | 8/4 | DA+3 |  |  |  | 12780.428 | 422.4 | 75.5 | 830 | 415 | 195 | 242 | 437 | 193 | 254 | 447 | 75° 16' 57.91"E | 24° 9' 42.74"N | 528723.06 | 2672177.4 |  | Khajuri_chandrawat | Sitamau | MP
[5 empty] | 432 | [16 empty] | 33kV line, 11kV line, Metal road, Cart track & nala
35 |  | 8/5 | DA+0 |  |  |  | 13212.428 | 417.72 | 72.5 | 788 | 394 | 190 | 174 | 364 | 178 | 173 | 351 | 75° 17' 12.17"E | 24° 9' 37.63"N | 529125.7 | 2672020.85 |  | Beti_khedi | Sitamau | MP
[5 empty] | 356 | [16 empty] | Cart track
36 |  | 8/6 | DA+0 |  |  |  | 13568.428 | 418.57 | 72.5 | 764 | 382 | 182 | 228 | 410 | 183 | 238 | 421 | 75° 17' 23.92"E | 24° 9' 33.41"N | 529457.5 | 2671891.84 |  | Rojafatehag | Sitamau | MP
[5 empty] | 408 | [16 empty] | 11kV line & Cart track
37 |  | 8/7 | DA+0 |  |  |  | 13976.428 | 412 | 72.5 | 823 | 411.5 | 180 | 208 | 388 | 170 | 208 | 378 | 75° 17' 37.38"E | 24° 9' 28.58"N | 529837.77 | 2671743.99 |  | Rojafatehag | Sitamau | MP
[5 empty] | 415 | [16 empty] | LT line, Nala & Cart track
38 |  | 8/8 | DA+3 |  |  |  | 14391.428 | 408.975 | 75.5 | 786 | 393 | 207 | 216 | 423 | 207 | 230 | 437 | 75° 17' 51.08"E | 24° 9' 23.66"N | 530224.57 | 2671593.6 |  | Rojafatehag | Sitamau | MP
[5 empty] | 371 | [16 empty] | Nala
39 |  | 8/9 | DA(-)3 |  |  |  | 14762.428 | 407.29 | 69.5 | 735 | 367.5 | 155 | 162 | 317 | 141 | 153 | 294 | 75°18'3.31"E | 24° 9'19.26"N | 530570.35 | 2671459.16 |  | Rojafatehag | Sitamau | MP
[5 empty] | 364 | [16 empty] | 11kV line & Cart track
40 |  | 8/10 | DA+0 |  |  |  | 15126.428 | 409.2 | 72.5 | 779 | 389.5 | 202 | 205 | 407 | 211 | 204 | 415 | 75°18'15.31"E | 24° 9'14.95"N | 530909.61 | 2671327.25 |  | Rojafatehag | Sitamau | MP
[5 empty] | 415 | [16 empty] | 11kV line, metal road & Nala
41 | AP9/0 | 9/0 | DB2+0 | 9° 24' 57"LT |  | 4304 | 15541.428 | 409.93 | 70.72 | 804 | 402 | 210 | 181 | 391 | 211 | 175 | 386 | 75° 18' 29.02" | 24° 9' 10.04" | 531296.31 | 2671176.9 |  | Halu_Khedi | Sitamau | MP
[5 empty] | 389 | [16 empty] | LT line
42 |  | 9/1 | DA+3 |  |  |  | 15930.428 | 410.47 | 75.5 | 785 | 392.5 | 208 | 205 | 413 | 214 | 209 | 423 | 75° 18' 42.51" | 24° 9' 7.42" | 531677.04 | 2671097.15 |  | Halu_Khedi | Sitamau | MP
[5 empty] | 396 | [16 empty] | Nala
43 |  | 9/2 | DA+0 |  |  |  | 16326.428 | 411.48 | 72.5 | 835 | 417.5 | 191 | 190 | 381 | 187 | 176 | 363 | 75° 18' 56.24" | 24° 9' 4.75" | 532064.63 | 2671015.96 |  | Halu_Khedi | Sitamau | MP
[5 empty] | 439 | [16 empty] | 11kV line
44 |  | 9/3 | DA+6 |  |  |  | 16765.428 | 414.42 | 78.5 | 820 | 410 | 249 | 204 | 453 | 263 | 210 | 473 | 75° 19' 11.45" | 24° 9' 1.79" | 532494.3 | 2670925.96 |  | Rupni | Sitamau | MP
[5 empty] | 381 | [16 empty] | 11kV line
45 | AP10/0 | 10/0 | DB1+0 | 4° 31' 7"RT |  | 1605 | 17146.428 | 416.975 | 70.72 | 767 | 383.5 | 220 | 188 | 408 | 210 | 190 | 400 | 75°19'24.673" | 24°8'59.22" | 532867.524 | 2670847.779 |  | Rupni | Sitamau | MP
[5 empty] | 386 | [16 empty] | 33kV line,2no's LT line, Metal road & 2no's nala
46 |  | 10/1 | DA+0 |  |  |  | 17532.428 | 418.018 | 72.5 | 742 | 371 | 199 | 176 | 375 | 198 | 177 | 375 | 75°19'37.789" | 24°8'55.66" | 533237.916 | 2670739.123 |  | Rupni | Sitamau | MP
[5 empty] | 356 | [16 empty] | Cart track,Well
47 |  | 10/2 | DA(-)3 |  |  |  | 17888.428 | 421.412 | 69.5 | 721 | 360.5 | 181 | 129 | 310 | 180 | 146 | 326 | 75°19'49.885" | 24°8'52.375" | 533579.52 | 2670638.912 |  | Rupni | Sitamau | MP
[5 empty] | 365 | [16 empty] | 11kV line, Nala & Cart track
48 |  | 10/3 | DA+3 |  |  |  | 18253.428 | 424.562 | 75.5 | 840 | 420 | 236 | 118 | 354 | 220 | 155 | 375 | 75°20'2.287" | 24°8'49.007" | 533929.761 | 2670536.167 |  | Risthal | Sitamau | MP
[5 empty] | 475 | [16 empty] | 2 No's 11kV line, Nala & Cart track
49 | AP11/0 | 11/0 | DD60+25 | 25° 28' 21"LT |  | 1582 | 18728.428 | 429.486 | 95.72 | 671 | 335.5 | 359 | 75 | 434 | 323 | 89 | 412 | 75°20'18.43" | 24°8'44.623" | 534385.651 | 2670402.43 |  | Risthal | Sitamau | MP
[5 empty] | 196 | [16 empty] | 400 KV DC NEEMUCH-MANDSAUR TL TN 253 - TN 254
50 | AP12/0 | 12/0 | DD60+25 | 27° 8' 47"RT |  | 196 | 18924.428 | 430.037 | 95.72 | 673 | 336.5 | 121 | 349 | 470 | 107 | 315 | 422 | 75°20'25.289" | 24°8'45.618" | 534579.163 | 2670433.506 | 1M RC | Risthal | Sitamau | MP | 1 | 1 | 1 | 1
[5 empty] | 477 | [16 empty] | 11kV line, Nala & Cart track
51 |  | 12/1 | DA+3 |  |  |  | 19401.428 | 428.713 | 75.5 | 840 | 420 | 129 | 219 | 348 | 165 | 207 | 372 | 75°20'41.349" | 24°8'40.784" | 535032.758 | 2670285.922 |  | Risthal | Sitamau | MP
[5 empty] | 363 | [16 empty] | LT line, Nala & Cart track
52 |  | 12/2 | DA(-)3 |  |  |  | 19764.428 | 428.434 | 69.5 | 691 | 345.5 | 145 | 156 | 301 | 157 | 159 | 316 | 75°20'53.57" | 24°8'37.104" | 535377.946 | 2670173.61 |  | Risthal | Sitamau | MP
328
53 |  | 12/3 | DA(-)3 |  |  |  | 20092.428 | 429.607 | 69.5 | 704 | 352 | 172 | 161 | 333 | 170 | 170 | 340 | 75°21'4.613" | 24°8'33.779" | 535689.851 | 2670072.126 |  | Risthal | Sitamau | MP
[5 empty] | 376 | [16 empty] | Cart track & Nala
54 |  | 12/4 | DA+0 |  |  |  | 20468.428 | 431.437 | 72.5 | 769 | 384.5 | 216 | 180 | 396 | 207 | 185 | 392 | 75°21'17.272" | 24°8'29.967" | 536047.402 | 2669955.792 |  | Risthal | Sitamau | MP
[5 empty] | 393 | [16 empty] | 11kV line & Cart track
55 |  | 12/5 | DA+1.5 |  |  |  | 20861.428 | 433.068 | 74 | 790 | 395 | 214 | 209 | 423 | 209 | 206 | 415 | 75°21'30.503" | 24°8'25.983" | 536421.118 | 2669834.197 |  | Boliya | Sitamau | MP
[5 empty] | 397 | [16 empty] | LT line
56 |  | 12/6 | DA+0 |  |  |  | 21258.428 | 432.71 | 72.5 | 791 | 395.5 | 189 | 199 | 388 | 192 | 199 | 391 | 75°21'43.868" | 24°8'21.957" | 536798.638 | 2669711.365 |  | Boliya | Sitamau | MP
[5 empty] | 394 | [16 empty] | 11kV line & 2No'sCart track,Well
57 |  | 12/7 | DA+0 |  |  |  | 21652.428 | 432.437 | 72.5 | 767 | 383.5 | 196 | 194 | 390 | 197 | 192 | 389 | 75°21'57.132" | 24°8'17.962" | 537173.305 | 2669589.462 |  | Boliya | Sitamau | MP
[5 empty] | 373 | [16 empty] | 11kV line & Cart track
58 | AP13/0 | 13/0 | DB2+0 | 9° 25' 31"RT |  | 3101 | 22025.428 | 431.107 | 70.72 | 730 | 365 | 179 | 194 | 373 | 182 | 189 | 371 | 75°22'9.688" | 24°8'14.179" | 537527.991 | 2669474.059 |  | Boliya | Sitamau | MP
[5 empty] | 357 | [16 empty] | LT line, Nala & Cart track,Pond,Well
59 |  | 13/1 | DA(-)1.5 |  |  |  | 22382.428 | 430.193 | 71 | 731 | 365.5 | 164 | 179 | 343 | 169 | 183 | 352 | 75°22'20.897" | 24°8'8.801" | 537844.803 | 2669309.499 |  | Boliya | Sitamau | MP
[5 empty] | 374 | [16 empty] | 2No's Cart track
60 |  | 13/2 | DA+0 |  |  |  | 22756.428 | 430.005 | 72.5 | 754 | 377 | 195 | 200 | 395 | 193 | 197 | 390 | 75°22'32.641" | 24°8'3.167" | 538176.7 | 2669137.104 |  | Vishanya | Sitamau | MP
[5 empty] | 380 | [16 empty] | 2No'sLT line &2No's Cart track
61 |  | 13/3 | DA+0 |  |  |  | 23136.428 | 428.413 | 72.5 | 724 | 362 | 181 | 197 | 378 | 185 | 189 | 374 | 75°22'44.572" | 24°7'57.442" | 538513.922 | 2668961.943 |  | Vishanya | Sitamau | MP
[5 empty] | 344 | [16 empty] | Cart track & Nala
62 |  | 13/4 | DA(-)3 |  |  |  | 23480.428 | 427.526 | 69.5 | 674 | 337 | 147 | 159 | 306 | 156 | 161 | 317 | 75°22'55.372" | 24°7'52.259" | 538819.197 | 2668803.376 |  | Vishanya | Sitamau | MP
[5 empty] | 330 | [16 empty] | 11kV line & Cart track
63 |  | 13/5 | DA+0 |  |  |  | 23810.428 | 425.498 | 72.5 | 697 | 348.5 | 172 | 208 | 380 | 170 | 200 | 370 | 75°23'5.733" | 24°7'47.287" | 539112.047 | 2668651.262 |  | Vishanya | Sitamau | MP
[5 empty] | 367 | [16 empty] | Cart track
64 | AP14/0 | 14/0 | DC1+0 | 18° 44' 47"LT |  | 2152 | 24177.428 | 421.509 | 70.72 | 752 | 376 | 160 | 173 | 333 | 169 | 180 | 349 | 75°23'17.263" | 24°7'41.754" | 539437.951 | 2668481.98 |  | Vishanya | Sitamau | MP
[5 empty] | 385 | [16 empty] | 33kV line,11kV line,LT line, Metal road,Cart track & nala
65 |  | 14/1 | DA+0 |  |  |  | 24562.428 | 425.073 | 72.5 | 740 | 370 | 213 | 170 | 383 | 206 | 173 | 379 | 75°23'30.74" | 24°7'39.825" | 539818.519 | 2668423.73 |  | Vishanya | Sitamau | MP
[5 empty] | 355 | [16 empty] | Cart track
66 |  | 14/2 | DA+0 |  |  |  | 24917.428 | 426.383 | 72.5 | 712 | 356 | 186 | 179 | 365 | 183 | 179 | 362 | 75°23'43.167" | 24°7'38.047" | 540169.432 | 2668370.02 |  | Vishanya | Sitamau | MP
[5 empty] | 357 | [16 empty] | 11kV line,LT line, Metal road & Cart track
67 |  | 14/3 | DA(-)3 |  |  |  | 25274.428 | 429.339 | 69.5 | 750 | 375 | 178 | 169 | 347 | 179 | 179 | 358 | 75°23'55.664" | 24°7'36.258" | 540522.323 | 2668316.006 |  | Khajuri_Goud | Sitamau | MP
[5 empty] | 393 | [16 empty] | 11kV line & Cart track
68 |  | 14/4 | DA+3 |  |  |  | 25667.428 | 428.349 | 75.5 | 776 | 388 | 225 | 239 | 464 | 216 | 223 | 439 | 75°24'9.421" | 24°7'34.289" | 540910.798 | 2668256.546 |  | Khajuri_Goud | Sitamau | MP
[5 empty] | 383 | [16 empty] | LT line & Cart track
69 |  | 14/5 | DA+0 |  |  |  | 26050.428 | 423.122 | 72.5 | 771 | 385.5 | 145 | 218 | 363 | 161 | 211 | 372 | 75°24'22.828" | 24°7'32.369" | 541289.389 | 2668198.599 |  | Khajuri_Goud | Sitamau | MP
[5 empty] | 388 | [16 empty] | LT line (To be diverted), Nala & Cart track
70 | AP15/0 | 15/0 | DB2+0 | 12° 10' 5"RT |  | 2261 | 26438.428 | 418.854 | 70.72 | 756 | 378 | 170 | 193 | 363 | 179 | 190 | 369 | 75°24'36.413" | 24°7'30.424" | 541673.01 | 2668139.882 |  | Khajuri_Goud | Sitamau | MP
[5 empty] | 368 | [16 empty] | Nala
71 |  | 15/1 | DA+0 |  |  |  | 26806.428 | 417.373 | 72.5 | 780 | 390 | 176 | 175 | 351 | 179 | 185 | 364 | 75°24'48.581" | 24°7'26.128" | 542016.865 | 2668008.781 |  | Khajuri_Goud | Sitamau | MP
[5 empty] | 412 | [16 empty] | 11kV line, Nala & Cart track
72 |  | 15/2 | DA+3 |  |  |  | 27218.428 | 420.33 | 75.5 | 828 | 414 | 237 | 221 | 458 | 228 | 217 | 445 | 75°25'2.204" | 24°7'21.319" | 542401.834 | 2667862.005 |  | Khajuri_Goud | Sitamau | MP
416
73 |  | 15/3 | DA+0 |  |  |  | 27634.428 | 420.876 | 72.5 | 823 | 411.5 | 196 | 167 | 363 | 200 | 179 | 379 | 75°25'15.959" | 24°7'16.462" | 542790.54 | 2667713.804 |  | Khajuri_Goud | Sitamau | MP
[5 empty] | 407 | [16 empty] | Cart track
74 |  | 15/4 | DA+6 |  |  |  | 28041.428 | 421.793 | 78.5 | 832 | 416 | 240 | 318 | 558 | 229 | 285 | 514 | 75°25'29.416" | 24°7'11.71" | 543170.837 | 2667568.81 |  | Khajuri_Goud | Sitamau | MP
[5 empty] | 425 | [16 empty] | Nala
75 |  | 15/5 | DA(-)3 |  |  |  | 28466.428 | 410.078 | 69.5 | 811 | 405.5 | 108 | 150 | 258 | 142 | 164 | 306 | 75°25'43.468" | 24°7'6.748" | 543567.953 | 2667417.403 |  | Salriya | Sitamau | MP
[5 empty] | 386 | [16 empty] | 11kV line, Nala & Cart track
76 |  | 15/6 | DA+0 |  |  |  | 28852.428 | 414.874 | 72.5 | 745 | 372.5 | 237 | 128 | 365 | 223 | 144 | 367 | 75°25'56.23" | 24°7'2.241" | 543928.627 | 2667279.889 | Raised Chimney | Salriya | Sitamau | MP | 2 | 2 | 0 | 0
[5 empty] | 359 | [16 empty] | Cart track
77 |  | 15/7 | DA+0 |  |  |  | 29211.428 | 423.544 | 72.5 | 727 | 363.5 | 232 | 157 | 389 | 216 | 166 | 382 | 75°26'8.099" | 24°6'58.049" | 544264.073 | 2667151.995 |  | Salriya | Sitamau | MP
[5 empty] | 368 | [16 empty] | Cart track
78 |  | 15/8 | DA+0 |  |  |  | 29579.428 | 428.193 | 72.5 | 758 | 379 | 211 | 178 | 389 | 203 | 183 | 386 | 75°26'20.266" | 24°6'53.751" | 544607.929 | 2667020.894 |  | Salriya | Sitamau | MP
[5 empty] | 390 | [16 empty] | Cart track
79 |  | 15/9 | DA+3 |  |  |  | 29969.428 | 428.403 | 75.5 | 800 | 400 | 213 | 234 | 447 | 208 | 225 | 433 | 75°26'33.16" | 24°6'49.196" | 544972.341 | 2666881.956 |  | Borkhedi_Jagir | Sitamau | MP
[5 empty] | 410 | [16 empty] | Cart track
80 | AP16/0 | 16/0 | DB1+0 | 2°04'42"RT |  | 3941 | 30379.428 | 425.949 | 70.72 | 790 | 395 | 177 | 208 | 385 | 186 | 216 | 402 | 75° 26' 46.7" | 24° 6' 44.41" | 545355.05 | 2666736.04 |  | Borkhedi_Jagir | Sitamau | MP
380
81 |  | 16/1 | DA+0 |  |  |  | 30759.428 | 421.3 | 72.5 | 747 | 373.5 | 171 | 235 | 406 | 164 | 252 | 416 | 75° 26' 59.29" | 24° 6' 40.05" | 545711 | 2666603 |  | Borkhedi_Jagir | Sitamau | MP
[5 empty] | 367 | [16 empty] | 2 NOS CART TRACK / LT LINE
82 |  | 16/2 | DA+0 |  |  |  | 31126.428 | 409.5 | 72.5 | 800 | 400 | 132 | 187 | 319 | 115 | 177 | 292 | 75° 27' 11.46" | 24° 6' 35.84" | 546054.77 | 2666474.51 |  | Borkhedi_Jagir | Sitamau | MP
[5 empty] | 433 | [16 empty] | 3 NOS. NALA/ CART TRACK/LT LINE
83 |  | 16/3 | DA+9 |  |  |  | 31559.428 | 408.511 | 81.5 | 833 | 416.5 | 246 | 184 | 430 | 256 | 178 | 434 | 75° 27' 25.81" | 24° 6' 30.86" | 546460.37 | 2666322.91 |  | Borkhedi_Jagir | Sitamau | MP
[5 empty] | 400 | [16 empty] | WELL/NALA/CART TRACK /11 KV LINE
84 |  | 16/4 | DA+0 |  |  |  | 31959.428 | 421.58 | 72.5 | 796 | 398 | 216 | 155 | 371 | 222 | 140 | 362 | 75° 27' 39.06" | 24° 6' 26.27" | 546835.05 | 2666182.87 |  | Borkhedi_Jagir | Sitamau | MP
[5 empty] | 396 | [16 empty] | TAR ROAD/11KV LINE
85 |  | 16/5 | DA+6 |  |  |  | 32355.428 | 426.247 | 78.5 | 816 | 408 | 241 | 255 | 496 | 256 | 270 | 526 | 75° 27' 52.19" | 24° 6' 21.72" | 547205.99 | 2666044.23 |  | Borkhedi_Jagir | Sitamau | MP
[5 empty] | 420 | [16 empty] | 3 NOS NALA
86 |  | 16/6 | DA(-)3 |  |  |  | 32775.428 | 423.4 | 69.5 | 774 | 387 | 165 | 155 | 320 | 150 | 147 | 297 | 75° 28' 6.11" | 24° 6' 16.9" | 547599.4 | 2665897.18 |  | Chimangad | Sitamau | MP
[5 empty] | 354 | [16 empty] | WELL
87 |  | 16/7 | DA+0 |  |  |  | 33129.428 | 425.32 | 72.5 | 702 | 351 | 199 | 214 | 413 | 207 | 228 | 435 | 75° 28' 17.84" | 24° 6' 12.83" | 547931 | 2665773.25 |  | Chimangad | Sitamau | MP
[5 empty] | 348 | [16 empty] | 11 KV LINE/TAR ROAD/CART TRACK/WELL
88 |  | 16/8 | DA(-)3 |  |  |  | 33477.428 | 419.483 | 69.5 | 667 | 333.5 | 134 | 146 | 280 | 120 | 141 | 261 | 75° 28' 29.37" | 24° 6' 8.84" | 548256.97 | 2665651.41 |  | Chimangad | Sitamau | MP
[5 empty] | 319 | [16 empty] | WELL
89 |  | 16/9 | DA+0 |  |  |  | 33796.428 | 419.25 | 72.5 | 698 | 349 | 173 | 199 | 372 | 178 | 202 | 380 | 75° 28' 39.94" | 24° 6' 5.17" | 548555.78 | 2665539.72 |  | Chimangad | Sitamau | MP
[5 empty] | 379 | [16 empty] | 2 NOS 11KV /CART TRACK/BRICK FACTORY
90 |  | 16/10 | DA+6 |  |  |  | 34175.428 | 411.1 | 78.5 | 807 | 403.5 | 180 | 213 | 393 | 177 | 212 | 389 | 75° 28' 52.5" | 24° 6' 0.82" | 548910.8 | 2665407.03 |  | Chimangad | Sitamau | MP
[5 empty] | 428 | [16 empty] | NALA
91 |  | 16/11 | DA+0 |  |  |  | 34603.428 | 417.45 | 72.5 | 825 | 412.5 | 215 | 185 | 400 | 216 | 181 | 397 | 75° 29' 6.68" | 24° 5' 55.9" | 549311.71 | 2665257.19 |  | Chimangad | Sitamau | MP
[5 empty] | 397 | [16 empty] | CART TRACK/11KV LINE/PUMP
92 | AP17/0 | 17/0 | DB2+3 | 12°41'17"RT |  | 4621 | 35000.428 | 417.72 | 73.72 | 644 | 322 | 212 | 150 | 362 | 216 | 159 | 375 | 75° 29' 19.83" | 24° 5' 51.34" | 549683.4 | 2665118.26 |  | Chahkhedi | Sitamau | MP
[5 empty] | 247 | [16 empty] | 2 NOS 33KV LINE/NE-4 DELHI MUMBAI EXPRESSWAY/CART TRACK
93 | AP18/0 | 18/0 | DD45+0 | 35° 35' 35"LT |  | 247 | 35247.428 | 416.658 | 70.72 | 670 | 335 | 82 | 261 | 343 | 104 | 247 | 351 | 75°29'27.132"E | 24°5'46.924"N | 549890.07 | 2664983.112 |  | Chahkhedi | Sitamau | MP
423
94 |  | 18/1 | DA+6 |  |  |  | 35670.428 | 400.691 | 78.5 | 818 | 409 | 162 | 171 | 333 | 177 | 179 | 356 | 75°29'42.103"E | 24°5'47.454"N | 550312.695 | 2665000.909 |  | Chahkhedi | Sitamau | MP
[5 empty] | 395 | [16 empty] | CT, NALA
95 | AP19/0 | 19/0 | DD45+9 | 37° 14' 44"LT |  | 818 | 36065.428 | 402.673 | 79.72 | 894 | 447 | 224 | 246 | 470 | 218 | 247 | 465 | 75°29'56.082"E | 24°5'47.949"N | 550707.293 | 2665017.525 | Raised Chimney | Chahkhedi | Sitamau | MP | 0.5 | 0 | 1 | 2
[5 empty] | 499 | [16 empty] | 11KV, CHAMBAL RIVER, LT END
96 | AP20/0 | 20/0 | DD60+6 | 52° 09' 12"RT |  | 499 | 36564.428 | 406.4 | 76.72 | 876 | 438 | 253 | 182 | 435 | 252 | 183 | 435 | 75°30'9.71"E | 24° 5'58.26"N | 551091.52 | 2665336.02 | Raised Chimney | Dhandi | Suwasara | MP | 2.5 | 1 | 0 | 1.5
[5 empty] | 377 | [16 empty] | 11KV, LT
97 |  | 20/1 | DA(-)3 |  |  |  | 36941.428 | 416.61 | 69.5 | 820 | 410 | 195 | 214 | 409 | 194 | 216 | 410 | 75°30'22.74"E | 24° 5'55.55"N | 551459.58 | 2665254.43 |  | Dhandi | Suwasara | MP
[5 empty] | 443 | [16 empty] | CT, POND, WELL
98 |  | 20/2 | DA(-)3 |  |  |  | 37384.428 | 418.169 | 69.5 | 787 | 393.5 | 229 | 161 | 390 | 227 | 164 | 391 | 75°30'38.06"E | 24° 5'52.38"N | 551892.08 | 2665158.56 |  | Dhandi | Suwasara | MP
[5 empty] | 344 | [16 empty] | CT, POND, HUT
99 | AP21/0 | 21/0 | DC2+0 | 24° 53' 25"RT |  | 1164 | 37728.428 | 416.971 | 70.72 | 734 | 367 | 184 | 250 | 434 | 180 | 233 | 413 | 75°30'49.948"E | 24°5'49.936"N | 552227.864 | 2665084.121 |  | Dhandi | Suwasara | MP
[5 empty] | 390 | [16 empty] | 11KV, LT, NALA
100 |  | 21/1 | DA(-)3 |  |  |  | 38118.428 | 410.114 | 69.5 | 742 | 371 | 141 | 160 | 301 | 159 | 165 | 324 | 75°31'0.893"E | 24°5'42.199"N | 552537.73 | 2664847.302 |  | Haripura | Suwasara | MP
[5 empty] | 352 | [16 empty] | CT
101 |  | 21/2 | DA+0 |  |  |  | 38470.428 | 409.768 | 72.5 | 778 | 389 | 192 | 204 | 396 | 188 | 207 | 395 | 75°31'10.77"E | 24°5'35.216"N | 552817.404 | 2664633.558 |  | Haripura | Suwasara | MP
[5 empty] | 426 | [16 empty] | WELL
102 |  | 21/3 | DA+0 |  |  |  | 38896.428 | 411.604 | 72.5 | 820 | 410 | 223 | 118 | 341 | 220 | 143 | 363 | 75°31'22.724"E | 24°5'26.764"N | 553155.873 | 2664374.879 |  | Haripura | Suwasara | MP
[5 empty] | 394 | [16 empty] | CT
103 |  | 21/4 | DA+3 |  |  |  | 39290.428 | 423.212 | 75.5 | 802 | 401 | 277 | 206 | 483 | 252 | 206 | 458 | 75°31'33.78"E | 24°5'18.947"N | 553468.917 | 2664135.632 |  | Haripura | Suwasara | MP
[5 empty] | 408 | [16 empty] | CT
104 | AP22/0 | 22/0 | DD45+0 | 35° 17' 43"LT |  | 1970 | 39698.428 | 425.907 | 70.72 | 781 | 390.5 | 203 | 136 | 339 | 203 | 153 | 356 | 75°31'45.221"E | 24°5'10.857"N | 553792.883 | 2663888.037 | Raised Chimney | Haripura | Suwasara | MP | 0 | 0 | 1 | 1
[5 empty] | 373 | [16 empty] | NALA
105 |  | 22/1 | DA+6 |  |  |  | 40071.428 | 428.621 | 78.5 | 781 | 390.5 | 237 | 201 | 438 | 221 | 202 | 423 | 75°31'58.42"E | 24°5'10.368"N | 554165.634 | 2663874.407 |  | Haripura | Suwasara | MP
[5 empty] | 408 | [16 empty] | NALA, METAL ROAD, CT, 11KV, WELL
106 | AP23/0 | 23/0 | DD45+3 | 39° 44' 47"RT |  | 781 | 40479.428 | 432.286 | 73.72 | 787 | 393.5 | 208 | 183 | 391 | 207 | 185 | 392 | 75°32'12.86"E | 24°5'9.833"N | 554573.393 | 2663859.497 |  | Haripura | Suwasara | MP
[5 empty] | 379 | [16 empty] | 11KV, CT, LT
107 |  | 23/1 | DA+3 |  |  |  | 40858.428 | 433.578 | 75.5 | 785 | 392.5 | 197 | 205 | 402 | 195 | 205 | 400 | 75°32'22.825"E | 24°5'1.577"N | 554855.75 | 2663606.682 |  | Haripura | Suwasara | MP
[5 empty] | 406 | [16 empty] | 11KV, WELL, METAL ROAD
108 | AP24/0 | 24/0 | DC2+3 | 23° 2' 13"LT |  | 785 | 41264.428 | 433.22 | 73.72 | 791 | 395.5 | 201 | 195 | 396 | 202 | 195 | 397 | 75°32'33.491"E | 24°4'52.741"N | 555157.958 | 2663336.092 | Raised Chimney | Haripura | Suwasara | MP | 1 | 2 | 1 | 0
[5 empty] | 385 | [16 empty] | ORANGE GARDEN, 11KV, CT, WELL,
109 |  | 24/1 | DA+0 |  |  |  | 41649.428 | 435.751 | 72.5 | 785 | 392.5 | 190 | 190 | 380 | 191 | 194 | 385 | 75°32'46.381"E | 24°4'48.661"N | 555522.411 | 2663211.998 |  | Haripura | Suwasara | MP
[5 empty] | 400 | [16 empty] | LT,CT, WELL, 11KV
110 |  | 24/2 | DA+0 |  |  |  | 42049.428 | 437.648 | 72.5 | 839 | 419.5 | 210 | 174 | 384 | 208 | 188 | 396 | 75°32'59.773"E | 24°4'44.42"N | 555901.063 | 2663083.069 |  | Haripura | Suwasara | MP
[5 empty] | 439 | [16 empty] | 33KV
111 |  | 24/3 | DA+6 |  |  |  | 42488.428 | 441.109 | 78.5 | 839 | 419.5 | 266 | 224 | 490 | 252 | 217 | 469 | 75°33'14.471"E | 24°4'39.767"N | 556316.633 | 2662941.569 |  | Haripura | Suwasara | MP
[5 empty] | 400 | [16 empty] | 11KV, 33KV
112 |  | 24/4 | DA(-)3 |  |  |  | 42888.428 | 445.75 | 69.5 | 691 | 345.5 | 177 | 174 | 351 | 185 | 166 | 351 | 75°33'27.862"E | 24°4'35.526"N | 556695.285 | 2662812.64 |  | Haripura | Suwasara | MP
[5 empty] | 291 | [16 empty] | 11KV, 33KV, SH-8 ROAD
113 |  | 24/5 | DA(-)3 |  |  |  | 43179.428 | 441.826 | 69.5 | 681 | 340.5 | 117 | 172 | 289 | 126 | 179 | 305 | 75°33'37.604"E | 24°4'32.44"N | 556970.754 | 2662718.844 |  | Haripura | Suwasara | MP
[5 empty] | 390 | [16 empty] | 33KV, CT, WELL
114 |  | 24/6 | DA+3 |  |  |  | 43569.428 | 440.116 | 75.5 | 793 | 396.5 | 219 | 223 | 442 | 212 | 217 | 429 | 75°33'50.661"E | 24°4'28.305"N | 557339.94 | 2662593.138 |  | Haripura | Suwasara | MP
[5 empty] | 403 | [16 empty] | CT, BORE
115 |  | 24/7 | DA+0 |  |  |  | 43972.428 | 439.023 | 72.5 | 825 | 412.5 | 180 | 180 | 360 | 187 | 190 | 377 | 75°34'4.152"E | 24°4'24.032"N | 557721.432 | 2662463.242 |  | Haripura | Suwasara | MP
[5 empty] | 422 | [16 empty] | 33KV, WELL, 11KV, CT
116 |  | 24/8 | DA+6 |  |  |  | 44394.428 | 439.161 | 78.5 | 811 | 405.5 | 242 | 257 | 499 | 233 | 238 | 471 | 75°34'18.279"E | 24°4'19.556"N | 558120.91 | 2662327.222 |  | Kantiya | Suwasara | MP
[5 empty] | 389 | [16 empty] | 11KV, METAL ROAD
117 |  | 24/9 | DA(-)1.5 |  |  |  | 44783.428 | 435.355 | 71 | 825 | 412.5 | 133 | 206 | 339 | 152 | 210 | 362 | 75°34'31.301"E | 24°4'15.431"N | 558489.149 | 2662201.839 |  | Kantiya | Suwasara | MP
[5 empty] | 436 | [16 empty] | LT, NALA, CT
118 |  | 24/10 | DA+1.5 |  |  |  | 45219.428 | 434.97 | 74 | 816 | 408 | 231 | 183 | 414 | 228 | 185 | 413 | 75°34'45.896"E | 24°4'10.806"N | 558901.879 | 2662061.306 |  | Kantiya | Suwasara | MP
[5 empty] | 380 | [16 empty] | WELL, CT, 11KV
119 |  | 24/11 | DA+0 |  |  |  | 45599.428 | 437.855 | 72.5 | 825 | 412.5 | 198 | 154 | 352 | 196 | 175 | 371 | 75°34'58.616"E | 24°4'6.775"N | 559261.599 | 2661938.823 |  | Kantiya | Suwasara | MP
[5 empty] | 445 | [16 empty] | CT, WELL, NALA
120 | AP25/0 | 25/0 | DC2+18 | 12° 27' 1"RT |  | 4780 | 46044.428 | 434.424 | 88.72 | 665 | 332.5 | 293 | 140 | 433 | 272 | 123 | 395 | 75°35'13.522"E | 24°4'2.051"N | 559683.148 | 2661795.288 |  | Kantiya | Suwasara | MP
[5 empty] | 220 | [16 empty] | 220 KV DC MANDSAUR - NIPANIA TL MPPTCL T83-84, LT, ORANGE GARDEN
121 | AP26/0 | 26/0 | DC2+12 | 19° 44' 39"LT |  | 220 | 46264.428 | 438.091 | 82.72 | 655 | 327.5 | 80 | 252 | 332 | 97 | 244 | 341 | 75°35'20.159"E | 24°3'58.318"N | 559871.045 | 2661681.252 |  | Kantiya | Suwasara | MP
[5 empty] | 435 | [16 empty] | ORANGE GARDEN, CT, WELL
122 |  | 26/1 | DA+1.5 |  |  |  | 46699.428 | 440.005 | 74 | 840 | 420 | 184 | 187 | 371 | 193 | 191 | 384 | 75°35'35.24"E | 24°3'55.438"N | 560297.298 | 2661594.456 |  | Ruparail | Suwasara | MP
[5 empty] | 405 | [16 empty] | CT, LT, 11KV, WELL
123 |  | 26/2 | DA+6 |  |  |  | 47104.428 | 439.354 | 78.5 | 839 | 419.5 | 219 | 235 | 454 | 216 | 231 | 447 | 75°35'49.281"E | 24°3'52.755"N | 560694.154 | 2661513.645 |  | Ruparail | Suwasara | MP
[5 empty] | 434 | [16 empty] | METAL ROAD, 11KV, WELL, POND, CT, LT
124 |  | 26/3 | DA+6 |  |  |  | 47538.428 | 434.871 | 78.5 | 814 | 407 | 200 | 216 | 416 | 205 | 210 | 415 | 75°36'4.327"E | 24°3'49.881"N | 561119.427 | 2661427.049 |  | Ruparail | Suwasara | MP
[5 empty] | 380 | [16 empty] | CT, NALA, HUT, WELL, BARGAD TREE
125 |  | 26/4 | DA(-)3 |  |  |  | 47918.428 | 438.149 | 69.5 | 759 | 379.5 | 165 | 121 | 286 | 171 | 138 | 309 | 75°36'17.5"E | 24°3'47.364"N | 561491.785 | 2661351.227 |  | Ruparail | Suwasara | MP
379
126 | AP27/0 | 27/0 | DB2+9 | 13° 19' 59"RT |  | 2033 | 48297.428 | 441.418 | 79.72 | 857 | 428.5 | 275 | 258 | 533 | 250 | 255 | 505 | 75°36'30.634"E | 24°3'44.854"N | 561863.017 | 2661275.634 |  | Devriya_vijay | Suwasara | MP
[5 empty] | 478 | [16 empty] | WELL, CT, 11KV, PIPAL TREE
127 |  | 27/1 | DB1+9 |  |  | 478 | 48775.428 | 435.383 | 79.72 | 942 | 471 | 221 | 267 | 488 | 225 | 257 | 482 | 75036'45.962"E | 2403'38.263"N | 562296.784 | 2661074.813 |  | Devriya_vijay | Suwasara | MP
[5 empty] | 464 | [16 empty] | NALA, 11KV, SAMADHI, LT END, 11KV TF
128 |  | 27/2 | DA+0 |  |  |  | 49239.428 | 438.024 | 72.5 | 840 | 420 | 198 | 171 | 369 | 209 | 177 | 386 | 75°37'0.841"E | 24°3'31.865"N | 562717.849 | 2660879.874 |  | Devriya_vijay | Suwasara | MP
[5 empty] | 376 | [16 empty] | MAHUA TREE, GUAVA GARDEN, FENCE, WELL, PUMPHOUSE, LT, METAL ROAD, 11KV, NEW GARDEN
129 |  | 27/3 | DA+1.5 |  |  |  | 49615.428 | 439.558 | 74 | 756 | 378 | 206 | 202 | 408 | 200 | 199 | 399 | 75°37'12.898"E | 24°3'26.68"N | 563059.056 | 2660721.906 |  | Devriya_vijay | Suwasara | MP
[5 empty] | 380 | [16 empty] | NEW GARDEN, WELL, CT, 11KV, PIPAL TREE, LT
130 |  | 27/4 | DA(-)3 |  |  |  | 49995.428 | 441.94 | 69.5 | 732 | 366 | 178 | 159 | 337 | 182 | 163 | 345 | 75°37'25.083"E | 24°3'21.439"N | 563403.893 | 2660562.257 |  | Devriya_vijay | Suwasara | MP
[5 empty] | 352 | [16 empty] | NALA, WELL, LT, WELL
131 |  | 27/5 | DA(-)1.5 |  |  |  | 50347.428 | 443.323 | 71 | 713 | 356.5 | 193 | 122 | 315 | 189 | 137 | 326 | 75°37'36.37"E | 24° 3'16.58"N | 563723.32 | 2660414.37 |  | Devriya_vijay | Suwasara | MP
[5 empty] | 361 | [16 empty] | NALA, 11KV, METAL ROAD, WELL, BORE, CT, 11KV T-POINT, LT
132 | AP28/0 | 28/0 | DD45+6 | 41° 48' 21"RT |  | 1933 | 50708.428 | 445.747 | 76.72 | 613 | 306.5 | 241 | -28 | 213 | 222 | 53 | 275 | 75°37'47.94"E | 24°3'11.608"N | 564050.781 | 2660262.768 |  | Devriya_vijay | Suwasara | MP
[5 empty] | 252 | [16 empty] | LT, 220 KV D GUJARKHEDI-MANDSAUR TL MPPTCL (T57-58)
133 | AP29/0 | 29/0 | DD45+18 | 34° 38' 47"LT |  | 252 | 50960.428 | 448.058 | 88.72 | 646 | 323 | 281 | 265 | 546 | 199 | 244 | 443 | 75°37'51.439"E | 24°3'4.074"N | 564150.632 | 2660031.49 |  | Devriya_vijay | Suwasara | MP
[5 empty] | 394 | [16 empty] | POND, CT, PIPAL TREE, LT, WELL,
134 |  | 29/1 | DA+1.5 |  |  |  | 51354.428 | 452.242 | 74 | 783 | 391.5 | 130 | 180 | 310 | 152 | 185 | 337 | 75°38'3.236"E | 24°2'57.236"N | 564484.756 | 2659822.69 |  | Devriya_vijay | Suwasara | MP
[5 empty] | 389 | [16 empty] | METAL ROAD, WELL, 11KV, WELL, PUMPHOUSE, LT, BORE, 11KV TF
135 |  | 29/2 | DA+1.5 |  |  |  | 51743.428 | 454.842 | 74 | 788 | 394 | 209 | 220 | 429 | 205 | 214 | 419 | 75°38'14.882"E | 24°2'50.484"N | 564814.639 | 2659616.54 |  | Kishorpura | Suwasara | MP
[5 empty] | 399 | [16 empty] | WELL, BARGAD TREE, CT, 11KV, LT, METAL ROAD, TF, BORE, HOUSE
136 | AP30/0 | 30/0 | DC1+0 | 15° 16' 50"RT |  | 1182 | 52142.428 | 452.57 | 70.72 | 791 | 395.5 | 179 | 208 | 387 | 186 | 204 | 390 | 75°38'26.821"E | 24°2'43.563"N | 565152.813 | 2659405.21 |  | Kishorpura | Suwasara | MP
[5 empty] | 392 | [16 empty] | BORE, NALA, SAMADHI, WELL, ORANGE GARDEN, 11KV, LT
137 |  | 30/1 | DA+1.5 |  |  |  | 52534.428 | 449.024 | 74 | 755 | 377.5 | 185 | 210 | 395 | 189 | 201 | 390 | 75°38'36.19"E | 24°2'34.16"N | 565418.739 | 2659117.205 |  | Kishorpura | Suwasara | MP
[5 empty] | 363 | [16 empty] | WELL, CT, NALA, LT
138 |  | 30/2 | DA+0 |  |  |  | 52897.428 | 445.864 | 72.5 | 742 | 371 | 154 | 199 | 353 | 163 | 196 | 359 | 75038'44.865"E | 2402'25.451"N | 565664.994 | 2658850.504 |  | Kishorpura | Suwasara | MP
[5 empty] | 379 | [16 empty] | BORE, NALA, LT, WELL
139 | AP31/0 | 31/0 | DD60+0 | 43° 50' 25"LT |  | 1134 | 53276.428 | 444.125 | 70.72 | 605 | 302.5 | 180 | -12 | 168 | 183 | 57 | 240 | 75°38'53.916"E | 24°2'16.365"N | 565921.935 | 2658572.231 |  | Kishorpura | Suwasara | MP
[5 empty] | 226 | [16 empty] | WELL, DOUBLE TRACK ELECTRIFIED RAILWAY LINE, RAILWAY POLES 770/5 & 770/6
140 | AP32/0 | 32/0 | DD60+9 | 22° 23' 30"RT |  | 226 | 53502.428 | 445.949 | 79.72 | 725 | 362.5 | 238 | 237 | 475 | 169 | 240 | 409 | 75°39'1.902"E | 24°2'15.89"N | 566147.58 | 2658558.659 |  | Kishorpura | Suwasara | MP
[5 empty] | 499 | [16 empty] | WELL, CT, LT, 11KV, PUMPHOUSE
141 |  | 32/1 | DB1+9 |  |  | 499 | 54001.428 | 449.79 | 79.72 | 945 | 472.5 | 264 | 246 | 510 | 262 | 240 | 502 | 75°39'17.767"E | 24°2'8.752"N | 566596.71 | 2658341.213 |  | Nathu_Khedi | Suwasara | MP
[5 empty] | 446 | [16 empty] | ORANGE GARDEN, 11KV, WELL, MAHUA TREE, LT, BOREWELL
142 |  | 32/2 | DA+1.5 |  |  |  | 54447.428 | 452.46 | 74 | 840 | 420 | 201 | 207 | 408 | 208 | 204 | 412 | 75°39'31.946"E | 24°2'2.372"N | 566998.138 | 2658146.863 |  | Nathu_Khedi | Suwasara | MP
[5 empty] | 394 | [16 empty] | 11KV, BORE, WELL, HUT, METAL ROAD
143 |  | 32/3 | DA+1.5 |  |  |  | 54841.428 | 450.685 | 74 | 785 | 392.5 | 188 | 218 | 406 | 191 | 212 | 403 | 75°39'44.471"E | 24°1'56.736"N | 567352.762 | 2657975.172 |  | Dhabla_bhagwan | Suwasara | MP
[5 empty] | 391 | [16 empty] | METAL ROAD
144 |  | 32/4 | DA+0 |  |  |  | 55232.428 | 447.98 | 72.5 | 800 | 400 | 173 | 210 | 383 | 180 | 209 | 389 | 75°39'56.901"E | 24°1'51.142"N | 567704.686 | 2657804.789 |  | Dhabla_bhagwan | Suwasara | MP
[5 empty] | 409 | [16 empty] | LT, CT
145 |  | 32/5 | DA+1.5 |  |  |  | 55641.428 | 445.435 | 74 | 788 | 394 | 199 | 187 | 386 | 201 | 188 | 389 | 75°40'9.903"E | 24°1'45.29"N | 568072.811 | 2657626.562 |  | Dhabla_bhagwan | Suwasara | MP
[5 empty] | 379 | [16 empty] | NALA, LT, WELL
146 |  | 32/6 | DA+0 |  |  |  | 56020.428 | 447.45 | 72.5 | 743 | 371.5 | 193 | 209 | 402 | 192 | 201 | 393 | 75°40'21.951"E | 24°1'39.868"N | 568413.934 | 2657461.407 |  | Dhabla_bhagwan | Suwasara | MP
[5 empty] | 364 | [16 empty] | METAL ROAD, LT
147 |  | 32/7 | DA(-)1.5 |  |  |  | 56384.428 | 444.336 | 71 | 811 | 405.5 | 156 | 187 | 343 | 164 | 199 | 363 | 75°40'33.521"E | 24°1'34.659"N | 568741.557 | 2657302.79 |  | Dhabla_bhagwan | Suwasara | MP
[5 empty] | 447 | [16 empty] | NALA, CT
148 | AP33/0 | 33/0 | DD45+9 | 30° 25' 18"LT |  | 2830 | 56831.428 | 441.528 | 79.72 | 704 | 352 | 260 | 171 | 431 | 250 | 150 | 400 | 75°40'47.721"E | 24°1'28.267"N | 569143.623 | 2657108.13 |  | Bhaisola | Suwasara | MP
[5 empty] | 257 | [16 empty] | 132KV D/C SUWASARA - BADOD MPPTCL (T264-265), LT
149 | AP34/0 | 34/0 | DC1+3 | 18° 17' 56"RT |  | 257 | 57088.428 | 443.161 | 73.72 | 489 | 244.5 | 86 | 127 | 213 | 108 | 123 | 231 | 75°40'56.794"E | 24°1'28.895"N | 569399.846 | 2657128.691 |  | Bhaisola | Suwasara | MP
[5 empty] | 232 | [16 empty] | CT, WELL, METAL ROAD, 11KV
150 |  | 34/1 | DA+3 |  |  |  | 57320.428 | 442.052 | 75.5 | 597 | 298.5 | 106 | 214 | 320 | 109 | 204 | 313 | 75°41'4.763"E | 24°1'27.072"N | 569625.235 | 2657073.702 |  | Bhaisola | Suwasara | MP
[5 empty] | 365 | [16 empty] | WELL, CT, LT
151 |  | 34/2 | DA(-)3 |  |  |  | 57685.428 | 442.805 | 69.5 | 744 | 372 | 151 | 134 | 285 | 162 | 153 | 315 | 75°41'17.3"E | 24°1'24.203"N | 569979.835 | 2656987.189 |  | Bhaisola | Suwasara | MP
[5 empty] | 379 | [16 empty] | CT, WELL, PUMPHOUSE, NALA
152 |  | 34/3 | DA+6 |  |  |  | 58064.428 | 443.481 | 78.5 | 819 | 409.5 | 246 | 221 | 467 | 227 | 221 | 448 | 75°41'30.318"E | 24°1'21.223"N | 570348.035 | 2656897.357 |  | Bhaisola | Suwasara | MP
[5 empty] | 440 | [16 empty] | NALA, 11KV, LT
153 | AP35/0 | 35/0 | DB2+3 | 11° 11' 51"LT |  | 1416 | 58504.428 | 446.279 | 73.72 | 661 | 330.5 | 219 | 155 | 374 | 220 | 130 | 350 | 75°41'45.426"E | 24°1'17.765"N | 570775.331 | 2656793.108 |  | Tarnod | Suwasara | MP
[5 empty] | 221 | [16 empty] | NALA, NH752D
154 | AP36/0 | 36/0 | DC2+0 | 22° 26' 05"RT |  | 221 | 58725.428 | 445.52 | 70.72 | 616 | 308 | 77 | 163 | 240 | 89 | 173 | 262 | 75°41'53.23"E | 24° 1'17.40"N | 570996.14 | 2656783.42 |  | Tarnod | Suwasara | MP
[5 empty] | 395 | [16 empty] | CART TRACK, LT LINE, WELL, NALA, ORANGE GARDEN
155 |  | 36/1 | DA+0 |  |  |  | 59120.428 | 451.591 | 72.5 | 751 | 375.5 | 232 | 176 | 408 | 222 | 177 | 399 | 75°42'5.888"E | 24°1'11.94"N | 571354.287 | 2656616.808 |  | Tarnod | Suwasara | MP
[5 empty] | 356 | [16 empty] | CART TRACK
156 |  | 36/2 | DA+0 |  |  |  | 59476.428 | 451.993 | 72.5 | 760 | 380 | 181 | 204 | 385 | 180 | 204 | 384 | 75°42'17.287"E | 24°1'7.005"N | 571677.069 | 2656466.649 |  | Chapa_khedi | Suwasara | MP
[5 empty] | 404 | [16 empty] | CART TRACK, LT LINE END, WELL, ORANGE GARDEN
157 |  | 36/3 | DA+0 |  |  |  | 59880.428 | 451.707 | 72.5 | 784 | 392 | 201 | 163 | 364 | 202 | 171 | 373 | 75°42'30.223"E | 24°1'1.405"N | 572043.373 | 2656296.245 |  | Chapa_khedi | Suwasara | MP
[5 empty] | 380 | [16 empty] | 11 KV LINE, BARGAD TREE, CART TRACK
158 |  | 36/4 | DA+3 |  |  |  | 60260.428 | 453.658 | 75.5 | 840 | 420 | 218 | 211 | 429 | 210 | 218 | 428 | 75°42'42.39"E | 24°0'56.137"N | 572387.916 | 2656135.964 |  | Chapa_khedi | Suwasara | MP
[5 empty] | 460 | [16 empty] | CART TRACK, LT LINE, WELL, NALA, 11 KV LINE
159 |  | 36/5 | DA+6 |  |  |  | 60720.428 | 454.814 | 78.5 | 840 | 420 | 250 | 209 | 459 | 244 | 204 | 448 | 75°42'57.118"E | 24°0'49.76"N | 572804.995 | 2655941.939 |  | Chapa_khedi | Suwasara | MP
[5 empty] | 380 | [16 empty] | NALA
160 |  | 36/6 | DA(-)1.5 |  |  |  | 61100.428 | 458.852 | 71 | 793 | 396.5 | 171 | 155 | 326 | 177 | 171 | 348 | 75°43'9.284"E | 24°0'44.491"N | 573149.538 | 2655781.658 |  | Chapa_khedi | Suwasara | MP
[5 empty] | 413 | [16 empty] | CART TRACK, WELL, HUT
161 |  | 36/7 | DA+3 |  |  |  | 61513.428 | 464.541 | 75.5 | 826 | 413 | 259 | 221 | 480 | 244 | 217 | 461 | 75°43'22.506"E | 24°0'38.765"N | 573524.002 | 2655607.458 |  | Chapa_khedi | Suwasara | MP
[5 empty] | 413 | [16 empty] | NALA
162 |  | 36/8 | DA+0 |  |  |  | 61926.428 | 464.789 | 72.5 | 840 | 420 | 193 | 136 | 329 | 197 | 160 | 357 | 75°43'35.728"E | 24°0'33.038"N | 573898.466 | 2655433.257 |  | Khejdiya_bhup | Suwasara | MP
[5 empty] | 427 | [16 empty] | LT LINE, 11 KV LINE, METAL ROAD, WELL
163 | AP37/0 | 37/0 | DD45+12 | 41° 25' 41"LT |  | 3628 | 62353.428 | 468.46 | 82.72 | 647 | 323.5 | 291 | 148 | 439 | 269 | 127 | 396 | 75°43'49.398"E | 24°0'27.117"N | 574285.623 | 2655253.152 |  | Khejdiya_bhup | Suwasara | MP
[5 empty] | 220 | [16 empty] | 220 KV BAROD SUWASARA MPPTCL (T301-302)
164 | AP38/0 | 38/0 | DD45+9 | 37° 39' 42"RT |  | 220 | 62573.428 | 468.335 | 79.72 | 650 | 325 | 73 | 273 | 346 | 94 | 255 | 349 | 75°43'56.877"E | 24°0'29.111"N | 574496.585 | 2655315.563 |  | Khejdiya_bhup | Suwasara | MP
[5 empty] | 430 | [16 empty] | WELL, CART TRACK
165 |  | 38/1 | DA(-)3 |  |  |  | 63003.428 | 468.902 | 69.5 | 774 | 387 | 158 | 149 | 307 | 177 | 157 | 334 | 75°44'11.039"E | 24°0'23.991"N | 574897.535 | 2655160.194 |  | Khejdiya_bhup | Suwasara | MP
[5 empty] | 344 | [16 empty] | CART TRACK
166 |  | 38/2 | DA+0 |  |  |  | 63347.428 | 469.53 | 72.5 | 717 | 358.5 | 195 | 191 | 386 | 188 | 190 | 378 | 75°44'22.368"E | 24°0'19.896"N | 575218.294 | 2655035.899 |  | Borkhedi | Suwasara | MP
[5 empty] | 373 | [16 empty] | CART TRACK, LT LINE
167 |  | 38/3 | DA(-)3 |  |  |  | 63720.428 | 471.87 | 69.5 | 762 | 381 | 183 | 157 | 340 | 184 | 169 | 353 | 75°44'34.653"E | 24°0'15.454"N | 575566.095 | 2654901.126 |  | Borkhedi | Suwasara | MP
[5 empty] | 389 | [16 empty] | CART TRACK, 11 KV LINE, NALA, WELL
168 |  | 38/4 | DA+3 |  |  |  | 64109.428 | 472.761 | 75.5 | 833 | 416.5 | 233 | 196 | 429 | 221 | 205 | 426 | 75°44'47.464"E | 24°0'10.822"N | 575928.814 | 2654760.571 |  | Borkhedi | Suwasara | MP
[5 empty] | 444 | [16 empty] | LT LINE, 11 KV LINE, METAL ROAD, NALA, SAMADHI
169 |  | 38/5 | DA+6 |  |  |  | 64553.428 | 475.157 | 78.5 | 752 | 376 | 249 | 203 | 452 | 241 | 188 | 429 | 75°45'2.086"E | 24°0'5.534"N | 576342.818 | 2654600.144 | Raised Chimney | Borkhedi | Suwasara | MP | 2 | 1 | 0 | 1
[5 empty] | 308 | [16 empty] | 11 KV LINE, POND, LT LINE, CART TRACK, ORANGE GARDEN
170 |  | 38/6 | DA(-)3 |  |  |  | 64861.428 | 477.117 | 69.5 | 653 | 326.5 | 105 | 133 | 238 | 121 | 146 | 267 | 75°45'12.23"E | 24°0'1.866"N | 576630.009 | 2654488.856 |  | Borkhedi | Suwasara | MP
[5 empty] | 345 | [16 empty] | ORANGE GARDEN, NALA, CART TRACK
171 |  | 38/7 | DA+0 |  |  |  | 65206.428 | 480.413 | 72.5 | 770 | 385 | 212 | 173 | 385 | 200 | 186 | 386 | 75°45'23.591"E | 23°59'57.757"N | 576951.701 | 2654364.2 |  | Borkhedi | Suwasara | MP
[5 empty] | 425 | [16 empty] | NALA, CT, 11KV
172 |  | 38/8 | DA+6 |  |  |  | 65631.428 | 482.346 | 78.5 | 837 | 418.5 | 253 | 217 | 470 | 241 | 214 | 455 | 75°45'37.587"E | 23°59'52.695"N | 577347.989 | 2654210.638 |  | Borkhedi | Suwasara | MP
[5 empty] | 412 | [16 empty] | ORANGE GARDEN, WELL
173 | AP39/0 | 39/0 | DC1+0 | 17° 32' 52"RT |  | 3470 | 66043.428 | 486.321 | 70.72 | 811 | 405.5 | 196 | 156 | 352 | 200 | 170 | 370 | 75°45'51.149"E | 23°59'47.789"N | 577732.024 | 2654061.823 |  | Borkhedi | Suwasara | MP
[5 empty] | 399 | [16 empty] | Metal road
174 |  | 39/1 | DA+3 |  |  |  | 66442.428 | 491.543 | 75.5 | 819 | 409.5 | 244 | 235 | 479 | 231 | 228 | 459 | 75°46'2.117"E | 23°59'39.617"N | 578043.289 | 2653812.193 |  | Nipaniya(Devgarh) | Dag | RJ
[5 empty] | 420 | [16 empty] | 11kV line & Nala
175 |  | 39/2 | DA+0 |  |  |  | 66862.428 | 489.733 | 72.5 | 787 | 393.5 | 186 | 175 | 361 | 194 | 178 | 372 | 75°46'13.661"E | 23°59'31.016"N | 578370.936 | 2653549.424 |  | Nipaniya(Devgarh) | Dag | RJ
[5 empty] | 367 | [16 empty] | Nala
176 |  | 39/3 | DA+0 |  |  |  | 67229.428 | 491.245 | 72.5 | 721 | 360.5 | 193 | 151 | 344 | 190 | 159 | 349 | 75°46'23.749"E | 23°59'23.499"N | 578657.237 | 2653319.814 |  | Nipaniya(Devgarh) | Dag | RJ
[5 empty] | 354 | [16 empty] | Cart track
177 |  | 39/4 | DA+0 |  |  |  | 67583.428 | 495.569 | 72.5 | 753 | 376.5 | 203 | 221 | 424 | 195 | 214 | 409 | 75°46'33.478"E | 23°59'16.249"N | 578933.396 | 2653098.337 |  | Nipaniya(Devgarh) | Dag | RJ
[5 empty] | 399 | [16 empty] | Cart track
178 |  | 39/5 | DA+0 |  |  |  | 67982.428 | 491.707 | 72.5 | 774 | 387 | 179 | 209 | 388 | 186 | 202 | 388 | 75°46'44.445"E | 23°59'8.077"N | 579244.661 | 2652848.707 |  | Nipaniya(Devgarh) | Dag | RJ
[5 empty] | 375 | [16 empty] | LT line
179 |  | 39/6 | DC2+0 | TPT |  |  | 68357.428 | 488.049 | 70.72 | 755 | 377.5 | 167 | 206 | 373 | 174 | 201 | 375 | 75°46'54.751"E | 23°59'0.396"N | 579537.203 | 2652614.092 |  | Nipaniya(Devgarh) | Dag | RJ
[5 empty] | 380 | [16 empty] | 11kV line
180 |  | 39/7 | DA+0 |  |  |  | 68737.428 | 485.3 | 72.5 | 785 | 392.5 | 175 | 207 | 382 | 180 | 206 | 386 | 75°47'5.194"E | 23°58'52.613"N | 579833.645 | 2652376.349 |  | PeepalyaKhurd | Dag | RJ
[5 empty] | 405 | [16 empty] | 11kV line
181 |  | 39/8 | DA+3 |  |  |  | 69142.428 | 481.558 | 75.5 | 825 | 412.5 | 199 | 225 | 424 | 200 | 221 | 421 | 75°47'16.324"E | 23°58'44.317"N | 580149.591 | 2652122.965 |  | PatLai | Dag | RJ
420
182 |  | 39/9 | DA+3 |  |  |  | 69562.428 | 478.638 | 75.5 | 819 | 409.5 | 195 | 231 | 426 | 200 | 222 | 422 | 75°47'27.866"E | 23°58'35.714"N | 580477.238 | 2651860.196 |  | PatLai | Dag | RJ
[5 empty] | 399 | [16 empty] | 11kV line
183 |  | 39/10 | DA+0 |  |  |  | 69961.428 | 475.78 | 72.5 | 779 | 389.5 | 168 | 184 | 352 | 179 | 186 | 365 | 75°47'38.83"E | 23°58'27.541"N | 580788.502 | 2651610.565 |  | PatLai | Dag | RJ
[5 empty] | 380 | [16 empty] | 11kV line, LT line & Cart track
184 |  | 39/11 | DA+3 |  |  |  | 70341.428 | 473.953 | 75.5 | 795 | 397.5 | 197 | 220 | 417 | 195 | 217 | 412 | 75°47'49.272"E | 23°58'19.757"N | 581084.945 | 2651372.822 |  | PatLai | Dag | RJ
[5 empty] | 415 | [16 empty] | 11kV line & Nala
185 | AP40/0 | 40/0 | DC1+0 | 16° 39' 6"RT |  | 4713 | 70756.428 | 474.642 | 70.72 | 815 | 407.5 | 196 | 175 | 371 | 200 | 184 | 384 | 75°48'0.682"E | 23°58'11.25"N | 581408.913 | 2651113.004 |  | PatLai | Dag | RJ
[5 empty] | 400 | [16 empty] | Metal road & 11kV line
186 |  | 40/1 | DA+3 |  |  |  | 71156.428 | 476.332 | 75.5 | 792 | 396 | 226 | 201 | 427 | 218 | 199 | 417 | 75°48'8.657"E | 23°58'0.505"N | 581636.16 | 2650783.825 |  | PatLai | Dag | RJ
[5 empty] | 392 | [16 empty] | LT line
187 |  | 40/2 | DA+0 |  |  |  | 71548.428 | 478.562 | 72.5 | 779 | 389.5 | 192 | 210 | 402 | 194 | 205 | 399 | 75°48'16.471"E | 23°57'49.975"N | 581858.862 | 2650461.229 |  | PatLai | Dag | RJ
[5 empty] | 387 | [16 empty] | Metal road, Cart track & Nala
188 |  | 40/3 | DA+0 |  |  |  | 71935.428 | 475.59 | 72.5 | 733 | 366.5 | 177 | 178 | 355 | 183 | 177 | 360 | 75°48'24.186"E | 23°57'39.579"N | 582078.723 | 2650142.748 |  | ParthiGarh | Dag | RJ
346
189 | AP41/0 | 41/0 | DD45+0 | 41° 47' 29"LT |  | 1525 | 72281.428 | 474.76 | 70.72 | 746 | 373 | 168 | 168 | 336 | 170 | 178 | 348 | 75°48'31.085"E | 23°57'30.282"N | 582275.362 | 2649857.906 |  | ParthiGarh | Dag | RJ
[5 empty] | 400 | [16 empty] | 33kV line, Nala, Metal road, CT & LT line
190 |  | 41/1 | DA+6 |  |  |  | 72681.428 | 474.81 | 78.5 | 818 | 409 | 232 | 240 | 472 | 223 | 231 | 454 | 75°48'44.822"E | 23°57'27.153"N | 582664.164 | 2649763.92 |  | ParthiGarh | Dag | RJ
[5 empty] | 418 | [16 empty] | 11kV line, Orange garden, Well, Pipal Tree, Bargad Tree, Pumphouse, 11kV TF & Nala
191 |  | 41/2 | DA(-)1.5 |  |  |  | 73099.428 | 476.487 | 71 | 769 | 384.5 | 179 | 153 | 332 | 188 | 160 | 348 | 75°48'59.176"E | 23°57'23.884"N | 583070.461 | 2649665.705 |  | ParthiGarh | Dag | RJ
[5 empty] | 351 | [16 empty] | Nala, Well, Bargad Tree
192 |  | 41/3 | DA+1.5 |  |  |  | 73450.428 | 477.261 | 74 | 780 | 390 | 198 | 200 | 398 | 192 | 204 | 396 | 75°49'11.229"E | 23°57'21.138"N | 583411.635 | 2649583.233 |  | ParthiGarh | Dag | RJ
[5 empty] | 429 | [16 empty] | Metal road, Well, Bargad Tree & Nala
193 |  | 41/4 | DA+3 |  |  |  | 73879.428 | 478.635 | 75.5 | 840 | 420 | 230 | 213 | 443 | 226 | 211 | 437 | 75°49'25.961"E | 23°57'17.782"N | 583828.624 | 2649482.433 |  | Pipalya Kalan | Dag | RJ
[5 empty] | 411 | [16 empty] | 11kV line, Well, Nala
194 |  | 41/5 | DA+0 |  |  |  | 74290.428 | 480.441 | 72.5 | 792 | 396 | 199 | 151 | 350 | 201 | 163 | 364 | 75°49'40.074"E | 23°57'14.566"N | 584228.118 | 2649385.863 |  | Pipalya Kalan | Dag | RJ
[5 empty] | 381 | [16 empty] | 11kV line, Well, Pipal Tree, LT End, CT & Metal road
195 |  | 41/6 | DA+6 |  |  |  | 74671.428 | 481.366 | 78.5 | 840 | 420 | 231 | 215 | 446 | 219 | 220 | 439 | 75°49'53.157"E | 23°57'11.585"N | 584598.452 | 2649296.341 |  | Pipalya Kalan | Dag | RJ
[5 empty] | 459 | [16 empty] | Nala, Well, 11kV
196 |  | 41/7 | DA+6 |  |  |  | 75130.428 | 484.916 | 78.5 | 829 | 414.5 | 245 | 192 | 437 | 241 | 190 | 431 | 75°50'8.919"E | 23°57'7.992"N | 585044.601 | 2649188.493 |  | Dag | Dag | RJ
[5 empty] | 370 | [16 empty] | 11kV line & Cart track
197 |  | 41/8 | DA+3 |  |  |  | 75500.428 | 486.707 | 75.5 | 795 | 397.5 | 179 | 195 | 374 | 181 | 201 | 382 | 75°50'21.624"E | 23°57'5.096"N | 585404.243 | 2649101.556 |  | Dag | Dag | RJ
[5 empty] | 425 | [16 empty] | 11kV line, Well, Nala, House & Cart track
198 | AP42/0 | 42/0 | DC1+3 | 21° 35' 50"RT |  | 3644 | 75925.428 | 490.246 | 73.72 | 681 | 340.5 | 231 | 73 | 304 | 226 | 101 | 327 | 75°50'36.229"E | 23°57'1.767"N | 585817.676 | 2649001.616 |  | Dag | Dag | RJ
[5 empty] | 256 | [16 empty] | 132kV S/C Modak-Dag RJVPNL line (T193-194) & 11kV line
199 | AP43/0 | 43/0 | DC1+6 | 21° 27' 46"LT |  | 256 | 76181.428 | 492.833 | 76.72 | 699 | 349.5 | 183 | 223 | 406 | 155 | 223 | 378 | 75°50'43.598"E | 23°56'56.931"N | 586026.87 | 2648854.118 |  | Dag | Dag | RJ
[5 empty] | 443 | [16 empty] | 33kV line, 11kV line, Metal road, SH-19A & Cart track
200 | AP44/0 | 44/0 | DB2+6 | 11° 33' 40"RT |  | 443 | 76624.428 | 492.497 | 76.72 | 894 | 447 | 220 | 240 | 460 | 221 | 237 | 458 | 75°50'58.802"E | 23°56'53.429"N | 586457.283 | 2648749.003 |  | Dag | Dag | RJ
[5 empty] | 451 | [16 empty] | 11kV line & Nala
201 |  | 44/1 | DB1+3 |  |  | 451 | 77075.428 | 492.181 | 73.72 | 871 | 435.5 | 212 | 211 | 423 | 216 | 212 | 428 | 75°51'13.187"E | 23°56'47.086"N | 586865.074 | 2648556.369 |  | Dag | Dag | RJ
[5 empty] | 420 | [16 empty] | 11kV line & Nala
202 |  | 44/2 | DA+3 |  |  |  | 77495.428 | 491.967 | 75.5 | 838 | 419 | 209 | 188 | 397 | 210 | 195 | 405 | 75°51'26.583"E | 23°56'41.179"N | 587244.835 | 2648376.977 |  | Dag | Dag | RJ
[5 empty] | 418 | [16 empty] | Cart track
203 |  | 44/3 | DA+0 |  |  |  | 77913.428 | 499.12 | 72.5 | 767 | 383.5 | 231 | 181 | 412 | 224 | 179 | 403 | 75°51'39.915"E | 23°56'35.299"N | 587622.787 | 2648198.438 |  | Dag | Dag | RJ
[5 empty] | 349 | [16 empty] | 11kV line & Cart track
204 | AP45/0 | 45/0 | DC1+0 | 21° 45' 7"RT |  | 1187 | 78262.428 | 498.148 | 70.72 | 756.015 | 378.0075 | 169 | 216 | 385 | 171 | 213 | 384 | 75051'51.046"E | 23056'30.389"N | 587938.364 | 2648049.365 |  | Dag | Dag | RJ
[5 empty] | 407 | [16 empty] | Orange garden & Nala, CT
205 |  | 45/1 | DA(-)3 |  |  |  | 78669.428 | 498.836 | 69.5 | 730 | 365 | 192 | 147 | 339 | 196 | 152 | 348 | 75052'1.818"E | 23056'22.007"N | 588215.744 | 2647751.524 |  | Ganeshpura | Dag | RJ
323
206 |  | 45/2 | DA+0 |  |  |  | 78992.428 | 498.068 | 72.5 | 742 | 371 | 177 | 184 | 361 | 172 | 192 | 364 | 75052'10.674"E | 23056'15.117"N | 588435.876 | 2647515.153 |  | Ganeshpura | Dag | RJ
[5 empty] | 419 | [16 empty] | 11kV line, WELL, CT & Nala
207 |  | 45/3 | DA+0 |  |  |  | 79411.428 | 503.173 | 72.5 | 821 | 410.5 | 236 | 186 | 422 | 228 | 191 | 419 | 75052'21.419"E | 23056'6.756"N | 588721.434 | 2647208.531 |  | Ganeshpura | Dag | RJ
[5 empty] | 402 | [16 empty] | 11KV, WELL
208 |  | 45/4 | DA+1.5 |  |  |  | 79813.428 | 504.472 | 74 | 804.306 | 402.153 | 216 | 219 | 435 | 212 | 214 | 426 | 75052'31.516"E | 23055'58.898"N | 588995.406 | 2646914.348 |  | Chhaan(Chhaan Dug) | Dag | RJ
[5 empty] | 402.306 | [16 empty] | TAR ROAD
209 | AP45A/0 | 45A/0 | DC2+0 | 24° 2' 43"LT |  | 1953.31 | 80215.734 | 502.71 | 70.72 | 818.306 | 409.153 | 184 | 233 | 417 | 190 | 226 | 416 | 75052'42.557"E | 23055'50.305"N | 589269.587 | 2646619.942 |  | Daryavpura | Dag | RJ
[5 empty] | 416 | [16 empty] | 11KV
210 |  | 45A/1 | DA+1.5 |  |  |  | 80631.734 | 496.255 | 74 | 834.752 | 417.376 | 184 | 217 | 401 | 191 | 215 | 406 | 75052'52.95"E | 23055'42.217"N | 589652.54 | 2646457.451 | Raised Chimney Expected | Daryavpura | Dag | RJ | 2.5 | 1 | 0 | 0.5
418.752
211 | AP46/0 | 46/0 | DD45+0 | 30° 59' 37"LT |  | 834.75 | 81050.486 | 496.24 | 70.72 | 795.752 | 397.876 | 202 | 193 | 395 | 205 | 192 | 397 | 75053'4.931"E | 23055'32.891"N | 590038.026 | 2646293.886 |  | Dag | Dag | RJ
377
212 |  | 46/1 | DA+1.5 |  |  |  | 81427.486 | 494.033 | 74 | 817 | 408.5 | 185 | 279 | 464 | 186 | 262 | 448 | 75053'16.956"E | 23055'32.744"N | 590411.356 | 2646346.365 | Raised Chimney Expected | Dag | Dag | RJ | 1 | 1.5 | 0 | 0
440
213 |  | 46/2 | DA+3 |  |  |  | 81867.486 | 480.38 | 75.5 | 840.28 | 420.14 | 162 | 237 | 399 | 180 | 226 | 406 | 75053'33.154"E | 23055'32.544"N | 590847.072 | 2646407.613 |  | Ghati | Dag | RJ
[5 empty] | 400.28 | [16 empty] | 11kV line, Cart track, WELL
214 | AP46A/0 | 46A/0 | DC1+0 | 15° 18' 60"RT |  | 1217.28 | 82267.766 | 476.429 | 70.72 | 786.28 | 393.14 | 164 | 170 | 334 | 175 | 178 | 353 | 75053'46.452"E | 23055'32.38"N | 591243.455 | 2646463.333 |  | Ghati | Dag | RJ
386
215 |  | 46A/1 | DA+3 |  |  |  | 82653.766 | 477.492 | 75.5 | 806 | 403 | 216 | 274 | 490 | 209 | 253 | 462 | 75053'57.487"E | 23055'32.244"N | 591626.313 | 2646414.186 |  | Ghati | Dag | RJ
[5 empty] | 420 | [16 empty] | 11kV line, Nala & Cart track
216 |  | 46A/2 | DA(-)3 |  |  |  | 83073.766 | 471.289 | 69.5 | 757 | 378.5 | 147 | 167 | 314 | 169 | 168 | 337 | 75054'10.855"E | 23055'32.079"N | 592042.895 | 2646360.71 |  | Ghati | Dag | RJ
[5 empty] | 337 | [16 empty] | Nala
217 |  | 46A/3 | DA(-)3 |  |  |  | 83410.766 | 471.474 | 69.5 | 673.512 | 336.756 | 170 | 126 | 296 | 170 | 141 | 311 | 75054'24.932"E | 23055'31.904"N | 592377.152 | 2646317.802 |  | Ghati | Dag | RJ
[5 empty] | 336.512 | [16 empty] | Cart track, WELL & Nala
218 | AP47/0 | 47/0 | DC1+3 | 15° 21' 6"RT |  | 1479.51 | 83747.278 | 471.993 | 73.72 | 748.512 | 374.256 | 211 | 222 | 433 | 197 | 217 | 414 | 75054'39.466"E | 23055'31.724"N | 592710.926 | 2646274.956 |  | Ghati | Dag | RJ
[5 empty] | 412 | [16 empty] | Nala
219 |  | 47/1 | DA+0 |  |  |  | 84159.278 | 472.109 | 72.5 | 820 | 410 | 191 | 168 | 359 | 196 | 180 | 376 | 75°54'52.877"E | 23°55'26.482"N | 593091.104 | 2646116.183 |  | Dodhi | Dag | RJ
[5 empty] | 408 | [16 empty] | Cart track & Nala
220 |  | 47/2 | DA+6 |  |  |  | 84567.278 | 472.952 | 78.5 | 821 | 410.5 | 240 | 251 | 491 | 229 | 237 | 466 | 75°55'6.156"E | 23°55'21.29"N | 593467.591 | 2645958.952 |  | Dodhi | Dag | RJ
[5 empty] | 413 | [16 empty] | Cart track & Nala
221 |  | 47/3 | DA+0 |  |  |  | 84980.278 | 470.509 | 72.5 | 823 | 411.5 | 163 | 206 | 369 | 177 | 206 | 383 | 75°55'19.599"E | 23°55'16.035"N | 593848.692 | 2645799.794 |  | Chhaan(Chhaan Dug) | Dag | RJ
[5 empty] | 410 | [16 empty] | 11kV line
222 |  | 47/4 | DA+3 |  |  |  | 85390.278 | 467.308 | 75.5 | 816 | 408 | 204 | 212 | 416 | 205 | 209 | 414 | 75°55'32.943"E | 23°55'10.818"N | 594227.024 | 2645641.792 |  | Chhaan(Chhaan Dug) | Dag | RJ
[5 empty] | 406 | [16 empty] | Nala
223 |  | 47/5 | DA+3 |  |  |  | 85796.278 | 465.734 | 75.5 | 817 | 408.5 | 195 | 226 | 421 | 198 | 220 | 418 | 75°55'46.157"E | 23°55'5.651"N | 594601.665 | 2645485.332 |  | Chhaan(Chhaan Dug) | Dag | RJ
[5 empty] | 411 | [16 empty] | 11kV line
224 |  | 47/6 | DA+3 |  |  |  | 86207.278 | 461.972 | 75.5 | 783 | 391.5 | 186 | 215 | 401 | 193 | 207 | 400 | 75°55'59.533"E | 23°55'0.42"N | 594980.92 | 2645326.945 |  | Chhaan(Chhaan Dug) | Dag | RJ
[5 empty] | 372 | [16 empty] | Nala
225 |  | 47/7 | DA+0 |  |  |  | 86579.278 | 459.92 | 72.5 | 758 | 379 | 157 | 175 | 332 | 167 | 181 | 348 | 75°56'11.64"E | 23°54'55.685"N | 595324.188 | 2645183.587 |  | Chhaan(Chhaan Dug) | Dag | RJ
[5 empty] | 386 | [16 empty] | 11kV line & Cart track
226 |  | 47/8 | DA+0 |  |  |  | 86965.278 | 463.284 | 72.5 | 756 | 378 | 212 | 241 | 453 | 206 | 224 | 430 | 75°56'24.202"E | 23°54'50.772"N | 595680.374 | 2645034.834 |  | Chhaan(Chhaan Dug) | Dag | RJ
[5 empty] | 370 | [16 empty] | Cart track
227 |  | 47/9 | DA+0 |  |  |  | 87335.278 | 453.68 | 72.5 | 752 | 376 | 130 | 196 | 326 | 147 | 195 | 342 | 75°56'36.243"E | 23°54'46.062"N | 596021.796 | 2644892.247 |  | Chhaan(Chhaan Dug) | Dag | RJ
[5 empty] | 382 | [16 empty] | 11kV line & Cart track
228 |  | 47/10 | DA+3 |  |  |  | 87717.278 | 449.806 | 75.5 | 766 | 383 | 186 | 152 | 338 | 188 | 165 | 353 | 75°56'48.674"E | 23°54'41.199"N | 596374.291 | 2644745.036 |  | Chhaan(Chhaan Dug) | Dag | RJ
[5 empty] | 384 | [16 empty] | Nala
229 |  | 47/11 | DA+6 |  |  |  | 88101.278 | 453.993 | 78.5 | 766 | 383 | 233 | 208 | 441 | 220 | 203 | 423 | 75°57'1.171"E | 23°54'36.311"N | 596728.632 | 2644597.053 |  | Karnaliya | Badod | MP
[5 empty] | 382 | [16 empty] | 11kV line & Cart track
230 | AP48/0 | 48/0 | DB1+0 | 5° 44' 24"LT |  | 4736 | 88483.278 | 457.088 | 70.72 | 739 | 369.5 | 175 | 157 | 332 | 180 | 164 | 344 | 75°57'13.602"E | 23°54'31.447"N | 597081.153 | 2644449.831 |  | Karnaliya | Badod | MP
[5 empty] | 357 | [16 empty] | NALA, WELL, PIPAL TREE
231 |  | 48/1 | DA+0 |  |  |  | 88840.278 | 460.635 | 72.5 | 708 | 354 | 200 | 165 | 365 | 194 | 168 | 362 | 75°57'25.656"E | 23°54'27.993"N | 597422.687 | 2644345.89 |  | Karnaliya | Badod | MP
[5 empty] | 351 | [16 empty] | LT, BORE, HUT, SAMADHI, CT, 11KV
232 |  | 48/2 | DA(-)1.5 |  |  |  | 89191.278 | 463.934 | 71 | 764 | 382 | 187 | 212 | 399 | 183 | 210 | 393 | 75°57'37.506"E | 23°54'24.596"N | 597758.48 | 2644243.696 |  | Karnaliya | Badod | MP
[5 empty] | 413 | [16 empty] | NALA, WELL, PIPAL TREE, CT, BARGAD TREE
233 |  | 48/3 | DA+3 |  |  |  | 89604.278 | 458.511 | 75.5 | 836 | 418 | 202 | 202 | 404 | 204 | 206 | 410 | 75°57'51.45"E | 23°54'20.599"N | 598153.588 | 2644123.451 |  | Karnaliya | Badod | MP
[5 empty] | 423 | [16 empty] | 11KV, ORANGE GARDEN, LT, CT
234 |  | 48/4 | DA(-)1.5 |  |  |  | 90027.278 | 464.903 | 71 | 813 | 406.5 | 221 | 184 | 405 | 219 | 188 | 407 | 75°58'5.731"E | 23°54'16.505"N | 598558.262 | 2644000.294 |  | Karnaliya | Badod | MP
[5 empty] | 390 | [16 empty] | ORANGE GARDEN, 11KV, METAL ROAD, CT, NALA, WELL
235 |  | 48/5 | DA+0 |  |  |  | 90417.278 | 465.405 | 72.5 | 796 | 398 | 206 | 165 | 371 | 203 | 177 | 380 | 75°58'18.897"E | 23°54'12.73"N | 598931.367 | 2643886.745 |  | Karnaliya | Badod | MP
406
236 |  | 48/6 | DA+3 |  |  |  | 90823.278 | 469.712 | 75.5 | 796 | 398 | 242 | 257 | 499 | 230 | 238 | 468 | 75°58'32.604"E | 23°54'8.8"N | 599319.777 | 2643768.538 |  | Karnaliya | Badod | MP
[5 empty] | 390 | [16 empty] | CT, POND
237 |  | 48/7 | DA(-)1.5 |  |  |  | 91213.278 | 462.941 | 71 | 783 | 391.5 | 133 | 224 | 357 | 153 | 216 | 369 | 75°58'45.77"E | 23°54'5.025"N | 599692.882 | 2643654.989 | Raised Chimney | Gadhi | Badod | MP | 0 | 0 | 1.5 | 2
[5 empty] | 393 | [16 empty] | CT
238 |  | 48/8 | DA+0 |  |  |  | 91606.278 | 456.475 | 72.5 | 819 | 409.5 | 170 | 208 | 378 | 178 | 210 | 388 | 75°58'59.037"E | 23°54'1.22"N | 600068.856 | 2643540.567 |  | Gadhi | Badod | MP
[5 empty] | 426 | [16 empty] | LT, WELL, SAMADHI, CT, NALA, BARGAD TREE, ORANGE GARDEN
239 |  | 48/9 | DA+3 |  |  |  | 92032.278 | 454.559 | 75.5 | 833 | 416.5 | 219 | 231 | 450 | 218 | 223 | 441 | 75°59'13.418"E | 23°53'57.095"N | 600476.4 | 2643416.536 |  | Pipalya Chacha | Badod | MP
[5 empty] | 407 | [16 empty] | LT, NALA
240 | AP49/0 | 49/0 | DB1+0 | 5° 32' 52"RT |  | 3956 | 92439.278 | 452.437 | 70.72 | 811 | 405.5 | 177 | 164 | 341 | 186 | 175 | 361 | 75°59'27.158"E | 23°53'53.154"N | 600865.784 | 2643298.033 |  | Pipalya Chacha | Badod | MP
[5 empty] | 404 | [16 empty] | NALA, WELL, 11KV, METAL ROAD, LT
241 |  | 49/1 | DA+6 |  |  |  | 92843.278 | 453.942 | 78.5 | 822 | 411 | 241 | 251 | 492 | 230 | 239 | 469 | 75°59'40.32"E | 23°53'48.048"N | 601239.1 | 2643143.594 |  | Pipalya Chacha | Badod | MP
[5 empty] | 418 | [16 empty] | CT
242 |  | 49/2 | DA+0 |  |  |  | 93261.278 | 451.646 | 72.5 | 831 | 415.5 | 168 | 189 | 357 | 180 | 195 | 375 | 75°59'53.939"E | 23°53'42.764"N | 601625.352 | 2642983.804 |  | Pipalya Chacha | Badod | MP
[5 empty] | 413 | [16 empty] | WELL, LT, 11KV, NALA
243 |  | 49/3 | DA+3 |  |  |  | 93674.278 | 452.114 | 75.5 | 823 | 411.5 | 224 | 220 | 444 | 220 | 216 | 436 | 76°0'7.394"E | 23°53'37.543"N | 602006.985 | 2642825.925 |  | Pipalya Chacha | Badod | MP
[5 empty] | 410 | [16 empty] | PIPAL TREE
244 |  | 49/4 | DA+0 |  |  |  | 94084.278 | 452.147 | 72.5 | 836 | 418 | 190 | 226 | 416 | 195 | 222 | 417 | 76°0'20.751"E | 23°53'32.36"N | 602385.845 | 2642669.192 |  | Pipalya Chacha | Badod | MP
[5 empty] | 426 | [16 empty] | NALA
245 |  | 49/5 | DA+0 |  |  |  | 94510.278 | 449.67 | 72.5 | 823 | 411.5 | 201 | 167 | 368 | 205 | 176 | 381 | 76°0'34.629"E | 23°53'26.975"N | 602779.49 | 2642506.344 |  | Gangapur | Badod | MP
[5 empty] | 397 | [16 empty] | LT, NALA, 11KV
246 |  | 49/6 | DA+6 |  |  |  | 94907.278 | 449.78 | 78.5 | 801 | 400.5 | 231 | 108 | 339 | 222 |  | 358 | 76°0'47.562"E | 23°53'21.955"N | 603146.337 | 2642354.581 |  | Gyasari | Badod | MP
[5 empty] | 404 | [16 empty] | METAL ROAD
247 | AP50/0 | 50/0 | DC2+18 | 20° 9' 8"LT |  | 2872 | 95311.278 | 455.992 | 88.72 | 628 | 314 | 297 | 166 | 463 | 269 | 136 | 405 | 76°1'0.735"E | 23°53'16.843"N | 603519.994 | 2642200.001 |  | Gyasari | Badod | MP
[5 empty] | 224 | [16 empty] | 220KV S/C RUM-O2P-RTL T12-T13
248 | AP51/0 | 51/0 | DD45+9 | 31° 40' 27"RT |  | 224 | 95535.278 | 460.381 | 79.72 | 646 | 323 | 58 | 269 | 327 | 88 | 250 | 338 | 76°1'8.64"E | 23°53'16.495"N | 603743.631 | 2642190.931 |  | Gyasari | Badod | MP
[5 empty] | 422 | [16 empty] | NALA
249 |  | 51/1 | DA+0 |  |  |  | 95957.278 | 458.358 | 72.5 | 765 | 382.5 | 154 | 174 | 328 | 174 | 173 | 347 | 76°1'20.95"E | 23°53'8.742"N | 604093.499 | 2641954.973 |  | Gyasari | Badod | MP
[5 empty] | 343 | [16 empty] | SAMADHI, 11KV, CT
250 |  | 51/2 | DA(-)3 |  |  |  | 96300.278 | 461.041 | 69.5 | 703 | 351.5 | 170 | 189 | 359 | 171 | 186 | 357 | 76°1'30.956"E | 23°53'2.44"N | 604377.871 | 2641763.187 |  | Gyasari | Badod | MP
[5 empty] | 360 | [16 empty] | 11KV, LT, NALA
251 |  | 51/3 | DA(-)3 |  |  |  | 96660.278 | 459.485 | 69.5 | 699.682 | 349.841 | 171 | 121 | 292 | 175 | 138 | 313 | 7601'41.457"E | 23052'55.825"N | 604676.334 | 2641561.897 |  | Shyamgarh | Badod | MP
[5 empty] | 339.682 | [16 empty] | WELL, 11KV
252 | AP52/0 | 52/0 | DC2+0 | 24° 40' 51"LT |  | 1464.682 | 96999.96 | 464.21 | 70.72 | 748.682 | 374.341 | 219 | 152 | 371 | 203 | 168 | 371 | 7601'51.365"E | 23052'49.584"N | 604957.957 | 2641371.965 |  | Shyamgarh | Badod | MP
[5 empty] | 409 | [16 empty] | LT LINE/METAL ROAD/WELL
253 |  | 52/1 | DA+1.5 |  |  |  | 97408.96 | 472.854 | 74 | 800.063 | 400.0315 | 258 | 197 | 455 | 242 | 197 | 439 | 7602'5.618"E | 23052'47.335"N | 605361.563 | 2641305.759 |  | Shyamgarh | Badod | MP
[5 empty] | 391.063 | [16 empty] | CART TRACK
254 | AP53/0 | 53/0 | DB2+3 | 11° 13' 26"RT |  | 800.063 | 97800.023 | 471.117 | 73.72 | 777.138 | 388.569 | 195 | 251 | 446 | 195 | 233 | 428 | 7602'19.245"E | 23052'45.185"N | 605747.468 | 2641242.456 |  | Shyamgarh | Badod | MP
[5 empty] | 386.075 | [16 empty] | 11KV LINE/CART TRACK/SCHOOL/SCHOOL/CRICKET PITCH/CART TRACK/11KV LINE
255 | AP53A/0 | 53A/0 | DB1(-)1.5 | 4° 32' 26"RT |  | 386.075 | 98186.098 | 465.359 | 70.72 | 758.962 | 379.481 | 136 | 203 | 339 | 155 | 198 | 353 | 7602'31.992"E | 23052'40.695"N | 606109 | 2641107 |  | Saranga_khedi | Badod | MP
[5 empty] | 372.887 | [16 empty] | MUMBAI-MANMAD BIJWASAN GAS PIPE LINE(BPCL)
256 | AP53B/0 | 53B/0 | DB2(-)1.5 | 14° 18' 4"RT |  | 372.887 | 98558.985 | 462.537 | 70.72 | 705.887 | 352.9435 | 170 | 90 | 260 | 176 | 119 | 295 | 7602'43.891"E | 23052'35.475"N | 606446.73 | 2640948.939 |  | Saranga_khedi | Badod | MP
[5 empty] | 333 | [16 empty] | CART TRACK
257 |  | 53B/1 | DA+3 |  |  |  | 98891.985 | 469.401 | 75.5 | 690.142 | 345.071 | 243 | 100 | 343 | 215 | 129 | 344 | 7602'52.936"E | 23052'28.544"N | 606704.12 | 2640737.658 |  | Saranga_khedi | Badod | MP
[5 empty] | 357.142 | [16 empty] | 2 NOS. 11KV LINE
258 | AP54/0 | 54/0 | DC2+18 | 28° 2' 4"RT |  | 690.142 | 99249.127 | 467.149 | 88.72 | 591.313 | 295.6565 | 259 | 199 | 458 | 230 | 155 | 385 | 7603'2.636"E | 23052'21.111"N | 606980.17 | 2640511.06 |  | Maharundi | Badod | MP
[5 empty] | 234.171 | [16 empty] | 220KV DC BADOD-NALKHEDA TL(MPPTCL)
259 | AP55/0 | 55/0 | DD60+9 | 48° 36' 23"LT |  | 234.17 | 99483.298 | 467.785 | 79.72 | 586.171 | 293.0855 | 36 | 193 | 229 | 80 | 187 | 267 | 76d3'5.759"E | 23d52'14.06"N | 607070.102 | 2640294.846 | RC=1M | Maharundi | Badod | MP | 1 | 1 | 1 | 1
[5 empty] | 352 | [16 empty] | LT LINE/CART TRACK
260 |  | 55/1 | DA+6 |  |  |  | 99835.298 | 469.093 | 78.5 | 705 | 352.5 | 159 | 118 | 277 | 166 | 140 | 306 | 76d3'17.509"E | 23d52'10.289"N | 607403.304 | 2640181.355 |  | Maharundi | Badod | MP
353
261 |  | 55/2 | DA+3 |  |  |  | 100188.298 | 481.401 | 75.5 | 705.606 | 352.803 | 236 | 106 | 342 | 214 | 132 | 346 | 76d3'29.292"E | 23d52'6.508"N | 607737.453 | 2640067.541 |  | Maharundi | Badod | MP
[5 empty] | 352.606 | [16 empty] | TAR ROAD/CART TRACK/11KV LINE
262 | AP56/0 | 56/0 | DB2+9 | 10° 8' 39"LT |  | 1057.61 | 100540.904 | 486.487 | 79.72 | 620.606 | 310.303 | 247 | 117 | 364 | 221 | 126 | 347 | 76d3'41.061"E | 23d52'2.731"N | 608071.229 | 2639953.855 | Benching / Raised Chimney Expected | Barda_Barkheda | Badod | MP | 0.5 | 2 | 1 | 0
[5 empty] | 268 | [16 empty] | 11KV LINE
263 |  | 56/1 | DB1+18 |  |  | 268 | 100808.904 | 479.29 | 88.72 | 574 | 287 | 151 | 340 | 491 | 143 | 261 | 404 | 76d3'50.417"E | 23d52'1.353"N | 608336.17 | 2639913.479 | Benching / Raised Chimney Expected | Barda_Barkheda | Badod | MP | 0 | 0 | 2 | 3
[5 empty] | 306 | [16 empty] | 11KV LINE/33KV LINE/METAL ROAD/11KV LINE
264 |  | 56/2 | DB1+6 |  |  | 306 | 101114.904 | 466.95 | 76.72 | 603 | 301.5 | -33 | 77 | 44 | 47 | 102 | 149 | 76d4'1.099"E | 23d51'59.781"N | 608638.677 | 2639867.377 |  | Barda_Barkheda | Badod | MP
[5 empty] | 297 | [16 empty] | WELL
265 |  | 56/3 | DA(-)3 |  |  |  | 101411.904 | 485.7 | 69.5 | 711.403 | 355.7015 | 221 | 185 | 406 | 196 | 193 | 389 | 76d4'11.466"E | 23d51'58.254"N | 608932.287 | 2639822.632 | Benching / Raised Chimney Expected | Barda_Barkheda | Badod | MP | 0 | 3 | 2.5 | 1
[5 empty] | 414.403 | [16 empty] | NALA/LT LINE/WELL/CEMETERY AREA
266 | AP57/0 | 57/0 | DB2+0 | 8° 34' 46"RT |  | 711.4 | 101826.307 | 486.929 | 70.72 | 746.403 | 373.2015 | 230 | 349 | 579 | 223 | 278 | 501 | 76d4'25.932"E | 23d51'56.123"N | 609341.96 | 2639760.199 | Benching / Raised Chimney Expected | Barda_Barkheda | Badod | MP | 0.5 | 0 | 1 | 1
[5 empty] | 332 | [16 empty] | WELL/NALA/WELL/NALA
267 |  | 57/1 | DB1+3 |  |  | 332 | 102158.307 | 457.348 | 73.72 | 742 | 371 | -16 | 202 | 186 | 56 | 203 | 259 | 76d4'37.115"E | 23d51'52.845"N | 609659.036 | 2639661.778 |  | Barda_Barkheda | Badod | MP
[5 empty] | 410 | [16 empty] | CART TRACK
268 |  | 57/2 | DA+1.5 |  |  |  | 102568.307 | 459.582 | 74 | 824 | 412 | 209 | 170 | 379 | 208 | 181 | 389 | 76d4'50.925"E | 23d51'48.797"N | 610050.606 | 2639540.233 |  | Barda_Barkheda | Badod | MP
[5 empty] | 414 | [16 empty] | NALA/LT LINE/WELL/CART TRACK/11KV LINE
269 |  | 57/3 | DA+3 |  |  |  | 102982.307 | 465.57 | 75.5 | 821 | 410.5 | 245 | 235 | 480 | 234 | 226 | 460 | 76d5'4.869"E | 23d51'44.708"N | 610445.996 | 2639417.503 |  | Barda_Barkheda | Badod | MP
[5 empty] | 407 | [16 empty] | CART TRACK/WELL/SAMADHI/11KV LINE
270 |  | 57/4 | DA+0 |  |  |  | 103389.307 | 462.423 | 72.5 | 828.884 | 414.442 | 173 | 178 | 351 | 182 | 188 | 370 | 76d5'18.577"E | 23d51'40.689"N | 610834.701 | 2639296.847 |  | Barda_Barkheda | Badod | MP
[5 empty] | 421.884 | [16 empty] | CART TRACK/LT LINE/LOW LAND
271 | AP58/0 | 58/0 | DC1+6 | 16° 14' 41"RT |  | 1652.88 | 103811.191 | 463.252 | 76.72 | 954.078 | 477.039 | 245 | 254 | 499 | 236 | 257 | 493 | 76d5'32.786"E | 23d51'36.522"N | 611237.62 | 2639171.78 | Benching Expected | Barda_Barkheda | Badod | MP
[5 empty] | 532.192 | [16 empty] | Lake
272 | AP59/0 | 59/0 | DD45+18 | 24° 14' 33"LT |  | 532.192 | 104343.383 | 455.45 | 88.72 | 947.192 | 473.596 | 284 | 314 | 598 | 282 | 280 | 562 | 76°5'48.395"E | 23°51'26.863"N | 611681.464 | 2638878.126 | Raised Chimney | Barda_Barkheda | Badod | MP | 0 | 1 | 1 | 2.5
[5 empty] | 415 | [16 empty] | 33KkV line, Nala
273 |  | 59/1 | DA+9 |  |  |  | 104758.383 | 444.124 | 81.5 | 764.861 | 382.4305 | 102 | 221 | 323 | 137 | 207 | 344 | 76d6'2.856"E | 23d51'24.593"N | 612091.074 | 2638811.456 |  | Semalkhedi | Nalkheda | MP
[5 empty] | 350 | [16 empty] | 33kV lines, 11kV lines
274 | AP60/0 | 60/0 | DC2+6 | 26° 15' 27"RT |  | 765 | 105108.383 | 439.64 | 70.72 | 598.874 | 299.437 | 129 | 121 | 250 | 144 | 123 | 267 | 76d6'15.048"E | 23d51'22.678"N | 612436.39 | 2638755.25 |  | Semalkhedi | Nalkheda | MP
[5 empty] | 249.013 | [16 empty] | NH-552G, 33kV line, 11kV line, Nala
275 | AP61/0 | 61/0 | DB1+9 | 2° 56' 37"LT |  | 249.013 | 105357.396 | 436.98 | 70.72 | 600.013 | 300.0065 | 128 | 176 | 304 | 127 | 176 | 303 | 76d6'22.173"E | 23d51'17.925"N | 612639.11 | 2638610.64 |  | Semalkhedi | Nalkheda | MP
[5 empty] | 351 | [16 empty] | Nala, LT line, Well, Cart Track
276 |  | 61/1 | DA+6 |  |  |  | 105708.396 | 439.892 | 78.5 | 658.26 | 329.13 | 175 | 99 | 274 | 176 | 121 | 297 | 76d6'32.579"E | 23d51'11.709"N | 612934.948 | 2638421.745 |  | Semalkhedi | Nalkheda | MP
[5 empty] | 307.261 | [16 empty] | Metal road, 11kV line
277 | AP62/0 | 62/0 | DB1+12 | 2° 14' 43"LT |  | 658.261 | 106015.657 | 441.3 | 82.72 | 557.818 | 278.909 | 209 | 182 | 391 | 187 | 152 | 339 | 76°6'41.687"E | 23°51'6.267"N | 613193.92 | 2638256.39 |  | Semalkhedi | Nalkheda | MP
[5 empty] | 250.557 | [16 empty] | 132 KV DC CKT-1 AGAR -SUSNER , CKT-2 AGAR - NALKHEDA OHTL OHTL, 33kV lines, 11kV line, Cart track
278 | AP63/0 | 63/0 | DC2+12 | 24° 32' 28"LT |  | 250.557 | 106266.214 | 436.106 | 82.72 | 673.557 | 336.7785 | 69 | 324 | 393 | 99 | 286 | 385 | 76°6'49.297"E | 23°51'2.1"N | 613410.22 | 2638129.927 |  | Semalkhedi | Nalkheda | MP
[5 empty] | 423 | [16 empty] | Nala
279 |  | 63/1 | DA(-)3 |  |  |  | 106689.214 | 429.568 | 69.5 | 762 | 381 | 100 | 163 | 263 | 139 | 166 | 305 | 76°7'4.161"E | 23°51'0.609"N | 613831.075 | 2638087.383 |  | Semalkhedi | Nalkheda | MP
[5 empty] | 339 | [16 empty] | Cart Track
280 |  | 63/2 | DA(-)3 |  |  |  | 107028.214 | 430.538 | 69.5 | 679 | 339.5 | 176 | 194 | 370 | 174 | 186 | 360 | 76°7'16.074"E | 23°50'59.414"N | 614168.356 | 2638053.288 |  | Semalkhedi | Nalkheda | MP
[5 empty] | 340 | [16 empty] | Abandoned 11kV line, Cart track
281 |  | 63/3 | DA(-)3 |  |  |  | 107368.214 | 426.827 | 69.5 | 679.061 | 339.5305 | 146 | 159 | 305 | 155 | 163 | 318 | 76°7'28.021"E | 23°50'58.216"N | 614506.632 | 2638019.092 |  | Borkhedi_Saloki | Nalkheda | MP
339.061
282 | AP64/0 | 64/0 | DD45+0 | 41° 42' 42"RT |  | 1441.061 | 107707.275 | 425.402 | 70.72 | 722.061 | 361.0305 | 180 | 202 | 382 | 177 | 199 | 376 | 76°7'39.935"E | 23°50'57.02"N | 614843.974 | 2637984.991 |  | Borkhedi_Saloki | Nalkheda | MP
[5 empty] | 383 | [16 empty] | Nala
283 |  | 64/1 | DA+6 |  |  |  | 108090.275 | 417.627 | 78.5 | 783 | 391.5 | 182 | 263 | 445 | 185 | 243 | 428 | 76°7'49.004"E | 23°50'47.775"N | 615102.804 | 2637702.686 |  | Borkhedi_Saloki | Nalkheda | MP
[5 empty] | 400 | [16 empty] | Orange garden, Well, Cart track
284 | AP65/0 | 65/0 | DC2+0 | 22° 30' 31"LT |  | 783 | 108490.275 | 411.959 | 70.72 | 786 | 393 | 137 | 197 | 334 | 158 | 196 | 354 | 76°7'58.47"E | 23°50'38.125"N | 615372.954 | 2637408.036 |  | Borkhedi_Saloki | Nalkheda | MP
[5 empty] | 386 | [16 empty] | 11kV line, Nala, Well
285 |  | 65/1 | DA(-)1.5 |  |  |  | 108876.275 | 412.71 | 71 | 779 | 389.5 | 189 | 169 | 358 | 191 | 178 | 369 | 76°8'10.791"E | 23°50'32.736"N | 615722.859 | 2637245.056 |  | Borkhedi_Saloki | Nalkheda | MP
[5 empty] | 393 | [16 empty] | Nala
286 |  | 65/2 | DA+0 |  |  |  | 109269.275 | 416.226 | 72.5 | 815 | 407.5 | 224 | 174 | 398 | 216 | 186 | 402 | 76°8'23.335"E | 23°50'27.248"N | 616079.11 | 2637079.121 |  | Borkhedi_Saloki | Nalkheda | MP
[5 empty] | 422 | [16 empty] | Nala, Cart track, Well
287 |  | 65/3 | DA+6 |  |  |  | 109691.275 | 417.548 | 78.5 | 830 | 415 | 249 | 242 | 491 | 237 | 230 | 467 | 76°8'36.805"E | 23°50'21.355"N | 616461.649 | 2636900.941 |  | Suigaon | Nalkheda | MP
408
288 |  | 65/4 | DA(-)1.5 |  |  |  | 110099.275 | 417.939 | 71 | 778 | 389 | 167 | 195 | 362 | 179 | 193 | 372 | 76°8'49.827"E | 23°50'15.658"N | 616831.497 | 2636728.673 |  | Suigaon | Nalkheda | MP
[5 empty] | 370 | [16 empty] | 11kV line, LT line, Metal road, Well, Nala
289 |  | 65/5 | DA(-)3 |  |  |  | 110469.275 | 417.676 | 69.5 | 715 | 357.5 | 175 | 144 | 319 | 178 | 153 | 331 | 76°9'1.637"E | 23°50'10.49"N | 617166.898 | 2636572.449 |  | Suigaon | Nalkheda | MP
[5 empty] | 345 | [16 empty] | Nala
290 |  | 65/6 | DA+0 |  |  |  | 110814.275 | 419.33 | 72.5 | 697 | 348.5 | 202 | 100 | 302 | 193 | 124 | 317 | 76°9'12.648"E | 23°50'5.672"N | 617479.637 | 2636426.78 |  | Suigaon | Nalkheda | MP
352
291 |  | 65/7 | DA(-)3 |  |  |  | 111166.275 | 434.784 | 69.5 | 792 | 396 | 252 | 273 | 525 | 229 | 257 | 486 | 76°9'23.882"E | 23°50'0.756"N | 617798.722 | 2636278.156 |  | Suigaon | Nalkheda | MP
440
292 |  | 65/8 | DA+1.5 |  |  |  | 111606.275 | 419.428 | 74 | 820 | 410 | 167 | 199 | 366 | 184 | 196 | 380 | 76°9'37.924"E | 23°49'54.61"N | 618197.577 | 2636092.376 |  | Suigaon | Nalkheda | MP
[5 empty] | 380 | [16 empty] | Cart Track
293 |  | 65/9 | DA(-)3 |  |  |  | 111986.275 | 422.442 | 69.5 | 796 | 398 | 182 | 127 | 309 | 185 | 153 | 338 | 76°9'50.052"E | 23°49'49.302"N | 618542.043 | 2635931.93 |  | Suigaon | Nalkheda | MP
[5 empty] | 416 | [16 empty] | 11kV line, LT line, Cart track
294 |  | 65/10 | DA+9 |  |  |  | 112402.275 | 426.214 | 81.5 | 822 | 411 | 290 | 284 | 574 | 265 | 259 | 524 | 76°10'3.328"E | 23°49'43.491"N | 618919.143 | 2635756.284 | Raised Chimney | Kilona | Nalkheda | MP | 1 | 0 | 0 | 0
[5 empty] | 406 | [16 empty] | Metal road
295 |  | 65/11 | DA+6 |  |  |  | 112808.275 | 414.059 | 78.5 | 839.178 | 419.589 | 123 | 249 | 372 | 149 | 239 | 388 | 76°10'16.284"E | 23°49'37.819"N | 619287.178 | 2635584.86 |  | Kilona | Nalkheda | MP
[5 empty] | 433.178 | [16 empty] | 11kv line, Nala, Well
296 | AP66/0 | 66/0 | DB1+0 | 1° 44' 24"RT |  | 4751.178 | 113241.453 | 413.6 | 70.72 | 786.426 | 393.213 | 185 | 116 | 301 | 195 | 135 | 330 | 76°10'30.108"E | 23°49'31.768"N | 619679.85 | 2635401.96 |  | Kilona | Nalkheda | MP
[5 empty] | 353.248 | [16 empty] | Nala, Well, Cart track
297 |  | 66/1 | DA+6 | 0° 44' 14"RT |  |  | 113594.701 | 417.697 | 78.5 | 760.248 | 380.124 | 238 | 301 | 539 | 219 | 271 | 490 | 76°10'41.212"E | 23°49'26.52"N | 619995.389 | 2635243.154 | Raised Chimney | Pilwas | Nalkheda | MP | 2.5 | 2.5 | 0 | 0
[5 empty] | 407 | [16 empty] | Orange garden, Cart track
298 |  | 66/2 | DA(-)1.5 | 0° 50' 41"LT |  |  | 114001.701 | 406.747 | 71 | 823 | 411.5 | 107 | 187 | 294 | 137 | 194 | 331 | 76°10'53.918"E | 23°49'20.323"N | 620356.505 | 2635055.549 |  | Pilwas | Nalkheda | MP
[5 empty] | 416 | [16 empty] | Orange garden, Nala
299 |  | 66/3 | DA+6 |  |  |  | 114417.701 | 403.349 | 78.5 | 789 | 394.5 | 230 | 245 | 475 | 223 | 227 | 450 | 76°11'7.007"E | 23°49'14.165"N | 620728.447 | 2634869.23 |  | Pilwas | Nalkheda | MP
[5 empty] | 373 | [16 empty] | 11kV line, LT line, Cart track, Orange garden
300 |  | 66/4 | DA(-)3 |  |  |  | 114790.701 | 402.196 | 69.5 | 762 | 381 | 128 | 165 | 293 | 147 | 175 | 322 | 76°11'18.743"E | 23°49'8.643"N | 621061.944 | 2634702.169 |  | Pilwas | Nalkheda | MP
[5 empty] | 389 | [16 empty] | Orange garden, Cart track
301 |  | 66/5 | DA+3 |  |  |  | 115179.701 | 401.524 | 75.5 | 788 | 394 | 224 | 232 | 456 | 215 | 222 | 437 | 76°11'30.981"E | 23°49'2.884"N | 621409.746 | 2634527.943 |  | Pilwas | Nalkheda | MP
[5 empty] | 399 | [16 empty] | 11kV line
302 |  | 66/6 | DA(-)1.5 |  |  |  | 115578.701 | 400.071 | 71 | 811 | 405.5 | 168 | 172 | 340 | 178 | 183 | 361 | 76°11'43.534"E | 23°48'56.977"N | 621766.488 | 2634349.238 |  | Pilwas | Nalkheda | MP
[5 empty] | 412 | [16 empty] | Cart track, 11kV line, Well, Hut
303 |  | 66/7 | DA+6 |  |  |  | 115990.701 | 399.199 | 78.5 | 830 | 415 | 241 | 262 | 503 | 230 | 246 | 476 | 76°11'56.496"E | 23°48'50.877"N | 622134.854 | 2634164.71 |  | Pilwas | Nalkheda | MP
[5 empty] | 418 | [16 empty] | 11kv line, Cart track, Orange garden, Well
304 |  | 66/8 | DA(-)3 |  |  |  | 116408.701 | 397.889 | 69.5 | 812.107 | 406.0535 | 156 | 155 | 311 | 173 | 169 | 342 | 76°12'9.646"E | 23°48'44.687"N | 622508.585 | 2633977.495 |  | Pilwas | Nalkheda | MP
[5 empty] | 394.107 | [16 empty] | Metal road, 11kV line, Well, Hut
305 | AP67/0 | 67/0 | DB2+6 | 9° 0' 29"RT |  | 3561.355 | 116802.808 | 396.634 | 76.72 | 793.107 | 396.5535 | 240 | 245 | 485 | 227 | 231 | 458 | 76°12'22.044"E | 23°48'38.852"N | 622860.953 | 2633800.981 |  | Pilwas | Nalkheda | MP
[5 empty] | 399 | [16 empty] | 11kv line, Cart track, Orange garden, Well
306 |  | 67/1 | DA(-)3 |  |  |  | 117201.808 | 397.221 | 69.5 | 747 | 373.5 | 155 | 214 | 369 | 169 | 202 | 371 | 76°12'33.435"E | 23°48'31.208"N | 623185.315 | 2633568.623 |  | Pilwas | Nalkheda | MP
[5 empty] | 348 | [16 empty] | 11kv line, Cart track, Well
307 |  | 67/2 | DA(-)3 |  |  |  | 117549.808 | 390.617 | 69.5 | 706 | 353 | 134 | 120 | 254 | 146 | 138 | 284 | 76°12'43.37"E | 23°48'24.541"N | 623468.217 | 2633365.965 |  | Bhilkhedi | Nalkheda | MP
[5 empty] | 358 | [16 empty] | 11kv line, Cart track, Well, Metal road, Nala
308 |  | 67/3 | DA+9 |  |  |  | 117907.808 | 388.639 | 81.5 | 836.205 | 418.1025 | 239 | 264 | 503 | 221 | 257 | 478 | 76°12'53.591"E | 23°48'17.683"N | 623759.249 | 2633157.483 | Raised Chimney | Bhilkhedi | Nalkheda | MP | 0 | 0 | 2 | 0
[5 empty] | 478.205 | [16 empty] | Nala, LT line, orange garden, Well
309 | AP68/0 | 68/0 | DB2+6 | 13° 2' 58"LT |  | 1583.205 | 118386.013 | 386.186 | 76.72 | 118864.218 | 59432.109 | 215 | 0 | 215 | 223 | 0 | 223 | 76°13'7.242"E | 23°48'8.521"N | 624148 | 2632879 |  | Bhilkhedi | Nalkheda | MP
[5 empty] | 118386.013 | 118386.009
SUMMARY OF TOWERS QUANTITIES GANTRY TO AP 68 COMMON POINT
[7 empty] | TYPE OF TOWER | EXTENSION | [9 empty] | TOTAL TOWER
[8 empty] | -3 | -1.5 | +0 | +1.5 | +3 | +6 | +9 | +12 | +18 | +25
[7 empty] | DA | 40 | 15 | 77 | 20 | 40 | 32 | 6 | 0 | 0 | 0 | 230
[7 empty] | DB1 | 0 | 1 | 7 | 0 | 2 | 1 | 3 | 1 | 1 | 0 | 16
[7 empty] | DB2 | 0 | 1 | 4 | 0 | 3 | 3 | 2 | 0 | 0 | 0 | 13
[7 empty] | DC1 | 0 | 0 | 7 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 12
[7 empty] | DC2 | 0 | 0 | 8 | 0 | 1 | 1 | 0 | 2 | 3 | 0 | 15
[7 empty] | DD45 | 0 | 0 | 5 | 0 | 2 | 1 | 4 | 1 | 2 | 0 | 15
[7 empty] | DD60 | 0 | 0 | 3 | 0 | 0 | 1 | 2 | 0 | 0 | 2 | 8
[7 empty] | Total | 40 | 17 | 111 | 20 | 51 | 41 | 17 | 4 | 6 | 2 | 309

## Final Tower Schedule (hidden)
CLIENT :- POWER GRID CORPORATION OF INDIA LIMITED
NAME OF PROJECT :- 765 KV D/C Mandsaur - Kurawar (Part 1) Transmission Line
M/s. KEC INTERNATIONAL LIMITED
TOWER SCHEDULE SECTION:- GANTRY TO AP 68 LENGTH:- 119.178 KM
KEC/TA509/MKTL/CS/AS ON Dt-02.06.2026
Sl.No | AP NO. | TOWER NO. | TYPE OF TOWER | DEVIATION ANGLE (Deg) | SPAN (Mtr) | Section Length (m) | CUMULATIVE SPAN | R.L (Mtr) | HT of Tower (Mtr) | Sum of Adjacent Spans | WIND SPAN (Mtr) | WEIGHT SPAN IN Mtr (Cold) |  |  | WEIGHT SPAN IN Mtr (Hot) |  |  | Spherical Coordinate |  | UTM Coordinates |  | CROSSING DETAILS | NAME OF VILLAGE | NAME OF TEHSIL | NAME OF STATAT | LEG EXTENSION
[12 empty] | Left | Right | Total | Left | Right | Total | Longitude (Easting) | Latitude (Northing) | Easting | Northing |  |  |  |  | A | B | C | D
0 |  | Mandsaur Gantry | Gantry |  |  |  | 0 | 435.03 | 46.3 | 107.961 | 53.9805 | 0 | 6 | 6 | 0 | 11 | 11 | 75°10'24.829"E | 24°12'17.524"N | 517625.299 | 2676919.49
[5 empty] | 107.961 | [16 empty] | BOUNDARY WALL
1 | AP1/0 | 1/0 | DD60+0 | 7° 41' 29"LT |  | 107.961 | 107.961 | 434.455 | 70.72 | 256.439 | 128.2195 | 33 | 141 | 174 | 35 | 95 | 130 | 75°10'21.828"E | 24°12'15.345"N | 517540.723 | 2676852.389 | Tower cast at 0deg w.r.t. Gantry | Talabpipalya | Malhargarh | MP
148.478
2 | AP2/0 | 2/0 | DD60+0 | 58° 40' 0"LT |  | 148.478 | 256.439 | 431.101 | 70.72 | 557.31 | 278.655 | 7 | 220 | 227 | 53 | 215 | 268 | 75°10'18.175"E | 24°12'11.87"N | 517437.804 | 2676745.368 |  | Talabpipalya | Malhargarh | MP
[5 empty] | 408.832 | [16 empty] | NALA/LT LINE
3 | AP3/0 | 3/0 | DD45+3 | 42° 45' 44"LT |  | 408.832 | 665.271 | 425.18 | 73.72 | 788.832 | 394.416 | 190 | 213 | 403 | 194 | 206 | 400 | 75°10'21.856"E | 24°11'59.012"N | 517542.143 | 2676350.074 |  | Talabpipalya | Malhargarh | MP
[5 empty] | 380 | [16 empty] | ROAD/WELL
4 |  | 3/1 | DA(-)1.5 |  |  |  | 1045.271 | 425.63 | 71 | 802 | 401 | 167 | 198 | 365 | 175 | 202 | 377 | 75°10'33.214"E | 24°11'52.369"N | 517862.804 | 2676146.17 |  | Talabpipalya | Malhargarh | MP
[5 empty] | 422 | [16 empty] | LT/CT, WELL/NALA
5 |  | 3/2 | DA+6 |  |  |  | 1467.271 | 420.86 | 78.5 | 830.352 | 415.176 | 225 | 237 | 462 | 221 | 228 | 449 | 75°10'45.827"E | 24°11'44.992"N | 518218.906 | 2675919.73 |  | Talabpipalya | Malhargarh | MP
[5 empty] | 408.352 | [16 empty] | LT LINE, LT T POINT, WELL, CT, NALA/11KV LINE/ LT/CT/ WELL/ SAMADHI
6 | AP4/0 | 4/0 | DC1+0 | 19° 8' 15"LT |  | 1210.352 | 1875.623 | 420.532 | 70.72 | 827.805 | 413.9025 | 171 | 124 | 295 | 182 | 149 | 331 | 75°10'58.032"E | 24°11'37.853"N | 518563.491 | 2675700.613 |  | Kachariya | Malhargarh | MP
[5 empty] | 419.453 | [16 empty] | NALA, POND, WELL
7 |  | 4/1 | DA+9 |  |  |  | 2295.076 | 429.129 | 81.5 | 800.453 | 400.2265 | 297 | 175 | 472 | 272 | 179 | 451 | 75°11'12.496"E | 24°11'34.694"N | 518971.67 | 2675604.017 | Benching / Raised Chimney Expected | Kachariya | Malhargarh | MP | 1.5 |  |  | 0.5 | 1.5 mtr & 0.5 mtr RC DFR fdn dwg available
[5 empty] | 381 | [16 empty] | CT
8 |  | 4/2 | DA+9 |  |  |  | 2676.076 | 432.129 | 81.5 | 798.002 | 399.001 | 207 | 312 | 519 | 203 | 282 | 485 | 75°11'25.634"E | 24°11'31.825"N | 519342.43 | 2675516.275 | Benching / Raised Chimney Expected | Kachariya | Malhargarh | MP | 1.5 | 2 |  |  | 2 mtr RC DFR fdn dwg available
417.002
9 |  | 4/3 | DA(-)3 |  |  |  | 3093.078 | 423.427 | 69.5 | 834.004 | 417.002 | 107 | 196 | 303 | 136 | 200 | 336 | 75°11'40.014"E | 24°11'28.684"N | 519748.223 | 2675420.243 |  | Sohangara | Malhargarh | MP
[5 empty] | 417.002 | [16 empty] | METAL ROAD, CT, 11KV, LT
10 |  | 4/4 | DA+6 |  |  |  | 3510.08 | 416.978 | 78.5 | 834.004 | 417.002 | 221 | 270 | 491 | 218 | 253 | 471 | 75°11'54.393"E | 24°11'25.543"N | 520154.016 | 2675324.211 |  | Sohangara | Malhargarh | MP
[5 empty] | 417.002 | [16 empty] | WELL, LT
11 |  | 4/5 | DA(-)3 |  |  |  | 3927.082 | 413.573 | 69.5 | 805.005 | 402.5025 | 148 | 163 | 311 | 166 | 172 | 338 | 75°12'8.772"E | 24°11'22.402"N | 520559.81 | 2675228.179 |  | Sohangara | Malhargarh | MP
[5 empty] | 388.003 | [16 empty] | CT
12 |  | 4/6 | DA+6 |  |  |  | 4315.085 | 410.487 | 78.5 | 840.346 | 420.173 | 226 | 248 | 474 | 217 | 242 | 459 | 75°12'22.151"E | 24°11'19.479"N | 520937.383 | 2675138.826 |  | Sohangara | Malhargarh | MP
[5 empty] | 452.343 | [16 empty] | 11 KV LINE/SHIVNA RIVER/CART TRACK
13 | AP5/0 | 5/0 | DB1+0 | 0° 56' 36"LT |  | 2891.805 | 4767.428 | 411.761 | 70.72 | 853.343 | 426.6715 | 205 | 239 | 444 | 212 | 227 | 439 | 75°12'37.748"E | 24°11'16.07"N | 521377.568 | 2675034.655 |  | Aabakhedi | Sitamau | MP
[5 empty] | 401 | [16 empty] | NALA, PIPAL TREE
14 |  | 5/1 | DA(-)3 |  |  |  | 5168.428 | 407.682 | 69.5 | 731 | 365.5 | 162 | 118 | 280 | 175 | 134 | 309 | 75°12'51.627"E | 24°11'13.257"N | 521769.257 | 2674948.744 |  | Aabakhedi | Sitamau | MP
[5 empty] | 330 | [16 empty] | LT LINE, HUT, CART TRACK
15 |  | 5/2 | DA+0 |  |  |  | 5498.428 | 411.854 | 72.5 | 743 | 371.5 | 212 | 194 | 406 | 197 | 199 | 396 | 75°13'3.049"E | 24°11'10.942"N | 522091.595 | 2674878.045 |  | Nahargarh | Sitamau | MP
[5 empty] | 413 | [16 empty] | LT LINE, 11KV LINE, CART TRACK, WELL, LT T POINT
16 |  | 5/3 | DA+3 |  |  |  | 5911.428 | 411.285 | 75.5 | 835 | 417.5 | 220 | 223 | 443 | 216 | 219 | 435 | 75°13'17.343"E | 24°11'8.045"N | 522495.005 | 2674789.563 |  | Nahargarh | Sitamau | MP
[5 empty] | 422 | [16 empty] | GUAVA GARDEN, CART TRACK, WELL, ORANGE GARDEN
17 |  | 5/4 | DA+1.5 |  |  |  | 6333.428 | 410.546 | 74 | 818 | 409 | 200 | 210 | 410 | 204 | 206 | 410 | 75°13'31.948"E | 24°11'5.084"N | 522907.207 | 2674699.153 |  | Nahargarh | Sitamau | MP
[5 empty] | 396 | [16 empty] | GUAVA GARDEN, CART TRACK, ORANGE GARDEN
18 |  | 5/5 | DA+0 |  |  |  | 6729.428 | 409.91 | 72.5 | 781 | 390.5 | 186 | 194 | 380 | 190 | 194 | 384 | 75°13'45.65"E | 24°11'2.29"N | 523294.01 | 2674614.31 |  | Nahargarh | Sitamau | MP
[5 empty] | 385 | [16 empty] | 11KV LINE, CART TRACK, WELL, 11KV T POINT
19 |  | 5/6 | DA+0 |  |  |  | 7114.428 | 409.514 | 72.5 | 723 | 361.5 | 191 | 188 | 379 | 191 | 182 | 373 | 75°13'58.978"E | 24°10'59.603"N | 523670.073 | 2674531.831 |  | Nahargarh | Sitamau | MP
[5 empty] | 338 | [16 empty] | LT LINE, SAMADHI, WELL, CART TRACK
20 |  | 5/7 | DA(-)3 |  |  |  | 7452.428 | 409.625 | 69.5 | 662 | 331 | 151 | 146 | 297 | 157 | 152 | 309 | 75°14'10.676"E | 24°10'57.23"N | 524000.224 | 2674459.418 |  | Nahargarh | Sitamau | MP
[5 empty] | 324 | [16 empty] | NALA, METAL ROAD, WELL, CART TRACK
21 | AP6/0 | 6/0 | DC2+0 | 28° 53' 29"RT |  | 3009 | 7776.428 | 408.99 | 70.72 | 704 | 352 | 178 | 203 | 381 | 173 | 199 | 372 | 75°14'21.884"E | 24°10'54.956"N | 524316.58 | 2674390.03 |  | Nahargarh | Sitamau | MP
[5 empty] | 380 | [16 empty] | CART TRACK
22 |  | 6/1 | DA(-)1.5 |  |  |  | 8156.428 | 408.326 | 71 | 754 | 377 | 178 | 161 | 339 | 182 | 169 | 351 | 75°14'31.994"E | 24°10'46.792"N | 524602.224 | 2674139.416 |  | Nahargarh | Sitamau | MP
[5 empty] | 374 | [16 empty] | CART TRACK, ORANGE GARDEN, 33 KV LINE, WELL, LT LINE, LT T POINT, 11KVTF, 11 KV LINE (TO BE DIVERTED)
23 |  | 6/2 | DA+1.5 |  |  |  | 8530.428 | 409.895 | 74 | 789 | 394.5 | 213 | 196 | 409 | 205 | 200 | 405 | 75°14'41.93"E | 24°10'38.73"N | 524883.36 | 2673892.76 |  | Nahargarh | Sitamau | MP
[5 empty] | 415 | [16 empty] | 11 KV LINE , 11KV T POINT
24 |  | 6/3 | DA+1.5 |  |  |  | 8945.428 | 412.132 | 74 | 801 | 400.5 | 219 | 192 | 411 | 215 | 192 | 407 | 75°14'52.982"E | 24°10'29.838"N | 525195.313 | 2673619.063 |  | Nahargarh | Sitamau | MP
[5 empty] | 386 | [16 empty] | METAL ROAD, LT LINE, CART TRACK, 11 KV LINE
25 | AP7/0 | 7/0 | DC2+0 | 22° 44' 15"LT |  | 1555 | 9331.428 | 413.89 | 70.72 | 738 | 369 |  | 178 | 178 |  | 179 | 179 | 75°15'3.249"E | 24°10'21.544"N | 525485.462 | 2673364.497 |  | Khajuri_chandrawat | Sitamau | MP
[5 empty] | 352 | [16 empty] | LT line & Cart track
26 |  | 7/1 | DA+0 |  |  |  | 9683.428 | 413.39 | 72.5 | 744 | 372 | 174 | 200 | 374 | 173 | 202 | 375 | 75° 15' 15.02"E | 24° 10' 17.75"N | 525817.81 | 2673248.52 |  | Khajuri_chandrawat | Sitamau | MP
[5 empty] | 392 | [16 empty] | 11kV line & Cart track
27 |  | 7/2 | DA+0 |  |  |  | 10075.428 | 412.24 | 72.5 | 773 | 386.5 | 192 | 195 | 387 | 190 | 198 | 388 | 75° 15' 28.13"E | 24° 10' 13.53"N | 526187.92 | 2673119.37 |  | Khajuri_chandrawat | Sitamau | MP
[5 empty] | 381 | [16 empty] | Cart track
28 |  | 7/3 | DA+0 |  |  |  | 10456.428 | 410.96 | 72.5 | 771 | 385.5 | 186 | 190 | 376 | 183 | 187 | 370 | 75° 15' 40.87"E | 24° 10' 9.43"N | 526547.65 | 2672993.84 |  | Khajuri_chandrawat | Sitamau | MP
[5 empty] | 390 | [16 empty] | LT line, Cart track & Nala
29 |  | 7/4 | DA+0 |  |  |  | 10846.428 | 412.34 | 72.5 | 781 | 390.5 | 200 | 188 | 388 | 203 | 185 | 388 | 75° 15' 53.91"E | 24° 10' 5.23"N | 526915.87 | 2672865.34 |  | Khajuri_chandrawat | Sitamau | MP
[5 empty] | 391 | [16 empty] | 11kV line, LT line & Cart track
30 | AP8/0 | 8/0 | DB1+0 | 2° 0' 34"RT |  | 1906 | 11237.428 | 414.33 | 70.72 | 722 | 361 | 203 | 155 | 358 | 206 | 150 | 356 | 75° 16' 6.98"E | 24° 10' 1.02"N | 527284.94 | 2672736.55 |  | Khajuri_chandrawat | Sitamau | MP
[5 empty] | 331 | [16 empty] | Cart track & Nala
31 |  | 8/1 | DA+0 |  |  |  | 11568.428 | 416.74 | 72.5 | 735 | 367.5 | 176 | 177 | 353 | 181 | 165 | 346 | 75° 16' 17.91"E | 24° 9' 57.1"N | 527593.44 | 2672616.6 |  | Khajuri_chandrawat | Sitamau | MP
[5 empty] | 404 | [16 empty] | LT line & Cart track
32 |  | 8/2 | DA+3 |  |  |  | 11972.428 | 420.745 | 75.5 | 814 | 407 | 227 | 195 | 422 | 239 | 190 | 429 | 75° 16' 31.24"E | 24° 9' 52.31"N | 527969.98 | 2672470.2 |  | Khajuri_chandrawat | Sitamau | MP
[5 empty] | 410 | [16 empty] | 11kV line, LT line & Cart track
33 |  | 8/3 | DA+3 |  |  |  | 12382.428 | 423.53 | 75.5 | 808 | 404 | 215 | 203 | 418 | 220 | 205 | 425 | 75° 16' 44.77"E | 24° 9' 47.46"N | 528352.12 | 2672321.62 |  | Khajuri_chandrawat | Sitamau | MP
[5 empty] | 398 | [16 empty] | LT line & Cart track
34 |  | 8/4 | DA+3 |  |  |  | 12780.428 | 422.4 | 75.5 | 830 | 415 | 195 | 242 | 437 | 193 | 254 | 447 | 75° 16' 57.91"E | 24° 9' 42.74"N | 528723.06 | 2672177.4 |  | Khajuri_chandrawat | Sitamau | MP
[5 empty] | 432 | [16 empty] | 33kV line, 11kV line, Metal road, Cart track & nala
35 |  | 8/5 | DA+0 |  |  |  | 13212.428 | 417.72 | 72.5 | 788 | 394 | 190 | 174 | 364 | 178 | 173 | 351 | 75° 17' 12.17"E | 24° 9' 37.63"N | 529125.7 | 2672020.85 |  | Beti_khedi | Sitamau | MP
[5 empty] | 356 | [16 empty] | Cart track
36 |  | 8/6 | DA+0 |  |  |  | 13568.428 | 418.57 | 72.5 | 764 | 382 | 182 | 228 | 410 | 183 | 238 | 421 | 75° 17' 23.92"E | 24° 9' 33.41"N | 529457.5 | 2671891.84 |  | Rojafatehag | Sitamau | MP
[5 empty] | 408 | [16 empty] | 11kV line & Cart track
37 |  | 8/7 | DA+0 |  |  |  | 13976.428 | 412 | 72.5 | 823 | 411.5 | 180 | 208 | 388 | 170 | 208 | 378 | 75° 17' 37.38"E | 24° 9' 28.58"N | 529837.77 | 2671743.99 |  | Rojafatehag | Sitamau | MP
[5 empty] | 415 | [16 empty] | LT line, Nala & Cart track
38 |  | 8/8 | DA+3 |  |  |  | 14391.428 | 408.975 | 75.5 | 786 | 393 | 207 | 216 | 423 | 207 | 230 | 437 | 75° 17' 51.08"E | 24° 9' 23.66"N | 530224.57 | 2671593.6 |  | Rojafatehag | Sitamau | MP
[5 empty] | 371 | [16 empty] | Nala
39 |  | 8/9 | DA(-)3 |  |  |  | 14762.428 | 407.29 | 69.5 | 735 | 367.5 | 155 | 162 | 317 | 141 | 153 | 294 | 75°18'3.31"E | 24° 9'19.26"N | 530570.35 | 2671459.16 |  | Rojafatehag | Sitamau | MP
[5 empty] | 364 | [16 empty] | 11kV line & Cart track
40 |  | 8/10 | DA+0 |  |  |  | 15126.428 | 409.2 | 72.5 | 779 | 389.5 | 202 | 205 | 407 | 211 | 204 | 415 | 75°18'15.31"E | 24° 9'14.95"N | 530909.61 | 2671327.25 |  | Rojafatehag | Sitamau | MP
[5 empty] | 415 | [16 empty] | 11kV line, metal road & Nala
41 | AP9/0 | 9/0 | DB2+0 | 9° 24' 57"LT |  | 4304 | 15541.428 | 409.93 | 70.72 | 804 | 402 | 210 | 181 | 391 | 211 | 175 | 386 | 75° 18' 29.02" | 24° 9' 10.04" | 531296.31 | 2671176.9 |  | Halu_Khedi | Sitamau | MP
[5 empty] | 389 | [16 empty] | LT line
42 |  | 9/1 | DA+3 |  |  |  | 15930.428 | 410.47 | 75.5 | 785 | 392.5 | 208 | 205 | 413 | 214 | 209 | 423 | 75° 18' 42.51" | 24° 9' 7.42" | 531677.04 | 2671097.15 |  | Halu_Khedi | Sitamau | MP
[5 empty] | 396 | [16 empty] | Nala
43 |  | 9/2 | DA+0 |  |  |  | 16326.428 | 411.48 | 72.5 | 835 | 417.5 | 191 | 190 | 381 | 187 | 176 | 363 | 75° 18' 56.24" | 24° 9' 4.75" | 532064.63 | 2671015.96 |  | Halu_Khedi | Sitamau | MP
[5 empty] | 439 | [16 empty] | 11kV line
44 |  | 9/3 | DA+6 |  |  |  | 16765.428 | 414.42 | 78.5 | 820 | 410 | 249 | 204 | 453 | 263 | 210 | 473 | 75° 19' 11.45" | 24° 9' 1.79" | 532494.3 | 2670925.96 |  | Rupni | Sitamau | MP
[5 empty] | 381 | [16 empty] | 11kV line
45 | AP10/0 | 10/0 | DB1+0 | 4° 31' 7"RT |  | 1605 | 17146.428 | 416.975 | 70.72 | 767 | 383.5 | 220 | 188 | 408 | 210 | 190 | 400 | 75°19'24.673" | 24°8'59.22" | 532867.524 | 2670847.779 |  | Rupni | Sitamau | MP
[5 empty] | 386 | [16 empty] | 33kV line,2no's LT line, Metal road & 2no's nala
46 |  | 10/1 | DA+0 |  |  |  | 17532.428 | 418.018 | 72.5 | 742 | 371 | 199 | 176 | 375 | 198 | 177 | 375 | 75°19'37.789" | 24°8'55.66" | 533237.916 | 2670739.123 |  | Rupni | Sitamau | MP
[5 empty] | 356 | [16 empty] | Cart track,Well
47 |  | 10/2 | DA(-)3 |  |  |  | 17888.428 | 421.412 | 69.5 | 721 | 360.5 | 181 | 129 | 310 | 180 | 146 | 326 | 75°19'49.885" | 24°8'52.375" | 533579.52 | 2670638.912 |  | Rupni | Sitamau | MP
[5 empty] | 365 | [16 empty] | 11kV line, Nala & Cart track
48 |  | 10/3 | DA+3 |  |  |  | 18253.428 | 424.562 | 75.5 | 840 | 420 | 236 | 118 | 354 | 220 | 155 | 375 | 75°20'2.287" | 24°8'49.007" | 533929.761 | 2670536.167 |  | Risthal | Sitamau | MP
[5 empty] | 475 | [16 empty] | 2 No's 11kV line, Nala & Cart track
49 | AP11/0 | 11/0 | DD60+25 | 25° 28' 21"LT |  | 1582 | 18728.428 | 429.486 | 95.72 | 671 | 335.5 | 359 | 75 | 434 | 323 | 89 | 412 | 75°20'18.43" | 24°8'44.623" | 534385.651 | 2670402.43 |  | Risthal | Sitamau | MP
[5 empty] | 196 | [16 empty] | 400 KV DC NEEMUCH-MANDSAUR TL TN 253 - TN 254
50 | AP12/0 | 12/0 | DD60+25 | 27° 8' 47"RT |  | 196 | 18924.428 | 430.037 | 95.72 | 673 | 336.5 | 121 | 349 | 470 | 107 | 315 | 422 | 75°20'25.289" | 24°8'45.618" | 534579.163 | 2670433.506 | 1M RC | Risthal | Sitamau | MP | 1 | 1 | 1 | 1 | 1 mtr RC DFR/WFR FDN DWG Available
[5 empty] | 477 | [16 empty] | 11kV line, Nala & Cart track
51 |  | 12/1 | DA+3 |  |  |  | 19401.428 | 428.713 | 75.5 | 840 | 420 | 129 | 219 | 348 | 165 | 207 | 372 | 75°20'41.349" | 24°8'40.784" | 535032.758 | 2670285.922 |  | Risthal | Sitamau | MP
[5 empty] | 363 | [16 empty] | LT line, Nala & Cart track
52 |  | 12/2 | DA(-)3 |  |  |  | 19764.428 | 428.434 | 69.5 | 691 | 345.5 | 145 | 156 | 301 | 157 | 159 | 316 | 75°20'53.57" | 24°8'37.104" | 535377.946 | 2670173.61 |  | Risthal | Sitamau | MP
328
53 |  | 12/3 | DA(-)3 |  |  |  | 20092.428 | 429.607 | 69.5 | 704 | 352 | 172 | 161 | 333 | 170 | 170 | 340 | 75°21'4.613" | 24°8'33.779" | 535689.851 | 2670072.126 |  | Risthal | Sitamau | MP
[5 empty] | 376 | [16 empty] | Cart track & Nala
54 |  | 12/4 | DA+0 |  |  |  | 20468.428 | 431.437 | 72.5 | 769 | 384.5 | 216 | 180 | 396 | 207 | 185 | 392 | 75°21'17.272" | 24°8'29.967" | 536047.402 | 2669955.792 |  | Risthal | Sitamau | MP
[5 empty] | 393 | [16 empty] | 11kV line & Cart track
55 |  | 12/5 | DA+1.5 |  |  |  | 20861.428 | 433.068 | 74 | 790 | 395 | 214 | 209 | 423 | 209 | 206 | 415 | 75°21'30.503" | 24°8'25.983" | 536421.118 | 2669834.197 |  | Boliya | Sitamau | MP
[5 empty] | 397 | [16 empty] | LT line
56 |  | 12/6 | DA+0 |  |  |  | 21258.428 | 432.71 | 72.5 | 791 | 395.5 | 189 | 199 | 388 | 192 | 199 | 391 | 75°21'43.868" | 24°8'21.957" | 536798.638 | 2669711.365 |  | Boliya | Sitamau | MP
[5 empty] | 394 | [16 empty] | 11kV line & 2No'sCart track,Well
57 |  | 12/7 | DA+0 |  |  |  | 21652.428 | 432.437 | 72.5 | 767 | 383.5 | 196 | 194 | 390 | 197 | 192 | 389 | 75°21'57.132" | 24°8'17.962" | 537173.305 | 2669589.462 |  | Boliya | Sitamau | MP
[5 empty] | 373 | [16 empty] | 11kV line & Cart track
58 | AP13/0 | 13/0 | DB2+0 | 9° 25' 31"RT |  | 3101 | 22025.428 | 431.107 | 70.72 | 730 | 365 | 179 | 194 | 373 | 182 | 189 | 371 | 75°22'9.688" | 24°8'14.179" | 537527.991 | 2669474.059 |  | Boliya | Sitamau | MP
[5 empty] | 357 | [16 empty] | LT line, Nala & Cart track,Pond,Well
59 |  | 13/1 | DA(-)1.5 |  |  |  | 22382.428 | 430.193 | 71 | 731 | 365.5 | 164 | 179 | 343 | 169 | 183 | 352 | 75°22'20.897" | 24°8'8.801" | 537844.803 | 2669309.499 |  | Boliya | Sitamau | MP
[5 empty] | 374 | [16 empty] | 2No's Cart track
60 |  | 13/2 | DA+0 |  |  |  | 22756.428 | 430.005 | 72.5 | 754 | 377 | 195 | 200 | 395 | 193 | 197 | 390 | 75°22'32.641" | 24°8'3.167" | 538176.7 | 2669137.104 |  | Vishanya | Sitamau | MP
[5 empty] | 380 | [16 empty] | 2No'sLT line &2No's Cart track
61 |  | 13/3 | DA+0 |  |  |  | 23136.428 | 428.413 | 72.5 | 724 | 362 | 181 | 197 | 378 | 185 | 189 | 374 | 75°22'44.572" | 24°7'57.442" | 538513.922 | 2668961.943 |  | Vishanya | Sitamau | MP
[5 empty] | 344 | [16 empty] | Cart track & Nala
62 |  | 13/4 | DA(-)3 |  |  |  | 23480.428 | 427.526 | 69.5 | 674 | 337 | 147 | 159 | 306 | 156 | 161 | 317 | 75°22'55.372" | 24°7'52.259" | 538819.197 | 2668803.376 |  | Vishanya | Sitamau | MP
[5 empty] | 330 | [16 empty] | 11kV line & Cart track
63 |  | 13/5 | DA+0 |  |  |  | 23810.428 | 425.498 | 72.5 | 697 | 348.5 | 172 | 208 | 380 | 170 | 200 | 370 | 75°23'5.733" | 24°7'47.287" | 539112.047 | 2668651.262 |  | Vishanya | Sitamau | MP
[5 empty] | 367 | [16 empty] | Cart track
64 | AP14/0 | 14/0 | DC1+0 | 18° 44' 47"LT |  | 2152 | 24177.428 | 421.509 | 70.72 | 752 | 376 | 160 | 173 | 333 | 169 | 180 | 349 | 75°23'17.263" | 24°7'41.754" | 539437.951 | 2668481.98 |  | Vishanya | Sitamau | MP
[5 empty] | 385 | [16 empty] | 33kV line,11kV line,LT line, Metal road,Cart track & nala
65 |  | 14/1 | DA+0 |  |  |  | 24562.428 | 425.073 | 72.5 | 740 | 370 | 213 | 170 | 383 | 206 | 173 | 379 | 75°23'30.74" | 24°7'39.825" | 539818.519 | 2668423.73 |  | Vishanya | Sitamau | MP
[5 empty] | 355 | [16 empty] | Cart track
66 |  | 14/2 | DA+0 |  |  |  | 24917.428 | 426.383 | 72.5 | 712 | 356 | 186 | 179 | 365 | 183 | 179 | 362 | 75°23'43.167" | 24°7'38.047" | 540169.432 | 2668370.02 |  | Vishanya | Sitamau | MP
[5 empty] | 357 | [16 empty] | 11kV line,LT line, Metal road & Cart track
67 |  | 14/3 | DA(-)3 |  |  |  | 25274.428 | 429.339 | 69.5 | 750 | 375 | 178 | 169 | 347 | 179 | 179 | 358 | 75°23'55.664" | 24°7'36.258" | 540522.323 | 2668316.006 |  | Khajuri_Goud | Sitamau | MP
[5 empty] | 393 | [16 empty] | 11kV line & Cart track
68 |  | 14/4 | DA+3 |  |  |  | 25667.428 | 428.349 | 75.5 | 776 | 388 | 225 | 239 | 464 | 216 | 223 | 439 | 75°24'9.421" | 24°7'34.289" | 540910.798 | 2668256.546 |  | Khajuri_Goud | Sitamau | MP
[5 empty] | 383 | [16 empty] | LT line & Cart track
69 |  | 14/5 | DA+0 |  |  |  | 26050.428 | 423.122 | 72.5 | 771 | 385.5 | 145 | 218 | 363 | 161 | 211 | 372 | 75°24'22.828" | 24°7'32.369" | 541289.389 | 2668198.599 |  | Khajuri_Goud | Sitamau | MP
[5 empty] | 388 | [16 empty] | LT line (To be diverted), Nala & Cart track
70 | AP15/0 | 15/0 | DB2+0 | 12° 10' 5"RT |  | 2261 | 26438.428 | 418.854 | 70.72 | 756 | 378 | 170 | 193 | 363 | 179 | 190 | 369 | 75°24'36.413" | 24°7'30.424" | 541673.01 | 2668139.882 |  | Khajuri_Goud | Sitamau | MP
[5 empty] | 368 | [16 empty] | Nala
71 |  | 15/1 | DA+0 |  |  |  | 26806.428 | 417.373 | 72.5 | 780 | 390 | 176 | 175 | 351 | 179 | 185 | 364 | 75°24'48.581" | 24°7'26.128" | 542016.865 | 2668008.781 |  | Khajuri_Goud | Sitamau | MP
[5 empty] | 412 | [16 empty] | 11kV line, Nala & Cart track
72 |  | 15/2 | DA+3 |  |  |  | 27218.428 | 420.33 | 75.5 | 828 | 414 | 237 | 221 | 458 | 228 | 217 | 445 | 75°25'2.204" | 24°7'21.319" | 542401.834 | 2667862.005 |  | Khajuri_Goud | Sitamau | MP
416
73 |  | 15/3 | DA+0 |  |  |  | 27634.428 | 420.876 | 72.5 | 823 | 411.5 | 196 | 167 | 363 | 200 | 179 | 379 | 75°25'15.959" | 24°7'16.462" | 542790.54 | 2667713.804 |  | Khajuri_Goud | Sitamau | MP
[5 empty] | 407 | [16 empty] | Cart track
74 |  | 15/4 | DA+6 |  |  |  | 28041.428 | 421.793 | 78.5 | 832 | 416 | 240 | 318 | 558 | 229 | 285 | 514 | 75°25'29.416" | 24°7'11.71" | 543170.837 | 2667568.81 |  | Khajuri_Goud | Sitamau | MP
[5 empty] | 425 | [16 empty] | Nala
75 |  | 15/5 | DA(-)3 |  |  |  | 28466.428 | 410.078 | 69.5 | 811 | 405.5 | 108 | 150 | 258 | 142 | 164 | 306 | 75°25'43.468" | 24°7'6.748" | 543567.953 | 2667417.403 |  | Salriya | Sitamau | MP
[5 empty] | 386 | [16 empty] | 11kV line, Nala & Cart track
76 |  | 15/6 | DA+0 |  |  |  | 28852.428 | 414.874 | 72.5 | 745 | 372.5 | 237 | 128 | 365 | 223 | 144 | 367 | 75°25'56.23" | 24°7'2.241" | 543928.627 | 2667279.889 | Raised Chimney | Salriya | Sitamau | MP | 2 | 2 | 0 | 0 | FDN DA+0 RC2m DFR AVIALBLE
[5 empty] | 359 | [16 empty] | Cart track
77 |  | 15/7 | DA+0 |  |  |  | 29211.428 | 423.544 | 72.5 | 727 | 363.5 | 232 | 157 | 389 | 216 | 166 | 382 | 75°26'8.099" | 24°6'58.049" | 544264.073 | 2667151.995 |  | Salriya | Sitamau | MP
[5 empty] | 368 | [16 empty] | Cart track
78 |  | 15/8 | DA+0 |  |  |  | 29579.428 | 428.193 | 72.5 | 758 | 379 | 211 | 178 | 389 | 203 | 183 | 386 | 75°26'20.266" | 24°6'53.751" | 544607.929 | 2667020.894 |  | Salriya | Sitamau | MP
[5 empty] | 390 | [16 empty] | Cart track
79 |  | 15/9 | DA+3 |  |  |  | 29969.428 | 428.403 | 75.5 | 800 | 400 | 213 | 234 | 447 | 208 | 225 | 433 | 75°26'33.16" | 24°6'49.196" | 544972.341 | 2666881.956 |  | Borkhedi_Jagir | Sitamau | MP
[5 empty] | 410 | [16 empty] | Cart track
80 | AP16/0 | 16/0 | DB1+0 | 2°04'42"RT |  | 3941 | 30379.428 | 425.949 | 70.72 | 790 | 395 | 177 | 208 | 385 | 186 | 216 | 402 | 75° 26' 46.7" | 24° 6' 44.41" | 545355.05 | 2666736.04 |  | Borkhedi_Jagir | Sitamau | MP
380
81 |  | 16/1 | DA+0 |  |  |  | 30759.428 | 421.3 | 72.5 | 747 | 373.5 | 171 | 235 | 406 | 164 | 252 | 416 | 75° 26' 59.29" | 24° 6' 40.05" | 545711 | 2666603 |  | Borkhedi_Jagir | Sitamau | MP
[5 empty] | 367 | [16 empty] | 2 NOS CART TRACK / LT LINE
82 |  | 16/2 | DA+0 |  |  |  | 31126.428 | 409.5 | 72.5 | 800 | 400 | 132 | 187 | 319 | 115 | 177 | 292 | 75° 27' 11.46" | 24° 6' 35.84" | 546054.77 | 2666474.51 |  | Borkhedi_Jagir | Sitamau | MP
[5 empty] | 433 | [16 empty] | 3 NOS. NALA/ CART TRACK/LT LINE
83 |  | 16/3 | DA+9 |  |  |  | 31559.428 | 408.511 | 81.5 | 833 | 416.5 | 246 | 184 | 430 | 256 | 178 | 434 | 75° 27' 25.81" | 24° 6' 30.86" | 546460.37 | 2666322.91 |  | Borkhedi_Jagir | Sitamau | MP
[5 empty] | 400 | [16 empty] | WELL/NALA/CART TRACK /11 KV LINE
84 |  | 16/4 | DA+0 |  |  |  | 31959.428 | 421.58 | 72.5 | 796 | 398 | 216 | 155 | 371 | 222 | 140 | 362 | 75° 27' 39.06" | 24° 6' 26.27" | 546835.05 | 2666182.87 |  | Borkhedi_Jagir | Sitamau | MP
[5 empty] | 396 | [16 empty] | TAR ROAD/11KV LINE
85 |  | 16/5 | DA+6 |  |  |  | 32355.428 | 426.247 | 78.5 | 816 | 408 | 241 | 255 | 496 | 256 | 270 | 526 | 75° 27' 52.19" | 24° 6' 21.72" | 547205.99 | 2666044.23 |  | Borkhedi_Jagir | Sitamau | MP
[5 empty] | 420 | [16 empty] | 3 NOS NALA
86 |  | 16/6 | DA(-)3 |  |  |  | 32775.428 | 423.4 | 69.5 | 774 | 387 | 165 | 155 | 320 | 150 | 147 | 297 | 75° 28' 6.11" | 24° 6' 16.9" | 547599.4 | 2665897.18 |  | Chimangad | Sitamau | MP
[5 empty] | 354 | [16 empty] | WELL
87 |  | 16/7 | DA+0 |  |  |  | 33129.428 | 425.32 | 72.5 | 702 | 351 | 199 | 214 | 413 | 207 | 228 | 435 | 75° 28' 17.84" | 24° 6' 12.83" | 547931 | 2665773.25 |  | Chimangad | Sitamau | MP
[5 empty] | 348 | [16 empty] | 11 KV LINE/TAR ROAD/CART TRACK/WELL
88 |  | 16/8 | DA(-)3 |  |  |  | 33477.428 | 419.483 | 69.5 | 667 | 333.5 | 134 | 146 | 280 | 120 | 141 | 261 | 75° 28' 29.37" | 24° 6' 8.84" | 548256.97 | 2665651.41 |  | Chimangad | Sitamau | MP
[5 empty] | 319 | [16 empty] | WELL
89 |  | 16/9 | DA+0 |  |  |  | 33796.428 | 419.25 | 72.5 | 698 | 349 | 173 | 199 | 372 | 178 | 202 | 380 | 75° 28' 39.94" | 24° 6' 5.17" | 548555.78 | 2665539.72 |  | Chimangad | Sitamau | MP
[5 empty] | 379 | [16 empty] | 2 NOS 11KV /CART TRACK/BRICK FACTORY
90 |  | 16/10 | DA+6 |  |  |  | 34175.428 | 411.1 | 78.5 | 807 | 403.5 | 180 | 213 | 393 | 177 | 212 | 389 | 75° 28' 52.5" | 24° 6' 0.82" | 548910.8 | 2665407.03 |  | Chimangad | Sitamau | MP
[5 empty] | 428 | [16 empty] | NALA
91 |  | 16/11 | DA+0 |  |  |  | 34603.428 | 417.45 | 72.5 | 825 | 412.5 | 215 | 185 | 400 | 216 | 181 | 397 | 75° 29' 6.68" | 24° 5' 55.9" | 549311.71 | 2665257.19 |  | Chimangad | Sitamau | MP
[5 empty] | 397 | [16 empty] | CART TRACK/11KV LINE/PUMP
92 | AP17/0 | 17/0 | DB2+3 | 12°41'17"RT |  | 4621 | 35000.428 | 417.72 | 73.72 | 644 | 322 | 212 | 150 | 362 | 216 | 159 | 375 | 75° 29' 19.83" | 24° 5' 51.34" | 549683.4 | 2665118.26 |  | Chahkhedi | Sitamau | MP
[5 empty] | 247 | [16 empty] | 2 NOS 33KV LINE/NE-4 DELHI MUMBAI EXPRESSWAY/CART TRACK
93 | AP18/0 | 18/0 | DD45+0 | 35° 35' 35"LT |  | 247 | 35247.428 | 416.658 | 70.72 | 670 | 335 | 82 | 261 | 343 | 104 | 247 | 351 | 75°29'27.132"E | 24°5'46.924"N | 549890.07 | 2664983.112 |  | Chahkhedi | Sitamau | MP
423
94 |  | 18/1 | DA+6 |  |  |  | 35670.428 | 400.691 | 78.5 | 818 | 409 | 162 | 171 | 333 | 177 | 179 | 356 | 75°29'42.103"E | 24°5'47.454"N | 550312.695 | 2665000.909 |  | Chahkhedi | Sitamau | MP
[5 empty] | 395 | [16 empty] | CT, NALA
95 | AP19/0 | 19/0 | DD45+9 | 37° 14' 44"LT |  | 818 | 36065.428 | 402.673 | 79.72 | 894 | 447 | 224 | 246 | 470 | 218 | 247 | 465 | 75°29'56.082"E | 24°5'47.949"N | 550707.293 | 2665017.525 | Raised Chimney | Chahkhedi | Sitamau | MP | 0.5 | 0 | 1 | 2 | 1 MTR & 2 MTR RC DFR DWG AVAILABLE
[5 empty] | 499 | [16 empty] | 11KV, CHAMBAL RIVER, LT END
96 | AP20/0 | 20/0 | DD60+6 | 52° 09' 12"RT |  | 499 | 36564.428 | 406.4 | 76.72 | 876 | 438 | 253 | 182 | 435 | 252 | 183 | 435 | 75°30'9.71"E | 24° 5'58.26"N | 551091.52 | 2665336.02 | Raised Chimney | Dhandi | Suwasara | MP | 2.5 | 1 | 0 | 1.5 | 1 M & 1.5 RC WFR FDN DWG Available
[5 empty] | 377 | [16 empty] | 11KV, LT
97 |  | 20/1 | DA(-)3 |  |  |  | 36941.428 | 416.61 | 69.5 | 820 | 410 | 195 | 214 | 409 | 194 | 216 | 410 | 75°30'22.74"E | 24° 5'55.55"N | 551459.58 | 2665254.43 |  | Dhandi | Suwasara | MP
[5 empty] | 443 | [16 empty] | CT, POND, WELL
98 |  | 20/2 | DA(-)3 |  |  |  | 37384.428 | 418.169 | 69.5 | 787 | 393.5 | 229 | 161 | 390 | 227 | 164 | 391 | 75°30'38.06"E | 24° 5'52.38"N | 551892.08 | 2665158.56 |  | Dhandi | Suwasara | MP
[5 empty] | 344 | [16 empty] | CT, POND, HUT
99 | AP21/0 | 21/0 | DC2+0 | 24° 53' 25"RT |  | 1164 | 37728.428 | 416.971 | 70.72 | 734 | 367 | 184 | 250 | 434 | 180 | 233 | 413 | 75°30'49.948"E | 24°5'49.936"N | 552227.864 | 2665084.121 |  | Dhandi | Suwasara | MP
[5 empty] | 390 | [16 empty] | 11KV, LT, NALA
100 |  | 21/1 | DA(-)3 |  |  |  | 38118.428 | 410.114 | 69.5 | 742 | 371 | 141 | 160 | 301 | 159 | 165 | 324 | 75°31'0.893"E | 24°5'42.199"N | 552537.73 | 2664847.302 |  | Haripura | Suwasara | MP
[5 empty] | 352 | [16 empty] | CT
101 |  | 21/2 | DA+0 |  |  |  | 38470.428 | 409.768 | 72.5 | 751.46 | 375.73 | 192 | 204 | 396 | 188 | 207 | 395 | 75°31'10.77"E | 24°5'35.216"N | 552817.404 | 2664633.558 |  | Haripura | Suwasara | MP
297.36
102 | AP21A/0 | 21A/0 | DD60+0 |  |  | 1039.36 | 38767.788
420
103 |  | 21A/1 | DA+6 |  |  |  | 39187.788
416.91
104 | AP22/0 | 22/0 | DD60+0 |  |  | 836.91 | 39604.698
397.53
105 | AP22A/0 | 22A/0 | DC2+3 |  |  | 397.53 | 40002.228
430
106 |  | 22A/1 | DA+6 |  |  |  | 40432.228
[5 empty] | 399.46 | [16 empty] | WELL
107 | AP23/0 | 23/0 | DC1+0 |  |  | 829.46 | 40831.688 | 411.604 | 72.5 | 733.46 | 366.73 | 223 | 118 | 341 | 220 | 143 | 363 | 75°31'22.724"E | 24°5'26.764"N | 553155.873 | 2664374.879 |  | Haripura | Suwasara | MP
[5 empty] | 334 | [16 empty] | CT
108 |  | 23/1 | DA+3 |  |  |  | 41165.688 | 433.578 | 75.5 | 739.89 | 369.945 | 197 | 205 | 402 | 195 | 205 | 400 | 75°32'22.825"E | 24°5'1.577"N | 554855.75 | 2663606.682 |  | Haripura | Suwasara | MP
[5 empty] | 405.89 | [16 empty] | 11KV, WELL, METAL ROAD
109 | AP24/0 | 24/0 | DC2+3 | 23° 2' 13"LT |  | 739.89 | 41571.578 | 433.22 | 73.72 | 790.89 | 395.445 | 201 | 195 | 396 | 202 | 195 | 397 | 75°32'33.491"E | 24°4'52.741"N | 555157.958 | 2663336.092 | Raised Chimney | Haripura | Suwasara | MP | 1 | 2 | 1 | 0 | RC DWG AVIALBLE
[5 empty] | 385 | [16 empty] | ORANGE GARDEN, 11KV, CT, WELL,
110 |  | 24/1 | DA+0 |  |  |  | 41956.578 | 435.751 | 72.5 | 785 | 392.5 | 190 | 190 | 380 | 191 | 194 | 385 | 75°32'46.381"E | 24°4'48.661"N | 555522.411 | 2663211.998 |  | Haripura | Suwasara | MP
[5 empty] | 400 | [16 empty] | LT,CT, WELL, 11KV
111 |  | 24/2 | DA+0 |  |  |  | 42356.578 | 437.648 | 72.5 | 839 | 419.5 | 210 | 174 | 384 | 208 | 188 | 396 | 75°32'59.773"E | 24°4'44.42"N | 555901.063 | 2663083.069 |  | Haripura | Suwasara | MP
[5 empty] | 439 | [16 empty] | 33KV
112 |  | 24/3 | DA+6 |  |  |  | 42795.578 | 441.109 | 78.5 | 839 | 419.5 | 266 | 224 | 490 | 252 | 217 | 469 | 75°33'14.471"E | 24°4'39.767"N | 556316.633 | 2662941.569 |  | Haripura | Suwasara | MP
[5 empty] | 400 | [16 empty] | 11KV, 33KV
113 |  | 24/4 | DA(-)3 |  |  |  | 43195.578 | 445.75 | 69.5 | 691 | 345.5 | 177 | 174 | 351 | 185 | 166 | 351 | 75°33'27.862"E | 24°4'35.526"N | 556695.285 | 2662812.64 |  | Haripura | Suwasara | MP
[5 empty] | 291 | [16 empty] | 11KV, 33KV, SH-8 ROAD
114 |  | 24/5 | DA(-)3 |  |  |  | 43486.578 | 441.826 | 69.5 | 681 | 340.5 | 117 | 172 | 289 | 126 | 179 | 305 | 75°33'37.604"E | 24°4'32.44"N | 556970.754 | 2662718.844 |  | Haripura | Suwasara | MP
[5 empty] | 390 | [16 empty] | 33KV, CT, WELL
115 |  | 24/6 | DA+3 |  |  |  | 43876.578 | 440.116 | 75.5 | 793 | 396.5 | 219 | 223 | 442 | 212 | 217 | 429 | 75°33'50.661"E | 24°4'28.305"N | 557339.94 | 2662593.138 |  | Haripura | Suwasara | MP
[5 empty] | 403 | [16 empty] | CT, BORE
116 |  | 24/7 | DA+0 |  |  |  | 44279.578 | 439.023 | 72.5 | 825 | 412.5 | 180 | 180 | 360 | 187 | 190 | 377 | 75°34'4.152"E | 24°4'24.032"N | 557721.432 | 2662463.242 |  | Haripura | Suwasara | MP
[5 empty] | 422 | [16 empty] | 33KV, WELL, 11KV, CT
117 |  | 24/8 | DA+6 |  |  |  | 44701.578 | 439.161 | 78.5 | 811 | 405.5 | 242 | 257 | 499 | 233 | 238 | 471 | 75°34'18.279"E | 24°4'19.556"N | 558120.91 | 2662327.222 |  | Kantiya | Suwasara | MP
[5 empty] | 389 | [16 empty] | 11KV, METAL ROAD
118 |  | 24/9 | DA(-)1.5 |  |  |  | 45090.578 | 435.355 | 71 | 825 | 412.5 | 133 | 206 | 339 | 152 | 210 | 362 | 75°34'31.301"E | 24°4'15.431"N | 558489.149 | 2662201.839 |  | Kantiya | Suwasara | MP
[5 empty] | 436 | [16 empty] | LT, NALA, CT
119 |  | 24/10 | DA+1.5 |  |  |  | 45526.578 | 434.97 | 74 | 816 | 408 | 231 | 183 | 414 | 228 | 185 | 413 | 75°34'45.896"E | 24°4'10.806"N | 558901.879 | 2662061.306 |  | Kantiya | Suwasara | MP
[5 empty] | 380 | [16 empty] | WELL, CT, 11KV
120 |  | 24/11 | DA+0 |  |  |  | 45906.578 | 437.855 | 72.5 | 825 | 412.5 | 198 | 154 | 352 | 196 | 175 | 371 | 75°34'58.616"E | 24°4'6.775"N | 559261.599 | 2661938.823 |  | Kantiya | Suwasara | MP
[5 empty] | 445 | [16 empty] | CT, WELL, NALA
121 | AP25/0 | 25/0 | DC2+18 | 12° 27' 1"RT |  | 4780 | 46351.578 | 434.424 | 88.72 | 665 | 332.5 | 293 | 140 | 433 | 272 | 123 | 395 | 75°35'13.522"E | 24°4'2.051"N | 559683.148 | 2661795.288 |  | Kantiya | Suwasara | MP
[5 empty] | 220 | [16 empty] | 220 KV DC MANDSAUR - NIPANIA TL MPPTCL T83-84, LT, ORANGE GARDEN
122 | AP26/0 | 26/0 | DC2+12 | 19° 44' 39"LT |  | 220 | 46571.578 | 438.091 | 82.72 | 655 | 327.5 | 80 | 252 | 332 | 97 | 244 | 341 | 75°35'20.159"E | 24°3'58.318"N | 559871.045 | 2661681.252 |  | Kantiya | Suwasara | MP
[5 empty] | 435 | [16 empty] | ORANGE GARDEN, CT, WELL
123 |  | 26/1 | DA+1.5 |  |  |  | 47006.578 | 440.005 | 74 | 840 | 420 | 184 | 187 | 371 | 193 | 191 | 384 | 75°35'35.24"E | 24°3'55.438"N | 560297.298 | 2661594.456 |  | Ruparail | Suwasara | MP
[5 empty] | 405 | [16 empty] | CT, LT, 11KV, WELL
124 |  | 26/2 | DA+6 |  |  |  | 47411.578 | 439.354 | 78.5 | 839 | 419.5 | 219 | 235 | 454 | 216 | 231 | 447 | 75°35'49.281"E | 24°3'52.755"N | 560694.154 | 2661513.645 |  | Ruparail | Suwasara | MP
[5 empty] | 434 | [16 empty] | METAL ROAD, 11KV, WELL, POND, CT, LT
125 |  | 26/3 | DA+6 |  |  |  | 47845.578 | 434.871 | 78.5 | 814 | 407 | 200 | 216 | 416 | 205 | 210 | 415 | 75°36'4.327"E | 24°3'49.881"N | 561119.427 | 2661427.049 |  | Ruparail | Suwasara | MP
[5 empty] | 380 | [16 empty] | CT, NALA, HUT, WELL, BARGAD TREE
126 |  | 26/4 | DA(-)3 |  |  |  | 48225.578 | 438.149 | 69.5 | 759 | 379.5 | 165 | 121 | 286 | 171 | 138 | 309 | 75°36'17.5"E | 24°3'47.364"N | 561491.785 | 2661351.227 |  | Ruparail | Suwasara | MP
379
127 | AP27/0 | 27/0 | DB2+9 | 13° 19' 59"RT |  | 2033 | 48604.578 | 441.418 | 79.72 | 858 | 429 | 275 | 258 | 533 | 250 | 255 | 505 | 75°36'30.634"E | 24°3'44.854"N | 561863.017 | 2661275.634 |  | Devriya_vijay | Suwasara | MP
[5 empty] | 479 | [16 empty] | WELL, CT, 11KV, PIPAL TREE
128 |  | 27/1 | DB1+9 |  |  | 479 | 49083.578 | 435.383 | 79.72 | 943 | 471.5 | 221 | 267 | 488 | 225 | 257 | 482 | 75036'45.962"E | 2403'38.263"N | 562296.784 | 2661074.813 |  | Devriya_vijay | Suwasara | MP
[5 empty] | 464 | [16 empty] | NALA, 11KV, SAMADHI, LT END, 11KV TF
129 |  | 27/2 | DA+0 |  |  |  | 49547.578 | 438.024 | 72.5 | 840 | 420 | 198 | 171 | 369 | 209 | 177 | 386 | 75°37'0.841"E | 24°3'31.865"N | 562717.849 | 2660879.874 |  | Devriya_vijay | Suwasara | MP
[5 empty] | 376 | [16 empty] | MAHUA TREE, GUAVA GARDEN, FENCE, WELL, PUMPHOUSE, LT, METAL ROAD, 11KV, NEW GARDEN
130 |  | 27/3 | DA+1.5 |  |  |  | 49923.578 | 439.558 | 74 | 756 | 378 | 206 | 202 | 408 | 200 | 199 | 399 | 75°37'12.898"E | 24°3'26.68"N | 563059.056 | 2660721.906 |  | Devriya_vijay | Suwasara | MP
[5 empty] | 380 | [16 empty] | NEW GARDEN, WELL, CT, 11KV, PIPAL TREE, LT
131 |  | 27/4 | DA(-)3 |  |  |  | 50303.578 | 441.94 | 69.5 | 732 | 366 | 178 | 159 | 337 | 182 | 163 | 345 | 75°37'25.083"E | 24°3'21.439"N | 563403.893 | 2660562.257 |  | Devriya_vijay | Suwasara | MP
[5 empty] | 352 | [16 empty] | NALA, WELL, LT, WELL
132 |  | 27/5 | DA(-)1.5 |  |  |  | 50655.578 | 443.323 | 71 | 713 | 356.5 | 193 | 122 | 315 | 189 | 137 | 326 | 75°37'36.37"E | 24° 3'16.58"N | 563723.32 | 2660414.37 |  | Devriya_vijay | Suwasara | MP
[5 empty] | 361 | [16 empty] | NALA, 11KV, METAL ROAD, WELL, BORE, CT, 11KV T-POINT, LT
133 | AP28/0 | 28/0 | DD45+6 | 41° 48' 21"RT |  | 1933 | 51016.578 | 445.747 | 76.72 | 613 | 306.5 | 241 | -28 | 213 | 222 | 53 | 275 | 75°37'47.94"E | 24°3'11.608"N | 564050.781 | 2660262.768 |  | Devriya_vijay | Suwasara | MP
[5 empty] | 252 | [16 empty] | LT, 220 KV D GUJARKHEDI-MANDSAUR TL MPPTCL (T57-58)
134 | AP29/0 | 29/0 | DD45+18 | 34° 38' 47"LT |  | 252 | 51268.578 | 448.058 | 88.72 | 646 | 323 | 281 | 265 | 546 | 199 | 244 | 443 | 75°37'51.439"E | 24°3'4.074"N | 564150.632 | 2660031.49 |  | Devriya_vijay | Suwasara | MP
[5 empty] | 394 | [16 empty] | POND, CT, PIPAL TREE, LT, WELL,
135 |  | 29/1 | DA+1.5 |  |  |  | 51662.578 | 452.242 | 74 | 783 | 391.5 | 130 | 180 | 310 | 152 | 185 | 337 | 75°38'3.236"E | 24°2'57.236"N | 564484.756 | 2659822.69 |  | Devriya_vijay | Suwasara | MP
[5 empty] | 389 | [16 empty] | METAL ROAD, WELL, 11KV, WELL, PUMPHOUSE, LT, BORE, 11KV TF
136 |  | 29/2 | DA+1.5 |  |  |  | 52051.578 | 454.842 | 74 | 788 | 394 | 209 | 220 | 429 | 205 | 214 | 419 | 75°38'14.882"E | 24°2'50.484"N | 564814.639 | 2659616.54 |  | Kishorpura | Suwasara | MP
[5 empty] | 399 | [16 empty] | WELL, BARGAD TREE, CT, 11KV, LT, METAL ROAD, TF, BORE, HOUSE
137 | AP30/0 | 30/0 | DC1+0 | 15° 16' 50"RT |  | 1182 | 52450.578 | 452.57 | 70.72 | 791 | 395.5 | 179 | 208 | 387 | 186 | 204 | 390 | 75°38'26.821"E | 24°2'43.563"N | 565152.813 | 2659405.21 |  | Kishorpura | Suwasara | MP
[5 empty] | 392 | [16 empty] | BORE, NALA, SAMADHI, WELL, ORANGE GARDEN, 11KV, LT
138 |  | 30/1 | DA+1.5 |  |  |  | 52842.578 | 449.024 | 74 | 755 | 377.5 | 185 | 210 | 395 | 189 | 201 | 390 | 75°38'36.19"E | 24°2'34.16"N | 565418.739 | 2659117.205 |  | Kishorpura | Suwasara | MP
[5 empty] | 363 | [16 empty] | WELL, CT, NALA, LT
139 |  | 30/2 | DA+0 |  |  |  | 53205.578 | 445.864 | 72.5 | 742 | 371 | 154 | 199 | 353 | 163 | 196 | 359 | 75038'44.865"E | 2402'25.451"N | 565664.994 | 2658850.504 |  | Kishorpura | Suwasara | MP
[5 empty] | 379 | [16 empty] | BORE, NALA, LT, WELL
140 | AP31/0 | 31/0 | DD60+0 | 43° 50' 25"LT |  | 1134 | 53584.578 | 444.125 | 70.72 | 605 | 302.5 | 180 | -12 | 168 | 183 | 57 | 240 | 75°38'53.916"E | 24°2'16.365"N | 565921.935 | 2658572.231 |  | Kishorpura | Suwasara | MP
[5 empty] | 226 | [16 empty] | WELL, DOUBLE TRACK ELECTRIFIED RAILWAY LINE, RAILWAY POLES 770/5 & 770/6
141 | AP32/0 | 32/0 | DD60+9 | 22° 23' 30"RT |  | 226 | 53810.578 | 445.949 | 79.72 | 725 | 362.5 | 238 | 237 | 475 | 169 | 240 | 409 | 75°39'1.902"E | 24°2'15.89"N | 566147.58 | 2658558.659 |  | Kishorpura | Suwasara | MP
[5 empty] | 499 | [16 empty] | WELL, CT, LT, 11KV, PUMPHOUSE
142 |  | 32/1 | DB1+9 |  |  | 499 | 54309.578 | 449.79 | 79.72 | 945 | 472.5 | 264 | 246 | 510 | 262 | 240 | 502 | 75°39'17.767"E | 24°2'8.752"N | 566596.71 | 2658341.213 |  | Nathu_Khedi | Suwasara | MP
[5 empty] | 446 | [16 empty] | ORANGE GARDEN, 11KV, WELL, MAHUA TREE, LT, BOREWELL
143 |  | 32/2 | DA+1.5 |  |  |  | 54755.578 | 452.46 | 74 | 840 | 420 | 201 | 207 | 408 | 208 | 204 | 412 | 75°39'31.946"E | 24°2'2.372"N | 566998.138 | 2658146.863 |  | Nathu_Khedi | Suwasara | MP
[5 empty] | 394 | [16 empty] | 11KV, BORE, WELL, HUT, METAL ROAD
144 |  | 32/3 | DA+1.5 |  |  |  | 55149.578 | 450.685 | 74 | 785 | 392.5 | 188 | 218 | 406 | 191 | 212 | 403 | 75°39'44.471"E | 24°1'56.736"N | 567352.762 | 2657975.172 |  | Dhabla_bhagwan | Suwasara | MP
[5 empty] | 391 | [16 empty] | METAL ROAD
145 |  | 32/4 | DA+0 |  |  |  | 55540.578 | 447.98 | 72.5 | 800 | 400 | 173 | 210 | 383 | 180 | 209 | 389 | 75°39'56.901"E | 24°1'51.142"N | 567704.686 | 2657804.789 |  | Dhabla_bhagwan | Suwasara | MP
[5 empty] | 409 | [16 empty] | LT, CT
146 |  | 32/5 | DA+1.5 |  |  |  | 55949.578 | 445.435 | 74 | 788 | 394 | 199 | 187 | 386 | 201 | 188 | 389 | 75°40'9.903"E | 24°1'45.29"N | 568072.811 | 2657626.562 |  | Dhabla_bhagwan | Suwasara | MP
[5 empty] | 379 | [16 empty] | NALA, LT, WELL
147 |  | 32/6 | DA+0 |  |  |  | 56328.578 | 447.45 | 72.5 | 743 | 371.5 | 193 | 209 | 402 | 192 | 201 | 393 | 75°40'21.951"E | 24°1'39.868"N | 568413.934 | 2657461.407 |  | Dhabla_bhagwan | Suwasara | MP
[5 empty] | 364 | [16 empty] | METAL ROAD, LT
148 |  | 32/7 | DA(-)1.5 |  |  |  | 56692.578 | 444.336 | 71 | 811 | 405.5 | 156 | 187 | 343 | 164 | 199 | 363 | 75°40'33.521"E | 24°1'34.659"N | 568741.557 | 2657302.79 |  | Dhabla_bhagwan | Suwasara | MP
[5 empty] | 447 | [16 empty] | NALA, CT
149 | AP33/0 | 33/0 | DD45+9 | 30° 25' 18"LT |  | 2830 | 57139.578 | 441.528 | 79.72 | 704 | 352 | 260 | 171 | 431 | 250 | 150 | 400 | 75°40'47.721"E | 24°1'28.267"N | 569143.623 | 2657108.13 |  | Bhaisola | Suwasara | MP
[5 empty] | 257 | [16 empty] | 132KV D/C SUWASARA - BADOD MPPTCL (T264-265), LT
150 | AP34/0 | 34/0 | DC1+3 | 18° 17' 56"RT |  | 257 | 57396.578 | 443.161 | 73.72 | 489 | 244.5 | 86 | 127 | 213 | 108 | 123 | 231 | 75°40'56.794"E | 24°1'28.895"N | 569399.846 | 2657128.691 |  | Bhaisola | Suwasara | MP
[5 empty] | 232 | [16 empty] | CT, WELL, METAL ROAD, 11KV
151 |  | 34/1 | DA+3 |  |  |  | 57628.578 | 442.052 | 75.5 | 597 | 298.5 | 106 | 214 | 320 | 109 | 204 | 313 | 75°41'4.763"E | 24°1'27.072"N | 569625.235 | 2657073.702 |  | Bhaisola | Suwasara | MP
[5 empty] | 365 | [16 empty] | WELL, CT, LT
152 |  | 34/2 | DA(-)3 |  |  |  | 57993.578 | 442.805 | 69.5 | 744 | 372 | 151 | 134 | 285 | 162 | 153 | 315 | 75°41'17.3"E | 24°1'24.203"N | 569979.835 | 2656987.189 |  | Bhaisola | Suwasara | MP
[5 empty] | 379 | [16 empty] | CT, WELL, PUMPHOUSE, NALA
153 |  | 34/3 | DA+6 |  |  |  | 58372.578 | 443.481 | 78.5 | 819 | 409.5 | 246 | 221 | 467 | 227 | 221 | 448 | 75°41'30.318"E | 24°1'21.223"N | 570348.035 | 2656897.357 |  | Bhaisola | Suwasara | MP
[5 empty] | 440 | [16 empty] | NALA, 11KV, LT
154 | AP35/0 | 35/0 | DB2+3 | 11° 11' 51"LT |  | 1416 | 58812.578 | 446.279 | 73.72 | 661 | 330.5 | 219 | 155 | 374 | 220 | 130 | 350 | 75°41'45.426"E | 24°1'17.765"N | 570775.331 | 2656793.108 |  | Tarnod | Suwasara | MP
[5 empty] | 221 | [16 empty] | NALA, NH752D
155 | AP36/0 | 36/0 | DC2+0 | 22° 26' 05"RT |  | 221 | 59033.578 | 445.52 | 70.72 | 616 | 308 | 77 | 163 | 240 | 89 | 173 | 262 | 75°41'53.23"E | 24° 1'17.40"N | 570996.14 | 2656783.42 |  | Tarnod | Suwasara | MP
[5 empty] | 395 | [16 empty] | CART TRACK, LT LINE, WELL, NALA, ORANGE GARDEN
156 |  | 36/1 | DA+0 |  |  |  | 59428.578 | 451.591 | 72.5 | 751 | 375.5 | 232 | 176 | 408 | 222 | 177 | 399 | 75°42'5.888"E | 24°1'11.94"N | 571354.287 | 2656616.808 |  | Tarnod | Suwasara | MP
[5 empty] | 356 | [16 empty] | CART TRACK
157 |  | 36/2 | DA+0 |  |  |  | 59784.578 | 451.993 | 72.5 | 760 | 380 | 181 | 204 | 385 | 180 | 204 | 384 | 75°42'17.287"E | 24°1'7.005"N | 571677.069 | 2656466.649 |  | Chapa_khedi | Suwasara | MP
[5 empty] | 404 | [16 empty] | CART TRACK, LT LINE END, WELL, ORANGE GARDEN
158 |  | 36/3 | DA+0 |  |  |  | 60188.578 | 451.707 | 72.5 | 784 | 392 | 201 | 163 | 364 | 202 | 171 | 373 | 75°42'30.223"E | 24°1'1.405"N | 572043.373 | 2656296.245 |  | Chapa_khedi | Suwasara | MP
[5 empty] | 380 | [16 empty] | 11 KV LINE, BARGAD TREE, CART TRACK
159 |  | 36/4 | DA+3 |  |  |  | 60568.578 | 453.658 | 75.5 | 840 | 420 | 218 | 211 | 429 | 210 | 218 | 428 | 75°42'42.39"E | 24°0'56.137"N | 572387.916 | 2656135.964 |  | Chapa_khedi | Suwasara | MP
[5 empty] | 460 | [16 empty] | CART TRACK, LT LINE, WELL, NALA, 11 KV LINE
160 |  | 36/5 | DA+6 |  |  |  | 61028.578 | 454.814 | 78.5 | 840 | 420 | 250 | 209 | 459 | 244 | 204 | 448 | 75°42'57.118"E | 24°0'49.76"N | 572804.995 | 2655941.939 |  | Chapa_khedi | Suwasara | MP
[5 empty] | 380 | [16 empty] | NALA
161 |  | 36/6 | DA(-)1.5 |  |  |  | 61408.578 | 458.852 | 71 | 793 | 396.5 | 171 | 155 | 326 | 177 | 171 | 348 | 75°43'9.284"E | 24°0'44.491"N | 573149.538 | 2655781.658 |  | Chapa_khedi | Suwasara | MP
[5 empty] | 413 | [16 empty] | CART TRACK, WELL, HUT
162 |  | 36/7 | DA+3 |  |  |  | 61821.578 | 464.541 | 75.5 | 826 | 413 | 259 | 221 | 480 | 244 | 217 | 461 | 75°43'22.506"E | 24°0'38.765"N | 573524.002 | 2655607.458 |  | Chapa_khedi | Suwasara | MP
[5 empty] | 413 | [16 empty] | NALA
163 |  | 36/8 | DA+0 |  |  |  | 62234.578 | 464.789 | 72.5 | 840 | 420 | 193 | 136 | 329 | 197 | 160 | 357 | 75°43'35.728"E | 24°0'33.038"N | 573898.466 | 2655433.257 |  | Khejdiya_bhup | Suwasara | MP
[5 empty] | 427 | [16 empty] | LT LINE, 11 KV LINE, METAL ROAD, WELL
164 | AP37/0 | 37/0 | DD45+12 | 41° 25' 41"LT |  | 3628 | 62661.578 | 468.46 | 82.72 | 647 | 323.5 | 291 | 148 | 439 | 269 | 127 | 396 | 75°43'49.398"E | 24°0'27.117"N | 574285.623 | 2655253.152 |  | Khejdiya_bhup | Suwasara | MP
[5 empty] | 220 | [16 empty] | 220 KV BAROD SUWASARA MPPTCL (T301-302)
165 | AP38/0 | 38/0 | DD45+9 | 37° 39' 42"RT |  | 220 | 62881.578 | 468.335 | 79.72 | 650 | 325 | 73 | 273 | 346 | 94 | 255 | 349 | 75°43'56.877"E | 24°0'29.111"N | 574496.585 | 2655315.563 |  | Khejdiya_bhup | Suwasara | MP
[5 empty] | 430 | [16 empty] | WELL, CART TRACK
166 |  | 38/1 | DA(-)3 |  |  |  | 63311.578 | 468.902 | 69.5 | 774 | 387 | 158 | 149 | 307 | 177 | 157 | 334 | 75°44'11.039"E | 24°0'23.991"N | 574897.535 | 2655160.194 |  | Khejdiya_bhup | Suwasara | MP
[5 empty] | 344 | [16 empty] | CART TRACK
167 |  | 38/2 | DA+0 |  |  |  | 63655.578 | 469.53 | 72.5 | 717 | 358.5 | 195 | 191 | 386 | 188 | 190 | 378 | 75°44'22.368"E | 24°0'19.896"N | 575218.294 | 2655035.899 |  | Borkhedi | Suwasara | MP
[5 empty] | 373 | [16 empty] | CART TRACK, LT LINE
168 |  | 38/3 | DA(-)3 |  |  |  | 64028.578 | 471.87 | 69.5 | 762 | 381 | 183 | 157 | 340 | 184 | 169 | 353 | 75°44'34.653"E | 24°0'15.454"N | 575566.095 | 2654901.126 |  | Borkhedi | Suwasara | MP
[5 empty] | 389 | [16 empty] | CART TRACK, 11 KV LINE, NALA, WELL
169 |  | 38/4 | DA+3 |  |  |  | 64417.578 | 472.761 | 75.5 | 833 | 416.5 | 233 | 196 | 429 | 221 | 205 | 426 | 75°44'47.464"E | 24°0'10.822"N | 575928.814 | 2654760.571 |  | Borkhedi | Suwasara | MP
[5 empty] | 444 | [16 empty] | LT LINE, 11 KV LINE, METAL ROAD, NALA, SAMADHI
170 |  | 38/5 | DA+6 |  |  |  | 64861.578 | 475.157 | 78.5 | 752 | 376 | 249 | 203 | 452 | 241 | 188 | 429 | 75°45'2.086"E | 24°0'5.534"N | 576342.818 | 2654600.144 | Raised Chimney | Borkhedi | Suwasara | MP | 2 | 1 | 0 | 1 | RC DWG AVIALBLE
[5 empty] | 308 | [16 empty] | 11 KV LINE, POND, LT LINE, CART TRACK, ORANGE GARDEN
171 |  | 38/6 | DA(-)3 |  |  |  | 65169.578 | 477.117 | 69.5 | 653 | 326.5 | 105 | 133 | 238 | 121 | 146 | 267 | 75°45'12.23"E | 24°0'1.866"N | 576630.009 | 2654488.856 |  | Borkhedi | Suwasara | MP
[5 empty] | 345 | [16 empty] | ORANGE GARDEN, NALA, CART TRACK
172 |  | 38/7 | DA+0 |  |  |  | 65514.578 | 480.413 | 72.5 | 770 | 385 | 212 | 173 | 385 | 200 | 186 | 386 | 75°45'23.591"E | 23°59'57.757"N | 576951.701 | 2654364.2 |  | Borkhedi | Suwasara | MP
[5 empty] | 425 | [16 empty] | NALA, CT, 11KV
173 |  | 38/8 | DA+6 |  |  |  | 65939.578 | 482.346 | 78.5 | 837 | 418.5 | 253 | 217 | 470 | 241 | 214 | 455 | 75°45'37.587"E | 23°59'52.695"N | 577347.989 | 2654210.638 |  | Borkhedi | Suwasara | MP
[5 empty] | 412 | [16 empty] | ORANGE GARDEN, WELL
174 | AP39/0 | 39/0 | DC1+0 | 17° 32' 52"RT |  | 3470 | 66351.578 | 486.321 | 70.72 | 811 | 405.5 | 196 | 156 | 352 | 200 | 170 | 370 | 75°45'51.149"E | 23°59'47.789"N | 577732.024 | 2654061.823 |  | Borkhedi | Suwasara | MP
[5 empty] | 399 | [16 empty] | Metal road
175 |  | 39/1 | DA+3 |  |  |  | 66750.578 | 491.543 | 75.5 | 819 | 409.5 | 244 | 235 | 479 | 231 | 228 | 459 | 75°46'2.117"E | 23°59'39.617"N | 578043.289 | 2653812.193 |  | Nipaniya(Devgarh) | Dag | RJ
[5 empty] | 420 | [16 empty] | 11kV line & Nala
176 |  | 39/2 | DA+0 |  |  |  | 67170.578 | 489.733 | 72.5 | 787 | 393.5 | 186 | 175 | 361 | 194 | 178 | 372 | 75°46'13.661"E | 23°59'31.016"N | 578370.936 | 2653549.424 |  | Nipaniya(Devgarh) | Dag | RJ
[5 empty] | 367 | [16 empty] | Nala
177 |  | 39/3 | DA+0 |  |  |  | 67537.578 | 491.245 | 72.5 | 721 | 360.5 | 193 | 151 | 344 | 190 | 159 | 349 | 75°46'23.749"E | 23°59'23.499"N | 578657.237 | 2653319.814 |  | Nipaniya(Devgarh) | Dag | RJ
[5 empty] | 354 | [16 empty] | Cart track
178 |  | 39/4 | DA+0 |  |  |  | 67891.578 | 495.569 | 72.5 | 753 | 376.5 | 203 | 221 | 424 | 195 | 214 | 409 | 75°46'33.478"E | 23°59'16.249"N | 578933.396 | 2653098.337 |  | Nipaniya(Devgarh) | Dag | RJ
[5 empty] | 399 | [16 empty] | Cart track
179 |  | 39/5 | DA+0 |  |  |  | 68290.578 | 491.707 | 72.5 | 774 | 387 | 179 | 209 | 388 | 186 | 202 | 388 | 75°46'44.445"E | 23°59'8.077"N | 579244.661 | 2652848.707 |  | Nipaniya(Devgarh) | Dag | RJ
[5 empty] | 375 | [16 empty] | LT line
180 |  | 39/6 | DC2+0 | TPT |  |  | 68665.578 | 488.049 | 70.72 | 755 | 377.5 | 167 | 206 | 373 | 174 | 201 | 375 | 75°46'54.751"E | 23°59'0.396"N | 579537.203 | 2652614.092 |  | Nipaniya(Devgarh) | Dag | RJ
[5 empty] | 380 | [16 empty] | 11kV line
181 |  | 39/7 | DA+0 |  |  |  | 69045.578 | 485.3 | 72.5 | 785 | 392.5 | 175 | 207 | 382 | 180 | 206 | 386 | 75°47'5.194"E | 23°58'52.613"N | 579833.645 | 2652376.349 |  | PeepalyaKhurd | Dag | RJ
[5 empty] | 405 | [16 empty] | 11kV line
182 |  | 39/8 | DA+3 |  |  |  | 69450.578 | 481.558 | 75.5 | 825 | 412.5 | 199 | 225 | 424 | 200 | 221 | 421 | 75°47'16.324"E | 23°58'44.317"N | 580149.591 | 2652122.965 |  | PatLai | Dag | RJ
420
183 |  | 39/9 | DA+3 |  |  |  | 69870.578 | 478.638 | 75.5 | 819 | 409.5 | 195 | 231 | 426 | 200 | 222 | 422 | 75°47'27.866"E | 23°58'35.714"N | 580477.238 | 2651860.196 |  | PatLai | Dag | RJ
[5 empty] | 399 | [16 empty] | 11kV line
184 |  | 39/10 | DA+0 |  |  |  | 70269.578 | 475.78 | 72.5 | 779 | 389.5 | 168 | 184 | 352 | 179 | 186 | 365 | 75°47'38.83"E | 23°58'27.541"N | 580788.502 | 2651610.565 |  | PatLai | Dag | RJ
[5 empty] | 380 | [16 empty] | 11kV line, LT line & Cart track
185 |  | 39/11 | DA+3 |  |  |  | 70649.578 | 473.953 | 75.5 | 795 | 397.5 | 197 | 220 | 417 | 195 | 217 | 412 | 75°47'49.272"E | 23°58'19.757"N | 581084.945 | 2651372.822 |  | PatLai | Dag | RJ
[5 empty] | 415 | [16 empty] | 11kV line & Nala
186 | AP40/0 | 40/0 | DC1+0 | 16° 39' 6"RT |  | 4713 | 71064.578 | 474.642 | 70.72 | 815 | 407.5 | 196 | 175 | 371 | 200 | 184 | 384 | 75°48'0.682"E | 23°58'11.25"N | 581408.913 | 2651113.004 |  | PatLai | Dag | RJ
[5 empty] | 400 | [16 empty] | Metal road & 11kV line
187 |  | 40/1 | DA+3 |  |  |  | 71464.578 | 476.332 | 75.5 | 792 | 396 | 226 | 201 | 427 | 218 | 199 | 417 | 75°48'8.657"E | 23°58'0.505"N | 581636.16 | 2650783.825 |  | PatLai | Dag | RJ
[5 empty] | 392 | [16 empty] | LT line
188 |  | 40/2 | DA+0 |  |  |  | 71856.578 | 478.562 | 72.5 | 779 | 389.5 | 192 | 210 | 402 | 194 | 205 | 399 | 75°48'16.471"E | 23°57'49.975"N | 581858.862 | 2650461.229 |  | PatLai | Dag | RJ
[5 empty] | 387 | [16 empty] | Metal road, Cart track & Nala
189 |  | 40/3 | DA+0 |  |  |  | 72243.578 | 475.59 | 72.5 | 733 | 366.5 | 177 | 178 | 355 | 183 | 177 | 360 | 75°48'24.186"E | 23°57'39.579"N | 582078.723 | 2650142.748 |  | ParthiGarh | Dag | RJ
346
190 | AP41/0 | 41/0 | DD45+0 | 41° 47' 29"LT |  | 1525 | 72589.578 | 474.76 | 70.72 | 746 | 373 | 168 | 168 | 336 | 170 | 178 | 348 | 75°48'31.085"E | 23°57'30.282"N | 582275.362 | 2649857.906 |  | ParthiGarh | Dag | RJ
[5 empty] | 400 | [16 empty] | 33kV line, Nala, Metal road, CT & LT line
191 |  | 41/1 | DA+6 |  |  |  | 72989.578 | 474.81 | 78.5 | 818 | 409 | 232 | 240 | 472 | 223 | 231 | 454 | 75°48'44.822"E | 23°57'27.153"N | 582664.164 | 2649763.92 |  | ParthiGarh | Dag | RJ
[5 empty] | 418 | [16 empty] | 11kV line, Orange garden, Well, Pipal Tree, Bargad Tree, Pumphouse, 11kV TF & Nala
192 |  | 41/2 | DA(-)1.5 |  |  |  | 73407.578 | 476.487 | 71 | 769 | 384.5 | 179 | 153 | 332 | 188 | 160 | 348 | 75°48'59.176"E | 23°57'23.884"N | 583070.461 | 2649665.705 |  | ParthiGarh | Dag | RJ
[5 empty] | 351 | [16 empty] | Nala, Well, Bargad Tree
193 |  | 41/3 | DA+1.5 |  |  |  | 73758.578 | 477.261 | 74 | 780 | 390 | 198 | 200 | 398 | 192 | 204 | 396 | 75°49'11.229"E | 23°57'21.138"N | 583411.635 | 2649583.233 |  | ParthiGarh | Dag | RJ
[5 empty] | 429 | [16 empty] | Metal road, Well, Bargad Tree & Nala
194 |  | 41/4 | DA+3 |  |  |  | 74187.578 | 478.635 | 75.5 | 840 | 420 | 230 | 213 | 443 | 226 | 211 | 437 | 75°49'25.961"E | 23°57'17.782"N | 583828.624 | 2649482.433 |  | Pipalya Kalan | Dag | RJ
[5 empty] | 411 | [16 empty] | 11kV line, Well, Nala
195 |  | 41/5 | DA+0 |  |  |  | 74598.578 | 480.441 | 72.5 | 792 | 396 | 199 | 151 | 350 | 201 | 163 | 364 | 75°49'40.074"E | 23°57'14.566"N | 584228.118 | 2649385.863 |  | Pipalya Kalan | Dag | RJ
[5 empty] | 381 | [16 empty] | 11kV line, Well, Pipal Tree, LT End, CT & Metal road
196 |  | 41/6 | DA+6 |  |  |  | 74979.578 | 481.366 | 78.5 | 840 | 420 | 231 | 215 | 446 | 219 | 220 | 439 | 75°49'53.157"E | 23°57'11.585"N | 584598.452 | 2649296.341 |  | Pipalya Kalan | Dag | RJ
[5 empty] | 459 | [16 empty] | Nala, Well, 11kV
197 |  | 41/7 | DA+6 |  |  |  | 75438.578 | 484.916 | 78.5 | 829 | 414.5 | 245 | 192 | 437 | 241 | 190 | 431 | 75°50'8.919"E | 23°57'7.992"N | 585044.601 | 2649188.493 |  | Dag | Dag | RJ
[5 empty] | 370 | [16 empty] | 11kV line & Cart track
198 |  | 41/8 | DA+3 |  |  |  | 75808.578 | 486.707 | 75.5 | 689.998 | 344.999 | 180 | 154 | 334 | 182 | 156 | 338 | 75d50'21.623"E | 23d57'5.095"N | 585404.229 | 2649101.505 |  | Dag | Dag | RJ
[5 empty] | 319.998 | [16 empty] | 11kV line, Well, Nala, House & Cart track
199 | AP42/0 | 42/0 | DD60+0 | 53° 59' 52"LT |  | 3538.998 | 76128.576 | 490.573 | 70.72 | 767.847 | 383.9235 | 166 | 188 | 354 | 164 | 197 | 361 | 75d50'32.611"E | 23d57'2.59"N | 585715.267 | 2649026.312 |  | Dag
[5 empty] | 447.849 | [16 empty] | Road, 11 KV line
200 | AP42A/0 | 42A/0 | DD45+9 | 30° 48' 25"RT |  | 447.849 | 76576.425 | 490.029 | 79.72 | 917.543 | 458.7715 | 261 | 236 | 497 | 252 | 237 | 489 | 75d50'44.737"E | 23d57'11.962"N | 586056.284 | 2649316.616 |  | Dag
[5 empty] | 469.694 | [16 empty] | 2 nos 11 KV line, CT
201 | AP42B/0 | 42B/0 | DD60+6 | 57° 32' 3"RT |  | 469.694 | 77046.119 | 492.861 | 76.72 | 662.554 | 331.277 | 235 | 122 | 357 | 236 | 107 | 343 | 75d51'1.137"E | 23d57'14.418"N | 586519.4 | 2649394.95 |  | Dag
[5 empty] | 192.86 | [16 empty] | 132 KV SC BHAWANI MANDI - DAG T/L (RRVPNL (T192-193) & Nala
202 | AP43/0 | 43/0 | DB1+3 | 4° 46' 49"LT |  | 192.86 | 77238.979 | 493.985 | 73.72 | 562.027 | 281.0135 | 72 | 161 | 233 | 87 | 169 | 256 | 75d51'5.678"E | 23d57'9.738"N | 586648.614 | 2649251.776 |  | Dag
[5 empty] | 369.167 | [16 empty] | 33kV line,2 nos 11kV line,SH-19A & Cart track
203 | AP44/0 | 44/0 | DB2+6 | 13° 21' 7"RT |  | 369.167 | 77608.146 | 495.397 | 76.72 | 776.167 | 388.0835 | 209 | 243 | 452 | 202 | 232 | 434 | 75d51'15.152"E | 23d57'1.476"N | 586917.93 | 2648999.282 |  | Dag
[5 empty] | 407 | [16 empty] | 33 KV line, Road. 11 KV line
204 |  | 44/1 | DA+0 |  |  |  | 78015.146 | 493.75 | 72.5 | 816.186 | 408.093 | 164 | 204 | 368 | 176 | 205 | 381 | 75d51'23.025"E | 23d56'50.396"N | 587142.535 | 2648659.869 |  | Dag
[5 empty] | 409.186 | [16 empty] | 11kV line & Cart track
205 | AP44/2 | 44/2 | DD45+0 | 31° 13' 13"LT |  | 816.186 | 78424.332 | 493.921 | 70.72 | 690.186 | 345.093 | 206 | 98 | 304 | 206 | 115 | 321 | 75d51'30.94"E | 23d56'39.257"N | 587368.347 | 2648318.632 |  | Dag
[5 empty] | 281 | [16 empty] | Orange garden & Nala, CT
206 |  | 44/3 | DA+0 |  |  |  | 78705.332 | 499.124 | 72.5 | 630.416 | 315.208 | 183 | 181 | 364 | 166 | 179 | 345 | 75d51'39.902"E | 23d56'35.305"N | 587622.425 | 2648198.61 |  | Dag
349.416
207 | AP45/0 | 45/0 | DC1+0 | 21° 45' 7"RT |  | 630.416 | 79054.748 | 498.148 | 70.72 | 756.416 | 378.208 | 169 | 216 | 385 | 172 | 213 | 385 | 75d51'51.046"E | 23d56'30.389"N | 587938.364 | 2648049.365 |  | Dag
[5 empty] | 407 | [16 empty] | Orange garden & Nala, CT
208 |  | 45/1 | DA(-)3 |  |  |  | 79461.748 | 498.836 | 69.5 | 730 | 365 | 192 | 147 | 339 | 196 | 152 | 348 | 75052'1.818"E | 23056'22.007"N | 588215.744 | 2647751.524 |  | Ganeshpura | Dag | RJ
323
209 |  | 45/2 | DA+0 |  |  |  | 79784.748 | 498.068 | 72.5 | 742 | 371 | 177 | 184 | 361 | 172 | 192 | 364 | 75052'10.674"E | 23056'15.117"N | 588435.876 | 2647515.153 |  | Ganeshpura | Dag | RJ
[5 empty] | 419 | [16 empty] | 11kV line, WELL, CT & Nala
210 |  | 45/3 | DA+0 |  |  |  | 80203.748 | 503.173 | 72.5 | 821 | 410.5 | 236 | 186 | 422 | 228 | 191 | 419 | 75052'21.419"E | 23056'6.756"N | 588721.434 | 2647208.531 |  | Ganeshpura | Dag | RJ
[5 empty] | 402 | [16 empty] | 11KV, WELL
211 |  | 45/4 | DA+1.5 |  |  |  | 80605.748 | 504.472 | 74 | 804.306 | 402.153 | 216 | 219 | 435 | 212 | 214 | 426 | 75052'31.516"E | 23055'58.898"N | 588995.406 | 2646914.348 |  | Chhaan(Chhaan Dug) | Dag | RJ
[5 empty] | 402.306 | [16 empty] | TAR ROAD
212 | AP45A/0 | 45A/0 | DC2+0 | 24° 2' 43"LT |  | 1953.31 | 81008.054 | 502.71 | 70.72 | 818.306 | 409.153 | 184 | 233 | 417 | 190 | 226 | 416 | 75052'42.557"E | 23055'50.305"N | 589269.587 | 2646619.942 |  | Daryavpura | Dag | RJ
[5 empty] | 416 | [16 empty] | 11KV
213 |  | 45A/1 | DA+1.5 |  |  |  | 81424.054 | 496.255 | 74 | 834.752 | 417.376 | 184 | 217 | 401 | 191 | 215 | 406 | 75052'52.95"E | 23055'42.217"N | 589652.54 | 2646457.451 | Raised Chimney Expected | Daryavpura | Dag | RJ | 2.5 | 1 | 0 | 0.5
418.752
214 | AP46/0 | 46/0 | DD45+0 | 30° 59' 37"LT |  | 834.75 | 81842.806 | 496.24 | 70.72 | 795.752 | 397.876 | 202 | 193 | 395 | 205 | 192 | 397 | 75053'4.931"E | 23055'32.891"N | 590038.026 | 2646293.886 |  | Dag | Dag | RJ
377
215 |  | 46/1 | DA+1.5 |  |  |  | 82219.806 | 494.033 | 74 | 817 | 408.5 | 185 | 279 | 464 | 186 | 262 | 448 | 75053'16.956"E | 23055'32.744"N | 590411.356 | 2646346.365 | Raised Chimney Expected | Dag | Dag | RJ | 1 | 1.5 | 0 | 0 | RC DWG AVIALBLE
440
216 |  | 46/2 | DA+3 |  |  |  | 82659.806 | 480.38 | 75.5 | 840.28 | 420.14 | 162 | 237 | 399 | 180 | 226 | 406 | 75053'33.154"E | 23055'32.544"N | 590847.072 | 2646407.613 |  | Ghati | Dag | RJ
[5 empty] | 400.28 | [16 empty] | 11kV line, Cart track, WELL
217 | AP46A/0 | 46A/0 | DC1+0 | 15° 18' 60"RT |  | 1217.28 | 83060.086 | 476.429 | 70.72 | 786.28 | 393.14 | 164 | 170 | 334 | 175 | 178 | 353 | 75053'46.452"E | 23055'32.38"N | 591243.455 | 2646463.333 |  | Ghati | Dag | RJ
386
218 |  | 46A/1 | DA+3 |  |  |  | 83446.086 | 477.492 | 75.5 | 806 | 403 | 216 | 274 | 490 | 209 | 253 | 462 | 75053'57.487"E | 23055'32.244"N | 591626.313 | 2646414.186 |  | Ghati | Dag | RJ
[5 empty] | 420 | [16 empty] | 11kV line, Nala & Cart track
219 |  | 46A/2 | DA(-)3 |  |  |  | 83866.086 | 471.289 | 69.5 | 757 | 378.5 | 147 | 167 | 314 | 169 | 168 | 337 | 75054'10.855"E | 23055'32.079"N | 592042.895 | 2646360.71 |  | Ghati | Dag | RJ
[5 empty] | 337 | [16 empty] | Nala
220 |  | 46A/3 | DA(-)3 |  |  |  | 84203.086 | 471.474 | 69.5 | 673.512 | 336.756 | 170 | 126 | 296 | 170 | 141 | 311 | 75054'24.932"E | 23055'31.904"N | 592377.152 | 2646317.802 |  | Ghati | Dag | RJ
[5 empty] | 336.512 | [16 empty] | Cart track, WELL & Nala
221 | AP47/0 | 47/0 | DC1+3 | 15° 21' 6"RT |  | 1479.51 | 84539.598 | 471.993 | 73.72 | 748.512 | 374.256 | 211 | 222 | 433 | 197 | 217 | 414 | 75054'39.466"E | 23055'31.724"N | 592710.926 | 2646274.956 |  | Ghati | Dag | RJ
[5 empty] | 412 | [16 empty] | Nala
222 |  | 47/1 | DA+0 |  |  |  | 84951.598 | 472.109 | 72.5 | 820 | 410 | 191 | 168 | 359 | 196 | 180 | 376 | 75°54'52.877"E | 23°55'26.482"N | 593091.104 | 2646116.183 |  | Dodhi | Dag | RJ
[5 empty] | 408 | [16 empty] | Cart track & Nala
223 |  | 47/2 | DA+6 |  |  |  | 85359.598 | 472.952 | 78.5 | 821 | 410.5 | 240 | 251 | 491 | 229 | 237 | 466 | 75°55'6.156"E | 23°55'21.29"N | 593467.591 | 2645958.952 |  | Dodhi | Dag | RJ
[5 empty] | 413 | [16 empty] | Cart track & Nala
224 |  | 47/3 | DA+0 |  |  |  | 85772.598 | 470.509 | 72.5 | 823 | 411.5 | 163 | 206 | 369 | 177 | 206 | 383 | 75°55'19.599"E | 23°55'16.035"N | 593848.692 | 2645799.794 |  | Chhaan(Chhaan Dug) | Dag | RJ
[5 empty] | 410 | [16 empty] | 11kV line
225 |  | 47/4 | DA+3 |  |  |  | 86182.598 | 467.308 | 75.5 | 816 | 408 | 204 | 212 | 416 | 205 | 209 | 414 | 75°55'32.943"E | 23°55'10.818"N | 594227.024 | 2645641.792 |  | Chhaan(Chhaan Dug) | Dag | RJ
[5 empty] | 406 | [16 empty] | Nala
226 |  | 47/5 | DA+3 |  |  |  | 86588.598 | 465.734 | 75.5 | 817 | 408.5 | 195 | 226 | 421 | 198 | 220 | 418 | 75°55'46.157"E | 23°55'5.651"N | 594601.665 | 2645485.332 |  | Chhaan(Chhaan Dug) | Dag | RJ
[5 empty] | 411 | [16 empty] | 11kV line
227 |  | 47/6 | DA+3 |  |  |  | 86999.598 | 461.972 | 75.5 | 783 | 391.5 | 186 | 215 | 401 | 193 | 207 | 400 | 75°55'59.533"E | 23°55'0.42"N | 594980.92 | 2645326.945 |  | Chhaan(Chhaan Dug) | Dag | RJ
[5 empty] | 372 | [16 empty] | Nala
228 |  | 47/7 | DA+0 |  |  |  | 87371.598 | 459.92 | 72.5 | 758 | 379 | 157 | 175 | 332 | 167 | 181 | 348 | 75°56'11.64"E | 23°54'55.685"N | 595324.188 | 2645183.587 |  | Chhaan(Chhaan Dug) | Dag | RJ
[5 empty] | 386 | [16 empty] | 11kV line & Cart track
229 |  | 47/8 | DA+0 |  |  |  | 87757.598 | 463.284 | 72.5 | 756 | 378 | 212 | 241 | 453 | 206 | 224 | 430 | 75°56'24.202"E | 23°54'50.772"N | 595680.374 | 2645034.834 |  | Chhaan(Chhaan Dug) | Dag | RJ
[5 empty] | 370 | [16 empty] | Cart track
230 |  | 47/9 | DA+0 |  |  |  | 88127.598 | 453.68 | 72.5 | 752 | 376 | 130 | 196 | 326 | 147 | 195 | 342 | 75°56'36.243"E | 23°54'46.062"N | 596021.796 | 2644892.247 |  | Chhaan(Chhaan Dug) | Dag | RJ
[5 empty] | 382 | [16 empty] | 11kV line & Cart track
231 |  | 47/10 | DA+3 |  |  |  | 88509.598 | 449.806 | 75.5 | 766 | 383 | 186 | 152 | 338 | 188 | 165 | 353 | 75°56'48.674"E | 23°54'41.199"N | 596374.291 | 2644745.036 |  | Chhaan(Chhaan Dug) | Dag | RJ
[5 empty] | 384 | [16 empty] | Nala
232 |  | 47/11 | DA+6 |  |  |  | 88893.598 | 453.993 | 78.5 | 766 | 383 | 233 | 208 | 441 | 220 | 203 | 423 | 75°57'1.171"E | 23°54'36.311"N | 596728.632 | 2644597.053 |  | Karnaliya | Badod | MP
[5 empty] | 382 | [16 empty] | 11kV line & Cart track
233 | AP48/0 | 48/0 | DB1+0 | 5° 44' 24"LT |  | 4736 | 89275.598 | 457.088 | 70.72 | 739 | 369.5 | 175 | 157 | 332 | 180 | 164 | 344 | 75°57'13.602"E | 23°54'31.447"N | 597081.153 | 2644449.831 |  | Karnaliya | Badod | MP
[5 empty] | 357 | [16 empty] | NALA, WELL, PIPAL TREE
234 |  | 48/1 | DA+0 |  |  |  | 89632.598 | 460.635 | 72.5 | 708 | 354 | 200 | 165 | 365 | 194 | 168 | 362 | 75°57'25.656"E | 23°54'27.993"N | 597422.687 | 2644345.89 |  | Karnaliya | Badod | MP
[5 empty] | 351 | [16 empty] | LT, BORE, HUT, SAMADHI, CT, 11KV
235 |  | 48/2 | DA(-)1.5 |  |  |  | 89983.598 | 463.934 | 71 | 764 | 382 | 187 | 212 | 399 | 183 | 210 | 393 | 75°57'37.506"E | 23°54'24.596"N | 597758.48 | 2644243.696 |  | Karnaliya | Badod | MP
[5 empty] | 413 | [16 empty] | NALA, WELL, PIPAL TREE, CT, BARGAD TREE
236 |  | 48/3 | DA+3 |  |  |  | 90396.598 | 458.511 | 75.5 | 836 | 418 | 202 | 202 | 404 | 204 | 206 | 410 | 75°57'51.45"E | 23°54'20.599"N | 598153.588 | 2644123.451 |  | Karnaliya | Badod | MP
[5 empty] | 423 | [16 empty] | 11KV, ORANGE GARDEN, LT, CT
237 |  | 48/4 | DA(-)1.5 |  |  |  | 90819.598 | 464.903 | 71 | 813 | 406.5 | 221 | 184 | 405 | 219 | 188 | 407 | 75°58'5.731"E | 23°54'16.505"N | 598558.262 | 2644000.294 |  | Karnaliya | Badod | MP
[5 empty] | 390 | [16 empty] | ORANGE GARDEN, 11KV, METAL ROAD, CT, NALA, WELL
238 |  | 48/5 | DA+0 |  |  |  | 91209.598 | 465.405 | 72.5 | 796 | 398 | 206 | 165 | 371 | 203 | 177 | 380 | 75°58'18.897"E | 23°54'12.73"N | 598931.367 | 2643886.745 |  | Karnaliya | Badod | MP
406
239 |  | 48/6 | DA+3 |  |  |  | 91615.598 | 469.712 | 75.5 | 796 | 398 | 242 | 257 | 499 | 230 | 238 | 468 | 75°58'32.604"E | 23°54'8.8"N | 599319.777 | 2643768.538 |  | Karnaliya | Badod | MP
[5 empty] | 390 | [16 empty] | CT, POND
240 |  | 48/7 | DA(-)1.5 |  |  |  | 92005.598 | 462.941 | 71 | 783 | 391.5 | 133 | 224 | 357 | 153 | 216 | 369 | 75°58'45.77"E | 23°54'5.025"N | 599692.882 | 2643654.989 | Raised Chimney | Gadhi | Badod | MP | 0 | 0 | 1.5 | 2 | RC DWG AVIALBLE
[5 empty] | 393 | [16 empty] | CT
241 |  | 48/8 | DA+0 |  |  |  | 92398.598 | 456.475 | 72.5 | 819 | 409.5 | 170 | 208 | 378 | 178 | 210 | 388 | 75°58'59.037"E | 23°54'1.22"N | 600068.856 | 2643540.567 |  | Gadhi | Badod | MP
[5 empty] | 426 | [16 empty] | LT, WELL, SAMADHI, CT, NALA, BARGAD TREE, ORANGE GARDEN
242 |  | 48/9 | DA+3 |  |  |  | 92824.598 | 454.559 | 75.5 | 833 | 416.5 | 219 | 231 | 450 | 218 | 223 | 441 | 75°59'13.418"E | 23°53'57.095"N | 600476.4 | 2643416.536 |  | Pipalya Chacha | Badod | MP
[5 empty] | 407 | [16 empty] | LT, NALA
243 | AP49/0 | 49/0 | DB1+0 | 5° 32' 52"RT |  | 3956 | 93231.598 | 452.437 | 70.72 | 811 | 405.5 | 177 | 164 | 341 | 186 | 175 | 361 | 75°59'27.158"E | 23°53'53.154"N | 600865.784 | 2643298.033 |  | Pipalya Chacha | Badod | MP
[5 empty] | 404 | [16 empty] | NALA, WELL, 11KV, METAL ROAD, LT
244 |  | 49/1 | DA+6 |  |  |  | 93635.598 | 453.942 | 78.5 | 822 | 411 | 241 | 251 | 492 | 230 | 239 | 469 | 75°59'40.32"E | 23°53'48.048"N | 601239.1 | 2643143.594 |  | Pipalya Chacha | Badod | MP
[5 empty] | 418 | [16 empty] | CT
245 |  | 49/2 | DA+0 |  |  |  | 94053.598 | 451.646 | 72.5 | 831 | 415.5 | 168 | 189 | 357 | 180 | 195 | 375 | 75°59'53.939"E | 23°53'42.764"N | 601625.352 | 2642983.804 |  | Pipalya Chacha | Badod | MP
[5 empty] | 413 | [16 empty] | WELL, LT, 11KV, NALA
246 |  | 49/3 | DA+3 |  |  |  | 94466.598 | 452.114 | 75.5 | 823 | 411.5 | 224 | 220 | 444 | 220 | 216 | 436 | 76°0'7.394"E | 23°53'37.543"N | 602006.985 | 2642825.925 |  | Pipalya Chacha | Badod | MP
[5 empty] | 410 | [16 empty] | PIPAL TREE
247 |  | 49/4 | DA+0 |  |  |  | 94876.598 | 452.147 | 72.5 | 836 | 418 | 190 | 226 | 416 | 195 | 222 | 417 | 76°0'20.751"E | 23°53'32.36"N | 602385.845 | 2642669.192 |  | Pipalya Chacha | Badod | MP
[5 empty] | 426 | [16 empty] | NALA
248 |  | 49/5 | DA+0 |  |  |  | 95302.598 | 449.67 | 72.5 | 823 | 411.5 | 201 | 167 | 368 | 205 | 176 | 381 | 76°0'34.629"E | 23°53'26.975"N | 602779.49 | 2642506.344 |  | Gangapur | Badod | MP
[5 empty] | 397 | [16 empty] | LT, NALA, 11KV
249 |  | 49/6 | DA+6 |  |  |  | 95699.598 | 449.78 | 78.5 | 801 | 400.5 | 231 | 108 | 339 | 222 |  | 358 | 76°0'47.562"E | 23°53'21.955"N | 603146.337 | 2642354.581 |  | Gyasari | Badod | MP
[5 empty] | 404 | [16 empty] | METAL ROAD
250 | AP50/0 | 50/0 | DC2+18 | 20° 9' 8"LT |  | 2872 | 96103.598 | 455.992 | 88.72 | 628 | 314 | 297 | 166 | 463 | 269 | 136 | 405 | 76°1'0.735"E | 23°53'16.843"N | 603519.994 | 2642200.001 |  | Gyasari | Badod | MP
[5 empty] | 224 | [16 empty] | 220KV S/C RUM-O2P-RTL T12-T13
251 | AP51/0 | 51/0 | DD45+9 | 31° 40' 27"RT |  | 224 | 96327.598 | 460.381 | 79.72 | 646 | 323 | 58 | 269 | 327 | 88 | 250 | 338 | 76°1'8.64"E | 23°53'16.495"N | 603743.631 | 2642190.931 |  | Gyasari | Badod | MP
[5 empty] | 422 | [16 empty] | NALA
252 |  | 51/1 | DA+0 |  |  |  | 96749.598 | 458.358 | 72.5 | 765 | 382.5 | 154 | 174 | 328 | 174 | 173 | 347 | 76°1'20.95"E | 23°53'8.742"N | 604093.499 | 2641954.973 |  | Gyasari | Badod | MP
[5 empty] | 343 | [16 empty] | SAMADHI, 11KV, CT
253 |  | 51/2 | DA(-)3 |  |  |  | 97092.598 | 461.041 | 69.5 | 703 | 351.5 | 170 | 189 | 359 | 171 | 186 | 357 | 76°1'30.956"E | 23°53'2.44"N | 604377.871 | 2641763.187 |  | Gyasari | Badod | MP
[5 empty] | 360 | [16 empty] | 11KV, LT, NALA
254 |  | 51/3 | DA(-)3 |  |  |  | 97452.598 | 459.485 | 69.5 | 699.682 | 349.841 | 171 | 121 | 292 | 175 | 138 | 313 | 7601'41.457"E | 23052'55.825"N | 604676.334 | 2641561.897 |  | Shyamgarh | Badod | MP
[5 empty] | 339.682 | [16 empty] | WELL, 11KV
255 | AP52/0 | 52/0 | DC2+0 | 24° 40' 51"LT |  | 1464.682 | 97792.28 | 464.21 | 70.72 | 748.682 | 374.341 | 219 | 152 | 371 | 203 | 168 | 371 | 7601'51.365"E | 23052'49.584"N | 604957.957 | 2641371.965 |  | Shyamgarh | Badod | MP
[5 empty] | 409 | [16 empty] | LT LINE/METAL ROAD/WELL
256 |  | 52/1 | DA+1.5 |  |  |  | 98201.28 | 472.854 | 74 | 800.063 | 400.0315 | 258 | 197 | 455 | 242 | 197 | 439 | 7602'5.618"E | 23052'47.335"N | 605361.563 | 2641305.759 |  | Shyamgarh | Badod | MP
[5 empty] | 391.063 | [16 empty] | CART TRACK
257 | AP53/0 | 53/0 | DB2+3 | 11° 13' 26"RT |  | 800.063 | 98592.343 | 471.117 | 73.72 | 777.138 | 388.569 | 195 | 251 | 446 | 195 | 233 | 428 | 7602'19.245"E | 23052'45.185"N | 605747.468 | 2641242.456 |  | Shyamgarh | Badod | MP
[5 empty] | 386.075 | [16 empty] | 11KV LINE/CART TRACK/SCHOOL/SCHOOL/CRICKET PITCH/CART TRACK/11KV LINE
258 | AP53A/0 | 53A/0 | DB1(-)1.5 | 4° 32' 26"RT |  | 386.075 | 98978.418 | 465.359 | 70.72 | 758.962 | 379.481 | 136 | 203 | 339 | 155 | 198 | 353 | 7602'31.992"E | 23052'40.695"N | 606109 | 2641107 |  | Saranga_khedi | Badod | MP
[5 empty] | 372.887 | [16 empty] | MUMBAI-MANMAD BIJWASAN GAS PIPE LINE(BPCL)
259 | AP53B/0 | 53B/0 | DB2(-)1.5 | 14° 18' 4"RT |  | 372.887 | 99351.305 | 462.537 | 70.72 | 705.887 | 352.9435 | 170 | 90 | 260 | 176 | 119 | 295 | 7602'43.891"E | 23052'35.475"N | 606446.73 | 2640948.939 |  | Saranga_khedi | Badod | MP
[5 empty] | 333 | [16 empty] | CART TRACK
260 |  | 53B/1 | DA+3 |  |  |  | 99684.305 | 469.401 | 75.5 | 690.142 | 345.071 | 243 | 100 | 343 | 215 | 129 | 344 | 7602'52.936"E | 23052'28.544"N | 606704.12 | 2640737.658 |  | Saranga_khedi | Badod | MP
[5 empty] | 357.142 | [16 empty] | 2 NOS. 11KV LINE
261 | AP54/0 | 54/0 | DC2+18 | 28° 2' 4"RT |  | 690.142 | 100041.447 | 467.149 | 88.72 | 591.313 | 295.6565 | 259 | 199 | 458 | 230 | 155 | 385 | 7603'2.636"E | 23052'21.111"N | 606980.17 | 2640511.06 |  | Maharundi | Badod | MP
[5 empty] | 234.171 | [16 empty] | 220KV DC BADOD-NALKHEDA TL(MPPTCL)
262 | AP55/0 | 55/0 | DD60+9 | 48° 36' 23"LT |  | 234.17 | 100275.618 | 467.785 | 79.72 | 586.171 | 293.0855 | 36 | 193 | 229 | 80 | 187 | 267 | 76d3'5.759"E | 23d52'14.06"N | 607070.102 | 2640294.846 | RC=1M | Maharundi | Badod | MP | 1 | 1 | 1 | 1 | RC DWG AVIALBLE IN WFR
[5 empty] | 352 | [16 empty] | LT LINE/CART TRACK
263 |  | 55/1 | DA+6 |  |  |  | 100627.618 | 469.093 | 78.5 | 705 | 352.5 | 159 | 118 | 277 | 166 | 140 | 306 | 76d3'17.509"E | 23d52'10.289"N | 607403.304 | 2640181.355 |  | Maharundi | Badod | MP
353
264 |  | 55/2 | DA+3 |  |  |  | 100980.618 | 481.401 | 75.5 | 705.606 | 352.803 | 236 | 106 | 342 | 214 | 132 | 346 | 76d3'29.292"E | 23d52'6.508"N | 607737.453 | 2640067.541 |  | Maharundi | Badod | MP
[5 empty] | 352.606 | [16 empty] | TAR ROAD/CART TRACK/11KV LINE
265 | AP56/0 | 56/0 | DB2+9 | 10° 8' 39"LT |  | 1057.61 | 101333.224 | 486.487 | 79.72 | 620.606 | 310.303 | 247 | 117 | 364 | 221 | 126 | 347 | 76d3'41.061"E | 23d52'2.731"N | 608071.229 | 2639953.855 | Benching / Raised Chimney Expected | Barda_Barkheda | Badod | MP | 0.5 | 2 | 1 | 0 | RC DWG NOT AVIALABLE
[5 empty] | 268 | [16 empty] | 11KV LINE
266 |  | 56/1 | DB1+18 |  |  | 268 | 101601.224 | 479.29 | 88.72 | 574 | 287 | 151 | 340 | 491 | 143 | 261 | 404 | 76d3'50.417"E | 23d52'1.353"N | 608336.17 | 2639913.479 | Benching / Raised Chimney Expected | Barda_Barkheda | Badod | MP | 0 | 0 | 2 | 3 | RC DWG NOT AVIALABLE
[5 empty] | 306 | [16 empty] | 11KV LINE/33KV LINE/METAL ROAD/11KV LINE
267 |  | 56/2 | DB1+6 |  |  | 306 | 101907.224 | 466.95 | 76.72 | 603 | 301.5 | -33 | 77 | 44 | 47 | 102 | 149 | 76d4'1.099"E | 23d51'59.781"N | 608638.677 | 2639867.377 |  | Barda_Barkheda | Badod | MP
[5 empty] | 297 | [16 empty] | WELL
268 |  | 56/3 | DA(-)3 |  |  |  | 102204.224 | 485.7 | 69.5 | 711.403 | 355.7015 | 221 | 185 | 406 | 196 | 193 | 389 | 76d4'11.466"E | 23d51'58.254"N | 608932.287 | 2639822.632 | Benching / Raised Chimney Expected | Barda_Barkheda | Badod | MP | 0 | 3 | 2.5 | 1 | RC DWG NOT AVIALABLE
[5 empty] | 414.403 | [16 empty] | NALA/LT LINE/WELL/CEMETERY AREA
269 | AP57/0 | 57/0 | DB2+0 | 8° 34' 46"RT |  | 711.4 | 102618.627 | 486.929 | 70.72 | 746.403 | 373.2015 | 230 | 349 | 579 | 223 | 278 | 501 | 76d4'25.932"E | 23d51'56.123"N | 609341.96 | 2639760.199 | Benching / Raised Chimney Expected | Barda_Barkheda | Badod | MP | 0.5 | 0 | 1 | 1 | RC DWG NOT AVIALABLE
[5 empty] | 332 | [16 empty] | WELL/NALA/WELL/NALA
270 |  | 57/1 | DB1+3 |  |  | 332 | 102950.627 | 457.348 | 73.72 | 742 | 371 | -16 | 202 | 186 | 56 | 203 | 259 | 76d4'37.115"E | 23d51'52.845"N | 609659.036 | 2639661.778 |  | Barda_Barkheda | Badod | MP
[5 empty] | 410 | [16 empty] | CART TRACK
271 |  | 57/2 | DA+1.5 |  |  |  | 103360.627 | 459.582 | 74 | 824 | 412 | 209 | 170 | 379 | 208 | 181 | 389 | 76d4'50.925"E | 23d51'48.797"N | 610050.606 | 2639540.233 |  | Barda_Barkheda | Badod | MP
[5 empty] | 414 | [16 empty] | NALA/LT LINE/WELL/CART TRACK/11KV LINE
272 |  | 57/3 | DA+3 |  |  |  | 103774.627 | 465.57 | 75.5 | 821 | 410.5 | 245 | 235 | 480 | 234 | 226 | 460 | 76d5'4.869"E | 23d51'44.708"N | 610445.996 | 2639417.503 |  | Barda_Barkheda | Badod | MP
[5 empty] | 407 | [16 empty] | CART TRACK/WELL/SAMADHI/11KV LINE
273 |  | 57/4 | DA+0 |  |  |  | 104181.627 | 462.423 | 72.5 | 828.884 | 414.442 | 173 | 178 | 351 | 182 | 188 | 370 | 76d5'18.577"E | 23d51'40.689"N | 610834.701 | 2639296.847 |  | Barda_Barkheda | Badod | MP
[5 empty] | 421.884 | [16 empty] | CART TRACK/LT LINE/LOW LAND
274 | AP58/0 | 58/0 | DC1+6 | 16° 14' 41"RT |  | 1652.88 | 104603.511 | 463.252 | 76.72 | 954.078 | 477.039 | 245 | 254 | 499 | 236 | 257 | 493 | 76d5'32.786"E | 23d51'36.522"N | 611237.62 | 2639171.78 | Benching Expected | Barda_Barkheda | Badod | MP
[5 empty] | 532.192 | [16 empty] | Lake
275 | AP59/0 | 59/0 | DD45+18 | 24° 14' 33"LT |  | 532.192 | 105135.703 | 455.45 | 88.72 | 947.192 | 473.596 | 284 | 314 | 598 | 282 | 280 | 562 | 76°5'48.395"E | 23°51'26.863"N | 611681.464 | 2638878.126 | Raised Chimney | Barda_Barkheda | Badod | MP | 0 | 1 | 1 | 2.5 | RC DWG NOT AVIALABLE
[5 empty] | 415 | [16 empty] | 33KkV line, Nala
276 |  | 59/1 | DA+9 |  |  |  | 105550.703 | 444.124 | 81.5 | 764.861 | 382.4305 | 102 | 221 | 323 | 137 | 207 | 344 | 76d6'2.856"E | 23d51'24.593"N | 612091.074 | 2638811.456 |  | Semalkhedi | Nalkheda | MP
[5 empty] | 350 | [16 empty] | 33kV lines, 11kV lines
277 | AP60/0 | 60/0 | DC2+6 | 26° 15' 27"RT |  | 765 | 105900.703 | 439.64 | 70.72 | 598.874 | 299.437 | 129 | 121 | 250 | 144 | 123 | 267 | 76d6'15.048"E | 23d51'22.678"N | 612436.39 | 2638755.25 |  | Semalkhedi | Nalkheda | MP
[5 empty] | 249.013 | [16 empty] | NH-552G, 33kV line, 11kV line, Nala
278 | AP61/0 | 61/0 | DB1+9 | 2° 56' 37"LT |  | 249.013 | 106149.716 | 436.98 | 70.72 | 600.013 | 300.0065 | 128 | 176 | 304 | 127 | 176 | 303 | 76d6'22.173"E | 23d51'17.925"N | 612639.11 | 2638610.64 |  | Semalkhedi | Nalkheda | MP
[5 empty] | 351 | [16 empty] | Nala, LT line, Well, Cart Track
279 |  | 61/1 | DA+6 |  |  |  | 106500.716 | 439.892 | 78.5 | 658.26 | 329.13 | 175 | 99 | 274 | 176 | 121 | 297 | 76d6'32.579"E | 23d51'11.709"N | 612934.948 | 2638421.745 |  | Semalkhedi | Nalkheda | MP
[5 empty] | 307.261 | [16 empty] | Metal road, 11kV line
280 | AP62/0 | 62/0 | DB1+12 | 2° 14' 43"LT |  | 658.261 | 106807.977 | 441.3 | 82.72 | 557.818 | 278.909 | 209 | 182 | 391 | 187 | 152 | 339 | 76°6'41.687"E | 23°51'6.267"N | 613193.92 | 2638256.39 |  | Semalkhedi | Nalkheda | MP
[5 empty] | 250.557 | [16 empty] | 132 KV DC CKT-1 AGAR -SUSNER , CKT-2 AGAR - NALKHEDA OHTL OHTL, 33kV lines, 11kV line, Cart track
281 | AP63/0 | 63/0 | DC2+12 | 24° 32' 28"LT |  | 250.557 | 107058.534 | 436.106 | 82.72 | 673.557 | 336.7785 | 69 | 324 | 393 | 99 | 286 | 385 | 76°6'49.297"E | 23°51'2.1"N | 613410.22 | 2638129.927 |  | Semalkhedi | Nalkheda | MP
[5 empty] | 423 | [16 empty] | Nala
282 |  | 63/1 | DA(-)3 |  |  |  | 107481.534 | 429.568 | 69.5 | 762 | 381 | 100 | 163 | 263 | 139 | 166 | 305 | 76°7'4.161"E | 23°51'0.609"N | 613831.075 | 2638087.383 |  | Semalkhedi | Nalkheda | MP
[5 empty] | 339 | [16 empty] | Cart Track
283 |  | 63/2 | DA(-)3 |  |  |  | 107820.534 | 430.538 | 69.5 | 679 | 339.5 | 176 | 194 | 370 | 174 | 186 | 360 | 76°7'16.074"E | 23°50'59.414"N | 614168.356 | 2638053.288 |  | Semalkhedi | Nalkheda | MP
[5 empty] | 340 | [16 empty] | Abandoned 11kV line, Cart track
284 |  | 63/3 | DA(-)3 |  |  |  | 108160.534 | 426.827 | 69.5 | 679.061 | 339.5305 | 146 | 159 | 305 | 155 | 163 | 318 | 76°7'28.021"E | 23°50'58.216"N | 614506.632 | 2638019.092 |  | Borkhedi_Saloki | Nalkheda | MP
339.061
285 | AP64/0 | 64/0 | DD45+0 | 41° 42' 42"RT |  | 1441.061 | 108499.595 | 425.402 | 70.72 | 722.061 | 361.0305 | 180 | 202 | 382 | 177 | 199 | 376 | 76°7'39.935"E | 23°50'57.02"N | 614843.974 | 2637984.991 |  | Borkhedi_Saloki | Nalkheda | MP
[5 empty] | 383 | [16 empty] | Nala
286 |  | 64/1 | DA+6 |  |  |  | 108882.595 | 417.627 | 78.5 | 783 | 391.5 | 182 | 263 | 445 | 185 | 243 | 428 | 76°7'49.004"E | 23°50'47.775"N | 615102.804 | 2637702.686 |  | Borkhedi_Saloki | Nalkheda | MP
[5 empty] | 400 | [16 empty] | Orange garden, Well, Cart track
287 | AP65/0 | 65/0 | DC2+0 | 22° 30' 31"LT |  | 783 | 109282.595 | 411.959 | 70.72 | 786 | 393 | 137 | 197 | 334 | 158 | 196 | 354 | 76°7'58.47"E | 23°50'38.125"N | 615372.954 | 2637408.036 |  | Borkhedi_Saloki | Nalkheda | MP
[5 empty] | 386 | [16 empty] | 11kV line, Nala, Well
288 |  | 65/1 | DA(-)1.5 |  |  |  | 109668.595 | 412.71 | 71 | 779 | 389.5 | 189 | 169 | 358 | 191 | 178 | 369 | 76°8'10.791"E | 23°50'32.736"N | 615722.859 | 2637245.056 |  | Borkhedi_Saloki | Nalkheda | MP
[5 empty] | 393 | [16 empty] | Nala
289 |  | 65/2 | DA+0 |  |  |  | 110061.595 | 416.226 | 72.5 | 815 | 407.5 | 224 | 174 | 398 | 216 | 186 | 402 | 76°8'23.335"E | 23°50'27.248"N | 616079.11 | 2637079.121 |  | Borkhedi_Saloki | Nalkheda | MP
[5 empty] | 422 | [16 empty] | Nala, Cart track, Well
290 |  | 65/3 | DA+6 |  |  |  | 110483.595 | 417.548 | 78.5 | 830 | 415 | 249 | 242 | 491 | 237 | 230 | 467 | 76°8'36.805"E | 23°50'21.355"N | 616461.649 | 2636900.941 |  | Suigaon | Nalkheda | MP
408
291 |  | 65/4 | DA(-)1.5 |  |  |  | 110891.595 | 417.939 | 71 | 778 | 389 | 167 | 195 | 362 | 179 | 193 | 372 | 76°8'49.827"E | 23°50'15.658"N | 616831.497 | 2636728.673 |  | Suigaon | Nalkheda | MP
[5 empty] | 370 | [16 empty] | 11kV line, LT line, Metal road, Well, Nala
292 |  | 65/5 | DA(-)3 |  |  |  | 111261.595 | 417.676 | 69.5 | 715 | 357.5 | 175 | 144 | 319 | 178 | 153 | 331 | 76°9'1.637"E | 23°50'10.49"N | 617166.898 | 2636572.449 |  | Suigaon | Nalkheda | MP
[5 empty] | 345 | [16 empty] | Nala
293 |  | 65/6 | DA+0 |  |  |  | 111606.595 | 419.33 | 72.5 | 697 | 348.5 | 202 | 100 | 302 | 193 | 124 | 317 | 76°9'12.648"E | 23°50'5.672"N | 617479.637 | 2636426.78 |  | Suigaon | Nalkheda | MP
352
294 |  | 65/7 | DA(-)3 |  |  |  | 111958.595 | 434.784 | 69.5 | 792 | 396 | 252 | 273 | 525 | 229 | 257 | 486 | 76°9'23.882"E | 23°50'0.756"N | 617798.722 | 2636278.156 |  | Suigaon | Nalkheda | MP
440
295 |  | 65/8 | DA+1.5 |  |  |  | 112398.595 | 419.428 | 74 | 820 | 410 | 167 | 199 | 366 | 184 | 196 | 380 | 76°9'37.924"E | 23°49'54.61"N | 618197.577 | 2636092.376 |  | Suigaon | Nalkheda | MP
[5 empty] | 380 | [16 empty] | Cart Track
296 |  | 65/9 | DA(-)3 |  |  |  | 112778.595 | 422.442 | 69.5 | 796 | 398 | 182 | 127 | 309 | 185 | 153 | 338 | 76°9'50.052"E | 23°49'49.302"N | 618542.043 | 2635931.93 |  | Suigaon | Nalkheda | MP
[5 empty] | 416 | [16 empty] | 11kV line, LT line, Cart track
297 |  | 65/10 | DA+9 |  |  |  | 113194.595 | 426.214 | 81.5 | 822 | 411 | 290 | 284 | 574 | 265 | 259 | 524 | 76°10'3.328"E | 23°49'43.491"N | 618919.143 | 2635756.284 | Raised Chimney | Kilona | Nalkheda | MP | 1 | 0 | 0 | 0 | RC DWG AVIABLE
[5 empty] | 406 | [16 empty] | Metal road
298 |  | 65/11 | DA+6 |  |  |  | 113600.595 | 414.059 | 78.5 | 839.178 | 419.589 | 123 | 249 | 372 | 149 | 239 | 388 | 76°10'16.284"E | 23°49'37.819"N | 619287.178 | 2635584.86 |  | Kilona | Nalkheda | MP
[5 empty] | 433.178 | [16 empty] | 11kv line, Nala, Well
299 | AP66/0 | 66/0 | DB1+0 | 1° 44' 24"RT |  | 4751.178 | 114033.773 | 413.6 | 70.72 | 786.426 | 393.213 | 185 | 116 | 301 | 195 | 135 | 330 | 76°10'30.108"E | 23°49'31.768"N | 619679.85 | 2635401.96 |  | Kilona | Nalkheda | MP
[5 empty] | 353.248 | [16 empty] | Nala, Well, Cart track
300 |  | 66/1 | DA+6 | 0° 44' 14"RT |  |  | 114387.021 | 417.697 | 78.5 | 760.248 | 380.124 | 238 | 301 | 539 | 219 | 271 | 490 | 76°10'41.212"E | 23°49'26.52"N | 619995.389 | 2635243.154 | Raised Chimney | Pilwas | Nalkheda | MP | 2.5 | 2.5 | 0 | 0 | RC DWG NOT AVIALABLE
[5 empty] | 407 | [16 empty] | Orange garden, Cart track
301 |  | 66/2 | DA(-)1.5 | 0° 50' 41"LT |  |  | 114794.021 | 406.747 | 71 | 823 | 411.5 | 107 | 187 | 294 | 137 | 194 | 331 | 76°10'53.918"E | 23°49'20.323"N | 620356.505 | 2635055.549 |  | Pilwas | Nalkheda | MP
[5 empty] | 416 | [16 empty] | Orange garden, Nala
302 |  | 66/3 | DA+6 |  |  |  | 115210.021 | 403.349 | 78.5 | 789 | 394.5 | 230 | 245 | 475 | 223 | 227 | 450 | 76°11'7.007"E | 23°49'14.165"N | 620728.447 | 2634869.23 |  | Pilwas | Nalkheda | MP
[5 empty] | 373 | [16 empty] | 11kV line, LT line, Cart track, Orange garden
303 |  | 66/4 | DA(-)3 |  |  |  | 115583.021 | 402.196 | 69.5 | 762 | 381 | 128 | 165 | 293 | 147 | 175 | 322 | 76°11'18.743"E | 23°49'8.643"N | 621061.944 | 2634702.169 |  | Pilwas | Nalkheda | MP
[5 empty] | 389 | [16 empty] | Orange garden, Cart track
304 |  | 66/5 | DA+3 |  |  |  | 115972.021 | 401.524 | 75.5 | 788 | 394 | 224 | 232 | 456 | 215 | 222 | 437 | 76°11'30.981"E | 23°49'2.884"N | 621409.746 | 2634527.943 |  | Pilwas | Nalkheda | MP
[5 empty] | 399 | [16 empty] | 11kV line
305 |  | 66/6 | DA(-)1.5 |  |  |  | 116371.021 | 400.071 | 71 | 811 | 405.5 | 168 | 172 | 340 | 178 | 183 | 361 | 76°11'43.534"E | 23°48'56.977"N | 621766.488 | 2634349.238 |  | Pilwas | Nalkheda | MP
[5 empty] | 412 | [16 empty] | Cart track, 11kV line, Well, Hut
306 |  | 66/7 | DA+6 |  |  |  | 116783.021 | 399.199 | 78.5 | 830 | 415 | 241 | 262 | 503 | 230 | 246 | 476 | 76°11'56.496"E | 23°48'50.877"N | 622134.854 | 2634164.71 |  | Pilwas | Nalkheda | MP
[5 empty] | 418 | [16 empty] | 11kv line, Cart track, Orange garden, Well
307 |  | 66/8 | DA(-)3 |  |  |  | 117201.021 | 397.889 | 69.5 | 812.107 | 406.0535 | 156 | 155 | 311 | 173 | 169 | 342 | 76°12'9.646"E | 23°48'44.687"N | 622508.585 | 2633977.495 |  | Pilwas | Nalkheda | MP
[5 empty] | 394.107 | [16 empty] | Metal road, 11kV line, Well, Hut
308 | AP67/0 | 67/0 | DB2+6 | 9° 0' 29"RT |  | 3561.355 | 117595.128 | 396.634 | 76.72 | 793.107 | 396.5535 | 240 | 245 | 485 | 227 | 231 | 458 | 76°12'22.044"E | 23°48'38.852"N | 622860.953 | 2633800.981 |  | Pilwas | Nalkheda | MP
[5 empty] | 399 | [16 empty] | 11kv line, Cart track, Orange garden, Well
309 |  | 67/1 | DA(-)3 |  |  |  | 117994.128 | 397.221 | 69.5 | 747 | 373.5 | 155 | 214 | 369 | 169 | 202 | 371 | 76°12'33.435"E | 23°48'31.208"N | 623185.315 | 2633568.623 |  | Pilwas | Nalkheda | MP
[5 empty] | 348 | [16 empty] | 11kv line, Cart track, Well
310 |  | 67/2 | DA(-)3 |  |  |  | 118342.128 | 390.617 | 69.5 | 706 | 353 | 134 | 120 | 254 | 146 | 138 | 284 | 76°12'43.37"E | 23°48'24.541"N | 623468.217 | 2633365.965 |  | Bhilkhedi | Nalkheda | MP
[5 empty] | 358 | [16 empty] | 11kv line, Cart track, Well, Metal road, Nala
311 |  | 67/3 | DA+9 |  |  |  | 118700.128 | 388.639 | 81.5 | 836.205 | 418.1025 | 239 | 264 | 503 | 221 | 257 | 478 | 76°12'53.591"E | 23°48'17.683"N | 623759.249 | 2633157.483 | Raised Chimney | Bhilkhedi | Nalkheda | MP | 0 | 0 | 2 | 0 | RC DWG AVIABLE
[5 empty] | 478.205 | [16 empty] | Nala, LT line, orange garden, Well
312 | AP68/0 | 68/0 | DB2+6 | 13° 2' 58"LT |  | 1583.205 | 119178.333 | 386.186 | 76.72 | 478.205 | 239.1025 | 215 | 0 | 215 | 223 | 0 | 223 | 76°13'7.242"E | 23°48'8.521"N | 624148 | 2632879 |  | Bhilkhedi | Nalkheda | MP
[5 empty] | 119178.333 | 119178.329
SUMMARY OF TENTITIVE TOWERS QUANTITIES GANTRY TO AP 68 COMMON POINT
[7 empty] | TYPE OF TOWER | EXTENSION | [9 empty] | TOTAL TOWER
[8 empty] | -3 | -1.5 | +0 | +1.5 | +3 | +6 | +9 | +12 | +18 | +25
[7 empty] | DA | 40 | 15 | 77 | 20 | 38 | 33 | 6 | 0 | 0 | 0 | 229
[7 empty] | DB1 | 0 | 1 | 7 | 0 | 2 | 1 | 3 | 1 | 1 | 0 | 16
[7 empty] | DB2 | 0 | 1 | 4 | 0 | 3 | 3 | 2 | 0 | 0 | 0 | 13
[7 empty] | DC1 | 0 | 0 | 8 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 11
[7 empty] | DC2 | 0 | 0 | 8 | 0 | 2 | 1 | 0 | 2 | 3 | 0 | 16
[7 empty] | DD45 | 0 | 0 | 5 | 0 | 1 | 1 | 5 | 1 | 2 | 0 | 15
[7 empty] | DD60 | 0 | 0 | 6 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 12
[7 empty] | Total | 40 | 17 | 115 | 20 | 48 | 42 | 18 | 4 | 6 | 2 | 312
Note on AA200: Author: NOT AVAILABLE
Note on AA434: unicom: NOT AVIALABLE

## Sheet1 (hidden)
VC-765kV MKTL'!A1
FOUNDATION!A1
EARTHING!A1
ERECTION!A1
TS!A1

## SURVEY SUMMARY (hidden)
Original Route alignment | KM | 118.288 | 106.341 | 106.341
Detailed Survey | KM | 118.288 | 106.341 | 106.341
Diverted Route Alignment | KM | 0 | 1.558 | Pending |  | TRUE
Check Survey | KM | 118.288 | 106.341 | 106.341
Crossing Proposals
Power line Crossings | Nos | 9 | 8 | 8
NH Crossing | Nos | 3 | 1 | 1
Railway crossing | Nos | 1 | 1 | NOC Received
Aviation/Defence proposal | Nos | 1 | 1 | NOC Received
Major river crossing | Nos | 1 | 0 | 0
Forest | Nos | 0 | 1 |  |  |  | TRUE
Other Crossings (Specify) | Nos
Original Route alignment | KM | 117.8509 | 117.8509 | 117.8509
Detailed Survey | KM | 117.8509 | 117.8509 | 117.8509
Diverted Route Alignment | KM | 0 | 0 | 0
Check Survey | KM | 117.8509 | 117.8509 | 117.8509
Crossing Proposals
Power line Crossings | Nos | 6 | 6 | 6
NH Crossing | Nos | 2 | 2 | 1 |  | TRUE
Railway crossing | Nos | 1 | 1 | 0 |  | TRUE
Aviation/Defence proposal | Nos | 1 | 1 | 1
Major river crossing | Nos | 0 | 0 | 0
Forest | Nos | 2 | 2 | 0 |  | TRUE
Other Crossings (Specify) | Nos
Original Route alignment | KM | 78.579 | 78.579 | 78.579
Detailed Survey | KM | 78.579 | 78.579 | 78.579 | TRUE
Diverted Route Alignment | KM | 0 | 0 | 0
Check Survey | KM | 66.683 | 53.932 | 53.932 | TRUE
Crossing Proposals
Power line Crossings | Nos | 2 | 1 | 1 | TRUE
NH Crossing | Nos | 0 | 0 | 0
Railway crossing | Nos | 0 | 0 | 0
Aviation/Defence proposal | Nos | 0 | 0 | 0 | TRUE
Major river crossing | Nos | 0 | 0 | 0
Forest | Nos | 1 | 1 | 0 | TRUE
Other Crossings (Specify) | Nos
Original Route alignment | KM | 136.706 | 136.706 | 136.706
Detailed Survey | KM | 136.706 | 136.706 | 133.729 | TRUE
Diverted Route Alignment | KM | 0 | 0 | 0
Check Survey | KM | 136.706 | 133.729 | 133.083 | TRUE
Crossing Proposals
Power line Crossings | Nos | 12 | 12 | 0
NH Crossing | Nos | 2 | 2 | 0
Railway crossing | Nos | 1 | 1 | 0 |  | TRUE
Aviation/Defence proposal | Nos | 1 | 1 | 0
Major river crossing | Nos | 0 | 0 | 0
Forest | Nos | 25 | 25 | 0
Other Crossings (Specify) | Nos | 1 | 1 | 0
Original Route alignment | KM | 222.811 | 222.811 | 222.811
Detailed Survey | KM | 222.811 | 205.936 | 199.134 | TRUE
Diverted Route Alignment | KM | 0 | 0 | 0
Check Survey | KM | 222.811 | 199.134 | 199.134 | TRUE
Crossing Proposals
Power line Crossings | Nos | 19 | 17 | 8 | TRUE
NH Crossing | Nos | 8 | 8 | 0 | TRUE
Railway crossing | Nos | 3 | 3 | 0
Aviation/Defence proposal | Nos | 2 | 0 | 0
Major river crossing | Nos | 0 | 0 | 0
Forest | Nos | 1 | 1 | 0
Other Crossings (Gas/oil pipe line) | Nos | 7 | 7 | 0 | TRUE
Original Route alignment | KM | 123.182 | 123.182 | 110.754 | TRUE
Detailed Survey | KM | 123.182 | 105.651 | 105.651 | TRUE
Diverted Route Alignment | KM | 0 | 0 | 0
Check Survey | KM | 123.182 | 60.862 | 60.862 | TRUE
Crossing Proposals
Power line Crossings | Nos | 6 | 6 | 6
NH Crossing | Nos | 2 | 1 | 0 | TRUE
Railway crossing | Nos | 1 | 1 | 0 | TRUE
Aviation/Defence proposal | Nos | 0 | 0 | 0
Major river crossing | Nos | 0 | 0 | 0
Forest | Nos | 1 | 0 | 0
Gas/Oil Pipe line | Nos | 1 | 0 | 0
Canal | Nos | 1 | 0 | 0
Other Crossings (State Highway) | Nos | 0 | 0 | 0
Original Route alignment | KM | 122.071 | 122.071 | 122.071
Detailed Survey | KM | 122.071 | 122.071 | 122
Diverted Route Alignment | KM |  | 0 | 0
Check Survey | KM | 122.071 | 122.071 | 122
Crossing Proposals
Power line Crossings | Nos | 27 | 27 | 17 |  | TRUE
NH Crossing | Nos | 7 | 7 | 0 |  | TRUE
Railway crossing | Nos | 5 | 5 | 0 |  | TRUE
Aviation/Defence proposal | Nos | 1 | 1 | 0
Major river crossing | Nos | 0 | 0 | 0
Forest | Nos | 0 | 0 | 0
Other Crossings (State Highway) | Nos | 10 | 10 | 0
Original Route alignment | KM | 115.134 | 115.134 | 115.134
Detailed Survey | KM | 115.134 | 115.134 | 115.134
Diverted Route Alignment | KM | 0 | 0 | 0
Check Survey | KM | 115.134 | 115.134 | 115.134
Crossing Proposals
Power line Crossings | Nos | 21 | 21 | 21
NH Crossing | Nos | 3 | 3 | 3
Railway crossing | Nos | 3 | 3 | 3
Aviation/Defence proposal | Nos | 1 | 1 | 0 | TRUE
Major river crossing | Nos | 1 | 1 | 1
Forest | Nos | 1 | 1 | 0 | TRUE
Other Crossings (State Highway) | Nos | 4 | 4 | 4
Original Route alignment | KM | 127.83 | 127.83 | 127.83
Detailed Survey | KM | 127.83 | 123.958 | 123.958 | TRUE
Diverted Route Alignment | KM | 3.896 | 3.896 | 0 | TRUE
Check Survey | KM | 127.83 | 123.958 | 123.958
Crossing Proposals
Power line Crossings | Nos | 48 | 48 | 19 | TRUE
NH Crossing | Nos | 8 | 8 | 0 | TRUE
Railway crossing | Nos | 6 | 6 | 1 | TRUE
Aviation/Defence proposal | Nos | 1 | 0 | 0 | TRUE
Major river crossing | Nos | 2 | 2 | 1 | TRUE
Forest | Nos | 3 | 3 | 0 | TRUE
Other Crossings (Civil Aviation) | Nos | 18 | 15 | 0 | TRUE
Original Route alignment | KM | 177.044 | 177.044 | 177.044
Detailed Survey | KM | 177.044 | 177.044 | 177.044
Diverted Route Alignment | KM | 0 | 0 | 0
Check Survey | KM | 177.044 | 177.044 | 177.044
Crossing Proposals
Power line Crossings | Nos | 68 | 68 | 65 | TRUE
NH Crossing | Nos | 9 | 9 | 6 | TRUE
Railway crossing | Nos | 9 | 9 | 9
Aviation/Defence proposal | Nos | 1 | 1 | 1
Major river crossing | Nos | 3 | 3 | 3
Forest | Nos | 1 | 1 | 1
Other Crossings (Specify) | Nos
TA-509 - 765 kV D/C Mandsaur - Kurawar |  |  | KEC International Ltd.
Description | Unit | Total Qty | Submitted | Approved |  |  |  | Remarks
Original Route alignment | KM | 118.288 | 118.406 | 113.533
Detailed Survey | KM | 118.288 | 118.406 | 108.989
Diverted Route Alignment | KM | 0 | 0 | 0
Check Survey | KM | 118.288 | 108.171 | 108.171 |  |  |  | 55/0-58/0-ROUTE DIVERSION
Crossing Proposals
Power line Crossings | Nos | 9 | 8 | 6
NH Crossing | Nos | 3 | 3 | 0 |  |  |  | APPROVAL AWAITED
Railway crossing | Nos | 1 | 1 | 0 |  |  |  | APPROVAL AWAITED
Aviation/Defence proposal | Nos | 1 | 1 | 0 |  |  |  | APPROVAL AWAITED
Major river crossing | Nos | 1 | NA | NA (Non navigable)
Forest | Nos | 0 | 0 | 0
42/0-43/0-POWERLINE-XING JOINT VERFICATION DONE BY (26/06/2025)
31/0-32/0-RAILWAY-XING JOINT VERFICATION DONE BY (27/06/2025)
28/0-29/0-POWERLINE-XING JOINT VERFICATION DONE BY (04/07/2025)

## SURVEY STATUS (hidden)
TA-509 765 KV D/C Mandsaur - Kurawar (Part-1)Transmission Line(WZ-4)
Sl No | SL NO. | AP NO | Towe Type | AP No | Tower Type | Type of Crossings | Line Name | LINE OWNER | Status | Proposal Submitted (Y/N) | Inspection Status (Y/N) | Remarks
1 | 1 | 11/0 | DD60+25 | 12/0 | DD60+25 (1 MRC) | POWERLINE-XING | EXISTING 400 KV DC NEEMUCH-MANDSAUR TRANSMISSION LINE | Power Grid | APPROVAL-AWAITED | SUBMITTED | JOINT INSPECTION DONE BY 04.06.2025
2 | 2 | 25/0 | DC2+1 | 26/0 | DC2+12 | POWERLINE-XING | 220 KV DC MANDSAUR - NIPANIA TL | MPPTCL | APPROVAL-AWAITED | SUBMITTED | JOINT INSPECTION DONE BY 04.06.2025
3 | 3 | 28/0 | DD45+6 | 29/0 | DD45+18 | POWERLINE-XING | 220 KV DC SITAMAU-SUWASRA OHTL MPPTCL | MPPTCL | APPROVAL-AWAITED | SUBMITTED | JOINT INSPECTION DONE BY 04.06.2025
4 | 4 | 33/0 | DD45+9 | 34/0 | DC1+3 | POWERLINE-XING | 132KV D/C SUWASARA - BADOD TL (Joint joint inspection Done) | MPPTCL | APPROVAL-AWAITED | SUBMITTED | JOINT INSPECTION DONE BY 04.06.2025
5 | 5 | 37/0 | DD45+12 | 38/0 | DD45+9 | POWERLINE-XING | 220 KV OHTL DC BHANPUR-BAROD MPPTCL | MPPTCL | APPROVAL-AWAITED | SUBMITTED | JOINT INSPECTION DONE BY 04.06.2025
8 | 6 | 42/0 | DC1+3 | 43/0 | DC1+6 | POWERLINE-XING | 132 KV SC BHAWANI MANDI - DAG T/L (RRVPNL) | RVPNL | APPROVAL-AWAITED | SUBMITTED | JOINT INSPECTION DONE BY 26.06.2025
| 7 | 50/0 | DC2+18 | 51/0 | DD60+9 | POWERLINE-XING | 220 KV S/C SUSNER - PACHORA T/L | RTL | APPROVAL-AWAITED | SUBMITTED | JOINT INSPECTION PENDING
6 | 8 | 54/0 | DD45+9 | 55/0 | DC2+2 | POWERLINE-XING | 220kV D/C Badod-Nalkheda T/Line | MPPTCL | - | NOT SUBMITTED YET | PENDING DUE TO FINALIZATION OF SURVEY FOR AVOIDING FOREST IN B/T 52/0-58/0
7 | 9 | 62/0 | DB1+12 | 63/0 | DC2+2 | POWERLINE-XING | 132 KV DC CKT-1 AGAR -SUSNER , CKT-2 AGAR - NALKHEDA OHTL | MPPTCL | APPROVAL-AWAITED | SUBMITTED | JOINT INSPECTION PENDING
9 | 10 | 17/0 | DB2+3 | 18/0 | DD45+0 | NH-XING | NE-4 DELHI MUMBAI EXPRESSWAY | NHAI | APPROVAL-AWAITED | SUBMITTED | JOINT INSPECTION PENDING
10 | 11 | 35/0 | DB2+3 | 36/0 | DC2+0 | NH-XING | NATIONAL HIGHWAY-752D | NHAI | APPROVAL-AWAITED | SUBMITTED | JOINT INSPECTION PENDING
11 | 12 | 60/0 | DC2+0 | 61/0 | DB1+0 | NH-XING | NATIONAL HIGHWAY-552G | NHAI | APPROVAL-AWAITED | SUBMITTED | JOINT INSPECTION PENDING
12 | 13 | 31/0 | DD60+0 | 32/0 | DD60+9 | RAILWAY-XING | Between Suwasra & Nathukheri Railway station BG | INDIAN-RAILWAY KOTA DIVISION | APPROVAL-AWAITED | SUBMITTED | JOINT INSPECTION DONE BY 27.06.2025 & REVISE INSPECTION PENDING

## Erection productivity (hidden)
KEC International Limited - Gurgaon.
Erection Productivity Gang wise - Nov'25
Sr. No. | Sub-Contractor Name | Loc. No. | Type of Tower | Tower Weight (MT) | Previous Month | 01.11.25 (MT) | 02.11.25 (MT) | 03.11.25 (MT) | 04.11.25 (MT) | 05.11.25 (MT) | 06.11.25 (MT) | 07.11.25 (MT) | 08.11.25 (MT) | 09.11.25 (MT) | 10.11.25 (MT) | 11.11.25 (MT) | 12.11.25 (MT) | 13.11.25 (MT) | 14.11.25 (MT) | 15.11.25 (MT) | 16.11.25 (MT) | 17.11.25 (MT) | 18.11.25 (MT) | 19.11.25 (MT) | 20.11.25 (MT) | 21.11.25 (MT) | 22.11.25 (MT) | 23.11.25 (MT) | 24.11.25 (MT) | 25.11.25 (MT) | 26.11.25 (MT) | 27.11.25 (MT) | 28.11.25 (MT) | 29.11.25 (MT) | 30.11.25 (MT) | Cumulative Till dated | Status | Manpower/Gang
[38 empty] | Plan | Actual | Shotfall
1 | Devi Construction | 9/2 | DA+0 | 36.1598 | 27.12 | 4.519 | 4.519 | [28 empty] | 9.038 | Completed | 10 | 5 | 6
2 | Devi Construction | 8/4 | DA+3 | 37.9311 |  |  |  | 7 | 8 | 7 | 7.5 | 7.7 | [23 empty] | 37.2 | Completed
3 | Devi Construction | 10/2 | DA(-)3 | 34.7898 | [8 empty] | 6.78 | 11 | 9 | 8 | [19 empty] | 34.78 | Completed
4 | Devi Construction | 12/3 | DA(-)3 | 34.7898 | [12 empty] | 5.78 | 7 | 8 | 7 | 7 | [14 empty] | 34.78 | Completed
5 | Devi Construction | 13/0 | DB2+0 | 59.5006 | [17 empty] | 8 | 3 | 3 | 4 | 1.5 | 3 | 4 | 8 | 8 | 8 | 9 |  |  |  | 59.5 | Completed
6 | Aravali Infra-1 | 15/4 | DA+6 | 43.8044 | [16 empty] | 6 | 8 | 4 | 4 | 4 | 2 | 2 | 4 | 4 | 5.8 | [5 empty] | 43.8 | Completed
7 | Aravali Infra-2 | 16/2 | DA+0 | 36.1598 | [16 empty] | 2 | 5 | 3.8 | 5 | 3 | 5 | 3 | 4 | 5.359 | [6 empty] | 36.159 | Completed
8 | Aravali Infra-3 | 24/1 | DA+0 | 36.1598 | [27 empty] | 3 | 5 | 3 | 1 | 12
9 | Jawala singh | 5/1 | DA(-)3 | 34.7898 | [20 empty] | 8 | 8 | 5 | 6 | 3 | 4.78 | [5 empty] | 34.78 | Completed
10 | Arawali infra-2 | 15/9 | DA+3 | 37.9311 | [26 empty] | 3 | 5 | 5 | 3 | 5 | 21
11 | Arawali infra-1 | 15/3 | DA+0 | 36.1598 | [27 empty] | 3 | 6 | 5 | 4 | 18
12 | DEVI CONST. | 8/1 | DA+0 | 36.1598 | [28 empty] | 4 | 3 | 3 | 10
13 | Jawala singh | 5/5 | DA+0 | 36.1598 | [31 empty] | 0
14 | [35 empty] | 0
0
Total | [35 empty] | 0