## TB401 DPR..... (hidden)
| Project Code |  | TB-401 |  | Date |  | 2026-02-17 | LOA Start Date |  |  | 2023-04-25 | Business Head (T&D)- India & Sri Lanka |  |  | Rajinder Gupta
| Project Name |  | 765KV D/C Fategarh-III Beawar Transmission Line |  |  |  |  | LOA End Date |  |  | 2024-07-25 | PCH |  |  | Sivaraman Nataraajan
| Client Name |  | Strelite Power |  |  |  |  | Time Extn |  |  | 2024-07-25 | Regional Manager |  |  | Sandeep Singh Kumar
| LE Value |  | Rs 312 Cr -Supply -Rs 227.5 Cr.; Service.-Rs 84.4 Cr |  |  |  |  | Planning |  |  | Shah Ali Khan | Project Manager |  |  | Virender Gupta
Activity | Unit | LOA Qty. | LE Qty | Progress till Last Month | Balance | L2 for Dec'23 | Plan for Dec.'23 | Today's Progress | Month Progress | WIP | Gangs at Present | L2 Till Month-Dec.23 | Progress Till Date | Balance Work | Remarks
Route Alignment | km | 215 | 202 | 167 | 35 | 0 | 35 |  |  |  |  | 215 | 167 | 35 | 35 Km is hold due to ROW issues
Detailed Survey | km | 215 | 202 | 202 | 0 | 0 | [5 empty] | 215 | 202 | 0 | SPTL Approved -202/202-Kms
Check Survey | km | 215 | 202 | 92.704 | 109.296 | 20 | 50 |  | 17.852 |  |  | 160 | 110.556 | 91.444 | 1. Total 7.854 Km is under review of SPTL. 2. Total check survey completed (Field work) 167 Km. 3. Total 60 Km check survey is hold due to row issues & Other issues.
Foundation | Nos | 534 | 521 | 109 | 412 | 75 | 30 |  | 1 | 4 | 3 | 399 | 110 | 411 |  | 12.48% | -2.434% | -13 | 48 | 306
Earthing | Nos | 534 | 521 | 106 | 415 | 75 | 30 |  | 2 |  |  | 399 | 108 | 413 |  | 12.48%
Tower Erection | Nos | 534 | 521 | 45 | 476 | 75 | 40 | 2 | 6 | 5 | 5 | 260 | 51 | 470 | 56/2 58/15 Complete | 12.48%
Tack welding | Nos | 534 | 521 | 15 | 506 | 75 | 40 | 1 | 3 | 1 | 1 | 260 | 18 | 503 | 56/7 complete | 12.48%
Stringing | Km | 215 | 202 | 0 | 202 | 20 | [5 empty] | 25 | 0 | 202 |  | 10.22% |  | 68.21%
#DIV/0!

## Eng. (hidden)
Tower | Tower Design |  | Test Tower |  | Balance Structural Drawing. |  | Tower | Stub & Template Drawings | Foundation
Types |  |  | Structural Drawing(BTB+0) |  | (3M/6M/9M) |  | Testing |  | Design/Drg
| Target | Status | Target | Status | Target | Status |  |  | Target | Status
DA Tower | 2023-05-12 | Approved | 2023-06-04 | Approved | 2023-06-24 | Approved for proto | Completed | Approved | 15-July | Approved
DB Tower | 2023-05-30 | Approved | 2023-07-30 | Approved | 2023-07-19 | Approvedin Cat-B | Completed | Approved for Proto | DB all Fdn. By 25 -July | Approved
DD Tower | 2023-06-21 | Approved | 30-Sept. | Approved in Cat -B | 2023-08-20 | Approved in Cat -B | Completed | Approved in Cat -B | 2023-07-31 | Approved
DC Tower | 2023-07-16 | Approved | 2023-10-08 | Approved in Cat -B | 2023-09-19 | Approved in Cat -B | Completed | Approved in Cat -B | 2023-08-25 | Approved

## Fdn (Pkg -G Section -I) (hidden)
KEC INTERNATIONAL LIMITED | [10 empty] | Date: | 2026-02-17
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
FOUNDATION
Sl. No. | Month Sl. No. | JMC No. | Location No. | Tower Type | Classification | Excavation Start | Dt. of Start | Dt. of Concrete | Name of Sub-Contractor | KEC representative | KEC Section In-Charge | Remarks
1 | 1 |  | 32/7 | DA+0 | SANDY | 23.10.23 | 25.10.23 | 28.10.23 | Shakti Construction | Kumar Nayak | Jish C Verghese | Complete
2 | 2 |  | 32/5 | DA+6 | SANDY | 29.10.23 | 31.10.23 | 04.11.2023 | Shakti Construction | Kumar Nayak | Jish C Verghese | Complete
3 | 3 |  | 32/1 | DA+9 | SANDY | 03.11.23 | 06.11.23 | 10.11.23 | Shakti Construction | Kumar Nayak | Jish C Verghese | Complete
4 | 4 |  | 30/2 | DA+0 | SANDY | 13.11.23 | 15.11.23 | 16.11.23 | Shakti Construction | Kumar Nayak | Jish C Verghese | Complete
5 | 5 |  | 32/0 | DB2+6 | SANDY | 18.11.23 | 20.11.23 | 28.11.23 | Shakti Construction | Dipesh | Jish C Verghese | Complete
Dec-23
1 | 6 |  | 31/3 | DA+0 | SANDY | 28.11.23 | 30.11.23 | 04.12.23 | Shakti Construction | Dipesh | Jish C Verghese | Complete

## Sheet2 (hidden)
S.No | Line | Activity | UOM | LOA Qty | L2 till Sep'25 | Completed till Date | Balance | WIP | Gangs | Remarks
1 | Samba- Jalandhar | Survey | Km | 144 | 70 | 129.36 | 14.64 |  | 2
|  | Foundation | Nos | 434 | 17 | 2 | 432 | 4 | 3
2 | Kishepur- Samba | Survey | Km | 33.103 | 20 | 8.56 | 24.543 | 0.3 | 1
|  | Foundation | Nos | 129 |  |  | 129
3 | LILO-Kisthwar | Survey | Km | 2.18 | 2.18 | 2.18 | 0
|  | Foundation | Nos | 14 | 6 |  | 14
| Total | Survey | Km | 179.283 | 92.18 | 140.1 | 39.183 | 0.3 | 3
|  | Foundation | Nos | 577 | 23 | 2 | 575 | 4 | 3
[11 empty] | S.No | Loc | TOT | S.No | Loc | TOT
[11 empty] | 1 | AP156 | DC+0 | 11 | AP91 | DD+25
[11 empty] | 2 | 70/2 | DA+0 | 12 | 153/2 | DA+3
[11 empty] | 3 | 153/1 | DA+0
[11 empty] | 4 | AP111 | DC+0
[11 empty] | 5 | 136/3 | DA+0
[11 empty] | 6 | 157/1 | DA+0
[11 empty] | 7 | AP150 | DC+0
[11 empty] | 8 | AP70 | DC+3
[11 empty] | 9 | 136/4 | DA+3
[11 empty] | 10 | AP68 | DB+0

## Sheet3 (hidden)
Line | Activity | Section | L2 Oct'25 | Plan Oct'25 | L2 Nov'25 | Plan Nov'25 | L2 Dec'25 | Plan Dec'25 | L2 (Oct'25-Dec'25) | Plan (Oct'25-Dec'25)
Samba-Jalandhar | FDN | Jammu | 25 | 10 | 35 | 10 | 40 | 20 | 100 | 110
| Gangs |  |  | 3 |  | 3 |  | 6
| FDN | Punjab |  | 15 |  | 25 |  | 30
| Gangs |  |  | 5 |  | 6 |  | 6
Kishenpur-Samba | FDN | Jammu | 2 |  | 7 | 5 | 10 | 8 | 19 | 13
| Gangs |  |  |  |  | 3 |  | 4
LILO-Kishtwar | FDN | Kishtwar | 2 |  | 2 | 1 |  | 1 | 4 | 2
| Gangs |  |  |  |  | 1 |  | 1
Total | FDN |  | 29 | 25 | 44 | 41 | 50 | 59 | 123 | 125
| Gangs |  |  | 8 |  | 13 |  | 17

## Sheet4 (hidden)
Line | Portion | Section | Length | ROW Lead | ROW Team | Remarks
|  |  | Km |  | Currently Working
Samba-Jalandhar | Jammu | Gantry-AP52 | 47 | Karmanya Pathania | ROW Team-1 Akhil S ( Engineer) / Radhe Shyam (Supervisor) | At site since the works are in initial phase , hence we have engaged site engineer/supervisor for ROW document collection for time being , further we can engage separate ROW team as per requirement
| Punjab | AP52 - AP115 | 47 |  | ROW Team -2 K Govind ( Section In charge) / Kuldeep Singh ( DET)
|  | AP115 - AP187 | 48 |  | ROW Team -3 Manish Nirala (Section In charge) / Govardhan (DET)
Kishenpur-Samba |  | Gantry- AP109 | 33 |  | ROW Team -4 Mukesh ( Admin) /Yadhuveer (Supervisor) | Due to heavy rains/landslides local administration blocked the roads
LILO | Kishtewar | AP1-Tapping Point | 2.1 |  |  | Due to heavy rains/landslides local administration blocked the roads

## Sheet5 (hidden)
Line | Portion | Section | Loc as per Survey | ROW Detail Collected by M/s. KEC | ROW Detail Submitted to M/s. RKPTL | Balance to Submit
Samba-Jalandhar | Jammu | Gantry-AP52 | 133 | 41 | 40 | 1
| Punjab | AP52 - AP115 | 129 | 60 | 50 | 10
|  | AP115 - AP187 | 140 | 45 | 43 | 2
Kishenpur-Samba | Jammu | Gantry- AP109 | 124 | 7 | 7
LILO | Kishtwar | AP1-Tapping Point | 13
Total |  |  | 539 | 153 | 140 | 13

## TB-605
| Project Code | TB-605 | Date | 2026-02-16 |  |  | President-T & D | Ganesh Srinivasan
| Project Name | Transmission Line Portion for “Transmission scheme for evacuation of power from Ratle HEP (850 MW) & Kiru HEP (624 MW): Part-A” |  |  | LOA Start Date | 2025-05-16 | SBU Head- T&D | Rajinder Gupta
| Client Name | Ratle Kiru Power Transmission Ltd |  |  | LOA End Date | 2027-03-15 | PCH | Dhiraj Vashisth
| Revised End Date |  |  |  | Planning | Aditya. M | Project Manager | Mithu Dutta
400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5-Jammu Portion
Progress Status
Activity | Final Estimated Qty | Cumulative L2 till Last Month | Cumulative Progress till Last Month | L2 for present Month | Plan for the Month | Today's Progress | Progress till Date for the Month | L2 till Current Month | Completed till Date | Balance Work | Under Progress | Gangs at Present | Remarks
Check Survey | 46.92 | 49 | 46.44 |  |  |  |  | 49 | 46.44 | 0.48 |  |  | Submitted - 46 Km Approved - 46 Km
Foundation | 129 | 58 | 55 | 16 | 24 |  | 5 | 74 | 60 | 69 | 8 | 8
Earthing | 129 | 65 | 46 | 16 | 24 |  | 3 | 81 | 49 | 80
Tower Erection | 129 | 29 | 10 | 16 | 24 |  | 8 | 45 | 18 | 111 | 5 | 5
Tack welding | 129 | 29 | 0 | 16 | 24 |  |  | 45 | 0 | 129 | 0 | 0
Stringing | 46.92 | 0 | 0 |  |  |  |  | 0 | 0 | 46.92 | 0 | 0
400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5- Punjab Portion
Progress Status
Activity | Final Estimated Qty | Cumulative L2 till Last Month | Cumulative Progress till Last Month | L2 for present Month | Plan for the Month | Today's Progress | Progress till Date for the Month | L2 till Current Month | Completed till Date | Balance Work | Under Progress | Gangs at Present | Remarks
Check Survey | 90 | 95 | 90 |  |  |  |  | 95 | 85 | 5 |  | 2 | Submitted - 85 Km Approved - 85 Km
Foundation | 258 | 104 | 105 | 29 | 35 |  | 13 | 133 | 118 | 140 | 12 | 11
Earthing | 258 | 104 | 84 | 29 | 35 |  | 16 | 133 | 100 | 158 | 0
Tower Erection | 258 | 51 | 0 | 29 | 40 | 2 | 11 | 80 | 11 | 247 | 6 | 6
Tack welding | 258 | 51 | 0 | 29 | 40 |  |  | 80 | 0 | 258 | 0 | 0
Stringing | 90 | 0 | 0 |  |  |  |  | 0 | 0 | 90 | 0 | 0
400 kV Kishenpur-Samba D/C Line (Quad) - Wind Zone-5
Progress Status
Activity | Final Estimated Qty | Cumulative L2 till Last Month | Cumulative Progress till Last Month | L2 for present Month | Plan for the Month | Today's Progress | Progress till Date for the Month | L2 till Current Month | Completed till Date | Balance Work | Under Progress | Gangs at Present | Remarks
Check Survey | 33.103 | 33.103 | 33.103 |  |  |  |  | 33.103 | 33.103 | 0 |  | 1 | Submitted -30.26 Km Approved - 30.26 Km
Foundation | 129 | 31 | 27 | 8 | 13 |  | 1 | 39 | 28 | 101 | 6 | 6
Earthing | 129 | 31 | 23 | 8 | 13 |  | 1 | 39 | 24 | 105 | 0
Tower Erection | 129 | 0 | 0 |  | 4 |  |  | 0 | 0 | 129 | 0 | 0
Tack welding | 129 | 0 | 0 |  |  |  |  | 0 | 0 | 129 | 0 | 0
Stringing | 33.103 | 0 | 0 |  |  |  |  | 0 | 0 | 33.103 | 0 | 0
400kV DC LILO at Kistwar(Twin) Line - Wind Zone-2
Progress Status
Activity | Final Estimated Qty | Cumulative L2 till Last Month | Cumulative Progress till Last Month | L2 for present Month | Plan for the Month | Today's Progress | Progress till Date for the Month | L2 till Current Month | Completed till Date | Balance Work | Under Progress | Gangs at Present | Remarks
Check Survey | 2.571 | 2.1 | 2.571 |  |  |  |  | 2.1 | 2.571 | 0
Foundation | 16 | 14 | 0 |  | 1 |  |  | 14 | 0 | 16 |  |  | Revised route provided by RKPTL on 17th Jan'26. revised detail survey submitted to RKPTL & Check survey under progress as per revised route
Earthing | 16 | 14 | 0 |  | 1 |  |  | 14 | 0 | 16 | 0
Tower Erection | 16 | 0 | 0 |  |  |  |  | 0 | 0 | 16 | 0 | 0
Tack welding | 16 | 0 | 0 |  |  |  |  | 0 | 0 | 16 | 0 | 0
Stringing | 2.571 | 0 | 0 |  |  |  |  | 0 | 0 | 2.571 | 0 | 0
Supply Status
Line | Description | Final Estimated Qty | L2 till Feb'26 | Qty Supplied till Feb'26 | Remarks
Samba-Jalandhar | Stubs | 387 | 434 | 288
| Towers | 387 | 216 | 216
Samba-Kishenpur | Stubs | 129 | 129 | 48
| Towers | 129 | 100 | 26
LILO at Kishtwar | Stubs | 16 | 14 | 10
| Towers | 16 | 14

## TB401 DPR (hidden)
Project Progress for TB-401/408,Section-II
765KV D/C Fategarh-III Beawar Transmission Line |  |  | TB-401 |  |  | LOA Date |  | Pkg-G -26.04.23 |  |  | Completion Period |  | 2025-03-31 |  |  | Date: | 2026-02-17
|  |  | TB-408 |  |  |  |  | Pkg-F - 11.09.23 |  |  | Completion Period |  | 2025-03-31
.
Activity | Qty as per LOA | Qty Received | L2 |  | Overall Progress |  | Mar'25 |  | Balance | Apr'25 |  |  |  | Plan |  | Remarks
|  |  | 2024-12-30 | Till Mar-25 | As on date | Till Mar-25 | Plan | Actual | As on date | Plan | WIP | Today comp | Actual | 2024-09-01 | 2024-07-01
Details Survey | 215 | 189.53 |  | 203 | 199.841 | 199.841
Pkg-G (Section-II) |  | 101.1 |  | 107.5 | 101.1 | 101.1
Pkg-F (Section-II) |  | 88.43 |  | 95.5 | 98.741 | 98.741
Check Survey | 215 | 189.53 | 0 | 203 | 189.526 | 184.552 | 14.88 | 6.08 | 0.004 | 0 | 0 |  | 4.974 | 0
Pkg-G (Section-II) |  | 101.1 |  | 107.5 | 101.096 | 101.096 | 6.08 | 6.08 | 0.004
Pkg-F (Section-II) |  | 88.43 |  | 95.5 | 88.43 | 83.456 | 8.8 |  | 0 |  |  |  | 4.974
Foundation | 534 | 488 | 0 | 488 | 485 | 485 | 9 | 6 | 3 | 0 | 3 |  | 0 | 0 | 0
Pkg-G (Section-II) |  | 265 |  | 265 | 265 | 265 | 5 | 5 | 0 | [8 empty] | 9649905358 | D S Jangid
Pkg-F (Section-II) |  | 223 |  | 223 | 220 | 220 | 4 | 1 | 3 |  | 3 | [6 empty] | 7014675307 | jangid
Gang / Worker | [9 empty] | 10/180 | 02/55
Erection | 534 | 488 | 0 | 488 | 367 | 365 | 36 | 24 | 121 | 0 | 4 | 1 | 2 | 0 | 0
Pkg-G (Section-II) |  | 265 |  | 265 | 201 | 201 | 20 | 11 | 64 |  | 0
Pkg-F (Section-II) |  | 223 |  | 223 | 166 | 164 | 16 | 13 | 57 |  | 4 | 1 | 2 |  |  | 70/10 Complete
Gang / Worker | [9 empty] | 7/240 | 4/241
Stringing Payout | 215 | 189.53 | 0 | 189.53 | 94.743 | 94.743 | 0 | 9.18 | 94.787 | 0 | 1.881 | 0 | 0 | 0 | 15
Pkg-G (Section-II) |  | 101.1 |  | 101.1 | 52.284 | 52.284 |  |  | 48.816
Pkg-F (Section-II) |  | 88.43 |  | 88.43 | 42.459 | 42.459 |  | 9.18 | 45.971 |  | 1.881
Gang / Worker | [10 empty] | 2/154
Stringing Final sag | 215 | 189.53 | 0 | 189.53 | 88.935 | 88.935 | 0 | 14.161 | 100.595 | 0 | 5.808 | 0 | 0 | 0 | 15
Pkg-G (Section-II) |  | 101.1 |  | 101.1 | 49.703 | 49.703 |  | 4.981 | 51.397 |  | 2.581
Pkg-F (Section-II) |  | 88.43 |  | 88.43 | 39.232 | 39.232 |  | 9.18 | 49.198 |  | 3.227
Gang / Worker | [10 empty] | 2/154

## Survey-Summary (hidden)
PROJECT NAME | INDIGRID - 400kV D/C QUAD WZ-5 SAMBA-JALANDHAR & KISHENPUR-SAMBA TL | [10 empty] | COMP | APPROVED
START DATE (NOA DATE) | 16-MAY-2025 | [10 empty] | PENDING | UNDER REVIEW
KEC PROJECT | TB-605 | [11 empty] | PENDING
NAME OF CLIENT | RATLE KIRU POWER TRANSMISSION LIMITED
TITLE | SITE SURVEY STATUS
TEAM FORMATION | [5 empty] | CHECK SURVEY SUMMARY (KM)
Portion | SURVEY LEAD | TEAM MEMBERS | MACHINE | LINE NAME | SECTION LENGTH | COMPLETED | BALANCE | SUBMITTED | APPROVED | APPROVAL PENDING | REMARK
Jammu | 1)BIPPAN SHARMA | 2) Shiv Kumar( Asst Surveyor) | DGPS-1 TS-02 | 400kV D/C Jalandar - Samba T/L (GANTRY TO AP 52) | 46.915 | 46.44 | 0.475 | 46.053 | 46.053 | 0 | 0.48 km is from Sambha Gantyry to AP 4
|  | 3) Sahil Raj(Asst Surveyor) |  | 400kV D/C Samba - Kishenpur T/L | 33 | 27.138 | 5.862 | 19.6 | 19.6 | 0 | AP4-AP14, AP24-AP55, AP55-AP70, AP70-AP86,AP95-AP109 C/S Completed AP15-AP24 - Re-routing required due to landsliding (Hold) AP86-AP95 - Hold due to under powerline crossing
|  | 4) Sunil (Survey Helper) |  | LILO at Kistwar | 2.18 | 2.18 | 0 | 2.18 | 2.18 | 0 | Contour completed 12 Locations out of 13 location AP 11 conturing not done due to ROW since 29th Jul'25
|  | 5) Sanjhi Ram((Survey Helper) |  |  |  |  | 0 |  |  | 0
Punjab | 1)RAJ KAMAL GHOSH | 2) Anupam Basak (Survayor DET) | TS-01 | 400kV D/C Jalandar - Samba T/L ( AP 52-115) | 47.25 | 46.474 | 0.776 | 45.892 | 45.892 | 0
|  | 3) Kuldeep singh (supervisor DET) |  |  |  |  | 0 |  |  | 0
|  | 4) Vickey Ghosh (Survey DET) |  |  |  |  | 0 |  |  | 0
|  | 5) Rupak Kumar (Survey Helper) | [7 empty] | 0
Punjab | 1)SAGAR MAJHI | 2) Surajit Majhi(Asst Surveyor) | TS-01 | 400kV D/C Jalandar - Samba T/L ( AP 115-187) | 47.805 | 40.97 | 6.835 | 47.81 | 23.519 | 24.291
|  | 3) Rudra Madhav (supervisor DET) |  |  |  |  | 0 |  |  | 0
|  | 4)Gordhan Ram (supervisor DET) |  |  |  |  | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
TOTAL (KM) |  |  |  |  | 177.15 | 163.202 | 13.948 | 161.535 | 137.244 | 24.291 | 0
400kV D/C Samba-Jalandhar C/S -Details
[5 empty] | S.No | Section | Section | Length | Submitted | Approval Date | Remarks
[8 empty] | Km | Date
[5 empty] | 1 | AP20-AP30 | Jammu | 10.43 | 2025-07-08 | 2025-07-16
[5 empty] | 2 | AP30-AP41 | Jammu | 13.72 | 2025-07-19 | 2025-07-24
[5 empty] | 3 | AP41-AP51 | Jammu | 15.05 | 2025-07-30 | 2025-08-04
[5 empty] | 4 | AP15-AP20 | Jammu | 4.51 | 2025-09-08 | 2025-09-09
[5 empty] | 5 | AP5-AP15 | Jammu | 2.346 | 2025-09-18 | 2025-09-30
[5 empty] | 5 | AP53-AP66 | Punjab | 11.37 | 2025-08-06 | 2025-08-25
[5 empty] | 6 | AP70-AP84 | Punjab | 11.41 | 2025-08-16 | 2025-08-31
[5 empty] | 7 | AP84-AP96 | Punjab | 10.07 | 2025-08-21 | 2025-08-25
[5 empty] | 8 | AP115-AP123 | Punjab | 6.93 | 2025-08-19 | 2025-09-04
[5 empty] | 9 | AP131-AP140 | Punjab | 10.3 | 2025-08-19 | 2025-09-04
[5 empty] | 10 | AP145-AP153 | Punjab | 6.29 | 2025-08-23 | 2025-09-04
[5 empty] | 11 | AP96-AP115 | Punjab | 9.626 | 2025-09-13 | 2025-10-31
[5 empty] | 12 | AP66-AP70 | Punjab | 3.42 | 2025-09-19 | 2025-10-31
[5 empty] | 13 | AP153-AP175 | Punjab | 12.083 | 2025-09-22 |  | Route diversion in between 168-175 to be finalized
[5 empty] | Total |  |  | 127.555
400kV D/C Kishenpur-Samba C/S -Details
[5 empty] | S.No | Section | Section | Length | Submitted | Approval Date | Remarks
[8 empty] | Km | Date
[5 empty] | 1 | AP95-AP109 | Jammu | 3.13 | 2025-09-08 | 2025-09-09
[5 empty] | 2 | AP78-AP86 | Jammu | 1.945 | 2025-09-27 | 2025-09-30
[5 empty] | 3 | AP24-AP39 | Jammu | 5.5 | 16-10-2025 30-10-2025 | 2025-11-01
[5 empty] | 4 | AP39-AP55 | Jammu | 5.463 | 2025-11-24 | 2025-12-03
[5 empty] | 5 | AP4-AP14 | Jammu | 3.597 | 2025-12-03 | 2025-12-03
[5 empty] | Total |  |  | 19.635
LILO-Kisthewar C/S -Details
[5 empty] | S.No | Section | Section | Length | Submitted | Approval Date | Remarks
[8 empty] | Km | Date
[5 empty] | 1 | TP-Gantry | Kishtwar | 2.18 | 30-08-2025 08-09-2025 27-09-2025 | 2025-09-30
[5 empty] | Total |  |  | 2.18

## Sheet6 (hidden)
Survey
Line | Portion | Scope | Completed | Submitted | Approved
S-J | Jammu | 46.92 | 46.44 | 46.44 | 46.44
S-J | Punjab | 95.06 | 95.06 | 84.936 | 72.85
K-S |  | 33.103 | 23.393 | 16.04 | 10.6
LILO |  | 2.18 | 2.18 | 2.18 | 2.18
Total |  | 177.263 | 167.073 | 149.596 | 132.07
|  | 16.04 |  |  |  | 10.58
|  | 45.892 |  |  |  | 45.892
|  | 46.06 |  |  |  | 46.06
|  | 20.674 | 18.37 |  |  | 20.674
12.08
2.18
72.856

## Vertical Chart -JS Line Jammu
KEC INTERNATIONAL LIMITED
400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5-Jammu Portion
Vertical Chart
[9 empty] | Complete |  | 72 | 60 | 49 | 18 | 0
[9 empty] | WIP |  |  | 8 | 0 | 5 | 0
S.No | Tower | TOT | Angle of Deviation | Raised Chimney |  |  |  | FDN Classification | Span Length (Mtr) | Section Length (m) | ROW | Foundation | Earthing | Tower Erection | Tack Welding | Stringing | Remarks
|  |  |  | LEG A | LEG B | LEG C | LEG D
1 | AP5 | DD+0 | 47°01'59"LT | 0 | 0 | 0 | 0 |  |  | 0
119.059
2 | AP6 | DD+9 | 40°54'42"RT | 0 | 0 | 0 | 0 |  |  | 119.059
92.496
3 | AP7 | DD+30 | 47°08'48"LT | 4 | 4 | 4 | 4 |  |  | 92.496
[9 empty] | 134.988 | [7 empty] | 400 KV D/C Line Jalandhar to Samba
4 | AP8 | DD+30 | 41°15'08"RT | 4 | 4 | 4 | 4 |  |  | 134.988
365.176
5 | AP9 | DD+9 | 37°05'47"RT | 0 | 0 | 0 | 0 |  |  | 365.176
[9 empty] | 236.697 | [7 empty] | Railway Crossing Electrified (Jammu/Delhi)
6 | AP10 | DD+9 | 20°40'31"LT | 0 | 0 | 0 | 0 |  |  | 236.697
213.252
7 | AP11 | DD+25 | 51°34'02"RT | 0 | 0 | 0 | 0 |  |  | 213.252
[9 empty] | 206.593 | [7 empty] | 400 KV D/C Line Jalandhar to Samba
8 | AP12 | DD+30 | 47°50'13"LT | 0 | 0 | 0 | 0 |  |  | 206.593
[9 empty] | 289.862 | [7 empty] | 220 KV D/C Line Samba To Hiranagar
9 | AP13 | DD+25 | 39°08'44"LT | 1.5 | 1.5 | 0 | 0 |  |  | 289.862
402.938
10 | AP14 | DB+9 | 14°33'47"RT | 0 | 0 | 2 | 0 |  |  | 402.938
[9 empty] | 284.883 | [7 empty] | 220 KV D/C Line Bishnah-Hiranagar
11 | AP15 | DD+18 | 4°57'01"LT | 1.5 | 0 | 0 | 0 | WET |  | 284.883 | Clear | C
412.199
12 | 15/1 | DA+0 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C | C | C
428.128
13 | 15/2 | DA+0 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C | C
405.152
14 | 15/3 | DA+9 |  | 0 | 0 | 0 | 0 |  |  |  | Clear
427.96
15 | AP16 | DC+0 | 22°18'18"LT | 0 | 0 | 0 | 0 | FS |  | 1673.439 | Clear | C
285.948
16 | AP17 | DC+3 | 19°02'28"LT | 0 | 0 | 0 | 0 | FS |  | 285.948 | Clear | C | C
[9 empty] | 401.159 | [7 empty] | 66 KV H Pole (Sandhi) Ghagwal To Rajpura
17 | AP18 | DC+0 | 24°05'21"RT | 0 | 0 | 0 | 0 | FS |  | 401.159 | Clear | C | C | C
345
18 | 18/1 | DA+0 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C | C
360.001
19 | 18/2 | DA+6 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C
350.217
20 | AP19 | DC+0 | 24°17'20"LT | 0 | 0 | 0 | 0 | FS |  | 1055.218 | Clear | C | C | WIP
369.999
21 | 19/1 | DA+0 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C | C | C
360
22 | 19/2 | DA+0 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C | C
358.748
23 | AP20 | DB+6 | 5°25'51"RT | 1.5 | 1.5 | 1.5 | 1.5 | WET |  | 1088.747 | Clear | C | C
485.93
24 | AP21 | DD+6 | 39°17'49" RT | 1.5 | 1.5 | 1.5 | 1.5 | WET |  | 485.93 | Clear | WIP
325
25 | 21/1 | DA+0 |  | 0 | 0 | 0 | 0 | WET |  |  | Clear | C | C
387.337
26 | AP22 | DC+3 | 15°58'43"LT | 0 | 0 | 0 | 0 | WET |  | 712.337 | Clear | C | C
390
27 | 22/1 | DA+3 |  | 0 | 0 | 0 | 0 | WET |  |  | Clear | C | C
388.629
28 | 22/2 | DA+3 |  | 0 | 0 | 0 | 0 | WET |  |  | Clear | C | C
398.45
29 | AP23 | DB+0 | 9°30'47"LT | 0 | 0 | 0 | 0 | FS |  | 1177.079 | Clear | C | C | C
435.999
30 | 23/1 | DA+6 |  | 0 | 0 | 0 | 0 | WET |  |  | Clear | C | C | C
384
31 | 23/2 | DA+3 |  | 0 | 0 | 0 | 0
420
32 | 23/3 | DA+3 |  | 0 | 0 | 0 | 0 |  |  |  | Clear
410
33 | 23/4 | DA+3 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C
407.25
34 | 23/5 | DA+3 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C |  | WIP
397.702
35 | AP24 | DC+3 | 26°6'39"RT | 0 | 0 | 0 | 0 |  |  | 2454.951
366.004
36 | AP25 | DD+0 | 36°50'56"LT | 0 | 0 | 0 | 0 |  |  | 366.004 | Clear | WIP
372.4
37 | 25/1 | DA+0 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C
311.866
38 | 25/2 | DA+0 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C
343.763
39 | AP26 | DD+0 | 51°30'37"RT | 0 | 0 | 0 | 0 | FS |  | 1028.029 | Clear | C
442.371
40 | AP27 | DB+0 | 10°41'20"RT | 0 | 0 | 0 | 0 | WET |  | 442.371 | Clear | C | C | C
360
41 | 27/1 | DA+3 |  | 1.5 |  | 1.5 | 2.5 | WET |  |  | Clear | C | C
379.739
42 | AP28 | DC+6 | 27°47'33"LT | 1.5 | 2.5 | 1.5 | 1.5 | WET |  | 739.739 | Clear | C | C
445.991
43 | AP29 | DC+9 | 22°59'55"LT | 1.5 | 3 | 3 | 1.5 | WET |  | 445.991 | Clear | C | C
373
44 | 29/1 | DA+0 |  | 1.5 | 1.5 | 0 | 0 | WET |  |  | Clear | C | C |  |  |  | RC Pending
374
45 | 29/2 | DA+3 |  | 1 | 1 | 1 | 1 | PS(SD) |  |  | Clear | WIP
352
46 | 29/3 | DA+0 |  | 1.5 | 0 | 0 | 0 | DRY |  |  | Clear | C |  |  |  |  | RC Pending
406
47 | 29/4 | DA+0 |  | 0 | 0 | 0 | 0 | DRY |  |  | Clear | C | C | C
352
48 | 29/5 | DA+0 |  | 0 | 0 | 0 | 0 | WET |  |  | Clear | C | C | C
340
49 | 29/6 | DA+3 |  | 0 | 0 | 0 | 0 | WET |  |  | Clear | C | C | C
376.629
50 | AP30 | DB+0 | 05° 34' 43"LT | 0 | 0 | 0 | 0 | FS |  | 2573.629 | Clear | C
423
51 | 30/1 | DA+6 |  | 0 | 0 | 0 | 0 |  |  |  | Clear
417
52 | 30/2 | DA+0 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C | C
415
53 | 30/3 | DA+6 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C | C | C
421
54 | 30/4 | DA+0 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C | C
404
55 | 30/5 | DA+9 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C | C | C
434.73
56 | AP31 | DB+0 | 12° 48' 28"LT | 0 | 0 | 0 | 0 | FS |  | 2514.73 | Clear | C | C
395
57 | 31/1 | DA+3 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C | C | C
385
58 | 31/2 | DA+0 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C | C
395
59 | 31/3 | DA+0 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C | C | C
390
60 | 31/4 | DA+3 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C | C
420
61 | 31/5 | DA+3 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C
389.48
62 | AP32 | DB+0 | 09° 51' 20"RT | 0 | 0 | 0 | 0 | FS |  | 2374.48 | Clear | C | C | WIP
410
63 | 32/1 | DA+6 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C
426.984
64 | AP33 | DC+0 | 25° 29' 10"RT | 0 | 0 | 0 | 0 | FS |  | 836.984 | Clear | C | C
290
65 | 33/1 | DA+0 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | WIP
360
66 | 33/2 | DA+0 |  | 0 | 0 | 0 | 0
317.8
67 | AP34 | DB+0 | 05° 33' 15"RT | 0 | 0 | 0 | 0 |  |  | 967.8
427.154
68 | 34/1 | DA+6 |  | 0 | 0 | 0 | 0
392.753
69 | AP35 | DD+0 | 35° 45' 17"LT | 2 | 2 | 2 | 2 | FS |  | 819.907 | Clear | WIP
415
70 | 35/1 | DA+6 |  | 0 | 0 | 0 | 0
405.234
71 | AP36 | DC+0 | 18° 50' 40"RT | 0 | 0 | 0 | 0 |  |  | 820.234
439.8
72 | AP37 | DB+9 | 04° 23' 18"LT | 0 | 0 | 0 | 0 |  |  | 439.8
376
73 | 37/1 | DA+3 |  | 0 | 0 | 0 | 0
416
74 | 37/2 | DA+3 |  | 0 | 0 | 0 | 0
411.4
75 | AP38 | DB+0 | 12° 51' 19"RT | 0 | 0 | 0 | 0 |  |  | 1203.4
390
76 | 38/1 | DA+3 |  | 0 | 0 | 0 | 0
385.272
77 | AP39 | DB+0 | 10° 49' 41"LT | 0 | 0 | 0 | 0 |  |  | 775.272
399.206
78 | 39/1 | DA+3 |  | 0 | 0 | 0 | 0 | WET
407.487
79 | 39/2 | DA+0 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C
403.2
80 | AP40 | DC+3 | 14° 41' 57"LT | 0 | 0 | 0 | 0 | PS |  | 1209.893 | Clear | C | C
429.653
81 | 40/1 | DA+3 |  | 0 | 0 | 0 | 0 | WET |  |  | Clear | C | C | WIP
400.3
82 | 40/2 | DA+3 |  | 0 | 0 | 0 | 0
414.63
83 | 40/3 | DB+3 |  | 0 | 0 | 0 | 0
515.89
84 | AP41 | DD+30 | 36° 33' 25"LT | [6 empty] | 1760.473
212.443
85 | AP42 | DD+30 | 29° 48' 40"RT | [6 empty] | 212.443
459.999
86 | 42/1 | DA+0 |  | 0 | 0 | 0 | 0
260
87 | 42/2 | DA+0 |  | 0 | 0 | 0 | 0
330
88 | 42/3 | DA+0 |  | 0 | 0 | 0 | 0
311.04
89 | AP43 | DD+3 | 38° 14' 17"RT | 0 | 0 | 0 | 0 | WET |  | 1361.039 | Clear | C | C
408.948
90 | 43/1 | DA+6 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C
371.345
91 | 43/2 | DA+0 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C
364.114
92 | 43/3 | DA+3 |  | 0 | 0 | 0 | 0
419.36
93 | 43/4 | DA+0 |  | 0 | 0 | 0 | 0
348.129
94 | AP44 | DB+0 | 05° 00' 32"LT | 0 | 0 | 0 | 0 | PS |  | 1911.896 | Clear | WIP
367.848
95 | 44/1 | DA+0 |  | 0 | 0 | 0 | 0
396.726
96 | 44/2 | DA+0 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C
375.111
97 | 44/3 | DA+0 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C
335.003
98 | AP45 | DB+0 | 12° 18' 41"RT | 0 | 0 | 0 | 0 | WET |  | 1474.688 | Clear | C | C | WIP
360
99 | 45/1 | DA+3 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C
360
100 | 45/2 | DA+0 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C | C
359.496
101 | AP46 | DB+0 | 09° 05' 55"RT | 0 | 0 | 0 | 0 | FS |  | 1079.496 | Clear | WIP
350.739
102 | 46/1 | DA+0 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | C | C
337.891
103 | 46/2 | DA+0 |  | 0 | 0 | 0 | 0 |  |  |  | Clear
331.001
104 | 46/3 | DA+0 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C | C
360.369
105 | 46/4 | DA+0 |  | 0 | 0 | 0 | 0
425
106 | 46/5 | DA+6 |  | 0 | 0 | 0 | 0
411.448
107 | AP47 | DB+0 | 14° 19' 33"RT | 0 | 0 | 0 | 0 |  |  | 2216.448
298
108 | 47/1 | DA+0 |  | 1 | 1 | 1 | 1
349
109 | 47/2 | DA+0 |  | 0 | 0 | 0 | 0
350
110 | 47/3 | DA+0 |  | 0 | 0 | 0 | 0
363.364
111 | AP48 | DB+0 | 11° 23' 48"RT | 0 | 0 | 0 | 0 |  |  | 1360.364
371.504
112 | AP49 | DD+25 | 49° 40' 12"RT | 2 | 2 | 2 | 2 |  |  | 371.504
[9 empty] | 203.304 | [7 empty] | 400 KV D/C Line Jalandhar to Samba
113 | AP50 | DD+25 | 47° 29' 26"LT | 2 | 2 | 2 | 2 |  |  | 203.304
409.908
114 | AP50A | DC+0 | 26° 30' 32"LT | 0 | 0 | 0 | 0 |  |  | 409.908
412
115 | 50A/1 | DA+3 |  | 0 | 0 | 0 | 0
428
116 | 50A/2 | DA+3 |  | 0 | 0 | 0 | 0
409
117 | 50A/3 | DA+3 |  | 0 | 0 | 0 | 0 | PS |  |  | Clear | WIP
416
118 | 50A/4 | DA+0 |  | 0 | 0 | 0 | 0
397
119 | 50A/5 | DA+0 |  | 0 | 0 | 0 | 0
337
120 | 50A/6 | DA+3 |  | 0 | 0 | 0 | 0
451
121 | 50A/7 | DA+6 |  | 0 | 0 | 0 | 0 | FS |  |  | Clear | C
389
122 | 50A/8 | DA+0 |  | 0 | 0 | 0 | 0
395
123 | 50A/9 | DA+0 |  | 0 | 0 | 0 | 0
391
124 | 50A/10 | DA+0 |  | 0 | 0 | 0 | 0
425.903
125 | AP51 | DC+9 |  | 0 | 0 | 0 | 0 |  |  | 4450.903
46.0515

## Approved Survey (hidden)
KEC INTERNATIONAL LIMITED
400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5 |  |  |  | 400 kV Samba- Kishenpur D/C Line(Quad) - Wind Zone - 5
Approved Check Survey Sections |  |  |  | Approved Check Survey Sections
S.No | Portion | Section | Length Km | S.No | Section | Length Km
1 | Jammu | AP5-AP6 | 0.11906 | 1 | AP78-AP86 | 1.945
2 | Jammu | AP6-AP7 | 0.092496 | 2 | AP95-AP109 | 3.13
3 | Jammu | AP7-AP8 | 0.13499 | 3 | AP24-AP39 | 5.5
4 | Jammu | AP8-AP9 | 0.36518 | Total |  | 10.575
5 | Jammu | AP9-AP10 | 0.2367
6 | Jammu | AP10-AP11 | 0.21315 | LILO-Kishtwar
7 | Jammu | AP11-AP12 | 0.20659 | Approved Check Survey Sections
8 | Jammu | AP12-AP13 | 0.28986 | S.No | Section | Length Km
9 | Jammu | AP13-AP14 | 0.40294 | 1 | AP1-TP | 2.18
10 | Jammu | AP14-AP15 | 0.28488
11 | Jammu | AP15-AP16 | 1.6734
12 | Jammu | AP16-AP17 | 0.28595
13 | Jammu | AP17-AP18 | 0.40116
14 | Jammu | AP18-AP19 | 1.0552
15 | Jammu | AP19-AP20 | 1.0887
16 | Jammu | AP20-AP21 | 0.48593
17 | Jammu | AP21-AP22 | 0.71234
18 | Jammu | AP22-AP23 | 1.1771
19 | Jammu | AP23-AP24 | 2.455
20 | Jammu | AP24-AP25 | 0.36604
21 | Jammu | AP25-AP26 | 1.028
22 | Jammu | AP26-AP27 | 0.44237
23 | Jammu | AP27-AP28 | 0.73974
24 | Jammu | AP28-AP29 | 0.44599
25 | Jammu | AP29-AP30 | 2.5736
26 | Jammu | AP30-AP31 | 2.5147
27 | Jammu | AP31-AP32 | 2.3745
28 | Jammu | AP32-AP33 | 0.83698
29 | Jammu | AP33-AP34 | 0.9678
30 | Jammu | AP34-AP35 | 0.81991
31 | Jammu | AP35-AP36 | 0.82023
32 | Jammu | AP36-AP37 | 0.4398
33 | Jammu | AP37-AP38 | 1.2034
34 | Jammu | AP38-AP39 | 0.77527
35 | Jammu | AP39-AP40 | 1.2099
36 | Jammu | AP40-AP41 | 1.7605
37 | Jammu | AP41-AP42 | 0.21244
38 | Jammu | AP42-AP43 | 1.361
39 | Jammu | AP43-AP44 | 1.9119
40 | Jammu | AP44-AP45 | 1.4747
41 | Jammu | AP45-AP46 | 1.0795
42 | Jammu | AP46-AP47 | 2.2165
43 | Jammu | AP47-AP48 | 1.3604
44 | Jammu | AP48-AP49 | 0.3715
45 | Jammu | AP49-AP50 | 0.2033
46 | Jammu | AP50-AP50A | 0.40991
47 | Jammu | AP50A-AP51 | 4.4509
48 | Punjab | AP53-AP54 | 0.41666
49 | Punjab | AP54-AP55 | 0.38929
50 | Punjab | AP55-AP56 | 0.79345
51 | Punjab | AP56-AP57 | 1.9061
52 | Punjab | AP57-AP58 | 0.98237
53 | Punjab | AP58-AP59 | 0.40644
54 | Punjab | AP59-AP60 | 0.78804
55 | Punjab | AP60-AP61 | 0.75758
56 | Punjab | AP61-AP62 | 0.56392
57 | Punjab | AP62-AP63 | 1.0812
58 | Punjab | AP63-AP64 | 0.45086
59 | Punjab | AP64-AP65 | 0.60284
60 | Punjab | AP65-AP66 | 2.2285
61 | Punjab | AP70-AP71 | 1.599
62 | Punjab | AP71-AP72 | 1.6662
63 | Punjab | AP72-AP73 | 0.80957
64 | Punjab | AP73-AP74 | 0.40669
65 | Punjab | AP74-AP75 | 0.31625
66 | Punjab | AP75-AP76 | 0.24842
67 | Punjab | AP76-AP77 | 1.6815
68 | Punjab | AP77-AP78 | 1.6304
69 | Punjab | AP78-AP79 | 0.32074
70 | Punjab | AP79-AP80 | 0.24222
71 | Punjab | AP80-AP81 | 0.83925
72 | Punjab | AP81-AP82 | 0.24266
73 | Punjab | AP82-AP83 | 1.1492
74 | Punjab | AP83-AP84 | 0.25152
75 | Punjab | AP84-AP85 | 0.44513
76 | Punjab | AP85-AP86 | 0.83855
77 | Punjab | AP86-AP87 | 0.83676
78 | Punjab | AP87-AP88 | 1.1854
79 | Punjab | AP88-AP89 | 0.21106
80 | Punjab | AP89-AP90 | 0.61823
81 | Punjab | AP90-AP91 | 1.181
82 | Punjab | AP91-AP92 | 0.24768
83 | Punjab | AP92-AP93 | 1.4552
84 | Punjab | AP93-AP94 | 0.88908
85 | Punjab | AP94-AP95 | 0.41154
86 | Punjab | AP95-AP96 | 1.751
87 | Punjab | AP115-AP116 | 0.75141
88 | Punjab | AP116-AP117 | 0.51547
89 | Punjab | AP117-AP118 | 1.4097
90 | Punjab | AP118-AP119 | 0.63436
91 | Punjab | AP119-AP120 | 0.51818
92 | Punjab | AP120-AP121 | 1.2124
93 | Punjab | AP121-AP122 | 1.1369
94 | Punjab | AP122-AP123 | 0.75355
95 | Punjab | AP131-AP132 | 2.842
96 | Punjab | AP132-AP133 | 0.81608
97 | Punjab | AP133-AP134 | 0.22737
98 | Punjab | AP134-AP135 | 0.40137
99 | Punjab | AP135-AP136 | 1.2219
100 | Punjab | AP136-AP137 | 2.0004
101 | Punjab | AP137-AP138 | 1.0376
102 | Punjab | AP138-AP139 | 0.94497
103 | Punjab | AP139-AP140 | 0.80912
104 | Punjab | AP145-AP146 | 1.0669
105 | Punjab | AP146-AP147 | 0.24568
106 | Punjab | AP147-AP148 | 0.35293
107 | Punjab | AP148-AP149 | 0.2323
108 | Punjab | AP149-AP150 | 0.47498
109 | Punjab | AP150-AP151 | 0.93803
110 | Punjab | AP151-AP152 | 1.117
111 | Punjab | AP152-AP153 | 1.8616
Total |  |  | 102.4149

## Approved CS J-S Line (hidden)
Line: 400 kV D/C Quad Jalandhar-Samba TL
Approved Check Survey Tower Schedule
AS PER DETAIL SURVEY | [7 empty] | AS PER CHECK SURVEY
Sr. No. | Tower No. | Type of Tower | Span Length (m) | Section Length (m) | Angle of Deviation | UTM Coordinates |  | Sr. No. | Tower No. | Type of Tower | Raised Chimney |  |  |  | Leg Extension |  |  |  | Span Length (m) | Section Length (m) | Reduced Level | Angle of Deviation | UTM Coordinates |  | Crossing/Remarks
[6 empty] | Easting | Northing |  |  |  | LEG A | LEG B | LEG C | LEG D | LEG A | LEG B | LEG C | LEG D |  |  |  |  | Easting | Northing
1 | AP 5/0 | DD+18 |  | 0 | 47°01'57"L | 516661.837 | 3596578.147 | 1 | AP 5/0 | DD+0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 384.3 | 47°01'59"LT | 516472.785 | 3598642.658
|  |  | 119.059 | [15 empty] | 119.059 | [5 empty] | 2 nos 11 KV,Road Crossing
2 | AP 6/0 | DA+0 |  | 119.059 | 40°54'41"R | 516805.332 | 3596183.208 | 2 | AP 6/0 | DD+9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 119.059 | 384.202 | 40°54'42"RT | 516557.855 | 3598559.362
|  |  | 92.496 | [15 empty] | 92.496
3 | AP 7/0 | DA+0 |  | 211.555 | 47°08'48"L | 516948.802 | 3595788.337 | 3 | AP 7/0 | DD+25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 211.555 | 382.166 | 47°08'48"LT | 516565.421 | 3598467.176
|  |  | 134.989 | [15 empty] | 134.988 | [5 empty] | 400 KV(JAL-SAM) line Crossing
4 | AP 8/0 | DA+6 |  | 346.544 | 41°15'08"R | 517087.159 | 3595407.541 | 4 | AP 8/0 | DD+25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 346.543 | 377.89 | 41°15'08"RT | 516671.559 | 3598383.77
|  |  | 365.175 | [15 empty] | 365.176 | [5 empty] | Nalla Crossing
5 | AP 9/0 | DC+6 |  | 711.719 | 37°05'47"R | 517233.304 | 3595005.308 | 5 | AP 9/0 | DD+9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 711.719 | 373.28 | 37°05'47"RT | 516738.65 | 3598024.81
|  |  | 236.697 | [15 empty] | 236.697 | [5 empty] | 2 nos 25KV,Railway Crossing
6 | AP 10/0 | DC+3 |  | 948.416 | 20°40'31"L | 517425.65 | 3594793.72 | 6 | AP 10/0 | DD+9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 948.416 | 364.063 | 20°40'31"LT | 516633 | 3597813
|  |  | 213.252 | [15 empty] | 213.252
7 | AP 11/0 | DC+3 |  | 1161.668 | 51°34'01"R | 517777.572 | 3594601.159 | 7 | AP 11/0 | DD+25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1161.668 | 361.99 | 51°34'02"RT | 516611.322 | 3597600.853
|  |  | 206.592 | [15 empty] | 206.593 | [5 empty] | Cannal,11 KV,Road,400 kv(JAL-SAM) Line Crossing
8 | AP 12/0 | DA+0 |  | 1368.26 | 47°50'12"L | 517986.277 | 3594326.446 | 8 | AP 12/0 | DD+30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1368.261 | 353.883 | 47°50'13"LT | 516437.274 | 3597489.552
|  |  | 289.862 | [15 empty] | 289.862 | [5 empty] | 220 kv(HRN-SAM) Line Crossing
9 | AP 13/0 | DA+0 |  | 1658.122 | 39°08'44"L | 518204.057 | 3594039.789 | 9 | AP 13/0 | DD+25 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 0 | 0 |  | 1658.123 | 348.38 | 39°08'44"LT | 516389.11 | 3597203.72
|  |  | 402.938 | [15 empty] | 402.938 | [5 empty] | Cannal,Cart Track Crossing
10 | AP 14/0 | DC+0 |  | 2061.06 | 14°33'47"R | 518415.918 | 3593760.922 | 10 | AP 14/0 | DB+9 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 2061.061 | 345.17 | 14°33'47"RT | 516588.02 | 3596853.3
|  |  | 284.883 | [15 empty] | 284.883 | [5 empty] | River,220 KV(BAR-HRN)Line Crossing
11 | AP 15/0 | DA+0 |  | 2345.943 | 4°57'01"L | 518741.122 | 3593584.451 | 11 | AP 15/0 | DD+18 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 |  | 2345.944 | 341.282 | 4°57'01"LT | 516661.837 | 3596578.147
|  |  | 420.199 | [15 empty] | 412.199 | [5 empty] | Canal crosssing
12 | 15/1 | DA+0 |  |  |  | 516805.332 | 3596183.208 | 12 | 15/1 | DA+0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 337.118 |  | 516802.6 | 3596190.728
|  |  | 420.127 | [15 empty] | 428.128
13 | 15/2 | DA+0 |  |  |  | 516948.802 | 3595788.337 | 13 | 15/2 | DA+0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 331.591 |  | 516948.803 | 3595788.337
|  |  | 405.152 | [15 empty] | 405.152 | [5 empty] | Road and LT Line crossing
14 | 15/3 | DA+6 |  |  |  | 517087.159 | 3595407.541 | 14 | 15/3 | DA+9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 327.063 |  | 517087.159 | 3595407.541
|  |  | 427.96 | [15 empty] | 427.96
15 | AP 16/0 | DC+6 |  | 1673.438 | 22°18'18"LT | 517233.304 | 3595005.308 | 15 | AP 16/0 | DC+0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1673.439 | 320.406 | 22°18'18"LT | 517233.304 | 3595005.308
|  |  | 285.948 | [15 empty] | 285.948 | [5 empty] | 11 KV,Road,LTLine Crossing
16 | AP 17/0 | DC+3 |  | 285.948 | 19°02'28"LT | 517425.65 | 3594793.72 | 16 | AP 17/0 | DC+3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 285.948 | 317.232 | 19°02'28"LT | 517425.65 | 3594793.72 | LTLine to be shifted
|  |  | 401.159 | [15 empty] | 401.159 | [5 empty] | 11KV,66KV,Road,LTLine Crossing
17 | AP 18/0 | DC+3 |  | 401.159 | 24°05'21"RT | 517777.572 | 3594601.159 | 17 | AP 18/0 | DC+0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 401.159 | 315.046 | 24°05'21"RT | 517777.572 | 3594601.159
|  |  | 345 | [15 empty] | 345 | [5 empty] | LTLine Crossing
18 | 18/1 | DA+0 |  |  |  | 517986.277 | 3594326.446 | 18 | 18/1 | DA+0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 316.217 |  | 517986.277 | 3594326.446
|  |  | 360 | [15 empty] | 360.001
19 | 18/2 | DA+0 |  |  |  | 518204.057 | 3594039.789 | 19 | 18/2 | DA+0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 317.215 |  | 518204.057 | 3594039.789
|  |  | 350.217 | [15 empty] | 350.217 | [5 empty] | Canal crosssing
20 | AP 19/0 | DC+0 |  | 1055.217 | 24°17'20"LT | 518415.918 | 3593760.922 | 20 | AP 19/0 | DC+0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1055.218 | 317.08 | 24°17'20"LT | 518415.918 | 3593760.922
|  |  | 370 | [15 empty] | 369.999 | [5 empty] | LTLine,Road Crossing
21 | 19/1 | DA+0 |  |  |  | 518741.122 | 3593584.451 | 21 | 19/1 | DA+0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 318.753 |  | 518741.122 | 3593584.451
|  |  | 360 | [15 empty] | 360 | [5 empty] | Canal,nalla crosssing
22 | 19/2 | DA+0 |  |  |  | 519057.537 | 3593412.749 | 22 | 19/2 | DA+0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 318.952 |  | 519057.537 | 3593412.749
|  |  | 358.747 | [15 empty] | 358.748 | [5 empty] | Road and LT Line crossing
23 | 20/0 | DB+6 |  | 0 |  | 519372.851 | AP24-AP39 | 23 | 20/0 | DB+6 | Raised Chimney LEG A: Comments by RKPTL , need to be rectified by M/s. KEC; Raised Chimney LEG B: 1.5; Raised Chimney LEG C: 1.5; Raised Chimney LEG D: 1.5 |  | 0 | 320.649 |  | 519372.851 | 3593241.644
|  |  | 485.93 | [15 empty] | 485.93 | [5 empty] | River Crossing
24 | 21/0 | DD+6 |  | 485.93 | 39° 17' 49"RT | 519776.097 | 3592970.498 | 24 | 21/0 | DD+6 | Raised Chimney LEG A: 1.5; Raised Chimney LEG B: 1.5; Raised Chimney LEG C: 1.5; Raised Chimney LEG D: 1.5 |  | 485.93 | 319.74 | 39°17'49" RT | 519776.097 | 3592970.498
|  |  | 325 | [15 empty] | 325 | [5 empty] | 2 nos LT Line,Cart Track
25 | 21/1 | DA+0 |  |  |  | 519869.956 | 3592659.346 | 25 | 21/1 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 316.858 |  | 519869.956 | 3592659.346 | LT Line to be shifted
|  |  | 387.337 | [15 empty] | 387.337 | [5 empty] | 11 kv Line Crossing
26 | 22/0 | DC+3 |  | 712.337 | 15°58'43"LT | 519981.816 | 3592288.512 | 26 | 22/0 | DC+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 712.337 | 312.93 | 15°58'43"LT | 519981.816 | 3592288.512
|  |  | 390 | [15 empty] | 390 | [5 empty] | 3nos LT Line,Road,11 KV Crossing
27 | 22/1 | DA+3 |  |  |  | 520192.878 | 3591960.56 | 27 | 22/1 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 310.637 |  | 520192.878 | 3591960.56
|  |  | 388.629 | [15 empty] | 388.629 | [5 empty] | LT Line crosiing
28 | 22/2 | DA+3 |  |  |  | 520403.198 | 3591633.76 | 28 | 22/2 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 306.671 |  | 520403.198 | 3591633.76
|  |  | 398.45 | [15 empty] | 398.45 | [5 empty] | 2 nos LT Line Crossing
29 | 23/0 | DB+0 |  | 1177.079 | 9°30'47"LT | 520618.833 | 3591298.703 | 29 | 23/0 | DB+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 1177.079 | 303.472 | 9°30'47"LT | 520618.833 | 3591298.703
|  |  | 419.999 | [15 empty] | 435.999 | [5 empty] | Road and LT Line Crossing
30 | 23/1 | DA+6 |  |  |  | 520901.376 | 3590987.947 | 30 | 23/1 | DA+6 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 299.951 |  | 520912.1393 | 3590976.1085
|  |  | 400 | [15 empty] | 384 | [5 empty] | Road,LT Line,11 KV Line Crossing
31 | 23/2 | DA+3 |  |  |  | 521170.464 | 3590691.989 | 31 | 23/2 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 296.476 |  | 521170.464 | 3590691.989
|  |  | 420 | [15 empty] | 420 | [5 empty] | LT Line Crossing
32 | 23/3 | DA+3 |  |  |  | 521453.008 | 3590381.233 | 32 | 23/3 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 293.587 |  | 521453.008 | 3590381.233
|  |  | 410 | [15 empty] | 410 | [5 empty] | 2 nos LT Line Crossing
33 | 23/4 | DA+3 |  |  |  | 521728.824 | 3590077.875 | 33 | 23/4 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 290.264 |  | 521728.824 | 3590077.875
|  |  | 407.25 | [15 empty] | 407.25 | [5 empty] | 2 LT Line,Nalla Crossing
34 | 23/5 | DA+3 |  |  |  | 522002.79 | 3589776.553 | 34 | 23/5 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 286.229 |  | 522002.79 | 3589776.553
|  |  | 397.702 | [15 empty] | 397.702 | [5 empty] | 11 KV,Nalla,Road Crossing
35 | 24/0 | DC+0 |  | 2454.951 | 26° 06' 39"RT | 522270.332 | 3589482.295 | 35 | 24/0 | DC+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 2454.951 | 284.901 | 26°6'39"RT | 522270.332 | 3589482.295
|  |  | 310.147 | [15 empty] | 366.004 | [5 empty] | 2 nos LT Line, Road Crossing
36 | 25/0 | DD+0 |  | 310.147 | 35° 11' 52"LT | 522356.687 | 3589184.412 | 36 | 25/0 | DD+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 366.004 | 282.934 | 36°50'56"LT | 522372.24 | 3589130.764
|  |  | 374.999 | [15 empty] | 372.4 | [5 empty] | Nalla Crossing
37 | 25/1 | DA+0 |  |  |  | 522649.611 | 3588950.275 | 37 | 25/1 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 282.874 |  | 522669.712 | 3588906.729
|  |  | 330 | [15 empty] | 311.866 | [5 empty] | Drain, 2nos LT Line,Road Crossing,
38 | 25/2 | DA+0 |  |  |  | 522907.385 | 3588744.234 | 38 | 25/2 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 283.88 |  | 522918.83 | 3588719.11
|  |  | 366.046 | [15 empty] | 343.763 | [5 empty] | LT Line Crossing
39 | 26/0 | DD+0 |  | 1071.045 | 49° 51' 22"RT | 523193.315 | 3588515.688 | 39 | 26/0 | DD+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 1028.029 | 284.271 | 51°30'37"RT | 523193.427 | 3588512.303
|  |  | 445.757 | [15 empty] | 442.371 | [5 empty] | River Crossing
40 | 27/0 | DB+0 |  | 445.757 | 10° 41' 31"RT | 523205.047 | 3588070.085 | 40 | 27/0 | DB+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 442.371 | 299.465 | 10°41'20"RT | 523205.047 | 3588070.085
|  |  | 320 | [15 empty] | 360 | [5 empty] | LT Line Crossing
41 | 27/1 | DA+3 |  |  |  | 523153.976 | 3587754.187 | 41 | 27/1 | DA+3 | [10 empty] | 295.54 |  | 523147.5919 | 3587714.6997 | Contouring Required | bar: Raised Chimney LEG A to Raised Chimney LEG D
|  |  | 419.739 | [15 empty] | 379.739 | [5 empty] | Road Crossing
42 | 28/0 | DC+6 |  | 739.739 | 27° 47' 33"LT | 523086.985 | 3587339.828 | 42 | 28/0 | DC+6 | Raised Chimney LEG A: 2; Raised Chimney LEG B: 2; Raised Chimney LEG C: 2; Raised Chimney LEG D: 2 |  | 739.739 | 299.027 | 27°47'33"LT | 523086.985 | 3587339.828 | Contouring Required
|  |  | 445.991 | [15 empty] | 445.991 | [5 empty] | 11 KV Line,Road Crossing
43 | 29/0 | DC+9 |  | 445.991 | 22° 59' 55"LT | 523229.302 | 3586917.153 | 43 | 29/0 | DC+9 | Raised Chimney LEG A: 2; Raised Chimney LEG B: 2; Raised Chimney LEG C: 2; Raised Chimney LEG D: 2 |  | 445.991 | 297.021 | 22°59'55"LT | 523229.302 | 3586917.153 | Contouring Required
|  |  | 378 | [15 empty] | 373 | [5 empty] | LT Line Crossing
44 | 29/1 | DA+0 |  |  |  | 523480.302 | 3586634.517 | 44 | 29/1 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 295.767 |  | 523476.9819 | 3586638.2556 | LT Line to be shifted,Contouring Required
|  |  | 361 | [15 empty] | 374
45 | 29/2 | DA+3 |  |  |  | 523720.014 | 3586364.593 | 45 | 29/2 | DA+3 | [10 empty] | 287.94 |  | 523725.3262 | 3586358.6113 | bar: Raised Chimney LEG A to Raised Chimney LEG D
|  |  | 356 | [15 empty] | 352
46 | 29/3 | DA+0 |  |  |  | 523956.405 | 3586098.407 | 46 | 29/3 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 296.014 |  | 523959.0613 | 3586095.4159 | Conturing Required
|  |  | 410 | [15 empty] | 406
47 | 29/4 | DA+0 |  |  |  | 524228.654 | 3585791.844 | 47 | 29/4 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 298.58 |  | 524228.654 | 3585791.844 | Conturing Required
|  |  | 358 | [15 empty] | 352 | [5 empty] | 11 KV Line Crossing
48 | 29/5 | DA+0 |  |  |  | 524466.373 | 3585524.162 | 48 | 29/5 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 296.73 |  | 524462.389 | 3585528.649
|  |  | 324 | [15 empty] | 340 | [5 empty] | Road Crossing
49 | 29/6 | DA+0 |  |  |  | 524681.516 | 3585281.903 | 49 | 29/6 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 287.329 |  | 524688.156 | 3585274.426 | Conturing Required
|  |  | 386.629 | [15 empty] | 376.629 | [5 empty] | 2 nos LTLine,Road,11KV Line Crossing
50 | AP 30/0 | DB+0 |  | 2573.629 | 05° 34' 43"LT | 524938.246 | 3584992.815 | 50 | AP 30/0 | DB+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 2573.629 | 283.957 | 05° 34' 43"LT | 524938.246 | 3584992.815
|  |  | 423 | [15 empty] | 423 | [5 empty] | 11 KV Line Crossing
51 | 30/1 | DA+6 |  |  |  | 525248.542 | 3584705.335 | 51 | 30/1 | DA+6 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 282.422 |  | 525248.542 | 3584705.335
|  |  | 417 | [15 empty] | 417 | [5 empty] | Nalla Crossing
52 | 30/2 | DA+0 |  |  |  | 525554.438 | 3584421.932 | 52 | 30/2 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 281.581 |  | 525554.437 | 3584421.932
|  |  | 415 | [15 empty] | 415 | [5 empty] | Nalla Crossing
53 | 30/3 | DA+6 |  |  |  | 525858.866 | 3584139.888 | 53 | 30/3 | DA+6 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 280.866 |  | 525858.865 | 3584139.889
|  |  | 421 | [15 empty] | 421 | [5 empty] | Cart Track,
54 | 30/4 | DA+0 |  |  |  | 526167.695 | 3583853.767 | 54 | 30/4 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 279.306 |  | 526167.695 | 3583853.768
|  |  | 404 | [15 empty] | 404
55 | 30/5 | DA+9 |  |  |  | 526464.054 | 3583579.2 | 55 | 30/5 | DA+9 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 277.739 |  | 526464.054 | 3583579.2
|  |  | 434.729 | [15 empty] | 434.73 | [5 empty] | Nalla, 2 nos 11 kv,Road Crossing
56 | AP 31/0 | DB+0 |  | 2514.729 | 12° 48' 28"LT | 526782.955 | 3583283.748 | 56 | AP 31/0 | DB+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 2514.73 | 276.594 | 12° 48' 28"LT | 526782.955 | 3583283.748
|  |  | 395 | [15 empty] | 395
57 | 31/1 | DA+3 |  |  |  | 527125.013 | 3583086.211 | 57 | 31/1 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 276.084 |  | 527125.013 | 3583086.211
|  |  | 385 | [15 empty] | 385
58 | 31/2 | DA+0 |  |  |  | 527458.413 | 3582893.675 | 58 | 31/2 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 274.623 |  | 527458.412 | 3582893.675
|  |  | 395 | [15 empty] | 395
59 | 31/3 | DA+0 |  |  |  | 527800.471 | 3582696.138 | 59 | 31/3 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 274.094 |  | 527800.471 | 3582696.138
|  |  | 390 | [15 empty] | 390
60 | 31/4 | DA+3 |  |  |  | 528138.2 | 3582501.102 | 60 | 31/4 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 271.88 |  | 528138.2 | 3582501.102
|  |  | 420 | [15 empty] | 420 | [5 empty] | Nalla,Cart Track
61 | 31/5 | DA+3 |  |  |  | 528501.908 | 3582291.063 | 61 | 31/5 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 271.69 |  | 528501.908 | 3582291.063
|  |  | 389.477 | [15 empty] | 389.48 | [5 empty] | LT Line Crossing
62 | AP 32/0 | DB+0 |  | 2374.477 | 09° 51' 20"RT | 528839.184 | 3582096.288 | 62 | AP 32/0 | DB+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 2374.48 | 270.444 | 09° 51' 20"RT | 528839.184 | 3582096.288
|  |  | 409.999 | [15 empty] | 410 | [5 empty] | Road,11KV Crossing
63 | 32/1 | DA+6 |  |  |  | 529153.896 | 3581833.504 | 63 | 32/1 | DA+6 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 268.214 |  | 529153.896 | 3581833.504
|  |  | 426.984 | [15 empty] | 426.984 | [5 empty] | Nalla Crossing
64 | AP 33/0 | DC+0 |  | 836.983 | 25° 29' 10"RT | 529481.646 | 3581559.834 | 64 | AP 33/0 | DC+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 836.984 | 266.756 | 25° 29' 10"RT | 529481.646 | 3581559.834
|  |  | 289.999 | [15 empty] | 290
65 | 33/1 | DA+0 |  |  |  | 529602.607 | 3581296.266 | 65 | 33/1 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 264.567 |  | 529602.607 | 3581296.267
|  |  | 360 | [15 empty] | 360 | [5 empty] | Nalla Crossing
66 | 33/2 | DA+0 |  |  |  | 529752.766 | 3580969.078 | 66 | 33/2 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 264.358 |  | 529752.766 | 3580969.078
|  |  | 317.799 | [15 empty] | 317.8 | [5 empty] | Nalla,LT Line Crossing
67 | AP 34/0 | DB+0 |  | 967.798 | 05° 33' 15"RT | 529885.323 | 3580680.244 | 67 | AP 34/0 | DB+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 967.8 | 264.775 | 05° 33' 15"RT | 529885.323 | 3580680.244
|  |  | 412.154 | [15 empty] | 427.154 | [5 empty] | Hut,3 nos LT Line Crossing
68 | 34/1 | DA+3 |  |  |  | 530020.173 | 3580290.775 | 68 | 34/1 | DA+6 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 264.717 |  | 530025.08 | 3580276.601
|  |  | 407.753 | [15 empty] | 392.753 | [5 empty] | Carty Track,LT Line,Nalla Crossing
69 | AP 35/0 | DD+0 |  | 819.907 | 35° 45' 17"LT | 530153.583 | 3579905.464 | 69 | AP 35/0 | DD+0 | Raised Chimney LEG A: 2; Raised Chimney LEG B: 2; Raised Chimney LEG C: 2; Raised Chimney LEG D: 2 |  | 819.907 | 263.836 | 35° 45' 17"LT | 530153.583 | 3579905.464
|  |  | 415 | [15 empty] | 415 | [5 empty] | LT Line,2nos 11 kv, Road Crossing
70 | 35/1 | DA+6 |  |  |  | 530492.917 | 3579666.555 | 70 | 35/1 | DA+6 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 264.417 |  | 530492.917 | 3579666.555
|  |  | 405.233 | [15 empty] | 405.234 | [5 empty] | LT Line Crossing
71 | AP 36/0 | DC+0 |  | 820.233 | 15° 39' 07"RT | 530824.265 | 3579433.269 | 71 | AP 36/0 | DC+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 820.234 | 263.776 | 18° 50' 40"RT | 530824.265 | 3579433.269
|  |  | 425.904 | [15 empty] | 439.8
72 | 36/1 | DA+6 |  |  |  | 531093.452 | 3579103.22 | 72 | AP 37/0 | DB+9 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 439.8 | 264.091 | 04° 23' 18"LT | 531082.822 | 3579077.502
|  |  | 380.069 | [15 empty] | 376 | [5 empty] | Road, 11 kv crossing
73 | 36/2 | DA+6 |  |  |  | 531333.669 | 3578808.69 | 73 | 37/1 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 263.543 |  | 531326.349 | 3578791.022
|  |  | 416.942 | [15 empty] | 416 | [5 empty] | 2 nos LT Line,Road, 11 kv Line Crossing
74 | 36/3 | DA+3 |  |  |  | 531597.192 | 3578485.585 | 74 | 37/2 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 261.313 |  | 531595.782 | 3578474.066
|  |  | 419.356 | [15 empty] | 411.4 | [5 empty] | Nalla, Cart Track Crossing
75 | AP 37/0 | DC+0 |  | 1642.271 | 11° 41' 21"RT | 531862.24 | 3578160.61 | 75 | AP 38/0 | DB+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 1203.4 | 261.432 | 12° 51' 19"RT | 531862.24 | 3578160.61
|  |  | 390 | [15 empty] | 390
76 | 37/1 | DA+3 |  |  |  | 532042.391 | 3577814.712 | 76 | 38/1 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 260.879 |  | 532042.391 | 3577814.712
|  |  | 385.272 | [15 empty] | 385.272
77 | AP 38/0 | DC+0 |  | 775.272 | 10° 49' 41"LT | 532220.358 | 3577473.007 | 77 | AP 39/0 | DB+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 775.272 | 260.635 | 10° 49' 41"LT | 532220.358 | 3577473.007
|  |  | 399.206 | [15 empty] | 399.206 | [5 empty] | 2 times 11 kv Line, Road, LT Line,Cart Track
78 | 38/1 | DA+3 |  |  |  | 532467.993 | 3577159.89 | 78 | 39/1 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 258.646 |  | 532467.993 | 3577159.89
|  |  | 407.487 | [15 empty] | 407.487 | [5 empty] | Nalla,2 nos 11 kv line,Road Crossing
79 | 38/2 | DA+0 |  |  |  | 532720.765 | 3576840.278 | 79 | 39/2 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 258.609 |  | 532720.765 | 3576840.278
|  |  | 403.201 | [15 empty] | 403.2 | [5 empty] | Cart Track Crossing
80 | AP 39/0 | DC+3 |  | 1209.894 | 14° 41' 57"LT | 532970.879 | 3576524.027 | 80 | AP 40/0 | DC+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 1209.893 | 258.404 | 14° 41' 57"LT | 532970.879 | 3576524.027
|  |  | 429.653 | [15 empty] | 429.653
81 | 39/1 | DA+3 |  |  |  | 533314.189 | 3576265.687 | 81 | 40/1 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 258.158 |  | 533314.189 | 3576265.687
|  |  | 400.296 | [15 empty] | 400.3 | [5 empty] | 11 kv Line,Road,Nalla Crossing
82 | 39/2 | DA+3 |  |  |  | 533634.042 | 3576024.998 | 82 | 40/2 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 256.271 |  | 533634.042 | 3576024.998
|  |  | 414.63 | [15 empty] | 414.63 | [5 empty] | Nalla,11 kv Crossing
83 | 39/3 | DB+3 |  |  |  | 533965.348 | 3575775.69 | 83 | 40/3 | DB+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 256.993 |  | 533965.348 | 3575775.69
|  |  | 515.886 | [15 empty] | 515.89 | [5 empty] | Road Crossing
84 | AP 40/0 | DD+25 |  | 1760.465 | 36° 33' 25"LT | 534377.562 | 3575465.5 | 84 | AP 41/0 | DD+25 | Raised Chimney LEG A: 4; Raised Chimney LEG B: 4; Raised Chimney LEG C: 4; Raised Chimney LEG D: 4 |  |  | 256.55 | 36° 33' 25"LT | 534377.562 | 3575465.5
|  |  | 212.443 | [15 empty] | 212.443 | [5 empty] | 400 KV D/C Crossing
85 | AP 41/0 | DD+25 |  | 212.443 | 29° 48' 40"RT | 534590 | 3575464 | 85 | AP 42/0 | DD+25 | Raised Chimney LEG A: 4; Raised Chimney LEG B: 4; Raised Chimney LEG C: 4; Raised Chimney LEG D: 4 |  | 212.443 | 255.764 | 29° 48' 40"RT | 534590 | 3575464 | LT Line to be shifted
|  |  | 440 | [15 empty] | 459.999 | [5 empty] | 2 nos 11KV, Road and Nalla Crossing
86 | 41/1 | DA+0 |  |  |  | 534970.22 | 3575242.568 | 86 | 42/1 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 255.089 |  | 534987.503 | 3575232.503
|  |  | 280 | [15 empty] | 260
87 | 41/2 | DA+0 |  |  |  | 535212.179 | 3575101.656 | 87 | 42/2 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 255.033 |  | 535212.178 | 3575101.656
|  |  | 330 | [15 empty] | 330 | [5 empty] | Nalla crossing
88 | 41/3 | DA+0 |  |  |  | 535497.344 | 3574935.582 | 88 | 42/3 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 255.023 |  | 535497.344 | 3574935.582
|  |  | 311.04 | [15 empty] | 311.04 | [5 empty] | 2 nos 11KV, and Cart Track Crossing
89 | AP 42/0 | DD+0 |  | 1361.04 | 36° 03' 25"RT | 535766.125 | 3574779.049 | 89 | AP 43/0 | DD+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 1361.039 | 255.179 | 38° 14' 17"RT | 535766.125 | 3574779.049
|  |  | 389.999 | [15 empty] | 408.948 | [5 empty] | 11 KV Line,River Crossing
90 | 42/1 | DA+3 |  |  |  | 535923.054 | 3574422.016 | 90 | 43/1 | DA+6 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 256.009 |  | 535916.313 | 3574398.678
|  |  | 385 | [15 empty] | 371.345
91 | 42/2 | DA+0 |  |  |  | 536077.972 | 3574069.559 | 91 | 43/2 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 255.012 |  | 536052.691 | 3574053.282
|  |  | 385 | [15 empty] | 364.114 | [5 empty] | LT Line,11KV Line and Road Crossing
92 | 42/3 | DA+3 |  |  |  | 536232.889 | 3573717.103 | 92 | 43/3 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 255.347 |  | 536186.413 | 3573714.612
|  |  | 400 | [15 empty] | 419.36 | [5 empty] | 11 KV Crossing
93 | 42/4 | DA+0 |  |  |  | 536393.843 | 3573350.914 | 93 | 43/4 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 255.104 |  | 536340.424 | 3573324.557
|  |  | 357.48 | [15 empty] | 348.129 | [5 empty] | Road,11 KV,LT Line Crossing
94 | 42/5 | DA+0 |  |  |  | 536537.687 | 3573023.652 | 94 | 44/0 | DB+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 1911.896 | 254.781 | 05° 00' 32"LT | 536468.276 | 3573000.755
|  |  | 367.825 | [15 empty] | 367.848 | [5 empty] | 11 KV Line,LT Line Crossing
95 | 42/6 | DA+0 |  |  |  | 536685.693 | 3572686.919 | 95 | 44/1 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 254.789 |  | 536632.726 | 3572671.713
|  |  | 387.171 | [15 empty] | 396.726 | [5 empty] | Cart Track,Nalla Crossing
96 | 42/7 | DA+0 |  |  |  | 536841.484 | 3572332.475 | 96 | 44/2 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 254.287 |  | 536810.086 | 3572316.84
|  |  | 375.543 | [15 empty] | 375.111 | [5 empty] | Cart Track,LT Line Crossing
97 | 42/8 | DA+0 |  |  |  | 536992.596 | 3571988.676 | 97 | 44/3 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 253.675 |  | 536977.783 | 3571981.302
|  |  | 335.385 | [15 empty] | 335.003 | [5 empty] | 11 KV, LT Line Road crossing
98 | AP 43/0 | DB+0 |  | 3383.403 | 09° 29' 0"RT | 537127.55 | 3571681.64 | 98 | AP 45/0 | DB+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 1474.688 | 253.7 | 12° 18' 41"RT | 537127.55 | 3571681.64 | Lcation Spotted on Bore Well
|  |  | 360 | [15 empty] | 360 | [5 empty] | Road,11 KV,Nalla Crossing
99 | 43/1 | DA+3 |  |  |  | 537216.128 | 3571332.708 | 99 | 45/1 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 252.708 |  | 537216.128 | 3571332.708
|  |  | 360 | [15 empty] | 360 | [5 empty] | 2 nos Cart Track and Road Crossing
100 | 43/2 | DA+0 |  |  |  | 537304.706 | 3570983.775 | 100 | 45/2 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 253.174 |  | 537304.706 | 3570983.775
|  |  | 359.496 | [15 empty] | 359.496 | [5 empty] | LT Line Crossing
101 | AP 44/0 | DB+0 |  | 1079.496 | 09° 05' 54"RT | 537393.16 | 3570635.331 | 101 | AP 46/0 | DB+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 1079.496 | 253.122 | 09° 05' 55"RT | 537393.16 | 3570635.331
|  |  | 350.739 | [15 empty] | 350.739 | [5 empty] | 2nos 11KV,LT Line and Road Crossing
102 | 44/1 | DA+0 |  |  |  | 537424.615 | 3570286.005 | 102 | 46/1 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 252.533 |  | 537424.615 | 3570286.005
|  |  | 337.891 | [15 empty] | 337.891 | [5 empty] | Drain Crossing
103 | 44/2 | DA+0 |  |  |  | 537454.918 | 3569949.476 | 103 | 46/2 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 251.738 |  | 537454.918 | 3569949.476
|  |  | 331.001 | [15 empty] | 331.001 | [5 empty] | 2nos 11KV Line Crossing
104 | 44/3 | DA+0 |  |  |  | 537484.604 | 3569619.809 | 104 | 46/3 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 252.177 |  | 537484.604 | 3569619.809
|  |  | 370.369 | [15 empty] | 360.369 | [5 empty] | 11 KV,3nos LTLine,Nalla Crossing and Poplar Orchard
105 | 44/4 | DA+0 |  |  |  | 537517.82 | 3569250.932 | 105 | 46/4 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 252.018 |  | 537516.923 | 3569260.892
|  |  | 415 | [15 empty] | 425 | [5 empty] | Nalla,Road Crossing
106 | 44/5 | DA+6 |  |  |  | 537555.039 | 3568837.605 | 106 | 46/5 | DA+6 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 251.398 |  | 537555.039 | 3568837.605
|  |  | 411.448 | [15 empty] | 411.448
107 | AP 45/0 | DB+0 |  | 2216.448 | 14° 19' 34"LT | 537591.939 | 3568427.815 | 107 | AP 47/0 | DB+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 2216.448 | 250.71 | 14° 19' 33"RT | 537591.939 | 3568427.815 | poplar orchard
|  |  | 288.426 | [15 empty] | 298 | [5 empty] | LTLine and Poplar orchard
108 | 45/1 | DA+0 |  |  |  | 537545.922 | 3568143.083 | 108 | 47/1 | DA+0 | [10 empty] | 251.309 |  | 537544.395 | 3568133.632 | poplar orchard | bar: Raised Chimney LEG A to Raised Chimney LEG D
|  |  | 378.896 | [15 empty] | 349
109 | 45/2 | DA+0 |  |  |  | 537485.472 | 3567769.04 | 109 | 47/2 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 250.317 |  | 537488.714 | 3567789.102 | poplar orchard
|  |  | 330.346 | [15 empty] | 350 | [5 empty] | 2nos Cart Track and 11 KV Line Crossing
110 | 45/3 | DA+0 |  |  |  | 537432.768 | 3567442.926 | 110 | 47/3 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 250.186 |  | 537432.874 | 3567443.585
|  |  | 362.696 | [15 empty] | 363.364 | [5 empty] | LTLine Crossing
111 | 45/4 | DA+0 |  |  |  | 537374.902 | 3567084.876 | 111 | AP 48 | DB+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 1360.364 | 250.509 | 11° 23' 48"RT | 537374.902 | 3567084.876
|  |  | 349.635 | [15 empty] | 371.504
112 | 45/5 | DB+0 |  |  |  | 537319.12 | 3566739.719 | 112 | AP 49 | DD+25 | Raised Chimney LEG A: 2; Raised Chimney LEG B: 2; Raised Chimney LEG C: 2; Raised Chimney LEG D: 2 |  | 371.504 | 250.679 | 49° 40' 12"RT | 537244.331 | 3566737.074 | Poplar orchard
|  |  | 313.602 | [15 empty] | 203.304 | [5 empty] | 400 KV D/C Crossing
113 | AP 46/0 | DD+25 |  | 2023.601 | 56° 14' 34"RT | 537269.087 | 3566430.134 | 113 | AP 50 | DD+25 | Raised Chimney LEG A: 2; Raised Chimney LEG B: 2; Raised Chimney LEG C: 2; Raised Chimney LEG D: 2 |  | 203.304 | 250.612 | 47° 29' 26"LT | 537052.994 | 3566668.353
|  |  | 203.662 | [15 empty] | 409.908 | [5 empty] | Cart Track and LT Line Crossing
114 | AP 47/0 | DD+30 |  | 203.662 | 56° 35' 59"LT | 537083.876 | 3566345.429 | 114 | AP 50A/0 | DC+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 409.908 | 250.497 | 26° 30' 32"LT | 536894.457 | 3566290.345
|  |  | 432.85 | [15 empty] | 412 | [5 empty] | Road Crossing
115 | 47/1 | DB+9 |  |  |  | 537017.479 | 3565917.702 | 115 | 50A/1 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 249.936 |  | 536921.443 | 3565879.23
|  |  | 475.239 | [15 empty] | 428 | [5 empty] | 2 nos 11kv Line Crossing
116 | AP 48/0 | DB+6 |  | 908.089 | 12° 39' 41"LT | 536944.579 | 3565448.087 | 116 | 50A/2 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 249.342 |  | 536949.478 | 3565452.149
|  |  | 407.305 | [15 empty] | 409 | [5 empty] | 2 nos 11kv Line and Road Crossing
117 | 48/1 | DA+0 |  |  |  | 536971.839 | 3565041.696 | 117 | 50A/3 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 249.638 |  | 536976.269 | 3565044.027
|  |  | 383.49 | [15 empty] | 416 | [5 empty] | 11 KV Line and LT Line Crossing
118 | 48/2 | DA+0 |  |  |  | 536997.505 | 3564659.066 | 118 | 50A/4 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 249.269 |  | 537003.518 | 3564628.92
|  |  | 414.162 | [15 empty] | 397
119 | 48/3 | DA+3 |  |  |  | 537025.224 | 3564245.832 | 119 | 50A/5 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 249.986 |  | 537029.522 | 3564232.773
|  |  | 375.848 | [15 empty] | 337 | [5 empty] | 11 KV Line and LT Line Crossing
120 | 48/4 | DA+3 |  |  |  | 537050.379 | 3563870.827 | 120 | 50A/6 | DA+3 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 249.813 |  | 537051.596 | 3563896.497 | Poplar orchard
|  |  | 424.195 | [15 empty] | 451 | [5 empty] | Cart Track Crossing
121 | 48/5 | DA+3 |  |  |  | 537078.77 | 3563447.583 | 121 | 50A/7 | DA+6 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 248.975 |  | 537081.138 | 3563446.465 | Poplar orchard
|  |  | 395 | [15 empty] | 389 | [5 empty] | Cart Track,11 kv Line Crossing
122 | 48/6 | DA+3 |  |  |  | 537105.206 | 3563053.469 | 122 | 50A/8 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 248.52 |  | 537106.618 | 3563058.301
|  |  | 390 | [15 empty] | 395
123 | 48/7 | DA+0 |  |  |  | 537131.308 | 3562664.343 | 123 | 50A/9 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 248.89 |  | 537132.491 | 3562664.149 | Poplar orchard
|  |  | 390 | [15 empty] | 391 | [5 empty] | LT Line and Cart Track
124 | 48/8 | DA+0 |  |  |  | 537157.41 | 3562275.218 | 124 | 50A/10 | DA+0 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  |  | 248.37 |  | 537158.102 | 3562273.989 | Poplar orchard
|  |  | 427.175 | [15 empty] | 425.903 | [5 empty] | Water Pipe Line and Cart Track Crossing
125 | AP 49/0 | DC+9 |  | 3607.175 | 17° 34' 31"LT | 537186 | 3561849 | 125 | AP 51/0 | DC+9 | Raised Chimney LEG A: 0; Raised Chimney LEG B: 0; Raised Chimney LEG C: 0; Raised Chimney LEG D: 0 |  | 4450.903 | 246.843 |  | 537186 | 3561849
126 | AP-53/0 | DC+0 |  | 420.525 | 29°11'18" | 537906.361 | 3560968.449 | 126 | AP-53/0 | DC+0 | [9 empty] | 416.658 | 250.021 | Tentative | 537906.361 | 3560968.449
|  |  | 420.525 | [15 empty] | 416.658 | [5 empty] | 2 nos cat track,11 kv line
127 | AP-54/0 | DC+6 |  | 394.271 | 15°14'19" | 538072.032 | 3560581.933 | 127 | AP-54/0 | DC+6 | [9 empty] | 389.277 | 248.53 | 15°23'8" RT | 538071.474 | 3560585.903
|  |  | 394.271 | [15 empty] | 389.277 | [5 empty] | Pamp house,solar pamp,bore,2 nos 11 kv line
128 | AP-55/0 | DD+3 |  | 786.42 | 38°43'29" | 538126.65 | 3560191.464 | 128 | AP-55/0 | DD+3 | [9 empty] | 793.451 | 248.266 | 38°18'51"RT | 538125.383 | 3560200.377
|  |  | 377.114 | [15 empty] | 384.151 | [5 empty] | Cart Track,11 Kv Line,LT Line
129 | 55/1 | DA+3 |  |  |  | 537933.767 | 3559867.41 | 129 | 55/1 | DA+6 | [10 empty] | 247.77 |  | 537931.255 | 3559868.886
|  |  | 409.306 | [15 empty] | 409.3 | [5 empty] | Nala,POPULAR TREE
130 | AP-56/0 | DC+0 |  |  | 25°29'30" | 537724.418 | 3559515.693 | 130 | AP-56/0 | DC+3 | [10 empty] | 247.416 | 25°53'58" RT | 537724.418 | 3559515.693
|  |  | 409.72 | 1906.102 | [14 empty] | 409.72 | 1906.102 |  |  |  |  | Pamp POPULAR TREE
131 | 56/1 | DA+3 |  |  |  | 537383.735 | 3559288.086 | 131 | 56/1 | DA+6 | [10 empty] | 247.164 |  | 537383.735 | 3559288.085
|  |  | 406.732 | [15 empty] | 406.732 | [5 empty] | Peach Road,Nala POPULAR TREE
132 | 56/2 | DA+3 |  |  |  | 537045.536 | 3559062.138 | 132 | 56/2 | DA+3 | [10 empty] | 246.603 |  | 537045.536 | 3559062.138
|  |  | 389.913 | [15 empty] | 404.913 | [5 empty] | Nala
133 | 56/3 | DA+3 |  |  |  | 536721.322 | 3558845.534 | 133 | 56/3 | DA+6 | [10 empty] | 246.5 |  | 536708.849 | 3558837.201
|  |  | 325.563 | [15 empty] | 285.563 | [5 empty] | 11 Kv Line
134 | 56/4 | DA+6 |  |  |  | 536450.615 | 3558664.677 | 134 | 56/4 | DA+6 | [10 empty] | 247.63 |  | 536471.402 | 3558678.565
|  |  | 374.174 | [15 empty] | 399.174 | [5 empty] | Peach Road,3 NOS 11 KV Line,Crt Track
135 | AP-57/0 | DD+6 |  | 982.372 | 39°39'48" | 536139.488 | 3558456.816 | 135 | AP-57/0 | DD+3 | [9 empty] | 982.372 | 247.141 | 39°39'48" LT | 536139.488 | 3558456.816
|  |  | 343.784 | [15 empty] | 343.784 | [5 empty] | 2 nos Pamp House,2nos 11 Kv Line,Peach Road ,Cart Track
136 | 57/1 | DA+0 |  |  |  | 536041.329 | 3558127.343 | 136 | 57/1 | DA+0 | [10 empty] | 246.804 |  | 536041.329 | 3558127.343
|  |  | 313.063 | [15 empty] | 313.063 | [5 empty] | 2 nos 11 Kv Line, Cart Track,Pamp House
137 | 57/2 | DA+0 |  |  |  | 535951.942 | 3557827.313 | 137 | 57/2 | DA+0 | [10 empty] | 246.653 |  | 535951.941 | 3557827.313
|  |  | 325.525 | [15 empty] | 325.525 | [5 empty] | Pamp House,11 Kv Line
138 | AP-58/0 | DD+0 |  | 406.443 | 24°19'0" | 535858.996 | 3557515.339 | 138 | AP-58/0 | DC+0 | [9 empty] | 406.443 | 246.504 | 24°19'0"RT | 535858.996 | 3557515.339
|  |  | 406.443 | [15 empty] | 406.443 | [5 empty] | 2 nos 11 KV Line,Peach Road,
139 | AP-59/0 | DD+6 |  |  | 47°9'41" | 535592.844 | 3557208.16 | 139 | AP-59/0 | DD+6 | [10 empty] | 245.264 | 47°9'41"LT | 535592.844 | 3557208.16
|  |  | 393.08 | 788.039 | [14 empty] | 423.081 | 788.039 |  |  |  |  | 11 KV Line,Nala
140 | 59/1 | DA+6 |  |  |  | 535635.668 | 3556817.419 | 140 | 59/1 | DA+3 | [10 empty] | 245.759 |  | 535638.936 | 3556787.597
|  |  | 394.959 | [15 empty] | 364.958 | [5 empty] | 3 nos 11 KV Line,2 nos Peach Road
141 | AP-60/0 | DB+6 |  | 757.575 | 8°29'30" | 535678.696 | 3556424.811 | 141 | AP-60/0 | DB+6 | [9 empty] | 757.575 | 245.819 | 8°29'30"LT | 535678.696 | 3556424.811
|  |  | 380.949 | [15 empty] | 380.949 | [5 empty] | 11 KV Line
142 | 60/1 | DA+0 |  |  | 21°46'8" | 535775.661 | 3556056.409 | 142 | 60/1 | DA+0 | [10 empty] | 245.478 |  | 535775.661 | 3556056.409
|  |  | 376.626 | [15 empty] | 376.626 | [5 empty] | 11 KV Line ,Cart Track
143 | AP-61/0 | DC+0 |  | 547.975 | 21°46'8" | 535871.525 | 3555692.188 | 143 | AP-61/0 | DC+0 | [9 empty] | 563.919 | 245.252 | 21°54'40" RT | 535871.525 | 3555692.188
|  |  | 299.109 | [15 empty] | 299.077 | [5 empty] | 11 KV Line
144 | 61/1 | DA+0 |  |  |  | 535834.954 | 3555395.323 | 144 | 61/1 | DA+0 | [10 empty] | 245.05 |  | 535834.222 | 3555395.446
|  |  | 248.866 | [15 empty] | 264.842 | [5 empty] | Road,3 nos 11KVLine
145 | AP-62/0 | DB+0 |  | 1097.236 | 5°0'50" | 535804.525 | 3555148.324 | 145 | AP-62/0 | DB+0 | [9 empty] | 1081.233 | 244.83 | 4°52'29" RT | 535801.188 | 3555132.673
|  |  | 380.068 | [15 empty] | 364.064 | [5 empty] | Pamp House
146 | 62/1 | DA+0 |  |  |  | 535725.265 | 3554776.613 | 146 | 62/1 | DA+0 | [10 empty] | 244.347 |  | 535725.265 | 3554776.613
|  |  | 319.184 | [15 empty] | 319.184 | [5 empty] | 11 KV Line
147 | 62/2 | DA+0 |  |  |  | 535658.701 | 3554464.447 | 147 | 62/2 | DA+0 | [10 empty] | 244.154 |  | 535658.701 | 3554464.447
|  |  | 397.984 | [15 empty] | 397.985 | [5 empty] | 11 KV Line,Cart Track
148 | AP-63/0 | DB+9 |  | 450.859 | 12°25'24" | 535575.704 | 3554075.213 | 148 | AP-63/0 | DB+9 | [9 empty] | 450.859 | 244.074 | 12°25'23"LT | 535575.704 | 3554075.213
|  |  | 450.859 | [15 empty] | 450.859 | [5 empty] | 3 nos 11KV Line,Pamp House,CartTrack
149 | AP-64/0 | DC+9 |  |  | 17°10'17" | 535578.743 | 3553624.364 | 149 | AP-64/0 | DC+9 | [10 empty] | 243.572 | 17°10'17" RT | 535578.743 | 3553624.364
|  |  | 326.478 | 602.841 | [14 empty] | 326.477 | 602.84
150 | 64/1 | DA+0 |  |  |  | 535484.461 | 3553311.796 | 150 | 64/1 | DA+0 | [10 empty] | 243.963 |  | 535484.461 | 3553311.797
|  |  | 276.363 | [15 empty] | 276.363 | [5 empty] | Road,Cart Track, 11 KV Line, Peach Road
151 | AP-65/0 | DB+0 |  |  | 12°37'37" | 535404.652 | 3553047.208 | 151 | AP-65/0 | DB+0 | [10 empty] | 243.196 | 12°37'37" RT | 535404.652 | 3553047.208
|  |  | 307.216 | 2228.492 | [14 empty] | 307.216 | 2228.492 |  |  |  |  | Nala
152 | 65/1 | DA+0 |  |  |  | 535253.782 | 3552779.589 | 152 | 65/1 | DA+0 | [10 empty] | 243.218 |  | 535253.782 | 3552779.589
|  |  | 389.397 | [15 empty] | 389.397 | [5 empty] | 2 nos 11 KV Line
153 | 65/2 | DA+6 |  |  |  | 535062.553 | 3552440.381 | 153 | 65/2 | DA+6 | [10 empty] | 242.836 |  | 535062.554 | 3552440.382
|  |  | 368.792 | [15 empty] | 368.792 | [5 empty] | Cart Track ,Peach Road.
154 | 65/3 | DA+0 |  |  |  | 534881.444 | 3552119.123 | 154 | 65/3 | DA+0 | [10 empty] | 242.408 |  | 534881.444 | 3552119.123
|  |  | 404.386 | [15 empty] | 404.386
155 | 65/4 | DA+3 |  |  |  | 534682.855 | 3551766.858 | 155 | 65/4 | DA+3 | [10 empty] | 242.131 |  | 534682.855 | 3551766.858
|  |  | 378.135 | [15 empty] | 378.135 | [5 empty] | Cart Tarck, 2nos 11 KV Line
156 | 65/5 | DA+3 |  |  |  | 534497.158 | 3551437.461 | 156 | 65/5 | DA+3 | [10 empty] | 241.837 |  | 534497.158 | 3551437.461
|  |  | 380.566 | [15 empty] | 380.566 | [5 empty] | Peach Road,2 nos 11 KV Line
157 | 66/0 | DC+0 |  |  | 27°53'14" | 534310.267 | 3551105.946 | 157 | 66/0 | DC+0 | [10 empty] | 241.546 | Tentative | 534310.267 | 3551105.946
158 | AP 70 | DC+3 |  | 1599.782 | 28°13'44"RT | 533703.461 | 3547814.252 | 158 | AP 70 | DC+3 | [9 empty] | 1598.955 | 242.922 | Tentative | 533703.461 | 3547814.252
|  |  | 381.554 | [15 empty] | 435.863 | [5 empty] | 11kv Line
159 | 70/1 | DA+0 |  |  |  | 533491.278 | 3547497.137 | 159 | 70/1 | DA+9 | [10 empty] | 242.715 |  | 533459.001 | 3547453.398
|  |  | 392.701 | [15 empty] | 338.945
160 | 70/2 | DA+0 |  |  |  | 533272.897 | 3547170.758 | 160 | 70/2 | DA+0 | [10 empty] | 242.635 |  | 533268.899 | 3547172.783
|  |  | 414.335 | [15 empty] | 497.836 | [5 empty] | Peach Road,11kv Line nos.2 ,Cut Track
161 | 70/3 | DA+3 |  |  |  | 533042.484 | 3546826.398 | 161 | 70/3 | DD+18 | Raised Chimney LEG A: 2; Raised Chimney LEG B: 2; Raised Chimney LEG C: 2; Raised Chimney LEG D: 2 |  |  | 242.408 | 2°59'27"LT | 532989.68 | 3546760.621
|  |  | 411.192 | [15 empty] | 326.311 | [5 empty] | Cut Track,11kv Line nos.3,132kv Line,Peach Road
162 | AP 71 | DC+0 |  |  | 20°21'35"LT | 532813.82 | 3546484.65 | 162 | AP 71 | DC+9 | [9 empty] | 1666.222 | 242.52 | 17°25'49"LT | 532821.009 | 3546481.284
|  |  | 416.863 | 1667.808 | [14 empty] | 415.29 | [5 empty] | 11kv Line nos.2
163 | 71/1 | DA+3 |  |  |  | 532717.021 | 3546079.182 | 163 | 71/1 | DA+3 | [10 empty] | 242.914 |  | 532722.691 | 3546077.8
|  |  | 422.426 | [15 empty] | 422.422 | [5 empty] | RCC Road,11kv Line
164 | 71/2 | DA+6 |  |  |  | 532618.93 | 3545668.302 | 164 | 71/2 | DA+6 | [10 empty] | 243.716 |  | 532622.685 | 3545667.387
|  |  | 418.378 | [15 empty] | 418.373 | [5 empty] | Peach Road,11kv Line nos.2 ,LT Line,Pump House
165 | 71/3 | DA+6 |  |  |  | 532521.779 | 3545261.36 | 165 | 71/3 | DA+6 | [10 empty] | 243.867 |  | 532523.638 | 3545260.907
|  |  | 410.141 | [15 empty] | 410.137 | [5 empty] | Cut Track,Nala,Peach Road,Pump House nos.2,11kv Line
166 | AP 72 | DB+0 |  |  | 2°47'40"LT | 532426.54 | 3544862.43 | 166 | AP 72 | DB+0 | Raised Chimney LEG A: 1.5; Raised Chimney LEG B: 1.5; Raised Chimney LEG C: 1.5; Raised Chimney LEG D: 1.5 |  | 809.571 | 244.921 | 1°9'23"LT | 532426.54 | 3544862.43
|  |  | 422.698 | 820.509 | [14 empty] | 422.214 | [5 empty] | 11Kkv Line nos.2, Cut Track
167 | 72/1 | DA+3 |  |  |  | 532348.546 | 3544446.99 | 167 | 72/1 | DA+3 | [10 empty] | 243.634 |  | 532334.883 | 3544450.284
|  |  | 397.811 | [15 empty] | 387.357 | [5 empty] | Cut Track,11kv Live
168 | AP 73 | DB+6 |  | 397.142 | 5°50'37"RT | 532275.144 | 3544056.01 | 168 | AP 73 | DA+6 | [9 empty] | 406.688 | 244.201 |  | 532250.793 | 3544072.165
|  |  | 397.142 | [15 empty] | 406.688 | [5 empty] | 11kv Line, Cut Track
169 | AP 74 | DC+0 |  |  | 20°42'17"LT | 532162.507 | 3543675.176 | 169 | AP 74 | DB+0 | [10 empty] | 243.493 | 12°51'60"LT | 532162.507 | 3543675.176
|  |  | 305.026 | 305.026 | [14 empty] | 316.253 | 316.253 |  |  |  |  | LT Line,11kv Line nos.2,Pump House,Peach Road
170 | AP 75 | DD+18 |  | 259.883 | 1°18'37"LT | 532184.997 | 3543370.98 | 170 | AP 75 | DD+9 | [10 empty] | 243.53 | 3°17'24"LT | 532164.321 | 3543358.928
|  |  | 259.883 | [15 empty] | 248.423 | 248.423 |  |  |  |  | NH Road,11kv Line,66 kv line
171 | AP 76 | DD+18 |  |  | 12°20'42"LT | 532210.08 | 3543112.31 | 171 | AP 76 | DD+9 | [9 empty] | 1681.454 | 243.28 | 15°15'15"LT | 532180 | 3543111
|  |  | 458.101 | 1673.212 | [14 empty] | 427.328 | [5 empty] | Nala
172 | 76/1 | DA+0 |  |  |  | 532350.754 | 3542676.343 | 172 | 76/1 | DA+0 | [10 empty] | 243.937 |  | 532318.226 | 3542706.646
|  |  | 381.451 | [15 empty] | 413.234 | [5 empty] | Cart track, 11 kv line
173 | 76/2 | DA+0 |  |  |  | 532467.891 | 3542313.322 | 173 | 76/2 | DA+3 | [10 empty] | 244.927 |  | 532451.893 | 3542315.627
|  |  | 407.013 | [15 empty] | 414.719
174 | 76/3 | DA+3 |  |  |  | 532592.877 | 3541925.975 | 174 | 76/3 | DA+3 | [10 empty] | 246.9 |  | 532586.041 | 3541923.204
|  |  | 426.647 | [15 empty] | 426.173 | [5 empty] | 2 nos 11 kv line,
175 | AP 77 | DB+3 |  |  | 5°27'44"LT | 532723.893 | 3541519.942 | 175 | AP 77 | DB+3 | [10 empty] | 247.023 | 4°28'22"LT | 532723.893 | 3541519.942
|  |  | 404.809 | 1630.397 | [14 empty] | 404.809 | 1630.396 |  |  |  |  | 2 nos Pamp house,3 nos 11 kv line ,Peach Road
176 | 77/1 | DA+0 |  |  |  | 532884.309 | 3541148.274 | 176 | 77/1 | DA+0 | [10 empty] | 247.026 |  | 532884.309 | 3541148.274
|  |  | 392.738 | [15 empty] | 392.738 | [5 empty] | 11 Kv Line .LT Line,Pamp house
177 | 77/2 | DA+0 |  |  |  | 533039.942 | 3540787.689 | 177 | 77/2 | DA+0 | [10 empty] | 247.048 |  | 533039.942 | 3540787.689
|  |  | 391.939 | [15 empty] | 391.939 | [5 empty] | 2 nos 11 kv line,Peach Road
178 | 77/3 | DA+0 |  |  |  | 533195.258 | 3540427.838 | 178 | 77/3 | DA+0 | [10 empty] | 247.309 |  | 533195.259 | 3540427.837
|  |  | 440.911 | [15 empty] | 440.91
179 | AP 78 | DD+18 |  |  | 3°32'31"RT | 533369.981 | 3540023.024 | 179 | AP 78 | DD+18 | [10 empty] | 248.954 | 2°8'23"RT | 533369.981 | 3540023.024 | bar: Raised Chimney LEG A to Raised Chimney LEG D
|  |  | 186.014 | 186.014 | [14 empty] | 320.743 | 320.7425 |  |  |  |  | 132 KV Line Crossing,2nos 11kv line,Peach Road
180 | AP 79 | DD+9 |  |  | 21°37'48"LT | 533433.003 | 3539848.011 | 180 | AP 79 | DD+9 | [10 empty] | 250.76 | 31°24'00"LT | 533486 | 3539724
|  |  | 372.46 | 372.46 | [14 empty] | 242.225 | 242.225 |  |  |  |  | NH Crossing,2 nos 11 kv line,Cart Track
181 | AP 80 | DD+0 |  |  | 37°14'10"RT | 533679.48 | 3539568.77 | 181 | AP 80 | DD+0 | [9 empty] | 839.249 | 253.15 | 50°30'34"RT | 533678.443 | 3539576.899
|  |  | 378.292 | 378.292 | [14 empty] | 380.988 | [5 empty] | 2 nos 11 kv line,Cart Track,Peach Road,Nala
182 | 80/1 | DA+0 |  | 703.042 |  | 533707.17 | 3539191.493 | 182 | 80/1 | DA+0 | [10 empty] | 252.871 |  | 533692.382 | 3539196.166
|  |  | 455.595 | [15 empty] | 458.261
183 | AP 81 | DD+9 |  |  | 34°8'5"LT | 533740.519 | 3538737.12 | 183 | AP 81 | DD+9 | [10 empty] | 252.385 | 45°20'20"LT | 533709.148 | 3538738.212
|  |  | 247.447 | [15 empty] | 242.663 | 242.663 |  |  |  |  | Raliway Crossing,2 nos Cart Track,Peach Road,Pamp House,DP
184 | AP 82 | DD+9 |  |  | 27°45'23"RT | 533893.991 | 3538543.016 | 184 | AP 82 | DD+3 | [9 empty] | 1149.152 | 252.473 | 36°50'39"RT | 533887.874 | 3538574.071
|  |  | 376.607 | 1117.502 | [14 empty] | 408.258 | [5 empty] | Cart Track
185 | 82/1 | DA+0 |  |  |  | 533963.113 | 3538172.807 | 185 | 82/1 | DA+0 | [10 empty] | 252.708 |  | 533962.914 | 3538172.769
|  |  | 342.477 | [15 empty] | 342.476 | [5 empty] | Peach Road,11Kv Line
186 | 82/2 | DA+0 |  |  |  | 534025.97 | 3537836.148 | 186 | 82/2 | DA+0 | [10 empty] | 252.365 |  | 534025.863 | 3537836.128
|  |  | 398.418 | [15 empty] | 398.418
187 | AP 83 | DD+18 |  |  | 0°35'33"LT | 534099.095 | 3537444.498 | 187 | AP 83 | DD+18 | [10 empty] | 251.542 | 0°34'37"LT | 534099.095 | 3537444.498
|  |  | 251.516 | 251.516 | [14 empty] | 251.516 | 251.516 |  |  |  |  | 220 KV Line Crossing,11KV Line
188 | AP 84 | DD+18 |  |  | 2°42'43"RT | 534147.812 | 3537197.745 | 188 | AP 84 | DD+18 | [10 empty] | 251.394 | 3°10'24"RT | 534147.812 | 3537197.745
|  |  | 430.213 | 430.213 | [14 empty] | 445.126 | 445.126 |  |  |  |  | Upper Bari Doad Canal,Cart Tarck,11 Kv Line
189 | AP 85 | DB+0 |  |  | 2°42'42"RT | 534211.08 | 3536772.21 | 189 | AP 85 | DB+0 | [10 empty] | 248.76 | 1°42'24"RT | 534209.724 | 3536756.945
|  |  | 413.168 | 834.258 | [14 empty] | 418.777 | 838.553 |  |  |  |  | Village Road ,11 Kv Line ,2 Nos Pump House
190 | 85/1 | DA+6 |  |  |  | 534252.374 | 3536361.111 | 190 | 85/1 | DA+6 | [10 empty] | 249.171 |  | 534255.595 | 3536340.689
|  |  | 421.09 | [15 empty] | 419.776 | [5 empty] | Cart Tarck,Village Road
191 | AP 86 | DC+0 |  | 835.173 | 15°06'21"LT | 534294.46 | 3535942.13 | 191 | AP 86 | DC+0 | [9 empty] | 836.764 | 248.58 | 14°18'25"LT | 534301.576 | 3535923.439
|  |  | 400.632 | [15 empty] | 404.589 | [5 empty] | Nala,Village Road,11 Kv Line,LT Line
192 | 86/1 | DA+3 |  |  |  | 534437.001 | 3535567.712 | 192 | 86/1 | DA+3 | [10 empty] | 247.868 |  | 534443.898 | 3535544.708
|  |  | 434.541 | [15 empty] | 432.175 | [5 empty] | 11 Kv Line,LT Line,Village Road
193 | AP 87 | DB+9 |  |  | 9°27'32"RT | 534591.606 | 3535161.605 | 193 | AP 87 | DB+9 | [10 empty] | 247.573 | 8°55'19"RT | 534595.924 | 3535140.155
|  |  | 384.782 | 1209.716 | [14 empty] | 383.249 | 1185.42 |  |  |  |  | 11 Kv Line,Nala
194 | 87/1 | DA+3 |  |  |  | 534667.548 | 3534784.392 | 194 | 87/1 | DA+3 | [10 empty] | 259.11 |  | 534673.47 | 3534764.833
|  |  | 376.645 | [15 empty] | 382.084 | [5 empty] | 11 Kv Line ,2 Nos Pump House
195 | 87/2 | DA+3 |  |  |  | 534741.884 | 3534415.155 | 195 | 87/2 | DA+3 | [10 empty] | 259.087 |  | 534750.78 | 3534390.652
|  |  | 448.289 | [15 empty] | 420.087 | [5 empty] | 11 Kv Line,Village Road
196 | AP 88 | DD+18 |  |  | 31°55'40"LT | 534830.36 | 3533975.684 | 196 | AP 88 | DD+18 | [10 empty] | 259.185 | 29°54'06"LT | 534835.779 | 3533979.254
|  |  | 212.085 | 212.085 | [14 empty] | 211.063 | 211.063 |  |  |  |  | 220 kv Line Crossing ,3 nos11 kv Line
197 | AP 89 | DD+18 |  |  | 34°27'36"RT | 534975.841 | 3533821.361 | 197 | AP 89 | DD+18 | [10 empty] | 259.192 | 31°35'10"RT | 534975.841 | 3533821.361 | 11 kv line shifting
|  |  | 384.985 | 604.231 | [14 empty] | 385.103 | 618.229 |  |  |  |  | Cart Tarck,Village Road,11 kv Line,Bore
198 | 89/1 | DA+3 |  |  |  | 535035.073 | 3533440.96 | 198 | 89/1 | DA+3 | [10 empty] | 259.195 |  | 535042.642 | 3533442.096
|  |  | 219.246 | [15 empty] | 233.126 | [5 empty] | 2 Nos 11 Kv Line,LT Line,Village Road
199 | AP 90 | DD+0 |  |  | 41°31'33"LT | 535068.805 | 3533224.324 | 199 | AP 90 | DD+0 | [10 empty] | 259.264 | 40°23'13"LT | 535083.08 | 3533212.504
|  |  | 389.651 | 1199.544 | [14 empty] | 401.232 | 1181.01 |  |  |  |  | 3 Nos 11 Kv Line,Village Road
200 | 90/1 | DA+3 |  |  |  | 535368.932 | 3532975.826 | 200 | 90/1 | DA+3 | [10 empty] | 259.921 |  | 535392.127 | 3532956.62
|  |  | 367.11 | [15 empty] | 342.999 | [5 empty] | 11 Kv Line
201 | 90/2 | DA+0 |  |  |  | 535651.697 | 3532741.703 | 201 | 90/2 | DA+0 | [10 empty] | 260.325 |  | 535656.321 | 3532737.873
|  |  | 442.783 | [15 empty] | 436.779 | [5 empty] | 2 Nos 11 Kv Line,LT Line,Village Road
202 | AP 91 | DD+18 |  |  | 7°0'57"RT | 535992.749 | 3532459.319 | 202 | AP 91 | DD+25 | [10 empty] | 260.559 | 11°45'19"RT | 535992.749 | 3532459.319
|  |  | 242.124 | 242.124 | [14 empty] | 247.685 | 247.685 |  |  |  |  | 220 kv Line Crossing ,11 kv Line,Village Road,Nala
203 | AP 92 | DD+18 |  |  | 39°23'4"RT | 536158.986 | 3532283.282 | 203 | AP 92 | DD+18 | [10 empty] | 260.692 | 34°8'24"RT | 536147.344 | 3532265.804
|  |  | 377.468 | 1471.729 | [14 empty] | 360.878 | 1455.156 |  |  |  |  | 11 Kv Line
204 | 92/1 | DA+3 |  |  |  | 536185.157 | 3531906.723 | 204 | 92/1 | DA+3 | [10 empty] | 260.876 |  | 536175.537 | 3531906.029
|  |  | 415.652 | [15 empty] | 415.643 | [5 empty] | 2 Nos 11 Kv Line,Cart Track
205 | 92/2 | DA+6 |  |  |  | 536213.976 | 3531492.071 | 205 | 92/2 | DA+6 | [10 empty] | 259.988 |  | 536208.008 | 3531491.659
|  |  | 378.397 | [15 empty] | 379.751 | [5 empty] | Village Road
206 | 92/3 | DA+0 |  |  |  | 536240.211 | 3531114.584 | 206 | 92/3 | DA+0 | [10 empty] | 259.393 |  | 536237.676 | 3531113.066
|  |  | 300.212 | [15 empty] | 298.884 | [5 empty] | 11 Kv Line
207 | AP 93 | DC+0 |  | 889.075 | 18°10'19"RT | 536261.026 | 3530815.095 | 207 | AP 93 | DC+0 | [9 empty] | 889.075 | 259.567 | 18°40'38"RT | 536261.026 | 3530815.095
|  |  | 314.663 | [15 empty] | 314.664 | [5 empty] | Village Road,11 Kv Line
208 | 93/1 | DA+0 |  |  |  | 536183.855 | 3530510.041 | 208 | 93/1 | DA+0 | [10 empty] | 260.007 |  | 536183.855 | 3530510.041
|  |  | 301.757 | [15 empty] | 301.757 | [5 empty] | 2 Nos 11 Kv Line,Village Road
209 | 93/2 | DA+0 |  |  |  | 536109.85 | 3530217.5 | 209 | 93/2 | DA+0 | [10 empty] | 259.339 |  | 536109.85 | 3530217.499
|  |  | 272.655 | [15 empty] | 272.654
210 | AP 94 | DB+0 |  |  | 0°29'53"RT | 536042.983 | 3529953.172 | 210 | A[P 94 | DB+0 | [10 empty] | 259.192 | 0°29'54"RT | 536042.983 | 3529953.172
|  |  | 411.542 | 411.542 | [14 empty] | 411.542 | 411.542 |  |  |  |  | Road
211 | AP 95 | DC+3 |  |  | 19°44'6"LT | 535938.588 | 3529555.091 | 211 | AP 95 | DC+3 | [10 empty] | 258.815 | 19°44'6"LT | 535938.588 | 3529555.091
|  |  | 375.053 | 1751.018 | [14 empty] | 375.054 | 1751.019 |  |  |  |  | 11kv Line,Pump House
212 | 95/1 | DA+0 |  |  |  | 535971.537 | 3529181.488 | 212 | 95/1 | DA+0 | [10 empty] | 258.941 |  | 535971.537 | 3529181.487
|  |  | 357.801 | [15 empty] | 357.801 | [5 empty] | Pump House,Cart track,11kv D.P
213 | 95/2 | DA+0 |  |  |  | 536002.972 | 3528825.07 | 213 | 95/2 | DA+0 | [10 empty] | 258.584 |  | 536002.972 | 3528825.07
|  |  | 338.209 | [15 empty] | 338.209 | [5 empty] | 11kv Line
214 | 95/3 | DA+0 |  |  |  | 536032.685 | 3528488.169 | 214 | 95/3 | DA+0 | [10 empty] | 258.516 |  | 536032.685 | 3528488.169
|  |  | 358.793 | [15 empty] | 358.793 | [5 empty] | 11KV LINE,Cart Track
215 | 95/4 | DA+0 |  |  |  | 536064.206 | 3528130.763 | 215 | 95/4 | DA+0 | [10 empty] | 259.278 |  | 536064.206 | 3528130.763
|  |  | 321.162 | [15 empty] | 321.162 | [5 empty] | LT LINE, 11KV LINE,Pump House
216 | AP 96 | DC+0 |  |  | 21°39'3"LT | 536092.421 | 3527810.843 | 216 | AP 96 | DC+0 | [10 empty] | 258.704 | 21°39'3"LT | 536092.421 | 3527810.843
217 | AP 115/0 | DB+0 |  | 751.41 | 10°13'52"LT | 537339.014 | 3519225.887 | 217 | AP 115/0 | DB+0 | [9 empty] | 751.411 | 255.816 | 10°13'52"LT | 537339.014 | 3519225.887
|  |  | 373.378 | [15 empty] | 373.379 | [5 empty] | CT ROAD,LT LINE,RCC DRAIN,ROAD,LT LINE 11kV
218 | 115/1 | DA+6 |  |  |  | 537297.253 | 3518854.852 | 218 | 115/1 | DA+6 | [10 empty] | 255.913 |  | 537297.253 | 3518854.852
|  |  | 378.003 | [15 empty] | 378.032 | [5 empty] | 66kV
219 | AP 116/0 | DB+0 |  | 515.47 | 4°18'31"LT | 537254.972 | 3518479.191 | 219 | AP 116/0 | DB+0 | [9 empty] | 515.469 | 255.826 | 4°18'31"LT | 537254.972 | 3518479.191
|  |  | 283.156 | [15 empty] | 283.157 | [5 empty] | CANEL,ROAD,11 Kv
220 | 116/1 | DA+0 |  |  |  | 537244.531 | 3518196.227 | 220 | 116/1 | DC+0 | [10 empty] | 254.81 |  | 537244.531 | 3518196.227 | 2nd Transposition Tower
|  |  | 232.312 | [15 empty] | 232.312
221 | AP 117/0 | DB+0 |  |  | 6°09'51"RT | 537235.965 | 3517964.073 | 221 | AP 117/0 | DB+0 | [10 empty] | 254.461 | 6°09'51"RT | 537235.965 | 3517964.073
|  |  | 323.186 | 1409.68 | [14 empty] | 323.186 | 1409.681 |  |  |  |  | 11kV,S.H,LT LINE
222 | 117/1 | DA+0 |  |  |  | 537189.438 | 3517644.254 | 222 | 117/1 | DA+0 | [10 empty] | 254.091 |  | 537189.438 | 3517644.254
|  |  | 351.475 | [15 empty] | 351.475 | [5 empty] | 11kV,ROAD,11kV
223 | 117/2 | DA+3 |  |  |  | 537138.839 | 3517296.44 | 223 | 117/2 | DA+3 | [10 empty] | 253.624 |  | 537138.839 | 3517296.44
|  |  | 368.874 | [15 empty] | 368.874 | [5 empty] | LT LINE
224 | 117/3 | DA+0 |  |  |  | 537085.734 | 3516931.409 | 224 | 117/3 | DA+0 | [10 empty] | 252.684 |  | 537085.734 | 3516931.409
|  |  | 366.147 | [15 empty] | 366.146 | [5 empty] | ROAD,LT LINE,11kV,11kV
225 | AP 118/0 | DC+0 |  | 634.36 | 16°09'46"LT | 537033.022 | 3516569.076 | 225 | AP 118/0 | DC+0 | [9 empty] | 634.359 | 252.402 | 16°09'46"LT | 537033.022 | 3516569.076
|  |  | 326.21 | [15 empty] | 326.211 | [5 empty] | LT LINE,ROAD
226 | 118/1 | DA+0 |  |  |  | 537077.777 | 3516245.951 | 226 | 118/1 | DA+0 | [10 empty] | 253.281 |  | 537077.777 | 3516245.951
|  |  | 308.149 | [15 empty] | 308.148 | [5 empty] | LT.LINE,LT LINE,LT LINE
227 | AP 119/0 | DC+0 |  | 518.18 | 26°16'41"LT | 537120.054 | 3515940.716 | 227 | AP 119/0 | DC+0 | [9 empty] | 518.175 | 253.51 | 26°16'41"LT | 537120.054 | 3515940.716
|  |  | 285.935 | [15 empty] | 285.936 | [5 empty] | 11kV,11kV
228 | 119/1 | DA+0 |  |  |  | 537280.623 | 3515704.123 | 228 | 119/1 | DA+0 | [10 empty] | 253.748 |  | 537280.623 | 3515704.123
|  |  | 232.24 | [15 empty] | 232.239 | [5 empty] | ROAD, LT LINE ,LT LINE
229 | AP 120/0 | DD+0 |  | 1212.37 | 42°02'04"RT | 537411.04 | 3515511.959 | 229 | AP 120/0 | DD+0 | [9 empty] | 1212.369 | 254.132 | 42°02'04"RT | 537411.04 | 3515511.959
|  |  | 396.913 | [15 empty] | 396.914 | [5 empty] | RCC NALA
230 | 120/1 | DA+3 |  |  |  | 537356.687 | 3515118.785 | 230 | 120/1 | DA+3 | [10 empty] | 253.923 |  | 537356.687 | 3515118.785
|  |  | 412.776 | [15 empty] | 412.766 | [5 empty] | LT LINE,11kV,CANEL,LT LINE,CT ROAD
231 | 120/2 | DA+6 |  |  |  | 537300.163 | 3514709.907 | 231 | 120/2 | DA+6 | [10 empty] | 253.783 |  | 537300.163 | 3514709.907
|  |  | 402.69 | [15 empty] | 402.689 | [5 empty] | ROAD,11kV TRANSFORMER
232 | AP 121/0 | DC+3 |  | 1136.05 | 20°15'43"LT | 537245.018 | 3514311.011 | 232 | AP 121/0 | DC+3 | [9 empty] | 1136.859 | 253.607 | 19°30'25"LT | 537245.018 | 3514311.011
|  |  | 373.866 | [15 empty] | 374.133 | [5 empty] | LT LINE,CT ROAD,11kV
233 | 121/1 | DA+0 |  |  |  | 537325.244 | 3513945.854 | 233 | 121/1 | DA+0 | [10 empty] | 253.477 |  | 537320.478 | 3513944.567
|  |  | 377.108 | [15 empty] | 377.376 | [5 empty] | 11kV,LT LINE,LT LINE
234 | 121/2 | DA+0 |  |  |  | 537406.164 | 3513577.53 | 234 | 121/2 | DA+0 | [10 empty] | 253.354 |  | 537396.591 | 3513574.946
|  |  | 385.076 | [15 empty] | 385.35 | [5 empty] | CT ROAD,LT LINE,11kV,11kV
235 | 122/0 | DB+0 |  | 753.4 | 2°42'37"LT | 537488.795 | 3513201.424 | 235 | AP122/0 | DB+0 | [9 empty] | 753.546 | 253.229 | 4°36'22"LT | 537474.313 | 3513197.516 | AP SHIFTED DUE TO PRESENT OF HOUSE IN BETWEEN CENTER LINE AND CORRIDOR
|  |  | 395.172 | [15 empty] | 395.25 | [5 empty] | SABRAWAN NAHER,ROAD,11kV
236 | 122/1 | DA+3 |  |  |  | 537591.748 | 3512819.899 | 236 | 122/1 | DA+3 | [10 empty] | 254.136 |  | 537584.941 | 3512817.772
|  |  | 358.225 | [15 empty] | 358.296 | [5 empty] | LT LINE,11kV,11kV
237 | 123/0 | DD+0 |  |  | 17°16'00"RT | 537685.706 | 3512474.045 | 237 | AP123/0 | DD+0 | [10 empty] | 253.947 | 18°24'26"RT | 537685.076 | 3512474.045
s
238 | AP 131/0 | DC+0 |  | 2841.987 | 22°30'33"LT | 538168.009 | 3509218.148 | 238 | AP 131/0 | DC+0 | [9 empty] | 2841.988 | 252.715 | 22°30'33"LT | 538168.009 | 3509218.148
|  |  | 407.945 | [15 empty] | 407.946 | [5 empty] | LT LINE,LT LINE
239 | 131/1 | DA+3 |  |  |  | 538287.402 | 3508828.065 | 239 | 131/1 | DA+3 | [10 empty] | 253.285 |  | 538287.402 | 3508828.065
|  |  | 429.847 | [15 empty] | 429.847 | [5 empty] | LT LINE,ROAD
240 | 131/2 | DA+3 |  |  |  | 538413.205 | 3508417.039 | 240 | 131/2 | DA+3 | [10 empty] | 252.581 |  | 538413.205 | 3508417.039
|  |  | 407.778 | [15 empty] | 407.778 | [5 empty] | LT LINE
241 | 131/3 | DA+3 |  |  |  | 538532.549 | 3508027.116 | 241 | 131/3 | DA+3 | [10 empty] | 253.641 |  | 538532.549 | 3508027.116
|  |  | 416.733 | [15 empty] | 416.733 | [5 empty] | CT ROAD,LT LINE
242 | 131/4 | DA+0 |  |  |  | 538654.513 | 3507628.63 | 242 | 131/4 | DA+0 | [10 empty] | 251.638 |  | 538654.513 | 3507628.63
|  |  | 421.345 | [15 empty] | 421.345 | [5 empty] | ROAD
243 | 131/5 | DA+3 |  |  |  | 538777.828 | 3507225.734 | 243 | 131/5 | DA+3 | [10 empty] | 250.849 |  | 538777.828 | 3507225.734
|  |  | 385.64 | [15 empty] | 385.64 | [5 empty] | 11kV,ROAD,11kV
244 | 131/6 | DA+0 |  |  |  | 538890.693 | 3506856.98 | 244 | 131/6 | DA+0 | [10 empty] | 249.36 |  | 538890.693 | 3506856.98
|  |  | 372.699 | [15 empty] | 372.699 | [5 empty] | 66kV
245 | AP 132/0 | DC+6 1.5 mrc |  |  | 28°22'39"RT | 538999.77 | 3506500.6 | 245 | AP 132/0 | DC+6 | Raised Chimney LEG A: 1.5; Raised Chimney LEG B: 1.5; Raised Chimney LEG C: 1.5; Raised Chimney LEG D: 1.5 |  |  | 250.43 | 28°22'39"RT | 538999.77 | 3506500.6
|  |  | 407.912 | 816.077 | [14 empty] | 407.912 | 816.077 |  |  |  |  | LT LINE, PUMP HOUSE,ROAD,LT LINE
246 | 132/1 | DA+3 |  |  |  | 538919.425 | 3506100.679 | 246 | 132/1 | DA+3 | [10 empty] | 250.22 |  | 538919.425 | 3506100.679
|  |  | 408.165 | [15 empty] | 408.165 | [5 empty] | 11kV
247 | AP 133/0 | DC+6 |  | 227.366 | 18°40'20"LT | 538839.029 | 3505700.51 | 247 | AP 133/0 | DD+6 | [10 empty] | 249.72 | 18°40'20"LT | 538839.029 | 3505700.51
|  |  | 227.366 | [15 empty] | 227.366 | 227.366 |  |  |  |  | CT ROAD,NALA,ROAD(SH),11kV
248 | AP 134/0 | DB+3 |  | 401.366 | 2°30'44"RT | 538867.969 | 3505474.993 | 248 | AP 134/0 | DD+3 | [10 empty] | 248.902 | 2°30'44"RT | 538867.969 | 3505474.993
|  |  | 401.366 | [15 empty] | 401.366 | 401.366 |  |  |  |  | LT LINE,11kV
249 | AP 135/0 | DB+3 |  | 1221.902 | 12°42'21"RT | 538901.556 | 3505075.035 | 249 | AP 135/0 | DB+3 | [10 empty] | 249.039 | 12°42'21"RT | 538901.556 | 3505075.035
|  |  | 403.064 | [15 empty] | 403.064 | 1221.902 |  |  |  |  | LT LINE,CT ROAD
250 | 135/1 | DA+6 |  |  |  | 538846.119 | 3504675.802 | 250 | 135/1 | DA+6 | [10 empty] | 248.761 |  | 538846.119 | 3504675.802
|  |  | 398.933 | [15 empty] | 398.933 | [5 empty] | LT LINE,11 Kv,CT ROAD,LT LINE
251 | 135/2 | DA+3 |  |  |  | 538791.249 | 3504280.66 | 251 | 135/2 | DA+3 | [10 empty] | 248.543 |  | 538791.249 | 3504280.66
|  |  | 419.905 | [15 empty] | 419.905 | [5 empty] | LT LINE, 11kV, LT LINE
252 | AP 136/0 | DC+3 |  |  | 18°07'49"LT | 538733.495 | 3503864.746 | 252 | AP 136/0 | DC+3 | [10 empty] | 248.354 | 18°07'48"LT | 538733.495 | 3503864.746
|  |  | 373.389 | 2000.393 | [14 empty] | 373.389 | 2000.393 |  |  |  |  | LT LINE, CT ROAD
253 | 136/1 | DA+3 |  |  |  | 538799.775 | 3503497.287 | 253 | 136/1 | DA+3 | [10 empty] | 248.311 |  | 538799.775 | 3503497.287
|  |  | 419.813 | [15 empty] | 419.813 | [5 empty] | LT LINE
254 | 136/2 | DA+3 |  |  |  | 538874.295 | 3503084.14 | 254 | 136/2 | DA+3 | [10 empty] | 248.224 |  | 538874.295 | 3503084.14
|  |  | 410.049 | [15 empty] | 410.049 | [5 empty] | LT LINE
255 | 136/3 | DA+0 |  |  |  | 538947.081 | 3502680.603 | 255 | 136/3 | DA+0 | [10 empty] | 248.366 |  | 538947.081 | 3502680.603
|  |  | 415.171 | [15 empty] | 415.171 | [5 empty] | ROAD,SMALL CANEL
256 | 136/4 | DA+3 |  |  |  | 539020.777 | 3502272.025 | 256 | 136/4 | DA+3 | [10 empty] | 248.901 |  | 539020.777 | 3502272.025
|  |  | 381.971 | [15 empty] | 381.971
257 | AP 137/0 | DC+3 |  | 1037.588 | 28°54'26"RT | 539088.58 | 3501896.12 | 257 | AP 137/0 | DC+3 | [10 empty] | 248.51 | 28°54'25"RT | 539088.58 | 3501896.12
|  |  | 377.623 | [15 empty] | 377.623 | 1037.587 |  |  |  |  | ROAD
258 | 137/1 | DA+0 |  |  |  | 538967.619 | 3501538.395 | 258 | 137/1 | DA+0 | [10 empty] | 248.489 |  | 538967.619 | 3501538.395
|  |  | 354.138 | [15 empty] | 354.138 | [5 empty] | 11kV
259 | 137/2 | DA+0 |  |  |  | 538854.18 | 3501202.917 | 259 | 137/2 | DA+0 | [10 empty] | 248.278 |  | 538854.18 | 3501202.917
|  |  | 305.827 | [15 empty] | 305.826 | [5 empty] | 11kV,11kV,ROAD,LT LINE,11kV,11kV
260 | AP 138/0 | DD+0 |  | 944.974 | 31°45'48"LT | 538756.216 | 3500913.205 | 260 | AP 138/0 | DD+0 | [9 empty] | 944.974 | 248.041 | 31°45'48"LT | 538756.216 | 3500913.205
|  |  | 320.986 | [15 empty] | 320.987 | [5 empty] | 11kV,11kV
261 | 138/1 | DA+0 |  |  |  | 538828.865 | 3500600.548 | 261 | 138/1 | DA+0 | [10 empty] | 248.307 |  | 538828.865 | 3500600.548
|  |  | 329.946 | [15 empty] | 329.946 | [5 empty] | CT ROAD,11kV,LT LINE,11kV
262 | 138/2 | DA+0 |  |  |  | 538903.541 | 3500279.164 | 262 | 138/2 | DA+0 | [10 empty] | 248.359 |  | 538903.541 | 3500279.164
|  |  | 294.042 | [15 empty] | 294.041 | [5 empty] | 11kV,11kV, CT ROAD,11kV
263 | AP 139/0 | DB+0 |  | 809.122 | 5°55'31"LT | 538970.092 | 3499992.752 | 263 | AP 139/0 | DB+0 | [9 empty] | 809.122 | 246.903 | 5°55'30"LT | 538970.092 | 3499992.752
|  |  | 381.668 | [15 empty] | 381.669 | [5 empty] | 11kV,SOLAR PUMP
264 | 139/1 | DA+3 |  |  |  | 539094.39 | 3499631.891 | 264 | 139/1 | DA+3 | [10 empty] | 239.424 |  | 539094.39 | 3499631.891
|  |  | 427.454 | [15 empty] | 427.453 | [5 empty] | 11kV,CT ROAD,11kV
265 | AP 140/0 | DD+18 |  |  | 29°55'22"LT | 539233.6 | 3499227.741 | 265 | AP 140/0 | DD+18 | [10 empty] | 235.973 | 29°55'22"LT | 539233.6 | 3499227.741
266 | 145/0 | DB+0 |  | 1066.883 | 13°54'60"RT | 539550.52 | 3494836.47 | 266 | 145/0 | DB+0 | [9 empty] | 1066.883 | 232.373 | 13°54'60"RT | 539550.52 | 3494836.47
|  |  | 330.492 | [15 empty] | 330.492 | [5 empty] | ROAD,11kV,LT LINE
267 | 145/1 | DA+0 |  |  |  | 539481.199 | 3494513.33 | 267 | 145/1 | DA+0 | [10 empty] | 232.053 |  | 539481.199 | 3494513.33
|  |  | 342.106 | [15 empty] | 342.106 | [5 empty] | LT LINE,11kV,LT LINE
268 | 145/2 | DA+3 |  |  |  | 539409.442 | 3494178.834 | 268 | 145/2 | DA+3 | [10 empty] | 232.074 |  | 539409.442 | 3494178.834
|  |  | 394.285 | [15 empty] | 394.285 | [5 empty] | CT ROAD,11kV,LT LINE
269 | 146/0 | DC+0 |  |  | 29°42'51"LT | 539326.74 | 3493793.32 | 269 | 146/0 | DC+0 | [10 empty] | 232.347 | 29°42'51"LT | 539326.74 | 3493793.32
|  |  | 245.679 | 245.679 | [14 empty] | 245.679 | 245.679
270 | 147/0 | DB+0 |  |  |  | 539401.052 | 3493559.149 | 270 | 147/0 | DB+0 | [10 empty] | 231.946 |  | 539401.052 | 3493559.149
|  |  | 352.93 | 352.93 | [14 empty] | 352.93 | 352.93 |  |  |  |  | LT LINE,CT ROAD,ROAD
271 | 148/0 | DD+25 |  |  | 51°9'48"RT | 539507.805 | 3493222.751 | 271 | 148/0 | DD+25 | [10 empty] | 232.344 | 51°9'48"RT | 539507.805 | 3493222.751
|  |  | 232.301 | 232.301 | [14 empty] | 232.301 | 232.301 |  |  |  |  | 400kV
272 | 149/0 | DD+25 |  |  | 22°39'7"LT | 539379.397 | 3493029.166 | 272 | 149/0 | DD+25 | [10 empty] | 232.158 | 22°39'7"LT | 539379.397 | 3493029.166
|  |  | 474.983 | 474.983 | [14 empty] | 474.983 | 474.983 |  |  |  |  | LT LINE,11kV,LT LINE
273 | 150/0 | DC+0 |  |  | 24°16'48"LT | 539289.54 | 3492562.76 | 273 | 150/0 | DC+0 | [10 empty] | 232.187 | 24°16'48"LT | 539289.54 | 3492562.76
|  |  | 322.588 | 938.207 | [14 empty] | 322.588 | 938.207 |  |  |  |  | 11kV,CT ROAD,LT LINE
274 | 150/1 | DA+0 |  |  |  | 539364.162 | 3492248.922 | 274 | 150/1 | DA+0 | [10 empty] | 231.729 |  | 539364.162 | 3492248.922
|  |  | 317.884 | [15 empty] | 317.884
275 | 150/2 | DA+0 |  |  |  | 539437.697 | 3491939.66 | 275 | 150/2 | DA+0 | [10 empty] | 232.067 |  | 539437.697 | 3491939.66
|  |  | 297.735 | [15 empty] | 297.735
276 | 151/0 | DC+0 |  |  | 24°58'4"RT | 539506.57 | 3491650 | 276 | 151/0 | DC+0 | [10 empty] | 231.965 | 24°58'4"RT | 539506.57 | 3491650
|  |  | 357.249 | 1117.048 | [14 empty] | 357.249 | 1117.048
277 | 151/1 | DA+0 |  |  |  | 539434.779 | 3491300.039 | 277 | 151/1 | DA+0 | [10 empty] | 231.645 |  | 539434.779 | 3491300.039
|  |  | 353.032 | [15 empty] | 353.032 | [5 empty] | LT LINE(6 NOS),11 Kv(4 nos),ROAD(2nos),
278 | 151/2 | DA+3 |  |  |  | 539363.835 | 3490954.209 | 278 | 151/2 | DA+3 | [10 empty] | 231.556 |  | 539363.835 | 3490954.209
|  |  | 406.767 | [15 empty] | 406.767 | [5 empty] | LT LINE,11kV
279 | 152/0 | DD+0 |  |  | 39°38'38"LT | 539282.092 | 3490555.74 | 279 | 152/0 | DD+0 | [10 empty] | 231.491 | 39°38'36"LT | 539282.092 | 3490555.74
|  |  | 392.394 | 1861.602 | [14 empty] | 392.394 | 1861.602 |  |  |  |  | 11kV,LT LINE(3nos),ROAD
280 | 152/1 | DA+3 |  |  |  | 539466.617 | 3490209.44 | 280 | 152/1 | DA+3 | [10 empty] | 231.324 |  | 539466.617 | 3490209.44
|  |  | 408.835 | [15 empty] | 408.835 | [5 empty] | LT LINE
281 | 152/2 | DA+0 |  |  |  | 538658.874 | 3489848.631 | 281 | 152/2 | DA+0 | [10 empty] | 230.851 |  | 538658.874 | 3489848.631
|  |  | 343.091 | [15 empty] | 333.091 | [5 empty] | CT ROAD,11kV(2nos)
282 | 152/3 | DA+0 |  |  |  | 539820.245 | 3489545.843 | 282 | 152/3 | DA+0 | [10 empty] | 230.407 |  | 539815.512 | 3489554.668 | DUE TO PRESENCE OF ROAD TOWER SHIFTING 10 mtr TO 152/3 | bar: Raised Chimney LEG A to Raised Chimney LEG D
|  |  | 333.683 | [15 empty] | 343.683 | [5 empty] | ROAD,LT LINE(2nos),11kv(2nos)
283 | 152/4 | DA+0 |  |  |  | 539977.131 | 3489251.357 | 283 | 152/4 | DA+0 | [10 empty] | 230.115 |  | 539977.131 | 3489251.357
|  |  | 383.599 | [15 empty] | 383.599
284 | 153/0 | DC+0 |  |  | 23°26'55"RT | 540157.52 | 3488912.82 | 284 | 153/0 | DC+0 | [10 empty] | 230.15 | 23°26'55"RT | 540157.52 | 3488912.82
81
192

## Approved CS K-S Line (hidden)
Line: 400 kV D/C Quad Kishenpur-Samba TL
Approved Check Survey Tower Schedule
AS PER DETAIL SURVEY | [7 empty] | AS PER CHECK SURVEY
Sr. No. | Tower No. | Type of Tower | Span Length (m) | Section Length (m) | Angle of Deviation | UTM Coordinates |  | Sr. No. | Tower No. | Type of Tower | Raised Chimney |  |  |  | Leg Extension |  |  |  | Span Length (m) | Section Length (m) | Reduced Level | Angle of Deviation | UTM Coordinates |  | Crossing/Remarks
[6 empty] | Easting | Northing |  |  |  | LEG A | LEG B | LEG C | LEG D | LEG A | LEG B | LEG C | LEG D |  |  |  |  | Easting | Northing
1 | AP 78/0 | DC+9 |  | 0 | 28°55'39"L | 515334.466 | 3621567.153 | 1 | AP 78/0 | DC+9 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 3 |  | 0 | 524.77 | 29°55'53"L | 515334.47 | 3621567.15
|  |  | 361.044 | [15 empty] | 340.277
2 | AP 79/0 | DD+9 |  | 361.044 | 31°39'03"R | 515034.271 | 3621767.742 | 2 | AP 79/0 | DD+9 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 340.277 | 524.982 | 30°11'47"R | 515048.273 | 3621751.214 | LT LINE TO BE SHIFTED
|  |  | 374.114 | [15 empty] | 392.251 | [5 empty] | NALLA CROSSING
3 | AP 80/0 | DD+3 |  | 735.158 | 36°56'25"L | 514878.544 | 3622107.904 | 3 | AP 80/0 | DD+3 | 0 | -1.5 | 0 | 0 | 0 | 0 | 0 | 1 |  | 732.528 | 532.688 | 30°16'26"L | 514869.848 | 3622100.535
|  |  | 148.51 | [15 empty] | 144.77
4 | AP 81/0 | DD+18 |  | 883.668 | 49°18'55"L | 514747.983 | 3622178.679 | 4 | AP 81/0 | DD+18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | 877.298 | 535.86 | 53°31'26"L | 514747.98 | 3622178.68
|  |  | 195.926 | [15 empty] | 195.926 | [5 empty] | 220 KV S/C CROSSING(KSN-SRN)
5 | AP 82/0 | DD+18 |  | 1079.594 | 5°38'12"R | 514564.892 | 3622108.932 | 5 | AP 82/0 | DD+18 | 0 | 0 | 0 | 0 | 1 | 3 | 4 | 4 |  | 1073.224 | 532.66 | 5°38'20"R | 514564.89 | 3622108.93
|  |  | 194.627 | [15 empty] | 194.623 | [5 empty] | 220 D/C CROSSING(KSN-SRN)
6 | AP 83/0 | DD+25 |  | 1274.221 | 46°40'30"R | 514377.089 | 3622057.846 | 6 | AP 83/0 | DD+25 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1267.847 | 522.13 | 46°40'25"R | 514377.09 | 3622057.85
|  |  | 123.478 | [15 empty] | 123.478
7 | AP 84/0 | DC+9 |  | 1397.699 | 26°50'39"R | 514271.759 | 3622122.285 | 7 | AP 84/0 | DC+9 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 |  | 1391.325 | 525.46 | 26°50'39"R | 514271.76 | 3622122.29 | CONTOUR NOT REQUIRED
|  |  | 358.138 | [15 empty] | 358.134
8 | AP 85/0 | DC+0 |  | 1755.837 | 18°33'39"R | 514083.577 | 3622426.999 | 8 | AP 85/0 | DC+0 | 0 | -1.5 | 0 | 1 | 0 | 0 | 0 | 0 |  | 1749.459 | 513.5 | 18°33'34"R | 514083.58 | 3622427
|  |  | 195.995 | [15 empty] | 195.99 | [5 empty] | LT LINE,2 NOS 11 KV CROSSING
9 | AP 86/0 | DD+0 |  | 1951.832 | 37°33'24"L | 514039.03 | 3622617.864 | 9 | AP 86/0 | DD+0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 |  | 1945.449 | 519.05 |  | 514039.03 | 3622617.86
[19 empty] | 402.938 | [5 empty] | Cannal,Cart Track Crossing
10 | AP 95/0 | DD+0 |  | 0 | 49° 37' 37"RT | 511950.666 | 3623917.519 | 10 | AP 95/0 | DD+0 | 0 | -1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 |  | 0 | 483.848 | 47° 47' 09"RT | 511953.99 | 3623920.015
|  |  | 216.941 | [15 empty] | 215.857 | [5 empty] | LT Line,2 NOS 11KV Line Crossing
11 | AP 96/0 | DC+0 |  | 216.941 | 23° 11' 17"RT | 511872.021 | 3624119.703 | 11 | AP 96/0 | DC-3 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | 215.857 | 480.277 | 24° 15' 00"RT | 511872.021 | 3624119.703
|  |  | 166.009 | [15 empty] | 166.009 | [5 empty] | LT Line Crossing
12 | AP 97/0 | DC+0 |  | 382.95 | 25° 05' 24"LT | 511877.62 | 3624285.618 | 12 | AP 97/0 | DC-3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 381.866 | 485.367 | 25° 09' 02"LT | 511877.62 | 3624285.618 | Contour Not Required
|  |  | 242.696 | [15 empty] | 242.696 | [5 empty] | Nalla and LT Line crossing
13 | AP 98/0 | DD+9 |  | 625.646 | 48° 10' 12"LT | 511782.169 | 3624508.756 | 13 | AP 98/0 | DD+9 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 2 |  | 624.562 | 486.733 | 48° 10' 19"LT | 511782.169 | 3624508.756
|  |  | 202.992 | [15 empty] | 202.992 | [5 empty] | 132 KV S/C Line Crossing
14 | AP 99/0 | DD+18 |  | 828.638 | 58° 23' 34"RT | 511589.857 | 3624573.732 | 14 | AP 99/0 | DD+18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 827.554 | 468.882 | 58° 23' 34"RT | 511589.857 | 3624573.732 | Contour Not Required
|  |  | 155.699 | [15 empty] | 155.699
15 | AP 100/0 | DD+9 |  | 984.337 | 45° 03' 40"RT | 511554.995 | 3624725.478 | 15 | AP 100/0 | DD+9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 983.253 | 468.116 | 45° 03' 40"RT | 511554.995 | 3624725.478
|  |  | 491.503 | [15 empty] | 491.503 | [5 empty] | Nalla and LT Line crossing
16 | AP 101/0 | DD+9 |  | 1475.84 | 34° 37' 48"LT | 511816.341 | 3625141.739 | 16 | AP 101/0 | DD+9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1474.756 | 482.052 | 34° 37' 48"LT | 511816.341 | 3625141.739 | Contour Not Required
|  |  | 136.501 | [15 empty] | 136.501
17 | AP 102/0 | DD+0 |  | 1612.341 | 49° 54' 56"LT | 511810.369 | 3625278.109 | 17 | AP 102/0 | DD+0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 1611.257 | 479.213 | 49° 54' 56"LT | 511810.369 | 3625278.109
|  |  | 122.195 | [15 empty] | 122.195 | [5 empty] | 11 kv Line Crossing
18 | AP 103/0 | DD+6 |  | 1734.536 | 37° 03' 00"RT | 511713.535 | 3625352.639 | 18 | AP 103/0 | DD+6 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 |  | 1733.452 | 476.5 | 37° 03' 00"RT | 511713.535 | 3625352.639
|  |  | 185.672 | [15 empty] | 185.672 | [5 empty] | Electrified Railway crossing,11 KV Crossing
19 | AP 104/0 | DD+9 |  | 1920.208 | 24° 32' 24"LT | 511664.337 | 3625531.674 | 19 | AP 104/0 | DD+9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1919.124 | 475.575 | 24° 32' 24"LT | 511664.337 | 3625531.674 | Contour Not Required
|  |  | 303.562 | [15 empty] | 303.562
20 | AP 105/0 | DD+0 |  | 2223.77 | 55° 28' 40"RT | 511469.585 | 3625764.529 | 20 | AP 105/0 | DD+0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 2222.686 | 475.007 | 55° 28' 40"RT | 511469.585 | 3625764.529
|  |  | 287.716 | [15 empty] | 287.716 | [5 empty] | 2nos 11KV Line Crossing
21 | AP 106/0 | DB+0 |  | 2511.486 | 13° 39' 57"RT | 511546.814 | 3626041.686 | 21 | AP 106/0 | DB+0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2510.402 | 469.175 | 13° 39' 57"RT | 511546.814 | 3626041.686 | Contour Not Required
|  |  | 425.991 | [15 empty] | 425.991
22 | AP 107/0 | DC+0 |  | 2937.477 | 27° 39' 10"RT | 511754.875 | 3626413.41 | 22 | AP 107/0 | DC+0 | -1.5 | -1.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2936.393 | 457.977 | 27° 39' 10"RT | 511754.875 | 3626413.41 | 2nos LTLine crossing
|  |  | 141.744 |  |  |  | AP24-AP39 | [11 empty] | 141.744
23 | AP 108/0 | DC+0 |  | 3079.221 | 16° 58' 12"LT | 511873.602 | 3626490.839 | 23 | AP 108/0 | DC+0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3078.137 | 458.784 | 16° 58' 12"LT | 511873.602 | 3626490.839 | Contour Not Required
|  |  | 52.346 | [15 empty] | 52.346
24 | AP 109/0 | DD+0 |  | 3131.567 |  | 511907.194 | 3626530.984 | 24 | AP 109/0 | DD+0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3130.483 | 458.578 |  | 511907.194 | 3626530.984 | Contour Not Required

## Foundation JS-Line -Jammu
KEC INTERNATIONAL LIMITED | [13 empty] | Date: | 2026-02-16
400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5-Jammu Portion
FOUNDATION
S.No | Loc No. | Tower Type | Classification | Conc Volume | Start Date | Foundation | [5 empty] | Earthing | FDN Status | Gang Name | Gang Strength | Remark
[6 empty] | Excavation | Stub Setting | PCC | Rebar Placing | RCC | Completion Date
1 | 29/5 | DA+0 | WET | 34.389 | 2025-07-28 | 2025-08-07 | 2025-08-10 | 2025-08-10 | 2025-08-10 | 2025-08-11 | 2025-08-11 | 2025-12-03 | Completed | Rakesh | 8
2 | 29/4 | DA+0 | DRY | 21.318 | 2025-08-11 | 2025-08-21 | 2025-08-21 | 2025-08-22 | 2025-08-22 | 2025-09-06 | 2025-09-06 | 2025-12-03 | Completed | Rakesh | 5
3 | 29/3 | DA+0 | DRY | 21.318 | 2025-08-31 | 2025-09-21 | 2025-09-21 | 2025-09-22 | 2025-09-22 | 2025-09-24 | 2025-09-24 |  | Completed | Adishiv | 12 | Completed & 1 leg 1.5 M RC pending
4 | 27/0 | DB+0 | WET | 71.702 | 2025-09-07 | 2025-09-16 | 2025-09-18 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-20 | 2026-01-10 | Completed | Adishiv | 12
5 | 17/0 | DC+3 | FS | 142.45 | 2025-09-10 | 2025-11-21 | 2025-11-22 | 2025-11-22 | 2025-11-22 | 2025-11-23 | 2025-11-23 | 2025-12-07 | Completed | Md.Farooq | 12 | Benching work completed on 21.9.25 Pit B- Casting completed. Work on hold since 12th Oct'25 & restart from 07th Nov'25 & completed on 23rd Nov'25
6 | 18/0 | DC+0 | FS | 134.312 | 2025-09-11 | 2025-10-14 | 2025-10-14 | 2025-10-14 | 2025-10-14 | 2025-10-16 | 2025-10-16 | 2025-10-18 | Completed | Md. Sharif | 20
7 | 29/6 | DA+3 | WET |  | 2025-10-10 | 2025-10-14 | 2025-10-14 | 2025-10-15 | 2025-10-15 | 2025-10-16 | 2025-10-16 | 2025-10-18 | Completed | Adishiv | 12 | Intially work started on 26.9.25 but due to high water table work was hold till 3.10.25 and as advised by RKPTL team loc shifted about 60 mtrs and work resumed from 10.10.25 & completed on 16.10.25
8 | 30/3 | DA+6 | PS |  | 2025-10-30 | 2025-11-22 | 2025-11-23 | 2025-11-23 | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-26 | Completed | Kewal Krishan | 9
9 | 23/1 | DA+6 | WET |  | 2025-09-25 | 2025-11-04 | 2025-11-07 | 2025-11-07 | 2025-11-08 | 2025-11-10 | 2025-11-10 | 2025-12-06 | Completed | Vishal | 8
10 | 29/1 | DA+0 | WET |  | 2025-10-03 | 2025-10-07 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-10 | 2025-10-10 | 2025-10-29 | Completed | Adishiv | 12 | RC Casting done by Anil Sharma on 11.02.2026
11 | 22/1 | DA+3 | WET |  | 2025-10-10 | 2025-10-27 | 2025-10-27 | 2025-10-27 | 2025-10-27 | 2025-10-28 | 2025-10-28 | 2025-11-20 | Completed | ANB Construction | 5
12 | 15/2 | DA+0 | FS |  | 2025-10-18 | 2025-11-09 | 2025-11-18 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-12-07 | Completed | Balwanth Singh | 21
13 | 31/1 | DA+3 | PS |  | 2025-10-17 | 2025-10-27 | 2025-10-28 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-30 | 2025-11-20 | Completed | Md. Sharif | 24
14 | 22/0 | DC+3 | WET |  | 2025-10-18 | 2025-10-30 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-11-19 | Completed | Surjeet | 10
15 | 21/1 | DA+0 | WET |  | 2025-10-28 | 2025-10-30 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-11-09 | Completed | Surjeet | 19
16 | 31/3 | DA+0 | PS |  | 2025-10-30 | 2025-11-07 | 2025-11-09 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-11 | 2025-11-11 | Completed | Md. Sharif | 12
17 | 22/2 | DA+3 | WET |  | 2025-10-29 | 2025-11-10 | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-11-13 | 2025-11-13 | 2025-11-20 | Completed | ANB Construction | 8
18 | 15/1 | DA+0 | PS |  | 2025-11-06 | 2025-11-13 | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-12-02 | Completed | Balwanth Singh | 21
19 | 40/0 | DC+3 | PS |  | 2025-11-09 | 2025-11-30 | 2025-12-02 | 2025-12-02 | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-15 | Completed | Pawan Kumar Shama | 15
20 | 20/0 | DB+6 | WET |  | 2025-11-12 | 2025-11-25 | 2025-11-28 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-11-30 | 2025-12-04 | Completed | Surjeet | 8
21 | 27/1 | DA+3 | WET |  | 2025-11-14 | 2025-11-17 | 2025-11-22 | 2025-11-22 | 2025-11-23 | 2025-11-23 | 2025-11-23 | 2025-12-07 | Completed | Md.Sharif | 40 | RC Casting Pending
22 | AP32 | DB+0 | FS |  | 2025-11-12 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-23 | 2025-11-26 | 2025-11-26 | 2025-12-02 | Completed | Md.Sharif
23 | 23/0 | DB+0 | FS |  | 2025-11-15 | 2025-12-06 | 2025-12-07 | 2025-12-07 | 2025-12-08 | 2205-12-09 | 2025-12-09 | 2025-12-11 | Completed | ANB Construction | 9
24 | 30/5 | DA+9 | PS |  | 2025-11-16 | 2025-11-28 | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-12-05 | Completed | Akram | 15
25 | 40/1 | DA+3 | WET |  | 2025-11-16 | 2025-11-29 | 2025-11-30 | 2025-11-30 | 2025-11-30 | 2025-11-30 | 2025-11-30 | 2025-12-06 | Completed | Thakur Cosnt | 7
26 | 19/2 | DA+0 | FS |  | 2025-11-23 | 2025-12-11 | 2025-12-11 | 2025-12-13 | 2025-12-13 | 2025-12-13 | 2025-12-13 | 2025-12-16 | Completed | Balwanth Singh | 9
27 | 18/1 | DA+0 | PS |  | 2025-11-25 | 2025-12-05 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-07 | Completed | Md.Farooq | 12
28 | AP28 | DC+6 | WET |  | 2025-11-27 | 2025-11-28 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-04 | 2025-12-04 | 2025-12-03 | Completed | Md. Sharif | 35
29 | 30/2 | DA+0 | PS |  | 2025-11-27 | 2025-12-09 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-12 | 2025-12-12 | 2025-12-16 | Completed | Kewal Krishan | 8
30 | 23/4 | DA+3 | FS |  | 2025-11-30 | 2025-12-28 | 2025-12-30 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2026-01-07 | Completed | Anil Sharma | 7 | Pit B, C, D- Casting Completed Pit A- Prop Setting/PCC
31 | 29/0 | DC+9 | WET |  | 2025-12-03 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-10 | 2025-12-12 | Completed | Md. Sharif | 28
32 | 23/5 | DA+3 | FS |  | 2025-12-03 | 2025-12-20 | 2025-12-21 | 2025-12-21 | 2025-12-21 | 2025-12-21 | 2025-12-21 |  | Completed | Balwanth Singh | 20
33 | 39/2 | DA+0 | FS |  | 2025-12-05 | 2025-12-12 | 2025-12-12 | 2025-12-13 | 2025-12-13 | 2025-12-13 | 2025-12-13 | 2025-12-15 | Completed | Pawan Kumar Shama | 17
34 | 30/4 | DA+0 | FS |  | 2025-12-05 | 2025-12-18 | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-23 | Completed | Akram | 15
35 | AP33 | DC+0 | FS |  | 2025-12-09 | 2025-12-28 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-16 | Completed | Adishiv | 8 | Pit A,D,C - Casting Completed Pit B- Excavation Completed
36 | AP19 | DC+0 | FS |  | 2025-12-10 | 2025-12-22 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-24 | 2025-12-24 | 2025-12-21 | Completed | Md.Farooq | 12
37 | AP43 | DD+3 | WET |  | 2025-12-11 | 2025-12-20 | 2025-12-21 | 2025-12-23 | 2025-12-23 | 2025-12-25 | 2025-12-25 | 2026-01-03 | Completed | Thakur Cosnt | 16
38 | AP45 | DB+0 | WET |  | 2025-12-12 | 2025-12-20 | 2025-12-22 | 2025-12-22 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-25 | Completed | Md. Sharif | 28
39 | 31/2 | DA+0 | FS |  | 2025-12-16 | 2025-12-24 | 2025-12-25 | 2025-12-25 | 2025-12-27 | 2025-12-27 | 2025-12-27 | 2026-01-19 | Completed | Gulam | 12
40 | 46/1 | DA+0 | PS |  | 2025-12-17 | 2025-12-24 | 2025-12-24 | 2025-12-25 | 2025-12-25 | 2025-12-25 | 2025-12-25 | 2026-01-02 | Completed | Pawan Kumar Shama | 17
41 | AP31 | DB+0 | FS |  | 2025-12-19 | 2026-01-11 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-18 | 2026-01-18 | 2026-01-02 | Completed | Akram | 15
42 | AP16 | DC+0 | FS |  | 2026-01-04 | 2026-01-21 | 2026-01-24 | 2026-01-24 | 2026-01-25 | 2026-01-25 | 2026-01-25 |  | Completed | Balwanth Singh | 20 | Pit B,C,D - Casting Completed
43 | 18/2 | DA+6 | FS |  | 2025-12-25 | 2026-01-06 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-08 | 2026-01-08 | 2026-01-22 | Completed | Md.Farooq | 12
44 | AP26 | DD+0 | FS |  | 2025-12-24 | 2026-01-04 | 2026-01-05 | 2026-01-07 | 2026-01-07 | 2026-01-08 | 2026-01-08 |  | Completed | Balwanth Singh | 20
45 | 43/1 | DA+6 | FS |  | 2025-12-27 | 2026-01-02 | 2026-01-02 | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-04 | 2026-01-22 | Completed | Thakur Cosnt | 16
46 | 31/4 | DA+3 | FS |  | 2025-12-29 | 2026-01-07 | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-09 | 2026-01-09 | 2026-01-10 | Completed | Gulam | 12
47 | 46/3 | DA+0 | FS |  | 2025-12-29 | 2026-01-07 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-10 | Completed | Pawan Kumar Shama | 17
48 | AP30 | DB+0 | FS |  | 2026-01-04 | 2026-01-21 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-31 | 2026-01-31 |  | Completed | Akram | 18
49 | 43/2 | DA+0 | FS |  | 2026-01-07 | 2026-01-11 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-21 | Completed | Thakur Cosnt | 16
50 | 32/1 | DA+6 | FS |  | 2026-01-08 | 2026-01-29 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-02-02 | Completed | Anil Sharma | 7
51 | 33/1 | DA+0 | FS |  | 2026-01-08: 2026-01-09 | WIP | Adishiv | 8 | Pit C - Casting Completed Due to heavy rains loc water logged
52 | 25/2 | DA+0 | FS |  | 2026-01-11 | 2026-01-20 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-02-01 | Completed | Balwanth Singh | 20
53 | 45/2 | DA+0 | PS |  | 2026-01-12 | 2026-01-20 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-02-08 | Completed | Pawan Kumar Shama | 12
54 | 19/1 | DA+0 | FS |  | 2026-01-12 | 2026-01-19 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-22 | Completed | Md.Farooq | 10
55 | 31/5 | DA+3 | FS |  | 2026-01-14 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | Completed | Gulam | 10
56 | 50A/7 | DA+6 | PS |  | 2026-01-31 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-14 | 2026-02-14 |  | Completed | Wani Const | 8
57 | 44/3 | DA+0 | FS |  | 2026-01-16 | 2026-01-20 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 |  | Completed | Thakur Cosnt | 16
58 | 44/2 | DA+0 | FS |  | 2026-01-29 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-07 | 2026-02-07 | 2026-02-07 |  | Completed | Thakur Cosnt | 16
59 | AP21 | DD+6 | WET |  | 2026-01-14: 2026-01-29 | WIP | Akram | 18 | Pit C,D - Casting upto frustrum
60 | 45/1 | DA+3 | PS |  | 2026-01-29 | 2026-02-04 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 |  | Completed | Pawan Kumar Shama | 12
61 | AP15 | DD+18 | WET |  | 2026-01-31 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-08 | 2026-02-08 |  | Completed | Balwanth Singh | 20
62 | AP12 | DD+30 | WET /PS |  | 2026-01-14: 2026-02-03 | WIP | Gulam | 10 | Pit C,D - Casting Completed Pit A,B - Steel Binding
63 | 25/1 | DA+0 | FS |  | 2026-02-05 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-13 | 2026-02-13 |  | Completed | Balwanth Singh | 20
64 | AP35 | DD+0 | FS |  | 2026-01-14: 2026-02-05 | WIP | Adishiv | 8 | Casting u/p
65 | AP46 | DB+0 | FS |  | 2026-01-14: 2026-02-10 | WIP | Pawan Kumar Shama | 12 | Pit C,D - Casting Completed
66 | AP44 | DB+0 | PS |  | 2026-01-14: 2026-02-11 | WIP | Thakur Cosnt | 16 | Pit B,C - Casting upto frustrum
67 | AP25 | DD+0 | FS |  | 2026-01-14: 2026-02-15 | WIP | Balwanth Singh | 20 | Block level
68 | 29/2 | DA+3 | PS (SD) |  | 2026-01-14: 2026-02-13 | WIP | Anil Sharma | 8 | Block level
69 | 50A/3 | DA+3 | PS |  | 2026-01-14: 2026-02-15 | WIP | Wani Const | 8 | Excavation

## Erection -Jammu
KEC INTERNATIONAL LIMITED | [7 empty] | Date: | 2026-02-16
400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5-Jammu Portion
TOWER ERECTION
S.No | Loc No. | Tower Type | Weight MT | Conc Volume | Starting Date | Completion Date | Status | Gang Name | Gang Strength | Remark
1 | 29/5 | DA+0 | 18.32 | 34.389 | 2025-11-27 | 2025-12-03 | Completed | Raj Labour Suppliers | 23
2 | 29/4 | DA+0 | 18.32 | 21.318 | 2025-12-05 | 2025-12-10 | Completed | Raj Labour Suppliers | 23
3 | 27/0 | DB+0 | 27.92 | 21.318 | 2025-12-11 | 2025-11-21 | Completed | Raj Labour Suppliers | 23
4 | 29/6 | DA+3 | 19.44 |  | 2025-12-22 | 2025-12-29 | Completed | Raj Labour Suppliers | 20
5 | 15/1 | DA+0 | 18.32 |  | 2025-12-25 | 2026-01-05 | Completed | Anbi Construction | 15
6 | 30/3 | DA+6 | 22.68 |  | 2025-12-29 | 2026-01-08 | Completed | Raj Labour Suppliers | 20
7 | 15/2 | DA+0 | 18.32 |  | 2026-01-07 | 2026-01-16 | Completed | Anbi Construction | 15
8 | 30/5 | DA+9 | 24.13 |  | 2026-01-09 | 2026-01-18 | Completed | Raj Labour Suppliers | 20
9 | AP18 | DC+0 | 32.22 |  | 2026-01-18 | 2026-01-31 | Completed | Anbi Construction | 21
10 | 30/4 | DA+0 | 18.32 |  | 2026-01-18 | 2026-01-22 | Completed | Raj Labour Suppliers | 22
11 | 31/1 | DA+3 | 19.44 |  | 2026-01-25 | 2026-02-01 | Completed | Raj Labour Suppliers | 22
12 | 31/2 | DA+0 | 18.32 |  | 2026-02-01 | 2026-02-06 | Completed | Raj Labour Suppliers | 22
13 | 19/2 | DA+0 | 18.32 |  | 2026-02-01 | 2026-02-07 | Completed | Anbi Construction | 21
14 | 23/1 | DA+0 | 18.32 |  | 2026-02-05 | 2026-02-10 | Completed | Kushboo Devi | 21 | Due to row gang idle for 2 days 07-02-2026 to 08-02-2026
15 | 31/3 | DA+0 | 18.32 |  | 2026-02-06 |  | Completed | Raj Labour Suppliers | 22
16 | 19/1 | DA+0 | 18.32 |  | 2026-02-08 | 2026-02-13 | Completed | Anvi Construction | 21
17 | 31/4 | DA+3 | 19.44 |  | 2026-02-09 | 2026-02-13 | Completed | Raj Labour Suppliers | 22
18 | AP23 | DB+0 | 27.92 |  | 2026-02-11 | 2026-02-15 | Completed | Kushboo Devi | 21
19 | AP32 | DB+0 | 27.921 |  | 2026-02-13 |  | Bottom Section | Raj Labour Suppliers | 22
20 | AP19 | DC+0 | 32.222 |  | 2026-02-13 |  | 1st section | Anvi Construction | 21
21 | 23/5 | DA+3 | 19.44 |  | 2026-02-15 |  | 1st section | Kushboo Devi | 21
22 | 40/1 | DA+3 | 19.44 |  | 2026-02-16 |  | Material Shifting | Sanjay | 26
23 | AP45 | DB+0 | 27.92 |  | 2026-02-16 |  | Material Shifting | Raju Kumar | 23

## Erection-Punjab
KEC INTERNATIONAL LIMITED | [7 empty] | Date: | 2026-02-16
400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5- Punjab Portion
TOWER ERECTION
S.No | Loc No. | Tower Type | Weight MT | Conc Volume | Starting Date | Completion Date | Status | Gang Name | Gang Strength | Remark
1 | 89/1 | DA+3 | 19.44 | 34.389 | 2026-02-02 | 2026-02-06 | Completed | Saritha Devi | 30
2 | 92/2 | DA+6 | 22.68 | 21.318 | 2026-02-02 | 2026-02-10 | Completed | Dhruv Strategic | 32
3 | 117/3 | DA+0 | 18.32 |  | 2026-02-03 | 2026-02-07 | Completed | Poonam Kumari | 34
4 | 97/2 | DA+0 | 18.32 |  | 2026-02-05 | 2026-02-09 | Completed | Jwala Singh | 22
5 | 95/3 | DA+0 | 18.32 |  | 2026-02-06 | 2026-02-08 | Completed | Saritha Devi | 30
6 | 117/1 | DA+0 | 18.32 |  | 2026-02-07 | 2026-02-11 | Completed | Poonam Kumari | 34
7 | 95/2 | DA+0 | 18.32 |  | 2026-02-08 | 2026-02-11 | Completed | Saritha Devi | 30
8 | 97/1 | DA+0 | 18.32 |  | 2026-02-09 | 2026-02-12 | Completed | Jwala Singh | 22
9 | 117/2 | DA+3 | 19.44 |  | 2026-02-11 | 2026-02-16 | Completed | Poonam Kumari-1 | 34
10 | 95/4 | DA+0 | 18.32 |  | 2026-02-11 | 2026-02-13 | Completed | Saritha Devi | 30
11 | 131/4 | DA+0 | 18.32 |  | 2026-02-12 |  | Cross Arm Fitting | ZR Construction | 30
12 | 92/3 | DA+0 | 18.32 |  | 2026-02-12 | 2026-02-16 | Completed | Poonam Kumari-2 | 30
13 | 97/3 | DA+3 | 19.44 |  | 2026-02-12 |  | Body Completed | Jwala Singh | 22
14 | AP96 | DC+0 | 32.222 |  | 2026-02-13 |  | Body Completed | Saritha Devi | 30
15 | 76/1 | DA+0 | 18.32 |  | 2026-02-16 |  | Material Shifting | Rakesh | 23
16 | 93/2 | DA+0 | 18.32 |  | 2026-02-16 |  | Material Shifting | Poonam Kumari-2 | 30
17 | AP115 | DB+0 | 27.92 |  | 2026-02-16 |  | Leg Jointing | Poonam Kumari-1 | 30

## Vertical Chart -JS Line Punjab
KEC INTERNATIONAL LIMITED
400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5-Punjab Portion
Vertical Chart
[9 empty] | Complete |  | 134 | 118 | 99 | 11 | 0
[9 empty] | WIP |  |  | 12 | 0 | 6 | 0
S.No | Tower | TOT | Angle of Deviation | Raised Chimney |  |  |  | FDN Classification | Span Length (Mtr) | Section Length (m) | ROW | Foundation | Earthing | Tower Erection | Tack Welding | Stringing | Remarks
|  |  |  | LEG A | LEG B | LEG C | LEG D
1 | AP53 | DC+0 | 29°2'38"RT | [6 empty] | 0
416.658
2 | AP54 | DC+6 | 15°23'08"RT | [6 empty] | 416.658
389.277
3 | AP55 | DD+3 | 38°18'51"RT | [6 empty] | 389.277
384.151
4 | 55/1 | DA+6 | [7 empty] | 384.151
409.3
5 | AP56 | DC+3 | 25°53'58"RT | [6 empty] | 409.3
409.72
6 | 56/1 | DA+6 | [7 empty] | 409.72
406.732
7 | 56/2 | DA+3 | [7 empty] | 406.732
404.913
8 | 56/3 | DA+6 | [7 empty] | 404.913
285.563
9 | 56/4 | DA+6 | [7 empty] | 285.563
399.174
10 | AP57 | DD+3 | 39°39'47"LT | [6 empty] | 399.174
343.784
11 | 57/1 | DA+0 | [7 empty] | 343.784
313.063
12 | 57/2 | DA+0
325.525
13 | AP58 | DC+0 | 24°19'0"RT
406.443
14 | AP59 | DD+6 | 47°09'41"LT
423.081
15 | 59/1 | DA+3 | [7 empty] | 1468.112
364.958
16 | AP60 | DB+6 | 8°29'30"LT | [6 empty] | 364.958
380.949
17 | 60/1 | DA+0 | [7 empty] | 380.949
376.626
18 | AP61 | DC+0 | 21°54'40"RT
299.077
19 | 61/1 | DA+0
264.842
20 | AP62 | DB+0 | 4°52'18"RT | [6 empty] | 940.545
364.064
21 | 62/1 | DA+0
319.184
22 | 62/2 | DA+0
397.985
23 | AP63 | DB+9 | 12°25'23"LT | [6 empty] | 1081.233
450.859
24 | AP64 | DC+9 | 17°10'17"RT | [6 empty] | 450.859
326.477
25 | 64/1 | DA+0
276.363
26 | AP65 | DB+0 | 12°37'37"RT | [6 empty] | 602.84
307.216
27 | 65/1 | DA+0
389.397
28 | 65/2 | DA+6
368.792
29 | 65/3 | DA+0 | [7 empty] | 1065.405
404.386
30 | 65/4 | DA+3
378.135
31 | 65/5 | DA+3
370.482
32 | AP66 | DC+0 | 26°31'54"RT
199.386
33 | AP67 | DD+0 | 42°51'4"LT
294.009
34 | 67/1 | DA+0
312.708
35 | 67/2 | DA+0 | [7 empty] | 1959.106
[9 empty] | 321.893 | [7 empty] | 66 KV H Pole Gurdaspur To Gahlari T/L
36 | 67/3 | DA+0 | [7 empty] | 321.893
382.475
37 | AP68 | DB+0 | 12°54'1"LT |  |  |  |  | PS (SD) |  |  | Clear | WIP
388.11
38 | AP69 | DB+0 | 5°21'56"RT
382.675
39 | 69/1 | DA+0 | [5 empty] | FS |  | 1153.26 | Clear | C
390.446
40 | 69/2 | DA+0 | [5 empty] | FS |  | 390.446 | Clear | C | C
361.751
41 | 69/3 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
396.035
42 | AP70 | DC+3 | 28°33'28"RT |  |  |  |  | PS (SD) |  |  | Clear | WIP
435.862
43 | 70/1 | DA+9 | [7 empty] | 435.862
333.945
44 | 70/2 | DA+0 | [5 empty] | PS (SD) |  |  | Clear | WIP
502.836
45 | AP70/3 | DD+18 | 2°59'27"LT | 2 | 2 | 2 | 2
326.311
46 | AP71 | DC+9 | 17°25'49"LT
415.29
47 | 71/1 | DA+3 | [8 empty] | Clear
422.422
48 | 71/2 | DA+9 | [5 empty] | WET |  |  | Clear | C
418.373
49 | 71/3 | DA+6 | [5 empty] | WET |  |  | Clear | C
410.137
50 | AP72 | DB+3 | 1°09'23"LT |  |  |  |  | WET |  | 2829.314 | Clear | C | C
422.214
51 | 72/1 | DA+3 | [5 empty] | WET |  |  | Clear | WIP
387.357
52 | 72/2 | DA+6 | [5 empty] | WET |  |  | Clear | C
406.688
53 | AP74 | DB+0 | 12°51'59"LT |  |  |  |  | WET |  |  | Clear | C | C
316.253
54 | AP75 | DB+9 | 3°17'24"LT |  |  |  |  | FS |  |  | Clear | C | C
[9 empty] | 248.423 | [7 empty] | 66 KV D/C Gurdaspur To Jaura Chattran T/L N-H 354 GUDASPUR TO DERA BAB NANAK STON KM LEFT-183 RITE-182
55 | AP76 | DC+9 | 15°15'15"LT
427.328
56 | 76/1 | DA+0 | [5 empty] | WET |  | 2208.263 | Clear | C | C | WIP
413.234
57 | 76/2 | DA+3 | [5 empty] | WET |  |  | Clear | C | C
414.719
58 | 76/3 | DA+3 | [5 empty] | WET |  |  | Clear | C | C
426.172
59 | AP77 | DB+3 | 4°28'22"LT |  |  |  |  | WET |  |  | Clear | C | C
404.81
60 | 77/1 | DA+3 | [5 empty] | WET |  |  | Clear | C | C
392.738
61 | 77/2 | DB+0 | [5 empty] | WET |  |  | Clear | C | C
391.939
62 | 77/3 | DA+0 | [7 empty] | 2443.612
440.91
63 | AP78 | DB+9 | 2°13'37"RT | 2 | 2 | 2 | 2
[9 empty] | 310.905 | [7 empty] | 132 KV S/C DHARIWAL-GURDASPUR
64 | AP79 | DD+9 | 33°52'12"LT |  |  |  |  | WET |  | 751.815 | Clear | WIP
[9 empty] | 240.527 | [7 empty] | NH-54 AMRITSAR TO GURDASPUR STON KM LEFT-41 RITE-42
65 | AP80 | DD+0 | 52°58'23"RT |  |  |  |  | PS |  |  | Clear | C | C
389
66 | 80/1 | DB+3 | [5 empty] | WET |  |  | Clear | C | C
468.318
67 | AP81 | DD+9 | 45°25'14"LT | [6 empty] | 1097.845
[9 empty] | 242.663 | [7 empty] | SINGLE LINE RAIL WAY TRACK EP NO-62/9 EP NO-62/8 (Non Electrified)
68 | AP82 | DD+3 | 36°50'39"RT
408.258
69 | 82/1 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
337.476
70 | 82/2 | DA+3 | [5 empty] | WET |  |  | Clear | C | C
403.418
71 | AP83 | DD+25 | 0°34'37"LT | [6 empty] | 740.894
[9 empty] | 251.516 | [7 empty] | 220 KV D/C Sohal TES to Tibber Transmission Line
72 | AP84 | DD+18 | 3°10'24"RT | [6 empty] | 251.516
445.126
73 | AP85 | DB+0 | 2°22'29"RT |  |  |  |  | WET |  |  | Clear | C | C
387.7
74 | 85/1 | DA+9 | [5 empty] | WET |  |  | Clear | C | C
449.348
75 | AP86 | DC+0 | 14°12'50"LT | [6 empty] | 1282.174 | ROW
408.793
76 | 86/1 | DA+3 | [5 empty] | WET |  |  | Clear | C | C
425.487
77 | AP87 | DB+9 | 7°9'8"RT |  |  |  |  | PS |  | 834.28 | Clear | C | C
386.799
78 | 87/1 | DA+3 | [8 empty] | ROW
380.77
79 | 87/2 | DA+3 | [5 empty] | WET |  |  | Clear | C | C
421.314
80 | AP88 | DD+18 | 28°53'35"LT | [6 empty] | 1188.883
[9 empty] | 211.063 | [7 empty] | 220 KV D/C Wadala Grinthian To Sarna CKT-4, 220 KV D/C Wadala Grinthian To Tibber CKT-3
81 | AP89 | DD+18 | 31°35'10"RT
385.103
82 | 89/1 | DA+3 | [5 empty] | WET |  |  | Clear | C | C | C
233.126
83 | AP90 | DD+0 | 40°23'13"LT |  |  |  |  | WET |  |  | Clear | C | C
411.24
84 | 90/1 | DA+3 | [5 empty] | WET |  | 1240.532 | Clear | C
320.979
85 | 90/2 | DA+0 | [5 empty] | WET |  | 320.979 | Clear | C | C
448.791
86 | AP91 | DD+25 | 11°45'19"RT |  |  |  |  | PS |  |  | Clear | WIP
[9 empty] | 247.685 | [7 empty] | 220 KV D/C Sarna To Wadala Granthian T/L
87 | AP92 | DD+25 | 34°8'24"RT |  |  |  |  | PS |  |  | Clear | C
360.878
88 | 92/1 | DA+3 | [5 empty] | WET |  |  | Clear | C | C
415.643
89 | 92/2 | DA+6 | [5 empty] | WET |  | 1472.997 | Clear | C |  | C
379.751
90 | 92/3 | DA+0 | [5 empty] | WET |  |  | Clear | C |  | C
298.884
91 | AP93 | DC+0 | 18°20'38"RT |  |  |  |  | WET |  |  | Clear | C | C
314.664
92 | 93/1 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
301.757
93 | 93/2 | DA+0 | [5 empty] | WET |  |  | Clear | C |  | WIP
272.654
94 | AP94 | DB+0 | 0°29'54"RT |  |  |  |  | WET |  | 1567.71 | Clear | C | C
411.542
95 | AP95 | DC+3 | 19°44'06"LT |  |  |  |  | WET |  |  | Clear | C | C
375.054
96 | 95/1 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
357.801
97 | 95/2 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
338.209
98 | 95/3 | DA+0 | [5 empty] | WET |  | 1482.606 | Clear | C | C | C
358.793
99 | 95/4 | DA+0 | [5 empty] | WET |  | 2114.053 | Clear | C | C | C
321.162
100 | AP96 | DC+0 | 21°39'03"LT |  |  |  |  | WET |  |  | Clear | C | C | WIP
243.936
101 | AP97 | DD+3 | 31°16'41"RT |  |  |  |  | WET |  | 923.891 | Clear | C | C
406.692
102 | 97/1 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
387.95
103 | 97/2 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
401.317
104 | 97/3 | DA+3 | [5 empty] | WET |  | 2119.85 | Clear | C | C | WIP
419.636
105 | AP98 | DB+3 | 3°04'27"LT |  |  |  |  | WET |  |  | Clear | C | C
369.141
106 | 98/1 | DA+3 | [5 empty] | WET |  |  | Clear | C | C
280.435
107 | AP99 | DB+0 | 5°27'41"RT |  |  |  |  | WET |  | 2265.171 | Clear | C | C
392.603
108 | 99/1 | DA+9 | [5 empty] | WET |  |  | Clear | C | C
384.166
109 | AP100 | DC+3 | 22°17'08"LT |  |  |  |  | WET |  |  | Clear | C | C
408.003
110 | AP101 | DC+0 | 26°08'26"RT | [7 empty] | ROW
390.238
111 | AP102 | DB+0 | 11°0'39"LT |  |  |  |  | WET |  | 1575.01 | Clear | C | C
360.683
112 | 102/1 | DA+6 | [5 empty] | WET |  | 360.683 | Clear | C | C
350.527
113 | AP103 | DD+0 | 34°17'09"LT |  |  |  |  | WET |  | 350.527 | Clear | C | C
380.322
114 | 103/1 | DA+0 | [5 empty] | WET |  | 380.322 | Clear | C | C
331.6
115 | AP104 | DB+0 | 5°25'28"LT |  |  |  |  | WET |  |  | Clear | C | C
406.096
116 | 104/1 | DA+3 | [5 empty] | WET |  |  | Clear | C | C
313.788
117 | AP105 | DD+3 | 33°19'08"RT | 1 | 1 | 1 | 1
413.223
118 | AP106 | DD+6 | 32°25'19"LT |  |  |  |  | WET |  |  | Clear | C | C
297.539
119 | 106/1 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
283.671
120 | AP107 | DB+0 | [8 empty] | ROW
378.12
121 | AP108 | DD+25 | 42°31'57"LT
[9 empty] | 249.176 | [7 empty] | 800 KV S/C Kishenpur-Moga Transmission line CKT-1
122 | AP109 | DD+30 | 42°18'19"RT
198.719
123 | AP110 | DD+0 | 37°33'29"RT
287.047
124 | AP111 | DC+0 | 22°58'26"RT |  |  |  |  | WET |  |  | Clear | WIP
317.654
125 | AP112 | DD+30 | 48°59'48"RT | [6 empty] | 3476.633
[9 empty] | 245.547 | [7 empty] | 800 KV S/C Kishenpur-Moga Transmission line CKT-1
126 | AP113 | DD+25 | 53°39'13"LT
342.986
127 | AP114 | DB+0
384.064
128 | AP115 | DB+0 | 10°13'52"LT |  |  |  |  | WET |  |  | Clear | C | C | WIP
373
129 | 115/1 | DA+6 | [5 empty] | WET |  |  | Clear | C | C
[9 empty] | 378 | [7 empty] | 66 kV H-Pole Power Line Qadian to Bharth (CL- 13.300 m)
130 | AP116 | DCT+0 | [5 empty] | FS |  |  | Clear | C | C
283
131 | 116/1 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
232.015
132 | AP117 | DB+0 | 3°36'30"RT |  |  |  |  | WET |  |  | Clear | C | C
323.186
133 | 117/1 | DA+0 | [5 empty] | WET |  |  | Clear | C |  | C
351.475
134 | 117/2 | DA+3 | [5 empty] | WET |  |  | Clear | C | C | C
368.874
135 | 117/3 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | C
366.147
136 | AP118 | DC+0 | 16°09'46"LT |  |  |  |  | WET |  |  | Clear | C | C
326.21
137 | 118/1 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
308.149
138 | AP119 | DC+0 | 26°16'41"LT
285.935
139 | 119/1 | DA+0
232.238
140 | AP120 | DD+0 | 42°02'04"RT
396.913
141 | 120/1 | DA+3
412.767
142 | 120/2 | DA+6
402.69
143 | AP121 | DC+3 | 19°30'25"LT
374.133
144 | 121/1 | DA+0
377.376
145 | 121/2 | DA+0
385.349
146 | AP122 | DB+0 | 4°36'22"LT
395.252
147 | 122/1 | DA+3
358.294
148 | AP123 | DC+0 | 18°24'26"RT
[9 empty] | 426.276 | [7 empty] | 132 KV S/C LINE Power Wadala to Hargobindpur (CL- 9.2 M)
149 | AP124 | DB+9 | 04°41'01"RT
217.161
150 | AP125 | DD+18 | 31°42'07"LT
425.244
151 | AP126 | DB+ 0
373.291
152 | AP127 | DD+30 | 28°54'28"LT
[9 empty] | 240.81 | [7 empty] | 800 KV S/C Power LINE Kishanpur to Moga (CL- 9.300 M)
153 | AP128 | DD +30 | 44°0'03"RT
501.813
154 | AP129 | DB+9 | 8°06'53"RT |  |  |  |  | PS |  |  | Clear | C | C
[9 empty] | 244.068 | [7 empty] | 132 KV S/C Power Line Wadala to Hargobindpur (CL -7.1 m)
155 | AP130 | DD+18 | 7°08'11"RT |  |  |  |  | PS |  |  | Clear | C | C
387.815
156 | 130/1 | DA +0 | [5 empty] | WET |  |  | Clear | C | C
303.927
157 | 130/2 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
158 | AP131 | DC +0 | 22°30'33"LT |  |  |  |  | WET |  |  | Clear | C | C
407.946
159 | 131/1 | DA+3 | [5 empty] | WET |  |  | Clear | C | C
429.847
160 | 131/2 | DA+3 | [5 empty] | WET |  |  | Clear | C | C
407.778
161 | 131/3 | DA+3 | [5 empty] | WET |  |  | Clear | C | C
416.733
162 | 131/4 | DA+0 | [5 empty] | WET |  |  | Clear | C | C | WIP
421.345
163 | 131/5 | DA+3 | [5 empty] | WET |  |  | Clear | C | C
385.64
164 | 131/6 | DA+9 | [5 empty] | WET |  |  | Clear | C | C
[9 empty] | 372.699 | [7 empty] | 66 Kv H-Pole Power Line Crossing Ghoman to Shri Hargobindpur (CL- 6.100 m)
165 | AP132 | DC+9 | 28°22'39"RT | 1.5 | 1.5 | 1.5 | 1.5 | WET |  |  | Clear | WIP
407.912
166 | 132/1 | DA+3 | [5 empty] | WET |  |  | Clear | C | C
408.165
167 | AP133 | DC+6 | 18°40'20"LT
[9 empty] | 227.366 | [7 empty] | NHAI 503A Amritsar-Bathinda (CL- 19.400 M) ,NALA,11kV
168 | AP134 | DB+3 | 2°30'44"RT
401.366
169 | AP135 | DB+3 | 12°42'21"RT |  |  |  |  | WET |  |  | Clear | C | C
403.064
170 | 135/1 | DA+6 | [5 empty] | WET |  |  | Clear | C | C
398.933
171 | 135/2 | DA+3 | [5 empty] | WET |  |  | Clear | C | C
419.905
172 | AP136 | DC+3 | 18°07'48"LT
373.389
173 | 136/1 | DA+3 | [5 empty] | WET |  |  | Clear | C | C
419.813
174 | 136/2 | DA+3 | [5 empty] | WET |  |  | Clear | C | C
410.049
175 | 136/3 | DA+0 | [5 empty] | WET |  |  | Clear | C
415.171
176 | 136/4 | DA+3 | [5 empty] | WET |  |  | Clear | WIP
381.971
177 | AP137 | DC+3 | 28°54'25"RT |  |  |  |  | WET |  |  | Clear | WIP
377.623
178 | 137/1 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
354.138
179 | 137/2 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
305.826
180 | AP138 | DD+0 | 31°45'48"LT |  |  |  |  | WET |  |  | Clear | C | C
320.987
181 | 138/1 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
329.946
182 | 138/2 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
294.041
183 | AP139 | DB+0 | 5°55'30"LT |  |  |  |  | WET |  |  | Clear | C
381.669
184 | 139/1 | DA+3 | [5 empty] | WET |  |  | Clear | C | C
427.453
185 | AP140 | DD+18 | 29°55'22"LT
AP140-AP142( Survey Submission/Aprroval Pending)
186 | AP142 | DD+0 | 31°09'11"RT | 1.5 | 1.5 | 1.5 | 1.5
392.505
187 | 142/1 | DA+0 |  | 1.5 | 1.5 | 1.5 | 1.5
392.67
188 | AP143 | DB+0 | 9°07'39"RT | 1.5 | 1.5 | 1.5 | 1.5
292.264
189 | 143/1 | DA+0 |  | 1.5 | 1.5 | 1.5 | 1.5
321.587
190 | 143/2 | DA+0 |  | 1.5 | 1.5 | 1.5 | 1.5
363.882
191 | AP144 | DB +0 | 6°57'45"LT
369.226
192 | 144/1 | DA+3
380.673
193 | 144/2 | DA+0
385.667
194 | 144/3 | DA+6 | [8 empty] | Clear
380.896
195 | 144/4 | DA+0 | [8 empty] | Clear
391.349
196 | AP145 | DB+0 | 13°54'59"RT
330.493
197 | 145/1 | DA+0 | [5 empty] | PS |  |  | Clear
342.106
198 | 145/2 | DA+3 | [5 empty] | PS |  |  | Clear | C | C
394.284
199 | AP146 | DC+0 | 29°42'51"LT |  |  |  |  | WET |  |  | Clear | C | C
245.679
200 | AP147 | DB+0 | [5 empty] | WET |  |  | Clear | C | C
352.93
201 | AP148 | DD+25 | 51°9'48"RT | 2 | 2 | 2 | 2
[9 empty] | 232.301 | [7 empty] | 400kv BN-ASR TRANSMISSION LINE(CL-7.0m)
202 | AP149 | DD+25 | 22°39'7"LT
474.983
203 | AP150 | DC+0 | 24°16'48"LT |  |  |  |  | WET |  |  | Clear | WIP
322.588
204 | 150/1 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
317.884
205 | 150/2 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
297.735
206 | AP151 | DC+0 | 24°58'4"RT
357.249
207 | 151/1 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
353.033
208 | 151/2 | DA+3 | [5 empty] | WET |  |  | Clear | C | C
406.766
209 | AP152 | DD+0 | 39°38'36"LT
392.395
210 | 152/1 | DA+3 | [5 empty] | WET |  |  | Clear | C | C
408.835
211 | 152/2 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
333.09
212 | 152/3 | DA+0 |  | 1 | 1 | 1 | 1
343.683
213 | 152/4 | DA+0 | [5 empty] | WET |  |  | Clear | C
383.599
214 | AP153 | DC+0 | 23°26'55"RT |  |  |  |  | WET |  |  | Clear | C
282.759
215 | 153/1 | DA+0 | [5 empty] | WET |  |  | Clear | C
385.271
216 | 153/2 | DA+3 | [5 empty] | WET |  |  | Clear | WIP
361.361
217 | AP154 | DC+0 | 29°57'53"LT |  |  |  |  | WET |  |  | Clear | C
235.09
218 | AP155 | DD+0 | 34°42'34"RT |  |  |  |  | WET |  |  | Clear | C
351.743
219 | 155/1 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
386.038
220 | 155/2 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
387.695
221 | 155/3 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
389.568
222 | AP156 | DC+0 | 16°34'55"LT |  |  |  |  | WET |  |  | Clear | C | C
376.144
223 | 156/1 | DA+6 | [5 empty] | WET |  |  | Clear | C | C
408
224 | 156/2 | DA+0 | [5 empty] | WET |  |  | Clear | C
365.413
225 | 156/3 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
280.471
226 | 156/4 | DA+0 | [5 empty] | WET |  |  | Clear | C | C
305.689
227 | AP157 | DB+0 | 3°55'39"LT |  |  |  |  | WET |  |  | Clear | C | C
363.359
228 | 157/1 | DA+0 | [5 empty] | WET |  |  | Clear | C
428.543
229 | AP158 | DD+9 | 36°59'34"RT
[9 empty] | 223.002 | [7 empty] | 220kV S/C BBMB jalandhar to Butari(CL-6.3m)
230 | AP159 | DD+18 | 5°51'30"LT
433.784
231 | 159/1 | DA+0
377.777
232 | 159/2 | DA+0
375.892
233 | 159/3 | DA+0
394.944
234 | AP161 | DD+9 | 11°43'56"LT
[9 empty] | 237.641 | [7 empty] | 400kV S/C ASR TO JAL T/L (CL-7.9m)
235 | AP162 | DD+18 | 32°22'36"RT
222.608
236 | AP163 | DB+9 | 4°06'44"LT
[9 empty] | 201.442 | [7 empty] | 132kV S/C, Kartarpur to Rayia(CL-8.1m)
237 | AP164 | DB+3 | 7°26'35"LT
[9 empty] | 228.755 | [7 empty] | 132kV S/C Jalandhar to Dhilwan Line
238 | AP165 | DB+6 | 1°0'33"LT | 1 | 1 | 1 | 1
[9 empty] | 241.171 | [7 empty] | NH-1(AMRITSAR-DELHI) (CL-12.3m)
239 | AP166 | DB+6 | 7°22'22"RT
265.922
240 | AP167 | DD+9 | 0°43'25"RT
[9 empty] | 215.817 | [7 empty] | RAILWAY CROSSING (CL-21.8m) &2 nos -11 kv line
241 | AP168 | DD+9 | 5°57'13"LT
84.9301

## Sheet7 (hidden)
S.No | Loc | TOT | RC | RC | RC | RC
1 | AP144 | DB+0
2
3
4 |  |  | 1 | 1 | 1 | 1
5
6 | AP145 | DB+0 | 2 | 2 | 2 | 2
7
8
9
10
11
12 | [6 empty] | Hussain
13 | [6 empty] | Hussain
14 | [6 empty] | Hussain
15 | [6 empty] | Hussain
16
17
18
19 |  |  | 1 | 1 | 1 | 1
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46 | AP66 | DC+0
47 | AP67 | DD+0
48 | 67/1 | DA+0
49 | 67/2 | DA+0
50 | 67/3 | DA+0
51 | AP68 | DB+0
52
53
54
55 | 69/3 | DA+0
56 | AP70 | DC+3

## Foundation -JS Line- Punjab
KEC INTERNATIONAL LIMITED | [13 empty] | Date: | 2026-02-16
400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5-Punjab Portion
FOUNDATION
S.No | Loc No. | Tower Type | Classification | Conc Volume | Start Date | Foundation |  |  |  |  | Completion Date | FDN Status | Earthing | Gang Name | Gang Strength | Remark
[6 empty] | Excavation | Stub Setting | PCC | Rebar Placing | RCC
1 | 90/1 | DA+3 | WET | 36.109 | 2025-09-25 | 2026-01-11 | 2026-01-11 | 2026-01-11 | 2026-01-11 | 2026-01-11 | 2026-01-11 | Completed |  | Anchal Singh | 25 | 3 pits casting completed on 24.10.25. After clearence of ROW on 09.01.26, Work resumed since 10.01.26 in the 4th pit and work completed on 11.01.26
2 | 117/1 | DA+0 | WET |  | 2025-10-13 | 2025-10-18 | 2025-10-18 | 2025-10-19 | 2025-10-19 | 2025-10-20 | 2025-10-20 | Completed |  | Sakrala Material | 10
3 | 92/3 | DA+0 | WET |  | 2025-10-16 | 2025-10-25 | 2025-10-25 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-27 | Completed |  | MS Constructions | 9
4 | 92/2 | DA+6 | WET |  | 2025-10-19 | 2025-10-25 | 2025-10-27 | 2025-10-27 | 2025-10-28 | 2025-10-28 | 2025-10-28 | Completed |  | MS Constructions | 10
5 | 71/3 | DA+6 | WET |  | 2025-10-17 | 2025-10-19 | 2025-10-20 | 2025-10-20 | 2025-10-21 | 2025-10-23 | 2025-10-23 | Completed |  | Ramesh | 12
6 | 72/2 | DA+6 | WET |  | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-25 | 2025-10-26 | 2025-10-28 | 2025-10-28 | Completed |  | Ramesh | 12
7 | 117/3 | DA+0 | WET |  | 2025-10-23 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-29 | 2025-10-29 | 2025-10-29 | Completed | 2025-11-04 | Sakrala Material | 10
8 | 74/0 | DB+0 | WET |  | 2025-10-25 | 2025-10-27 | 2025-10-31 | 2025-10-31 | 2025-11-01 | 2025-11-06 | 2025-11-06 | Completed | 2025-11-12 | Ramesh | 16
9 | 72/0 | DB+3 | WET |  | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-09 | 2025-11-09 | Completed | 2025-11-12 | Ramesh
10 | 89/1 | DA+3 | WET |  | 2025-10-26 | 2025-10-30 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | Completed | 2025-11-07 | Anchal Singh | 23
11 | 93/1 | DA+0 | WET |  | 2025-10-27 | 2025-10-28 | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-31 | 2025-10-31 | Completed | 2025-11-09 | MS Constructions | 19
12 | 117/2 | DA+3 | WET |  | 2025-10-26 | 2025-10-28 | 2025-11-01 | 2025-11-01 | 2025-11-02 | 2025-11-04 | 2025-11-04 | Completed | 2025-11-06 | Sakrala Material | 20
13 | 118/1 | DA+0 | WET |  | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-06 | 2025-11-06 | Completed | 2025-11-08 | Sakrala Material
14 | 95/2 | DA+0 | WET |  | 2025-10-29 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-06 | 2025-11-08 | 2025-11-08 | Completed | 2025-11-09 | Ikrar/MS Hussain | 13
15 | 95/3 | DA+0 | WET |  | 2025-10-31 | 2025-11-08 | 2025-11-09 | 2025-11-09 | 2025-11-09 | 2025-11-10 | 2025-11-10 | Completed | 2025-11-11 | Ikrar/MS Hussain
16 | 93/2 | DA+0 | WET |  | 2025-10-29 | 2025-10-30 | 2025-11-02 | 2025-11-02 | 2025-11-02 | 2025-11-04 | 2025-11-04 | Completed |  | MS Constructions | 19
17 | 92/1 | DA+3 | WET |  | 2025-11-03 | 2025-11-07 | 2025-11-09 | 2025-11-09 | 2025-11-10 | 2025-11-10 | 2025-11-10 | Completed | 2025-11-14 | MS Constructions
18 | 97/2 | DA+0 | WET |  | 2025-10-30 | 2025-11-02 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-12 | 2025-11-12 | Completed | 2025-11-16 | Md. Latif | 25
19 | 97/1 | DA+0 | WET |  | 2025-11-02 | 2025-11-06 | 2025-11-10 | 2025-11-11 | 2025-11-11 | 2025-11-13 | 2025-11-13 | Completed | 2025-11-16 | Md. Latif
20 | AP90 | DD+0 | WET |  | 2025-11-01 | 2025-11-17 | 2025-11-18 | 2025-11-18 | 2025-11-20 | 2025-11-22 | 2025-11-22 | Completed | 2025-11-19 | Anchal Singh | 25
21 | AP118 | DC+0 | WET |  | 2025-11-07 | 2025-11-12 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-16 | 2025-11-16 | Completed | 2025-11-19 | Sakrala Material | 20
22 | 131/1 | DA+3 | WET |  | 2025-11-06 | 2025-12-12 | 2025-12-12 | 2025-11-14 | 2025-11-14 | 2025-11-15 | 2025-11-15 | Completed | 2025-11-21 | TCC Construction | 16
23 | 95/1 | DA+0 | WET |  | 2025-11-09 | 2025-11-13 | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-15 | 2025-11-15 | Completed | 2025-11-16 | Ikrar/MS Hussain | 20
24 | AP93 | DC+0 | WET |  | 2025-11-10 | 2025-11-17 | 2025-11-18 | 2025-11-18 | 2025-11-18 | 2025-11-19 | 2025-11-19 | Completed | 2025-12-01 | MS Constructions | 19
25 | 76/2 | DA+3 | WET |  | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-14 | 2025-11-14 | Completed | 2025-11-15 | Ramesh | 16
26 | 97/3 | DA+3 | WET |  | 2025-11-11 | 2025-11-12 | 2025-11-15 | 2025-11-18 | 2025-11-18 | 2025-11-20 | 2025-11-20 | Completed | 2025-11-21 | Md. Latif | 25
27 | AP98 | DB+3 | WET |  | 2025-11-12 | 2025-11-19 | 2025-11-21 | 2025-11-21 | 2025-11-23 | 2025-11-24 | 2025-11-24 | Completed | 2025-12-01 | Md. Latif
28 | 95/4 | DA+0 | WET |  | 2025-11-13 | 2025-11-18 | 2025-11-19 | 2025-11-19 | 2025-11-20 | 2025-11-20 | 2025-11-20 | Completed | 2025-11-21 | Ikrar | 11
29 | 76/1 | DA+0 | WET |  | 2025-11-14 | 2025-11-15 | 2025-11-15 | 2025-11-16 | 2025-11-16 | 2025-11-18 | 2025-11-18 | Completed | 2025-11-19 | Ramesh | 16
30 | 131/3 | DA+3 | WET |  | 2025-11-15 | 2025-11-16 | 2025-11-18 | 2025-11-18 | 2025-11-19 | 2025-11-19 | 2025-11-19 | Completed | 2025-11-21 | TCC Construction | 16
31 | AP116 | DCT+0 | FS |  | 2025-11-16 | 2025-11-27 | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-11-30 | 2025-11-30 | Completed | 2025-12-01 | Sakrala Material | 20
32 | AP96 | DC+0 | WET |  | 2025-11-17 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-29 | Completed | 2025-12-01 | MS Hussain | 12
33 | AP77 | DB+3 | WET |  | 2025-11-18 | 2025-12-10 | 2025-12-11 | 2025-12-11 | 2025-12-11 | 2025-12-13 | 2025-12-13 | Completed | 2025-12-14 | Ramesh | 16 | 2 pits casting completed on 22.11.2025 Balance 2 pits under ROW till 08.12.2025 Work resumed from 09.12.2025 & Completed on 13.12.25
34 | 131/2 | DA+3 | WET |  | 2025-11-19 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-23 | 2025-11-24 | 2025-11-24 | Completed | 2025-11-26 | TCC Construction | 16
35 | AP94 | DB+0 | WET |  | 2025-11-20 | 2025-11-24 | 2025-11-25 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-27 | Completed | 2025-12-05 | MS Constructions | 19
36 | 98/1 | DA+3 | WET |  | 2025-11-20 | 2025-11-23 | 2025-11-25 | 2025-11-25 | 2025-11-26 | 2025-11-26 | 2025-11-26 | Completed | 2025-11-26 | Md. Latif | 12
37 | 103/1 | DA+0 | WET |  | 2025-11-22 | 2025-11-26 | 2025-11-27 | 2025-11-27 | 2025-11-28 | 2025-11-28 | 2025-11-28 | Completed | 2025-11-28 | Ikrar | 11
38 | 131/4 | DA+0 | WET |  | 2025-11-22 | 2025-11-27 | 2025-11-28 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-11-30 | Completed | 2025-12-01 | TCC Construction | 16
39 | AP87 | DB+9 | PS |  | 2025-11-21 | 2025-11-27 | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-11-30 | 2025-11-30 | Completed | 2025-12-03 | Anchal Singh | 25
40 | AP99 | DB+0 | WET |  | 2025-11-23 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-28 | 2025-11-30 | 2025-11-30 | Completed | 2025-12-10 | Md. Latif | 15
41 | AP75 | DB+9 | FS |  | 2025-11-25 | 2025-11-28 | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-12-01 | 2025-12-01 | Completed | 2025-12-01 | Ramesh | 16
42 | 82/2 | DA+3 | WET |  | 2025-11-26 | 2025-12-02 | 2025-12-03 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-05 | Completed | 2025-12-08 | Anchal Singh | 25
43 | AP100 | DC+3 | WET |  | 2025-11-26 | 2025-12-03 | 2025-12-05 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-07 | Completed | 2025-12-10 | Md. Latif | 13
44 | AP117 | DB+0 | WET |  | 2025-11-29 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-06 | 2205-12-09 | 2025-12-09 | Completed | 2025-12-09 | Sakrala Material | 20
45 | AP95 | DC+3 | WET |  | 2025-11-29 | 2025-12-05 | 2025-12-05 | 2025-12-06 | 2025-12-06 | 2025-12-07 | 2025-12-07 | Completed | 2025-12-07 | MS Constructions | 19
46 | 104/1 | DA+3 | WET |  | 2025-11-30 | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-04 | 2025-12-04 | 2025-12-04 | Completed | 2025-12-05 | MS Hussain | 12
47 | AP103 | DD+0 | WET |  | 2025-12-02 | 2025-12-15 | 2025-12-16 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-18 | Completed | 2025-12-12 | Ikrar | 11
48 | 99/1 | DA+9 | WET |  | 2025-12-01 | 2025-12-03 | 2025-12-05 | 05-12-205 | 2025-12-05 | 2025-12-06 | 2025-12-06 | Completed | 2025-12-11 | Md. Latif | 12
49 | 82/1 | DA+0 | WET |  | 2025-12-03 | 2025-12-05 | 2025-12-08 | 2025-12-09 | 2025-12-09 | 2025-12-10 | 2025-12-10 | Completed | 2025-12-11 | Anchal Singh | 25
50 | 76/3 | DA+3 | WET |  | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-04 | 2025-12-06 | 2025-12-06 | Completed | 2025-12-07 | Ramesh | 16
51 | 77/2 | DB+0 | WET |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-10 | 2025-12-10 | Completed | 2025-12-12 | Ramesh | 16
52 | AP106 | DD+6 | WET |  | 2025-12-05 | 2025-12-11 | 2025-12-12 | 2025-12-12 | 2025-12-13 | 2025-12-15 | 2025-12-15 | Completed | 2025-12-17 | Md. Latif | 25
53 | AP104 | DB+0 | WET |  | 2025-12-05 | 2025-12-11 | 2025-12-11 | 2025-12-12 | 2025-12-12 | 2025-12-13 | 2025-12-13 | Completed | 2025-12-15 | MS Hussain | 12
54 | AP135 | DB+3 | WET |  | 2025-12-05 | 2025-12-07 | 2025-12-09 | 2025-12-09 | 2025-12-12 | 2025-12-16 | 2025-12-16 | Completed | 2025-12-20 | Ram Sadotra | 40
55 | 135/1 | DA+6 | WET |  | 2025-12-07 | 2025-12-09 | 2025-12-11 | 2025-12-12 | 2025-12-14 | 2025-12-29 | 2025-12-29 | Completed | 2026-01-03 | Ram Sadotra | 40 | Since farmers left water in the field work hampered since 14.12.25. Work restarted from 28.12.25 and completed on 29.12.25
56 | 85/1 | DA+9 | WET |  | 2025-12-06 | 2025-12-12 | 2025-12-14 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-16 | Completed | 2025-12-21 | Anchal Singh | 25
57 | 106/1 | DA+0 | WET |  | 2025-12-10 | 2025-12-14 | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-17 | 2025-12-17 | Completed | 2025-12-22 | Md. Latif | 25
58 | 136/1 | DA+3 | WET |  | 2025-12-11 | 2025-12-12 | 2025-12-15 | 2025-12-15 | 2025-12-17 | 2025-12-19 | 2025-12-19 | Completed | 2025-12-24 | Ram Sadotra | 40
59 | 130/2 | DA+0 | WET |  | 2025-12-12 | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-17 | 2025-12-17 | Completed | 2025-12-20 | MS Constructions | 20
60 | AP85 | DB+0 | WET |  | 2025-12-12 | 2025-12-18 | 2025-12-20 | 2025-12-20 | 2025-12-23 | 2025-12-24 | 2025-12-24 | Completed | 2025-12-26 | Anchal Singh | 25
61 | 135/2 | DA+3 | WET |  | 2025-12-13 | 2025-12-14 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-21 | 2025-12-21 | Completed | 2025-12-25 | Ram Sadotra | 40
62 | 77/1 | DA+3 | WET |  | 2025-12-13 | 2025-12-14 | 2025-12-14 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-16 | Completed | 2025-12-18 | Ramesh | 16
63 | 102/1 | DA+6 | WET |  | 2025-12-14 | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-18 | 2025-12-18 | Completed | 2025-12-18 | MS Hussain | 12
64 | 130/1 | DA+0 | WET |  | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-19 | 2025-12-20 | 2025-12-20 | Completed | 2025-12-20 | MS Constructions | 20
65 | AP80 | DD+0 | PS |  | 2025-12-16 | 2025-12-21 | 2025-12-22 | 2025-12-22 | 2025-12-23 | 2025-12-25 | 2025-12-25 | Completed | 2025-12-26 | Ramesh | 16
66 | 116/1 | DA+0 | WET |  | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-20 | 2025-12-20 | Completed | 2025-12-21 | Md. Latif | 25
67 | 156/4 | DA+0 | WET |  | 2025-12-18 | 2025-12-21 | 2025-12-21 | 2025-12-25 | 2025-12-25 | 2025-12-26 | 2025-12-26 | Completed | 2026-01-03 | Md. Latif | 25
68 | 139/1 | DA+0 | WET |  | 2025-12-19 | 2025-12-21 | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-24 | 2025-12-24 | Completed | 2025-12-27 | Ram Sadotra | 40
69 | 69/3 | DA+0 | WET |  | 2025-12-19 | 2026-01-04 | 2026-01-04 | 2026-01-05 | 2026-01-05 | 2026-01-07 | 2026-01-07 | Completed | 2026-01-09 | Abdul Jabbar | 12
70 | 131/6 | DA+9 | WET |  | 2025-12-20 | 2025-12-21 | 2025-12-22 | 2025-12-23 | 2025-12-23 | 2025-12-24 | 2025-12-24 | Completed | 2025-12-26 | MS Constructions | 20
71 | 150/1 | DA+0 | WET |  | 2025-12-21 | 2025-12-26 | 2025-12-26 | 2025-12-26 | 2025-12-26 | 2025-12-27 | 2025-12-27 | Completed | 2025-12-31 | Ms. Hussain | 13
72 | 138/1 | DA+0 | WET |  | 2025-12-21 | 2025-12-22 | 2025-12-23 | 2025-12-23 | 2025-12-24 | 2025-12-26 | 2025-12-26 | Completed | 2025-12-31 | Ram Sadotra | 40
73 | 137/1 | DA+0 | WET |  | 2025-12-21 | 2025-12-22 | 2025-12-26 | 2025-12-26 | 2025-12-27 | 2025-12-28 | 2025-12-28 | Completed | 2026-01-09 | Ram Sadotra | 40
74 | 131/5 | DA+3 | WET |  | 2025-12-23 | 2025-12-24 | 2025-12-26 | 2025-12-26 | 2025-12-26 | 2025-12-27 | 2025-12-27 | Completed | 2025-12-27 | MS Constructions | 20
75 | AP146 | DC+0 | WET |  | 2025-12-23 | 2026-01-03 | 2026-01-03 | 2026-01-04 | 2026-01-04 | 2026-01-05 | 2026-01-05 | Completed | 2026-01-05 | Ikrar | 11
76 | AP102 | DB+0 | WET |  | 2025-12-23 | 2025-12-28 | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29 | Completed | 2026-01-02 | Md. Latif | 25
77 | 80/1 | DB+3 | WET |  | 2025-12-24 | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-30 | 2025-12-30 | 2025-12-30 | Completed | 2025-12-31 | Ramesh | 16
78 | 86/1 | DA+3 | WET |  | 2025-12-24 | 2025-12-28 | 2025-12-29 | 2025-12-29 | 2025-12-30 | 2025-12-30 | 2025-12-30 | Completed | 2025-12-31 | Anchal Singh | 25
79 | 156/3 | DA+0 | WET |  | 2025-12-24 | 2025-12-28 | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-30 | 2025-12-30 | Completed | 2026-01-07 | Md. Latif | 25
80 | 150/2 | DA+0 | WET |  | 2025-12-27 | 2026-01-02 | 2026-01-03 | 2026-01-03 | 2026-01-03 | 2026-01-04 | 2026-01-04 | Completed | 2026-01-03 | Ms. Hussain | 13
81 | 132/1 | DA+3 | WET |  | 2025-12-27 | 2025-12-29 | 2025-12-30 | 2025-12-30 | 2025-12-30 | 2025-12-31 | 2025-12-31 | Completed | 2026-01-02 | MS Constructions | 20
82 | 138/2 | DA+0 | WET |  | 2025-12-27 | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-31 | 2025-12-31 | 2025-12-31 | Completed | 2026-01-21 | Ram Sadotra | 40
83 | 156/2 | DA+0 | WET |  | 2025-12-28 | 2025-12-29 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-08 | 2026-01-08 | Completed |  | Md. Latif | 25
84 | 155/1 | DA+0 | WET |  | 2025-12-31 | 2026-01-07 | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-09 | 2026-01-09 | Completed | 2026-02-13 | Md. Latif | 25
85 | AP131 | DC+0 | WET |  | 2026-01-05 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-11 | Completed | 2026-01-09 | MS Constructions | 20
86 | 90/2 | DA+0 | WET |  | 2026-01-04 | 2026-01-10 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-16 | 2026-01-16 | Completed | 2026-01-17 | Anchal Singh | 25
87 | AP115 | DB+0 | WET |  | 2026-01-05 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-22 | 2026-01-22 | Completed | 2026-02-22 | Sakrala Material | 12
88 | 152/1 | DA+3 | WET |  | 2026-01-05 | 2026-01-07 | 2026-01-09 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-11 | Completed | 2026-02-03 | Ram Sadotra | 40
89 | 137/2 | DA+0 | WET |  | 2026-01-05 | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-10 | Completed | 2026-01-20 | Ram Sadotra | 40
90 | 87/2 | DA+3 | WET |  | 2026-01-07 | 2026-01-11 | 2026-01-11 | 2026-01-11 | 2026-01-11 | 2026-01-12 | 2026-01-12 | Completed | 2026-01-13 | Ramesh | 16
91 | 145/2 | DA+3 | PS |  | 2026-01-07 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-20 | 2026-01-20 | Completed | 2026-01-20 | Ikrar | 11
92 | AP147 | DB+0 | WET |  | 2026-01-07 | 2026-01-14 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | Completed | 2026-01-16 | Ms. Hussain | 13
93 | AP154 | DC+0 | WET |  | 2026-01-08 | 2026-01-14 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-18 | 2026-01-18 | Completed |  | Md. Latif | 25
94 | 152/2 | D+0 | WET |  | 2026-01-08 | 2026-01-12 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-16 | 2026-01-16 | Completed | 2026-02-03 | Ram Sadotra | 40
95 | AP138 | DD+0 | WET |  | 2026-01-08 | 2026-01-16 | 2026-01-17 | 2026-01-17 | 2026-01-18 | 2026-01-20 | 2026-01-20 | Completed | 2026-01-20 | Ram Sadotra | 40
96 | AP157 | DB+0 | WET |  | 2026-01-09 | 2026-01-13 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-17 | 2026-01-17 | Completed | 2026-01-20 | Md. Latif | 25
97 | AP129 | DB+9 | PS |  | 2026-01-11 | 2026-01-16 | 2026-01-17 | 2026-01-17 | 2026-01-19 | 2026-01-20 | 2026-01-20 | Completed | 2026-01-20 | MS Constructions | 20
98 | 69/2 | DA+0 | FS |  | 2026-01-15 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-22 | 2026-01-22 | Completed | 2026-01-25 | Sufiyan Ali | 25
99 | 156/1 | DA+6 | WET |  | 2026-01-17 | 2026-01-19 | 2026-01-20 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-22 | Completed | 2026-02-13 | Md. Latif | 25
100 | 153/0 | DC+0 | WET |  | 2026-01-17 | 2026-02-02 | 2026-02-03 | 2026-02-03 | 2026-02-03 | 2026-02-05 | 2026-02-05 | Completed |  | Ram Sadotra | 40
101 | AP130 | DD+18 | PS |  | 2026-01-18 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-12 | Completed | 2026-02-12 | MS Constructions | 20
102 | AP92 | DD+25 | PS |  | 2026-01-21 | 2026-02-08 | 2026-02-09 | 2026-02-09 | 2026-02-10 | 2026-02-13 | 2026-02-13 | Completed |  | Anchal Singh | 20
103 | 71/2 | DA+6 DA+9 | WET |  | 2026-01-18 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-21 | 2026-01-21 | Completed | 2026-01-22 | Ramesh | 16 | Loc: 71/2 -recasted with DA+9 Started : 11-2-26 & Completed : 12-2-26
104 | 151/1 | DA+0 | WET |  | 2026-01-18 | 2026-01-22 | 2026-01-30 | 2026-01-30 | 2026-01-31 | 2026-01-31 | 2026-01-31 | Completed | 2026-02-01 | Ms. Hussain | 13
105 | 69/1 | DA+0 | FS |  | 2026-01-18 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-27 | 2026-01-27 | Completed |  | Sufiyan Ali | 25
106 | AP139 | DB+0 | WET |  | 2026-01-20 | 2026-02-04 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-06 | 2026-02-06 | Completed |  | Ram Sadotra | 40
107 | 155/2 | DA+0 | WET |  | 2026-01-20 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-30 | 2026-01-30 | 2026-01-30 | Completed | 2026-01-30 | Md. Latif | 25
108 | 115/1 | DA+6 | WET |  | 2026-01-21 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-31 | 2026-01-31 | 2026-01-31 | Completed | 2026-02-02 | Sakrala Material | 20
109 | 136/2 | DA+3 | WET |  | 2026-01-22 | 2026-02-06 | 2026-02-07 | 2026-02-07 | 2026-02-10 | 2026-02-11 | 2026-02-11 | Completed | 2026-02-15 | Ram Sadotra | 40
110 | 155/3 | DA+0 | WET |  | 2026-01-23 | 2026-01-30 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | Completed | 2026-02-05 | Md. Latif | 25
111 | AP97 | DD+3 | WET |  | 2026-01-29 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-08 | Completed | 2026-02-07 | Sufiyan Ali | 20
112 | AP155 | DD+0 | WET |  | 2026-01-31 | 2026-02-06 | 2026-02-07 | 2026-02-07 | 2026-02-09 | 2026-02-09 | 2026-02-09 | Completed |  | Md. Latif | 25
113 | 151/2 | DA+3 | WET |  | 2026-02-03 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-07 | 2026-02-07 | Completed | 2026-02-07 | Ms. Hussain | 13
114 | 152/4 | DA+0 | WET |  | 2026-02-04 | 2024-02-05 | 2026-02-10 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-12 | Completed |  | Ram Sadotra | 40
115 | AP156 | DC+0 | WET |  | 2026-02-05 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-14 | 2026-02-14 | 2026-02-14 | Completed | 2026-02-15 | Md. Latif | 25
116 | 70/2 | DA+0 | PS(SD) |  | 2026-02-05 | [6 empty] | WIP |  | Ramesh | 16 | Pit D - Casting Completed
117 | 153/1 | DA+0 | WET |  | 2026-02-06 | 2026-02-10 | 2026-02-11 | 2026-02-11 | 2026-02-13 | 2026-02-13 | 2026-02-13 | Completed |  | Ram Sadotra | 40
118 | AP111 | DC+0 | WET |  | 2026-02-06 | 2026-02-14 | 2026-02-14 | 2026-02-14 | 2026-02-15 |  |  | WIP |  | Sakrala Material | 20 | Pit A,B,C - Casting Completed Pit D - Casting upto frustrum
119 | 136/3 | DA+0 | WET |  | 2026-02-09 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-15 | Completed |  | Ram Sadotra | 40
120 | 157/1 | DA+0 | WET |  | 2026-02-09 | 2026-02-13 | 2026-02-13 | 2026-02-14 | 2026-02-14 | 2026-02-15 | 2026-02-15 | Completed |  | Md. Latif | 25
121 | AP150 | DC+0 | WET |  | 2026-02-09 | 2026-02-15 | 2026-02-16 | 2026-02-16 |  |  |  | WIP |  | Ms. Hussain | 13 | Pit A,D- Casting Completed Pit C- Casting upto frustrum Pit B -Prop Setting /PCC
122 | AP70 | DC+3 | PS(SD) |  | 2026-02-10 | 2026-02-14 | 2026-02-15 | 2026-02-15 | 2026-02-16 |  |  | WIP |  | Sufiyan Ali-1 | 18 | Pit C,D - Casting Completed Pit B- Casting upto frustrum Pit A - Steel Binding WIP
123 | 136/4 | DA+3 | WET |  | 2026-02-12 | 2026-02-15 | 2026-02-16 | 2026-02-16 | 2026-02-16 |  |  | WIP |  | Ram Sadotra-1 | 25 | Steel Binding
124 | AP68 | DB+0 | PS(SD) |  | 2026-02-10 | [6 empty] | WIP |  | Sufiyan Ali-2 | 15 | Pit A- Casting Complete Pit D- Casting Complete
125 | AP91 | DD+25 | WET |  | 2026-02-12 | [6 empty] | WIP |  | Anchal Singh | 20 | Steel Binding WIP
126 | 153/2 | DA+3 | WET |  | 2026-02-13 | [6 empty] | WIP |  | Ram Sadotra-2 | 20 | Pit B,D - Casting Complete Pit C - Casting upto frustrum Pit A - Excavation WIP
127 | AP79 | DD+9 | WET |  | 2026-02-15 | [6 empty] | WIP |  | Sufiyan Ali-3 | 15 | Steel Binding WIP
128 | 72/1 | DA+3 | WET |  | 2026-02-14 | 2026-02-15 | 2026-02-15 | 2026-02-15 | 2026-02-16 |  |  | WIP |  | Ramesh | 16 | Pit A,D -Casting Completed Pit B,C- Casting upto frustrum
129 | AP137 | DC+3 | WET |  | 2026-02-15 | [6 empty] | WIP |  | Ram Sadotra-2 | 20 | Pit D - Steel Binding
130 | AP132 | DC+9 1.5m RC | WET |  | 2026-02-15 | [6 empty] | WIP |  | MS Constructions | 20 | Pit B - Casting upto frustrum

## Sheet8 (hidden)
Tower | Structure | Supplied Qty till date | Material DI received and will dispatch in 1 week | Total | Tower | Supplied Qty | Material Under Transit | Total
DA | Basic Tower Body | 87 |  | 87 | DA+0 | 34 |  | 34
| +0MBE | 48 |  | 48 | DA+3 | 39 |  | 39
| +3MBE | 39 |  | 39 | DA+6 | 12 |  | 12
| +6MBE | 12 |  | 12 | DA+9 | 2 |  | 2
| +9MBE | 2 |  | 2 |  |  |  | 0
DB | Basic Tower Body | 13 | 16 | 29 | DB+0 | 10 | 14 | 24
| +0MBE | 11 | 16 | 27 | DB+3 | 2 |  | 2
| +3MBE | 2 |  | 2 | DB+6 | 1 |  | 1
| +6MBE | 1 |  | 1 | DB+9 |  | 2 | 2
| +9MBE |  | 2 | 2 |  |  |  | 0
DC | Basic Tower Body | 5 |  | 5 | DC+0 |  |  | 0
| +0MBE | 2 |  | 2 | DC+3 | 3 |  | 3
| +3MBE | 3 |  | 3 | DC+6 | 2 |  | 2
| +6MBE | 2 |  | 2 | DC+9 |  |  | 0
| +9MBE | [6 empty] | 0
DD | Basic Tower Body | 5 | 19 | 24 | DD+0 |  | 13 | 13
| +0MBE | 2 | 18 | 20 | DD+3 | 3 | 1 | 4
| +3MBE | 3 | 1 | 4 | DD+6 | 2 |  | 2
| +6MBE | 2 |  | 2 | DD+9 |  | 5 | 5
| +9MBE |  | 5 | 5 |  |  |  | 0
| +18MBE | [6 empty] | 0
| +25MBE | [6 empty] | 0
| +30MBE | [6 empty] | 0
Total |  | 110 | 35 | 145 | Total | 110 | 35 | 145

## Foundation -LILO
KEC INTERNATIONAL LIMITED | [12 empty] | Date: | 2026-02-16
LILO Kishtwar - Wind Zone - 2
FOUNDATION
S.No | Loc No. | Tower Type | Classification | Conc Volume | Start Date | Foundation |  |  |  |  | Completion Date | Status | Gang Name | Gang Strength | Remark
[6 empty] | Excavation | Stub Setting | PCC | Rebar Placing | RCC
1 | AP5 | DDM+E3+0 | DFR | 36.109 | 22-12-205 | [6 empty] | WIP | Zaffar | 5 | Excavation Work hampered since 30-12-2025 due to approach issue. Work on hold in LILO line as advised by RKPTL

## ROW Front vs Progress
S.No | Line | ROW Clearence Work Front | Completed | WIP | Balance
1 | Samba-Jalandhar (Jammu Portion) | 72 | 60 | 8 | 4
2 | Samba-Jalandhar (Punjab Portion) | 134 | 118 | 12 | 4
3 | Samba-Kishenpur | 34 | 28 | 6 | 0
4 | LILO-Kishtwar |  |  |  | 0
Total |  | 240 | 206 | 26 | 8

## Foundation -KS Line
KEC INTERNATIONAL LIMITED | [12 empty] | Date: | 2026-02-16
400 kV Kishenpur -Samba T/L
FOUNDATION
S.No | Loc No. | Tower Type | Classification | Start Date | Foundation |  |  |  |  | Completion Date | Status | Earthing | Gang Name | Gang Strength | Remark
[5 empty] | Excavation | Stub Setting | PCC | Rebar Placing | RCC
1 | 85/0 | DC+0 | DFR | 2025-10-01 | 2025-10-15 | 2025-10-23 | 2025-10-23 | 2025-10-24 | 2025-10-26 | 2025-10-26 | Completed | 2025-11-09 | Ankush Sharma | 8
2 | 86/0 | DD+0 | DFR | 2025-10-24 | 2025-11-06 | 2025-11-07 | 2025-11-09 | 2025-11-09 | 2025-11-10 | 2025-11-10 | Completed | 2025-11-11 | Ankush Sharma | 13
3 | 106/0 | DB+0 | DFR | 2025-10-14 | 2025-10-23 | 2025-10-30 | 2025-10-30 | 2025-10-31 | 2025-10-31 | 2025-10-31 | Completed | 2025-11-20 | Naresh | 8
4 | 28/0 | DC+3 | DFR | 2025-10-24 | 2025-10-30 | 2025-11-06 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-08 | Completed | 2025-11-14 | Asish Gupta | 9
5 | 27/0 | DB+3 | DFR | 2025-11-07 | 2025-11-29 | 2025-11-30 | 2025-11-30 | 2025-11-30 | 2025-11-30 | 2025-11-30 | Completed | 2025-12-04 | Asish Gupta | 10
6 | 25/0 | DB+0 | DFR | 2025-11-14 | 2025-11-18 | 2025-11-20 | 2025-11-21 | 22-11-205 | 2025-11-22 | 2025-11-22 | Completed | 2025-12-04
7 | 97/0 | DC-3 | DFR | 2025-10-28 | 2025-11-04 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-29 | 2025-11-29 | Completed | 2025-12-04 | Balveer Singh | 10
8 | AP107 | DC+0 | DFR | 2025-11-02 | 2025-11-18 | 2025-11-20 | 2025-11-21 | 22-11-205 | 2025-11-22 | 2025-11-22 | Completed | 2025-12-03 | Naresh | 12
9 | AP79 | DD+9 | DFR | 2025-11-10 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | Completed | 2025-12-08 | Ankush Sharma | 13
10 | AP33 | DB+6 | DFR | 2025-11-14 | 2025-11-18 | 2025-11-28 | 2025-11-28 | 2025-11-29 | 2025-11-29 | 2025-11-29 | Completed | 2025-12-03 | Akthar | 10
11 | AP29 | DD-3 | WET | 2025-11-23 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-08 | Completed | 2026-01-02 | Asish Gupta | 10
12 | AP32 | DC-3 | WET | 2025-11-26 | 2025-12-17 | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-19 | 2025-12-19 | Completed | 2025-12-21 | Akthar | 10
13 | AP80 | DD+3 | DFR | 2025-11-28 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 2025-12-21 | 2025-12-21 | 2025-12-21 | Completed | 2025-12-23 | Ankush Sharma | 13
14 | AP105 | DD+0 | DFR | 2025-12-02 | 2025-12-09 | 2025-12-15 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-17 | Completed | 2025-12-18 | Naresh | 12
15 | AP96 | DC-3 | DFR | 2025-12-03 | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-21 | 2025-12-21 | 2025-12-21 | Completed | 2025-12-26 | Balveer Singh | 10
16 | 30/1 | DA+0 | WET | 2025-12-08 | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-17 | 2025-12-17 | Completed | 2026-01-03 | Asish Gupta | 10
17 | AP43 | DC-3 | DFR | 2025-12-21 | 2025-12-28 | 2025-12-30 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | Completed | 2026-01-02 | Akthar | 10
18 | AP31 | DB+9 | WET | 2025-12-21 | 2025-12-25 | 2025-12-26 | 2025-12-26 | 2025-12-27 | 2025-12-28 | 2025-12-28 | Completed | 2026-01-10 | Asish Gupta | 10
19 | AP51 | DB+0 | DFR | 2025-12-25 | 2025-12-28 | 2026-01-03 | 2026-01-04 | 2026-01-04 | 2026-01-05 | 2026-01-05 | Completed | 2026-01-08 | Balveer Singh | 10
20 | AP52 | DC-3 | DFR | 2025-12-25 | 2025-12-28 | 2025-12-30 | 2025-12-30 | 2025-12-30 | 2026-01-03 | 2026-01-03 | Completed | 2026-01-04 | Naresh | 12
21 | AP54 | DD+9 | DFR | 2025-12-25 | 2025-12-31 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-07 | 2026-01-07 | Completed | 2026-01-12 | Ankush Sharma | 13
22 | AP30 | DD+0 | WET | 2025-12-28 | 2026-01-09 | 2026-01-11 | 2026-01-11 | 2026-01-11 | 2026-01-12 | 2026-01-12 | Completed |  | Asish Gupta | 10
23 | AP44 | DD-3 | DFR | 2025-12-29 | 2026-01-12 | 2026-01-16 | 2026-01-17 | 2026-01-17 | 2026-01-19 | 2026-01-19 | Completed | 2026-01-21 | Akthar | 10
24 | AP26 | DB-3 | DFR | 2026-01-11 | 2026-01-19 | 2026-01-19 | 2026-01-20 | 2026-01-20 | 2026-01-21 | 2026-01-21 | Completed | 2026-01-22 | Asish Gupta | 10
25 | AP81 | DD+18 | WET | 2026-01-12 | [6 empty] | WIP |  | Ankush Sharma | 13 | Pit A- Casting Completed Pit B - Prop Setting/PCC
26 | AP8 | DD+0 | DRY | 2026-01-15 | 2026-02-03 | 2026-02-07 | 2026-02-07 | 2026-02-07 | 2026-02-10 | 2026-02-10 | Completed | 2026-02-11 | Kulbhushan | 6
27 | AP108 | DC+0 | DFR | 2026-01-17 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | Completed |  | Naresh | 12
28 | AP27A | DB+6 | FS | 2026-01-18 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | Completed |  | Asish Gupta | 10
29 | AP39 | DB+0 | DFR | 2026-01-19 | [6 empty] | WIP |  | Akthar | 10 | Prop Setting/PCC Work on hold due to forest area
30 | 8/2 | DB+3 | DFR | 2026-01-22 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | Completed |  | Md. Farooq | 6
31 | AP9 | DB+9 | DFR | 2026-02-03 | [8 empty] | Asish Gupta | 10 | Work on hold due to forest area
32 | AP11 | DD+18 | DFR | 2026-02-03 | [8 empty] | Akthar | 10 | Pit C,D- Casting Completed
33 | 8/1 | DB+3 | DFR | 2026-02-05 | [8 empty] | Kulbhushan | 6 | Pit C - Casting Completed Pit D- Prop Setting/PCC
34 | 26/1 | DB | DFR | 2026-02-07 | [8 empty] | Asish Gupta | 10 | Pit A,B - Casting upto frustrum
35 | 9/1 | DD+18 | DFR | 2026-02-10 | [8 empty] | Asish Gupta | 10 | Steel Binding WIP
36 | AP53 | DC | DFR | 11-02-025 | [8 empty] | DS Constr | 10 | Pit B - Casting upto frustrum Pit A- Steel Binding WIP

## Manpower
[11 empty] | Date | 2026-02-16
MAN POWER & MACHINERY RESOURCES
Type of Staff | M/s. KEC | Manpower in Gangs |  | Line | Qty | Manpower in Gangs |  | Line | Qty | CIVIL Machinery & Plant | Working | Idle | Total | Adhshiv | Vishal | Md S | Bal | Zaff | KK | Anchal | Ramesh | MS | Ikrar | Latif | Sakra
|  | Team | Foundation |  |  | Team | Tower Erection |  |  | JCB | 15 |  | 15 |  | 2 |  | 2 |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 10
Project Manager | 1 | 1 | Adhishiv | J-S (Jammu) | 8 | 1 | Raj Labour Supplier | J-S (Jammu) | 22 | Ajax Flori | 8 |  | 8 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 6
ROW Lead | 2 | 2 | Gulam | J-S (Jammu) | 12 | 2 | Anvi Construction | J-S (Jammu) | 21 | Water Tanker | 5 |  | 5 | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 5
ROWOfficer /Patwari | 5 | 3 | Balwanth Singh | J-S (Jammu) | 20 | 3 | Kushboo Devi | J-S (Jammu) | 21 | Dewatering Pump | 13 |  | 13 | [12 empty] | 0
Planning/Cons. Manager | 3 | 4 | Md. Farooq | J-S (Jammu) | 12 | 4 | Saritha Devi | J-S (Punjab) | 30 | Tractor | 11 |  | 11 | 1 | 2 | 5 | 2 | 2 | 1 | [6 empty] | 13
Commercial Incharge/ Officer | 2 | 5 | Pawan Kumar Sharma | J-S (Jammu) | 18 | 5 | Jwala Singh | J-S (Punjab) | 22 | Mixer Machine | 12 |  | 12 | 1 |  |  |  | 1 | 1 | 1 |  | 1 | 1 |  | 1 | 7
Quality Incharge/ Engineer | 7 | 6 | Akram | J-S (Jammu) | 12 | 6 | Punam Kumari | J-S (Punjab) | 34 | Poclain | 11 |  | 11 | 1 | 1 | 1 | 1 | 1 | 1 | 2 |  | 1 | 2 | 1 |  | 12
EHS lead / Officer | 9 | 7 | Thakur Const | J-S (Jammu) | 16 | 7 | ZR CONSTRUCTION | J-S (Punjab) | 30 | Boring Motor | 11 |  | 11 | 1 |  | 1 | 1 | 1 |  |  | 1 |  |  | 1 | 1 | 7
Sr. Surveyor | 3 | 8 | Anchal Singh | J-S (Punjab) | 25 | 8 | Punam Kumari-2 | J-S (Punjab) | 30 |  |  |  |  | 2 | 1 | 4 |  |  | 4 | [6 empty] | 11
Surveyor | 1 | 9 | S Ali | J-S (Punjab) | 25
Asst. Surveyor | 5 | 10 | MS Constructions | J-S (Punjab) | 19
Store Incharge/Asst | 4 | 11 | Hussain | J-S (Punjab) | 13
Section Incharge/Engineer | 5 | 12 | Ikrar | J-S (Punjab)
Line Engineer/Supervisor | 20 | 13 | Md. Latif | J-S (Punjab) | 25
|  | 14 | Ankush Sharma | K-S | 13
|  | 15 | Naresh | K-S | 12
|  | 16 | Ashish Gupta | K-S | 10
|  | 17 | Balveer | K-S | 10
|  | 18 | Akthar | K-S | 9
|  | 19&20 | Ram Sadotra | J-S (Punjab) | 40
|  | 21 | Anil Sharma | J-S (Jammu) | 7
|  | 22 | Jabbar | J-S (Punjab) | 12
|  | 23 | Sakrala Building | J-S (Punjab) | 12
|  | 24 | Ramesh | J-S (Punjab) | 16
|  | 25 | Wani Construction | J-S (Jammu) | 6
|  | 26 | Kulbhushan | K-S | 6
Total staff | 67 |  | Total |  | 358 |  | Total |  | 210 | Total Machinery & Plant | 86 |  | 86

## Hindrance
Hindrance Details.
S.No | Line | From | To | Days | Status | Impact Location / Work | Hindrance Details | Remarks
1 | 400 kV D/C Samba-Jalandhar | 2025-07-29 | 2025-07-30 | 2 | Closed | Loc: 29/5 (Foundation) | Due to heavy rains at site excavated Pits (B,C,D) collapsed and site works are hampered
2 | 400 kV D/C Samba-Jalandhar | 2025-08-01 | 2025-08-01 | 1 | Closed | Loc: 29/5 (Foundation) | Due to heavy rains PCC, Steel Binding, RCC work in Pit B
3 | 400 kV D/C Kishenpur-Samba | 2025-08-06 | 2025-08-06 | 1 | Closed | Check Survey Work | Due to landslides, road blocked and at site unable to carry out the survey work
4 | 400 kV D/C Samba-Jalandhar | 2025-08-07 | 2025-08-07 | 1 | Closed | Loc: 29/5 (Foundation) | Due to heavy rains at site , RCC work hampered in Pit A
5 | 400 kV D/C Samba-Jalandhar | 2025-08-09 | 2025-08-09 | 1 | Closed | Loc: 29/5 (Foundation) | Due to heavy rains at site , RCC work hampered in Pit C
6 | 400 kV D/C Samba-Jalandhar | 2025-08-12 | 2025-08-14 | 3 | Closed | Loc: 29/4 (Foundation) | Due to heavy rains for continous 3 days site excavation work hampered
7 | 400 kV D/C Kishenpur-Samba | 2025-08-12 | 2025-08-12 | 1 | Closed | Check Survey Work | Due to rains /landslides, at site unable to carry out the survey work
8 | 400 kV D/C Kishenpur-Samba | 2025-08-16 | 2025-08-18 | 3 | Closed | Check Survey Work | Due to rains/ landslides , at site unable to carry out the survey work
9 | 400 kV D/C Samba-Jalandhar | 2025-08-17 | 2025-08-18 | 2 | Closed | Loc: 29/4 (Foundation) | Due to heavy rains for continous 2 days site Stub Setting , PCC , Steel Binding work hampered
10 | 400 kV D/C Samba-Jalandhar | 2025-08-20 | 2025-08-20 | 0.5 | Closed | Loc: 29/4 (Foundation) & Check Survey Work | Due to heavy rains Pit B - Stub Setting, PCC, Pit C - RCC work and also unable to carry out survey work in the line
11 | 400 kV D/C Samba-Jalandhar | 2025-08-23 | 2025-08-28 | 6 | Closed | Loc: 29/4 (Foundation) & Check Survey Work | Due to continous heavy rains / floods for 6 days all site related works are hampered
12 | 400 kV D/C Kishenpur-Samba | 2025-08-23 | 2025-08-28 | 6 | Closed | Check Survey Work | Due to continous heavy rains / floods for 6 days landslides occurred and there is no approach for carrying out site activities and all roads are blocked by local gov. authority
13 | 400 kV D/C Samba-Jalandhar | 2025-08-30 | 2025-09-03 | 5 | Closed | Loc: 29/4 & Loc: 29/3 (Foundation) & Check Survey Work | Due to continous heavy rains / floods for 6 days all site related works are hampered
14 | 400 kV D/C Kishenpur-Samba | 2025-08-29 | 2025-09-11 | 14 | Closed | Check Survey Work | Due to heavy rains / floods landslides occurred and there is no approach for carrying out site activities and all roads are blocked by local gov. authority
15 | LILO-Kishtwar | 2025-08-28 | 2025-09-17 | 20 | Closed | All site works | Due to heavy rains/floods NH closed & also due to local political issues administration issued section 144 , 163
16 | 400 kV D/C Samba-Jalandhar | 2025-09-28 | 2025-09-29 | 2 | Closed | Loc: 90/1 -Foundation Works | Due to farmers issues work on hold
17 | 400 kV D/C Samba-Jalandhar | 2025-10-05 | 2025-10-07 | 3 | Closed | All site works | Due to heavy rains work hampered
18 | 400 kV D/C Kishenpur-Samba | 2025-10-05 | 2025-10-09 | 4 | Closed | All site works | Due to heavy rains work hampered Roads closed by local administration due to landslides
19 | LILO-Kishtwar | 2025-10-05 | 2025-10-07 | 3 | Closed | All site works | Due to heavy rains work hampered
20 | 400 kV D/C Samba-Jalandhar | 2025-10-13 | 2025-10-15 | 3 | Closed | Loc: 90/1 -Foundation Works | Due to farmers issues work on hold for 3 days
21 | 400 kV D/C Samba-Jalandhar | 2025-10-18 | 2025-10-18 | 1 | Closed | Loc: 90/1 -Foundation Works | Due to farmers issues work on hold
22 | 400 kV D/C Samba-Jalandhar | 2025-10-24 | 2025-11-20 | 27 | Closed | Loc: 90/1 - 4th pit works | Due to farmers issues work on hold
23 | 400 kV D/C Samba-Jalandhar | 2025-12-04 | 2025-12-06 | 3 | Closed | Foundation works at loc: 23/4 | Due to ROW - foundation work hampered
24 | 400 kV D/C Samba-Jalandhar | 2025-12-11 | 2025-12-14 | 3 | Closed | Foundation works at loc: 115/0 | Due to ROW - foundation work hampered
25 | 400 kV D/C Samba-Jalandhar | 2025-12-14 | 2025-12-16 | 2 | Closed | Contractor pawan kumar sharma , required further work front , the team is idle since 14-12-2025 after completion of loc: 39/2 on 13.12.25 | Due to ROW - foundation work hampered
26 | 400 kV D/C Kishenpur-Samba | 2025-12-12 | 2025-12-14 | 2 | Closed | Foundation Works at AP32 , due to ROW issues | Due to ROW - foundation work hampered
27 | 400 kV D/C Samba-Jalandhar | 2025-12-19 | 2025-12-20 | 2 | Closed | Contractor Ikrar , required further work front , the team is idle since 19-12-2025 after completion of loc: 103/0 on 18.12.25 | Due to ROW - foundation work hampered
28 | 400 kV D/C Kishenpur-Samba | 2025-12-22 | 2025-12-23 | 2 | Closed | Contractor -Naresh idle for work front since 22-12-2025 at Loc: 52/0 | Due to ROW - foundation work hampered
29 | LILO-Kishtwar | 2025-12-30 | 2026-01-16 | 17 | Closed | Due to approach issue / ROW clearence required for loc: AP5 Foundation work hampered. Work on hold in LILO Line as advised by RKPTL | Due to ROW/ Route diversion
30 | 400 kV D/C Samba-Jalandhar | 2026-01-02 | 2026-01-04 | 2 | Closed | Work front required for vendor Ram Sadotra after completion of Loc: 138/2 . 2 teams engaged by Ram Sadotra - 1 team being mobilized at 152 section from 05-01-2026 & 2nd team required work front | Due to ROW
31 | 400 kV D/C Samba-Jalandhar | 2026-01-23 | 2026-02-01 | 9 | Closed | All site works | Due to heavy rains
32 | 400 kV D/C Samba-Jalandhar Kishenpur Samba Jammu Portion | 2026-02-01 | 2026-02-04 | 3 | Closed | All Foundation Works | Due to non availabilty of cement
33 | 400 kV D/C Samba-Jalandhar Jammu Portion | 2026-02-07 | 2026-02-08 | 2 | Closed | 23/1- Tower Erection Works | Due to ROW

## Planned Vs Actual -FDN (hidden)
KEC INTERNATIONAL LIMITED
400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5
FOUNDATION -Plan Vs Actual
Week | W1 (1-7) | W2 (8-14) | W3 (15-21) | W4 (22-30) | Total
Planned | 1 | 3 | 7 | 8 | 19
Actual | 1 |  | 1 | 1 | 3
Sr. No. | Section | Loc. No. | Tower Type | Classification | Status | Planned | [5 empty] | Actual |  | Remark
|  | Loc. No. | Tower Type | Classification | Status | Start | End | Start | End | Start | End | Start | End
1 | Jammu | 29/3 | DA+0 | Dry | ROW Clear | 2025-08-31 | 2025-09-04 | 2025-09-02 | 2025-09-05 | 2025-09-04 | 2025-09-09 | 2025-08-31 | 2025-09-24
2 |  | AP27 | DB+0 | Wet | ROW Clear | 2025-09-09 | 2025-09-14 | 2025-09-12 | 2025-09-16 | 2025-09-14 | 2025-09-20 | 2025-09-07 | 2025-09-20
3 |  | 30/3 | DA+6 | PS | ROW Clear | 2025-09-20 | 2025-09-24 | 2025-09-22 | 2025-09-25 | 2025-09-24 | 2025-09-27 | 2025-09-30 |  | Boring u/p
4 |  | 29/6 | DA+0 | PS | ROW Clear | 2025-08-28 | 2025-09-02 | 2025-08-30 | 2025-09-03 | 2025-09-02 | 2025-09-07 | 2025-09-26 |  | Excavation u/p
5 |  | AP17 | DC+3 | FS | ROW Clear | 2025-09-07 | 2025-09-12 | 2025-09-10 | 2025-09-14 | 2025-09-12 | 2025-09-18 | 2025-09-10 |  | Excavation u/p
6 |  | AP18 | DC+0 | FS | ROW Clear | 2025-09-18 | 2025-09-23 | 2025-09-21 | 2025-09-25 | 2025-09-23 | 2025-09-29 | 2025-09-11 |  | 1 pit Casting Completed
7 |  | 23/1 | DA+3 | WET | ROW Clear | 2025-09-02 | 2025-09-05 | 2025-09-04 | 2025-09-07 | 2025-09-05 | 2025-09-09 | 2025-09-25 |  | Boring u/p
8 |  | 35/1 | DA+6 |  | Standing Crop | 2025-09-08 | 2025-09-11 | 2025-09-10 | 2025-09-13 | 2025-09-11 | 2025-09-15
9 |  | 37/1 | DA+3 |  | Standing Crop | 2025-09-14 | 2025-09-17 | 2025-09-16 | 2025-09-19 | 2025-09-17 | 2025-09-21
10 |  | 37/2 | DA+3 |  | Standing Crop | 2025-09-20 | 2025-09-23 | 2025-09-22 | 2025-09-25 | 2025-09-23 | 2025-09-27
11 | Punjab | 90/1 | DA+3 | WET | ROW Clear | 2025-09-05 | 2025-09-09 | 2025-09-07 | 2025-09-10 | 2025-09-09 | 2025-09-12 | 2025-09-25 |  | Excavation u/p
12 |  | 117/1 | DA+0 |  | Standing Crop | 2025-09-11 | 2025-09-15 | 2025-09-13 | 2025-09-16 | 2025-09-15 | 2025-09-18
13 |  | 117/3 | DA+0 |  | Standing Crop | 2025-09-20 | 2025-09-24 | 2025-09-22 | 2025-09-25 | 2025-09-24 | 2025-09-28
14 |  | 56/4 | DA+6 |  | Standing Crop | 2025-09-08 | 2025-09-12 | 2025-09-10 | 2025-09-13 | 2025-09-12 | 2025-09-15
15 |  | 56/2 | DA+3 |  | Standing Crop | 2025-09-15 | 2025-09-19 | 2025-09-17 | 2025-09-20 | 2025-09-19 | 2025-09-22
16 |  | 57/1 | DA+0 |  | Standing Crop | 2025-09-22 | 2025-09-26 | 2025-09-24 | 2025-09-27 | 2025-09-26 | 2025-09-29
17 |  | 65/3 | DA+0 |  | Standing Crop | 2025-09-08 | 2025-09-12 | 2025-09-10 | 2025-09-13 | 2025-09-12 | 2025-09-15
18 |  | 65/2 | DA+6 |  | Standing Crop | 2025-09-15 | 2025-09-19 | 2025-09-17 | 2025-09-20 | 2025-09-19 | 2025-09-22
19 |  | 65/5 | DA+0 |  | Standing Crop | 2025-09-22 | 2025-09-26 | 2025-09-24 | 2025-09-27 | 2025-09-26 | 2025-09-29
400 kV Samba- Kishanpur D/C Line(Quad) - Wind Zone - 5
FOUNDATION -Plan Vs Actual
| Week | W1 (1-7) | W2 (8-14) | W3 (15-21) | W4 (22-30) | Total
| Planned |  |  | 2 | 1 | 3
| Actual |  |  |  |  | 0
| Sr. No. | Loc. No. | Tower Type | Classification | Status | Planned | [5 empty] | Actual |  | Remark
[6 empty] | Date | Date | Start | End | Start | End | Start | End
| 1 | AP106 | DB+0 |  |  | 2025-09-04 | 2025-09-15 | 2025-09-07 | 2025-09-12 | 2025-09-09 | 2025-09-15 |  |  | Due to heavy rains/floods & lanslides works hampered
| 2 | AP107 | DC+0 |  |  | 2025-09-14 | 2025-09-25 | 2025-09-17 | 2025-09-22 | 2025-09-19 | 2025-09-25
| 3 | AP97 | DC+0 |  |  | 2025-09-10 | 2025-09-21 | 2025-09-13 | 2025-09-18 | 2025-09-15 | 2025-09-21
LILO Line
FOUNDATION -Plan Vs Actual
| Week | W1 (1-7) | W2 (8-14) | W3 (15-21) | W4 (22-30) | Total
| Planned |  |  | 1 |  | 1
Actual
| Sr. No. | Loc. No. | Tower Type | Classification | Status | Planned | [5 empty] | Actual |  | Remark
|  | Loc. No. | Tower Type | Classification | Status | Start | End | Start | End | Start | End | Start | End
| 1 | AP8 | DDM+0 |  |  | 2025-09-08 | 2025-09-15 | 2025-08-12 | 2025-09-16 | 2025-09-14 | 2025-09-21 |  |  | Due to heavy rains , landslides occurred and road blocked. Hence foundation works will be planned after improvement of weather conditions
Formulas:
End = [Planned]+5
End = [Start]+4
Start = [Planned]+3
Start = [Start]+2

## Supply Status
Samba-Jalandhar (Stubs) | [6 empty] | Samba-Kishenpur (Stubs) | [6 empty] | LILO-Kishtwar (Stubs)
S.No | Stub | Qty asper approved Survey | L2 till Feb'26 | Supplied Qty till date | Supply u/p | Remarks | S.No | Stub | Qty asper approved Survey | L2 till Feb'26 | Supplied Qty till date | Supply u/p | Remarks | S.No | Stub | Qty asper Survey | L2 till Feb'26 | Supplied Qty till date
1 | DA | 201 | 434 | 170 |  |  | 1 | DA | 1 | 129 | 2 |  |  | 1 | DDM | 13 | 14 | 10
2 | DB | 57 |  | 44 |  |  | 2 | DB | 20 |  | 14 |  |  | Total |  | 13 | 14 | 10
3 | DC | 44 |  | 33 |  |  | 3 | DC | 21 |  | 12.75
4 | DD | 63 |  | 40 |  |  | 4 | DD | 29 |  | 18.5
Total |  | 365 | 434 | 287 |  |  | Total |  | 71 | 129 | 47.25
Samba-Jalandhar (Stubs) | [6 empty] | Samba-Kishenpur(Towers) | [6 empty] | LILO-Kishtwar (Tower)
S.No | Tower | Qty asper approved Survey | L2 till Feb'26 | Supplied Qty till date | Supply u/p | Remarks | S.No | Tower | Qty asper approved Survey | L2 till Feb'26 | Supplied Qty till date | Supply u/p | Remarks | S.No | Tower | Qty asper Survey | L2 till Feb'26 | Supplied Qty till date
1 | DA |  | 216 |  |  |  | 1 | DA |  | 100 |  |  |  | 1 | DDM | 13 | 14
| BTB | 201 |  | 168 |  |  |  | BTB | [5 empty] | Total |  | 13 | 14
| 0M | 140 |  | 109 |  |  |  | 0M
| 3M | 61 |  | 59 |  |  |  | 3M
| 6M | 25 |  | 22 |  |  |  | 6M
| 9M | 6 |  | 3 |  |  |  | 9M
2 | DB | [5 empty] | 2 | DB
| BTB | 57 |  | 18 |  |  |  | BTB |  |  | 14
| 0M | 49 |  | 15 |  |  |  | 0M |  |  | 14
| 3M | 8 |  | 3 |  |  |  | 3M
| 6M | 4 |  | 2 |  |  |  | 6M
| 9M | 9 | [5 empty] | 9M |  |  | 4
| -3M | [6 empty] | -3M
| 1-.5M | [6 empty] | 1-.5M
3 | DC | [5 empty] | 3 | DC
| BTB | 44 |  | 25 |  |  |  | BTB |  |  | 12
| 0M | 33 |  | 22 |  |  |  | 0M |  |  | 12
| 3M | 11 |  | 3 |  |  |  | 3M
| 6M | 3 |  | 2 |  |  |  | 6M
| 9M | 6 | [5 empty] | 9M |  |  | 2
| -3M | [6 empty] | -3M
| 1-.5M | [6 empty] | 1-.5M
4 | DD | [5 empty] | 4 | DD
| BTB | 63 |  | 5 |  |  |  | BTB |  |  | 15
| 0M | 57 |  | 2 |  |  |  | 0M |  |  | 15
| 3M | 6 |  | 3 |  |  |  | 3M
| 6M | 3 |  | 2 |  |  |  | 6M
| 9M | 9 | [5 empty] | 9M |  |  | 5
| 18M | 11 | [5 empty] | 18M
| 25M | 10 | [5 empty] | 25M
| 30M | 9 | [5 empty] | 30M
| -3M | [6 empty] | -3M
| 1-.5M | [6 empty] | 1-.5M
Total |  | 365 | 216 | 216 | 0 |  | Total |  | 0 | 100 | 41 | 0

## Material Status-Jammu
CLIENT :- Ratle Kiru Power Transmission Ltd
EXECUTING AGENCY:- KEC INTERNATIONAL LTD.
Name of Project :- ''Transmission Line Portion for “Transmission scheme for evacuation of power from Ratle HEP (850 MW) & Kiru HEP (624 MW): Part-A”
Project Code :- TB605 |  |  | Date :- |  | 2026-02-16
MATERIAL STATUS AS ON DATE
Sl No. | Description of Material | Unit | Receipt of Material | [11 empty] | Material Issued to Site |  |  | Stock Avaialbilty | Remarks
|  |  | Receipt through Direct Supply |  |  | Transfer In |  |  | Transfer Out |  |  | Net Receipt
|  |  | Since Previous | On Date | Total as on Date | Since Previous | On Date | Total as on Date | Since Previous | On Date | Total as on Date | Since Previous | On Date | Total as on Date | Since Previous | On Date | Total as on Date
1 | Cement | Bags
1.1 | (a) OPC43 - Ambuja | Bags | 8697 |  | 8697 | 0 | 0 | 0 | 0 | 0 | 0 | 8697 | 0 | 8697 | 7172 |  | 7172 | 1500
[5 empty] | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Reinforcement Steel | MT
2.1 | (a) Real Ispat | MT | 213.15 | 0 | 213.15 | 0 | 0 | 0 | 18.3727 | 0 | 18.3727 | 194.7773 | 0 | 194.7773 | 68.852 | 0 | 68.852 | 125.9253
| 8 MM | MT | 8.224 | 0 | 8.224 | 0 | 0 | 0 | 0.52438 | 0 | 0.52438 | 7.6996 | 0 | 7.6996 | 1.649 |  | 1.649 | 7.922
| 10 MM | MT | 42.156 | 0 | 42.156 | 0 | 0 | 0 | 0 | 0 | 0 | 42.156 | 0 | 42.156 | 10.271 |  | 10.271 | 52.061
| 12 MM | MT | 117.2 | 0 | 117.2 | 0 | 0 | 0 | 14.7005 | 0 | 14.7005 | 102.4995 | 0 | 102.4995 | 46.856 |  | 46.856 | 133.687
| 16 MM | MT | 18.97 | 0 | 18.97 | 0 | 0 | 0 | 0 | 0 | 0 | 18.97 | 0 | 18.97 | 0.134 |  | 0.134 | 48.517
| 20 MM | MT | 13.325 | 0 | 13.325 | 0 | 0 | 0 | 0.46 | 0 | 0.46 | 12.865 | 0 | 12.865 | 3.82 |  | 3.82 | 54.777
| 25 MM | MT | 13.275 | 0 | 13.275 | 0 | 0 | 0 | 2.6878 | 0 | 2.6878 | 10.5872 | 0 | 10.5872 | 6.122 |  | 6.122 | 55.323
3 | STUBS | Set |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | DA | Set | 80 | 0 | 80 | 0 | 0 | 0 | 34 | 0 | 34 | 46 | 0 | 46 | 13 |  | 13 | 33
3.2 | DB | Set | 34 |  | 34 |  |  |  | 5 |  | 5 | 29 |  | 29 | 3 |  | 3 | 26
3.3 | DC | Set | 32 |  | 32 |  |  |  | 5 |  | 5 | 27 |  | 27 | 6 |  | 6 | 21
3.4 | DD | Set | 25 |  | 25 |  |  |  | 2 |  | 2 | 23 |  | 23 | 1 |  | 1 | 22
3.5 | DDM | Set | 10 |  | 10 |  |  | 0 |  |  | 0 | 10 | 0 | 10 | 0 |  | 0 | 10
4 | Towers | Set |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | DC |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| BTB | Set | 20 |  | 20 | [6 empty] | 20 |  | 20 |  |  | 0 | 20
| 0M | Set | 20 |  | 20 | [6 empty] | 20 |  | 20 |  |  | 0 | 20
3.2 | DA |  |  |  | 0 | [6 empty] | 0 |  | 0 |  |  | 0 | 0
| BTB | Set | 81 |  | 81 | [6 empty] | 81 |  | 81 |  |  | 0 | 81
| 0M | Set | 61 |  | 61 | [6 empty] | 61 |  | 61 |  |  | 0 | 61
| 9M | Set | 1 |  | 1 | [6 empty] | 1 |  | 1 |  |  | 0 | 1
5 | EARTHING |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Counter Poise | Sets | 51 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 51 | 3 | 0 | 3 | 48
5.2 | Pipe Type Earthing | Nos | 130 | 0 | 130 | 0 | 0 | 0 | 46 | 0 | 46 | 84 | 0 | 84 | 4 |  | 4 | 80

## Material Status-Punjab (hidden)
CLIENT :- Ratle Kiru Power Transmission Ltd
EXECUTING AGENCY:- KEC INTERNATIONAL LTD. | [17 empty] | *Material supply updated / Consumption to beupdated
Name of Project :- ''Transmission Line Portion for “Transmission scheme for evacuation of power from Ratle HEP (850 MW) & Kiru HEP (624 MW): Part-A”
Project Code :- TB605 |  |  | Date :- |  | 2026-02-16
MATERIAL STATUS AS ON DATE
Sl No. | Description of Material | Unit | Receipt of Material | [11 empty] | Material Issued to Site |  |  | Balance in stock | Remarks
|  |  | Receipt through Direct Supply |  |  | Transfer In |  |  | Transfer Out |  |  | Net Receipt
|  |  | Since Previous | On Date | Total as on Date | Since Previous | On Date | Total as on Date | Since Previous | On Date | Total as on Date | Since Previous | On Date | Total as on Date | Since Previous | On Date | Total as on Date
1 | Cement | Bags
1.1 | (a) OPC43 - Ambuja | Bags | 6300 |  | 6300 | 0 | 0 | 0 | 0 | 0 | 0 | 6300 | 0 | 6300 | 5539 |  | 5539 | 761
[5 empty] | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Reinforcement Steel
2.1 | (a) Real Ispat | MT | 200.24 | 0 | 200.24 | 18.3727 | 0 | 18.3727 | 0 | 0 | 0 | 218.6127 | 0 | 218.6127 | 59.6538 | 0 | 59.6538 | 158.9588
| 8 MM | MT | 4.08 | 0 | 4.08 | 0.52438 | 0 | 0.52438 | 0 | 0 | 0 | 4.6044 | 0 | 4.6044 | 1.5444 |  | 1.5444 | 3.06
| 10 MM | MT | 27.86 | 0 | 27.86 | 0 | 0 | 0 | 0 | 0 | 0 | 27.86 | 0 | 27.86 | 3.9521 |  | 3.9521 | 23.9079
| 12 MM | MT | 140.46 | 0 | 140.46 | 14.7005 | 0 | 14.7005 | 0 | 0 | 0 | 155.1605 | 0 | 155.1605 | 45.1097 |  | 45.1097 | 110.0508
| 16 MM | MT | 8.03 | 0 | 8.03 | 0 | 0 | 0 | 0 | 0 | 0 | 8.03 | 0 | 8.03 | 0 |  | 0 | 8.03
| 20 MM | MT | 10.06 | 0 | 10.06 | 0.46 | 0 | 0.46 | 0 | 0 | 0 | 10.52 | 0 | 10.52 | 2.4705 |  | 2.4705 | 8.0495
| 25 MM | MT | 9.75 | 0 | 9.75 | 2.6878 | 0 | 2.6878 | 0 | 0 | 0 | 12.4378 | 0 | 12.4378 | 6.5772 |  | 6.5772 | 5.8605
3 | STUBS | Set |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | DA | Set |  | 0 | 0 | 34 | 0 | 34 |  | 0 | 0 | 34 | 0 | 34 | 18 |  | 18 | 16
3.2 | DB | Set |  |  | 0 | 5 |  | 5 |  |  |  | 5 |  | 5 | 2 |  | 2 | 3
3.3 | DC | Set |  |  | 0 | 5 |  | 5 |  |  |  | 5 |  | 5 | 1 |  | 1 | 4
3.4 | DD | Set |  |  | 0 | 2 |  | 2 |  |  |  | 2 |  | 2 | 1 |  | 1 | 1
3.5 | DDM | Set |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
4 | EARTHING |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Counter Poise | Sets |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2 | Pipe Type Earthing | Nos |  | 0 | 0 | 46 | 0 | 46 |  | 0 | 0 | 46 | 0 | 46 | 11 | 0 | 11 | 35

## Earthing (PKG-F) (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Earthing
Sl. No. | Cum S No | Location No. | Tower Type | Classification | Type of Earthing | Earthing | Name of Sub-Contractor | Check list
2023-12-01
1 | 1 | 61/3 | DA+6 | DRY | Pipe Type | 18.12.23 | Manoj Sharma
2 | 2 | 62/4 | DA+3 | DRY | Pipe Type | 31.12.23 | Shakti Const.
2024-01-01
3 | 1 | 59/7 | DA+3 | DRY | Pipe Type | 03.01.24 | Manoj Sharma
4 | 2 | 59/8 | DB+3 | DRY | Pipe Type | 03.01.24 | Manoj Sharma
5 | 3 | 59/9 | DA+3 | DRY | Pipe Type | 03.01.24 | Manoj Sharma
6 | 4 | 59/10 | DA+0 | DRY | Pipe Type | 03.01.24 | Manoj Sharma
7 | 5 | 59/13 | DA+3 | DRY | Pipe Type | 03.01.24 | Manoj Sharma
8 | 6 | 59/14 | DA+6 | DRY | Pipe Type | 03.01.24 | Manoj Sharma
9 | 7 | 59/5 | DA+3 | DFR | Counter Poise | 05.01.24 | om Const.
10 | 8 | 59/6 | DA+3 | DFR | Counter Poise | 05.01.24 | om Const.
11 | 9 | 60/7 | DA+3 | DRY | Pipe Type | 06.01.24 | Imran
12 | 10 | 60/8 | DA+0 | DRY | Pipe Type | 06.01.24 | Imran
13 | 11 | 60/9 | DA+3 | DRY | Pipe Type | 06.01.24 | Imran
14 | 12 | 62/2 | DA+3(RC) | DRY | Pipe Type | 07.01.24 | Shakti Const.
15 | 13 | 62/5 | DA+0 | DRY | Pipe Type | 07.01.24 | Shakti Const.
16 | 14 | 62/6 | DA+3 | DRY | Pipe Type | 07.01.24 | Shakti Const.
17 | 15 | 62/3 | DA+0 | DRY | Pipe Type | 07.01.24 | Shakti Const.
18 | 16 | 62/7 | DA+3 | DRY | Pipe Type | 09.01.24 | Shakti Const.
19 | 17 | 63/6 | DA+3 | DRY | Pipe Type | 12.01.24 | Mahadev Eng
20 | 18 | 65/2 | DA+0 | DRY | Pipe Type | 12.01.24 | Veerteja
21 | 19 | 65/11 | DA+0 | DRY | Pipe Type | 15.1.24 | Bhati Const.
22 | 20 | 65/9 | DA+0 | DRY | Pipe Type | 15.1.24 | Bhati Const.
23 | 21 | 60/5 | DA+3 | DRY | Pipe Type | 16.01.2024 | Manoj Sharma
24 | 22 | 60/6 | DA+0 | DRY | Pipe Type | 16.01.2024 | Manoj Sharma
25 | 23 | 59/12 | DA+6 | DFR | Counter Poise | 16.01.2024 | Manoj Sharma
26 | 24 | 55/4 | DA+0(RC) | SANDY | Pipe Type | 17.01.2024 | Imran
27 | 25 | 64/4 | DA+3 | DRY | Pipe Type | 19.01.24 | Mahadev Eng
28 | 26 | 65/3 | DA+3 | DRY | Pipe Type | 20.01.24 | Veerteja
29 | 27 | 63/1 | DA+3 | DFR | Counter Poise | 27.01.24 | Shakti Const.
30 | 28 | 63/2 | DA+0 | DFR | Counter Poise | 27.01.24 | Shakti Const.
31 | 29 | 64/2 | DA+3 | DRY | Pipe Type | 25.01.24 | Mahadev Eng
32 | 30 | 64/5 | DA+3 | DRY | Pipe Type | 25.01.24 | Mahadev Eng
33 | 31 | 65/4 | DA+0 | DRY | Pipe Type | 25.01.24 | Bhati Const.
34 | 32 | 62/11 | DA+3 | DRY | Pipe Type | 28.01.24 | Shakti Const.
35 | 33 | 55/5 | DA+0 RC | SANDY | Pipe Type | 29.01.24 | Imran
36 | 34 | 55/6 | DA+0 RC | SANDY | Pipe Type | 29.01.24 | Imran
Feb-24
37 | 1 | 64/8 | DA+3 | DRY | Pipe Type | 01.02.24 | Veerteja
38 | 2 | 60/10 | DA+0 | DFR | Counter Poise | 02.02.24 | Manoj Sharma
39 | 3 | 60/11 | DA+3 | DRY | Pipe Type | 02.02.24 | Manoj Sharma
40 | 4 | 61/0 | DB2+0 | DRY | Pipe Type | 02.02.24 | Manoj Sharma
41 | 5 | 61/1 | DA+6 | DFR | Counter Poise | 02.02.24 | Manoj Sharma
42 | 6 | 61/2 | DA+6 | DFR | Counter Poise | 02.02.24 | Manoj Sharma
43 | 7 | 55/3 | DA+0 | SANDY | Pipe Type | 02.02.24 | Imran
44 | 8 | 55/7 | DA+0 | SANDY | Pipe Type | 02.02.24 | Imran
45 | 9 | 52/5 | DA+9 RC | SANDY | Pipe Type | 05.02.24 | Imran
46 | 10 | 52/6 | DA+6 | SANDY | Pipe Type | 08.02.24 | Imran
47 | 11 | 65/6 | DA+0 | DRY | Pipe Type | 09.02.24 | Bhati Const.
48 | 12 | 65/5 | DA+0 | DRY | Pipe Type | 09.02.24 | Bhati Const.
49 | 13 | 67/2 | DA+0 | DRY | Pipe Type | 09.02.24 | Bhati Const.
50 | 14 | 64/10 | DA+3 | DRY | Pipe Type | 11.02.24 | Veerteja Enterprises
51 | 15 | 52/7 | DA+3 RC | SANDY | Pipe Type | 13.02.24 | Imran
52 | 16 | 64/7 | DA+3 | DRY | Pipe Type | 14.02.24 | Mahadev Eng
53 | 17 | 64/6 | DA+0 | DRY | Pipe Type | 14.02.24 | Mahadev Eng
54 | 18 | 64/3 | DA+0 | DRY | Pipe Type | 14.02.24 | Mahadev Eng
55 | 19 | 64/1 | DA+0 | DRY | Counter Poise | 14.02.24 | Mahadev Eng
56 | 20 | 64/0 | DB2+0 | DRY | Counter Poise | 14.02.24 | Mahadev Eng
57 | 21 | 63/8 | DA+3 | DRY | Pipe Type | 14.02.24 | Mahadev Eng
58 | 22 | 63/7 | DA+3 | DRY | Pipe Type | 14.02.24 | Mahadev Eng
59 | 23 | 63/4 | DA+0 | DRY | Pipe Type | 14.02.24 | Shakti Const.
60 | 24 | 57/2 | DA+3 | DRY | Pipe Type | 14.02.24 | om Const.
61 | 25 | 57/4 | DA+0 | SANDY | Pipe Type | 14.02.24 | om Const.
62 | 26 | 57/5 | DA+3 RC | SANDY | Pipe Type | 14.02.24 | om Const.
63 | 27 | 63/0 | DC1+0 | DFR | Counter Poise | 15.02.24 | Shakti Const.
64 | 28 | 63/5 | DA+3 | DFR | Counter Poise | 15.02.24 | Shakti Const.
65 | 29 | 52/10 | DA+9 RC | SANDY | Pipe Type | 17.02.24 | Imran
66 | 30 | 64/9 | DA+3 | DRY | Pipe Type | 20.02.24 | Veerteja Enterprises
67 | 31 | 57/3 | DA+0 | DRY | Pipe Type | 22.02.24 | om Const.
68 | 32 | 57/6 | DA+3 RC | SANDY | Pipe Type | 22.02.24 | om Const.
69 | 33 | 59/3 | DA+3(RC) | DFR | Counter Poise | 22.02.24 | om Const.
70 | 34 | 61/9 | DA+0 | Dry | Pipe Type | 22.02.24 | Manoj Sharma
71 | 35 | 61/8 | DA+6 RC | DRY | Pipe Type | 22.02.24 | Manoj Sharma
72 | 36 | 61/7 | DA+9 RC | Dry | Pipe Type | 22.02.24 | Manoj Sharma
73 | 37 | 61/6 | DA+3 | DRY | Pipe Type | 22.02.24 | Manoj Sharma
74 | 38 | 61/5 | DA+3 | DRY | Pipe Type | 22.02.24 | Manoj Sharma
75 | 39 | 62/10 | DA+0 | DFR | Counter Poise | 22.02.24 | Shakti Const.
76 | 40 | 62/1 | DA+3 RC | SANDY | Pipe Type | 22.02.24 | Shakti Const.
77 | 41 | 62/9 | DA+3 | DFR | Counter Poise | 21.02.24 | Shakti Const.
78 | 42 | 62/8 | DA+0 | DFR | Counter Poise | 21.02.24 | Shakti Const.
79 | 43 | 52/9 | DA+3 | SANDY | Pipe Type | 22.02.24 | Imran
80 | 44 | 52/8 | DA+6 | SANDY | Pipe Type | 22.02.24 | Imran |  | 210
81 | 45 | 63/3 | DA+3 | DFR | Pipe Type | 22.02.24 | Shakti Const.
82 | 46 | 67/1 | DA+0 | DRY | Pipe Type | 13.02.24 | Bhati Const.
83 | 47 | 60/1 | DA+6 | DRY | Pipe Type | 23.02.24 | om Const.
84 | 48 | 53/5 | DA+3 | SANDY | Pipe Type | 25.02.24 | Imran
85 | 49 | 60/2 | DA+3 | DFR | Counter Poise | 26.02.24 | om Const.
March'24
86 | 1 | 60/3 | DA+3 | DFR | Counter Poise | 01.03.24 | Manoj Sharma
87 | 2 | 60/4 | DA+3 | DFR | Counter Poise | 01.03.24 | Manoj Sharma
88 | 3 | 64/11 | DA+3 | DRY | Pipe Type | 06.03.24 | Bhati Const.
89 | 4 | 65/0 | DB1+0 | DRY | Pipe Type | 06.03.24 | Bhati Const.
90 | 5 | 65/1 | DA+0 | DRY | Pipe Type | 07.03.24 | Bhati Const.
91 | 6 | 59/16 | DA+9 | Dry | Pipe Type | 26.02.24 | om Const.
92 | 7 | 59/15 | DA+6 | DRY | Pipe Type | 26.02.24 | om Const.
93 | 8 | 49/2 | DA+3 | SANDY | Pipe Type | 08.03.24 | Veerteja Enterprises
94 | 9 | 61/10 | DA+9 | DRY | Pipe Type | 12.03.24 | Manoj Sharma
95 | 10 | 62/0 | DB2+0 | DRY | Pipe Type | 12.03.24 | Manoj Sharma
96 | 11 | 60/0 | DC1+0 | DRY | Pipe Type | 19.03.24 | Manoj Sharma
97 | 12 | 49/3 | DA+3 | SANDY | Pipe Type | 21.03.24 | Veerteja Enterprises
98 | 13 | 49/5 | DA+3 | SANDY | Pipe Type | 21.03.24 | Shakti Const.
99 | 14 | 61/4 | DA+3 | DRY | Pipe Type | 22.03.24 | Manoj Sharma
100 | 15 | 47/10 | DA+6 | SANDY | Pipe Type | 29.03.24 | Bhati Const.
101 | 16 | 47/9 | DA+3 | SANDY | Pipe Type | 29.03.24 | Bhati Const.
102 | 17 | 47/8 | DA+0 RC | SANDY | Pipe Type | 29.03.24 | Bhati Const.
April'24
103 | 1 | 47/7 | DA+3 | SANDY | Pipe Type | 02.04.24 | Bhati Const.
104 | 2 | 48/0 | DC2+0 | SANDY | Pipe Type | 07.04.24 | Bhati Const.
105 | 3 | 48/1 | DA+9 | SANDY | Pipe Type | 16.04.24 | Veerteja Enterprises
106 | 4 | 50/9 | DA+0 RC | SANDY | Pipe Type | 19.04.24 | Shakti Const.
107 | 5 | 50/10 | DA+0 RC | SANDY | Pipe Type | 19.04.24 | Shakti Const.
108 | 6 | 51/1 | DA+0 RC | SANDY | Pipe Type | 19.04.24 | Shakti Const.
109 | 7 | 50/8 | DA+9 | SANDY | Pipe Type | 20.04.24 | Shakti Const.
110 | 8 | 49/6 | DA+0 | SANDY | Pipe Type | 20.04.24 | Shakti Const.
111 | 9 | 49/4 | DA+3 | SANDY | Pipe Type | 22.04.24 | Veerteja
112 | 10 | 49/1 | DA+0 | SANDY | Pipe Type | 22.04.24 | Veerteja
May'24
113 | 1 | 49/0 | DD45+0 | SANDY | Pipe Type | 03.05.24 | Veerteja Enterprises
114 | 2 | 52/3 | DA+9 | SANDY | Pipe Type | 23.05.24 | SB MEHAR CONST.
115 | 3 | 47/2 | DA+9 | SANDY | Pipe Type | 28.05.24 | Bhati Const.
116 | 4 | 50/7 | DA+0 RC | SANDY | Pipe Type | 31.05.24 | Veerteja Enterprises
117 | 5 | 50/1 | DA+6 | SANDY | Pipe Type | 31.05.24 | Veerteja Enterprises
118 | 6 | 51/2 | DA+0 | SANDY | Pipe Type | 31.05.24 | SB MEHAR CONST. |  | 41.96 | 41.82
June'24
119 | 1 | 50/4 | DA+9 RC | SANDY | Pipe Type | 03.02.24 | Veerteja Enterprises
120 | 2 | 50/2 | DA+9 RC | SANDY | Pipe Type | 04.02.24 | Veerteja Enterprises
121 | 3 | 47/3 | DA+9 RC | SANDY | Pipe Type | 08.06.24 | Bhati Const.
122 | 4 | 47/5 | DA+0 RC | SANDY | Pipe Type | 08.06.24 | Bhati Const.
123 | 5 | 47/6 | DA+3 | SANDY | Pipe Type | 08.06.24 | Bhati Const.
124 | 6 | 51/0 | DC2+0 | SANDY | Pipe Type | 11.06.24 | SB MEHAR CONST.
July'24
125 | 1 | 53/7 | DA+3 | SANDY | Pipe Type | 02.07.24 | Bhati Const.
126 | 2 | 58/0 | DC1+3 | DFR | Counter Poise | 30.07.24 | Bhati Const.
Aug'24
127 | 1 | 50/0 | DB2+0 RC | SANDY | Pipe Type | 03.08.24 | Veerteja Enterprises
128 | 2 | 57/7 | DA+3 | DFR | Counter Poise | 12.08.24 | Bhati Const.
129 | 3 | 59/2 | DA+3 | DFR | Counter Poise | 23.08.24 | Bhati Const.
Sept'24
130 | 1 | 53/8 | DA+3 | Sandy | Pipe Type | 03.09.24 | Bhati Const.
131 | 2 | 53/6 | DA+6 RC | Sandy | Pipe Type | 13.09.24 | Bhati Const.
132 | 3 | 54/1 | DA+3 RC | Sandy | Pipe Type | 14.09.24 | Bhati Const.
133 | 4 | 54/2 | DA+3 | Sandy | Pipe Type | 14.09.24 | Bhati Const.
134 | 5 | 73/0 | DB2+0 | DRY | Pipe Type | 15.09.24 | Shree Shyam Const.
135 | 6 | 73/2 | DA+0 | DRY | Pipe Type | 16.09.24 | Shree Shyam Const.
136 | 7 | 73/1 | DA+0 | DRY | Pipe Type | 19.09.24 | Shree Shyam Const.
137 | 8 | 73/9 | DA+0 | DRY | Pipe Type | 19.09.24 | Shakti Const.
138 | 9 | 73/6 | DA+0 | DRY | Pipe Type | 22.09.24 | Shree Shyam Const.
139 | 10 | 66/0 | DC2+6 | DFR | Pipe Type | 27.09.24 | Bhati Const.
140 | 11 | 69/1 | DA+3 | DRY | Pipe Type | 27.09.24 | Bhati Const.
141 | 12 | 59/11 | DA+6 | DFR | Counter Poise | 28.09.24 | Mahadev Eng
142 | 13 | 50/3 | DA+6 | Sandy | Pipe Type | 29.09.24 | Kalpana Const.
143 | 14 | 50/6 | DA+9 RC | Sandy | Pipe Type | 29.09.24 | Kalpana Const.
Oct'24
144 | 1 | 59/1 | DA+3 RC | DRY | Pipe Type | 01.10.24 | Bhati Const.
145 | 2 | 59/0 | DC2+0 | DRY | Pipe Type | 5.10.24 | Bhati Const.
146 | 3 | 72/2 | DA+0 | DRY | Pipe Type | 07.10.24 | Shree Shyam Const.
147 | 4 | 73/3 | DA+0 | DRY | Pipe Type | 07.10.24 | Awadh Const
148 | 5 | 73/5 | DA+0 | DRY | Pipe Type | 07.10.24 | Shree Shyam Const.
149 | 6 | 73/7 | DA+0 | DRY | Pipe Type | 07.10.24 | Shakti Const.
150 | 7 | 73/8 | DA+3 | DRY | Pipe Type | 07.10.24 | Shakti Const.
151 | 8 | 73/4 | DA+0 | DRY | Pipe Type | 10.10.24 | Shree Shyam Const.
152 | 9 | 67/0 | DC1+9 | DRY | Pipe Type | 10.10.24 | Bhati Const.
153 | 10 | 69/0 | DB2+0 | DFR | Counter Poise | 16.10.24 | Bhati Const.
154 | 11 | 74/0 | DB2+0 | SANDY | Pipe Type | 16.10.24 | Shakti Const.
155 | 12 | 72/3 | DA+3 | DRY | Pipe Type | 18.10.24 | Shree Shyam Const.
156 | 13 | 71/6 | DA+0 | DRY | Pipe Type | 22.10.24 | Shree Shyam Const.
157 | 14 | 71/7 | DA+3 | DRY | Pipe Type | 22.10.24 | Shree Shyam Const.
158 | 15 | 49/7 | DA+0 RC | Sandy | Pipe Type | 23.10.24 | Kalpana Const.
159 | 16 | 59/4 | DA+3 | DFR | Counter Poise | 23.10.24 | Bhati Const.
Nov'24
160 | 1 | 54/0 | DB1+6 | Sandy | Pipe Type | 21.11.24 | Bhati Const.
Dec'24
161 | 1 | 65/8 | DA+0 | DRY | Pipe Type | 06.12.24 | Bhati Const.
162 | 2 | 65/7 | DA+0 | DRY | Pipe Type | 06.12.24 | Bhati Const.
2025-01-25
163 | 1 | 54/3 | DA+6 RC | Sandy | Pipe Type | 07.01.25 | Tantray Construction
164 | 2 | 54/4 | DA+9 RC | Sandy | Pipe Type | 10.01.25 | Tantray Construction
165 | 3 | 50/5 | DA+9 RC | SANDY | Pipe Type | 23.01.25 | om Const.
166 | 4 | 70/1 | DA+3 | DRY | Pipe Type | 25.01.25 | Meer Cost.
167 | 5 | 70/3 | DA+3 | DRY | Pipe Type | 25.01.25 | Meer Cost.
168 | 6 | 70/4 | DA+3 | DRY | Pipe Type | 25.01.25 | Meer Cost.
169 | 7 | 70/0 | DA+3 | DRY | Pipe Type | 25.01.25 | Meer Cost.
170 | 8 | 70/5 | DA+3 | DRY | Pipe Type | 27.01.25 | Meer Cost.
171 | 9 | 70/6 | DA+3 | DRY | Pipe Type | 27.01.25 | Tantray Construction
172 | 10 | 71/0 | DB2+3 | DRY | Pipe Type | 27.01.25 | Tantray Construction
173 | 11 | 71/1 | DA+3 | DRY | Pipe Type | 27.01.25 | Meer Cost.
174 | 12 | 71/2 | DA+3 | DRY | Pipe Type | 27.01.25 | Meer Cost.
175 | 13 | 71/3 | DA+6 | DRY | Pipe Type | 28.01.25 | Meer Cost.
176 | 14 | 71/4 | DA+3 | DRY | Pipe Type | 28.01.25 | Meer Cost.
177 | 15 | 72/0 | DB2+3 | DRY | Pipe Type | 28.01.25 | Meer Cost.
178 | 16 | 47/4 | DA+3 | SANDY | Pipe Type | 29.01.25 | Tantray Construction
179 | 17 | 47/1 | DA+3 | SANDY | Pipe Type | 29.01.25 | Tantray Construction
180 | 18 | 57/1 | DA | SANDY | Pipe Type | 29.01.25 | Meer Cost.
Feb-25
181 | 1 | 70/7 | DA+3 | DRY | Pipe Type | 01.02.25 | Tantray Construction
182 | 2 | 70/8 | DA+3 | DRY | Pipe Type | 01.02.25 | Tantray Construction
183 | 3 | 70/9 | DA+3 | DRY | Pipe Type | 01.02.25 | Tantray Construction
184 | 4 | 70/10 | DA+3 | DRY | Pipe Type | 01.02.25 | Tantray Construction
185 | 5 | 71/5 | DA+3 | DRY | Pipe Type | 01.02.25 | Meer Cost.
186 | 6 | 71/8 | DA+3 | DRY | Pipe Type | 01.02.25 | Meer Cost.
187 | 7 | 72/1 | DA+3 | DRY | Pipe Type | 01.02.25 | Meer Cost.
188 | 8 | 55/8 | DA+6 | SANDY | Pipe Type | 03.02.25 | Meer Cost.
189 | 9 | 55/2 | DA+0 | WFR | Counter Poise | 07.02.25 | Meer Cost.
190 | 10 | 52/0 | DC2+0 RC | Sandy | Pipe Type | 17.02.25 | Tantray Construction
191 | 11 | 52/1 | DA+6 RC | Sandy | Pipe Type | 17.02.25 | Tantray Construction
192 | 12 | 52/2 | DA+6 RC | Sandy | Pipe Type | 17.02.25 | Tantray Construction
193 | 13 | 52/4 | DA+9 RC | Sandy | Pipe Type | 17.02.25 | Tantray Construction
194 | 14 | 44/3 | DA+0 RC | SANDY | Pipe Type | 18.02.25 | Tantray Construction
195 | 15 | 44/7 | DA+9 | SANDY | Pipe Type | 18.02.25 | Iqbal
196 | 16 | 70/2 | DA+3 | DRY | Pipe Type | 19.02.25 | Bhati Const.
197 | 17 | 68/0 | DD45+0 | DRY | Pipe Type | 19.02.25 | Bhati Const.
198 | 18 | 65/10 | DA+0 | DRY | Pipe Type | 19.02.25 | Bhati Const.
199 | 19 | 54/5 | DA+9 RC | SANDY | Pipe Type | 23.02.25 | Meer const
200 | 20 | 55/0 | DB1+6 RC | SANDY | Pipe Type | 23.02.25 | Meer const
201 | 21 | 53/0 | DB2+9 RC | Sandy | Pipe Type | 23.02.25 | Meer const
202 | 22 | 53/1 | DA+9 RC | Sandy | Pipe Type | 23.02.25 | Meer const
203 | 23 | 53/2 | DA+0 RC | Sandy | Pipe Type | 23.02.25 | Meer const
204 | 24 | 53/3 | DA+6 RC | Sandy | Pipe Type | 23.02.25 | Meer const
205 | 25 | 53/4 | DA+0 RC | Sandy | Pipe Type | 23.02.25 | Meer const
206 | 26 | 45/1 | DA+9 RC | SANDY | Pipe Type | 26.02.25 | Tantray Construction
207 | 27 | 45/0 | DC2+0 RC | Sandy | Pipe Type | 26.02.25 | Nadeem
208 | 28 | 44/11 | DA+0 RC | Sandy | Pipe Type | 27.02.25 | Nadeem
209 | 29 | 44/10 | DB1+9 RC | Sandy | Pipe Type | 27.02.25 | Nadeem
210 | 30 | 44/9 | DA+9 RC | Sandy | Pipe Type | 27.02.25 | Iqbal
211 | 31 | 44/8 | DCT1+0 | SANDY | Pipe Type | 28.02.25 | Iqbal
212 | 32 | 44/5 | DA+9 RC | Sandy | Pipe Type | 28.02.25 | Tantray Construction
213 | 33 | 44/6 | DB1+3 RC | SANDY | Pipe Type | 28.02.25 | Tantray Construction
214 | 34 | 44/4 | DA+9 RC | Sandy | Pipe Type | 28.02.25 | Tantray Construction
| Mar-25 |  |  | 1 | 1 |  | 1
215 | 1 | 55/1 | DA+0 | WFR | Counter Poise | 02.03.25 | Bhati
216 | 2 | 44/0 | DB1+3 RC | SANDY | Pipe Type | 16.03.25 | OM Const
217 | 3 | 44/1 | DA+0 RC | Sandy | Pipe Type | 16.03.25 | OM Const
218 | 4 | 44/2 | DA+0 | Sandy | Pipe Type | 16.03.25 | OM Const
219 | 5 | 43/10 | DA+3 RC | SANDY | Pipe Type | 16.03.25 | OM Const
219 | 5 | 70/11 | DA+3 | DRY | Pipe Type | 29.03.25 | Bhati Const.

## Earthing (PKG-G) (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Earthing
Cum S No | Sl. No. | Location No. | Tower Type | Classification | Type of Earthing | Earthing | Name of Sub-Contractor | Check list
2023-08-01
1 | 1 | 58/1 | DA+0 | DRY | Pipe Type | 16.08.23 | Mahadev engg. | Check list submitted
2 | 2 | 58/11 | DA+3 | DRY | Pipe Type | 20.08.23 | Mahadev engg. | Check list submitted
3 | 3 | 58/3 | DA+3 | DRY | Pipe Type | 24.8.23 | Mahadev engg. | Check list submitted
4 | 4 | 58/5 | DA+3 | DRY | Pipe Type | 24.8.23 | Mahadev engg. | Check list submitted
5 | 5 | 57/10 | DA+0 | DRY | Pipe Type | 24.8.23 | Manoj Sharma | Check list submitted
6 | 6 | 57/13 | DA+0 | DRY | Pipe Type | 24.8.23 | Manoj Sharma | Check list submitted
7 | 7 | 57/11 | DA+0 | DRY | Pipe Type | 24.8.23 | Manoj Sharma | Check list submitted
8 | 8 | 57/12 | DA+3 | DRY | Pipe Type | 24.8.23 | Manoj Sharma | Check list submitted
9 | 9 | 58/6 | DA+3 | DRY | Pipe Type | 24.8.23 | Mahadev engg. | Check list submitted
10 | 10 | 57/8 | DA+3 | DRY | Pipe Type | 25.08.23 | Manoj Sharma | Check list submitted
11 | 11 | 52/2 | DA+3 | DFR | Counter Poise | 25.08.23 | Khewanjrai Electrical | Check list submitted
12 | 12 | 57/9 | DA+0 | DRY | Pipe Type | 25.08.23 | Manoj Sharma | Check list submitted
13 | 13 | 58/15 | DA+3 | DRY | Pipe Type | 26.08.23 | Mahadev engg. | Check list submitted
14 | 14 | 58/10 | DA+3 | DRY | Pipe Type | 26.08.23 | Mahadev engg. | Check list submitted
15 | 15 | 58/9 | DA+0 | DRY | Pipe Type | 26.08.23 | Mahadev engg. | Check list submitted
16 | 16 | 58/16 | DA+0 | DRY | Pipe Type | 29.08.23 | Mahadev engg. | Check list submitted
17 | 17 | 52/1 | DA+0 | DFR | Counter Poise | 31.08.23 | Khewanjrai Electrical | Check list submitted
18 | 18 | 58/12 | DA+0 | DRY | Pipe Type | 31.08.23 | Mahadev engg. | Check list submitted
19 | 19 | 51/4 | DA+3 | DFR | Counter Poise | 31.08.23 | B S Electrical | Check list submitted
20 | 20 | 58/8 | DA+0 | DRY | Pipe Type | 31.08.23 | Mahadev engg. | Check list submitted
21 | 21 | 51/3 | DA+0 | DFR | Counter Poise | 31.08.23 | B S Electrical | Check list submitted
22 | 22 | 52/4 | DA+0 | DFR | Counter Poise | 31.08.23 | Khewanjrai Electrical | Check list submitted
2023-09-01
23 | 1 | 61/1 | DA+0 | DRY | Pipe Type | 03.09.2023 | Mahadev engg. | Check list submitted
24 | 2 | 59/5 | DA+0 | DRY | Pipe Type | 05.09.23 | Mahadev engg. | Check list submitted
25 | 3 | 61/2 | DA+0 | DRY | Pipe Type | 06.09.23 | Mahadev engg. | Check list submitted
26 | 4 | 58/2 | DA+0 | DRY | Pipe Type | 10.09.23 | Mahadev engg. | Check list submitted
27 | 5 | 59/1 | DA+0 | DRY | Pipe Type | 10.09.23 | Manoj Sharma | Check list submitted
28 | 6 | 59/3 | DA+0 | DRY | Pipe Type | 10.09.23 | Manoj Sharma | Check list submitted
29 | 7 | 59/2 | DA+0 | DRY | Pipe Type | 10.09.23 | Manoj Sharma | Check list submitted
30 | 8 | 59/6 | DA+0 | DRY | Pipe Type | 10.09.23 | Manoj Sharma | Check list submitted
31 | 9 | 53/3 | DA+3 | DRY | Pipe Type | 12.09.23 | Vaishali Const | Check list submitted
32 | 10 | 53/4 | DA+3 | DRY | Pipe Type | 12.09.23 | Vaishali Const | Check list submitted
33 | 11 | 47/3 | DA+0 | DFR | Counter Poise | 18.09.23 | B S Electrical | received
34 | 12 | 47/2 | DA+0 | DFR | Counter Poise | 18.09.23 | B S Electrical | received
35 | 13 | 51/10 | DA+3 | DFR | Counter Poise | 19.09.23 | Nurul Amin | received
36 | 14 | 55/2 | DA+3 | DFR | Counter Poise | 20.09.23 | Amirul Islam | Not received
37 | 15 | 48/1 | DA+0 | DRY | Pipe Type | 21.09.23 | Shri Bhadariyarai Enterprises | received
38 | 16 | 50/4 | DA+3 | DRY | Pipe Type | 21.09.23 | Shri Bhadariyarai Enterprises | received
39 | 17 | 48/2 | DA+3 | DRY | Pipe Type | 22.09.23 | Shri Bhadariyarai Enterprises | received
40 | 18 | 52/5 | DA+3 | DRY | Pipe Type | 23.09.23 | Nurul Amin | received
41 | 19 | 55/3 | DA+0 | DFR | Counter Poise | 24.09.23 | Amirul Islam | Not received
42 | 20 | 56/3 | DA+0 | DFR | Counter Poise | 25.9.23 | Vaishali Const | Not received
43 | 21 | 43/4 | DA+9 | DRY | Pipe Type | 25.09.23 | Shakti Construction | Not received
44 | 22 | 56/6 | DA+3 | DRY | Pipe Type | 26.09.23 | Manoj Sharma | Not received
45 | 23 | 56/7 | DA+3 | DRY | Pipe Type | 26.09.23 | Manoj Sharma | Not received
46 | 24 | 55/4 | DA+3 | DFR | Counter Poise | 27.09.23 | Amirul Islam | Not received
47 | 25 | 43/5 | DA+0 | DFR | Counter Poise | 28.09.23 | Amirul Islam | received
48 | 26 | 51/2 | DA+0 | DRY | Pipe Type | 29.09.23 | B S Electrical | received
49 | 27 | 44/1 | DA+0 | WFR | Counter Poise | 29.09.23 | Shakti Construction | Not received
50 | 28 | 55/10 | DA+3 | DRY | Pipe Type | 29.09.23 | Nurul Amin | Not received
51 | 29 | 44/4 | DA+0 | WFR | Counter Poise | 30.09.23 | B S Electrical
52 | 30 | 44/2 | DA+0 | SANDY | Pipe Type | 30.09.23 | Shakti Construction
2023-10-01
53 | 1 | 50/3 | DA+0 | DFR | Counter Poise | 01.10.23 | Shri Bhadariyarai Enterprises
54 | 2 | 72/3 | DA+0 | DRY | Pipe Type | 01.10.23 | Mahadev engg.
55 | 3 | 72/4 | DA+0 | DRY | Pipe Type | 01.10.23 | Mahadev engg.
56 | 4 | 72/5 | DA+0 | DRY | Pipe Type | 01.10.23 | Mahadev engg.
57 | 5 | 72/2 | DA+0 | DRY | Pipe Type | 03.10.23 | Mahadev engg.
58 | 6 | 71/3 | DA+0 | DRY | Pipe Type | 03.10.23 | Mahadev engg.
59 | 7 | 71/4 | DA+0 | DRY | Pipe Type | 03.10.23 | Mahadev engg.
60 | 8 | 71/1 | DA+0 | DRY | Pipe Type | 03.10.23 | Mahadev engg.
61 | 9 | 57/4 | DA+0 | DRY | Pipe Type | 04.10.23 | Manoj Sharma
62 | 10 | 57/5 | DA+3 | DRY | Pipe Type | 04.10.23 | Manoj Sharma
63 | 11 | 57/2 | DA+0 | DRY | Pipe Type | 04.10.23 | Manoj Sharma
64 | 12 | 57/1 | DA+3 | DRY | Pipe Type | 04.10.23 | Manoj Sharma
65 | 13 | 57/3 | DA+0 | DRY | Pipe Type | 04.10.23 | Manoj Sharma
66 | 14 | 56/9 | DA+3 | DRY | Pipe Type | 04.10.23 | Manoj Sharma
67 | 15 | 56/8 | DA+3 | DRY | Pipe Type | 04.10.23 | Manoj Sharma
68 | 16 | 56/4 | DA+3 | DFR | Counter Poise | 04.10.23 | Manoj Sharma
69 | 17 | 57/7 | DA+3 | DRY | Pipe Type | 04.10.23 | Manoj Sharma |  | 72/1
70 | 18 | 56/5 | DA+0 | DRY | Pipe Type | 05.10.23 | Manoj Sharma |  | 71/5
71 | 19 | 55/11 | DA+3 | DRY | Pipe Type | 05.10.23 | Nurul Amin
72 | 20 | 55/7 | DA+0 | DRY | Pipe Type | 06.10.23 | Nurul Amin
73 | 21 | 55/8 | DA+3 | DRY | Pipe Type | 06.10.23 | Nurul Amin
74 | 22 | 55/9 | DA+3 | DRY | Pipe Type | 06.10.23 | Nurul Amin
75 | 23 | 55/5 | DA+0 | DFR | Counter Poise | 07.10.23 | Amirul Islam
76 | 24 | 56/1 | DA+3 | DFR | Counter Poise | 08.10.23 | Vaishali Const
77 | 25 | 58/14 | DA+0 | DRY | Pipe Type | 08.10.23 | Mahadev engg.
78 | 26 | 41/7 | DA+3 | SANDY | Pipe Type | 09.10.23 | Om Const
79 | 27 | 41/10 | DA+3 | SANDY | Pipe Type | 09.10.23 | Om Const
80 | 28 | 44/3 | DA+3 | WFR | Counter Poise | 10.10.23 | Shakti Construction
81 | 29 | 41/11 | DA+3 | SANDY | Pipe Type | 12.10.23 | Om Const
82 | 30 | 58/4 | DA+0 | DRY | Pipe Type | 11.10.23 | Mahadev engg.
83 | 31 | 56/2 | DA+3 | DFR | Counter Poise | 17.10.23 | Vaishali Const
84 | 32 | 55/1 | DA+3 | DRY | Pipe Type | 17.10.23 | Amirul Islam
85 | 33 | 58/7 | DB1+0 | DRY | Pipe Type | 19.10.23 | Mahadev engg.
86 | 34 | 57/6 | DB1+0 | DRY | Pipe Type | 22.10.23 | Manoj Sharma
87 | 35 | 51/5 | DA+0 | DRY | Pipe Type | 23.10.23 | Vaishali Const
88 | 36 | 51/7 | DA+3 | DFR | Counter Poise | 23.10.23 | Vaishali Const
89 | 37 | 53/2 | DA+3 | DFR | Counter Poise | 23.10.23 | Vaishali Const
90 | 38 | 59/0 | DB2+0 | DRY | Pipe Type | 26.10.23 | Mahadev engg.
91 | 39 | 57/0 | DB2+0 | DRY | Pipe Type | 28.10.23 | Manoj Sharma
2023-11-01
92 | 1 | 56/0 | DB1+0 | DFR | Counter Poise | 02.11.23 | Vaishali Const
93 | 2 | 51/0 | DB2+0 | DFR | Counter Poise | 02.11.23 | Manoj Sharma
94 | 3 | 48/0 | DB2+0 | SANDY | Pipe Type | 05.11.23 | Om Const
95 | 4 | 55/6 | DA+3 | DRY | Pipe Type | 07.11.23 | Amirul Islam
96 | 5 | 33/1 | DA+0 | SANDY | Pipe Type | 07.11.23 | Shakti Construction
97 | 7 | 52/0 | DB2+0 | DRY | Pipe Type | 08.11.23 | Manoj Sharma
98 | 8 | 43/1 | DA+9 | SANDY | Pipe Type | 08.11.23 | Om Const
99 | 9 | 46/2 | DA+0 | DRY | Pipe Type | 09.11.23 | Bhadariya
100 | 10 | 47/0 | DB1+0 | SANDY | Pipe Type | 09.11.23 | Om Const
101 | 13 | 51/9 | DA+0 | DRY | Pipe Type | 14.11.23 | Om Const
2023-12-01
102 | 1 | 51/6 | DA+0 | DRY | Pipe Type | 02.12.23 | Om Const
103 | 2 | 46/3 | DA+0 | SANDY | Pipe Type | 09.12.23 | Manoj Sharma
104 | 3 | 51/1 | DA+0 | DFR | Counter Poise | 09.12.23 | Om Const
105 | 4 | 41/5 | DA+0 RC | SANDY | Pipe Type | 13.12.23 | Shakti Construction
106 | 5 | 53/1 | DA+0 RC | DRY | Pipe Type | 17.12.23 | Om Const
107 | 7 | 51/8 | DA+3 | DFR | Counter Poise | 17.12.23 | Om Const
108 | 8 | 52/3 | DA+0 RC | SANDY | Pipe Type | 22.12.23 | Om Const
2024-01-01
109 | 1 | 41/6 | DA+0(RC) | SANDY | Pipe Type | 17.01.24 | Riddhika Tech.
110 | 2 | 41/4 | DA+0(RC) | SANDY | Pipe Type | 17.01.24 | Riddhika Tech.
111 | 3 | 41/12 | DA+3 RC | SANDY | Pipe Type | 27.01.24 | Riddhika Tech.
112 | 4 | 41/8 | DA+0 (RC) | SANDY | Pipe Type | 27.01.24 | Riddhika Tech.
113 | 5 | 41/9 | DA+0(RC) | SANDY | Pipe Type | 28.01.24 | Riddhika Tech.
Feb-24
114 | 1 | 53/0 | DC2+3 | DRY | Pipe Type | 02.02.24 | Om Const
115 | 2 | 55/0 | DC1+0 | DRY | Pipe Type | 06.02.24 | Manoj Sharma
116 | 3 | 58/0 | DC2+0 | DRY | Pipe Type | 19.02.24 | Mahadev engg.
117 | 4 | 65/1 | DA+3 | DRY | Pipe Type | 21.2.24 | Bhati Const.
118 | 5 | 65/4 | DA+0 | DRY | Pipe Type | 21.2.24 | Bhati Const.
119 | 6 | 63/6 | DA+3 | DRY | Pipe Type | 22.2.24 | Bhati Const.
120 | 7 | 65/3 | DA+0 | DRY | Pipe Type | 22.2.24 | Bhati Const.
121 | 8 | 65/5 | DA+0 | DRY | Pipe Type | 22.2.24 | Bhati Const.
122 | 9 | 46/4 | DA+0 (RC) | SANDY | Pipe Type | 20.02.24 | Om Const
123 | 10 | 63/5 | DA+3 | DRY | Pipe Type | 10.02.24 | Bhati Const.
124 | 11 | 40/10 | DB1+6 | SANDY | Pipe Type | 24.02.24 | Riddhika Tech.
125 | 12 | 40/11 | DA+9 RC | SANDY | Pipe Type | 24.02.24 | Riddhika Tech.
126 | 13 | 40/6 | DA+3 RC | SANDY | Pipe Type | 25.02.24 | Riddhika Tech.
March'24
127 | 1 | 40/4 | DA+9 RC | SANDY | Pipe Type | 06.03.24 | Riddhika Tech.
128 | 2 | 37/3 | DA+0 | SANDY | Pipe Type | 08.03.24 | Veerteja Enterprises
129 | 3 | 37/2 | DB1+6 | SANDY | Pipe Type | 08.03.24 | Veerteja Enterprises
130 | 4 | 38/1 | DA+3 RC | SANDY | Pipe Type | 12.03.24 | Shakti Construction
131 | 5 | 38/6 | DA+0 RC | SANDY | Pipe Type | 13.03.24 | Shakti Construction
132 | 6 | 37/4 | DA+6 RC | SANDY | Pipe Type | 13.03.24 | Veerteja Enterprises
133 | 7 | 40/3 | DA+3 RC | SANDY | Pipe Type | 14.03.24 | Riddhika Tech.
134 | 8 | 39/1 | DA+6 RC | SANDY | Pipe Type | 14.03.24 | Riddhika Tech.
135 | 9 | 65/2 | DA+0 | SANDY | Pipe Type | 14.03.24 | Bhati Const.
136 | 10 | 63/2 | DA+0 | DRY | Pipe Type | 14.03.24 | Bhati Const.
137 | 11 | 65/6 | DA+0 | Dry | Pipe Type | 14.03.24 | Bhati Const.
138 | 12 | 40/5 | DB1+9 | SANDY | Pipe Type | 14.03.24 | Riddhika Tech.
139 | 13 | 38/2 | DA+6 | SANDY | Pipe Type | 16.03.24 | Veerteja Enterprises
140 | 14 | 38/3 | DA+9 RC | SANDY | Pipe Type | 16.03.24 | Veerteja Enterprises
141 | 15 | 39/3 | DA+3 RC | SANDY | Pipe Type | 21.03.24 | Riddhika Tech.
April'24
142 | 1 | 38/8 | DA+0 RC | SANDY | Pipe Type | 21.04.24 | Shakti Construction
May'24
143 | 1 | 39/4 | DA+0(RC) | SANDY | Pipe Type | 12.05.24 | SB MEHAR CONST.
July'24
144 | 1 | 40/2 | DB1+9 | SANDY | Pipe Type | 15.07.24 | Bhati Const.
145 | 2 | 49/0 | DC1+3 | DFR | Counter Poise | 20.07.24 | Mahadev engg.
146 | 3 | 50/0 | DC2+3 | DFR | Counter Poise | 29.07.24 | Mahadev engg.
Aug'24
147 | 1 | 72/0 | DB1+0 | DRY | Pipe Type | 01.08.24 | Mahadev engg.
148 | 2 | 71/2 | DA+0 | DRY | Pipe Type | 01.08.24 | Mahadev engg. |  |  |  | 51
149 | 3 | 43/6 | DA+6 RC | SANDY | Pipe Type | 01.08.24 | Om Const |  |  |  | 22
150 | 4 | 44/0 | DB1+0 | SANDY | Pipe Type | 02.08.24 | Om Const
151 | 5 | 50/2 | DA+0 | DFR | Counter Poise | 11.08.24 | Bhati Const.
152 | 6 | 42/0 | DC2+9 RC | SANDY | Pipe Type | 11.08.24 | Om Const
153 | 7 | 47/1 | DA+0 | DRY | Pipe Type | 14.08.24 | Bhati Const.
154 | 8 | 72/7 | DB1+9 RC | SANDY | Pipe Type | 14.08.24 | Mahadev engg.
155 | 9 | 72/6 | DA+0 RC | SANDY | Pipe Type | 14.08.24 | Mahadev engg. |  |  | 48
156 | 10 | 69/6 | DA+0 | DRY | Pipe Type | 23.08.24 | Mahadev engg. |  |  | 27
157 | 11 | 68/5 | DA+3 | DRY | Pipe Type | 23.08.24 | Shakti Construction
158 | 12 | 63/0 | DD45+0 | DRY | Pipe Type | 24.08.24 | Mahadev engg.
159 | 13 | 43/0 | DB2+9 RC | SANDY | Pipe Type | 31.08.24 | Om Const
160 | 14 | 50/1 | DA+0 RC | DFR | Counter Poise | 31.08.24 | Mahadev engg.
Sept'24
161 | 1 | 69/2 | DA+0 | DRY | Pipe Type | 02.09.24 | Bhati Const.
162 | 2 | 69/3 | DA+0 | Sandy | Pipe Type | 02.09.24 | Bhati Const.
163 | 3 | 69/4 | DA+0 | DRY | Pipe Type | 02.09.24 | Bhati Const.
164 | 4 | 69/5 | DA+0 | DRY | Pipe Type | 02.09.24 | Bhati Const.
165 | 5 | 68/2 | DA+3 | DRY | Pipe Type | 02.09.24 | Shakti Construction
166 | 6 | 67/0 | DD45+0 | DRY | Pipe Type | 04.09.24 | Awadh Const.
167 | 7 | 69/7 | DA+0 | DRY | Pipe Type | 05.09.24 | Mahadev engg.
168 | 8 | 73/0 | DD45+9 | DFR | Counter Poise | 07.10.24 | Mahadev engg.
169 | 9 | 69/1 | DA+0 | DRY | Pipe Type | 05.09.24 | Bhati Const.
170 | 10 | 67/1 | DB1+9 | DRY | Pipe Type | 05.09.24 | Awadh Const.
171 | 11 | 35/5 | DA+0 RC | SANDY | Pipe Type | 09.09.24 | Om Const
172 | 12 | 68/4 | DA+3 | DRY | Pipe Type | 10.09.24 | Shakti Construction
173 | 13 | 68/6 | DA+3 | DRY | Pipe Type | 10.09.24 | Shakti Construction
174 | 14 | 35/6 | DA+9 RC | SANDY | Pipe Type | 15.09.24 | Om Const
175 | 15 | 66/1 | DA+3 | DRY | Pipe Type | 15.09.24 | Shree Shyam Const.
176 | 16 | 66/2 | DA+0 | DRY | Pipe Type | 15.09.24 | Shree Shyam Const.
177 | 17 | 66/4 | DA+3 | DRY | Pipe Type | 15.09.24 | Shree Shyam Const.
178 | 18 | 69/0 | DB1+0 | DRY | Pipe Type | 16.09.24 | Bhati Const.
179 | 19 | 71/5 | DA+0 | DRY | Pipe Type | 16.09.24 | Mahadev engg.
180 | 20 | 68/3 | DA+0 | DRY | Pipe Type | 22.09.24 | Shakti Construction
181 | 21 | 65/7 | DA+0 | DRY | Pipe Type | 23.09.24 | Shree Shyam Const.
182 | 22 | 35/4 | DA+3 RC | SANDY | Pipe Type | 27.09.24 | Om Const
183 | 23 | 43/2 | DA+9 RC | SANDY | Pipe Type | 27.09.24 | Kalpana
184 | 24 | 43/3 | DA+3 RC | SANDY | Pipe Type | 27.09.24 | Kalpana
Oct'24
185 | 1 | 35/8 | DA+0 RC | SANDY | Pipe Type | 04.10.24 | Om Const
186 | 2 | 35/7 | DA+3 RC | SANDY | Pipe Type | 04.10.24 | Om Const
187 | 3 | 68/0 | DD45+0 | DRY | Pipe Type | 07.10.23 | Shakti Construction
188 | 4 | 68/1 | DA+3 | DRY | Pipe Type | 07.10.23 | Shakti Construction
189 | 5 | 66/3 | DA+3 | DRY | Pipe Type | 07.10.23 | Shree Shyam Const.
190 | 6 | 66/0 | DD45+0 | DRY | Pipe Type | 07.10.23 | Shree Shyam Const.
191 | 7 | 62/0 | DC2+0 | DRY | Pipe Type | 07.10.23 | Mahadev engg.
192 | 8 | 72/1 | DA+0 | DRY | Pipe Type | 19.10.24 | Mahadev engg.
193 | 9 | 71/0 | DD60+0 | FS | Pipe Type | 22.10.24 | Mahadev engg.
194 | 10 | 35/2 | DA+0 (RC) | SANDY | Pipe Type | 23.10.24 | Om Const
195 | 11 | 69/9 | DA+0 | DFR | Counter Poise | 26.10.24 | Mahadev engg.
196 | 12 | 64/0 | DB2+0 | DRY | Pipe Type | 26.10.24 | Bhati Const.
197 | 13 | 35/1 | DA+0 RC | SANDY | Pipe Type | 17.10.24 | Om Const
198 | 14 | 35/0 | DB2+0 RC | SANDY | Pipe Type | 17.10.24 | Om Const
Nov'24
199 | 1 | 35/3 | DA+0 (RC) | SANDY | Pipe Type | 06.11.24 | Om Const
200 | 2 | 34/4 | DA+6 RC | SANDY | Pipe Type | 08.11.24 | Om Const
201 | 3 | 34/6 | DA+6 RC | SANDY | Pipe Type | 22.11.24 | Om Const
202 | 4 | 38/9 | DB1+6 RC | SANDY | Pipe Type | 22.11.24 | Om Const
203 | 5 | 39/0 | DC2+3 RC | SANDY | Pipe Type | 22.11.24 | Om Const
204 | 6 | 58/13 | DA+0 | DRY | Pipe Type | 29.11.24 | Bhati Const.
Dec'24
205 | 1 | 34/3 | DA+9 RC | SANDY | Pipe Type | 04.12.24 | Om Const
206 | 2 | 40/12 | DA+0 RC | SANDY | Pipe Type | 06.12.24 | Nadeem rasool
207 | 3 | 69/8 | DA+0 | DFR | Pipe Type | 08.12.24 | Mahadev engg.
208 | 4 | 64/8 | DA+0 | DRY | Pipe Type | 08.12.24 | Bhati Const.
209 | 5 | 64/7 | DA+3 | DRY | Pipe Type | 12.12.24 | Bhati Const.
210 | 6 | 34/2 | DA+9 RC | SANDY | Pipe Type | 17.12.24 | Om Const
211 | 7 | 37/8 | DA+0 | SANDY | Pipe Type | 17.12.24 | Nadeem rasool
212 | 8 | 64/1 | DA+6 | DRY | Pipe Type | 19.12.24 | Bhati Const.
213 | 9 | 64/9 | DA+0 | DRY | Pipe Type | 19.12.24 | Bhati Const.
214 | 10 | 70/0 | DD60+0 | FS | Pipe Type | 19.12.24 | Mahadev engg.
215 | 11 | 64/6 | DA+3 | DRY | Pipe Type | 28.12.24 | Bhati Const.
216 | 12 | 38/4 | DA+0 RC | SANDY | Pipe Type | 30.12.24 | Nadeem rasool
217 | 13 | 38/0 | DC1+0 | SANDY | Pipe Type | 31.12.24 | Nadeem rasool
218 | 14 | 38/5 | DA+0 RC | SANDY | Pipe Type | 31.12.24 | Nadeem rasool
219 | 15 | 38/7 | DA+0 RC | SANDY | Pipe Type | 31.12.24 | Nadeem/Iqbal
2025-01-25
220 | 1 | 34/5 | DCT+0 | SANDY | Pipe Type | 03.01.25 | Om Const
221 | 2 | 33/8 | DA+3 RC | SANDY | Pipe Type | 04.01.25 | Om Const
222 | 3 | 34/1 | DA+3 RC | SANDY | Pipe Type | 05.01.25 | Om Const
223 | 4 | 63/1 | DA+6 | DRY | Pipe Type | 06.01.25 | Bhati Const.
224 | 5 | 37/7 | DA+3 RC | SANDY | Pipe Type | 07.01.25 | Iqbal
225 | 6 | 37/5 | DA+3 RC | SANDY | Pipe Type | 07.01.25 | Iqbal
226 | 7 | 37/6 | DA+6 RC | SANDY | Pipe Type | 07.01.25 | Iqbal
227 | 8 | 40/1 | DA+0 RC | SANDY | Pipe Type | 10.01.25 | Meer Construction
228 | 9 | 40/0 | DC2+0 RC | SANDY | Pipe Type | 10.01.25 | Meer Construction
229 | 10 | 39/2 | DA+0 RC | SANDY | Pipe Type | 10.01.25 | Meer Construction
230 | 11 | 39/5 | DA+3 RC | SANDY | Pipe Type | 10.01.25 | Meer Construction
231 | 12 | 39/6 | DA+0 RC | SANDY | Pipe Type | 10.01.25 | Meer Construction
232 | 13 | 39/7 | DA+0 RC | SANDY | Pipe Type | 10.01.25 | Meer Construction
233 | 14 | 60/0 | DC2+3 | DRY | Pipe Type | 20.01.25 | Bhati Const.
234 | 15 | 41/0 | DB1+0 RC | SANDY | Pipe Type | 23.01.25 | Nadeem rasool
235 | 16 | 41/1 | DA+3 RC | SANDY | Pipe Type | 23.01.25 | Nadeem rasool
236 | 17 | 41/2 | DA+0 RC | SANDY | Pipe Type | 23.01.25 | Nadeem rasool
237 | 18 | 41/3 | DA+0 RC | SANDY | Pipe Type | 23.01.25 | Nadeem rasool
Feb'25
238 | 1 | 64/2 | DA+0 | DRY | Pipe Type | 03.02.25 | Tantary Const.
239 | 2 | 64/3 | DA+0 | DRY | Pipe Type | 03.02.25 | Tantary Const.
240 | 3 | 64/4 | DA+3 | DRY | Pipe Type | 03.02.25 | Tantary Const.
241 | 4 | 64/5 | DA+3 | DRY | Pipe Type | 03.02.25 | Tantary Const.
242 | 5 | 33/3 | DA+0 | SANDY | Pipe Type | 07.02.25 | Tantary Const.
243 | 6 | 44/5 | DA+6 | WFR | Counter Poise | 07.02.25 | Bhati Const.
244 | 7 | 33/4 | DA+0 (RC) | SANDY | Pipe Type | 14.02.25 | Tantray Construction
245 | 8 | 33/5 | DA+0 | SANDY | Pipe Type | 15.02.25 | Tantray Construction
246 | 9 | 59/4 | DA+0 | DRY | Pipe Type | 19.02.25 | Bhati Const.
247 | 10 | 61/0 | DB1+6 | DRY | Pipe Type | 19.02.25 | Bhati Const.
248 | 11 | 63/4 | DA+0 | DRY | Pipe Type | 19.02.25 | Bhati Const.
249 | 12 | 40/8 | DA+0 RC | SANDY | Pipe Type | 23.02.25 | Tantray Construction
250 | 13 | 40/9 | DA+0 RC | SANDY | Pipe Type | 23.02.25 | Tantray Construction
251 | 14 | 33/0 | DB2+3 RC | SANDY | Pipe Type | 26.02.25 | Nadeem rasool
252 | 15 | 33/2 | DA+0 RC | SANDY | Pipe Type | 26.02.25 | Iqbal
253 | 16 | 33/6 | DA+6 RC | SANDY | Pipe Type | 26.02.25 | Iqbal
Mar'25
254 | 1 | 37/0 | DD60+25 RC | SANDY | Pipe Type | 11.03.25 | OM Const
255 | 2 | 37/1 | DB1+9 RC | SANDY | Pipe Type | 11.03.25 | OM Const
256 | 3 | 33/7 | DA+9 RC | SANDY | Pipe Type | 16.03.25 | Om Const
257 | 4 | 45/0 | DD60+25 RC | SANDY | Pipe Type | 19.03.25 | Bhati Const.
258 | 5 | 46/0 | DD60+25 RC | SANDY | Pipe Type | 19.03.25 | Bhati Const.
259 | 6 | 46/1 | DA+6 RC | SANDY | Pipe Type | 19.03.25 | Bhati Const.
260 | 7 | 35/9 | DA+3 RC | SANDY | Pipe Type | 21.03.25 | Om Const
261 | 8 | 34/0 | DB1+6 RC | SANDY | Pipe Type | 21.03.25 | Om Const
262 | 9 | 36/0 | DD60+25 RC | SANDY | Pipe Type | 22.03.25 | OM Const
263 | 10 | 40/7 | DA+3 RC | SANDY | Pipe Type | 06.12.24
264 | 11 | 65/0 | DB2+3 | SANDY | Pipe Type | 28.03.25 | Bhati Const.
265 | 12 | 63/3 | DA+3 | DRY | Pipe Type | 29.03.25 | Bhati Const.
1 |  |  |  | 1 | 1 |  | 1
1 |  |  |  | 1 | 1 |  | 1
1 |  |  |  | 1 | 1 |  | 1
1 |  |  |  | 1 | 1 |  | 1
1 |  |  |  | 1 | 1 |  | 1
1 |  |  |  | 1 | 1 |  | 1

## Revetment Pkg-G (hidden)
Revetment work
SI. No | Loc No | Tower Type | Dt. of Start | Dt. of complete | Random Rubble stone masonry including excavation (1:5 Cement concrete) | Excavation Volume | Back filling and levelling of volumes enclosed by revetment. | M15 Conc Nominal Mix 1:2:4 for top seal cover | M10 (PEDDING -PCC)
1 | 35/5 | DA+0 RC | 20.11.24
Total |  |  |  |  | 0 |  | 0 | 0 | 0

## Benching Status-F (hidden)
RC, Benching & Revetment Locations
Sl No. | RC | Loc No. | Tower Type | CP Position Up/Down | Raised Chimney | Chimney Extension |  |  |  | Submitted Benching Volume (Cum) |  | Approved Benching Volume (Cum) |  | Approval Date | JMC NO | JMC Date
[6 empty] | A | B | C | D | Cutting | Filling | Cutting | Filling
|  | 47 | [7 empty] | 26947.807 |  | 10818.857 |  |  | 10
1 |  | 40/0 | DC2+0 |  |  | 1 | 1 | 0 | 0 | 91.75
2 | Y | 40/1 | DA+6 |  |  | 1 | 2 | 0 | 0 | 153.267
3 |  | 40/2 | DA+3 |  |  | 0 | 0 | 0 | 0 | 48.633
4 | Y | 40/3 | DA+6 |  |  | 1 | 2 | 0 | 0 | 238.433
5 | Y | 41/0 | DC1+6 |  |  | 3 | 1 | 0 | 1 | 249.883
6 | Y | 41/1 | DB1+9 | 4 | 4 | 4 | 1 | 6 | 6 | 120.747
7 | Y | 41/2 | DA+0 |  |  | 0 | 0 | 1 | 1 | 1170.806
8 | Y | 42/0 | DC1+0 |  |  | 1 | 0 | 0 | 2 | 339.457
9 | Y | 42/1 | DA+6 |  |  | 1 | 0 | 0 | 0 | 127.8
10 | Y | 42/2 | DA+6 |  |  | 0 | 0 | 1 | 3 | 91.933
11 |  | 42/3 | DA+0 |  |  | 0 | 0 | 0 | 0 | 9.463
12 |  | 42/4 | DA+0 |  |  | 0 | 0 | 0 | 0 | 136.417
13 | Y | 42/5 | DA+9 |  |  | 0 | 0 | 0 | 1 | 106.4
14 | Y | 42/6 | DA+0 |  |  | 2 | 1 | 0 | 2 | 144.417
15 |  | 43/0 | DB1+0 |  |  | 0 | 0 | 0 | 0 | 68.726
16 | Y | 43/1 | DA+6 |  |  | 0 | 0 | 3 | 3 | 199.917
17 | Y | 43/2 | DA+3 |  |  | 1 | 0 | 0 | 1 | 189.737
18 | Y | 43/3 | DA+0 |  |  | 0 | 1 | 0 | 0 | 275.117
19 | Y | 43/4 | DA+3 |  |  | 1 | 1 | 0 | 0 | 108.9
20 |  | 43/5 | DA+3 |  |  | 0 | 0 | 0 | 0 | 35.95
21 | Y | 43/6 | DA+3 |  |  | 0 | 0 | 0 | 0 | 17.8
22 |  | 43/7 | DA+3 | 0.2 |  | 0 | 0 | 0 | 0 | 46.75
23 | Y | 43/8 | DA+9 |  |  | 1 | 0 | 0 | 0 | 120.65
24 |  | 43/9 | DA+9 |  |  | 0 | 0 | 0 | 0 | 61.583
25 | Y | 43/10 | DA+3 |  |  | 3 | 3 | 0 | 0 | 70.8
26 | Y | 43/11 | DA+3 | 1 |  | 2 | 3 | 0 | 1 | 125.717
27 | Y | 44/0 | DB1+3 |  |  | 0 | 1 | 1 | 0 | 227.366
28 |  | 44/1 | DA+0 |  |  | 0 | 0 | 1 | 0 | 516.62
29 |  | 44/2 | DA+0 |  |  | 0 | 0 | 0 | 0 | 145.7
30 | Y | 44/3 | DA+0 |  |  | 2 | 0 | 0 | 1 | 35.453
31 | Y | 44/4 | DA+9 | 3.3 | 3 | 4 | 3 | 3 | 3 | 62.367
32 | Y | 44/5 | DA+9 |  |  | 1 | 3 | 0 | 0 | 476.6
33 | Y | 44/6 | DB1+3 |  |  | 1 | 0 | 0 | 1 | 263.667
34 |  | 44/7 | DA+9 |  |  | 0 | 0 | 0 | 0 | 107.267
35 | Y | 44/8 | DC1+0 |  |  | 1 | 2 | 0 | 1 | 114.075
36 | Y | 44/9 | DA+9 | 3 |  | 4 | 0 | 2 | 6 | 218.923
37 | Y | 44/10 | DA+9 |  |  | 0 | 1 | 0 | 0 | 68.233
38 | Y | 44/11 | DA+0 |  |  | 0 | 1 | 0 | 0 | 148.233
39 | Y | 45/0 | DC2+0 |  |  | 0 | 1 | 0 | 0 | 104.47
40 | Y | 45/1 | DA+0 |  |  | 0 | 0 | 1 | 2 | 329.483
41 | Y | 46/0 | DD60+18 | 3 |  | 0 | 4 | 4 | 0 | 773.08
42 | Y | 47/0 | DD60+18 |  | 2 | 3 | 2 | 2 | 2 | 333.585
43 | Y | 47/1 | DA+6 |  | 1 | 1 | 1 | 2 | 2 | 334.445 |  | 183.244
44 |  | 47/2 | DA+9 |  |  | 0 | 0 | 0 | 0 | 35.008 |  | 14.894 |  |  | JMC-72
45 | Y | 47/3 | DA+9 |  |  | 1 | 2 | 0 | 0 | 351.248 |  | 198.462 |  |  | JMC-73
46 |  | 47/4 | DA+3
47 | Y | 47/5 | DA+0 |  |  | 0 | 1 | 0 | 0 | 151.406 |  | 50.19 |  |  | JMC-74
48 |  | 47/6 | DA+3 |  |  | 0 | 0 | 0 | 0 | 214.683 |  | 105.461 |  |  | JMC-68
49 |  | 47/7 | DA+3 |  |  | 0 | 0 | 0 | 0 | 146.833 |  | 85.356 |  |  | JMC-55 | 31-07-24
50 | Y | 47/8 | DA+0 |  |  | 1 | 0 | 0 | 0 | 186.171 |  | 58.541 |  |  | JMC-56 | 31-07-24
51 |  | 47/9 | DA+3 |  |  | 0 | 0 | 0 | 0 | 36.917 |  | 21.243 |  |  | JMC-57 | 31-07-24
52 |  | 47/10 | DA+6 |  |  | 0 | 0 | 0 | 0 | 105.1 |  | 44.208 |  |  | JMC-58 | 31-07-24
53 |  | 48/0 | DC2+0 |  |  | 0 | 0 | 0 | 0 | 271.371 |  | 121.376
54 |  | 48/1 | DA+9 |  |  | 0 | 0 | 0 | 0 | 83.933 |  | 43.92 |  |  | JMC-64 | 31-07-24
55 |  | 49/1 | DA+0 |  |  | 0 | 0 | 0 | 0 | 28.5 |  | 20.37 |  |  | JMC-65 | 31-07-24
56 |  | 49/2 | DA+3 |  |  | 0 | 0 | 0 | 0 | 237.2 |  | 152.093 |  |  | JMC-43 | 31-07-24
57 |  | 49/3 | DA+3 |  |  | 0 | 0 | 0 | 0 | 130.95 |  | 59.392 |  |  | JMC-44 | 31-07-24
58 |  | 49/4 | DA+3 |  |  | 0 | 0 | 0 | 0 | 52.95 |  | 27.468 |  |  | JMC-45 | 31-07-24
59 |  | 49/5 | DA+3 | 0.1 |  | 0 | 0 | 0 | 0 | 68.133 |  | 33.446 |  |  | JMC-46 | 31-07-24
60 |  | 49/6 | DA+0 | 0.1 |  | 0 | 0 | 0 | 0 | 29.783 |  | 10.948 |  |  | JMC-47 | 31-07-24
61 | Y | 49/7 | DA+3 |  |  | 0 | 3 | 2 | 2 | 190.733 |  | 89.935
62 | Y | 50/0 | DB2+0 |  |  | 0 | 0 | 0 | 1 | 29.469 |  | 6.775
63 | Y | 50/1 | DA+6 |  |  | 1 | 0 | 0 | 0 | 258.417 |  | 126.731 |  |  | JMC-66 | 31-07-24
64 | Y | 50/2 | DA+9 |  | 2 | 2 | 2 | 2 | 2 | 109.183 |  | 50.596 |  |  | JMC-75
65 | Y | 50/3 | DA+6 |  |  | 0 | 0 | 1 | 0 | 82.817 |  | 40.792
66 | Y | 50/4 | DA+9 |  | 3 | 3 | 3 | 4 | 3 | 90.133 |  | 31.88 |  |  | JMC-76
67 | Y | 50/5 | DA+9 |  | 3 | 4 | 3 | 4 | 3 | 82.717 |  | 13.972
68 | Y | 50/6 | DA+9 |  | 3 | 3 | 4 | 3 | 3 | 266.417 |  | 133.278
69 | Y | 50/7 | DA+0 |  |  | 0 | 0 | 0 | 1 | 58.15 |  | 20.044 |  |  | JMC-67 | 31-07-24
70 |  | 50/8 | DA+9 |  |  | 0 | 0 | 0 | 0 | 379.65 |  | 287.607 |  |  | JMC-69
71 | Y | 50/9 | DA+0 |  |  | 0 | 0 | 1 | 0 | 551.811 |  | 283.026
72 | Y | 50/10 | DA+0 |  |  | 0 | 0 | 1 | 0 | 304.834 |  | 114.598
73 |  | 51/0 | DC2+0 |  |  | 0 | 0 | 0 | 0 | 119.229 |  | 103.624
74 | Y | 51/1 | DA+0 |  |  | 0 | 0 | 1 | 0 | 74.897 |  | 10.113 |  |  | JMC-70
75 |  | 51/2 | DA+0 | -1 |  | 0 | 0 | 0 | 0 | 73.95 |  | 12.784
76 | Y | 52/0 | DC2+0 |  |  | 0 | 0 | 3 | 3 | 474.917 |  | 226.626 |  | 2024-01-09
77 | Y | 52/1 | DA+6 |  |  | 0 | 4 | 0 | 0 | 95.517 |  | 20.215 |  | 2024-01-09
78 | Y | 52/2 | DA+6 |  |  | 0 | 0 | 0 | 3 | 74.467 |  | 56.535 |  | 2024-01-09
79 | Y | 52/3 | DA+9 |  | 3 | 4 | 3 | 3 | 3 | 54.25 |  | 21.459 |  | 2024-01-09 | JMC-71
80 | Y | 52/4 | DA+9 |  |  | 2 | 2 | 0 | 0 | 35.517 |  | 14.371 |  | 2024-01-09
81 | Y | 52/5 | DA+9 |  |  | 0 | 0 | 0 | 1 | 269.167 |  | 177.797 |  | 2024-01-09 | JMC-9 | 22.03.24
82 |  | 52/6 | DA+6 |  |  | 0 | 0 | 0 | 0 | 343.483 |  | 239.936 |  | 2024-01-09 | JMC-10 | 22.03.24
83 | Y | 52/7 | DA+3 |  |  | 0 | 3 | 1 | 0 | 464.317 |  | 306.372 |  | 2024-01-09 | JMC-11 | 22.03.24
84 |  | 52/8 | DA+6 |  |  | 0 | 0 | 0 | 0 | 644.717 |  | 582.599 |  | 2024-01-09 | JMC-12 | 22.03.24
85 |  | 52/9 | DA+3 |  |  | 0 | 0 | 0 | 0 | 192.433 |  | 139.028 |  | 2024-01-09 | JMC-13 | 22.03.24
86 | Y | 52/10 | DA+9 |  | 1 | 1 | 2 | 1 | 1 | 270.567 |  | 123.839 |  | 2024-01-09 | JMC-14 | 22.03.24
87 | Y | 53/0 | DB2+9 |  | 4 | 4 | 4 | 4 | 4 | 102.651 |  | 342.89 |  | 2024-01-09
88 | Y | 53/1 | DA+9 |  | 4 | 4 | 4 | 4 | 4 | 511.767 |  | 302.874 |  | 2024-01-09
89 | Y | 53/2 | DA+0 |  |  | 0 | 0 | 0 | 2 | 121.063 |  | 38.768 |  | 2024-01-09
90 | Y | 53/3 | DA+9 |  |  | 0 | 4 | 1 | 0 | 454.927 |  | 204.813 |  | 2024-01-09
91 | Y | 53/4 | DA+0 |  |  | 0 | 2 | 1 | 0 | 686.16 |  | 280.645 |  | 2024-01-09
92 |  | 53/5 | DA+3 |  |  | 0 | 0 | 0 | 0 | 104.9 |  | 76.75 |  | 2024-01-09 | JMC-49 | 31-07-24
93 | Y | 53/6 | DA+6 |  |  | 1 | 1 | 3 | 1 | 111.483 |  | 14.573 |  | 2024-01-09
94 |  | 53/7 | DA+0 |  |  | 0 | 0 | 0 | 0 | 245.537 |  | 112.464 |  | 2024-01-09
95 |  | 53/8 | DA+9 |  | 0 | 0 | 0 | 0 | 0 | 326.55 |  | 334.123 |  | 2024-01-09
96 |  | 54/0 | DB1+6 |  |  | 0 | 0 | 0 | 0 | 400.8 |  | 293.967 |  | 2024-01-09
97 | Y | 54/1 | DA+9 |  |  | 1 | 1 | 0 | 0 | 74.4 |  | 17.753 |  | 2024-01-09
98 |  | 54/2 | DA+3 |  |  | 0 | 0 | 0 | 0 | 105.35 |  | 63.16 |  | 2024-01-09
99 | Y | 54/3 | DA+6 |  |  | 0 | 2 | 0 | 0 | 106.517 |  | 71.292 |  | 2024-01-09
100 | Y | 54/4 | DA+9 |  | 0 | 1 | 2 | 0 | 0 | 264 |  | 131.156 |  | 2024-01-09
101 | Y | 54/5 | DA+9 |  | 1 | 1 | 3 | 3 | 1 | 210.2 |  | 91.403 |  | 2024-01-09
102 | Y | 55/0 | DB1+6 |  |  | 0 | 1 | 1 | 0 | 375.874 |  | 244.465 |  | 2024-01-09
103 | Y | 55/4 | DA+0 |  |  | 0 | 0 | 0 | 1 | 248.177 |  | 98.757 |  | 2024-01-09 | JMC-15 | 22.03.24
104 | Y | 55/5 | DA+0 |  |  | 0 | 0 | 1 | 3 | 674.16 |  | 250.709 |  | 2024-01-09 | JMC-16 | 22.03.24
105 | Y | 55/6 | DA+0 |  |  | 0 | 0 | 1 | 2 | 100.954 |  | 24.027 |  | 2024-01-09 | JMC-17 | 22.03.24
106 | Y | 55/7 | DA+0 |  |  | 0 | 0 | 1 | 0 | 551.126 |  | 317.518 |  | 2024-01-09 | JMC-18 | 22.03.24
107 | Y | 55/8 | DA+9 |  |  | 0 | 0 | 1 | 0 | 480.283 |  | 241.51 |  | 2024-01-09
108 | Y | 56/0 | DD60+9 |  | 4 | 4 | 6 | 4 | 4 | 454.562 |  | 387.425 |  | 2024-01-09
109 | Y | 57/0 | DD60+9 |  | 0 | 0 | 1 | 1 | 0 | 715.032 |  | 562.651 |  | 2024-01-09
110 |  | 57/1 | DA+3 |  |  | 0 | 0 | 0 | 0 | 38.65 |  | 24.155 |  | 2024-01-09
111 |  | 57/2 | DA+3 |  |  | 0 | 0 | 0 | 0 | 64.033 |  | 20.988 |  | 2024-01-09 | JMC-50 | 31-07-24
112 |  | 57/3 | DA+0 |  |  | 0 | 0 | 0 | 0 | 91.063 |  | 39.024 |  | 2024-01-09 | JMC-51 | 31-07-24
113 |  | 57/4 | DA+0 |  |  | 0 | 0 | 0 | 0 | 165.446 |  | 77.472 |  | 2024-01-09 | JMC-52 | 31-07-24
114 | Y | 57/5 | DA+3 |  |  | 0 | 0 | 0 | 1 | 114.817 |  | 54.629 |  | 2024-01-09 | JMC-53 | 31-07-24
115 | Y | 57/6 | DA+3 |  |  | 0 | 1 | 0 | 0 | 118.95 |  | 69.342 |  | 2024-01-09 | JMC-54 | 31-07-24
116 |  | 58/0 | DC1+3 |  |  | 0 | 0 | 0 | 0 | 16.509 |  |  |  | 2023-12-22
117 |  | 59/0 | DC2+0 |  |  | 0 | 0 | 0 | 0 | 97.629 |  | 97.629 |  | 2023-12-22
118 | Y | 59/1 | DA+3 |  |  | 0 | 0 | 0 | 1 | 30.167 |  |  |  | 2023-12-22
119 |  | 59/2 | DA+3 |  |  | 0 | 0 | 0 | 0 | 74.35 |  | 57.328 |  | 2023-12-22
120 | Y | 59/3 | DA+3 |  |  | 0 | 0 | 0 | 1 | 29.783 |  |  |  | 2023-12-22
121 |  | 59/7 | DA+3 |  |  | 0 | 0 | 0 | 0 | 88.917 |  | 67.301 |  | 2023-12-22 | JMC-19 | 31-07-24
122 |  | 59/8 | DB1+3 |  |  | 0 | 0 | 0 | 0 | 30.926 |  |  |  | 2023-12-22
123 |  | 59/9 | DA+3 |  |  | 0 | 0 | 0 | 0 | 51.683 |  |  |  | 2023-12-22
124 | Y | 59/11 | DA+6 |  |  | 0 | 0 | 2 | 0 | 609.4 |  | 443.002 |  | 2023-12-22
125 |  | 59/12 | DA+6 |  |  | 0 | 0 | 0 | 0 | 69.983 |  |  |  | 2023-12-22
126 | Y | 60/2 | DA+3 |  |  | 2 | 2 | 0 | 0 | 150.115 |  | 67.99 |  | 2023-12-22 | JMC-20 | 31-07-24
127 |  | 61/1 | DA+6 |  |  | 0 | 0 | 0 | 0 | 130.228 |  | 98.667 |  | 2023-12-22 | JMC-21 | 31-07-24
128 | Y | 61/7 | DA+9 |  |  | 0 | 0 | 0 | 1 | 237.78 |  | 155.449 |  | 2023-12-22 | JMC-22 | 31-07-24
129 | Y | 61/8 | DA+6 |  |  | 1 | 2 | 1 | 0 | 139.242 |  | 18.852 |  | 2023-12-22 | JMC-23 | 31-07-24
130 |  | 62/0 | DB2+0 |  |  | 0 | 0 | 0 | 0 | 50.997 |  | 36.79 |  | 2023-12-22 | JMC-62 | 31-07-24
131 | Y | 62/1 | DA+3 |  |  | 0 | 0 | 1 | 2 | 200.388 |  | 135.911 |  | 2023-12-22 | JMC-24 | 31-07-24
132 | Y | 62/2 | DA+3 |  |  | 0 | 1 | 0 | 0 | 22.433 |  |  |  | 2023-12-22
133 |  | 62/4 | DA+3 |  |  | 0 | 0 | 0 | 0 | 27.142 |  |  |  | 2023-12-22
134 |  | 62/5 | DA+0 |  |  | 0 | 0 | 0 | 0 | 109.341 |  | 45.234 |  | 2023-12-22 | JMC-25 | 31-07-24
135 |  | 62/6 | DA+3 |  |  | 0 | 0 | 0 | 0 | 23.573 |  |  |  | 2023-12-22
136 |  | 63/0 | DC1+0 |  |  | 0 | 0 | 0 | 0 | 199.633 |  | 199.633 |  | 2023-12-22 | JMC-63 | 31-07-24
137 |  | 63/3 | DA+3 |  |  | 0 | 0 | 0 | 0 | 173.683 |  | 140.624 |  | 2023-12-22 | JMC-48 | 31-07-24
138 |  | 63/5 | DA+3 |  |  | 0 | 0 | 0 | 0 | 31.908 |  |  |  | 2023-12-22

## Benching Status-G (hidden)
RC, Benching & Revetment Locations
Sl No. | RC | Loc No. | Tower Type | CP Position Up/Down | Raised Chimney | Chimney Extension |  |  |  | Submitted Benching Volume (Cum) |  | Approved Benching Volume (Cum) |  | Approval Date | JMC NO | JMC Date
[6 empty] | A | B | C | D | Cutting | Filling | Cutting | Filling
|  | 28 | [7 empty] | 36249.329 |  | 13738.234 |  |  | 8
1 |  | 2/0 | DC1+0
2 |  | 2/2 | DA+0 |  |  | 0 | 0 | 1 | 1 | 141.89 |  | 140.97 |  | 24-11-23
3 |  | 2/3 | DA+0 |  |  | 1 | 1 | 0 | 0 | 33.32 |  | 22.61 |  | 24-11-23
4 |  | 2/4 | DA+3 |  |  | 0 | 0 | 0 | 0 | 28.01 |  | 28.01 |  | 24-11-23
5 |  | 2/5 | DA+3 |  |  | 0 | 1 | 1 | 0 | 64.4 |  | 53.49 |  | 24-11-23
6 |  | 2/6 | DA+6 |  |  | 0 | 2 | 0 | 0 | 111.36 |  | 107.54 |  | 24-11-23
7 |  | 2/7 | DA+6 |  |  | 0 | 0 | 1 | 0 | 210 |  | 209.95 |  | 24-11-23
8 |  | 3/0 | DD60+0
9 |  | 5/0 | DB1+9 |  | 2 | 2 | 2 | 2 | 2
10 |  | 6/0 | DB2+9 |  | 2 | 2 | 2 | 2 | 2
11 |  | 6/1 | DA+0 |  |  | 1 | 0 | 0 | 0 | 57.82 |  | 53.48 |  | 24-11-23
12 |  | 7/0 | DB1+0
13 |  | 8/3 | DA+3 |  |  | 0 | 0 | 0 | 1 | 49.13
14 |  | 8/4 | DA+0 |  |  | 1 | 1 | 1 | 2 | 38.56
15 |  | 8/5 | DA+3 |  |  | 0 | 0 | 0 | 0 | 35.69
16 |  | 8/9 | DA+3 |  |  | 0 | 0 | 0 | 0 | 42.16
17 |  | 9/0 | DD60+18
18 |  | 10/0 | DD60+18
19 |  | 10/1 | DA+3 |  |  | 0 | 0 | 0 | 0 | 74.8
20 |  | 10/22 | DA+0 |  |  | 1 | 4 | 0 | 0 | 82.26
21 |  | 10/23 | DA+9 |  |  | 2 | 6 | 1 | 1 | 79.35
22 |  | 11/0 | DB1+3
23 |  | 11/12 | DA+0
24 |  | 11/13 | DA+0
25 |  | 13/3 | DA+0
26 |  | 15/5 | DA+3
27 |  | 15/6 | DA+0
28 |  | 15/7 | DA+6
29 |  | 21/2 | DA+3 |  |  | 0 | 0 | 1 | 0 | 33.758 |  | 13.878
30 |  | 21/5 | DA+3 |  |  | 0 | 0 | 0 | 2 | 301.545 |  | 175.845
31 |  | 21/10 | DA+9 |  |  | 1 | 1 | 0 | 0 | 259.925 |  | 127.123
32 |  | 21/12 | DA+9 |  |  | 0 | 0 | 1 | 0 | 175.99 |  | 80.099
33 |  | 22/6 | DA+6 |  |  | 0 | 0 | 2 | 1 | 396.942 |  | 249.598
34 |  | 22/9 | DA+6 |  |  | 0 | 0 | 0 | 1 | 330.54 |  | 176.873
35 |  | 23/0 | DB2+0 |  |  | 0 | 1 | 0 | 0 | 344.386 |  | 344.386
36 |  | 23/1 | DA+0 |  |  | 0 | 0 | 0 | 0 | 175.029 |  | 76.44
37 |  | 23/3 | DA+0 |  |  | 0 | 0 | 0 | 0 | 69.578 |  | 33.81
38 |  | 23/6 | DA+6 |  |  | 0 | 0 | 0 | 0 | 203.947 |  | 95.149
39 |  | 23/7 | DA+9 |  |  | 1 | 0 | 0 | 2 | 428.652 |  | 212.812
40 |  | 23/8 | DA+9 |  |  | 1 | 1 | 0 | 0 | 230.72 |  | 119.029
41 |  | 23/11 | DA+6 |  |  | 0 | 0 | 1 | 0 | 227.185 |  | 107.373
42 |  | 24/0 | DB2+0 |  |  | 0 | 0 | 0 | 0 | 212.246
43 |  | 24/6 | DA+0 |  |  | 1 | 0 | 0 | 0 | 77.827 |  | 20.536
44 |  | 25/0 | DC1+0
45 |  | 25/2 | DA+0 |  |  | 0 | 0 | 0 | 0 | 37.344
46 |  | 25/3 | DA+0 |  |  | 0 | 2 | 1 | 0 | 196.759
47 |  | 25/4 | DA+0 |  |  | 0 | 4 | 1 | 0 | 388.33
48 |  | 25/5 | DA+3 |  |  | 1 | 0 | 0 | 0 | 37.272
49 |  | 25/7 | DA+9 |  | 3 | 4 | 3 | 3 | 3 | 238.517
50 |  | 25/8 | DA+9 |  | 4 | 4 | 4 | 4 | 4 | 0
51 |  | 26/1 | DA+3 |  |  | 0 | 1 | 1 | 0 | 360.189
52 |  | 26/2 | DA+3 |  |  | 0 | 2 | 3 | 0 | 417.632
53 |  | 26/3 | DA+0 |  |  | 0 | 0 | 0 | 0 | 235.859
54 |  | 26/4 | DA+9 |  |  | 3 | 2 | 0 | 0 | 293.157
55 |  | 26/5 | DA+9 |  |  | 2 | 0 | 0 | 2 | 139.673
56 |  | 26/6 | DA+0 |  |  | 2 | 0 | 0 | 1 | 124.417
57 |  | 26/7 | DA+3 |  |  | 1 | 0 | 0 | 3 | 265.2
58 |  | 27/0 | DC2+9
59 |  | 27/1 | DB1+9 |  | 3 | 3 | 3 | 4 | 5 | 178.762
60 |  | 27/3 | DA+0 |  |  | 0 | 2 | 1 | 0 | 112.974
61 |  | 27/4 | DA+0 |  |  | 0 | 1 | 0 | 0 | 210.484
62 |  | 28/2 | DA+6 |  |  | 3 | 0 | 0 | 1 | 385.474
63 |  | 28/3 | DA+3 |  |  | 0 | 4 | 2 | 0 | 311.35
64 |  | 28/4 | DA+9 |  |  | 1 | 2 | 0 | 0 | 293.3
65 |  | 28/5 | DA+9 | 1.5 |  | 2 | 5 | 1 | 6 | 218.617
66 |  | 28/6 | DA+9 |  |  | 1 | 6 | 1 | 6 | 230.05
67 |  | 28/7 | DA+0 | 1.5 |  | 3 | 0 | 1 | 4 | 220.61
68 |  | 28/8 | DA+3 |  |  | 0 | 1 | 5 | 0 | 453.087
69 |  | 28/9 | DA+0 |  |  | 1 | 0 | 0 | 0 | 146.587
70 |  | 29/01 | DA+06 |  |  | 1 | 0 | 0 | 1 | 253.932
71 |  | 29/02 | DA+09 |  |  | 0 | 0 | 1 | 0 | 155.856
72 |  | 29/03 | DA+06 |  |  | 0 | 0 | 0 | 0 | 185.571
73 |  | 29/04 | DA+03 |  |  | 0 | 0 | 0 | 0 | 55.903
74 |  | 29/05 | DA+00 |  |  | 0 | 0 | 0 | 1 | 159.981
75 |  | 29/06 | DA+06 |  |  | 1 | 0 | 0 | 0 | 234.032
76 |  | 29/07 | DA+03 |  |  | 0 | 0 | 0 | 0 | 125.586
77 |  | 29/09 | DA+0 |  |  | 2 | 2 | 0 | 0 | 351.09
78 |  | 29/10 | DA+06 |  |  | 0 | 2 | 0 | 0 | 455.37
79 |  | 30/00 | DC2+00 | [6 empty] | 0
80 |  | 30/01 | DA+03 |  |  | 1 | 1 | 0 | 0 | 343.4
81 |  | 30/02 | DA+00 |  |  | 0 | 0 | 0 | 0 | 42.27
82 |  | 31/00 | DD45+3
83 |  | 31/01 | DA+09 |  | 3 | 3 | 3 | 3 | 3 | 0
84 |  | 31/02 | DA+00 |  |  | 1 | 2 | 1 | 0 | 289.42
85 |  | 31/04 | DA+03 |  |  | 0 | 0 | 0 | 1 | 67.71
86 |  | 32/00 | DB2+6
87 |  | 32/02 | DA+00 |  |  | 1 | 0 | 0 | 0 | 411.95
88 |  | 32/03 | DA+03 |  |  | 0 | 2 | 0 | 0 | 99.076
89 |  | 32/04
90 |  | 32/08 | DA+09 |  |  | 0 | 0 | 0 | 0 | 98.23
91 | Y | 33/0 | DB2+3 |  |  | 2 | 0 | 0 | 4 | 381.6 |  | 222.533 |  | 2023-12-29
92 |  | 33/1 | DA+0 |  |  | 0 | 0 | 0 | 0 | 352.48 |  | 200.16 |  |  | JMC-1 | 13.03.24
93 | Y | 33/2 | DA+0 |  |  | 1 | 1 | 0 | 0 | 492.78 |  | 226.416
94 | Y | 33/3 | DA+0 |  |  | 2 | 0 | 0 | 2 | 151.2 |  | 77.104
95 | Y | 33/4 | DA+0 | -0.4 |  | 1 | 4 | 0 | 0 | 243.1 |  | 88.432
96 | Y | 33/6 | DA+6 |  |  | 0 | 0 | 4 | 4 | 214.88 |  | 156.032
97 | Y | 33/7 | DA+9 |  |  | 3 | 1 | 0 | 0 | 645.745 |  | 359.696
98 | Y | 33/8 | DA+3 |  |  | 1 | 0 | 1 | 3 | 265.799 |  | 78.225
99 | Y | 34/0 | DB1+6 |  |  | 0 | 0 | 2 | 1 | 564.394 |  | 359.682 |  | 2023-12-29
100 | Y | 34/1 | DA+3 | 0.3 |  | 2 | 0 | 2 | 3 | 256.233 |  | 50.319
101 | Y | 34/2 | DA+9 |  |  | 0 | 0 | 0 | 1 | 32.451 |  | 5.505
102 | Y | 34/3 | DA+9 | 1 |  | 0 | 0 | 3 | 6 | 1134.87 |  | 452.318
103 | Y | 34/4 | DA+6 |  |  | 1 | 3 | 1 | 0 | 313.904 |  | 87.476
104 |  | 34/5 | DCT+0 | -0.5 |  | 0 | 0 | 0 | 0 | 361.8
105 | Y | 34/6 | DA+6 |  |  | 1 | 0 | 0 | 1 | 220.4 |  | 71.358
106 | Y | 35/0 | DB2+0 |  |  | 1 | 3 | 1 | 0 | 467.993 |  | 256.377 |  | 2023-12-29
107 | Y | 35/1 | DA+0 |  |  | 0 | 3 | 0 | 0 | 69.549 |  | 21.863
108 | Y | 35/2 | DA+0 |  |  | 1 | 3 | 0 | 0 | 44.623 |  | 5.323
109 | Y | 35/3 | DA+0 |  |  | 2 | 0 | 0 | 4 | 419.263 |  | 157.798
110 | Y | 35/4 | DA+3 |  |  | 0 | 3 | 2 | 0 | 116.817 |  | 36.068
111 | Y | 35/5 | DA+0 | 0.4 |  | 0 | 3 | 1 | 0 | 703.989 |  | 299.892
112 | Y | 35/6 | DA+9 |  |  | 0 | 2 | 0 | 0 | 401.023 |  | 155.645
113 | Y | 35/7 | DA+3 |  |  | 1 | 0 | 0 | 3 | 368.217 |  | 241.532
114 | Y | 35/8 | DA+0 |  |  | 1 | 3 | 0 | 0 | 39.017 |  | 9.15
115 | Y | 35/9 | DA+0 |  |  | 0 | 2 | 0 | 0 | 147.994 |  | 64.4
116 | Y | 36/0 | DD60+18 |  |  | 2 | 0 | 0 | 0 | 162.61 |  | 84.936
117 | Y | 37/0 | DD60+18 |  | 3 | 3 | 3 | 3 | 3 | 1384.198 |  | 1254.084
118 | Y | 37/1 | DA+9 |  | 2 | 4 | 6 | 2 | 2 | 612.6 |  | 400.141
119 |  | 37/2 | DB1+6 |  |  | 0 | 0 | 0 | 0 | 105.717 |  | 98.297 |  |  | JMC-59 | 29-07-24
120 |  | 37/3 | DA+0 |  |  | 0 | 0 | 0 | 0 | 62.64 |  | 28.816 |  |  | JMC-60 | 29-07-24
121 | Y | 37/4 | DA+6 |  |  | 2 | 0 | 0 | 3 | 327.85 |  | 144.213 |  |  | JMC-61 | 29-07-24
122 | Y | 37/5 | DA+3 |  |  | 1 | 0 | 0 | 3 | 163.167 |  | 62.312
123 | Y | 37/6 | DA+6 |  |  | 1 | 0 | 0 | 0 | 284.595 |  | 143.717
124 | Y | 37/7 | DA+3 |  |  | 1 | 1 | 0 | 0 | 360.916 |  | 181.161
125 |  | 37/8 | DA+0 |  |  | 0 | 0 | 0 | 0 | 61.657 |  | 13.36
126 | Y | 38/0 | DC1+0 |  |  | 0 | 2 | 0 | 0 | 547.123 |  | 509.174 |  | 2023-12-29
127 | Y | 38/1 | DA+3 |  |  | 0 | 2 | 0 | 0 | 539.139 |  | 361.314 |  |  | JMC-26 | 29-07-24
128 | Y | 38/3 | DA+9 |  |  | 2 | 0 | 0 | 1 | 297.4957 |  | 152.854 |  |  | JMC-27 | 29-07-24
129 | Y | 38/4 | DA+0 |  |  | 1 | 1 | 0 | 2 | 191.745 |  | 48.406
130 | Y | 38/5 | DA+0 |  |  | 2 | 0 | 1 | 2 | 295.659 |  | 71.81
131 | Y | 38/6 | DA+0 |  |  | 0 | 0 | 0 | 1 | 205.829 |  | 79.449 |  |  | JMC-28 | 29-07-24
132 | Y | 38/7 | DA+0 |  |  | 1 | 0 | 0 | 1 | 100.0663 |  | 42.547
133 | Y | 38/8 | DA+0 |  |  | 0 | 1 | 0 | 1 | 159.4651 |  | 51.758 |  |  | JMC-29 | 29-07-24
134 | Y | 38/9 | DB1+6 |  |  | 0 | 0 | 2 | 2 | 411.929 |  | 272.86
135 | Y | 39/0 | DC2+3 |  |  | 2 | 0 | 0 | 2 | 428.739 |  | 280.711 |  | 2023-12-29
136 | Y | 39/1 | DA+6 |  |  | 1 | 2 | 0 | 0 | 427.017 |  | 264.925 |  |  | JMC-30 | 29-07-24
137 | Y | 39/2 | DA+0 |  |  | 0 | 3 | 0 | 0 | 315.583 |  | 127.368
138 | Y | 39/3 | DA+3 |  |  | 1 | 0 | 0 | 1 | 258.267 |  | 154.272 |  |  | JMC-31 | 29-07-24
139 | Y | 39/4 | DA+0 |  |  | 2 | 3 | 0 | 0 | 446.297 |  | 139.368
140 | Y | 39/5 | DA+3 | -1 |  | 0 | 4 | 0 | 3 | 160.354 |  | 34.435
141 | Y | 39/6 | DA+0 |  |  | 0 | 3 | 0 | 3 | 385.92 |  | 46.854
142 | Y | 39/7 | DA+0 |  |  | 0 | 0 | 0 | 3 | 435.806 |  | 187.109
143 | Y | 40/0 | DC2+0 |  |  | 0 | 5 | 2 | 0 | 1250.246 |  | 997.507 |  | 2023-12-29
144 | Y | 40/1 | DA+0 |  |  | 2 | 4 | 0 | 0 | 401.527 |  | 104.013
145 | Y | 40/2 | DB1+9 |  |  | 0 | 2 | 1 | 0 | 501.187 |  | 408.528
146 | Y | 40/3 | DA+3 |  |  | 0 | 1 | 1 | 0 | 236.907 |  | 113.002 |  |  | JMC-32 | 29-07-24
147 | Y | 40/4 | DA+9 |  |  | 0 | 0 | 0 | 1 | 521.072 |  | 489.056 |  |  | JMC-33 | 29-07-24
148 |  | 40/5 | DB1+9 |  |  | 0 | 0 | 0 | 0 | 354.1 |  | 349.912 |  |  | JMC-4 | 22.03.24
149 | Y | 40/6 | DA+3 |  |  | 1 | 0 | 0 | 2 | 154.883 |  | 79.128 |  |  | JMC-34 | 29-07-24
150 | Y | 40/7 | DA+3 |  |  | 1 | 4 | 1 | 4 | 221.71 |  | 37.48
151 | Y | 40/8 | DA+0 |  |  | 0 | 4 | 0 | 0 | 630.783 |  | 331.389
152 | Y | 40/9 | DA+0 |  |  | 0 | 6 | 1 | 2 | 133.683 |  | 21.333
153 | Y | 40/11 | DA+9 |  |  | 1 | 0 | 0 | 0 | 104.4 |  | 58 |  |  | JMC-5 | 22.03.24
154 | Y | 40/12 | DA+0 |  |  | 2 | 0 | 0 | 5 | 599.16 |  | 200.901
155 | Y | 41/0 | DB1+0 |  |  | 0 | 1 | 1 | 0 | 299.222 |  | 165.175 |  | 2023-12-29
156 | Y | 41/1 | DA+3 |  |  | 0 | 0 | 0 | 3 | 338.21 |  | 51.94 |  | 2023-09-12
157 | Y | 41/2 | DA+0 | -0.5 |  | 1 | 0 | 1 | 3 | 290.62 | 38.76 | 67.854 |  | 2023-09-12
158 | Y | 41/3 | DA+0 |  |  | 0 | 0 | 1 | 1 | 41.922 |  | 41.922 |  | 2023-09-12
159 | Y | 41/4 | DA+0 |  |  | 0 | 1 | 0 | 1 | 38.232 |  | 38.232 |  | 2023-09-12 | JMC-35 | 29-07-24
160 | Y | 41/5 | DA+0 |  |  | 0 | 0 | 1 | 1 | 128.736 | 56.312 | 35 |  | 2023-09-12 | JMC-36 | 29-07-24
161 | Y | 41/6 | DA+0 |  |  | 2 | 0 | 0 | 1 | 213.714 |  | 57.698 |  | 2023-09-12 | JMC-37 | 29-07-24
162 | Y | 41/8 | DA+0 |  |  | 0 | 2 | 1 | 0 | 30.774 |  | 30.774 |  | 2023-09-12 | JMC-6 | 22.03.24
163 | Y | 41/9 | DA+0 |  |  | 0 | 2 | 2 | 2 | 168.2 |  | 45.88 |  | 2023-09-12 | JMC-7 | 22.03.24
164 | Y | 41/12 | DA+3 |  |  | 1 | 0 | 0 | 0 | 152.648 | 28.888 | 66.766 |  | 2023-09-12 | JMC-8 | 22.03.24
165 | Y | 42/0 | DC2+9 |  |  | 0 | 0 | 0 | 1 | 442.886 |  | 408.487 |  | 2023-12-29
166 | Y | 43/0 | DB2+9 |  |  | 0 | 3 | 0 | 3 | 254.434 |  | 132.326 |  | 2023-12-29
167 |  | 43/1 | DA+9 |  |  | 0 | 0 | 0 | 0 | 94.646 |  | 34.848 |  | 2023-09-12 | JMC-2 | 13.03.24
168 | Y | 43/2 | DA+9 |  |  | 1 | 0 | 0 | 1 | 266.086 | 72.72 | 146.712 |  | 2023-09-12 | JMC-38 | 29-07-24
169 | Y | 43/3 | DA+3 | 0.21 |  | 1 | 0 | 1 | 2 | 212.394 |  | 89.962 |  | 2023-09-12 | JMC-39 | 29-07-24
170 | Y | 43/6 | DA+6 |  |  | 1 | 1 | 0 | 2 | 128.022 |  | 56.258 |  | 2023-09-12
171 | Y | 44/0 | DB1+0 |  |  | 0 | 1 | 0 | 0 | 46.923 |  | 23.625 |  | 2023-12-29
172 |  | 45/0 | DD60+18
173 |  | 46/0 | DD60+18
174 | Y | 46/1 | DA+6 |  |  | 0 | 1 | 0 | 0 | 161.416 |  | 48.006 |  | 2023-09-12
175 |  | 46/2 | DA+0 | 0.3 |  | 0 | 0 | 0 | 0 | 226.73 |  | 168.6 |  | 2023-09-12 | JMC-3 | 13.03.24
176 |  | 46/3 | DA+0 |  |  | 0 | 0 | 0 | 0 | 113.754 |  | 44.602 |  | 2023-09-12 | JMC-40 | 29-07-24
177 | Y | 46/4 | DA+0 |  |  | 0 | 2 | 0 | 3 | 168.612 |  | 96.296 |  | 2023-09-12 | JMC-41 | 29-07-24
178 | Y | 50/1 | DA+0 |  |  | 2 | 0 | 0 | 0 | 87.804
179 | Y | 51/6 | DA+0 |  |  | 1 | 0 | 0 | 0
180 | Y | 52/3 | DA+0 |  |  | 0 | 3 | 1 | 0 | 866.16 |  |  |  |  | JMC-42 | 29-07-24
181 | Y | 53/1 | DA+0 |  | 1 | 1 | 1 | 1 | 1
182 | Y | 72/6 | DA+0 |  |  | 1 | 1 | 1 | 1
183 | Y | 72/7 | DB1+9 |  |  | 1 | 1 | 1 | 1

## Earthing Pkg -G Ist section (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
FOUNDATION
Sl. No. | Cum S No | Location No. | Tower Type | Classification | Type of Earthing | Earthing | Name of Sub-Contractor
1 | 1 | 32/7 | DA+0 | SANDY | Pipe Type | 07.11.23 | Shakti Construction
2 | 2 | 32/1 | DA+9 | SANDY | Pipe Type | 10.11.23 | Shakti Construction
3 | 3 | 32/5 | DA+6 | SANDY | Pipe Type | 10.11.23 | Shakti Construction
4 | 4 | 30/2 | DA+0 | SANDY | Pipe Type | 18.11.23 | Om Const
5 | 5 | 32/0 | DB2+6 | SANDY | Pipe Type | 28.11.23 | Shakti Construction
6 | 6 | 31/3 | DA+0 | SANDY | Pipe Type | 05.12.23 | Shakti Construction

## Earthing balance (hidden)
S no | PKG- G |  | PKG- F
1 | 72/1 | Mahadev engg. | 50/3 | Kalpana Const.
2 | 71/5 | Mahadev engg. | 73/9 | Shakti Const. -2
3 | 43/2 | Sai Infra | 73/2 | Shree Shyam Const.
4 | 43/3 | Sai Infra | 50/6 | Kalpana Const.
5 | 68/3 | Shakti Const. -2
6 | 73/0 | Mahadev engg. - 2
7 | 68/1 | Shakti Const. -2
8 | 66/3 | Shree Shyam Const.
9 | 69/0 | Bhati Const.-2

## Tack Welding - PKG-G (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Tack Welding
Cum Sl. No. | Month Sl. No. | JMC No. | Location No. | Tower Type | Dt. of Start | Dt. of Complete | Tack Welding Status | Name of Sub-Contractor | Ramarks
2023-10-01
1 | 1 |  | 57/12 | DA+3 | 24.10.23 | 25.10.23 | Done | Suraja Ram
2 | 2 |  | 57/13 | DA+0 | 24.10.23 | 25.10.23 | Done | Suraja Ram
3 | 3 |  | 57/11 | DA+0 | 25.10.23 | 26.10.23 | Done | Suraja Ram
4 | 4 |  | 57/10 | DA+3 | 26.10.23 | 27.10.23 | Done | Suraja Ram
5 | 5 |  | 57/9 | DA+0 | 27.10.23 | 29.10.23 | Done | Suraja Ram
2023-11-01
6 | 1 |  | 57/4 | DA+0 | 31.10.23 | 01.11.23 | Done | Suraja Ram
7 | 2 |  | 57/3 | DA+0 | 01.11.23 | 02.11.23 | Done | Suraja Ram
8 | 3 |  | 57/2 | DA+0 | 02.11.23 | 03.11.2023 | Done | Suraja Ram
9 | 4 |  | 57/5 | DA+3 | 03.11.2023 | 04.11.2023 | Done | Suraja Ram
10 | 5 |  | 58/8 | DA+0 | 05.11.2023 | 06.111.23 | Done | Suraja Ram
11 | 6 |  | 58/9 | DA+0 | 06.111.23 | 07.11.23 | Done | Suraja Ram
12 | 7 |  | 57/8 | DA+3 | 07.11.23 | 08.11.23 | Done | Suraja Ram
13 | 8 |  | 58/11 | DA+3 | 09.11.23 | 27.11.23 | Done | Suraja Ram
14 | 9 |  | 58/12 | DA+0 | 27.11.23 | 28.11.23 | Done | Suraja Ram
15 | 10 |  | 57/1 | DA+3 | 28.11.23 | 30.11.23 | Done | Suraja Ram
2023-12-01
16 | 1 |  | 56/9 | DA+3 | 30.11.23 | 02.12.23 | Done | Suraja Ram
17 | 2 |  | 56/8 | DA+3 | 02.12.23 | 03.12.23 | Done | Suraja Ram
18 | 3 |  | 56/7 | DA+3 | 06.12.23 | 06.12.23 | Done | Suraja Ram
19 | 4 |  | 58/14 | DA+0 | 07.12.23 | 07.12.23 | Done | Suraja Ram
20 | 5 |  | 58/16 | DA+0 | 13.12.23 | 13.12.23 | Done | Suraja Ram
21 | 6 |  | 58/10 | DA+3 | 14.12.23 | 15.12.23 | Done | Suraja Ram
22 | 7 |  | 59/1 | DA+0 | 18.12.23 | 18.12.23 | Done | Suraja Ram
23 | 8 |  | 59/2 | DA+0 | 19.12.23 | 19.12.23 | Done | Suraja Ram
24 | 9 |  | 59/3 | DA+0 | 20.12.23 | 20.12.23 | Done | Suraja Ram
25 | 10 |  | 59/5 | DA+0 | 21.12.23 | 21.12.23 | Done | Suraja Ram
26 | 11 |  | 59/6 | DA+0 | 22.12.23 | 22.12.23 | Done | Suraja Ram
27 | 12 |  | 56/3 | DA+0 | 23.12.23 | 23.12.23 | Done | Suraja Ram
28 | 13 |  | 56/4 | DA+3 | 24.12.23 | 24.12.23 | Done | Suraja Ram
29 | 14 |  | 55/4 | DA+3 | 25.12.23 | 25.12.23 | Done | Suraja Ram
30 | 15 |  | 55/5 | DA+0 | 26.12.23 | 26.12.23 | Done | Suraja Ram
31 | 16 |  | 51/5 | DA+0 | 21.12.23 | 26.12.23 | Done | Kailash Nath
32 | 17 |  | 51/4 | DA+3 | 21.12.23 | 26.12.23 | Done | Kailash Nath
33 | 18 |  | 51/3 | DA+0 | 26.12.23 | 27.12.23 | Done | Kailash Nath
34 | 19 |  | 51/2 | DA+0 | 27.12.23 | 28.12.23 | Done | Kailash Nath
35 | 20 |  | 55/6 | DA+3 | 29.12.23 | 29.12.23 | Done | Suraja Ram
36 | 21 |  | 51/7 | DA+3 | 29.12.23 | 29.12.23 | Done | Kailash Nath
37 | 22 |  | 51/10 | DA+3 | 29.12.23 | 30.12.23 | Done | Kailash Nath
38 | 23 |  | 52/1 | DA+0 | 30.12.23 | 30.12.23 | Done | Kailash Nath
39 | 24 |  | 55/7 | DA+0 | 30.12.23 | 30.12.23 | Done | Suraja Ram
40 | 25 |  | 55/9 | DA+3 | 31.12.23 | 31.12.23 | Done | Suraja Ram
41 | 26 |  | 52/2 | DA+3 | 31.12.23 | 31.12.23 | Done | Kailash Nath
2024-01-01
42 | 1 |  | 55/10 | DA+3 | 02.01.24 | 02.01.24 | Done | Suraja Ram
43 | 2 |  | 55/11 | DA+3 | 02.01.24 | 02.01.24 | Done | Suraja Ram
44 | 3 |  | 52/5 | DA+3 | 02.01.24 | 02.01.24 | Done | Kailash Nath
45 | 4 |  | 57/7 | DA+3 | 03.01.24 | 03.01.24 | Done | Suraja Ram
46 | 5 |  | 58/5 | DA+3 | 04.01.24 | 05.01.24 | Done | Suraja Ram
47 | 6 |  | 57/6 | DB1+0 | 06.01.24 | 06.01.24 | Done | Suraja Ram
48 | 7 |  | 57/0 | DB2+0 | 07.01.24 | 07.01.24 | Done | Suraja Ram
49 | 8 |  | 56/6 | DA+3 | 08.01.24 | 08.01.24 | Done | Suraja Ram
50 | 9 |  | 56/2 | DA+3 | 11.01.24 | 12.01.24 | Done | Suraja Ram
51 | 10 |  | 56/5 | DA+0 | 13.01.24 | 13.01.24 | Done | Suraja Ram
52 | 11 |  | 56/0 | DB1+0 | 13.01.24 | 13.01.24 | Done | Suraja Ram
53 | 12 |  | 55/8 | DA+3 | 14.1.24 | 14.1.24 | Done | Suraja Ram
54 | 13 |  | 58/1 | DA+0 | 16.01.2024 | 16.01.2024 | Done | Suraja Ram
55 | 14 |  | 58/4 | DA+0 | 17.01.2024 | 17.01.2024 | Done | Suraja Ram
56 | 15 |  | 58/6 | DA+3 | 19.01.24 | 19.01.24 | Done | Suraja Ram
57 | 16 |  | 50/4 | DA+3 | 22.01.24 | 22.01.24 | Done | Ramagora
58 | 17 |  | 50/3 | DA+0 | 24.01.24 | 24.01.24 | Done | Ramagora
59 | 18 |  | 44/4 | DA+0 | 25.01.24 | 25.01.24 | Done | Ramagora
60 | 19 |  | 58/3 | DA+3 | 27.01.24 | 27.01.24 | Done | Suraja Ram
61 | 20 |  | 44/2 | DA+0 | 27.01.24 | 27.01.24 | Done | Ramagora
62 | 21 |  | 41/10 | DA+0 | 28.01.24 | 28.01.24 | Done | Ramagora
63 | 22 |  | 41/11 | DA+3 | 29.01.24 | 29.01.24 | Done | Ramagora
64 | 23 |  | 58/7 | DB+0 | 29.01.24 | 29.01.24 | Done | Suraja Ram
65 | 24 |  | 41/7 | DA+3 | 30.01.24 | 30.01.24 | Done | Ramagora
66 | 25 |  | 58/15 | DA+3 | 30.01.24 | 30.01.24 | Done | Suraja Ram
67 | 26 |  | 47/2 | DA+0 | 31.01.24 | 31.01.24 | Done | Ramagora
Feb-24
68 | 1 |  | 59/0 | DB+0 | 01.02.24 | 01.02.24 | Done | Suraja Ram
69 | 2 |  | 46/3 | DA+0 | 01.02.24 | 01.02.24 | Done | Ramagora
70 | 3 |  | 61/1 | DA+0 | 02.02.24 | 02.02.24 | Done | Suraja Ram
71 | 4 |  | 48/1 | DA+0 | 03.02.24 | 03.02.24 | Done | Ramagora
72 | 5 |  | 51/9 | DA+3 | 04.02.24 | 04.02.24 | Done | Ramagora
73 | 6 |  | 55/1 | DA+3 | 04.02.24 | 04.02.24 | Done | Suraja Ram
74 | 7 |  | 55/2 | DA+3 | 04.02.24 | 05.02.24 | Done | Suraja Ram
75 | 8 |  | 52/4 | DA+0 | 04.02.24 | 05.02.24 | Done | Ramagora
76 | 9 |  | 55/3 | DA+0 | 06.02.24 | 06.02.24 | Done | Suraja Ram
77 | 10 |  | 53/4 | DA+3 | 07..02.24 | 07..02.24 | Done | Suraja Ram
78 | 11 |  | 51/8 | DA+3 | 07..02.24 | 07..02.24 | Done | Ramagora
79 | 12 |  | 53/3 | DA+3 | 08.02.24 | 08.02.24 | Done | Suraja Ram
80 | 13 |  | 51/6 | DA+0 | 09.02.24 | 09.02.24 | Done | Ramagora
81 | 14 |  | 43/1 | DA+9 | 10.02.24 | 10.02.24 | Done | Ramagora
82 | 15 |  | 48/2 | DA+3 | 12.02.24 | 12.02.24 | Done | Suraja Ram
83 | 16 |  | 41/5 | DA+0 | 14.02.24 | 14.02.24 | Done | Ramagora
84 | 17 |  | 47/0 | DB+0 | 16.02.24 | 16.02.24 | Done | Suraja Ram |  | 23
85 | 18 |  | 46/2 | DA+0 | 17.02.24 | 17.02.24 | Done | Suraja Ram |  | 16
86 | 19 |  | 53/1 | DA+0 | 23.02.24 | 23.02.24 | Done | Suraja Ram |  | 7
87 | 20 |  | 52/0 | DB+0 | 24.02.24 | 24.02.24 | Done | Suraja Ram
88 | 21 |  | 44/3 | DA+3 | 27.02.24 | 27.02.24 | Done | Ramagora
89 | 22 |  | 43/5 | DA+0 | 28.02.24 | 28.02.24 | Done | Ramagora
90 | 23 |  | 41/9 | DA+0 | 29.02.24 | 29.02.24 | Done | Ramagora
March'24
91 | 1 |  | 41/8 | DA+0 | 04.03.24 | 04.03.24 | Done | Ramagora
92 | 2 |  | 41/4 | DA+0 | 05.03.24 | 05.03.24 | Done | Ramagora
93 | 3 |  | 41/6 | DA+0 | 07.03.24 | 07.03.24 | Done | Ramagora
94 | 4 |  | 53/2 | DA+3 | 08.03.24 | 08.03.24 | Done | Suraja Ram
95 | 5 |  | 43/4 | DA+9 | 09.03.24 | 09.03.24 | Done | Ramagora
96 | 6 |  | 51/1 | DA+0 | 11.03.24 | 11.03.24 | Done | Ramagora
97 | 7 |  | 51/0 | DB+0 | 28.03.24 | 28.03.24 | Done | Ramagora |  | Sanjay
| April'24 | [8 empty] | Manoj
98 | 1 |  | 47/3 | DA+0 | 20.04.24 | 21.04.24 | Done | Ramagora
99 | 2 |  | 56/1 | DA+3 | 24.04.24 | 24.04.24 | Done | Ramagora |  | publesh
| May'24 | [8 empty] | Pradeep
100 | 1 |  | 58/0 | DC2+0 | 04.05.24 | 04.05.24 | Done | Suraja Ram
101 | 2 |  | 61/2 | DA+0 | 06.05.24 | 06.05.24 | Done | Suraja Ram
102 | 3 |  | 44/1 | DA+0 | 12.05.24 | 12.05.24 | Done | Ramagora
103 | 4 |  | 55/0 | DC+0 | 24.05.24 | 24.05.24 | Done | Suraja Ram
104 | 5 |  | 65/5 | DA+0 | 30.05.24 | 30.05.24 | Done | Suraja Ram
105 | 6 |  | 65/4 | DA+0 | 31.05.24 | 31.05.24 | Done | Suraja Ram
June'24
106 | 1 |  | 58/2 | DA+0 | 02.06.24 | 02.06.24 | Done | Suraja Ram
107 | 2 |  | 65/3 | DA+0 | 02.06.24 | 02.06.24 | Done | Suraja Ram
108 | 3 |  | 53/0 | DC2+3 | 22.06.24 | 22.06.24 | Done | Suraja Ram
109 | 4 |  | 52/3 | DA+0 | 24.06.24 | 24.06.24 | Done | Suraja Ram
July'24
110 | 1 |  | 48/0 | DB+0 | 23.07.24 | 23.07.24 | Done | Suraja Ram
Sept'24
111 | 1 |  | 46/4 | DA+0 | 16.09.24 | 16.09.24 | Done | Suraja Ram
112 | 2 |  | 47/1 | DA+0 | 19.09.24 | 19.09.24 | Done | Suraja Ram
113 | 3 |  | 50/2 | DA+0 | 20.09.24 | 20.09.24 | Done | Suraja Ram
114 | 4 |  | 50/1 | DA+0 | 22.09.24 | 22.09.24 | Done | Suraja Ram
115 | 5 |  | 72/4 | DA+0 | 26.09.24 | 26.09.24 | Done | Suraja Ram
116 | 6 |  | 72/5 | DA+0 | 26.09.24 | 26.09.24 | Done | Suraja Ram
117 | 7 |  | 72/3 | DA+0 | 29.09.24 | 29.09.24 | Done | Suraja Ram
118 | 8 |  | 72/6 | DA+0 | 29.09.24 | 29.09.24 | Done | Suraja Ram
119 | 9 |  | 71/5 | DA+0 | 29.09.24 | 29.09.24 | Done | Suraja Ram
Oct'24
120 | 1 |  | 72/0 | DB1+0 | 04.10.24 | 04.10.24 | Done | Suraja Ram
121 | 2 |  | 50/0 | DC2+3 | 04.10.24 | 05.10.24 | Done | Suraja Ram
122 | 3 |  | 71/4 | DA+0 | 13.10.24 | 13.10.24 | Done | Suraja Ram
123 | 4 |  | 72/2 | DA+0 | 14.10.24 | 14.10.24 | Done | Suraja Ram
124 | 5 |  | 71/2 | DA+0 | 15.10.24 | 15.10.24 | Done | Suraja Ram
125 | 6 |  | 71/1 | DA+0 | 16.10.24 | 16.10.24 | Done | Suraja Ram
126 | 7 |  | 68/1 | DA+3 | 19.10.24 | 19.10.24 | Done | Suraja Ram
127 | 8 |  | 72/1 | DA+0 | 19.10.24 | 19.10.24 | Done | Suraja Ram
Nov'24
128 | 1 |  | 69/6 | DA+0 | 04.11.24 | 04.11.24 | Done | Suraja Ram
129 | 2 |  | 72/7 | DB1+9 | 09.11.24 | 09.11.24 | Done | Suraja Ram
130 | 3 |  | 68/6 | DA+3 | 14.11.24 | 14.11.24 | Done | Suraja Ram
131 | 4 |  | 71/3 | DA+0 | 14.11.24 | 14.11.24 | Done | Suraja Ram
132 | 5 |  | 68/3 | DA+0 | 14.11.24 | 14.11.24 | Done | Suraja Ram
133 | 6 |  | 66/2 | DA+0 | 14.11.24 | 14.11.24 | Done | Suraja Ram
134 | 7 |  | 73/0 | DD45+9 | 17.11.24 | 17.11.24 | Done | Suraja Ram
135 | 8 |  | 68/4 | DA+3 | 20.11.24 | 20.11.24 | Done | Suraja Ram
136 | 9 |  | 68/2 | DA+3 | 20.11.24 | 20.11.24 | Done | Suraja Ram
137 | 10 |  | 68/5 | DA+3 | 20.11.24 | 20.11.24 | Done | Suraja Ram
138 | 11 |  | 69/7 | DA+0 | 22.11.24 | 22.11.24 | Done | Suraja Ram
Dec'24
139 | 1 |  | 69/5 | DA+0 | 08.12.24 | 08.12.24 | Done | Suraja Ram
140 | 2 |  | 69/1 | DA+0 | 10.12.24 | 10.12.24 | Done | Suraja Ram
141 | 3 |  | 69/2 | DA+0 | 11.12.24 | 11.12.24 | Done | Suraja Ram
142 | 4 |  | 66/4 | DA+3 | 12.12.24 | 12.12.24 | Done | Suraja Ram
143 | 5 |  | 66/1 | DA+3 | 15.12.24 | 15.12.24 | Done | Suraja Ram
144 | 6 |  | 68/0 | DD45+0 | 16.12.24 | 16.12.24 | Done | Suraja Ram
145 | 7 |  | 67/1 | DB1+9 | 20.12.24 | 20.12.24 | Done | Suraja Ram
146 | 8 |  | 43/3 | DA+3 | 21.12.24 | 21.12.24 | Done | Suraja Ram
147 | 9 |  | 69/0 | DB1+0 | 22.12.24 | 22.12.24 | Done | Suraja Ram
148 | 10 |  | 58/13 | DA+0 | 26.12.24 | 26.12.24 | Done | Suraja Ram
149 | 11 |  | 69/3 | DA+0 | 26.12.24 | 26.12.24 | Done | Suraja Ram
150 | 12 |  | 69/4 |  | 27.12.24 | 27.12.24 | Done | Suraja Ram
151 | 14 |  | 38/1 | DA+3 | 29.12.24 | 29.12.24 | Done | Suraja Ram
152 | 15 |  | 38/2 | DA+6 | 30.12.24 | 30.12.24 | Done | Suraja Ram
153 | 16 |  | 69/8 | DA+0 | 31.12.24 | 31.12.24 | Done | Suraja Ram
154 | 17 |  | 69/9 | DA+0 | 31.12.24 | 31.12.24 | Done | Suraja Ram
Jan'25
155 | 1 |  | 37/3 | DA+0 | 02.01.25 | 02.01.25 | Done | Suraja Ram
156 | 2 |  | 38/3 | DA+9 | 04.01.25 | 04.01.25 | Done | Suraja Ram
157 | 3 |  | 37/4 | DA+6 | 09.01.25 | 09.01.25 | Done | Suraja Ram
158 | 4 |  | 67/0 | DD45+0 | 15.01.25 | 15.01.25 | Done | Suraja Ram
159 | 5 |  | 59/4 | DA+0 | 16.01.25 | 16.01.25 | Done | Suraja Ram
160 | 6 |  | 41/2 | DA+0 | 18.01.25 | 18.01.25 | Done | Suraja Ram
161 | 7 |  | 71/0 | DD60+0 | 12.01.25 | 12.01.25 | Done | Suraja Ram
162 | 8 |  | 37/2 | DB1+6 | 20.01.25 | 20.01.25 | Done | Suraja Ram
163 | 9 |  | 70/0 | DD60+0 | 24.01.25 | 24.01.25 | Done | Suraja Ram
Feb'25
164 | 1 |  | 41/12 | DA+3 | 01.02.25 | 01.02.25 | Done | Suraja Ram
165 | 2 |  | 41/3 | DA+0 | 01.02.25 | 01.02.25 | Done | Suraja Ram
166 | 3 |  | 37/5 | DA+3 | 02.02.25 | 02.02.25 | Done | Suraja Ram
167 | 4 |  | 37/6 | DA+6 | 03.02.25 | 04.02.25 | Done | Suraja Ram
168 | 5 |  | 37/7 | DA+3 | 04.02.25 | 04.02.25 | Done | Suraja Ram
169 | 6 |  | 37/8 | DA+0 | 06.02.25 | 06.02.25 | Done | Suraja Ram
170 | 7 |  | 41/1 | DA+3 | 07.02.25 | 07.02.25 | Done | Suraja Ram
171 | 8 |  | 42/0 | DC2+9 | 08.02.25 | 08.02.25 | Done | Suraja Ram
172 | 9 |  | 65/6 | DA+0 | 20.02.25 | 20.02.25 | Done | Suraja Ram
173 | 10 |  | 65/7 | DA+0 | 21.02.25 | 21.02.25 | Done | Suraja Ram
174 | 11 |  | 40/11 | DA+3 | 24.02.25 | 24.02.25 | Done | Suraja Ram
175 | 12 |  | 40/10 | DA+3 | 24.02.25 | 24.02.25 | Done | Suraja Ram
176 | 13 |  | 40/2 |  | 26.02.25 | 26.02.25 | Done | Suraja Ram
177 | 14 |  | 41/0 |  | 27.02.25 | 27.02.25 | Done | Suraja Ram
Mar'25
178 | 1 |  | 40/12 |  | 03.03.25 | 03.03.25 | Done | Suraja Ram
179 | 2 |  | 38/0 |  | 06.03.25 | 06.03.25 | Done | Suraja Ram
180 | 3 |  | 40/6 |  | 07.03.25 | 07.03.25 | Done | Suraja Ram
181 | 4 |  | 40/7 |  | 08.03.25 | 08.03.25 | Done | Suraja Ram
182 | 5 |  | 60/0 |  | 13.03.25 | 13.03.25 | Done | Suraja Ram
183 | 6 |  | 39/0 |  | 18.03.25 | 18.03.25 | Done | Suraja Ram
184 | 7 |  | 40/0 |  | 19.03.25 | 19.03.25 | Done | Suraja Ram
185 | 8 |  | 40/1 |  | 20.03.25 | 20.03.25 | Done | Suraja Ram
186 | 9 |  | 38/8 |  | 22.03.25 | 22.03.25 | Done | Suraja Ram
187 | 10 |  | 38/9 |  | 23.03.25 | 23.03.25 | Done | Suraja Ram
188 | 11 |  | 38/7 |  | 24.03.35 | 24.03.35 | Done | Suraja Ram

## Tack Welding - PKG-F (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Tack Welding
Cum Sl. No. | Month Sl. No. | JMC No. | Location No. | Tower Type | Depth of Fdn | Dt. of Start | Dt. of Complete | Tack Welding Status | Name of Sub-Contractor | Ramarks
Feb-24
1 | 1 |  | 59/13 | DA+3 |  | 20.02.24 | 20.02.24 | Done | Suraja Ram
2 | 2 |  | 59/14 | DA+6 |  | 22.02.24 | 22.02.24 | Done | Suraja Ram
3 | 3 |  | 62/5 | DA+0 |  | 27.02.24 | 27.02.24 | Done | Suraja Ram
4 | 4 |  | 63/6 | DA+3 |  | 28.02.24 | 28.02.24 | Done | Suraja Ram
March'24
5 | 1 |  | 63/8 | DA+3 |  | 01.03.24 | 02.03.24 | Done | Suraja Ram
6 | 2 |  | 62/3 | DA+0 |  | 03.02.24 | 03.02.24 | Done | Suraja Ram
7 | 3 |  | 62/4 | DA+3 |  | 04.03.24 | 04.03.24 | Done | Suraja Ram
8 | 4 |  | 59/12 | DA+6 |  | 05.03.24 | 05.03.24 | Done | Suraja Ram
9 | 5 |  | 59/10 | DA+0 |  | 06.03.24 | 06.03.24 | Done | Suraja Ram
10 | 6 |  | 59/9 | DA+3 |  | 07.03.24 | 07.03.24 | Done | Suraja Ram
11 | 7 |  | 60/7 | DA+3 |  | 09.03.24 | 09.03.24 | Done | Suraja Ram
12 | 8 |  | 62/2 | DA+3 |  | 10.03.24 | 10.03.24 | Done | Suraja Ram
13 | 9 |  | 62/7 | DA+3 |  | 11.03.24 | 11.03.24 | Done | Suraja Ram
14 | 10 |  | 64/1 | DA+0 |  | 12.03.24 | 12.03.24 | Done | Suraja Ram
15 | 11 |  | 59/7 | DA+3 |  | 12.03.24 | 12.03.24 | Done | Ramagora
16 | 12 |  | 64/4 | DA+3 |  | 13.03.24 | 13.03.24 | Done | Suraja Ram
17 | 13 |  | 60/11 | DA+3 |  | 15.03.24 | 15.03.24 | Done | Ramagora
18 | 14 |  | 62/8 | DA+0 |  | 15.03.24 | 15.03.24 | Done | Suraja Ram
19 | 15 |  | 65/2 | DA+0 |  | 16.03.24 | 16.03.24 | Done | Suraja Ram
20 | 16 |  | 60/6 | DA+0 |  | 16.03.24 | 16.03.24 | Done | Ramagora
21 | 17 |  | 65/4 | DA+0 |  | 17.03.24 | 17.03.24 | Done | Suraja Ram
22 | 18 |  | 64/5 | DA+3 |  | 18.03.24 | 18.03.24 | Done | Suraja Ram
23 | 19 |  | 62/9 | DA+3 |  | 19.03.24 | 19.03.24 | Done | Suraja Ram
24 | 20 |  | 60/8 | DA+0 |  | 19.03.24 | 19.03.24 | Done | Ramagora
25 | 21 |  | 62/10 | DA+0 |  | 21.03.24 | 21.03.24 | Done | Suraja Ram
26 | 22 |  | 65/3 | DA+0 |  | 22.03.24 | 22.03.24 | Done | Suraja Ram
27 | 23 |  | 59/6 | DA+3 |  | 22.03.24 | 22.03.24 | Done | Ramagora
28 | 24 |  | 60/10 | DA+0 |  | 24.03.24 | 24.03.24 | Done | Suraja Ram
29 | 25 |  | 61/6 | DA+3 |  | 28.03.24 | 28.03.24 | Done | Suraja Ram
30 | 26 |  | 65/5 | DA+0 |  | 29.03.24 | 29.03.24 | Done | Suraja Ram
Apr'24
31 | 1 |  | 64/6 | DA+0 |  | 01.04.24 | 01.04.24 | Done | Suraja Ram
32 | 2 |  | 61/7 | DA+9 |  | 03.04.24 | 03.04.24 | Done | Suraja Ram
33 | 3 |  | 65/6 | DA+0 |  | 04.04.24 | 04.04.24 | Done | Suraja Ram
34 | 4 |  | 64/7 | DA+3 |  | 06.04.24 | 06.04.24 | Done | Suraja Ram
35 | 5 |  | 63/7 | DA+3 |  | 21.04.24 | 22.04.24 | Done | Suraja Ram
36 | 6 |  | 64/9 | DA+3 |  | 24.04.24 | 24.04.24 | Done | Suraja Ram
37 | 7 |  | 61/0 | DB+0 |  | 25.04.24 | 25.04.24 | Done | Ramagora
38 | 8 |  | 65/9 | DA+0 |  | 27.04.24 | 27.04.24 | Done | Suraja Ram
39 | 9 |  | 65/11 | DA+0 |  | 28.04.24 | 28.04.24 | Done | Suraja Ram
40 | 10 |  | 67/2 | DA+0 |  | 29.04.24 | 29.04.24 | Done | Suraja Ram
41 | 11 |  | 61/2 | DA+6 |  | 29.04.24 | 30.04.24 | Done | Ramagora
May'24
42 | 1 |  | 64/10 | DA+3 |  | 05.05.24 | 05.05.24 | Done | Suraja Ram
43 | 2 |  | 67/1 | DA+0 |  | 07.05.24 | 07.05.24 | Done | Suraja Ram
44 | 3 |  | 64/8 | DA+3 |  | 09.05.24 | 09.05.24 | Done | Suraja Ram
45 | 4 |  | 65/1 | DA+0 |  | 10.05.24 | 10.05.24 | Done | Suraja Ram
46 | 5 |  | 65/0 | DB1+0 |  | 10.05.24 | 10.05.24 | Done | Suraja Ram
47 | 6 |  | 61/1 | DA+6 |  | 10.05.24 | 10.05.24 | Done | Ramagora
48 | 7 |  | 60/9 | DA+3 |  | 11.05.24 | 11.05.24 | Done | Ramagora
49 | 8 |  | 63/4 | DA+0 |  | 14.05.24 | 14.05.24 | Done | Suraja Ram
50 | 9 |  | 63/3 | DA+3 |  | 15.05.24 | 15.05.24 | Done | Suraja Ram
51 | 10 |  | 63/5 | DA+3 |  | 16.05.24 | 16.05.24 | Done | Suraja Ram
52 | 11 |  | 61/3 | DA+6 |  | 17.05.24 | 17.05.24 | Done | Ramagora
53 | 12 |  | 62/11 | DA+3 |  | 19.05.24 | 19.05.24 | Done | Suraja Ram
54 | 13 |  | 61/4 | DA+3 |  | 23.05.24 | 23.05.24 | Done | Suraja Ram
55 | 14 |  | 61/5 | DA+3 |  | 25.05.24 | 25.05.24 | Done | Suraja Ram
Jun'24
56 | 1 |  | 64/2 | DA+3 |  | 03.06.24 | 03.06.24 | Done | Suraja Ram
57 | 2 |  | 64/3 | DA+0 |  | 06.06.24 | 06.06.24 | Done | Suraja Ram |  | 125
58 | 3 |  | 64/0 | DB2+0 |  | 06.06.24 | 06.06.24 | Done | Suraja Ram
59 | 4 |  | 61/10 | DA+9 |  | 07.06.24 | 07.06.24 | Done | Suraja Ram
60 | 5 |  | 61/8 | DA+6 |  | 08.06.24 | 08.06.24 | Done | Ramagora
61 | 6 |  | 63/2 | DA+0 |  | 08.06.24 | 08.06.24 | Done | Suraja Ram
62 | 7 |  | 61/9 | DA+0 |  | 09.06.24 | 09.06.24 | Done | Ramagora
63 | 8 |  | 63/1 | DA+3 |  | 09.06.24 | 09.06.24 | Done | Suraja Ram
64 | 9 |  | 59/5 | DA+3 |  | 10.06.24 | 10.06.24 | Done | Ramagora |  | 59/16
65 | 10 |  | 63/0 | DC1+0 |  | 10.06.24 | 11.06.24 | Done | Suraja Ram |  | 48/0
66 | 11 |  | 60/5 | DA+3 |  | 11.06.24 | 11.06.24 | Done | Ramagora
67 | 12 |  | 60/4 | DA+3 |  | 13.06.24 | 13.06.24 | Done | Ramagora
68 | 13 |  | 60/3 | DA+3 |  | 23.06.24 | 23.06.24 | Done | Ramagora
69 | 14 |  | 60/2 | DA+3 |  | 25.06.24 | 25.06.24 | Done | Ramagora
70 | 15 |  | 60/1 | DA+6 |  | 30.06.24 | 30.06.24 | Done | Ramagora
Jul'24
71 | 1 |  | 59/16 | DA+9 |  | 01.07.24 | 01.07.24 | Done | Suraja Ram
72 | 2 |  | 59/15 | DA+6 |  | 02.07.24 | 02.07.24 | Done | Suraja Ram
73 | 3 |  | 60/0 | DC+0 |  | 24.07.24 | 24.07.24 | Done | Suraja Ram
74 | 4 |  | 59/8 | DB1+3 |  | 27.07.24 | 27.07.24 | Done | Suraja Ram
Aug'24
75 | 1 |  | 55/3 | DA+0 |  | 23.08.24 | 23.08.24 | Done | Suraja Ram
76 | 2 |  | 55/4 | DA+0 |  | 24.08.24 | 24.08.24 | Done | Suraja Ram
77 | 4 |  | 57/6 | DA+3 |  | 27.08.24 | 27.08.24 | Done | Suraja Ram
78 | 5 |  | 57/3 | DA+0 |  | 28.08.24 | 28.08.24 | Done | Suraja Ram
79 | 6 |  | 57/4 | DA+0 |  | 30.08.24 | 30.08.24 | Done | Suraja Ram
80 | 7 |  | 57/5 | DA+3 |  | 30.08.24 | 30.08.24 | Done | Suraja Ram
Sept'24
81 | 1 |  | 62/0 | DB2+0 |  | 15.09.24 | 15.09.24 | Done | Suraja Ram
82 | 2 |  | 62/1 | DA+3 |  | 23.09.24 | 24.09.24 | Done | Suraja Ram
83 | 3 |  | 62/6 | DA+3 |  | 25.09.24 | 26.09.24 | Done | Suraja Ram
Oct'24
84 | 1 |  | 57/7 | DA+3 |  | 05.10.24 | 06.10.24 | Done | Suraja Ram
85 | 2 |  | 50/9 | DA+0 |  | 06.10.24 | 07.10.24 | Done | Suraja Ram
86 | 3 |  | 50/10 | DA+3 |  | 09.10.24 | 09.10.24 | Done | Suraja Ram
87 | 4 |  | 50/0 | DB2+0 |  | 10.10.24 | 10.10.24 | Done | Suraja Ram
88 | 5 |  | 50/3 | DA+6 |  | 24.10.24 | 24.10.24 | Done | Suraja Ram
89 | 6 |  | 50/1 | DA+6 |  | 25.10.24 | 25.10.24 | Done | Suraja Ram
90 | 7 |  | 51/1 | DA+0 |  | 25.10.24 | 25.10.24 | Done | Suraja Ram
91 | 8 |  | 50/2 | DA+9 |  | 28.10.24 | 28.10.24 | Done | Suraja Ram
92 | 9 |  | 64/11 | DA+3 |  | 29.10.24 | 29.10.24 | Done | Suraja Ram
Nov'24
93 | 1 |  | 59/11 | DA+6 |  | 11.11.24 | 11.11.24 | Done | Suraja Ram
94 | 2 |  | 50/7 | DA+0 |  | 14.11.24 | 14.11.24 | Done | Suraja Ram
95 | 3 |  | 73/1 | DA+0 |  | 14.11.24 | 14.11.24 | Done | Suraja Ram
96 | 4 |  | 73/2 | DA+0 |  | 19.11.24 | 19.11.24 | Done | Suraja Ram
97 | 5 |  | 73/9 | DA+0 |  | 20.11.24 | 20.11.24 | Done | Suraja Ram
98 | 6 |  | 52/7 | DA+3 |  | 25.11.24 | 25.11.24 | Done | Suraja Ram
99 | 7 |  | 52/6 | DA+6 |  | 25.11.24 | 25.11.24 | Done | Suraja Ram
100 | 8 |  | 52/8 | DA+6 |  | 26.11.24 | 26.11.24 | Done | Suraja Ram
101 | 9 |  | 48/0 | DC2+0 |  | 27.11.24 | 27.11.24 | Done | Suraja Ram
102 | 10 |  | 49/4 | DA+3 |  | 27.11.24 | 27.11.24 | Done | Suraja Ram
103 | 11 |  | 48/1 | DA+9 |  | 29.11.24 | 29.11.24 | Done | Suraja Ram
104 | 12 |  | 47/10 | DA+6 |  | 29.11.24 | 29.11.24 | Done | Suraja Ram
Dec'24
105 | 1 |  | 49/7 | DA+0 |  | 02.12.24 | 02.12.24 | Done | Suraja Ram
106 | 2 |  | 49/6 | DA+0 |  | 03.12.24 | 03.12.24 | Done | Suraja Ram
107 | 3 |  | 49/5 | DA+3 |  | 04.12.24 | 04.12.24 | Done | Suraja Ram
108 | 4 |  | 59/3 | DA+3 |  | 05.12.24 | 05.12.24 | Done | Suraja Ram |  |  | 05.12.24
109 | 5 |  | 59/4 | DA+3 |  | 06.12.24 | 06.12.24 | Done | Suraja Ram
110 | 6 |  | 73/6 | DA+0 |  | 13.12.24 | 13.12.24 | Done | Suraja Ram
111 | 7 |  | 72/3 | DA+3 |  | 17.12.24 | 17.12.24 | Done | Suraja Ram
112 | 8 |  | 59/1 | DA+3 |  | 18.12.24 | 18.12.24 | Done | Suraja Ram
113 | 9 |  | 59/2 | DA+3 |  | 20.12.24 | 20.12.24 | Done | Suraja Ram
114 | 10 |  | 50/8 | DA+9 |  | 23.12.24 | 23.12.24 | Done | Suraja Ram
115 | 11 |  | 73/8 | DA+0 |  | 25.12.24 | 25.12.24 | Done | Suraja Ram
116 | 12 |  | 51/2 | DA+0 |  | 26.12,24 | 26.12,24 | Done | Suraja Ram
117 | 13 |  | 49/2 | DA+0 |  | 26.12,24 | 26.12,24 | Done | Suraja Ram
118 | 14 |  | 49/3 | DA+3 |  | 26.12,24 | 26.12,24 | Done | Suraja Ram
119 | 15 |  | 49/1 | DA+0 |  | 28.12.24 | 28.12.24 | Done | Suraja Ram
2025-01-25
120 | 1 |  | 50/4 | DA+9 |  | 06.01.25 | 06.01.25 | Done | Suraja Ram
121 | 2 |  | 59/0 | DC2+0 |  | 07.01.25 | 07.01.25 | Done | Suraja Ram
122 | 3 |  | 50/6 | DA+9 |  | 12.01.25 | 12.01.25 | Done | Suraja Ram
123 | 4 |  | 65/7 | DA+0 |  | 17.01.25 | 17.01.25 | Done | Suraja Ram
124 | 5 |  | 65/8 | DA+0 |  | 18.01.25 | 18.01.25 | Done | Suraja Ram
125 | 6 |  | 73/3 | DA+0 |  | 27.01.25 | 27.01.25 | Done | Suraja Ram
126 | 7 |  | 73/4 | DA+0 |  | 28.01.25 | 29.01.25 | Done | Suraja Ram
2025-02-25
127 | 1 |  | 73/7 | DA+0 |  | 13.02.25 | 13.02.25 | Done | Suraja Ram
128 | 2 |  | 74/0 | DB+0 |  | 14.02.25 | 14.02.25 | Done | Suraja Ram
129 | 3 |  | 73/5 | DA+0 |  | 15.02.25 | 15.02.25 | Done | Suraja Ram
130 | 4 |  | 65/10 | DA+0 |  | 17.02.25 | 17.02.25 | Done | Suraja Ram
131 | 5 |  | 66/0 | DC2+6 |  | 19.02.25 | 19.02.25 | Done | Suraja Ram
132 | 6 |  | 51/0 | DC2+0 |  | 26.02.25 | 26.02.25 | Done | Suraja Ram
133 | 1 |  | 50/5 |  |  | 02.03.25 | 02.03.25 | Done | Suraja Ram
134 | 2 |  | 52/0 |  |  | 05.03.25 | 05.03.25 | Done | Suraja Ram
135 | 3 |  | 49/0 |  |  | 10.03.25 | 10.03.25 | Done | Suraja Ram
136 | 4 |  | 52/9 |  |  | 11.03.25 | 11.03.25 | Done | Suraja Ram
137 | 5 |  | 52/10 |  |  | 12.03.25 | 12.03.25 | Done | Suraja Ram
138 | 6 |  | 73/0 |  |  | 13.03.25 | 13.03.25 | Done | Suraja Ram
139 | 7 |  | 52/5 |  |  | 17.3.25 | 17.3.25 | Done | Suraja Ram

## Painting - PKG-G (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Painting
Cum Sl. No. | Month Sl. No. | JMC No. | Location No. | Tower Type | Depth of Fdn | Dt. of Start | Dt. of Complete | Tack Welding Status | Name of Sub-Contractor | Ramarks
2023-12-01
1 | 1 |  | 56/9 | DA+3 |  | 02.12.23 | 03.12.23 | Done | Suraja Ram
2 | 2 |  | 57/1 | DA+3 |  | 02.12.23 | 03.12.23 | Done | Suraja Ram
3 | 3 |  | 56/8 | DA+3 |  | 03.12.23 | 06.12.23 | Done | Suraja Ram
4 | 4 |  | 57/2 | DA+0 |  | 04.12.23 | 08.12.23 | Done | Suraja Ram
5 | 5 |  | 57/3 | DA+0 |  | 04.12.23 | 08.12.23 | Done | Suraja Ram
6 | 6 |  | 57/4 | DA+0 |  | 04.12.23 | 08.12.23 | Done | Suraja Ram
7 | 7 |  | 57/5 | DA+3 |  | 04.12.23 | 08.12.23 | Done | Suraja Ram
8 | 8 |  | 57/8 | DA+3 |  | 05.12.23 | 09.12.23 | Done | Suraja Ram
9 | 9 |  | 57/9 | DA+0 |  | 05.12.23 | 09.12.23 | Done | Suraja Ram
10 | 10 |  | 57/10 | DA+0 |  | 05.12.23 | 09.12.23 | Done | Suraja Ram
11 | 11 |  | 57/11 | DA+0 |  | 09.12.23 | 10.12.23 | Done | Suraja Ram
12 | 12 |  | 57/12 | DA+3 |  | 10.12.23 | 11.12.23 | Done | Suraja Ram
13 | 13 |  | 58/14 | DA+0 |  | 08.12.23 | 11.12.23 | Done | Suraja Ram
14 | 14 |  | 57/13 | DA+0 |  | 12.12.23 | 16.12.23 | Done | Suraja Ram
15 | 15 |  | 58/8 | DA+0 |  | 12.12.23 | 16.12.23 | Done | Suraja Ram
16 | 16 |  | 58/9 | DA+0 |  | 12.12.23 | 16.12.23 | Done | Suraja Ram
17 | 17 |  | 58/11 | DA+3 |  | 14.12.23 | 17.12.23 | Done | Suraja Ram
18 | 18 |  | 58/10 | DA+3 |  | 15.12.23 | 17.12.23 | Done | Suraja Ram
19 | 19 |  | 58/12 | DA+0 |  | 15.12.23 | 17.12.23 | Done | Suraja Ram
20 | 20 |  | 56/7 | DA+3 |  | 17.12.23 | 17.12.23 | Done | Suraja Ram
21 | 21 |  | 58/16 | DA+0 |  | 18.12.23 | 18.12.23 | Done | Suraja Ram
22 | 22 |  | 59/1 | DA+0 |  | 18.12.23 | 18.12.23 | Done | Suraja Ram
23 | 23 |  | 59/2 | DA+0 |  | 20.12.23 | 20.12.23 | Done | Suraja Ram
24 | 24 |  | 59/3 | DA+0 |  | 21.12.23 | 21.12.23 | Done | Suraja Ram
25 | 25 |  | 59/5 | DA+0 |  | 22.12.23 | 22.12.23 | Done | Suraja Ram
26 | 26 |  | 59/6 | DA+0 |  | 23.12.23 | 24.12.23 | Done | Suraja Ram
27 | 27 |  | 56/3 | DA+0 |  | 25.12.23 | 27.12.23 | Done | Suraja Ram
28 | 28 |  | 56/4 | DA+3 |  | 26.12.23 | 27.12.23 | Done | Suraja Ram
29 | 29 |  | 55/4 | DA+3 |  | 26.12.23 | 27.12.23 | Done | Suraja Ram
30 | 30 |  | 55/5 | DA+0 |  | 28.12.23 | 28.12.23 | Done | Suraja Ram
31 | 31 |  | 55/6 | DA+3 |  | 29.12.23 | 30.12.23 | Done | Suraja Ram
2024-01-01
32 | 1 |  | 55/11 | DA+3 |  | 08.01.24 | 09.01.24 | Done | Suraja Ram
33 | 2 |  | 55/10 | DA+3 |  | 10.01.24 | 10.01.24 | Done | Suraja Ram
34 | 3 |  | 58/1 | DA+0 |  | 18.01.24 | 19.01.24 | Done | Suraja Ram
35 | 4 |  | 58/6 | DA+3 |  | 19.01.24 | 20.01.24 | Done | Suraja Ram
36 | 5 |  | 58/5 | DA+3 |  | 19.01.24 | 20.01.24 | Done | Suraja Ram
37 | 6 |  | 58/4 | DA+0 |  | 20.01.24 | 20.01.24 | Done | Suraja Ram
38 | 7 |  | 57/6 | DB1+0 |  | 21.01.24 | 21.01.24 | Done | Suraja Ram
39 | 8 |  | 57/7 | DA+3 |  | 21.01.24 | 21.01.24 | Done | Suraja Ram
40 | 9 |  | 51/7 | DA+3 |  | 21.01.24 | 21.01.24 | Done | Kailash Nath
41 | 10 |  | 51/5 | DA+0 |  | 22.01.24 | 22.01.24 | Done | Kailash Nath
42 | 11 |  | 57/0 | DB2+0 |  | 22.01.24 | 22.01.24 | Done | Suraja Ram
43 | 12 |  | 56/6 | DA+3 |  | 22.01.24 | 22.01.24 | Done | Suraja Ram
44 | 13 |  | 56/5 | DA+0 |  | 23.01.24 | 23.01.24 | Done | Suraja Ram |  | comp
45 | 14 |  | 56/2 | DA+3 |  | 23.01.24 | 23.01.24 | Done | Suraja Ram
46 | 15 |  | 51/4 | DA+3 |  | 23.01.24 | 23.01.24 | Done | Kailash Nath
47 | 16 |  | 51/3 | DA+0 |  | 23.01.24 | 23.01.24 | Done | Kailash Nath
48 | 17 |  | 51/2 | DA+0 |  | 24.01.24 | 24.01.24 | Done | Kailash Nath
49 | 18 |  | 56/0 | DB1+0 |  | 24.01.24 | 24.01.24 | Done | Suraja Ram
50 | 19 |  | 55/9 | DA+3 |  | 25.01.24 | 25.01.24 | Done | Suraja Ram
51 | 20 |  | 55/8 | DA+3 |  | 25.01.24 | 25.01.24 | Done | Suraja Ram
52 | 21 |  | 52/2 | DA+3 |  | 25.01.24 | 25.01.24 | Done | Kailash Nath
53 | 22 |  | 52/5 | DA+3 |  | 25.01.24 | 25.01.24 | Done | Kailash Nath
54 | 23 |  | 51/10 | DA+3 |  | 27.01.24 | 27.01.24 | Done | Kailash Nath
55 | 24 |  | 52/1 | DA+0 |  | 27.01.24 | 27.01.24 | Done | Kailash Nath
56 | 25 |  | 55/7 | DA+0 |  | 26.01.24 | 26.01.24 | Done | Suraja Ram
57 | 26 |  | 58/3 | DA+3 |  | 30.01.24 | 30.01.24 | Done | Suraja Ram
58 | 27 |  | 58/7 | DB+0 |  | 29.01.24 | 29.01.24 | Done | Suraja Ram
Feb-24
59 | 1 |  | 59/0 | DB+0 |  | 02.02.24 | 02.02.24 | Done | Suraja Ram
60 | 2 |  | 58/15 | DA+3 |  | 02.02.24 | 02.02.24 | Done | Suraja Ram
61 | 3 |  | 61/1 | DA+0 |  | 03.02.24 | 03.02.24 | Done | Suraja Ram
62 | 4 |  | 55/1 | DA+3 |  | 04.02.24 | 04.02.24 | Done | Suraja Ram
63 | 5 |  | 55/3 | DA+0 |  | 06.02.24 | 06.02.24 | Done | Suraja Ram
64 | 6 |  | 55/2 | DA+3 |  | 04.02.24 | 05.02.24 | Done | Suraja Ram |  |  | 52/4
65 | 7 |  | 41/5 | DA+0 |  | 15.02.24 | 15.02.24 | Done | Ramagora
66 | 8 |  | 41/7 | DA+3 |  | 15.02.24 | 15.02.24 | Done | Ramagora
67 | 9 |  | 41/10 | DA+3 |  | 28.01.24 | 16.02.24 | Done | Ramagora
68 | 10 |  | 41/11 | DA+3 |  | 29.01.24 | 17.02.24 | Done | Ramagora
69 | 11 |  | 46/2 | DA+0 |  | 17.02.24 | 18.02.24 | Done | Suraja Ram
70 | 12 |  | 43/1 | DA+9 |  | 10.02.24 | 18.02.24 | Done | Ramagora
71 | 13 |  | 44/2 | DA+0 |  | 27.01.24 | 18.02.24 | Done | Ramagora
72 | 14 |  | 47/0 | DB+0 |  | 19.02.24 | 19.02.24 | Done | Suraja Ram
73 | 15 |  | 48/2 | DA+3 |  | 19.02.24 | 19.02.24 | Done | Suraja Ram
74 | 16 |  | 53/3 | DA+3 |  | 19.02.24 | 19.02.24 | Done | Suraja Ram
75 | 17 |  | 44/4 | DA+0 |  | 19.02.24 | 19.02.24 | Done | Ramagora
76 | 18 |  | 46/3 | DA+0 |  | 20.02.24 | 20.02.24 | Done | Ramagora
77 | 19 |  | 47/2 | DA+0 |  | 22.02.24 | 22.02.24 | Done | Ramagora
78 | 20 |  | 50/3 | DA+0 |  | 22.02.24 | 22.02.24 | Done | Ramagora
79 | 21 |  | 48/1 | DA+0 |  | 03.02.24 | 22.02.24 | Done | Ramagora
80 | 22 |  | 50/4 | DA+3 |  | 23.02.24 | 23.02.24 | Done | Ramagora
81 | 23 |  | 51/6 | DA+0 |  | 24.02.24 | 24.02.24 | Done | Ramagora
82 | 24 |  | 51/8 | DA+3 |  | 24.02.24 | 24.02.24 | Done | Ramagora
83 | 25 |  | 51/9 | DA+3 |  | 25.02.24 | 25.02.24 | Done | Ramagora
84 | 26 |  | 53/4 | DA+3 |  | 25.02.24 | 25.02.24 | Done | Suraja Ram
85 | 27 |  | 53/1 | DA+0 |  | 25.02.24 | 25.02.24 | Done | Suraja Ram
86 | 28 |  | 52/0 | DB+0 |  | 26.02.24 | 26.02.24 | Done | Suraja Ram
87 | 29 |  | 52/4 | DA+0 |  | 27.02.24 | 27.02.24 | Done | Ramagora
March'24
88 | 1 |  | 41/8 | DA+0 |  | 08.03.24 | 08.03.24 | Done | Ramagora
89 | 2 |  | 41/4 | DA+0 |  | 08.03.24 | 08.03.24 | Done | Ramagora
90 | 3 |  | 41/6 | DA+0 |  | 08.03.24 | 08.03.24 | Done | Ramagora
91 | 4 |  | 41/9 | DA+0 |  | 08.03.24 | 08.03.24 | Done | Ramagora
92 | 5 |  | 43/4 | DA+9 |  | 10.03.24 | 10.03.24 | Done | Ramagora
93 | 6 |  | 43/5 | DA+0 |  | 10.03.24 | 10.03.24 | Done | Ramagora
94 | 7 |  | 51/1 | DA+0 |  | 14.03.24 | 14.03.24 | Done | Ramagora
95 | 8 |  | 53/2 | DA+3 |  | 23.03.24 | 23.03.24 | Done | Suraja Ram
96 | 9 |  | 51/0 | DB+0 |  | 29.03.24 | 29.03.24 | Done | Ramagora
97 | 10 |  | 44/3 | DA+3 |  | 30.03.24 | 30.03.24 | Done | Ramagora
April'24
98 | 1 |  | 47/3 | DA+0 |  | 23.04.24 | 23.04.24 | Done | Ramagora
99 | 2 |  | 56/1 | DA+3 |  | 29.04.24 | 29.04.24 | Done | Ramagora
May'24
100 | 1 |  | 61/2 | DA+0 | 06.05.24 | 12.05.24 | 12.05.24 | Done | Suraja Ram
101 | 2 |  | 44/1 | DA+0 | 12.05.24 | 13.05.24 | 13.05.24 | Done | Ramagora
102 | 3 |  | 58/0 | DC2+0 | 04.05.24 | 13.05.24 | 13.05.24 | Done | Suraja Ram
103 | 4 |  | 55/0 | DC+0 | 24.05.24 | 26.05.24 | 26.05.24 | Done | Suraja Ram
June'24
104 | 1 |  | 65/5 | DA+0 | 30.05.24 | 02.06.24 | 02.06.24 | Done | Suraja Ram
105 | 2 |  | 65/4 | DA+0 | 31.05.24 | 02.06.24 | 02.06.24 | Done | Suraja Ram
106 | 3 |  | 58/2 | DA+0 | 02.06.24 | 02.06.24 | 02.06.24 | Done | Suraja Ram
107 | 4 |  | 65/3 | DA+0 | 02.06.24 | 03.06.24 | 03.06.24 | Done | Suraja Ram
108 | 5 |  | 52/3 | DA+0 |  | 24.06.24 | 24.06.24 | Done | Suraja Ram
109 | 6 |  | 53/0 | DC2+3 | 22.06.24 | 25.06.24 | 25.06.24 | Done | Suraja Ram
Sept'24
110 | 1 |  | 48/0 | DB+0 | 23.07.24 | 24.07.24 | 24.07.24 | Done | Suraja Ram
111 | 2 |  | 46/4 | DA+0 | 16.09.24 | 21.09.24 | 21.09.24 | Done | Suraja Ram
112 | 3 |  | 47/1 | DA+0 | 19.09.24 | 21.09.24 | 21.09.24 | Done | Suraja Ram
113 | 4 |  | 50/2 | DA+0 | 20.09.24 | 22.09.24 | 22.09.24 | Done | Suraja Ram
114 | 5 |  | 50/1 | DA+0 | 22.09.24 | 24.09.24 | 24.09.24 | Done | Suraja Ram
115 | 6 |  | 72/5 | DA+0 | 26.09.24 | 26.09.24 | 26.09.24 | Done | Suraja Ram
116 | 7 |  | 72/3 | DA+0 |  | 29.09.24 | 29.09.24 | Done | Suraja Ram
117 | 8 |  | 72/4 | DA+0 |  | 29.09.24 | 29.09.24 | Done | Suraja Ram
118 | 9 |  | 72/6 | DA+0 | 29.09.24 | 30.09.24 | 30.09.24 | Done | Suraja Ram
119 | 10 |  | 71/5 | DA+0 | 29.09.24 | 30.09.24 | 30.09.24 | Done | Suraja Ram
Oct'24
120 | 1 |  | 50/0 | DC2+3 | 04.10.24 | 08.10.24 | 08.10.24 | Done | Suraja Ram
121 | 2 |  | 72/0 | DB1+0 | 04.10.24 | 04.10.24 | 16.10.24 | Done | Suraja Ram
122 | 3 |  | 71/4 | DA+0 | 13.10.24 | 13.10.24 | 16.10.24 | Done | Suraja Ram
123 | 4 |  | 72/2 | DA+0 | 14.10.24 | 14.10.24 | 14.10.24 | Done | Suraja Ram
124 | 5 |  | 71/2 | DA+0 | 15.10.24 | 15.10.24 | 17.10.24 | Done | Suraja Ram
125 | 6 |  | 71/1 | DA+0 | 16.10.24 | 16.10.24 | 17.10.24 | Done | Suraja Ram
126 | 7 |  | 68/1 | DA+3 | 19.10.24 | 19.10.24 | 19.10.24 | Done | Suraja Ram
127 | 8 |  | 72/1 | DA+0 | 19.10.24 | 19.10.24 | 19.10.24 | Done | Suraja Ram
Nov'24
128 | 1 |  | 72/7 | DB1+9 | 09.11.24 | 09.11.24 | 09.11.24 | Done | Suraja Ram
129 | 2 |  | 68/6 | DA+3 | 14.11.24 | 15.11.24 | 15.11.24 | Done | Suraja Ram
130 | 3 |  | 71/3 | DA+0 | 14.11.24 | 14.11.24 | 14.11.24 | Done | Suraja Ram
131 | 4 |  | 68/3 | DA+0 | 14.11.24 | 14.11.24 | 14.11.24 | Done | Suraja Ram
132 | 5 |  | 66/2 | DA+0 | 14.11.24 | 14.11.24 | 14.11.24 | Done | Suraja Ram
133 | 6 |  | 73/0 | DD45+9 |  | 18.11.24 | 18.11.24 | Done | Suraja Ram
134 | 7 |  | 68/4 | DA+3 | 20.11.24 | 20.11.24 | 20.11.24 | Done | Suraja Ram
135 | 8 |  | 69/6 | DA+0 | 04.11.24 | 04.11.24 | 04.11.24 | Done | Suraja Ram
136 | 9 |  | 68/2 | DA+3 | 20.11.24 | 20.11.24 | 20.11.24 | Done | Suraja Ram
137 | 10 |  | 68/5 | DA+3 | 20.11.24 | 20.11.24 | 20.11.24 | Done | Suraja Ram
Dec'24
138 | 1 |  | 69/5 | DA+0 | 08.12.24 | 08.12.24 | 08.12.24 | Done | Suraja Ram
139 | 2 |  | 69/1 | DA+0 | 10.12.24 | 10.12.24 | 10.12.24 | Done | Suraja Ram
140 | 3 |  | 69/2 | DA+0 | 11.12.24 | 11.12.24 | 11.12.24 | Done | Suraja Ram
141 | 4 |  | 66/4 | DA+3 | 12.12.24 | 12.12.24 | 12.12.24 | Done | Suraja Ram
142 | 5 |  | 66/1 | DA+3 | 15.12.24 | 15.12.24 | 15.12.24 | Done | Suraja Ram
143 | 6 |  | 68/0 | DD+0 | 16.12.24 | 16.12.24 | 16.12.24 | Done | Suraja Ram
144 | 7 |  | 43/3 | DA+3 | 22.12.24 | 22.12.24 | 22.12.24 | Done | Suraja Ram
145 | 8 |  | 69/7 | DA+0 | 22.11.24 | 22.11.24 | 22.11.24 | Done | Suraja Ram
146 | 9 |  | 69/0 | DB1+0 | 22.12.24 | 25.12.24 | 25.12.24 | Done | Suraja Ram
147 | 10 |  | 69/8 | DA+0 | 31.12.24 | 31.12.24 | 31.12.24 | Done | Suraja Ram
148 | 11 |  | 69/9 | DA+0 | 31.12.24 | 31.12.24 | 31.12.24 | Done | Suraja Ram
2025-01-25
149 | 1 |  | 67/1 | DB1+9 | 20.12.24 | 02.01.25 | 02.01.25 | Done | Suraja Ram
150 | 2 |  | 38/1 | DA+3 | 29.12.24 | 03.01.25 | 03.01.25 | Done | Suraja Ram
151 | 3 |  | 38/2 | DA+6 | 30.12.24 | 03.01.25 | 03.01.25 | Done | Suraja Ram
152 | 4 |  | 69/3 | DA+0 | 26.12.24 | 04.01.25 | 04.01.25 | Done | Suraja Ram
153 | 5 |  | 69/4 |  | 27.12.24 | 04.01.25 | 04.01.25 | Done | Suraja Ram
154 | 6 |  | 37/3 | DA+0 | 02.01.25 | 04.01.25 | 04.01.25 | Done | Suraja Ram
155 | 7 |  | 38/3 | DA+9 | 04.01.25 | 04.01.25 | 04.01.25 | Done | Suraja Ram
156 | 8 |  | 37/4 | DA+6 | 09.01.25 | 09.01.25 | 09.01.25 | Done | Suraja Ram
157 | 9 |  | 41/2 | DA+0 |  | 19.01.25 | 19.01.25 | Done | Suraja Ram
158 | 10 |  | 71/0 | DD60+0 |  | 13.01.25 | 13.01.25 | Done | Suraja Ram
159 | 11 |  | 37/2 | DB1+6 | 20.01.25 | 22.01.25 | 22.01.25 | Done | Suraja Ram
160 | 12 |  | 59/4 | DA+0 | 16.01.25 | 23.01.25 | 23.01.25 | Done | Suraja Ram
161 | 13 |  | 70/0 | DD60+0 |  | 25.01.25 | 25.01.25 | Done | Suraja Ram
162 | 14 |  | 67/0 | DD45+0 |  | 24.01.25 | 24.01.25 | Done | Suraja Ram
Feb'25
163 | 1 |  | 41/12 | DA+3 |  | 02.02.25 | 02.02.25 | Done | Suraja Ram
164 | 2 |  | 41/3 | DA+0 |  | 02.02.25 | 02.02.25 | Done | Suraja Ram
165 | 3 |  | 37/5 | DA+3 |  | 03.02.25 | 03.02.25 | Done | Suraja Ram
166 | 4 |  | 37/6 | DA+6 |  | 04.02.25 | 04.02.25 | Done | Suraja Ram
167 | 5 |  | 37/7 | DA+3 |  | 05.02.25 | 05.02.25 | Done | Suraja Ram
168 | 6 |  | 37/8 | DA+0 |  | 06.02.25 | 06.02.25 | Done | Suraja Ram
169 | 7 |  | 41/1 | DA+3 |  | 08.02.25 | 08.02.25 | Done | Suraja Ram
170 | 8 |  | 42/0 | DC2+9 |  | 09.02.25 | 09.02.25 | Done | Suraja Ram
171 | 9 |  | 65/6 |  | 20.02.25 | 21.02.25 | 21.02.25 | Done | Suraja Ram
172 | 10 |  | 40/11 | DA+3 | 24.02.25 | 28.02.25 | 28.02.25 | Done | Suraja Ram
173 | 11 |  | 40/10 | DA+3 | 24.02.25 | 28.02.25 | 28.02.25 | Done | Suraja Ram
Feb'25
174 | 1 |  | 40/2 |  | 26.02.25 | 01.03.25 | 01.3.25 | Done | Suraja Ram
175 | 2 |  | 41/0 |  | 27.02.25 | 01.03.25 | 01.03.25 | Done | Suraja Ram
176 | 3 |  | 40/12 |  | 03.03.25 | 03.03.25 | 03.03.25 | Done | Suraja Ram
177 | 4 |  | 65/7 | DA+0 | 21.02.25 | 21.02.25 | 21.02.25 | Done | Suraja Ram
178 | 5 |  | 58/13 | DA+0 | 26.12.24 | 26.12.24 | 26.12.24 | Done | Suraja Ram
179 | 1 |  | 40/6 |  | 07.03.25 | 07.03.25 | 07.03.25 | Done | Suraja Ram
180 | 2 |  | 60/0 |  | 13.03.25 | 16.03.25 | 16.03.25 | Done | Suraja Ram
181 | 6 |  | 39/0 |  | 18.03.25 | 18.03.25 | 18.03.25 | Done | Suraja Ram
182 | 7 |  | 40/0 |  | 19.03.25 | 19.03.25 | 19.03.25 | Done | Suraja Ram
183 | 8 |  | 40/1 |  | 20.03.25 | 20.03.25 | 20.03.25 | Done | Suraja Ram
184 | 4 |  | 40/7 |  | 08.03.25 | 08.03.25 | 08.03.25 | Done | Suraja Ram
185 | 5 |  | 38/0 |  | 06.03.25 | 06.03.25 | 06.03.25 | Done | Suraja Ram
186 | 9 |  | 38/8 |  | 22.03.25 | 22.03.25 | 22.03.25 | Done | Suraja Ram
187 | 10 |  | 38/9 |  | 23.03.25 | 23.03.25 | 23.03.25 | Done | Suraja Ram

## Painting - PKG-F (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Painting
Cum Sl. No. | Month Sl. No. | JMC No. | Location No. | Tower Type | Depth of Fdn | Dt. of Start | Dt. of Complete | Tack Welding Status | Name of Sub-Contractor | Ramarks
1 | 1 |  | 59/14 | DA+6 |  | 26.02.24 | 26.02.24 | Done | Suraja Ram
2 | 2 |  | 63/6 | DA+3 |  | 29.02.24 | 29.02.24 | Done | Suraja Ram
March'24
3 | 1 |  | 62/3 | DA+0 |  | 11.03.24 | 11.03.24 | Done | Suraja Ram
4 | 2 |  | 62/4 | DA+3 |  | 11.03.24 | 11.03.24 | Done | Suraja Ram
5 | 3 |  | 62/2 | DA+3 |  | 11.03.24 | 11.03.24 | Done | Suraja Ram
6 | 4 |  | 59/7 | DA+3 |  | 12.03.24 | 13.03.24 | Done | Ramagora
7 | 5 |  | 59/9 | DA+3 |  | 14.03.24 | 14.03.24 | Done | Suraja Ram
8 | 6 |  | 59/12 | DA+6 |  | 14.03.24 | 14.03.24 | Done | Suraja Ram
9 | 7 |  | 59/10 | DA+0 |  | 14.03.24 | 14.03.24 | Done | Suraja Ram
10 | 8 |  | 63/8 | DA+3 |  | 15.03.24 | 15.03.24 | Done | Suraja Ram
11 | 9 |  | 62/7 | DA+3 |  | 15.03.24 | 15.03.24 | Done | Suraja Ram
12 | 10 |  | 62/8 | DA+0 |  | 16.03.24 | 16.03.24 | Done | Suraja Ram
13 | 11 |  | 64/4 | DA+3 |  | 16.03.24 | 16.03.24 | Done | Suraja Ram
14 | 12 |  | 60/6 | DA+0 |  | 16.03.24 | 16.03.24 | Done | Ramagora
15 | 13 |  | 60/11 | DA+3 |  | 18.03.24 | 18.03.24 | Done | Ramagora
16 | 14 |  | 64/5 | DA+3 |  | 20.03.24 | 20.03.24 | Done | Suraja Ram
17 | 15 |  | 62/9 | DA+3 |  | 20.03.24 | 20.03.24 | Done | Suraja Ram
18 | 16 |  | 60/8 | DA+0 |  | 21.03.24 | 21.03.24 | Done | Ramagora
19 | 17 |  | 65/4 | DA+0 |  | 21.03.24 | 21.03.24 | Done | Suraja Ram
20 | 18 |  | 65/2 | DA+0 |  | 16.03.24 | 16.03.24 | Done | Suraja Ram
21 | 19 |  | 60/7 | DA+3 |  | 23.03.24 | 23.03.24 | Done | Suraja Ram
22 | 20 |  | 59/13 | DA+3 |  | 23.03.24 | 23.03.24 | Done | Suraja Ram
23 | 21 |  | 59/6 | DA+3 |  | 23.03.24 | 23.03.24 | Done | Ramagora
24 | 22 |  | 60/10 | DA+0 |  | 26.03.24 | 26.03.24 | Done | Suraja Ram
25 | 23 |  | 62/10 | DA+0 |  | 26.03.24 | 26.03.24 | Done | Suraja Ram
26 | 24 |  | 61/6 | DA+3 |  | 28.03.24 | 28.03.24 | Done | Suraja Ram
27 | 25 |  | 64/1 | DA+0 |  | 28.03.24 | 28.03.24 | Done | Suraja Ram
28 | 26 |  | 62/5 | DA+0 |  | 28.03.24 | 28.03.24 | Done | Suraja Ram
29 | 27 |  | 65/3 | DA+0 |  | 29.03.24 | 29.03.24 | Done | Suraja Ram
30 | 28 |  | 65/5 | DA+0 |  | 31.03.24 | 31.03.24 | Done | Suraja Ram
April'24
31 | 1 |  | 61/7 | DA+9 |  | 03.04.24 | 03.04.24 | Done | Suraja Ram
32 | 2 |  | 64/6 | DA+0 |  | 06.04.24 | 06.04.24 | Done | Suraja Ram
33 | 3 |  | 65/6 | DA+0 |  | 06.04.24 | 06.04.24 | Done | Suraja Ram
34 | 4 |  | 61/0 | DB+0 |  | 28.04.24 | 28.04.24 | Done | Ramagora
35 | 5 |  | 63/7 | DA+3 |  | 29.04.24 | 30.04.24 | Done | Suraja Ram
May'24
36 | 1 |  | 65/9 | DA+0 |  | 02.05.24 | 02.05.24 | Done | Suraja Ram
37 | 2 |  | 64/7 | DA+3 |  | 02.05.24 | 02.05.24 | Done | Suraja Ram
38 | 3 |  | 61/2 | DA+6 |  | 02.05.24 | 02.05.24 | Done | Ramagora
39 | 4 |  | 64/9 | DA+3 |  | 02.05.24 | 02.05.24 | Done | Suraja Ram
40 | 5 |  | 65/11 | DA+0 |  | 03.05.24 | 03.05.24 | Done | Suraja Ram
41 | 6 |  | 64/8 | DA+3 |  | 11.05.24 | 11.05.24 | Done | Suraja Ram
42 | 7 |  | 65/1 | DA+0 |  | 11.05.24 | 11.05.24 | Done | Suraja Ram
43 | 8 |  | 64/10 | DA+3 |  | 11.05.24 | 11.05.24 | Done | Suraja Ram
44 | 9 |  | 67/1 | DA+0 |  | 12.05.24 | 12.05.24 | Done | Suraja Ram
45 | 10 |  | 67/2 | DA+0 |  | 12.05.24 | 12.05.24 | Done | Suraja Ram
46 | 11 |  | 65/0 | DB1+0 |  | 13.05.24 | 13.05.24 | Done | Suraja Ram
47 | 12 |  | 60/9 | DA+3 |  | 11.05.24 | 11.05.24 | Done | Ramagora
48 | 13 |  | 63/4 | DA+0 |  | 17.05.24 | 17.05.24 | Done | Suraja Ram
49 | 14 |  | 63/3 | DA+3 |  | 17.05.24 | 17.05.24 | Done | Suraja Ram
50 | 15 |  | 61/1 | DA+6 |  | 18.05.24 | 18.05.24 | Done | Ramagora
51 | 16 |  | 61/3 | DA+6 |  | 18.05.24 | 18.05.24 | Done | Ramagora
52 | 17 |  | 63/5 | DA+3 |  | 20.05.24 | 20.05.24 | Done | Suraja Ram
53 | 18 |  | 62/11 | DA+3 |  | 20.05.24 | 20.05.24 | Done | Suraja Ram
54 | 13 |  | 61/4 | DA+3 |  | 23.05.24 | 23.05.24 | Done | Suraja Ram
55 | 1`4 |  | 61/5 | DA+3 |  | 25.05.24 | 25.05.24 | Done | Suraja Ram
June'24
56 | 1 |  | 64/2 | DA+3 |  | 04.06.24 | 04.06.24 | Done | Suraja Ram
57 | 2 |  | 64/0 | DB2+0 |  | 06.06.24 | 06.06.24 | Done | Suraja Ram
58 | 3 |  | 63/0 | DC1+0 |  | 10.06.24 | 11.06.24 | Done | Suraja Ram
59 | 4 |  | 60/5 | DA+3 |  | 12.06.24 | 12.06.24 | Done | Ramagora
60 | 5 |  | 61/10 | DA+9 |  | 12.06.24 | 12.06.24 | Done | Suraja Ram
61 | 6 |  | 63/1 | DA+3 |  | 12.06.24 | 12.06.24 | Done | Suraja Ram
62 | 7 |  | 63/2 | DA+0 |  | 12.06.24 | 12.06.24 | Done | Suraja Ram
63 | 8 |  | 64/3 | DA+0 |  | 12.06.24 | 12.06.24 | Done | Suraja Ram
64 | 9 |  | 60/4 | DA+3 |  | 13.06.24 | 13.06.24 | Done | Ramagora
65 | 10 |  | 59/5 | DA+3 |  | 14.06.24 | 14.06.24 | Done | Ramagora
66 | 11 |  | 61/8 | DA+6 |  | 15.06.24 | 15.06.24 | Done | Ramagora
67 | 12 |  | 61/9 | DA+0 |  | 15.06.24 | 15.06.24 | Done | Ramagora
68 | 13 |  | 60/3 | DA+3 |  | 23.06.24 | 23.06.24 | Done | Ramagora
69 | 14 |  | 60/2 | DA+3 |  | 25.06.24 | 25.06.24 | Done | Ramagora
July'24
70 | 1 |  | 60/1 | DA+6 |  | 01.07.24 | 01.07.24 | Done | Ramagora
71 | 2 |  | 60/0 | DC+0 |  | 24.07.24 | 24.07.24 | Done | Suraja Ram
72 | 3 |  | 59/16 | DA+9 |  | 01.07.24 | 01.07.24 | Done | Suraja Ram
73 | 4 |  | 59/15 | DA+6 |  | 02.07.24 | 02.07.24 | Done | Suraja Ram
74 | 5 |  | 59/8 | DB1+3 |  | 27.07.24 | 27.07.24 | Done | Suraja Ram
Sept'24
75 | 1 |  | 55/3 | DA+0 |  | 01.09.24 | 01.09.24 | Done | Suraja Ram
76 | 2 |  | 55/4 | DA+0 |  | 02.09.24 | 02.09.24 | Done | Suraja Ram
77 | 3 |  | 62/6 | DA+3 |  | 03.09.24 | 03.09.24 | Done | Suraja Ram
78 | 4 |  | 57/6 | DA+3 |  | 04.09.24 | 04.09.24 | Done | Suraja Ram
79 | 5 |  | 57/3 | DA+0 |  | 05.09.24 | 05.09.24 | Done | Suraja Ram
80 | 6 |  | 57/4 | DA+0 |  | 06.09.24 | 06.09.24 | Done | Suraja Ram
81 | 7 |  | 57/5 | DA+3 |  | 07.09.24 | 07.09.24 | Done | Suraja Ram
82 | 8 |  | 62/1 | DA+3 |  | 26.09.24 | 26.09.24 | Done | Suraja Ram
83 | 9 |  | 62/0 | DB2+0 |  | 15.09.24 | 15.09.24 | Done | Suraja Ram
Oct'24
84 | 1 |  | 57/7 | DA+3 |  | 07.10.24 | 07.10.24 | Done | Suraja Ram
85 | 2 |  | 50/9 | DA+0 |  | 08.10.24 | 08.10.24 | Done | Suraja Ram
86 | 3 |  | 50/10 | DA+0 |  | 10.101.24 | 10.10.24 | Done | Suraja Ram
87 | 4 |  | 50/0 | DB2+0 |  | 11.10.24 | 11.10.24 | Done | Suraja Ram
88 | 5 |  | 50/3 | DA+6 |  | 24.10.24 | 24.10.24 | Done | Suraja Ram
89 | 6 |  | 50/1 | DA+6 |  | 25.10.24 | 25.10.24 | Done | Suraja Ram
90 | 7 |  | 51/1 | DA+0 |  | 25.10.24 | 25.10.24 | Done | Suraja Ram
91 | 8 |  | 50/2 | DA+9 |  | 28.10.24 | 28.10.24 | Done | Suraja Ram
Nov'24
92 | 1 |  | 59/11 | DA+6 |  | 11.11.24 | 11.11.24 | Done | Suraja Ram
93 | 2 |  | 50/7 | DA+0 |  | 14.11.24 | 14.11.24 | Done | Suraja Ram
94 | 3 |  | 73/1 | DA+0 |  | 14.11.24 | 14.11.24 | Done | Suraja Ram
95 | 4 |  | 73/9 | DA+0 |  | 20.11.24 | 20.11.24 | Done | Suraja Ram
96 | 5 |  | 64/11 | DA+3 |  | 21.11.24 | 21.11.24 | Done | Suraja Ram
97 | 6 |  | 73/2 | DA+0 |  | 19.11.24 | 19.11.24 | Done | Suraja Ram
98 | 7 |  | 52/6 | DA+6 |  | 25.11.24 | 25.11.24 | Done | Suraja Ram
99 | 8 |  | 52/7 | DA+3 |  | 26.11.24 | 26.11.24 | Done | Suraja Ram
100 | 9 |  | 52/8 | DA+6 |  | 26.11.24 | 26.11.24 | Done | Suraja Ram
101 | 11 |  | 48/1 | DA+9 |  | 30.11.24 | 30.11.24 | Done | Suraja Ram
Dec'24
102 | 1 |  | 49/4 | DA+3 |  | 27.11.24 | 27.11.24 | Done | Suraja Ram
103 | 2 |  | 48/0 | DC2+0 |  | 27.11.24 | 27.11.24 | Done | Suraja Ram
104 | 3 |  | 47/10 | DA+6 |  | 29.11.24 | 29.11.24 | Done | Suraja Ram
105 | 4 |  | 49/6 | DA+0 |  | 03.12.24 | 03.12.24 | Done | Suraja Ram
106 | 5 |  | 49/5 | DA+3 |  | 04.12.24 | 04.12.24 | Done | Suraja Ram
107 | 6 |  | 59/4 | DA+3 |  | 06.12.24 | 06.12.24 | Done | Suraja Ram
108 | 7 |  | 49/7 | DA+0 |  | 02.12.24 | 02.12.24 | Done | Suraja Ram
109 | 8 |  | 73/6 | DA+0 |  | 13.12.24 | 13.12.24 | Done | Suraja Ram
110 | 9 |  | 59/1 | DA+3 |  | 18.12.24 | 18.12.24 | Done | Suraja Ram
111 | 10 |  | 59/2 | DA+3 |  | 20.12.24 | 20.12.24 | Done | Suraja Ram
112 | 11 |  | 59/3 | DA+3 |  | 07.12.24 | 07.12.24 | Done | Suraja Ram
113 | 12 |  | 72/3 | DA+3 |  | 17.12.24 | 17.12.24 | Done | Suraja Ram
114 | 13 |  | 50/8 | DA+9 |  | 23.12.24 | 23.12.24 | Done | Suraja Ram
115 | 14 |  | 51/2 | DA+0 |  | 26.12,24 | 26.12,24 | Done | Suraja Ram
116 | 15 |  | 49/2 | DA+0 |  | 26.12,24 | 26.12,24 | Done | Suraja Ram
117 | 16 |  | 49/3 | DA+3 |  | 26.12,24 | 26.12,24 | Done | Suraja Ram
118 | 17 |  | 49/1 | DA+0 |  | 29.12.24 | 29.12.24 | Done | Suraja Ram
119 | 18 |  | 73/8 | DA+0 |  | 29.12.24 | 29.12.24 | Done | Suraja Ram
Jan'25
120 | 1 |  | 50/4 | DA+9 |  | 06.01.25 | 06.01.25 | Done | Suraja Ram
121 | 2 |  | 59/0 | DC2+0 |  | 07.01.25 | 07.01.25 | Done | Suraja Ram
122 | 3 |  | 50/6 | DA+9 |  | 12.01.25 | 12.01.25 | Done | Suraja Ram
123 | 4 |  | 65/7 | DA+0 |  | 23.01.25 | 23.01.25 | Done | Suraja Ram
124 | 5 |  | 65/8 | DA+0 |  | 23.01.25 | 23.01.25 | Done | Suraja Ram
125 | 6 |  | 73/3 | DA+0 |  | 28.01.25 | 28.01.25 | Done | Suraja Ram
126 | 7 |  | 73/4 | DA+0 |  | 29.01.25 | 29.01.25 | Done | Suraja Ram
Feb'25
127 | 1 |  | 73/5 | DA+0 |  | 15.02.25 | 15.02.25 | Done | Suraja Ram
128 | 2 |  | 65/10 | DA+0 |  | 17.02.25 | 17.02.25 | Done | Suraja Ram
129 | 3 |  | 66/0 | DC2+6 |  | 19.02.25 | 19.02.25 | Done | Suraja Ram
130 | 4 |  | 51/0 | DC2+0 |  | 26.02.25 | 26.02.25 | Done | Suraja Ram
131 | 5 |  | 74/0 | DB+0 |  | 14.02.25 | 14.02.25 | Done | Suraja Ram
132 | 6 |  | 73/7 | DA+0 |  | 13.02.25 | 13.02.25 | Done | Suraja Ram
Mar'25
133 | 1 |  | 52/0 |  |  | 05.03.25 | 05.03.25 | Done | Suraja Ram
134 | 2 |  | 49/0 |  |  | 10.03.25 | 10.03.25 | Done | Suraja Ram
135 | 5 |  | 52/10 |  |  | 12.03.25 | 12.03.25 | Done | Suraja Ram
136 | 6 |  | 73/0 |  |  | 13.03.25 | 13.03.25 | Done | Suraja Ram
137 | 7 |  | 52/5 |  |  | 17.3.25 | 17.3.25 | Done | Suraja Ram
138 | 4 |  | 52/9 |  |  | 11.03.25 | 11.03.25 | Done | Suraja Ram
139 | 5 |  | 50/5 |  |  | 02.03.25 | 02.03.25 | Done | Suraja Ram

## Eretion - PKG-G (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Erection
Cum Sl. No. | Month Sl. No. | JMC No. | Location No. | Tower Type | Depth of Fdn | Dt. of Start | Dt. of Complete | Name of Sub-Contractor | Ramarks
2023-09-01
1 | 1 |  | 57/9 | DA+0 |  | 13.09.23 | 21.09.23 | Sobha Devi | Complete | 37.504
2 | 2 |  | 58/12 | DA+0 |  | 18.09.23 | 25.09.23 | Sunny Const | Complete | 37.504
3 | 3 |  | 57/11 | DA+0 |  | 21.09.23 | 26.09.23 | Sobha Devi | Complete | 37.504
| 2023-10-01 | [9 empty] | 112.512
4 | 1 |  | 58/14 | DA+0 |  | 25.09.23 | 01.10.23 | Sunny Const | Complete | 37.504
5 | 2 |  | 57/13 | DA+0 |  | 26.09.23 | 01.10.23 | Sobha Devi | Complete | 37.504
6 | 3 |  | 57/10 | DA+0 |  | 01.10.23 | 06.10.23 | Sobha Devi | Complete | 37.504
7 | 4 |  | 58/9 | DA+0 |  | 01.10.23 | 07.10.23 | Sunny Const | Complete | 37.504
8 | 5 |  | 52/1 | DA+0 |  | 03.10.23 | 10.10.23 | Suraj const | Complete | 37.504
9 | 6 |  | 57/12 | DA+3 |  | 06.10.23 | 11.10.23 | Sobha Devi | Complete | 38.847
10 | 7 |  | 58/8 | DA+0 |  | 7.10.23 | 11.10.23 | Sunny Const | Complete | 37.504
11 | 8 |  | 58/1 | DA+0 |  | 25.09.23 | 12.10.23 | Ganesh Const. | Complete | 37.504
12 | 9 |  | 57/2 | DA+0 |  | 10.10.23 | 16.10.23 | Sobha Devi | Complete | 37.504
13 | 10 |  | 51/2 | DA+0 |  | 10.10.23 | 15.10.23 | Suraj const | Complete | 37.504
14 | 11 |  | 58/16 | DA+0 |  | 10.10.23 | 17.10.23 | Sunny Const | Complete | 37.504
15 | 12 |  | 57/3 | DA+0 |  | 15.10.23 | 20.10.23 | Sobha Devi | Complete | 37.504
16 | 13 |  | 51/4 | DA+3 |  | 15.10.23 | 21.10.23 | Suraj const | Complete | 38.847
17 | 14 |  | 58/3 | DA+3 |  | 12.10.23 | 22.10.23 | Ganesh Const. | Complete | 38.847
18 | 15 |  | 58/10 | DA+3 |  | 17.10.23 | 23.10.23 | Sunny Const | Complete | 38.847
19 | 16 |  | 57/4 | DA+0 |  | 20.10.23 | 26.10.23 | Sobha Devi | Complete | 37.504
20 | 17 |  | 51/5 | DA+0 |  | 20.10.23 | 29.10.23 | Suraj const | Complete | 37.504
21 | 18 |  | 57/5 | DA+3 |  | 26.10.23 | 30.10.23 | Sobha Devi | Complete | 38.847
22 | 19 |  | 58/5 | DA+3 |  | 20.10.23 | 31.10.23 | Ganesh Const. | Complete | 38.847
23 | 20 |  | 58/11 | DA+3 |  | 23.10.23 | 31.10.23 | Sunny Const | Complete | 38.847
| 2023-11-01 | [9 empty] | 759.481
24 | 1 |  | 57/8 | DA+3 |  | 30.10.23 | 03.11.2023 | Sobha Devi | Complete | 38.847
25 | 2 |  | 51/7 | DA+3 |  | 29.10.23 | 04.11.2023 | Suraj const | Complete | 38.847
26 | 3 |  | 59/6 | DA+0 |  | 31.10.23 | 07.11.2023 | Sunny Const | Complete | 37.504
27 | 4 |  | 57/7 | DA+3 |  | 03.11.23 | 07.11.2023 | Sobha Devi | Complete | 38.847
28 | 5 |  | 51/3 | DA+0 |  | 04.11.23 | 09.11.2023 | Suraj const | Complete | 37.504
29 | 6 |  | 58/4 | DA+0 |  | 31.10.23 | 11.11.2023 | Ganesh Const. | Complete | 37.504
30 | 7 |  | 57/1 | DA+3 |  | 07.11.23 | 13.11.2023 | Sobha Devi | Complete | 38.847
31 | 8 |  | 59/5 | DA+0 |  | 07.11.23 | 13.11.2023 | Sunny Const | Complete | 37.504
32 | 9 |  | 51/10 | DA+3 |  | 10.11.23 | 14.11.2023 | Suraj const | Complete | 38.847
33 | 10 |  | 56/9 | DA+3 |  | 13.11.23 | 16.11.2023 | Sobha Devi | Complete | 38.847
34 | 11 |  | 59/3 | DA+0 |  | 13.11.23 | 18.11.2023 | Sunny Const | Complete | 37.504
35 | 12 |  | 52/2 | DA+3 |  | 15.11.23 | 19.11.2023 | Suraj const | Complete | 38.847
36 | 13 |  | 55/7 | DA+0 |  | 15.11.23 | 21.11.2023 | Chinta devi | Complete | 37.504
37 | 14 |  | 58/6 | DA+3 |  | 13.11.23 | 21.11.2023 | Ganesh Const. | Complete | 38.847
38 | 15 |  | 56/8 | DA+3 |  | 16.11.23 | 21.11.2023 | Sobha Devi | Complete | 38.847
39 | 16 |  | 59/2 | DA+0 |  | 18.11.23 | 24.11.2023 | Sunny Const | Complete | 37.504
40 | 17 |  | 52/5 | DA+3 |  | 19.11.23 | 24.11.2023 | Suraj const | Complete | 38.847
41 | 18 |  | 56/7 | DA+3 |  | 22.11.23 | 24.11.2023 | Sobha Devi | Complete | 38.847
42 | 19 |  | 55/5 | DA+0 |  | 22.11.23 | 26.11.2023 | Chinta devi | Complete | 37.504
43 | 20 |  | 56/3 | DA+0 |  | 24.11.23 | 29.11.23 | Sobha Devi | Complete | 37.504
44 | 21 |  | 53/3 | DA+3 |  | 24.11.23 | 29.11.23 | Suraj const | Complete | 38.847
45 | 22 |  | 59/1 | DA+0 |  | 24.11.23 | 30.11.23 | Sunny Const | Complete | 37.504
| 2023-12-01 | [9 empty] | 841.204
46 | 1 |  | 50/4 | DA+3 |  | 22.11.23 | 01.12.23 | Ganesh Const. | Complete | 38.847
47 | 2 |  | 55/4 | DA+3 |  | 27.11.23 | 02.12.23 | Chinta devi | Complete | 38.847
48 | 3 |  | 56/4 | DA+3 |  | 29.11.23 | 02.12.23 | Sobha Devi | Complete | 38.847
49 | 4 |  | 53/4 | DA+3 |  | 29.11.23 | 03.12.23 | Suraj const | Complete | 38.847
50 | 5 |  | 58/15 | DA+3 |  | 30.11.23 | 06.12.23 | Sunny Const | Complete | 38.847
51 | 6 |  | 56/2 | DA+3 |  | 02.12.23 | 06.12.23 | Sobha Devi | Complete | 38.847
52 | 7 |  | 55/6 | DA+3 |  | 02.12.23 | 07.12.23 | Chinta devi | Complete | 38.847
53 | 8 |  | 48/1 | DA+0 |  | 02.12.23 | 09.12.23 | Ganesh Const. | Complete | 37.504
54 | 9 |  | 55/1 | DA+3 |  | 03.12.23 | 09.12.23 | Suraj const | Complete | 38.847
55 | 10 |  | 55/9 | DA+3 |  | 07.12.23 | 12.12.23 | Chinta devi | Complete | 38.847
56 | 11 |  | 57/6 | DB+0 |  | 06.12.23 | 13.12.23 | Sobha Devi | Complete | 57.597
57 | 12 |  | 61/2 | DA+0 |  | 06.12.23 | 14.12.23 | Sunny Const | Complete | 37.504
58 | 13 |  | 55/2 | DA+3 |  | 09.12.23 | 15.12.23 | Suraj const | Complete | 38.847
59 | 14 |  | 48/2 | DA+3 |  | 09.12.23 | 16.12.23 | Ganesh Const. | Complete | 38.847
60 | 15 |  | 55/10 | DA+3 |  | 12.12.23 | 17.12.23 | Chinta devi | Complete | 38.847
61 | 16 |  | 57/0 | DB+0 |  | 13.12.23 | 19.12.23 | Sobha Devi | Complete | 57.597
62 | 17 |  | 55/3 | DA+0 |  | 16.12.23 | 19.12.23 | Suraj const | Complete | 37.504
63 | 18 |  | 61/1 | DA+0 |  | 14.12.23 | 20.12.23 | Sunny Const | Complete | 37.504
64 | 19 |  | 50/3 | DA+0 |  | 16.12.23 | 22.12.23 | Ganesh Const. | Complete | 37.504
65 | 20 |  | 55/11 | DA+3 |  | 17.12.23 | 22.12.23 | Chinta devi | Complete | 38.847
66 | 21 |  | 56/5 | DA+0 |  | 20.12.23 | 24.12.23 | Sobha Devi | Complete | 37.504
67 | 22 |  | 52/4 | DA+0 |  | 20.12.23 | 24.12.23 | Suraj const | Complete | 37.504
68 | 23 |  | 55/8 | DA+3 |  | 22.12.23 | 28.12.23 | Chinta devi | Complete | 38.847
69 | 24 |  | 56/6 | DA+3 |  | 24.12.23 | 28.12.23 | Sobha Devi | Complete | 38.847
70 | 25 |  | 59/0 | DB+0 |  | 07.12.23 | 29.12.23 | Sunny Const | Complete | 57.597
71 | 26 |  | 47/3 | DA+0 |  | 22.12.23 | 29.12.23 | Ganesh Const. | Complete | 37.504
72 | 27 |  | 51/9 | DA+3 |  | 24.12.23 | 29.12.23 | Suraj const | Complete | 38.847
| 2024-01-01 | [9 empty] | 1094.375
73 | 1 |  | 56/0 | DB+0 |  | 28.12.23 | 05.01.24 | Sobha Devi | Complete | 57.597
74 | 2 |  | 44/2 | DA+0 |  | 28.12.23 | 05.01.24 | Chinta devi | Complete | 37.504
75 | 3 |  | 51/8 | DA+3 |  | 29.12.23 | 06.01.24 | Suraj const | Complete | 38.847
76 | 4 |  | 47/2 | DA+0 |  | 29.12.23 | 07.01.24 | Ganesh Const. | Complete | 37.504
77 | 5 |  | 58/7 | DB+0 |  | 29.12.23 | 09.01.24 | Sunny Const | Complete | 57.597
78 | 6 |  | 44/4 | DA+0 |  | 05.01.24 | 09.01.24 | Chinta devi | Complete | 37.504
79 | 7 |  | 53/2 | DA+3 |  | 06.01.24 | 11.01.24 | Suraj const | Complete | 38.847
80 | 8 |  | 41/11 | DA+3 |  | 05.01.24 | 12.01.24 | Sobha Devi | Complete | 38.847
81 | 9 |  | 44/3 | DA+3 |  | 09.01.24 | 15.01.24 | Chinta devi | Complete | 38.847
82 | 10 |  | 41/10 | DA+3 |  | 12.10.23 | 16.01.24 | Sobha Devi | Complete | 38.847
83 | 11 |  | 48/0 | DB+0 |  | 07.01.24 | 19.01.24 | Ganesh Const. | Complete | 57.597
84 | 12 |  | 46/3 | DA+0 |  | 12.01.24 | 19.01.24 | Sunny Const | Complete | 37.504
85 | 13 |  | 51/6 | DA+0 |  | 12.01.24 | 19.01.24 | Suraj const | Complete | 37.504
86 | 14 |  | 41/7 | DA+3 |  | 16.01.24 | 20.01.24 | Sobha Devi | Complete | 38.847
87 | 15 |  | 43/4 | DA+9 |  | 15.01.24 | 22.01.24 | Chinta devi | Complete | 47.148
88 | 16 |  | 43/5 | DA+0 |  | 22.1.24 | 27.01.24 | Chinta devi | Complete | 37.504
89 | 17 |  | 47/0 | DB+0 |  | 20.01.24 | 28.01.24 | Sunny Const | Complete | 57.597
90 | 18 |  | 51/0 | DB+0 |  | 20.01.24 | 28.01.24 | Ganesh Const. | Complete | 57.597
91 | 19 |  | 52/0 | DB+0 |  | 20.01.24 | 28.01.24 | Suraj const | Complete | 57.597
92 | 20 |  | 43/1 | DA+9 |  | 23.01.24 | 28.01.24 | Sobha Devi | Complete | 47.148
93 | 21 |  | 41/5 | DA+0 |  | 28.01.24 | 31.01.24 | Sobha Devi | Bottom complete | 37.504
| Feb-24 | [9 empty] | 935.488
94 | 1 |  | 44/1 | DA+0 |  | 28.01.24 | 01.02.24 | Chinta devi | Complete | 37.504
95 | 2 |  | 46/2 | DA+0 |  | 28.01.24 | 02.02.24 | Sunny Const | Complete | 37.504
96 | 3 |  | 51/1 | DA+0 |  | 28.01.24 | 04.02.24 | Ganesh Const. | Complete | 37.504
97 | 4 |  | 41/4 | DA+0 |  | 01.02.24 | 05.02.24 | Sobha Devi | Complete | 37.504
98 | 5 |  | 53/1 | DA+0 |  | 04.02.24 | 09.02.24 | Suraj const | Complete | 37.504
99 | 6 |  | 41/6 | DA+0 |  | 07.02.24 | 09.02.24 | Sobha Devi | Complete | 37.504
100 | 7 |  | 41/8 | DA+0 |  | 09.02.24 | 13.02.24 | Sobha Devi | Complete | 37.504
101 | 8 |  | 41/9 | DA+0 |  | 13.02.24 | 17.02.24 | Sobha Devi | Complete | 37.504
| April'24 | [9 empty] | 300.032
102 | 1 |  | 55/0 | DC+0 |  | 28.03.24 | 04.04.24 | Sobha Devi | Complete | 66.381
103 | 2 |  | 58/0 | DC2+0 |  | 08.04.24 | 16.04.24 | Sunny Const | Complete | 66.381
104 | 3 |  | 56/1 | DA+3 |  | 12.04.24 | 16.04.24 | Sobha Devi | Complete | 38.847
105 | 4 |  | 53/0 | DC2+3 |  | 08.04.24 | 18.04.24 | Ganesh Const. | Complete | 69.229
| May'24 | [9 empty] | 240.838
106 | 1 |  | 52/3 | DA+0 |  | 26.04.24 | 05.05.24 | Ganesh Const. | Complete | 37.504
107 | 2 |  | 58/2 | DA+0 |  | 05.05.24 | 10.05.24 | Sunny Const | Complete | 37.504
108 | 3 |  | 65/4 | DA+0 |  | 10.05.24 | 16.05.24 | Sunny Const | Complete | 37.504
109 | 4 |  | 65/3 | DA+0 |  | 16.05.24 | 21.05.24 | Sunny Const | Complete | 37.504
110 | 5 |  | 65/5 | DA+0 |  | 16.05.24 | 26.05.24 | Sunny Const | Complete | 37.504
| Aug'24 | [9 empty] | 187.52
111 | 1 |  | 46/4 | DA+0 |  | 27.08.24 | 30.08.24 | Sobha devi | Complete | 37.504
Sept'24
112 | 1 |  | 72/3 | DA+0 |  | 25.08.24 | 01.09.24 | Sunny Const | Complete | 37.504
113 | 2 |  | 72/4 | DA+0 |  | 01.09.24 | 06.09.24 | Sunny Const | Complete | 37.504
114 | 3 |  | 71/5 | DA+0 |  | 28.08.24 | 06.09.24 | Chinta Devi | Complete | 37.504
115 | 4 |  | 72/5 | DA+0 |  | 01.09.24 | 11.09.24 | Sunny Const | Complete | 37.504
116 | 5 |  | 47/1 | DA+0 |  | 09.09.24 | 12.09.24 | Sobha devi | Complete | 37.504
117 | 6 |  | 72/6 | DA+0 |  | 11.09.24 | 15.09.24 | Sunny Const | Complete | 37.504
118 | 7 |  | 72/0 | DB1+0 |  | 06.09.24 | 16.09.24 | Chinta Devi | Complete | 57.597
119 | 8 |  | 50/2 | DA+0 |  | 12.09.24 | 16.09.24 | Sobha devi | Complete | 37.504
120 | 9 |  | 50/1 | DA+0 |  | 16.09.24 | 20.09.24 | Sobha devi | Complete | 37.504
121 | 10 |  | 71/4 | DA+0 |  | 16.09.24 | 22.09.24 | Chinta Devi | Complete | 37.504
122 | 11 |  | 72/7 | DB1+9 |  | 15.09.24 | 25.09.24 | Sunny Const | Complete | 70.701
123 | 12 |  | 43/6 | DA+6 |  | 09.09.24 | 26.09.24 | Jirwa Devi | Complete | 45.413
124 | 13 |  | 50/0 | DC+3 |  | 20.09.24 | 26.09.24 | Sobha devi | Complete | 69.229
125 | 14 |  | 71/2 | DA+0 |  | 22.09.24 | 26.09.24 | Chinta Devi | Complete | 37.504
126 | 15 |  | 72/2 | DA+0 |  | 25.09.24 | 29.09.24 | Sunny Const | Complete | 37.504
| Oct'24 | [9 empty] | 655.484
127 | 1 |  | 71/1 | DA+0 |  | 26.09.24 | 01.10.24 | Chinta Devi | Complete | 37.504
128 | 2 |  | 72/1 | DA+0 |  | 29.09.24 | 03.10.24 | Sunny Const | Complete | 37.504
129 | 3 |  | 68/1 | DA+3 |  | 2.10.24 | 05.10.24 | Chinta Devi | Complete | 38.847
130 | 4 |  | 43/3 | DA+3 |  | 27.09.24 | 08.10.24 | Jirwa Devi | Complete | 38.847
131 | 5 |  | 68/2 | DA+3 |  | 05.10.24 | 10.10.24 | Chinta Devi | Complete | 38.847
132 | 6 |  | 66/2 | DA+0 |  | 30.09.24 | 10.10.24 | Sanjeev Kumar | Complete | 37.504
133 | 7 |  | 73/0 | DD45+9 |  | 03.10.24 | 17.10.24 | Sunny Const | Complete | 105.068
134 | 8 |  | 67/1 | DB1+9 |  | 10.10.24 | 19.10.24 | Chinta devi | Complete | 70.701
135 | 9 |  | 43/2 | DA+9 |  | 08.10.24 | 22.10.24 | Jirwa Devi | Complete | 47.148
136 | 10 |  | 71/3 | DA+0 |  | 18.10.24 | 23.10.24 | Sunny Const | Complete | 37.504 |  | 202
137 | 11 |  | 69/6 | DA+0 |  | 23.10.24 | 27.10.24 | Sunny Const | Complete | 37.504 |  | 9090
138 | 12 |  | 68/3 | DA+0 |  | 24.10.24 | 28.10.24 | Chinta devi | Complete | 37.504
139 | 13 |  | 40/11 | DA+9 |  | 23.10.24 | 30.10.24 | Ganesh Sinha | Complete | 47.148
140 | 14 |  | 69/7 | DA+0 |  | 27.10.24 | 31.10.24 | Sunny Const | Complete | 37.504
| Nov'24 | [9 empty] | 649.134
141 | 1 |  | 68/5 | DA+3 |  | 28.09.24 | 01.11.24 | Chinta devi | Complete | 38.847
142 | 2 |  | 68/6 | DA+3 |  | 01.11.24 | 05.11.24 | Chinta devi | Complete | 38.847
143 | 3 |  | 69/5 | DA+0 |  | 01.11.24 | 05.11.24 | Sunny Const | Complete | 37.504
144 | 4 |  | 68/4 | DA+3 |  | 05.11.24 | 09.11.24 | Chinta devi | Complete | 38.847
145 | 5 |  | 69/4 | DA+0 |  | 05.11.24 | 09.11.24 | Sunny Const | Complete | 37.504
146 | 6 |  | 40/10 | DB1+6 |  | 30.10.24 | 11.11.24 | Ganesh Sinha | Complete | 67.873
147 | 7 |  | 69/3 | DA+0 |  | 09.11.24 | 13.11.24 | Sunny Const | Complete | 37.504
148 | 8 |  | 66/4 | DA+3 |  | 29.10.24 | 14.11.24 | Sanjeev Kumar | Complete | 38.847
149 | 9 |  | 69/2 | DA+0 |  | 13.11.24 | 17.11.24 | Sunny Const | Complete | 37.504 |  | 840
150 | 10 |  | 69/1 | DA+0 |  | 18.11.24 | 22.11.24 | Sunny Const | Complete | 37.504 |  | 840
151 | 11 |  | 68/0 | DD45+0 |  | 22.11.24 | 29.11.24 | Chinta devi | Complete | 86.129 |  | 840
152 | 12 |  | 69/0 | DB1+0 |  | 23.11.24 | 30.11.24 | Sunny Const | Complete | 57.597 |  | 840
| Dec'24 | [9 empty] | 554.507 | 700
153 | 1 |  | 69/9 | DA+0 |  | 01.12.24 | 06.12.24 | Sunny Const | Complete | 37.504 |  | 840
154 | 2 |  | 67/0 | DD45+0 |  | 01.12.24 | 08.12.24 | Chinta devi | Complete | 86.129 |  | 4900
155 | 3 |  | 66/1 | DA+3 |  | 02.12.24 | 08.12.24 | Sanjeev Kumar | Complete | 38.847
156 | 4 |  | 38/3 | DA+9 |  | 10.12.24 | 15.12.24 | Sobha Devi | Complete | 47.148
157 | 5 |  | 41/12 | DA+3 |  | 09.12.24 | 17.12.24 | Ganesh Sinha | Complete | 38.847
158 | 6 |  | 71/0 | DD+0 |  | 07.12.24 | 17.12.24 | Sunny Const | Complete | 86.129
159 | 7 |  | 65/6 | DA+0 |  | 14.12.24 | 18.12.24 | Chinta devi | Complete | 37.504
160 | 8 |  | 58/13 | DA+0 |  | 11.12.24 | 19.12.24 | Sanjeev Kumar | Complete | 37.504
161 | 9 |  | 38/2 | DA+6 |  | 15.12.24 | 19.12.24 | Sobha Devi | Complete | 45.413
162 | 10 |  | 69/8 | DA+0 |  | 18.12.24 | 22.12.24 | Sunny Const | Complete | 37.504
163 | 11 |  | 65/7 | DA+0 |  | 18.12.24 | 22.12.24 | Chinta devi | Complete | 37.504
164 | 12 |  | 38/1 | DA+3 |  | 20.12.24 | 24.12.24 | Sobha Devi | Complete | 38.847
165 | 13 |  | 37/3 | DA+0 |  | 25.12.24 | 28.12.24 | Sobha Devi | Complete | 37.504
166 | 14 |  | 41/2 | DA+0 |  | 21.12.24 | 28.12.24 | Jirwa Devi | Complete | 37.504
167 | 15 |  | 70/0 | DD60+0 |  | 22.12.24 | 31.12.24 | Sunny Const | Complete | 86.129
168 | 16 |  | 42/0 | DC2+9 |  | 19.12.24 | 31.12.24 | Ganesh Sinha | Complete | 81.945
169 | 17 |  | 66/0 | DD45+0 |  | 22.12.24 | 31.12.24 | Chinta devi | Complete | 86.129
| Jan'25 | [9 empty] | 898.091
170 | 1 |  | 37/4 | DA+6 |  | 29.12.24 | 03.01.25 | Sobha Devi | Complete | 45.413
171 | 2 |  | 41/3 | DA+0 |  | 29.12.24 | 07.01.25 | Jirwa Devi | Complete | 37.504
172 | 3 |  | 59/4 | DA+0 |  | 06.01.25 | 10.01.25 | Sanjeev Kumar | Complete | 37.504
173 | 4 |  | 37/2 | DB1+6 |  | 04.01.25 | 10.01.25 | Sobha Devi | Complete | 67.873
174 | 5 |  | 37/5 | DA+3 |  | 10.01.25 | 16.01.25 | Sobha Devi | Complete | 38.847
175 | 6 |  | 41/1 | DA+3 |  | 10.01.25 | 17.01.25 | Jirwa Devi | Complete | 38.847 | 8
176 | 7 |  | 37/6 | DA+6 |  | 16.01.25 | 20.01.25 | Sobha Devi | Complete | 45.413
177 | 8 |  | 37/7 | DA+3 |  | 20.01.25 | 24.01.25 | Sobha Devi | Complete | 38.847
178 | 9 |  | 39/1 | DA+6 |  | 19.01.25 | 28.01.25 | Om Construction | Complete | 45.413
179 | 10 |  | 37/8 | DA+0 |  | 25.01.25 | 28.01.25 | Sobha Devi | Complete | 37.504
180 | 11 |  | 41/0 | DB1+0 |  | 18.01.25 | 29.01.25 | Jirwa Devi | Complete | 57.597
181 | 12 |  | 40/2 | DB1+9 |  | 10.01.25 | 30.01.25 | Sunny Const | Complete | 70.701
| Feb'25 | [9 empty] | 561.463
182 | 1 | -180 | 38/0 | DC1+0 |  | 29.01.25 | 04.02.25 | Sobha Devi | Complete | 66.381
183 | 2 | -179 | 40/12 | DA+0 |  | 29.01.25 | 08.02.25 | Jirwa Devi | Complete | 37.504
184 | 3 | -178 | 43/0 | DB1+9 |  | 31.01.25 | 18.02.25 | Ganesh Sinha | Complete | 70.701
185 | 4 |  | 60/0 | DC2+3 |  | 07.02.25 | 19.02.25 | Sanjeev kumar | Complete | 69.229
186 | 5 |  | 40/6 | DA+3 |  | 15.02.25 | 20.02.25 | Sunny Const. | Complete | 38.847
187 | 6 |  | 49/0 | DC1+3 |  | 09.02.25 | 23.02.25 | Jirwa Devi | Complete | 69.229
188 | 7 |  | 40/7 | DA+3 |  | 21.02.25 | 26.02.25 | Sunny Const. | Complete | 38.847
189 | 8 |  | 44/0 | DB1+0 |  | 19.02.25 | 28.02.25 | Ganesh Sinha | Complete | 57.597
190 | 9 |  | 39/0 | DC2+3 |  | 21.02.25 | 28.02.25 | Sobha Devi | Complete | 69.229
| Mar'25 | [9 empty] | 517.564
191 | 1 |  | 61/0 | DB1+6 |  | 20.01.25 |  | Sanjeev kumar | Complete | 67.873
192 | 2 |  | 40/0 | DC2+0 |  | 27.02.25 | 06.03.25 | Sunny Const. | Complete | 66.381
193 | 3 |  | 38/9 | DB1+6 |  | 01.03.25 | 07.03.25 | Sobha Devi | Complete | 67.873
194 | 4 |  | 38/8 | DA+0 |  | 08.03.25 | 11.03.25 | Sobha Devi | Complete | 37.504
195 | 5 |  | 40/1 | DA+0 |  | 08.03.25 | 12.03.25 | Sunny Const. | Complete | 37.504
196 | 6 |  | 38/7 | DA+0 |  | 13.03.25 | 17.03.25 | Sobha Devi | Complete | 37.504
197 | 7 |  | 40/4 | DA+9 |  | 13.03.25 |  | Sunny Const. | Complete | 47.148
198 | 8 |  | 38/6 | DA+0 |  | 18.03.25 | 21.03.25 | Sobha Devi | Complete | 37.504
199 | 9 |  | 38/5 | DA+0 |  | 22.03.25 | 25.03.25 | Sobha Devi | Complete | 37.504 | 436.795
200 | 10 |  | 40/5 | DB1+9 |  | 21.03.25 | 28.03.25 | Sunny Const. | Complete | 70.701
201 | 11 |  | 38/4 | DA+0 |  | 26.03.25 | 29.03.25 | Sobha Devi | Complete | 37.504
April'25
202 | 1 |  | 66/3 | DA+3 |  | 19.01.25 |  | Chinta devi | Work Hold due to unavailabilty of 33kv Shutdown
203 | 2 |  | 64/9 | DA+0 |  |  |  | Sunny Const. | ROW since 02.04.25 | 37.504

## Eretion - PKG-F (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Erection PKG-F
Cum Sl. No. | Month Sl. No. | JMC No. | Location No. | Tower Type | Depth of Fdn | Dt. of Start | Dt. of Complete | Name of Sub-Contractor | Ramarks
Feb-24
1 | 1 |  | 60/7 | DA+3 |  | 28.1.24 | 04.02.24 | Suraj const | Complete |  |  |  | 38.847
2 | 2 |  | 59/13 | DA+3 |  | 01.02.24 | 07.02.24 | Chinta Devi | Complete |  |  |  | 38.847
3 | 3 |  | 63/6 | DA+3 |  | 03.02.24 | 10.02.24 | Sunny Const. | Complete |  |  |  | 38.847
4 | 4 |  | 59/5 | DA+3 |  | 05.02.24 | 11.02.24 | Ganesh Const | Complete |  |  |  | 38.847
5 | 5 |  | 59/14 | DA+6 |  | 08.02.24 | 13.02.24 | Chinta Devi | Complete |  |  |  | 45.413
6 | 6 |  | 60/8 | DA+0 |  | 09.02.24 | 15.02.24 | Suraj const | Complete |  |  |  | 37.504
7 | 7 |  | 63/7 | DA+3 |  | 11.02.24 | 15.02.24 | Sunny Const. | Complete |  |  |  | 38.847
8 | 8 |  | 59/6 | DA+3 |  | 12.02.24 | 18.02.24 | Ganesh Const | Complete |  |  |  | 38.847
9 | 9 |  | 59/12 | DA+6 |  | 13.02.24 | 20.02.24 | Chinta Devi | Complete |  |  |  | 45.413
10 | 10 |  | 63/8 | DA+3 |  | 15.02.24 | 20.02.24 | Sunny Const. | Complete |  |  |  | 38.847
11 | 11 |  | 60/10 | DA+0 |  | 15.02.24 | 21.02.24 | Suraj const | Complete |  |  |  | 37.504
12 | 12 |  | 62/5 | DA+0 |  | 17.02.24 | 22.02.24 | Sobha Devi | Complete |  |  |  | 37.504
13 | 13 |  | 59/7 | DA+3 |  | 18.02.24 | 24.02.24 | Ganesh Const | Complete |  |  |  | 38.847
14 | 14 |  | 59/10 | DA+0 |  | 20.02.24 | 24.02.24 | Chinta Devi | Complete |  |  |  | 37.504
15 | 15 |  | 64/1 | DA+0 |  | 20.02.24 | 24.02.24 | Sunny Const. | Complete |  |  |  | 37.504
16 | 16 |  | 60/11 | DA+3 |  | 21.02.24 | 26.02.24 | Suraj const | Complete |  |  |  | 38.847
17 | 17 |  | 62/4 | DA+3 |  | 22.02.24 | 26.02.24 | Sobha Devi | Complete |  |  |  | 38.847
18 | 18 |  | 59//9 | DA+3 |  | 24.02.24 | 28.02.24 | Chinta Devi | Complete |  |  |  | 38.847
19 | 19 |  | 62/3 | DA+0 |  | 26.02.24 | 28.02.24 | Sobha Devi | Complete |  |  |  | 37.504
20 | 20 |  | 59/8 | DB1+3 |  | 24.02.24 | 29.02.24 | Ganesh Const | Complete |  |  |  | 60.097
21 | 21 |  | 64/4 | DA+3 |  | 24.02.24 | 29.02.24 | Sunny Const. | Complete |  |  |  | 38.847
22 | 22 |  | 60/6 | DA+0 |  | 26.02.24 | 29.02.24 | Suraj const | Complete |  |  |  | 37.504
| March'24 | [12 empty] | 879.615
23 | 1 |  | 62/2 | DA+3 |  | 29.02.24 | 03.03.24 | Sobha Devi | Complete |  |  |  | 38.847
24 | 2 |  | 64/5 | DA+3 |  | 29.02.24 | 04.03.24 | Sunny Const. | Complete |  |  |  | 38.847
25 | 3 |  | 65/2 | DA+0 |  | 29.02.24 | 06.03.24 | Chinta Devi | Complete |  |  |  | 37.504
26 | 4 |  | 62/7 | DA+3 |  | 04.03.24 | 07.03.24 | Sobha Devi | Complete |  |  |  | 38.847
27 | 5 |  | 59/16 | DA+9 |  | 29.02.24 | 11.03.24 | Ganesh Const. | Complete |  |  |  | 47.418
28 | 6 |  | 65/4 | DA+0 |  | 06.03.24 | 11.03.24 | Chinta Devi | Complete |  |  |  | 37.504
29 | 7 |  | 62/8 | DA+0 |  | 07.03.24 | 11.03.24 | Sobha Devi | Complete |  |  |  | 37.504
30 | 8 |  | 62/9 | DA+3 |  | 11.03.24 | 15.03.24 | Sobha Devi | Complete |  |  |  | 38.847
31 | 9 |  | 65/3 | DA+3 |  | 11.03.24 | 16.03.24 | Chinta Devi | Complete |  |  |  | 38.847
32 | 10 |  | 60/5 | DA+3 |  | 11.03.24 | 17.03.24 | Ganesh Const. | Complete |  |  |  | 38.847
33 | 11 |  | 62/10 | DA+0 |  | 15.03.24 | 18.03.24 | Sobha Devi | Complete |  |  |  | 37.504
34 | 12 |  | 65/5 | DA+0 |  | 16.03.24 | 20.03.24 | Chinta Devi | Complete |  |  |  | 37.504
35 | 13 |  | 61/6 | DA+3 |  | 18.03.24 | 22.03.24 | Sobha Devi | Complete |  |  |  | 38.847
36 | 14 |  | 60/4 | DA+3 |  | 18.03.24 | 23.03.24 | Ganesh Const. | Complete |  |  |  | 38.847
37 | 15 |  | 65/6 | DA+0 |  | 20.03.24 | 26.03.24 | Chinta Devi | Complete |  |  |  | 37.504
38 | 16 |  | 64/6 | DA+0 |  | 21.03.24 | 26.03.24 | Sunny Const. | Complete |  |  |  | 37.504
39 | 17 |  | 61/7 | DA+9 |  | 22.03.24 | 28.03.24 | Sobha Devi | Complete |  |  |  | 47.418
40 | 18 |  | 64/7 | DA+3 |  | 26.03.24 | 30.03.24 | Sunny Const. | Complete |  |  |  | 38.847
41 | 19 |  | 60/3 | DA+3 |  | 23.03.24 | 31.03.24 | Ganesh Const. | Complete |  |  |  | 38.847
42 | 20 |  | 65/9 | DA+0 |  | 26.03.24 | 31.03.24 | Chinta Devi | Complete |  |  |  | 37.504
| Apr-'24 | [12 empty] | 783.338
43 | 1 |  | 64/8 | DA+3 |  | 30.03.24 | 03.04.24 | Sunny Const. | Complete |  |  |  | 38.847
44 | 2 |  | 65/11 | DA+0 |  | 31.03.24 | 04.04.24 | Chinta Devi | Complete |  |  |  | 37.504
45 | 3 |  | 60/2 | DA+3 |  | 31.03.24 | 07.04.24 | Ganesh Const. | Complete |  |  |  | 38.847
46 | 4 |  | 63/5 | DA+3 |  | 01.04.24 | 07.04.24 | Suraj Const | Complete |  |  |  | 38.847
47 | 5 |  | 64/9 | DA+3 |  | 03.04.24 | 08.04.24 | Sunny Const. | Complete |  |  |  | 38.847
48 | 6 |  | 67/1 | DA+0 |  | 06.04.24 | 10.04.24 | Chinta Devi | Complete |  |  |  | 37.504
49 | 7 |  | 61/0 | DB+0 |  | 06.04.24 | 11.04.24 | Sobha Devi | Complete |  |  |  | 57.598
50 | 8 |  | 63/4 | DA+0 |  | 07.04.24 | 13.04.24 | Suraj Const | Complete |  |  |  | 37.504
51 | 9 |  | 67/2 | DA+0 |  | 10.04.24 | 15.04.24 | Chinta Devi | Complete |  |  |  | 37.504
52 | 10 |  | 63/3 | DA+3 |  | 13.04.24 | 17.04.24 | Suraj Const | Complete |  |  |  | 38.847
53 | 11 |  | 64/10 | DA+3 |  | 15.04.24 | 20.04.24 | Chinta Devi | Complete |  |  |  | 38.847
54 | 12 |  | 64/2 | DA+3 |  | 16.04.243 | 21.04.24 | Sunny Const. | Complete |  |  |  | 38.847
55 | 13 |  | 61/2 | DA+6 |  | 16.04.24 | 22.04.24 | Sobha Devi | Complete |  |  |  | 45.413
56 | 14 |  | 63/2 | DA+0 |  | 17.04.24 | 22.04.24 | Suraj const | Complete |  |  |  | 37.504
57 | 15 |  | 60/1 | DA+6 |  | 18.04.24 | 25.04.24 | Ganesh Const. | Complete |  |  |  | 45.413
58 | 16 |  | 64/3 | DA+0 |  | 21.04.24 | 26.04.24 | Sunny Const. | Complete |  |  |  | 37.504
59 | 17 |  | 65/0 | DB1+0 |  | 21.04.24 | 27.04.24 | Chinta Devi | Complete |  |  |  | 57.598
60 | 18 |  | 63/1 | DA+3 |  | 22.04.24 | 27.04.24 | Suraj const | Complete |  |  |  | 38.847
61 | 19 |  | 61/1 | DA+6 |  | 22.04.24 | 29.04.24 | Sobha Devi | Complete |  |  |  | 45.413
| May'24 | [12 empty] | 787.235
62 | 1 |  | 65/1 | DA+0 |  | 27.04.24 | 03.05.24 | Chinta Devi | Complete |  |  |  | 37.504
63 | 2 |  | 62/11 | DA+3 |  | 27.04.24 | 03.05.24 | Suraj const | Complete |  |  |  | 38.847
64 | 3 |  | 64/0 | DB2+0 |  | 27.04.24 | 05.05.24 | Sunny Const. | Complete |  |  |  | 57.598
65 | 4 |  | 60/9 | DA+3 |  | 29.04.24 | 05.05.24 | Sobha Devi | Complete |  |  |  | 38.847
66 | 5 |  | 61/3 | DA+6 |  | 05.05.24 | 11.5.24 | Sobha Devi | Complete |  |  |  | 45.413
67 | 6 |  | 63/0 | DC1+0 |  | 03.05.24 | 12.5.24 | Suraj const | Complete |  |  |  | 66.381
68 | 7 |  | 61/4 | DA+3 |  | 11.5.24 | 16.05.24 | Sobha Devi | Complete |  |  |  | 38.847
69 | 8 |  | 60/0 | DC+0 |  | 05.05.24 | 18.05.24 | Ganesh | Complete |  |  |  | 66.381
70 | 9 |  | 61/10 | DA+9 |  | 12.5.24 | 19.05.24 | Suraj const | Complete |  |  |  | 47.418
71 | 10 |  | 61/5 | DA+3 |  | 16.05.24 | 22.05.24 | Sobha Devi | Complete |  |  |  | 38.847
72 | 11 |  | 61/9 | DA+0 |  | 19.05.24 | 23.05.24 | Suraj const | Complete |  |  |  | 37.504
73 | 12 |  | 59/15 | DA+6 |  | 18.05.24 | 30.05.24 | Ganesh | Complete |  |  |  | 45.413
74 | 13 |  | 61/8 | DA+6 |  | 23.05.24 | 30.05.24 | Suraj const | Complete |  |  |  | 45.413
75 | 14 |  | 55/3 | DA+0 |  | 12.5.24 | 31.05.24 | Mansukh lal | Complete |  |  |  | 37.504
| June'24 | [12 empty] | 641.917
76 | 1 |  | 57/3 | DA+0 |  | 29.05.24 | 11.06.24 | Bhuvneshwar | Complete |  |  |  | 37.504
77 | 2 |  | 55/4 | DA+0 |  | 01.06.24 | 19.06.24 | Mansukh lal | Complete |  |  |  | 37.504
78 | 3 |  | 57/4 | DA+0 |  | 12.06.24 | 27.06.24 | Bhuvneshwar | Complete |  |  |  | 37.504
| July'24 | [12 empty] | 112.512
79 | 1 |  | 62/1 | DA+3 |  | 04.07.24 | 12.07.24 | Bhuvneshwar | Complete |  |  |  | 38.847
80 | 2 |  | 62/6 | DA+3 |  | 15.07.24 | 26.07.24 | Bhuvneshwar | Complete |  |  |  | 38.847
| Aug'24 | [12 empty] | 77.694
81 | 1 |  | 57/6 | DA+3 |  | 13.08.24 | 20.08.24 | Sobha devi | Complete |  |  |  | 38.847
82 | 2 |  | 57/5 | DA+3 |  | 20.08.24 | 26.08.24 | Sobha devi | Complete |  |  |  | 38.847
| Sept'24 | [12 empty] | 77.694
83 | 1 |  | 62/0 | DB2+0 |  | 31.08.24 | 08.09.24 | Sobha devi | Complete |  |  |  | 57.598
84 | 2 |  | 50/9 | DA+0 |  | 28.08.24 | 09.09.24 | Uma const | Complete |  |  |  | 37.504
85 | 3 |  | 52/5 | DA+9 |  | 27.08.24 | 19.09.24 | Ganesh Sinha | Complete |  |  |  | 47.418
86 | 4 |  | 50/10 | DA+0 |  | 10.09.24 | 19.09.24 | Uma const | Complete |  |  |  | 37.504
87 | 5 |  | 48/1 | DA+9 |  | 08.09.24 | 25.09.24 | Kaushalya const | Complete |  |  |  | 47.418
88 | 6 |  | 51/1 | DA+0 |  | 19.09.24 | 26.09.24 | Uma const | Complete |  |  |  | 37.504
89 | 7 |  | 52/6 | DA+6 |  | 19.09.24 | 30.09.24 | Ganesh Sinha | Complete |  |  |  | 45.413
| Oct'24 | [8 empty] | WT | JMC | FTR |  | 310.359
90 | 1 | 1 | 57/7 | DA+3 |  | 27.09.24 | 01.10.24 | Sobha devi | Complete | 38.847 | Received | Done | 38.847
91 | 2 | 2 | 51/2 | DA+0 |  | 26.09.24 | 04.10.24 | Uma const | Complete | 37.504 | Not received | Not checked | 37.504
92 | 3 | 3 | 50/0 | DB2+0 |  | 02.10.24 | 07.10.24 | Sobha devi | Complete | 57.597 | Received | Done | 57.598
93 | 4 |  | 52/7 | DA+3 |  | 01.10.24 | 07.10.24 | Ganesh Sinha | Complete | 38.847 | Not received | Not checked | 38.847
94 | 5 |  | 50/1 | DA+6 |  | 07.10.24 | 15.10.24 | Sobha Devi | Complete | 45.413 | Not received | Done | 45.413
95 | 6 |  | 50/8 | DA+9 |  | 07.10.24 | 16.10.24 | Uma const | Complete | 47.148 | Not received | Not checked | 47.418
96 | 7 |  | 50/3 | DA+6 |  | 13.10.24 | 18.10.24 | Sobha Devi | Complete | 45.413 | Not received | Done | 45.413
97 | 8 |  | 48/0 | DC2+0 |  | 28.09.24 | 19.10.24 | Kaushalya const | Complete | 66.381 | Not received | Not checked | 66.381
98 | 9 |  | 52/8 | DA+6 |  | 08.10.24 | 19.10.24 | Ganesh Sinha | Complete | 45.413 | Not received | Not checked | 45.413
99 | 10 |  | 73/2 | DA+0 |  | 10.10.24 | 20.10.24 | Sanjeev Kumar | Complete | 37.504 | Not received | Not checked | 37.504
100 | 11 |  | 50/2 | DA+9 |  | 18.10.24 | 24.10.24 | Sobha Devi | Complete | 47.148 | Not received | Erection completed on 24.10.24 | 47.418
101 | 12 |  | 64/11 | DA+3 |  | 20.10.24 | 24.10.24 | Chinta devi | Complete |  | Not received | Erection completed on 24.10.24 | 38.847
102 | 13 |  | 59/11 | DA+6 |  | 17.10.24 | 26.10.24 | Uma const | Complete |  |  |  | 45.413
103 | 14 |  | 73/1 | DA+0 |  | 21.10.24 | 29.10.24 | Sanjeev Kumar | Complete |  |  |  | 37.504
104 | 15 |  | 50/4 | DA+9 |  | 24.10.24 | 30.10.24 | Sobha Devi | Complete |  |  |  | 47.418
| Nov'24 | [12 empty] | 676.938
105 | 1 |  | 55/6 | DA+0 |  | 23.10.24 | 01.11.24 | Jirwa Devi | Complete |  |  |  | 37.504
106 | 2 |  | 59/3 | DA+3 |  | 27.10.24 | 02.11.24 | Uma const | Complete |  |  |  | 38.847
107 | 3 |  | 50/7 | DA+0 |  | 01.11.24 | 04.11.24 | Sobha Devi | Complete |  |  |  | 37.504
108 | 4 |  | 59/4 | DA+3 |  | 01.11.24 | 09.11.24 | Uma const | Complete |  |  |  | 38.847
109 | 5 |  | 50/6 | DA+9 |  | 04.11.24 | 10.11.24 | Sobha Devi | Complete |  |  |  | 47.418
110 | 6 |  | 55/5 | DA+0 |  | 01.11.24 | 12.11.24 | Jirwa Devi | Complete |  |  |  | 37.504
111 | 7 |  | 73/9 | DA+0 |  | 09.11.24 | 13.11.24 | Chinta devi | Complete |  |  |  | 37.504
112 | 8 |  | 49/7 | DA+0 |  | 11.11.24 | 14.11.24 | Sobha Devi | Complete |  |  |  | 37.504
113 | 9 |  | 73/8 | DA+3 |  | 13.11.24 | 17.11.24 | Chinta devi | Complete |  |  |  | 38.847
114 | 10 |  | 49/6 | DA+0 |  | 15.11.24 | 18.11.24 | Sobha Devi | Complete |  |  |  | 37.504
115 | 11 |  | 73/6 | DA+0 |  | 17.11.24 | 20.11.24 | Chinta devi | Complete |  |  |  | 37.504
116 | 12 |  | 47/10 | DA+6 |  | 02.11.24 | 22.11.24 | Kaushalya const | Complete |  |  |  | 45.413
117 | 13 |  | 49/4 | DA+3 |  | 18.11.24 | 22.11.24 | Sobha Devi | Complete |  |  |  | 38.847
118 | 14 |  | 59/2 | DA+3 |  | 12.11.24 | 24.11.24 | Jirwa Devi | Complete |  |  |  | 38.847
119 | 15 |  | 52/10 | DA+9 |  | 13.11.24 | 25.11.24 | Ganesh Sinha | Complete |  |  |  | 47.418
120 | 16 |  | 49/5 | DA+3 |  | 23.11.24 | 27.11.24 | Sobha Devi | Complete |  |  |  | 38.847
121 | 17 |  | 49/2 | DA+3 |  | 27.11.24 | 30.11.24 | Sobha Devi | Complete |  |  |  | 38.847
122 | 18 |  | 72/3 | DA+3 |  | 24.11.24 | 30.11.24 | Sanjeev Kumar | Complete |  |  |  | 38.847
| Dec'24 | [12 empty] | 713.553
123 | 1 | -121 | 59/1 | DA+3 |  | 25.11.24 | 03.12.24 | Jirwa Devi | Complete |  |  |  | 38.847
124 | 2 | -120 | 52/9 | DA+3 |  | 26.11.24 | 05.12.24 | Ganesh Sinha | Complete |  |  |  | 38.847
125 | 3 | -119 | 49/3 | DA+3 |  | 02.12.24 | 05.12.24 | Sobha Devi | Complete |  |  |  | 38.847
126 | 4 |  | 49/1 | DA+0 |  | 06.12.24 | 09.12.24 | Sobha Devi | Complete |  |  |  | 37.504
127 | 5 |  | 73/3 | DA+0 |  | 09.12.24 | 13.12.24 | Chinta devi | Complete |  |  |  | 37.504
128 | 6 |  | 59/0 | DC2+0 |  | 03.12.24 | 16.12.24 | Jirwa Devi | Complete |  |  |  | 66.381
129 | 7 |  | 65/8 | DA+0 |  | 20.12.24 | 27.12.24 | Sanjeev Kumar | Complete |  |  |  | 37.504
| Jan'25 | [12 empty] | 295.434
130 | 1 |  | 65/7 | DA+0 |  | 28.12.24 | 04.01.25 | Sanjeev Kumar | Complete |  |  |  | 37.504
131 | 2 |  | 73/0 | DB2+0 |  | 03.01.25 | 09.01.25 | Chinta devi | Complete |  |  |  | 57.598
132 | 3 |  | 53/8 | DA+3 |  | 04.01.25 | 09.01.25 | Ganesh Sinha | Complete |  |  |  | 38.847
133 | 4 |  | 74/0 | DB2+0 |  | 05.01.25 | 13.01.25 | Sunny Const | Complete |  |  |  | 57.598
134 | 5 |  | 73/4 | DA+0 |  | 10.01.25 | 14.01.25 | Chinta devi | Complete |  |  |  | 37.504
135 | 6 |  | 53/7 | DA+3 |  | 10.01.25 | 18.01.25 | Ganesh Sinha | Complete |  |  |  | 38.847
136 | 7 |  | 73/5 | DA+0 |  | 15.01.25 | 19.01.25 | Chinta devi | Complete |  |  |  | 37.504
137 | 8 |  | 73/7 | DA+0 |  | 14.01.25 | 19.01.25 | Sunny Const | Complete |  |  |  | 37.504
138 | 9 |  | 72/0 | DB2+3 |  | 21.01.25 | 27.01.25 | Chinta Devi | Complete |  |  |  | 60.097
139 | 10 |  | 66/0 | DC+6 |  | 11.01.25 | 29.01.25 | Sanjeev Kumar | Complete |  |  |  | 78.132
140 | 11 |  | 53/6 | DA+6 |  | 19.01.25 | 30.01.25 | Ganesh Sinha | Complete |  |  |  | 45.413
| Feb'25 | [12 empty] | 526.548
141 | 1 |  | 72/1 | DA+3 |  | 28.01.25 | 02.02.25 | Chinta Devi | Complete |  |  |  | 38.847
142 | 2 |  | 65/10 | DA+0 |  | 29.01.25 | 06.02.25 | Sanjeev Kumar | Complete |  |  |  | 37.504
143 | 3 |  | 72/2 | DA+0 |  | 02.02.25 | 06.02.25 | Chinta Devi | Complete |  |  |  | 37.504
144 | 4 |  | 51/0 | DC2+0 |  | 31.01.25 | 07.02.25 | Sunny Const. | Complete |  |  |  | 66.381
145 | 5 |  | 71/8 | DA+3 |  | 07.02.25 | 10.02.25 | Chinta Devi | Complete |  |  |  | 38.847
146 | 6 |  | 52/0 | DC2+0 |  | 08.02.25 | 14.02.25 | Sunny Const. | Complete |  |  |  | 66.381
147 | 7 |  | 49/0 | DD45+0 |  | 05.02.25 | 14.02.25 | Sobha Devi | Complete |  |  |  | 86.129
148 | 8 |  | 71/7 | DA+3 |  | 11.02.25 | 15.02.25 | Chinta Devi | Complete |  |  |  | 38.847
149 | 9 |  | 71/6 | DA+0 |  | 16.02.25 | 19.02.25 | Chinta Devi | Complete |  |  |  | 37.504
150 | 10 |  | 50/5 | DA+9 |  | 15.02.25 | 20.02.25 | Sobha Devi | Complete |  |  |  | 47.418
151 | 11 |  | 71/5 | DA+3 |  | 20.02.25 | 24.02.25 | Chinta Devi | Complete |  |  |  | 38.847
| March'25 | [12 empty] | 534.209
152 | 1 |  | 71/4 | DA+3 |  | 25.02.25 | 01.03.25 | Chinta Devi | Complete |  |  |  | 38.847
153 | 2 |  | 53/5 | DA+3 |  | 01.3.25 | 07.03.25 | Ganesh Sinha | Complete |  |  |  | 38.847
154 | 3 |  | 71/3 | DA+6 |  | 02.03.25 | 07.03.25 | Chinta Devi | Complete |  |  |  | 45.413
155 | 4 |  | 58/0 | DC1+3 |  | 26.02.25 | 10.03.25 | Jirwa Devi | Complete |  |  |  | 69.228
156 | 5 |  | 71/2 | DA+3 |  | 08.03.25 | 12.03.25 | Chinta Devi | Complete |  |  |  | 38.847
157 | 6 |  | 70/3 | DA+3 |  | 08.03.25 | 16.03.25 | Sanjeev kumar | Complete |  |  |  | 38.847
158 | 7 |  | 53/4 | DA+0 |  | 09.03.25 | 17.03.25 | Ganesh Sinha | Complete |  |  |  | 37.504
159 | 8 |  | 71/1 | DA+3 |  | 13.03.25 | 18.03.25 | Chinta Devi | Complete |  |  |  | 38.847
160 | 9 |  | 53/3 | DA+6 |  | 18.03.25 | 25.03.25 | Ganesh Sinha | Complete |  |  |  | 45.413
161 | 10 |  | 71/0 | DB2+3 |  | 19.03.25 | 25.03.25 | Chinta Devi | Complete |  |  |  | 60.097
162 | 11 |  | 70/5 | DA+3 |  | 20.03.25 | 29.03.25 | Sanjeev kumar | Complete |  |  |  | 38.847
163 | 12 |  | 53/2 | DA+0 |  | 26.03.25 | 31.03.25 | Ganesh Sinha | Complete |  |  |  | 37.504 | 451.89
164 | 13 |  | 70/11 | DA+3 |  | 26.03.25 | 31.03.25 | Chinta Devi | Complete |  |  |  | 38.847
April'25
165 | 1 |  | 47/9 | DA+3 |  | 31.03.25 | 02.04.25 | Sobha Devi | Complete |  |  |  | 38.847
166 | 2 |  | 70/10 | DA+3 |  | 31.03.25 | 04.04.25 | Chinta Devi | Complete |  |  |  | 38.847
167 | 3 |  | 53/1 | DA+9 |  | 02.04.25 |  | Ganesh Sinha | 2nd Section |  |  |  | 47.418
168 | 4 |  | 70/9 | DA+3 |  |  |  | Chinta Devi | TNP shifting
169 | 5 |  | 68/0 | DD+0 |  | 13.03.25 |  | Sunny Const. | 1st Section |  |  |  | 86.129
170 | 6 |  | 47/8 | DA+0 |  | 03.04.25 |  | Sobha Devi | Cage-1 |  |  |  | 37.504

## Sheet1 (hidden)
S No | Loc No | TOT | Classification
1 | 58/14 | DA+0 | DRY
2 | 51/7 | DA+3 | DFR
3 | 51/5 | DA+0 | DRY
4 | 51/2 | DA+0 | DRY
5 | 53/2 | DA+3 | DFR
6 | 57/7 | DA+3 | DRY
7 | 57/4 | DA+0 | DRY
8 | 55/7 | DA+0 | DRY
9 | 57/5 | DA+3 | DRY
10 | 55/1 | DA+3 | DRY
11 | 55/8 | DA+3 | DRY
12 | 57/2 | DA+0 | DRY
13 | 55/9 | DA+0 | DRY
14 | 57/1 | DA+3 | DRY
15 | 57/3 | DA+0 | DRY
16 | 72/3 | DA+0 | DRY
17 | 43/4 | DA+9 | DRY
18 | 72/4 | DA+0 | DRY
19 | 43/5 | DA+0 | SANDY
20 | 56/9 | DA+3 | DRY
21 | 71/1 | DA+0 | DRY
22 | 56/8 | DA+3 | DRY
23 | 55/10 | DA+3 | DRY
24 | 56/7 | DA+3 | DRY
25 | 55/4 | DA+3 | DFR

## JMC 27.9.23 (hidden)
S no | Locs no | TOT | Classification
1 | 56/3 | DA+0 | DFR | 14.09.23 | 23.09.23 | 25.09.23 | Vaishali Const | JMC required
2 | 44/1 | DA+0 | WFR | 16.09.23 | 20.09.23 | 25.09.23 | Shakti Construction | JMC required
3 | 72/5 | DA+0 | DRY | 19.09.23 | 24.09.23 | 25.09.23 | Mahadev engg. | JMC required
4 | 41/10 | DA+3 | SANDY | 19.09.23 | 22.09.23 | 25.09.23 | Om Const | JMC required
5 | 56/6 | DA+3 | DRY | 21.09.23 | 24.09.23 | 25.09.23 | Manoj Sharma | JMC required
6 | 72/2 | DA+0 | DRY | 15.09.23 | 20.09.23 | 26.09.23 | Mahadev engg. | JMC required
7 | 51/1 | DA+0 | DFR | 10.09.23 |  |  | Amirul Islam | Excavation u/p
8 | 50/3 | DA+0 | DFR | 18.09.23 | 21.09.23 |  | Shri Bhadariyarai Enterprises | Casting
9 | 56/1 | DA+3 | DFR | 21.09.23 |  |  | Vaishali Const | Excavation done
10 | 44/4 | DA+0 | WFR | 19.09.23 | 23.09.23 |  | B S Electrical | Casting
11 | 55/5 | DA+0 | DFR | 22.09.23 |  |  | Amirul Islam | Frustum complete | Manpower | 6
12 | 71/3 | DA+0 | DRY | 21.09.23 |  |  | Mahadev engg. | Block level done
13 | 71/4 | DA+0 | DRY | 23.09.23 |  |  | Mahadev engg. | Excavation complete |  |  | 51
14 | 55/11 | DA+3 | DFR | 22.09.23 |  |  | Nurul Amin | Excavation u/p |  |  | 32
15 | 44/2 | DA+0 | SANDY | 24.9.23 |  |  | Shakti Construction | PCC u/p
16 | 56/4 | DA+3 | DFR | 24.9.23 |  |  | Manoj Sharma | Excavation
17 | 41/11 | DA+3 | SANDY | 23.09.23 |  |  | Om Const | PCC u/p
18 | 56/5 | DA+3 | DRY |  |  |  | Manoj Sharma | Pit marking done
19 | 71/5 | DA+0 |  | 26.09.23 |  |  | Mahadev engg. | Excavation u/p
20 | 46/2 | DA+0 | DRY |  |  |  | Shri Bhadariyarai Enterprises | Excavation u/p
21 | 55/6 | DA+3 |  |  |  |  | Amirul Islam | Excavation u/p

## Jumpering-G (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Insulator Hoisting
Cum Sl. No. | Month Sl. No. | Location No. | Tower Type | Dt. of Jumpering | Name of Sub-Contractor | Ramarks
1 | 1 | 57/6 | DB+0 | 02.06.24 | GPJ Const. | Done
2 | 2 | 57/0 | DB2+0 | 12.07.24 | GPJ Const. | Done
3 | 3 | 56/0 | DB1+0 | 21.07.24 | GPJ Const. | Done
4 | 4 | 55/0 | DC1+0 |  | GPJ Const. | Done
5 | 5 | 53/0 | DC2+3 | 15.09.24 | GPJ Const. | Done
6 | 6 | 51/0 |  | 19.10.24 | GPJ Const. | Done
7 | 7 | 58/7 |  |  | Kuddus | Done
8 | 8 | 72/7 |  | 26.12.24 |  | Done

## Insulator Hoisting - F (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Insulator Hoisting
Cum Sl. No. | Month Sl. No. | Location No. | Tower Type | Dt. of Start | Dt. of Complete | Name of Sub-Contractor | Ramarks
July'24
1 | 1 | 60/11 | DA+3 | 21.07.24 | 21.07.24 | Kuddus | Complete
2 | 2 | 60/9 | DA+3 | 22.07.24 | 22.07.24 | Kuddus | Complete
3 | 3 | 60/10 | DA+0 | 22.07.24 | 22.07.24 | Kuddus | Complete
4 | 4 | 60/8 | DA+0 | 23.07.24 | 23.07.24 | Kuddus | Complete
5 | 5 | 60/7 | DA+3 | 23.07.24 | 23.07.24 | Kuddus | Complete
6 | 6 | 60/6 | DA+0 | 24.07.24 | 24.07.24 | Kuddus | Complete
7 | 7 | 60/5 | DA+3 | 24.07.24 | 24.07.24 | Kuddus | Complete
8 | 8 | 60/3 | DA+3 | 25.07.24 |  | Kuddus | 5 Phase hoisting done
9 | 9 | 60/4 | DA+3 | 25.07.24 | 25.07.24 | Kuddus | Complete
10 | 10 | 61/0 | DB2+0 | 26.07.24 | 26.07.24 | Kuddus | Complete
11 | 11 | 61/1 | DA+6 | 28.07.24 | 28.07.24 | Kuddus | Complete
12 | 12 | 61/2 | DA+6 | 28.07.24 | 28.07.24 | Kuddus | Complete
13 | 13 | 61/3 | DA+6 | 28.07.24 | 28.07.24 | Kuddus | Complete
14 | 14 | 61/4 | DA+3 | 29.07.24 | 29.07.24 | Kuddus | Complete
15 | 15 | 61/5 | DA+3 | 29.07.24 | 29.07.24 | Kuddus | Complete
16 | 16 | 61/6 | DA+3 | 29.07.24 | 29.07.24 | Kuddus | Complete
17 | 17 | 61/10 | DA+9 | 30.07.24 | 30.07.24 | Kuddus | Complete
18 | 18 | 61/8 | DA+6 | 31.07.24 | 31.07.24 | Kuddus | Complete
19 | 19 | 61/9 | DA+0 | 31.07.24 | 31.07.24 | Kuddus | Complete
Aug'24
20 | 1 | 61/7 | DA+9 | 01.08.24 | 01.08.24 | Kuddus | Complete
21 | 2 | 60/1 | DA+6 | 03.08.24 | 03.08.24 | Kuddus | Complete
22 | 3 | 60/2 | DA+3 | 03.08.24 | 03.08.24 | Kuddus | Complete
Sept'24
23 | 1 | 62/1 | DA+3 | 03.09.24 | 03.09.24 | Kuddus | Complete
24 | 2 | 62/2 | DA+3 | 03.09.24 | 03.09.24 | Kuddus | Complete
25 | 3 | 62/4 | DA+3 | 04.09.24 | 04.09.24 | Kuddus | Complete
26 | 4 | 62/3 | DA+0 | 05.09.24 | 05.09.24 | Kuddus | Complete
27 | 5 | 62/5 | DA+0 | 09.09.24 | 09.09.24 | Kuddus | Complete
28 | 6 | 62/6 | DA+3 | 12.09.24 | 12.09.24 | Kuddus | Complete
29 | 7 | 62/7 | DA+3 | 12.09.24 | 12.09.24 | Kuddus | Complete
30 | 8 | 62/8 | DA+0 | 14.09.24 | 14.09.24 | Kuddus | Complete
31 | 9 | 62/10 | DA+0 | 15.09.24 | 15.09.24 | Kuddus | Complete
32 | 10 | 62/11 | DA+3 | 15.09.24 | 15.09.24 | Kuddus | Complete
33 | 11 | 62/9 |  | 16.09.24 | 16.09.24 | Kuddus | Complete
34 | 1 | 63/4 |  | 05.10.24 | 05.10.24 | Kuddus | Complete
35 | 2 | 63/7 |  | 09.10.24 | 09.10.24 | Kuddus | Complete

## Insulator Hoisting - G (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Insulator Hoisting
Cum Sl. No. | Month Sl. No. | Location No. | Tower Type | Dt. of Start | Dt. of Complete | Name of Sub-Contractor | Ramarks
Jan'24
1 | 1 | 57/5 | DA+3 | 05.01.24 | 05.01.24 | Mainul Hoque | Complete
2 | 2 | 57/4 | DA+0 | 06.01.24 | 06.01.24 | Mainul Hoque | Complete
3 | 3 | 57/3 | DA+0 | 07.01.24 | 07.01.24 | Mainul Hoque | Complete
4 | 4 | 57/2 | DA+0 | 07.01.24 | 07.01.24 | Mainul Hoque | Complete
April'24
5 | 1 | 57/7 | DA+3 | 08.04.24 | 08.04.24 | GPJ Const. | Complete
6 | 2 | 57/9 | DA+0 | 09.04.24 | 09.04.24 | GPJ Const. | Complete
7 | 3 | 57/11 | DA+0 | 09.04.24 | 09.04.24 | GPJ Const. | Complete
8 | 4 | 57/12 | DA+3 | 10.04.24 | 10.04.24 | GPJ Const. | Complete
9 | 5 | 57/13 | DA+0 | 10.04.24 | 10.04.24 | GPJ Const. | Complete
10 | 6 | 57/1 | DA+3 | 11.04.24 | 11.04.24 | GPJ Const. | Complete
11 | 7 | 57/10 | DA+0 | 11.04.24 | 11.04.24 | GPJ Const. | Complete
12 | 8 | 56/8 | DA+3 | 12.04.24 | 12.04.24 | GPJ Const. | Complete
13 | 9 | 56/9 | DA+3 | 12.04.24 | 12.04.24 | GPJ Const. | Complete
14 | 10 | 56/6 | DA+3 | 13.04.24 | 13.04.24 | GPJ Const. | Complete
15 | 11 | 56/7 | DA+3 | 13.04.24 | 13.04.24 | GPJ Const. | Complete
16 | 12 | 56/4 | DA+3 | 14.04.24 | 14.04.24 | GPJ Const. | Complete
17 | 13 | 56/5 | DA+0 | 14.04.24 | 14.04.24 | GPJ Const. | Complete
18 | 14 | 56/3 | DA+0 | 15.04.24 | 15.04.24 | GPJ Const. | Complete
19 | 15 | 56/2 | DA+3 | 15.04.24 | 15.04.24 | GPJ Const. | Complete
20 | 16 | 55/10 | DA+3 | 16.04.24 | 16.04.24 | GPJ Const. | Complete
21 | 17 | 55/11 | DA+3 | 16.04.24 | 16.04.24 | GPJ Const. | Complete
22 | 18 | 55/9 | DA+3 | 17.04.24 | 17.04.24 | GPJ Const. | Complete
23 | 19 | 55/7 | DA+0 | 17.04.24 | 17.04.24 | GPJ Const. | Complete
24 | 20 | 55/6 | DA+3 | 17.04.24 | 17.04.24 | GPJ Const. | Complete
25 | 21 | 55/1 | DA+3 | 18.04.24 | 18.04.24 | GPJ Const. | Complete
26 | 22 | 55/2 | DA+3 | 18.04.24 | 18.04.24 | GPJ Const. | Complete
27 | 23 | 55/3 | DA+0 | 18.04.24 | 18.04.24 | GPJ Const. | Complete
28 | 24 | 55/5 | DA+0 | 18.04.24 | 18.04.24 | GPJ Const. | Complete
29 | 25 | 55/8 | DA+3 | 19.04.24 | 19.04.24 | GPJ Const. | Complete
30 | 26 | 53/2 | DA+3 | 20.04.24 | 20.04.24 | GPJ Const. | Complete
31 | 27 | 53/3 | DA+3 | 20.04.24 | 20.04.24 | GPJ Const. | Complete
32 | 28 | 53/4 | DA+3 | 20.04.24 | 20.04.24 | GPJ Const. | Complete
33 | 29 | 57/6 | DB+0 | 21.04.24 | 21.04.24 | GPJ Const. | Complete
34 | 30 | 57/0 | DB+0 | 22.04.24 | 22.04.24 | GPJ Const. | Complete
35 | 31 | 51/8 | DA+3 | 23.04.24 | 23.04.24 | GPJ Const. | Complete
36 | 32 | 51/9 | DA+3 | 23.04.24 | 23.04.24 | GPJ Const. | Complete
37 | 33 | 56/1 | DA+3 | 24.04.24 | 24.04.24 | GPJ Const. | Complete
38 | 34 | 56/0 | DB+0 | 26.04.24 | 26.04.24 | GPJ Const. | Complete
39 | 35 | 51/6 | DA+0 | 27.04.24 | 27.04.24 | GPJ Const. | Complete
40 | 36 | 51/7 | DA+3 | 27.04.24 | 27.04.24 | GPJ Const. | Complete
41` | 37 | 57/8 | DA+3 | 28.04.24 | 28.04.24 | GPJ Const. | Complete
May'24
42 | 1 | 58/0 | DC2+0 | 04.05.24 | 19.09.24 | GPJ Const. | Complete
June'24
43 | 1 | 55/0 | DC1+0 | 02.06.24 | 02.06.24 | GPJ Const. | Complete | 07.09.24
July'24
44 | 1 | 53/1 | DA+0 | 08.07.24 | 08.07.24 | GPJ Const. | Complete
45 | 2 | 53/0 | DC2+3 | 10.07.24 | 31.07.24 | GPJ Const. | Complete
46 | 3 | 52/1 | DA+0 | 29.07.24 | 29.07.24 | GPJ Const. | Complete
47 | 4 | 52/2 | DA+3 | 29.07.24 | 29.07.24 | GPJ Const. | Complete
48 | 5 | 52/3 | DA+0 | 30.07.24 | 30.07.24 | GPJ Const. | Complete
Aug'24
49 | 1 | 52/0 | DB2+0 | 14.08.24 | 14.08.24 | GPJ Const. | Complete
50 | 2 | 51/10 | DA+3 | 14.08.24 | 14.08.24 | GPJ Const. | Complete
51 | 3 | 51/1 | DA+0 | 23.08.24 | 23.08.24 | GPJ Const. | Complete
52 | 4 | 51/3 | DA+0 | 24.08.24 | 24.08.24 | GPJ Const. | Complete
53 | 5 | 51/4 | DA+3 | 24.08.24 | 24.08.24 | GPJ Const. | Complete
54 | 6 | 51/5 | DA+0 | 24.08.24 | 24.08.24 | GPJ Const. | Complete
55 | 7 | 51/0 | DB2+0 | 25.08.24 | 25.08.24 | GPJ Const. | Complete
56 | 8 | 51/2 | DA+0 | 25.08.24 | 25.08.24 | GPJ Const. | Complete
Sept'24
57 | 1 | 50/4 | DA+3 | 15.09.24 | 15.09.24 | GPJ Const. | Complete
58 | 2 | 50/3 | DA+0 | 16.09.24 | 16.09.24 | GPJ Const. | Complete
59 | 3 | 58/1 | DA+0 | 19.09.24 | 19.09.24 | GPJ Const. | Complete
60 | 4 | 50/2 | DA+0 | 21.09.24 | 21.09.24 | GPJ Const. | Complete
61 | 5 | 50/0 | DC2+3 | 07.10.24 | 07.10.24 | GPJ Const. | Complete

## Jumpering-F (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Insulator Hoisting
Cum Sl. No. | Month Sl. No. | Location No. | Tower Type | Dt. of Jumpering | Name of Sub-Contractor | Ramarks
1 | 1 | 61/0 |  | 23.10.24 | Kuddua Ali
2 | 2 | 62/0 |  | 11.11.24 | Kuddua Ali

## Stringing - PKG-F (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
STRINGING
Stringing - PKG-F
S. No | Section |  |  |  | Paying Out |  |  | Final Sag |  |  | Name of Gang | Remarks
| From | To | Length | Cum | Start Date | Finish Date | Month | Start Date | Finish Date | Month
1 | 60/0 | 61/0 | 4.877 | 4.877 | 21.08.24 | 28.08.24 | 2024-08-24 | 09.09.24 | 16.09.24 | 2024-09-24 | Kuddus ali | Final sag completed
2 | 61/0 | 62/0 | 4.568 | 9.445 | 06.09.24 | 16.09.24 | 2024-09-24 | 26.9.24 | 03.10.24 | 2024-10-24 | Kuddus ali | Final sag completed
3 | 62/0 | 63/0 | 4.863 | 14.308 | 23.09.24 | 02.10.24 | 2024-10-24 | 17.10.24 | 22.10.24 | 2024-10-24 | Kuddus ali | Final sag completed
4 | 63/0 | 64/0 | 3.711 | 18.019 | 14.10.24 | 21.10.24 | 2024-10-24 | 31.10.24 | 06.11.24 | 2024-11-24 | Kuddus ali | Final sag completed
5 | 64/0 | 65/0 | 4.918 | 22.937 | 30.10.24 | 05.11.24 | 2024-11-24 | 13.11.24 | 16.11.24 | 2024-11-24 | Kuddus ali | Final sag completed
6 | 59/8 | 60/0 | 3.778 | 26.715 | 22.12.24 | 27.12.24 | 2024-12-24 | 04.01.25 | 09.01.25 | 2025-01-25 | Gopal Associate | Final sag completed
7 | 59/0 | 59/8 | 3.337 | 30.052 | 02.01.25 | 08.01.25 | 2025-01-25 | 12.01.25 | 15.01.25 | 2025-01-25 | Gopal Associate | Final sag completed
8 | 65/0 | 66/0 | 4.736 | 34.788 | 3.02.25 | 22.03.25 | 2025-03-25 | 10.03.25 | 23.03.25 | 2025-03-25 | MR Power | Final sag completed
9 | 50/0 | 51/0 | 4.444 | 39.232 | 12.03.25 | 23.03.25 | 2025-03-25 | 17.03.25 | 24.03.25 | 2025-03-25 | Gopal Associate | Final sag completed & 50/6 Clipping done | 50/4 &50/6 Hoisting done-23.02.25 | 50/8 &50/9, 50/10 Hoisting done | 51/1 & 51/2 Hoisting done
10 | 49/0 | 50/0 | 3.227 | 42.459 | 06.02.25 | 19.02.25 | 2025-03-25 |  |  |  | Gopal Associate | Rough sag done & Earth wire payour rough sag done
11 | 51/0 | 52/0 | 1.049 | 43.508 | 02.04.25 |  | 2025-03-25 | 04.04.25 |  |  | Gopal Associate | Top phase Final Sag done | 35
12 | 48/0 | 49/0 | 0.832 | 44.34 |  |  | 2025-03-25 |  |  |  | Gopal Associate

## Stringing - PKG-G (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
STRINGING- PKG-G
S. No | Section |  |  | Paying Out |  |  | Final Sag |  |  | Name of Gang | Remarks
| From | To | Length | Start Date | Finish Date | Month | Start Date | Finish Date | Month
1 | 57/6 | 58/0 | 3.141 | 06.05.2024 | 10.05.24 | 2024-05-24 | 19.05.24 | 24.05.24 | 2024-05-24 | GPJ Const. | Final sag done
2 | 57/0 | 57/6 | 2.344 | 16.05.24 | 24.05.24 | 2024-05-24 | 07.06.24 | 12.06.25 | 2024-06-24 | GPJ Const. | Final sag done
3 | 56/0 | 57/0 | 4.127 | 04.06.24 | 12.06.24 | 2024-06-24 | 28.06.24 | 04.07.24 | 2024-07-24 | GPJ Const. | Final sag done
4 | 55/0 | 56/0 | 4.9 | 25.06.24 | 04.07.24 | 2024-07-24 | 17.07.24 | 22.07.24 | 2024-07-24 | GPJ Const. | Final sag done
5 | 53/0 | 55/0 | 2.013 | 16.07.24 | 22.07.24 | 2024-07-24 | 09.08.24 | 10.08.24 | 2024-08-24 | GPJ Const. | Final sag done
6 | 52/0 | 53/0 | 2.364 | 19.08.24 | 22.08.24 | 2024-08-24 | 04.09.24 | 09.09.24 | 2024-09-24 | GPJ Const. | Final sag done
7 | 51/0 | 52/0 | 4.403 | 01.09.24 | 08.09.24 | 2024-09-24 | 28.09.24 | 05.10.24 | 2024-10-24 | GPJ Const. | Final sag done
8 | 50/0 | 51/0 | 1.971 | 26.9.24 | 02.10.24 | 2024-10-24 | 08.10.24 | 10.10.24 | 2024-10-24 | GPJ Const. | Final sag done
9 | 72/7 | 73/0 | 0.49623 | 12.11.24 | 15.11.24 | 2024-11-24 | 27.11.24 | 29.11.24 | 2024-11-24 | MR Power | Final sag done
10 | 58/0 | 58/7 | 2.797 | 20.11.24 | 23.11.24 | 2024-11-24 | 01.12.245 | 05.12.24 | 2024-12-24 | Kddus Ali | Final sag done
11 | 72/0 | 72/7 | 2.589 | 18.11.24 | 23.11.24 | 2024-11-24 | 06.12.24 | 10.12.24 | 2024-12-24 | MR Power | Final sag done
12 | 67/1 | 68/0 | 0.42647 | 22.12.24 | 23.12.24 | 2024-12-24 | 23.12.24 | 25.12.25 | 2024-12-24 | Nasruddin | Final sag done
13 | 68/0 | 69/0 | 2.855 | 11.12.24 | 20.12.24 | 2024-12-24 | 01.01.25 | 05.01.25 | 2025-01-25 | Nasruddin | Final sag done
16 | 58/7 | 59/0 | 3.885 | 27.12.24 | 04.01.25 | 2025-01-25 | 07.01.25 | 09.01.25 | 2025-01-25 | MR Power | Final sag done
17 | 71/0 | 72/0 | 2.092 | 03.12.24 | 10.12.24 | 2024-12-24 | 16.01.25 | 19.01.25 | 2025-01-25 | MR Power | Final sag done
18 | 67/0 | 67/1 | 0.43755 | 21.12.24 | 22.12.24 | 2024-12-24 | 20.01.25 | 21.01.25 | 2025-01-25 | Nasruddin | Final sag done
19 | 69/0 | 70/0 | 3.881 | 30.12.24 | 05.01.25 | 2025-01-25 | 27.01.25 | 28.01.25 | 2025-01-26 | Nasruddin | Final sag done
21 | 41/0 | 42/0 | 4.981 | 13.02.25 | 20.02.25 | 2025-02-25 | 28.02.25 | 02.03.25 | 2025-03-26 | Nasruddin | Final sag done | 41/0 hoisting done
20 | 59/0 | 60/0 | 2.581 | 20.01.25 | 25.01.25 | 2025-01-25 |  |  |  | MR Power | Final sag arrangement wip

## OPGW PKG-G (hidden)
EXECUTING AGENCY : M/s. KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
OPGW Progress details(Pkg-G)
Sr. No | Section |  | Section length in Kms | OPGW Drum Length (In KMs) | Start date | End date | Splicing | Jointing Details | Agency | OTDR reading status | Splicing done by | Remarks
1 | 51/0 | 52/0 | 4.403 | 4.653 | 11.01.25 | 12.01.25 |  |  | Congent tech |  |  | Final sag completed
2 | 52/0 | 55/0 | 4.377 | 4.627 | 17.01.25 | 18.01.25 |  |  | Congent tech |  |  | Final sag completed
3 | 55/0 | 56/0 | 4.9 | 5.16 | 20.01.25 | 21.01.25 |  |  | Congent tech |  |  | Final sag completed
4 | 56/0 | 57/0 | 4.127 | 4.372 | 23.01.25 | 24.01.25 |  |  | Congent tech |  |  | Final sag completed
5 | 57/0 | 57/6 | 1.954 | 2.553 | 27.01.25 | 28.01.25 |  |  | Congent tech |  |  | Final sag completed
6 | 57/6 | 58/0 | 3.141 | 3.365 | 29.01.25 | 30.01.25 |  |  | Congent tech |  |  | Final sag completed
7 | 58/0 | 58/7 | 2.789 | 3.015 | 01.02.25 | 02.02.25 |  |  | Congent tech |  |  | Final sag completed
8 | 58/7 | 59/0 | 3.885 | 4.124 | 04.02.25 | 05.02.25 |  |  | Congent tech |  |  | Final sag completed
Total Length in Kms |  |  | 29.576 | 31.869
Total Length in Km |  |  | 29.576 | 31.869

## OPGW PKG-F (hidden)
EXECUTING AGENCY : M/s. KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
OPGW Progress details(PKG-F)
Sr. No | Section |  | Section length in Kms | OPGW Drum Length (In KMs) | Start date | End date | Splicing | Jointing Details | Agency | OTDR reading status | Splicing done by | Remarks
1 | 59/0 | 59/8 | 3.337 |  | 10.02.25 | 11.02.25 | 05.03.25 |  | Congent tech |  | Revant Sharma | Final Sag Complete
2 | 59/8 | 60/0 | 3.778 |  | 12.02.25 | 13.02.25 | 26.02.25 |  | Congent tech |  | Revant Sharma | Final Sag Complete
3 | 60/0 | 61/0 | 4.877 |  | 15.02.25 | 16.02.25 |  |  | Congent tech |  |  | Final Sag Complete
4 | 61/0 | 62/0 | 4.568 |  | 19.02.25 | 19.02.25 | 27.02.25 |  | Congent tech |  | Revant Sharma | Final Sag Complete
5 | 62/0 | 63/0 | 4.863 |  | 23.02.25 | 24.02.25 |  |  | Congent tech |  |  | Final Sag Complete
6 | 63/0 | 64/0 | 3.711 |  | 01.03.25 | 02.03.25 |  |  | Congent tech |  |  | Final Sag Complete
7 | 64/0 | 65/0 | 4.918 |  | 03.03.25 | 03.03.25 |  |  | Congent tech |  |  | Final Sag Complete
Total Length in Kms |  |  | 30.052 | 0
Total Length in Km |  |  | 30.052 | 0
31.869

## Crossing (hidden)
CROSSING DETAILS FOR 765 KV DC FATEHGARH 3 - BEAWAR T/L (Part-G & Part-F)
Sl No | Crossing Name | PART - G | [6 empty] | PART - F
|  | Section |  | Owner Name | Date of Submission | Date of Site Inspection | Proposal Status | Remarks | Section |  | Owner Name | Date of Submission | Date of Site Inspection | Proposal Status | Remarks
|  | From | To | [5 empty] | From | To
A | Power Line
1 | 400 KV D/C Rajwest - Jodhpur Line | AP 36 | AP 37 | RRVPNL |  |  | Hard copy submitted on - 08/03/24. |  | AP 46 | AP 47 | RRVPNL |  | 2 days |  |  | 5,5,5,5
2 | U/C LILO of 400 KV D/C Rajwest - Jodhpur Line at Newai S/S | AP 45 | AP 46 | RRVPNL | 2023-12-25 |  | Hard copy submitted on - 10/01/24. |  | AP 56 | AP 57 | RRVPNL |  | 1week
3 | 220 KV S/C GSS Boranada - Balotra Line | AP 60 | AP 61 | RRVPNL | 2023-11-13 |  | Approved on dated 18.07.24 |  | AP 66 | AP 67 | RRVPNL | 2024-02-13 |  | Approved on dated 18.07.24
B | Railway
1 | Electrified BG Double Track Line (Jodhpur - Barmer) | AP 70 | AP 71 | NWR |  |  | Hard copy submitted on - 21/02/24.
C | NH/SH
1 | SH - 28 (Bikaner - Barmer) | AP 44 | 44/1 | PWD |  |  | NR |  | AP 55 | 55/1 | PWD
2 | Bharatmala Expressway (Amritsar - Kandla) | AP 49 | AP 50 | NHAI | 2023-11-13 |  | Approved on dated - 01.06.24 |  | AP 58 | AP 59 | NHAI | 2024-01-21 |  | Approved on dated - 01.06.24
3 | SH - 66 (Kalyanpur - Balesar) | 51/7 | 51/8 | PWD |  |  | NR |  | 59/14 | 59/15 | PWD
4 | NH 25 (Jodhpur - Barmer) | AP 62 | AP 63 | NHAI | 2023-12-06 |  | Approved on dated - 24.06.24 |  | AP 68 | AP 69 | NHAI | 2024-02-13 |  | Approved on dated - 24.06.24
5 | SH - 68 (Shikarpura - Luni) | 72/1 | 72/2 | PWD |  |  | NR
D | River
1 | Luni River | 72/7 | AP 73 |  |  |  | NR | NR
E | Pipe Line
1 | Under Ground Oil Pipe Line | 59/2 | 59/3 | HPML |  |  |  | Format awaited from SPTL | 65/7 | 65/8 | HPML
2 | Under Ground Oil Pipe Line (Mundra - Bhatinda) | 72/3 | 72/4 | IOCL

## Clear locs shared by client (hidden)
Erection Workfront_shared by SPTL Section II_29.11.2024
SL No. | Location (G) | Current Status | SL No. | Location(F) | Current Status
1 | 33/1 | Untouch | 1 | 47/2 | Untouch | 33/8
2 | 35/0 | Untouch | 2 | 47/3 | Untouch
3 | 35/1 | Untouch | 3 | 47/5 | Untouch
4 | 35/2 | Untouch | 4 | 47/6 | Untouch
5 | 35/3 | Untouch | 5 | 47/7 | Untouch
6 | 35/4 | Untouch | 6 | 47/8 | Untouch
7 | 35/5 | Untouch | 7 | 47/9 | Untouch |  | 137
8 | 35/6 | Untouch | 8 | 49/0 | Untouch
9 | 35/7 | Untouch | 9 | 49/1 | Untouch
10 | 35/8 | Untouch | 10 | 49/3 | WIP (Sobha Devi)
11 | 37/2 | Untouch | 11 | 51/0 | Untouch
12 | 37/3 | Untouch | 12 | 52/3 | Untouch
13 | 37/4 | Untouch | 13 | 53/5 | Untouch
14 | 38/1 | Untouch | 14 | 53/6 | Untouch
15 | 38/2 | Untouch | 15 | 53/7 | Untouch
16 | 38/3 | Untouch | 16 | 53/8 | Untouch
17 | 38/6 | Untouch | 17 | 54/1 | Untouch
18 | 38/8 | Untouch | 18 | 54/2 | Untouch
19 | 39/0 | Untouch | 19 | 55/7 | Untouch
20 | 39/1 | Untouch | 20 | 57/2 | Untouch
21 | 39/4 | Untouch | 21 | 58/0 | Untouch
22 | 40/2 | Untouch | 22 | 59/0 | Materials shifting wip (Jirwa Devi)
23 | 40/3 | Untouch | 23 | 66/0 | Untouch
24 | 40/4 | Untouch | 24 | 67/0 | Untouch
25 | 40/5 | Untouch | 25 | 69/1 | Untouch
26 | 40/6 | Untouch | 26 | 71/6 | Untouch
27 | 41/12 | Untouch | 27 | 71/7 | Untouch
28 | 42/0 | Untouch | 28 | 73/3 | Untouch
29 | 43/0 | Untouch | 29 | 73/4 | Untouch
30 | 44/0 | Untouch | 30 | 73/5 | Untouch
31 | 49/0 | Untouch | 31 | 73/7 | Untouch
32 | 62/0 | Untouch | 32 | 74/0 | Untouch
33 | 63/2 | Untouch
34 | 63/5 | Untouch
35 | 63/6 | Untouch
36 | 64/0 | Untouch
37 | 65/1 | Untouch
38 | 65/2 | Untouch
39 | 65/6 | Untouch
40 | 65/7 | Untouch
41 | 66/0 | Untouch
42 | 66/1 | WIP (Sanjeev Kumar )
43 | 66/3
44 | 67/0 | WIP (Chinta Devi)
45 | 69/9 | WIP (Sunny const)
46 | 71/0