## DPR
220 kV Neemuch Bay Extension Substation
WORK PLAN- CIVIL WORK
LOA No.: - LOI/EPC/Serentica/Neemuch_Bay Ext/KEC/01 , 26th March 2025 CLIENT- STERLITE POWER
Date:-10-03-2026
Sl No | Description | Unit | Qty | Completed till Feb 26 | Balance for March 26 | Current Month (March 2026)
[6 empty] | Planned | Completed | Progress on Today | Balance | Remarks
#REF! | Internal Cable Trench | RM | 70 | 70 | 0 | - | - | - | - | Completed
#REF! | Brickwork | cum | 186 | 186 | 0 | - | - | - | - | Completed
#REF! | Internal Plaster | sqm | 1017 | 1017 | 0 | - | - | - | - | Completed
#REF! | External Plaster | sqm | 4851 | 4821 | 30 | 30 | 30 | - | -
1 | 220kV SPR Building
1.1 | Internal Cable Trench | LS | 1 | 1 | 0 |  |  |  |  | Completed
1.1 | Excavation | cum | 60 | 60 | 0 |  |  |  |  | Completed
1.2 | PCC | cum | 6 | 6 | 0 | 0 | 0 | - | 0 | Completed
1.3 | Raft | nos | 6 | 6 | 0 | 0 | 0 | - | 0 | Completed
1.4 | Column up to plinth Beam | nos | 6 | 6 | 0 | - | - | - | - | Completed
1.5 | Plinth Beam | rmt | 22 | 22 | 0 |  |  |  |  | Completed
1.6 | Column above to plinth Beam | nos | 6 | 6 | 0 |  |  |  |  | Completed
1.7 | Roof slab & Beam | Nos | 1 | 1 | 0 |  |  |  |  | Completed
18 | Brickwork | cum | 23.5 | 23.5 | 0 |  |  |  |  | Completed
1.9 | Plaster | sqm | 180 | 0 | 180 | 180 | 0 | - | 180
1.1 | Paint | sqm | 180 | 0 | 180 |  | - | -
1.11 | Door | NOS | 2 | 0 | 2 | 2 | - | - | 2
1.12 | Window | NOS | 2 |  | 2 | 2 | - | - | 2
1.13 | Water Proofing | sqm | 48 | 0 | 48
1.14 | Plinth Protection | rmt | 16 | 0 | 16
2 | 220kV Equipment |  |  |  | 0 | 0 | - | -
2.1 | Excavation | Nos | 98 | 76 | 22 | 22 | 5 | 3 | 17 | WIP
2.2 | PCC | Nos | 98 | 71 | 27 | 27 | 2 |  | 25 | WIP
2.3 | Raft Casting | Nos | 98 | 64 | 34 | 34 | 7 | 3 | 27 | WIP
5.1 | Column | NOS | 1 | 1 | 0 | 0 |  |  | 0 | Completed
6.1 | 132kV Equipment | NOS | 1 | 0 | 1 | 1 |  |  | 1
2.4 | Column Casting | Nos | 102 | 55 | 47 | 47 | 7 | 3 | 40 | WIP
3 | OUTDOOR CABLE TRENCH
3.1 | Excavation | RMT | 75 | 0 | 75 | 75 | 0 | - | 75
3.2 | PCC | RMT | 75 | 0 | 75 | 75 | 0 | - | 75
3.3 | Raft Casting | RMT | 75 | 0 | 75 | 75 | 0 | - | 75
3.4 | Wall RCC | RMT | 150 | 0 | 150 | 150 |  |  | 150

## Steel Cement (hidden)
KEC International Ltd. | [9 empty] | Date.17.06.2025
TB-501 220/132Kv Sub-Station Chandriya |  |  | Materials reconcilation statement for the month of May-2025
Sl.No. | Material Description | UOM | Received Qty. |  |  | Issue Qty. to Site |  |  | Total Issue | Total Consumed | Balance
|  |  | Other Store | Received From Supplier | Total | 220/132KV SS | RMC | other Store
1 | Cement | Bag | 1431 | 16713 | 18144 | 14820 | 0 | 2512 | 17332 | 17332 | 812
2 | Cement | MT | 0 | 135.16 | 135.16 | 0 | 135 | 0 | 0 | 135.16 | 0
2 | 8mm Steel | MT | 3.803 | 49.625 | 53.428 | 21.774 | 0 | 0.76 | 22.534 | 24.487 | 28.941
3 | 10mm Steel | MT | 2.119 | 83.24 | 85.359 | 23.461 | 0 | 4.648 | 28.109 | 24.336 | 61.023 | [8 empty] | *
4 | 12mm Steel | MT | 0 | 57.136 | 57.136 | 37.26 | 0 | 6.065 | 43.325 | 37.26 | 19.876
5 | 16mm Steel | MT | 20.924 | 65.641 | 86.565 | 62.358 | 0 | 3.795 | 66.153 | 62.358 | 24.207
6 | 20mm Steel | MT | 0 | 40.69 | 40.69 | 13.244 | 0 | 5.1455 | 18.3895 | 13.244 | 27.446
7 | 25mmSteel | MT | 0.751 | 21.05 | 21.801 | 17.539 | 0 | 0 | 17.539 | 17.539 | 4.262
Abstract
|  |  |  | Month |  | 8MM |  |  |  | 10MM | 12MM | 16MM | 20MM | 25MM | 28MM | 32MM | All dia Mix | CUM TOTAL | Remarks
|  |  |  | Total Received Qty |  | 49.625 |  |  |  | 83.24 | 57.136 | 65.641 | 40.69 | 21.05 | #REF! | #REF! | #REF! | #REF!
|  |  |  | Issue to Site |  | 24.144 |  |  |  | 26.905 | 40.46 | 68.046 | 16.206 | 17.539 | #REF! | #REF! | #REF! | #REF!
|  |  |  | Issue to Other Store |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total Consumption Qty in MT | JAN -16 consumed | 24.144 |  |  |  | 26.905 | 40.46 | 68.046 | 16.206 | 17.539 | #REF! | #REF! | #REF! | #REF!
|  |  |  | Balance Stock Qty in MT | JAN -16 consumed | 25.481 |  |  |  | 56.335 | 16.676 | -2.405 | 24.484 | 3.511 | #REF! | #REF! | #REF! | #REF!