## Summary
765 kV D/C BEAWAR MANDSAUR TRANSMISSION LINE
Revenue Cost (October-2025)
Sr. No. | Description | UOM | Locations (As per Micro Plan) | Locations (To be Achieved) | Amount in Rs. (As per Micro Plan) | Amount in Rs (To be Achieved)
1 | Foundation | Nos | 30 | 1 | 20509194.0832 | 564041.6
2 | Erection | Nos | 48 | 5 | 27566250.98 | 2815813.78
3 | Stringing | Kms | - |  | -
| Total Amount (Rs) = |  |  |  | 48075445.0632 | 3379855.38

## FDN
Project Code |  |  | TA-505
Name of Line |  |  | 765KV D/C BEAWAR MANDSAUR (PKG-TL02)
Activity |  |  | Foundation | Qty
|  |  | Total | 371
|  |  | Completed (Till Sept-25) | 283
|  |  | Balance | 88
Micro Plan for month |  |  | 2025-10-01 | 30 | Nos | 20193024.0832 | Rs. Cr. |  |  |  | Total Cost with Earthing |  | 316170 | 20509194.0832
Achievement for Month |  |  | Wk-1 | 1 | 3.333% | 564041.6 | 2.793%
|  |  | Wk-2 | 0 | 0% | 0 | 0%
|  |  | Wk-3 | 0 | 0% | 0 | 0%
|  |  | Wk-4 | 0 | 0% | 0 | 0%
|  |  | Wk-5 | 0 | 0% | 0 | 0%
Actual for the Month |  |  | Total | 1 | 0.033333 | 564041.6 | 0.027932 |  |  |  | Actual Cost with Earthing |  | 10539 | 574580.6
SL | Loc No. | Tower Type | Classification | Conc. Vol (CuM) | Reinf (MT) | Sub-Cont | KEC Responsibility | Section | Work Plan | [7 empty] | Revenue | Actual Completion | Physical Completion | [5 empty] | Revenue Achievement | [5 empty] | Shortfall
[9 empty] | Excavation |  | Stub-setting |  | Concreting |  | Earthing | Backfilling |  |  | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total
[9 empty] | Start | End | Start | End | Start | End |  |  | Rs. Lacs. | Date | [11 empty] | Rs. Lacs. | Rs. Lacs.
1 | 168/0 | DC2+0 | DFR | 101.79 | 4.557 | Saktawat | P. Satish | MP | 2025-10-01 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-10 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 1268583.84 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1268583.84
2 | 169/8 | DA+0 | DRY | 26.39 | 1.979 | Saktawat | P. Satish | MP | 2025-10-04 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-16 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 485697.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
3 | 169/9 | DA-3 | DRY | 26.39 | 1.979 | Saktawat | P. Satish | MP | 2025-10-07 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-22 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 485697.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
4 | 169/0 | DC1+3 | DFR | 83.13 | 3.855 | Saktawat | P. Satish | MP | 2025-10-10 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-28 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 1235682.7 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1235682.7
5 | 165/0 | DB1+6 | DFR | 63.24 | 2.716 | Garg Const. | P. Satish | MP | 2025-10-01 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-10 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 812044.6526 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 812044.6526
6 | 165/2 | DA+0 | DRY | 26.39 | 1.979 | Garg Const. | P. Satish | MP | 2025-10-04 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-16 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 485697.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
7 | 162/1 | DA+0 | DRY | 26.39 | 1.979 | Garg Const. | P. Satish | MP | 2025-10-07 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-22 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 485697.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
8 | 162/2 | DA+0 | DRY | 26.39 | 1.979 | Garg Const. | P. Satish | MP | 2025-10-10 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-28 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 485697.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
9 | 162/0 | DB2+0 | DFR | 76.03 | 3.4 | RESHMI DEVI | P. Satish | MP | 2025-10-01 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-10 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 922043.6526 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 922043.6526
10 | 179/0 | DC2+0 | DFR | 101.79 | 4.557 | RESHMI DEVI | P. Satish | MP | 2025-10-04 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-16 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 1268583.84 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1268583.84
11 | 179/3 | DA+0 | DRY | 26.39 | 1.979 | RESHMI DEVI | P. Satish | MP | 2025-10-07 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-22 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 485697.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
12 | 179/5 | DA+0 | DRY | 26.39 | 1.979 | RESHMI DEVI | P. Satish | MP | 2025-10-10 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-28 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 485697.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
13 | 179/8 | DA+0 | DRY | 26.39 | 1.979 | INFINITY CONST. | P. Satish | MP | 2025-10-01 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-10 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 485697.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
14 | 179/9 | DA+3 | DRY | 29.42 | 2.473 | INFINITY CONST. | P. Satish | MP | 2025-10-04 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-16 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 564041.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 564041.6
15 | 181/1 | DA+0 | DRY | 26.39 | 1.979 | INFINITY CONST. | P. Satish | MP | 2025-10-07 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-22 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 485697.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
16 | 181/2 | DA-3 | DRY | 26.39 | 1.979 | INFINITY CONST. | P. Satish | MP | 2025-10-10 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-28 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 485697.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
17 | 181/3 | DA-3 | DRY | 26.39 | 1.979 | New Gang-MP | P. Satish | MP | 2025-10-01 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-10 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 485697.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
18 | 181/4 | DA-3 | DRY | 26.39 | 1.979 | New Gang-MP | P. Satish | MP | 2025-10-04 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-16 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 485697.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
19 | 181/5 | DA-3 | DRY | 26.39 | 1.979 | New Gang-MP | P. Satish | MP | 2025-10-07 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-22 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 485697.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
20 | 181/6 | DA+0 | DRY | 26.39 | 1.979 | New Gang-MP | P. Satish | MP | 2025-10-10 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-28 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 485697.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
21 | 100/0 | DD45+0 | DFR | 101.56 | 8.669 | Sumit Const. | Deepak Anand | RAJ | 2025-10-01 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-10 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 1438583.84 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1438583.84
22 | 103/5 | DA+3 (RC) | DFR | 34.29 | 1.802 | Sumit Const. | Deepak Anand | RAJ | 2025-10-04 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-16 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 564041.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 564041.6
23 | 149B/1 | DB2+15 | DFR | 34.29 | 1.802 | RST | Deepak Anand | RAJ | 2025-10-01 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-10 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 922043.6526 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 922043.6526
24 | 149B/2 | DA+6 (RC) | DFR | 34.29 | 1.802 | RST | Deepak Anand | RAJ | 2025-10-04 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-16 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 564041.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 564041.6
25 | 149B/4 | DA+0 (RC) | DFR | 30.22 | 1.45 | RST | Deepak Anand | RAJ | 2025-10-07 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-22 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 485697.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
26 | 136/3 | DA+0 | DFR | 30.22 | 1.45 | Vikash Const. | Deepak Anand | RAJ | 2025-10-01 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-10 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 485697.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
27 | 126/1 | DA+9 (RC) | DFR | 34.29 | 1.802 | Vikash Const. | Deepak Anand | RAJ | 2025-10-04 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-16 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 564041.6 | 2025-10-05 | 1 |  |  |  |  | 1 | 564041.6 | 0 | 0 | 0 | 0 | 564041.6 | 0
28 | 153/0 | DB1+6 | DFR | 63.78 | 2.692 | Vikash Const. | Deepak Anand | RAJ | 2025-10-07 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-22 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 812044.6526 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 812044.6526
29 | 154/0 | DB2+9 | DFR | 76.69 | 3.466 | Sumit Const. | Deepak Anand | RAJ | 2025-10-07 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-22 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 922043.6526 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 922043.6526
30 | 156/2 | DA+3 | DFR | 34.29 | 1.802 | Sumit Const. | Deepak Anand | RAJ | 2025-10-10 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-28 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 564041.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 564041.6
|  |  |  | 1298.78 | 76.001 | [11 empty] | 20193024.0832 |  | 1 | 0 | 0 | 0 | 0 | 1 | 564041.6 | 0 | 0 | 0 | 0 | 564041.6 | 19628982.4832
Formulas:
End = [Work Plan]+2
End = [Stub-setting]+1
Stub-setting = [End]+1
Concreting = [End]+5
Concreting = [End, row above]+1
Earthing = [End]+1
Backfilling = [Earthing]+1
Work Plan = [End, row above]+1

## Erection-Oct25
Project Code |  |  | TA-505
Name of Line |  |  | 765KV D/C BEAWAR MANDSAUR (PKG-TL-02)
Activity |  |  | Erection | Qty
|  |  | Total | 371
|  |  | Completed (Till -Sept 25) | 127
|  |  | Balance | 244
Micro Plan for month |  |  | 2025-10-01 | 48 | Nos | 27566250.98 | Rs. Cr
Achievement for Month |  |  | Wk-1 | 4 | 8.333% | 2420223.38 | 8.78%
|  |  | Wk-2 | 1 | 2.083% | 395590.4 | 1.435%
|  |  | Wk-3 | 0 | 0% | 0 | 0%
|  |  | Wk-4 | 0 | 0% | 0 | 0%
|  |  | Wk-5 | 0 | 0% | 0 | 0%
|  |  | Total | 5 | 10.42% | 2815813.78 | 10.21%
SL | Location No. | Tower type | Tower Weight | Gang Name | Work Plan | [6 empty] | Revenue Planned | Actual Completion | Physical Completion | [5 empty] | Revenue Achievement | [5 empty] | Shortfall
[5 empty] | Material Feeding | Erection |  | Tack-welding | Final checking | SECTION | Section Incharge |  |  | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Revenue Realised
[6 empty] | Starting Date | Completion Date |  |  |  |  | Rs. Lacs. | Date | [11 empty] | Rs. Cr. | Rs. Cr.
1 | 110/0 | DC2+3 | 70.745 | Jwala Singh | 2025-10-01 | 2025-10-02 | 2025-10-08 | 2025-10-09 | 2025-10-11 | RAJ | Deepak Anand | 773950.3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 773950.3
2 | 126/1 | DA+9 | 45.697 | Jwala Singh | 2025-10-08 | 2025-10-09 | 2025-10-15 | 2025-10-16 | 2025-10-18 | RAJ | Deepak Anand | 499925.18 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499925.18
3 | 109/0 | DC1+0 | 62.444 | Jwala Singh | 2025-10-15 | 2025-10-16 | 2025-10-22 | 2025-10-23 | 2025-10-24 | RAJ | Deepak Anand | 683137.36 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 683137.36
4 | 101/0 | DC1+3 | 65.873 | Jwala Singh | 2025-10-22 | 2025-10-23 | 2025-10-29 | 2025-10-30 | 2025-10-31 | RAJ | Deepak Anand | 720650.62 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720650.62
5 | 116/0 | DD45+3 | 77.077 | New Gang-1 | 2025-10-01 | 2025-10-02 | 2025-10-10 | 2025-10-11 | 2025-10-13 | RAJ | Deepak Anand | 843222.38 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 843222.38
6 | 102/0 | DC2+3 | 70.745 | New Gang-1 | 2025-10-10 | 2025-10-11 | 2025-10-19 | 2025-10-20 | 2025-10-22 | RAJ | Deepak Anand | 773950.3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 773950.3
7 | 118/0 | DD60+6 | 97.168 | New Gang-1 | 2025-10-19 | 2025-10-20 | 2025-10-28 | 2025-10-29 | 2025-10-30 | RAJ | Deepak Anand | 1063017.92 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1063017.92
8 | 103/4 | DA+0 | 36.16 | New Gang-2 | 2025-10-01 | 2025-10-02 | 2025-10-10 | 2025-10-11 | 2025-10-13 | RAJ | Deepak Anand | 395590.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395590.4
9 | 114/4 | DA+3 | 37.931 | New Gang-2 | 2025-10-10 | 2025-10-11 | 2025-10-19 | 2025-10-20 | 2025-10-22 | RAJ | Deepak Anand | 414965.14 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414965.14
10 | 121/0 | DB1+6 | 65.028 | New Gang-2 | 2025-10-19 | 2025-10-20 | 2025-10-28 | 2025-10-29 | 2025-10-30 | RAJ | Deepak Anand | 711406.32 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 711406.32
11 | 126/3 | DA+3 | 37.931 | Shila Devi | 2025-10-01 | 2025-10-02 | 2025-10-07 | 2025-10-08 | 2025-10-10 | RAJ | Deepak Anand | 414965.14 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414965.14
12 | 141/0 | DD45+0 | 73.245 | Shila Devi | 2025-10-07 | 2025-10-08 | 2025-10-13 | 2025-10-14 | 2025-10-16 | RAJ | Deepak Anand | 801300.3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 801300.3
13 | 130/2 | DA-1.5 | 35.602 | Shila Devi | 2025-10-13 | 2025-10-14 | 2025-10-20 | 2025-10-21 | 2025-10-22 | RAJ | Deepak Anand | 389485.88 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 389485.88
14 | 128/0 | DC2+9 | 81.829 | Shila Devi | 2025-10-20 | 2025-10-21 | 2025-10-29 | 2025-10-30 | 2025-10-31 | RAJ | Deepak Anand | 895209.26 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 895209.26
15 | 129A/2 | DA+0 | 36.16 | Jyoti Enterprises | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09 | RAJ | Deepak Anand | 395590.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395590.4
16 | 132/0 | DD60+6 | 97.168 | Jyoti Enterprises | 2025-10-06 | 2025-10-07 | 2025-10-16 | 2025-10-17 | 2025-10-19 | RAJ | Deepak Anand | 1063017.92 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1063017.92
17 | 112/0 | DD60+18 | 124.95 | Jyoti Enterprises | 2025-10-16 | 2025-10-17 | 2025-10-29 | 2025-10-30 | 2025-10-31 | RAJ | Deepak Anand | 1366953 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1366953
18 | 115/0 | DD60+3 | 87.021 | Deglal Mahto | 2025-10-01 | 2025-10-02 | 2025-10-08 | 2025-10-09 | 2025-10-11 | RAJ | Deepak Anand | 952009.74 | 2025-10-04 | 1 |  |  |  |  | 1 | 952009.74 | 0 | 0 | 0 | 0 | 952009.74 | 0
19 | 114/0 | DC2+0 | 67.262 | Deglal Mahto | 2025-10-08 | 2025-10-09 | 2025-10-17 | 2025-10-18 | 2025-10-20 | RAJ | Deepak Anand | 735846.28 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 735846.28
20 | 136/2 | DA+3 | 37.931 | Deglal Mahto | 2025-10-17 | 2025-10-18 | 2025-10-23 | 2025-10-24 | 2025-10-25 | RAJ | Deepak Anand | 414965.14 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414965.14
21 | 136/5 | DA+3 | 37.931 | Deglal Mahto | 2025-10-23 | 2025-10-24 | 2025-10-29 | 2025-10-30 | 2025-10-31 | RAJ | Deepak Anand | 414965.14 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414965.14
22 | 156/0 | DC1+0 | 62.444 | Anil Kumar | 2025-10-01 | 2025-10-02 | 2025-10-12 | 2025-10-13 | 2025-10-15 | RAJ | Deepak Anand | 683137.36 | 2025-10-04 | 1 |  |  |  |  | 1 | 683137.36 | 0 | 0 | 0 | 0 | 683137.36 | 0
23 | 140/0 | DC1+9 | 75.279 | Anil Kumar | 2025-10-12 | 2025-10-13 | 2025-10-23 | 2025-10-24 | 2025-10-26 | RAJ | Bapan Mandal | 823552.26 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 823552.26
24 | 140/1 | DA+3 | 37.931 | Anil Kumar | 2025-10-23 | 2025-10-24 | 2025-10-29 | 2025-10-30 | 2025-10-31 | RAJ | Bapan Mandal | 414965.14 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414965.14
25 | 135/1 | DA+3 | 37.931 | Toshan Mahto | 2025-10-01 | 2025-10-02 | 2025-10-07 | 2025-10-08 | 2025-10-10 | RAJ | Bapan Mandal | 414965.14 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414965.14
26 | 135/3 | DA+9 | 45.697 | Toshan Mahto | 2025-10-07 | 2025-10-08 | 2025-10-13 | 2025-10-14 | 2025-10-16 | RAJ | Bapan Mandal | 499925.18 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499925.18
27 | 142/0 | DD45+3 | 77.077 | Toshan Mahto | 2025-10-13 | 2025-10-14 | 2025-10-19 | 2025-10-20 | 2025-10-21 | RAJ | Bapan Mandal | 843222.38 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 843222.38
28 | 148/1 | DA+0 | 36.16 | Toshan Mahto | 2025-10-19 | 2025-10-20 | 2025-10-25 | 2025-10-26 | 2025-10-27 | RAJ | Bapan Mandal | 395590.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395590.4
29 | 148A/0 | DB1+0 | 55.451 | Toshan Mahto | 2025-10-25 | 2025-10-26 | 2025-10-31 | 2025-11-01 | 2025-11-02 | RAJ | Bapan Mandal | 606633.94 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606633.94
30 | 158/2 | DA+0 | 36.16 | Parmanand (MP) | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09 | MP | Vinod Hankare | 395590.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395590.4
31 | 160/2 | DA-1.5 | 35.602 | Parmanand (MP) | 2025-10-06 | 2025-10-07 | 2025-10-15 | 2025-10-16 | 2025-10-18 | MP | Vinod Hankare | 389485.88 | 2025-10-07 | 1 |  |  |  |  | 1 | 389485.88 | 0 | 0 | 0 | 0 | 389485.88 | 0
32 | 159/3 | DA+0 | 36.16 | Parmanand (MP) | 2025-10-15 | 2025-10-16 | 2025-10-20 | 2025-10-21 | 2025-10-22 | MP | Vinod Hankare | 395590.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395590.4
33 | 160/1 | DA-1.5 | 35.602 | Parmanand (MP) | 2025-10-20 | 2025-10-21 | 2025-10-29 | 2025-10-30 | 2025-10-31 | MP | Vinod Hankare | 389485.88 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 389485.88
34 | 160/0 | DB1+0 | 55.451 | Jagannath Mahto | 2025-10-01 | 2025-10-02 | 2025-10-08 | 2025-10-09 | 2025-10-11 | MP | Vinod Hankare | 606633.94 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606633.94
35 | 161/0 | DB2+3 | 62.116 | Jagannath Mahto | 2025-10-08 | 2025-10-09 | 2025-10-15 | 2025-10-16 | 2025-10-18 | MP | Vinod Hankare | 679549.04 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 679549.04
36 | 161/1 | DA+3 | 37.931 | Jagannath Mahto | 2025-10-15 | 2025-10-16 | 2025-10-20 | 2025-10-21 | 2025-10-22 | MP | Vinod Hankare | 414965.14 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414965.14
37 | 164/2 | DA+0 | 36.16 | Jagannath Mahto | 2025-10-20 | 2025-10-21 | 2025-10-25 | 2025-10-26 | 2025-10-27 | MP | Vinod Hankare | 395590.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395590.4
38 | 164/3 | DA+3 | 37.931 | Jagannath Mahto | 2025-10-25 | 2025-10-26 | 2025-10-30 | 2025-10-31 | 2025-11-01 | MP | Vinod Hankare | 414965.14 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414965.14
39 | 167/4 | DA+0 | 36.16 | Pankaj Singh | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09 | MP | Vinod Hankare | 395590.4 | 2025-10-01 | 1 |  |  |  |  | 1 | 395590.4 | 0 | 0 | 0 | 0 | 395590.4 | 0
40 | 164/6 | DA+3 | 37.931 | Pankaj Singh | 2025-10-06 | 2025-10-07 | 2025-10-11 | 2025-10-12 | 2025-10-14 | MP | Vinod Hankare | 414965.14 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414965.14
41 | 164/7 | DA+3 | 37.931 | Pankaj Singh | 2025-10-11 | 2025-10-12 | 2025-10-16 | 2025-10-17 | 2025-10-18 | MP | Vinod Hankare | 414965.14 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414965.14
42 | 164/5 | DA+6 | 43.804 | Pankaj Singh | 2025-10-16 | 2025-10-17 | 2025-10-21 | 2025-10-22 | 2025-10-23 | MP | Vinod Hankare | 479215.76 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479215.76
43 | 167/3 | DA+0 | 36.16 | Pankaj Singh | 2025-10-21 | 2025-10-22 | 2025-10-26 | 2025-10-27 | 2025-10-28 | MP | Vinod Hankare | 395590.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395590.4
44 | 167/2 | DA+0 | 36.16 | Deglal Mahto (MP) | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09 | MP | Vinod Hankare | 395590.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395590.4
45 | 167/1 | DA+0 | 36.16 | Deglal Mahto (MP) | 2025-10-06 | 2025-10-07 | 2025-10-11 | 2025-10-12 | 2025-10-14 | MP | Vinod Hankare | 395590.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395590.4
46 | 169/2 | DA+0 | 36.16 | Deglal Mahto (MP) | 2025-10-11 | 2025-10-12 | 2025-10-16 | 2025-10-17 | 2025-10-18 | MP | Vinod Hankare | 395590.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395590.4
47 | 169/4 | DA+0 | 36.16 | Deglal Mahto (MP) | 2025-10-16 | 2025-10-17 | 2025-10-21 | 2025-10-22 | 2025-10-23 | MP | Vinod Hankare | 395590.4 | 2025-10-08 |  | 1 |  |  |  | 1 | 0 | 395590.4 | 0 | 0 | 0 | 395590.4 | 0
48 | 169/5 | DA+0 | 36.16 | Deglal Mahto (MP) | 2025-10-21 | 2025-10-22 | 2025-10-26 | 2025-10-27 | 2025-10-28 | MP | Vinod Hankare | 395590.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395590.4
|  |  | 2519.767 | [8 empty] | 27566250.98 |  | 4 | 1 | 0 | 0 | 0 | 5 | 2420223.38 | 395590.4 | 0 | 0 | 0 | 2815813.78 | 24750437.2
Formulas:
Erection = [Work Plan]+1
Erection = [Completion Date, row above]+1
Completion Date = [Erection]+6
Tack-welding = [Completion Date]+1
Final checking = [Tack-welding]+2
Work Plan = [Completion Date, row above]