## FDN-June25 (hidden)
Project Code |  |  | TA-416
Name of Line |  |  | NEEMRANA-II-BAREILLY (PG) 765KV D/C LINE,WZ-5 (Part-III)
Activity |  |  | Foundation | Qty
|  |  | Total | 302
|  |  | Completed (May-25) | 301
|  |  | Balance | 1
Micro Plan for month |  |  | 2025-06-01 | 1 | Nos | 4925228.89 | Rs. Cr.
Achievement for Month |  |  | Wk-1 | 1 | 100% | 4925228.89 | 100%
|  |  | Wk-2 | 0 | 0% | 0 | 0%
|  |  | Wk-3 | 0 | 0% | 0 | 0%
|  |  | Wk-4 | 0 | 0% | 0 | 0%
|  |  | Wk-5 | 0 | 0% | 0 | 0%
Actual for the Month |  |  | Total | 1 | 1 | 4925228.89 | 1
Sl | Loc No. | Tower type | Classification | Conc. Vol (CuM) | Reinf (MT) | Sub-Cont | Work Plan | [7 empty] | Revenue | Actual Completion | Physical Completion | [5 empty] | Revenue Achievement | [5 empty] | Shortfall
[7 empty] | Excavation |  | Stub-setting |  | Concreting |  | Earthing | Backfilling |  |  | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total
[7 empty] | Start | End | Start | End | Start | End |  |  | Rs. Lacs. | Date | [11 empty] | Rs. Lacs. | Rs. Lacs.
1 | 38/0 | DC2+18 | FS | 261.196 | 15.029 | AVI | 2025-05-21 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 4925228.89 | 2025-06-03 | 1 |  |  |  |  | 1 | 4925228.89 | 0 | 0 | 0 | 0 | 4925228.89 | 0
2 | [21 empty] | 0 |  |  |  |  | 0 | 0 | 0
3 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 261.196 | 15.029 | [9 empty] | 4925228.89 |  | 1 | 0 | 0 | 0 | 0 | 1 | 4925228.89 | 0 | 0 | 0 | 0 | 4925228.89 | 0
[13 empty] | STUB Setting-1 |  | 7224.33
[13 empty] | Earthing-1 |  | 7782.57
[13 empty] | Total Reve |  | 4940235.79

## Stub dispatch (hidden)
Location | Project | Tower type | Structure | B LOT | Actual PRS Date | STEEL Wt (MT) | BNA Wt | Disp Bal | May'24 Disp Plan | Wk01 | WK02 | WK03 | WK04 | Jun'24 Disp Plan MT | July'24 Disp Plan | Remark
JPR | TA416 | DA | Stub - 28 Nos | TA416-00018 | 2024-04-11 | 26.8617 | 0.46323 | 26.8617 | 0 |  |  |  | 0 | 26.8617 | 0 | As on date 160 stub reieved.
JPR | TA416 | DA | Stub - 132 Nos | TA416-00026 | 2024-04-15 | 126.634 | 2.184 | 126.634 | [5 empty] | 126.634 | 0
Total |  |  | 160 | [10 empty] | 153.4957

## Erection-Sep25
Sl | Location No. | Tower type | Tower Weight | Gang Name | Manpower | Section Incharge | Supervisor | Power Tools Issued (YES/NO) | Material Feeding | Starting Date | Completion Date | Tack-welding | Final checking | Revenue Planned | Revenue Realised
1 | 12/0 | DB+18 | 97.704 | Gagan Enterprise-1 | 30 | Prabin Patra | Bijendra |  | 2025-08-06 | 2025-08-06 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 861022 | 86102.2
2 | 29/0 | DD60+25 | 161.355 | Reeta Bharti | 32 | Prabin Patra | Rupesh | No | 2025-08-10 | 2025-08-10 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 1610385.43 | 322077.086
3 | 27/0 | DD60+3 | 101.69 | Reeta Bharti |  | Prabin Patra | Rupesh |  | 2025-09-11 | 2025-09-11 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 875860
4 | 25/0 | DD60+25 | 161.355 | Kongres-1 | 32 | Prabin Patra | Bijendra | No | 2025-08-30 | 2025-08-30 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 1610385.43
5 | 26/0 | DB+9 | 68.678 | Kongres-1 |  | Prabin Patra | Bijendra |  | 2025-09-22 | 2025-09-22 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 712728.77 | 142545.754
6 | 19/0 | DC+6 | 87.012 | Sainik Trader. | 25 | Prabin Patra | Rahman | No | 2025-09-01 | 2025-09-01 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 789838
7 | 37/0 | DC+18 | 110.696 | Sainik Trader. |  | D N Prasad | Rahman |  | 2025-09-14 | 2025-09-14 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 1004656
8 | 11/0 | DB+18 | 97.704 | Gourishankar | 45 | Prabin Patra | Sitaram | No | 2025-08-24 | 2025-08-24 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 861022
9 | 22A/0 | DB+25 | 110.575 | Gourishankar |  | Prabin Patra | Sitaram |  | 2025-09-15 | 2025-09-15 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 974538 | 194907.6
10 | 23/0 | DC+18 | 110.696 | Mohika Con | 34 | D N Prasad | Bijendra | No | 2025-08-30 | 2025-08-30 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 1492772
11 | 46/0 | DB+0 | 64.482 | Mohika Con |  | D N Prasad | Bijendra |  | 2025-09-22 | 2025-09-22 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 568304
12 | 2/0 | DD45+3 | 89.713 | Radha Construction | 33 | Prabin Patra | Churamani | No | 2025-09-01 | 2025-09-01 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 827835
13 | 2/2 | DA+0 | 43.776 | Radha Construction |  | Prabin Patra | Churamani |  | 2025-09-17 | 2025-09-17 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 371402
14 | 43/0 | DD60+9 | 118.43 | Ananya Trader | 34 | D N Prasad | J S Jha |  | 2025-08-16 | 2025-08-16 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 1062230
15 | 47/0 | DC+9 | 90.125 | Ananya Trader |  | D N Prasad | J S Jha | No | 2025-09-06 | 2025-09-06 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 828626 | 165725.2
16 | 54/1 | DA+9 | 55.339 | Punam Kumari | 33 | D N Prasad | Madhusudan | No | 2025-08-18 | 2025-08-18 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 470947
17 | 52/0 | DC+9 | 90.125 | Punam Kumari |  | D N Prasad | Madhusudan |  | 2025-09-05 | 2025-09-05 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 828626
18 | 16/0 | DB+25 | 110.575 | Amit Choudhury | 40 | Prabin Patra | Rahman | No | 2025-08-18 | 2025-08-18 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 974538
19 | 17/0 | DB+6 | 75.897 | Amit Choudhury |  | Prabin Patra | Rahman |  | 2025-09-14 | 2025-09-15 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 669569.35 | 133913.87
20 | 17/6 | DA-3 | 42.374 | Amit Choudhury |  | Prabin Patra | Rahman |  | 2025-09-22 | 2025-09-22 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 359483
21 | 64/0 | DC+0 | 73.43 | Kongres-2 | 30 | D N Prasad | Ritlal | No | 2025-09-01 | 2025-09-01 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 666437
22 | 69A/0 | DD60+0 | 97.229 | Kongres-2 |  | D N Prasad | Ritlal |  | 2025-09-13 | 2025-09-13 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 837742 | 167548.4
23 | 48/1 | DA-3 | 42.374 | MK Infra | 16 | D N Prasad | Somenath | No | 2025-08-30 | 2025-08-30 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 359483
24 | 49/0 | DC+9 | 90.125 | MK Infra |  | D N Prasad | Somenath |  | 2025-09-11 | 2025-09-11 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 828626
25 | 52/7 | DA+6 | 53.324 | Spotify-1 | 20 | D N Prasad | Ritlal | No | 2025-08-30 | 2025-08-30 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 450628
26 | 53/0 | DC+0 | 73.426 | Spotify-1 |  | D N Prasad | Ritlal |  | 2025-09-15 | 2025-09-15 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 666437
27 | 53A/1 | DA+6 | 53.324 | Spotify-2 | 20 | D N Prasad | Aflaudin | No | 2025-08-30 | 2025-08-30 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 450628 | 90125.6
28 | 55/0 | DC+0 | 73.426 | Spotify-2 |  | D N Prasad | Aflaudin |  | 2025-09-15 | 2025-09-15 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 666437
29 | 56/8 | DA-3 | 42.374 | Spotify-3 | 24 | D N Prasad | Akhtarul | No | 2025-08-30 | 2025-08-30 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 359483
30 | 56/7 | DA+6 | 53.324 | Spotify-3 |  | D N Prasad | Aflaudin |  | 2025-09-15 | 2025-09-15 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 450628
|  |  | 2540.657 | [10 empty] | 23491296.98

## STG-Sep25 (hidden)
Project Code
Name of Line
Activity |  |  | Stringing | Qty |  |  |  |  | Rate @Kms | 905812
|  |  | Total | 115
|  |  | Completed (Aug-25) | 32.6
|  |  | Balance | 82.4
Micro Plan for month |  |  | 2025-09-01 | 23.985 | km | 21725900.82 | Rs. Cr
Achievement for Month |  |  | Wk-1 | 0 | 0% | 0 | 0%
|  |  | Wk-2 | 0 | 0% | 0 | 0%
|  |  | Wk-3 | 0 | 0% | 0 | 0%
|  |  | Wk-4 | 0 | 0% | 0 | 0%
|  |  | Wk-5 | 0 | 0% | 0 | 0%
|  |  | Total | 0 | 0% | 0 | 0%
Sl | Section | Section Length (km) | Manual/TSE | Sub-Cont | Work Plan |  |  |  |  | Revenue | Actual Completion | Physical Completion | [5 empty] | Revenue Achievement | [5 empty] | Shortfall
[5 empty] | Matl feeding | Pay-Out |  | Final Sag |  |  |  | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total
[6 empty] | Start | End | Start | End | Rs. Cr. | Date | [11 empty] | Rs. Cr. | Rs. Cr.
1 | 14/0-15/0 | 3.611 | TSE | Anarul | 2025-08-30 | 2025-09-01 | 2025-09-08 | 2025-09-09 | 2025-09-12 | 3270887.132 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3270887.132
2 | 12/0-13/0 | 3.92 | TSE |  | 2025-09-13 | 2025-09-14 | 2025-09-19 | 2025-09-20 | 2025-09-22 | 3550783.04 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3550783.04
3 | 3/0-4/0 | 0.28 | Manual-1 |  | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-12 | 2025-09-12 | 253627.36 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253627.36
4 | 11/0-12/0 | 0.313 | Manual-1 |  | 2025-09-27 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 283519.156 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283519.156
5 | 13/0-14/0 | 0.319 | Manual-1 |  | 2025-09-15 | 2025-09-16 | 2025-09-16 | 2025-09-16 | 2025-09-16 | 288954.028 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288954.028
6 | 20/0-21/0 | 4.958 | TSE | Pankaj | 2025-09-03 | 2025-09-04 | 2025-09-09 | 2025-09-10 | 2025-09-13 | 4491015.896 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4491015.896
7 | 21/0-22/0 | 1.606 | TSE |  | 2025-09-14 | 2025-09-15 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 1454734.072 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1454734.072
8 | 18/0-19/0 | 0.323 | Manual-1 |  | 2025-09-20 | 2025-09-21 | 2025-09-26 | 2025-09-27 | 2025-09-30 | 292577.276 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292577.276
9 | 36/0-37/0 | 4.947 | TSE |  | 2025-08-30 | 2025-08-31 | 2025-09-06 | 2025-09-07 | 2025-09-10 | 4481051.964 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4481051.964
10 | 30/0-31/0 | 2.75 | TSE |  | 2025-09-11 | 2025-09-12 | 2025-09-17 | 2025-09-18 | 2025-09-21 | 2490983 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2490983
11 | 29/0-30/0 | 0.27 | TSE |  | 2025-09-20 | 2025-09-20 | 2025-09-20 | 2025-09-22 | 2025-09-22 | 244569.24 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244569.24
12 | 28/0-29/0 | 0.688 | Manual-2 |  | 2025-09-27 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 623198.656 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 623198.656
13 | [9 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 23.985 | [7 empty] | 21725900.82 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21725900.82