## 765kV Summery
|  | TB-507 | DAILY PROGRESS REPORT | [8 empty] | 2026-03-20 10:53
CONTRACTUAL START DATE: |  | 2024-12-06 | FATEGARH III-BEAWAR 765KV D/C TRANSMISSION LILO LINE
CONTRACTUAL FINISH DATE: |  | 2026-06-05
REPORTING DATE |  |  | Client Name : RAJASTHAN IV A POWER TRANSMISSION LTD
TOTAL DAYS |  |  | NOA Ref No(Supply): RIVA/LOA-KEC(SUP)/AUG 24/405
COMP. DAYS |  |  | NOA Ref No(Service): RIVA/LOA-KEC(SER)/AUG 24/406
Progress Summary | [11 empty] | 2026-03-20 10:53
Sl No. | Activity | LOA Quantity | Estimated Line Quantity | Cumm. Progress till Last Month | Plan For MAR'25 | Progress in MAR'25 | WIP | Today's Progress | Cumulative progress till date | Balance | Gangs working Mar-26 | Remarks
A.i | Route Alignment (Kms) | 15.478 | 15.478 | [5 empty] | 15.478 | 0 |  | In the Scope of Rajasthan IV A Power Transmission Ltd
ii | Detailed Survey (Kms) | 15.478 | 15.478 | 15.478 |  | 0 |  |  | 15.478 | 0
iii | Check Survey (Kms) | 15.478 | 15.478 | 15.478 | 15.478 |  |  |  | 15.478 | 0
B. | Soil Investigation (Nos) | 26 | 26 | 26 |  |  |  |  | 26 | 0
C. | Foundation (Nos) | 43 | 43 | 7 | 0 | 5 | 3 | 0 | 12 | 31 | 2
D. | Earthing (Nos) | 43 | 43 | 3 | 0 | 0 |  | 0 | 3 | 40
E. | Tower Erection (Nos) | 43 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 43
F. | Tack Welding (Nos) | 43 | 43 | [5 empty] | 0 | 43
G. | Stringing (Kms) | [8 empty] | 0
i | Paying Out (Kms) | 15.478 | 15.478 | 0 |  |  |  |  | 0 | 15.478
ii | Final Sag (Kms) | 15.478 | 15.478 | 0 |  |  |  |  | 0 | 15.478
I. | OPGW Stringing (Kms) | 15.478 | 15.478 | 0 |  |  |  |  | 0 | 15.478
0

## Check Survey
Sr. no | Section AP To AP | Section length | Check Survey | Details Survey | Remarks
1 | S/S Gantry To AP-7/0 | 10.369 | YES | YES | Details Survey Completed. Profile & Tower Schedule Submitted with Apraava Engg.
2 | AP-7/0 To AP-10/0 | 8.713 | YES |  | Approved
3 | AP-10/0 To AP-21/0 | 19.57 | YES |  | Approved
4 | AP-21/0 To AP-24/0 | 2.618 | YES |  | Approved
5 | AP-24/0 To AP-27/0 | 1.44 | YES |  | Check Survey Completed. Profile & Tower Schedule Submitted with Apraava Engg.
6 | AP-27/0 To AP-40/0 | 16.759 | YES |  | Approved
7 | AP-40/0 To AP-45/0 | 6.672 | YES |  | Approved
8 | AP-45/0 To AP-48/0 | 3.172 | YES | YES | Details Survey Completed. Profile & Tower Schedule Submitted with Apraava Engg.
9 | AP 48/0 to AP 51/0, | 1.05 | Yes |  | Approved
10 | AP-51/0 To AP-60/0 | 7.962 | Yes |  | Approved
11 | AP-60/0 To AP-75/0 | 19.567 | Yes |  | Approved
12 | AP-75/0 To AP-92/0 | 20.273 | Yes |  | Approved
13 | AP-92/0 To AP-96/0 | 3.084 | Yes |  | Approved
14 | AP-96/0 To AP-107/0 | 14.119 | Yes |  | Approved
15 | AP-107/0 To AP-121/0 | 9.495 | Yes |  | Approved
16 | AP-121/0 To AP-131/0 | 8.697 | Yes |  | Approved
17 | AP-131/0 To AP-139/0 | 12.65 | Yes |  | Approved
18 | AP-139/0 To AP-148/0 | 14.392 | Yes |  | Approved
19 | AP-148/0 To AP-153/0 | 6.321 | Yes |  | Approved
20 | AP-153/0 To S/S Gantry | 1.521 | Yes |  | Check Survey Completed. Profile & Tower Schedule Submitted with Apraava Engg.
| TOTAL | 188.444

## Check Survey Status (hidden)
NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE
Client : RAJASTHAN IV A POWER TRANSMISSION LTD.
CONTRACTOR : KEC INTERNATIONAL LIMITED
400 KV CHECK SURVEY
SL No | Section | Section Length | Submission Date | Approval Date | Remarks
1 | AP 51- AP 54 | 2.653 | 2025-01-27 | 2025-02-03 | Approved
2 | AP 54- AP 60 | 5.31 |  |  | Approved
3 | AP 60- AP 75 | 19.672 | 15.02.2025 , 24-02-2025 25-02-2025 | 2025-02-25 | Approved | Required Change
4 | AP 75- AP 92 | 20.273 | 2024-12-31 | 2025-02-03 | Approved
5 | AP 92- AP 96 | 3.084 | 15-02-25 & 21-02-2025 | 2025-02-24 | Approved
6 | AP 96- AP 97 | 1.063 | 2025-02-25 | 2025-02-27 | Approved
7 | AP 97- AP 98B | 2.09 | 2025-02-25 |  | Approved
8 | AP 98B- 99A/0 | 3.893 | 2025-02-25 |  | Approved
9 | AP99A/0-AP 107 | 6.971 | 2025-02-25 |  | Approved
10 | AP 107- AP 121 | 9.495 | 2025-03-05 | 2025-03-06 | Approved
11 | AP 121- AP 131 | 8.697 | 12-03-2025 & ReSubmission 4-04-2025 |  | Submitted | Resubmitted
12 | AP 131- AP 133 | 3.084 |  |  | Submitted
13 | AP 133- AP 134 | 3.963 |  |  | Submitted
14 | AP 134- AP 135 | 1.656 |  |  | Submitted
15 | AP 135- AP 136 | 1.635 |  |  | Submitted
16 | AP 136 - AP 139 | 2.221 |  |  | Submitted
17 | AP 139 - AP 147 | 10.724 | 26-03-2025 Resubmission 4-04-2025 &28-04-25 |  | Submitted | Resubmitted
18 | AP 147/0 - AP 148 | 3.666 | 26-03-2025 Resubmission 4-04-2025 & 28-04-25 |  | Submitted | Resubmitted
19 | AP148/0 - AP 149B | 4.88 |  |  | Submitted
20 | AP 150 to Bhinmal GTY | 2.474 | 2025-04-18 |  | Submitted
21 | AP 50- AP 51 | 0.275 | 2025-04-05 |  | Submitted
22 | AP 47- AP 50 | 2.008 | 2025-04-05 |  | Submitted
23 | AP 46- AP 47 | 0.223 | 2025-04-05 |  | Submitted
24 | AP 42- AP 43 | 2.731 | 2025-04-05 |  | Submitted
25 | AP 45- AP 46 | 1.717 | 2025-04-05 |  | Submitted
26 | AP 43- AP 45 | 1.068 | 2025-04-05 |  | Submitted
27 | AP 40- AP 42 | 2.873 | 2025-04-05 |  | Submitted
28 | AP 10- AP 21 | 19.57 | 16-04-2025 & 16.05.2025 |  | Re Submitted
29 | 21/0-24/0 | 2.618 | 2025-05-04 |  | Complete
30 | 24/0-40/0 | 18.193 | 2025-05-28 |  | Complete
| AS on date | 168.78
Submission of Check Survey
SL. No. | Section | Date of submission | Section Length in kms | Letter Reference Number | Date of Approval | Section Length in kms
1 | AP75 To AP92 | 2024-12-31 | 20.273 | KEC/FBTL/RPTL/TB507/008A | 2025-02-03 | 20.273
2 | AP51 To AP60 | 2025-01-27 | 7.962 | KEC/FBTL/RPTL/TB507/0014 | 2025-02-03 | 7.962
3 | AP92 To AP96 | 2025-02-21 | 3.084 | KEC/FBTL/RPTL/TB507/0025 & 0029 | 2025-02-24 | 3.084
4 | AP60 To AP75 | 2025-02-15 | 19.672 | KEC/FBTL/RPTL/TB507/0025 , 0030 & 0033 | 2025-02-25 | 19.672
5 | AP96 To AP107 | 2025-02-25 | 14.017 | KEC/FBTL/RPTL/TB507/0032 | 2025-02-27 | 14.017
6 | AP107 To AP121 | 2025-03-05 | 9.495 | KEC/FBTL/RPTL/TB507/0036 | 2025-03-06 | 9.495
7 | AP121 To AP131 | 2025-04-04 | 8.697 | KEC/FBTL/RPTL/TB507/0043 ,0050,0061 | 2025-03-16 | 8.697
8 | AP139 To AP148 | 2025-03-26 | 14.39 | KEC/FBTL/RPTL/TB507/0049 | 2025-03-16 | 14.39
9 | AP40 To AP51 | 2025-04-05 | 10.894 | KEC/FBTL/RPTL/TB507/0064
10 | AP10 To AP21 | 06-04-2025 & 16.05.2025 | 19.57 | KEC/FBTL/RPTL/TB507/79
11 | AP150 To Bhinmal GTY | 2025-04-18 | 2.474 | KEC/FBTL/RPTL/TB507/0068
12 | AP131-AP 133 | 2025-05-10 | 3.084 | KEC/FBTL/RPTL/TB507/0077
13 | AP136-AP 139 | 2025-05-10 | 2.22 | KEC/FBTL/RPTL/TB507/0077
14 | AP 133-AP 135 | 2025-05-25 | 5.619 | Resubmitted on dated 25/05/2025
15 | AP 99-AP 100 | 2025-05-17 | 3.95 | KEC/FBTL/RPTL/TB507/82 | 2025-06-02
16 | AP 135-AP 136 | 2025-05-25 | 1.635 | KEC/FBTL/RPTL/TB507/0077 on 10/05/25
17 | AP 148-AP 149B | 2025-05-25 | 4.88
Total |  |  | 151.916 |  |  | 97.59
Check Survey
Sr. no | Action by | Section AP To AP | Section length | Approved by Client | Pending by Client | Remarks
1 | KEC | S/S Gantry To AP-7/0 | 10.373 |  |  | Details Survey Completed. Profile Preperation in process with KEC Engg.
2 | KEC | AP-7/0 To AP-10/0 | 8.719 |  |  | Submitted on 3.07.2025,
3 |  | AP-10/0 To AP-21/0 | 19.57 | YES |  | Approved
4 | Apraava | AP-21/0 To AP-24/0 | 2.618 |  | YES | Hard Copy Submitted on 24-06-2025
5 | KEC | AP-24/0 To AP-40/0 | 18.193 |  |  | Submited on 30.06.2025
6 |  | AP-40/0 To AP-45/0 | 6.659 | Yes |  | Approved on 18-06-2025
7 | KEC | AP-45/0 To AP-48/0 | 3.17 |  |  | Profile Preperation in process with KEC Engg.
8 |  | AP 48/0 to AP 51/0, | 1.05 | Yes |  | Approved on 18-06-2025
9 |  | AP-51/0 To AP-60/0 | 7.962 | Yes |  | Approved
10 |  | AP-60/0 To AP-75/0 | 19.567 | Yes |  | Approved
11 |  | AP-75/0 To AP-92/0 | 20.273 | Yes |  | Approved
12 |  | AP-92/0 To AP-96/0 | 3.084 | Yes |  | Approved
13 |  | AP-96/0 To AP-107/0 | 14.119 | Yes |  | Approved
14 |  | AP-107/0 To AP-121/0 | 9.495 | Yes |  | Approved
15 |  | AP-121/0 To AP-131/0 | 8.694 | Yes |  | Approved
16 | KEC | AP-131/0 To AP-139/0 | 12.559 | Yes |  | Approved
17 | KEC | AP-139/0 To AP-148/0 | 14.391 | Yes |  | Approved
18 | KEC | AP-148/0 To AP-153/0 | 6.321 | Yes |  | Approved
19 | Apraava | AP-153/0 To AP-154/0 | 0.389 |  | Yes
20 | KEC | AP-154/0 To AP-155/0 | 0.22 |  |  | Underneath crossing proposal under process with KEC Engg.
21 | Apraava | AP-155/0 To S/S Gantry | 0.57 |  | Yes | Submitted on 16.04.2025,
|  | TOTAL | 187.996
|  |  |  | 2.618 | AP 21 to AP 24
TOTAL |  |  |  | 187.996
Check Survey Submitted |  |  |  | 156.04
Check Survey Approved |  |  |  | 152.463
Balance for Approval by Client |  |  |  | 3.577
Check Survey report to be Submitted |  |  |  | 31.956
Check Survey
| Sr.no | Section AP To AP | Section length | Approved | Resposnibility | Remarks
| 1 | AP-1/0 To AP-10/0 | 18.116 |  | M/s Kec | Rerouting confirmation given on 12.06.2025 to carry out detail survey, When will be the survey started
| 2 | AP-10/0 To AP-21/0 | 19.57 |  | M/s Apraava | Will be approved by 17.06.2025
| 3 | AP-21/0 To AP-40/0 | 20.811 |  | M/s Kec | From AP 21 to AP 24 and AP 27 to AP 40 has to be submitted. From AP 24 to AP 27 Underneath data has also to be submitted. When it will be submitted
| 4 | AP-40/0 To AP 45 and AP 48 to AP 51/0 | 10.894 |  | M/s Apraava | From AP 40 to AP 45, AP 48 to AP 51 will be approved by 17.06.2025
|  | AP 45 to AP 48 |  |  | M/s Kec | Railway crossing detail survey profile, Tower Schedule yet not provided, When will we get this.
| 5 | AP-51/0 To AP-60/0 | 7.962 | 2025-02-03
| 6 | AP-60/0 To AP-75/0 | 19.567 | 2025-02-25
| 7 | AP-75/0 To AP-92/0 | 20.273 | 2025-02-03
| 8 | AP-92/0 To AP-96/0 | 3.084 | 2025-02-24
| 9 | AP-96/0 To AP-107/0 | 14.017 | 2025-02-27
| 10 | AP-107/0 To AP-121/0 | 9.495 | 2025-03-06
| 11 | AP-121/0 To AP-131/0 | 8.694 | 2025-04-16
| 12 | AP-131/0 To AP-133/0 | 3.084 |  | M/s Kec | Yet not submitted
| 13 | AP-133/0 To AP-135/0 | 5.619 |  | M/s Kec | Yet not submitted
| 14 | AP-135/0 To AP-139/0 | 3.856 |  | M/s Kec | Yet not submitted
| 15 | AP-139/0 To AP-148/0 | 14.391 | 2025-04-16
| 16 | AP-148/0 To AP-150/0 | 5.268 |  | M/s Apraava | Will be approved by 17.06.2025
| 17 | AP-150/0 To AP-157/0 | 2.474 | 2025-04-18 | M/s Apraava & M/s Kec | Under discussion due to Underneath crossing at 154/0 to 155/0 and railway proposal crossing 150/0 to 151/0.
|  | Total | 187.175

## Check Survey (hidden)
NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE
Client : RAJASTHAN IV A POWER TRANSMISSION LTD.
CONTRACTOR : KEC INTERNATIONAL LIMITED
400 KV CHECK SURVEY
SL No | Section | Section Length | Submission Date | Approval Date | Remarks
1 | AP 51- AP 54 | 2.653 | 2025-01-27 | 2025-02-03 | Approved
2 | AP 54- AP 60 | 5.31 |  |  | Approved
3 | AP 60- AP 75 | 19.672 | 15.02.2025 , 24-02-2025 25-02-2025 | 2025-02-25 | Approved | Required Change | Approved | 97.59
4 | AP 75- AP 92 | 20.273 | 2024-12-31 | 2025-02-03 | Approved
5 | AP 92- AP 96 | 3.084 | 15-02-25 & 21-02-2025 | 2025-02-24 | Approved |  | Submitted | 151.916
6 | AP 96- AP 97 | 1.063 | 2025-02-25 | 2025-02-27 | Approved
7 | AP 97- AP 98B | 2.09 | 2025-02-25 |  | Approved
8 | AP 98B- 99A/0 | 3.893 | 2025-02-25 |  | Approved
9 | AP99A/0-AP 107 | 6.971 | 2025-02-25 |  | Approved
10 | AP 107- AP 121 | 9.495 | 2025-03-05 | 2025-03-06 | Approved
11 | AP 121- AP 131 | 8.697 | 12-03-2025 & ReSubmission 4-04-2025 |  | Submitted | Resubmitted
12 | AP 131- AP 133 | 3.084 |  |  | Submitted
13 | AP 133- AP 134 | 3.963 |  |  | Submitted
14 | AP 134- AP 135 | 1.656 |  |  | Submitted
15 | AP 135- AP 136 | 1.635 |  |  | Submitted
16 | AP 136 - AP 139 | 2.221 |  |  | Submitted
17 | AP 139 - AP 147 | 10.724 | 26-03-2025 Resubmission 4-04-2025 &28-04-25 |  | Submitted | Resubmitted
18 | AP 147/0 - AP 148 | 3.666 | 26-03-2025 Resubmission 4-04-2025 & 28-04-25 |  | Submitted | Resubmitted |  |  | Blance | 187.176
19 | AP148/0 - AP 149B | 4.88 |  |  | Submitted
20 | AP 150 to Bhinmal GTY | 2.474 | 2025-04-18 |  | Submitted
21 | AP 50- AP 51 | 0.275 | 2025-04-05 |  | Submitted
22 | AP 47- AP 50 | 2.008 | 2025-04-05 |  | Submitted
23 | AP 46- AP 47 | 0.223 | 2025-04-05 |  | Submitted
24 | AP 42- AP 43 | 2.731 | 2025-04-05 |  | Submitted
25 | AP 45- AP 46 | 1.717 | 2025-04-05 |  | Submitted
26 | AP 43- AP 45 | 1.068 | 2025-04-05 |  | Submitted
27 | AP 40- AP 42 | 2.873 | 2025-04-05 |  | Submitted
28 | AP 10- AP 21 | 19.57 | 16-04-2025 & 16.05.2025 |  | Re Submitted
29 | 21/0-24/0 | 2.618 | 2025-05-04 |  | Complete
30 | 24/0-40/0 | 18.193 | 2025-05-28 |  | Complete |  |  | 25.321
| AS on date | 168.78
Submission of Check Survey
SL. No. | Section | Date of submission | Section Length in kms | Letter Reference Number | Date of Approval | Section Length in kms | Approved By | Remarks
1 | AP75 To AP92 | 2024-12-31 | 20.273 | KEC/FBTL/RPTL/TB507/008A | 2025-02-03 | 20.273 | Gundewadi Mallappa
2 | AP51 To AP60 | 2025-01-27 | 7.962 | KEC/FBTL/RPTL/TB507/0014 | 2025-02-03 | 7.962 | Gundewadi Mallappa
3 | AP92 To AP96 | 2025-02-21 | 3.084 | KEC/FBTL/RPTL/TB507/0025 & 0029 | 2025-02-24 | 3.084 | Gundewadi Mallappa | Resubmission on dated 21/02/2025
4 | AP60 To AP75 | 2025-02-15 | 19.672 | KEC/FBTL/RPTL/TB507/0025 , 0030 & 0033 | 2025-02-25 | 19.672 | Gundewadi Mallappa | Resubmission on dated 24/02/2025 & 25/02/2025
5 | AP96 To AP107 | 2025-02-25 | 14.017 | KEC/FBTL/RPTL/TB507/0032 | 2025-02-27 | 14.017 | Gundewadi Mallappa
6 | AP107 To AP121 | 2025-03-05 | 9.495 | KEC/FBTL/RPTL/TB507/0036 | 2025-03-06 | 9.495 | Gundewadi Mallappa
7 | AP121 To AP131 | 2025-04-04 | 8.697 | KEC/FBTL/RPTL/TB507/0043 ,0050,0061 | 2025-03-16 | 8.697 | Gundewadi Mallappa | Resubmission on dated 04/04/2025
8 | AP139 To AP148 | 2025-03-26 | 14.39 | KEC/FBTL/RPTL/TB507/0049 | 2025-03-16 | 14.39 | Gundewadi Mallappa | Resubmission on dated 04/04/2025
9 | AP40 To AP51 | 2025-04-05 | 10.894 | KEC/FBTL/RPTL/TB507/0064
10 | AP10 To AP21 | 06-04-2025 & 16.05.2025 | 19.57 | KEC/FBTL/RPTL/TB507/79 |  |  |  | Resubmission on dated 16/05/2025
11 | AP150 To Bhinmal GTY | 2025-04-18 | 2.474 | KEC/FBTL/RPTL/TB507/0068
12 | AP131-AP 133 | 2025-05-10 | 3.084 | KEC/FBTL/RPTL/TB507/0077 |  |  |  | Resubmission on dated 10/05/2025
13 | AP136-AP 139 | 2025-05-10 | 2.22 | KEC/FBTL/RPTL/TB507/0077 |  |  |  | Resubmission on dated 10/05/2025
14 | AP 133-AP 135 | 2025-05-25 | 5.619 | Resubmitted on dated 25/05/2025 |  |  |  | Resubmission on dated 25/05/2025
15 | AP 99-AP 100 | 2025-05-17 | 3.95 | KEC/FBTL/RPTL/TB507/82 | 2025-06-02 |  |  | Resubmission on dated 16/05/2025
16 | AP 135-AP 136 | 2025-05-25 | 1.635 | KEC/FBTL/RPTL/TB507/0077 on 10/05/25 |  |  |  | Resubmission on dated 25/05/2025
17 | AP 148-AP 149B | 2025-05-25 | 4.88 |  |  |  |  | Resubmission on dated 25/05/2025
Resubmission on dated 25/05/2025
Total |  |  | 151.916 |  |  | 97.59
Check Survey
Action by | Sr.no | Section AP To AP | Section length | Approved by Client | Pending by Client | Remarks | Apraava Comments
Apraava | 1 | AP-1/0 To AP-7/0 | 9.4 |  |  | Details Survey Completed | Discussion and coordination with Statcraft are ongoing. Awaiting their response
| 2 | AP-7/0 To AP-10/0 | 9.096 |  |  | Check Survry Completed
KEC | 3 | AP-10/0 To AP-21/0 | 19.57 |  | YES | Approved | KEC was to submit a proposal avoiding the shifting of the 11 kV line; their response is still awaited. The rest of the profile is acceptable—awaiting a hard-signed copy along with revised tower schdule from the KEC team for official release
| 4 | AP-21/0 To AP-24/0 | 2.618 |  |  | Hard Copy Submitted on 24-06-2025
KEC | 5 | AP-24/0 To AP-40/0 | 18.193 |  | 2025-05-07 | AP 27 to AP 40(16.753Km) CS completed and Profile Under Process in KEC Engg, GTY position finalization at AP 24 to AP 27(1.440 KM) | Check Survey for two oil/gas pipeline crossings is awaited, and the re-survey for the 400kV line crossing between AP25 to AP26 (underneath crossing) is pending from KEC.
KEC | 6 | AP-40/0 To AP-45/0 | 6.659 |  |  | Approved on 18-06-2025
KEC | 7 | AP-45/0 To AP-48/0 | 3.17 |  |  | Hold due to Railway crossing angle 870 to 900 | Re-survey for the railway crossing between AP46 and AP47, due to alignment change from 86° to 90°, is pending from KEC.
KEC | 8 | AP 48/0 to AP 51/0, | 1.05 |  | 2025-04-05 | Approved on 18-06-2025
KEC | 9 | AP-51/0 To AP-60/0 | 7.962 | 2025-02-03 |  | Approved | Tower schedule has been approved; however, the profile as per the approved check survey is still awaited from KEC
| 10 | AP-60/0 To AP-75/0 | 19.567 | 2025-02-25 |  | Approved
| 11 | AP-75/0 To AP-92/0 | 20.273 | 2025-02-03 |  | Approved
| 12 | AP-92/0 To AP-96/0 | 3.084 | 2025-02-24 |  | Approved
| 13 | AP-96/0 To AP-107/0 | 14.119 | 2025-02-27 |  | Approved
| 14 | AP-107/0 To AP-121/0 | 9.495 | 2025-03-06 |  | Approved
| 15 | AP-121/0 To AP-131/0 | 8.694 | 2025-04-16 |  | Approved
KEC | 16 | AP-131/0 To AP-139/0 | 12.559 |  | YES | Approved | Location of AP132 has been changed due to the presence of a house within the corridor; revised check survey and profile are awaited from KEC."
KEC | 17 | AP-139/0 To AP-148/0 | 14.391 | 2025-04-16 |  | Approved | Tower schedule has been approved; however, the profile as per the approved check survey is still awaited from KEC
KEC | 18 | AP-148/0 To AP-150/0 | 5.268 |  | 2025-05-23 | Approved | Hard signed profile & Tower schudle copies are awaited from KEC to offical realse.
KEC | 19 | AP-150/0 To AP-157/0 | 2.474 | 2025-04-18 |  | Approval pending from Engg Team | Re-survey for the 400kV line crossing between AP154 to AP155 (underneath crossing) is pending from KEC.
187.642
|  |  | CS Submitted | 166.062
|  |  |  | 2.618 | AP 21 to AP 24
|  |  | TOTAL | 187.642
|  |  | Approved | 145.165
|  |  | Balance | 42.477
Check Survey
| Sr.no | Section AP To AP | Section length | Approved | Resposnibility | Remarks
| 1 | AP-1/0 To AP-10/0 | 18.116 |  | M/s Kec | Rerouting confirmation given on 12.06.2025 to carry out detail survey, When will be the survey started
| 2 | AP-10/0 To AP-21/0 | 19.57 |  | M/s Apraava | Will be approved by 17.06.2025
| 3 | AP-21/0 To AP-40/0 | 20.811 |  | M/s Kec | From AP 21 to AP 24 and AP 27 to AP 40 has to be submitted. From AP 24 to AP 27 Underneath data has also to be submitted. When it will be submitted
| 4 | AP-40/0 To AP 45 and AP 48 to AP 51/0 | 10.894 |  | M/s Apraava | From AP 40 to AP 45, AP 48 to AP 51 will be approved by 17.06.2025
|  | AP 45 to AP 48 |  |  | M/s Kec | Railway crossing detail survey profile, Tower Schedule yet not provided, When will we get this.
| 5 | AP-51/0 To AP-60/0 | 7.962 | 2025-02-03
| 6 | AP-60/0 To AP-75/0 | 19.567 | 2025-02-25
| 7 | AP-75/0 To AP-92/0 | 20.273 | 2025-02-03
| 8 | AP-92/0 To AP-96/0 | 3.084 | 2025-02-24
| 9 | AP-96/0 To AP-107/0 | 14.017 | 2025-02-27
| 10 | AP-107/0 To AP-121/0 | 9.495 | 2025-03-06
| 11 | AP-121/0 To AP-131/0 | 8.694 | 2025-04-16
| 12 | AP-131/0 To AP-133/0 | 3.084 |  | M/s Kec | Yet not submitted
| 13 | AP-133/0 To AP-135/0 | 5.619 |  | M/s Kec | Yet not submitted
| 14 | AP-135/0 To AP-139/0 | 3.856 |  | M/s Kec | Yet not submitted
| 15 | AP-139/0 To AP-148/0 | 14.391 | 2025-04-16
| 16 | AP-148/0 To AP-150/0 | 5.268 |  | M/s Apraava | Will be approved by 17.06.2025
| 17 | AP-150/0 To AP-157/0 | 2.474 | 2025-04-18 | M/s Apraava & M/s Kec | Under discussion due to Underneath crossing at 154/0 to 155/0 and railway proposal crossing 150/0 to 151/0.
|  | Total | 187.175

## Sheet8 (hidden)
S No. | MOM as on 11/6/25 | Timeline | Responsibility | Status as on 19/6/25
1 | 400kv Detail Survey from AP 01 to AP 10
a | Apraava will give clearance for further proceeding of Detail Survey | 2025-06-13 | M/S Apraava | Clearance provided for Detail Survey
b | Completion of Detail Survey | 2025-06-25 | M/S KEC | Detail Survey work under progress
c | Detail Survey of 765 kV is submitted by KEC, observation raised by Apraava, KEC has to re-submitted according to observation | 2025-06-16 | M/S KEC | Reobservation mail by Engg. Team on dt. 19.06.25
2 | Check Survey
a | 50 km will be approved | 2025-06-12 | M/S Apraava & KEC | 33 km Approved & 15 km submitted by KEC
b | Pending Section of 21 km will be approved | 2025-06-20 | M/S Apraava & KEC | Under Progress
c | Check Survey of 765kV is to be submitted by KEC | 2026-06-25 | M/S KEC | Detail Survey work under progress
3 | Statutory Approvals
a | 02 No NH Proposal Submission | 2025-06-30 | M/S KEC | Under Progress
b | 02 No Railway Proposal Submission | 2025-06-30 | M/S KEC | Under Progress
c | 02 Nos PLC Proposal of 400 kV Underneath has to Submit | ASAP | M/S KEC | Under Progress
d | Statutory Approvals tracker to be maintain for monitoring current status of NOC | N/A | M/S Apraava & KEC | Under Progress
e | 04 Submission of SH Proposal to SH Authority | 2025-06-20 | M/S Apraava | Under Progress
f | 03 Submission of Oil Proposal to Oil Authority | 2025-06-20 | M/s Apraava | Under Progress
4 | Deployment of surveyor, supervisors, engineers & section in charge to be expedite in Bhinmal Section | 2025-06-12 | M/S KEC | Under Progress
5 | KEC committed 43 nos. foundation for this month & accordingly Apraava will provide ROW clearance | 2025-06-30 | M/S Apraava & KEC | Till date 13 foundations completed, 10 are in WIP and 30 work fronts are available
6 | Manpower in each foundation gang need to be strengthen with at least 8-10 manpower/gang | ASAP | M/S KEC | Under Progress
7 | Apraava asked to increase 4 more foundation gangs to expedite foundation work (currently 7 gangs are available with insufficient manpower | ASAP | M/S KEC | 9 Gangs are available (insufficient manpower in 4 gangs)
8 | 40 Nos Departmental Manpower availability at site | 2025-06-30 | M/S KEC | -
9 | Quality Constraints
a | Information regarding supply of cement with prior & proper documentation | N/A | M/S KEC | -
b | Material availability at site from approved source | - | M/S KEC | -
c | Approval of use of Curing compound in foundation work need to be expedite after jointly discussion of both team | ASAP | M/S Apraava & KEC | Cubes taken after applying curing compound & further process is u/p
d | CTM Machine at store need be installed on priority for cube testing | 2025-06-13 | M/S KEC | Under Progress
10 | Erection team to be deployed and erection to be start | 2025-06-18 | M/S KEC | Erection to be start by Monday, 23/6/25
11 | July month foundation & erection plan to be shared by KEC | 2025-06-16 | M/S KEC | July month plan to be shared within 2-3 days by KEC
12 | Supply of conductor to be start in September month | 2025-09-30 | M/S Apraava | Planned for September month
13 | Total 121 nos. of DA type of tower supplied to store & 2nd lot of 74 nos. towers (approx. 1500 MT) supply, consisting of DC & DD type towers are scheduled for next month | 2025-07-10 | M/S KEC | DA type towers are supplied

## Sheet2 (hidden)
400kV D/C Fatehgarh IV (Section-2)PS - Bhinmal (PG) Transmission Line
Sl No | Section AP To AP | Section length | Remarks
1 | AP-21/0 To AP-24/0 | 2.618
2 | AP-24/0 To AP-27/0 | 1.428
3 | AP-27/0 To AP-40/0 | 16.76
4 | AP-45/0 To AP-48/0 | 3.187
5 | AP-153/0 To AP-154/0 | 0.732
6 | AP-154/0 To AP-155/0 | 0.218
7 | AP-155/0 To S/S Gantry | 0.571
| TOTAL | 25.514
765kV D/C Fatehgarh IV (Section-2)PS - Bhinmal (PG) Transmission Line
Sl No | Section AP To AP | Section length | Route Allignment,Detail Survey,Check survey
| LI | 7.584
| LO | 6.951
| TOTAL | 14.535

## Sheet1 (hidden)
FOUNDATION STATUS | [7 empty] | 18
SL. No. | Location Number | Span | Tower Type | RC | Foundation type
[6 empty] | Starting date | Completion Date | Agency | Remark | Remarks
1 | 83/1 | 83/1 | DA+3 |  | Sandy | 2025-01-08 | 2025-01-17 | Mahadeep Company | 2025-01-17 | Complete
2 | 81/4 | 81/4 | DA+0 |  | Sandy | 2025-01-18 | ROW | Mahadeep Company | ROW LOC HOLD | Row Since 20-01-2025, Gang Domobilized
3 | 75/7 | 75/7 | DA+0 |  | Sandy | 2025-01-18 | 2025-01-27 | AR PATEL |  | RCC Complete
4 | 75/6 |  | DA+0 |  | Sandy | 2025-01-28 | 2025-02-02 | AR PATEL |  | RCC Complete, Backfilling Done
5 | 75/5 |  | DA+0 |  | Sandy | 2025-01-28 | 2025-02-05 | AR PATEL |  | RCC Complete.
6 | 75/4 |  | DA+0 |  | Sandy | 2025-01-29 | 2025-02-05 | Om Constraction |  | RCC Complete, Backfilling Done
7 | 75/3 |  | DA+3 |  | Sandy | 2025-02-03 | 2025-02-10 | Om Constraction |  | RCC Complete.
8 | 75/1 |  | DA+0 |  | Sandy | 2025-02-09 | 2025-02-17 | Om Constraction |  | RCC Complete.
9 | 75/2 |  | DA+0 |  | Sandy | 2025-02-12 | 2025-02-18 | Om Constraction |  | RCC Complete.
10 | 77/1 |  | DA+0 |  | Sandy | 2025-02-03 | 2025-02-11 | Anjaana Construction |  | RCC Complete.
11 | 77/2 |  | DA+3 |  | Sandy | 2025-02-03 | 2025-02-09 | AR PATEL |  | RCC Complete, Backfilling Done
12 | 77/3 |  | DA+0 |  | Sandy | 2025-02-08 | 2025-02-14 | AR PATEL |  | RCC Complete.
13 | 77/4 |  | DA+3 |  | Sandy | 2015-02-11 | 2025-02-17 | Anjaana Construction |  | RCC Complete.
14 | 77/5 |  | DA+6 |  | Sandy | 2025-02-13 |  | AR PATEL |  | Pit B,C RCC Done & Pit A,D Frustrum RCC done.
15 | 86/2 |  | DA+0 |  | Sandy | 2025-02-10 |  | Kalpana Enterprises |  | Pit A , Pit B RCC Done , Pit C -Stub setting.
16 | 66/1 |  | DA+9 |  | Sandy | 2025-02-17 |  | Siyag Construction |  | Excavation WIP, ROW,Material Shifting WIP
17 | 73/3 |  | DA+9 |  | Sandy | 2025-02-17 |  | Om Constraction |  | Excavation WIP, ROW, Material Shifting WIP
18 | 79/1 |  | DA+9 |  | Sandy | 2025-02-17 |  | Anjana Construction |  | Excavation WIP, ROW, Material Shifting WIP
19 | 95A/1 |  | DA+0 |  | Sandy |  |  | Gurukripa Enterprises |  | Pit Marking Done
20 | 80/1
21 | 85/1
22 | 73/2
23 | 66/2
24 | 66/3
25 | 86/1
26 | 76/1

## VC 51-96 (hidden)
TB-507 400 KV (Twin) D/C Fatehgarh IV - Bhinmal Transmission Line
DPR and VISUAL CHART
DPR- |  |  | District |  | No.Of Towers | Length | Foundation |  |  | Earthing | Tower Erection |  |  | Stringing
[7 empty] | Com | WIP | Bal | Com | Com | WIP | Bal | Com | WIP | Bal
[5 empty] | 163 | 50.886 | 16 | 5 | 142 | 10 |  |  | 163 |  |  | 50.886
|  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9
|  |  | 465.03 |  | 375.98 |  | 414.86 |  | 381.02 |  | 353.63 |  | 351.4 |  | 433.26 |  | 396.56 |  | 408.11 | 3579.85
|  | AP51 |  | 51/1 |  | 51/2 |  | 51/3 |  | AP52 |  | 52/1 |  | AP53 |  | AP54 |  | 54/1
|  | DD+18 |  | DA+03 |  | DA+00 |  | DA+03 |  | DB+0 |  | DA+06 |  | DD+0 |  | DC+00 |  | DA+03
[10 empty] | RC |  | RC
| 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19
|  | 425.22 |  | 420.54 |  | 340.56 |  | 336.52 |  | 375.99 |  | 303.41 |  | 448.76 |  | 393.09 |  | 407.8 |  | 206.06 | 3657.95
| 54/2 |  | 54/3 |  | AP55 |  | AP56 |  | 56/1 |  | 56/2 |  | 56/3 |  | 56/4 |  | 56/5 |  | AP57
| DA+06 |  | DA+03 |  | DD+18 |  | DB+09 |  | DB+9 |  | DA+0 |  | DB+9 |  | DA+6 |  | DA+6 |  | DB+09
| Benching &RC |  | RC |  | RC |  | Benching &RC |  |  |  | Benching Required | [5 empty] | Benching &RC |  | Benching &RC
| 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29
|  | 417.38 |  | 304.56 |  | 408.66 |  | 434.89 |  | 408.17 |  | 398.59 |  | 446.37 |  | 297.58 |  | 240.47 |  | 312.69 | 3669.36
| AP58 |  | AP59 |  | 59/1 |  | AP60 |  | 60/1 |  | 60/2 |  | 60/3 |  | AP61 |  | 61/1 |  | AP62
| DB+09 |  | DC+09 |  | DA+0 |  | DD+00 |  | DA+9 |  | DA+0 |  | DA+9 |  | DC+00 |  | DA+9 |  | DB+00
[5 empty] | Benching | [7 empty] | RC
| 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39
|  | 347.88 |  | 379.25 |  | 398.7 |  | 439.06 |  | 381.53 |  | 379.71 |  | 426.3 |  | 387.14 |  |  |  | 423.77 | #REF!
| 62/1 |  | 62/2 |  | 62/3 |  | 62/4 |  | 62/5 |  | AP63 |  | 63/1 |  | AP64 |  | 64/1 |  | 64/2
| DA+0 |  | DA+0 |  | DA+09 |  | DA+06 |  | DA+06 |  | DC+00 |  | DA+0 |  | DC+09 |  | DA+9 |  | DA+9
| RC |  |  |  | RC | [9 empty] | Benching &RC |  |  |  | RC
| 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49
|  | 407.9 |  | 426.63 |  | 392.27 |  | 431.96 |  | 426.02 |  | 405.36 |  | 411.93 |  | 423.77 |  | 407.9 |  | 426.63
| F |  | WIP | [13 empty] | F |  | F
| 64/3 |  | 64/4 |  | 64/5 |  | 64/6 |  | 64/7 |  | 65/0 |  | 65/1 |  | 66/0 |  | 66/1 |  | 66/2
| DA+9 |  | DA+9 |  | DA+9 |  | DA+3 |  | DA+3 |  | DD+0 |  | DB+09 |  | DD+0 |  | DA+9 |  | DA+0 |  | #REF!
RC
| 50 |  | 51 |  | 52 |  | 53 |  | 54 |  | 55 |  | 56 |  | 57 |  | 58 |  | 59
|  | 392.27 |  | 431.96 |  | 426.02 |  | 405.36 |  | 411.93 |  | 350.33 |  | 378.3 |  | 416.82 |  | 371.85
WIP
| 66/3 |  | 66/4 |  | 67/0 |  | 67/1 |  | 67/2 |  | AP68 |  | AP69 |  | 69/1 |  | 69/2 |  | 69/3
| DA+3 |  | DA+9 |  | DC+6 |  | DA+6 |  | DB+0 |  | DB+09 |  | DD+3 |  | DA+6 |  | DA+0 |  | DA+00
[5 empty] | RC | [11 empty] | Benching |  | RC |  | #REF!
| 60 |  | 61 |  | 62 |  | 63 |  | 64 |  | 65 |  | 66 |  | 67 |  | 68 |  | 69
|  | 392.27 |  | 431.96 |  | 426.02 |  | 405.36 |  | 411.93 |  | 350.33 |  | 378.3 |  | 416.82 |  | 371.85
F
| AP71 |  | 71/1 |  | 71/2 |  | 71/3 |  | AP72 |  | 72/1 |  | 72/2 |  | AP73 |  | 73/1 |  | 73/2
| DB+00 |  | DA+09 |  | DA+00 |  | DA+00 |  | DD+00 |  | DA+03 |  | DA+03 |  | DB+00 |  | DA+00 |  | DA+09
[7 empty] | RC |  | Benching &RC |  | RC | [5 empty] | Benching & RC |  | CLEAR |  | 3994.99
| 70 |  | 71 |  | 72 |  | 73 |  | 74 |  | 75 |  | 76 |  | 77 |  | 78 |  | 79
|  | 385.17 |  | 345.19 |  | 332.38 |  | 393.62 |  | 387.95 |  | 340.35 |  | 393.12 |  | 328.54 |  | 398.52
| F |  |  |  | F |  |  |  | F |  | F |  | F |  | F |  | F |  | F
| Er | [7 empty] | Er |  | Er |  | Er | [5 empty] | Er
| 73/3 |  | AP74 |  | 74/1 |  | AP75 |  | 75/1 |  | 75/2 |  | 75/3 |  | 75/4 |  | 75/5 |  | 75/6
| DA+09 |  | DB+09 |  | DA+0 |  | DC+0 |  | DA+00 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0
| CLEAR | [5 empty] | Benching |  | Benching |  | Benching &RC
| 80 |  | 81 |  | 82 |  | 83 |  | 84 |  | 85 |  | 86 |  | 87 |  | 88 |  | 89
[6 empty] | 388.46 |  | 380.96 |  | 374.03 |  | 351.96 |  | 395.64 |  | 414.76 |  | 401.93
| F |  |  |  | F |  |  |  | F |  | F |  | F |  | F |  | F
| Er | [7 empty] | Er | [5 empty] | Er |  | Er
| 75/7 |  | AP76 |  | 76/1 |  | 77/0 |  | 77/1 |  | 77/2 |  | 77/3 |  | 77/4 |  | 77/5 |  | AP78
| DA+0 |  | DC+00 |  | DA+06 |  | DB+00 |  | DA+00 |  | DA+03 |  | DA+00 |  | DA+03 |  | DA+06 |  | DC+00
[5 empty] | Clear | [5 empty] | Benching
| 90 |  | 91 |  | 92 |  | 93 |  | 94 |  | 95 |  | 96 |  | 97 |  | 98 |  | 99
|  | 385.54 |  |  |  | 351.18 |  | 441.06 |  | 387.5 |  | 372.63 |  | 415.3 |  | 424.58 |  | 391.7 |  | 410.47
[5 empty] | F | [5 empty] | F
Er
| 78/1 |  | AP79 |  | 79/1 |  | 79/2 |  | AP80 |  | 80/1 |  | AP81 |  | 81/1 |  | 81/2 |  | 81/3
| DA+03 |  | DD+00 |  | DA+09 |  | DA+00 |  | DB+03 |  | DA+9 |  | DB+09 |  | DA+00 |  | DA+03 |  | DA+00
[5 empty] | Clear |  | RC,Benching |  |  |  | Benching |  |  |  | Benching &RC
| 100 |  | 101 |  | 102 |  | 103 |  | 104 |  | 105 |  | 106 |  | 107 |  | 108 |  | 109
#REF!
415.03 |  | 416.87 |  |  |  | 426.47 |  | 396.98 |  | 429.38 |  | 403.83 |  | 384.63 |  | 380.68 |  | 354.53
| ROW | [11 empty] | F
U/P
| 81/4 |  | 81/5 |  | AP82 |  | 82/1 |  | 82/2 |  | AP83 |  | 83/1 |  | AP84 |  | AP85 |  | 85/1
| DA+00 |  | DA+06 |  | DB+03 |  | DA+00 |  | DA+03 |  | DC+00 |  | DA+03 |  | DC+06 |  | DC+00 |  | DA+00
[7 empty] | RC | [11 empty] | CLEAR
| 110 |  | 111 |  | 112 |  | 113 |  | 114 |  | 115 |  | 116 |  | 117 |  | 118 |  | 119
3121.94
|  | 395.01 | #REF! |  |  | 380.77 |  | 411.81 |  | 432.08 |  | 256.87 |  | 412.4 |  | 382.17 |  | 452.74
F
| AP86 |  | 86/1 |  | 86/2 |  | AP87 |  | 87/1 |  | 87/2 |  | AP88 |  | AP89 |  | 89/1 |  | AP90
| DD+00 |  | DA+06 |  | DA+00 |  | DC+00 |  | DA+03 |  | DA+09 |  | DC+00 |  | DC+00 |  | DA+09 |  | DC+00
| CLEAR |  | CLEAR |  | CLEAR
| 120 |  | 121 |  | 122 |  | 123 |  | 124 |  | 125 |  | 126 |  | 127 |  | 128 |  | 129
#REF!
|  | 430.39 |  |  |  | 378.62 |  | 350.22 |  | 357.91 |  | 237.48 |  | 440.03 |  | 504 |  | 430.57
| 90/1 |  | AP91 |  | 91/1 |  | 91/2 |  | 91/3 |  | AP92 |  | AP93 |  | AP94 |  | AP95 |  | 95/1
| DA+09 |  | DD+00 |  | DA+00 |  | DA+00 |  | DA+00 |  | DC+00 |  | DC+00 |  | DB+06 |  | DB+06 |  | DB+00
| 130 |  | 131 |  | 132 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137 |  | 138 |  | 139 |  | 130
|  | 354.92 |  |  |  | 419.38 |  | 406.18 |  | 427.47 |  |  |  | 416.77 |  | 378.13 |  | 358.57 |  | 360.52
[5 empty] | F |  |  |  | F
| 95/2 |  | 95A/0 |  | 95A/1 |  | AP96 |  | 96/1 |  | 96/2 |  | AP97 |  | 97/1 |  | AP98 |  | AP98/1 |  | 98A/0
| DA+09 |  | DB+0 |  | DA+00 |  | DC+00 |  | DA+00 |  | DA+00 |  | DC+00 |  | DA+03 |  | DC+00 |  | DA+00 |  | DC+00
RC
| 131 |  | 132 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137 |  | 138 |  | 139 |  | 140 |  | 141
| 98A/1 |  | 98B/0 |  | 98B/1 |  | 98B/2 |  | 99/0 |  | 99/1 |  | 99/2 |  | 99/3 |  | 99/4 |  | 99/5 |  | 99/6
| DA+00 |  | DD+00 |  | DA+00 |  | DCT+00 |  | DC+0 |  | DA+06 |  | DA+00 |  | DA+00 |  | DA+06 |  | DA+03 |  | DA+03
[5 empty] | RC | [9 empty] | RC
| 142 |  | 143 |  | 144 |  | 145 |  | 146 |  | 147 |  | 148 |  | 149 |  | 150 |  | 151 |  | 152
| AP99A |  | 99A/1 |  | 99A/2 |  | AP100 |  | 100/1 |  | AP101 |  | AP102 |  | 102/1 |  | 102/2 |  | AP103 |  | 103/1
| DB+00 |  | DA+00 |  | DA+00 |  | DC+00 |  | DA+6 |  | DD+06 |  | DD+3 |  | DA+00 |  | DA+00 |  | DC+0 |  | DA+6
| 153 |  | 154 |  | 155 |  | 156 |  | 157 |  | 158 |  | 159 |  | 160 |  | 161 |  | 162 |  | 163
| AP104 |  | AP104A |  | AP104B |  | 104B/1 |  | 104B/2 |  | AP105 |  | 105/1 |  | AP106 |  | AP107
| DB+9 |  | DC+9 |  | DB+9 |  | DA+0 |  | DA+0 |  | DD+0 |  | DA+3 |  | DC+6 |  | DD+3
|  |  | RC |  | RC
| 164 |  | 165 |  | 166 |  | 167 |  | 168 |  | 169 |  | 170 |  | 171 |  | 172 |  | 173 |  | 174
| AP104 |  | AP104A |  | AP104B |  | 104B/1 |  | 104B/2 |  | AP105 |  | 105/1 |  | AP106 |  | AP107 |  | 107/1 |  | 108/0
| DB+9 |  | DC+9 |  | DB+9 |  | DA+0 |  | DA+0 |  | DD+0 |  | DA+3 |  | DC+6 |  | DD+3 |  | DA+9 |  | DC+0
|  |  | RC |  | RC | [15 empty] | 1MRC
| 175 |  | 176 |  | 177 |  | 178 |  | 179 |  | 180 |  | 181 |  | 182 |  | 183 |  | 184 |  | 185
| AP109 |  | AP109A |  | AP110 |  | AP111 |  | AP112 |  | AP113 |  | AP113A |  | AP114 |  | 114/1 |  | AP115 |  | 115/1
| DC+3 |  | DB+6 |  | DC+0 |  | DB+9 |  | DC+9 |  | DD+0 |  | DC+0 |  | DC+0 |  | DA+9 |  | DC+0 |  | DB+9
[7 empty] | 3 MRC |  | 3 MRC | [9 empty] | 1MRC
| 186 |  | 187 |  | 188 |  | 189 |  | 190 |  | 191 |  | 192 |  | 193 |  | 194 |  | 195 |  | 196
| AP116 |  | 116/1 |  | AP117 |  | 117/1 |  | 117/2 |  | AP118 |  | AP119 |  | 119/1 |  | 119/2 |  | AP120 |  | 120/1
| DD+0 |  | DA+0 |  | DD+0 |  | DA+3 |  | DB+9 |  | DC+3 |  | DD+3 |  | DA+3 |  | DA+3 |  | DC+0 |  | DA+6
|  |  | Benching |  | RC
197
AP121
DD+0
TSE
Manual
Total
Paying out/ Rough sag
[11 empty] | Tack welding completed | [5 empty] | Erection ROW
Erection Completed ------>
|  | Foundation completed ----> | [8 empty] | <------Insulator hosting
|  | Earthing completed -----> |  |  |  |  | U/P | [9 empty] | Erection Cleared
Road
[7 empty] | 325 | Span
[12 empty] | HT-D/C Power Line Crossing |  |  |  |  | Cart Track
| Transformer |  |  | ROW | ROW |  |  | Water Tank
| Temple |  |  | A+0 | Tower Type |  |  | LT Power Line Crossing |  |  |  | HT-S/C Power Line Crossing |  |  |  |  | Broad Gauge Railway
[8 empty] | 11 KV Line Crossing | [8 empty] | Line Crossing
| Hut |  |  | 1/0 | Location No. |  |  | 33 KV Line Crossing
| Bore & Handpump |  |  |  | Minor River Crossing | [6 empty] | Forest Stretch |  |  |  |  | SH Crossing
| Oil Pipe Line |  |  | RC | Raised Chimney |  |  | Major River Crossing |  |  |  | NH Crossing |  |  |  |  | Wild Life Sanctuary
3
3
3
3
3

## VC (hidden)
TB-507 400 KV (Twin) D/C Fatehgarh IV - Bhinmal Transmission Line
DPR and VISUAL CHART
| DPR- |  |  | District |  | No.Of Towers | Length | Foundation |  |  | Earthing | Tower Erection |  |  | Stringing
[8 empty] | Com | WIP | Bal | Com | Com | WIP | Bal | Com | WIP | Bal
[6 empty] | 495 | 187.175 | 9 | 5 | 481 | 3 |  |  | 495 |  |  | 187.175
r
| 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10
|  | 97.4 |  | 139.42 |  | 484.04 |  | 398 |  | 443.16 |  | 399.53 |  | 402.87 |  | 437.15 |  | 381.84 |  | 416.91 | 3600.32 | FDN | TE | Earthing | Stringing |  | Tack Welding | 3600.32
1 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| GE |  | AP1 |  | AP2 |  | AP3 |  | 03/1 |  | 3/2 |  | 3/3 |  | 3/4 |  | 3/5 |  | 3/6 |  |  | 0 | 0 | 0 |  | ROW
|  |  | DD+03 |  | DD+9 |  | DC+9 |  | DA+9 |  | DA+0 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+00
| 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20
|  | 428.12 |  | 249.58 |  | 454.54 |  | 377.83 |  | 447.64 |  | 396.44 |  | 445.93 |  | 156.98 |  | 409.67 |  | 382.38 | 3749.11 | [6 empty] | 3749.11
2 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 3/7 |  | 3/8 |  | AP4 |  | 4/1 |  | AP5 |  | 5/1 |  | 5/2 |  | AP6 |  | AP7 |  | 7/1 |  |  | 0 | 0 | 0 |  | ROW
| DA+03 |  | DD+03 RC |  | DD+03 |  | DA+09 |  | DC+3 |  | DA+06 |  | DA+03 |  | DD+09 |  | DD+09 |  | DA+00
| 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30
|  | 353.89 |  | 385.21 |  | 367.67 |  | 378.32 |  | 392.49 |  | 399.24 |  | 390.93 |  | 412.07 |  | 421.95 |  | 391.87 | 3893.64 | [6 empty] | 3893.64
3 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 7/2 |  | 7/3 |  | 7/4 |  | 7/5 |  | 7/6 |  | '7/7 |  | AP8 |  | 08/01 |  | 08/2 |  | 08/3 |  |  | 0 | 0 | 0 |  | ROW
| DA+00 |  | DA+00 |  | DA+00 |  | DA+00 |  | DA+00 |  | DA+00 |  | DB+00 |  | DA+06 |  | DA+00 |  | DA+00
| 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40
|  | 406.65 |  | 383.31 |  | 402.96 |  | 433.9 |  | 328.55 |  | 331.44 |  | 358.83 |  | 358.55 |  | 429.37 |  | 354.9 | 3788.46 | [6 empty] | 3788.46
4 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 08/4 |  | 08/5 |  | 08/6 |  | 08/7 |  | AP9 |  | 09/01 |  | 09/02 |  | 09/03 |  | 09/04 |  | 09/05 |  |  | 0 | 0 | 0 |  | ROW
| DA+03 |  | DA+00 |  | DA+06 |  | DA+06 |  | DB+00 |  | DA+00 |  | DA+00 |  | DA+00 |  | DA+00 |  | DA+00
| 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49 |  | 50
|  | 340.94 |  | 405.66 |  | 409.41 |  | 378.36 |  | 322.47 |  | 386.39 |  | 386.19 |  | 406.2 |  | 351.15 |  | 380.59 | 3767.36 | [6 empty] | 3767.36
5 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 09/06 |  | AP10 |  | 10/01 |  | 10/02 |  | 10/03 |  | 10/04 |  | 10/05 |  | 10/06 |  | 10/07 |  | 10/08 |  |  | 0 | 0 | 0 |  | ROW
| DA+00 |  | DC+9 |  | DA+09 |  | DA+00 |  | DA+00 |  | DA+00 |  | DA+00 |  | DA+00 |  | DA+00 |  | DA+00
| 51 |  | 52 |  | 53 |  | 54 |  | 55 |  | 56 |  | 57 |  | 58 |  | 59 |  | 60
|  | 380.02 |  | 393.7 |  | 390.68 |  | 349.16 |  | 416.01 |  | 400.75 |  | 406.84 |  | 404.76 |  | 311.74 |  | 389.98 | 3843.64 | [6 empty] | 3843.64
6 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 10/09 |  | AP11 |  | 11/01 |  | AP12 |  | 12/01 |  | 12/02 |  | 12/03 |  | 12/04 |  | 12/05 |  | 12/06 |  |  | 0 | 0 | 0 |  | ROW
| DA+00 |  | DC+00 |  | DA+03 |  | DD+00 |  | DA+03 |  | DA+03 |  | DA+00 |  | DA+03 |  | DA+00 |  | DA+00
| 61 |  | 62 |  | 63 |  | 64 |  | 65 |  | 66 |  | 67 |  | 68 |  | 69 |  | 70
|  | 384.15 |  | 350.96 |  | 437.11 |  | 406.67 |  | 421.42 |  | 421.75 |  | 380.8 |  | 438.78 |  | 426.5 |  | 375.59 | 4066.13 | [6 empty] | 4043.73
7 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 12/07 |  | 12/08 |  | AP13 |  | 13/01 |  | 13/02 |  | 13/03 |  | 13/04 |  | AP14 |  | AP15 |  | 15/01 |  |  | 0 | 0 | 0 |  | ROW
| DA+00 |  | DA+00 |  | DC+00 |  | DA+09 |  | DA+00 |  | DA+06 |  | DA+03 |  | DB+09 |  | DC+06 |  | DA+03
Paddy
| 71 |  | 72 |  | 73 |  | 74 |  | 75 |  | 76 |  | 77 |  | 78 |  | 79 |  | 80
|  | 413.56 |  | 407.62 |  | 397.38 |  | 408.9 |  | 395.25 |  | 384.81 |  | 388.05 |  | 362.31 |  | 359.92 |  | 386.31 | #REF! | [6 empty] | 3904.11
8 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 15/02 |  | 15/03 |  | AP16 |  | 16/01 |  | 16/02 |  | 16/03 |  | 16/04 |  | 16/05 |  | 16/06 |  | 16/07 |  |  | 0 | 0 | 0 |  | ROW
| DA+03 |  | DA+06 |  | DC+00 |  | DA+03 |  | DA+09 |  | DA+00 |  | DA+00 |  | DA+00 |  | DA+00 |  | DA+00
Paddy
| 81 |  | 82 |  | 83 |  | 84 |  | 85 |  | 86 |  | 87 |  | 88 |  | 89 |  | 90
|  | 319.93 |  | 342.16 |  | 384.83 |  | 365.71 |  | 394.61 |  | 315.81 |  | 419.79 |  | 418.97 |  | 420.65 |  | 422.09 | 3804.55 | [6 empty] | 3804.55
9 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 16/08 |  | AP17 |  | 17/01 |  | 17/02 |  | 17/03 |  | AP18 |  | AP19 |  | AP20 |  | 20/01 |  | 20/02 |  |  | 0 | 0 | 0 |  | ROW
| DA+00 |  | DB+0 |  | DA+00 |  | DA+00 |  | DA+03 |  | DB+00 |  | DB+06 |  | DB+09 |  | DA+03 |  | DA+00
[11 empty] | Paddy | [5 empty] | Paddy
| 91 |  | 92 |  | 93 |  | 94 |  | 95 |  | 96 |  | 97 |  | 98 |  | 99 |  | 100
|  | 420.49 |  | 459.09 |  | 386.28 |  | 273.16 |  | 313.62 |  | 361.38 |  | 308.79 |  | 332.52 |  | 269.07 |  | 357.59 | 3481.99 | [6 empty] | 3481.99
10 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 20/03 |  | 20/04 |  | 20/05 |  | AP21 |  | 21/01 |  | 21/02 |  | 21/03 |  | AP22 |  | 22/01 |  | 22/02 |  |  | 0 | 0 | 0 |  | ROW
| DA+06 |  | DB+00 |  | DA+09 |  | DC+09 |  | DA+03 |  | DA+06 |  | DA+00 |  | DC+09 |  | DA+03 |  | DA+06
[13 empty] | Paddy | [5 empty] | Paddy
| 101 |  | 102 |  | 103 |  | 104 |  | 105 |  | 106 |  | 107 |  | 108 |  | 109 |  | 110
|  | 201.38 |  | 218.35 |  | 439.11 |  | 365.6 |  | 424.47 |  | 412.73 |  | 401.93 |  | 379.06 |  | 404.19 |  | 441.06 | 3687.88 | [6 empty] | 3687.88
11 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| AP23 |  | AP24 |  | AP25 |  | 25/01 |  | AP26 |  | 26/01 |  | 26/02 |  | 26/03 |  | 26/04 |  | 26/05 |  |  | 0 | 0 | 0 |  | ROW
| DD+18 |  | DD+25 |  | DD+06 |  | DA+09 |  | DC+09 |  | DA+09 |  | DA+06 |  | DA+03 |  | DA+06 |  | DA+03
Paddy
| 111 |  | 112 |  | 113 |  | 114 |  | 115 |  | 116 |  | 117 |  | 118 |  | 119 |  | 120
|  | 404.77 |  | 386.79 |  | 382.59 |  | 460.27 |  | 369.05 |  | 447.91 |  | 371.72 |  | 373.16 |  | 423.96 |  | 381.03 | 4001.25 | [6 empty] | 4001.25
12 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 26/06 |  | AP27 |  | 27/1 |  | 27/2 |  | AP28 |  | 28/1 |  | 28/2 |  | 28/3 |  | 28/4 |  | AP29 |  |  | 0 | 0 | 0 |  | ROW
| DA+06 |  | DC+3 |  | DA+09 |  | DA+09 |  | DB+0 |  | DA+00 |  | DA+09 |  | DA+00 |  | DB+9 |  | DC+3
Paddy
| 121 |  | 122 |  | 123 |  | 124 |  | 125 |  | 126 |  | 127 |  | 128 |  | 129 |  | 130
|  | 419.6 |  | 425.18 |  | 287.54 |  | 336.51 |  | 325.3 |  | 214.25 |  | 455.95 |  | 421.16 |  | 423.79 |  | 403.85 | 3725.44 | [6 empty] | 3713.13
13 |  |  | ROW | [5 empty] | ROW |  | ROW | [10 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 29/1 |  | 29/2 |  | AP30 |  | 30/1 |  | 30/2 |  | 30/3 |  | AP31 |  | AP32 |  | 32/1 |  | 32/2 |  |  | 3 | 0 | 0 |  | ROW
| DA+06 |  | DA+09 |  | DC+0 |  | DA+00 |  | DA+00 |  | DA+00 |  | DC+9 |  | DC+9 |  | DA+03 |  | DA+03
Paddy
| 131 |  | 132 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137 |  | 138 |  | 139 |  | 140
|  | 408.95 |  | 324.03 |  | 366.7 |  | 473.31 |  | 358.32 |  | 477.82 |  | 411.46 |  | 406.23 |  | 437.43 |  | 455.92 | #REF! | [6 empty] | 4120.17
14 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 32/3 |  | AP33 |  | AP34 |  | 34/1 |  | AP35 |  | 35/1 |  | AP36 |  | 36/1 |  | 36/2 |  | AP37 |  |  | 0 | 0 | 0 |  | ROW
| DA+09 |  | DB+0 |  | DC+6 |  | DA+09 |  | DC+9 |  | DA+09 |  | DC+9 |  | DA+09 |  | DA+09 |  | DD+3
| 141 |  | 142 |  | 143 |  | 144 |  | 145 |  | 146 |  | 147 |  | 148 |  | 149 |  | 150
|  | 368.5 |  | 419.77 |  | 418.92 |  | 386.49 |  | 376.53 |  | 404.74 |  | 366.73 |  | 274.59 |  | 341.67 |  | 425.86 | 3783.8 | [6 empty] | 3783.8
15 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 37/1 |  | AP38 |  | 38/1 |  | 38/2 |  | 38/3 |  | AP39 |  | 39/1 |  | 39/2 |  | 39/3 |  | 39/4 |  |  | 0 | 0 | 0 |  | ROW
| DA+06 |  | DB+0 |  | DA+06 |  | DA+09 |  | DA+03 |  | DB+3 |  | DA+06 |  | DA+00 |  | DA+00 |  | DA+00
| 151 |  | 152 |  | 153 |  | 154 |  | 155 |  | 156 |  | 157 |  | 158 |  | 159 |  | 160
|  | 394.31 |  | 370.45 |  | 436.75 |  | 397.61 |  | 413.4 |  | 423.65 |  | 415.97 |  | 415.35 |  | 394.88 |  | 429.62 | 4091.99 | [6 empty] | 4091.99
16 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 39/5 |  | AP40 |  | 40/1 |  | 40/2 |  | AP41 |  | 41/1 |  | 41/2 |  | 41/3 |  | AP42 |  | 42/1 |  |  | 0 | 0 | 0 |  | ROW
| DA+06 |  | DD+3 |  | DB+06 |  | DA+06 |  | DB+0 |  | DA+09 |  | DCT+0 |  | DA+09 |  | DC+3 |  | DA+09
| 161 |  | 162 |  | 163 |  | 164 |  | 165 |  | 166 |  | 167 |  | 168 |  | 169 |  | 170
|  | 381.91 |  | 405.26 |  | 338.16 |  | 288.3 |  | 297.15 |  | 195.9 |  | 249.66 |  | 374.48 |  | 443.95 |  | 404.39 | #REF! | [6 empty] | 3379.16
17 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 42/2 |  | 42/3 |  | 42/4 |  | 42/5 |  | 42/6 |  | 42/7 |  | AP43 |  | AP44 |  | 44/1 |  | AP45 |  |  | 0 | 0 | 0 |  | ROW
| DA+06 |  | DA+09 |  | DA+09 |  | DA+00 |  | DA+03 |  | DA+00 |  | DC+6 |  | DB+09 |  | DA+09 |  | DD+09
| 171 |  | 172 |  | 173 |  | 174 |  | 175 |  | 176 |  | 177 |  | 178 |  | 179 |  | 180
|  | 341.42 |  | 305.4 |  | 319.98 |  | 345.62 |  | 223.15 |  | 389.84 |  | 439.14 |  | 403.21 |  | 422.55 |  | 353.48 | 3543.79 | [6 empty] | 3543.79
18 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 45/1 |  | 45/2 |  | 45/3 |  | 45/4 |  | AP46 |  | AP47 |  | 47/1 |  | 47/2 |  | AP48 |  | AP49 |  |  | 0 | 0 | 0 |  | ROW
| DA+00 |  | DA+03 |  | DA+00 |  | DA+06 |  | DD+09 |  | DD+09 |  | DA+09 |  | DA+09 |  | DD+03 |  | DD+03
| 181 |  | 182 |  | 183 |  | 184 |  | 185 |  | 186 |  | 187 |  | 188 |  | 189 |  | 190
0
19 |  |  |  | 465.03 |  | 375.98 |  | 414.86 |  | 381.02 |  | 353.63 |  | 351.4 |  | 433.26 |  | 396.56 |  | 408.11 |  | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
[22 empty] | 0 | 0 | 0 |  | ROW
| AP51 |  | AP51 |  | 51/1 |  | 51/2 |  | 51/3 |  | AP52 |  | 52/1 |  | AP53 |  | AP54 |  | 54/1
| DD+18 |  | DD+18 |  | DA+03 |  | DA+00 |  | DA+03 |  | DB+0 |  | DA+06 |  | DD+0 |  | DC+00 |  | DA+03
| 191 |  | 192 |  | 193 |  | 194 |  | 195 |  | 196 |  | 197 |  | 198 |  | 199 |  | 200
0
20 |  | 425.22 |  | 420.54 |  | 340.56 |  | 336.52 |  | 375.99 |  | 303.41 |  | 448.76 |  | 393.09 |  | 407.8 |  | 206.06 |  | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
[22 empty] | 0 | 0 | 0 |  | ROW
| 54/2 |  | 54/3 |  | AP55 |  | AP56 |  | 56/1 |  | 56/2 |  | 56/3 |  | 56/4 |  | 56/5 |  | AP57
| DA+06 |  | DA+03 |  | DD+18 |  | DB+09 |  | DB+9 |  | DA+0 |  | DB+9 |  | DA+6 |  | DA+6 |  | DB+09
| Benching &RC | [5 empty] | Benching &RC |  |  |  | Benching &RC | [5 empty] | Benching &RC |  | Benching &RC
| 201 |  | 202 |  | 203 |  | 204 |  | 205 |  | 206 |  | 207 |  | 208 |  | 209 |  | 210
0
21 |  | 417.38 |  | 304.56 |  | 408.66 |  | 434.89 |  | 408.17 |  | 398.59 |  | 446.37 |  | 297.58 |  | 240.47 |  | 312.69 |  | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
[22 empty] | 0 | 0 | 0 |  | ROW
| AP58 |  | AP59 |  | 59/1 |  | AP60 |  | 60/1 |  | 60/2 |  | 60/3 |  | AP61 |  | 61/1 |  | AP62
| DB+09 |  | DC+09 |  | DA+0 |  | DD+00 |  | DA+9 |  | DA+0 |  | DA+9 |  | DC+00 |  | DA+9 |  | DB+00
[5 empty] | Benching &RC |  |  |  | CHECK SURVEY WIP
| 211 |  | 212 |  | 213 |  | 214 |  | 215 |  | 216 |  | 217 |  | 218 |  | 219 |  | 220
0
22 |  | 347.88 |  | 379.25 |  | 398.7 |  | 439.06 |  | 381.53 |  | 379.71 |  | 387.43 |  | 426.3 |  | 387.14 |  | 392.93 |  | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
[22 empty] | 0 | 0 | 0 |  | ROW
| 62/1 |  | 62/2 |  | 62/3 |  | 62/4 |  | 62/5 |  | AP63 |  | 63/1 |  | 63/2 |  | AP64 |  | 64/1
| DA+0 |  | DA+0 |  | DA+09 |  | DA+06 |  | DA+06 |  | DC+00 |  | DA+0 |  | DA+9 |  | DB+09 |  | DA+9
CHECK SURVEY WIP
| 221 |  | 222 |  | 223 |  | 224 |  | 225 |  | 226 |  | 227 |  | 228 |  | 229 |  | 230
0
23 |  | 423.77 |  | 407.9 |  | 426.63 |  | 392.27 |  | 431.96 |  | 426.02 |  | 405.36 |  | 411.93 |  | 350.33 |  | 378.3 |  | 0 | 0 | 0 |  | COM
[17 empty] | U/P |  |  |  |  | 1 | 0 | 0 |  | WIP
[22 empty] | 0 | 0 | 0 |  | ROW
| 64/2 |  | 64/3 |  | 64/4 |  | 64/5 |  | 64/6 |  | AP65 |  | 65/1 |  | AP66 |  | 66/1 |  | AP67
| DA+9 |  | DA+9 |  | DA+9 |  | DA+3 |  | DA+3 |  | DC+00 |  | DB+9 |  | DD+03 |  | DA+06 |  | DC+00
CHECK SURVEY WIP
Paddy
| 231 |  | 232 |  | 233 |  | 234 |  | 235 |  | 236 |  | 237 |  | 238 |  | 239 |  | 240
0
24 |  | 387.92 |  | 418.48 |  | 408.62 |  | 432.92 |  | 430.33 |  | 379.76 |  | 387.45 |  | 425.67 |  | 351.42 |  | 389.3 |  | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
[22 empty] | 0 | 0 | 0 |  | ROW
| 67/1 |  | 67/2 |  | 67/3 |  | 67/4 |  | 67/5 |  | AP68 |  | AP69 |  | 69/1 |  | 69/2 |  | 69/3
| DA+0 |  | DA+6 |  | DA+9 |  | DA+03 |  | DA+0 |  | DB+09 |  | DC+09 |  | DA+0 |  | DA+0 |  | DA+03
CHECK SURVEY WIP
| 241 |  | 242 |  | 243 |  | 244 |  | 245 |  | 246 |  | 247 |  | 248 |  | 249 |  | 250
0
25 |  | 416.82 |  | 371.85 |  | 404.03 |  | 422.11 |  | 388.48 |  | 455.28 |  | 464.05 |  | 376.87 |  | 415.71 |  | 409.51 |  | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
[22 empty] | 0 | 0 | 0 |  | ROW
| AP70 |  | AP71 |  | 71/1 |  | 71/2 |  | AP72 |  | 72/1 |  | 72/2 |  | AP73 |  | 73/1 |  | 73/2
| DD+00 |  | DB+00 |  | DA+03 |  | DA+00 |  | DD+03 |  | DA+06 |  | DA+00 |  | DB+00 |  | DA+09 |  | DA+09
CHECK SURVEY WIP
| 251 |  | 252 |  | 253 |  | 254 |  | 255 |  | 256 |  | 257 |  | 258 |  | 259 |  | 260
0
26 |  | 385.17 |  | 345.19 |  | 332.38 |  | 393.62 |  | 387.95 |  | 340.35 |  | 393.12 |  | 328.54 |  | 398.52 |  | 425.85 |  | 6 | 0 | 3 |  | COM
[7 empty] | F |  | U/P |  | F |  | F |  | F |  | F |  | F |  |  | 1 | 0 | 0 |  | WIP
[11 empty] | Er | [5 empty] | Er |  | Er |  |  | 0 | 0 | 0 |  | ROW
| AP74 |  | 74/1 |  | AP75 |  | 75/1 |  | 75/2 |  | 75/3 |  | 75/4 |  | 75/5 |  | 75/6 |  | 75/7
| DB+09 |  | DA+0 |  | DC+0 |  | DA+00 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0
| CHECK SURVEY WIP |  |  |  | Benching |  | Benching |  | Benching &RC
| 261 |  | 262 |  | 263 |  | 264 |  | 265 |  | 266 |  | 267 |  | 268 |  | 269 |  | 270
0
27 |  | 409.37 |  | 388.46 |  | 380.96 |  | 374.03 |  | 351.96 |  | 395.64 |  | 414.76 |  | 401.93 |  | 354.95 |  | 425..84 |  | 4 | 0 | 0 |  | COM
[7 empty] | F |  | F |  | F |  | F |  | U/P | [6 empty] | 1 | 0 | 0 |  | WIP
[22 empty] | 0 | 0 | 0 |  | ROW
| AP76 |  | 76/1 |  | 77/0 |  | 77/1 |  | 77/2 |  | 77/3 |  | 77/4 |  | 77/5 |  | AP78 |  | 78/1
| DC+00 |  | DA+06 |  | DB+00 |  | DA+00 |  | DA+03 |  | DA+00 |  | DA+03 |  | DA+06 |  | DC+00 |  | DA+03
[9 empty] | Benching | [5 empty] | CLEAR
| 271 |  | 272 |  | 273 |  | 274 |  | 275 |  | 276 |  | 277 |  | 278 |  | 279 |  | 280
0
28 |  | 415.03 |  | 351.18 |  | 441.06 |  | 387.5 |  | 372.63 |  | 415.3 |  | 424.58 |  | 391.7 |  | 410.47 |  | 385.54 |  | 0 | 0 | 0 |  | COM
[9 empty] | ROW |  | ROW |  | ROW |  | ROW |  | ROW |  | ROW |  |  | 0 | 0 | 0 |  | WIP
[19 empty] | U/P |  |  | 6 | 0 | 0 |  | ROW
| AP79 |  | 79/1 |  | 79/2 |  | AP80 |  | 80/1 |  | AP81 |  | 81/1 |  | 81/2 |  | 81/3 |  | 81/4
| DD+00 |  | DA+09 |  | DA+00 |  | DB+03 |  | DA+9 |  | DB+09 |  | DA+00 |  | DA+03 |  | DA+00 |  | DA+00
[5 empty] | Benching |  |  |  | Benching |  |  |  | Benching &RC
| 281 |  | 282 |  | 283 |  | 284 |  | 285 |  | 286 |  | 287 |  | 288 |  | 289 |  | 290
0
29 |  | 418.31 |  | 426.47 |  | 396.98 |  | 429.38 |  | 403.83 |  | 384.63 |  | 380.68 |  | 354.53 |  | 405.57 |  | 416.87 |  | 1 | 0 | 0 |  | COM
| ROW |  | ROW |  | ROW |  | ROW |  | ROW |  | F |  | ROW |  | ROW | [6 empty] | 0 | 0 | 0 |  | WIP
[22 empty] | 7 | 0 | 0 |  | ROW
| 81/5 |  | AP82 |  | 82/1 |  | 82/2 |  | AP83 |  | 83/1 |  | AP84 |  | AP85 |  | 85/1 |  | AP86
| DA+06 |  | DB+03 |  | DA+00 |  | DA+03 |  | DC+00 |  | DA+03 |  | DC+06 |  | DC+00 |  | DA+00 |  | DD+00
[17 empty] | CLEAR |  | CLEAR
| 291 |  | 292 |  | 293 |  | 294 |  | 295 |  | 296 |  | 297 |  | 298 |  | 299 |  | 300
0
30 |  | 380.77 |  | 411.81 |  | 432.08 |  | 256.87 |  | 412.4 |  | 382.17 |  | 452.74 |  | 420.21 |  | 395.01 |  | 386.74 |  | 0 | 0 | 0 |  | COM
| U/P | [20 empty] | 1 | 0 | 0 |  | WIP
[22 empty] | 0 | 0 | 0 |  | ROW
| 86/2 |  | AP87 |  | 87/1 |  | 87/2 |  | AP88 |  | AP89 |  | 89/1 |  | AP90 |  | 90/1 |  | AP91
| DA+00 |  | DC+00 |  | DA+03 |  | DA+09 |  | DC+00 |  | DC+00 |  | DA+09 |  | DC+00 |  | DA+09 |  | DD+00
CLEAR
| 301 |  | 302 |  | 303 |  | 304 |  | 305 |  | 306 |  | 307 |  | 308 |  | 309 |  | 310
0
31 |  | 378.62 |  | 350.22 |  | 357.91 |  | 237.48 |  | 440.03 |  | 504 |  | 430.57 |  | 415.06 |  | 430.39 |  | 414.36 |  | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
[22 empty] | 0 | 0 | 0 |  | ROW
| 91/1 |  | 91/2 |  | 91/3 |  | AP92 |  | AP93 |  | AP94 |  | AP95 |  | 95/1 |  | 95/2 |  | 95A/0
| DA+00 |  | DA+00 |  | DA+00 |  | DC+00 |  | DC+00 |  | DB+06 |  | DB+06 |  | DA+00 |  | DA+06 |  | DB+0
WIP CHECK SURVEY
| 311 |  | 312 |  | 313 |  | 314 |  | 315 |  | 316 |  | 317 |  | 318 |  | 319 |  | 320
0
32 |  | 419.38 |  | 406.18 |  | 427.47 |  | 416.77 |  | 378.13 |  | 358.57 |  | 360.52 |  | 324.53 |  | 354.92 |  | 406.11 |  | 0 | 0 | 0 |  | COM
| ROW | [20 empty] | 0 | 0 | 0 |  | WIP
[22 empty] | 0 | 0 | 0 |  | ROW
| 95A/1 |  | AP96 |  | 96/1 |  | AP97 |  | 97/1 |  | AP98 |  | AP98/1 |  | 98/2 |  | 98/3 |  | 98/4
| DA+00 |  | DC+00 |  | DA+00 |  | DC+00 |  | DA+03 |  | DC+00 |  | DA+00 |  | DA+00 |  | DA+00 |  | DA+00
| 321 |  | 322 |  | 323 |  | 324 |  | 325 |  | 326 |  | 327 |  | 328 |  | 329 |  | 330
|  | 357.82 |  | 424.78 |  | 414.36 |  | 413.59 |  | 432.24 |  | 397.06 |  | 426.06 |  | 417.12 |  | 364.36 |  | 332.45 | 3979.84 | [6 empty] | 3979.84
33 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 98/5 |  | AP99 |  | 99/1 |  | 99/2 |  | 99/3 |  | 99/4 |  | 99/5 |  | 99/6 |  | AP99A |  | 99A/1 |  |  | 0 | 0 | 0 |  | ROW
| DA+06 |  | DB+03 |  | DA+03 |  | DA+00 |  | DA+00 |  | DA+03 |  | DA+03 |  | DA+03 |  | DB+00 |  | DA+06
| 331 |  | 332 |  | 333 |  | 334 |  | 335 |  | 336 |  | 337 |  | 338 |  | 339 |  | 340
|  | 348.85 |  | 381.82 |  | 458.16 |  | 420.55 |  | 426.94 |  | 416.99 |  | 366.19 |  | 351 |  | 251.81 |  | 420 | 3842.31 | [6 empty] | 3842.31
34 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 99A/2 |  | 100/0 |  | 100/1 |  | 101/0 |  | 102/0 |  | 102/1 |  | 102/2 |  | 103/0 |  | 103/1 |  | 104/0 |  |  | 0 | 0 | 0 |  | ROW
| DA+00 |  | DC+06 |  | DD+03 |  | DD+3 |  | DD+3 |  | DA+06 |  | DA+06 |  | DC+0 |  | DA+00 |  | DD+0
| 341 |  | 342 |  | 343 |  | 344 |  | 345 |  | 346 |  | 347 |  | 348 |  | 349 |  | 350
|  | 425 |  | 420 |  | 367.44 |  | 398 |  | 370.48 |  | 437.33 |  | 447 |  | 394.62 |  | 388.49 |  | 440 | 44 | [6 empty] | 4088.36
35 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 104/1 |  | 104/2 |  | 104/3 |  | 105/0 |  | 105/1 |  | 106/0 |  | AP107 |  | 107/1 |  | AP108 |  | AP109 |  |  | 0 | 0 | 0 |  | ROW
| DA+03 |  | DA+09 |  | DA+03 |  | DD+00 |  | DA+3 |  | DC+06 |  | DD+03 |  | DA+9 |  | DC+00 |  | DC+03
| 351 |  | 352 |  | 353 |  | 354 |  | 355 |  | 356 |  | 357 |  | 358 |  | 359 |  | 360
|  | 227.51 |  | 279 |  | 365.62 |  | 217.72 |  | 378.38 |  | 295.12 |  | 390 |  | 428.04 |  | 384 |  | 398.62 | 3364.01 | [6 empty] | 3364.01
36 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 109/1 |  | 110/0 |  | 110/1 |  | AP111 |  | AP112 |  | AP113 |  | AP114 |  | 114/1 |  | AP115 |  | 115/1 |  |  | 0 | 0 | 0 |  | ROW
| DA+06 |  | DD+00 |  | DA+00 |  | DD+09 |  | DB+9 |  | DD+00 |  | DD+00 |  | DA+09 |  | DC+00 |  | DA+03
| 361 |  | 362 |  | 363 |  | 364 |  | 365 |  | 366 |  | 367 |  | 368 |  | 369 |  | 370
|  | 395 |  | 446.11 |  | 398 |  | 390 |  | 419.64 |  | 424.44 |  | 444 |  | 400 |  | 391.11 |  | 413 | 4121.3 | [6 empty] | 4121.3
37 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| AP116 |  | 116/1 |  | AP117 |  | 117/1 |  | 117/2 |  | AP118 |  | AP119 |  | 119/1 |  | 119/2 |  | AP120 |  |  | 0 | 0 | 0 |  | ROW
| DD+00 |  | DA+0 |  | DC+00 |  | DA+0 |  | DA+06 |  | DC+03 |  | DD+03 |  | DA+03 |  | DA+00 |  | DC+00
| 371 |  | 372 |  | 373 |  | 374 |  | 375 |  | 376 |  | 377 |  | 378 |  | 379 |  | 380
|  | 402.25 |  | 250.69 |  | 403 |  | 387 |  | 369.16 |  | 419.36 |  | 421.74 |  | 403 |  | 355 |  | 355 | 3766.2 | [6 empty] | 3766.2
38 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 120/1 |  | AP121 |  | AP122 |  | 122/1 |  | 122/2 |  | AP123 |  | AP124 |  | AP125 |  | 125/1 |  | 125/2 |  |  | 0 | 0 | 0 |  | ROW
| DA+06 |  | DD+00 |  | DC+03 |  | DA+03 |  | DA+03 |  | DC+00 |  | DC+03 |  | DC+03 |  | DA+00 |  | DA+00
| 381 |  | 382 |  | 383 |  | 384 |  | 385 |  | 386 |  | 387 |  | 388 |  | 389 |  | 390
|  | 373.77 |  | 364 |  | 421 |  | 334 |  | 388.22 |  | 398 |  | 442.51 |  | 415 |  | 417.97 |  | 439 | 3993.47 | [6 empty] | 3993.47
39 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 125/3 |  | AP126 |  | 126/1 |  | 126/2 |  | 126/3 |  | AP127 |  | 127/1 |  | AP128 |  | 128/1 |  | AP129 |  |  | 0 | 0 | 0 |  | ROW
| DA+00 |  | DC+00 |  | DA+06 |  | DA+03 |  | DA+06 |  | DD+06 |  | DA+09 |  | DC+03 |  | DA+06 |  | DC+00
| 391 |  | 392 |  | 393 |  | 394 |  | 395 |  | 396 |  | 397 |  | 398 |  | 399 |  | 400
|  | 406 |  | 406.21 |  | 260 |  | 267.27 |  | 395 |  | 408 |  | 352 |  | 373 |  | 367 |  | 384 | 3618.48 | [6 empty] | 3618.48
40 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 129/1 |  | 129/2 |  | AP130 |  | 130/1 |  | 131/0 |  | 131/1 |  | 131/2 |  | 132/0 |  | 132/1 |  | 132/2 |  |  | 0 | 0 | 0 |  | ROW
| DA+03 |  | DA+09 |  | DC+06 |  | DA+00 |  | DD+0 |  | DA+03 |  | DA+03 |  | DD+0 |  | DA+00 |  | DA+00
| 401 |  | 402 |  | 403 |  | 404 |  | 405 |  | 406 |  | 407 |  | 408 |  | 409 |  | 410
|  | 385 |  | 419.37 |  | 288 |  | 404 |  | 411 |  | 411 |  | 419 |  | 425 |  | 409 |  | 407 | 3978.37 | [6 empty] | 3978.37
41 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 132/3 |  | 132/4 |  | AP133 |  | 133/1 |  | 133/2 |  | 133/3 |  | 133/4 |  | 133/5 |  | 133/6 |  | 133/7 |  |  | 0 | 0 | 0 |  | ROW
| DA+00 |  | DA+00 |  | DC+00 |  | DA+00 |  | DA+00 |  | DA+03 |  | DA+03 |  | DA+03 |  | DA+03 |  | DA+00
| 411 |  | 412 |  | 413 |  | 414 |  | 415 |  | 416 |  | 417 |  | 418 |  | 419 |  | 420
|  | 389 |  | 399.98 |  | 408 |  | 405 |  | 418 |  | 425.34 |  | 392 |  | 397 |  | 420 |  | 425.56 | 4079.88 | [6 empty] | 4079.88
42 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 133/8 |  | 133/9 |  | AP134 |  | 134/1 |  | 134/2 |  | 134/3 |  | AP135 |  | 135/1 |  | 135/2 |  | 135/3 |  |  | 0 | 0 | 0 |  | ROW
| DA+03 |  | DA+03 |  | DB+00 |  | DA+03 |  | DA+00 |  | DA+06 |  | DC+00 |  | DA+00 |  | DA+03 |  | DA+06
| 421 |  | 422 |  | 423 |  | 424 |  | 425 |  | 426 |  | 427 |  | 428 |  | 429 |  | 430
|  | 356.03 |  | 426.82 |  | 381 |  | 334 |  | 347 |  | 375.55 |  | 382 |  | 417.97 |  | 390 |  | 407 | 3817.37 | [6 empty] | 3817.37
43 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| AP136 |  | AP137 |  | AP138 |  | 138/1 |  | 138/2 |  | 138/3 |  | AP139 |  | 139/1 |  | AP140 |  | 140/1 |  |  | 0 | 0 | 0 |  | ROW
| DD+00 |  | DB+03 |  | DB+03 |  | DA+00 |  | DA+00 |  | DA+00 |  | DC+03 |  | DA+09 |  | DB+00 |  | DA+03
| 431 |  | 432 |  | 433 |  | 434 |  | 435 |  | 436 |  | 437 |  | 438 |  | 439 |  | 440
|  | 433 |  | 380.33 |  | 386 |  | 391 |  | 399.83 |  | 437.01 |  | 423 |  | 395 |  | 417 |  | 399 | 4061.17 | [6 empty] | 4061.17
44 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 140/2 |  | 140/3 |  | AP141 |  | 141/1 |  | 141/2 |  | AP142 |  | AP143 |  | 143/1 |  | 143/2 |  | 143/3 |  |  | 0 | 0 | 0 |  | ROW
| DA+03 |  | DA+03 |  | DC+00 |  | DA+00 |  | DA+06 |  | DC+03 |  | DC+03 |  | DA+03 |  | DA+00 |  | DA+03
| 441 |  | 442 |  | 443 |  | 444 |  | 445 |  | 446 |  | 447 |  | 448 |  | 449 |  | 450
|  | 420 |  | 409 |  | 412 |  | 400.41 |  | 232.12 |  | 442 |  | 385 |  | 362 |  | 399 |  | 382.07 | 3843.6 | [6 empty] | 3843.6
45 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 143/4 |  | 143/5 |  | 143/6 |  | 143/7 |  | AP144 |  | AP145 |  | 145/1 |  | 145/2 |  | 145/3 |  | 145/4 |  |  | 0 | 0 | 0 |  | ROW
| DA+03 |  | DA+03 |  | DA+00 |  | DA+03 |  | DD+06 |  | DD+06 |  | DA+03 |  | DA+00 |  | DA+00 |  | DA+03
| 451 |  | 452 |  | 453 |  | 454 |  | 455 |  | 456 |  | 457 |  | 458 |  | 459 |  | 460
|  | 392 |  | 422 |  | 409.46 |  | 402 |  | 409 |  | 404 |  | 394 |  | 423 |  | 421 |  | 411 | 4087.46 | [6 empty] | 4087.46
46 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| AP146 |  | 146/1 |  | 146/2 |  | 147/0 |  | 147/1 |  | 147/2 |  | 147/3 |  | 147/4 |  | 147/5 |  | 147/6 |  |  | 0 | 0 | 0 |  | ROW
| DC+00 |  | DA+03 |  | DA+00 |  | DC+00 |  | DA+03 |  | DA+00 |  | DA+03 |  | DA+03 |  | DA+03 |  | DA+03
| 461 |  | 462 |  | 463 |  | 464 |  | 465 |  | 466 |  | 467 |  | 468 |  | 469 |  | 470
|  | 429 |  | 373.37 |  | 403 |  | 402 |  | 387 |  | 386 |  | 413 |  | 407 |  | 390 |  | 392 | 3982.37 | [6 empty] | 3982.37
47 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 147/7 |  | 147/8 |  | 148/0 |  | 148/1 |  | 148/2 |  | 148/3 |  | 148/4 |  | 148/5 |  | 148/6 |  | 148/7 |  |  | 0 | 0 | 0 |  | ROW
| DA+00 |  | DA+09 |  | DB+00 |  | DA+03 |  | DA+00 |  | DA+00 |  | DA+00 |  | DA+03 |  | DA+00 |  | DA+00
| 471 |  | 472 |  | 473 |  | 474 |  | 475 |  | 476 |  | 477 |  | 478 |  | 479 |  | 480
|  | 415 |  | 407.99 |  | 420 |  | 404 |  | 440.94 |  | 249.42 |  | 415.86 |  | 278.87 |  | 426.84 |  | 286.02 | 3744.94 | [6 empty] | 3744.94
48 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| 148/8 |  | 148/9 |  | AP149 |  | 149/1 |  | 149/2 |  | AP150 |  | AP151 |  | AP152 |  | AP153 |  | 153/1 |  |  | 0 | 0 | 0 |  | ROW
| DA+00 |  | DA+03 |  | DB+00 |  | DA+03 |  | DCT+00 |  | DD+09 |  | DD+09 |  | DD+18 |  | DD+18 |  | DB+09
| 481 |  | 482 |  | 483 |  | 484 |  | 485
|  | 220.25 |  | 241.31 |  | 214.9 |  | 113.74 | [12 empty] | 790.2 | [6 empty] | 790.2
49 | [21 empty] | 0 | 0 | 0 |  | COM
[22 empty] | 0 | 0 | 0 |  | WIP
| AP154 |  | AP155 |  | AP156 |  | AP157 |  | GE | [12 empty] | 0 | 0 | 0 |  | ROW
| DD+30 |  | DD+30 |  | DD+09 |  | DD+00
131357.41
[28 empty] | 131.3574 | 54.6426
[22 empty] | 11 | FDN COM |  | TE COM |  | STR COM
|  |  |  | Crossing Type | 110kV | 230kV | 400kV | 320kV | 765kV | NH-Xing | Railway Xing | Total | Remarks | [8 empty] | 4 | FDN WIP |  | TE WIP |  | STR WIP
|  |  |  | Total Nos | 4 | 3 |  |  |  | 2 | 1 | 10 | [9 empty] | 13 | FDN ROW |  | TE ROW |  | STR ROW
Completed
|  |  |  | Balance | 4 | 3 | 0 | 0 | 0 | 2 | 1 | 10 | [9 empty] | 3 | Earthing COM |  | Tackwelding COM
[5 empty] | Nos | CMP | WIP | Balance | Kms | CMP | WIP | Balance | Remarks
TSE
Manual
Total
Paying out/ Rough sag
[11 empty] | Tack welding completed | [5 empty] | Erection ROW
Erection Completed ------>
|  | Foundation completed ----> | [8 empty] | <------Insulator hosting
|  | Earthing completed -----> |  |  |  |  | U/P | [9 empty] | Erection Cleared
Road
[7 empty] | 325 | Span
[12 empty] | HT-D/C Power Line Crossing |  |  |  |  | Cart Track
| Transformer |  |  | ROW | ROW |  |  | Water Tank
| Temple |  |  | A+0 | Tower Type |  |  | LT Power Line Crossing |  |  |  | HT-S/C Power Line Crossing |  |  |  |  | Broad Gauge Railway
[8 empty] | 11 KV Line Crossing | [8 empty] | Line Crossing
| Hut |  |  | 1/0 | Location No. |  |  | 33 KV Line Crossing
| Bore & Handpump |  |  |  | Minor River Crossing | [6 empty] | Forest Stretch |  |  |  |  | SH Crossing
| Oil Pipe Line |  |  | RC | Raised Chimney |  |  | Major River Crossing |  |  |  | NH Crossing |  |  |  |  | Wild Life Sanctuary
2
2
2
2
2
2
3
2
3
2
2
2
3
3
2
2
3

## ROW (hidden)
NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE
Client : RAJASTHAN IV A POWER TRANSMISSION LTD.
CONTRACTOR : KEC INTERNATIONAL LIMITED
FOUNDATION STATUS
SL. No. | Location Number | Span | Tower Type | AS PER RAPTL ROW CLEARED ON | WORK COMMENCED KEC | STATUS
1 | 80/0
2 | 66/4 |  |  |  | ROW
3 | 89/1 |  |  |  | ROW
4 | 102/1
5 | 102/2 |  |  |  | Anjana Const |  | Previous Loc Done 99/2 on 25/4/2025
6 | 107/1
7 | 90/1 |  |  |  | ROW
8 | 81/1
9 | 51/1
10 | 99A/2
11 | 61/1
12 | 72/2
13 | 73/1
14 | 99/5
15 | 56/2
16 | 63/1
17 | 114/1
18 | 116/1
19 | 56/1
20 | 99A/2
21 | 73/1
22 | 63/1
23 | 114/1
24 | 56/1
25 | 125/2
26 | 84/0
27 | 85/0
28 | 86/0
29 | 110/0
30 | 113A/0
31 | 147/1
32 | 147/7

## June (hidden)
Sl No | Loc No | TOT | Classification | Starting Date | Completion
1 | 81/3 | DA+0 | Sandy | 2025-05-22 | 2025-06-04
2 | 120/1 | DA+6 | Sandy | 2025-05-30 | 2025-06-05
3 | 96/0 | DC+0 | DFR | 2025-05-28 | 2025-06-06
4 | 75/0 | DC+0 | Sandy | 2025-06-01 | 2025-06-07
5 | 147/2 | DA+0 | Sandy | 2025-06-02 | 2025-06-08
6 | 82/2 | DA+0 | Sandy | 2025-06-02 | 2025-06-10
7 | 79/0 | DD+0 | Sandy | 2025-08-08 | 2025-06-12
8 | 147/5 | DA+0 | Sandy | 2025-06-04 | 2025-06-12
9 | 119/0 | DD+3 | Sandy | 2025-06-05 | 2025-06-15
10 | 82/1 | DA+6 | Sandy | 2025-06-10 | 2025-06-15
11 | 147/0 | DC+0 | Sandy | 2025-06-08 | 2025-06-15
12 | 78/0 | DC+0 | Sandy | 2025-06-13 | 2025-06-16
13 | 147/4 | DA+0 | Sandy | 2025-06-13 | 2025-06-16
14 | 74/0 | DB+9 | Sandy | 2025-06-16 | 2025-06-20
15 | 147/1 | DA+0 | Sandy | 2025-06-15 | 2025-06-21
16 | 147/7 | DA+0 | Sandy | 2025-06-15 | 2025-06-22
17 | 95A/0 | DB+0 | DFR | 2025-06-16 | 2025-06-23
18 | 146/2 | DA+0 | Sandy | 2025-06-22 | 2025-06-25
19 | 147/3 | DA+0 | Sandy | 2025-06-22 | 2025-06-25
20 | 73/0 | DB+0 | Sandy | 2025-06-20 | 2025-06-26
21 | 86/0 | DD+0 | Sandy | 2025-06-17 | 2025-06-27
22 | 72/2 | DA+3 | DFR | 2025-06-25 | 2025-06-30
23 | 114/0 | DC+0 | Sandy | 2025-06-10 | 2025-06-30
24 | 146/1 | DA+3 | Sandy | 2025-06-25 | 2025-06-30
25 | 147/8 | DA+0 | Sandy | 2025-06-25 | 2025-06-30

## Foundation
NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE
Client : RAJASTHAN IV A POWER TRANSMISSION LTD.
CONTRACTOR : KEC INTERNATIONAL LIMITED
FOUNDATION STATUS
SL. No. | Location Number | Span |  | Tower Type | M10 | M20 | Excavation | Reinforcement | Stub | RC | Foundation type
|  |  | LI / LO | [8 empty] | Starting date | Completion Date | Agency | Remark | Remarks
1 | 7/0 |  | LI | DE+9 (Aux. X-arm) | [6 empty] | DFR | 2026-02-06 | 2026-02-11 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
2 | 1/1 |  | LO | DA-3 | [6 empty] | DFR | 2026-02-11 | 2026-02-14 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
3 | 6/2 |  | LI | DA+0 | [6 empty] | DFR | 2026-02-12 | 2026-02-16 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
4 | 1/2 |  | LO | DA-3 | [6 empty] | DFR | 2026-02-15 | 2026-02-18 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
5 | 6/1 |  | LI | DA+0 | [6 empty] | DFR | 2026-02-17 | 2026-02-20 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
6 | 1/0 |  | LO | DE+3 | [6 empty] | DFR | 2026-02-11 | 2026-02-28 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
7 | 6/0 |  | Li | DD45+0 | [6 empty] | DFR | 2026-02-19 | 2026-02-28 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done | 185
8 | 2/1 |  | LO | DA+0 | [6 empty] | DFR | 08-03-226 | 2026-03-11 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
9 | 2/0 |  | LO | DC1+0 | [6 empty] | DFR | 2026-02-28 | 2026-03-13 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done | 5
10 | 2/2 |  | LO | DA-3 | [6 empty] | DFR | 2026-03-12 | 2026-03-15 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
11 | 2/3 |  | LO | DA+0 | [6 empty] | DFR | 2026-03-13 | 2026-03-16 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
12 | 2/4 |  | LO | DA+3 | [6 empty] | DFR | 2026-03-15 | 2026-03-17 | Karni Mata Construction Company |  | RCC Complete, Backfilling Done
13 | 1/0 |  | LI | DD60+0 | [6 empty] | DFR | 2026-03-10 |  | Karni Mata Construction Company |  | A & C frustum B & D chimney Next A, C Chimney
14 | 5/2 |  | LI | DA+0 | [6 empty] | DFR | 2026-03-20 |  | Karni Mata Construction Company |  | Exacavation WIP
15 | 7/0 |  | LO | DD60+0 | [6 empty] | DFR | 2026-03-20 |  | Karni Mata Construction Company |  | Prop set WIP Next: PCC, Steel Binding

## Royalty (hidden)
OM Construction
Loc No | TOT | M-10 | M-20
120/1 | DA+6 | 1.86 | 12.47 |  |  |  | 75/0 | DC+0 | 1.6 | 13.13
119/0 | DD+3 | 2.93 | 20.34 |  |  |  | 79/0 | DD+0 | 2.93 | 20.34
| CUM | 4.79 | 32.81 |  |  | ROYALTY ISSUED | 78/0 | DC+0 | 1.6 | 13.13
CUM | 20MM | 4.426 | 27.5604 | 31.9864 |  | 20MM | 74/0 | DB+9 | 1.68 | 12.41
CUM | SAND | 2.0448 | 11.5754 | 13.6202 |  | 18.48 | 73/0 | DB+0 | 1.68 | 12.41
MT | 20MM |  |  | 51.1782 | Required | 14.67 | 72/2 | DA+3 | 1.86 | 12.47
MT | SAND |  |  | 21.7923 | Required | 33.15 |  |  | 11.35 | 83.89
[7 empty] | CUM | 20MM | 10.4874 | 70.4676 | 80.955
[7 empty] | CUM | SAND | 4.8452 | 29.5964 | 34.4416
77/1 | DA+0 | 1.57 | 11.05 |  |  |  | MT | 20MM |  |  | 129.528
77/4 | DA+3 | 1.86 | 12.47 |  |  |  | MT | SAND |  |  | 55.1065
79/1 | DA+9 | 1.86 | 12.47
76/1 | DA+6 | 1.86 | 12.47
85/1 | DA+0 | 1.57 | 11.05 |  |  |  | JP Enterprises
87/1 | DA+3 | 1.86 | 12.47 |  |  |  |  | 147/2 | DA+0 | 1.57 | 11.05
87/2 | DA+9 | 1.86 | 12.47 |  |  |  |  | 147/0 | DC+0 | 1.6 | 13.13
91/1 | DA+0 | 1.57 | 11.05 |  |  |  |  | 147/1 | DA+0 | 1.57 | 11.05
91/2 | DA+0 | 1.57 | 11.05 |  |  |  |  | 146/2 | DA+0 | 1.57 | 11.05
99/2 | DA+0 | 1.08 | 8.68 |  |  |  |  | 146/1 | DA+3 | 1.86 | 12.47
97/0 | DC+0 | 1.6 | 13.13 | [6 empty] | 8.17 | 58.75
82/2 | DA+0 | 1.57 | 11.05 |  |  |  |  | CUM | 20MM | 7.5491 | 49.35 | 56.8991
82/1 | DA+6 | 1.86 | 12.47 |  |  |  |  | CUM | SAND | 3.4877 | 20.727 | 24.2147
86/0 | DD+0 | 2.93 | 20.34 |  |  |  |  | MT | 20MM |  |  | 91.0385
85/0 | DC+0 | 1.6 | 13.13 |  |  |  |  | MT | SAND |  |  | 38.7435
|  | 26.22 | 185.35 | [9 empty] | Balance
CUM | 20MM | 24.2273 | 155.694 | 179.9213 |  |  | Submitted | MT | 20MM |  |  | 68.58 | 22.4585
CUM | SAND | 11.193 | 65.3915 | 76.5845
MT | 20MM |  |  | 287.874
MT | SAND |  |  | 122.5352

## Sheet14 (hidden)
1 | 95/1 | DB+0 |  | DFR | 2025-06-23 | 2025-07-04 | Baba Ramdev Construction | RCC Complete, Backfilling Done
2 | 148/3 | DA+0 |  | Sandy | 2025-06-27 | 2025-07-05 | AR Patel | RCC Complete, Backfilling Done
3 | 106/0 | DC+6 |  | Sandy | 2025-06-25 | 2025-07-06 | Mundhan Trading Company | RCC Complete, Backfilling Done
4 | 148/1 | DA+0 |  | Sandy | 2025-07-04 | 2025-07-08 | AR Patel | RCC Complete, Backfilling Done
5 | 146/0 | DC+0 |  | Sandy | 2025-07-03 | 2025-07-08 | JP Enterprises | RCC Complete, Backfilling Done
6 | 80/0 | DB+3 | 1MRC | Sandy | 2025-06-28 | 2025-07-10 | Mahadev Enterprises | RCC Complete, Backfilling Done
7 | 114/1 | DA+9 |  | Sandy | 2025-07-04 | 2025-07-10 | Goswami and Company | RCC Complete, Backfilling Done
8 | 148/2 | DA+0 |  | Sandy | 2025-07-07 | 2025-07-10 | AR Patel | RCC Complete, Backfilling Done
9 | 95/0 | DB+6 |  | Sandy | 2025-06-27 | 2025-07-11 | Baba Ramdev Construction | RCC Complete, Backfilling Done
10 | 141/1 | DA+0 |  | Sandy | 2025-07-07 | 2025-07-11 | Mahadev Construction | RCC Complete, Backfilling Done
11 | 148/4 | DA+0 |  | Sandy | 2025-07-10 | 2025-07-12 | AR Patel | RCC Complete, Backfilling Done
12 | 141/2 | DA+6 |  | Sandy | 2025-07-09 | 2025-07-13 | Mahadev Construction | RCC Complete, Backfilling Done
13 | 145/4 | DA+3 |  | Sandy | 2025-07-09 | 2025-07-13 | JP Enterprises | RCC Complete, Backfilling Done
14 | 133/6 | DA+3 |  | Sandy | 2025-07-10 | 2025-07-14 | OM Construction | RCC Complete, Backfilling Done
15 | 125/1 | DA+0 |  | Sandy | 2025-07-04 | 2025-07-14 | Instance Wave Pvt Ltd | RCC Complete, Backfilling Done
16 | 148/5 | DA+0 |  | Sandy | 2025-07-13 | 2025-07-15 | AR Patel | RCC Complete, Backfilling Done
17 | 109A/0 | DB+6 |  | Sandy | 2025-07-09 | 2025-07-16 | Mundhan Construction | RCC Complete, Backfilling Done
18 | 113A/0 | DC+0 |  | Sandy | 2025-07-08 | 2025-07-16 | Goswami and Company-1 | RCC Complete, Backfilling Done
19 | 133/5 | DA+0 |  | Sandy | 2025-07-14 | 2025-07-16 | OM Construction | RCC Complete, Backfilling Done
20 | 145/2 | DA+0 |  | Sandy | 2025-07-14 | 2025-07-16 | JP Enterprises | RCC Complete, Backfilling Done
21 | 142/0 | DC+3 |  | Sandy | 2025-07-12 | 2025-07-17 | Mahadev Construction | RCC Complete, Backfilling Done
22 | 115/0 | DC+0,1MRC |  | Sandy | 2025-07-10 | 2025-07-18 | Goswami and Company-2 | RCC Complete, Backfilling Done
23 | 148/6 | DA+0 |  | Sandy | 2025-07-15 | 2025-07-18 | AR Patel | RCC Complete, Backfilling Done
24 | 77/0 | DB+0 |  | Sandy | 2025-07-08 | 2025-07-19 | Godara Enterprises | RCC Complete, Backfilling Done
25 | 133/4 | DA+0 |  | Sandy | 2025-07-17 | 2025-07-21 | OM Construction | RCC Complete, Backfilling Done
26 | 143/0 | DC+3 |  | Sandy | 2025-07-17 | 2025-07-21 | Mahadev Construction | RCC Complete, Backfilling Done
27 | 145/1 | DA+3 |  | Sandy | 2025-07-16 | 2025-07-21 | JP Enterprises | RCC Complete, Backfilling Done
28 | 148/7 | DA+0 |  | Sandy | 2025-07-19 | 2025-07-23 | AR Patel | RCC Complete, Backfilling Done
29 | 125/0 | DC+3 |  | Sandy | 2025-07-15 | 2025-07-24 | Instance Wave Pvt Ltd | RCC Complete, Backfilling Done
30 | 94/0 | DB+6 |  | Sandy | 2025-07-13 | 2025-07-24 | Baba Ramdev Construction | RCC Complete, Backfilling Done
31 | 133/3 | DA+0 |  | Sandy | 2025-07-22 | 2025-07-24 | OM Construction | RCC Complete, Backfilling Done
32 | 145/3 | DA+0 |  | Sandy | 2025-07-22 | 2025-07-25 | JP Enterprises | RCC Complete, Backfilling Done
33 | 126/2 | DA+3 |  | Sandy | 2025-07-15 | 2025-07-26 | MS Construction | RCC Complete, Backfilling Done
34 | 143/3 | DA+3 |  | Sandy | 2025-07-22 | 2025-07-26 | Mahadev Construction | RCC Complete, Backfilling Done
35 | 79/2 | DA+0 |  | Sandy | 2025-07-11 | 2025-07-27 | Mahadev Enterprises | RCC Complete, Backfilling Done
36 | 133/8 | DA+6 |  | Sandy | 2025-07-24 | 2025-07-27 | OM Construction | RCC Complete, Backfilling Done
37 | 149B/1 | DA+3 |  | Sandy | 2025-07-24 | 2025-07-27 | AR Patel | RCC Complete, Backfilling Done
38 | 110/0 | DC+0 |  | Sandy | 2025-07-21 | 2025-07-28 | Mundhan Construction | RCC Complete, Backfilling Done
39 | 99/3 | DA+3 |  | Sandy | 2025-07-13 | 2025-07-29 | Anjana Construction | RCC Complete, Backfilling Done
40 | 143/1 | DA+3 |  | Sandy | 2025-07-25 | 2025-07-29 | Mahadev Construction | RCC Complete, Backfilling Done
41 | 133/1 | DA+0 |  | Sandy | 2025-07-27 | 2025-07-30 | OM Construction | RCC Complete, Backfilling Done
42 | 149B/2 | DA+0 |  | Sandy | 2025-07-27 | 2025-07-30 | AR Patel | RCC Complete, Backfilling Done
43 | 145/0 | DD+6 |  | Sandy | 2025-07-25 | 2025-07-31 | JP Enterprises | RCC Complete, Backfilling Done
44 | 143/6 | DA+0 |  | Sandy | 2025-07-29 | 2025-07-31 | Mahadev Construction | RCC Complete, Backfilling Done
45 | 133/7 | DA+0 |  | Sandy | 2025-07-30 | 2025-07-31 | OM Construction | RCC Complete, Backfilling Done
46 | 129/1 | DA+9 |  | Sandy | 2025-07-25 | 2025-07-31 | Instance Wave Pvt Ltd | RCC Complete, Backfilling Done
47 | 111/0 | DB+9,3MRC |  | Sandy | 2025-07-17 | 2025-07-31 | Goswami and Company-1 | RCC Complete, Backfilling Done
48 | 98B/0 | DD+0 |  | DFR | 2025-06-10 | 2025-07-31 | Anajana Construction | RCC Complete, Backfilling Done
49 | 76/0 | DC+0 |  | Sandy | 2025-07-24 | 2025-07-31 | Baba Ramdev Construction | RCC Complete, Backfilling Done
50 | 116/0 | DD+0 |  | Sandy | 2025-07-23 | 2025-07-31 | Goswami and Company-2 | RCC Complete, Backfilling Done

## Sheet7 (hidden)
SL | Loc | TOT | Gang | Starting Date | Completion
1 | 148/3 | DA+0 | Gokul Sarkar | 2025-08-29 | 2025-09-04 | Completed
2 | 81/2 | DA+3 | Dipak | 2025-09-01 | 2025-09-05 | Completed
3 | 145/1 | DA+3 | Ayansh Const | 2025-08-27 | 2025-09-09 | Completed
4 | 81/4 | DA+0 | Dipak | 2025-09-05 | 2025-09-09 | Completed
5 | 148/2 | DA+0 | Gokul Sarkar | 2025-09-05 | 2025-09-10 | Completed
6 | 83/1 | DA+3 | Ahmed Construction | 2025-08-29 | 2025-09-11 | Completed
7 | 97/0 | DC+0 | Ajay Kumar1 | 2025-09-01 | 2025-09-11 | Completed
8 | 148/5 | DA+0 | Gokul Sarkar | 2025-09-11 | 2025-09-14 | Completed
9 | 145/2 | DA+0 | Ayansh Const | 2025-09-09 | 2025-09-14 | Completed
10 | 82/1 | DA+6 | Dipak | 2025-09-09 | 2025-09-14 | Completed
11 | 96/1 | DA+0 | Ajay Kumar1 | 2025-09-01 | 2025-09-15 | Completed
12 | 79/2 | DA+0 | Ahmed Construction | 2025-09-11 | 2025-09-15 | Completed
13 | 133/2 | DA+0 | Windbridge Energy | 2025-08-28 | 2025-09-16 | Completed
14 | 148/6 | DA+0 | Gokul Sarkar | 2025-09-14 | 2025-09-19 | Completed
15 | 145/3 | DA+0 | Ayansh Const | 2025-09-14 | 2025-09-19 | Completed
16 | 143/5 | DA+3 | Prayag Saw1 | 2025-09-11 | 2025-09-17 | Completed
17 | 143/4 | DA+3 | Prayag Saw2 | 2025-09-11 | 2025-09-17 | Completed
18 | 143/2 | DA+0 | Prayag Saw1 | 2025-09-18 | 2025-09-20 | Completed
19 | 143/6 | DA+0 | Prayag Saw2 | 2025-09-18 | 2025-09-20 | Completed
20 | 97/1 | DA+3 | Ajay Kumar2 | 2025-09-11 | 2025-09-21 | Completed
21 | 113A/0 | DC+0 | Dipak | 2025-09-14 | 2025-09-21 | Completed
22 | 133/3 | DA+0 | Windbridge Energy | 2025-09-17 | 2025-09-22 | Completed
23 | 143/3 | DA+3 | Prayag Saw1 | 2025-09-21 | 2025-09-23 | Completed
24 | 143/7 | DA+6 | Prayag Saw2 | 2025-09-21 | 2025-09-23 | Completed
25 | 148/7 | DA+0 | Gokul Sarkar | 2025-09-20 | 2025-09-23 | Completed
26 | 98/1 | DA+0 | Ajay Kumar1 | 2025-09-15 | 2025-09-24 | Completed
27 | 114/1 | DA+9 | Dipak | 2025-09-24 | 2025-09-26 | Completed
28 | 143/1 | DA+6 | Prayag Saw2 | 2025-09-22 | 2025-09-27 | Completed
29 | 141/2 | DA+6 | Prayag Saw1 | 2025-09-24 | 2025-09-27 | Completed
30 | 149B/1 | DA+3 | Gokul Sarkar | 2025-09-24 | 2025-09-27 | Completed

## Project Details
Project Code | Project Name | Client Name | LOA Start Date | LOA End Date | Planning Engineer | PCH | Regional Manager | Project Manger | Section Incharge | Supervisor/Engineer
TB 507 | 400kV D/C Fatehgarh IV (Section-2)PS - Bhinmal (PG) Transmission Line | RAJASTHAN IV A POWER TRANSMISSION LTD | 2024-12-06 | 2026-06-05 | Amartya sarkar | Sanjay Kr Gupta |  | ALOK SINHA | ALOK JANA VARUN TYAGI

## Erection (hidden)
NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE
Client : RAJASTHAN IV A POWER TRANSMISSION LTD.
CONTRACTOR : KEC INTERNATIONAL LIMITED
SL. No. | Location No. | Tower Type | Tower Weight | Gang Name | Starting Date | Completion Date | Remarks
1 | 77/2 | DA+3 | 11.145 | Dipak | 2025-06-23 | 2025-06-28 | Completed
2 | 77/4 | DA+3 | 11.997 | Dipak | 2025-06-28 | 2025-07-02 | Completed
3 | 75/7 | DA+0 | 11.145 | Srikarni | 2025-06-29 | 2025-07-05 | Completed
4 | 77/5 | DA+6 | 13.072 | Dipak | 2025-07-03 | 2025-07-05 | Completed
5 | 77/3 | DA+0 | 11.145 | Dipak | 2025-07-07 | 2025-07-10 | Completed
6 | 77/1 | DA+0 | 11.145 | Dipak | 2025-07-11 | 2025-07-14 | Completed |  |  |  |  | 185
7 | 75/6 | DA+0 | 11.145 | Dipak | 2025-07-15 | 2025-07-18 | Completed
8 | 75/5 | DA+0 | 11.145 | Dipak | 2025-07-19 | 2025-07-22 | Completed |  |  | 90 |  | 24
9 | 75/4 | DA+0 | 11.145 | Dipak | 2025-07-22 | 2025-07-25 | Completed
10 | 75/3 | DA+3 | 11.997 | Dipak | 2025-07-25 | 2025-07-28 | Completed
11 | 75/2 | DA+0 | 11.145 | Dipak | 2025-07-29 | 2025-07-31 | Completed
12 | 74/1 | DA+0 | 11.145 | Ahmed Construction | 2025-07-24 | 2025-07-31 | Completed
13 | 75/1 | DA+0 | 11.145 | Dipak | 2025-08-01 | 2025-08-04 | Completed |  | 41
14 | 73/3 | DA+9 | 13.958 | Ahmed Construction | 2025-08-01 | 2025-08-08 | Completed
15 | 75/0 | DC+0 | 18.727 | Dipak | 2025-08-04 | 2025-08-09 | Completed
16 | 73/2 | DA+9 | 13.958 | Ahmed Construction | 2025-08-08 | 2025-08-16 | Completed
17 | 78/0 | DC+0 | 18.727 | Dipak | 2025-08-10 | 2025-08-16 | Completed
18 | 85/1 | DA+0 | 11.145 | Ahmed Construction | 2025-08-17 | 2025-08-23 | Completed
19 | 79/0 | DD+0 | 21.41 | Dipak | 2025-08-17 | 2025-08-23 | Completed
20 | 86/1 | DA+6 | 13.072 | Ahmed Construction | 2025-08-23 | 2025-08-28 | Completed
21 | 80/1 | DA+9 | 13.958 | Dipak | 2025-08-23 | 2025-08-28 | Completed
22 | 148/4 | DA+0 | 11.145 | Gokul Sarkar | 2025-08-27 | 2025-08-29 | Completed
23 | 95A/1 | DA+0 | 11.145 | Ajay Kumar | 2025-08-23 | 2025-08-31 | Completed
24 | 81/3 | DA+0 | 11.145 | Dipak | 2025-08-29 | 2025-08-31 | Completed
25 | 148/3 | DA+0 | 11.145 | Gokul Sarkar | 2025-08-29 | 2025-09-04 | Completed
26 | 81/2 | DA+3 | 11.997 | Dipak | 2025-09-01 | 2025-09-05 | Completed
27 | 145/1 | DA+3 | 11.997 | Ayansh Const | 2025-08-27 | 2025-09-09 | Completed
28 | 81/4 | DA+0 | 11.145 | Dipak | 2025-09-05 | 2025-09-09 | Completed | 148/1 | HOLD
29 | 148/2 | DA+0 | 11.145 | Gokul Sarkar | 2025-09-05 | 2025-09-10 | Completed
30 | 83/1 | DA+3 | 11.997 | Ahmed Construction | 2025-08-29 | 2025-09-11 | Completed
31 | 97/0 | DC+0 | 18.727 | Ajay Kumar1 | 2025-09-01 | 2025-09-11 | Completed
32 | 148/5 | DA+0 | 11.145 | Gokul Sarkar | 2025-09-11 | 2025-09-14 | Completed
33 | 145/2 | DA+0 | 11.145 | Ayansh Const | 2025-09-09 | 2025-09-14 | Completed
34 | 82/1 | DA+6 | 13.072 | Dipak | 2025-09-09 | 2025-09-14 | Completed |  | 113/0,DC+0
35 | 96/1 | DA+0 | 11.145 | Ajay Kumar1 | 2025-09-01 | 2025-09-15 | Completed
36 | 79/2 | DA+0 | 11.145 | Ahmed Construction | 2025-09-11 | 2025-09-15 | Completed | 133/3
37 | 133/2 | DA+0 | 11.145 | Bhoi Enterprises | 2025-08-28 | 2025-09-16 | Completed
38 | 148/6 | DA+0 | 11.145 | Gokul Sarkar | 2025-09-14 | 2025-09-19 | Completed | 148/7
39 | 145/3 | DA+0 | 11.145 | Ayansh Const | 2025-09-14 | 2025-09-19 | Completed | 145/4
40 | 143/5 | DA+3 | 11.997 | Prayag Saw1 | 2025-09-11 | 2025-09-17 | Completed
41 | 143/4 | DA+3 | 11.997 | Prayag Saw2 | 2025-09-11 | 2025-09-17 | Completed | 143/2
42 | 143/2 | DA+0 | 11.145 | Prayag Saw1 | 2025-09-18 | 2025-09-20 | Completed | 143/3 | 143/1
43 | 143/6 | DA+0 | 11.145 | Prayag Saw2 | 2025-09-18 | 2025-09-20 | Completed | 143/7
44 | 97/1 | DA+3 | 11.997 | Ajay Kumar2 | 2025-09-11 | 2025-09-21 | Completed | 98A/1
45 | 113A/0 | DC+0 | 18.727 | Dipak | 2025-09-14 | 2025-09-21 | Completed
46 | 133/3 | DA+0 | 11.145 | Bhoi Enterprises | 2025-09-17 | 2025-09-22 | Completed |  |  |  | 79/1 | 64/3
47 | 143/3 | DA+3 | 11.997 | Prayag Saw1 | 2025-09-21 | 2025-09-23 | Completed | 98/0 | ROW | 98A/1
48 | 143/7 | DA+6 | 13.072 | Prayag Saw2 | 2025-09-21 | 2025-09-23 | Completed
49 | 148/7 | DA+0 | 11.145 | Gokul Sarkar | 2025-09-20 | 2025-09-23 | Completed
50 | 98/1 | DA+0 | 11.145 | Ajay Kumar1 | 2025-09-15 | 2025-09-24 | Completed | 115/0,116/1,114/0,112/1,111/0
51 | 114/1 | DA+9 | 13.958 | Dipak | 2025-09-24 | 2025-09-26 | Completed | 96/2 | 2025-09-15 | 76/0 | 98A/0
52 | 143/1 | DA+6 | 13.072 | Prayag Saw2 | 2025-09-22 | 2025-09-27 | Completed
53 | 141/2 | DA+6 | 13.072 | Prayag Saw1 | 2025-09-24 | 2025-09-27 | Completed
54 | 149B/1 | DA+3 | 11.997 | Gokul Sarkar | 2025-09-24 | 2025-09-27 | Completed
55 | 76/1 | DA+6 | 13.072 | Ahmed Construction | 2025-09-19 | 2025-09-27 | Completed
56 | 116/1 | DA+0 | 11.145 | Dipak | 2025-09-27 | 2025-09-29 | Completed | [5 empty] | 2025-09-29
57 | 133/6 | DA+3 | 11.997 | Bhoi Enterprises | 2025-09-23 | 2025-09-29 | Completed | [5 empty] | 2025-09-30 | 133/7
58 | 149B/2 | DA+0 | 11.145 | Gokul Sarkar | 2025-09-27 | 2025-09-30 | Completed | [5 empty] | 2025-09-29 | 147/7 | 147/8 | 149/0 | 149A/0
59 | 145/4 | DA+3 | 11.997 | Pritam Enterprises | 2025-09-20 | 2025-09-30 | Completed | [5 empty] | 2025-09-29 | 146/1
60 | 141/1 | DA+0 | 11.145 | Prayag Saw1 | 2025-09-27 | 2025-09-30 | Completed
61 | 143/0 | DC+3 | 18.9798 | Prayag Saw2 | 2025-09-27 | 2025-09-30 | Completed | [5 empty] | 2025-09-29 | 142/0
62 | 98A/1 | DA+0 | 11.145 | Ajay Kumar2 | 2025-09-23 | 2025-10-01 | Completed
63 | 146/1 | DA+3 | 11.997 | Pritam Enterprises | 2025-09-30 | 2025-10-03 | Completed
64 | 147/7 | DA+0 | 11.145 | Gokul Sarkar | 2025-09-30 | 2025-10-03 | Completed
65 | 133/7 | DA+0 | 11.145 | Bhoi Enterprises | 2025-09-29 | 2025-10-05 | Completed
66 | 146/2 | DA+0 | 11.145 | Pritam Enterprises | 2025-10-03 | 2025-10-05 | Completed
67 | 116/0 | DD+0 | 21.41 | Dipak | 2025-09-30 | 2025-10-07 | Completed | [14 empty] | GST@18 | #REF!
68 | 142/0 | DC+3 | 18.9798 | Prayag Saw1 | 2025-10-01 | 2025-10-07 | Completed | [5 empty] | ROW SINCE 3-10-25 to 5-10-25 |  |  |  |  | 85/1 | DA+0 | DA+0 | 3 | 11.15 | 33.45 | 439
69 | 144/0 | DD+6 | 26.291 | Prayag Saw2 | 2025-10-01 | 2025-10-08 | Completed | [15 empty] | 9000
70 | 146/0 | DC+0 | 18.727 | Pritam Enterprises | 2025-10-05 | 2025-10-10 | Completed | [10 empty] | 73/2 | DA+9
71 | 140/2 | DA+3 | 11.997 | Prayag Saw1 | 2025-10-08 | 2025-10-10 | Completed
72 | 149/0 | DD+0 | 21.41 | Gokul Sarkar | 2025-10-03 | 2025-10-10 | Completed | [14 empty] | TOTAL | #REF!
73 | 133/8 | DA+6 | 13.072 | Bhoi Enterprises | 2025-10-05 | 2025-10-11 | Completed | [14 empty] | RETENTION | #REF!
74 | 140/3 | DA+3 | 11.997 | Prayag Saw1 | 2025-10-10 | 2025-10-11 | Completed | [14 empty] | TDS 1% | #REF!
75 | 147/0 | DC+0 | 18.727 | Pritam Enterprises | 2025-10-10 | 2025-10-12 | Completed | [14 empty] | PF 10 | #REF!
76 | 115/0 | DC+0 | 18.727 | Dipak | 2025-10-08 | 2025-10-13 | Completed | [14 empty] | GST 20 | #REF!
77 | 138/1 | DA+0 | 11.145 | Prayag Saw2 | 2025-10-08 | 2025-10-13 | Completed | [14 empty] | ADVANCE | 600000
78 | 98A/0 | DC+0 | 18.727 | Ajay Kumar | 2025-09-26 | 2025-10-15 | Completed | [14 empty] | TIGHT & PUNCH 10 | #REF!
79 | 149A/0 | DD+0 | 21.41 | Gokul Sarkar | 2025-10-10 | 2025-10-15 | Completed | [14 empty] | NET PAYABLE | #REF!
80 | 133/4 | DA+0 | 11.145 | Bhoi Enterprises | 2025-10-11 | 2025-10-15 | Completed
81 | 141/0 | DC+0 | 18.727 | Prayag Saw1 | 2025-10-11 | 2025-10-16 | Completed
82 | 147/3 | DA+0 | 11.145 | Pritam Enterprises | 2025-10-12 | 2025-10-15 | Completed
83 | 138/2 | DA+0 | 11.145 | Prayag Saw2 | 2025-10-13 | 2025-10-16 | Completed
84 | 110/0 | DC+0 | 18.727 | Dipak | 2025-10-13 | 2025-10-18 | Completed
85 | 133/1 | DA+0 | 11.145 | Bhoi Enterprises | 2025-10-15 | 2025-10-19 | Completed
86 | 138/3 | DA+0 | 11.145 | Prayag Saw2 | 2025-10-16 | 2025-10-19 | Completed
87 | 147/9 | DA+0 | 11.145 | Gokul Sarkar | 2025-10-16 | 2025-10-19 | Completed
88 | 147/2 | DA+0 | 11.145 | Pritam Enterprises | 2025-10-15 | 2025-10-19 | Completed
89 | 147/1 | DA+0 | 11.145 | Pritam Enterprises | 2025-10-19 | 2025-10-22 | Completed
90 | 147/8 | DA+0 | 11.145 | Gokul Sarkar | 2025-10-19 | 2025-10-22 | Completed
91 | 134A/0 | DD+0 | 21.41 | Prayag Saw1 | 2025-10-16 | 2025-10-23 | Completed
92 | 135/1 | DA+0 | 11.145 | Bhoi Enterprises | 2025-10-19 | 2025-10-24 | Completed
93 | 82/2 | DA+0 | 11.145 | Namechand Mahto | 2025-10-19 | 2025-10-24 | Completed
94 | 138/0 | DB+3 | 18.1115 | Prayag Saw2 | 2025-10-19 | 2025-10-24 | Completed
95 | 134A/2 | DA+3 | 11.997 | Prayag Saw1 | 2025-10-24 | 2025-10-26 | Completed
96 | 112/0 | DC+9 | 24.1826 | Dipak | 2025-10-19 | 2025-10-27 | Completed
97 | 147/6 | DA+0 |  | Pritam Enterprises | 2025-10-23 | 2025-10-26 | Completed
98 | 148/1 | DA+0 |  | Gokul Sarkar | 2025-10-23 | 2025-10-27 | Completed
99 | 147/5 | DA+0 |  | Pritam Enterprises | 2025-10-27 | 2025-10-28 | Completed
100 | 134/0 | DD+0 |  | Prayag Saw2 | 2025-10-27 | 2025-10-29 | Completed
101 | 76/0 | DC+0 | 18.727 | Namechand Mahto | 2025-10-24 | 2025-10-31 | Completed
102 | 133/0 | DC+0 | 18.727 | Bhoi Enterprises | 2025-10-24 | 2025-10-31 | Completed
103 | 147/4 | DA+0 |  | Pritam Enterprises | 2025-10-28 | 2025-10-31 | Completed
104 | 139/0 | DC+3 |  | Prayag Saw1 | 2025-10-26 | 2025-10-28 | Completed
105 | 153A/0 | DB+0 |  | Gokul Sarkar | 2025-10-27 | 2025-11-01 | Completed
106 | 115/1 | DB+9 |  | Dipak | 2025-10-27 | 2025-11-02 | Completed
107 | 135/0 | DC+0 |  | Prayag Saw1 | 2025-10-29 | 2025-11-02 | Completed
108 | 134A/1 | DA+9 |  | Prayag Saw2 | 2025-10-29 | 2025-11-03 | Completed
109 | 132/3 | DA+0 |  | Bhoi Enterprises | 2025-11-01 | 2025-11-04 | Completed
110 | 77/0 | DB+0 |  | Namechand Mahto | 2025-11-01 | 2025-11-05 | Completed
111 | 129/1 | DA+3 |  | Pritam Enterprises | 2025-11-01 | 2025-11-05 | Completed
112 | 134A/4 | DA+9 |  | Prayag Saw2 | 2025-11-04 | 2025-11-06 | Completed
113 | 132/1 | DA+0 |  | Bhoi Enterprises | 2025-11-05 | 2025-11-07 | Completed | Strong ROW. Landowner stopped work not allowing to enter at location and Tower material left without watchmen.
114 | 136/0 | DD+0 |  | Prayag Saw1 | 2025-11-03 | 2025-11-08 | Completed
115 | 131/1 | DA+3 |  | Pritam Enterprises | 2025-11-06 | 2025-11-09 | Completed
116 | 98/0 | DC+0 | 18.727 | Namechand Mahto | 2025-11-06 | 2025-11-10 | Completed
117 | 111/0 | DB+9 |  | Dipak | 2025-11-03 | 2025-11-10 | Completed
118 | 132/4 | DA+0 |  | Bhoi Enterprises | 2025-11-08 | 2025-11-11 | Completed
119 | 137/0 | DB+3 |  | Prayag Saw2 | 2025-11-06 | 2025-11-12 | Completed
120 | 152/0 | DD+18 |  | Gokul Sarkar | 2025-11-01 | 2025-11-14 | Completed | [5 empty] | 149B/3
121 | 129/0 | DC+0 |  | Pritam Enterprises | 2025-11-09 | 2025-11-14 | Completed | [5 empty] | 133/5
122 | 131/2 | DA+3 | 11.997 | Bhoi Enterprises | 11.11.2025 | 2025-11-15 | Completed
123 | 80/0 | DB+3 | 18.1115 | Namechand Mahto | 10.11.2025 | 2025-11-15 | Completed
124 | 145/0 | DD+6 |  | Prayag Saw2 | 12.11.2025 | 2025-11-17 | Completed | [5 empty] | 2025-11-17
125 | 82/0 | DB+3 |  | Namechand Mahto | 2025-11-15 | 2025-11-20 | Completed
126 | 109A/0 | DB+6 |  | Dipak | 2025-11-13 | 2025-11-20 | Completed
127 | 133/5 | DA+0 |  | Bhoi Enterprises | 2025-11-15 | 2025-11-20 | Completed | [5 empty] | 2025-11-19
128 | 148/0 | DB+0 |  | Prayag Saw2 | 2025-11-16 | 2025-11-21 | Completed
129 | 149B/3 | DB+9 |  | Gokul Sarkar | 2025-11-14 | 2025-11-22 | Completed | [5 empty] | 2025-11-19 | 2025-11-22
130 | 78/1 | DA+3 |  | Namechand Mahto | 2025-11-21 | 2025-11-25 | Completed | [5 empty] | 2025-11-24 | 79/1
131 | 134A/3 | DA+6 |  | Prayag Saw2 | 2025-11-21 | 2025-11-25 | Completed | [5 empty] | 2025-11-24 | 135/2 | Approach Road
132 | 135/2 | DA+0 |  | Prayag Saw2 | 2025-11-25 | 2025-11-27 | Completed
133 | 149B/0 | DB+3 |  | Gokul Sarkar | 2025-11-23 | 2025-11-28 | Completed | [5 empty] | 2025-11-27
134 | 128/0 | DC+3 |  | Bhoi Enterprises | 2025-11-21 | 2025-11-28 | Completed | [5 empty] | 2025-11-26 | 130/0 | 129/2
135 | 98B/0 | DD+0 |  | Dipak | 2025-11-22 | 2025-11-29 | Completed | [5 empty] | 2025-11-25 | 99/0
136 | 79/1 | DA+9 |  | Namechand Mahto | 2025-11-25 | 2025-11-30 | Completed
137 | 135/3 | DA+3 |  | Prayag Saw2 | 2025-11-28 | 2025-11-30 | Completed
138 | 140/1 | DA+3 |  | Prayag Saw2 | 2025-12-01 | 2025-12-03 | Completed
139 | 130/0 | DC+6 |  | Bhoi Enterprises | 2025-11-28 | 2025-12-05 | Completed
140 | 81/1 | DA+0 |  | Namechand Mahto | 2025-12-01 | 2025-12-05 | Completed
141 | 150/0 | DD+9 |  | Gokul Sarkar | 2025-11-28 | 2025-12-07 | Completed
142 | 95/0 | DB+9 |  | Dipak | 2025-11-29 | 2025-12-07 | Completed
143 | 139/1 | DA+9 |  | Prayag Saw2 | 2025-12-06 | 2025-12-10 | Completed
144 | 81/0 | DB+9 |  | Namechand Mahto | 2025-12-06 | 2025-12-11 | Completed
145 | 126/2 | DA+3 |  | Bhoi Enterprises | 2025-12-06 | 2025-12-12 | Completed
146 | 140/0 | DB+0 |  | Prayag Saw2 | 2025-12-09 | 2025-12-13 | Completed
147 | 151/0 | DD+9 |  | Gokul Sarkar | 2025-12-07 | 2025-12-14 | Completed
148 | 126/1 | DA+6 |  | Bhoi Enterprises | 2025-12-12 | 2025-12-16 | Completed
149 | 85/0 | DC+0 |  | Namechand Mahto | 2025-12-12 | 2025-12-16 | Completed
150 | 72/2 | DA+3 |  | Balaji Tour & Travels 2 | 2025-12-06 | 2025-12-16 | Completed
151 | 119/2 | DA+3 |  | Prayag Saw | 2025-12-13 | 2025-12-18 | Completed
152 | 104B/2 | DA+0 |  | Namechand Mahto2 | 2025-10-18 |  | WIP
153 | 95/1 | DB+0 |  | Balaji Tour & Travels | 2025-12-07 |  | WIP
154 | 90/1 | DA+9 |  | Namechand Mahto 2 | 2025-12-12 |  | WIP
155 | 154/0 | DD+0 |  | Gokul Sarkar | 2025-12-14 |  | WIP
156 | 84/0 | DC+6 |  | Namechand Mahto | 2025-12-17 |  | Material Shifting
157 | 119/1 | DA+3 |  | Prayag Saw | 2025-12-18 |  | Material Shifting
185
5

## Completion date (hidden)
Location no | Tower type | FDN TYPE | FDN CMP date | Erection CMP Date | Earthing CMP Date
GANTRY | GE | #N/A | #N/A | #N/A | #N/A
1/0 | DE+0 | 0 | 2026-02-11 | #N/A | #N/A
1A/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
2/0 | DD+0 | 0 | 2026-02-28 | #N/A | #N/A
2/1 | Gantry UCS | 0 | 08-03-226 | #N/A | #N/A
3/0 | Gantry UCS | #N/A | #N/A | #N/A | #N/A
3/1 | DD+3 | #N/A | #N/A | #N/A | #N/A
4/0 | DD+18 | #N/A | #N/A | #N/A | #N/A
5/0 | DD+9 | #N/A | #N/A | #N/A | #N/A
5/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
5/2 | DA+0 | 0 | 2026-03-20 | #N/A | #N/A
5/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
5/4 | DA+0 | #N/A | #N/A | #N/A | #N/A
5/5 | DA+0 | #N/A | #N/A | #N/A | #N/A
5/6 | DA+6 | #N/A | #N/A | #N/A | #N/A
5A/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
5A/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
5B/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
5B/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
5C/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
5D/0 | DC+3 | #N/A | #N/A | #N/A | #N/A
5E/0 | DC+3 | #N/A | #N/A | #N/A | #N/A
6/0 | DC+0 | 0 | 2026-02-19 | #N/A | #N/A
6A/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
68/0 | DB+9 | #N/A | #N/A | #N/A | #N/A
6C/0 | DC+3 | #N/A | #N/A | #N/A | #N/A
6C/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
6D/0 | DD+6 | #N/A | #N/A | #N/A | #N/A
6D/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
6D/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
6D/3 | DA+3 | #N/A | #N/A | #N/A | #N/A
6D/4 | DA+3 | #N/A | #N/A | #N/A | #N/A
7/0 | DB+0 | 0 | 2026-02-06 | #N/A | #N/A
7/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
7/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
7/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
7/4 | DA+0 | #N/A | #N/A | #N/A | #N/A
7/5 | DA+0 | #N/A | #N/A | #N/A | #N/A
7/6 | DA+0 | #N/A | #N/A | #N/A | #N/A
7/7 | DA+0 | #N/A | #N/A | #N/A | #N/A
7/8 | DA+3 | #N/A | #N/A | #N/A | #N/A
7/9 | DA+0 | #N/A | #N/A | #N/A | #N/A
7/10 | DA+3 | #N/A | #N/A | #N/A | #N/A
8/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
8/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
8/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
8/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
8/4 | DA+3 | #N/A | #N/A | #N/A | #N/A
9/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
9/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
9/2 | DA+6 | #N/A | #N/A | #N/A | #N/A
9/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
9/4 | DA+3 | #N/A | #N/A | #N/A | #N/A
9/5 | DB+9 | #N/A | #N/A | #N/A | #N/A
10/0 | DC+3 | #N/A | #N/A | #N/A | #N/A
10/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
10/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
10/3 | DA+3 | #N/A | #N/A | #N/A | #N/A
10/4 | DA+6 | #N/A | #N/A | #N/A | #N/A
10/5 | DA+0 | #N/A | #N/A | #N/A | #N/A
10/6 | DA+0 | #N/A | #N/A | #N/A | #N/A
10/7 | DA+0 | #N/A | #N/A | #N/A | #N/A
10/8 | DA+0 | #N/A | #N/A | #N/A | #N/A
10/9 | DB+0 | #N/A | #N/A | #N/A | #N/A
10/10 | DA+0 | #N/A | #N/A | #N/A | #N/A
10/11 | DA+3 | #N/A | #N/A | #N/A | #N/A
10/12 | DA+3 | #N/A | #N/A | #N/A | #N/A
10/13 | DA+3 | #N/A | #N/A | #N/A | #N/A
10/14 | DA+0 | #N/A | #N/A | #N/A | #N/A
10/15 | DA+6 | #N/A | #N/A | #N/A | #N/A
11/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
11/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
11/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
11/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
11/4 | DA+0 | #N/A | #N/A | #N/A | #N/A
11/5 | DA+0 | #N/A | #N/A | #N/A | #N/A
11/6 | DA+0 | #N/A | #N/A | #N/A | #N/A
12/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
12/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
12/2 | DA+3 | #N/A | #N/A | #N/A | #N/A
13/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
13/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
13/2 | DA+6 | #N/A | #N/A | #N/A | #N/A
13/3 | DA+3 | #N/A | #N/A | #N/A | #N/A
14/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
14/1 | DB+9 | #N/A | #N/A | #N/A | #N/A
15/0 | DC+9 | #N/A | #N/A | #N/A | #N/A
15/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
16/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
16/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
17/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
17/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
18/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
18/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
19/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
19/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
19/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
19/3 | DA+3 | #N/A | #N/A | #N/A | #N/A
20/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
20/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
20/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
20/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
20/4 | DA+0 | #N/A | #N/A | #N/A | #N/A
20/5 | DA+3 | #N/A | #N/A | #N/A | #N/A
20/6 | DA+9 | #N/A | #N/A | #N/A | #N/A
21/0 | DD+3 | #N/A | #N/A | #N/A | #N/A
21/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
21/2 | DA+6 | #N/A | #N/A | #N/A | #N/A
22/0 | DB+3 | #N/A | #N/A | #N/A | #N/A
23/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
23/1 | DB+3 | #N/A | #N/A | #N/A | #N/A
23/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
23/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
24/0 | DC+9 | #N/A | #N/A | #N/A | #N/A
24/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
25/0 | DD+6 | #N/A | #N/A | #N/A | #N/A
25/1 | Gantry UCS | #N/A | #N/A | #N/A | #N/A
25/2 | Gantry UCS | #N/A | #N/A | #N/A | #N/A
26/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
27/0 | DC+9 | #N/A | #N/A | #N/A | #N/A
27A/0 | DD+9 | #N/A | #N/A | #N/A | #N/A
27A/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
27A/2 | DA+6 | #N/A | #N/A | #N/A | #N/A
27B/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
27B/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
27B/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
27B/3 | DA+9 | #N/A | #N/A | #N/A | #N/A
28/0 | DB+3 | #N/A | #N/A | #N/A | #N/A
28/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
29/0 | DB+9 | #N/A | #N/A | #N/A | #N/A
29/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
29/2 | DA+9 | #N/A | #N/A | #N/A | #N/A
29/3 | DB+9 | #N/A | #N/A | #N/A | #N/A
30/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
30/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
30/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
30/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
31/0 | DC+9 | #N/A | #N/A | #N/A | #N/A
32/0 | DC+9 | #N/A | #N/A | #N/A | #N/A
32/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
32/2 | DA+3 | #N/A | #N/A | #N/A | #N/A
32/3 | DA+9 | #N/A | #N/A | #N/A | #N/A
33/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
34/0 | DC+6 | #N/A | #N/A | #N/A | #N/A
34/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
35/0 | DC+9 | #N/A | #N/A | #N/A | #N/A
35/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
36/0 | DC+6 | #N/A | #N/A | #N/A | #N/A
36/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
36/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
36A | DD+0 | #N/A | #N/A | #N/A | #N/A
37/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
38/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
38/1 | DB+6 | #N/A | #N/A | #N/A | #N/A
38/2 | DA+3 | #N/A | #N/A | #N/A | #N/A
38/3 | DA+9 | #N/A | #N/A | #N/A | #N/A
38/4 | DA+0 | #N/A | #N/A | #N/A | #N/A
38/5 | DA+9 | #N/A | #N/A | #N/A | #N/A
39/0 | DB+3 | #N/A | #N/A | #N/A | #N/A
39/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
39/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
39/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
39/4 | DA+6 | #N/A | #N/A | #N/A | #N/A
40/0 | DD+3 | #N/A | #N/A | #N/A | #N/A
40/1 | DB+6 | #N/A | #N/A | #N/A | #N/A
40/2 | DA+6 | #N/A | #N/A | #N/A | #N/A
41/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
41/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
41/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
41/3 | DA+9 | #N/A | #N/A | #N/A | #N/A
42/0 | DC+3 | #N/A | #N/A | #N/A | #N/A
42/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
42/2 | DCT+6 | #N/A | #N/A | #N/A | #N/A
42/3 | DA+9 | #N/A | #N/A | #N/A | #N/A
42/4 | DA+9 | #N/A | #N/A | #N/A | #N/A
42/5 | DA+0 | #N/A | #N/A | #N/A | #N/A
42/6 | DA+3 | #N/A | #N/A | #N/A | #N/A
42/7 | DA+0 | #N/A | #N/A | #N/A | #N/A
43/0 | DC+6 | #N/A | #N/A | #N/A | #N/A
44/0 | DB+9 | #N/A | #N/A | #N/A | #N/A
44/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
45/0 | DD+9 | #N/A | #N/A | #N/A | #N/A
45/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
45/2 | DA+6 | #N/A | #N/A | #N/A | #N/A
45/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
45/4 | DA+6 | #N/A | #N/A | #N/A | #N/A
46/0 | DD+3 | #N/A | #N/A | #N/A | #N/A
47/0 | DD+9 | #N/A | #N/A | #N/A | #N/A
47/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
47/2 | DA+9 | #N/A | #N/A | #N/A | #N/A
48/0 | DD+3 | #N/A | #N/A | #N/A | #N/A
49/0 | DD+3 | #N/A | #N/A | #N/A | #N/A
50/0 | DD+9 | #N/A | #N/A | #N/A | #N/A
51/0 | DD+18 | #N/A | #N/A | #N/A | #N/A
51/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
51/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
51/3 | DA+3 | #N/A | #N/A | #N/A | #N/A
52/0 | DB+3 | #N/A | #N/A | #N/A | #N/A
52/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
53/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
54/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
54/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
54/2 | DA+6 | #N/A | #N/A | #N/A | #N/A
54/3 | DA+3 | #N/A | #N/A | #N/A | #N/A
55/0 | DD+18 | #N/A | #N/A | #N/A | #N/A
56/0 | DB+9 | #N/A | #N/A | #N/A | #N/A
56/1 | DB+9 | #N/A | #N/A | #N/A | #N/A
56/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
56/3 | DB+9 | #N/A | #N/A | #N/A | #N/A
56/4 | DA+6 | #N/A | #N/A | #N/A | #N/A
56/5 | DA+6 | #N/A | #N/A | #N/A | #N/A
57/0 | DB+9 | #N/A | #N/A | #N/A | #N/A
58/0 | DB+9 | #N/A | #N/A | #N/A | #N/A
59/0 | DC+9 | #N/A | #N/A | #N/A | #N/A
59/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
60/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
60/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
60/2 | DA+3 | #N/A | #N/A | #N/A | #N/A
60/3 | DA+9 | #N/A | #N/A | #N/A | #N/A
61/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
61/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
62/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
62/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
62/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
62/3 | DA+9 | #N/A | #N/A | #N/A | #N/A
62/4 | DA+6 | #N/A | #N/A | #N/A | #N/A
62/5 | DA+6 | #N/A | #N/A | #N/A | #N/A
63/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
63/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
64/0 | DC+9 | #N/A | #N/A | #N/A | #N/A
64/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
64/2 | DA+9 | #N/A | #N/A | #N/A | #N/A
64/3 | DA+9 | #N/A | #N/A | #N/A | #N/A
64/4 | DA+9 | #N/A | #N/A | #N/A | #N/A
64/5 | DA+9 | #N/A | #N/A | #N/A | #N/A
64/6 | DA+3 | #N/A | #N/A | #N/A | #N/A
64/7 | DA+3 | #N/A | #N/A | #N/A | #N/A
65/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
65/1 | DB+9 | #N/A | #N/A | #N/A | #N/A
66/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
66/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
66/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
66/3 | DA+3 | #N/A | #N/A | #N/A | #N/A
66/4 | DA+9 | #N/A | #N/A | #N/A | #N/A
67/0 | DC+6 | #N/A | #N/A | #N/A | #N/A
67/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
67/2 | DB+0 | #N/A | #N/A | #N/A | #N/A
68/0 | DB+9 | #N/A | #N/A | #N/A | #N/A
69/0 | DD+3 | #N/A | #N/A | #N/A | #N/A
69/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
69/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
69/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
70/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
71/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
71/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
71/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
71/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
72/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
72/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
72/2 | DA+3 | #N/A | #N/A | #N/A | #N/A
73/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
73/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
74/0 | DB+9 | #N/A | #N/A | #N/A | #N/A
81/0 | DB+9 | #N/A | #N/A | #N/A | #N/A
81/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
81/5 | DA+6 | #N/A | #N/A | #N/A | #N/A
83/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
84/0 | DC+6 | #N/A | #N/A | #N/A | #N/A
85/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
86/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
86/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
87/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
87/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
87/2 | DA+9 | #N/A | #N/A | #N/A | #N/A
88/0 | DC+6 | #N/A | #N/A | #N/A | #N/A
89/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
89/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
90/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
90/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
91/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
91/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
91/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
91/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
92/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
93/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
94/0 | DB+6 | #N/A | #N/A | #N/A | #N/A
95/0 | DB+9 | #N/A | #N/A | #N/A | #N/A
95/1 | DB+0 | #N/A | #N/A | #N/A | #N/A
95/2 | DA+9 | #N/A | #N/A | #N/A | #N/A
95A/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
96/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
96/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
98B/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
98B/2 | DCT+0 | #N/A | #N/A | #N/A | #N/A
99/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
99/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
99/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
99/3 | DA+3 | #N/A | #N/A | #N/A | #N/A
99/4 | DA+3 | #N/A | #N/A | #N/A | #N/A
99A/0 | DB+6 | #N/A | #N/A | #N/A | #N/A
99B/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
99C/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
99C/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
99C/2 | DA+3 | #N/A | #N/A | #N/A | #N/A
100/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
100/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
101/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
102/0 | DD+3 | #N/A | #N/A | #N/A | #N/A
102/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
102/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
103/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
103/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
104/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
104A/0 | DC+9 | #N/A | #N/A | #N/A | #N/A
104B/0 | DB+9 | #N/A | #N/A | #N/A | #N/A
104B/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
105/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
105/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
106/0 | DC+6 | #N/A | #N/A | #N/A | #N/A
107/0 | DD+3 | #N/A | #N/A | #N/A | #N/A
107/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
108/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
109/0 | DC+3 | #N/A | #N/A | #N/A | #N/A
113/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
114/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
117/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
117/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
117/2 | DB+9 | #N/A | #N/A | #N/A | #N/A
118/0 | DC+3 | #N/A | #N/A | #N/A | #N/A
119/0 | DD+3 | #N/A | #N/A | #N/A | #N/A
119/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
119/2 | DA+3 | #N/A | #N/A | #N/A | #N/A
120/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
120/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
121/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
122/0 | DC+6 | #N/A | #N/A | #N/A | #N/A
122/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
122/2 | DA+3 | #N/A | #N/A | #N/A | #N/A
123/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
124/0 | DC+3 | #N/A | #N/A | #N/A | #N/A
125/0 | DC+3 | #N/A | #N/A | #N/A | #N/A
125/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
125/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
125/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
126/0 | DC+6 | #N/A | #N/A | #N/A | #N/A
126/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
126/2 | DA+3 | #N/A | #N/A | #N/A | #N/A
126/3 | DA+6 | #N/A | #N/A | #N/A | #N/A
127/0 | DD+6 | #N/A | #N/A | #N/A | #N/A
127/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
128/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
129/2 | DA+9 | #N/A | #N/A | #N/A | #N/A
130/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
131/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
132/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
132/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
139/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
140/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
151/0 | DD+9 | #N/A | #N/A | #N/A | #N/A
153/0 | DD+18 | #N/A | #N/A | #N/A | #N/A
154/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
154/1 | Gantry UCS | #N/A | #N/A | #N/A | #N/A
154/2 | Gantry UCS | #N/A | #N/A | #N/A | #N/A
155/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
156/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
157/0 | DD+0(aux) | #N/A | #N/A | #N/A | #N/A
GE | GE(aux) | #N/A | #N/A | #N/A | #N/A
140/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
79/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
135/3 | DA+3 | #N/A | #N/A | #N/A | #N/A
98B/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
128/0 | DC+3 | #N/A | #N/A | #N/A | #N/A
149B/0 | DB+3 | #N/A | #N/A | #N/A | #N/A
135/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
78/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
134A/3 | DA+6 | #N/A | #N/A | #N/A | #N/A
149B/3 | DB+9 | #N/A | #N/A | #N/A | #N/A
148/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
82/0 | DB+3 | #N/A | #N/A | #N/A | #N/A
109A/0 | DB+6 | #N/A | #N/A | #N/A | #N/A
133/5 | DA+0 | #N/A | #N/A | #N/A | #N/A
145/0 | DD+6 | #N/A | #N/A | #N/A | #N/A
80/0 | DB+3 | #N/A | #N/A | #N/A | #N/A
131/2 | DA+3 | #N/A | #N/A | #N/A | #N/A
129/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
152/0 | DD+18 | #N/A | #N/A | #N/A | #N/A
137/0 | DB+3 | #N/A | #N/A | #N/A | #N/A
132/4 | DA+0 | #N/A | #N/A | #N/A | #N/A
98/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
111/0 | DB+9 | #N/A | #N/A | #N/A | #N/A
131/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
136/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
132/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
134A/4 | DA+9 | #N/A | #N/A | #N/A | #N/A
77/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
129/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
132/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
134A/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
115/1 | DB+9 | #N/A | #N/A | #N/A | #N/A
135/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
153A/0 | DB+0 | #N/A | #N/A | #N/A | #N/A
76/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
133/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
147/4 | DA+0 | #N/A | #N/A | #N/A | #N/A
134/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
139/0 | DC+3 | #N/A | #N/A | #N/A | #N/A
147/5 | DA+0 | #N/A | #N/A | #N/A | #N/A
112/0 | DC+9 | #N/A | #N/A | #N/A | #N/A
148/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
134A/2 | DA+3 | #N/A | #N/A | #N/A | #N/A
147/6 | DA+0 | #N/A | #N/A | #N/A | #N/A
82/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
135/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
138/0 | DB+3 | #N/A | #N/A | #N/A | #N/A
134A/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
147/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
147/8 | DA+0 | #N/A | #N/A | #N/A | #N/A
133/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
138/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
147/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
147/9 | DA+0 | #N/A | #N/A | #N/A | #N/A
110/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
138/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
141/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
98A/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
133/4 | DA+0 | #N/A | #N/A | #N/A | #N/A
147/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
149A/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
115/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
138/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
147/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
133/8 | DA+6 | #N/A | #N/A | #N/A | #N/A
140/3 | DA+3 | #N/A | #N/A | #N/A | #N/A
140/2 | DA+3 | #N/A | #N/A | #N/A | #N/A
146/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
149/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
144/0 | DD+6 | #N/A | #N/A | #N/A | #N/A
116/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
142/0 | DC+3 | #N/A | #N/A | #N/A | #N/A
133/7 | DA+0 | #N/A | #N/A | #N/A | #N/A
146/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
146/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
147/7 | DA+0 | #N/A | #N/A | #N/A | #N/A
98A/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
141/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
143/0 | DC+3 | #N/A | #N/A | #N/A | #N/A
145/4 | DA+3 | #N/A | #N/A | #N/A | #N/A
149B/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
116/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
133/6 | DA+3 | #N/A | #N/A | #N/A | #N/A
76/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
141/2 | DA+6 | #N/A | #N/A | #N/A | #N/A
143/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
149B/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
114/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
98/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
143/3 | DA+3 | #N/A | #N/A | #N/A | #N/A
143/7 | DA+3 | #N/A | #N/A | #N/A | #N/A
148/7 | DA+0 | #N/A | #N/A | #N/A | #N/A
133/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
97/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
113A/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
143/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
143/6 | DA+0 | #N/A | #N/A | #N/A | #N/A
145/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
148/6 | DA+0 | #N/A | #N/A | #N/A | #N/A
143/4 | DA+3 | #N/A | #N/A | #N/A | #N/A
143/5 | DA+3 | #N/A | #N/A | #N/A | #N/A
133/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
79/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
96/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
82/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
145/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
148/5 | DA+0 | #N/A | #N/A | #N/A | #N/A
83/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
97/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
148/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
81/4 | DA+0 | #N/A | #N/A | #N/A | #N/A
145/1 | DA+3 | #N/A | #N/A | #N/A | #N/A
81/2 | DA+3 | #N/A | #N/A | #N/A | #N/A
148/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
81/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
95A/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
148/4 | DA+0 | #N/A | #N/A | #N/A | #N/A
80/1 | DA+9 | #N/A | #N/A | #N/A | #N/A
86/1 | DA+6 | #N/A | #N/A | #N/A | #N/A
79/0 | DD+0 | #N/A | #N/A | #N/A | #N/A
85/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
73/2 | DA+9 | #N/A | #N/A | #N/A | #N/A
78/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
75/0 | DC+0 | #N/A | #N/A | #N/A | #N/A
73/3 | DA+9 | #N/A | #N/A | #N/A | #N/A
75/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
74/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
75/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
75/3 | DA+3 | #N/A | #N/A | #N/A | #N/A
75/4 | DA+0 | #N/A | #N/A | #N/A | #N/A
75/5 | DA+0 | #N/A | #N/A | #N/A | #N/A
75/6 | DA+0 | #N/A | #N/A | #N/A | #N/A
77/1 | DA+0 | #N/A | #N/A | #N/A | #N/A
77/3 | DA+0 | #N/A | #N/A | #N/A | #N/A
75/7 | DA+0 | #N/A | #N/A | #N/A | #N/A
77/5 | DA+6 | #N/A | #N/A | #N/A | #N/A
77/4 | DA+3 | #N/A | #N/A | #N/A | #N/A
77/2 | DA+3 | #N/A | #N/A | #N/A | #N/A
104B/2 | DA+0 | #N/A | #N/A | #N/A | #N/A
130/0 | DC+6 | #N/A | #N/A | #N/A | #N/A
150/0 | DD+9 | #N/A | #N/A | #N/A | #N/A
Formulas:
FDN TYPE = VLOOKUP([Location no],Foundation!$B8:Q294,10, 0)
FDN CMP date = VLOOKUP([Location no],Foundation!$B8:Q277,12, 0)

## Erection Compiled
SL No. | Location No. | LI / LO | Tower Type | Classification | Starting Date | Tower Weight | Status | Completion Date | Gang Name | Gang Strength | Remark

## Earthing
NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE
Client : RAJASTHAN IV A POWER TRANSMISSION LTD.
CONTRACTOR : KEC INTERNATIONAL LIMITED
SL. No. | Location Number | LI / LO | Tower Type | Foundation type | Completion Date | Remarks
1 | 1/1 | LO | DA-3 | DFR | 2026-02-20
2 | 1/2 | LO | DA-3 | DFR | 2026-02-20
3 | 6/2 | LI | DA+0 | DFR | 2026-02-20

## Stringing Compiled
Number of TSE
S.no | Sec | From AP | To AP | Span (M) | Method | Section Readiness | P/O Starting Date | P/O Completion Date | P/O | F/S Starting Date | F/S/ Completion Date | Length | Status | Gang Name | Hindrance | Remarks
Total

## Soil Investigation
NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE
Client : RAJASTHAN IV A POWER TRANSMISSION LTD.
CONTRACTOR : KEC INTERNATIONAL LIMITED

## Sheet9 (hidden)
400 KV D/C (TWIN) FATEHGARH IV - BHINMAL (PG) TRANSMISSION LINE (VISUAL CHART)
Name of Contractor:M/S KEC INTERNATIONAL LIMITED | [24 empty] | AS ON |  | 2026-03-20 10:53
PROGRESS AT A GLANCE :
[18 empty] | Stringing WIP |  |  |  | Stringing Completed
Sl. No. |  | Activity |  |  | UoM |  | Total Qty |  |  | Completed |  |  | Balance | [12 empty] | River Crossing
1 |  | Detail survey |  |  | Kms. |  | 188.444 |  |  | 188.444 |  |  | 0
2 |  | Check survey |  |  | Kms. |  | 188.444 |  |  | 178.075 |  |  | 10.369
3 |  | CS Approval |  |  | Kms. |  | 188.444 |  |  | 178.075 |  |  | 10.369
4 |  | Soil Investigation |  |  | Loc |  | 73 |  |  | 73 |  |  | 0
5 |  | Foundation |  |  | Loc |  | 512 |  |  | 208 |  |  | 304 | [12 empty] | Erection WIP
6 |  | Earthing |  |  | Nos. |  | 514 |  |  | 190 |  |  | 324 |  |  |  |  | Erection Comp |  |  | Span | [6 empty] | Rly. X-ing
7 |  | Erection |  |  | Loc |  | 512 |  |  | 75 |  |  | 437 |  |  |  |  | Earthing
8 |  | Tack Welding |  |  | Nos. |  | 512 | [5 empty] | 512
9 |  | Stringing(P/0) |  |  | Kms. |  | 188.444 | [5 empty] | 188.444 |  |  |  |  | Pipe Line |  |  |  |  | Excavation
10 |  | Stringing (F/S) |  |  | Kms. |  | 188.444 | [5 empty] | 188.444 | [11 empty] | NH | SH | 66/132/ 220/ 400
GANTRY |  |  | AP1 |  | AP 1A |  | AP2 |  | AP3 |  | 3/1 |  | 3/2 |  | 3/3 |  | AP4 |  | 4/1 |  | 4/2 |  | 4/3 |  | 4/4 |  | 4/5 | SH
[36 empty] | U/P | ROW | CLEAR
|  | 89 |  | 113 |  | 264 |  | 244 |  | 657 |  | 419.226 |  | 420.01 |  | 416.531 |  | 356.262 |  | 343.074 |  | 381.329 |  | 373.323 |  | 246.012 |  | 249.424 | [7 empty] | 0 | 0 | 0
|  |  | DD+0 |  | DD+3 |  | DD+25 |  | DD+25 |  | DB+6 |  | DA+0 |  | DA+9 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+6 |  | DA+3 |  | DB+0
REVISED DETAIL SURVEY REPORT SUBMITTED
| 4/6 |  | 4/7 |  | 4/8 |  | 4/9 |  | AP5 |  | AP6 |  | 6/1 |  | 6/2 |  | 6/3 |  | 6/4 |  | 6/5 |  | 6/6 |  | 6/7 |  | AP7
|  | 399.707 |  | 438.616 |  | 400.604 |  | 438.765 |  | 226.315 |  | 442.553 |  | 389.329 |  | 359.361 |  | 405.006 |  | 426.518 |  | 356.055 |  | 369.295 |  | 374.993 |  | 383.768 | [7 empty] | 0 | 0 | 0
| DA+0 |  | DA+6 |  | DA+6 |  | DA+3 |  | DD+18 |  | DD+18 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB+0
REVISED DETAIL SURVEY REPORT SUBMITTED
| 7/1 |  |  |  | 7/2 |  | 7/3 |  | 7/4 |  | 7/5 |  | 7/6 |  | 7/7 |  | 7/8 |  | 7/9 |  | 7/10 |  | AP8 |  | 8/1 |  | 8/2
|  |  | 396.38 |  |  | 392.534 |  | 332.162 |  | 352.112 |  | 389.393 |  | 374.477 |  | 419.977 |  | 387.899 |  | 407.654 |  | 402.357 |  | 372.259 |  | 410.949 |  | 379.075 | [7 empty] | 0 | 0 | 0
1MRC
| DA+0 |  |  |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DB+0 |  | DA+0 |  | DA+0
WORK FRONT TO BE CLEARED
| 8/3 |  | 8/4 |  | AP9 |  | 9/1 |  | 9/2 |  | 9/3 |  | 9/4 |  | 9/5 |  | AP 10 |  | 10/1 |  | 10/2 |  | 10/3 |  | 10/4 |  | 10/5
|  | 412.596 |  | 340.112 |  | 410.76 |  | 427.9 |  | 404.21 |  | 398.446 |  | 431.939 |  | 486.196 |  | 369.717 |  | 389.344 |  | 395.602 |  | 375 |  | 462 |  | 382 | [7 empty] | 0 | 0 | 0
| DA+0 |  | DA+3 |  | DB+0 |  | DA+3 |  | DA+6 |  | DA+0 |  | DA+3 |  | DB+9 |  | DC+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+6 |  | DA+0
WORK FRONT YET TO BE CLEARED
| 10/6 |  | 10/7 |  | 10/8 |  | 10/9 |  | 10/10 |  | 10/11 |  | 10/12 |  | 10/13 |  | 10/14 |  | 10/15 |  | AP11 |  | 11/1 |  | 11/2 |  | 11/3
|  | 428 |  | 411 |  | 352 |  | 405 |  | 400.126 |  | 384 |  | 406 |  | 378 |  | 373 |  | 378.362 |  | 433.995 |  | 370.685 |  | 323.972 |  | 384.462 | [7 empty] | 0 | 0 | 0
| DA+0 |  | DA+0 |  | DA+0 |  | DB+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+6 |  | DB+0 |  | DA+3 |  | DA+0 |  | DA+0
|  |  | 1 MRC-4 Leg | [5 empty] | 1 MRC-4 Leg
WORK FRONT YET TO BE CLEARED
| 11/4 |  | 11/5 |  | 11/6 |  | AP12 |  | 12/1 |  | 12/2 |  | AP13 |  | 13/1 |  | 13/2 |  | 13/3 |  | AP14 |  | 14/1 |  | AP15 |  | 15/1
|  | 381.188 |  | 336.409 |  | 438.97 |  | 395.179 |  | 388.12 |  | 364.446 |  | 404.572 |  | 432.27 |  | 404.23 |  | 416.621 |  | 468.039 |  | 432.318 |  | 464.521 |  | 369.743 | [7 empty] | 0 | 0 | 0
| DA+0 |  | DA+0 |  | DA+0 |  | DB+0 |  | DA+0 |  | DA+3 |  | DC+0 |  | DA+9 |  | DA+6 |  | DA+3 |  | DB+0 |  | DB+9 |  | DC+9 |  | DA+6
[8 empty] | Pit A,B 1MRC |  |  | B,C Bench | [9 empty] | 1 MRC -4 Leg
WORK FRONT YET TO BE CLEARED
| AP16 |  | 16/1 |  | AP17 |  | 17/1 |  | AP18 |  | 18/1 |  | AP19 |  | 19/1 |  | 19/2 |  | 19/3 |  | AP20 |  | 20/1 |  | 20/2 |  | 20/3
|  | 284.16 |  | 270.742 |  | 286.64 |  | 291.699 |  | 398.719 |  | 425.465 |  | 383.813 |  | 403.279 |  | 355.215 |  | 399.839 |  | 287.442 |  | 390.748 |  | 364.274 |  | 337.546 | [7 empty] | 0 | 0 | 0
| DD+0 |  | DA+0 |  | DB+0 |  | DA+0 |  | DC+0 |  | DA+6 |  | DD+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+0
[12 empty] | Pit D 1MRC | [10 empty] | Pit B 1MRC
WORK FRONT YET TO BE CLEARED
| 20/4 |  | 20/5 |  | 20/6 |  | AP21 |  | 21/1 |  | 21/2 |  | AP22 |  | AP23 |  | 23/1 |  | 23/2 |  | 23/3 |  | AP24 |  | 24/1 |  | AP25
|  | 348.292 |  | 418.835 |  | 408.963 |  | 365.467 |  | 437.074 |  | 363.142 |  | 159.789 |  | 300.158 |  | 293.131 |  | 357.377 |  | 341.409 |  | 362.905 |  | 421.052 |  | 216.448 | [7 empty] | 0 | 0 | 0
| DA+0 |  | DA+3 |  | DA+9 |  | DD+3 |  | DA+0 |  | DA+6 |  | DB+3 |  | DD+0 |  | DB+3 |  | DA+0 |  | DA+0 |  | DC+9 |  | DA+9 |  | DD+6
3MRC-4 LEG
WORK FRONT YET TO BE CLEARED | [22 empty] | C/S REPORT TO BE APPROVED
| 25/1 |  | 25/2 |  | AP 26 |  | AP 27 |  | 27A/0 |  | 27A/1 |  | 27A/2 |  | AP27B |  | 27B/1 |  | 27B/2 |  | 27B/3 |  | AP28 |  | 28/1 |  | AP29
|  | 439.695 |  | 243.188 |  | 333.219 |  | 333.219 |  | 363.001 |  | 363.001 |  | 356.124 |  | 376.245 |  | 381.122 |  | 364.433 |  | 263.077 |  | 356.193 |  | 352.42 |  | 381.028 | [7 empty] | 0 | 0 | 0
| GTY |  | GTY |  | DB+0 |  | DC+9 |  | DD+9 |  | DA+0 |  | DA+6 |  | DC+0 |  | DA+6 |  | DA+0 |  | DA+9 |  | DB+3 |  | DA+3 |  | DB+9
C/S REPORT YET TO BE APPROVED | [7 empty] | WORK FRONT TO BE CLEARED
| 29/1 |  | 29/2 |  | 29/3 |  | AP30 |  | 30/1 |  | 30/2 |  | 30/3 |  | AP31 |  | AP32 |  | 32/1 |  | 32/2 |  | 32/3 |  | AP33 |  | AP34 |  | 34/1
|  | 419.603 |  | 425.18 |  | 425.18 |  | 287.537 |  | 336.512 |  | 325.304 |  | 214.253 |  | 455.946 |  | 421 |  | 419 |  | 408 |  | 409.749 |  | 324.03 |  | 366.7 |  | 473.305 | [5 empty] | 0 | 0 | 0
| DA+6 |  | DA+9 |  | DB+9 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC+9 |  | DC+9 |  | DA+3 |  | DA+3 |  | DA+9 |  | DB+0 |  | DC+6 |  | DA+9
WORK FRONT TO BE CLEARED
| AP35 |  | 35/1 |  | AP36 |  | 36/1 |  | 36/2 |  | 36A |  | AP37 |  | AP38 |  | 38/1 |  | 38/2 |  | 38/3 |  | 38/4 |  | 38/5 |  | AP39 |  | 39/1 |  | 39/2
|  | 358.321 |  | 477.815 |  | 415.464 |  | 402.229 |  | 437.434 |  |  |  | 455.922 |  | 419.765 |  | 418.917 |  | 386.486 |  | 376.53 | [5 empty] | 404.739 |  | 366.729 |  | 274.587 |  |  |  | 0 | 0 | 0
| DC+9 |  | DA+9 |  | DC+6 |  | DA+9 |  | DA+0 |  | DD+0 |  | DD+0 |  | DB+0 |  | DB+6 |  | DA+3 |  | DA+9 |  | DA+0 |  | DA+9 |  | DB+3 |  | DA+6 |  | DA+0
WORK FRONT TO BE CLEARED
| 39/3 |  | 39/4 |  | AP40 |  |  | AP41 |  | 41/1 |  | 41/2 |  | 41/3 |  | AP42 |  | 42/1 |  | 42/2 |  | 42/3
|  | 341.668 |  | 425.863 |  | 370.45 | 397.61 |  | 413.4 |  | 423.65 |  | 415.97 |  | 415.35 |  | 394.875 | U/P | 429.62 |  | 381.905 |  | 405.26 | [9 empty] | 1 | 0 | 0 | 1 | 0 | 0
ROW
| DA+0 |  | DA+6 |  | DD+3 |  |  | DB+0 |  | DA+9 |  | DA+0 |  | DA+9 |  | DC+3 |  | DA+9 |  | DCT+6 |  | DA+9
[12 empty] | Pit C,B 1MRC |  |  |  |  | Benching ,Pit C,B 1MRC |  |  |  |  | 3MRC-4 LEG
WORK FRONT YET TO BE CLEARED
| 42/4 |  | 42/5 |  | 42/6 |  | 42/7 |  | AP43 | NH | AP44 |  | 44/1 |  | AP45 |  | 45/1 |  | 45/2 |  | 45/3 |  | 45/4 |  | AP46 |  | AP47
|  | 338.156 |  | 288.303 |  | 297.15 |  | 195.903 |  | 249.66 |  | 374.48 |  | 430.3 |  | 404.386 |  | 341.423 |  | 305.401 |  | 319.981 |  | 345.621 |  | 223.151 |  | 393.817 | [7 empty] | 0 | 0 | 0
| DA+9 |  | DA+0 |  | DA+3 |  | DA+0 |  | DC+6 |  | DB+9 |  | DA+9 |  | DD+9 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+6 |  | DD+3 |  | DD+9
3MRC-4 LEG |  |  | Benching |  | 1MRC-4 leg |  | Benching |  |  |  | 3MRC |  | 3MRC
WORK FRONT YET TO BE CLEARED | [15 empty] | REVISED CHECK SURVEY TO BE SUBMITTED
| 47/1 |  | 47/2 |  | AP48 |  | AP49 |  | AP50 |  | AP51 |  | 51/1 |  | 51/2 |  | 51/3 |  | AP52 |  | 52/1 |  | AP53 | SH | AP54 |  | 54/1
|  | 435.136 | U/P | 403.209 |  | 422.554 |  | 353.484 |  | 274.9 |  | 465.033 |  | 373.98 |  | 416.864 |  | 381.019 |  | 391.52 |  | 374.93 |  | 248.57 |  | 384.17 |  | 330.76 | [7 empty] | 1 | 0 | 0
ROW
| DA+9 |  | DA+9 |  | DD+3 |  | DD+3 |  | DD+9 |  | DD+18 |  | DA+3 |  | DA+0 |  | DA+3 |  | DB+0 |  | DA+6 |  | DD+0 |  | DC+0 |  | DA+3
[9 empty] | 3MRC | [9 empty] | 2MRC ?? |  | 1MRC-4LEG
REVISED C/S TO BE SUBMITTED | [5 empty] | WOK FRONT YET TO BE CLEARED | [11 empty] | WORK FRONT YET TO BE CLEARED
| 54/2 |  | 54/3 |  | AP55 |  | AP56 |  | 56/1 |  | 56/2 |  | 56/3 |  | 56/4 |  | 56/5 |  | AP57 |  | AP58 |  | AP59 |  | 59/1 |  | AP60
C
| C | 285.32 |  | 354.7 |  | 420.54 |  | 340.56 |  | 336.52 |  | 375.99 |  | 308.41 |  | 444.84 |  | 392.02 |  | 407.803 |  | 206.062 |  | 417.384 |  | 304.564 |  | 395.51 | [7 empty] | 0 | 0 | 1
| DA+6 |  | DA+3 |  | DD+18 |  | DB+9 |  | DB+9 |  | DA+0 |  | DB+9 |  | DA+6 |  | DA+6 |  | DB+9 |  | DB+9 |  | DC+9 |  | DA+0 |  | DD+0
|  |  | 1MRC-4Leg |  | 3MRC-4 Leg |  | 2MRC?? |  |  |  | Pit | [5 empty] | B & RC?? |  | B & RC?? | [5 empty] | Benching
WORK FRONT YET TO BE CLEARED | [12 empty] | ROW | [6 empty] | WORK FRONT YET TO BE CLEARED
| 60/1 |  | 60/2 |  | 60/3 |  | AP61 |  | 61/1 |  | AP62 |  | 62/1 |  | 62/2 |  | 62/3 |  | 62/4 |  | 62/5 |  | AP63 |  | 63/1 |  | AP64
ROW
|  | 431.02 |  | 403.43 |  | 420.36 |  | 446.37 |  | 297.58 |  | 280.47 |  | 272.69 |  | 347.88 |  | 379.25 |  | 398.7 |  | 439.06 | ROW | 360.21 |  | 379.58 |  | 384 | [7 empty] | 0 | 1 | 0
| DA+9 |  | DA+3 |  | DA+9 |  | DC+0 |  | DA+9 |  | DB+0 |  | DA+0 |  | DA+0 |  | DA+9 |  | DA+6 |  | DA+6 |  | DC+0 |  | DA+0 |  | DC+9
[5 empty] | RC 3M-4 Leg | [7 empty] | B Leg A&D,C Leg 1MRC |  |  |  | 3MRC-4 Leg | [11 empty] | 1MRC-4 Leg, A,D Benching,C Leg 1MRC
WORK FRONT YET TO BE CLEARED | [22 empty] | ROW
| 64/1 |  | 64/2 |  | 64/3 |  | 64/4 |  | 64/5 |  | 64/6 |  | 64/7 |  | AP65 |  | 65/1 |  | AP66 |  | 66/1 |  | 66/2 |  | 66/3 |  | 66/4
| ROW | 442 | ROW | 397 |  | 395 |  | 432 |  | 408 |  | 426 |  | 392.95 |  | 431.96 |  | 426.02 |  | 401 |  | 437 |  | 402 |  | 436 |  | 392.28 | [7 empty] | 0 | 1 | 0
| DA+9 |  | DA+9 |  | DA+9 |  | DA+9 |  | DA+9 |  | DA+3 |  | DA+3 |  | DD+0 |  | DB+9 |  | DD+0 |  | DA+9 |  | DA+0 |  | DA+3 |  | DA+9
| 3MRC-4 Leg |  | 1MRC-4 Leg | [15 empty] | 1MRC-4 Leg
| ROW | [13 empty] | ROW | [11 empty] | ROW
| AP67 |  | 67/1 |  | 67/2 |  | AP68 |  | AP69 |  | 69/1 |  | 69/2 |  | 69/3 | AP70 |  | AP71 |  | SH | 71/1 |  | 71/2 |  | 71/3 |  | AP72
|  | 402.5 |  | 411.56 |  | 438.46 |  | 410.36 |  | 379.76 |  | 396.95 |  | 414.59 |  | 352.99 |  | 389.3 |  | 237.59 |  | 290.88 |  | 345.61 |  | 318.63 | U/P | 307.02 | [7 empty] | 1 | 0 | 0
| DC+6 |  | DA+6 |  | DB+0 |  | DB+9 |  | DD+3 |  | DA+6 |  | DA+0 |  | DA+0 |  | DD+0 |  | DB+0 |  | DA+9 |  | DA+0 |  | DA+0 |  | DD+0
| 1MRC-4 Leg | [11 empty] | Bench |  | 1MRC-4 Leg | [9 empty] | 1MRC-4 Leg?? |  | Bench 4 Legs,RC A&C- 3M, B&D- 1M RC
WORK FRONT YET TO BE CLEARED | [21 empty] | WORK FRONT YET TO BE CLEARED
| 72/1 |  | 72/2 |  | AP73 |  | 73/1 |  | 73/2 |  | 73/3 |  | AP74 |  | 74/1 |  | AP75 |  | 75/1 |  | 75/2 |  | 75/3 |  | 75/4 |  | 75/5
|  | 346.85 |  | 300.19 |  | 317 | U/P | 454 |  | 385 |  | 417.69 |  | 409.51 |  | 385.17 |  | 345.19 |  | 332.38 |  | 393.62 |  | 387.95 |  | 340.35 |  | 393.12 | [7 empty] | 1 | 0 | 0
| DA+3 |  | DA+3 |  | DB+0 |  | DA+0 |  | DA+9 |  | DA+9 |  | DB+9 |  | DA+0 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0
Bench A & B, Pit C 1MRC & Pit D 3M RC | [6 empty] | C&D-3MRC | [11 empty] | Bench
| 75/6 |  | 75/7 |  | AP76 |  | 76/1 |  | AP77 |  | 77/1 |  | 77/2 |  | 77/3 |  | 77/4 |  | 77/5 |  | AP78 |  | 78/1 |  | AP79 |  | 79/1
|  | 328.54 |  | 398.52 |  | 425.85 |  | 409.37 |  | 388.46 |  | 380.96 |  | 381.39 |  | 344.6 |  | 395.64 |  | 414.76 |  | 401.93 | ROW | 354.95 |  | 425 |  | 414 | [7 empty] | 0 | 1 | 0
| DA+0 |  | DA+0 |  | DC+0 |  | DA+6 |  | DB+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+6 |  | DC+0 |  | DA+3 |  | DD+0 |  | DA+9
[13 empty] | Bench | [9 empty] | 1MRC
ROW
| 79/2 |  | AP80 |  | 80/1 |  | AP81 |  | 81/1 |  | 81/2 |  | 81/3 |  | 81/4 |  | 81/5 |  | AP82 |  | 82/1 |  | 82/2 |  | AP83 |  | 83/1
|  | 353.05 |  | 441.06 |  | 387.5 |  | 372.63 |  | 415.3 |  | 424.58 |  | 391.7 |  | 410.47 |  | 385.54 |  | 418.31 |  | 421.47 |  | 401.98 |  | 429.38 |  | 403.83 | [7 empty] | 0 | 0 | 0
| DA+0 |  | DB+3 |  | DA+9 |  | DB+9 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+6 |  | DB+3 |  | DA+6 |  | DA+3 |  | DC+0 |  | DA+3
Bench & 1MRC |  |  | 1MRC |  | Bench |  | Bench |  | Bench
[7 empty] | ROW | [17 empty] | ROW
| AP84 |  | AP85 |  | 85/1 |  | AP86 |  | 86/1 |  | 86/2 |  | AP87 |  | 87/1 |  | 87/2 |  | AP88 |  | AP89 |  | 89/1 |  | AP90 |  | 90/1
| U/P | 384.63 |  | 380.682 |  | 354.526 |  | 405.574 |  | 416.874 |  | 380.766 |  | 411.81 |  | 392.08 |  | 296.87 | ROW | 412.4 | ROW | 382.17 | ROW | 452.74 | ROW | 420.21 | ROW | 395.01 | [7 empty] | 1 | 5 | 0
| DC+6 |  | DC+0 |  | DA+0 |  | DD+0 |  | DA+6 |  | DA+0 |  | DC+0 |  | DA+3 |  | DA+9 |  | DC+6 |  | DC+0 |  | DA+9 |  | DC+0 |  | DA+9
WORK FRONT YET TO BE CLEARED
| AP91 |  | 91/1 |  | 91/2 |  | 91/3 |  | AP92 | SH | AP93 |  | AP94 |  | AP95 |  | 95/1 |  | 95/2 |  | AP95A |  | 95A/1 |  | AP96 |  | 96/1
| ROW | 386.74 |  | 378.62 |  | 350.215 | ROW | 357.91 | ROW | 237.48 | ROW | 440.03 |  | 503.74 |  | 437 |  | 430 |  | 409.27 |  | 312.45 |  | 314.25 |  | 361.96 |  | 329.49 | [7 empty] | 0 | 3 | 0
ROW
| DD+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC+0 |  | DC+0 |  | DB+6 |  | DB+9 |  | DB+0 |  | DA+9 |  | DB+0 |  | DA+0 |  | DC+0 |  | DA+0
| ROW | [5 empty] | ROW
| 96/2 |  | AP97 |  | 97/1 |  | AP98 |  | 98/1 |  | AP98A |  | 98A/1 |  | AP98B |  | 98B/1 |  | 98B/2 |  | AP99 |  | 99/1 |  | 99/2 |  | 99/3
|  | 371.33 |  | 417.92 |  | 376.99 |  | 343.8 |  | 318.7 |  | 308 |  | 324.87 |  | 365.39 | ROW | 269.53 | ROW | 360.33 |  | 414 |  | 424 |  | 405 |  | 426 | [7 empty] | 0 | 2 | 0
| DA+0 |  | DC+0 |  | DA+3 |  | DC+0 |  | DA+0 |  | DC+0 |  | DA+0 |  | DD+0 |  | DA+0 |  | DCT+0 |  | DC+0 |  | DA+6 |  | DA+0 |  | DA+3
[5 empty] | 1MRC-4 Leg | [6 empty] | ROW |  |  |  |  | 1MRC-4Leg
ROW
| 99/4 |  | 99A/0 |  | 99B/0 |  | 99C/0 |  | 99C/1 |  | 99C/2 |  | AP100 |  | 100/1 |  | AP101 |  | AP102 |  | 102/1 |  | 102/2 |  | AP103 |  | 103/1
|  | 410 |  | 421 | ROW | 407.61 | ROW | 364.36 | ROW | 332.448 |  | 348.85 | ROW | 387.35 |  | 452.64 | ROW | 386.96 | ROW | 382.14 |  | 336.47 |  | 389.14 | ROW(P) | 334.55 | ROW(P) | 396.2 | [7 empty] | 0 | 6 | 0
| DA+3 |  | DB+6 |  | DD+0 |  | DD+0 |  | DA+6 |  | DA+3 |  | DC+0 |  | DA+6 |  | DD+0 |  | DD+3 |  | DA+0 |  | DA+0 |  | DC+0 |  | DA+6
Bench A&D
[5 empty] | ROW | [7 empty] | ROW |  |  |  | ROW | [7 empty] | ROW
AP104 |  | AP 104A |  |  | AP 104B |  | 104B/1 |  | 104B/2 |  | AP105 |  | 105/1 |  | AP106 |  | AP107 |  | 107/1 |  | AP108 |  | AP 109 | AP 109A |  |  | AP110
|  | 233.29 |  | 467.19 | ROW(P) | 423.02 |  | 248.69 |  | 282.03 |  | 398 |  | 370.48 |  | 437.33 |  | 435 | ROW(P) | 406.62 |  |  | (P) | 440.63 |  | 410.34 |  | 444.33 | [7 empty] | 0 | 0 | 0
| DD+0 |  | DC+9 |  | DB+9 |  | DA+0 |  | DA+0 |  | DD+0 |  | DA+3 |  | DC+6 |  | DD+3 |  | DA+9 |  | DC+0 |  | DC+3 |  | DB+6 |  | DC+0
|  |  | 3MRC-4Leg |  | 3MRC-4Leg | [15 empty] | 1MRC-4Leg
WORK FRONT YET TO BE CLEARED | [15 empty] | WORK FRONT YET TO BE CLEARED
AP111 |  |  | AP112 |  | AP113 |  | AP 113A |  | AP114 |  | 114/1 |  | AP115 |  | 115/1 |  | AP116 |  | 116/1 |  | AP117 |  | 117/1 |  | 117/2 |  | AP118
|  | 189.81 |  | 157.88 | C(P) | 200.69 |  | 165.49 |  | 403.86 |  | 434.79 |  | 425.38 |  | 441.35 |  | 357.54 |  | 438.29 | (P) | 430 |  | 410 |  | 439.98 | (P) | 424.44 | [7 empty] | 0 | 0 | 0
| DB+9 |  | DC+9 |  | DD+0 |  | DC+0 |  | DC+0 |  | DA+9 |  | DC+0 |  | DB+9 |  | DD+0 |  | DA+0 |  | DD+0 |  | DA+3 |  | DB+9 |  | DC+3
| 3MRC | [11 empty] | 1MRC-4 Leg |  |  |  |  | Benching,LegB&C
[5 empty] | ROW | [15 empty] | ROW
AP119 |  |  | 119/1 |  | 119/2 |  | AP120 |  | 120/1 | AP121 |  | NH | AP122 |  | 122/1 |  | 122/2 |  | AP123 |  | AP124 |  | AP125 |  | 125/1 |  | 125/2
|  | 439 |  | 395 |  | 401.11 | ROW | 413 |  | 402.25 |  | 250.69 |  | 425.61 | (P) | 381.68 | (P) | 351.87 |  | 419.36 | (P) | 421.74 |  | 403 |  | 355 |  | 355 | [7 empty] | 0 | 1 | 0
| DD+3 |  | DA+3 |  | DA+3 |  | DC+0 |  | DA+6 |  | DD+0 |  | DC+6 |  | DA+3 |  | DA+3 |  | DC+0 |  | DC+3 |  | DC+3 |  | DA+0 |  | DA+0
[7 empty] | ROW | [6 empty] | WORK FRONT YET TO BE CLEARED | [5 empty] | WORK FRONT YET TO BE CLEARED
| 125/3 |  | AP126 |  | 126/1 |  | 126/2 |  | 126/3 |  | AP127 |  | 127/1 |  | AP128 |  | 128/1 |  | AP129 |  | 129/1 |  | 129/2 |  | AP130 |  | 130/1 | SH
|  | 373.771 |  | 364 |  | 421 |  | 334 | R | 388.22 | R | 398 | C(P) | 442.515 |  | 415 | (P) | 417.97 |  | 424 |  | 415 |  | 412.21 |  | 268 | (P) | 259.27 | [7 empty] | 0 | 0 | 0
| DA+0 |  | DC+6 |  | DA+6 |  | DA+3 |  | DA+6 |  | DD+6 |  | DA+9 |  | DC+3 |  | DA+6 |  | DC+0 |  | DA+3 |  | DA+9 |  | DC+6 |  | DA+0
[9 empty] | ROW | [7 empty] | ROW |  |  |  |  | 3MRC-4 Leg
| AP131 |  | 131/1 |  | 131/2 |  | AP132 |  | 132/1 |  | 132/2 |  | 132/3 |  | 132/4 |  | AP133 |  | 133/1 |  | 133/2 |  | 133/3 |  | 133/4 |  | 133/5
|  | 395 |  | 408 |  | 356 |  | 379 |  | 367 |  | 384 |  | 385 |  | 419.37 |  | 343.49 |  | 392.09 |  | 390.92 |  | 372.24 |  | 388.01 |  | 414.07 | [7 empty] | 0 | 0 | 0
| DD+0 |  | DA+3 |  | DA+3 |  | DD+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0
[17 empty] | A&D 3MRC |  |  |  | 1MRC-4 Leg
[7 empty] | ROW |  |  |  | ROW
| 133/6 |  | 133/7 |  | 133/8 |  | AP134 |  | 134A/0 |  | 134A/1 |  | 134A/2 |  | 134A/3 |  | 134A/4 |  | AP135 |  | 135/1 |  | 135/2 |  | 135/3 |  | AP136 |  | AP137
|  | 410.11 |  | 414.83 |  | 360.43 |  | 226.21 |  | 438.04 |  | 402.74 |  | 433.49 | U/P | 409.21 |  | 436.61 |  | 394.61 |  | 383.9 |  | 356.32 | U/P | 378.3 |  | 356.03 |  | 426.817 | [5 empty] | 2 | 0 | 0
| DA+3 |  | DA+0 |  | DA+6 |  | DD+0 |  | DD+0 |  | DA+9 |  | DA+3 |  | DA+6 |  | DA+9 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DD+0 |  | DB+3
ROW
| AP138 |  | 138/1 |  | 138/2 |  | 138/3 |  | AP139 |  | 139/1 |  | AP140 |  | 140/1 |  | 140/2 |  | 140/3 |  | AP141 |  | 141/1 |  | 141/2 |  | AP142
|  | 381 |  | 334 |  | 347 |  | 375.55 |  | 392 | R | 407.97 | (P) | 392 | R | 405 |  | 435 |  | 378.33 |  | 386 |  | 391 |  | 399.83 |  | 437.01 | [7 empty] | 0 | 0 | 0
| DB+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC+3 |  | DA+9 |  | DB+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DC+0 |  | DA+0 |  | DA+6 |  | DC+3
[9 empty] | 1MRC-4 Leg |  | ROW | [15 empty] | ROW
| AP143 |  | 143/1 |  | 143/2 |  | 143/3 |  | 143/4 |  | 143/5 |  | 143/6 |  | 143/7 |  | AP144 |  | AP145 |  | 145/1 |  | 145/2 |  | 145/3 |  | 145/4
|  | 401.76 |  | 416.24 |  | 417 |  | 399 |  | 420 |  | 409 |  | 412 |  | 400.41 |  | 232.12 |  | 442 |  | 385 |  | 362 |  | 399 |  | 382.07 | [7 empty] | 0 | 0 | 0
| DC+3 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DD+6 |  | DD+6 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+3
| AP146 |  | 146/1 |  | 146/2 |  | AP147 |  | 147/1 |  | 147/2 |  | 147/3 |  | 147/4 |  | 147/5 |  | 147/6 |  | 147/7 |  | 147/8 |  | 147/9 | SH | AP148
|  | 392 |  | 422 |  | 409.46 |  | 373.69 |  | 381.62 |  | 381.82 |  | 391.44 |  | 385.78 |  | 367.45 |  | 379.63 |  | 380.46 |  | 382.98 |  | 241.5 | ROW | 363.92 | [7 empty] | 0 | 1 | 0
| DC+0 |  | DA+3 |  | DA+0 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB+0
ROW
| 148/1 |  | 148/2 |  | 148/3 |  | 148/4 |  | 148/5 |  | 148/6 |  | 148/7 |  | AP149 |  | 149A/0 |  | AP149B/0 |  | 149B/1 |  | 149B/2 |  | 149B/3 |  | AP150 |  | AP151
|  | 359.14 |  | 384.88 |  | 381.91 |  | 397.15 |  | 387.13 |  | 392.12 |  | 364.62 |  | 188.37 |  | 395.54 |  | 425 |  | 407 |  | 433 | U/P | 489.23 | C | 290 |  | 419.403 | [5 empty] | 1 | 0 | 1
| DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DD+0 |  | DD+0 |  | DB+3 |  | DA+3 |  | DA+0 |  | DB+9 |  | DD+9 |  | DD+9
UNDER HOLD
| AP152 |  | AP153 |  | AP153A |  | AP154 |  | AP155 |  | AP156 |  | AP157 |  | GANTRY |  |  |  | 1 | Total Locations
[19 empty] | 2 | Completed Locations | [8 empty] | 0
[19 empty] | 3 | Work in Progress
|  | 242.63 | U/P | 342.727 |  | 389.221 |  | 220.253 |  | 241.312 |  | 214.902 |  | 113.742 |  |  |  |  | 4 | ROW Cleared Locations | [15 empty] | 1 | 0 | 0
[19 empty] | 5 | Not Cleared due to D/S & C/S Approval | [8 empty] | 0 | [6 empty] | 9 | 21 | 2
| DD+18 |  | DD+18 |  | DB+0 |  | DD+0 |  | DD+0 |  | DD+9 |  | DD+0 | [5 empty] | 6 | Hold Due to Major Crossing & Others | [15 empty] | U/P | ROW | CLEAR
|  |  | ROW | [5 empty] | UNDER HOLD | [9 empty] | 7 | ROW Not Cleared
R

## VC (hidden)
52
2026-03-20 10:53
Name of Contractor:M/S KEC INTERNATIONAL LIMITED
PROGRESS AT A GLANCE :
[18 empty] | Stringing WIP |  |  |  | Stringing Completed
Sl. No. |  | Activity |  |  | UoM |  | Total Qty |  |  | Completed Till Date |  |  | Balance | [15 empty] | River Crossing
1 |  | Detail survey |  |  | Kms. |  | 187.175 |  |  | 187.175 |  |  | 0 |  |  | Oil pipeline
2 |  | Check survey |  |  | Kms. |  | 187.175 |  |  | 169.168 |  |  | 18.007 |  |  | Gas pipeline
3 |  | Soil Investigation |  |  | Loc |  | 73 |  |  | 73 |  |  | 0
4 |  | Foundation |  |  | Loc |  | 495 |  |  | 79 |  |  | 416 | [12 empty] | Erection WIP
5 |  | Earthing |  |  | Nos. |  | 497 |  |  | 61 |  |  | 436 |  |  |  |  | Erection Comp |  |  | Span | [8 empty] | Railway Crossing
6 |  | Erection |  |  | Loc |  | 495 | [5 empty] | 495 |  |  |  |  | Earthing
7 |  | Tack Welding |  |  | Nos. |  | 405 | [5 empty] | 405
8 |  | Stringing(Paying out) |  |  | Kms. |  | 187.175 | [5 empty] | 187.175 | [9 empty] | Excavation
9 |  | Stringing (Final Sag) |  |  | Kms. |  | 187.175 | [5 empty] | 187.175 | [11 empty] | NH/SH |  | 66/132/ 220/400KV
| 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14
| GNT |  | AP1 |  | AP1A |  | AP2 |  | AP3 |  | 3/1 |  | 3/2 |  | 3/3 |  | AP4 |  | 4/1 |  | 4/2 |  | 4/3 |  | 4/4 |  | 4/5 |  |  |  | T | F | EA | ER | Length | TW
|  | 96.534 |  | 114.097 |  | 290.581 |  | 214.485 |  | 451.783 |  | 419.226 |  | 420.01 |  | 416.531 |  | 356.262 |  | 343.074 |  | 381.329 |  | 373.323 |  | 246.012 |  | 249.424 |  |  | 13
|  |  | DD+0 |  | DD+3 |  | DD+25 |  | DD+25 |  | DB+6 |  | DA+0 |  | DA+9 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+6 |  | DA+3 |  | DB+0
| 4/6 |  | 4/7 |  | 4/8 |  | 4/9 |  | AP5 |  | AP6 |  | 6/1 |  | 6/2 |  | 6/3 |  | 6/4 |  | 6/5 |  | 6/6 |  | 6/7 |  | AP7
[31 empty] | T | F | EA | ER | Length | TW
|  | 399.707 |  | 438.616 |  | 400.604 |  | 438.765 |  | 226.315 |  | 442.553 |  | 389.329 |  | 359.361 |  | 405.006 |  | 426.518 |  | 356.055 |  | 369.295 |  | 374.993 |  | 383.768 |  |  | 14
| DA+0 |  | DA+6 |  | DA+6 |  | DA+3 |  | DD+18 |  | DD+18 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB+0
| 7/1 |  | 7/1 |  | 7/2 |  | 7/3 |  | 7/4 |  | 7/5 |  | 7/6 |  | 7/7 |  | 7/8 |  | 7/9 |  | 7/10 |  | AP8 |  | 8/1 |  | 8/2
[31 empty] | T | F | EA | ER | Length | TW
|  | 383.768 |  | 396.38 |  | 392.534 |  | 332.162 |  | 352.112 |  | 389.393 |  | 374.477 |  | 419.977 |  | 387.899 |  | 407.654 |  | 402.357 |  | 372.259 |  | 410.949 |  | 379.075 |  |  | 14
| DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DB+0 |  | DA+0 |  | DA+0
| 8/3 |  | 8/4 |  | AP9 |  | 9/1 |  | 9/2 |  | 9/3 |  | 9/4 |  | 9/5 |  | AP10 |  | 10/1 |  | 10/2 |  | 10/3 |  | 10/4 |  | 10/5
[31 empty] | T | F | EA | ER | Length | TW
|  | 412.596 |  | 340.112 |  | 410.76 |  | 427.9 |  | 404.21 |  | 398.446 |  | 431.939 |  | 486.196 |  | 369.717 |  | 389.344 |  | 395.602 |  | 372.377 |  | 431.547 |  | 370.651 |  |  | 14
| DA+0 |  | DA+3 |  | DB+0 |  | DA+0 |  | DA+6 |  | DA+0 |  | DA+3 |  | DB+9 |  | DC+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+6 |  | DA+0
| 10/6 |  | 10/7 |  | 10/8 |  | 10/9 |  | 10/10 |  | 10/11 |  | 10/12 |  | 10/13 |  | 10/14 |  | 10/15 |  | AP11 |  | 11/1 |  | 11/2 |  | 11/3
[31 empty] | T | F | EA | ER | Length | TW
|  | 345.352 |  | 381.912 |  | 366.819 |  | 424.002 |  | 400.126 |  | 403.795 |  | 437.705 |  | 399.87 |  | 437.786 |  | 378.362 |  | 433.995 |  | 370.685 |  | 323.972 |  | 384.462 |  |  | 14
| DA+0 |  | DA+0 |  | DA+0 |  | DB+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+6 |  | DB+0 |  | DA+3 |  | DA+0 |  | DA+0
| 11/4 |  | 11/5 |  | 11/6 |  | AP12 |  | 12/1 |  | 12/2 |  | AP13 |  | 13/1 |  | 13/2 |  | 13/3 |  | AP14 |  | 14/1 |  | AP15 |  | 15/1
[31 empty] | T | F | EA | ER | Length | TW
|  | 381.188 |  | 336.409 |  | 438.97 |  | 395.179 |  | 388.12 |  | 364.446 |  | 404.572 |  | 432.27 |  | 404.23 |  | 416.621 |  | 468.039 |  | 432.318 |  | 464.521 |  | 369.743 |  |  | 14
| DA+0 |  | DA+0 |  | DA+0 |  | DB+0 |  | DA+0 |  | DA+3 |  | DC+0 |  | DA+9 |  | DA+6 |  | DA+3 |  | DB+0 |  | DB+9 |  | DC+9 |  | DA+6
| AP16 |  | 16/1 |  | AP17 |  | 17/1 |  | AP18 |  | 18/1 |  | AP19 |  | 19/1 |  | 19/2 |  | 19/3 |  | AP20 |  | 20/1 |  | 20/2 |  | 20/3
[31 empty] | T | F | EA | ER | Length | TW
|  | 284.16 |  | 270.742 |  | 286.64 |  | 291.699 |  | 398.719 |  | 425.465 |  | 383.813 |  | 403.279 |  | 355.215 |  | 399.839 |  | 287.442 |  | 390.748 |  | 364.274 |  | 337.546 |  |  | 14
| DD+0 |  | DA+0 |  | DB+0 |  | DA+0 |  | DC+0 |  | DA+6 |  | DD+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+0
| 20/4 |  | 20/5 |  | 20/6 |  | AP21 |  | 21/1 |  | 21/2 |  | AP22 |  | AP23 |  | 23/1 |  | 23/2 |  | 23/3 |  | AP24 |  | 24/1 |  | AP25
[31 empty] | T | F | EA | ER | Length | TW
|  | 348.292 |  | 418.835 |  | 408.963 |  | 365.467 |  | 437.074 |  | 363.142 |  | 159.789 |  | 300.158 |  | 293.131 |  | 357.377 |  | 341.409 |  | 362.905 |  | 421.052 |  | 216.448 |  |  | 14
| DA+0 |  | DA+3 |  | DA+9 |  | DD+3 |  | DA+0 |  | DA+6 |  | DB+3 |  | DD+0 |  | DB+3 |  | DA+0 |  | DA+0 |  | DC+9 |  | DA+9 |  | DD+30
| AP26 |  | AP27 |  | AP27A |  | 27A/1 |  | 27A/2 |  | 27A/3 |  | AP27B |  | 27B/1 |  | 27B/2 |  | 27B/3 |  | AP28 |  | 28/1 |  | 28/2 |  | AP29
[31 empty] | T | F | EA | ER | Length | TW
|  | 439.695 |  | 243.188 |  | 333.219 |  | 363.001 |  | 356.124 |  | 511.692 |  | 376.245 |  | 381.122 |  | 364.433 |  | 263.077 |  | 356.193 |  | 352.42 |  | 460.564 |  | 381.028 |  |  | 14
| DD+30 |  | DC+0 |  | DD+0 |  | DA+3 |  | DA+3 |  | DB+0 |  | DB+0 |  | DA+0 |  | DA+3 |  | DA+9 |  | DD+6 |  | DA+0 |  | DB+9 |  | DC+6
| 29/1 |  | 29/2 |  | AP30 |  | 30/1 |  | 30/2 |  | 30/3 |  | AP31 |  | AP32 |  | 32/1 |  | 32/2 |  | 32/3 |  | AP33 |  | AP34 |  | 34/1
[31 empty] | T | F | EA | ER | Length | TW
|  | 419.603 |  | 425.18 |  | 287.537 |  | 336.512 |  | 325.304 |  | 214.253 |  | 455.946 |  | 421 |  | 419 |  | 408 |  | 409.749 |  | 324.03 |  | 366.7 |  | 473.305 |  |  | 14
| DA+3 |  | DA+9 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC+9 |  | DC+9 |  | DA+3 |  | DA+3 |  | DA+9 |  | DB+0 |  | DC+6 |  | DA+9
| AP35 |  | 35/1 |  | AP36 |  | 36/1 |  | 36/2 |  | 36A |  | AP37 |  | 37/1 |  | AP38 |  | 38/1 |  | 38/2 |  | 38/3 |  | AP39 |  | 39/1 |  | 39/2
[31 empty] | T | F | EA | ER | Length | TW
|  | 358.321 |  | 477.815 |  | 415.464 |  | 402.229 |  | 437.434 |  |  |  | 455.922 |  | 368.5 |  | 419.765 |  | 418.917 |  | 386.486 |  | 376.53 |  | 404.739 |  | 366.729 |  | 274.587 | 14
| DC+9 |  | DA+9 |  | DC+9 |  | DA+9 |  | DA+9 |  | DD+0 |  | DD+0 |  | DA+6 |  | DB+0 |  | DA+6 |  | DA+9 |  | DA+3 |  | DB+3 |  | DA+6 |  | DA+0
| 39/3 |  | 39/4 |  | 39/5 |  | AP40 |  | 40/1 |  | 40/2 |  | AP41 |  | 41/1 |  | 41/2 |  | 41/3 |  | AP42 |  | 42/1 |  | 42/2 |  | 42/3
[31 empty] | T | F | EA | ER | Length | TW
|  | 341.668 |  | 425.863 |  | 394.307 |  | 370.45 |  | 436.754 |  | 397.605 |  | 413.401 |  | 423.645 |  | 415.968 |  | 415.349 |  | 394.875 |  | 429.62 |  | 381.905 |  | 405.26 |  |  | 14
| DA+0 |  | DA+0 |  | DA+6 |  | DD+3 |  | DB+6 |  | DA+6 |  | DB+0 |  | DA+9 |  | DA+0 |  | DA+9 |  | DC+3 |  | DA+9 |  | DCT+6 |  | DA+9
| 42/4 |  | 42/5 |  | 42/6 |  | 42/7 |  | AP43 |  | AP44 |  | 44/1 |  | AP45 |  | 45/1 |  | 45/2 |  | 45/3 |  | 45/4 |  | AP46 |  | AP47
[31 empty] | T | F | EA | ER | Length | TW
s
|  | 338.156 |  | 288.303 |  | 297.148 |  | 195.903 |  | 249.66 |  | 374.475 |  | 443.95 |  | 404.386 |  | 341.423 |  | 305.401 |  | 319.981 |  | 345.621 |  | 223.151 |  | 393.817 |  |  | 14
| DA+9 |  | DA+0 |  | DA+3 |  | DA+0 |  | DC+6 |  | DB+9 |  | DA+9 |  | DD+9 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+6 |  | DD+3 |  | DD+9
| 47/1 |  | 47/2 |  | AP48 |  | AP49 |  | AP50 |  | AP51 |  | 51/1 |  | 51/2 |  | 51/3 |  | AP52 |  | 52/1 |  | AP53 |  | AP54 |  | 54/1
[31 empty] | T | F | EA | ER | Length | TW
|  | 435.136 |  | 403.209 |  | 422.554 |  | 353.484 |  | 274.899 |  | 465.033 |  | 373.977 |  | 416.864 |  | 381.019 |  | 391.519 |  | 374.934 |  | 248.567 |  | 384.17 |  | 330.764 |  |  | 14 | 1
| DA+9 |  | DA+9 |  | DD+3 |  | DD+3 |  | DD+9 |  | DD+18 |  | DA+3 |  | DA+0 |  | DA+3 |  | DB+0 |  | DA+6 |  | DD+0 |  | DC+0 |  | DA+3
[19 empty] | RC 3M |  | RC 1M
| 54/2 |  | 54/3 |  | AP55 |  | AP56 |  | 56/1 |  | 56/2 |  | 56/3 |  | 56/4 |  | 56/5 |  | AP57 |  | AP58 |  | AP59 |  | 59/1 |  | AP60
[31 empty] | T | F | EA | ER | Length | TW
|  | 285.319 |  | 354.7 |  | 420.541 |  | 340.559 |  | 336.519 |  | 375.992 |  | 308.407 |  | 444.838 |  | 392.016 |  | 407.803 |  | 206.062 |  | 417.384 |  | 304.564 |  | 395.509 |  |  | 14
| DA+6 |  | DA+3 |  | DD+18 |  | DB+9 |  | DB+9 |  | DA+0 |  | DB+9 |  | DA+6 |  | DA+6 |  | DB+9 |  | DB+9 |  | DC+9 |  | DA+0 |  | DD+0
| RC 1M |  | RC 1M |  | RC 3M |  | RC 3M | [11 empty] | RC 1M & 3M
| 60/1 |  | 60/2 |  | 60/3 |  | AP61 |  | 61/1 |  | AP62 |  | 62/1 |  | 62/2 |  | 62/3 |  | 62/4 |  | 62/5 |  | AP63 |  | 63/1 |  | AP64
[31 empty] | T | F | EA | ER | Length | TW
|  | 431.017 |  | 403.426 |  | 420.357 |  | 446.37 |  | 297.577 |  | 240.473 |  | 312.687 |  | 347.884 |  | 379.249 |  | 398.697 |  | 439.062 |  | 360.21 |  | 399.579 |  | 364 |  |  | 14
| DA+9 |  | DA+3 |  | DA+9 |  | DC+0 |  | DA+9 |  | DB+0 |  | DA+0 |  | DA+0 |  | DA+9 |  | DA+6 |  | DA+6 |  | DC+0 |  | DA+0 |  | DC+9
[5 empty] | RC 3M | [7 empty] | RC 1M |  |  |  | RC 3M | [9 empty] | RC 1M
| 64/1 |  | 64/2 |  | 64/3 |  | 64/4 |  | 64/5 |  | 64/6 |  | 64/7 |  | AP65 |  | 65/1 |  | AP66 |  | 66/1 |  | 66/2 |  | 66/3 |  | 66/4
[31 empty] | T | F | EA | ER | Length | TW
|  | 442 |  | 397 |  | 395 |  | 432 |  | 408 |  | 426 |  | 392.954 |  | 431.957 |  | 426.02 |  | 401 |  | 437 |  | 402 |  | 436 |  | 392.283 |  |  | 14 | 8 | 2
| DA+9 |  | DA+9 |  | DA+9 |  | DA+9 |  | DA+9 |  | DA+3 |  | DA+3 |  | DD+0 |  | DB+9 |  | DD+0 |  | DA+9 |  | DA+0 |  | DA+3 |  | DA+9
| RC 3M |  | RC 1M | [15 empty] | RC 1M
| AP67 |  | 67/1 |  | 67/2 |  | AP68 |  | AP69 |  | 69/1 |  | 69/2 |  | 69/3 |  | AP70 |  | AP71 |  | 71/1 |  | 71/2 |  | 71/3 |  | AP72
[31 empty] | T | F | EA | ER | Length | TW
|  | 402.5 |  | 411.557 |  | 438.461 |  | 410.356 |  | 379.755 |  | 396.947 |  | 414.594 |  | 352.994 |  | 389.303 |  | 237.59 |  | 290.877 |  | 345.605 |  | 318.63 |  | 307.017 |  |  | 14
| DC+6 |  | DA+6 |  | DB+0 |  | DB+9 |  | DD+3 |  | DA+6 |  | DA+0 |  | DA+0 |  | DD+0 |  | DB+0 |  | DA+9 |  | DA+0 |  | DA+0 |  | DD+0
| RC 1M | [13 empty] | RC 1M | [9 empty] | RC 1M |  | RC 1M & 3M
| 72/1 |  | 72/2 |  | AP73 |  | 73/1 |  | 73/2 |  | 73/3 |  | AP74 |  | 74/1 |  | AP75 |  | 75/1 |  | 75/2 |  | 75/3 |  | 75/4 |  | 75/5
[31 empty] | T | F | EA | ER | Length | TW
|  | 346.846 | u/p | 300.193 | u/p | 317 |  | 454 |  | 385 |  | 417.688 |  | 409.505 |  | 385.169 |  | 345.191 |  | 332.383 |  | 393.622 |  | 387.948 |  | 340.348 |  | 393.121 |  |  | 14 | 8 | 7
| DA+3 |  | DA+3 |  | DB+0 |  | DA+0 |  | DA+9 |  | DA+9 |  | DB+9 |  | DA+0 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0
| RC 1M & 3M | [5 empty] | RC 3M
| 75/6 |  | 75/7 |  | AP76 |  | 76/1 |  | AP77 |  | 77/1 |  | 77/2 |  | 77/3 |  | 77/4 |  | 77/5 |  | AP78 |  | 78/1 |  | AP79 |  | 79/1
[31 empty] | T | F | EA | ER | Length | TW
|  | 328.536 |  | 398.515 |  | 425.848 |  | 409.369 |  | 388.455 |  | 380.961 |  | 381.389 |  | 344.595 |  | 395.641 |  | 414.763 |  | 401.929 |  | 354.949 |  | 425 |  | 414 |  |  | 14 | 9 | 9
| DA+0 |  | DA+0 |  | DC+0 |  | DA+6 |  | DB+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+6 |  | DC+0 |  | DA+3 |  | DD+0 |  | DA+9
RC 1M
| 79/2 |  | AP80 |  | 80/1 |  | AP81 |  | 81/1 |  | 81/2 |  | 81/3 |  | 81/4 |  | 81/5 |  | AP82 |  | 82/1 |  | 82/2 |  | AP83 |  | 83/1
[31 empty] | T | F | EA | ER | Length | TW
|  | 353.052 |  | 441.055 |  | 387.495 |  | 372.627 |  | 415.304 |  | 424.584 |  | 391.704 |  | 410.466 |  | 385.541 |  | 418.313 |  | 421.473 |  | 401.979 | ROW | 429.379 |  | 403.832 |  |  | 14 | 2 | 2
| DA+0 |  | DB+3 |  | DA+9 |  | DB+9 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+6 |  | DB+3 |  | DA+6 |  | DA+0 |  | DC+0 |  | DA+3
| RC 1M |  | RC 1M | [5 empty] | RC 3M
| AP84 |  | AP85 |  | 85/1 |  | AP86 |  | 86/1 |  | 86/2 |  | AP87 |  | 87/1 |  | 87/2 |  | AP88 |  | AP89 |  | 89/1 |  | AP90 |  | 90/1
[31 empty] | T | F | EA | ER | Length | TW
|  | 384.63 |  | 380.682 |  | 354.526 | u/p | 405.574 |  | 416.874 |  | 380.766 |  | 411.814 |  | 392.08 |  | 296.873 |  | 412.399 |  | 382.173 |  | 452.737 |  | 420.207 |  | 395.011 |  |  | 14 | 5
| ROW |  | ROW
| DC+6 |  | DC+0 |  | DA+0 |  | DD+0 |  | DA+6 |  | DA+0 |  | DC+0 |  | DA+3 |  | DA+9 |  | DC+0 |  | DC+0 |  | DA+9 |  | DC+0 |  | DA+9
| AP91 |  | 91/1 |  | 91/2 |  | 91/3 |  | AP92 |  | AP93 |  | AP94 |  | AP95 |  | 95/1 |  | 95/2 |  | AP95A |  | 95A/1 |  | AP96 |  | 96/1
[31 empty] | T | F | EA | ER | Length | TW
|  | 386.735 |  | 378.624 |  | 350.215 |  | 357.906 |  | 237.476 |  | 440.03 |  | 503.74 | u/p | 437 | U/P | 430 |  | 409.273 |  | 312.446 |  | 314.247 |  | 361.96 |  | 329.486 |  |  | 14 | 2 | 2
| DD+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC+0 |  | DC+0 |  | DB+6 |  | DB+6 |  | DB+0 |  | DA+9 |  | DB+0 |  | DA+0 |  | DC+0 |  | DA+0
| 96/2 |  | AP97 |  | 97/1 |  | AP98 |  | 98/1 |  | AP98A |  | 98A/1 |  | AP98B |  | 98B/1 |  | 98B/2 |  | AP99 |  | 99/1 |  | 99/2 |  | 99/3
[31 empty] | T | F | EA | ER | Length | TW
|  | 371.327 |  | 417.917 |  | 376.988 | U/P | 343.797 |  | 318.696 |  | 308 |  | 324.874 | U/P | 365.391 |  | 269.525 |  | 350.326 |  | 414 |  | 424 |  | 405 |  | 426 |  |  | 14 | 4 | 2
[7 empty] | ROW | [7 empty] | ROW
| DA+0 |  | DC+0 |  | DA+3 |  | DC+0 |  | DA+0 |  | DC+0 |  | DA+0 |  | DD+0 |  | DA+0 |  | DCT+0 |  | DC+0 |  | DA+6 |  | DA+0 |  | DA+3
[5 empty] | RC 1M | [11 empty] | RC 1M | [9 empty] | RC 3M
| 99/4 |  | 99A/0 |  | 99B/0 |  | AP99C/0 |  | 99C/1 |  | 99C/2 |  | AP100 |  | 100/1 |  | AP101 |  | AP102 |  | 102/1 |  | 102/2 |  | AP103 |  | 103/1
[31 empty] | T | F | EA | ER | Length | TW
|  | 410 |  | 421 |  | 407.607 |  | 364.364 |  | 332.448 |  | 348.853 |  | 387.348 |  | 452.637 |  | 386.957 |  | 382.143 |  | 336.469 |  | 389.14 |  | 334.554 |  | 396.198 |  |  | 14
| DA+3 |  | DB+6 |  | DD+0 |  | DD+0 |  | DA+6 |  | DA+3 |  | DC+0 |  | DA+6 |  | DD+0 |  | DD+3 |  | DA+0 |  | DA+0 |  | DC+0 |  | DA+6
| AP104 |  | AP104A |  | AP104B |  | 104B/1 |  | 104B/2 |  | AP105 |  | 105/1 |  | AP106 |  | AP107 |  | 107/1 |  | AP108 |  | AP109 |  | AP109A |  | AP110
[31 empty] | T | F | EA | ER | Length | TW
|  | 233.292 |  | 467.189 |  | 423.018 |  | 248.691 |  | 282.025 |  | 398 |  | 370.48 | u/p | 437.333 |  | 435 |  | 406.615 |  | 388.494 |  | 440.626 |  | 410.342 |  | 444.331 |  |  | 14
| DD+0 |  | DC+9 |  | DB+9 |  | DA+0 |  | DA+0 |  | DD+0 |  | DA+3 |  | DC+6 |  | DD+3 |  | DA+9 |  | DC+0 |  | DC+3 |  | DB+6 |  | DC+0
|  |  | RC 3M |  | RC 3M | [15 empty] | RC 1M
| AP111 |  | AP112 |  | AP113 |  | AP113A |  | AP114 |  | 114/1 |  | AP115 |  | 115/1 |  | AP116 |  | 116/1 |  | AP117 |  | 117/1 |  | 117/2 |  | AP118
[31 empty] | T | F | EA | ER | Length | TW
|  | 189.805 |  | 157.883 |  | 200.685 |  | 165.49 | U/P | 403.859 |  | 434.788 |  | 425.384 |  | 441.345 |  | 357.543 |  | 438.293 |  | 430 |  | 410 |  | 439.976 |  | 424.44 |  |  | 14
| DB+9 |  | DC+9 |  | DD+0 |  | DC+0 |  | DC+0 |  | DA+9 |  | DC+0 |  | DB+9 |  | DD+0 |  | DA+0 |  | DD+0 |  | DA+3 |  | DB+9 |  | DC+3
| RC 3M |  | RC 3M | [9 empty] | RC 1M
| AP119 |  | 119/1 |  | 119/2 |  | AP120 |  | 120/1 |  | AP121 |  | AP122 |  | 122/1 |  | 122/2 |  | AP123 |  | AP124 |  | AP125 |  | 125/1 |  | 125/2
T
|  | 439 |  | 395 |  | 401.113 |  | 413 |  | 402.253 |  | 250.694 |  | 425.612 |  | 381.675 |  | 351.869 |  | 419.361 |  | 421.739 |  | 403 |  | 355 |  | 355 |  |  | 14
| DD+3 |  | DA+3 |  | DA+3 |  | DC+0 |  | DA+6 |  | DD+0 |  | DC+6 |  | DA+3 |  | DA+3 |  | DC+0 |  | DC+3 |  | DC+3 |  | DA+0 |  | DA+0
| 125/3 |  | AP126 |  | 126/1 |  | 126/2 |  | 126/3 |  | AP127 |  | 127/1 |  | AP128 |  | 128/1 |  | AP129 |  | 129/1 |  | 129/2 |  | AP130 |  | 130/1
[31 empty] | T | F | EA | ER | Length | TW
|  | 373.771 |  | 364 |  | 421 |  | 334 |  | 388.22 |  | 398 |  | 442.515 |  | 415 |  | 417.968 |  | 424 |  | 415 |  | 412.205 |  | 278 |  | 249.272 |  |  | 14
| DA+0 |  | DC+0 |  | DA+6 |  | DA+3 |  | DA+6 |  | DD+6 |  | DA+9 |  | DC+3 |  | DA+6 |  | DC+0 |  | DA+3 |  | DA+9 |  | DC+6 |  | DA+0
| AP131 |  | 131/1 |  | 131/2 |  | AP132 |  | 132/1 |  | 132/2 |  | 132/3 |  | 132/4 |  | AP133 |  | 133/1 |  | 133/2 |  | 133/3 |  | 133/4 |  | 133/5
T
|  | 395 |  | 408 |  | 352.002 |  | 373.572 |  | 367 |  | 384 |  | 385 |  | 419.368 |  | 288 |  | 404 |  | 413 |  | 414 |  | 414 |  | 425 |  |  | 14
| DD+0 |  | DA+3 |  | DA+3 |  | DD+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0
1MRC
| 133/6 |  | 133/7 |  | 133/8 |  | AP134 |  | 134A/0 |  | 134A/1 |  | 134A/2 |  | 134A/3 |  | 134A/4 |  | AP135 |  | 135/1 |  | 135/2 |  | 135/3 |  | AP136 |  | AP137
[31 empty] | T | F | EA | ER | Length | TW
|  | 410.108 |  | 414.825 |  | 360.431 |  | 226 |  | 438.037 |  | 402.737 |  | 433.49 |  | 409.206 |  | 436.605 |  | 394.613 |  | 383.901 |  | 356.322 |  | 378.301 |  | 356.028 |  |  | 14
| DA+3 |  | DA+0 |  | DA+6 |  | DD+0 |  | DD+0 |  | DA+9 |  | DA+3 |  | DA+6 |  | DA+9 |  | DC+0 |  | DA+0 |  | DA+3 |  | DA+6 |  | DD+0 |  | DB+3
| AP138 |  | 138/1 |  | 138/2 |  | 138/3 |  | AP139 |  | 139/1 |  | AP140 |  | 140/1 |  | 140/2 |  | 140/3 |  | AP141 |  | 141/1 |  | 141/2 |  | AP142
T
|  | 381 |  | 334 |  | 347 |  | 375.546 |  | 392 |  | 407.974 |  | 392 |  | 405 |  | 435 |  | 378.328 |  | 386 |  | 391 |  | 399.827 |  | 437.008 |  |  | 14
| DB+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC+3 |  | DA+9 |  | DB+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DC+0 |  | DA+0 |  | DA+6 |  | DC+3
| AP143 |  | 143/1 |  | 143/2 |  | 143/3 |  | 143/4 |  | 143/5 |  | 143/6 |  | 143/7 |  | AP144 |  | AP145 |  | 145/1 |  | 145/2 |  | 145/3 |  | 145/4
T
|  | 401.757 |  | 416.243 |  | 417 |  | 399 |  | 420 |  | 409 |  | 412 |  | 400.406 |  | 232.123 |  | 442 |  | 385 |  | 362 |  | 399 |  | 382.072 |  |  | 14
| DC+3 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DD+6 |  | DD+6 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+3
| AP146 |  | 146/1 |  | 146/2 |  | AP147 |  | 147/1 |  | 147/2 |  | 147/3 |  | 147/4 |  | 147/5 |  | 147/6 |  | 147/7 |  | 147/8 |  | 147/9 |  | AP148
T
|  | 392 | u/p | 422 |  | 409.457 |  | 373.694 |  | 381.617 |  | 381.822 |  | 391.436 |  | 385.784 |  | 367.452 |  | 379.63 |  | 380.459 | U/P | 382.979 |  | 241.496 |  | 403 |  |  | 14
| DC+0 |  | DA+3 |  | DA+0 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB+0
| 148/1 |  | 148/2 |  | 148/3 |  | 148/4 |  | 148/5 |  | 148/6 |  | 148/7 |  | AP149 |  | 149A/0 |  | AP149B/0 |  | 149B/1 |  | 149B/2 |  | 149B/3 |  | AP150 |  | AP151
T
|  | 359.142 |  | 384.878 |  | 381.905 |  | 397.152 |  | 387.131 |  | 392.124 |  | 364.623 |  | 188.369 |  | 396 |  | 425 |  | 407 |  | 433 |  | 489.23 |  | 419.403 |  |  | 14
| DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DD+0 |  | DD+0 |  | DB+3 |  | DA+3 |  | DA+0 |  | DB+9 |  | DD+9 |  | DD+9
| AP152 |  | AP153 |  | AP153A |  | AP154 |  | AP155 |  | AP156 |  | AP157 |  | GNT
T
|  | 242.63 |  | 342.727 |  | 389.221 |  | 220.253 |  | 241.312 |  | 214.902 |  | 113.742 | [16 empty] | 7
| DD+18 |  | DD+18 |  | DB+6 |  | DD+30 |  | DD+30 |  | DD+9 |  | DD+0
T
[31 empty] | 496 | 39 | 24

## Sheet6 (hidden)
SL No | Loc No | TOT | Classificatin | M-10 | M-20
1 | 83/1 | DA+3 | Sandy | 1.86 | 12.47
2 | 75/7 | DA+0 | Sandy | 1.57 | 11.05
3 | 75/6 | DA+0 | Sandy | 1.57 | 11.05
4 | 75/5 | DA+0 | Sandy | 1.57 | 11.05
5 | 75/4 | DA+0 | Sandy | 1.57 | 11.05
6 | 75/3 | DA+3 | Sandy | 1.86 | 12.47
7 | 75/1 | DA+0 | Sandy | 1.57 | 11.05
8 | 75/2 | DA+0 | Sandy | 1.57 | 11.05
9 | 77/1 | DA+0 | Sandy | 1.57 | 11.05
10 | 77/2 | DA+3 | Sandy | 1.86 | 12.47
11 | 77/3 | DA+0 | Sandy | 1.57 | 11.05
12 | 77/4 | DA+3 | Sandy | 1.86 | 12.47
13 | 77/5 | DA+6 | Sandy | 1.86 | 12.47
14 | 73/3 | DA+9 | Sandy | 1.86 | 12.47
15 | 86/2 | DA+0 | Sandy | 1.57 | 11.05
16 | 79/1 | DA+9 | Sandy | 1.86 | 12.47
17 | 95A/1 | DA+0 | DFR | 1.08 | 8.68
18 | 73/2 | DA+9 | Sandy | 1.86 | 12.47
19 | 66/1 | DA+9 | Sandy | 1.86 | 12.47
20 | 80/1 | DA+9 | Sandy | 1.86 | 12.47
21 | 86/1 | DA+6 | Sandy | 1.86 | 12.47
22 | 76/1 | DA+6 | Sandy | 1.86 | 12.47
23 | 74/1 | DA+0 | Sandy | 1.57 | 11.05
24 | 96/1 | DA+0 | Sandy | 1.57 | 11.05
25 | 99/1 | DA+6 | Sandy | 1.86 | 12.47
26 | 66/2 | DA+0 | Sandy | 1.57 | 11.05
27 | 96/2 | DA+0 | Sandy | 1.57 | 11.05
28 | 81/2 | DA+3 | Sandy | 1.86 | 12.47
29 | 64/3 | DA+9 | Sandy | 1.86 | 12.47
30 | 66/3 | DA+9 | Sandy | 1.86 | 12.47
31 | 64/4 | DA+9 | Sandy | 1.86 | 12.47
32 | 85/1 | DA+0 | Sandy | 1.57 | 11.05
33 | 87/1 | DA+3 | Sandy | 1.86 | 12.47
34 | 64/7 | DA+3 | Sandy | 1.86 | 12.47
35 | 98A/1 | DA+0 | DFR | 1.08 | 8.68 |  | ]]
36 | 87/2 | DA+9 | Sandy | 1.86 | 12.47
37 | 64/6 | DA+3 | Sandy | 1.86 | 12.47
38 | 64/5 | DA+9 | Sandy | 1.86 | 12.47
|  |  |  | 65.06 | 446.4 | 511.46

## VC 51-121 (hidden)
TB-507 400 KV (Twin) D/C Fatehgarh IV - Bhinmal Transmission Line
DPR and VISUAL CHART
DPR- |  |  | As per Approved Check Survey |  | No.Of Towers | Length | Foundation |  |  | Earthing | Tower Erection |  |  | Stringing
[7 empty] | Com | WIP | Bal | Com | Com | WIP | Bal | Com | WIP | Bal
|  |  | AP 51- AP 121 |  | 196 | 74.398 | 39 | 4 | 153 | 25 |  |  | 196 |  |  | 74.398
|  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9
[23 empty] | DA |  |  |  |  | DB |  |  |  |  | DC |  |  |  |  | DD
|  |  | 465.03 |  | 375.98 |  | 414.86 |  | 381.02 |  | 353.63 |  | 351.4 |  | 433.26 |  | 396.56 |  | 408.11 | 3579.85 |  | +0 | +3 | +6 | +9 |  | +0 | +3 | +6 | +9 |  | +0 | +3 | +6 | +9 |  | +0 | +3 | +6 | +9
[6 empty] | U/P | [15 empty] | 1 | 3 | 1 | 0 |  | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
|  | AP51 |  | 51/1 |  | 51/2 |  | 51/3 |  | AP52 |  | 52/1 |  | AP53 |  | AP54 |  | 54/1
|  | DD+18 |  | DA+3 |  | DA+0 |  | DA+3 |  | DB+0 |  | DA+6 |  | DD+0 |  | DC+00 |  | DA+3
[10 empty] | RC |  | RC
| 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19
|  | 425.22 |  | 420.54 |  | 340.56 |  | 336.52 |  | 375.99 |  | 303.41 |  | 448.76 |  | 393.09 |  | 407.8 |  | 206.06 | 3657.95
| 54/2 |  | 54/3 |  | AP55 |  | AP56 |  | 56/1 |  | 56/2 |  | 56/3 |  | 56/4 |  | 56/5 |  | AP57 |  |  | 1 | 1 | 3 | 0 |  | 0 | 0 | 0 | 2 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| DA+6 |  | DA+3 |  | DD+18 |  | DB+09 |  | DB+9 |  | DA+0 |  | DB+9 |  | DA+6 |  | DA+6 |  | DB+09
| Benching &RC |  | RC |  | RC |  | Benching &RC | [11 empty] | Benching &RC
| 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29
|  | 417.38 |  | 304.56 |  | 408.66 |  | 434.89 |  | 408.17 |  | 398.59 |  | 446.37 |  | 297.58 |  | 240.47 |  | 312.69 | 3669.36
| AP58 |  | AP59 |  | 59/1 |  | AP60 |  | 60/1 |  | 60/2 |  | 60/3 |  | AP61 |  | 61/1 |  | AP62
| DB+09 |  | DC+09 |  | DA+0 |  | DD+00 |  | DA+9 |  | DA+0 |  | DA+9 |  | DC+00 |  | DA+9 |  | DB+00 |  |  | 2 | 0 | 0 | 3 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[5 empty] | Benching | [7 empty] | RC
| 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39
|  | 347.88 |  | 379.25 |  | 398.7 |  | 439.06 |  | 381.53 |  | 379.71 |  | 426.3 |  | 387.14 |  |  |  | 423.77 | #REF!
| 62/1 |  | 62/2 |  | 62/3 |  | 62/4 |  | 62/5 |  | AP63 |  | 63/1 |  | AP64 |  | 64/1 |  | 64/2
| DA+0 |  | DA+0 |  | DA+9 |  | DA+6 |  | DA+6 |  | DC+00 |  | DA+0 |  | DC+09 |  | DA+9 |  | DA+9 |  |  | 3 | 0 | 2 | 3 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| RC |  |  |  | RC | [9 empty] | Benching &RC |  | RC |  | RC
| 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49
|  | 407.9 |  | 426.63 |  | 392.27 |  | 431.96 |  | 426.02 |  | 405.36 |  | 411.93 |  | 423.77 |  | 407.9 |  | 426.63
| F |  | F |  | F |  | F |  | F | [7 empty] | F |  | F
| Er |  |  |  | Er
| 64/3 |  | 64/4 |  | 64/5 |  | 64/6 |  | 64/7 |  | 65/0 |  | 65/1 |  | 66/0 |  | 66/1 |  | 66/2
| DA+9 |  | DA+9 |  | DA+9 |  | DA+3 |  | DA+3 |  | DD+0 |  | DB+09 |  | DD+0 |  | DA+9 |  | DA+0 |  | #REF! | 1 | 3 | 1 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 2 | 0 | 0 | 0
RC
| 50 |  | 51 |  | 52 |  | 53 |  | 54 |  | 55 |  | 56 |  | 57 |  | 58 |  | 59 |  | 60
|  | 392.27 |  | 431.96 |  | 426.02 |  | 405.36 |  | 411.93 |  | 350.33 |  | 378.3 |  | 416.82 |  | 371.85
| F |  | ROW
| 66/3 |  | 66/4 |  | 67/0 |  | 67/1 |  | 67/2 |  | AP68 |  | AP69 |  | 69/1 |  | 69/2 |  | 69/3 |  | 70/0
| DA+3 |  | DA+9 |  | DC+6 |  | DA+6 |  | DB+0 |  | DB+09 |  | DD+3 |  | DA+6 |  | DA+0 |  | DA+0 |  | DD+00 | 2 | 1 | 2 | 1 |  | 1 | 0 | 0 | 0 |  | 0 | 0 | 1 | 0 |  | 0 | 1 | 0 | 0
[5 empty] | RC | [11 empty] | Benching |  | RC |  | #REF!
| 61 |  | 62 |  | 63 |  | 64 |  | 65 |  | 66 |  | 67 |  | 68 |  | 69 |  | 70
|  | 392.27 |  | 431.96 |  | 426.02 |  | 405.36 |  | 411.93 |  | 350.33 |  | 378.3 |  | 416.82 |  | 371.85
F
| AP71 |  | 71/1 |  | 71/2 |  | 71/3 |  | AP72 |  | 72/1 |  | 72/2 |  | AP73 |  | 73/1 |  | 73/2
| DB+00 |  | DA+9 |  | DA+0 |  | DA+0 |  | DD+00 |  | DA+3 |  | DA+3 |  | DB+00 |  | DA+0 |  | DA+9 |  |  | 3 | 2 | 0 | 2 |  | 0 | 2 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | RC |  | Benching &RC |  | RC | [5 empty] | Benching & RC |  | CLEAR |  | 3994.99
| 71 |  | 72 |  | 73 |  | 74 |  | 75 |  | 76 |  | 77 |  | 78 |  | 79 |  | 80
|  | 385.17 |  | 345.19 |  | 332.38 |  | 393.62 |  | 387.95 |  | 340.35 |  | 393.12 |  | 328.54 |  | 398.52
| F |  |  |  | F |  |  |  | F |  | F |  | F |  | F |  | F |  | F
| Er |  |  |  | Er |  |  |  | Er |  | Er |  | Er |  | Er |  |  |  | Er
| 73/3 |  | AP74 |  | 74/1 |  | AP75 |  | 75/1 |  | 75/2 |  | 75/3 |  | 75/4 |  | 75/5 |  | 75/6
| DA+9 |  | DB+09 |  | DA+0 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  |  | 6 | 1 | 0 | 1 |  | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| CLEAR | [5 empty] | Benching |  | Benching |  | Benching &RC
| 81 |  | 82 |  | 83 |  | 84 |  | 85 |  | 86 |  | 87 |  | 88 |  | 89 |  | 90
[6 empty] | 388.46 |  | 380.96 |  | 374.03 |  | 351.96 |  | 395.64 |  | 414.76 |  | 401.93
| F |  |  |  | F |  |  |  | F |  | F |  | F |  | F |  | F
| Er |  |  |  | Er |  |  |  | Er |  | Er |  | Er |  | Er |  | Er
| 75/7 |  | AP76 |  | 76/1 |  | 77/0 |  | 77/1 |  | 77/2 |  | 77/3 |  | 77/4 |  | 77/5 |  | AP78
| DA+0 |  | DC+00 |  | DA+6 |  | DB+00 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+6 |  | DC+00 |  |  | 2 | 2 | 2 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[5 empty] | Clear | [5 empty] | Benching
| 91 |  | 92 |  | 93 |  | 94 |  | 95 |  | 96 |  | 97 |  | 98 |  | 99 |  | 100
|  | 385.54 |  |  |  | 351.18 |  | 441.06 |  | 387.5 |  | 372.63 |  | 415.3 |  | 424.58 |  | 391.7 |  | 410.47
[5 empty] | F | [5 empty] | F | [5 empty] | F
[5 empty] | Er | [5 empty] | Er | [5 empty] | Er
| 78/1 |  | AP79 |  | 79/1 |  | 79/2 |  | AP80 |  | 80/1 |  | AP81 |  | 81/1 |  | 81/2 |  | 81/3
| DA+3 |  | DD+00 |  | DA+9 |  | DA+0 |  | DB+03 |  | DA+9 |  | DB+09 |  | DA+0 |  | DA+3 |  | DA+0 |  |  | 3 | 2 | 0 | 2 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[5 empty] | RC |  | RC,Benching |  |  |  | Benching |  |  |  | Benching &RC
| 101 |  | 102 |  | 103 |  | 104 |  | 105 |  | 106 |  | 107 |  | 108 |  | 109 |  | 110
#REF!
415.03 |  | 416.87 |  |  |  | 426.47 |  | 396.98 |  | 429.38 |  | 403.83 |  | 384.63 |  | 380.68 |  | 354.53
| ROW | [11 empty] | F | [5 empty] | F
U/P
| 81/4 |  | 81/5 |  | AP82 |  | 82/1 |  | 82/2 |  | AP83 |  | 83/1 |  | AP84 |  | AP85 |  | 85/1
| DA+0 |  | DA+6 |  | DB+03 |  | DA+0 |  | DA+3 |  | DC+00 |  | DA+3 |  | DC+06 |  | DC+00 |  | DA+0 |  |  | 3 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 | 0 |  | 0 | 1 | 0 | 0
[7 empty] | RC | [11 empty] | CLEAR
| 111 |  | 112 |  | 113 |  | 114 |  | 115 |  | 116 |  | 117 |  | 118 |  | 119 |  | 120
3121.94
|  | 395.01 | #REF! |  |  | 380.77 |  | 411.81 |  | 432.08 |  | 256.87 |  | 412.4 |  | 382.17 |  | 452.74
|  |  | F |  | F |  |  |  | F |  | F
| AP86 |  | 86/1 |  | 86/2 |  | AP87 |  | 87/1 |  | 87/2 |  | AP88 |  | AP89 |  | 89/1 |  | AP90
| DD+00 |  | DA+6 |  | DA+0 |  | DC+00 |  | DA+3 |  | DA+9 |  | DC+00 |  | DC+00 |  | DA+9 |  | DC+00 |  |  | 1 | 1 | 1 | 2 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| CLEAR |  | CLEAR |  | CLEAR
| 121 |  | 122 |  | 123 |  | 124 |  | 125 |  | 126 |  | 127 |  | 128 |  | 129 |  | 130
#REF!
|  | 430.39 |  |  |  | 378.62 |  | 350.22 |  | 357.91 |  | 237.48 |  | 440.03 |  | 504 |  | 430.57
U/P
| 90/1 |  | AP91 |  | 91/1 |  | 91/2 |  | 91/3 |  | AP92 |  | AP93 |  | AP94 |  | AP95 |  | 95/1
| DA+9 |  | DD+00 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC+00 |  | DC+00 |  | DB+06 |  | DB+06 |  | DB+00 |  |  | 3 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| 131 |  | 132 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137 |  | 138 |  | 139 |  | 140 |  | 141
|  | 354.92 |  |  |  | 419.38 |  | 406.18 |  | 427.47 |  |  |  | 416.77 |  | 378.13 |  | 358.57 |  | 360.52
[5 empty] | F |  |  |  | F |  | F | [7 empty] | F
[9 empty] | Er |  | Er | [7 empty] | Er
| 95/2 |  | 95A/0 |  | 95A/1 |  | AP96 |  | 96/1 |  | 96/2 |  | AP97 |  | 97/1 |  | AP98 |  | AP98/1 |  | 98A/0
| DA+9 |  | DB+0 |  | DA+0 |  | DC+00 |  | DA+0 |  | DA+0 |  | DC+00 |  | DA+3 |  | DC+00 |  | DA+0 |  | DC+00 | 4 | 1 | 0 | 1 |  | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
RC
| 142 |  | 143 |  | 144 |  | 145 |  | 146 |  | 147 |  | 148 |  | 149 |  | 150 |  | 151 |  | 152
| F | [9 empty] | F
Er
| 98A/1 |  | 98B/0 |  | 98B/1 |  | 98B/2 |  | 99/0 |  | 99/1 |  | 99/2 |  | 99/3 |  | 99/4 |  | 99/5 |  | 99/6
| DA+0 |  | DD+00 |  | DA+0 |  | DCT+00 |  | DC+0 |  | DA+6 |  | DA+0 |  | DA+0 |  | DA+6 |  | DA+3 |  | DA+3 | 4 | 2 | 2 | 0 |  | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[5 empty] | RC | [9 empty] | RC
| 153 |  | 154 |  | 155 |  | 156 |  | 157 |  | 158 |  | 159 |  | 160 |  | 161 |  | 162 |  | 163
| AP99A |  | 99A/1 |  | 99A/2 |  | AP100 |  | 100/1 |  | AP101 |  | AP102 |  | 102/1 |  | 102/2 |  | AP103 |  | 103/1
| DB+00 |  | DA+0 |  | DA+0 |  | DC+00 |  | DA+6 |  | DD+06 |  | DD+3 |  | DA+0 |  | DA+0 |  | DC+0 |  | DA+6 | 4 | 0 | 2 | 0 |  | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 0 | 1 | 0 | 0
| 164 |  | 165 |  | 166 |  | 167 |  | 168 |  | 169 |  | 170 |  | 171 |  | 172 |  | 173 |  | 174
| AP104 |  | AP104A |  | AP104B |  | 104B/1 |  | 104B/2 |  | AP105 |  | 105/1 |  | AP106 |  | AP107 |  | 107/1 |  | 108/0
| DB+9 |  | DC+9 |  | DB+9 |  | DA+0 |  | DA+0 |  | DD+0 |  | DA+3 |  | DC+6 |  | DD+3 |  | DA+9 |  | DC+0 | 2 | 1 | 0 | 1 |  | 0 | 0 | 0 | 2 |  | 1 | 0 | 1 | 1 |  | 1 | 1 | 0 | 0
|  |  | RC |  | RC | [15 empty] | 1MRC
| 175 |  | 176 |  | 177 |  | 178 |  | 179 |  | 180 |  | 181 |  | 182 |  | 183 |  | 184 |  | 185
| AP109 |  | AP109A |  | AP110 |  | AP111 |  | AP112 |  | AP113 |  | AP113A |  | AP114 |  | 114/1 |  | AP115 |  | 115/1
| DC+3 |  | DB+6 |  | DC+0 |  | DB+9 |  | DC+9 |  | DD+0 |  | DC+0 |  | DC+0 |  | DA+9 |  | DC+0 |  | DB+9 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 | 2 |  | 4 | 1 | 0 | 1 |  | 1 | 0 | 0 | 0
[7 empty] | 3 MRC |  | 3 MRC | [9 empty] | 1MRC
| 186 |  | 187 |  | 188 |  | 189 |  | 190 |  | 191 |  | 192 |  | 193 |  | 194 |  | 195 |  | 196
| AP116 |  | 116/1 |  | AP117 |  | 117/1 |  | 117/2 |  | AP118 |  | AP119 |  | 119/1 |  | 119/2 |  | AP120 |  | 120/1
| DD+0 |  | DA+0 |  | DD+0 |  | DA+3 |  | DB+9 |  | DC+3 |  | DD+3 |  | DA+3 |  | DA+3 |  | DC+0 |  | DA+6 | 1 | 3 | 1 | 0 |  | 0 | 0 | 0 | 1 |  | 1 | 1 | 0 | 0 |  | 2 | 1 | 0 | 0
|  |  | Benching |  | RC
| 197 |  | 198 |  | 199 |  | 200 |  | 201 |  | 202 |  | 203 |  | 204 |  | 205 |  | 206 |  | 207
| AP121 |  | 122/0 |  | 122/1 |  | 122/2 |  | 123/0 |  | 124/0 |  | 125/0 |  | 125/1 |  | 125/2 |  | 125/3 |  | 126/0
| DD+0 |  | DC+6 |  | DA+3 |  | DA+3 |  | DC+0 |  | DC+3 |  | DC+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC+0 | 3 | 2 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 2 | 2 | 1 | 0 |  | 1 | 0 | 0 | 0
| 208 |  | 209 |  | 210 |  | 211 |  | 212 |  | 213 |  | 214 |  | 215 |  | 216 |  | 217 |  | 218
[22 empty] | 0 | 2 | 3 | 2 |  | 0 | 0 | 0 | 0 |  | 1 | 1 | 1 | 0 |  | 0 | 0 | 1 | 0
| 126/1 |  | 126/2 |  | 126/3 |  | 127/0 |  | 127/1 |  | 128/0 |  | 128/1 |  | 129/0 |  | 129/1 |  | 129/2 |  | 130/0
| DA+6 |  | DA+3 |  | DA+6 |  | DD+6 |  | DA+9 |  | DC+3 |  | DA+6 |  | DC+0 |  | DA+3 |  | DA+9 |  | DC+6
| 219 |  | 220 |  | 221 |  | 222 |  | 223 |  | 224 |  | 225 |  | 226 |  | 227 |  | 228 |  | 229
| 130/1 |  | 131/0 | [18 empty] | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
| DA+0 |  | DD+0
| 230 |  | 231 |  | 232 |  | 233 |  | 234 |  | 235 |  | 236 |  | 237 |  | 238 |  | 239 |  | 240
[22 empty] | 50 | 28 | 21 | 20 | 119 | 3 | 2 | 1 | 7 | 13 | 12 | 6 | 4 | 2 | 24 | 9 | 5 | 1 | 0 | 15
52
TSE
Manual
Total
Paying out/ Rough sag
[11 empty] | Tack welding completed | [5 empty] | Erection ROW
Erection Completed ------>
|  | Foundation completed ----> | [8 empty] | <------Insulator hosting
|  | Earthing completed -----> |  |  |  |  | U/P | [9 empty] | Erection Cleared
Road
[7 empty] | 325 | Span
[12 empty] | HT-D/C Power Line Crossing |  |  |  |  | Cart Track
| Transformer |  |  | ROW | ROW |  |  | Water Tank
| Temple |  |  | A+0 | Tower Type |  |  | LT Power Line Crossing |  |  |  | HT-S/C Power Line Crossing |  |  |  |  | Broad Gauge Railway
[8 empty] | 11 KV Line Crossing | [8 empty] | Line Crossing
| Hut |  |  | 1/0 | Location No. |  |  | 33 KV Line Crossing
| Bore & Handpump |  |  |  | Minor River Crossing | [6 empty] | Forest Stretch |  |  |  |  | SH Crossing
| Oil Pipe Line |  |  | RC | Raised Chimney |  |  | Major River Crossing |  |  |  | NH Crossing |  |  |  |  | Wild Life Sanctuary
3
3
3
3
3

## Sheet5 (hidden)
Sl.No. | Loc.No. | Tower Type |  | Tower Leg |  |  |  | Remarks
|  |  |  | A | B | C | D
1 | AP52 | DB+0 | 2 | 3 | 3 | 3 | 3
2 | 52/1 | DA+6 | 1 | 1 | 1 | 1 | 1
3 | 54/2 | DA+6 | Benching & RC Required | - | - | 1 | -
4 | 54/3 | DA+3 | 1 | 1 | 1 | 1 | 1
5 | AP55 | DD+18 | 3 | 3 | 3 | 3 | 3
6 | AP56 | DB+9 | Benching & RC Required | 3 | 3 | 3 | 3
7 | 57/0 | DB+9 | Benching & RC Required | - | 1 | 3 | -
8 | 60/3 | DA+9 | 2 | 3 | 3 | 3 | 3
9 | 62/1 | DA+0 | 1) Benching - A&D Legs, 2) C-Leg 1MRC, | - | - | 1 | -
10 | 62/3 | DA+9 | 3 | 3 | 3 | 3 | 3
11 | 64/0 | DC+9 | 1) Benching - A&D Legs, 2) C-Leg 1MRC, | - | - | 1 | -
12 | 64/1 | DA+9 | 3 | 3 | 3 | 3 | 3
13 | 64/2 | DA+9 | 1 | 1 | 1 | 1 | 1
14 | AP66 | DD+0 | 1 | 1 | 1 | 1 | 1
15 | AP67 | DC+6 | 1 | 1 | 1 | 1 | 1
16 | 69/3 | DA+0 | 1 | 1 | 1 | 1 | 1
17 | 71/3 | DA+0 | 1 | 1 | 1 | 1 | 1
18 | 72/0 | DD+0 | 1) ABC Benching, 2) C-Leg 1MRC,D-LEG-3MRC | - | - | 1 | 3
19 | 72/1 | DA+3 | 1) A&B Leg Benching, 2) C-Leg 1MRC 3) D-Leg 3MRC | - | - | 1 | 3
20 | 73/1 | DA+0 | 1) A-Leg Benching, C-Leg 2MRC & D-Leg 1MRC | - | - | 3 | 3
21 | 78/1 | DA+3 | 1 | 1 | 1 | 1 | 1
22 | 79/2 | DA+0 | 1 | 1 | 1 | 1 | 1
23 | AP80 | DB+3 | 1 | 1 | 1 | 1 | 1
24 | 81/1 | DA+0 | Benching & RC Required | - | 3 | 3 | -
25 | 82/1 | DA+0 | 1 | 1 | 1 | 1 | 1
26 | 97/1 | DA+3 | 1 | 1 | 1 | 1 | 1
27 | 98B/1 | DA+0 | 1 | 1 | 1 | 1 | 1
28 | 99/3 | DA+0 | 1 | 1 | 1 | 1 | 1
29 | AP104A | DC+9 | 3 | 3 | 3 | 3 | 3
30 | AP104B | DB+9 | 3 | 3 | 3 | 3 | 3
31 | AP108 | DC+0 | 1 | 1 | 1 | 1 | 1
32 | AP111 | DB+9 | 3 | 3 | 3 | 3 | 3
33 | AP112 | DC+9 | 2 | 3 | 3 | 3 | 3
34 | AP115 | DC+0 | 1 | 1 | 1 | 1 | 1

## Sheet3 (hidden)
TB-507 400 KV (Twin) D/C Fatehgarh IV - Bhinmal Transmission Line
DPR and VISUAL CHART
DPR- |  |  | As per Approved Check Survey |  | No.Of Towers | Length | Foundation |  |  | Earthing | Tower Erection |  |  | Stringing
[7 empty] | Com | WIP | Bal | Com | Com | WIP | Bal | Com | WIP | Bal
|  |  | AP 51- AP 121 |  | 171 | 74 | 34 | 3 | 134 | 21 |  |  | 171 |  |  | 74
|  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9
|  |  | 465.03 |  | 375.98 |  | 414.86 |  | 381.02 |  | 353.63 |  | 351.4 |  | 433.26 |  | 396.56 |  | 408.11 | 3579.85
|  | AP51 |  | 51/1 |  | 51/2 |  | 51/3 |  | AP52 |  | 52/1 |  | AP53 |  | AP54 |  | 54/1
|  | DD+18 |  | DA+3 |  | DA+0 |  | DA+3 |  | DB+0 |  | DA+6 |  | DD+0 |  | DC+00 |  | DA+3
[10 empty] | RC |  | RC
| 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19
|  | 425.22 |  | 420.54 |  | 340.56 |  | 336.52 |  | 375.99 |  | 303.41 |  | 448.76 |  | 393.09 |  | 407.8 |  | 206.06 | 3657.95
| 54/2 |  | 54/3 |  | AP55 |  | AP56 |  | 56/1 |  | 56/2 |  | 56/3 |  | 56/4 |  | 56/5 |  | AP57
| DA+6 |  | DA+3 |  | DD+18 |  | DB+09 |  | DB+9 |  | DA+0 |  | DB+9 |  | DA+6 |  | DA+6 |  | DB+09
| Benching &RC |  | RC |  | RC |  | Benching &RC |  |  |  | Benching Required | [5 empty] | Benching &RC |  | Benching &RC
| 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29
|  | 417.38 |  | 304.56 |  | 408.66 |  | 434.89 |  | 408.17 |  | 398.59 |  | 446.37 |  | 297.58 |  | 240.47 |  | 312.69 | 3669.36
| AP58 |  | AP59 |  | 59/1 |  | AP60 |  | 60/1 |  | 60/2 |  | 60/3 |  | AP61 |  | 61/1 |  | AP62
| DB+09 |  | DC+09 |  | DA+0 |  | DD+00 |  | DA+9 |  | DA+0 |  | DA+9 |  | DC+00 |  | DA+9 |  | DB+00
[5 empty] | Benching | [7 empty] | RC
| 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39
|  | 347.88 |  | 379.25 |  | 398.7 |  | 439.06 |  | 381.53 |  | 379.71 |  | 426.3 |  | 387.14 |  |  |  | 423.77 | #REF!
| 62/1 |  | 62/2 |  | 62/3 |  | 62/4 |  | 62/5 |  | AP63 |  | 63/1 |  | AP64 |  | 64/1 |  | 64/2
| DA+0 |  | DA+0 |  | DA+9 |  | DA+6 |  | DA+6 |  | DC+00 |  | DA+0 |  | DC+09 |  | DA+9 |  | DA+9
| RC |  |  |  | RC | [9 empty] | Benching &RC |  |  |  | RC
| 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49
|  | 407.9 |  | 426.63 |  | 392.27 |  | 431.96 |  | 426.02 |  | 405.36 |  | 411.93 |  | 423.77 |  | 407.9 |  | 426.63
| F |  | F | [13 empty] | F |  | F
U/P
| 64/3 |  | 64/4 |  | 64/5 |  | 64/6 |  | 64/7 |  | 65/0 |  | 65/1 |  | 66/0 |  | 66/1 |  | 66/2
| DA+9 |  | DA+9 |  | DA+9 |  | DA+3 |  | DA+3 |  | DD+0 |  | DB+09 |  | DD+0 |  | DA+9 |  | DA+0 |  | #REF!
RC
| 50 |  | 51 |  | 52 |  | 53 |  | 54 |  | 55 |  | 56 |  | 57 |  | 58 |  | 59 |  | 60
|  | 392.27 |  | 431.96 |  | 426.02 |  | 405.36 |  | 411.93 |  | 350.33 |  | 378.3 |  | 416.82 |  | 371.85
F
| 66/3 |  | 66/4 |  | 67/0 |  | 67/1 |  | 67/2 |  | AP68 |  | AP69 |  | 69/1 |  | 69/2 |  | 69/3 |  | 70/0
| DA+3 |  | DA+9 |  | DC+6 |  | DA+6 |  | DB+0 |  | DB+09 |  | DD+3 |  | DA+6 |  | DA+0 |  | DA+0 |  | DD+00
[5 empty] | RC | [11 empty] | Benching |  | RC |  | #REF!
| 61 |  | 62 |  | 63 |  | 64 |  | 65 |  | 66 |  | 67 |  | 68 |  | 69 |  | 70
|  | 392.27 |  | 431.96 |  | 426.02 |  | 405.36 |  | 411.93 |  | 350.33 |  | 378.3 |  | 416.82 |  | 371.85
F
| AP71 |  | 71/1 |  | 71/2 |  | 71/3 |  | AP72 |  | 72/1 |  | 72/2 |  | AP73 |  | 73/1 |  | 73/2
| DB+00 |  | DA+9 |  | DA+0 |  | DA+0 |  | DD+00 |  | DA+3 |  | DA+3 |  | DB+00 |  | DA+0 |  | DA+9
[7 empty] | RC |  | Benching &RC |  | RC | [5 empty] | Benching & RC |  | CLEAR |  | 3994.99
| 71 |  | 72 |  | 73 |  | 74 |  | 75 |  | 76 |  | 77 |  | 78 |  | 79 |  | 80
|  | 385.17 |  | 345.19 |  | 332.38 |  | 393.62 |  | 387.95 |  | 340.35 |  | 393.12 |  | 328.54 |  | 398.52
| F |  |  |  | F |  |  |  | F |  | F |  | F |  | F |  | F |  | F
| Er | [7 empty] | Er |  | Er |  | Er | [5 empty] | Er
| 73/3 |  | AP74 |  | 74/1 |  | AP75 |  | 75/1 |  | 75/2 |  | 75/3 |  | 75/4 |  | 75/5 |  | 75/6
| DA+9 |  | DB+09 |  | DA+0 |  | DC+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0
| CLEAR | [5 empty] | Benching |  | Benching |  | Benching &RC
| 81 |  | 82 |  | 83 |  | 84 |  | 85 |  | 86 |  | 87 |  | 88 |  | 89 |  | 90
[6 empty] | 388.46 |  | 380.96 |  | 374.03 |  | 351.96 |  | 395.64 |  | 414.76 |  | 401.93
| F |  |  |  | F |  |  |  | F |  | F |  | F |  | F |  | F
| Er | [7 empty] | Er | [5 empty] | Er |  | Er
| 75/7 |  | AP76 |  | 76/1 |  | 77/0 |  | 77/1 |  | 77/2 |  | 77/3 |  | 77/4 |  | 77/5 |  | AP78
| DA+0 |  | DC+00 |  | DA+6 |  | DB+00 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+6 |  | DC+00
[5 empty] | Clear | [5 empty] | Benching
| 91 |  | 92 |  | 93 |  | 94 |  | 95 |  | 96 |  | 97 |  | 98 |  | 99 |  | 100
|  | 385.54 |  |  |  | 351.18 |  | 441.06 |  | 387.5 |  | 372.63 |  | 415.3 |  | 424.58 |  | 391.7 |  | 410.47
[5 empty] | F | [5 empty] | F | [5 empty] | F
Er
| 78/1 |  | AP79 |  | 79/1 |  | 79/2 |  | AP80 |  | 80/1 |  | AP81 |  | 81/1 |  | 81/2 |  | 81/3
| DA+3 |  | DD+00 |  | DA+9 |  | DA+0 |  | DB+03 |  | DA+9 |  | DB+09 |  | DA+0 |  | DA+3 |  | DA+0
[5 empty] | Clear |  | RC,Benching |  |  |  | Benching |  |  |  | Benching &RC
| 101 |  | 102 |  | 103 |  | 104 |  | 105 |  | 106 |  | 107 |  | 108 |  | 109 |  | 110
#REF!
415.03 |  | 416.87 |  |  |  | 426.47 |  | 396.98 |  | 429.38 |  | 403.83 |  | 384.63 |  | 380.68 |  | 354.53
| ROW | [11 empty] | F | [5 empty] | F
U/P
| 81/4 |  | 81/5 |  | AP82 |  | 82/1 |  | 82/2 |  | AP83 |  | 83/1 |  | AP84 |  | AP85 |  | 85/1
| DA+0 |  | DA+6 |  | DB+03 |  | DA+0 |  | DA+3 |  | DC+00 |  | DA+3 |  | DC+06 |  | DC+00 |  | DA+0
[7 empty] | RC | [11 empty] | CLEAR
| 111 |  | 112 |  | 113 |  | 114 |  | 115 |  | 116 |  | 117 |  | 118 |  | 119 |  | 120
3121.94
|  | 395.01 | #REF! |  |  | 380.77 |  | 411.81 |  | 432.08 |  | 256.87 |  | 412.4 |  | 382.17 |  | 452.74
|  |  | F |  | F |  |  |  | F
U/P
| AP86 |  | 86/1 |  | 86/2 |  | AP87 |  | 87/1 |  | 87/2 |  | AP88 |  | AP89 |  | 89/1 |  | AP90
| DD+00 |  | DA+6 |  | DA+0 |  | DC+00 |  | DA+3 |  | DA+9 |  | DC+00 |  | DC+00 |  | DA+9 |  | DC+00
| CLEAR |  | CLEAR |  | CLEAR
| 121 |  | 122 |  | 123 |  | 124 |  | 125 |  | 126 |  | 127 |  | 128 |  | 129 |  | 130
#REF!
|  | 430.39 |  |  |  | 378.62 |  | 350.22 |  | 357.91 |  | 237.48 |  | 440.03 |  | 504 |  | 430.57
| 90/1 |  | AP91 |  | 91/1 |  | 91/2 |  | 91/3 |  | AP92 |  | AP93 |  | AP94 |  | AP95 |  | 95/1
| DA+9 |  | DD+00 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC+00 |  | DC+00 |  | DB+06 |  | DB+06 |  | DB+00
| 131 |  | 132 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137 |  | 138 |  | 139 |  | 140 |  | 141
|  | 354.92 |  |  |  | 419.38 |  | 406.18 |  | 427.47 |  |  |  | 416.77 |  | 378.13 |  | 358.57 |  | 360.52
[5 empty] | F |  |  |  | F |  | F
| 95/2 |  | 95A/0 |  | 95A/1 |  | AP96 |  | 96/1 |  | 96/2 |  | AP97 |  | 97/1 |  | AP98 |  | AP98/1 |  | 98A/0
| DA+9 |  | DB+0 |  | DA+0 |  | DC+00 |  | DA+0 |  | DA+0 |  | DC+00 |  | DA+3 |  | DC+00 |  | DA+0 |  | DC+00
RC
| 142 |  | 143 |  | 144 |  | 145 |  | 146 |  | 147 |  | 148 |  | 149 |  | 150 |  | 151 |  | 152
F
U/P
| 98A/1 |  | 98B/0 |  | 98B/1 |  | 98B/2 |  | 99/0 |  | 99/1 |  | 99/2 |  | 99/3 |  | 99/4 |  | 99/5 |  | 99/6
| DA+0 |  | DD+00 |  | DA+0 |  | DCT+00 |  | DC+0 |  | DA+6 |  | DA+0 |  | DA+0 |  | DA+6 |  | DA+3 |  | DA+3
[5 empty] | RC | [9 empty] | RC
| 153 |  | 154 |  | 155 |  | 156 |  | 157 |  | 158 |  | 159 |  | 160 |  | 161 |  | 162 |  | 163
| AP99A |  | 99A/1 |  | 99A/2 |  | AP100 |  | 100/1 |  | AP101 |  | AP102 |  | 102/1 |  | 102/2 |  | AP103 |  | 103/1
| DB+00 |  | DA+0 |  | DA+0 |  | DC+00 |  | DA+6 |  | DD+06 |  | DD+3 |  | DA+0 |  | DA+0 |  | DC+0 |  | DA+6
| 164 |  | 165 |  | 166 |  | 167 |  | 168 |  | 169 |  | 170 |  | 171 |  | 172 |  | 173 |  | 174
| AP104 |  | AP104A |  | AP104B |  | 104B/1 |  | 104B/2 |  | AP105 |  | 105/1 |  | AP106 |  | AP107 |  | 107/1 |  | 108/0
| DB+9 |  | DC+9 |  | DB+9 |  | DA+0 |  | DA+0 |  | DD+0 |  | DA+3 |  | DC+6 |  | DD+3 |  | DA+9 |  | DC+0
|  |  | RC |  | RC | [15 empty] | 1MRC
| 175 |  | 176 |  | 177 |  | 178 |  | 179 |  | 180 |  | 181 |  | 182 |  | 183 |  | 184 |  | 185
| AP109 |  | AP109A |  | AP110 |  | AP111 |  | AP112 |  | AP113 |  | AP113A |  | AP114 |  | 114/1 |  | AP115 |  | 115/1
| DC+3 |  | DB+6 |  | DC+0 |  | DB+9 |  | DC+9 |  | DD+0 |  | DC+0 |  | DC+0 |  | DA+9 |  | DC+0 |  | DB+9
[7 empty] | 3 MRC |  | 3 MRC | [9 empty] | 1MRC
| 186 |  | 187 |  | 188 |  | 189 |  | 190 |  | 191 |  | 192 |  | 193 |  | 194 |  | 195 |  | 196
| AP116 |  | 116/1 |  | AP117 |  | 117/1 |  | 117/2 |  | AP118 |  | AP119 |  | 119/1 |  | 119/2 |  | AP120 |  | 120/1
| DD+0 |  | DA+0 |  | DD+0 |  | DA+3 |  | DB+9 |  | DC+3 |  | DD+3 |  | DA+3 |  | DA+3 |  | DC+0 |  | DA+6
|  |  | Benching |  | RC
| 197 |  | 198 |  | 199 |  | 200 |  | 201 |  | 202 |  | 203 |  | 204 |  | 205 |  | 206 |  | 207
| AP121 |  | 122/0 |  | 122/1 |  | 122/2 |  | 123/0 |  | 124/0 |  | 125/0 |  | 125/1 |  | 125/2 |  | 125/3 |  | 126/0
| DD+0 |  | DC+6 |  | DA+3 |  | DA+3 |  | DC+0 |  | DC+3 |  | DC+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC+0
| 208 |  | 209 |  | 210 |  | 211 |  | 212 |  | 213 |  | 214 |  | 215 |  | 216 |  | 217 |  | 218
| 126/1 |  | 126/2 |  | 126/3 |  | 127/0 |  | 127/1 |  | 128/0 |  | 128/1 |  | 129/0 |  | 129/1 |  | 129/2 |  | 130/0
| DA+6 |  | DA+3 |  | DA+6 |  | DD+6 |  | DA+9 |  | DC+3 |  | DA+6 |  | DC+0 |  | DA+3 |  | DA+9 |  | DC+6
| 219 |  | 220 |  | 221 |  | 222 |  | 223 |  | 224 |  | 225 |  | 226 |  | 227 |  | 228 |  | 229
| 130/1 |  | 131/0
| DA+0 |  | DD+0
| 230 |  | 231 |  | 232 |  | 233 |  | 234 |  | 235 |  | 236 |  | 237 |  | 238 |  | 239 |  | 240
DA+0
| 50 | 28 | 21 | 20 | 119 | 3 | 2 | 1 | 7 | 13 | 12 | 6 | 4 | 2 | 24 | 9 | 5 | 1 | 0 | 15
SUMMERY
| TOT | QTY | TOT | QTY | TOT | QTY | TOT | QTY
| DA+0 | 50 | DB+0 | 3 | DC+0 | 12 | DD+0 | 9
| DA+3 | 28 | DB+3 | 2 | DC+3 | 6 | DD+3 | 5
| DA+6 | 21 | DB+6 | 1 | DC+6 | 4 | DD+6 | 1
| DA+9 | 20 | DB+9 | 7 | DC+9 | 2 | DD+9 | 0
|  | 119 |  | 13 |  | 24 | DD+18
DD+25
DD+30
15
3
3
3
3
3

## Tower Schedule (hidden)
NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE
Client : RAJASTHAN IV A POWER TRANSMISSION LTD.
CONTRACTOR : KEC INTERNATIONAL LIMITED
CHECK SURVEY
Tower Schedule from AP-75/0 to AP-92/0 (Section Length = 20.273 kms)
AS PER DETAILED SURVEY | [6 empty] | AS PER CHECK SURVEY
Sl. No | Twr No. | Tower Type | Raise Chimney | Deviation Angle (DMS) | Span (m) | Section Length (M) | Sl. No | Twr No. | Tower Type | Raise Chimney | Ground Cutting Length X Height | Deviation Angle (DMS) | Span (m) | Section Length (M) | Sum of Adjacent Span |  |  | Wind Span (m) | Weight Span (Cold) |  |  | Weight Span (Hot) |  |  | Major Crossings /Remarks | UTM Coordinate (Zone 43)
[15 empty] | Left | Right | Total |  | Left | Right | Total | Left | Right | Total |  | Easting | Northing | Elevation
1 | AP75 | DC+0 |  | 17°34'26"(RT) |  |  | 1 | AP75 | DC+0 |  | Benching Required | 00°00'00"(RT) |  |  | 385.17 | 345.19 | 730.36 | 365 | 197 | 128 | 325 | 196 | 147 | 343 |  | 782527.143 | 2837712.305 | 125.81
[5 empty] | 345.19 | 2920 | [6 empty] | 345.19 | 2920 | [10 empty] | Road,11Kv Line
2 | 75/1 | DA+0 |  |  |  |  | 2 | 75/1 | DA+0 | [5 empty] | 345.19 | 332.38 | 677.57 | 339 | 218 | 116 | 334 | 200 | 137 | 337 |  | 782723.206 | 2837428.199 | 133.297
[5 empty] | 332.38 | [7 empty] | 332.38 | [11 empty] | Water Tank
3 | 75/2 | DA+0 |  |  |  |  | 3 | 75/2 | DA+0 | [5 empty] | 332.38 | 393.62 | 726.01 | 363 | 217 | 288 | 505 | 197 | 252 | 449 |  | 782911.993 | 2837154.634 | 141.17
[5 empty] | 393.62 | [7 empty] | 393.62
4 | 75/3 | DA+3 |  |  |  |  | 4 | 75/3 | DA+3 | [5 empty] | 393.62 | 387.95 | 781.57 | 391 | 107 | 260 | 367 | 144 | 234 | 378 |  | 783135.564 | 2836830.667 | 121.365
[5 empty] | 387.95 | [7 empty] | 387.95 | [11 empty] | Cart Track
5 | 75/4 | DA+0 |  |  |  |  | 5 | 75/4 | DA+0 | [5 empty] | 387.95 | 340.35 | 728.3 | 364 | 129 | 196 | 325 | 156 | 186 | 342 |  | 783355.912 | 2836511.37 | 112.432
[5 empty] | 340.35 | [7 empty] | 340.35 | [11 empty] | 11kV Line
6 | 75/5 | DA+0 |  |  |  |  | 6 | 75/5 | DA+0 | [5 empty] | 340.35 | 393.12 | 733.47 | 367 | 145 | 176 | 321 | 156 | 185 | 341 |  | 783549.223 | 2836231.25 | 108.339
[5 empty] | 393.12 | [7 empty] | 393.12
7 | 75/6 | DA+0 |  |  |  |  | 7 | 75/6 | DA+0 | [5 empty] | 393.12 | 328.54 | 721.66 | 361 | 217 | 180 | 397 | 210 | 174 | 384 |  | 783772.509 | 2835907.696 | 112.147
[5 empty] | 328.54 | [7 empty] | 328.54
8 | 75/7 | DA+0 |  |  |  |  | 8 | 75/7 | DA+0 | [5 empty] | 328.54 | 398.52 | 727.05 | 364 | 149 | 240 | 389 | 156 | 224 | 380 |  | 783959.112 | 2835637.297 | 109.802
[5 empty] | 398.52 | [7 empty] | 398.52 | [11 empty] | 11kV Line
9 | AP76 | DC+0 |  | 16°40'52"(LT) |  |  | 9 | AP76 | DC+0 |  |  | 16°40'52"(LT) |  |  | 398.52 | 425.85 | 824.36 | 412 | 159 | 190 | 349 | 176 | 199 | 375 |  | 784185.462 | 2835309.303 | 101.99
[5 empty] | 425.85 | 835 | [6 empty] | 425.85 | 835 | [10 empty] | 11kV Line
10 | 76/1 | DA+6 |  |  |  |  | 10 | 76/1 | DA+6 | [5 empty] | 425.85 | 409.37 | 835.22 | 418 | 237 | 224 | 461 | 229 | 218 | 447 |  | 784517.764 | 2835042.992 | 101.179
[5 empty] | 409.37 | [7 empty] | 409.37
11 | AP77 | DB+0 |  | 12°41'03"(RT) |  |  | 11 | AP77 | DB+0 |  |  | 12°41'03"(RT) |  |  | 409.37 | 388.46 | 797.82 | 399 | 186 | 199 | 385 | 193 | 198 | 391 |  | 784837.208 | 2834786.986 | 103.07
[5 empty] | 388.46 | 2306 | [6 empty] | 388.46 | 2306
12 | 77/1 | DA+0 |  |  |  |  | 12 | 77/1 | DA+0 | [5 empty] | 388.46 | 380.96 | 769.42 | 385 | 190 | 193 | 383 | 192 | 192 | 384 |  | 785079.593 | 2834483.429 | 102.411
[5 empty] | 380.96 | [7 empty] | 380.96 | [11 empty] | 2Nos.11kV Line,Road
13 | 77/2 | DA+3 |  |  |  |  | 13 | 77/2 | DA+3 |  | Benching Required |  |  |  | 380.96 | 381.39 | 762.35 | 381 | 189 | 212 | 401 | 190 | 204 | 394 |  | 785317.301 | 2834185.728 | 99.05
[5 empty] | 381.39 | [7 empty] | 381.39 | [11 empty] | 11kV Line
14 | 77/3 | DA+0 |  |  |  |  | 14 | 77/3 | DA+0 | [5 empty] | 381.39 | 344.6 | 725.98 | 363 | 170 | 170 | 340 | 179 | 171 | 350 |  | 785555.277 | 2833887.693 | 98.293
[5 empty] | 344.6 | [7 empty] | 344.6 | [11 empty] | 11kV Line,Road
15 | 77/4 | DA+3 |  |  |  |  | 15 | 77/4 | DA+3 | [5 empty] | 344.6 | 395.64 | 740.24 | 370 | 175 | 205 | 380 | 174 | 203 | 377 |  | 785770.295 | 2833618.41 | 95.695
[5 empty] | 395.64 | [7 empty] | 395.64
16 | 77/5 | DA+6 |  |  |  |  | 16 | 77/5 | DA+6 | [5 empty] | 395.64 | 414.76 | 810.4 | 405 | 191 | 118 | 309 | 195 | 153 | 348 |  | 786017.163 | 2833309.237 | 91.436
[5 empty] | 414.76 | [7 empty] | 414.76 | [11 empty] | 11kV Line
17 | AP78 | DC+0 |  | 24°47'00"(LT) |  |  | 17 | AP78 | DC+0 |  |  | 24°47'00"(LT) |  |  | 414.76 | 401.93 | 816.69 | 409 | 298 | 296 | 594 | 264 | 259 | 523 |  | 786275.963 | 2832985.122 | 114.99
[5 empty] | 401.93 | 757 | [6 empty] | 401.93 | 757 | [10 empty] | WaterTank
18 | 78/1 | DA+3 | 1 |  |  |  | 18 | 78/1 | DA+3 | 1 |  |  |  |  | 401.93 | 354.95 | 756.88 | 379 | 106 | 225 | 331 | 144 | 207 | 351 |  | 786635.319 | 2832805.093 | 93.103
[5 empty] | 354.95 | [7 empty] | 354.95
19 | AP79 | DD+0 |  | 38°25'04"(RT) |  |  | 19 | AP79 | DD+0 |  |  | 38°25'04"(RT) |  |  | 354.95 | 425 | 779.95 | 390 | 130 | 142 | 272 | 149 | 169 | 318 |  | 786952.67 | 2832646.107 | 88.93
[5 empty] | 425 | 1192 | [6 empty] | 425 | 1192 | [10 empty] | 3No.11kV Line,Cart Track
20 | 79/1 | DA+9 |  |  |  |  | 20 | 79/1 | DA+9 | [5 empty] | 425 | 414 | 839 | 420 | 284 | 203 | 487 | 258 | 205 | 463 |  | 787132.097 | 2832260.84 | 94.695
[5 empty] | 414 | [7 empty] | 414
21 | 79/2 | DA+0 | 1 |  |  |  | 21 | 79/2 | DA+0 | 1 | Benching Required |  |  |  | 414 | 353.05 | 767.05 | 384 | 211 | 188 | 399 | 210 | 184 | 394 |  | 787306.881 | 2831885.544 | 103.516
[5 empty] | 353.05 | [7 empty] | 353.05 | [11 empty] | 11kV Line
22 | AP80 | DB+3 | 1 | 14°24'42"(LT) |  |  | 22 | AP80 | DB+3 | 1 |  | 14°24'42"(LT) |  |  | 353.05 | 441.06 | 794.11 | 397 | 165 | 156 | 321 | 170 | 179 | 349 |  | 787455.933 | 2831565.499 | 98.39
[5 empty] | 441.06 | 829 | [6 empty] | 441.06 | 829 | [10 empty] | Road
23 | 80/1 | DA+9 |  |  |  |  | 23 | 80/1 | DA+9 |  | Benching Required |  |  |  | 441.06 | 387.5 | 828.55 | 415 | 287 | 271 | 558 | 264 | 245 | 509 |  | 787735.789 | 2831224.603 | 108.033
[5 empty] | 387.5 | [7 empty] | 387.5 | [11 empty] | Cart Track,2Nos.11kV Line
24 | AP81 | DB+9 |  | 14°07'31"(RT) |  |  | 24 | AP81 | DB+9 |  |  | 14°07'31"(RT) |  |  | 387.5 | 372.63 | 760.12 | 380 | 117 | 157 | 274 | 145 | 168 | 313 |  | 787981.661 | 2830925.105 | 92.91
[5 empty] | 372.63 | 2400 | [6 empty] | 372.63 | 2400 | [10 empty] | Cart Track
25 | 81/1 | DA+0 |  |  |  |  | 25 | 81/1 | DA+0 |  | Benching & RC Required |  |  |  | 372.63 | 415.3 | 787.93 | 394 | 216 | 255 | 471 | 206 | 238 | 444 |  | 788140.665 | 2830588.105 | 107.482
[5 empty] | 415.3 | [7 empty] | 415.3 | [11 empty] | Cart Track,2Nos.WaterTank
26 | 81/2 | DA+3 |  |  |  |  | 26 | 81/2 | DA+3 | [5 empty] | 415.3 | 424.58 | 839.89 | 420 | 161 | 132 | 293 | 179 | 162 | 341 |  | 788317.879 | 2830212.509 | 94.983
[5 empty] | 424.58 | [7 empty] | 424.58
27 | 81/3 | DA+0 |  |  |  |  | 27 | 81/3 | DA+0 | [5 empty] | 424.58 | 391.7 | 816.29 | 408 | 294 | 205 | 499 | 264 | 202 | 466 |  | 788499.053 | 2829828.52 | 114.644
[5 empty] | 391.7 | [7 empty] | 391.7
28 | 81/4 | DA+0 |  |  |  |  | 28 | 81/4 | DA+0 | [5 empty] | 391.7 | 410.47 | 802.17 | 401 | 187 | 206 | 393 | 191 | 206 | 397 |  | 788666.198 | 2829474.268 | 112.98
[5 empty] | 410.47 | [7 empty] | 410.47 | [11 empty] | WaterTank,11kV Line,Road,33kV Line
29 | 81/5 | DA+6 |  |  |  |  | 29 | 81/5 | DA+6 | [5 empty] | 410.47 | 385.54 | 796.01 | 398 | 205 | 235 | 440 | 206 | 220 | 426 |  | 788841.348 | 2829103.047 | 106.942
[5 empty] | 385.54 | [7 empty] | 385.54 | [11 empty] | 2Nos. 11kV Line
30 | AP82 | DB+3 |  | 12°00'06"(LT) |  |  | 30 | AP82 | DB+3 |  |  | 12°00'06"(LT) |  |  | 385.54 | 418.31 | 803.85 | 402 | 151 | 214 | 365 | 167 | 213 | 380 |  | 789005.862 | 2828754.368 | 101.9
[5 empty] | 418.31 | 1242 | [6 empty] | 418.31 | 1242 | [10 empty] | Cart Track
31 | 82/1 | DA+0 | 1 |  |  |  | 31 | 82/1 | DA+0 | 1 |  |  |  |  | 418.31 | 421.47 | 839.79 | 420 | 205 | 230 | 435 | 207 | 224 | 431 |  | 789259.126 | 2828421.437 | 103.093
[5 empty] | 421.47 | [7 empty] | 421.47 | [11 empty] | 11kV Line
32 | 82/2 | DA+3 |  |  |  |  | 32 | 82/2 | DA+3 | [5 empty] | 421.47 | 401.98 | 823.45 | 412 | 192 | 233 | 425 | 199 | 222 | 421 |  | 789514.304 | 2828085.991 | 97.132
[5 empty] | 401.98 | [7 empty] | 401.98 | [11 empty] | 11kV Line
33 | AP83 | DC+0 |  | 14°21'11"(RT) |  |  | 33 | AP83 | DC+0 |  |  | 14°21'11"(RT) |  |  | 401.98 | 429.38 | 831.36 | 416 | 170 | 198 | 368 | 182 | 205 | 387 |  | 789757.679 | 2827766.061 | 93.67
[5 empty] | 429.38 | 833 | [6 empty] | 429.38 | 833 | [10 empty] | 2Nos.Cart Track
34 | 83/1 | DA+3 |  |  |  |  | 34 | 83/1 | DA+3 | [5 empty] | 429.38 | 403.83 | 833.21 | 417 | 233 | 191 | 424 | 227 | 196 | 423 |  | 789924.813 | 2827370.545 | 94.494
[5 empty] | 403.83 | [7 empty] | 403.83 | [11 empty] | Road
35 | AP84 | DC+6 |  | 17°28'54"(LT) |  |  | 35 | AP84 | DC+6 |  |  | 17°28'54"(LT) |  |  | 403.83 | 384.63 | 788.46 | 394 | 214 | 272 | 486 | 210 | 241 | 451 |  | 790082.003 | 2826998.562 | 93.69
[5 empty] | 384.63 | 385 | [6 empty] | 384.63 | 385 | [10 empty] | Cart Track
36 | AP85 | DC+0 |  | 26°43'01"(RT) |  |  | 36 | AP85 | DC+0 |  |  | 26°43'01"(RT) |  |  | 384.63 | 380.68 | 765.31 | 383 | 114 | 189 | 303 | 145 | 190 | 335 |  | 790331.234 | 2826705.605 | 85.28
[5 empty] | 380.68 | 735 | [6 empty] | 380.68 | 735 | [10 empty] | 11kV Line
37 | 85/1 | DA+0 |  |  |  |  | 37 | 85/1 | DA+0 | [5 empty] | 380.68 | 354.53 | 735.21 | 368 | 193 | 176 | 369 | 193 | 177 | 370 |  | 790421.216 | 2826335.71 | 85.764
[5 empty] | 354.53 | [7 empty] | 354.53 | [11 empty] | Cart Track
38 | AP86 | DD+0 |  | 40°12'50"(LT) |  |  | 38 | AP86 | DD+0 |  |  | 40°12'50"(LT) |  |  | 354.53 | 405.57 | 760.1 | 380 | 180 | 165 | 345 | 180 | 180 | 360 |  | 790505.015 | 2825991.23 | 86.03
[5 empty] | 405.57 | 1203 | [6 empty] | 405.57 | 1203
39 | 86/1 | DA+6 |  |  |  |  | 39 | 86/1 | DA+6 | [5 empty] | 405.57 | 416.87 | 822.45 | 411 | 241 | 246 | 487 | 227 | 233 | 460 |  | 790832.658 | 2825752.189 | 87.613
[5 empty] | 416.87 | [7 empty] | 416.87 | [11 empty] | 11kV Line,2No.Cart Track
40 | 86/2 | DA+0 |  |  |  |  | 40 | 86/2 | DA+0 | [5 empty] | 416.87 | 380.77 | 797.64 | 399 | 172 | 191 | 363 | 186 | 191 | 377 |  | 791169.429 | 2825506.488 | 86.123
[5 empty] | 380.77 | [7 empty] | 380.77 | [11 empty] | Cart Track
41 | AP87 | DC+0 |  | 23°52'06"(RT) |  |  | 41 | AP87 | DC+0 |  |  | 23°52'06"(RT) |  |  | 380.77 | 411.81 | 792.58 | 396 | 191 | 203 | 394 | 191 | 205 | 396 |  | 791477.031 | 2825282.069 | 85.95
[5 empty] | 411.81 | 1101 | [6 empty] | 411.81 | 1101 | [10 empty] | Cart Track,2Nos.11kV Line
42 | 87/1 | DA+3 |  |  |  |  | 42 | 87/1 | DA+3 | [5 empty] | 411.81 | 392.08 | 803.89 | 402 | 210 | 169 | 379 | 209 | 180 | 389 |  | 791683.05 | 2824925.492 | 83.796
[5 empty] | 392.08 | [7 empty] | 392.08 | [11 empty] | Cart Track
43 | 87/2 | DA+9 |  |  |  |  | 43 | 87/2 | DA+9 | [5 empty] | 392.08 | 296.87 | 688.95 | 345 | 224 | 191 | 415 | 213 | 174 | 387 |  | 791879.197 | 2824586.003 | 82.85
[5 empty] | 296.87 | [7 empty] | 296.87 | [11 empty] | Cart Track , Benching Required 1m depth & 5m Length
44 | AP88 | DC+0 |  | 24°54'04"(RT) |  |  | 44 | AP88 | DC+0 |  |  | 24°54'04"(RT) |  |  | 296.87 | 412.4 | 709.27 | 355 | 107 | 209 | 316 | 124 | 209 | 333 |  | 792027.714 | 2824328.95 | 85.77
[5 empty] | 412.4 | 412 | [6 empty] | 412.4 | 412
45 | AP89 | DC+0 |  | 24°07'20"(LT) |  |  | 45 | AP89 | DC+0 |  |  | 24°07'20"(LT) |  |  | 412.4 | 382.17 | 794.57 | 397 | 204 | 107 | 311 | 206 | 137 | 343 |  | 792064.495 | 2823918.194 | 85.31
[5 empty] | 382.17 | 835 | [6 empty] | 382.17 | 835 | [10 empty] | Road,Cart Track
46 | 89/1 | DA+9 |  |  |  |  | 46 | 89/1 | DA+9 | [5 empty] | 382.17 | 452.74 | 834.91 | 418 | 276 | 266 | 542 | 247 | 253 | 500 |  | 792251.169 | 2823584.714 | 92.75
[5 empty] | 452.74 | [7 empty] | 452.74 | [11 empty] | 2Nos.11kV Line
47 | AP90 | DC+0 |  | 17°57'57"(RT) |  |  | 47 | AP90 | DC+0 |  |  | 17°57'57"(RT) |  |  | 452.74 | 420.21 | 872.94 | 437 | 188 | 205 | 393 | 202 | 207 | 409 |  | 792472.311 | 2823189.661 | 92.68
[5 empty] | 420.21 | 815 | [6 empty] | 420.21 | 815
48 | 90/1 | DA+9 |  |  |  |  | 48 | 90/1 | DA+9 | [5 empty] | 420.21 | 395.01 | 815.22 | 408 | 216 | 252 | 468 | 215 | 233 | 448 |  | 792554.457 | 2822777.562 | 85.094
[5 empty] | 395.01 | [7 empty] | 395.01 | [11 empty] | 2Nos. WaterTank,11kV Line,Cart Track
49 | AP91 | DD+0 |  | 38°03'06"(LT) |  |  | 49 | AP91 | DD+0 |  |  | 38°03'06"(LT) |  |  | 395.01 | 386.74 | 781.75 | 391 | 143 | 197 | 340 | 164 | 196 | 360 |  | 792631.678 | 2822390.172 | 83.39
[5 empty] | 386.74 | 1473 | [6 empty] | 386.74 | 1473
50 | 91/1 | DA+0 |  |  |  |  | 50 | 91/1 | DA+0 | [5 empty] | 386.74 | 378.62 | 765.36 | 383 | 191 | 198 | 389 | 192 | 195 | 387 |  | 792924.985 | 2822138.111 | 83.029
[5 empty] | 378.62 | [7 empty] | 378.62
51 | 91/2 | DA+0 |  |  |  |  | 51 | 91/2 | DA+0 | [5 empty] | 378.62 | 350.22 | 728.84 | 364 | 181 | 228 | 409 | 185 | 207 | 392 |  | 793212.14 | 2821891.335 | 81.543
[5 empty] | 350.22 | [7 empty] | 350.22 | [11 empty] | Cart Track,11kV Line
52 | 91/3 | DA+0 |  |  |  |  | 52 | 91/3 | DA+0 | [5 empty] | 350.22 | 357.91 | 708.12 | 354 | 122 | 184 | 306 | 144 | 182 | 326 |  | 793477.75 | 2821663.077 | 72.815
[5 empty] | 357.91 | [7 empty] | 357.91
53 | AP92 | DC+0 |  | 15°43'35"(LT) |  |  | 53 | AP92 | DC+0 |  |  | 00°00'00"(LT) |  |  | 357.91 | 237.48 | 595.38 | 298 | 174 | 165 | 339 | 177 | 140 | 317 |  | 793749.192 | 2821429.805 | 71.78
Summary of Tower Quantities
|  |  |  | As per Detail survey |  |  |  |  | As per Check Survey
|  |  |  | Twr Type |  | Qty in Nos |  |  | Twr Type |  | Qty in Nos
|  |  |  | DA+0 | = | 18 |  |  | DA+0 | = | 18
|  |  |  | DA+3 | = | 8 |  |  | DA+3 | = | 8
|  |  |  | DA+6 | = | 4 |  |  | DA+6 | = | 4
|  |  |  | DA+9 | = | 5 |  |  | DA+9 | = | 5
|  |  |  | DB+0 | = | 1 |  |  | DB+0 | = | 1
|  |  |  | DB+3 | = | 2 |  |  | DB+3 | = | 2
|  |  |  | DB+6 | = | 0 |  |  | DB+6 | = | 0
|  |  |  | DB+9 | = | 1 |  |  | DB+9 | = | 1
|  |  |  | DC+0 | = | 10 |  |  | DC+0 | = | 10
|  |  |  | DC+3 | = | 0 |  |  | DC+3 | = | 0
|  |  |  | DC+6 | = | 1 |  |  | DC+6 | = | 1
|  |  |  | DC+9 | = | 0 |  |  | DC+9 | = | 0
|  |  |  | DD+0 | = | 3 |  |  | DD+0 | = | 3
|  |  |  | DD+3 | = | 0 |  |  | DD+3 | = | 0
|  |  |  | DD+6 | = | 0 |  |  | DD+6 | = | 0
|  |  |  | DD+9 | = | 0 |  |  | DD+9 | = | 0
|  |  |  | DD+18 | = | 0 |  |  | DD+18 | = | 0
|  |  |  | DD+25 | = | 0 |  |  | DD+25 | = | 0
|  |  |  | DD+30 | = | 0 |  |  | DD+30 | = | 0
|  |  |  | Total | = | 53 |  |  | Total | = | 53
FOR KEC INTERNATIONAL LTD | [13 empty] | FOR RAJASTHAN IV A POWER TRANSMISSION LTD.
SURVEYED BY: |  |  |  |  | CHECKED BY: |  |  |  | SUBMITTED BY: |  |  |  |  | CHECKED BY: |  |  |  |  | RECOMMENDED BY: | [5 empty] | APPROVED BY:

## Visual Chart
NAME OF PROJECT : FATEGARH III-BEAWAR 765KV D/C TRANSMISSION LILO LINE
Client : RAJASTHAN IV A POWER TRANSMISSION LTD.
AGENCY : KEC INTERNATIONAL LIMITED
PROGRESS AT A GLANCE | [19 empty] | AS ON |  | 2026-03-20 10:53
Sl. No. | Activity |  |  | UoM | LOOP IN | [5 empty] | LOOP OUT | [5 empty] | Total Quantity |  | Total Balanced |  | Remarks
[5 empty] | Final Quantity |  | Completed |  | Balanced |  | Final Quantity |  | Completed |  | Balanced | [5 empty] | LOOP IN WIP
1 | Detail survey |  |  | Kms. | 7.556 |  | 7.556 |  | 0 |  | 7.922 |  | 7.922 |  | 0 |  | 15.478 |  | 0 |  | FDN WIP LI : 1/0, 5/2
2 | Check survey |  |  | Kms. | 7.556 |  | 7.556 |  | 0 |  | 7.922 |  | 7.922 |  | 0 |  | 15.478 |  | 0
3 | CS Approval |  |  | Kms. | 7.556 |  | 7.556 |  | 0 |  | 7.922 |  | 7.922 |  | 0 |  | 15.478 |  | 0
4 | Soil Investigation |  |  | Loc | 11 |  | 11 |  | 0 |  | 15 |  | 15 |  | 0 |  | 26 |  | 0
5 | Foundation |  |  | Loc | 20 |  | 4 |  | 16 |  | 23 |  | 8 |  | 15 |  | 43 |  | 31 |  | LOOP OUT WIP
6 | Earthing |  |  | Loc | 20 |  | 1 |  | 19 |  | 23 |  | 2 |  | 21 |  | 43 |  | 40 |  | FDN WIP LO : 7/0
7 | Erection |  |  | Loc | 20 |  |  |  | 20 |  | 23 |  |  |  | 23 |  | 43 |  | 43
8 | Tack Welding |  |  | Nos. | 20 |  |  |  | 20 |  | 23 |  |  |  | 23 |  | 43 |  | 43
9 | Stringing(P/0) |  |  | Kms. | 7.556 |  |  |  | 7.556 |  | 7.922 |  |  |  | 7.922 |  | 15.478 |  | 15.478
10 | Stringing (F/S) |  |  | Kms. | 7.556 |  |  |  | 7.556 |  | 7.922 |  |  |  | 7.922 |  | 15.478 |  | 15.478
LOOP IN
Existing 10/4 |  | 1/0 |  | 2/0 |  | 2A/0 |  | 3/0 |  | 3A/0 |  | 3A/1 |  | 3B/0 |  | 4/0 |  | 4/1 |  | 4/2 |  | 4/3
| 200 |  | 132 |  | 358 |  | 344 |  | 398 |  | 420 |  | 421 |  | 418 |  | 407 |  | 415 |  | 410 |  | 397
Taping point SPTL |  | DD60+0 |  | DD60+0 (Aux. X-arm) |  | DD45+0 |  | DD60+0 |  | DD45+3 |  | DB1+6 | 841 | DC2+3 |  | DD45+0 |  | DA+3 |  | DA+3 |  | DA+3
4/4 |  | 4/5 |  | 5/0 |  | 5/1 |  | 5/2 |  | 6/0 |  | 6/1 |  | 6/2 |  | 7/0 |  | GANTRY
| 388 |  | 400 |  | 365 |  | 387 |  | 365 |  | 374 |  | 381 |  | 366 |  | 214
DA+0 |  | DA+0 | 2029 | DC2+0 |  | DA+0 |  | DA+0 | 1117 | DD45+0 |  | DA+0 |  | DA+0 | 1121 | DE+9 (Aux. X-arm)
LOOP OUT
Gantry |  | 1/0 |  | 1/1 |  | 1/2 |  | 2/0 |  | 2/1 |  | 2/2 |  | 2/3 |  | 2/4 |  | 2/5 |  | 3/0 |  | 3/1
| 143 |  | 384 |  | 317 |  | 297 |  | 367 |  | 343 |  | 299 |  | 384 |  | 356 |  | 336 |  | 416 |  | 417
Gantry |  | DE+3 |  | DA-3 |  | DA-3 | 998 | DC1+0 |  | DA+0 |  | DA-3 |  | DA+0 |  | DA+3 |  | DA-3 | 2085 | DC1+0 |  | DA+3
3/2 |  | 3/3 |  | 3/4 |  | 3/5 |  | 4/0 |  | 4/1 |  | 4/2 |  | 4/3 |  | 5/0 |  | 5A/0 |  | 6/0 |  | 7/0
| 398 |  | 417 |  | 355 |  | 367 |  | 362 |  | 362 |  | 365 |  | 319 |  | 368 | 281 | 222 | 137 | 138 |  | 192
DA+0 |  | DA+3 |  | DA+0 |  | DA-3 | 2370 | DD60+0 |  | DA+0 |  | DA+0 |  | DA+0 | 1408 | DD45+0 |  | DC2+0 |  | DD60+0 |  | DD60+0
Existing 10/6 | [10 empty] | Stringing WIP |  |  |  | Stringing Complete
[10 empty] | Erection WIP |  |  |  | Erection Complete |  |  |  | Tack Welding
[10 empty] | Foundation WIP |  |  |  | Foundation Complete |  |  |  | Earthing
Taping point SPTL

## L2 Vs Actual Progress Chart (2) (hidden)
NAME OF LINE: 400kV Transmisison Line Fatehgarh IV to Bhinmal
As Per L2
Sl. No. | ACTIVITY | Responsibility | Sch. Start date | Sch. Finish date | Days | Unit | Quantity | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26 | Feb'26 | Mar'26 | Apr'26 | May'26 | June'26
[8 empty] | M0 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18
1 | Notice of Award | KEC & Apraava | 2024-12-06 | 2026-06-05 | 546
Services
1 | Establishment of site office | KEC | 2024-12-16 | 2025-01-15 | 30 | LS
| Check Survey Submission & Approval | KEC & Apraava | 2025-01-05 | 2025-04-15 | 100 | Kms. | 184 | M1: 20; M2: 60; M3: 60; M4: 44
5.a | ROW clearance and front avaibility for Civil foundation | Apraava | 25.12.24 | 30.12.25 | #VALUE! | Loc. | 508 | 5 | 35 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 45 | 48 | 50 | 45
5.b | Foundation Work execution | KEC | 2025-01-07 | 2026-01-26 | 384 | Loc. | 508 |  | 35 | 40 | 40 | 40 | 40 | 40 | 30 | 25 | 25 | 48 | 45 | 50 | 48
Note | ROW / Way leave clearance / Forest clearance / Tree Cutting clearance / any other Statutory clearance to be arranged suitably ahead of respective work schedule by
Any delay due to ROW / Statutory approvals / Railway, Forest, NHAI , etc shall be on account of Apraava.
The L2 schedule is formulated considering average rainfall / heat in these areas, any unprecedented rain / heat waves will have an impact on overall completion schedule.
Actual Done
Sl. No. | ACTIVITY | Responsibility | Sch. Start date | Sch. Finish date | Days | Unit | Quantity | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26 | Feb'26 | Mar'26 | Apr'26 | May'26 | June'26
[8 empty] | M0 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18
1 | Notice of Award | KEC & Apraava | 2024-12-06 | 2026-06-05 | 546
Services
1 | Establishment of site office | KEC | 2024-12-16 | 2025-01-15 | 30 | LS |  | M1: 100%
| Check Survey Submission & Approval | KEC & Apraava | 2025-01-05 | 2025-04-15 | 100 | Kms. | 184 | M1: 28
5.a | ROW clearance and front avaibility for Civil foundation | Apraava | 25.12.24 | 30.12.25 | #VALUE! | Loc. | 508 | M1: 4
5.b | Foundation Work execution | KEC | 2025-01-07 | 2026-01-26 | 384 | Loc. | 508 | M1: 2; M2: 20; M3: 16; M4: 13; M5: 9
Formulas:
Sch. Finish date = [Sch. Start date]+30
Sch. Finish date = [Sch. Start date]+364+20

## Sheet4 (hidden)
Activity | As Per L2
| Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26 | Feb'26 | Mar'26 | Apr'26 | May'26 | June'26
Check Survey (Kms) |  | 20 | 60 | 60 | 44
Actual Progress |  | 28
Foundation (Nos) |  | 35 | 40 | 40 | 40 | 40 | 40 | 30 | 25 | 25 | 48 | 45 | 50 | 48
ROW Front Clearence | 5 | 35 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 45 | 48 | 50 | 45
Actual Foundation Completed (Nos) |  | 3
WIP |  | 2
Work Stopped
Front Availaibility |  | 8